## Summary
WMP Initiative | Project | 2020 | 2021 | 2022
Distribution communications reliability improvements | Trans Fiber Links HFTD | 4290607.6536 | 5084960 | 6190960
Distribution communications reliability improvements | LTE | 31182129.1931 | 45243360.1966 | 64754736.8536
Total |  | 35472736.8466 | 50328320.1966 | 70945696.8536
Note: Costs above are direct CPUC costs only

## Trans. Fiber Links -2020
19134 Fiber Programs
2020 Actuals by Program
(Capital Expenditures, Direct Costs $ Only)
CAPEX ($M)
Category | Fiber
Engineering/Design | 212.1217
Project Management | 643.5911
Construction | 3168.2365
Material | 266.6582
Total Direct CAPEX $ | 4290.6077

## Trans. Fiber Links - 2021-2022
Fiber 2021 - Budget by Category
Miles
Engineering/Design/Project Management | 35
Construction | 47
Engineering/Design/Project Management | 29056.9143 | 20%
Construction | 80061.0723 | 74%
Material | 6491.4383 | 6%
Direct Cost (per mile) | 115609.4249 | 100%
| Miles | Direct - $'s
Engineering/Design/Project Management | 35 | 1016992
Construction | 47 | 3762870.4
Material | 47 | 305097.6
Total Direct Cost |  | 5084960
Fiber 2022 - Budget by Category
Miles
Engineering/Design/Project Management | 42.61
Construction | 57.22
Engineering/Design/Project Management | 29056.9143 | 20%
Construction | 80061.0723 | 74%
Material | 6491.4383 | 6%
Direct Cost (per mile) | 115609.4249 | 100%
| Miles | Direct - $'s
Engineering/Design/Project Management | 42.61 | 1238115.1177
Construction | 57.22 | 4581094.5593
Material | 57.22 | 371440.0994
Total Direct Cost |  | 6190649.7764

## LTE
2021 WMP Filing LTE | Actual $M Sum of 2020 | Forecast $M Sum of 2021 | Forecast $M Sum of 2022
19873/19872
Spectrum | 21.3 | 20 | 26.3
Design & Program Mgmt | 10 | 17.6 | 31.5
Implementation | 5 | 12 | 15.5
Contingency | 0 | 3 | 2
Total | 36.3 | 52.6 | 75.3
CPUC Allocation (86%) | 31.182 | 45.243 | 64.754