## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | SDGE
Report Year |  | 2021
Report Quarter |  | Q1
Submission Date |  | 2021-05-03
Definition of fields
| Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
| I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
| N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail
SDGE | 2021-05-03 | Risk Assessment & Mapping | 5.3.1. | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment |  | 1 | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment - WRRM Ops (7.3.1.1) |  | SDGE_Risk Assessment & Mapping_A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment __2021 | 176 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to enhance WRRM-Ops throughout 2021. Enhancements planned for 2021 include upgrading fuel moisture inputs into the fire behavior modeling, upgrading the forecaster interface, and incorporating the data into a PSPS decision support tool. | SDG&E remains focused on the inititative to enhance WRRM-Ops throughout 2021. An upgraded forecaster interface has already been installed to assist our SME assess and analyze any wildfire activity in 2021. |  |  |  | In Progress
SDGE | 2021-05-03 | Risk Assessment & Mapping | 5.3.1. | Climate-driven risk map and modelling based on various relevant weather scenarios |  | 2 | Climate-driven risk map and modelling based on various relevant weather stations (7.3.1.2) |  | SDGE_Risk Assessment & Mapping_Climate-driven risk map and modelling based on various relevant weather scenarios __2021 | 178 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Risk Assessment & Mapping | 5.3.1. | Ignition probability mapping showing the probability of ignition along the electric lines and equipment |  | 3 | Ignition probability mapping (7.3.1.3) |  | SDGE_Risk Assessment & Mapping_Ignition probability mapping showing the probability of ignition along the electric lines and equipment __2021 | 178 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Risk Assessment & Mapping | 5.3.1. | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact |  | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact (7.3.1.4) |  | SDGE_Risk Assessment & Mapping_Initiative mapping and estimation of wildfire and PSPS risk-reduction impact __2021 | 178 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Risk Assessment & Mapping | 5.3.1. | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment |  | 5 | Match drop simulations (7.3.1.5) |  | SDGE_Risk Assessment & Mapping_Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment __2021 | 178 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Risk Assessment & Mapping | 5.3.1. | Other | Weather-driven risk map and modelling | Weather-driven risk map and modelling | Weather-driven risk map and modelling (7.3.1.6) |  | SDGE_Risk Assessment & Mapping_Weather-driven risk map and modelling__2021 | 178 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Advanced weather monitoring and weather stations |  | 1 | Advanced weather monitoring and weather stations (7.3.2.1) | WX | SDGE_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _WX_2021 | 179 | Weather stations (upgrades) | 25 | 0 | 10 | 17 | 25 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Continuous monitoring sensors |  | 2 | Continuous monitoring sensors (7.3.2.2) |  | SDGE_Situational Awareness & Forecasting_Continuous monitoring sensors __2021 | 180 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Fault indicators for detecting faults on electric lines and equipment |  | 3 | Fault indicators for detecting faults on electric lines and equipment - Wireless Fault Indicators (7.3.2.3) | WFI | SDGE_Situational Awareness & Forecasting_Fault indicators for detecting faults on electric lines and equipment _WFI_2021 | 180 | Wireless fault indicators | 500 | 10 | 86 | 400 | 500 | 10 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Forecast of a fire risk index, fire potential index, or similar (7.3.2.4) |  | SDGE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar __2021 | 183 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Other | Fire science and climate adaptation department | Fire science and climate adaptation department | Fire science and climate adaptation department (7.3.2.4.1) |  | SDGE_Situational Awareness & Forecasting_Fire science and climate adaptation department__2021 | 183 | Cameras | 17 | 0 | 5 | 10 | 17 | 0 |  |  |  | The FS&CA Department plans to continue establishing long-lasting partnerships with academia to create opportunities to advance fire science and climate science while doing our part to educate the next generation of utility wildfire subject matter expertise. | As planned, the FSCA department has been working very closely and establishing long-term partnerships with academia to conitnue to push forward weather science, fire sciene and climate science. Specific academic partners in 2021 in Scripps Institution of Oceanography, San Jose State University and the San Diego Supercomputing Center. |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Other | Fire potential index | Fire potential index | Fire potential index (7.3.2.4.2) |  | SDGE_Situational Awareness & Forecasting_Fire potential index__2021 | 184 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E will continue to prioritize the integration of the FPI into its operational decision-making to mitigate wildfire potential. Additionally, SDG&E’s meteorology team consists of experts in fire science and data science who will continue to conduct daily verification of the FPI tool. Through the verification process of the FPI, any instance of the index not performing as expected will be investigated, leading to improvements by the fire science team. | SDG&E has continued to prioritize the advancement and continuous improvement of the Fie Potential Index in 2021. Specifically, in addition to the daily verification conducted by SDG&E SMEs, a Capstone Team of graduate students at the San Diego Supercomputer Center (SDSC) have initiated a project to closly analyze index performance in an effort to recommend potential improvements. |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Other | Santa Ana wildfire threat index | Santa Ana wildfire threat index | Santa Ana wildfire threat index (7.3.2.4.3) |  | SDGE_Situational Awareness & Forecasting_Santa Ana wildfire threat index__2021 | 185 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E will continue to work with academia and the fire agencies to further develop fire science for integration into SAWTI. | SDG&E has continued to generate the SAWTI data daily and is sending the information to the fire agencies. An addition in 2021 is that SDG&E is working towards leveraging the San Diego Supercomputer Center (SDSC) to help transfer the data to the fire agencies. |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Other | High-performance computing infrastructure | High-performance computing infrastructure | High-performance computing infrastructure (7.3.2.4.4) |  | SDGE_Situational Awareness & Forecasting_High-performance computing infrastructure__2021 | 187 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E intends to maintain and update this program to stay aligned with the latest computing technology and intends to share all the data that is generated with the wildfire community. SDG&E intends to work closely with the San Diego Supercomputing Center to closely monitor data science advancements to ensure that this program remains highly capable of providing the advanced analytics required to operate the utility of today and of the future. | SDG&E's High Performance Computing infrastructure has been performing as planned and designed in 2021. Operationally, several weather models are run twice daily to generate detainled wind forecast, the FPI, the SAWTI as additional products to support utility operations. All the data generated is made publicly availiable through the San Diego Supercomputer Center (SDSC). |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions (7.3.2.5) |  | SDGE_Situational Awareness & Forecasting_Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions __2021 | 188 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E will continue to integrate the latest risk assessments and scientific understanding to the deployment of observers during high-risk events to try to place observers in the best place to mitigate risk. | SDG&E remains committed to continously improving the science that is integrated into its risk assessment tools. This remains the case in 2021 and these tools will be used in 2021 during high-risk events to try to place observers in the best place to mitigate risk. |  |  |  | In Progress
SDGE | 2021-05-03 | Situational Awareness & Forecasting | 5.3.2. | Weather forecasting and estimating impacts on electric lines and equipment |  | 6 | Weather forecasting and estimating impacts on electric lines and equipment (7.3.2.6) |  | SDGE_Situational Awareness & Forecasting_Weather forecasting and estimating impacts on electric lines and equipment __2021 | 189 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Capacitor maintenance and replacement program |  | 1 | Capacitor maintenance and replacement program - SCADA Capacitors (7.3.3.1) | Cap | SDGE_Grid Design & System Hardening_Capacitor maintenance and replacement program _Cap_2021 | 189 | SCADA capacitors | 32 | 15 | 26 | 32 | 32 | 21 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault (7.3.3.2) |  | SDGE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault __2021 | 191 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Covered conductor installation |  | 3 | Covered conductor installation - Distribution OH Hardening - Covered Conductor (7.3.3.3) | FIRM-CC | SDGE_Grid Design & System Hardening_Covered conductor installation _FIRM-CC_2021 | 191 | Miles | 20 | 0 | 1 | 7 | 20 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Covered conductor maintenance |  | 4 | Covered conductor maintenance (7.3.3.4) |  | SDGE_Grid Design & System Hardening_Covered conductor maintenance __2021 | 194 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Crossarm maintenance, repair, and replacement |  | 5 | Crossarm maintenance, repair, and replacement (7.3.3.5) |  | SDGE_Grid Design & System Hardening_Crossarm maintenance, repair, and replacement __2021 | 194 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | Distribution pole replacement and reinforcement, including with composite poles - Pole Replacement and Reinforcement (7.3.3.6) |  | SDGE_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles __2021 | 194 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue its mandated and enhanced inspection programs over the next 10 years. Regular inspections and subsequent remediations are a critical piece of preventing potential equipment failures, faults, and ignitions. Expected structure replacement forecasts are adjusted annually based on the latest inspection data results, and the location and number of assets contained in specific inspection cycles. | SDG&E continued its mandated and enhanced inspection programs. In Q1, SDG&E completed 90% of the planned pole replacements in the HFTD for Q1 2021. |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Expulsion fuse replacement |  | 7 | Expulsion fuse replacement (7.3.3.7) | Fuse | SDGE_Grid Design & System Hardening_Expulsion fuse replacement _Fuse_2021 | 196 | Expulsion fuses | 3970 | 200 | 1200 | 2800 | 3970 | 202 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | Grid topology improvements to mitigate or reduce PSPS events (7.3.3.8) |  | SDGE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events __2021 | 198 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | PSPS sectionalizing enhancements | PSPS sectionalizing enhancements | PSPS sectionalizing enhancements (7.3.3.8.1) | Switch | SDGE_Grid Design & System Hardening_PSPS sectionalizing enhancements_Switch_2021 | 198 | Sectionalizing devices | 10 | 3 | 6 | 9 | 10 | 2 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Microgrids | Microgrids | Microgrids (7.3.3.8.2) | Micro | SDGE_Grid Design & System Hardening_Microgrids_Micro_2021 | 200 | Microgrids | 2 | 0 | 0 | 0 | 2 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Installation of system automation equipment |  | 9 | Installation of system automation equipment - Advanced Protection (7.3.3.9) | AdvProt | SDGE_Grid Design & System Hardening_Installation of system automation equipment _AdvProt_2021 | 202 | Circuits | 8 | 2 | 4 | 6 | 8 | 2 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Maintenance, repair, and replacement of connectors, including hotline clamps |  | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps - Hotline Clamps (7.3.3.10) | HLC | SDGE_Grid Design & System Hardening_Maintenance, repair, and replacement of connectors, including hotline clamps _HLC_2021 | 205 | Hotline clamps | 2250 | 1000 | 1500 | 2000 | 2250 | 1030 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | Mitigation of impact on customers and other residents affected during PSPS events (7.3.3.11) |  | SDGE_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event __2021 | 207 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Resiliency Grant Programs | Resiliency Grant Programs | Resiliency Grant Programs (7.3.3.11.1) | RGP | SDGE_Grid Design & System Hardening_Resiliency Grant Programs_RGP_2021 | 208 | Generators | 2000 | 0 | 200 | 1300 | 2000 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Standby Power Programs | Standby Power Programs | Standby Power Programs (7.3.3.11.2) | SPP | SDGE_Grid Design & System Hardening_Standby Power Programs_SPP_2021 | 210 | Generators | 413 | 60 | 180 | 300 | 413 | 67 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Resiliency Assistance Programs | Resiliency Assistance Programs | Resiliency Assistance Programs (7.3.3.11.3) | RAP | SDGE_Grid Design & System Hardening_Resiliency Assistance Programs_RAP_2021 | 212 | Generators | 1250 | 0 | 188 | 938 | 1250 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other corrective action |  | 12 | Other corrective action (7.3.3.12) |  | SDGE_Grid Design & System Hardening_Other corrective action __2021 | 215 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program |  | 13 | Pole loading infrastructure hardening and replacement program (7.3.3.13) |  | SDGE_Grid Design & System Hardening_Pole loading infrastructure hardening and replacement program based on pole loading assessment program __2021 | 215 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Transformers maintenance and replacement |  | 14 | Transformers maintenance and replacement (7.3.3.14) |  | SDGE_Grid Design & System Hardening_Transformers maintenance and replacement __2021 | 215 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Transmission tower maintenance and replacement |  | 15 | Transmission tower maintenance and replacement (7.3.3.15) |  | SDGE_Grid Design & System Hardening_Transmission tower maintenance and replacement __2021 | 215 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Undergrounding of electric lines and/or equipment |  | 16 | Undergrounding of electric lines and/or equipment (7.3.3.16) | SUG | SDGE_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _SUG_2021 | 215 | Miles | 25 | 4 | 19 | 25 | 25 | 4.38 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | Updates to grid topology to minimize the risk of ignition in HFTD (7.3.3.17) |  | SDGE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs __2021 | 217 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Distribution overhead system hardening | Distribution overhead system hardening | Distribution overhead system hardening (7.3.3.17.1) | FIRM-Bare | SDGE_Grid Design & System Hardening_Distribution overhead system hardening_FIRM-Bare_2021 | 217 | Miles | 100 | 11 | 46 | 74 | 100 | 16.6 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Transmission overhead system hardening | Transmission overhead system hardening | Transmission overhead system hardening (7.3.3.17.2) | TransHard-TOH | SDGE_Grid Design & System Hardening_Transmission overhead system hardening_TransHard-TOH_2021 | 221 | Miles | 6.7 | 0 | 0.7 | 3.6 | 6.7 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Transmission overhead system hardening | Transmission overhead system hardening | Transmission overhead system hardening (7.3.3.17.2) | TransHard-TOH | SDGE_Grid Design & System Hardening_Transmission overhead system hardening_TransHard-TOH_2021 | 221 | Miles | N/A | 0 | 0.7 | 3.6 | 6.7 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Transmission overhead system hardening | Transmission overhead system hardening | Transmission overhead system hardening (7.3.3.17.2) | TransHard-TOH | SDGE_Grid Design & System Hardening_Transmission overhead system hardening_TransHard-TOH_2021 | 221 | Miles | 6.7 | 0 | 0.7 | 3.6 | 6.7 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Cleveland National Forest distribution and transmission system hardening | Cleveland National Forest distribution and transmission system hardening | Cleveland National Forest distribution and transmission system hardening (7.3.3.17.3) | CNF-TOH | SDGE_Grid Design & System Hardening_Cleveland National Forest distribution and transmission system hardening_CNF-TOH_2021 | 224 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Cleveland National Forest distribution and transmission system hardening | Cleveland National Forest distribution and transmission system hardening | Cleveland National Forest distribution and transmission system hardening (7.3.3.17.3) | CNF-TOH | SDGE_Grid Design & System Hardening_Cleveland National Forest distribution and transmission system hardening_CNF-TOH_2021 | 224 | Miles | 6.8 | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Cleveland National Forest distribution and transmission system hardening | Cleveland National Forest distribution and transmission system hardening | Cleveland National Forest distribution and transmission system hardening (7.3.3.17.3) | CNF-TOH | SDGE_Grid Design & System Hardening_Cleveland National Forest distribution and transmission system hardening_CNF-TOH_2021 | 224 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Other | Other | Other (7.3.3.18) |  | SDGE_Grid Design & System Hardening_Other__2021 | 227 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Distribution Communications Reliability Improvements | Distribution Communications Reliability Improvements | Distribution Communications Reliability Improvements (7.3.3.18.1) | DCRI | SDGE_Grid Design & System Hardening_Distribution Communications Reliability Improvements_DCRI_2021 | 227 | Base stations | 10 | 1 | 1 | 5 | 10 | 1 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Design & System Hardening | 5.3.3. | Other | Lightning arrestor removal and replacement | Lightning arrestor removal and replacement | Lightning arrestor removal and replacement (7.3.3.18.2) | Arrestor | SDGE_Grid Design & System Hardening_Lightning arrestor removal and replacement_Arrestor_2021 | 229 | Lightning arrestors | 924 | 90 | 350 | 700 | 924 | 93 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Detailed inspections of distribution electric lines and equipment |  | 1 | Detailed inspections of distribution electric lines and equipment (7.3.4.1) | CMP-Detail | SDGE_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _CMP-Detail_2021 | 231 | Inspections | 22269 | 12000 | 22269 | 22269 | 22269 | 11943 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Detailed inspections of transmission electric lines and equipment |  | 2 | Detailed inspections of transmission electric lines and equipment (7.3.4.2) | TRANS-Detail | SDGE_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _TRANS-Detail_2021 | 233 | Inspections | 1943 | 620 | 1100 | 1500 | 1943 | 620 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Improvement of inspections |  | 3 | Improvement of inspections (7.3.4.3) |  | SDGE_Asset Management & Inspections_Improvement of inspections __2021 | 236 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Infrared inspections of distribution electric lines and equipment |  | 4 | Infrared inspections of distribution electric lines and equipment (7.3.4.4) | DistIR | SDGE_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment _DistIR_2021 | 236 | Inspections | 18000 | 1200 | 6000 | 12000 | 18000 | 1241 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Infrared inspections of transmission electric lines and equipment |  | 5 | Infrared inspections of transmission electric lines and equipment (7.3.4.5) | TRANS-IR | SDGE_Asset Management & Inspections_Infrared inspections of transmission electric lines and equipment _TRANS-IR_2021 | 238 | Inspections | 6166 | 0 | 0 | 4500 | 6166 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Intrusive pole inspections |  | 6 | Intrusive pole inspections (7.3.4.6) | CMP-Intrusive | SDGE_Asset Management & Inspections_Intrusive pole inspections _CMP-Intrusive_2021 | 240 | Inspections | 9796 | 4500 | 6000 | 8000 | 9796 | 4543 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | LiDAR inspections of distribution electric lines and equipment |  | 7 | LiDAR inspections of distribution electric lines and equipment (7.3.4.7) |  | SDGE_Asset Management & Inspections_LiDAR inspections of distribution electric lines and equipment __2021 | 242 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E continues to use LiDAR inspections to supplement the grid hardening efforts and post-construction analysis, where possible. SDG&E plans to implement vegetation risk analysis within the HFTD and potentially expand into non-HFTD projects. Additionally, SDG&E plans to use the results of these analyses for emergency operations during red flag and other extreme events. | SDG&E made significant progress drafting a request for proposal and clearly defined scope of work for LiDAR capture and vegetation analysis within the HFTD. |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | LiDAR inspections of transmission electric lines and equipment |  | 8 | LiDAR inspections of transmission electric lines and equipment (7.3.4.8) |  | SDGE_Asset Management & Inspections_LiDAR inspections of transmission electric lines and equipment __2021 | 243 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E continues to use LiDAR inspections to supplement grid hardening efforts and post-construction analysis, where possible. SDG&E plans to implement vegetation and clearance checks within the HFTD and potentially expand into non-HFTD projects. Additionally, SDG&E plans to use the results of these analyses for emergency operations during red flag and other extreme events. | In Q1 2021, SDG&E Transmission completed LiDAR for a couple of tielines associated with Wood to Steel Projects within the HFTD. SDG&E Transmission also used previously processed LiDAR to proactively model transmission lines that our meteorology department has identified as likely to experience high winds during red flag events. This is an ongoing activity that is expected to continue through 2021. Additionally, SDG&E Transmission used previously processed LiDAR sets to evaluate transmission lines for clearance, vegetation, and structural loading for emergency operation center activations in Q1 2021. |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations (7.3.4.9) |  | SDGE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations __2021 | 245 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Other | HFTD Tier 3 inspections | HFTD Tier 3 inspections | HFTD Tier 3 inspections (7.3.4.9.1) | CMP-Tier3 | SDGE_Asset Management & Inspections_HFTD Tier 3 inspections_CMP-Tier3_2021 | 245 | Inspections | 10815 | 10505 | 10815 | 10815 | 10815 | 10505 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Other | Drone assessments of distribution infrastructure | Drone assessments of distribution infrastructure | Drone assessments of distribution infrastructure (7.3.4.9.2) | DIAR-Dist | SDGE_Asset Management & Inspections_Drone assessments of distribution infrastructure_DIAR-Dist_2021 | 247 | Inspections | 22000 | 0 | 3500 | 12500 | 22000 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Other | Circuit ownership | Circuit ownership | Circuit ownership (7.3.4.9.3) |  | SDGE_Asset Management & Inspections_Circuit ownership__2021 | 250 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continues to evaluate the Circuit Ownership Program. This initiative has the potential to expand to all users in SDG&E’s Electric Regional Operations or even outside departments to submit concerns. | SDG&E continues to encourage participation of the circuit ownership program during regular Electric Regional Operations safety meetings and roadshows. We will leverage the data and submission rates/quality to continue to evaluate success of the program. |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Other | Drone assessment of transmission | Drone assessment of transmission | Drone assessment of transmission (7.3.4.9.4) | DIAR-Trans | SDGE_Asset Management & Inspections_Drone assessment of transmission_DIAR-Trans_2021 | 252 | Inspections | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E will continue to develop the program to enhance its existing inspection efforts of transmission structures in HFTD areas starting in 2020. SDG&E plans to focus on inspecting select transmission structures in both Tier 2 and Tier 3 HFTD areas in 2021, as part of an initial pilot effort. | SDG&E initially set a target of 2715 structures in the 2021 WMP Update. At the time, SDG&E was still completing a pilot program for transmission assessments using drones on approximately 1,600 structures. Based on the results of that pilot program, which included a very low issue rate of ~1%, SDG&E is reevaluating the number of structures that will be included in its drone assessment program in 2021. Moreover, as the scope of other WMP programs evolve, SDG&E is endeavoring to reduce overlap with other efforts, such as fire-hardening or other inspection efforts. Accordingly, SDG&E is providing a qualitative target and quarterly qualitative progress updates as the scope of the program for 2021 is refined. SDG&E inspected 202 transmission structures in the Tier 2 HFTD in Q1 2021 as part of its initial pilot program. |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Other | Additional Transmission Aerial 69kV Tier 3 Visual Inspection | Additional Transmission Aerial 69kV Tier 3 Visual Inspection | Additional Transmission Aerial 69kV Tier 3 Visual Inspection (7.3.4.9.5) | TRANS-Aerial | SDGE_Asset Management & Inspections_Additional Transmission Aerial 69kV Tier 3 Visual Inspection_TRANS-Aerial_2021 | 254 | Inspections | 1654 | 0 | 0 | 1654 | 1654 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Patrol inspections of distribution electric lines and equipment |  | 11 | Patrol inspections of distribution electric lines and equipment (7.3.4.10) | CMP-Patrol | SDGE_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _CMP-Patrol_2021 | 256 | Inspections | 86000 | 28000 | 50000 | 72000 | 86000 | 28005 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Patrol inspections of transmission electric lines and equipment |  | 12 | Patrol inspections of transmission electric lines and equipment (7.3.4.11) | TRANS-Patrol | SDGE_Asset Management & Inspections_Patrol inspections of transmission electric lines and equipment _TRANS-Patrol_2021 | 258 | Inspections | 6324 | 3989 | 5850 | 6324 | 6324 | 3989 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Pole loading assessment program to determine safety factor |  | 13 | Pole loading assessment program to determine safety factor (7.3.4.12) |  | SDGE_Asset Management & Inspections_Pole loading assessment program to determine safety factor __2021 | 260 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Quality assurance / quality control of inspections |  | 14 | Quality assurance/quality control of inspections (7.3.4.13) |  | SDGE_Asset Management & Inspections_Quality assurance / quality control of inspections __2021 | 260 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E does not currently plan on implementing any improvements to this initiative. SDG&E will continue its current process of auditing its inspection and maintenance results on a quarterly basis. | SDG&E completed 100% of the QA/QC audits for the electric distribution system. SDG&E performer 109 audits on the OH distribution system, with four additional findings found. |  |  |  | In Progress
SDGE | 2021-05-03 | Asset Management & Inspections | 5.3.4. | Substation inspections |  | 15 | Substation inspections (7.3.4.14) | SUBS | SDGE_Asset Management & Inspections_Substation inspections _SUBS_2021 | 261 | Inspections | 330 | 83 | 166 | 249 | 330 | 95 | N/A | N/A | N/A | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Additional efforts to manage community and environmental impacts |  | 1 | Additional efforts to manage community and environmental impacts (7.3.5.1) |  | SDGE_Vegetation Management & Inspections_Additional efforts to manage community and environmental impacts __2021 | 265 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to work with multiple internal departments toward the goal of providing comprehensive outreach and education regarding its vegetation management activities including web content, specific literature, and public events | SDG&E initiated the creation of an internal Vegetation Management department website to provide awareness to internal company employees, and to facilitate work activity process flows. Developed VM overview presentation to provide customers during upcoming Wildfire Safety webinars to be held Q2. Presentation will include overview of VM and specific enhanced activities scheduled for 2021. |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 | Detailed inspections of vegetation around distribution electric lines and equipment (7.3.5.2) | TT | SDGE_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _TT_2021 | 267 | trees inspected | 455000 | 113750 | 227500 | 341250 | 455000 | 110315 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Detailed inspections of vegetation around transmission electric lines and equipment |  | 3 | Detailed inspections of vegetation around transmission electric lines and equipment (7.3.5.3) |  | SDGE_Vegetation Management & Inspections_Detailed inspections of vegetation around transmission electric lines and equipment __2021 | 270 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Emergency response vegetation management due to red flag warning or other urgent conditions |  | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions (7.3.5.4) |  | SDGE_Vegetation Management & Inspections_Emergency response vegetation management due to red flag warning or other urgent conditions __2021 | 270 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Fuel management and reduction of “slash” from vegetation management activities |  | 5 | Fuels management and reduction of “slash” from vegetation management activities (7.3.5.5) | FM | SDGE_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _FM_2021 | 270 | poles cleared | 500 | 0 | 0 | 500 | 500 | 0 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Improvement of inspections |  | 3 | Improvement of inspections (7.3.5.6) |  | SDGE_Vegetation Management & Inspections_Improvement of inspections __2021 | 274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | LiDAR inspections of vegetation around distribution electric lines and equipment |  | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment (7.3.5.7) |  | SDGE_Vegetation Management & Inspections_LiDAR inspections of vegetation around distribution electric lines and equipment __2021 | 274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to research LiDAR as a tool for post-trim auditing and change detection in trees and equipment, though the latter appears still in the early stages of advancement. SDG&E expects to use LiDAR technology to some degree across multiple Company initiatives and throughout a larger portion of the HFTD in 2021. As the frequency of flights increase, and data acquisition becomes more efficient, Vegetation Management will continue to pilot LiDAR as a more integrated component of its operations. | SDG&E continued to assess findings from its LiDAR pilot project and internal discussions on if/how to broaden and operationalize this technology as a component of routine VM activities. |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | LiDAR inspections of transmission electric lines and equipment |  | 8 | LiDAR inspections for vegetation around transmission electric lines and equipment (7.3.5.8) |  | SDGE_Vegetation Management & Inspections_LiDAR inspections of transmission electric lines and equipment __2021 | 276 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations (7.3.5.9) | ENH | SDGE_Vegetation Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _ENH_2021 | 276 | trees trimmed/removed | 17000 | 4250 | 8500 | 12750 | 17000 | 3137 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Other discretionary inspection of transmission electric lines and |  | 10 | Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations (7.3.5.10) |  | SDGE_Vegetation Management & Inspections_Other discretionary inspection of transmission electric lines and __2021 | 279 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Patrol inspections of distribution electric lines and equipment |  | 11 | Patrol inspections of vegetation around distribution electric lines and equipment (7.3.5.11) |  | SDGE_Vegetation Management & Inspections_Patrol inspections of distribution electric lines and equipment __2021 | 279 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Patrol inspections of transmission electric lines and equipment |  | 12 | Patrol inspections of vegetation around transmission electric lines and equipment (7.3.5.12) |  | SDGE_Vegetation Management & Inspections_Patrol inspections of transmission electric lines and equipment __2021 | 279 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Quality assurance / quality control of vegetation inspections |  | 13 | Quality assurance/quality control of inspections (7.3.5.13) |  | SDGE_Vegetation Management & Inspections_Quality assurance / quality control of vegetation inspections __2021 | 279 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | Over the next 5 years, SDG&E will work to develop a comprehensive audit program to continue to assess and quantify the state of compliance of the Vegetation Management program with regulatory requirements. These audits will inform on overall success of the program, state of compliance, and procedural integrity | SDG&E continued to audit 100% of all completed hazard tree trimming in HFTD and 100% of all completed tree removals in HFTD. SDG&E Vegetation Management initiated the requisition for a new internal Business Advisor who will assist in developing a compliance component of the existing audit program. |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Recruiting and training of vegetation management personnel |  | 14 | Recruiting and training of vegetation management personnel (7.3.5.14) |  | SDGE_Vegetation Management & Inspections_Recruiting and training of vegetation management personnel __2021 | 280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue working with the stakeholders to expand the Utility Arborist Trainee program to colleges in Southern California by early 2021. SDG&E is also collaborating to develop and implement a “Pre-Inspection” curriculum in 2021 with a goal of developing a career path for local students into the utility workforce. | SDG&E began a collaborative initiative with industry and academia stakeholders to develop a Utility Arborist Training program through the local community colleges. Pandemic restrictions delayed the actual implementation of the program but is target to be implemented Q2. |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Remediation of at-risk species |  | 15 | Remediation of at-risk species (7.3.5.15) |  | SDGE_Vegetation Management & Inspections_Remediation of at-risk species __2021 | 282 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 | Removal and remediation of trees with strike potential to electric lines and equipment (Hazard tree removal and Right Tree-Right Place) (7.3.5.16) |  | SDGE_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment __2021 | 282 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue its robust hazard tree inspection and trimming operations. SDG&E will begin implementing an internal workforce of internal SDG&E inspectors to perform its off-cycle, enhanced inspections and hazard tree assessments within the HFTD. SDG&E requires contractors to perform annual hazard tree training for their field personnel as a refresher and to learn the latest evaluation techniques. Additionally, SDG&E will continue its outreach and collaboration with cities and other stakeholders to increase the number of tree plantings as a sustainability initiative. | SDG&E hired and began to use internal company Patrollers to perform the off-cycle inspections within the HFTD. SDG&E Vegetation Management participated in the company’s corporate sustainability initiative with the formation of a team to increase, track and record green waste diversions to 100% recyclable facilities. SDG&E increased its tree planting outreach by engaging stakeholders including cities, agencies, tribal reservations, customers to meet expanded goals. |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Substation inspection |  | 17 | Substation inspections (7.3.5.17) |  | SDGE_Vegetation Management & Inspections_Substation inspection __2021 | 284 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Substation vegetation management |  | 18 | Substation vegetation management (7.3.5.18) |  | SDGE_Vegetation Management & Inspections_Substation vegetation management __2021 | 284 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Vegetation inventory system |  | 19 | Vegetation inventory system (7.3.5.19) |  | SDGE_Vegetation Management & Inspections_Vegetation inventory system __2021 | 284 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to investigate the integration of its new work management system with other inter‐departmental systems to streamline workflows. SDG&E will research opportunities to share its inventory data with external stakeholders for cross‐activity initiatives. | SDG&E implemented new work management system database called EPOCH to schedule, manage, and document all VM work activities. |  |  |  | In Progress
SDGE | 2021-05-03 | Vegetation Management & Inspections | 5.3.5. | Vegetation management to achieve clearances around electric lines and equipment |  | 20 | Vegetation management to achieve clearances around electric lines and equipment (7.3.5.20) | PB | SDGE_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _PB_2021 | 286 | poles brushed | 35500 | 21000 | 35500 | 35500 | 35500 | 21869 |  |  |  | N/A | N/A |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Automatic recloser operations |  | 1 | Automatic recloser operations (7.3.6.1) |  | SDGE_Grid Operations & Operating Protocols_Automatic recloser operations __2021 | 289 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Other | Recloser protocols | Recloser protocols | Recloser protocols (7.3.6.1.1) |  | SDGE_Grid Operations & Operating Protocols_Recloser protocols__2021 | 289 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E’s reclosing operations continue to represent a standard best practice for California utilities. SDG&E plans to continue to look for innovative system protection settings for its automated reclosers and other automated sectionalizing devices, such as the fast trip settings to reduce fault energy. | SDG&E continues to leave reclosing disabled in the HFTD on its distribution circuits. No extreme operating conditions occurred in Q1 2021 that required disabling reclosing in the WUI located outside the HFTD. |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Other | Sensitive/Fast Protection settings | Sensitive/Fast Protection settings | Sensitive/Fast Protection settings (7.3.6.1.2) |  | SDGE_Grid Operations & Operating Protocols_Sensitive/Fast Protection settings__2021 | 291 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to enable sensitive/Fast protection settings on more devices within the HFTD. This program has synergies with SDG&E’s PSPS sectionalizing enhancement program and the Advanced Protection program. As more remote sectionalizing devices are deployed and upgraded system protection equipment is installed on the distribution system, then these fast protection settings can be enabled/ | SDG&E continues its practice of enabling sensitive/Fast protection setting capabilities on new sectionalizing devices installed in the HFTD and areas of coastal risk. No wildfire risk events triggered activation of sensitive relay profiles in Q1 2021, but sensitive ground protection remains in-place to protect against high impedance faults. |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Crew-accompanying ignition prevention and suppression resources and services |  | 2 | Crew accompanying ignition prevention and suppression resources and services (7.3.6.2) |  | SDGE_Grid Operations & Operating Protocols_Crew-accompanying ignition prevention and suppression resources and services __2021 | 292 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to regularly refine this initiative with the training qualifications of personnel serving on CFRs and utility activities are being reviewed annually. | SDG&E continued to work with CFR providers to ensure training requirements are met and incorporating feedback to enhance efficiency. |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Personnel work procedures and training in conditions of elevated fire risk |  | 3 | Personnel work procedures and training in conditions of elevated fire risk (7.3.6.3) |  | SDGE_Grid Operations & Operating Protocols_Personnel work procedures and training in conditions of elevated fire risk __2021 | 293 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to update procedures and review training annually with feedback from attendees. Additionally, the feedback will be incorporated into future training. | SDG&E performed training for 1,185 internal personnel in Q1. These trainings related to internal work practice and emergency response procedures. SDG&E also incorporated feedback from personnel on topics they wished to have a more information on. |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Protocols for PSPS re-energization |  | 4 | Protocols for PSPS re‐energization (7.3.6.4) |  | SDGE_Grid Operations & Operating Protocols_Protocols for PSPS re-energization __2021 | 295 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to look for ways to reduce post-event patrol times in an effort to reduce the impacts of PSPS events on its customers. Some of these ideas include leveraging drone pilots to perform patrols on areas that can only be accessed by helicopter, when wind conditions delay the use of helicopter-only patrols. | SDG&E continues to refine its restoration protocols, including pre-identified resource requirements needed to patrol circuit and circuit segments subject to PSPS. Mapping these foot and aerial patrol resource needs ensures more accurate resource forecasting during events, preventing resource shortages that hinder timely restoration of service to customers. SDG&E also reviews all relay operation data ahead of performing circuit patrols to identify if a real fault occurred or if the relay tripped due to sensitive protection. |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | PSPS events and mitigation of PSPS impacts |  | 5 | PSPS events and mitigation of PSPS impacts (7.3.6.5) |  | SDGE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts __2021 | 296 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E will continue refining the activities associated with reducing PSPS impacts | Although SDG&E has not seen any PSPS impacts in Q1 2021, it continues to refine communication protocols with community partners, build stronger workflow and tools to communicate with customers, and implement PSPS system enhancements to minimize customers impacted by PSPS. These programs are referenced in other areas of the WMP. In addition, SDG&E has met with the CAISO and other IOUs regarding the 2021 peak season as well as fire season to discuss the potential for PSPS events and their impact on system reliability. |  |  |  | In Progress
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Stationed and on-call ignition prevention and suppression resources and services |  | 6 | Stationed and on‐call ignition prevention and suppression resources and services (7.3.6.6) |  | SDGE_Grid Operations & Operating Protocols_Stationed and on-call ignition prevention and suppression resources and services __2021 | 298 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Grid Operations & Operating Protocols | 5.3.6. | Other | Aviation firefighting program | Aviation firefighting program | Aviation firefighting program (7.3.6.6.1) |  | SDGE_Grid Operations & Operating Protocols_Aviation firefighting program__2021 | 298 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to take ownership of a Sikorsky S-70M (Firehawk), which will serve as one of SDG&E’s lead aerial firefighting resources once it is outfitting with firefighting capability. Once the Firehawk is in service, which is expected to be in 2022, the Blackhawk will be available as a backup if needed. Operations with the S-70M (Firehawk) will be a more capable and safer for firefighting compared to the current Blackhawk due to the platforms advanced safety systems and enhanced performance characteristics. | Under the SDG&E's Aerial Firefighting Program, two aerial firefighting assets have been made available seven days a week, 365 days per year. The acquisition of the S-70M has been delayed until 2023. Availability is measured in days. Any days that an asset is not available for immediate dispatch degrades the availability. Additionally, the number of dispatches is equal to a response to need. For 2021 Q1, SDG&E provided the following availability and dispatches: • Air Crane - zero days unavailable • Blackhawk - zero days unavailable Totals: • 12 dispatches, 2 with fire attack |  |  |  | In Progress
SDGE | 2021-05-03 | Data Governance | 5.3.7. | Centralized repository for data |  | 1 | Centralized repository for data (7.3.7.1) |  | SDGE_Data Governance_Centralized repository for data __2021 | 303 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to further develop and maintain the EAMP program. The EAMP program will continue to maintain and improve currently integrated assets, while expanding to integrate other asset attributes from other asset types as the data quality and availability improves. | SDG&E delivered initial consolidated data views for Distribution Switches and Transmission structures. In addition, SDG&E will continue to enhance these views as well as add further assets in Distribution and Transmission. |  |  |  | In Progress
SDGE | 2021-05-03 | Data Governance | 5.3.7. | Collaborative research on utility ignition and/or wildfire |  | 2 | Collaborative research on utility ignition and/or wildfire (7.3.7.2) |  | SDGE_Data Governance_Collaborative research on utility ignition and/or wildfire __2021 | 304 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to establish even stronger partnerships and relationships with the academic community to sponsor ongoing wildfire mitigation-related collaborative research through internships programs where SDG&E further exposes graduate-level academic students to wildfire mitigation within utility companies. This will serve as a mechanism to begin training the next generation of scientists to support this growing problem. | As planned, the FSCA department has been working very closely and establishing long-term partnerships with academia to continue to push forward weather science, fire science and climate science. Specific academic partners in 2021 in Scripps Institution of Oceanography, San Jose State University and the San Diego Supercomputing Center. |  |  |  | In Progress
SDGE | 2021-05-03 | Data Governance | 5.3.7. | Documentation and disclosure of wildfire-related data and algorithms |  | 3 | Documentation and disclosure of wildfire‐related data and algorithms (7.3.7.3) |  | SDGE_Data Governance_Documentation and disclosure of wildfire-related data and algorithms __2021 | 306 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Data Governance | 5.3.7. | Tracking and analysis of near miss data |  | 4 | Tracking and analysis of risk event data (7.3.7.4) |  | SDGE_Data Governance_Tracking and analysis of near miss data __2021 | 306 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Data Governance | 5.3.7. | Other | Ignition management program | Ignition management program | Ignition management program (7.3.7.4.1) |  | SDGE_Data Governance_Ignition management program__2021 | 306 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E aims to further refine process documents and connect mitigation owners with data repositories. | For Q1, SDG&E's Ignition Management Program followed up on evidence of heat reports and continued to work through the process of refining the data gathering procedures. |  |  |  | In Progress
SDGE | 2021-05-03 | Data Governance | 5.3.7. | Other |  | Reliability database | Reliability database (7.3.7.4.2) |  | SDGE_Data Governance___2021 | 307 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to migrate the current database to an Oracle IT supported OUA application which allows for easier viewing of data by a broader internal audience. | SDG&E continues to work towards migrating the current database to an Oracle IT supported OUA application. For Q1, the Reliability team has shared 10 year historical data to the project team to mesh with the OUA outage data, such that it is consistent with the current reporting needs. |  |  |  | In Progress
SDGE | 2021-05-03 | Resource Allocation Methodology | 5.3.8. | Allocation methodology development and application |  | 1 | Allocation methodology development and application (7.3.8.1) |  | SDGE_Resource Allocation Methodology_Allocation methodology development and application __2021 | 309 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | Investment Prioritization As the Investment Prioritization matures, performance evaluation and continuous improvement capabilities will be developed. The performance evaluation capability will create business processes around identifying objectives and key performance indicators and determining action plans to monitor the effectiveness of the Investment Prioritization. The continuous improvement capability will produce business processes on developing the approach and collaboration to address the recommended corrective or improvement actions. WiNGS As far as the WiNGS model, SDG&E’s team will continue to improve the data that is used to evaluate the risks at the segment level and will work on assessing the need and approach for expanding the use of the model to other areas across the system and other initiatives that could benefit a more granular approach to prioritization. | Investment Prioritization - Completed Data consolidation and integration on initial set of distribution and transmission asset types, while continuing to add other asset classes/types, to enable asset performance evaluation and improve data quality. - Completed the pilot formulation of the value framework and risk calculations on sample projects to allow investment prioritization tool calibration and identify enhancements. - Configured the tool for additional projects intake and risk scoring analysis to support the ongoing first phase implementation and drive towards more granular, data-driven and risk-informed approach to prioritization. - The Data Analytics and Quantification team has been enabled and commenced supporting electric operating groups on asset and risk analyses and modeling, providing data science services and applying machine learning and advanced analytical strategies to align with continuous data quality improvement efforts. WiNGS SDG&E's team is currently updating the data in the model to continue to inform its priorization efforts. The team is also working on proof of concepts for modeling additional initiatives such as microgrids and continuing to evaluate ways to refine its assessment framework including refinements to PSPS customer valuation as well as planning the development of machine learning probability of ignition models at the asset leve. |  |  |  | In Progress
SDGE | 2021-05-03 | Resource Allocation Methodology | 5.3.8. | Risk spend efficiency analysis |  | 3 | Risk reduction scenario development and analysis (7.3.8.2) |  | SDGE_Resource Allocation Methodology_Risk spend efficiency analysis__2021 | 311 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Resource Allocation Methodology | 5.3.8. | Other | Risk spend efficiency analysis – not to include PSPS | Risk spend efficiency analysis – not to include PSPS | Risk spend efficiency analysis – not to include PSPS (7.3.8.3) |  | SDGE_Resource Allocation Methodology_Risk spend efficiency analysis – not to include PSPS__2021 | 311 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Resource Allocation Methodology | 5.3.8. | Other | Other resource allocation methodology initiatives | Other resource allocation methodology initiatives | Other resource allocation methodology initiatives (7.3.8.4) |  | SDGE_Resource Allocation Methodology_Other resource allocation methodology initiatives__2021 | 312 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Resource Allocation Methodology | 5.3.8. | Other | Wildfire mitigation personnel | Wildfire mitigation personnel | Wildfire mitigation personnel (7.3.8.4.1) |  | SDGE_Resource Allocation Methodology_Wildfire mitigation personnel__2021 | 312 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E's wildfire mitigation team personnel continues to review feedback from external stakeholders including WSD and intervenors so that SDG&E’s WMP, WMP Updates, and WMP Quarterly Reports meet or exceed expectations. | SDG&E filed the 2021 WMP Update, 2020 Q4 QIU, and 2020 Annual Compliance Report on the required due dates. SDG&E responded to all data requests related to the 2021 WMP Update within the required timeframes. Work began on preparing the 2021 Q1 reports due on May 3rd. |  |  |  | In Progress
SDGE | 2021-05-03 | Emergency Planning & Preparedness | 5.3.9. | Adequate and trained workforce for service restoration |  | 1 | Adequate and trained workforce for service restoration (7.3.9.1) |  | SDGE_Emergency Planning & Preparedness_Adequate and trained workforce for service restoration __2021 | 313 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue future improvements in this area, which include exercises and tabletops in partnership with various SDG&E departments such as: Emergency Services, Electric Distribution Operations, Substation, Transmission Construction and Maintenance, and Grid Operations. In addition to the AR/VR and 2.5 D inspection testing programs, in December 2020, SDG&E began construction on a physical infractions test yard with a target of 25-30 infractions that will be changed regularly for Journeyman to identify and properly code. | In Q1, SDG&E continued to make improvements in this area, which include: The Electric Safety Center is preparing training material to support ERO Operational Leadership and Field personnel to become better versed in ICS and working across departments to integrate ICS into “Blue Sky” days for more readily transition to “Gray Sky”. Training has already begun with the new hire lineman and line assistants up at Skills Training. Training along with tabletops are slated to take place in 2nd and 3rd Qtr. within ERO. Additionally, teams have been formed to build a process around resource allocation and the integration of Resource Coordination into the daily “Blue Sky” work allocation across ERO. The Resource Coordination team is refining their process to support PSPS and refine the work management tools in conjunction with the districts and dispatch with the goal of completion by 3rd Qtr. The development of AR/VR and 2.5D OHVI/QC fire ignition infraction training has been developed and currently we are working with IT and the Cornerstone LMS team to integrate this technology with the goal of having all inspectors brought through this training by the end of 3rd Qtr. The Electric Safety Center has updated the PSPS Training Program to include a deeper dive into ICS with training slated to be completed by 3rd Qtr. The physical infraction yard at Skills is 60% complete with the goal of completion by end of 2nd Qtr. Current inspectors will be run through this yard by end of 4th Qtr. |  |  |  | In Progress
SDGE | 2021-05-03 | Emergency Planning & Preparedness | 5.3.9. | Community outreach, public awareness, and communications efforts |  | 2 | Community outreach, public awareness, and communication efforts (7.3.9.2) |  | SDGE_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts __2021 | 315 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to expand its AFN campaigns to reach and communicate with a greater number of hard-to-reach vulnerable populations. SDG&E will continue to host Webinars to educate the communities through collaboration with both CAL FIRE and 2-1-1. Additionally, the Company is considering and evaluating additional efforts including, but not limited to, working with local school districts to enhance public education efforts. The Company is also examining new opportunities within its established partnerships with local Tribal Councils as well as focusing on strengthening and expanding partnerships with other CBOs who represent customers with access and functional needs. | SDG&E’s first quarter efforts related to the expanded Access and Functional Needs (AFN) public-education campaign are on track to achieve year-end targets. During first quarter, SDG&E began the strategic planning of it's public education and communications campaign, which is deeply rooted in emergency preparedness and planning. Development of public education and outreach materials and implementation tactics has begun. This year’s campaign will be in market effective April – approximately six months sooner than the previous years campaign – and will remain in market for the remainder of the year. Wildfire Safety Community outreach efforts, including Webinars and Drive-thru Safety Fairs, will continue to be aggressively promoted. Additionally, in 2021 SDG&E is adding Wildfire Safety Workshops customized to Community Partners and Public Safety Partners. Planning of the events, and the development of outreach materials began during the first quarter. The various events are scheduled to begin in April, and will be promoted using diverse communication platforms. Community events available to the general public will be promoted through digital and broadcast media communications in April and May. The Drive-thru Safety Fairs and corresponding promotions will continue through August. SDG&E has begun to explore a partnership with two Native American tribal subject matter experts (SME) to consult on appropriately customized messaging and communication channels for tribal nations within the service territory. The SME's communication expertise is extensive and thorough, both recognized locally and nationally for their expertise. The consultative resources will assist SDG&E to develop culturally appropriate messaging, public education and outreach materials for distribution in subsequent months. Work to begin in the second quarter. SDG&E has set up new annual MOUs with CBO partnership networks, and expanded to include wildfire preparedness and PSPS support/amplification. In addition, added 7 new partnerships supporting AFN constituents. SDG&E utilized direct mail to Life Support customers update best contact information on file in order to notify them of PSPS events and available support and has met with the Indian Health Councils to identify areas of needed support |  |  |  | In Progress
SDGE | 2021-05-03 | Emergency Planning & Preparedness | 5.3.9. | Customer support in emergencies |  | 3 | Customer support in emergencies (7.3.9.3) |  | SDGE_Emergency Planning & Preparedness_Customer support in emergencies __2021 | 320 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to evaluate new partnerships, programs and service offerings both directly provided by the Company, as well as provided through community partnerships. Central to SDG&E’s planning will be collaboration with 2-1-1 San Diego and 2-1-1 Orange County on continued ways to support AFN customers in 2021. | SDG&E’s first quarter efforts related to the expanded Access and Functional Needs (AFN) public-education campaign are on track to achieve year-end targets. During the first quarter, SDG&E began the development and planning of communications and outreach materials related to the campaign. This year’s campaign will move into market in April – approximately six months sooner than the previous year’s campaign – and will remain in market for the duration of the year. Additionally, in additional to extensive ongoing communications related to community resource center availability and resources through diverse communications channels such as digital and social media, radio and broadcast, and in community signage and trusted in-community communication networks, the AFN public education campaign will continue to promote service offerings from Community-Based Organizations (CBOs) affiliated with 2-1-1 San Diego and 2-1-1 Orange County. |  |  |  | In Progress
SDGE | 2021-05-03 | Emergency Planning & Preparedness | 5.3.9. | Disaster and emergency preparedness plan |  | 4 | Disaster and emergency preparedness plan (7.3.9.4) |  | SDGE_Emergency Planning & Preparedness_Disaster and emergency preparedness plan __2021 | 325 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to update its CERP based on lessons learned. Processes and standards are enhanced, and training exercises are designed to stress test lessons learned and improvements to support a continuously improved response. | In Q1, SDG&E continued to update the CERP with lessons learned and it is on track to be completed by July 2021. SDG&E has conducted an Earthquake workshop and tabletop exercise in Q1 of 2021. We have scheduled 3 PSPS exercises for Q2 & Q3 and a Cyber exercise in Q4. |  |  |  | In Progress
SDGE | 2021-05-03 | Emergency Planning & Preparedness | 5.3.9. | Preparedness and planning for service restoration |  | 5 | Preparedness and planning for service restoration (7.3.9.5) |  | SDGE_Emergency Planning & Preparedness_Preparedness and planning for service restoration __2021 | 326 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | Mutual assistance is an essential part of the energy industry’s contingency planning and restoration process. SDG&E plans to continue to make improvements in this area. Future improvements to the Mutual Assistance program will include transitioning from cash advances to a debit card system for per diem disbursements. Debit card systems are safer for COVID-19 purposes as handling cash is discouraged by the Centers for Disease Control. | Mutual Assistance per diem has been transitioned from cash advances to a debit card system. |  |  |  | In Progress
SDGE | 2021-05-03 | Emergency Planning & Preparedness | 5.3.9. | Protocols in place to learn from wildfire events |  | 6 | Protocols in place to learn from wildfire events (7.3.9.6) |  | SDGE_Emergency Planning & Preparedness_Protocols in place to learn from wildfire events __2021 | 328 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E plans to continue to review all significant incidents and activations to identify potential improvements and establish a comprehensive and measurable After Action Report. Additionally, SDG&E will evaluate if the AAR program can align and integrate the processes with SDG&E's Safety Management System (SMS). SMS will provide a systematic, cohesive framework which builds upon SDG&E’s strong safety culture and integrates new and existing processes; it will promote improved communication, better documentation, enhanced coordination, and continuous improvement. Where the AAR focuses on emergency incidents and events involving SDG&E’s EOC, the SMS will provide an enterprise-wide approach to risk and safety and allow for cross-functional learning and information sharing on all events. | SDG&E's Emergency Management continues to support the implementation of SDG&E's Safety Management System (SMS). The After-Action Review program will play a critical role in SMS stakeholder engagement and process planning leading up to the implementation. Lessons learned gleaned from 2020 are currently being incorporated into both the 2021 training and exercise schedule, as well as fire season planning efforts. |  |  |  | In Progress
SDGE | 2021-05-03 | Emergency Planning & Preparedness | 5.3.9. | Other | Other – Emergency management operations | Other – Emergency management operations | Other – Emergency management operations (7.3.9.7) |  | SDGE_Emergency Planning & Preparedness_Other – Emergency management operations__2021 | 329 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E's Training and Exercise Division in Emergency Management will continue to work with the AAR team to ensure lesson learned are incorporated into all trainings and exercises for continual improvement. Additionally, SDG&E plans to implement a 24/7 Watch Desk program. This program is the natural evolution of developing a world class emergency management program. This capability will increase the capacity of Emergency Management for situational awareness. | SDG&E's Training and Exercise Division in Emergency Management have incorporated lesson learned identified in the AAR program into the trainings & exercises. Additionally, the 24/7 Watch Desk program has been included in the RAMP process and is pending approval for implementation. |  |  |  | In Progress
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Community engagement |  | 1 | Community engagement – Community outreach and public awareness (7.3.10.1) |  | SDGE_Stakeholder Cooperation & Community Engagement_Community engagement __2021 | 335 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E will continue to host webinars in 2021 to provide communities with additional educational efforts and collaboration with both CAL FIRE and 2-1-1. Pending the pandemic in 2021, SDG&E’s past open house events will be scheduled to continue to bring rural customers together to educate, share updated information as well as build relationships. Additionally, SDG&E will continue to have Wildfire Safety Fairs to serve the communities with information, education, resiliency and opportunities to help before, during and after a PSPS activation and/or any other emergency situation. | Community outreach efforts, including Webinars and Drive-thru Safety Fairs, will continue to be aggressively promoted. Additionally, in 2021 SDG&E is adding Wildfire Safety Workshops customized to Community Partners. Planning of the events, and the development of outreach materials began during the first quarter. The various events are scheduled to begin in April, and will be promoted using diverse communication platforms. Community events available to the general public will be promoted through digital and broadcast media communications in April and May. The Drive-thru Safety Fairs and corresponding promotions will continue through August. SDG&E has set up new annual MOUs with CBO partnership networks, and expanded to include wildfire preparedness and PSPS support/amplification. In addition, added 7 new partnerships supporting AFN constituents. SDG&E utilized direct mail to Life Support customers update best contact information on file in order to notify them of PSPS events and available support and has met with the Indian Health Councils to identify areas of needed support |  |  |  | In Progress
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Other | PSPS communication practices | PSPS communication practices | PSPS communication practices (7.3.10.1.1) |  | SDGE_Stakeholder Cooperation & Community Engagement_PSPS communication practices__2021 | 337 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | In 2021, SDG&E will be investing in improvements that enhance both the wildfire safety and PSPS communications. Future improvements will be available and utilized for both communications initiatives. These efforts include the expansion of the AFN campaign to better communicate with hard-to-reach populations. The public education campaign will start sooner in the year and will work to expand the reach of communications within the service territory. The Company will also review and assess the prevalent languages identified, as well as explore other accessibility enhancements to PSPS notifications. Additionally, the Company is considering and evaluating additional efforts including, but not limited to, working with local school districts to enhance public education efforts. SDG&E is also examining new opportunities within its established partnerships with local Tribal Councils and other resources that serve Native American communities. | SDG&E is on track to achieve its year-end targets. During the first quarter, SDG&E conducted qualitative research among customers to gain feedback regarding the Public Safety Power Shutoff (PSPS) process and communication practices. Findings are being evaluated and incorporated into this year’s PSPS communication strategy, including preferences related to CBO services and assistance. SDG&E’s first quarter efforts related to the expanded Access and Functional Needs (AFN) public-education campaign are on track to achieve year-end targets. During quarter one, SDG&E began the strategic planning of it's PSPS communications campaign. The campaign is deeply rooted in preparedness, planning and resiliency messaging. This year’s campaign will begin to go into market in April – approximately six months sooner than the previous years campaign – and will remain in market for the remainder of the year. Additionally, the AFN campaign will continue to communicate service offerings available through Community-Based Organizations (CBOs) affiliated with 2-1-1 San Diego and 2-1-1 Orange County. SDG&E is currently reviewing any material changed to prevalent languages spoken in the territory and will make any necessary adjustments related to demographic or population changes that meet the CPUC’s “prevalent language” definition. If needed, the prevalent language list will be updated accordingly. SDG&E has begun to explore a partnership with two Native American tribal subject matter experts (SME) to consult on appropriately customized PSPS messaging and communication channels for tribal nations within the service territory. The SME's communication expertise is extensive and thorough, both recognized locally and nationally for their expertise. The consultative resources will assist SDG&E to review current communications and, where needed, develop culturally appropriate messaging. Work to begin in the second quarter. Finally, current customer notifications messaging is being reviewed and adjustment will be made based customer insights gained through feedback sessions conducted earlier in quarter one. |  |  |  | In Progress
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Cooperation and best practice sharing with agencies outside CA |  | 2 | Cooperation and best practice sharing with agencies outside California (7.3.10.2) |  | SDGE_Stakeholder Cooperation & Community Engagement_Cooperation and best practice sharing with agencies outside CA __2021 | 342 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Other | Emergency Management and Fire Science & Climate Adaptation | Emergency Management and Fire Science & Climate Adaptation | Emergency Management and Fire Science & Climate Adaptation (7.3.10.2.1) |  | SDGE_Stakeholder Cooperation & Community Engagement_Emergency Management and Fire Science & Climate Adaptation__2021 | 342 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | To continue to build comprehensive resilience to wildfire and other climate hazards, SDG&E will expand its proven formula of cooperation and best practice sharing and collaborating with agencies. This will be achieved by combining the best available science (spearheading the development of that science where it is lacking), cutting-edge situational awareness technology, and subject matter expertise dedicated to solving complex climate change-related issues. | During Q1 of 2021, SDG&E has developed plans for a comprehensive wildfire outreach plan in 2021 which includes webinars and community fairs. Additionally SDG&E has partnered with over a dozen community based organization who will be engaging in this community outreach. |  |  |  | In Progress
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Other | International Wildfire Risk Mitigation Consortium | International Wildfire Risk Mitigation Consortium | International Wildfire Risk Mitigation Consortium (7.3.10.2.2) |  | SDGE_Stakeholder Cooperation & Community Engagement_International Wildfire Risk Mitigation Consortium__2021 | 344 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | The consortium plans to continue to add utilities interested in participating and contribute to the collaboration and learnings. It is hoped experiences with various mitigation approaches and implementations will inform future SDG&E wildfire risk mitigation related work. In the future, more details regarding the progress of the various activities from this consortium may be shared. | SDG&E has been an active participant in the International Wildfire Risk Mitigation Consortium in 2021. This has been an international platform for sharing best practices and ideas with other utilities regarding the challenge of safe operations with increasing wildfire risk. |  |  |  | In Progress
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Cooperation with suppression agencies |  | 3 | Cooperation with suppression agencies (7.3.10.3) |  | SDGE_Stakeholder Cooperation & Community Engagement_Cooperation with suppression agencies __2021 | 345 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E is constantly refining training and solicits input from training officers for topics that firefighters are interested in knowing more about. These topics, as well as lessons learned on incidents, are incorporated into training. | SDG&E performed 27 external trainings with a total of 365 attendees during Q1. In 2021 these trainings are chief officer level material covering topics relating to emergency response, unique utility hazards, and scenarios. SDG&E also regularly interacts with the agencies in our service territory and is part of the planning committee for the San Diego County wide wildland drill which will occur in Q2. |  |  |  | In Progress
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Forest service and fuel reduction cooperation and joint roadmap |  | 4 | Forest service and fuel reduction cooperation and joint roadmap (7.3.10.4) |  | SDGE_Stakeholder Cooperation & Community Engagement_Forest service and fuel reduction cooperation and joint roadmap __2021 | 346 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A
SDGE | 2021-05-03 | Stakeholder Cooperation & Community Engagement | 5.3.10. | Other | Non‐Conductive Balloon Initiative | Non‐Conductive Balloon Initiative | Non‐Conductive Balloon Initiative (7.3.10.5) |  | SDGE_Stakeholder Cooperation & Community Engagement_Non‐Conductive Balloon Initiative__2021 | 346 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | SDG&E is pursuing the development of a non-conductive balloon with a major manufacturer in the balloon industry. Both companies are working collaboratively to develop a prototype non-conductive balloon, which will not cause an electrical fault when it comes in contact with overhead distribution power lines. If the prototypes continue to have success in the high voltage tests, the balloon manufacturer may seek improvements to lower the production costs and apply the technology to complex balloon designs. | In the first quarter, SDG&E continued testing balloon prototypes at a test lab in Georgia. Balloons were tested at 33kv under conditions similar to SCE's overhead power lines and they passed. |  |  |  | In Progress

## Initiative mapping-DO NOT EDIT (hidden)
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment & Mapping | 1 | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | Risk Assessment & Mapping | 5.3.1. | PGE
Risk Assessment & Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 5.3.2. | SCE
Risk Assessment & Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 5.3.3. | SDGE
Risk Assessment & Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 5.3.4. | BVES
Risk Assessment & Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 5.3.5. | LU
Situational Awareness & Forecasting | 1 | Advanced weather monitoring and weather stations | Grid Operations & Operating Protocols | 5.3.6. | PC
Situational Awareness & Forecasting | 2 | Continuous monitoring sensors | Data Governance | 5.3.7. | TBC
Situational Awareness & Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 5.3.8. | HWT
Situational Awareness & Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 5.3.9.
Situational Awareness & Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 5.3.10.
Situational Awareness & Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment
Grid Design & System Hardening | 1 | Capacitor maintenance and replacement program
Grid Design & System Hardening | 2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design & System Hardening | 3 | Covered conductor installation
Grid Design & System Hardening | 4 | Covered conductor maintenance
Grid Design & System Hardening | 5 | Crossarm maintenance, repair, and replacement
Grid Design & System Hardening | 6 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design & System Hardening | 7 | Expulsion fuse replacement
Grid Design & System Hardening | 8 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design & System Hardening | 9 | Installation of system automation equipment
Grid Design & System Hardening | 10 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design & System Hardening | 11 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design & System Hardening | 12 | Other corrective action
Grid Design & System Hardening | 13 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design & System Hardening | 14 | Transformers maintenance and replacement
Grid Design & System Hardening | 15 | Transmission tower maintenance and replacement
Grid Design & System Hardening | 16 | Undergrounding of electric lines and/or equipment
Grid Design & System Hardening | 17 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management & Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management & Inspections | 2 | Detailed inspections of transmission electric lines and equipment
Asset Management & Inspections | 3 | Improvement of inspections
Asset Management & Inspections | 4 | Infrared inspections of distribution electric lines and equipment
Asset Management & Inspections | 5 | Infrared inspections of transmission electric lines and equipment
Asset Management & Inspections | 6 | Intrusive pole inspections
Asset Management & Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management & Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management & Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management & Inspections | 10 | Other discretionary inspection of transmission electric lines and
Asset Management & Inspections | 11 | Patrol inspections of distribution electric lines and equipment
Asset Management & Inspections | 12 | Patrol inspections of transmission electric lines and equipment
Asset Management & Inspections | 13 | Pole loading assessment program to determine safety factor
Asset Management & Inspections | 14 | Quality assurance / quality control of inspections
Asset Management & Inspections | 15 | Substation inspections
Vegetation Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Vegetation Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions
Vegetation Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation Management & Inspections | 6 | Improvement of inspections
Vegetation Management & Inspections | 7 | LiDAR inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 8 | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 9 | Other discretionary inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 10 | Other discretionary inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 11 | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation Management & Inspections | 12 | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation Management & Inspections | 13 | Quality assurance / quality control of vegetation inspections
Vegetation Management & Inspections | 14 | Recruiting and training of vegetation management personnel
Vegetation Management & Inspections | 15 | Remediation of at-risk species
Vegetation Management & Inspections | 16 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation Management & Inspections | 17 | Substation inspection
Vegetation Management & Inspections | 18 | Substation vegetation management
Vegetation Management & Inspections | 19 | Vegetation inventory system
Vegetation Management & Inspections | 20 | Vegetation management to achieve clearances around electric lines and equipment
Grid Operations & Operating Protocols | 1 | Automatic recloser operations
Grid Operations & Operating Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Operating Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Operating Protocols | 4 | Protocols for PSPS re-energization
Grid Operations & Operating Protocols | 5 | PSPS events and mitigation of PSPS impacts
Grid Operations & Operating Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of near miss data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 3 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 4 | Forest service and fuel reduction cooperation and joint roadmap
| x | Other