## CalPA DR1 - Q10
| 2019 WMP Filing Target | 2020 WMP Filing Targets |  |  | 2019 & 2020 Actuals
Program target |  | 2020 Target | 2021 Target | 2022 Target | 2019 Actual | 2020 Actual | Units | Comments
Install weather stations | 13 | 20 | 20 | 20 | 13 | 30 | Weather stations
Install cameras | NA | NA | NA | NA | NA | 4 | Cameras
Install wireless fault indicators | 500 | 500 | 500 | 500 | 594 | 502 | Wireless fault indicators
Replace SCADA capacitors | NA | 30 | 30 | 38 | NA | 30 | SCADA capacitors
Harden the overhead distribution system - covered conductor | 0 | 1 | 10 | 10 | 0 | 1.9 | miles
Replace and reinforce poles | 841 | 670 | 670 | 670 | 725 | 598 | poles
Replace expulsion fuses | 2250 | 3000 | 4000 | 1535 | 2490 | 3179 | expulsion fuses
Install sectionalizing devices | 7 | 10 | 10 | 10 | 7 | 23 | sectionalizing device
Install micro grids | 0.5 | 3 | 3 | 1 | 0 | 4 | micro grids
Enable circuits with Advanced Protection | 8 | 8 | 9 | 15 | 8 | 6 | circuits
Replace hotline clamps | 500 | 1650 | 1650 | 1650 | 660 | 2061 | hotline clamps
Provide generators to MBL and AFN customers impacted by PSPS | 65 | 1250 | 1500 | 1880 | 65 | 1420 | generators
Provide whole facility generators to customers impacted by PSPS | NA | 300 | 300 | 300 | NA | 75 | generators
Provide generator rebates to customers impacted by PSPS within HFTD | NA | 130 | 130 | 130 | NA | 1274 | generators
Underground electric lines/equipment | 1.5 | 10 | 50 | 60 | 2.6 | 15.8 | miles
Harden the overhead distribution system - bare wire | 130 | 102 | 14 | 8.4 | 122.9 | 99.5 | miles
Harden transmission system - overhead | 10 | 19.3 | 24.4 | 18.5 | 7 | 21.6 | miles
Harden transmission system - underground |  | 0 | 6 | 0 | 3 | 0 | miles
Harden transmission system - distribution underbuild |  | 12.3 | 21.8 | 7.9 | 10 | 9.4 | miles
Fire harden CNF - transmission overhead | 68 | 29 | 0 | 0 | 25 | 29.1 | miles
Fire harden CNF - distribution overhead |  | 50 | 1 | 0 | 26.4 | 46.8 | miles
Fire harden CNF - distribution underground |  | 14 | 0.5 | 0 | 8.7 | 14.4 | miles
Replace lightning arrestors | NA | 0 | 924 | 1848 | NA | 0 | lightning arrestors
Install LTE communication network stations | NA | 25 | 65 | 85 | NA | 15 | base stations
Perform compliance maintenance program HFTD - 5-year detailed | 16500 | 17500 | 22500 | 18500 | 16329 | 17977 | inspections
Perform transmission system inspections - detailed | 37 | 41 | 41 | 41 | 37 | 2679 | inspections | 2020 targets and 2019 actual presented in TL's, now tracking by structure to align with distribution inspections
Perform distribution infrared inspections | NA | 8500 | 8500 | 8500 | NA | 13077 | inspections
Perform transmission system inspections - infrared | 113 | 113 | 113 | 113 | 112 | 6481 | inspections | 2020 targets and 2019 actual presented in TL's, now tracking by structure to align with distribution inspections
Perform compliance maintenance program HFTD - wood pole instrusive | 19000 | 18000 | 8000 | 400 | 19729 | 14450 | inspections
Perform HFTD Tier 3 inspections | 11500 | 11500 | 11500 | 12500 | 15176 | 11864 | inspections
Perform drone assessments of distribution infrastructure | 15000 | 33000 | 19750 | 16500 | 10400 | 37310 | inspections
Perform drone assessments of transmission infrastructure | NA | NA | NA | NA | NA | 2679 | inspections
Perform transmission system inspections - aerial 69kV Tier 3 visual | 27 | 27 | 27 | 27 | 22 | 1957 | inspections | 2020 targets and 2019 actual presented in TL's, now tracking by structure to align with distribution inspections
Perform compliance maintenance program HFTD - annual patrols | 86000 | 86000 | 86000 | 86000 | 86401 | 86075 | inspections
Perform transmission system inspections - visual | 117 | 117 | 117 | 117 | 116 | 6940 | inspections | 2020 targets and 2019 actual presented in TL's, now tracking by structure to align with distribution inspections
Perform substation system inspections | 300 | 330 | 330 | 330 | 301 | 405 | inspections
Perform tree trimming | 455000 | 455000 | 455000 | 455000 | 453330 | 451207 | trees inspected
Perform fuels management | 500 | 500 | 500 | 500 | 511 | 324 | poles cleared
Perform enhanced inspections, patrols and trimming | 7500 | 17000 | 17000 | 17000 | 8310 | 17095 | trees trimmed/removed
Perform pole brushing | 35500 | 35500 | 35500 | 35500 | 34000 | 36563 | poles brushed