## 2020
Report | Utilitiy | Inpsection Date | Report Date | County | Circuit | Stucture Number | Coordinates | Defect Description | Defect Severity | Defect Category | Required Remiditation Date | Responsible | Status | Completion Date
IG-SDGE-002 | SDG&E | 2020-10-29 | 2020-11-05 | San Diego | 1021 | P117743 | 33.23297385,-117.04618931 | Work not completed as identified by utility | Moderate | WMP3 | 2021-03-29 | PRIME | Pending
IG-SDGE-002 | SDG&E | 2020-10-29 | 2020-11-05 | San Diego | 1021 | P117746 | 33.23311328,-117.04744022 | Work not completed as identified by utility | Moderate | WMP3 | 2021-03-29 | PRIME | Pending
EW-SDGE-002 | SDG&E | 2020-10-28 | 2020-11-05 | San Diego | 1021 | P517194 | 33.23129503,-117.03905107 | Guywire contacting veg amd com above insulator | Minor | WMP5 | 2021-10-28 | VM | Pending
IG-SDGE-001 | SDG&E | 2020-10-28 | 2020-11-05 | San Diego | 215 | P718161 | 33.25508498,-116.99176049 | Vegetation contacting wire above guy insulator | Minor | WMP5 | 2021-10-28 | VM | Pending
IG-SDGE-001 | SDG&E | 2020-10-28 | 2020-11-05 | San Diego | 215 | P718158 | 33.25491544,-116.99092174 | Vegetation contacting wire above guy insulator | Minor | WMP5 | 2021-10-28 | VM | Pending
EW-SDGE-001 | SDG&E | 2020-10-28 | 2020-11-05 | San Diego | 908 | P117352 | 33.2561972,-117.02308332 | Guywire in contact with com wire | Minor | WMP3 | 2021-10-28 | CMP | Pending
EW-SDGE-001 | SDG&E | 2020-10-28 | 2020-11-05 | San Diego | 908 | P615107 | 33.25614561,-117.02909938 | Groundwire exposed | Minor | WMP3 | 2021-10-28 | CMP | Pending
IG-SDGE-003 | SDG&E | 2020-12-16 | 2020-12-24 | San Diego | 240 | P72670 | 32.87620557,-116.91837513 | Down guy in contact with primary cross arm GO95 defect | Minor | WMP3 | 2021-12-16 | CMP | Pending
EW-SDGE-003 | SDG&E | 2020-12-16 | 2020-12-28 | San Diego | 357 | P176021 | 32.82114115,-116.78621782 | Vegetation is in contact with guy wire above the insulator | Minor | WMP5 | 2021-12-16 | VM | Pending
IG-SDGD-004 | SDG&E | 2020-12-17 | 2020-12-24 | San Diego | 176 | P119362 | 32.99773218,-117.00397463 | Vegetation Management to achieve clearances around electric lines and equipment | Minor | WMP5 | 2021-12-17 | VM | Pending