## 2025_Q2 PERFORMANCE SUMMARY
CPUC Rule 21 Timeline Compliance Reporting - Performance Summary - SDGE- 2025-Q2
Milestone | Description | % Met | Total Opportunities | Tariff Standard | Minimum Days | Maximum Days | Median Days
A | Time from Receipt of Submission to Acknowledgement | 100% | 221 | 3 | 1 | 1 | 1
B | Time from Receipt of Submission to Deemed Complete | 93% | 221 | 10 | 0 | 95^ | 1
C | Time from Deemed Complete to Issuance of Fast Track Initial Review Results | 100% | 79 | 15 | 1 | 15 | 6
D | Time from Start of Fast Track Supplemental Review to Issuance of Fast Track Supplemental Review Results | 100% | 1 | 20 | 0 | 18 | N/A
E | Time from Electrical Independence Test Start to Electrical Independence Test Completion | N/A | 0 | 20 | 0 | 0 | 0
F | Time from Electrical Independence Test Completion to Electrical Independence Test Results Scoping Meeting | Excluded - No Tariff Standard to Measure Performance
G | Time from Study Scoping Meeting to Issuance of Study Agreement | N/A | 0 | 15 | 0 | 0 | 0
H | Time from System Impact Study Start to System Impact Study Completion | N/A | 0 | 60 | 0 | 0 | 0
I | Time to Issue Draft Generator Interconenction Agreement from Applicable Milestone (If Fast Track Process) | N/A | N/A | 15 | N/A | N/A | N/A
J | Time from Issuance of Draft Generator Interconnection Agreement or Final Study Report to Execution of Generator Interconnection Agreement | Excluded - No Tariff Standard to Measure Performance
K | Time from Completion of Customer Obligations/Commissioning Test to Issuance of Permission to Operate | 100% | 221 | 30 | 0 | 15 | 0
L | Total Time from Submission of Interconnection Request to Permission to Operate | Excluded - No Tariff Standard to Measure Performance
M | Time from Request to Consider Modification to Determine Whether Modification is Material | N/A | 0 | 10 | 0 | 0 | 0
N | Time for Responding to Line-Side Tap Variance Requests | Excluded - Does Not Apply to SDG&E
O | Time to Issuance of Invoice for Net Generation Output Meter Design | 100% | 31 | 20 | 1 | 19 | 4
P | Time for Net Generation Output Meter Installation | 100% | 31 | 20 | 3 | 9 | 7
Q | Time from Customer Agreement to Proceed with Upgrades to Final Design to Issuance of Invoice | N/A | 0 | 60 | 0 | 0 | 0
R | Time from Customer Payment of Invoice and Completion of Customer Work to Completion of Upgrade Construction | N/A | 0 | 60 | 0 | 0 | 0
S | Time for Scheduling of Commissioning Test | Excluded - Does Not Apply to SDG&E
*BD = Business Days --- CD = Calendar Days
Tariff Standard Does Not Reflect Different Timelines Agreed Upon with Customer
^ = Projects reported on during this period include submittals from 2023 NEM-ST. Delayed time due to volume was communicated to customers and CPUC.

## PERFORMANCE DATA
MILESTONE B |  |  | MILESTONE C |  |  | MILESTONE K |  |  | MILESTONE O |  |  | MILESTONE P
| MIN # OF DAYS | 0 |  | MIN # OF DAYS | 1 |  | MIN # OF DAYS | 0 |  | MIN # OF DAYS | 1 |  | MIN # OF DAYS | 3
| MAX # OF DAYS | 95 |  | MAX # OF DAYS | 15 |  | MAX # OF DAYS | 15 |  | MAX # OF DAYS | 19 |  | MAX # OF DAYS | 9
| MEDIAN | 1 |  | MEDIAN | 6 |  | MEDIAN | 0 |  | MEDIAN | 4 |  | MEDIAN | 7
| OPPORTUNITIES | APP REVIEW TIME |  | OPPORTUNITIES | INITAL REVIEW RESULTS |  | OPPORTUNITIES | DAYS TO PTO |  | OPPORTUNITIES | NGOM INVOICE |  | OPPORTUNITIES | NGOM SET
| 221 | 0 |  | 79 | 1 |  | 221 | 0 |  | 31 | 1 |  | 31 | 3
|  | 0 |  |  | 1 |  |  | 0 |  |  | 1 |  |  | 3
|  | 0 |  |  | 1 |  |  | 0 |  |  | 3 |  |  | 4
|  | 1 |  |  | 1 |  |  | 0 |  |  | 3 |  |  | 4
|  | 1 |  |  | 1 |  |  | 0 |  |  | 3 |  |  | 4
|  | 1 |  |  | 1 |  |  | 0 |  |  | 3 |  |  | 4
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 4
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 5
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 5
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 5
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 6
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 6
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 6
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 7
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 7
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 7
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 7
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 7
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 7
|  | 1 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 7
|  | 1 |  |  | 1 |  |  | 0 |  |  | 5 |  |  | 7
|  | 1 |  |  | 2 |  |  | 0 |  |  | 5 |  |  | 7
|  | 1 |  |  | 2 |  |  | 0 |  |  | 6 |  |  | 7
|  | 1 |  |  | 3 |  |  | 0 |  |  | 6 |  |  | 7
|  | 1 |  |  | 3 |  |  | 0 |  |  | 6 |  |  | 7
|  | 1 |  |  | 3 |  |  | 0 |  |  | 11 |  |  | 7
|  | 1 |  |  | 3 |  |  | 0 |  |  | 15 |  |  | 7
|  | 1 |  |  | 3 |  |  | 0 |  |  | 15 |  |  | 8
|  | 1 |  |  | 3 |  |  | 0 |  |  | 16 |  |  | 8
|  | 1 |  |  | 4 |  |  | 0 |  |  | 17 |  |  | 8
|  | 1 |  |  | 4 |  |  | 0 |  |  | 19 |  |  | 9
|  | 1 |  |  | 4 |  |  | 0
|  | 1 |  |  | 4 |  |  | 0
|  | 1 |  |  | 4 |  |  | 0
|  | 1 |  |  | 4 |  |  | 0
|  | 1 |  |  | 4 |  |  | 0
|  | 1 |  |  | 5 |  |  | 0
|  | 1 |  |  | 5 |  |  | 0
|  | 1 |  |  | 6 |  |  | 0
|  | 1 |  |  | 6 |  |  | 0
|  | 1 |  |  | 7 |  |  | 0
|  | 1 |  |  | 7 |  |  | 0
|  | 1 |  |  | 7 |  |  | 0
|  | 1 |  |  | 7 |  |  | 0
|  | 1 |  |  | 7 |  |  | 0
|  | 1 |  |  | 7 |  |  | 0
|  | 1 |  |  | 8 |  |  | 0
|  | 1 |  |  | 8 |  |  | 0
|  | 1 |  |  | 8 |  |  | 0
|  | 1 |  |  | 8 |  |  | 0
|  | 1 |  |  | 8 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 9 |  |  | 0
|  | 1 |  |  | 10 |  |  | 0
|  | 1 |  |  | 10 |  |  | 0
|  | 1 |  |  | 10 |  |  | 0
|  | 1 |  |  | 10 |  |  | 0
|  | 1 |  |  | 10 |  |  | 0
|  | 1 |  |  | 10 |  |  | 0
|  | 1 |  |  | 10 |  |  | 0
|  | 1 |  |  | 11 |  |  | 0
|  | 1 |  |  | 11 |  |  | 0
|  | 1 |  |  | 14 |  |  | 0
|  | 1 |  |  | 15 |  |  | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 0
|  | 1 | [5 empty] | 1
|  | 1 | [5 empty] | 1
|  | 2 | [5 empty] | 1
|  | 2 | [5 empty] | 1
|  | 2 | [5 empty] | 1
|  | 2 | [5 empty] | 1
|  | 2 | [5 empty] | 1
|  | 2 | [5 empty] | 1
|  | 3 | [5 empty] | 1
|  | 3 | [5 empty] | 1
|  | 3 | [5 empty] | 1
|  | 3 | [5 empty] | 1
|  | 3 | [5 empty] | 1
|  | 4 | [5 empty] | 1
|  | 4 | [5 empty] | 1
|  | 4 | [5 empty] | 1
|  | 4 | [5 empty] | 2
|  | 4 | [5 empty] | 2
|  | 4 | [5 empty] | 2
|  | 4 | [5 empty] | 2
|  | 4 | [5 empty] | 2
|  | 4 | [5 empty] | 2
|  | 5 | [5 empty] | 2
|  | 5 | [5 empty] | 2
|  | 5 | [5 empty] | 2
|  | 5 | [5 empty] | 2
|  | 5 | [5 empty] | 2
|  | 5 | [5 empty] | 2
|  | 6 | [5 empty] | 2
|  | 6 | [5 empty] | 2
|  | 6 | [5 empty] | 2
|  | 6 | [5 empty] | 2
|  | 6 | [5 empty] | 2
|  | 6 | [5 empty] | 2
|  | 6 | [5 empty] | 2
|  | 6 | [5 empty] | 3
|  | 6 | [5 empty] | 3
|  | 6 | [5 empty] | 3
|  | 6 | [5 empty] | 3
|  | 6 | [5 empty] | 3
|  | 7 | [5 empty] | 3
|  | 7 | [5 empty] | 3
|  | 7 | [5 empty] | 3
|  | 7 | [5 empty] | 3
|  | 7 | [5 empty] | 3
|  | 7 | [5 empty] | 3
|  | 7 | [5 empty] | 3
|  | 8 | [5 empty] | 3
|  | 8 | [5 empty] | 3
|  | 8 | [5 empty] | 3
|  | 8 | [5 empty] | 3
|  | 8 | [5 empty] | 3
|  | 8 | [5 empty] | 3
|  | 8 | [5 empty] | 4
|  | 8 | [5 empty] | 4
|  | 8 | [5 empty] | 4
|  | 8 | [5 empty] | 4
|  | 8 | [5 empty] | 4
|  | 8 | [5 empty] | 4
|  | 9 | [5 empty] | 4
|  | 9 | [5 empty] | 4
|  | 9 | [5 empty] | 4
|  | 9 | [5 empty] | 4
|  | 9 | [5 empty] | 4
|  | 9 | [5 empty] | 5
|  | 9 | [5 empty] | 5
|  | 9 | [5 empty] | 5
|  | 9 | [5 empty] | 5
|  | 9 | [5 empty] | 5
|  | 9 | [5 empty] | 5
|  | 10 | [5 empty] | 5
|  | 10 | [5 empty] | 6
|  | 10 | [5 empty] | 6
|  | 10 | [5 empty] | 6
|  | 10 | [5 empty] | 6
|  | 10 | [5 empty] | 6
|  | 10 | [5 empty] | 6
|  | 10 | [5 empty] | 7
|  | 10 | [5 empty] | 7
|  | 10 | [5 empty] | 7
|  | 10 | [5 empty] | 7
|  | 10 | [5 empty] | 7
|  | 10 | [5 empty] | 8
|  | 10 | [5 empty] | 8
|  | 10 | [5 empty] | 8
|  | 10 | [5 empty] | 8
|  | 11 | [5 empty] | 8
|  | 11 | [5 empty] | 8
|  | 12 | [5 empty] | 9
|  | 13 | [5 empty] | 9
|  | 14 | [5 empty] | 9
|  | 48 | [5 empty] | 9
|  | 58 | [5 empty] | 9
|  | 59 | [5 empty] | 9
|  | 68 | [5 empty] | 9
|  | 68 | [5 empty] | 10
|  | 68 | [5 empty] | 11
|  | 68 | [5 empty] | 12
|  | 68 | [5 empty] | 14
|  | 95 | [5 empty] | 14
|  | 95 | [5 empty] | 15

## OP4 PROCESSING COSTS
2025 Q2 Processing Cost Summary (≤ 1MW Rule 21 Non-NEM)
New Rule 21 Non-NEM projects Using “midpoint” of pay ranges for the labor rate component (based on the employees included in the “stage of processing” buckets)
Stage of Processing: | Number Evaluated | Total Cost per Stage | Average Cost per Stage
Application Review and Deficiency Clearing | 143 | 5863 | 41
Technical Review/Engineering | 143 | 9724 | 68
Agreement Execution, Insurance Requirements, Accounting/Costing | 143 | 8700 | 60.8392
Field Inspection | 2 | 212 | 106
Post Agreement Execution to PTO | 143 | 19734 | 138
| Average Cost per Project* |  | 413.8392
*Costs are based on estimated time spent reviewing projects

## COVERSHEET FOR ALL_IOUs
Rule 21 Timeline Reporting Coversheet
This coversheet aggregates quarterly PG&E, SCE and SDG&E (Utilities) interconnection timeline reports from January 2021. Utilities submit quarterly reports to the Rulemaking R.17-07-007 Service List. To sign up for the service list, click the link below in row 7 and navigate to the "Subscribe" button near the top of the page. Quarterly reports will also be archived and posted at the CPUC Rule 21 Webpage (link below in cell A6).
Links to relevant information:
D.20-09-035 (see Issue 12 and Issue 8c)
Electric Rule 21 Webpage
Subscription to Rulemaking 1707007 Service List
Notes for interpreting spreadsheet: Row 9 indicates the relevant Ordering Paragraph (OP) in Decision D.20-09-035 that mandated the timeline tracking, which is specified in Row 10. An asterisk next to the OP in Row 9 indicates that customer time (i.e., time that is outside of the direct control of the Utility) is included in the tracked time. Row 10 draws directly from text in Issues 12 and 8c in D.20-09-035. The text in red is intended to increase clarity beyond the Issue 12 language in the OP. References to the Rule 21 Tariff section appears in parenthesis for ease of reference.
Project Specifics | [8 empty] | OP 22 a) | OP 22 b)* | OP 22 c) (no upgrade) | OP 22 c) (if upgrade required) | OP 22 d) (no upgrade) | OP 22 d) (if upgrade required) | OP 22 e) (if Electrical Independence Test required) | OP 22 f) (if Detailed Study Required)* | OP 22 g) (if Detailed Study Required)* | OP 22 h) (if Detailed Study required) | OP 22 i) |  | OP 22 i) | OP 22 j)* | OP 22 k) | OP 22 l)* | OP 22 m) | OP 22 m) | OP 22 n) | OP 24 o) | OP 24 p) | OP 24 q) | OP 22 r) | OP 22 s)* | OP 4 | OP 4 | OP 4
Utility | ZIP Code | Project ID | NEM / Non-NEM | Project Type (Request Type) | Project Status (Current Phase) | Technology Type | Size (kW - Net Nameplate Rating) | Cost Envelope Requested? | Time from Submission of Interconnection Request to Utility's Acknowledgement of Receipt of Interconnection Request | Time from submission of Interconnection Request to time deemed complete | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if no upgrades are required) | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if upgrades are required) | Time from Supplemental Review start date to completion of Supplemental Review (if no upgrade is required) | Time from Supplemental Review start date to completion of Supplemental Review (if upgrade required) | Time from receipt of Detailed Study Deposit (F.1.b) to perform Electrical Independence Test (Screens Q and R) and issue Electrical Independence Test (F.3.c.ii) results (if Electrical Independence Test required) | Time from Electrical Independence Test results issuance to scheduling of Detailed Study Scoping Meeting (F.3.b.i) (if Detailed Study required) | Time from Detailed Study Scoping Meeting held to issuance of draft Detailed Study Agreement (F.3.b.ii) (if Detailed Study required) | Time from Detailed Study Agreement execution to issuance of System Impact Study results/report (F.3.b.i.-ii) (if Detailed Study required) | Time from Applicable Milestone to Provision of Draft Generator Agreement (see applicable milestone in column U) | Permission to Operate | Applicable Milestone (referenced in column U) | Time from issuance of draft Generator Interconnection Agreement to date Generator Interconnection Agreement executed | Time from when the Producer completes "satisfactory compliance with the terms of all applicable agreements" to when the utility issues written Permission to Operate (F.5.b) | Total time from Utility receipt of Interconnection Request to issuance of Permission to Operate | Time from customer request to consider whether a proposed modification is material to issuance of material modification analysis/results by utility (F.3.b.v) (Note: customers are not limited in the number of material modification requests and the total number of customer material modification requests appears in column Z) | Total Number of Customer Material Modification Requests (referenced in column Y) | Time for responding to line-side taps variance requests (for Utilities that require a variance request) | Time from Utility confirmation that customer has taken all necessary steps to prepare for construction to Utility completion of design and invoice of net generation output meter | Time from date Utility issues a Service Request to date installation of net generation output meter is complete | Distribution Upgrades: Time from Utility confirmation that customer has taken all necessary steps to initiate Preliminary Design process to Utility submission of Preliminary Design to customer | Distribution Upgrades: Time from Customer Acceptance of Preliminary Design to Utility issuance of Final Design to Customer | Time from Utility scheduling commissioning test to completion of commissioning testing | (Y/N) Would Integration Capacity Analysis outdated values have lead to Interconnection Requests failing the Initial Review? | If Integration Capacity Analysis oudated values would have led to Interconnection Requests Failing the Initial Review, what cost was associated with the updates to the ICA necessitated by evaluating the outdated values? | Actual Costs Associated with processing of interconnection applications (as discussed in proposal 8s). | Notes
SDGE | 92040 | 337161 | NEM | NEMA | APPROVED | SOLAR PV | 104.068 | NO | 1 | 6 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 5 | 218 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92059 | 339132 | NEM | NEM-ST | APPROVED | SOLAR PV & BATTERY STORAGE | 792.169 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | INTERCONNECTION COMPLETE | N/A | 0 | 72 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92064 | 341473 | NEM | NEM-ST | APPROVED | SOLAR PV | 38.25 | NO | 1 | 4 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | INTERCONNECTION COMPLETE | N/A | 8 | 1239 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 342197 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 69.7 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 936 | N/A | N/A | N/A | 5 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92131 | 357122 | NEM | NEMA | APPROVED | SOLAR PV | 1548.752 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 3 | 305 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92130 | 358760 | NEM | NEM-ST NGOM | APPROVED | SOLAR PV & BATTERY STORAGE | 300 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 329 | N/A | N/A | N/A | 3 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92108 | 364445 | NON-NEM | RULE 21 AES INADVERTANT EXPORT | APPROVED | BATTERY STORAGE | 210 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 9 | 1004 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 759
SDGE | 92127 | 366395 | NEM | NEM-ST | APPROVED | SOLAR PV | 305 | NO | 1 | 9 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | INTERCONNECTION COMPLETE | N/A | 0 | 204 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92069 | 394078 | NEM | NEM-ST NGOM | APPROVED | SOLAR PV & BATTERY STORAGE | 491 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | INTERCONNECTION COMPLETE | N/A | 7 | 24 | N/A | N/A | N/A | 1 | 3 | N/A | N/A | N/A | N/A | N/A
SDGE | 92081 | 405091 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 25 | NO | 1 | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | INTERCONNECTION COMPLETE | N/A | 1 | 313 | N/A | N/A | N/A | 1 | 6 | N/A | N/A | N/A | N/A | N/A
SDGE | 92040 | 407008 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 30.741 | NO | 1 | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 650 | N/A | N/A | N/A | 6 | 6 | N/A | N/A | N/A | N/A | N/A
SDGE | 92040 | 412835 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33.442 | NO | 1 | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | INTERCONNECTION COMPLETE | N/A | 9 | 227 | N/A | N/A | N/A | 6 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92040 | 412906 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 34.425 | NO | 1 | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | INTERCONNECTION COMPLETE | N/A | 9 | 227 | N/A | N/A | N/A | 6 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92014 | 414117 | NEM | NEM-ST | APPROVED | SOLAR PV | 45.6 | NO | 1 | 5 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 0 | 806 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92081 | 415109 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 35.76 | NO | 1 | 3 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | INTERCONNECTION COMPLETE | N/A | 4 | 145 | N/A | N/A | N/A | 3 | 8 | N/A | N/A | N/A | N/A | N/A
SDGE | 92081 | 416495 | NEM | NEMA | APPROVED | SOLAR PV | 188 | NO | 1 | 8 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 164 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92019 | 416875 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 45.245 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 3 | 245 | N/A | N/A | N/A | 19 | 5 | N/A | N/A | N/A | N/A | N/A
SDGE | 92058 | 422976 | NEM | NEMA | APPROVED | SOLAR PV | 51.265 | NO | 1 | 10 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | INTERCONNECTION COMPLETE | N/A | 14 | 290 | N/A | N/A | N/A | 15 | 5 | N/A | N/A | N/A | N/A | N/A
SDGE | 92127 | 424406 | NEM | NEMA | APPROVED | SOLAR PV | 738 | NO | 1 | 5 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | INTERCONNECTION COMPLETE | N/A | 9 | 231 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92105 | 426421 | NEM | NEM-ST | APPROVED | SOLAR PV | 200.924 | NO | 1 | 58 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | INTERCONNECTION COMPLETE | N/A | 8 | 679 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92069 | 433221 | NEM | NEM-ST | APPROVED | SOLAR PV & BATTERY STORAGE | 449 | NO | 1 | 1 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | INTERCONNECTION COMPLETE | N/A | 0 | 733 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92104 | 436162 | NEM | NEM-ST | APPROVED | SOLAR PV | 237.281 | NO | 1 | 7 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 0 | 113 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92154 | 438596 | NEM | NEM-ST | APPROVED | SOLAR PV | 988.82 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 0 | 669 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92025 | 439513 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 96.359 | NO | 1 | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 2 | 232 | N/A | N/A | N/A | 11 | 8 | N/A | N/A | N/A | N/A | N/A
SDGE | 92084 | 443935 | NEM | NEM-ST | APPROVED | SOLAR PV | 39.574 | NO | 1 | 48 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | INTERCONNECTION COMPLETE | N/A | 0 | 600 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92083 | 443953 | NEM | NEM-ST | APPROVED | SOLAR PV | 65.557 | NO | 1 | 59 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 0 | 688 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92114 | 447263 | NEM | NEMA | APPROVED | SOLAR PV | 43.826 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 591 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92114 | 447481 | NEM | NEMA | APPROVED | SOLAR PV | 43.826 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | INTERCONNECTION COMPLETE | N/A | 0 | 590 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453406 | NEM | NEM-ST | APPROVED | SOLAR PV | 126.614 | NO | 1 | 68 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 1 | 625 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453460 | NEM | NEM-ST | APPROVED | SOLAR PV | 43.198 | NO | 1 | 68 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 1 | 625 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453507 | NEM | NEM-ST | APPROVED | SOLAR PV | 53.625 | NO | 1 | 68 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | INTERCONNECTION COMPLETE | N/A | 0 | 665 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453611 | NEM | NEM-ST | APPROVED | SOLAR PV | 48.784 | NO | 1 | 68 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 0 | 680 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453620 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453713 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 32 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453769 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 32 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453792 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453827 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453828 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453855 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453862 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453881 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453883 | NEM | NEM-ST | APPROVED | SOLAR PV | 125.869 | NO | 1 | 68 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | INTERCONNECTION COMPLETE | N/A | 0 | 688 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453900 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453903 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453915 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453946 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 455278 | NEM | NEM-ST | APPROVED | SOLAR PV | 93.743 | NO | 1 | 95 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 0 | 631 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92009 | 456341 | NEM | NEM-ST | APPROVED | SOLAR PV | 83.746 | NO | 1 | 95 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 0 | 640 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92036 | 458544 | NEM | NEMA | APPROVED | SOLAR PV | 34 | NO | 1 | 6 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | INTERCONNECTION COMPLETE | N/A | 0 | 389 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 458720 | NEM | NBT | APPROVED | SOLAR PV | 45.988 | NO | 1 | 9 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | INTERCONNECTION COMPLETE | N/A | 1 | 358 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92677 | 458813 | NON-NEM | RULE 21 AES INADVERTANT EXPORT | APPROVED | BATTERY STORAGE | 10 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | INTERCONNECTION COMPLETE | N/A | 0 | 476 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 459135 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 10 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 0 | 641 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 459566 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 2567.2 | NO | 1 | 1 | 8 | N/A | 18 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | INTERCONNECTION COMPLETE | N/A | 3 | 591 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91950 | 459590 | NON-NEM | RULE 21 NON EXPORT | APPROVED | INTERNAL COMBUSTION ENGINE | 350 | NO | 1 | 14 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | INTERCONNECTION COMPLETE | N/A | 0 | 649 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 759
SDGE | 92020 | 462948 | NEM | NEMA | APPROVED | SOLAR PV | 63.452 | NO | 1 | 9 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 10 | 147 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92118 | 466696 | NEM | NBT | APPROVED | SOLAR PV | 584.508 | NO | 1 | 2 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | INTERCONNECTION COMPLETE | N/A | 0 | 487 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92118 | 466701 | NEM | NBT | APPROVED | SOLAR PV | 81.514 | NO | 1 | 10 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 14 | 329 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92108 | 466723 | NEM | NBT | APPROVED | SOLAR PV | 65.85 | NO | 1 | 8 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | INTERCONNECTION COMPLETE | N/A | 0 | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92108 | 466730 | NEM | NBT | APPROVED | SOLAR PV | 43.33 | NO | 1 | 8 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | INTERCONNECTION COMPLETE | N/A | 0 | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92123 | 467643 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 39.129 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | INTERCONNECTION COMPLETE | N/A | 1 | 252 | N/A | N/A | N/A | 17 | 6 | N/A | N/A | N/A | N/A | N/A
SDGE | 92115 | 467918 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 30.617 | NO | 1 | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 3 | 152 | N/A | N/A | N/A | 4 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92024 | 467943 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 70 | NO | 1 | 2 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | INTERCONNECTION COMPLETE | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 470859 | NEM | NEM-ST | APPROVED | BATTERY STORAGE | 530 | NO | 1 | 4 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 1 | 279 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91978 | 471298 | NEM | NEM-ST | APPROVED | SOLAR PV | 94.685 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 377 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92123 | 471375 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 113 | NO | 1 | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 1 | 105 | N/A | N/A | N/A | 15 | 8 | N/A | N/A | N/A | N/A | N/A
SDGE | 92084 | 478747 | NEM | NBT | APPROVED | SOLAR PV | 565.287 | NO | 1 | 5 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | INTERCONNECTION COMPLETE | N/A | 5 | 350 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91941 | 478818 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92118 | 478820 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92127 | 478825 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.53 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 478922 | NEM | NEM-ST | APPROVED | SOLAR PV | 112 | NO | 1 | 6 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | INTERCONNECTION COMPLETE | N/A | 8 | 216 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92009 | 479181 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 479188 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | 5 | 9 | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 479195 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 221.328 | NO | 1 | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 3 | 165 | N/A | N/A | N/A | 3 | 5 | N/A | N/A | N/A | N/A | N/A
SDGE | 91913 | 479260 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92109 | 479737 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 78 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92154 | 479803 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 105 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 479991 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 78 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 480110 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | INTERCONNECTION COMPLETE | N/A | 0 | 98 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92024 | 480612 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 8 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92004 | 480969 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 481516 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92126 | 483030 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92057 | 483031 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 5 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92025 | 483309 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 82 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91941 | 483312 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91950 | 483367 | NEM | NBT | APPROVED | SOLAR PV | 34.138 | NO | 1 | 8 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 1 | 138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91950 | 483475 | NEM | NBT-V | APPROVED | SOLAR PV | 48.52 | NO | 1 | 3 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 9 | 158 | N/A | N/A | N/A | 16 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 91911 | 483627 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 108 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 483694 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 483757 | NEM | NBT-V | APPROVED | SOLAR PV | 82.613 | NO | 1 | 2 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | INTERCONNECTION COMPLETE | N/A | 9 | 224 | N/A | N/A | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 483795 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 0 | 88 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92010 | 483973 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 7 | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 484625 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92054 | 484626 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92129 | 484659 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91942 | 484839 | NEM | NBT | APPROVED | SOLAR PV | 190.195 | NO | 1 | 6 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 1 | 260 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92105 | 485019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 12 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | INTERCONNECTION COMPLETE | N/A | 0 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 485174 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 485720 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 0 | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92129 | 486169 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | INTERCONNECTION COMPLETE | N/A | 0 | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91902 | 486594 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 104 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 486781 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 0 | 88 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92071 | 487299 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 79 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 487300 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 81 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 487304 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.42 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 487412 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 8 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92027 | 487465 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 8 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 487629 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 487633 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 487706 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | INTERCONNECTION COMPLETE | N/A | 0 | 124 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92029 | 487856 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 4 | 33 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 487944 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 11.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 6 | 109 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 488037 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | INTERCONNECTION COMPLETE | N/A | 0 | 42 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 488579 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 7.1 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92082 | 489448 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92120 | 489451 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 491678 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 79 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91913 | 492351 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 492387 | NEM | NEMA | APPROVED | SOLAR PV | 160 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 2 | 241 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92024 | 492529 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 38 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92673 | 493740 | NEM | NBT | APPROVED | PV | 45.67 | NO | 1 | 10 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | INTERCONNECTION COMPLETE | N/A | 15 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92673 | 493757 | NEM | NBT | APPROVED | PV | 50 | NO | 1 | 11 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | INTERCONNECTION COMPLETE | N/A | 1 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92120 | 494050 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | INTERCONNECTION COMPLETE | N/A | 0 | 125 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 494182 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 79 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 494186 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 67 | NO | 1 | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 1 | 127 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91915 | 494730 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92024 | 494853 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | INTERCONNECTION COMPLETE | N/A | 4 | 56 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92694 | 494874 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 495144 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 42 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92069 | 495322 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 4 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91941 | 495500 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.64 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 495516 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | INTERCONNECTION COMPLETE | N/A | 0 | 42 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92114 | 495520 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 495525 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | INTERCONNECTION COMPLETE | N/A | 0 | 43 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 495526 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92040 | 495527 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | INTERCONNECTION COMPLETE | N/A | 5 | 36 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 495530 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.73 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92028 | 495551 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 495556 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.8 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 495619 | NEM | NBT | APPROVED | SOLAR PV | 70.551 | NO | 1 | 7 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-14 | INTERCONNECTION COMPLETE | N/A | 5 | 186 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92154 | 495658 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.49 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 495892 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 2 | 38 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 495902 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 80 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92040 | 496083 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.4 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 3 | 38 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92078 | 496093 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92131 | 496098 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | INTERCONNECTION COMPLETE | N/A | 0 | 35 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92119 | 496111 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.07 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 9 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92114 | 496275 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 496839 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-17 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92173 | 497279 | NEM | NBT | APPROVED | SOLAR PV | 34.51 | NO | 1 | 6 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | INTERCONNECTION COMPLETE | N/A | 0 | 97 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92024 | 497366 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 1 | 66 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92102 | 497486 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.8 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 3 | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92029 | 497594 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92130 | 498518 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 498658 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.68 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 0 | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92624 | 498805 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 498906 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 3 | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92131 | 498907 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.68 | NO | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 11 | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92024 | 498929 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92118 | 499151 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.12 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 499395 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.3 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92653 | 499543 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.1 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 500807 | NEM | NEM-ST | APPROVED | SOLAR PV | 41 | NO | 1 | 8 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 0 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91913 | 501660 | NEM | NEM-ST | APPROVED | SOLAR PV | 208.3 | NO | 1 | 5 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 0 | 132 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92029 | 502371 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 2 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 502381 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 12 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 3 | 91 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 502577 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 502804 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 11.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | INTERCONNECTION COMPLETE | N/A | 0 | 57 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92075 | 502980 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 16 | NO | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 1 | 62 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92029 | 502993 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 8 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 6 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 503006 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 503014 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.85 | NO | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | INTERCONNECTION COMPLETE | N/A | 1 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 503017 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92128 | 503098 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 4 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91945 | 503550 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | INTERCONNECTION COMPLETE | N/A | 0 | 54 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 503561 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.35 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92057 | 503749 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | INTERCONNECTION COMPLETE | N/A | 0 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 503771 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92025 | 504194 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 13 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 504345 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 31 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 504608 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | INTERCONNECTION COMPLETE | N/A | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92120 | 504609 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 505424 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 2 | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92111 | 505438 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 5 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92129 | 505444 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.74 | NO | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | INTERCONNECTION COMPLETE | N/A | 0 | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 505449 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.1 | NO | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-22 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 505557 | NEM | NBT | APPROVED | PV | 72.94 | NO | 1 | 13 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 4 | 32 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92128 | 505689 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.1 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 506039 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92067 | 506265 | NON-NEM | RULE 21 AES EXPORT | APPROVED | BATTERY STORAGE | 20 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91913 | 506391 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.56 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 6 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91902 | 506533 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 506857 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | INTERCONNECTION COMPLETE | N/A | 0 | 82 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 507756 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92071 | 507897 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92673 | 508485 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92020 | 508871 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 7.8 | NO | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 6 | 76 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 509399 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18.46 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 2 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 509433 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11.78 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 6 | 26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92081 | 509494 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 8 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92130 | 509595 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 10 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | INTERCONNECTION COMPLETE | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92025 | 509646 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.85 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 12 | 41 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 509764 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.03 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 509777 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.93 | NO | 1 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92124 | 510556 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.42 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 6 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 510566 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.96 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91977 | 510737 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 7 | 18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92103 | 510751 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 0 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 510762 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 8.27 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 0 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92067 | 511209 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 62 | NO | 1 | 10 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 1 | 44 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92069 | 511315 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 3 | 46 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 511499 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.16 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | INTERCONNECTION COMPLETE | N/A | 0 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 511762 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.4 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 7 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91962 | 511990 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.56 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92123 | 513244 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.85 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92102 | 513250 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91950 | 513501 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | INTERCONNECTION COMPLETE | N/A | 0 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 513639 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 7 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91902 | 513934 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.19 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92028 | 514046 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.48 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 5 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 516093 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.74 | NO | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | INTERCONNECTION COMPLETE | N/A | 0 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389

## Q2 2025 SDGE PROJECTS
Utility | ZIP Code | Project ID | NEM OR Non-NEM | Project Type (Request Type) | Project Status (Current Phase) | Technology Type | Size (kW - Net Nameplate Rating) | Cost Envelope Requested? | Time from Submission of Interconnection Request to Utility's Acknowledgement of Receipt of Interconnection Request | Time from submission of Interconnection Request to time deemed complete | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if no upgrades are required) | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if upgrades are required) | Time from Supplemental Review start date to completion of Supplemental Review (if no upgrade is required) | Time from Supplemental Review start date to completion of Supplemental Review (if no upgrades are required) | Time from receipt of Detailed Study Deposit (F.1.b) to perform Electrical Independence Test (Screens Q and R) and issue Electrical Independence Test (F.3.c.ii) results (if Electrical Independence Test required) | Time from Electrical Independence Test results issuance to scheduling of Detailed Study Scoping Meeting (F.3.b.i) (if Detailed Study required) | Time from Detailed Study Scoping Meeting held to issuance of draft Detailed Study Agreement (F.3.b.ii) (if Detailed Study required) | Time from Detailed Study Agreement execution to issuance of System Impact Study results/report (F.3.b.i.-ii) (if Detailed Study required) | Time from Applicable Milestone to Provision of Draft Generator Agreement (see applicable milestone in column V) | PTO DATE | Applicable Milestone (referenced in column I) | Time from issuance of draft Generator Interconnection Agreement to date Generator Interconnection Agreement executed | Time from when the Producer completes "satisfactory compliance with the terms of all applicable agreements" to when the utility issues written Permission to Operate (F.5.b) | Total time from Utility receipt of Interconnection Request to issuance of Permission to Operate | Time from customer request to consider whether a proposed modification is material to issuance of material modification analysis/results by utility (F.3.b.v) (Note: customers are not limited in the number of material modification requests and the total number of customer material modification requests appears in column Z) | Total Number of Customer Material Modification Requests (referenced in column Y) | Time for responding to line-side taps variance requests (for Utilities that require a variance request) | Time from Utility confirmation that customer has taken all necessary steps to prepare for construction to Utility completion of design and invoice of net generation output meter | Time from date Utility issues a Service Request to date installation of net generation output meter is complete | Distribution Upgrades: Time from Utility confirmation that customer has taken all necessary steps to initiate Preliminary Design process to Utility submission of Preliminary Design to customer | Distribution Upgrades: Time from Customer Acceptance of Preliminary Design to Utility issuance of Final Design to Customer | Time from Utility scheduling commissioning test to completion of commissioning testing | (Y/N) Would Integration Capacity Analysis outdated values have lead to Interconnection Requests failing the Initial Review? | If Integration Capacity Analysis oudated values would have led to Interconnection Requests Failing the Initial Review, what cost was associated with the updates to the ICA necessitated by evaluating the outdated values? | Actual Costs Associated with processing of interconnection applications (as discussed in proposal 8s).
SDGE | 92040 | 337161 | NEM | NEMA | APPROVED | SOLAR PV | 104.068 | NO | 1 | 6 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 5 | 218 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92059 | 339132 | NEM | NEM-ST | APPROVED | SOLAR PV & BATTERY STORAGE | 792.169 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | INTERCONNECTION COMPLETE | N/A | 0 | 72 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92064 | 341473 | NEM | NEM-ST | APPROVED | SOLAR PV | 38.25 | NO | 1 | 4 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | INTERCONNECTION COMPLETE | N/A | 8 | 1239 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 342197 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 69.7 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 936 | N/A | N/A | N/A | 5 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92131 | 357122 | NEM | NEMA | APPROVED | SOLAR PV | 1548.752 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 3 | 305 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92130 | 358760 | NEM | NEM-ST NGOM | APPROVED | SOLAR PV & BATTERY STORAGE | 300 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 329 | N/A | N/A | N/A | 3 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92108 | 364445 | NON-NEM | RULE 21 AES INADVERTANT EXPORT | APPROVED | BATTERY STORAGE | 210 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 9 | 1004 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 759
SDGE | 92127 | 366395 | NEM | NEM-ST | APPROVED | SOLAR PV | 305 | NO | 1 | 9 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | INTERCONNECTION COMPLETE | N/A | 0 | 204 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92069 | 394078 | NEM | NEM-ST NGOM | APPROVED | SOLAR PV & BATTERY STORAGE | 491 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | INTERCONNECTION COMPLETE | N/A | 7 | 24 | N/A | N/A | N/A | 1 | 3 | N/A | N/A | N/A | N/A | N/A
SDGE | 92081 | 405091 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 25 | NO | 1 | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | INTERCONNECTION COMPLETE | N/A | 1 | 313 | N/A | N/A | N/A | 1 | 6 | N/A | N/A | N/A | N/A | N/A
SDGE | 92040 | 407008 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 30.741 | NO | 1 | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 650 | N/A | N/A | N/A | 6 | 6 | N/A | N/A | N/A | N/A | N/A
SDGE | 92040 | 412835 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33.442 | NO | 1 | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | INTERCONNECTION COMPLETE | N/A | 9 | 227 | N/A | N/A | N/A | 6 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92040 | 412906 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 34.425 | NO | 1 | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | INTERCONNECTION COMPLETE | N/A | 9 | 227 | N/A | N/A | N/A | 6 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92014 | 414117 | NEM | NEM-ST | APPROVED | SOLAR PV | 45.6 | NO | 1 | 5 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 0 | 806 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92081 | 415109 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 35.76 | NO | 1 | 3 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | INTERCONNECTION COMPLETE | N/A | 4 | 145 | N/A | N/A | N/A | 3 | 8 | N/A | N/A | N/A | N/A | N/A
SDGE | 92081 | 416495 | NEM | NEMA | APPROVED | SOLAR PV | 188 | NO | 1 | 8 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 164 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92019 | 416875 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 45.245 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 3 | 245 | N/A | N/A | N/A | 19 | 5 | N/A | N/A | N/A | N/A | N/A
SDGE | 92058 | 422976 | NEM | NEMA | APPROVED | SOLAR PV | 51.265 | NO | 1 | 10 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | INTERCONNECTION COMPLETE | N/A | 14 | 290 | N/A | N/A | N/A | 15 | 5 | N/A | N/A | N/A | N/A | N/A
SDGE | 92127 | 424406 | NEM | NEMA | APPROVED | SOLAR PV | 738 | NO | 1 | 5 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | INTERCONNECTION COMPLETE | N/A | 9 | 231 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92105 | 426421 | NEM | NEM-ST | APPROVED | SOLAR PV | 200.924 | NO | 1 | 58 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | INTERCONNECTION COMPLETE | N/A | 8 | 679 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92069 | 433221 | NEM | NEM-ST | APPROVED | SOLAR PV & BATTERY STORAGE | 449 | NO | 1 | 1 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | INTERCONNECTION COMPLETE | N/A | 0 | 733 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92104 | 436162 | NEM | NEM-ST | APPROVED | SOLAR PV | 237.281 | NO | 1 | 7 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 0 | 113 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92154 | 438596 | NEM | NEM-ST | APPROVED | SOLAR PV | 988.82 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 0 | 669 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92025 | 439513 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 96.359 | NO | 1 | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 2 | 232 | N/A | N/A | N/A | 11 | 8 | N/A | N/A | N/A | N/A | N/A
SDGE | 92084 | 443935 | NEM | NEM-ST | APPROVED | SOLAR PV | 39.574 | NO | 1 | 48 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | INTERCONNECTION COMPLETE | N/A | 0 | 600 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92083 | 443953 | NEM | NEM-ST | APPROVED | SOLAR PV | 65.557 | NO | 1 | 59 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 0 | 688 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92114 | 447263 | NEM | NEMA | APPROVED | SOLAR PV | 43.826 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 591 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92114 | 447481 | NEM | NEMA | APPROVED | SOLAR PV | 43.826 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | INTERCONNECTION COMPLETE | N/A | 0 | 590 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453406 | NEM | NEM-ST | APPROVED | SOLAR PV | 126.614 | NO | 1 | 68 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 1 | 625 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453460 | NEM | NEM-ST | APPROVED | SOLAR PV | 43.198 | NO | 1 | 68 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 1 | 625 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453507 | NEM | NEM-ST | APPROVED | SOLAR PV | 53.625 | NO | 1 | 68 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | INTERCONNECTION COMPLETE | N/A | 0 | 665 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453611 | NEM | NEM-ST | APPROVED | SOLAR PV | 48.784 | NO | 1 | 68 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 0 | 680 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453620 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453713 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 32 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453769 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 32 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453792 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453827 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453828 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453855 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453862 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453881 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92008 | 453883 | NEM | NEM-ST | APPROVED | SOLAR PV | 125.869 | NO | 1 | 68 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | INTERCONNECTION COMPLETE | N/A | 0 | 688 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453900 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453903 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453915 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 92026 | 453946 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 2 | 64 | N/A | N/A | N/A | 4 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 455278 | NEM | NEM-ST | APPROVED | SOLAR PV | 93.743 | NO | 1 | 95 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 0 | 631 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92009 | 456341 | NEM | NEM-ST | APPROVED | SOLAR PV | 83.746 | NO | 1 | 95 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 0 | 640 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92036 | 458544 | NEM | NEMA | APPROVED | SOLAR PV | 34 | NO | 1 | 6 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | INTERCONNECTION COMPLETE | N/A | 0 | 389 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 458720 | NEM | NBT | APPROVED | SOLAR PV | 45.988 | NO | 1 | 9 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | INTERCONNECTION COMPLETE | N/A | 1 | 358 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92677 | 458813 | NON-NEM | RULE 21 AES INADVERTANT EXPORT | APPROVED | BATTERY STORAGE | 10 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | INTERCONNECTION COMPLETE | N/A | 0 | 476 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 459135 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 10 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 0 | 641 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 459566 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 2567.2 | NO | 1 | 1 | 8 | N/A | 18 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-02 | INTERCONNECTION COMPLETE | N/A | 3 | 591 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91950 | 459590 | NON-NEM | RULE 21 NON EXPORT | APPROVED | INTERNAL COMBUSTION ENGINE | 350 | NO | 1 | 14 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | INTERCONNECTION COMPLETE | N/A | 0 | 649 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 759
SDGE | 92020 | 462948 | NEM | NEMA | APPROVED | SOLAR PV | 63.452 | NO | 1 | 9 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 10 | 147 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92118 | 466696 | NEM | NBT | APPROVED | SOLAR PV | 584.508 | NO | 1 | 2 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | INTERCONNECTION COMPLETE | N/A | 0 | 487 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92118 | 466701 | NEM | NBT | APPROVED | SOLAR PV | 81.514 | NO | 1 | 10 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 14 | 329 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92108 | 466723 | NEM | NBT | APPROVED | SOLAR PV | 65.85 | NO | 1 | 8 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | INTERCONNECTION COMPLETE | N/A | 0 | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92108 | 466730 | NEM | NBT | APPROVED | SOLAR PV | 43.33 | NO | 1 | 8 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | INTERCONNECTION COMPLETE | N/A | 0 | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92123 | 467643 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 39.129 | NO | 1 | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | INTERCONNECTION COMPLETE | N/A | 1 | 252 | N/A | N/A | N/A | 17 | 6 | N/A | N/A | N/A | N/A | N/A
SDGE | 92115 | 467918 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 30.617 | NO | 1 | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 3 | 152 | N/A | N/A | N/A | 4 | 4 | N/A | N/A | N/A | N/A | N/A
SDGE | 92024 | 467943 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 70 | NO | 1 | 2 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-30 | INTERCONNECTION COMPLETE | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 470859 | NEM | NEM-ST | APPROVED | BATTERY STORAGE | 530 | NO | 1 | 4 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 1 | 279 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91978 | 471298 | NEM | NEM-ST | APPROVED | SOLAR PV | 94.685 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 377 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92123 | 471375 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 113 | NO | 1 | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 1 | 105 | N/A | N/A | N/A | 15 | 8 | N/A | N/A | N/A | N/A | N/A
SDGE | 92084 | 478747 | NEM | NBT | APPROVED | SOLAR PV | 565.287 | NO | 1 | 5 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | INTERCONNECTION COMPLETE | N/A | 5 | 350 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91941 | 478818 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92118 | 478820 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92127 | 478825 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.53 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 478922 | NEM | NEM-ST | APPROVED | SOLAR PV | 112 | NO | 1 | 6 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | INTERCONNECTION COMPLETE | N/A | 8 | 216 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92009 | 479181 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 479188 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | 5 | 9 | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 479195 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 221.328 | NO | 1 | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 3 | 165 | N/A | N/A | N/A | 3 | 5 | N/A | N/A | N/A | N/A | N/A
SDGE | 91913 | 479260 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92109 | 479737 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 78 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92154 | 479803 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 105 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 479991 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 78 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 480110 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | INTERCONNECTION COMPLETE | N/A | 0 | 98 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92024 | 480612 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 8 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92004 | 480969 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 481516 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92126 | 483030 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92057 | 483031 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 5 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92025 | 483309 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 82 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91941 | 483312 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91950 | 483367 | NEM | NBT | APPROVED | SOLAR PV | 34.138 | NO | 1 | 8 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 1 | 138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91950 | 483475 | NEM | NBT-V | APPROVED | SOLAR PV | 48.52 | NO | 1 | 3 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 9 | 158 | N/A | N/A | N/A | 16 | 7 | N/A | N/A | N/A | N/A | N/A
SDGE | 91911 | 483627 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 108 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 483694 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 483757 | NEM | NBT-V | APPROVED | SOLAR PV | 82.613 | NO | 1 | 2 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | INTERCONNECTION COMPLETE | N/A | 9 | 224 | N/A | N/A | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A
SDGE | 91910 | 483795 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 0 | 88 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92010 | 483973 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 7 | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 484625 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92054 | 484626 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92129 | 484659 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91942 | 484839 | NEM | NBT | APPROVED | SOLAR PV | 190.195 | NO | 1 | 6 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 1 | 260 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92105 | 485019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 12 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | INTERCONNECTION COMPLETE | N/A | 0 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 485174 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 485720 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 0 | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92129 | 486169 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | INTERCONNECTION COMPLETE | N/A | 0 | 87 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91902 | 486594 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 104 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 486781 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | INTERCONNECTION COMPLETE | N/A | 0 | 88 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92071 | 487299 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 79 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 487300 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 81 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 487304 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.42 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 487412 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 8 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92027 | 487465 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | INTERCONNECTION COMPLETE | N/A | 8 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 487629 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 487633 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 487706 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | INTERCONNECTION COMPLETE | N/A | 0 | 124 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92029 | 487856 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 4 | 33 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 487944 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 11.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 6 | 109 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 488037 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | INTERCONNECTION COMPLETE | N/A | 0 | 42 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 488579 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 7.1 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92082 | 489448 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92120 | 489451 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 491678 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 79 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91913 | 492351 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 492387 | NEM | NEMA | APPROVED | SOLAR PV | 160 | NO | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 2 | 241 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92024 | 492529 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 38 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92673 | 493740 | NEM | NBT | APPROVED | PV | 45.67 | NO | 1 | 10 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | INTERCONNECTION COMPLETE | N/A | 15 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92673 | 493757 | NEM | NBT | APPROVED | PV | 50 | NO | 1 | 11 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | INTERCONNECTION COMPLETE | N/A | 1 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92120 | 494050 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | INTERCONNECTION COMPLETE | N/A | 0 | 125 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 494182 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 79 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 494186 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 67 | NO | 1 | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | INTERCONNECTION COMPLETE | N/A | 1 | 127 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91915 | 494730 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92024 | 494853 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | INTERCONNECTION COMPLETE | N/A | 4 | 56 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92694 | 494874 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 495144 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 3 | 42 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92069 | 495322 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 4 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91941 | 495500 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.64 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 495516 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | INTERCONNECTION COMPLETE | N/A | 0 | 42 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92114 | 495520 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 495525 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | INTERCONNECTION COMPLETE | N/A | 0 | 43 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 495526 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92040 | 495527 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | INTERCONNECTION COMPLETE | N/A | 5 | 36 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 495530 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.73 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92028 | 495551 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 495556 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.8 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 495619 | NEM | NBT | APPROVED | SOLAR PV | 70.551 | NO | 1 | 7 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-14 | INTERCONNECTION COMPLETE | N/A | 5 | 186 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92154 | 495658 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.49 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92026 | 495892 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 2 | 38 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 495902 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 80 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92040 | 496083 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.4 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 3 | 38 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92078 | 496093 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92131 | 496098 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | INTERCONNECTION COMPLETE | N/A | 0 | 35 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92119 | 496111 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.07 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 9 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92114 | 496275 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 496839 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-17 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92173 | 497279 | NEM | NBT | APPROVED | SOLAR PV | 34.51 | NO | 1 | 6 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | INTERCONNECTION COMPLETE | N/A | 0 | 97 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92024 | 497366 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 1 | 66 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92102 | 497486 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.8 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 3 | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92029 | 497594 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92130 | 498518 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 498658 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.68 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 0 | 28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92624 | 498805 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 498906 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 3 | 34 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92131 | 498907 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.68 | NO | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 11 | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92024 | 498929 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92118 | 499151 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.12 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 499395 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.3 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92653 | 499543 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.1 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 500807 | NEM | NEM-ST | APPROVED | SOLAR PV | 41 | NO | 1 | 8 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 0 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 91913 | 501660 | NEM | NEM-ST | APPROVED | SOLAR PV | 208.3 | NO | 1 | 5 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 0 | 132 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92029 | 502371 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.3 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 2 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 502381 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 12 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 3 | 91 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 502577 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 502804 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 11.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | INTERCONNECTION COMPLETE | N/A | 0 | 57 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92075 | 502980 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 16 | NO | 1 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 1 | 62 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92029 | 502993 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 8 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 6 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91935 | 503006 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 503014 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.85 | NO | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | INTERCONNECTION COMPLETE | N/A | 1 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 503017 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92128 | 503098 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 4 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91945 | 503550 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | INTERCONNECTION COMPLETE | N/A | 0 | 54 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 503561 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.35 | NO | 1 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | INTERCONNECTION COMPLETE | N/A | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92057 | 503749 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | INTERCONNECTION COMPLETE | N/A | 0 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 503771 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92025 | 504194 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 13 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92084 | 504345 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 31 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 4 | 21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 504608 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | INTERCONNECTION COMPLETE | N/A | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92120 | 504609 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92064 | 505424 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 1 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | INTERCONNECTION COMPLETE | N/A | 2 | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92111 | 505438 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | INTERCONNECTION COMPLETE | N/A | 5 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92129 | 505444 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.74 | NO | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | INTERCONNECTION COMPLETE | N/A | 0 | 89 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 505449 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.1 | NO | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-22 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 505557 | NEM | NBT | APPROVED | PV | 72.94 | NO | 1 | 13 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 4 | 32 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92128 | 505689 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.1 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 506039 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92067 | 506265 | NON-NEM | RULE 21 AES EXPORT | APPROVED | BATTERY STORAGE | 20 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91913 | 506391 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.56 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 6 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91902 | 506533 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.7 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 506857 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | INTERCONNECTION COMPLETE | N/A | 0 | 82 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91910 | 507756 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92071 | 507897 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92673 | 508485 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92020 | 508871 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 7.8 | NO | 1 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 6 | 76 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 509399 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18.46 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 2 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92117 | 509433 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11.78 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 6 | 26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92081 | 509494 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 8 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92130 | 509595 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 10 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | INTERCONNECTION COMPLETE | N/A | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92025 | 509646 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.85 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 12 | 41 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 509764 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.03 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 0 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92037 | 509777 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.93 | NO | 1 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | INTERCONNECTION COMPLETE | N/A | 0 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92124 | 510556 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.42 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | INTERCONNECTION COMPLETE | N/A | 6 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92008 | 510566 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.96 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91977 | 510737 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 7 | 18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92103 | 510751 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 0 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92009 | 510762 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 8.27 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 0 | 29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92067 | 511209 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 62 | NO | 1 | 10 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 1 | 44 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SDGE | 92069 | 511315 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | INTERCONNECTION COMPLETE | N/A | 3 | 46 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92065 | 511499 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.16 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | INTERCONNECTION COMPLETE | N/A | 0 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92021 | 511762 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.4 | NO | 1 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | INTERCONNECTION COMPLETE | N/A | 7 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91962 | 511990 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.56 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92123 | 513244 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.85 | NO | 1 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 0 | 17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92102 | 513250 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91950 | 513501 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | INTERCONNECTION COMPLETE | N/A | 0 | 31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91901 | 513639 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 1 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-03 | INTERCONNECTION COMPLETE | N/A | 7 | 25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 91902 | 513934 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.19 | NO | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | INTERCONNECTION COMPLETE | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92028 | 514046 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.48 | NO | 1 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | INTERCONNECTION COMPLETE | N/A | 5 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389
SDGE | 92019 | 516093 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.74 | NO | 1 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | INTERCONNECTION COMPLETE | N/A | 0 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 389

## APPROVED_ALL TIMELINES
SDG&E's Rule 21 Processing Timelines | [7 empty] | Application Review: | [5 empty] | Fast Track Initial Review (IR): |  |  | Fast Track Initial Review (IR) Cost Report: |  | Fast Track Supplemental Review (SR): |  |  | Supplemental Review (SR) Cost Report: |  | Electrical Independence Test (EIT): |  |  | Scoping Meeting and Study Agreement: |  |  | System Impact Study (SIS): |  |  | Facilities Study: | Draft Interconnection Agreement (IA): |  |  |  | Material Modification (MM): |  |  | Net Generating Output Meter (NGOM): | [5 empty] | Minor Upgrades Construction: | [9 empty] | Permission to Operate (PTO):
Project Specifics | [7 empty] | ● 10 Business Days for initial application review [E.5.a.] (15 Business Days if Cost Envelope Option is selected [E.5.a.]) | [5 empty] | 15 Business Days [F.2.a.] |  |  | 15 Business Days [F.2.a. & F.2.b.] |  | 20 Business Days [F.2.c.i.] |  |  | 15 Business Days [F.2.c.iii.] |  | 20 Business Days [F.3.a.] |  |  | 5 Business Days [F.3.b.i.] |  |  | 60 Business Days [F.3.b.ii.] |  |  | F.3.b.vii |  |  |  |  | 10 Business Days [F.3.b.v] (20 Business Days if Cost Envelope Option is selected [F.3.b.v]) | [8 empty] | 60 Business Days (estimated timeline) to Design / 60 Business Days to Construct | [9 empty] | 5 Business Days (Goal) / 30 Days from Complete Application
[34 empty] | ● 15 Business Days for Fast Track [F.2.a] | [6 empty] | ● 20 Business Days to Design (Invoice)
[34 empty] | ● 30 Calendar Days for Detailed Study [F.3.e.i.] | [6 empty] | ● 20 Business Days to Install
Project ID | Zip Code | NEM or Non-NEM | PROJECT TYPE (REQUEST TYPE) | Project Status (Current Phase) | TECHNOLOGY TYPE | Size (kW - Net Nameplate Rating) | Cost Envelope Requested? | First Interconnection Request Received Date | Interconnection Request Submission Acknowledged Date | Business Days to Acknowledge Interconnection Request Submission | Last Date Application Submitted/RCA | Application Deemed Complete Date | Business Days to Deem Complete | Start Date of IR by DP/CG | Date IR Results Issued to Customer | Business Days to Issue IR Results | Date IR Cost Report Issued to Customer | Business Days to Issue IR Cost Report | Start Date of SR | Date SR Results Issued to Customer | Business Days to Issue SR Results | Date SR Cost Report Issued to Customer | Business Days to Issue SR Cost Report | Start Date of EIT | Date EIT Results Issued to Customer | Business Days to Issue EIT Results | Date of Scoping Meeting | Date Study Agreement Issued | Business Days to Issue Study Agreement | Start Date of Interconnection SIS | Date Interconnection SIS Report Issued to Customer | Business Days to Issue SIS Results | Date Facilities Study Waived | Date Draft Generator IA Requested | Date Draft Generator IA Sent to Customer | Business Days to Send Draft IA for Fast Track | Detailed Study Only-Calendar Days to Send Draft IA | Date MM Request Received | Date of MM Results | Business Days to Issue MM Review Results | Date Initial Field Inspection Completed (Deemed Completed) | Date Costing Invoice Sent | Business Days to Send NGOM Invoice | Date Request Sent for NGOM Meter Set | Date NGOM Installed | Business Days to Install NGOM | Preliminary Design Start Date [Engineering Fee Paid] | Preliminary Design Issued to Customer Date [Design Costs Delivered] | Business Days to Issue Preliminary Design | Preliminary Design Approved by Customer Date [Customer Consents and Pays in Full] | Final Design Issued Date [Design sent to Construction Services] | Business Days to Issue Final Design | Total Design Business Days (Preliminary plus Final) | SDGE Construction Start Date | SDGE Construction Complete Date | Business Days to Construct | Date Last Customer Issue Resolved | Date of PTO | Number of Days from Last Issue Resolved to PTO Date | Calendar Days from Application Deemed Complete Date to PTO Date
337161 | 92040 | NEM | NEMA | APPROVED | SOLAR PV | 104.068 | NO | 2021-12-10 | 2021-12-10 | 1 | 2024-09-18 | 2024-09-25 | 6 | 2024-09-25 | 2024-09-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-26 | 2025-05-01 | 5 | 218
339132 | 92059 | NEM | NEM-ST | APPROVED | SOLAR PV & BATTERY STORAGE | 792.169 | NO | 2021-12-29 | 2021-12-29 | 1 | 2025-02-03 | 2025-02-03 | 1 | 2025-02-03 | 2025-02-03 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 0 | 72
341473 | 92064 | NEM | NEM-ST | APPROVED | SOLAR PV | 38.25 | NO | 2022-01-25 | 2022-01-25 | 1 | 2022-01-25 | 2022-01-28 | 4 | 2022-01-28 | 2022-02-09 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-20 | 8 | 1239
342197 | 92008 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 69.7 | NO | 2022-01-31 | 2022-01-31 | 1 | 2022-09-14 | 2022-09-14 | 1 | 2022-09-22 | 2022-09-22 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-14 | 2022-09-20 | 5 | 2025-03-31 | 2025-04-03 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-07 | 4 | 936
357122 | 92131 | NEM | NEMA | APPROVED | SOLAR PV | 1548.752 | NO | 2022-05-24 | 2022-05-24 | 1 | 2024-06-06 | 2024-06-06 | 1 | 2024-06-06 | 2024-06-06 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-07 | 3 | 305
358760 | 92130 | NEM | NEM-ST NGOM | APPROVED | SOLAR PV & BATTERY STORAGE | 300 | NO | 2022-06-25 | 2022-06-25 | 1 | 2024-05-10 | 2024-05-10 | 1 | 2024-05-10 | 2024-05-10 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-14 | 3 | 2025-03-31 | 2025-04-03 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-04 | 3 | 329
364445 | 92108 | NON-NEM | RULE 21 AES INADVERTANT EXPORT | APPROVED | BATTERY STORAGE | 210 | NO | 2022-07-13 | 2022-07-13 | 1 | 2022-07-13 | 2022-07-18 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2022-07-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-17 | 9 | 1004
366395 | 92127 | NEM | NEM-ST | APPROVED | SOLAR PV | 305 | NO | 2022-07-26 | 2022-07-26 | 1 | 2024-11-04 | 2024-11-14 | 9 | 2024-11-14 | 2024-11-19 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | 0 | 204
394078 | 92069 | NEM | NEM-ST NGOM | APPROVED | SOLAR PV & BATTERY STORAGE | 491 | NO | 2023-01-20 | 2023-01-20 | 1 | 2025-03-10 | 2025-03-10 | 1 | 2025-03-10 | 2025-03-10 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 1 | 2025-03-31 | 2025-04-02 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-03 | 7 | 24
405091 | 92081 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 25 | NO | 2023-03-02 | 2023-03-02 | 1 | 2024-08-08 | 2024-08-08 | 1 | 2024-08-08 | 2024-08-18 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 2025-06-09 | 2025-06-16 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-17 | 1 | 313
407008 | 92040 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 30.741 | NO | 2023-03-06 | 2023-03-06 | 1 | 2023-06-27 | 2023-06-27 | 1 | 2023-06-27 | 2023-07-07 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-08 | 6 | 2025-03-27 | 2025-04-03 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-07 | 4 | 650
412835 | 92040 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33.442 | NO | 2023-03-10 | 2023-03-10 | 1 | 2024-10-21 | 2024-10-21 | 1 | 2024-10-21 | 2024-11-01 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-28 | 6 | 2025-05-29 | 2025-06-03 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-06-05 | 9 | 227
412906 | 92040 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 34.425 | NO | 2023-03-10 | 2023-03-10 | 1 | 2024-10-21 | 2024-10-21 | 1 | 2024-10-21 | 2024-11-01 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-28 | 6 | 2025-05-29 | 2025-06-03 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-06-05 | 9 | 227
414117 | 92014 | NEM | NEM-ST | APPROVED | SOLAR PV | 45.6 | NO | 2023-03-10 | 2023-03-10 | 1 | 2023-03-10 | 2023-03-16 | 5 | 2023-03-16 | 2023-03-28 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 0 | 806
415109 | 92081 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 35.76 | NO | 2023-03-14 | 2023-03-14 | 1 | 2025-01-06 | 2025-01-08 | 3 | 2025-01-08 | 2025-01-16 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-08 | 3 | 2025-05-19 | 2025-05-29 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-06-02 | 4 | 145
416495 | 92081 | NEM | NEMA | APPROVED | SOLAR PV | 188 | NO | 2023-03-15 | 2023-03-15 | 1 | 2024-10-11 | 2024-10-22 | 8 | 2024-10-22 | 2024-10-22 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 164
416875 | 92019 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 45.245 | NO | 2023-03-16 | 2023-03-16 | 1 | 2024-08-05 | 2024-08-05 | 1 | 2024-08-05 | 2024-08-05 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-29 | 19 | 2025-03-31 | 2025-04-04 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-07 | 3 | 245
422976 | 92058 | NEM | NEMA | APPROVED | SOLAR PV | 51.265 | NO | 2023-03-27 | 2023-03-27 | 1 | 2024-06-11 | 2024-06-24 | 10 | 2024-06-24 | 2024-06-24 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-28 | 15 | 2025-03-28 | 2025-04-03 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-04-10 | 14 | 290
424406 | 92127 | NEM | NEMA | APPROVED | SOLAR PV | 738 | NO | 2023-03-23 | 2023-03-23 | 1 | 2024-09-19 | 2024-09-25 | 5 | 2024-09-25 | 2024-09-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-14 | 9 | 231
426421 | 92105 | NEM | NEM-ST | APPROVED | SOLAR PV | 200.924 | NO | 2023-03-24 | 2023-03-24 | 1 | 2023-03-24 | 2023-06-14 | 58 | 2023-06-14 | 2023-06-22 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-23 | 8 | 679
433221 | 92069 | NEM | NEM-ST | APPROVED | SOLAR PV & BATTERY STORAGE | 449 | NO | 2023-04-03 | 2023-04-03 | 1 | 2023-06-22 | 2023-06-22 | 1 | 2023-08-07 | 2023-08-24 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | 0 | 733
436162 | 92104 | NEM | NEM-ST | APPROVED | SOLAR PV | 237.281 | NO | 2023-04-01 | 2023-04-01 | 1 | 2025-02-10 | 2025-02-19 | 7 | 2025-02-19 | 2025-02-19 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | 0 | 113
438596 | 92154 | NEM | NEM-ST | APPROVED | SOLAR PV | 988.82 | NO | 2023-04-04 | 2023-04-04 | 1 | 2023-07-31 | 2023-07-31 | 1 | 2023-07-31 | 2023-07-31 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 0 | 669
439513 | 92025 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 96.359 | NO | 2023-04-04 | 2023-04-04 | 1 | 2024-10-10 | 2024-10-10 | 1 | 2024-10-10 | 2024-10-15 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-24 | 11 | 2025-05-16 | 2025-05-28 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-30 | 2 | 232
443935 | 92084 | NEM | NEM-ST | APPROVED | SOLAR PV | 39.574 | NO | 2023-04-10 | 2023-04-10 | 1 | 2023-07-09 | 2023-09-14 | 48 | 2023-09-14 | 2023-09-25 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | 0 | 600
443953 | 92083 | NEM | NEM-ST | APPROVED | SOLAR PV | 65.557 | NO | 2023-04-10 | 2023-04-10 | 1 | 2023-04-10 | 2023-07-02 | 59 | 2023-07-02 | 2023-07-17 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | 0 | 688
447263 | 92114 | NEM | NEMA | APPROVED | SOLAR PV | 43.826 | NO | 2023-04-10 | 2023-04-10 | 1 | 2023-09-18 | 2023-09-18 | 1 | 2023-09-18 | 2023-09-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 0 | 591
447481 | 92114 | NEM | NEMA | APPROVED | SOLAR PV | 43.826 | NO | 2023-04-11 | 2023-04-11 | 1 | 2023-09-18 | 2023-09-18 | 1 | 2023-09-18 | 2023-09-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 0 | 590
453406 | 92008 | NEM | NEM-ST | APPROVED | SOLAR PV | 126.614 | NO | 2023-04-13 | 2023-04-13 | 1 | 2023-04-13 | 2023-07-19 | 68 | 2023-07-19 | 2023-07-24 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-04 | 1 | 625
453460 | 92008 | NEM | NEM-ST | APPROVED | SOLAR PV | 43.198 | NO | 2023-04-13 | 2023-04-13 | 1 | 2023-04-13 | 2023-07-19 | 68 | 2023-07-19 | 2023-07-24 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-04 | 1 | 625
453507 | 92008 | NEM | NEM-ST | APPROVED | SOLAR PV | 53.625 | NO | 2023-04-13 | 2023-04-13 | 1 | 2023-04-13 | 2023-07-19 | 68 | 2023-07-19 | 2023-07-24 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | 0 | 665
453611 | 92008 | NEM | NEM-ST | APPROVED | SOLAR PV | 48.784 | NO | 2023-04-13 | 2023-04-13 | 1 | 2023-04-13 | 2023-07-19 | 68 | 2023-07-19 | 2023-07-20 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 0 | 680
453620 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453713 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 32 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453769 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 32 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453792 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453827 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453828 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453855 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453862 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453881 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453883 | 92008 | NEM | NEM-ST | APPROVED | SOLAR PV | 125.869 | NO | 2023-04-13 | 2023-04-13 | 1 | 2023-04-13 | 2023-07-19 | 68 | 2023-07-19 | 2023-07-20 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-06 | 2025-06-06 | 0 | 688
453900 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453903 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 31 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453915 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 29 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
453946 | 92026 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 33 | NO | 2023-04-13 | 2023-04-13 | 1 | 2025-03-26 | 2025-03-26 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-31 | 4 | 2025-05-16 | 2025-05-27 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-29 | 2 | 64
455278 | 91910 | NEM | NEM-ST | APPROVED | SOLAR PV | 93.743 | NO | 2023-04-14 | 2023-04-14 | 1 | 2023-04-14 | 2023-08-28 | 95 | 2023-08-28 | 2023-08-31 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | 0 | 631
456341 | 92009 | NEM | NEM-ST | APPROVED | SOLAR PV | 83.746 | NO | 2023-04-14 | 2023-04-14 | 1 | 2023-04-14 | 2023-08-28 | 95 | 2023-08-28 | 2023-08-31 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 0 | 640
458544 | 92036 | NEM | NEMA | APPROVED | SOLAR PV | 34 | NO | 2023-07-25 | 2023-07-25 | 1 | 2024-04-22 | 2024-04-29 | 6 | 2024-04-29 | 2024-05-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-23 | 0 | 389
458720 | 91910 | NEM | NBT | APPROVED | SOLAR PV | 45.988 | NO | 2023-07-31 | 2023-07-31 | 1 | 2024-05-02 | 2024-05-14 | 9 | 2024-05-14 | 2024-05-21 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-07 | 1 | 358
458813 | 92677 | NON-NEM | RULE 21 AES INADVERTANT EXPORT | APPROVED | BATTERY STORAGE | 10 | NO | 2023-07-27 | 2023-07-27 | 1 | 2024-01-29 | 2024-01-29 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | 0 | 476
459135 | 92064 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 10 | NO | 2023-08-17 | 2023-08-17 | 1 | 2023-08-17 | 2023-08-25 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | 0 | 641
459566 | 92008 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 2567.2 | NO | 2023-08-25 | 2023-08-25 | 1 | 2023-10-20 | 2023-10-20 | 1 | 2023-10-20 | 2023-10-31 | 8 | N/A | N/A | 2023-11-20 | 2023-12-15 | 18 | 2023-12-15 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-06-02 | 3 | 591
459590 | 91950 | NON-NEM | RULE 21 NON EXPORT | APPROVED | INTERNAL COMBUSTION ENGINE | 350 | NO | 2023-08-18 | 2023-08-18 | 1 | 2023-08-18 | 2023-09-07 | 14 | 2023-08-18 | 2023-08-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-17 | 0 | 649
462948 | 92020 | NEM | NEMA | APPROVED | SOLAR PV | 63.452 | NO | 2023-10-18 | 2023-10-18 | 1 | 2024-10-29 | 2024-11-08 | 9 | 2024-11-08 | 2024-11-08 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-04 | 10 | 147
466696 | 92118 | NEM | NBT | APPROVED | SOLAR PV | 584.508 | NO | 2023-12-15 | 2023-12-15 | 1 | 2023-12-15 | 2023-12-18 | 2 | 2023-12-18 | 2023-12-28 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 0 | 487
466701 | 92118 | NEM | NBT | APPROVED | SOLAR PV | 81.514 | NO | 2023-12-15 | 2023-12-15 | 1 | 2024-04-25 | 2024-05-08 | 10 | 2024-04-30 | 2024-05-02 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-04-02 | 14 | 329
466723 | 92108 | NEM | NBT | APPROVED | SOLAR PV | 65.85 | NO | 2023-12-15 | 2023-12-15 | 1 | 2025-01-16 | 2025-01-28 | 8 | 2025-01-28 | 2025-01-30 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | 0 | 87
466730 | 92108 | NEM | NBT | APPROVED | SOLAR PV | 43.33 | NO | 2023-12-15 | 2023-12-15 | 1 | 2025-01-16 | 2025-01-28 | 8 | 2025-01-28 | 2025-01-30 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-25 | 2025-04-25 | 0 | 87
467643 | 92123 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 39.129 | NO | 2023-12-31 | 2023-12-31 | 1 | 2024-08-15 | 2024-08-15 | 1 | 2024-08-15 | 2024-08-27 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-09-09 | 17 | 2025-04-16 | 2025-04-23 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-24 | 1 | 252
467918 | 92115 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 30.617 | NO | 2023-12-31 | 2023-12-31 | 1 | 2024-11-13 | 2024-11-13 | 1 | 2024-11-13 | 2024-11-20 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-18 | 4 | 2025-04-08 | 2025-04-11 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-14 | 3 | 152
467943 | 92024 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 70 | NO | 2023-12-29 | 2023-12-29 | 1 | 2025-06-26 | 2025-06-27 | 2 | 2025-06-27 | 2025-06-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-27 | 2025-06-30 | 3 | 3
470859 | 91910 | NEM | NEM-ST | APPROVED | BATTERY STORAGE | 530 | NO | 2024-02-07 | 2024-02-07 | 1 | 2024-08-20 | 2024-08-24 | 4 | 2024-03-11 | 2024-03-21 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-30 | 1 | 279
471298 | 91978 | NEM | NEM-ST | APPROVED | SOLAR PV | 94.685 | NO | 2024-02-13 | 2024-02-13 | 1 | 2024-04-05 | 2024-04-05 | 1 | 2024-04-05 | 2024-04-05 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 0 | 377
471375 | 92123 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 113 | NO | 2024-02-12 | 2024-02-12 | 1 | 2025-02-14 | 2025-02-14 | 1 | 2025-02-14 | 2025-02-28 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-03-07 | 15 | 2025-05-19 | 2025-05-29 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-30 | 1 | 105
478747 | 92084 | NEM | NBT | APPROVED | SOLAR PV | 565.287 | NO | 2024-05-16 | 2024-05-16 | 1 | 2024-05-16 | 2024-05-22 | 5 | 2024-05-22 | 2024-05-29 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-07 | 5 | 350
478818 | 91941 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.1 | NO | 2024-05-21 | 2024-05-21 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
478820 | 92118 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 2024-05-20 | 2024-05-20 | 1 | 2025-04-17 | 2025-04-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 0 | 0
478825 | 92127 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.53 | NO | 2024-05-17 | 2024-05-17 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
478922 | 92019 | NEM | NEM-ST | APPROVED | SOLAR PV | 112 | NO | 2024-08-06 | 2024-08-06 | 1 | 2024-09-11 | 2024-09-18 | 6 | 2024-09-18 | 2024-10-08 | 15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-22 | 8 | 216
479181 | 92009 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 2024-06-05 | 2024-06-05 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
479188 | 92064 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-05-22 | 2024-05-22 | 1 | 2025-04-04 | 2025-04-04 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 0
479195 | 91901 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 221.328 | NO | 2024-08-19 | 2024-08-19 | 1 | 2024-11-07 | 2024-11-07 | 1 | 2024-11-07 | 2024-11-11 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-11 | 3 | 2025-04-14 | 2025-04-18 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-21 | 3 | 165
479260 | 91913 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 2024-05-23 | 2024-05-23 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
479737 | 92109 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 2024-05-30 | 2024-05-30 | 1 | 2025-01-16 | 2025-01-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 78
479803 | 92154 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 2024-05-31 | 2024-05-31 | 1 | 2025-01-16 | 2025-01-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 0 | 105
479991 | 91910 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-06-04 | 2024-06-04 | 1 | 2025-01-16 | 2025-01-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 78
480110 | 92019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-06-04 | 2024-06-04 | 1 | 2025-01-16 | 2025-01-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | 0 | 98
480612 | 92024 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4 | NO | 2024-06-12 | 2024-06-12 | 1 | 2025-03-25 | 2025-03-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-02 | 8 | 8
480969 | 92004 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-06-18 | 2024-06-18 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
481516 | 92117 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 2024-06-24 | 2024-06-24 | 1 | 2025-04-02 | 2025-04-02 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | 0 | 0
483030 | 92126 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 2024-07-14 | 2024-07-14 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
483031 | 92057 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2024-07-15 | 2024-07-15 | 1 | 2025-05-07 | 2025-05-16 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-16 | 5 | 31
483309 | 92025 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.1 | NO | 2024-07-17 | 2024-07-17 | 1 | 2025-01-15 | 2025-01-15 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 82
483312 | 91941 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2024-07-17 | 2024-07-17 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 18
483367 | 91950 | NEM | NBT | APPROVED | SOLAR PV | 34.138 | NO | 2024-08-08 | 2024-08-08 | 1 | 2024-11-06 | 2024-11-15 | 8 | 2024-11-15 | 2024-11-25 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-02 | 1 | 138
483475 | 91950 | NEM | NBT-V | APPROVED | SOLAR PV | 48.52 | NO | 2024-12-19 | 2024-12-19 | 1 | 2024-12-19 | 2024-12-23 | 3 | 2025-01-03 | 2025-01-14 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-01-14 | 16 | 2025-05-21 | 2025-05-30 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-05-30 | 9 | 158
483627 | 91911 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-07-22 | 2024-07-22 | 1 | 2025-01-13 | 2025-01-13 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 0 | 108
483694 | 92037 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 2024-07-23 | 2024-07-23 | 1 | 2025-05-09 | 2025-05-16 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-16 | 0 | 0
483757 | 92009 | NEM | NBT-V | APPROVED | SOLAR PV | 82.613 | NO | 2024-07-23 | 2024-07-23 | 1 | 2024-08-21 | 2024-08-22 | 2 | 2024-10-24 | 2024-11-04 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-28 | 3 | 2025-03-27 | 2025-03-31 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-03 | 9 | 224
483795 | 91910 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 2024-07-24 | 2024-07-24 | 1 | 2025-01-16 | 2025-01-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | 0 | 88
483973 | 92010 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 2024-07-25 | 2024-07-25 | 1 | 2025-01-15 | 2025-01-15 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-14 | 7 | 89
484625 | 92026 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 2024-08-01 | 2024-08-01 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
484626 | 92054 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-08-01 | 2024-08-01 | 1 | 2025-04-28 | 2025-05-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 0 | 0
484659 | 92129 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 2024-08-01 | 2024-08-01 | 1 | 2025-02-15 | 2025-02-15 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 48
484839 | 91942 | NEM | NBT | APPROVED | SOLAR PV | 190.195 | NO | 2024-08-15 | 2024-08-15 | 1 | 2024-09-18 | 2024-09-25 | 6 | 2024-10-02 | 2024-10-02 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-12 | 1 | 260
485019 | 92105 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 12 | NO | 2024-08-09 | 2024-08-09 | 1 | 2025-04-29 | 2025-05-09 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-23 | 0 | 45
485174 | 92021 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 2024-08-07 | 2024-08-07 | 1 | 2025-04-21 | 2025-04-21 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 0 | 0
485720 | 92009 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 2024-08-13 | 2024-08-13 | 1 | 2025-04-23 | 2025-05-01 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 0 | 28
486169 | 92129 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 2024-08-16 | 2024-08-16 | 1 | 2025-03-13 | 2025-03-18 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-13 | 0 | 87
486594 | 91902 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2024-08-20 | 2024-08-20 | 1 | 2025-01-14 | 2025-01-14 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | 0 | 104
486781 | 92084 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.1 | NO | 2024-08-22 | 2024-08-22 | 1 | 2025-01-16 | 2025-01-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | 0 | 88
487299 | 92071 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 2024-08-27 | 2024-08-27 | 1 | 2025-01-13 | 2025-01-15 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 79
487300 | 92019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-08-27 | 2024-08-27 | 1 | 2025-01-13 | 2025-01-13 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-04 | 3 | 81
487304 | 92021 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.42 | NO | 2024-08-27 | 2024-08-27 | 1 | 2025-04-21 | 2025-04-28 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | 0 | 0
487412 | 92019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 2024-08-27 | 2024-08-27 | 1 | 2025-03-25 | 2025-03-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-02 | 8 | 8
487465 | 92027 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.1 | NO | 2024-08-28 | 2024-08-28 | 1 | 2025-03-25 | 2025-03-25 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-04-02 | 8 | 8
487629 | 91901 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 2024-08-29 | 2024-08-29 | 1 | 2025-02-18 | 2025-02-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-04 | 3 | 45
487633 | 91910 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2024-08-29 | 2024-08-29 | 1 | 2025-03-25 | 2025-04-07 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
487706 | 92021 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 2024-08-30 | 2024-08-30 | 1 | 2025-01-15 | 2025-01-15 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | 0 | 124
487856 | 92029 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 2024-09-02 | 2024-09-02 | 1 | 2025-04-28 | 2025-05-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-06-03 | 4 | 33
487944 | 91935 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 11.5 | NO | 2024-09-04 | 2024-09-04 | 1 | 2025-02-27 | 2025-02-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-16 | 6 | 109
488037 | 92065 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 2024-09-04 | 2024-09-04 | 1 | 2025-03-10 | 2025-03-19 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 0 | 42
488579 | 92019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 7.1 | NO | 2024-09-09 | 2024-09-09 | 1 | 2025-03-27 | 2025-04-07 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
489448 | 92082 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.5 | NO | 2024-09-18 | 2024-09-18 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
489451 | 92120 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.2 | NO | 2024-09-18 | 2024-09-18 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | 0 | 21
491678 | 92117 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2 | NO | 2024-10-07 | 2024-10-07 | 1 | 2025-01-15 | 2025-01-15 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 79
492351 | 91913 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.5 | NO | 2024-10-14 | 2024-10-14 | 1 | 2025-06-16 | 2025-06-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | 0 | 0
492387 | 92064 | NEM | NEMA | APPROVED | SOLAR PV | 160 | NO | 2024-10-14 | 2024-10-14 | 1 | 2024-10-14 | 2024-10-14 | 1 | 2024-10-14 | 2024-10-14 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-12 | 2 | 241
492529 | 92024 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 2024-10-15 | 2024-10-15 | 1 | 2025-02-19 | 2025-02-25 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-04 | 3 | 38
493740 | 92673 | NEM | NBT | APPROVED | PV | 45.67 | NO | 2024-11-05 | 2024-11-05 | 1 | 2025-03-06 | 2025-03-19 | 10 | 2025-03-19 | 2025-04-02 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-18 | 15 | 30
493757 | 92673 | NEM | NBT | APPROVED | PV | 50 | NO | 2024-11-05 | 2024-11-05 | 1 | 2025-03-05 | 2025-03-19 | 11 | 2025-03-19 | 2025-03-21 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-07 | 1 | 49
494050 | 92120 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2024-10-29 | 2024-10-29 | 1 | 2025-01-23 | 2025-01-23 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-05-28 | 0 | 125
494182 | 92026 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-10-30 | 2024-10-30 | 1 | 2025-01-15 | 2025-01-15 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 79
494186 | 92008 | NEM | NEM-ST-V | APPROVED | SOLAR PV | 67 | NO | 2024-11-06 | 2024-11-06 | 1 | 2025-01-23 | 2025-01-23 | 1 | 2025-01-23 | 2025-01-29 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-29 | 5 | 2025-05-16 | 2025-05-29 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-30 | 1 | 127
494730 | 91915 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2 | NO | 2024-11-05 | 2024-11-05 | 1 | 2025-04-18 | 2025-04-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-21 | 3 | 3
494853 | 92024 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.3 | NO | 2024-11-05 | 2024-11-05 | 1 | 2025-03-14 | 2025-03-14 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-09 | 4 | 56
494874 | 92694 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 2024-11-06 | 2024-11-06 | 1 | 2025-05-07 | 2025-05-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-08 | 1 | 1
495144 | 92065 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-11-07 | 2024-11-07 | 1 | 2025-02-16 | 2025-02-21 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-04 | 3 | 42
495322 | 92069 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 2024-11-11 | 2024-11-11 | 1 | 2025-05-30 | 2025-05-30 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-06-03 | 4 | 4
495500 | 91941 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.64 | NO | 2024-11-11 | 2024-11-11 | 1 | 2025-04-21 | 2025-04-21 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 0 | 0
495516 | 92065 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-03-26 | 2025-04-07 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-19 | 0 | 42
495520 | 92114 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-04-04 | 2025-04-07 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
495525 | 92084 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.6 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-05-01 | 2025-05-01 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-13 | 0 | 43
495526 | 92117 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
495527 | 92040 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-03-25 | 2025-04-07 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-13 | 5 | 36
495530 | 92026 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.73 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-03-05 | 2025-03-18 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 0 | 34
495551 | 92028 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
495556 | 92021 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.8 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-04-08 | 2025-04-17 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 0 | 0
495619 | 92009 | NEM | NBT | APPROVED | SOLAR PV | 70.551 | NO | 2024-11-20 | 2024-11-20 | 1 | 2024-12-02 | 2024-12-10 | 7 | 2024-12-10 | 2024-12-26 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-14 | 5 | 186
495658 | 92154 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.49 | NO | 2024-11-12 | 2024-11-12 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
495892 | 92026 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-11-13 | 2024-11-13 | 1 | 2025-03-31 | 2025-04-07 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-15 | 2 | 38
495902 | 91901 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 2024-11-14 | 2024-11-14 | 1 | 2025-01-14 | 2025-01-14 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 80
496083 | 92040 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.4 | NO | 2024-11-14 | 2024-11-14 | 1 | 2025-03-25 | 2025-04-07 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-15 | 3 | 38
496093 | 92078 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-11-15 | 2024-11-15 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
496098 | 92131 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 2024-11-15 | 2024-11-15 | 1 | 2025-03-16 | 2025-03-19 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 0 | 35
496111 | 92119 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.07 | NO | 2024-11-15 | 2024-11-15 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-17 | 9 | 31
496275 | 92114 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.7 | NO | 2024-11-16 | 2024-11-16 | 1 | 2025-04-28 | 2025-05-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 0 | 0
496839 | 91935 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.5 | NO | 2024-11-20 | 2024-11-20 | 1 | 2025-05-07 | 2025-05-17 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-17 | 2025-05-17 | 0 | 0
497279 | 92173 | NEM | NBT | APPROVED | SOLAR PV | 34.51 | NO | 2024-12-19 | 2024-12-19 | 1 | 2025-02-26 | 2025-03-05 | 6 | 2025-03-05 | 2025-03-18 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | 0 | 97
497366 | 92024 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18 | NO | 2025-01-27 | 2025-01-27 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-05-22 | 1 | 66
497486 | 92102 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.8 | NO | 2024-12-24 | 2024-12-24 | 1 | 2025-04-04 | 2025-04-04 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-08 | 3 | 34
497594 | 92029 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2024-11-27 | 2024-11-27 | 1 | 2025-04-30 | 2025-05-09 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 0 | 0
498518 | 92130 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 2024-12-09 | 2024-12-09 | 1 | 2025-04-14 | 2025-04-24 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | 0 | 0
498658 | 92065 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.68 | NO | 2024-12-10 | 2024-12-10 | 1 | 2025-03-18 | 2025-03-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | 0 | 28
498805 | 92624 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2024-12-11 | 2024-12-11 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
498906 | 91910 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.7 | NO | 2024-12-12 | 2024-12-12 | 1 | 2025-03-18 | 2025-03-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-21 | 3 | 34
498907 | 92131 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.68 | NO | 2024-12-12 | 2024-12-12 | 1 | 2025-03-17 | 2025-03-18 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-27 | 11 | 70
498929 | 92024 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 2024-12-12 | 2024-12-12 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
499151 | 92118 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.12 | NO | 2025-01-15 | 2025-01-15 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
499395 | 91935 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.3 | NO | 2024-12-16 | 2024-12-16 | 1 | 2025-03-25 | 2025-04-07 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
499543 | 92653 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.1 | NO | 2024-12-30 | 2024-12-30 | 1 | 2025-03-25 | 2025-04-07 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
500807 | 92065 | NEM | NEM-ST | APPROVED | SOLAR PV | 41 | NO | 2025-01-06 | 2025-01-06 | 1 | 2025-04-07 | 2025-04-16 | 8 | 2025-04-16 | 2025-04-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | 0 | 29
501660 | 91913 | NEM | NEM-ST | APPROVED | SOLAR PV | 208.3 | NO | 2025-01-08 | 2025-01-08 | 1 | 2025-01-29 | 2025-02-04 | 5 | 2025-02-04 | 2025-02-18 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | 0 | 132
502371 | 92029 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.3 | NO | 2025-01-14 | 2025-01-14 | 1 | 2025-03-18 | 2025-03-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-17 | 2 | 30
502381 | 92064 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 12 | NO | 2025-01-14 | 2025-01-14 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-16 | 3 | 91
502577 | 92064 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 6.7 | NO | 2025-01-16 | 2025-01-16 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
502804 | 92037 | NON-NEM | RULE 21 AES NON EXPORT | APPROVED | BATTERY STORAGE | 11.5 | NO | 2025-02-20 | 2025-02-20 | 1 | 2025-04-22 | 2025-04-22 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | 0 | 57
502980 | 92075 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 16 | NO | 2025-01-20 | 2025-01-20 | 1 | 2025-03-18 | 2025-03-19 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-20 | 1 | 62
502993 | 92029 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 8 | NO | 2025-01-20 | 2025-01-20 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-15 | 6 | 29
503006 | 91935 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 2025-01-20 | 2025-01-20 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-07 | 4 | 21
503014 | 92064 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.85 | NO | 2025-01-20 | 2025-01-20 | 1 | 2025-02-15 | 2025-02-15 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-04-01 | 1 | 45
503017 | 92084 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 2025-01-20 | 2025-01-20 | 1 | 2025-03-18 | 2025-03-18 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-07 | 4 | 20
503098 | 92128 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 6 | NO | 2025-01-21 | 2025-01-21 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-15 | 4 | 29
503550 | 91945 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11 | NO | 2025-01-24 | 2025-01-24 | 1 | 2025-03-06 | 2025-03-19 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | 0 | 54
503561 | 92037 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.35 | NO | 2025-01-24 | 2025-01-24 | 1 | 2025-03-07 | 2025-03-18 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 0 | 17
503749 | 92057 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 2025-04-20 | 2025-04-20 | 1 | 2025-04-20 | 2025-05-01 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 0 | 8
503771 | 92037 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11 | NO | 2025-01-27 | 2025-01-27 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 21
504194 | 92025 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 13 | NO | 2025-01-29 | 2025-01-29 | 1 | 2025-05-09 | 2025-05-16 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-16 | 0 | 0
504345 | 92084 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 31 | NO | 2025-01-30 | 2025-01-30 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-07 | 4 | 21
504608 | 92019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 2025-02-03 | 2025-02-03 | 1 | 2025-04-28 | 2025-05-11 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-19 | 0 | 39
504609 | 92120 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2025-02-24 | 2025-02-24 | 1 | 2025-05-22 | 2025-05-22 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | 0 | 0
505424 | 92064 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.7 | NO | 2025-02-11 | 2025-02-11 | 1 | 2025-02-11 | 2025-02-15 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-15 | 2 | 89
505438 | 92111 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 2025-02-11 | 2025-02-11 | 1 | 2025-03-17 | 2025-03-17 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-15 | 5 | 29
505444 | 92129 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.74 | NO | 2025-02-11 | 2025-02-11 | 1 | 2025-02-11 | 2025-02-13 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-13 | 2025-05-13 | 0 | 89
505449 | 91910 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.1 | NO | 2025-02-11 | 2025-02-11 | 1 | 2025-06-22 | 2025-06-22 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-22 | 2025-06-22 | 0 | 0
505557 | 92008 | NEM | NBT | APPROVED | PV | 72.94 | NO | 2025-02-19 | 2025-02-19 | 1 | 2025-03-04 | 2025-03-20 | 13 | 2025-03-20 | 2025-03-28 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-21 | 4 | 32
505689 | 92128 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.1 | NO | 2025-03-23 | 2025-03-23 | 1 | 2025-03-23 | 2025-04-06 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 0 | 15
506039 | 92037 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.5 | NO | 2025-02-18 | 2025-02-18 | 1 | 2025-04-28 | 2025-04-28 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | 0 | 0
506265 | 92067 | NON-NEM | RULE 21 AES EXPORT | APPROVED | BATTERY STORAGE | 20 | NO | 2025-02-18 | 2025-02-18 | 1 | 2025-04-23 | 2025-05-05 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-05 | 2025-05-05 | 0 | 0
506391 | 91913 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.56 | NO | 2025-02-26 | 2025-02-26 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-08 | 6 | 31
506533 | 91902 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 5.7 | NO | 2025-02-20 | 2025-02-20 | 1 | 2025-04-21 | 2025-04-21 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 0 | 0
506857 | 91901 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.9 | NO | 2025-03-11 | 2025-03-11 | 1 | 2025-03-11 | 2025-03-19 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | 0 | 82
507756 | 91910 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.34 | NO | 2025-03-04 | 2025-03-04 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
507897 | 92071 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 14 | NO | 2025-03-05 | 2025-03-05 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 0 | 10
508485 | 92673 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.6 | NO | 2025-03-10 | 2025-03-10 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 0 | 0
508871 | 92020 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 7.8 | NO | 2025-03-13 | 2025-03-13 | 1 | 2025-03-13 | 2025-03-19 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-28 | 2025-06-03 | 6 | 76
509399 | 92065 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18.46 | NO | 2025-03-19 | 2025-03-19 | 1 | 2025-04-18 | 2025-05-01 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-08 | 2 | 7
509433 | 92117 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 11.78 | NO | 2025-03-19 | 2025-03-19 | 1 | 2025-04-23 | 2025-05-01 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-21 | 2025-05-27 | 6 | 26
509494 | 92081 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 8 | NO | 2025-03-20 | 2025-03-20 | 1 | 2025-04-28 | 2025-04-28 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-04-28 | 0 | 0
509595 | 92130 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 10 | NO | 2025-03-20 | 2025-03-20 | 1 | 2025-06-20 | 2025-06-20 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-20 | 2025-06-23 | 3 | 3
509646 | 92025 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.85 | NO | 2025-03-21 | 2025-03-21 | 1 | 2025-04-16 | 2025-04-16 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-27 | 12 | 41
509764 | 92021 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.03 | NO | 2025-03-23 | 2025-03-23 | 1 | 2025-04-07 | 2025-04-07 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-17 | 0 | 10
509777 | 92037 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.93 | NO | 2025-03-24 | 2025-03-24 | 1 | 2025-03-24 | 2025-04-07 | 11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 0 | 14
510556 | 92124 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.42 | NO | 2025-03-31 | 2025-03-31 | 1 | 2025-03-31 | 2025-04-07 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-17 | 6 | 10
510566 | 92008 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 4.96 | NO | 2025-04-01 | 2025-04-01 | 1 | 2025-05-08 | 2025-05-08 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | 0 | 0
510737 | 91977 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 18 | NO | 2025-04-02 | 2025-04-02 | 1 | 2025-04-29 | 2025-05-09 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-27 | 7 | 18
510751 | 92103 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV & BATTERY STORAGE | 7 | NO | 2025-04-02 | 2025-04-02 | 1 | 2025-05-15 | 2025-05-22 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | 0 | 25
510762 | 92009 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 8.27 | NO | 2025-04-02 | 2025-04-02 | 1 | 2025-05-14 | 2025-05-14 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | 0 | 29
511209 | 92067 | NEM | NBT | APPROVED | SOLAR PV & BATTERY STORAGE | 62 | NO | 2025-04-08 | 2025-04-08 | 1 | 2025-04-16 | 2025-04-29 | 10 | 2025-04-29 | 2025-05-12 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-11 | 2025-06-12 | 1 | 44
511315 | 92069 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.2 | NO | 2025-04-09 | 2025-04-09 | 1 | 2025-05-01 | 2025-05-01 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-13 | 2025-06-16 | 3 | 46
511499 | 92065 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.16 | NO | 2025-04-10 | 2025-04-10 | 1 | 2025-04-10 | 2025-04-23 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-02 | 0 | 9
511762 | 92021 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.4 | NO | 2025-04-28 | 2025-04-28 | 1 | 2025-05-09 | 2025-05-22 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-29 | 7 | 7
511990 | 91962 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.56 | NO | 2025-04-15 | 2025-04-15 | 1 | 2025-06-12 | 2025-06-12 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | 0 | 0
513244 | 92123 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.85 | NO | 2025-04-28 | 2025-04-28 | 1 | 2025-04-28 | 2025-05-05 | 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | 0 | 17
513250 | 92102 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 2025-04-28 | 2025-04-28 | 1 | 2025-05-22 | 2025-05-22 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | 0 | 0
513501 | 91950 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 2025-04-29 | 2025-04-29 | 1 | 2025-04-29 | 2025-05-09 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-09 | 2025-06-09 | 0 | 31
513639 | 91901 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 2.14 | NO | 2025-05-01 | 2025-05-01 | 1 | 2025-05-01 | 2025-05-09 | 7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-06-03 | 7 | 25
513934 | 91902 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.19 | NO | 2025-05-05 | 2025-05-05 | 1 | 2025-05-20 | 2025-05-20 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | 0 | 0
514046 | 92028 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 3.48 | NO | 2025-05-05 | 2025-05-05 | 1 | 2025-05-05 | 2025-05-15 | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-27 | 5 | 12
516093 | 92019 | NON-NEM | RULE 21 NON EXPORT | APPROVED | SOLAR PV | 1.74 | NO | 2025-05-16 | 2025-05-16 | 1 | 2025-05-16 | 2025-06-03 | 12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-18 | 2025-06-18 | 0 | 15
Formulas:
Business Days to Deem Complete = NETWORKDAYS([Last Date Application Submitted/RCA],[Application Deemed Complete Date],[1]Holidays!$A1:A49)
Business Days to Issue IR Results = NETWORKDAYS([Fast Track Initial Review (IR):],[Date IR Results Issued to Customer],[1]Holidays!$A1:A49)
Business Days to Send NGOM Invoice = NETWORKDAYS([Net Generating Output Meter (NGOM):],[Date Costing Invoice Sent],[1]Holidays!$A1:A49)
Business Days to Install NGOM = NETWORKDAYS([Date Request Sent for NGOM Meter Set],[Date NGOM Installed],[1]Holidays!$A1:A49)
Business Days to Issue SR Results = NETWORKDAYS([Fast Track Supplemental Review (SR):],[Date SR Results Issued to Customer],[1]Holidays!$A1:A49)
Business Days to Issue SR Cost Report = NETWORKDAYS([Date SR Results Issued to Customer],[Supplemental Review (SR) Cost Report:],[1]Holidays!$A1:A49)