## Underground
Project Name / Circuit | Project Start Date | Project Completion Date | Planning Time (Months) | Design Time (Months) | Construction Time (Months) | Other Time (Months) | Other Time Explanation | Miles Undergrounded/Overhead | HFTD Area | Expected Useful Life | Notes
CNF - C449 | 2012-09-01 | 2019-07-18 | 83 | 16 | 13 |  |  | 1.7 | Tier 3 | 45 Years | Planning start date = Plan of Development submittal date of 09/1/2012
SUG-C754 Quick Win - Vellecitos | 2019-02-19 | 2020-05-05 | 0.2 | 11 | 3.1 |  |  | 0.3 | Tier 2 | 45 Years | This was a legacy project prior to official establishment of SUG
CNF - C79A | 2012-09-01 | 2020-06-26 | 94 | 17 | 11 |  |  | 2.72 | Tier 3 | 45 Years | Planning start date = Plan of Development submittal date of 09/1/2012
CNF - C440 Phase I | 2012-09-01 | 2020-08-18 | 96 | 14 | 14 | 3 | +3 month construction delay due to environmental & weather | 9.1 | Tier 3 | 45 Years | Planning start date = Plan of Development submittal date of 09/1/2012
SUG-C221 Ph.2 - Banner Rd | 2019-08-26 | 2020-09-03 | 1 | 5.5 | 3.3 | 2 | Delay due to Caltrans Permit | 0.91 | Tier 3 | 45 Years | This was a legacy project prior to official establishment of SUG
SUG-C221 Ph.1 - Cape Horn | 2019-08-26 | 2020-09-20 | 1 | 1.7 | 9.8 | 7 | Delay due to weather conditions and red flag events | 0.53 | Tier 3 | 45 Years | This was a legacy project prior to official establishment of SUG
SUG-C357 Quick Win Job#1 and #2 - E. Victoria Rd | 2020-02-21 | 2020-09-30 | 1.3 | 1.7 | 3.6 |  |  | 0.83 | Tier 2 | 45 Years | This project was on an expedited schedule.
SUG-C1021 Quick Win - Lilac | 2019-11-01 | 2020-10-24 | 1.2 | 6 | 5 | 2 | Construction delay due to material shortage and school DSA bridge inspection. | 0.31 | Tier 2 | 45 Years
SUG-C75 DUG Ph.1 - Jamul Tribe | 2020-03-04 | 2020-12-15 | 1.1 | 5.5 | 3.5 |  |  | 6.83 | Tier 2,3 | 45 Years
SUG-C1030 Ph.1 - Skyline Ranch | 2019-10-17 | 2021-02-28 | 6.3 | 3.1 | 6.7 | 2 | Delay due to weather conditions and red flag events | 5.9 | Tier 3 | 45 Years
SUG-C1030 Ph.2B - Hell Hole Canyon | 2019-10-17 | 2021-04-05 | 6.4 | 5.2 | 5.8 |  |  | 4.49 | Tier 3 | 45 Years
CNF - C440/C442 Phase II | 2012-09-01 | 2021-06-01 | 106 | 10 | 12 | 4 | +4 month construction delay due to environmental | 3.19 | Tier 3 | 45 Years | Planning start date = Plan of Development submittal date of 09/1/2012
SUG-C1458 Quick Win Ph.1A - W. Victoria Rd | 2020-02-21 | Seee Note Column L | 1.3 | 6.4 | Seee Note Column L |  |  | 4.14 | Tier 2 | 45 Years | In Construction, time frame is subject to change due to design issues being fixed in the field.
SUG-C79 DUG - Oak Grove Drive | 2019-12-11 | Seee Note Column L | 3.7 | 9.4 | Seee Note Column L | 2 | Delay due to reroute to avoid CNF | 3.09 | Tier 3 | 45 Years | In Construction, time frame is subject to change due to weather, subsurface condition, and resource constraint.
SUG-C221 DUG Ph.2 - ST to Dudley's | 2019-10-09 | Seee Note Column L | 6.5 | 13.4 | Seee Note Column L | 7 | month due to Caltrans Permit Delay | 0.41 | Tier 3 | 45 Years | In Construction, time frame is subject to change due to weather, subsurface condition, and resource constraint.
SUG-C1030 Ph.2A - Paradise Mtn. | 2019-10-17 | Seee Note Column L | 6.4 | 5.2 | Seee Note Column L |  |  | 6 | Tier 3 | 45 Years | In Construction, time frame is subject to change due to weather, subsurface condition, and resource constraint.
SUG-C1030 DUG PH.1 - Valley Center | 2019-10-17 | Seee Note Column L | 6.4 | 5.7 | Seee Note Column L |  |  | 3.88 | Tier 2 | 45 Years | In Construction, time frame is subject to change due to weather, subsurface condition, and resource constraint.
SUG-C448 DUG - Buckman Spring Rd. | 2019-12-01 | Seee Note Column L | 4.3 | 11 | Seee Note Column L | 3 | Design delay due to COVID and access restrictions | 1.25 | Tier 3 | 45 Years | In Construction, time frame is subject to change due to weather, subsurface condition, and resource constraint.
SUG-C221 DUG Ph.1 - Dwntn Julian Connection | 2019-10-09 | Seee Note Column L | 6.5 | Seee Note Column L | Seee Note Column L | 4+ | Design delay due to Caltrans Permit | 1.68 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C221 DUG Ph.24 - Spencer Sch to Hwy 79 | 2019-10-09 | Seee Note Column L | 6.5 | Seee Note Column L | Seee Note Column L | 4+ | Design delay due to Caltrans Permit | 2.52 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C445 DUG - Old Hwy 80 | 2019-12-01 | Seee Note Column L | 4.3 | Seee Note Column L | Seee Note Column L | 4+ | Design delay due to Caltrans Permit | 3.04 | Tier 2 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1030 Ph.1A - Service Conversion Private | 2019-10-17 | Seee Note Column L | 16.5 | Seee Note Column L | Seee Note Column L |  |  | 3.1 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1030 DUG Ph.2 N Wohlford Rd | 2019-10-17 | Seee Note Column L | 15.6 | Seee Note Column L | Seee Note Column L |  |  | 2.47 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C908 DUG - Cole Grade Rd | 2019-12-01 | Seee Note Column L | 7 | Seee Note Column L | Seee Note Column L | 5 | Design delay due to coordination issues with other SDGE internal projects and County projects. | 1 | Tier 2 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C216 DUG Ph.2 | 2019-12-01 | Seee Note Column L | 14.3 | Seee Note Column L | Seee Note Column L |  | Design delay due to Tribal resolution/easement | 1.75 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1458 Quick Win Ph.1B - Calrans Crossing | 2020-02-21 | Seee Note Column L | 11.8 | Seee Note Column L | Seee Note Column L | 4+ | Design delay due to Caltrans Permit | 0.1 | Tier 2 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1458 Quick Win Ph.2 - AL Elem School | 2020-02-01 | Seee Note Column L | 12.5 | Seee Note Column L | Seee Note Column L |  |  | 0.24 | Tier 2 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C216 DUG Ph.1 - to Rincon Harrah's Casino | 2019-12-01 | Seee Note Column L | 14.3 | Seee Note Column L | Seee Note Column L |  | Design delay due to Tribal resolution/easement | 3.11 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1030 Ph.1B - Service Conversion Tribal | 2019-10-17 | Seee Note Column L | 16.5 | Seee Note Column L | Seee Note Column L |  |  | 3.4 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C448 Microgrid partnership | 2019-12-01 | Seee Note Column L | 6.8 | Seee Note Column L | Seee Note Column L | 4+ | Design delay due to Caltrans Permit | 0.82 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1030 Ph.3A - Santee Ln. | 2019-10-17 | Seee Note Column L | 6.2 | Seee Note Column L | Seee Note Column L |  |  | 4.39 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1030 Ph.3B - Oos Place | 2019-10-17 | Seee Note Column L | 6.2 | Seee Note Column L | Seee Note Column L |  |  | 6.63 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C1030 Ph.4 - South Kiavo | 2019-10-17 | Seee Note Column L | 16.6 | Seee Note Column L | Seee Note Column L |  |  | 8.5 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C220 DUG Ph.1 | 2020-11-20 | Seee Note Column L | Seee Note Column L | Seee Note Column L | Seee Note Column L |  |  | 3.42 | Tier 3 | 45 Years | In Planning, pending schedule.
SUG-SUG-C221 DUG PH.3 - ST to Spencer Sch. | 2019-10-09 | Seee Note Column L | 6.5 | Seee Note Column L | Seee Note Column L | 4+ | Design Delay due to Caltrans Permit and CNF Easement | 2.92 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C221 WiNGS - Extention for OK1 and SL1 | 2020-03-01 | Seee Note Column L | Seee Note Column L | Seee Note Column L | Seee Note Column L |  |  | 2 | Tier 3 | 45 Years | In Planning, pending schedule.
SUG-C357 Quick Win Job#3 - E. Victoria Rd (FIRM) | 2020-02-21 | Seee Note Column L | Seee Note Column L | Seee Note Column L | Seee Note Column L |  |  | 0.1 | TIer 2 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C358 DUG Ph.1 - Alpine Blvd | 2020-02-01 | Seee Note Column L | 14.6 | Seee Note Column L | Seee Note Column L |  |  | 0.97 | Tier 2,3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C358 DUG Ph.2 - Caltrans Crossing & Willows Rd. | 2020-02-01 | Seee Note Column L | 14.6 | Seee Note Column L | Seee Note Column L |  |  | 2 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C358 DUG Ph.3 - Viejas Casino | 2020-02-01 | Seee Note Column L | 14.6 | Seee Note Column L | Seee Note Column L |  |  | 2.3 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C441 DUG | 2019-12-01 | Seee Note Column L | 4 | Seee Note Column L | Seee Note Column L | 4+ | Design delay due to CNF Easement and COVID | 4.9 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C442 DUG | 2019-12-01 | Seee Note Column L | 2.2 | Seee Note Column L | Seee Note Column L | 4+ | Design delay due to CNF Easement and COVID | 3.1 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C75 DUG Ph. 2 - Lyons Valley Rd | 2020-03-04 | Seee Note Column L | 13.8 | Seee Note Column L | Seee Note Column L |  |  | 1.7 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C79 Ph.1 - Sherilton Valley | 2019-12-11 | Seee Note Column L | 3.8 | Seee Note Column L | Seee Note Column L | 11+ | Design delay due to CNF Easement and COVID | 8.08 | Tier 3 | 45 Years | In Design, duration subject to change depending on access, permit, and easment, and weather condition restraints.
SUG-C972 DUG | 2020-03-01 | Seee Note Column L | Seee Note Column L | Seee Note Column L | Seee Note Column L |  |  | 6 | Tier 2 | 45 Years | In Planning, pending schedule.
SUG-OK1 WiNGS - Convert to 12kV UG | 2020-03-01 | Seee Note Column L | Seee Note Column L | Seee Note Column L | Seee Note Column L |  |  | 8 | Tier 3 | 45 Years | In Planning, pending schedule.
SUG-SL1 WiNGS - Convert to 12kV UG | 2020-03-01 | Seee Note Column L | Seee Note Column L | Seee Note Column L | Seee Note Column L |  |  | 5.3 | Tier 3 | 45 Years | In Planning, pending schedule.
SUG-C222 WiNGS- Wynola | 2020-03-01 | Seee Note Column L | Seee Note Column L | Seee Note Column L | Seee Note Column L |  |  | 9.1 | Tier 3 | 45 Years | In Planning, pending schedule.

## CoveredConductor
Project Name / Circuit | Project Start Date | Project Completion Date | Planning Time (Months) | Design Time (Months) | Construction Time (Months) | Other Time (Months) | Other Time Explanation | Miles Undergrounded | HFTD Area | Expected Useful Life | Notes
0972-F-CC | 2020-03-23 | 2020-11-07 | 3 | 3 | 2 | 1 | Land/ENV/Permit | 1.9 | Tier 3 | 45 Years | Construction completed
448II | 2020-06-22 | 2021-05-27 | 6 | 9 | 1 | 2 | Permit | 0.65 | Tier 3 | 45 Years | In construction
0222-CC-CC | 2020-03-01 | 2021-06-30 | 2 | 8 | 4 | 3 | Land/ENV/Permit | 0.84 | Tier 3 | 45 Years | In construction
448LL | 2020-06-22 | 2021-07-06 | 6 | 11 | 1 | 2 | Land/ENV/Permit | 0.4 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448QQQ | 2020-06-22 | 2021-07-25 | 6 | 12 | 1 | 3 | Land/ENV/Permit | 0.4 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448RR | 2020-06-22 | 2021-07-31 | 6 | 12 | 1 | 2 | Land/ENV/Permit | 0.6 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448MM | 2020-06-22 | 2021-08-03 | 6 | 11 | 1 | 3 | Land/ENV/Permit | 0.89 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448RRR | 2020-06-22 | 2021-08-09 | 6 | 12 | 1 | 3 | Land/ENV/Permit | 0.55 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448DD | 2020-06-22 | 2021-08-19 | 6 | 12 | 2 | 4 | Land/ENV/Permit | 0.45 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
0157-DD-CC | 2020-06-22 | 2021-08-19 | 6 | 10 | 4 | 1 | Land/ENV/Permit | 1.39 | Tier 3 | 45 Years | In construction
448GG | 2020-06-22 | 2021-08-21 | 6 | 13 | 1 | 3 | Land/ENV/Permit | 0.15 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448G | 2020-06-22 | 2021-08-28 | 6 | 12 | 1 | 3 | Land/ENV/Permit | 0.4 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448BB | 2020-06-22 | 2021-09-01 | 6 | 12 | 1 | 5 | Land/ENV/Permit | 0.25 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
1090-A-CC | 2021-01-12 | 2021-09-01 | 2 | 13 | 2 | 2 | Land/ENV | 1.54 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
448HH | 2020-06-22 | 2021-09-07 | 6 | 11 | 1 | 5 | Land/ENV/Permit | 0.45 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
0078-H-CC | 2020-03-24 | 2021-09-20 | 3 | 13 | 2 | 2 | Land/ENV/Permit | 1.49 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448KK | 2020-06-22 | 2021-09-22 | 6 | 11 | 1 | 4 | Land/ENV/Permit | 0.3 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448F | 2020-06-22 | 2021-09-22 | 6 | 13 | 1 | 4 | Permit | 0.5 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448FF | 2020-06-22 | 2021-09-27 | 6 | 11 | 1 | 4 | Land/ENV/Permit | 0.5 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
0157-O-CC | 2020-06-22 | 2021-11-03 | 6 | 13 | 4 | 2 | Land/ENV/Permit | 1.74 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448JJ | 2020-06-22 | 2021-11-16 | 6 | 13 | 2 | 4 | Land/ENV/Permit | 0.35 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
448CC | 2020-06-22 | 2021-12-14 | 6 | 13 | 2 | 3 | Land/ENV/Permit | 1.29 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-S-CC | 2020-06-22 | 2021-12-28 | 6 | 14 | 4 | 4 | Land/ENV/Permit | 2.13 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
0448-E2-CC | 2020-06-22 | 2021-12-31 | 6 | 8 | 4 | 4 | Land/ENV | 2.03 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
0448-E4-CC | 2020-06-22 | 2021-12-31 | 6 | 15 | 4 | 4 | Land/ENV | 1.39 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in final design
0445-L-CC | 2020-06-22 | 2021-12-31 | 6 | 15 | 3 | 4 | Land/ENV/Permit | 2.68 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-P-CC | 2020-06-22 | 2021-12-31 | 6 | 15 | 4 | 4 | Land/ENV/Permit | 3.08 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-F2-CC | 2020-06-22 | 2021-12-31 | 6 | 8 | 3 | 4 | Land/ENV | 1.19 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0212-GG-CC | 2020-06-22 | 2021-12-31 | 6 | 11 | 8 | 3 | Land/ENV/Permit | 0.79 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in final design
448AA | 2020-06-22 | 2022-03-17 | 6 | 13 | 4 | 5 | Land/ENV/Permit | 0.35 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-N-CC | 2020-06-22 | 2022-05-03 | 6 | 11 | 4 | 5 | Land/ENV/Permit | 1.49 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-S-CC-PH-02 | 2020-06-22 | 2022-05-04 | 6 | 10 | 4 | 4 | Land/ENV | 2.63 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-O-CC | 2020-06-22 | 2022-06-02 | 6 | 11 | 4 | 4 | Land/ENV | 2.23 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-XX-CC | 2020-06-22 | 2022-06-16 | 6 | 11 | 4 | 4 | Land/ENV | 0.5 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-E3-CC | 2020-06-22 | 2022-07-23 | 6 | 12 | 4 | 4 | Land/ENV | 1.04 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-J2-CC | 2020-06-22 | 2022-08-05 | 6 | 10 | 4 | 4 | Land/ENV/Permit | 0.55 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-A-CC | 2020-06-22 | 2022-08-20 | 6 | 10 | 4 | 4 | Land/ENV/Permit | 3.47 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0212-N-CC | 2020-06-22 | 2022-08-23 | 6 | 11 | 3 | 5 | Land/ENV/Permit | 4.76 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0445-H-CC | 2020-06-22 | 2022-08-24 | 6 | 10 | 4 | 4 | Land/ENV/Permit | 0.84 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-J-CC | 2020-06-22 | 2022-08-24 | 6 | 13 | 4 | 4 | Land/ENV/Permit | 2.68 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0445-P-CC | 2020-06-22 | 2022-08-25 | 6 | 10 | 4 | 5 | Land/ENV/Permit | 1.69 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0212-O-CC | 2020-06-22 | 2022-08-29 | 6 | 12 | 3 | 5 | Land/ENV/Permit | 3.92 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0176-T-CC | 2021-03-26 | 2022-08-30 | 10 | 9 | 4 | 4 | Land/ENV/Permit | 0.79 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0445-I-CC | 2020-06-22 | 2022-08-31 | 6 | 11 | 4 | 4 | Land/ENV/Permit | 2.98 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-E-CC | 2020-06-22 | 2022-08-31 | 6 | 11 | 4 | 4 | Land/ENV | 2.38 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0212-R-CC | 2020-06-22 | 2022-09-01 | 6 | 12 | 3 | 5 | Land/ENV/Permit | 2.88 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-J3-CC | 2020-06-22 | 2022-09-06 | 6 | 14 | 4 | 4 | Land/ENV/Permit | 0.69 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0176-S-CC | 2021-03-26 | 2022-09-07 | 10 | 9 | 4 | 4 | Land/ENV | 2.23 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-Z-CC | 2020-06-22 | 2022-09-08 | 6 | 11 | 4 | 5 | Land/ENV/Permit | 1.84 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-C-CC | 2020-06-22 | 2022-09-09 | 6 | 11 | 4 | 4 | Land/ENV/Permit | 0.2 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0176-R-CC | 2021-03-26 | 2022-09-13 | 10 | 9 | 4 | 4 | Land/ENV | 1.84 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0176-Q-CC | 2021-03-26 | 2022-09-14 | 10 | 9 | 4 | 4 | Land/ENV | 1.49 | Tier 2 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-N-PH-02-CC | 2020-06-22 | 2022-09-15 | 6 | 11 | 4 | 5 | Land/ENV/Permit | 3.08 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-G-CC | 2020-06-22 | 2022-09-15 | 6 | 11 | 4 | 4 | Land/ENV/Permit | 3.62 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-D-CC | 2020-06-22 | 2022-09-15 | 6 | 11 | 4 | 4 | Land/ENV | 2.38 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-B-CC | 2020-06-22 | 2022-09-22 | 6 | 11 | 4 | 4 | Land/ENV | 3.03 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-H2-CC | 2020-06-22 | 2022-09-22 | 6 | 11 | 4 | 4 | Land/ENV | 1.94 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-A2-CC | 2020-06-22 | 2022-09-24 | 6 | 11 | 4 | 4 | Land/ENV | 1.74 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-B2-CC | 2020-06-22 | 2022-09-28 | 6 | 11 | 4 | 4 | Land/ENV | 1.44 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-A3-CC | 2020-06-22 | 2022-10-01 | 6 | 27 | 4 | 4 | Land/ENV | 1.69 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-F-CC | 2020-06-22 | 2022-10-05 | 6 | 12 | 4 | 4 | Land/ENV/Permit | 2.63 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-G2-CC | 2020-06-22 | 2022-10-07 | 6 | 12 | 4 | 5 | Land/ENV | 1.84 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0448-H-CC | 2020-06-22 | 2022-10-12 | 6 | 12 | 4 | 5 | Land/ENV/Permit | 3.67 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0157-EE-CC | 2020-06-22 | 2022-11-03 | 6 | 10 | 4 | 6 | Land/ENV/Permit | 2.53 | Tier 3 | 45 Years | Design pivoted from traditional to covered conductor, in preliminary design
0079-Q-CC | 2021-03-19 | 2022-11-08 | 3 | 13 | 4 | 6 | Land/ENV/Permit | 2.58 | Tier 3 | 45 Years | In preliminary design