## Sheet1
a) Order Number | b) Program | c) Circuit ID Number | d) Circuit-Segment ID | e) Wildfire Risk Score Post-mitigation | e2) Wildfire Risk Score Pre-mitigation | f) Expected/Actual Start Date | g) Expected Completion Date | h) Length of CC to be Installed (Circuit Miles) | i) Length of SUG conductor to be installed in 2025 | j) Length of OH Conductor Permanent Removed in 2025 replaced with SUG (Circuit Miles) | k) Length of OH Conductor Permanent Removed in 2025 replaced with CC (Circuit Miles) | l) Length of Bare Wire Install in 2024 | m) Length of Bare Wire Install in 2025
0073-CC-CC | CC | C0073 | 73-1130 | 0.00025314 | 0.00058691 | 2024-11-07 | 2025-02-04 | 0.60966 |  |  |  |  | 0
0073-DD-CC | CC | C0073 | 73-1130 | 0.00025314 | 0.00058691 | 2025-03-05 | 2025-06-02 | 1.5929 |  |  |  |  | 0
0073-EE-CC | CC | C0073 | 73-23R | 0.00024549 | 0.00042991 | 2025-07-02 | 2025-09-29 | 2.7576 |  |  |  |  | 0
0075-A-CC | CC | C0075 | 75-996R, CB 91 | 2.3879e-05 | 3.9133e-05 | 2024-10-22 | 2025-01-19 | 0.32083 |  |  |  |  | 0
0079-Q-CC | CC | C0079 | 79-785 | 0.00045693 | 0.00055008 | 2025-01-23 | 2025-04-22 | 1.7868 |  |  |  |  | 0
0176-F-TU | Trad | C0176 | 176-197F | 4.6996e-05 | 4.7158e-05 | 2023-10-13 | 2024-04-05 | 0 |  |  |  | 0.45 | 0.44798
0209-A-CC | CC | C0209 | 209-1769F | 8.1224e-05 | 8.1224e-05 | 2025-07-18 | 2025-10-15 | 0 |  |  |  |  | 0
0211-A-CC | CC | C0211 | 211-312R | 0.00021157 | 0.00021157 | 2025-07-02 | 2025-09-29 | 0.1217 |  |  |  |  | 0
0212-C-CC | CC | C0212 | 212-1177R, 212-880R | 0.00025303 | 0.00035697 | 2025-05-28 | 2025-08-25 | 1.3185 |  |  |  |  | 0
0212-D-CC | CC | C0212 | 212-1177R, 212-1204R, 212-743R | 0.00025303 | 0.00035697 | 2025-06-04 | 2025-09-01 | 1.4777 |  |  |  |  | 0
0212-E-CC | CC | C0212 | 212-1177R, 212-1204R, 212-758R | 0.00025303 | 0.00035697 | 2025-05-14 | 2025-08-11 | 0.95084 |  |  |  |  | 0
0212-F-CC | CC | C0212 | 212-1177R, 212-1204R, 212-758R, 212-799R, 212-888R | 0.00025303 | 0.00035697 | 2025-05-07 | 2025-08-04 | 0.95707 |  |  |  |  | 0
0212-G-CC | CC | C0212 | 212-1204R, 212-758R, 212-799R | 4.1612e-05 | 5.6696e-05 | 2025-06-11 | 2025-09-08 | 1.0797 |  |  |  |  | 0
0212-H-CC | CC | C0212 | 212-758R, 212-799R, 212-888R | 5.0784e-05 | 8.6972e-05 | 2025-05-07 | 2025-08-04 | 1.4448 |  |  |  |  | 0
0212-I-CC | CC | C0212 | 212-799R, 212-888R | 5.0784e-05 | 8.6972e-05 | 2025-06-04 | 2025-09-01 | 0.89759 |  |  |  |  | 0
0212-J-CC | CC | C0212 | 212-888R | 5.0784e-05 | 8.6972e-05 | 2025-05-20 | 2025-08-17 | 0.94133 |  |  |  |  | 0
0212-K-CC | CC | C0212 | 212-1204R, 212-888R | 5.0784e-05 | 8.6972e-05 | 2025-06-11 | 2025-09-08 | 1.0628 |  |  |  |  | 0
0212-L-CC | CC | C0212 | 212-1204R, 212-888R | 5.0784e-05 | 8.6972e-05 | 2025-05-20 | 2025-08-17 | 1.1938 |  |  |  |  | 0
0212-M-CC | CC | C0212 | 212-1204R, 212-880R | 7.4398e-06 | 1.1055e-05 | 2025-05-28 | 2025-08-25 | 0.88488 |  |  |  |  | 0
0212-N-CC-ESH | CC | C0212 | 212-1204R, 212-743R | 6.6984e-05 | 7.3722e-05 | 2025-05-14 | 2025-08-11 | 0.4081 |  |  |  |  | 0
0214-A-CC | CC | C0214 | 214-647R | 7.6322e-05 | 0.00025371 | 2025-07-31 | 2025-10-28 | 1.5696 |  |  |  |  | 0
0214-B-CC | CC | C0214 | 214-647R | 7.6322e-05 | 0.00025371 | 2025-07-31 | 2025-10-28 | 1.1289 |  |  |  |  | 0
0214-C-CC | CC | C0214 | 214-647R | 7.6322e-05 | 0.00025371 | 2025-07-31 | 2025-10-28 | 1.242 |  |  |  |  | 0
0214-D-CC | CC | C0214 | 214-647R | 7.6322e-05 | 0.00025371 | 2025-07-31 | 2025-10-28 | 1.5926 |  |  |  |  | 0
0217-Z | Trad | C0217 | 217-835R | 0.0013957 | 0.0013957 | 2024-05-11 | 2024-08-08 | 0 |  |  |  | 0.49 | 0.49877
0231-A-CC | CC | C0231 | 231-1635R, CB 233 | 0.00012016 | 0.00055793 | 2025-07-02 | 2025-09-29 | 0.41251 |  |  |  |  | 0
0260-A-CC | CC | C0260 | 260-358R | 0.00030676 | 0.00030676 | 2025-07-02 | 2025-09-29 | 1.1898 |  |  |  |  | 0
0260-B-CC | CC | C0260 | 260-358R | 0.00030676 | 0.00030676 | 2025-07-02 | 2025-09-29 | 1.5604 |  |  |  |  | 0
0260-C-CC | CC | C0260 | 260-358R | 0.00030676 | 0.00030676 | 2025-07-02 | 2025-09-29 | 0.6372 |  |  |  |  | 0
0260-D-CC | CC | C0260 | 260-358R | 0.00030676 | 0.00030676 | 2025-07-02 | 2025-09-29 | 1.1043 |  |  |  |  | 0
0350-F-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2024-10-25 | 2025-01-22 | 1.4571 |  |  |  |  | 0
0350-L-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2025-01-02 | 2025-04-01 | 0.34155 |  |  |  |  | 0
0350-M-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2025-01-02 | 2025-04-01 | 1.1523 |  |  |  |  | 0
0350-P-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2025-01-02 | 2025-04-01 | 0.6642 |  |  |  |  | 0
0350-Q-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2025-02-12 | 2025-05-12 | 0.73912 |  |  |  |  | 0
0350-R-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2025-01-02 | 2025-04-01 | 1.2316 |  |  |  |  | 0
0350-S-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2025-01-04 | 2025-04-03 | 1.3045 |  |  |  |  | 0
0444-A2-CC | CC | C0444 | N/A |  |  | 2025-03-14 | 2025-06-11 | 0 |  |  |  |  | 0
0444-A-CC | CC | C0444 | 444-43R, CB 444 | 0.00040137 | 0.00055657 | 2025-01-02 | 2025-04-01 | 0.95833 |  |  |  |  | 0
0444-E-CC | CC | C0444 | 444-43R | 0.00040137 | 0.00055657 | 2025-01-02 | 2025-04-01 | 1.1672 |  |  |  |  | 0
0444-F-CC | CC | C0444 | 444-43R | 0.00040137 | 0.00055657 | 2025-01-02 | 2025-04-01 | 0.75937 |  |  |  |  | 0
0444-G-CC | CC | C0444 | 444-15R | 2.8812e-05 | 2.8812e-05 | 2025-07-02 | 2025-09-29 | 1.2541 |  |  |  |  | 0
0445-P-CC-ESH | CC | C0445 | 445-1311R | 0.00054182 | 0.001547 | 2025-07-02 | 2025-09-29 | 0.038775 |  |  |  |  | 0
0448-F-CC | CC | C0448 | 448-11R, 448-744R | 0.0022025 | 0.0030746 | 2025-02-04 | 2025-05-04 | 1.7023 |  |  |  |  | 0
0448-H-CC | CC | C0448 | 448-33R | 0.00014217 | 0.00026837 | 2025-01-07 | 2025-04-06 | 1.1741 |  |  |  |  | 0
0449-A-CC | CC | C0449 | 449-6R | 0.00064343 | 0.00065906 | 2025-07-08 | 2025-10-05 | 0.79984 |  |  |  |  | 0
0449-B-CC | CC | C0449 | 449-6R | 0.00064343 | 0.00065906 | 2025-07-02 | 2025-09-29 | 0.21791 |  |  |  |  | 0
0520-A-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2024-11-13 | 2025-02-10 | 1.3078 |  |  |  |  | 0
0520-B-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2024-11-27 | 2025-02-24 | 1.2658 |  |  |  |  | 0
0520-C-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2025-01-02 | 2025-04-01 | 1.0258 |  |  |  |  | 0
0520-D-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2025-01-02 | 2025-04-01 | 0.98984 |  |  |  |  | 0
0520-E-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2024-10-17 | 2025-01-14 | 1.0604 |  |  |  |  | 0
0520-G-CC | CC | C0520 | 520-45 | 6.6607e-05 | 8.5924e-05 | 2025-01-02 | 2025-04-01 | 1.0744 |  |  |  |  | 0
0908-G-PH-02 | Trad | C0908 | 908-1172R | 0.00029651 | 0.00029651 | 2025-09-22 | 2025-12-20 | 0 |  |  |  |  | 0.043244
1166-A-CC | CC | C1166 | 1166-342R | 0.00032837 | 0.00032837 | 2025-07-02 | 2025-09-29 | 0.66332 |  |  |  |  | 0
1233-A-CC | CC | C1233 | 1233-587R, 1233-589R |  |  | 2025-01-25 | 2025-04-24 | 0.9773 |  |  |  |  | 0
1233-B-CC | CC | C1233 | 1233-589R |  |  | 2025-03-05 | 2025-06-02 | 2.227 |  |  |  |  | 0
1233-C-CC | CC | C1233 | 1233-587R |  |  | 2025-01-31 | 2025-04-30 | 0.85592 |  |  |  |  | 0
1233-D-CC | CC | C1233 | 1233-587R |  |  | 2025-02-08 | 2025-05-08 | 1.3009 |  |  |  |  | 0
1233-E-CC | CC | C1233 | 1233-587R |  |  | 2025-02-07 | 2025-05-07 | 0.74033 |  |  |  |  | 0
1233-F-CC | CC | C1233 | 1233-587R |  |  | 2025-02-18 | 2025-05-18 | 1.5462 |  |  |  |  | 0
1233-G-CC | CC | C1233 | 1233-585R |  |  | 2025-02-18 | 2025-05-18 | 1.6527 |  |  |  |  | 0
1233-H-CC | CC | C1233 | 1233-587R |  |  | 2025-02-22 | 2025-05-22 | 1.1152 |  |  |  |  | 0
1233-I-CC | CC | C1233 | 1233-585R |  |  | 2025-02-22 | 2025-05-22 | 0.93334 |  |  |  |  | 0
1233-J-CC | CC | C1233 | 1233-585R |  |  | 2025-03-08 | 2025-06-05 | 1.1303 |  |  |  |  | 0
1233-K-CC | CC | C1233 | 1233-585R, 239-2215R |  |  | 2025-03-08 | 2025-06-05 | 1.0778 |  |  |  |  | 0
1233-L-CC | CC | C1233 | 1233-585R |  |  | 2025-03-15 | 2025-06-12 | 1.1676 |  |  |  |  | 0
1233-M-CC | CC | C1233 | 1233-585R |  |  | 2025-03-22 | 2025-06-19 | 0.74637 |  |  |  |  | 0
1233-N-CC | CC | C1233 | 1233-585R, 1233-591R |  |  | 2025-03-25 | 2025-06-22 | 1.4617 |  |  |  |  | 0
1233-O-CC | CC | C1233 | 1233-591R |  |  | 2025-03-29 | 2025-06-26 | 1.4312 |  |  |  |  | 0
1233-P-CC | CC | C1233 | 1233-591R |  |  | 2025-04-05 | 2025-07-03 | 1.003 |  |  |  |  | 0
1233-Q-CC | CC | C1233 | 1233-591R |  |  | 2025-04-05 | 2025-07-03 | 1.0867 |  |  |  |  | 0
1233-R-CC | CC | C1233 | 1233-591R |  |  | 2025-04-11 | 2025-07-09 | 0.45206 |  |  |  |  | 0
1233-S-CC | CC | C1233 | 1233-591R |  |  | 2025-04-19 | 2025-07-17 | 0.89021 |  |  |  |  | 0
448N CC | CC | C0448 | 448-9R | 0.00055273 | 0.0008739 | 2025-03-26 | 2025-05-25 | 0.79704 |  |  |  |  | 0
448V-TU | Trad | C0448 | 448-744R |  |  | 2024-01-18 | 2024-03-18 | 0 |  |  |  | 0.1 | 0.1036
CJU1-A-CC | CC | C0JU1 | CB JU1 | 5.3305e-05 | 5.3305e-05 | 2025-07-18 | 2025-10-15 | 0.31543 |  |  |  |  | 0
0220-U-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2024-07-26 | 2025-01-08 | 0 | 3.02 | 2.3 |  | 0 | 0
0220-W-SUG | SUG | C0220 | 220-288R | 0 | 0.00013367 | 2024-09-16 | 2025-01-10 | 0 | 2.04 |  |  | 0 | 0
0217-A-SUG | SUG | C0217 | 217-983R | 0 | 0.0029499 | 2024-08-05 | 2025-01-16 | 0 | 3.3 |  |  | 0 | 0
0222-B-SUG | SUG | C0222 | 222-1364R | 0.000985 | 0.0045724 | 2024-07-29 | 2025-01-17 | 0 | 3.8 |  |  | 0 | 0
0222-K-SUG | SUG | C0222 | 222-1503, 222-2013R | 0.0010472 | 0.0014909 | 2024-11-12 | 2025-02-14 | 0 | 3.18 |  |  | 0 | 0
0210-C-SUG | SUG | C0210 | 210-172R | 0 | 0.00027968 | 2024-12-30 | 2025-02-20 | 0 | 0.5 | 0.19 |  | 0 | 0
0222-T-SUG | SUG | C0222 | 222-1401R | 8.4956e-06 | 0.006763 | 2024-10-30 | 2025-02-25 | 0 | 1.73 | 1.94 |  | 0 | 0
0217-B-SUG | SUG | C0217 | 217-983R | 0 | 0.0029499 | 2024-08-09 | 2025-03-10 | 0 | 3.7 |  |  | 0 | 0
0445-G-SUG | SUG | C0445 | 445-1311R | 0.00054182 | 0.001547 | 2024-08-16 | 2025-03-17 | 0 | 4.12 | 2.88 |  | 0 | 0
0220-N-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2024-10-07 | 2025-03-19 | 0 | 3.5 | 1.12 |  | 0 | 0
0210-G-SUG | SUG | C0210 | 210-9R | 0 | 6.4591e-05 | 2024-11-26 | 2025-03-24 | 0 | 2.7 | 1.8 |  | 0 | 0
0222-FF-SUG | SUG | C0222 | 222-2013R | 0.0010472 | 0.0014909 | 2024-10-09 | 2025-04-15 | 0 | 4.18 |  |  | 0 | 0
0210-N-SUG | SUG | C0210 | 210-9R | 0 | 6.4591e-05 | 2024-12-27 | 2025-04-21 | 0 | 3.6 |  |  | 0 | 0
0442-DUG-SUG | SUG | C0442 | 442-729 |  |  | 2024-08-09 | 2025-04-22 | 0 | 6.2 | 1.59 |  | 0 | 0
0314-A-SUG | SUG | C0314 | 314-13F |  |  | 2025-03-25 | 2025-04-28 | 0 | 0 |  |  | 0 | 0
0210-E-SUG | SUG | C0210 | 210-9R | 0 | 6.4591e-05 | 2025-02-26 | 2025-04-29 | 0 | 3.2 | 2.1 |  | 0 | 0
1215-D-SUG | SUG | C1215 | 1215-12R | 0.00045964 | 0.00088047 | 2025-01-22 | 2025-05-14 | 0 | 1.4 | 1.4 |  | 0 | 0
0220-S-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2024-10-23 | 2025-05-21 | 0 | 4.2 | 2.81 |  | 0 | 0
0211-A-SUG | SUG | C0211 | 211-279R | 4.7459e-07 | 0.00069999 | 2025-01-29 | 2025-05-21 | 0 | 5 |  |  | 0 | 0
0211-B-SUG | SUG | C0211 | 211-280R | 0 | 0.00052761 | 2025-02-06 | 2025-05-30 | 0 | 4.4 |  |  | 0 | 0
0210-F-SUG | SUG | C0210 | 210-9R | 0 | 6.4591e-05 | 2025-03-21 | 2025-05-30 | 0 | 3.2 | 1.3 |  | 0 | 0
1030-1B-SUG | SUG | C1030 | 1030-18R | 5.0986e-06 | 0.00025914 | 2025-01-28 | 2025-06-03 | 0 | 3.47 | 1.35 |  | 0 | 0
1215-C-SUG | SUG | C1215 | 1215-12R | 0.00045964 | 0.00088047 | 2025-02-14 | 2025-06-09 | 0 | 0.5 | 0.95 |  | 0 | 0
0211-D-SUG | SUG | C0211 | 211-280R | 0 | 0.00052761 | 2025-02-17 | 2025-06-10 | 0 | 4.4 |  |  | 0 | 0
0211-I-SUG | SUG | C0211 | 211-280R | 0 | 0.00052761 | 2025-02-17 | 2025-06-10 | 0 | 2.8 |  |  | 0 | 0
0212-A-SUG | SUG | C0212 | 212-638R | 3.1059e-05 | 3.4051e-05 | 2025-04-16 | 2025-06-23 | 0 | 0.3 |  |  | 0 | 0
0221-B-SUG | SUG | C0221 | 221-37AE | 0.00023319 | 0.00026009 | 2024-12-05 | 2025-06-24 | 0 | 5 |  |  | 0 | 0
0442-A-SUG | SUG | C0442 | 442-16R | 0.00034354 | 0.00070083 | 2025-01-16 | 2025-06-25 | 0 | 3.02 |  |  | 0 | 0
0442-B-SUG | SUG | C0442 | 442-16R | 0.00034354 | 0.00070083 | 2025-01-16 | 2025-06-25 | 0 | 2.89 |  |  | 0 | 0
0441-E-SUG | SUG | C0441 | 441-30R | 0.00046514 | 0.00087393 | 2025-04-25 | 2025-07-03 | 0 | 0.77 |  |  | 0 | 0
0078-C-SUG | SUG | C0078 | 78-782R, 78-35R | 0.00019725 | 0.00019725 | 2025-03-18 | 2025-07-10 | 0 | 0.4 |  |  | 0 | 0
0211-E-SUG | SUG | C0211 | 211-279R | 4.7459e-07 | 0.00069999 | 2025-03-24 | 2025-07-16 | 0 | 4.3 |  |  | 0 | 0
0222-AA-SUG | SUG | C0222 | 222-1401R | 8.4956e-06 | 0.006763 | 2025-02-10 | 2025-07-18 | 0 | 4.35 | 2.53 |  | 0 | 0
0211-H-SUG | SUG | C0211 | 211-279R | 4.7459e-07 | 0.00069999 | 2025-03-26 | 2025-07-18 | 0 | 1.7 |  |  | 0 | 0
0211-G-SUG | SUG | C0211 | 211-279R | 4.7459e-07 | 0.00069999 | 2025-03-27 | 2025-07-21 | 0 | 2.1 |  |  | 0 | 0
0211-J-SUG | SUG | C0211 | 211-279R, 211-280R | 4.7459e-07 | 0.00069999 | 2025-03-31 | 2025-07-23 | 0 | 2.1 |  |  | 0 | 0
0078-A-SUG | SUG | C0078 | 78-26R | 0.00060533 | 0.00083499 | 2025-04-03 | 2025-07-28 | 0 | 0.5 |  |  | 0 | 0
0078-B-SUG | SUG | C0078 | 78-26R | 0.00060533 | 0.00083499 | 2025-04-08 | 2025-07-31 | 0 | 0.4 |  |  | 0 | 0
0078-D-SUG | SUG | C0078 | 78-782R, 78-35R | 0.00019725 | 0.00019725 | 2025-04-09 | 2025-08-01 | 0 | 0.3 |  |  | 0 | 0
0212-D-SUG | SUG | C0212 | 212-739R | 6.4761e-05 | 0.00014142 | 2025-04-09 | 2025-08-01 | 0 | 1.8 |  |  | 0 | 0
0212-F-SUG | SUG | C0212 | 212-739R | 6.4761e-05 | 0.00014142 | 2025-05-28 | 2025-08-04 | 0 | 0.4 |  |  | 0 | 0
0222-Q-SUG | SUG | C0222 | 222-1370R | 4.4716e-05 | 0.0028076 | 2025-04-17 | 2025-08-11 | 0 | 1.68 | 1.54 |  | 0 | 0
0210-B-SUG | SUG | C0210 | 210-172R | 0 | 0.00027968 | 2025-05-06 | 2025-08-21 | 0 | 1.6 |  |  | 0 | 0
0075-A-SUG | SUG | C0075 | 75-996R | 2.3879e-05 | 3.9133e-05 | 2025-06-30 | 2025-08-25 | 0 | 0.2 |  |  | 0 | 0
0445-P-SUG | SUG | C0445 | 445-1311R | 0.00054182 | 0.001547 | 2025-06-25 | 2025-09-02 | 0 | 1.35 |  |  | 0 | 0
0909-B-SUG | SUG | C0909 | 909-805R | 0.0060773 | 0.0069859 | 2025-07-29 | 2025-09-19 | 0 | 0.55 |  |  | 0 | 0
0220-K-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2025-07-23 | 2025-09-29 | 0 | 0.77 |  |  | 0 | 0
0210-D-SUG | SUG | C0210 | 210-9R | 0 | 6.4591e-05 | 2025-06-18 | 2025-10-03 | 0 | 2.2 | 2.5 |  | 0 | 0
0212-B-SUG | SUG | C0212 | 212-739R | 6.4761e-05 | 0.00014142 | 2025-05-08 | 2025-10-06 | 0 | 2.7 |  |  | 0 | 0
0220-P-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2025-08-11 | 2025-10-16 | 0 | 1.33 | 1.97 |  | 0 | 0
0971-Q-SUG | SUG | C0971 | 971-388R | 0.00026811 | 0.00027079 | 2025-09-03 | 2025-10-17 | 0 | 0.5 |  |  | 0 | 0
0231-A-SUG | SUG | C0231 | CB 231 | 2.5372e-05 | 0.00019092 | 2025-08-19 | 2025-10-24 | 0 | 1.01 |  |  | 0 | 0
0231-K-SUG | SUG | C0231 | 231-1635R | 3.6412e-06 | 0.00055793 | 2025-08-07 | 2025-10-30 | 0 | 1.26 |  |  | 0 | 0
0971-U-SUG | SUG | C0971 | 971-29R | 0.00040149 | 0.00040149 | 2025-09-03 | 2025-11-07 | 0 | 1 |  |  | 0 | 0
0220-V-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2025-07-22 | 2025-11-12 | 0 | 1.54 | 0.8 |  | 0 | 0
0220-T-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2025-07-23 | 2025-11-13 | 0 | 2.08 | 1.63 |  | 0 | 0
0971-M-SUG | SUG | C0971 | 971-383R | 0.00087604 | 0.00087779 | 2025-08-21 | 2025-11-13 | 0 | 1.3 |  |  | 0 | 0
0220-B2-SUG | SUG | C0220 | 220-298R, 220-294R | 0.00065801 | 0.0018868 | 2025-09-08 | 2025-11-13 | 0 | 0.75 |  |  | 0 | 0
0212-H-SUG | SUG | C0212 | 212-773R, 212-886R | 0.00016412 | 0.00033158 | 2025-06-09 | 2025-11-14 | 0 | 2.97 |  |  | 0 | 0
0237-AA-SUG | SUG | C0237 | 222-1401R, 237-30R | 0.00053794 | 0.0070124 | 2025-07-24 | 2025-11-14 | 0 | 5.93 |  |  | 0 | 0
0237-AB-SUG | SUG | C0237 | 237-2R | 4.8979e-06 | 0.00078332 | 2025-07-24 | 2025-11-14 | 0 | 3.24 |  |  | 0 | 0
0237-B-SUG | SUG | C0237 | 237-1765R, 237-17R | 2.2225e-05 | 0.0021647 | 2025-07-24 | 2025-11-14 | 0 | 3.5 |  |  | 0 | 0
0237-C-SUG | SUG | C0237 | 237-1765R | 0 | 0.0021647 | 2025-07-24 | 2025-11-14 | 0 | 2.74 |  |  | 0 | 0
0237-D-SUG | SUG | C0237 | 237-1765R | 0 | 0.0021647 | 2025-07-24 | 2025-11-14 | 0 | 5.89 |  |  | 0 | 0
0237-F-SUG | SUG | C0237 | 237-17R, CB RA3 | 2.2225e-05 | 0.0018932 | 2025-07-24 | 2025-11-14 | 0 | 3.74 |  |  | 0 | 0
0237-G-SUG | SUG | C0237 | 237-17R | 2.2225e-05 | 0.0018932 | 2025-07-24 | 2025-11-14 | 0 | 2.93 |  |  | 0 | 0
0237-H-SUG | SUG | C0237 | 237-17R, CB RA3, CB RA1 | 2.2225e-05 | 0.0018932 | 2025-07-24 | 2025-11-14 | 0 | 2.15 |  |  | 0 | 0
0237-I-SUG | SUG | C0237 | 237-17R, CB RA3, CB RA1 | 2.2225e-05 | 0.0018932 | 2025-07-24 | 2025-11-14 | 0 | 2.78 |  |  | 0 | 0
0237-K-SUG | SUG | C0237 | 237-17R, CB RA3 | 2.2225e-05 | 0.0018932 | 2025-07-24 | 2025-11-14 | 0 | 0.24 |  |  | 0 | 0
0237-L-SUG | SUG | C0237 | 237-17R, CB RA3, CB RA1, 236-1535 | 0.00049702 | 0.0018932 | 2025-07-24 | 2025-11-14 | 0 | 3.93 |  |  | 0 | 0
0237-N-SUG | SUG | C0237 | 222-1401R, 237-30R, 237-17R, CB RA1 | 0.00053794 | 0.0070124 | 2025-07-24 | 2025-11-14 | 0 | 3.29 |  |  | 0 | 0
0237-O-SUG | SUG | C0237 | 237-17R, 237-2R, CB RA1 | 2.2225e-05 | 0.0018932 | 2025-07-24 | 2025-11-14 | 0 | 3.41 |  |  | 0 | 0
0237-P-SUG | SUG | C0237 | 237-2R | 4.8979e-06 | 0.00078332 | 2025-07-24 | 2025-11-14 | 0 | 5.87 |  |  | 0 | 0
0237-Q-SUG | SUG | C0237 | 237-30R, 237-1761R, 237-2R | 0.00053794 | 0.0070124 | 2025-07-24 | 2025-11-14 | 0 | 6.18 |  |  | 0 | 0
0237-W-SUG | SUG | C0237 | 237-30R | 0.00053794 | 0.0070124 | 2025-07-24 | 2025-11-14 | 0 | 2.5 |  |  | 0 | 0
0237-X-SUG | SUG | C0237 | 237-30R | 0.00053794 | 0.0070124 | 2025-07-24 | 2025-11-14 | 0 | 4.55 |  |  | 0 | 0
0237-Z-SUG | SUG | C0237 | 237-30R | 0.00053794 | 0.0070124 | 2025-07-24 | 2025-11-14 | 0 | 3.35 |  |  | 0 | 0
0220-A-SUG | SUG | C0220 | 220-288R | 0 | 0.00013367 | 2025-07-28 | 2025-11-26 | 0 | 2.61 |  |  | 0 | 0
0212-G-SUG | SUG | C0212 | 212-773R | 0.00015064 | 0.00033158 | 2025-06-09 | 2025-12-02 | 0 | 3.41 |  |  | 0 | 0
0971-B-SUG | SUG | C0971 | 971-29R | 0.00040149 | 0.00040149 | 2025-09-03 | 2025-12-02 | 0 | 1.6 |  |  | 0 | 0
0971-C-SUG | SUG | C0971 | 971-29R | 0.00040149 | 0.00040149 | 2025-09-03 | 2025-12-02 | 0 | 1.6 |  |  | 0 | 0
0971-D-SUG | SUG | C0971 | 971-29R, 971-371R | 0.00040149 | 0.00040149 | 2025-09-03 | 2025-12-02 | 0 | 1.4 |  |  | 0 | 0
0971-E-SUG | SUG | C0971 | 971-381R, 971-29R | 0.00040149 | 0.00040149 | 2025-09-03 | 2025-12-03 | 0 | 1.4 |  |  | 0 | 0
0971-K-SUG | SUG | C0971 | 971-383R | 0.00087604 | 0.00087779 | 2025-09-03 | 2025-12-03 | 0 | 1.4 |  |  | 0 | 0
0971-R-SUG | SUG | C0971 | 971-383R | 0.00087604 | 0.00087779 | 2025-09-03 | 2025-12-03 | 0 | 1.3 |  |  | 0 | 0
0231-C-SUG | SUG | C0231 | 231-1635R, CB 231, CB 233 | 0.00012016 | 0.00055793 | 2025-08-19 | 2025-12-12 | 0 | 2.18 |  |  | 0 | 0
0212-E-SUG | SUG | C0212 | 212-739R | 6.4761e-05 | 0.00014142 | 2025-05-08 | 2025-12-15 | 0 | 4.2 |  |  | 0 | 0
0231-H-SUG | SUG | C0231 | 231-1635R | 3.6412e-06 | 0.00055793 | 2025-08-07 | 2025-12-15 | 0 | 2.21 |  |  | 0 | 0
0441-B-SUG | SUG | C0441 | 441-23R, 441-30R | 0.00046514 | 0.00087393 | 2025-10-06 | 2025-12-15 | 0 | 0.47 |  |  | 0 | 0
0445-E-SUG | SUG | C0445 | 445-17R | 6.329e-05 | 0.00014121 | 2025-07-09 | 2025-12-18 | 0 | 2.53 |  |  | 0 | 0
0222-S-SUG | SUG | C0222 | 222-1370R, 222-1401R | 4.4716e-05 | 0.006763 | 2025-08-26 | 2025-12-19 | 0 | 2.25 | 1.26 |  | 0 | 0
0231-L-SUG | SUG | C0231 | 231-1635R | 3.6412e-06 | 0.00055793 | 2025-08-07 | 2025-12-24 | 0 | 2.61 |  |  | 0 | 0
0971-J-SUG | SUG | C0971 | 971-383R | 0.00087604 | 0.00087779 | 2025-09-03 | 2025-12-29 | 0 | 2 |  |  | 0 | 0
0971-S-SUG | SUG | C0971 | 971-383R | 0.00087604 | 0.00087779 | 2025-09-03 | 2025-12-29 | 0 | 2.1 |  |  | 0 | 0
0971-F-SUG | SUG | C0971 | 971-381R, 971-371R | 0.00013658 | 0.00013658 | 2025-09-05 | 2025-12-31 | 0 | 1.9 |  |  | 0 | 0
0971-G-SUG | SUG | C0971 | 971-383R, 971-381R | 0.00087604 | 0.00087779 | 2025-09-05 | 2025-12-31 | 0 | 2.1 |  |  | 0 | 0
0971-H-SUG | SUG | C0971 | 971-381R | 4.8175e-06 | 4.8175e-06 | 2025-09-05 | 2025-12-31 | 0 | 2 |  |  | 0 | 0
0524-C-SUG | SUG | C0524 | 524-69R | 5.926e-06 | 0.0053589 | 2025-09-26 | 2025-12-31 | 0 | 1.53 |  |  | 0 | 0
0441-DUG-A-SUG | SUG | C0441 | 441-23R | 0.00036495 | 0.00072605 | 2024-05-23 | 2025-02-11 |  | 6.12 | 4.65