## Overview
SM 2.0 Program and Deployment Workpaper Overview
Workpaper Purpose and Overview
The purpose of this workpaper is to provide additional information and insights into cost tables referenced in Chapter 3 of the Testimony. This workpaper further breaks down the major components of Electric Meter Replacement, Gas Module Replacement, and Program Management costs, and their categorization as capital or operations and maintenance (O&M).
Workpaper Color Coding
Color | Explanation
Indicates that there are confidential numbers within the worksheet. Workpaper tabs with-C also denote that a workpaper is confidential.
Workpaper Tabs
Tab | Overview
Testimony Reference Tables | These tables reference the tables that exist in Chapter 3 of the testimony, that are relevant to Electric Meter Replacement, Gas Module Replacement, and Program Management.
Divider Tabs | These tabs divide the workpaper by its relevant table and section in the testimony. This workpaper has tabs for Electric Meter Replacement, Gas Module Replacement, and Program Management.
Master Tables | These tabs provide a summary of both capital and O&M costs by year for each major cost category. There is one for Electric Meter Replacement, Gas Module Replacement, and Program Management.
Cost Category Tables | These tabs provide a breakdown of each major cost category from the master tables by year for both capital and O&M. In addition to cost calculations, FTE calculations are provided for internal and purchased labor tabs.
Workpaper Tab Structure and Sections
Section | Overview
Section Summary | The section summary provides key information on the witness, and categories relevant to the numbers presented in the tables.
Actuals and Forecast | Each workpaper table is separated by actuals (which consist of costs incurred and FTEs in 2024-2025), and forecast, which consist of cost and FTE estimates from 2026-2031
Forecast Methodology, Assumptions and Notes | The forecast methodology, assumptions and notes section provides the reader with further context on the numbers presented in the tables, and any assumptions or methodologies used to produce the numbers.

## Testimony Table 3-1-C
The yellow highlighted data in this document is CONFIDENTIAL – Pursuant to Public Utilities (PU) Code Section 583, Decision (D.) 21-09-020, and General Order (GO) No. 66-D. The detailed justification is provided in Attachment A of the accompanying Confidentiality Declaration.
Summary of SM 2.0 Escalated Direct Costs ($M)
SM 2.0 Escalated Direct Cost Categories | Total | Capital | O&M | Work Paper Reference
Electric Meter Replacement |  |  | 8660344.5236 | Testimony Table 3-2
Gas Module Replacement |  |  | 23905680.7797 | Testimony Table 3-3
Foundational Technology | 122251996.9391 | 110457438.1003 | 11794558.8388 | Refer to Chapter 3 - Workpaper 2 - Foundational and NextGen Technology Workpapers
NextGen Technology | 42670987.6017 | 37148663.8882 | 5522323.7135 | Refer to Chapter 3 - Workpaper 2 - Foundational and NextGen Technology Workpapers
Program Management | 41788134.0786 | 38308284.0486 | 3479850.03 | Testimony Table 3-6
SM 2.0 Escalated Direct Cost Subtotal | 701909901.9095 | 648547144.0239 | 53362757.8856
Contingency | 60069514.6549 | 54265154.1246 | 5804360.5302
SM 2.0 Escalated Direct Cost Total | 761979416.5644 | 702812298.1486 | 59167118.4158

## Electric Meter Replacement>>
Page left blank intentionally

## Testimony Table 3-2-C
The yellow highlighted data in this document is CONFIDENTIAL – Pursuant to Public Utilities (PU) Code Section 583, Decision (D.) 21-09-020, and General Order (GO) No. 66-D. The detailed justification is provided in Attachment A of the accompanying Confidentiality Declaration.
Summary of Electric Meters and Installation Costs
Cost Category | Total | Capital | O&M | Work Paper Reference
Hardware |  |  | 0 | WP 3.2.1 (Capital and O&M)
Install | 80577845.3522 | 80577845.3522 | 0 | WP 3.2.1 (Capital and O&M)
Removal | 8953093.928 | 0 | 8953093.928 | WP 3.2.1 (Capital and O&M)
Testing & Disposal | 1184488.3112 | 1477237.7156 | -292749.4044 | WP 3.2.1 (Capital and O&M)
Warehouse | 10000000 | 10000000 | 0 | WP 3.2.1 (Capital and O&M)
Total Electric Meters and Installation Costs |  |  | 8660344.5236

## WP 3.2.1-C (Capital and O&M)
The yellow highlighted data in this document is CONFIDENTIAL – Pursuant to Public Utilities (PU) Code Section 583, Decision (D.) 21-09-020, and General Order (GO) No. 66-D. The detailed justification is provided in Attachment A of the accompanying Confidentiality Declaration.
Overall Summary For Exhibit No : SDG&E-03
Area | SM 2.0 Program and Deployment - - Electric Meter Replacement Costs
Witness | David Thai
Category | 3.2 Capital & O&M Costs - Electric Meter Replacement
Sub-Category 1 | 3.2.1 Master Summary Table
Electric Meter Replacement - Capital
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2024: Actual ($); 2026: Forecast ($) |  | Notes | Reference
1 | Hardware
2 | Install | 0 | 0 | 0 | 4481325.046 | 19235358.4733 | 31707005.521 | 23639734.4029 | 1514421.909 | 80577845.3522 | Costs related to the number of meters being installed per year. | -
3 | Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
4 | Testing & Disposal | 0 | 0 | 772394.8275 | 115878.4994 | 175810.882 | 231581.7859 | 181571.7208 | 0 | 1477237.7156 | See more details on the testing tab | WP 3.2.2
5 | Warehouse | 0 | 0 | 0 | 1000000 | 3000000 | 3000000 | 3000000 | 0 | 10000000 |  | -
Total Electric Meters and Installation Costs (Capital)
Electric Electric Meter Replacement - O&M
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2024: Actual ($); 2026: Forecast ($) |  | Notes | Reference
1 | Hardware | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
2 | Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
3 | Removal | 0 | 0 | 0 | 497925.0051 | 2137262.0526 | 3523000.6134 | 2626637.1559 | 168269.101 | 8953093.928 | Costs related to the number of meters being installed per year. | -
4 | Testing & Disposal | 0 | 0 | 0 | -17658.3306 | -69843.8708 | -119503.6212 | -85743.5818 | 0 | -292749.4044 | SDG&E will receive a recyling credit for its electric meters
5 | Warehouse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
| Total Electric Meters and Installation Costs (O&M) | 0 | 0 | 0 | 480266.6745 | 2067418.1818 | 3403496.9922 | 2540893.5741 | 168269.101 | 8660344.5236 |  | -
Forecast Methodology/Assumptions | bar: 2024 to 2030
1) The forecast are based on projected electric meters installations of: 2027: 132,363 2028: 388,681 2029: 653,596 2030: 459,858
2) Installation/removal costs are split 90/10. Install costs are capital and removal costs are conisdered O&M
3) Costs are direct, escalated cost.

## WP 3.2.2(Electric - Testing)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment - - Electric Meter Replacement Costs
Witness | David Thai
Category | 3.2 Capital & O&M Costs - Electric Meter Replacement
Sub-Category 1 | 3.2.2 Electric Meter Testing & Disposal Costs
Electric Meter Testing & Disposal Costs - Capital
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2024: Actual (FTEs); 2026: Forecast (FTEs) |  | Notes | Reference
1 | FAT - Electric Meter Testing | 0 | 0 | 6.875 | 0 | 0 | 0 | 0 | 0 | 6.875 | FAT testing for all device types from the vendor | -
2 | Electric - Residential | 0 | 0 | 0 | 0.71806 | 0.77778 | 1.225 | 0.77778 | 0 | 3.4986 | Ongoing sample testing for devices through out the deployment | -
3 | Electric - C&I | 0 | 0 | 0 | 0.29167 | 0.72917 | 0.72917 | 0.72917 | 0 | 2.4792 | Ongoing sample testing for devices through out the deployment | -
| Total FTEs | 0 | 0 | 6.875 | 1.0097 | 1.5069 | 1.9542 | 1.5069 | 0 | 12.8528 |  | -
| Total Electric Testing Costs | 0 | 0 | 772394.8275 | 115878.4994 | 175810.882 | 231581.7859 | 181571.7208 | 0 | 1477237.7156 |  | -
Forecast Methodology/Assumptions | bar: 2024 to 2029
1) Factory Acceptance Testing (FAT) is conducted in 2026 to validate the accuracy and compliance of new electric meters.
2) Sample testing of devices will be conducted between 2027 and 2030 as part of the device deployment process.

## Gas Module Replacement >>
Page left blank intentionally

## Testimony Table 3-3-C
The yellow highlighted data in this document is CONFIDENTIAL – Pursuant to Public Utilities (PU) Code Section 583, Decision (D.) 21-09-020, and General Order (GO) No. 66-D. The detailed justification is provided in Attachment A of the accompanying Confidentiality Declaration.
Summary of Gas Modules and Installation Costs
Cost Category | Total | Capital | O&M | Capital Work Paper Reference
Hardware |  |  | 0 | WP 3.3.1 (Capital and O&M)
Install | 21778550.6695 | 21778550.6695 | 0 | WP 3.3.1 (Capital and O&M)
Removal | 21597663.2479 | 0 | 21597663.2479 | WP 3.3.1 (Capital and O&M)
Testing & Disposal | 3712000.2468 | 1403982.715 | 2308017.5318 | WP 3.3.1 (Capital and O&M)
Total Gas Modules and Installation Costs |  |  | 23905680.7797

## WP 3.3.1-C (Capital & O&M)
The yellow highlighted data in this document is CONFIDENTIAL – Pursuant to Public Utilities (PU) Code Section 583, Decision (D.) 21-09-020, and General Order (GO) No. 66-D. The detailed justification is provided in Attachment A of the accompanying Confidentiality Declaration.
Overall Summary For Exhibit No : SDG&E-03
Area | SM 2.0 Program and Deployment - - Gas Module Replacement Costs
Witness | David Thai
Category | 3.3 Capital & O&M Costs - Gas Module Replacement
Sub-Category 1 | 3.3.1 Master Summary Table
Gas Modules and Installation - Capital
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2024: Actual ($); 2026: Forecast ($) |  | Notes | Reference
1 | Hardware | [10 empty] | -
2 | Install | 0 | 0 | 0 | 736498 | 4986515.268 | 8739280.586 | 6899002.2334 | 417254.5822 | 21778550.6695 | Costs related to the number of modules being installed per year. | -
3 | Removal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
4 | Testing & Disposal | 0 | 0 | 1091651.3562 | 35703.9668 | 90741.1004 | 92171.8551 | 93714.4365 | 0 | 1403982.715 | See more details on the testing tab | WP 3.3.2
Total Gas Modules and Installation Costs (Capital)
Gas Modules and Installation - O&M
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2024: Actual ($); 2026: Forecast ($) |  | Notes | Reference
1 | Hardware | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
2 | Install | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
3 | Removal | 0 | 0 | 0 | 555610.5784 | 4986515.268 | 8739280.586 | 6899002.2334 | 417254.5822 | 21597663.2479 |  | -
4 | Testing & Disposal | 0 | 0 | 0 | 72246.2336 | 532831.9675 | 967900.0739 | 735039.2569 | 0 | 2308017.5318
5 | Gridstream Mobile Radio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -
| Total Gas Modules and Installation Costs (O&M) | 0 | 0 | 0 | 627856.8119 | 5519347.2354 | 9707180.6599 | 7634041.4903 | 417254.5822 | 23905680.7797 |  | -
Forecast Methodology/Assumptions
1) The forecast are based on projected gas module installations of: 2027: 30,904 2028: 224,038 2029: 399,968 2030: 297,851
2) Installation/removal costs are split 50/50. Install costs are capital.
3) Costs are direct, escalated cost.

## WP 3.3.2 (Gas -Testing)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment - - Gas Module Replacement Costs
Witness | David Thai
Category | 3.3 Capital & O&M Costs - Gas Module Replacement
Sub-Category 1 | 3.3.2 Gas Module Testing Costs
Gas Module Testing - Internal Labor - Capital
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2025: Actual (FTEs); 2027: Forecast (FTEs) |  | Notes | Reference
1 | FAT - Gas Module Testing |  | 0 | 9.7167 | 0 | 0 | 0 | 0 | 0 | 9.7167 | FAT testing for all device types from the vendor | -
2 | Gas Module Testing |  | 0 | 0 | 0.31111 | 0.77778 | 0.77778 | 0.77778 | 0 | 2.6444 | Ongoing sample testing for devices through out the deployment | -
| Total FTEs |  | 0 | 9.7167 | 0.31111 | 0.77778 | 0.77778 | 0.77778 | 0 | 12.3611 |  | -
| Total Gas Testing Costs |  | 0 | 1091651.3562 | 35703.9668 | 90741.1004 | 92171.8551 | 93714.4365 | 0 | 1403982.715 |  | -
Forecast Methodology/Assumptions
1) Factory Acceptance Testing (FAT) is conducted in 2026 to validate the accuracy and compliance of new vendor gas modules and electric meters.
2) Sample testing of devices will be conducted between 2027 and 2030 as part of the device deployment process.

## Program Management >>
Page left blank intentionally

## Testimony Table 3-6
Summary of Program Costs
Cost Category | Total | Capital | O&M | Capital Work Paper Reference
Program Management | 8909734.3593 | 5429884.3293 | 3479850.03 | WP 3.6.1 (Capital and O&M)
Training and Change Management | 3166811.9164 | 3166811.9164 | 0 | WP 3.6.1 (Capital and O&M)
ME&O | 7272502.008 | 7272502.008 | 0 | WP 3.6.1 (Capital and O&M)
Business Implementation | 4555181.5446 | 4555181.5446 | 0 | WP 3.6.1 (Capital and O&M)
Deployment | 17883904.2503 | 17883904.2503 | 0 | WP 3.6.1 (Capital and O&M)
Total Program Costs | 41788134.0786 | 38308284.0486 | 3479850.03

## WP 3.6.1 (Capital and O&M)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment- - Program Management Costs
Witness | David Thai
Category | 3.6 Capital & O&M Costs - Program Management
Sub-Category 1 | 3.6.1 Master Summary Table
Program - Capital
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2024: Actual ($); 2026: Forecast ($) |  | Notes | Reference
1 | Project Management | 0 | 2959726.9247 | 1117198.9833 | 897010.6018 | 455947.8195 | 0 | 0 | 0 | 5429884.3293 |  | WP 3.6.2
2 | Training and Change Management | 0 | 0 | 2217053.5899 | 949758.3265 | 0 | 0 | 0 | 0 | 3166811.9164 |  | WP 3.6.3
3 | Marketing, Outreach and Education | 0 | 0 | 665824.9762 | 684857.866 | 1601528.9734 | 2442032.7125 | 1878257.4799 | 0 | 7272502.008 |  | WP 3.6.4
4 | Business Implementation | 0 | 0 | 3318136.5848 | 1069568.9628 | 167475.9971 | 0 | 0 | 0 | 4555181.5446 |  | WP 3.6.5
5 | Deployment | 0 | 0 | 2320647.1496 | 3471411.2966 | 4151677.4724 | 4330922.962 | 3609245.3697 | 0 | 17883904.2503 |  | WP 3.6.6
| Total Program Costs (Capital) | 0 | 2959726.9247 | 9638861.2837 | 7072607.0537 | 6376630.2624 | 6772955.6745 | 5487502.8496 | 0 | 38308284.0486
Program - O&M
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Description | 2024: Actual ($); 2026: Forecast ($) |  | Notes | Reference
1 | Project Management | 0 | 3479850.03 | 0 | 0 | 0 | 0 | 0 | 0 | 3479850.03
2 | Training and Change Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Customer Engagement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Business Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Deployment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Program Costs (O&M) | 0 | 3479850.03 | 0 | 0 | 0 | 0 | 0 | 0 | 3479850.03 |  | -

## WP 3.6.2 (Program - PMO)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment - - Program Management Costs
Witness | David Thai
Category | 3.6 Capital & O&M Costs - Program Management
Sub-Category 1 | 3.6.2 Project Management Costs (Internal Labor and Purchased Labor)
Project Management - Capital
|  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Category | Description | 2024: Actual (FTEs); 2026: Forecasted (FTEs) |  | Notes | Reference
1 | Internal Labor | SDGE PMO Contract Admin Analyst | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 2.5
2 |  | Project Managers | 0 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 |  | -
3 |  | Project Advisor | 0 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  | -
4 |  | Software Engineer | 0 | 0.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | -
5 |  | Business Analyst | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 |  | -
6 | Purchased Labor | PMO - Project Coordinator | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 2.5 |  | -
7 |  | PMO Program Manager | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 2.5 |  | -
8 |  | SM 2.0 Solution Validation Support | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | -
|  | Total FTEs | 0 | 3.68 | 3.5 | 3 | 1.5 | 0 | 0 | 0 | 11.8 |  | -
|  | Total Project Management Costs | 0 | 2959726.9247 | 1117198.9833 | 897010.6018 | 455947.8195 | 0 | 0 | 0 | 5429884.3293 |  | -
Forecast Methodology/Assumptions | bar: 2024 to 2030
1) FTEs are calculated as 1920 hours per year.

## WP 3.6.3 (Program - Change)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment - - Program Management Costs
Witness | David Thai
Category | 3.6 Capital & O&M Costs - Program Management
Sub-Category 1 | 3.6.3 Change Management Costs (Internal Labor and Purchased Labor)
Training and Change Management - Capital
|  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Category | Description | 2024: Actual (FTEs); 2026: Forecast (FTEs) |  | Notes | Reference
1 | Internal Labor | Change Champion Execution | 0 | 0 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0.66667 |  | -
2 |  | Internal Communications Delivery Lead | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 |  | -
3 |  | SDGE Change Management Leads | 0 | 0 | 1 | 0.75 | 0 | 0 | 0 | 0 | 1.75 |  | -
4 |  | SDGE Training & Business Capabilities Leads | 0 | 0 | 0.75 | 0.83333 | 0 | 0 | 0 | 0 | 1.5833 |  | -
5 |  | Training & Business Capabilities Analysts | 0 | 0 | 1.5 | 1.6667 | 0 | 0 | 0 | 0 | 3.1667 |  | -
6 |  | Training Developers | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 1.5 |  | -
7 | Purchased Labor | Change Management Manager | 0 | 0 | 1 | 0.75 | 0 | 0 | 0 | 0 | 1.75 |  | -
8 |  | Change Management Sr Analysts (CIA) | 0 | 0 | 1.8333 | 0 | 0 | 0 | 0 | 0 | 1.8333 |  | -
|  | Total FTEs | 0 | 0 | 9.25 | 5 | 0 | 0 | 0 | 0 | 14.25 |  | -
|  | Total Change Management Costs | 0 | 0 | 2217053.5899 | 949758.3265 | 0 | 0 | 0 | 0 | 3166811.9164 |  | -
Forecast Methodology/Assumptions
1) FTEs are calculated as 1920 hours per year.

## WP 3.6.4 (Program - MEO)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment - - Program Management Costs
Witness | David Thai
Category | 3.6 Capital & O&M Costs - Program Management
Sub-Category 1 | 3.6.4 Marketing Engagement and Outreach (MEO) Costs (Internal Labor and Non-Labor)
Marketing Engagement & Outreach - Internal Labor - Capital
|  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Category | Description | 2024: Actual (FTEs); 2026: Forecast (FTEs) |  | Notes | Reference
1 | Internal Labor | SDGE Community & Customer Engagement Lead | 0 | 0 | 1.8 | 1 | 0.5 | 0 | 0 | 0 | 0.83333 |  | -
2 |  | SDGE Marketing Lead | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0.83333 |  | -
| - | Total FTEs | 0 | 0 | 2.6333 | 1 | 0.5 | 0 | 0 | 0 | 1.6667 |  | -
| - | Total Marketing Engagement & Outreach Labor Costs | 0 | 0 | 358391.9132 | 137285.2134 | 69781.6655 | 0 | 0 | 0 | 565458.7921 |  | -
Forecast Methodology/Assumptions
1) FTEs are calculated as 1920 hours per year.
Marketing Engagement & Outreach - Non-Labor - Capital
|  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Category | Description | 2024: Actual ($); 2026: Forecast ($) |  | Notes | Reference
1 | Non-Labor | Letter Costs | 0 | 0 | 0 | 233532.7269 | 1212496.1884 | 2117747.8209 | 1548545.3799 | 0 | 5112322.1161 | Costs to support customer communication around deployment schedules | -
2 |  | Vendor Costs | 0 | 0 | 307433.063 | 314039.9257 | 319251.1195 | 324284.8917 | 329712.1 | 0 | 1594721.0999 |  | -
| - | Total Marketing Engagement & Outreach Non-Labor Costs | 0 | 0 | 307433.063 | 547572.6526 | 1531747.3079 | 2442032.7125 | 1878257.4799 | 0 | 6707043.2159 |  | -
Forecast Methodology/Assumptions
1) Letter and vendor costs will support engagement/communication during deployment.
2) Assumptions for customer contact (2 mails, 5 emails, 5 text and 5 voice calls ) will be initiated per customer install

## WP 3.6.5 (Program - BI)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment- - Program Management Costs
Witness | David Thai
Category | 3.6 Capital & O&M Costs - Program Management
Sub-Category 1 | 3.6.5 Business Integration Costs (Internal Labor and Purchased Labor)
Business Integration - Internal/Purchased Labor - Capital
|  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Category | Description | 2024: Actual (FTEs); 2026: Forecast (FTEs) |  | Notes | Reference
1 | Internal Labor | SDGE SMRs | 0 | 0 | 2.4 | 2.4 | 1.2 | 0 | 0 | 0 | 6 |  | -
2 |  | SDGE BPD Senior Analyst | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0.83333 |  | -
3 |  | SDGE Business Testing Lead | 0 | 0 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5 |  | -
4 |  | SDGE Testing Execution Analyst | 0 | 0 | 0.5 | 0.83333 | 0 | 0 | 0 | 0 | 1.3333 |  | -
5 | Purchased Labor | BPD Analysts | 0 | 0 | 3.1667 | 0 | 0 | 0 | 0 | 0 | 3.1667 |  | -
6 |  | BPD Leads | 0 | 0 | 1.6667 | 0 | 0 | 0 | 0 | 0 | 1.6667 |  | -
7 |  | BPD Manager | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0.83333 |  | -
8 |  | Business Readiness Lead | 0 | 0 | 0.41667 | 1 | 0 | 0 | 0 | 0 | 1.4167 |  | -
| - | Total FTEs | 0 | 0 | 10.3167 | 5.2333 | 1.2 | 0 | 0 | 0 | 16.75 |  | -
| - | Total Business Implementation Costs | 0 | 0 | 3318136.5848 | 1069568.9628 | 167475.9971 | 0 | 0 | 0 | 4555181.5446 |  | -
Forecast Methodology/Assumptions
1) FTEs are calculated as 1920 hours per year.

## WP 3.6.6 (Program - Deployment)
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment - - Program Management Costs
Witness | David Thai
Category | 3.6 Capital & O&M Costs - Program Management
Sub-Category 1 | 3.6.6 Deployment Costs (Internal Labor and Purchased Labor)
Deployment - Internal/Purchased Labor - Capital
|  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Line No. | Category | Description | 2024: Actual (FTEs); 2026: Forecast (FTEs) |  | Notes | Reference
1 | Internal Labor | Deployment Planning Lead | 0 | 0 | 1 | 0.25 | 0 | 0 | 0 | 0 | 1.25 |  | -
2 |  | Deployment Planning Analysts | 0 | 0 | 2 | 0.75 | 0.5 | 0.75 | 0.75 | 0 | 4.75 |  | -
3 |  | Deployment Management Exception Handling Analysts | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 7 |  | -
4 |  | Deployment Mgmt Field Supervisor / QA Lead | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
5 |  | Deployment Mgmt Inventory Lead | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
6 |  | Deployment Mgmt Lead | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
7 |  | Deployment Mgmt Network Management | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
8 |  | Deployment Mgmt Performance Reporting Analyst | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
9 |  | Deployment Mgmt Process Improvement Analyst | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
10 |  | Deployment Mgmt Program Communications | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
11 |  | Deployment Mgmt Scheduling/Forecast Analyst | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
12 |  | Operations Data Analysts | 0 | 0 | 0.5 | 1.5 | 2.25 | 2.5 | 3 | 0 | 9.75 |  | -
13 |  | Operations Lead | 0 | 0 | 0 | 0.25 | 0.5 | 0.5 | 1 | 0 | 2.25 |  | -
14 |  | Operations Systems Analysts | 0 | 0 | 0.5 | 1.25 | 1 | 1 | 1 | 0 | 4.75 |  | -
15 |  | Operations Engineering Analysts | 0 | 0 | 0.5 | 0.5 | 0.25 | 0.5 | 1 | 0 | 2.75 |  | -
16 | Purchased Labor | Deployment Planning Analysts | 0 | 0 | 2 | 0.25 | 0 | 0 | 0 | 0 | 2.25 |  | -
17 |  | Deployment Planning Functional Lead | 0 | 0 | 1 | 0.25 | 0 | 0 | 0 | 0 | 1.25 |  | -
18 |  | Deployment Management Exception Handling Analyst | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 0 | 3.5 |  | -
19 |  | Operations Functional Lead | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 3 |  | -
20 |  | Operations Data Analysts | 0 | 0 | 0.5 | 1.25 | 1 | 1 | 0 | 0 | 3.75 |  | -
21 |  | Operations System Analysts | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 4 |  | -
| - | Total FTEs | 0 | 0 | 8 | 13.75 | 18.5 | 19.25 | 18.75 | 0 | 78.25 |  | -
| - | Total Deployment Management Costs | 0 | 0 | 2320647.1496 | 3471411.2966 | 4151677.4724 | 4330922.962 | 3609245.3697 | 0 | 17883904.2503 |  | -
Forecast Methodology/Assumptions
1) FTEs are calculated as 1920 hours per year.