## Depreciation (hidden)
Useful life | 15
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Depreciation Curve | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667%

## WP 3.10.1 Delayed Deployment
The yellow highlighted data in this document is CONFIDENTIAL – Pursuant to Public Utilities (PU) Code Section 583, Decision (D.) 21-09-020, and General Order (GO) No. 66-D. The detailed justification is provided in Attachment A of the accompanying Confidentiality Declaration.
Overall Summary For Exhibit No : SDG&E-
Area | SM 2.0 Program and Deployment -- Delayed Deployment Costs
Witness | David Thai
Category | 3.10.1 Delayed Deployment Cost Analysis
Purpose |  | This workpaper has been prepared to document the methodology applied in conducting the delayed deployment analysis. Specifically, Tables 1.03 and 1.04 present the escalation factors utilized to calculate the projected cost impacts under the proposed scenarios, assuming program delays of five and four years, respectively
1.01 | Summary Table
|  |  | Proposed Scenario | 4 Year Delay |  |  | 5 Year Delay
| Line No. |  |  | SM 2.0 (Escalated) | Incremental 1.0 | Total | SM 2.0 (Escalated) | Incremental 1.0 | Total
| 1 | Electric Meter Replacement
| 2 | Gas Module Replacement
| 3 | Foundational Technology | 122251996.9391 | 131641698.1437 | 26095770.1604 | 157737468.3041 | 133900124.5415 | 30927569.3661 | 164827693.9076
| 4 | NextGen Technology | 42670987.6017 | 46030964.7828 | 0 | 46030964.7828 | 46972408.3553 | 0 | 46972408.3553
| 5 | Program Management | 41788134.0786 | 49686709 | 0 | 49686709 | 50544170 | 0 | 50544170
| 6 | Contingency | 60069514.6549 | 64722048.5101 | 17103741.3653 | 81825789.8754 | 65817349.4505 | 24949048.5067 | 90766397.9572
| 7 | Total | 761979416.14 | 833279888.4366 | 188141155.0186 | 1021421043.4552 | 848870231.3473 | 274439533.5736 | 1123309764.9209
1.02 | Original Model Inflation
| https://www.ceicdata.com/en/united-states/consumer-price-index-urban-projection-congressional-budget-office/cbo-projection-consumer-price-index-urban-yoy |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046
| Electric Meter Escalation | % | 0% | 0% | 0% | 0% | 1.861% | 1.758% | 1.826% | 2.095% | 2.218% | 2.225% | 2.199% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218%
| Gas Module Escalation | % | 0% | 0% | 0% | 0% | 1.113% | 1.536% | 1.821% | 1.797% | 1.699% | 1.799% | 1.93% | 1.705% | 1.707% | 1.709% | 1.71% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712%
| Electric Plant Escalation | % | 0% | 3.557% | 3.146% | 2.423% | 1.861% | 1.758% | 1.826% | 2.095% | 2.218% | 2.225% | 2.199% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218%
| Gas Plant Escalation | % | 0% | 0.716% | 0.5217% | 0.4142% | 1.113% | 1.536% | 1.821% | 1.797% | 1.699% | 1.799% | 1.93% | 1.705% | 1.707% | 1.709% | 1.71% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712%
| Union Labor Escalation | % | 0% | 4% | 3.352% | 3.051% | 2.863% | 2.682% | 2.762% | 2.897% | 2.864% | 2.843% | 2.881% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864%
| Other Capital Escalation | % | 0% | 2.478% | 2.149% | 1.659% | 1.577% | 1.674% | 1.824% | 1.982% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| SWHW AMI Vendor | % | 0% | 0% | 0% | 0% | 1.577% | 1.674% | 1.824% | 1.982% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| SWHW Other Vendor | % | 0% | 2.478% | 2.149% | 1.659% | 1.577% | 1.674% | 1.824% | 1.982% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| O&M Escalation | % | 0% | 2.089% | 1.774% | 1.734% | 1.751% | 1.978% | 2.102% | 2.148% | 2.132% | 2.14% | 2.173% | 2.133% | 2.134% | 2.134% | 2.134% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135%
1.03 | 5 Year Change | bar: 2031
| https://www.ceicdata.com/en/united-states/consumer-price-index-urban-projection-congressional-budget-office/cbo-projection-consumer-price-index-urban-yoy |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046
| Equivalent Year: |  | 2025 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051
| Electric Meter Escalation | % | 0% | 15.47% | 0% | 0% | 2.225% | 2.199% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218%
| Gas Module Escalation | % | 0% | 6.272% | 0% | 0% | 1.799% | 1.93% | 1.705% | 1.707% | 1.709% | 1.71% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712%
| Electric Plant Escalation | % | 0% | 15.47% | 2.095% | 2.218% | 2.225% | 2.199% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218%
| Gas Plant Escalation | % | 0% | 6.272% | 1.797% | 1.699% | 1.799% | 1.93% | 1.705% | 1.707% | 1.709% | 1.71% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712%
| Union Labor Escalation | % | 0% | 20.22% | 2.897% | 2.864% | 2.843% | 2.881% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864%
| Other Capital Escalation | % | 0% | 11.91% | 1.982% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| SWHW AMI Vendor | % | 0% | 11.91% | 0% | 0% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| SWHW Other Vendor | % | 0% | 11.91% | 1.982% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| O&M Escalation | % | 0% | 11.99% | 2.148% | 2.132% | 2.14% | 2.173% | 2.133% | 2.134% | 2.134% | 2.134% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135%
1.04 | 4 Year Change
| https://www.ceicdata.com/en/united-states/consumer-price-index-urban-projection-congressional-budget-office/cbo-projection-consumer-price-index-urban-yoy |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046
| Equivalent Year: |  | 2025 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
| Electric Meter Escalation | % | 0% | 13.4% | 0% | 0% | 2.218% | 2.225% | 2.199% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218%
| Gas Module Escalation | % | 0% | 4.372% | 0% | 0% | 1.699% | 1.799% | 1.93% | 1.705% | 1.707% | 1.709% | 1.71% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712%
| Electric Plant Escalation | % | 0% | 13.4% | 1.826% | 2.095% | 2.218% | 2.225% | 2.199% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218% | 2.218%
| Gas Plant Escalation | % | 0% | 4.372% | 1.821% | 1.797% | 1.699% | 1.799% | 1.93% | 1.705% | 1.707% | 1.709% | 1.71% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712% | 1.712%
| Union Labor Escalation | % | 0% | 16.99% | 2.762% | 2.897% | 2.864% | 2.843% | 2.881% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864% | 2.864%
| Other Capital Escalation | % | 0% | 9.904% | 1.824% | 1.982% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| SWHW AMI Vendor | % | 0% | 9.904% | 0% | 0% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| SWHW Other Vendor | % | 0% | 9.904% | 1.824% | 1.982% | 2.021% | 2.063% | 2.097% | 2.023% | 2.024% | 2.025% | 2.025% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026% | 2.026%
| O&M Escalation | % | 0% | 9.68% | 2.102% | 2.148% | 2.132% | 2.14% | 2.173% | 2.133% | 2.134% | 2.134% | 2.134% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135% | 2.135%
1.05 | Notes:
1. First year of both models is compunded for the delayed initial years from the originally proposed model.
2. For both gas & electric AMI vendors, escalation doesn't impact for the first 2 years, similar to the assumptions made in the proposed model.

## Updated IT Assumption (hidden)
Option B | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
One-time move to Itron Cloud (OWCE) | 2234096.8 | 830213.5922 |  |  | 0
Itron Cloud "run costs" hosting for OWCE |  | 4384059.0558 | 4384059.0558 | 4384059.0558 | 4384059.0558 | 4384059.0558 | 4384059.0558 | 4384059.0558
Subtract costs for 1.0 baseline costs for systems otherwise replaced with 2.0 |  | -800000 | -800000 | -800000 | -800000 | -800000 | -800000 | -800000
Total | 2234096.8 | 4414272.648 | 3584059.0558 | 3584059.0558 | 3584059.0558 | 3584059.0558 | 3584059.0558 | 3584059.0558 | << EY Added
*** costs shown are in 2026 dollars, and should be escalated to get to the appropriate year 3% per year per RFQ.
DO NOT INCLUDE
OWCE maintenance costs - these are not expected to change significantly
Offset of datacenter hardware costs that we don't have to buy?
Did not calculate a reduction in the costs over time due to fewer endpoints
For Option 1 - costs above extend through 2035 (at 25% for a half year)
For Option 2 - costs above extend through 2036 (at 25% for a half year)
OPTION 1:
OPTION 2:

## Dileep_Rough (hidden)
|  |  | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | A | B
Hardware
| Meter |  |  | 84000 | 108000 | 132000 | 152000 | 244000
| Rate | 111.58 |  | 9372720 | 12050640 | 14728560 | 16960160 | 27225520 | 53112080 | 80337600
| Module |  |  | 28000 | 54000 | 105000 | 184000 | 161000
| Rate | 59.69 |  | 1671320 | 3223260 | 6267450 | 10982960 | 9610090 | 22144990 | 31755080
Network
Total |  |  |  | 11044040 | 15273900 | 20996010 | 27943120 | 36835610 | 75257070 | 112092680
Deployment
| Meter | 44 |  | 3696000 | 4752000 | 5808000 | 6688000 | 10736000
| Module | 27 |  | 756000 | 1458000 | 2835000 | 4968000 | 4347000
Total |  |  |  | 4452000 | 6210000 | 8643000 | 11656000 | 15083000 | 30961000 | 46044000
IT |  |  |  | 5968718.9321 | 7232687.5392 | 5968718.9321 | 7232687.5392 | 5968718.9321 | 26402812.9426 | 32371531.8747
Network |  |  |  | 1186508.1263 | 1186508.1263 | 1186508.1263 | 1186508.1263 | 1186508.1263 | 4746032.5053 | 5932540.6317
Total Cost | [8 empty] | 137366915.4479 | 196440752.5063