## Business Unit Reporting (hidden)
Group | Program | Desc | Type | Period | Month | Service Accounts | Ex Ante Estimated MW
0 | BIP - (20 minute option) |  | c | 1 | Jan | 4 | 0.59176
1 | CPP-D (Large and Medium customers) |  | c | 1 | Jan | 14093 | 1.973
2 | Armed Forces Pilot | Active but no participants | c | 1 | Jan | #N/A | #N/A
3 | Over Generation Pilot |  | c | 1 | Jan | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 1 | Jan | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 1 | Jan | 17376 | 0.00019548
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 1 | Jan | 704 | 0.00025596
7 | AC Saver Day-Of Residential | Switches | r | 1 | Jan | 10225 | 0
8 | AC Saver Day-Of Commercial | Switches | c | 1 | Jan | 2652 | 0
9 | CBP - Day-Ahead |  | c | 1 | Jan | 0 | 0
10 | CBP - Day-Of |  | c | 1 | Jan | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 1 | Jan | 111812 | 1.1181
12 | TOU-DR-P Voluntary Residential |  | r | 1 | Jan | 17743 | 0.68664
0 | BIP - (20 minute option) |  | c | 2 | Feb | 4 | 0.49343
1 | CPP-D (Large and Medium customers) |  | c | 2 | Feb | 14068 | 1.9695
2 | Armed Forces Pilot | Active but no participants | c | 2 | Feb | #N/A | #N/A
3 | Over Generation Pilot |  | c | 2 | Feb | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 2 | Feb | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 2 | Feb | 17278 | 4.5015e-05
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 2 | Feb | 704 | 5.9277e-05
7 | AC Saver Day-Of Residential | Switches | r | 2 | Feb | 10185 | 0
8 | AC Saver Day-Of Commercial | Switches | c | 2 | Feb | 2648 | 0
9 | CBP - Day-Ahead |  | c | 2 | Feb | 0 | 0
10 | CBP - Day-Of |  | c | 2 | Feb | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 2 | Feb | 111739 | 1.1174
12 | TOU-DR-P Voluntary Residential |  | r | 2 | Feb | 18502 | 0.63577
0 | BIP - (20 minute option) |  | c | 3 | Mar | 0 | 0.6167
1 | CPP-D (Large and Medium customers) |  | c | 3 | Mar | 13616 | 0
2 | Armed Forces Pilot | Active but no participants | c | 3 | Mar | #N/A | #N/A
3 | Over Generation Pilot |  | c | 3 | Mar | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 3 | Mar | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 3 | Mar | 17050 | 0
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 3 | Mar | 268 | 0
7 | AC Saver Day-Of Residential | Switches | r | 3 | Mar | 10091 | 0
8 | AC Saver Day-Of Commercial | Switches | c | 3 | Mar | 2627 | 0
9 | CBP - Day-Ahead |  | c | 3 | Mar | 0 | 0
10 | CBP - Day-Of |  | c | 3 | Mar | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 3 | Mar | 111470 | 0.011605
12 | TOU-DR-P Voluntary Residential |  | r | 3 | Mar | 19323 | 0.81721
0 | BIP - (20 minute option) |  | c | 4 | Apr | 2 | 0.28273
1 | CPP-D (Large and Medium customers) |  | c | 4 | Apr | 14076 | 0
2 | Armed Forces Pilot | Active but no participants | c | 4 | Apr | #N/A | #N/A
3 | Over Generation Pilot |  | c | 4 | Apr | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 4 | Apr | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 4 | Apr | 17283 | 0.6322
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 4 | Apr | 268 | 0.092078
7 | AC Saver Day-Of Residential | Switches | r | 4 | Apr | 9815 | 0.27113
8 | AC Saver Day-Of Commercial | Switches | c | 4 | Apr | 2774 | 0.15617
9 | CBP - Day-Ahead |  | c | 4 | Apr | 0 | 0
10 | CBP - Day-Of |  | c | 4 | Apr | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 4 | Apr | 112449 | 0.082589
12 | TOU-DR-P Voluntary Residential |  | r | 4 | Apr | 16109 | 0.74186
0 | BIP - (20 minute option) |  | c | 5 | May | 2 | 0.2746
1 | CPP-D (Large and Medium customers) |  | c | 5 | May | 13310 | 0
2 | Armed Forces Pilot | Active but no participants | c | 5 | May | #N/A | #N/A
3 | Over Generation Pilot |  | c | 5 | May | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 5 | May | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 5 | May | 17130 | 1.3921
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 5 | May | 256 | 0.23587
7 | AC Saver Day-Of Residential | Switches | r | 5 | May | 9593 | 0.55346
8 | AC Saver Day-Of Commercial | Switches | c | 5 | May | 2705 | 0.17428
9 | CBP - Day-Ahead |  | c | 5 | May | 41 | 0.48483
10 | CBP - Day-Of |  | c | 5 | May | 134 | 1.2141
11 | TOU-A-P Small Commercial |  | c | 5 | May | 106176 | 0.14519
12 | TOU-DR-P Voluntary Residential |  | r | 5 | May | 19517 | 1.9293
0 | BIP - (20 minute option) |  | c | 6 | Jun | 1 | 0.16708
1 | CPP-D (Large and Medium customers) |  | c | 6 | Jun | 7017 | 0
2 | Armed Forces Pilot | Active but no participants | c | 6 | Jun | #N/A | #N/A
3 | Over Generation Pilot |  | c | 6 | Jun | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 6 | Jun | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 6 | Jun | 14623 | 0.7511
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 6 | Jun | 236 | 0.20211
7 | AC Saver Day-Of Residential | Switches | r | 6 | Jun | 9409 | 0.34679
8 | AC Saver Day-Of Commercial | Switches | c | 6 | Jun | 2244 | 0.13421
9 | CBP - Day-Ahead |  | c | 6 | Jun | 49 | 0.57943
10 | CBP - Day-Of |  | c | 6 | Jun | 125 | 1.1326
11 | TOU-A-P Small Commercial |  | c | 6 | Jun | 105904 | 0.092932
12 | TOU-DR-P Voluntary Residential |  | r | 6 | Jun | 20395 | 1.5282
0 | BIP - (20 minute option) |  | c | 7 | Jul | 1 | 0.15949
1 | CPP-D (Large and Medium customers) |  | c | 7 | Jul | 5806 | 0
2 | Armed Forces Pilot | Active but no participants | c | 7 | Jul | #N/A | #N/A
3 | Over Generation Pilot |  | c | 7 | Jul | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 7 | Jul | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 7 | Jul | 14955 | 2.4867
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 7 | Jul | 249 | 0.51759
7 | AC Saver Day-Of Residential | Switches | r | 7 | Jul | 9340 | 1.2445
8 | AC Saver Day-Of Commercial | Switches | c | 7 | Jul | 2705 | 0.21937
9 | CBP - Day-Ahead |  | c | 7 | Jul | 35 | 0.41388
10 | CBP - Day-Of |  | c | 7 | Jul | 131 | 1.1869
11 | TOU-A-P Small Commercial |  | c | 7 | Jul | 62705 | 0.13719
12 | TOU-DR-P Voluntary Residential |  | r | 7 | Jul | 21149 | 1.8182
0 | BIP - (20 minute option) |  | c | 8 | Aug | 1 | 0.15983
1 | CPP-D (Large and Medium customers) |  | c | 8 | Aug | 5772 | 0
2 | Armed Forces Pilot | Active but no participants | c | 8 | Aug | #N/A | #N/A
3 | Over Generation Pilot |  | c | 8 | Aug | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 8 | Aug | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 8 | Aug | 15274 | 3.3836
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 8 | Aug | 274 | 0.82842
7 | AC Saver Day-Of Residential | Switches | r | 8 | Aug | 9238 | 1.8141
8 | AC Saver Day-Of Commercial | Switches | c | 8 | Aug | 2684 | 0.24563
9 | CBP - Day-Ahead |  | c | 8 | Aug | 47 | 0.55578
10 | CBP - Day-Of |  | c | 8 | Aug | 133 | 1.2051
11 | TOU-A-P Small Commercial |  | c | 8 | Aug | 52619 | 0.1655
12 | TOU-DR-P Voluntary Residential |  | r | 8 | Aug | 21943 | 2.017
0 | BIP - (20 minute option) |  | c | 9 | Sep | 0 | 0
1 | CPP-D (Large and Medium customers) |  | c | 9 | Sep | 0 | 0
2 | Armed Forces Pilot | Active but no participants | c | 9 | Sep | #N/A | #N/A
3 | Over Generation Pilot |  | c | 9 | Sep | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 9 | Sep | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 9 | Sep | 0 | 0
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 9 | Sep | 0 | 0
7 | AC Saver Day-Of Residential | Switches | r | 9 | Sep | 0 | 0
8 | AC Saver Day-Of Commercial | Switches | c | 9 | Sep | 0 | 0
9 | CBP - Day-Ahead |  | c | 9 | Sep | 0 | 0
10 | CBP - Day-Of |  | c | 9 | Sep | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 9 | Sep | 0 | 0
12 | TOU-DR-P Voluntary Residential |  | r | 9 | Sep | 0 | 0
0 | BIP - (20 minute option) |  | c | 10 | Oct | 0 | 0
1 | CPP-D (Large and Medium customers) |  | c | 10 | Oct | 0 | 0
2 | Armed Forces Pilot | Active but no participants | c | 10 | Oct | #N/A | #N/A
3 | Over Generation Pilot |  | c | 10 | Oct | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 10 | Oct | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 10 | Oct | 0 | 0
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 10 | Oct | 0 | 0
7 | AC Saver Day-Of Residential | Switches | r | 10 | Oct | 0 | 0
8 | AC Saver Day-Of Commercial | Switches | c | 10 | Oct | 0 | 0
9 | CBP - Day-Ahead |  | c | 10 | Oct | 0 | 0
10 | CBP - Day-Of |  | c | 10 | Oct | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 10 | Oct | 0 | 0
12 | TOU-DR-P Voluntary Residential |  | r | 10 | Oct | 0 | 0
0 | BIP - (20 minute option) |  | c | 11 | Nov | 0 | 0
1 | CPP-D (Large and Medium customers) |  | c | 11 | Nov | 0 | 0
2 | Armed Forces Pilot | Active but no participants | c | 11 | Nov | #N/A | #N/A
3 | Over Generation Pilot |  | c | 11 | Nov | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 11 | Nov | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 11 | Nov | 0 | 0
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 11 | Nov | 0 | 0
7 | AC Saver Day-Of Residential | Switches | r | 11 | Nov | 0 | 0
8 | AC Saver Day-Of Commercial | Switches | c | 11 | Nov | 0 | 0
9 | CBP - Day-Ahead |  | c | 11 | Nov | 0 | 0
10 | CBP - Day-Of |  | c | 11 | Nov | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 11 | Nov | 0 | 0
12 | TOU-DR-P Voluntary Residential |  | r | 11 | Nov | 0 | 0
0 | BIP - (20 minute option) |  | c | 12 | Dec | 0 | 0
1 | CPP-D (Large and Medium customers) |  | c | 12 | Dec | 0 | 0
2 | Armed Forces Pilot | Active but no participants | c | 12 | Dec | #N/A | #N/A
3 | Over Generation Pilot |  | c | 12 | Dec | #N/A | #N/A
4 | Small Business Energy Management Pilot | Closed | c | 12 | Dec | #N/A | #N/A
5 | AC Saver Day-Ahead Residential | Thermostats | r | 12 | Dec | 0 | 0
6 | AC Saver Day-Ahead Commercial | Thermostats | c | 12 | Dec | 0 | 0
7 | AC Saver Day-Of Residential | Switches | r | 12 | Dec | 0 | 0
8 | AC Saver Day-Of Commercial | Switches | c | 12 | Dec | 0 | 0
9 | CBP - Day-Ahead |  | c | 12 | Dec | 0 | 0
10 | CBP - Day-Of |  | c | 12 | Dec | 0 | 0
11 | TOU-A-P Small Commercial |  | c | 12 | Dec | 0 | 0
12 | TOU-DR-P Voluntary Residential |  | r | 12 | Dec | 0 | 0

## Program MW
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
SUBSCRIPTION STATISTICS - ENROLLED MWs
August 2021
|  | 1900-01-01 | 1900-01-01 |  | 1900-01-02 | 1900-01-02 |  | 1900-01-03 | 1900-01-03 |  | 1900-01-04 | 1900-01-04 |  | 1900-01-05 | 1900-01-05 |  | 1900-01-06 | 1900-01-06
|  | January |  |  | February |  |  | March |  |  | April |  |  | May |  |  | June
Programs | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Eligible Accounts as of Aug 31, 2012
Interruptible/Reliability
BIP - (20 minute option) | 4 | 0.59176 | 0.42432 | 4 | 0.49343 | 0.42432 | 4 | 0.6167 | 0.424 | 2 | 0.28273 | 0.212 | 2 | 0.2746 | 0.212 | 1 | 0.16708 | 0.106 | 5276
Sub-Total Interruptible | 4 | 0.59176 | 0.42432 | 4 | 0.49343 | 0.42432 | 4 | 0.6167 | 0.424 | 2 | 0.28273 | 0.212 | 2 | 0.2746 | 0.212 | 1 | 0.16708 | 0.106
Demand Response Programs
CPP-D (Large and Medium customers) | 14093 | 1.973 | 5.6372 | 14068 | 1.9695 | 5.6272 | 13616 | 0 | 6.5521 | 14076 | 0 | 6.7735 | 13310 | 0 | 6.4049 | 7017 | 0 | 3.3766 | 138123
Armed Forces Pilot 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC Saver Day-Ahead Residential | 17376 | 0.00019548 | 5.5603 | 17278 | 4.5015e-05 | 5.529 | 17050 | 0 | 5.1199 | 17283 | 0.6322 | 5.1898 | 17130 | 1.3921 | 5.1439 | 14623 | 0.7511 | 4.3911 | 663393.5
AC Saver Day-Ahead Commercial | 704 | 0.00025596 | 0.32384 | 704 | 5.9277e-05 | 0.32384 | 268 | 0 | 0.12431 | 268 | 0.092078 | 0.12431 | 256 | 0.23587 | 0.11874 | 236 | 0.20211 | 0.10947
AC Saver Day-Of Residential | 10225 | 0 | 1.3293 | 10185 | 0 | 1.3241 | 10091 | 0 | 1.3536 | 9815 | 0.27113 | 1.3166 | 9593 | 0.55346 | 1.2868 | 9409 | 0.34679 | 1.2621 | 157189
AC Saver Day-Of Commercial | 2652 | 0 | 0.1326 | 2648 | 0 | 0.1324 | 2627 | 0 | 0.12963 | 2774 | 0.15617 | 0.13688 | 2705 | 0.17428 | 0.13348 | 2244 | 0.13421 | 0.11073 | 157189
CBP - Day-Ahead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0.48483 | 0.73609 | 49 | 0.57943 | 0.87971 | 18875
CBP - Day-Of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 1.2141 | 1.8493 | 125 | 1.1326 | 1.7251 | 18875
TOU-PA-P Agricultural | 94 | 0 | 0 | 94 |  |  | 92 | 0.00078712 | 0.043655 | 91 | 0 | 0.04318 | 87 | 0 | 0.041282 | 95 | 0 | 0.045078
TOU-A-P Small Commercial | 111812 | 1.1181 | 5.5906 | 111739 | 1.1174 | 5.5869 | 111470 | 0.011605 | 5.5695 | 112449 | 0.082589 | 5.6184 | 106176 | 0.14519 | 5.305 | 105904 | 0.092932 | 5.2914
TOU-DR-P Voluntary Residential | 17743 | 0.68664 | 3.0163 | 18502 | 0.63577 | 3.1453 | 19323 | 0.81721 | 3.2291 | 16109 | 0.74186 | 2.692 | 19517 | 1.9293 | 3.2615 | 20395 | 1.5282 | 3.4082
Sub-Total Demand Response Programs | 174699 | 3.7782 | 21.5901 | 175218 | 3.7228 | 21.6687 | 174537 | 0.8296 | 22.1218 | 172865 | 1.976 | 21.8947 | 168949 | 6.1291 | 24.2809 | 160097 | 4.7674 | 20.5995
Total All Programs | 174703 | 4.37 | 22.0144 | 175222 | 4.2162 | 22.0931 | 174541 | 1.4463 | 22.5458 | 172867 | 2.2587 | 22.1067 | 168951 | 6.4037 | 24.4929 | 160098 | 4.9345 | 20.7055
|  | 1900-01-07 | 1900-01-07 |  | 1900-01-08 | 1900-01-08 |  | 1900-01-09 | 1900-01-09 |  | 1900-01-10 | 1900-01-10 |  | 1900-01-11 | 1900-01-11 |  | 1900-01-12 | 1900-01-12
|  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December
Programs | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Service Accounts | Ex Ante Estimated MW 1 | Ex Post Estimated MW 2 | Service Accounts | Ex Ante Estimated MW | Ex Post Estimated MW | Service Accounts | Ex Ante Estimated MW | Ex Post Estimated MW | Service Accounts | Ex Ante Estimated MW | Ex Post Estimated MW | Service Accounts | Ex Ante Estimated MW | Ex Post Estimated MW | Eligible Accounts as of Aug 31, 2012
Interruptible/Reliability
BIP - (20 minute option) | 1 | 0.15949 | 0.106 | 1 | 0.15983 | 0.106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5276
Sub-Total Interruptible | 1 | 0.15949 | 0.106 | 1 | 0.15983 | 0.106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Demand Response Programs
CPP-D (Large and Medium customers) | 5806 | 0 | 2.7939 | 5772 | 0 | 2.7775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138123
Armed Forces Pilot 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC Saver Day-Ahead Residential | 14955 | 2.4867 | 4.4908 | 15274 | 3.3836 | 4.5866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 663393.5
AC Saver Day-Ahead Commercial | 249 | 0.51759 | 0.1155 | 274 | 0.82842 | 0.12709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC Saver Day-Of Residential | 9340 | 1.2445 | 1.2529 | 9238 | 1.8141 | 1.2392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157189
AC Saver Day-Of Commercial | 2705 | 0.21937 | 0.13348 | 2684 | 0.24563 | 0.13244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157189
CBP - Day-Ahead | 35 | 0.41388 | 0.62837 | 47 | 0.55578 | 0.84381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18875
CBP - Day-Of | 131 | 1.1869 | 1.8079 | 133 | 1.2051 | 1.8355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18875
TOU-PA-P Agricultural | 95 | 0 | 0.045078 | 102 | 0 | 0.0484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOU-A-P Small Commercial | 62705 | 0.13719 | 3.133 | 52619 | 0.1655 | 2.6291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOU-DR-P Voluntary Residential | 21149 | 1.8182 | 3.5342 | 21943 | 2.017 | 3.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total Demand Response Programs | 117170 | 8.0244 | 17.9351 | 108086 | 10.215 | 17.8865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total All Programs | 117171 | 8.1839 | 18.0411 | 108087 | 10.3749 | 17.9925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
1 The Ex-Ante average per customer estimates are based on Program Year 2019 SDG&E DR Load Impacts report filed April 1st, 2020 for the months of January and February. The Ex-Ante average per customer estimates are based on Program Year 2020 SDG&E DR Load Impacts report filed April 1st, 2021 for the months of March thru December.
2 The Ex-Post average per customer estimates are based on Program Year 2020 draft SDG&E DR Load Impacts report for the months of January and February. The Ex-Post average per customer estimates are based on Program Year 2020 SDG&E DR Load Impacts report filed April 1st, 2021 for the months of March thru December.
3 On March 27, 2020 SDG&E filed Advice Letter 3522-E (Tier 3) proposed to close the Armed Forces Pilot. SDG&E is awaiting a Decision.
4 On March 27, 2020 SDG&E filed Advice Letter 3522-E (Tier 3) proposed to close the Over Generation Pilot, SDG&E is awaiting a Decision. The Over Generation Pilot close on December 31, 2020.
- The reduction in the number of customers on AC Saver Day-Ahead Commercial in March is due to the un-enrollment of customer with thermostat that had been offline for more then 18 months.
- Capacity Bidding Program reports the number of nominations not enrollments.
- Count of Service Accounts reported for TOU-PA-P Agricultural, TOU-A-P Small Commercial and TOU-DR-P Voluntary Residential for April 2021 includes accounts enrolled through May 13, 2021 due to Envision cutover data validation activities.
- The reduction in the number of customer on AC Saver day-ahead residential in June, is due to approximately 2,500 customers with Google-Nest devices did not agree to the new Google terms and conditions.
- CPP-D (Large and Medium Customers) service account numbers for Jan, Feb, and March 2021 are being rechecked. The reason is due to IT conversion data issues. These should be corrected in next months Aug 2021 report.
- BIP service accounts for April and May were updated in August 2021 to denote a customer who unenrolled from the program.
- The "TOU-DR-P Voluntary Residential" and “TOU-A-P Small Commercial” service accounts numbers were inadvertently reported on the wrong row January through June. This report has been corrected to reflect the service account numbers for both programs.
(End of page)

## Ex ante LI & Eligibility Stats
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
August 2021
Average Ex Ante Load Impact kW / Customer
Program | January | February | March | April | May | June | July | August | September | October | November | December | Eligible Accounts as of January | Eligibility Criteria (Refer to tariff for specifics)
BIP - (20 minute option) | 147.9393 | 123.3584 | 154.1762 | 141.3628 | 137.3003 | 167.0845 | 159.488 | 159.8284 | 182.0331 | 153.4139 | 178.6724 | 115.0728 | 5326 | Applicable to all non-residential time-of-use metered customers who either: 1) commit to curtail at least 15% of Monthly Average Peak Demand, with a minimum load reduction of 100 kW, or b) sign up through an aggregator. This tariff is available to bundled, Direct Access, and Community Choice Aggregation (CCA) customers.
CPP-D (Large and Medium customers) | 0.14 | 0.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24298 | This Schedule is the default commodity rate for customers currently receiving bundled utility service on a commercial/industrial rate schedule for customers whose Maximum Monthly Demand is equal to or exceeds or is expected to equal or exceed 20 kW for twelve consecutive months. This Schedule is not applicable to Direct Access (DA) or Community Choice Aggregation (CCA) customers.
AC Saver Day-Ahead Residential | 1.125e-05 | 2.6054e-06 | 0 | 0.036579 | 0.081266 | 0.051364 | 0.16628 | 0.22153 | 0.2874 | 0.15124 | 0.022868 | 0 | 590220 | AC Saver Day Ahead (thermostats) is a voluntary demand response program available to all residential customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. Residential customers with Net Energy Metering are not eligible for this schedule. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of we used 54% based on 2019 California Residential Appliance Saturation Survey (RASS) report.
AC Saver Day-Ahead Commercial | 0.00036358 | 8.4201e-05 | 0 | 0.34358 | 0.92136 | 0.85638 | 2.0787 | 3.0234 | 2.5093 | 2.0845 | 0.46238 | 0 | 133226 | AC Saver Day Ahead (thermostats) is a voluntary demand response program available to all commercial customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of we used 85% based on commercial estimates.
AC Saver Day-Of Residential | 0 | 0 | 0 | 0.027624 | 0.057695 | 0.036857 | 0.13325 | 0.19637 | 0.24342 | 0.12679 | 0 | 0 | 590220 | AC Saver is a voluntary demand response program available to all residential customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. Residential customers with Net Energy Metering are not eligible for this schedule. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) or Community Choice Aggregation (CCA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of in the past we used 54% based on 2019 California Residential Appliance Saturation Survey (RASS) report.
AC Saver Day-Of Commercial | 0 | 0 | 0 | 0.056297 | 0.06443 | 0.059808 | 0.081098 | 0.091516 | 0.10404 | 0.083493 | 0 | 0 | 133226 | AC Saver Day Of (switches) is a voluntary demand response program available to all commercial customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) or Community Choice Aggregation (CCA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of we used 85% based on commercial estimates
CBP - Day-Ahead | 0 | 0 | 0 | 0 | 11.8252 | 11.8252 | 11.8252 | 11.8252 | 11.8252 | 11.8252 | 0 | 0 | 78368 | This schedule is available to commercial and industrial Utility customers receiving Bundled Utility service, Direct Access (“DA”) service or Community Choice Aggregation (“CCA”) service, and being billed on a Utility commercial, industrial or agricultural rate schedule.
CBP - Day-Of | 0 | 0 | 0 | 0 | 9.0606 | 9.0606 | 9.0606 | 9.0606 | 9.0606 | 9.0606 | 0 | 0 | 78368 | This schedule is available to commercial and industrial Utility customers receiving Bundled Utility service, Direct Access (“DA”) service or Community Choice Aggregation (“CCA”) service, and being billed on a Utility commercial, industrial or agricultural rate schedule.
TOU-DR-P Voluntary Residential | 0.038699 | 0.034362 | 0.042292 | 0.046052 | 0.098851 | 0.074933 | 0.085971 | 0.091919 | 0.10056 | 0.093665 | 0.14195 | 0.1612 | 1292629 | This optional tariff provides residential customers with the opportunity to manage their electric costs by either reducing load during high cost pricing periods defined as a Reduce Your Use (RYU) Event Day, or shifting load from high cost pricing periods to lower cost pricing periods. This Schedule is not applicable to commercial customers. This Schedule is not applicable to Direct Access (DA), Transitional Bundled Service (TBS) or Community Choice Aggregation (CCA) customers.
TOU-A-P Small Commercial | 0.01 | 0.01 | 0.00010411 | 0.00073446 | 0.0013674 | 0.00087752 | 0.0021878 | 0.0031452 | 0.0044619 | 0.002859 | 0.00031512 | -7.772e-05 | 120672 | This optional tariff provides residential customers with the opportunity to manage their electric costs by either reducing load during high cost pricing periods defined as a Reduce Your Use (RYU) Event Day, or shifting load from high cost pricing periods to lower cost pricing periods. This Schedule is not applicable to commercial customers. This Schedule is not applicable to Direct Access (DA), Transitional Bundled Service (TBS) or Community Choice Aggregation (CCA) customers.
TOU-PA-P Agricultural | 0.0070192 | 0.0070192 | 0.0085557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2822 | This Schedule is the standard Schedule for customers whose monthly maximum demand does not exceed 20kW for no more than 3 out of 12 consecutive months for general power service utilized to pump water, or in the production of agricultural products including feed choppers, milking machines, heaters for incubators, brooders, poultry house and flower production lighting, but excluding power service used for the processing of agricultural products, general or protective lighting, or domestic household uses. This schedule is available to agricultural and water pumping customers.
Notes:
- The Ex-Ante average per customer estimates are based on Program Year 2019 SDG&E DR Load Impacts report filed April 1st, 2020 for the months of January and February. The Ex-Ante average per customer estimates are based on Program Year 2020 SDG&E DR Load Impacts report filed April 1st, 2021 for the months of March thru December.
- The Estimated Average Ex-Ante Load Impact kW/Customer = Average kW / Customer, under 1-in-2 weather conditions, of an event that would occur from 4 - 9 pm year around.
- The Resource Adequacy measurement hours were modified to HE17-HE21 (4:00 p.m. – 9:00 p.m.) for each month of the year beginning in 2019.
- CPP-D, TOU-DR-P (Voluntary Residential) and TOU-A-P (Small Commercial) ex-ante estimates include Technology Deployment (TD).
(End of page)
0

## Ex post LI & Eligibility Stats
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
August 2021
Average Ex Post Load Impact kW / Customer
Program | January | February | March | April | May | June | July | August | September | October | November | December | Eligible Accounts as of January | Eligibility Criteria (Refer to tariff for specifics)
BIP - (20 minute option) | 106.08 | 106.08 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 5326 | Applicable to all non-residential time-of-use metered customers who either: 1) commit to curtail at least 15% of Monthly Average Peak Demand, with a minimum load reduction of 100 kW, or b) sign up through an aggregator. This tariff is available to bundled, Direct Access, and Community Choice Aggregation (CCA) customers.
CPP-D (Large and Medium customers) | 0.4 | 0.4 | 0.48121 | 0.48121 | 0.48121 | 0.48121 | 0.48121 | 0.48121 | 0.48121 | 0.48121 | 0.48121 | 0.48121 | 24298 | This Schedule is the default commodity rate for customers currently receiving bundled utility service on a commercial/industrial rate schedule for customers whose Maximum Monthly Demand is equal to or exceeds or is expected to equal or exceed 20 kW for twelve consecutive months. This Schedule is not applicable to Direct Access (DA) or Community Choice Aggregation (CCA) customers.
AC Saver Day-Ahead Residential | 0.32 | 0.32 | 0.30029 | 0.30029 | 0.30029 | 0.30029 | 0.30029 | 0.30029 | 0.30029 | 0.30029 | 0.30029 | 0.30029 | 590220 | AC Saver Day Ahead (thermostats) is a voluntary demand response program available to all residential customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. Residential customers with Net Energy Metering are not eligible for this schedule. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of we used 54% based on 2019 California Residential Appliance Saturation Survey (RASS) report.
AC Saver Day-Ahead Commercial | 0.46 | 0.46 | 0.46384 | 0.46384 | 0.46384 | 0.46384 | 0.46384 | 0.46384 | 0.46384 | 0.46384 | 0.46384 | 0.46384 | 133226 | AC Saver Day Ahead (thermostats) is a voluntary demand response program available to all commercial customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of we used 85% based on commercial estimates.
AC Saver Day-Of Residential | 0.13 | 0.13 | 0.13414 | 0.13414 | 0.13414 | 0.13414 | 0.13414 | 0.13414 | 0.13414 | 0.13414 | 0.13414 | 0.13414 | 590220 | AC Saver is a voluntary demand response program available to all residential customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. Residential customers with Net Energy Metering are not eligible for this schedule. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) or Community Choice Aggregation (CCA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of in the past we used 54% based on 2019 California Residential Appliance Saturation Survey (RASS) report.
AC Saver Day-Of Commercial | 0.05 | 0.05 | 0.049344 | 0.049344 | 0.049344 | 0.049344 | 0.049344 | 0.049344 | 0.049344 | 0.049344 | 0.049344 | 0.049344 | 133226 | AC Saver Day Of (switches) is a voluntary demand response program available to all commercial customers with air conditioner (AC) units installed at their premise with SDG&E approved technology capable of curtailing the customers’ AC unit. This schedule is available to customers receiving Bundled Utility Service or, Direct Access (DA) or Community Choice Aggregation (CCA) service and billed by the Utility. Service on this schedule must be taken in combination with the customer’s otherwise applicable rate schedule. Note: AC Saver Day Of we used 85% based on commercial estimates
CBP - Day-Ahead | 18 | 18 | 17.9533 | 17.9533 | 17.9533 | 17.9533 | 17.9533 | 17.9533 | 17.9533 | 17.9533 | 17.9533 | 17.9533 | 78368 | This schedule is available to commercial and industrial Utility customers receiving Bundled Utility service, Direct Access (“DA”) service or Community Choice Aggregation (“CCA”) service, and being billed on a Utility commercial, industrial or agricultural rate schedule.
CBP - Day-Of | 13.8 | 13.8 | 13.8009 | 13.8009 | 13.8009 | 13.8009 | 13.8009 | 13.8009 | 13.8009 | 13.8009 | 13.8009 | 13.8009 | 78368 | This schedule is available to commercial and industrial Utility customers receiving Bundled Utility service, Direct Access (“DA”) service or Community Choice Aggregation (“CCA”) service, and being billed on a Utility commercial, industrial or agricultural rate schedule.
TOU-DR-P Voluntary Residential | 0.17 | 0.17 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 0.16711 | 1292629 | This optional tariff provides residential customers with the opportunity to manage their electric costs by either reducing load during high cost pricing periods defined as a Reduce Your Use (RYU) Event Day, or shifting load from high cost pricing periods to lower cost pricing periods. This Schedule is not applicable to commercial customers. This Schedule is not applicable to Direct Access (DA), Transitional Bundled Service (TBS) or Community Choice Aggregation (CCA) customers.
TOU-A-P Small Commercial | 0.05 | 0.05 | 0.049964 | 0.049964 | 0.049964 | 0.049964 | 0.049964 | 0.049964 | 0.049964 | 0.049964 | 0.049964 | 0.049964 | 120672 | This optional tariff provides residential customers with the opportunity to manage their electric costs by either reducing load during high cost pricing periods defined as a Reduce Your Use (RYU) Event Day, or shifting load from high cost pricing periods to lower cost pricing periods. This Schedule is not applicable to commercial customers. This Schedule is not applicable to Direct Access (DA), Transitional Bundled Service (TBS) or Community Choice Aggregation (CCA) customers.
TOU-PA-P Agricultural | 0 | 0 | 0.47451 | 0.47451 | 0.47451 | 0.47451 | 0.47451 | 0.47451 | 0.47451 | 0.47451 | 0.47451 | 0.47451 | 2822 | This Schedule is the standard Schedule for customers whose monthly maximum demand does not exceed 20kW for no more than 3 out of 12 consecutive months for general power service utilized to pump water, or in the production of agricultural products including feed choppers, milking machines, heaters for incubators, brooders, poultry house and flower production lighting, but excluding power service used for the processing of agricultural products, general or protective lighting, or domestic household uses. This schedule is available to agricultural and water pumping customers.
Notes:
- The Ex-Post average per customer estimates are based on Program Year 2020 draft SDG&E DR Load Impacts report for the months of January and February. The Ex-Post average per customer estimates are based on Program Year 2020 SDG&E DR Load Impacts report filed April 1st, 2021 for the months of March thru December.
- Estimated Average Ex-Post Load Impact kW / Customer = Average kW / Customer service account over all actual event hours for the preceding year if events occurred.
- CPP-D, TOU-DR-P (Voluntary Residential) and TOU-A-P (Small Commercial) include Technology Deployment (TD).
- The TOU-PA-P Agricultural Ex-Post average per customer estimates are based on Program Year 2020 draft SDG&E DR Load Impacts report for the months of January and February. The draft ex-post estimates show an increase load impact of (-0.06kW), therefore the estimates were converted to zero.
(End of page)
0

## TA-TI Distribution@ (hidden)
Detailed Breakdown of MWs To Date in TA/Auto DR/TI Programs (A)
1905-07-08 | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
Price Responsive | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs
CPP-D |  | 5.8977 | 2.303 | 8.2007 |  | 5.8977 | 2.303 | 8.2007 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
CBP |  | 12.8962 | 1.475 | 14.3712 |  | 12.9119 | 1.475 | 14.3869 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total |  | 18.7939 | 3.778 | 22.5719 |  | 18.8096 | 3.778 | 22.5876 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Interruptible/Reliability | [23 empty] | 0
BIP | [23 empty] | 0
SLRP | [23 empty] | 0
Total |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
[12 empty] | 0 |  |  |  | 0 |  |  |  | 0
Total Technology MWs |  | 18.7939 | 3.778 | 22.5719 |  | 18.8096 | 3.778 | 22.5876 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
General Program
TA (may also be enrolled in TI and AutoDR)
|  |  |  | 59.3 |  |  |  | 59.3
Total | 0 |  |  | 59.3 | 0 |  |  | 59.3 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total TA MWs | 0 |  |  | 59.3 | 0 |  |  | 59.3 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| July |  |  |  | August |  |  | July | September |  |  | July | October |  |  | July | November |  |  | July | December |  |  | July
Price Responsive | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs | TA Identified MWs | Auto DR Verified MWs | TI Verified MWs | Total Technology MWs
AMP
CBP |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
DBP | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0
Peak Choice - Best Effort | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0
Peak Choice - Committed | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0
CPP-D |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Interruptible/Reliability | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
BIP | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
OBMC | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
SLRP | [7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total Technology MWs |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Program
TA (may also be enrolled in TI and AutoDR)
Total | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Total TA MWs | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Notes: |  | ddd
· TA Identified MW | Represents identified MW for service accounts from completed TA in accumulative value (may or may not be enrolled in DR).
· AutoDR Verified MW | Represents verified/tested MW for service accounts from complete TI (i.e. must be enrolled in DR) and must be Auto DR in accumulative value.
· TI Verified MW | Represents verified MW for service accounts from completed TI (i.e. must be enrolled in DR) but not AutoDR in accumulative value; MW reported here not necessarily amount enrolled in DR.
· Total Technology MW | Represents the sum of verified MW associated with the service accounts from the completed TI (i.e. must be enrolled in DR), including Auto DR and non-Auto DR.

## Event Summary
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
EVENT SUMMARY
August 2021
Year-to-Date Event Summary
Program Category | Event No. | Date | Event Trigger | Load Reduction MW 1 | Event Beginning to End | Program Total Hours (Annual) 2
AC Saver DA Residential | 1 | 2021-06-17 | Heat Rate | 2.0274 | 6:00pm-9:00pm | 3
BIP | 2 | 2021-06-17 | Temperature and System Load | 0.26279 | 6:00pm-8:00pm | 2
CBP Day Ahead 11-7 | 3 | 2021-06-15 | Market Price | 0.69502 | 4:00pm-7:00pm | 3
CBP Day Ahead 1-9 | 4 | 2021-06-15 | Market Price | 0.62631 | 6:00pm-8:00pm | 2
CBP Day Of 1-9 | 5 | 2021-06-15 | Real Time Price | 3.068 | 6:00pm-8:00pm | 2
CBP Day Ahead 11-7 | 6 | 2021-06-16 | Market Price | 0.78972 | 5:00pm-7:00pm | 5
CBP Day Ahead 1-9 | 7 | 2021-06-16 | Market Price | 0.51412 | 6:00pm-8:00pm | 4
CBP Day Of 1-9 | 8 | 2021-06-16 | Real Time Price | 2.6918 | 6:00pm-8:00pm | 4
CBP Day Ahead 11-7 | 9 | 2021-06-17 | Market Price | 0.85353 | 5:00pm-7:00pm | 7
CBP Day Ahead 1-9 | 10 | 2021-06-17 | Market Price | 0.49246 | 6:00pm-9:00pm | 7
CBP Day Of 1-9 | 11 | 2021-06-17 | Real Time Price | 2.6816 | 6:00pm-9:00pm | 7
AC Saver DO (Summer Saver) Commercial | 12 | 2021-06-15 | Heat Rate | 0.73429 | 6:00pm-8:00pm | 2
AC Saver DO (Summer Saver) Residential | 13 | 2021-06-15 | Heat Rate | -0.32389 | 6:00pm-8:00pm | 2
AC Saver DO (Summer Saver) Commercial | 14 | 2021-06-16 | Heat Rate | 0.34985 | 6:00pm-8:00pm | 4
AC Saver DO (Summer Saver) Residential | 15 | 2021-06-16 | Heat Rate | 0.85614 | 6:00pm-8:00pm | 4
AC Saver DO (Summer Saver) Commercial | 16 | 2021-06-17 | Heat Rate | 1.1166 | 6:00pm-9:00pm | 7
AC Saver DO (Summer Saver) Residential | 17 | 2021-06-17 | Heat Rate | 1.0483 | 6:00pm-9:00pm | 7
CBP Day Ahead 11-7 | 18 | 2021-06-28 | Market Price | 0.79717 | 3:00pm-7:00pm | 11
CBP Day Ahead 1-9 | 19 | 2021-06-28 | Market Price | 0.27668 | 5:00pm-9:00pm | 11
CBP Day Of 1-9 | 20 | 2021-06-28 | Real Time Price | 2.7157 | 6:00pm-9:00pm | 10
CBP Day Ahead 11-7 | 21 | 2021-06-29 | Market Price | 0.20942 | 3:00pm-7:00pm | 15
CBP Day Ahead 1-9 | 22 | 2021-06-29 | Market Price | 0.36333 | 5:00pm-9:00pm | 15
CBP Day Of 1-9 | 23 | 2021-06-29 | Real Time Price | 2.6901 | 6:00pm-9:00pm | 13
CBP Day Ahead 1-9 | 24 | 2021-06-30 | Market Price | 0.42822 | 7:00pm-9:00pm | 17
CBP Day Ahead 11-7 | 24 | 2021-07-09 | Market Price | 0.68833 | 5:00pm-7:00pm | 17
CBP Day Of 1-9 | 24 | 2021-07-09 | Real Time Price | 2.5532 | 6:00pm-8:00pm | 15
CBP Day Ahead 11-7 | 24 | 2021-07-12 | Market Price | 0.72287 | 5:00pm-7:00pm | 19
CBP Day Of 1-9 | 24 | 2021-07-12 | Real Time Price | 2.5086 | 6:00pm-9:00pm | 18
AC Saver DA Residential | 24 | 2021-07-12 | Heat Rate | 2.3349 | 6:00pm-8:00pm | 5
AC Saver DO (Summer Saver) Commercial | 24 | 2021-07-12 | Heat Rate | 0.65403 | 6:00pm-8:00pm | 9
AC Saver DO (Summer Saver) Residential | 24 | 2021-07-12 | Heat Rate | 0.70324 | 6:00pm-8:00pm | 9
CBP Day Ahead 11-7 | 24 | 2021-07-19 | Market Price | 0.73355 | 5:00pm-7:00pm | 21
CBP Day Of 1-9 | 24 | 2021-07-19 | Real Time Price | 3.2948 | 6:00pm-8:00pm | 20
CBP Day Ahead 11-7 | 24 | 2021-07-28 | Market Price | 0.84053 | 5:00pm-7:00pm | 23
CBP Day Of 1-9 | 24 | 2021-07-28 | Real Time Price | 2.5504 | 6:00pm-8:00pm | 22
CBP Day Ahead 11-7 | 24 | 2021-07-29 | Market Price | 0.77589 | 5:00pm-7:00pm | 25
CBP Day Of 1-9 | 24 | 2021-07-29 | Real Time Price | 2.6163 | 6:00pm-8:00pm | 24
AC Saver DO (Summer Saver) Commercial | 24 | 2021-07-29 | Heat Rate | -0.24348 | 6:00pm-9:00pm | 12
AC Saver DO (Summer Saver) Residential | 24 | 2021-07-29 | Heat Rate | 0.29244 | 6:00pm-9:00pm | 12
CBP Day Ahead 11-7 | 24 | 2021-07-30 | Market Price | 0.76379 | 3:00pm-7:00pm | 29
CBP Day Of 1-9 | 24 | 2021-07-30 | Real Time Price | 3.6944 | 5:00pm-9:00pm | 28
AC Saver DA Residential | 24 | 2021-07-29 | Heat Rate | 2.3803 | 6:00pm-9:00pm | 8
CBP Day Ahead 11-7 | 43 | 2021-08-26 | Market Price | 0.53 | 5:00pm-7:00pm | 31
CBP Day Of 1-9 | 44 | 2021-08-26 | Real Time Price | 2.55 | 6:00pm-8:00pm | 30
CBP Day Of 11-7 | 45 | 2021-08-26 | Real Time Price | 0.04 | 5:00pm-7:00pm | 2
CBP Day Ahead 11-7 | 46 | 2021-08-27 | Market Price | 0.32 | 3:00pm-7:00pm | 35
CBP Day Of 1-9 | 47 | 2021-08-27 | Real Time Price | 1.55 | 5:00pm-8:00pm | 33
CBP Day Of 11-7 | 48 | 2021-08-27 | Real Time Price | 0.03 | 5:00pm-7:00pm | 4
CBP Day Ahead 11-7 | 49 | 2021-08-31 | Market Price | 0.67 | 5:00pm-7:00pm | 37
Notes:
1 If the MW Load Reduction is 0.00, there was no actual load reduction. If the MW Load Reduction is negative, there was an increase of load during the event hours. If there is nothing there, there were no events.
2 Program Total Hours (Annual) is cumulative.
Due to time differences in our new and old customer information systems event performance has been revised from June 2021 report.
(End of page)

## Auto DR (TI) & Tech Deployment
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
Auto-DR (TI) and Technology Deployment (TD) Programs Breakdown of MWs
August 2021
| Jan | Feb | March | April | May | June | July | August | September | October | November | December
Eligible Programs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs | Auto DR Verified MWs
CPP-D | 0.0123 | 0.0123 | 0.0909 | 0.0909 | 0.0909 | 0.0909 | 0 | 0 | 0 | 0 | 0 | 0
CBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AFP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DRAM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0.0123 | 0.0123 | 0.0909 | 0.0909 | 0.0909 | 0.0909 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
- Auto DR Verified MWs: Represent the verified/tested MW for service accounts from completed TI (i.e. must be enrolled in DR).
| Jan | Feb | March | April | May | June | July | August | September | October | November | December
Eligible Programs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs | Technology Deployment- Residential MWs
AC Saver Day-Ahead Residential | 5.5603 | 5.529 | 5.1199 | 5.1898 | 5.1439 | 4.3911 | 4.4908 | 4.4908 | 0 | 0 | 0 | 0
TOU-DR-P Voluntary Residential | 0.38496 | 0.40608 | 0.34293 | 0.34533 | 0.33962 | 0.30029 | 0.30389 | 0.25104 | 0 | 0 | 0 | 0
DRAM | 0.61728 | 0.61152 | 0.44742 | 0.44742 | 0.44742 | 0.44742 | 0.44742 | 0.44742 | 0 | 0 | 0 | 0
Total | 6.5626 | 6.5466 | 5.9102 | 5.9826 | 5.9309 | 5.1388 | 5.2421 | 5.1892 | 0 | 0 | 0 | 0
Notes:
- Technology Deployment (TD) Verified MWs: Represents the average load reduction expected on an event day based on the ex-post results for customers with qualifying technology.
| Jan | Feb | March | April | May | June | July | August | September | October | November | December
Eligible Programs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs | Technology Deployment- Commercial MWs
AC Saver Day-Ahead Commercial | 0.32384 | 0.32384 | 0.12431 | 0.12431 | 0.11874 | 0.10947 | 0.1155 | 0.12709 | 0 | 0 | 0 | 0
TOU-A-P Small Commercial | 0.34086 | 0.33948 | 0.22404 | 0.22404 | 0.21893 | 0.18368 | 0 | 0.18415 | 0 | 0 | 0 | 0
TOU-PA-P Agricultural | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPP-D | 0.16744 | 0.1656 | 0.13776 | 0.13637 | 0.12988 | 0.109 | 0.10808 | 0.10808 | 0 | 0 | 0 | 0
CBP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AFP | 0.0285 | 0.0285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DRAM | 0.036 | 0.036 | 0.017953 | 0.017953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0.89664 | 0.89342 | 0.50406 | 0.50267 | 0.46756 | 0.40215 | 0.22357 | 0.41932 | 0 | 0 | 0 | 0
Notes:
(End of page)

## Marketing
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
MARKETING, EDUCATION & OUTREACH
August 2021
| 2021 Expenditures for Marketing, Education and Outreach | [11 empty] | Year-to Date 2021 Expenditures | Program Cycle-to Date 2018-2021 Expenditures |  | Authorized Budget (if Applicable) 1
| January | February | March | April | May | June | July | August | September | October | November | December |  |  | Carryover Expenditures to Date 2012 - 2014
I. UTILITY MARKETING BY ACTIVITY
PROGRAMS, RATES & ACTIVITES WHICH DO NOT REQUIRE ITEMIZED ACCOUNTING
Local IDSM Marketing | 11850 | 31485.81 | 36584.06 | 25762.2 | 10906.94 | 9892.69 | 8822.6 | 11628.38 | 0 | 0 | 0 | 0 | 146932.68 | 1726015.68 |  | 2813694
Base Interruptible Program | 0 | 0 | 315.4 | 67.83 | 335.75 | 1234.93 | 256.72 | 1056.41 | 0 | 0 | 0 | 0 | 3267.04 | 27380.04 |  | 35302
Back Up Generators (BUGs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000
Capacity Bidding Program | 0 | 0 | 627 | 139.45 | 671.5 | 2469.87 | 513.44 | 2112.82 | 0 | 0 | 0 | 0 | 6534.08 | 42037.08 |  | 78149
AC Saver Day Ahead | 0 | 0 | 1620.44 | 1297.3 | 1343 | 4939.74 | 1026.92 | 4247.63 | 0 | 0 | 0 | 0 | 14475.03 | 148993.03 |  | 303149.5
AC Saver Day Of | 0 | 0 | 3629 | 203.2 | 11464.3 | 12349.3 | 2567.21 | 10564.09 | 0 | 0 | 0 | 0 | 40777.1 | 277969.1 |  | 303150
Technology Deployment | 0 | 0 | 5494.8 | 253.58 | 6036.25 | 18523.94 | 3850.81 | 15927.14 | 0 | 0 | 0 | 0 | 50086.52 | 391796.52 |  | 643043
Technology Incentives 3 | 0 | 0 | 2827.2 | -144.62 | 2350.25 | 8644.51 | 2797.04 | 7394.87 | 0 | 0 | 0 | 0 | 23869.25 | 200095.25 |  | 383701
CPP-D | 1375 | 0 | 9270.88 | 543.65 | 8729.5 | 32108.18 | 7154.81 | 27727.26 | 0 | 0 | 0 | 0 | 86909.28 | 791447.28 |  | 1102357
Smart Pricing 3 | 1375 | 0 | 16627.38 | -719.32 | 12519 | 50522.58 | 9465.32 | 37948.35 | 0 | 0 | 0 | 0 | 127738.31 | 1215856.31 |  | 1653537
Small Customer Technology Deployment (SCTD) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2328 |  | 0
Small Business Energy Management Pilot (SBEMP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 |  | 50000
I. TOTAL UTILITY MARKETING BY ACTIVITY | 14600 | 31485.81 | 76996.16 | 27403.27 | 54356.49 | 140685.74 | 36454.87 | 118606.95 | 0 | 0 | 0 | 0 | 500589.29 | 4824448.29 |  | 7367082.5
II. UTILITY MARKETING BY ITEMIZED COST
Customer Research | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collateral- Development, Printing, Distribution etc. (all non-labor costs) | 0.49 | 0 | 66.24 | 0 | 2957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3023.73 | 250548.73
Labor 4 | 18233.67 | 17764.31 | 17228.58 | 11049.69 | -154.67 | 7055.18 | 6822.6 | 10878.38 | 0 | 0 | 0 | 0 | 88877.74 | 1122223.74
Paid Media | 2750 | 0 | 40201.35 | 1641.05 | 40492.3 | 130793 | 26672.05 | 106454.54 | 0 | 0 | 0 | 0 | 349004.29 | 2807327.29
Other Costs 2 | -6384 | 13721.5 | 19500 | 14712.5 | 11061.6 | 2837.5 | 2960.14 | 1274.03 | 0 | 0 | 0 | 0 | 59683.27 | 644348.27
II. TOTAL UTILITY MARKETING BY ITEMIZED COST | 14600.16 | 31485.81 | 76996.17 | 27403.24 | 54356.23 | 140685.68 | 36454.79 | 118606.95 | 0 | 0 | 0 | 0 | 500589.03 | 4824448.03
III. UTILITY MARKETING BY CUSTOMER SEGMENT
Agricultural | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Large Commercial and Industrial | 1375 | 0 | 13223.7 | 1115.51 | 12087 | 44457.49 | 10722.03 | 38302.36 | 0 | 0 | 0 | 0 | 121283.09 | 1523769.09
Small and Medium Commercial | 3942.05 | 9833.75 | 23203.51 | 12722.3 | 21936.25 | 32695.2 | 10561.84 | 26912.22 | 0 | 0 | 0 | 0 | 141807.12 | 1190178.12
Residential | 9283.14 | 21652.06 | 40568.95 | 13565.46 | 20333 | 63533.05 | 15171 | 53392.45 | 0 | 0 | 0 | 0 | 237499.11 | 2110501.11
III. TOTAL UTILITY MARKETING BY CUSTOMER SEGMENT | 14600.19 | 31485.81 | 76996.16 | 27403.27 | 54356.25 | 140685.74 | 36454.87 | 118607.03 | 0 | 0 | 0 | 0 | 500589.32 | 4824448.32 | 0
Notes:
1 LME&O Approved Budget is a Five (5) Year Program Cycle 2018-2022 with the exception of Local IDSM Marketing which is funded per the approved Advice Letter 3598-E_2898-G/3599-E_2897G.
2 January credit is related to an accrual reversal. The expense accrual occurred in a prior period (December 2020).
3 April credits are related to accrual reversals that occurred in a previous reporting period (March).
4 May credits are related to labor reversals to reflect proper labor allocation.
(End of page)

## DRP Expenditures
SAN DIEGO GAS & ELECTRIC REPORT COMPANY ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
YEAR TO DATE PROGRAM EXPENDITURES
August 2021
Cost Item | January | February | March | April | May | June | July | August | September | October | November | December | Year-to Date 2021 Expenditures | Program Cycle-to-Date Total Expenditures (2018-2021) | 5-Year Funding (2018-2022) | Fund shift Adjustments | Percent Funding
Category 1: Supply Side DR Programs
AC Saver Day-Ahead | 130414 | 8364 | 10848 | 10628 | 12351 | 13271.69 | 11670.65 | 11117.74 | 0 | 0 | 0 | 0 | 208665.08 | 1119826.08 | 2869200 | 0 | 39.03%
AC Saver Day-Of | 44397 | 11855 | 76438 | 45377 | 42134 | 48670.9 | 50157.36 | 45191.22 | 0 | 0 | 0 | 0 | 364220.48 | 4500612.48 | 9020700 | 0 | 49.89%
Base Interruptible Program (BIP) 1,2,4 | 23503 | 5443 | 25267 | 6695 | 7589 | 8120.44 | 7570.55 | 5652.44 | 0 | 0 | 0 | 0 | 89840.43 | 624655.43 | 4664400 | 0 | 13.39%
Capacity Bidding Program (CBP) | 6528 | 9156 | 9539 | 20911 | 16437 | 18691.11 | 31062.91 | 7862.02 | 0 | 0 | 0 | 0 | 120187.04 | 1048397.04 | 10301202 | 0 | 10.18%
Peak Time Rebate (PTR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15326 | 20000 | 0 | 76.63%
Budget Category 1 Total | 204842 | 34818 | 122092 | 83611 | 78511 | 88754.14 | 100461.47 | 69823.42 | 0 | 0 | 0 | 0 | 782913.03 | 7308817.03 | 26875502 | 0 | 27.2%
Category 2: Load Modifying Demand Response Program
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Budget Category 2 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Category 3: Demand Response Auction Mechanism (DRAM)
Demand Response Auction Mechanism Pilot (DRAM) 3 | 96846 | 105482 | 267497 | 23357 | -19352 | 320557.87 | 14894.96 | 5637.3 | 0 | 0 | 0 | 0 | 814920.13 | 4661665.13 | 8320000 | 0 | 56.03%
Budget Category 3 Total | 96846 | 105482 | 267497 | 23357 | -19352 | 320557.87 | 14894.96 | 5637.3 | 0 | 0 | 0 | 0 | 814920.13 | 4661665.13 | 8320000 | 0 | 56.03%
Category 4: Emerging & Enabling Technologies
Emerging Technology (ET) | 22999 | 17650 | 50081 | 21035 | 41123 | 14076.98 | 15605.67 | 16998.69 | 0 | 0 | 0 | 0 | 199569.34 | 1525836.34 | 3483000 | 0 | 43.81%
Technology Deployment (TD) | 29511 | 26533 | 28341 | 40374 | 18416 | 28532.93 | 28883.03 | 36229.44 | 0 | 0 | 0 | 0 | 236820.4 | 1845467.4 | 3794000 | 0 | 48.64%
Technology Incentives (TI) | 7417 | 9018 | 10206 | 25263 | 7642 | 10083.32 | 8791.14 | 9782.41 | 0 | 0 | 0 | 0 | 88202.87 | 1056627.87 | 11267000 | 0 | 9.378%
Budget Category 4 Total | 59927 | 53201 | 88628 | 86672 | 67181 | 52693.23 | 53279.84 | 63010.54 | 0 | 0 | 0 | 0 | 524592.61 | 4427931.61 | 18544000 | 0 | 23.88%
Category 5: Pilots
Armed Forces Pilot (AFP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8111.66 | 2507000 | 0 | 0.3236%
Constrained Local Capacity Program (CLCP) | 111344 | 1498 | 2143 | 1954 | 1678 | 621.53 | 3349.6 | 1602.93 | 0 | 0 | 0 | 0 | 124191.06 | 187932.06 | 500000 | 0 | 37.59%
Capacity Bidding Program Residential Pilot (CBP)6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4056.99 | 0 | 0 | 0 | 0 | 4056.99 | 4056.99 | 708000 | 0 | 0.573%
Over Generation Pilot (OGP) 5 | 1681 | 1873 | 2679 | 2442 | 2098 | 775.91 | -1986.67 | 0 | 0 | 0 | 0 | 0 | 9562.24 | 624583.24 | 2148000 | 0 | 29.08%
Small Business Energy Management Pilot (SBEMP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36789 | 340000 | 0 | 10.82%
Budget Category 5 Total | 113025 | 3371 | 4822 | 4396 | 3776 | 1397.44 | 1362.93 | 5659.92 | 0 | 0 | 0 | 0 | 137810.29 | 861472.95 | 6203000 | 0 | 13.89%
Category 6: Marketing, Education, and Outreach
Local Marketing Education & Outreach (LME&O) | 2750 | 0 | 40412 | 1641 | 43449 | 130793 | 27632.19 | 106978.57 | 0 | 0 | 0 | 0 | 353655.76 | 3098433.76 | 4502000 | 0 | 68.82%
Budget Category 6 Total | 2750 | 0 | 40412 | 1641 | 43449 | 130793 | 27632.19 | 106978.57 | 0 | 0 | 0 | 0 | 353655.76 | 3098433.76 | 4502000 | 0 | 68.82%
Category 7: Portfolio Support
Regulatory Policy & Program Support (Gen. Admin.) | 37208 | 42548 | 57579 | 51549 | 49262 | 42520.36 | 37597.16 | 46096.33 | 0 | 0 | 0 | 0 | 364359.85 | 1902021.85 | 3929000 | -166000 | 48.41%
IT Infrastructure & Systems Support | 120524 | 107796 | 152214 | 150024 | 74804 | 506283.61 | 38850.83 | 52255.11 | 0 | 0 | 0 | 0 | 1202751.55 | 6464922.55 | 8514000 | 566000 | 75.93%
EM&V | 23262 | 81327 | 69734 | 49413 | 35721 | 33500.62 | 87598.66 | 49483.81 | 0 | 0 | 0 | 0 | 430040.09 | 2555915.09 | 5200600 | -400000 | 49.15%
DR Potential Study | 3379 | 24799 | 0 | 0 | 0 | 103866.39 | 0 | 0 | 0 | 0 | 0 | 0 | 132044.39 | 371500.39 | 1000000 | 0 | 37.15%
Budget Category 7 Total | 184373 | 256470 | 279527 | 250986 | 159787 | 686170.98 | 164046.65 | 147835.25 | 0 | 0 | 0 | 0 | 2129195.88 | 11294359.88 | 18643600 | 0 | 60.58%
Total Incremental Cost | 661763 | 453342 | 802978 | 450663 | 333352 | 1280366.66 | 361678.04 | 398945 | 0 | 0 | 0 | 0 | 4743087.7 | 31652680.36 | 83088102 | 0 | 38.1%
Notes:
1 BIP total does not include April bill credits as a result of Reporting outages related to Envision Cross Over.
2 BIP April total of $6,695 was revised to include April bill credits of $1,935 that were posted in a different reporting period as a result of the Envision Cross Over.
3 May credits are a result of accrual reversals that occurred in prior reporting period (April).
4 June BIP incentives were adjusted to exclude $783.50 that was reversed in Envision.
5 July Credits are due to labor reversals.
6 CBP Residential Pilot was approved in D.21.03.056, Decision Directing Pacific Gas and Electric Company, Southern California Edison Company, and San Diego Gas & Electric Company to take actions to prepare for potential extreme weather in the summers of 2021 and 2022.
(End of page)
2021 Expenditures

## Fund Shift Log
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
FUND SHIFT LOG
Program Cycle to Date (2018 - 2021)
Program Category | Fund Shift | Programs Impacted | Date | Rationale for Fund Shift
Category 1: Supply Side DR Programs | -234498 | Capacity Bidding Program (CBP) | 2018-07-21 | Per Resolution E-4906 (issued 7/21/18), Ordering Paragraph 30 approved a total fund shift of $934,498 of which $234,498 shifted from the Capacity Bidding Program to support the Back Up Generators (BUGs) prohibited resources restrictions.
Category 4: Emerging & Enabling Technologies | -700000 | Technology Incentives (TI) | 2018-07-21 | Per Resolution E-4906 (issued 7/21/18), Ordering Paragraph 30 approved a total fund shift of $934,498 of which $700,000 to be shifted from the Technology Incentives Program to support the Back Up Generators (BUGs) prohibited resources restrictions.
Category 7: Portfolio Support | -194400 | EM&V | 2018-07-23 | Per SDG&E's AL 3031-E-B (filed July 23, 2018) a total of $194,400 to be shifted from EM&V funds for the cost to test the installation of loggers, meters and the cost of the verification administrator to support the Back Up Generators (BUGs) prohibited resources restrictions.
AMDRMA | 1128898 | Back Up Generation Resources (BUGs) | 2018-07-21 | Per Resolution E-4906 (issued 7/21/18), Ordering Paragraph 30 approved a total fund shift of $934,498 to support the Back Up Generators (BUGs) prohibited resources restrictions. Per SDG&E's AL 3031-E-B (filed July 23, 2018) a total of $194,400 to be shifted from EM&V funds for the cost to test the installation of loggers, meters and the cost of the verification administrator to support the Back Up Generators (BUGs) prohibited resources restrictions.
Category 7: Portfolio Support | -166000 | Regulatory Policy & Program Support (Gen. Admin.) | 2020-08-18 | Shifting the funds to IT will allow SDG&E to properly maintain systems to ensure compliance and customer experience. IT is projected to be overspent; M&E and Policy (Gen Admin) have unspent dollars that can be applied towards the IT shortfall.
Category 7: Portfolio Support | -400000 | EM&V | 2020-08-18 | Shifting the funds to IT will allow SDG&E to properly maintain systems to ensure compliance and customer experience. IT is projected to be overspent; M&E and Policy (Gen Admin) have unspent dollars that can be applied towards the IT shortfall.
Category 7: Portfolio Support | 566000 | IT Infrastructure & Systems Support | 2020-08-18 | Shifting the funds to IT will allow SDG&E to properly maintain systems to ensure compliance and customer experience. IT is projected to be overspent; M&E and Policy (Gen Admin) have unspent dollars that can be applied towards the IT shortfall.
Total | 0
Notes:
- All Fund Shifting Rules remain in effect as adopted in D.12-04-045 as referenced in D.17-12-003 at page 131.
(End of page)

## SDGE Costs - AMDRMA Balance
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
TOTAL COST AND AMDRMA ACCOUNT BALANCES ($000)
August 2021
Annual Total Cost | January | February | March | April | May | June | July | August | September | October | November | December | Year-to-Date Cost
Administrative (O&M)
AC Saver Day‐Ahead | 5.434 | 8.364 | 10.848 | 10.628 | 12.351 | 13.272 | 11.591 | 11.098 | 0 | 0 | 0 | 0 | 83.586 | 0 | 0
AC Saver Day‐Of | 44.155 | 11.639 | 76.114 | 45.377 | 41.934 | 48.671 | 50.157 | 45.191 | 0 | 0 | 0 | 0 | 363.238
Base Interruptible Program (BIP) | 5.372 | 5.443 | 5.997 | 6.695 | 5.654 | 6.054 | 4.821 | 5.652 | 0 | 0 | 0 | 0 | 45.688
Back Up Generators (BUGs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capacity Bidding Program (CBP) | 6.528 | 9.156 | 9.539 | 17.847 | 16.437 | 18.691 | 15.735 | 14.573 | 0 | 0 | 0 | 0 | 108.506
Demand Response Auction Mechanism (DRAM) | 10.265 | 9.854 | 13.487 | 12.322 | 28.375 | 11.579 | 25.823 | 2.95 | 0 | 0 | 0 | 0 | 114.655
Emerging Tech (ET) | 22.999 | 17.65 | 50.08 | 21.035 | 41.123 | 14.077 | 15.606 | 16.999 | 0 | 0 | 0 | 0 | 199.569
Technology Deployment (TD) | 11.461 | 10.833 | 13.04 | 20.324 | 12.916 | 14.783 | 13.433 | 15.829 | 0 | 0 | 0 | 0 | 112.619
Technology Incentives (TI) | 7.418 | 9.018 | 9.929 | 25.263 | 7.642 | 10.083 | 8.791 | 9.782 | 0 | 0 | 0 | 0 | 87.926
Armed Forces Pilot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Over Gen Pilot 8 | 1.681 | 1.873 | 2.679 | 2.442 | 2.098 | 0.777 | -1.987 | 0 | 0 | 0 | 0 | 0 | 9.563
Small Business Energy Management Pilot (SBEMP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CBP Res Pilot 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.057 | 0 | 0 | 0 | 0 | 4.057
Constrained Local Capacity Program (CLCP) | 111.344 | 1.498 | 2.143 | 1.953 | 1.678 | 0.622 | 3.35 | 1.603 | 0 | 0 | 0 | 0 | 124.191
Local Marketing Education & Outreach (LMEO) | 2.75 | 0 | 40.412 | 1.641 | 43.449 | 130.793 | 27.632 | 106.979 | 0 | 0 | 0 | 0 | 353.656
General Admin | 37.208 | 42.548 | 57.579 | 51.549 | 49.263 | 43.06 | 37.057 | 46.096 | 0 | 0 | 0 | 0 | 364.36
IT | 120.524 | 107.796 | 152.214 | 150.024 | 74.804 | 506.284 | 38.851 | 52.255 | 0 | 0 | 0 | 0 | 1202.752
EM&V | 23.262 | 81.327 | 69.734 | 49.413 | 35.181 | 33.501 | 88.139 | 49.484 | 0 | 0 | 0 | 0 | 430.041
DR Potential Study | 3.379 | 24.799 | 0 | 0 | 0 | 103.866 | 0 | 0 | 0 | 0 | 0 | 0 | 132.044
Local Capacity Requirements (LCR) 1 | 55.296 | -33.178 | 56.866 | 0 | 8.942 | 59.112 | 0 | 0 | 0 | 0 | 0 | 0 | 147.038
SW-COM 9 | 22.979 | 1.4 | 1.101 | 1.042 | 0.947 | 0.916 | -0.193 | 0.277 | 0 | 0 | 0 | 0 | 28.469
SW-IND | 8.077 | 40.624 | 2.505 | 10.302 | 0.998 | 0.207 | 1.411 | 13.917 | 0 | 0 | 0 | 0 | 78.041
SW-AG | 0.072 | 1.652 | 0.844 | 0.083 | 0.856 | 1.637 | 0.159 | 0.092 | 0 | 0 | 0 | 0 | 5.395
Local Marketing Res and Non-Res | 11.85 | 31.485 | 36.584 | 25.762 | 10.907 | 9.893 | 8.823 | 11.628 | 0 | 0 | 0 | 0 | 146.932
IDSM DR COM 1,2 | 3.212 | -50.23 | -2.179 | 0 | 58.035 | 35.96 | 163.944 | 0 | 0 | 0 | 0 | 0 | 208.742
Behavioral | 0 | 544.18 | 285.537 | 285.326 | 185.326 | 235.326 | 248.402 | 248.402 | 0 | 0 | 0 | 0 | 2032.499
Total Administrative (O&M) | 515.266 | 877.731 | 895.053 | 739.028 | 638.916 | 1299.164 | 761.545 | 656.864 | 0 | 0 | 0 | 0 | 6383.567
Customer Incentives
AC Saver Day‐Ahead | 124.98 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.02 | 0 | 0 | 0 | 0 | 125.08
AC Saver Day‐Of | 0.242 | 0.216 | 0.324 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.982
Base Interruptible Program (BIP) 3,4 | 18.131 | 0 | 19.27 | 0 | 1.9 | 2.067 | 2.75 | 0.005 | 0 | 0 | 0 | 0 | 44.123
Capacity Bidding Program (CBP) 10 | 0 | 0 | 0 | 3.063 | 0 | 0 | 15.328 | -6.711 | 0 | 0 | 0 | 0 | 11.68
Demand Response Auction Mechanism (DRAM) 5,9 | 86.581 | 95.628 | 254.01 | 11.034 | -47.727 | 308.979 | -10.928 | 2.687 | 0 | 0 | 0 | 0 | 700.264
Technology Deployment (TD) | 18.05 | 15.7 | 15.3 | 20.05 | 5.5 | 13.75 | 15.45 | 20.4 | 0 | 0 | 0 | 0 | 124.2
Technology Incentives (TI) | 0 | 0 | 0.276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.276
Armed Forces Pilot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Small Business Energy Management Pilot (SBEMP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EM&V 6 | 0 | 0 | 0 | 0 | 0.54 | 0 | -0.54 | 0 | 0 | 0 | 0 | 0 | 0
General Admin 7 | 0 | 0 | 0 | 0 | 0 | -0.54 | 0.54 | 0 | 0 | 0 | 0 | 0
CPPD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Customer Incentives | 247.984 | 111.544 | 289.18 | 34.147 | -39.587 | 324.256 | 22.68 | 16.401 | 0 | 0 | 0 | 0 | 1006.605
Total | 763.25 | 989.275 | 1184.233 | 773.175 | 599.329 | 1623.42 | 784.225 | 673.265 | 0 | 0 | 0 | 0 | 7390.172
AMDRMA Account End of Month Balance for Monthly Activity with Interest | 763.291 | 989.38 | 1184.389 | 773.397 | 599.53 | 1623.633 | 784.489 | 673.618 | 0 | 0 | 0 | 0 | 7391.727
Notes:
1 February credits are related to accrual reversals related to a prior period expense (January 2021).
2 March Credit is related to a discount received on services purchased in a prior period.
3 April Bill credits for BIP were not posted as a result of Reporting outages related to Envision Cross Over.
4 BIP April Incentive total was revised to include April bill credits of $1,935 that were posted in a different reporting period as a result of the Envision Cross Over. June BIP incentives were adjusted to exclude $783.50 that was reversed in Envision.
5 May incentive credits are a result of accrual reversals that occurred in prior reporting period (April).
6 EM&V charges for May include a misclassification of incentive payment. This charge is pending a journal entry to reclassify $540 to the correct cost type and will be reflected in June Report.
7 EM&V charges for May include a misclassification of incentive payment, charge was corrected using incorrect program IO to reclassify $540 to the correct cost type. Correction will be reflected in July Reporting.
8 July Credits are due to labor reversals.
9 July Credits are due to accrual reversals.
10 August Credit it related to Journal Entry Corrections
11CBP Residential Pilot was approved in D.21.03.056, Decision Directing Pacific Gas and Electric Company, Southern California Edison Company, and San Diego Gas & Electric Company to take actions to prepare for potential extreme weather in the summers of 2021 and 2022.
(End of page)

## SDGE Costs -GRC
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
GENERAL RATE CASE PROGRAMS ($000)
August 2021
Annual Total Cost | January | February | March | April | May | June | July | August | September | October | November | December | Year-to-Date Total Cost
Programs in General Rate Case
Administrative (O&M)
CPP-D 1 | 2.012 | 2.296 | 3.038 | 4.974 | 4.119 | 6.5 | -1.461 | 2.108 | 0 | 0 | 0 | 0 | 23.586
SLRP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Peak Generation (RBRP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Administrative (O&M) | 2.012 | 2.296 | 3.038 | 4.974 | 4.119 | 6.5 | -1.461 | 2.108 | 0 | 0 | 0 | 0 | 23.586
Capital
Peak Generation (RBRP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capital | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Measurement and Evaluation
Peak Generation (RBRP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total M&E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer Incentives
BIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SLRP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Peak Generation (RBRP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Customer Incentives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Revenue from Penalties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total GRC Program Costs | 2.012 | 2.296 | 3.038 | 4.974 | 4.119 | 6.5 | -1.461 | 2.108 | 0 | 0 | 0 | 0 | 23.586
1 July credits are due to accrual reversals and labor corrections.
(End of page)

## SDGE Costs -DPDRMA
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE PROGRAMS
DIRECT PARTICIPATION DR MEMO ACCOUNT ($000)
August 2021
Annual Total Cost | January | February | March | April | May | June | July | August | September | October | November | December | Year-to-Date Total Cost
Programs in Direct Participation Demand Response Memorandum Account (DPDRMA)
Administrative (O&M)
Rule 32 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 210
Rule 32 Operations 2 | 32.535 | 51.665 | 37.147 | 27.42 | 29.666 | 29.3 | 29.231 | 19.877 | 0 | 0 | 0 | 0 | 256.841
Rule 32 Meter 4 | -9.125 | 3.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.083
Rule 32 CISR Enhancement 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rule 32 Click-Through 1,5 | 1.773 | 0.465 | 1.005 | 22.388 | 13.225 | 12.7 | -1.939 | 19.012 | 0 | 0 | 0 | 0 | 68.629
Total Administrative (O&M) | 25.183 | 55.172 | 38.152 | 49.808 | 42.891 | 252 | 27.292 | 38.889 | 0 | 0 | 0 | 0 | 529.387
Capital Related Costs
Depreciation | 43.359 | 43.359 | 43.359 | 43.359 | 43.347 | 43.3 | 43.347 | 43.347 | 0 | 0 | 0 | 0 | 346.777
DPDRMA Tax | 18.229 | 11.869 | 21.67 | 18.1 | 18.011 | 17.9 | 17.843 | 17.758 | 0 | 0 | 0 | 0 | 141.38
DPDRMA Property Tax | 1.773 | 1.773 | 1.773 | 1.773 | 1.773 | 1.8 | 1.164 | 1.164 | 0 | 0 | 0 | 0 | 12.993
Return on Rate Base | 5.037 | 4.765 | 4.492 | 4.219 | 3.946 | 3.7 | 3.401 | 3.128 | 0 | 0 | 0 | 0 | 32.688
Total Capital | 68.398 | 61.766 | 71.294 | 67.451 | 67.077 | 66.7 | 65.755 | 65.397 | 0 | 0 | 0 | 0 | 533.838
Measurement and Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total M&E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer Incentives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Customer Incentives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Revenue from Penalties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total DPDRMA Program Costs | 93.581 | 116.938 | 109.446 | 117.259 | 109.968 | 318.7 | 93.047 | 104.286 | 0 | 0 | 0 | 0 | 1063.225
Total DPDRMA Program Costs with Interest | 93.631 | 116.951 | 109.464 | 117.284 | 109.993 | 318.729 | 93.085 | 104.337 | 0 | 0 | 0 | 0 | 1063.474
Notes:
1 Rule 32 click-through was approved in Decision 17-06-005.
2 Rule 32 Operations was approved in AL 3191-E.
3 Rule 32 CISR Enhancement was approved in AL 3136-E.
4 January credit is related to labor corrections and labor accrual reversals related to a prior period expense (December 2020).
5 July Credits are due to accrual reversals.
(End of page)

## SDGE Costs -ELRP
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON INTERRUPTIBLE LOAD AND DEMAND RESPONSE EMERGENCY
LOADSHED REDUCTION PROGRAM (ELRP) BALANCING ACCOUNT ($000)
August 2021
Annual Total Cost | January | February | March | April | May | June | July | August | September | October | November | December | Year-to-Date Total Cost
Program in Emergency Load shed Reduction Balancing Account
Administrative (O&M)
ELRP | 0 | 0 | 0 | 0 | 0 | 0 | 10.2925 | 4.591 | 0 | 0 | 0 | 0 | 14.8835
Total Administrative (O&M) | 0 | 0 | 0 | 0 | 0 | 0 | 10.2925 | 4.591 | 0 | 0 | 0 | 0 | 14.8835
Capital Related Costs
Depreciation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELRP Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELRP Property Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Return on Rate Base | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capital | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Measurement and Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total M&E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer Incentives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Customer Incentives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Revenue from Penalties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total ELRP Program Costs | 0 | 0 | 0 | 0 | 0 | 0 | 10.2925 | 4.591 | 0 | 0 | 0 | 0 | 14.8835
Total ELRP Program Costs with Interest | 0 | 0 | 0.018 | 0.025 | 0.025 | 0.029 | 10.3305 | 4.592 | 0 | 0 | 0 | 0 | 15.0195
0
Notes:
ELRP was approved in Decision 21.02.006.
(End of page)

## SDGE Costs -CSEP
SAN DIEGO GAS & ELECTRIC COMPANY REPORT ON CALIFORNIA STATE EMERGENCY PROGRAM
August 2021
Annual Total Cost | January | February | March | April | May | June | July | August | September | October | November | December | Year-to-Date Total Cost
Program Expenses Related To CSEP
Administrative (O&M)
CSEP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.921 | 0 | 0 | 0 | 0 | 11.921
Total Administrative (O&M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.921 | 0 | 0 | 0 | 0 | 11.921
Capital Related Costs
Depreciation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSEP Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSEP Property Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Return on Rate Base | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Capital | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Measurement and Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total M&E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer Incentives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Customer Incentives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Revenue from Penalties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total CSEP Program Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.921 | 0 | 0 | 0 | 0 | 11.921
Total CSEP Program Costs with Interest - NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.921 | 0 | 0 | 0 | 0 | 11.921
0
Notes:
CSEP implemented as a result of the CA Governor Emergency Proclamation.
(End of page)