## Data for Questions 2 and 4
Number | App Submit Date | Order Create Date | First Design Completion | Last Design Completion | Design Status | Contract Received | Contract Status | Dependencies Cleared | Dependencies Status | Customer Ready Date | Customer Ready Status | Construction Completion | Construction Status | Rule Category | Intake CT | Design CT | Contract CT | Dependency CT | Customer Ready CT | Construction CT | E2E CT
3 | 2007-12-12 | 2008-02-21 | 2016-06-01 | 2016-06-01 | COMP | 2017-03-21 | COMP | 2017-06-15 | COMP | 2022-07-16 | INPR | 2021-03-03 | COMP | Rule 16 | 48 | 2080 | 202 | 62 |  |  | 3320
4 | 2007-12-12 | 2008-02-21 | 2016-06-18 | 2016-06-18 | COMP | 2017-03-21 | COMP | 2017-06-19 | COMP | 2023-04-15 | INPR | 2021-02-08 | COMP | Rule 16 | 48 | 2092 | 189 | 64 |  |  | 3304
14 | 2007-12-20 | 2009-09-23 | 2009-10-01 | 2009-10-01 | COMP | 2009-10-22 | COMP |  |  |  |  | 2021-08-03 | COMP | Rule 16 | 443 | 7 | 16 |  |  |  | 3421
5 | 2008-04-25 | 2008-06-07 | 2009-05-12 | 2009-05-12 | COMP | 2009-05-12 | COMP |  |  | 2020-04-04 | INPR | 2020-03-04 | COMP | Other | 30 | 233 | 1 |  |  |  | 2976
11 | 2008-06-16 | 2009-04-28 | 2009-11-02 | 2009-11-02 | COMP | 2010-10-01 | COMP | 2023-12-02 | COMP | 2012-05-11 | COMP | 2021-05-25 | COMP | Rule 16 | 218 | 132 | 230 | 3306 | 0 |  | 3251
8 | 2008-07-10 | 2008-09-17 | 2009-08-09 | 2009-08-09 | COMP | 2011-01-19 | COMP | 2021-11-14 | COMP | 2021-11-14 | INPR | 2019-02-11 | COMP | Rule 15/16 | 49 | 224 | 361 | 2721 |  |  | 2658
6 | 2008-07-21 | 2008-08-04 | 2020-07-29 | 2010-02-02 | COMP | 2020-08-22 | REQD | 2020-08-22 | REQD |  |  | 2020-05-21 | COMP | Other | 11 | 3011 |  |  |  |  | 2973
9 | 2008-08-27 | 2008-11-06 | 2009-03-24 | 2009-03-24 | COMP | 2009-03-24 | COMP |  |  | 2020-07-04 | REQD | 2020-05-04 | COMP | Other | 51 | 92 | 1 |  |  |  | 2933
7 | 2008-09-05 | 2008-09-06 | 2010-03-08 | 2010-03-08 | COMP | 2010-04-28 | COMP | 2010-05-10 | COMP | 2013-09-09 | COMP | 2020-06-29 | COMP | Rule 16 | 1 | 374 | 38 | 9 | 839 | 1709 | 2966
10 | 2009-02-24 | 2009-03-11 | 2009-08-19 | 2009-08-19 | COMP | 2009-12-14 | COMP |  | COMP | 2022-05-10 | COMP | 2022-07-15 | COMP | Rule 15/16 | 12 | 114 | 80 |  |  |  | 3366
12 | 2009-07-23 | 2009-07-29 | 2009-09-14 | 2009-09-14 | COMP | 2009-09-23 | COMP |  | COMP |  | INPR | 2019-04-19 | COMP | Rule 16 | 5 | 33 | 8 |  |  |  | 2446
13 | 2009-07-23 | 2009-07-29 | 2010-02-12 | 2010-02-12 | COMP | 2010-02-23 | COMP | 2019-09-21 | COMP | 2019-09-21 | REQD | 2019-05-15 | COMP | Rule 15/16 | 5 | 136 | 7 | 2408 |  |  | 2464
146 | 2009-08-11 | 2014-10-21 | 2015-01-27 | 2018-11-21 | COMP | 2018-10-17 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-03-16 | COMP | Rule 15/16 | 1306 | 65 |  | 25 | 1 | 77 | 2408
25 | 2009-09-02 | 2011-07-29 | 2012-06-16 | 2012-06-16 | COMP | 2013-01-28 | COMP | 2013-01-16 | COMP | 2020-05-16 | REQD | 2020-04-09 | COMP | Rule 15/16 | 478 | 222 | 154 |  |  |  | 2661
15 | 2010-04-20 | 2010-04-20 | 2011-02-24 | 2017-09-11 | COMP | 2017-10-04 | COMP | 2012-05-14 | COMP | 2017-08-09 | COMP | 2019-05-03 | COMP | Rule 16 | 1 | 213 | 18 |  | 1318 | 435 | 2271
16 | 2010-04-20 | 2010-04-20 | 2011-02-17 | 2017-09-11 | COMP | 2017-09-29 | COMP | 2012-05-14 | COMP | 2017-08-09 | COMP | 2019-05-03 | COMP | Rule 16 | 1 | 209 | 15 |  | 1318 | 435 | 2271
17 | 2010-06-04 | 2010-09-10 | 2010-10-05 | 2010-10-05 | COMP | 2010-10-01 | COMP | 2020-04-25 | REQD | 2020-04-25 | REQD | 2020-04-15 | COMP | Rule 16 | 69 | 18 |  |  |  |  | 2477
18 | 2010-08-24 | 2010-10-18 | 2013-06-17 | 2013-06-17 | COMP | 2016-06-03 | COMP | 2014-08-18 | COMP | 2016-08-25 | COMP | 2021-04-12 | COMP | Rule 15/16 | 39 | 669 | 745 |  | 509 | 1162 | 2670
19 | 2010-11-08 | 2010-11-20 | 2011-03-23 | 2011-03-23 | COMP | 2011-04-22 | COMP | 2011-04-25 | COMP |  |  | 2019-05-30 | COMP | Rule 15/16 | 9 | 82 | 23 | 2 |  |  | 2148
20 | 2010-12-16 | 2011-04-05 | 2015-08-22 | 2015-08-22 | COMP | 2019-05-13 | COMP | 2017-01-23 | COMP | 2019-04-26 | COMP | 2019-06-14 | COMP | Rule 16 | 75 | 1103 | 934 |  | 569 | 35 | 2134
21 | 2011-02-25 | 2011-04-29 | 2020-06-12 | 2011-05-09 | COMP |  |  |  |  | 2023-02-25 | INPR | 2021-07-30 | COMP | Other | 46 | 2292 |  |  |  |  | 2622
29 | 2011-03-03 | 2012-04-24 | 2013-10-30 | 2018-03-07 | COMP | 2018-10-31 | COMP | 2018-12-13 | COMP | 2023-04-22 | INPR | 2022-02-24 | COMP | Rule 16 | 289 | 385 | 168 | 29 |  |  | 2761
22 | 2011-05-24 | 2011-06-04 | 2013-06-19 | 2013-06-19 | COMP | 2016-02-23 | COMP | 2016-02-23 | COMP | 2019-10-03 | INPR | 2019-01-11 | COMP | Rule 16 | 8 | 514 | 671 | 1 |  |  | 1918
23 | 2011-05-24 | 2011-06-04 | 2013-06-19 | 2016-12-01 | COMP |  | INPR | 2017-06-01 | COMP | 2020-05-05 | COMP | 2020-05-06 | COMP | Rule 16 | 8 | 514 |  | 127 | 735 | 2 | 2249
1346 | 2011-05-31 | 2017-05-16 | 2017-05-25 | 2017-05-25 | COMP | 2017-11-02 | COMP | 2017-11-02 | COMP |  | INPR | 2021-04-11 | COMP | Rule 16 | 1499 | 8 | 113 | 1 |  |  | 2478
24 | 2011-07-07 | 2011-07-22 | 2011-08-15 | 2011-08-15 | COMP | 2012-01-03 | COMP | 2012-01-03 | COMP |  | INPR | 2021-06-23 | COMP | Rule 16 | 12 | 17 | 96 | 1 |  |  | 2504
106 | 2011-10-04 | 2014-05-08 | 2014-10-13 | 2014-10-13 | COMP | 2015-09-23 | COMP | 2015-09-24 | COMP | 2016-10-28 | COMP | 2019-05-04 | COMP | Rule 15/16 | 652 | 110 | 238 | 2 | 277 | 630 | 1904
26 | 2011-10-27 | 2011-12-16 | 2014-11-10 | 2014-11-10 | COMP | 2018-06-21 | COMP | 2015-03-30 | COMP | 2020-10-12 | COMP | 2020-11-18 | COMP | Rule 16 | 34 | 731 | 907 |  | 1395 | 27 | 2277
50 | 2011-12-27 | 2013-04-02 | 2013-06-20 | 2013-06-20 | COMP | 2013-09-12 | NOTN | 2013-10-08 | COMP | 2013-09-12 | COMP | 2023-07-03 | COMP | Other | 319 | 57 |  | 77 | 0 | 2444 | 2894
28 | 2012-02-29 | 2012-04-20 | 2012-05-08 | 2012-05-08 | COMP | 2012-07-18 | COMP | 2014-10-03 | COMP | 2019-06-29 | REQD | 2019-04-25 | COMP | Rule 16 | 38 | 13 | 50 | 558 |  |  | 1799
37 | 2012-03-12 | 2012-11-12 | 2014-10-15 | 2014-10-15 | COMP | 2014-11-06 | COMP | 2014-11-03 | COMP | 2020-10-31 | INPR | 2020-07-26 | COMP | Rule 15/16 | 173 | 484 | 17 |  |  |  | 2106
27 | 2012-03-19 | 2012-04-09 | 2012-10-02 | 2012-10-02 | COMP | 2018-06-06 | COMP | 2018-08-02 | COMP | 2018-11-16 | COMP | 2019-01-04 | COMP | Rule 16 | 16 | 124 | 1426 | 41 | 75 | 32 | 1709
31 | 2012-04-03 | 2012-05-23 | 2012-06-22 | 2012-06-22 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2020-03-16 | COMP | 2020-08-04 | COMP | Rule 16 | 37 | 22 | 1761 | 1 | 180 | 101 | 2097
51 | 2012-04-13 | 2013-04-02 | 2013-05-31 | 2013-05-31 | COMP | 2014-06-10 | COMP | 2013-10-08 | COMP | 2019-10-19 | INPR | 2019-06-21 | COMP | Rule 16 | 244 | 43 | 258 |  |  |  | 1807
32 | 2012-04-25 | 2012-05-25 | 2012-07-16 | 2012-07-16 | COMP | 2018-09-27 | COMP | 2012-08-08 | COMP | 2019-04-23 | COMP | 2019-06-25 | COMP | Rule 16 | 23 | 35 | 1560 |  | 1684 | 45 | 1801
30 | 2012-05-07 | 2012-05-14 | 2012-09-13 | 2012-09-13 | COMP | 2013-01-07 | COMP | 2013-01-07 | COMP | 2019-08-31 | INPR | 2019-04-30 | COMP | Rule 16 | 6 | 86 | 79 | 1 |  |  | 1754
57 | 2012-05-16 | 2013-05-10 | 2014-01-10 | 2014-01-10 | COMP | 2014-02-11 | COMP | 2018-08-02 | INPR | 2018-07-23 | COMP | 2019-07-23 | COMP | Rule 15/16 | 249 | 168 | 22 |  |  |  | 1805
40 | 2012-05-25 | 2012-12-11 | 2014-03-24 | 2014-03-24 | COMP | 2014-03-28 | COMP | 2014-04-16 | COMP | 2019-07-27 | INPR | 2019-07-27 | COMP | Rule 16 | 138 | 321 | 5 | 14 |  |  | 1801
42 | 2012-07-25 | 2013-01-25 | 2013-02-19 | 2013-02-19 | COMP | 2013-05-20 | COMP | 2013-05-20 | COMP | 2019-04-30 | COMP | 2019-06-06 | COMP | Rule 16 | 127 | 17 | 65 | 1 | 1493 | 27 | 1725
33 | 2012-08-13 | 2012-08-14 | 2012-09-19 | 2018-11-05 | COMP | 2019-02-05 | COMP | 2019-08-22 | COMP | 2020-05-05 | COMP | 2020-10-16 | COMP | Rule 16 | 2 | 26 | 61 | 140 | 176 | 117 | 2057
34 | 2012-08-14 | 2012-09-10 | 2012-10-16 | 2012-10-03 | COMP | 2012-10-15 | COMP | 2012-10-16 | COMP | 2012-10-16 | COMP | 2019-08-12 | COMP | Rule 16 | 19 | 27 | 9 | 2 | 1 | 1713 | 1757
35 | 2012-08-30 | 2012-10-17 | 2012-11-10 | 2012-11-10 | COMP | 2014-05-08 | COMP | 2012-12-13 | COMP | 2022-08-21 | INPR | 2021-08-14 | COMP | Rule 16 | 34 | 18 | 373 |  |  |  | 2250
209 | 2012-09-04 | 2015-04-17 | 2016-04-06 | 2019-12-14 | COMP | 2020-09-28 | COMP | 2021-03-01 | COMP | 2021-02-25 | COMP | 2021-04-08 | COMP | Rule 15/16 | 658 | 244 | 200 | 104 | 0 | 29 | 2159
84 | 2012-09-10 | 2014-01-22 | 2015-06-24 | 2015-06-24 | COMP | 2015-09-21 | COMP | 2018-11-28 | COMP | 2019-01-15 | COMP | 2019-08-02 | COMP | Rule 15/16 | 343 | 359 | 62 | 801 | 33 | 140 | 1733
36 | 2012-09-19 | 2012-11-06 | 2013-03-18 | 2014-06-22 | COMP | 2015-08-10 | COMP | 2015-09-29 | COMP | 2019-04-20 | INPR | 2019-01-19 | COMP | Rule 16 | 35 | 89 | 285 | 36 |  |  | 1590
3073 | 2012-09-20 | 2018-03-06 | 2018-08-15 | 2018-08-15 | COMP | 2018-11-01 | COMP | 2019-03-04 | COMP | 2020-08-24 | COMP | 2020-10-14 | COMP | Rule 16 | 1369 | 115 | 56 | 81 | 375 | 37 | 2028
39 | 2012-10-08 | 2012-12-03 | 2013-03-14 | 2013-03-14 | COMP | 2013-05-07 | COMP | 2013-06-05 | COMP | 2016-07-15 | COMP | 2021-04-04 | COMP | Rule 15/16 | 39 | 70 | 39 | 21 | 782 | 1185 | 2131
46 | 2012-11-06 | 2013-02-27 | 2013-03-13 | 2013-03-13 | COMP | 2013-05-24 | COMP | 2013-06-10 | COMP | 2013-12-16 | COMP | 2022-08-24 | COMP | Rule 16 | 76 | 11 | 53 | 11 | 131 | 2185 | 2462
44 | 2012-11-13 | 2013-02-14 | 2013-05-01 | 2013-05-01 | COMP | 2014-10-22 | COMP | 2014-10-22 | COMP | 2015-03-27 | COMP | 2019-04-23 | COMP | Rule 16 | 63 | 54 | 373 | 1 | 106 | 1024 | 1616
49 | 2012-11-19 | 2013-03-25 | 2015-05-19 | 2015-05-19 | COMP | 2018-03-07 | COMP | 2018-04-20 | COMP | 2020-04-25 | INPR | 2020-01-06 | COMP | Rule 15/16 | 85 | 542 | 703 | 33 |  |  | 1788
38 | 2012-11-28 | 2012-11-30 | 2012-12-01 | 2012-12-02 | COMP | 2013-01-03 | COMP | 2015-04-30 | COMP | 2015-04-30 | COMP | 2023-12-28 | COMP | Rule 16 | 3 | 1 | 22 | 584 | 1 | 2176 | 2783
52 | 2012-12-18 | 2013-04-03 | 2013-07-17 | 2020-07-14 | COMP | 2020-07-16 | COMP | 2020-08-12 | COMP | 2020-08-31 | COMP | 2020-10-13 | COMP | Rule 16 | 73 | 74 | 3 | 20 | 14 | 31 | 1966
45 | 2013-01-08 | 2013-02-20 | 2013-08-09 | 2013-08-09 | COMP | 2013-08-23 | COMP | 2013-08-23 | COMP |  | INPR | 2022-02-09 | COMP | Rule 16 | 30 | 121 | 11 | 1 |  |  | 2285
47 | 2013-01-08 | 2013-03-15 | 2013-06-14 | 2013-06-14 | COMP | 2013-07-30 | COMP | 2013-08-05 | COMP | 2023-04-29 | INPR | 2022-02-17 | COMP | Rule 15/16 | 47 | 65 | 32 | 5 |  |  | 2291
41 | 2013-01-21 | 2013-01-23 | 2013-09-12 | 2013-09-12 | COMP | 2013-09-19 | COMP | 2013-09-25 | COMP | 2013-08-25 | COMP | 2020-11-05 | COMP | Rule 16 | 2 | 163 | 6 | 5 | 0 | 1789 | 1961
43 | 2013-02-06 | 2013-02-07 | 2013-03-04 | 2013-03-04 | COMP | 2023-02-25 | REQD | 2023-02-25 | REQD | 2023-02-25 | REQD | 2019-05-31 | COMP | Rule 16 | 2 | 17 |  |  |  |  | 1587
19974 | 2013-02-15 | 2020-05-30 | 2020-06-23 | 2020-06-23 | COMP | 2020-08-18 | COMP | 2021-01-04 | COMP | 2021-01-07 | COMP | 2021-02-09 | COMP | Rule 15/16 | 1830 | 17 | 41 | 94 | 4 | 23 | 2005
48 | 2013-03-05 | 2013-03-18 | 2014-01-30 | 2014-01-30 | COMP | 2014-08-01 | COMP | 2021-09-21 | COMP | 2021-07-28 | COMP | 2021-11-15 | COMP | Rule 16 | 10 | 220 | 129 | 1794 | 0 | 39 | 2188
60 | 2013-03-05 | 2013-06-21 | 2013-07-24 | 2013-07-24 | COMP | 2013-08-02 | COMP | 2013-09-09 | COMP | 2017-04-28 | COMP | 2020-02-05 | COMP | Rule 16 | 78 | 23 | 8 | 26 | 914 | 695 | 1739
54 | 2013-03-11 | 2013-04-12 | 2013-05-17 | 2018-12-05 | COMP | 2019-03-14 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-04-25 | COMP | Rule 16 | 25 | 26 | 68 | 4 | 1 | 28 | 1540
65 | 2013-03-14 | 2013-09-05 | 2013-11-23 | 2020-12-03 | COMP | 2021-03-12 | COMP | 2021-03-12 | COMP | 2023-01-26 | COMP | 2023-06-08 | COMP | Rule 16 | 123 | 56 | 68 | 1 | 472 | 94 | 2573
53 | 2013-03-19 | 2013-04-05 | 2014-05-27 | 2014-05-27 | COMP | 2013-04-05 | NOTN | 2014-07-17 | COMP | 2014-08-05 | COMP | 2019-10-08 | COMP | Other | 14 | 287 |  | 37 | 14 | 1301 | 1649
75 | 2013-03-21 | 2013-12-12 | 2013-12-27 | 2013-12-26 | COMP | 2014-01-21 | COMP | 2014-01-21 | COMP | 2014-02-05 | COMP | 2019-07-22 | COMP | Rule 16 | 185 | 11 | 17 | 1 | 12 | 1372 | 1592
55 | 2013-03-25 | 2013-04-08 | 2013-07-05 | 2013-07-05 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-07-26 | COMP | 2020-10-16 | COMP | Rule 16 | 11 | 63 | 1663 | 1 | 111 | 59 | 1904
59 | 2013-04-01 | 2013-05-31 | 2013-12-30 | 2014-04-04 | COMP | 2017-11-20 | COMP | 2016-07-28 | COMP | 2020-06-16 | COMP | 2020-08-07 | COMP | Rule 15/16 | 44 | 146 | 914 |  | 976 | 39 | 1850
82 | 2013-04-04 | 2014-01-15 | 2014-04-28 | 2014-04-28 | COMP | 2014-05-21 | COMP | 2014-05-28 | COMP | 2014-09-11 | COMP | 2019-04-30 | COMP | Rule 15/16 | 197 | 72 | 18 | 5 | 75 | 1163 | 1525
56 | 2013-04-18 | 2013-04-25 | 2013-06-12 | 2013-06-12 | COMP | 2013-07-22 | COMP | 2013-07-26 | COMP | 2013-08-05 | COMP | 2021-02-09 | COMP | Rule 16 | 6 | 34 | 28 | 5 | 7 | 1887 | 1962
58 | 2013-04-25 | 2013-05-13 | 2013-06-29 | 2013-06-29 | COMP | 2013-09-03 | COMP | 2019-04-23 | INPR | 2019-05-30 | COMP | 2019-06-04 | COMP | Rule 16 | 13 | 34 | 45 |  |  |  | 1534
76 | 2013-04-29 | 2013-12-20 | 2014-01-29 | 2014-01-29 | COMP | 2014-04-01 | COMP | 2014-04-02 | COMP | 2020-12-05 | INPR | 2020-11-16 | COMP | Rule 16 | 164 | 26 | 44 | 2 |  |  | 1899
109 | 2013-05-07 | 2014-05-21 | 2015-08-08 | 2015-08-08 | COMP | 2015-10-14 | COMP | 2016-07-11 | COMP |  | INPR | 2021-09-29 | COMP | Rule 15/16 | 262 | 306 | 47 | 185 |  |  | 2111
1609 | 2013-05-22 | 2017-06-30 | 2017-12-22 | 2017-12-22 | COMP | 2019-05-16 | COMP | 2019-09-23 | COMP | 2019-08-28 | COMP | 2019-10-15 | COMP | Rule 15/16 | 1033 | 121 | 351 | 90 | 0 | 17 | 1608
236 | 2013-05-23 | 2015-07-30 | 2015-10-09 | 2018-10-01 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2021-03-10 | COMP | 2021-04-16 | COMP | Rule 16 | 549 | 51 | 62 | 1 | 551 | 28 | 1984
4389 | 2013-05-23 | 2017-11-09 | 2018-05-29 | 2018-05-29 | COMP | 2018-09-05 | COMP | 2018-09-05 | COMP | 2019-02-20 | COMP | 2019-04-02 | COMP | Rule 15/16 | 1124 | 136 | 70 | 1 | 114 | 30 | 1470
68 | 2013-05-30 | 2013-09-16 | 2013-11-07 | 2018-01-16 | COMP | 2018-04-26 | COMP | 2018-04-26 | COMP | 2018-11-09 | COMP | 2019-01-22 | COMP | Rule 16 | 76 | 39 | 72 | 1 | 139 | 47 | 1417
72 | 2013-05-31 | 2013-10-10 | 2013-11-05 | 2018-01-16 | COMP | 2018-04-26 | COMP | 2018-04-28 | COMP | 2021-03-03 | COMP | 2021-03-29 | COMP | Rule 15/16 | 93 | 19 | 72 | 2 | 714 | 19 | 1965
61 | 2013-06-19 | 2013-06-28 | 2013-07-26 | 2013-07-26 | COMP | 2013-11-19 | COMP | 2013-11-21 | INPR | 2014-04-09 | COMP | 2019-04-29 | COMP | Rule 15/16 | 8 | 20 | 81 |  |  |  | 1471
66 | 2013-06-19 | 2013-09-06 | 2013-10-02 | 2013-09-26 | COMP | 2013-10-28 | COMP | 2013-10-28 | COMP | 2014-01-22 | COMP | 2019-04-29 | COMP | Rule 16 | 56 | 19 | 23 | 1 | 57 | 1324 | 1471
69 | 2013-06-21 | 2013-09-19 | 2013-11-22 | 2013-11-22 | COMP | 2018-09-28 | COMP | 2018-09-28 | COMP | 2021-03-27 | REQD | 2020-03-11 | COMP | Rule 16 | 63 | 46 | 1218 | 1 |  |  | 1686
62 | 2013-06-24 | 2013-07-10 | 2016-10-21 | 2016-10-21 | COMP | 2017-03-21 | COMP | 2022-05-31 | COMP | 2022-05-27 | COMP | 2022-06-27 | COMP | Rule 16 | 12 | 827 | 102 | 1308 | 0 | 19 | 2264
3875 | 2013-07-08 | 2018-09-06 | 2018-09-25 | 2018-09-25 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-02-24 | COMP | 2020-02-25 | COMP | Rule 16 | 1299 | 14 | 336 | 1 | 18 | 2 | 1665
93 | 2013-07-10 | 2014-03-28 | 2017-10-28 | 2017-10-28 | COMP | 2018-02-05 | COMP | 2018-02-05 | COMP |  | INPR | 2022-05-04 | COMP | Rule 15/16 | 180 | 904 | 65 | 1 |  |  | 2217
88 | 2013-07-18 | 2014-02-08 | 2014-05-19 | 2014-05-19 | COMP | 2018-11-15 | COMP | 2014-07-09 | COMP | 2019-11-14 | COMP | 2019-12-06 | COMP | Rule 15/16 | 140 | 70 | 1131 |  | 1346 | 15 | 1604
89 | 2013-07-18 | 2014-02-08 | 2016-03-04 | 2016-03-04 | COMP | 2018-03-05 | COMP | 2018-03-06 | COMP | 2020-09-25 | COMP | 2021-03-02 | COMP | Rule 16 | 140 | 519 | 503 | 2 | 647 | 106 | 1913
70 | 2013-07-19 | 2013-10-04 | 2013-10-22 | 2013-10-22 | COMP | 2013-11-01 | COMP | 2013-11-01 | COMP | 2022-11-05 | INPR | 2021-10-02 | COMP | Rule 16 | 55 | 13 | 9 | 1 |  |  | 2062
63 | 2013-07-24 | 2013-08-08 | 2014-12-04 | 2014-12-04 | COMP | 2018-10-24 | COMP |  | REQD |  | INPR | 2022-10-04 | COMP | Rule 16 | 12 | 332 | 979 |  |  |  | 2312
64 | 2013-07-26 | 2013-08-20 | 2014-05-01 | 2017-09-21 | COMP | 2018-06-29 | COMP | 2018-12-04 | COMP | 2018-12-21 | COMP | 2019-03-18 | COMP | Rule 15/16 | 18 | 175 | 194 | 108 | 14 | 58 | 1415
270 | 2013-08-19 | 2015-10-05 | 2016-01-15 | 2016-01-15 | COMP | 2017-07-31 | COMP | 2018-01-08 | COMP | 2020-09-22 | COMP | 2020-10-28 | COMP | Rule 16 | 535 | 70 | 389 | 110 | 683 | 27 | 1809
139 | 2013-08-29 | 2014-09-25 | 2016-10-10 | 2018-07-07 | COMP | 2019-02-20 | COMP | 2019-02-21 | COMP | 2019-03-27 | COMP | 2019-03-13 | COMP | Rule 15/16 | 270 | 513 | 155 | 2 | 25 |  | 1388
141 | 2013-09-03 | 2014-10-02 | 2015-10-19 | 2017-10-17 | COMP | 2018-11-16 | COMP | 2019-03-07 | COMP | 2019-03-12 | COMP | 2019-05-07 | COMP | Rule 15/16 | 273 | 263 | 273 | 74 | 4 | 41 | 1425
67 | 2013-09-05 | 2013-09-12 | 2013-10-22 | 2013-10-22 | COMP | 2013-11-04 | COMP | 2013-11-04 | COMP | 2014-03-14 | COMP | 2020-11-18 | COMP | Rule 16 | 6 | 29 | 10 | 1 | 88 | 1682 | 1811
645 | 2013-09-30 | 2016-09-20 | 2016-11-14 | 2016-11-14 | COMP | 2018-01-03 | COMP | 2018-01-09 | COMP | 2019-08-21 | COMP | 2019-10-03 | COMP | Rule 15/16 | 747 | 39 | 285 | 5 | 408 | 31 | 1510
112 | 2013-10-01 | 2014-05-30 | 2015-10-06 | 2015-10-06 | COMP | 2015-12-02 | COMP | 2018-01-25 | COMP | 2022-10-20 | COMP | 2022-11-11 | COMP | Rule 16 | 166 | 341 | 39 | 540 | 1194 | 16 | 2291
214 | 2013-10-01 | 2015-05-07 | 2015-07-27 | 2015-07-27 | COMP | 2015-11-18 | COMP | 2018-01-02 | COMP | 2019-04-03 | COMP | 2019-04-18 | COMP | Rule 15/16 | 401 | 56 | 81 | 532 | 315 | 12 | 1392
215 | 2013-10-01 | 2015-05-07 | 2015-09-23 | 2015-09-23 | COMP | 2015-11-17 | COMP | 2018-01-02 | COMP | 2019-05-08 | COMP | 2019-06-25 | COMP | Rule 15/16 | 401 | 97 | 39 | 533 | 340 | 34 | 1439
83 | 2013-10-02 | 2014-01-16 | 2014-02-26 | 2014-02-26 | COMP | 2014-03-28 | COMP | 2014-04-17 | COMP | 2020-07-04 | INPR | 2019-05-02 | COMP | Rule 16 | 72 | 28 | 23 | 15 |  |  | 1401
71 | 2013-10-03 | 2013-10-07 | 2013-11-22 | 2013-11-16 | COMP | 2013-12-02 | COMP | 2013-12-02 | INPR | 2019-06-29 | REQD | 2019-04-22 | COMP | Rule 16 | 3 | 34 | 9 |  |  |  | 1392
97 | 2013-10-04 | 2014-04-09 | 2014-04-28 | 2014-04-28 | COMP | 2014-05-15 | COMP | 2014-05-15 | COMP | 2014-05-16 | COMP | 2019-11-25 | COMP | Rule 16 | 127 | 14 | 14 | 1 | 2 | 1389 | 1542
73 | 2013-10-10 | 2013-10-28 | 2017-07-25 | 2019-04-13 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-06-11 | COMP | 2019-10-01 | COMP | Rule 15/16 | 13 | 939 | 94 | 1 | 0 | 26 | 1500
85 | 2013-10-17 | 2014-01-27 | 2014-07-17 | 2014-07-17 | COMP | 2014-10-20 | COMP | 2014-10-22 | COMP |  | INPR | 2019-05-03 | COMP | Rule 15/16 | 67 | 121 | 67 | 3 |  |  | 1391
174 | 2013-10-22 | 2015-01-21 | 2015-11-19 | 2015-11-19 | COMP | 2018-01-09 | COMP | 2018-01-23 | COMP | 2018-11-07 | COMP | 2019-01-05 | COMP | Rule 15/16 | 311 | 212 | 536 | 10 | 203 | 38 | 1305
74 | 2013-10-23 | 2013-12-09 | 2014-02-11 | 2014-02-11 | COMP | 2014-03-06 | COMP | 2014-04-09 | COMP |  |  | 2019-07-15 | COMP | Rule 16 | 31 | 44 | 17 | 25 |  |  | 1436
92 | 2013-10-23 | 2014-03-21 | 2016-01-11 | 2016-01-11 | COMP | 2016-03-23 | COMP | 2016-05-04 | COMP |  | INPR | 2022-06-17 | COMP | Rule 15/16 | 101 | 454 | 51 | 31 |  |  | 2174
409 | 2013-10-24 | 2016-04-08 | 2016-06-02 | 2016-06-02 | COMP | 2016-07-06 | COMP | 2016-07-12 | COMP | 2016-08-12 | COMP | 2019-05-16 | COMP | Other | 615 | 39 | 24 | 5 | 24 | 693 | 1395
87 | 2013-10-25 | 2014-02-02 | 2014-06-19 | 2014-06-19 | COMP | 2016-06-10 | COMP | 2015-08-14 | COMP | 2020-01-28 | COMP | 2020-04-03 | COMP | Rule 16 | 65 | 97 | 497 |  | 1117 | 48 | 1615
108 | 2013-10-31 | 2014-05-14 | 2014-08-17 | 2014-08-17 | COMP | 2014-11-13 | COMP | 2014-11-13 | COMP | 2014-12-31 | COMP | 2019-07-31 | COMP | Rule 15/16 | 133 | 66 | 62 | 1 | 32 | 1152 | 1442
77 | 2013-11-06 | 2013-12-30 | 2014-07-17 | 2014-07-17 | COMP | 2014-09-26 | COMP | 2014-09-26 | COMP | 2018-04-27 | COMP | 2019-05-02 | COMP | Rule 16 | 35 | 139 | 51 | 1 | 900 | 255 | 1376
79 | 2013-11-06 | 2013-12-31 | 2014-01-31 | 2014-01-31 | COMP | 2014-02-21 | COMP | 2014-02-21 | COMP | 2014-05-16 | COMP | 2019-04-22 | COMP | Rule 16 | 36 | 22 | 15 | 1 | 61 | 1238 | 1368
173 | 2013-11-14 | 2015-01-15 | 2018-05-09 | 2018-05-09 | COMP | 2018-10-01 | COMP | 2021-02-23 | COMP | 2021-04-08 | COMP | 2021-08-03 | COMP | Rule 15/16 | 292 | 834 | 101 | 601 | 33 | 82 | 1938
105 | 2013-11-25 | 2014-05-02 | 2016-10-25 | 2017-06-03 | COMP | 2018-09-26 | COMP | 2019-07-25 | COMP | 2019-08-20 | COMP | 2020-06-01 | COMP | Rule 15/16 | 109 | 625 | 331 | 208 | 19 | 196 | 1635
78 | 2013-11-27 | 2013-12-31 | 2014-02-18 | 2014-02-18 | COMP | 2015-09-10 | COMP | 2016-08-26 | COMP | 2019-04-01 | COMP | 2019-04-23 | COMP | Rule 15/16 | 22 | 33 | 395 | 243 | 650 | 17 | 1355
94 | 2013-12-03 | 2014-03-31 | 2014-06-21 | 2014-06-21 | COMP | 2014-07-21 | COMP | 2014-07-21 | INPR | 2019-06-29 | REQD | 2019-04-18 | COMP | Rule 16 | 81 | 59 | 20 |  |  |  | 1350
80 | 2013-12-05 | 2014-01-10 | 2014-03-09 | 2014-03-09 | COMP | 2014-03-24 | COMP | 2019-11-23 | REQD | 2014-05-16 | COMP | 2019-07-23 | COMP | Rule 16 | 25 | 39 | 11 |  |  |  | 1414
110 | 2013-12-05 | 2014-05-22 | 2014-10-28 | 2017-10-19 | COMP | 2019-03-15 | COMP | 2017-10-31 | COMP | 2019-09-30 | COMP | 2019-11-06 | COMP | Rule 15/16 | 117 | 111 | 350 |  | 480 | 28 | 1489
4146 | 2013-12-17 | 2019-04-04 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-28 | COMP | 2019-05-29 | COMP | 2019-07-20 | COMP | 2019-12-05 | COMP | Rule 16 | 1330 | 16 | 23 | 2 | 37 | 95 | 1499
4228 | 2013-12-17 | 2019-09-12 | 2019-10-22 | 2019-10-22 | COMP | 2019-10-30 | COMP | 2019-11-18 | COMP | 2020-03-16 | COMP | 2020-03-19 | COMP | Rule 16 | 1442 | 29 | 7 | 13 | 80 | 4 | 1570
126 | 2013-12-18 | 2014-07-25 | 2014-09-30 | 2014-09-30 | COMP | 2014-11-17 | COMP | 2014-11-17 | COMP | 2022-06-29 | COMP | 2022-08-08 | COMP | Rule 16 | 152 | 47 | 34 | 1 | 1914 | 28 | 2171
360 | 2013-12-19 | 2016-01-25 | 2016-05-23 | 2016-05-23 | COMP | 2016-07-01 | COMP | 2016-07-05 | COMP | 2016-07-26 | COMP | 2021-04-09 | COMP | Rule 16 | 525 | 85 | 29 | 2 | 16 | 1183 | 1835
95 | 2013-12-27 | 2014-04-01 | 2014-07-10 | 2014-07-10 | COMP | 2018-09-28 | COMP | 2017-11-29 | COMP | 2020-12-11 | COMP | 2021-01-15 | COMP | Rule 16 | 65 | 71 | 1062 |  | 764 | 24 | 1772
235 | 2013-12-30 | 2015-07-30 | 2015-10-27 | 2015-10-27 | COMP | 2015-11-13 | COMP | 2016-01-13 | COMP | 2016-08-02 | COMP | 2021-02-11 | COMP | Rule 15/16 | 399 | 63 | 13 | 40 | 141 | 1138 | 1789
96 | 2014-01-03 | 2014-04-01 | 2017-02-18 | 2017-02-18 | COMP | 2017-06-27 | COMP | 2017-06-27 | COMP | 2020-07-25 | REQD | 2019-03-04 | COMP | Rule 15/16 | 61 | 726 | 90 | 1 |  |  | 1296
4184 | 2014-01-06 | 2019-06-05 | 2019-07-11 | 2019-07-11 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | 2019-11-04 | COMP | 2019-11-22 | COMP | Rule 15/16 | 1361 | 26 | 72 | 2 | 10 | 14 | 1480
81 | 2014-01-08 | 2014-01-13 | 2017-08-19 | 2017-08-19 | COMP | 2018-06-07 | COMP | 2018-06-18 | COMP | 2020-01-15 | COMP | 2020-03-09 | COMP | Rule 16 | 4 | 907 | 200 | 8 | 396 | 37 | 1548
86 | 2014-01-09 | 2014-01-30 | 2014-04-18 | 2018-04-23 | COMP | 2019-03-29 | COMP | 2014-08-08 | COMP | 2019-04-08 | COMP | 2019-05-29 | COMP | Rule 15/16 | 15 | 56 | 235 |  | 1170 | 37 | 1353
98 | 2014-01-27 | 2014-04-12 | 2014-09-13 | 2019-03-14 | COMP | 2019-08-06 | COMP | 2019-03-14 | INPR | 2023-04-15 | CANC | 2020-05-29 | COMP | Rule 15/16 | 54 | 107 | 102 |  |  |  | 1594
90 | 2014-02-14 | 2014-03-06 | 2014-03-30 | 2014-03-28 | COMP | 2014-03-30 | NOTN | 2014-03-30 | COMP | 2014-03-27 | NOTN | 2020-10-30 | COMP | Rule 16 | 14 | 17 |  | 1 |  |  | 1689
3234 | 2014-02-19 | 2018-03-26 | 2018-06-13 | 2018-06-13 | COMP | 2018-08-07 | COMP | 2018-11-29 | COMP | 2018-11-17 | COMP | 2019-01-04 | COMP | Rule 15/16 | 1030 | 57 | 39 | 79 | 0 | 25 | 1226
91 | 2014-03-05 | 2014-03-16 | 2014-04-30 | 2014-04-30 | COMP | 2014-05-23 | COMP | 2014-05-27 | COMP | 2022-01-29 | INPR | 2021-01-20 | COMP | Rule 16 | 8 | 33 | 18 | 2 |  |  | 1729
134 | 2014-03-05 | 2014-09-16 | 2015-07-02 | 2015-07-02 | COMP | 2016-02-25 | COMP | 2016-03-01 | COMP | 2020-03-21 | INPR | 2019-07-09 | COMP | Other | 137 | 200 | 162 | 4 |  |  | 1344
135 | 2014-03-05 | 2014-09-16 | 2015-07-02 | 2015-07-02 | COMP | 2016-02-25 | COMP | 2016-03-01 | COMP | 2020-03-21 | INPR | 2019-07-09 | COMP | Other | 137 | 200 | 162 | 4 |  |  | 1344
136 | 2014-03-05 | 2014-09-16 | 2015-07-02 | 2015-07-02 | COMP | 2016-02-25 | COMP | 2016-03-01 | COMP | 2016-08-08 | COMP | 2019-07-09 | COMP | Other | 137 | 200 | 162 | 4 | 113 | 733 | 1344
103 | 2014-03-12 | 2014-05-02 | 2014-06-23 | 2018-01-31 | COMP | 2018-06-06 | COMP | 2018-06-06 | COMP | 2022-04-01 | COMP | 2022-05-28 | COMP | Rule 16 | 38 | 36 | 89 | 1 | 962 | 41 | 2067
148 | 2014-03-15 | 2014-10-27 | 2015-01-16 | 2015-01-16 | COMP | 2016-09-12 | COMP | 2016-09-12 | COMP | 2019-12-28 | INPR | 2019-08-30 | COMP | Rule 15/16 | 158 | 55 | 417 | 1 |  |  | 1374
107 | 2014-03-20 | 2014-05-13 | 2017-10-15 | 2022-05-24 | COMP | 2022-06-29 | COMP | 2022-11-01 | COMP | 2022-08-16 | COMP | 2023-08-29 | COMP | Rule 15/16 | 39 | 862 | 25 | 88 | 0 | 206 | 2374
1467 | 2014-03-21 | 2017-06-07 | 2017-06-30 | 2017-06-30 | COMP | 2018-10-05 | COMP | 2018-10-29 | COMP | 2018-12-12 | COMP | 2019-02-11 | COMP | Rule 16 | 809 | 18 | 319 | 17 | 30 | 41 | 1229
104 | 2014-03-24 | 2014-05-02 | 2014-05-27 | 2014-05-27 | COMP | 2014-06-27 | COMP | 2014-06-27 | COMP | 2014-07-16 | COMP | 2019-05-08 | COMP | Rule 16 | 30 | 17 | 24 | 1 | 13 | 1209 | 1289
198 | 2014-03-24 | 2015-04-02 | 2015-04-29 | 2015-04-29 | COMP | 2015-04-24 | NOTN | 2020-02-13 | COMP | 2020-02-11 | COMP | 2020-07-06 | COMP | Other | 259 | 20 |  | 1204 | 0 | 101 | 1581
285 | 2014-03-24 | 2015-10-31 | 2015-11-20 | 2015-11-20 | COMP | 2016-02-17 | COMP | 2015-12-10 | COMP | 2016-02-17 | COMP | 2019-04-22 | COMP | Rule 16 | 407 | 14 | 58 |  | 46 | 800 | 1277
4069 | 2014-03-26 | 2019-01-08 | 2019-01-08 | 2019-01-08 | COMP | 2019-01-08 | NOTN | 2019-01-08 | COMP |  | INPR | 2019-06-18 | COMP | Other | 1203 | 1 |  | 1 |  |  | 1315
111 | 2014-04-02 | 2014-05-30 | 2015-02-09 | 2015-02-09 | COMP | 2015-06-03 | COMP | 2015-07-21 | COMP | 2015-10-02 | COMP | 2019-05-04 | COMP | Rule 15/16 | 42 | 174 | 81 | 34 | 53 | 900 | 1279
114 | 2014-04-02 | 2014-06-06 | 2015-12-04 | 2018-04-17 | COMP | 2019-03-21 | COMP | 2017-04-26 | COMP | 2020-06-30 | COMP | 2020-08-28 | COMP | Rule 15/16 | 47 | 376 | 233 |  | 799 | 44 | 1613
99 | 2014-04-03 | 2014-04-14 | 2014-05-19 | 2014-05-19 | COMP | 2014-05-28 | COMP | 2014-05-28 | COMP | 2020-01-18 | INPR | 2019-09-18 | COMP | Rule 16 | 8 | 26 | 7 | 1 |  |  | 1373
164 | 2014-04-03 | 2014-12-03 | 2017-06-09 | 2017-06-09 | COMP | 2018-02-28 | COMP | 2018-03-20 | COMP | 2018-03-20 | COMP | 2019-02-04 | COMP | Rule 15/16 | 169 | 634 | 180 | 15 | 1 | 221 | 1215
763 | 2014-04-09 | 2016-11-14 | 2017-05-01 | 2017-05-01 | COMP | 2017-06-08 | COMP | 2017-05-02 | COMP | 2017-05-02 | COMP | 2022-02-28 | COMP | Rule 16 | 655 | 116 | 28 |  | 1 | 1213 | 1983
116 | 2014-04-14 | 2014-06-12 | 2015-11-18 | 2018-03-19 | COMP | 2018-08-08 | COMP | 2018-09-07 | COMP | 2020-10-12 | COMP | 2020-12-23 | COMP | Rule 15/16 | 43 | 362 | 101 | 22 | 528 | 50 | 1684
102 | 2014-04-15 | 2014-04-29 | 2014-07-22 | 2014-07-22 | COMP | 2018-02-26 | COMP | 2018-04-02 | COMP | 2019-03-28 | COMP | 2019-08-23 | COMP | Rule 16 | 11 | 59 | 903 | 26 | 249 | 105 | 1348
118 | 2014-04-15 | 2014-06-19 | 2014-09-05 | 2014-09-05 | COMP | 2014-11-10 | COMP | 2017-09-28 | COMP | 2019-06-19 | COMP | 2019-08-23 | COMP | Rule 16 | 47 | 55 | 47 | 725 | 432 | 47 | 1348
225 | 2014-04-15 | 2015-06-15 | 2015-08-13 | 2015-08-13 | COMP | 2017-12-20 | NOTN | 2018-01-02 | NOTN | 2017-06-13 | COMP | 2021-02-25 | COMP | Rule 16 | 294 | 43 |  |  |  |  | 1725
234 | 2014-04-16 | 2015-07-30 | 2015-10-28 | 2015-10-28 | COMP | 2018-11-07 | COMP | 2016-03-24 | COMP | 2019-02-08 | COMP | 2019-04-19 | COMP | Rule 16 | 325 | 64 | 762 |  | 724 | 50 | 1259
101 | 2014-04-22 | 2014-04-25 | 2014-06-22 | 2014-06-13 | COMP | 2014-07-08 | COMP | 2014-07-22 | COMP | 2014-07-26 | COMP | 2019-04-22 | COMP | Rule 16 | 4 | 40 | 17 | 11 | 4 | 1189 | 1256
100 | 2014-04-23 | 2014-04-24 | 2015-12-09 | 2015-10-27 | COMP | 2018-09-14 | COMP | 2018-09-14 | COMP | 2019-08-13 | COMP | 2019-11-12 | COMP | Rule 16 | 2 | 409 | 725 | 1 | 229 | 64 | 1397
16433 | 2014-04-23 | 2019-12-30 | 2020-06-04 | 2020-12-09 | COMP | 2021-02-16 | COMP | 2021-02-17 | COMP | 2021-03-23 | COMP | 2021-03-29 | COMP | Rule 16 | 1428 | 110 | 46 | 2 | 25 | 5 | 1741
130 | 2014-04-25 | 2014-08-26 | 2014-09-06 | 2014-09-06 | COMP | 2020-02-29 | INPR | 2017-04-19 | NOTN | 2019-09-25 | COMP | 2019-11-04 | COMP | Rule 16 | 86 | 8 |  |  |  |  | 1390
120 | 2014-04-29 | 2014-06-30 | 2015-10-19 | 2015-10-19 | COMP | 2015-11-30 | COMP | 2016-02-20 | COMP | 2015-12-01 | COMP | 2022-03-08 | COMP | Rule 15/16 | 44 | 329 | 28 | 56 | 0 | 1521 | 1975
117 | 2014-05-02 | 2014-06-18 | 2014-09-30 | 2014-09-30 | COMP | 2019-06-25 | COMP | 2019-08-12 | COMP | 2019-12-10 | COMP | 2020-01-10 | COMP | Rule 15/16 | 33 | 73 | 1189 | 34 | 83 | 22 | 1429
113 | 2014-05-03 | 2014-06-06 | 2014-09-28 | 2014-09-28 | COMP | 2022-09-13 | COMP | 2022-09-13 | INPR | 2022-10-31 | COMP | 2023-02-10 | COMP | Rule 16 | 24 | 79 | 2000 |  |  |  | 2204
115 | 2014-05-07 | 2014-06-10 | 2017-10-17 | 2017-10-17 | COMP | 2018-03-10 | COMP | 2020-10-26 | COMP | 2020-10-27 | COMP | 2020-11-23 | COMP | Rule 15/16 | 24 | 845 | 97 | 664 | 2 | 19 | 1647
1041 | 2014-05-07 | 2017-03-08 | 2017-06-19 | 2017-06-19 | COMP | 2017-07-27 | COMP | 2017-08-30 | COMP | 2017-08-04 | COMP | 2019-11-17 | COMP | Rule 16 | 712 | 73 | 28 | 25 | 0 | 556 | 1390
182 | 2014-05-12 | 2015-02-19 | 2015-12-10 | 2015-12-10 | COMP | 2015-12-22 | COMP | 2016-02-16 | COMP | 2016-04-24 | COMP | 2019-09-18 | COMP | Rule 15/16 | 194 | 205 | 9 | 37 | 49 | 856 | 1346
439 | 2014-05-15 | 2016-04-29 | 2016-06-03 | 2016-06-03 | COMP | 2017-02-01 | COMP | 2017-05-18 | COMP | 2017-08-25 | COMP | 2021-01-11 | COMP | Rule 16 | 492 | 25 | 167 | 76 | 70 | 847 | 1672
128 | 2014-05-22 | 2014-08-12 | 2016-03-31 | 2016-03-31 | COMP | 2016-04-13 | COMP | 2016-07-20 | INPR | 2016-08-16 | COMP | 2020-07-22 | COMP | Rule 15/16 | 57 | 410 | 10 |  |  |  | 1550
4220 | 2014-05-22 | 2019-08-08 | 2019-08-21 | 2019-08-21 | COMP | 2022-07-06 | COMP | 2020-11-18 | COMP | 2022-12-09 | COMP | 2023-01-18 | COMP | Rule 15/16 | 1310 | 10 | 723 |  | 517 | 26 | 2174
125 | 2014-06-05 | 2014-07-25 | 2014-08-08 | 2014-08-08 | COMP | 2014-12-09 | COMP | 2017-04-13 | COMP | 2017-05-02 | COMP | 2020-02-24 | COMP | Rule 16 | 36 | 11 | 84 | 590 | 14 | 705 | 1435
240 | 2014-06-10 | 2015-08-13 | 2016-01-21 | 2016-01-21 | COMP | 2017-11-07 | COMP | 2018-01-16 | COMP | 2018-05-18 | COMP | 2021-04-16 | COMP | Rule 15/16 | 297 | 109 | 456 | 45 | 88 | 732 | 1722
119 | 2014-06-11 | 2014-06-19 | 2014-08-21 | 2014-08-21 | COMP | 2019-06-19 | COMP | 2020-07-06 | COMP | 2020-06-30 | COMP | 2020-07-17 | COMP | Other | 7 | 45 | 1212 | 264 | 0 | 10 | 1534
259 | 2014-06-19 | 2015-09-18 | 2018-01-17 | 2018-01-17 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2022-12-31 | REQD | 2021-10-12 | COMP | Rule 16 | 315 | 584 | 415 | 1 |  |  | 1839
131 | 2014-06-23 | 2014-09-02 | 2015-07-07 | 2015-07-07 | COMP | 2018-03-05 | COMP | 2018-03-05 | COMP | 2018-05-15 | COMP | 2022-04-29 | COMP | Rule 16 | 50 | 212 | 668 | 1 | 52 | 997 | 1975
132 | 2014-06-24 | 2014-09-09 | 2015-10-07 | 2018-12-28 | COMP | 2019-02-14 | COMP | 2019-09-05 | COMP | 2021-03-28 | INPR | 2020-03-04 | COMP | Rule 15/16 | 54 | 272 | 33 | 142 |  |  | 1429
160 | 2014-06-24 | 2014-11-06 | 2015-01-25 | 2015-01-25 | COMP | 2016-12-09 | COMP | 2016-12-09 | COMP | 2019-03-28 | COMP | 2019-04-25 | COMP | Rule 16 | 96 | 51 | 473 | 1 | 577 | 21 | 1215
161 | 2014-06-24 | 2014-11-06 | 2015-02-01 | 2015-02-01 | COMP | 2017-01-03 | COMP | 2017-01-03 | COMP | 2017-07-15 | COMP | 2019-05-02 | COMP | Rule 16 | 96 | 56 | 484 | 1 | 135 | 451 | 1220
122 | 2014-07-01 | 2014-07-17 | 2015-03-23 | 2015-03-23 | COMP | 2016-07-13 | COMP | 2016-09-09 | COMP | 2016-10-07 | COMP | 2019-08-24 | COMP | Rule 16 | 12 | 170 | 331 | 42 | 21 | 723 | 1294
137 | 2014-07-02 | 2014-09-24 | 2017-10-11 | 2017-10-11 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2020-10-16 | COMP | 2021-02-01 | COMP | Rule 16 | 59 | 767 | 765 | 1 | 0 | 65 | 1653
221 | 2014-07-02 | 2015-06-03 | 2015-06-04 | 2015-06-04 | COMP | 2015-06-17 | COMP | 2015-06-18 | COMP | 2015-06-17 | COMP | 2019-04-14 | COMP | Rule 16 | 231 | 2 | 10 | 2 | 0 | 959 | 1200
121 | 2014-07-03 | 2014-07-07 | 2014-08-08 | 2017-09-01 | COMP | 2018-08-21 | COMP | 2018-08-24 | COMP | 2020-02-25 | COMP | 2020-06-11 | COMP | Rule 16 | 2 | 25 | 243 | 4 | 375 | 77 | 1492
224 | 2014-07-07 | 2015-06-09 | 2015-08-07 | 2015-08-07 | COMP | 2015-06-09 | NOTN | 2015-08-07 | COMP | 2021-11-14 | INPR | 2020-09-09 | COMP | Other | 233 | 43 |  | 1 |  |  | 1554
123 | 2014-07-15 | 2014-07-18 | 2014-11-14 | 2014-11-14 | COMP | 2015-06-08 | COMP | 2015-06-08 | COMP | 2019-12-28 | INPR | 2019-07-19 | COMP | Rule 15/16 | 4 | 84 | 140 | 1 |  |  | 1260
228 | 2014-07-17 | 2015-06-29 | 2016-06-17 | 2016-06-17 | COMP | 2017-04-06 | COMP | 2017-04-06 | COMP | 2019-04-03 | COMP | 2019-04-27 | COMP | Rule 15/16 | 239 | 245 | 202 | 1 | 500 | 18 | 1200
124 | 2014-07-18 | 2014-07-23 | 2017-12-20 | 2017-12-20 | COMP | 2017-12-20 | NOTN | 2018-07-25 | COMP | 2018-08-06 | COMP | 2019-01-13 | COMP | Other | 4 | 858 |  | 150 | 9 | 109 | 1126
129 | 2014-07-24 | 2014-08-21 | 2016-02-18 | 2016-02-18 | COMP | 2019-04-08 | COMP | 2016-09-02 | COMP | 2016-09-03 | COMP | 2019-11-08 | COMP | Rule 15/16 | 21 | 373 | 789 |  | 1 | 800 | 1332
170 | 2014-07-25 | 2015-01-09 | 2015-10-21 | 2015-10-21 | COMP | 2017-10-09 | COMP | 2018-07-23 | COMP | 2019-01-02 | COMP | 2019-04-03 | COMP | Rule 15/16 | 115 | 199 | 495 | 197 | 112 | 64 | 1177
127 | 2014-08-01 | 2014-08-04 | 2017-02-07 | 2017-02-07 | COMP | 2020-03-26 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-06-16 | COMP | Rule 16 | 2 | 631 | 787 | 32 | 1 | 27 | 1475
143 | 2014-08-01 | 2014-10-08 | 2018-06-13 | 2018-06-13 | COMP | 2018-08-22 | COMP | 2018-09-17 | COMP | 2019-07-21 | INPR | 2019-01-10 | COMP | Rule 16 | 48 | 924 | 50 | 18 |  |  | 1115
357 | 2014-08-04 | 2016-01-19 | 2016-03-15 | 2016-03-15 | COMP | 2016-04-04 | COMP | 2018-01-20 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | Rule 16 | 365 | 40 | 15 | 452 | 408 | 1 | 1277
190 | 2014-08-05 | 2015-03-24 | 2016-09-08 | 2016-09-08 | COMP | 2016-10-26 | COMP | 2019-06-13 | COMP | 2020-10-06 | COMP | 2020-11-06 | COMP | Rule 16 | 158 | 370 | 35 | 660 | 333 | 24 | 1575
546 | 2014-08-06 | 2016-07-19 | 2016-12-20 | 2016-12-20 | COMP | 2019-10-31 | COMP | 2020-06-29 | COMP | 2021-03-30 | COMP | 2021-05-27 | COMP | Rule 15/16 | 490 | 107 | 722 | 165 | 189 | 43 | 1711
166 | 2014-08-07 | 2014-12-06 | 2015-12-28 | 2017-07-13 | COMP | 2017-08-11 | COMP | 2017-09-20 | COMP | 2017-09-21 | COMP | 2019-04-29 | COMP | Rule 15/16 | 83 | 265 | 22 | 28 | 2 | 401 | 1186
484 | 2014-08-07 | 2016-05-31 | 2016-07-19 | 2016-07-19 | COMP | 2019-07-18 | COMP | 2018-12-21 | COMP | 2018-12-29 | COMP | 2019-02-20 | COMP | Rule 16 | 455 | 35 | 754 |  | 5 | 35 | 1138
1125 | 2014-08-08 | 2017-03-30 | 2017-11-27 | 2019-01-16 | COMP | 2019-03-08 | COMP | 2019-04-04 | COMP | 2021-02-27 | INPR | 2019-06-19 | COMP | Rule 15/16 | 663 | 167 | 36 | 20 |  |  | 1221
145 | 2014-08-12 | 2014-10-13 | 2014-11-22 | 2014-11-22 | COMP | 2014-10-13 | NOTN | 2014-11-22 | COMP |  | INPR | 2019-05-13 | COMP | Other | 44 | 29 |  | 0 |  |  | 1193
2132 | 2014-08-12 | 2017-09-27 | 2018-04-28 | 2018-04-28 | COMP | 2018-08-08 | COMP | 2019-01-11 | COMP | 2019-08-31 | INPR | 2019-04-17 | COMP | Rule 15/16 | 787 | 146 | 71 | 107 |  |  | 1175
133 | 2014-08-18 | 2014-09-09 | 2014-12-26 | 2014-12-26 | COMP | 2017-06-19 | NOTN | 2017-06-19 | COMP | 2020-01-08 | NOTN | 2020-02-21 | COMP | Rule 16 | 16 | 75 |  | 624 |  |  | 1383
140 | 2014-08-20 | 2014-09-29 | 2015-04-27 | 2015-04-27 | COMP | 2019-06-27 | COMP | 2017-07-14 | COMP | 2019-06-26 | COMP | 2019-09-24 | COMP | Rule 15/16 | 28 | 144 | 1049 |  | 490 | 63 | 1280
1206 | 2014-08-21 | 2017-04-21 | 2017-06-08 | 2017-06-08 | COMP | 2019-08-09 | COMP | 2019-08-22 | COMP | 2020-01-13 | COMP | 2020-02-25 | COMP | Rule 16 | 670 | 34 | 546 | 10 | 97 | 30 | 1382
183 | 2014-08-22 | 2015-02-28 | 2015-03-25 | 2015-03-25 | COMP | 2015-04-13 | COMP | 2015-05-13 | COMP | 2019-10-19 | INPR | 2019-06-19 | COMP | Rule 16 | 128 | 18 | 14 | 23 |  |  | 1211
296 | 2014-08-26 | 2015-12-02 | 2016-02-10 | 2016-02-10 | COMP | 2019-04-30 | COMP | 2019-05-03 | COMP | 2019-04-27 | COMP | 2019-05-29 | COMP | Rule 16 | 318 | 48 | 810 | 4 | 0 | 18 | 1194
297 | 2014-08-26 | 2015-12-02 | 2016-02-24 | 2016-02-24 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-09-21 | INPR | 2019-05-29 | COMP | Rule 16 | 318 | 57 | 801 | 3 |  |  | 1194
298 | 2014-08-26 | 2015-12-02 | 2016-07-18 | 2016-07-18 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2020-03-06 | COMP | 2020-04-02 | COMP | Rule 16 | 318 | 158 | 700 | 3 | 212 | 20 | 1406
142 | 2014-08-27 | 2014-10-07 | 2015-10-07 | 2018-11-04 | COMP | 2018-12-04 | COMP | 2019-01-10 | COMP | 2019-01-18 | COMP | 2019-03-12 | COMP | Rule 15/16 | 29 | 252 | 19 | 26 | 7 | 36 | 1138
336 | 2014-08-27 | 2016-01-06 | 2017-03-06 | 2017-03-06 | COMP | 2017-10-24 | COMP | 2017-10-24 | NOTN | 2019-09-21 | REQD | 2019-05-30 | COMP | Rule 16 | 340 | 293 | 164 |  |  |  | 1194
466 | 2014-08-27 | 2016-05-23 | 2016-08-24 | 2016-08-24 | COMP | 2016-09-14 | COMP | 2018-03-21 | COMP | 2018-09-27 | COMP | 2021-05-24 | COMP | Rule 15/16 | 436 | 66 | 15 | 380 | 134 | 667 | 1693
320 | 2014-09-03 | 2015-12-21 | 2017-02-27 | 2017-02-27 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-04-09 | COMP | 2020-05-08 | COMP | Rule 16 | 326 | 298 | 782 | 1 | 3 | 22 | 1427
339 | 2014-09-03 | 2016-01-07 | 2016-02-25 | 2016-02-25 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2020-02-06 | COMP | 2020-02-14 | COMP | Rule 16 | 337 | 34 | 800 | 3 | 192 | 7 | 1368
340 | 2014-09-03 | 2016-01-07 | 2016-02-23 | 2016-02-23 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-09-21 | INPR | 2019-05-31 | COMP | Rule 16 | 337 | 32 | 802 | 3 |  |  | 1191
341 | 2014-09-03 | 2016-01-07 | 2016-11-09 | 2016-11-09 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-07-19 | COMP | 2019-08-14 | COMP | Rule 16 | 337 | 215 | 619 | 3 | 55 | 19 | 1243
342 | 2014-09-03 | 2016-01-07 | 2016-11-08 | 2016-11-08 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-06-22 | COMP | 2019-08-20 | COMP | Rule 16 | 337 | 214 | 620 | 3 | 36 | 41 | 1247
343 | 2014-09-03 | 2016-01-07 | 2016-08-06 | 2016-08-06 | COMP | 2018-04-09 | COMP | 2018-07-12 | COMP | 2019-08-01 | COMP | 2019-06-27 | COMP | Rule 16 | 337 | 148 | 419 | 67 | 266 |  | 1210
344 | 2014-09-03 | 2016-01-07 | 2016-02-28 | 2016-02-28 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-09-21 | INPR | 2019-05-31 | COMP | Rule 16 | 337 | 35 | 798 | 3 |  |  | 1191
159 | 2014-09-04 | 2014-10-31 | 2015-06-01 | 2015-06-01 | COMP | 2018-03-13 | COMP | 2018-03-07 | COMP | 2020-02-19 | COMP | 2020-08-01 | COMP | Rule 16 | 42 | 144 | 699 |  | 491 | 117 | 1485
319 | 2014-09-04 | 2015-12-21 | 2019-08-02 | 2016-03-10 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-06-22 | COMP | 2019-07-29 | COMP | Rule 16 | 325 | 910 | 790 | 3 | 36 | 25 | 1230
321 | 2014-09-04 | 2015-12-23 | 2016-10-31 | 2016-10-31 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2020-02-28 | COMP | 2020-04-24 | COMP | Rule 16 | 327 | 217 | 626 | 1 | 209 | 41 | 1416
322 | 2014-09-04 | 2015-12-23 | 2016-04-27 | 2016-04-27 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2020-03-03 | COMP | 2020-03-10 | COMP | Rule 16 | 327 | 87 | 756 | 1 | 211 | 6 | 1383
323 | 2014-09-04 | 2015-12-23 | 2016-11-02 | 2016-11-02 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-02-28 | COMP | 2020-04-29 | COMP | Rule 16 | 327 | 219 | 859 | 1 | 0 | 17 | 1419
324 | 2014-09-04 | 2015-12-23 | 2017-02-13 | 2016-04-26 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2020-03-03 | COMP | 2020-03-06 | COMP | Rule 16 | 327 | 287 | 805 | 1 | 163 | 4 | 1381
325 | 2014-09-04 | 2015-12-23 | 2016-11-01 | 2016-11-01 | COMP | 2019-04-30 | COMP | 2020-02-14 | COMP | 2020-04-01 | COMP | 2020-04-07 | COMP | Rule 16 | 327 | 218 | 625 | 200 | 33 | 5 | 1403
326 | 2014-09-04 | 2015-12-23 | 2016-12-03 | 2016-12-03 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2020-01-22 | COMP | 2020-02-22 | COMP | Rule 15 | 327 | 238 | 604 | 3 | 181 | 22 | 1371
327 | 2014-09-04 | 2015-12-23 | 2017-01-30 | 2017-01-30 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2020-03-03 | COMP | 2020-03-06 | COMP | Rule 16 | 327 | 277 | 566 | 3 | 209 | 4 | 1381
328 | 2014-09-04 | 2015-12-23 | 2016-06-08 | 2016-06-08 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2020-03-13 | COMP | 2020-03-25 | COMP | Rule 16 | 327 | 116 | 727 | 3 | 217 | 9 | 1394
329 | 2014-09-04 | 2015-12-23 | 2016-06-08 | 2016-06-08 | COMP | 2018-08-24 | COMP | 2019-08-21 | COMP | 2020-03-13 | COMP | 2020-05-16 | COMP | Rule 16 | 327 | 116 | 558 | 249 | 140 | 46 | 1431
330 | 2014-09-04 | 2015-12-23 | 2016-06-29 | 2016-06-29 | COMP | 2019-04-30 | COMP | 2019-07-18 | COMP | 2020-01-27 | COMP | 2020-04-07 | COMP | Rule 16 | 327 | 131 | 712 | 56 | 131 | 51 | 1403
331 | 2014-09-04 | 2015-12-23 | 2016-06-28 | 2016-06-28 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2020-03-06 | COMP | 2020-05-06 | COMP | Rule 16 | 327 | 130 | 713 | 3 | 212 | 44 | 1424
346 | 2014-09-04 | 2016-01-08 | 2016-11-08 | 2016-11-08 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-07-19 | COMP | 2019-08-14 | COMP | Rule 16 | 337 | 213 | 620 | 3 | 55 | 19 | 1242
347 | 2014-09-04 | 2016-01-08 | 2016-11-08 | 2016-11-08 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-10-02 | COMP | 2019-10-18 | COMP | Rule 16 | 337 | 213 | 620 | 3 | 107 | 13 | 1288
348 | 2014-09-04 | 2016-01-08 | 2016-11-09 | 2016-11-09 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-09-21 | INPR | 2019-06-04 | COMP | Rule 16 | 337 | 214 | 619 | 3 |  |  | 1192
3850 | 2014-09-04 | 2018-08-16 | 2018-09-25 | 2018-09-25 | COMP | 2019-05-10 | COMP | 2019-05-10 | NOTN | 2020-03-19 | COMP | 2020-04-02 | COMP | Rule 16 | 993 | 28 | 157 |  |  |  | 1400
138 | 2014-09-05 | 2014-09-25 | 2015-11-02 | 2018-12-31 | COMP | 2019-01-14 | COMP | 2019-01-28 | COMP | 2019-02-11 | COMP | 2019-04-12 | COMP | Rule 15/16 | 15 | 278 | 10 | 10 | 11 | 44 | 1155
156 | 2014-09-05 | 2014-10-31 | 2015-06-20 | 2015-06-20 | COMP | 2018-03-13 | COMP | 2018-12-21 | COMP | 2018-09-22 | COMP | 2020-06-27 | COMP | Rule 16 | 41 | 158 | 684 | 198 | 0 | 381 | 1459
1646 | 2014-09-05 | 2017-07-08 | 2017-11-10 | 2017-11-10 | COMP | 2018-06-05 | COMP | 2018-06-05 | COMP | 2021-02-27 | INPR | 2019-10-23 | COMP | Rule 15/16 | 713 | 88 | 140 | 1 |  |  | 1290
314 | 2014-09-09 | 2015-12-18 | 2016-03-09 | 2016-03-09 | COMP | 2017-04-05 | COMP | 2017-07-10 | COMP | 2019-04-08 | COMP | 2019-05-16 | COMP | Rule 16 | 321 | 55 | 272 | 67 | 438 | 29 | 1177
315 | 2014-09-09 | 2015-12-18 | 2016-02-27 | 2016-02-27 | COMP | 2017-04-05 | COMP | 2017-07-10 | COMP | 2019-01-22 | COMP | 2019-05-14 | COMP | Rule 15/16 | 321 | 47 | 279 | 67 | 385 | 80 | 1175
316 | 2014-09-09 | 2015-12-18 | 2016-03-10 | 2016-03-10 | COMP | 2017-04-05 | COMP | 2017-07-10 | COMP | 2019-01-22 | COMP | 2019-06-04 | COMP | Rule 16 | 321 | 56 | 271 | 67 | 385 | 94 | 1189
317 | 2014-09-09 | 2015-12-18 | 2016-02-22 | 2016-02-22 | COMP | 2017-04-05 | COMP | 2017-07-14 | COMP | 2019-04-08 | COMP | 2019-05-24 | COMP | Rule 16 | 321 | 43 | 284 | 71 | 434 | 35 | 1183
150 | 2014-09-13 | 2014-10-28 | 2015-01-08 | 2015-01-08 | COMP | 2016-04-15 | COMP | 2016-04-15 | COMP | 2020-01-09 | COMP | 2020-01-21 | COMP | Rule 16 | 32 | 48 | 320 | 1 | 938 | 8 | 1342
151 | 2014-09-13 | 2014-10-28 | 2015-01-28 | 2015-01-28 | COMP | 2016-04-15 | COMP | 2016-04-15 | COMP | 2020-01-09 | COMP | 2020-01-21 | COMP | Rule 16 | 32 | 61 | 307 | 1 | 938 | 8 | 1342
152 | 2014-09-13 | 2014-10-28 | 2014-12-09 | 2015-01-08 | COMP | 2016-04-18 | COMP | 2016-04-18 | COMP | 2020-01-09 | COMP | 2020-01-21 | COMP | Rule 16 | 32 | 28 | 321 | 1 | 937 | 8 | 1342
153 | 2014-09-13 | 2014-10-28 | 2015-01-08 | 2015-01-08 | COMP | 2016-04-15 | COMP | 2016-04-21 | COMP | 2020-01-09 | COMP | 2020-01-10 | COMP | Rule 16 | 32 | 48 | 320 | 5 | 934 | 2 | 1336
154 | 2014-09-13 | 2014-10-31 | 2016-05-12 | 2016-05-12 | COMP | 2016-08-23 | COMP | 2016-06-08 | COMP |  |  | 2020-01-20 | COMP | Rule 16 | 35 | 383 | 72 |  |  |  | 1341
155 | 2014-09-13 | 2014-10-31 | 2015-01-12 | 2015-12-22 | COMP | 2016-04-15 | COMP | 2017-11-30 | COMP |  |  | 2021-02-15 | COMP | Rule 16 | 35 | 47 | 80 | 410 |  |  | 1611
157 | 2014-09-13 | 2014-11-01 | 2015-01-09 | 2015-01-09 | COMP | 2016-04-15 | COMP | 2016-04-21 | COMP |  |  | 2020-08-04 | COMP | Rule 16 | 35 | 45 | 319 | 5 |  |  | 1480
158 | 2014-09-13 | 2014-11-01 | 2015-11-22 | 2015-11-17 | COMP | 2016-04-15 | COMP | 2016-04-15 | COMP |  |  | 2020-01-21 | COMP | Rule 16 | 35 | 264 | 103 | 1 |  |  | 1342
144 | 2014-09-17 | 2014-10-13 | 2014-11-05 | 2014-11-05 | COMP | 2015-01-12 | COMP | 2015-01-08 | COMP | 2015-01-08 | COMP | 2019-10-04 | COMP | Rule 16 | 19 | 18 | 44 |  | 1 | 1193 | 1269
149 | 2014-09-17 | 2014-10-28 | 2015-01-23 | 2015-01-23 | COMP | 2015-01-29 | COMP | 2015-03-06 | COMP | 2015-04-28 | COMP | 2021-10-05 | COMP | Rule 16 | 30 | 58 | 5 | 26 | 38 | 1620 | 1772
13405 | 2014-09-30 | 2019-07-24 | 2019-12-03 | 2019-12-03 | COMP | 2020-04-03 | COMP | 2021-01-28 | COMP | 2021-11-17 | COMP | 2022-01-19 | COMP | Rule 15/16 | 1209 | 91 | 85 | 207 | 205 | 43 | 1835
163 | 2014-10-06 | 2014-12-02 | 2017-09-30 | 2018-03-11 | COMP | 2018-06-27 | COMP | 2019-02-22 | COMP | 2019-01-16 | COMP | 2019-05-05 | COMP | Rule 15/16 | 39 | 713 | 77 | 164 | 0 | 51 | 1149
4824 | 2014-10-08 | 2018-04-02 | 2018-07-17 | 2019-04-30 | COMP | 2019-05-16 | COMP | 2019-08-07 | COMP | 2022-07-16 | INPR | 2019-11-12 | COMP | Rule 15/16 | 873 | 75 | 13 | 58 |  |  | 1280
147 | 2014-10-14 | 2014-10-21 | 2014-10-29 | 2014-10-29 | COMP | 2014-12-17 | COMP | 2015-05-01 | COMP | 2022-07-16 | INPR | 2021-02-25 | COMP | Rule 16 | 6 | 7 | 33 | 94 |  |  | 1598
356 | 2014-10-15 | 2016-01-19 | 2016-03-24 | 2016-03-24 | COMP | 2016-04-25 | COMP | 2016-10-21 | COMP | 2016-11-01 | COMP | 2021-09-29 | COMP | Rule 16 | 314 | 47 | 23 | 127 | 8 | 1234 | 1748
175 | 2014-10-16 | 2015-01-23 | 2015-03-16 | 2015-03-16 | COMP | 2017-08-31 | NOTN | 2017-11-10 | COMP | 2017-09-06 | COMP | 2021-04-10 | COMP | Other | 66 | 36 |  | 672 | 0 | 855 | 1627
184 | 2014-10-17 | 2015-03-07 | 2016-12-13 | 2016-12-13 | COMP | 2017-02-07 | COMP | 2017-02-09 | COMP | 2020-09-28 | COMP | 2020-10-02 | COMP | Rule 15/16 | 94 | 446 | 39 | 3 | 915 | 5 | 1498
267 | 2014-10-17 | 2015-09-29 | 2016-04-11 | 2016-04-11 | COMP | 2017-11-15 | COMP | 2017-11-16 | COMP | 2018-07-17 | COMP | 2019-04-29 | COMP | Rule 16 | 238 | 133 | 405 | 2 | 166 | 197 | 1136
169 | 2014-10-20 | 2014-12-18 | 2015-02-21 | 2015-02-21 | COMP | 2017-05-01 | COMP | 2017-05-01 | COMP | 2018-11-26 | COMP | 2019-01-10 | COMP | Rule 16 | 41 | 43 | 552 | 1 | 395 | 32 | 1060
165 | 2014-10-21 | 2014-12-03 | 2018-10-16 | 2018-10-16 | COMP | 2020-03-23 | COMP | 2019-11-01 | COMP | 2021-01-30 | INPR | 2020-01-03 | COMP | Rule 16 | 29 | 974 | 358 |  |  |  | 1305
162 | 2014-10-22 | 2014-11-13 | 2015-01-15 | 2015-01-15 | COMP | 2015-04-24 | COMP | 2015-04-27 | COMP | 2022-12-22 | COMP | 2023-01-30 | COMP | Rule 16 | 16 | 42 | 70 | 2 | 1926 | 25 | 2076
189 | 2014-10-28 | 2015-03-17 | 2015-09-15 | 2015-09-11 | COMP | 2015-11-10 | COMP | 2016-08-24 | COMP | 2018-12-12 | COMP | 2019-01-25 | COMP | Rule 15/16 | 94 | 128 | 43 | 198 | 578 | 30 | 1064
168 | 2014-11-03 | 2014-12-17 | 2015-05-04 | 2015-05-04 | COMP | 2017-12-12 | COMP | 2017-12-12 | COMP | 2019-04-19 | COMP | 2019-05-16 | COMP | Rule 15/16 | 30 | 95 | 657 | 1 | 340 | 20 | 1138
195 | 2014-11-03 | 2015-03-31 | 2017-11-21 | 2018-08-20 | COMP | 2018-10-09 | COMP | 2019-07-08 | COMP | 2019-11-14 | COMP | 2019-12-09 | COMP | Rule 15/16 | 100 | 668 | 36 | 186 | 92 | 16 | 1279
384 | 2014-11-03 | 2016-03-03 | 2017-05-13 | 2017-05-13 | COMP | 2018-03-22 | COMP | 2017-08-02 | COMP | 2020-08-11 | INPR | 2019-03-11 | COMP | Rule 15/16 | 332 | 303 | 214 |  |  |  | 1090
207 | 2014-11-12 | 2015-04-11 | 2015-07-18 | 2015-07-18 | COMP | 2017-04-07 | COMP | 2018-02-16 | COMP | 2023-04-15 | CANC | 2020-10-30 | COMP | Rule 15/16 | 102 | 68 | 433 | 217 |  |  | 1501
218 | 2014-11-13 | 2015-05-13 | 2015-05-16 | 2015-05-16 | COMP | 2018-03-27 | COMP | 2015-06-30 | NOTN | 2018-12-04 | COMP | 2019-01-03 | COMP | Rule 16 | 124 | 3 | 718 |  |  |  | 1038
931 | 2014-11-13 | 2017-02-06 | 2018-02-27 | 2018-02-27 | COMP | 2018-07-27 | COMP | 2018-07-31 | COMP | 2018-07-26 | COMP | 2021-11-10 | COMP | Rule 16 | 559 | 266 | 107 | 3 | 0 | 827 | 1758
932 | 2014-11-13 | 2017-02-06 | 2017-07-03 | 2017-07-03 | COMP | 2018-05-16 | COMP | 2018-05-16 | COMP | 2021-10-26 | COMP | 2021-11-08 | COMP | Rule 16 | 559 | 104 | 219 | 1 | 868 | 10 | 1756
933 | 2014-11-13 | 2017-02-06 | 2018-02-10 | 2018-02-10 | COMP | 2022-12-03 | REQD | 2018-06-12 | COMP | 2018-06-06 | COMP | 2021-11-12 | COMP | Other | 559 | 255 |  | 85 | 0 | 862 | 1759
1297 | 2014-11-13 | 2017-05-06 | 2017-07-05 | 2017-07-05 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2018-07-26 | COMP | 2021-09-29 | COMP | Rule 16 | 622 | 41 | 625 | 1 | 0 | 442 | 1728
1315 | 2014-11-13 | 2017-05-10 | 2017-07-06 | 2017-07-06 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2021-10-26 | COMP | 2021-11-08 | COMP | Rule 16 | 625 | 40 | 624 | 1 | 461 | 10 | 1756
1316 | 2014-11-13 | 2017-05-10 | 2017-07-08 | 2017-07-08 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2021-10-26 | COMP | 2021-11-12 | COMP | Rule 16 | 625 | 41 | 622 | 1 | 461 | 13 | 1759
1317 | 2014-11-13 | 2017-05-10 | 2017-07-01 | 2017-07-01 | COMP | 2018-05-16 | COMP | 2018-05-16 | COMP | 2021-10-26 | COMP | 2021-11-09 | COMP | Rule 16 | 625 | 37 | 219 | 1 | 868 | 11 | 1757
1318 | 2014-11-13 | 2017-05-10 | 2017-07-01 | 2017-07-01 | COMP | 2019-12-30 | COMP | 2018-07-31 | COMP | 2018-03-21 | COMP | 2021-11-10 | COMP | Rule 16 | 625 | 37 | 625 |  | 0 | 827 | 1758
1376 | 2014-11-13 | 2017-05-22 | 2018-02-20 | 2018-02-20 | COMP | 2018-10-09 | COMP | 2019-01-04 | COMP | 2021-10-26 | COMP | 2021-11-09 | COMP | Rule 16 | 633 | 187 | 163 | 59 | 709 | 11 | 1757
167 | 2014-11-14 | 2014-12-10 | 2015-03-27 | 2015-03-27 | COMP | 2018-09-11 | COMP |  | REQD | 2018-12-12 | COMP | 2019-02-05 | COMP | Other | 17 | 74 | 871 |  |  |  | 1059
171 | 2014-11-14 | 2015-01-13 | 2015-06-23 | 2015-06-23 | COMP | 2015-07-31 | COMP | 2015-10-19 | COMP | 2018-03-05 | COMP | 2019-09-12 | COMP | Rule 15/16 | 39 | 113 | 28 | 56 | 595 | 386 | 1212
516 | 2014-11-17 | 2016-06-24 | 2019-02-05 | 2019-02-05 | COMP |  | REQD |  | REQD |  | REQD | 2019-03-13 | COMP | Other | 403 | 656 |  |  |  |  | 1083
1046 | 2014-11-17 | 2017-03-10 | 2017-04-12 | 2017-04-12 | COMP | 2017-07-21 | COMP | 2017-07-21 | COMP | 2018-07-26 | COMP | 2021-03-08 | COMP | Other | 580 | 24 | 71 | 1 | 255 | 656 | 1582
1090 | 2014-11-17 | 2017-03-24 | 2017-06-29 | 2017-06-29 | COMP | 2018-09-20 | COMP | 2020-07-10 | COMP | 2020-08-31 | COMP | 2022-09-13 | COMP | Other | 590 | 69 | 309 | 454 | 37 | 512 | 1966
1099 | 2014-11-17 | 2017-03-24 | 2017-06-29 | 2017-06-29 | COMP | 2018-05-16 | COMP | 2020-04-17 | COMP | 2020-05-01 | COMP | 2021-03-10 | COMP | Other | 590 | 69 | 221 | 483 | 11 | 215 | 1584
3826 | 2014-11-17 | 2018-08-02 | 2018-09-21 | 2018-09-21 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | Other | 932 | 36 | 293 | 1 | 119 | 1 | 1377
666 | 2014-11-18 | 2016-09-29 | 2017-04-01 | 2017-04-01 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2019-02-16 | COMP | 2019-02-16 | COMP | Other | 469 | 126 | 371 | 1 | 101 | 0 | 1065
676 | 2014-11-18 | 2016-10-06 | 2017-02-18 | 2017-02-18 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP |  | INPR | 2020-05-26 | COMP | Other | 474 | 92 | 413 | 1 |  |  | 1385
677 | 2014-11-18 | 2016-10-06 | 2017-02-18 | 2017-02-18 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP |  | INPR | 2020-06-11 | COMP | Other | 474 | 92 | 413 | 1 |  |  | 1397
703 | 2014-11-18 | 2016-10-20 | 2017-02-04 | 2017-02-04 | COMP | 2018-07-27 | COMP | 2018-07-27 | COMP | 2018-07-26 | COMP | 2019-03-11 | COMP | Other | 484 | 72 | 372 | 1 | 0 | 154 | 1080
704 | 2014-11-18 | 2016-10-20 | 2017-02-04 | 2017-02-04 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2020-09-03 | COMP | 2021-02-25 | COMP | Other | 484 | 72 | 410 | 1 | 493 | 118 | 1574
706 | 2014-11-18 | 2016-10-20 | 2017-02-09 | 2017-02-09 | COMP | 2018-01-19 | NOTN | 2018-01-19 | COMP |  | INPR | 2019-05-23 | COMP | Other | 484 | 76 |  | 237 |  |  | 1133
707 | 2014-11-18 | 2016-10-20 | 2017-02-09 | 2017-02-09 | COMP | 2018-01-19 | NOTN | 2018-01-19 | COMP | 2020-07-01 | COMP | 2021-03-01 | COMP | Other | 484 | 76 |  | 237 | 617 | 166 | 1576
1122 | 2014-11-18 | 2017-03-29 | 2017-06-17 | 2017-06-17 | COMP |  |  |  |  | 2020-09-03 | COMP | 2021-03-01 | COMP | Other | 592 | 57 |  |  |  |  | 1576
6198 | 2014-11-18 | 2018-08-03 | 2018-10-16 | 2020-05-05 | COMP | 2020-02-21 | COMP | 2020-05-06 | COMP | 2020-05-05 | COMP | 2021-05-20 | COMP | Other | 932 | 52 |  | 54 | 0 | 263 | 1634
6199 | 2014-11-18 | 2018-08-03 | 2018-10-22 | 2020-07-15 | COMP | 2019-12-30 | COMP | 2021-03-03 | COMP | 2020-09-03 | COMP | 2021-03-09 | COMP | Other | 932 | 56 |  | 296 | 0 | 5 | 1582
6227 | 2014-11-18 | 2018-08-03 | 2018-10-12 | 2018-10-12 | COMP | 2020-02-21 | COMP | 2021-02-10 | COMP | 2020-09-09 | COMP | 2021-03-09 | COMP | Other | 932 | 50 | 339 | 246 | 0 | 19 | 1582
559 | 2014-11-19 | 2016-07-28 | 2018-10-10 | 2020-08-07 | COMP | 2021-03-08 | COMP | 2021-06-30 | COMP | 2021-06-08 | COMP | 2021-09-02 | COMP | Rule 15/16 | 424 | 555 | 144 | 82 | 0 | 46 | 1706
172 | 2014-11-21 | 2015-01-15 | 2015-10-02 | 2015-10-02 | COMP | 2018-08-15 | COMP | 2018-09-21 | COMP | 2021-12-30 | COMP | 2022-02-14 | COMP | Rule 15/16 | 36 | 182 | 721 | 27 | 823 | 32 | 1816
550 | 2014-11-25 | 2016-07-21 | 2016-09-17 | 2016-09-17 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2020-09-03 | COMP | 2021-03-09 | COMP | Other | 415 | 41 | 518 | 1 | 480 | 126 | 1577
655 | 2014-11-25 | 2016-09-27 | 2016-11-01 | 2016-11-01 | COMP | 2018-04-05 | COMP | 2018-04-05 | COMP | 2018-03-21 | COMP | 2019-06-11 | COMP | Other | 462 | 26 | 357 | 1 | 0 | 298 | 1140
675 | 2014-11-25 | 2016-10-06 | 2016-11-07 | 2016-11-07 | COMP | 2018-04-05 | COMP | 2018-04-05 | COMP | 2018-03-21 | COMP | 2019-03-12 | COMP | Other | 469 | 23 | 353 | 1 | 0 | 234 | 1076
1100 | 2014-11-25 | 2017-03-24 | 2017-07-10 | 2017-07-10 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2020-08-31 | COMP | 2019-05-23 | COMP | Other | 584 | 75 | 303 | 1 | 490 |  | 1128
1101 | 2014-11-25 | 2017-03-24 | 2017-06-29 | 2017-06-29 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2020-09-03 | COMP | 2019-05-23 | COMP | Other | 584 | 69 | 791 | 1 | 11 |  | 1128
1102 | 2014-11-25 | 2017-03-24 | 2017-07-12 | 2017-07-12 | COMP | 2017-11-27 | COMP | 2020-07-06 | COMP | 2020-09-03 | COMP | 2021-04-08 | COMP | Other | 584 | 77 | 95 | 656 | 44 | 148 | 1599
1241 | 2014-11-25 | 2017-04-27 | 2017-07-17 | 2017-07-17 | COMP | 2020-02-21 | COMP | 2020-07-04 | INPR | 2020-09-03 | COMP | 2021-05-18 | COMP | Other | 608 | 56 | 652 |  |  |  | 1627
188 | 2014-11-26 | 2015-03-17 | 2015-12-08 | 2015-12-08 | COMP | 2018-12-12 | COMP | 2019-02-22 | COMP | 2019-02-11 | COMP | 2019-04-09 | COMP | Rule 16 | 74 | 185 | 758 | 49 | 0 | 33 | 1095
281 | 2014-12-02 | 2015-10-23 | 2016-04-07 | 2016-04-07 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-08-31 | INPR | 2019-05-03 | COMP | Rule 16 | 227 | 113 | 751 | 1 |  |  | 1111
367 | 2014-12-02 | 2016-02-04 | 2016-08-30 | 2017-05-01 | COMP | 2017-06-27 | COMP | 2017-06-27 | COMP | 2021-03-31 | COMP | 2021-05-07 | COMP | Rule 16 | 295 | 146 | 41 | 1 | 944 | 28 | 1617
212 | 2014-12-05 | 2015-04-27 | 2015-05-29 | 2018-02-24 | COMP | 2018-03-20 | COMP | 2018-03-20 | COMP | 2019-03-14 | COMP | 2019-04-11 | COMP | Rule 16 | 98 | 24 | 17 | 1 | 248 | 21 | 1092
349 | 2014-12-05 | 2016-01-08 | 2016-03-08 | 2018-04-03 | COMP | 2018-11-14 | COMP | 2018-12-19 | COMP | 2018-12-11 | COMP | 2019-05-16 | COMP | Rule 16 | 274 | 41 | 158 | 24 | 0 | 103 | 1117
199 | 2014-12-11 | 2015-04-02 | 2015-11-16 | 2015-11-16 | COMP | 2015-12-30 | COMP | 2015-12-31 | COMP | 2018-06-08 | COMP | 2019-03-26 | COMP | Rule 15/16 | 77 | 159 | 30 | 2 | 614 | 199 | 1076
1017 | 2014-12-12 | 2017-03-01 | 2017-11-15 | 2017-11-15 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2020-01-09 | COMP | 2020-02-27 | COMP | Rule 16 | 556 | 182 | 459 | 1 | 80 | 34 | 1307
179 | 2014-12-15 | 2015-02-13 | 2020-01-09 | 2020-01-14 | COMP | 2020-01-03 | COMP | 2020-01-17 | COMP | 2023-04-16 | CANC | 2020-04-02 | COMP | Rule 15/16 | 42 | 1232 |  | 11 |  |  | 1331
178 | 2014-12-18 | 2015-02-10 | 2015-07-14 | 2015-07-14 | COMP | 2015-07-17 | COMP | 2015-07-20 | COMP | 2015-07-15 | COMP | 2019-04-15 | COMP | Rule 16 | 36 | 108 | 4 | 2 | 0 | 939 | 1085
176 | 2014-12-19 | 2015-02-02 | 2015-03-27 | 2015-03-27 | COMP | 2015-07-20 | COMP | 2015-07-20 | COMP | 2020-07-04 | INPR | 2020-04-30 | COMP | Other | 29 | 39 | 80 | 1 |  |  | 1347
177 | 2014-12-22 | 2015-02-06 | 2015-09-14 | 2015-09-14 | COMP | 2016-06-28 | COMP | 2016-06-28 | INPR | 2023-04-29 | CANC | 2020-06-17 | COMP | Rule 16 | 32 | 153 | 199 |  |  |  | 1379
206 | 2014-12-22 | 2015-04-09 | 2015-06-23 | 2015-06-23 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-11-26 | COMP | 2019-12-12 | COMP | Rule 16 | 75 | 53 | 916 | 1 | 199 | 11 | 1250
180 | 2014-12-26 | 2015-02-14 | 2015-04-14 | 2018-02-10 | COMP | 2018-06-07 | COMP | 2019-02-13 | COMP | 2019-03-06 | COMP | 2019-03-25 | COMP | Rule 15/16 | 34 | 41 | 82 | 172 | 15 | 14 | 1065
1661 | 2015-01-05 | 2017-07-13 | 2017-08-29 | 2017-08-29 | COMP | 2018-03-16 | COMP | 2018-03-16 | COMP | 2018-05-31 | COMP | 2019-04-19 | COMP | Rule 16 | 636 | 34 | 136 | 1 | 54 | 223 | 1079
181 | 2015-01-06 | 2015-02-17 | 2017-04-03 | 2020-05-13 | COMP | 2023-11-11 | PEND | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-08-06 | COMP | Rule 16 | 29 | 536 |  | 26 | 1 | 36 | 1406
408 | 2015-01-08 | 2016-04-05 | 2016-04-29 | 2016-04-29 | COMP | 2016-05-24 | COMP | 2016-06-01 | COMP | 2020-01-09 | COMP | 2020-01-10 | COMP | Rule 16 | 312 | 19 | 18 | 6 | 906 | 2 | 1258
1529 | 2015-01-08 | 2017-06-17 | 2017-09-15 | 2017-09-15 | COMP | 2019-08-14 | NOTN | 2019-08-14 | COMP |  | INPR | 2019-10-02 | COMP | Other | 615 | 63 |  | 480 |  |  | 1191
192 | 2015-01-12 | 2015-03-27 | 2017-06-21 | 2017-06-21 | COMP | 2017-06-29 | COMP | 2017-07-03 | COMP | 2020-08-01 | INPR | 2019-10-23 | COMP | Rule 15/16 | 53 | 564 | 7 | 3 |  |  | 1204
305 | 2015-01-13 | 2015-12-06 | 2016-08-18 | 2018-01-29 | COMP | 2018-02-22 | COMP | 2018-02-22 | COMP | 2018-03-29 | COMP | 2021-06-04 | COMP | Rule 15/16 | 226 | 178 | 18 | 1 | 26 | 802 | 1608
1756 | 2015-01-13 | 2017-07-19 | 2019-05-16 | 2019-05-16 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-09-22 | COMP | 2020-10-09 | COMP | Rule 16 | 634 | 459 | 159 | 1 | 184 | 14 | 1446
223 | 2015-01-21 | 2015-06-08 | 2016-06-29 | 2016-06-29 | COMP | 2017-11-07 | COMP | 2017-11-29 | COMP | 2018-11-13 | COMP | 2019-01-04 | COMP | Rule 15/16 | 97 | 268 | 344 | 14 | 242 | 35 | 995
186 | 2015-01-26 | 2015-03-10 | 2015-08-06 | 2017-06-19 | COMP | 2017-06-08 | COMP | 2018-03-23 | COMP | 2018-07-15 | COMP | 2021-03-22 | COMP | Rule 16 | 31 | 106 |  | 198 | 79 | 674 | 1547
208 | 2015-01-28 | 2015-04-14 | 2019-07-31 | 2019-07-31 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-01-09 | COMP | 2020-02-13 | COMP | Rule 16 | 54 | 1081 | 78 | 1 | 34 | 25 | 1268
197 | 2015-01-30 | 2015-04-02 | 2015-05-08 | 2015-05-08 | COMP | 2015-06-02 | COMP | 2015-06-02 | COMP | 2015-07-20 | COMP | 2019-04-22 | COMP | Rule 16 | 44 | 27 | 17 | 1 | 34 | 944 | 1062
443 | 2015-01-30 | 2016-05-02 | 2016-11-22 | 2016-11-22 | COMP | 2019-02-22 | COMP | 2019-03-07 | COMP | 2019-04-16 | COMP | 2019-04-18 | COMP | Rule 15/16 | 316 | 143 | 564 | 10 | 29 | 3 | 1060
203 | 2015-02-02 | 2015-04-08 | 2015-04-17 | 2015-04-17 | COMP | 2015-04-23 | COMP | 2015-04-23 | COMP | 2019-07-27 | INPR | 2019-07-27 | COMP | Rule 16 | 47 | 8 | 5 | 1 |  |  | 1128
204 | 2015-02-03 | 2015-04-08 | 2015-05-11 | 2015-05-11 | COMP | 2015-06-01 | COMP | 2015-06-01 | COMP | 2022-07-30 | INPR | 2021-07-16 | COMP | Rule 16 | 46 | 24 | 15 | 1 |  |  | 1623
392 | 2015-02-11 | 2016-03-15 | 2016-05-26 | 2016-05-26 | COMP | 2019-11-04 | COMP | 2019-01-15 | COMP | 2021-11-15 | COMP | 2022-02-06 | COMP | Rule 15/16 | 274 | 53 | 866 |  | 715 | 57 | 1757
185 | 2015-02-13 | 2015-03-10 | [7 empty] | 2015-03-12 | COMP | 2022-05-04 | COMP | Other | 17 | [5 empty] | 1817
430 | 2015-02-17 | 2016-04-22 | 2017-02-01 | 2017-02-01 | COMP | 2017-03-27 | COMP | 2017-03-27 | COMP | 2019-02-12 | COMP | 2019-03-28 | COMP | Rule 16 | 299 | 196 | 38 | 1 | 473 | 32 | 1034
765 | 2015-02-17 | 2016-11-14 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-06 | COMP | 2019-12-13 | COMP | 2020-01-14 | COMP | 2020-02-05 | COMP | Rule 15/16 | 441 | 465 | 35 | 276 | 21 | 16 | 1249
4191 | 2015-02-18 | 2019-06-19 | 2019-06-27 | 2019-06-27 | COMP | 2019-09-27 | COMP | 2020-02-03 | COMP | 2020-03-30 | COMP | 2020-06-16 | COMP | Rule 16 | 1091 | 7 | 65 | 86 | 40 | 56 | 1340
194 | 2015-02-19 | 2015-03-31 | 2015-06-05 | 2018-04-20 | COMP | 2018-07-18 | COMP | 2018-07-18 | COMP | 2021-06-19 | INPR | 2021-03-19 | COMP | Rule 15/16 | 29 | 48 | 62 | 1 |  |  | 1529
213 | 2015-02-24 | 2015-04-28 | 2015-07-27 | 2015-07-27 | COMP | 2018-01-17 | COMP | 2018-09-20 | COMP |  | REQD | 2019-07-26 | COMP | Rule 16 | 46 | 63 | 622 | 173 |  |  | 1113
222 | 2015-02-24 | 2015-06-06 | 2015-07-06 | 2019-06-04 | COMP | 2019-05-03 | COMP | 2019-11-27 | COMP | 2020-02-07 | COMP | 2020-04-23 | COMP | Rule 15/16 | 73 | 20 |  | 145 | 48 | 54 | 1299
698 | 2015-02-27 | 2016-10-15 | 2017-08-25 | 2017-08-25 | COMP | 2018-04-13 | COMP | 2018-08-09 | COMP | 2018-12-11 | COMP | 2019-01-03 | COMP | Rule 15/16 | 413 | 217 | 158 | 83 | 85 | 16 | 968
263 | 2015-03-03 | 2015-09-24 | 2015-10-26 | 2015-11-17 | COMP | 2015-11-30 | COMP | 2015-11-30 | COMP | 2016-07-15 | COMP | 2019-11-14 | COMP | Rule 16 | 145 | 23 | 8 | 1 | 159 | 839 | 1185
220 | 2015-03-04 | 2015-05-19 | 2015-06-19 | 2015-06-19 | COMP | 2015-06-26 | COMP | 2015-07-08 | COMP | 2015-08-10 | COMP | 2020-12-09 | COMP | Rule 16 | 55 | 23 | 6 | 8 | 24 | 1341 | 1452
313 | 2015-03-04 | 2015-12-17 | 2016-01-25 | 2016-01-25 | COMP | 2016-08-02 | COMP | 2018-01-02 | COMP | 2019-07-21 | REQD | 2019-04-12 | COMP | Rule 16 | 201 | 25 | 134 | 356 |  |  | 1034
406 | 2015-03-04 | 2016-03-29 | 2016-09-16 | 2016-09-16 | COMP | 2017-01-20 | COMP | 2019-03-13 | COMP | 2019-03-19 | COMP | 2019-10-06 | COMP | Rule 15/16 | 270 | 121 | 86 | 538 | 5 | 141 | 1156
201 | 2015-03-10 | 2015-04-06 | 2015-06-19 | 2015-06-19 | COMP | 2015-06-29 | COMP | 2015-07-03 | COMP | 2019-06-17 | COMP | 2019-08-30 | COMP | Rule 16 | 20 | 54 | 7 | 4 | 993 | 54 | 1128
187 | 2015-03-11 | 2015-03-11 | 2015-06-09 | 2015-06-09 | COMP | 2016-01-27 | COMP | 2016-01-28 | COMP | 2019-05-01 | COMP | 2019-06-07 | COMP | Rule 15/16 | 1 | 64 | 159 | 2 | 820 | 27 | 1068
288 | 2015-03-11 | 2015-11-04 | 2016-04-13 | 2016-04-13 | COMP | 2017-03-14 | COMP | 2017-03-14 | COMP | 2020-05-14 | COMP | 2020-06-10 | COMP | Rule 16 | 168 | 109 | 231 | 1 | 798 | 19 | 1321
193 | 2015-03-12 | 2015-03-30 | 2015-07-27 | 2015-07-27 | COMP | 2020-05-18 | COMP | 2017-01-31 | COMP | 2017-07-14 | COMP | 2021-03-30 | COMP | Rule 16 | 13 | 84 | 1209 |  | 116 | 931 | 1521
237 | 2015-03-12 | 2015-08-04 | 2017-07-31 | 2017-07-31 | COMP | 2017-08-28 | COMP | 2017-08-28 | COMP | 2019-01-04 | COMP | 2019-03-05 | COMP | Rule 16 | 102 | 501 | 21 | 1 | 339 | 41 | 1000
494 | 2015-03-12 | 2016-06-07 | 2017-02-09 | 2017-02-09 | COMP | 2017-03-27 | COMP | 2017-11-29 | COMP | 2019-10-19 | INPR | 2019-06-06 | COMP | Rule 16 | 313 | 171 | 32 | 172 |  |  | 1066
256 | 2015-03-17 | 2015-09-14 | 2016-10-08 | 2016-10-08 | COMP | 2017-10-25 | COMP | 2019-07-09 | COMP | 2021-04-28 | COMP | 2021-06-29 | COMP | Rule 15/16 | 127 | 270 | 264 | 426 | 455 | 44 | 1582
534 | 2015-03-17 | 2016-07-07 | 2017-01-14 | 2017-01-14 | COMP | 2017-08-08 | COMP | 2018-10-30 | COMP | 2017-05-03 | COMP | 2019-06-04 | COMP | Rule 15/16 | 331 | 132 | 143 | 310 | 0 | 148 | 1061
289 | 2015-03-18 | 2015-11-05 | 2016-01-04 | 2016-01-04 | COMP | 2016-01-25 | COMP | 2023-02-25 | REQD | 2023-02-25 | REQD | 2021-04-11 | COMP | Rule 16 | 164 | 38 | 15 |  |  |  | 1525
200 | 2015-03-20 | 2015-04-06 | 2015-05-20 | 2015-05-20 | COMP | 2015-06-03 | COMP | 2015-06-04 | COMP | 2015-06-09 | COMP | 2021-03-13 | COMP | Rule 16 | 12 | 33 | 10 | 2 | 4 | 1447 | 1503
191 | 2015-03-25 | 2015-03-27 | 2015-06-11 | 2015-06-11 | COMP | 2015-07-10 | COMP | 2015-07-16 | INPR | 2015-08-04 | COMP | 2019-05-02 | COMP | Rule 16 | 3 | 54 | 21 |  |  |  | 1033
205 | 2015-03-28 | 2015-04-08 | 2015-04-10 | 2015-04-10 | COMP | 2015-04-24 | COMP | 2015-04-24 | COMP | 2015-05-06 | COMP | 2019-07-27 | COMP | Rule 16 | 8 | 3 | 11 | 1 | 9 | 1062 | 1089
196 | 2015-03-30 | 2015-03-31 | 2016-05-23 | 2016-05-23 | COMP | 2017-04-13 | COMP | 2017-04-20 | COMP | 2017-08-01 | COMP | 2019-09-11 | COMP | Rule 16 | 2 | 290 | 225 | 6 | 72 | 531 | 1121
202 | 2015-03-31 | 2015-04-07 | 2015-06-05 | 2015-06-05 | COMP | 2015-08-10 | COMP | 2015-08-14 | COMP |  | INPR | 2019-04-16 | COMP | Other | 6 | 43 | 46 | 5 |  |  | 1017
239 | 2015-03-31 | 2015-08-12 | 2015-09-29 | 2015-12-18 | COMP | 2017-07-28 | COMP | 2017-08-10 | COMP | 2019-01-22 | COMP | 2019-08-21 | COMP | Rule 16 | 95 | 34 | 406 | 10 | 362 | 149 | 1106
262 | 2015-03-31 | 2015-09-22 | 2017-02-22 | 2022-08-02 | COMP | 2022-09-07 | COMP | 2022-09-23 | COMP | 2022-09-07 | COMP | 2023-10-25 | COMP | Rule 15/16 | 123 | 356 | 26 | 13 | 0 | 273 | 2156
1486 | 2015-04-06 | 2017-06-09 | 2017-10-06 | 2019-12-20 | COMP | 2020-11-13 | COMP | 2021-01-06 | COMP | 2021-03-10 | COMP | 2021-03-20 | COMP | Rule 15/16 | 550 | 84 | 229 | 35 | 44 | 8 | 1497
710 | 2015-04-08 | 2016-10-21 | 2017-01-22 | 2017-01-22 | COMP | 2017-08-23 | COMP | 2017-09-26 | COMP | 2021-11-29 | COMP | 2022-05-16 | COMP | Rule 16 | 390 | 61 | 150 | 24 | 1048 | 119 | 1788
216 | 2015-04-09 | 2015-05-08 | 2017-10-11 | 2018-09-08 | COMP | 2019-07-19 | COMP | 2019-08-07 | COMP | 2020-08-24 | COMP | 2020-09-16 | COMP | Rule 16 | 22 | 612 | 216 | 14 | 265 | 17 | 1369
238 | 2015-04-09 | 2015-08-05 | 2015-11-25 | 2015-11-25 | COMP | 2016-11-17 | COMP | 2016-11-17 | COMP | 2019-02-05 | COMP | 2019-03-21 | COMP | Rule 16 | 83 | 79 | 247 | 1 | 555 | 32 | 992
2154 | 2015-04-09 | 2017-09-30 | 2018-09-10 | 2018-09-10 | COMP | 2019-07-19 | COMP | 2019-08-21 | COMP | 2020-08-24 | COMP | 2020-09-16 | COMP | Rule 16 | 625 | 236 | 216 | 24 | 255 | 17 | 1369
272 | 2015-04-10 | 2015-10-08 | 2016-08-18 | 2017-07-14 | COMP | 2017-10-02 | COMP | 2017-10-05 | COMP | 2018-05-08 | COMP | 2020-04-13 | COMP | Rule 15/16 | 127 | 217 | 56 | 4 | 147 | 485 | 1258
847 | 2015-04-10 | 2016-12-19 | 2017-03-06 | 2017-03-06 | COMP | 2019-01-14 | COMP | 2019-01-15 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | Rule 15/16 | 426 | 53 | 468 | 2 | 236 | 1 | 1181
951 | 2015-04-10 | 2017-02-10 | 2017-09-18 | 2017-09-18 | COMP | 2018-05-30 | COMP | 2018-07-12 | COMP | 2019-03-05 | COMP | 2019-03-30 | COMP | Rule 15/16 | 463 | 153 | 175 | 31 | 161 | 19 | 997
1395 | 2015-04-10 | 2017-05-25 | 2017-07-13 | 2017-07-13 | COMP | 2017-09-19 | COMP | 2017-12-30 | COMP | 2018-05-10 | COMP | 2021-02-15 | COMP | Other | 536 | 34 | 48 | 70 | 91 | 694 | 1469
4800 | 2015-04-10 | 2018-03-31 | 2020-02-21 | 2020-05-19 | COMP | 2020-06-11 | COMP |  | REQD |  | REQD | 2020-11-12 | COMP | Rule 15/16 | 747 | 475 | 17 |  |  |  | 1408
279 | 2015-04-13 | 2015-10-22 | 2016-05-17 | 2016-05-17 | COMP | 2016-06-24 | COMP | 2016-06-30 | COMP | 2018-02-13 | COMP | 2019-02-13 | COMP | Rule 16 | 136 | 142 | 28 | 5 | 407 | 252 | 965
210 | 2015-04-15 | 2015-04-20 | 2015-09-24 | 2017-10-30 | COMP | 2018-06-20 | COMP | 2018-06-20 | COMP | 2019-08-27 | COMP | 2020-04-17 | COMP | Rule 16 | 4 | 111 | 160 | 1 | 299 | 161 | 1259
753 | 2015-04-16 | 2016-11-09 | 2017-04-10 | 2017-04-10 | COMP | 2017-04-20 | COMP | 2017-04-20 | COMP | 2019-06-01 | INPR | 2019-02-05 | COMP | Rule 16 | 397 | 103 | 9 | 1 |  |  | 956
352 | 2015-04-17 | 2016-01-12 | 2017-09-01 | 2019-03-26 | COMP | 2018-07-24 | COMP | 2019-02-06 | COMP | 2019-09-17 | COMP | 2020-01-31 | COMP | Rule 15/16 | 185 | 416 |  | 135 | 156 | 93 | 1203
211 | 2015-04-20 | 2015-04-23 | 2015-12-19 | 2016-09-09 | COMP | 2016-11-04 | COMP | 2017-05-25 | COMP | 2017-09-19 | COMP | 2021-05-17 | COMP | Rule 15/16 | 4 | 166 | 41 | 139 | 81 | 919 | 1528
217 | 2015-04-22 | 2015-05-11 | 2016-03-01 | 2015-07-24 | COMP | 2018-05-29 | COMP | 2020-01-22 | COMP | 2019-12-23 | COMP | 2021-10-27 | COMP | Rule 15/16 | 14 | 202 | 715 | 414 | 0 | 448 | 1640
264 | 2015-04-23 | 2015-09-25 | 2019-03-02 | 2019-03-02 | COMP | 2019-07-17 | COMP | 2020-01-18 | REQD | 2020-01-18 | REQD | 2019-08-31 | COMP | Rule 15/16 | 109 | 860 | 96 |  |  |  | 1096
241 | 2015-04-24 | 2015-08-14 | 2016-05-12 | 2016-05-12 | COMP | 2016-07-29 | COMP | 2016-12-09 | COMP | 2017-04-28 | COMP | 2020-02-24 | COMP | Rule 15/16 | 79 | 187 | 55 | 92 | 98 | 707 | 1213
282 | 2015-04-24 | 2015-10-27 | 2016-01-14 | 2016-01-14 | COMP | 2016-05-24 | COMP | 2016-05-24 | COMP | 2020-06-03 | COMP | 2020-06-04 | COMP | Rule 15/16 | 130 | 53 | 92 | 1 | 1012 | 2 | 1285
1761 | 2015-04-28 | 2017-07-20 | 2017-09-03 | 2017-09-03 | COMP | 2018-04-17 | COMP | 2018-04-17 | COMP | 2019-07-21 | INPR | 2019-02-26 | COMP | Rule 15/16 | 562 | 32 | 154 | 1 |  |  | 962
226 | 2015-04-30 | 2015-06-17 | 2015-08-12 | 2015-08-12 | COMP | 2015-10-16 | COMP | 2018-01-02 | COMP | 2022-07-16 | INPR | 2021-01-14 | COMP | Rule 16 | 34 | 40 | 47 | 554 |  |  | 1435
227 | 2015-04-30 | 2015-06-19 | 2015-09-13 | 2018-05-21 | COMP | 2019-07-24 | COMP | 2019-08-29 | COMP | 2019-09-04 | COMP | 2019-10-16 | COMP | Rule 15/16 | 36 | 59 | 296 | 27 | 4 | 31 | 1123
385 | 2015-05-01 | 2016-03-07 | 2016-04-19 | 2019-01-30 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-09-19 | COMP | 2019-08-05 | COMP | Rule 16 | 212 | 32 | 34 | 1 | 130 |  | 1071
219 | 2015-05-05 | 2015-05-13 | 2015-06-11 | 2015-06-11 | COMP | 2015-07-10 | COMP | 2015-07-10 | COMP | 2015-07-29 | COMP | 2022-05-04 | COMP | Rule 16 | 7 | 21 | 21 | 1 | 14 | 1702 | 1761
354 | 2015-05-05 | 2016-01-15 | 2016-12-07 | 2020-10-14 | COMP | 2021-07-07 | COMP | 2021-11-23 | COMP | 2021-12-07 | COMP | 2022-01-13 | COMP | Rule 15 | 176 | 226 | 182 | 98 | 9 | 28 | 1684
1818 | 2015-05-06 | 2017-08-02 | 2017-10-01 | 2017-10-01 | COMP | 2018-04-20 | COMP | 2018-04-25 | COMP | 2020-08-11 | COMP | 2020-09-24 | COMP | Other | 565 | 42 | 138 | 4 | 579 | 32 | 1356
268 | 2015-05-07 | 2015-10-02 | 2016-01-15 | 2017-03-09 | COMP | 2017-11-17 | COMP | 2017-11-15 | COMP | 2020-01-18 | INPR | 2019-06-24 | COMP | Rule 15/16 | 104 | 71 | 178 |  |  |  | 1038
359 | 2015-05-08 | 2016-01-23 | 2016-05-02 | 2020-01-27 | COMP | 2020-04-13 | COMP | 2020-05-18 | COMP | 2020-05-16 | COMP | 2020-06-09 | COMP | Rule 16 | 177 | 70 | 55 | 26 | 0 | 16 | 1278
275 | 2015-05-12 | 2015-10-19 | 2018-02-27 | 2018-02-27 | COMP | 2019-03-12 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2020-01-28 | COMP | Rule 16 | 112 | 591 | 261 | 61 | 1 | 162 | 1183
472 | 2015-05-12 | 2016-05-24 | 2016-11-10 | 2022-04-15 | COMP | 2022-06-15 | COMP | 2022-09-01 | COMP | 2022-08-29 | COMP | 2022-11-17 | COMP | Rule 16 | 261 | 120 | 43 | 55 | 0 | 54 | 1892
4080 | 2015-05-12 | 2019-01-11 | 2019-03-15 | 2019-03-15 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-10-19 | INPR | 2019-06-26 | COMP | Rule 15/16 | 922 | 44 | 38 | 1 |  |  | 1037
13411 | 2015-05-12 | 2019-07-25 | 2019-12-23 | 2019-12-23 | COMP | 2020-02-20 | COMP | 2020-03-23 | COMP | 2020-03-21 | COMP | 2020-06-03 | COMP | Rule 15/16 | 1057 | 104 | 40 | 23 | 0 | 52 | 1272
1087 | 2015-05-13 | 2017-03-23 | 2018-02-21 | 2018-02-21 | COMP | 2018-06-06 | COMP | 2019-12-18 | COMP | 2020-04-29 | COMP | 2020-05-23 | COMP | Rule 15/16 | 468 | 230 | 75 | 386 | 92 | 18 | 1264
840 | 2015-05-14 | 2016-12-15 | 2017-01-25 | 2017-01-25 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-07-05 | COMP | 2019-07-23 | COMP | Other | 400 | 28 | 605 | 1 | 11 | 13 | 1053
660 | 2015-05-16 | 2016-09-28 | 2016-11-29 | 2016-11-29 | COMP | 2018-02-02 | COMP | 2018-03-27 | COMP | 2018-01-29 | COMP | 2019-08-10 | COMP | Rule 15/16 | 345 | 42 | 297 | 37 | 0 | 347 | 1064
616 | 2015-05-19 | 2016-09-08 | 2017-04-18 | 2017-04-18 | COMP | 2017-04-27 | COMP | 2017-12-07 | COMP | 2018-01-23 | COMP | 2022-06-15 | COMP | Rule 15/16 | 330 | 153 | 8 | 155 | 31 | 1108 | 1780
1223 | 2015-05-21 | 2017-04-25 | 2017-08-15 | 2017-08-15 | COMP | 2017-12-26 | COMP | 2017-12-28 | COMP | 2019-10-10 | COMP | 2019-11-14 | COMP | Rule 16 | 485 | 79 | 91 | 3 | 450 | 25 | 1128
248 | 2015-05-26 | 2015-09-01 | 2015-11-10 | 2015-11-10 | COMP | 2016-02-12 | COMP | 2016-02-16 | COMP | 2019-03-05 | COMP | 2019-04-18 | COMP | Rule 16 | 70 | 50 | 63 | 2 | 767 | 33 | 980
283 | 2015-05-26 | 2015-10-28 | 2016-01-07 | 2018-01-23 | COMP | 2018-06-22 | COMP | 2018-10-02 | COMP | 2019-03-28 | COMP | 2019-06-28 | COMP | Rule 16 | 110 | 47 | 107 | 71 | 121 | 66 | 1030
4294 | 2015-05-29 | 2020-04-21 | 2020-05-01 | 2020-05-01 | COMP | 2020-08-21 | COMP | 2020-08-25 | COMP | 2020-09-01 | COMP | 2020-11-10 | COMP | Rule 16 | 1230 | 9 | 80 | 3 | 6 | 50 | 1373
242 | 2015-06-01 | 2015-08-17 | 2016-07-18 | 2018-11-19 | COMP | 2019-07-25 | COMP | 2019-07-25 | INPR | 2018-12-18 | COMP | 2019-03-23 | COMP | Rule 15/16 | 55 | 231 | 171 |  |  |  | 957
1127 | 2015-06-01 | 2017-03-31 | 2017-04-05 | 2017-04-05 | COMP | 2017-04-21 | COMP | 2017-04-21 | COMP | 2017-08-23 | COMP | 2022-01-23 | COMP | Rule 16 | 462 | 4 | 13 | 1 | 87 | 1109 | 1671
233 | 2015-06-03 | 2015-07-24 | 2015-10-26 | 2016-07-22 | COMP | 2016-10-19 | COMP | 2018-02-23 | COMP | 2019-05-10 | COMP | 2019-06-14 | COMP | Rule 15/16 | 37 | 66 | 63 | 337 | 306 | 25 | 1014
1411 | 2015-06-05 | 2017-05-30 | 2018-01-18 | 2018-01-18 | COMP | 2020-02-19 | COMP | 2020-03-12 | COMP | 2020-03-02 | COMP | 2020-07-25 | COMP | Rule 15/16 | 499 | 160 | 524 | 17 | 0 | 96 | 1292
1768 | 2015-06-08 | 2017-07-24 | 2018-06-07 | 2018-06-07 | COMP | 2018-07-13 | COMP | 2019-01-04 | COMP | 2020-11-21 | INPR | 2019-11-09 | COMP | Rule 16 | 536 | 220 | 26 | 120 |  |  | 1114
998 | 2015-06-11 | 2017-02-22 | 2017-06-16 | 2017-06-16 | COMP | 2020-05-07 | COMP | 2020-07-20 | COMP | 2020-04-03 | COMP | 2020-10-12 | COMP | Rule 15/16 | 427 | 82 | 726 | 52 | 0 | 60 | 1343
261 | 2015-06-12 | 2015-09-21 | 2015-10-22 | 2015-10-22 | COMP | 2017-09-21 | COMP | 2017-09-21 | INPR | 2019-03-11 | COMP | 2019-04-06 | COMP | Rule 15/16 | 70 | 24 | 482 |  |  |  | 958
366 | 2015-06-15 | 2016-02-03 | 2018-10-25 | 2018-12-05 | COMP | 2020-04-14 | COMP | 2020-09-21 | COMP |  | INPR | 2021-07-15 | COMP | Rule 15/16 | 160 | 689 | 341 | 113 |  |  | 1530
741 | 2015-06-17 | 2016-11-01 | 2017-03-20 | 2017-03-20 | COMP | 2017-03-31 | COMP | 2017-03-31 | COMP | 2017-06-01 | COMP | 2020-12-08 | COMP | Rule 16 | 348 | 94 | 10 | 1 | 44 | 885 | 1377
278 | 2015-06-18 | 2015-10-21 | 2015-11-18 | 2015-11-18 | COMP | 2015-11-24 | COMP | 2015-11-24 | COMP | 2015-12-11 | COMP | 2020-05-14 | COMP | Rule 16 | 88 | 20 | 5 | 1 | 12 | 1112 | 1233
229 | 2015-06-24 | 2015-07-07 | 2015-08-17 | 2015-10-02 | COMP | 2015-11-13 | COMP | 2015-11-21 | COMP | 2015-11-03 | COMP | 2021-02-25 | COMP | Rule 16 | 9 | 30 | 30 | 6 | 0 | 1320 | 1425
250 | 2015-06-24 | 2015-09-08 | 2016-05-10 | 2016-05-10 | COMP | 2018-04-02 | COMP | 2019-01-31 | COMP | 2019-09-05 | COMP | 2019-10-07 | COMP | Rule 15/16 | 53 | 169 | 476 | 210 | 152 | 23 | 1078
277 | 2015-06-24 | 2015-10-20 | 2016-06-02 | 2016-06-02 | COMP | 2017-05-25 | COMP | 2017-06-29 | COMP | 2017-06-23 | COMP | 2019-08-02 | COMP | Rule 15/16 | 83 | 155 | 248 | 25 | 0 | 526 | 1033
246 | 2015-06-26 | 2015-08-26 | 2015-10-29 | 2015-10-29 | COMP | 2015-11-25 | COMP | 2015-11-25 | COMP | 2019-09-21 | INPR | 2019-06-06 | COMP | Rule 16 | 43 | 46 | 19 | 1 |  |  | 991
1530 | 2015-06-29 | 2017-06-17 | 2017-08-24 | 2017-08-24 | COMP | 2018-03-01 | COMP | 2018-02-15 | COMP | 2018-02-12 | COMP | 2019-01-07 | COMP | Other | 496 | 48 | 128 |  | 0 | 224 | 885
1595 | 2015-06-29 | 2017-06-29 | 2017-08-10 | 2017-08-10 | COMP | 2018-04-12 | COMP | 2018-04-12 | INPR | 2020-07-22 | COMP | 2021-04-09 | COMP | Other | 505 | 30 | 168 |  |  |  | 1453
292 | 2015-06-30 | 2015-11-16 | 2017-11-22 | 2019-11-08 | COMP | 2019-11-12 | COMP | 2019-07-01 | COMP | 2019-11-08 | COMP | 2019-12-14 | COMP | Rule 16 | 97 | 509 | 2 |  | 93 | 23 | 1120
1908 | 2015-06-30 | 2017-08-18 | 2018-04-20 | 2018-04-20 | COMP | 2018-05-18 | COMP | 2018-06-19 | COMP | 2019-06-13 | COMP | 2019-07-12 | COMP | Rule 15/16 | 539 | 168 | 21 | 22 | 248 | 21 | 1014
232 | 2015-07-02 | 2015-07-21 | 2017-12-02 | 2019-10-18 | COMP | 2020-12-04 | COMP | 2020-12-22 | COMP |  | INPR | 2021-01-15 | COMP | Rule 15/16 | 13 | 596 | 284 | 13 |  |  | 1392
355 | 2015-07-02 | 2016-01-19 | 2017-12-11 | 2017-12-11 | COMP | 2021-01-12 | COMP | 2021-02-13 | COMP | 2021-03-12 | COMP | 2021-03-17 | COMP | Rule 15/16 | 136 | 479 | 776 | 23 | 19 | 4 | 1433
987 | 2015-07-02 | 2017-02-22 | 2017-10-03 | 2017-10-03 | COMP | 2017-06-01 | NOTN | 2018-01-08 | COMP | 2019-03-14 | COMP | 2020-06-30 | COMP | Other | 412 | 157 |  | 65 | 297 | 328 | 1255
230 | 2015-07-06 | 2015-07-10 | 2015-08-24 | 2015-08-24 | COMP | 2015-10-20 | COMP | 2015-10-20 | COMP | 2019-09-21 | INPR | 2019-06-03 | COMP | Rule 16 | 5 | 32 | 41 | 1 |  |  | 983
1120 | 2015-07-06 | 2017-03-28 | 2017-04-14 | 2017-04-14 | COMP | 2019-05-28 | COMP | 2017-05-01 | COMP | 2019-12-30 | COMP | 2020-01-10 | COMP | Rule 16 | 435 | 14 | 532 |  | 669 | 9 | 1135
4079 | 2015-07-06 | 2019-01-10 | 2019-05-17 | 2019-05-17 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-12-24 | COMP | 2020-01-10 | COMP | Rule 16 | 884 | 90 | 47 | 1 | 106 | 12 | 1135
273 | 2015-07-07 | 2015-10-12 | 2016-10-14 | 2016-10-14 | COMP | 2017-07-07 | COMP | 2017-09-15 | COMP | 2019-03-19 | COMP | 2019-07-21 | COMP | Rule 15/16 | 69 | 255 | 183 | 50 | 376 | 87 | 1015
440 | 2015-07-07 | 2016-04-29 | 2017-04-04 | 2017-04-04 | COMP | 2017-07-13 | COMP | 2017-07-13 | COMP | 2021-07-19 | COMP | 2023-04-01 | COMP | Rule 16 | 206 | 234 | 71 | 1 | 1009 | 428 | 1944
790 | 2015-07-08 | 2016-11-29 | 2017-07-25 | 2017-07-25 | COMP | 2018-03-14 | COMP | 2018-03-14 | COMP | 2019-03-21 | COMP | 2019-05-12 | COMP | Rule 16 | 351 | 166 | 159 | 1 | 257 | 37 | 966
690 | 2015-07-09 | 2016-10-12 | 2017-12-08 | 2017-12-08 | COMP | 2018-04-24 | COMP | 2019-07-25 | COMP |  | INPR | 2019-08-21 | COMP | Rule 16 | 319 | 291 | 94 | 316 |  |  | 1036
231 | 2015-07-10 | 2015-07-16 | 2017-04-19 | 2018-12-30 | COMP | 2021-06-07 | COMP | 2021-06-09 | COMP | 2021-06-08 | COMP | 2021-07-30 | COMP | Rule 16 | 5 | 443 | 613 | 3 | 0 | 37 | 1523
681 | 2015-07-13 | 2016-10-07 | 2017-10-29 | 2017-10-29 | COMP | 2018-10-08 | COMP | 2019-10-08 | COMP | 2021-05-10 | COMP | 2021-06-11 | COMP | Rule 16 | 314 | 267 | 236 | 252 | 399 | 24 | 1488
284 | 2015-07-15 | 2015-10-29 | 2015-12-15 | 2015-12-15 | COMP | 2016-02-11 | COMP | 2017-02-14 | COMP |  |  | 2020-01-10 | COMP | Rule 16 | 76 | 31 | 40 | 255 |  |  | 1128
508 | 2015-07-15 | 2016-06-22 | 2017-04-01 | 2017-04-01 | COMP | 2017-08-11 | COMP | 2019-03-14 | COMP | 2019-05-06 | COMP | 2019-05-31 | COMP | Rule 15/16 | 237 | 195 | 93 | 397 | 38 | 19 | 975
293 | 2015-07-16 | 2015-11-18 | 2016-07-25 | 2016-07-25 | COMP | 2019-04-04 | COMP | 2019-05-02 | COMP | 2019-04-04 | COMP | 2019-06-01 | COMP | Rule 15 | 88 | 171 | 677 | 21 | 0 | 21 | 974
345 | 2015-07-16 | 2016-01-08 | 2017-01-06 | 2017-01-06 | COMP | 2016-12-21 | COMP | 2017-02-28 | COMP | 2019-07-21 | INPR | 2019-04-25 | COMP | Rule 15/16 | 121 | 252 |  | 47 |  |  | 949
280 | 2015-07-17 | 2015-10-23 | 2017-08-16 | 2019-07-18 | COMP | 2019-07-31 | COMP | 2019-08-07 | COMP | 2019-04-08 | COMP | 2019-09-18 | COMP | Rule 16 | 70 | 456 | 10 | 6 | 0 | 30 | 1049
424 | 2015-07-20 | 2016-04-19 | 2016-07-25 | 2016-07-25 | COMP | 2017-05-15 | COMP | 2017-05-15 | COMP | 2017-06-02 | COMP | 2020-02-26 | COMP | Rule 15/16 | 189 | 68 | 204 | 1 | 14 | 685 | 1156
493 | 2015-07-20 | 2016-06-06 | 2017-03-14 | 2018-06-06 | COMP | 2023-04-29 | CANC | 2017-12-08 | COMP | 2018-08-30 | COMP | 2020-02-24 | COMP | Rule 15/16 | 222 | 194 |  |  | 184 | 370 | 1154
1381 | 2015-07-20 | 2017-05-23 | 2018-02-16 | 2019-02-01 | COMP | 2019-02-22 | COMP | 2019-03-08 | COMP | 2019-06-20 | COMP | 2019-07-26 | COMP | Rule 16 | 465 | 185 | 15 | 11 | 74 | 26 | 1011
815 | 2015-07-21 | 2016-12-08 | 2019-06-05 | 2019-06-05 | COMP | 2020-09-16 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2021-02-12 | COMP | Rule 15/16 | 349 | 626 | 325 | 67 | 1 | 36 | 1399
442 | 2015-07-22 | 2016-05-03 | 2016-08-16 | 2016-08-16 | COMP | 2016-10-11 | COMP | 2017-03-28 | INPR | 2019-08-08 | COMP | 2019-08-16 | COMP | Rule 15/16 | 197 | 74 | 40 |  |  |  | 1024
2056 | 2015-07-22 | 2017-09-15 | 2018-01-25 | 2018-01-25 | COMP | 2018-08-09 | COMP | 2018-10-17 | COMP | 2018-11-30 | COMP | 2019-01-29 | COMP | Rule 16 | 543 | 89 | 138 | 49 | 30 | 40 | 884
252 | 2015-07-30 | 2015-09-09 | 2016-08-26 | 2016-08-26 | COMP | 2017-06-20 | COMP | 2020-02-03 | COMP | 2020-11-05 | COMP | 2021-01-17 | COMP | Rule 15 | 29 | 244 | 205 | 657 | 196 | 47 | 1373
254 | 2015-07-30 | 2015-09-11 | 2015-11-22 | 2018-06-10 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-10-29 | COMP | 2019-11-07 | COMP | Rule 16 | 31 | 50 | 291 | 1 | 60 | 8 | 1076
260 | 2015-07-30 | 2015-09-19 | 2017-02-06 | 2019-01-23 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | Rule 15/16 | 36 | 346 | 191 | 1 | 79 | 1 | 1142
1508 | 2015-07-30 | 2017-06-13 | 2017-09-15 | 2019-01-24 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-02-18 | COMP | 2020-02-21 | COMP | Rule 16 | 471 | 67 | 190 | 1 | 79 | 4 | 1145
306 | 2015-07-31 | 2015-12-07 | 2016-02-28 | 2016-02-28 | COMP | 2016-04-08 | COMP | 2016-04-08 | COMP | 2019-02-04 | COMP | 2019-04-08 | COMP | Rule 16 | 88 | 56 | 30 | 1 | 709 | 45 | 925
705 | 2015-07-31 | 2016-10-20 | 2017-02-05 | 2017-02-05 | COMP | 2019-12-09 | COMP | 2019-05-16 | COMP | 2019-12-21 | COMP | 2019-09-06 | COMP | Rule 15/16 | 309 | 72 | 714 |  | 151 |  | 1031
24633 | 2015-07-31 | 2021-01-05 | 2021-05-06 | 2021-05-06 | COMP | 2022-05-09 | COMP | 2022-09-14 | COMP | 2023-07-06 | COMP | 2023-10-12 | COMP | Rule 15/16 | 1364 | 86 | 255 | 89 | 202 | 70 | 2061
244 | 2015-08-03 | 2015-08-24 | 2016-10-24 | 2019-01-17 | COMP | 2019-03-05 | COMP | 2019-06-07 | COMP | 2019-06-10 | COMP | 2019-10-14 | COMP | Rule 15/16 | 16 | 295 | 32 | 68 | 2 | 89 | 1056
247 | 2015-08-03 | 2015-08-26 | 2018-05-09 | 2019-04-20 | COMP | 2019-05-08 | COMP | 2019-06-07 | COMP | 2019-06-13 | COMP | 2019-09-05 | COMP | Rule 15/16 | 18 | 679 | 13 | 22 | 5 | 59 | 1029
290 | 2015-08-03 | 2015-11-10 | 2018-03-21 | 2018-03-21 | COMP | 2019-02-04 | COMP | 2019-06-07 | COMP | 2019-06-10 | COMP | 2019-10-14 | COMP | Rule 15/16 | 71 | 591 | 220 | 88 | 2 | 89 | 1056
334 | 2015-08-03 | 2016-01-03 | 2016-05-27 | 2016-05-27 | COMP | 2020-02-11 | COMP | 2016-09-01 | COMP | 2021-02-27 | INPR | 2020-02-12 | COMP | Rule 15/16 | 104 | 103 | 930 |  |  |  | 1137
245 | 2015-08-04 | 2015-08-24 | 2016-11-08 | 2019-01-15 | COMP | 2019-02-12 | COMP | 2019-06-07 | COMP | 2020-02-07 | COMP | 2020-06-10 | COMP | Rule 15/16 | 15 | 306 | 20 | 82 | 168 | 87 | 1219
266 | 2015-08-04 | 2015-09-29 | 2015-12-03 | 2015-12-03 | COMP | 2017-12-28 | COMP | 2018-01-05 | COMP | 2018-11-18 | COMP | 2019-01-11 | COMP | Rule 16 | 40 | 45 | 521 | 6 | 220 | 36 | 864
1197 | 2015-08-04 | 2017-04-18 | 2019-10-04 | 2019-10-04 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP |  | INPR | 2021-04-28 | COMP | Rule 16 | 429 | 621 | 9 | 1 |  |  | 1441
255 | 2015-08-05 | 2015-09-14 | 2016-04-18 | 2018-02-20 | COMP | 2018-03-15 | COMP | 2018-04-06 | COMP | 2020-03-26 | COMP | 2020-06-17 | COMP | Rule 15/16 | 28 | 149 | 18 | 17 | 495 | 59 | 1223
258 | 2015-08-10 | 2015-09-17 | 2018-03-21 | 2018-03-21 | COMP | 2018-06-25 | COMP | 2019-02-08 | COMP | 2019-03-15 | COMP | 2019-06-06 | COMP | Rule 16 | 28 | 629 | 68 | 157 | 25 | 59 | 961
251 | 2015-08-11 | 2015-09-09 | 2015-10-12 | 2015-10-12 | COMP | 2015-10-30 | COMP | 2015-11-05 | COMP | 2015-11-06 | COMP | 2021-03-04 | COMP | Rule 16 | 21 | 24 | 15 | 5 | 2 | 1335 | 1397
649 | 2015-08-11 | 2016-09-23 | 2016-12-14 | 2016-12-14 | COMP | 2021-11-18 | COMP | 2019-02-15 | COMP | 2021-11-09 | COMP | 2022-02-01 | COMP | Rule 15/16 | 283 | 56 | 1241 |  | 690 | 57 | 1628
650 | 2015-08-11 | 2016-09-23 | 2016-12-15 | 2016-12-15 | COMP | 2021-11-05 | COMP | 2019-02-15 | COMP | 2021-11-09 | COMP | 2022-02-01 | COMP | Rule 16 | 283 | 57 | 1232 |  | 690 | 57 | 1628
257 | 2015-08-17 | 2015-09-14 | 2016-05-27 | 2016-05-27 | COMP | 2018-08-08 | COMP | 2019-04-03 | INPR | 2019-02-26 | COMP | 2019-06-13 | COMP | Rule 15/16 | 20 | 178 | 553 |  |  |  | 961
523 | 2015-08-17 | 2016-06-28 | 2017-06-22 | 2017-06-22 | COMP | 2017-10-03 | COMP | 2017-10-03 | COMP | 2018-11-20 | COMP | 2019-03-18 | COMP | Rule 15/16 | 218 | 249 | 72 | 1 | 285 | 79 | 899
39140 | 2015-08-17 | 2022-10-03 | 2023-01-03 | 2023-01-03 | COMP | 2023-01-06 | NOTN | 2023-06-20 | COMP | 2023-05-08 | COMP | 2023-09-12 | COMP | Other | 1793 | 62 |  | 117 | 0 | 59 | 2028
419 | 2015-08-18 | 2016-04-18 | 2016-08-01 | 2022-02-20 | COMP | 2023-04-26 | COMP | 2023-04-26 | COMP | 2023-04-25 | COMP | 2023-08-02 | COMP | Rule 15/16 | 167 | 74 | 296 | 1 | 0 | 68 | 1999
243 | 2015-08-19 | 2015-08-24 | 2015-12-10 | 2015-12-10 | COMP | 2018-11-20 | COMP | 2020-07-09 | COMP | 2020-07-07 | COMP | 2020-11-10 | COMP | Rule 15/16 | 4 | 75 | 742 | 411 | 0 | 88 | 1316
249 | 2015-08-25 | 2015-09-01 | 2015-10-10 | 2015-10-10 | COMP | 2015-10-22 | COMP | 2015-11-25 | COMP | 2015-12-04 | COMP | 2019-04-24 | COMP | Rule 16 | 6 | 28 | 9 | 24 | 6 | 851 | 920
467 | 2015-08-26 | 2016-05-24 | 2016-09-09 | 2016-09-09 | COMP | 2018-12-18 | COMP | 2017-06-05 | COMP | 2019-01-26 | COMP | 2019-03-26 | COMP | Rule 15/16 | 187 | 76 | 571 |  | 412 | 41 | 898
798 | 2015-08-26 | 2016-12-02 | 2017-02-10 | 2018-09-24 | COMP | 2018-11-09 | COMP | 2017-10-27 | COMP | 2018-08-10 | COMP | 2019-03-19 | COMP | Rule 15/16 | 319 | 49 | 35 |  | 197 | 150 | 893
286 | 2015-08-27 | 2015-11-02 | 2016-01-10 | 2016-09-15 | COMP | 2016-09-30 | COMP | 2016-09-30 | COMP | 2017-02-16 | COMP | 2019-01-03 | COMP | Rule 16 | 47 | 45 | 12 | 1 | 95 | 472 | 841
271 | 2015-08-28 | 2015-10-05 | 2018-03-18 | 2018-03-18 | COMP | 2018-06-05 | COMP | 2018-07-27 | COMP |  | INPR | 2019-07-26 | COMP | Rule 15/16 | 26 | 614 | 56 | 38 |  |  | 982
287 | 2015-08-28 | 2015-11-02 | 2016-09-16 | 2019-01-25 | COMP | 2019-05-23 | COMP | 2019-07-23 | COMP | 2019-11-15 | COMP | 2019-12-19 | COMP | Rule 15/16 | 46 | 220 | 84 | 42 | 82 | 23 | 1082
365 | 2015-08-28 | 2016-02-03 | 2018-06-12 | 2018-09-06 | COMP | 2018-10-02 | COMP | 2018-11-06 | COMP | 2019-05-10 | COMP | 2019-10-23 | COMP | Rule 15/16 | 107 | 594 | 19 | 26 | 127 | 116 | 1044
383 | 2015-08-28 | 2016-03-01 | 2016-06-09 | 2020-06-12 | COMP | 2020-11-17 | COMP | 2021-03-29 | COMP | 2021-03-10 | COMP | 2021-05-21 | COMP | Rule 16 | 125 | 72 | 111 | 89 | 0 | 40 | 1440
590 | 2015-09-01 | 2016-08-19 | 2018-04-24 | 2018-04-24 | COMP | 2018-05-31 | COMP | 2018-05-31 | COMP | 2018-07-24 | COMP | 2019-06-19 | COMP | Rule 16 | 244 | 421 | 27 | 1 | 38 | 228 | 954
274 | 2015-09-03 | 2015-10-15 | 2015-12-02 | 2015-12-02 | COMP | 2016-03-22 | COMP | 2016-03-22 | COMP | 2019-10-03 | COMP | 2019-11-07 | COMP | Rule 16 | 30 | 32 | 76 | 1 | 891 | 26 | 1051
269 | 2015-09-04 | 2015-10-03 | 2015-10-06 | 2015-10-06 | COMP | 2015-10-30 | COMP | 2018-01-05 | COMP | 2019-04-03 | COMP | 2019-04-02 | COMP | Rule 16 | 20 | 2 | 19 | 547 | 312 |  | 896
253 | 2015-09-08 | 2015-09-11 | 2015-11-25 | 2018-07-20 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2020-02-14 | COMP | 2020-04-02 | COMP | Other | 4 | 53 | 195 | 1 | 200 | 34 | 1147
265 | 2015-09-08 | 2015-09-28 | 2017-03-20 | 2017-03-20 | COMP | 2017-08-08 | COMP | 2018-01-22 | COMP | 2019-01-23 | COMP | 2019-02-25 | COMP | Rule 15/16 | 15 | 370 | 100 | 113 | 253 | 23 | 869
304 | 2015-09-08 | 2015-12-04 | 2018-08-12 | 2018-08-12 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2023-04-15 | CANC | 2021-05-14 | COMP | Rule 15/16 | 61 | 676 | 163 | 1 |  |  | 1429
1966 | 2015-09-08 | 2017-08-28 | 2018-09-28 | 2019-01-23 | COMP | 2019-04-15 | COMP | 2023-04-15 | CANC | 2023-04-15 | CANC | 2020-06-02 | COMP | Rule 15/16 | 497 | 274 | 58 |  |  |  | 1189
3771 | 2015-09-08 | 2018-07-12 | 2019-01-04 | 2019-01-04 | COMP | 2019-03-28 | COMP | 2019-04-10 | COMP | 2020-11-21 | INPR | 2019-10-23 | COMP | Rule 15/16 | 715 | 121 | 58 | 10 |  |  | 1038
353 | 2015-09-09 | 2016-01-14 | 2016-03-04 | 2016-03-04 | COMP | 2016-04-20 | COMP | 2019-03-06 | COMP | 2019-07-19 | COMP | 2019-11-17 | COMP | Rule 16 | 87 | 35 | 34 | 722 | 96 | 84 | 1053
9045 | 2015-09-09 | 2019-01-15 | 2019-02-05 | 2019-02-05 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-03-11 | COMP | 2021-05-21 | COMP | Rule 15 | 841 | 15 | 26 | 1 | 0 | 554 | 1433
307 | 2015-09-10 | 2015-12-08 | 2016-02-22 | 2020-06-01 | COMP | 2021-04-16 | COMP | 2021-07-01 | COMP | 2021-07-14 | COMP | 2021-07-20 | COMP | Rule 16 | 61 | 51 | 222 | 54 | 9 | 5 | 1472
1951 | 2015-09-10 | 2017-08-25 | 2018-02-27 | 2018-02-27 | COMP | 2018-03-20 | COMP | 2018-03-22 | COMP | 2021-07-10 | COMP | 2021-08-12 | COMP | Rule 15/16 | 494 | 125 | 16 | 3 | 831 | 24 | 1489
318 | 2015-09-14 | 2015-12-18 | 2016-05-10 | 2016-05-10 | COMP | 2017-04-05 | COMP | 2017-07-14 | COMP | 2018-10-26 | COMP | 2019-05-20 | COMP | Rule 16 | 67 | 99 | 228 | 71 | 325 | 140 | 925
335 | 2015-09-14 | 2016-01-04 | 2016-03-17 | 2016-03-17 | COMP | 2017-04-05 | COMP | 2017-07-14 | COMP | 2018-10-26 | COMP | 2019-06-04 | COMP | Rule 16 | 76 | 52 | 266 | 71 | 325 | 150 | 935
373 | 2015-09-14 | 2016-02-18 | 2016-06-01 | 2016-06-01 | COMP | 2016-08-31 | COMP | 2016-12-02 | COMP | 2017-08-15 | COMP | 2019-05-31 | COMP | Rule 15/16 | 107 | 74 | 65 | 64 | 178 | 450 | 933
351 | 2015-09-15 | 2016-01-09 | 2016-03-04 | 2016-03-04 | COMP | 2016-05-17 | COMP | 2016-05-17 | COMP | 2019-06-29 | INPR | 2019-04-30 | COMP | Rule 16 | 79 | 38 | 53 | 1 |  |  | 910
2848 | 2015-09-16 | 2018-02-07 | 2018-03-29 | 2018-03-29 | COMP | 2019-06-28 | COMP | 2019-08-05 | COMP | 2019-07-31 | COMP | 2019-09-17 | COMP | Rule 16 | 601 | 36 | 316 | 26 | 0 | 31 | 1006
294 | 2015-09-17 | 2015-11-24 | 2019-04-04 | 2019-04-04 | COMP | 2020-01-22 | COMP | 2020-03-30 | COMP | 2020-04-03 | COMP | 2020-04-29 | COMP | Rule 16 | 48 | 843 | 201 | 48 | 5 | 19 | 1159
10176 | 2015-09-17 | 2019-03-05 | 2019-10-15 | 2019-10-15 | COMP | 2019-11-27 | NOTN | 2019-11-27 | COMP | 2019-12-11 | COMP | 2020-09-14 | COMP | Other | 868 | 158 |  | 31 | 9 | 193 | 1255
17975 | 2015-09-17 | 2020-03-06 | 2020-03-13 | 2020-03-13 | COMP | 2020-03-17 | NOTN | 2020-05-11 | COMP | 2020-05-19 | COMP | 2020-09-16 | COMP | Other | 1121 | 6 |  | 42 | 7 | 85 | 1257
391 | 2015-09-18 | 2016-03-15 | 2016-05-25 | 2016-05-25 | COMP | 2016-08-15 | COMP | 2016-08-09 | COMP | 2019-07-21 | INPR | 2019-01-10 | COMP | Rule 16 | 121 | 52 | 57 |  |  |  | 831
637 | 2015-09-21 | 2016-09-17 | 2017-02-24 | 2017-02-24 | COMP | 2018-01-26 | COMP | 2018-01-26 | COMP | 2019-04-09 | COMP | 2019-05-01 | COMP | Rule 16 | 250 | 109 | 232 | 1 | 302 | 17 | 907
1078 | 2015-09-23 | 2017-03-22 | 2017-06-02 | 2017-06-02 | COMP | 2017-08-10 | COMP | 2017-08-10 | COMP |  | INPR | 2021-11-03 | COMP | Rule 16 | 375 | 52 | 49 | 1 |  |  | 1538
2244 | 2015-09-23 | 2017-10-20 | 2018-06-01 | 2018-06-01 | COMP | 2019-12-11 | COMP | 2020-01-17 | COMP | 2021-02-23 | COMP | 2021-06-04 | COMP | Rule 15/16 | 524 | 153 | 384 | 26 | 277 | 73 | 1432
423 | 2015-09-24 | 2016-04-19 | 2016-06-22 | 2016-06-22 | COMP | 2016-06-22 | NOTN | 2016-06-22 | COMP | 2021-12-22 | COMP | 2022-01-22 | COMP | Other | 142 | 46 |  | 1 | 1383 | 22 | 1590
310 | 2015-09-25 | 2015-12-10 | 2018-08-28 | 2018-08-28 | COMP | 2019-02-26 | COMP | 2019-03-06 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | Rule 16 | 52 | 684 | 123 | 7 | 116 | 1 | 978
387 | 2015-09-25 | 2016-03-09 | 2018-01-23 | 2018-01-23 | COMP | 2019-01-24 | COMP | 2019-02-19 | COMP | 2021-04-07 | COMP | 2021-06-08 | COMP | Rule 15/16 | 112 | 472 | 253 | 18 | 538 | 44 | 1432
598 | 2015-09-25 | 2016-08-25 | 2017-03-03 | 2017-03-03 | COMP | 2018-02-05 | COMP | 2018-02-08 | COMP | 2019-01-08 | COMP | 2019-01-11 | COMP | Rule 15/16 | 231 | 130 | 233 | 4 | 230 | 4 | 827
370 | 2015-09-28 | 2016-02-16 | 2016-03-04 | 2016-03-04 | COMP | 2019-07-18 | COMP | 2020-01-17 | COMP | 2020-01-31 | COMP | 2020-04-10 | COMP | Rule 16 | 95 | 14 | 849 | 126 | 10 | 50 | 1139
539 | 2015-09-29 | 2016-07-14 | 2017-04-24 | 2017-04-24 | COMP | 2018-06-08 | COMP | 2018-06-11 | COMP | 2020-02-24 | COMP | 2020-04-29 | COMP | Rule 15/16 | 199 | 196 | 284 | 2 | 427 | 48 | 1151
618 | 2015-09-29 | 2016-09-09 | 2016-10-18 | 2016-10-18 | COMP | 2016-11-14 | COMP | 2016-11-14 | COMP | 2018-11-08 | COMP | 2019-01-28 | COMP | Rule 16 | 239 | 28 | 19 | 1 | 501 | 52 | 835
775 | 2015-09-30 | 2016-11-18 | 2017-04-26 | 2017-04-26 | COMP | 2017-07-18 | COMP | 2018-05-14 | COMP | 2020-03-24 | COMP | 2019-04-16 | COMP | Rule 16 | 287 | 109 | 58 | 207 | 467 |  | 889
338 | 2015-10-02 | 2016-01-06 | 2016-03-12 | 2016-03-12 | COMP | 2016-04-04 | COMP | 2016-04-05 | COMP | 2020-09-15 | COMP | 2020-12-23 | COMP | Rule 15/16 | 64 | 46 | 16 | 2 | 1120 | 69 | 1313
302 | 2015-10-05 | 2015-12-03 | 2017-02-17 | 2017-02-17 | COMP | 2018-05-29 | COMP | 2018-07-02 | COMP | 2020-02-29 | REQD | 2019-11-20 | COMP | Rule 16 | 41 | 305 | 321 | 25 |  |  | 1038
350 | 2015-10-05 | 2016-01-08 | 2016-06-04 | 2016-06-04 | COMP | 2016-12-14 | COMP | 2016-12-14 | COMP | 2018-11-21 | COMP | 2019-05-30 | COMP | Rule 16 | 65 | 103 | 133 | 1 | 489 | 130 | 917
490 | 2015-10-05 | 2016-06-03 | 2017-03-14 | 2017-03-14 | COMP | 2017-06-26 | COMP | 2017-06-26 | COMP | 2020-01-07 | COMP | 2020-02-29 | COMP | Rule 15/16 | 167 | 195 | 74 | 1 | 635 | 37 | 1104
565 | 2015-10-05 | 2016-08-01 | 2016-09-07 | 2016-09-07 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-08-16 | COMP | 2019-10-22 | COMP | Rule 16 | 207 | 27 | 753 | 1 | 0 | 34 | 1018
1076 | 2015-10-05 | 2017-03-21 | 2017-08-07 | 2017-08-07 | COMP | 2017-09-19 | COMP | 2018-04-16 | COMP | 2019-02-04 | COMP | 2019-04-01 | COMP | Rule 16 | 366 | 98 | 31 | 143 | 202 | 40 | 875
308 | 2015-10-06 | 2015-12-09 | 2016-02-25 | 2016-02-25 | COMP | 2017-08-31 | COMP | 2017-08-31 | COMP | 2019-08-21 | COMP | 2019-09-20 | COMP | Rule 16 | 44 | 53 | 385 | 1 | 495 | 22 | 995
549 | 2015-10-06 | 2016-07-20 | 2017-05-06 | 2017-05-06 | COMP | 2017-06-26 | COMP | 2017-06-26 | COMP | 2018-02-23 | COMP | 2019-03-15 | COMP | Rule 16 | 198 | 201 | 35 | 1 | 166 | 266 | 863
300 | 2015-10-08 | 2015-12-02 | 2016-05-25 | 2016-05-25 | COMP | 2018-06-11 | COMP | 2017-11-17 | COMP | 2020-01-18 | INPR | 2019-03-18 | COMP | Rule 16 | 37 | 122 | 514 |  |  |  | 862
301 | 2015-10-08 | 2015-12-02 | 2016-05-31 | 2016-05-31 | COMP | 2017-11-15 | COMP | 2019-01-07 | COMP | 2019-03-12 | COMP | 2019-04-03 | COMP | Rule 15/16 | 37 | 125 | 370 | 285 | 45 | 17 | 874
622 | 2015-10-08 | 2016-09-11 | 2017-10-02 | 2017-10-02 | COMP | 2018-03-02 | COMP | 2018-03-02 | COMP | 2023-04-15 | INPR | 2021-09-10 | COMP | Rule 15/16 | 232 | 267 | 103 | 1 |  |  | 1489
291 | 2015-10-12 | 2015-11-13 | 2016-07-18 | 2016-07-18 | COMP | 2017-12-15 | COMP | 2018-08-31 | COMP | 2018-11-24 | COMP | 2019-01-28 | COMP | Rule 15/16 | 24 | 169 | 357 | 180 | 57 | 43 | 826
560 | 2015-10-12 | 2016-07-28 | 2017-05-18 | 2017-05-18 | COMP | 2017-07-24 | COMP | 2017-08-16 | COMP | 2017-06-02 | COMP | 2019-05-30 | COMP | Rule 16 | 200 | 204 | 46 | 18 | 0 | 448 | 912
393 | 2015-10-13 | 2016-03-15 | 2017-12-02 | 2020-06-05 | COMP | 2020-07-07 | COMP | 2020-07-08 | COMP | 2020-07-31 | COMP | 2020-10-08 | COMP | Rule 15/16 | 104 | 434 | 23 | 2 | 18 | 49 | 1255
517 | 2015-10-13 | 2016-06-27 | 2016-12-07 | 2018-07-14 | COMP | 2021-07-30 | COMP | 2019-01-09 | INPR | 2022-03-29 | COMP | 2022-07-27 | COMP | Other | 177 | 113 | 766 |  |  |  | 1706
332 | 2015-10-15 | 2015-12-27 | 2016-05-11 | 2019-03-14 | COMP | 2019-01-28 | COMP | 2019-07-06 | COMP | 2019-06-25 | COMP | 2019-10-15 | COMP | Rule 15/16 | 48 | 95 |  | 112 | 0 | 71 | 1005
481 | 2015-10-16 | 2016-05-27 | 2017-03-07 | 2019-03-14 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-02-23 | COMP | 2019-06-05 | COMP | Rule 15/16 | 154 | 194 | 4 | 1 | 0 | 56 | 912
737 | 2015-10-16 | 2016-10-27 | 2017-01-07 | 2017-01-07 | COMP | 2018-06-07 | COMP | 2018-06-15 | COMP | 2019-06-10 | COMP | 2019-10-01 | COMP | Rule 16 | 260 | 48 | 356 | 7 | 247 | 80 | 994
311 | 2015-10-20 | 2015-12-13 | 2018-08-18 | 2018-08-18 | COMP | 2018-09-17 | COMP | 2018-10-30 | COMP | 2018-11-26 | COMP | 2019-04-16 | COMP | Rule 16 | 36 | 675 | 20 | 32 | 17 | 98 | 875
276 | 2015-10-21 | 2015-10-21 | 2015-11-18 | 2015-11-18 | COMP | 2016-09-19 | COMP | 2016-09-19 | INPR | 2016-10-10 | COMP | 2022-07-23 | COMP | Other | 1 | 20 | 210 |  |  |  | 1697
303 | 2015-10-21 | 2015-12-04 | 2016-06-01 | 2016-06-01 | COMP | 2017-10-19 | COMP | 2017-10-19 | COMP | 2019-06-29 | INPR | 2019-03-08 | COMP | Rule 16 | 30 | 124 | 351 | 1 |  |  | 847
3244 | 2015-10-21 | 2018-03-27 | 2018-04-06 | 2018-08-29 | COMP | 2019-06-13 | COMP | 2020-08-14 | COMP | 2020-06-18 | COMP | 2020-10-22 | COMP | Rule 16 | 609 | 9 | 198 | 297 | 0 | 49 | 1259
1165 | 2015-10-22 | 2017-04-11 | 2017-06-22 | 2017-06-22 | COMP | 2017-07-25 | COMP | 2017-07-25 | COMP | 2018-03-19 | COMP | 2019-04-11 | COMP | Rule 16 | 368 | 52 | 23 | 1 | 162 | 269 | 870
15390 | 2015-10-22 | 2019-10-29 | 2020-02-13 | 2020-02-13 | COMP | 2020-03-11 | COMP | 2020-06-01 | INPR | 2020-05-31 | COMP | 2020-08-26 | COMP | Rule 16 | 1010 | 72 | 19 |  |  |  | 1218
39322 | 2015-10-22 | 2022-10-12 | 2023-05-11 | 2023-05-11 | COMP | 2023-06-12 | COMP | 2023-08-16 | COMP | 2023-09-19 | COMP | 2023-09-20 | COMP | Rule 15/16 | 1753 | 145 | 22 | 46 | 24 | 2 | 1987
1502 | 2015-10-27 | 2017-06-12 | 2018-12-05 | 2019-10-26 | COMP | 2021-03-17 | COMP | 2021-07-08 | COMP | 2021-07-03 | COMP | 2021-07-17 | COMP | Rule 16 | 408 | 373 | 347 | 80 | 0 | 7 | 1437
4204 | 2015-10-27 | 2019-07-12 | 2019-10-26 | 2019-10-26 | COMP | 2021-03-25 | NOTN | 2021-03-25 | COMP | 2021-03-25 | COMP | 2021-07-17 | COMP | Other | 931 | 75 |  | 353 | 1 | 80 | 1437
410 | 2015-10-28 | 2016-04-07 | 2016-10-05 | 2018-10-02 | COMP | 2019-04-11 | COMP | 2019-04-12 | COMP | 2019-04-11 | COMP | 2019-05-31 | COMP | Rule 16 | 110 | 127 | 131 | 2 | 0 | 35 | 901
420 | 2015-10-28 | 2016-04-18 | 2016-10-01 | 2016-10-01 | COMP | 2019-01-04 | COMP | 2018-12-12 | COMP | 2018-12-21 | COMP | 2020-06-05 | COMP | Rule 15/16 | 117 | 117 | 566 |  | 8 | 366 | 1156
738 | 2015-10-28 | 2016-10-27 | 2016-12-22 | 2016-12-22 | COMP | 2017-01-10 | COMP | 2017-04-12 | COMP | 2017-05-12 | COMP | 2019-01-31 | COMP | Rule 16 | 252 | 38 | 13 | 65 | 23 | 431 | 817
1131 | 2015-10-28 | 2017-04-01 | 2017-04-09 | 2017-04-09 | COMP | 2018-03-06 | COMP | 2018-03-06 | COMP | 2019-08-17 | COMP | 2019-09-12 | COMP | Rule 16 | 357 | 5 | 227 | 1 | 367 | 18 | 973
299 | 2015-10-30 | 2015-12-02 | 2016-03-31 | 2016-03-31 | COMP | 2016-06-29 | COMP | 2018-01-02 | COMP | 2019-08-31 | INPR | 2019-05-13 | COMP | Rule 15/16 | 21 | 83 | 64 | 379 |  |  | 886
309 | 2015-10-30 | 2015-12-10 | 2015-12-18 | 2015-12-18 | COMP | 2020-04-17 | COMP | 2018-01-03 | COMP | 2020-06-01 | COMP | 2020-06-22 | COMP | Rule 15/16 | 27 | 7 | 1088 |  | 606 | 16 | 1165
381 | 2015-11-02 | 2016-02-26 | 2016-04-06 | 2016-04-06 | COMP | 2016-06-03 | COMP | 2019-06-21 | COMP | 2019-04-24 | COMP | 2019-07-17 | COMP | Rule 16 | 78 | 29 | 42 | 767 | 0 | 18 | 930
362 | 2015-11-03 | 2016-01-26 | 2016-07-18 | 2016-07-18 | COMP | 2019-01-30 | COMP | 2017-06-27 | COMP | 2019-05-16 | COMP | 2019-06-28 | COMP | Rule 15/16 | 55 | 122 | 637 |  | 474 | 31 | 917
295 | 2015-11-05 | 2015-12-01 | 2017-04-03 | 2017-04-03 | COMP | 2018-08-27 | COMP | 2018-09-04 | COMP | 2018-09-04 | COMP | 2019-07-11 | COMP | Rule 16 | 16 | 337 | 354 | 6 | 1 | 214 | 923
658 | 2015-11-10 | 2016-09-28 | 2017-08-25 | 2017-08-30 | COMP | 2018-07-25 | COMP | 2018-09-24 | COMP | 2019-02-28 | COMP | 2019-05-08 | COMP | Rule 15/16 | 222 | 230 | 226 | 43 | 107 | 50 | 876
2195 | 2015-11-11 | 2017-10-11 | 2018-04-16 | 2018-04-16 | COMP | 2018-10-22 | COMP | 2021-02-28 | REQD | 2018-12-05 | COMP | 2019-01-15 | COMP | Rule 15/16 | 482 | 127 | 133 |  |  |  | 796
395 | 2015-11-16 | 2016-03-21 | 2016-08-26 | 2019-03-11 | COMP | 2019-04-05 | COMP | 2019-06-21 | COMP | 2019-09-13 | COMP | 2019-11-22 | COMP | Rule 15/16 | 85 | 113 | 20 | 55 | 59 | 50 | 1011
2202 | 2015-11-16 | 2017-10-10 | 2018-12-03 | 2018-12-03 | COMP | 2018-12-18 | COMP | 2019-02-26 | COMP | 2019-09-21 | INPR | 2019-06-06 | COMP | Rule 16 | 479 | 287 | 12 | 47 |  |  | 893
603 | 2015-11-18 | 2016-08-31 | 2016-11-21 | 2019-10-18 | COMP | 2019-11-12 | COMP | 2017-06-20 | COMP | 2023-11-04 | INPR | 2019-12-04 | COMP | Rule 16 | 198 | 57 | 17 |  |  |  | 1015
1912 | 2015-11-18 | 2017-08-21 | 2018-10-11 | 2018-10-11 | COMP | 2020-07-14 | COMP | 2022-01-07 | COMP | 2021-12-01 | COMP | 2021-11-04 | COMP | Rule 16 | 442 | 288 | 441 | 375 | 0 |  | 1500
938 | 2015-11-19 | 2017-02-07 | 2017-05-02 | 2017-05-02 | COMP | 2018-01-03 | COMP | 2018-01-03 | COMP | 2019-07-11 | COMP | 2019-08-15 | COMP | Rule 16 | 305 | 60 | 169 | 1 | 383 | 26 | 939
579 | 2015-11-23 | 2016-08-11 | 2017-07-27 | 2017-07-27 | COMP | 2018-06-13 | COMP | 2018-08-13 | COMP | 2019-05-23 | COMP | 2019-02-17 | COMP | Rule 16 | 181 | 242 | 221 | 43 | 196 |  | 811
377 | 2015-11-24 | 2016-02-21 | 2017-06-23 | 2017-06-23 | COMP | 2018-12-06 | COMP | 2019-01-28 | COMP |  | REQD | 2019-04-24 | COMP | Rule 15/16 | 58 | 340 | 365 | 35 |  |  | 857
396 | 2015-11-24 | 2016-03-21 | 2017-07-25 | 2018-03-27 | COMP | 2018-04-19 | COMP | 2018-09-28 | COMP | 2018-10-05 | COMP | 2019-01-10 | COMP | Rule 16 | 79 | 341 | 18 | 114 | 6 | 65 | 785
399 | 2015-11-24 | 2016-03-22 | 2016-07-15 | 2019-07-22 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2019-09-19 | COMP | 2020-02-28 | COMP | Rule 16 | 80 | 82 | 54 | 1 | 0 | 99 | 1069
538 | 2015-11-30 | 2016-07-11 | 2016-08-30 | 2016-08-30 | COMP | 2019-04-02 | COMP | 2019-04-02 | INPR | 2019-10-19 | REQD | 2019-06-07 | COMP | Rule 15/16 | 155 | 37 | 649 |  |  |  | 886
453 | 2015-12-02 | 2016-05-09 | 2016-06-13 | 2018-02-20 | COMP | 2018-07-19 | COMP | 2018-07-19 | COMP | 2019-10-15 | COMP | 2019-12-03 | COMP | Rule 16 | 110 | 25 | 106 | 1 | 313 | 33 | 1006
503 | 2015-12-02 | 2016-06-16 | 2017-04-10 | 2017-10-15 | COMP | 2018-04-03 | COMP | 2018-10-25 | COMP | 2018-10-18 | COMP | 2019-01-09 | COMP | Rule 15/16 | 137 | 205 | 115 | 145 | 0 | 50 | 780
739 | 2015-12-03 | 2016-10-31 | 2017-08-15 | 2017-08-15 | COMP | 2017-09-07 | COMP | 2017-09-07 | COMP | 2019-06-20 | COMP | 2019-07-18 | COMP | Other | 231 | 199 | 17 | 1 | 448 | 20 | 911
358 | 2015-12-04 | 2016-01-22 | 2017-04-24 | 2017-04-24 | COMP | 2017-08-08 | COMP | 2018-09-17 | COMP | 2019-04-20 | INPR | 2019-01-11 | COMP | Rule 15/16 | 33 | 317 | 75 | 279 |  |  | 780
403 | 2015-12-07 | 2016-03-25 | 2016-04-20 | 2016-04-20 | COMP | 2017-06-09 | COMP | 2017-06-15 | COMP | 2018-06-04 | COMP | 2021-02-25 | COMP | Rule 16 | 76 | 19 | 288 | 5 | 243 | 686 | 1312
418 | 2015-12-07 | 2016-04-15 | 2016-06-03 | 2016-06-03 | COMP | 2018-11-01 | COMP | 2018-11-17 | COMP | 2019-03-19 | COMP | 2019-03-25 | COMP | Rule 16 | 91 | 35 | 609 | 11 | 81 | 5 | 828
5617 | 2015-12-07 | 2018-06-20 | 2018-11-08 | 2019-02-20 | COMP | 2019-03-12 | COMP | 2018-12-31 | COMP | 2019-06-28 | COMP | 2019-08-12 | COMP | Rule 16 | 639 | 100 | 15 |  | 126 | 31 | 926
312 | 2015-12-08 | 2015-12-17 | 2016-09-01 | 2016-09-01 | COMP | 2020-02-06 | COMP | 2020-05-11 | COMP | 2023-01-27 | COMP | 2023-04-05 | COMP | Rule 15/16 | 8 | 180 | 860 | 67 | 683 | 48 | 1841
526 | 2015-12-08 | 2016-06-29 | 2016-11-23 | 2016-11-23 | COMP | 2020-10-27 | COMP | 2020-10-27 | COMP | 2020-09-02 | COMP | 2020-12-10 | COMP | Other | 142 | 103 | 988 | 1 | 0 | 30 | 1260
527 | 2015-12-08 | 2016-06-29 | 2016-10-27 | 2016-10-27 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2021-04-30 | COMP | 2021-05-25 | COMP | Other | 142 | 85 | 681 | 1 | 452 | 18 | 1374
725 | 2015-12-08 | 2016-10-25 | 2017-07-29 | 2017-07-29 | COMP | 2017-09-11 | COMP | 2017-09-11 | COMP | 2018-12-11 | COMP | 2019-02-20 | COMP | Rule 15/16 | 224 | 191 | 30 | 1 | 314 | 48 | 804
995 | 2015-12-08 | 2017-02-22 | 2017-07-06 | 2017-07-06 | COMP | 2018-10-17 | COMP | 2020-06-08 | COMP |  | INPR | 2020-12-18 | COMP | Other | 304 | 95 | 324 | 411 |  |  | 1266
996 | 2015-12-08 | 2017-02-22 | 2017-08-25 | 2017-08-25 | COMP | 2021-01-04 | COMP | 2021-01-04 | INPR |  | INPR | 2021-09-25 | COMP | Other | 304 | 131 | 842 |  |  |  | 1459
997 | 2015-12-08 | 2017-02-22 | 2017-09-08 | 2017-09-08 | COMP | 2018-10-17 | COMP | 2022-03-31 | COMP | 2022-03-29 | COMP | 2022-05-04 | COMP | Other | 304 | 140 | 279 | 868 | 0 | 25 | 1612
4182 | 2015-12-08 | 2019-06-05 | 2019-10-02 | 2019-10-02 | COMP | 2021-05-13 | COMP | 2021-06-24 | COMP | 2021-06-22 | COMP | 2021-07-13 | COMP | Other | 878 | 84 | 406 | 30 | 0 | 13 | 1407
364 | 2015-12-09 | 2016-01-27 | 2016-02-02 | 2016-02-02 | COMP | 2016-04-13 | COMP | 2016-09-22 | COMP | 2019-04-24 | COMP | 2019-06-21 | COMP | Rule 16 | 33 | 5 | 51 | 114 | 649 | 42 | 889
374 | 2015-12-09 | 2016-02-18 | 2019-08-12 | 2016-11-17 | COMP | 2018-03-28 | COMP | 2018-04-06 | COMP | 2019-06-12 | COMP | 2019-08-03 | COMP | Rule 15/16 | 48 | 877 | 340 | 8 | 298 | 37 | 918
375 | 2015-12-09 | 2016-02-18 | 2016-09-22 | 2016-09-22 | COMP | 2018-03-28 | COMP | 2018-04-06 | COMP | 2019-06-12 | COMP | 2019-08-04 | COMP | Rule 15/16 | 48 | 153 | 379 | 8 | 298 | 37 | 918
376 | 2015-12-09 | 2016-02-18 | 2016-07-27 | 2016-07-27 | COMP | 2018-03-28 | COMP | 2018-03-30 | COMP | 2019-06-12 | COMP | 2019-08-04 | COMP | Rule 15/16 | 48 | 113 | 419 | 3 | 303 | 37 | 918
720 | 2015-12-09 | 2016-10-25 | 2017-02-15 | 2017-02-15 | COMP | 2017-08-17 | COMP | 2017-08-17 | COMP |  |  | 2019-04-03 | COMP | Rule 16 | 223 | 77 | 129 | 1 |  |  | 833
394 | 2015-12-10 | 2016-03-17 | 2016-09-17 | 2018-07-19 | COMP | 2018-11-06 | COMP | 2019-03-27 | COMP | 2019-06-04 | COMP | 2019-05-24 | COMP | Rule 15/16 | 67 | 129 | 78 | 95 | 49 |  | 869
361 | 2015-12-14 | 2016-01-26 | 2016-04-20 | 2016-05-30 | COMP | 2017-10-13 | COMP | 2019-08-22 | COMP | 2019-10-01 | COMP | 2020-02-26 | COMP | Rule 15/16 | 29 | 61 | 348 | 466 | 28 | 100 | 1055
337 | 2015-12-15 | 2016-01-06 | 2016-04-04 | 2017-10-03 | COMP | 2019-05-21 | COMP | 2018-07-16 | COMP | 2019-07-19 | COMP | 2019-07-31 | COMP | Rule 16 | 15 | 62 | 409 |  | 255 | 9 | 912
3171 | 2015-12-15 | 2018-03-16 | 2018-05-03 | 2018-05-03 | COMP | 2018-05-30 | COMP | 2018-06-04 | COMP | 2019-03-26 | COMP | 2019-05-02 | COMP | Rule 16 | 566 | 35 | 19 | 4 | 203 | 28 | 850
388 | 2015-12-16 | 2016-03-14 | 2017-09-05 | 2020-01-23 | COMP | 2020-02-05 | COMP | 2020-07-21 | COMP | 2020-07-20 | COMP | 2020-08-24 | COMP | Rule 15/16 | 60 | 375 | 10 | 118 | 0 | 25 | 1180
389 | 2015-12-16 | 2016-03-14 | 2017-08-31 | 2019-12-20 | COMP | 2020-02-05 | COMP | 2020-08-26 | COMP | 2020-08-25 | COMP | 2020-10-14 | COMP | Rule 16 | 60 | 373 | 31 | 144 | 0 | 35 | 1216
402 | 2015-12-16 | 2016-03-24 | 2017-08-05 | 2017-10-02 | COMP | 2020-06-08 | COMP | 2021-06-15 | COMP | 2021-06-25 | COMP | 2021-07-22 | COMP | Rule 15/16 | 68 | 346 | 673 | 258 | 9 | 19 | 1408
2057 | 2015-12-16 | 2017-09-15 | 2018-05-25 | 2018-05-25 | COMP | 2018-07-13 | COMP | 2018-08-07 | COMP | 2020-04-25 | INPR | 2019-07-25 | COMP | Rule 16 | 442 | 174 | 34 | 18 |  |  | 907
8703 | 2015-12-17 | 2018-12-19 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-23 | COMP | 2019-06-02 | COMP | 2019-04-27 | COMP | 2019-07-16 | COMP | Rule 16 | 756 | 76 | 11 | 28 | 0 | 31 | 899
679 | 2015-12-18 | 2016-10-07 | 2017-01-27 | 2018-01-05 | COMP | 2019-10-31 | COMP | 2019-05-02 | COMP | 2019-12-11 | COMP | 2020-01-30 | COMP | Rule 16 | 204 | 76 | 460 |  | 154 | 34 | 1033
648 | 2015-12-19 | 2016-09-21 | 2017-01-30 | 2017-01-30 | COMP | 2017-09-21 | COMP | 2018-03-06 | COMP | 2019-06-27 | COMP | 2019-07-25 | COMP | Rule 15/16 | 191 | 89 | 165 | 112 | 332 | 20 | 904
390 | 2015-12-23 | 2016-03-14 | 2016-06-20 | 2016-06-20 | COMP | 2016-07-27 | COMP | 2018-12-03 | COMP | 2019-01-02 | COMP | 2019-01-28 | COMP | Rule 16 | 55 | 70 | 27 | 591 | 21 | 18 | 777
692 | 2015-12-23 | 2016-10-13 | 2017-04-10 | 2017-04-10 | COMP | 2017-05-09 | COMP | 2017-05-23 | COMP | 2017-07-05 | COMP | 2020-07-23 | COMP | Rule 16 | 205 | 122 | 22 | 11 | 30 | 768 | 1153
445 | 2015-12-24 | 2016-05-03 | 2016-05-17 | 2016-05-17 | COMP | 2016-08-05 | COMP | 2016-08-05 | COMP | 2018-12-13 | COMP | 2019-01-24 | COMP | Rule 16 | 90 | 11 | 57 | 1 | 592 | 28 | 774
417 | 2015-12-28 | 2016-04-13 | 2016-12-17 | 2016-12-17 | COMP | 2018-05-21 | COMP | 2018-06-04 | COMP | 2019-02-20 | COMP | 2019-03-22 | COMP | Rule 16 | 75 | 172 | 358 | 10 | 179 | 23 | 813
333 | 2015-12-30 | 2016-01-02 | 2016-02-05 | 2016-02-05 | COMP | 2016-03-28 | COMP | 2016-04-18 | COMP | 2020-01-09 | COMP | 2020-01-10 | COMP | Rule 16 | 2 | 24 | 36 | 16 | 937 | 2 | 1013
665 | 2015-12-31 | 2016-09-28 | 2018-05-31 | 2018-10-18 | COMP | 2018-11-26 | COMP | 2018-11-28 | COMP | 2017-05-23 | COMP | 2019-04-17 | COMP | Rule 15/16 | 189 | 420 | 25 | 3 | 0 | 97 | 828
368 | 2016-01-04 | 2016-02-08 | 2017-11-03 | 2018-03-14 | COMP | 2018-10-29 | COMP | 2018-10-29 | COMP | 2019-01-17 | COMP | 2019-01-31 | COMP | Rule 15/16 | 25 | 442 | 161 | 1 | 54 | 10 | 774
371 | 2016-01-04 | 2016-02-17 | 2016-06-09 | 2017-12-21 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-09-30 | COMP | 2019-12-23 | COMP | Rule 15/16 | 31 | 81 | 270 | 1 | 177 | 58 | 999
372 | 2016-01-04 | 2016-02-17 | 2016-06-09 | 2018-01-03 | COMP | 2019-01-18 | COMP | 2019-01-23 | COMP | 2019-09-30 | COMP | 2019-12-18 | COMP | Rule 16 | 31 | 81 | 263 | 3 | 175 | 55 | 996
398 | 2016-01-04 | 2016-03-22 | 2016-10-01 | 2016-10-01 | COMP | 2020-02-10 | COMP | 2017-05-20 | COMP | 2019-07-08 | COMP | 2019-08-13 | COMP | Rule 15/16 | 55 | 136 | 841 |  | 534 | 27 | 909
449 | 2016-01-04 | 2016-05-06 | 2017-06-09 | 2017-11-11 | COMP | 2018-01-02 | COMP | 2018-11-20 | COMP | 2018-10-23 | COMP | 2019-01-28 | COMP | Rule 15/16 | 88 | 276 | 33 | 225 | 0 | 45 | 771
379 | 2016-01-05 | 2016-02-23 | 2016-02-28 | 2016-02-28 | COMP | 2016-04-25 | COMP | 2016-04-25 | INPR | 2018-12-19 | COMP | 2019-01-11 | COMP | Rule 16 | 34 | 4 | 41 |  |  |  | 760
415 | 2016-01-05 | 2016-04-11 | 2017-09-15 | 2018-08-02 | COMP | 2019-01-02 | COMP | 2019-01-08 | COMP | 2021-01-25 | COMP | 2021-03-24 | COMP | Rule 15/16 | 68 | 363 | 104 | 5 | 515 | 42 | 1312
464 | 2016-01-05 | 2016-05-19 | 2016-08-22 | 2016-08-22 | COMP | 2017-04-07 | COMP | 2017-04-27 | COMP | 2019-05-23 | COMP | 2019-11-15 | COMP | Rule 15/16 | 96 | 66 | 158 | 15 | 521 | 123 | 974
397 | 2016-01-06 | 2016-03-21 | 2016-11-03 | 2016-11-03 | COMP | 2018-08-06 | COMP | 2018-08-06 | COMP | 2020-05-21 | COMP | 2020-06-24 | COMP | Rule 16 | 52 | 161 | 440 | 1 | 451 | 24 | 1124
448 | 2016-01-06 | 2016-05-06 | 2018-03-21 | 2018-03-21 | COMP | 2018-06-07 | COMP | 2018-07-10 | COMP | 2019-08-16 | COMP | 2019-09-20 | COMP | Rule 15/16 | 86 | 470 | 56 | 23 | 279 | 25 | 934
796 | 2016-01-06 | 2016-12-02 | 2017-08-18 | 2017-08-18 | COMP | 2017-10-23 | COMP | 2017-10-23 | COMP | 2019-03-12 | COMP | 2019-04-24 | COMP | Rule 16 | 230 | 181 | 46 | 1 | 345 | 32 | 830
426 | 2016-01-07 | 2016-04-20 | 2016-05-11 | 2016-05-11 | COMP | 2016-08-15 | COMP | 2016-08-15 | COMP | 2016-09-27 | COMP | 2020-06-13 | COMP | Rule 16 | 73 | 16 | 67 | 1 | 31 | 932 | 1115
721 | 2016-01-07 | 2016-10-25 | 2016-12-20 | 2018-10-22 | COMP | 2020-09-08 | COMP | 2020-09-30 | COMP |  |  | 2020-10-17 | COMP | Rule 15/16 | 204 | 38 | 473 | 17 |  |  | 1204
4101 | 2016-01-07 | 2019-02-05 | 2019-04-17 | 2019-04-17 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-04-25 | COMP | 2019-06-28 | COMP | Rule 16 | 774 | 51 | 4 | 1 | 4 | 46 | 875
413 | 2016-01-08 | 2016-04-11 | 2017-04-24 | 2018-10-15 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2018-10-22 | COMP | 2020-12-15 | COMP | Rule 15/16 | 65 | 262 | 116 | 1 | 0 | 430 | 1242
1813 | 2016-01-10 | 2017-08-02 | 2018-02-06 | 2018-02-06 | COMP | 2020-05-27 | COMP | 2020-08-07 | COMP | 2020-06-11 | COMP | 2020-11-02 | COMP | Rule 15/16 | 395 | 128 | 580 | 53 | 0 | 61 | 1213
1345 | 2016-01-11 | 2017-05-15 | 2018-04-10 | 2018-12-14 | COMP | 2020-10-08 | COMP | 2020-10-23 | COMP | 2021-01-27 | COMP | 2021-03-10 | COMP | Rule 15/16 | 340 | 227 | 459 | 12 | 63 | 30 | 1298
369 | 2016-01-13 | 2016-02-16 | 2016-11-01 | 2016-11-01 | COMP | 2018-11-28 | COMP | 2018-11-30 | COMP | 2018-11-26 | COMP | 2019-02-09 | COMP | Rule 15/16 | 23 | 183 | 520 | 3 | 0 | 48 | 773
382 | 2016-01-13 | 2016-03-01 | 2017-06-04 | 2017-06-04 | COMP | 2017-11-21 | COMP | 2017-11-29 | COMP | 2020-02-21 | COMP | 2020-06-11 | COMP | Rule 16 | 33 | 319 | 119 | 5 | 559 | 79 | 1110
437 | 2016-01-13 | 2016-04-27 | 2017-05-26 | 2018-07-11 | COMP | 2018-07-18 | COMP | 2018-09-05 | COMP | 2017-08-25 | COMP | 2022-02-04 | COMP | Rule 15/16 | 74 | 274 | 6 | 35 | 0 | 860 | 1526
460 | 2016-01-13 | 2016-05-17 | 2017-01-31 | 2017-01-31 | COMP | 2017-05-30 | COMP | 2019-03-19 | COMP | 2019-01-22 | COMP | 2019-04-22 | COMP | Rule 15/16 | 88 | 178 | 84 | 452 | 0 | 25 | 823
1323 | 2016-01-13 | 2017-05-10 | 2017-05-30 | 2017-05-30 | COMP | 2018-06-06 | COMP | 2018-06-06 | COMP | 2019-02-06 | COMP | 2019-03-08 | COMP | Rule 16 | 335 | 14 | 257 | 1 | 168 | 22 | 792
3019 | 2016-01-13 | 2018-02-28 | 2018-06-11 | 2018-06-11 | COMP | 2019-07-30 | COMP | 2019-08-07 | COMP | 2019-09-19 | COMP | 2019-10-02 | COMP | Rule 15/16 | 535 | 73 | 286 | 7 | 31 | 10 | 937
1177 | 2016-01-14 | 2017-04-14 | 2018-02-15 | 2019-12-18 | COMP | 2020-03-11 | COMP | 2021-02-17 | COMP | 2021-02-23 | COMP | 2021-05-15 | COMP | Rule 15/16 | 316 | 211 | 57 | 237 | 5 | 59 | 1342
404 | 2016-01-15 | 2016-03-25 | 2017-08-05 | 2017-08-05 | COMP | 2018-01-23 | COMP | 2019-07-29 | COMP | 2019-06-11 | COMP | 2019-09-13 | COMP | Rule 15/16 | 49 | 345 | 115 | 382 | 0 | 34 | 922
363 | 2016-01-19 | 2016-01-28 | 2017-01-19 | 2018-08-28 | COMP | 2018-08-17 | COMP | 2018-12-06 | COMP | 2020-03-11 | COMP | 2020-05-14 | COMP | Rule 15/16 | 8 | 247 |  | 76 | 316 | 47 | 1088
433 | 2016-01-19 | 2016-04-25 | 2016-09-07 | 2017-11-08 | COMP | 2019-03-04 | COMP | 2018-06-19 | COMP | 2019-08-21 | COMP | 2019-12-13 | COMP | Rule 15/16 | 69 | 95 | 327 |  | 296 | 79 | 983
2514 | 2016-01-19 | 2017-12-12 | 2018-08-27 | 2018-08-27 | COMP | 2018-11-28 | COMP | 2019-07-29 | COMP | 2019-11-23 | INPR | 2019-08-13 | COMP | Rule 15/16 | 480 | 179 | 64 | 168 |  |  | 899
2958 | 2016-01-19 | 2018-02-22 | 2018-06-07 | 2018-06-07 | COMP | 2018-08-24 | COMP | 2019-02-22 | COMP | 2019-11-23 | INPR | 2019-07-15 | COMP | Rule 16 | 528 | 75 | 56 | 123 |  |  | 878
378 | 2016-01-20 | 2016-02-22 | 2016-06-23 | 2016-06-23 | COMP | 2019-03-11 | COMP | 2019-02-26 | NOTN | 2019-02-26 | COMP | 2019-03-12 | COMP | Rule 16 | 23 | 88 | 680 |  |  |  | 790
386 | 2016-01-20 | 2016-03-09 | 2016-06-22 | 2016-06-22 | COMP | 2019-09-24 | COMP | 2022-03-21 | COMP | 2022-01-11 | COMP | 2022-04-13 | COMP | Rule 15 | 35 | 75 | 819 | 626 | 0 | 18 | 1569
457 | 2016-01-20 | 2016-05-16 | 2016-09-26 | 2016-09-26 | COMP | 2016-11-07 | COMP | 2022-12-12 | COMP | 2022-11-09 | COMP | 2023-06-02 | COMP | Rule 16 | 83 | 93 | 31 | 1531 | 0 | 120 | 1854
711 | 2016-01-20 | 2016-10-21 | 2017-03-29 | 2017-03-29 | COMP | 2021-02-27 | REQD | 2018-02-06 | COMP | 2021-02-27 | INPR | 2019-03-29 | COMP | Rule 16 | 194 | 108 |  | 216 |  |  | 803
492 | 2016-01-25 | 2016-06-05 | 2016-07-18 | 2018-03-01 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-01-28 | COMP | 2019-10-23 | COMP | Rule 16 | 93 | 30 | 117 | 1 | 113 | 189 | 945
444 | 2016-01-26 | 2016-05-02 | 2016-07-19 | 2019-06-26 | COMP | 2019-10-21 | COMP | 2020-01-27 | COMP | 2020-05-11 | COMP | 2020-06-06 | COMP | Rule 16 | 69 | 55 | 82 | 65 | 75 | 19 | 1098
582 | 2016-01-26 | 2016-08-15 | 2016-10-02 | 2016-10-02 | COMP | 2017-01-17 | COMP | 2017-07-13 | COMP | 2017-07-14 | COMP | 2020-11-23 | COMP | Rule 16 | 142 | 34 | 72 | 125 | 2 | 846 | 1217
39143 | 2016-01-26 | 2022-10-03 | 2022-12-31 | 2022-12-31 | COMP | 2023-03-17 | NOTN | 2023-04-04 | COMP | 2023-04-13 | COMP | 2023-07-10 | COMP | Other | 1684 | 61 |  | 64 | 8 | 60 | 1874
853 | 2016-01-27 | 2016-12-23 | 2017-04-17 | 2017-04-17 | COMP | 2019-02-28 | COMP | 2019-03-04 | COMP | 2019-09-21 | INPR | 2019-06-14 | COMP | Rule 15/16 | 231 | 79 | 469 | 3 |  |  | 852
2161 | 2016-01-27 | 2017-10-02 | 2018-03-05 | 2018-04-19 | COMP | 2018-09-10 | COMP | 2019-02-13 | COMP | 2019-07-21 | INPR | 2019-04-11 | COMP | Rule 15/16 | 426 | 104 | 100 | 107 |  |  | 807
3045 | 2016-01-27 | 2018-03-02 | 2018-11-08 | 2018-11-08 | COMP | 2018-11-19 | COMP | 2020-05-12 | COMP | 2020-07-14 | COMP | 2020-11-05 | COMP | Rule 15/16 | 528 | 177 | 7 | 371 | 45 | 82 | 1205
3046 | 2016-01-27 | 2018-03-02 | 2018-09-18 | 2018-09-18 | COMP | 2018-11-02 | COMP | 2019-11-20 | COMP | 2020-06-15 | COMP | 2020-08-26 | COMP | Rule 15/16 | 528 | 140 | 34 | 263 | 142 | 53 | 1155
4295 | 2016-01-27 | 2020-04-28 | 2020-06-08 | 2020-06-08 | COMP | 2020-10-15 | COMP | 2020-10-23 | COMP | 2020-10-19 | COMP | 2020-11-24 | COMP | Rule 16 | 1070 | 29 | 93 | 7 | 0 | 22 | 1217
39154 | 2016-01-29 | 2022-10-04 | 2023-03-10 | 2023-03-10 | COMP | 2023-03-10 | NOTN | 2023-05-22 | COMP | 2023-05-25 | COMP | 2023-09-24 | COMP | Other | 1682 | 107 |  | 52 | 4 | 83 | 1924
506 | 2016-02-02 | 2016-06-21 | 2016-09-27 | 2016-09-27 | COMP | 2016-11-07 | COMP | 2016-11-07 | COMP | 2017-01-13 | COMP | 2019-04-22 | COMP | Rule 16 | 99 | 69 | 30 | 1 | 46 | 570 | 810
4100 | 2016-02-02 | 2019-02-05 | 2020-05-20 | 2020-05-20 | COMP | 2020-03-19 | COMP | 2020-11-10 | COMP | 2021-03-15 | COMP | 2021-05-11 | COMP | Rule 16 | 757 | 326 |  | 167 | 83 | 42 | 1327
380 | 2016-02-03 | 2016-02-23 | 2016-12-22 | 2016-12-22 | COMP | 2018-08-16 | COMP | 2018-08-16 | COMP | 2019-06-26 | COMP | 2020-01-31 | COMP | Rule 16 | 14 | 212 | 416 | 1 | 216 | 150 | 1004
929 | 2016-02-03 | 2017-02-03 | 2017-08-22 | 2017-08-22 | COMP | 2019-05-09 | COMP | 2020-07-28 | COMP | 2020-08-19 | COMP | 2020-09-24 | COMP | Rule 15/16 | 254 | 140 | 430 | 308 | 17 | 26 | 1170
1613 | 2016-02-04 | 2017-07-03 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-08 | COMP | 2019-01-23 | COMP | 2018-12-11 | COMP | 2019-04-08 | COMP | Rule 15/16 | 357 | 333 | 9 | 49 | 0 | 53 | 798
1652 | 2016-02-04 | 2017-07-13 | 2017-11-22 | 2017-11-22 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-18 | COMP | 2019-03-20 | COMP | Rule 16 | 364 | 93 | 319 | 1 | 10 | 3 | 785
3729 | 2016-02-04 | 2018-06-19 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-13 | COMP | 2018-12-12 | COMP | 2018-11-28 | COMP | 2019-01-23 | COMP | Rule 16 | 598 | 92 | 11 | 20 | 0 | 28 | 746
533 | 2016-02-05 | 2016-07-06 | 2018-05-01 | 2018-05-01 | COMP | 2018-09-17 | COMP | 2018-09-27 | COMP | 2019-09-12 | COMP | 2019-11-15 | COMP | Rule 16 | 106 | 458 | 97 | 9 | 241 | 46 | 952
663 | 2016-02-05 | 2016-09-28 | 2018-09-11 | 2018-09-11 | COMP | 2019-01-10 | COMP | 2019-01-15 | COMP | 2019-01-21 | COMP | 2019-05-01 | COMP | Rule 16 | 165 | 491 | 83 | 4 | 4 | 71 | 814
1029 | 2016-02-05 | 2017-03-03 | 2017-06-05 | 2017-06-05 | COMP | 2017-06-28 | COMP | 2017-11-10 | COMP | 2017-11-20 | COMP | 2020-12-23 | COMP | Rule 16 | 271 | 66 | 18 | 95 | 6 | 777 | 1229
39155 | 2016-02-05 | 2022-10-04 | 2023-02-19 | 2023-09-27 | COMP | 2023-02-19 | NOTN | 2023-06-27 | COMP | 2023-06-26 | COMP | 2023-08-18 | COMP | Other | 1677 | 93 |  |  | 0 | 38 | 1895
400 | 2016-02-08 | 2016-03-23 | 2016-04-08 | 2019-06-28 | COMP | 2019-07-19 | COMP | 2019-11-12 | COMP | 2019-12-23 | COMP | 2020-02-06 | COMP | Rule 16 | 32 | 13 | 15 | 81 | 28 | 31 | 1005
452 | 2016-02-10 | 2016-05-08 | 2017-03-29 | 2017-03-29 | COMP | 2018-05-16 | COMP | 2019-09-04 | COMP | 2020-09-14 | COMP | 2021-01-20 | COMP | Rule 15/16 | 62 | 224 | 286 | 328 | 260 | 87 | 1243
416 | 2016-02-11 | 2016-04-13 | 2017-04-24 | 2017-04-24 | COMP | 2017-09-11 | COMP | 2019-03-13 | COMP | 2019-03-19 | COMP | 2019-05-31 | COMP | Rule 15/16 | 44 | 260 | 98 | 376 | 5 | 53 | 831
903 | 2016-02-11 | 2017-01-26 | 2017-06-12 | 2017-06-12 | COMP | 2017-07-20 | COMP | 2017-07-24 | COMP | 2018-11-05 | COMP | 2019-02-01 | COMP | Rule 16 | 242 | 96 | 28 | 3 | 325 | 59 | 748
544 | 2016-02-12 | 2016-07-18 | 2017-05-04 | 2017-05-04 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2019-03-27 | COMP | 2019-04-19 | COMP | Rule 16 | 109 | 202 | 342 | 1 | 134 | 18 | 801
726 | 2016-02-12 | 2016-10-25 | 2017-11-13 | 2017-11-13 | COMP | 2019-03-08 | COMP | 2019-07-17 | COMP | 2020-01-18 | INPR | 2019-10-01 | COMP | Rule 16 | 179 | 265 | 329 | 92 |  |  | 915
3336 | 2016-02-17 | 2018-04-10 | 2018-05-07 | 2018-05-07 | COMP | 2018-09-10 | COMP | 2018-09-21 | COMP | 2019-07-21 | INPR | 2019-04-02 | COMP | Rule 15/16 | 541 | 20 | 88 | 10 |  |  | 786
405 | 2016-02-18 | 2016-03-28 | 2017-03-27 | 2017-03-27 | COMP | 2017-09-11 | COMP | 2018-02-23 | COMP | 2018-05-10 | COMP | 2019-07-10 | COMP | Rule 15/16 | 28 | 252 | 118 | 113 | 55 | 293 | 854
976 | 2016-02-19 | 2017-02-18 | 2017-08-07 | 2018-02-02 | COMP | 2018-02-13 | COMP | 2018-08-06 | COMP | 2019-04-15 | COMP | 2019-04-30 | COMP | Rule 15/16 | 253 | 118 | 8 | 122 | 173 | 12 | 804
485 | 2016-02-22 | 2016-06-01 | 2016-08-24 | 2016-08-24 | COMP | 2022-04-16 | REQD | 2016-09-15 | COMP | 2017-07-13 | COMP | 2019-08-01 | COMP | Rule 16 | 72 | 60 |  | 16 | 208 | 516 | 868
556 | 2016-02-22 | 2016-07-24 | 2019-04-11 | 2019-11-12 | COMP | 2019-11-26 | COMP | 2019-12-09 | COMP | 2020-03-02 | COMP | 2020-07-30 | COMP | Rule 16 | 108 | 682 | 11 | 8 | 57 | 108 | 1119
13591 | 2016-02-22 | 2019-07-31 | 2019-09-25 | 2019-09-25 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-06-17 | COMP | 2020-07-11 | COMP | Rule 16 | 867 | 40 | 77 | 1 | 107 | 18 | 1105
407 | 2016-02-23 | 2016-03-30 | 2016-07-06 | 2018-01-04 | COMP | 2018-12-06 | COMP | 2019-05-08 | COMP | 2019-07-16 | COMP | 2019-09-11 | COMP | Rule 15/16 | 27 | 69 | 233 | 106 | 48 | 41 | 895
432 | 2016-02-24 | 2016-04-25 | 2016-09-27 | 2016-09-27 | COMP | 2016-12-30 | COMP | 2017-01-04 | COMP | 2019-03-11 | COMP | 2019-05-29 | COMP | Rule 16 | 44 | 109 | 65 | 4 | 547 | 57 | 821
536 | 2016-02-24 | 2016-07-11 | 2018-04-12 | 2018-04-12 | COMP | 2020-01-07 | COMP | 2020-04-29 | COMP | 2020-05-26 | COMP | 2020-06-25 | COMP | Rule 16 | 97 | 442 | 436 | 80 | 19 | 23 | 1092
436 | 2016-02-25 | 2016-04-27 | 2016-11-29 | 2016-11-29 | COMP | 2017-02-13 | COMP | 2017-05-13 | COMP | 2019-09-06 | COMP | 2019-10-03 | COMP | Rule 15/16 | 45 | 149 | 53 | 64 | 582 | 20 | 909
962 | 2016-02-25 | 2017-02-17 | 2017-12-16 | 2017-12-16 | COMP | 2019-03-07 | COMP | 2019-03-13 | COMP | 2018-09-07 | COMP | 2019-04-18 | COMP | Rule 15/16 | 249 | 209 | 305 | 5 | 0 | 27 | 792
511 | 2016-02-26 | 2016-06-23 | 2017-03-17 | 2018-10-08 | COMP | 2018-10-19 | COMP | 2019-01-11 | COMP | 2018-12-05 | COMP | 2020-05-08 | COMP | Rule 15/16 | 84 | 184 | 10 | 56 | 0 | 334 | 1057
581 | 2016-02-26 | 2016-08-15 | 2017-06-03 | 2018-12-31 | COMP | 2019-05-15 | COMP | 2019-10-08 | COMP | 2020-05-26 | COMP | 2021-02-11 | COMP | Rule 15/16 | 120 | 202 | 95 | 102 | 158 | 181 | 1248
601 | 2016-02-26 | 2016-08-29 | 2017-11-21 | 2017-11-21 | COMP | 2018-11-08 | COMP | 2021-02-27 | REQD | 2018-11-27 | COMP | 2019-09-04 | COMP | Rule 15/16 | 130 | 311 | 244 |  |  |  | 887
1204 | 2016-02-26 | 2017-04-19 | 2017-06-23 | 2017-06-23 | COMP | 2017-07-06 | COMP | 2017-07-06 | COMP | 2019-04-20 | INPR | 2019-01-30 | COMP | Rule 16 | 290 | 47 | 9 | 1 |  |  | 736
1833 | 2016-02-26 | 2017-08-07 | 2017-12-15 | 2017-12-15 | COMP | 2019-02-01 | COMP | 2019-02-22 | COMP | 2020-01-22 | COMP | 2020-02-28 | COMP | Rule 16 | 366 | 91 | 283 | 15 | 230 | 27 | 1007
435 | 2016-02-29 | 2016-04-26 | 2016-09-12 | 2016-09-12 | COMP | 2019-07-26 | COMP | 2021-03-09 | COMP | 2021-03-08 | COMP | 2021-05-06 | COMP | Rule 16 | 42 | 97 | 722 | 406 | 0 | 43 | 1306
3924 | 2016-02-29 | 2018-10-09 | 2020-05-05 | 2020-05-05 | COMP | 2020-09-23 | COMP | 2020-10-06 | COMP | 2020-09-25 | COMP | 2020-11-10 | COMP | Rule 15/16 | 660 | 394 | 100 | 10 | 0 | 26 | 1186
401 | 2016-03-01 | 2016-03-24 | 2019-06-19 | 2019-06-19 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-07-03 | COMP | 2020-02-25 | COMP | Rule 16 | 18 | 815 | 59 | 1 | 0 | 113 | 1002
496 | 2016-03-01 | 2016-06-10 | 2016-08-24 | 2016-08-24 | COMP | 2017-04-06 | COMP | 2017-04-06 | COMP | 2019-02-22 | COMP | 2019-04-06 | COMP | Rule 15/16 | 73 | 53 | 155 | 1 | 472 | 31 | 780
4098 | 2016-03-01 | 2019-01-31 | 2019-01-31 | 2019-01-31 | COMP | 2019-01-31 | NOTN | 2019-03-12 | COMP | 2019-03-18 | NOTN | 2019-03-23 | COMP | Other | 735 | 1 |  | 28 |  |  | 770
5730 | 2016-03-01 | 2018-06-27 | 2018-10-05 | 2019-02-26 | COMP | 2019-04-04 | COMP | 2019-04-05 | COMP | 2019-04-09 | COMP | 2019-05-10 | COMP | Rule 15/16 | 587 | 71 | 28 | 2 | 3 | 24 | 805
498 | 2016-03-02 | 2016-06-12 | 2017-03-30 | 2016-11-18 | COMP | 2017-05-24 | COMP | 2018-06-13 | COMP | 2021-06-17 | COMP | 2019-04-05 | COMP | Rule 15/16 | 72 | 201 | 129 | 265 | 758 |  | 779
500 | 2016-03-02 | 2016-06-14 | 2016-09-15 | 2016-09-15 | COMP | 2018-02-26 | COMP | 2018-03-06 | COMP | 2020-02-29 | INPR | 2019-11-13 | COMP | Rule 15/16 | 74 | 66 | 362 | 7 |  |  | 933
512 | 2016-03-02 | 2016-06-24 | 2016-07-26 | 2016-07-26 | COMP | 2016-09-27 | COMP | 2016-09-29 | COMP | 2022-01-29 | INPR | 2020-06-16 | COMP | Rule 16 | 82 | 22 | 45 | 3 |  |  | 1080
548 | 2016-03-02 | 2016-07-19 | 2016-08-30 | 2016-08-30 | COMP | 2016-09-07 | COMP | 2016-09-08 | COMP |  |  | 2020-05-11 | COMP | Rule 16 | 98 | 31 | 6 | 2 |  |  | 1055
1503 | 2016-03-02 | 2017-06-12 | 2017-11-28 | 2017-11-28 | COMP | 2018-03-06 | COMP | 2018-03-08 | COMP | 2019-05-06 | COMP | 2019-06-12 | COMP | Rule 15/16 | 324 | 117 | 67 | 3 | 293 | 27 | 826
3460 | 2016-03-02 | 2018-05-01 | 2019-01-24 | 2019-01-24 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-06-10 | COMP | 2019-08-14 | COMP | Rule 15/16 | 546 | 184 | 53 | 1 | 44 | 47 | 870
438 | 2016-03-03 | 2016-04-27 | 2016-07-28 | 2016-07-28 | COMP | 2019-01-09 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-05-29 | COMP | Rule 16 | 40 | 65 | 615 | 93 | 1 | 6 | 815
1034 | 2016-03-03 | 2017-03-06 | 2017-09-05 | 2017-09-05 | COMP | 2018-05-09 | COMP | 2018-05-09 | COMP | 2019-06-28 | COMP | 2019-07-31 | COMP | Rule 15/16 | 254 | 129 | 170 | 1 | 287 | 23 | 859
422 | 2016-03-04 | 2016-04-19 | 2016-08-24 | 2018-12-18 | COMP | 2019-08-16 | COMP | 2018-09-21 | COMP | 2019-11-15 | COMP | 2019-12-12 | COMP | Rule 15/16 | 33 | 90 | 168 |  | 290 | 18 | 950
447 | 2016-03-07 | 2016-05-05 | 2018-02-03 | 2018-07-16 | COMP | 2018-10-03 | COMP | 2018-10-04 | COMP | 2019-07-21 | INPR | 2019-03-15 | COMP | Rule 16 | 44 | 439 | 57 | 2 |  |  | 761
1957 | 2016-03-07 | 2017-08-25 | 2018-06-25 | 2018-06-25 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP |  | INPR | 2021-12-20 | COMP | Rule 16 | 374 | 208 | 152 | 1 |  |  | 1457
4190 | 2016-03-07 | 2019-06-19 | 2019-07-17 | 2019-07-17 | COMP | 2019-09-18 | COMP | 2019-10-10 | COMP | 2020-01-13 | COMP | 2022-12-14 | COMP | Rule 15/16 | 828 | 20 | 45 | 17 | 63 | 737 | 1705
4765 | 2016-03-07 | 2018-03-30 | 2018-05-21 | 2018-05-21 | COMP | 2018-06-08 | COMP | 2019-03-07 | COMP | 2019-03-19 | COMP | 2019-03-21 | COMP | Rule 16 | 521 | 37 | 14 | 186 | 9 | 3 | 765
459 | 2016-03-08 | 2016-05-17 | 2017-03-27 | 2017-03-27 | COMP | 2018-05-30 | COMP | 2018-08-23 | COMP | 2019-03-25 | COMP | 2019-04-17 | COMP | Rule 15/16 | 51 | 216 | 297 | 61 | 145 | 18 | 783
478 | 2016-03-08 | 2016-05-25 | 2018-03-15 | 2018-03-15 | COMP | 2019-10-29 | COMP | 2020-01-13 | COMP | 2020-09-10 | COMP | 2020-12-05 | COMP | Rule 16 | 57 | 453 | 411 | 50 | 170 | 59 | 1195
1328 | 2016-03-08 | 2017-05-11 | 2017-06-29 | 2019-03-02 | COMP | 2019-07-31 | COMP | 2019-08-01 | COMP | 2019-10-30 | COMP | 2019-11-19 | COMP | Rule 16 | 299 | 35 | 106 | 2 | 64 | 14 | 933
1576 | 2016-03-08 | 2017-06-26 | 2017-08-23 | 2017-08-23 | COMP | 2017-10-17 | COMP | 2017-10-17 | COMP | 2020-06-19 | COMP | 2020-08-06 | COMP | Rule 16 | 330 | 42 | 39 | 1 | 671 | 35 | 1113
421 | 2016-03-10 | 2016-04-19 | 2016-08-29 | 2016-08-29 | COMP | 2018-12-28 | COMP | 2019-02-07 | COMP | 2019-05-05 | COMP | 2019-06-12 | COMP | Rule 15/16 | 29 | 93 | 586 | 28 | 61 | 27 | 820
458 | 2016-03-10 | 2016-05-16 | 2017-01-21 | 2017-01-21 | COMP | 2018-01-23 | COMP | 2019-10-24 | COMP | 2020-03-04 | COMP | 2020-03-23 | COMP | Rule 16 | 48 | 172 | 252 | 444 | 88 | 14 | 1014
462 | 2016-03-10 | 2016-05-18 | 2016-08-29 | 2016-08-29 | COMP | 2018-03-29 | COMP | 2019-10-24 | COMP | 2019-12-11 | COMP | 2020-01-16 | COMP | Rule 16 | 50 | 72 | 397 | 398 | 32 | 25 | 969
1023 | 2016-03-10 | 2017-03-02 | 2017-08-27 | 2017-08-27 | COMP | 2018-04-11 | COMP | 2019-12-28 | REQD | 2019-01-17 | COMP | 2019-02-20 | COMP | Rule 15/16 | 247 | 125 | 155 |  |  |  | 741
1196 | 2016-03-14 | 2017-04-18 | 2017-09-04 | 2017-09-04 | COMP | 2019-02-06 | COMP | 2019-02-07 | COMP | 2019-03-29 | COMP | 2019-05-23 | COMP | Rule 15/16 | 278 | 97 | 356 | 2 | 36 | 40 | 805
412 | 2016-03-15 | 2016-04-08 | 2016-10-13 | 2019-12-18 | COMP | 2020-10-29 | COMP | 2020-03-17 | COMP | 2020-10-29 | COMP | 2021-03-05 | COMP | Rule 15/16 | 19 | 132 | 221 |  | 161 | 85 | 1251
487 | 2016-03-15 | 2016-06-01 | 2017-08-14 | 2019-02-13 | COMP | 2020-08-17 | COMP | 2020-10-05 | COMP | 2022-11-08 | COMP | 2021-01-21 | COMP | Rule 15/16 | 56 | 304 | 382 | 35 | 528 |  | 1221
4225 | 2016-03-15 | 2019-09-05 | 2019-09-19 | 2019-09-19 | COMP | 2019-11-12 | COMP | 2020-02-14 | COMP | 2020-06-11 | COMP | 2020-07-22 | COMP | Rule 16 | 876 | 11 | 38 | 64 | 83 | 30 | 1097
476 | 2016-03-17 | 2016-05-25 | 2016-06-10 | 2018-11-04 | COMP | 2018-11-16 | COMP | 2019-01-30 | COMP | 2018-12-13 | COMP | 2019-04-04 | COMP | Rule 15/16 | 50 | 12 | 9 | 49 | 0 | 46 | 767
489 | 2016-03-17 | 2016-06-02 | 2017-04-28 | 2017-04-28 | COMP | 2017-06-08 | COMP | 2017-10-17 | COMP | 2019-06-25 | COMP | 2019-08-02 | COMP | Rule 16 | 55 | 229 | 29 | 92 | 423 | 28 | 851
532 | 2016-03-17 | 2016-07-01 | 2016-09-02 | 2016-09-02 | COMP | 2019-08-31 | COMP | 2018-05-07 | COMP | 2018-07-17 | COMP | 2019-05-06 | COMP | Rule 16 | 76 | 45 | 752 |  | 50 | 202 | 789
776 | 2016-03-17 | 2016-11-18 | 2017-04-13 | 2017-04-13 | COMP | 2017-10-23 | COMP | 2018-10-02 | COMP | 2018-09-12 | COMP | 2019-01-31 | COMP | Rule 15/16 | 173 | 100 | 135 | 237 | 0 | 82 | 723
411 | 2016-03-21 | 2016-04-08 | 2016-08-18 | 2016-08-18 | COMP | 2017-07-24 | COMP | 2017-08-28 | COMP | 2019-02-22 | COMP | 2019-04-01 | COMP | Rule 16 | 15 | 93 | 234 | 26 | 372 | 27 | 762
1760 | 2016-03-21 | 2017-07-20 | 2017-10-28 | 2017-10-28 | COMP | 2017-11-07 | COMP | 2017-11-07 | COMP | 2020-01-31 | COMP | 2020-02-18 | COMP | Rule 16 | 338 | 71 | 7 | 1 | 558 | 12 | 983
427 | 2016-03-22 | 2016-04-21 | 2018-01-19 | 2019-03-29 | COMP | 2019-05-03 | COMP | 2019-06-21 | COMP | 2019-09-03 | COMP | 2019-12-01 | COMP | Rule 15/16 | 23 | 439 | 26 | 35 | 51 | 61 | 929
455 | 2016-03-22 | 2016-05-11 | 2017-11-22 | 2018-03-05 | COMP | 2018-03-28 | COMP | 2018-11-13 | COMP | 2018-04-13 | COMP | 2019-01-02 | COMP | Rule 15/16 | 37 | 388 | 18 | 161 | 0 | 33 | 700
522 | 2016-03-22 | 2016-06-28 | 2018-03-20 | 2018-06-29 | COMP | 2019-01-09 | COMP | 2020-07-03 | COMP | 2020-07-07 | COMP | 2020-10-08 | COMP | Rule 15/16 | 70 | 433 | 132 | 375 | 3 | 67 | 1147
5074 | 2016-03-22 | 2018-04-27 | 2018-11-15 | 2018-12-14 | COMP | 2019-01-09 | COMP | 2020-02-10 | COMP | 2020-09-08 | COMP | 2020-09-24 | COMP | Rule 15/16 | 530 | 141 | 17 | 273 | 149 | 13 | 1137
441 | 2016-03-23 | 2016-05-01 | 2016-07-20 | 2016-07-20 | COMP | 2016-09-30 | COMP | 2016-09-30 | COMP | 2018-12-09 | COMP | 2019-04-15 | COMP | Rule 16 | 28 | 56 | 52 | 1 | 549 | 87 | 770
509 | 2016-03-23 | 2016-06-22 | 2017-02-16 | 2017-02-16 | COMP | 2017-04-03 | COMP | 2017-06-01 | COMP | 2019-10-19 | INPR | 2019-07-01 | COMP | Rule 16 | 65 | 165 | 32 | 43 |  |  | 824
727 | 2016-03-23 | 2016-10-25 | 2018-06-20 | 2018-06-22 | COMP | 2020-06-16 | COMP | 2020-10-30 | COMP | 2021-03-02 | COMP | 2021-03-06 | COMP | Rule 16 | 152 | 415 | 498 | 98 | 81 | 4 | 1245
769 | 2016-03-23 | 2016-11-15 | 2017-05-23 | 2017-05-23 | COMP | 2018-06-27 | COMP | 2018-07-10 | COMP | 2018-01-19 | COMP | 2019-12-13 | COMP | Rule 16 | 166 | 131 | 276 | 9 | 0 | 360 | 938
5293 | 2016-03-23 | 2018-05-17 | 2018-09-24 | 2018-09-24 | COMP | 2019-02-05 | COMP | 2019-03-17 | COMP | 2019-03-08 | COMP | 2019-04-10 | COMP | Other | 543 | 90 | 91 | 28 | 0 | 18 | 767
451 | 2016-03-24 | 2016-05-07 | 2016-12-29 | 2016-12-29 | COMP | 2017-03-01 | COMP | 2018-03-01 | COMP | 2021-01-30 | INPR | 2020-01-24 | COMP | Rule 16 | 32 | 162 | 43 | 252 |  |  | 964
470 | 2016-03-24 | 2016-05-24 | 2016-08-29 | 2016-08-29 | COMP | 2018-05-30 | COMP | 2018-06-25 | COMP | 2018-10-25 | COMP | 2019-01-24 | COMP | Rule 15/16 | 44 | 68 | 440 | 19 | 87 | 60 | 713
525 | 2016-03-24 | 2016-06-28 | 2017-01-26 | 2017-06-26 | COMP | 2017-10-25 | COMP | 2018-02-01 | COMP | 2019-05-15 | COMP | 2019-06-28 | COMP | Rule 15/16 | 68 | 146 | 86 | 66 | 324 | 32 | 822
537 | 2016-03-24 | 2016-07-11 | 2017-05-12 | 2017-05-12 | COMP | 2017-05-24 | COMP | 2017-12-27 | COMP | 2018-04-05 | COMP | 2021-03-20 | COMP | Rule 16 | 76 | 213 | 9 | 149 | 69 | 743 | 1254
747 | 2016-03-24 | 2016-11-03 | 2017-01-10 | 2017-01-10 | COMP | 2017-02-13 | COMP | 2018-01-18 | COMP | 2020-08-29 | INPR | 2019-02-07 | COMP | Rule 16 | 158 | 45 | 24 | 234 |  |  | 723
910 | 2016-03-24 | 2017-01-27 | 2017-06-12 | 2017-06-12 | COMP | 2017-12-13 | COMP | 2017-12-14 | COMP | 2020-04-25 | INPR | 2019-07-26 | COMP | Rule 15/16 | 214 | 95 | 128 | 2 |  |  | 841
434 | 2016-03-25 | 2016-04-26 | 2016-06-08 | 2016-06-08 | COMP | 2019-02-19 | COMP | 2019-02-21 | COMP | 2020-02-06 | COMP | 2020-04-15 | COMP | Rule 16 | 23 | 31 | 677 | 3 | 242 | 49 | 1020
3470 | 2016-03-25 | 2018-05-01 | 2018-07-30 | 2018-07-30 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2021-01-02 | INPR | 2019-11-22 | COMP | Rule 15/16 | 529 | 63 | 156 | 1 |  |  | 923
465 | 2016-03-28 | 2016-05-23 | 2016-09-01 | 2018-04-20 | COMP | 2018-06-19 | COMP | 2018-08-06 | COMP | 2019-03-28 | COMP | 2019-05-13 | COMP | Rule 15/16 | 41 | 72 | 42 | 34 | 161 | 33 | 787
488 | 2016-03-28 | 2016-06-01 | 2017-05-25 | 2017-05-25 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-04-09 | COMP | 2019-05-09 | COMP | Rule 16 | 47 | 249 | 468 | 1 | 2 | 23 | 785
1159 | 2016-03-28 | 2017-04-10 | 2017-04-25 | 2017-04-25 | COMP | 2018-05-22 | COMP | 2019-12-30 | COMP | 2020-02-28 | COMP | 2020-03-02 | COMP | Rule 16 | 262 | 12 | 271 | 403 | 42 | 2 | 987
482 | 2016-03-29 | 2016-05-30 | 2016-08-25 | 2016-08-25 | COMP | 2017-10-24 | COMP | 2017-10-26 | COMP | 2019-08-13 | COMP | 2019-10-07 | COMP | Rule 16 | 44 | 62 | 294 | 3 | 450 | 39 | 888
1829 | 2016-03-29 | 2017-08-03 | 2018-03-22 | 2018-03-22 | COMP | 2019-02-06 | COMP | 2019-03-20 | COMP | 2019-05-17 | COMP | 2019-07-23 | COMP | Rule 15/16 | 342 | 158 | 221 | 30 | 43 | 46 | 835
1919 | 2016-03-29 | 2017-08-21 | 2018-04-16 | 2018-04-16 | COMP | 2019-02-04 | COMP | 2019-10-08 | COMP | 2020-02-19 | COMP | 2020-03-05 | COMP | Rule 15/16 | 354 | 163 | 202 | 173 | 90 | 12 | 989
414 | 2016-03-30 | 2016-04-11 | 2016-04-15 | 2016-04-15 | COMP | 2018-02-21 | COMP | 2018-02-21 | COMP | 2018-02-23 | COMP | 2019-05-23 | COMP | Rule 16 | 9 | 5 | 465 | 1 | 3 | 315 | 793
898 | 2016-03-30 | 2017-01-24 | 2018-02-07 | 2018-02-07 | COMP | 2018-03-10 | COMP | 2018-03-30 | COMP | 2020-02-26 | COMP | 2020-10-09 | COMP | Rule 15/16 | 207 | 262 | 22 | 15 | 479 | 161 | 1142
908 | 2016-03-30 | 2017-01-27 | 2017-12-21 | 2017-10-06 | COMP | 2018-03-16 | COMP | 2018-06-19 | COMP | 2019-01-09 | COMP | 2019-01-28 | COMP | Rule 15/16 | 210 | 228 | 109 | 67 | 140 | 13 | 711
1116 | 2016-03-30 | 2017-03-27 | 2017-06-08 | 2017-06-08 | COMP | 2019-01-09 | COMP | 2021-03-17 | COMP | 2021-04-16 | COMP | 2021-05-20 | COMP | Rule 16 | 250 | 53 | 398 | 550 | 23 | 25 | 1294
1643 | 2016-03-30 | 2017-07-08 | 2017-09-28 | 2018-01-12 | COMP | 2018-03-29 | COMP | 2018-06-22 | COMP | 2019-01-22 | COMP | 2019-03-14 | COMP | Rule 15/16 | 322 | 58 | 53 | 61 | 145 | 37 | 743
446 | 2016-03-31 | 2016-05-05 | 2016-12-06 | 2016-12-06 | COMP | 2020-02-03 | COMP | 2020-06-23 | COMP | 2020-07-01 | COMP | 2020-07-14 | COMP | Rule 16 | 26 | 148 | 793 | 100 | 7 | 10 | 1079
479 | 2016-03-31 | 2016-05-25 | 2016-10-17 | 2016-10-17 | COMP | 2017-01-20 | COMP | 2019-11-27 | COMP | 2019-12-17 | COMP | 2020-01-10 | COMP | Rule 15/16 | 40 | 101 | 65 | 719 | 13 | 17 | 950
541 | 2016-03-31 | 2016-07-18 | 2017-09-21 | 2017-09-21 | COMP | 2018-04-24 | COMP | 2018-04-24 | COMP | 2022-06-18 | INPR | 2019-06-13 | COMP | Rule 15/16 | 76 | 299 | 147 | 1 |  |  | 806
611 | 2016-03-31 | 2016-09-05 | 2017-01-24 | 2017-01-24 | COMP | 2018-08-15 | COMP | 2019-01-15 | COMP |  | INPR | 2019-03-07 | COMP | Other | 110 | 96 | 394 | 104 |  |  | 737
612 | 2016-03-31 | 2016-09-05 | 2017-01-06 | 2017-01-06 | COMP | 2018-08-15 | COMP | 2018-09-27 | INPR |  | REQD | 2019-02-06 | COMP | Other | 110 | 85 | 405 |  |  |  | 717
613 | 2016-03-31 | 2016-09-05 | 2017-01-12 | 2017-01-12 | COMP | 2018-08-15 | COMP | 2018-08-28 | COMP | 2019-07-09 | COMP | 2019-08-07 | COMP | Other | 110 | 89 | 401 | 10 | 216 | 22 | 844
614 | 2016-03-31 | 2016-09-05 | 2017-01-06 | 2017-01-06 | COMP | 2018-08-15 | COMP | 2018-12-11 | INPR |  | REQD | 2019-03-12 | COMP | Other | 110 | 85 | 405 |  |  |  | 740
593 | 2016-04-01 | 2016-08-22 | 2016-09-05 | 2016-09-05 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-12-28 | INPR | 2019-09-11 | COMP | Rule 16 | 100 | 10 | 590 | 1 |  |  | 867
624 | 2016-04-01 | 2016-09-12 | 2017-04-29 | 2017-04-29 | COMP | 2017-06-05 | COMP | 2019-05-01 | COMP | 2019-04-08 | COMP | 2019-06-26 | COMP | Rule 16 | 114 | 159 | 25 | 479 | 0 | 40 | 814
807 | 2016-04-01 | 2016-12-03 | 2017-05-19 | 2017-05-19 | COMP | 2017-06-07 | COMP | 2019-03-20 | COMP | 2019-07-21 | INPR | 2019-04-15 | COMP | Rule 16 | 170 | 117 | 13 | 447 |  |  | 763
1819 | 2016-04-01 | 2017-08-05 | 2017-11-08 | 2017-11-08 | COMP | 2017-12-05 | COMP | 2018-03-09 | COMP | 2019-07-21 | INPR | 2019-04-01 | COMP | Rule 16 | 340 | 67 | 17 | 65 |  |  | 753
2525 | 2016-04-01 | 2017-12-14 | 2017-12-16 | 2017-12-16 | COMP | 2019-04-18 | COMP | 2018-03-02 | COMP | 2021-03-27 | INPR | 2020-03-06 | COMP | Rule 16 | 430 | 2 | 335 |  |  |  | 987
431 | 2016-04-04 | 2016-04-25 | 2016-10-10 | 2016-10-10 | COMP | 2018-07-25 | COMP | 2020-12-08 | COMP | 2021-02-17 | COMP | 2021-04-08 | COMP | Rule 15/16 | 16 | 118 | 450 | 597 | 48 | 37 | 1261
480 | 2016-04-04 | 2016-05-26 | 2016-12-09 | 2016-12-09 | COMP | 2018-05-04 | COMP | 2018-06-11 | COMP | 2017-08-18 | COMP | 2019-03-20 | COMP | Rule 15/16 | 39 | 136 | 353 | 26 | 0 | 194 | 744
483 | 2016-04-04 | 2016-06-01 | 2017-09-14 | 2017-09-14 | COMP | 2018-03-05 | COMP | 2018-04-10 | COMP | 2021-07-01 | COMP | 2021-08-06 | COMP | Rule 16 | 42 | 326 | 116 | 27 | 813 | 26 | 1345
566 | 2016-04-04 | 2016-08-02 | 2017-02-02 | 2017-02-02 | COMP | 2017-03-06 | COMP | 2017-03-06 | COMP | 2019-09-21 | INPR | 2019-05-20 | COMP | Rule 16 | 85 | 127 | 22 | 1 |  |  | 787
1183 | 2016-04-04 | 2017-04-14 | 2017-07-21 | 2017-07-21 | COMP | 2018-05-25 | COMP | 2018-05-25 | COMP | 2020-04-06 | COMP | 2020-05-01 | COMP | Rule 15/16 | 261 | 69 | 213 | 1 | 467 | 20 | 1026
425 | 2016-04-05 | 2016-04-20 | 2018-04-03 | 2018-11-29 | COMP | 2019-01-30 | COMP | 2019-03-05 | COMP | 2019-03-04 | COMP | 2019-05-02 | COMP | Rule 16 | 12 | 491 | 42 | 24 | 0 | 43 | 774
1389 | 2016-04-05 | 2017-05-25 | 2018-11-14 | 2018-11-14 | COMP | 2022-03-23 | COMP | 2022-03-23 | COMP | 2022-08-29 | COMP | 2022-10-27 | COMP | Rule 15/16 | 289 | 371 | 843 | 1 | 111 | 43 | 1653
6146 | 2016-04-05 | 2018-07-30 | 2018-11-16 | 2018-11-16 | COMP | 2019-04-10 | COMP | 2019-02-20 | COMP | 2019-06-14 | COMP | 2019-07-26 | COMP | Rule 16 | 584 | 78 | 98 |  | 82 | 30 | 833
477 | 2016-04-06 | 2016-05-25 | 2017-10-11 | 2017-10-11 | COMP | 2018-04-11 | COMP | 2018-04-16 | COMP | 2019-07-21 | INPR | 2019-03-01 | COMP | Rule 16 | 36 | 349 | 124 | 4 |  |  | 729
986 | 2016-04-06 | 2017-02-21 | 2017-05-22 | 2017-05-22 | COMP | 2019-10-16 | COMP | 2019-11-15 | COMP | 2020-05-13 | COMP | 2020-06-09 | COMP | Rule 16 | 221 | 65 | 605 | 22 | 123 | 19 | 1050
4625 | 2016-04-06 | 2018-02-20 | 2018-06-02 | 2018-06-02 | COMP | 2018-09-19 | COMP | 2019-01-18 | COMP | 2019-02-05 | COMP | 2019-03-07 | COMP | Rule 15/16 | 471 | 73 | 76 | 83 | 12 | 22 | 733
529 | 2016-04-07 | 2016-06-29 | 2017-03-28 | 2017-03-28 | COMP | 2017-04-24 | COMP | 2017-05-09 | COMP | 2019-03-18 | COMP | 2019-04-17 | COMP | Rule 16 | 59 | 187 | 20 | 12 | 465 | 23 | 761
1036 | 2016-04-07 | 2017-03-06 | 2017-04-04 | 2017-04-04 | COMP | 2018-08-24 | COMP | 2018-09-04 | COMP | 2019-06-29 | INPR | 2019-02-22 | COMP | Rule 16 | 229 | 22 | 352 | 7 |  |  | 723
8149 | 2016-04-07 | 2018-11-16 | 2019-03-06 | 2019-03-06 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2021-02-25 | COMP | 2021-05-26 | COMP | Rule 15/16 | 659 | 73 | 69 | 1 | 430 | 65 | 1292
540 | 2016-04-08 | 2016-07-15 | 2017-02-06 | 2019-02-06 | COMP | 2019-05-07 | COMP | 2019-05-08 | COMP | 2019-05-31 | COMP | 2019-07-08 | COMP | Rule 16 | 69 | 141 | 64 | 2 | 17 | 26 | 816
561 | 2016-04-08 | 2016-07-28 | 2017-08-24 | 2017-08-24 | COMP | 2017-10-13 | COMP | 2017-10-18 | COMP |  |  | 2021-02-20 | COMP | Rule 16 | 78 | 272 | 36 | 4 |  |  | 1223
429 | 2016-04-11 | 2016-04-22 | 2016-05-20 | 2016-05-20 | COMP | 2016-06-02 | COMP | 2016-06-02 | COMP | 2020-02-26 | COMP | 2020-01-30 | COMP | Rule 16 | 10 | 21 | 9 | 1 | 937 |  | 956
519 | 2016-04-11 | 2016-06-27 | 2016-08-24 | 2019-05-09 | COMP | 2019-06-17 | COMP | 2019-08-28 | COMP | 2020-03-19 | COMP | 2020-03-30 | COMP | Rule 16 | 55 | 42 | 27 | 52 | 139 | 8 | 997
733 | 2016-04-11 | 2016-10-26 | 2017-06-27 | 2017-06-27 | COMP | 2017-09-25 | COMP | 2018-01-02 | COMP | 2019-03-03 | COMP | 2019-03-27 | COMP | Rule 16 | 140 | 168 | 63 | 67 | 292 | 18 | 744
1260 | 2016-04-11 | 2017-05-02 | 2017-08-17 | 2017-08-17 | COMP | 2019-02-04 | COMP | 2020-01-02 | COMP | 2020-05-18 | COMP | 2020-07-20 | COMP | Rule 16 | 268 | 76 | 366 | 230 | 96 | 45 | 1076
463 | 2016-04-12 | 2016-05-18 | 2016-08-15 | 2016-08-15 | COMP | 2016-09-23 | COMP | 2016-09-29 | COMP | 2017-01-31 | COMP | 2021-07-09 | COMP | Rule 15/16 | 27 | 62 | 29 | 5 | 84 | 1117 | 1319
701 | 2016-04-12 | 2016-10-19 | 2016-12-12 | 2016-12-12 | COMP | 2017-06-01 | COMP | 2019-03-30 | COMP | 2020-07-01 | COMP | 2020-07-13 | COMP | Rule 16 | 134 | 36 | 120 | 458 | 317 | 9 | 1070
848 | 2016-04-12 | 2016-12-19 | 2017-03-27 | 2017-03-27 | COMP | 2018-03-27 | COMP | 2019-10-31 | COMP | 2020-04-06 | COMP | 2020-05-18 | COMP | Rule 16 | 174 | 68 | 252 | 405 | 106 | 31 | 1031
1851 | 2016-04-12 | 2017-08-10 | 2018-04-20 | 2018-04-20 | COMP | 2018-11-15 | COMP | 2018-11-22 | COMP | 2019-04-20 | INPR | 2019-01-30 | COMP | Rule 15/16 | 337 | 174 | 146 | 5 |  |  | 704
2188 | 2016-04-12 | 2017-10-05 | 2018-02-14 | 2018-02-14 | COMP | 2018-11-27 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2019-02-23 | COMP | Rule 16 | 376 | 89 | 198 | 25 | 1 | 36 | 720
9798 | 2016-04-12 | 2019-02-16 | 2019-04-26 | 2019-04-26 | COMP | 2019-09-23 | COMP | 2019-10-08 | COMP | 2019-09-25 | COMP | 2019-12-27 | COMP | Rule 16 | 716 | 49 | 104 | 12 | 0 | 55 | 933
507 | 2016-04-13 | 2016-06-22 | 2017-04-12 | 2017-04-12 | COMP | 2018-07-27 | COMP | 2019-01-10 | COMP | 2020-12-01 | COMP | 2021-01-05 | COMP | Rule 15/16 | 50 | 203 | 326 | 114 | 477 | 24 | 1189
6330 | 2016-04-14 | 2018-08-11 | 2018-09-21 | 2018-09-21 | COMP | 2018-09-28 | COMP | 2018-09-28 | COMP | 2019-02-26 | COMP | 2019-04-01 | COMP | Rule 16 | 586 | 29 | 6 | 1 | 101 | 25 | 744
461 | 2016-04-15 | 2016-05-18 | 2016-10-03 | 2016-10-03 | COMP | 2016-11-28 | COMP | 2019-11-19 | COMP | 2020-02-20 | COMP | 2020-06-16 | COMP | Rule 15/16 | 24 | 96 | 38 | 750 | 62 | 83 | 1048
883 | 2016-04-15 | 2017-01-17 | 2017-03-10 | 2017-03-10 | COMP | 2017-03-31 | COMP | 2017-03-31 | COMP | 2017-05-08 | COMP | 2019-05-13 | COMP | Rule 16 | 190 | 38 | 16 | 1 | 27 | 506 | 773
1320 | 2016-04-15 | 2017-05-10 | 2018-10-02 | 2018-10-02 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-01-15 | COMP | 2019-02-27 | COMP | Rule 16 | 270 | 352 | 67 | 1 | 5 | 30 | 720
2593 | 2016-04-15 | 2018-01-03 | 2018-02-26 | 2018-02-26 | COMP | 2018-08-10 | COMP | 2019-03-14 | COMP | 2019-03-04 | COMP | 2019-05-21 | COMP | Rule 16 | 432 | 37 | 118 | 147 | 0 | 49 | 779
4605 | 2016-04-15 | 2018-02-12 | 2018-06-24 | 2018-06-24 | COMP | 2019-01-30 | COMP | 2019-02-21 | COMP | 2019-10-21 | INPR | 2019-06-06 | COMP | Rule 16 | 459 | 93 | 150 | 16 |  |  | 790
450 | 2016-04-19 | 2016-05-07 | 2017-04-08 | 2017-04-08 | COMP | 2017-06-15 | COMP | 2018-12-13 | COMP | 2019-07-30 | COMP | 2019-10-18 | COMP | Rule 15/16 | 14 | 231 | 48 | 376 | 158 | 58 | 882
469 | 2016-04-19 | 2016-05-23 | 2016-05-25 | 2016-05-25 | COMP | 2016-06-01 | COMP | 2016-06-01 | COMP | 2017-03-29 | COMP | 2019-08-19 | COMP | Rule 16 | 25 | 3 | 5 | 1 | 208 | 602 | 839
486 | 2016-04-19 | 2016-06-01 | 2017-01-22 | 2017-01-22 | COMP | 2019-12-09 | COMP | 2017-04-25 | COMP | 2019-12-05 | COMP | 2020-01-02 | COMP | Rule 15/16 | 31 | 161 | 724 |  | 657 | 19 | 931
428 | 2016-04-20 | 2016-04-20 | 2016-12-22 | 2016-12-22 | COMP | 2017-01-04 | COMP | 2017-03-23 | COMP | 2017-03-21 | COMP | 2021-03-11 | COMP | Rule 16 | 1 | 171 | 9 | 55 | 0 | 997 | 1229
570 | 2016-04-20 | 2016-08-06 | 2016-11-28 | 2019-01-12 | COMP | 2019-04-18 | COMP | 2019-04-26 | COMP | 2019-04-18 | COMP | 2019-06-26 | COMP | Rule 16 | 76 | 77 | 67 | 7 | 0 | 43 | 801
571 | 2016-04-20 | 2016-08-06 | 2016-11-17 | 2019-01-12 | COMP | 2019-04-18 | COMP | 2019-05-15 | COMP | 2019-04-26 | COMP | 2019-06-04 | COMP | Rule 16 | 76 | 72 | 67 | 20 | 0 | 14 | 785
5689 | 2016-04-20 | 2018-06-26 | 2019-01-07 | 2022-06-09 | COMP | 2022-06-21 | COMP | 2023-10-30 | COMP | 2023-10-20 | COMP | 2023-11-22 | COMP | Rule 16 | 550 | 133 | 8 | 342 | 0 | 17 | 1909
699 | 2016-04-21 | 2016-10-17 | 2017-04-10 | 2017-04-10 | COMP | 2017-04-05 | COMP | 2018-01-08 | COMP | 2018-12-11 | COMP | 2019-10-17 | COMP | Rule 16 | 125 | 120 |  | 191 | 234 | 216 | 879
1238 | 2016-04-21 | 2017-04-27 | 2017-06-15 | 2017-06-15 | COMP | 2017-07-18 | COMP | 2020-02-21 | COMP | 2020-02-12 | COMP | 2020-03-04 | COMP | Other | 257 | 35 | 23 | 651 | 0 | 9 | 971
3486 | 2016-04-21 | 2018-05-07 | 2018-10-12 | 2018-10-12 | COMP | 2019-01-09 | COMP | 2019-03-18 | COMP | 2019-03-13 | COMP | 2019-04-18 | COMP | Rule 16 | 514 | 112 | 59 | 47 | 0 | 24 | 752
474 | 2016-04-25 | 2016-05-25 | 2017-04-17 | 2019-05-24 | COMP | 2019-08-14 | COMP | 2020-08-27 | COMP | 2021-01-13 | COMP | 2021-02-25 | COMP | Rule 15/16 | 23 | 225 | 57 | 263 | 94 | 30 | 1216
475 | 2016-04-25 | 2016-05-25 | 2017-04-26 | 2019-06-10 | COMP | 2019-06-26 | COMP | 2019-12-13 | COMP | 2019-11-23 | COMP | 2020-02-27 | COMP | Rule 15/16 | 23 | 232 | 13 | 118 | 0 | 51 | 965
504 | 2016-04-25 | 2016-06-16 | 2016-10-07 | 2016-10-07 | COMP | 2017-07-17 | COMP | 2018-08-16 | COMP | 2020-05-19 | COMP | 2020-06-23 | COMP | Rule 16 | 38 | 80 | 194 | 274 | 441 | 25 | 1047
510 | 2016-04-25 | 2016-06-22 | 2016-10-03 | 2018-04-11 | COMP | 2018-06-07 | COMP | 2018-12-17 | COMP | 2020-04-25 | INPR | 2020-01-10 | COMP | Rule 16 | 42 | 72 | 41 | 133 |  |  | 933
557 | 2016-04-25 | 2016-07-25 | 2016-08-29 | 2016-08-29 | COMP | 2016-10-05 | COMP | 2016-11-16 | COMP | 2016-12-13 | COMP | 2022-03-18 | COMP | Rule 16 | 64 | 26 | 27 | 30 | 18 | 1324 | 1484
605 | 2016-04-25 | 2016-09-01 | 2018-04-04 | 2018-04-04 | COMP | 2020-09-08 | COMP | 2020-11-05 | COMP | 2021-03-19 | COMP | 2021-04-08 | COMP | Rule 16 | 92 | 398 | 613 | 43 | 90 | 15 | 1246
880 | 2016-04-25 | 2017-01-14 | 2017-04-07 | 2020-08-12 | COMP | 2020-10-09 | COMP | 2020-02-28 | COMP | 2021-08-31 | COMP | 2022-01-26 | COMP | Rule 15/16 | 183 | 58 | 42 |  | 382 | 102 | 1448
1869 | 2016-04-25 | 2017-08-11 | 2017-10-03 | 2017-10-03 | COMP | 2017-10-25 | COMP | 2017-10-25 | COMP | 2018-03-16 | COMP | 2022-03-26 | COMP | Rule 16 | 329 | 37 | 17 | 1 | 96 | 1014 | 1489
3564 | 2016-04-25 | 2018-05-17 | 2019-04-18 | 2019-04-18 | COMP | 2020-02-27 | COMP | 2020-09-14 | COMP |  | INPR | 2020-10-01 | COMP | Rule 16 | 520 | 231 | 216 | 141 |  |  | 1118
4081 | 2016-04-25 | 2019-01-14 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-25 | COMP | 2019-02-26 | COMP | 2019-08-31 | INPR | 2019-04-23 | COMP | Rule 16 | 684 | 7 | 23 | 2 |  |  | 753
454 | 2016-04-26 | 2016-05-09 | 2016-08-08 | 2016-08-08 | COMP | 2016-09-13 | COMP | 2018-03-29 | COMP | 2022-02-25 | COMP | 2022-06-21 | COMP | Rule 16 | 10 | 64 | 26 | 387 | 985 | 81 | 1548
1182 | 2016-04-26 | 2017-04-14 | 2017-09-30 | 2018-07-19 | COMP | 2018-08-16 | COMP | 2018-11-30 | COMP | 2019-07-21 | INPR | 2019-02-07 | COMP | Rule 16 | 245 | 118 | 21 | 73 |  |  | 700
456 | 2016-04-28 | 2016-05-11 | 2016-09-27 | 2016-09-27 | COMP | 2017-04-11 | COMP | 2017-06-01 | COMP | 2017-08-03 | COMP | 2020-11-03 | COMP | Rule 16 | 10 | 97 | 135 | 37 | 45 | 819 | 1138
730 | 2016-04-28 | 2016-10-25 | 2017-04-24 | 2017-12-14 | COMP | 2018-01-02 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-08-13 | COMP | Rule 16 | 126 | 124 | 12 | 352 | 1 | 56 | 828
491 | 2016-04-29 | 2016-06-04 | 2016-06-13 | 2016-06-13 | COMP | 2016-07-13 | COMP | 2016-07-13 | COMP | 2020-10-27 | COMP | 2020-11-25 | COMP | Rule 16 | 25 | 6 | 22 | 1 | 1081 | 21 | 1152
990 | 2016-04-29 | 2017-02-22 | 2017-10-06 | 2017-10-06 | COMP | 2018-11-06 | COMP | 2018-11-07 | COMP | 2019-03-20 | COMP | 2019-05-07 | COMP | Rule 16 | 205 | 160 | 273 | 2 | 89 | 35 | 759
473 | 2016-05-02 | 2016-05-25 | 2018-03-09 | 2018-03-09 | COMP | 2018-06-13 | COMP | 2018-06-13 | COMP | 2019-01-03 | COMP | 2019-02-27 | COMP | Rule 16 | 18 | 449 | 68 | 1 | 140 | 38 | 709
553 | 2016-05-02 | 2016-07-23 | 2018-03-22 | 2018-03-22 | COMP | 2018-04-09 | COMP | 2019-07-10 | COMP | 2019-07-08 | COMP | 2019-08-20 | COMP | Rule 16 | 58 | 417 | 13 | 316 | 0 | 30 | 831
531 | 2016-05-03 | 2016-06-30 | 2017-10-22 | 2017-10-22 | COMP | 2019-10-30 | COMP | 2020-09-08 | COMP | 2020-10-19 | COMP | 2020-10-30 | COMP | Rule 15/16 | 42 | 331 | 508 | 216 | 30 | 10 | 1133
667 | 2016-05-03 | 2016-09-29 | 2016-12-13 | 2016-12-13 | COMP | 2017-08-01 | COMP | 2017-08-24 | COMP | 2017-08-07 | COMP | 2019-08-22 | COMP | Rule 16 | 105 | 51 | 161 | 18 | 0 | 501 | 832
750 | 2016-05-03 | 2016-11-07 | 2018-01-23 | 2018-08-02 | COMP | 2018-12-17 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-01-22 | COMP | Rule 15 | 132 | 302 | 94 | 242 | 1 | 34 | 934
1263 | 2016-05-03 | 2017-05-02 | 2017-06-09 | 2017-06-09 | COMP | 2017-05-02 | NOTN | 2018-11-16 | COMP | 2017-05-02 | COMP | 2019-01-29 | COMP | Other | 252 | 28 |  | 363 | 0 | 48 | 688
1417 | 2016-05-03 | 2017-05-31 | 2018-07-31 | 2018-07-31 | COMP | 2018-08-23 | COMP | 2019-03-11 | COMP | 2019-03-04 | COMP | 2019-03-28 | COMP | Rule 15/16 | 272 | 294 | 18 | 135 | 0 | 14 | 729
609 | 2016-05-04 | 2016-09-03 | 2017-04-22 | 2017-04-22 | COMP | 2019-08-07 | COMP | 2017-07-07 | COMP | 2019-10-03 | COMP | 2019-11-05 | COMP | Rule 16 | 86 | 158 | 576 |  | 564 | 24 | 883
501 | 2016-05-09 | 2016-06-15 | 2016-09-17 | 2019-01-09 | COMP | 2019-10-07 | COMP | 2019-10-07 | COMP | 2019-09-30 | COMP | 2020-07-10 | COMP | Rule 16 | 27 | 66 | 189 | 1 | 0 | 192 | 1050
505 | 2016-05-09 | 2016-06-20 | 2016-11-16 | 2016-11-16 | COMP | 2017-03-07 | COMP | 2017-03-10 | COMP | 2019-03-17 | COMP | 2019-04-12 | COMP | Rule 16 | 30 | 105 | 75 | 4 | 506 | 20 | 736
794 | 2016-05-09 | 2016-11-30 | 2017-07-18 | 2017-10-30 | COMP | 2018-03-07 | COMP | 2020-10-05 | COMP | 2022-01-29 | REQD | 2020-11-04 | COMP | Rule 16 | 142 | 160 | 86 | 652 |  |  | 1132
845 | 2016-05-09 | 2016-12-16 | 2017-11-17 | 2017-11-17 | COMP | 2018-11-27 | COMP | 2019-07-30 | COMP | 2019-10-21 | COMP | 2019-12-31 | COMP | Rule 16 | 154 | 234 | 256 | 170 | 59 | 48 | 916
1580 | 2016-05-09 | 2017-06-27 | 2018-02-21 | 2018-02-21 | COMP | 2018-04-30 | COMP | 2018-04-30 | COMP | 2018-12-13 | COMP | 2019-01-17 | COMP | Rule 15/16 | 287 | 163 | 49 | 1 | 158 | 24 | 677
1906 | 2016-05-09 | 2017-08-18 | 2019-01-30 | 2019-01-30 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-29 | COMP | 2019-06-26 | COMP | Other | 324 | 362 | 66 | 1 | 19 | 21 | 788
3497 | 2016-05-09 | 2018-05-08 | 2018-09-26 | 2018-09-26 | COMP | 2019-03-20 | COMP | 2019-06-19 | COMP | 2023-11-11 | INPR | 2019-06-23 | COMP | Rule 15/16 | 503 | 99 | 119 | 65 |  |  | 785
729 | 2016-05-10 | 2016-10-25 | 2018-05-11 | 2018-05-11 | COMP | 2019-03-07 | COMP | 2019-04-10 | COMP | 2019-10-08 | COMP | 2020-01-06 | COMP | Rule 15/16 | 118 | 388 | 205 | 25 | 127 | 60 | 918
822 | 2016-05-10 | 2016-12-09 | 2017-04-03 | 2018-05-22 | COMP | 2018-07-24 | COMP | 2018-07-24 | COMP | 2019-11-23 | INPR | 2019-07-15 | COMP | Rule 16 | 148 | 79 | 44 | 1 |  |  | 799
1000 | 2016-05-10 | 2017-02-23 | 2018-01-12 | 2020-04-20 | COMP | 2023-04-29 | INPR | 2018-04-12 | COMP | 2019-08-22 | COMP | 2020-08-19 | COMP | Rule 15/16 | 199 | 224 |  |  | 344 | 251 | 1077
686 | 2016-05-11 | 2016-10-11 | 2017-05-25 | 2017-05-25 | COMP | 2017-08-16 | COMP | 2017-08-16 | INPR | 2019-03-01 | COMP | 2019-03-13 | COMP | Rule 16 | 107 | 157 | 58 |  |  |  | 712
471 | 2016-05-12 | 2016-05-24 | 2016-06-24 | 2016-06-24 | COMP | 2016-07-07 | COMP | 2016-08-12 | COMP | 2017-03-09 | COMP | 2019-12-31 | COMP | Rule 16 | 9 | 23 | 9 | 27 | 143 | 707 | 913
921 | 2016-05-12 | 2017-02-01 | 2017-06-19 | 2017-06-19 | COMP | 2018-03-22 | COMP | 2019-02-01 | COMP | 2018-09-25 | COMP | 2019-03-15 | COMP | Rule 15/16 | 182 | 97 | 190 | 218 | 0 | 30 | 713
1904 | 2016-05-12 | 2017-08-18 | 2017-12-14 | 2017-12-14 | COMP | 2018-07-16 | COMP | 2018-07-16 | COMP | 2022-07-16 | INPR | 2021-03-08 | COMP | Rule 15/16 | 321 | 81 | 147 | 1 |  |  | 1210
2487 | 2016-05-12 | 2017-12-07 | 2019-08-28 | 2018-02-28 | COMP | 2019-03-05 | COMP | 2019-12-17 | COMP | 2020-02-12 | COMP | 2020-06-30 | COMP | Rule 16 | 396 | 434 | 255 | 200 | 39 | 98 | 1039
468 | 2016-05-13 | 2016-05-23 | 2017-04-22 | 2018-12-07 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-07-05 | COMP | 2019-09-04 | COMP | Rule 15/16 | 7 | 231 | 112 | 1 | 34 | 43 | 832
567 | 2016-05-13 | 2016-08-02 | 2017-02-01 | 2018-06-05 | COMP | 2018-08-27 | COMP | 2019-03-08 | COMP | 2019-04-09 | COMP | 2019-04-29 | COMP | Rule 15/16 | 56 | 126 | 59 | 132 | 23 | 15 | 743
714 | 2016-05-13 | 2016-10-21 | 2017-08-11 | 2017-08-11 | COMP | 2017-08-30 | COMP | 2017-08-30 | NOTN | 2018-01-15 | COMP | 2019-05-01 | COMP | Other | 113 | 203 | 14 |  |  |  | 745
812 | 2016-05-13 | 2016-12-06 | 2017-02-01 | 2017-02-01 | COMP | 2017-08-18 | COMP | 2017-08-25 | COMP | 2017-08-23 | COMP | 2022-03-29 | COMP | Rule 16 | 142 | 40 | 140 | 6 | 0 | 1153 | 1477
515 | 2016-05-16 | 2016-06-23 | 2016-12-14 | 2016-12-14 | COMP | 2018-10-31 | COMP | 2018-11-14 | COMP | 2019-04-22 | COMP | 2019-07-12 | COMP | Rule 15/16 | 28 | 120 | 475 | 10 | 108 | 58 | 794
530 | 2016-05-16 | 2016-06-30 | 2017-05-17 | 2017-05-17 | COMP | 2018-03-06 | COMP | 2019-11-12 | COMP | 2019-10-11 | COMP | 2019-11-08 | COMP | Rule 15/16 | 33 | 222 | 200 | 427 | 0 |  | 878
562 | 2016-05-16 | 2016-07-30 | 2017-04-26 | 2017-04-26 | COMP | 2019-06-05 | COMP | 2019-06-25 | COMP | 2019-06-05 | COMP | 2019-08-06 | COMP | Rule 15/16 | 53 | 186 | 530 | 15 | 0 | 30 | 811
1382 | 2016-05-16 | 2017-05-23 | 2017-08-04 | 2017-08-04 | COMP | 2017-12-01 | COMP | 2017-12-01 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | Rule 15/16 | 258 | 52 | 82 | 1 | 320 | 1 | 709
495 | 2016-05-17 | 2016-06-09 | 2016-06-14 | 2016-06-14 | COMP | 2017-11-15 | COMP | 2017-11-16 | COMP | 2019-10-03 | COMP | 2020-01-24 | COMP | Rule 16 | 17 | 4 | 360 | 2 | 472 | 76 | 926
542 | 2016-05-17 | 2016-07-18 | 2016-08-05 | 2016-08-05 | COMP | 2016-08-29 | COMP | 2023-07-29 | CANC | 2017-10-03 | COMP | 2022-03-14 | COMP | Rule 16 | 43 | 15 | 17 |  |  |  | 1464
3192 | 2016-05-17 | 2018-03-21 | 2018-04-13 | 2018-04-13 | COMP | 2019-04-15 | COMP | 2019-04-17 | COMP | 2019-08-31 | INPR | 2019-05-09 | COMP | Rule 16 | 463 | 18 | 252 | 3 |  |  | 749
580 | 2016-05-18 | 2016-08-13 | 2017-02-13 | 2017-02-13 | COMP | 2017-05-12 | COMP | 2017-05-15 | COMP | 2019-05-24 | COMP | 2019-06-18 | COMP | Rule 16 | 61 | 125 | 64 | 2 | 510 | 17 | 775
779 | 2016-05-18 | 2016-11-21 | 2016-12-23 | 2016-12-23 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-03-06 | COMP | 2019-04-01 | COMP | Rule 16 | 130 | 23 | 471 | 1 | 81 | 19 | 720
629 | 2016-05-19 | 2016-09-13 | 2017-10-15 | 2017-10-15 | COMP | 2018-03-23 | COMP | 2019-05-31 | COMP | 2019-05-16 | COMP | 2019-06-27 | COMP | Rule 15/16 | 81 | 275 | 108 | 300 | 0 | 20 | 781
502 | 2016-05-20 | 2016-06-17 | 2016-09-18 | 2016-09-18 | COMP | 2018-12-28 | COMP | 2020-04-07 | COMP | 2021-10-23 | REQD | 2020-06-19 | COMP | Rule 15/16 | 20 | 64 | 572 | 320 |  |  | 1026
694 | 2016-05-20 | 2016-10-14 | 2016-11-07 | 2016-11-07 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-08-20 | COMP | 2019-09-12 | COMP | Rule 16 | 103 | 17 | 515 | 1 | 185 | 17 | 833
3688 | 2016-05-20 | 2018-06-07 | 2018-12-28 | 2018-12-28 | COMP | 2019-03-25 | COMP | 2020-01-29 | COMP | 2021-02-28 | INPR | 2020-02-11 | COMP | Rule 15/16 | 515 | 141 | 59 | 214 |  |  | 935
5185 | 2016-05-20 | 2018-05-08 | 2018-09-07 | 2018-09-07 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-02-26 | COMP | 2019-11-12 | COMP | Rule 16 | 494 | 86 | 115 | 1 | 2 | 182 | 875
797 | 2016-05-23 | 2016-12-02 | 2017-03-25 | 2017-03-25 | COMP | 2017-05-31 | COMP | 2017-05-31 | COMP | 2020-02-06 | COMP | 2020-02-20 | COMP | Rule 16 | 134 | 78 | 47 | 1 | 674 | 10 | 940
4780 | 2016-05-23 | 2018-03-29 | 2019-12-03 | 2019-12-27 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-08-06 | COMP | 2020-11-09 | COMP | Rule 16 | 465 | 423 | 7 | 1 | 150 | 67 | 1125
5297 | 2016-05-23 | 2018-05-18 | 2018-10-22 | 2018-10-22 | COMP | 2019-01-22 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-05-04 | COMP | Rule 16 | 501 | 109 | 61 | 55 | 1 | 19 | 741
13890 | 2016-05-23 | 2019-08-15 | 2020-03-17 | 2020-03-17 | COMP | 2020-03-30 | COMP | 2020-04-03 | COMP | 2020-10-29 | COMP | 2020-11-03 | COMP | Rule 16 | 813 | 146 | 10 | 5 | 148 | 4 | 1121
585 | 2016-05-24 | 2016-08-17 | 2016-11-14 | 2017-02-07 | COMP | 2017-04-25 | COMP | 2017-05-31 | COMP | 2017-06-29 | COMP | 2021-01-14 | COMP | Rule 15/16 | 60 | 62 | 55 | 26 | 22 | 890 | 1167
697 | 2016-05-24 | 2016-10-15 | 2017-08-25 | 2017-08-25 | COMP | 2018-09-06 | COMP | 2018-09-06 | COMP | 2020-03-18 | COMP | 2020-07-17 | COMP | Rule 15/16 | 101 | 217 | 259 | 1 | 383 | 87 | 1044
2269 | 2016-05-24 | 2017-10-26 | 2018-01-23 | 2018-01-23 | COMP | 2018-06-06 | COMP | 2018-06-06 | COMP | 2019-02-06 | COMP | 2019-03-11 | COMP | Rule 16 | 361 | 58 | 95 | 1 | 168 | 23 | 701
827 | 2016-05-25 | 2016-12-12 | 2017-04-24 | 2017-04-24 | COMP | 2017-10-11 | COMP | 2018-01-17 | COMP | 2018-10-11 | COMP | 2019-01-02 | COMP | Rule 15/16 | 138 | 93 | 120 | 65 | 188 | 55 | 654
1347 | 2016-05-25 | 2017-05-15 | 2017-11-11 | 2017-11-11 | COMP | 2018-01-02 | COMP | 2018-04-12 | COMP | 2020-08-29 | INPR | 2019-02-28 | COMP | Rule 15/16 | 245 | 126 | 33 | 71 |  |  | 693
1866 | 2016-05-25 | 2017-08-11 | 2017-12-13 | 2017-12-11 | COMP | 2018-01-30 | COMP | 2018-01-30 | COMP |  | INPR | 2023-06-09 | COMP | Rule 15/16 | 307 | 85 | 34 | 1 |  |  | 1770
2707 | 2016-05-25 | 2018-01-23 | 2018-02-09 | 2018-02-09 | COMP | 2018-03-26 | COMP | 2018-05-23 | COMP | 2021-09-24 | COMP | 2021-10-19 | COMP | Rule 16 | 417 | 14 | 31 | 43 | 841 | 18 | 1359
528 | 2016-05-26 | 2016-06-29 | 2017-01-16 | 2017-01-16 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2021-06-08 | COMP | 2021-06-23 | COMP | Rule 16 | 24 | 137 | 884 | 1 | 222 | 12 | 1276
572 | 2016-05-26 | 2016-08-06 | 2016-11-17 | 2018-06-28 | COMP | 2018-08-03 | COMP | 2019-05-28 | COMP | 2019-05-06 | COMP | 2019-06-20 | COMP | Rule 16 | 50 | 72 | 26 | 204 | 0 | 18 | 771
625 | 2016-05-26 | 2016-09-12 | 2017-01-18 | 2017-01-18 | COMP | 2017-07-06 | COMP | 2017-07-06 | COMP | 2022-11-05 | INPR | 2021-09-23 | COMP | Rule 16 | 75 | 88 | 119 | 1 |  |  | 1340
633 | 2016-05-26 | 2016-09-14 | 2017-03-06 | 2017-03-06 | COMP | 2017-05-08 | COMP | 2017-05-08 | COMP | 2019-05-01 | COMP | 2019-05-10 | COMP | Rule 16 | 77 | 118 | 46 | 1 | 498 | 8 | 743
3413 | 2016-05-26 | 2018-04-24 | 2018-08-21 | 2019-01-31 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-03-27 | COMP | 2019-06-28 | COMP | Rule 15/16 | 480 | 84 | 7 | 1 | 33 | 67 | 777
3415 | 2016-05-26 | 2018-04-24 | 2019-01-09 | 2019-01-09 | COMP | 2019-03-28 | COMP | 2019-06-25 | COMP | 2019-06-14 | COMP | 2019-08-25 | COMP | Rule 15/16 | 480 | 179 | 55 | 63 | 0 | 43 | 816
626 | 2016-05-27 | 2016-09-12 | 2016-12-12 | 2016-12-12 | COMP | 2018-02-26 | COMP | 2018-02-26 | COMP | 2018-11-21 | COMP | 2019-01-15 | COMP | Rule 16 | 74 | 63 | 303 | 1 | 189 | 36 | 661
702 | 2016-05-27 | 2016-10-19 | 2016-12-20 | 2016-12-20 | COMP | 2019-09-13 | COMP | 2020-01-22 | COMP | 2020-01-28 | COMP | 2020-03-17 | COMP | Rule 16 | 101 | 42 | 688 | 88 | 5 | 35 | 954
3890 | 2016-05-27 | 2018-09-18 | 2019-07-22 | 2019-07-22 | COMP | 2020-02-07 | COMP | 2020-05-07 | COMP | 2022-07-16 | INPR | 2020-05-13 | COMP | Rule 16 | 581 | 211 | 138 | 64 |  |  | 995
543 | 2016-05-31 | 2016-07-18 | 2016-07-30 | 2016-12-06 | COMP | 2016-12-28 | COMP | 2016-12-28 | INPR | 2019-06-05 | COMP | 2019-06-27 | COMP | Rule 16 | 34 | 10 | 16 |  |  |  | 774
2581 | 2016-05-31 | 2017-12-30 | 2018-03-08 | 2018-03-08 | COMP | 2018-03-30 | COMP | 2018-03-30 | COMP | 2019-06-29 | COMP | 2019-08-14 | COMP | Rule 16 | 399 | 46 | 17 | 1 | 315 | 32 | 807
2999 | 2016-05-31 | 2018-02-26 | 2018-04-16 | 2018-04-16 | COMP | 2018-05-24 | COMP | 2018-06-21 | COMP | 2018-12-12 | COMP | 2019-07-16 | COMP | Rule 16 | 437 | 36 | 29 | 20 | 120 | 149 | 786
499 | 2016-06-01 | 2016-06-14 | 2016-09-05 | 2016-09-05 | COMP | 2017-09-26 | COMP | 2018-03-10 | COMP | 2019-07-22 | COMP | 2022-05-11 | COMP | Rule 15/16 | 10 | 58 | 267 | 112 | 344 | 708 | 1496
4039 | 2016-06-01 | 2018-12-26 | 2018-12-28 | 2018-12-28 | COMP | 2019-02-27 | COMP | 2019-03-19 | COMP | 2019-03-22 | COMP | 2019-04-23 | COMP | Rule 16 | 646 | 3 | 41 | 15 | 4 | 23 | 727
552 | 2016-06-03 | 2016-07-22 | 2016-10-10 | 2018-03-03 | COMP | 2018-10-18 | COMP | 2019-08-15 | COMP | 2019-06-13 | COMP | 2019-11-07 | COMP | Rule 15/16 | 35 | 56 | 161 | 207 | 0 | 60 | 864
555 | 2016-06-03 | 2016-07-23 | 2017-02-17 | 2017-02-17 | COMP | 2019-06-27 | COMP | 2017-11-30 | COMP | 2019-06-10 | COMP | 2019-07-15 | COMP | Rule 16 | 35 | 144 | 593 |  | 383 | 25 | 782
876 | 2016-06-03 | 2017-01-12 | 2017-04-14 | 2018-05-25 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2020-10-12 | COMP | 2020-11-10 | COMP | Rule 16 | 154 | 65 | 179 | 1 | 422 | 22 | 1118
664 | 2016-06-04 | 2016-09-28 | 2017-02-03 | 2017-02-03 | COMP | 2018-05-18 | COMP | 2017-08-01 | COMP | 2019-03-14 | COMP | 2019-03-26 | COMP | Rule 16 | 81 | 88 | 325 |  | 405 | 9 | 704
518 | 2016-06-06 | 2016-06-27 | 2016-10-03 | 2016-10-03 | COMP | 2016-11-10 | COMP | 2016-11-28 | COMP | 2018-11-21 | COMP | 2019-01-11 | COMP | Rule 16 | 16 | 69 | 29 | 10 | 501 | 34 | 654
497 | 2016-06-07 | 2016-06-10 | 2016-06-17 | 2016-06-17 | COMP | 2016-06-21 | COMP | 2018-02-27 | INPR | 2021-06-19 | REQD | 2021-04-02 | COMP | Rule 16 | 4 | 6 | 3 |  |  |  | 1212
713 | 2016-06-07 | 2016-10-21 | 2017-03-22 | 2017-03-22 | COMP | 2017-07-06 | COMP | 2018-04-30 | COMP | 2019-02-20 | COMP | 2019-03-26 | COMP | Rule 16 | 97 | 103 | 75 | 205 | 203 | 25 | 703
800 | 2016-06-07 | 2016-12-02 | 2017-07-11 | 2017-07-11 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-11-23 | COMP | 2019-11-30 | COMP | Rule 16 | 124 | 153 | 453 | 3 | 143 | 3 | 875
801 | 2016-06-07 | 2016-12-02 | 2017-07-24 | 2017-07-24 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-11-23 | INPR | 2019-08-14 | COMP | Rule 16 | 124 | 162 | 444 | 3 |  |  | 802
802 | 2016-06-07 | 2016-12-02 | 2017-07-15 | 2017-07-15 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-08-05 | COMP | 2019-09-24 | COMP | Rule 16 | 124 | 156 | 449 | 3 | 66 | 36 | 830
803 | 2016-06-07 | 2016-12-02 | 2017-05-22 | 2017-05-22 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-08-05 | COMP | 2019-10-16 | COMP | Rule 16 | 124 | 119 | 487 | 3 | 66 | 52 | 846
804 | 2016-06-07 | 2016-12-02 | 2017-04-28 | 2017-04-28 | COMP | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-01-08 | COMP | 2019-04-03 | COMP | Other | 124 | 103 | 476 | 1 | 0 | 9 | 709
805 | 2016-06-07 | 2016-12-02 | 2017-05-25 | 2017-05-25 | COMP | 2018-12-17 | COMP | 2018-12-18 | COMP | 2019-10-19 | INPR | 2019-03-01 | COMP | Rule 16 | 124 | 122 | 392 | 2 |  |  | 686
806 | 2016-06-07 | 2016-12-02 | 2017-05-01 | 2017-05-01 | COMP | 2018-12-17 | COMP | 2018-12-18 | COMP | 2019-07-21 | INPR | 2019-03-04 | COMP | Rule 16 | 124 | 104 | 410 | 2 |  |  | 687
911 | 2016-06-07 | 2017-01-30 | 2017-08-03 | 2017-06-28 | COMP | 2019-07-09 | COMP | 2019-10-30 | COMP | 2020-01-14 | COMP | 2020-04-29 | COMP | Other | 163 | 131 | 509 | 81 | 50 | 75 | 979
1042 | 2016-06-07 | 2017-03-09 | 2017-06-16 | 2017-06-16 | COMP | 2018-07-02 | COMP | 2019-09-26 | COMP |  | INPR | 2020-11-20 | COMP | Rule 16 | 190 | 71 | 262 | 312 |  |  | 1123
2676 | 2016-06-07 | 2018-01-18 | 2018-03-13 | 2018-03-13 | COMP | 2019-04-30 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2020-03-10 | COMP | Other | 406 | 38 | 286 | 199 | 1 | 18 | 943
2677 | 2016-06-07 | 2018-01-18 | 2018-04-04 | 2018-04-04 | COMP | 2019-07-09 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-03-04 | COMP | Other | 406 | 54 | 318 | 152 | 1 | 13 | 939
2678 | 2016-06-07 | 2018-01-18 | 2018-04-03 | 2018-04-03 | COMP | 2019-04-30 | COMP | 2019-11-07 | COMP | 2019-10-23 | COMP | 2020-01-27 | COMP | Other | 406 | 53 | 271 | 135 | 0 | 52 | 913
2680 | 2016-06-07 | 2018-01-18 | 2018-07-18 | 2018-07-18 | COMP | 2019-03-25 | COMP | 2020-02-18 | COMP | 2020-03-19 | COMP | 2020-03-25 | COMP | Other | 406 | 127 | 171 | 227 | 23 | 5 | 954
2681 | 2016-06-07 | 2018-01-18 | 2018-12-11 | 2018-03-08 | COMP | 2019-03-25 | COMP | 2020-02-18 | COMP | 2020-03-30 | COMP | 2020-04-02 | COMP | Other | 406 | 227 | 263 | 227 | 30 | 4 | 960
2682 | 2016-06-07 | 2018-01-18 | 2018-12-11 | 2018-03-20 | COMP | 2019-03-25 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-03-13 | COMP | Other | 406 | 227 | 255 | 226 | 1 | 20 | 946
4943 | 2016-06-07 | 2018-04-13 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-31 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2020-01-11 | COMP | Rule 16 | 466 | 166 | 15 | 165 | 1 | 95 | 903
521 | 2016-06-08 | 2016-06-27 | 2017-04-23 | 2017-04-23 | COMP | 2016-06-27 | NOTN | 2018-10-01 | COMP | 2018-08-04 | COMP | 2019-01-15 | COMP | Other | 14 | 207 |  | 363 | 0 | 72 | 654
535 | 2016-06-08 | 2016-07-11 | 2016-11-18 | 2016-11-18 | COMP | 2016-12-21 | COMP | 2016-12-22 | COMP | 2019-06-20 | COMP | 2019-07-06 | COMP | Rule 15/16 | 23 | 93 | 22 | 2 | 627 | 11 | 773
551 | 2016-06-08 | 2016-07-20 | 2016-08-18 | 2016-08-18 | COMP | 2016-09-01 | COMP | 2016-09-01 | COMP | 2020-06-16 | COMP | 2020-08-31 | COMP | Rule 15/16 | 30 | 22 | 11 | 1 | 951 | 55 | 1065
520 | 2016-06-09 | 2016-06-27 | 2017-03-04 | 2017-03-04 | COMP | 2018-07-26 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-01-09 | COMP | Rule 15/16 | 13 | 172 | 352 | 334 | 1 | 32 | 900
746 | 2016-06-09 | 2016-11-03 | 2018-01-10 | 2018-01-10 | COMP | 2019-07-31 | COMP | 2019-11-01 | COMP | 2019-10-31 | COMP | 2019-12-11 | COMP | Rule 15/16 | 104 | 296 | 392 | 67 | 0 | 26 | 881
1515 | 2016-06-09 | 2017-06-15 | 2021-02-01 | 2021-09-10 | COMP | 2023-04-15 | INPR | 2023-04-15 | CANC | 2023-04-15 | CANC | 2021-10-14 | COMP | Rule 15/16 | 257 | 911 |  |  |  |  | 1346
3161 | 2016-06-09 | 2018-03-15 | 2018-06-11 | 2018-06-11 | COMP | 2018-07-18 | COMP | 2018-07-18 | COMP | 2020-01-21 | COMP | 2020-03-10 | COMP | Rule 16 | 443 | 62 | 27 | 1 | 378 | 35 | 941
3709 | 2016-06-09 | 2018-06-14 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-24 | COMP | 2018-10-25 | NOTN | 2018-11-15 | COMP | 2019-01-10 | COMP | Other | 507 | 73 | 21 |  |  |  | 650
771 | 2016-06-10 | 2016-11-16 | 2018-05-29 | 2018-11-12 | COMP | 2019-07-08 | COMP | 2019-07-10 | COMP | 2021-02-02 | COMP | 2021-02-25 | COMP | Rule 15/16 | 111 | 384 | 162 | 3 | 394 | 17 | 1183
958 | 2016-06-10 | 2017-02-15 | 2017-09-09 | 2017-09-09 | COMP | 2018-02-05 | COMP | 2018-03-19 | COMP | 2019-01-22 | COMP | 2019-02-05 | COMP | Rule 16 | 172 | 144 | 100 | 30 | 213 | 11 | 666
1115 | 2016-06-10 | 2017-03-27 | 2018-11-25 | 2018-11-25 | COMP | 2019-03-12 | COMP | 2019-03-26 | COMP | 2020-08-10 | COMP | 2020-10-13 | COMP | Rule 16 | 199 | 419 | 73 | 11 | 349 | 46 | 1093
657 | 2016-06-13 | 2016-09-28 | 2018-05-25 | 2018-10-02 | COMP | 2019-01-30 | COMP | 2018-06-25 | COMP | 2019-03-05 | COMP | 2019-04-22 | COMP | Rule 15/16 | 76 | 417 | 81 |  | 173 | 35 | 718
1468 | 2016-06-13 | 2017-06-07 | 2017-08-26 | 2017-08-26 | COMP | 2018-03-26 | COMP | 2018-03-26 | COMP |  | INPR | 2021-01-08 | COMP | Rule 16 | 249 | 57 | 143 | 1 |  |  | 1150
39188 | 2016-06-13 | 2022-10-05 | 2023-02-09 | 2023-03-22 | COMP | 2023-03-22 | NOTN | 2023-06-09 | COMP | 2023-03-27 | NOTN | 2023-07-26 | COMP | Other | 1589 | 86 |  | 57 |  |  | 1789
513 | 2016-06-14 | 2016-06-23 | 2016-12-09 | 2016-12-09 | COMP | 2018-10-31 | COMP | 2018-11-14 | COMP | 2019-04-22 | COMP | 2019-07-03 | COMP | Rule 15/16 | 8 | 117 | 478 | 10 | 108 | 52 | 768
514 | 2016-06-14 | 2016-06-23 | 2016-12-09 | 2016-12-09 | COMP | 2018-10-31 | COMP | 2018-11-14 | COMP | 2019-04-22 | COMP | 2019-07-03 | COMP | Rule 15/16 | 8 | 117 | 478 | 10 | 108 | 52 | 768
577 | 2016-06-14 | 2016-08-10 | 2017-11-17 | 2017-11-17 | COMP | 2018-04-06 | COMP | 2018-06-20 | COMP | 2018-05-15 | COMP | 2019-09-19 | COMP | Rule 15/16 | 41 | 322 | 95 | 53 | 0 | 315 | 822
604 | 2016-06-14 | 2016-08-31 | 2016-09-16 | 2016-09-16 | COMP | 2016-10-19 | COMP | 2016-10-19 | COMP | 2017-02-15 | COMP | 2020-05-21 | COMP | Rule 16 | 56 | 12 | 24 | 1 | 81 | 821 | 990
719 | 2016-06-14 | 2016-10-24 | 2017-03-09 | 2017-03-09 | COMP | 2019-03-13 | COMP | 2017-11-27 | COMP | 2018-05-29 | COMP | 2020-07-21 | COMP | Rule 16 | 93 | 93 | 505 |  | 127 | 541 | 1032
852 | 2016-06-14 | 2016-12-22 | 2017-05-26 | 2018-01-08 | COMP | 2018-04-06 | COMP | 2018-04-12 | COMP | 2018-10-28 | COMP | 2019-05-09 | COMP | Rule 15/16 | 133 | 109 | 63 | 5 | 139 | 132 | 730
554 | 2016-06-15 | 2016-07-23 | 2017-02-17 | 2019-01-10 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-06-12 | COMP | Rule 16 | 27 | 144 | 61 | 1 | 1 | 47 | 752
592 | 2016-06-15 | 2016-08-22 | 2017-12-06 | 2017-12-06 | COMP | 2018-12-12 | COMP | 2019-01-08 | COMP | 2021-02-27 | INPR | 2019-06-10 | COMP | Rule 15/16 | 48 | 325 | 256 | 18 |  |  | 750
628 | 2016-06-15 | 2016-09-12 | 2017-02-17 | 2017-02-17 | COMP | 2017-05-15 | COMP | 2017-10-06 | COMP | 2019-04-28 | COMP | 2019-07-12 | COMP | Rule 16 | 62 | 110 | 61 | 102 | 389 | 53 | 773
684 | 2016-06-15 | 2016-10-10 | 2017-01-26 | 2017-07-25 | COMP | 2021-07-12 | COMP | 2022-07-18 | COMP | 2022-06-29 | COMP | 2022-08-02 | COMP | Rule 16 | 82 | 74 | 996 | 257 | 0 | 12 | 1542
824 | 2016-06-15 | 2016-12-09 | 2017-06-16 | 2019-05-13 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-06-17 | COMP | 2019-08-06 | COMP | Rule 16 | 123 | 132 | 21 | 1 | 5 | 36 | 790
934 | 2016-06-15 | 2017-02-10 | 2017-07-05 | 2018-08-26 | COMP | 2018-09-26 | COMP | 2018-09-26 | COMP | 2019-02-20 | COMP | 2019-06-20 | COMP | Rule 15/16 | 166 | 101 | 22 | 1 | 99 | 86 | 758
670 | 2016-06-17 | 2016-10-03 | 2017-05-10 | 2017-05-10 | COMP | 2018-12-28 | COMP | 2019-08-22 | COMP | 2023-07-29 | INPR | 2021-05-18 | COMP | Rule 16 | 75 | 152 | 411 | 165 |  |  | 1236
922 | 2016-06-17 | 2017-02-02 | 2017-03-22 | 2017-03-22 | COMP | 2017-11-14 | COMP | 2018-05-01 | COMP | 2020-06-16 | COMP | 2020-07-28 | COMP | Rule 16 | 158 | 34 | 166 | 115 | 535 | 31 | 1034
1751 | 2016-06-17 | 2017-07-19 | 2018-10-09 | 2018-10-09 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-09-30 | COMP | 2019-11-06 | COMP | Rule 15/16 | 274 | 309 | 31 | 1 | 215 | 28 | 853
1752 | 2016-06-17 | 2017-07-19 | 2018-10-03 | 2018-10-03 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-10-19 | COMP | 2019-11-06 | COMP | Rule 15/16 | 274 | 305 | 35 | 1 | 229 | 13 | 853
563 | 2016-06-20 | 2016-07-31 | 2016-11-04 | 2016-11-04 | COMP | 2018-09-06 | COMP | 2018-10-19 | COMP | 2019-08-09 | COMP | 2019-11-18 | COMP | Rule 16 | 29 | 69 | 461 | 32 | 202 | 70 | 859
1324 | 2016-06-20 | 2017-05-10 | 2017-06-27 | 2017-06-27 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2022-01-14 | COMP | 2020-06-29 | COMP | Rule 16 | 225 | 34 | 622 | 1 | 524 |  | 1012
1611 | 2016-06-20 | 2017-07-03 | 2017-10-02 | 2019-06-11 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP |  | INPR | 2023-07-18 | COMP | Rule 16 | 262 | 64 | 132 | 1 |  |  | 1778
564 | 2016-06-21 | 2016-08-01 | 2017-06-30 | 2017-06-30 | COMP | 2018-03-13 | COMP | 2018-03-23 | COMP | 2020-08-06 | COMP | 2020-08-21 | COMP | Rule 15/16 | 29 | 232 | 174 | 9 | 599 | 12 | 1050
1627 | 2016-06-21 | 2017-07-06 | 2017-10-20 | 2017-10-20 | COMP | 2018-07-18 | COMP | 2019-01-16 | COMP | 2019-01-22 | COMP | 2019-03-29 | COMP | Rule 16 | 263 | 76 | 185 | 125 | 4 | 48 | 696
524 | 2016-06-22 | 2016-06-28 | 2017-07-26 | 2017-07-26 | COMP | 2016-06-28 | NOTN | 2018-03-21 | INPR | 2017-06-29 | COMP | 2019-01-03 | COMP | Other | 5 | 272 |  |  |  |  | 636
547 | 2016-06-22 | 2016-07-20 | 2020-02-26 | 2020-02-26 | COMP | 2020-08-21 | COMP | 2021-03-12 | COMP | 2021-02-22 | COMP | 2021-06-07 | COMP | Rule 16 | 20 | 904 | 127 | 138 | 0 | 61 | 1246
594 | 2016-06-23 | 2016-08-23 | 2017-09-08 | 2017-09-08 | COMP | 2018-01-30 | COMP | 2018-02-12 | COMP | 2018-10-24 | COMP | 2019-01-28 | COMP | Rule 15/16 | 43 | 264 | 97 | 10 | 179 | 63 | 651
793 | 2016-06-23 | 2016-11-29 | 2016-12-15 | 2016-12-15 | COMP | 2017-05-18 | COMP | 2017-06-23 | COMP | 2019-08-09 | COMP | 2019-10-02 | COMP | Rule 16 | 109 | 13 | 108 | 26 | 535 | 38 | 824
13081 | 2016-06-23 | 2019-07-09 | 2019-08-13 | 2019-08-13 | COMP | 2019-12-20 | COMP | 2020-01-28 | COMP | 2020-01-10 | COMP | 2020-02-26 | COMP | Rule 16 | 764 | 26 | 90 | 25 | 0 | 21 | 922
761 | 2016-06-27 | 2016-11-14 | 2017-05-10 | 2017-05-10 | COMP | 2018-08-14 | COMP | 2018-09-15 | COMP | 2019-05-13 | COMP | 2019-06-06 | COMP | Rule 15/16 | 98 | 123 | 318 | 23 | 164 | 18 | 740
826 | 2016-06-27 | 2016-12-12 | 2017-08-14 | 2018-12-05 | COMP | 2018-12-19 | COMP | 2019-05-08 | COMP | 2019-08-16 | COMP | 2019-08-22 | COMP | Other | 116 | 171 | 11 | 97 | 71 | 5 | 794
610 | 2016-06-28 | 2016-09-03 | 2017-03-09 | 2017-03-09 | COMP | 2018-03-10 | COMP | 2018-03-10 | COMP | 2018-03-21 | COMP | 2020-11-13 | COMP | Rule 16 | 48 | 127 | 252 | 0 | 8 | 670 | 1103
768 | 2016-06-28 | 2016-11-16 | 2017-09-02 | 2017-09-02 | COMP | 2019-09-24 | COMP | 2019-02-05 | COMP | 2019-02-07 | COMP | 2019-04-01 | COMP | Rule 16 | 99 | 201 | 516 |  | 3 | 37 | 692
1436 | 2016-06-28 | 2017-06-01 | 2018-01-23 | 2018-01-23 | COMP | 2018-09-06 | COMP | 2018-11-02 | COMP | 2018-12-11 | COMP | 2019-01-01 | COMP | Rule 15/16 | 234 | 161 | 159 | 42 | 25 | 14 | 630
7494 | 2016-06-28 | 2018-10-17 | 2019-01-03 | 2019-01-03 | COMP | 2019-02-14 | COMP | 2019-07-03 | COMP | 2019-03-29 | COMP | 2020-01-07 | COMP | Rule 16 | 581 | 52 | 30 | 98 | 0 | 128 | 885
597 | 2016-06-29 | 2016-08-25 | 2017-06-16 | 2020-05-11 | COMP | 2020-06-16 | COMP | 2020-07-01 | COMP | 2020-06-23 | COMP | 2020-09-24 | COMP | Rule 15/16 | 41 | 204 | 26 | 12 | 0 | 61 | 1067
652 | 2016-06-29 | 2016-09-26 | 2016-11-11 | 2016-11-11 | COMP | 2017-10-12 | COMP | 2017-10-13 | COMP | 2019-04-05 | COMP | 2019-04-30 | COMP | Rule 15/16 | 62 | 34 | 231 | 2 | 369 | 18 | 712
948 | 2016-06-29 | 2017-02-10 | 2017-03-27 | 2018-03-17 | COMP | 2018-03-29 | COMP | 2018-04-05 | COMP | 2019-09-13 | COMP | 2019-10-17 | COMP | Rule 16 | 156 | 31 | 9 | 6 | 364 | 25 | 831
644 | 2016-06-30 | 2016-09-20 | 2017-01-20 | 2017-01-20 | COMP | 2017-08-29 | COMP | 2019-02-07 | COMP | 2019-03-14 | COMP | 2019-04-11 | COMP | Rule 16 | 57 | 84 | 155 | 361 | 25 | 21 | 698
715 | 2016-06-30 | 2016-10-22 | 2017-03-08 | 2017-03-08 | COMP | 2018-11-20 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-01-31 | COMP | Rule 16 | 80 | 92 | 431 | 4 | 1 | 45 | 649
819 | 2016-06-30 | 2016-12-09 | 2017-06-23 | 2017-06-23 | COMP | 2018-01-24 | COMP | 2019-02-19 | COMP | 2019-03-12 | COMP | 2019-04-23 | COMP | Rule 16 | 112 | 137 | 146 | 269 | 16 | 31 | 706
558 | 2016-07-01 | 2016-07-25 | 2016-08-22 | 2016-08-22 | COMP | 2016-11-21 | COMP | 2016-11-21 | NOTN | 2019-01-25 | COMP | 2019-01-30 | COMP | Rule 16 | 16 | 21 | 64 |  |  |  | 647
573 | 2016-07-01 | 2016-08-08 | 2016-11-30 | 2016-11-30 | COMP | 2017-04-19 | COMP | 2018-01-09 | COMP | 2017-12-08 | COMP | 2022-05-10 | COMP | Rule 16 | 26 | 79 | 98 | 182 | 0 | 1092 | 1473
575 | 2016-07-01 | 2016-08-09 | 2016-10-17 | 2016-10-17 | COMP | 2017-02-16 | COMP | 2019-09-12 | COMP |  |  | 2019-10-15 | COMP | Rule 16 | 27 | 49 | 84 | 647 |  |  | 827
596 | 2016-07-01 | 2016-08-24 | 2017-09-22 | 2017-09-22 | COMP | 2018-01-02 | COMP | 2018-02-20 | COMP | 2018-08-06 | COMP | 2019-07-26 | COMP | Rule 15/16 | 38 | 273 | 68 | 34 | 118 | 245 | 771
1044 | 2016-07-01 | 2017-03-09 | 2017-05-06 | 2017-05-06 | COMP | 2018-02-22 | COMP | 2018-02-23 | COMP | 2021-04-01 | COMP | 2021-04-08 | COMP | Rule 16 | 172 | 42 | 199 | 2 | 781 | 6 | 1198
5962 | 2016-07-01 | 2018-07-16 | 2018-12-10 | 2019-05-28 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-04-17 | COMP | 2019-07-09 | COMP | Rule 15/16 | 512 | 102 | 8 | 1 | 0 | 23 | 758
545 | 2016-07-06 | 2016-07-18 | 2016-10-25 | 2016-10-25 | COMP | 2017-05-02 | NOTN | 2017-06-23 | COMP | 2018-11-14 | COMP | 2019-01-09 | COMP | Other | 9 | 71 |  | 167 | 351 | 37 | 631
576 | 2016-07-06 | 2016-08-09 | 2017-02-01 | 2017-02-01 | COMP | 2017-05-26 | COMP | 2017-06-20 | COMP | 2017-09-20 | COMP | 2020-01-29 | COMP | Rule 15/16 | 25 | 121 | 82 | 17 | 65 | 590 | 895
1124 | 2016-07-07 | 2017-03-30 | 2017-05-17 | 2017-05-17 | COMP | 2018-07-09 | COMP | 2018-07-20 | COMP | 2019-02-07 | COMP | 2019-03-29 | COMP | Rule 15/16 | 184 | 35 | 287 | 10 | 138 | 36 | 685
4202 | 2016-07-07 | 2019-07-11 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-18 | COMP | 2019-09-18 | COMP | 2019-10-08 | COMP | 2019-10-15 | COMP | Rule 16 | 757 | 41 | 9 | 1 | 15 | 6 | 824
631 | 2016-07-08 | 2016-09-14 | 2018-02-02 | 2019-07-22 | COMP | 2020-04-20 | COMP | 2020-05-07 | COMP | 2023-12-31 | INPR | 2020-08-09 | COMP | Rule 15/16 | 48 | 348 | 188 | 14 |  |  | 1028
632 | 2016-07-08 | 2016-09-14 | 2016-10-11 | 2016-10-11 | COMP | 2016-11-14 | COMP | 2016-11-14 | COMP | 2017-12-13 | COMP | 2019-09-14 | COMP | Rule 16 | 48 | 20 | 24 | 1 | 272 | 441 | 801
600 | 2016-07-11 | 2016-08-27 | 2017-06-06 | 2017-06-06 | COMP | 2017-07-05 | COMP | 2017-07-05 | COMP | 2017-07-11 | COMP | 2020-09-15 | COMP | Rule 15/16 | 35 | 194 | 21 | 1 | 5 | 801 | 1053
646 | 2016-07-11 | 2016-09-20 | 2016-10-02 | 2016-10-02 | COMP | 2016-10-18 | COMP | 2018-01-04 | COMP | 2022-07-16 | INPR | 2021-01-25 | COMP | Rule 16 | 51 | 9 | 12 | 304 |  |  | 1141
808 | 2016-07-11 | 2016-12-05 | 2017-05-06 | 2017-05-06 | COMP | 2019-02-05 | COMP | 2018-06-04 | COMP | 2019-07-09 | COMP | 2020-07-01 | COMP | Rule 16 | 102 | 107 | 438 |  | 276 | 248 | 1000
39189 | 2016-07-11 | 2022-10-05 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-19 | NOTN | 2023-08-28 | COMP | 2023-06-20 | COMP | 2023-09-25 | COMP | Other | 1570 | 168 |  | 57 | 0 | 20 | 1812
912 | 2016-07-13 | 2017-01-29 | 2017-05-11 | 2017-05-11 | COMP | 2019-11-19 | COMP | 2017-06-27 | COMP | 2020-03-24 | COMP | 2020-06-09 | COMP | Rule 15/16 | 137 | 73 | 635 |  | 687 | 55 | 982
914 | 2016-07-13 | 2017-01-29 | 2017-05-05 | 2017-05-05 | COMP | 2017-06-27 | COMP | 2017-06-27 | COMP | 2019-10-16 | COMP | 2019-12-12 | COMP | Rule 15/16 | 137 | 69 | 37 | 1 | 580 | 39 | 859
967 | 2016-07-13 | 2017-02-16 | 2017-05-20 | 2018-04-25 | COMP | 2018-05-17 | COMP | 2018-05-24 | COMP | 2019-03-25 | COMP | 2019-04-13 | COMP | Rule 15/16 | 151 | 66 | 17 | 6 | 208 | 15 | 691
968 | 2016-07-13 | 2017-02-16 | 2018-01-14 | 2018-01-14 | COMP | 2018-03-10 | COMP | 2018-09-25 | COMP | 2019-08-30 | COMP | 2019-11-14 | COMP | Rule 16 | 151 | 228 | 38 | 139 | 235 | 53 | 841
970 | 2016-07-13 | 2017-02-16 | 2018-01-18 | 2018-01-18 | COMP | 2018-03-10 | COMP | 2018-09-25 | COMP | 2020-04-25 | INPR | 2019-11-12 | COMP | Rule 16 | 151 | 231 | 36 | 139 |  |  | 839
973 | 2016-07-13 | 2017-02-17 | 2018-01-16 | 2018-01-16 | COMP | 2018-05-11 | COMP | 2018-05-23 | COMP | 2019-10-16 | COMP | 2019-11-19 | COMP | Rule 16 | 152 | 228 | 83 | 9 | 353 | 24 | 844
1129 | 2016-07-13 | 2017-03-31 | 2017-05-03 | 2017-05-03 | COMP | 2017-06-26 | COMP | 2017-09-20 | COMP | 2019-08-30 | COMP | 2019-11-09 | COMP | Rule 16 | 181 | 24 | 38 | 61 | 489 | 50 | 838
1155 | 2016-07-13 | 2017-04-08 | 2017-05-11 | 2017-05-11 | COMP | 2017-07-13 | COMP | 2017-09-19 | COMP | 2020-06-09 | COMP | 2020-11-30 | COMP | Rule 16 | 186 | 24 | 44 | 48 | 683 | 121 | 1102
1157 | 2016-07-13 | 2017-04-09 | 2017-05-11 | 2017-05-11 | COMP | 2017-07-13 | COMP | 2017-09-19 | COMP | 2019-08-30 | COMP | 2020-01-07 | COMP | Rule 15/16 | 186 | 24 | 44 | 48 | 490 | 87 | 875
1158 | 2016-07-13 | 2017-04-09 | 2017-05-03 | 2017-05-03 | COMP | 2017-07-13 | COMP | 2017-08-22 | COMP | 2019-08-30 | COMP | 2019-10-01 | COMP | Rule 15/16 | 186 | 18 | 50 | 29 | 509 | 22 | 810
1702 | 2016-07-13 | 2017-07-18 | 2017-08-25 | 2017-08-25 | COMP | 2018-03-05 | COMP | 2018-06-19 | COMP | 2022-12-03 | INPR | 2020-12-01 | COMP | Rule 16 | 256 | 29 | 129 | 76 |  |  | 1103
2213 | 2016-07-13 | 2017-10-13 | 2018-01-29 | 2018-01-29 | COMP | 2018-05-01 | COMP | 2018-05-09 | COMP | 2020-09-23 | COMP | 2020-11-05 | COMP | Rule 16 | 318 | 71 | 66 | 7 | 599 | 32 | 1088
4242 | 2016-07-13 | 2019-10-14 | 2019-10-19 | 2019-10-19 | COMP | 2019-12-27 | COMP | 2020-01-13 | COMP | 2020-02-26 | COMP | 2020-03-16 | COMP | Rule 16 | 819 | 5 | 46 | 11 | 31 | 14 | 922
6940 | 2016-07-13 | 2018-09-18 | 2018-11-01 | 2018-11-01 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2018-12-20 | COMP | 2019-02-01 | COMP | Rule 15/16 | 550 | 33 | 32 | 1 | 2 | 29 | 642
568 | 2016-07-14 | 2016-08-05 | 2018-05-10 | 2018-05-10 | COMP | 2018-06-01 | COMP | 2018-06-22 | COMP | 2019-09-18 | COMP | 2019-10-03 | COMP | Rule 16 | 17 | 443 | 16 | 16 | 312 | 12 | 811
636 | 2016-07-14 | 2016-09-16 | 2016-11-14 | 2016-11-14 | COMP | 2016-11-15 | COMP | 2016-11-15 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | Rule 16 | 46 | 41 | 2 | 1 | 542 | 1 | 628
1806 | 2016-07-14 | 2017-07-31 | 2017-09-13 | 2017-09-13 | COMP | 2017-10-03 | COMP | 2017-10-03 | COMP | 2018-11-29 | COMP | 2019-01-22 | COMP | Rule 16 | 264 | 32 | 15 | 1 | 290 | 36 | 633
1850 | 2016-07-14 | 2017-08-09 | 2017-10-10 | 2017-10-10 | COMP | 2018-01-04 | COMP | 2018-01-05 | COMP | 2018-12-10 | COMP | 2019-07-17 | COMP | Rule 15/16 | 271 | 44 | 58 | 2 | 234 | 152 | 756
574 | 2016-07-15 | 2016-08-08 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-02-21 | COMP | 2020-03-17 | COMP | Rule 16 | 17 | 834 | 10 | 1 | 46 | 18 | 921
621 | 2016-07-15 | 2016-09-10 | 2016-11-21 | 2016-11-21 | COMP | 2018-05-22 | COMP | 2018-06-20 | COMP | 2019-08-31 | INPR | 2019-05-02 | COMP | Rule 16 | 40 | 50 | 377 | 21 |  |  | 703
639 | 2016-07-15 | 2016-09-19 | 2016-10-10 | 2016-10-10 | COMP | 2016-12-29 | COMP | 2016-12-29 | COMP | 2017-07-09 | COMP | 2019-05-13 | COMP | Rule 16 | 46 | 16 | 55 | 1 | 133 | 463 | 710
736 | 2016-07-15 | 2016-10-27 | 2017-10-02 | 2017-10-02 | COMP | 2018-04-30 | COMP | 2018-10-04 | COMP | 2019-08-20 | COMP | 2019-09-30 | COMP | Rule 15/16 | 74 | 234 | 144 | 111 | 220 | 29 | 807
1240 | 2016-07-15 | 2017-04-27 | 2017-09-19 | 2017-11-15 | COMP | 2018-01-03 | COMP | 2018-01-26 | COMP | 2019-11-23 | INPR | 2019-07-16 | COMP | Rule 15/16 | 198 | 101 | 32 | 17 |  |  | 754
578 | 2016-07-17 | 2016-08-11 | 2019-12-17 | 2019-12-17 | COMP | 2020-09-04 | COMP | 2021-03-09 | COMP | 2021-03-30 | COMP | 2021-04-24 | COMP | Rule 15/16 | 19 | 841 | 184 | 125 | 16 | 19 | 1199
754 | 2016-07-18 | 2016-11-08 | 2017-05-03 | 2018-04-16 | COMP | 2018-11-26 | COMP | 2018-12-03 | COMP | 2020-08-29 | INPR | 2019-03-12 | COMP | Rule 15/16 | 81 | 121 | 155 | 6 |  |  | 665
764 | 2016-07-18 | 2016-11-15 | 2017-04-03 | 2018-04-29 | COMP | 2018-05-31 | COMP | 2018-07-06 | COMP | 2018-07-06 | COMP | 2019-04-25 | COMP | Rule 16 | 85 | 95 | 23 | 26 | 1 | 202 | 697
583 | 2016-07-19 | 2016-08-15 | 2017-05-10 | 2017-05-10 | COMP | 2018-02-22 | COMP | 2018-02-22 | COMP | 2020-08-17 | COMP | 2020-10-19 | COMP | Rule 16 | 20 | 186 | 197 | 1 | 627 | 45 | 1071
662 | 2016-07-19 | 2016-09-28 | 2018-11-05 | 2018-11-05 | COMP | 2019-12-02 | COMP | 2019-12-10 | COMP | 2021-04-16 | COMP | 2021-06-12 | COMP | Rule 16 | 51 | 530 | 268 | 7 | 341 | 40 | 1232
683 | 2016-07-19 | 2016-10-09 | 2017-04-22 | 2018-09-10 | COMP | 2020-03-20 | COMP | 2020-06-02 | COMP | 2020-05-18 | COMP | 2020-10-30 | COMP | Rule 15/16 | 58 | 134 | 383 | 52 | 0 | 108 | 1080
1245 | 2016-07-19 | 2017-04-28 | 2017-08-21 | 2018-04-11 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2019-03-04 | COMP | 2019-04-20 | COMP | Rule 16 | 197 | 80 | 114 | 1 | 111 | 35 | 692
1499 | 2016-07-19 | 2017-06-10 | 2017-08-10 | 2019-05-10 | COMP | 2019-07-05 | COMP | 2018-10-29 | COMP | 2023-11-11 | INPR | 2019-10-18 | COMP | Rule 16 | 226 | 43 | 39 |  |  |  | 819
586 | 2016-07-20 | 2016-08-18 | 2017-05-16 | 2018-09-21 | COMP | 2019-03-27 | COMP | 2019-03-28 | COMP | 2019-04-15 | COMP | 2019-05-04 | COMP | Rule 15/16 | 22 | 187 | 127 | 2 | 13 | 15 | 701
587 | 2016-07-20 | 2016-08-18 | 2017-04-26 | 2019-02-05 | COMP | 2019-03-27 | COMP | 2019-03-28 | COMP | 2019-05-14 | COMP | 2019-06-08 | COMP | Rule 15/16 | 22 | 173 | 36 | 2 | 34 | 18 | 725
588 | 2016-07-20 | 2016-08-18 | 2017-08-05 | 2019-01-25 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-05-07 | COMP | 2019-06-11 | COMP | Rule 15/16 | 22 | 243 | 47 | 1 | 26 | 25 | 727
589 | 2016-07-20 | 2016-08-18 | 2017-10-17 | 2018-10-11 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-05-14 | COMP | 2019-06-11 | COMP | Rule 15/16 | 22 | 294 | 113 | 1 | 35 | 20 | 727
595 | 2016-07-20 | 2016-08-24 | 2018-03-08 | 2018-10-02 | COMP | 2018-12-21 | COMP | 2020-08-28 | COMP | 2020-04-02 | COMP | 2020-10-30 | COMP | Rule 15/16 | 26 | 385 | 56 | 426 | 0 | 45 | 1079
634 | 2016-07-20 | 2016-09-14 | 2016-10-17 | 2016-10-17 | COMP | 2016-11-28 | COMP | 2016-11-28 | INPR | 2019-07-21 | REQD | 2019-04-15 | COMP | Rule 15/16 | 40 | 24 | 28 |  |  |  | 687
865 | 2016-07-20 | 2017-01-05 | 2017-03-15 | 2017-03-15 | COMP | 2017-04-25 | COMP | 2017-04-25 | COMP | 2020-07-29 | COMP | 2020-11-06 | COMP | Rule 15/16 | 117 | 48 | 30 | 1 | 821 | 72 | 1084
894 | 2016-07-20 | 2017-01-23 | 2018-01-02 | 2018-01-02 | COMP | 2018-07-19 | COMP | 2019-03-11 | COMP | 2020-08-10 | COMP | 2020-11-08 | COMP | Rule 15/16 | 128 | 238 | 139 | 160 | 360 | 64 | 1084
924 | 2016-07-20 | 2017-02-02 | 2017-09-13 | 2019-01-17 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2019-12-19 | COMP | 2020-02-04 | COMP | Rule 16 | 136 | 156 | 230 | 1 | 4 | 31 | 889
3233 | 2016-07-20 | 2018-03-27 | 2018-07-27 | 2018-07-27 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-01-07 | COMP | 2019-01-24 | COMP | Rule 16 | 423 | 87 | 71 | 1 | 41 | 13 | 631
12702 | 2016-07-20 | 2019-06-18 | 2020-01-15 | 2020-02-06 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-05-12 | COMP | 2020-06-15 | COMP | Rule 16 | 732 | 145 | 14 | 1 | 55 | 24 | 981
1205 | 2016-07-21 | 2017-04-21 | 2017-05-17 | 2017-05-17 | COMP | 2018-03-30 | COMP | 2018-03-30 | COMP | 2019-05-31 | COMP | 2019-07-20 | COMP | Rule 16 | 190 | 19 | 218 | 1 | 295 | 35 | 753
2584 | 2016-07-21 | 2018-01-02 | 2018-12-07 | 2020-07-23 | COMP | 2020-08-26 | COMP | 2020-08-28 | COMP | 2020-08-26 | COMP | 2020-10-18 | COMP | Rule 15/16 | 364 | 236 | 25 | 3 | 0 | 35 | 1068
985 | 2016-07-22 | 2017-02-21 | 2017-02-28 | 2017-02-28 | COMP | 2017-07-28 | COMP | 2017-07-28 | COMP | 2019-03-01 | COMP | 2019-03-21 | COMP | Rule 16 | 146 | 6 | 107 | 1 | 398 | 15 | 668
2499 | 2016-07-22 | 2017-12-11 | 2018-04-12 | 2018-04-12 | COMP | 2018-05-07 | COMP | 2018-09-24 | COMP | 2018-11-08 | COMP | 2019-01-03 | COMP | Rule 16 | 349 | 85 | 18 | 98 | 34 | 36 | 615
717 | 2016-07-25 | 2016-10-22 | 2017-01-07 | 2017-01-07 | COMP | 2019-01-30 | COMP | 2018-12-19 | COMP | 2019-07-21 | INPR | 2019-03-21 | COMP | Rule 16 | 64 | 51 | 517 |  |  |  | 667
1221 | 2016-07-25 | 2017-04-25 | 2017-11-09 | 2017-11-09 | COMP | 2017-11-08 | COMP | 2018-12-19 | COMP | 2018-12-01 | COMP | 2019-01-24 | COMP | Rule 15/16 | 190 | 140 |  | 278 | 0 | 24 | 628
615 | 2016-07-26 | 2016-09-06 | 2017-04-17 | 2017-04-17 | COMP | 2018-01-03 | COMP | 2018-01-16 | COMP | 2020-10-23 | COMP | 2020-12-04 | COMP | Rule 15/16 | 30 | 154 | 180 | 9 | 701 | 28 | 1097
647 | 2016-07-26 | 2016-09-20 | 2017-05-25 | 2017-05-25 | COMP | 2017-02-21 | COMP | 2017-05-25 | COMP | 2019-03-02 | COMP | 2019-03-11 | COMP | Rule 16 | 40 | 172 |  | 68 | 442 | 6 | 658
689 | 2016-07-26 | 2016-10-12 | 2016-12-20 | 2016-12-20 | COMP | 2017-01-17 | COMP | 2017-05-05 | COMP |  |  | 2020-03-26 | COMP | Rule 16 | 56 | 47 | 19 | 78 |  |  | 921
952 | 2016-07-26 | 2017-02-13 | 2017-06-02 | 2017-06-02 | COMP | 2018-11-01 | NOTN | 2017-06-15 | INPR | 2020-03-21 | REQD | 2019-02-22 | COMP | Other | 139 | 78 |  |  |  |  | 647
1011 | 2016-07-26 | 2017-02-28 | 2018-02-23 | 2018-02-23 | COMP | 2018-06-12 | COMP | 2018-06-13 | COMP | 2019-01-26 | COMP | 2019-03-04 | COMP | Rule 15/16 | 149 | 249 | 77 | 2 | 155 | 25 | 653
2946 | 2016-07-26 | 2018-02-22 | 2018-11-02 | 2018-11-02 | COMP | 2019-01-09 | COMP | 2019-10-19 | REQD | 2019-10-19 | REQD | 2019-06-25 | COMP | Rule 15/16 | 396 | 179 | 44 |  |  |  | 733
7967 | 2016-07-26 | 2018-11-07 | 2019-03-30 | 2019-03-30 | COMP | 2019-06-03 | COMP | 2019-07-16 | COMP | 2020-03-21 | INPR | 2019-12-10 | COMP | Rule 15/16 | 577 | 96 | 45 | 31 |  |  | 848
5098 | 2016-07-27 | 2018-04-30 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-14 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2019-01-02 | COMP | Rule 16 | 442 | 113 | 27 | 2 | 1 | 31 | 611
635 | 2016-07-29 | 2016-09-16 | 2017-10-02 | 2017-10-02 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-10-04 | COMP | 2020-02-06 | COMP | Rule 15/16 | 35 | 263 | 509 | 1 | 0 | 80 | 884
732 | 2016-07-31 | 2016-10-26 | 2016-10-28 | 2016-10-28 | COMP | 2017-01-26 | COMP | 2017-01-27 | COMP | 2017-03-07 | COMP | 2019-03-21 | COMP | Rule 16 | 62 | 3 | 60 | 2 | 27 | 513 | 662
584 | 2016-08-01 | 2016-08-17 | 2017-01-17 | 2017-01-18 | COMP | 2017-04-28 | COMP | 2017-07-07 | COMP | 2020-04-25 | INPR | 2019-02-12 | COMP | Rule 16 | 13 | 104 | 72 | 49 |  |  | 636
1136 | 2016-08-01 | 2017-04-04 | 2017-05-23 | 2017-05-23 | COMP | 2017-08-02 | COMP | 2017-08-02 | COMP | 2020-01-07 | COMP | 2020-12-16 | COMP | Rule 16 | 170 | 36 | 50 | 1 | 609 | 240 | 1101
1176 | 2016-08-01 | 2017-04-13 | 2017-07-26 | 2019-03-26 | COMP | 2019-08-28 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-12-04 | COMP | Rule 16 | 177 | 73 | 110 | 5 | 1 | 63 | 840
3646 | 2016-08-01 | 2018-06-01 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-27 | COMP | 2021-02-10 | COMP | 2022-11-08 | COMP | 2022-11-23 | COMP | Rule 15/16 | 462 | 528 | 15 | 136 | 442 | 11 | 1589
9313 | 2016-08-01 | 2019-01-30 | 2019-03-31 | 2019-09-05 | COMP | 2019-09-12 | COMP | 2019-10-04 | COMP | 2019-09-18 | COMP | 2019-12-04 | COMP | Rule 16 | 627 | 42 | 6 | 17 | 0 | 41 | 840
9558 | 2016-08-01 | 2019-02-07 | 2019-04-16 | 2019-08-23 | COMP | 2019-09-12 | COMP | 2019-10-04 | COMP | 2019-10-01 | COMP | 2019-12-04 | COMP | Rule 16 | 633 | 48 | 14 | 17 | 0 | 41 | 840
1075 | 2016-08-02 | 2017-03-21 | 2017-06-08 | 2017-06-08 | COMP | 2017-07-19 | COMP | 2017-07-19 | COMP | 2022-09-24 | INPR | 2021-06-21 | COMP | Rule 16 | 159 | 57 | 29 | 1 |  |  | 1228
1123 | 2016-08-02 | 2017-03-30 | 2017-10-17 | 2017-10-17 | COMP | 2018-09-10 | COMP | 2019-04-23 | COMP | 2019-07-19 | COMP | 2019-08-24 | COMP | Rule 15/16 | 166 | 141 | 225 | 155 | 62 | 26 | 770
2082 | 2016-08-02 | 2017-09-20 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-19 | COMP | 2018-12-27 | COMP | 2019-08-30 | COMP | 2019-09-03 | COMP | Rule 16 | 287 | 280 | 14 | 26 | 172 | 2 | 776
2558 | 2016-08-02 | 2017-12-22 | 2018-07-26 | 2018-07-26 | COMP | 2020-06-12 | COMP | 2020-09-16 | COMP | 2022-01-29 | INPR | 2020-10-14 | COMP | Rule 16 | 351 | 149 | 473 | 68 |  |  | 1058
4032 | 2016-08-02 | 2018-12-17 | 2018-12-28 | 2018-12-28 | COMP | 2019-05-28 | COMP | 2019-07-02 | COMP | 2019-09-20 | COMP | 2019-10-18 | COMP | Rule 16 | 597 | 9 | 104 | 26 | 57 | 21 | 809
672 | 2016-08-03 | 2016-10-05 | 2016-10-19 | 2016-10-19 | COMP | 2017-03-10 | COMP | 2017-03-10 | COMP | 2017-10-26 | COMP | 2020-04-10 | COMP | Rule 16 | 45 | 11 | 97 | 1 | 162 | 615 | 926
3453 | 2016-08-03 | 2018-05-01 | 2018-06-20 | 2018-06-20 | COMP | 2018-10-18 | COMP | 2018-10-31 | COMP | 2019-08-06 | COMP | 2019-09-26 | COMP | Rule 16 | 438 | 36 | 85 | 10 | 191 | 37 | 792
4533 | 2016-08-03 | 2018-01-26 | 2018-10-03 | 2018-10-31 | COMP | 2020-05-19 | COMP | 2020-07-01 | COMP | 2020-05-01 | COMP | 2020-08-04 | COMP | Rule 15/16 | 372 | 175 | 388 | 31 | 0 | 25 | 1007
774 | 2016-08-04 | 2016-11-17 | 2016-12-01 | 2016-12-01 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-06-28 | COMP | 2019-08-06 | COMP | Rule 16 | 74 | 9 | 646 | 1 | 3 | 27 | 755
4169 | 2016-08-04 | 2019-05-16 | 2019-07-16 | 2019-07-16 | COMP | 2019-08-14 | COMP | 2019-11-07 | COMP | 2020-02-25 | COMP | 2020-09-27 | COMP | Rule 15/16 | 699 | 42 | 22 | 61 | 72 | 152 | 1043
9046 | 2016-08-04 | 2019-01-15 | 2019-02-26 | 2019-03-11 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-05-02 | COMP | 2020-07-02 | COMP | Rule 16 | 614 | 29 | 46 | 1 | 0 | 288 | 983
591 | 2016-08-05 | 2016-08-22 | 2016-09-27 | 2016-09-27 | COMP | 2016-10-07 | COMP | 2016-11-04 | COMP | 2020-02-29 | INPR | 2019-10-24 | COMP | Rule 15 | 12 | 26 | 9 | 21 |  |  | 810
602 | 2016-08-05 | 2016-09-02 | 2016-11-02 | 2016-10-14 | COMP | 2017-03-13 | NOTN | 2017-03-13 | COMP | 2020-02-26 | COMP | 2020-02-25 | COMP | Other | 21 | 43 |  | 101 | 743 |  | 891
606 | 2016-08-05 | 2016-08-31 | 2016-11-07 | 2016-11-07 | COMP |  |  |  |  | 2020-08-05 | COMP | 2021-03-04 | COMP | Other | 19 | 48 |  |  |  |  | 1149
607 | 2016-08-05 | 2016-08-31 | 2016-11-16 | 2016-11-16 | COMP | 2017-01-10 | COMP | 2018-07-09 | COMP | 2020-08-05 | COMP | 2020-08-11 | COMP | Other | 19 | 54 | 37 | 376 | 524 | 5 | 1010
627 | 2016-08-05 | 2016-09-12 | 2016-11-02 | 2016-11-02 | COMP |  |  |  |  | 2020-08-05 | COMP | 2021-03-04 | COMP | Other | 26 | 38 |  |  |  |  | 1149
638 | 2016-08-05 | 2016-09-17 | 2017-04-18 | 2017-04-18 | COMP | 2018-01-23 | COMP | 2018-01-29 | COMP | 2019-02-08 | COMP | 2019-03-15 | COMP | Rule 15/16 | 30 | 146 | 192 | 5 | 260 | 25 | 654
983 | 2016-08-05 | 2017-02-21 | 2018-03-30 | 2018-03-30 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-07-21 | COMP | 2020-07-31 | COMP | Rule 16 | 136 | 279 | 500 | 1 | 83 | 9 | 1003
1198 | 2016-08-05 | 2017-04-18 | 2017-09-21 | 2017-07-20 | COMP | 2021-07-29 | COMP | 2021-08-10 | COMP | 2021-07-26 | COMP | 2021-10-14 | COMP | Rule 16 | 176 | 110 | 1012 | 9 | 0 | 47 | 1306
1219 | 2016-08-05 | 2017-04-24 | 2018-03-19 | 2018-06-25 | COMP | 2018-10-17 | COMP | 2018-10-29 | COMP | 2018-11-26 | COMP | 2019-01-11 | COMP | Rule 15/16 | 180 | 226 | 81 | 9 | 18 | 33 | 611
1581 | 2016-08-05 | 2017-06-27 | 2017-09-19 | 2017-08-30 | COMP | 2017-11-22 | COMP | 2018-01-25 | COMP | 2019-12-02 | COMP | 2020-01-08 | COMP | Rule 16 | 225 | 59 | 59 | 42 | 466 | 26 | 859
1642 | 2016-08-05 | 2017-07-08 | 2018-08-06 | 2018-08-06 | COMP | 2022-04-01 | COMP | 2022-12-07 | COMP | 2022-12-07 | COMP | 2023-02-09 | COMP | Rule 16 | 232 | 271 | 920 | 172 | 1 | 44 | 1636
2599 | 2016-08-05 | 2018-01-05 | 2018-07-20 | 2018-07-20 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2023-02-25 | INPR | 2020-09-16 | COMP | Rule 16 | 356 | 137 | 487 | 1 |  |  | 1035
569 | 2016-08-06 | 2016-08-06 | 2016-08-31 | 2016-08-31 | COMP | 2016-09-14 | COMP | 2017-12-15 | NOTN | 2019-10-03 | COMP | 2019-10-08 | COMP | Rule 16 | 0 | 18 | 10 |  |  |  | 797
716 | 2016-08-07 | 2016-10-22 | 2018-03-12 | 2018-03-12 | COMP | 2018-07-30 | COMP | 2018-12-21 | COMP | 2019-10-23 | COMP | 2019-12-16 | COMP | Rule 16 | 54 | 345 | 99 | 101 | 212 | 36 | 843
842 | 2016-08-07 | 2016-12-16 | 2017-12-03 | 2021-02-26 | COMP | 2021-03-16 | COMP | 2021-03-16 | COMP | 2021-03-01 | COMP | 2021-04-23 | COMP | Rule 15/16 | 91 | 242 | 13 | 1 | 0 | 29 | 1184
864 | 2016-08-08 | 2017-01-05 | 2017-07-19 | 2017-07-19 | COMP | 2017-10-18 | COMP | 2018-08-17 | COMP | 2019-09-24 | COMP | 2019-11-12 | COMP | Rule 16 | 104 | 136 | 65 | 209 | 277 | 35 | 821
5766 | 2016-08-08 | 2018-07-02 | 2018-08-13 | 2018-09-07 | COMP | 2018-12-28 | COMP | 2019-01-03 | COMP | 2020-01-24 | COMP | 2020-03-16 | COMP | Rule 16 | 478 | 30 | 77 | 4 | 266 | 36 | 904
608 | 2016-08-09 | 2016-09-02 | 2017-06-05 | 2017-09-30 | COMP | 2017-11-06 | COMP | 2018-10-09 | COMP |  | INPR | 2019-03-22 | COMP | Rule 15/16 | 19 | 189 | 26 | 232 |  |  | 657
671 | 2016-08-09 | 2016-10-05 | 2017-04-28 | 2017-04-28 | COMP | 2018-04-18 | COMP | 2018-04-18 | COMP | 2019-10-15 | COMP | 2019-11-26 | COMP | Rule 16 | 41 | 142 | 244 | 1 | 377 | 30 | 830
735 | 2016-08-09 | 2016-10-27 | 2017-05-19 | 2017-05-19 | COMP | 2017-06-06 | COMP | 2018-01-03 | COMP | 2019-05-08 | COMP | 2019-06-25 | COMP | Rule 16 | 57 | 141 | 12 | 145 | 339 | 34 | 723
1298 | 2016-08-09 | 2017-05-05 | 2017-06-15 | 2017-06-15 | COMP | 2017-08-30 | COMP | 2017-12-07 | COMP | 2019-07-15 | COMP | 2019-08-13 | COMP | Rule 16 | 187 | 29 | 54 | 68 | 402 | 22 | 757
1639 | 2016-08-09 | 2017-07-08 | 2017-12-04 | 2017-12-04 | COMP | 2018-04-25 | COMP | 2019-02-19 | COMP | 2019-10-21 | INPR | 2019-05-31 | COMP | Rule 15/16 | 230 | 102 | 99 | 205 |  |  | 706
4108 | 2016-08-09 | 2019-02-11 | 2019-04-02 | 2019-04-02 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-06-13 | COMP | 2019-07-19 | COMP | Rule 16 | 629 | 36 | 34 | 1 | 19 | 26 | 740
599 | 2016-08-10 | 2016-08-26 | 2016-10-25 | 2016-10-25 | COMP | 2016-12-20 | COMP | 2017-01-26 | COMP | 2019-04-05 | COMP | 2019-05-07 | COMP | Rule 16 | 13 | 42 | 38 | 26 | 551 | 23 | 688
659 | 2016-08-10 | 2016-09-28 | 2017-04-26 | 2017-04-26 | COMP | 2017-06-12 | COMP | 2017-06-12 | COMP | 2022-07-16 | INPR | 2021-02-25 | COMP | Rule 15/16 | 35 | 145 | 33 | 1 |  |  | 1141
740 | 2016-08-10 | 2016-10-31 | 2018-01-16 | 2018-05-29 | COMP | 2018-10-31 | COMP | 2018-11-13 | COMP | 2019-12-28 | INPR | 2019-01-30 | COMP | Rule 16 | 58 | 302 | 110 | 9 |  |  | 620
767 | 2016-08-10 | 2016-11-15 | 2017-08-05 | 2018-09-07 | COMP | 2018-09-13 | COMP | 2018-09-13 | COMP | 2018-09-07 | COMP | 2020-02-05 | COMP | Rule 15/16 | 68 | 182 | 5 | 1 | 0 | 349 | 875
830 | 2016-08-10 | 2016-12-12 | 2017-01-26 | 2017-01-26 | COMP | 2017-04-04 | COMP | 2018-07-03 | COMP | 2020-01-07 | COMP | 2020-02-03 | COMP | Rule 16 | 85 | 32 | 48 | 315 | 379 | 19 | 873
1566 | 2016-08-10 | 2017-06-23 | 2018-09-19 | 2018-09-19 | COMP | 2018-12-17 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-04 | COMP | Rule 16 | 220 | 312 | 61 | 4 | 1 | 10 | 603
1589 | 2016-08-10 | 2017-06-28 | 2017-11-01 | 2017-11-01 | COMP | 2018-07-12 | COMP | 2018-08-08 | COMP | 2019-02-05 | COMP | 2019-03-01 | COMP | Rule 16 | 223 | 89 | 173 | 20 | 123 | 18 | 641
1800 | 2016-08-10 | 2017-07-28 | 2017-09-11 | 2017-09-11 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2019-12-09 | COMP | 2019-12-19 | COMP | Rule 16 | 244 | 31 | 253 | 1 | 311 | 9 | 844
1079 | 2016-08-11 | 2017-03-22 | 2017-05-03 | 2017-05-03 | COMP | 2017-11-20 | COMP | 2017-07-06 | COMP | 2021-08-12 | COMP | 2023-04-22 | COMP | Rule 15/16 | 153 | 31 | 140 |  | 1032 | 425 | 1682
640 | 2016-08-12 | 2016-09-20 | 2018-01-24 | 2018-01-24 | COMP | 2018-03-10 | COMP | 2018-11-01 | COMP | 2019-07-21 | COMP | 2019-04-30 | COMP | Rule 16 | 27 | 337 | 32 | 166 | 178 |  | 681
766 | 2016-08-12 | 2016-11-15 | 2017-02-03 | 2017-02-03 | COMP | 2017-05-11 | COMP | 2017-05-20 | COMP | 2019-06-29 | INPR | 2019-02-07 | COMP | Rule 16 | 66 | 55 | 69 | 7 |  |  | 624
839 | 2016-08-12 | 2016-12-15 | 2017-01-29 | 2017-01-29 | COMP | 2017-12-11 | COMP | 2018-04-20 | COMP | 2020-01-21 | COMP | 2020-02-05 | COMP | Rule 16 | 86 | 30 | 219 | 91 | 439 | 12 | 873
1592 | 2016-08-12 | 2017-06-28 | 2017-09-16 | 2017-09-16 | COMP | 2018-02-20 | COMP | 2018-02-20 | COMP | 2018-01-10 | COMP | 2020-01-27 | COMP | Rule 16 | 221 | 56 | 105 | 1 | 0 | 486 | 866
620 | 2016-08-15 | 2016-09-09 | 2016-10-31 | 2016-10-31 | COMP | 2018-04-25 | COMP | 2018-04-26 | COMP | 2019-07-19 | COMP | 2019-08-21 | COMP | Rule 16 | 19 | 37 | 372 | 2 | 310 | 24 | 759
687 | 2016-08-15 | 2016-10-11 | 2017-01-23 | 2017-01-23 | COMP | 2017-05-30 | COMP | 2017-05-31 | COMP | 2018-12-03 | COMP | 2019-02-05 | COMP | Rule 16 | 41 | 70 | 90 | 2 | 379 | 44 | 621
1809 | 2016-08-15 | 2017-08-01 | 2018-02-15 | 2018-02-15 | COMP | 2018-06-11 | COMP | 2020-02-26 | COMP | 2020-07-07 | COMP | 2020-08-15 | COMP | Rule 15/16 | 243 | 136 | 81 | 429 | 94 | 29 | 1007
5552 | 2016-08-15 | 2018-06-13 | 2018-08-15 | 2018-08-15 | COMP | 2019-02-15 | COMP | 2019-02-15 | COMP | 2023-04-30 | INPR | 2019-06-06 | COMP | Rule 16 | 460 | 45 | 126 | 1 |  |  | 706
623 | 2016-08-16 | 2016-09-12 | 2017-01-31 | 2017-01-10 | COMP | 2017-01-31 | COMP | 2017-01-31 | COMP | 2019-08-13 | COMP | 2019-09-09 | COMP | Rule 16 | 19 | 97 | 15 | 1 | 638 | 19 | 770
641 | 2016-08-16 | 2016-09-20 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-31 | COMP | 2019-03-22 | COMP | 2019-11-14 | COMP | 2019-06-06 | COMP | Rule 16 | 25 | 565 | 29 | 36 | 166 |  | 705
642 | 2016-08-16 | 2016-09-20 | 2018-11-29 | 2018-11-19 | COMP | 2018-12-17 | COMP | 2019-06-06 | COMP | 2019-08-27 | COMP | 2019-08-26 | COMP | Rule 16 | 25 | 551 | 19 | 119 | 58 |  | 761
643 | 2016-08-16 | 2016-09-20 | 2018-12-12 | 2018-11-27 | COMP | 2018-12-17 | COMP | 2019-03-07 | COMP | 2019-11-14 | COMP | 2022-04-20 | COMP | Rule 16 | 25 | 560 | 15 | 55 | 177 | 612 | 1428
680 | 2016-08-16 | 2016-10-06 | 2016-11-30 | 2016-11-30 | COMP | 2018-05-16 | COMP | 2018-06-11 | COMP | 2019-09-10 | COMP | 2019-12-12 | COMP | Rule 16 | 37 | 37 | 368 | 18 | 315 | 65 | 835
907 | 2016-08-16 | 2017-01-27 | 2017-05-24 | 2017-05-24 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP |  | INPR | 2021-04-09 | COMP | Rule 15/16 | 113 | 83 | 388 | 1 |  |  | 1168
1130 | 2016-08-16 | 2017-04-01 | 2018-06-10 | 2018-06-10 | COMP | 2018-06-15 | COMP | 2018-08-13 | COMP | 2019-07-26 | COMP | 2019-11-20 | COMP | Rule 15/16 | 157 | 299 | 5 | 41 | 240 | 82 | 821
1170 | 2016-08-16 | 2017-04-13 | 2017-07-31 | 2017-07-31 | COMP | 2018-09-19 | COMP | 2017-09-05 | COMP | 2019-01-15 | COMP | 2019-12-23 | COMP | Rule 16 | 166 | 76 | 287 |  | 341 | 237 | 842
630 | 2016-08-17 | 2016-09-13 | 2018-09-11 | 2018-09-11 | COMP | 2019-01-09 | COMP | 2019-07-24 | INPR | 2019-06-06 | COMP | 2019-08-07 | COMP | Rule 16 | 19 | 502 | 82 |  |  |  | 747
780 | 2016-08-17 | 2016-11-23 | 2018-01-07 | 2018-01-07 | COMP | 2018-08-08 | COMP | 2019-09-04 | COMP | 2020-01-07 | COMP | 2020-01-30 | COMP | Rule 16 | 69 | 280 | 149 | 270 | 85 | 17 | 866
818 | 2016-08-17 | 2016-12-09 | 2017-03-17 | 2017-03-17 | COMP | 2018-03-27 | COMP | 2018-03-28 | COMP | 2019-04-24 | COMP | 2019-06-24 | COMP | Rule 16 | 79 | 68 | 258 | 2 | 271 | 43 | 716
897 | 2016-08-17 | 2017-01-23 | 2017-09-19 | 2020-03-08 | COMP | 2020-05-04 | COMP | 2018-01-17 | COMP | 2020-06-16 | COMP | 2020-07-10 | COMP | Rule 15/16 | 108 | 168 | 41 |  | 608 | 19 | 980
1211 | 2016-08-18 | 2017-04-21 | 2018-04-03 | 2018-04-03 | COMP | 2018-06-05 | COMP | 2018-06-05 | COMP | 2022-06-18 | INPR | 2020-08-10 | COMP | Rule 15/16 | 170 | 238 | 45 | 1 |  |  | 1000
1548 | 2016-08-18 | 2017-06-21 | 2017-09-19 | 2017-09-19 | COMP | 2017-06-21 | NOTN | 2018-03-16 | COMP | 2018-03-16 | COMP | 2019-10-02 | COMP | Other | 212 | 63 |  | 122 | 1 | 391 | 785
3123 | 2016-08-18 | 2018-03-12 | 2018-03-21 | 2018-05-22 | COMP | 2021-01-19 | COMP | 2021-02-19 | COMP | 2021-06-01 | COMP | 2021-08-24 | COMP | Rule 15/16 | 391 | 8 | 668 | 23 | 72 | 60 | 1261
24745 | 2016-08-18 | 2021-01-11 | 2021-08-12 | 2021-08-12 | COMP | 2021-10-25 | COMP | 2022-07-27 | COMP | 2022-08-09 | COMP | 2022-10-05 | COMP | Rule 15/16 | 1104 | 150 | 52 | 190 | 10 | 41 | 1542
661 | 2016-08-19 | 2016-09-28 | 2017-02-07 | 2017-02-07 | COMP | 2018-08-23 | COMP | 2019-01-09 | COMP | 2019-08-05 | COMP | 2019-07-16 | COMP | Rule 15/16 | 28 | 90 | 390 | 94 | 145 |  | 729
669 | 2016-08-19 | 2016-10-01 | 2016-10-12 | 2016-10-12 | COMP | 2016-10-19 | COMP | 2016-10-21 | COMP | 2016-11-28 | COMP | 2021-12-22 | COMP | Rule 16 | 30 | 8 | 6 | 3 | 24 | 1275 | 1342
795 | 2016-08-22 | 2016-12-01 | 2017-06-23 | 2017-06-23 | COMP | 2020-01-15 | COMP | 2020-01-22 | COMP | 2020-02-25 | COMP | 2020-06-02 | COMP | Rule 16 | 70 | 143 | 642 | 5 | 24 | 70 | 949
4007 | 2016-08-22 | 2018-11-26 | 2018-11-27 | 2018-11-27 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-09-21 | INPR | 2019-06-13 | COMP | Other | 568 | 2 | 119 | 1 |  |  | 706
688 | 2016-08-23 | 2016-10-11 | 2019-07-12 | 2021-03-30 | COMP | 2019-12-13 | COMP | 2020-02-12 | COMP | 2020-10-05 | COMP | 2021-02-05 | COMP | Rule 16 | 35 | 691 |  | 41 | 166 | 84 | 1119
984 | 2016-08-23 | 2017-02-21 | 2017-04-04 | 2021-02-23 | COMP | 2021-03-15 | COMP |  | REQD | 2021-03-31 | COMP | 2021-05-13 | COMP | Rule 16 | 124 | 31 | 15 |  |  |  | 1187
3209 | 2016-08-23 | 2018-03-22 | 2019-08-08 | 2019-08-08 | COMP | 2021-05-27 | COMP | 2021-11-10 | COMP | 2023-01-28 | INPR | 2021-11-29 | COMP | Rule 16 | 396 | 349 | 454 | 117 |  |  | 1323
829 | 2016-08-24 | 2016-12-13 | 2017-07-05 | 2017-07-05 | COMP | 2018-04-16 | COMP | 2018-05-29 | COMP | 2020-05-31 | INPR | 2019-11-17 | COMP | Rule 15/16 | 76 | 142 | 196 | 31 |  |  | 812
913 | 2016-08-24 | 2017-01-29 | 2017-05-11 | 2017-05-11 | COMP | 2019-08-30 | COMP | 2017-06-26 | COMP | 2020-03-24 | COMP | 2020-06-09 | COMP | Rule 15/16 | 107 | 73 | 580 |  | 688 | 55 | 952
915 | 2016-08-24 | 2017-01-29 | 2017-05-05 | 2017-05-05 | COMP | 2017-06-20 | COMP | 2017-06-20 | COMP | 2019-10-16 | COMP | 2019-12-12 | COMP | Rule 16 | 107 | 69 | 32 | 1 | 585 | 39 | 829
965 | 2016-08-24 | 2017-02-16 | 2017-05-20 | 2018-09-12 | COMP | 2019-03-27 | COMP | 2019-04-04 | COMP | 2019-08-30 | COMP | 2019-10-03 | COMP | Other | 121 | 66 | 134 | 7 | 105 | 24 | 782
966 | 2016-08-24 | 2017-02-16 | 2017-05-20 | 2018-04-24 | COMP | 2018-05-11 | COMP | 2018-05-15 | COMP | 2019-03-25 | COMP | 2019-04-13 | COMP | Rule 16 | 121 | 66 | 14 | 3 | 215 | 15 | 661
969 | 2016-08-24 | 2017-02-16 | 2018-01-16 | 2018-01-16 | COMP | 2018-03-02 | COMP | 2018-08-22 | COMP | 2021-02-27 | INPR | 2019-11-12 | COMP | Rule 16 | 121 | 229 | 33 | 122 |  |  | 809
971 | 2016-08-24 | 2017-02-16 | 2018-01-14 | 2018-01-14 | COMP | 2018-03-02 | COMP | 2018-04-05 | COMP | 2019-02-12 | COMP | 2019-03-14 | COMP | Rule 15/16 | 121 | 228 | 33 | 25 | 215 | 22 | 640
972 | 2016-08-24 | 2017-02-17 | 2018-01-14 | 2018-01-14 | COMP | 2018-03-01 | COMP | 2019-07-03 | COMP | 2019-10-16 | COMP | 2019-11-19 | COMP | Rule 16 | 122 | 227 | 32 | 339 | 74 | 24 | 814
989 | 2016-08-24 | 2017-02-22 | 2018-01-14 | 2018-01-14 | COMP | 2018-03-02 | COMP | 2019-03-01 | COMP | 2019-08-30 | COMP | 2019-10-03 | COMP | Rule 16 | 124 | 225 | 33 | 251 | 129 | 24 | 782
1128 | 2016-08-24 | 2017-03-31 | 2017-04-29 | 2017-04-29 | COMP | 2017-06-23 | COMP | 2017-09-01 | COMP | 2019-08-30 | COMP | 2019-10-20 | COMP | Rule 16 | 151 | 21 | 39 | 50 | 501 | 35 | 793
1156 | 2016-08-24 | 2017-04-09 | 2017-05-11 | 2017-05-11 | COMP | 2017-07-13 | COMP | 2017-09-12 | COMP | 2019-08-30 | COMP | 2020-01-08 | COMP | Rule 16 | 156 | 24 | 44 | 43 | 495 | 88 | 846
1400 | 2016-08-24 | 2017-05-26 | 2018-03-21 | 2018-03-21 | COMP | 2018-05-25 | COMP | 2018-10-26 | COMP | 2019-05-17 | COMP | 2019-06-19 | COMP | Rule 15/16 | 191 | 204 | 48 | 108 | 139 | 23 | 708
2214 | 2016-08-24 | 2017-10-13 | 2018-01-26 | 2018-01-26 | COMP | 2018-04-12 | COMP | 2018-04-13 | COMP | 2020-09-23 | COMP | 2020-11-05 | COMP | Rule 15/16 | 288 | 70 | 54 | 2 | 617 | 32 | 1058
20684 | 2016-08-24 | 2020-07-01 | 2020-08-19 | 2020-08-19 | COMP | 2020-08-26 | COMP | 2022-01-25 | COMP | 2023-04-10 | COMP | 2023-05-31 | COMP | Rule 16 | 968 | 36 | 6 | 355 | 303 | 37 | 1700
700 | 2016-08-25 | 2016-10-19 | 2017-02-16 | 2017-02-16 | COMP | 2017-05-22 | COMP | 2017-05-22 | COMP | 2019-04-05 | COMP | 2019-07-26 | COMP | Rule 16 | 39 | 82 | 67 | 1 | 470 | 79 | 733
1137 | 2016-08-25 | 2017-04-04 | 2017-11-13 | 2017-11-13 | COMP | 2017-12-11 | NOTN | 2017-12-11 | COMP | 2018-03-22 | COMP | 2019-04-04 | COMP | Other | 152 | 156 |  | 19 | 70 | 261 | 654
1185 | 2016-08-25 | 2017-04-17 | 2017-10-22 | 2019-09-09 | COMP | 2019-09-18 | COMP | 2019-10-01 | COMP | 2019-09-17 | COMP | 2022-08-25 | COMP | Rule 15/16 | 161 | 132 | 8 | 10 | 0 | 731 | 1509
2346 | 2016-08-25 | 2017-11-08 | 2018-05-30 | 2018-05-30 | COMP | 2019-04-16 | COMP | 2019-04-18 | COMP | 2019-07-23 | COMP | 2019-08-24 | COMP | Rule 15/16 | 305 | 138 | 221 | 3 | 67 | 24 | 753
4429 | 2016-08-25 | 2017-12-07 | 2018-01-04 | 2019-06-11 | COMP | 2019-06-25 | COMP | 2019-08-22 | COMP | 2019-08-19 | COMP | 2019-12-11 | COMP | Rule 16 | 323 | 19 | 11 | 42 | 0 | 76 | 827
782 | 2016-08-26 | 2016-11-23 | 2017-01-07 | 2017-01-07 | COMP | 2016-12-29 | COMP | 2017-01-05 | COMP | 2017-03-28 | COMP | 2020-07-15 | COMP | Rule 16 | 62 | 30 |  | 6 | 57 | 831 | 976
783 | 2016-08-26 | 2016-11-23 | 2018-12-07 | 2018-12-07 | COMP | 2019-03-28 | COMP | 2019-03-29 | COMP | 2019-09-18 | COMP | 2019-10-02 | COMP | Rule 15/16 | 62 | 512 | 76 | 2 | 121 | 11 | 779
1513 | 2016-08-26 | 2017-06-14 | 2017-12-28 | 2017-12-28 | COMP | 2018-05-25 | COMP | 2019-08-09 | COMP | 2019-08-30 | COMP | 2019-09-17 | COMP | Rule 15/16 | 201 | 136 | 104 | 304 | 16 | 12 | 768
1142 | 2016-08-27 | 2017-04-05 | 2017-07-19 | 2018-06-18 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2020-05-30 | INPR | 2019-04-29 | COMP | Rule 16 | 151 | 74 | 156 | 1 |  |  | 669
821 | 2016-08-29 | 2016-12-09 | 2017-10-02 | 2017-10-02 | COMP | 2018-08-22 | COMP | 2018-08-28 | COMP | 2019-10-18 | COMP | 2020-06-17 | COMP | Rule 15/16 | 71 | 206 | 224 | 5 | 288 | 166 | 955
862 | 2016-08-29 | 2017-01-03 | 2018-04-24 | 2020-08-05 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-09-21 | COMP | 2020-10-30 | COMP | Rule 16 | 87 | 329 | 50 | 1 | 0 | 13 | 1051
4857 | 2016-08-29 | 2018-04-06 | 2018-06-10 | 2018-06-10 | COMP | 2018-08-23 | COMP | 2018-08-23 | COMP | 2020-01-02 | COMP | 2020-01-13 | COMP | Rule 16 | 403 | 45 | 53 | 1 | 340 | 8 | 846
6717 | 2016-08-29 | 2018-09-11 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-10-21 | INPR | 2019-04-17 | COMP | Rule 16 | 512 | 62 | 6 | 1 |  |  | 661
40245 | 2016-08-29 | 2022-12-14 | 2023-05-30 | 2023-05-30 | COMP | 2023-06-19 | NOTN | 2023-08-07 | COMP | 2023-07-21 | COMP | 2023-09-11 | COMP | Other | 1582 | 115 |  | 48 | 0 | 25 | 1767
673 | 2016-08-30 | 2016-10-05 | 2017-08-05 | 2017-08-05 | COMP | 2018-08-22 | COMP | 2021-05-04 | COMP | 2021-03-01 | COMP | 2021-06-07 | COMP | Rule 15/16 | 26 | 210 | 263 | 678 | 0 | 24 | 1198
744 | 2016-08-30 | 2016-11-02 | 2018-03-08 | 2018-03-08 | COMP |  | REQD | 2018-06-22 | COMP | 2019-01-10 | COMP | 2019-09-21 | COMP | Rule 15/16 | 46 | 336 |  | 76 | 138 | 177 | 769
843 | 2016-08-30 | 2016-12-16 | 2017-10-25 | 2017-10-25 | COMP | 2018-07-05 | COMP | 2018-07-12 | COMP | 2018-10-25 | COMP | 2019-03-19 | COMP | Rule 16 | 75 | 218 | 173 | 6 | 75 | 97 | 639
1028 | 2016-08-30 | 2017-03-03 | 2017-06-23 | 2017-06-23 | COMP | 2018-05-15 | COMP | 2018-05-15 | COMP | 2019-04-10 | COMP | 2019-06-26 | COMP | Rule 15/16 | 127 | 80 | 224 | 1 | 227 | 55 | 709
1039 | 2016-08-30 | 2017-03-07 | 2017-08-23 | 2019-11-20 | COMP | 2020-12-31 | COMP | 2021-01-06 | COMP | 2021-09-07 | COMP | 2021-10-22 | COMP | Rule 16 | 129 | 120 | 280 | 4 | 170 | 34 | 1295
1764 | 2016-08-30 | 2017-07-21 | 2017-09-16 | 2017-09-16 | COMP | 2017-12-01 | COMP | 2017-12-01 | COMP | 2019-10-23 | COMP | 2019-12-20 | COMP | Rule 16 | 225 | 40 | 52 | 1 | 477 | 40 | 831
1959 | 2016-08-30 | 2017-08-27 | 2017-11-08 | 2017-10-27 | COMP | 2019-05-17 | COMP | 2019-05-21 | COMP | 2019-06-24 | COMP | 2019-10-14 | COMP | Rule 16 | 250 | 52 | 389 | 3 | 24 | 79 | 785
6208 | 2016-08-30 | 2018-08-03 | 2018-10-31 | 2018-10-31 | COMP | 2019-01-31 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-06-07 | COMP | Rule 15/16 | 485 | 63 | 61 | 50 | 1 | 41 | 696
718 | 2016-08-31 | 2016-10-24 | 2017-02-16 | 2017-02-16 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2019-01-08 | COMP | 2019-02-08 | COMP | Rule 15/16 | 38 | 79 | 183 | 1 | 293 | 23 | 612
1069 | 2016-08-31 | 2017-03-20 | 2017-06-26 | 2017-06-26 | COMP | 2019-03-06 | COMP | 2017-09-07 | COMP |  | INPR | 2019-01-15 | COMP | Rule 15/16 | 137 | 70 | 424 |  |  |  | 595
1222 | 2016-08-31 | 2017-04-25 | 2018-07-24 | 2018-07-20 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2020-09-21 | COMP | 2020-11-12 | COMP | Rule 16 | 163 | 314 | 51 | 1 | 497 | 38 | 1057
651 | 2016-09-01 | 2016-09-27 | 2017-11-15 | 2018-09-27 | COMP | 2019-01-15 | COMP | 2019-02-26 | COMP |  | REQD | 2019-04-24 | COMP | Rule 15/16 | 18 | 287 | 74 | 29 |  |  | 663
1022 | 2016-09-01 | 2017-03-02 | 2017-12-08 | 2020-07-03 | COMP | 2020-07-15 | COMP | 2020-09-16 | COMP | 2020-10-28 | COMP | 2020-11-06 | COMP | Rule 15/16 | 124 | 196 | 9 | 45 | 31 | 8 | 1053
734 | 2016-09-02 | 2016-10-26 | 2018-05-01 | 2019-02-13 | COMP | 2019-03-18 | COMP | 2019-03-27 | COMP | 2019-07-18 | COMP | 2019-11-22 | COMP | Rule 15/16 | 38 | 379 | 23 | 8 | 80 | 90 | 810
773 | 2016-09-02 | 2016-11-17 | 2017-02-18 | 2017-02-18 | COMP | 2019-07-10 | COMP | 2017-11-06 | COMP | 2019-07-11 | COMP | 2019-09-20 | COMP | Rule 15/16 | 53 | 63 | 600 |  | 420 | 51 | 766
2016 | 2016-09-02 | 2017-09-07 | 2018-03-06 | 2018-03-06 | COMP | 2019-01-16 | COMP | 2021-09-22 | COMP | 2021-09-03 | COMP | 2021-11-30 | COMP | Rule 15/16 | 255 | 122 | 219 | 677 | 0 | 47 | 1316
2391 | 2016-09-02 | 2017-11-16 | 2018-03-07 | 2018-10-11 | COMP | 2019-08-31 | INPR | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-03-14 | COMP | Rule 16 | 304 | 74 |  | 64 | 1 | 41 | 633
4416 | 2016-09-02 | 2017-11-27 | 2018-02-20 | 2018-02-20 | COMP | 2018-06-19 | COMP | 2018-06-19 | COMP | 2019-05-16 | COMP | 2019-06-19 | COMP | Rule 16 | 309 | 58 | 85 | 1 | 229 | 24 | 701
5707 | 2016-09-02 | 2018-06-27 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-07-21 | INPR | 2019-03-19 | COMP | Rule 16 | 456 | 76 | 26 | 1 |  |  | 636
619 | 2016-09-06 | 2016-09-09 | 2017-02-04 | 2017-02-04 | COMP | 2020-03-08 | NOTN | 2018-04-06 | COMP | 2019-01-14 | COMP | 2019-06-03 | COMP | Rule 15/16 | 4 | 101 |  | 294 | 194 | 98 | 688
712 | 2016-09-06 | 2016-10-21 | 2016-11-20 | 2016-11-20 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-01-16 | COMP | Rule 16 | 34 | 20 | 522 | 1 | 1 | 19 | 593
917 | 2016-09-06 | 2017-02-01 | 2018-04-16 | 2018-04-16 | COMP | 2018-05-14 | COMP | 2018-12-27 | COMP | 2019-02-07 | COMP | 2019-03-26 | COMP | Rule 15/16 | 102 | 303 | 21 | 157 | 29 | 33 | 640
2459 | 2016-09-06 | 2017-12-05 | 2018-04-05 | 2018-07-06 | COMP | 2018-07-10 | COMP | 2018-07-10 | COMP |  | INPR | 2022-05-18 | COMP | Rule 16 | 314 | 84 | 3 | 1 |  |  | 1434
4820 | 2016-09-06 | 2018-04-01 | 2018-08-16 | 2018-08-16 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-10-21 | INPR | 2019-07-12 | COMP | Rule 16 | 393 | 97 | 58 | 1 |  |  | 716
2388 | 2016-09-07 | 2017-11-15 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2020-11-21 | INPR | 2019-10-23 | COMP | Rule 16 | 301 | 313 | 20 | 1 |  |  | 787
3024 | 2016-09-07 | 2018-02-27 | 2018-09-11 | 2018-09-11 | COMP | 2018-12-04 | COMP | 2019-02-06 | COMP | 2019-11-15 | COMP | 2021-03-11 | COMP | Rule 15/16 | 369 | 138 | 58 | 44 | 198 | 330 | 1132
617 | 2016-09-08 | 2016-09-08 | 2018-02-20 | 2018-02-20 | COMP | 2020-01-27 | COMP | 2020-02-21 | INPR | 2020-02-18 | COMP | 2020-03-13 | COMP | Rule 15/16 | 1 | 363 | 486 |  |  |  | 881
654 | 2016-09-08 | 2016-09-27 | 2017-06-19 | 2017-06-19 | COMP | 2017-06-27 | COMP | 2017-06-27 | COMP | 2017-08-10 | COMP | 2020-01-28 | COMP | Rule 16 | 14 | 183 | 7 | 1 | 32 | 617 | 849
685 | 2016-09-08 | 2016-10-11 | 2016-11-07 | 2016-11-07 | COMP |  |  |  |  | 2017-06-08 | COMP | 2022-07-21 | COMP | Other | 24 | 20 |  |  |  |  | 1475
696 | 2016-09-08 | 2016-10-15 | 2017-04-30 | 2017-04-30 | COMP | 2018-08-28 | COMP | 2018-09-27 | COMP | 2019-03-01 | COMP | 2019-03-08 | COMP | Rule 15/16 | 27 | 134 | 335 | 22 | 105 | 6 | 626
749 | 2016-09-08 | 2016-11-04 | 2016-11-30 | 2016-11-30 | COMP | 2017-02-07 | COMP | 2017-02-13 | COMP | 2018-02-14 | COMP | 2019-12-09 | COMP | Rule 16 | 42 | 16 | 48 | 5 | 253 | 457 | 816
784 | 2016-09-08 | 2016-11-23 | 2017-07-10 | 2017-07-10 | COMP | 2018-08-20 | COMP | 2019-01-04 | COMP | 2021-02-28 | INPR | 2019-04-04 | COMP | Rule 15/16 | 54 | 157 | 281 | 94 |  |  | 645
2004 | 2016-09-08 | 2017-09-06 | 2018-05-30 | 2018-05-30 | COMP | 2018-11-14 | COMP | 2019-07-09 | COMP | 2019-09-03 | COMP | 2019-09-12 | COMP | Rule 15/16 | 251 | 183 | 118 | 162 | 40 | 8 | 757
708 | 2016-09-09 | 2016-10-20 | 2017-07-10 | 2017-07-10 | COMP | 2018-05-23 | COMP | 2018-05-23 | COMP | 2020-01-07 | COMP | 2020-02-07 | COMP | Rule 16 | 30 | 180 | 220 | 1 | 407 | 23 | 856
758 | 2016-09-09 | 2016-11-10 | 2017-04-11 | 2018-07-14 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2018-11-19 | COMP | 2019-01-16 | COMP | Rule 16 | 45 | 103 | 69 | 1 | 21 | 39 | 590
949 | 2016-09-09 | 2017-02-10 | 2017-06-20 | 2017-06-20 | COMP | 2018-12-18 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-04-30 | COMP | Rule 15/16 | 106 | 91 | 376 | 59 | 1 | 34 | 662
1040 | 2016-09-09 | 2017-03-08 | 2017-09-05 | 2017-09-05 | COMP | 2018-10-11 | COMP | 2018-10-11 | COMP | 2020-07-06 | COMP | 2020-07-29 | COMP | Rule 15/16 | 123 | 127 | 278 | 1 | 435 | 18 | 977
1619 | 2016-09-09 | 2017-07-05 | 2019-06-05 | 2021-02-03 | COMP | 2021-03-08 | COMP | 2021-05-12 | COMP | 2021-04-08 | NOTN | 2021-05-14 | COMP | Rule 16 | 206 | 482 | 23 | 48 |  |  | 1176
2891 | 2016-09-09 | 2018-02-12 | 2018-04-29 | 2018-04-29 | COMP | 2018-06-07 | COMP | 2018-06-07 | COMP | 2019-05-10 | COMP | 2019-05-30 | COMP | Rule 16 | 357 | 54 | 28 | 1 | 233 | 14 | 683
656 | 2016-09-12 | 2016-09-27 | 2016-10-28 | 2017-08-28 | COMP | 2017-09-18 | COMP | 2017-09-18 | COMP | 2019-10-19 | INPR | 2019-07-02 | COMP | Rule 16 | 12 | 24 | 15 | 1 |  |  | 705
682 | 2016-09-12 | 2016-10-07 | 2016-11-03 | 2016-11-03 | COMP | 2017-09-06 | COMP | 2018-04-19 | COMP | 2019-05-09 | COMP | 2019-06-28 | COMP | Rule 16 | 20 | 20 | 211 | 155 | 266 | 36 | 703
1059 | 2016-09-12 | 2017-03-16 | 2017-04-18 | 2017-04-18 | COMP | 2017-05-10 | COMP | 2017-05-25 | COMP | 2018-12-18 | COMP | 2019-01-11 | COMP | Rule 16 | 128 | 24 | 17 | 12 | 393 | 17 | 586
1098 | 2016-09-12 | 2017-03-25 | 2017-09-21 | 2017-09-21 | COMP | 2018-09-14 | COMP | 2018-09-28 | COMP | 2020-09-17 | COMP | 2019-02-22 | COMP | Rule 15/16 | 134 | 126 | 247 | 11 | 496 |  | 614
1139 | 2016-09-12 | 2017-04-05 | 2017-07-06 | 2017-07-06 | COMP | 2017-07-13 | COMP | 2017-07-13 | COMP | 2019-05-23 | COMP | 2019-07-31 | COMP | Rule 15/16 | 142 | 65 | 6 | 1 | 468 | 48 | 725
1767 | 2016-09-12 | 2017-07-22 | 2018-07-25 | 2018-07-25 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-09-21 | INPR | 2019-06-11 | COMP | Rule 16 | 217 | 253 | 167 | 1 |  |  | 690
723 | 2016-09-13 | 2016-10-25 | 2016-12-19 | 2016-12-19 | COMP | 2018-05-10 | COMP | 2018-02-22 | COMP | 2019-05-16 | COMP | 2019-07-24 | COMP | Rule 15/16 | 31 | 37 | 351 |  | 311 | 48 | 719
731 | 2016-09-14 | 2016-10-26 | 2016-12-05 | 2018-08-22 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP |  |  | 2019-01-28 | COMP | Rule 16 | 31 | 26 | 53 | 1 |  |  | 594
900 | 2016-09-14 | 2017-01-24 | 2017-06-08 | 2017-06-08 | COMP | 2017-07-24 | COMP | 2018-12-17 | INPR | 2021-02-27 | REQD | 2019-07-03 | COMP | Rule 15/16 | 90 | 96 | 32 |  |  |  | 704
1056 | 2016-09-14 | 2017-03-15 | 2017-05-17 | 2017-05-17 | COMP | 2017-05-24 | COMP | 2017-06-29 | COMP | 2017-10-17 | COMP | 2023-09-25 | COMP | Rule 16 | 125 | 46 | 6 | 26 | 77 | 1491 | 1766
1977 | 2016-09-14 | 2017-08-31 | 2019-04-28 | 2019-04-28 | COMP | 2019-01-25 | COMP | 2019-04-29 | COMP | 2019-10-02 | COMP | 2019-11-07 | COMP | Rule 15/16 | 244 | 414 |  | 66 | 110 | 27 | 793
9070 | 2016-09-14 | 2019-01-15 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-04-18 | COMP | 2019-06-05 | COMP | Rule 15/16 | 586 | 21 | 44 | 1 | 3 | 34 | 684
653 | 2016-09-15 | 2016-09-27 | 2018-08-09 | 2018-08-09 | COMP | 2019-01-11 | COMP | 2019-01-17 | COMP | 2019-01-18 | COMP | 2019-03-24 | COMP | Rule 16 | 9 | 470 | 106 | 5 | 2 | 44 | 631
722 | 2016-09-15 | 2016-10-25 | 2017-04-19 | 2017-04-19 | COMP | 2017-10-24 | COMP | 2017-10-24 | COMP | 2018-12-17 | COMP | 2019-03-01 | COMP | Rule 16 | 29 | 121 | 132 | 1 | 287 | 51 | 616
756 | 2016-09-16 | 2016-11-09 | 2018-06-07 | 2018-06-07 | COMP | 2018-06-07 | NOTN | 2018-06-17 | INPR | 2018-06-11 | COMP | 2021-03-22 | COMP | Other | 39 | 395 |  |  |  |  | 1132
778 | 2016-09-16 | 2016-11-18 | 2017-03-21 | 2017-03-21 | COMP | 2018-03-19 | COMP | 2018-03-19 | COMP | 2019-03-01 | COMP | 2019-04-22 | COMP | Rule 16 | 45 | 83 | 250 | 1 | 240 | 37 | 651
820 | 2016-09-16 | 2016-12-09 | 2017-04-13 | 2017-04-13 | COMP | 2017-05-15 | COMP | 2017-11-30 | COMP | 2019-03-18 | COMP | 2019-04-29 | COMP | Rule 16 | 58 | 87 | 23 | 138 | 324 | 31 | 656
885 | 2016-09-19 | 2017-01-17 | 2017-12-13 | 2017-11-02 | COMP | 2017-11-16 | COMP | 2017-12-13 | COMP | 2017-12-21 | COMP | 2019-01-28 | COMP | Rule 15/16 | 82 | 230 | 10 | 18 | 7 | 275 | 591
886 | 2016-09-19 | 2017-01-17 | 2017-05-27 | 2017-05-27 | COMP | 2017-09-18 | COMP | 2017-10-18 | COMP | 2017-12-21 | COMP | 2019-01-28 | COMP | Rule 15/16 | 82 | 93 | 78 | 23 | 44 | 275 | 591
920 | 2016-09-19 | 2017-02-01 | 2017-08-22 | 2017-08-22 | COMP | 2017-09-06 | COMP | 2017-09-06 | COMP | 2020-02-13 | COMP | 2020-03-10 | COMP | Rule 16 | 93 | 142 | 11 | 1 | 611 | 18 | 871
3851 | 2016-09-19 | 2018-08-16 | 2018-08-28 | 2018-08-28 | COMP | 2018-10-30 | COMP | 2018-11-17 | COMP | 2019-04-20 | INPR | 2019-01-28 | COMP | Rule 16 | 481 | 9 | 45 | 13 |  |  | 591
4382 | 2016-09-19 | 2017-11-06 | 2018-04-20 | 2018-04-20 | COMP | 2018-08-15 | COMP | 2018-10-23 | COMP | 2018-11-13 | COMP | 2019-02-20 | COMP | Rule 16 | 287 | 113 | 82 | 49 | 15 | 66 | 607
9721 | 2016-09-19 | 2019-02-12 | 2019-04-06 | 2019-04-26 | COMP | 2019-05-16 | COMP | 2019-07-12 | COMP | 2020-01-27 | COMP | 2020-02-26 | COMP | Rule 16 | 602 | 38 | 15 | 40 | 135 | 22 | 862
859 | 2016-09-20 | 2016-12-30 | 2017-08-09 | 2017-08-09 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2020-01-29 | COMP | 2020-06-09 | COMP | Rule 16 | 70 | 155 | 401 | 1 | 219 | 93 | 934
988 | 2016-09-20 | 2017-02-22 | 2017-08-05 | 2019-01-15 | COMP | 2019-02-01 | COMP | 2019-03-06 | COMP | 2023-12-03 | INPR | 2019-04-10 | COMP | Rule 15/16 | 106 | 116 | 13 | 23 |  |  | 641
4482 | 2016-09-20 | 2018-01-04 | 2018-03-13 | 2018-03-19 | COMP | 2018-07-12 | COMP | 2018-09-04 | COMP | 2019-07-05 | COMP | 2019-08-26 | COMP | Rule 15/16 | 324 | 47 | 82 | 38 | 210 | 37 | 737
890 | 2016-09-21 | 2017-01-20 | 2017-05-12 | 2017-05-12 | COMP | 2018-08-27 | COMP | 2019-03-05 | COMP |  |  | 2020-03-10 | COMP | Rule 16 | 83 | 80 | 325 | 129 |  |  | 869
1072 | 2016-09-21 | 2017-03-20 | 2017-12-04 | 2018-05-21 | COMP | 2018-12-04 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-08-24 | COMP | Rule 15/16 | 123 | 180 | 136 | 120 | 1 | 64 | 735
1300 | 2016-09-21 | 2017-05-05 | 2017-10-17 | 2017-10-17 | COMP | 2017-10-31 | COMP | 2018-01-19 | COMP | 2018-08-17 | COMP | 2020-11-02 | COMP | Rule 16 | 157 | 115 | 11 | 53 | 148 | 557 | 1036
2221 | 2016-09-21 | 2017-10-16 | 2018-02-25 | 2018-02-25 | COMP | 2018-03-26 | COMP | 2018-04-23 | COMP | 2019-06-29 | INPR | 2019-03-13 | COMP | Rule 16 | 270 | 88 | 21 | 21 |  |  | 620
838 | 2016-09-22 | 2016-12-15 | 2017-03-20 | 2017-03-20 | COMP | 2017-04-27 | COMP | 2017-04-27 | COMP | 2019-03-05 | COMP | 2019-06-25 | COMP | Rule 16 | 58 | 65 | 29 | 1 | 464 | 80 | 692
1212 | 2016-09-22 | 2017-04-21 | 2017-06-05 | 2017-06-05 | COMP | 2018-01-08 | COMP | 2018-04-18 | COMP | 2019-04-08 | COMP | 2019-05-06 | COMP | Rule 15/16 | 146 | 31 | 149 | 71 | 244 | 21 | 657
1421 | 2016-09-22 | 2017-06-01 | 2017-12-18 | 2017-12-18 | COMP | 2018-06-05 | COMP | 2018-06-05 | INPR | 2019-04-25 | COMP | 2019-06-22 | COMP | Rule 15/16 | 174 | 138 | 117 |  |  |  | 690
1422 | 2016-09-22 | 2017-06-01 | 2017-07-28 | 2017-07-28 | COMP | 2017-12-11 | COMP | 2017-12-11 | COMP | 2019-04-16 | COMP | 2019-06-08 | COMP | Rule 15/16 | 174 | 41 | 93 | 1 | 338 | 38 | 680
1423 | 2016-09-22 | 2017-06-01 | 2017-10-24 | 2017-10-24 | COMP | 2018-01-08 | COMP | 2018-01-08 | COMP | 2019-03-19 | COMP | 2019-06-07 | COMP | Rule 15/16 | 174 | 102 | 50 | 1 | 300 | 58 | 680
1424 | 2016-09-22 | 2017-06-01 | 2017-09-01 | 2017-09-01 | COMP | 2017-12-11 | COMP | 2019-02-07 | COMP | 2019-03-11 | COMP | 2019-07-09 | COMP | Rule 15/16 | 174 | 66 | 68 | 291 | 22 | 85 | 701
1425 | 2016-09-22 | 2017-06-01 | 2017-07-21 | 2017-07-21 | COMP | 2017-12-11 | COMP | 2019-07-08 | COMP | 2019-08-20 | COMP | 2019-08-23 | COMP | Rule 16 | 174 | 36 | 98 | 395 | 32 | 4 | 734
1550 | 2016-09-22 | 2017-06-22 | 2017-10-29 | 2017-10-29 | COMP | 2017-11-22 | COMP | 2017-11-22 | COMP | 2021-01-30 | INPR | 2019-08-20 | COMP | Rule 15/16 | 189 | 90 | 17 | 1 |  |  | 731
4450 | 2016-09-22 | 2017-12-19 | 2018-02-21 | 2018-02-21 | COMP | 2018-08-21 | COMP | 2018-08-28 | COMP | 2019-05-16 | COMP | 2020-11-14 | COMP | Rule 15/16 | 312 | 43 | 128 | 6 | 180 | 379 | 1043
691 | 2016-09-23 | 2016-10-14 | 2018-07-16 | 2017-10-04 | COMP | 2019-01-02 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-06-18 | COMP | Rule 15/16 | 16 | 439 | 311 | 93 | 1 | 25 | 686
849 | 2016-09-23 | 2016-12-20 | 2017-09-02 | 2017-09-02 | COMP | 2017-11-27 | COMP | 2018-01-12 | COMP | 2020-02-09 | INPR | 2019-07-17 | COMP | Rule 15/16 | 60 | 179 | 57 | 33 |  |  | 706
866 | 2016-09-23 | 2017-01-06 | 2017-03-24 | 2017-03-24 | COMP | 2017-11-21 | COMP | 2017-11-21 | COMP | 2019-03-12 | COMP | 2019-04-09 | COMP | Rule 16 | 72 | 54 | 169 | 1 | 325 | 21 | 637
878 | 2016-09-23 | 2017-01-14 | 2017-08-27 | 2017-08-27 | COMP | 2018-03-05 | COMP | 2019-05-06 | COMP | 2019-04-30 | COMP | 2019-05-24 | COMP | Rule 16 | 77 | 156 | 128 | 296 | 0 | 15 | 670
926 | 2016-09-23 | 2017-02-02 | 2017-06-13 | 2019-03-11 | COMP | 2019-04-16 | COMP | 2019-04-17 | COMP | 2019-04-04 | COMP | 2019-05-22 | COMP | Rule 16 | 90 | 92 | 27 | 2 | 0 | 26 | 668
947 | 2016-09-23 | 2017-02-10 | 2017-09-30 | 2017-09-30 | COMP | 2017-11-10 | COMP | 2019-03-12 | COMP | 2019-03-11 | COMP | 2019-04-20 | COMP | Rule 15/16 | 96 | 162 | 29 | 331 | 0 | 29 | 645
1814 | 2016-09-23 | 2017-08-02 | 2018-02-14 | 2019-02-26 | COMP | 2019-07-24 | COMP | 2019-08-29 | COMP | 2020-07-28 | COMP | 2020-09-17 | COMP | Rule 15/16 | 216 | 134 | 105 | 27 | 230 | 37 | 1002
14857 | 2016-09-23 | 2019-10-01 | 2020-02-24 | 2020-03-02 | COMP | 2020-06-16 | COMP | 2020-07-20 | COMP | 2020-09-01 | COMP | 2020-09-03 | COMP | Rule 16 | 759 | 98 | 76 | 25 | 32 | 3 | 993
668 | 2016-09-24 | 2016-09-30 | 2016-12-14 | 2016-12-14 | COMP | 2017-04-05 | COMP | 2017-04-05 | COMP | 2019-05-15 | COMP | 2019-08-09 | COMP | Rule 16 | 5 | 51 | 78 | 1 | 531 | 61 | 722
709 | 2016-09-24 | 2016-10-20 | 2017-11-11 | 2017-11-11 | COMP | 2018-02-26 | COMP | 2018-02-28 | COMP | 2020-02-04 | COMP | 2020-03-16 | COMP | Rule 15/16 | 19 | 267 | 70 | 3 | 486 | 29 | 870
3846 | 2016-09-24 | 2018-08-16 | 2018-11-12 | 2018-11-12 | COMP | 2019-03-27 | COMP | 2019-03-29 | COMP | 2019-06-25 | COMP | 2019-07-21 | COMP | Rule 15/16 | 476 | 61 | 91 | 3 | 62 | 18 | 707
1705 | 2016-09-26 | 2017-07-18 | 2018-02-21 | 2018-02-21 | COMP | 2018-10-01 | COMP | 2019-02-08 | COMP | 2020-02-19 | COMP | 2021-03-23 | COMP | Rule 15/16 | 204 | 149 | 156 | 89 | 258 | 276 | 1127
4636 | 2016-09-26 | 2018-02-22 | 2018-05-16 | 2018-05-16 | COMP | 2018-06-05 | COMP | 2018-06-05 | COMP | 2019-11-06 | COMP | 2019-11-18 | COMP | Rule 15/16 | 353 | 60 | 14 | 1 | 360 | 8 | 791
15892 | 2016-09-26 | 2019-11-26 | 2020-02-27 | 2020-02-27 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-07-27 | NOTN | 2020-12-29 | COMP | Rule 16 | 797 | 62 | 74 | 1 |  |  | 1070
728 | 2016-09-27 | 2016-10-25 | 2017-05-17 | 2017-05-17 | COMP | 2018-10-02 | COMP | 2018-10-24 | COMP | 2018-12-13 | COMP | 2019-01-07 | COMP | Rule 16 | 21 | 141 | 347 | 17 | 34 | 16 | 571
759 | 2016-09-27 | 2016-11-12 | 2017-02-18 | 2017-02-18 | COMP | 2021-05-26 | COMP | 2021-06-28 | COMP | 2021-05-26 | COMP | 2021-07-22 | COMP | Rule 16 | 33 | 66 | 1073 | 23 | 0 | 18 | 1211
977 | 2016-09-27 | 2017-02-18 | 2017-07-07 | 2017-07-07 | COMP | 2018-09-28 | COMP | 2018-10-02 | COMP | 2019-02-12 | COMP | 2019-04-18 | COMP | Rule 16 | 99 | 97 | 310 | 3 | 90 | 47 | 642
1008 | 2016-09-27 | 2017-02-27 | 2017-06-06 | 2017-06-06 | COMP | 2017-08-10 | COMP | 2018-04-09 | COMP | 2019-06-29 | INPR | 2019-03-25 | COMP | Rule 16 | 104 | 71 | 47 | 165 |  |  | 624
1218 | 2016-09-27 | 2017-04-24 | 2017-07-26 | 2017-07-26 | COMP | 2018-08-22 | COMP | 2018-08-22 | COMP | 2018-08-29 | COMP | 2019-08-20 | COMP | Rule 15/16 | 144 | 66 | 271 | 1 | 6 | 245 | 728
1286 | 2016-09-27 | 2017-05-05 | 2017-11-20 | 2017-11-20 | COMP | 2017-12-07 | COMP | 2018-08-17 | COMP | 2018-07-03 | COMP | 2019-06-27 | COMP | Rule 15/16 | 153 | 138 | 12 | 176 | 0 | 216 | 691
2394 | 2016-09-27 | 2017-11-16 | 2019-07-13 | 2019-07-13 | COMP | 2019-09-24 | COMP | 2019-11-04 | COMP | 2020-10-29 | COMP | 2020-12-04 | COMP | Rule 16 | 288 | 414 | 51 | 30 | 250 | 24 | 1053
693 | 2016-09-28 | 2016-10-13 | 2017-03-10 | 2020-03-30 | COMP | 2020-07-27 | COMP | 2020-08-20 | COMP | 2020-08-19 | COMP | 2020-10-02 | COMP | Rule 16 | 12 | 101 | 85 | 19 | 0 | 31 | 1010
762 | 2016-09-28 | 2016-11-14 | 2017-10-07 | 2017-10-07 | COMP | 2020-02-28 | COMP | 2018-03-15 | COMP | 2019-09-27 | COMP | 2020-03-02 | COMP | Rule 15/16 | 33 | 227 | 598 |  | 389 | 105 | 858
1009 | 2016-09-28 | 2017-02-27 | 2017-09-30 | 2018-08-02 | COMP | 2019-06-03 | COMP | 2019-07-29 | COMP | 2019-07-08 | COMP | 2019-09-30 | COMP | Rule 15/16 | 103 | 152 | 209 | 40 | 0 | 45 | 755
2991 | 2016-09-28 | 2018-02-26 | 2018-03-29 | 2018-03-29 | COMP | 2018-02-26 | NOTN | 2018-03-29 | COMP | 2018-07-03 | COMP | 2019-12-05 | COMP | Other | 353 | 24 |  | 1 | 68 | 358 | 800
1779 | 2016-09-29 | 2017-07-25 | 2018-05-14 | 2018-05-14 | COMP | 2019-01-28 | COMP | 2019-07-29 | COMP | 2019-10-29 | COMP | 2020-01-29 | COMP | Rule 15/16 | 206 | 202 | 177 | 128 | 66 | 61 | 835
2451 | 2016-09-29 | 2017-12-02 | 2018-03-29 | 2018-03-29 | COMP | 2018-06-19 | COMP | 2018-07-25 | COMP | 2019-07-26 | COMP | 2019-08-16 | COMP | Rule 15/16 | 295 | 80 | 58 | 26 | 253 | 16 | 724
38336 | 2016-09-29 | 2022-08-22 | 2022-09-14 | 2022-10-25 | COMP | 2022-12-06 | COMP | 2022-12-08 | COMP | 2022-12-06 | COMP | 2023-01-27 | COMP | Rule 15/16 | 1482 | 17 | 28 | 3 | 0 | 34 | 1589
678 | 2016-09-30 | 2016-10-06 | 2017-06-02 | 2017-06-02 | COMP | 2017-10-02 | COMP | 2018-09-24 | COMP | 2019-06-07 | COMP | 2019-07-10 | COMP | Rule 16 | 5 | 165 | 85 | 246 | 177 | 23 | 696
3478 | 2016-09-30 | 2018-05-04 | 2018-06-14 | 2018-06-14 | COMP | 2018-07-30 | COMP | 2018-07-30 | COMP | 2023-01-28 | INPR | 2021-12-07 | COMP | Rule 16 | 400 | 29 | 32 | 1 |  |  | 1302
39147 | 2016-09-30 | 2022-10-03 | 2023-01-13 | 2023-03-22 | COMP | 2023-03-22 | NOTN | 2023-05-30 | COMP | 2023-07-19 | NOTN | 2023-08-08 | COMP | Other | 1510 | 70 |  | 49 |  |  | 1721
742 | 2016-10-03 | 2016-11-01 | 2017-12-20 | 2017-12-20 | COMP | 2017-12-28 | COMP | 2017-12-28 | COMP | 2018-12-11 | COMP | 2019-02-20 | COMP | Rule 16 | 22 | 285 | 6 | 1 | 240 | 48 | 597
1443 | 2016-10-03 | 2017-06-05 | 2018-02-22 | 2018-02-22 | COMP | 2018-04-25 | COMP | 2018-10-17 | COMP | 2019-04-20 | INPR | 2019-01-25 | COMP | Rule 16 | 169 | 180 | 45 | 123 |  |  | 580
1484 | 2016-10-03 | 2017-06-08 | 2017-07-31 | 2017-07-31 | COMP | 2017-12-11 | COMP | 2018-01-11 | COMP | 2019-06-21 | COMP | 2019-08-27 | COMP | Rule 16 | 172 | 37 | 92 | 22 | 364 | 47 | 729
6819 | 2016-10-03 | 2018-09-12 | 2019-01-28 | 2019-06-26 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2020-12-08 | COMP | 2021-01-12 | COMP | Rule 15/16 | 489 | 93 | 18 | 1 | 349 | 24 | 1074
16318 | 2016-10-03 | 2019-12-19 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-17 | COMP | 2020-07-01 | COMP | 2024-03-02 | INPR | 2021-10-01 | COMP | Rule 15/16 | 807 | 48 | 13 | 76 |  |  | 1257
674 | 2016-10-04 | 2016-10-06 | 2017-04-08 | 2017-04-08 | COMP | 2017-04-26 | COMP | 2017-04-26 | COMP | 2017-04-07 | COMP | 2021-10-14 | COMP | Rule 16 | 3 | 126 | 13 | 1 | 0 | 1125 | 1265
695 | 2016-10-04 | 2016-10-14 | 2017-08-14 | 2018-09-14 | COMP | 2018-10-09 | COMP | 2018-11-10 | COMP | 2018-12-11 | COMP | 2019-01-29 | COMP | Rule 16 | 9 | 209 | 18 | 24 | 19 | 33 | 581
724 | 2016-10-04 | 2016-10-25 | 2017-09-12 | 2017-09-12 | COMP | 2017-10-16 | COMP | 2017-10-16 | COMP | 2018-12-14 | COMP | 2019-01-09 | COMP | Rule 16 | 16 | 222 | 25 | 1 | 292 | 17 | 568
770 | 2016-10-04 | 2016-11-16 | 2017-07-13 | 2017-07-13 | COMP | 2017-10-31 | COMP | 2017-12-04 | COMP | 2019-03-19 | COMP | 2019-04-25 | COMP | Rule 15/16 | 31 | 165 | 78 | 22 | 323 | 28 | 642
1033 | 2016-10-04 | 2017-03-04 | 2017-05-03 | 2017-05-03 | COMP | 2017-05-15 | COMP | 2017-05-26 | COMP |  |  | 2020-03-30 | COMP | Rule 16 | 103 | 43 | 9 | 10 |  |  | 874
1133 | 2016-10-04 | 2017-04-03 | 2017-08-24 | 2018-11-14 | COMP | 2018-11-19 | COMP | 2019-06-24 | COMP | 2019-07-25 | COMP | 2019-09-05 | COMP | Rule 16 | 124 | 102 | 4 | 149 | 23 | 30 | 734
2429 | 2016-10-04 | 2017-11-28 | 2018-05-21 | 2018-05-21 | COMP | 2019-01-04 | COMP | 2021-02-08 | COMP | 2021-02-05 | COMP | 2021-03-12 | COMP | Rule 15/16 | 289 | 121 | 157 | 527 | 0 | 24 | 1114
6620 | 2016-10-04 | 2018-08-31 | 2019-01-18 | 2019-08-13 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-11-20 | COMP | 2019-11-29 | COMP | Rule 16 | 481 | 95 | 11 | 1 | 60 | 6 | 792
816 | 2016-10-05 | 2016-12-08 | 2017-03-08 | 2017-03-08 | COMP | 2018-09-10 | COMP | 2018-09-11 | COMP | 2018-12-17 | COMP | 2019-01-23 | COMP | Rule 16 | 44 | 62 | 381 | 2 | 67 | 25 | 576
855 | 2016-10-05 | 2016-12-28 | 2017-06-02 | 2017-06-02 | COMP | 2018-02-01 | COMP | 2018-02-27 | COMP | 2018-05-04 | COMP | 2019-08-20 | COMP | Rule 15/16 | 57 | 110 | 167 | 18 | 49 | 326 | 722
1004 | 2016-10-05 | 2017-02-25 | 2017-07-13 | 2017-07-13 | COMP | 2017-07-24 | COMP | 2017-11-16 | COMP |  |  | 2021-08-13 | COMP | Rule 16 | 97 | 97 | 8 | 82 |  |  | 1221
1172 | 2016-10-05 | 2017-04-13 | 2017-12-01 | 2017-12-01 | COMP | 2017-12-07 | COMP | 2017-12-12 | COMP | 2023-04-29 | INPR | 2022-04-18 | COMP | Rule 16 | 131 | 161 | 5 | 4 |  |  | 1391
1194 | 2016-10-05 | 2017-04-18 | 2017-05-25 | 2017-05-25 | COMP | 2017-06-19 | COMP | 2018-02-20 | COMP | 2022-02-26 | INPR | 2021-02-09 | COMP | Rule 16 | 134 | 28 | 17 | 168 |  |  | 1091
1514 | 2016-10-05 | 2017-06-15 | 2017-09-29 | 2017-09-29 | COMP | 2018-03-23 | COMP | 2018-04-06 | COMP |  | INPR | 2019-01-08 | COMP | Rule 15/16 | 175 | 75 | 119 | 11 |  |  | 566
2551 | 2016-10-05 | 2017-12-21 | 2018-08-03 | 2018-08-03 | COMP | 2018-09-19 | COMP | 2018-11-13 | COMP | 2019-02-11 | COMP | 2019-04-15 | COMP | Rule 16 | 305 | 156 | 33 | 39 | 60 | 45 | 633
39156 | 2016-10-05 | 2022-10-04 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-30 | NOTN | 2023-11-03 | COMP | 2023-07-06 | COMP | 2023-11-11 | COMP | Other | 1508 | 177 |  | 97 | 0 | 5 | 1784
1273 | 2016-10-06 | 2017-05-04 | 2017-12-21 | 2017-12-21 | COMP | 2018-01-05 | COMP | 2018-03-22 | COMP | 2018-07-27 | COMP | 2019-01-31 | COMP | Rule 16 | 145 | 160 | 10 | 53 | 90 | 128 | 581
1274 | 2016-10-06 | 2017-05-04 | 2017-12-14 | 2017-12-14 | COMP | 2017-12-28 | COMP | 2018-03-22 | COMP | 2023-04-29 | INPR | 2022-04-18 | COMP | Rule 16 | 145 | 155 | 10 | 58 |  |  | 1390
1303 | 2016-10-06 | 2017-05-06 | 2017-08-01 | 2017-08-01 | COMP | 2017-08-23 | COMP | 2017-10-05 | COMP |  | INPR | 2021-02-15 | COMP | Rule 16 | 146 | 60 | 17 | 31 |  |  | 1093
1304 | 2016-10-06 | 2017-05-06 | 2017-07-27 | 2017-07-27 | COMP | 2017-08-29 | COMP | 2018-03-15 | COMP |  | INPR | 2022-04-22 | COMP | Rule 16 | 146 | 57 | 24 | 135 |  |  | 1394
1352 | 2016-10-06 | 2017-05-16 | 2017-10-17 | 2017-10-17 | COMP | 2017-12-04 | COMP | 2019-10-04 | COMP | 2020-12-11 | COMP | 2022-04-22 | COMP | Rule 16 | 153 | 108 | 32 | 463 | 299 | 344 | 1394
1426 | 2016-10-06 | 2017-06-01 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-08 | COMP | 2018-12-06 | COMP | 2019-08-31 | INPR | 2019-04-04 | COMP | Rule 16 | 164 | 328 | 37 | 18 |  |  | 625
1427 | 2016-10-06 | 2017-06-01 | 2017-12-14 | 2017-12-14 | COMP | 2017-12-20 | COMP | 2017-12-20 | COMP |  | INPR | 2021-02-15 | COMP | Rule 16 | 164 | 136 | 5 | 1 |  |  | 1093
1428 | 2016-10-06 | 2017-06-01 | 2018-10-29 | 2018-10-25 | COMP | 2018-11-28 | COMP | 2019-02-08 | COMP | 2019-09-21 | INPR | 2019-06-04 | COMP | Rule 16 | 164 | 356 | 22 | 50 |  |  | 667
1684 | 2016-10-06 | 2017-07-16 | 2017-09-14 | 2017-09-14 | COMP | 2017-09-22 | COMP | 2018-03-21 | COMP | 2023-05-27 | INPR | 2022-04-22 | COMP | Rule 16 | 194 | 43 | 7 | 122 |  |  | 1394
2040 | 2016-10-06 | 2017-09-11 | 2017-11-10 | 2017-11-10 | COMP | 2017-11-17 | COMP | 2018-05-16 | COMP |  | INPR | 2022-07-18 | COMP | Rule 16 | 234 | 44 | 5 | 123 |  |  | 1452
2041 | 2016-10-06 | 2017-09-11 | 2017-10-30 | 2017-10-30 | COMP | 2017-11-09 | COMP | 2018-01-16 | COMP | 2018-05-15 | COMP | 2019-06-09 | COMP | Rule 16 | 234 | 36 | 9 | 43 | 85 | 268 | 670
2081 | 2016-10-06 | 2017-09-20 | 2018-02-08 | 2018-02-08 | COMP | 2018-03-10 | COMP | 2018-03-10 | COMP | 2019-08-31 | INPR | 2019-05-15 | COMP | Rule 16 | 241 | 96 | 21 | 0 |  |  | 654
2200 | 2016-10-06 | 2017-10-10 | 2017-11-03 | 2017-11-03 | COMP | 2017-11-09 | COMP | 2017-12-21 | COMP | 2023-12-02 | INPR | 2022-04-22 | COMP | Rule 16 | 255 | 19 | 5 | 28 |  |  | 1394
2237 | 2016-10-06 | 2017-10-19 | 2017-12-05 | 2017-12-05 | COMP | 2017-12-07 | COMP | 2017-12-28 | COMP |  | INPR | 2022-04-22 | COMP | Rule 16 | 262 | 31 | 3 | 15 |  |  | 1394
2773 | 2016-10-06 | 2018-01-30 | 2018-07-15 | 2018-07-15 | COMP | 2018-12-28 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-22 | COMP | Rule 16 | 329 | 116 | 115 | 100 | 1 | 23 | 680
1275 | 2016-10-07 | 2017-05-04 | 2018-05-04 | 2018-05-04 | COMP | 2018-05-17 | COMP | 2018-08-02 | COMP | 2023-05-27 | INPR | 2022-04-13 | COMP | Rule 16 | 144 | 252 | 10 | 54 |  |  | 1386
1538 | 2016-10-07 | 2017-06-20 | 2017-08-04 | 2017-08-04 | COMP | 2017-08-10 | COMP | 2018-02-14 | COMP |  | INPR | 2022-04-22 | COMP | Rule 16 | 176 | 33 | 5 | 128 |  |  | 1393
1565 | 2016-10-07 | 2017-06-23 | 2017-08-28 | 2017-08-28 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-05-01 | COMP | 2019-06-26 | COMP | Rule 16 | 179 | 46 | 411 | 1 | 10 | 40 | 682
2404 | 2016-10-07 | 2017-11-17 | 2018-04-21 | 2018-04-21 | COMP | 2021-01-30 | INPR | 2019-10-23 | COMP | 2019-12-04 | COMP | 2020-01-07 | COMP | Rule 16 | 281 | 105 |  | 380 | 28 | 23 | 814
1150 | 2016-10-08 | 2017-04-07 | 2017-08-28 | 2017-08-28 | COMP | 2017-10-24 | COMP | 2017-10-24 | COMP | 2019-01-09 | COMP | 2019-02-11 | COMP | Rule 16 | 124 | 100 | 41 | 1 | 302 | 23 | 586
813 | 2016-10-10 | 2016-12-07 | 2017-02-03 | 2017-02-03 | COMP | 2017-09-12 | COMP | 2018-03-12 | COMP | 2020-03-21 | INPR | 2019-08-22 | COMP | Other | 40 | 41 | 154 | 123 |  |  | 721
814 | 2016-10-10 | 2016-12-07 | 2017-03-10 | 2017-03-10 | COMP | 2017-09-05 | COMP | 2017-09-05 | COMP | 2021-02-27 | INPR | 2019-05-08 | COMP | Other | 40 | 65 | 125 | 1 |  |  | 647
836 | 2016-10-10 | 2016-12-15 | 2017-03-29 | 2017-03-29 | COMP | 2018-04-10 | COMP | 2020-01-27 | COMP |  | INPR | 2020-07-17 | COMP | Other | 46 | 72 | 260 | 451 |  |  | 948
837 | 2016-10-10 | 2016-12-15 | 2017-03-29 | 2017-03-29 | COMP | 2018-02-21 | COMP | 2019-06-26 | COMP |  | INPR | 2019-09-04 | COMP | Other | 46 | 72 | 226 | 340 |  |  | 729
1278 | 2016-10-10 | 2017-05-04 | 2017-11-15 | 2017-11-15 | COMP | 2017-11-22 | COMP | 2017-12-01 | COMP | 2022-02-26 | INPR | 2021-02-15 | COMP | Rule 16 | 143 | 136 | 6 | 6 |  |  | 1091
1379 | 2016-10-10 | 2017-05-23 | 2017-06-24 | 2017-06-24 | COMP | 2019-03-20 | COMP | 2019-03-23 | COMP | 2019-08-09 | COMP | 2019-08-26 | COMP | Rule 16 | 156 | 23 | 434 | 3 | 98 | 12 | 723
1409 | 2016-10-10 | 2017-05-30 | 2017-07-14 | 2017-07-14 | COMP | 2017-07-24 | COMP | 2017-12-05 | COMP | 2018-03-12 | COMP | 2021-02-10 | COMP | Rule 16 | 160 | 33 | 7 | 93 | 66 | 735 | 1089
1418 | 2016-10-10 | 2017-05-31 | 2017-08-04 | 2017-08-04 | COMP | 2017-08-23 | COMP | 2018-03-09 | COMP | 2022-01-29 | INPR | 2021-01-14 | COMP | Rule 16 | 161 | 47 | 14 | 135 |  |  | 1071
1543 | 2016-10-10 | 2017-06-21 | 2017-08-18 | 2017-08-18 | COMP | 2017-08-24 | COMP | 2018-03-22 | COMP | 2022-02-26 | INPR | 2021-02-15 | COMP | Rule 16 | 176 | 42 | 5 | 143 |  |  | 1091
4185 | 2016-10-10 | 2019-06-11 | 2019-10-30 | 2019-10-30 | COMP | 2020-02-06 | COMP | 2020-04-30 | COMP |  | INPR | 2020-06-17 | COMP | Rule 16 | 670 | 100 | 66 | 60 |  |  | 926
4187 | 2016-10-10 | 2019-06-17 | 2019-09-13 | 2019-09-13 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2022-07-16 | INPR | 2020-06-22 | COMP | Other | 674 | 63 | 128 | 1 |  |  | 929
4227 | 2016-10-10 | 2019-09-09 | 2020-01-16 | 2020-01-16 | COMP | 2020-03-19 | COMP | 2020-06-08 | COMP | 2022-07-16 | INPR | 2020-06-29 | COMP | Other | 732 | 89 | 44 | 57 |  |  | 934
4245 | 2016-10-10 | 2019-10-23 | 2020-01-16 | 2020-01-16 | COMP | 2020-03-19 | COMP | 2020-06-19 | COMP | 2022-07-16 | INPR | 2020-07-03 | COMP | Other | 764 | 57 | 44 | 66 |  |  | 938
4246 | 2016-10-10 | 2019-10-23 | 2020-01-17 | 2020-01-17 | COMP | 2020-03-19 | COMP | 2020-04-28 | COMP | 2023-09-02 | INPR | 2020-05-29 | COMP | Other | 764 | 58 | 43 | 29 |  |  | 913
4254 | 2016-10-10 | 2019-11-22 | 2020-01-30 | 2020-01-30 | COMP | 2020-03-19 | COMP | 2020-04-28 | COMP | 2020-05-11 | COMP | 2020-05-18 | COMP | Rule 15 | 785 | 45 | 35 | 29 | 10 | 6 | 905
4255 | 2016-10-10 | 2019-11-22 | 2020-01-22 | 2020-01-22 | COMP | 2020-03-19 | COMP | 2020-04-28 | COMP | 2023-09-02 | INPR | 2020-05-29 | COMP | Rule 15 | 785 | 39 | 41 | 29 |  |  | 913
14131 | 2016-10-10 | 2019-08-26 | 2020-10-26 | 2020-10-26 | COMP | 2021-02-01 | COMP | 2021-02-01 | COMP | 2021-07-20 | COMP | 2022-02-01 | COMP | Rule 16 | 723 | 296 | 65 | 1 | 119 | 136 | 1335
751 | 2016-10-11 | 2016-11-07 | 2017-05-27 | 2019-04-11 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-05-29 | COMP | 2019-08-29 | COMP | Rule 16 | 20 | 139 | 35 | 1 | 0 | 65 | 725
787 | 2016-10-11 | 2016-11-28 | 2017-09-07 | 2018-01-24 | COMP | 2018-03-22 | COMP | 2020-06-05 | COMP | 2020-05-15 | COMP | 2020-08-03 | COMP | Rule 15/16 | 32 | 198 | 41 | 556 | 0 | 42 | 958
810 | 2016-10-11 | 2016-12-06 | 2017-02-13 | 2017-02-13 | COMP | 2017-05-09 | COMP | 2017-06-26 | COMP |  |  | 2020-05-21 | COMP | Rule 16 | 38 | 48 | 61 | 34 |  |  | 907
904 | 2016-10-11 | 2017-01-26 | 2017-12-01 | 2018-07-19 | COMP | 2018-09-25 | COMP | 2019-08-12 | COMP | 2019-08-19 | COMP | 2019-09-12 | COMP | Rule 15/16 | 73 | 215 | 48 | 221 | 6 | 18 | 734
1030 | 2016-10-11 | 2017-03-04 | 2017-05-12 | 2017-05-12 | COMP | 2018-05-11 | COMP | 2018-05-16 | COMP |  |  | 2021-02-26 | COMP | Rule 16 | 98 | 50 | 251 | 4 |  |  | 1099
1031 | 2016-10-11 | 2017-03-04 | 2017-04-17 | 2017-04-17 | COMP | 2017-05-19 | COMP | 2017-07-28 | COMP |  |  | 2021-02-26 | COMP | Rule 16 | 98 | 31 | 25 | 49 |  |  | 1099
1032 | 2016-10-11 | 2017-03-04 | 2017-05-22 | 2017-05-22 | COMP | 2017-05-30 | COMP | 2017-08-16 | COMP |  |  | 2021-01-14 | COMP | Rule 16 | 98 | 56 | 6 | 56 |  |  | 1070
1064 | 2016-10-11 | 2017-03-17 | 2017-06-22 | 2017-06-22 | COMP | 2017-10-16 | COMP | 2018-11-01 | COMP | 2018-10-17 | COMP | 2019-01-24 | COMP | Rule 16 | 108 | 69 | 81 | 264 | 0 | 55 | 573
1192 | 2016-10-11 | 2017-04-18 | 2017-06-12 | 2017-06-12 | COMP | 2017-06-30 | COMP | 2017-09-25 | COMP | 2018-03-12 | COMP | 2021-02-10 | COMP | Rule 16 | 130 | 39 | 15 | 60 | 114 | 735 | 1088
1338 | 2016-10-11 | 2017-05-13 | 2017-06-22 | 2017-06-22 | COMP | 2017-06-29 | COMP | 2017-09-06 | COMP | 2018-03-12 | COMP | 2021-02-02 | COMP | Rule 16 | 148 | 28 | 6 | 48 | 127 | 729 | 1082
1340 | 2016-10-11 | 2017-05-13 | 2017-08-04 | 2017-08-04 | COMP | 2017-08-23 | COMP | 2018-02-28 | COMP |  | INPR | 2021-02-10 | COMP | Rule 16 | 148 | 58 | 14 | 128 |  |  | 1088
1344 | 2016-10-11 | 2017-05-15 | 2017-06-21 | 2017-06-21 | COMP | 2017-06-23 | COMP | 2017-07-26 | COMP | 2018-03-12 | COMP | 2021-02-10 | COMP | Rule 16 | 149 | 27 | 3 | 23 | 156 | 735 | 1088
1674 | 2016-10-11 | 2017-07-13 | 2017-09-14 | 2017-09-14 | COMP | 2017-09-22 | COMP | 2018-03-14 | COMP | 2022-02-26 | INPR | 2021-02-10 | COMP | Rule 16 | 190 | 45 | 7 | 117 |  |  | 1088
2160 | 2016-10-11 | 2017-10-02 | 2017-11-10 | 2017-11-10 | COMP | 2017-11-09 | COMP | 2017-11-15 | COMP | 2017-11-30 | COMP | 2021-04-05 | COMP | Rule 16 | 246 | 29 |  | 4 | 10 | 840 | 1125
2518 | 2016-10-11 | 2017-12-13 | 2018-06-01 | 2018-06-01 | COMP | 2018-11-08 | COMP | 2019-09-09 | COMP | 2019-01-08 | COMP | 2019-02-01 | COMP | Rule 15/16 | 295 | 118 | 113 | 208 | 0 |  | 579
22232 | 2016-10-11 | 2020-09-15 | 2020-12-18 | 2020-12-28 | COMP | 2021-02-17 | COMP | 2021-07-30 | COMP | 2021-08-03 | COMP | 2021-09-14 | COMP | Rule 15/16 | 988 | 66 | 35 | 116 | 3 | 30 | 1238
777 | 2016-10-12 | 2016-11-18 | 2017-10-02 | 2019-05-03 | COMP | 2019-05-28 | COMP | 2020-08-28 | COMP |  | REQD | 2020-11-08 | COMP | Rule 15/16 | 27 | 219 | 17 | 319 |  |  | 1025
832 | 2016-10-12 | 2016-12-13 | 2017-07-18 | 2018-04-02 | COMP | 2018-04-25 | COMP | 2018-04-25 | COMP | 2019-11-23 | INPR | 2019-08-08 | COMP | Rule 16 | 42 | 151 | 18 | 1 |  |  | 709
2109 | 2016-10-12 | 2017-09-25 | 2017-11-06 | 2017-11-06 | COMP | 2017-09-25 | NOTN | 2017-11-06 | COMP | 2019-01-15 | COMP | 2019-02-26 | COMP | Other | 240 | 31 |  | 1 | 297 | 29 | 594
745 | 2016-10-13 | 2016-11-03 | 2016-12-17 | 2016-12-17 | COMP | 2017-04-14 | COMP | 2018-08-06 | COMP | 2018-07-02 | COMP | 2019-07-23 | COMP | Other | 16 | 29 | 82 | 330 | 0 | 242 | 696
755 | 2016-10-13 | 2016-11-09 | 2016-12-19 | 2016-12-19 | COMP | 2017-04-14 | COMP |  | REQD | 2018-07-02 | COMP | 2019-07-23 | COMP | Other | 20 | 26 | 82 |  |  |  | 696
781 | 2016-10-13 | 2016-11-22 | 2016-12-21 | 2018-04-03 | COMP |  |  |  |  | 2018-07-02 | COMP | 2019-08-13 | COMP | Other | 28 | 20 |  |  |  |  | 711
792 | 2016-10-13 | 2016-11-29 | 2017-02-06 | 2017-02-06 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2018-11-28 | COMP | 2019-01-09 | COMP | Rule 16 | 31 | 48 | 457 | 1 | 0 | 28 | 561
825 | 2016-10-13 | 2016-12-10 | 2017-06-06 | 2018-02-01 | COMP | 2019-06-29 | REQD | 2018-03-14 | COMP | 2018-04-11 | COMP | 2019-03-21 | COMP | Rule 16 | 39 | 123 |  | 29 | 21 | 237 | 610
884 | 2016-10-13 | 2017-01-17 | 2018-04-09 | 2018-04-09 | COMP | 2019-04-19 | COMP | 2019-10-15 | COMP | 2020-07-03 | COMP | 2020-09-10 | COMP | Rule 15/16 | 64 | 309 | 260 | 125 | 181 | 49 | 983
941 | 2016-10-13 | 2017-02-08 | 2017-05-24 | 2017-05-24 | COMP | 2018-04-19 | COMP | 2018-04-25 | COMP | 2019-01-24 | COMP | 2019-03-08 | COMP | Rule 15/16 | 80 | 75 | 227 | 5 | 188 | 31 | 601
942 | 2016-10-13 | 2017-02-08 | 2017-06-16 | 2017-06-16 | COMP | 2018-04-26 | COMP | 2018-04-26 | COMP | 2019-01-24 | COMP | 2019-03-08 | COMP | Rule 16 | 80 | 91 | 216 | 1 | 187 | 31 | 601
1350 | 2016-10-13 | 2017-05-16 | 2017-12-14 | 2017-12-14 | COMP | 2017-12-20 | COMP | 2017-12-20 | COMP |  | INPR | 2022-04-22 | COMP | Rule 16 | 148 | 147 | 5 | 1 |  |  | 1389
2201 | 2016-10-13 | 2017-10-10 | 2017-12-06 | 2017-12-06 | COMP | 2017-12-07 | COMP | 2019-01-10 | COMP | 2022-07-09 | INPR | 2022-05-31 | COMP | Rule 16 | 250 | 39 | 2 | 274 |  |  | 1415
6025 | 2016-10-13 | 2018-07-18 | 2018-10-19 | 2018-10-19 | COMP | 2019-02-26 | COMP | 2019-04-17 | COMP | 2019-06-18 | COMP | 2019-06-26 | COMP | Rule 16 | 442 | 67 | 86 | 37 | 44 | 7 | 678
748 | 2016-10-14 | 2016-11-04 | 2017-02-21 | 2017-02-21 | COMP | 2017-06-02 | COMP | 2019-03-04 | COMP | 2019-01-17 | COMP | 2019-04-04 | COMP | Rule 15/16 | 16 | 72 | 73 | 438 | 0 | 24 | 619
1797 | 2016-10-14 | 2017-07-28 | 2018-02-06 | 2018-02-06 | COMP | 2018-03-10 | COMP | 2018-03-14 | COMP | 2019-01-14 | COMP | 2019-01-29 | COMP | Rule 16 | 198 | 131 | 23 | 3 | 211 | 11 | 573
4141 | 2016-10-14 | 2019-04-03 | 2019-04-03 | 2019-04-03 | COMP | 2019-04-12 | COMP | 2019-04-12 | COMP | 2019-05-01 | COMP | 2019-07-12 | COMP | Rule 16 | 618 | 1 | 8 | 1 | 14 | 51 | 688
8826 | 2016-10-15 | 2018-12-31 | 2019-09-03 | 2021-01-13 | COMP | 2021-01-25 | COMP | 2021-02-08 | COMP | 2021-01-08 | COMP | 2021-02-24 | COMP | Rule 16 | 553 | 171 | 8 | 11 | 0 | 12 | 1093
1377 | 2016-10-16 | 2017-05-23 | 2017-11-11 | 2017-11-11 | COMP | 2018-08-24 | COMP | 2018-08-29 | COMP | 2019-02-19 | COMP | 2019-03-28 | COMP | Rule 16 | 151 | 120 | 197 | 4 | 117 | 28 | 613
1242 | 2016-10-17 | 2017-04-27 | 2017-08-07 | 2017-08-07 | COMP | 2018-02-02 | COMP | 2018-07-31 | COMP | 2019-07-21 | INPR | 2019-04-24 | COMP | Rule 15/16 | 133 | 71 | 123 | 125 |  |  | 632
1279 | 2016-10-17 | 2017-05-04 | 2017-11-02 | 2017-11-02 | COMP | 2017-11-15 | COMP | 2018-01-30 | COMP |  | INPR | 2022-04-13 | COMP | Rule 16 | 138 | 128 | 9 | 50 |  |  | 1380
1351 | 2016-10-17 | 2017-05-16 | 2017-10-11 | 2017-10-11 | COMP | 2017-11-02 | COMP | 2017-11-02 | COMP | 2023-05-27 | INPR | 2022-04-22 | COMP | Rule 16 | 146 | 104 | 17 | 1 |  |  | 1387
1353 | 2016-10-17 | 2017-05-16 | 2017-11-28 | 2017-11-28 | COMP | 2017-12-07 | COMP | 2018-07-30 | COMP |  | INPR | 2022-04-22 | COMP | Rule 16 | 146 | 135 | 8 | 162 |  |  | 1387
5191 | 2016-10-17 | 2018-05-08 | 2018-08-21 | 2018-08-21 | COMP | 2018-11-15 | COMP | 2018-11-16 | COMP | 2019-03-13 | COMP | 2019-05-10 | COMP | Rule 16 | 391 | 74 | 61 | 2 | 78 | 43 | 644
785 | 2016-10-18 | 2016-11-23 | 2017-01-26 | 2017-01-26 | COMP | 2017-03-08 | COMP | 2018-05-10 | COMP | 2019-09-21 | INPR | 2019-04-16 | COMP | Rule 16 | 26 | 43 | 29 | 297 |  |  | 625
1054 | 2016-10-18 | 2017-03-14 | 2018-06-06 | 2019-01-15 | COMP | 2019-06-25 | COMP | 2019-11-26 | COMP | 2019-11-18 | COMP | 2020-01-06 | COMP | Rule 15/16 | 100 | 311 | 113 | 108 | 0 | 26 | 806
1057 | 2016-10-18 | 2017-03-15 | 2017-05-02 | 2017-05-02 | COMP | 2017-05-15 | COMP | 2017-05-31 | COMP |  |  | 2021-01-15 | COMP | Rule 16 | 101 | 35 | 10 | 12 |  |  | 1066
752 | 2016-10-19 | 2016-11-07 | 2016-11-12 | 2016-11-12 | COMP | 2017-12-06 | COMP | 2017-12-07 | COMP | 2017-12-07 | COMP | 2019-05-24 | COMP | Rule 16 | 14 | 4 | 267 | 2 | 1 | 368 | 652
1065 | 2016-10-19 | 2017-03-18 | 2017-05-24 | 2017-05-24 | COMP | 2017-05-30 | COMP | 2017-07-26 | COMP | 2018-03-12 | COMP | 2021-02-25 | COMP | Rule 16 | 102 | 48 | 4 | 41 | 156 | 745 | 1092
1070 | 2016-10-19 | 2017-03-18 | 2017-06-21 | 2017-06-21 | COMP | 2017-06-23 | COMP | 2017-09-18 | COMP |  |  | 2021-02-25 | COMP | Rule 16 | 102 | 67 | 3 | 60 |  |  | 1092
1193 | 2016-10-19 | 2017-04-18 | 2017-06-22 | 2017-06-22 | COMP | 2017-06-30 | COMP | 2017-08-09 | COMP | 2018-03-12 | COMP | 2021-01-19 | COMP | Rule 16 | 124 | 47 | 7 | 28 | 146 | 719 | 1066
1431 | 2016-10-19 | 2017-06-01 | 2018-02-02 | 2018-02-02 | COMP | 2018-03-10 | COMP | 2018-05-22 | COMP | 2020-03-21 | INPR | 2019-10-16 | COMP | Rule 16 | 155 | 169 | 25 | 52 |  |  | 752
1573 | 2016-10-19 | 2017-06-26 | 2018-05-23 | 2018-05-23 | COMP | 2018-08-28 | COMP | 2019-12-09 | COMP | 2020-05-30 | INPR | 2019-12-20 | COMP | Rule 16 | 172 | 229 | 68 | 321 |  |  | 796
12660 | 2016-10-19 | 2019-06-18 | 2019-10-09 | 2019-10-09 | COMP | 2020-09-21 | COMP | 2020-10-07 | COMP | 2021-01-14 | COMP | 2021-01-25 | COMP | Rule 16 | 668 | 80 | 240 | 13 | 67 | 7 | 1070
760 | 2016-10-20 | 2016-11-12 | 2017-07-17 | 2017-07-17 | COMP | 2018-03-02 | COMP | 2018-03-23 | COMP | 2019-08-31 | INPR | 2019-05-09 | COMP | Rule 16 | 16 | 169 | 157 | 16 |  |  | 640
791 | 2016-10-20 | 2016-11-29 | 2017-07-10 | 2017-07-10 | COMP | 2019-01-22 | COMP | 2018-05-11 | COMP | 2019-06-05 | COMP | 2019-07-30 | COMP | Rule 16 | 26 | 155 | 385 |  | 268 | 39 | 696
1410 | 2016-10-20 | 2017-05-30 | 2017-08-04 | 2017-08-04 | COMP | 2017-12-12 | COMP | 2017-12-20 | COMP | 2018-03-12 | COMP | 2021-02-10 | COMP | Rule 16 | 152 | 48 | 89 | 7 | 55 | 735 | 1081
1559 | 2016-10-20 | 2017-06-22 | 2018-08-20 | 2018-08-20 | COMP | 2018-09-20 | COMP | 2018-12-10 | COMP | 2019-01-17 | COMP | 2019-04-05 | COMP | Rule 15/16 | 169 | 292 | 23 | 55 | 27 | 55 | 616
3315 | 2016-10-20 | 2018-04-06 | 2018-08-27 | 2019-04-17 | COMP | 2019-07-08 | COMP | 2019-08-14 | COMP | 2019-09-12 | COMP | 2019-11-11 | COMP | Rule 15/16 | 366 | 100 | 57 | 28 | 21 | 42 | 768
6679 | 2016-10-20 | 2018-09-06 | 2019-02-27 | 2019-02-27 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-27 | COMP | 2020-04-21 | COMP | Rule 16 | 472 | 118 | 257 | 1 | 17 | 18 | 878
772 | 2016-10-21 | 2016-11-16 | 2018-02-21 | 2018-02-21 | COMP | 2017-08-24 | COMP | 2018-04-20 | COMP | 2018-04-20 | COMP | 2019-07-23 | COMP | Rule 16 | 18 | 316 |  | 164 | 1 | 316 | 690
833 | 2016-10-21 | 2016-12-14 | 2017-03-28 | 2017-05-31 | COMP | 2017-12-28 | COMP | 2018-01-31 | COMP | 2018-11-14 | COMP | 2019-03-29 | COMP | Rule 15/16 | 36 | 72 | 146 | 23 | 201 | 92 | 610
891 | 2016-10-21 | 2017-01-23 | 2017-05-12 | 2017-05-12 | COMP | 2017-08-01 | COMP | 2019-07-31 | COMP | 2021-02-27 | INPR | 2019-10-03 | COMP | Rule 16 | 62 | 79 | 56 | 502 |  |  | 741
892 | 2016-10-21 | 2017-01-23 | 2017-05-07 | 2017-05-07 | COMP | 2017-08-29 | COMP | 2017-08-29 | COMP | 2019-11-23 | INPR | 2019-07-19 | COMP | Rule 16 | 62 | 74 | 80 | 1 |  |  | 688
944 | 2016-10-21 | 2017-02-09 | 2017-06-13 | 2017-06-13 | COMP | 2017-09-25 | COMP | 2018-01-19 | COMP | 2021-07-15 | COMP | 2021-08-06 | COMP | Rule 15/16 | 75 | 87 | 73 | 79 | 878 | 17 | 1204
1002 | 2016-10-21 | 2017-02-24 | 2018-05-14 | 2018-05-14 | COMP | 2018-06-14 | COMP | 2019-10-15 | COMP | 2019-10-16 | COMP | 2019-11-26 | COMP | Rule 15/16 | 85 | 307 | 23 | 337 | 2 | 29 | 778
1265 | 2016-10-21 | 2017-05-03 | 2017-12-01 | 2017-12-01 | COMP | 2018-04-24 | COMP | 2018-08-30 | COMP | 2018-08-30 | COMP | 2019-07-24 | COMP | Rule 16 | 133 | 147 | 99 | 91 | 1 | 225 | 691
1488 | 2016-10-21 | 2017-06-09 | 2017-07-19 | 2017-07-19 | COMP | 2017-07-27 | COMP | 2017-11-02 | COMP |  | INPR | 2021-02-26 | COMP | Rule 16 | 159 | 28 | 7 | 70 |  |  | 1091
2743 | 2016-10-21 | 2018-01-26 | 2018-06-01 | 2018-06-01 | COMP | 2018-06-12 | COMP | 2019-01-25 | COMP | 2019-03-22 | COMP | 2019-06-28 | COMP | Rule 16 | 316 | 89 | 8 | 156 | 40 | 70 | 674
789 | 2016-10-24 | 2016-11-29 | 2017-02-27 | 2017-02-27 | COMP | 2018-05-31 | COMP | 2018-07-10 | COMP | 2019-05-30 | COMP | 2019-08-06 | COMP | Rule 15 | 24 | 62 | 318 | 28 | 224 | 48 | 699
1287 | 2016-10-24 | 2017-05-05 | 2018-07-16 | 2018-07-16 | COMP | 2018-10-26 | COMP | 2019-04-09 | COMP |  |  | 2020-01-10 | COMP | Rule 16 | 134 | 300 | 74 | 111 |  |  | 806
1412 | 2016-10-24 | 2017-05-30 | 2017-09-11 | 2017-09-11 | COMP | 2017-09-22 | COMP | 2018-11-01 | COMP | 2019-04-20 | INPR | 2019-01-10 | COMP | Rule 16 | 150 | 73 | 10 | 280 |  |  | 555
1542 | 2016-10-24 | 2017-06-20 | 2018-01-23 | 2017-08-08 | COMP | 2018-03-15 | COMP | 2018-03-15 | COMP | 2018-11-21 | COMP | 2019-01-09 | COMP | Rule 16 | 165 | 148 | 150 | 1 | 176 | 32 | 554
1858 | 2016-10-24 | 2017-08-10 | 2017-09-25 | 2017-09-25 | COMP | 2017-10-04 | COMP | 2017-11-02 | COMP | 2018-03-12 | COMP | 2021-02-10 | COMP | Rule 16 | 201 | 32 | 8 | 22 | 86 | 735 | 1079
1859 | 2016-10-24 | 2017-08-10 | 2017-09-25 | 2017-09-25 | COMP | 2017-10-03 | COMP | 2017-11-02 | COMP | 2018-03-12 | COMP | 2021-02-10 | COMP | Rule 16 | 201 | 32 | 7 | 23 | 86 | 735 | 1079
1865 | 2016-10-24 | 2017-08-11 | 2017-09-22 | 2017-09-22 | COMP | 2017-10-03 | COMP | 2018-02-07 | COMP | 2017-12-26 | COMP | 2021-01-21 | COMP | Rule 16 | 202 | 30 | 8 | 86 | 0 | 743 | 1065
2660 | 2016-10-24 | 2018-01-16 | 2018-10-25 | 2018-10-25 | COMP | 2018-11-20 | COMP | 2019-05-22 | COMP | 2019-11-23 | INPR | 2019-08-07 | COMP | Rule 16 | 307 | 199 | 18 | 126 |  |  | 700
3389 | 2016-10-24 | 2018-04-18 | 2019-05-24 | 2020-02-28 | COMP | 2023-04-29 | INPR | 2019-08-22 | COMP | 2019-08-26 | COMP | 2020-03-14 | COMP | Rule 15/16 | 372 | 278 |  |  | 3 | 137 | 849
980 | 2016-10-25 | 2017-02-17 | 2018-01-08 | 2018-01-08 | COMP | 2018-03-28 | COMP | 2018-05-17 | COMP | 2018-05-02 | COMP | 2021-06-04 | COMP | Rule 15/16 | 79 | 223 | 56 | 37 | 0 | 767 | 1158
1341 | 2016-10-25 | 2017-05-13 | 2017-08-07 | 2017-08-07 | COMP | 2017-12-01 | COMP | 2017-12-01 | COMP | 2017-12-04 | COMP | 2019-11-13 | COMP | Rule 16 | 138 | 59 | 81 | 1 | 2 | 490 | 767
1840 | 2016-10-25 | 2017-08-08 | 2018-12-22 | 2018-12-22 | COMP | 2020-04-15 | COMP | 2022-06-29 | COMP | 2022-06-28 | COMP | 2022-07-18 | COMP | Rule 16 | 198 | 345 | 329 | 557 | 0 | 13 | 1439
2426 | 2016-10-25 | 2017-11-28 | 2019-12-10 | 2019-12-10 | COMP | 2021-02-02 | COMP | 2021-02-25 | COMP | 2021-11-02 | COMP | 2021-12-23 | COMP | Rule 16 | 274 | 511 | 289 | 17 | 176 | 35 | 1297
835 | 2016-10-26 | 2016-12-14 | 2017-04-01 | 2017-04-01 | COMP | 2018-03-20 | NOTN | 2018-03-20 | COMP | 2017-07-11 | COMP | 2021-02-17 | COMP | Rule 16 | 33 | 75 |  | 242 | 0 | 733 | 1081
893 | 2016-10-26 | 2017-01-23 | 2017-09-19 | 2017-09-19 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-05-07 | COMP | 2019-06-25 | COMP | Rule 15/16 | 59 | 168 | 399 | 1 | 11 | 35 | 668
928 | 2016-10-26 | 2017-02-03 | 2017-10-31 | 2017-10-31 | COMP | 2018-02-14 | COMP | 2018-05-07 | COMP | 2018-06-04 | COMP | 2019-01-04 | COMP | Rule 15/16 | 68 | 189 | 71 | 58 | 20 | 148 | 549
1071 | 2016-10-26 | 2017-03-18 | 2017-06-12 | 2017-06-12 | COMP | 2017-06-27 | COMP | 2017-06-27 | COMP | 2019-07-11 | COMP | 2019-10-16 | COMP | Rule 15/16 | 97 | 60 | 12 | 1 | 512 | 69 | 747
1149 | 2016-10-26 | 2017-04-07 | 2018-07-24 | 2018-07-24 | COMP | 2018-10-17 | COMP | 2019-07-24 | COMP | 2019-08-24 | COMP | 2019-09-20 | COMP | Rule 16 | 112 | 326 | 61 | 192 | 23 | 19 | 729
1909 | 2016-10-26 | 2017-08-19 | 2017-10-19 | 2017-10-19 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2018-11-07 | COMP | 2019-01-16 | COMP | Rule 16 | 205 | 43 | 283 | 1 | 0 | 28 | 557
2385 | 2016-10-26 | 2017-11-15 | 2018-09-19 | 2018-02-22 | COMP | 2018-12-27 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-08-01 | COMP | Rule 16 | 266 | 212 | 214 | 127 | 1 | 25 | 694
2555 | 2016-10-26 | 2017-12-22 | 2018-07-16 | 2018-07-16 | COMP | 2018-07-11 | NOTN | 2019-05-13 | COMP | 2019-06-21 | COMP | 2019-11-05 | COMP | Other | 291 | 141 |  | 208 | 29 | 96 | 761
3770 | 2016-10-26 | 2018-07-09 | 2018-08-01 | 2018-08-01 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2019-02-04 | COMP | 2019-04-09 | COMP | Rule 16 | 426 | 18 | 43 | 1 | 85 | 46 | 614
4573 | 2016-10-26 | 2018-02-02 | 2019-07-16 | 2019-07-18 | COMP | 2020-03-13 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-06-17 | COMP | Rule 15/16 | 318 | 365 | 164 | 52 | 1 | 17 | 914
799 | 2016-10-27 | 2016-12-03 | 2017-07-25 | 2017-07-25 | COMP | 2017-10-11 | COMP | 2019-08-05 | COMP |  |  | 2020-01-22 | COMP | Rule 16 | 24 | 162 | 56 | 455 |  |  | 810
844 | 2016-10-27 | 2016-12-16 | 2017-03-07 | 2017-03-07 | COMP | 2017-03-16 | COMP | 2019-01-08 | COMP |  |  | 2019-03-04 | COMP | Rule 16 | 34 | 55 | 8 | 456 |  |  | 587
879 | 2016-10-27 | 2017-01-14 | 2018-09-26 | 2018-09-26 | COMP | 2018-11-20 | COMP | 2019-05-15 | COMP | 2019-05-02 | COMP | 2019-07-11 | COMP | Rule 16 | 53 | 428 | 39 | 121 | 0 | 40 | 678
960 | 2016-10-27 | 2017-02-16 | 2017-06-13 | 2017-06-13 | COMP | 2017-06-28 | COMP | 2018-04-19 | COMP | 2019-04-20 | INPR | 2019-01-02 | COMP | Rule 16 | 76 | 82 | 12 | 203 |  |  | 546
981 | 2016-10-27 | 2017-02-18 | 2017-06-30 | 2019-11-22 | COMP | 2020-08-31 | COMP | 2021-03-03 | COMP | 2021-02-09 | COMP | 2021-03-23 | COMP | Rule 16 | 77 | 93 | 195 | 125 | 0 | 15 | 1104
1466 | 2016-10-27 | 2017-06-07 | 2018-06-28 | 2018-06-28 | COMP | 2018-08-31 | COMP | 2019-05-15 | COMP | 2019-05-16 | COMP | 2019-08-23 | COMP | Rule 16 | 153 | 267 | 46 | 176 | 2 | 70 | 709
2594 | 2016-10-27 | 2018-01-04 | 2018-09-20 | 2018-09-20 | COMP | 2018-11-05 | COMP | 2018-11-13 | INPR |  |  | 2019-01-03 | COMP | Rule 16 | 297 | 181 | 33 |  |  |  | 547
4408 | 2016-10-27 | 2017-11-21 | 2018-03-04 | 2018-03-04 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-07-13 | COMP | Rule 16 | 269 | 68 | 567 | 1 | 1 | 29 | 931
6290 | 2016-10-27 | 2018-08-09 | 2018-10-05 | 2019-01-11 | COMP | 2019-02-19 | COMP | 2019-05-06 | COMP | 2019-07-08 | COMP | 2019-08-05 | COMP | Rule 16 | 448 | 41 | 26 | 55 | 44 | 21 | 695
18988 | 2016-10-27 | 2020-04-16 | 2020-12-04 | 2020-12-14 | COMP | 2021-01-04 | COMP | 2021-03-09 | COMP |  | INPR | 2021-03-08 | COMP | Rule 15/16 | 870 | 162 | 14 | 45 |  |  | 1093
854 | 2016-10-28 | 2016-12-24 | 2017-04-29 | 2017-04-29 | COMP | 2018-04-26 | COMP | 2018-05-11 | COMP | 2021-07-27 | COMP | 2021-09-07 | COMP | Rule 16 | 38 | 87 | 249 | 12 | 807 | 30 | 1220
6703 | 2016-10-28 | 2018-09-07 | 2019-01-04 | 2019-01-04 | COMP | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-06-27 | COMP | 2019-08-21 | COMP | Rule 16 | 467 | 81 | 18 | 7 | 99 | 39 | 706
1207 | 2016-10-30 | 2017-04-21 | 2018-11-30 | 2018-11-28 | COMP | 2019-01-08 | COMP | 2019-02-25 | COMP | 2020-05-30 | INPR | 2019-07-22 | COMP | Rule 16 | 119 | 405 | 28 | 33 |  |  | 683
1180 | 2016-10-31 | 2017-04-14 | 2017-12-04 | 2017-12-04 | COMP | 2018-02-15 | COMP | 2018-02-24 | COMP | 2018-06-22 | COMP | 2020-05-13 | COMP | Rule 15 | 114 | 161 | 51 | 6 | 84 | 475 | 887
1620 | 2016-10-31 | 2017-07-05 | 2017-09-29 | 2017-09-29 | COMP | 2018-04-17 | COMP | 2017-11-06 | COMP | 2019-04-12 | COMP | 2019-03-27 | COMP | Rule 16 | 170 | 62 | 136 |  | 358 |  | 602
4515 | 2016-10-31 | 2018-01-18 | 2018-05-17 | 2018-05-17 | COMP | 2018-07-27 | COMP | 2018-07-27 | COMP | 2019-09-25 | COMP | 2019-12-17 | COMP | Rule 16 | 304 | 85 | 50 | 1 | 293 | 57 | 785
4518 | 2016-10-31 | 2018-01-18 | 2018-05-17 | 2018-05-17 | COMP | 2018-08-09 | COMP | 2018-08-09 | COMP | 2019-09-25 | COMP | 2019-10-31 | COMP | Rule 16 | 304 | 85 | 59 | 1 | 284 | 27 | 755
5198 | 2016-10-31 | 2018-05-10 | 2018-08-16 | 2018-08-16 | COMP | 2018-10-17 | COMP | 2018-10-17 | COMP | 2019-03-11 | COMP | 2019-03-22 | COMP | Rule 16 | 383 | 69 | 44 | 1 | 97 | 10 | 599
757 | 2016-11-01 | 2016-11-09 | 2017-10-17 | 2018-03-11 | COMP | 2018-09-12 | COMP | 2018-09-17 | COMP | 2018-12-28 | COMP | 2019-02-21 | COMP | Rule 15/16 | 7 | 236 | 130 | 4 | 71 | 37 | 577
846 | 2016-11-01 | 2016-12-19 | 2017-06-12 | 2017-06-12 | COMP | 2017-06-30 | COMP | 2017-09-26 | COMP | 2019-09-10 | COMP | 2019-10-27 | COMP | Rule 15/16 | 32 | 122 | 15 | 61 | 491 | 34 | 750
872 | 2016-11-01 | 2017-01-09 | 2018-03-20 | 2018-03-20 | COMP | 2018-08-20 | COMP | 2018-10-12 | COMP | 2020-01-29 | COMP | 2020-04-27 | COMP | Rule 15/16 | 46 | 300 | 108 | 39 | 323 | 63 | 874
874 | 2016-11-01 | 2017-01-10 | 2017-04-24 | 2017-04-24 | COMP | 2017-06-05 | COMP | 2017-08-22 | COMP | 2019-05-30 | COMP | 2019-07-18 | COMP | Rule 15/16 | 47 | 73 | 30 | 56 | 444 | 35 | 680
1014 | 2016-11-01 | 2017-02-27 | 2018-02-16 | 2018-08-14 | COMP | 2018-12-26 | COMP | 2019-09-16 | COMP | 2021-01-30 | REQD | 2020-01-16 | COMP | Rule 15/16 | 79 | 246 | 92 | 183 |  |  | 804
1184 | 2016-11-01 | 2017-04-17 | 2017-12-11 | 2017-12-11 | COMP | 2018-02-08 | COMP | 2018-03-16 | COMP | 2019-02-21 | COMP | 2019-03-25 | COMP | Rule 15/16 | 114 | 165 | 41 | 26 | 235 | 23 | 599
3529 | 2016-11-01 | 2018-05-10 | 2018-11-19 | 2018-11-19 | COMP | 2019-03-18 | COMP | 2019-04-29 | COMP | 2021-02-28 | INPR | 2019-08-20 | COMP | Rule 15/16 | 382 | 134 | 80 | 31 |  |  | 703
5385 | 2016-11-01 | 2018-05-25 | 2018-09-11 | 2018-09-11 | COMP | 2018-12-07 | COMP | 2018-12-20 | COMP | 2023-05-27 | INPR | 2019-03-04 | COMP | Rule 15/16 | 393 | 75 | 61 | 10 |  |  | 584
743 | 2016-11-02 | 2016-11-02 | 2017-04-26 | 2017-02-13 | COMP | 2018-05-11 | COMP | 2018-08-21 | COMP | 2017-06-26 | COMP | 2019-09-16 | COMP | Rule 16 | 1 | 120 | 314 | 71 | 0 | 269 | 720
786 | 2016-11-02 | 2016-11-26 | 2016-12-20 | 2018-03-21 | COMP | 2021-03-27 | INPR | 2018-04-30 | COMP | 2020-02-25 | COMP | 2020-03-20 | COMP | Rule 15/16 | 15 | 17 |  | 29 | 457 | 19 | 847
919 | 2016-11-02 | 2017-02-01 | 2017-04-06 | 2017-04-06 | COMP | 2017-05-11 | COMP | 2017-05-11 | COMP | 2020-06-30 | COMP | 2020-08-04 | COMP | Rule 16 | 61 | 46 | 26 | 1 | 788 | 26 | 943
2108 | 2016-11-02 | 2017-09-27 | 2018-01-30 | 2018-01-30 | COMP | 2018-07-09 | COMP | 2018-08-03 | COMP | 2019-05-30 | COMP | 2019-07-05 | COMP | Rule 15/16 | 227 | 84 | 112 | 20 | 206 | 26 | 670
2116 | 2016-11-02 | 2017-09-26 | 2017-11-01 | 2017-11-01 | COMP | 2018-01-08 | COMP | 2018-01-08 | COMP | 2018-06-28 | COMP | 2020-11-19 | COMP | Rule 16 | 226 | 27 | 44 | 1 | 121 | 604 | 1018
1343 | 2016-11-03 | 2017-05-15 | 2017-09-01 | 2017-09-01 | COMP | 2017-10-24 | COMP | 2017-10-27 | COMP | 2018-04-30 | COMP | 2021-03-08 | COMP | Rule 16 | 132 | 78 | 37 | 4 | 125 | 717 | 1088
4422 | 2016-11-03 | 2017-11-30 | 2018-03-21 | 2021-02-13 | COMP | 2021-03-26 | COMP | 2021-12-13 | COMP | 2022-02-17 | COMP | 2022-04-12 | COMP | Rule 15/16 | 269 | 76 | 29 | 181 | 48 | 38 | 1366
7109 | 2016-11-03 | 2018-09-28 | 2018-11-01 | 2018-11-01 | COMP | 2019-01-24 | COMP | 2019-04-30 | COMP | 2019-05-16 | COMP | 2019-06-06 | COMP | Rule 16 | 478 | 25 | 55 | 68 | 13 | 15 | 649
828 | 2016-11-04 | 2016-12-12 | 2017-04-26 | 2017-04-26 | COMP | 2017-05-08 | COMP | 2017-05-08 | COMP | 2019-05-01 | COMP | 2019-05-20 | COMP | Rule 16 | 24 | 95 | 9 | 1 | 498 | 14 | 636
935 | 2016-11-04 | 2017-02-06 | 2017-06-01 | 2018-10-08 | COMP | 2018-10-31 | COMP | 2018-12-26 | COMP | 2023-04-29 | INPR | 2019-06-27 | COMP | Rule 16 | 62 | 82 | 18 | 37 |  |  | 663
1313 | 2016-11-04 | 2017-05-09 | 2017-05-22 | 2017-05-22 | COMP | 2017-06-21 | COMP | 2018-01-02 | COMP | 2022-07-16 | INPR | 2020-10-09 | COMP | Rule 16 | 127 | 10 | 22 | 133 |  |  | 988
5902 | 2016-11-04 | 2018-07-10 | 2018-10-12 | 2019-03-14 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-04-15 | COMP | 2019-05-16 | COMP | Rule 16 | 420 | 68 | 10 | 1 | 14 | 24 | 634
1068 | 2016-11-05 | 2017-03-17 | 2017-07-21 | 2017-07-21 | COMP | 2017-11-21 | COMP | 2017-12-01 | COMP | 2018-07-25 | COMP | 2020-05-13 | COMP | Rule 16 | 89 | 89 | 86 | 7 | 163 | 453 | 882
869 | 2016-11-07 | 2017-01-06 | 2017-06-07 | 2017-06-07 | COMP | 2017-09-05 | COMP | 2017-09-05 | COMP | 2019-08-29 | COMP | 2019-11-06 | COMP | Rule 16 | 41 | 106 | 63 | 1 | 499 | 49 | 754
1349 | 2016-11-07 | 2017-05-16 | 2017-08-15 | 2017-08-15 | COMP | 2017-10-12 | COMP | 2022-09-13 | INPR | 2017-10-09 | COMP | 2022-06-17 | COMP | Rule 16 | 131 | 64 | 42 |  |  |  | 1411
953 | 2016-11-08 | 2017-02-14 | 2017-05-03 | 2017-05-03 | COMP | 2019-03-27 | COMP | 2019-04-17 | INPR | 2019-08-31 | REQD | 2019-05-09 | COMP | Rule 16 | 66 | 56 | 476 |  |  |  | 627
975 | 2016-11-08 | 2017-02-17 | 2017-06-13 | 2017-06-13 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-05-29 | COMP | 2019-06-21 | COMP | Rule 16 | 69 | 81 | 461 | 1 | 32 | 18 | 657
1510 | 2016-11-08 | 2017-06-13 | 2017-11-14 | 2017-11-14 | COMP | 2020-03-27 | COMP | 2020-06-09 | COMP | 2020-12-17 | COMP | 2021-07-22 | COMP | Rule 16 | 149 | 108 | 593 | 52 | 134 | 150 | 1181
4791 | 2016-11-08 | 2018-03-30 | 2018-09-24 | 2018-09-24 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-07-09 | COMP | 2019-08-02 | COMP | Rule 16 | 348 | 124 | 92 | 1 | 107 | 19 | 686
11123 | 2016-11-08 | 2019-04-16 | 2020-04-01 | 2020-04-01 | COMP | 2020-06-05 | COMP | 2020-06-13 | COMP | 2020-05-19 | COMP | 2020-06-30 | COMP | Rule 15/16 | 610 | 242 | 47 | 6 | 0 | 12 | 914
788 | 2016-11-09 | 2016-11-28 | 2016-11-28 | 2016-11-28 | COMP | 2016-12-02 | COMP | 2016-11-28 | COMP | 2016-11-28 | COMP | 2020-01-14 | COMP | Rule 16 | 11 | 1 | 5 |  | 1 | 786 | 796
860 | 2016-11-09 | 2016-12-31 | 2017-04-03 | 2017-04-03 | COMP | 2018-10-26 | NOTN | 2019-02-06 | COMP | 2018-10-26 | COMP | 2019-02-25 | COMP | Other | 34 | 64 |  | 464 | 0 | 13 | 573
867 | 2016-11-09 | 2017-01-06 | 2017-05-24 | 2017-05-24 | COMP | 2017-08-09 | COMP | 2017-08-09 | COMP | 2020-04-28 | COMP | 2020-06-04 | COMP | Other | 39 | 97 | 54 | 1 | 682 | 27 | 895
899 | 2016-11-09 | 2017-01-24 | 2017-04-20 | 2017-04-20 | COMP |  |  |  |  | 2018-01-08 | COMP | 2023-02-17 | COMP | Other | 50 | 62 |  |  |  |  | 1575
937 | 2016-11-09 | 2017-02-07 | 2017-10-10 | 2017-10-10 | COMP | 2017-10-31 | COMP | 2018-01-04 | COMP | 2018-06-11 | COMP | 2019-02-07 | COMP | Rule 15/16 | 60 | 172 | 16 | 43 | 110 | 166 | 562
994 | 2016-11-09 | 2017-02-22 | 2017-06-03 | 2017-06-03 | COMP | 2020-11-03 | COMP | 2017-10-02 | COMP | 2023-11-15 | COMP | 2023-12-28 | COMP | Rule 16 | 70 | 72 | 861 |  | 1538 | 29 | 1790
1091 | 2016-11-09 | 2017-03-24 | 2017-08-10 | 2017-08-10 | COMP | 2018-09-11 | COMP | 2018-09-24 | COMP | 2019-04-10 | COMP | 2019-05-28 | COMP | Rule 16 | 92 | 98 | 273 | 10 | 136 | 34 | 638
1093 | 2016-11-09 | 2017-03-24 | 2017-08-10 | 2017-08-10 | COMP | 2018-09-11 | COMP | 2018-09-11 | COMP | 2019-05-01 | COMP | 2019-05-28 | COMP | Rule 16 | 92 | 98 | 273 | 1 | 160 | 19 | 638
1094 | 2016-11-09 | 2017-03-24 | 2017-08-08 | 2017-08-08 | COMP | 2018-09-11 | COMP | 2018-09-27 | COMP | 2019-05-01 | COMP | 2019-05-28 | COMP | Rule 16 | 92 | 96 | 275 | 13 | 148 | 19 | 638
1095 | 2016-11-09 | 2017-03-24 | 2017-08-10 | 2017-08-10 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2020-03-18 | COMP | 2020-04-23 | COMP | Rule 15/16 | 92 | 98 | 481 | 1 | 172 | 27 | 866
1153 | 2016-11-09 | 2017-04-08 | 2017-07-06 | 2017-07-06 | COMP | 2017-08-15 | COMP | 2017-10-09 | COMP | 2017-09-29 | COMP | 2020-09-14 | COMP | Rule 16 | 102 | 62 | 29 | 39 | 0 | 737 | 966
1333 | 2016-11-09 | 2017-05-12 | 2018-12-14 | 2018-12-14 | COMP | 2019-02-27 | COMP | 2019-03-06 | COMP | 2020-03-02 | COMP | 2019-10-21 | COMP | Rule 15/16 | 127 | 400 | 50 | 6 | 249 |  | 740
4481 | 2016-11-09 | 2018-01-03 | 2018-03-22 | 2019-08-17 | COMP | 2020-02-19 | COMP | 2018-06-28 | COMP | 2020-02-24 | COMP | 2020-04-02 | COMP | Rule 16 | 287 | 55 | 125 |  | 414 | 29 | 851
5484 | 2016-11-09 | 2018-06-04 | 2018-10-27 | 2018-10-27 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-03-27 | COMP | 2022-04-28 | COMP | Rule 16 | 392 | 103 | 89 | 1 | 13 | 780 | 1374
1027 | 2016-11-10 | 2017-03-03 | 2018-07-19 | 2018-07-19 | COMP | 2019-02-15 | COMP | 2019-09-26 | COMP |  |  | 2019-10-21 | COMP | Rule 16 | 76 | 348 | 145 | 156 |  |  | 739
1045 | 2016-11-10 | 2017-03-09 | 2017-05-07 | 2017-05-07 | COMP | 2017-06-22 | COMP | 2017-07-06 | COMP | 2019-04-09 | COMP | 2019-06-14 | COMP | Rule 16 | 80 | 42 | 33 | 10 | 441 | 48 | 650
1058 | 2016-11-10 | 2017-03-15 | 2017-04-11 | 2017-04-11 | COMP | 2017-10-19 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-08-21 | COMP | Rule 15/16 | 84 | 20 | 135 | 422 | 1 | 40 | 697
1084 | 2016-11-10 | 2017-03-23 | 2017-09-14 | 2017-09-14 | COMP | 2017-10-09 | COMP | 2017-10-11 | COMP | 2020-03-21 | INPR | 2019-12-10 | COMP | Rule 16 | 90 | 123 | 18 | 3 |  |  | 772
1936 | 2016-11-10 | 2017-08-23 | 2017-11-06 | 2017-11-06 | COMP | 2020-11-23 | COMP | 2020-11-07 | COMP | 2020-11-19 | COMP | 2021-04-03 | COMP | Rule 16 | 197 | 53 | 766 |  | 8 | 91 | 1102
11521 | 2016-11-10 | 2019-04-30 | 2019-05-24 | 2019-05-24 | COMP | 2019-05-24 | NOTN | 2019-06-26 | COMP | 2019-07-12 | COMP | 2019-07-15 | COMP | Other | 618 | 19 |  | 23 | 12 | 2 | 670
868 | 2016-11-14 | 2017-01-07 | 2018-06-12 | 2018-06-12 | COMP | 2019-11-19 | COMP | 2019-11-21 | COMP | 2019-12-23 | COMP | 2020-01-29 | COMP | Rule 15/16 | 37 | 359 | 363 | 3 | 21 | 25 | 804
875 | 2016-11-14 | 2017-01-11 | 2017-04-24 | 2017-04-24 | COMP | 2017-05-08 | COMP | 2019-05-30 | COMP | 2019-05-29 | COMP | 2019-07-29 | COMP | Rule 16 | 40 | 72 | 11 | 518 | 0 | 42 | 679
1617 | 2016-11-14 | 2017-07-03 | 2017-09-15 | 2017-09-15 | COMP | 2017-12-11 | COMP | 2019-01-02 | INPR | 2019-02-08 | COMP | 2019-03-21 | COMP | Rule 16 | 160 | 53 | 59 |  |  |  | 589
3498 | 2016-11-14 | 2018-05-07 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-31 | COMP | 2020-03-11 | COMP | 2020-06-03 | COMP | 2020-07-23 | COMP | Rule 16 | 371 | 128 | 58 | 279 | 60 | 37 | 928
5173 | 2016-11-14 | 2018-05-07 | 2018-08-13 | 2018-08-13 | COMP | 2018-10-30 | COMP | 2018-11-13 | COMP | 2019-01-04 | COMP | 2019-02-01 | COMP | Rule 16 | 371 | 69 | 56 | 10 | 35 | 20 | 556
856 | 2016-11-15 | 2016-12-27 | 2017-04-12 | 2017-04-12 | COMP | 2020-03-25 | COMP | 2020-04-02 | COMP | 2017-04-13 | COMP | 2020-05-22 | COMP | Other | 28 | 75 | 741 | 7 | 0 | 37 | 884
881 | 2016-11-15 | 2017-01-14 | 2017-04-12 | 2017-04-12 | COMP | 2020-02-26 | COMP | 2020-03-02 | COMP | 2017-04-13 | COMP | 2020-05-08 | COMP | Other | 41 | 61 | 721 | 4 | 0 | 50 | 874
925 | 2016-11-15 | 2017-02-02 | 2017-06-01 | 2017-06-01 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP |  | INPR | 2020-08-04 | COMP | Rule 16 | 54 | 84 | 740 | 1 |  |  | 935
999 | 2016-11-15 | 2017-02-23 | 2017-05-02 | 2017-05-02 | COMP | 2017-05-17 | COMP | 2017-05-17 | COMP | 2020-01-28 | COMP | 2020-02-27 | COMP | Rule 16 | 68 | 49 | 12 | 1 | 676 | 22 | 823
1025 | 2016-11-15 | 2017-03-03 | 2017-09-01 | 2017-09-01 | COMP | 2017-10-04 | COMP | 2017-10-09 | COMP | 2019-01-22 | COMP | 2019-03-09 | COMP | Rule 15/16 | 74 | 129 | 23 | 4 | 321 | 33 | 579
1092 | 2016-11-15 | 2017-03-24 | 2017-08-10 | 2017-08-10 | COMP | 2018-09-11 | COMP | 2018-09-27 | COMP | 2019-05-01 | COMP | 2019-05-28 | COMP | Rule 15/16 | 89 | 98 | 273 | 13 | 148 | 19 | 635
1173 | 2016-11-15 | 2017-04-13 | 2017-06-02 | 2017-06-02 | COMP | 2017-09-07 | COMP | 2017-09-07 | COMP | 2020-01-31 | COMP | 2020-02-06 | COMP | Rule 16 | 103 | 36 | 68 | 1 | 601 | 5 | 809
1216 | 2016-11-15 | 2017-04-24 | 2019-05-09 | 2019-05-09 | COMP | 2019-12-09 | COMP | 2019-10-19 | COMP | 2019-10-11 | COMP | 2020-01-14 | COMP | Rule 16 | 110 | 514 | 147 |  | 0 | 57 | 793
1246 | 2016-11-15 | 2017-04-30 | 2017-11-27 | 2017-11-27 | COMP | 2018-03-27 | COMP | 2019-03-26 | COMP | 2019-10-19 | INPR | 2019-04-18 | COMP | Rule 16 | 114 | 145 | 83 | 251 |  |  | 608
1248 | 2016-11-15 | 2017-04-30 | 2017-10-30 | 2017-10-30 | COMP | 2018-01-17 | COMP | 2018-01-17 | COMP | 2019-12-18 | COMP | 2019-12-30 | COMP | Rule 16 | 114 | 128 | 52 | 1 | 484 | 8 | 783
1281 | 2016-11-15 | 2017-05-04 | 2017-12-21 | 2017-12-21 | COMP | 2018-01-30 | COMP | 2018-01-30 | COMP | 2019-11-21 | COMP | 2020-01-07 | COMP | Rule 16 | 118 | 160 | 26 | 1 | 458 | 30 | 788
1598 | 2016-11-15 | 2017-06-29 | 2018-02-08 | 2018-02-08 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-04-16 | COMP | 2019-07-18 | COMP | Rule 15/16 | 157 | 153 | 243 | 1 | 56 | 66 | 671
1658 | 2016-11-15 | 2017-07-13 | 2017-08-09 | 2017-08-09 | COMP | 2017-08-10 | COMP | 2018-03-03 | COMP | 2021-06-19 | INPR | 2021-03-03 | COMP | Rule 16 | 166 | 20 | 2 | 139 |  |  | 1078
2152 | 2016-11-15 | 2017-09-30 | 2018-03-18 | 2018-03-11 | COMP | 2018-04-24 | COMP | 2018-04-24 | COMP | 2019-06-14 | COMP | 2019-08-16 | COMP | Rule 15/16 | 221 | 113 | 32 | 1 | 288 | 45 | 692
3006 | 2016-11-15 | 2018-02-26 | 2018-07-02 | 2018-07-02 | COMP | 2018-08-22 | COMP | 2018-12-06 | COMP | 2019-01-03 | COMP | 2019-04-10 | COMP | Rule 15/16 | 320 | 90 | 37 | 73 | 19 | 68 | 602
11473 | 2016-11-15 | 2019-04-29 | 2019-08-05 | 2019-08-05 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2021-04-24 | INPR | 2020-04-08 | COMP | Rule 15/16 | 615 | 69 | 128 | 1 |  |  | 852
14863 | 2016-11-15 | 2019-10-01 | 2020-01-28 | 2020-01-28 | COMP | 2020-12-08 | COMP | 2022-03-28 | COMP | 2022-08-22 | COMP | 2022-08-22 | COMP | Rule 16 | 723 | 80 | 220 | 328 | 103 | 1 | 1450
1154 | 2016-11-16 | 2017-04-08 | 2017-05-04 | 2017-05-04 | COMP | 2017-07-13 | COMP | 2017-09-01 | COMP | 2019-08-30 | COMP | 2021-03-01 | COMP | Rule 16 | 98 | 19 | 49 | 37 | 501 | 375 | 1075
1217 | 2016-11-16 | 2017-04-24 | 2017-07-10 | 2017-07-10 | COMP | 2018-07-27 | COMP | 2018-07-30 | COMP | 2019-08-22 | COMP | 2019-08-26 | COMP | Rule 16 | 109 | 54 | 265 | 2 | 269 | 3 | 697
943 | 2016-11-17 | 2017-02-08 | 2018-05-20 | 2018-04-27 | COMP | 2018-07-16 | COMP | 2018-07-16 | COMP | 2019-03-11 | COMP | 2019-04-23 | COMP | Rule 16 | 56 | 322 | 55 | 1 | 163 | 32 | 609
2761 | 2016-11-17 | 2018-01-29 | 2018-07-28 | 2018-07-28 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2020-02-29 | INPR | 2019-10-24 | COMP | Rule 15/16 | 299 | 127 | 292 | 1 |  |  | 738
4175 | 2016-11-17 | 2019-05-28 | 2019-08-03 | 2019-08-03 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-04-10 | COMP | 2020-07-08 | COMP | Rule 16 | 633 | 48 | 131 | 1 | 42 | 63 | 914
1035 | 2016-11-18 | 2017-03-07 | 2017-05-27 | 2017-05-27 | COMP | 2018-05-17 | COMP | 2019-01-31 | INPR | 2019-09-09 | COMP | 2019-10-22 | COMP | Rule 15/16 | 73 | 59 | 244 |  |  |  | 735
1144 | 2016-11-18 | 2017-04-05 | 2017-05-10 | 2017-05-10 | COMP | 2019-03-04 | COMP | 2019-03-06 | COMP | 2020-05-15 | COMP | 2019-04-23 | COMP | Other | 94 | 26 | 454 | 3 | 303 |  | 608
1236 | 2016-11-18 | 2017-04-26 | 2017-05-21 | 2017-05-21 | COMP | 2017-09-27 | COMP | 2017-09-27 | COMP | 2019-02-27 | COMP | 2019-04-09 | COMP | Rule 16 | 109 | 18 | 90 | 1 | 354 | 30 | 598
1314 | 2016-11-18 | 2017-05-09 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-17 | COMP | 2018-12-20 | COMP | 2019-01-05 | COMP | 2019-01-21 | COMP | Rule 16 | 118 | 391 | 14 | 4 | 10 | 10 | 543
1534 | 2016-11-18 | 2017-06-19 | 2017-10-09 | 2017-10-09 | COMP | 2018-05-23 | COMP | 2018-07-05 | COMP | 2019-03-01 | COMP | 2019-03-21 | COMP | Rule 16 | 146 | 79 | 156 | 30 | 164 | 15 | 585
2220 | 2016-11-18 | 2017-10-16 | 2018-03-12 | 2018-03-12 | COMP | 2018-04-03 | COMP | 2018-04-03 | COMP | 2018-04-23 | COMP | 2019-11-06 | COMP | Rule 15/16 | 229 | 99 | 17 | 1 | 15 | 390 | 746
2236 | 2016-11-18 | 2017-10-19 | 2018-01-09 | 2018-01-09 | COMP | 2018-05-30 | COMP | 2019-05-03 | COMP | 2019-05-21 | COMP | 2019-06-22 | COMP | Rule 16 | 232 | 54 | 99 | 234 | 13 | 23 | 650
2433 | 2016-11-18 | 2017-11-28 | 2018-06-19 | 2019-05-22 | COMP | 2019-06-26 | COMP | 2019-09-20 | COMP | 2019-06-17 | COMP | 2019-12-12 | COMP | Rule 15/16 | 257 | 141 | 25 | 61 | 0 | 57 | 769
7770 | 2016-11-18 | 2018-10-30 | 2019-01-03 | 2019-09-07 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-12-03 | COMP | 2020-01-03 | COMP | Rule 16 | 490 | 43 | 11 | 1 | 49 | 22 | 783
834 | 2016-11-21 | 2016-12-14 | 2017-03-01 | 2018-09-06 | COMP | 2018-11-08 | COMP | 2018-11-26 | COMP | 2019-04-20 | INPR | 2019-01-02 | COMP | Rule 16 | 16 | 53 | 46 | 10 |  |  | 530
851 | 2016-11-21 | 2016-12-21 | 2017-11-27 | 2017-11-27 | COMP | 2018-06-06 | COMP | 2018-06-06 | COMP | 2019-10-19 | INPR | 2019-07-03 | COMP | Rule 16 | 21 | 235 | 133 | 1 |  |  | 657
991 | 2016-11-21 | 2017-02-22 | 2017-08-13 | 2018-05-08 | COMP | 2018-06-04 | COMP | 2018-08-16 | COMP | 2021-01-02 | INPR | 2019-12-24 | COMP | Rule 16 | 63 | 121 | 19 | 53 |  |  | 776
1547 | 2016-11-21 | 2017-06-21 | 2017-10-28 | 2017-10-28 | COMP | 2017-11-06 | COMP | 2017-11-06 | COMP | 2018-01-05 | COMP | 2021-03-05 | COMP | Rule 16 | 147 | 91 | 6 | 1 | 40 | 795 | 1076
2730 | 2016-11-21 | 2018-01-24 | 2018-09-18 | 2018-09-18 | COMP | 2019-03-05 | COMP | 2019-03-06 | COMP | 2019-08-15 | COMP | 2019-12-19 | COMP | Rule 16 | 294 | 166 | 114 | 2 | 115 | 87 | 773
3380 | 2016-11-21 | 2018-04-16 | 2018-08-04 | 2018-08-04 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-12-09 | COMP | 2020-03-06 | COMP | Rule 16 | 351 | 78 | 179 | 1 | 159 | 61 | 825
6268 | 2016-11-21 | 2018-08-07 | 2018-10-03 | 2018-10-03 | COMP | 2019-04-02 | COMP | 2019-07-29 | COMP | 2020-05-27 | COMP | 2020-07-23 | COMP | Rule 15/16 | 430 | 41 | 123 | 83 | 209 | 42 | 923
841 | 2016-11-22 | 2016-12-15 | 2017-04-29 | 2017-04-29 | COMP | 2017-06-05 | COMP | 2017-07-10 | COMP | 2017-07-19 | COMP | 2019-03-15 | COMP | Rule 16 | 16 | 94 | 25 | 25 | 8 | 415 | 579
882 | 2016-11-22 | 2017-01-17 | 2017-10-18 | 2017-10-18 | COMP | 2018-02-13 | COMP | 2018-02-16 | COMP | 2021-04-13 | COMP | 2021-05-20 | COMP | Rule 16 | 37 | 193 | 79 | 4 | 793 | 28 | 1129
1261 | 2016-11-22 | 2017-05-02 | 2018-02-20 | 2018-02-20 | COMP | 2018-07-16 | COMP | 2019-02-12 | COMP | 2019-02-06 | COMP | 2019-03-25 | COMP | Rule 15/16 | 111 | 201 | 103 | 145 | 0 | 29 | 585
4126 | 2016-11-22 | 2019-03-18 | 2021-02-22 | 2021-02-22 | COMP |  | INPR | 2022-01-03 | COMP |  | INPR | 2022-11-22 | COMP | Rule 15/16 | 580 | 487 |  | 220 |  |  | 1509
4446 | 2016-11-22 | 2017-12-11 | 2018-05-23 | 2018-05-23 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2019-01-07 | COMP | 2019-01-30 | COMP | Rule 16 | 264 | 114 | 4 | 1 | 153 | 17 | 548
1001 | 2016-11-23 | 2017-02-23 | 2017-04-17 | 2017-04-17 | COMP | 2017-05-16 | COMP | 2017-05-18 | COMP | 2021-10-23 | INPR | 2020-04-08 | COMP | Rule 16 | 62 | 38 | 22 | 3 |  |  | 846
1473 | 2016-11-23 | 2017-06-08 | 2018-03-11 | 2018-03-11 | COMP | 2018-08-03 | COMP | 2018-08-07 | COMP | 2019-10-30 | COMP | 2020-01-07 | COMP | Rule 16 | 136 | 188 | 103 | 3 | 311 | 45 | 782
1523 | 2016-11-23 | 2017-06-15 | 2018-05-02 | 2018-05-02 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2021-01-30 | INPR | 2020-01-06 | COMP | Rule 15/16 | 141 | 221 | 347 | 1 |  |  | 781
4828 | 2016-11-23 | 2018-04-02 | 2019-01-07 | 2019-01-07 | COMP | 2019-05-14 | COMP | 2019-06-07 | COMP | 2019-08-29 | COMP | 2019-09-25 | COMP | Rule 15/16 | 339 | 193 | 90 | 18 | 59 | 19 | 713
850 | 2016-11-25 | 2016-12-20 | 2017-07-05 | 2017-07-05 | COMP | 2019-07-23 | COMP | 2019-09-11 | COMP | 2019-10-16 | COMP | 2019-11-08 | COMP | Rule 15/16 | 17 | 137 | 515 | 36 | 26 | 18 | 744
811 | 2016-11-28 | 2016-12-06 | 2018-04-18 | 2018-04-18 | COMP | 2017-11-15 | NOTN | 2018-05-04 | COMP | 2021-06-16 | COMP | 2021-08-24 | COMP | Other | 7 | 344 |  | 13 | 784 | 49 | 1193
861 | 2016-11-28 | 2016-12-31 | 2017-04-11 | 2017-04-11 | COMP | 2019-10-05 | NOTN | 2019-10-22 | COMP | 2019-10-05 | COMP | 2019-12-06 | COMP | Other | 24 | 70 |  | 638 | 0 | 31 | 761
955 | 2016-11-28 | 2017-02-15 | 2017-05-30 | 2018-05-25 | COMP | 2018-06-19 | COMP | 2018-02-28 | COMP | 2018-11-20 | COMP | 2019-02-25 | COMP | Rule 15/16 | 56 | 73 | 17 |  | 186 | 64 | 563
1024 | 2016-11-28 | 2017-03-02 | 2018-05-24 | 2018-11-01 | COMP | 2018-12-03 | COMP | 2019-06-25 | COMP | 2019-07-02 | COMP | 2019-09-03 | COMP | Rule 16 | 66 | 311 | 20 | 142 | 6 | 44 | 696
1049 | 2016-11-28 | 2017-03-13 | 2017-08-23 | 2017-08-23 | COMP | 2018-05-04 | COMP | 2018-05-04 | COMP | 2019-01-31 | COMP | 2019-04-10 | COMP | Rule 16 | 73 | 116 | 175 | 1 | 186 | 49 | 595
1262 | 2016-11-28 | 2017-05-02 | 2017-08-18 | 2017-08-18 | COMP | 2017-09-06 | COMP | 2018-02-26 | COMP | 2022-01-28 | COMP | 2023-07-11 | COMP | Rule 16 | 109 | 77 | 13 | 117 | 989 | 363 | 1663
2212 | 2016-11-28 | 2017-10-13 | 2017-11-08 | 2017-11-08 | COMP | 2018-03-20 | COMP | 2018-03-26 | COMP | 2019-02-14 | COMP | 2019-04-16 | COMP | Rule 16 | 224 | 19 | 88 | 5 | 225 | 43 | 599
3145 | 2016-11-28 | 2018-03-15 | 2020-06-13 | 2020-06-13 | COMP | 2020-07-08 | COMP | 2022-01-05 | COMP | 2023-04-01 | INPR | 2022-03-02 | COMP | Rule 16 | 326 | 566 | 18 | 377 |  |  | 1323
3762 | 2016-11-28 | 2018-06-29 | 2018-10-05 | 2020-09-24 | COMP | 2020-12-31 | COMP | 2021-03-18 | COMP | 2021-03-08 | COMP | 2021-04-26 | COMP | Rule 16 | 401 | 69 | 67 | 53 | 0 | 28 | 1109
1164 | 2016-11-29 | 2017-04-11 | 2017-12-04 | 2017-12-04 | COMP | 2019-04-16 | COMP | 2019-10-21 | COMP | 2019-10-15 | COMP | 2019-11-08 | COMP | Rule 15/16 | 93 | 164 | 343 | 132 | 0 | 15 | 743
1195 | 2016-11-29 | 2017-04-18 | 2017-07-18 | 2017-07-18 | COMP | 2017-09-13 | COMP | 2019-03-18 | COMP | 2021-02-27 | INPR | 2020-02-07 | COMP | Rule 16 | 98 | 64 | 41 | 377 |  |  | 802
4522 | 2016-11-29 | 2018-01-20 | 2018-09-17 | 2018-09-17 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2021-01-30 | INPR | 2020-01-10 | COMP | Rule 16 | 287 | 167 | 97 | 1 |  |  | 783
6456 | 2016-11-29 | 2018-08-20 | 2019-02-19 | 2019-02-19 | COMP | 2019-10-15 | COMP | 2020-03-05 | COMP | 2020-02-13 | COMP | 2020-06-20 | COMP | Rule 16 | 435 | 124 | 168 | 96 | 0 | 76 | 895
888 | 2016-11-30 | 2017-01-19 | 2017-06-05 | 2017-08-03 | COMP | 2018-01-16 | COMP | 2018-01-17 | COMP | 2018-11-30 | COMP | 2020-06-17 | COMP | Rule 15/16 | 35 | 96 | 112 | 2 | 221 | 389 | 892
889 | 2016-11-30 | 2017-01-20 | 2017-02-10 | 2017-02-10 | COMP | 2017-02-24 | COMP | 2017-07-10 | COMP | 2019-12-19 | COMP | 2020-02-18 | COMP | Rule 16 | 36 | 16 | 10 | 95 | 615 | 40 | 807
1524 | 2016-11-30 | 2017-06-15 | 2017-12-02 | 2017-12-02 | COMP | 2018-07-11 | COMP | 2018-09-06 | COMP | 2020-04-16 | COMP | 2020-05-29 | COMP | Rule 16 | 138 | 117 | 152 | 41 | 404 | 31 | 879
6207 | 2016-11-30 | 2018-08-03 | 2019-05-16 | 2019-07-15 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-09-15 | COMP | 2019-11-21 | COMP | Rule 16 | 423 | 197 | 27 | 1 | 18 | 48 | 750
809 | 2016-12-01 | 2016-12-05 | 2017-06-17 | 2017-06-17 | COMP | 2018-03-10 | COMP | 2019-02-28 | COMP | 2019-03-08 | COMP | 2019-07-31 | COMP | Rule 15/16 | 3 | 136 | 181 | 244 | 7 | 102 | 670
905 | 2016-12-01 | 2017-01-26 | 2017-06-21 | 2018-01-09 | COMP | 2019-01-30 | COMP | 2018-05-04 | COMP | 2019-03-04 | COMP | 2019-04-18 | COMP | Rule 16 | 39 | 103 | 266 |  | 207 | 34 | 598
1021 | 2016-12-01 | 2017-03-02 | 2017-05-09 | 2017-05-09 | COMP | 2019-01-17 | COMP | 2018-06-28 | COMP | 2018-06-19 | COMP | 2019-01-27 | COMP | Rule 16 | 63 | 49 | 425 |  | 0 | 144 | 540
1704 | 2016-12-01 | 2017-07-18 | 2018-02-02 | 2018-02-02 | COMP | 2018-04-27 | COMP | 2018-04-27 | COMP | 2018-12-03 | COMP | 2019-01-08 | COMP | Rule 16 | 159 | 137 | 60 | 1 | 151 | 25 | 528
2936 | 2016-12-01 | 2018-02-20 | 2018-05-21 | 2018-05-21 | COMP | 2019-05-30 | COMP | 2019-06-03 | COMP | 2021-09-21 | COMP | 2021-10-13 | COMP | Rule 16 | 306 | 65 | 258 | 3 | 581 | 17 | 1225
817 | 2016-12-02 | 2016-12-08 | 2017-01-03 | 2017-01-03 | COMP | 2018-04-30 | COMP | 2018-05-01 | COMP | 2020-08-04 | COMP | 2020-09-14 | COMP | Rule 16 | 5 | 18 | 333 | 2 | 570 | 29 | 952
916 | 2016-12-02 | 2017-01-30 | 2017-06-29 | 2017-06-29 | COMP | 2017-11-01 | COMP | 2018-10-16 | COMP | 2018-10-16 | COMP | 2019-01-11 | COMP | Rule 15/16 | 40 | 107 | 88 | 240 | 1 | 59 | 530
1237 | 2016-12-02 | 2017-04-27 | 2018-01-04 | 2018-01-04 | COMP | 2018-03-28 | COMP | 2019-01-07 | COMP | 2023-04-29 | INPR | 2021-05-24 | COMP | Rule 15/16 | 102 | 173 | 58 | 196 |  |  | 1125
2772 | 2016-12-02 | 2018-01-30 | 2018-08-06 | 2018-08-06 | COMP | 2018-08-29 | COMP | 2018-10-30 | COMP | 2018-10-09 | COMP | 2019-04-27 | COMP | Rule 15/16 | 291 | 132 | 18 | 44 | 0 | 122 | 603
4838 | 2016-12-02 | 2018-04-09 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-14 | COMP | 2019-04-17 | COMP | 2019-04-03 | COMP | 2019-11-19 | COMP | Rule 16 | 339 | 147 | 8 | 105 | 0 | 151 | 746
5048 | 2016-12-02 | 2018-04-26 | 2018-10-28 | 2018-10-28 | COMP | 2018-11-01 | COMP | 2018-11-13 | COMP | 2019-05-09 | COMP | 2019-05-16 | COMP | Rule 16 | 352 | 129 | 4 | 8 | 122 | 6 | 617
10889 | 2016-12-02 | 2019-04-03 | 2019-04-11 | 2019-04-24 | COMP | 2019-04-24 | NOTN | 2019-04-24 | COMP | 2019-09-02 | INPR | 2019-05-06 | COMP | Rule 16 | 586 | 7 |  | 1 |  |  | 609
1179 | 2016-12-05 | 2017-04-14 | 2017-12-28 | 2017-10-17 | COMP | 2017-11-07 | COMP | 2017-12-28 | COMP | 2019-03-20 | COMP | 2019-04-15 | COMP | Rule 16 | 92 | 178 | 16 | 34 | 307 | 19 | 593
1291 | 2016-12-05 | 2017-05-05 | 2018-01-22 | 2018-01-22 | COMP | 2018-08-01 | COMP | 2018-08-01 | COMP | 2018-12-19 | COMP | 2019-02-08 | COMP | Rule 16 | 107 | 178 | 135 | 1 | 97 | 35 | 548
1294 | 2016-12-05 | 2017-05-05 | 2017-11-20 | 2017-11-20 | COMP | 2018-06-05 | COMP | 2018-07-17 | COMP | 2018-11-19 | COMP | 2019-05-20 | COMP | Rule 16 | 107 | 138 | 135 | 30 | 88 | 125 | 618
1507 | 2016-12-05 | 2017-06-13 | 2017-07-30 | 2017-07-30 | COMP | 2017-08-28 | COMP | 2017-08-28 | COMP | 2017-08-30 | COMP | 2020-11-11 | COMP | Rule 16 | 133 | 33 | 21 | 1 | 3 | 805 | 992
3449 | 2016-12-05 | 2018-04-28 | 2018-05-23 | 2018-05-23 | COMP | 2018-12-24 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2019-04-08 | COMP | Rule 15/16 | 352 | 18 | 148 | 29 | 1 | 44 | 588
1015 | 2016-12-06 | 2017-02-28 | 2017-10-18 | 2019-02-02 | COMP | 2019-07-29 | COMP | 2019-09-03 | COMP | 2019-08-20 | COMP | 2019-11-06 | COMP | Rule 15/16 | 58 | 164 | 123 | 26 | 0 | 47 | 736
2147 | 2016-12-06 | 2017-09-29 | 2017-12-22 | 2017-12-22 | COMP | 2019-10-21 | COMP | 2020-02-13 | COMP | 2020-02-14 | COMP | 2020-04-08 | COMP | Rule 16 | 208 | 58 | 460 | 78 | 2 | 38 | 839
873 | 2016-12-07 | 2017-01-09 | 2017-03-31 | 2017-04-10 | COMP | 2017-05-22 | NOTN | 2017-09-07 | COMP | 2019-11-14 | COMP | 2021-03-05 | COMP | Rule 16 | 23 | 58 |  | 106 | 550 | 327 | 1066
956 | 2016-12-07 | 2017-02-15 | 2017-08-14 | 2017-08-14 | COMP | 2018-03-10 | COMP | 2020-10-23 | COMP | 2020-10-27 | COMP | 2020-12-23 | COMP | Rule 15/16 | 49 | 126 | 142 | 663 | 3 | 39 | 1018
1387 | 2016-12-07 | 2017-05-24 | 2017-07-10 | 2017-07-10 | COMP | 2017-07-11 | COMP | 2017-08-15 | COMP | 2017-10-17 | COMP | 2022-02-04 | COMP | Rule 16 | 118 | 32 | 2 | 26 | 45 | 1081 | 1299
1487 | 2016-12-07 | 2017-06-09 | 2018-04-17 | 2017-06-22 | COMP | 2017-08-03 | COMP | 2018-04-23 | COMP | 2019-09-24 | COMP | 2019-10-14 | COMP | Rule 16 | 129 | 214 | 30 | 180 | 359 | 15 | 718
1624 | 2016-12-07 | 2017-07-05 | 2017-12-28 | 2017-09-18 | COMP | 2017-10-24 | COMP | 2018-01-18 | COMP | 2018-12-05 | COMP | 2019-05-10 | COMP | Other | 146 | 122 | 27 | 57 | 223 | 109 | 610
4438 | 2016-12-07 | 2017-12-09 | 2018-05-25 | 2018-05-25 | COMP | 2018-11-16 | COMP | 2019-04-05 | COMP | 2019-03-15 | COMP | 2019-04-27 | COMP | Rule 16 | 254 | 116 | 122 | 95 | 0 | 16 | 600
7537 | 2016-12-07 | 2018-10-18 | 2019-03-25 | 2019-07-18 | COMP | 2019-08-20 | COMP | 2019-10-18 | COMP | 2019-11-13 | COMP | 2020-01-08 | COMP | Rule 16 | 471 | 106 | 24 | 43 | 18 | 37 | 775
823 | 2016-12-08 | 2016-12-09 | 2016-12-12 | 2016-12-12 | COMP |  |  |  |  | 2016-12-30 | COMP | 2022-07-21 | COMP | Other | 2 | 2 |  |  |  |  | 1413
857 | 2016-12-08 | 2016-12-28 | 2017-09-20 | 2017-09-20 | COMP | 2018-04-25 | COMP | 2020-05-09 | COMP | 2020-03-02 | COMP | 2020-06-26 | COMP | Rule 16 | 14 | 186 | 149 | 513 | 0 | 34 | 893
863 | 2016-12-08 | 2017-01-03 | 2017-03-02 | 2017-03-02 | COMP | 2017-05-05 | COMP | 2017-05-05 | COMP | 2018-09-20 | COMP | 2019-08-15 | COMP | Rule 16 | 18 | 41 | 47 | 1 | 347 | 227 | 676
923 | 2016-12-08 | 2017-02-02 | 2017-03-07 | 2017-03-07 | COMP | 2017-04-17 | COMP | 2017-04-29 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | Rule 16 | 39 | 23 | 30 | 10 | 476 | 1 | 575
1608 | 2016-12-08 | 2017-06-30 | 2018-06-11 | 2018-06-11 | COMP | 2018-06-27 | COMP | 2019-01-07 | NOTN | 2019-01-16 | COMP | 2019-02-21 | COMP | Rule 16 | 143 | 237 | 13 |  |  |  | 553
4681 | 2016-12-08 | 2018-03-13 | 2018-03-20 | 2018-03-20 | COMP | 2018-03-27 | COMP | 2018-03-27 | COMP | 2019-02-25 | COMP | 2019-03-12 | COMP | Rule 16 | 316 | 6 | 6 | 1 | 230 | 12 | 566
902 | 2016-12-09 | 2017-01-25 | 2017-08-06 | 2017-08-06 | COMP | 2018-04-25 | COMP | 2018-05-10 | COMP | 2020-05-15 | COMP | 2020-07-31 | COMP | Rule 16 | 32 | 135 | 180 | 12 | 507 | 55 | 917
1758 | 2016-12-09 | 2017-07-19 | 2017-12-21 | 2017-12-21 | COMP | 2018-08-31 | COMP | 2019-01-17 | COMP | 2018-11-26 | COMP | 2019-01-23 | COMP | Rule 16 | 154 | 108 | 176 | 94 | 0 | 4 | 532
2046 | 2016-12-10 | 2017-09-12 | 2018-02-21 | 2018-02-21 | COMP | 2018-03-27 | COMP | 2018-10-22 | COMP | 2018-11-19 | COMP | 2020-03-06 | COMP | Rule 15/16 | 191 | 110 | 25 | 147 | 20 | 324 | 812
10261 | 2016-12-10 | 2019-03-07 | 2019-05-13 | 2019-05-13 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2020-01-24 | COMP | 2020-02-12 | COMP | Rule 16 | 561 | 48 | 96 | 1 | 81 | 14 | 796
1175 | 2016-12-11 | 2017-04-14 | 2017-05-08 | 2017-05-08 | COMP | 2017-05-17 | COMP | 2017-05-17 | COMP | 2019-01-22 | COMP | 2019-03-06 | COMP | Rule 16 | 87 | 17 | 8 | 1 | 421 | 31 | 560
858 | 2016-12-12 | 2016-12-28 | 2017-03-16 | 2017-03-16 | COMP | 2017-10-18 | COMP | 2017-10-17 | COMP | 2019-02-27 | COMP | 2019-03-25 | COMP | Rule 16 | 12 | 55 | 152 |  | 340 | 19 | 573
906 | 2016-12-12 | 2017-01-26 | 2017-07-26 | 2017-07-26 | COMP | 2017-08-10 | COMP | 2019-01-17 | COMP | 2019-01-23 | COMP | 2019-03-01 | COMP | Rule 16 | 32 | 127 | 12 | 360 | 4 | 27 | 557
927 | 2016-12-12 | 2017-02-02 | 2017-04-06 | 2017-04-06 | COMP | 2017-04-12 | COMP | 2017-04-12 | COMP | 2019-01-03 | COMP | 2019-02-11 | COMP | Rule 16 | 37 | 45 | 5 | 1 | 434 | 27 | 544
1339 | 2016-12-12 | 2017-05-13 | 2017-07-17 | 2017-07-17 | COMP | 2017-10-17 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-08-31 | COMP | Rule 16 | 107 | 44 | 66 | 412 | 1 | 59 | 685
992 | 2016-12-13 | 2017-02-22 | 2017-11-08 | 2017-11-08 | COMP | 2018-03-06 | COMP | 2018-08-29 | COMP | 2019-09-10 | COMP | 2019-10-21 | COMP | Rule 16 | 49 | 183 | 78 | 125 | 259 | 30 | 719
1043 | 2016-12-13 | 2017-03-09 | 2017-08-07 | 2017-08-07 | COMP | 2018-03-05 | COMP | 2018-03-05 | COMP | 2019-01-03 | COMP | 2019-01-30 | COMP | Rule 15/16 | 60 | 106 | 143 | 1 | 211 | 19 | 535
1151 | 2016-12-13 | 2017-04-08 | 2018-11-15 | 2019-01-27 | COMP | 2019-04-09 | COMP | 2020-03-20 | COMP | 2020-05-04 | COMP | 2020-06-20 | COMP | Rule 15/16 | 81 | 405 | 51 | 239 | 32 | 34 | 885
1152 | 2016-12-13 | 2017-04-08 | 2019-05-16 | 2019-05-16 | COMP | 2019-07-30 | COMP | 2020-06-30 | COMP | 2020-08-21 | COMP | 2020-09-23 | COMP | Rule 16 | 81 | 529 | 52 | 232 | 39 | 23 | 952
1267 | 2016-12-13 | 2017-05-03 | 2017-08-16 | 2017-08-16 | COMP | 2019-02-06 | COMP | 2019-03-25 | COMP | 2019-05-13 | COMP | 2019-06-16 | COMP | Rule 15/16 | 99 | 74 | 369 | 33 | 36 | 24 | 630
2257 | 2016-12-13 | 2017-10-25 | 2018-03-24 | 2018-03-24 | COMP | 2018-05-02 | COMP | 2018-08-25 | COMP | 2019-04-20 | INPR | 2019-01-31 | COMP | Rule 16 | 221 | 101 | 28 | 81 |  |  | 536
961 | 2016-12-14 | 2017-02-17 | 2018-01-04 | 2019-09-09 | COMP | 2020-11-24 | COMP | 2021-04-07 | COMP | 2021-07-28 | COMP | 2021-08-25 | COMP | Rule 15/16 | 46 | 221 | 307 | 91 | 79 | 21 | 1182
1650 | 2016-12-14 | 2017-07-10 | 2018-02-20 | 2018-02-20 | COMP | 2018-10-11 | COMP | 2019-01-07 | COMP | 2019-05-01 | COMP | 2019-05-13 | COMP | Rule 16 | 144 | 154 | 165 | 58 | 81 | 9 | 606
2198 | 2016-12-14 | 2017-10-09 | 2018-04-10 | 2018-04-10 | COMP | 2018-05-23 | COMP | 2019-07-23 | COMP |  | INPR | 2020-11-17 | COMP | Rule 16 | 208 | 125 | 32 | 293 |  |  | 989
831 | 2016-12-15 | 2016-12-15 | 2017-07-28 | 2020-04-16 | COMP | 2018-01-05 | COMP | 2020-04-22 | COMP | 2021-10-23 | INPR | 2020-07-13 | COMP | Rule 16 | 1 | 157 |  | 577 |  |  | 899
959 | 2016-12-15 | 2017-02-15 | 2018-08-16 | 2018-08-16 | COMP | 2018-08-27 | COMP | 2019-03-27 | COMP | 2018-12-04 | COMP | 2019-04-18 | COMP | Rule 16 | 43 | 379 | 8 | 145 | 0 | 17 | 588
2055 | 2016-12-15 | 2017-09-15 | 2018-04-10 | 2019-03-06 | COMP | 2018-12-17 | COMP | 2019-03-08 | COMP | 2019-04-11 | COMP | 2019-04-26 | COMP | Rule 15/16 | 191 | 141 |  | 56 | 25 | 12 | 594
2337 | 2016-12-15 | 2017-11-06 | 2018-06-13 | 2019-01-15 | COMP | 2020-02-28 | COMP | 2020-03-23 | COMP | 2020-04-30 | COMP | 2020-05-25 | COMP | Rule 16 | 227 | 150 | 282 | 17 | 29 | 17 | 864
2695 | 2016-12-15 | 2018-01-20 | 2018-06-12 | 2018-06-12 | COMP | 2018-08-14 | COMP | 2018-10-22 | COMP | 2019-02-08 | COMP | 2019-03-21 | COMP | Rule 15/16 | 275 | 100 | 45 | 49 | 74 | 29 | 568
2734 | 2016-12-15 | 2018-01-25 | 2018-10-19 | 2019-07-26 | COMP | 2020-11-24 | COMP | 2021-01-26 | COMP |  | INPR | 2021-09-07 | COMP | Rule 15/16 | 279 | 188 | 337 | 41 |  |  | 1189
887 | 2016-12-16 | 2017-01-18 | 2018-01-12 | 2018-01-12 | COMP | 2018-09-21 | COMP | 2020-06-09 | COMP | 2021-09-15 | COMP | 2020-07-23 | COMP | Rule 16 | 22 | 249 | 176 | 430 | 321 |  | 906
945 | 2016-12-16 | 2017-02-09 | 2017-05-20 | 2017-05-20 | COMP | 2019-08-06 | COMP | 2019-08-15 | COMP | 2019-09-05 | COMP | 2019-09-20 | COMP | Other | 38 | 71 | 555 | 8 | 15 | 12 | 695
946 | 2016-12-16 | 2017-02-09 | 2017-05-10 | 2017-05-10 | COMP | 2017-10-10 | COMP | 2018-01-04 | COMP | 2018-12-21 | COMP | 2019-07-24 | COMP | Other | 38 | 64 | 107 | 58 | 244 | 148 | 654
1117 | 2016-12-16 | 2017-03-28 | 2018-06-12 | 2019-12-26 | COMP | 2020-03-06 | COMP | 2020-11-12 | COMP | 2021-01-07 | COMP | 2021-02-19 | COMP | Rule 15/16 | 70 | 305 | 49 | 177 | 37 | 30 | 1049
1941 | 2016-12-16 | 2017-08-23 | 2017-11-21 | 2017-11-21 | COMP | 2019-01-02 | COMP | 2019-08-02 | COMP | 2021-02-23 | COMP | 2021-02-24 | COMP | Rule 15/16 | 174 | 63 | 278 | 149 | 391 | 2 | 1052
2118 | 2016-12-16 | 2017-09-26 | 2017-10-30 | 2017-10-30 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2020-03-27 | COMP | 2020-07-16 | COMP | Rule 16 | 197 | 25 | 408 | 1 | 196 | 79 | 901
5015 | 2016-12-16 | 2018-04-23 | 2018-08-30 | 2018-08-30 | COMP | 2019-03-25 | COMP | 2019-10-17 | COMP |  |  | 2019-10-30 | COMP | Rule 16 | 339 | 92 | 140 | 146 |  |  | 723
5294 | 2016-12-16 | 2018-05-18 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-09 | COMP | 2019-01-14 | COMP | 2019-08-20 | COMP | 2019-09-03 | COMP | Rule 16 | 358 | 103 | 21 | 42 | 153 | 10 | 682
1251 | 2016-12-18 | 2017-05-01 | 2017-07-07 | 2017-07-07 | COMP | 2017-07-18 | COMP | 2019-02-05 | COMP | 2019-11-23 | INPR | 2019-05-07 | COMP | Rule 16 | 93 | 48 | 8 | 389 |  |  | 599
1264 | 2016-12-18 | 2017-05-02 | 2017-05-23 | 2017-05-23 | COMP | 2017-06-19 | COMP | 2019-01-26 | COMP | 2020-01-31 | COMP | 2019-05-06 | COMP | Rule 16 | 94 | 16 | 19 | 402 | 255 |  | 598
1415 | 2016-12-18 | 2017-06-01 | 2017-08-02 | 2017-08-02 | COMP | 2017-08-15 | COMP | 2017-10-17 | COMP | 2020-01-09 | COMP | 2020-03-25 | COMP | Rule 16 | 115 | 44 | 10 | 45 | 558 | 53 | 820
1476 | 2016-12-18 | 2017-06-08 | 2017-08-17 | 2017-08-17 | COMP | 2017-08-30 | COMP | 2017-09-30 | COMP | 2020-01-09 | COMP | 2020-03-27 | COMP | Rule 16 | 120 | 50 | 10 | 22 | 569 | 55 | 822
1480 | 2016-12-18 | 2017-06-08 | 2017-09-19 | 2017-09-19 | COMP | 2019-11-14 | COMP | 2019-12-10 | INPR | 2021-04-24 | REQD | 2020-03-27 | COMP | Rule 16 | 120 | 72 | 542 |  |  |  | 822
1481 | 2016-12-18 | 2017-06-08 | 2017-08-18 | 2017-08-18 | COMP | 2017-08-30 | COMP | 2017-09-11 | COMP | 2020-01-09 | COMP | 2020-05-22 | COMP | Rule 16 | 120 | 51 | 9 | 8 | 584 | 95 | 862
2098 | 2016-12-18 | 2017-09-22 | 2018-01-09 | 2018-01-09 | COMP | 2019-11-14 | COMP | 2019-11-14 | INPR |  | REQD | 2020-03-26 | COMP | Rule 16 | 194 | 73 | 467 |  |  |  | 821
909 | 2016-12-19 | 2017-01-27 | 2017-03-10 | 2017-03-10 | COMP | 2017-04-05 | COMP | 2017-04-05 | COMP | 2019-04-19 | COMP | 2019-04-25 | COMP | Rule 16 | 28 | 30 | 19 | 1 | 513 | 5 | 591
936 | 2016-12-19 | 2017-02-07 | 2017-08-31 | 2017-08-31 | COMP | 2017-10-03 | COMP | 2017-11-29 | COMP | 2018-10-03 | COMP | 2019-05-31 | COMP | Rule 15/16 | 35 | 145 | 23 | 39 | 214 | 165 | 616
1006 | 2016-12-19 | 2017-02-27 | 2018-02-14 | 2018-02-14 | COMP | 2018-08-13 | COMP | 2018-08-30 | COMP | 2021-02-02 | COMP | 2021-02-20 | COMP | Rule 15/16 | 48 | 244 | 126 | 14 | 608 | 13 | 1048
1037 | 2016-12-19 | 2017-03-06 | 2017-06-01 | 2017-06-01 | COMP | 2017-06-20 | COMP | 2018-03-15 | COMP | 2022-05-04 | COMP | 2022-07-30 | COMP | Rule 16 | 53 | 63 | 14 | 184 | 1043 | 60 | 1412
1066 | 2016-12-19 | 2017-03-18 | 2017-06-22 | 2017-06-22 | COMP | 2017-07-25 | COMP | 2018-04-25 | COMP | 2019-10-25 | COMP | 2020-08-11 | COMP | Rule 16 | 62 | 68 | 23 | 189 | 380 | 200 | 918
1067 | 2016-12-19 | 2017-03-18 | 2017-06-21 | 2017-06-21 | COMP | 2017-07-25 | COMP | 2018-04-23 | COMP | 2019-10-25 | COMP | 2022-03-30 | COMP | Rule 16 | 62 | 67 | 24 | 187 | 382 | 610 | 1328
1414 | 2016-12-19 | 2017-06-01 | 2017-08-02 | 2017-08-02 | COMP | 2017-08-15 | COMP | 2017-10-17 | COMP | 2020-01-09 | COMP | 2020-07-24 | COMP | Rule 16 | 115 | 44 | 10 | 45 | 558 | 139 | 906
1482 | 2016-12-19 | 2017-06-08 | 2017-08-11 | 2017-08-11 | COMP | 2017-08-29 | COMP | 2017-10-18 | COMP | 2021-05-04 | COMP | 2021-06-16 | COMP | Rule 16 | 120 | 46 | 13 | 36 | 889 | 31 | 1130
1483 | 2016-12-19 | 2017-06-08 | 2018-03-02 | 2018-03-02 | COMP | 2018-03-21 | COMP | 2019-01-14 | COMP | 2020-01-31 | COMP | 2022-06-10 | COMP | Rule 16 | 120 | 183 | 14 | 206 | 264 | 597 | 1379
3033 | 2016-12-19 | 2018-02-28 | 2018-10-11 | 2018-10-11 | COMP | 2018-11-08 | COMP | 2019-01-17 | COMP | 2019-04-04 | COMP | 2019-04-11 | COMP | Rule 15/16 | 300 | 159 | 21 | 46 | 54 | 6 | 581
4982 | 2016-12-19 | 2018-04-19 | 2019-01-24 | 2019-01-24 | COMP | 2020-02-19 | COMP | 2020-03-02 | COMP | 2020-03-10 | COMP | 2020-06-26 | COMP | Rule 16 | 336 | 192 | 269 | 9 | 7 | 78 | 886
7989 | 2016-12-19 | 2018-11-09 | 2019-06-17 | 2019-06-17 | COMP | 2019-11-18 | COMP | 2020-12-21 | COMP | 2020-12-15 | COMP | 2021-02-05 | COMP | Rule 16 | 479 | 149 | 108 | 275 | 0 | 32 | 1039
1171 | 2016-12-20 | 2017-04-13 | 2017-10-02 | 2017-10-02 | COMP | 2018-03-12 | COMP | 2018-03-14 | COMP | 2018-11-14 | COMP | 2019-01-25 | COMP | Other | 80 | 120 | 109 | 3 | 172 | 48 | 527
1369 | 2016-12-20 | 2017-05-18 | 2017-09-04 | 2017-09-04 | COMP | 2018-03-08 | COMP | 2018-03-08 | COMP | 2018-10-31 | COMP | 2019-02-11 | COMP | Rule 15/16 | 105 | 75 | 126 | 1 | 167 | 68 | 538
39173 | 2016-12-20 | 2022-10-05 | 2023-02-07 | 2023-02-07 | COMP | 2023-03-07 | NOTN | 2023-03-07 | COMP |  | INPR | 2023-04-26 | COMP | Other | 1458 | 84 |  | 20 |  |  | 1596
2253 | 2016-12-21 | 2017-10-24 | 2018-05-24 | 2018-05-24 | COMP | 2019-07-10 | COMP | 2018-09-06 | COMP | 2019-02-06 | COMP | 2019-04-19 | COMP | Rule 15/16 | 214 | 146 | 283 |  | 104 | 52 | 585
2520 | 2016-12-21 | 2017-12-14 | 2018-04-18 | 2018-06-06 | COMP | 2018-11-14 | COMP | 2019-05-30 | COMP | 2019-06-25 | COMP | 2019-08-29 | COMP | Rule 15/16 | 248 | 86 | 113 | 135 | 19 | 47 | 677
3204 | 2016-12-21 | 2018-03-22 | 2018-11-04 | 2018-11-04 | COMP | 2019-07-01 | COMP | 2020-03-20 | COMP | 2020-02-04 | COMP | 2020-06-02 | COMP | Rule 15/16 | 314 | 159 | 163 | 181 | 0 | 52 | 866
3224 | 2016-12-21 | 2018-03-24 | 2018-12-28 | 2019-01-14 | COMP | 2019-04-12 | COMP | 2019-05-02 | COMP | 2019-08-16 | COMP | 2019-10-14 | COMP | Rule 16 | 315 | 193 | 63 | 15 | 75 | 41 | 708
5008 | 2016-12-21 | 2018-04-23 | 2018-09-04 | 2018-09-04 | COMP | 2018-09-11 | COMP | 2018-09-25 | COMP | 2019-04-04 | COMP | 2019-04-18 | COMP | Rule 16 | 336 | 94 | 6 | 11 | 131 | 11 | 584
5811 | 2016-12-21 | 2018-07-05 | 2018-10-17 | 2018-10-17 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-08-14 | COMP | 2019-12-03 | COMP | Rule 15/16 | 387 | 74 | 132 | 1 | 76 | 76 | 741
6401 | 2016-12-21 | 2018-08-15 | 2019-01-02 | 2019-01-02 | COMP | 2019-01-11 | NOTN | 2019-11-19 | COMP | 2019-01-11 | COMP | 2019-12-06 | COMP | Other | 416 | 95 |  | 224 | 0 | 12 | 744
40974 | 2016-12-21 | 2023-02-13 | 2023-03-25 | 2023-03-25 | COMP | 2023-04-10 | COMP | 2023-04-27 | COMP | 2023-04-13 | COMP | 2023-05-23 | COMP | Rule 16 | 1544 | 29 | 11 | 14 | 0 | 19 | 1614
901 | 2016-12-22 | 2017-01-25 | 2017-09-11 | 2017-09-11 | COMP | 2017-12-27 | COMP | 2017-12-27 | COMP |  | INPR | 2019-04-24 | COMP | Other | 23 | 160 | 74 | 1 |  |  | 587
1232 | 2016-12-22 | 2017-04-26 | 2017-05-09 | 2018-11-01 | COMP | 2018-12-28 | COMP | 2019-03-23 | COMP | 2018-11-08 | COMP | 2021-04-17 | COMP | Rule 16 | 87 | 10 | 38 | 58 | 0 | 521 | 1085
1644 | 2016-12-22 | 2017-07-08 | 2017-09-11 | 2017-09-11 | COMP | 2018-07-25 | COMP | 2019-06-03 | COMP | 2021-12-25 | INPR | 2019-06-15 | COMP | Rule 16 | 137 | 45 | 219 | 215 |  |  | 623
1019 | 2016-12-24 | 2017-03-01 | 2017-03-06 | 2017-03-06 | COMP | 2017-04-05 | COMP | 2017-04-05 | COMP | 2019-06-29 | INPR | 2019-02-12 | COMP | Rule 16 | 45 | 4 | 23 | 1 |  |  | 535
1060 | 2016-12-27 | 2017-03-16 | 2018-02-02 | 2018-02-02 | COMP | 2018-05-01 | COMP | 2019-07-26 | COMP | 2019-06-24 | COMP | 2019-09-12 | COMP | Other | 56 | 223 | 62 | 312 | 0 | 34 | 683
1061 | 2016-12-27 | 2017-03-16 | 2017-05-26 | 2017-05-26 | COMP | 2017-12-04 | COMP | 2018-01-08 | COMP | 2020-03-21 | INPR | 2019-06-28 | COMP | Other | 56 | 52 | 131 | 24 |  |  | 631
1126 | 2016-12-27 | 2017-03-31 | 2017-05-26 | 2017-05-26 | COMP | 2017-12-04 | COMP | 2018-04-25 | COMP | 2023-04-22 | INPR | 2020-06-22 | COMP | Other | 67 | 41 | 131 | 99 |  |  | 877
1256 | 2016-12-27 | 2017-05-01 | 2017-05-10 | 2017-05-10 | COMP | 2017-12-04 | COMP | 2018-02-26 | COMP | 2022-07-16 | INPR | 2020-05-30 | COMP | Other | 88 | 8 | 143 | 57 |  |  | 861
6143 | 2016-12-27 | 2018-07-30 | 2019-04-04 | 2019-04-04 | COMP | 2019-11-19 | COMP | 2020-05-18 | INPR | 2020-05-13 | COMP | 2020-05-18 | COMP | Rule 15/16 | 401 | 171 | 160 |  |  |  | 853
6145 | 2016-12-27 | 2018-07-30 | 2019-03-28 | 2019-03-28 | COMP | 2019-11-19 | COMP | 2020-05-18 | COMP | 2020-05-13 | COMP | 2020-07-22 | COMP | Rule 15/16 | 401 | 166 | 165 | 124 | 0 | 47 | 899
870 | 2016-12-28 | 2017-01-08 | 2018-01-19 | 2018-01-30 | COMP | 2018-03-08 | COMP | 2018-03-08 | COMP | 2018-06-08 | COMP | 2019-02-25 | COMP | Rule 16 | 8 | 259 | 27 | 1 | 66 | 178 | 542
871 | 2016-12-28 | 2017-01-09 | 2017-02-04 | 2017-02-04 | COMP | 2017-03-15 | COMP | 2018-05-01 | COMP | 2018-03-30 | COMP | 2021-01-15 | COMP | Rule 16 | 9 | 19 | 27 | 285 | 0 | 682 | 1019
895 | 2016-12-28 | 2017-01-23 | 2017-05-19 | 2017-05-19 | COMP | 2017-06-09 | COMP | 2017-06-13 | COMP | 2019-04-05 | COMP | 2019-05-13 | COMP | Rule 16 | 18 | 84 | 15 | 3 | 455 | 27 | 597
1269 | 2016-12-28 | 2017-05-02 | 2018-10-09 | 2018-10-09 | COMP | 2019-03-22 | COMP | 2019-03-28 | COMP |  | INPR | 2020-07-08 | COMP | Rule 16 | 88 | 363 | 112 | 5 |  |  | 888
1437 | 2016-12-28 | 2017-06-01 | 2017-09-13 | 2018-04-06 | COMP | 2018-04-27 | COMP | 2018-05-02 | COMP | 2018-06-05 | COMP | 2019-04-06 | COMP | Rule 16 | 109 | 73 | 16 | 4 | 24 | 210 | 571
1477 | 2016-12-28 | 2017-06-08 | 2017-08-07 | 2017-08-07 | COMP | 2017-08-29 | COMP | 2017-10-16 | COMP | 2020-01-09 | COMP | 2020-03-27 | COMP | Rule 16 | 114 | 42 | 17 | 34 | 559 | 55 | 816
4574 | 2016-12-28 | 2018-02-06 | 2018-03-15 | 2018-10-01 | COMP | 2018-06-15 | COMP | 2018-06-15 | COMP | 2019-01-15 | COMP | 2019-03-25 | COMP | Rule 16 | 279 | 27 |  | 1 | 146 | 48 | 562
4767 | 2016-12-28 | 2018-03-27 | 2020-02-27 | 2020-02-27 | COMP | 2020-05-05 | COMP | 2020-07-23 | COMP | 2020-07-22 | COMP | 2020-10-13 | COMP | Rule 16 | 313 | 483 | 49 | 57 | 0 | 58 | 956
19120 | 2016-12-28 | 2020-04-22 | 2020-05-23 | 2020-05-23 | COMP | 2020-07-03 | COMP | 2020-07-30 | COMP | 2020-07-09 | COMP | 2020-08-12 | COMP | Rule 16 | 834 | 23 | 29 | 20 | 0 | 10 | 913
39193 | 2016-12-28 | 2022-10-05 | 2023-02-25 | 2023-02-25 | COMP | 2023-03-08 | NOTN | 2023-07-13 | COMP |  | INPR | 2023-08-31 | COMP | Other | 1453 | 96 |  | 96 |  |  | 1679
940 | 2016-12-29 | 2017-02-08 | 2018-02-12 | 2018-02-12 | COMP | 2018-05-23 | COMP | 2018-09-19 | COMP | 2019-04-29 | COMP | 2019-05-22 | COMP | Rule 15/16 | 29 | 254 | 72 | 83 | 152 | 18 | 603
993 | 2016-12-29 | 2017-02-22 | 2017-10-12 | 2017-10-12 | COMP | 2017-10-16 | COMP | 2017-11-08 | COMP | 2018-04-10 | COMP | 2019-01-07 | COMP | Rule 16 | 38 | 164 | 3 | 18 | 103 | 187 | 508
1475 | 2016-12-29 | 2017-06-08 | 2017-08-15 | 2018-08-16 | COMP | 2018-08-30 | COMP | 2018-11-13 | COMP |  |  | 2020-01-02 | COMP | Rule 16 | 113 | 48 | 11 | 52 |  |  | 756
2744 | 2016-12-29 | 2018-01-26 | 2018-10-01 | 2018-10-01 | COMP | 2019-05-23 | COMP | 2019-11-20 | COMP | 2019-11-21 | COMP | 2020-08-07 | COMP | Rule 15/16 | 271 | 173 | 162 | 126 | 2 | 180 | 909
3377 | 2016-12-29 | 2018-04-20 | 2018-09-15 | 2018-09-15 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2021-03-27 | INPR | 2020-03-12 | COMP | Rule 16 | 330 | 103 | 114 | 1 |  |  | 804
1667 | 2016-12-30 | 2017-07-14 | 2017-08-30 | 2017-08-30 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-06-12 | COMP | 2019-07-25 | COMP | Rule 16 | 137 | 34 | 420 | 1 | 28 | 31 | 646
1018 | 2017-01-03 | 2017-03-02 | 2017-08-31 | 2017-08-31 | COMP | 2017-09-07 | COMP | 2017-09-07 | COMP | 2019-07-03 | COMP | 2019-08-01 | COMP | Rule 16 | 41 | 129 | 5 | 1 | 457 | 21 | 649
1026 | 2017-01-03 | 2017-03-03 | 2017-06-26 | 2017-06-26 | COMP | 2018-12-12 | COMP | 2018-12-20 | COMP | 2018-12-18 | COMP | 2019-02-07 | COMP | Rule 16 | 42 | 81 | 368 | 7 | 0 | 33 | 527
1119 | 2017-01-03 | 2017-03-28 | 2017-10-10 | 2017-10-10 | COMP | 2018-04-09 | COMP | 2018-04-18 | COMP | 2018-07-23 | COMP | 2019-07-11 | COMP | Rule 15/16 | 59 | 138 | 123 | 8 | 67 | 244 | 634
1135 | 2017-01-03 | 2017-04-03 | 2020-01-28 | 2020-01-28 | COMP | 2019-09-09 | NOTN | 2020-07-27 | COMP | 2020-01-28 | COMP | 2020-12-08 | COMP | Other | 63 | 708 |  | 128 | 0 | 93 | 989
1327 | 2017-01-03 | 2017-05-10 | 2017-09-13 | 2017-09-13 | COMP | 2017-10-05 | COMP | 2017-12-29 | COMP | 2019-06-11 | COMP | 2019-06-25 | COMP | Rule 16 | 90 | 88 | 17 | 58 | 364 | 11 | 623
1373 | 2017-01-03 | 2017-05-19 | 2017-07-28 | 2018-10-08 | COMP | 2019-01-09 | COMP | 2017-08-28 | COMP | 2018-12-19 | COMP | 2019-02-12 | COMP | Rule 16 | 97 | 49 | 63 |  | 329 | 37 | 530
1571 | 2017-01-03 | 2017-06-26 | 2020-02-04 | 2020-02-04 | COMP | 2020-08-03 | COMP | 2021-05-04 | COMP |  | INPR | 2021-05-03 | COMP | Rule 16 | 122 | 654 | 128 | 189 |  |  | 1089
4373 | 2017-01-03 | 2017-11-03 | 2018-07-25 | 2018-07-25 | COMP | 2018-09-04 | COMP | 2019-01-15 | COMP | 2019-06-19 | COMP | 2019-07-18 | COMP | Rule 16 | 214 | 180 | 29 | 91 | 109 | 21 | 639
24758 | 2017-01-03 | 2021-01-11 | 2021-05-07 | 2021-05-07 | COMP | 2021-09-29 | COMP | 2021-08-03 | COMP | 2023-12-04 | INPR | 2021-08-16 | COMP | Rule 16 | 1011 | 83 | 101 |  |  |  | 1162
4412 | 2017-01-04 | 2017-11-27 | 2018-04-01 | 2018-04-01 | COMP | 2018-08-09 | COMP | 2018-08-09 | COMP | 2019-09-24 | COMP | 2019-10-09 | COMP | Rule 16 | 226 | 86 | 92 | 1 | 283 | 12 | 696
1062 | 2017-01-05 | 2017-03-16 | 2017-07-17 | 2017-07-17 | COMP | 2017-09-19 | COMP | 2017-09-19 | COMP | 2021-11-30 | COMP | 2022-02-23 | COMP | Rule 15/16 | 49 | 86 | 46 | 1 | 1054 | 60 | 1291
1299 | 2017-01-05 | 2017-05-05 | 2017-09-25 | 2017-09-25 | COMP | 2017-10-18 | COMP | 2017-10-27 | COMP | 2022-01-29 | INPR | 2020-11-02 | COMP | Rule 16 | 85 | 99 | 18 | 8 |  |  | 964
1449 | 2017-01-05 | 2017-06-06 | 2018-02-26 | 2018-07-19 | COMP | 2018-08-03 | COMP | 2019-04-12 | COMP | 2019-08-08 | COMP | 2019-08-21 | COMP | Rule 15/16 | 106 | 181 | 12 | 173 | 83 | 10 | 661
1664 | 2017-01-05 | 2017-07-13 | 2018-02-22 | 2018-02-22 | COMP | 2018-03-05 | COMP | 2019-02-13 | COMP | 2019-03-27 | COMP | 2019-05-13 | COMP | Rule 15/16 | 132 | 153 | 8 | 239 | 30 | 34 | 591
2242 | 2017-01-05 | 2017-10-20 | 2017-12-09 | 2017-12-09 | COMP | 2018-04-10 | COMP | 2018-04-10 | COMP | 2019-09-27 | COMP | 2019-05-07 | COMP | Rule 16 | 202 | 33 | 83 | 1 | 371 |  | 587
2243 | 2017-01-05 | 2017-10-20 | 2017-12-29 | 2019-01-03 | COMP | 2019-02-08 | COMP | 2019-06-11 | COMP |  |  | 2019-07-03 | COMP | Rule 16 | 202 | 47 | 26 | 86 |  |  | 627
2336 | 2017-01-05 | 2017-11-03 | 2018-02-12 | 2018-02-12 | COMP | 2018-03-10 | COMP | 2019-07-02 | COMP | 2020-03-27 | COMP | 2020-04-29 | COMP | Rule 16 | 212 | 66 | 19 | 331 | 185 | 24 | 833
3218 | 2017-01-05 | 2018-03-22 | 2018-12-04 | 2018-12-04 | COMP | 2019-04-02 | COMP | 2019-06-07 | COMP | 2019-06-11 | COMP | 2019-07-10 | COMP | Rule 15/16 | 304 | 178 | 82 | 48 | 3 | 21 | 631
4978 | 2017-01-05 | 2018-04-18 | 2018-04-19 | 2018-04-19 | COMP | 2018-04-30 | COMP | 2019-03-04 | COMP | 2019-08-30 | COMP | 2019-09-24 | COMP | Rule 16 | 323 | 2 | 8 | 211 | 128 | 17 | 684
896 | 2017-01-06 | 2017-01-23 | 2017-07-26 | 2017-07-26 | COMP | 2017-09-05 | COMP | 2019-03-21 | COMP | 2019-06-19 | COMP | 2019-07-30 | COMP | Rule 16 | 11 | 130 | 29 | 386 | 64 | 29 | 644
1778 | 2017-01-06 | 2017-07-24 | 2017-08-30 | 2017-08-30 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-02-26 | COMP | 2020-02-21 | COMP | Other | 138 | 28 | 597 | 1 | 27 |  | 784
1782 | 2017-01-06 | 2017-07-25 | 2017-09-14 | 2017-09-14 | COMP | 2017-10-22 | NOTN | 2017-10-22 | COMP | 2020-02-25 | COMP | 2020-06-02 | COMP | Other | 139 | 37 |  | 27 | 585 | 70 | 855
1786 | 2017-01-06 | 2017-07-26 | 2017-09-13 | 2017-09-13 | COMP | 2019-11-01 | NOTN | 2019-11-01 | INPR | 2020-01-21 | COMP | 2020-02-21 | COMP | Other | 140 | 35 |  |  |  |  | 784
1808 | 2017-01-06 | 2017-07-31 | 2017-09-02 | 2017-09-02 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP |  | INPR | 2019-11-14 | COMP | Other | 143 | 25 | 465 | 1 |  |  | 719
2448 | 2017-01-06 | 2017-12-01 | 2018-05-17 | 2018-05-17 | COMP | 2018-09-13 | COMP | 2018-12-04 | COMP | 2018-12-05 | COMP | 2019-04-05 | COMP | Rule 15 | 228 | 116 | 83 | 56 | 2 | 84 | 564
2561 | 2017-01-06 | 2017-12-26 | 2018-06-08 | 2018-06-08 | COMP | 2018-12-04 | COMP | 2018-08-30 | COMP | 2019-04-20 | INPR | 2019-01-10 | COMP | Rule 16 | 244 | 115 | 123 |  |  |  | 505
18243 | 2017-01-06 | 2020-03-16 | 2021-01-26 | 2021-01-26 | COMP | 2021-02-22 | COMP | 2021-03-18 | COMP | 2021-11-02 | COMP | 2022-01-12 | COMP | Rule 16 | 800 | 219 | 19 | 19 | 161 | 49 | 1262
963 | 2017-01-07 | 2017-02-21 | 2018-06-07 | 2018-06-07 | COMP | 2018-10-25 | COMP | 2019-03-27 | COMP | 2019-05-08 | COMP | 2019-06-07 | COMP | Rule 15/16 | 30 | 327 | 99 | 103 | 31 | 22 | 607
1145 | 2017-01-09 | 2017-04-05 | 2017-05-10 | 2019-01-08 | COMP | 2019-03-04 | COMP | 2019-03-08 | COMP | 2020-03-09 | COMP | 2019-04-23 | COMP | Other | 61 | 26 | 38 | 5 | 252 |  | 575
2847 | 2017-01-09 | 2018-02-07 | 2018-03-02 | 2018-03-02 | COMP | 2018-10-09 | COMP | 2018-10-11 | COMP | 2019-07-21 | INPR | 2019-03-13 | COMP | Rule 16 | 272 | 17 | 155 | 3 |  |  | 546
3516 | 2017-01-09 | 2018-05-10 | 2018-09-13 | 2018-09-13 | COMP | 2018-12-21 | COMP | 2019-02-07 | COMP | 2019-05-28 | COMP | 2019-06-06 | COMP | Rule 16 | 337 | 88 | 69 | 32 | 77 | 8 | 606
877 | 2017-01-10 | 2017-01-12 | 2017-01-22 | 2017-01-22 | COMP | 2017-03-07 | COMP | 2017-03-08 | COMP | 2017-03-08 | COMP | 2019-08-19 | COMP | Rule 16 | 3 | 6 | 31 | 2 | 1 | 617 | 656
1375 | 2017-01-10 | 2017-05-20 | 2017-08-11 | 2017-08-11 | COMP | 2017-09-29 | COMP | 2018-04-10 | COMP | 2018-05-01 | COMP | 2019-08-29 | COMP | Rule 16 | 92 | 58 | 35 | 131 | 16 | 336 | 664
1478 | 2017-01-10 | 2017-06-08 | 2017-08-07 | 2018-05-04 | COMP | 2018-05-29 | COMP | 2020-01-31 | COMP | 2020-02-10 | COMP | 2020-06-05 | COMP | Rule 16 | 105 | 42 | 17 | 421 | 7 | 83 | 856
1690 | 2017-01-10 | 2017-07-17 | 2018-02-02 | 2018-02-02 | COMP | 2018-02-12 | COMP | 2018-02-12 | COMP | 2018-10-17 | COMP | 2019-02-20 | COMP | Rule 16 | 131 | 138 | 7 | 1 | 174 | 84 | 530
2246 | 2017-01-10 | 2017-10-21 | 2017-12-03 | 2017-12-03 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2019-09-17 | COMP | 2019-10-21 | COMP | Rule 16 | 199 | 27 | 122 | 1 | 329 | 25 | 700
2406 | 2017-01-10 | 2017-11-17 | 2018-11-09 | 2018-11-09 | COMP | 2018-11-09 | NOTN | 2019-03-01 | COMP | 2018-11-09 | NOTN | 2019-06-21 | COMP | Other | 218 | 247 |  | 74 |  |  | 616
2585 | 2017-01-10 | 2018-01-02 | 2018-01-16 | 2018-01-16 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2018-01-09 | COMP | 2019-04-11 | COMP | Rule 15/16 | 246 | 10 | 226 | 1 | 0 | 87 | 566
1020 | 2017-01-11 | 2017-03-02 | 2017-06-05 | 2017-07-26 | COMP | 2019-07-22 | NOTN | 2017-08-07 | COMP | 2020-02-29 | INPR | 2019-11-11 | COMP | Rule 15/16 | 35 | 67 |  | 9 |  |  | 713
1074 | 2017-01-11 | 2017-03-20 | 2017-12-11 | 2017-12-11 | COMP | 2018-09-26 | COMP | 2019-03-18 | COMP | 2019-03-04 | COMP | 2019-05-31 | COMP | Rule 15/16 | 47 | 185 | 201 | 117 | 0 | 54 | 600
1097 | 2017-01-11 | 2017-03-24 | 2017-03-27 | 2017-03-27 | COMP | 2017-04-05 | COMP | 2017-04-03 | COMP | 2019-02-28 | COMP | 2019-04-11 | COMP | Rule 16 | 51 | 2 | 8 |  | 479 | 31 | 565
1302 | 2017-01-11 | 2017-05-05 | 2017-09-25 | 2017-09-25 | COMP | 2018-09-11 | COMP | 2018-09-11 | COMP | 2019-10-15 | COMP | 2019-10-31 | COMP | Rule 15/16 | 81 | 99 | 242 | 1 | 276 | 13 | 707
7135 | 2017-01-11 | 2018-09-28 | 2018-11-02 | 2018-11-11 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-07-03 | COMP | 2019-08-23 | COMP | Rule 16 | 433 | 26 | 18 | 1 | 143 | 37 | 659
7763 | 2017-01-11 | 2018-10-30 | 2019-04-23 | 2019-04-23 | COMP | 2020-05-04 | COMP | 2020-10-02 | COMP | 2020-09-30 | COMP | 2020-10-15 | COMP | Rule 16 | 455 | 119 | 260 | 108 | 0 | 10 | 948
23862 | 2017-01-11 | 2020-11-29 | 2021-06-07 | 2021-11-22 | COMP | 2022-05-27 | COMP | 2022-05-27 | COMP | 2023-02-21 | COMP | 2023-05-23 | COMP | Rule 15/16 | 976 | 131 | 131 | 1 | 182 | 66 | 1600
930 | 2017-01-12 | 2017-02-03 | 2017-05-26 | 2017-05-26 | COMP | 2017-08-14 | COMP | 2017-08-14 | COMP | 2019-07-06 | COMP | 2019-07-31 | COMP | Rule 16 | 16 | 80 | 55 | 1 | 475 | 18 | 641
1357 | 2017-01-12 | 2017-05-17 | 2017-07-19 | 2017-06-28 | COMP | 2018-02-28 | COMP | 2018-03-01 | COMP | 2018-09-21 | COMP | 2019-03-29 | COMP | Rule 15/16 | 88 | 44 | 167 | 2 | 144 | 129 | 555
1367 | 2017-01-12 | 2017-05-18 | 2018-10-12 | 2018-10-12 | COMP | 2019-06-25 | COMP | 2019-09-27 | COMP | 2020-02-29 | INPR | 2019-10-16 | COMP | Rule 16 | 89 | 354 | 175 | 67 |  |  | 695
1638 | 2017-01-12 | 2017-07-08 | 2017-07-14 | 2017-07-14 | COMP | 2017-12-21 | COMP | 2017-12-21 | COMP | 2019-02-22 | COMP | 2019-01-04 | COMP | Rule 16 | 123 | 5 | 111 | 1 | 293 |  | 497
1695 | 2017-01-12 | 2017-07-17 | 2017-11-19 | 2020-04-09 | COMP | 2020-06-10 | COMP | 2020-07-31 | INPR | 2020-07-31 | COMP | 2020-09-02 | COMP | Rule 15/16 | 129 | 88 | 44 |  |  |  | 917
2042 | 2017-01-12 | 2017-09-11 | 2017-12-07 | 2017-12-07 | COMP | 2018-04-25 | COMP | 2018-04-26 | COMP | 2020-02-21 | COMP | 2021-03-18 | COMP | Rule 16 | 168 | 61 | 96 | 2 | 457 | 271 | 1050
918 | 2017-01-13 | 2017-01-31 | 2018-08-30 | 2018-08-30 | COMP | 2018-09-25 | COMP | 2018-09-27 | COMP | 2019-12-28 | INPR | 2019-09-03 | COMP | Rule 15/16 | 12 | 400 | 18 | 3 |  |  | 663
1214 | 2017-01-13 | 2017-04-23 | 2018-02-02 | 2018-02-02 | COMP | 2018-10-01 | COMP | 2019-03-04 | COMP | 2023-04-29 | INPR | 2019-06-17 | COMP | Rule 15/16 | 69 | 196 | 168 | 104 |  |  | 609
2022 | 2017-01-13 | 2017-09-07 | 2018-04-16 | 2018-04-16 | COMP | 2018-07-25 | COMP | 2018-08-06 | COMP | 2019-07-21 | INPR | 2019-02-12 | COMP | Rule 16 | 165 | 151 | 71 | 9 |  |  | 522
2878 | 2017-01-13 | 2018-02-09 | 2018-05-10 | 2018-05-10 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2021-01-02 | COMP | 2019-12-17 | COMP | Rule 16 | 270 | 64 | 305 | 1 | 361 |  | 735
3140 | 2017-01-13 | 2018-03-13 | 2018-09-18 | 2018-09-18 | COMP | 2018-10-10 | COMP | 2018-12-21 | COMP | 2019-07-21 | INPR | 2019-03-29 | COMP | Rule 15/16 | 291 | 133 | 17 | 50 |  |  | 554
4694 | 2017-01-13 | 2018-03-14 | 2018-05-14 | 2018-05-14 | COMP | 2018-07-06 | COMP | 2018-08-16 | COMP | 2019-02-26 | COMP | 2019-04-03 | COMP | Rule 16 | 292 | 44 | 38 | 30 | 131 | 27 | 557
6169 | 2017-01-13 | 2018-08-02 | 2018-12-15 | 2019-10-11 | COMP | 2020-07-30 | COMP | 2020-08-07 | COMP | 2020-09-30 | COMP | 2020-12-09 | COMP | Rule 15/16 | 391 | 93 | 202 | 7 | 38 | 48 | 982
2696 | 2017-01-15 | 2018-01-19 | 2018-02-26 | 2018-02-26 | COMP | 2018-10-03 | COMP | 2018-10-30 | COMP |  | INPR | 2020-01-02 | COMP | Rule 15/16 | 254 | 26 | 155 | 20 |  |  | 744
1537 | 2017-01-16 | 2017-06-19 | 2018-04-18 | 2017-12-13 | COMP | 2018-10-30 | COMP | 2018-11-06 | COMP | 2018-12-05 | COMP | 2019-01-24 | COMP | Rule 15/16 | 108 | 209 | 223 | 6 | 19 | 34 | 508
1585 | 2017-01-16 | 2017-06-27 | 2018-02-07 | 2018-02-07 | COMP | 2018-10-26 | COMP | 2019-03-25 | COMP | 2019-03-13 | COMP | 2019-05-01 | COMP | Rule 15/16 | 114 | 154 | 184 | 100 | 0 | 28 | 576
2078 | 2017-01-16 | 2017-09-20 | 2018-08-21 | 2018-08-21 | COMP | 2018-11-14 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2020-08-25 | COMP | Rule 16 | 173 | 231 | 60 | 7 | 1 | 442 | 909
2168 | 2017-01-16 | 2017-10-03 | 2018-03-08 | 2018-06-12 | COMP | 2018-08-07 | COMP | 2019-01-08 | COMP | 2018-12-14 | COMP | 2019-03-21 | COMP | Rule 16 | 182 | 106 | 40 | 105 | 0 | 51 | 547
20889 | 2017-01-16 | 2020-07-10 | 2020-09-01 | 2020-09-01 | COMP | 2020-09-28 | COMP | 2021-01-14 | COMP | 2020-12-14 | COMP | 2021-02-11 | COMP | Rule 16 | 877 | 38 | 19 | 74 | 0 | 20 | 1024
978 | 2017-01-17 | 2017-02-17 | 2017-06-15 | 2017-08-02 | COMP | 2017-08-21 | COMP | 2017-08-21 | COMP | 2019-01-17 | COMP | 2019-04-09 | COMP | Rule 16 | 24 | 83 | 14 | 1 | 353 | 57 | 560
1181 | 2017-01-17 | 2017-04-14 | 2018-03-19 | 2019-12-14 | COMP | 2020-03-16 | COMP | 2020-04-27 | COMP | 2020-05-04 | COMP | 2020-06-24 | COMP | Rule 15/16 | 63 | 232 | 62 | 31 | 6 | 37 | 865
1208 | 2017-01-17 | 2017-04-21 | 2017-11-28 | 2017-11-28 | COMP | 2017-12-11 | COMP | 2017-12-11 | COMP | 2019-02-11 | COMP | 2019-01-30 | COMP | Rule 15/16 | 68 | 152 | 10 | 1 | 293 |  | 512
1685 | 2017-01-17 | 2017-07-17 | 2018-02-06 | 2018-04-12 | COMP | 2018-12-11 | COMP | 2019-06-04 | COMP | 2019-05-01 | COMP | 2019-08-08 | COMP | Rule 16 | 127 | 140 | 168 | 121 | 0 | 47 | 645
1894 | 2017-01-17 | 2017-08-17 | 2017-09-10 | 2017-09-10 | COMP | 2017-09-27 | COMP | 2017-09-28 | COMP | 2022-07-16 | INPR | 2021-03-19 | COMP | Rule 15 | 150 | 16 | 13 | 2 |  |  | 1049
1905 | 2017-01-17 | 2017-08-18 | 2017-11-22 | 2017-11-22 | COMP | 2018-06-25 | COMP | 2018-06-25 | COMP | 2018-11-21 | COMP | 2019-03-25 | COMP | Rule 16 | 151 | 67 | 147 | 1 | 105 | 83 | 549
2119 | 2017-01-17 | 2017-09-27 | 2017-12-04 | 2017-12-04 | COMP | 2018-03-08 | COMP | 2019-06-26 | COMP | 2019-11-23 | INPR | 2019-08-02 | COMP | Rule 15/16 | 178 | 46 | 65 | 329 |  |  | 641
5436 | 2017-01-17 | 2018-05-30 | 2018-05-31 | 2018-05-31 | COMP | 2018-10-10 | COMP | 2018-10-10 | COMP | 2019-08-26 | COMP | 2019-10-24 | COMP | Rule 16 | 345 | 2 | 93 | 1 | 220 | 43 | 699
9472 | 2017-01-17 | 2019-02-05 | 2019-05-16 | 2019-05-16 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-01-30 | COMP | 2020-02-24 | COMP | Rule 16 | 516 | 72 | 174 | 1 | 4 | 17 | 779
939 | 2017-01-18 | 2017-02-07 | 2017-06-15 | 2019-05-16 | COMP | 2019-06-10 | COMP | 2019-07-23 | COMP | 2019-07-09 | COMP | 2019-08-09 | COMP | Rule 16 | 15 | 91 | 17 | 31 | 0 | 14 | 645
979 | 2017-01-18 | 2017-02-17 | 2017-07-24 | 2019-05-16 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-07-23 | COMP | 2019-08-09 | COMP | Rule 16 | 23 | 109 | 24 | 1 | 24 | 14 | 645
1088 | 2017-01-18 | 2017-03-23 | 2017-05-23 | 2017-05-23 | COMP | 2017-11-20 | COMP | 2018-04-16 | COMP | 2019-02-09 | COMP | 2019-04-11 | COMP | Rule 16 | 46 | 44 | 126 | 100 | 206 | 43 | 561
1938 | 2017-01-18 | 2017-08-23 | 2017-11-10 | 2017-11-10 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2019-07-10 | COMP | 2019-09-12 | COMP | Rule 16 | 153 | 56 | 135 | 1 | 281 | 46 | 668
5177 | 2017-01-18 | 2018-05-07 | 2018-08-30 | 2018-08-30 | COMP | 2018-10-24 | COMP | 2018-12-11 | COMP | 2018-12-21 | COMP | 2019-03-07 | COMP | Rule 16 | 328 | 82 | 39 | 32 | 9 | 51 | 536
13969 | 2017-01-18 | 2019-08-19 | 2020-02-11 | 2020-09-14 | COMP | 2020-09-22 | COMP | 2020-10-20 | COMP | 2021-03-25 | COMP | 2020-11-20 | COMP | Rule 16 | 651 | 120 | 7 | 21 | 106 |  | 969
1191 | 2017-01-19 | 2017-04-18 | 2017-06-07 | 2017-06-07 | COMP | 2018-05-10 | COMP | 2018-05-16 | COMP | 2019-04-18 | COMP | 2019-05-20 | COMP | Rule 16 | 63 | 36 | 233 | 5 | 232 | 23 | 587
1442 | 2017-01-19 | 2017-06-05 | 2017-10-17 | 2017-10-17 | COMP | 2018-08-09 | NOTN | 2018-08-17 | COMP | 2023-05-27 | INPR | 2022-05-17 | COMP | Rule 16 | 96 | 95 |  | 210 |  |  | 1341
1554 | 2017-01-19 | 2017-06-22 | 2018-05-10 | 2018-05-10 | COMP | 2018-05-15 | COMP | 2018-07-27 | COMP | 2019-09-20 | COMP | 2020-06-25 | COMP | Rule 16 | 109 | 222 | 4 | 52 | 290 | 192 | 864
2053 | 2017-01-19 | 2017-09-14 | 2017-12-26 | 2018-07-23 | COMP | 2018-08-20 | COMP | 2019-04-16 | COMP | 2019-11-12 | COMP | 2019-11-21 | COMP | Rule 16 | 167 | 70 | 21 | 164 | 147 | 8 | 716
1525 | 2017-01-20 | 2017-06-15 | 2018-10-26 | 2018-10-26 | COMP | 2018-11-24 | NOTN | 2018-11-24 | COMP | 2018-11-24 | COMP | 2019-01-29 | COMP | Other | 103 | 345 |  | 18 | 0 | 44 | 508
2300 | 2017-01-20 | 2017-10-30 | 2018-03-05 | 2018-03-05 | COMP | 2018-12-27 | COMP | 2020-02-29 | REQD | 2018-10-11 | COMP | 2019-07-29 | COMP | Rule 15/16 | 198 | 84 | 207 |  |  |  | 634
1630 | 2017-01-21 | 2017-07-06 | 2017-08-24 | 2017-08-24 | COMP | 2017-12-29 | COMP | 2017-12-29 | COMP | 2019-01-10 | COMP | 2021-01-18 | COMP | Rule 16 | 116 | 36 | 87 | 1 | 259 | 508 | 1002
2164 | 2017-01-22 | 2017-10-04 | 2018-01-02 | 2018-01-02 | COMP | 2018-02-26 | COMP | 2018-12-08 | COMP |  |  | 2019-04-24 | COMP | Rule 16 | 179 | 60 | 38 | 199 |  |  | 567
2165 | 2017-01-22 | 2017-10-04 | 2018-01-03 | 2018-01-03 | COMP | 2018-02-23 | COMP | 2020-08-12 | COMP | 2023-12-02 | INPR | 2020-05-07 | COMP | Rule 16 | 179 | 61 | 36 | 623 |  |  | 828
3623 | 2017-01-22 | 2018-05-25 | 2018-08-08 | 2018-08-08 | COMP | 2019-01-09 | COMP | 2019-04-23 | COMP | 2019-04-30 | COMP | 2019-05-08 | COMP | Rule 16 | 339 | 52 | 105 | 73 | 6 | 7 | 577
1012 | 2017-01-23 | 2017-02-27 | 2017-12-01 | 2017-12-01 | COMP | 2018-03-29 | COMP | 2018-11-05 | COMP | 2019-01-28 | COMP | 2019-03-14 | COMP | Rule 15/16 | 25 | 194 | 81 | 155 | 55 | 33 | 538
1013 | 2017-01-23 | 2017-02-27 | 2018-01-08 | 2018-01-08 | COMP | 2018-04-13 | COMP | 2018-09-13 | COMP | 2019-02-19 | COMP | 2019-03-14 | COMP | Rule 15/16 | 25 | 218 | 68 | 107 | 107 | 18 | 538
1048 | 2017-01-23 | 2017-03-13 | 2017-09-22 | 2017-09-22 | COMP | 2017-12-11 | COMP | 2017-12-11 | COMP |  |  | 2019-02-05 | COMP | Rule 15/16 | 35 | 137 | 54 | 1 |  |  | 512
1147 | 2017-01-23 | 2017-04-06 | 2018-03-14 | 2018-06-13 | COMP | 2018-10-31 | COMP | 2018-11-06 | COMP | 2019-09-21 | INPR | 2019-06-03 | COMP | Rule 15/16 | 53 | 235 | 99 | 5 |  |  | 594
1311 | 2017-01-23 | 2017-05-08 | 2017-10-31 | 2017-10-31 | COMP | 2018-10-24 | COMP | 2019-04-15 | COMP | 2020-05-03 | COMP | 2020-05-20 | COMP | Rule 15/16 | 75 | 124 | 247 | 117 | 265 | 13 | 837
1897 | 2017-01-23 | 2017-08-17 | 2018-02-20 | 2018-02-20 | COMP | 2018-03-26 | COMP | 2018-07-16 | COMP | 2019-03-14 | COMP | 2019-04-18 | COMP | Rule 15/16 | 146 | 126 | 25 | 79 | 166 | 26 | 563
2469 | 2017-01-23 | 2017-12-06 | 2018-04-04 | 2018-04-04 | COMP | 2018-04-11 | COMP | 2018-12-19 | COMP | 2018-12-01 | COMP | 2019-03-26 | COMP | Rule 15/16 | 221 | 82 | 6 | 175 | 0 | 66 | 546
2470 | 2017-01-23 | 2017-12-06 | 2018-04-04 | 2018-04-04 | COMP | 2018-04-12 | COMP | 2018-12-19 | COMP | 2018-12-01 | COMP | 2019-03-25 | COMP | Rule 16 | 221 | 82 | 7 | 174 | 0 | 65 | 545
4030 | 2017-01-23 | 2018-12-15 | 2019-03-16 | 2019-03-16 | COMP | 2019-04-25 | COMP | 2019-06-17 | COMP | 2019-06-14 | COMP | 2019-08-29 | COMP | Rule 16 | 478 | 61 | 29 | 37 | 0 | 53 | 656
4310 | 2017-01-23 | 2020-07-20 | 2020-08-10 | 2020-08-10 | COMP | 2021-04-08 | COMP | 2021-04-08 | COMP | 2021-04-19 | COMP | 2021-06-04 | COMP | Rule 16 | 879 | 16 | 166 | 1 | 8 | 34 | 1099
1083 | 2017-01-24 | 2017-03-23 | 2019-05-06 | 2019-05-06 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2019-11-01 | COMP | 2019-12-06 | COMP | Rule 16 | 42 | 533 | 74 | 1 | 54 | 23 | 722
1511 | 2017-01-24 | 2017-06-14 | 2018-06-29 | 2019-10-18 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-03-31 | COMP | 2020-05-30 | COMP | Rule 15/16 | 100 | 263 | 107 | 1 | 5 | 43 | 842
1961 | 2017-01-24 | 2017-08-28 | 2017-12-22 | 2017-12-22 | COMP | 2018-04-03 | COMP | 2018-04-03 | COMP | 2018-04-30 | COMP | 2022-06-10 | COMP | Rule 15/16 | 152 | 81 | 69 | 1 | 20 | 1037 | 1355
2241 | 2017-01-24 | 2017-10-20 | 2018-06-13 | 2018-06-13 | COMP | 2018-07-13 | COMP | 2018-12-07 | COMP | 2019-06-29 | REQD | 2019-03-21 | COMP | Rule 16 | 190 | 161 | 22 | 102 |  |  | 542
4668 | 2017-01-24 | 2018-03-05 | 2018-06-08 | 2018-06-08 | COMP | 2019-03-01 | COMP | 2019-04-10 | COMP | 2019-06-19 | COMP | 2019-08-02 | COMP | Rule 16 | 279 | 69 | 182 | 29 | 50 | 32 | 636
5226 | 2017-01-24 | 2018-05-14 | 2018-07-05 | 2018-07-05 | COMP | 2018-09-18 | COMP | 2018-09-18 | COMP | 2018-09-25 | COMP | 2019-01-07 | COMP | Rule 16 | 329 | 37 | 53 | 1 | 6 | 70 | 491
950 | 2017-01-25 | 2017-02-11 | 2017-02-14 | 2017-02-14 | COMP | 2017-03-20 | COMP | 2017-03-21 | COMP | 2018-12-06 | COMP | 2020-09-30 | COMP | Rule 16 | 13 | 2 | 24 | 2 | 432 | 459 | 928
964 | 2017-01-25 | 2017-02-17 | 2017-03-13 | 2017-03-13 | COMP | 2017-03-28 | COMP | 2017-03-30 | COMP | 2019-03-27 | COMP | 2019-04-23 | COMP | Rule 16 | 18 | 16 | 12 | 3 | 500 | 20 | 564
1010 | 2017-01-26 | 2017-02-27 | 2017-04-26 | 2017-04-26 | COMP | 2017-06-28 | COMP | 2017-06-29 | COMP | 2019-08-21 | COMP | 2019-11-06 | COMP | Rule 16 | 22 | 43 | 45 | 2 | 539 | 55 | 701
2371 | 2017-01-26 | 2017-11-18 | 2018-01-23 | 2018-01-23 | COMP | 2018-02-28 | COMP | 2018-02-28 | COMP | 2023-05-27 | INPR | 2022-04-26 | COMP | Rule 16 | 207 | 42 | 26 | 1 |  |  | 1321
5862 | 2017-01-26 | 2018-07-10 | 2018-10-04 | 2019-06-25 | COMP |  | INPR | 2019-08-13 | COMP |  | INPR | 2020-02-14 | COMP | Rule 15/16 | 366 | 62 |  | 35 |  |  | 767
974 | 2017-01-27 | 2017-02-17 | 2017-10-10 | 2017-10-10 | COMP | 2018-04-30 | COMP | 2019-12-03 | COMP | 2020-04-10 | COMP | 2020-04-24 | COMP | Rule 15/16 | 16 | 164 | 138 | 401 | 90 | 11 | 815
1052 | 2017-01-27 | 2017-03-14 | 2017-05-16 | 2017-05-16 | COMP | 2019-02-19 | COMP | 2019-02-21 | COMP | 2019-03-12 | COMP | 2019-06-11 | COMP | Rule 16 | 32 | 46 | 441 | 3 | 14 | 65 | 596
1161 | 2017-01-27 | 2017-04-10 | 2018-04-20 | 2018-04-20 | COMP | 2018-09-06 | COMP | 2018-09-18 | COMP | 2018-10-29 | COMP | 2019-01-31 | COMP | Rule 15/16 | 51 | 260 | 97 | 9 | 30 | 63 | 505
1203 | 2017-01-27 | 2017-04-19 | 2018-07-02 | 2018-07-02 | COMP | 2018-07-19 | COMP | 2018-12-07 | COMP | 2021-02-27 | INPR | 2019-07-25 | COMP | Rule 15/16 | 58 | 303 | 13 | 98 |  |  | 627
1258 | 2017-01-27 | 2017-05-01 | 2018-03-09 | 2018-03-09 | COMP | 2018-06-15 | COMP | 2018-10-24 | COMP | 2018-10-18 | COMP | 2019-01-31 | COMP | Rule 15/16 | 66 | 215 | 70 | 92 | 0 | 66 | 505
1005 | 2017-01-30 | 2017-02-25 | 2017-05-01 | 2017-05-01 | COMP | 2017-06-22 | COMP | 2017-06-22 | COMP | 2019-08-27 | COMP | 2019-09-25 | COMP | Rule 16 | 19 | 46 | 38 | 1 | 548 | 21 | 669
1402 | 2017-01-30 | 2017-05-26 | 2017-06-19 | 2017-06-19 | COMP | 2019-02-26 | COMP | 2017-09-11 | COMP | 2019-05-21 | COMP | 2019-10-02 | COMP | Rule 15/16 | 84 | 16 | 423 |  | 425 | 94 | 674
1810 | 2017-01-30 | 2017-08-01 | 2018-03-08 | 2018-03-08 | COMP | 2018-04-17 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-05-04 | COMP | Rule 15/16 | 129 | 150 | 29 | 208 | 1 | 57 | 569
4417 | 2017-01-30 | 2017-11-27 | 2018-03-22 | 2018-03-22 | COMP | 2018-06-12 | COMP | 2019-06-27 | COMP | 2019-06-23 | COMP | 2019-09-26 | COMP | Rule 16 | 209 | 80 | 58 | 263 | 0 | 64 | 670
21794 | 2017-01-30 | 2020-08-27 | 2020-10-12 | 2020-10-12 | COMP | 2020-12-28 | COMP | 2021-03-22 | COMP | 2021-07-09 | COMP | 2021-09-02 | COMP | Rule 16 | 902 | 32 | 52 | 58 | 78 | 40 | 1157
954 | 2017-01-31 | 2017-02-14 | 2017-03-20 | 2017-03-20 | COMP | 2017-04-28 | COMP | 2017-11-29 | COMP | 2020-01-08 | COMP | 2019-12-16 | COMP | Rule 16 | 11 | 24 | 30 | 148 | 529 |  | 723
1359 | 2017-01-31 | 2017-05-17 | 2017-06-15 | 2017-06-15 | COMP | 2017-07-11 | COMP | 2017-07-11 | COMP | 2017-07-11 | COMP | 2021-12-02 | COMP | Rule 16 | 76 | 21 | 18 | 1 | 1 | 1105 | 1217
2857 | 2017-01-31 | 2018-02-08 | 2019-04-05 | 2019-04-05 | COMP | 2019-06-06 | COMP | 2019-08-30 | COMP | 2020-01-31 | COMP | 2020-02-20 | COMP | Rule 16 | 258 | 291 | 44 | 61 | 104 | 14 | 767
4424 | 2017-01-31 | 2017-12-01 | 2018-11-01 | 2019-06-07 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | Rule 15/16 | 212 | 233 | 21 | 1 | 15 | 1 | 626
13130 | 2017-01-31 | 2019-07-11 | 2020-01-31 | 2020-10-09 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2021-03-17 | COMP | 2021-04-27 | COMP | Rule 16 | 615 | 140 | 14 | 1 | 94 | 30 | 1066
1107 | 2017-02-01 | 2017-03-25 | 2017-11-28 | 2017-11-28 | COMP | 2018-01-24 | COMP | 2018-03-13 | COMP |  |  | 2019-03-18 | COMP | Rule 16 | 37 | 171 | 39 | 34 |  |  | 533
1330 | 2017-02-01 | 2017-05-11 | 2017-05-15 | 2017-05-15 | COMP | 2017-05-23 | COMP | 2017-07-06 | COMP | 2018-12-11 | COMP | 2019-01-04 | COMP | Rule 16 | 71 | 3 | 7 | 31 | 360 | 17 | 484
3512 | 2017-02-01 | 2018-05-09 | 2018-05-13 | 2018-05-13 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-11-23 | INPR | 2019-08-13 | COMP | Rule 16 | 320 | 3 | 295 | 1 |  |  | 637
1077 | 2017-02-02 | 2017-03-21 | 2017-11-11 | 2018-05-10 | COMP | 2018-10-01 | COMP | 2019-03-21 | COMP | 2021-02-07 | INPR | 2019-12-02 | COMP | Rule 15/16 | 33 | 165 | 100 | 117 |  |  | 711
1942 | 2017-02-02 | 2017-08-23 | 2017-11-03 | 2017-11-03 | COMP | 2017-12-13 | COMP | 2017-12-13 | COMP | 2019-06-06 | COMP | 2019-07-06 | COMP | Rule 15/16 | 142 | 52 | 26 | 1 | 372 | 21 | 609
2321 | 2017-02-02 | 2017-11-03 | 2018-03-10 | 2018-03-10 | COMP | 2018-04-24 | COMP | 2018-06-05 | COMP | 2020-12-28 | COMP | 2021-01-25 | COMP | Rule 16 | 193 | 84 | 32 | 30 | 645 | 19 | 999
2629 | 2017-02-02 | 2018-01-09 | 2018-03-23 | 2018-03-23 | COMP | 2018-04-20 | COMP | 2018-04-20 | COMP | 2018-05-10 | COMP | 2020-11-12 | COMP | Other | 235 | 52 | 21 | 1 | 15 | 633 | 952
2775 | 2017-02-02 | 2018-01-30 | 2019-01-11 | 2019-01-11 | COMP | 2018-01-30 | NOTN | 2021-03-03 | INPR | 2021-03-03 | REQD | 2021-03-03 | COMP | Other | 249 | 240 |  |  |  |  | 1025
4193 | 2017-02-02 | 2019-06-25 | 2019-06-26 | 2019-06-26 | COMP | 2019-08-15 | COMP | 2019-08-19 | COMP | 2020-10-20 | COMP | 2021-02-04 | COMP | Other | 602 | 2 | 36 | 3 | 297 | 72 | 1007
1189 | 2017-02-03 | 2017-04-17 | 2017-08-02 | 2018-07-09 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-01-14 | COMP | 2019-02-25 | COMP | Rule 16 | 51 | 76 | 127 | 1 | 4 | 29 | 516
5560 | 2017-02-03 | 2018-06-14 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-18 | COMP | 2019-06-12 | COMP | 2019-05-16 | COMP | 2019-07-22 | COMP | Rule 15/16 | 343 | 178 | 12 | 62 | 0 | 28 | 619
3155 | 2017-02-04 | 2018-03-15 | 2018-07-28 | 2018-07-28 | COMP | 2018-11-01 | COMP | 2018-11-05 | COMP | 2018-11-21 | COMP | 2019-05-07 | COMP | Rule 16 | 278 | 95 | 68 | 3 | 12 | 114 | 566
982 | 2017-02-06 | 2017-02-21 | 2017-03-29 | 2017-03-29 | COMP | 2017-06-29 | COMP | 2018-03-14 | COMP | 2020-05-30 | COMP | 2020-06-29 | COMP | Rule 16 | 11 | 27 | 66 | 176 | 557 | 21 | 854
1103 | 2017-02-06 | 2017-03-24 | 2017-07-29 | 2017-07-29 | COMP | 2017-08-14 | COMP | 2017-09-06 | COMP |  |  | 2020-12-26 | COMP | Rule 16 | 34 | 89 | 11 | 17 |  |  | 978
1104 | 2017-02-06 | 2017-03-24 | 2017-08-13 | 2017-08-13 | COMP | 2017-08-22 | COMP | 2017-08-28 | COMP | 2019-04-20 | INPR | 2019-01-24 | COMP | Rule 16 | 34 | 99 | 7 | 5 |  |  | 494
1110 | 2017-02-06 | 2017-03-25 | 2017-07-15 | 2017-07-15 | COMP | 2017-07-28 | COMP | 2017-08-14 | COMP |  |  | 2019-04-15 | COMP | Rule 16 | 34 | 78 | 10 | 12 |  |  | 550
1419 | 2017-02-06 | 2017-06-01 | 2017-11-13 | 2018-11-19 | COMP | 2019-01-30 | COMP | 2018-07-18 | COMP | 2019-02-26 | COMP | 2019-03-25 | COMP | Rule 15/16 | 82 | 115 | 48 |  | 152 | 20 | 535
4159 | 2017-02-06 | 2019-04-24 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-21 | COMP | 2019-05-30 | COMP | 2020-01-18 | INPR | 2019-09-24 | COMP | Rule 16 | 557 | 7 | 14 | 7 |  |  | 663
4160 | 2017-02-06 | 2019-04-24 | 2019-05-02 | 2020-05-29 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2020-07-28 | COMP | 2020-09-16 | COMP | Rule 16 | 557 | 7 | 45 | 1 | 0 | 34 | 910
1051 | 2017-02-07 | 2017-03-14 | 2017-09-12 | 2017-09-12 | COMP | 2017-12-01 | COMP | 2018-11-26 | COMP | 2018-12-04 | COMP | 2019-01-29 | COMP | Rule 16 | 25 | 128 | 56 | 247 | 7 | 38 | 496
1063 | 2017-02-07 | 2017-03-16 | 2017-05-04 | 2017-05-04 | COMP | 2017-05-08 | COMP | 2018-01-08 | COMP | 2019-07-21 | INPR | 2019-04-16 | COMP | Rule 16 | 27 | 36 | 3 | 168 |  |  | 550
1570 | 2017-02-07 | 2017-06-26 | 2017-09-13 | 2018-03-08 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-05-21 | COMP | 2019-06-26 | COMP | Rule 15/16 | 98 | 56 | 222 | 1 | 83 | 26 | 600
1579 | 2017-02-07 | 2017-06-27 | 2018-02-08 | 2018-02-08 | COMP | 2019-10-21 | COMP | 2020-01-09 | COMP | 2020-07-18 | COMP | 2020-10-13 | COMP | Rule 16 | 99 | 155 | 429 | 54 | 134 | 61 | 928
1841 | 2017-02-07 | 2017-08-08 | 2018-06-18 | 2018-06-18 | COMP | 2018-08-29 | COMP | 2019-05-15 | COMP | 2020-01-28 | COMP | 2020-05-19 | COMP | Rule 15/16 | 128 | 216 | 52 | 178 | 176 | 80 | 825
1843 | 2017-02-07 | 2017-08-08 | 2017-12-20 | 2017-12-20 | COMP | 2018-03-01 | COMP | 2018-03-01 | COMP | 2019-03-15 | COMP | 2019-04-16 | COMP | Rule 15/16 | 128 | 93 | 48 | 1 | 262 | 23 | 550
4492 | 2017-02-07 | 2018-01-08 | 2018-06-02 | 2018-11-05 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2018-10-18 | COMP | 2019-01-30 | COMP | Rule 16 | 231 | 102 | 7 | 1 | 0 | 51 | 497
1016 | 2017-02-08 | 2017-02-28 | 2017-05-25 | 2017-05-25 | COMP | 2018-10-18 | COMP | 2019-04-11 | COMP | 2019-04-09 | COMP | 2019-08-22 | COMP | Rule 16 | 14 | 63 | 353 | 119 | 0 | 94 | 639
1111 | 2017-02-08 | 2017-03-25 | 2017-08-12 | 2017-08-12 | COMP | 2017-08-22 | COMP | 2017-08-28 | COMP |  |  | 2019-02-11 | COMP | Rule 16 | 32 | 98 | 7 | 5 |  |  | 504
1374 | 2017-02-08 | 2017-05-20 | 2017-06-20 | 2018-01-02 | COMP | 2018-11-15 | COMP | 2018-12-11 | COMP | 2021-02-27 | INPR | 2019-10-15 | COMP | Rule 16 | 72 | 21 | 222 | 17 |  |  | 676
10355 | 2017-02-08 | 2019-03-12 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-29 | COMP | 2019-08-30 | COMP | 2019-09-26 | COMP | 2019-12-26 | COMP | Rule 16 | 524 | 71 | 51 | 2 | 19 | 62 | 724
1105 | 2017-02-09 | 2017-03-24 | 2017-07-17 | 2017-07-17 | COMP | 2017-12-11 | COMP | 2017-12-11 | COMP |  |  | 2019-01-24 | COMP | Rule 16 | 31 | 80 | 102 | 1 |  |  | 491
1106 | 2017-02-09 | 2017-03-25 | 2017-08-07 | 2017-08-07 | COMP | 2017-08-22 | COMP | 2017-09-18 | COMP | 2017-11-16 | COMP | 2019-02-21 | COMP | Rule 16 | 31 | 94 | 12 | 19 | 43 | 315 | 510
1108 | 2017-02-09 | 2017-03-25 | 2017-08-24 | 2018-01-24 | COMP | 2018-11-30 | COMP | 2018-11-30 | COMP |  |  | 2019-03-18 | COMP | Rule 15/16 | 31 | 107 | 216 | 1 |  |  | 527
1109 | 2017-02-09 | 2017-03-25 | 2017-08-28 | 2017-08-28 | COMP | 2017-09-01 | COMP | 2017-10-13 | COMP | 2017-11-16 | COMP | 2019-04-04 | COMP | Rule 15/16 | 31 | 109 | 5 | 30 | 24 | 345 | 540
1163 | 2017-02-09 | 2017-04-10 | 2017-12-16 | 2017-12-16 | COMP | 2018-08-09 | COMP | 2018-09-26 | COMP | 2019-05-28 | COMP | 2019-07-17 | COMP | Rule 16 | 42 | 174 | 163 | 34 | 167 | 36 | 612
1210 | 2017-02-09 | 2017-04-21 | 2017-06-08 | 2017-06-08 | COMP | 2017-09-28 | COMP | 2018-12-10 | COMP | 2019-08-19 | COMP | 2019-09-24 | COMP | Rule 16 | 51 | 34 | 79 | 300 | 175 | 26 | 660
1416 | 2017-02-09 | 2017-05-31 | 2017-07-17 | 2017-07-17 | COMP | 2017-12-14 | COMP | 2017-12-14 | COMP | 2019-06-21 | COMP | 2019-12-04 | COMP | Rule 16 | 78 | 33 | 105 | 1 | 382 | 114 | 708
1439 | 2017-02-09 | 2017-06-02 | 2017-09-26 | 2017-09-26 | COMP | 2018-07-05 | COMP | 2019-03-19 | COMP | 2019-05-01 | COMP | 2019-07-09 | COMP | Rule 15/16 | 80 | 81 | 194 | 176 | 32 | 48 | 606
1081 | 2017-02-10 | 2017-03-22 | 2017-08-18 | 2017-08-18 | COMP | 2018-05-04 | COMP | 2018-05-16 | COMP | 2018-11-27 | COMP | 2019-01-23 | COMP | Rule 16 | 28 | 106 | 178 | 9 | 134 | 39 | 489
1082 | 2017-02-10 | 2017-03-22 | 2017-07-29 | 2017-07-29 | COMP | 2018-03-26 | COMP | 2018-03-26 | COMP | 2019-06-21 | COMP | 2019-07-26 | COMP | Rule 16 | 28 | 91 | 163 | 1 | 314 | 25 | 618
1112 | 2017-02-10 | 2017-03-25 | 2017-08-21 | 2017-08-21 | COMP | 2018-02-06 | COMP | 2018-02-16 | COMP | 2018-12-20 | COMP | 2019-02-28 | COMP | Rule 15/16 | 30 | 104 | 115 | 9 | 213 | 47 | 514
1289 | 2017-02-10 | 2017-05-05 | 2017-08-09 | 2017-08-09 | COMP | 2017-11-15 | COMP | 2018-01-25 | COMP | 2018-06-22 | COMP | 2020-01-09 | COMP | Rule 16 | 60 | 67 | 69 | 47 | 105 | 388 | 731
1509 | 2017-02-10 | 2017-06-13 | 2018-03-15 | 2018-03-15 | COMP | 2018-04-11 | COMP | 2018-05-10 | COMP | 2019-09-24 | COMP | 2019-09-23 | COMP | Rule 16 | 86 | 189 | 20 | 22 | 346 |  | 658
1587 | 2017-02-10 | 2017-06-28 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-26 | COMP | 2019-09-27 | COMP | 2019-11-15 | COMP | 2019-12-05 | COMP | Rule 15/16 | 97 | 398 | 19 | 151 | 35 | 13 | 708
2636 | 2017-02-10 | 2018-01-10 | 2018-10-22 | 2018-10-22 | COMP | 2019-10-02 | COMP | 2020-03-01 | REQD | 2020-03-01 | REQD | 2019-11-15 | COMP | Rule 15/16 | 230 | 199 | 238 |  |  |  | 696
3528 | 2017-02-10 | 2018-05-11 | 2018-05-20 | 2018-05-20 | COMP | 2018-06-04 | COMP | 2018-06-04 | COMP | 2019-10-25 | COMP | 2019-11-07 | COMP | Rule 16 | 315 | 6 | 10 | 1 | 353 | 10 | 691
5312 | 2017-02-10 | 2018-05-23 | 2018-08-25 | 2018-09-29 | COMP | 2018-12-11 | COMP | 2019-08-12 | COMP | 2019-08-13 | COMP | 2019-10-01 | COMP | Rule 15/16 | 323 | 66 | 49 | 169 | 2 | 35 | 664
9934 | 2017-02-10 | 2019-02-22 | 2019-03-07 | 2019-03-07 | COMP | 2019-07-19 | COMP | 2019-06-14 | COMP |  | INPR | 2019-07-31 | COMP | Rule 15/16 | 510 | 10 | 95 |  |  |  | 621
16114 | 2017-02-10 | 2019-12-10 | 2020-04-09 | 2020-04-14 | COMP | 2020-04-16 | COMP | 2020-06-08 | COMP | 2020-06-23 | COMP | 2020-07-21 | COMP | Rule 16 | 711 | 84 | 3 | 37 | 12 | 21 | 866
1050 | 2017-02-12 | 2017-03-13 | 2017-08-04 | 2017-08-04 | COMP | 2017-08-11 | COMP | 2019-07-16 | COMP | 2019-07-23 | COMP | 2019-08-06 | COMP | Rule 16 | 20 | 103 | 6 | 483 | 6 | 11 | 624
1169 | 2017-02-14 | 2017-04-13 | 2018-07-02 | 2018-07-02 | COMP | 2018-07-26 | COMP | 2018-08-03 | COMP |  | INPR | 2019-07-24 | COMP | Rule 16 | 42 | 307 | 18 | 7 |  |  | 614
1226 | 2017-02-14 | 2017-04-25 | 2017-09-22 | 2017-09-22 | COMP | 2019-07-09 | COMP | 2020-11-23 | COMP | 2023-12-02 | INPR | 2022-05-01 | COMP | Rule 15/16 | 50 | 106 | 449 | 349 |  |  | 1311
1433 | 2017-02-14 | 2017-06-02 | 2017-09-26 | 2017-09-26 | COMP | 2018-10-05 | COMP | 2018-10-31 | COMP | 2019-03-19 | COMP | 2019-05-03 | COMP | Rule 15/16 | 77 | 81 | 259 | 19 | 93 | 34 | 558
957 | 2017-02-15 | 2017-02-15 | 2017-06-28 | 2017-06-28 | COMP | 2019-05-21 | COMP | 2019-05-29 | COMP | 2019-11-13 | COMP | 2020-03-06 | COMP | Rule 15/16 | 1 | 94 | 476 | 6 | 118 | 77 | 767
1089 | 2017-02-15 | 2017-03-23 | 2017-06-09 | 2017-06-09 | COMP | 2017-08-10 | COMP | 2018-06-08 | COMP |  |  | 2019-03-15 | COMP | Rule 16 | 26 | 56 | 44 | 208 |  |  | 522
1835 | 2017-02-15 | 2017-08-07 | 2018-02-16 | 2018-02-16 | COMP | 2018-03-07 | COMP | 2018-04-03 | COMP | 2019-06-29 | INPR | 2019-03-14 | COMP | Rule 16 | 121 | 133 | 13 | 20 |  |  | 521
1944 | 2017-02-15 | 2017-08-24 | 2017-09-28 | 2017-09-28 | COMP | 2017-11-13 | COMP | 2018-05-09 | COMP | 2020-01-27 | COMP | 2020-02-28 | COMP | Rule 16 | 134 | 25 | 32 | 122 | 430 | 24 | 762
7232 | 2017-02-15 | 2018-10-04 | 2018-10-29 | 2018-10-29 | COMP | 2019-01-17 | COMP | 2019-03-12 | COMP | 2019-02-26 | COMP | 2019-04-04 | COMP | Rule 16 | 413 | 18 | 54 | 37 | 0 | 18 | 536
11084 | 2017-02-15 | 2019-04-11 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-30 | COMP | 2020-09-15 | COMP | 2021-06-01 | COMP | 2021-07-22 | COMP | Rule 16 | 541 | 233 | 11 | 120 | 178 | 37 | 1115
1053 | 2017-02-16 | 2017-03-14 | 2018-04-23 | 2018-04-23 | COMP | 2021-12-10 | COMP | 2021-12-10 | COMP |  | INPR | 2023-09-15 | COMP | Rule 15/16 | 18 | 280 | 915 | 1 |  |  | 1654
1186 | 2017-02-16 | 2017-04-18 | 2018-03-03 | 2018-03-03 | COMP | 2018-11-08 | COMP | 2019-02-28 | COMP | 2019-02-14 | COMP | 2019-05-10 | COMP | Rule 15/16 | 43 | 219 | 176 | 74 | 0 | 52 | 561
1863 | 2017-02-16 | 2017-08-10 | 2017-09-20 | 2017-09-20 | COMP | 2017-10-12 | COMP | 2017-11-07 | COMP | 2020-03-21 | INPR | 2019-01-08 | COMP | Other | 123 | 29 | 17 | 19 |  |  | 475
5590 | 2017-02-16 | 2018-06-18 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-04 | COMP | 2019-04-17 | COMP | 2020-01-19 | INPR | 2019-09-26 | COMP | Rule 16 | 336 | 106 | 12 | 93 |  |  | 657
1113 | 2017-02-17 | 2017-03-26 | 2017-10-16 | 2019-05-01 | COMP | 2019-09-10 | COMP | 2019-12-28 | REQD | 2018-05-17 | COMP | 2019-09-11 | COMP | Rule 16 | 25 | 143 | 92 |  |  |  | 645
1364 | 2017-02-17 | 2017-05-17 | 2017-07-28 | 2017-07-28 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2018-12-03 | COMP | 2019-01-19 | COMP | Rule 16 | 63 | 51 | 342 | 1 | 0 | 29 | 482
1572 | 2017-02-17 | 2017-06-26 | 2017-12-11 | 2017-12-11 | COMP | 2019-10-11 | NOTN | 2019-05-13 | COMP | 2019-10-11 | COMP | 2020-02-19 | COMP | Rule 16 | 90 | 116 |  | 357 | 107 | 87 | 753
1933 | 2017-02-20 | 2017-08-23 | 2017-10-11 | 2017-10-11 | COMP | 2018-06-05 | COMP | 2018-06-12 | COMP |  |  | 2019-10-01 | COMP | Rule 16 | 130 | 35 | 162 | 6 |  |  | 658
1038 | 2017-02-21 | 2017-03-07 | 2018-02-13 | 2018-02-13 | COMP | 2019-09-16 | COMP | 2020-03-16 | COMP | 2020-03-25 | COMP | 2020-05-13 | COMP | Rule 15/16 | 11 | 237 | 401 | 124 | 8 | 36 | 812
1047 | 2017-02-21 | 2017-03-13 | 2017-06-06 | 2017-06-06 | COMP | 2017-06-15 | COMP | 2018-01-06 | COMP | 2017-08-01 | COMP | 2021-07-30 | COMP | Rule 16 | 15 | 61 | 8 | 140 | 0 | 897 | 1118
1247 | 2017-02-21 | 2017-04-30 | 2018-03-06 | 2018-03-06 | COMP | 2019-08-28 | COMP | 2019-03-26 | INPR | 2020-01-18 | REQD | 2019-07-24 | COMP | Rule 16 | 49 | 212 | 375 |  |  |  | 610
1249 | 2017-02-21 | 2017-04-30 | 2017-12-05 | 2017-12-05 | COMP | 2018-02-14 | COMP | 2019-03-26 | COMP | 2020-05-30 | INPR | 2019-04-15 | COMP | Rule 16 | 49 | 151 | 49 | 279 |  |  | 540
1280 | 2017-02-21 | 2017-05-04 | 2017-12-14 | 2017-12-14 | COMP | 2018-02-14 | COMP | 2019-03-26 | INPR | 2019-11-08 | COMP | 2019-05-06 | COMP | Rule 16 | 53 | 155 | 42 |  |  |  | 555
1283 | 2017-02-21 | 2017-05-04 | 2018-01-23 | 2018-01-23 | COMP | 2018-03-10 | COMP | 2018-05-10 | COMP | 2019-08-31 | INPR | 2019-04-14 | COMP | Rule 15/16 | 53 | 180 | 33 | 44 |  |  | 539
4206 | 2017-02-21 | 2019-07-16 | 2019-08-23 | 2019-08-23 | COMP | 2019-11-15 | COMP | 2020-01-10 | INPR | 2020-01-10 | COMP | 2020-01-14 | COMP | Rule 16 | 604 | 29 | 59 |  |  |  | 728
4293 | 2017-02-21 | 2020-04-19 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-16 | NOTN | 2020-08-04 | COMP | 2022-07-16 | INPR | 2020-08-27 | COMP | Rule 16 | 794 | 34 |  | 43 |  |  | 887
7557 | 2017-02-21 | 2018-10-19 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-03 | COMP | 2021-03-01 | COMP | 2021-05-10 | COMP | 2021-06-26 | COMP | Rule 15/16 | 421 | 192 | 27 | 374 | 51 | 34 | 1094
1134 | 2017-02-22 | 2017-04-03 | 2017-07-07 | 2017-07-07 | COMP | 2017-12-07 | COMP | 2017-12-07 | COMP | 2018-08-15 | COMP | 2022-02-05 | COMP | Rule 16 | 29 | 68 | 106 | 1 | 174 | 874 | 1247
1255 | 2017-02-22 | 2017-04-30 | 2018-01-04 | 2018-01-04 | COMP | 2018-02-14 | COMP | 2019-02-15 | COMP | 2020-02-29 | INPR | 2019-11-14 | COMP | Rule 16 | 48 | 171 | 29 | 253 |  |  | 688
1420 | 2017-02-22 | 2017-06-01 | 2017-08-02 | 2017-08-02 | COMP | 2018-12-21 | COMP | 2019-01-09 | COMP | 2023-11-11 | CANC | 2020-08-05 | COMP | Rule 16 | 71 | 44 | 349 | 12 |  |  | 870
2505 | 2017-02-22 | 2017-12-11 | 2018-07-16 | 2018-07-16 | COMP | 2018-09-05 | COMP | 2019-05-30 | COMP | 2020-05-27 | COMP | 2020-10-01 | COMP | Rule 15/16 | 203 | 150 | 37 | 184 | 250 | 91 | 910
2509 | 2017-02-22 | 2017-12-11 | 2018-06-26 | 2018-06-26 | COMP | 2019-01-17 | COMP | 2019-05-30 | COMP | 2023-04-22 | INPR | 2020-08-20 | COMP | Rule 15/16 | 203 | 137 | 141 | 93 |  |  | 881
10160 | 2017-02-22 | 2019-03-05 | 2019-06-06 | 2020-07-17 | COMP | 2020-08-18 | COMP | 2020-06-02 | COMP | 2020-11-23 | COMP | 2020-12-19 | COMP | Rule 16 | 510 | 67 | 23 |  | 123 | 18 | 963
1007 | 2017-02-23 | 2017-02-27 | 2017-04-13 | 2017-04-13 | COMP | 2020-11-12 | COMP | 2020-12-09 | COMP | 2021-05-07 | COMP | 2021-05-16 | COMP | Rule 16 | 3 | 34 | 903 | 18 | 104 | 6 | 1063
1654 | 2017-02-23 | 2017-07-11 | 2017-08-22 | 2018-04-17 | COMP | 2018-08-16 | COMP | 2018-08-16 | COMP | 2019-08-31 | INPR | 2019-04-26 | COMP | Rule 16 | 97 | 31 | 86 | 1 |  |  | 547
2512 | 2017-02-23 | 2017-12-12 | 2018-05-15 | 2018-05-15 | COMP | 2018-05-30 | COMP | 2018-07-19 | COMP | 2019-08-31 | INPR | 2019-04-11 | COMP | Rule 15/16 | 203 | 107 | 11 | 36 |  |  | 536
2749 | 2017-02-23 | 2018-01-26 | 2018-04-10 | 2018-04-10 | COMP | 2018-07-19 | COMP | 2018-08-16 | COMP | 2019-10-01 | COMP | 2019-12-03 | COMP | Rule 16 | 233 | 52 | 71 | 21 | 283 | 43 | 698
2952 | 2017-02-23 | 2018-02-22 | 2018-05-16 | 2018-05-16 | COMP | 2018-08-08 | COMP | 2018-08-13 | COMP | 2019-10-14 | COMP | 2019-12-05 | COMP | Rule 16 | 251 | 60 | 59 | 4 | 295 | 36 | 700
1003 | 2017-02-24 | 2017-02-24 | 2017-05-23 | 2017-05-23 | COMP | 2017-10-03 | COMP | 2017-10-03 | COMP | 2017-05-24 | COMP | 2021-01-07 | COMP | Rule 16 | 1 | 63 | 93 | 1 | 0 | 819 | 973
1085 | 2017-02-24 | 2017-03-23 | 2017-12-02 | 2017-12-02 | COMP | 2018-06-18 | COMP | 2021-05-27 | COMP | 2021-04-05 | COMP | 2021-06-24 | COMP | Rule 16 | 20 | 176 | 136 | 741 | 0 | 20 | 1090
1146 | 2017-02-24 | 2017-04-06 | 2017-07-20 | 2017-07-20 | COMP | 2018-12-04 | COMP | 2019-09-27 | COMP | 2019-10-16 | COMP | 2019-12-06 | COMP | Rule 15/16 | 30 | 74 | 345 | 207 | 14 | 35 | 700
1188 | 2017-02-24 | 2017-04-19 | 2017-08-03 | 2021-06-11 | COMP | 2021-08-12 | COMP | 2021-09-08 | COMP | 2021-07-27 | COMP | 2021-12-06 | COMP | Rule 15/16 | 39 | 75 | 44 | 19 | 0 | 61 | 1202
1266 | 2017-02-24 | 2017-05-02 | 2017-12-16 | 2019-02-22 | COMP | 2019-04-17 | COMP | 2019-07-16 | COMP | 2019-06-12 | COMP | 2019-08-14 | COMP | Rule 15/16 | 48 | 158 | 39 | 63 | 0 | 22 | 622
2049 | 2017-02-24 | 2017-09-13 | 2018-04-10 | 2019-03-18 | COMP | 2019-12-05 | COMP | 2020-01-15 | COMP | 2021-02-28 | INPR | 2020-01-29 | COMP | Rule 15/16 | 141 | 143 | 183 | 28 |  |  | 735
3129 | 2017-02-24 | 2018-03-12 | 2019-10-09 | 2019-10-29 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2022-02-26 | INPR | 2021-02-22 | COMP | Rule 16 | 262 | 400 | 16 | 1 |  |  | 1003
1114 | 2017-02-25 | 2017-03-26 | 2018-03-14 | 2018-03-14 | COMP | 2018-04-09 | COMP | 2018-05-11 | COMP | 2019-04-01 | COMP | 2019-05-02 | COMP | Rule 16 | 20 | 243 | 19 | 25 | 222 | 24 | 549
4802 | 2017-02-25 | 2018-03-31 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-27 | COMP | 2019-11-14 | COMP | 2019-11-18 | COMP | 2020-01-06 | COMP | Rule 16 | 275 | 137 | 51 | 224 | 3 | 32 | 718
1086 | 2017-02-27 | 2017-03-23 | 2017-07-26 | 2017-07-26 | COMP | 2017-09-19 | COMP | 2017-09-19 | COMP | 2019-07-21 | INPR | 2019-04-13 | COMP | Rule 16 | 19 | 88 | 39 | 1 |  |  | 535
2690 | 2017-02-27 | 2018-01-18 | 2018-09-12 | 2018-09-12 | COMP | 2019-04-08 | COMP | 2019-04-24 | COMP | 2019-11-03 | COMP | 2020-11-04 | COMP | Rule 16 | 225 | 166 | 142 | 13 | 135 | 254 | 931
1055 | 2017-02-28 | 2017-03-14 | 2018-02-06 | 2018-02-06 | COMP | 2018-12-10 | COMP | 2019-03-19 | COMP | 2019-05-16 | COMP | 2019-07-17 | COMP | Rule 15/16 | 11 | 227 | 213 | 68 | 43 | 43 | 600
1178 | 2017-02-28 | 2017-04-14 | 2017-08-10 | 2017-08-10 | COMP | 2017-08-24 | COMP | 2017-08-24 | COMP | 2019-01-03 | COMP | 2019-01-18 | COMP | Rule 16 | 34 | 83 | 11 | 1 | 340 | 12 | 476
1493 | 2017-02-28 | 2017-06-09 | 2017-09-29 | 2017-09-29 | COMP | 2017-11-01 | COMP | 2017-11-09 | COMP |  |  | 2019-04-09 | COMP | Rule 16 | 73 | 79 | 24 | 7 |  |  | 531
2307 | 2017-02-28 | 2017-10-31 | 2018-01-23 | 2018-01-23 | COMP | 2019-02-12 | COMP | 2019-10-31 | COMP | 2020-01-14 | COMP | 2020-01-30 | COMP | Rule 16 | 173 | 55 | 266 | 184 | 49 | 12 | 734
39190 | 2017-02-28 | 2022-10-05 | 2023-05-01 | 2023-05-01 | COMP | 2023-05-01 | NOTN | 2023-06-13 | COMP | 2023-09-22 | COMP | 2023-12-05 | COMP | Other | 1411 | 142 |  | 31 | 71 | 50 | 1701
1118 | 2017-03-01 | 2017-03-28 | 2017-05-09 | 2017-05-09 | COMP | 2020-04-02 | COMP | 2020-04-28 | COMP | 2020-05-23 | COMP | 2020-06-17 | COMP | Rule 15/16 | 20 | 31 | 728 | 19 | 19 | 17 | 830
1138 | 2017-03-01 | 2017-04-05 | 2017-12-16 | 2019-03-30 | COMP | 2019-04-19 | COMP | 2019-05-02 | COMP | 2019-08-13 | COMP | 2019-09-12 | COMP | Rule 15/16 | 26 | 177 | 15 | 10 | 72 | 22 | 639
2153 | 2017-03-01 | 2017-09-30 | 2018-03-09 | 2018-05-17 | COMP | 2018-11-29 | COMP | 2018-04-24 | COMP | 2018-12-26 | COMP | 2019-02-23 | COMP | Rule 15/16 | 150 | 108 | 135 |  | 170 | 40 | 498
2262 | 2017-03-01 | 2017-10-25 | 2018-07-01 | 2018-07-01 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2023-04-04 | COMP | 2023-05-11 | COMP | Rule 16 | 168 | 170 | 145 | 1 | 1051 | 28 | 1559
6491 | 2017-03-01 | 2018-08-21 | 2018-10-04 | 2018-10-04 | COMP | 2018-11-30 | COMP | 2018-11-30 | COMP | 2018-12-07 | COMP | 2019-02-08 | COMP | Rule 16 | 373 | 32 | 39 | 1 | 6 | 43 | 489
1160 | 2017-03-02 | 2017-04-10 | 2018-03-03 | 2018-04-20 | COMP | 2018-07-19 | COMP | 2018-08-01 | COMP | 2018-11-26 | COMP | 2019-04-19 | COMP | Rule 15/16 | 28 | 225 | 63 | 10 | 80 | 101 | 537
1270 | 2017-03-02 | 2017-05-03 | 2018-04-02 | 2018-04-02 | COMP | 2018-07-25 | COMP | 2018-08-09 | COMP | 2018-11-26 | COMP | 2019-02-08 | COMP | Rule 16 | 45 | 229 | 81 | 12 | 74 | 52 | 488
1660 | 2017-03-02 | 2017-07-12 | 2017-08-21 | 2017-08-21 | COMP | 2017-10-26 | COMP | 2018-01-12 | COMP | 2021-06-19 | INPR | 2021-03-22 | COMP | Rule 16 | 93 | 29 | 48 | 52 |  |  | 1019
1700 | 2017-03-02 | 2017-07-17 | 2017-07-20 | 2017-07-20 | COMP | 2017-07-24 | COMP | 2017-07-24 | COMP | 2020-07-16 | COMP | 2020-08-31 | COMP | Rule 16 | 96 | 4 | 3 | 1 | 750 | 33 | 882
1763 | 2017-03-02 | 2017-07-21 | 2017-08-24 | 2017-08-24 | COMP | 2018-02-01 | COMP | 2018-02-01 | COMP | 2018-07-18 | COMP | 2019-05-14 | COMP | Rule 16 | 100 | 25 | 109 | 1 | 117 | 207 | 554
2252 | 2017-03-02 | 2017-10-24 | 2018-04-20 | 2018-04-20 | COMP | 2018-10-17 | COMP | 2018-10-17 | COMP | 2018-11-26 | COMP | 2019-01-28 | COMP | Rule 16 | 166 | 122 | 126 | 1 | 26 | 43 | 479
7287 | 2017-03-02 | 2018-10-05 | 2019-02-04 | 2019-02-04 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-09-25 | COMP | 2019-10-22 | COMP | Rule 16 | 404 | 81 | 58 | 1 | 107 | 20 | 666
18848 | 2017-03-02 | 2020-04-09 | 2020-06-29 | 2020-06-29 | COMP | 2021-02-23 | COMP | 2021-03-29 | COMP | 2021-05-12 | COMP | 2021-07-28 | COMP | Rule 16 | 781 | 57 | 164 | 25 | 33 | 54 | 1109
1166 | 2017-03-03 | 2017-04-11 | 2017-07-12 | 2017-07-12 | COMP | 2017-11-27 | COMP | 2017-11-27 | COMP | 2021-02-27 | INPR | 2020-01-29 | COMP | Other | 28 | 65 | 95 | 1 |  |  | 730
1229 | 2017-03-03 | 2017-04-25 | 2017-05-24 | 2017-05-24 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2019-10-23 | COMP | 2019-10-30 | COMP | Other | 38 | 22 | 334 | 1 | 275 | 6 | 671
1230 | 2017-03-03 | 2017-04-25 | 2017-05-24 | 2017-05-24 | COMP | 2017-07-21 | COMP | 2017-07-21 | INPR |  | INPR | 2019-10-17 | COMP | Other | 38 | 22 | 41 |  |  |  | 662
1231 | 2017-03-03 | 2017-04-25 | 2017-05-26 | 2017-05-26 | COMP | 2017-07-21 | COMP | 2017-07-21 | COMP | 2019-10-15 | COMP | 2019-11-14 | COMP | Other | 38 | 24 | 39 | 1 | 562 | 22 | 681
1234 | 2017-03-03 | 2017-04-26 | 2017-05-24 | 2017-05-24 | COMP | 2018-09-20 | COMP | 2018-09-20 | INPR | 2019-10-29 | COMP | 2019-12-09 | COMP | Other | 39 | 21 | 334 |  |  |  | 696
3855 | 2017-03-03 | 2018-08-21 | 2019-01-22 | 2019-01-22 | COMP | 2019-05-24 | COMP | 2019-10-21 | COMP | 2021-11-12 | COMP | 2022-02-17 | COMP | Rule 15/16 | 371 | 104 | 88 | 104 | 520 | 67 | 1249
1141 | 2017-03-04 | 2017-04-05 | 2017-06-13 | 2017-06-13 | COMP | 2018-04-19 | COMP | 2017-07-14 | COMP | 2017-09-16 | COMP | 2020-07-22 | COMP | Rule 15/16 | 23 | 49 | 214 |  | 45 | 715 | 852
2031 | 2017-03-05 | 2017-09-09 | 2017-11-10 | 2017-11-10 | COMP | 2019-02-01 | COMP | 2019-02-27 | COMP | 2019-02-01 | COMP | 2019-04-03 | COMP | Rule 16 | 132 | 44 | 305 | 18 | 0 | 26 | 523
1209 | 2017-03-06 | 2017-04-21 | 2017-06-22 | 2017-06-22 | COMP | 2017-08-28 | COMP | 2017-08-28 | COMP | 2019-03-27 | COMP | 2019-05-26 | COMP | Rule 16 | 35 | 44 | 47 | 1 | 395 | 43 | 560
1284 | 2017-03-06 | 2017-05-04 | 2017-10-25 | 2017-10-25 | COMP | 2018-02-14 | COMP | 2019-03-26 | COMP | 2019-07-21 | INPR | 2019-03-28 | COMP | Rule 16 | 44 | 122 | 75 | 279 |  |  | 519
1290 | 2017-03-06 | 2017-05-05 | 2018-05-24 | 2018-05-24 | COMP | 2018-09-04 | COMP | 2019-04-01 | COMP | 2019-08-31 | INPR | 2019-05-01 | COMP | Rule 16 | 45 | 265 | 71 | 143 |  |  | 543
1391 | 2017-03-06 | 2017-05-25 | 2017-10-04 | 2018-02-28 | COMP | 2018-05-03 | COMP | 2018-05-03 | COMP | 2019-04-02 | COMP | 2022-01-27 | COMP | Rule 15/16 | 59 | 92 | 47 | 1 | 229 | 712 | 1233
2312 | 2017-03-06 | 2017-11-01 | 2018-08-22 | 2018-08-22 | COMP | 2020-02-20 | COMP | 2019-02-05 | COMP | 2018-10-24 | COMP | 2019-07-02 | COMP | Rule 16 | 170 | 202 | 374 |  | 0 | 104 | 586
2418 | 2017-03-06 | 2017-11-28 | 2018-09-10 | 2018-09-10 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2019-02-14 | COMP | 2019-04-01 | COMP | Rule 15/16 | 186 | 198 | 40 | 1 | 69 | 32 | 521
4362 | 2017-03-06 | 2017-10-11 | 2018-04-09 | 2018-04-09 | COMP | 2018-06-25 | COMP | 2019-01-10 | COMP | 2018-12-27 | COMP | 2019-02-08 | COMP | Rule 16 | 155 | 122 | 55 | 137 | 0 | 21 | 486
4363 | 2017-03-06 | 2017-10-11 | 2018-01-16 | 2018-01-16 | COMP | 2018-04-13 | COMP | 2018-10-19 | COMP | 2018-12-27 | COMP | 2019-02-12 | COMP | Rule 16 | 155 | 64 | 63 | 133 | 46 | 32 | 488
4364 | 2017-03-06 | 2017-10-11 | 2018-02-08 | 2020-02-24 | COMP | 2020-04-08 | COMP | 2020-04-09 | COMP | 2020-04-09 | COMP | 2020-05-13 | COMP | Rule 16 | 155 | 81 | 33 | 2 | 1 | 25 | 803
1167 | 2017-03-07 | 2017-04-11 | 2017-04-12 | 2017-04-12 | COMP | 2021-12-01 | NOTN | 2017-08-22 | COMP | 2021-09-27 | COMP | 2021-12-01 | COMP | Rule 15/16 | 26 | 2 |  | 93 | 1030 | 45 | 1192
1250 | 2017-03-07 | 2017-04-30 | 2017-11-30 | 2017-11-30 | COMP | 2018-01-17 | COMP | 2018-12-17 | COMP | 2018-12-18 | COMP | 2019-03-26 | COMP | Rule 16 | 39 | 148 | 32 | 232 | 2 | 67 | 516
1254 | 2017-03-07 | 2017-04-30 | 2018-02-13 | 2018-02-13 | COMP | 2018-03-10 | COMP | 2019-01-09 | COMP | 2019-01-23 | COMP | 2019-02-07 | COMP | Rule 16 | 39 | 198 | 18 | 210 | 10 | 12 | 484
1296 | 2017-03-07 | 2017-05-05 | 2018-08-27 | 2018-08-27 | COMP | 2018-10-04 | COMP | 2018-11-13 | COMP | 2019-09-13 | COMP | 2020-08-12 | COMP | Rule 16 | 44 | 330 | 28 | 28 | 210 | 231 | 866
1385 | 2017-03-07 | 2017-05-24 | 2017-07-15 | 2017-07-15 | COMP | 2017-12-07 | COMP | 2018-07-05 | COMP | 2019-02-01 | COMP | 2019-03-08 | COMP | Rule 15/16 | 57 | 36 | 100 | 145 | 145 | 25 | 504
1407 | 2017-03-07 | 2017-05-30 | 2017-12-11 | 2017-12-11 | COMP | 2018-11-21 | COMP | 2020-01-30 | COMP | 2020-02-27 | COMP | 2020-05-20 | COMP | Rule 15/16 | 60 | 135 | 240 | 297 | 20 | 60 | 807
10648 | 2017-03-07 | 2019-03-25 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2020-03-02 | COMP | 2020-05-11 | COMP | Rule 15/16 | 515 | 47 | 37 | 1 | 154 | 51 | 800
1201 | 2017-03-08 | 2017-04-19 | 2017-09-10 | 2017-09-10 | COMP | 2018-07-10 | COMP | 2018-07-16 | COMP | 2019-09-04 | COMP | 2019-09-26 | COMP | Rule 15/16 | 31 | 100 | 208 | 5 | 287 | 17 | 644
1244 | 2017-03-08 | 2017-04-28 | 2018-07-10 | 2018-07-10 | COMP | 2018-10-30 | COMP | 2019-01-04 | COMP | 2019-05-31 | COMP | 2020-01-02 | COMP | Rule 15/16 | 38 | 301 | 80 | 44 | 103 | 148 | 709
1526 | 2017-03-08 | 2017-06-16 | 2017-11-30 | 2017-11-30 | COMP | 2018-05-31 | COMP | 2019-01-16 | COMP | 2018-11-13 | COMP | 2019-01-24 | COMP | Rule 16 | 72 | 115 | 126 | 158 | 0 | 6 | 473
1820 | 2017-03-08 | 2017-08-02 | 2017-12-11 | 2017-12-11 | COMP | 2018-07-09 | COMP | 2018-07-09 | COMP | 2018-12-18 | COMP | 2019-02-07 | COMP | Rule 16 | 104 | 90 | 145 | 1 | 113 | 35 | 483
2443 | 2017-03-08 | 2017-11-30 | 2018-01-26 | 2018-01-26 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-01-22 | COMP | 2019-04-02 | COMP | Rule 15/16 | 186 | 39 | 213 | 1 | 36 | 50 | 520
2492 | 2017-03-08 | 2017-12-08 | 2018-03-20 | 2018-03-20 | COMP | 2018-08-08 | COMP | 2018-08-08 | COMP | 2019-02-12 | COMP | 2019-03-13 | COMP | Rule 15/16 | 192 | 69 | 100 | 1 | 128 | 21 | 506
1849 | 2017-03-09 | 2017-08-09 | 2017-10-10 | 2017-10-10 | COMP | 2017-11-01 | COMP | 2018-03-05 | COMP | 2019-04-01 | COMP | 2019-04-26 | COMP | Rule 15/16 | 108 | 44 | 17 | 82 | 271 | 20 | 537
1982 | 2017-03-09 | 2017-09-01 | 2018-09-21 | 2018-09-21 | COMP | 2019-02-06 | COMP | 2019-02-22 | COMP | 2019-06-29 | INPR | 2019-03-13 | COMP | Rule 16 | 125 | 265 | 93 | 12 |  |  | 505
1073 | 2017-03-10 | 2017-03-20 | 2017-05-09 | 2017-05-09 | COMP | 2017-05-31 | COMP | 2017-09-18 | COMP | 2019-02-21 | COMP | 2019-06-17 | COMP | Rule 16 | 7 | 37 | 16 | 77 | 357 | 82 | 571
1080 | 2017-03-10 | 2017-03-22 | 2017-07-25 | 2017-07-25 | COMP | 2018-01-26 | COMP | 2018-02-17 | COMP | 2019-04-03 | COMP | 2019-08-27 | COMP | Other | 9 | 88 | 127 | 16 | 282 | 103 | 621
2089 | 2017-03-10 | 2017-09-21 | 2017-10-27 | 2017-10-27 | COMP | 2018-04-04 | COMP | 2018-04-04 | COMP | 2018-08-15 | COMP | 2022-03-28 | COMP | Rule 16 | 137 | 27 | 107 | 1 | 94 | 909 | 1270
2135 | 2017-03-10 | 2017-09-27 | 2017-11-13 | 2017-11-13 | COMP | 2017-12-01 | COMP | 2018-01-04 | COMP | 2018-07-19 | COMP | 2022-06-10 | COMP | Rule 16 | 141 | 33 | 13 | 23 | 137 | 981 | 1323
4536 | 2017-03-10 | 2018-01-24 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-10-28 | COMP | 2019-11-21 | COMP | Rule 15/16 | 220 | 253 | 37 | 1 | 157 | 18 | 681
5852 | 2017-03-10 | 2018-07-07 | 2018-09-27 | 2018-09-27 | COMP | 2018-12-24 | COMP | 2018-12-24 | COMP | 2019-02-04 | COMP | 2019-04-12 | COMP | Rule 16 | 334 | 58 | 60 | 1 | 28 | 49 | 526
1233 | 2017-03-13 | 2017-04-26 | 2017-05-24 | 2017-05-24 | COMP | 2017-07-19 | COMP | 2017-07-19 | COMP | 2019-10-23 | COMP | 2019-11-08 | COMP | Other | 33 | 21 | 39 | 1 | 570 | 13 | 672
1252 | 2017-03-13 | 2017-04-30 | 2018-08-20 | 2018-08-20 | COMP | 2018-11-07 | COMP | 2018-11-13 | COMP | 2019-12-05 | COMP | 2020-01-30 | COMP | Rule 16 | 35 | 329 | 57 | 4 | 266 | 38 | 725
1253 | 2017-03-13 | 2017-04-30 | 2018-08-20 | 2018-08-20 | COMP | 2018-10-25 | COMP | 2018-11-02 | COMP | 2020-01-14 | COMP | 2020-08-03 | COMP | Rule 15/16 | 35 | 329 | 48 | 7 | 298 | 142 | 855
1325 | 2017-03-13 | 2017-05-10 | 2017-08-10 | 2017-08-10 | COMP | 2017-10-23 | COMP | 2017-10-23 | COMP | 2018-11-01 | COMP | 2019-01-10 | COMP | Rule 16 | 43 | 65 | 52 | 1 | 259 | 46 | 461
1535 | 2017-03-13 | 2017-06-19 | 2017-10-30 | 2017-10-30 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2018-10-01 | COMP | 2020-12-24 | COMP | Rule 16 | 70 | 94 | 5 | 1 | 227 | 562 | 954
2209 | 2017-03-13 | 2017-10-12 | 2019-01-04 | 2019-01-04 | COMP | 2019-01-25 | COMP | 2021-11-16 | INPR | 2019-01-30 | COMP | 2021-12-02 | COMP | Rule 16 | 151 | 307 | 15 |  |  |  | 1189
1096 | 2017-03-14 | 2017-03-24 | 2017-10-09 | 2017-10-09 | COMP | 2017-12-11 | COMP | 2019-01-08 | COMP | 2018-12-24 | COMP | 2019-01-26 | COMP | Rule 16 | 9 | 139 | 43 | 270 | 0 | 13 | 470
1140 | 2017-03-14 | 2017-04-05 | 2017-09-20 | 2017-09-20 | COMP | 2019-02-13 | COMP | 2019-03-21 | COMP | 2023-04-15 | INPR | 2019-03-19 | COMP | Rule 16 | 17 | 118 | 350 | 26 |  |  | 506
1174 | 2017-03-14 | 2017-04-13 | 2018-05-30 | 2018-05-30 | COMP | 2018-06-19 | COMP | 2019-12-31 | COMP | 2019-10-15 | COMP | 2020-01-21 | COMP | Rule 15/16 | 23 | 284 | 15 | 385 | 0 | 14 | 717
1408 | 2017-03-14 | 2017-05-30 | 2017-09-18 | 2017-09-18 | COMP | 2017-10-12 | COMP | 2017-10-12 | COMP | 2019-01-22 | COMP | 2019-01-23 | COMP | Rule 16 | 55 | 78 | 19 | 1 | 318 | 2 | 468
1591 | 2017-03-14 | 2017-06-28 | 2017-08-20 | 2017-08-20 | COMP | 2017-09-18 | COMP | 2017-09-18 | COMP | 2017-11-07 | COMP | 2021-05-14 | COMP | Rule 16 | 76 | 37 | 20 | 1 | 37 | 883 | 1050
1780 | 2017-03-14 | 2017-07-25 | 2018-02-06 | 2018-02-06 | COMP | 2020-07-14 | COMP | 2020-07-16 | COMP | 2021-04-27 | COMP | 2021-05-21 | COMP | Rule 16 | 94 | 134 | 614 | 3 | 196 | 19 | 1055
1795 | 2017-03-14 | 2017-07-27 | 2017-10-03 | 2020-01-07 | COMP | 2020-02-27 | COMP | 2020-05-19 | COMP | 2020-04-20 | COMP | 2020-11-13 | COMP | Rule 15/16 | 96 | 48 | 36 | 59 | 0 | 126 | 926
2140 | 2017-03-14 | 2017-09-28 | 2018-05-20 | 2018-05-20 | COMP | 2018-09-05 | COMP | 2018-12-27 | COMP | 2018-12-28 | COMP | 2019-02-19 | COMP | Rule 15/16 | 140 | 160 | 75 | 78 | 2 | 35 | 486
2272 | 2017-03-14 | 2017-10-26 | 2018-03-12 | 2018-03-12 | COMP | 2018-03-16 | COMP | 2019-04-19 | COMP | 2020-07-13 | COMP | 2020-08-31 | COMP | Rule 15/16 | 160 | 91 | 5 | 276 | 311 | 36 | 874
3534 | 2017-03-14 | 2018-05-12 | 2018-12-08 | 2018-12-08 | COMP | 2019-02-28 | COMP | 2023-02-25 | REQD | 2019-12-18 | COMP | 2020-02-11 | COMP | Rule 15/16 | 294 | 144 | 55 |  |  |  | 732
4365 | 2017-03-14 | 2017-10-11 | 2018-04-09 | 2018-04-09 | COMP | 2018-06-20 | COMP | 2018-06-20 | COMP | 2018-12-27 | COMP | 2019-03-18 | COMP | Rule 16 | 149 | 122 | 52 | 1 | 131 | 55 | 505
5490 | 2017-03-14 | 2018-06-04 | 2018-08-03 | 2018-08-03 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2019-03-17 | COMP | 2019-04-24 | COMP | Rule 16 | 309 | 44 | 34 | 1 | 120 | 28 | 532
9831 | 2017-03-14 | 2019-02-19 | 2019-04-30 | 2021-03-28 | COMP | 2021-04-13 | COMP | 2021-08-09 | COMP | 2021-07-28 | COMP | 2021-09-14 | COMP | Rule 16 | 486 | 51 | 12 | 83 | 0 | 26 | 1134
1268 | 2017-03-15 | 2017-05-03 | 2017-07-26 | 2017-07-26 | COMP | 2017-10-11 | COMP | 2018-06-12 | COMP | 2019-05-22 | COMP | 2019-05-17 | COMP | Rule 16 | 36 | 59 | 55 | 167 | 238 |  | 548
1335 | 2017-03-15 | 2017-05-12 | 2017-07-24 | 2017-07-24 | COMP | 2017-08-04 | COMP | 2017-08-04 | COMP | 2018-01-11 | COMP | 2021-01-16 | COMP | Rule 16 | 43 | 50 | 10 | 1 | 109 | 758 | 966
1406 | 2017-03-15 | 2017-05-30 | 2018-02-21 | 2018-02-21 | COMP | 2019-08-14 | COMP | 2019-11-06 | COMP | 2019-10-02 | COMP | 2019-12-18 | COMP | Rule 15/16 | 54 | 183 | 374 | 60 | 0 | 28 | 695
1444 | 2017-03-15 | 2017-06-05 | 2017-11-15 | 2017-11-15 | COMP | 2018-09-11 | COMP | 2019-01-14 | COMP | 2019-04-19 | COMP | 2019-06-19 | COMP | Rule 16 | 58 | 115 | 206 | 85 | 68 | 43 | 570
1450 | 2017-03-15 | 2017-06-06 | 2017-09-14 | 2017-09-14 | COMP | 2018-09-12 | COMP | 2018-10-11 | COMP | 2020-07-04 | INPR | 2019-06-21 | COMP | Rule 16 | 59 | 71 | 250 | 22 |  |  | 572
1578 | 2017-03-15 | 2017-06-26 | 2018-01-10 | 2018-01-10 | COMP | 2018-03-13 | COMP | 2018-04-13 | COMP | 2019-07-01 | COMP | 2019-11-13 | COMP | Rule 16 | 73 | 136 | 43 | 24 | 306 | 95 | 672
1629 | 2017-03-15 | 2017-07-06 | 2018-06-06 | 2018-06-06 | COMP | 2018-07-11 | COMP | 2018-09-21 | COMP | 2019-01-15 | COMP | 2019-02-07 | COMP | Rule 16 | 80 | 231 | 25 | 52 | 78 | 17 | 478
1675 | 2017-03-15 | 2017-07-13 | 2018-03-20 | 2018-03-20 | COMP | 2018-09-28 | COMP | 2019-04-15 | COMP | 2020-05-13 | COMP | 2019-08-29 | COMP | Rule 15/16 | 85 | 171 | 136 | 135 | 273 |  | 620
1955 | 2017-03-15 | 2017-08-25 | 2017-10-11 | 2017-10-11 | COMP | 2018-05-10 | COMP | 2018-06-04 | COMP | 2019-07-21 | INPR | 2019-04-15 | COMP | Rule 15/16 | 116 | 33 | 145 | 17 |  |  | 524
1224 | 2017-03-16 | 2017-04-25 | 2017-12-18 | 2017-12-18 | COMP | 2017-12-26 | COMP | 2017-12-30 | COMP | 2019-07-21 | INPR | 2019-03-25 | COMP | Rule 15/16 | 29 | 164 | 6 | 4 |  |  | 508
1393 | 2017-03-16 | 2017-05-25 | 2017-10-04 | 2017-10-04 | COMP | 2018-06-05 | COMP | 2018-06-28 | COMP | 2018-11-19 | COMP | 2019-01-03 | COMP | Rule 15/16 | 51 | 92 | 167 | 18 | 100 | 30 | 453
1635 | 2017-03-16 | 2017-07-07 | 2017-09-29 | 2017-09-29 | COMP | 2018-02-07 | COMP | 2018-04-27 | COMP | 2018-12-26 | COMP | 2019-01-25 | COMP | Rule 16 | 80 | 60 | 88 | 57 | 167 | 21 | 468
2180 | 2017-03-16 | 2017-10-05 | 2018-07-30 | 2018-07-30 | COMP | 2018-10-22 | COMP | 2019-01-02 | COMP | 2020-12-04 | COMP | 2021-02-21 | COMP | Rule 16 | 143 | 204 | 60 | 48 | 486 | 52 | 988
4407 | 2017-03-16 | 2017-11-20 | 2018-09-04 | 2019-03-25 | COMP | 2019-05-08 | COMP | 2019-08-07 | COMP | 2019-09-03 | COMP | 2019-09-30 | COMP | Rule 16 | 174 | 198 | 33 | 64 | 19 | 20 | 640
5172 | 2017-03-16 | 2018-05-07 | 2018-08-13 | 2018-09-26 | COMP | 2018-10-17 | COMP | 2018-11-27 | COMP | 2020-09-16 | COMP | 2020-10-19 | COMP | Rule 16 | 288 | 69 | 16 | 27 | 456 | 24 | 906
6823 | 2017-03-16 | 2018-09-12 | 2019-01-17 | 2019-04-17 | COMP | 2019-04-26 | COMP | 2019-03-28 | COMP | 2019-03-29 | COMP | 2019-06-27 | COMP | Rule 15/16 | 377 | 87 | 8 |  | 2 | 64 | 575
1143 | 2017-03-17 | 2017-04-05 | 2017-07-14 | 2018-09-17 | COMP | 2018-10-01 | COMP | 2019-03-25 | COMP | 2021-01-02 | INPR | 2019-08-15 | COMP | Rule 16 | 14 | 71 | 11 | 119 |  |  | 608
1235 | 2017-03-17 | 2017-04-26 | 2017-06-13 | 2017-06-13 | COMP | 2017-11-27 | COMP | 2017-11-27 | COMP | 2020-01-17 | COMP | 2020-01-15 | COMP | Other | 29 | 34 | 115 | 1 | 538 |  | 711
1293 | 2017-03-17 | 2017-05-05 | 2019-11-13 | 2019-11-13 | COMP | 2020-01-27 | COMP | 2020-02-05 | COMP |  |  | 2020-04-17 | COMP | Rule 16 | 36 | 635 | 49 | 8 |  |  | 776
1358 | 2017-03-17 | 2017-05-17 | 2018-02-08 | 2018-02-08 | COMP | 2018-05-08 | COMP | 2018-06-26 | COMP | 2019-07-21 | INPR | 2019-04-12 | COMP | Rule 15/16 | 44 | 183 | 63 | 35 |  |  | 521
1497 | 2017-03-17 | 2017-06-09 | 2017-08-18 | 2017-08-18 | COMP |  |  |  |  | 2017-12-22 | COMP | 2022-07-21 | COMP | Other | 60 | 50 |  |  |  |  | 1345
2652 | 2017-03-17 | 2018-01-12 | 2019-02-19 | 2019-11-26 | COMP | 2019-12-27 | COMP | 2020-06-03 | COMP | 2020-10-22 | COMP | 2020-11-10 | COMP | Rule 16 | 208 | 276 | 21 | 110 | 101 | 14 | 921
6280 | 2017-03-17 | 2018-08-08 | 2018-10-08 | 2018-10-24 | COMP | 2018-11-19 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-01-25 | COMP | Rule 16 | 352 | 43 | 18 | 3 | 1 | 43 | 467
4723 | 2017-03-20 | 2018-03-23 | 2018-09-19 | 2018-09-19 | COMP | 2018-12-06 | COMP | 2019-03-01 | COMP | 2019-12-28 | INPR | 2019-09-04 | COMP | Rule 16 | 255 | 126 | 54 | 58 |  |  | 620
6573 | 2017-03-20 | 2018-08-27 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-03-26 | COMP | 2019-05-01 | COMP | Rule 16 | 364 | 39 | 26 | 1 | 81 | 27 | 533
17234 | 2017-03-20 | 2020-02-05 | 2020-03-06 | 2020-07-29 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2021-05-21 | COMP | 2021-06-16 | COMP | Rule 15/16 | 724 | 22 | 8 | 1 | 198 | 18 | 1068
1215 | 2017-03-21 | 2017-04-24 | 2018-10-08 | 2018-10-08 | COMP | 2019-01-24 | COMP | 2019-10-17 | INPR | 2019-11-08 | COMP | 2019-12-18 | COMP | Rule 15/16 | 25 | 368 | 73 |  |  |  | 691
1220 | 2017-03-21 | 2017-04-25 | 2017-06-26 | 2020-07-15 | COMP | 2020-08-27 | COMP | 2020-08-27 | COMP | 2020-12-01 | COMP | 2020-12-18 | COMP | Rule 16 | 26 | 44 | 32 | 1 | 65 | 14 | 944
1301 | 2017-03-21 | 2017-05-05 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-19 | COMP | 2019-09-20 | COMP | 2020-05-30 | INPR | 2020-01-29 | COMP | Rule 16 | 34 | 566 | 10 | 24 |  |  | 718
1321 | 2017-03-21 | 2017-05-10 | 2017-11-03 | 2017-11-03 | COMP | 2018-02-23 | COMP | 2020-03-05 | COMP | 2020-03-16 | COMP | 2020-04-29 | COMP | Rule 16 | 37 | 125 | 74 | 510 | 8 | 33 | 782
1368 | 2017-03-21 | 2017-05-18 | 2019-07-11 | 2019-07-11 | COMP | 2019-10-03 | COMP | 2019-11-14 | COMP | 2020-05-30 | COMP | 2020-01-15 | COMP | Rule 16 | 43 | 539 | 60 | 30 | 135 |  | 709
1372 | 2017-03-21 | 2017-05-19 | 2017-07-17 | 2017-07-17 | COMP | 2017-07-17 | NOTN | 2017-07-17 | COMP | 2017-08-15 | COMP | 2019-04-03 | COMP | Other | 44 | 40 |  | 1 | 22 | 409 | 512
1562 | 2017-03-21 | 2017-06-23 | 2017-09-02 | 2017-09-02 | COMP | 2017-12-04 | COMP | 2017-12-04 | COMP | 2018-02-12 | COMP | 2020-12-17 | COMP | Rule 16 | 68 | 50 | 62 | 1 | 48 | 718 | 943
1590 | 2017-03-21 | 2017-06-28 | 2018-02-13 | 2018-02-13 | COMP | 2018-03-27 | COMP | 2018-04-26 | COMP | 2018-12-14 | COMP | 2019-01-24 | COMP | Rule 15/16 | 71 | 157 | 30 | 23 | 161 | 27 | 464
1628 | 2017-03-21 | 2017-07-06 | 2018-09-11 | 2019-10-10 | COMP | 2020-01-02 | COMP | 2019-10-10 | COMP | 2020-01-28 | COMP | 2020-05-19 | COMP | Rule 15/16 | 76 | 298 | 56 |  | 73 | 80 | 796
1903 | 2017-03-21 | 2017-08-18 | 2018-03-09 | 2018-03-09 | COMP | 2018-05-31 | COMP | 2019-01-07 | COMP | 2020-01-13 | COMP | 2020-02-25 | COMP | Rule 15/16 | 107 | 138 | 59 | 151 | 256 | 30 | 736
5101 | 2017-03-21 | 2018-04-30 | 2018-07-18 | 2018-07-18 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-08-23 | COMP | 2019-08-30 | COMP | Rule 16 | 280 | 56 | 150 | 1 | 129 | 6 | 617
5225 | 2017-03-21 | 2018-05-14 | 2018-06-25 | 2018-06-25 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-09-22 | INPR | 2019-05-03 | COMP | Rule 16 | 290 | 30 | 140 | 1 |  |  | 534
1132 | 2017-03-22 | 2017-04-03 | 2017-10-17 | 2018-03-11 | COMP | 2019-05-01 | COMP | 2019-07-31 | COMP | 2019-06-11 | COMP | 2019-08-09 | COMP | Rule 15/16 | 9 | 139 | 288 | 64 | 0 | 8 | 601
1288 | 2017-03-22 | 2017-05-05 | 2017-10-16 | 2017-10-16 | COMP | 2018-01-22 | COMP | 2018-04-13 | COMP | 2018-02-20 | COMP | 2019-05-22 | COMP | Rule 16 | 33 | 114 | 65 | 59 | 0 | 279 | 546
1469 | 2017-03-22 | 2017-06-07 | 2017-11-10 | 2017-11-10 | COMP | 2017-11-20 | COMP | 2017-11-20 | COMP | 2019-02-28 | COMP | 2019-04-15 | COMP | Rule 16 | 55 | 110 | 6 | 1 | 318 | 33 | 519
1584 | 2017-03-22 | 2017-06-27 | 2017-08-28 | 2017-12-10 | COMP | 2018-02-15 | COMP | 2018-11-27 | COMP | 2019-03-13 | COMP | 2019-05-17 | COMP | Rule 16 | 69 | 44 | 46 | 197 | 73 | 48 | 543
2005 | 2017-03-22 | 2017-09-06 | 2017-12-13 | 2018-12-17 | COMP | 2018-12-18 | COMP | 2019-01-17 | COMP | 2019-01-04 | COMP | 2019-04-30 | COMP | Rule 16 | 118 | 68 | 2 | 21 | 0 | 72 | 530
2233 | 2017-03-22 | 2017-10-19 | 2018-05-30 | 2018-05-30 | COMP | 2018-08-14 | COMP | 2019-01-18 | COMP | 2019-01-22 | COMP | 2019-03-13 | COMP | Rule 15/16 | 149 | 152 | 54 | 108 | 2 | 36 | 496
2528 | 2017-03-22 | 2017-12-16 | 2018-04-26 | 2018-04-26 | COMP | 2018-06-26 | COMP | 2018-06-26 | COMP | 2018-12-24 | COMP | 2019-01-09 | COMP | Rule 16 | 187 | 90 | 43 | 1 | 125 | 11 | 453
5540 | 2017-03-22 | 2018-06-11 | 2018-12-14 | 2018-12-14 | COMP | 2018-12-14 | NOTN | 2019-04-01 | COMP | 2018-12-14 | COMP | 2019-05-08 | COMP | Other | 308 | 130 |  | 73 | 0 | 28 | 536
1334 | 2017-03-23 | 2017-05-12 | 2018-05-01 | 2018-05-01 | COMP | 2020-07-20 | COMP | 2020-10-12 | COMP | 2020-10-21 | COMP | 2021-02-22 | COMP | Rule 15/16 | 37 | 243 | 559 | 60 | 8 | 82 | 984
5432 | 2017-03-23 | 2018-05-30 | 2018-09-27 | 2018-09-27 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-09-19 | COMP | 2019-10-15 | COMP | Rule 16 | 299 | 85 | 76 | 1 | 171 | 19 | 646
39139 | 2017-03-23 | 2022-10-03 | 2023-02-01 | 2023-02-01 | COMP | 2023-02-01 | NOTN | 2023-10-12 | COMP | 2023-10-13 | NOTN | 2023-12-13 | COMP | Other | 1392 | 82 |  | 177 |  |  | 1690
1227 | 2017-03-24 | 2017-04-26 | 2017-10-31 | 2017-10-31 | COMP | 2019-03-05 | COMP | 2019-03-06 | COMP | 2018-10-18 | COMP | 2019-05-02 | COMP | Rule 15/16 | 24 | 132 | 334 | 2 | 0 | 42 | 530
1365 | 2017-03-24 | 2017-05-17 | 2019-04-10 | 2019-04-10 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2020-05-04 | COMP | 2020-06-15 | COMP | Rule 16 | 39 | 476 | 67 | 1 | 203 | 30 | 811
1522 | 2017-03-24 | 2017-06-15 | 2017-08-19 | 2017-08-19 | COMP | 2018-03-10 | COMP | 2018-03-10 | COMP | 2019-06-27 | COMP | 2019-07-31 | COMP | Rule 16 | 59 | 46 | 137 | 0 | 328 | 24 | 592
1757 | 2017-03-25 | 2017-07-19 | 2017-10-06 | 2018-06-11 | COMP | 2018-11-15 | COMP | 2019-01-11 | COMP | 2018-11-15 | COMP | 2019-01-31 | COMP | Rule 16 | 81 | 57 | 111 | 38 | 0 | 14 | 465
1276 | 2017-03-27 | 2017-05-04 | 2018-01-24 | 2019-01-10 | COMP | 2019-05-01 | COMP | 2018-10-24 | COMP | 2019-05-08 | COMP | 2019-05-28 | COMP | Rule 16 | 29 | 181 | 78 |  | 134 | 14 | 546
2025 | 2017-03-27 | 2017-09-08 | 2017-11-22 | 2017-11-22 | COMP | 2018-06-14 | COMP | 2019-04-08 | COMP | 2019-04-09 | COMP | 2019-05-02 | COMP | Rule 16 | 117 | 53 | 140 | 204 | 2 | 18 | 529
2850 | 2017-03-27 | 2018-02-08 | 2018-11-11 | 2018-11-11 | COMP | 2018-11-29 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-01-30 | COMP | Rule 16 | 220 | 193 | 11 | 24 | 1 | 19 | 464
3541 | 2017-03-27 | 2018-05-14 | 2018-05-19 | 2018-05-18 | COMP | 2019-01-08 | COMP | 2019-04-22 | COMP | 2019-04-17 | COMP | 2019-06-26 | COMP | Other | 286 | 5 | 160 | 73 | 0 | 47 | 567
4727 | 2017-03-27 | 2018-03-21 | 2018-06-01 | 2018-06-01 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-02-27 | COMP | 2020-05-12 | COMP | Rule 16 | 248 | 52 | 435 | 1 | 2 | 54 | 787
1121 | 2017-03-28 | 2017-03-28 | 2017-12-22 | 2017-12-22 | COMP | 2018-03-20 | COMP | 2018-03-21 | COMP |  | INPR | 2021-03-22 | COMP | Rule 16 | 1 | 188 | 59 | 2 |  |  | 1001
1148 | 2017-03-28 | 2017-04-07 | 2017-06-02 | 2017-06-02 | COMP | 2017-08-07 | COMP | 2017-08-07 | INPR | 2022-03-19 | REQD | 2021-03-12 | COMP | Rule 16 | 9 | 40 | 46 |  |  |  | 995
1187 | 2017-03-28 | 2017-04-18 | 2017-11-20 | 2017-11-20 | COMP | 2018-01-02 | COMP | 2018-01-02 | COMP | 2018-04-18 | COMP | 2020-11-19 | COMP | Rule 16 | 16 | 151 | 28 | 1 | 75 | 654 | 920
1292 | 2017-03-28 | 2017-05-05 | 2018-10-12 | 2018-10-12 | COMP | 2019-10-07 | COMP | 2019-10-14 | COMP | 2019-11-13 | COMP | 2019-11-29 | COMP | Rule 15/16 | 29 | 363 | 247 | 6 | 22 | 11 | 673
1295 | 2017-03-28 | 2017-05-05 | 2018-06-04 | 2018-06-04 | COMP | 2018-10-04 | COMP | 2019-09-05 | COMP | 2019-12-19 | COMP | 2020-06-25 | COMP | Rule 16 | 29 | 271 | 87 | 231 | 73 | 131 | 817
1337 | 2017-03-28 | 2017-05-13 | 2017-08-19 | 2017-08-19 | COMP | 2018-09-14 | COMP | 2018-09-22 | COMP | 2019-06-09 | COMP | 2019-08-28 | COMP | Rule 15/16 | 34 | 68 | 269 | 6 | 177 | 57 | 610
1586 | 2017-03-28 | 2017-06-27 | 2019-03-23 | 2019-03-23 | COMP | 2019-04-16 | COMP | 2019-08-01 | COMP | 2020-02-18 | COMP | 2020-06-24 | COMP | Rule 15/16 | 65 | 435 | 17 | 76 | 136 | 91 | 816
2034 | 2017-03-28 | 2017-09-08 | 2018-03-29 | 2018-03-29 | COMP | 2018-05-03 | COMP | 2018-06-01 | COMP | 2019-01-14 | COMP | 2019-01-25 | COMP | Rule 15/16 | 116 | 138 | 26 | 21 | 155 | 9 | 460
2048 | 2017-03-28 | 2017-09-13 | 2017-11-06 | 2017-11-06 | COMP | 2017-12-06 | COMP | 2017-12-06 | COMP | 2019-04-03 | COMP | 2019-05-10 | COMP | Rule 16 | 119 | 39 | 20 | 1 | 332 | 28 | 534
2720 | 2017-03-28 | 2018-01-23 | 2020-02-04 | 2020-02-04 | COMP | 2019-09-09 | NOTN | 2020-02-10 | COMP | 2020-01-29 | COMP | 2020-06-05 | COMP | Other | 207 | 511 |  | 5 | 0 | 83 | 803
3304 | 2017-03-28 | 2018-04-04 | 2019-05-16 | 2019-05-16 | COMP | 2021-06-21 | COMP | 2021-06-21 | COMP | 2021-06-30 | COMP | 2021-07-21 | COMP | Rule 16 | 257 | 282 | 528 | 1 | 8 | 15 | 1086
5034 | 2017-03-28 | 2018-04-24 | 2018-06-03 | 2018-06-03 | COMP | 2018-08-09 | COMP | 2018-08-09 | COMP | 2019-02-12 | COMP | 2019-04-02 | COMP | Rule 16 | 271 | 28 | 48 | 1 | 127 | 35 | 506
1277 | 2017-03-29 | 2017-05-04 | 2018-11-02 | 2018-11-02 | COMP | 2019-01-22 | COMP | 2019-04-09 | COMP | 2019-05-20 | COMP | 2019-12-10 | COMP | Rule 16 | 27 | 379 | 52 | 55 | 30 | 141 | 679
1649 | 2017-03-29 | 2017-07-10 | 2018-02-06 | 2019-07-08 | COMP | 2019-07-03 | COMP | 2019-07-06 | COMP | 2018-09-05 | COMP | 2019-09-04 | COMP | Rule 16 | 72 | 145 |  | 2 | 0 | 42 | 613
4034 | 2017-03-29 | 2018-12-19 | 2019-01-07 | 2019-01-07 | COMP | 2021-06-21 | COMP | 2021-06-21 | COMP | 2021-06-25 | COMP | 2021-07-21 | COMP | Rule 16 | 435 | 12 | 619 | 1 | 5 | 18 | 1085
4645 | 2017-03-29 | 2018-02-26 | 2018-07-02 | 2018-12-14 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-07-16 | COMP | 2020-01-25 | COMP | Rule 16 | 229 | 90 | 118 | 1 | 30 | 132 | 709
1213 | 2017-03-30 | 2017-04-23 | 2018-08-27 | 2018-08-27 | COMP | 2018-12-04 | COMP | 2019-01-03 | COMP | 2018-12-11 | COMP | 2019-03-26 | COMP | Rule 15/16 | 17 | 339 | 68 | 21 | 0 | 57 | 499
1366 | 2017-03-30 | 2017-05-18 | 2018-01-06 | 2018-01-06 | COMP | 2018-03-23 | NOTN | 2018-03-23 | COMP | 2018-03-23 | COMP | 2022-09-16 | COMP | Other | 36 | 159 |  | 53 | 1 | 1130 | 1376
2719 | 2017-03-30 | 2018-01-23 | 2020-01-28 | 2020-01-28 | COMP | 2019-09-09 | NOTN | 2020-01-28 | COMP | 2020-01-27 | COMP | 2020-06-04 | COMP | Other | 205 | 506 |  | 1 | 0 | 91 | 800
4460 | 2017-03-30 | 2017-12-15 | 2018-07-11 | 2018-07-11 | COMP | 2019-10-28 | COMP | 2018-12-18 | COMP | 2019-09-24 | COMP | 2019-10-18 | COMP | Rule 16 | 181 | 143 | 328 |  | 194 | 19 | 644
5189 | 2017-03-30 | 2018-05-08 | 2018-07-25 | 2018-07-25 | COMP | 2018-08-30 | COMP | 2018-08-30 | COMP | 2018-11-29 | COMP | 2019-01-10 | COMP | Rule 16 | 279 | 55 | 27 | 1 | 62 | 29 | 448
5627 | 2017-03-30 | 2018-06-21 | 2018-09-17 | 2018-09-17 | COMP | 2019-08-28 | COMP | 2019-06-10 | COMP | 2020-02-10 | COMP | 2020-06-29 | COMP | Rule 16 | 310 | 61 | 239 |  | 168 | 99 | 817
1370 | 2017-03-31 | 2017-05-18 | 2017-08-30 | 2019-08-29 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2020-04-09 | COMP | 2020-06-12 | COMP | Rule 15/16 | 35 | 73 | 39 | 1 | 115 | 46 | 805
1470 | 2017-03-31 | 2017-06-07 | 2019-07-08 | 2019-07-08 | COMP | 2019-07-30 | COMP | 2019-10-08 | COMP | 2019-11-01 | COMP | 2019-10-23 | COMP | Rule 16 | 48 | 523 | 17 | 50 | 19 |  | 646
1471 | 2017-03-31 | 2017-06-07 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-30 | COMP | 2019-09-24 | COMP | 2020-01-31 | COMP | 2019-10-22 | COMP | Rule 16 | 48 | 519 | 21 | 40 | 88 |  | 645
1964 | 2017-03-31 | 2017-08-28 | 2020-04-06 | 2020-04-06 | COMP | 2020-05-08 | COMP | 2020-07-10 | COMP | 2020-06-19 | COMP | 2020-09-15 | COMP | Rule 16 | 105 | 653 | 25 | 45 | 0 | 47 | 871
2261 | 2017-03-31 | 2017-10-25 | 2018-01-04 | 2019-11-15 | COMP | 2020-02-25 | COMP | 2020-03-09 | COMP | 2020-03-16 | COMP | 2020-07-06 | COMP | Rule 15/16 | 146 | 47 | 67 | 10 | 6 | 80 | 821
4397 | 2017-03-31 | 2017-11-13 | 2018-03-09 | 2018-03-09 | COMP | 2018-06-07 | COMP | 2018-06-07 | COMP | 2019-06-25 | COMP | 2019-12-16 | COMP | Rule 15/16 | 158 | 79 | 64 | 1 | 264 | 120 | 681
5517 | 2017-03-31 | 2018-06-07 | 2019-02-15 | 2019-02-15 | COMP | 2019-11-27 | COMP | 2020-01-22 | COMP | 2021-04-02 | COMP | 2021-05-11 | COMP | Rule 15/16 | 299 | 174 | 199 | 36 | 303 | 28 | 1034
6094 | 2017-03-31 | 2018-07-25 | 2018-12-04 | 2020-02-24 | COMP | 2020-06-12 | COMP | 2020-06-17 | COMP |  | INPR | 2020-08-19 | COMP | Rule 15/16 | 332 | 91 | 79 | 4 |  |  | 853
2101 | 2017-04-01 | 2017-09-25 | 2018-09-14 | 2018-09-14 | COMP | 2019-03-12 | COMP | 2019-10-18 | COMP | 2019-10-11 | COMP | 2020-01-08 | COMP | Rule 15/16 | 123 | 245 | 121 | 156 | 0 | 54 | 695
3180 | 2017-04-01 | 2018-03-20 | 2018-05-25 | 2018-05-25 | COMP | 2018-06-18 | COMP | 2018-08-06 | COMP | 2023-11-11 | INPR | 2020-07-29 | COMP | Rule 16 | 242 | 49 | 16 | 35 |  |  | 837
4427 | 2017-04-02 | 2017-12-06 | 2018-07-26 | 2018-07-26 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2022-08-08 | COMP | 2022-11-30 | COMP | Rule 16 | 172 | 161 | 103 | 1 | 913 | 79 | 1424
1319 | 2017-04-03 | 2017-05-10 | 2017-07-21 | 2017-07-21 | COMP | 2017-08-30 | COMP | 2017-09-06 | COMP |  |  | 2019-05-04 | COMP | Rule 16 | 28 | 51 | 29 | 5 |  |  | 525
1356 | 2017-04-03 | 2017-05-16 | 2018-09-01 | 2018-09-01 | COMP | 2018-10-02 | COMP | 2018-10-02 | COMP | 2019-01-23 | COMP | 2019-02-27 | COMP | Rule 16 | 32 | 327 | 21 | 1 | 76 | 25 | 478
1383 | 2017-04-03 | 2017-05-23 | 2019-07-09 | 2019-07-09 | COMP | 2019-09-13 | COMP | 2019-11-07 | COMP | 2019-10-21 | COMP | 2019-11-26 | COMP | Rule 15/16 | 37 | 534 | 48 | 40 | 0 | 13 | 668
1655 | 2017-04-03 | 2017-07-12 | 2017-09-05 | 2017-09-05 | COMP | 2017-10-31 | COMP | 2018-01-25 | COMP |  |  | 2021-03-05 | COMP | Rule 16 | 71 | 39 | 41 | 57 |  |  | 986
1776 | 2017-04-03 | 2017-07-24 | 2017-09-12 | 2017-09-12 | COMP | 2019-05-13 | COMP | 2019-05-23 | COMP | 2023-12-09 | INPR | 2020-10-20 | COMP | Rule 16 | 79 | 36 | 418 | 9 |  |  | 895
2733 | 2017-04-03 | 2018-01-25 | 2018-04-15 | 2018-04-15 | COMP | 2018-11-20 | COMP | 2019-09-19 | COMP | 2020-08-18 | COMP | 2020-10-13 | COMP | Rule 16 | 205 | 56 | 153 | 209 | 231 | 40 | 890
5194 | 2017-04-03 | 2018-05-09 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-11 | COMP | 2019-09-27 | COMP |  |  | 2020-09-14 | COMP | Rule 16 | 278 | 331 | 8 | 13 |  |  | 869
1239 | 2017-04-04 | 2017-04-27 | 2017-06-12 | 2017-06-12 | COMP | 2017-06-13 | NOTN | 2017-08-16 | COMP | 2018-10-30 | COMP | 2019-01-29 | COMP | Other | 18 | 32 |  | 47 | 304 | 60 | 457
1336 | 2017-04-04 | 2017-05-12 | 2017-07-19 | 2017-07-19 | COMP | 2020-01-08 | COMP | 2020-07-13 | COMP | 2020-07-14 | COMP | 2020-10-07 | COMP | Rule 15/16 | 29 | 47 | 620 | 131 | 2 | 61 | 885
1371 | 2017-04-04 | 2017-05-18 | 2018-01-03 | 2018-01-03 | COMP | 2018-04-24 | COMP | 2018-05-21 | COMP | 2018-12-11 | COMP | 2019-01-07 | COMP | Rule 16 | 33 | 157 | 78 | 20 | 141 | 18 | 442
1495 | 2017-04-04 | 2017-06-09 | 2017-09-29 | 2017-09-29 | COMP | 2017-10-16 | COMP | 2017-10-16 | COMP | 2018-12-18 | COMP | 2019-01-25 | COMP | Rule 16 | 48 | 79 | 12 | 1 | 294 | 26 | 455
3332 | 2017-04-04 | 2018-04-10 | 2019-02-07 | 2019-02-07 | COMP | 2019-05-17 | COMP | 2019-05-02 | COMP | 2023-04-15 | INPR | 2019-07-31 | COMP | Rule 15/16 | 256 | 209 | 71 |  |  |  | 585
3333 | 2017-04-04 | 2018-04-10 | 2018-11-27 | 2018-11-27 | COMP | 2018-12-11 | COMP | 2019-03-25 | COMP | 2019-04-20 | COMP | 2019-04-30 | COMP | Rule 15/16 | 256 | 160 | 11 | 71 | 20 | 7 | 521
4556 | 2017-04-04 | 2018-01-29 | 2018-05-23 | 2018-05-23 | COMP | 2018-08-22 | COMP | 2019-01-08 | COMP | 2018-12-07 | COMP | 2019-01-17 | COMP | Rule 16 | 206 | 82 | 64 | 94 | 0 | 8 | 450
6600 | 2017-04-04 | 2018-08-30 | 2018-09-24 | 2018-09-24 | COMP | 2019-01-10 | COMP | 2019-03-26 | COMP | 2020-07-21 | COMP | 2020-07-31 | COMP | Rule 16 | 356 | 17 | 74 | 52 | 335 | 9 | 838
11112 | 2017-04-04 | 2019-04-13 | 2019-08-14 | 2019-08-14 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-08-25 | COMP | 2020-10-26 | COMP | Rule 15/16 | 509 | 86 | 120 | 1 | 142 | 44 | 898
1162 | 2017-04-05 | 2017-04-10 | 2017-04-25 | 2018-08-09 | COMP | 2018-10-29 | COMP | 2018-11-13 | COMP | 2019-03-15 | COMP | 2019-04-30 | COMP | Rule 16 | 4 | 12 | 57 | 11 | 83 | 33 | 520
1228 | 2017-04-05 | 2017-04-26 | 2017-08-24 | 2017-08-24 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2017-08-23 | COMP | 2021-03-22 | COMP | Rule 16 | 16 | 85 | 418 | 1 | 0 | 479 | 995
1363 | 2017-04-05 | 2017-05-17 | 2017-07-14 | 2017-07-14 | COMP | 2017-08-10 | COMP | 2019-04-22 | COMP | 2019-07-08 | COMP | 2019-09-05 | COMP | Rule 16 | 31 | 41 | 20 | 425 | 54 | 43 | 609
1555 | 2017-04-05 | 2017-06-22 | 2017-07-18 | 2017-07-18 | COMP | 2017-12-27 | COMP | 2018-01-02 | COMP | 2019-09-10 | COMP | 2019-11-19 | COMP | Rule 16 | 56 | 18 | 112 | 4 | 426 | 50 | 661
6014 | 2017-04-05 | 2018-07-18 | 2018-10-29 | 2018-10-29 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-02-27 | COMP | 2019-09-04 | COMP | Rule 16 | 324 | 73 | 30 | 1 | 52 | 133 | 608
6243 | 2017-04-05 | 2018-08-06 | 2018-10-02 | 2018-10-02 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-11-12 | COMP | 2020-05-05 | COMP | Rule 16 | 337 | 41 | 205 | 1 | 76 | 120 | 775
1272 | 2017-04-06 | 2017-05-04 | 2017-07-30 | 2017-07-30 | COMP | 2021-12-02 | COMP | 2020-09-23 | COMP | 2022-05-23 | COMP | 2022-06-22 | COMP | Rule 15/16 | 21 | 60 | 1091 |  | 419 | 21 | 1311
1380 | 2017-04-06 | 2017-05-23 | 2017-06-09 | 2017-06-09 | COMP | 2017-08-08 | COMP | 2017-08-11 | COMP | 2018-04-11 | COMP | 2019-09-26 | COMP | Rule 15/16 | 34 | 13 | 42 | 4 | 166 | 369 | 623
1403 | 2017-04-06 | 2017-05-27 | 2017-11-10 | 2017-11-10 | COMP | 2018-03-08 | COMP | 2018-03-14 | COMP | 2019-08-31 | INPR | 2019-05-14 | COMP | Rule 16 | 37 | 116 | 78 | 5 |  |  | 529
1533 | 2017-04-06 | 2017-06-19 | 2017-08-07 | 2017-08-07 | COMP | 2018-01-23 | COMP | 2018-01-29 | COMP | 2019-07-21 | INPR | 2019-02-21 | COMP | Rule 16 | 52 | 35 | 115 | 5 |  |  | 471
1631 | 2017-04-06 | 2017-07-06 | 2017-09-25 | 2019-09-28 | COMP | 2019-11-01 | COMP | 2020-01-13 | COMP | 2020-04-22 | COMP | 2020-08-21 | COMP | Rule 16 | 64 | 57 | 25 | 47 | 71 | 87 | 851
1888 | 2017-04-06 | 2017-08-16 | 2018-03-18 | 2018-03-18 | COMP | 2018-09-04 | COMP | 2018-09-14 | COMP | 2019-09-09 | COMP | 2019-11-16 | COMP | Rule 15/16 | 93 | 145 | 119 | 9 | 247 | 49 | 658
1889 | 2017-04-06 | 2017-08-16 | 2018-08-07 | 2018-08-07 | COMP | 2018-09-04 | COMP | 2018-11-06 | COMP | 2019-10-17 | COMP | 2020-07-23 | COMP | Rule 15/16 | 93 | 245 | 20 | 46 | 238 | 193 | 830
2054 | 2017-04-06 | 2017-09-14 | 2018-12-24 | 2019-07-16 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2020-01-31 | COMP | 2020-03-04 | COMP | Rule 16 | 113 | 320 | 66 | 1 | 72 | 23 | 730
2902 | 2017-04-06 | 2018-02-13 | 2018-07-11 | 2018-07-11 | COMP | 2018-07-24 | COMP | 2018-12-10 | COMP | 2019-02-21 | COMP | 2019-03-07 | COMP | Rule 16 | 215 | 104 | 10 | 96 | 50 | 11 | 481
4437 | 2017-04-06 | 2017-12-08 | 2018-04-22 | 2018-04-22 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-02-12 | COMP | 2019-03-13 | COMP | Rule 15/16 | 171 | 92 | 80 | 1 | 124 | 21 | 485
4937 | 2017-04-06 | 2018-04-13 | 2018-06-11 | 2018-06-11 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-03-05 | COMP | 2019-01-24 | COMP | Rule 16 | 257 | 41 | 121 | 1 | 63 |  | 452
39141 | 2017-04-06 | 2022-10-03 | 2023-03-21 | 2023-03-21 | COMP | 2023-04-04 | NOTN | 2023-08-10 | COMP | 2023-08-10 | COMP | 2023-12-02 | COMP | Other | 1382 | 115 |  | 100 | 1 | 78 | 1672
1285 | 2017-04-07 | 2017-05-05 | 2017-11-30 | 2017-11-30 | COMP | 2018-05-23 | COMP | 2018-07-16 | COMP | 2018-07-30 | COMP | 2019-01-09 | COMP | Rule 15/16 | 21 | 144 | 121 | 37 | 11 | 112 | 441
1326 | 2017-04-07 | 2017-05-10 | 2017-07-27 | 2019-01-11 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-03-18 | COMP | 2019-05-02 | COMP | Rule 16 | 24 | 55 | 22 | 1 | 24 | 34 | 520
1392 | 2017-04-07 | 2017-05-25 | 2017-12-20 | 2017-12-20 | COMP | 2018-04-30 | COMP | 2018-07-17 | COMP | 2018-12-03 | COMP | 2019-01-27 | COMP | Rule 15/16 | 35 | 144 | 90 | 55 | 96 | 37 | 452
1474 | 2017-04-07 | 2017-06-08 | 2018-03-21 | 2018-03-21 | COMP | 2018-06-26 | COMP | 2018-07-16 | COMP | 2018-09-04 | COMP | 2019-12-10 | COMP | Rule 15/16 | 44 | 196 | 69 | 14 | 36 | 318 | 672
1498 | 2017-04-07 | 2017-06-10 | 2017-10-23 | 2017-10-23 | COMP | 2017-11-13 | COMP | 2017-11-14 | COMP | 2019-01-23 | COMP | 2019-02-27 | COMP | Rule 16 | 45 | 94 | 15 | 2 | 297 | 25 | 474
1846 | 2017-04-07 | 2017-08-08 | 2017-12-01 | 2017-12-01 | COMP | 2018-03-07 | COMP | 2018-03-07 | COMP | 2020-11-04 | COMP | 2020-11-13 | COMP | Rule 16 | 86 | 80 | 65 | 1 | 674 | 7 | 908
2354 | 2017-04-07 | 2017-11-09 | 2018-02-02 | 2018-02-22 | COMP | 2018-03-05 | COMP | 2018-03-14 | COMP | 2018-03-19 | COMP | 2019-03-19 | COMP | Rule 16 | 152 | 56 | 8 | 8 | 4 | 252 | 488
5382 | 2017-04-07 | 2018-05-25 | 2019-01-03 | 2020-09-17 | COMP | 2021-05-28 | COMP | 2021-06-23 | COMP | 2021-06-30 | COMP | 2021-07-22 | COMP | Rule 15/16 | 286 | 152 | 175 | 18 | 6 | 16 | 1079
6510 | 2017-04-07 | 2018-08-23 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-02 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-06-19 | COMP | Rule 15/16 | 348 | 297 | 23 | 68 | 1 | 73 | 805
39142 | 2017-04-07 | 2022-10-03 | 2023-02-28 | 2023-02-28 | COMP | 2023-02-28 | NOTN | 2023-10-18 | COMP | 2023-04-26 | NOTN | 2023-11-08 | COMP | Other | 1381 | 100 |  | 163 |  |  | 1657
1354 | 2017-04-08 | 2017-05-16 | 2017-10-19 | 2017-10-19 | COMP | 2017-11-02 | COMP | 2017-11-02 | COMP | 2019-06-12 | COMP | 2019-06-29 | COMP | Rule 16 | 27 | 110 | 11 | 1 | 402 | 13 | 559
1259 | 2017-04-10 | 2017-05-01 | 2018-02-14 | 2018-11-14 | COMP | 2019-03-28 | COMP | 2019-04-10 | COMP | 2019-08-31 | INPR | 2019-05-09 | COMP | Rule 15/16 | 16 | 199 | 91 | 10 |  |  | 524
1930 | 2017-04-10 | 2017-08-22 | 2017-10-12 | 2017-10-12 | COMP | 2019-01-10 | COMP | 2019-01-15 | COMP | 2019-01-30 | COMP | 2019-02-21 | COMP | Rule 16 | 95 | 37 | 311 | 4 | 11 | 16 | 469
2484 | 2017-04-10 | 2017-12-07 | 2018-04-26 | 2020-03-20 | COMP | 2020-08-04 | COMP | 2021-12-21 | COMP | 2021-12-10 | COMP | 2022-02-18 | COMP | Rule 15/16 | 168 | 97 | 97 | 347 | 0 | 43 | 1224
2741 | 2017-04-10 | 2018-01-25 | 2018-12-05 | 2018-12-05 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-09-05 | COMP | 2019-09-21 | COMP | Rule 16 | 200 | 218 | 186 | 1 | 5 | 12 | 617
3160 | 2017-04-10 | 2018-03-15 | 2018-05-28 | 2018-05-28 | COMP | 2018-10-02 | COMP | 2018-11-01 | COMP | 2020-01-08 | COMP | 2020-01-30 | COMP | Rule 16 | 234 | 52 | 89 | 23 | 295 | 16 | 705
3170 | 2017-04-10 | 2018-03-17 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-17 | COMP | 2019-03-19 | COMP | 2019-10-22 | COMP | 2019-11-12 | COMP | Rule 16 | 235 | 132 | 19 | 103 | 153 | 15 | 653
3886 | 2017-04-10 | 2018-09-15 | 2018-10-19 | 2018-10-19 | COMP | 2019-01-02 | COMP | 2019-01-09 | COMP | 2019-02-12 | COMP | 2019-03-03 | COMP | Rule 16 | 362 | 25 | 49 | 6 | 24 | 13 | 475
4637 | 2017-04-10 | 2018-02-21 | 2018-05-31 | 2018-05-31 | COMP | 2018-09-05 | COMP | 2018-12-04 | COMP | 2019-08-02 | COMP | 2019-08-10 | COMP | Rule 16 | 218 | 71 | 68 | 62 | 168 | 6 | 588
5835 | 2017-04-10 | 2018-07-06 | 2018-10-17 | 2018-10-17 | COMP | 2019-01-14 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-06-21 | COMP | Rule 16 | 313 | 73 | 59 | 82 | 1 | 31 | 554
6802 | 2017-04-10 | 2018-09-12 | 2018-10-02 | 2018-10-02 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2021-04-06 | COMP | 2021-04-07 | COMP | Rule 16 | 360 | 15 | 107 | 1 | 524 | 2 | 1004
1190 | 2017-04-11 | 2017-04-18 | 2018-12-22 | 2018-12-22 | COMP | 2019-05-09 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2020-03-27 | COMP | Rule 15/16 | 6 | 423 | 95 | 71 | 1 | 152 | 744
1309 | 2017-04-11 | 2017-05-09 | 2018-03-08 | 2018-03-08 | COMP | 2018-09-18 | COMP | 2018-11-16 | COMP | 2018-10-18 | COMP | 2019-10-10 | COMP | Rule 15/16 | 21 | 208 | 136 | 43 | 0 | 226 | 630
1518 | 2017-04-11 | 2017-06-15 | 2018-01-08 | 2019-02-05 | COMP | 2018-10-23 | COMP | 2018-11-09 | COMP | 2018-11-07 | COMP | 2019-03-07 | COMP | Rule 15/16 | 47 | 141 |  | 14 | 0 | 78 | 478
1527 | 2017-04-11 | 2017-06-16 | 2017-09-15 | 2017-09-15 | COMP | 2017-10-16 | COMP | 2017-11-14 | COMP | 2018-12-12 | COMP | 2019-01-24 | COMP | Rule 16 | 48 | 64 | 22 | 21 | 270 | 29 | 449
1954 | 2017-04-11 | 2017-08-26 | 2017-11-06 | 2017-11-06 | COMP | 2017-11-16 | COMP | 2017-11-21 | COMP | 2018-05-08 | COMP | 2019-01-07 | COMP | Rule 16 | 97 | 50 | 8 | 4 | 115 | 167 | 437
2711 | 2017-04-11 | 2018-01-23 | 2018-04-11 | 2018-04-07 | COMP | 2018-10-01 | COMP | 2019-07-10 | COMP | 2020-05-11 | COMP | 2020-06-13 | COMP | Rule 15/16 | 197 | 56 | 123 | 194 | 211 | 24 | 798
2732 | 2017-04-11 | 2018-01-25 | 2018-04-23 | 2018-04-15 | COMP | 2018-09-12 | COMP | 2020-08-03 | COMP | 2020-06-23 | COMP | 2020-09-30 | COMP | Rule 15/16 | 199 | 62 | 105 | 476 | 0 | 42 | 875
3220 | 2017-04-11 | 2018-03-23 | 2018-07-28 | 2018-07-28 | COMP | 2018-09-12 | COMP | 2018-09-24 | COMP | 2021-01-30 | INPR | 2019-05-08 | COMP | Rule 16 | 239 | 89 | 32 | 9 |  |  | 522
4537 | 2017-04-11 | 2018-01-24 | 2018-05-14 | 2018-05-14 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-01-16 | COMP | Rule 16 | 198 | 78 | 145 | 1 | 1 | 26 | 444
7013 | 2017-04-11 | 2018-09-22 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-08 | COMP | 2019-04-12 | COMP | 2019-03-06 | COMP | 2019-04-28 | COMP | Rule 15/16 | 366 | 80 | 15 | 45 | 0 | 11 | 514
8677 | 2017-04-11 | 2018-12-15 | 2019-04-09 | 2019-05-24 | COMP | 2019-08-08 | COMP | 2019-10-02 | COMP | 2020-01-16 | COMP | 2020-02-05 | COMP | Rule 16 | 423 | 78 | 53 | 39 | 72 | 14 | 708
1168 | 2017-04-12 | 2017-04-12 | 2017-08-25 | 2019-11-16 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-02-04 | COMP | 2020-06-15 | COMP | Other | 1 | 96 | 32 | 1 | 21 | 93 | 798
1677 | 2017-04-12 | 2017-07-14 | 2018-10-08 | 2018-10-08 | COMP | 2020-02-24 | COMP | 2020-06-08 | COMP | 2021-04-06 | COMP | 2021-04-12 | COMP | Rule 16 | 66 | 311 | 344 | 75 | 209 | 5 | 1005
1753 | 2017-04-12 | 2017-07-19 | 2018-04-20 | 2018-04-20 | COMP | 2018-07-20 | COMP | 2019-09-27 | COMP | 2019-08-16 | COMP | 2019-12-04 | COMP | Rule 15/16 | 69 | 190 | 64 | 300 | 0 | 46 | 665
1781 | 2017-04-12 | 2017-07-25 | 2017-07-31 | 2017-07-31 | COMP | 2017-08-11 | COMP | 2017-08-14 | COMP | 2017-09-12 | COMP | 2021-03-04 | COMP | Rule 16 | 73 | 5 | 10 | 2 | 21 | 872 | 978
2366 | 2017-04-12 | 2017-11-13 | 2018-06-01 | 2018-06-01 | COMP | 2022-01-14 | COMP | 2022-03-21 | COMP | 2022-03-04 | COMP | 2022-06-01 | COMP | Rule 15/16 | 150 | 138 | 912 | 45 | 0 | 52 | 1293
4467 | 2017-04-12 | 2017-12-20 | 2018-02-27 | 2018-02-27 | COMP | 2018-04-06 | COMP | 2018-04-09 | COMP | 2019-05-29 | COMP | 2019-06-17 | COMP | Rule 16 | 175 | 46 | 29 | 2 | 287 | 14 | 548
1282 | 2017-04-13 | 2017-05-04 | 2017-12-07 | 2017-12-07 | COMP | 2018-01-19 | COMP | 2019-03-26 | COMP | 2020-05-30 | INPR | 2019-04-14 | COMP | Rule 16 | 16 | 150 | 29 | 297 |  |  | 502
1446 | 2017-04-13 | 2017-06-06 | 2018-07-19 | 2018-07-19 | COMP | 2018-10-30 | COMP | 2019-03-11 | COMP | 2020-02-06 | COMP | 2019-09-17 | COMP | Rule 15/16 | 38 | 282 | 73 | 88 | 230 |  | 611
1447 | 2017-04-13 | 2017-06-06 | 2018-07-23 | 2018-07-23 | COMP | 2018-10-04 | COMP | 2019-07-26 | COMP | 2019-07-09 | NOTN | 2020-01-20 | COMP | Rule 16 | 38 | 284 | 53 | 203 |  |  | 694
1448 | 2017-04-13 | 2017-06-06 | 2018-07-17 | 2018-07-17 | COMP | 2018-10-04 | COMP | 2019-07-26 | COMP | 2019-12-27 | COMP | 2020-01-15 | COMP | Rule 16 | 38 | 280 | 57 | 203 | 106 | 13 | 692
1451 | 2017-04-13 | 2017-06-06 | 2018-06-19 | 2018-06-19 | COMP | 2018-10-04 | COMP | 2019-07-26 | COMP | 2019-12-18 | COMP | 2020-01-09 | COMP | Rule 16 | 38 | 261 | 76 | 203 | 100 | 15 | 688
1452 | 2017-04-13 | 2017-06-06 | 2018-12-28 | 2018-12-28 | COMP | 2019-08-15 | COMP | 2019-08-26 | COMP | 2023-11-11 | INPR | 2020-02-02 | COMP | Rule 16 | 38 | 393 | 160 | 8 |  |  | 703
1453 | 2017-04-13 | 2017-06-06 | 2018-12-24 | 2018-12-21 | COMP | 2019-08-27 | COMP | 2019-10-02 | COMP | 2020-11-24 | COMP | 2020-02-12 | COMP | Rule 15/16 | 38 | 390 | 172 | 26 | 290 |  | 711
1454 | 2017-04-13 | 2017-06-06 | 2018-12-17 | 2018-12-14 | COMP | 2019-08-27 | COMP | 2019-10-08 | INPR | 2020-05-30 | REQD | 2019-11-14 | COMP | Rule 16 | 38 | 385 | 177 |  |  |  | 652
1455 | 2017-04-13 | 2017-06-06 | 2018-12-17 | 2018-12-14 | COMP | 2019-08-22 | COMP | 2020-09-17 | COMP | 2020-09-08 | COMP | 2020-11-23 | COMP | Rule 15/16 | 38 | 385 | 174 | 271 | 0 | 47 | 910
1456 | 2017-04-13 | 2017-06-06 | 2018-12-17 | 2018-12-11 | COMP | 2019-08-27 | COMP | 2020-07-03 | COMP | 2020-06-01 | COMP | 2020-08-12 | COMP | Rule 16 | 38 | 385 | 180 | 215 | 0 | 29 | 839
1457 | 2017-04-13 | 2017-06-06 | 2018-12-17 | 2018-12-17 | COMP | 2019-08-27 | COMP | 2019-10-28 | COMP | 2020-11-24 | COMP | 2020-01-30 | COMP | Rule 16 | 38 | 385 | 176 | 44 | 272 |  | 702
1458 | 2017-04-13 | 2017-06-06 | 2018-11-14 | 2018-11-14 | COMP | 2019-08-27 | COMP | 2019-10-04 | COMP | 2020-11-19 | COMP | 2019-11-20 | COMP | Rule 16 | 38 | 364 | 197 | 28 | 285 |  | 656
1459 | 2017-04-13 | 2017-06-06 | 2018-10-16 | 2018-10-16 | COMP | 2019-08-27 | COMP | 2020-10-02 | COMP | 2020-06-01 | COMP | 2020-12-02 | COMP | Rule 16 | 38 | 344 | 217 | 279 | 0 | 41 | 915
1460 | 2017-04-13 | 2017-06-06 | 2018-12-12 | 2018-12-07 | COMP | 2019-08-27 | COMP | 2019-11-15 | COMP | 2020-12-11 | COMP | 2020-02-04 | COMP | Rule 16 | 38 | 382 | 182 | 57 | 270 |  | 705
1461 | 2017-04-13 | 2017-06-06 | 2019-01-23 | 2019-01-23 | COMP | 2019-09-03 | COMP | 2019-09-20 | COMP | 2020-12-10 | COMP | 2019-11-06 | COMP | Rule 16 | 38 | 409 | 156 | 14 | 308 |  | 647
1462 | 2017-04-13 | 2017-06-06 | 2019-05-15 | 2019-05-15 | COMP | 2019-09-18 | COMP | 2019-10-02 | COMP | 2020-12-02 | COMP | 2021-01-15 | COMP | Rule 16 | 38 | 488 | 88 | 11 | 294 | 31 | 945
1489 | 2017-04-13 | 2017-06-09 | 2018-10-18 | 2018-10-18 | COMP | 2019-08-20 | COMP | 2019-09-17 | COMP | 2020-02-29 | INPR | 2019-11-14 | COMP | Rule 16 | 41 | 343 | 210 | 20 |  |  | 652
1490 | 2017-04-13 | 2017-06-09 | 2019-01-08 | 2019-01-02 | COMP | 2019-09-03 | COMP | 2020-04-14 | COMP | 2020-06-01 | COMP | 2020-08-13 | COMP | Rule 16 | 41 | 396 | 170 | 154 | 34 | 54 | 840
1491 | 2017-04-13 | 2017-06-09 | 2018-10-17 | 2018-10-17 | COMP | 2019-04-09 | COMP | 2019-09-16 | COMP | 2020-05-30 | INPR | 2020-01-28 | COMP | Rule 15/16 | 41 | 342 | 118 | 112 |  |  | 700
1492 | 2017-04-13 | 2017-06-09 | 2018-09-25 | 2018-09-25 | COMP | 2019-08-20 | COMP | 2020-01-06 | COMP | 2020-04-23 | COMP | 2020-07-30 | COMP | Rule 16 | 41 | 326 | 227 | 94 | 77 | 70 | 830
1824 | 2017-04-13 | 2017-08-03 | 2018-04-16 | 2018-04-16 | COMP | 2018-11-08 | COMP | 2019-02-14 | COMP | 2018-12-31 | COMP | 2019-03-22 | COMP | Rule 16 | 79 | 175 | 146 | 65 | 0 | 26 | 487
2008 | 2017-04-13 | 2017-09-07 | 2018-01-26 | 2018-01-26 | COMP | 2019-04-15 | COMP | 2019-04-16 | COMP | 2019-10-21 | INPR | 2019-05-31 | COMP | Rule 15/16 | 103 | 96 | 306 | 2 |  |  | 536
2009 | 2017-04-13 | 2017-09-07 | 2018-01-17 | 2018-01-17 | COMP | 2018-06-18 | COMP | 2018-10-30 | COMP | 2019-04-20 | INPR | 2019-01-09 | COMP | Rule 15/16 | 103 | 89 | 107 | 95 |  |  | 437
3036 | 2017-04-13 | 2018-03-01 | 2018-11-09 | 2018-11-09 | COMP | 2019-06-24 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-04-22 | COMP | Rule 16 | 221 | 179 | 154 | 113 | 1 | 97 | 760
4414 | 2017-04-13 | 2017-11-28 | 2018-01-02 | 2018-01-02 | COMP | 2018-03-06 | COMP | 2018-03-12 | COMP | 2018-04-19 | COMP | 2019-04-16 | COMP | Rule 16 | 158 | 24 | 44 | 5 | 29 | 249 | 504
5073 | 2017-04-13 | 2018-04-27 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-31 | COMP | 2018-11-14 | COMP | 2019-06-17 | COMP | 2019-07-27 | COMP | Rule 16 | 262 | 102 | 30 | 10 | 147 | 29 | 575
5961 | 2017-04-13 | 2018-07-16 | 2019-11-07 | 2019-11-07 | COMP | 2020-05-06 | COMP | 2020-08-28 | COMP | 2021-03-04 | COMP | 2021-03-31 | COMP | Rule 16 | 316 | 333 | 123 | 82 | 127 | 20 | 996
6535 | 2017-04-13 | 2018-08-28 | 2018-10-16 | 2018-10-16 | COMP | 2018-10-31 | COMP | 2019-02-21 | COMP | 2019-07-21 | INPR | 2019-03-10 | COMP | Rule 16 | 347 | 35 | 12 | 75 |  |  | 477
1305 | 2017-04-14 | 2017-05-08 | 2017-06-17 | 2017-06-17 | COMP | 2017-11-27 | COMP | 2017-11-27 | COMP | 2018-11-17 | COMP | 2019-07-19 | COMP | Other | 17 | 29 | 111 | 1 | 247 | 167 | 569
1306 | 2017-04-14 | 2017-05-08 | 2017-06-17 | 2017-06-17 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2019-03-22 | COMP | 2019-03-29 | COMP | Other | 17 | 29 | 330 | 1 | 112 | 6 | 491
1361 | 2017-04-14 | 2017-05-17 | 2017-06-08 | 2017-06-08 | COMP | 2017-09-28 | COMP | 2017-09-28 | INPR | 2018-09-18 | COMP | 2020-02-26 | COMP | Other | 24 | 16 | 79 |  |  |  | 719
1626 | 2017-04-14 | 2017-07-05 | 2018-01-04 | 2018-01-04 | COMP | 2019-11-21 | COMP | 2020-02-05 | COMP | 2020-02-06 | COMP | 2020-03-11 | COMP | Rule 15/16 | 57 | 126 | 475 | 50 | 2 | 24 | 729
1839 | 2017-04-14 | 2017-08-07 | 2017-08-13 | 2017-08-13 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP |  | INPR | 2019-07-30 | COMP | Other | 80 | 5 | 291 | 1 |  |  | 576
1907 | 2017-04-14 | 2017-08-19 | 2018-04-01 | 2018-04-01 | COMP | 2018-07-20 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-06-11 | COMP | Rule 15/16 | 89 | 152 | 78 | 175 | 1 | 50 | 542
2278 | 2017-04-14 | 2017-10-26 | 2018-03-18 | 2018-02-14 | COMP | 2018-08-14 | COMP | 2018-09-24 | COMP | 2021-09-15 | COMP | 2021-10-14 | COMP | Rule 16 | 137 | 95 | 127 | 29 | 749 | 22 | 1133
3346 | 2017-04-14 | 2018-04-10 | 2018-04-23 | 2018-04-23 | COMP | 2018-07-17 | COMP | 2018-07-20 | COMP | 2019-09-10 | COMP | 2019-10-04 | COMP | Rule 16 | 248 | 10 | 60 | 4 | 287 | 19 | 623
1257 | 2017-04-16 | 2017-05-02 | 2018-01-13 | 2018-01-13 | COMP | 2018-04-03 | COMP | 2018-09-05 | COMP | 2018-12-13 | COMP | 2019-01-25 | COMP | Rule 15/16 | 12 | 176 | 55 | 109 | 69 | 29 | 446
1199 | 2017-04-17 | 2017-04-19 | 2018-05-29 | 2018-05-29 | COMP | 2018-06-12 | COMP | 2018-06-25 | COMP | 2019-04-16 | COMP | 2019-05-23 | COMP | Rule 16 | 3 | 279 | 11 | 10 | 203 | 28 | 529
1200 | 2017-04-17 | 2017-04-19 | 2018-05-29 | 2021-10-28 | COMP | 2021-11-18 | COMP | 2021-11-23 | COMP | 2021-11-18 | COMP | 2021-11-23 | COMP | Rule 16 | 3 | 279 | 15 | 4 | 0 | 1 | 1159
1202 | 2017-04-17 | 2017-04-19 | 2018-05-31 | 2019-09-16 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2021-02-17 | COMP | 2021-02-27 | COMP | Rule 16 | 3 | 281 | 118 | 1 | 240 | 8 | 971
1438 | 2017-04-17 | 2017-06-02 | 2017-08-16 | 2017-08-16 | COMP | 2017-10-23 | COMP | 2017-11-02 | COMP | 2019-03-18 | COMP | 2019-03-23 | COMP | Rule 16 | 34 | 53 | 48 | 9 | 341 | 5 | 485
1464 | 2017-04-17 | 2017-06-07 | 2017-08-13 | 2017-08-13 | COMP | 2018-01-22 | COMP | 2018-01-25 | COMP | 2019-03-05 | COMP | 2019-03-13 | COMP | Rule 16 | 37 | 47 | 109 | 4 | 278 | 7 | 478
1823 | 2017-04-17 | 2017-08-03 | 2017-09-07 | 2017-09-07 | COMP | 2019-03-01 | COMP | 2019-03-01 | COMP | 2019-03-25 | COMP | 2019-05-03 | COMP | Rule 15/16 | 77 | 25 | 370 | 1 | 17 | 30 | 515
1981 | 2017-04-17 | 2017-09-01 | 2018-04-27 | 2018-04-27 | COMP | 2018-10-17 | COMP | 2018-10-30 | COMP | 2019-07-08 | COMP | 2019-08-09 | COMP | Rule 16 | 98 | 163 | 121 | 10 | 171 | 25 | 583
2673 | 2017-04-17 | 2018-01-17 | 2018-12-07 | 2018-12-07 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2020-07-28 | COMP | 2020-08-25 | COMP | Rule 15/16 | 189 | 226 | 83 | 1 | 331 | 21 | 846
3018 | 2017-04-17 | 2018-02-27 | 2018-05-07 | 2018-05-07 | COMP | 2018-06-11 | COMP | 2018-06-22 | COMP | 2018-12-13 | COMP | 2019-01-08 | COMP | Rule 16 | 217 | 50 | 25 | 10 | 120 | 17 | 434
3076 | 2017-04-17 | 2018-03-06 | 2018-03-14 | 2018-03-14 | COMP | 2018-03-22 | COMP | 2018-04-23 | COMP | 2022-04-16 | INPR | 2021-04-02 | COMP | Rule 16 | 222 | 7 | 7 | 23 |  |  | 996
3276 | 2017-04-17 | 2018-03-31 | 2018-08-16 | 2018-08-16 | COMP | 2018-08-30 | COMP | 2018-10-30 | COMP | 2019-01-15 | COMP | 2019-03-07 | COMP | Rule 16 | 240 | 97 | 11 | 43 | 51 | 36 | 474
4812 | 2017-04-17 | 2018-03-31 | 2018-09-19 | 2018-09-19 | COMP | 2019-09-17 | COMP | 2020-11-13 | COMP | 2021-01-15 | COMP | 2021-02-23 | COMP | Rule 16 | 240 | 120 | 250 | 294 | 42 | 26 | 968
10240 | 2017-04-17 | 2019-03-06 | 2019-06-24 | 2019-10-25 | COMP | 2019-11-15 | COMP | 2019-11-25 | COMP | 2019-09-23 | COMP | 2019-12-16 | COMP | Rule 16 | 473 | 78 | 15 | 7 | 0 | 14 | 670
1225 | 2017-04-18 | 2017-04-25 | 2017-07-27 | 2017-07-27 | COMP | 2017-10-20 | COMP | 2017-11-10 | COMP | 2017-10-23 | COMP | 2019-01-10 | COMP | Rule 16 | 6 | 66 | 61 | 15 | 0 | 290 | 435
1500 | 2017-04-18 | 2017-06-10 | 2017-10-30 | 2017-10-30 | COMP | 2018-04-17 | COMP | 2018-03-28 | COMP | 2018-12-17 | COMP | 2019-01-14 | COMP | Rule 16 | 38 | 99 | 115 |  | 183 | 19 | 437
1603 | 2017-04-18 | 2017-06-30 | 2018-10-11 | 2019-04-22 | COMP | 2019-06-28 | COMP | 2020-04-26 | REQD | 2020-04-26 | REQD | 2019-12-13 | COMP | Rule 15/16 | 53 | 323 | 49 |  |  |  | 668
1623 | 2017-04-18 | 2017-07-05 | 2018-05-21 | 2018-05-21 | COMP | 2019-02-19 | COMP | 2020-02-10 | COMP | 2021-02-27 | INPR | 2020-02-24 | COMP | Rule 15/16 | 55 | 221 | 187 | 246 |  |  | 715
1789 | 2017-04-18 | 2017-07-27 | 2017-08-23 | 2017-08-23 | COMP | 2018-06-26 | COMP | 2018-06-26 | COMP | 2018-07-09 | COMP | 2019-03-27 | COMP | Rule 16 | 71 | 20 | 211 | 1 | 9 | 180 | 487
1927 | 2017-04-18 | 2017-08-21 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-26 | COMP | 2019-06-07 | COMP | 2019-07-27 | COMP | 2019-12-11 | COMP | Rule 16 | 88 | 304 | 14 | 135 | 35 | 94 | 666
2348 | 2017-04-18 | 2017-11-08 | 2018-08-08 | 2018-08-08 | COMP | 2019-03-21 | COMP | 2020-01-15 | COMP | 2019-09-27 | COMP | 2020-02-23 | COMP | Rule 15/16 | 144 | 187 | 154 | 207 | 0 | 26 | 714
2389 | 2017-04-18 | 2017-11-15 | 2018-11-14 | 2019-01-10 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-19 | COMP | 2020-01-16 | COMP | Rule 15/16 | 148 | 251 | 213 | 1 | 6 | 39 | 690
1243 | 2017-04-19 | 2017-04-27 | 2017-11-17 | 2017-11-17 | COMP | 2019-02-19 | COMP | 2019-02-22 | COMP | 2021-01-05 | COMP | 2021-01-26 | COMP | Rule 15/16 | 7 | 143 | 312 | 4 | 471 | 15 | 947
1329 | 2017-04-19 | 2017-05-10 | 2017-06-07 | 2017-06-07 | COMP | 2018-04-25 | COMP | 2018-05-21 | COMP | 2020-02-03 | COMP | 2020-02-14 | COMP | Rule 16 | 16 | 20 | 222 | 19 | 427 | 10 | 709
1348 | 2017-04-19 | 2017-05-16 | 2018-03-24 | 2018-03-24 | COMP | 2018-09-18 | COMP | 2019-04-11 | COMP | 2019-01-23 | COMP | 2019-05-03 | COMP | Rule 15/16 | 20 | 214 | 124 | 141 | 0 | 17 | 513
1440 | 2017-04-19 | 2017-06-02 | 2018-03-16 | 2018-03-16 | COMP | 2018-04-02 | COMP | 2018-05-29 | COMP | 2022-07-02 | INPR | 2020-11-16 | COMP | Rule 16 | 32 | 197 | 12 | 41 |  |  | 901
1531 | 2017-04-19 | 2017-06-19 | 2018-01-26 | 2018-01-26 | COMP | 2018-04-17 | COMP | 2018-08-22 | COMP | 2019-02-26 | COMP | 2019-03-29 | COMP | Rule 15/16 | 43 | 152 | 57 | 90 | 127 | 24 | 488
1541 | 2017-04-19 | 2017-06-20 | 2018-02-25 | 2018-02-25 | COMP | 2019-03-04 | COMP | 2020-02-28 | COMP | 2020-03-02 | COMP | 2020-06-16 | COMP | Rule 15/16 | 44 | 170 | 256 | 250 | 2 | 76 | 794
1920 | 2017-04-19 | 2017-08-21 | 2018-07-24 | 2018-07-24 | COMP | 2019-03-15 | COMP | 2019-04-05 | COMP | 2019-03-11 | COMP | 2019-08-13 | COMP | Rule 15/16 | 87 | 232 | 161 | 16 | 0 | 91 | 583
1928 | 2017-04-19 | 2017-08-22 | 2017-09-20 | 2017-09-20 | COMP | 2018-04-05 | COMP | 2018-05-16 | COMP | 2019-09-09 | COMP | 2019-09-19 | COMP | Rule 16 | 88 | 21 | 135 | 30 | 331 | 9 | 609
2365 | 2017-04-19 | 2017-11-13 | 2018-02-11 | 2018-11-17 | COMP | 2019-01-31 | COMP | 2019-08-16 | COMP | 2019-07-29 | COMP | 2019-09-20 | COMP | Rule 15/16 | 145 | 60 | 49 | 139 | 0 | 25 | 610
2646 | 2017-04-19 | 2018-01-12 | 2018-05-16 | 2018-05-16 | COMP | 2018-05-21 | COMP | 2018-06-21 | COMP | 2019-10-18 | COMP | 2019-12-16 | COMP | Rule 16 | 185 | 87 | 4 | 23 | 335 | 39 | 668
3268 | 2017-04-19 | 2018-03-29 | 2018-06-25 | 2018-06-25 | COMP | 2018-12-12 | COMP | 2018-12-20 | COMP | 2020-04-27 | COMP | 2020-06-28 | COMP | Rule 16 | 237 | 62 | 118 | 7 | 339 | 44 | 802
3833 | 2017-04-19 | 2018-08-06 | 2018-09-18 | 2018-09-18 | COMP | 2019-05-06 | COMP | 2019-07-22 | COMP | 2019-10-21 | COMP | 2019-11-19 | COMP | Rule 15/16 | 327 | 31 | 158 | 54 | 65 | 21 | 651
1384 | 2017-04-20 | 2017-05-24 | 2017-10-06 | 2017-10-06 | COMP | 2018-01-08 | COMP | 2018-06-08 | COMP | 2019-05-10 | COMP | 2019-08-21 | COMP | Rule 15/16 | 25 | 95 | 62 | 107 | 232 | 72 | 588
1404 | 2017-04-20 | 2017-05-27 | 2017-08-30 | 2018-07-09 | COMP | 2018-08-29 | COMP | 2019-03-13 | COMP | 2020-04-03 | COMP | 2020-04-21 | COMP | Rule 16 | 27 | 66 | 38 | 133 | 268 | 13 | 754
1429 | 2017-04-20 | 2017-06-01 | 2017-06-03 | 2017-06-03 | COMP | 2019-08-08 | COMP | 2019-08-08 | INPR | 2019-10-18 | COMP | 2019-11-25 | COMP | Rule 16 | 30 | 2 | 548 |  |  |  | 654
1612 | 2017-04-20 | 2017-07-03 | 2018-06-14 | 2018-06-14 | COMP | 2018-09-13 | COMP | 2018-11-02 | COMP | 2021-02-27 | INPR | 2019-11-22 | COMP | Rule 16 | 52 | 239 | 64 | 37 |  |  | 653
1668 | 2017-04-20 | 2017-07-14 | 2017-09-29 | 2017-09-29 | COMP | 2019-05-02 | COMP | 2018-05-10 | COMP | 2019-05-28 | COMP | 2021-04-24 | COMP | Rule 15/16 | 60 | 55 | 398 |  | 263 | 481 | 1008
1735 | 2017-04-20 | 2017-07-19 | 2017-09-20 | 2017-09-13 | COMP | 2018-05-21 | COMP | 2018-06-26 | COMP | 2018-06-14 | COMP | 2019-05-23 | COMP | Rule 15/16 | 63 | 45 | 172 | 26 | 0 | 229 | 526
2024 | 2017-04-20 | 2017-09-08 | 2018-02-23 | 2019-07-15 | COMP | 2019-07-18 | COMP | 2018-06-22 | COMP | 2019-07-31 | COMP | 2019-09-10 | COMP | Rule 15/16 | 99 | 114 | 4 |  | 278 | 29 | 601
2376 | 2017-04-20 | 2017-11-14 | 2018-06-18 | 2018-06-18 | COMP | 2020-05-29 | COMP | 2020-06-15 | COMP | 2021-02-09 | COMP | 2021-02-24 | COMP | Rule 16 | 145 | 148 | 490 | 12 | 165 | 11 | 966
39151 | 2017-04-20 | 2022-10-03 | 2023-01-05 | 2023-01-05 | COMP | 2023-05-29 | NOTN | 2023-05-30 | COMP | 2023-05-30 | COMP | 2023-09-05 | COMP | Other | 1372 | 64 |  | 101 | 1 | 68 | 1602
1388 | 2017-04-21 | 2017-05-24 | 2017-06-01 | 2017-06-01 | COMP | 2017-09-08 | COMP | 2017-09-08 | COMP | 2019-04-20 | INPR | 2019-01-03 | COMP | Rule 16 | 24 | 6 | 70 | 1 |  |  | 427
1686 | 2017-04-21 | 2017-07-17 | 2017-12-20 | 2017-12-20 | COMP | 2018-02-26 | COMP | 2018-03-12 | COMP | 2019-01-07 | COMP | 2019-04-24 | COMP | Rule 16 | 60 | 109 | 45 | 11 | 208 | 76 | 504
1754 | 2017-04-21 | 2017-07-19 | 2017-09-18 | 2017-09-18 | COMP | 2018-04-11 | COMP | 2018-10-15 | COMP | 2019-08-26 | COMP | 2020-01-24 | COMP | Rule 15/16 | 62 | 43 | 141 | 131 | 217 | 103 | 692
1925 | 2017-04-21 | 2017-08-22 | 2018-02-05 | 2018-02-05 | COMP | 2018-06-18 | COMP | 2019-04-29 | COMP | 2020-05-04 | COMP | 2022-10-10 | COMP | Rule 15/16 | 86 | 113 | 94 | 217 | 256 | 615 | 1376
3348 | 2017-04-21 | 2018-04-10 | 2019-02-06 | 2020-06-30 | COMP | 2020-08-04 | COMP | 2020-09-23 | COMP | 2020-08-04 | COMP | 2020-10-17 | COMP | Rule 16 | 243 | 208 | 26 | 36 | 0 | 18 | 879
7925 | 2017-04-21 | 2018-11-05 | 2019-04-02 | 2019-04-02 | COMP | 2019-07-10 | COMP | 2021-01-04 | COMP | 2021-01-04 | COMP | 2021-02-04 | COMP | Rule 16 | 389 | 100 | 70 | 374 | 1 | 23 | 952
38681 | 2017-04-21 | 2022-09-08 | 2022-09-13 | 2022-09-13 | COMP | 2022-09-27 | COMP | 2022-10-06 | COMP | 2022-10-13 | COMP | 2022-11-16 | COMP | Rule 15/16 | 1354 | 4 | 11 | 8 | 6 | 24 | 1402
5300 | 2017-04-22 | 2018-05-19 | 2018-12-14 | 2020-03-18 | COMP | 2020-04-06 | COMP | 2020-10-06 | COMP | 2020-06-26 | COMP | 2020-12-11 | COMP | Rule 15/16 | 270 | 144 | 14 | 130 | 0 | 46 | 915
1271 | 2017-04-24 | 2017-05-03 | 2017-10-17 | 2017-10-17 | COMP | 2018-12-21 | COMP | 2019-01-07 | COMP | 2020-11-10 | COMP | 2020-12-18 | COMP | Rule 16 | 8 | 117 | 296 | 10 | 468 | 26 | 920
1360 | 2017-04-24 | 2017-05-17 | 2020-04-08 | 2020-04-08 | COMP | 2020-04-27 | COMP | 2020-07-07 | COMP | 2020-06-11 | COMP | 2020-09-01 | COMP | Rule 16 | 18 | 726 | 14 | 51 | 0 | 41 | 846
1494 | 2017-04-24 | 2017-06-09 | 2017-06-30 | 2017-06-30 | COMP | 2017-08-17 | COMP | 2017-08-18 | COMP | 2022-05-22 | INPR | 2021-04-15 | COMP | Rule 16 | 34 | 16 | 34 | 2 |  |  | 1000
1648 | 2017-04-24 | 2017-07-10 | 2018-03-18 | 2018-03-18 | COMP | 2020-09-26 | REQD | 2019-07-30 | COMP | 2020-09-26 | INPR | 2019-08-23 | COMP | Rule 16 | 54 | 172 |  | 345 |  |  | 588
3191 | 2017-04-24 | 2018-03-20 | 2018-06-27 | 2018-06-27 | COMP | 2018-08-08 | COMP | 2018-09-04 | COMP | 2018-09-28 | COMP | 2019-01-09 | COMP | Rule 15/16 | 227 | 71 | 30 | 19 | 19 | 69 | 430
4629 | 2017-04-24 | 2018-02-20 | 2018-06-11 | 2018-11-30 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2018-12-26 | COMP | 2019-02-07 | COMP | Rule 16 | 207 | 79 | 6 | 1 | 13 | 30 | 450
1310 | 2017-04-25 | 2017-05-08 | 2017-06-19 | 2017-06-19 | COMP | 2020-04-20 | COMP | 2022-02-07 | COMP | 2022-02-03 | COMP | 2022-04-04 | COMP | Rule 16 | 10 | 30 | 712 | 455 | 0 | 40 | 1243
1331 | 2017-04-25 | 2017-05-11 | 2017-06-23 | 2017-06-23 | COMP | 2018-01-09 | COMP | 2018-02-05 | COMP | 2019-02-21 | COMP | 2019-03-20 | COMP | Rule 16 | 13 | 31 | 136 | 19 | 263 | 20 | 477
1520 | 2017-04-25 | 2017-06-15 | 2017-11-06 | 2019-11-05 | COMP | 2020-01-08 | COMP | 2020-05-15 | COMP | 2020-06-25 | COMP | 2020-07-22 | COMP | Rule 16 | 37 | 101 | 42 | 91 | 29 | 20 | 816
1546 | 2017-04-25 | 2017-06-21 | 2017-12-27 | 2018-05-16 | COMP | 2018-06-08 | COMP | 2018-06-09 | COMP | 2020-01-23 | COMP | 2020-02-28 | COMP | Rule 16 | 41 | 130 | 17 | 1 | 406 | 26 | 714
2353 | 2017-04-25 | 2017-11-09 | 2017-11-26 | 2017-11-22 | COMP | 2018-03-22 | COMP | 2018-03-22 | COMP | 2019-04-17 | COMP | 2019-05-15 | COMP | Rule 16 | 140 | 9 | 81 | 1 | 270 | 21 | 517
3656 | 2017-04-25 | 2018-06-04 | 2019-03-15 | 2019-06-07 | COMP | 2019-07-25 | COMP | 2019-09-03 | COMP | 2019-09-05 | COMP | 2019-12-06 | COMP | Rule 16 | 279 | 196 | 34 | 28 | 3 | 64 | 658
7144 | 2017-04-25 | 2018-09-28 | 2018-11-10 | 2018-11-10 | COMP | 2019-04-11 | COMP | 2019-06-25 | COMP | 2019-07-15 | COMP | 2019-09-19 | COMP | Rule 15/16 | 361 | 31 | 102 | 53 | 14 | 48 | 605
1441 | 2017-04-26 | 2017-06-02 | 2017-07-26 | 2017-07-26 | COMP | 2019-08-23 | COMP | 2017-09-14 | COMP | 2019-08-06 | COMP | 2019-12-06 | COMP | Rule 16 | 27 | 38 | 523 |  | 475 | 85 | 657
1599 | 2017-04-26 | 2017-06-29 | 2018-04-01 | 2018-03-27 | COMP | 2021-05-27 | COMP | 2021-06-03 | COMP | 2021-08-31 | COMP | 2021-11-12 | COMP | Rule 16 | 46 | 188 | 799 | 5 | 63 | 52 | 1145
1607 | 2017-04-26 | 2017-06-30 | 2018-01-24 | 2018-01-24 | COMP | 2018-09-26 | COMP | 2018-06-20 | COMP | 2018-12-18 | COMP | 2019-04-09 | COMP | Rule 16 | 47 | 141 | 172 |  | 125 | 77 | 490
1669 | 2017-04-26 | 2017-07-13 | 2017-09-22 | 2017-09-22 | COMP | 2017-09-26 | COMP | 2017-10-20 | COMP | 2017-10-23 | COMP | 2021-03-21 | COMP | Rule 16 | 55 | 51 | 3 | 19 | 2 | 854 | 979
2193 | 2017-04-26 | 2017-10-06 | 2017-12-01 | 2017-12-01 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-01-10 | COMP | 2019-03-04 | COMP | Rule 15/16 | 115 | 38 | 244 | 1 | 35 | 36 | 464
2735 | 2017-04-26 | 2018-01-25 | 2018-05-15 | 2018-05-15 | COMP | 2018-09-07 | COMP | 2018-09-21 | COMP | 2018-09-19 | COMP | 2019-01-08 | COMP | Rule 15 | 188 | 78 | 81 | 11 | 0 | 73 | 427
2904 | 2017-04-26 | 2018-02-13 | 2018-04-06 | 2018-04-06 | COMP | 2018-06-19 | COMP | 2018-06-19 | COMP | 2018-10-22 | COMP | 2019-03-04 | COMP | Rule 16 | 201 | 38 | 52 | 1 | 88 | 89 | 464
6669 | 2017-04-26 | 2018-09-05 | 2018-12-06 | 2020-05-27 | COMP | 2020-06-04 | COMP | 2020-04-29 | COMP | 2020-05-19 | COMP | 2020-07-22 | COMP | Rule 15/16 | 343 | 64 | 7 |  | 15 | 46 | 815
1307 | 2017-04-27 | 2017-05-09 | 2017-10-15 | 2017-10-15 | COMP | 2018-11-06 | COMP | 2018-12-08 | COMP | 2018-11-09 | COMP | 2019-05-24 | COMP | Rule 15/16 | 9 | 111 | 267 | 21 | 0 | 116 | 522
1308 | 2017-04-27 | 2017-05-09 | 2017-10-15 | 2017-10-15 | COMP | 2018-12-06 | COMP | 2019-05-23 | COMP | 2018-12-07 | COMP | 2019-06-29 | COMP | Rule 16 | 9 | 111 | 286 | 117 | 0 | 26 | 546
1390 | 2017-04-27 | 2017-05-25 | 2018-01-11 | 2018-01-11 | COMP | 2018-02-14 | COMP | 2019-11-08 | INPR | 2019-11-08 | COMP | 2019-10-15 | COMP | Rule 16 | 21 | 158 | 24 |  |  |  | 621
1399 | 2017-04-27 | 2017-05-25 | 2018-12-20 | 2018-12-20 | COMP | 2019-11-15 | COMP | 2020-07-13 | COMP | 2019-12-09 | COMP | 2020-10-09 | COMP | Rule 16 | 21 | 395 | 229 | 165 | 0 | 64 | 870
1574 | 2017-04-27 | 2017-06-27 | 2017-09-12 | 2020-04-24 | COMP | 2020-05-18 | COMP | 2020-06-15 | COMP | 2020-06-23 | COMP | 2020-07-03 | COMP | Rule 15/16 | 43 | 54 | 17 | 20 | 7 | 9 | 801
2107 | 2017-04-27 | 2017-09-26 | 2018-02-17 | 2018-02-17 | COMP | 2018-06-07 | COMP | 2018-06-26 | COMP | 2019-06-29 | INPR | 2019-03-04 | COMP | Rule 16 | 106 | 98 | 77 | 14 |  |  | 463
4836 | 2017-04-27 | 2018-04-12 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2019-01-25 | COMP | 2019-02-09 | COMP | Rule 16 | 241 | 134 | 22 | 1 | 44 | 11 | 448
6475 | 2017-04-27 | 2018-08-20 | 2019-06-06 | 2019-10-04 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-01-09 | COMP | 2020-08-15 | COMP | Rule 16 | 331 | 200 | 52 | 1 | 14 | 154 | 831
1394 | 2017-04-28 | 2017-05-25 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-11 | COMP | 2020-06-16 | COMP | 2020-08-21 | COMP | 2020-09-14 | COMP | Rule 16 | 20 | 690 | 11 | 69 | 49 | 16 | 850
1405 | 2017-04-28 | 2017-05-30 | 2018-03-03 | 2018-03-03 | COMP | 2018-05-23 | COMP | 2018-06-26 | COMP |  | INPR | 2019-03-20 | COMP | Rule 15/16 | 22 | 190 | 58 | 24 |  |  | 474
1672 | 2017-04-28 | 2017-07-13 | 2017-08-15 | 2018-05-20 | COMP | 2018-09-05 | COMP | 2018-09-05 | COMP | 2018-11-02 | COMP | 2019-01-02 | COMP | Rule 15/16 | 53 | 24 | 75 | 1 | 43 | 39 | 421
1988 | 2017-04-28 | 2017-09-01 | 2018-01-11 | 2018-03-12 | COMP | 2018-03-29 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-02-08 | COMP | Rule 15/16 | 89 | 89 | 14 | 193 | 1 | 26 | 447
1994 | 2017-04-28 | 2017-09-05 | 2018-03-21 | 2018-03-21 | COMP | 2018-08-06 | COMP | 2019-02-05 | COMP | 2019-01-23 | COMP | 2019-03-14 | COMP | Rule 16 | 90 | 135 | 97 | 125 | 0 | 27 | 470
2763 | 2017-04-28 | 2018-01-29 | 2018-05-29 | 2018-05-29 | COMP | 2018-08-13 | COMP | 2019-10-23 | COMP | 2019-09-12 | COMP | 2019-12-09 | COMP | Rule 16 | 188 | 85 | 54 | 302 | 0 | 31 | 656
4631 | 2017-04-28 | 2018-02-20 | 2018-06-27 | 2018-10-10 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-06-05 | COMP | 2019-07-19 | COMP | Rule 15/16 | 203 | 91 | 65 | 1 | 99 | 32 | 559
1397 | 2017-04-29 | 2017-05-25 | 2019-07-29 | 2019-07-29 | COMP | 2019-08-23 | COMP | 2019-10-05 | COMP | 2023-05-27 | INPR | 2019-10-24 | COMP | Rule 16 | 19 | 546 | 20 | 30 |  |  | 626
1398 | 2017-04-30 | 2017-05-25 | 2019-07-25 | 2019-07-25 | COMP | 2019-09-16 | COMP | 2019-10-05 | COMP | 2019-11-01 | COMP | 2019-10-25 | COMP | Rule 16 | 19 | 544 | 37 | 15 | 20 |  | 627
2464 | 2017-04-30 | 2017-12-05 | 2018-06-14 | 2018-06-14 | COMP | 2019-04-01 | COMP | 2019-04-09 | COMP | 2020-02-14 | COMP | 2020-03-26 | COMP | Rule 16 | 151 | 133 | 199 | 7 | 215 | 29 | 729
1312 | 2017-05-01 | 2017-05-09 | 2018-11-26 | 2018-11-26 | COMP | 2019-01-08 | COMP | 2019-02-19 | COMP | 2020-09-26 | INPR | 2019-07-24 | COMP | Rule 16 | 7 | 389 | 30 | 29 |  |  | 561
1605 | 2017-05-01 | 2017-07-01 | 2018-04-27 | 2018-04-27 | COMP | 2018-11-16 | COMP | 2019-09-17 | COMP | 2019-09-18 | COMP | 2019-11-12 | COMP | Rule 15/16 | 44 | 206 | 142 | 209 | 2 | 39 | 638
1606 | 2017-05-01 | 2017-07-01 | 2018-08-27 | 2018-08-27 | COMP | 2020-12-02 | COMP | 2021-04-16 | COMP |  | INPR | 2022-03-23 | COMP | Rule 15/16 | 44 | 290 | 570 | 94 |  |  | 1231
1653 | 2017-05-01 | 2017-07-10 | 2017-08-03 | 2017-08-03 | COMP | 2017-08-10 | COMP | 2017-10-31 | COMP | 2019-04-20 | INPR | 2019-01-19 | COMP | Rule 16 | 49 | 19 | 6 | 58 |  |  | 432
1711 | 2017-05-01 | 2017-07-18 | 2017-10-10 | 2017-10-10 | COMP | 2017-10-23 | COMP | 2017-12-20 | COMP | 2020-12-17 | COMP | 2021-04-02 | COMP | Rule 16 | 55 | 60 | 10 | 40 | 753 | 73 | 986
2075 | 2017-05-01 | 2017-09-19 | 2017-11-29 | 2017-11-29 | COMP | 2017-12-12 | COMP | 2018-01-31 | COMP |  |  | 2019-08-20 | COMP | Rule 16 | 99 | 49 | 10 | 34 |  |  | 580
2577 | 2017-05-01 | 2017-12-29 | 2018-02-09 | 2018-02-09 | COMP | 2018-03-13 | COMP | 2018-06-14 | COMP | 2019-09-21 | INPR | 2019-06-14 | COMP | Rule 16 | 168 | 29 | 22 | 67 |  |  | 534
3372 | 2017-05-01 | 2018-04-14 | 2018-10-09 | 2018-10-09 | COMP | 2018-12-19 | COMP | 2019-08-01 | COMP | 2019-07-02 | COMP | 2019-08-23 | COMP | Rule 16 | 240 | 124 | 49 | 156 | 0 | 17 | 583
4006 | 2017-05-01 | 2018-11-19 | 2019-03-27 | 2019-03-27 | COMP | 2019-05-30 | COMP | 2019-06-12 | COMP |  |  | 2019-08-27 | COMP | Rule 16 | 392 | 87 | 46 | 10 |  |  | 585
13970 | 2017-05-01 | 2019-08-19 | 2019-12-18 | 2019-12-18 | COMP | 2020-01-07 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-05-13 | COMP | Rule 16 | 579 | 84 | 13 | 75 | 1 | 16 | 763
1332 | 2017-05-02 | 2017-05-11 | 2018-10-09 | 2019-03-26 | COMP | 2019-03-15 | COMP | 2019-06-18 | COMP | 2019-06-11 | COMP | 2019-08-01 | COMP | Rule 15/16 | 8 | 356 |  | 67 | 0 | 32 | 566
1386 | 2017-05-02 | 2017-05-25 | 2018-01-04 | 2018-01-04 | COMP | 2018-03-13 | COMP | 2018-03-13 | COMP | 2019-02-20 | COMP | 2019-04-12 | COMP | Rule 15/16 | 18 | 153 | 47 | 1 | 237 | 38 | 489
1401 | 2017-05-02 | 2017-05-26 | 2018-01-16 | 2018-01-16 | COMP | 2018-11-15 | COMP | 2018-11-28 | COMP | 2019-04-16 | COMP | 2019-04-25 | COMP | Rule 16 | 19 | 159 | 213 | 8 | 96 | 8 | 498
1812 | 2017-05-02 | 2017-08-02 | 2018-01-26 | 2018-09-26 | COMP | 2018-09-27 | COMP | 2018-10-01 | COMP | 2018-10-11 | COMP | 2019-03-05 | COMP | Rule 15/16 | 65 | 121 | 2 | 3 | 9 | 97 | 461
1867 | 2017-05-02 | 2017-08-11 | 2018-03-20 | 2018-03-20 | COMP | 2019-09-16 | COMP | 2019-11-04 | COMP | 2020-10-15 | COMP | 2021-02-04 | COMP | Rule 15/16 | 72 | 150 | 377 | 36 | 240 | 75 | 945
1963 | 2017-05-02 | 2017-08-28 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-29 | COMP | 2019-09-06 | COMP | 2019-08-26 | COMP | 2019-10-21 | COMP | Rule 16 | 83 | 462 | 20 | 29 | 0 | 32 | 622
2488 | 2017-05-02 | 2017-12-07 | 2019-02-05 | 2019-02-05 | COMP | 2019-02-11 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-05-08 | COMP | Rule 16 | 152 | 291 | 5 | 36 | 1 | 27 | 507
4444 | 2017-05-02 | 2017-12-13 | 2018-03-04 | 2018-03-04 | COMP | 2018-05-14 | COMP | 2019-12-17 | COMP | 2020-02-14 | COMP | 2020-04-29 | COMP | Rule 16 | 156 | 54 | 51 | 401 | 41 | 53 | 752
1322 | 2017-05-03 | 2017-05-10 | 2017-10-22 | 2020-01-23 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-02-20 | COMP | 2020-04-10 | COMP | Rule 15/16 | 6 | 115 | 28 | 1 | 0 | 29 | 738
1683 | 2017-05-03 | 2017-07-15 | 2017-08-16 | 2017-08-16 | COMP | 2018-04-11 | COMP | 2018-11-30 | INPR | 2022-01-29 | REQD | 2020-06-29 | COMP | Rule 16 | 51 | 23 | 163 |  |  |  | 793
2166 | 2017-05-03 | 2017-10-03 | 2018-07-18 | 2018-07-13 | COMP | 2018-08-23 | COMP | 2018-10-16 | COMP | 2018-10-15 | COMP | 2020-02-20 | COMP | Rule 15/16 | 107 | 198 | 30 | 38 | 0 | 336 | 702
2211 | 2017-05-03 | 2017-10-12 | 2018-02-01 | 2018-02-01 | COMP | 2018-04-27 | COMP | 2018-05-03 | COMP |  | INPR | 2021-07-23 | COMP | Rule 16 | 114 | 75 | 61 | 5 |  |  | 1062
3001 | 2017-05-03 | 2018-02-26 | 2018-05-20 | 2018-05-20 | COMP | 2018-02-26 | NOTN | 2018-08-30 | COMP | 2018-07-03 | COMP | 2019-04-06 | COMP | Other | 204 | 60 |  | 72 | 0 | 149 | 483
3283 | 2017-05-03 | 2018-04-02 | 2018-06-25 | 2018-06-25 | COMP | 2018-08-01 | COMP | 2018-08-01 | COMP | 2019-04-29 | COMP | 2019-08-08 | COMP | Rule 16 | 229 | 60 | 27 | 1 | 186 | 72 | 570
6473 | 2017-05-03 | 2018-08-20 | 2018-12-04 | 2018-12-04 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2021-03-10 | COMP | 2021-05-20 | COMP | Rule 16 | 327 | 73 | 62 | 1 | 508 | 52 | 1018
9423 | 2017-05-03 | 2019-02-04 | 2019-05-01 | 2019-06-12 | COMP | 2019-06-20 | COMP | 2019-07-03 | COMP | 2019-07-22 | NOTN | 2019-09-18 | COMP | Rule 16 | 440 | 62 | 7 | 10 |  |  | 598
1435 | 2017-05-04 | 2017-06-01 | 2020-04-08 | 2020-04-08 | COMP | 2020-10-16 | COMP | 2021-01-22 | COMP | 2021-01-29 | COMP | 2021-04-21 | COMP | Rule 16 | 20 | 716 | 136 | 65 | 6 | 58 | 996
1544 | 2017-05-04 | 2017-06-21 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-11 | COMP | 2018-12-20 | COMP | 2019-01-19 | COMP | 2019-01-30 | COMP | Rule 16 | 34 | 361 | 10 | 8 | 20 | 7 | 436
1597 | 2017-05-04 | 2017-06-29 | 2017-10-15 | 2017-10-15 | COMP | 2018-06-13 | COMP | 2018-09-12 | COMP | 2020-09-29 | COMP | 2020-10-01 | COMP | Rule 15/16 | 40 | 75 | 165 | 64 | 516 | 3 | 859
1647 | 2017-05-04 | 2017-07-10 | 2017-12-05 | 2017-12-05 | COMP | 2017-12-27 | COMP | 2018-02-28 | COMP | 2022-01-29 | INPR | 2020-11-18 | COMP | Rule 15/16 | 46 | 103 | 16 | 43 |  |  | 892
1659 | 2017-05-04 | 2017-07-12 | 2017-09-01 | 2017-09-01 | COMP | 2018-04-25 | COMP | 2018-05-21 | COMP | 2019-11-02 | COMP | 2019-11-14 | COMP | Rule 16 | 48 | 38 | 161 | 19 | 367 | 8 | 637
1771 | 2017-05-04 | 2017-07-24 | 2017-09-01 | 2017-09-01 | COMP | 2018-05-08 | COMP | 2018-05-23 | COMP |  |  | 2019-04-18 | COMP | Rule 16 | 56 | 30 | 170 | 12 |  |  | 491
2358 | 2017-05-04 | 2017-11-10 | 2018-05-16 | 2018-05-16 | COMP | 2019-07-17 | COMP | 2018-11-28 | COMP | 2019-06-10 | COMP | 2020-01-17 | COMP | Rule 15/16 | 133 | 127 | 294 |  | 134 | 153 | 679
2643 | 2017-05-04 | 2018-01-11 | 2018-06-13 | 2018-06-13 | COMP | 2018-08-03 | COMP | 2019-05-22 | COMP | 2019-11-04 | COMP | 2019-11-12 | COMP | Rule 16 | 173 | 107 | 37 | 201 | 116 | 6 | 635
2751 | 2017-05-04 | 2018-01-26 | 2018-06-15 | 2019-01-10 | COMP | 2019-03-07 | COMP | 2019-04-17 | COMP | 2019-03-28 | COMP | 2019-06-01 | COMP | Rule 15/16 | 183 | 99 | 39 | 30 | 0 | 32 | 521
4421 | 2017-05-04 | 2017-11-30 | 2018-02-16 | 2018-02-16 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2021-02-24 | COMP | 2021-04-13 | COMP | Rule 16 | 145 | 54 | 176 | 1 | 584 | 35 | 990
1445 | 2017-05-05 | 2017-06-05 | 2017-06-16 | 2017-06-16 | COMP | 2017-11-10 | COMP | 2017-11-10 | COMP | 2019-04-20 | INPR | 2019-01-11 | COMP | Rule 15/16 | 21 | 10 | 103 | 0 |  |  | 423
1519 | 2017-05-05 | 2017-06-14 | 2017-07-25 | 2017-07-25 | COMP | 2017-08-04 | COMP | 2017-08-24 | COMP |  | INPR | 2019-08-05 | COMP | Rule 16 | 28 | 29 | 9 | 15 |  |  | 565
1676 | 2017-05-05 | 2017-07-14 | 2017-09-07 | 2017-09-07 | COMP | 2017-10-03 | COMP | 2017-10-03 | COMP | 2018-12-04 | COMP | 2019-01-30 | COMP | Rule 15/16 | 49 | 39 | 19 | 1 | 293 | 39 | 435
2028 | 2017-05-05 | 2017-09-08 | 2018-02-06 | 2018-02-06 | COMP | 2019-01-23 | COMP | 2019-02-01 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | Rule 16 | 88 | 102 | 242 | 8 | 122 | 2 | 559
2030 | 2017-05-05 | 2017-09-08 | 2018-02-07 | 2018-02-07 | COMP | 2018-05-16 | COMP | 2020-01-16 | COMP |  |  | 2020-02-13 | COMP | Rule 15/16 | 88 | 103 | 70 | 419 |  |  | 696
5134 | 2017-05-05 | 2018-05-02 | 2018-07-25 | 2018-07-25 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2020-09-21 | COMP | 2020-09-14 | COMP | Rule 16 | 249 | 59 | 71 | 1 | 474 |  | 845
1594 | 2017-05-07 | 2017-06-29 | 2017-08-18 | 2018-05-01 | COMP | 2020-10-26 | COMP | 2020-12-01 | COMP | 2020-11-30 | COMP | 2021-06-26 | COMP | Rule 16 | 38 | 36 | 628 | 24 | 0 | 144 | 1040
1434 | 2017-05-08 | 2017-06-01 | 2018-10-15 | 2018-10-15 | COMP | 2018-11-08 | COMP | 2019-08-19 | COMP | 2020-01-09 | COMP | 2020-05-26 | COMP | Rule 16 | 18 | 346 | 19 | 194 | 98 | 96 | 766
1816 | 2017-05-08 | 2017-08-02 | 2018-01-08 | 2018-01-08 | COMP | 2018-05-21 | COMP | 2018-05-23 | COMP | 2019-11-19 | COMP | 2019-12-23 | COMP | Rule 16 | 61 | 108 | 94 | 3 | 376 | 23 | 660
1953 | 2017-05-08 | 2017-08-25 | 2017-10-11 | 2017-10-11 | COMP | 2017-11-17 | COMP | 2018-02-05 | COMP | 2019-07-21 | INPR | 2019-04-25 | COMP | Rule 16 | 78 | 33 | 27 | 52 |  |  | 494
2044 | 2017-05-08 | 2017-09-11 | 2017-11-01 | 2017-11-01 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2018-11-01 | COMP | 2019-02-12 | COMP | Rule 16 | 88 | 38 | 250 | 1 | 3 | 68 | 443
2854 | 2017-05-08 | 2018-02-07 | 2018-12-17 | 2018-12-14 | COMP | 2019-08-01 | COMP | 2020-08-28 | COMP | 2020-06-08 | COMP | 2020-10-10 | COMP | Rule 16 | 189 | 217 | 159 | 273 | 0 | 30 | 863
3310 | 2017-05-08 | 2018-04-05 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-12 | COMP | 2019-04-12 | COMP |  |  | 2019-09-25 | COMP | Rule 16 | 229 | 221 | 37 | 1 |  |  | 600
3319 | 2017-05-08 | 2018-04-06 | 2019-04-06 | 2019-04-06 | COMP | 2019-06-11 | COMP | 2019-06-19 | COMP | 2019-11-11 | COMP | 2021-05-05 | COMP | Rule 16 | 230 | 251 | 46 | 7 | 101 | 372 | 1004
3620 | 2017-05-08 | 2018-05-24 | 2018-09-06 | 2018-09-06 | COMP | 2018-10-02 | COMP | 2019-05-31 | COMP | 2019-09-21 | INPR | 2019-06-14 | COMP | Rule 15/16 | 264 | 73 | 19 | 166 |  |  | 529
4451 | 2017-05-08 | 2017-12-12 | 2018-02-28 | 2018-09-26 | COMP | 2018-11-01 | COMP | 2018-11-13 | COMP | 2018-07-02 | COMP | 2019-03-11 | COMP | Rule 15/16 | 151 | 53 | 27 | 8 | 0 | 79 | 461
1413 | 2017-05-09 | 2017-05-30 | 2017-06-08 | 2017-06-08 | COMP | 2018-10-31 | COMP | 2018-10-31 | COMP | 2023-11-04 | INPR | 2022-10-07 | COMP | Rule 16 | 15 | 8 | 353 | 1 |  |  | 1363
1432 | 2017-05-09 | 2017-06-01 | 2019-01-15 | 2019-01-15 | COMP | 2020-05-19 | COMP | 2020-08-14 | NOTN | 2021-02-25 | COMP | 2021-04-07 | COMP | Rule 16 | 17 | 407 | 339 |  |  |  | 983
1472 | 2017-05-09 | 2017-06-07 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-08 | COMP | 2019-10-18 | COMP | 2020-01-31 | COMP | 2020-03-25 | COMP | Rule 15/16 | 21 | 337 | 24 | 237 | 70 | 38 | 722
1496 | 2017-05-09 | 2017-06-09 | 2018-10-06 | 2018-10-06 | COMP | [5 empty] | INPR | 2019-10-22 | COMP | Other | 23 | 334 |  |  |  |  | 618
1505 | 2017-05-09 | 2017-06-12 | 2017-08-24 | 2017-08-24 | COMP | [5 empty] | REQD | 2019-10-21 | COMP | Other | 24 | 53 |  |  |  |  | 617
1506 | 2017-05-09 | 2017-06-12 | 2017-08-29 | 2017-08-29 | COMP | [5 empty] | REQD | 2019-10-21 | COMP | Other | 24 | 56 |  |  |  |  | 617
1551 | 2017-05-09 | 2017-06-22 | 2017-08-15 | 2017-08-15 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP |  | INPR | 2019-10-21 | COMP | Other | 32 | 38 | 277 | 1 |  |  | 617
1552 | 2017-05-09 | 2017-06-22 | 2017-07-23 | 2017-07-23 | COMP | 2018-02-14 | COMP | 2018-02-16 | COMP | 2018-04-13 | COMP | 2021-04-06 | COMP | Rule 16 | 32 | 21 | 141 | 3 | 40 | 749 | 982
1582 | 2017-05-09 | 2017-06-27 | 2017-08-26 | 2017-08-26 | COMP |  |  |  |  | 2019-04-11 | COMP | 2022-10-12 | COMP | Other | 35 | 43 |  |  |  |  | 1366
1583 | 2017-05-09 | 2017-06-27 | 2017-08-26 | 2017-08-26 | COMP | 2018-09-21 | COMP | 2018-09-21 | COMP |  | INPR | 2019-10-22 | COMP | Other | 35 | 43 | 269 | 1 |  |  | 618
1645 | 2017-05-09 | 2017-07-08 | 2018-02-15 | 2018-02-15 | COMP | 2018-02-26 | COMP | 2018-05-18 | COMP | 2019-04-04 | COMP | 2019-06-19 | COMP | Rule 15/16 | 42 | 152 | 7 | 60 | 220 | 54 | 531
1657 | 2017-05-09 | 2017-07-12 | 2017-08-19 | 2017-08-19 | COMP | 2018-09-21 | COMP | 2018-09-21 | COMP |  | INPR | 2019-10-21 | COMP | Other | 45 | 28 | 274 | 1 |  |  | 617
1665 | 2017-05-09 | 2017-07-13 | 2017-08-04 | 2017-08-04 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2020-03-21 | INPR | 2019-10-22 | COMP | Other | 46 | 17 | 284 | 1 |  |  | 618
1679 | 2017-05-09 | 2017-07-14 | 2018-07-16 | 2018-07-16 | COMP | 2020-08-26 | COMP | 2020-09-01 | COMP |  |  | 2020-10-13 | COMP | Rule 16 | 47 | 252 | 534 | 5 |  |  | 864
1945 | 2017-05-09 | 2017-08-24 | 2018-12-11 | 2018-12-11 | COMP | 2019-01-09 | COMP | 2019-01-10 | COMP | 2019-03-29 | COMP | 2019-05-02 | COMP | Rule 16 | 76 | 325 | 20 | 2 | 55 | 25 | 498
2095 | 2017-05-09 | 2017-09-22 | 2018-02-09 | 2018-02-09 | COMP | 2018-08-09 | COMP | 2018-08-09 | COMP | 2019-02-15 | COMP | 2019-02-22 | COMP | Rule 16 | 96 | 95 | 127 | 1 | 130 | 5 | 449
2146 | 2017-05-09 | 2017-09-29 | 2018-05-22 | 2018-05-22 | COMP | 2018-06-15 | COMP | 2018-09-04 | COMP | 2019-09-11 | COMP | 2019-09-17 | COMP | Rule 15/16 | 101 | 161 | 18 | 56 | 257 | 5 | 593
2419 | 2017-05-09 | 2017-11-28 | 2018-01-18 | 2018-01-18 | COMP | 2018-02-14 | COMP | 2018-02-28 | COMP | 2018-12-06 | COMP | 2019-02-05 | COMP | Rule 16 | 140 | 35 | 20 | 10 | 196 | 41 | 437
4847 | 2017-05-09 | 2018-04-04 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-01-03 | COMP | Rule 16 | 227 | 156 | 16 | 1 | 1 | 19 | 415
5543 | 2017-05-09 | 2018-06-11 | 2018-11-02 | 2019-01-18 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-04-24 | COMP | Rule 15/16 | 274 | 103 | 285 | 1 | 1 | 35 | 744
39152 | 2017-05-09 | 2022-10-03 | 2023-03-03 | 2023-03-03 | COMP | 2023-04-03 | NOTN | 2023-07-16 | COMP | 2023-04-06 | COMP | 2023-10-02 | COMP | Other | 1359 | 103 |  | 93 | 0 | 55 | 1608
1666 | 2017-05-10 | 2017-07-13 | 2017-08-02 | 2017-08-02 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP |  | INPR | 2019-04-19 | COMP | Other | 45 | 15 | 286 | 1 |  |  | 488
3751 | 2017-05-10 | 2018-06-27 | 2018-09-11 | 2018-09-11 | COMP | 2018-09-11 | NOTN | 2019-07-22 | COMP | 2020-01-23 | COMP | 2020-02-26 | COMP | Other | 285 | 53 |  | 216 | 127 | 24 | 701
3866 | 2017-05-10 | 2018-08-27 | 2018-12-12 | 2018-12-01 | COMP | 2019-03-14 | COMP | 2019-08-01 | INPR |  |  | 2019-08-30 | COMP | Rule 16 | 327 | 74 | 70 |  |  |  | 581
4376 | 2017-05-10 | 2017-11-02 | 2018-03-30 | 2018-03-30 | COMP | 2018-05-04 | COMP | 2019-01-17 | COMP | 2019-07-30 | COMP | 2019-08-26 | COMP | Rule 15/16 | 124 | 100 | 26 | 177 | 135 | 20 | 577
1378 | 2017-05-11 | 2017-05-23 | 2017-07-05 | 2017-07-05 | COMP | 2017-08-30 | COMP | 2023-05-27 | CANC | 2017-07-27 | COMP | 2022-05-10 | COMP | Rule 16 | 9 | 30 | 41 |  |  |  | 1257
1396 | 2017-05-11 | 2017-05-25 | 2018-11-09 | 2018-11-05 | COMP | 2020-01-21 | COMP | 2020-01-23 | COMP | 2019-12-30 | COMP | 2020-03-09 | COMP | Rule 16 | 11 | 369 | 301 | 3 | 0 | 32 | 708
1602 | 2017-05-11 | 2017-06-29 | 2017-09-05 | 2017-09-05 | COMP | 2017-09-25 | COMP | 2018-07-10 | COMP | 2019-01-23 | COMP | 2019-03-05 | COMP | Rule 16 | 35 | 47 | 15 | 198 | 135 | 29 | 454
1604 | 2017-05-11 | 2017-06-30 | 2018-01-05 | 2018-11-08 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-03-05 | COMP | 2019-07-10 | COMP | Rule 16 | 36 | 129 | 61 | 1 | 17 | 90 | 543
1610 | 2017-05-11 | 2017-06-30 | 2018-02-27 | 2018-02-27 | COMP | 2018-04-04 | COMP | 2018-06-18 | COMP | 2020-04-25 | INPR | 2019-04-13 | COMP | Rule 16 | 36 | 164 | 27 | 53 |  |  | 482
1615 | 2017-05-11 | 2017-07-07 | 2018-02-18 | 2018-02-18 | COMP | 2018-05-18 | COMP | 2018-06-25 | COMP | 2018-12-30 | COMP | 2019-01-30 | COMP | Rule 15/16 | 40 | 154 | 64 | 26 | 129 | 21 | 431
2178 | 2017-05-11 | 2017-10-05 | 2017-12-03 | 2017-12-03 | COMP | 2018-01-26 | COMP | 2018-01-26 | COMP | 2018-01-30 | COMP | 2020-03-23 | COMP | Rule 16 | 103 | 39 | 37 | 1 | 3 | 539 | 718
4600 | 2017-05-11 | 2018-02-13 | 2018-03-03 | 2018-03-03 | COMP | 2018-04-20 | COMP | 2018-11-20 | COMP | 2019-01-15 | COMP | 2019-02-25 | COMP | Rule 16 | 190 | 13 | 35 | 149 | 37 | 28 | 448
5313 | 2017-05-11 | 2018-05-22 | 2018-07-13 | 2018-07-13 | COMP | 2018-08-10 | COMP | 2018-08-14 | COMP | 2019-04-16 | COMP | 2019-06-07 | COMP | Rule 16 | 259 | 37 | 21 | 3 | 168 | 38 | 521
1355 | 2017-05-12 | 2017-05-16 | 2017-08-14 | 2017-08-14 | COMP | 2018-05-29 | COMP | 2018-06-22 | COMP | 2018-11-19 | COMP | 2019-01-27 | COMP | Rule 16 | 3 | 63 | 198 | 19 | 104 | 45 | 427
1556 | 2017-05-12 | 2017-06-22 | 2017-06-22 | 2017-06-22 | COMP | 2019-09-21 | COMP | 2019-09-21 | REQD | 2019-09-21 | REQD | 2019-06-11 | COMP | Rule 16 | 29 | 1 | 565 |  |  |  | 522
1978 | 2017-05-12 | 2017-08-31 | 2018-05-24 | 2018-05-24 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-11-13 | COMP | 2019-12-11 | COMP | Rule 16 | 78 | 183 | 57 | 1 | 315 | 19 | 648
3629 | 2017-05-12 | 2018-05-26 | 2018-06-18 | 2018-06-18 | COMP | 2018-08-07 | COMP | 2018-08-15 | COMP | 2019-04-20 | INPR | 2019-01-30 | COMP | Rule 16 | 261 | 15 | 36 | 7 |  |  | 430
5634 | 2017-05-12 | 2018-06-23 | 2018-08-23 | 2018-08-23 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2019-11-24 | INPR | 2019-06-24 | COMP | Rule 16 | 280 | 43 | 45 | 1 |  |  | 531
8027 | 2017-05-12 | 2018-11-14 | 2019-02-20 | 2019-02-20 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-04-02 | COMP | 2019-10-22 | COMP | Rule 16 | 380 | 65 | 9 | 1 | 22 | 143 | 615
3221 | 2017-05-14 | 2018-03-23 | 2018-05-31 | 2018-05-30 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2020-02-13 | COMP | 2020-05-06 | COMP | Rule 16 | 215 | 49 | 93 | 1 | 337 | 59 | 748
1342 | 2017-05-15 | 2017-05-17 | 2019-03-03 | 2019-03-03 | COMP | 2019-05-06 | COMP | 2019-07-02 | COMP | 2019-07-03 | COMP | 2019-09-09 | COMP | Rule 15/16 | 3 | 448 | 46 | 41 | 2 | 47 | 583
1485 | 2017-05-15 | 2017-06-08 | 2018-01-30 | 2018-01-30 | COMP | 2018-03-16 | COMP | 2018-03-16 | COMP | 2018-12-13 | COMP | 2020-05-18 | COMP | Rule 16 | 18 | 161 | 33 | 1 | 189 | 359 | 756
1891 | 2017-05-15 | 2017-08-16 | 2018-03-26 | 2018-03-26 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-02-03 | COMP | 2019-05-31 | COMP | Rule 16 | 66 | 151 | 100 | 1 | 117 | 83 | 514
1971 | 2017-05-15 | 2017-08-30 | 2018-01-09 | 2018-01-09 | COMP | 2018-06-25 | COMP | 2018-06-25 | COMP | 2018-12-15 | COMP | 2020-04-08 | COMP | Rule 16 | 76 | 89 | 117 | 1 | 120 | 329 | 728
1985 | 2017-05-15 | 2017-09-01 | 2017-11-10 | 2017-11-10 | COMP | 2017-12-05 | COMP | 2018-02-08 | INPR | 2022-03-19 | REQD | 2019-01-31 | COMP | Rule 16 | 78 | 49 | 15 |  |  |  | 430
2012 | 2017-05-15 | 2017-09-06 | 2017-11-12 | 2017-11-12 | COMP | 2018-10-11 | COMP | 2018-10-11 | COMP | 2019-08-05 | COMP | 2019-09-13 | COMP | Rule 16 | 80 | 47 | 230 | 1 | 204 | 29 | 587
2393 | 2017-05-15 | 2017-11-16 | 2018-04-23 | 2018-04-23 | COMP | 2018-05-30 | COMP | 2018-07-05 | COMP | 2019-01-19 | COMP | 2019-04-16 | COMP | Rule 16 | 130 | 107 | 27 | 26 | 136 | 60 | 482
6157 | 2017-05-15 | 2018-08-01 | 2018-10-12 | 2018-10-12 | COMP | 2019-01-25 | COMP | 2019-06-28 | COMP | 2023-03-09 | COMP | 2023-05-05 | COMP | Rule 16 | 306 | 52 | 70 | 109 | 928 | 42 | 1502
1430 | 2017-05-16 | 2017-06-01 | 2017-10-04 | 2017-10-04 | COMP | 2019-02-25 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-06-12 | COMP | Rule 16 | 12 | 88 | 347 | 2 | 1 | 76 | 521
1465 | 2017-05-16 | 2017-06-07 | 2017-10-06 | 2017-10-06 | COMP | 2017-11-02 | COMP | 2017-11-16 | COMP | 2019-09-13 | COMP | 2020-12-23 | COMP | Rule 16 | 16 | 86 | 20 | 10 | 458 | 322 | 907
1517 | 2017-05-16 | 2017-06-14 | 2017-07-27 | 2017-12-19 | COMP | 2018-02-08 | COMP | 2018-02-08 | COMP | 2019-02-06 | COMP | 2019-03-12 | COMP | Rule 16 | 21 | 31 | 35 | 1 | 250 | 24 | 456
1673 | 2017-05-16 | 2017-07-13 | 2019-07-01 | 2019-07-01 | COMP | 2019-08-21 | COMP | 2019-09-10 | COMP | 2020-06-04 | COMP | 2019-11-25 | COMP | Rule 16 | 41 | 494 | 37 | 14 | 185 |  | 636
1698 | 2017-05-16 | 2017-07-17 | 2018-08-16 | 2020-04-08 | COMP | 2020-05-01 | COMP | 2020-05-01 | COMP | 2020-08-19 | COMP | 2020-06-16 | COMP | Rule 16 | 43 | 274 | 18 | 1 | 78 |  | 775
1879 | 2017-05-16 | 2017-08-15 | 2017-12-08 | 2017-12-08 | COMP | 2018-07-12 | COMP | 2018-08-02 | COMP | 2019-06-13 | COMP | 2019-07-23 | COMP | Rule 16 | 64 | 80 | 149 | 16 | 217 | 28 | 549
1896 | 2017-05-16 | 2017-08-17 | 2018-08-16 | 2018-08-16 | COMP | 2018-09-28 | COMP | 2018-11-19 | COMP | 2019-06-13 | COMP | 2019-08-09 | COMP | Rule 16 | 66 | 251 | 31 | 36 | 142 | 41 | 562
2181 | 2017-05-16 | 2017-10-05 | 2018-03-20 | 2018-03-20 | COMP | 2018-06-06 | COMP | 2018-10-25 | COMP | 2019-11-24 | INPR | 2019-08-16 | COMP | Rule 15/16 | 100 | 112 | 56 | 100 |  |  | 567
2279 | 2017-05-16 | 2017-10-27 | 2018-03-14 | 2018-03-14 | COMP | 2018-04-20 | COMP | 2018-07-23 | COMP | 2018-12-20 | COMP | 2019-01-24 | COMP | Rule 15/16 | 116 | 92 | 28 | 65 | 105 | 23 | 424
4434 | 2017-05-16 | 2017-12-07 | 2018-01-29 | 2018-01-29 | COMP | 2018-06-19 | COMP | 2018-06-19 | COMP | 2019-09-12 | COMP | 2019-10-05 | COMP | Rule 15/16 | 142 | 35 | 100 | 1 | 311 | 17 | 601
4484 | 2017-05-16 | 2018-01-05 | 2018-05-11 | 2019-05-31 | COMP | 2019-07-15 | COMP | 2019-07-29 | COMP | 2019-07-24 | COMP | 2019-09-27 | COMP | Rule 15/16 | 161 | 89 | 31 | 11 | 0 | 44 | 596
1362 | 2017-05-17 | 2017-05-17 | 2017-08-18 | 2017-08-18 | COMP | 2017-08-21 | COMP | 2017-08-21 | COMP | 2019-07-21 | REQD | 2019-03-27 | COMP | Rule 16 | 1 | 66 | 2 | 1 |  |  | 466
1536 | 2017-05-17 | 2017-06-19 | 2017-07-31 | 2017-07-31 | COMP | 2017-08-02 | COMP | 2017-08-04 | COMP | 2018-06-08 | COMP | 2022-05-20 | COMP | Rule 16 | 23 | 30 | 3 | 3 | 212 | 995 | 1261
1593 | 2017-05-17 | 2017-06-28 | 2019-01-16 | 2019-01-16 | COMP | 2019-07-24 | COMP | 2019-08-07 | COMP | 2019-08-09 | COMP | 2019-09-11 | COMP | Rule 15/16 | 30 | 389 | 132 | 11 | 3 | 23 | 583
1618 | 2017-05-17 | 2017-07-03 | 2017-08-27 | 2017-08-27 | COMP | 2018-09-28 | COMP | 2017-10-24 | COMP | 2019-04-18 | COMP | 2019-05-08 | COMP | Rule 16 | 33 | 39 | 274 |  | 371 | 15 | 496
1854 | 2017-05-17 | 2017-08-11 | 2017-12-15 | 2017-12-15 | COMP | 2018-05-01 | COMP | 2018-06-06 | COMP | 2018-06-06 | COMP | 2019-01-11 | COMP | Rule 16 | 61 | 87 | 94 | 26 | 1 | 151 | 415
2069 | 2017-05-17 | 2017-09-19 | 2017-10-20 | 2017-10-20 | COMP | 2019-02-28 | COMP | 2019-03-29 | COMP | 2019-03-28 | COMP | 2019-05-28 | COMP | Rule 16 | 87 | 24 | 338 | 22 | 0 | 42 | 509
2268 | 2017-05-17 | 2017-10-26 | 2018-03-07 | 2018-03-07 | COMP | 2018-11-27 | COMP | 2019-01-07 | COMP | 2020-06-02 | COMP | 2021-01-04 | COMP | Rule 16 | 114 | 88 | 184 | 28 | 354 | 149 | 912
4525 | 2017-05-17 | 2018-01-22 | 2018-06-21 | 2019-03-26 | COMP | 2019-07-22 | COMP | 2019-12-05 | COMP | 2020-07-27 | COMP | 2020-09-26 | COMP | Rule 16 | 170 | 107 | 83 | 95 | 163 | 44 | 846
5563 | 2017-05-17 | 2018-06-13 | 2018-08-31 | 2018-08-31 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-06-25 | COMP | 2019-10-21 | COMP | Rule 15/16 | 270 | 57 | 46 | 1 | 159 | 83 | 611
1504 | 2017-05-18 | 2017-06-13 | 2017-06-13 | 2017-06-13 | COMP | 2017-06-15 | COMP | 2017-06-15 | COMP | 2019-11-23 | INPR | 2019-08-08 | COMP | Rule 16 | 18 | 1 | 3 | 1 |  |  | 559
1539 | 2017-05-18 | 2017-06-20 | 2017-08-02 | 2020-07-21 | COMP | 2020-08-06 | COMP | 2021-01-02 | COMP | 2021-01-16 | COMP | 2021-02-22 | COMP | Rule 16 | 23 | 31 | 13 | 101 | 10 | 24 | 944
1569 | 2017-05-18 | 2017-06-25 | 2017-09-20 | 2017-09-20 | COMP | 2017-10-09 | COMP | 2018-01-20 | COMP | 2018-01-22 | COMP | 2021-02-20 | COMP | Rule 16 | 26 | 61 | 14 | 69 | 1 | 775 | 943
1622 | 2017-05-18 | 2017-07-05 | 2017-10-15 | 2017-10-15 | COMP | 2018-09-04 | REQD | 2018-10-08 | COMP | 2018-12-18 | COMP | 2019-02-20 | COMP | Rule 15/16 | 33 | 72 |  | 246 | 49 | 43 | 440
1692 | 2017-05-18 | 2017-07-17 | 2018-10-18 | 2020-04-10 | COMP | 2020-09-14 | COMP | 2020-10-02 | COMP | 2020-10-22 | COMP | 2020-10-30 | COMP | Rule 16 | 41 | 318 | 110 | 15 | 15 | 7 | 870
1947 | 2017-05-18 | 2017-08-24 | 2017-09-18 | 2017-09-18 | COMP | 2018-03-21 | COMP | 2018-03-21 | COMP | 2019-06-25 | COMP | 2019-08-12 | COMP | Rule 16 | 69 | 17 | 126 | 1 | 319 | 34 | 561
2111 | 2017-05-18 | 2017-09-26 | 2018-07-19 | 2018-07-19 | COMP | 2018-10-01 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-08-13 | COMP | Rule 15/16 | 91 | 204 | 52 | 199 | 1 | 20 | 562
1691 | 2017-05-19 | 2017-07-17 | 2018-07-09 | 2018-07-09 | COMP | 2018-07-06 | COMP | 2018-11-12 | COMP | 2019-02-20 | COMP | 2019-03-08 | COMP | Rule 15/16 | 40 | 246 |  | 90 | 66 | 13 | 451
1785 | 2017-05-19 | 2017-07-25 | 2018-01-26 | 2018-01-26 | COMP | 2018-12-04 | COMP | 2018-12-05 | COMP | 2018-12-17 | COMP | 2019-01-04 | COMP | Rule 16 | 46 | 127 | 216 | 2 | 9 | 13 | 408
1842 | 2017-05-19 | 2017-08-08 | 2017-12-22 | 2017-12-22 | COMP | 2018-02-07 | COMP | 2018-05-17 | COMP | 2019-02-12 | COMP | 2019-04-25 | COMP | Rule 16 | 56 | 95 | 31 | 71 | 185 | 52 | 485
1983 | 2017-05-19 | 2017-09-01 | 2018-02-06 | 2018-02-06 | COMP | 2018-02-26 | COMP | 2018-02-26 | COMP | 2019-01-28 | COMP | 2019-02-25 | COMP | Rule 16 | 74 | 106 | 14 | 1 | 232 | 20 | 442
2017 | 2017-05-19 | 2017-09-07 | 2017-10-07 | 2017-10-07 | COMP | 2017-10-11 | COMP | 2017-10-25 | COMP | 2021-05-08 | INPR | 2021-03-03 | COMP | Rule 16 | 77 | 22 | 3 | 11 |  |  | 950
7807 | 2017-05-19 | 2018-11-01 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-06 | COMP | 2018-12-11 | NOTN | 2019-01-04 | COMP | 2019-02-25 | COMP | Rule 16 | 367 | 8 | 16 |  |  |  | 442
15839 | 2017-05-19 | 2019-11-24 | 2020-03-03 | 2020-10-05 | COMP | 2020-11-23 | COMP | 2020-12-16 | COMP | 2020-07-07 | COMP | 2021-02-17 | COMP | Rule 16 | 632 | 66 | 35 | 16 | 0 | 42 | 940
1687 | 2017-05-20 | 2017-07-17 | 2019-06-04 | 2019-06-04 | COMP | 2019-07-11 | COMP | 2019-09-20 | COMP | 2020-08-13 | COMP | 2020-06-24 | COMP | Rule 16 | 39 | 473 | 27 | 51 | 227 |  | 777
1688 | 2017-05-20 | 2017-07-17 | 2018-07-09 | 2018-07-09 | COMP | 2018-08-30 | COMP | 2018-11-27 | COMP | 2023-11-11 | INPR | 2019-08-18 | COMP | Rule 16 | 39 | 246 | 39 | 60 |  |  | 563
1689 | 2017-05-20 | 2017-07-17 | 2018-10-15 | 2018-10-15 | COMP | 2019-01-28 | COMP | 2019-02-28 | COMP | 2019-02-20 | COMP | 2019-04-17 | COMP | Rule 16 | 39 | 315 | 70 | 23 | 0 | 35 | 478
1697 | 2017-05-20 | 2017-07-17 | 2018-06-19 | 2018-06-19 | COMP | 2018-07-18 | COMP | 2018-08-27 | COMP | 2019-01-30 | COMP | 2019-01-31 | COMP | Rule 16 | 39 | 233 | 21 | 29 | 106 | 2 | 425
1826 | 2017-05-20 | 2017-08-03 | 2017-11-13 | 2018-04-01 | COMP | 2018-05-11 | COMP | 2018-05-16 | COMP | 2018-10-15 | COMP | 2019-03-23 | COMP | Rule 15/16 | 52 | 71 | 30 | 4 | 106 | 108 | 460
1693 | 2017-05-21 | 2017-07-17 | 2018-08-21 | 2020-07-22 | COMP | 2020-10-19 | COMP | 2019-03-26 | COMP | 2023-12-02 | INPR | 2020-12-03 | COMP | Rule 16 | 39 | 277 | 63 |  |  |  | 889
1694 | 2017-05-21 | 2017-07-17 | 2018-11-28 | 2020-05-21 | COMP | 2020-06-10 | COMP | 2020-08-07 | COMP | 2020-10-24 | COMP | 2020-10-12 | COMP | Rule 16 | 39 | 344 | 14 | 43 | 55 |  | 854
1696 | 2017-05-21 | 2017-07-17 | 2018-03-15 | 2018-03-15 | COMP | 2018-04-02 | COMP | 2018-06-15 | COMP | 2023-11-11 | INPR | 2020-12-11 | COMP | Rule 16 | 39 | 166 | 13 | 54 |  |  | 895
1830 | 2017-05-22 | 2017-08-04 | 2018-02-16 | 2018-02-16 | COMP | 2018-05-09 | COMP | 2018-09-28 | COMP | 2020-05-31 | INPR | 2020-01-10 | COMP | Rule 15/16 | 53 | 134 | 58 | 100 |  |  | 662
2151 | 2017-05-22 | 2017-09-30 | 2019-08-29 | 2019-08-29 | COMP | 2019-09-12 | COMP | 2019-10-21 | COMP | 2020-04-02 | COMP | 2020-06-03 | COMP | Rule 15/16 | 92 | 480 | 10 | 28 | 112 | 44 | 762
2572 | 2017-05-22 | 2017-12-27 | 2018-01-20 | 2018-01-20 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2020-06-04 | COMP | 2020-07-15 | COMP | Rule 16 | 151 | 16 | 266 | 1 | 332 | 30 | 792
3602 | 2017-05-22 | 2018-05-23 | 2018-10-16 | 2018-10-16 | COMP | 2019-04-03 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-05-19 | COMP | Rule 15/16 | 253 | 102 | 115 | 238 | 1 | 48 | 752
4405 | 2017-05-22 | 2017-11-20 | 2018-03-01 | 2018-03-01 | COMP | 2018-04-25 | COMP | 2018-04-26 | COMP | 2018-12-18 | COMP | 2019-02-25 | COMP | Rule 16 | 127 | 68 | 40 | 2 | 163 | 46 | 441
4502 | 2017-05-22 | 2018-01-10 | 2018-04-23 | 2018-04-23 | COMP | 2018-08-16 | COMP | 2018-08-16 | COMP | 2019-03-06 | COMP | 2019-03-22 | COMP | Rule 16 | 160 | 72 | 82 | 1 | 137 | 13 | 460
4535 | 2017-05-22 | 2018-01-23 | 2018-03-11 | 2020-03-08 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2020-04-07 | COMP | 2020-07-10 | COMP | Rule 16 | 168 | 33 | 12 | 1 | 11 | 68 | 789
4593 | 2017-05-23 | 2018-02-09 | 2018-04-01 | 2018-04-01 | COMP | 2018-09-05 | COMP | 2018-09-05 | COMP | 2019-07-21 | INPR | 2019-03-15 | COMP | Rule 16 | 180 | 35 | 110 | 1 |  |  | 454
1614 | 2017-05-24 | 2017-07-07 | 2018-03-08 | 2019-02-14 | COMP | 2019-06-19 | COMP | 2019-10-16 | COMP | 2019-10-20 | COMP | 2019-12-12 | COMP | Rule 15/16 | 31 | 167 | 88 | 84 | 3 | 36 | 641
1637 | 2017-05-24 | 2017-07-07 | 2018-06-12 | 2019-09-09 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2023-04-29 | INPR | 2020-06-25 | COMP | Rule 16 | 31 | 234 | 50 | 1 |  |  | 776
1801 | 2017-05-24 | 2017-07-28 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-28 | COMP | 2019-04-04 | COMP | 2021-01-07 | COMP | 2021-02-16 | COMP | Rule 15/16 | 46 | 374 | 44 | 6 | 444 | 27 | 936
1993 | 2017-05-24 | 2017-09-05 | 2018-02-28 | 2018-02-28 | COMP | 2018-03-27 | COMP | 2018-03-27 | COMP | 2022-01-29 | INPR | 2020-12-06 | COMP | Rule 16 | 72 | 120 | 20 | 1 |  |  | 888
2249 | 2017-05-24 | 2017-10-23 | 2018-12-30 | 2019-12-02 | COMP | 2020-06-30 | COMP | 2019-09-16 | INPR | 2023-04-29 | CANC | 2020-09-30 | COMP | Rule 15/16 | 106 | 296 | 147 |  |  |  | 844
2515 | 2017-05-24 | 2017-12-12 | 2018-05-29 | 2018-05-29 | COMP | 2018-07-26 | COMP | 2019-02-06 | COMP | 2019-10-19 | INPR | 2019-06-19 | COMP | Rule 15/16 | 139 | 116 | 42 | 133 |  |  | 520
3406 | 2017-05-24 | 2018-04-19 | 2018-05-14 | 2018-05-14 | COMP | 2019-01-24 | COMP | 2019-05-15 | COMP | 2019-05-15 | COMP | 2019-06-25 | COMP | Rule 16 | 227 | 18 | 175 | 79 | 1 | 29 | 524
4024 | 2017-05-24 | 2018-12-07 | 2019-03-28 | 2019-03-28 | COMP | 2019-07-24 | COMP | 2020-04-16 | COMP | 2020-04-02 | COMP | 2020-05-29 | COMP | Rule 16 | 387 | 76 | 83 | 184 | 0 | 31 | 757
5434 | 2017-05-24 | 2018-05-30 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-13 | COMP | 2018-11-16 | COMP | 2019-02-17 | COMP | 2019-01-28 | COMP | Rule 16 | 255 | 109 | 9 | 4 | 61 |  | 420
1501 | 2017-05-25 | 2017-06-10 | 2018-04-26 | 2018-04-26 | COMP | 2018-04-26 | NOTN | 2018-06-06 | COMP | 2018-05-22 | COMP | 2019-07-15 | COMP | Other | 11 | 220 |  | 29 | 0 | 278 | 536
1532 | 2017-05-25 | 2017-06-19 | 2017-08-19 | 2017-08-19 | COMP | 2017-10-02 | COMP | 2018-07-02 | COMP | 2018-01-18 | COMP | 2019-02-11 | COMP | Other | 17 | 44 | 30 | 188 | 0 | 153 | 429
1557 | 2017-05-25 | 2017-06-22 | 2018-07-09 | 2018-07-09 | COMP | 2018-09-04 | COMP | 2018-10-30 | COMP | 2020-01-31 | COMP | 2019-12-09 | COMP | Rule 16 | 20 | 262 | 41 | 41 | 313 |  | 637
1563 | 2017-05-25 | 2017-06-23 | 2018-04-20 | 2018-04-20 | COMP | 2018-05-22 | COMP | 2018-09-04 | COMP | 2019-09-06 | COMP | 2019-10-22 | COMP | Rule 16 | 21 | 207 | 23 | 73 | 254 | 33 | 606
1564 | 2017-05-25 | 2017-06-23 | 2018-08-16 | 2018-08-16 | COMP | 2018-10-04 | COMP | 2019-01-18 | COMP | 2019-01-23 | COMP | 2019-07-26 | COMP | Rule 16 | 21 | 289 | 35 | 72 | 3 | 130 | 545
1625 | 2017-05-25 | 2017-07-05 | 2017-12-13 | 2019-01-25 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2020-01-30 | COMP | 2020-03-07 | COMP | Rule 16 | 28 | 112 | 68 | 1 | 188 | 26 | 697
2428 | 2017-05-25 | 2017-11-28 | 2018-07-11 | 2018-07-11 | COMP | 2018-10-31 | COMP | 2019-09-04 | COMP | 2019-10-01 | COMP | 2019-12-14 | COMP | Rule 15/16 | 128 | 156 | 80 | 211 | 20 | 51 | 641
2817 | 2017-05-25 | 2018-02-04 | 2018-05-08 | 2018-05-08 | COMP | 2018-09-25 | COMP | 2018-09-27 | COMP | 2020-03-03 | COMP | 2020-04-26 | COMP | Rule 16 | 173 | 66 | 98 | 3 | 357 | 39 | 732
5805 | 2017-05-25 | 2018-07-06 | 2018-12-20 | 2018-12-20 | COMP | 2019-04-30 | COMP | 2019-03-12 | COMP | 2019-07-21 | INPR | 2019-04-04 | COMP | Rule 16 | 280 | 116 | 90 |  |  |  | 466
12431 | 2017-05-25 | 2019-06-06 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-19 | COMP | 2019-08-27 | COMP | 2019-12-31 | COMP | 2020-01-08 | COMP | Rule 16 | 510 | 40 | 13 | 7 | 86 | 6 | 657
1528 | 2017-05-26 | 2017-06-16 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-06 | COMP | 2019-10-08 | COMP | 2020-01-31 | COMP | 2019-11-22 | COMP | Rule 16 | 15 | 337 | 34 | 212 | 78 |  | 627
1670 | 2017-05-26 | 2017-07-13 | 2017-08-09 | 2017-08-09 | COMP | 2017-07-13 | NOTN | 2018-06-01 | COMP | 2018-11-21 | COMP | 2019-01-23 | COMP | Other | 33 | 20 |  | 204 | 121 | 41 | 415
1918 | 2017-05-26 | 2017-08-21 | 2018-08-08 | 2019-04-27 | COMP | 2019-09-04 | COMP | 2022-03-11 | COMP | 2022-05-11 | COMP | 2022-06-28 | COMP | Rule 15/16 | 60 | 243 | 90 | 634 | 44 | 33 | 1279
2739 | 2017-05-26 | 2018-01-25 | 2018-04-13 | 2018-04-13 | COMP | 2018-07-24 | COMP | 2018-07-24 | COMP | 2019-03-05 | COMP | 2019-05-02 | COMP | Rule 16 | 166 | 56 | 71 | 1 | 153 | 43 | 485
3003 | 2017-05-26 | 2018-02-26 | 2018-08-27 | 2018-08-27 | COMP | 2018-09-26 | COMP | 2019-01-30 | COMP | 2024-02-03 | INPR | 2019-02-10 | COMP | Rule 16 | 187 | 129 | 22 | 85 |  |  | 427
2142 | 2017-05-27 | 2017-09-28 | 2018-03-01 | 2018-03-01 | COMP | 2020-10-06 | COMP | 2020-10-06 | COMP | 2020-10-23 | COMP | 2021-05-01 | COMP | Rule 16 | 86 | 104 | 657 | 1 | 14 | 129 | 986
1479 | 2017-05-30 | 2017-06-08 | 2017-07-25 | 2017-07-25 | COMP | 2018-09-18 | COMP | 2018-11-14 | COMP | 2019-10-24 | COMP | 2019-11-25 | COMP | Rule 16 | 8 | 33 | 290 | 41 | 238 | 22 | 627
1516 | 2017-05-30 | 2017-06-14 | 2018-04-12 | 2018-04-12 | COMP | 2019-02-28 | COMP | 2018-05-17 | COMP | 2018-10-10 | COMP | 2019-05-03 | COMP | Rule 16 | 12 | 208 | 221 |  | 102 | 141 | 485
1558 | 2017-05-30 | 2017-06-22 | 2019-09-27 | 2019-09-27 | COMP | 2020-02-11 | COMP | 2020-08-10 | COMP | 2020-07-31 | COMP | 2020-08-27 | COMP | Rule 16 | 18 | 570 | 92 | 128 | 0 | 14 | 818
1596 | 2017-05-30 | 2017-06-28 | 2018-06-05 | 2018-06-05 | COMP | 2018-09-28 | COMP | 2018-11-14 | COMP | 2021-02-27 | INPR | 2019-09-13 | COMP | Rule 15/16 | 22 | 235 | 82 | 33 |  |  | 577
1600 | 2017-05-30 | 2017-06-29 | 2018-05-01 | 2019-02-13 | COMP | 2019-02-22 | COMP | 2019-04-11 | COMP |  | INPR | 2019-11-19 | COMP | Rule 15/16 | 23 | 210 | 7 | 35 |  |  | 623
1616 | 2017-05-30 | 2017-07-07 | 2018-03-12 | 2018-08-02 | COMP | 2019-07-03 | COMP | 2019-07-16 | COMP | 2019-06-26 | COMP | 2022-03-23 | COMP | Rule 15/16 | 28 | 169 | 231 | 9 | 0 | 677 | 1211
1682 | 2017-05-30 | 2017-07-15 | 2018-11-06 | 2018-11-06 | COMP | 2019-09-04 | COMP | 2020-02-20 | COMP | 2020-05-11 | COMP | 2020-06-15 | COMP | Rule 15/16 | 33 | 331 | 207 | 115 | 58 | 25 | 765
1831 | 2017-05-30 | 2017-08-04 | 2017-09-25 | 2017-09-25 | COMP | 2018-07-06 | COMP | 2018-07-06 | COMP | 2020-03-26 | COMP | 2020-04-01 | COMP | Rule 16 | 48 | 36 | 196 | 1 | 432 | 5 | 713
2281 | 2017-05-30 | 2017-10-27 | 2018-10-17 | 2018-10-17 | COMP | 2019-04-03 | COMP | 2019-04-04 | COMP | 2019-04-30 | COMP | 2019-07-25 | COMP | Rule 16 | 107 | 244 | 114 | 2 | 19 | 61 | 542
2382 | 2017-05-30 | 2017-11-15 | 2018-06-14 | 2018-06-14 | COMP | 2018-09-04 | COMP | 2018-10-19 | COMP |  | INPR | 2019-07-11 | COMP | Rule 15/16 | 119 | 145 | 57 | 34 |  |  | 532
2463 | 2017-05-30 | 2017-12-05 | 2019-02-08 | 2019-02-08 | COMP | 2019-03-07 | COMP | 2019-05-09 | COMP | 2019-06-13 | COMP | 2019-07-19 | COMP | Rule 16 | 131 | 296 | 19 | 46 | 25 | 26 | 538
2483 | 2017-05-30 | 2017-12-07 | 2018-04-26 | 2020-12-08 | COMP | 2021-01-20 | COMP | 2021-01-20 | COMP | 2021-04-19 | COMP | 2021-05-14 | COMP | Rule 16 | 133 | 97 | 29 | 1 | 63 | 20 | 996
2485 | 2017-05-30 | 2017-12-07 | 2018-04-26 | 2020-03-23 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2021-12-21 | COMP | 2022-02-18 | COMP | Rule 15/16 | 133 | 97 | 95 | 1 | 348 | 43 | 1189
4461 | 2017-05-30 | 2017-12-15 | 2018-03-21 | 2019-08-21 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2021-02-27 | INPR | 2020-01-06 | COMP | Rule 16 | 139 | 65 | 12 | 1 |  |  | 653
5736 | 2017-05-30 | 2018-06-27 | 2018-11-16 | 2018-12-04 | COMP | 2018-12-07 | COMP | 2018-12-13 | COMP | 2019-04-03 | COMP | 2019-05-08 | COMP | Rule 16 | 272 | 100 | 4 | 5 | 76 | 26 | 488
1521 | 2017-05-31 | 2017-06-14 | 2017-07-20 | 2017-07-20 | COMP | 2017-08-17 | COMP | 2017-08-25 | COMP | 2017-10-09 | COMP | 2019-05-31 | COMP | Rule 16 | 11 | 26 | 21 | 7 | 31 | 412 | 503
1567 | 2017-05-31 | 2017-06-24 | 2017-09-01 | 2017-09-01 | COMP | 2019-01-16 | COMP | 2019-01-16 | COMP | 2019-09-11 | COMP | 2019-11-19 | COMP | Rule 16 | 18 | 49 | 343 | 1 | 166 | 49 | 622
1656 | 2017-05-31 | 2017-07-12 | 2017-12-01 | 2017-12-01 | COMP | 2018-01-16 | COMP | 2018-03-21 | COMP | 2018-12-21 | COMP | 2019-01-31 | COMP | Rule 16 | 30 | 99 | 30 | 46 | 192 | 27 | 419
1759 | 2017-05-31 | 2017-07-20 | 2018-01-14 | 2018-01-14 | COMP | 2018-03-28 | COMP | 2018-04-06 | COMP | 2022-03-19 | INPR | 2021-02-25 | COMP | Rule 16 | 36 | 121 | 51 | 8 |  |  | 939
1783 | 2017-05-31 | 2017-07-25 | 2017-10-28 | 2018-09-04 | COMP | 2018-09-12 | COMP | 2018-11-19 | COMP | 2018-10-31 | COMP | 2019-01-12 | COMP | Rule 16 | 39 | 68 | 7 | 48 | 0 | 36 | 406
2230 | 2017-05-31 | 2017-10-18 | 2018-05-03 | 2018-05-03 | COMP | 2018-06-18 | COMP | 2018-09-28 | COMP | 2019-01-16 | COMP | 2019-02-28 | COMP | Rule 15/16 | 99 | 135 | 32 | 73 | 74 | 30 | 438
3395 | 2017-05-31 | 2018-04-18 | 2019-04-01 | 2019-04-01 | COMP | 2022-09-12 | COMP | 2022-11-07 | COMP | 2022-09-19 | COMP | 2023-04-27 | COMP | Rule 16 | 222 | 239 | 870 | 41 | 0 | 117 | 1485
4197 | 2017-05-31 | 2019-07-02 | 2019-11-18 | 2020-06-19 | COMP | 2020-07-02 | COMP | 2020-07-16 | COMP | 2020-09-14 | COMP | 2020-09-25 | COMP | Rule 16 | 525 | 97 | 10 | 11 | 42 | 10 | 837
4714 | 2017-05-31 | 2018-03-20 | 2018-11-08 | 2018-11-08 | COMP | 2019-03-18 | COMP | 2019-04-10 | COMP | 2019-05-08 | COMP | 2019-08-12 | COMP | Rule 16 | 201 | 165 | 86 | 18 | 21 | 67 | 553
5930 | 2017-05-31 | 2018-07-12 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-05 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2019-12-05 | COMP | Rule 16 | 281 | 82 | 20 | 187 | 1 | 66 | 632
9069 | 2017-05-31 | 2019-01-15 | 2019-02-08 | 2019-02-08 | COMP | 2019-02-22 | COMP | 2019-03-08 | COMP | 2019-03-18 | COMP | 2019-05-14 | COMP | Rule 16 | 408 | 18 | 10 | 11 | 7 | 42 | 491
1762 | 2017-06-01 | 2017-07-21 | 2018-04-18 | 2018-06-06 | COMP | 2018-07-11 | COMP | 2019-12-04 | COMP | 2020-03-11 | COMP | 2020-05-01 | COMP | Rule 15/16 | 36 | 186 | 25 | 352 | 67 | 38 | 733
1775 | 2017-06-01 | 2017-07-24 | 2017-09-17 | 2017-09-17 | COMP | 2020-03-26 | COMP | 2017-10-05 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | Rule 16 | 37 | 39 | 632 |  | 622 | 1 | 710
1787 | 2017-06-01 | 2017-07-26 | 2018-03-12 | 2018-03-12 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-04-18 | COMP | 2019-05-23 | COMP | Rule 16 | 39 | 156 | 237 | 1 | 43 | 26 | 497
1796 | 2017-06-01 | 2017-07-28 | 2017-10-25 | 2017-10-25 | COMP | 2017-12-01 | NOTN | 2018-01-18 | COMP | 2017-08-25 | COMP | 2019-01-24 | COMP | Other | 41 | 63 |  | 56 | 0 | 256 | 413
1950 | 2017-06-01 | 2017-08-25 | 2017-12-04 | 2017-12-04 | COMP | 2018-01-02 | COMP | 2018-01-17 | COMP | 2018-10-10 | COMP | 2019-03-08 | COMP | Rule 16 | 61 | 68 | 20 | 11 | 187 | 101 | 443
3605 | 2017-06-01 | 2018-05-23 | 2018-10-30 | 2018-10-30 | COMP | 2018-12-19 | COMP | 2019-05-09 | COMP |  | INPR | 2019-06-05 | COMP | Rule 15/16 | 246 | 112 | 34 | 98 |  |  | 505
4565 | 2017-06-01 | 2018-01-31 | 2018-05-16 | 2018-05-16 | COMP | 2018-05-18 | COMP | 2018-05-18 | COMP | 2019-10-21 | INPR | 2019-04-01 | COMP | Rule 16 | 167 | 75 | 3 | 1 |  |  | 459
1545 | 2017-06-02 | 2017-06-21 | 2017-07-26 | 2018-06-04 | COMP | 2018-12-18 | COMP | 2017-11-09 | COMP | 2018-12-18 | COMP | 2019-02-01 | COMP | Rule 16 | 14 | 25 | 137 |  | 276 | 31 | 418
1560 | 2017-06-02 | 2017-06-22 | 2019-07-25 | 2019-07-25 | COMP | 2019-09-16 | COMP | 2019-10-04 | COMP | 2019-11-01 | COMP | 2019-10-25 | COMP | Rule 16 | 15 | 525 | 37 | 15 | 21 |  | 604
1802 | 2017-06-02 | 2017-07-28 | 2018-06-25 | 2019-01-14 | COMP | 2019-12-16 | COMP | 2020-08-14 | COMP | 2020-11-10 | COMP | 2021-04-06 | COMP | Rule 15/16 | 40 | 228 | 233 | 170 | 62 | 99 | 965
1815 | 2017-06-02 | 2017-08-02 | 2018-01-18 | 2020-02-11 | COMP | 2021-03-16 | COMP | 2021-08-19 | COMP | 2021-04-26 | COMP | 2022-02-08 | COMP | Rule 15/16 | 43 | 115 | 276 | 111 | 0 | 119 | 1178
2018 | 2017-06-02 | 2017-09-07 | 2018-03-30 | 2018-03-30 | COMP |  | INPR | 2019-02-07 | COMP |  | INPR | 2019-04-17 | COMP | Rule 15/16 | 68 | 140 |  | 216 |  |  | 470
2189 | 2017-06-02 | 2017-10-06 | 2018-02-25 | 2018-05-31 | COMP | 2018-08-23 | COMP | 2018-09-21 | COMP | 2019-01-02 | COMP | 2019-02-08 | COMP | Rule 15/16 | 89 | 94 | 60 | 21 | 69 | 27 | 423
2439 | 2017-06-02 | 2017-11-30 | 2018-03-01 | 2018-02-14 | COMP | 2018-05-11 | COMP | 2018-05-11 | COMP | 2020-02-29 | INPR | 2019-10-24 | COMP | Rule 16 | 125 | 62 | 62 | 1 |  |  | 603
2816 | 2017-06-02 | 2018-02-07 | 2018-09-03 | 2018-09-03 | COMP | 2018-10-30 | COMP | 2018-12-11 | COMP | 2019-02-13 | COMP | 2019-04-16 | COMP | Rule 16 | 171 | 145 | 41 | 28 | 44 | 44 | 469
3474 | 2017-06-02 | 2018-05-03 | 2018-09-22 | 2018-07-17 | COMP | 2019-10-21 | COMP | 2019-12-09 | COMP | 2020-01-14 | COMP | 2020-02-07 | COMP | Other | 231 | 99 | 319 | 33 | 25 | 18 | 673
4584 | 2017-06-02 | 2018-02-06 | 2018-05-08 | 2018-05-08 | COMP | 2018-05-22 | COMP | 2019-02-28 | COMP | 2019-02-12 | COMP | 2019-03-30 | COMP | Rule 16 | 170 | 65 | 11 | 193 | 0 | 22 | 457
39153 | 2017-06-02 | 2022-10-03 | 2023-02-14 | 2023-02-14 | COMP | 2023-03-17 | NOTN | 2023-04-12 | COMP |  | INPR | 2023-06-29 | COMP | Other | 1342 | 91 |  | 41 |  |  | 1526
2347 | 2017-06-04 | 2017-11-08 | 2018-07-27 | 2018-07-27 | COMP | 2018-09-04 | COMP | 2018-09-27 | COMP | 2019-06-29 | INPR | 2019-02-18 | COMP | Rule 16 | 111 | 179 | 27 | 18 |  |  | 427
1561 | 2017-06-05 | 2017-06-22 | 2017-09-18 | 2017-09-18 | COMP | 2017-10-10 | COMP | 2017-10-10 | COMP | 2019-03-26 | COMP | 2019-05-08 | COMP | Rule 16 | 14 | 61 | 17 | 1 | 364 | 32 | 484
1784 | 2017-06-05 | 2017-07-25 | 2017-11-01 | 2017-11-01 | COMP | 2018-02-23 | COMP | 2018-05-31 | COMP | 2019-07-21 | INPR | 2019-04-11 | COMP | Rule 16 | 36 | 71 | 76 | 69 |  |  | 465
1825 | 2017-06-05 | 2017-08-03 | 2017-09-17 | 2017-09-17 | COMP | 2018-05-08 | COMP | 2019-01-31 | COMP |  |  | 2019-05-18 | COMP | Rule 16 | 43 | 31 | 160 | 184 |  |  | 491
1937 | 2017-06-05 | 2017-08-23 | 2017-09-28 | 2017-09-28 | COMP | 2017-11-03 | COMP | 2018-09-12 | COMP | 2018-02-01 | NOTN | 2019-01-31 | COMP | Rule 15/16 | 57 | 26 | 27 | 214 |  |  | 416
2092 | 2017-06-05 | 2017-09-22 | 2018-07-11 | 2019-10-17 | COMP | 2019-11-18 | COMP | 2020-03-03 | COMP | 2020-02-01 | COMP | 2020-04-17 | COMP | Rule 15/16 | 78 | 200 | 22 | 71 | 0 | 34 | 721
2431 | 2017-06-05 | 2017-11-28 | 2018-02-20 | 2018-02-20 | COMP | 2018-05-16 | COMP | 2020-03-20 | COMP | 2020-08-04 | COMP | 2020-10-09 | COMP | Rule 15/16 | 122 | 57 | 62 | 463 | 97 | 48 | 844
2615 | 2017-06-05 | 2018-01-09 | 2018-11-27 | 2018-11-27 | COMP | 2019-08-14 | COMP | 2019-08-15 | COMP | 2019-08-14 | COMP | 2019-09-23 | COMP | Rule 15/16 | 150 | 223 | 181 | 2 | 0 | 27 | 579
4428 | 2017-06-05 | 2017-12-05 | 2018-01-19 | 2018-01-19 | COMP | 2018-06-21 | COMP | 2019-06-27 | COMP | 2019-07-17 | COMP | 2019-09-04 | COMP | Rule 15/16 | 127 | 31 | 108 | 256 | 14 | 35 | 566
4457 | 2017-06-05 | 2017-12-14 | 2018-09-13 | 2018-09-13 | COMP | 2018-11-02 | COMP | 2019-01-16 | COMP | 2019-01-15 | COMP | 2019-04-03 | COMP | Rule 15/16 | 134 | 189 | 37 | 49 | 0 | 54 | 459
4523 | 2017-06-05 | 2018-01-22 | 2018-02-24 | 2018-02-24 | COMP | 2018-05-01 | COMP | 2019-01-04 | COMP | 2019-07-01 | COMP | 2019-07-23 | COMP | Rule 15/16 | 158 | 24 | 47 | 171 | 124 | 16 | 536
5288 | 2017-06-05 | 2018-05-17 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-11 | COMP | 2019-02-05 | COMP | 2019-04-22 | COMP | 2019-05-21 | COMP | Other | 240 | 120 | 45 | 17 | 54 | 22 | 493
18084 | 2017-06-05 | 2020-03-10 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-07 | COMP | 2020-11-17 | COMP | 2021-02-10 | COMP | 2021-05-18 | COMP | Rule 16 | 693 | 89 | 20 | 71 | 57 | 69 | 994
18256 | 2017-06-05 | 2020-03-18 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-17 | COMP | 2020-04-19 | COMP | 2020-04-17 | COMP | 2020-06-03 | COMP | Rule 16 | 699 | 13 | 11 | 1 | 0 | 32 | 753
1463 | 2017-06-06 | 2017-06-06 | 2017-08-02 | 2017-08-02 | COMP | 2017-06-06 | NOTN | 2017-08-02 | COMP | 2017-06-06 | COMP | 2022-07-04 | COMP | Other | 1 | 41 |  | 1 | 0 | 1236 | 1276
1636 | 2017-06-06 | 2017-07-07 | 2020-05-22 | 2020-05-22 | COMP | 2019-08-17 | NOTN | 2020-07-31 | COMP | 2020-03-11 | COMP | 2021-03-23 | COMP | Other | 23 | 723 |  | 50 | 0 | 160 | 953
2065 | 2017-06-06 | 2017-09-16 | 2018-02-05 | 2018-02-05 | COMP | 2018-02-28 | COMP | 2018-05-16 | COMP | 2019-03-05 | COMP | 2019-03-27 | COMP | Rule 16 | 72 | 95 | 17 | 56 | 200 | 17 | 453
2157 | 2017-06-06 | 2017-10-02 | 2018-05-29 | 2018-05-29 | COMP | 2018-08-30 | COMP | 2018-11-30 | COMP | 2019-02-07 | COMP | 2019-05-31 | COMP | Rule 16 | 83 | 164 | 67 | 63 | 47 | 80 | 499
3468 | 2017-06-06 | 2018-05-01 | 2018-12-08 | 2018-12-08 | COMP | 2019-02-22 | COMP | 2019-10-19 | REQD | 2019-10-19 | REQD | 2019-06-25 | COMP | Rule 16 | 227 | 153 | 51 |  |  |  | 516
4558 | 2017-06-06 | 2018-01-29 | 2018-05-09 | 2019-01-18 | COMP | 2019-03-08 | COMP | 2019-04-03 | COMP | 2019-11-24 | INPR | 2019-05-09 | COMP | Rule 16 | 162 | 72 | 34 | 19 |  |  | 484
1549 | 2017-06-07 | 2017-06-21 | 2018-07-27 | 2020-01-24 | COMP | 2020-05-13 | COMP | 2020-05-21 | COMP | 2020-05-26 | COMP | 2020-07-06 | COMP | Rule 16 | 11 | 277 | 78 | 7 | 3 | 30 | 774
1847 | 2017-06-07 | 2017-08-08 | 2017-10-23 | 2020-06-15 | COMP | 2020-08-13 | COMP | 2020-08-27 | COMP | 2020-11-02 | COMP | 2020-11-25 | COMP | Rule 15/16 | 44 | 54 | 44 | 11 | 47 | 17 | 874
1934 | 2017-06-07 | 2017-08-23 | 2017-11-30 | 2017-11-30 | COMP | 2018-01-17 | COMP | 2018-10-04 | COMP | 2018-12-07 | COMP | 2019-01-30 | COMP | Rule 16 | 55 | 68 | 32 | 183 | 44 | 36 | 413
2087 | 2017-06-07 | 2017-09-21 | 2017-11-11 | 2019-05-08 | COMP | 2019-08-01 | COMP | 2019-08-14 | COMP | 2019-08-06 | COMP | 2019-09-05 | COMP | Rule 16 | 75 | 36 | 60 | 10 | 0 | 16 | 565
2175 | 2017-06-07 | 2017-10-05 | 2018-04-18 | 2018-04-18 | COMP | 2018-07-13 | COMP | 2018-07-13 | COMP | 2019-09-26 | COMP | 2019-11-19 | COMP | Rule 16 | 85 | 133 | 61 | 1 | 304 | 38 | 617
2392 | 2017-06-07 | 2017-11-16 | 2018-05-07 | 2018-05-07 | COMP | 2019-02-01 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-03-29 | COMP | Rule 15/16 | 114 | 117 | 186 | 2 | 1 | 39 | 454
2689 | 2017-06-07 | 2018-01-18 | 2018-02-15 | 2018-11-17 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2020-01-18 | INPR | 2019-09-24 | COMP | Rule 16 | 154 | 21 | 200 | 1 |  |  | 578
1662 | 2017-06-08 | 2017-07-13 | 2017-11-17 | 2017-11-17 | COMP | 2017-12-11 | COMP | 2017-12-11 | COMP |  | INPR | 2019-06-12 | COMP | Rule 16 | 25 | 90 | 15 | 1 |  |  | 505
1852 | 2017-06-08 | 2017-08-09 | 2017-10-19 | 2017-10-19 | COMP | 2018-06-04 | COMP | 2018-09-12 | COMP | 2019-03-19 | COMP | 2019-08-01 | COMP | Rule 16 | 44 | 51 | 155 | 71 | 128 | 96 | 540
2020 | 2017-06-08 | 2017-09-07 | 2017-11-05 | 2018-01-29 | COMP | 2018-03-26 | COMP | 2018-05-23 | COMP | 2018-06-21 | COMP | 2021-02-24 | COMP | Rule 16 | 64 | 42 | 40 | 43 | 21 | 672 | 932
2079 | 2017-06-08 | 2017-09-20 | 2018-03-13 | 2018-03-13 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-12-04 | COMP | 2019-12-23 | COMP | Rule 16 | 73 | 118 | 433 | 1 | 4 | 14 | 638
3165 | 2017-06-08 | 2018-03-15 | 2020-01-29 | 2020-01-29 | COMP | 2020-04-28 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-06-11 | COMP | Rule 16 | 192 | 471 | 64 | 10 | 1 | 23 | 756
3434 | 2017-06-08 | 2018-04-25 | 2018-08-13 | 2018-08-13 | COMP | 2019-01-30 | COMP | 2019-02-13 | COMP | 2020-01-18 | INPR | 2019-08-27 | COMP | Rule 16 | 221 | 77 | 116 | 11 |  |  | 558
4655 | 2017-06-08 | 2018-02-27 | 2018-09-05 | 2018-09-05 | COMP | 2018-12-27 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-06-27 | COMP | Rule 15/16 | 180 | 134 | 78 | 100 | 1 | 28 | 516
1640 | 2017-06-09 | 2017-07-08 | 2018-08-06 | 2018-08-06 | COMP | 2020-03-02 | COMP | 2020-03-03 | COMP | 2020-08-05 | COMP | 2020-08-03 | COMP | Rule 16 | 20 | 271 | 393 | 2 | 111 |  | 792
1641 | 2017-06-09 | 2017-07-08 | 2017-12-03 | 2017-12-03 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-08-05 | COMP | 2020-08-19 | COMP | Rule 16 | 20 | 101 | 489 | 1 | 185 | 11 | 804
1798 | 2017-06-09 | 2017-07-28 | 2018-01-25 | 2019-09-05 | COMP | 2019-09-26 | COMP | 2022-01-21 | COMP | 2022-01-04 | COMP | 2022-02-26 | COMP | Rule 16 | 35 | 123 | 16 | 584 | 0 | 25 | 1185
1921 | 2017-06-09 | 2017-08-21 | 2018-01-05 | 2018-01-05 | COMP | 2018-04-27 | COMP | 2018-04-27 | COMP | 2019-03-28 | COMP | 2019-05-08 | COMP | Rule 15/16 | 51 | 94 | 79 | 1 | 230 | 30 | 480
4509 | 2017-06-09 | 2018-01-17 | 2018-06-25 | 2018-06-25 | COMP | 2019-04-01 | COMP | 2019-04-04 | COMP | 2019-04-08 | COMP | 2019-06-27 | COMP | Rule 15/16 | 151 | 112 | 192 | 4 | 3 | 58 | 515
5810 | 2017-06-10 | 2018-07-05 | 2018-10-17 | 2018-10-17 | COMP | 2018-10-29 | COMP | 2018-11-08 | NOTN | 2018-11-08 | COMP | 2019-01-03 | COMP | Rule 16 | 268 | 74 | 9 |  |  |  | 392
13666 | 2017-06-10 | 2019-08-05 | 2019-10-25 | 2019-10-25 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-01-21 | COMP | 2020-02-06 | COMP | Rule 16 | 540 | 59 | 12 | 1 | 46 | 13 | 666
1621 | 2017-06-12 | 2017-07-06 | 2017-09-11 | 2017-09-11 | COMP | 2018-03-21 | COMP | 2018-03-21 | COMP | 2019-06-29 | INPR | 2019-02-06 | COMP | Rule 16 | 18 | 47 | 131 | 1 |  |  | 415
1884 | 2017-06-12 | 2017-08-15 | 2017-11-08 | 2017-11-08 | COMP | 2017-12-15 | COMP | 2017-12-19 | COMP | 2019-01-04 | COMP | 2019-01-28 | COMP | Rule 16 | 46 | 61 | 25 | 3 | 262 | 16 | 408
2650 | 2017-06-12 | 2018-01-12 | 2018-04-04 | 2018-04-04 | COMP | 2018-07-03 | COMP | 2018-07-03 | COMP | 2019-08-28 | COMP | 2019-09-21 | COMP | Rule 16 | 148 | 57 | 64 | 1 | 291 | 17 | 573
4459 | 2017-06-12 | 2017-12-14 | 2018-05-31 | 2018-05-31 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-12-13 | COMP | 2020-01-24 | COMP | Rule 16 | 129 | 116 | 145 | 1 | 243 | 28 | 657
1512 | 2017-06-13 | 2017-06-14 | 2018-12-08 | 2018-12-08 | COMP | 2019-10-08 | COMP | 2019-10-11 | COMP | 2020-10-14 | COMP | 2020-11-05 | COMP | Rule 15/16 | 2 | 373 | 210 | 4 | 255 | 17 | 857
1968 | 2017-06-13 | 2017-08-29 | 2017-10-19 | 2018-11-17 | COMP | 2018-12-06 | COMP | 2018-02-21 | COMP | 2019-12-09 | COMP | 2020-01-08 | COMP | Rule 15/16 | 55 | 37 | 12 |  | 453 | 21 | 645
2023 | 2017-06-13 | 2017-09-08 | 2019-05-31 | 2019-05-31 | COMP | 2019-07-19 | COMP | 2019-07-25 | COMP | 2020-06-16 | COMP | 2020-07-17 | COMP | Rule 15/16 | 62 | 433 | 35 | 5 | 225 | 24 | 779
2072 | 2017-06-13 | 2017-09-18 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-01 | COMP | 2019-05-01 | COMP | 2019-04-01 | COMP | 2019-05-23 | COMP | Rule 16 | 68 | 366 | 19 | 23 | 0 | 17 | 489
2106 | 2017-06-13 | 2017-09-25 | 2018-02-11 | 2018-02-11 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-06-16 | COMP | 2020-07-08 | COMP | Rule 16 | 73 | 94 | 534 | 1 | 57 | 17 | 772
2467 | 2017-06-13 | 2017-12-05 | 2018-08-04 | 2018-08-04 | COMP | 2018-08-14 | COMP | 2018-12-10 | COMP | 2019-01-06 | COMP | 2019-04-16 | COMP | Rule 16 | 121 | 168 | 7 | 81 | 18 | 70 | 462
4377 | 2017-06-13 | 2017-11-03 | 2018-02-14 | 2019-11-05 | COMP | 2020-08-25 | COMP | 2020-09-21 | COMP | 2020-10-12 | COMP | 2020-11-20 | COMP | Rule 15/16 | 102 | 68 | 203 | 19 | 16 | 29 | 867
4626 | 2017-06-13 | 2018-02-20 | 2018-05-08 | 2018-05-08 | COMP | 2019-05-22 | COMP | 2019-06-03 | COMP | 2019-06-18 | COMP | 2019-08-24 | COMP | Rule 16 | 172 | 56 | 262 | 8 | 12 | 48 | 553
26678 | 2017-06-13 | 2021-03-30 | 2021-05-22 | 2021-05-22 | COMP | 2021-07-21 | NOTN | 2021-10-05 | COMP | 2021-09-14 | COMP | 2021-10-02 | COMP | Other | 953 | 39 |  | 94 | 0 |  | 1083
1601 | 2017-06-14 | 2017-06-29 | 2018-02-14 | 2018-02-14 | COMP | 2019-05-22 | COMP | 2019-05-29 | COMP | 2019-05-23 | COMP | 2019-07-11 | COMP | Rule 16 | 12 | 157 | 320 | 5 | 0 | 31 | 521
1822 | 2017-06-14 | 2017-08-03 | 2017-10-12 | 2018-03-16 | COMP | 2019-01-07 | COMP | 2019-02-11 | COMP | 2019-02-12 | COMP | 2019-03-11 | COMP | Rule 16 | 36 | 50 | 204 | 25 | 2 | 19 | 435
1890 | 2017-06-14 | 2017-08-16 | 2017-11-20 | 2017-11-20 | COMP | 2018-06-05 | COMP | 2018-06-25 | COMP | 2019-03-21 | COMP | 2019-04-29 | COMP | Rule 16 | 45 | 67 | 135 | 15 | 185 | 28 | 470
1911 | 2017-06-14 | 2017-08-21 | 2018-05-19 | 2018-05-19 | COMP | 2018-07-03 | COMP | 2018-07-12 | COMP | 2019-09-20 | COMP | 2019-10-16 | COMP | Rule 15/16 | 48 | 187 | 31 | 7 | 301 | 19 | 589
1946 | 2017-06-14 | 2017-08-24 | 2017-11-02 | 2017-11-02 | COMP | 2017-11-17 | COMP | 2018-09-24 | COMP | 2018-09-26 | COMP | 2019-05-07 | COMP | Rule 16 | 51 | 50 | 11 | 213 | 3 | 153 | 476
2570 | 2017-06-14 | 2017-12-28 | 2019-12-09 | 2019-12-09 | COMP | 2020-03-19 | COMP | 2020-09-02 | COMP | 2020-10-21 | COMP | 2020-12-16 | COMP | Rule 15/16 | 136 | 489 | 70 | 119 | 35 | 38 | 882
2571 | 2017-06-14 | 2017-12-28 | 2018-05-01 | 2018-05-01 | COMP | 2019-11-07 | COMP | 2020-11-19 | COMP | 2020-10-21 | COMP | 2020-12-15 | COMP | Rule 15/16 | 136 | 86 | 385 | 261 | 0 | 17 | 881
1632 | 2017-06-15 | 2017-07-06 | 2017-10-25 | 2017-10-25 | COMP | 2018-03-22 | COMP | 2018-06-19 | COMP | 2018-12-12 | COMP | 2019-03-12 | COMP | Rule 15/16 | 15 | 79 | 100 | 63 | 122 | 61 | 435
1633 | 2017-06-15 | 2017-07-07 | 2017-10-25 | 2017-10-25 | COMP | 2018-03-10 | COMP | 2018-06-19 | COMP | 2019-06-29 | INPR | 2019-03-12 | COMP | Rule 15/16 | 16 | 78 | 91 | 71 |  |  | 435
1772 | 2017-06-15 | 2017-07-24 | 2018-02-07 | 2018-05-01 | COMP | 2018-10-01 | COMP | 2018-10-15 | COMP | 2018-12-27 | COMP | 2019-03-12 | COMP | Rule 15/16 | 27 | 136 | 107 | 11 | 50 | 51 | 435
1980 | 2017-06-15 | 2017-09-01 | 2018-01-18 | 2018-01-18 | COMP | 2018-03-06 | COMP | 2018-04-18 | COMP | 2018-03-29 | COMP | 2022-06-10 | COMP | Rule 16 | 56 | 93 | 33 | 32 | 0 | 1045 | 1255
2104 | 2017-06-15 | 2017-09-25 | 2018-12-09 | 2019-07-24 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-03-10 | COMP | 2020-06-25 | COMP | Rule 15/16 | 71 | 302 | 135 | 1 | 23 | 77 | 761
2378 | 2017-06-15 | 2017-11-14 | 2018-08-01 | 2018-08-01 | COMP | 2018-08-02 | COMP | 2018-08-02 | COMP | 2018-12-10 | COMP | 2019-01-15 | COMP | Rule 16 | 106 | 179 | 2 | 1 | 89 | 25 | 397
2755 | 2017-06-15 | 2018-01-26 | 2018-05-08 | 2018-05-08 | COMP | 2018-08-09 | COMP | 2018-07-26 | COMP | 2019-01-03 | COMP | 2019-02-19 | COMP | Rule 16 | 154 | 72 | 66 |  | 110 | 32 | 420
3017 | 2017-06-15 | 2018-02-27 | 2018-03-15 | 2018-03-15 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-04-20 | INPR | 2019-01-24 | COMP | Rule 16 | 175 | 13 | 201 | 1 |  |  | 403
1540 | 2017-06-16 | 2017-06-20 | 2017-08-21 | 2018-08-21 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-08-12 | COMP | 2019-09-12 | COMP | Rule 16 | 3 | 44 | 182 | 1 | 64 | 23 | 563
1568 | 2017-06-16 | 2017-06-24 | 2018-08-08 | 2018-08-08 | COMP | 2021-02-11 | COMP | 2021-05-07 | COMP | 2023-02-01 | COMP | 2023-04-11 | COMP | Rule 15/16 | 6 | 282 | 631 | 61 | 436 | 49 | 1461
1811 | 2017-06-16 | 2017-08-01 | 2018-06-13 | 2018-06-13 | COMP | 2019-10-24 | COMP | 2019-11-13 | INPR | 2019-12-10 | COMP | 2019-12-11 | COMP | Rule 15/16 | 32 | 218 | 345 |  |  |  | 624
1821 | 2017-06-16 | 2017-08-02 | 2017-09-05 | 2017-09-05 | COMP | 2017-09-25 | COMP | 2019-05-08 | COMP |  |  | 2019-08-17 | COMP | Rule 16 | 33 | 24 | 15 | 406 |  |  | 545
1876 | 2017-06-16 | 2017-08-11 | 2018-05-28 | 2018-05-28 | COMP | 2018-06-01 | COMP | 2018-06-01 | COMP | 2019-02-13 | COMP | 2019-05-17 | COMP | Rule 16 | 40 | 198 | 4 | 1 | 176 | 67 | 482
1969 | 2017-06-16 | 2017-08-29 | 2018-07-29 | 2018-09-13 | COMP | 2018-10-22 | COMP | 2019-06-11 | INPR | 2019-06-11 | COMP | 2019-09-24 | COMP | Rule 16 | 52 | 229 | 28 |  |  |  | 571
2167 | 2017-06-16 | 2017-10-03 | 2017-12-05 | 2017-12-05 | COMP | 2019-07-24 | NOTN | 2019-07-24 | COMP | 2019-08-13 | COMP | 2019-09-12 | COMP | Rule 16 | 76 | 43 |  | 411 | 15 | 22 | 563
2529 | 2017-06-16 | 2017-12-15 | 2018-07-09 | 2018-07-09 | COMP | 2018-12-04 | COMP | 2019-03-06 | COMP | 2019-09-30 | COMP | 2019-12-04 | COMP | Rule 15/16 | 126 | 141 | 103 | 63 | 146 | 45 | 619
1979 | 2017-06-18 | 2017-08-31 | 2017-09-02 | 2017-09-02 | COMP | 2017-09-25 | COMP | 2017-09-25 | COMP | 2019-08-31 | INPR | 2019-04-30 | COMP | Rule 16 | 53 | 2 | 15 | 1 |  |  | 468
1634 | 2017-06-19 | 2017-07-07 | 2018-01-25 | 2018-01-25 | COMP | 2018-04-24 | COMP | 2018-04-25 | COMP | 2017-08-02 | COMP | 2019-06-18 | COMP | Rule 15/16 | 14 | 138 | 63 | 2 | 0 | 289 | 502
1836 | 2017-06-19 | 2017-08-07 | 2017-09-15 | 2017-09-15 | COMP | 2018-03-06 | COMP | 2018-03-06 | COMP | 2019-05-09 | COMP | 2019-07-30 | COMP | Rule 16 | 35 | 29 | 116 | 1 | 298 | 57 | 531
1845 | 2017-06-19 | 2017-08-08 | 2017-09-26 | 2017-09-26 | COMP | 2018-08-01 | COMP | 2018-01-16 | COMP | 2018-12-17 | COMP | 2019-02-05 | COMP | Rule 16 | 36 | 35 | 213 |  | 233 | 34 | 409
3485 | 2017-06-19 | 2018-05-07 | 2018-08-17 | 2018-08-16 | COMP | 2019-01-24 | COMP | 2019-05-22 | COMP | 2019-10-19 | INPR | 2019-07-11 | COMP | Rule 15/16 | 222 | 73 | 109 | 84 |  |  | 518
4415 | 2017-06-19 | 2017-11-28 | 2017-12-22 | 2018-03-01 | COMP | 2018-03-14 | COMP | 2018-02-26 | INPR | 2018-05-14 | COMP | 2020-12-11 | COMP | Rule 16 | 112 | 19 | 10 |  |  |  | 876
4449 | 2017-06-19 | 2017-12-12 | 2018-07-11 | 2018-07-11 | COMP | 2018-07-12 | NOTN | 2018-07-12 | COMP | 2018-07-12 | COMP | 2019-05-06 | COMP | Other | 122 | 146 |  | 2 | 1 | 205 | 472
1577 | 2017-06-20 | 2017-06-26 | 2017-11-06 | 2017-11-06 | COMP | 2019-05-09 | COMP | 2019-05-15 | COMP | 2020-09-01 | COMP | 2020-09-21 | COMP | Rule 15/16 | 5 | 94 | 377 | 5 | 329 | 14 | 819
1837 | 2017-06-20 | 2017-08-07 | 2017-10-19 | 2017-10-19 | COMP | 2018-03-07 | COMP | 2018-03-14 | COMP |  | INPR | 2019-06-13 | COMP | Other | 34 | 53 | 93 | 6 |  |  | 498
2021 | 2017-06-20 | 2017-09-07 | 2018-08-15 | 2018-08-15 | COMP | 2019-08-23 | COMP | 2019-08-29 | COMP | 2020-08-14 | COMP | 2020-09-26 | COMP | Rule 16 | 56 | 236 | 258 | 5 | 243 | 30 | 823
2029 | 2017-06-20 | 2017-09-08 | 2017-11-20 | 2017-11-20 | COMP | 2017-12-21 | COMP | 2017-12-27 | COMP | 2018-03-06 | COMP | 2022-07-06 | COMP | Rule 16 | 57 | 51 | 22 | 4 | 47 | 1092 | 1268
2840 | 2017-06-20 | 2018-02-06 | 2018-06-28 | 2018-06-28 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2020-01-17 | COMP | 2020-02-11 | COMP | Rule 15/16 | 158 | 101 | 259 | 1 | 132 | 17 | 663
4501 | 2017-06-20 | 2018-01-11 | 2018-04-11 | 2018-04-11 | COMP | 2018-05-31 | COMP | 2019-04-29 | COMP | 2019-04-26 | COMP | 2019-06-05 | COMP | Rule 16 | 141 | 63 | 36 | 229 | 0 | 27 | 492
5066 | 2017-06-20 | 2018-04-28 | 2018-08-29 | 2018-08-29 | COMP | 2018-10-05 | COMP | 2018-11-28 | COMP | 2018-10-17 | COMP | 2019-01-12 | COMP | Rule 15/16 | 215 | 86 | 27 | 36 | 0 | 31 | 392
6128 | 2017-06-20 | 2018-07-27 | 2018-08-07 | 2018-08-07 | COMP | 2019-02-07 | COMP | 2019-03-29 | COMP | 2024-02-03 | INPR | 2019-08-28 | COMP | Rule 16 | 278 | 8 | 126 | 36 |  |  | 551
9214 | 2017-06-20 | 2019-01-22 | 2019-09-10 | 2019-09-10 | COMP | 2020-03-03 | COMP | 2020-05-22 | COMP |  | INPR | 2021-01-27 | COMP | Rule 15/16 | 398 | 162 | 119 | 59 |  |  | 905
1553 | 2017-06-21 | 2017-06-22 | 2017-07-24 | 2019-03-28 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2020-07-21 | COMP | 2020-07-30 | COMP | Rule 16 | 2 | 22 | 86 | 1 | 248 | 8 | 782
1671 | 2017-06-21 | 2017-07-13 | 2017-09-11 | 2017-09-11 | COMP | 2018-02-01 | COMP | 2018-02-01 | COMP | 2018-11-19 | COMP | 2019-01-04 | COMP | Rule 16 | 16 | 42 | 98 | 1 | 203 | 31 | 386
1701 | 2017-06-21 | 2017-07-17 | 2017-10-04 | 2017-10-04 | COMP | 2017-10-05 | COMP | 2017-10-07 | COMP | 2019-05-03 | COMP | 2019-05-28 | COMP | Rule 16 | 18 | 57 | 2 | 2 | 393 | 17 | 485
1886 | 2017-06-21 | 2017-08-15 | 2018-04-23 | 2018-04-23 | COMP | 2018-06-12 | COMP | 2018-06-13 | COMP | 2019-01-09 | COMP | 2019-03-18 | COMP | Rule 16 | 39 | 172 | 36 | 2 | 144 | 47 | 435
1948 | 2017-06-21 | 2017-08-24 | 2017-10-03 | 2017-10-03 | COMP | 2017-10-26 | COMP | 2017-10-26 | COMP | 2019-02-06 | COMP | 2019-02-28 | COMP | Rule 16 | 46 | 28 | 18 | 1 | 319 | 16 | 423
1999 | 2017-06-21 | 2017-09-05 | 2018-04-13 |  | REQD | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-08-01 | COMP | 2019-12-13 | COMP | Rule 15/16 | 53 |  |  |  | 76 | 93 | 623
2000 | 2017-06-21 | 2017-09-05 | 2018-03-11 | 2018-03-11 | COMP | 2018-09-10 | COMP | 2019-02-27 | COMP | 2019-02-26 | COMP | 2019-05-31 | COMP | Rule 15/16 | 53 | 127 | 128 | 116 | 0 | 67 | 488
2001 | 2017-06-21 | 2017-09-05 | 2018-03-11 | 2019-05-31 | COMP | 2019-06-26 | COMP | 2019-07-17 | COMP | 2019-08-01 | COMP | 2019-12-13 | COMP | Rule 15/16 | 53 | 127 | 19 | 15 | 12 | 93 | 623
2172 | 2017-06-21 | 2017-10-04 | 2017-11-17 | 2017-11-17 | COMP | 2017-11-20 | COMP | 2017-11-21 | COMP | 2017-11-22 | COMP | 2021-07-01 | COMP | Rule 16 | 74 | 32 | 2 | 2 | 2 | 906 | 1013
2254 | 2017-06-21 | 2017-10-24 | 2018-07-03 | 2018-07-03 | COMP | 2019-02-13 | COMP | 2019-05-07 | COMP | 2019-04-09 | COMP | 2019-06-25 | COMP | Rule 16 | 88 | 173 | 154 | 59 | 0 | 35 | 505
4413 | 2017-06-21 | 2017-11-28 | 2018-01-09 | 2018-01-09 | COMP | 2018-05-04 | COMP | 2018-05-04 | COMP | 2019-01-12 | COMP | 2019-02-22 | COMP | Rule 16 | 110 | 29 | 82 | 1 | 173 | 28 | 419
1575 | 2017-06-22 | 2017-06-26 | 2018-01-16 | 2018-01-16 | COMP | 2018-04-23 | COMP | 2018-04-23 | COMP | 2018-06-27 | COMP | 2019-08-30 | COMP | Rule 16 | 3 | 139 | 69 | 1 | 47 | 297 | 551
1588 | 2017-06-22 | 2017-06-28 | 2018-01-08 | 2018-01-08 | COMP | 2018-02-28 | COMP | 2018-03-01 | COMP | 2018-04-16 | COMP | 2019-07-12 | COMP | Rule 15/16 | 5 | 132 | 36 | 2 | 33 | 313 | 516
1706 | 2017-06-22 | 2017-07-18 | 2018-10-08 | 2018-10-08 | COMP | 2019-03-05 | COMP | 2019-07-03 | COMP | 2019-12-10 | COMP | 2019-09-03 | COMP | Rule 16 | 18 | 309 | 100 | 86 | 110 |  | 552
1707 | 2017-06-22 | 2017-07-18 | 2018-12-17 | 2018-12-13 | COMP | 2019-02-21 | COMP | 2019-09-05 | COMP | 2019-12-10 | COMP | 2019-10-14 | COMP | Rule 16 | 18 | 356 | 47 | 138 | 66 |  | 581
1709 | 2017-06-22 | 2017-07-18 | 2018-10-08 | 2018-10-08 | COMP | 2019-03-05 | COMP | 2019-09-05 | COMP |  | INPR | 2019-09-18 | COMP | Rule 16 | 18 | 309 | 100 | 130 |  |  | 563
1710 | 2017-06-22 | 2017-07-18 | 2018-11-09 | 2018-11-06 | COMP | 2019-02-06 | COMP | 2019-04-22 | INPR | 2019-11-14 | COMP | 2019-06-06 | COMP | Rule 16 | 18 | 333 | 61 |  |  |  | 491
1712 | 2017-06-22 | 2017-07-18 | 2018-03-15 | 2018-03-15 | COMP | 2018-04-19 | COMP | 2018-08-21 | COMP | 2019-08-31 | INPR | 2019-03-11 | COMP | Rule 16 | 18 | 165 | 26 | 87 |  |  | 429
1713 | 2017-06-22 | 2017-07-18 | 2018-03-22 | 2018-03-22 | COMP | 2018-05-11 | COMP | 2019-01-15 | COMP | 2023-12-02 | INPR | 2019-03-08 | COMP | Rule 16 | 18 | 170 | 37 | 170 |  |  | 428
1714 | 2017-06-22 | 2017-07-18 | 2019-05-15 | 2019-05-15 | COMP | 2019-07-22 | COMP | 2020-02-19 | COMP | 2020-02-26 | COMP | 2020-06-29 | COMP | Rule 16 | 18 | 459 | 47 | 145 | 6 | 88 | 758
1715 | 2017-06-22 | 2017-07-18 | 2018-11-29 | 2018-11-29 | COMP | 2019-02-11 | COMP | 2019-10-29 | COMP | 2019-11-12 | COMP | 2020-01-07 | COMP | Rule 16 | 18 | 344 | 50 | 183 | 10 | 37 | 637
1716 | 2017-06-22 | 2017-07-18 | 2018-11-29 | 2018-11-29 | COMP | 2019-02-22 | COMP | 2019-07-26 | COMP |  | INPR | 2019-08-14 | COMP | Rule 16 | 18 | 344 | 58 | 109 |  |  | 539
1717 | 2017-06-22 | 2017-07-18 | 2018-07-17 | 2018-07-17 | COMP | 2018-09-11 | COMP | 2019-04-03 | COMP | 2019-08-31 | INPR | 2019-04-09 | COMP | Rule 16 | 18 | 251 | 40 | 140 |  |  | 450
1718 | 2017-06-22 | 2017-07-18 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-29 | COMP | 2019-10-19 | REQD | 2019-10-19 | INPR | 2019-01-31 | COMP | Rule 16 | 18 | 251 | 32 |  |  |  | 403
1719 | 2017-06-22 | 2017-07-18 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-27 | COMP | 2019-03-26 | COMP | 2019-10-19 | INPR | 2019-04-16 | COMP | Rule 16 | 18 | 251 | 30 | 144 |  |  | 455
1720 | 2017-06-22 | 2017-07-18 | 2018-07-19 | 2018-07-19 | COMP | 2018-09-12 | COMP | 2019-03-26 | INPR | 2019-08-31 | REQD | 2019-04-17 | COMP | Rule 16 | 18 | 253 | 39 |  |  |  | 456
1721 | 2017-06-22 | 2017-07-18 | 2018-03-22 | 2018-03-22 | COMP | 2018-07-19 | COMP | 2018-10-24 | COMP |  | INPR | 2021-02-15 | COMP | Rule 16 | 18 | 170 | 84 | 69 |  |  | 915
1722 | 2017-06-22 | 2017-07-18 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-27 | COMP | 2018-09-27 | COMP | 2019-02-28 | COMP | 2019-04-08 | COMP | Rule 16 | 18 | 251 | 30 | 23 | 104 | 28 | 449
1723 | 2017-06-22 | 2017-07-18 | 2018-09-21 | 2018-09-21 | COMP | 2018-12-07 | COMP | 2018-12-11 | COMP | 2019-07-21 | INPR | 2019-01-14 | COMP | Rule 16 | 18 | 298 | 53 | 3 |  |  | 391
1724 | 2017-06-22 | 2017-07-18 | 2018-12-12 | 2018-12-05 | COMP | 2019-02-22 | COMP | 2020-04-03 | COMP | 2019-11-15 | COMP | 2020-06-26 | COMP | Rule 16 | 18 | 353 | 54 | 281 | 0 | 60 | 757
1725 | 2017-06-22 | 2017-07-18 | 2018-07-17 | 2018-07-17 | COMP | 2019-07-19 | COMP | 2023-11-11 | CANC | 2019-11-14 | COMP | 2019-04-22 | COMP | Rule 16 | 18 | 251 | 254 |  |  |  | 459
1727 | 2017-06-22 | 2017-07-18 | 2019-01-08 | 2019-01-08 | COMP | 2019-08-12 | COMP | 2020-09-29 | COMP | 2020-05-11 | COMP | 2020-12-04 | COMP | Rule 15/16 | 18 | 370 | 151 | 287 | 0 | 46 | 868
1733 | 2017-06-22 | 2017-07-18 | 2018-10-11 | 2018-09-25 | COMP | 2019-03-08 | COMP | 2019-03-13 | INPR | 2019-11-23 | REQD | 2019-06-05 | COMP | Rule 16 | 18 | 312 | 112 |  |  |  | 490
1734 | 2017-06-22 | 2017-07-18 | 2018-06-28 | 2018-06-28 | COMP | 2018-12-26 | COMP | 2019-10-11 | COMP | 2019-12-06 | COMP | 2020-01-30 | COMP | Rule 16 | 18 | 239 | 124 | 202 | 38 | 37 | 653
1740 | 2017-06-22 | 2017-07-19 | 2018-03-02 | 2018-07-10 | COMP | 2018-08-27 | COMP | 2019-03-07 | COMP | 2019-08-31 | INPR | 2019-04-12 | COMP | Rule 16 | 19 | 155 | 35 | 131 |  |  | 453
1741 | 2017-06-22 | 2017-07-19 | 2018-06-07 | 2018-06-07 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-08-31 | INPR | 2019-04-18 | COMP | Rule 16 | 19 | 223 | 220 | 1 |  |  | 457
1744 | 2017-06-22 | 2017-07-19 | 2019-03-14 | 2019-03-14 | COMP | 2019-05-02 | COMP | 2019-12-05 | COMP | 2019-12-06 | COMP | 2020-02-12 | COMP | Rule 15/16 | 19 | 414 | 36 | 150 | 2 | 46 | 662
1750 | 2017-06-22 | 2017-07-19 | 2018-10-11 | 2018-09-25 | COMP | 2019-09-17 | COMP | 2019-11-07 | COMP | 2019-12-10 | COMP | 2020-01-08 | COMP | Rule 16 | 19 | 311 | 246 | 38 | 21 | 20 | 638
1766 | 2017-06-22 | 2017-07-21 | 2018-08-20 | 2018-08-20 | COMP | 2019-03-29 | COMP | 2019-03-30 | COMP | 2020-09-06 | INPR | 2019-04-28 | COMP | Rule 15/16 | 21 | 272 | 152 | 1 |  |  | 463
1769 | 2017-06-22 | 2017-07-24 | 2018-03-29 | 2018-03-29 | COMP | 2018-04-24 | COMP | 2018-08-15 | COMP | 2023-12-02 | INPR | 2022-03-23 | COMP | Rule 16 | 22 | 171 | 19 | 80 |  |  | 1194
1777 | 2017-06-22 | 2017-07-24 | 2019-07-03 | 2019-07-03 | COMP | 2019-07-30 | COMP | 2019-09-17 | COMP | 2019-11-01 | COMP | 2019-10-18 | COMP | Rule 16 | 22 | 489 | 19 | 35 | 34 |  | 585
1827 | 2017-06-22 | 2017-08-03 | 2017-09-04 | 2017-09-04 | COMP | 2018-08-08 | COMP | 2018-10-19 | COMP | 2019-07-21 | INPR | 2019-01-09 | COMP | Rule 15/16 | 30 | 22 | 233 | 52 |  |  | 388
1853 | 2017-06-22 | 2017-08-10 | 2017-10-10 | 2017-10-10 | COMP | 2017-10-30 | COMP | 2017-11-03 | COMP | 2020-04-03 | COMP | 2020-04-04 | COMP | Rule 16 | 35 | 43 | 15 | 5 | 604 | 1 | 698
2003 | 2017-06-22 | 2017-09-06 | 2018-07-09 | 2018-07-09 | COMP | 2018-10-04 | COMP | 2018-12-21 | COMP | 2019-01-03 | COMP | 2019-03-19 | COMP | Rule 15/16 | 53 | 210 | 63 | 54 | 8 | 52 | 435
2037 | 2017-06-22 | 2017-09-09 | 2018-03-18 | 2018-03-18 | COMP | 2018-05-24 | COMP | 2018-05-24 | COMP | 2019-06-11 | COMP | 2019-06-20 | COMP | Rule 16 | 55 | 128 | 49 | 1 | 263 | 8 | 501
2058 | 2017-06-22 | 2017-09-15 | 2018-08-02 | 2018-08-02 | COMP | 2018-10-31 | COMP | 2018-11-09 | COMP | 2018-11-30 | COMP | 2019-02-19 | COMP | Rule 16 | 60 | 221 | 64 | 8 | 13 | 54 | 415
2123 | 2017-06-22 | 2017-09-27 | 2018-01-05 | 2018-01-05 | COMP | 2018-02-22 | COMP | 2019-01-30 | COMP | 2019-02-05 | COMP | 2019-04-04 | COMP | Rule 16 | 68 | 68 | 33 | 236 | 5 | 42 | 447
2224 | 2017-06-22 | 2017-10-18 | 2018-06-14 | 2018-06-14 | COMP | 2019-06-14 | COMP | 2020-04-06 | COMP | 2020-05-07 | COMP | 2020-07-08 | COMP | Rule 15/16 | 83 | 164 | 252 | 203 | 24 | 44 | 765
3091 | 2017-06-22 | 2018-03-06 | 2018-06-05 | 2018-06-05 | COMP | 2018-07-09 | COMP | 2018-11-28 | COMP | 2018-10-15 | COMP | 2019-01-14 | COMP | Rule 15/16 | 175 | 65 | 24 | 99 | 0 | 32 | 391
4083 | 2017-06-22 | 2019-01-16 | 2019-11-25 | 2019-11-25 | COMP | 2020-03-17 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-05-14 | COMP | Rule 16 | 393 | 218 | 76 | 23 | 1 | 21 | 727
4433 | 2017-06-22 | 2017-12-07 | 2018-01-30 | 2019-03-15 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-04-08 | COMP | 2019-06-19 | COMP | Rule 16 | 116 | 36 | 13 | 1 | 5 | 52 | 500
4698 | 2017-06-22 | 2018-03-15 | 2018-08-04 | 2018-12-07 | COMP | 2019-02-07 | COMP | 2019-04-25 | COMP | 2019-07-15 | COMP | 2019-08-12 | COMP | Rule 16 | 182 | 100 | 42 | 55 | 56 | 21 | 537
4877 | 2017-06-22 | 2018-04-07 | 2018-04-08 | 2018-04-08 | COMP | 2018-04-27 | COMP | 2018-04-27 | COMP | 2019-10-21 | INPR | 2019-06-25 | COMP | Rule 16 | 198 | 0 | 15 | 1 |  |  | 504
1730 | 2017-06-23 | 2017-07-18 | 2019-10-28 | 2019-10-28 | COMP | 2020-03-06 | COMP | 2020-03-28 | COMP | 2020-04-29 | COMP | 2020-05-13 | COMP | Rule 15/16 | 17 | 574 | 88 | 16 | 23 | 11 | 725
1746 | 2017-06-23 | 2017-07-19 | 2018-07-17 | 2018-07-17 | COMP | 2018-09-12 | COMP | 2019-05-09 | COMP | 2019-12-09 | COMP | 2020-03-03 | COMP | Rule 16 | 18 | 250 | 41 | 165 | 147 | 58 | 674
1788 | 2017-06-23 | 2017-07-26 | 2019-01-31 | 2019-01-31 | COMP | 2019-03-22 | COMP | 2019-05-07 | COMP | 2019-06-11 | NOTN | 2020-07-27 | COMP | Rule 16 | 23 | 380 | 36 | 33 |  |  | 777
1791 | 2017-06-23 | 2017-07-27 | 2017-09-07 | 2017-09-07 | COMP | 2019-06-18 | COMP | 2019-07-17 | COMP | 2020-02-18 | COMP | 2020-04-03 | COMP | Rule 16 | 24 | 30 | 446 | 21 | 147 | 34 | 697
2362 | 2017-06-23 | 2017-11-12 | 2018-09-13 | 2018-09-13 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-08-31 | INPR | 2019-05-14 | COMP | Rule 15/16 | 98 | 210 | 34 | 1 |  |  | 474
3776 | 2017-06-23 | 2018-07-10 | 2019-02-02 | 2019-02-02 | COMP | 2019-09-30 | COMP | 2020-03-03 | COMP | 2020-07-07 | COMP | 2020-07-31 | COMP | Rule 16 | 262 | 142 | 167 | 105 | 90 | 19 | 781
4155 | 2017-06-23 | 2019-04-17 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2020-01-08 | COMP | 2020-02-11 | COMP | Rule 16 | 455 | 52 | 25 | 1 | 108 | 24 | 660
4216 | 2017-06-23 | 2019-07-27 | 2019-09-26 | 2019-09-26 | COMP | 2020-02-25 | COMP | 2020-06-30 | COMP | 2020-02-26 | COMP | 2020-07-17 | COMP | Rule 16 | 525 | 43 | 102 | 90 | 0 | 14 | 771
4391 | 2017-06-23 | 2017-11-10 | 2018-10-01 | 2018-10-01 | COMP | 2019-03-12 | COMP | 2019-03-13 | COMP | 2019-03-07 | COMP | 2019-05-09 | COMP | Rule 16 | 98 | 222 | 110 | 2 | 0 | 42 | 471
11111 | 2017-06-23 | 2019-04-12 | 2019-08-02 | 2019-08-02 | COMP | 2019-09-05 | COMP | 2020-02-11 | COMP |  | INPR | 2020-03-08 | COMP | Rule 15/16 | 452 | 79 | 24 | 108 |  |  | 677
2032 | 2017-06-24 | 2017-09-09 | 2017-11-14 | 2017-11-14 | COMP | 2018-07-25 | COMP | 2018-07-31 | COMP | 2019-10-19 | INPR | 2019-06-19 | COMP | Rule 16 | 53 | 46 | 174 | 5 |  |  | 498
4506 | 2017-06-24 | 2018-01-19 | 2018-05-30 | 2018-06-07 | COMP | 2018-06-26 | COMP | 2018-10-09 | COMP | 2019-01-08 | COMP | 2019-02-11 | COMP | Rule 16 | 142 | 92 | 14 | 74 | 61 | 24 | 408
1663 | 2017-06-26 | 2017-07-13 | 2017-11-17 | 2017-11-17 | COMP | 2017-12-11 | COMP | 2018-07-12 | COMP | 2019-09-11 | COMP | 2019-10-16 | COMP | Rule 15/16 | 13 | 90 | 15 | 148 | 294 | 26 | 581
1708 | 2017-06-26 | 2017-07-18 | 2018-08-30 | 2018-08-30 | COMP | 2018-09-14 | COMP | 2019-03-16 | COMP | 2019-03-18 | COMP | 2019-05-01 | COMP | Rule 16 | 16 | 283 | 11 | 124 | 1 | 33 | 464
1732 | 2017-06-26 | 2017-07-18 | 2019-10-02 | 2019-10-02 | COMP | 2019-11-26 | COMP | 2019-12-10 | COMP | 2020-01-08 | COMP | 2020-02-05 | COMP | Rule 16 | 16 | 556 | 39 | 9 | 20 | 20 | 655
1738 | 2017-06-26 | 2017-07-19 | 2019-01-14 | 2019-01-14 | COMP | 2019-03-13 | COMP | 2019-04-25 | COMP | 2019-12-06 | COMP | 2019-06-07 | COMP | Rule 16 | 17 | 373 | 41 | 32 | 156 |  | 490
1739 | 2017-06-26 | 2017-07-19 | 2018-11-09 | 2018-11-05 | COMP | 2020-04-17 | COMP | 2020-08-19 | COMP | 2020-07-14 | COMP | 2020-10-08 | COMP | Rule 16 | 17 | 332 | 363 | 88 | 0 | 36 | 828
1743 | 2017-06-26 | 2017-07-19 | 2018-05-08 | 2018-05-08 | COMP | 2020-06-22 | COMP | 2019-05-01 | COMP | 2019-12-10 | COMP | 2019-07-01 | COMP | Rule 16 | 17 | 202 | 534 |  | 154 |  | 506
1745 | 2017-06-26 | 2017-07-19 | 2018-12-20 | 2018-12-20 | COMP | 2019-02-22 | COMP | 2019-08-26 | COMP | 2019-12-06 | COMP | 2019-10-15 | COMP | Rule 16 | 17 | 358 | 43 | 130 | 71 |  | 580
1856 | 2017-06-26 | 2017-08-10 | 2017-12-20 | 2017-12-20 | COMP | 2019-04-29 | COMP | 2019-05-02 | COMP | 2019-06-10 | COMP | 2019-07-16 | COMP | Rule 16 | 33 | 91 | 340 | 4 | 27 | 26 | 516
1967 | 2017-06-26 | 2017-08-29 | 2018-01-30 | 2018-01-30 | COMP | 2018-09-06 | COMP | 2018-09-06 | COMP | 2018-11-19 | COMP | 2019-01-02 | COMP | Rule 16 | 46 | 104 | 154 | 1 | 52 | 29 | 381
2215 | 2017-06-26 | 2017-10-13 | 2018-04-26 | 2018-04-26 | COMP | 2018-12-17 | COMP | 2018-12-20 | COMP | 2019-02-06 | COMP | 2019-03-13 | COMP | Rule 16 | 78 | 133 | 162 | 4 | 32 | 25 | 429
2263 | 2017-06-26 | 2017-10-25 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-13 | COMP | 2019-01-07 | COMP | 2019-02-04 | COMP | 2019-03-06 | COMP | Rule 15/16 | 86 | 255 | 10 | 36 | 20 | 22 | 424
2276 | 2017-06-26 | 2017-10-26 | 2017-10-29 | 2017-10-29 | COMP | 2017-12-01 | COMP | 2017-12-01 | COMP | 2020-05-20 | COMP | 2020-07-16 | COMP | Rule 16 | 87 | 2 | 22 | 1 | 620 | 41 | 769
2277 | 2017-06-26 | 2017-10-26 | 2018-03-03 | 2018-03-03 | COMP | 2019-01-11 | COMP | 2019-04-25 | COMP |  |  | 2019-06-01 | COMP | Rule 16 | 87 | 85 | 217 | 73 |  |  | 485
5207 | 2017-06-26 | 2018-05-09 | 2018-07-11 | 2018-07-11 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-02-05 | COMP | 2019-03-14 | COMP | Rule 16 | 219 | 44 | 131 | 1 | 13 | 27 | 430
7123 | 2017-06-26 | 2018-09-28 | 2019-01-15 | 2019-01-15 | COMP | 2019-03-11 | COMP | 2019-09-17 | COMP | 2019-12-11 | COMP | 2020-01-15 | COMP | Rule 16 | 318 | 73 | 38 | 134 | 59 | 24 | 641
1799 | 2017-06-27 | 2017-07-28 | 2018-03-24 | 2018-03-24 | COMP | 2018-09-28 | COMP | 2018-12-26 | COMP | 2018-12-03 | COMP | 2019-04-25 | COMP | Rule 15/16 | 23 | 163 | 132 | 60 | 0 | 84 | 459
1817 | 2017-06-27 | 2017-08-02 | 2017-09-25 | 2017-09-25 | COMP | 2021-11-01 | NOTN | 2021-11-01 | COMP | 2023-04-15 | INPR | 2019-01-09 | COMP | Rule 16 | 26 | 38 |  | 1032 |  |  | 385
1834 | 2017-06-27 | 2017-08-07 | 2017-11-10 | 2017-11-10 | COMP | 2017-12-06 | COMP | 2019-01-17 | COMP | 2019-01-10 | COMP | 2019-02-28 | COMP | Rule 16 | 29 | 68 | 16 | 280 | 0 | 29 | 419
2169 | 2017-06-27 | 2017-10-04 | 2018-03-01 | 2018-03-01 | COMP | 2018-09-25 | COMP | 2018-11-01 | COMP | 2019-06-13 | COMP | 2019-09-30 | COMP | Rule 16 | 70 | 100 | 146 | 28 | 153 | 76 | 568
2327 | 2017-06-27 | 2017-11-03 | 2019-10-29 | 2019-10-29 | COMP | 2019-12-06 | COMP | 2020-06-24 | COMP | 2022-06-18 | INPR | 2021-04-22 | COMP | Rule 16 | 92 | 498 | 26 | 139 |  |  | 960
2335 | 2017-06-27 | 2017-11-03 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-06 | COMP | 2021-01-07 | COMP | 2021-11-17 | COMP | 2022-06-14 | COMP | Rule 16 | 92 | 489 | 35 | 274 | 219 | 145 | 1249
2379 | 2017-06-27 | 2017-11-14 | 2018-01-11 | 2018-01-11 | COMP | 2018-06-20 | COMP | 2018-06-20 | COMP | 2019-11-23 | INPR | 2019-07-19 | COMP | Rule 15/16 | 98 | 39 | 112 | 1 |  |  | 518
2750 | 2017-06-27 | 2018-01-26 | 2018-06-18 | 2018-06-18 | COMP | 2018-11-19 | COMP | 2019-01-24 | COMP | 2021-02-27 | INPR | 2019-06-06 | COMP | Rule 16 | 146 | 100 | 108 | 44 |  |  | 488
3057 | 2017-06-27 | 2018-03-06 | 2018-05-08 | 2018-05-08 | COMP | 2018-10-23 | COMP | 2019-07-21 | REQD | 2019-02-23 | COMP | 2019-02-28 | COMP | Rule 15/16 | 172 | 46 | 118 |  |  |  | 419
4435 | 2017-06-27 | 2017-12-08 | 2018-02-08 | 2018-02-08 | COMP | 2018-04-30 | COMP | 2018-04-30 | COMP | 2019-09-16 | COMP | 2019-10-01 | COMP | Rule 16 | 114 | 42 | 57 | 1 | 348 | 12 | 569
4560 | 2017-06-27 | 2018-01-31 | 2018-06-02 | 2018-06-02 | COMP | 2018-08-28 | COMP | 2018-11-16 | COMP | 2019-03-12 | COMP | 2019-04-01 | COMP | Rule 15/16 | 149 | 86 | 61 | 57 | 77 | 15 | 441
5319 | 2017-06-27 | 2018-05-22 | 2018-06-26 | 2020-04-27 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-06-09 | COMP | 2020-07-06 | COMP | Rule 16 | 227 | 25 | 10 | 1 | 22 | 20 | 760
39207 | 2017-06-27 | 2022-10-05 | 2023-02-09 | 2023-03-22 | COMP | 2023-03-22 | NOTN | 2023-07-06 | COMP |  | INPR | 2023-10-12 | COMP | Other | 1327 | 86 |  | 74 |  |  | 1582
1680 | 2017-06-28 | 2017-07-15 | 2017-09-01 | 2017-09-01 | COMP | 2017-10-02 | COMP | 2019-03-21 | COMP | 2019-03-24 | COMP | 2019-06-03 | COMP | Rule 16 | 12 | 35 | 21 | 367 | 2 | 50 | 484
1681 | 2017-06-28 | 2017-07-15 | 2018-08-09 | 2018-08-09 | COMP | 2018-10-03 | COMP | 2018-10-06 | COMP | 2019-02-22 | COMP | 2019-04-03 | COMP | Rule 15/16 | 12 | 269 | 39 | 3 | 93 | 29 | 442
1736 | 2017-06-28 | 2017-07-19 | 2017-09-20 | 2017-09-20 | COMP | 2018-06-04 | COMP | 2018-06-04 | COMP | 2019-04-09 | COMP | 2019-05-14 | COMP | Rule 16 | 15 | 45 | 176 | 1 | 213 | 26 | 471
1913 | 2017-06-28 | 2017-08-21 | 2018-06-02 | 2018-07-30 | COMP | 2018-10-23 | COMP | 2019-01-04 | COMP | 2019-02-01 | COMP | 2019-03-11 | COMP | Rule 15/16 | 38 | 196 | 61 | 49 | 20 | 26 | 425
1914 | 2017-06-28 | 2017-08-21 | 2018-08-31 | 2018-08-31 | COMP | 2018-10-23 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-03-11 | COMP | Rule 15/16 | 38 | 260 | 37 | 66 | 1 | 28 | 425
1915 | 2017-06-28 | 2017-08-21 | 2018-05-30 | 2018-06-29 | COMP | 2018-10-23 | COMP | 2018-11-15 | COMP | 2019-04-23 | COMP | 2019-06-06 | COMP | Rule 15/16 | 38 | 194 | 81 | 17 | 108 | 32 | 487
2045 | 2017-06-28 | 2017-09-12 | 2017-11-15 | 2017-11-15 | COMP | 2018-06-07 | COMP | 2018-06-07 | COMP | 2019-03-13 | COMP | 2019-05-06 | COMP | Rule 16 | 53 | 46 | 140 | 1 | 191 | 39 | 465
2560 | 2017-06-28 | 2017-12-23 | 2018-12-07 | 2019-02-06 | COMP | 2019-01-02 | COMP |  | REQD |  | REQD | 2020-01-16 | COMP | Rule 15/16 | 123 | 240 |  |  |  |  | 640
3590 | 2017-06-28 | 2018-05-22 | 2018-11-17 | 2018-11-17 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-10-08 | COMP | 2019-10-07 | COMP | Rule 16 | 226 | 125 | 53 | 1 | 171 |  | 572
1794 | 2017-06-29 | 2017-07-27 | 2018-05-14 | 2018-05-14 | COMP | 2018-07-16 | COMP | 2019-01-22 | COMP | 2019-06-29 | INPR | 2019-03-21 | COMP | Rule 16 | 20 | 200 | 44 | 130 |  |  | 432
1878 | 2017-06-29 | 2017-08-15 | 2017-12-28 | 2017-12-28 | COMP | 2018-03-08 | COMP | 2018-03-14 | COMP | 2019-04-30 | COMP | 2019-05-31 | COMP | Rule 16 | 33 | 93 | 48 | 5 | 285 | 23 | 482
1972 | 2017-06-29 | 2017-08-30 | 2017-11-10 | 2017-11-10 | COMP | 2017-12-21 | COMP | 2017-12-21 | COMP | 2019-10-18 | COMP | 2019-11-25 | COMP | Rule 16 | 44 | 51 | 27 | 1 | 460 | 26 | 605
1989 | 2017-06-29 | 2017-09-02 | 2017-11-17 | 2017-11-17 | COMP | 2018-03-09 | COMP | 2018-05-02 | COMP | 2018-11-21 | COMP | 2019-02-20 | COMP | Rule 16 | 46 | 53 | 75 | 39 | 142 | 60 | 411
2002 | 2017-06-29 | 2017-09-06 | 2018-02-26 | 2019-03-28 | COMP | 2019-12-02 | COMP | 2019-12-04 | COMP | 2020-02-25 | COMP | 2020-03-27 | COMP | Rule 16 | 48 | 117 | 172 | 3 | 56 | 24 | 688
2085 | 2017-06-29 | 2017-09-21 | 2018-02-02 | 2018-02-02 | COMP | 2018-07-03 | COMP | 2018-07-06 | COMP | 2020-08-27 | COMP | 2020-10-09 | COMP | Rule 16 | 59 | 91 | 106 | 3 | 541 | 31 | 826
2423 | 2017-06-29 | 2017-11-28 | 2018-07-02 | 2018-07-02 | COMP | 2018-08-20 | COMP | 2019-02-20 | COMP | 2020-04-16 | COMP | 2020-07-30 | COMP | Rule 16 | 104 | 150 | 35 | 125 | 292 | 75 | 776
2638 | 2017-06-29 | 2018-01-10 | 2018-03-13 | 2018-03-13 | COMP | 2018-05-21 | COMP | 2018-12-05 | COMP | 2019-06-27 | COMP | 2019-08-31 | COMP | Rule 15/16 | 133 | 43 | 50 | 137 | 142 | 46 | 546
3947 | 2017-06-29 | 2018-10-23 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-13 | COMP | 2019-01-02 | COMP |  |  | 2019-02-08 | COMP | Rule 16 | 332 | 21 | 15 | 13 |  |  | 404
4524 | 2017-06-29 | 2018-01-24 | 2018-04-30 | 2018-05-07 | COMP | 2019-02-19 | COMP | 2019-02-25 | COMP | 2019-02-27 | COMP | 2019-04-02 | COMP | Rule 16 | 142 | 68 | 197 | 5 | 3 | 25 | 440
4638 | 2017-06-29 | 2018-02-23 | 2018-08-02 | 2018-08-02 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-10-22 | COMP | 2019-12-06 | COMP | Rule 16 | 163 | 113 | 268 | 1 | 41 | 31 | 612
5612 | 2017-06-29 | 2018-06-20 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-03-12 | COMP | 2019-04-17 | COMP | Rule 16 | 245 | 105 | 11 | 1 | 66 | 27 | 451
1726 | 2017-06-30 | 2017-07-18 | 2018-10-29 | 2018-10-25 | COMP | 2019-07-30 | COMP | 2019-10-15 | COMP | 2019-12-05 | COMP | 2019-12-10 | COMP | Rule 16 | 12 | 324 | 190 | 55 | 35 | 4 | 613
1728 | 2017-06-30 | 2017-07-18 | 2018-11-09 | 2018-11-06 | COMP | 2019-03-28 | COMP | 2020-02-26 | COMP | 2020-05-11 | COMP | 2020-07-22 | COMP | Rule 16 | 12 | 333 | 96 | 230 | 54 | 52 | 769
1729 | 2017-06-30 | 2017-07-18 | 2018-12-12 | 2018-12-12 | COMP | 2019-12-19 | COMP | 2020-06-10 | COMP | 2020-02-12 | COMP | 2020-09-04 | COMP | Rule 16 | 12 | 353 | 257 | 120 | 0 | 63 | 801
1731 | 2017-06-30 | 2017-07-18 | 2018-11-02 | 2018-11-02 | COMP | 2019-02-06 | COMP | 2020-05-30 | REQD | 2019-12-05 | COMP | 2019-12-12 | COMP | Rule 16 | 12 | 328 | 63 |  |  |  | 615
1747 | 2017-06-30 | 2017-07-19 | 2018-09-06 | 2018-09-06 | COMP | 2019-02-20 | COMP | 2019-08-21 | COMP | 2019-12-06 | COMP | 2020-01-06 | COMP | Rule 16 | 13 | 286 | 113 | 129 | 74 | 20 | 630
1748 | 2017-06-30 | 2017-07-19 | 2018-08-16 | 2018-08-16 | COMP | 2019-02-20 | COMP | 2019-06-03 | COMP | 2019-09-21 | INPR | 2019-06-14 | COMP | Rule 16 | 13 | 272 | 127 | 73 |  |  | 491
1749 | 2017-06-30 | 2017-07-19 | 2019-05-17 | 2019-05-17 | COMP | 2019-09-18 | COMP | 2019-09-23 | COMP | 2019-12-05 | COMP | 2020-01-14 | COMP | Rule 16 | 13 | 460 | 86 | 4 | 51 | 27 | 636
1790 | 2017-06-30 | 2017-07-27 | 2018-03-22 | 2018-03-22 | COMP | 2018-05-03 | COMP | 2018-05-03 | COMP | 2019-03-18 | COMP | 2019-05-01 | COMP | Rule 16 | 19 | 163 | 31 | 1 | 218 | 33 | 460
1792 | 2017-06-30 | 2017-07-27 | 2018-07-23 | 2018-07-23 | COMP | 2018-08-24 | COMP | 2018-08-29 | COMP | 2019-01-22 | COMP | 2019-02-08 | COMP | Rule 16 | 19 | 248 | 25 | 4 | 98 | 14 | 403
1793 | 2017-06-30 | 2017-07-27 | 2018-07-19 | 2018-07-19 | COMP | 2018-07-27 | COMP | 2018-08-28 | COMP | 2019-06-29 | INPR | 2019-03-08 | COMP | Rule 16 | 19 | 246 | 7 | 23 |  |  | 422
2006 | 2017-06-30 | 2017-09-06 | 2018-02-25 | 2018-02-25 | COMP | 2018-08-22 | COMP | 2018-09-22 | COMP | 2019-05-20 | COMP | 2019-08-13 | COMP | Rule 15/16 | 47 | 116 | 126 | 22 | 164 | 60 | 532
3680 | 2017-06-30 | 2018-06-06 | 2018-07-20 | 2018-07-20 | COMP | 2018-08-27 | COMP | 2018-09-17 | COMP |  | INPR | 2023-11-07 | COMP | Rule 15/16 | 234 | 32 | 27 | 15 |  |  | 1597
12475 | 2017-06-30 | 2019-06-10 | 2020-02-21 | 2020-02-21 | COMP | 2020-04-13 | COMP | 2020-04-14 | COMP | 2020-07-07 | COMP | 2020-06-29 | COMP | Rule 15/16 | 487 | 176 | 37 | 2 | 60 |  | 752
19186 | 2017-06-30 | 2020-04-23 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-28 | COMP | 2020-05-28 | INPR | 2020-05-28 | COMP | 2020-07-17 | COMP | Rule 16 | 706 | 17 | 9 |  |  |  | 766
1755 | 2017-07-03 | 2017-07-19 | 2018-02-06 | 2018-02-06 | COMP | 2018-02-14 | COMP | 2018-02-14 | COMP | 2019-05-02 | COMP | 2019-06-21 | COMP | Rule 15/16 | 12 | 138 | 7 | 1 | 306 | 36 | 495
1803 | 2017-07-03 | 2017-07-28 | 2017-08-02 | 2017-08-02 | COMP | 2017-08-17 | COMP | 2017-08-17 | COMP | 2018-05-24 | COMP | 2021-05-09 | COMP | Rule 16 | 19 | 4 | 12 | 1 | 193 | 743 | 967
1939 | 2017-07-03 | 2017-08-23 | 2017-12-12 | 2017-12-12 | COMP | 2018-09-19 | COMP | 2018-09-19 | COMP | 2019-04-03 | COMP | 2019-04-29 | COMP | Rule 16 | 37 | 76 | 195 | 1 | 134 | 19 | 457
2061 | 2017-07-03 | 2017-09-15 | 2019-01-30 | 2019-01-30 | COMP | 2019-12-04 | COMP | 2019-12-10 | COMP | 2020-07-28 | COMP | 2020-05-20 | COMP | Rule 16 | 53 | 343 | 214 | 5 | 161 |  | 724
2295 | 2017-07-03 | 2017-10-28 | 2018-12-07 | 2019-03-25 | COMP | 2019-05-08 | COMP | 2019-09-24 | COMP | 2019-07-09 | COMP | 2019-11-14 | COMP | Rule 16 | 83 | 277 | 33 | 97 | 0 | 37 | 596
2338 | 2017-07-03 | 2017-11-06 | 2018-06-02 | 2018-06-02 | COMP | 2018-12-19 | COMP | 2019-01-07 | COMP | 2019-08-29 | COMP | 2020-01-17 | COMP | Rule 15/16 | 89 | 142 | 138 | 12 | 165 | 96 | 638
2339 | 2017-07-03 | 2017-11-06 | 2018-04-24 | 2018-06-26 | COMP | 2018-12-19 | COMP | 2019-01-08 | COMP | 2019-08-29 | COMP | 2020-01-31 | COMP | Rule 15/16 | 89 | 115 | 122 | 13 | 164 | 105 | 647
2601 | 2017-07-03 | 2018-01-05 | 2018-02-10 | 2018-02-10 | COMP | 2018-04-02 | COMP | 2018-04-05 | COMP | 2019-10-19 | INPR | 2019-04-18 | COMP | Rule 16 | 128 | 25 | 35 | 4 |  |  | 450
3327 | 2017-07-03 | 2018-04-09 | 2018-12-30 | 2020-10-19 | COMP | 2020-11-12 | COMP | 2020-11-16 | COMP | 2020-11-22 | COMP | 2021-02-02 | COMP | Rule 15/16 | 192 | 183 | 18 | 3 | 5 | 47 | 900
4499 | 2017-07-03 | 2018-01-08 | 2018-06-21 | 2018-06-21 | COMP | 2018-09-19 | COMP | 2018-09-19 | COMP | 2019-12-12 | COMP | 2020-01-13 | COMP | Rule 16 | 129 | 116 | 63 | 1 | 309 | 21 | 634
3158 | 2017-07-04 | 2018-03-15 | 2018-08-22 | 2018-08-22 | COMP | 2018-12-21 | COMP | 2020-11-16 | COMP | 2020-11-10 | COMP | 2021-01-07 | COMP | Rule 15/16 | 174 | 113 | 84 | 480 | 0 | 35 | 882
1651 | 2017-07-05 | 2017-07-10 | 2018-02-28 | 2018-02-28 | COMP | 2018-06-08 | COMP | 2018-06-11 | COMP | 2020-08-06 | COMP | 2020-08-28 | COMP | Rule 15/16 | 4 | 160 | 72 | 2 | 544 | 17 | 794
1737 | 2017-07-05 | 2017-07-19 | 2018-12-17 | 2018-12-14 | COMP | 2019-07-22 | COMP | 2019-09-10 | COMP | 2019-11-12 | COMP | 2019-12-17 | COMP | Rule 16 | 11 | 355 | 151 | 36 | 45 | 24 | 616
1742 | 2017-07-05 | 2017-07-19 | 2018-11-09 | 2018-11-07 | COMP | 2019-02-08 | COMP | 2019-06-07 | COMP | 2019-12-06 | COMP | 2019-09-04 | COMP | Rule 16 | 11 | 332 | 62 | 84 | 126 |  | 545
1881 | 2017-07-05 | 2017-08-15 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-23 | COMP | 2019-09-24 | COMP | 2020-11-21 | INPR | 2019-10-21 | COMP | Rule 16 | 30 | 501 | 9 | 22 |  |  | 578
1885 | 2017-07-05 | 2017-08-15 | 2019-07-31 | 2019-07-31 | COMP | 2019-07-30 | COMP | 2019-09-17 | COMP | 2019-11-21 | COMP | 2019-12-14 | COMP | Rule 16 | 30 | 492 |  | 35 | 47 | 15 | 614
2062 | 2017-07-05 | 2017-09-15 | 2019-02-22 | 2019-02-22 | COMP | 2019-12-04 | COMP | 2019-12-10 | COMP | 2020-08-28 | COMP | 2020-01-17 | COMP | Rule 16 | 52 | 359 | 198 | 5 | 184 |  | 637
2063 | 2017-07-05 | 2017-09-15 | 2019-01-24 | 2019-01-24 | COMP | 2019-12-04 | COMP | 2019-12-10 | COMP | 2020-08-28 | COMP | 2020-01-15 | COMP | Rule 16 | 52 | 339 | 218 | 5 | 184 |  | 635
2064 | 2017-07-05 | 2017-09-15 | 2019-03-13 | 2019-03-13 | COMP | 2019-12-04 | COMP | 2019-12-18 | COMP | 2020-08-06 | COMP | 2020-02-04 | COMP | Rule 16 | 52 | 372 | 185 | 11 | 162 |  | 648
4640 | 2017-07-05 | 2018-02-23 | 2018-04-03 | 2019-07-03 | COMP | 2019-08-23 | COMP | 2020-02-29 | REQD | 2019-10-23 | COMP | 2019-11-19 | COMP | Rule 16 | 160 | 28 | 37 |  |  |  | 598
5863 | 2017-07-05 | 2018-07-10 | 2018-09-28 | 2018-09-28 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2019-09-01 | INPR | 2019-01-23 | COMP | Rule 16 | 255 | 58 | 39 | 1 |  |  | 389
1765 | 2017-07-06 | 2017-07-21 | 2018-04-10 | 2018-11-10 | COMP | 2018-12-05 | COMP | 2019-02-27 | COMP | 2019-06-29 | INPR | 2019-03-27 | COMP | Rule 15/16 | 12 | 180 | 15 | 57 |  |  | 432
1770 | 2017-07-06 | 2017-07-24 | 2017-11-20 | 2017-11-20 | COMP | 2018-01-26 | COMP | 2018-06-04 | COMP | 2019-12-11 | COMP | 2020-01-07 | COMP | Rule 16 | 13 | 84 | 45 | 90 | 383 | 18 | 628
1880 | 2017-07-06 | 2017-08-15 | 2019-07-30 | 2019-07-30 | COMP | 2019-09-16 | COMP | 2019-10-18 | COMP | 2019-11-12 | COMP | 2019-11-15 | COMP | Rule 16 | 29 | 491 | 34 | 25 | 17 | 4 | 595
2097 | 2017-07-06 | 2017-09-22 | 2017-10-24 | 2017-10-24 | COMP | 2018-07-12 | COMP | 2018-07-13 | COMP | 2019-04-20 | INPR | 2019-01-03 | COMP | Rule 16 | 56 | 23 | 179 | 2 |  |  | 375
2145 | 2017-07-06 | 2017-09-29 | 2017-11-29 | 2017-11-29 | COMP | 2018-03-20 | COMP | 2018-04-12 | COMP | 2018-07-24 | COMP | 2019-02-01 | COMP | Rule 15/16 | 61 | 41 | 76 | 18 | 72 | 132 | 395
2182 | 2017-07-06 | 2017-10-05 | 2018-04-18 | 2018-04-18 | COMP | 2021-12-15 | COMP | 2023-08-30 | COMP | 2023-08-04 | COMP | 2023-10-27 | COMP | Rule 15/16 | 65 | 133 | 921 | 430 | 0 | 42 | 1587
2196 | 2017-07-06 | 2017-10-09 | 2018-05-04 | 2019-02-28 | COMP | 2018-06-08 | COMP | 2018-08-02 | COMP | 2019-05-29 | COMP | 2019-08-06 | COMP | Rule 15/16 | 67 | 143 |  | 39 | 206 | 49 | 524
2203 | 2017-07-06 | 2017-10-10 | 2018-09-12 | 2018-09-12 | COMP | 2018-10-08 | NOTN | 2018-10-30 | COMP | 2019-03-13 | COMP | 2019-03-18 | COMP | Rule 16 | 68 | 232 |  | 35 | 90 | 4 | 425
2387 | 2017-07-06 | 2017-11-15 | 2018-04-12 | 2018-04-12 | COMP | 2018-04-16 | COMP | 2018-04-16 | COMP | 2019-02-11 | COMP | 2019-02-27 | COMP | Rule 16 | 93 | 101 | 3 | 1 | 207 | 12 | 412
2787 | 2017-07-06 | 2018-01-31 | 2018-08-23 | 2018-08-23 | COMP | 2018-09-27 | COMP | 2018-09-28 | COMP | 2018-11-21 | COMP | 2019-01-26 | COMP | Rule 15/16 | 143 | 144 | 25 | 2 | 38 | 43 | 390
4371 | 2017-07-06 | 2017-10-27 | 2018-02-12 | 2018-06-15 | COMP | 2018-12-18 | COMP | 2019-02-08 | COMP | 2019-01-24 | COMP | 2019-03-13 | COMP | Rule 16 | 81 | 71 | 128 | 36 | 0 | 23 | 422
4772 | 2017-07-06 | 2018-03-28 | 2018-06-26 | 2018-06-26 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-12-27 | COMP | 2021-06-18 | COMP | Rule 16 | 182 | 64 | 236 | 1 | 143 | 373 | 994
6836 | 2017-07-06 | 2018-09-12 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-08-01 | COMP | 2019-08-29 | COMP | Rule 15/16 | 299 | 140 | 27 | 1 | 58 | 21 | 541
1848 | 2017-07-07 | 2017-08-09 | 2017-11-12 | 2017-11-12 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-06-19 | COMP | 2019-07-19 | COMP | Rule 16 | 24 | 66 | 290 | 1 | 112 | 22 | 511
2340 | 2017-07-07 | 2017-11-07 | 2018-08-02 | 2018-08-02 | COMP | 2018-11-05 | COMP | 2018-11-13 | COMP | 2018-11-21 | COMP | 2019-03-21 | COMP | Rule 16 | 87 | 184 | 67 | 6 | 7 | 81 | 427
2687 | 2017-07-07 | 2018-01-18 | 2018-04-09 | 2018-04-09 | COMP | 2018-06-20 | COMP | 2018-09-14 | COMP | 2021-06-01 | COMP | 2021-06-07 | COMP | Rule 15/16 | 133 | 57 | 52 | 61 | 681 | 5 | 984
2874 | 2017-07-07 | 2018-02-09 | 2018-06-18 | 2018-06-18 | COMP | 2018-06-22 | COMP | 2018-06-27 | COMP | 2018-11-20 | COMP | 2019-01-22 | COMP | Rule 16 | 149 | 90 | 5 | 4 | 102 | 41 | 386
4496 | 2017-07-07 | 2018-01-09 | 2018-03-13 | 2018-04-18 | COMP | 2018-05-09 | COMP | 2018-09-11 | COMP | 2019-03-11 | COMP | 2019-04-10 | COMP | Rule 16 | 127 | 44 | 16 | 87 | 123 | 23 | 441
5408 | 2017-07-07 | 2018-05-29 | 2018-09-28 | 2018-09-28 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-09-06 | COMP | 2019-12-23 | COMP | Rule 16 | 224 | 87 | 75 | 1 | 162 | 74 | 618
5708 | 2017-07-07 | 2018-06-26 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-14 | COMP | 2019-04-23 | COMP | 2019-05-28 | COMP | 2019-05-31 | COMP | Rule 16 | 244 | 162 | 18 | 29 | 25 | 4 | 477
6187 | 2017-07-07 | 2018-08-02 | 2018-10-08 | 2018-10-08 | COMP | 2019-01-22 | COMP | 2019-05-30 | COMP | 2019-11-24 | INPR | 2019-08-06 | COMP | Rule 16 | 270 | 47 | 71 | 91 |  |  | 523
1703 | 2017-07-10 | 2017-07-18 | 2018-04-02 | 2018-04-02 | COMP | 2018-12-17 | COMP | 2019-01-07 | COMP | 2019-08-28 | COMP | 2019-10-01 | COMP | Rule 16 | 7 | 177 | 180 | 14 | 164 | 24 | 561
2077 | 2017-07-10 | 2017-09-20 | 2018-01-26 | 2018-01-26 | COMP | 2018-02-07 | COMP | 2018-02-08 | COMP | 2019-01-08 | COMP | 2019-02-22 | COMP | Rule 16 | 52 | 87 | 9 | 2 | 230 | 32 | 407
2305 | 2017-07-10 | 2017-10-31 | 2018-02-19 | 2018-02-19 | COMP | 2018-03-02 | COMP | 2018-03-06 | COMP | 2020-06-30 | COMP | 2020-07-22 | COMP | Rule 16 | 81 | 73 | 9 | 3 | 585 | 17 | 764
2441 | 2017-07-10 | 2017-11-30 | 2019-04-03 | 2019-04-03 | COMP | 2019-06-17 | COMP | 2019-06-24 | COMP | 2019-06-12 | COMP | 2019-10-22 | COMP | Rule 15/16 | 100 | 336 | 53 | 6 | 0 | 85 | 576
3027 | 2017-07-10 | 2018-02-28 | 2018-03-26 | 2018-03-26 | COMP | 2018-07-12 | COMP | 2018-07-20 | COMP | 2019-12-19 | COMP | 2020-01-09 | COMP | Rule 16 | 160 | 19 | 77 | 7 | 356 | 14 | 628
3264 | 2017-07-10 | 2018-03-28 | 2019-01-08 | 2019-01-08 | COMP | 2019-02-04 | COMP | 2019-02-12 | COMP | 2019-09-21 | INPR | 2019-05-29 | COMP | Rule 16 | 180 | 197 | 19 | 7 |  |  | 474
4367 | 2017-07-10 | 2017-10-19 | 2018-03-01 | 2018-03-01 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2018-11-17 | COMP | 2019-02-12 | COMP | Rule 15/16 | 73 | 89 | 183 | 1 | 1 | 57 | 400
4368 | 2017-07-10 | 2017-10-23 | 2018-03-01 | 2018-03-01 | COMP | 2018-05-01 | COMP | 2018-05-01 | COMP | 2019-08-01 | COMP | 2019-09-10 | COMP | Rule 16 | 75 | 87 | 44 | 1 | 316 | 28 | 546
5344 | 2017-07-10 | 2018-05-23 | 2018-11-13 | 2018-11-13 | COMP | 2018-11-28 | COMP | 2019-02-05 | NOTN | 2019-11-24 | REQD | 2019-01-25 | COMP | Rule 16 | 220 | 121 | 10 |  |  |  | 388
8199 | 2017-07-10 | 2018-11-17 | 2018-12-17 | 2018-12-17 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-08-19 | COMP | 2019-09-27 | COMP | Rule 16 | 343 | 19 | 5 | 1 | 166 | 29 | 559
29932 | 2017-07-10 | 2021-08-06 | 2021-12-08 | 2021-12-09 | COMP | 2021-12-14 | COMP | 2021-12-14 | COMP |  | INPR | 2022-11-16 | COMP | Rule 16 | 1026 | 85 | 4 | 1 |  |  | 1348
1868 | 2017-07-11 | 2017-08-11 | 2018-07-12 | 2018-07-12 | COMP | 2018-08-08 | COMP | 2018-08-08 | COMP | 2019-05-29 | COMP | 2019-07-31 | COMP | Rule 15/16 | 24 | 230 | 20 | 1 | 202 | 45 | 517
1883 | 2017-07-11 | 2017-08-16 | 2017-09-26 | 2017-09-26 | COMP | 2017-11-03 | COMP | 2017-11-06 | COMP | 2019-08-26 | COMP | 2019-09-26 | COMP | Rule 16 | 27 | 29 | 29 | 2 | 452 | 23 | 557
1986 | 2017-07-11 | 2017-09-01 | 2018-05-08 | 2018-05-08 | COMP | 2018-05-24 | COMP | 2018-06-20 | COMP | 2018-12-12 | COMP | 2019-03-26 | COMP | Rule 16 | 39 | 170 | 13 | 19 | 121 | 71 | 428
2545 | 2017-07-11 | 2017-12-21 | 2018-02-02 | 2018-02-02 | COMP | 2018-11-09 | COMP | 2019-09-17 | COMP | 2019-04-12 | COMP | 2019-11-08 | COMP | Rule 16 | 114 | 29 | 197 | 213 | 0 | 39 | 588
2631 | 2017-07-11 | 2018-01-09 | 2018-08-21 | 2018-08-21 | COMP | 2018-10-25 | COMP | 2019-01-02 | COMP | 2018-12-20 | COMP | 2019-05-08 | COMP | Rule 15/16 | 125 | 157 | 47 | 45 | 0 | 89 | 459
2647 | 2017-07-11 | 2018-01-12 | 2019-05-21 | 2019-05-21 | COMP | 2019-08-26 | COMP | 2020-04-28 | COMP | 2020-04-23 | COMP | 2020-06-16 | COMP | Rule 15/16 | 128 | 341 | 68 | 169 | 0 | 35 | 737
3507 | 2017-07-11 | 2018-05-09 | 2018-08-25 | 2018-08-25 | COMP | 2019-03-05 | COMP | 2018-10-04 | COMP | 2018-10-15 | COMP | 2019-04-16 | COMP | Rule 16 | 209 | 76 | 129 |  | 8 | 125 | 443
4564 | 2017-07-11 | 2018-02-01 | 2018-08-09 | 2018-08-09 | COMP | 2018-08-21 | COMP | 2018-08-21 | COMP | 2018-10-24 | COMP | 2019-01-31 | COMP | Rule 16 | 141 | 133 | 9 | 1 | 46 | 66 | 391
4731 | 2017-07-11 | 2018-03-22 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-05 | COMP | 2020-04-17 | COMP | 2021-01-10 | COMP | 2021-02-04 | COMP | Rule 16 | 175 | 478 | 14 | 32 | 184 | 18 | 897
6042 | 2017-07-11 | 2018-07-21 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-11 | COMP | 2019-05-23 | COMP | 2019-11-06 | COMP | 2019-11-14 | COMP | Rule 16 | 259 | 172 | 9 | 31 | 117 | 6 | 591
6245 | 2017-07-11 | 2018-08-06 | 2018-10-10 | 2019-01-12 | COMP | 2019-02-26 | COMP | 2019-03-08 | COMP | 2019-03-26 | COMP | 2019-04-29 | COMP | Rule 16 | 270 | 47 | 30 | 9 | 13 | 25 | 452
14584 | 2017-07-11 | 2019-09-17 | 2020-01-08 | 2020-01-08 | COMP | 2020-05-20 | COMP | 2020-12-15 | COMP | 2020-12-14 | COMP | 2021-02-04 | COMP | Rule 16 | 550 | 77 | 94 | 145 | 0 | 35 | 897
1678 | 2017-07-12 | 2017-07-14 | 2017-07-29 | 2017-07-29 | COMP | 2017-08-16 | COMP | 2019-05-10 | COMP | 2019-07-05 | COMP | 2019-07-16 | COMP | Rule 16 | 3 | 11 | 13 | 435 | 39 | 8 | 505
1902 | 2017-07-12 | 2017-08-18 | 2017-11-17 | 2017-11-17 | COMP | 2017-12-04 | COMP | 2018-04-30 | COMP | 2020-07-07 | COMP | 2020-08-06 | COMP | Rule 16 | 28 | 64 | 10 | 102 | 551 | 23 | 773
2557 | 2017-07-12 | 2017-12-22 | 2018-02-19 | 2018-02-19 | COMP | 2018-07-18 | COMP | 2018-07-18 | COMP | 2020-08-21 | COMP | 2020-10-12 | COMP | Rule 16 | 114 | 38 | 105 | 1 | 529 | 36 | 819
2939 | 2017-07-12 | 2018-02-20 | 2018-04-16 | 2018-04-16 | COMP | 2018-08-07 | COMP | 2018-08-07 | COMP | 2019-11-25 | COMP | 2020-01-28 | COMP | Rule 16 | 152 | 40 | 80 | 1 | 328 | 42 | 638
3000 | 2017-07-12 | 2018-02-26 | 2018-04-16 | 2018-04-16 | COMP | 2018-06-12 | COMP | 2018-07-12 | COMP | 2019-11-23 | INPR | 2019-07-16 | COMP | Rule 16 | 156 | 36 | 41 | 22 |  |  | 505
4385 | 2017-07-12 | 2017-11-08 | 2018-01-08 | 2018-01-08 | COMP | 2018-04-26 | COMP | 2018-05-08 | COMP | 2019-10-09 | COMP | 2020-01-21 | COMP | Rule 16 | 85 | 39 | 77 | 9 | 359 | 69 | 633
4975 | 2017-07-12 | 2018-04-17 | 2018-09-24 | 2019-01-08 | COMP | 2019-03-08 | COMP | 2019-08-07 | COMP | 2019-06-27 | COMP | 2019-08-19 | COMP | Rule 16 | 192 | 112 | 42 | 107 | 0 | 9 | 529
7823 | 2017-07-12 | 2018-11-01 | 2019-01-30 | 2019-01-30 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-06-28 | COMP | 2019-08-28 | COMP | Rule 16 | 331 | 59 | 68 | 1 | 39 | 43 | 536
16418 | 2017-07-12 | 2019-12-30 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-05-20 | COMP | 2020-06-11 | COMP | Rule 16 | 619 | 33 | 31 | 1 | 38 | 16 | 733
21351 | 2017-07-12 | 2020-08-03 | 2020-08-21 | 2021-07-21 | COMP | 2021-08-13 | COMP | 2021-09-09 | COMP | 2021-08-31 | COMP | 2021-09-24 | COMP | Rule 16 | 770 | 15 | 18 | 19 | 0 | 12 | 1058
1832 | 2017-07-13 | 2017-08-04 | 2017-09-20 | 2017-09-20 | COMP | 2018-06-07 | COMP | 2018-10-23 | COMP | 2019-01-18 | COMP | 2019-01-24 | COMP | Rule 16 | 17 | 33 | 179 | 97 | 59 | 4 | 384
1929 | 2017-07-13 | 2017-08-22 | 2018-05-31 | 2018-06-28 | COMP | 2018-08-08 | COMP | 2019-05-13 | COMP | 2020-07-24 | COMP | 2020-07-16 | COMP | Rule 15/16 | 29 | 194 | 29 | 191 | 304 |  | 757
2067 | 2017-07-13 | 2017-09-18 | 2018-07-29 | 2018-07-29 | COMP | 2018-08-07 | COMP | 2019-01-08 | COMP | 2020-03-02 | COMP | 2020-03-18 | COMP | Rule 16 | 47 | 216 | 7 | 105 | 288 | 13 | 672
2390 | 2017-07-13 | 2017-11-16 | 2017-11-16 | 2017-11-16 | COMP | 2018-12-19 | COMP | 2019-01-07 | COMP | 2023-04-29 | INPR | 2021-03-18 | COMP | Rule 16 | 89 | 1 | 273 | 12 |  |  | 924
3337 | 2017-07-13 | 2018-04-10 | 2018-05-23 | 2018-05-23 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-09-21 | INPR | 2019-05-24 | COMP | Rule 16 | 186 | 32 | 138 | 1 |  |  | 469
4881 | 2017-07-13 | 2018-04-10 | 2018-08-22 | 2018-08-22 | COMP | 2018-08-27 | COMP | 2019-01-24 | COMP | 2019-02-25 | COMP | 2019-03-25 | COMP | Rule 15/16 | 186 | 95 | 4 | 102 | 22 | 21 | 425
5127 | 2017-07-13 | 2018-05-02 | 2018-10-10 | 2018-10-10 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-02-08 | COMP | 2019-03-26 | COMP | Rule 15/16 | 202 | 113 | 63 | 1 | 20 | 32 | 426
5750 | 2017-07-13 | 2018-06-29 | 2019-10-09 | 2019-10-09 | COMP | 2020-03-16 | COMP | 2020-12-10 | COMP | 2021-01-26 | COMP | 2021-03-10 | COMP | Rule 15/16 | 243 | 322 | 107 | 189 | 31 | 31 | 918
8248 | 2017-07-13 | 2018-11-20 | 2019-02-14 | 2019-02-14 | COMP | 2019-03-05 | COMP | 2019-03-07 | COMP | 2019-08-13 | COMP | 2019-09-24 | COMP | Rule 16 | 342 | 58 | 13 | 3 | 112 | 30 | 553
24260 | 2017-07-13 | 2020-12-17 | 2021-01-04 | 2021-01-04 | COMP | 2021-05-20 | COMP | 2021-06-08 | COMP | 2021-07-13 | COMP | 2021-08-12 | COMP | Rule 16 | 863 | 11 | 97 | 13 | 25 | 23 | 1027
1860 | 2017-07-14 | 2017-08-10 | 2017-11-14 | 2017-11-14 | COMP | 2017-12-29 | COMP | 2017-12-29 | COMP | 2017-12-26 | COMP | 2019-04-29 | COMP | Rule 15/16 | 20 | 67 | 31 | 1 | 0 | 334 | 449
1861 | 2017-07-14 | 2017-08-10 | 2017-11-08 | 2017-11-08 | COMP | 2017-12-29 | COMP | 2017-12-29 | COMP | 2017-12-26 | COMP | 2019-05-03 | COMP | Rule 16 | 20 | 64 | 34 | 1 | 0 | 338 | 453
1862 | 2017-07-14 | 2017-08-10 | 2017-11-08 | 2017-11-08 | COMP | 2017-12-29 | COMP | 2017-12-29 | COMP | 2017-12-26 | COMP | 2019-04-29 | COMP | Rule 15/16 | 20 | 64 | 34 | 1 | 0 | 334 | 449
1882 | 2017-07-14 | 2017-08-16 | 2017-12-04 | 2017-12-04 | COMP | 2018-01-25 | COMP | 2020-09-14 | COMP | 2020-09-21 | COMP | 2020-10-21 | COMP | Rule 15/16 | 24 | 75 | 36 | 665 | 6 | 23 | 824
2051 | 2017-07-14 | 2017-09-14 | 2018-05-13 | 2018-05-13 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2021-08-09 | COMP | 2022-05-12 | COMP | Other | 44 | 165 | 387 | 1 | 429 | 193 | 1215
2544 | 2017-07-14 | 2017-12-20 | 2018-02-10 | 2018-02-10 | COMP | 2018-02-27 | COMP | 2019-03-14 | COMP | 2019-03-18 | COMP | 2022-05-03 | COMP | Rule 16 | 110 | 35 | 11 | 263 | 3 | 790 | 1208
5241 | 2017-07-14 | 2018-05-14 | 2018-07-19 | 2018-07-19 | COMP | 2020-06-10 | COMP | 2020-06-10 | INPR | 2023-04-30 | CANC | 2020-12-31 | COMP | Rule 16 | 209 | 47 | 476 |  |  |  | 871
6870 | 2017-07-14 | 2018-09-14 | 2018-11-30 | 2018-11-30 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2019-09-27 | COMP | 2019-11-22 | COMP | Rule 16 | 295 | 53 | 190 | 1 | 20 | 40 | 594
1774 | 2017-07-16 | 2017-07-26 | 2018-03-21 | 2018-03-21 | COMP | 2018-04-19 | COMP | 2018-08-14 | COMP | 2019-07-17 | COMP | 2019-08-16 | COMP | Rule 15/16 | 8 | 163 | 22 | 82 | 232 | 23 | 525
1699 | 2017-07-17 | 2017-07-17 | 2017-08-09 | 2017-08-09 | COMP | 2017-08-04 | NOTN | 2017-08-09 | COMP | 2017-09-29 | COMP | 2022-04-04 | COMP | Other | 1 | 18 |  | 1 | 37 | 1133 | 1186
1805 | 2017-07-17 | 2017-07-31 | 2017-09-15 | 2017-09-15 | COMP | 2017-09-29 | COMP | 2018-09-27 | COMP | 2019-07-10 | COMP | 2019-08-20 | COMP | Rule 16 | 11 | 34 | 11 | 250 | 196 | 30 | 527
1916 | 2017-07-17 | 2017-08-21 | 2017-09-27 | 2017-09-27 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-10-03 | COMP | Rule 15/16 | 26 | 27 | 493 | 1 | 1 | 15 | 558
1962 | 2017-07-17 | 2017-08-28 | 2017-10-12 | 2018-03-02 | COMP | 2018-03-29 | COMP | 2019-08-07 | COMP |  |  | 2019-07-05 | COMP | Rule 16 | 31 | 33 | 20 | 343 |  |  | 495
2150 | 2017-07-17 | 2017-09-30 | 2018-02-12 | 2018-02-12 | COMP | 2018-07-24 | COMP | 2019-03-29 | COMP | 2019-09-21 | INPR | 2019-05-10 | COMP | Rule 15/16 | 54 | 90 | 114 | 171 |  |  | 457
2369 | 2017-07-17 | 2017-11-13 | 2018-07-13 | 2018-07-13 | COMP | 2019-06-06 | COMP | 2019-09-06 | COMP | 2019-10-21 | COMP | 2019-11-12 | COMP | Rule 15/16 | 84 | 167 | 226 | 65 | 32 | 16 | 585
2583 | 2017-07-17 | 2017-12-30 | 2018-03-31 | 2018-03-31 | COMP | 2018-05-07 | COMP | 2019-08-15 | COMP | 2019-08-28 | COMP | 2019-09-16 | COMP | Rule 16 | 115 | 62 | 26 | 322 | 10 | 13 | 545
2700 | 2017-07-17 | 2018-01-20 | 2018-06-18 | 2018-06-06 | COMP | 2019-02-19 | COMP | 2019-07-29 | COMP | 2019-07-30 | COMP | 2019-08-28 | COMP | Rule 16 | 128 | 104 | 176 | 113 | 2 | 22 | 533
4632 | 2017-07-17 | 2018-02-20 | 2018-04-29 | 2018-04-29 | COMP | 2019-05-13 | COMP | 2019-05-21 | COMP | 2019-09-11 | COMP | 2019-11-18 | COMP | Rule 16 | 149 | 49 | 261 | 7 | 79 | 48 | 589
4914 | 2017-07-17 | 2018-04-11 | 2018-07-02 | 2018-07-02 | COMP | 2018-07-18 | COMP | 2019-06-12 | COMP | 2019-05-18 | COMP | 2019-07-10 | COMP | Rule 16 | 185 | 58 | 12 | 227 | 0 | 20 | 498
5041 | 2017-07-17 | 2018-04-25 | 2018-09-12 | 2020-01-10 | COMP | 2020-02-24 | COMP | 2019-01-08 | COMP | 2020-02-11 | COMP | 2020-04-17 | COMP | Rule 16 | 195 | 98 | 30 |  | 275 | 48 | 692
5424 | 2017-07-17 | 2018-05-30 | 2018-12-16 | 2018-12-16 | COMP | 2019-01-09 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-03-26 | COMP | Rule 15/16 | 219 | 138 | 16 | 43 | 1 | 11 | 424
6310 | 2017-07-17 | 2018-08-09 | 2019-01-07 | 2019-01-28 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-04-25 | COMP | 2022-04-08 | COMP | Rule 15/16 | 269 | 102 | 10 | 1 | 54 | 745 | 1190
1773 | 2017-07-18 | 2017-07-26 | 2018-02-23 | 2018-02-23 | COMP | 2018-05-07 | COMP | 2019-07-02 | COMP | 2019-07-03 | COMP | 2019-07-31 | COMP | Rule 15/16 | 7 | 145 | 52 | 291 | 2 | 20 | 512
1804 | 2017-07-18 | 2017-07-29 | 2018-09-27 | 2018-09-27 | COMP | 2018-12-18 | COMP | 2018-12-20 | COMP | 2018-12-18 | COMP | 2019-05-24 | COMP | Rule 16 | 9 | 293 | 56 | 3 | 0 | 108 | 466
1807 | 2017-07-18 | 2017-07-31 | 2017-11-25 | 2017-11-25 | COMP | 2018-05-15 | COMP | 2018-11-16 | COMP | 2019-04-17 | COMP | 2019-06-10 | COMP | Rule 15/16 | 10 | 81 | 118 | 130 | 103 | 38 | 476
1949 | 2017-07-18 | 2017-08-25 | 2018-12-14 | 2018-12-14 | COMP | 2019-02-26 | COMP | 2019-04-17 | COMP | 2020-07-30 | COMP | 2020-11-14 | COMP | Rule 15/16 | 29 | 327 | 49 | 37 | 326 | 75 | 838
2011 | 2017-07-18 | 2017-09-07 | 2018-03-16 | 2018-03-16 | COMP |  | REQD | 2018-09-17 | COMP | 2019-01-24 | COMP | 2021-10-05 | COMP | Rule 15/16 | 37 | 130 |  | 129 | 88 | 681 | 1061
2015 | 2017-07-18 | 2017-09-07 | 2018-01-08 | 2020-04-11 | COMP | 2021-05-07 | COMP | 2021-05-24 | COMP | 2021-05-11 | COMP | 2021-06-09 | COMP | Rule 16 | 37 | 83 | 271 | 12 | 0 | 12 | 979
2449 | 2017-07-18 | 2017-12-01 | 2018-02-14 | 2018-02-14 | COMP | 2018-07-11 | COMP | 2018-07-17 | COMP | 2019-05-11 | COMP | 2019-03-30 | COMP | Rule 15/16 | 95 | 51 | 103 | 5 | 206 |  | 426
2826 | 2017-07-18 | 2018-02-06 | 2018-07-13 | 2018-07-10 | COMP | 2018-09-18 | COMP | 2018-09-27 | COMP | 2019-01-28 | COMP | 2019-02-28 | COMP | Rule 16 | 139 | 111 | 50 | 8 | 82 | 23 | 405
3080 | 2017-07-18 | 2018-03-06 | 2018-05-22 | 2018-05-22 | COMP | 2018-05-31 | COMP | 2018-06-21 | COMP | 2021-03-09 | COMP | 2021-04-26 | COMP | Rule 16 | 158 | 56 | 7 | 16 | 681 | 35 | 948
10166 | 2017-07-18 | 2019-03-05 | 2019-05-09 | 2019-05-09 | COMP | 2019-05-13 | NOTN | 2019-05-14 | COMP | 2019-05-16 | COMP | 2019-07-02 | COMP | Rule 16 | 408 | 48 |  | 4 | 3 | 33 | 492
1864 | 2017-07-19 | 2017-08-11 | 2018-05-28 | 2018-05-28 | COMP | 2018-05-07 | NOTN | 2018-05-28 | COMP | 2019-11-01 | COMP | 2020-02-14 | COMP | Other | 18 | 198 |  | 0 | 362 | 70 | 646
1960 | 2017-07-19 | 2017-08-28 | 2018-01-04 | 2018-01-04 | COMP | 2019-01-16 | COMP | 2019-03-08 | COMP | 2019-01-24 | COMP | 2019-04-01 | COMP | Rule 15/16 | 29 | 88 | 260 | 36 | 0 | 17 | 426
2019 | 2017-07-19 | 2017-09-07 | 2017-11-02 | 2017-11-02 | COMP | 2018-06-06 | COMP | 2018-07-02 | COMP | 2019-10-19 | INPR | 2019-07-03 | COMP | Rule 16 | 36 | 41 | 147 | 19 |  |  | 492
2026 | 2017-07-19 | 2017-09-08 | 2017-10-16 | 2017-10-16 | COMP | 2019-09-16 | COMP | 2019-09-24 | COMP | 2020-05-05 | COMP | 2020-06-02 | COMP | Rule 15/16 | 37 | 27 | 481 | 7 | 154 | 20 | 721
3800 | 2017-07-19 | 2018-07-19 | 2019-06-07 | 2019-06-07 | COMP | 2020-08-11 | COMP |  | REQD |  | REQD | 2021-03-10 | COMP | Rule 15/16 | 252 | 223 | 298 |  |  |  | 914
4988 | 2017-07-19 | 2018-04-18 | 2018-07-16 | 2018-07-16 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-04-09 | COMP | 2019-04-18 | COMP | Rule 16 | 188 | 62 | 104 | 1 | 81 | 8 | 439
5211 | 2017-07-19 | 2018-05-10 | 2018-07-25 | 2018-07-25 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-07-14 | COMP | 2019-12-27 | COMP | Rule 16 | 204 | 53 | 241 | 1 | 3 | 115 | 613
7267 | 2017-07-19 | 2018-10-04 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-04-26 | COMP | 2019-05-23 | COMP | Rule 16 | 306 | 76 | 17 | 1 | 49 | 20 | 464
1828 | 2017-07-20 | 2017-08-03 | 2017-10-04 | 2017-10-04 | COMP | 2018-05-23 | COMP | 2018-05-25 | COMP | 2020-03-13 | COMP | 2020-04-02 | COMP | Rule 16 | 11 | 44 | 159 | 3 | 451 | 15 | 678
2128 | 2017-07-20 | 2017-09-27 | 2018-07-19 | 2018-07-19 | COMP | 2018-08-24 | COMP | 2018-10-11 | COMP | 2020-04-28 | COMP | 2020-06-30 | COMP | Rule 15/16 | 49 | 203 | 27 | 34 | 387 | 45 | 740
2301 | 2017-07-20 | 2017-10-31 | 2018-02-20 | 2018-10-02 | COMP | 2019-01-10 | COMP | 2019-01-28 | COMP | 2019-07-21 | INPR | 2019-03-09 | COMP | Rule 15/16 | 73 | 74 | 68 | 12 |  |  | 409
2341 | 2017-07-20 | 2017-11-07 | 2018-09-19 | 2018-09-18 | COMP | 2018-12-03 | COMP | 2018-12-13 | COMP | 2020-07-28 | COMP | 2020-08-14 | COMP | Rule 15/16 | 78 | 217 | 52 | 9 | 409 | 14 | 773
2386 | 2017-07-20 | 2017-11-15 | 2018-03-25 | 2018-03-25 | COMP | 2020-07-17 | COMP | 2020-10-01 | COMP | 2020-09-02 | COMP | 2020-12-10 | COMP | Rule 15/16 | 83 | 87 | 584 | 54 | 0 | 48 | 853
2910 | 2017-07-20 | 2018-02-15 | 2019-09-09 | 2020-06-16 | COMP | 2020-06-24 | COMP | 2020-06-25 | COMP | 2020-07-20 | COMP | 2020-08-10 | COMP | Rule 15/16 | 144 | 394 | 7 | 2 | 18 | 16 | 769
10006 | 2017-07-20 | 2019-02-26 | 2019-07-10 | 2019-08-02 | COMP | 2020-06-09 | COMP | 2020-07-10 | COMP | 2020-07-15 | COMP | 2020-06-10 | COMP | Rule 16 | 401 | 95 | 214 | 24 | 4 |  | 726
39579 | 2017-07-20 | 2022-10-27 | 2023-02-02 | 2023-03-22 | COMP | 2023-03-22 | NOTN | 2023-04-20 | COMP | 2023-05-23 | COMP | 2023-07-25 | COMP | Other | 1327 | 65 |  | 22 | 24 | 43 | 1510
1844 | 2017-07-21 | 2017-08-08 | 2017-12-13 | 2017-12-13 | COMP | 2018-03-27 | COMP | 2018-09-10 | COMP | 2020-08-12 | COMP | 2020-09-03 | COMP | Rule 15/16 | 13 | 88 | 71 | 117 | 485 | 17 | 786
2280 | 2017-07-21 | 2017-10-27 | 2018-02-10 | 2018-02-10 | COMP | 2018-03-10 | COMP | 2019-05-15 | COMP | 2019-04-25 | COMP | 2019-06-20 | COMP | Rule 15/16 | 70 | 70 | 19 | 298 | 0 | 26 | 481
3050 | 2017-07-21 | 2018-03-03 | 2018-03-19 | 2018-03-19 | COMP | 2019-10-22 | COMP | 2023-02-25 | REQD | 2023-02-25 | REQD | 2019-11-05 | COMP | Other | 153 | 11 | 404 |  |  |  | 577
3267 | 2017-07-21 | 2018-03-29 | 2018-09-17 | 2018-09-17 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2020-07-02 | COMP | 2020-08-10 | COMP | Rule 16 | 172 | 120 | 64 | 1 | 388 | 28 | 768
3272 | 2017-07-21 | 2018-03-29 | 2018-06-15 | 2018-06-15 | COMP | 2019-01-10 | COMP | 2019-01-15 | COMP | 2019-04-08 | COMP | 2019-06-03 | COMP | Rule 15/16 | 172 | 56 | 143 | 4 | 58 | 40 | 468
5045 | 2017-07-21 | 2018-04-26 | 2018-08-28 | 2018-10-08 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2018-12-19 | COMP | 2019-01-10 | COMP | Rule 16 | 192 | 87 | 13 | 1 | 38 | 15 | 369
8890 | 2017-07-21 | 2019-01-04 | 2019-02-22 | 2019-02-22 | COMP | 2019-05-28 | COMP | 2019-09-20 | COMP | 2020-04-07 | COMP | 2020-04-08 | COMP | Rule 16 | 365 | 34 | 67 | 82 | 136 | 2 | 681
1910 | 2017-07-22 | 2017-08-19 | 2017-12-16 | 2017-12-16 | COMP | 2018-03-21 | COMP | 2018-08-03 | COMP | 2018-11-16 | COMP | 2019-01-03 | COMP | Rule 15/16 | 20 | 81 | 64 | 96 | 74 | 31 | 363
1970 | 2017-07-22 | 2017-08-30 | 2018-03-12 | 2018-03-12 | COMP | 2018-04-05 | COMP | 2018-12-19 | COMP | 2019-01-15 | COMP | 2019-02-06 | COMP | Rule 15/16 | 28 | 131 | 19 | 179 | 18 | 16 | 386
2562 | 2017-07-22 | 2017-12-29 | 2018-06-14 | 2018-06-14 | COMP | 2019-11-20 | COMP | 2020-05-29 | COMP | 2020-05-11 | COMP | 2020-07-23 | COMP | Rule 15/16 | 110 | 116 | 362 | 131 | 0 | 40 | 755
2250 | 2017-07-23 | 2017-10-23 | 2018-06-12 | 2018-06-12 | COMP | 2018-08-10 | COMP | 2018-11-01 | COMP | 2018-10-27 | COMP | 2020-02-21 | COMP | Rule 16 | 65 | 159 | 43 | 59 | 0 | 325 | 647
1872 | 2017-07-24 | 2017-08-11 | 2017-10-11 | 2017-10-11 | COMP | 2017-10-18 | COMP | 2017-11-29 | COMP | 2019-10-19 | INPR | 2019-06-25 | COMP | Rule 16 | 15 | 43 | 6 | 28 |  |  | 483
1893 | 2017-07-24 | 2017-08-17 | 2017-10-24 | 2017-10-24 | COMP | 2018-02-22 | COMP | 2018-02-22 | COMP | 2022-07-16 | INPR | 2021-01-16 | COMP | Rule 16 | 19 | 48 | 81 | 1 |  |  | 875
1898 | 2017-07-24 | 2017-08-17 | 2017-11-17 | 2017-11-17 | COMP | 2018-05-17 | COMP | 2018-05-17 | COMP | 2022-07-09 | INPR | 2022-06-23 | COMP | Rule 16 | 19 | 65 | 124 | 1 |  |  | 1237
1899 | 2017-07-24 | 2017-08-17 | 2017-12-19 | 2017-12-19 | COMP | 2018-02-22 | COMP | 2018-02-22 | COMP | 2018-08-29 | COMP | 2022-06-23 | COMP | Rule 16 | 19 | 85 | 44 | 1 | 133 | 960 | 1237
1900 | 2017-07-24 | 2017-08-17 | 2018-03-05 | 2018-03-05 | COMP | 2018-04-11 | COMP | 2018-04-11 | COMP | 2022-07-16 | INPR | 2021-01-16 | COMP | Rule 16 | 19 | 135 | 28 | 1 |  |  | 875
1901 | 2017-07-24 | 2017-08-17 | 2018-02-28 | 2018-02-28 | COMP | 2018-04-11 | COMP | 2018-04-11 | COMP | 2018-05-08 | COMP | 2022-06-23 | COMP | Rule 16 | 19 | 132 | 31 | 1 | 20 | 1039 | 1237
2010 | 2017-07-24 | 2017-09-07 | 2017-12-01 | 2017-12-01 | COMP | 2020-08-10 | COMP | 2019-09-24 | COMP | 2020-07-01 | COMP | 2020-09-22 | COMP | Rule 16 | 33 | 59 | 677 |  | 194 | 59 | 797
2039 | 2017-07-24 | 2017-09-11 | 2018-02-01 | 2018-02-01 | COMP | 2018-03-19 | COMP | 2018-03-23 | COMP | 2018-12-21 | COMP | 2019-03-26 | COMP | Rule 16 | 35 | 98 | 32 | 5 | 190 | 64 | 419
2070 | 2017-07-24 | 2017-09-20 | 2017-12-16 | 2017-12-16 | COMP | 2018-03-06 | COMP | 2018-05-01 | COMP | 2019-10-19 | INPR | 2019-07-05 | COMP | Rule 16 | 42 | 60 | 53 | 41 |  |  | 490
2163 | 2017-07-24 | 2017-10-03 | 2018-03-05 | 2018-03-05 | COMP | 2018-05-01 | COMP | 2018-06-28 | COMP | 2018-07-02 | COMP | 2019-05-17 | COMP | Rule 16 | 51 | 103 | 42 | 42 | 3 | 221 | 457
2206 | 2017-07-24 | 2017-10-11 | 2018-08-01 | 2018-08-01 | COMP | 2018-09-19 | COMP | 2019-04-25 | COMP | 2023-04-29 | CANC | 2019-09-06 | COMP | Rule 15/16 | 57 | 202 | 35 | 150 |  |  | 534
2361 | 2017-07-24 | 2017-11-12 | 2018-02-16 | 2018-02-16 | COMP | 2018-03-09 | COMP | 2018-09-11 | COMP | 2019-07-21 | INPR | 2019-01-04 | COMP | Rule 16 | 78 | 65 | 15 | 130 |  |  | 364
2422 | 2017-07-24 | 2017-11-30 | 2017-12-16 | 2019-03-19 | COMP | 2019-04-11 | COMP | 2019-06-19 | COMP | 2019-07-02 | COMP | 2019-07-08 | COMP | Rule 16 | 90 | 12 | 18 | 49 | 10 | 4 | 491
3105 | 2017-07-24 | 2018-03-09 | 2018-06-01 | 2018-06-01 | COMP | 2018-06-12 | COMP | 2018-06-21 | NOTN | 2019-04-20 | INPR | 2019-01-02 | COMP | Rule 16 | 157 | 60 | 8 |  |  |  | 362
4912 | 2017-07-24 | 2018-04-10 | 2018-06-21 | 2018-12-13 | COMP | 2018-05-23 | NOTN | 2018-12-13 | COMP | 2018-11-27 | COMP | 2019-01-04 | COMP | Other | 179 | 52 |  | 1 | 0 | 15 | 364
7943 | 2017-07-24 | 2018-11-06 | 2019-04-18 | 2019-04-18 | COMP | 2019-08-13 | COMP | 2023-10-16 | COMP | 2023-10-11 | COMP | 2023-11-29 | COMP | Rule 15/16 | 326 | 111 | 82 | 1050 | 0 | 30 | 1595
1996 | 2017-07-25 | 2017-09-05 | 2018-11-02 | 2018-11-02 | COMP | 2019-03-05 | NOTN | 2019-03-08 | COMP | 2019-02-05 | COMP | 2019-04-10 | COMP | Other | 30 | 294 |  | 84 | 0 | 24 | 429
2314 | 2017-07-25 | 2017-11-02 | 2018-01-19 | 2018-01-19 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-11-22 | COMP | 2020-01-13 | COMP | Rule 16 | 72 | 51 | 346 | 1 | 121 | 33 | 619
2322 | 2017-07-25 | 2017-11-03 | 2018-01-03 | 2017-11-27 | COMP | 2017-11-25 | NOTN | 2018-06-01 | COMP | 2018-12-11 | COMP | 2019-04-10 | COMP | Other | 73 | 39 |  | 130 | 133 | 83 | 429
3127 | 2017-07-25 | 2018-03-12 | 2018-06-19 | 2018-06-19 | COMP | 2018-07-16 | COMP | 2018-09-10 | COMP | 2019-01-16 | COMP | 2019-02-21 | COMP | Rule 15/16 | 157 | 71 | 19 | 40 | 88 | 25 | 395
4201 | 2017-07-25 | 2019-07-09 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-26 | COMP | 2019-09-10 | COMP | 2020-02-28 | COMP | 2020-02-26 | COMP | Rule 15/16 | 491 | 7 | 29 | 11 | 117 |  | 649
5114 | 2017-07-25 | 2018-05-01 | 2018-08-16 | 2018-09-11 | COMP | 2018-11-08 | COMP | 2019-01-07 | COMP | 2019-12-11 | COMP | 2020-01-06 | COMP | Rule 16 | 193 | 76 | 43 | 38 | 235 | 17 | 614
12667 | 2017-07-25 | 2019-06-17 | 2019-07-17 | 2019-07-17 | COMP | 2019-06-18 | NOTN | 2019-07-17 | COMP | 2019-11-21 | COMP | 2019-12-20 | COMP | Other | 476 | 22 |  | 1 | 90 | 20 | 605
1838 | 2017-07-26 | 2017-08-07 | 2018-01-09 | 2018-01-09 | COMP | 2018-02-02 | COMP | 2018-03-14 | COMP | 2018-04-17 | COMP | 2019-05-18 | COMP | Rule 15/16 | 9 | 106 | 18 | 28 | 25 | 274 | 455
2035 | 2017-07-26 | 2017-09-09 | 2018-01-07 | 2018-01-07 | COMP | 2018-01-10 | COMP | 2018-03-06 | COMP | 2019-03-14 | COMP | 2019-04-11 | COMP | Rule 16 | 32 | 80 | 3 | 38 | 258 | 21 | 429
2068 | 2017-07-26 | 2017-09-19 | 2018-03-02 | 2018-03-02 | COMP | 2018-06-26 | COMP | 2019-01-30 | COMP | 2019-01-08 | COMP | 2019-02-20 | COMP | Rule 16 | 39 | 112 | 82 | 149 | 0 | 15 | 393
2110 | 2017-07-26 | 2017-09-26 | 2018-04-13 | 2018-04-13 | COMP | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-03-18 | COMP | Rule 16 | 44 | 137 | 201 | 2 | 1 | 31 | 411
2481 | 2017-07-26 | 2017-12-07 | 2018-03-22 | 2019-10-18 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-27 | COMP | 2020-02-07 | COMP | Rule 16 | 93 | 72 | 60 | 1 | 7 | 10 | 636
2582 | 2017-07-26 | 2017-12-30 | 2018-01-06 | 2018-01-06 | COMP | 2018-01-11 | COMP | 2018-01-11 | COMP | 2021-02-02 | COMP | 2021-02-24 | COMP | Rule 16 | 108 | 4 | 4 | 1 | 769 | 16 | 899
4822 | 2017-07-26 | 2018-04-03 | 2018-08-29 | 2018-09-13 | COMP | 2018-09-26 | COMP | 2018-10-15 | COMP | 2018-11-27 | COMP | 2019-01-02 | COMP | Rule 16 | 172 | 105 | 10 | 14 | 29 | 25 | 360
18453 | 2017-07-26 | 2020-03-25 | 2021-04-26 | 2021-04-26 | COMP | 2021-05-11 | COMP | 2021-05-11 | COMP | 2022-03-01 | COMP | 2021-07-14 | COMP | Rule 15/16 | 668 | 275 | 12 | 1 | 203 |  | 997
1877 | 2017-07-27 | 2017-08-14 | 2018-06-23 | 2018-06-23 | COMP | 2019-01-15 | COMP | 2019-06-28 | COMP | 2020-10-24 | INPR | 2019-09-19 | COMP | Rule 16 | 13 | 216 | 140 | 116 |  |  | 540
1926 | 2017-07-27 | 2017-08-22 | 2018-06-15 | 2018-06-15 | COMP | 2018-08-08 | COMP | 2019-02-12 | COMP | 2019-02-19 | COMP | 2019-04-12 | COMP | Rule 15/16 | 19 | 205 | 38 | 128 | 5 | 39 | 429
3950 | 2017-07-27 | 2018-10-24 | 2018-12-12 | 2018-12-07 | COMP | 2019-01-28 | COMP | 2019-10-02 | COMP |  |  | 2019-10-22 | COMP | Rule 16 | 314 | 33 | 34 | 174 |  |  | 563
3959 | 2017-07-27 | 2018-10-30 | 2018-12-12 | 2018-12-05 | COMP | 2019-03-05 | COMP | 2019-03-06 | NOTN |  |  | 2019-10-04 | COMP | Rule 15/16 | 318 | 29 | 61 |  |  |  | 551
4018 | 2017-07-27 | 2018-12-03 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-20 | COMP | 2019-10-03 | COMP | 2019-11-07 | COMP | 2019-12-09 | COMP | Rule 16 | 339 | 128 | 12 | 74 | 26 | 20 | 594
5636 | 2017-07-27 | 2018-06-22 | 2018-09-25 | 2018-09-25 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2019-09-01 | INPR | 2019-05-06 | COMP | Rule 16 | 228 | 66 | 5 | 1 |  |  | 445
7822 | 2017-07-27 | 2018-11-01 | 2019-04-03 | 2019-04-03 | COMP | 2019-06-27 | COMP | 2019-10-22 | COMP | 2023-04-22 | INPR | 2020-03-04 | COMP | Rule 15/16 | 320 | 103 | 61 | 82 |  |  | 652
8830 | 2017-07-27 | 2019-01-02 | 2019-01-11 | 2019-01-11 | COMP | 2019-02-13 | COMP | 2019-03-07 | COMP | 2019-03-04 | COMP | 2019-07-01 | COMP | Rule 16 | 359 | 8 | 23 | 16 | 0 | 82 | 484
1871 | 2017-07-28 | 2017-08-11 | 2017-10-16 | 2017-10-16 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2019-06-20 | COMP | Rule 15/16 | 11 | 46 | 15 | 1 | 1 | 407 | 476
1873 | 2017-07-28 | 2017-08-11 | 2017-10-16 | 2017-10-16 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2019-08-13 | COMP | Rule 16 | 11 | 46 | 15 | 1 | 1 | 444 | 513
1874 | 2017-07-28 | 2017-08-11 | 2017-10-16 | 2017-10-16 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2019-07-31 | COMP | Rule 16 | 11 | 46 | 15 | 1 | 1 | 435 | 504
1875 | 2017-07-28 | 2017-08-11 | 2017-10-12 | 2017-10-12 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2017-11-03 | COMP | 2019-06-18 | COMP | Rule 16 | 11 | 44 | 17 | 1 | 1 | 405 | 474
2304 | 2017-07-28 | 2017-10-31 | 2017-12-28 | 2017-12-28 | COMP | 2018-12-27 | COMP | 2019-02-06 | COMP | 2019-03-04 | COMP | 2019-04-04 | COMP | Rule 16 | 67 | 39 | 251 | 28 | 18 | 24 | 422
2424 | 2017-07-28 | 2017-11-28 | 2018-05-10 | 2018-05-10 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-02-06 | COMP | 2019-03-07 | COMP | Rule 15/16 | 84 | 114 | 178 | 1 | 9 | 21 | 402
3035 | 2017-07-28 | 2018-03-01 | 2018-08-01 | 2018-08-01 | COMP | 2018-08-20 | COMP | 2018-08-20 | COMP | 2019-01-23 | COMP | 2019-04-10 | COMP | Rule 16 | 147 | 108 | 14 | 1 | 106 | 55 | 426
4806 | 2017-07-28 | 2018-03-31 | 2018-09-19 | 2018-09-19 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-04-02 | COMP | 2019-05-02 | COMP | Rule 16 | 168 | 120 | 64 | 1 | 70 | 23 | 442
2102 | 2017-07-29 | 2017-09-26 | 2018-02-01 | 2018-02-01 | COMP | 2018-10-31 | COMP | 2019-08-29 | COMP | 2019-08-01 | COMP | 2019-10-04 | COMP | Rule 15/16 | 41 | 87 | 191 | 208 | 0 | 26 | 549
2033 | 2017-07-31 | 2017-09-08 | 2017-11-10 | 2017-11-10 | COMP | 2018-08-31 | COMP | 2018-09-05 | COMP | 2019-08-19 | COMP | 2019-09-20 | COMP | Rule 16 | 29 | 45 | 202 | 3 | 240 | 24 | 539
2149 | 2017-07-31 | 2017-09-30 | 2017-10-02 | 2017-10-02 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2021-02-27 | INPR | 2020-02-20 | COMP | Rule 16 | 44 | 1 | 362 | 1 |  |  | 641
2156 | 2017-07-31 | 2017-10-01 | 2018-02-02 | 2018-02-02 | COMP | 2018-03-21 | COMP | 2018-12-07 | COMP | 2019-07-21 | INPR | 2019-03-18 | COMP | Rule 16 | 44 | 84 | 33 | 182 |  |  | 408
2461 | 2017-07-31 | 2017-12-05 | 2018-02-13 | 2018-02-13 | COMP | 2018-04-20 | COMP | 2018-04-26 | COMP | 2019-02-02 | COMP | 2019-03-23 | COMP | Rule 16 | 88 | 48 | 48 | 5 | 193 | 34 | 412
2524 | 2017-07-31 | 2017-12-14 | 2018-05-08 | 2018-05-08 | COMP | 2019-01-02 | COMP | 2021-01-07 | COMP |  | INPR | 2023-02-11 | COMP | Rule 15/16 | 95 | 100 | 164 | 508 |  |  | 1390
2597 | 2017-07-31 | 2018-01-04 | 2018-04-24 | 2018-04-24 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-05-06 | COMP | 2019-05-22 | COMP | Rule 16 | 108 | 77 | 216 | 1 | 45 | 13 | 455
2808 | 2017-07-31 | 2018-02-02 | 2018-10-02 | 2020-01-04 | COMP | 2019-12-12 | COMP | 2020-01-04 | COMP | 2020-01-15 | COMP | 2020-02-12 | COMP | Rule 16 | 128 | 169 |  | 15 | 8 | 20 | 636
3925 | 2017-07-31 | 2018-10-10 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-25 | COMP | 2019-03-20 | COMP | 2020-01-02 | COMP | 2019-12-13 | COMP | Rule 16 | 302 | 33 | 40 | 38 | 199 |  | 596
4370 | 2017-07-31 | 2017-10-26 | 2018-03-05 | 2018-03-26 | COMP | 2018-05-10 | COMP | 2018-05-10 | COMP | 2018-12-07 | COMP | 2019-02-01 | COMP | Rule 16 | 63 | 86 | 34 | 1 | 146 | 38 | 378
4980 | 2017-07-31 | 2018-04-19 | 2018-11-26 | 2019-03-18 | COMP | 2019-04-09 | COMP | 2019-10-02 | INPR |  | REQD | 2019-09-27 | COMP | Rule 15/16 | 181 | 152 | 17 |  |  |  | 544
2093 | 2017-08-01 | 2017-09-22 | 2018-07-30 | 2018-07-30 | COMP | 2019-05-06 | COMP | 2020-03-03 | COMP | 2020-02-01 | COMP | 2020-04-17 | COMP | Rule 15/16 | 38 | 213 | 193 | 207 | 0 | 34 | 681
2138 | 2017-08-01 | 2017-09-28 | 2018-07-11 | 2018-07-11 | COMP | 2019-05-06 | COMP | 2020-03-03 | COMP | 2020-02-01 | COMP | 2020-04-17 | COMP | Rule 15/16 | 42 | 196 | 206 | 207 | 0 | 34 | 681
2235 | 2017-08-01 | 2017-10-19 | 2018-01-19 | 2018-01-19 | COMP | 2018-01-23 | COMP | 2018-02-09 | COMP | 2019-07-21 | INPR | 2019-03-29 | COMP | Rule 15/16 | 57 | 61 | 3 | 14 |  |  | 416
2737 | 2017-08-01 | 2018-01-25 | 2018-08-08 | 2019-09-11 | COMP | 2019-10-29 | COMP | 2020-03-03 | COMP | 2020-02-01 | COMP | 2020-04-17 | COMP | Rule 15/16 | 121 | 137 | 35 | 84 | 0 | 34 | 681
2980 | 2017-08-01 | 2018-02-26 | 2018-10-10 | 2018-10-10 | COMP | 2018-12-18 | COMP | 2018-12-20 | COMP | 2019-11-12 | COMP | 2019-12-17 | COMP | Rule 16 | 142 | 160 | 47 | 3 | 226 | 24 | 597
8905 | 2017-08-01 | 2019-01-04 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-06-07 | COMP | 2019-08-13 | COMP | Rule 15/16 | 358 | 42 | 40 | 1 | 28 | 47 | 511
1887 | 2017-08-02 | 2017-08-16 | 2018-04-23 | 2018-04-23 | COMP | 2018-05-10 | COMP | 2018-05-15 | COMP | 2019-09-06 | COMP | 2019-12-03 | COMP | Rule 16 | 11 | 171 | 14 | 4 | 331 | 60 | 586
1931 | 2017-08-02 | 2017-08-22 | 2018-02-05 | 2018-02-05 | COMP | 2018-04-11 | COMP | 2018-09-06 | COMP | 2019-02-26 | COMP | 2019-02-25 | COMP | Rule 15/16 | 15 | 113 | 47 | 104 | 117 |  | 391
2100 | 2017-08-02 | 2017-09-24 | 2018-06-25 | 2018-06-25 | COMP | 2018-10-31 | COMP | 2018-11-13 | COMP | 2020-01-14 | COMP | 2020-03-12 | COMP | Rule 15/16 | 37 | 188 | 91 | 9 | 292 | 41 | 654
2139 | 2017-08-02 | 2017-09-28 | 2018-08-03 | 2018-08-03 | COMP | 2019-06-24 | COMP | 2020-03-03 | COMP | 2020-02-01 | COMP | 2020-04-12 | COMP | Rule 15/16 | 41 | 213 | 223 | 173 | 0 | 29 | 675
2141 | 2017-08-02 | 2017-09-28 | 2018-02-01 | 2018-02-01 | COMP | 2019-06-11 | COMP | 2020-06-13 | COMP | 2020-06-15 | COMP | 2020-11-05 | COMP | Rule 15/16 | 41 | 85 | 342 | 254 | 1 | 103 | 822
2179 | 2017-08-02 | 2017-10-05 | 2020-01-28 | 2020-01-28 | COMP | 2018-02-15 | NOTN | 2020-01-29 | COMP | 2020-01-28 | COMP | 2020-07-24 | COMP | Other | 46 | 578 |  | 2 | 0 | 126 | 749
2610 | 2017-08-02 | 2018-01-08 | 2018-02-24 | 2018-02-24 | COMP | 2019-09-12 | NOTN | 2019-09-12 | COMP |  | INPR | 2019-10-01 | COMP | Other | 108 | 33 |  | 391 |  |  | 544
2611 | 2017-08-02 | 2018-01-08 | 2018-02-09 | 2018-02-09 | COMP | 2019-09-12 | NOTN | 2019-09-12 | COMP |  | INPR | 2019-10-02 | COMP | Other | 108 | 24 |  | 401 |  |  | 545
2612 | 2017-08-02 | 2018-01-08 | 2018-03-22 | 2018-03-22 | COMP | 2019-09-30 | NOTN | 2019-09-30 | INPR |  | REQD | 2020-03-17 | COMP | Other | 108 | 52 |  |  |  |  | 657
2613 | 2017-08-02 | 2018-01-08 | 2018-03-02 | 2018-03-02 | COMP | 2019-09-13 | NOTN | 2019-09-13 | COMP |  | INPR | 2019-10-16 | COMP | Other | 108 | 38 |  | 388 |  |  | 555
2666 | 2017-08-02 | 2018-01-16 | 2018-03-24 | 2018-03-24 | COMP | 2019-09-12 | NOTN | 2019-09-12 | COMP |  | INPR | 2019-09-27 | COMP | Other | 113 | 48 |  | 371 |  |  | 542
2667 | 2017-08-02 | 2018-01-16 | 2018-03-24 | 2018-03-24 | COMP |  |  |  |  | 2019-11-04 | COMP | 2020-06-04 | COMP | Other | 113 | 48 |  |  |  |  | 713
2672 | 2017-08-02 | 2018-01-17 | 2018-03-27 | 2018-03-27 | COMP | 2019-09-12 | NOTN | 2019-09-12 | INPR |  | REQD | 2019-10-04 | COMP | Other | 114 | 49 |  |  |  |  | 547
2856 | 2017-08-02 | 2018-02-07 | 2018-04-07 | 2018-04-07 | COMP | 2018-08-01 | COMP | 2018-08-01 | COMP |  | INPR | 2020-01-09 | COMP | Other | 129 | 42 | 81 | 1 |  |  | 611
2942 | 2017-08-02 | 2018-02-20 | 2018-07-27 | 2018-07-27 | COMP | 2018-08-20 | COMP | 2018-09-01 | COMP | 2019-11-26 | COMP | 2020-06-29 | COMP | Rule 15/16 | 137 | 112 | 17 | 10 | 310 | 148 | 730
4419 | 2017-08-02 | 2017-11-29 | 2018-01-17 | 2018-01-17 | COMP | 2018-04-27 | COMP | 2018-04-27 | COMP | 2019-10-17 | COMP | 2020-06-24 | COMP | Rule 16 | 82 | 33 | 72 | 1 | 372 | 172 | 727
6467 | 2017-08-02 | 2018-08-20 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-05 | COMP | 2019-05-14 | COMP | 2019-08-13 | COMP | 2019-08-28 | COMP | Rule 16 | 264 | 149 | 9 | 28 | 64 | 12 | 521
14970 | 2017-08-02 | 2019-10-07 | 2019-10-30 | 2020-03-25 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-08-19 | COMP | 2021-01-07 | COMP | Rule 16 | 548 | 18 | 18 | 1 | 88 | 96 | 862
39581 | 2017-08-02 | 2022-10-27 | 2023-01-31 | 2023-01-31 | COMP | 2023-03-22 | NOTN | 2023-04-06 | COMP | 2023-04-10 | COMP | 2023-05-16 | COMP | Other | 1318 | 63 |  | 47 | 3 | 27 | 1454
1870 | 2017-08-03 | 2017-08-11 | 2017-09-24 | 2017-09-24 | COMP | 2017-10-30 | NOTN | 2017-10-30 | COMP | 2017-10-30 | COMP | 2022-06-03 | COMP | Other | 7 | 30 |  | 26 | 1 | 1155 | 1216
1895 | 2017-08-03 | 2017-08-17 | 2017-12-18 | 2017-12-18 | COMP | 2018-07-12 | COMP | 2021-05-19 | COMP | 2021-06-14 | COMP | 2021-09-13 | COMP | Rule 16 | 11 | 84 | 143 | 718 | 18 | 64 | 1033
1932 | 2017-08-03 | 2017-08-22 | 2017-12-21 | 2019-10-15 | COMP | 2019-12-10 | COMP | 2020-01-09 | COMP | 2019-12-17 | COMP | 2020-02-06 | COMP | Rule 15 | 14 | 84 | 38 | 21 | 0 | 20 | 629
2073 | 2017-08-03 | 2017-09-19 | 2017-12-12 | 2017-12-12 | COMP | 2018-06-01 | COMP | 2018-06-01 | COMP | 2019-02-04 | COMP | 2019-03-29 | COMP | Rule 16 | 33 | 58 | 119 | 1 | 169 | 39 | 414
2313 | 2017-08-03 | 2017-11-02 | 2017-11-02 | 2017-11-02 | COMP | 2018-01-26 | COMP | 2018-01-26 | COMP | 2019-02-19 | COMP | 2019-03-12 | COMP | Rule 16 | 65 | 1 | 56 | 1 | 267 | 16 | 401
2352 | 2017-08-03 | 2017-11-09 | 2018-05-25 | 2018-05-25 | COMP | 2018-07-13 | COMP | 2018-08-24 | COMP | 2019-04-03 | COMP | 2019-07-25 | COMP | Rule 15/16 | 70 | 135 | 34 | 31 | 151 | 80 | 496
2565 | 2017-08-03 | 2017-12-27 | 2018-06-25 | 2022-01-12 | COMP | 2023-12-03 | CANC | 2022-02-02 | COMP | 2021-11-15 | COMP | 2022-02-18 | COMP | Rule 15/16 | 100 | 125 |  | 15 | 0 | 13 | 1143
4410 | 2017-08-03 | 2017-11-21 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-16 | COMP | 2018-11-20 | COMP | 2018-11-26 | COMP | 2019-02-22 | COMP | Rule 16 | 77 | 205 | 23 | 25 | 3 | 61 | 389
7197 | 2017-08-03 | 2018-10-02 | 2019-02-01 | 2019-05-13 | COMP | 2019-05-17 | COMP | 2019-07-05 | COMP | 2019-07-03 | COMP | 2019-07-26 | COMP | Rule 16 | 293 | 83 | 5 | 34 | 0 | 16 | 497
26347 | 2017-08-03 | 2021-03-18 | 2022-01-12 | 2022-01-12 | COMP | 2022-06-13 | COMP | 2023-01-06 | COMP | 2023-04-07 | COMP | 2023-03-31 | COMP | Rule 15/16 | 909 | 209 | 106 | 142 | 64 |  | 1421
26348 | 2017-08-03 | 2021-03-18 | 2022-01-12 | 2022-01-12 | COMP | 2022-04-22 | COMP | 2022-05-31 | COMP |  | INPR | 2023-04-14 | COMP | Rule 15/16 | 909 | 209 | 71 | 27 |  |  | 1431
40652 | 2017-08-03 | 2023-01-19 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-30 | NOTN | 2023-08-09 | COMP |  | INPR | 2023-11-02 | COMP | Other | 1371 | 106 |  | 36 |  |  | 1571
1855 | 2017-08-04 | 2017-08-10 | 2018-03-14 | 2018-03-14 | COMP | 2018-05-09 | COMP | 2018-05-09 | COMP | 2018-12-20 | COMP | 2019-02-22 | COMP | Rule 16 | 5 | 147 | 41 | 1 | 156 | 43 | 388
1857 | 2017-08-04 | 2017-08-10 | 2017-08-23 | 2017-08-23 | COMP | 2017-09-12 | COMP | 2017-09-12 | COMP | 2020-04-25 | INPR | 2019-12-26 | COMP | Rule 16 | 5 | 10 | 14 | 1 |  |  | 600
1997 | 2017-08-04 | 2017-09-05 | 2019-08-22 | 2019-09-17 | COMP | 2020-01-16 | COMP | 2020-02-03 | COMP | 2020-08-17 | COMP | 2020-04-23 | COMP | Rule 16 | 22 | 494 | 83 | 12 | 139 |  | 682
2094 | 2017-08-04 | 2017-09-22 | 2017-11-03 | 2017-11-03 | COMP | 2018-09-10 | COMP | 2019-04-26 | COMP | 2019-05-21 | COMP | 2019-07-18 | COMP | Rule 15/16 | 35 | 31 | 212 | 158 | 18 | 41 | 490
2117 | 2017-08-04 | 2017-09-26 | 2018-02-02 | 2018-02-02 | COMP | 2018-10-12 | COMP | 2018-11-30 | COMP | 2021-02-28 | INPR | 2019-01-31 | COMP | Rule 16 | 37 | 88 | 177 | 33 |  |  | 373
3592 | 2017-08-04 | 2018-05-22 | 2018-09-03 | 2018-09-03 | COMP | 2020-09-02 | COMP | 2020-10-14 | COMP | 2021-03-08 | COMP | 2021-03-22 | COMP | Rule 16 | 200 | 72 | 504 | 30 | 97 | 11 | 910
1998 | 2017-08-05 | 2017-09-05 | 2019-07-01 | 2019-07-01 | COMP | 2019-11-12 | COMP | 2019-11-19 | COMP | 2020-06-02 | NOTN | 2020-07-28 | COMP | Rule 16 | 21 | 457 | 94 | 6 |  |  | 748
4360 | 2017-08-05 | 2017-10-03 | 2018-04-21 | 2018-04-21 | COMP | 2019-06-17 | COMP | 2019-06-17 | INPR | 2020-02-29 | REQD | 2019-10-21 | COMP | Rule 16 | 41 | 137 | 290 |  |  |  | 555
4547 | 2017-08-05 | 2018-01-26 | 2018-05-12 | 2018-05-12 | COMP | 2018-05-23 | COMP | 2020-02-24 | COMP | 2020-01-15 | COMP | 2020-03-02 | COMP | Rule 16 | 118 | 75 | 8 | 439 | 0 | 6 | 643
2183 | 2017-08-06 | 2017-10-05 | 2018-04-09 | 2018-04-09 | COMP | 2018-07-03 | COMP | 2019-02-07 | COMP | 2019-04-15 | COMP | 2019-07-15 | COMP | Rule 15/16 | 43 | 126 | 61 | 150 | 47 | 64 | 486
4471 | 2017-08-06 | 2017-12-28 | 2018-03-08 | 2018-03-23 | COMP | 2018-05-15 | COMP | 2018-05-15 | COMP | 2021-03-27 | INPR | 2020-03-24 | COMP | Rule 16 | 99 | 48 | 38 | 1 |  |  | 659
1892 | 2017-08-07 | 2017-08-16 | 2017-09-02 | 2017-09-02 | COMP | 2018-11-13 | COMP | 2018-12-13 | COMP | 2018-12-13 | COMP | 2019-01-02 | COMP | Rule 16 | 8 | 13 | 300 | 21 | 1 | 13 | 352
1923 | 2017-08-07 | 2017-08-23 | 2018-03-20 | 2018-10-25 | COMP | 2019-01-24 | COMP | 2019-02-14 | COMP | 2019-01-25 | COMP | 2019-03-01 | COMP | Rule 15/16 | 13 | 142 | 60 | 16 | 0 | 11 | 392
2043 | 2017-08-07 | 2017-09-11 | 2017-12-14 | 2017-12-14 | COMP | 2020-07-21 | COMP | 2021-03-11 | COMP | 2021-06-26 | COMP | 2021-04-22 | COMP | Rule 16 | 25 | 66 | 654 | 160 | 76 |  | 932
2171 | 2017-08-07 | 2017-10-04 | 2017-10-24 | 2017-10-24 | COMP | 2017-10-30 | COMP | 2017-10-30 | COMP | 2017-10-31 | COMP | 2021-01-20 | COMP | Rule 16 | 42 | 15 | 5 | 1 | 2 | 807 | 867
2457 | 2017-08-07 | 2017-12-05 | 2018-04-28 | 2018-04-28 | COMP | 2018-05-30 | COMP | 2018-05-30 | COMP | 2019-04-05 | COMP | 2019-09-17 | COMP | Rule 16 | 83 | 100 | 22 | 1 | 214 | 115 | 531
2634 | 2017-08-07 | 2018-01-09 | 2019-01-04 | 2019-01-04 | COMP | 2019-02-25 | COMP | 2019-02-26 | COMP | 2019-12-28 | INPR | 2019-09-04 | COMP | Rule 15/16 | 106 | 249 | 35 | 2 |  |  | 522
3060 | 2017-08-07 | 2018-03-07 | 2018-06-14 | 2018-06-14 | COMP | 2018-08-08 | COMP | 2018-09-27 | COMP | 2020-03-17 | COMP | 2020-05-07 | COMP | Other | 145 | 71 | 39 | 36 | 367 | 38 | 691
4279 | 2017-08-07 | 2020-03-09 | 2020-11-02 | 2020-11-02 | COMP | 2021-05-14 | COMP | 2021-05-14 | COMP |  | INPR | 2021-10-04 | COMP | Rule 16 | 648 | 169 | 133 | 1 |  |  | 1046
4466 | 2017-08-07 | 2017-12-21 | 2018-04-11 | 2018-04-11 | COMP | 2018-06-12 | COMP | 2018-06-12 | COMP | 2019-11-24 | INPR | 2019-07-16 | COMP | Rule 16 | 95 | 76 | 44 | 1 |  |  | 487
5711 | 2017-08-07 | 2018-06-26 | 2019-05-20 | 2019-05-20 | COMP | 2019-05-28 | COMP | 2020-07-10 | COMP | 2020-07-02 | COMP | 2020-07-16 | COMP | Rule 16 | 223 | 226 | 6 | 284 | 0 | 5 | 740
9595 | 2017-08-07 | 2019-02-07 | 2019-09-06 | 2019-09-06 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-10-30 | COMP | 2020-01-27 | COMP | Rule 16 | 377 | 148 | 26 | 1 | 14 | 58 | 619
9611 | 2017-08-07 | 2019-02-08 | 2019-08-29 | 2020-04-15 | COMP | 2020-05-19 | COMP | 2021-11-16 | COMP | 2021-10-07 | COMP | 2021-12-08 | COMP | Rule 15/16 | 378 | 142 | 25 | 378 | 0 | 15 | 1090
13911 | 2017-08-07 | 2019-08-15 | 2020-02-28 | 2020-02-28 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-10-02 | COMP | 2021-01-10 | COMP | Rule 16 | 509 | 134 | 50 | 1 | 105 | 66 | 860
16978 | 2017-08-07 | 2020-01-27 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2022-07-16 | INPR | 2020-07-30 | COMP | Rule 16 | 619 | 30 | 57 | 1 |  |  | 750
1976 | 2017-08-08 | 2017-08-31 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-11 | COMP | 2019-01-16 | COMP | 2019-03-06 | COMP | 2019-05-14 | COMP | Rule 16 | 18 | 319 | 23 | 4 | 34 | 50 | 443
2052 | 2017-08-08 | 2017-09-14 | 2018-06-27 | 2018-06-27 | COMP | 2018-07-27 | COMP | 2018-08-06 | COMP | 2019-05-07 | COMP | 2019-06-24 | COMP | Rule 16 | 27 | 197 | 22 | 7 | 189 | 34 | 471
2248 | 2017-08-08 | 2017-10-23 | 2018-04-02 | 2018-04-02 | COMP | 2019-07-19 | COMP | 2019-09-05 | COMP | 2020-05-26 | COMP | 2020-07-24 | COMP | Rule 16 | 54 | 109 | 328 | 34 | 181 | 44 | 745
3049 | 2017-08-08 | 2018-03-03 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-11 | COMP | 2018-10-17 | COMP | 2019-09-21 | INPR | 2019-06-13 | COMP | Rule 15/16 | 141 | 141 | 16 | 5 |  |  | 464
3633 | 2017-08-08 | 2018-05-30 | 2019-02-21 | 2019-02-21 | COMP | 2020-02-28 | COMP | 2021-08-12 | COMP | 2021-08-24 | COMP | 2022-03-26 | COMP | Rule 15/16 | 203 | 183 | 257 | 369 | 9 | 148 | 1164
3679 | 2017-08-08 | 2018-06-06 | 2018-12-30 | 2022-02-28 | COMP |  | INPR | 2021-12-28 | COMP | 2022-02-15 | COMP | 2022-03-26 | COMP | Rule 15/16 | 208 | 142 |  |  | 35 | 28 | 1164
4381 | 2017-08-08 | 2017-11-08 | 2018-01-29 | 2018-05-14 | COMP | 2018-05-21 | COMP | 2018-05-21 | COMP | 2018-05-31 | COMP | 2019-07-02 | COMP | Rule 16 | 66 | 53 | 6 | 1 | 8 | 274 | 477
4669 | 2017-08-08 | 2018-03-06 | 2018-07-05 | 2018-07-05 | COMP | 2018-09-04 | COMP | 2018-09-21 | COMP | 2019-10-21 | INPR | 2019-01-29 | COMP | Rule 16 | 143 | 86 | 43 | 14 |  |  | 369
4670 | 2017-08-08 | 2018-03-06 | 2018-07-05 | 2018-07-05 | COMP | 2018-09-04 | COMP | 2018-09-21 | COMP | 2018-11-02 | COMP | 2019-01-31 | COMP | Rule 16 | 143 | 86 | 43 | 14 | 31 | 59 | 371
4839 | 2017-08-08 | 2018-04-09 | 2018-07-19 | 2018-07-19 | COMP | 2018-12-07 | COMP | 2018-12-10 | COMP | 2018-12-07 | COMP | 2019-01-14 | COMP | Rule 16 | 167 | 72 | 98 | 2 | 0 | 24 | 359
5361 | 2017-08-08 | 2018-05-24 | 2018-07-26 | 2018-07-26 | COMP | 2018-11-28 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-03-30 | COMP | Rule 16 | 200 | 44 | 86 | 2 | 1 | 83 | 411
6032 | 2017-08-08 | 2018-07-19 | 2019-01-09 | 2019-03-27 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-10-21 | COMP | 2019-12-12 | COMP | Rule 16 | 238 | 119 | 8 | 1 | 139 | 36 | 589
6341 | 2017-08-08 | 2018-08-13 | 2018-10-02 | 2018-10-02 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2023-07-01 | INPR | 2022-04-27 | COMP | Rule 16 | 255 | 36 | 58 | 1 |  |  | 1187
1975 | 2017-08-09 | 2017-08-31 | 2018-05-31 | 2018-05-31 | COMP | 2018-06-04 | COMP | 2018-06-06 | COMP | 2019-07-03 | COMP | 2019-07-17 | COMP | Rule 15/16 | 17 | 187 | 3 | 3 | 271 | 10 | 486
2084 | 2017-08-09 | 2017-09-20 | 2018-01-15 | 2018-01-15 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-08-20 | COMP | 2019-10-14 | COMP | Rule 16 | 30 | 78 | 384 | 1 | 20 | 39 | 548
2088 | 2017-08-09 | 2017-09-21 | 2018-08-06 | 2019-08-28 | COMP | 2018-08-05 | NOTN | 2019-05-06 | COMP | 2018-08-05 | COMP | 2019-12-17 | COMP | Other | 31 | 219 |  |  | 0 | 156 | 591
2090 | 2017-08-09 | 2017-09-21 | 2017-09-25 | 2017-09-25 | COMP | 2017-10-12 | COMP | 2017-10-12 | COMP | 2017-11-08 | COMP | 2021-09-29 | COMP | Rule 16 | 31 | 3 | 14 | 1 | 20 | 977 | 1041
2133 | 2017-08-09 | 2017-09-27 | 2018-08-24 | 2018-08-24 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2023-02-25 | INPR | 2020-01-06 | COMP | Rule 16 | 35 | 229 | 71 | 1 |  |  | 603
2222 | 2017-08-09 | 2017-10-16 | 2017-12-08 | 2017-12-08 | COMP | 2018-08-31 | NOTN | 2018-09-07 | COMP | 2019-08-31 | INPR | 2019-05-09 | COMP | Rule 16 | 48 | 37 |  | 189 |  |  | 439
2500 | 2017-08-09 | 2017-12-11 | 2018-05-23 | 2018-05-23 | COMP | 2019-04-08 | COMP | 2019-04-10 | COMP | 2019-11-23 | INPR | 2019-07-26 | COMP | Rule 16 | 85 | 114 | 219 | 3 |  |  | 493
3199 | 2017-08-09 | 2018-03-21 | 2018-08-08 | 2018-08-08 | COMP | 2020-11-04 | COMP | 2021-05-06 | COMP | 2021-05-04 | COMP | 2021-06-02 | COMP | Rule 15/16 | 153 | 99 | 566 | 125 | 0 | 19 | 958
3444 | 2017-08-09 | 2018-04-28 | 2019-04-20 | 2019-04-20 | COMP | 2019-08-23 | COMP | 2019-09-26 | COMP | 2019-12-10 | COMP | 2019-11-15 | COMP | Rule 16 | 180 | 245 | 88 | 24 | 51 |  | 571
3732 | 2017-08-09 | 2018-06-19 | 2019-03-03 | 2019-03-03 | COMP | 2019-03-06 | COMP | 2019-03-19 | COMP | 2019-03-07 | COMP | 2019-04-11 | COMP | Rule 15/16 | 216 | 175 | 3 | 10 | 0 | 18 | 419
3750 | 2017-08-09 | 2018-06-27 | 2018-09-14 | 2018-09-14 | COMP | 2020-02-12 | NOTN | 2020-03-09 | COMP | 2020-02-12 | COMP | 2020-09-10 | COMP | Other | 222 | 56 |  | 370 | 0 | 132 | 777
3799 | 2017-08-09 | 2018-07-18 | 2018-09-23 | 2018-09-23 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2019-08-06 | COMP | 2019-11-14 | COMP | Other | 236 | 47 | 91 | 1 | 128 | 71 | 570
3808 | 2017-08-09 | 2018-07-24 | 2018-10-02 | 2018-10-02 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP |  | INPR | 2019-11-18 | COMP | Other | 240 | 50 | 239 | 1 |  |  | 572
3809 | 2017-08-09 | 2018-07-24 | 2018-10-03 | 2018-10-03 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2019-08-06 | COMP | 2019-11-14 | COMP | Other | 240 | 51 | 84 | 1 | 128 | 71 | 570
3810 | 2017-08-09 | 2018-07-24 | 2018-09-17 | 2018-09-17 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2020-02-19 | COMP | 2019-11-18 | COMP | Other | 240 | 39 | 250 | 1 | 107 |  | 572
3813 | 2017-08-09 | 2018-07-26 | 2018-09-26 | 2018-09-23 | COMP | 2019-02-05 | COMP | 2019-02-05 | INPR | 2019-08-07 | COMP | 2019-10-02 | COMP | Other | 242 | 44 | 91 |  |  |  | 540
3818 | 2017-08-09 | 2018-07-31 | 2018-09-25 | 2018-09-25 | COMP | 2019-02-05 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-10-31 | COMP | Other | 245 | 40 | 90 | 129 | 1 | 61 | 561
5629 | 2017-08-09 | 2018-06-21 | 2018-10-04 | 2018-10-04 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2018-12-26 | COMP | 2019-01-09 | COMP | Rule 16 | 218 | 74 | 22 | 1 | 35 | 10 | 355
11174 | 2017-08-09 | 2019-04-16 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-19 | COMP | 2019-10-21 | COMP | 2019-11-06 | COMP | 2020-01-08 | COMP | Rule 16 | 422 | 101 | 10 | 23 | 13 | 41 | 605
39582 | 2017-08-09 | 2022-10-27 | 2023-01-29 | 2023-03-22 | COMP | 2023-03-22 | NOTN | 2023-08-22 | COMP | 2023-09-27 | COMP | 2023-11-01 | COMP | Other | 1313 | 61 |  | 107 | 26 | 26 | 1566
1940 | 2017-08-10 | 2017-08-23 | 2017-11-27 | 2017-11-27 | COMP | 2017-12-11 | COMP | 2017-12-11 | COMP | 2018-01-12 | COMP | 2019-01-16 | COMP | Other | 10 | 65 | 11 | 1 | 23 | 254 | 359
1987 | 2017-08-10 | 2017-09-02 | 2017-11-27 | 2017-11-27 | COMP | 2018-03-26 | COMP | 2018-03-26 | COMP | 2019-08-26 | COMP | 2019-10-01 | COMP | Rule 16 | 17 | 57 | 82 | 1 | 359 | 26 | 538
1991 | 2017-08-10 | 2017-09-06 | 2018-03-07 | 2018-03-07 | COMP | 2018-05-03 | COMP | 2018-07-30 | COMP | 2018-11-28 | COMP | 2019-07-12 | COMP | Rule 15/16 | 19 | 124 | 42 | 61 | 84 | 157 | 482
2050 | 2017-08-10 | 2017-09-13 | 2018-01-17 | 2018-01-17 | COMP | 2019-01-28 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-03-01 | COMP | Rule 15/16 | 24 | 85 | 259 | 6 | 1 | 19 | 389
2086 | 2017-08-10 | 2017-09-21 | 2018-04-13 | 2018-04-13 | COMP | 2018-06-12 | COMP | 2018-10-10 | COMP | 2019-02-12 | COMP | 2019-04-10 | COMP | Rule 16 | 30 | 140 | 42 | 85 | 84 | 41 | 417
2155 | 2017-08-10 | 2017-10-02 | 2017-11-22 | 2017-11-22 | COMP | 2018-01-04 | COMP | 2018-03-01 | COMP | 2018-03-20 | COMP | 2022-07-04 | COMP | Rule 16 | 37 | 37 | 28 | 39 | 14 | 1080 | 1230
2158 | 2017-08-10 | 2017-10-02 | 2018-06-09 | 2018-06-09 | COMP | 2018-12-28 | COMP | 2018-12-31 | COMP | 2019-09-21 | INPR | 2019-04-19 | COMP | Rule 15/16 | 37 | 172 | 139 | 2 |  |  | 424
2191 | 2017-08-10 | 2017-10-05 | 2018-03-17 | 2018-03-17 | COMP | 2020-11-05 | COMP | 2020-11-05 | COMP | 2021-09-30 | COMP | 2021-11-02 | COMP | Rule 15/16 | 40 | 110 | 667 | 1 | 226 | 24 | 1064
2436 | 2017-08-10 | 2017-11-29 | 2018-07-09 | 2018-07-09 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-01-16 | COMP | 2019-04-30 | COMP | Rule 15/16 | 76 | 153 | 150 | 1 | 0 | 55 | 431
2437 | 2017-08-10 | 2017-11-29 | 2018-07-12 | 2018-07-12 | COMP | 2019-08-23 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-03-19 | COMP | Rule 15/16 | 76 | 156 | 282 | 57 | 1 | 86 | 653
4359 | 2017-08-10 | 2017-10-02 | 2018-05-10 | 2018-05-10 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-10-19 | INPR | 2019-07-12 | COMP | Rule 15/16 | 37 | 152 | 198 | 1 |  |  | 482
4781 | 2017-08-10 | 2018-03-29 | 2018-08-20 | 2018-08-20 | COMP | 2020-03-17 | COMP | 2020-04-29 | COMP |  |  | 2020-06-24 | COMP | Rule 16 | 158 | 101 | 394 | 32 |  |  | 721
5592 | 2017-08-10 | 2018-06-18 | 2018-06-28 | 2018-07-20 | COMP | 2018-07-25 | COMP | 2018-07-25 | COMP | 2018-10-31 | COMP | 2019-03-14 | COMP | Rule 16 | 214 | 9 | 4 | 1 | 70 | 90 | 398
5955 | 2017-08-10 | 2018-07-16 | 2018-11-16 | 2018-11-16 | COMP | 2019-04-25 | COMP | 2019-09-24 | COMP | 2019-10-15 | COMP | 2019-10-23 | COMP | Rule 16 | 233 | 88 | 109 | 106 | 16 | 7 | 554
1974 | 2017-08-11 | 2017-08-30 | 2017-09-18 | 2017-09-18 | COMP | 2017-09-25 | COMP | 2017-09-25 | COMP | 2019-03-20 | COMP | 2019-03-27 | COMP | Rule 16 | 14 | 13 | 6 | 1 | 371 | 6 | 406
1992 | 2017-08-11 | 2017-09-05 | 2019-03-25 | 2019-03-25 | COMP | 2019-12-04 | COMP | 2019-12-10 | INPR | 2020-08-06 | COMP | 2020-02-03 | COMP | Rule 16 | 17 | 388 | 177 |  |  |  | 620
2318 | 2017-08-11 | 2017-11-02 | 2018-01-09 | 2018-01-09 | COMP | 2018-06-13 | COMP | 2018-10-29 | COMP | 2019-06-29 | INPR | 2019-03-07 | COMP | Rule 16 | 59 | 44 | 109 | 97 |  |  | 392
2372 | 2017-08-11 | 2017-11-13 | 2017-11-19 | 2017-11-19 | COMP | 2017-12-04 | NOTN | 2017-12-04 | COMP | 2018-07-10 | COMP | 2020-12-09 | COMP | Rule 16 | 65 | 5 |  | 9 | 151 | 609 | 836
3424 | 2017-08-11 | 2018-04-25 | 2018-04-26 | 2018-04-26 | COMP | 2018-04-30 | COMP | 2019-04-20 | REQD | 2018-05-21 | COMP | 2019-01-10 | COMP | Rule 16 | 176 | 2 | 3 |  |  |  | 354
4778 | 2017-08-11 | 2018-03-30 | 2018-08-24 | 2018-08-24 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-07-24 | COMP | 2019-08-23 | COMP | Rule 15/16 | 158 | 104 | 70 | 1 | 160 | 23 | 511
8591 | 2017-08-11 | 2018-12-11 | 2019-01-31 | 2019-02-15 | COMP | 2019-02-19 | NOTN | 2019-08-07 | COMP | 2019-09-03 | COMP | 2019-09-17 | COMP | Rule 16 | 334 | 35 |  | 121 | 19 | 11 | 527
7657 | 2017-08-13 | 2018-10-24 | 2019-03-31 | 2019-03-31 | COMP | 2019-08-13 | COMP | 2019-09-04 | NOTN | 2019-08-30 | COMP | 2019-09-13 | COMP | Rule 16 | 302 | 106 | 95 |  |  |  | 524
1952 | 2017-08-14 | 2017-08-25 | 2017-11-01 | 2017-11-01 | COMP | 2017-11-30 | COMP | 2018-04-25 | COMP | 2018-12-06 | COMP | 2020-01-29 | COMP | Rule 16 | 10 | 48 | 19 | 101 | 156 | 287 | 616
1956 | 2017-08-14 | 2017-08-25 | 2018-01-19 | 2018-01-19 | COMP | 2019-05-07 | COMP | 2018-10-22 | COMP | 2019-05-09 | COMP | 2019-07-14 | COMP | Rule 16 | 10 | 99 | 327 |  | 137 | 45 | 480
2099 | 2017-08-14 | 2017-09-25 | 2018-05-10 | 2018-05-10 | COMP | 2018-05-29 | COMP | 2018-06-20 | COMP | 2020-12-15 | COMP | 2021-01-13 | COMP | Rule 16 | 30 | 157 | 13 | 17 | 626 | 20 | 858
2103 | 2017-08-14 | 2017-09-25 | 2017-11-17 | 2017-11-17 | COMP | 2018-09-24 | COMP | 2018-09-27 | COMP | 2019-04-07 | COMP | 2019-06-10 | COMP | Rule 16 | 30 | 39 | 213 | 4 | 130 | 45 | 457
2217 | 2017-08-14 | 2017-10-14 | 2017-12-05 | 2018-04-30 | COMP | 2018-08-21 | COMP | 2018-10-05 | COMP | 2019-11-13 | COMP | 2019-12-27 | COMP | Rule 15/16 | 44 | 34 | 80 | 33 | 278 | 30 | 595
2367 | 2017-08-14 | 2017-11-14 | 2018-01-02 | 2018-01-02 | COMP | 2018-05-15 | COMP | 2018-12-28 | COMP | 2019-02-26 | COMP | 2019-01-03 | COMP | Rule 15/16 | 65 | 32 | 94 | 157 | 40 |  | 348
2642 | 2017-08-14 | 2018-01-10 | 2018-02-08 | 2018-02-08 | COMP | 2018-04-10 | COMP | 2018-04-10 | COMP | 2019-02-20 | COMP | 2019-04-09 | COMP | Rule 16 | 102 | 21 | 43 | 1 | 217 | 35 | 414
2688 | 2017-08-14 | 2018-01-18 | 2018-02-23 | 2018-02-23 | COMP | 2018-04-19 | COMP | 2018-04-26 | COMP | 2019-04-08 | COMP | 2019-06-06 | COMP | Rule 16 | 107 | 26 | 40 | 6 | 238 | 43 | 455
3175 | 2017-08-14 | 2018-03-18 | 2018-08-07 | 2018-08-07 | COMP | 2018-11-30 | COMP | 2018-11-30 | COMP | 2019-01-08 | COMP | 2019-01-23 | COMP | Rule 16 | 147 | 100 | 80 | 1 | 26 | 11 | 361
3386 | 2017-08-14 | 2018-04-17 | 2018-08-25 | 2018-09-13 | COMP | 2019-02-27 | COMP | 2019-02-27 | COMP | 2019-12-28 | INPR | 2019-05-13 | COMP | Rule 16 | 169 | 92 | 113 | 1 |  |  | 438
4526 | 2017-08-14 | 2018-01-23 | 2018-09-05 | 2018-09-05 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-09-20 | COMP | 2019-10-17 | COMP | Rule 15/16 | 110 | 158 | 220 | 1 | 44 | 20 | 548
7072 | 2017-08-14 | 2018-09-25 | 2019-07-25 | 2019-08-19 | COMP | 2019-09-23 | COMP | 2021-02-27 | REQD | 2021-02-27 | REQD | 2019-11-20 | COMP | Rule 16 | 281 | 209 | 25 |  |  |  | 571
23425 | 2017-08-14 | 2020-11-05 | 2021-03-01 | 2021-03-01 | COMP | 2021-04-27 | COMP | 2021-04-27 | COMP | 2021-08-20 | COMP | 2021-11-30 | COMP | Rule 15/16 | 814 | 76 | 42 | 1 | 82 | 69 | 1079
1943 | 2017-08-15 | 2017-08-23 | 2017-10-20 | 2017-10-20 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-11-19 | COMP | 2019-12-06 | COMP | Rule 16 | 7 | 42 | 326 | 1 | 197 | 12 | 580
1984 | 2017-08-15 | 2017-09-01 | 2018-01-16 | 2020-03-28 | COMP | 2020-06-24 | COMP | 2020-06-08 | COMP | 2020-07-03 | COMP | 2020-08-11 | COMP | Rule 15/16 | 14 | 91 | 62 |  | 20 | 28 | 752
1990 | 2017-08-15 | 2017-09-03 | 2018-05-01 | 2018-05-01 | COMP | 2019-06-17 | COMP | 2020-05-13 | COMP | 2020-06-17 | COMP | 2020-10-13 | COMP | Rule 15/16 | 14 | 164 | 284 | 229 | 25 | 84 | 796
2096 | 2017-08-15 | 2017-09-22 | 2019-01-04 | 2019-01-04 | COMP | 2018-12-21 | COMP | 2019-01-11 | INPR | 2019-02-12 | COMP | 2019-07-23 | COMP | Rule 15/16 | 28 | 321 |  |  |  |  | 486
2185 | 2017-08-15 | 2017-10-05 | 2017-10-30 | 2017-10-30 | COMP | 2018-04-04 | COMP | 2018-04-04 | COMP | 2019-07-15 | COMP | 2019-08-30 | COMP | Rule 15/16 | 37 | 18 | 106 | 1 | 322 | 35 | 514
2486 | 2017-08-15 | 2017-12-07 | 2018-04-13 | 2018-04-13 | COMP | 2018-08-29 | COMP | 2019-01-22 | COMP | 2019-01-24 | COMP | 2019-05-17 | COMP | Rule 16 | 79 | 88 | 97 | 98 | 3 | 81 | 441
2879 | 2017-08-15 | 2018-02-09 | 2018-05-19 | 2018-05-19 | COMP | 2019-05-14 | COMP | 2019-06-06 | INPR | 2019-06-06 | COMP | 2020-06-30 | COMP | Rule 16 | 122 | 70 | 247 |  |  |  | 722
2899 | 2017-08-15 | 2018-02-14 | 2018-08-21 | 2018-08-21 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP |  | INPR | 2021-01-11 | COMP | Rule 16 | 125 | 132 | 47 | 1 |  |  | 855
3026 | 2017-08-15 | 2018-02-28 | 2018-05-02 | 2018-05-02 | COMP | 2018-05-21 | COMP | 2018-05-21 | COMP | 2021-09-08 | COMP | 2021-11-29 | COMP | Rule 16 | 134 | 46 | 14 | 1 | 831 | 56 | 1077
3053 | 2017-08-15 | 2018-03-03 | 2018-03-14 | 2018-03-14 | COMP | 2018-08-06 | COMP | 2019-07-01 | COMP | 2023-05-27 | INPR | 2019-08-09 | COMP | Rule 16 | 136 | 8 | 102 | 227 |  |  | 499
3491 | 2017-08-15 | 2018-05-07 | 2018-07-17 | 2018-07-17 | COMP | 2019-03-12 | COMP | 2019-03-19 | COMP | 2020-05-05 | COMP | 2020-06-29 | COMP | Other | 182 | 50 | 163 | 6 | 286 | 39 | 721
3492 | 2017-08-15 | 2018-05-07 | 2018-11-05 | 2018-11-05 | COMP | 2019-03-12 | COMP | 2019-03-28 | COMP | 2020-05-05 | COMP | 2020-06-29 | COMP | Other | 182 | 128 | 85 | 13 | 279 | 39 | 721
4703 | 2017-08-15 | 2018-03-16 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-07-21 | INPR | 2019-03-15 | COMP | Rule 16 | 146 | 207 | 6 | 1 |  |  | 396
1917 | 2017-08-16 | 2017-08-21 | 2017-10-27 | 2017-10-27 | COMP | 2017-11-27 | COMP | 2017-11-27 | COMP | 2018-12-19 | COMP | 2019-02-06 | COMP | Rule 16 | 4 | 49 | 19 | 1 | 268 | 33 | 369
1922 | 2017-08-16 | 2017-08-21 | 2018-12-13 | 2018-12-13 | COMP | 2018-12-28 | NOTN | 2018-12-28 | COMP | 2018-12-28 | COMP | 2019-04-24 | COMP | Rule 16 | 4 | 330 |  | 11 | 1 | 81 | 423
1973 | 2017-08-16 | 2017-08-30 | 2018-04-16 | 2018-04-16 | COMP | 2018-07-26 | COMP | 2018-08-21 | COMP | 2018-12-03 | COMP | 2019-01-08 | COMP | Rule 16 | 11 | 156 | 72 | 19 | 71 | 25 | 349
2071 | 2017-08-16 | 2017-09-18 | 2018-05-07 | 2018-05-07 | COMP | 2018-10-30 | COMP | 2018-11-02 | COMP | 2019-03-06 | COMP | 2020-05-19 | COMP | Rule 15/16 | 23 | 159 | 124 | 4 | 82 | 305 | 692
2080 | 2017-08-16 | 2017-09-20 | 2017-11-03 | 2017-11-03 | COMP | 2018-03-20 | COMP | 2018-03-20 | COMP | 2018-12-19 | COMP | 2019-02-04 | COMP | Rule 16 | 25 | 33 | 91 | 1 | 191 | 31 | 367
2113 | 2017-08-16 | 2017-09-26 | 2018-02-25 | 2019-02-14 | COMP | 2019-02-13 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-04-08 | COMP | Rule 16 | 29 | 102 |  | 6 | 1 | 33 | 411
2173 | 2017-08-16 | 2017-10-04 | 2017-11-27 | 2017-11-27 | COMP | 2018-03-10 | COMP | 2018-03-10 | COMP | 2019-04-01 | COMP | 2019-05-08 | COMP | Rule 16 | 35 | 36 | 71 | 0 | 266 | 28 | 433
2176 | 2017-08-16 | 2017-10-04 | 2018-08-27 | 2018-08-27 | COMP | 2018-11-28 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-16 | COMP | Rule 16 | 35 | 225 | 64 | 175 | 1 | 28 | 523
2712 | 2017-08-16 | 2018-01-23 | 2018-05-15 | 2018-05-15 | COMP | 2022-01-28 | COMP | 2023-01-12 | COMP | 2023-01-10 | COMP | 2023-02-14 | COMP | Rule 16 | 108 | 80 | 933 | 240 | 0 | 23 | 1380
2762 | 2017-08-16 | 2018-01-29 | 2018-09-10 | 2018-09-10 | COMP | 2019-06-27 | COMP | 2019-10-14 | COMP | 2019-11-13 | COMP | 2019-12-17 | COMP | Rule 16 | 112 | 157 | 201 | 76 | 22 | 23 | 586
3313 | 2017-08-16 | 2018-04-06 | 2018-09-17 | 2018-09-17 | COMP | 2018-10-04 | COMP | 2018-11-19 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | Rule 16 | 160 | 114 | 14 | 32 | 89 | 1 | 405
4464 | 2017-08-16 | 2017-12-16 | 2018-04-23 | 2018-04-23 | COMP | 2018-05-25 | COMP | 2018-10-25 | COMP | 2019-01-22 | COMP | 2019-05-07 | COMP | Rule 16 | 84 | 87 | 25 | 107 | 58 | 75 | 432
4582 | 2017-08-16 | 2018-02-06 | 2018-03-14 | 2018-03-14 | COMP | 2018-05-10 | COMP | 2018-05-16 | COMP | 2020-05-15 | COMP | 2020-06-15 | COMP | Rule 16 | 118 | 26 | 42 | 5 | 503 | 21 | 710
5581 | 2017-08-16 | 2018-06-15 | 2018-10-23 | 2018-10-23 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-09-25 | COMP | 2019-10-02 | COMP | Rule 16 | 209 | 91 | 43 | 1 | 190 | 6 | 535
8726 | 2017-08-16 | 2018-12-20 | 2018-12-21 | 2018-12-21 | COMP | 2019-03-05 | COMP | 2019-03-06 | COMP | 2019-03-21 | COMP | 2019-04-25 | COMP | Rule 16 | 338 | 2 | 49 | 2 | 12 | 26 | 424
2038 | 2017-08-17 | 2017-09-11 | 2017-10-25 | 2017-12-19 | COMP | 2018-04-17 | COMP | 2018-11-07 | COMP | 2019-02-19 | COMP | 2019-03-05 | COMP | Rule 15/16 | 17 | 33 | 82 | 144 | 68 | 11 | 386
2174 | 2017-08-17 | 2017-10-05 | 2018-02-23 | 2018-02-23 | COMP | 2018-04-11 | COMP | 2018-04-11 | COMP | 2019-01-22 | COMP | 2019-03-18 | COMP | Rule 16 | 35 | 95 | 34 | 1 | 196 | 39 | 395
2199 | 2017-08-17 | 2017-10-09 | 2018-03-30 | 2018-03-30 | COMP | 2019-08-04 | NOTN | 2019-08-04 | COMP | 2020-01-21 | COMP | 2020-02-21 | COMP | Other | 37 | 118 |  | 339 | 115 | 23 | 629
2490 | 2017-08-17 | 2017-12-08 | 2018-02-24 | 2018-02-24 | COMP | 2018-03-08 | COMP | 2018-03-08 | COMP | 2019-06-29 | INPR | 2019-03-19 | COMP | Rule 16 | 78 | 52 | 9 | 1 |  |  | 396
4721 | 2017-08-17 | 2018-03-22 | 2018-08-17 | 2020-07-01 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-04-20 | COMP | 2021-05-25 | COMP | Rule 16 | 148 | 105 | 40 | 1 | 163 | 26 | 947
4799 | 2017-08-17 | 2018-03-31 | 2018-06-26 | 2018-10-01 | COMP | 2018-10-09 | COMP | 2018-10-22 | COMP | 2021-02-27 | INPR | 2019-11-16 | COMP | Rule 15/16 | 154 | 61 | 7 | 10 |  |  | 565
11859 | 2017-08-17 | 2019-05-14 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2019-08-29 | COMP | 2019-11-01 | COMP | Rule 16 | 436 | 52 | 15 | 1 | 11 | 46 | 556
2126 | 2017-08-18 | 2017-09-27 | 2019-08-21 | 2019-08-21 | COMP | 2019-11-25 | COMP | 2019-12-10 | COMP | 2020-08-12 | COMP | 2020-10-14 | COMP | Rule 16 | 28 | 477 | 67 | 10 | 172 | 45 | 794
2266 | 2017-08-18 | 2017-10-26 | 2018-02-21 | 2018-02-21 | COMP | 2018-07-12 | COMP | 2019-07-09 | COMP | 2019-07-12 | COMP | 2019-07-25 | COMP | Rule 15/16 | 49 | 78 | 100 | 249 | 4 | 10 | 485
2267 | 2017-08-18 | 2017-10-26 | 2018-05-02 | 2018-05-02 | COMP | 2018-11-02 | COMP | 2018-11-14 | COMP | 2022-08-21 | INPR | 2021-01-07 | COMP | Rule 16 | 49 | 128 | 130 | 8 |  |  | 850
2814 | 2017-08-18 | 2018-02-05 | 2018-02-14 | 2018-02-14 | COMP | 2018-11-30 | COMP | 2019-08-13 | COMP | 2019-10-05 | COMP | 2019-11-21 | COMP | Rule 15/16 | 115 | 8 | 201 | 177 | 38 | 33 | 568
2965 | 2017-08-18 | 2018-02-24 | 2018-03-25 | 2018-03-25 | COMP | 2019-07-12 | COMP | 2018-03-26 | COMP | 2020-02-26 | COMP | 2020-02-19 | COMP | Other | 128 | 20 | 328 |  | 483 |  | 626
3121 | 2017-08-18 | 2018-03-11 | 2018-08-09 | 2018-08-09 | COMP | 2018-10-02 | COMP | 2018-10-18 | COMP | 2020-07-04 | INPR | 2019-04-17 | COMP | Rule 15/16 | 138 | 107 | 38 | 13 |  |  | 416
3172 | 2017-08-18 | 2018-03-16 | 2018-07-16 | 2018-07-16 | COMP | 2019-04-18 | COMP | 2020-06-22 | COMP | 2020-07-16 | COMP | 2020-08-07 | COMP | Rule 16 | 143 | 85 | 191 | 297 | 19 | 17 | 747
5559 | 2017-08-18 | 2018-06-14 | 2018-07-02 | 2019-07-31 | COMP | 2019-08-22 | COMP | 2018-07-17 | COMP | 2020-07-28 | COMP | 2020-10-02 | COMP | Rule 16 | 206 | 13 | 17 |  | 512 | 48 | 786
6800 | 2017-08-18 | 2018-09-11 | 2019-02-15 | 2019-09-17 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2021-02-27 | INPR | 2020-01-02 | COMP | Rule 15/16 | 267 | 108 | 20 | 1 |  |  | 594
1924 | 2017-08-19 | 2017-08-24 | 2018-03-08 | 2018-03-08 | COMP | 2018-04-30 | COMP | 2018-05-25 | COMP | 2019-08-07 | COMP | 2020-01-28 | COMP | Rule 16 | 4 | 133 | 38 | 20 | 302 | 118 | 610
4581 | 2017-08-20 | 2018-02-06 | 2018-03-15 | 2018-03-15 | COMP | 2018-04-24 | COMP | 2018-04-24 | COMP | 2018-10-18 | COMP | 2019-01-08 | COMP | Rule 16 | 115 | 27 | 29 | 1 | 125 | 54 | 346
1995 | 2017-08-21 | 2017-09-05 | 2017-12-07 | 2017-12-07 | COMP |  | REQD |  | REQD |  | REQD | 2021-03-17 | COMP | Other | 11 | 65 |  |  |  |  | 896
2047 | 2017-08-21 | 2017-09-13 | 2017-10-25 | 2019-07-09 | COMP | 2019-10-02 | COMP | 2017-10-27 | COMP | 2020-02-04 | COMP | 2020-02-18 | COMP | Rule 16 | 17 | 31 | 61 |  | 567 | 10 | 624
2197 | 2017-08-21 | 2017-10-09 | 2018-02-01 | 2018-02-01 | COMP | 2018-02-15 | COMP | 2018-03-15 | COMP | 2019-04-02 | COMP | 2019-07-23 | COMP | Rule 16 | 35 | 78 | 11 | 20 | 264 | 79 | 482
2283 | 2017-08-21 | 2017-10-28 | 2018-01-13 | 2018-05-07 | COMP | 2018-08-31 | COMP | 2019-02-28 | COMP | 2019-02-28 | COMP | 2019-03-23 | COMP | Rule 16 | 49 | 50 | 83 | 122 | 1 | 17 | 397
2328 | 2017-08-21 | 2017-11-03 | 2018-10-10 | 2018-10-10 | COMP | 2018-12-26 | COMP | 2019-03-26 | COMP | 2019-07-21 | INPR | 2019-04-10 | COMP | Rule 16 | 54 | 234 | 52 | 62 |  |  | 410
2825 | 2017-08-21 | 2018-02-06 | 2018-08-02 | 2018-08-02 | COMP | 2018-08-24 | COMP | 2018-09-07 | COMP | 2018-09-06 | COMP | 2019-01-14 | COMP | Rule 15/16 | 115 | 125 | 17 | 10 | 0 | 87 | 350
3718 | 2017-08-21 | 2018-06-15 | 2018-09-20 | 2018-09-20 | COMP | 2018-09-27 | COMP | 2018-09-28 | COMP | 2019-12-16 | COMP | 2020-01-07 | COMP | Rule 15/16 | 206 | 68 | 6 | 2 | 304 | 15 | 596
4392 | 2017-08-21 | 2017-11-15 | 2018-02-22 | 2018-02-22 | COMP | 2019-08-06 | COMP | 2019-04-30 | COMP | 2019-07-31 | COMP | 2019-08-24 | COMP | Rule 15/16 | 61 | 66 | 367 |  | 65 | 18 | 505
1935 | 2017-08-22 | 2017-08-23 | 2017-11-03 | 2017-11-03 | COMP | 2018-05-15 | COMP | 2018-06-04 | COMP | 2019-12-26 | COMP | 2020-02-03 | COMP | Other | 2 | 52 | 131 | 14 | 393 | 26 | 613
2083 | 2017-08-22 | 2017-09-20 | 2018-02-08 | 2018-02-08 | COMP | 2018-10-23 | COMP | 2019-01-14 | COMP | 2019-04-08 | COMP | 2019-06-20 | COMP | Rule 15/16 | 21 | 96 | 180 | 55 | 59 | 53 | 459
2091 | 2017-08-22 | 2017-09-22 | 2018-08-08 | 2018-08-08 | COMP | 2018-08-13 | COMP | 2018-09-10 | COMP | 2019-04-02 | COMP | 2019-05-28 | COMP | Rule 16 | 23 | 220 | 4 | 20 | 140 | 40 | 442
2125 | 2017-08-22 | 2017-09-27 | 2018-01-05 | 2018-01-05 | COMP | 2018-06-05 | COMP | 2019-09-27 | COMP | 2019-10-13 | COMP | 2019-12-19 | COMP | Rule 15/16 | 26 | 68 | 105 | 332 | 11 | 46 | 584
2137 | 2017-08-22 | 2017-09-28 | 2018-01-12 | 2018-01-12 | COMP | 2018-03-06 | COMP | 2018-03-14 | COMP |  |  | 2019-02-06 | COMP | Rule 16 | 27 | 72 | 36 | 7 |  |  | 365
2275 | 2017-08-22 | 2017-10-27 | 2017-12-15 | 2017-12-15 | COMP | 2018-03-23 | COMP | 2018-03-23 | COMP | 2020-04-30 | COMP | 2020-06-24 | COMP | Rule 16 | 48 | 33 | 67 | 1 | 530 | 39 | 713
2370 | 2017-08-22 | 2017-11-13 | 2018-01-08 | 2018-01-08 | COMP | 2018-04-20 | COMP | 2018-04-26 | COMP |  |  | 2019-03-13 | COMP | Rule 16 | 58 | 37 | 73 | 5 |  |  | 389
2568 | 2017-08-22 | 2017-12-27 | 2018-03-26 | 2018-03-26 | COMP | 2018-08-29 | COMP | 2018-08-29 | COMP | 2019-03-25 | COMP | 2019-05-10 | COMP | Rule 16 | 87 | 61 | 111 | 1 | 141 | 35 | 431
4458 | 2017-08-22 | 2017-12-14 | 2018-08-15 | 2018-08-15 | COMP | 2018-09-19 | COMP | 2018-10-26 | COMP | 2020-07-25 | INPR | 2019-07-08 | COMP | Rule 15/16 | 79 | 169 | 25 | 28 |  |  | 470
5001 | 2017-08-22 | 2018-04-23 | 2018-06-25 | 2018-06-25 | COMP | 2018-08-30 | COMP | 2018-08-30 | COMP | 2018-11-20 | COMP | 2019-01-21 | COMP | Rule 16 | 167 | 45 | 48 | 1 | 57 | 40 | 353
5106 | 2017-08-22 | 2018-04-30 | 2018-08-16 | 2018-08-16 | COMP | 2018-10-01 | COMP | 2018-11-13 | COMP | 2018-11-07 | COMP | 2019-01-29 | COMP | Rule 16 | 172 | 77 | 32 | 31 | 0 | 51 | 359
5107 | 2017-08-22 | 2018-04-30 | 2018-08-23 | 2018-08-23 | COMP | 2018-11-08 | COMP | 2018-11-08 | COMP | 2020-03-21 | REQD | 2019-08-12 | COMP | Rule 15/16 | 172 | 82 | 55 | 1 |  |  | 495
5439 | 2017-08-22 | 2018-05-31 | 2018-08-13 | 2018-08-13 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2018-12-10 | COMP | 2019-01-04 | COMP | Rule 16 | 194 | 52 | 56 | 1 | 27 | 18 | 343
6263 | 2017-08-22 | 2018-08-07 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-19 | COMP | 2019-04-09 | COMP | 2024-02-03 | INPR | 2020-01-13 | COMP | Rule 16 | 241 | 114 | 20 | 36 |  |  | 599
6707 | 2017-08-22 | 2018-09-10 | 2019-09-11 | 2019-09-11 | COMP | 2020-10-29 | COMP | 2021-10-28 | COMP | 2023-02-13 | COMP | 2023-06-08 | COMP | Rule 15/16 | 264 | 253 | 288 | 251 | 323 | 82 | 1456
39120 | 2017-08-22 | 2022-10-03 | 2022-12-30 | 2022-12-30 | COMP | 2023-06-27 | NOTN | 2023-10-11 | COMP |  | INPR | 2023-12-06 | COMP | Other | 1286 | 61 |  | 197 |  |  | 1579
2120 | 2017-08-23 | 2017-09-27 | 2018-01-12 | 2018-01-12 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-11-07 | COMP | 2020-01-06 | COMP | Rule 16 | 25 | 73 | 438 | 1 | 23 | 38 | 593
2130 | 2017-08-23 | 2017-09-27 | 2018-01-12 | 2018-01-12 | COMP | 2018-03-06 | COMP | 2019-03-07 | COMP | 2019-07-17 | COMP | 2019-09-06 | COMP | Rule 16 | 25 | 73 | 36 | 253 | 93 | 37 | 512
2131 | 2017-08-23 | 2017-09-27 | 2018-02-08 | 2018-02-08 | COMP | 2018-04-20 | COMP | 2019-06-10 | COMP | 2020-03-21 | INPR | 2019-10-02 | COMP | Rule 16 | 25 | 91 | 51 | 286 |  |  | 530
2360 | 2017-08-23 | 2017-11-11 | 2018-09-06 | 2018-09-06 | COMP | 2018-10-17 | COMP | 2019-09-04 | COMP | 2022-06-30 | COMP | 2022-10-24 | COMP | Rule 15/16 | 56 | 205 | 30 | 221 | 711 | 81 | 1300
2373 | 2017-08-23 | 2017-11-14 | 2018-07-07 | 2018-07-07 | COMP | 2019-02-28 | COMP | 2019-10-03 | COMP | 2023-04-22 | INPR | 2021-06-08 | COMP | Rule 15/16 | 58 | 161 | 161 | 153 |  |  | 952
2462 | 2017-08-23 | 2017-12-05 | 2018-06-07 | 2018-08-13 | COMP | 2019-01-31 | COMP | 2019-11-18 | COMP | 2020-05-06 | COMP | 2020-07-07 | COMP | Rule 15/16 | 71 | 128 | 117 | 203 | 117 | 44 | 721
2538 | 2017-08-23 | 2017-12-19 | 2018-06-06 | 2018-06-06 | COMP | 2018-12-17 | COMP | 2019-04-03 | COMP | 2020-01-24 | COMP | 2020-07-27 | COMP | Rule 16 | 81 | 117 | 134 | 74 | 204 | 130 | 735
2602 | 2017-08-23 | 2018-01-05 | 2018-04-03 | 2018-04-03 | COMP | 2018-04-25 | COMP | 2018-07-18 | COMP | 2018-08-14 | COMP | 2020-05-13 | COMP | Rule 16 | 92 | 61 | 17 | 59 | 20 | 439 | 683
3094 | 2017-08-23 | 2018-03-07 | 2018-06-28 | 2018-06-28 | COMP | 2019-02-07 | COMP | 2019-02-14 | COMP | 2019-05-14 | COMP | 2019-07-12 | COMP | Rule 16 | 133 | 81 | 153 | 6 | 63 | 42 | 473
4219 | 2017-08-23 | 2019-08-05 | 2019-08-14 | 2019-08-14 | COMP | 2019-11-19 | COMP |  | REQD |  | REQD | 2020-07-27 | COMP | Rule 16 | 489 | 8 | 68 |  |  |  | 735
4483 | 2017-08-23 | 2018-01-05 | 2018-04-25 | 2018-04-25 | COMP | 2018-05-04 | COMP | 2018-05-04 | COMP | 2018-08-15 | COMP | 2020-04-11 | COMP | Rule 16 | 92 | 77 | 8 | 1 | 72 | 415 | 660
4566 | 2017-08-23 | 2018-01-31 | 2018-05-11 | 2018-05-11 | COMP | 2018-09-24 | COMP | 2018-09-24 | COMP | 2019-02-04 | COMP | 2019-03-18 | COMP | Rule 16 | 109 | 72 | 94 | 1 | 90 | 30 | 391
5350 | 2017-08-23 | 2018-05-23 | 2018-12-07 | 2020-01-22 | COMP | 2020-04-10 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-25 | COMP | Rule 16 | 188 | 137 | 57 | 62 | 1 | 36 | 756
5353 | 2017-08-23 | 2018-05-23 | 2018-08-07 | 2018-08-07 | COMP | 2019-03-26 | COMP | 2019-06-14 | COMP | 2019-12-28 | INPR | 2019-08-28 | COMP | Rule 16 | 188 | 53 | 158 | 58 |  |  | 506
12769 | 2017-08-23 | 2019-06-21 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-30 | COMP | 2020-02-03 | COMP | 2020-02-10 | COMP | 2020-02-26 | COMP | Rule 15/16 | 459 | 137 | 16 | 3 | 6 | 12 | 628
1958 | 2017-08-24 | 2017-08-31 | 2018-03-21 | 2018-03-21 | COMP | 2019-10-07 | COMP | 2019-10-29 | COMP | 2019-10-15 | COMP | 2019-12-13 | COMP | Rule 15/16 | 6 | 137 | 391 | 17 | 0 | 31 | 578
2027 | 2017-08-24 | 2017-09-08 | 2018-08-12 | 2018-08-12 | COMP | 2018-09-06 | COMP | 2019-06-18 | COMP | 2018-11-28 | COMP | 2019-07-19 | COMP | Rule 16 | 11 | 232 | 18 | 196 | 0 | 23 | 477
2074 | 2017-08-24 | 2017-09-19 | 2018-03-21 | 2018-03-21 | COMP | 2019-02-12 | COMP | 2019-02-25 | COMP | 2019-12-02 | COMP | 2020-01-22 | COMP | Rule 15/16 | 18 | 125 | 226 | 9 | 195 | 35 | 603
2115 | 2017-08-24 | 2017-09-26 | 2018-04-27 | 2018-04-27 | COMP | 2018-08-09 | COMP | 2018-08-13 | COMP | 2019-07-10 | COMP | 2019-08-19 | COMP | Rule 16 | 23 | 147 | 73 | 3 | 228 | 29 | 498
2218 | 2017-08-24 | 2017-10-15 | 2018-09-10 | 2018-09-10 | COMP | 2018-10-18 | COMP | 2018-10-29 | COMP | 2018-11-05 | COMP | 2019-01-31 | COMP | Rule 16 | 36 | 226 | 29 | 8 | 6 | 58 | 359
2284 | 2017-08-24 | 2017-10-28 | 2018-03-12 | 2018-03-12 | COMP | 2018-05-18 | COMP | 2019-06-28 | COMP | 2019-08-07 | COMP | 2019-08-22 | COMP | Rule 15/16 | 46 | 89 | 50 | 280 | 28 | 12 | 501
2377 | 2017-08-24 | 2017-11-14 | 2018-03-22 | 2018-03-22 | COMP | 2018-03-30 | COMP | 2018-03-30 | COMP | 2018-05-10 | COMP | 2020-02-26 | COMP | Rule 16 | 57 | 87 | 7 | 1 | 30 | 450 | 627
2644 | 2017-08-24 | 2018-01-11 | 2018-04-18 | 2018-04-18 | COMP | 2018-07-20 | COMP | 2018-09-10 | COMP | 2019-01-16 | COMP | 2019-07-13 | COMP | Rule 16 | 95 | 68 | 66 | 36 | 88 | 124 | 472
2651 | 2017-08-24 | 2018-01-12 | 2018-08-23 | 2018-08-23 | COMP | 2018-08-30 | COMP | 2018-09-07 | COMP | 2018-12-27 | COMP | 2019-01-31 | COMP | Rule 16 | 96 | 156 | 6 | 6 | 76 | 24 | 359
3388 | 2017-08-24 | 2018-04-19 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-13 | COMP | 2019-02-27 | COMP | 2019-04-11 | COMP | 2019-07-21 | COMP | Rule 15/16 | 163 | 150 | 16 | 51 | 32 | 70 | 477
3422 | 2017-08-24 | 2018-04-24 | 2019-02-25 | 2019-02-25 | COMP | 2020-08-27 | COMP | 2019-09-03 | COMP |  | INPR | 2020-09-14 | COMP | Rule 16 | 166 | 210 | 383 |  |  |  | 768
6508 | 2017-08-24 | 2018-08-23 | 2018-10-04 | 2018-10-04 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2019-09-25 | COMP | 2019-09-26 | COMP | Rule 16 | 251 | 30 | 17 | 1 | 229 | 2 | 525
39122 | 2017-08-24 | 2022-10-03 | 2023-01-06 | 2023-01-06 | COMP | 2023-01-06 | NOTN | 2023-08-30 | COMP |  | INPR | 2023-12-07 | COMP | Other | 1284 | 65 |  | 164 |  |  | 1578
1965 | 2017-08-25 | 2017-08-28 | 2018-08-09 | 2018-08-09 | COMP | 2017-08-28 | NOTN | 2018-12-14 | COMP | 2019-06-29 | INPR | 2019-03-23 | COMP | Other | 2 | 239 |  | 88 |  |  | 393
2059 | 2017-08-25 | 2017-09-15 | 2020-03-23 | 2020-03-23 | COMP | 2020-05-19 | COMP | 2020-08-27 | COMP | 2020-08-10 | COMP | 2020-11-30 | COMP | Rule 16 | 15 | 630 | 42 | 72 | 0 | 64 | 819
2060 | 2017-08-25 | 2017-09-15 | 2019-12-13 | 2019-12-13 | COMP | 2020-06-12 | COMP | 2020-07-10 | COMP | 2020-08-21 | COMP | 2020-10-01 | COMP | Rule 15/16 | 15 | 563 | 126 | 21 | 31 | 29 | 780
2159 | 2017-08-25 | 2017-10-02 | 2018-03-03 | 2018-03-03 | COMP | 2018-08-07 | COMP | 2018-08-07 | COMP | 2023-11-11 | INPR | 2021-07-13 | COMP | Rule 16 | 26 | 103 | 110 | 1 |  |  | 974
2162 | 2017-08-25 | 2017-10-02 | 2017-11-29 | 2017-11-29 | COMP | 2017-11-27 | COMP | 2017-12-29 | COMP | 2017-11-29 | COMP | 2019-01-11 | COMP | Rule 16 | 26 | 40 |  | 24 | 0 | 260 | 345
2225 | 2017-08-25 | 2017-10-18 | 2017-12-26 | 2017-12-26 | COMP | 2019-10-19 | INPR | 2019-01-14 | NOTN | 2019-07-09 | COMP | 2019-07-12 | COMP | Rule 16 | 38 | 46 |  |  |  |  | 471
2754 | 2017-08-25 | 2018-01-26 | 2018-03-05 | 2018-03-02 | COMP | 2018-03-23 | COMP | 2018-03-23 | COMP | 2019-06-26 | COMP | 2019-07-15 | COMP | Rule 16 | 104 | 26 | 16 | 1 | 318 | 13 | 472
3211 | 2017-08-25 | 2018-03-22 | 2018-07-09 | 2018-07-09 | COMP | 2019-03-04 | COMP | 2019-04-05 | COMP | 2020-03-10 | COMP | 2020-03-26 | COMP | Rule 16 | 142 | 76 | 163 | 25 | 233 | 13 | 647
4423 | 2017-08-25 | 2017-12-01 | 2018-03-31 | 2018-03-31 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-01-03 | COMP | 2019-01-28 | COMP | Rule 16 | 67 | 82 | 192 | 1 | 0 | 16 | 355
4902 | 2017-08-25 | 2018-04-12 | 2018-08-09 | 2018-08-09 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2019-03-15 | COMP | 2019-05-13 | COMP | Rule 16 | 157 | 84 | 99 | 1 | 51 | 42 | 429
4448 | 2017-08-26 | 2017-12-12 | 2018-02-23 | 2018-06-05 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-06-10 | COMP | 2019-07-14 | COMP | Rule 16 | 73 | 50 | 147 | 1 | 109 | 24 | 470
2122 | 2017-08-28 | 2017-09-27 | 2018-01-12 | 2018-01-12 | COMP | 2018-03-06 | COMP | 2018-03-07 | COMP | 2019-10-08 | COMP | 2019-11-13 | COMP | Rule 16 | 22 | 73 | 36 | 2 | 402 | 26 | 556
2124 | 2017-08-28 | 2017-09-27 | 2018-01-12 | 2018-01-12 | COMP | 2018-05-08 | COMP | 2019-03-06 | COMP | 2019-11-05 | COMP | 2019-11-12 | COMP | Rule 16 | 22 | 73 | 81 | 207 | 172 | 5 | 555
2383 | 2017-08-28 | 2017-11-15 | 2018-02-17 | 2018-02-17 | COMP | 2018-05-08 | COMP | 2018-06-23 | COMP | 2019-06-29 | INPR | 2019-02-01 | COMP | Rule 15/16 | 56 | 63 | 56 | 33 |  |  | 358
2395 | 2017-08-28 | 2017-11-16 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-26 | COMP | 2021-04-16 | COMP | 2021-05-04 | COMP | 2021-06-13 | COMP | Rule 16 | 57 | 621 | 78 | 160 | 13 | 28 | 952
2440 | 2017-08-28 | 2017-11-30 | 2018-11-26 | 2018-11-26 | COMP | 2018-12-13 | COMP | 2018-12-20 | COMP | 2020-01-31 | COMP | 2020-02-28 | COMP | Rule 15/16 | 65 | 248 | 14 | 6 | 279 | 20 | 627
2453 | 2017-08-28 | 2017-12-02 | 2017-12-09 | 2017-12-09 | COMP | 2018-01-29 | COMP | 2018-01-29 | COMP | 2019-03-04 | COMP | 2019-04-29 | COMP | Rule 16 | 66 | 5 | 33 | 1 | 275 | 41 | 418
2501 | 2017-08-28 | 2017-12-11 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2019-12-20 | COMP | 2020-01-07 | COMP | Rule 16 | 72 | 196 | 15 | 1 | 301 | 11 | 591
2692 | 2017-08-28 | 2018-01-19 | 2018-07-11 | 2018-07-11 | COMP | 2018-08-09 | COMP | 2018-10-10 | COMP | 2019-03-25 | COMP | 2019-05-02 | COMP | Rule 15/16 | 98 | 121 | 22 | 44 | 112 | 29 | 421
2931 | 2017-08-28 | 2018-02-20 | 2018-05-10 | 2018-05-10 | COMP | 2018-08-24 | COMP | 2019-02-28 | COMP | 2019-02-07 | COMP | 2019-03-28 | COMP | Rule 16 | 119 | 58 | 75 | 127 | 0 | 21 | 396
3126 | 2017-08-28 | 2018-03-15 | 2018-07-02 | 2018-07-02 | COMP | 2018-10-19 | COMP | 2018-10-30 | COMP | 2019-04-17 | COMP | 2019-05-22 | COMP | Rule 16 | 136 | 77 | 78 | 8 | 115 | 26 | 435
4479 | 2017-08-28 | 2018-01-03 | 2018-03-27 | 2018-03-27 | COMP | 2018-05-08 | COMP | 2018-05-08 | COMP | 2020-02-29 | COMP | 2020-06-26 | COMP | Rule 15/16 | 87 | 58 | 31 | 1 | 454 | 84 | 711
4932 | 2017-08-28 | 2018-04-12 | 2019-01-02 | 2019-01-02 | COMP | 2019-04-25 | COMP | 2021-04-01 | COMP | 2021-07-23 | COMP | 2021-08-02 | COMP | Rule 16 | 156 | 182 | 80 | 487 | 80 | 7 | 987
6225 | 2017-08-28 | 2018-08-06 | 2018-11-28 | 2018-11-28 | COMP | 2019-05-07 | COMP | 2019-05-08 | COMP | 2019-05-07 | COMP | 2019-07-19 | COMP | Rule 16 | 236 | 79 | 111 | 2 | 0 | 51 | 475
2013 | 2017-08-29 | 2017-09-07 | 2018-04-13 | 2018-04-13 | COMP | 2018-05-21 | COMP | 2018-05-21 | COMP | 2023-04-01 | INPR | 2021-12-10 | COMP | Rule 16 | 7 | 150 | 27 | 1 |  |  | 1076
2014 | 2017-08-29 | 2017-09-07 | 2018-04-13 | 2018-04-13 | COMP | 2018-06-12 | COMP | 2018-06-12 | COMP | 2023-04-01 | INPR | 2021-12-10 | COMP | Rule 16 | 7 | 150 | 42 | 1 |  |  | 1076
2076 | 2017-08-29 | 2017-09-19 | 2018-05-02 | 2018-05-02 | COMP | 2018-05-04 | COMP | 2018-05-04 | COMP | 2023-04-01 | INPR | 2021-12-10 | COMP | Rule 16 | 15 | 155 | 3 | 1 |  |  | 1076
2112 | 2017-08-29 | 2017-09-26 | 2017-12-01 | 2017-12-01 | COMP | 2017-12-20 | COMP | 2017-12-28 | COMP | 2019-02-02 | COMP | 2019-03-06 | COMP | Rule 16 | 20 | 46 | 14 | 6 | 275 | 22 | 379
2129 | 2017-08-29 | 2017-09-28 | 2017-11-17 | 2017-11-17 | COMP | 2018-03-01 | COMP | 2018-03-01 | COMP | 2019-03-06 | COMP | 2019-03-04 | COMP | Rule 16 | 22 | 36 | 69 | 1 | 255 |  | 377
2351 | 2017-08-29 | 2017-11-08 | 2018-02-12 | 2018-02-12 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2020-04-24 | COMP | 2020-06-05 | COMP | Rule 16 | 51 | 63 | 361 | 1 | 194 | 30 | 695
2425 | 2017-08-29 | 2017-11-28 | 2018-05-03 | 2018-05-03 | COMP | 2019-03-20 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-04-06 | COMP | Rule 16 | 62 | 109 | 220 | 5 | 1 | 9 | 401
2553 | 2017-08-29 | 2017-12-21 | 2018-05-18 | 2018-05-18 | COMP | 2018-05-31 | COMP | 2018-06-13 | COMP | 2019-01-26 | COMP | 2019-03-08 | COMP | Rule 16 | 79 | 103 | 9 | 10 | 155 | 29 | 381
2664 | 2017-08-29 | 2018-01-16 | 2018-02-04 | 2018-02-04 | COMP | 2018-05-01 | COMP | 2018-05-01 | COMP | 2019-08-06 | COMP | 2019-05-31 | COMP | Rule 16 | 94 | 14 | 61 | 1 | 319 |  | 440
3482 | 2017-08-29 | 2018-05-04 | 2018-05-14 | 2018-05-14 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2020-08-10 | COMP | 2020-10-07 | COMP | Rule 16 | 171 | 7 | 233 | 1 | 333 | 42 | 782
4399 | 2017-08-29 | 2017-11-15 | 2018-01-10 | 2018-01-10 | COMP | 2018-03-22 | COMP | 2018-03-22 | COMP | 2020-02-29 | INPR | 2019-10-25 | COMP | Rule 16 | 55 | 37 | 50 | 1 |  |  | 543
4445 | 2017-08-29 | 2017-12-11 | 2018-01-23 | 2018-01-23 | COMP | 2018-02-28 | COMP | 2019-01-24 | COMP | 2019-01-16 | COMP | 2019-02-20 | COMP | Rule 16 | 71 | 29 | 26 | 228 | 0 | 19 | 369
4485 | 2017-08-29 | 2018-01-05 | 2018-02-28 | 2018-04-13 | COMP | 2018-04-23 | COMP | 2018-12-26 | COMP | 2018-11-26 | COMP | 2019-02-25 | COMP | Rule 16 | 88 | 37 | 7 | 171 | 0 | 41 | 372
4516 | 2017-08-29 | 2018-01-18 | 2018-05-10 | 2019-03-20 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-06-03 | COMP | 2019-07-11 | COMP | Rule 16 | 96 | 80 | 52 | 1 | 2 | 28 | 468
6363 | 2017-08-29 | 2018-08-14 | 2018-12-11 | 2018-12-11 | COMP | 2019-03-26 | COMP | 2020-07-23 | COMP | 2023-04-19 | COMP | 2023-05-17 | COMP | Rule 16 | 241 | 82 | 72 | 337 | 688 | 21 | 1436
8507 | 2017-08-29 | 2018-12-05 | 2019-01-30 | 2019-07-27 | COMP | 2019-10-15 | COMP | 2020-08-19 | COMP | 2021-06-09 | COMP | 2021-07-21 | COMP | Rule 16 | 318 | 38 | 56 | 214 | 202 | 30 | 978
2232 | 2017-08-30 | 2017-10-19 | 2018-04-26 | 2018-04-26 | COMP | 2018-07-18 | COMP | 2018-11-05 | COMP | 2019-10-02 | COMP | 2019-11-09 | COMP | Rule 15/16 | 36 | 129 | 58 | 78 | 228 | 28 | 552
3066 | 2017-08-30 | 2018-03-07 | 2018-08-04 | 2018-11-28 | COMP | 2018-12-12 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-01-23 | COMP | Rule 16 | 128 | 106 | 11 | 5 | 1 | 24 | 349
4366 | 2017-08-30 | 2017-10-13 | 2018-03-01 | 2018-03-01 | COMP | 2018-04-20 | COMP | 2019-01-14 | COMP | 2019-01-10 | COMP | 2019-03-01 | COMP | Rule 16 | 32 | 93 | 37 | 184 | 0 | 33 | 375
4617 | 2017-08-30 | 2018-02-15 | 2018-05-30 | 2018-05-30 | COMP | 2018-07-20 | COMP | 2018-10-24 | COMP | 2023-04-30 | INPR | 2019-05-08 | COMP | Rule 16 | 115 | 73 | 37 | 68 |  |  | 423
4997 | 2017-08-30 | 2018-04-23 | 2018-09-07 | 2018-09-07 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-01-15 | COMP | 2019-01-31 | COMP | Rule 16 | 161 | 97 | 56 | 1 | 33 | 12 | 355
6603 | 2017-08-30 | 2018-08-29 | 2018-11-20 | 2018-11-20 | COMP | 2019-06-21 | COMP | 2019-08-22 | COMP | 2019-11-18 | COMP | 2020-05-02 | COMP | Rule 15/16 | 251 | 58 | 147 | 44 | 61 | 114 | 670
7019 | 2017-08-30 | 2018-09-23 | 2018-11-26 | 2018-11-26 | COMP | 2019-02-28 | COMP | 2019-02-28 | COMP | 2020-01-06 | COMP | 2020-01-31 | COMP | Rule 16 | 267 | 43 | 65 | 1 | 215 | 19 | 606
10375 | 2017-08-30 | 2019-03-12 | 2019-05-28 | 2019-10-01 | COMP | 2019-12-18 | COMP | 2019-12-19 | COMP | 2023-11-11 | INPR | 2020-03-06 | COMP | Rule 16 | 382 | 55 | 54 | 2 |  |  | 630
2007 | 2017-08-31 | 2017-09-06 | 2017-12-02 | 2017-12-02 | COMP | 2018-05-21 | COMP | 2019-12-03 | COMP | 2020-03-27 | COMP | 2020-01-10 | COMP | Rule 16 | 4 | 60 | 117 | 386 | 80 |  | 591
2121 | 2017-08-31 | 2017-09-27 | 2018-02-02 | 2018-02-02 | COMP | 2019-12-30 | COMP | 2020-01-13 | COMP | 2020-02-18 | COMP | 2020-02-19 | COMP | Rule 15/16 | 19 | 87 | 479 | 10 | 25 | 2 | 617
2187 | 2017-08-31 | 2017-10-05 | 2018-04-23 | 2018-04-23 | COMP | 2018-06-12 | COMP | 2018-07-10 | COMP | 2019-01-08 | COMP | 2019-04-19 | COMP | Rule 15/16 | 25 | 136 | 36 | 20 | 125 | 72 | 409
2413 | 2017-08-31 | 2017-11-20 | 2018-01-17 | 2018-01-17 | COMP | 2018-06-05 | COMP | 2020-05-11 | COMP | 2020-05-06 | COMP | 2020-05-21 | COMP | Rule 15/16 | 56 | 38 | 98 | 486 | 0 | 9 | 683
2416 | 2017-08-31 | 2017-11-22 | 2018-05-16 | 2019-05-12 | COMP | 2019-06-13 | COMP | 2019-06-19 | INPR | 2019-07-29 | COMP | 2019-09-07 | COMP | Rule 15/16 | 58 | 120 | 23 |  |  |  | 506
2494 | 2017-08-31 | 2017-12-08 | 2018-04-24 | 2018-09-05 | COMP | 2018-10-10 | COMP | 2018-12-06 | COMP | 2019-08-22 | COMP | 2020-01-07 | COMP | Rule 15/16 | 68 | 94 | 26 | 39 | 180 | 93 | 588
2758 | 2017-08-31 | 2018-01-29 | 2018-03-22 | 2018-03-22 | COMP | 2018-06-14 | COMP | 2018-07-03 | COMP |  | INPR | 2020-03-26 | COMP | Rule 16 | 101 | 38 | 60 | 14 |  |  | 643
4476 | 2017-08-31 | 2018-01-05 | 2018-02-02 | 2018-02-02 | COMP | 2018-10-15 | COMP | 2018-10-15 | COMP | 2018-10-22 | COMP | 2019-01-31 | COMP | Rule 15/16 | 86 | 20 | 178 | 1 | 6 | 68 | 354
14672 | 2017-08-31 | 2019-09-23 | 2019-10-19 | 2019-10-19 | COMP | 2019-10-30 | COMP | 2019-11-23 | COMP | 2019-12-11 | COMP | 2019-12-24 | COMP | Rule 16 | 517 | 20 | 8 | 17 | 11 | 10 | 580
15006 | 2017-08-31 | 2019-10-09 | 2019-10-26 | 2019-10-26 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2021-01-11 | COMP | 2021-03-05 | COMP | Rule 16 | 529 | 13 | 147 | 1 | 156 | 38 | 880
2036 | 2017-09-01 | 2017-09-09 | 2018-07-21 | 2018-07-21 | COMP | 2018-10-30 | COMP | 2018-11-05 | COMP | 2018-11-09 | COMP | 2019-04-10 | COMP | Rule 16 | 5 | 216 | 71 | 5 | 5 | 102 | 401
2143 | 2017-09-01 | 2017-09-29 | 2019-01-14 | 2018-12-21 | COMP | 2019-02-12 | COMP | 2019-04-29 | COMP | 2019-05-02 | COMP | 2019-06-28 | COMP | Rule 16 | 20 | 322 | 35 | 54 | 4 | 41 | 457
2177 | 2017-09-01 | 2017-10-04 | 2018-01-23 | 2018-01-23 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2018-12-06 | COMP | 2019-02-11 | COMP | Rule 16 | 23 | 74 | 163 | 1 | 59 | 45 | 360
2605 | 2017-09-01 | 2018-01-05 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-26 | COMP | 2019-01-28 | COMP | 2018-12-07 | COMP | 2019-03-08 | COMP | Rule 16 | 85 | 179 | 46 | 43 | 0 | 29 | 378
2635 | 2017-09-01 | 2018-01-09 | 2018-06-02 | 2019-12-24 | COMP | 2020-01-24 | COMP | 2020-03-16 | COMP | 2020-03-23 | COMP | 2020-06-10 | COMP | Rule 15/16 | 87 | 101 | 21 | 36 | 6 | 57 | 695
3472 | 2017-09-01 | 2018-05-02 | 2018-09-06 | 2018-09-06 | COMP | 2018-10-29 | COMP | 2018-11-06 | COMP | 2019-06-29 | INPR | 2019-02-21 | COMP | Rule 15/16 | 166 | 89 | 38 | 7 |  |  | 367
4400 | 2017-09-01 | 2017-11-15 | 2018-03-14 | 2018-03-14 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2019-07-21 | INPR | 2019-04-02 | COMP | Rule 15/16 | 52 | 80 | 173 | 1 |  |  | 395
5821 | 2017-09-03 | 2018-07-06 | 2018-08-07 | 2018-08-07 | COMP | 2018-08-22 | COMP | 2018-08-29 | COMP | 2019-08-22 | COMP | 2019-09-20 | COMP | Rule 16 | 210 | 23 | 12 | 6 | 247 | 21 | 514
2438 | 2017-09-04 | 2017-11-30 | 2018-03-18 | 2018-02-23 | COMP | 2018-04-30 | COMP | 2018-04-30 | COMP | 2019-11-23 | INPR | 2019-07-19 | COMP | Rule 16 | 60 | 73 | 47 | 1 |  |  | 470
2860 | 2017-09-05 | 2018-02-07 | 2018-07-01 | 2018-07-01 | COMP | 2018-11-07 | COMP | 2018-11-07 | COMP | 2019-01-15 | COMP | 2019-03-20 | COMP | Rule 16 | 106 | 101 | 91 | 1 | 45 | 45 | 385
3723 | 2017-09-05 | 2018-06-19 | 2019-01-24 | 2019-06-21 | COMP | 2019-07-29 | COMP | 2020-09-11 | COMP | 2020-09-14 | COMP | 2021-04-29 | COMP | Rule 15/16 | 198 | 150 | 26 | 285 | 2 | 157 | 917
4409 | 2017-09-05 | 2017-11-21 | 2018-04-25 | 2018-04-25 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-03-31 | COMP | 2020-07-02 | COMP | Rule 15/16 | 55 | 106 | 466 | 1 | 20 | 67 | 710
4454 | 2017-09-05 | 2017-12-15 | 2018-02-05 | 2018-02-05 | COMP | 2018-03-05 | COMP | 2018-03-05 | COMP | 2019-04-16 | COMP | 2019-06-26 | COMP | Rule 16 | 71 | 34 | 20 | 1 | 282 | 51 | 454
5040 | 2017-09-05 | 2018-04-25 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-08 | COMP | 2019-03-18 | INPR | 2019-02-06 | COMP | 2019-03-09 | COMP | Rule 16 | 160 | 123 | 17 |  |  |  | 377
8369 | 2017-09-05 | 2018-11-28 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-01-28 | COMP | 2019-02-12 | COMP | Rule 16 | 309 | 11 | 8 | 1 | 24 | 12 | 360
8920 | 2017-09-05 | 2019-01-07 | 2019-04-12 | 2019-04-12 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-12-28 | INPR | 2019-07-30 | COMP | Rule 16 | 335 | 68 | 51 | 1 |  |  | 477
2066 | 2017-09-06 | 2017-09-18 | 2018-08-02 | 2018-08-02 | COMP | 2018-08-15 | NOTN | 2018-08-15 | COMP | 2022-04-16 | INPR | 2021-03-23 | COMP | Other | 9 | 220 |  | 10 |  |  | 889
2205 | 2017-09-06 | 2017-10-11 | 2018-08-22 | 2018-08-22 | COMP | 2018-11-19 | COMP | 2019-03-14 | COMP | 2018-12-01 | COMP | 2019-04-18 | COMP | Rule 15/16 | 26 | 217 | 62 | 78 | 0 | 26 | 405
2273 | 2017-09-06 | 2017-10-26 | 2018-06-02 | 2018-06-02 | COMP | 2018-12-24 | COMP | 2019-05-22 | COMP | 2021-02-28 | INPR | 2019-07-31 | COMP | Rule 15/16 | 37 | 149 | 141 | 104 |  |  | 477
2274 | 2017-09-06 | 2017-10-26 | 2018-06-02 | 2018-06-02 | COMP | 2018-12-24 | COMP | 2020-10-23 | COMP | 2020-06-30 | COMP | 2020-12-16 | COMP | Rule 15/16 | 37 | 149 | 141 | 464 | 0 | 36 | 824
2598 | 2017-09-06 | 2018-01-05 | 2018-05-08 | 2021-05-12 | COMP | 2021-06-08 | COMP | 2021-07-13 | COMP | 2023-01-25 | COMP | 2023-03-08 | COMP | Rule 16 | 83 | 86 | 19 | 25 | 386 | 30 | 1381
2624 | 2017-09-06 | 2018-01-08 | 2018-02-04 | 2018-02-04 | COMP | 2018-03-10 | COMP | 2018-03-10 | INPR |  | REQD | 2023-01-22 | COMP | Other | 84 | 19 | 24 |  |  |  | 1349
2661 | 2017-09-06 | 2018-01-16 | 2018-11-09 | 2018-11-09 | COMP | 2018-11-15 | COMP | 2019-02-15 | COMP | 2018-12-04 | COMP | 2019-03-19 | COMP | Rule 16 | 89 | 210 | 4 | 62 | 0 | 22 | 383
2714 | 2017-09-06 | 2018-01-24 | 2018-04-13 | 2018-04-13 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2019-08-31 | INPR | 2019-05-17 | COMP | Rule 16 | 95 | 57 | 106 | 1 |  |  | 426
2861 | 2017-09-06 | 2018-02-08 | 2018-11-01 | 2019-08-05 | COMP | 2019-09-16 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-03-11 | COMP | Rule 15/16 | 106 | 187 | 30 | 27 | 1 | 95 | 629
3095 | 2017-09-06 | 2018-03-07 | 2018-06-14 | 2018-06-14 | COMP | 2018-11-09 | COMP | 2018-12-14 | COMP | 2018-11-09 | COMP | 2019-01-03 | COMP | Rule 16 | 124 | 71 | 105 | 23 | 0 | 13 | 332
3858 | 2017-09-06 | 2018-08-21 | 2018-09-05 | 2018-09-05 | COMP | 2018-11-01 | COMP | 2018-11-07 | COMP | 2019-07-21 | INPR | 2019-04-04 | COMP | Rule 16 | 241 | 11 | 42 | 5 |  |  | 395
4588 | 2017-09-06 | 2018-02-08 | 2018-06-29 | 2018-06-29 | COMP | 2018-10-22 | COMP | 2018-10-26 | COMP | 2020-10-19 | COMP | 2020-12-14 | COMP | Rule 16 | 106 | 100 | 80 | 5 | 498 | 38 | 822
4998 | 2017-09-06 | 2018-04-23 | 2018-12-03 | 2021-04-21 | COMP | 2021-11-05 | COMP | 2021-11-29 | COMP | 2021-11-20 | COMP | 2022-04-12 | COMP | Rule 15/16 | 157 | 155 | 140 | 14 | 0 | 95 | 1156
5359 | 2017-09-06 | 2018-05-24 | 2018-10-05 | 2020-05-13 | COMP | 2020-05-29 | COMP | 2020-09-10 | COMP | 2021-03-19 | COMP | 2021-04-26 | COMP | Rule 15/16 | 180 | 94 | 12 | 74 | 130 | 27 | 913
5360 | 2017-09-06 | 2018-05-24 | 2018-10-05 | 2018-10-05 | COMP | 2020-05-14 | COMP | 2019-05-10 | COMP | 2019-03-28 | COMP | 2019-05-23 | COMP | Other | 180 | 94 | 403 |  | 0 | 10 | 430
6634 | 2017-09-06 | 2018-09-01 | 2019-07-11 | 2021-11-19 | COMP | 2021-11-30 | COMP |  | REQD |  | REQD | 2022-10-27 | COMP | Rule 16 | 249 | 214 | 6 |  |  |  | 1294
30998 | 2017-09-06 | 2021-09-22 | 2021-11-15 | 2021-11-15 | COMP | 2021-12-14 | COMP | 2022-01-13 | COMP |  | INPR | 2023-09-25 | COMP | Rule 15/16 | 1017 | 38 | 20 | 23 |  |  | 1520
2521 | 2017-09-07 | 2017-12-13 | 2018-03-07 | 2018-03-07 | COMP | 2018-04-27 | COMP | 2018-05-31 | COMP | 2018-12-27 | COMP | 2019-03-13 | COMP | Rule 16 | 67 | 57 | 38 | 24 | 145 | 52 | 378
2760 | 2017-09-07 | 2018-01-29 | 2018-06-23 | 2018-06-23 | COMP | 2018-08-03 | COMP | 2018-11-15 | COMP | 2019-07-24 | COMP | 2019-08-15 | COMP | Rule 15/16 | 97 | 103 | 29 | 73 | 172 | 17 | 487
3435 | 2017-09-07 | 2018-04-25 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-22 | COMP | 2020-03-26 | COMP | 2020-04-07 | COMP | 2020-06-03 | COMP | Rule 15/16 | 158 | 373 | 27 | 84 | 9 | 41 | 687
4361 | 2017-09-07 | 2017-10-09 | 2017-12-11 | 2017-12-11 | COMP | 2018-07-19 | COMP | 2018-07-19 | COMP | 2019-10-19 | INPR | 2019-06-17 | COMP | Rule 16 | 23 | 43 | 153 | 1 |  |  | 445
4475 | 2017-09-07 | 2018-01-06 | 2018-04-01 | 2018-04-01 | COMP | 2018-04-11 | COMP | 2018-04-12 | COMP | 2019-09-17 | COMP | 2022-05-02 | COMP | Rule 16 | 82 | 58 | 8 | 2 | 361 | 661 | 1169
12156 | 2017-09-07 | 2019-05-24 | 2020-01-15 | 2020-01-15 | COMP | 2020-07-07 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | 2020-12-03 | COMP | Rule 15/16 | 430 | 161 | 122 | 37 | 1 | 68 | 814
2190 | 2017-09-08 | 2017-10-05 | 2018-04-23 | 2018-04-23 | COMP | 2018-06-07 | COMP | 2018-10-04 | COMP |  | INPR | 2019-04-06 | COMP | Rule 15/16 | 20 | 136 | 33 | 84 |  |  | 394
2192 | 2017-09-08 | 2017-10-05 | 2017-10-12 | 2017-10-12 | COMP | 2018-03-16 | COMP | 2018-03-16 | INPR | 2018-03-01 | COMP | 2021-06-23 | COMP | Rule 16 | 20 | 6 | 105 |  |  |  | 952
2194 | 2017-09-08 | 2017-10-07 | 2018-04-23 | 2019-02-11 | COMP | 2019-04-10 | COMP | 2019-04-30 | COMP | 2022-07-24 | INPR | 2020-07-13 | COMP | Rule 15/16 | 21 | 134 | 42 | 15 |  |  | 714
2216 | 2017-09-08 | 2017-10-13 | 2017-12-17 | 2017-12-17 | COMP | 2018-08-09 | COMP | 2018-11-06 | COMP | 2020-07-16 | COMP | 2021-03-18 | COMP | Rule 15/16 | 26 | 43 | 163 | 63 | 425 | 168 | 884
2231 | 2017-09-08 | 2017-10-19 | 2018-04-13 | 2018-04-13 | COMP | 2018-04-27 | COMP | 2018-09-04 | COMP | 2019-03-07 | COMP | 2019-04-06 | COMP | Rule 15/16 | 30 | 120 | 11 | 90 | 126 | 22 | 394
2234 | 2017-09-08 | 2017-10-19 | 2018-06-28 | 2018-06-28 | COMP | 2018-09-18 | COMP | 2019-01-30 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | Rule 15 | 30 | 173 | 57 | 91 | 51 | 1 | 398
2238 | 2017-09-08 | 2017-10-19 | 2018-06-07 | 2018-06-07 | COMP | 2018-09-06 | COMP | 2018-09-07 | COMP | 2019-03-07 | COMP | 2021-08-03 | COMP | Rule 15 | 30 | 158 | 64 | 2 | 123 | 608 | 980
2306 | 2017-09-08 | 2017-10-31 | 2019-07-23 | 2019-07-23 | COMP | 2020-01-17 | COMP | 2020-03-09 | COMP | 2020-04-30 | COMP | 2020-06-24 | COMP | Rule 16 | 38 | 432 | 123 | 35 | 39 | 39 | 701
2415 | 2017-09-08 | 2017-11-20 | 2018-04-01 | 2018-04-01 | COMP | 2018-05-01 | COMP | 2018-07-30 | COMP | 2019-02-19 | COMP | 2019-02-26 | COMP | Rule 16 | 51 | 89 | 22 | 63 | 139 | 6 | 366
3007 | 2017-09-08 | 2018-02-27 | 2018-05-30 | 2018-05-30 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-07-03 | COMP | 2019-07-30 | COMP | Rule 16 | 116 | 66 | 165 | 1 | 112 | 19 | 474
3253 | 2017-09-08 | 2018-03-28 | 2019-01-24 | 2020-10-25 | COMP | 2023-12-03 | CANC | 2020-04-28 | COMP | 2020-08-14 | COMP | 2020-10-15 | COMP | Rule 15/16 | 137 | 208 |  |  | 78 | 44 | 781
4571 | 2017-09-08 | 2018-02-01 | 2018-07-05 | 2018-07-05 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-02-05 | COMP | Rule 15/16 | 99 | 108 | 29 | 1 | 1 | 119 | 352
5511 | 2017-09-08 | 2018-06-06 | 2018-08-29 | 2019-01-09 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-08-15 | COMP | 2019-11-06 | COMP | Rule 16 | 186 | 60 | 11 | 1 | 143 | 59 | 544
6865 | 2017-09-08 | 2018-09-14 | 2018-11-27 | 2018-11-27 | COMP | 2018-12-13 | COMP | 2019-01-22 | COMP | 2018-11-26 | COMP | 2019-02-11 | COMP | Rule 16 | 256 | 50 | 13 | 26 | 0 | 15 | 356
8444 | 2017-09-08 | 2018-12-03 | 2019-05-16 | 2019-05-16 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2022-05-05 | COMP | 2022-06-14 | COMP | Rule 15/16 | 309 | 115 | 339 | 1 | 411 | 28 | 1198
2285 | 2017-09-09 | 2017-10-28 | 2017-12-29 | 2017-12-29 | COMP | 2018-09-14 | COMP | 2019-06-28 | COMP | 2019-05-06 | COMP | 2019-07-14 | COMP | Other | 35 | 41 | 180 | 198 | 0 | 10 | 461
2287 | 2017-09-09 | 2017-10-28 | 2018-02-16 | 2018-02-16 | COMP | 2018-09-06 | COMP | 2018-09-27 | COMP | 2019-05-06 | COMP | 2019-07-07 | COMP | Other | 35 | 74 | 141 | 16 | 151 | 43 | 456
2288 | 2017-09-09 | 2017-10-28 | 2018-03-19 | 2018-03-19 | COMP | 2018-08-22 | COMP | 2019-07-11 | COMP | 2019-05-06 | COMP | 2019-07-29 | COMP | Other | 35 | 94 | 111 | 222 | 0 | 13 | 472
2289 | 2017-09-09 | 2017-10-28 | 2018-02-26 | 2018-02-26 | COMP | 2018-09-06 | COMP | 2018-09-17 | COMP | 2019-05-06 | COMP | 2019-06-27 | COMP | Other | 35 | 79 | 136 | 8 | 159 | 38 | 451
2742 | 2017-09-09 | 2018-01-25 | 2018-07-31 | 2018-06-23 | COMP | 2019-01-09 | COMP | 2019-04-01 | COMP | 2019-06-14 | COMP | 2019-07-01 | COMP | Rule 16 | 93 | 131 | 136 | 57 | 54 | 12 | 453
7331 | 2017-09-09 | 2018-10-08 | 2018-11-26 | 2018-11-26 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2018-12-11 | COMP | 2019-01-14 | COMP | Rule 16 | 271 | 33 | 13 | 1 | 0 | 22 | 336
2136 | 2017-09-11 | 2017-09-28 | 2018-11-15 | 2018-11-15 | COMP | 2018-07-13 | COMP | 2018-11-19 | COMP | 2020-08-29 | INPR | 2019-04-04 | COMP | Rule 16 | 14 | 285 |  | 90 |  |  | 392
2259 | 2017-09-11 | 2017-10-25 | 2018-03-22 | 2018-03-22 | COMP | 2018-04-24 | COMP | 2018-05-21 | COMP | 2018-10-30 | COMP | 2019-02-22 | COMP | Rule 16 | 33 | 100 | 24 | 20 | 114 | 77 | 363
2286 | 2017-09-11 | 2017-10-28 | 2018-03-19 | 2018-03-19 | COMP | 2018-09-06 | COMP | 2019-08-29 | COMP | 2019-08-28 | COMP | 2019-12-16 | COMP | Other | 35 | 94 | 121 | 247 | 0 | 74 | 568
2290 | 2017-09-11 | 2017-10-28 | 2018-03-05 | 2018-03-05 | COMP | 2018-08-22 | COMP | 2018-09-27 | COMP | 2019-05-06 | COMP | 2019-06-10 | COMP | Other | 35 | 84 | 121 | 26 | 151 | 25 | 438
2886 | 2017-09-11 | 2018-02-13 | 2019-01-25 | 2019-01-25 | COMP | 2019-07-01 | COMP | 2019-07-03 | COMP | 2019-07-29 | COMP | 2019-09-03 | COMP | Rule 16 | 106 | 239 | 110 | 3 | 18 | 26 | 497
3038 | 2017-09-11 | 2018-03-01 | 2018-08-31 | 2019-02-27 | COMP | 2019-06-20 | COMP | 2019-07-08 | COMP | 2019-10-30 | COMP | 2019-12-18 | COMP | Rule 15/16 | 117 | 130 | 81 | 12 | 82 | 33 | 570
3476 | 2017-09-11 | 2018-05-03 | 2018-07-11 | 2018-07-11 | COMP | 2018-09-06 | COMP | 2018-09-06 | INPR | 2019-01-09 | COMP | 2019-02-04 | COMP | Other | 162 | 48 | 41 |  |  |  | 350
3517 | 2017-09-11 | 2018-05-09 | 2018-07-10 | 2018-07-10 | COMP | 2018-09-06 | COMP | 2018-09-06 | INPR |  | REQD | 2019-03-07 | COMP | Other | 166 | 43 | 42 |  |  |  | 372
4288 | 2017-09-11 | 2020-04-07 | 2020-07-15 | 2020-07-15 | COMP | 2021-05-10 | COMP | 2021-08-31 | COMP | 2021-09-07 | COMP | 2021-10-29 | COMP | Rule 15/16 | 645 | 71 | 206 | 80 | 5 | 39 | 1041
4528 | 2017-09-11 | 2018-01-23 | 2018-08-07 | 2018-08-07 | COMP | 2019-01-16 | COMP | 2019-01-17 | COMP | 2019-01-31 | COMP | 2019-03-08 | COMP | Rule 16 | 91 | 138 | 111 | 2 | 10 | 26 | 373
5193 | 2017-09-11 | 2018-05-08 | 2018-07-05 | 2018-07-05 | COMP | 2018-11-14 | COMP | 2018-11-14 | INPR | 2019-01-08 | COMP | 2019-01-29 | COMP | Rule 16 | 165 | 41 | 93 |  |  |  | 346
10692 | 2017-09-11 | 2019-03-26 | 2019-07-10 | 2019-07-10 | COMP | 2020-01-29 | COMP | 2020-10-21 | COMP | 2022-09-16 | COMP | 2022-09-16 | COMP | Rule 16 | 385 | 75 | 139 | 188 | 479 | 1 | 1262
10983 | 2017-09-11 | 2019-04-08 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-10-01 | COMP | 2019-10-25 | COMP | Rule 15/16 | 394 | 52 | 47 | 1 | 27 | 19 | 535
2148 | 2017-09-12 | 2017-09-29 | 2018-01-13 | 2018-01-13 | COMP | 2018-01-29 | COMP | 2018-02-17 | COMP | 2018-12-18 | COMP | 2019-01-28 | COMP | Rule 16 | 14 | 71 | 10 | 15 | 210 | 27 | 344
2204 | 2017-09-12 | 2017-10-11 | 2018-03-09 | 2018-04-24 | COMP | 2018-07-13 | COMP | 2019-01-22 | COMP | 2019-07-03 | COMP | 2019-08-06 | COMP | Rule 15/16 | 22 | 101 | 57 | 131 | 115 | 24 | 477
2219 | 2017-09-12 | 2017-10-15 | 2018-09-13 | 2018-09-13 | COMP | 2018-11-06 | COMP | 2018-11-13 | COMP | 2019-11-23 | INPR | 2019-07-17 | COMP | Rule 16 | 24 | 229 | 39 | 5 |  |  | 463
2264 | 2017-09-12 | 2017-10-25 | 2018-03-30 | 2018-03-30 | COMP | 2018-04-18 | COMP | 2018-06-07 | COMP | 2018-05-31 | COMP | 2021-04-18 | COMP | Rule 16 | 32 | 106 | 14 | 36 | 0 | 719 | 903
2657 | 2017-09-12 | 2018-01-12 | 2018-10-25 | 2018-10-25 | COMP | 2019-11-21 | COMP | 2020-10-21 | COMP | 2020-10-01 | COMP | 2020-12-02 | COMP | Rule 15/16 | 84 | 200 | 270 | 232 | 0 | 28 | 810
2894 | 2017-09-12 | 2018-02-12 | 2018-03-09 | 2018-03-09 | COMP | 2018-10-19 | COMP | 2018-10-30 | COMP | 2018-12-10 | COMP | 2019-03-15 | COMP | Rule 16 | 104 | 19 | 158 | 8 | 27 | 66 | 377
3351 | 2017-09-12 | 2018-04-11 | 2018-08-07 | 2021-04-24 | COMP | 2021-05-13 | COMP | 2021-05-14 | COMP | 2021-05-13 | COMP | 2021-06-14 | COMP | Rule 16 | 145 | 83 | 14 | 2 | 0 | 21 | 943
4580 | 2017-09-12 | 2018-02-09 | 2018-10-17 | 2020-07-20 | COMP | 2021-12-28 | COMP | 2019-06-12 | COMP | 2023-09-28 | COMP | 2023-11-28 | COMP | Rule 16 | 103 | 175 | 363 |  | 1081 | 41 | 1559
5573 | 2017-09-12 | 2018-06-14 | 2018-11-07 | 2018-11-07 | COMP | 2019-03-14 | COMP | 2019-04-08 | COMP | 2019-06-11 | COMP | 2019-07-05 | COMP | Rule 16 | 190 | 103 | 85 | 18 | 46 | 18 | 455
5709 | 2017-09-12 | 2018-06-26 | 2018-09-17 | 2018-09-17 | COMP | 2018-09-18 | NOTN | 2018-09-18 | COMP | 2018-09-18 | COMP | 2020-06-03 | COMP | Other | 198 | 58 |  | 2 | 1 | 429 | 684
6000 | 2017-09-12 | 2018-07-19 | 2018-11-01 | 2019-03-12 | COMP | 2019-03-25 | COMP | 2019-04-04 | NOTN | 2018-08-27 | COMP | 2019-06-25 | COMP | Rule 16 | 214 | 75 | 10 |  |  |  | 448
2105 | 2017-09-13 | 2017-09-26 | 2017-11-15 | 2017-11-15 | COMP | 2018-01-18 | COMP | 2018-01-23 | COMP | 2017-11-15 | COMP | 2021-06-24 | COMP | Rule 16 | 10 | 36 | 42 | 4 | 0 | 862 | 950
2127 | 2017-09-13 | 2017-09-27 | 2018-07-30 | 2018-07-30 | COMP | 2018-11-09 | COMP | 2019-06-13 | NOTN | 2020-09-26 | REQD | 2019-06-17 | COMP | Rule 16 | 11 | 210 | 74 |  |  |  | 441
2144 | 2017-09-13 | 2017-09-28 | 2018-02-13 | 2018-02-13 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-04-02 | COMP | 2019-05-02 | COMP | Rule 15/16 | 12 | 93 | 275 | 1 | 11 | 23 | 410
2240 | 2017-09-13 | 2017-10-19 | 2018-02-15 | 2018-02-15 | COMP | 2018-03-13 | COMP | 2018-03-13 | COMP | 2019-04-12 | COMP | 2019-06-11 | COMP | Rule 16 | 27 | 80 | 18 | 1 | 274 | 42 | 437
2255 | 2017-09-13 | 2017-10-24 | 2018-08-01 | 2018-08-01 | COMP | 2018-08-22 | COMP | 2018-09-11 | COMP | 2018-10-24 | COMP | 2019-01-03 | COMP | Other | 30 | 193 | 16 | 14 | 32 | 47 | 327
2502 | 2017-09-13 | 2017-12-11 | 2018-03-12 | 2018-03-12 | COMP | 2018-04-20 | COMP | 2018-12-07 | COMP | 2018-11-26 | COMP | 2019-01-08 | COMP | Other | 61 | 62 | 30 | 160 | 0 | 21 | 330
2903 | 2017-09-13 | 2018-02-13 | 2018-12-12 | 2018-10-15 | COMP | 2019-08-19 | COMP | 2019-08-29 | COMP | 2019-10-02 | COMP | 2019-12-03 | COMP | Rule 16 | 104 | 210 | 212 | 9 | 24 | 42 | 557
4401 | 2017-09-13 | 2017-11-16 | 2018-06-11 | 2018-06-11 | COMP | 2018-12-06 | COMP | 2019-04-22 | COMP | 2019-04-16 | COMP | 2019-07-14 | COMP | Rule 15/16 | 46 | 141 | 124 | 94 | 0 | 58 | 459
4667 | 2017-09-13 | 2018-03-08 | 2018-08-01 | 2018-08-01 | COMP | 2019-05-07 | COMP | 2019-08-06 | COMP | 2019-08-08 | COMP | 2019-10-18 | COMP | Rule 15/16 | 120 | 103 | 192 | 64 | 3 | 51 | 528
5072 | 2017-09-13 | 2018-04-27 | 2018-08-13 | 2018-08-13 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2019-04-11 | COMP | 2019-05-16 | COMP | Rule 16 | 156 | 75 | 68 | 1 | 99 | 26 | 420
5905 | 2017-09-13 | 2018-07-11 | 2018-11-10 | 2018-11-10 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-04-26 | COMP | 2019-05-24 | COMP | Rule 15/16 | 207 | 87 | 90 | 1 | 24 | 21 | 426
22756 | 2017-09-13 | 2020-10-08 | 2020-10-28 | 2020-10-28 | COMP | 2020-11-13 | COMP | 2021-04-22 | COMP | 2021-04-19 | COMP | 2021-06-08 | COMP | Rule 16 | 773 | 15 | 12 | 109 | 0 | 33 | 938
2303 | 2017-09-14 | 2017-10-31 | 2018-11-17 | 2018-11-17 | COMP | 2019-01-04 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-06-24 | COMP | Rule 16 | 34 | 263 | 31 | 110 | 1 | 10 | 445
3316 | 2017-09-14 | 2018-04-06 | 2018-06-18 | 2018-06-18 | COMP | 2019-07-31 | COMP | 2019-08-01 | COMP | 2019-09-26 | COMP | 2019-11-12 | COMP | Rule 16 | 140 | 51 | 282 | 2 | 40 | 33 | 543
4369 | 2017-09-14 | 2017-10-27 | 2018-01-22 | 2018-01-22 | COMP | 2018-12-20 | COMP | 2019-02-11 | COMP | 2019-03-07 | COMP | 2019-05-10 | COMP | Rule 16 | 32 | 56 | 232 | 35 | 18 | 47 | 415
4378 | 2017-09-14 | 2017-11-03 | 2018-01-18 | 2018-01-18 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-03-07 | COMP | 2019-05-10 | COMP | Rule 16 | 37 | 49 | 234 | 1 | 52 | 47 | 415
4404 | 2017-09-14 | 2017-11-17 | 2018-03-05 | 2018-03-05 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2018-12-31 | COMP | 2019-04-12 | COMP | Rule 16 | 46 | 71 | 203 | 1 | 7 | 72 | 395
4447 | 2017-09-14 | 2017-12-12 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-02-22 | COMP | 2019-05-02 | COMP | Rule 15/16 | 61 | 195 | 34 | 1 | 73 | 50 | 409
4469 | 2017-09-14 | 2017-12-27 | 2018-06-21 | 2018-06-21 | COMP | 2018-07-13 | COMP | 2018-08-30 | COMP | 2018-10-24 | COMP | 2019-01-23 | COMP | Rule 16 | 71 | 123 | 16 | 35 | 39 | 60 | 339
9890 | 2017-09-14 | 2019-02-21 | 2019-05-10 | 2019-06-12 | COMP | 2019-06-25 | COMP | 2020-01-16 | COMP | 2020-02-26 | COMP | 2020-03-05 | COMP | Rule 16 | 359 | 57 | 10 | 141 | 28 | 7 | 619
15041 | 2017-09-14 | 2019-10-10 | 2020-02-19 | 2020-02-19 | COMP | 2020-04-22 | COMP | 2022-01-05 | COMP |  | INPR | 2022-02-24 | COMP | Rule 15/16 | 521 | 88 | 46 | 431 |  |  | 1117
2614 | 2017-09-15 | 2018-01-08 | 2018-08-15 | 2018-08-15 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-12-16 | COMP | 2020-06-29 | COMP | Rule 16 | 77 | 154 | 228 | 1 | 108 | 136 | 699
4379 | 2017-09-15 | 2017-11-03 | 2018-01-17 | 2018-01-17 | COMP | 2019-04-15 | COMP | 2019-04-15 | INPR | 2019-03-27 | COMP | 2019-05-08 | COMP | Rule 16 | 36 | 48 | 313 |  |  |  | 412
4386 | 2017-09-15 | 2017-11-09 | 2018-03-01 | 2018-03-01 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-03-12 | COMP | 2019-03-18 | COMP | Rule 16 | 40 | 74 | 202 | 1 | 58 | 5 | 375
4390 | 2017-09-15 | 2017-11-09 | 2018-02-14 | 2018-02-14 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-03-12 | COMP | 2019-04-08 | COMP | Rule 16 | 40 | 64 | 215 | 1 | 55 | 20 | 390
4394 | 2017-09-15 | 2017-11-14 | 2018-01-19 | 2018-01-19 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-03-12 | COMP | 2019-03-20 | COMP | Rule 16 | 42 | 44 | 230 | 1 | 58 | 7 | 377
4440 | 2017-09-15 | 2017-12-11 | 2018-02-28 | 2018-02-28 | COMP | 2018-03-20 | COMP | 2018-05-16 | COMP | 2018-05-11 | COMP | 2019-01-11 | COMP | Rule 15/16 | 59 | 54 | 15 | 42 | 0 | 165 | 331
4452 | 2017-09-15 | 2017-12-12 | 2018-02-23 | 2018-02-23 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2020-05-31 | INPR | 2019-03-18 | COMP | Rule 16 | 60 | 50 | 232 | 1 |  |  | 375
4589 | 2017-09-15 | 2018-02-08 | 2018-08-13 | 2018-08-13 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2021-02-27 | INPR | 2019-10-08 | COMP | Rule 15/16 | 99 | 130 | 58 | 1 |  |  | 518
4734 | 2017-09-15 | 2018-03-23 | 2018-05-14 | 2018-05-14 | COMP | 2018-09-06 | COMP | 2018-09-06 | COMP | 2018-12-13 | COMP | 2019-06-03 | COMP | Rule 16 | 129 | 37 | 81 | 1 | 68 | 118 | 429
5238 | 2017-09-15 | 2018-05-14 | 2018-08-01 | 2020-07-27 | COMP | 2020-10-14 | COMP | 2018-11-09 | COMP | 2018-12-17 | COMP | 2021-03-23 | COMP | Rule 15/16 | 165 | 56 | 57 |  | 24 | 569 | 882
11612 | 2017-09-15 | 2019-05-05 | 2019-09-04 | 2019-09-04 | COMP | 2020-07-28 | COMP | 2020-01-16 | COMP | 2020-09-28 | COMP | 2020-11-09 | COMP | Rule 15/16 | 409 | 85 | 227 |  | 179 | 31 | 793
5054 | 2017-09-17 | 2018-04-26 | 2018-11-13 | 2018-11-13 | COMP | 2018-11-28 | COMP | 2019-02-25 | COMP | 2019-07-19 | COMP | 2019-09-13 | COMP | Rule 15/16 | 152 | 140 | 10 | 60 | 103 | 40 | 500
2114 | 2017-09-18 | 2017-09-26 | 2018-04-04 | 2018-04-04 | COMP | 2018-04-19 | COMP | 2018-04-20 | COMP | 2019-04-15 | COMP | 2019-06-06 | COMP | Rule 16 | 7 | 130 | 12 | 2 | 247 | 38 | 431
2317 | 2017-09-18 | 2017-11-02 | 2018-01-02 | 2018-01-02 | COMP | 2018-03-22 | COMP | 2018-03-23 | COMP | 2018-12-21 | COMP | 2019-02-25 | COMP | Rule 16 | 34 | 39 | 56 | 2 | 190 | 43 | 359
2368 | 2017-09-18 | 2017-11-14 | 2018-03-12 | 2018-03-12 | COMP | 2019-08-16 | COMP | 2018-05-11 | COMP | 2019-08-20 | COMP | 2019-09-17 | COMP | Rule 16 | 41 | 79 | 363 |  | 321 | 20 | 502
2774 | 2017-09-18 | 2018-01-30 | 2019-10-28 | 2019-10-28 | COMP | 2020-06-24 | COMP | 2021-03-19 | COMP | 2021-03-08 | COMP | 2021-03-30 | COMP | Rule 15/16 | 91 | 441 | 165 | 185 | 0 | 8 | 886
4358 | 2017-09-18 | 2017-09-28 | 2017-11-04 | 2017-11-04 | COMP | 2018-03-29 | COMP | 2018-02-12 | COMP | 2018-01-02 | COMP | 2019-03-14 | COMP | Rule 16 | 9 | 27 | 97 |  | 0 | 273 | 372
4395 | 2017-09-18 | 2017-11-14 | 2018-03-27 | 2018-03-27 | COMP | 2018-06-25 | COMP | 2018-06-25 | COMP | 2019-08-14 | COMP | 2019-09-18 | COMP | Rule 16 | 41 | 90 | 64 | 1 | 287 | 25 | 503
4583 | 2017-09-18 | 2018-02-06 | 2018-06-19 | 2018-06-19 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-05-06 | COMP | 2019-05-24 | COMP | Rule 15/16 | 96 | 94 | 172 | 1 | 50 | 15 | 423
4970 | 2017-09-18 | 2018-04-17 | 2018-04-23 | 2018-04-23 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2022-07-16 | INPR | 2020-05-17 | COMP | Rule 16 | 145 | 5 | 26 | 1 |  |  | 668
4992 | 2017-09-18 | 2018-04-20 | 2018-09-24 | 2018-09-24 | COMP | 2018-10-16 | COMP | 2018-10-16 | COMP | 2018-11-27 | COMP | 2019-01-29 | COMP | Rule 16 | 148 | 109 | 17 | 1 | 28 | 43 | 341
5099 | 2017-09-18 | 2018-04-30 | 2018-05-22 | 2018-05-22 | COMP | 2019-10-01 | COMP | 2019-10-01 | INPR | 2019-10-22 | COMP | 2019-11-22 | COMP | Rule 16 | 154 | 17 | 343 |  |  |  | 549
5537 | 2017-09-18 | 2018-06-12 | 2018-07-27 | 2018-07-27 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-07-21 | INPR | 2019-04-15 | COMP | Rule 15/16 | 184 | 33 | 102 | 1 |  |  | 394
5979 | 2017-09-18 | 2018-07-16 | 2018-10-30 | 2018-11-13 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-01-04 | COMP | 2019-01-22 | COMP | Rule 16 | 207 | 76 | 5 | 1 | 31 | 12 | 336
6258 | 2017-09-18 | 2018-08-07 | 2019-01-28 | 2019-02-15 | COMP | 2019-02-19 | COMP | 2019-04-01 | COMP | 2019-03-27 | COMP | 2019-06-03 | COMP | Rule 16 | 223 | 118 | 2 | 30 | 0 | 45 | 428
2381 | 2017-09-19 | 2017-11-15 | 2017-12-21 | 2017-12-21 | COMP | 2018-05-30 | COMP | 2018-10-24 | COMP | 2018-11-14 | COMP | 2019-02-11 | COMP | Rule 16 | 41 | 25 | 110 | 104 | 15 | 59 | 349
2397 | 2017-09-19 | 2017-11-16 | 2019-07-26 | 2019-07-26 | COMP | 2019-10-30 | COMP | 2019-11-18 | COMP | 2020-01-28 | COMP | 2020-03-02 | COMP | Rule 16 | 42 | 424 | 68 | 13 | 47 | 24 | 613
2398 | 2017-09-19 | 2017-11-16 | 2020-07-15 | 2020-07-15 | COMP | 2020-08-26 | COMP | 2020-10-16 | COMP | 2021-01-14 | COMP | 2021-02-03 | COMP | Rule 16 | 42 | 668 | 31 | 37 | 60 | 14 | 847
2400 | 2017-09-19 | 2017-11-16 | 2019-06-07 | 2019-06-07 | COMP | 2019-10-03 | COMP | 2019-10-12 | COMP |  | INPR | 2020-10-28 | COMP | Rule 16 | 42 | 390 | 83 | 7 |  |  | 783
2401 | 2017-09-19 | 2017-11-16 | 2018-10-12 | 2018-10-12 | COMP | 2019-12-02 | COMP | 2019-12-16 | COMP | 2020-04-28 | COMP | 2020-05-25 | COMP | Rule 16 | 42 | 228 | 284 | 11 | 93 | 19 | 672
2675 | 2017-09-19 | 2018-01-17 | 2018-09-10 | 2018-09-10 | COMP | 2018-11-09 | COMP | 2018-11-21 | COMP | 2018-12-07 | COMP | 2019-01-25 | COMP | Rule 16 | 81 | 165 | 45 | 8 | 11 | 33 | 338
2837 | 2017-09-19 | 2018-02-06 | 2018-05-11 | 2018-05-11 | COMP | 2018-06-11 | COMP | 2018-10-03 | COMP | 2019-04-23 | COMP | 2019-04-26 | COMP | Rule 16 | 95 | 68 | 21 | 81 | 138 | 4 | 402
3185 | 2017-09-19 | 2018-03-24 | 2018-04-03 | 2018-04-03 | COMP | 2018-05-18 | COMP | 2019-01-17 | COMP | 2019-01-26 | COMP | 2019-03-06 | COMP | Rule 16 | 127 | 7 | 34 | 167 | 6 | 27 | 365
3344 | 2017-09-19 | 2018-04-10 | 2018-07-03 | 2018-07-03 | COMP | 2019-03-14 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-07-12 | COMP | Rule 16 | 139 | 60 | 174 | 35 | 1 | 51 | 455
3749 | 2017-09-19 | 2018-06-27 | 2019-02-06 | 2020-10-16 | COMP | 2020-11-25 | COMP | 2021-05-10 | COMP | 2020-02-27 | COMP | 2021-06-11 | COMP | Rule 15/16 | 194 | 153 | 28 | 113 | 0 | 24 | 937
3779 | 2017-09-19 | 2018-07-11 | 2018-09-21 | 2018-09-21 | COMP | 2018-11-29 | COMP | 2019-03-12 | COMP | 2019-02-12 | COMP | 2019-03-18 | COMP | Rule 15/16 | 203 | 52 | 47 | 70 | 0 | 5 | 373
4396 | 2017-09-19 | 2017-11-14 | 2018-03-27 | 2019-06-05 | COMP | 2019-06-26 | COMP | 2019-07-23 | COMP | 2021-01-29 | COMP | 2021-03-09 | COMP | Rule 16 | 40 | 90 | 16 | 19 | 383 | 27 | 870
4418 | 2017-09-19 | 2017-11-27 | 2018-03-12 | 2019-05-29 | COMP | 2019-06-11 | COMP | 2020-12-11 | COMP | 2021-02-09 | COMP | 2021-03-11 | COMP | Rule 16 | 47 | 72 | 10 | 380 | 40 | 22 | 872
4530 | 2017-09-19 | 2018-01-25 | 2018-04-11 | 2018-04-11 | COMP | 2018-05-01 | COMP | 2018-05-01 | COMP | 2019-02-13 | COMP | 2019-04-22 | COMP | Rule 16 | 87 | 54 | 15 | 1 | 198 | 48 | 398
4544 | 2017-09-19 | 2018-01-25 | 2018-04-11 | 2018-04-11 | COMP | 2018-05-01 | COMP | 2018-05-01 | COMP | 2019-02-13 | COMP | 2019-04-03 | COMP | Rule 16 | 87 | 54 | 15 | 1 | 198 | 35 | 385
4545 | 2017-09-19 | 2018-01-25 | 2018-04-11 | 2018-04-11 | COMP | 2018-05-01 | COMP | 2018-05-01 | COMP | 2019-02-13 | COMP | 2019-06-25 | COMP | Rule 16 | 87 | 54 | 15 | 1 | 198 | 93 | 443
4829 | 2017-09-19 | 2018-04-02 | 2018-09-18 | 2018-09-18 | COMP | 2018-11-06 | COMP | 2018-11-07 | COMP | 2020-10-26 | COMP | 2020-11-23 | COMP | Rule 16 | 133 | 119 | 36 | 2 | 495 | 20 | 800
5665 | 2017-09-19 | 2018-06-25 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-08-01 | COMP | 2019-09-03 | COMP | Rule 16 | 192 | 78 | 26 | 1 | 176 | 23 | 491
5857 | 2017-09-19 | 2018-07-09 | 2019-02-22 | 2019-02-22 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2022-01-30 | INPR | 2021-01-22 | COMP | Other | 201 | 157 | 71 | 1 |  |  | 839
7426 | 2017-09-19 | 2018-10-12 | 2019-11-22 | 2019-11-22 | COMP | 2021-05-25 | COMP | 2021-07-28 | COMP | 2022-07-01 | COMP | 2022-08-08 | COMP | Rule 15/16 | 269 | 280 | 378 | 45 | 235 | 26 | 1228
2271 | 2017-09-20 | 2017-10-26 | 2018-03-05 | 2018-03-05 | COMP | 2018-03-16 | COMP | 2018-03-16 | COMP | 2018-02-08 | COMP | 2021-01-19 | COMP | Rule 16 | 27 | 86 | 10 | 1 | 0 | 715 | 835
2291 | 2017-09-20 | 2017-10-28 | 2018-03-05 | 2018-03-05 | COMP | 2018-07-31 | COMP | 2019-01-25 | INPR | 2018-10-15 | COMP | 2019-02-27 | COMP | Other | 28 | 84 | 105 |  |  |  | 359
2363 | 2017-09-20 | 2017-11-13 | 2018-02-20 | 2018-02-20 | COMP | 2018-10-23 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-06-25 | COMP | Rule 15/16 | 38 | 66 | 173 | 128 | 1 | 41 | 442
2434 | 2017-09-20 | 2017-11-29 | 2018-08-14 | 2018-08-14 | COMP | 2018-08-13 | COMP | 2018-09-18 | COMP | 2018-11-15 | COMP | 2019-02-07 | COMP | Rule 16 | 48 | 179 |  | 26 | 42 | 56 | 346
2574 | 2017-09-20 | 2017-12-28 | 2018-06-26 | 2018-06-26 | COMP | 2018-07-25 | COMP | 2018-09-13 | COMP | 2018-09-17 | COMP | 2019-09-24 | COMP | Rule 15/16 | 68 | 125 | 21 | 36 | 3 | 257 | 505
2855 | 2017-09-20 | 2018-02-07 | 2019-05-12 | 2019-05-12 | COMP | 2019-07-24 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2020-01-16 | COMP | Rule 15/16 | 95 | 317 | 51 | 51 | 1 | 71 | 582
4168 | 2017-09-20 | 2019-05-10 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-09 | COMP | 2020-07-14 | COMP | 2020-11-18 | COMP | 2021-01-15 | COMP | Rule 15/16 | 411 | 101 | 6 | 192 | 90 | 39 | 834
4899 | 2017-09-20 | 2018-04-12 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-01 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-03-07 | COMP | Rule 15/16 | 140 | 109 | 12 | 47 | 1 | 61 | 365
7069 | 2017-09-20 | 2018-09-25 | 2019-01-09 | 2019-01-09 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2020-04-26 | INPR | 2020-01-13 | COMP | Rule 15/16 | 255 | 72 | 38 | 1 |  |  | 579
7550 | 2017-09-20 | 2018-10-19 | 2019-02-01 | 2019-02-01 | COMP | 2019-06-26 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2019-08-19 | COMP | Rule 16 | 273 | 70 | 102 | 36 | 1 | 3 | 480
11675 | 2017-09-20 | 2019-05-07 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2020-01-22 | COMP | 2020-03-11 | COMP | Rule 16 | 408 | 78 | 19 | 1 | 83 | 35 | 619
2325 | 2017-09-21 | 2017-11-03 | 2018-10-10 | 2018-10-10 | COMP | 2019-11-21 | COMP | 2020-04-07 | COMP | 2020-04-28 | COMP | 2020-05-17 | COMP | Rule 16 | 32 | 234 | 281 | 93 | 16 | 14 | 665
2326 | 2017-09-21 | 2017-11-03 | 2019-06-04 | 2019-06-04 | COMP | 2019-10-08 | COMP | 2019-10-14 | COMP |  | INPR | 2020-04-22 | COMP | Rule 16 | 32 | 395 | 89 | 5 |  |  | 648
2402 | 2017-09-21 | 2017-11-16 | 2018-10-19 | 2018-10-19 | COMP | 2019-08-21 | COMP | 2019-10-28 | COMP | 2020-11-17 | COMP | 2020-11-29 | COMP | Rule 15/16 | 40 | 233 | 210 | 48 | 267 | 7 | 800
2403 | 2017-09-21 | 2017-11-16 | 2020-05-06 | 2020-05-06 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2020-07-10 | COMP | 2020-11-02 | COMP | Rule 16 | 40 | 619 | 61 | 1 | 0 | 67 | 784
2407 | 2017-09-21 | 2017-11-17 | 2019-11-04 | 2019-11-04 | COMP | 2020-01-16 | COMP | 2020-02-22 | COMP | 2020-11-20 | COMP | 2020-03-13 | COMP | Rule 16 | 41 | 493 | 49 | 25 | 192 |  | 620
2408 | 2017-09-21 | 2017-11-17 | 2018-10-17 | 2018-10-17 | COMP | 2019-09-11 | COMP | 2020-05-01 | COMP | 2020-05-22 | COMP | 2020-08-26 | COMP | Rule 16 | 41 | 230 | 226 | 161 | 16 | 68 | 737
2409 | 2017-09-21 | 2017-11-17 | 2018-10-18 | 2018-10-18 | COMP | 2019-08-21 | COMP | 2019-09-09 | COMP | 2020-06-29 | COMP | 2020-11-02 | COMP | Rule 16 | 41 | 231 | 211 | 13 | 203 | 90 | 784
2410 | 2017-09-21 | 2017-11-17 | 2019-06-07 | 2019-06-07 | COMP | 2019-08-28 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-04-12 | COMP | Rule 16 | 41 | 389 | 58 | 124 | 1 | 32 | 640
2444 | 2017-09-21 | 2017-12-01 | 2018-02-01 | 2018-02-01 | COMP | 2018-03-01 | COMP | 2018-03-26 | COMP | 2019-09-18 | COMP | 2019-10-08 | COMP | Rule 16 | 49 | 42 | 20 | 18 | 375 | 15 | 514
2504 | 2017-09-21 | 2017-12-11 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-10 | COMP | 2019-01-17 | COMP | 2019-01-18 | COMP | 2019-08-27 | COMP | Rule 15/16 | 55 | 244 | 29 | 6 | 2 | 154 | 485
2569 | 2017-09-21 | 2017-12-27 | 2018-03-22 | 2018-03-22 | COMP | 2018-05-23 | COMP | 2018-06-05 | COMP | 2019-06-12 | COMP | 2019-07-23 | COMP | Other | 66 | 59 | 45 | 9 | 257 | 29 | 460
2592 | 2017-09-21 | 2018-01-03 | 2018-05-10 | 2018-05-10 | COMP | 2019-01-10 | COMP | 2019-03-07 | COMP | 2020-07-04 | INPR | 2019-06-17 | COMP | Rule 15/16 | 70 | 90 | 168 | 39 |  |  | 435
2654 | 2017-09-21 | 2018-01-12 | 2018-02-08 | 2018-02-08 | COMP | 2018-03-26 | COMP | 2018-03-26 | COMP | 2018-04-17 | COMP | 2021-01-21 | COMP | Rule 16 | 77 | 19 | 32 | 1 | 17 | 695 | 836
2715 | 2017-09-21 | 2018-01-23 | 2018-04-13 | 2019-04-26 | COMP | 2019-07-31 | COMP | 2019-09-18 | COMP | 2019-12-24 | COMP | 2020-01-22 | COMP | Rule 16 | 83 | 58 | 67 | 35 | 67 | 19 | 584
2756 | 2017-09-21 | 2018-01-26 | 2018-03-26 | 2018-12-17 | COMP | 2019-08-05 | COMP | 2018-04-26 | COMP | 2019-09-13 | COMP | 2019-09-18 | COMP | Rule 16 | 86 | 41 | 160 |  | 349 | 4 | 500
2941 | 2017-09-21 | 2018-02-20 | 2018-07-20 | 2018-07-20 | COMP | 2018-08-20 | COMP | 2019-05-30 | COMP | 2019-06-01 | COMP | 2019-09-27 | COMP | Rule 16 | 102 | 107 | 22 | 195 | 2 | 83 | 507
3075 | 2017-09-21 | 2018-03-06 | 2018-05-09 | 2018-05-09 | COMP | 2018-09-04 | COMP | 2018-09-21 | COMP | 2019-10-18 | COMP | 2019-12-03 | COMP | Rule 16 | 112 | 47 | 82 | 14 | 271 | 30 | 551
3124 | 2017-09-21 | 2018-03-11 | 2018-06-02 | 2018-06-02 | COMP | 2018-12-12 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-04-26 | COMP | Rule 16 | 115 | 59 | 133 | 33 | 1 | 62 | 400
3197 | 2017-09-21 | 2018-03-21 | 2018-04-30 | 2018-04-30 | COMP | 2018-05-18 | COMP | 2018-05-18 | COMP | 2019-06-29 | INPR | 2019-03-27 | COMP | Rule 16 | 123 | 29 | 15 | 1 |  |  | 378
3208 | 2017-09-21 | 2018-03-22 | 2019-02-04 | 2019-02-04 | COMP | 2019-04-15 | COMP | 2019-04-18 | COMP | 2020-05-07 | COMP | 2020-06-18 | COMP | Rule 15/16 | 124 | 219 | 50 | 4 | 266 | 30 | 688
4561 | 2017-09-21 | 2018-01-31 | 2018-04-07 | 2018-04-17 | COMP | 2018-08-22 | COMP | 2018-08-22 | COMP | 2018-12-11 | COMP | 2019-01-10 | COMP | Rule 15/16 | 89 | 47 | 90 | 1 | 76 | 21 | 326
4879 | 2017-09-21 | 2018-04-09 | 2018-08-03 | 2018-08-03 | COMP | 2018-11-09 | COMP | 2018-11-09 | COMP | 2018-11-09 | COMP | 2019-01-12 | COMP | Rule 16 | 136 | 83 | 70 | 1 | 1 | 41 | 327
5071 | 2017-09-21 | 2018-04-27 | 2018-10-12 | 2019-03-18 | COMP | 2019-04-11 | COMP | 2019-01-15 | COMP | 2020-03-25 | COMP | 2020-07-13 | COMP | Rule 16 | 150 | 118 | 19 |  | 300 | 78 | 705
5444 | 2017-09-21 | 2018-05-31 | 2018-09-14 | 2018-11-02 | COMP | 2020-03-06 | COMP | 2020-03-12 | COMP | 2020-06-02 | COMP | 2020-06-04 | COMP | Rule 16 | 173 | 75 | 334 | 5 | 58 | 3 | 678
5772 | 2017-09-21 | 2018-07-02 | 2018-10-10 | 2018-10-10 | COMP | 2019-03-05 | COMP | 2019-03-21 | COMP | 2019-06-19 | COMP | 2019-08-07 | COMP | Rule 16 | 195 | 71 | 98 | 13 | 64 | 35 | 471
10598 | 2017-09-21 | 2019-03-21 | 2019-10-30 | 2019-10-30 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-10-16 | COMP | 2020-11-11 | COMP | Rule 15/16 | 374 | 157 | 80 | 1 | 165 | 18 | 790
2134 | 2017-09-22 | 2017-09-27 | 2017-11-17 | 2018-02-16 | COMP | 2018-12-28 | COMP | 2018-12-28 | COMP | 2018-12-31 | COMP | 2019-03-11 | COMP | Rule 16 | 4 | 37 | 218 | 1 | 2 | 48 | 365
2170 | 2017-09-22 | 2017-10-04 | 2017-12-22 | 2017-12-22 | COMP | 2019-03-04 | COMP | 2018-11-19 | COMP | 2019-08-21 | COMP | 2019-09-10 | COMP | Rule 16 | 9 | 55 | 298 |  | 190 | 14 | 493
2184 | 2017-09-22 | 2017-10-05 | 2018-03-29 | 2018-03-29 | COMP | 2019-02-11 | COMP | 2019-09-12 | COMP | 2019-09-16 | COMP | 2019-12-09 | COMP | Rule 16 | 10 | 119 | 219 | 150 | 3 | 58 | 554
2316 | 2017-09-22 | 2017-11-02 | 2018-08-27 | 2018-08-27 | COMP | 2018-09-19 | COMP | 2018-09-27 | COMP | 2020-07-22 | COMP | 2020-09-18 | COMP | Rule 16 | 30 | 204 | 17 | 7 | 457 | 42 | 752
2417 | 2017-09-22 | 2017-11-27 | 2018-01-30 | 2018-01-30 | COMP | 2018-09-06 | COMP | 2018-09-24 | COMP | 2019-05-09 | COMP | 2019-05-31 | COMP | Rule 15/16 | 44 | 44 | 154 | 13 | 157 | 16 | 423
2450 | 2017-09-22 | 2017-12-02 | 2018-01-29 | 2018-01-29 | COMP | 2018-12-31 | COMP | 2019-01-09 | COMP | 2020-03-10 | COMP | 2020-05-11 | COMP | Rule 16 | 48 | 38 | 233 | 7 | 293 | 45 | 660
2482 | 2017-09-22 | 2017-12-07 | 2018-05-16 | 2018-05-16 | COMP | 2018-08-21 | COMP | 2018-10-17 | COMP | 2019-03-29 | COMP | 2019-05-10 | COMP | Rule 16 | 52 | 111 | 68 | 41 | 111 | 31 | 409
2633 | 2017-09-22 | 2018-01-09 | 2018-06-14 | 2018-06-14 | COMP | 2018-08-10 | COMP | 2019-01-15 | COMP | 2019-03-12 | COMP | 2019-05-02 | COMP | Rule 15/16 | 73 | 110 | 41 | 107 | 39 | 38 | 403
2665 | 2017-09-22 | 2018-01-16 | 2018-03-14 | 2018-03-14 | COMP | 2018-07-27 | COMP | 2018-08-16 | COMP | 2019-04-30 | COMP | 2019-05-07 | COMP | Rule 16 | 77 | 41 | 96 | 15 | 176 | 6 | 406
2839 | 2017-09-22 | 2018-02-06 | 2018-08-02 | 2019-08-08 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-11-12 | COMP | 2019-11-19 | COMP | Rule 16 | 92 | 125 | 47 | 1 | 21 | 6 | 542
4267 | 2017-09-22 | 2020-01-16 | 2020-02-18 | 2020-02-18 | COMP | 2020-03-17 | COMP | 2020-03-18 | COMP | 2020-01-06 | COMP | 2020-05-09 | COMP | Rule 16 | 580 | 22 | 21 | 2 | 0 | 38 | 659
5005 | 2017-09-22 | 2018-04-23 | 2018-08-03 | 2018-08-27 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-03-06 | COMP | 2019-04-17 | COMP | Rule 16 | 145 | 73 | 98 | 1 | 33 | 31 | 392
5809 | 2017-09-22 | 2018-07-05 | 2018-12-12 | 2018-12-12 | COMP | 2019-01-17 | COMP | 2019-02-04 | COMP | 2019-01-10 | COMP | 2019-06-20 | COMP | Rule 15/16 | 196 | 111 | 25 | 12 | 0 | 97 | 437
4977 | 2017-09-24 | 2018-04-17 | 2018-10-10 | 2018-10-10 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-03-07 | COMP | 2019-03-14 | COMP | Rule 16 | 140 | 124 | 81 | 1 | 20 | 6 | 367
2497 | 2017-09-25 | 2017-12-08 | 2018-09-21 | 2018-09-21 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP |  | INPR | 2019-06-22 | COMP | Other | 52 | 199 | 38 | 1 |  |  | 437
3232 | 2017-09-25 | 2018-03-27 | 2018-08-13 | 2019-07-31 | COMP | 2019-11-27 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-04-15 | COMP | Rule 15/16 | 125 | 98 | 84 | 60 | 1 | 36 | 641
4699 | 2017-09-25 | 2018-03-15 | 2018-05-13 | 2018-08-13 | COMP | 2018-10-18 | COMP | 2018-11-16 | COMP | 2019-07-19 | COMP | 2019-08-12 | COMP | Rule 16 | 117 | 42 | 48 | 21 | 168 | 17 | 472
5865 | 2017-09-25 | 2018-07-09 | 2018-11-10 | 2019-10-01 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-12-11 | COMP | 2020-01-17 | COMP | Rule 16 | 197 | 89 | 36 | 1 | 14 | 26 | 580
7059 | 2017-09-25 | 2018-09-25 | 2018-11-27 | 2018-11-27 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-03-11 | COMP | Rule 16 | 252 | 43 | 45 | 1 | 2 | 26 | 364
7143 | 2017-09-25 | 2018-09-28 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-21 | COMP | 2019-04-11 | COMP | 2019-03-26 | COMP | 2019-05-20 | COMP | Rule 16 | 255 | 80 | 19 | 36 | 0 | 28 | 414
7422 | 2017-09-25 | 2018-10-12 | 2019-01-03 | 2019-01-03 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-02-20 | COMP | 2019-02-28 | COMP | Rule 16 | 265 | 55 | 21 | 1 | 13 | 7 | 357
8582 | 2017-09-25 | 2018-12-10 | 2019-03-11 | 2019-03-11 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-10-14 | COMP | 2019-11-18 | COMP | Rule 16 | 303 | 62 | 105 | 1 | 49 | 25 | 540
2207 | 2017-09-26 | 2017-10-12 | 2018-07-02 | 2018-07-02 | COMP | 2019-06-04 | COMP | 2020-12-21 | COMP | 2023-12-02 | INPR | 2021-03-01 | COMP | Rule 15/16 | 13 | 180 | 232 | 391 |  |  | 859
2226 | 2017-09-26 | 2017-10-18 | 2017-12-04 | 2017-12-04 | COMP | 2018-07-31 | NOTN | 2018-07-31 | NOTN | 2020-10-06 | COMP | 2020-07-22 | COMP | Rule 16 | 17 | 31 |  |  |  |  | 709
2292 | 2017-09-26 | 2017-10-28 | 2018-04-06 | 2018-04-06 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2018-12-06 | COMP | 2019-03-24 | COMP | Rule 15/16 | 24 | 108 | 157 | 1 | 13 | 73 | 372
2293 | 2017-09-26 | 2017-10-28 | 2018-03-05 | 2018-03-05 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2018-12-06 | COMP | 2019-03-24 | COMP | Rule 16 | 24 | 84 | 184 | 1 | 10 | 73 | 372
2294 | 2017-09-26 | 2017-10-28 | 2018-05-10 | 2018-05-10 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2018-12-06 | COMP | 2019-03-24 | COMP | Rule 16 | 24 | 132 | 133 | 1 | 13 | 73 | 372
2496 | 2017-09-26 | 2017-12-08 | 2018-09-21 | 2018-09-21 | COMP | 2018-11-14 | COMP |  | REQD |  | REQD | 2019-06-22 | COMP | Other | 51 | 199 | 38 |  |  |  | 436
2498 | 2017-09-26 | 2017-12-08 | 2018-09-25 | 2018-09-25 | COMP | 2018-11-14 | COMP |  | REQD |  | REQD | 2019-06-22 | COMP | Other | 51 | 201 | 36 |  |  |  | 436
2630 | 2017-09-26 | 2018-01-10 | 2018-03-03 | 2020-03-26 | COMP | 2020-08-10 | COMP | 2020-08-11 | COMP | 2020-07-24 | COMP | 2020-09-01 | COMP | Rule 16 | 72 | 36 | 97 | 2 | 0 | 16 | 738
2637 | 2017-09-26 | 2018-01-10 | 2018-02-20 | 2018-02-20 | COMP | 2018-04-13 | COMP | 2018-07-12 | COMP | 2020-07-04 | INPR | 2019-04-05 | COMP | Rule 16 | 72 | 28 | 39 | 63 |  |  | 382
2727 | 2017-09-26 | 2018-01-24 | 2018-04-30 | 2018-04-30 | COMP | 2018-07-17 | COMP | 2018-10-18 | COMP | 2019-04-09 | COMP | 2019-05-08 | COMP | Rule 16 | 81 | 68 | 55 | 67 | 117 | 22 | 405
2851 | 2017-09-26 | 2018-02-08 | 2018-03-17 | 2018-03-17 | COMP | 2019-02-01 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-03-26 | COMP | Rule 16 | 92 | 26 | 221 | 17 | 1 | 21 | 374
2884 | 2017-09-26 | 2018-02-13 | 2018-05-16 | 2019-02-27 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-29 | COMP | Rule 16 | 95 | 66 | 24 | 1 | 1 | 21 | 398
3242 | 2017-09-26 | 2018-03-27 | 2018-04-24 | 2018-04-24 | COMP | 2019-01-14 | COMP | 2019-01-18 | COMP | 2019-01-28 | COMP | 2019-03-19 | COMP | Rule 16 | 124 | 21 | 182 | 5 | 6 | 36 | 369
4393 | 2017-09-26 | 2017-11-16 | 2018-04-03 | 2018-04-03 | COMP | 2018-07-24 | COMP | 2019-10-14 | COMP | 2019-10-10 | COMP | 2019-12-03 | COMP | Rule 16 | 37 | 93 | 79 | 309 | 0 | 34 | 548
4576 | 2017-09-26 | 2018-02-05 | 2018-04-04 | 2018-04-04 | COMP | 2018-06-12 | COMP | 2018-06-12 | COMP | 2019-10-14 | COMP | 2019-11-07 | COMP | Rule 16 | 89 | 42 | 49 | 1 | 338 | 19 | 533
5318 | 2017-09-26 | 2018-05-21 | 2018-09-27 | 2018-09-27 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-01-10 | COMP | 2019-02-05 | COMP | Rule 16 | 163 | 91 | 47 | 1 | 25 | 18 | 340
2227 | 2017-09-27 | 2017-10-18 | 2018-04-24 | 2018-04-24 | COMP | 2018-07-24 | COMP | 2018-06-26 | COMP | 2019-01-16 | COMP | 2019-01-27 | COMP | Rule 15/16 | 16 | 128 | 64 |  | 140 | 7 | 332
2245 | 2017-09-27 | 2017-10-20 | 2018-04-02 | 2018-04-02 | COMP | 2019-11-21 | COMP | 2018-09-27 | COMP | 2020-01-31 | COMP | 2020-05-14 | COMP | Rule 15/16 | 18 | 110 | 415 |  | 336 | 74 | 660
2265 | 2017-09-27 | 2017-10-25 | 2018-08-08 | 2018-08-08 | COMP | 2019-06-04 | COMP | 2019-06-05 | COMP | 2019-11-04 | COMP | 2020-02-21 | COMP | Rule 15/16 | 21 | 197 | 206 | 2 | 107 | 73 | 601
2309 | 2017-09-27 | 2017-11-01 | 2018-08-11 | 2018-08-11 | COMP | 2018-12-06 | COMP | 2018-12-11 | COMP | 2019-03-14 | COMP | 2019-04-29 | COMP | Rule 15/16 | 26 | 194 | 80 | 4 | 64 | 33 | 397
2853 | 2017-09-27 | 2018-02-08 | 2018-05-09 | 2018-05-09 | COMP | 2018-08-07 | COMP | 2018-08-07 | COMP | 2018-12-13 | COMP | 2019-02-08 | COMP | Rule 15/16 | 91 | 64 | 63 | 1 | 89 | 39 | 342
4372 | 2017-09-27 | 2017-10-28 | 2018-02-28 | 2018-06-05 | COMP | 2018-12-28 | COMP | 2018-12-28 | COMP | 2019-05-06 | COMP | 2019-07-28 | COMP | Rule 16 | 23 | 81 | 143 | 1 | 89 | 58 | 459
4497 | 2017-09-27 | 2018-01-09 | 2018-07-18 | 2018-08-31 | COMP | 2018-09-18 | COMP | 2019-06-06 | COMP | 2019-06-07 | COMP | 2019-07-15 | COMP | Rule 15/16 | 70 | 133 | 12 | 180 | 2 | 26 | 450
5047 | 2017-09-27 | 2018-04-27 | 2018-09-04 | 2018-09-04 | COMP | 2018-10-11 | COMP | 2018-10-11 | COMP | 2018-11-28 | COMP | 2019-01-18 | COMP | Rule 16 | 146 | 90 | 28 | 1 | 32 | 36 | 328
5381 | 2017-09-27 | 2018-05-25 | 2018-09-27 | 2018-11-11 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-05-22 | COMP | 2019-06-17 | COMP | Rule 16 | 166 | 87 | 9 | 1 | 123 | 18 | 431
5982 | 2017-09-27 | 2018-07-17 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-20 | COMP | 2019-04-18 | COMP | 2019-06-03 | COMP | 2019-06-25 | COMP | Rule 15/16 | 201 | 121 | 29 | 42 | 32 | 17 | 437
6041 | 2017-09-27 | 2018-07-20 | 2019-03-12 | 2019-06-27 | COMP | 2019-08-09 | COMP | 2019-09-25 | COMP | 2019-11-08 | COMP | 2020-02-21 | COMP | Rule 15/16 | 204 | 160 | 31 | 33 | 33 | 69 | 601
39145 | 2017-09-27 | 2022-10-03 | 2023-01-06 | 2023-01-06 | COMP | 2023-01-24 | NOTN | 2023-03-06 | COMP | 2023-01-24 | COMP | 2023-04-04 | COMP | Other | 1261 | 65 |  | 40 | 0 | 22 | 1385
2223 | 2017-09-28 | 2017-10-18 | 2017-10-31 | 2017-10-31 | COMP | 2017-11-17 | COMP | 2017-11-17 | COMP | 2018-12-21 | COMP | 2019-01-15 | COMP | Rule 16 | 15 | 10 | 13 | 1 | 274 | 16 | 324
2228 | 2017-09-28 | 2017-10-18 | 2018-03-18 | 2018-03-18 | COMP | 2018-03-30 | COMP | 2018-11-27 | COMP | 2019-04-20 | INPR | 2019-01-22 | COMP | Rule 15/16 | 15 | 101 | 10 | 167 |  |  | 328
2229 | 2017-09-28 | 2017-10-18 | 2018-03-25 | 2018-03-25 | COMP | 2018-05-15 | COMP | 2019-01-30 | COMP | 2019-01-23 | COMP | 2019-03-01 | COMP | Rule 15/16 | 15 | 106 | 37 | 178 | 0 | 22 | 355
2270 | 2017-09-28 | 2017-10-26 | 2017-12-07 | 2017-12-07 | COMP | 2018-02-13 | COMP | 2018-02-13 | COMP | 2018-03-20 | COMP | 2022-02-04 | COMP | Rule 16 | 21 | 28 | 46 | 1 | 25 | 978 | 1094
2435 | 2017-09-28 | 2017-11-29 | 2018-05-04 | 2018-05-04 | COMP | 2018-05-22 | COMP | 2018-07-31 | COMP | 2018-08-16 | COMP | 2019-01-11 | COMP | Rule 16 | 42 | 109 | 13 | 49 | 13 | 101 | 322
2466 | 2017-09-28 | 2017-12-06 | 2018-04-09 | 2018-04-09 | COMP | 2018-11-19 | COMP | 2021-02-25 | COMP | 2021-09-28 | COMP | 2022-01-20 | COMP | Rule 16 | 47 | 85 | 157 | 569 | 151 | 79 | 1083
2491 | 2017-09-28 | 2017-12-08 | 2018-09-23 | 2018-09-23 | COMP | 2018-11-14 | COMP | 2018-11-14 | INPR |  | REQD | 2019-06-22 | COMP | Other | 49 | 199 | 37 |  |  |  | 434
3107 | 2017-09-28 | 2018-03-09 | 2018-06-15 | 2018-06-15 | COMP | 2019-03-04 | COMP | 2019-03-08 | COMP | 2019-03-07 | COMP | 2019-05-08 | COMP | Rule 16 | 110 | 70 | 178 | 5 | 0 | 44 | 403
3151 | 2017-09-28 | 2018-03-15 | 2018-05-07 | 2018-05-07 | COMP | 2018-07-03 | COMP | 2018-11-29 | COMP | 2018-11-26 | COMP | 2019-01-24 | COMP | Rule 16 | 114 | 38 | 41 | 103 | 0 | 38 | 330
4453 | 2017-09-28 | 2017-12-14 | 2018-03-07 | 2018-03-07 | COMP | 2018-03-21 | COMP | 2018-10-22 | COMP | 2018-05-08 | COMP | 2019-01-24 | COMP | Rule 16 | 53 | 56 | 11 | 151 | 0 | 63 | 330
4529 | 2017-09-28 | 2018-01-25 | 2018-03-13 | 2018-03-13 | COMP | 2018-06-13 | COMP | 2018-06-13 | COMP | 2018-11-15 | COMP | 2019-01-23 | COMP | Rule 16 | 80 | 33 | 66 | 1 | 109 | 45 | 329
4596 | 2017-09-28 | 2018-02-12 | 2018-05-07 | 2018-05-07 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2019-09-01 | INPR | 2019-05-16 | COMP | Rule 16 | 92 | 60 | 109 | 1 |  |  | 409
5258 | 2017-09-28 | 2018-05-15 | 2018-10-23 | 2018-10-23 | COMP | 2019-01-02 | COMP | 2019-02-04 | COMP | 2019-07-23 | COMP | 2019-09-12 | COMP | Rule 15/16 | 157 | 113 | 47 | 23 | 119 | 37 | 491
5931 | 2017-09-28 | 2018-07-12 | 2018-08-10 | 2018-08-10 | COMP | 2018-09-12 | COMP | 2019-07-02 | COMP | 2019-06-29 | COMP | 2019-08-02 | COMP | Rule 16 | 197 | 22 | 23 | 202 | 0 | 23 | 463
7071 | 2017-09-28 | 2018-09-25 | 2018-11-26 | 2018-11-26 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-02-13 | COMP | 2019-05-22 | COMP | Rule 16 | 249 | 42 | 32 | 1 | 24 | 70 | 413
39125 | 2017-09-28 | 2022-10-04 | 2022-12-19 | 2022-12-19 | COMP | 2023-07-04 | NOTN | 2023-08-03 | COMP | 2023-08-03 | COMP | 2023-11-13 | COMP | Other | 1261 | 52 |  | 157 | 1 | 71 | 1538
2210 | 2017-09-29 | 2017-10-12 | 2018-07-20 | 2018-07-20 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2018-11-20 | COMP | 2019-01-02 | COMP | Rule 16 | 10 | 193 | 76 | 1 | 11 | 28 | 314
2319 | 2017-09-29 | 2017-11-02 | 2018-03-02 | 2018-03-02 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-08-31 | INPR | 2019-05-10 | COMP | Rule 16 | 25 | 80 | 267 | 1 |  |  | 404
2359 | 2017-09-29 | 2017-11-10 | 2019-05-10 | 2019-05-10 | COMP | 2019-06-10 | COMP | 2019-08-07 | COMP | 2019-09-17 | COMP | 2019-09-20 | COMP | Rule 16 | 30 | 374 | 21 | 42 | 29 | 4 | 496
2384 | 2017-09-29 | 2017-11-15 | 2018-02-26 | 2018-02-26 | COMP | 2018-09-12 | COMP | 2018-09-21 | COMP | 2019-01-30 | COMP | 2019-03-13 | COMP | Rule 15/16 | 33 | 68 | 140 | 8 | 88 | 30 | 362
3173 | 2017-09-29 | 2018-03-17 | 2018-07-09 | 2018-07-09 | COMP | 2018-11-20 | COMP | 2018-07-11 | COMP | 2019-07-11 | COMP | 2020-04-27 | COMP | Rule 16 | 114 | 79 | 95 |  | 252 | 200 | 645
3589 | 2017-09-29 | 2018-05-22 | 2018-10-24 | 2018-10-24 | COMP | 2019-01-17 | COMP | 2019-08-05 | COMP | 2020-01-08 | COMP | 2020-01-14 | COMP | Rule 15/16 | 161 | 109 | 57 | 139 | 107 | 5 | 573
4384 | 2017-09-29 | 2017-11-08 | 2018-07-29 | 2018-07-29 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2019-09-03 | COMP | 2019-12-09 | COMP | Rule 16 | 29 | 179 | 245 | 1 | 32 | 67 | 549
4387 | 2017-09-29 | 2017-11-08 | 2018-01-12 | 2018-01-12 | COMP | 2018-01-30 | COMP | 2018-03-05 | COMP | 2019-01-14 | COMP | 2019-03-15 | COMP | Rule 16 | 29 | 43 | 12 | 24 | 218 | 43 | 364
4875 | 2017-09-29 | 2018-04-06 | 2018-07-17 | 2018-07-17 | COMP | 2018-10-02 | COMP | 2018-10-02 | COMP | 2019-06-05 | COMP | 2019-07-15 | COMP | Rule 16 | 129 | 71 | 55 | 1 | 169 | 28 | 448
7341 | 2017-09-29 | 2018-10-08 | 2018-11-08 | 2018-11-08 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-12-28 | INPR | 2019-08-08 | COMP | Rule 16 | 257 | 24 | 94 | 1 |  |  | 466
11250 | 2017-09-29 | 2019-04-20 | 2019-07-18 | 2019-07-18 | COMP | 2019-10-01 | COMP | 2019-09-11 | COMP | 2019-09-13 | COMP | 2019-10-14 | COMP | Rule 16 | 389 | 62 | 53 |  | 3 | 22 | 512
20178 | 2017-09-29 | 2020-06-09 | 2020-10-12 | 2020-10-27 | COMP | 2020-10-30 | COMP | 2020-10-30 | COMP | 2022-04-17 | INPR | 2021-03-22 | COMP | Rule 16 | 675 | 89 | 4 | 1 |  |  | 871
22295 | 2017-09-29 | 2020-09-18 | 2021-02-04 | 2021-02-04 | COMP | 2021-02-05 | NOTN | 2021-02-26 | COMP |  | INPR | 2021-05-12 | COMP | Rule 15 | 747 | 94 |  | 16 |  |  | 908
27983 | 2017-09-29 | 2021-05-17 | 2021-08-01 | 2021-11-17 | COMP | 2022-01-27 | COMP | 2022-04-14 | COMP | 2022-03-15 | COMP | 2022-06-06 | COMP | Rule 15/16 | 911 | 53 | 49 | 55 | 0 | 37 | 1177
2963 | 2017-09-30 | 2018-02-23 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-30 | COMP | 2019-06-14 | COMP | 2020-05-30 | INPR | 2019-11-13 | COMP | Rule 16 | 98 | 259 | 40 | 33 |  |  | 532
3002 | 2017-09-30 | 2018-02-26 | 2019-12-23 | 2019-12-23 | COMP | 2020-01-17 | COMP | 2020-03-27 | COMP | 2020-10-12 | COMP | 2020-07-09 | COMP | Rule 16 | 99 | 460 | 18 | 49 | 140 |  | 696
2311 | 2017-10-02 | 2017-11-01 | 2018-04-09 | 2018-04-16 | COMP | 2018-10-18 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-04-20 | COMP | Rule 16 | 23 | 107 | 131 | 58 | 1 | 68 | 388
2567 | 2017-10-02 | 2017-12-26 | 2018-02-19 | 2018-02-19 | COMP | 2018-06-25 | COMP | 2018-06-25 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | Rule 16 | 58 | 37 | 89 | 1 | 281 | 1 | 463
2579 | 2017-10-02 | 2017-12-29 | 2018-11-01 | 2018-11-01 | COMP | 2018-12-06 | COMP | 2019-03-06 | COMP |  | INPR | 2019-03-16 | COMP | Rule 15/16 | 61 | 214 | 23 | 61 |  |  | 363
2580 | 2017-10-02 | 2017-12-29 | 2018-02-26 | 2018-12-20 | COMP | 2020-05-21 | COMP | 2019-03-19 | COMP | 2020-03-05 | COMP | 2020-06-05 | COMP | Rule 15/16 | 61 | 39 | 357 |  | 243 | 66 | 672
2640 | 2017-10-02 | 2018-01-10 | 2018-01-11 | 2018-01-11 | COMP | 2018-01-18 | COMP | 2018-01-18 | COMP | 2018-04-10 | COMP | 2021-01-20 | COMP | Rule 16 | 68 | 2 | 5 | 1 | 58 | 699 | 828
2683 | 2017-10-02 | 2018-01-18 | 2018-07-03 | 2018-07-03 | COMP | 2018-11-01 | COMP | 2019-01-28 | COMP | 2021-02-27 | INPR | 2019-02-24 | COMP | Rule 16 | 73 | 117 | 86 | 57 |  |  | 348
2908 | 2017-10-02 | 2018-02-15 | 2018-10-25 | 2018-10-25 | COMP | 2019-01-06 | NOTN | 2019-05-14 | COMP | 2019-11-05 | COMP | 2019-12-12 | COMP | Other | 93 | 177 |  | 137 | 123 | 25 | 551
3008 | 2017-10-02 | 2018-02-27 | 2018-09-12 | 2018-09-12 | COMP | 2019-06-17 | COMP | 2019-07-08 | COMP | 2019-07-30 | COMP | 2019-08-07 | COMP | Rule 15/16 | 100 | 139 | 191 | 15 | 17 | 7 | 464
3226 | 2017-10-02 | 2018-03-26 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-31 | COMP | 2019-08-01 | COMP | 2019-07-05 | COMP | 2020-01-23 | COMP | Rule 16 | 119 | 80 | 34 | 230 | 0 | 119 | 578
3621 | 2017-10-02 | 2018-05-24 | 2018-12-08 | 2018-12-08 | COMP | 2019-01-14 | COMP | 2019-01-15 | COMP | 2023-04-15 | INPR | 2020-08-04 | COMP | Rule 15/16 | 162 | 136 | 24 | 2 |  |  | 714
4380 | 2017-10-02 | 2017-11-03 | 2017-12-12 | 2017-12-12 | COMP | 2018-03-06 | COMP | 2018-03-23 | COMP | 2019-10-29 | COMP | 2019-12-09 | COMP | Rule 16 | 25 | 25 | 57 | 14 | 405 | 27 | 548
4495 | 2017-10-02 | 2018-01-09 | 2018-09-05 | 2018-09-05 | COMP | 2019-03-28 | COMP | 2019-06-28 | COMP | 2020-07-16 | COMP | 2020-08-21 | COMP | Rule 16 | 67 | 167 | 140 | 66 | 265 | 27 | 727
4510 | 2017-10-02 | 2018-01-17 | 2018-09-24 | 2018-09-24 | COMP | 2018-10-10 | COMP | 2018-10-10 | INPR | 2019-01-02 | COMP | 2019-01-14 | COMP | Rule 16 | 72 | 175 | 13 |  |  |  | 321
4659 | 2017-10-02 | 2018-02-28 | 2018-05-16 | 2018-05-16 | COMP | 2018-06-25 | COMP | 2018-06-25 | COMP | 2019-07-21 | INPR | 2019-04-23 | COMP | Rule 16 | 101 | 56 | 28 | 1 |  |  | 390
4987 | 2017-10-02 | 2018-04-20 | 2018-10-22 | 2018-10-22 | COMP | 2018-11-02 | COMP | 2019-03-20 | COMP | 2020-03-06 | COMP | 2020-06-10 | COMP | Rule 16 | 138 | 129 | 10 | 92 | 243 | 68 | 675
9579 | 2017-10-02 | 2019-02-08 | 2019-04-01 | 2020-04-30 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-12-18 | COMP | 2021-04-07 | COMP | Rule 16 | 339 | 36 | 31 | 1 | 132 | 75 | 882
2186 | 2017-10-03 | 2017-10-05 | 2017-11-15 | 2017-11-15 | COMP | 2018-12-14 | NOTN | 2018-12-14 | COMP | 2018-12-14 | COMP | 2019-01-31 | COMP | Other | 3 | 29 |  | 271 | 1 | 32 | 332
2329 | 2017-10-03 | 2017-11-03 | 2020-10-15 | 2020-10-15 | COMP | 2021-03-18 | COMP | 2021-09-14 | COMP | 2021-08-20 | COMP | 2021-10-01 | COMP | Rule 16 | 24 | 741 | 104 | 126 | 0 | 14 | 1005
2330 | 2017-10-03 | 2017-11-03 | 2019-05-16 | 2019-05-16 | COMP | 2019-09-17 | COMP | 2019-11-05 | COMP | 2020-05-30 | INPR | 2019-12-12 | COMP | Rule 16 | 24 | 383 | 86 | 36 |  |  | 550
2343 | 2017-10-03 | 2017-11-07 | 2018-07-09 | 2018-07-09 | COMP | 2019-04-04 | COMP | 2019-04-10 | COMP | 2019-04-17 | COMP | 2019-06-19 | COMP | Rule 15/16 | 26 | 166 | 186 | 5 | 6 | 45 | 429
2587 | 2017-10-03 | 2018-01-03 | 2018-01-30 | 2018-01-30 | COMP | 2018-01-31 | COMP | 2018-03-20 | COMP | 2019-04-19 | COMP | 2019-07-15 | COMP | Rule 16 | 62 | 19 | 2 | 34 | 274 | 60 | 446
2969 | 2017-10-03 | 2018-02-23 | 2018-08-13 | 2019-04-20 | COMP | 2019-06-12 | COMP | 2019-07-19 | COMP | 2019-06-26 | COMP | 2019-10-04 | COMP | Rule 15/16 | 97 | 120 | 37 | 27 | 0 | 55 | 504
3023 | 2017-10-03 | 2018-02-27 | 2018-07-11 | 2018-07-11 | COMP | 2018-08-13 | COMP | 2018-08-13 | COMP | 2018-12-22 | COMP | 2019-03-16 | COMP | Rule 16 | 99 | 95 | 24 | 1 | 91 | 56 | 362
3044 | 2017-10-03 | 2018-03-02 | 2018-04-08 | 2018-04-08 | COMP | 2018-05-03 | COMP | 2018-08-21 | COMP | 2018-11-27 | COMP | 2019-01-30 | COMP | Rule 16 | 102 | 26 | 19 | 77 | 67 | 44 | 331
3184 | 2017-10-03 | 2018-03-19 | 2018-06-13 | 2018-06-13 | COMP | 2019-05-02 | COMP | 2019-05-20 | COMP | 2021-02-27 | INPR | 2019-10-18 | COMP | Rule 15/16 | 113 | 62 | 223 | 13 |  |  | 514
3471 | 2017-10-03 | 2018-05-02 | 2019-03-06 | 2019-03-06 | COMP | 2019-10-04 | COMP | 2020-09-18 | COMP | 2020-11-20 | COMP | 2021-01-06 | COMP | Rule 15/16 | 145 | 211 | 150 | 242 | 45 | 30 | 818
3480 | 2017-10-03 | 2018-05-04 | 2019-02-15 | 2019-02-15 | COMP | 2019-09-27 | COMP | 2019-04-25 | NOTN | 2019-12-10 | COMP | 2020-04-08 | COMP | Rule 16 | 147 | 197 | 157 |  |  |  | 630
3739 | 2017-10-03 | 2018-06-23 | 2018-12-05 | 2018-12-05 | COMP | 2019-10-16 | COMP | 2019-11-18 | COMP | 2020-06-15 | COMP | 2020-07-16 | COMP | Rule 15/16 | 181 | 113 | 219 | 23 | 144 | 24 | 700
4520 | 2017-10-03 | 2018-01-19 | 2018-04-13 | 2018-04-13 | COMP | 2018-06-28 | COMP | 2019-03-22 | INPR | 2019-03-19 | COMP | 2019-04-16 | COMP | Rule 16 | 73 | 60 | 54 |  |  |  | 384
4708 | 2017-10-03 | 2018-03-20 | 2018-08-10 | 2018-08-10 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2020-11-19 | COMP | 2021-01-13 | COMP | Rule 16 | 114 | 102 | 42 | 1 | 533 | 36 | 823
7466 | 2017-10-03 | 2018-10-16 | 2019-02-11 | 2019-02-11 | COMP | 2019-04-16 | COMP | 2019-10-21 | REQD | 2019-10-21 | REQD | 2019-05-07 | COMP | Rule 16 | 261 | 79 | 46 |  |  |  | 399
8873 | 2017-10-03 | 2019-01-03 | 2019-02-12 | 2019-02-12 | COMP | 2019-03-06 | COMP | 2019-05-21 | COMP | 2019-11-14 | COMP | 2020-02-25 | COMP | Rule 16 | 313 | 28 | 16 | 55 | 124 | 68 | 599
2260 | 2017-10-04 | 2017-10-25 | 2017-12-14 | 2017-12-14 | COMP | 2018-09-19 | COMP | 2018-09-19 | COMP | 2019-09-21 | INPR | 2019-05-22 | COMP | Rule 16 | 16 | 34 | 193 | 1 |  |  | 409
2282 | 2017-10-04 | 2017-10-27 | 2018-04-05 | 2018-04-05 | COMP | 2018-04-27 | COMP | 2018-04-27 | COMP | 2019-07-02 | COMP | 2019-08-13 | COMP | Rule 15/16 | 18 | 108 | 17 | 1 | 297 | 30 | 466
2310 | 2017-10-04 | 2017-11-01 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-16 | COMP | 2019-05-29 | COMP | 2021-01-08 | COMP | 2021-04-07 | COMP | Rule 16 | 21 | 363 | 23 | 9 | 407 | 62 | 880
2331 | 2017-10-04 | 2017-11-03 | 2019-11-01 | 2019-11-01 | COMP | 2020-03-18 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-09 | COMP | Rule 16 | 23 | 501 | 92 | 53 | 1 | 7 | 672
2332 | 2017-10-04 | 2017-11-03 | 2018-11-09 | 2018-11-09 | COMP | 2019-05-02 | COMP | 2019-12-13 | COMP | 2020-05-30 | INPR | 2019-09-23 | COMP | Rule 16 | 23 | 256 | 118 | 156 |  |  | 494
2333 | 2017-10-04 | 2017-11-03 | 2019-10-23 | 2019-10-23 | COMP | 2020-02-05 | COMP | 2020-11-24 | COMP | 2020-05-01 | COMP | 2020-12-08 | COMP | Rule 16 | 23 | 494 | 70 | 206 | 0 | 9 | 798
2334 | 2017-10-04 | 2017-11-03 | 2020-01-29 | 2020-01-29 | COMP | 2020-05-05 | COMP | 2020-06-19 | COMP | 2020-06-10 | COMP | 2020-07-01 | COMP | Rule 16 | 23 | 558 | 69 | 33 | 0 | 9 | 688
2716 | 2017-10-04 | 2018-01-23 | 2018-11-14 | 2018-11-14 | COMP | 2019-01-31 | COMP | 2020-05-06 | COMP | 2020-04-29 | COMP | 2020-10-23 | COMP | Rule 16 | 74 | 207 | 52 | 319 | 0 | 121 | 769
3514 | 2017-10-04 | 2018-05-09 | 2018-05-15 | 2018-05-15 | COMP | 2018-07-18 | NOTN | 2018-07-18 | NOTN | 2019-03-06 | COMP | 2019-03-13 | COMP | Rule 16 | 149 | 5 |  |  |  |  | 359
6192 | 2017-10-04 | 2018-08-03 | 2018-10-29 | 2018-10-29 | COMP | 2019-12-27 | COMP | 2020-06-01 | COMP | 2023-11-11 | INPR | 2020-12-01 | COMP | Rule 15/16 | 209 | 61 | 291 | 108 |  |  | 793
2208 | 2017-10-05 | 2017-10-12 | 2017-11-14 | 2017-11-14 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-04-23 | COMP | 2019-05-23 | COMP | Rule 16 | 6 | 23 | 311 | 1 | 50 | 23 | 409
2355 | 2017-10-05 | 2017-11-09 | 2018-06-28 | 2018-06-28 | COMP | 2019-05-03 | COMP | 2019-05-15 | COMP | 2019-12-03 | COMP | 2020-05-22 | COMP | Rule 15/16 | 26 | 158 | 213 | 9 | 139 | 120 | 660
2511 | 2017-10-05 | 2017-12-12 | 2018-01-29 | 2018-01-29 | COMP | 2018-03-08 | COMP | 2018-03-31 | COMP | 2018-05-01 | COMP | 2022-05-04 | COMP | Rule 16 | 46 | 32 | 28 | 17 | 22 | 1010 | 1151
2962 | 2017-10-05 | 2018-02-23 | 2018-12-20 | 2018-12-20 | COMP | 2018-12-04 | COMP | 2018-12-20 | COMP | 2018-12-05 | COMP | 2019-01-25 | COMP | Rule 16 | 95 | 209 |  | 13 | 0 | 24 | 326
3071 | 2017-10-05 | 2018-03-05 | 2018-08-30 | 2018-08-30 | COMP | 2018-09-18 | COMP | 2018-09-27 | COMP | 2019-06-29 | INPR | 2019-02-28 | COMP | Rule 15/16 | 101 | 127 | 13 | 8 |  |  | 349
3744 | 2017-10-05 | 2018-06-25 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-04 | COMP | 2019-02-14 | COMP | 2019-02-22 | COMP | 2019-04-11 | COMP | Rule 16 | 180 | 97 | 16 | 50 | 6 | 35 | 379
4406 | 2017-10-05 | 2017-11-20 | 2018-04-10 | 2018-04-10 | COMP | 2018-05-01 | COMP | 2018-05-29 | COMP | 2019-12-27 | COMP | 2023-03-10 | COMP | Rule 16 | 32 | 96 | 16 | 20 | 398 | 805 | 1362
4553 | 2017-10-05 | 2018-01-31 | 2018-07-05 | 2018-07-05 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-01-16 | COMP | 2019-03-21 | COMP | Rule 16 | 79 | 109 | 98 | 1 | 37 | 45 | 364
4562 | 2017-10-05 | 2018-01-31 | 2018-07-20 | 2018-07-20 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-02-12 | COMP | 2019-04-30 | COMP | Rule 16 | 79 | 120 | 170 | 1 | 0 | 26 | 392
4595 | 2017-10-05 | 2018-02-09 | 2018-04-17 | 2018-04-17 | COMP | 2018-07-23 | COMP | 2018-07-23 | COMP | 2019-10-21 | INPR | 2019-07-04 | COMP | Rule 15 | 86 | 47 | 68 | 1 |  |  | 437
5513 | 2017-10-05 | 2018-06-06 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-09-19 | COMP | 2019-10-15 | COMP | Rule 16 | 167 | 96 | 25 | 1 | 206 | 19 | 509
6046 | 2017-10-05 | 2018-07-23 | 2018-12-13 | 2019-06-30 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-11-08 | COMP | 2020-02-04 | COMP | Rule 15/16 | 199 | 100 | 29 | 1 | 65 | 57 | 583
6876 | 2017-10-05 | 2018-09-14 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-04 | COMP | 2019-01-16 | COMP | 2019-07-21 | INPR | 2019-02-12 | COMP | Rule 15/16 | 237 | 45 | 11 | 30 |  |  | 338
39149 | 2017-10-05 | 2022-10-04 | 2023-01-11 | 2023-01-11 | COMP | 2023-01-11 | NOTN | 2023-10-05 | COMP | 2023-08-04 | COMP | 2023-10-24 | COMP | Other | 1256 | 67 |  | 186 | 0 | 14 | 1520
39150 | 2017-10-05 | 2022-10-04 | 2023-01-25 | 2023-01-25 | COMP | 2023-01-25 | NOTN | 2023-06-30 | COMP | 2023-02-14 | COMP | 2023-10-16 | COMP | Other | 1256 | 76 |  | 110 | 0 | 75 | 1514
2297 | 2017-10-06 | 2017-10-30 | 2018-01-30 | 2018-01-30 | COMP | 2018-03-26 | COMP | 2018-03-26 | COMP | 2019-07-24 | COMP | 2019-10-15 | COMP | Rule 16 | 17 | 61 | 39 | 1 | 336 | 59 | 508
2552 | 2017-10-06 | 2017-12-21 | 2018-02-22 | 2018-02-22 | COMP | 2018-04-25 | COMP | 2018-05-02 | COMP | 2019-09-21 | INPR | 2019-05-21 | COMP | Rule 16 | 52 | 42 | 45 | 6 |  |  | 406
2588 | 2017-10-06 | 2018-01-03 | 2018-03-20 | 2018-03-16 | COMP | 2018-08-08 | COMP | 2019-05-16 | COMP | 2019-05-14 | COMP | 2019-06-11 | COMP | Rule 16 | 59 | 53 | 102 | 194 | 0 | 18 | 420
3271 | 2017-10-06 | 2018-03-29 | 2018-09-13 | 2018-09-13 | COMP | 2018-10-30 | COMP | 2018-11-14 | COMP | 2019-11-13 | COMP | 2020-02-06 | COMP | Rule 15/16 | 118 | 118 | 34 | 11 | 251 | 57 | 584
4715 | 2017-10-06 | 2018-03-21 | 2019-03-09 | 2019-06-29 | COMP | 2019-12-03 | COMP | 2020-04-01 | COMP | 2020-01-31 | COMP | 2020-05-04 | COMP | Rule 15/16 | 112 | 243 | 107 | 83 | 0 | 24 | 645
4994 | 2017-10-06 | 2018-04-19 | 2018-08-23 | 2018-08-23 | COMP | 2019-01-04 | COMP | 2019-01-09 | COMP | 2019-01-23 | COMP | 2019-05-30 | COMP | Rule 16 | 133 | 89 | 91 | 4 | 10 | 90 | 412
5180 | 2017-10-06 | 2018-05-08 | 2018-09-11 | 2020-11-15 | COMP | 2021-03-31 | COMP | 2020-06-24 | COMP | 2020-09-03 | COMP | 2020-11-05 | COMP | Rule 15/16 | 146 | 88 | 92 |  | 52 | 45 | 776
8684 | 2017-10-06 | 2018-12-18 | 2019-02-11 | 2019-02-11 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-09-06 | COMP | 2019-09-19 | COMP | Rule 16 | 300 | 37 | 21 | 1 | 126 | 10 | 490
9338 | 2017-10-06 | 2019-01-30 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-02 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-07-09 | COMP | Rule 16 | 328 | 57 | 9 | 23 | 1 | 25 | 439
11857 | 2017-10-06 | 2019-05-14 | 2020-01-02 | 2020-01-02 | COMP | 2020-01-17 | COMP | 2020-02-13 | COMP | 2020-01-02 | COMP | 2020-03-22 | COMP | Rule 16 | 401 | 160 | 12 | 19 | 0 | 26 | 614
2356 | 2017-10-08 | 2017-11-09 | 2018-06-26 | 2018-06-26 | COMP | 2019-01-03 | COMP | 2018-08-29 | COMP | 2019-03-20 | COMP | 2019-07-20 | COMP | Rule 15/16 | 24 | 156 | 131 |  | 138 | 86 | 446
3330 | 2017-10-08 | 2018-04-09 | 2018-05-10 | 2018-05-10 | COMP | 2018-07-20 | COMP | 2018-07-31 | COMP | 2019-01-22 | COMP | 2019-01-28 | COMP | Rule 16 | 124 | 24 | 50 | 8 | 119 | 5 | 325
2256 | 2017-10-09 | 2017-10-25 | 2018-09-01 | 2018-09-01 | COMP | 2018-12-11 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-01-31 | COMP | Rule 16 | 13 | 214 | 68 | 7 | 1 | 29 | 328
2296 | 2017-10-09 | 2017-10-30 | 2017-12-05 | 2017-12-05 | COMP | 2018-02-06 | COMP | 2019-03-12 | COMP | 2019-03-16 | COMP | 2019-04-23 | COMP | Rule 15/16 | 16 | 24 | 43 | 275 | 4 | 27 | 385
2302 | 2017-10-09 | 2017-10-31 | 2018-05-16 |  | INPR |  | INPR | 2020-02-05 | COMP | 2020-02-06 | COMP | 2020-06-09 | COMP | Rule 15/16 | 17 |  |  |  | 2 | 87 | 669
2586 | 2017-10-09 | 2018-01-03 | 2018-06-25 | 2018-06-25 | COMP | 2020-11-02 | COMP | 2021-10-28 | COMP | 2021-10-22 | COMP | 2021-11-30 | COMP | Rule 15/16 | 58 | 121 | 595 | 249 | 0 | 21 | 1040
3391 | 2017-10-09 | 2018-04-18 | 2018-09-25 | 2018-09-25 | COMP | 2020-04-24 | COMP | 2023-11-01 | INPR | 2020-10-14 | COMP | 2021-01-21 | COMP | Rule 15/16 | 131 | 112 | 397 |  |  |  | 824
3393 | 2017-10-09 | 2018-04-18 | 2018-07-24 | 2018-07-24 | COMP | 2018-08-22 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-06-07 | COMP | Rule 16 | 131 | 68 | 22 | 178 | 1 | 22 | 417
3827 | 2017-10-09 | 2018-08-02 | 2018-09-10 | 2018-09-10 | COMP | 2019-01-02 | COMP | 2019-04-24 | COMP | 2019-04-18 | COMP | 2019-05-09 | COMP | Rule 15 | 205 | 27 | 78 | 79 | 0 | 12 | 397
4474 | 2017-10-09 | 2018-01-02 | 2018-07-06 | 2018-07-06 | COMP | 2018-07-31 | COMP | 2019-02-12 | COMP | 2019-01-25 | COMP | 2019-03-21 | COMP | Rule 16 | 57 | 130 | 18 | 134 | 0 | 27 | 362
4858 | 2017-10-09 | 2018-04-06 | 2018-05-22 | 2018-05-22 | COMP | 2018-06-07 | COMP | 2018-06-07 | COMP | 2019-07-22 | COMP | 2019-07-26 | COMP | Rule 16 | 123 | 33 | 12 | 1 | 282 | 5 | 451
4864 | 2017-10-09 | 2018-04-05 | 2018-07-18 | 2018-07-18 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-04-24 | COMP | 2019-06-22 | COMP | Rule 16 | 122 | 73 | 180 | 1 | 14 | 42 | 427
14229 | 2017-10-09 | 2019-08-29 | 2020-01-21 | 2020-03-09 | COMP | 2020-03-27 | COMP | 2020-05-01 | COMP | 2020-10-28 | COMP | 2020-11-18 | COMP | Rule 16 | 475 | 97 | 15 | 26 | 127 | 15 | 783
2251 | 2017-10-10 | 2017-10-23 | 2018-01-11 | 2018-01-11 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-02-20 | COMP | Rule 16 | 10 | 54 | 257 | 1 | 1 | 22 | 340
2533 | 2017-10-10 | 2017-12-18 | 2018-04-14 | 2018-04-14 | COMP | 2018-04-19 | COMP | 2020-01-24 | COMP | 2018-05-22 | COMP | 2020-02-21 | COMP | Rule 16 | 47 | 81 | 4 | 443 | 0 | 20 | 592
2723 | 2017-10-10 | 2018-01-24 | 2018-08-16 | 2019-02-04 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-11-20 | COMP | 2019-12-27 | COMP | Rule 16 | 71 | 144 | 192 | 1 | 12 | 25 | 555
2724 | 2017-10-10 | 2018-01-24 | 2018-03-12 | 2018-03-12 | COMP | 2019-10-28 | COMP | 2019-11-04 | COMP | 2019-09-25 | COMP | 2020-01-07 | COMP | Rule 16 | 71 | 33 | 413 | 6 | 0 | 42 | 561
2725 | 2017-10-10 | 2018-01-24 | 2018-09-25 | 2018-09-25 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-11-20 | COMP | 2019-12-24 | COMP | Rule 16 | 71 | 171 | 280 | 1 | 12 | 23 | 553
2728 | 2017-10-10 | 2018-01-24 | 2018-08-09 | 2018-08-09 | COMP | 2019-10-28 | COMP | 2019-11-04 | COMP | 2019-11-20 | COMP | 2019-12-26 | COMP | Rule 16 | 71 | 139 | 307 | 6 | 12 | 24 | 554
2729 | 2017-10-10 | 2018-01-24 | 2018-03-30 | 2018-03-30 | COMP | 2019-10-28 | COMP | 2019-11-04 | COMP | 2019-09-25 | COMP | 2020-01-06 | COMP | Rule 15/16 | 71 | 47 | 399 | 6 | 0 | 41 | 560
3198 | 2017-10-10 | 2018-03-21 | 2018-05-08 | 2018-05-08 | COMP | 2018-07-10 | COMP | 2018-08-16 | COMP |  | INPR | 2022-04-20 | COMP | Rule 16 | 110 | 35 | 44 | 28 |  |  | 1138
4507 | 2017-10-10 | 2018-01-17 | 2018-02-13 | 2018-02-13 | COMP | 2018-05-08 | COMP | 2018-05-08 | COMP | 2018-12-18 | COMP | 2019-01-08 | COMP | Rule 16 | 66 | 20 | 60 | 1 | 155 | 14 | 311
4517 | 2017-10-10 | 2018-01-18 | 2018-02-28 | 2018-03-21 | COMP | 2018-10-02 | COMP | 2018-10-02 | COMP | 2019-10-29 | COMP | 2019-12-30 | COMP | Rule 16 | 67 | 29 | 137 | 1 | 271 | 41 | 556
5218 | 2017-10-10 | 2018-05-10 | 2018-09-07 | 2018-09-07 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-05-13 | COMP | 2019-07-16 | COMP | Rule 16 | 146 | 84 | 95 | 1 | 76 | 45 | 442
5227 | 2017-10-10 | 2018-05-14 | 2018-07-18 | 2018-12-19 | COMP | 2019-02-07 | COMP | 2019-07-01 | COMP | 2020-04-06 | COMP | 2020-06-18 | COMP | Rule 16 | 148 | 46 | 34 | 101 | 192 | 53 | 675
15410 | 2017-10-10 | 2019-11-01 | 2020-04-23 | 2020-04-23 | COMP | 2021-12-10 | COMP | 2021-12-13 | COMP | 2022-07-20 | COMP | 2022-10-05 | COMP | Rule 16 | 519 | 118 | 412 | 2 | 153 | 55 | 1254
2374 | 2017-10-11 | 2017-11-14 | 2017-12-14 | 2017-12-14 | COMP | 2018-01-02 | COMP | 2018-05-31 | COMP | 2020-06-05 | COMP | 2020-07-23 | COMP | Rule 15/16 | 24 | 21 | 12 | 105 | 507 | 35 | 699
2477 | 2017-10-11 | 2017-12-06 | 2018-02-06 | 2018-02-06 | COMP | 2018-03-05 | COMP | 2018-03-14 | COMP | 2018-10-20 | COMP | 2019-02-28 | COMP | Rule 16 | 38 | 42 | 19 | 8 | 155 | 87 | 345
3488 | 2017-10-11 | 2018-05-07 | 2018-11-25 | 2018-07-11 | COMP | 2018-11-24 | NOTN | 2018-11-25 | COMP | 2018-11-24 | COMP | 2019-01-31 | COMP | Other | 142 | 139 |  | 94 | 0 | 46 | 326
3509 | 2017-10-11 | 2018-05-08 | 2018-07-25 | 2018-07-25 | COMP | 2018-11-24 | NOTN | 2018-11-24 | COMP | 2018-11-24 | COMP | 2019-01-31 | COMP | Other | 143 | 55 |  | 84 | 0 | 46 | 326
4402 | 2017-10-11 | 2017-11-16 | 2018-03-09 | 2019-03-11 | COMP | 2019-03-18 | COMP | 2019-05-09 | COMP | 2019-12-13 | COMP | 2020-02-03 | COMP | Rule 15/16 | 26 | 76 | 6 | 39 | 151 | 34 | 578
4403 | 2017-10-11 | 2017-11-17 | 2018-03-16 | 2018-03-16 | COMP | 2018-04-20 | COMP | 2018-04-22 | COMP | 2018-12-07 | COMP | 2019-01-30 | COMP | Rule 16 | 27 | 80 | 26 | 1 | 159 | 36 | 325
4792 | 2017-10-11 | 2018-03-30 | 2018-07-31 | 2018-11-14 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-01-04 | COMP | 2019-01-14 | COMP | Rule 16 | 116 | 86 | 16 | 1 | 19 | 7 | 314
7324 | 2017-10-11 | 2018-10-08 | 2019-01-16 | 2021-03-03 | COMP | 2021-05-25 | COMP | 2021-05-25 | COMP | 2023-04-15 | INPR | 2021-10-09 | COMP | Rule 15/16 | 249 | 68 | 60 | 1 |  |  | 1004
10550 | 2017-10-11 | 2019-03-19 | 2019-07-01 | 2019-07-08 | COMP | 2020-02-21 | COMP | 2020-03-03 | COMP | 2020-07-20 | COMP | 2020-09-30 | COMP | Rule 16 | 358 | 74 | 157 | 8 | 99 | 52 | 747
2247 | 2017-10-12 | 2017-10-21 | 2018-04-16 | 2018-04-16 | COMP | 2018-06-05 | COMP | 2019-01-28 | COMP | 2019-05-17 | COMP | 2019-05-29 | COMP | Rule 15/16 | 7 | 119 | 36 | 162 | 79 | 8 | 407
2308 | 2017-10-12 | 2017-11-01 | 2018-06-25 | 2020-05-28 | COMP | 2020-09-22 | COMP | 2020-12-07 | COMP | 2020-11-10 | COMP | 2021-01-14 | COMP | Rule 15/16 | 15 | 161 | 83 | 52 | 0 | 27 | 817
2513 | 2017-10-12 | 2017-12-12 | 2018-08-11 | 2018-08-11 | COMP | 2018-08-22 | COMP | 2018-11-14 | COMP | 2019-03-11 | COMP | 2019-04-19 | COMP | Rule 15/16 | 41 | 168 | 8 | 59 | 78 | 30 | 380
2566 | 2017-10-12 | 2017-12-26 | 2018-04-29 | 2018-04-29 | COMP | 2018-07-27 | COMP | 2019-04-02 | COMP | 2019-04-16 | COMP | 2019-05-07 | COMP | Rule 16 | 50 | 86 | 63 | 170 | 11 | 16 | 392
3039 | 2017-10-12 | 2018-03-02 | 2018-08-11 | 2018-08-11 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2018-12-04 | COMP | 2019-02-25 | COMP | Rule 16 | 95 | 114 | 65 | 1 | 14 | 56 | 341
3059 | 2017-10-12 | 2018-03-06 | 2018-08-16 | 2018-08-14 | COMP | 2019-04-10 | NOTN | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-09-02 | COMP | Rule 16 | 97 | 116 |  | 164 | 1 | 101 | 473
4555 | 2017-10-12 | 2018-01-29 | 2018-03-29 | 2018-03-29 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-02-13 | COMP | 2019-06-13 | COMP | Rule 16 | 72 | 43 | 169 | 1 | 53 | 85 | 418
4619 | 2017-10-12 | 2018-02-16 | 2018-04-20 | 2018-04-20 | COMP | 2018-06-05 | COMP | 2018-07-10 | COMP | 2019-02-22 | COMP | 2019-05-14 | COMP | Rule 15/16 | 86 | 45 | 32 | 25 | 156 | 58 | 397
4627 | 2017-10-12 | 2018-02-20 | 2018-04-20 | 2018-04-20 | COMP | 2018-07-05 | COMP | 2018-07-05 | COMP | 2019-11-16 | COMP | 2020-01-10 | COMP | Rule 15/16 | 87 | 44 | 53 | 1 | 345 | 36 | 562
4643 | 2017-10-12 | 2018-02-26 | 2018-03-28 | 2018-06-14 | COMP | 2018-08-09 | COMP | 2018-12-05 | COMP | 2018-12-03 | COMP | 2019-01-10 | COMP | Rule 15/16 | 91 | 23 | 40 | 81 | 0 | 25 | 311
4754 | 2017-10-12 | 2018-03-26 | 2018-08-27 | 2018-08-27 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2020-02-11 | COMP | 2020-03-04 | COMP | Rule 15/16 | 111 | 109 | 108 | 1 | 258 | 16 | 598
4971 | 2017-10-12 | 2018-04-18 | 2020-03-25 | 2020-03-27 | COMP | 2020-10-06 | COMP | 2020-10-09 | COMP | 2020-10-28 | COMP | 2020-12-08 | COMP | Rule 16 | 128 | 486 | 136 | 4 | 14 | 27 | 792
5533 | 2017-10-12 | 2018-06-11 | 2018-08-21 | 2018-08-21 | COMP | 2018-09-24 | COMP | 2018-09-24 | COMP | 2019-07-12 | COMP | 2019-10-08 | COMP | Rule 16 | 165 | 51 | 24 | 1 | 201 | 62 | 499
10128 | 2017-10-12 | 2019-03-04 | 2019-03-20 | 2020-10-15 | COMP | 2021-02-17 | COMP | 2021-02-24 | COMP |  | INPR | 2021-09-21 | COMP | Rule 16 | 346 | 13 | 83 | 6 |  |  | 990
10143 | 2017-10-12 | 2019-03-04 | 2019-05-17 | 2019-05-17 | COMP | 2020-12-11 | COMP | 2020-12-11 | COMP | 2021-01-15 | COMP | 2021-02-23 | COMP | Rule 16 | 346 | 55 | 396 | 1 | 24 | 26 | 843
10734 | 2017-10-12 | 2019-03-28 | 2019-05-24 | 2019-05-24 | COMP | 2021-08-05 | COMP | 2022-04-04 | COMP |  | INPR | 2023-12-10 | COMP | Rule 16 | 364 | 42 | 554 | 167 |  |  | 1545
2349 | 2017-10-13 | 2017-11-08 | 2018-01-11 | 2018-01-11 | COMP | 2018-01-19 | COMP | 2018-01-19 | COMP | 2018-01-19 | COMP | 2022-04-08 | COMP | Rule 16 | 19 | 42 | 6 | 1 | 1 | 1063 | 1127
2563 | 2017-10-13 | 2017-12-27 | 2018-05-25 | 2018-07-09 | COMP | 2019-10-22 | COMP | 2020-08-25 | COMP | 2020-09-22 | COMP | 2020-11-24 | COMP | Rule 15/16 | 50 | 105 | 326 | 213 | 20 | 45 | 783
2766 | 2017-10-13 | 2018-01-29 | 2018-02-22 | 2018-02-22 | COMP | 2018-03-10 | COMP | 2018-03-15 | COMP | 2018-03-15 | COMP | 2019-04-22 | COMP | Rule 16 | 71 | 18 | 12 | 4 | 1 | 278 | 380
5473 | 2017-10-13 | 2018-06-01 | 2019-05-07 | 2019-05-07 | COMP | 2019-05-22 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-06-22 | COMP | Rule 15/16 | 158 | 234 | 12 | 2 | 1 | 21 | 423
5724 | 2017-10-13 | 2018-06-27 | 2018-09-20 | 2018-09-20 | COMP | 2018-12-19 | COMP | 2018-12-21 | COMP | 2019-04-30 | COMP | 2019-03-29 | COMP | Rule 16 | 176 | 60 | 62 | 3 | 89 |  | 364
5860 | 2017-10-13 | 2018-07-09 | 2018-11-21 | 2018-11-21 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-11-19 | COMP | 2020-11-30 | COMP | Other | 183 | 96 | 156 | 1 | 348 | 6 | 785
6019 | 2017-10-13 | 2018-07-19 | 2018-11-16 | 2018-11-16 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-12-08 | COMP | 2021-01-05 | COMP | Rule 15 | 191 | 85 | 159 | 1 | 359 | 19 | 809
6035 | 2017-10-13 | 2018-07-19 | 2019-07-16 | 2019-07-27 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2020-10-06 | COMP | 2020-12-09 | COMP | Rule 15/16 | 191 | 249 | 64 | 1 | 239 | 44 | 792
6746 | 2017-10-13 | 2018-09-11 | 2019-01-02 | 2019-01-02 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP |  | INPR | 2020-11-24 | COMP | Other | 228 | 77 | 130 | 1 |  |  | 783
6754 | 2017-10-13 | 2018-09-11 | 2019-01-03 | 2019-01-03 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-11-19 | COMP | 2020-11-30 | COMP | Other | 228 | 78 | 129 | 1 | 348 | 6 | 785
12981 | 2017-10-13 | 2019-07-03 | 2020-01-15 | 2020-01-15 | COMP | 2020-04-22 | COMP | 2020-04-27 | COMP | 2020-05-04 | COMP | 2020-06-30 | COMP | Rule 16 | 431 | 134 | 69 | 4 | 6 | 41 | 680
26884 | 2017-10-13 | 2021-04-07 | 2022-05-05 | 2022-05-05 | COMP | 2022-05-25 | COMP | 2022-08-19 | COMP | 2022-12-20 | COMP | 2023-04-10 | COMP | Rule 15/16 | 873 | 274 | 15 | 60 | 84 | 76 | 1377
2239 | 2017-10-16 | 2017-10-19 | 2017-10-21 | 2017-10-21 | COMP | 2019-06-06 | COMP | 2019-10-09 | COMP | 2023-02-25 | INPR | 2019-11-04 | COMP | Rule 16 | 4 | 2 | 406 | 88 |  |  | 516
2536 | 2017-10-16 | 2017-12-18 | 2018-02-13 | 2018-02-13 | COMP | 2018-05-03 | COMP | 2019-06-13 | COMP | 2019-11-01 | COMP | 2020-01-26 | COMP | Rule 15/16 | 43 | 39 | 57 | 280 | 100 | 55 | 569
2679 | 2017-10-16 | 2018-01-17 | 2018-07-11 | 2018-07-11 | COMP | 2018-10-19 | COMP | 2018-12-30 | COMP | 2018-12-30 | COMP | 2019-02-21 | COMP | Rule 16 | 62 | 123 | 72 | 47 | 0 | 36 | 337
2828 | 2017-10-16 | 2018-02-06 | 2019-05-17 | 2019-05-17 | COMP | 2019-09-09 | COMP | 2019-10-08 | COMP | 2019-10-29 | COMP | 2020-02-05 | COMP | Rule 16 | 76 | 323 | 79 | 22 | 16 | 66 | 577
2829 | 2017-10-16 | 2018-02-06 | 2019-05-15 | 2019-05-15 | COMP | 2019-07-24 | COMP | 2019-08-26 | COMP | 2019-12-16 | COMP | 2019-10-10 | COMP | Rule 16 | 76 | 321 | 49 | 24 | 77 |  | 499
2830 | 2017-10-16 | 2018-02-06 | 2019-05-17 | 2019-05-17 | COMP | 2019-10-03 | COMP | 2019-10-01 | COMP | 2020-05-30 | INPR | 2019-12-11 | COMP | Rule 16 | 76 | 323 | 97 |  |  |  | 540
2831 | 2017-10-16 | 2018-02-06 | 2018-10-08 | 2018-10-08 | COMP | 2019-03-29 | COMP | 2019-07-31 | COMP | 2020-02-29 | INPR | 2019-08-20 | COMP | Rule 16 | 76 | 171 | 118 | 87 |  |  | 463
2832 | 2017-10-16 | 2018-02-06 | 2019-05-17 | 2019-05-17 | COMP | 2019-08-28 | COMP | 2019-10-09 | COMP | 2020-04-03 | COMP | 2019-12-11 | COMP | Rule 16 | 76 | 323 | 72 | 30 | 121 |  | 540
3064 | 2017-10-16 | 2018-03-07 | 2018-06-01 | 2018-06-01 | COMP | 2018-10-01 | COMP | 2018-12-05 | COMP | 2018-11-15 | COMP | 2019-01-24 | COMP | Rule 16 | 96 | 62 | 85 | 45 | 0 | 34 | 318
3402 | 2017-10-16 | 2018-04-19 | 2018-09-12 | 2018-09-12 | COMP | 2018-11-01 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2020-02-06 | COMP | Rule 15/16 | 127 | 102 | 37 | 254 | 1 | 62 | 578
5296 | 2017-10-16 | 2018-05-18 | 2018-11-28 | 2018-12-18 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-02-01 | COMP | Rule 16 | 148 | 133 | 4 | 1 | 1 | 28 | 324
5383 | 2017-10-16 | 2018-05-25 | 2018-10-24 | 2018-10-24 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-04-03 | COMP | 2019-05-06 | COMP | Rule 16 | 153 | 106 | 71 | 1 | 39 | 24 | 389
10386 | 2017-10-16 | 2019-03-14 | 2019-05-03 | 2019-05-03 | COMP | 2019-07-26 | COMP | 2019-09-16 | COMP | 2019-09-09 | COMP | 2019-10-07 | COMP | Rule 15/16 | 352 | 37 | 59 | 36 | 0 | 16 | 496
2315 | 2017-10-17 | 2017-11-02 | 2018-02-22 | 2018-02-22 | COMP | 2018-05-11 | COMP | 2018-06-25 | COMP | 2019-05-17 | COMP | 2019-10-01 | COMP | Rule 16 | 13 | 74 | 57 | 31 | 226 | 95 | 491
2320 | 2017-10-17 | 2017-11-03 | 2017-11-11 | 2017-11-11 | COMP | 2018-04-27 | COMP | 2018-05-02 | COMP | 2017-11-06 | COMP | 2022-01-28 | COMP | Rule 16 | 14 | 5 | 114 | 4 | 0 | 942 | 1076
2430 | 2017-10-17 | 2017-11-28 | 2019-09-13 | 2019-09-13 | COMP | 2019-09-14 | NOTN | 2020-08-25 | COMP | 2020-09-01 | COMP | 2020-09-23 | COMP | Other | 28 | 452 |  | 240 | 6 | 16 | 738
2460 | 2017-10-17 | 2017-12-05 | 2018-04-17 | 2018-04-17 | COMP | 2018-11-06 | COMP | 2019-04-19 | COMP | 2019-09-21 | INPR | 2019-05-24 | COMP | Rule 15/16 | 33 | 92 | 143 | 112 |  |  | 402
2479 | 2017-10-17 | 2017-12-07 | 2019-01-30 | 2019-01-30 | COMP | 2019-04-15 | COMP | 2019-09-04 | COMP | 2019-10-16 | COMP | 2019-10-15 | COMP | Rule 15/16 | 35 | 287 | 53 | 100 | 31 |  | 501
2603 | 2017-10-17 | 2018-01-05 | 2018-04-12 | 2018-04-12 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2021-01-05 | COMP | 2021-05-20 | COMP | Rule 16 | 54 | 68 | 310 | 1 | 378 | 96 | 902
2858 | 2017-10-17 | 2018-02-08 | 2018-07-20 | 2018-07-20 | COMP | 2018-10-01 | COMP | 2018-12-04 | COMP | 2020-05-30 | INPR | 2019-02-05 | COMP | Rule 15/16 | 77 | 114 | 51 | 44 |  |  | 325
2867 | 2017-10-17 | 2018-02-08 | 2018-02-15 | 2018-02-15 | COMP | 2018-03-15 | COMP | 2018-03-15 | COMP | 2022-07-16 | INPR | 2021-01-16 | COMP | Rule 16 | 77 | 6 | 20 | 1 |  |  | 815
2868 | 2017-10-17 | 2018-02-08 | 2018-03-08 | 2018-03-08 | COMP | 2018-04-24 | COMP | 2018-04-24 | COMP | 2022-07-16 | INPR | 2021-01-16 | COMP | Rule 16 | 77 | 20 | 34 | 1 |  |  | 815
2869 | 2017-10-17 | 2018-02-08 | 2018-03-08 | 2018-03-08 | COMP | 2018-04-24 | COMP | 2018-04-24 | COMP | 2023-04-15 | INPR | 2022-03-31 | COMP | Rule 16 | 77 | 20 | 34 | 1 |  |  | 1119
2870 | 2017-10-17 | 2018-02-08 | 2018-03-08 | 2018-03-08 | COMP | 2018-04-24 | COMP | 2018-04-24 | COMP | 2018-07-26 | COMP | 2022-03-31 | COMP | Rule 16 | 77 | 20 | 34 | 1 | 66 | 926 | 1119
2915 | 2017-10-17 | 2018-02-15 | 2018-05-09 | 2018-05-09 | COMP | 2020-05-18 | COMP | 2020-07-21 | COMP | 2020-07-22 | COMP | 2020-10-30 | COMP | Rule 15/16 | 82 | 59 | 509 | 46 | 2 | 72 | 765
3062 | 2017-10-17 | 2018-03-07 | 2018-06-01 | 2018-06-01 | COMP | 2018-09-18 | COMP | 2018-09-27 | COMP | 2019-09-13 | COMP | 2019-12-14 | COMP | Rule 16 | 95 | 62 | 76 | 8 | 242 | 63 | 541
3063 | 2017-10-17 | 2018-03-07 | 2018-07-03 | 2018-07-03 | COMP | 2019-07-24 | COMP | 2020-02-20 | COMP | 2020-01-07 | COMP | 2020-04-09 | COMP | Rule 15/16 | 95 | 84 | 266 | 144 | 0 | 36 | 621
3065 | 2017-10-17 | 2018-03-07 | 2018-05-11 | 2019-02-13 | COMP | 2019-06-06 | COMP | 2019-06-12 | COMP | 2019-06-18 | COMP | 2019-07-17 | COMP | Rule 15/16 | 95 | 48 | 80 | 5 | 5 | 21 | 438
4411 | 2017-10-17 | 2017-11-27 | 2018-01-24 | 2023-05-27 | CANC | 2023-05-27 | CANC | 2018-07-25 | COMP | 2023-05-27 | INPR | 2022-05-10 | COMP | Unknown | 27 | [5 empty] | 1147
4473 | 2017-10-17 | 2017-12-29 | 2018-05-04 | 2019-03-05 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-03-15 | COMP | 2019-06-10 | COMP | Rule 15/16 | 50 | 88 | 21 | 1 | 0 | 49 | 412
4552 | 2017-10-17 | 2018-01-31 | 2018-09-27 | 2018-09-27 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-25 | COMP | 2019-04-12 | COMP | Rule 16 | 71 | 168 | 107 | 1 | 15 | 15 | 372
5120 | 2017-10-17 | 2018-05-02 | 2019-10-03 | 2019-10-03 | COMP | 2019-11-20 | COMP | 2020-01-16 | COMP | 2020-05-29 | COMP | 2020-07-06 | COMP | Rule 15/16 | 135 | 359 | 34 | 38 | 94 | 27 | 682
5250 | 2017-10-17 | 2018-05-15 | 2018-09-01 | 2018-09-01 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-11-12 | COMP | 2019-12-26 | COMP | Rule 16 | 144 | 77 | 79 | 1 | 222 | 30 | 549
2258 | 2017-10-18 | 2017-10-25 | 2017-12-11 | 2017-12-11 | COMP | 2017-12-14 | COMP | 2017-12-14 | COMP | 2019-02-01 | COMP | 2019-05-30 | COMP | Rule 16 | 6 | 31 | 4 | 1 | 284 | 83 | 404
2323 | 2017-10-18 | 2017-11-03 | 2017-11-21 | 2017-11-21 | COMP | 2019-12-11 | COMP | 2020-08-10 | COMP | 2020-08-10 | COMP | 2020-10-07 | COMP | Rule 16 | 13 | 12 | 515 | 169 | 1 | 42 | 747
2324 | 2017-10-18 | 2017-11-03 | 2018-02-27 | 2018-06-08 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-08-11 | COMP | 2020-09-02 | COMP | Rule 16 | 13 | 76 | 379 | 1 | 170 | 17 | 723
2342 | 2017-10-18 | 2017-11-07 | 2018-01-02 | 2018-01-02 | COMP | 2019-12-11 | COMP | 2020-01-29 | COMP | 2020-08-26 | COMP | 2020-10-26 | COMP | Rule 16 | 15 | 36 | 489 | 33 | 149 | 43 | 760
2344 | 2017-10-18 | 2017-11-07 | 2018-04-26 | 2018-04-26 | COMP | 2018-05-30 | COMP | 2018-06-23 | COMP | 2019-09-21 | INPR | 2019-06-14 | COMP | Rule 15/16 | 15 | 116 | 24 | 18 |  |  | 415
2380 | 2017-10-18 | 2017-11-14 | 2018-01-16 | 2018-01-16 | COMP |  |  |  |  | 2018-01-17 | COMP | 2020-04-17 | COMP | Other | 19 | 41 |  |  |  |  | 626
2399 | 2017-10-18 | 2017-11-17 | 2018-06-07 | 2018-06-07 | COMP | 2019-07-24 | COMP | 2019-08-15 | COMP | 2020-01-19 | INPR | 2019-10-03 | COMP | Rule 15/16 | 22 | 138 | 284 | 17 |  |  | 492
2535 | 2017-10-18 | 2017-12-18 | 2018-01-22 | 2018-01-22 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-08-18 | COMP | 2020-09-24 | COMP | Rule 16 | 41 | 23 | 476 | 1 | 175 | 27 | 738
2956 | 2017-10-18 | 2018-02-22 | 2018-03-23 | 2018-03-23 | COMP | 2019-12-11 | COMP | 2020-08-06 | COMP | 2020-11-18 | COMP | 2020-12-05 | COMP | Rule 15 | 85 | 22 | 433 | 167 | 73 | 11 | 786
4374 | 2017-10-18 | 2017-11-02 | 2018-02-05 | 2018-08-01 | COMP | 2019-01-08 | COMP | 2019-02-20 | COMP | 2019-10-19 | INPR | 2019-05-14 | COMP | Rule 16 | 12 | 62 | 109 | 30 |  |  | 393
4398 | 2017-10-18 | 2017-11-14 | 2018-04-04 | 2018-04-04 | COMP | 2018-09-10 | COMP | 2018-08-01 | COMP | 2020-01-11 | COMP | 2020-01-31 | COMP | Rule 15/16 | 19 | 96 | 111 |  | 362 | 14 | 572
4488 | 2017-10-18 | 2018-01-05 | 2018-06-05 | 2018-06-05 | COMP | 2018-06-13 | COMP | 2018-07-23 | COMP | 2019-05-22 | COMP | 2019-06-11 | COMP | Rule 16 | 53 | 105 | 7 | 28 | 210 | 14 | 412
4494 | 2017-10-18 | 2018-01-09 | 2018-04-07 | 2018-04-07 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2021-02-03 | COMP | 2021-03-10 | COMP | Rule 16 | 55 | 62 | 327 | 1 | 384 | 25 | 850
4748 | 2017-10-18 | 2018-03-26 | 2018-06-14 | 2018-10-10 | COMP | 2018-11-07 | COMP | 2018-11-01 | COMP | 2019-02-12 | COMP | 2019-02-08 | COMP | Rule 16 | 107 | 58 | 21 |  | 68 |  | 327
5224 | 2017-10-18 | 2018-05-12 | 2018-06-20 | 2018-06-20 | COMP | 2018-08-24 | COMP | 2018-08-24 | COMP | 2022-07-16 | INPR | 2021-03-13 | COMP | Rule 16 | 141 | 27 | 47 | 1 |  |  | 852
5585 | 2017-10-18 | 2018-06-15 | 2018-12-04 | 2018-12-04 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-04-25 | COMP | 2019-05-30 | COMP | Rule 16 | 165 | 118 | 62 | 1 | 38 | 25 | 404
5586 | 2017-10-18 | 2018-06-15 | 2018-10-22 | 2018-10-22 | COMP | 2018-12-07 | COMP | 2018-12-19 | COMP | 2019-04-25 | COMP | 2019-05-29 | COMP | Rule 16 | 165 | 90 | 32 | 9 | 88 | 24 | 403
5670 | 2017-10-18 | 2018-06-25 | 2018-10-27 | 2018-10-27 | COMP | 2019-03-07 | NOTN | 2019-03-07 | COMP | 2019-10-29 | COMP | 2019-11-26 | COMP | Other | 171 | 88 |  | 87 | 166 | 20 | 529
8101 | 2017-10-18 | 2018-11-15 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-23 | COMP | 2019-06-20 | INPR | 2019-10-21 | REQD | 2019-06-27 | COMP | Rule 16 | 271 | 86 | 23 |  |  |  | 424
13236 | 2017-10-18 | 2019-07-17 | 2019-07-23 | 2019-07-23 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-09-25 | COMP | Rule 15/16 | 437 | 5 | 3 | 1 | 1 | 44 | 486
19269 | 2017-10-18 | 2020-04-28 | 2020-05-14 | 2020-12-04 | COMP | 2021-02-03 | COMP | 2021-02-18 | COMP | 2021-03-09 | COMP | 2021-03-13 | COMP | Rule 16 | 633 | 13 | 41 | 11 | 14 | 4 | 852
2350 | 2017-10-19 | 2017-11-08 | 2017-12-19 | 2017-12-19 | COMP | 2017-12-26 | COMP | 2017-12-29 | COMP | 2018-09-17 | COMP | 2020-12-05 | COMP | Rule 16 | 15 | 27 | 5 | 4 | 181 | 558 | 785
2396 | 2017-10-19 | 2017-11-16 | 2017-11-17 | 2017-11-17 | COMP | 2017-12-13 | COMP | 2017-12-13 | COMP | 2022-08-21 | INPR | 2021-08-02 | COMP | Rule 16 | 20 | 2 | 17 | 1 |  |  | 950
2465 | 2017-10-19 | 2017-12-06 | 2018-09-14 | 2018-09-14 | COMP | 2018-11-13 | COMP | 2019-01-31 | COMP | 2018-12-12 | COMP | 2019-04-11 | COMP | Rule 16 | 32 | 196 | 42 | 53 | 0 | 50 | 369
2468 | 2017-10-19 | 2017-12-06 | 2018-07-11 | 2018-07-11 | COMP | 2018-08-09 | COMP | 2018-10-05 | COMP | 2021-02-28 | INPR | 2019-01-23 | COMP | Rule 15/16 | 32 | 150 | 22 | 41 |  |  | 314
2842 | 2017-10-19 | 2018-02-06 | 2018-02-12 | 2018-02-12 | COMP | 2018-03-19 | COMP | 2018-03-23 | COMP | 2023-02-25 | INPR | 2021-04-25 | COMP | Rule 15/16 | 73 | 5 | 25 | 5 |  |  | 881
4477 | 2017-10-19 | 2018-01-05 | 2018-02-25 | 2019-08-12 | COMP | 2019-10-02 | COMP | 2019-01-14 | COMP | 2019-05-22 | COMP | 2020-03-23 | COMP | Rule 16 | 52 | 34 | 37 |  | 91 | 209 | 606
4759 | 2017-10-19 | 2018-03-27 | 2018-06-02 | 2018-06-02 | COMP | 2019-03-25 | COMP | 2019-06-21 | COMP | 2020-01-19 | INPR | 2019-09-23 | COMP | Rule 16 | 107 | 48 | 202 | 64 |  |  | 483
4929 | 2017-10-19 | 2018-04-12 | 2018-11-28 | 2018-12-19 | COMP | 2019-01-30 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-06-14 | COMP | Rule 15/16 | 119 | 159 | 28 | 68 | 1 | 29 | 414
5030 | 2017-10-19 | 2018-04-24 | 2018-11-30 | 2018-11-30 | COMP | 2019-04-17 | COMP | 2020-06-25 | COMP | 2020-06-02 | COMP | 2020-07-13 | COMP | Rule 16 | 127 | 153 | 95 | 301 | 0 | 13 | 685
5635 | 2017-10-19 | 2018-06-22 | 2019-01-17 | 2019-01-17 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2020-05-04 | COMP | 2020-06-02 | COMP | Rule 15/16 | 169 | 143 | 66 | 1 | 261 | 21 | 656
6123 | 2017-10-19 | 2018-07-27 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-28 | COMP | 2019-12-17 | COMP | 2020-04-06 | COMP | 2020-06-03 | COMP | Rule 15/16 | 193 | 239 | 36 | 76 | 76 | 42 | 657
7702 | 2017-10-19 | 2018-10-26 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-29 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-06-25 | COMP | Rule 16 | 257 | 114 | 12 | 3 | 1 | 39 | 421
12817 | 2017-10-19 | 2019-06-26 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-27 | COMP | 2020-04-02 | COMP | 2020-04-21 | COMP | 2020-07-16 | COMP | Rule 15/16 | 422 | 158 | 32 | 5 | 14 | 62 | 688
2357 | 2017-10-20 | 2017-11-09 | 2018-10-10 | 2018-10-10 | COMP | 2019-01-28 | COMP | 2019-03-18 | COMP | 2023-11-11 | INPR | 2021-08-31 | COMP | Other | 15 | 230 | 73 | 35 |  |  | 970
2375 | 2017-10-20 | 2017-11-14 | 2018-06-18 | 2018-08-02 | COMP | 2019-02-05 | COMP | 2019-04-17 | COMP | 2019-04-29 | COMP | 2019-06-08 | COMP | Rule 15/16 | 17 | 148 | 127 | 51 | 9 | 29 | 408
2471 | 2017-10-20 | 2017-12-06 | 2018-07-11 | 2019-04-20 | REQD | 2018-09-06 | COMP | 2018-10-05 | COMP | 2019-04-20 | INPR | 2019-01-27 | COMP | Rule 15/16 | 31 | [5 empty] | 315
2472 | 2017-10-20 | 2017-12-06 | 2018-08-22 | 2018-08-22 | COMP | 2018-09-06 | COMP | 2018-10-05 | COMP | 2019-01-16 | COMP | 2019-01-27 | COMP | Rule 15/16 | 31 | 180 | 11 | 22 | 69 | 7 | 315
2607 | 2017-10-20 | 2018-01-05 | 2018-05-10 | 2018-05-10 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2019-06-28 | COMP | 2019-07-25 | COMP | Rule 15/16 | 51 | 88 | 117 | 1 | 170 | 19 | 441
2803 | 2017-10-20 | 2018-02-01 | 2018-07-19 | 2018-07-19 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-02-12 | COMP | 2019-03-04 | COMP | Rule 16 | 69 | 118 | 91 | 1 | 52 | 14 | 340
2804 | 2017-10-20 | 2018-02-01 | 2018-10-12 | 2018-10-12 | COMP | 2019-01-02 | COMP | 2019-01-08 | COMP | 2020-11-21 | INPR | 2019-06-06 | COMP | Rule 16 | 69 | 178 | 54 | 5 |  |  | 407
2889 | 2017-10-20 | 2018-02-12 | 2018-04-17 | 2018-04-17 | COMP | 2018-04-25 | COMP | 2018-11-26 | COMP | 2018-12-13 | COMP | 2019-01-22 | COMP | Rule 16 | 76 | 46 | 7 | 148 | 14 | 26 | 312
3240 | 2017-10-20 | 2018-03-27 | 2018-10-02 | 2018-10-02 | COMP | 2019-01-23 | COMP | 2020-01-30 | COMP | 2020-07-01 | COMP | 2020-07-29 | COMP | Rule 15/16 | 106 | 133 | 76 | 257 | 108 | 21 | 696
3404 | 2017-10-20 | 2018-04-18 | 2018-05-10 | 2018-05-10 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-10-19 | INPR | 2019-02-11 | COMP | Rule 16 | 122 | 17 | 145 | 1 |  |  | 326
3464 | 2017-10-20 | 2018-05-01 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-24 | COMP | 2019-10-09 | COMP | 2019-11-10 | COMP | 2019-12-05 | COMP | Rule 15/16 | 131 | 154 | 31 | 181 | 23 | 16 | 532
4863 | 2017-10-20 | 2018-04-06 | 2018-10-27 | 2018-10-27 | COMP | 2018-12-06 | COMP | 2019-08-21 | COMP | 2020-02-25 | COMP | 2019-11-12 | COMP | Rule 16 | 114 | 143 | 26 | 179 | 127 |  | 517
5717 | 2017-10-20 | 2018-06-26 | 2019-01-03 | 2019-01-03 | COMP | 2019-02-07 | COMP | 2019-08-14 | COMP | 2019-08-19 | COMP | 2019-09-25 | COMP | Rule 15/16 | 170 | 131 | 25 | 132 | 4 | 27 | 484
2298 | 2017-10-21 | 2017-10-30 | 2018-06-10 | 2019-01-02 | COMP | 2019-12-16 | COMP | 2020-01-17 | COMP | 2021-11-12 | COMP | 2022-02-01 | COMP | Rule 15/16 | 6 | 152 | 241 | 23 | 461 | 55 | 1074
2299 | 2017-10-21 | 2017-10-30 | 2018-06-04 | 2019-03-07 | COMP | 2019-12-16 | COMP | 2020-01-17 | COMP | 2020-11-10 | COMP | 2021-03-09 | COMP | Rule 15/16 | 6 | 148 | 197 | 23 | 209 | 79 | 846
2691 | 2017-10-21 | 2018-01-18 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-07 | COMP | 2019-04-26 | COMP | 2019-11-23 | INPR | 2019-07-24 | COMP | Rule 16 | 58 | 236 | 9 | 78 |  |  | 439
4551 | 2017-10-21 | 2018-01-31 | 2018-03-14 | 2018-04-22 | COMP | 2018-05-10 | COMP | 2018-05-10 | COMP | 2019-05-28 | COMP | 2019-07-09 | COMP | Rule 16 | 67 | 30 | 14 | 1 | 263 | 30 | 428
2412 | 2017-10-23 | 2017-11-20 | 2019-01-24 | 2019-01-24 | COMP | 2019-03-29 | COMP | 2019-08-19 | COMP | 2019-12-10 | COMP | 2020-02-12 | COMP | Rule 16 | 20 | 294 | 46 | 100 | 78 | 44 | 577
2445 | 2017-10-23 | 2017-12-01 | 2018-02-25 | 2018-02-25 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-10-01 | COMP | 2019-12-05 | COMP | Rule 16 | 27 | 57 | 191 | 1 | 214 | 45 | 531
2473 | 2017-10-23 | 2017-12-06 | 2018-06-28 | 2018-06-28 | COMP | 2018-07-19 | COMP | 2018-08-07 | COMP | 2018-11-14 | COMP | 2019-01-10 | COMP | Rule 15/16 | 30 | 142 | 15 | 14 | 70 | 38 | 304
2527 | 2017-10-23 | 2017-12-15 | 2018-02-26 | 2018-02-26 | COMP | 2018-11-27 | COMP | 2019-01-24 | COMP | 2019-10-01 | COMP | 2020-01-02 | COMP | Rule 16 | 37 | 48 | 191 | 40 | 175 | 63 | 549
2959 | 2017-10-23 | 2018-02-22 | 2018-04-05 | 2018-04-05 | COMP | 2018-05-08 | COMP | 2019-05-29 | COMP | 2019-11-23 | INPR | 2019-08-01 | COMP | Rule 16 | 82 | 31 | 24 | 266 |  |  | 445
3217 | 2017-10-23 | 2018-03-22 | 2018-09-05 | 2018-09-05 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2021-02-27 | INPR | 2019-07-24 | COMP | Rule 16 | 102 | 117 | 56 | 1 |  |  | 439
3994 | 2017-10-23 | 2018-11-10 | 2019-05-21 | 2020-03-18 | COMP | 2020-03-16 | COMP | 2020-03-18 | COMP | 2020-04-09 | COMP | 2020-09-19 | COMP | Other | 265 | 130 |  | 3 | 17 | 115 | 731
4375 | 2017-10-23 | 2017-11-01 | 2018-01-03 | 2018-01-03 | COMP | 2018-03-05 | COMP | 2018-05-02 | COMP | 2019-01-25 | COMP | 2019-05-08 | COMP | Rule 16 | 8 | 41 | 42 | 43 | 184 | 73 | 386
4383 | 2017-10-23 | 2017-11-08 | 2018-06-21 | 2018-06-21 | COMP | 2018-07-02 | COMP | 2018-07-02 | COMP | 2018-12-17 | COMP | 2019-01-14 | COMP | Rule 16 | 13 | 154 | 8 | 1 | 116 | 19 | 306
4425 | 2017-10-23 | 2017-12-05 | 2018-03-22 | 2018-03-22 | COMP | 2018-07-06 | COMP | 2018-07-06 | COMP | 2020-04-02 | COMP | 2020-06-11 | COMP | Rule 16 | 29 | 74 | 75 | 1 | 437 | 50 | 661
4548 | 2017-10-23 | 2018-01-26 | 2018-08-29 | 2019-07-08 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2020-02-13 | COMP | 2020-03-31 | COMP | Rule 16 | 64 | 151 | 18 | 1 | 135 | 33 | 610
5405 | 2017-10-23 | 2018-05-29 | 2018-10-12 | 2018-10-12 | COMP | 2019-03-21 | COMP | 2019-04-17 | COMP | 2019-03-21 | COMP | 2019-06-11 | COMP | Rule 16 | 149 | 97 | 108 | 20 | 0 | 39 | 409
5596 | 2017-10-23 | 2018-06-18 | 2018-07-27 | 2018-07-27 | COMP | 2018-08-22 | COMP | 2018-08-22 | COMP | 2019-10-11 | COMP | 2019-11-04 | COMP | Rule 16 | 163 | 29 | 19 | 1 | 287 | 17 | 511
6502 | 2017-10-23 | 2018-08-22 | 2019-01-24 | 2019-09-15 | COMP | 2019-11-13 | COMP | 2021-10-08 | COMP | 2019-10-02 | COMP | 2022-07-26 | COMP | Rule 16 | 209 | 105 | 42 | 480 | 0 | 200 | 1195
6765 | 2017-10-23 | 2018-09-11 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-13 | COMP | 2019-10-18 | COMP | 2019-10-02 | COMP | 2023-01-20 | COMP | Rule 15/16 | 222 | 71 | 36 | 174 | 0 | 817 | 1316
2414 | 2017-10-24 | 2017-11-21 | 2018-03-05 | 2018-03-05 | COMP | 2018-03-27 | COMP | 2018-08-07 | COMP | 2018-12-05 | COMP | 2019-03-16 | COMP | Rule 16 | 20 | 69 | 17 | 94 | 83 | 69 | 347
2522 | 2017-10-24 | 2017-12-14 | 2018-04-09 | 2018-04-09 | COMP | 2019-03-19 | COMP | 2019-03-25 | COMP | 2019-06-14 | COMP | 2019-07-21 | COMP | Rule 15/16 | 35 | 79 | 237 | 5 | 59 | 25 | 435
2871 | 2017-10-24 | 2018-02-08 | 2018-04-13 | 2018-04-13 | COMP | 2018-07-05 | COMP | 2018-07-05 | COMP | 2019-06-22 | COMP | 2019-07-18 | COMP | Rule 16 | 72 | 46 | 58 | 1 | 243 | 18 | 434
2872 | 2017-10-24 | 2018-02-08 | 2018-04-13 | 2018-04-13 | COMP | 2018-05-04 | COMP | 2018-05-04 | COMP | 2018-08-15 | COMP | 2022-03-31 | COMP | Rule 16 | 72 | 46 | 16 | 1 | 72 | 912 | 1114
2935 | 2017-10-24 | 2018-02-18 | 2018-04-26 | 2018-04-26 | COMP | 2018-12-13 | COMP | 2018-12-19 | COMP | 2019-01-14 | COMP | 2019-01-22 | COMP | Rule 16 | 78 | 48 | 160 | 5 | 17 | 6 | 310
3247 | 2017-10-24 | 2018-03-28 | 2018-11-01 | 2018-11-01 | COMP | 2019-03-05 | COMP | 2019-03-13 | COMP | 2019-07-16 | COMP | 2019-07-09 | COMP | Rule 15/16 | 105 | 154 | 82 | 7 | 88 |  | 427
3414 | 2017-10-24 | 2018-04-24 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-17 | COMP | 2019-11-26 | COMP | 2020-01-07 | COMP | 2020-03-06 | COMP | Rule 15/16 | 124 | 300 | 11 | 93 | 27 | 42 | 592
3967 | 2017-10-24 | 2018-10-30 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-02 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-09-09 | COMP | Rule 16 | 256 | 150 | 19 | 17 | 1 | 32 | 470
5064 | 2017-10-24 | 2018-04-27 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2020-06-03 | COMP | 2020-08-20 | COMP | Rule 16 | 127 | 118 | 45 | 1 | 367 | 57 | 710
7342 | 2017-10-24 | 2018-10-08 | 2018-11-08 | 2018-11-08 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-01-29 | COMP | Rule 16 | 240 | 24 | 37 | 1 | 1 | 17 | 315
2474 | 2017-10-25 | 2017-12-06 | 2018-09-21 | 2018-09-21 | COMP | 2018-12-17 | COMP | 2019-01-12 | COMP | 2020-01-03 | COMP | 2020-02-06 | COMP | Rule 15/16 | 28 | 201 | 59 | 18 | 245 | 24 | 571
2475 | 2017-10-25 | 2017-12-06 | 2019-03-03 | 2019-03-03 | COMP | 2020-09-25 | COMP | 2020-10-22 | COMP | 2021-02-11 | COMP | 2021-03-04 | COMP | Rule 15/16 | 28 | 309 | 398 | 20 | 75 | 15 | 841
2476 | 2017-10-25 | 2017-12-06 | 2019-11-22 | 2019-11-22 | COMP | 2020-12-21 | COMP | 2021-02-03 | COMP | 2021-08-13 | COMP | 2021-11-02 | COMP | Rule 15/16 | 28 | 495 | 271 | 30 | 135 | 57 | 1011
2530 | 2017-10-25 | 2017-12-16 | 2018-04-09 | 2018-04-09 | COMP | 2018-07-10 | COMP | 2018-08-03 | COMP | 2019-06-06 | COMP | 2019-07-08 | COMP | Rule 15/16 | 35 | 77 | 65 | 19 | 211 | 22 | 425
2531 | 2017-10-25 | 2017-12-16 | 2018-03-22 | 2018-03-22 | COMP | 2018-05-14 | COMP | 2018-07-26 | COMP | 2019-04-22 | COMP | 2019-06-26 | COMP | Rule 15/16 | 35 | 65 | 38 | 52 | 185 | 47 | 418
2668 | 2017-10-25 | 2018-01-17 | 2018-01-29 | 2018-01-29 | COMP | 2018-04-30 | COMP | 2018-05-03 | COMP | 2019-05-31 | COMP | 2019-12-16 | COMP | Rule 16 | 55 | 9 | 65 | 4 | 271 | 137 | 536
2798 | 2017-10-25 | 2018-02-01 | 2018-08-31 | 2018-08-31 | COMP | 2019-03-22 | COMP | 2019-07-18 | COMP | 2019-06-24 | COMP | 2019-10-16 | COMP | Rule 15/16 | 66 | 149 | 138 | 83 | 0 | 64 | 496
3798 | 2017-10-25 | 2018-07-17 | 2018-12-09 | 2018-12-09 | COMP | 2019-03-29 | COMP | 2019-05-14 | COMP | 2019-05-28 | COMP | 2019-07-24 | COMP | Rule 16 | 181 | 100 | 76 | 33 | 10 | 41 | 437
4443 | 2017-10-25 | 2017-12-11 | 2018-03-01 | 2018-03-01 | COMP | 2018-04-16 | COMP | 2019-09-06 | COMP | 2021-03-25 | COMP | 2021-04-03 | COMP | Rule 16 | 31 | 55 | 33 | 352 | 389 | 7 | 862
4542 | 2017-10-25 | 2018-01-25 | 2018-02-07 | 2019-01-08 | COMP | 2019-01-17 | COMP | 2019-02-04 | COMP | 2019-02-02 | COMP | 2019-02-08 | COMP | Rule 16 | 61 | 10 | 8 | 12 | 0 | 5 | 322
4654 | 2017-10-25 | 2018-02-27 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-14 | COMP | 2019-01-17 | COMP | 2019-04-01 | COMP | 2019-07-02 | COMP | Rule 16 | 83 | 174 | 10 | 43 | 51 | 66 | 422
4701 | 2017-10-25 | 2018-03-15 | 2018-05-11 | 2018-05-11 | COMP | 2018-06-25 | COMP | 2018-06-25 | COMP | 2023-04-30 | INPR | 2021-04-25 | COMP | Rule 16 | 95 | 42 | 31 | 1 |  |  | 877
5184 | 2017-10-25 | 2018-05-08 | 2018-09-09 | 2018-09-09 | COMP | 2019-01-30 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-09-18 | COMP | Rule 16 | 133 | 86 | 97 | 25 | 1 | 138 | 476
5649 | 2017-10-25 | 2018-06-23 | 2018-12-18 | 2018-12-18 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-11-15 | COMP | 2020-01-06 | COMP | Rule 16 | 165 | 122 | 91 | 1 | 141 | 33 | 549
5789 | 2017-10-25 | 2018-07-02 | 2019-01-14 | 2019-05-12 | COMP | 2019-09-11 | COMP | 2020-07-31 | COMP | 2020-08-18 | COMP | 2020-11-18 | COMP | Rule 15/16 | 171 | 134 | 85 | 225 | 13 | 65 | 771
6877 | 2017-10-25 | 2018-09-14 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-12 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-03 | COMP | Rule 16 | 223 | 43 | 19 | 153 | 1 | 10 | 444
15608 | 2017-10-25 | 2019-11-12 | 2020-01-04 | 2020-01-04 | COMP | 2020-02-19 | COMP | 2020-02-20 | COMP | 2020-07-20 | COMP | 2020-08-28 | COMP | Rule 15/16 | 514 | 35 | 31 | 2 | 107 | 30 | 715
2345 | 2017-10-26 | 2017-11-08 | 2018-04-18 | 2018-04-18 | COMP | 2019-04-08 | COMP | 2018-06-18 | COMP | 2019-04-18 | COMP | 2019-06-03 | COMP | Rule 16 | 10 | 109 | 244 |  | 210 | 32 | 400
2543 | 2017-10-26 | 2017-12-20 | 2018-06-02 | 2018-06-02 | COMP | 2020-02-14 | COMP | 2019-07-31 | COMP | 2019-06-24 | COMP | 2019-11-22 | COMP | Rule 15/16 | 37 | 113 | 427 |  | 0 | 81 | 521
2641 | 2017-10-26 | 2018-01-10 | 2019-01-11 | 2019-01-11 | COMP | 2019-12-04 | COMP | 2019-12-10 | COMP | 2020-10-14 | COMP | 2020-11-13 | COMP | Rule 15/16 | 50 | 253 | 226 | 5 | 216 | 22 | 767
2662 | 2017-10-26 | 2018-01-16 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-04 | COMP | 2019-03-08 | COMP | 2019-02-04 | COMP | 2019-04-19 | COMP | Rule 15/16 | 53 | 257 | 9 | 24 | 0 | 31 | 370
2815 | 2017-10-26 | 2018-02-05 | 2018-05-16 | 2018-05-16 | COMP | 2020-06-18 | COMP | 2022-01-21 | COMP | 2022-01-24 | COMP | 2022-04-28 | COMP | Rule 15/16 | 67 | 72 | 526 | 402 | 2 | 68 | 1132
2979 | 2017-10-26 | 2018-02-26 | 2018-03-22 | 2018-03-22 | COMP | 2019-03-28 | COMP | 2019-04-01 | COMP | 2019-04-07 | COMP | 2019-05-23 | COMP | Rule 16 | 81 | 19 | 256 | 3 | 5 | 34 | 394
3005 | 2017-10-26 | 2018-02-26 | 2018-06-28 | 2018-06-28 | COMP | 2018-09-07 | COMP | 2018-09-27 | COMP | 2018-09-12 | COMP | 2019-01-04 | COMP | Other | 81 | 88 | 50 | 15 | 0 | 67 | 297
3754 | 2017-10-26 | 2018-06-27 | 2018-08-21 | 2018-08-21 | COMP | 2018-10-15 | COMP | 2018-10-15 | COMP | 2021-02-27 | INPR | 2020-01-31 | COMP | Rule 16 | 167 | 39 | 39 | 1 |  |  | 566
4436 | 2017-10-26 | 2017-12-08 | 2018-05-10 | 2018-05-10 | COMP | 2018-12-13 | COMP | 2018-12-13 | COMP | 2019-02-12 | COMP | 2019-03-13 | COMP | Rule 16 | 29 | 106 | 150 | 1 | 41 | 21 | 343
4468 | 2017-10-26 | 2017-12-21 | 2018-05-23 | 2018-05-23 | COMP | 2018-06-15 | COMP | 2018-07-25 | COMP | 2020-04-26 | INPR | 2019-06-17 | COMP | Rule 16 | 38 | 106 | 17 | 28 |  |  | 410
5425 | 2017-10-26 | 2018-05-30 | 2019-10-08 | 2019-10-08 | COMP | 2019-11-14 | COMP | 2019-11-14 | COMP | 2020-04-14 | COMP | 2020-06-30 | COMP | Rule 16 | 147 | 343 | 27 | 1 | 103 | 55 | 671
8396 | 2017-10-26 | 2018-11-30 | 2019-03-25 | 2021-12-13 | COMP | 2022-03-01 | COMP | 2022-05-11 | COMP | 2022-05-13 | COMP | 2022-06-11 | COMP | Rule 16 | 274 | 78 | 55 | 52 | 3 | 20 | 1162
2364 | 2017-10-27 | 2017-11-12 | 2018-01-13 | 2018-01-13 | COMP | 2018-03-08 | COMP | 2018-03-08 | COMP | 2020-07-25 | INPR | 2019-04-29 | COMP | Rule 15/16 | 10 | 41 | 37 | 1 |  |  | 375
2455 | 2017-10-27 | 2017-12-05 | 2018-04-09 | 2018-04-09 | COMP | 2018-04-25 | COMP | 2018-11-26 | COMP | 2018-10-20 | COMP | 2019-04-23 | COMP | Rule 16 | 25 | 86 | 13 | 148 | 0 | 103 | 371
2532 | 2017-10-27 | 2017-12-16 | 2018-02-25 | 2018-02-25 | COMP | 2018-09-11 | COMP | 2018-09-27 | COMP | 2018-10-03 | COMP | 2019-01-28 | COMP | Rule 16 | 33 | 46 | 139 | 13 | 5 | 78 | 311
2823 | 2017-10-27 | 2018-02-05 | 2018-04-23 | 2018-04-23 | COMP | 2018-06-04 | COMP | 2018-12-11 | COMP | 2018-11-13 | COMP | 2019-01-10 | COMP | Rule 16 | 66 | 55 | 30 | 132 | 0 | 21 | 300
2966 | 2017-10-27 | 2018-02-23 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-02 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-05-06 | COMP | Rule 16 | 79 | 268 | 11 | 8 | 1 | 18 | 380
2995 | 2017-10-27 | 2018-02-27 | 2018-07-07 | 2018-06-05 | COMP | 2018-09-17 | COMP | 2018-09-27 | COMP | 2023-12-09 | INPR | 2019-07-17 | COMP | Rule 15/16 | 81 | 92 | 73 | 9 |  |  | 430
3084 | 2017-10-27 | 2018-03-07 | 2018-10-08 | 2018-10-08 | COMP | 2019-03-01 | COMP | 2019-03-06 | COMP |  | INPR | 2019-05-08 | COMP | Rule 15 | 87 | 151 | 98 | 4 |  |  | 382
3088 | 2017-10-27 | 2018-03-06 | 2018-05-04 | 2018-05-04 | COMP | 2018-06-27 | COMP | 2018-07-30 | COMP | 2018-12-05 | COMP | 2019-01-11 | COMP | Rule 16 | 86 | 44 | 38 | 23 | 89 | 26 | 301
4462 | 2017-10-27 | 2017-12-16 | 2018-03-30 | 2018-03-30 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2021-11-19 | COMP | 2022-02-18 | COMP | Rule 16 | 33 | 71 | 536 | 1 | 383 | 63 | 1083
4490 | 2017-10-27 | 2018-01-10 | 2018-04-12 | 2018-04-12 | COMP | 2018-08-21 | COMP | 2018-08-21 | COMP | 2019-01-03 | COMP | 2019-02-25 | COMP | Rule 16 | 49 | 65 | 92 | 1 | 92 | 36 | 330
4622 | 2017-10-27 | 2018-02-16 | 2018-06-27 | 2018-10-10 | COMP | 2018-10-12 | COMP | 2018-10-12 | COMP | 2019-07-30 | COMP | 2019-07-29 | COMP | Other | 75 | 92 | 3 | 1 | 199 |  | 438
4733 | 2017-10-27 | 2018-03-23 | 2018-06-25 | 2018-06-25 | COMP | 2018-07-31 | COMP | 2018-08-15 | COMP | 2019-01-07 | COMP | 2019-02-12 | COMP | Rule 16 | 99 | 66 | 26 | 12 | 98 | 26 | 322
4735 | 2017-10-27 | 2018-03-23 | 2018-05-16 | 2018-08-01 | COMP | 2018-09-10 | COMP | 2019-01-30 | COMP | 2019-01-07 | COMP | 2019-03-20 | COMP | Rule 16 | 99 | 39 | 28 | 97 | 0 | 35 | 347
5070 | 2017-10-27 | 2018-04-27 | 2018-08-13 | 2018-08-13 | COMP | 2019-07-01 | COMP | 2019-07-02 | COMP | 2020-06-16 | COMP | 2020-07-31 | COMP | Rule 16 | 124 | 75 | 222 | 2 | 241 | 34 | 693
5328 | 2017-10-27 | 2018-05-22 | 2018-10-27 | 2018-12-19 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-11-07 | COMP | 2019-12-05 | COMP | Rule 16 | 141 | 111 | 136 | 1 | 90 | 18 | 527
5914 | 2017-10-27 | 2018-07-10 | 2019-04-01 | 2020-02-10 | COMP | 2020-03-04 | COMP | 2019-08-23 | COMP | 2020-04-27 | COMP | 2020-05-14 | COMP | Rule 16 | 174 | 182 | 17 |  | 169 | 14 | 638
6229 | 2017-10-27 | 2018-08-04 | 2018-12-17 | 2018-12-17 | COMP | 2019-10-03 | COMP | 2020-07-01 | COMP | 2020-02-04 | COMP | 2020-09-04 | COMP | Rule 16 | 192 | 92 | 202 | 187 | 0 | 48 | 718
6981 | 2017-10-27 | 2018-09-20 | 2018-09-24 | 2018-09-24 | COMP | 2019-04-11 | COMP | 2019-05-06 | COMP | 2019-11-16 | COMP | 2020-01-10 | COMP | Rule 16 | 225 | 3 | 137 | 18 | 136 | 36 | 551
8442 | 2017-10-27 | 2018-12-03 | 2019-02-07 | 2019-02-07 | COMP | 2019-05-10 | COMP | 2019-06-19 | COMP | 2019-05-16 | COMP | 2019-10-04 | COMP | Rule 16 | 274 | 46 | 66 | 28 | 0 | 76 | 486
3055 | 2017-10-28 | 2018-03-05 | 2018-04-25 | 2018-04-25 | COMP | 2018-07-31 | COMP | 2018-08-06 | COMP | 2019-06-07 | COMP | 2019-07-01 | COMP | Rule 16 | 84 | 38 | 68 | 5 | 211 | 17 | 418
13124 | 2017-10-28 | 2019-07-12 | 2019-07-18 | 2019-07-18 | COMP | 2019-07-29 | COMP | 2019-11-14 | COMP | 2020-07-09 | COMP | 2021-02-16 | COMP | Rule 16 | 426 | 5 | 8 | 77 | 164 | 151 | 826
3077 | 2017-10-29 | 2018-03-06 | 2018-05-01 | 2018-05-01 | COMP | 2018-05-04 | COMP | 2018-11-06 | COMP | 2019-02-19 | COMP | 2019-08-29 | COMP | Rule 16 | 85 | 41 | 4 | 130 | 69 | 136 | 460
2442 | 2017-10-30 | 2017-11-30 | 2018-12-17 | 2018-12-17 | COMP | 2019-02-22 | COMP | 2019-08-12 | COMP | 2019-11-25 | COMP | 2019-09-21 | COMP | Rule 16 | 21 | 263 | 46 | 120 | 74 |  | 475
2510 | 2017-10-30 | 2017-12-12 | 2019-06-13 | 2018-02-28 | COMP | 2019-09-20 | NOTN | 2019-09-20 | COMP | 2020-12-08 | COMP | 2019-10-23 | COMP | Other | 29 | 378 |  | 395 | 306 |  | 498
2548 | 2017-10-30 | 2017-12-21 | 2019-04-20 | 2020-02-03 | COMP | 2020-10-23 | COMP | 2021-06-29 | COMP | 2021-07-23 | COMP | 2021-09-02 | COMP | Rule 15/16 | 36 | 333 | 187 | 170 | 18 | 30 | 966
2549 | 2017-10-30 | 2017-12-21 | 2019-03-03 | 2020-08-28 | COMP | 2020-10-13 | COMP | 2021-02-23 | COMP | 2021-01-12 | COMP | 2021-02-24 | COMP | Rule 15/16 | 36 | 298 | 32 | 89 | 0 | 2 | 832
3681 | 2017-10-30 | 2018-06-07 | 2018-07-28 | 2018-07-28 | COMP | 2019-09-20 | NOTN | 2019-09-20 | COMP | 2020-12-08 | COMP | 2019-10-24 | COMP | Other | 151 | 36 |  | 289 | 306 |  | 499
3690 | 2017-10-30 | 2018-06-07 | 2018-08-01 | 2018-08-01 | COMP | 2019-09-20 | NOTN | 2019-09-20 | COMP | 2020-02-26 | COMP | 2019-10-23 | COMP | Other | 151 | 39 |  | 287 | 107 |  | 498
3694 | 2017-10-30 | 2018-06-09 | 2018-07-28 | 2018-07-28 | COMP | 2019-09-20 | NOTN | 2019-09-20 | COMP | 2020-12-08 | COMP | 2019-10-23 | COMP | Other | 152 | 34 |  | 289 | 306 |  | 498
3988 | 2017-10-30 | 2018-11-08 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-11 | COMP | 2019-10-17 | COMP | 2020-06-08 | COMP | 2020-07-09 | COMP | Rule 16 | 259 | 129 | 18 | 91 | 160 | 24 | 676
4633 | 2017-10-30 | 2018-02-21 | 2018-04-27 | 2018-12-26 | COMP | 2019-04-01 | COMP | 2019-04-02 | COMP | 2019-04-01 | COMP | 2019-05-08 | COMP | Rule 16 | 76 | 48 | 66 | 2 | 0 | 27 | 381
5044 | 2017-10-30 | 2018-04-26 | 2018-10-08 | 2018-10-08 | COMP | 2019-02-15 | COMP | 2019-02-15 | COMP | 2021-02-27 | INPR | 2020-02-14 | COMP | Rule 15/16 | 122 | 115 | 89 | 1 |  |  | 574
5832 | 2017-10-30 | 2018-07-07 | 2019-04-19 | 2019-05-08 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-07-10 | COMP | 2019-08-19 | COMP | Rule 16 | 171 | 197 | 47 | 1 | 0 | 26 | 452
6021 | 2017-10-30 | 2018-07-20 | 2019-01-24 | 2020-01-27 | COMP | 2020-03-12 | COMP | 2020-03-13 | COMP | 2020-05-06 | COMP | 2020-06-22 | COMP | Rule 16 | 181 | 128 | 33 | 2 | 39 | 33 | 663
2427 | 2017-10-31 | 2017-11-28 | 2018-01-29 | 2018-01-29 | COMP | 2018-02-13 | COMP | 2018-02-16 | COMP | 2022-07-16 | INPR | 2022-05-27 | COMP | Rule 16 | 18 | 42 | 12 | 4 |  |  | 1150
2506 | 2017-10-31 | 2017-12-11 | 2018-04-02 | 2018-04-02 | COMP | 2019-08-21 | COMP | 2019-08-31 | COMP | 2020-09-11 | COMP | 2020-12-03 | COMP | Rule 16 | 27 | 77 | 351 | 8 | 260 | 57 | 776
2519 | 2017-10-31 | 2017-12-14 | 2018-05-21 | 2018-05-21 | COMP | 2018-08-08 | COMP | 2019-01-03 | COMP | 2019-03-18 | COMP | 2019-09-09 | COMP | Rule 16 | 30 | 109 | 56 | 101 | 51 | 123 | 465
3355 | 2017-10-31 | 2018-04-11 | 2019-01-25 | 2019-07-05 | COMP | 2020-07-09 | COMP | 2021-06-08 | COMP | 2021-08-23 | COMP | 2021-10-20 | COMP | Rule 15/16 | 110 | 199 | 256 | 230 | 54 | 42 | 998
4441 | 2017-10-31 | 2017-12-11 | 2018-04-23 | 2018-04-23 | COMP | 2018-06-20 | COMP | 2018-06-20 | COMP | 2019-03-26 | COMP | 2019-04-16 | COMP | Rule 16 | 27 | 92 | 42 | 1 | 191 | 16 | 364
5262 | 2017-10-31 | 2018-05-15 | 2018-12-12 | 2018-12-12 | COMP | 2019-02-21 | COMP | 2019-06-07 | COMP |  |  | 2019-07-11 | COMP | Rule 16 | 134 | 146 | 48 | 76 |  |  | 424
6555 | 2017-10-31 | 2018-08-27 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-28 | COMP | 2019-06-04 | COMP | 2019-12-31 | COMP | 2020-07-15 | COMP | Rule 16 | 206 | 123 | 24 | 48 | 145 | 138 | 679
6590 | 2017-10-31 | 2018-08-29 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-20 | COMP | 2020-09-10 | COMP | 2020-09-20 | COMP | 2020-10-22 | COMP | Rule 15/16 | 208 | 324 | 6 | 184 | 7 | 24 | 749
7500 | 2017-10-31 | 2018-10-17 | 2018-12-21 | 2023-04-03 | COMP | 2023-05-15 | COMP | 2023-05-25 | COMP | 2023-05-02 | COMP | 2023-07-26 | COMP | Rule 16 | 242 | 45 | 31 | 9 | 0 | 42 | 1439
7759 | 2017-10-31 | 2018-10-30 | 2018-12-04 | 2018-12-04 | COMP | 2019-01-28 | COMP | 2019-03-14 | COMP | 2019-04-16 | COMP | 2019-04-26 | COMP | Rule 15/16 | 251 | 23 | 37 | 33 | 24 | 9 | 372
40468 | 2017-10-31 | 2023-01-05 | 2023-03-17 | 2023-03-17 | COMP | 2023-03-20 | NOTN | 2023-07-11 | COMP | 2023-08-16 | NOTN | 2023-09-27 | COMP | Other | 1300 | 50 |  | 80 |  |  | 1483
4388 | 2017-11-01 | 2017-11-09 | 2018-03-01 | 2018-03-01 | COMP | 2018-03-28 | COMP | 2018-03-28 | COMP | 2018-12-18 | COMP | 2019-03-04 | COMP | Rule 16 | 7 | 74 | 20 | 1 | 184 | 51 | 332
4426 | 2017-11-01 | 2017-12-05 | 2018-08-17 | 2018-08-22 | COMP | 2018-09-21 | COMP | 2019-07-18 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | Rule 15/16 | 22 | 178 | 22 | 206 | 69 | 19 | 514
4465 | 2017-11-01 | 2017-12-18 | 2017-12-22 | 2017-12-22 | COMP | 2018-03-29 | COMP | 2018-01-08 | INPR | 2022-01-30 | REQD | 2020-12-11 | COMP | Rule 16 | 31 | 5 | 66 |  |  |  | 781
4480 | 2017-11-01 | 2018-01-04 | 2018-06-11 | 2018-06-11 | COMP | 2018-09-27 | COMP | 2018-09-27 | COMP | 2018-11-17 | COMP | 2019-02-01 | COMP | Rule 16 | 42 | 110 | 77 | 1 | 36 | 50 | 312
4505 | 2017-11-01 | 2018-01-19 | 2018-04-07 | 2018-07-27 | COMP | 2018-10-18 | COMP | 2018-10-18 | COMP | 2019-01-23 | COMP | 2019-03-08 | COMP | Rule 16 | 52 | 55 | 59 | 1 | 64 | 32 | 336
4512 | 2017-11-01 | 2018-01-18 | 2018-07-13 | 2018-08-16 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2019-08-12 | COMP | 2019-08-23 | COMP | Rule 15/16 | 51 | 124 | 19 | 1 | 230 | 10 | 454
4513 | 2017-11-01 | 2018-01-17 | 2018-03-02 | 2021-10-28 | COMP | 2021-11-15 | COMP | 2023-03-09 | COMP | 2023-06-01 | COMP | 2023-07-31 | COMP | Rule 15/16 | 50 | 32 | 12 | 329 | 60 | 41 | 1441
4616 | 2017-11-01 | 2018-02-14 | 2018-04-13 | 2018-04-13 | COMP | 2018-06-22 | COMP | 2018-06-22 | COMP | 2019-05-22 | COMP | 2019-06-26 | COMP | Rule 16 | 70 | 42 | 50 | 1 | 230 | 25 | 413
5263 | 2017-11-01 | 2018-05-15 | 2018-07-26 | 2018-07-26 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2019-01-18 | COMP | 2019-02-24 | COMP | Rule 16 | 133 | 51 | 71 | 1 | 51 | 24 | 326
5830 | 2017-11-01 | 2018-07-07 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-14 | COMP | 2019-02-05 | COMP | 2019-02-26 | COMP | 2019-03-14 | COMP | Rule 16 | 169 | 64 | 48 | 35 | 15 | 13 | 340
9270 | 2017-11-01 | 2019-01-25 | 2019-04-29 | 2019-04-29 | COMP | 2020-01-17 | COMP | 2021-06-21 | COMP | 2021-07-20 | COMP | 2022-04-13 | COMP | Rule 16 | 307 | 66 | 182 | 360 | 21 | 186 | 1117
39164 | 2017-11-01 | 2022-10-04 | 2023-03-26 | 2023-03-26 | COMP | 2023-03-26 | NOTN | 2023-06-07 | COMP | 2023-09-27 | COMP | 2023-12-12 | COMP | Other | 1237 | 117 |  | 52 | 78 | 52 | 1533
2747 | 2017-11-02 | 2018-01-26 | 2018-02-14 | 2018-02-14 | COMP | 2019-04-01 | COMP | 2019-04-02 | COMP | 2019-11-06 | COMP | 2019-12-09 | COMP | Rule 16 | 56 | 14 | 283 | 2 | 154 | 21 | 525
2782 | 2017-11-02 | 2018-01-31 | 2018-02-27 | 2018-02-27 | COMP | 2020-10-07 | NOTN | 2019-12-03 | COMP | 2020-11-08 | COMP | 2021-01-05 | COMP | Rule 15/16 | 59 | 19 |  | 445 | 238 | 37 | 795
2783 | 2017-11-02 | 2018-01-31 | 2018-02-24 | 2018-02-24 | COMP | 2020-10-07 | NOTN | 2019-12-20 | COMP | 2020-11-08 | COMP | 2021-01-04 | COMP | Rule 15/16 | 59 | 17 |  | 459 | 225 | 36 | 794
2811 | 2017-11-02 | 2018-02-03 | 2018-03-19 | 2018-03-19 | COMP | 2018-09-28 | COMP | 2018-09-28 | COMP | 2019-01-28 | COMP | 2019-03-21 | COMP | Rule 16 | 61 | 30 | 137 | 1 | 81 | 38 | 344
2838 | 2017-11-02 | 2018-02-06 | 2018-06-08 | 2018-06-08 | COMP | 2018-09-04 | COMP | 2018-09-04 | COMP | 2022-08-03 | COMP | 2022-03-20 | COMP | Rule 16 | 63 | 87 | 61 | 1 | 985 |  | 1098
3061 | 2017-11-02 | 2018-03-07 | 2018-05-22 | 2018-05-22 | COMP | 2018-06-20 | COMP | 2018-09-29 | COMP | 2018-12-19 | COMP | 2019-01-01 | COMP | Rule 16 | 83 | 55 | 21 | 71 | 55 | 8 | 289
3689 | 2017-11-02 | 2018-06-07 | 2018-09-18 | 2018-09-18 | COMP | 2019-04-29 | COMP | 2019-08-06 | COMP | 2020-01-21 | COMP | 2021-11-28 | COMP | Rule 15/16 | 148 | 72 | 153 | 70 | 114 | 468 | 1020
4430 | 2017-11-02 | 2017-12-08 | 2018-04-03 | 2018-04-03 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-09-26 | COMP | 2019-12-05 | COMP | Rule 16 | 24 | 79 | 370 | 1 | 6 | 48 | 523
5983 | 2017-11-02 | 2018-07-17 | 2018-10-09 | 2018-10-09 | COMP | 2018-12-06 | COMP | 2019-12-18 | COMP | 2019-12-05 | COMP | 2020-02-08 | COMP | Rule 15/16 | 175 | 60 | 40 | 260 | 0 | 35 | 566
7131 | 2017-11-02 | 2018-09-28 | 2018-10-10 | 2018-10-10 | COMP | 2018-10-17 | COMP | 2019-01-31 | COMP | 2019-12-28 | INPR | 2019-07-19 | COMP | Rule 16 | 227 | 9 | 6 | 71 |  |  | 428
2454 | 2017-11-03 | 2017-12-04 | 2018-08-02 | 2018-08-02 | COMP | 2018-10-01 | COMP | 2019-01-24 | COMP | 2021-02-28 | INPR | 2019-11-07 | COMP | Rule 15/16 | 19 | 168 | 42 | 78 |  |  | 505
2480 | 2017-11-03 | 2017-12-07 | 2018-01-30 | 2018-01-30 | COMP | 2018-03-07 | COMP | 2019-02-22 | COMP | 2019-03-27 | COMP | 2019-08-08 | COMP | Rule 15/16 | 22 | 36 | 26 | 243 | 24 | 95 | 441
2539 | 2017-11-03 | 2017-12-18 | 2018-05-02 | 2018-05-02 | COMP | 2019-12-11 | COMP | 2019-12-16 | COMP | 2020-08-18 | COMP | 2020-09-01 | COMP | Other | 29 | 94 | 405 | 4 | 172 | 11 | 710
2540 | 2017-11-03 | 2017-12-19 | 2018-03-16 | 2018-03-16 | COMP | 2018-04-10 | COMP | 2018-04-23 | COMP | 2018-09-24 | COMP | 2019-03-27 | COMP | Other | 30 | 60 | 18 | 10 | 108 | 126 | 347
2659 | 2017-11-03 | 2018-01-16 | 2018-07-31 | 2018-07-31 | COMP | 2018-08-21 | COMP | 2020-02-10 | COMP | 2020-02-12 | COMP | 2020-10-20 | COMP | Rule 16 | 47 | 138 | 16 | 368 | 3 | 177 | 744
2873 | 2017-11-03 | 2018-02-09 | 2018-06-28 | 2018-06-28 | COMP | 2018-08-13 | COMP | 2018-08-30 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | Rule 16 | 65 | 98 | 32 | 14 | 104 | 1 | 309
4519 | 2017-11-03 | 2018-01-18 | 2018-04-18 | 2021-05-10 | COMP | 2021-05-18 | COMP | 2021-05-20 | COMP | 2022-09-07 | COMP | 2022-10-13 | COMP | Rule 16 | 49 | 64 | 7 | 3 | 328 | 27 | 1242
4602 | 2017-11-03 | 2018-02-13 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-07-02 | COMP | 2019-07-18 | COMP | Rule 16 | 67 | 235 | 25 | 1 | 91 | 12 | 426
5080 | 2017-11-03 | 2018-04-28 | 2018-09-19 | 2018-09-19 | COMP | 2019-02-11 | COMP | 2019-10-22 | COMP | 2019-10-15 | COMP | 2019-11-11 | COMP | Rule 15/16 | 119 | 100 | 98 | 178 | 0 | 14 | 506
2405 | 2017-11-06 | 2017-11-17 | 2017-11-18 | 2017-11-18 | COMP | 2018-03-28 | COMP | 2018-03-28 | COMP | 2022-05-22 | INPR | 2021-05-19 | COMP | Rule 16 | 9 | 1 | 87 | 1 |  |  | 887
2745 | 2017-11-06 | 2018-01-26 | 2018-04-02 | 2018-04-02 | COMP | 2018-07-09 | COMP | 2019-02-27 | COMP | 2018-10-15 | COMP | 2019-04-16 | COMP | Rule 15/16 | 54 | 46 | 69 | 160 | 0 | 35 | 360
2785 | 2017-11-06 | 2018-01-31 | 2018-04-01 | 2018-04-01 | COMP | 2018-04-30 | COMP | 2018-07-30 | COMP | 2019-04-20 | INPR | 2019-01-09 | COMP | Rule 15/16 | 57 | 42 | 21 | 64 |  |  | 293
2824 | 2017-11-06 | 2018-02-05 | 2018-02-16 | 2018-02-16 | COMP | 2018-02-26 | COMP | 2018-03-09 | COMP | 2018-03-12 | COMP | 2022-05-23 | COMP | Rule 16 | 60 | 10 | 6 | 10 | 2 | 1059 | 1142
3051 | 2017-11-06 | 2018-03-03 | 2019-01-24 | 2019-01-24 | COMP | 2019-03-13 | COMP | 2019-08-19 | COMP |  | INPR | 2020-12-20 | COMP | Rule 15/16 | 78 | 225 | 34 | 112 |  |  | 783
3147 | 2017-11-06 | 2018-03-14 | 2018-04-09 | 2020-09-28 | COMP | 2020-10-15 | COMP | 2018-04-19 | COMP | 2019-01-28 | COMP | 2020-12-07 | COMP | Rule 16 | 86 | 19 | 14 |  | 194 | 470 | 774
3284 | 2017-11-06 | 2018-04-02 | 2018-07-31 | 2018-07-31 | COMP | 2018-09-18 | COMP | 2019-09-18 | COMP | 2020-07-03 | COMP | 2020-07-15 | COMP | Rule 16 | 99 | 85 | 35 | 252 | 200 | 9 | 675
3392 | 2017-11-06 | 2018-04-18 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-21 | COMP | 2019-07-15 | COMP | 2019-08-09 | COMP | 2019-08-22 | COMP | Rule 16 | 111 | 135 | 17 | 161 | 20 | 10 | 450
3740 | 2017-11-06 | 2018-06-25 | 2018-06-29 | 2018-06-29 | COMP | 2018-09-18 | COMP | 2018-09-21 | COMP | 2018-12-17 | COMP | 2019-01-09 | COMP | Rule 15/16 | 158 | 5 | 56 | 4 | 59 | 16 | 293
4500 | 2017-11-06 | 2018-01-08 | 2018-07-15 | 2018-07-15 | COMP | 2020-01-13 | COMP | 2019-06-12 | COMP | 2019-06-19 | COMP | 2019-07-22 | COMP | Rule 16 | 41 | 131 | 375 |  | 6 | 23 | 427
4773 | 2017-11-06 | 2018-03-30 | 2018-10-16 | 2018-10-16 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-05-16 | COMP | 2019-07-03 | COMP | Rule 16 | 98 | 140 | 56 | 1 | 91 | 34 | 415
5116 | 2017-11-06 | 2018-05-01 | 2018-08-13 | 2018-08-13 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-07-31 | COMP | 2020-09-25 | COMP | Rule 16 | 120 | 73 | 395 | 1 | 102 | 40 | 726
5749 | 2017-11-06 | 2018-06-29 | 2018-08-15 | 2018-08-15 | COMP | 2018-08-28 | COMP | 2018-09-04 | COMP | 2018-11-07 | COMP | 2019-01-23 | COMP | Rule 16 | 162 | 33 | 10 | 5 | 47 | 50 | 302
2447 | 2017-11-07 | 2017-12-01 | 2017-12-08 | 2017-12-08 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-02-05 | COMP | 2019-05-15 | COMP | Rule 16 | 16 | 6 | 288 | 1 | 3 | 71 | 380
2458 | 2017-11-07 | 2017-12-04 | 2017-12-21 | 2017-12-21 | COMP | 2018-01-03 | COMP | 2018-01-04 | COMP | 2022-07-16 | INPR | 2021-04-11 | COMP | Rule 16 | 17 | 14 | 8 | 2 |  |  | 858
2523 | 2017-11-07 | 2017-12-14 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-03 | NOTN | 2020-01-15 | COMP | 2020-01-06 | COMP | 2020-02-27 | COMP | Other | 25 | 494 |  | 30 | 0 | 30 | 576
2547 | 2017-11-07 | 2017-12-22 | 2018-06-28 | 2018-06-28 | COMP | 2020-05-04 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-06-05 | COMP | Rule 15/16 | 31 | 130 | 464 | 2 | 1 | 23 | 646
2628 | 2017-11-07 | 2018-01-09 | 2018-07-03 | 2018-07-03 | COMP | 2019-04-02 | COMP | 2019-04-04 | COMP | 2019-06-25 | COMP | 2019-08-09 | COMP | Rule 15/16 | 41 | 123 | 187 | 3 | 58 | 33 | 440
2877 | 2017-11-07 | 2018-02-09 | 2018-05-20 | 2018-05-20 | COMP | 2018-06-11 | COMP | 2018-08-21 | COMP | 2018-07-09 | COMP | 2021-04-10 | COMP | Rule 16 | 63 | 70 | 15 | 51 | 0 | 662 | 858
3125 | 2017-11-07 | 2018-03-12 | 2018-05-24 | 2018-05-24 | COMP | 2018-11-09 | COMP | 2018-11-13 | COMP | 2019-01-08 | COMP | 2019-03-14 | COMP | Rule 16 | 83 | 54 | 119 | 2 | 37 | 46 | 336
3149 | 2017-11-07 | 2018-03-14 | 2018-05-21 | 2018-05-21 | COMP | 2018-07-17 | COMP | 2018-07-17 | COMP |  | INPR | 2021-04-10 | COMP | Rule 16 | 85 | 49 | 40 | 1 |  |  | 858
3895 | 2017-11-07 | 2018-09-24 | 2019-06-22 | 2019-06-22 | COMP | 2021-02-05 | COMP | 2021-04-20 | COMP | 2022-01-05 | COMP | 2021-06-12 | COMP | Rule 15/16 | 220 | 187 | 408 | 52 | 181 |  | 902
4010 | 2017-11-07 | 2018-11-27 | 2019-04-29 | 2019-04-29 | COMP | 2019-08-16 | COMP | 2020-07-24 | COMP | 2022-05-25 | COMP | 2022-06-15 | COMP | Rule 15/16 | 263 | 106 | 78 | 237 | 463 | 15 | 1157
4432 | 2017-11-07 | 2017-12-07 | 2018-02-05 | 2018-02-05 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2018-12-17 | COMP | 2019-08-21 | COMP | Rule 15/16 | 20 | 40 | 80 | 1 | 140 | 172 | 448
4508 | 2017-11-07 | 2018-01-16 | 2018-09-10 | 2018-11-19 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-07 | COMP | 2019-03-04 | COMP | Rule 16 | 45 | 166 | 49 | 1 | 6 | 17 | 328
4557 | 2017-11-07 | 2018-01-29 | 2018-04-12 | 2018-04-12 | COMP | 2018-05-14 | COMP | 2018-05-14 | COMP | 2020-04-26 | INPR | 2019-12-23 | COMP | Rule 16 | 54 | 53 | 23 | 1 |  |  | 532
5435 | 2017-11-07 | 2018-05-31 | 2018-07-27 | 2018-07-27 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-04-05 | COMP | 2019-04-10 | COMP | Rule 16 | 140 | 41 | 69 | 1 | 105 | 4 | 355
2411 | 2017-11-08 | 2017-11-17 | 2018-01-06 | 2018-01-06 | COMP | 2018-05-16 | COMP | 2018-05-16 | COMP | 2018-05-22 | COMP | 2021-04-23 | COMP | Rule 16 | 7 | 32 | 91 | 1 | 5 | 735 | 867
2608 | 2017-11-08 | 2018-01-10 | 2018-04-23 | 2018-04-23 | COMP | 2019-04-09 | COMP | 2019-04-11 | COMP | 2019-08-27 | COMP | 2019-09-26 | COMP | Rule 16 | 41 | 72 | 242 | 3 | 97 | 22 | 472
2864 | 2017-11-08 | 2018-02-08 | 2018-08-02 | 2018-08-02 | COMP | 2019-12-13 | COMP | 2020-02-24 | COMP | 2022-01-30 | INPR | 2020-05-18 | COMP | Rule 15/16 | 61 | 123 | 343 | 48 |  |  | 632
2875 | 2017-11-08 | 2018-02-09 | 2018-06-25 | 2018-06-25 | COMP | 2018-08-23 | COMP | 2018-08-27 | COMP | 2019-07-16 | COMP | 2019-08-15 | COMP | Rule 15/16 | 62 | 95 | 43 | 3 | 222 | 23 | 443
2888 | 2017-11-08 | 2018-02-14 | 2018-04-11 | 2018-04-11 | COMP | 2018-11-08 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-07-01 | COMP | Rule 16 | 65 | 40 | 149 | 158 | 1 | 3 | 411
3359 | 2017-11-08 | 2018-04-13 | 2019-02-20 | 2019-02-20 | COMP | 2019-03-11 | COMP | 2019-05-07 | COMP | 2019-09-30 | COMP | 2019-11-05 | COMP | Rule 16 | 106 | 214 | 14 | 42 | 102 | 27 | 500
3381 | 2017-11-08 | 2018-04-17 | 2019-03-03 | 2019-03-03 | COMP | 2020-06-24 | COMP | 2021-09-03 | COMP | 2021-09-10 | COMP | 2021-10-27 | COMP | Rule 15/16 | 108 | 219 | 332 | 303 | 5 | 34 | 997
4491 | 2017-11-08 | 2018-01-10 | 2018-04-24 | 2018-04-24 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-08-02 | COMP | Rule 16 | 41 | 73 | 272 | 1 | 1 | 51 | 434
4675 | 2017-11-08 | 2018-03-08 | 2018-07-01 | 2018-07-02 | COMP | 2018-08-17 | COMP | 2018-09-06 | COMP | 2018-08-19 | COMP | 2019-05-03 | COMP | Rule 16 | 80 | 81 | 34 | 14 | 0 | 165 | 371
6666 | 2017-11-08 | 2018-09-05 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-03 | COMP | 2018-10-10 | COMP | 2019-07-21 | INPR | 2019-04-17 | COMP | Rule 16 | 206 | 13 | 9 | 6 |  |  | 359
26185 | 2017-11-08 | 2021-03-11 | 2023-01-28 | 2023-01-28 | COMP | 2023-06-15 | COMP | 2023-07-27 | COMP | 2023-05-25 | COMP | 2023-08-15 | COMP | Rule 16 | 836 | 474 | 97 | 29 | 0 | 14 | 1447
2656 | 2017-11-09 | 2018-01-12 | 2018-01-22 | 2018-01-22 | COMP | 2018-01-24 | COMP | 2018-01-24 | COMP | 2019-04-05 | COMP | 2019-05-16 | COMP | Rule 16 | 42 | 6 | 3 | 1 | 302 | 30 | 379
2768 | 2017-11-09 | 2018-01-29 | 2018-08-20 | 2018-08-20 | COMP | 2018-10-05 | COMP | 2019-04-25 | INPR | 2018-12-06 | COMP | 2019-06-13 | COMP | Rule 16 | 52 | 143 | 34 |  |  |  | 398
2885 | 2017-11-09 | 2018-02-13 | 2018-05-22 | 2018-05-22 | COMP | 2018-06-20 | COMP | 2018-06-20 | COMP | 2019-03-05 | COMP | 2019-05-22 | COMP | Rule 16 | 63 | 70 | 21 | 1 | 176 | 57 | 383
2983 | 2017-11-09 | 2018-02-26 | 2018-05-16 | 2018-05-16 | COMP | 2018-06-07 | COMP | 2018-06-07 | COMP | 2018-12-10 | COMP | 2019-01-23 | COMP | Rule 16 | 71 | 58 | 16 | 1 | 128 | 30 | 299
3157 | 2017-11-09 | 2018-03-16 | 2018-06-03 | 2018-06-03 | COMP | 2018-07-11 | COMP | 2018-07-11 | COMP | 2019-08-06 | COMP | 2019-08-30 | COMP | Rule 16 | 85 | 55 | 27 | 1 | 270 | 19 | 453
4107 | 2017-11-09 | 2019-02-09 | 2019-02-19 | 2019-02-19 | COMP | 2019-02-22 | NOTN | 2019-04-25 | COMP | 2019-04-30 | COMP | 2019-06-27 | COMP | Other | 311 | 6 |  | 48 | 4 | 42 | 408
4618 | 2017-11-09 | 2018-02-15 | 2018-03-20 | 2018-03-20 | COMP | 2018-07-09 | COMP | 2018-11-26 | COMP |  |  | 2019-05-04 | COMP | Rule 16 | 65 | 23 | 78 | 97 |  |  | 370
4880 | 2017-11-09 | 2018-04-09 | 2018-06-14 | 2018-06-14 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2018-11-13 | COMP | 2019-03-05 | COMP | Rule 16 | 101 | 48 | 94 | 1 | 13 | 75 | 327
5423 | 2017-11-09 | 2018-05-30 | 2018-10-11 | 2018-10-11 | COMP | 2019-12-13 | COMP | 2020-01-16 | COMP |  |  | 2020-03-13 | COMP | Rule 16 | 137 | 95 | 294 | 23 |  |  | 585
6466 | 2017-11-09 | 2018-08-20 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-04 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-06-13 | COMP | Rule 16 | 194 | 34 | 40 | 130 | 1 | 4 | 398
7108 | 2017-11-09 | 2018-09-27 | 2019-09-30 | 2019-09-30 | COMP | 2020-03-16 | COMP | 2020-04-01 | COMP | 2020-06-17 | COMP | 2020-11-17 | COMP | Rule 15/16 | 221 | 253 | 114 | 13 | 55 | 108 | 759
10241 | 2017-11-09 | 2019-03-07 | 2019-04-05 | 2019-04-05 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2020-09-15 | COMP | 2020-10-29 | COMP | Rule 16 | 329 | 22 | 46 | 1 | 321 | 33 | 747
16442 | 2017-11-09 | 2019-12-31 | 2020-03-08 | 2020-03-08 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-08-11 | COMP | 2020-10-06 | COMP | Rule 16 | 535 | 46 | 80 | 1 | 32 | 40 | 730
2887 | 2017-11-10 | 2018-02-15 | 2018-04-30 | 2018-04-30 | COMP | 2018-07-17 | COMP | 2018-07-17 | COMP |  |  | 2019-04-25 | COMP | Rule 16 | 64 | 52 | 55 | 1 |  |  | 363
2945 | 2017-11-10 | 2018-02-21 | 2018-05-09 | 2018-05-09 | COMP | 2018-06-05 | COMP | 2019-06-25 | COMP | 2019-09-05 | COMP | 2019-09-17 | COMP | Rule 15/16 | 67 | 56 | 19 | 266 | 51 | 9 | 463
3021 | 2017-11-10 | 2018-02-27 | 2018-09-25 | 2018-09-25 | COMP | 2018-11-01 | COMP | 2019-01-02 | COMP | 2019-12-30 | COMP | 2020-01-24 | COMP | Rule 15/16 | 71 | 148 | 28 | 40 | 250 | 18 | 550
3227 | 2017-11-10 | 2018-03-26 | 2019-01-07 | 2018-12-29 | COMP | 2019-10-22 | COMP | 2020-02-13 | COMP | 2020-01-10 | COMP | 2020-04-22 | COMP | Rule 16 | 90 | 198 | 206 | 77 | 0 | 49 | 612
4442 | 2017-11-10 | 2017-12-11 | 2018-04-27 | 2018-09-10 | COMP | 2019-01-14 | COMP | 2019-01-14 | INPR | 2018-10-23 | COMP | 2019-03-09 | COMP | Rule 16 | 19 | 96 | 86 |  |  |  | 329
4455 | 2017-11-10 | 2017-12-15 | 2018-03-05 | 2019-05-29 | COMP | 2019-07-03 | COMP | 2019-07-08 | COMP | 2019-07-09 | COMP | 2019-08-05 | COMP | Rule 16 | 23 | 53 | 26 | 3 | 2 | 20 | 433
4456 | 2017-11-10 | 2017-12-15 | 2018-03-01 | 2018-03-01 | COMP | 2018-04-30 | COMP | 2018-05-01 | COMP | 2018-05-29 | COMP | 2019-10-08 | COMP | Rule 16 | 23 | 51 | 43 | 2 | 20 | 344 | 478
9042 | 2017-11-10 | 2019-01-15 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-01 | NOTN | 2019-04-04 | COMP | 2019-06-17 | NOTN | 2019-06-28 | COMP | Other | 293 | 32 |  | 25 |  |  | 408
2911 | 2017-11-11 | 2018-02-15 | 2018-08-03 | 2018-08-03 | COMP | 2018-09-17 | COMP | 2018-09-21 | COMP | 2018-12-21 | COMP | 2019-01-18 | COMP | Rule 15/16 | 64 | 119 | 31 | 5 | 63 | 19 | 296
2508 | 2017-11-13 | 2017-12-12 | 2018-10-11 | 2018-10-11 | COMP | 2018-11-07 | COMP | 2019-04-12 | COMP | 2020-02-20 | COMP | 2020-03-12 | COMP | Rule 15/16 | 20 | 211 | 20 | 106 | 215 | 16 | 583
2526 | 2017-11-13 | 2017-12-15 | 2018-09-09 | 2018-09-09 | COMP | 2019-05-14 | COMP | 2019-05-15 | COMP | 2019-10-07 | COMP | 2019-10-11 | COMP | Rule 16 | 23 | 184 | 170 | 2 | 101 | 5 | 481
2606 | 2017-11-13 | 2018-01-05 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-20 | COMP | 2018-08-30 | COMP | 2018-11-13 | COMP | 2019-04-18 | COMP | Rule 16 | 36 | 134 | 25 | 9 | 52 | 107 | 358
2895 | 2017-11-13 | 2018-02-13 | 2018-04-02 | 2018-04-02 | COMP | 2018-10-04 | COMP | 2018-10-19 | COMP | 2019-03-06 | COMP | 2019-04-30 | COMP | Rule 16 | 62 | 34 | 131 | 12 | 92 | 40 | 366
3089 | 2017-11-13 | 2018-03-06 | 2018-05-31 | 2018-05-31 | COMP | 2018-06-04 | COMP | 2018-06-06 | COMP | 2019-02-09 | COMP | 2019-03-28 | COMP | Rule 16 | 76 | 62 | 3 | 3 | 170 | 33 | 343
3167 | 2017-11-13 | 2018-03-16 | 2018-06-04 | 2018-06-04 | COMP | 2018-06-18 | COMP | 2019-07-25 | COMP | 2019-07-16 | COMP | 2019-08-19 | COMP | Rule 16 | 84 | 56 | 11 | 278 | 0 | 18 | 443
3277 | 2017-11-13 | 2018-03-30 | 2018-09-10 | 2019-06-05 | COMP | 2019-06-26 | COMP | 2019-12-05 | COMP | 2019-11-25 | COMP | 2020-02-08 | COMP | Rule 15/16 | 94 | 114 | 16 | 112 | 0 | 44 | 560
3328 | 2017-11-13 | 2018-04-10 | 2018-10-12 | 2018-10-12 | COMP | 2019-08-30 | COMP | 2019-09-10 | COMP | 2019-10-08 | COMP | 2019-12-19 | COMP | Rule 15/16 | 101 | 131 | 222 | 7 | 21 | 50 | 527
4550 | 2017-11-13 | 2018-01-26 | 2018-05-02 | 2018-05-02 | COMP | 2018-05-07 | COMP | 2018-09-27 | COMP | 2018-10-04 | COMP | 2019-01-14 | COMP | Rule 16 | 50 | 68 | 4 | 101 | 6 | 68 | 292
4620 | 2017-11-13 | 2018-02-16 | 2018-12-21 | 2018-12-21 | COMP | 2019-07-09 | COMP | 2020-12-01 | COMP | 2020-12-15 | COMP | 2021-02-02 | COMP | Rule 15/16 | 65 | 214 | 137 | 353 | 11 | 33 | 808
5621 | 2017-11-13 | 2018-06-20 | 2018-06-25 | 2019-03-23 | COMP | 2018-07-18 | COMP | 2018-07-18 | COMP | 2019-08-15 | COMP | 2019-08-16 | COMP | Rule 16 | 151 | 4 |  | 1 | 272 | 2 | 442
6100 | 2017-11-13 | 2018-07-25 | 2018-12-05 | 2020-08-14 | COMP | 2021-03-18 | COMP | 2021-04-06 | COMP | 2023-07-27 | COMP | 2023-09-12 | COMP | Rule 16 | 175 | 92 | 147 | 14 | 581 | 33 | 1464
7037 | 2017-11-13 | 2018-09-24 | 2018-12-20 | 2019-02-06 | COMP | 2019-02-19 | COMP | 2019-03-22 | COMP | 2019-08-08 | COMP | 2019-08-21 | COMP | Rule 15/16 | 217 | 61 | 9 | 24 | 98 | 10 | 445
8435 | 2017-11-13 | 2018-12-01 | 2019-02-08 | 2019-02-08 | COMP | 2019-02-25 | COMP | 2019-03-04 | COMP | 2019-08-27 | COMP | 2020-01-13 | COMP | Rule 16 | 263 | 47 | 11 | 6 | 125 | 94 | 542
14034 | 2017-11-13 | 2019-08-23 | 2019-10-03 | 2019-10-03 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-05-14 | COMP | 2020-06-23 | COMP | Rule 15/16 | 447 | 29 | 101 | 1 | 54 | 28 | 655
2420 | 2017-11-14 | 2017-11-27 | 2018-02-26 | 2018-02-26 | COMP | 2021-10-21 | COMP | 2022-06-01 | COMP | 2022-06-01 | COMP | 2022-07-22 | COMP | Rule 16 | 8 | 62 | 922 | 154 | 1 | 36 | 1178
2421 | 2017-11-14 | 2017-11-27 | 2018-02-25 | 2018-02-25 | COMP | 2021-10-21 | COMP | 2021-12-09 | COMP | 2022-07-19 | COMP | 2022-07-26 | COMP | Rule 16 | 8 | 61 | 922 | 33 | 154 | 6 | 1180
2456 | 2017-11-14 | 2017-12-04 | 2018-02-21 | 2018-02-21 | COMP | 2018-02-22 | COMP | 2018-02-23 | COMP | 2018-12-31 | COMP | 2019-01-30 | COMP | Rule 16 | 13 | 54 | 2 | 2 | 215 | 21 | 302
2489 | 2017-11-14 | 2017-12-07 | 2018-05-10 | 2018-05-10 | COMP | 2019-01-03 | COMP | 2020-08-10 | COMP | 2021-05-27 | COMP | 2021-07-09 | COMP | Rule 15/16 | 16 | 107 | 163 | 405 | 201 | 30 | 917
2554 | 2017-11-14 | 2017-12-22 | 2018-06-20 | 2018-06-20 | COMP | 2018-07-18 | COMP | 2018-10-17 | COMP | 2019-03-11 | COMP | 2019-05-04 | COMP | Rule 16 | 27 | 124 | 20 | 65 | 97 | 40 | 368
2653 | 2017-11-14 | 2018-01-12 | 2018-03-13 | 2018-03-13 | COMP | 2018-04-19 | COMP | 2018-04-27 | COMP | 2020-09-29 | COMP | 2020-11-06 | COMP | Rule 16 | 40 | 41 | 28 | 7 | 611 | 29 | 751
2717 | 2017-11-14 | 2018-01-23 | 2018-12-31 | 2018-12-31 | COMP | 2019-03-05 | COMP | 2019-03-13 | COMP |  |  | 2019-10-07 | COMP | Rule 16 | 46 | 237 | 44 | 7 |  |  | 476
2836 | 2017-11-14 | 2018-02-06 | 2018-08-28 | 2018-08-28 | COMP | 2018-11-05 | COMP | 2018-12-10 | COMP | 2018-12-31 | COMP | 2019-03-22 | COMP | Rule 15/16 | 56 | 143 | 49 | 23 | 15 | 57 | 338
2883 | 2017-11-14 | 2018-02-13 | 2018-06-07 | 2018-06-07 | COMP | 2018-11-15 | COMP | 2019-02-06 | COMP | 2019-01-18 | COMP | 2019-02-26 | COMP | Rule 15/16 | 61 | 81 | 113 | 55 | 0 | 14 | 320
3275 | 2017-11-14 | 2018-03-30 | 2018-04-10 | 2018-04-10 | COMP | 2018-04-27 | COMP | 2018-04-28 | COMP | 2023-05-27 | INPR | 2022-05-11 | COMP | Rule 16 | 93 | 8 | 14 | 1 |  |  | 1129
3520 | 2017-11-14 | 2018-05-09 | 2018-10-11 | 2018-10-11 | COMP | 2018-09-18 | COMP | 2018-10-11 | COMP | 2019-04-24 | COMP | 2019-05-07 | COMP | Rule 16 | 121 | 109 |  | 18 | 133 | 10 | 370
4805 | 2017-11-14 | 2018-03-31 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-20 | COMP | 2019-02-26 | COMP | 2019-02-05 | COMP | 2019-04-27 | COMP | Rule 15/16 | 93 | 75 | 25 | 129 | 0 | 44 | 363
5851 | 2017-11-14 | 2018-07-07 | 2018-12-21 | 2018-12-27 | COMP | 2019-01-24 | COMP | 2019-02-04 | COMP | 2019-02-26 | COMP | 2019-03-15 | COMP | Rule 15/16 | 161 | 116 | 19 | 8 | 16 | 14 | 333
5886 | 2017-11-14 | 2018-07-09 | 2018-10-18 | 2019-01-28 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-04-16 | COMP | 2019-06-06 | COMP | Rule 15/16 | 162 | 73 | 12 | 1 | 45 | 37 | 391
6726 | 2017-11-14 | 2018-09-10 | 2018-09-25 | 2018-09-25 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2018-12-04 | COMP | 2019-02-08 | COMP | Rule 15/16 | 206 | 12 | 35 | 1 | 14 | 46 | 309
2645 | 2017-11-15 | 2018-01-11 | 2018-08-06 | 2018-07-26 | COMP | 2018-10-09 | COMP | 2018-10-29 | COMP | 2018-08-08 | COMP | 2019-06-27 | COMP | Rule 16 | 38 | 144 | 53 | 15 | 0 | 166 | 405
2705 | 2017-11-15 | 2018-01-22 | 2018-07-19 | 2018-07-19 | COMP | 2018-08-13 | COMP | 2018-11-21 | COMP | 2019-01-11 | COMP | 2019-02-20 | COMP | Rule 15/16 | 44 | 126 | 18 | 71 | 34 | 27 | 315
2784 | 2017-11-15 | 2018-01-31 | 2018-04-13 | 2018-04-13 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2020-05-23 | COMP | 2020-06-29 | COMP | Other | 51 | 52 | 337 | 1 | 195 | 25 | 657
2954 | 2017-11-15 | 2018-02-22 | 2018-03-28 | 2018-03-28 | COMP | 2018-09-14 | COMP | 2018-10-06 | COMP | 2019-07-31 | COMP | 2019-10-19 | COMP | Rule 15/16 | 66 | 25 | 120 | 16 | 204 | 57 | 484
3086 | 2017-11-15 | 2018-03-06 | 2018-09-22 | 2018-09-22 | COMP | 2018-10-09 | COMP | 2019-07-09 | COMP | 2019-07-23 | COMP | 2019-08-27 | COMP | Rule 15/16 | 74 | 141 | 12 | 187 | 11 | 26 | 447
3407 | 2017-11-15 | 2018-04-19 | 2019-03-11 | 2019-01-04 | COMP | 2019-07-18 | COMP | 2019-07-25 | COMP | 2019-12-28 | INPR | 2019-08-20 | COMP | Rule 16 | 106 | 223 | 136 | 6 |  |  | 442
3682 | 2017-11-15 | 2018-06-06 | 2018-08-28 | 2018-08-28 | COMP | 2019-04-01 | COMP | 2019-04-18 | NOTN | 2020-12-07 | COMP | 2020-12-31 | COMP | Rule 15/16 | 139 | 59 | 147 |  |  |  | 785
4420 | 2017-11-15 | 2017-11-30 | 2018-03-10 | 2018-03-10 | COMP | 2018-06-27 | COMP | 2018-06-27 | COMP | 2018-07-05 | COMP | 2020-08-26 | COMP | Rule 15/16 | 10 | 68 | 77 | 1 | 6 | 541 | 699
4470 | 2017-11-15 | 2017-12-27 | 2018-04-05 | 2018-04-05 | COMP | 2018-04-27 | COMP | 2018-04-27 | COMP | 2018-12-18 | COMP | 2019-02-21 | COMP | Rule 16 | 28 | 69 | 17 | 1 | 162 | 44 | 316
4549 | 2017-11-15 | 2018-01-26 | 2018-04-26 | 2019-07-22 | COMP | 2020-04-03 | COMP | 2021-10-19 | COMP | 2021-08-30 | COMP | 2021-12-11 | COMP | Rule 16 | 48 | 64 | 177 | 391 | 0 | 36 | 1022
4756 | 2017-11-15 | 2018-03-26 | 2018-04-26 | 2018-04-26 | COMP | 2018-05-11 | COMP | 2018-05-22 | COMP | 2022-03-19 | INPR | 2021-03-01 | COMP | Rule 16 | 88 | 24 | 12 | 8 |  |  | 824
4769 | 2017-11-15 | 2018-03-27 | 2018-05-25 | 2018-05-25 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-06-10 | COMP | 2019-07-16 | COMP | Rule 15/16 | 89 | 44 | 188 | 1 | 74 | 26 | 417
5103 | 2017-11-15 | 2018-04-30 | 2018-08-02 | 2018-08-02 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2019-05-11 | COMP | 2019-06-07 | COMP | Rule 16 | 113 | 67 | 61 | 1 | 134 | 19 | 391
5205 | 2017-11-15 | 2018-05-10 | 2018-06-27 | 2018-07-13 | COMP | 2018-07-16 | COMP | 2018-07-16 | INPR | 2023-04-30 | CANC | 2022-03-26 | COMP | Rule 16 | 121 | 34 | 2 |  |  |  | 1095
6168 | 2017-11-15 | 2018-08-01 | 2019-04-06 | 2019-04-06 | COMP | 2020-08-17 | COMP | 2020-02-21 | COMP | 2020-04-14 | COMP | 2020-06-27 | COMP | Rule 15/16 | 178 | 170 | 345 |  | 38 | 53 | 656
9052 | 2017-11-15 | 2019-01-14 | 2019-03-25 | 2019-03-25 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-01-08 | COMP | 2020-02-21 | COMP | Rule 15/16 | 290 | 49 | 194 | 1 | 7 | 31 | 567
12206 | 2017-11-15 | 2019-05-28 | 2019-08-28 | 2019-08-28 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-04-23 | COMP | 2020-06-18 | COMP | Rule 15/16 | 383 | 66 | 25 | 1 | 140 | 40 | 650
14777 | 2017-11-15 | 2019-09-26 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-19 | COMP | 2020-07-09 | COMP | 2020-07-21 | COMP | 2020-09-22 | COMP | Rule 16 | 468 | 88 | 32 | 80 | 9 | 45 | 717
19212 | 2017-11-15 | 2020-04-25 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2022-07-16 | INPR | 2020-08-24 | COMP | Rule 16 | 612 | 22 | 13 | 1 |  |  | 697
2446 | 2017-11-16 | 2017-12-01 | 2017-12-07 | 2017-12-07 | COMP | 2017-12-11 | COMP | 2017-12-11 | COMP | 2019-07-17 | COMP | 2019-09-04 | COMP | Rule 16 | 10 | 5 | 3 | 1 | 402 | 35 | 451
2541 | 2017-11-16 | 2017-12-20 | 2018-06-28 | 2018-06-28 | COMP | 2018-10-29 | COMP | 2018-12-05 | COMP | 2019-03-05 | COMP | 2019-04-11 | COMP | Rule 15/16 | 23 | 132 | 86 | 25 | 61 | 28 | 350
2542 | 2017-11-16 | 2017-12-20 | 2018-06-29 | 2018-06-29 | COMP | 2019-09-03 | COMP | 2019-10-29 | COMP | 2019-11-14 | COMP | 2019-12-13 | COMP | Rule 15/16 | 23 | 133 | 296 | 41 | 12 | 20 | 520
2556 | 2017-11-16 | 2017-12-22 | 2018-06-06 | 2018-06-06 | COMP | 2018-11-05 | COMP | 2019-03-28 | COMP | 2019-04-03 | COMP | 2019-05-09 | COMP | Rule 15/16 | 25 | 114 | 107 | 97 | 5 | 27 | 370
2913 | 2017-11-16 | 2018-02-15 | 2018-06-18 | 2018-06-18 | COMP | 2018-06-22 | COMP | 2019-01-09 | COMP | 2019-01-02 | COMP | 2019-03-13 | COMP | Rule 16 | 61 | 86 | 5 | 137 | 0 | 44 | 329
3074 | 2017-11-16 | 2018-03-06 | 2018-07-19 | 2018-11-13 | COMP | 2019-02-11 | COMP | 2019-02-13 | COMP | 2019-09-17 | COMP | 2019-10-02 | COMP | Rule 15/16 | 73 | 96 | 60 | 3 | 151 | 12 | 471
4472 | 2017-11-16 | 2017-12-28 | 2018-05-01 | 2018-05-01 | COMP | 2018-05-08 | COMP | 2018-05-08 | COMP | 2018-10-24 | COMP | 2019-02-10 | COMP | Rule 16 | 28 | 86 | 6 | 1 | 119 | 72 | 307
5028 | 2017-11-16 | 2018-04-24 | 2018-08-04 | 2018-08-04 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-08-28 | COMP | Rule 16 | 108 | 72 | 242 | 1 | 1 | 27 | 447
5747 | 2017-11-16 | 2018-06-29 | 2018-11-16 | 2019-01-23 | COMP | 2019-02-08 | COMP | 2019-04-26 | COMP | 2019-07-30 | COMP | 2019-08-15 | COMP | Rule 15/16 | 155 | 98 | 13 | 55 | 66 | 13 | 438
5767 | 2017-11-16 | 2018-07-02 | 2018-09-07 | 2018-09-07 | COMP | 2018-10-17 | COMP | 2018-10-17 | COMP | 2019-01-04 | COMP | 2019-04-01 | COMP | Rule 16 | 156 | 48 | 29 | 1 | 53 | 60 | 342
5838 | 2017-11-16 | 2018-07-06 | 2019-05-29 | 2019-05-29 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-09-30 | COMP | 2020-10-18 | COMP | Rule 15/16 | 159 | 225 | 121 | 1 | 220 | 13 | 734
11030 | 2017-11-16 | 2019-04-09 | 2019-08-16 | 2019-12-06 | COMP | 2020-01-31 | COMP | 2020-11-09 | COMP | 2022-05-17 | COMP | 2022-06-16 | COMP | Rule 15/16 | 348 | 92 | 38 | 199 | 382 | 22 | 1152
2432 | 2017-11-17 | 2017-11-29 | 2018-01-20 | 2018-01-20 | COMP | 2018-01-29 | COMP | 2018-02-19 | COMP | 2018-03-14 | COMP | 2019-09-30 | COMP | Rule 16 | 7 | 35 | 6 | 15 | 17 | 391 | 468
2746 | 2017-11-17 | 2018-01-26 | 2018-09-19 | 2018-10-26 | COMP | 2019-03-07 | COMP | 2020-05-11 | COMP | 2023-04-29 | INPR | 2020-06-18 | COMP | Rule 15/16 | 46 | 165 | 88 | 298 |  |  | 648
2770 | 2017-11-17 | 2018-01-29 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-04 | COMP | 2019-09-10 | COMP | 2019-09-24 | COMP | 2019-12-16 | COMP | Rule 16 | 47 | 368 | 37 | 5 | 11 | 57 | 520
3831 | 2017-11-17 | 2018-08-07 | 2018-08-13 | 2018-08-13 | COMP | 2018-12-04 | COMP | 2019-11-27 | COMP | 2020-01-21 | COMP | 2020-03-02 | COMP | Rule 16 | 180 | 5 | 78 | 249 | 35 | 29 | 571
4685 | 2017-11-17 | 2018-03-13 | 2018-06-19 | 2018-06-19 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-02-25 | COMP | 2019-07-19 | COMP | Rule 16 | 77 | 70 | 99 | 1 | 73 | 103 | 418
6583 | 2017-11-17 | 2018-08-28 | 2019-01-03 | 2019-01-03 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-04-15 | COMP | 2019-08-02 | COMP | Rule 16 | 195 | 87 | 73 | 1 | 0 | 76 | 428
9307 | 2017-11-17 | 2019-01-28 | 2019-05-31 | 2019-05-31 | COMP | 2019-11-22 | COMP | 2019-12-05 | COMP | 2019-12-11 | COMP | 2020-01-10 | COMP | Rule 16 | 297 | 88 | 123 | 8 | 5 | 21 | 537
2534 | 2017-11-18 | 2017-12-16 | 2018-06-13 | 2018-06-11 | COMP | 2018-07-11 | COMP | 2018-08-16 | COMP | 2019-07-02 | COMP | 2019-07-26 | COMP | Rule 16 | 18 | 123 | 22 | 27 | 220 | 18 | 422
2769 | 2017-11-18 | 2018-01-29 | 2018-06-21 | 2018-06-21 | COMP | 2018-07-11 | COMP | 2018-12-10 | COMP | 2019-07-21 | INPR | 2019-02-28 | COMP | Rule 16 | 46 | 102 | 14 | 105 |  |  | 318
4578 | 2017-11-18 | 2018-02-05 | 2018-03-26 | 2018-03-26 | COMP | 2018-05-23 | COMP | 2018-06-05 | COMP | 2021-08-30 | COMP | 2021-10-18 | COMP | Rule 16 | 51 | 35 | 43 | 9 | 815 | 35 | 983
4604 | 2017-11-19 | 2018-02-12 | 2018-05-03 | 2018-05-03 | COMP | 2018-08-27 | COMP | 2018-11-16 | COMP | 2018-11-21 | COMP | 2019-01-03 | COMP | Rule 16 | 56 | 58 | 81 | 58 | 4 | 28 | 280
6331 | 2017-11-19 | 2018-08-11 | 2018-09-24 | 2018-09-24 | COMP | 2018-10-03 | COMP | 2018-10-29 | COMP | 2018-12-17 | COMP | 2019-01-10 | COMP | Rule 16 | 182 | 30 | 8 | 19 | 33 | 17 | 285
2589 | 2017-11-20 | 2018-01-03 | 2018-08-04 | 2018-08-04 | COMP | 2018-01-03 | NOTN | 2019-03-11 | COMP | 2019-02-11 | COMP | 2019-04-29 | COMP | Other | 29 | 149 |  | 148 | 0 | 36 | 360
2627 | 2017-11-20 | 2018-01-09 | 2019-02-22 | 2019-02-22 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-04-30 | COMP | 2019-05-28 | COMP | Rule 16 | 33 | 282 | 49 | 1 | 0 | 19 | 380
2649 | 2017-11-20 | 2018-01-12 | 2018-04-06 | 2018-09-10 | COMP | 2018-09-14 | COMP | 2018-11-14 | COMP | 2019-01-09 | COMP | 2019-03-18 | COMP | Rule 16 | 36 | 59 | 5 | 43 | 37 | 47 | 330
2658 | 2017-11-20 | 2018-01-12 | 2018-03-30 | 2018-03-30 | COMP | 2018-06-05 | COMP | 2018-12-06 | COMP | 2019-05-08 | COMP | 2019-06-07 | COMP | Rule 16 | 36 | 54 | 47 | 128 | 106 | 22 | 388
2809 | 2017-11-20 | 2018-02-02 | 2018-11-28 | 2018-10-19 | COMP | 2019-02-12 | COMP | 2019-05-08 | COMP | 2020-05-30 | INPR | 2019-06-30 | COMP | Rule 16 | 50 | 207 | 77 | 61 |  |  | 403
2810 | 2017-11-20 | 2018-02-02 | 2018-11-01 | 2018-11-01 | COMP | 2019-01-28 | COMP | 2019-03-26 | COMP | 2020-05-30 | INPR | 2020-02-07 | COMP | Rule 16 | 50 | 191 | 57 | 41 |  |  | 555
2833 | 2017-11-20 | 2018-02-06 | 2019-01-14 | 2019-01-14 | COMP | 2019-08-13 | COMP | 2019-09-16 | COMP | 2019-11-01 | COMP | 2019-11-14 | COMP | Rule 16 | 52 | 236 | 148 | 24 | 35 | 9 | 499
3120 | 2017-11-20 | 2018-03-12 | 2018-05-15 | 2018-05-15 | COMP | 2018-07-31 | COMP | 2018-08-16 | COMP | 2018-09-05 | COMP | 2019-01-08 | COMP | Rule 16 | 75 | 47 | 54 | 13 | 14 | 85 | 283
3134 | 2017-11-20 | 2018-03-12 | 2018-03-13 | 2018-03-13 | COMP | 2018-05-31 | COMP | 2018-05-31 | COMP | 2019-03-28 | COMP | 2020-06-19 | COMP | Rule 16 | 75 | 2 | 57 | 1 | 207 | 311 | 648
3651 | 2017-11-20 | 2018-06-01 | 2018-06-14 | 2018-06-14 | COMP | 2020-05-04 | COMP | 2020-05-21 | COMP | 2020-08-06 | COMP | 2020-08-12 | COMP | Rule 15/16 | 133 | 10 | 474 | 14 | 55 | 5 | 686
4570 | 2017-11-20 | 2018-02-01 | 2018-04-18 | 2018-04-18 | COMP | 2018-06-08 | COMP | 2018-06-08 | INPR | 2019-02-20 | COMP | 2019-02-23 | COMP | Rule 16 | 49 | 54 | 37 |  |  |  | 314
5147 | 2017-11-20 | 2018-05-04 | 2018-07-02 | 2018-07-02 | COMP | 2018-08-07 | COMP | 2018-12-04 | COMP | 2018-12-26 | COMP | 2019-01-22 | COMP | Rule 15/16 | 114 | 41 | 26 | 82 | 16 | 18 | 292
5332 | 2017-11-20 | 2018-05-22 | 2018-08-28 | 2018-08-28 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-07-15 | COMP | 2019-08-14 | COMP | Rule 16 | 126 | 69 | 47 | 1 | 174 | 23 | 435
6036 | 2017-11-20 | 2018-07-19 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-03-13 | COMP | 2019-04-22 | COMP | Rule 16 | 166 | 92 | 8 | 1 | 64 | 29 | 355
6985 | 2017-11-20 | 2018-09-20 | 2019-01-03 | 2019-01-03 | COMP | 2019-05-24 | COMP | 2019-05-31 | COMP | 2019-09-27 | COMP | 2019-11-04 | COMP | Rule 16 | 210 | 71 | 100 | 5 | 84 | 27 | 492
11067 | 2017-11-20 | 2019-04-12 | 2019-10-06 | 2019-10-06 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-09-09 | COMP | 2020-10-26 | COMP | Rule 15/16 | 349 | 123 | 37 | 1 | 198 | 34 | 738
2616 | 2017-11-21 | 2018-01-08 | 2019-04-08 | 2019-04-08 | COMP | 2019-09-11 | COMP | 2019-11-14 | COMP |  |  | 2019-12-26 | COMP | Rule 16 | 31 | 314 | 110 | 46 |  |  | 525
2618 | 2017-11-21 | 2018-01-08 | 2019-01-23 | 2019-01-23 | COMP | 2019-09-06 | COMP | 2019-09-20 | COMP | 2020-11-18 | COMP | 2020-10-02 | COMP | Rule 16 | 31 | 262 | 159 | 11 | 294 |  | 721
2619 | 2017-11-21 | 2018-01-08 | 2019-11-14 | 2019-11-14 | COMP | 2020-06-15 | COMP | 2020-10-06 | COMP | 2023-11-11 | INPR | 2020-11-09 | COMP | Rule 16 | 31 | 468 | 146 | 81 |  |  | 747
2620 | 2017-11-21 | 2018-01-08 | 2019-01-16 | 2019-01-16 | COMP | 2019-09-06 | COMP | 2019-09-19 | COMP | 2023-12-02 | INPR | 2020-09-30 | COMP | Rule 16 | 31 | 258 | 163 | 10 |  |  | 719
2621 | 2017-11-21 | 2018-01-08 | 2019-04-08 | 2019-04-08 | COMP | 2019-12-04 | COMP | 2019-12-10 | COMP | 2020-05-30 | COMP | 2020-01-17 | COMP | Rule 16 | 31 | 314 | 167 | 5 | 119 |  | 540
2622 | 2017-11-21 | 2018-01-08 | 2019-03-06 | 2019-03-06 | COMP | 2019-09-06 | COMP | 2019-09-19 | COMP | 2020-07-07 | COMP | 2020-10-01 | COMP | Rule 16 | 31 | 291 | 130 | 10 | 201 | 62 | 720
2626 | 2017-11-21 | 2018-01-09 | 2020-08-25 | 2020-08-25 | COMP | 2021-01-29 | COMP | 2021-02-17 | COMP | 2021-09-28 | COMP | 2021-11-09 | COMP | Rule 15/16 | 32 | 663 | 107 | 13 | 157 | 31 | 998
2807 | 2017-11-21 | 2018-02-02 | 2018-08-04 | 2018-08-04 | COMP | 2019-04-02 | COMP | 2019-04-04 | COMP | 2019-04-10 | COMP | 2019-07-10 | COMP | Rule 16 | 49 | 128 | 164 | 3 | 5 | 64 | 409
2834 | 2017-11-21 | 2018-02-06 | 2020-02-21 | 2020-02-21 | COMP | 2020-04-17 | COMP | 2020-04-23 | COMP | 2020-02-26 | COMP | 2020-06-30 | COMP | Rule 15/16 | 51 | 513 | 41 | 5 | 0 | 48 | 654
2852 | 2017-11-21 | 2018-02-08 | 2018-05-24 | 2018-05-24 | COMP | 2018-10-03 | COMP | 2019-04-03 | COMP | 2019-02-13 | COMP | 2019-06-06 | COMP | Rule 15/16 | 53 | 75 | 92 | 124 | 0 | 46 | 386
2932 | 2017-11-21 | 2018-02-20 | 2018-03-08 | 2018-03-08 | COMP | 2018-04-30 | COMP | 2019-06-13 | COMP | 2019-06-10 | COMP | 2019-07-09 | COMP | Rule 16 | 60 | 13 | 38 | 283 | 0 | 18 | 408
3083 | 2017-11-21 | 2018-03-07 | 2018-08-27 | 2021-07-15 | COMP | 2021-08-18 | COMP | 2021-08-26 | COMP | 2022-02-15 | COMP | 2022-04-05 | COMP | Rule 15/16 | 71 | 122 | 25 | 7 | 119 | 35 | 1098
3255 | 2017-11-21 | 2018-03-28 | 2018-08-17 | 2018-08-17 | COMP | 2018-09-19 | COMP | 2018-09-19 | COMP | 2018-11-06 | COMP | 2019-01-01 | COMP | Rule 16 | 86 | 101 | 23 | 1 | 35 | 36 | 277
3262 | 2017-11-21 | 2018-03-28 | 2018-09-21 | 2018-09-21 | COMP | 2019-08-12 | COMP | 2019-08-29 | COMP | 2019-08-21 | COMP | 2019-10-02 | COMP | Rule 15/16 | 86 | 125 | 223 | 14 | 0 | 24 | 468
4546 | 2017-11-21 | 2018-01-25 | 2018-04-30 | 2018-04-30 | COMP | 2019-08-23 | COMP | 2019-08-26 | COMP | 2020-02-05 | COMP | 2020-02-14 | COMP | Rule 16 | 43 | 67 | 333 | 2 | 111 | 8 | 559
4613 | 2017-11-21 | 2018-02-14 | 2018-04-12 | 2018-04-12 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2019-02-11 | COMP | 2019-03-11 | COMP | Rule 16 | 57 | 41 | 33 | 1 | 177 | 20 | 324
4648 | 2017-11-21 | 2018-02-26 | 2018-04-20 | 2018-04-20 | COMP | 2018-07-19 | COMP | 2018-07-19 | COMP | 2020-02-29 | INPR | 2019-10-14 | COMP | Rule 16 | 64 | 40 | 63 | 1 |  |  | 476
4649 | 2017-11-21 | 2018-02-26 | 2018-04-20 | 2018-04-20 | COMP | 2018-07-19 | COMP | 2018-07-19 | COMP | 2020-01-19 | INPR | 2019-10-04 | COMP | Rule 16 | 64 | 40 | 63 | 1 |  |  | 470
4945 | 2017-11-21 | 2018-04-13 | 2018-11-07 | 2018-11-07 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-08-05 | COMP | 2019-08-26 | COMP | Rule 16 | 98 | 146 | 16 | 1 | 170 | 16 | 442
5135 | 2017-11-21 | 2018-05-03 | 2018-06-30 | 2018-09-08 | COMP | 2018-09-11 | COMP | 2018-09-11 | COMP | 2018-10-04 | COMP | 2020-07-14 | COMP | Rule 16 | 112 | 41 | 2 | 1 | 18 | 446 | 664
5771 | 2017-11-21 | 2018-07-02 | 2018-09-12 | 2018-09-12 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2019-11-24 | INPR | 2019-07-23 | COMP | Rule 15/16 | 153 | 51 | 20 | 1 |  |  | 418
8434 | 2017-11-21 | 2018-12-01 | 2019-01-23 | 2019-12-04 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2022-07-16 | INPR | 2020-07-16 | COMP | Rule 16 | 257 | 35 | 45 | 1 |  |  | 666
9736 | 2017-11-21 | 2019-02-13 | 2019-04-09 | 2019-05-08 | COMP | 2019-08-06 | COMP | 2019-08-05 | COMP | 2019-09-10 | COMP | 2019-10-24 | COMP | Rule 15/16 | 307 | 39 | 63 |  | 26 | 33 | 484
10251 | 2017-11-21 | 2019-03-08 | 2019-10-08 | 2021-03-29 | COMP | 2021-04-15 | COMP | 2020-01-29 | COMP | 2020-12-11 | COMP | 2021-06-02 | COMP | Rule 15/16 | 323 | 150 | 14 |  | 222 | 119 | 886
3043 | 2017-11-22 | 2018-03-02 | 2018-04-27 | 2018-04-27 | COMP | 2019-01-08 | COMP | 2019-02-07 | COMP |  | INPR | 2020-08-26 | COMP | Rule 15/16 | 67 | 41 | 175 | 22 |  |  | 694
3154 | 2017-11-22 | 2018-03-15 | 2018-05-04 | 2018-05-04 | COMP | 2020-04-13 | COMP | 2020-04-30 | COMP |  |  | 2020-07-22 | COMP | Rule 16 | 76 | 37 | 487 | 14 |  |  | 669
3274 | 2017-11-22 | 2018-03-30 | 2018-05-03 | 2018-05-03 | COMP | 2018-05-04 | COMP | 2018-05-16 | COMP | 2019-01-07 | COMP | 2019-02-25 | COMP | Rule 16 | 87 | 25 | 2 | 9 | 161 | 34 | 313
4732 | 2017-11-22 | 2018-03-23 | 2018-06-05 | 2018-06-05 | COMP | 2018-06-11 | COMP | 2019-05-13 | COMP | 2019-04-24 | COMP | 2019-06-17 | COMP | Rule 16 | 82 | 52 | 5 | 232 | 0 | 25 | 392
4955 | 2017-11-22 | 2018-04-14 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-27 | COMP | 2018-12-21 | COMP | 2019-04-21 | INPR | 2019-01-26 | COMP | Rule 16 | 97 | 146 | 32 |  |  |  | 293
5668 | 2017-11-22 | 2018-06-25 | 2018-12-17 | 2018-12-17 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2020-05-08 | COMP | 2020-06-25 | COMP | Rule 16 | 147 | 121 | 146 | 1 | 206 | 34 | 650
6728 | 2017-11-22 | 2018-09-10 | 2019-01-14 | 2019-10-14 | COMP | 2019-12-09 | COMP | 2019-12-10 | INPR | 2020-01-09 | COMP | 2020-01-22 | COMP | Rule 16 | 200 | 86 | 38 |  |  |  | 541
7199 | 2017-11-22 | 2018-10-02 | 2018-11-24 | 2021-01-11 | COMP | 2021-03-11 | COMP | 2020-10-30 | COMP | 2021-03-11 | COMP | 2021-05-04 | COMP | Rule 16 | 216 | 36 | 42 |  | 88 | 39 | 865
8863 | 2017-11-22 | 2019-01-03 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-01-19 | COMP | 2019-03-23 | COMP | Rule 16 | 278 | 6 | 7 | 1 | 1 | 43 | 332
3040 | 2017-11-24 | 2018-03-02 | 2018-03-27 | 2018-03-27 | COMP | 2018-03-23 | COMP | 2018-05-31 | INPR | 2020-01-18 | REQD | 2019-10-03 | COMP | Rule 16 | 66 | 18 |  |  |  |  | 467
2550 | 2017-11-27 | 2017-12-21 | 2018-05-30 | 2018-05-30 | COMP | 2018-06-21 | COMP | 2018-09-04 | COMP | 2019-04-02 | COMP | 2019-05-06 | COMP | Rule 15/16 | 19 | 110 | 17 | 52 | 144 | 25 | 362
2617 | 2017-11-27 | 2018-01-08 | 2019-04-08 | 2019-04-08 | COMP | 2019-09-06 | COMP | 2019-09-19 | COMP | 2020-09-16 | COMP | 2019-11-01 | COMP | Rule 16 | 29 | 314 | 107 | 10 | 251 |  | 488
2623 | 2017-11-27 | 2018-01-08 | 2019-03-06 | 2019-03-06 | COMP | 2019-09-06 | COMP | 2019-09-20 | COMP | 2020-06-18 | COMP | 2019-11-05 | COMP | Rule 16 | 29 | 291 | 130 | 11 | 187 |  | 490
2684 | 2017-11-27 | 2018-01-18 | 2018-04-24 | 2018-04-24 | COMP | 2018-04-24 | NOTN | 2018-06-15 | COMP | 2018-06-01 | COMP | 2020-01-22 | COMP | Other | 36 | 68 |  | 38 | 0 | 401 | 540
2748 | 2017-11-27 | 2018-01-26 | 2019-11-15 | 2019-11-15 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP |  |  | 2020-01-07 | COMP | Rule 16 | 42 | 456 | 9 | 1 |  |  | 530
2865 | 2017-11-27 | 2018-02-09 | 2018-04-26 | 2019-06-24 | COMP | 2019-06-26 | COMP | 2018-09-05 | COMP | 2019-11-24 | INPR | 2019-07-02 | COMP | Rule 16 | 52 | 54 | 3 |  |  |  | 402
3011 | 2017-11-27 | 2018-02-27 | 2018-03-21 | 2018-03-21 | COMP | 2019-12-28 | COMP | 2018-04-24 | COMP | 2019-01-18 | COMP | 2019-08-21 | COMP | Rule 16 | 63 | 17 | 446 |  | 186 | 150 | 437
3082 | 2017-11-27 | 2018-03-06 | 2018-03-30 | 2018-03-30 | COMP | 2018-04-02 | NOTN | 2018-05-02 | COMP | 2018-04-02 | NOTN | 2019-05-03 | COMP | Other | 68 | 19 |  | 24 |  |  | 361
3731 | 2017-11-27 | 2018-06-19 | 2018-10-09 | 2018-08-24 | COMP | 2018-10-26 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-01-25 | COMP | Rule 16 | 142 | 79 | 45 | 36 | 1 | 25 | 292
4044 | 2017-11-27 | 2018-12-27 | 2019-03-07 | 2019-03-07 | COMP | 2019-06-07 | COMP | 2019-07-17 | COMP | 2019-11-18 | COMP | 2019-10-16 | COMP | Rule 16 | 273 | 48 | 66 | 28 | 87 |  | 476
4606 | 2017-11-27 | 2018-02-14 | 2018-04-30 | 2018-04-30 | COMP | 2018-12-17 | COMP | 2018-12-17 | INPR | 2020-01-14 | COMP | 2020-01-21 | COMP | Rule 16 | 55 | 53 | 160 |  |  |  | 539
4889 | 2017-11-27 | 2018-04-10 | 2018-09-07 | 2018-09-07 | COMP | 2018-09-08 | NOTN | 2018-09-08 | COMP | 2018-10-22 | COMP | 2019-02-25 | COMP | Other | 93 | 106 |  | 1 | 31 | 84 | 312
7006 | 2017-11-27 | 2018-09-21 | 2018-09-26 | 2018-09-26 | COMP | 2019-04-16 | COMP | 2019-04-16 | INPR | 2019-04-30 | COMP | 2019-05-16 | COMP | Rule 16 | 208 | 4 | 138 |  |  |  | 370
8169 | 2017-11-27 | 2018-11-16 | 2019-01-16 | 2019-01-16 | COMP | 2019-02-19 | COMP | 2019-03-13 | COMP | 2019-03-25 | COMP | 2019-04-20 | COMP | Rule 16 | 247 | 40 | 23 | 17 | 9 | 20 | 351
9792 | 2017-11-27 | 2019-02-15 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-03-18 | COMP | 2019-03-22 | COMP | Rule 16 | 307 | 11 | 8 | 1 | 4 | 5 | 331
2564 | 2017-11-28 | 2017-12-28 | 2018-03-30 | 2018-03-30 | COMP | 2018-10-30 | COMP | 2018-11-13 | COMP | 2019-01-04 | COMP | 2019-03-21 | COMP | Rule 16 | 22 | 64 | 150 | 10 | 35 | 53 | 329
2604 | 2017-11-28 | 2018-01-05 | 2018-03-07 | 2018-03-07 | COMP | 2018-03-13 | COMP | 2018-07-24 | COMP | 2018-11-21 | COMP | 2019-01-22 | COMP | Rule 16 | 27 | 42 | 5 | 94 | 85 | 40 | 288
2906 | 2017-11-28 | 2018-02-14 | 2018-07-09 | 2019-08-16 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2020-02-04 | COMP | 2020-04-24 | COMP | Rule 15/16 | 54 | 101 | 91 | 1 | 26 | 58 | 605
2916 | 2017-11-28 | 2018-02-15 | 2018-08-14 | 2018-08-14 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-07-29 | COMP | 2019-08-14 | COMP | Rule 16 | 55 | 126 | 177 | 1 | 64 | 13 | 431
3052 | 2017-11-28 | 2018-03-03 | 2018-08-14 | 2018-08-14 | COMP | 2018-10-09 | COMP | 2018-10-16 | COMP | 2018-11-21 | COMP | 2019-03-15 | COMP | Rule 15/16 | 65 | 115 | 40 | 6 | 26 | 77 | 325
3058 | 2017-11-28 | 2018-03-05 | 2018-08-02 | 2018-08-02 | COMP | 2018-09-27 | COMP | 2018-09-27 | COMP | 2019-02-05 | COMP | 2019-03-28 | COMP | Rule 15/16 | 66 | 107 | 40 | 1 | 88 | 37 | 334
4984 | 2017-11-28 | 2018-04-18 | 2018-07-06 | 2018-07-06 | COMP | 2018-09-07 | COMP | 2019-10-15 | COMP | 2019-11-21 | COMP | 2020-01-07 | COMP | Rule 16 | 98 | 56 | 45 | 278 | 27 | 30 | 529
5004 | 2017-11-28 | 2018-04-23 | 2018-08-16 | 2018-08-16 | COMP | 2018-09-04 | COMP | 2018-09-20 | COMP |  |  | 2019-02-08 | COMP | Rule 16 | 101 | 82 | 13 | 13 |  |  | 301
5011 | 2017-11-28 | 2018-04-24 | 2018-09-10 | 2019-01-05 | COMP | 2019-02-20 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-09-05 | COMP | Rule 16 | 102 | 97 | 31 | 107 | 1 | 33 | 446
5084 | 2017-11-28 | 2018-04-30 | 2018-09-27 | 2018-09-27 | COMP | 2020-04-22 | NOTN | 2020-04-22 | COMP | 2020-08-04 | COMP | 2020-10-20 | COMP | Other | 106 | 106 |  | 393 | 74 | 55 | 730
5402 | 2017-11-28 | 2018-05-29 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-04 | COMP | 2019-01-07 | COMP | 2019-08-30 | COMP | 2019-12-10 | COMP | Rule 16 | 126 | 97 | 35 | 23 | 166 | 69 | 511
5628 | 2017-11-28 | 2018-06-21 | 2018-11-21 | 2018-11-21 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-07-17 | COMP | 2019-08-07 | COMP | Rule 16 | 143 | 107 | 96 | 1 | 68 | 16 | 426
6122 | 2017-11-28 | 2018-07-26 | 2020-09-22 | 2020-09-22 | COMP | 2022-01-04 | COMP | 2022-08-05 | COMP | 2022-08-02 | COMP | 2022-09-23 | COMP | Rule 15/16 | 167 | 544 | 323 | 149 | 0 | 35 | 1214
6406 | 2017-11-28 | 2018-08-16 | 2018-09-04 | 2018-09-04 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-04-23 | COMP | 2019-05-30 | COMP | Rule 16 | 182 | 13 | 124 | 1 | 36 | 27 | 378
2600 | 2017-11-29 | 2018-01-05 | 2018-06-05 | 2018-06-05 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2021-04-26 | COMP | 2020-09-16 | COMP | Rule 16 | 26 | 105 | 454 | 1 | 274 |  | 705
4431 | 2017-11-29 | 2017-12-06 | 2018-03-02 | 2018-03-02 | COMP | 2018-03-20 | COMP | 2018-04-17 | COMP | 2018-04-17 | COMP | 2019-07-25 | COMP | Rule 16 | 6 | 59 | 13 | 21 | 1 | 321 | 416
4850 | 2017-11-29 | 2018-04-05 | 2018-07-10 | 2018-07-10 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2021-06-15 | COMP | 2021-07-28 | COMP | Rule 16 | 88 | 67 | 84 | 1 | 655 | 31 | 921
5403 | 2017-11-29 | 2018-05-29 | 2018-06-02 | 2018-06-02 | COMP | 2018-07-03 | COMP | 2018-07-03 | COMP | 2019-04-21 | INPR | 2019-01-29 | COMP | Rule 16 | 125 | 4 | 22 | 1 |  |  | 292
6001 | 2017-11-29 | 2018-07-18 | 2018-09-07 | 2018-09-07 | COMP | 2018-11-08 | COMP | 2019-04-18 | COMP | 2019-03-05 | COMP | 2019-09-06 | COMP | Rule 16 | 160 | 37 | 45 | 109 | 0 | 99 | 446
6059 | 2017-11-29 | 2018-07-23 | 2018-09-11 | 2018-11-30 | COMP | 2018-12-27 | COMP | 2019-01-03 | INPR | 2018-12-04 | COMP | 2019-01-23 | COMP | Rule 16 | 163 | 36 | 19 |  |  |  | 288
39176 | 2017-11-29 | 2022-10-05 | 2023-01-20 | 2023-01-20 | COMP | 2023-03-22 | NOTN | 2023-06-22 | COMP |  | INPR | 2023-06-26 | COMP | Other | 1221 | 72 |  | 107 |  |  | 1400
2503 | 2017-11-30 | 2017-12-11 | 2018-07-11 | 2018-07-11 | COMP | 2018-07-11 | COMP | 2018-07-16 | COMP | 2020-08-18 | COMP | 2020-09-22 | COMP | Rule 16 | 8 | 147 | 1 | 4 | 528 | 25 | 708
2609 | 2017-11-30 | 2018-01-08 | 2018-04-11 | 2018-04-06 | COMP | 2018-06-18 | COMP | 2018-06-18 | COMP | 2019-03-01 | COMP | 2019-04-03 | COMP | Rule 15/16 | 26 | 66 | 51 | 1 | 176 | 24 | 336
2882 | 2017-11-30 | 2018-02-12 | 2018-06-26 | 2018-06-26 | COMP | 2018-09-18 | COMP | 2020-02-25 | COMP | 2020-04-07 | COMP | 2020-04-24 | COMP | Rule 15/16 | 50 | 95 | 59 | 359 | 31 | 14 | 603
3132 | 2017-11-30 | 2018-03-12 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-26 | COMP | 2019-03-12 | COMP | 2019-02-12 | COMP | 2019-04-16 | COMP | Rule 16 | 69 | 178 | 24 | 52 | 0 | 26 | 345
4463 | 2017-11-30 | 2017-12-20 | 2018-01-29 | 2018-01-29 | COMP | 2018-05-21 | COMP | 2018-05-21 | COMP | 2019-06-21 | COMP | 2019-07-08 | COMP | Rule 16 | 15 | 26 | 80 | 1 | 274 | 11 | 402
4901 | 2017-11-30 | 2018-04-12 | 2018-08-23 | 2018-08-23 | COMP | 2018-09-25 | COMP | 2018-09-25 | COMP | 2018-11-08 | COMP | 2019-02-01 | COMP | Rule 15/16 | 92 | 94 | 23 | 1 | 33 | 56 | 294
5341 | 2017-11-30 | 2018-05-25 | 2018-08-19 | 2018-08-19 | COMP | 2018-09-04 | COMP | 2019-12-04 | COMP | 2020-03-23 | COMP | 2020-06-17 | COMP | Rule 16 | 123 | 59 | 11 | 314 | 75 | 62 | 640
15098 | 2017-11-30 | 2019-10-12 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-06-18 | COMP | 2020-06-22 | COMP | Other | 470 | 87 | 8 | 1 | 78 | 3 | 643
2452 | 2017-12-01 | 2017-12-02 | 2017-12-11 | 2018-11-29 | COMP | 2018-12-27 | COMP | 2019-09-03 | COMP | 2023-12-02 | INPR | 2019-12-11 | COMP | Rule 15/16 | 1 | 6 | 20 | 173 |  |  | 509
2764 | 2017-12-01 | 2018-01-29 | 2018-04-18 | 2018-04-18 | COMP | 2018-06-19 | COMP | 2018-06-19 | COMP | 2019-03-05 | COMP | 2019-04-19 | COMP | Rule 16 | 39 | 57 | 44 | 1 | 177 | 34 | 347
2955 | 2017-12-01 | 2018-02-22 | 2018-04-02 | 2018-04-02 | COMP | 2018-04-30 | COMP | 2018-04-30 | COMP | 2020-11-03 | COMP | 2020-12-14 | COMP | Rule 16 | 56 | 28 | 21 | 1 | 635 | 27 | 763
3029 | 2017-12-01 | 2018-02-28 | 2018-05-10 | 2018-05-10 | COMP | 2019-05-08 | COMP | 2019-05-08 | NOTN | 2019-05-21 | COMP | 2019-05-30 | COMP | Rule 16 | 60 | 52 | 250 |  |  |  | 375
3952 | 2017-12-01 | 2018-10-26 | 2019-01-30 | 2019-01-30 | COMP | 2019-04-17 | COMP | 2019-04-29 | COMP | 2019-05-29 | COMP | 2019-07-24 | COMP | Rule 15/16 | 229 | 63 | 55 | 9 | 22 | 40 | 413
4531 | 2017-12-01 | 2018-01-22 | 2018-06-21 | 2018-06-21 | COMP | 2018-10-30 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2019-01-16 | COMP | Rule 16 | 34 | 107 | 92 | 17 | 1 | 36 | 282
4567 | 2017-12-01 | 2018-01-31 | 2018-04-26 | 2018-06-22 | COMP | 2018-08-08 | COMP | 2018-08-08 | COMP | 2019-01-24 | COMP | 2019-02-28 | COMP | Rule 16 | 41 | 61 | 33 | 1 | 115 | 25 | 311
4766 | 2017-12-01 | 2018-03-30 | 2018-05-10 | 2018-05-10 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2019-01-16 | COMP | 2019-01-30 | COMP | Rule 16 | 82 | 30 | 13 | 1 | 160 | 10 | 291
4869 | 2017-12-01 | 2018-04-05 | 2018-05-16 | 2018-10-08 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2020-08-20 | COMP | 2021-02-27 | COMP | Rule 15/16 | 86 | 30 | 39 | 1 | 433 | 129 | 813
8553 | 2017-12-01 | 2018-12-08 | 2019-04-16 | 2019-04-19 | COMP | 2020-02-11 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-08-20 | COMP | Rule 16 | 256 | 88 | 204 | 48 | 1 | 89 | 685
11494 | 2017-12-01 | 2019-04-29 | 2019-06-07 | 2019-06-07 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | Rule 16 | 353 | 29 | 46 | 1 | 18 | 1 | 443
12398 | 2017-12-01 | 2019-06-04 | 2019-10-15 | 2019-10-15 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2021-09-22 | COMP | 2021-11-04 | COMP | Rule 15/16 | 378 | 94 | 64 | 1 | 425 | 32 | 989
20541 | 2017-12-01 | 2020-06-25 | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | NOTN | 2020-08-25 | COMP | 2020-08-24 | COMP | 2020-09-16 | COMP | Other | 645 | 1 |  | 44 | 0 | 16 | 703
2517 | 2017-12-04 | 2017-12-13 | 2018-04-04 | 2018-09-25 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-02-12 | COMP | 2019-03-26 | COMP | Rule 16 | 8 | 77 | 93 | 1 | 3 | 30 | 328
2573 | 2017-12-04 | 2017-12-28 | 2018-04-16 | 2018-04-16 | COMP | 2018-10-02 | COMP | 2018-10-02 | COMP | 2019-12-17 | COMP | 2020-01-06 | COMP | Rule 16 | 18 | 75 | 119 | 1 | 303 | 13 | 524
2625 | 2017-12-04 | 2018-01-08 | 2018-04-02 | 2018-04-02 | COMP | 2019-01-08 | COMP | 2019-01-15 | COMP | 2020-08-04 | COMP | 2020-08-21 | COMP | Other | 24 | 59 | 194 | 6 | 393 | 14 | 685
2699 | 2017-12-04 | 2018-01-19 | 2019-03-11 | 2019-03-11 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-06-07 | COMP | 2019-07-18 | COMP | Rule 16 | 32 | 286 | 62 | 1 | 3 | 29 | 408
2929 | 2017-12-04 | 2018-02-17 | 2018-08-08 | 2019-09-19 | COMP | 2019-11-07 | COMP | 2020-08-14 | COMP | 2020-08-20 | COMP | 2021-04-24 | COMP | Rule 15/16 | 52 | 120 | 36 | 194 | 5 | 169 | 852
3072 | 2017-12-04 | 2018-03-06 | 2018-06-23 | 2018-06-23 | COMP | 2018-08-15 | COMP | 2018-08-15 | COMP | 2019-01-23 | COMP | 2019-03-25 | COMP | Rule 16 | 63 | 78 | 37 | 1 | 109 | 43 | 327
3479 | 2017-12-04 | 2018-05-03 | 2018-07-27 | 2018-07-27 | COMP | 2018-11-09 | COMP | 2019-01-07 | COMP | 2019-03-12 | COMP | 2019-04-02 | COMP | Rule 16 | 105 | 60 | 75 | 37 | 45 | 16 | 333
3543 | 2017-12-04 | 2018-05-14 | 2018-08-03 | 2018-08-03 | COMP | 2018-11-06 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2019-01-04 | COMP | Rule 15/16 | 112 | 58 | 67 | 8 | 1 | 32 | 273
4594 | 2017-12-04 | 2018-02-09 | 2018-05-03 | 2019-07-25 | COMP | 2019-08-19 | COMP | 2019-08-07 | COMP | 2019-08-28 | COMP | 2019-09-25 | COMP | Rule 16 | 47 | 59 | 18 |  | 16 | 20 | 456
4597 | 2017-12-04 | 2018-02-11 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-05 | COMP | 2018-12-14 | COMP | 2018-12-13 | COMP | 2019-02-07 | COMP | Rule 16 | 47 | 192 | 15 | 8 | 0 | 37 | 296
4904 | 2017-12-04 | 2018-04-11 | 2018-08-24 | 2018-08-24 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-10-21 | INPR | 2019-02-20 | COMP | Rule 15/16 | 89 | 96 | 62 | 1 |  |  | 304
4990 | 2017-12-04 | 2018-04-19 | 2018-10-01 | 2018-10-01 | COMP | 2018-11-07 | NOTN | 2018-11-07 | COMP | 2018-12-19 | COMP | 2019-03-07 | COMP | Other | 95 | 115 |  | 28 | 28 | 53 | 315
5797 | 2017-12-04 | 2018-07-03 | 2018-12-16 | 2018-12-16 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2020-08-10 | COMP | 2020-09-25 | COMP | Rule 16 | 147 | 114 | 186 | 1 | 231 | 34 | 709
5871 | 2017-12-04 | 2018-07-09 | 2018-12-27 | 2018-12-27 | COMP | 2020-12-31 | COMP | 2020-12-31 | COMP | 2021-01-05 | COMP | 2021-03-15 | COMP | Rule 16 | 150 | 119 | 507 | 1 | 3 | 48 | 823
6593 | 2017-12-04 | 2018-08-29 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-24 | COMP | 2018-12-24 | COMP | 2019-02-11 | COMP | 2019-03-23 | COMP | Rule 16 | 187 | 32 | 49 | 1 | 33 | 29 | 326
3078 | 2017-12-05 | 2018-03-06 | 2018-06-03 | 2018-06-03 | COMP | 2019-02-28 | COMP | 2019-08-20 | COMP | 2020-03-03 | COMP | 2020-04-02 | COMP | Rule 16 | 62 | 63 | 185 | 122 | 133 | 23 | 584
3230 | 2017-12-05 | 2018-03-26 | 2019-03-18 | 2019-03-18 | COMP | 2020-01-09 | COMP |  | REQD | 2021-05-12 | COMP | 2021-06-16 | COMP | Rule 15/16 | 76 | 246 | 206 |  |  |  | 888
3533 | 2017-12-05 | 2018-05-11 | 2018-09-10 | 2018-09-10 | COMP | 2018-12-26 | COMP | 2019-02-08 | COMP | 2019-06-28 | COMP | 2019-07-23 | COMP | Rule 15/16 | 110 | 84 | 74 | 31 | 99 | 17 | 410
3722 | 2017-12-05 | 2018-06-18 | 2018-08-24 | 2018-08-24 | COMP | 2018-10-05 | COMP | 2018-10-30 | COMP | 2019-02-05 | COMP | 2019-02-21 | COMP | Rule 16 | 135 | 49 | 30 | 18 | 65 | 12 | 304
4575 | 2017-12-05 | 2018-02-05 | 2018-10-04 | 2018-10-04 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-03-22 | COMP | 2019-07-09 | COMP | Rule 16 | 42 | 170 | 34 | 1 | 82 | 76 | 400
4774 | 2017-12-05 | 2018-03-29 | 2018-06-25 | 2018-06-25 | COMP | 2018-10-02 | COMP | 2018-10-02 | COMP | 2019-09-01 | INPR | 2019-05-08 | COMP | Rule 16 | 79 | 62 | 70 | 1 |  |  | 358
4946 | 2017-12-05 | 2018-04-13 | 2018-10-01 | 2018-10-01 | COMP | 2018-12-12 | COMP | 2019-01-30 | COMP | 2019-10-07 | COMP | 2019-10-24 | COMP | Rule 16 | 90 | 119 | 50 | 33 | 175 | 14 | 476
4966 | 2017-12-05 | 2018-04-16 | 2020-03-02 | 2020-06-11 | COMP | 2020-06-29 | COMP | 2020-07-22 | COMP | 2020-09-23 | COMP | 2020-12-06 | COMP | Rule 16 | 91 | 471 | 13 | 18 | 45 | 50 | 755
8194 | 2017-12-05 | 2018-11-17 | 2018-12-10 | 2019-01-31 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-06-06 | COMP | 2019-07-09 | COMP | Rule 16 | 241 | 14 |  | 1 | 104 | 23 | 400
10123 | 2017-12-05 | 2019-03-05 | 2020-03-27 | 2020-03-27 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2022-04-26 | COMP | 2021-03-09 | COMP | Rule 15/16 | 312 | 269 | 12 | 1 | 515 |  | 818
2478 | 2017-12-06 | 2017-12-06 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-01-30 | COMP | 2019-03-07 | COMP | Rule 16 | 1 | 274 | 13 | 1 | 3 | 26 | 313
2632 | 2017-12-06 | 2018-01-10 | 2018-06-13 | 2018-06-13 | COMP | 2018-06-18 | COMP | 2018-07-03 | COMP | 2019-03-12 | COMP | 2019-06-21 | COMP | Rule 16 | 24 | 108 | 4 | 12 | 172 | 73 | 388
2926 | 2017-12-06 | 2018-02-17 | 2018-08-15 | 2019-01-02 | COMP | 2019-01-23 | COMP | 2019-01-30 | COMP | 2020-05-26 | COMP | 2020-06-03 | COMP | Rule 16 | 50 | 125 | 15 | 6 | 333 | 7 | 626
3162 | 2017-12-06 | 2018-03-15 | 2018-05-28 | 2018-05-28 | COMP | 2018-10-03 | COMP | 2018-10-03 | COMP | 2019-02-06 | COMP | 2019-04-03 | COMP | Rule 16 | 68 | 52 | 90 | 1 | 85 | 40 | 332
3189 | 2017-12-06 | 2018-03-20 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-02 | NOTN | 2020-09-25 | COMP | 2020-06-17 | COMP | 2021-01-11 | COMP | Other | 71 | 161 |  | 477 | 0 | 72 | 778
3586 | 2017-12-06 | 2018-05-22 | 2018-06-03 | 2018-06-03 | COMP | 2018-12-11 | COMP | 2019-01-28 | COMP | 2019-01-16 | COMP | 2019-03-01 | COMP | Rule 16 | 116 | 8 | 132 | 32 | 0 | 24 | 309
4688 | 2017-12-06 | 2018-03-13 | 2018-09-07 | 2018-09-07 | COMP | 2018-10-15 | COMP | 2018-11-26 | COMP | 2019-04-09 | COMP | 2019-06-26 | COMP | Rule 16 | 66 | 126 | 27 | 28 | 93 | 56 | 391
4696 | 2017-12-06 | 2018-03-14 | 2018-08-13 | 2018-08-13 | COMP | 2018-08-27 | COMP | 2019-01-07 | COMP | 2019-02-16 | COMP | 2019-04-16 | COMP | Rule 15/16 | 67 | 107 | 11 | 90 | 29 | 41 | 341
4985 | 2017-12-06 | 2018-04-18 | 2018-10-25 | 2018-10-25 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-02-27 | COMP | 2019-03-21 | COMP | Rule 16 | 92 | 134 | 69 | 1 | 15 | 17 | 323
7949 | 2017-12-06 | 2018-11-08 | 2019-03-04 | 2020-03-20 | COMP | 2020-06-29 | COMP | 2020-09-02 | COMP | 2021-05-14 | COMP | 2021-05-19 | COMP | Rule 16 | 235 | 76 | 71 | 48 | 175 | 4 | 868
8049 | 2017-12-06 | 2018-11-13 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-23 | COMP | 2019-05-01 | COMP | 2023-04-30 | INPR | 2019-07-31 | COMP | Rule 15/16 | 237 | 76 | 35 | 7 |  |  | 415
10031 | 2017-12-06 | 2019-02-27 | 2019-05-03 | 2019-05-03 | COMP | 2020-02-03 | COMP | 2019-10-11 | COMP | 2020-03-16 | COMP | 2020-05-03 | COMP | Rule 16 | 307 | 48 | 188 |  | 105 | 35 | 604
11005 | 2017-12-06 | 2019-04-08 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-11-05 | COMP | Rule 16 | 335 | 112 | 13 | 1 | 1 | 25 | 483
18374 | 2017-12-06 | 2020-03-21 | 2020-06-11 | 2020-06-11 | COMP | 2020-09-18 | COMP | 2020-10-21 | COMP | 2020-11-10 | COMP | 2020-12-31 | COMP | Rule 16 | 574 | 58 | 71 | 24 | 15 | 34 | 772
2493 | 2017-12-07 | 2017-12-09 | 2018-05-29 | 2018-05-29 | COMP | 2019-02-27 | COMP | 2019-02-27 | COMP | 2019-03-13 | COMP | 2019-04-09 | COMP | Rule 15/16 | 2 | 117 | 188 | 1 | 11 | 20 | 335
2575 | 2017-12-07 | 2017-12-29 | 2018-03-13 | 2018-03-13 | COMP | 2018-08-01 | COMP | 2018-08-01 | COMP | 2020-02-26 | COMP | 2020-02-21 | COMP | Other | 16 | 50 | 100 | 1 | 393 |  | 553
2704 | 2017-12-07 | 2018-01-23 | 2018-05-23 | 2020-02-19 | COMP | 2020-10-08 | COMP | 2021-01-07 | INPR | 2021-02-17 | COMP | 2021-03-29 | COMP | Rule 16 | 31 | 86 | 165 |  |  |  | 830
2753 | 2017-12-07 | 2018-01-26 | 2019-05-31 | 2019-05-31 | COMP | 2020-09-18 | COMP | 2020-10-15 | COMP | 2022-08-02 | COMP | 2021-04-21 | COMP | Rule 16 | 34 | 339 | 330 | 20 | 451 |  | 847
2788 | 2017-12-07 | 2018-01-31 | 2018-10-24 | 2018-10-24 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2022-03-19 | INPR | 2021-03-05 | COMP | Rule 16 | 37 | 187 | 55 | 1 |  |  | 814
2796 | 2017-12-07 | 2018-02-01 | 2018-04-17 | 2018-04-17 | COMP | 2018-05-10 | COMP | 2018-05-10 | COMP | 2019-04-10 | COMP | 2021-01-25 | COMP | Other | 38 | 53 | 18 | 1 | 230 | 451 | 786
2918 | 2017-12-07 | 2018-02-16 | 2018-06-05 | 2018-06-05 | COMP | 2018-07-02 | COMP | 2018-11-08 | COMP | 2018-11-16 | COMP | 2019-02-06 | COMP | Rule 16 | 49 | 76 | 20 | 92 | 6 | 54 | 292
2947 | 2017-12-07 | 2018-02-23 | 2018-05-23 | 2018-05-23 | COMP | 2019-05-30 | COMP | 2019-06-04 | COMP | 2019-06-10 | COMP | 2019-08-09 | COMP | Rule 16 | 53 | 64 | 256 | 4 | 5 | 44 | 421
3462 | 2017-12-07 | 2018-05-01 | 2018-07-03 | 2019-02-19 | COMP | 2018-08-29 | COMP | 2018-08-29 | COMP | 2019-01-12 | COMP | 2019-12-04 | COMP | Rule 16 | 100 | 45 |  | 1 | 92 | 225 | 500
3657 | 2017-12-07 | 2018-06-05 | 2018-09-04 | 2018-09-04 | COMP | 2019-07-22 | COMP | 2019-12-03 | COMP | 2023-11-11 | INPR | 2021-05-06 | COMP | Rule 15/16 | 124 | 64 | 221 | 93 |  |  | 858
4493 | 2017-12-07 | 2018-01-09 | 2018-03-22 | 2018-03-22 | COMP | 2018-05-10 | COMP | 2018-05-10 | COMP | 2019-10-21 | INPR | 2019-05-30 | COMP | Rule 16 | 22 | 51 | 36 | 1 |  |  | 371
6323 | 2017-12-07 | 2018-08-10 | 2018-09-25 | 2018-09-25 | COMP | 2018-11-28 | COMP | 2018-12-03 | COMP | 2018-09-04 | COMP | 2019-03-08 | COMP | Rule 16 | 171 | 32 | 44 | 4 | 0 | 66 | 313
2495 | 2017-12-08 | 2017-12-08 | 2017-12-09 | 2017-12-09 | COMP | 2017-12-15 | COMP | 2017-12-15 | COMP | 2019-12-28 | INPR | 2019-08-20 | COMP | Rule 16 | 1 | 1 | 5 | 1 |  |  | 427
2693 | 2017-12-08 | 2018-01-19 | 2018-06-26 | 2018-06-26 | COMP | 2018-06-26 | NOTN | 2018-07-02 | COMP | 2018-10-30 | COMP | 2019-01-04 | COMP | Other | 28 | 111 |  | 5 | 85 | 44 | 269
2781 | 2017-12-08 | 2018-01-31 | 2018-04-05 | 2018-04-05 | COMP | 2018-04-25 | COMP | 2018-04-25 | COMP |  |  | 2019-01-12 | COMP | Rule 15/16 | 36 | 46 | 15 | 1 |  |  | 274
4439 | 2017-12-08 | 2017-12-14 | 2018-09-07 | 2018-09-07 | COMP | 2018-11-26 | COMP | 2019-03-08 | COMP | 2020-10-24 | INPR | 2019-09-30 | COMP | Rule 16 | 5 | 185 | 54 | 71 |  |  | 455
4541 | 2017-12-08 | 2018-01-25 | 2018-03-30 | 2018-03-30 | COMP | 2018-05-15 | COMP | 2018-05-16 | COMP | 2018-09-05 | COMP | 2021-09-29 | COMP | Rule 16 | 32 | 46 | 33 | 2 | 78 | 772 | 958
4586 | 2017-12-08 | 2018-02-06 | 2018-05-09 | 2018-05-23 | COMP | 2018-06-22 | COMP | 2018-12-12 | COMP | 2019-03-12 | COMP | 2019-04-08 | COMP | Rule 16 | 40 | 66 | 22 | 119 | 61 | 20 | 333
6566 | 2017-12-08 | 2018-08-27 | 2018-09-13 | 2018-09-13 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | Rule 16 | 181 | 13 | 99 | 1 | 150 | 1 | 440
6957 | 2017-12-08 | 2018-09-19 | 2019-03-14 | 2019-03-14 | COMP | 2019-04-11 | COMP | 2019-05-17 | COMP | 2019-05-21 | COMP | 2019-07-10 | COMP | Rule 16 | 197 | 120 | 21 | 27 | 3 | 35 | 398
7038 | 2017-12-08 | 2018-09-24 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-02 | COMP | 2019-04-30 | COMP | 2019-05-08 | COMP | 2019-07-18 | COMP | Rule 15/16 | 200 | 102 | 29 | 21 | 7 | 50 | 404
16381 | 2017-12-08 | 2019-12-23 | 2020-02-06 | 2020-02-06 | COMP | 2020-03-12 | COMP | 2020-03-16 | COMP | 2020-03-24 | COMP | 2020-04-17 | COMP | Rule 16 | 512 | 31 | 25 | 3 | 7 | 19 | 592
2777 | 2017-12-09 | 2018-01-31 | 2018-03-26 | 2018-03-26 | COMP | 2018-04-06 | COMP | 2018-04-06 | COMP |  |  | 2019-01-14 | COMP | Rule 15/16 | 35 | 38 | 10 | 1 |  |  | 274
6299 | 2017-12-10 | 2018-08-09 | 2019-03-06 | 2019-10-09 | COMP | 2019-11-05 | COMP | 2019-03-27 | COMP | 2019-10-14 | COMP | 2021-06-07 | COMP | Rule 16 | 168 | 142 | 20 |  | 141 | 414 | 877
11301 | 2017-12-10 | 2019-04-22 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-08-12 | COMP | 2019-08-23 | COMP | Rule 16 | 342 | 58 | 3 | 1 | 20 | 10 | 429
2671 | 2017-12-11 | 2018-01-17 | 2018-03-03 | 2018-03-03 | COMP | 2018-04-09 | COMP | 2018-04-10 | COMP | 2019-07-21 | INPR | 2019-03-26 | COMP | Rule 16 | 25 | 32 | 26 | 2 |  |  | 323
2694 | 2017-12-11 | 2018-01-19 | 2018-06-25 | 2018-06-25 | COMP | 2018-12-07 | NOTN | 2018-12-07 | COMP | 2018-12-13 | COMP | 2019-03-12 | COMP | Other | 27 | 110 |  | 115 | 5 | 60 | 313
2718 | 2017-12-11 | 2018-01-23 | 2018-06-25 | 2018-06-25 | COMP | 2019-06-06 | COMP | 2019-07-09 | COMP |  |  | 2019-08-02 | COMP | Rule 16 | 29 | 108 | 239 | 23 |  |  | 414
2757 | 2017-12-11 | 2018-01-29 | 2018-03-30 | 2018-03-30 | COMP | 2018-04-03 | COMP | 2018-09-24 | COMP | 2019-07-21 | INPR | 2019-04-08 | COMP | Rule 16 | 33 | 44 | 3 | 122 |  |  | 332
2771 | 2017-12-11 | 2018-01-29 | 2018-05-03 | 2018-05-03 | COMP | 2020-07-21 | COMP | 2020-08-24 | COMP | 2020-08-23 | COMP | 2020-12-10 | COMP | Rule 15/16 | 33 | 68 | 558 | 25 | 0 | 75 | 755
2778 | 2017-12-11 | 2018-01-31 | 2018-03-23 | 2018-03-23 | COMP | 2018-04-05 | COMP | 2018-08-08 | COMP |  |  | 2019-01-14 | COMP | Rule 16 | 35 | 37 | 10 | 88 |  |  | 274
2779 | 2017-12-11 | 2018-01-31 | 2018-03-30 | 2018-03-30 | COMP | 2018-04-11 | COMP | 2018-04-11 | COMP |  |  | 2019-09-30 | COMP | Rule 15/16 | 35 | 42 | 9 | 1 |  |  | 454
2780 | 2017-12-11 | 2018-01-31 | 2018-03-30 | 2018-03-30 | COMP | 2018-04-06 | COMP | 2018-04-06 | COMP |  |  | 2019-01-08 | COMP | Rule 16 | 35 | 42 | 6 | 1 |  |  | 270
2790 | 2017-12-11 | 2018-01-31 | 2018-04-26 | 2018-04-26 | COMP | 2018-05-04 | COMP | 2018-08-08 | COMP |  |  | 2019-08-16 | COMP | Rule 15/16 | 35 | 61 | 7 | 67 |  |  | 424
2791 | 2017-12-11 | 2018-01-31 | 2018-04-06 | 2018-04-06 | COMP | 2018-04-19 | COMP | 2018-08-08 | COMP |  |  | 2019-02-25 | COMP | Rule 16 | 35 | 47 | 10 | 78 |  |  | 302
2792 | 2017-12-11 | 2018-01-31 | 2018-06-11 | 2018-06-11 | COMP | 2018-07-10 | COMP | 2020-12-21 | COMP |  |  | 2021-02-10 | COMP | Rule 16 | 35 | 92 | 21 | 617 |  |  | 796
2793 | 2017-12-11 | 2018-01-31 | 2018-06-11 | 2018-06-11 | COMP | 2018-07-12 | COMP | 2018-07-12 | COMP |  |  | 2019-02-26 | COMP | Rule 16 | 35 | 92 | 23 | 1 |  |  | 303
2967 | 2017-12-11 | 2018-02-23 | 2018-06-21 | 2018-06-21 | COMP | 2018-09-28 | COMP | 2018-09-28 | COMP | 2019-11-23 | INPR | 2019-04-26 | COMP | Rule 16 | 51 | 84 | 70 | 1 |  |  | 346
2970 | 2017-12-11 | 2018-02-23 | 2018-10-17 | 2020-10-13 | COMP | 2020-10-27 | COMP | 2020-10-27 | COMP | 2020-12-01 | COMP | 2021-02-04 | COMP | Rule 15/16 | 51 | 166 | 11 | 1 | 23 | 45 | 792
2971 | 2017-12-11 | 2018-02-23 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-08 | COMP | 2019-03-19 | COMP | 2020-03-04 | COMP | 2020-04-24 | COMP | Rule 16 | 51 | 159 | 24 | 87 | 242 | 38 | 596
2972 | 2017-12-11 | 2018-02-23 | 2018-07-27 | 2018-07-27 | COMP | 2018-09-12 | COMP | 2018-12-11 | COMP | 2019-12-28 | INPR | 2019-05-06 | COMP | Rule 16 | 51 | 109 | 33 | 62 |  |  | 352
2973 | 2017-12-11 | 2018-02-23 | 2018-07-23 | 2018-07-23 | COMP | 2018-09-12 | COMP | 2019-02-12 | COMP | 2022-07-30 | INPR | 2020-04-23 | COMP | Rule 16 | 51 | 105 | 37 | 104 |  |  | 595
3654 | 2017-12-11 | 2018-06-04 | 2018-07-28 | 2019-04-26 | COMP | 2019-06-27 | COMP | 2023-02-25 | REQD | 2023-02-25 | REQD | 2019-06-24 | COMP | Rule 16 | 121 | 39 | 44 |  |  |  | 386
4503 | 2017-12-11 | 2018-01-12 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2018-11-14 | COMP | 2019-04-11 | COMP | Rule 16 | 23 | 236 | 35 | 1 | 0 | 44 | 335
4592 | 2017-12-11 | 2018-02-09 | 2018-03-29 | 2018-03-29 | COMP | 2018-04-05 | COMP | 2018-04-05 | COMP | 2021-02-25 | COMP | 2023-02-13 | COMP | Rule 16 | 42 | 34 | 6 | 1 | 727 | 495 | 1300
4612 | 2017-12-11 | 2018-02-14 | 2018-06-11 | 2019-01-11 | COMP | 2019-02-14 | COMP | 2019-02-25 | COMP | 2019-03-22 | COMP | 2019-05-08 | COMP | Rule 15/16 | 45 | 82 | 24 | 7 | 20 | 34 | 354
4634 | 2017-12-11 | 2018-02-21 | 2018-04-30 | 2018-04-30 | COMP | 2018-05-18 | COMP | 2018-05-18 | COMP | 2020-01-22 | COMP | 2020-02-21 | COMP | Rule 15/16 | 49 | 49 | 15 | 1 | 420 | 22 | 551
4717 | 2017-12-11 | 2018-03-21 | 2018-12-31 | 2018-12-31 | COMP | 2019-01-23 | COMP | 2019-06-12 | COMP | 2019-05-14 | COMP | 2019-07-15 | COMP | Rule 16 | 69 | 197 | 16 | 99 | 0 | 23 | 400
5355 | 2017-12-11 | 2018-05-23 | 2018-08-04 | 2018-08-04 | COMP | 2018-12-21 | COMP | 2019-01-09 | COMP | 2019-01-22 | COMP | 2019-03-21 | COMP | Rule 16 | 114 | 51 | 96 | 12 | 9 | 42 | 320
5450 | 2017-12-11 | 2018-05-31 | 2018-09-15 | 2018-11-04 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-05-30 | COMP | 2019-06-26 | COMP | Rule 16 | 119 | 75 | 10 | 1 | 132 | 20 | 388
5526 | 2017-12-11 | 2018-06-07 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-08 | COMP | 2019-05-13 | COMP | 2021-03-27 | INPR | 2020-03-02 | COMP | Rule 16 | 124 | 148 | 22 | 66 |  |  | 557
5846 | 2017-12-11 | 2018-07-07 | 2018-09-23 | 2019-02-08 | COMP | 2019-02-14 | COMP | 2019-01-26 | COMP | 2019-04-23 | COMP | 2019-06-26 | COMP | Rule 16 | 144 | 54 | 5 |  | 61 | 46 | 388
6436 | 2017-12-11 | 2018-08-18 | 2019-02-11 | 2019-02-27 | COMP | 2019-03-25 | COMP | 2019-04-12 | COMP | 2019-04-11 | COMP | 2019-09-05 | COMP | Rule 15/16 | 174 | 119 | 19 | 15 | 0 | 102 | 437
6591 | 2017-12-11 | 2018-08-29 | 2018-11-10 | 2018-11-10 | COMP | 2019-01-03 | COMP | 2019-01-10 | COMP | 2019-07-08 | COMP | 2019-08-21 | COMP | Rule 16 | 182 | 52 | 34 | 6 | 124 | 33 | 427
7088 | 2017-12-11 | 2018-09-26 | 2019-01-02 | 2019-02-27 | COMP | 2019-03-25 | COMP | 2019-04-12 | COMP | 2019-04-26 | COMP | 2019-08-28 | COMP | Rule 15/16 | 201 | 66 | 19 | 15 | 11 | 87 | 432
11016 | 2017-12-11 | 2019-04-09 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-20 | NOTN | 2019-09-04 | COMP | 2019-06-20 | COMP | 2020-02-03 | COMP | Other | 333 | 51 |  | 54 | 0 | 103 | 538
2507 | 2017-12-12 | 2017-12-12 | 2018-08-22 | 2018-08-22 | COMP | 2018-08-22 | NOTN | 2020-02-26 | COMP | 2020-02-21 | COMP | 2020-06-08 | COMP | Other | 1 | 176 |  | 378 | 0 | 73 | 625
2516 | 2017-12-12 | 2017-12-12 | 2018-02-07 | 2018-02-07 | COMP | 2018-07-12 | COMP | 2018-08-03 | NOTN | 2019-03-15 | COMP | 2019-03-28 | COMP | Rule 15/16 | 1 | 39 | 109 |  |  |  | 324
2546 | 2017-12-12 | 2017-12-21 | 2018-04-07 | 2018-04-07 | COMP | 2018-12-12 | COMP | 2018-12-20 | COMP | 2019-01-14 | COMP | 2019-03-19 | COMP | Rule 16 | 8 | 73 | 172 | 7 | 16 | 45 | 317
2713 | 2017-12-12 | 2018-01-23 | 2018-05-10 | 2018-05-10 | COMP | 2019-02-25 | COMP | 2019-10-21 | COMP | 2019-12-03 | COMP | 2020-01-28 | COMP | Rule 15/16 | 28 | 77 | 198 | 168 | 29 | 38 | 533
2835 | 2017-12-12 | 2018-02-06 | 2018-04-04 | 2018-04-04 | COMP | 2018-06-28 | COMP | 2019-02-11 | COMP | 2020-06-08 | COMP | 2020-08-25 | COMP | Rule 15/16 | 38 | 41 | 61 | 155 | 334 | 57 | 681
2898 | 2017-12-12 | 2018-02-14 | 2018-08-27 | 2018-08-27 | COMP | 2019-01-08 | COMP | 2019-05-07 | COMP | 2019-04-29 | COMP | 2019-06-24 | COMP | Rule 15/16 | 44 | 136 | 91 | 84 | 0 | 34 | 385
2937 | 2017-12-12 | 2018-02-20 | 2018-05-14 | 2018-05-14 | COMP | 2018-05-02 | NOTN | 2018-11-26 | COMP | 2019-01-09 | COMP | 2019-03-18 | COMP | Other | 47 | 60 |  | 135 | 31 | 47 | 316
2974 | 2017-12-12 | 2018-02-23 | 2018-07-23 | 2018-07-23 | COMP | 2018-09-28 | COMP | 2018-11-16 | COMP | 2020-07-20 | COMP | 2019-05-07 | COMP | Rule 16 | 50 | 105 | 49 | 35 | 420 |  | 352
3022 | 2017-12-12 | 2018-02-27 | 2018-04-13 | 2018-04-13 | COMP | 2019-02-26 | COMP | 2020-05-21 | COMP | 2020-06-26 | COMP | 2020-07-02 | COMP | Rule 16 | 52 | 34 | 218 | 313 | 26 | 5 | 643
3566 | 2017-12-12 | 2018-05-17 | 2019-08-01 | 2019-08-01 | COMP | 2020-07-02 | COMP | 2023-05-09 | COMP | 2022-08-15 | COMP | 2023-05-17 | COMP | Rule 15/16 | 109 | 304 | 232 | 717 | 0 | 7 | 1365
4054 | 2017-12-12 | 2019-01-04 | 2020-05-01 | 2020-05-01 | COMP | 2020-08-06 | COMP | 2020-05-28 | INPR | 2020-12-14 | COMP | 2020-11-29 | COMP | Rule 15/16 | 267 | 334 | 69 |  |  |  | 745
4061 | 2017-12-12 | 2019-01-04 | 2019-10-29 | 2019-10-29 | COMP | 2020-01-27 | COMP | 2020-08-27 | COMP | 2020-09-01 | COMP | 2020-10-06 | COMP | Rule 16 | 267 | 208 | 59 | 152 | 4 | 25 | 710
4623 | 2017-12-12 | 2018-02-16 | 2018-04-27 | 2018-04-27 | COMP | 2019-03-11 | COMP | 2019-03-12 | COMP | 2019-04-08 | COMP | 2019-04-30 | COMP | Rule 16 | 46 | 50 | 217 | 2 | 20 | 17 | 347
4680 | 2017-12-12 | 2018-03-12 | 2018-07-28 | 2018-07-28 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2021-09-02 | COMP | 2021-10-01 | COMP | Rule 16 | 61 | 98 | 174 | 1 | 607 | 21 | 958
13431 | 2017-12-12 | 2019-07-25 | 2019-10-15 | 2019-10-15 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-01-09 | COMP | 2020-03-23 | COMP | Rule 16 | 407 | 58 | 85 | 1 | 0 | 24 | 571
2890 | 2017-12-13 | 2018-02-12 | 2018-04-01 | 2018-04-01 | COMP | 2019-02-11 | COMP | 2019-04-03 | COMP | 2019-03-22 | COMP | 2019-05-29 | COMP | Rule 16 | 41 | 34 | 217 | 37 | 0 | 40 | 366
3169 | 2017-12-13 | 2018-03-17 | 2018-06-27 | 2018-06-27 | COMP | 2019-03-15 | COMP | 2019-03-28 | COMP | 2019-10-21 | COMP | 2019-12-05 | COMP | Rule 16 | 64 | 72 | 179 | 10 | 145 | 31 | 497
3410 | 2017-12-13 | 2018-04-20 | 2018-07-11 | 2018-07-11 | COMP | 2019-05-01 | COMP | 2018-11-09 | COMP | 2019-04-29 | COMP | 2019-05-29 | COMP | Rule 16 | 89 | 57 | 203 |  | 115 | 22 | 366
3483 | 2017-12-13 | 2018-05-04 | 2018-08-02 | 2018-08-02 | COMP | 2019-02-15 | COMP | 2019-03-05 | COMP | 2019-05-21 | COMP | 2019-06-04 | COMP | Rule 16 | 99 | 63 | 135 | 12 | 56 | 10 | 370
3571 | 2017-12-13 | 2018-05-17 | 2018-10-19 | 2018-10-19 | COMP | 2019-01-28 | COMP | 2019-08-05 | COMP | 2019-12-28 | INPR | 2019-09-06 | COMP | Rule 16 | 108 | 109 | 66 | 133 |  |  | 436
4478 | 2017-12-13 | 2018-01-02 | 2018-02-16 | 2018-02-16 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-07-21 | INPR | 2019-04-17 | COMP | Rule 16 | 13 | 33 | 247 | 1 |  |  | 337
4702 | 2017-12-13 | 2018-03-15 | 2018-08-16 | 2018-08-16 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-10-15 | COMP | 2019-11-06 | COMP | Rule 16 | 63 | 109 | 78 | 1 | 216 | 17 | 479
4882 | 2017-12-13 | 2018-04-09 | 2018-08-17 | 2018-08-17 | COMP | 2018-08-15 | NOTN | 2018-08-17 | COMP | 2019-02-12 | COMP | 2019-03-11 | COMP | Other | 80 | 93 |  | 1 | 121 | 19 | 310
5901 | 2017-12-13 | 2018-07-10 | 2018-12-10 | 2018-12-10 | COMP | 2019-02-19 | COMP | 2019-03-08 | COMP | 2019-04-16 | COMP | 2019-05-04 | COMP | Rule 16 | 144 | 106 | 48 | 14 | 28 | 14 | 349
6109 | 2017-12-13 | 2018-07-26 | 2018-08-09 | 2018-08-09 | COMP | 2018-08-29 | COMP | 2018-08-29 | COMP | 2018-12-11 | COMP | 2019-01-09 | COMP | Rule 16 | 156 | 11 | 15 | 1 | 71 | 20 | 269
7127 | 2017-12-13 | 2018-09-28 | 2019-01-03 | 2020-05-25 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2023-05-10 | COMP | 2023-07-27 | COMP | Rule 16 | 201 | 65 | 11 | 1 | 735 | 54 | 1412
2537 | 2017-12-14 | 2017-12-19 | 2018-07-16 | 2018-07-16 | COMP | 2018-12-05 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-04-19 | COMP | Other | 4 | 144 | 99 | 23 | 1 | 72 | 338
2752 | 2017-12-14 | 2018-01-26 | 2018-06-21 | 2018-06-21 | COMP | 2018-08-09 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2020-02-18 | COMP | Rule 16 | 29 | 103 | 35 | 335 | 1 | 47 | 545
2897 | 2017-12-14 | 2018-02-13 | 2018-09-13 | 2018-09-13 | COMP | 2018-09-20 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2019-01-28 | COMP | Rule 16 | 41 | 149 | 6 | 26 | 1 | 62 | 280
2976 | 2017-12-14 | 2018-02-23 | 2018-05-07 | 2018-05-07 | COMP | 2018-06-11 | COMP | 2018-06-11 | COMP | 2018-07-24 | COMP | 2021-02-25 | COMP | Rule 16 | 48 | 52 | 25 | 1 | 31 | 651 | 803
3650 | 2017-12-14 | 2018-06-02 | 2018-11-26 | 2019-08-07 | COMP | 2019-08-19 | COMP | 2019-09-06 | COMP | 2019-06-07 | COMP | 2019-11-01 | COMP | Rule 16 | 117 | 121 | 9 | 14 | 0 | 41 | 475
3772 | 2017-12-14 | 2018-07-09 | 2018-08-02 | 2018-08-02 | COMP | 2018-10-02 | COMP | 2018-10-05 | COMP | 2019-08-06 | COMP | 2019-07-26 | COMP | Other | 142 | 19 | 43 | 4 | 209 |  | 406
3914 | 2017-12-14 | 2018-10-01 | 2018-11-30 | 2018-11-30 | COMP | 2019-04-22 | COMP | 2019-05-02 | COMP | 2019-12-28 | INPR | 2019-08-23 | COMP | Rule 16 | 201 | 42 | 98 | 9 |  |  | 426
4504 | 2017-12-14 | 2018-01-11 | 2018-11-28 | 2018-11-30 | COMP | 2018-12-28 | COMP | 2019-03-15 | COMP | 2019-03-29 | COMP | 2019-05-01 | COMP | Rule 16 | 19 | 222 | 20 | 53 | 11 | 24 | 346
5281 | 2017-12-14 | 2018-05-17 | 2018-11-06 | 2018-11-06 | COMP | 2018-11-09 | COMP | 2018-12-20 | COMP | 2019-01-04 | COMP | 2019-03-26 | COMP | Rule 15/16 | 107 | 121 | 4 | 27 | 10 | 56 | 320
5631 | 2017-12-14 | 2018-06-22 | 2019-05-21 | 2019-05-22 | COMP | 2019-07-17 | COMP | 2020-12-15 | COMP | 2023-12-02 | INPR | 2021-01-15 | COMP | Rule 16 | 132 | 229 | 39 | 357 |  |  | 776
5667 | 2017-12-14 | 2018-06-25 | 2018-10-15 | 2018-10-15 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-11-24 | INPR | 2019-08-08 | COMP | Rule 16 | 133 | 79 | 34 | 1 |  |  | 415
5785 | 2017-12-14 | 2018-07-02 | 2018-09-27 | 2018-09-27 | COMP | 2018-11-06 | COMP | 2019-03-05 | COMP | 2019-09-22 | INPR | 2019-03-14 | COMP | Rule 16 | 138 | 62 | 29 | 79 |  |  | 312
7151 | 2017-12-14 | 2018-09-28 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-16 | COMP | 2019-02-20 | COMP | 2019-02-21 | COMP | 2019-03-12 | COMP | Rule 16 | 200 | 56 | 19 | 24 | 2 | 14 | 310
9631 | 2017-12-14 | 2019-02-09 | 2019-03-22 | 2019-04-06 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-06-20 | COMP | Rule 16 | 289 | 29 | 17 | 1 | 1 | 37 | 381
2559 | 2017-12-15 | 2017-12-22 | 2017-12-26 | 2017-12-26 | COMP | 2018-05-30 | COMP | 2018-05-30 | COMP | 2019-09-17 | COMP | 2019-10-15 | COMP | Rule 16 | 6 | 2 | 108 | 1 | 328 | 21 | 461
2663 | 2017-12-15 | 2018-01-16 | 2018-04-20 | 2018-04-20 | COMP | 2018-11-09 | COMP | 2018-11-09 | COMP | 2018-11-09 | COMP | 2019-01-28 | COMP | Rule 16 | 20 | 68 | 143 | 1 | 1 | 51 | 279
2698 | 2017-12-15 | 2018-01-19 | 2018-03-29 | 2018-03-29 | COMP | 2018-08-03 | COMP | 2018-08-03 | COMP | 2019-03-12 | COMP | 2019-06-06 | COMP | Rule 16 | 23 | 49 | 90 | 1 | 150 | 62 | 370
2701 | 2017-12-15 | 2018-01-20 | 2018-04-18 | 2018-04-18 | COMP | 2018-09-13 | COMP | 2019-03-27 | COMP | 2019-08-31 | INPR | 2019-04-20 | COMP | Rule 16 | 23 | 62 | 104 | 133 |  |  | 337
2738 | 2017-12-15 | 2018-01-25 | 2018-06-08 | 2018-06-08 | COMP | 2018-06-26 | COMP | 2018-07-09 | COMP | 2019-10-02 | COMP | 2019-12-16 | COMP | Rule 16 | 27 | 95 | 13 | 9 | 312 | 51 | 502
2795 | 2017-12-15 | 2018-02-01 | 2018-10-20 | 2018-10-20 | COMP | 2019-05-07 | COMP | 2019-05-15 | COMP | 2020-03-16 | COMP | 2020-04-09 | COMP | Other | 32 | 183 | 135 | 7 | 209 | 19 | 581
2905 | 2017-12-15 | 2018-02-14 | 2018-08-02 | 2018-08-02 | COMP | 2018-09-17 | COMP | 2018-09-27 | COMP | 2018-08-10 | COMP | 2019-01-03 | COMP | Rule 16 | 41 | 119 | 32 | 9 | 0 | 66 | 263
3308 | 2017-12-15 | 2018-04-04 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-24 | COMP | 2019-08-20 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | Rule 16 | 75 | 282 | 27 | 41 | 16 | 1 | 437
3309 | 2017-12-15 | 2018-04-04 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-24 | COMP | 2019-08-15 | COMP | 2019-09-11 | COMP | 2019-09-12 | COMP | Rule 16 | 75 | 288 | 21 | 38 | 19 | 2 | 438
7694 | 2017-12-15 | 2018-10-25 | 2019-01-08 | 2019-01-08 | COMP | 2019-01-22 | COMP | 2019-10-21 | REQD | 2019-10-21 | REQD | 2019-07-10 | COMP | Rule 16 | 218 | 49 | 10 |  |  |  | 393
6757 | 2017-12-17 | 2018-09-10 | 2019-01-25 | 2019-01-25 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-31 | COMP | 2019-07-18 | COMP | Rule 16 | 184 | 94 | 69 | 1 | 21 | 34 | 398
2655 | 2017-12-18 | 2018-01-12 | 2018-03-14 | 2018-03-14 | COMP | 2018-04-04 | COMP | 2018-04-05 | COMP | 2019-04-11 | COMP | 2019-04-27 | COMP | Rule 16 | 18 | 42 | 16 | 2 | 256 | 12 | 341
2669 | 2017-12-18 | 2018-01-16 | 2018-09-01 | 2018-09-01 | COMP | 2018-10-24 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2019-11-15 | COMP | Rule 16 | 19 | 161 | 37 | 263 | 1 | 5 | 482
2670 | 2017-12-18 | 2018-01-16 | 2018-09-01 | 2018-09-01 | COMP | 2018-12-13 | COMP | 2019-06-10 | COMP | 2019-06-04 | COMP | 2019-06-18 | COMP | Rule 16 | 19 | 161 | 70 | 123 | 0 | 7 | 377
2794 | 2017-12-18 | 2018-02-01 | 2018-05-21 | 2018-05-21 | COMP | 2018-10-04 | COMP | 2018-10-22 | COMP | 2018-10-23 | COMP | 2019-01-10 | COMP | Rule 16 | 31 | 77 | 96 | 13 | 2 | 53 | 267
2800 | 2017-12-18 | 2018-02-01 | 2018-03-06 | 2018-08-29 | COMP | 2019-03-18 | COMP | 2018-03-28 | COMP | 2019-03-15 | COMP | 2019-03-26 | COMP | Rule 16 | 31 | 23 | 136 |  | 243 | 8 | 318
2940 | 2017-12-18 | 2018-02-20 | 2018-08-21 | 2019-11-22 | COMP | 2019-12-27 | COMP | 2020-02-11 | COMP | 2020-02-05 | COMP | 2020-03-11 | COMP | Rule 15/16 | 43 | 129 | 23 | 31 | 0 | 21 | 559
3301 | 2017-12-18 | 2018-04-04 | 2018-09-12 | 2018-09-12 | COMP | 2018-10-09 | COMP | 2019-03-11 | COMP | 2019-04-12 | COMP | 2019-05-20 | COMP | Rule 16 | 74 | 113 | 20 | 103 | 25 | 27 | 357
3349 | 2017-12-18 | 2018-04-10 | 2018-05-20 | 2018-05-20 | COMP | 2018-07-20 | COMP | 2018-07-30 | COMP | 2020-01-10 | COMP | 2020-02-11 | COMP | Rule 16 | 78 | 29 | 43 | 7 | 364 | 22 | 539
3784 | 2017-12-18 | 2018-07-12 | 2018-09-27 | 2018-09-27 | COMP | 2018-10-23 | COMP | 2018-12-19 | COMP | 2019-01-20 | COMP | 2019-05-22 | COMP | Rule 16 | 143 | 55 | 19 | 39 | 21 | 86 | 359
4635 | 2017-12-18 | 2018-02-21 | 2018-05-30 | 2018-05-30 | COMP | 2019-02-26 | COMP | 2019-03-28 | COMP | 2019-04-29 | COMP | 2019-05-06 | COMP | Rule 16 | 44 | 70 | 186 | 23 | 23 | 6 | 347
4794 | 2017-12-18 | 2018-03-31 | 2019-01-02 | 2019-01-02 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-03-19 | COMP | 2019-04-09 | COMP | Rule 16 | 71 | 190 | 17 | 1 | 37 | 16 | 328
5316 | 2017-12-18 | 2018-05-22 | 2018-12-24 | 2018-12-24 | COMP | 2019-09-20 | COMP | 2019-09-27 | COMP |  |  | 2020-01-28 | COMP | Rule 15/16 | 108 | 149 | 188 | 6 |  |  | 529
5814 | 2017-12-18 | 2018-07-05 | 2018-08-23 | 2018-08-23 | COMP | 2018-12-13 | COMP | 2018-12-13 | COMP | 2019-11-24 | INPR | 2019-07-17 | COMP | Rule 16 | 138 | 36 | 77 | 1 |  |  | 397
6089 | 2017-12-18 | 2018-07-26 | 2018-11-02 | 2018-11-02 | COMP | 2019-03-06 | COMP | 2019-04-11 | COMP | 2019-04-12 | COMP | 2019-05-15 | COMP | Rule 15/16 | 153 | 71 | 82 | 27 | 2 | 24 | 354
11474 | 2017-12-18 | 2019-04-29 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-09-13 | COMP | 2019-10-07 | COMP | Rule 16 | 342 | 56 | 28 | 1 | 15 | 17 | 454
11863 | 2017-12-18 | 2019-05-15 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-12-29 | INPR | 2019-07-23 | COMP | Rule 16 | 354 | 6 | 23 | 1 |  |  | 401
11979 | 2017-12-18 | 2019-05-20 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-12-29 | INPR | 2019-07-23 | COMP | Rule 16 | 357 | 3 | 23 | 1 |  |  | 401
2576 | 2017-12-19 | 2017-12-28 | 2018-12-06 | 2018-12-06 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-02-11 | COMP | Rule 16 | 7 | 237 | 10 | 1 | 1 | 36 | 287
2596 | 2017-12-19 | 2018-01-04 | 2018-11-16 | 2019-05-21 | COMP | 2019-06-17 | COMP | 2019-10-22 | INPR | 2019-10-28 | COMP | 2019-12-14 | COMP | Rule 16 | 11 | 221 | 19 |  |  |  | 499
2639 | 2017-12-19 | 2018-01-10 | 2018-07-02 | 2018-07-02 | COMP | 2018-08-15 | NOTN | 2018-08-15 | COMP | 2018-08-22 | COMP | 2019-09-14 | COMP | Other | 15 | 121 |  | 32 | 6 | 267 | 437
3219 | 2017-12-19 | 2018-03-22 | 2018-08-07 | 2018-08-07 | COMP | 2019-05-16 | COMP | 2019-08-15 | COMP | 2020-02-12 | COMP | 2020-05-30 | COMP | Rule 15/16 | 64 | 97 | 195 | 64 | 123 | 76 | 614
3239 | 2017-12-19 | 2018-03-27 | 2020-04-20 | 2020-04-20 | COMP | 2020-06-17 | COMP | 2020-10-20 | COMP |  | INPR | 2021-02-24 | COMP | Rule 15/16 | 67 | 520 | 42 | 89 |  |  | 799
3350 | 2017-12-19 | 2018-04-11 | 2018-12-20 | 2018-12-20 | COMP | 2019-04-04 | COMP | 2023-10-18 | COMP | 2023-10-04 | COMP | 2023-11-08 | COMP | Rule 16 | 78 | 176 | 72 | 1143 | 0 | 16 | 1481
4498 | 2017-12-19 | 2018-01-08 | 2018-03-11 | 2018-06-07 | COMP | 2018-08-17 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-03-29 | COMP | Rule 16 | 13 | 43 | 51 | 119 | 1 | 35 | 320
4514 | 2017-12-19 | 2018-01-17 | 2018-04-03 | 2018-04-03 | COMP | 2018-09-17 | COMP | 2019-06-05 | COMP | 2020-02-27 | COMP | 2020-03-02 | COMP | Rule 16 | 19 | 54 | 117 | 180 | 183 | 3 | 551
4532 | 2017-12-19 | 2018-01-26 | 2018-06-25 | 2018-06-25 | COMP | 2018-07-27 | COMP | 2018-07-27 | COMP | 2019-04-19 | COMP | 2019-04-24 | COMP | Rule 16 | 26 | 105 | 24 | 1 | 183 | 4 | 338
4718 | 2017-12-19 | 2018-03-22 | 2018-06-18 | 2018-06-18 | COMP | 2018-10-30 | COMP | 2019-10-03 | COMP | 2019-10-08 | COMP | 2019-11-01 | COMP | Rule 16 | 64 | 62 | 95 | 233 | 4 | 19 | 472
4719 | 2017-12-19 | 2018-03-22 | 2018-06-22 | 2018-06-22 | COMP | 2018-10-30 | COMP | 2019-10-03 | COMP | 2019-09-19 | COMP | 2019-11-01 | COMP | Rule 16 | 64 | 66 | 91 | 233 | 0 | 22 | 472
4862 | 2017-12-19 | 2018-04-06 | 2019-07-31 | 2021-10-31 | COMP | 2021-11-05 | COMP | 2021-11-23 | COMP | 2023-12-02 | INPR | 2021-12-30 | COMP | Rule 16 | 75 | 332 | 5 | 12 |  |  | 1014
4973 | 2017-12-19 | 2018-04-17 | 2018-07-23 | 2018-07-23 | COMP | 2018-11-05 | COMP | 2018-11-20 | COMP | 2019-09-27 | COMP | 2019-10-07 | COMP | Rule 16 | 82 | 68 | 75 | 11 | 215 | 7 | 453
5683 | 2017-12-19 | 2018-06-25 | 2018-10-29 | 2019-01-24 | COMP | 2019-03-04 | COMP | 2019-05-14 | COMP | 2023-11-11 | INPR | 2019-07-24 | COMP | Rule 16 | 130 | 89 | 27 | 52 |  |  | 401
5963 | 2017-12-19 | 2018-07-16 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-21 | COMP | 2019-07-25 | COMP | 2019-08-14 | COMP | 2019-10-08 | COMP | Rule 16 | 144 | 79 | 13 | 169 | 15 | 39 | 454
6084 | 2017-12-19 | 2018-07-24 | 2018-11-13 | 2018-11-13 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-02-14 | COMP | 2019-08-21 | COMP | Rule 16 | 150 | 79 | 62 | 1 | 2 | 132 | 421
6232 | 2017-12-19 | 2018-08-06 | 2020-04-01 | 2020-12-28 | COMP | 2021-03-23 | COMP | 2021-04-14 | COMP | 2021-03-23 | COMP | 2021-06-04 | COMP | Rule 15/16 | 159 | 415 | 59 | 17 | 0 | 37 | 870
6629 | 2017-12-19 | 2018-09-01 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-02-28 | COMP | 2019-04-03 | COMP | Rule 15/16 | 178 | 49 | 30 | 1 | 43 | 25 | 323
7195 | 2017-12-19 | 2018-10-02 | 2018-12-05 | 2018-12-10 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-05-21 | COMP | 2019-06-05 | COMP | Rule 15/16 | 199 | 44 | 97 | 1 | 17 | 11 | 367
3307 | 2017-12-20 | 2018-04-05 | 2018-06-28 | 2018-06-28 | COMP | 2020-04-24 | COMP | 2020-04-27 | COMP | 2020-05-11 | COMP | 2020-05-27 | COMP | Rule 15/16 | 73 | 60 | 458 | 2 | 11 | 12 | 611
3368 | 2017-12-20 | 2018-04-13 | 2018-09-19 | 2018-09-19 | COMP | 2019-01-11 | COMP | 2019-05-08 | COMP | 2019-05-07 | COMP | 2019-07-03 | COMP | Rule 16 | 79 | 111 | 78 | 82 | 0 | 40 | 386
5162 | 2017-12-20 | 2018-05-04 | 2019-02-12 | 2019-09-25 | COMP | 2019-11-25 | COMP | 2019-12-20 | COMP | 2019-05-29 | COMP | 2020-01-28 | COMP | Rule 16 | 94 | 194 | 43 | 18 | 0 | 25 | 527
6151 | 2017-12-20 | 2018-07-30 | 2019-01-17 | 2019-01-17 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-06-27 | COMP | 2019-08-08 | COMP | Rule 16 | 153 | 118 | 100 | 1 | 14 | 30 | 411
6516 | 2017-12-20 | 2018-08-23 | 2018-12-18 | 2018-12-18 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-11-19 | COMP | 2019-11-18 | COMP | Other | 171 | 80 | 200 | 1 | 34 |  | 481
6919 | 2017-12-20 | 2018-09-17 | 2018-12-21 | 2018-12-21 | COMP | 2019-01-09 | COMP | 2019-09-24 | COMP | 2019-08-19 | COMP | 2019-11-20 | COMP | Rule 15/16 | 187 | 67 | 12 | 180 | 0 | 41 | 483
7014 | 2017-12-20 | 2018-09-22 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-12-16 | COMP | 2020-02-06 | COMP | Rule 16 | 191 | 111 | 34 | 1 | 165 | 36 | 534
40477 | 2017-12-20 | 2023-01-05 | 2023-03-27 | 2023-03-27 | COMP | 2023-03-27 | NOTN | 2023-05-18 | COMP | 2023-08-07 | COMP | 2023-08-22 | COMP | Other | 1267 | 56 |  | 39 | 55 | 12 | 1425
3103 | 2017-12-21 | 2018-03-08 | 2018-07-30 | 2018-07-30 | COMP | 2018-12-04 | COMP | 2019-09-06 | COMP | 2020-03-06 | COMP | 2020-10-03 | COMP | Rule 15/16 | 52 | 101 | 88 | 192 | 124 | 149 | 701
4489 | 2017-12-21 | 2018-01-05 | 2018-04-12 | 2018-04-12 | COMP | 2018-09-18 | COMP | 2018-10-11 | COMP | 2018-11-26 | COMP | 2019-02-01 | COMP | Rule 15/16 | 10 | 68 | 111 | 18 | 30 | 47 | 279
4521 | 2017-12-21 | 2018-01-19 | 2018-01-20 | 2018-01-20 | COMP | 2018-02-06 | COMP | 2018-02-06 | COMP | 2019-09-12 | COMP | 2019-07-26 | COMP | Rule 16 | 19 | 1 | 12 | 1 | 404 |  | 401
4543 | 2017-12-21 | 2018-01-26 | 2018-03-14 | 2018-03-14 | COMP | 2018-06-25 | COMP | 2018-08-24 | COMP |  |  | 2019-03-20 | COMP | Rule 16 | 24 | 33 | 73 | 44 |  |  | 311
4599 | 2017-12-21 | 2018-02-13 | 2018-04-13 | 2018-09-04 | COMP | 2018-09-27 | COMP | 2018-09-27 | COMP | 2019-03-29 | COMP | 2019-07-23 | COMP | Rule 16 | 36 | 43 | 18 | 1 | 125 | 81 | 398
4615 | 2017-12-21 | 2018-02-14 | 2018-05-08 | 2018-05-08 | COMP | 2018-06-01 | COMP | 2018-06-01 | COMP | 2019-02-25 | COMP | 2019-04-08 | COMP | Rule 16 | 37 | 59 | 18 | 1 | 183 | 31 | 324
4683 | 2017-12-21 | 2018-03-14 | 2018-04-24 | 2018-04-24 | COMP | 2018-11-07 | COMP | 2018-11-08 | COMP | 2018-11-08 | COMP | 2019-01-04 | COMP | Rule 16 | 56 | 30 | 139 | 2 | 1 | 37 | 260
4709 | 2017-12-21 | 2018-03-19 | 2018-10-27 | 2019-02-06 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-09-06 | COMP | 2019-11-14 | COMP | Rule 15/16 | 59 | 157 | 81 | 1 | 69 | 49 | 478
4786 | 2017-12-21 | 2018-03-29 | 2018-09-04 | 2018-09-04 | COMP | 2018-09-19 | COMP | 2018-09-19 | COMP | 2019-03-25 | COMP | 2019-05-02 | COMP | Rule 16 | 67 | 111 | 12 | 1 | 127 | 29 | 342
5233 | 2017-12-21 | 2018-05-14 | 2019-01-25 | 2019-01-25 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-19 | COMP | 2019-10-03 | COMP | Rule 16 | 99 | 176 | 82 | 1 | 21 | 75 | 449
5277 | 2017-12-21 | 2018-05-16 | 2018-09-08 | 2018-09-08 | COMP | 2019-08-28 | COMP | 2019-10-24 | INPR | 2021-02-27 | REQD | 2020-02-08 | COMP | Rule 16 | 101 | 80 | 244 |  |  |  | 534
5278 | 2017-12-21 | 2018-05-16 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2019-03-08 | COMP | 2019-06-03 | COMP | Rule 16 | 101 | 101 | 31 | 1 | 73 | 61 | 363
5915 | 2017-12-21 | 2018-07-12 | 2018-10-05 | 2018-10-05 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-03-08 | COMP | 2019-05-21 | COMP | Rule 16 | 140 | 61 | 18 | 1 | 87 | 53 | 355
7741 | 2017-12-21 | 2018-10-29 | 2019-03-06 | 2019-03-06 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-10-16 | COMP | Rule 16 | 216 | 86 | 59 | 1 | 1 | 100 | 458
2702 | 2017-12-22 | 2018-01-20 | 2018-04-20 | 2018-04-20 | COMP | 2018-07-31 | COMP | 2020-01-28 | COMP | 2020-01-13 | COMP | 2020-03-04 | COMP | Rule 16 | 18 | 64 | 71 | 374 | 0 | 26 | 550
3384 | 2017-12-22 | 2018-04-17 | 2018-07-27 | 2018-07-27 | COMP | 2018-09-20 | COMP | 2019-07-17 | COMP | 2019-07-03 | COMP | 2019-08-07 | COMP | Rule 16 | 79 | 72 | 39 | 206 | 0 | 16 | 408
3926 | 2017-12-22 | 2018-10-10 | 2019-10-30 | 2019-10-30 | COMP | 2020-09-14 | COMP | 2020-12-01 | COMP | 2023-12-02 | INPR | 2022-03-02 | COMP | Rule 16 | 202 | 266 | 220 | 54 |  |  | 1053
4676 | 2017-12-22 | 2018-03-08 | 2018-05-22 | 2018-05-22 | COMP | 2018-06-01 | COMP | 2018-06-01 | COMP | 2018-06-08 | COMP | 2019-03-01 | COMP | Rule 16 | 51 | 54 | 8 | 1 | 6 | 182 | 297
4724 | 2017-12-22 | 2018-03-21 | 2018-06-28 | 2018-06-28 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2019-12-16 | COMP | 2020-01-06 | COMP | Rule 16 | 60 | 71 | 103 | 1 | 266 | 14 | 510
4787 | 2017-12-22 | 2018-03-29 | 2018-08-31 | 2018-08-31 | COMP | 2018-10-31 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-04-12 | COMP | Rule 16 | 66 | 110 | 43 | 93 | 1 | 19 | 327
5853 | 2017-12-22 | 2018-07-07 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2021-03-27 | INPR | 2020-03-03 | COMP | Rule 16 | 135 | 128 | 15 | 1 |  |  | 549
5971 | 2017-12-22 | 2018-07-16 | 2018-09-12 | 2018-09-12 | COMP | 2018-09-26 | COMP | 2018-09-26 | COMP | 2019-03-20 | COMP | 2019-04-16 | COMP | Rule 16 | 141 | 42 | 11 | 1 | 119 | 20 | 329
7010 | 2017-12-22 | 2018-09-21 | 2018-09-27 | 2018-09-27 | COMP | 2018-10-11 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-04-18 | COMP | Rule 16 | 189 | 5 | 11 | 70 | 1 | 60 | 331
2706 | 2017-12-23 | 2018-01-22 | 2018-07-17 | 2018-07-17 | COMP | 2020-12-07 | COMP | 2020-12-07 | INPR |  | REQD | 2021-01-15 | COMP | Other | 18 | 124 | 602 |  |  |  | 769
2709 | 2017-12-23 | 2018-01-22 | 2018-07-17 | 2018-07-17 | COMP | 2020-09-11 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | 2021-01-21 | COMP | Other | 18 | 124 | 544 | 4 | 1 | 86 | 772
2731 | 2017-12-23 | 2018-01-24 | 2018-07-17 | 2018-07-17 | COMP | 2020-12-07 | COMP | 2020-12-07 | INPR |  | REQD | 2021-01-15 | COMP | Other | 20 | 122 | 602 |  |  |  | 769
3299 | 2017-12-23 | 2018-04-04 | 2018-07-18 | 2018-07-18 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2022-01-29 | REQD | 2021-01-21 | COMP | Other | 69 | 74 | 601 | 1 |  |  | 772
3312 | 2017-12-23 | 2018-04-05 | 2018-06-04 | 2018-06-04 | COMP | 2018-11-07 | COMP | 2018-11-07 | INPR |  | REQD | 2019-05-13 | COMP | Other | 70 | 42 | 111 |  |  |  | 347
3473 | 2017-12-23 | 2018-05-02 | 2018-07-18 | 2018-07-18 | COMP | 2020-09-11 | COMP | 2020-09-16 | COMP | 2022-01-29 | REQD | 2021-01-21 | COMP | Other | 89 | 54 | 543 | 4 |  |  | 772
7141 | 2017-12-23 | 2018-09-28 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-21 | COMP | 2019-05-08 | COMP | Rule 16 | 193 | 85 | 7 | 1 | 8 | 55 | 344
3122 | 2017-12-25 | 2018-03-12 | 2018-08-22 | 2018-08-22 | COMP | 2018-09-27 | COMP | 2019-01-17 | COMP | 2019-07-29 | COMP | 2019-09-03 | COMP | Rule 15/16 | 52 | 116 | 26 | 76 | 134 | 26 | 425
4539 | 2017-12-25 | 2018-01-24 | 2018-04-23 | 2018-05-15 | COMP | 2018-09-11 | COMP | 2018-09-11 | COMP | 2018-10-30 | COMP | 2019-08-13 | COMP | Rule 15/16 | 20 | 63 | 83 | 1 | 36 | 197 | 411
2648 | 2017-12-26 | 2018-01-12 | 2018-07-23 | 2018-07-23 | COMP | 2018-08-30 | COMP | 2018-12-04 | COMP | 2019-06-29 | INPR | 2019-03-27 | COMP | Rule 15/16 | 13 | 133 | 29 | 65 |  |  | 314
2710 | 2017-12-26 | 2018-01-22 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-20 | COMP | 2019-02-28 | COMP | 2019-02-08 | COMP | 2019-03-20 | COMP | Rule 15/16 | 18 | 184 | 29 | 67 | 0 | 15 | 309
2740 | 2017-12-26 | 2018-01-25 | 2018-04-29 | 2018-04-29 | COMP | 2018-09-18 | COMP | 2019-03-04 | COMP | 2019-01-31 | COMP | 2019-04-08 | COMP | Rule 16 | 21 | 66 | 99 | 113 | 0 | 26 | 322
3432 | 2017-12-26 | 2018-04-26 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-27 | COMP | 2019-01-17 | COMP |  | INPR | 2019-05-09 | COMP | Rule 15/16 | 85 | 130 | 19 | 36 |  |  | 345
5773 | 2017-12-26 | 2018-07-05 | 2018-09-24 | 2018-09-24 | COMP | 2018-11-07 | COMP | 2018-11-07 | COMP | 2019-01-07 | COMP | 2019-02-01 | COMP | Rule 16 | 133 | 57 | 33 | 1 | 39 | 19 | 277
8298 | 2017-12-26 | 2018-11-26 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-16 | NOTN | 2019-05-16 | COMP | 2019-08-31 | COMP | 2019-11-13 | COMP | Other | 231 | 120 |  | 1 | 75 | 51 | 475
8419 | 2017-12-26 | 2018-11-29 | 2019-02-13 | 2019-04-26 | COMP | 2019-06-03 | COMP | 2019-08-27 | COMP | 2019-10-08 | COMP | 2019-11-13 | COMP | Rule 16 | 234 | 52 | 26 | 61 | 30 | 26 | 475
8660 | 2017-12-26 | 2018-12-13 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-01 | COMP | 2019-02-01 | INPR | 2019-09-02 | REQD | 2019-05-17 | COMP | Rule 16 | 244 | 26 | 9 |  |  |  | 351
11917 | 2017-12-26 | 2019-05-16 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-02-20 | COMP | 2020-04-02 | COMP | Rule 16 | 350 | 125 | 26 | 1 | 42 | 31 | 570
2708 | 2017-12-27 | 2018-01-22 | 2018-10-02 | 2018-10-02 | COMP | 2019-02-25 | COMP | 2019-03-01 | COMP | 2019-04-05 | COMP | 2019-06-10 | COMP | Rule 15/16 | 17 | 178 | 98 | 5 | 26 | 46 | 365
2863 | 2017-12-27 | 2018-02-08 | 2018-05-28 | 2018-05-25 | COMP | 2018-06-08 | COMP | 2018-06-08 | COMP | 2018-12-11 | COMP | 2019-01-03 | COMP | Rule 16 | 30 | 76 | 10 | 1 | 128 | 16 | 256
2914 | 2017-12-27 | 2018-02-15 | 2018-04-09 | 2018-04-09 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-04-01 | COMP | 2019-04-05 | COMP | Rule 16 | 35 | 37 | 239 | 1 | 8 | 5 | 320
3079 | 2017-12-27 | 2018-03-06 | 2018-05-21 | 2018-05-21 | COMP | 2018-12-12 | COMP | 2018-12-15 | COMP | 2020-01-18 | INPR | 2019-08-29 | COMP | Rule 16 | 47 | 55 | 142 | 3 |  |  | 422
3148 | 2017-12-27 | 2018-03-14 | 2018-07-25 | 2018-07-25 | COMP | 2021-02-12 | COMP | 2021-02-17 | COMP | 2021-05-11 | COMP | 2021-06-07 | COMP | Rule 15/16 | 53 | 94 | 642 | 3 | 60 | 19 | 866
3174 | 2017-12-27 | 2018-03-21 | 2018-03-22 | 2018-03-22 | COMP | 2018-04-09 | COMP | 2018-04-26 | COMP | 2019-08-27 | COMP | 2019-09-06 | COMP | Rule 16 | 58 | 2 | 13 | 14 | 337 | 8 | 427
3362 | 2017-12-27 | 2018-04-12 | 2019-01-30 | 2020-03-31 | COMP | 2020-05-04 | COMP | 2019-10-01 | COMP | 2020-06-03 | COMP | 2020-07-20 | COMP | Rule 16 | 74 | 201 | 25 |  | 169 | 34 | 645
3506 | 2017-12-27 | 2018-05-08 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-25 | COMP | 2019-04-08 | COMP |  | INPR | 2019-07-24 | COMP | Rule 15/16 | 92 | 203 | 18 | 11 |  |  | 396
3542 | 2017-12-27 | 2018-05-14 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-18 | COMP | 2019-05-02 | COMP | 2019-12-29 | INPR | 2019-08-28 | COMP | Rule 15/16 | 96 | 194 | 41 | 11 |  |  | 421
4577 | 2017-12-27 | 2018-02-06 | 2018-05-02 | 2019-04-26 | COMP | 2019-05-17 | COMP | 2020-03-02 | COMP | 2020-03-05 | COMP | 2020-04-22 | COMP | Rule 16 | 28 | 61 | 16 | 197 | 4 | 35 | 583
4611 | 2017-12-27 | 2018-02-14 | 2018-05-16 | 2018-05-16 | COMP | 2019-01-07 | COMP | 2018-06-04 | COMP | 2019-01-07 | COMP | 2019-02-15 | COMP | Rule 16 | 34 | 65 | 161 |  | 149 | 29 | 286
5530 | 2017-12-27 | 2018-06-12 | 2018-09-03 | 2018-09-03 | COMP | 2018-09-24 | COMP | 2018-09-24 | COMP | 2019-03-18 | COMP | 2019-03-21 | COMP | Rule 15/16 | 116 | 58 | 15 | 1 | 119 | 4 | 309
7771 | 2017-12-27 | 2018-10-30 | 2019-01-03 | 2019-01-03 | COMP | 2019-03-01 | COMP | 2019-03-01 | COMP | 2019-05-14 | COMP | 2019-07-18 | COMP | Rule 16 | 214 | 43 | 40 | 1 | 53 | 46 | 392
3340 | 2017-12-28 | 2018-04-10 | 2018-06-22 | 2018-06-22 | COMP | 2018-07-30 | COMP | 2018-07-30 | COMP | 2018-12-05 | COMP | 2019-01-22 | COMP | Rule 16 | 71 | 53 | 26 | 1 | 89 | 32 | 267
3735 | 2017-12-28 | 2018-06-20 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-03 | COMP | 2019-04-30 | COMP | 2019-01-27 | COMP | 2019-08-23 | COMP | Rule 16 | 121 | 137 |  | 82 | 0 | 82 | 417
4511 | 2017-12-28 | 2018-01-18 | 2018-04-16 | 2018-04-16 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-06-28 | COMP | 2019-07-08 | COMP | Rule 16 | 14 | 62 | 292 | 1 | 13 | 6 | 383
4540 | 2017-12-28 | 2018-01-25 | 2018-01-25 | 2020-10-27 | COMP | 2021-03-09 | COMP | 2018-03-02 | COMP | 2021-03-15 | COMP | 2021-03-29 | COMP | Rule 16 | 19 | 1 | 89 |  | 763 | 11 | 816
4587 | 2017-12-28 | 2018-02-08 | 2018-06-22 | 2018-06-22 | COMP | 2018-07-30 | COMP | 2018-09-06 | COMP | 2019-10-16 | COMP | 2019-11-12 | COMP | Rule 16 | 29 | 95 | 26 | 28 | 280 | 19 | 472
4710 | 2017-12-28 | 2018-03-19 | 2018-04-26 | 2018-05-10 | COMP | 2018-08-10 | COMP | 2019-01-07 | COMP | 2019-01-15 | COMP | 2019-01-16 | COMP | Rule 16 | 55 | 29 | 65 | 101 | 7 | 2 | 264
4712 | 2017-12-28 | 2018-03-19 | 2018-05-09 | 2018-05-09 | COMP | 2018-08-10 | COMP | 2019-01-30 | COMP | 2019-01-15 | COMP | 2019-03-04 | COMP | Rule 16 | 55 | 38 | 66 | 117 | 0 | 23 | 295
5409 | 2017-12-28 | 2018-05-29 | 2018-10-17 | 2018-10-17 | COMP | 2018-10-31 | COMP | 2018-10-31 | COMP | 2018-11-09 | COMP | 2019-01-14 | COMP | Rule 15/16 | 105 | 100 | 11 | 1 | 8 | 42 | 262
5544 | 2017-12-28 | 2018-06-12 | 2018-08-17 | 2018-08-17 | COMP | 2018-11-06 | COMP | 2018-11-07 | COMP | 2018-11-26 | COMP | 2022-06-23 | COMP | Rule 16 | 115 | 48 | 57 | 2 | 11 | 901 | 1129
5718 | 2017-12-28 | 2018-06-27 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2019-04-21 | INPR | 2019-01-02 | COMP | Rule 16 | 126 | 74 | 18 | 1 |  |  | 254
5780 | 2017-12-28 | 2018-07-03 | 2018-10-22 | 2018-10-22 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-22 | COMP | 2019-04-05 | COMP | Rule 16 | 130 | 78 | 68 | 1 | 16 | 31 | 319
5891 | 2017-12-28 | 2018-07-09 | 2018-10-09 | 2019-04-02 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-07-03 | COMP | 2019-08-09 | COMP | Rule 16 | 133 | 66 | 17 | 1 | 50 | 27 | 407
5952 | 2017-12-28 | 2018-07-16 | 2018-09-20 | 2019-12-13 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-01-13 | COMP | 2020-01-29 | COMP | Rule 16 | 138 | 48 | 3 | 1 | 18 | 12 | 523
6814 | 2017-12-28 | 2018-09-12 | 2018-12-17 | 2018-12-17 | COMP | 2020-03-05 | COMP | 2020-12-16 | COMP | 2022-10-31 | COMP | 2022-12-16 | COMP | Rule 16 | 179 | 66 | 305 | 200 | 473 | 32 | 1250
10478 | 2017-12-28 | 2019-03-19 | 2019-06-05 | 2019-06-05 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-12-03 | COMP | 2019-12-11 | COMP | Rule 16 | 306 | 56 | 84 | 1 | 42 | 7 | 491
2578 | 2017-12-29 | 2017-12-30 | 2018-06-26 | 2018-06-26 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2019-01-22 | COMP | 2019-03-08 | COMP | Rule 16 | 1 | 123 | 101 | 1 | 43 | 33 | 298
2590 | 2017-12-29 | 2018-01-04 | 2018-11-28 | 2018-11-28 | COMP | 2019-06-25 | COMP | 2019-10-16 | NOTN | 2019-07-19 | COMP | 2019-12-18 | COMP | Rule 15/16 | 4 | 227 | 145 |  |  |  | 495
2843 | 2017-12-29 | 2018-02-06 | 2018-10-01 | 2018-10-01 | COMP | 2018-11-07 | COMP | 2019-04-10 | COMP | 2019-08-13 | COMP | 2019-08-27 | COMP | Rule 16 | 26 | 166 | 28 | 104 | 88 | 11 | 418
2844 | 2017-12-29 | 2018-02-06 | 2018-10-15 | 2018-10-15 | COMP | 2019-01-28 | COMP | 2019-08-28 | COMP | 2020-02-29 | INPR | 2019-10-21 | COMP | Rule 16 | 26 | 176 | 70 | 150 |  |  | 456
2845 | 2017-12-29 | 2018-02-06 | 2019-05-15 | 2019-05-15 | COMP | 2019-10-18 | COMP | 2020-01-04 | COMP | 2020-01-14 | COMP | 2020-02-25 | COMP | Rule 16 | 26 | 321 | 110 | 51 | 7 | 29 | 540
2846 | 2017-12-29 | 2018-02-06 | 2019-05-30 | 2019-05-30 | COMP | 2019-09-05 | COMP | 2019-12-23 | COMP | 2020-02-06 | COMP | 2020-04-07 | COMP | Rule 16 | 26 | 331 | 69 | 75 | 31 | 43 | 570
2933 | 2017-12-29 | 2018-02-20 | 2018-04-17 | 2018-04-17 | COMP | 2018-05-22 | COMP | 2018-08-23 | COMP | 2018-06-28 | COMP | 2021-03-04 | COMP | Rule 15/16 | 35 | 41 | 26 | 66 | 0 | 634 | 798
3034 | 2017-12-29 | 2018-03-01 | 2018-06-08 | 2019-02-15 | COMP | 2019-06-29 | REQD | 2018-09-27 | COMP | 2019-03-16 | COMP | 2019-03-26 | COMP | Rule 16 | 42 | 71 |  |  | 115 | 7 | 310
4807 | 2017-12-29 | 2018-03-31 | 2018-09-24 | 2018-09-24 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-12-07 | COMP | Rule 16 | 63 | 123 | 281 | 1 | 1 | 22 | 487
2591 | 2017-12-30 | 2018-01-04 | 2018-05-08 | 2018-05-08 | COMP | 2018-07-24 | COMP | 2018-07-25 | COMP | 2018-12-27 | COMP | 2019-01-25 | COMP | Rule 16 | 3 | 87 | 54 | 2 | 107 | 20 | 268
2674 | 2018-01-02 | 2018-01-17 | 2018-02-02 | 2018-02-02 | COMP | 2020-02-28 | COMP | 2020-03-03 | COMP | 2022-01-29 | INPR | 2020-07-15 | COMP | Rule 16 | 11 | 13 | 520 | 3 |  |  | 639
3067 | 2018-01-02 | 2018-03-07 | 2018-07-14 | 2018-07-14 | COMP | 2019-03-28 | COMP | 2019-04-04 | COMP | 2019-04-16 | COMP | 2019-06-14 | COMP | Rule 16 | 45 | 91 | 176 | 6 | 9 | 43 | 366
3608 | 2018-01-02 | 2018-05-23 | 2018-10-05 | 2018-10-05 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-02-10 | COMP | 2020-05-11 | COMP | Rule 16 | 100 | 95 | 249 | 1 | 88 | 65 | 593
4487 | 2018-01-02 | 2018-01-05 | 2018-10-08 | 2018-10-08 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-11-01 | COMP | 2019-11-22 | COMP | Rule 16 | 4 | 192 | 66 | 1 | 205 | 15 | 478
4607 | 2018-01-02 | 2018-02-15 | 2019-07-08 | 2019-07-09 | COMP | 2019-07-09 | NOTN | 2019-07-09 | COMP | 2019-08-06 | COMP | 2019-09-17 | COMP | Other | 32 | 350 |  | 1 | 21 | 30 | 431
4610 | 2018-01-02 | 2018-02-14 | 2018-02-19 | 2018-03-27 | COMP | 2018-04-02 | COMP | 2018-04-02 | COMP | 2018-04-04 | COMP | 2019-09-03 | COMP | Rule 16 | 31 | 3 | 5 | 1 | 3 | 357 | 421
5400 | 2018-01-02 | 2018-05-29 | 2018-09-26 | 2018-09-26 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-07-10 | COMP | 2019-08-22 | COMP | Rule 16 | 103 | 85 | 143 | 1 | 55 | 32 | 414
6477 | 2018-01-02 | 2018-08-20 | 2018-10-03 | 2019-03-16 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-09-22 | INPR | 2019-05-28 | COMP | Rule 15/16 | 161 | 32 | 7 | 1 |  |  | 353
7375 | 2018-01-02 | 2018-10-10 | 2019-01-24 | 2020-03-04 | COMP | 2019-08-06 | COMP | 2020-05-04 | COMP | 2021-08-10 | COMP | 2022-01-19 | COMP | Rule 16 | 197 | 71 |  | 187 | 321 | 112 | 1019
9744 | 2018-01-02 | 2019-02-13 | 2019-05-17 | 2019-05-17 | COMP | 2020-03-06 | COMP | 2020-10-22 | COMP | 2023-03-31 | COMP | 2023-05-25 | COMP | Rule 16 | 281 | 67 | 201 | 163 | 611 | 40 | 1358
2765 | 2018-01-03 | 2018-01-29 | 2018-06-07 | 2018-06-07 | COMP | 2018-07-11 | COMP | 2018-12-13 | COMP | 2018-11-25 | COMP | 2019-06-03 | COMP | Rule 15/16 | 18 | 92 | 24 | 108 | 0 | 118 | 356
2859 | 2018-01-03 | 2018-02-07 | 2018-05-15 | 2018-05-15 | COMP | 2018-06-12 | COMP | 2018-06-12 | COMP | 2018-11-28 | COMP | 2019-01-11 | COMP | Rule 16 | 25 | 69 | 20 | 1 | 117 | 31 | 258
2880 | 2018-01-03 | 2018-02-10 | 2018-08-15 | 2018-08-15 | COMP | 2018-10-30 | COMP | 2018-10-31 | COMP | 2020-07-29 | COMP | 2020-09-22 | COMP | Rule 15/16 | 27 | 130 | 54 | 2 | 438 | 39 | 686
2984 | 2018-01-03 | 2018-02-26 | 2018-07-09 | 2018-07-09 | COMP | 2018-10-23 | COMP | 2018-10-23 | COMP | 2019-01-14 | COMP | 2019-01-29 | COMP | Rule 16 | 37 | 94 | 76 | 1 | 55 | 11 | 269
2985 | 2018-01-03 | 2018-02-26 | 2018-07-09 | 2018-07-09 | COMP | 2018-10-19 | COMP | 2018-10-30 | COMP | 2019-06-04 | COMP | 2019-06-14 | COMP | Rule 16 | 37 | 94 | 74 | 8 | 148 | 9 | 365
2986 | 2018-01-03 | 2018-02-26 | 2018-06-26 | 2018-06-26 | COMP | 2018-10-10 | COMP | 2018-10-10 | COMP | 2019-06-04 | COMP | 2019-06-13 | COMP | Rule 15/16 | 37 | 86 | 75 | 1 | 162 | 8 | 364
2988 | 2018-01-03 | 2018-02-26 | 2018-06-26 | 2018-06-26 | COMP | 2018-10-10 | COMP | 2019-03-04 | COMP | 2019-06-04 | COMP | 2019-06-11 | COMP | Rule 16 | 37 | 86 | 75 | 97 | 66 | 6 | 362
3320 | 2018-01-03 | 2018-04-06 | 2018-12-28 | 2018-12-28 | COMP | 2018-10-04 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-08-19 | COMP | Rule 15/16 | 66 | 184 |  | 200 | 1 | 20 | 410
3575 | 2018-01-03 | 2018-05-17 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-11 | COMP | 2018-12-20 | COMP | 2019-06-06 | COMP | 2019-07-24 | COMP | Rule 16 | 95 | 134 | 10 | 8 | 116 | 34 | 392
4486 | 2018-01-03 | 2018-01-05 | 2018-10-27 | 2018-10-27 | COMP | 2019-08-29 | COMP | 2019-09-09 | COMP | 2019-09-30 | COMP | 2019-10-24 | COMP | Rule 16 | 3 | 206 | 210 | 7 | 16 | 19 | 457
4568 | 2018-01-03 | 2018-02-01 | 2018-02-27 | 2018-02-27 | COMP | 2018-04-24 | COMP | 2018-04-24 | COMP | 2019-05-02 | COMP | 2019-07-10 | COMP | Rule 16 | 21 | 18 | 41 | 1 | 258 | 48 | 382
4603 | 2018-01-03 | 2018-02-12 | 2018-04-29 | 2018-04-29 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2018-12-11 | COMP | 2019-03-28 | COMP | Rule 15/16 | 28 | 54 | 138 | 1 | 19 | 74 | 310
4803 | 2018-01-03 | 2018-03-31 | 2018-10-03 | 2018-10-03 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2018-11-27 | COMP | 2019-02-12 | COMP | Rule 16 | 61 | 130 | 35 | 1 | 3 | 53 | 279
5884 | 2018-01-03 | 2018-07-09 | 2018-12-12 | 2021-04-07 | COMP | 2021-04-26 | COMP | 2020-04-22 | COMP | 2021-09-07 | COMP | 2021-11-05 | COMP | Rule 15/16 | 130 | 109 | 14 |  | 348 | 44 | 969
6348 | 2018-01-03 | 2018-08-13 | 2018-10-09 | 2018-10-09 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2018-12-11 | COMP | 2019-09-11 | COMP | Rule 16 | 155 | 41 | 39 | 1 | 5 | 190 | 426
6432 | 2018-01-03 | 2018-08-18 | 2018-11-09 | 2018-11-09 | COMP | 2019-01-24 | COMP |  | REQD |  | REQD | 2020-06-17 | COMP | Rule 16 | 159 | 59 | 49 |  |  |  | 618
6594 | 2018-01-03 | 2018-08-29 | 2019-02-12 | 2019-03-15 | COMP | 2019-06-25 | COMP | 2019-10-31 | COMP | 2020-02-11 | COMP | 2020-05-12 | COMP | Rule 16 | 167 | 113 | 72 | 91 | 68 | 65 | 593
10645 | 2018-01-03 | 2019-03-25 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-10 | COMP | 2019-08-12 | COMP |  | INPR | 2020-04-15 | COMP | Rule 16 | 307 | 11 | 25 | 65 |  |  | 574
11423 | 2018-01-03 | 2019-04-26 | 2019-07-19 | 2019-07-19 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-03-12 | COMP | 2020-06-26 | COMP | Rule 16 | 331 | 59 | 95 | 1 | 68 | 76 | 625
11632 | 2018-01-03 | 2019-05-06 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP |  | INPR | 2019-10-16 | COMP | Rule 15/16 | 337 | 81 | 13 | 1 |  |  | 451
40478 | 2018-01-03 | 2023-01-05 | 2023-04-13 | 2023-04-13 | COMP | 2023-05-03 | NOTN | 2023-05-18 | COMP | 2023-06-13 | COMP | 2023-07-01 | COMP | Other | 1259 | 69 |  | 26 | 18 | 13 | 1381
2595 | 2018-01-04 | 2018-01-04 | 2018-02-01 | 2018-02-01 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2021-06-06 | COMP | 2021-07-14 | COMP | Rule 16 | 1 | 20 | 473 | 1 | 369 | 27 | 887
2703 | 2018-01-04 | 2018-01-22 | 2018-07-02 | 2018-07-02 | COMP | 2018-08-14 | COMP | 2018-08-15 | COMP | 2019-09-11 | COMP | 2019-12-09 | COMP | Rule 16 | 12 | 114 | 31 | 2 | 270 | 61 | 485
2759 | 2018-01-04 | 2018-01-29 | 2018-03-26 | 2018-03-26 | COMP | 2018-04-09 | COMP | 2018-05-30 | COMP | 2021-02-27 | INPR | 2020-02-20 | COMP | Rule 16 | 17 | 40 | 11 | 37 |  |  | 534
2821 | 2018-01-04 | 2018-02-05 | 2018-05-09 | 2018-05-09 | COMP | 2018-05-31 | COMP | 2018-06-01 | COMP | 2018-09-22 | COMP | 2019-03-08 | COMP | Rule 15/16 | 22 | 67 | 16 | 2 | 79 | 113 | 295
2849 | 2018-01-04 | 2018-02-08 | 2018-05-09 | 2018-06-28 | COMP | 2018-07-03 | COMP | 2019-01-28 | COMP | 2023-02-15 | COMP | 2023-04-21 | COMP | Rule 16 | 25 | 64 | 4 | 142 | 1020 | 47 | 1332
3179 | 2018-01-04 | 2018-03-19 | 2018-08-23 | 2018-08-23 | COMP | 2019-07-25 | COMP | 2019-04-05 | COMP | 2019-05-16 | COMP | 2019-05-17 | COMP | Rule 15/16 | 51 | 112 | 231 |  | 30 | 2 | 345
3201 | 2018-01-04 | 2018-03-21 | 2018-08-06 | 2018-08-06 | COMP | 2019-01-07 | COMP | 2019-01-08 | COMP | 2019-02-02 | COMP | 2019-04-13 | COMP | Rule 15/16 | 53 | 97 | 105 | 2 | 18 | 49 | 320
3223 | 2018-01-04 | 2018-03-24 | 2019-06-13 | 2019-06-13 | COMP | 2019-11-25 | COMP | 2020-09-24 | COMP | 2020-07-27 | COMP | 2020-11-23 | COMP | Rule 15/16 | 55 | 308 | 115 | 211 | 0 | 42 | 728
3326 | 2018-01-04 | 2018-04-09 | 2018-12-17 | 2020-04-20 | COMP | 2020-06-17 | COMP | 2020-08-21 | COMP | 2020-12-17 | COMP | 2021-03-06 | COMP | Rule 15/16 | 66 | 175 | 42 | 48 | 81 | 53 | 796
3343 | 2018-01-04 | 2018-04-10 | 2018-10-22 | 2018-10-22 | COMP | 2019-06-06 | COMP | 2019-06-19 | COMP | 2019-09-03 | COMP | 2019-08-29 | COMP | Rule 16 | 67 | 137 | 156 | 10 | 53 |  | 417
3530 | 2018-01-04 | 2018-05-10 | 2018-09-13 | 2018-09-13 | COMP | 2019-02-26 | COMP | 2019-05-08 | COMP | 2019-10-19 | INPR | 2019-07-02 | COMP | Rule 16 | 89 | 88 | 112 | 52 |  |  | 376
4153 | 2018-01-04 | 2019-04-15 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-29 | COMP | 2019-06-12 | COMP | 2019-05-28 | COMP | 2019-07-24 | COMP | Rule 16 | 321 | 2 | 31 | 11 | 0 | 30 | 391
4674 | 2018-01-04 | 2018-03-08 | 2018-07-06 | 2018-08-23 | COMP | 2018-10-22 | COMP | 2018-11-01 | COMP | 2019-10-21 | COMP | 2019-12-30 | COMP | Rule 16 | 44 | 85 | 42 | 9 | 243 | 47 | 499
5483 | 2018-01-04 | 2018-06-04 | 2018-08-25 | 2018-08-25 | COMP | 2018-09-13 | COMP | 2018-09-13 | COMP | 2018-10-22 | COMP | 2021-03-30 | COMP | Rule 16 | 105 | 59 | 13 | 1 | 28 | 611 | 813
6901 | 2018-01-04 | 2018-09-17 | 2018-11-16 | 2020-06-23 | COMP | 2020-07-17 | COMP | 2020-05-01 | COMP | 2021-08-23 | COMP | 2021-11-20 | COMP | Rule 15/16 | 178 | 44 | 19 |  | 331 | 63 | 977
7093 | 2018-01-04 | 2018-09-26 | 2019-03-02 | 2019-03-02 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2019-05-28 | COMP | 2020-01-21 | COMP | Rule 16 | 185 | 106 | 24 | 1 | 38 | 163 | 513
7438 | 2018-01-04 | 2018-10-12 | 2019-01-10 | 2019-01-10 | COMP | 2019-02-15 | COMP | 2019-03-20 | COMP | 2019-09-02 | INPR | 2019-05-04 | COMP | Rule 16 | 197 | 60 | 26 | 23 |  |  | 335
14381 | 2018-01-04 | 2019-09-09 | 2020-10-05 | 2020-10-05 | COMP | 2020-12-21 | COMP | 2020-12-21 | COMP | 2021-05-25 | COMP | 2021-08-19 | COMP | Rule 15/16 | 423 | 272 | 53 | 1 | 108 | 61 | 913
2896 | 2018-01-05 | 2018-02-13 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-13 | COMP | 2019-03-09 | COMP | 2019-12-26 | COMP | 2020-01-09 | COMP | Rule 15/16 | 27 | 166 | 26 | 78 | 202 | 10 | 505
2964 | 2018-01-05 | 2018-02-23 | 2018-07-13 | 2018-07-13 | COMP | 2018-10-30 | COMP | 2019-01-09 | COMP | 2018-11-01 | COMP | 2019-04-18 | COMP | Rule 15/16 | 34 | 99 | 77 | 47 | 0 | 70 | 323
3020 | 2018-01-05 | 2018-02-27 | 2018-07-23 | 2022-03-15 | COMP | 2021-11-03 | COMP | 2021-12-28 | COMP | 2022-01-12 | COMP | 2022-04-25 | COMP | Rule 15/16 | 36 | 103 |  | 37 | 12 | 72 | 1083
3118 | 2018-01-05 | 2018-03-10 | 2018-09-18 | 2018-09-18 | COMP | 2018-09-21 | COMP | 2018-09-21 | COMP | 2019-11-23 | INPR | 2019-07-25 | COMP | Rule 16 | 44 | 134 | 4 | 1 |  |  | 391
3245 | 2018-01-05 | 2018-03-27 | 2019-11-22 | 2019-11-22 | COMP | 2019-11-22 | COMP | 2019-12-05 | COMP | 2021-12-13 | COMP | 2022-07-16 | COMP | Rule 15/16 | 56 | 420 | 1 | 8 | 509 | 150 | 1139
3531 | 2018-01-05 | 2018-05-11 | 2018-09-28 | 2018-09-28 | COMP | 2018-12-27 | COMP | 2019-06-12 | COMP | 2019-10-19 | INPR | 2019-07-03 | COMP | Rule 16 | 89 | 98 | 61 | 116 |  |  | 376
4700 | 2018-01-05 | 2018-03-15 | 2018-04-16 | 2018-04-16 | COMP | 2018-07-12 | COMP | 2019-03-14 | COMP | 2019-02-19 | COMP | 2019-04-15 | COMP | Rule 16 | 48 | 23 | 62 | 168 | 0 | 23 | 320
4775 | 2018-01-05 | 2018-03-29 | 2018-06-02 | 2018-06-02 | COMP | 2018-12-27 | COMP | 2019-01-03 | COMP | 2023-04-30 | INPR | 2020-11-07 | COMP | Rule 15/16 | 58 | 46 | 143 | 5 |  |  | 717
4841 | 2018-01-05 | 2018-04-04 | 2018-10-20 | 2018-10-20 | COMP | 2018-12-03 | COMP | 2019-01-04 | COMP | 2019-04-05 | COMP | 2019-05-08 | COMP | Rule 16 | 62 | 140 | 28 | 23 | 64 | 24 | 337
5085 | 2018-01-05 | 2018-04-30 | 2018-10-22 | 2018-10-22 | COMP | 2018-12-04 | COMP | 2019-02-14 | COMP | 2019-11-24 | INPR | 2019-07-23 | COMP | Rule 15/16 | 80 | 123 | 29 | 50 |  |  | 389
5186 | 2018-01-05 | 2018-05-08 | 2018-06-06 | 2018-06-06 | COMP | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-10-21 | INPR | 2019-07-08 | COMP | Rule 16 | 86 | 21 | 199 | 1 |  |  | 378
5833 | 2018-01-05 | 2018-07-06 | 2018-11-15 | 2018-11-15 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-03-20 | COMP | 2019-04-08 | COMP | Rule 16 | 127 | 93 | 77 | 1 | 8 | 14 | 315
6420 | 2018-01-05 | 2018-08-17 | 2018-11-14 | 2018-11-14 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2020-10-23 | COMP | 2020-11-25 | COMP | Rule 15/16 | 157 | 62 | 115 | 1 | 376 | 23 | 729
9815 | 2018-01-05 | 2019-02-19 | 2019-03-26 | 2019-03-26 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-09-16 | COMP | 2019-09-22 | COMP | Rule 16 | 281 | 26 | 126 | 1 | 0 | 1 | 431
14069 | 2018-01-05 | 2019-08-23 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2019-11-08 | COMP | 2019-11-21 | COMP | Rule 16 | 412 | 47 | 8 | 1 | 2 | 9 | 474
20083 | 2018-01-05 | 2020-06-03 | 2020-07-06 | 2020-07-06 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP |  |  | 2021-05-14 | COMP | Rule 16 | 606 | 24 | 41 | 1 |  |  | 845
3042 | 2018-01-06 | 2018-03-01 | 2018-08-11 | 2018-08-11 | COMP | 2020-10-08 | COMP | 2021-04-27 | COMP | 2021-04-20 | COMP | 2021-06-23 | COMP | Rule 15/16 | 37 | 115 | 544 | 137 | 0 | 41 | 871
3202 | 2018-01-07 | 2018-03-21 | 2018-06-06 | 2018-06-06 | COMP | 2018-06-21 | COMP | 2018-07-25 | COMP | 2021-06-18 | COMP | 2021-07-14 | COMP | Rule 16 | 51 | 55 | 12 | 24 | 730 | 18 | 885
2786 | 2018-01-08 | 2018-01-31 | 2018-04-16 | 2018-04-16 | COMP | 2018-08-23 | COMP | 2018-09-17 | COMP | 2018-09-27 | COMP | 2019-03-29 | COMP | Rule 16 | 17 | 53 | 92 | 17 | 9 | 125 | 308
3109 | 2018-01-08 | 2018-03-09 | 2018-08-03 | 2018-08-03 | COMP | 2018-11-21 | COMP | 2019-04-26 | COMP | 2019-03-11 | COMP | 2019-05-15 | COMP | Rule 15/16 | 43 | 104 | 77 | 107 | 0 | 14 | 341
3251 | 2018-01-08 | 2018-03-28 | 2018-06-26 | 2018-06-26 | COMP | 2018-11-01 | COMP | 2019-09-23 | COMP | 2019-10-25 | COMP | 2019-12-10 | COMP | Rule 15/16 | 56 | 64 | 91 | 223 | 25 | 30 | 484
3321 | 2018-01-08 | 2018-04-09 | 2019-01-23 | 2019-01-23 | COMP | 2019-03-05 | COMP | 2019-05-20 | COMP | 2023-11-11 | INPR | 2020-02-26 | COMP | Rule 16 | 64 | 199 | 29 | 55 |  |  | 536
3527 | 2018-01-08 | 2018-05-10 | 2018-09-21 | 2019-03-07 | COMP | 2019-01-31 | COMP | 2019-06-20 | COMP | 2019-11-23 | INPR | 2019-07-23 | COMP | Rule 15/16 | 87 | 94 |  | 99 |  |  | 388
4534 | 2018-01-08 | 2018-01-23 | 2018-05-18 | 2020-04-09 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-07-08 | COMP | 2020-09-30 | COMP | Rule 15/16 | 11 | 83 | 69 | 1 | 0 | 55 | 689
4628 | 2018-01-08 | 2018-02-20 | 2018-08-27 | 2018-08-27 | COMP | 2018-10-17 | COMP | 2018-11-08 | COMP | 2018-11-26 | COMP | 2021-01-08 | COMP | Rule 16 | 30 | 133 | 37 | 17 | 10 | 534 | 756
4783 | 2018-01-08 | 2018-03-30 | 2019-08-12 | 2019-11-01 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-08-24 | COMP | 2020-09-14 | COMP | Rule 15/16 | 58 | 345 | 87 | 1 | 118 | 15 | 677
5117 | 2018-01-08 | 2018-05-01 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-09-06 | COMP | 2019-11-15 | COMP | Rule 16 | 80 | 132 | 39 | 1 | 172 | 50 | 469
5430 | 2018-01-08 | 2018-06-01 | 2018-09-07 | 2018-09-07 | COMP | 2018-11-05 | COMP | 2019-01-25 | COMP | 2019-02-13 | COMP | 2019-03-08 | COMP | Rule 15/16 | 102 | 69 | 42 | 54 | 14 | 17 | 293
5587 | 2018-01-08 | 2018-06-15 | 2018-11-16 | 2018-11-16 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-07-10 | COMP | 2019-08-26 | COMP | Rule 16 | 112 | 108 | 35 | 1 | 127 | 34 | 412
2697 | 2018-01-09 | 2018-01-19 | 2018-09-15 | 2019-10-18 | COMP | 2019-10-25 | COMP | 2018-11-08 | COMP | 2019-10-29 | COMP | 2019-11-22 | COMP | Rule 16 | 8 | 167 | 6 |  | 244 | 18 | 473
2721 | 2018-01-09 | 2018-01-23 | 2019-04-16 | 2019-04-16 | COMP | 2019-07-25 | NOTN | 2019-07-31 | COMP | 2019-08-17 | COMP | 2019-12-05 | COMP | Other | 10 | 310 |  | 75 | 13 | 75 | 480
2818 | 2018-01-09 | 2018-02-04 | 2018-04-10 | 2018-04-10 | COMP | 2019-01-04 | COMP | 2019-01-09 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | Rule 16 | 18 | 46 | 186 | 4 | 371 | 1 | 622
2822 | 2018-01-09 | 2018-02-05 | 2018-04-18 | 2018-04-18 | COMP | 2018-06-05 | COMP | 2019-08-07 | COMP | 2019-07-17 | COMP | 2019-08-22 | COMP | Rule 16 | 19 | 52 | 34 | 296 | 0 | 12 | 409
2892 | 2018-01-09 | 2018-02-12 | 2018-04-21 | 2018-04-21 | COMP | 2018-05-22 | COMP | 2019-01-03 | COMP | 2019-01-22 | COMP | 2019-04-09 | COMP | Rule 16 | 24 | 49 | 22 | 155 | 13 | 55 | 314
2901 | 2018-01-09 | 2018-02-13 | 2018-04-08 | 2018-10-11 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-05-28 | COMP | 2019-05-31 | COMP | Rule 15/16 | 25 | 38 | 87 | 1 | 70 | 4 | 351
3010 | 2018-01-09 | 2018-02-27 | 2018-04-30 | 2018-04-30 | COMP | 2018-08-23 | COMP | 2018-09-18 | COMP | 2022-12-22 | COMP | 2023-04-05 | COMP | Rule 16 | 34 | 45 | 82 | 18 | 1072 | 71 | 1317
3093 | 2018-01-09 | 2018-03-07 | 2018-05-20 | 2018-05-20 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2022-03-11 | COMP | 2022-04-04 | COMP | Rule 16 | 40 | 53 | 520 | 1 | 439 | 17 | 1066
3441 | 2018-01-09 | 2018-04-26 | 2018-05-26 | 2018-05-26 | COMP | 2018-07-11 | COMP | 2018-07-11 | COMP | 2018-11-14 | COMP | 2019-01-03 | COMP | Other | 76 | 22 | 31 | 1 | 89 | 33 | 248
3796 | 2018-01-09 | 2018-07-17 | 2018-08-10 | 2018-08-10 | COMP | 2019-02-22 | COMP | 2019-02-25 | COMP | 2019-03-11 | COMP | 2019-03-12 | COMP | Rule 16 | 132 | 19 | 133 | 2 | 11 | 2 | 294
3805 | 2018-01-09 | 2018-07-22 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-15 | COMP | 2018-11-28 | COMP | 2018-12-20 | COMP | 2019-02-07 | COMP | Rule 16 | 135 | 72 | 11 | 8 | 17 | 33 | 272
4156 | 2018-01-09 | 2019-04-17 | 2019-04-26 | 2019-04-26 | COMP | 2019-07-11 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-08-03 | COMP | Rule 16 | 320 | 8 | 53 | 5 | 1 | 13 | 395
4538 | 2018-01-09 | 2018-01-24 | 2018-03-16 | 2018-03-16 | COMP | 2019-01-24 | COMP | 2020-01-20 | COMP | 2020-02-04 | COMP | 2020-02-18 | COMP | Rule 16 | 11 | 37 | 216 | 248 | 11 | 10 | 529
4738 | 2018-01-09 | 2018-03-23 | 2018-07-10 | 2018-09-04 | COMP | 2018-10-30 | COMP | 2019-03-05 | COMP | 2019-02-13 | COMP | 2019-03-14 | COMP | Rule 16 | 52 | 76 | 41 | 84 | 0 | 8 | 296
4804 | 2018-01-09 | 2018-03-31 | 2018-08-22 | 2018-08-22 | COMP | 2018-08-24 | COMP | 2018-09-26 | COMP | 2018-09-26 | COMP | 2019-01-28 | COMP | Rule 15/16 | 57 | 101 | 3 | 23 | 1 | 83 | 264
5076 | 2018-01-09 | 2018-04-28 | 2019-10-10 | 2020-01-14 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-12-11 | COMP | 2020-12-16 | COMP | Rule 16 | 77 | 366 | 29 | 1 | 204 | 4 | 740
5086 | 2018-01-09 | 2018-04-30 | 2018-07-27 | 2018-07-27 | COMP | 2018-09-06 | COMP | 2019-10-03 | COMP | 2020-05-22 | COMP | 2020-06-17 | COMP | Rule 16 | 78 | 63 | 29 | 271 | 160 | 18 | 614
5273 | 2018-01-09 | 2018-05-15 | 2019-02-15 | 2021-01-22 | COMP | 2021-02-01 | COMP | 2021-02-09 | COMP | 2021-02-08 | COMP | 2021-04-02 | COMP | Rule 15/16 | 89 | 190 | 7 | 7 | 0 | 38 | 813
5591 | 2018-01-09 | 2018-06-18 | 2018-08-07 | 2018-08-07 | COMP | 2018-12-18 | COMP | 2019-04-02 | COMP | 2020-01-23 | COMP | 2020-01-24 | COMP | Rule 16 | 112 | 36 | 92 | 72 | 204 | 2 | 513
5700 | 2018-01-09 | 2018-06-25 | 2018-10-10 | 2018-10-10 | COMP | 2018-10-24 | COMP | 2018-11-08 | COMP | 2019-01-08 | COMP | 2019-04-09 | COMP | Rule 16 | 117 | 76 | 11 | 12 | 39 | 64 | 314
5714 | 2018-01-09 | 2018-06-26 | 2019-01-24 | 2019-01-24 | COMP | 2019-07-10 | COMP | 2019-09-26 | COMP | 2019-10-29 | COMP | 2019-12-09 | COMP | Rule 16 | 118 | 145 | 117 | 56 | 24 | 27 | 482
7040 | 2018-01-09 | 2018-09-24 | 2019-01-24 | 2019-01-24 | COMP | 2018-12-28 | NOTN | 2019-04-08 | COMP | 2019-01-24 | COMP | 2019-09-04 | COMP | Other | 180 | 83 |  | 52 | 0 | 105 | 417
7064 | 2018-01-09 | 2018-09-25 | 2019-01-24 | 2019-01-24 | COMP | 2018-12-28 | NOTN | 2019-06-20 | COMP | 2019-01-25 | COMP | 2019-07-31 | COMP | Other | 181 | 82 |  | 104 | 0 | 29 | 393
15843 | 2018-01-09 | 2019-11-24 | 2020-02-18 | 2020-02-18 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-07-02 | COMP | 2020-07-27 | COMP | Rule 16 | 473 | 56 | 37 | 1 | 61 | 18 | 642
2812 | 2018-01-10 | 2018-02-03 | 2018-04-23 | 2018-08-02 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-04-04 | COMP | 2019-05-03 | COMP | Rule 16 | 17 | 55 | 95 | 1 | 74 | 22 | 331
2841 | 2018-01-10 | 2018-02-06 | 2018-06-27 | 2019-06-24 | COMP | 2019-09-21 | REQD | 2019-04-25 | COMP | 2019-05-01 | COMP | 2019-05-17 | COMP | Rule 16 | 19 | 100 |  |  | 5 | 13 | 341
2862 | 2018-01-10 | 2018-02-08 | 2018-06-01 | 2018-10-02 | COMP | 2018-06-21 | COMP | 2018-08-13 | COMP | 2018-12-18 | COMP | 2019-01-29 | COMP | Rule 15/16 | 21 | 80 |  | 37 | 88 | 28 | 264
2876 | 2018-01-10 | 2018-02-09 | 2018-04-11 | 2018-04-11 | COMP | 2018-11-29 | COMP | 2018-12-03 | COMP | 2019-06-29 | INPR | 2019-02-06 | COMP | Rule 16 | 22 | 43 | 161 | 3 |  |  | 270
3087 | 2018-01-10 | 2018-03-06 | 2018-07-14 | 2019-05-25 | COMP | 2019-06-10 | COMP | 2020-02-20 | COMP | 2020-01-10 | COMP | 2020-04-17 | COMP | Rule 15/16 | 38 | 92 | 10 | 175 | 0 | 42 | 571
3102 | 2018-01-10 | 2018-03-08 | 2018-07-14 | 2018-07-14 | COMP | 2018-07-18 | COMP | 2019-04-03 | COMP | 2019-04-01 | COMP | 2019-06-28 | COMP | Rule 16 | 40 | 90 | 3 | 178 | 0 | 62 | 370
3252 | 2018-01-10 | 2018-03-28 | 2018-11-04 | 2019-02-27 | COMP | 2019-04-16 | COMP | 2019-07-10 | COMP | 2019-07-24 | COMP | 2019-09-28 | COMP | Rule 15/16 | 54 | 155 | 35 | 60 | 11 | 47 | 433
3286 | 2018-01-10 | 2018-04-02 | 2018-08-28 | 2018-08-28 | COMP | 2018-08-19 | NOTN | 2018-08-28 | COMP | 2018-09-17 | COMP | 2022-05-04 | COMP | Other | 57 | 105 |  | 1 | 14 | 914 | 1087
3437 | 2018-01-10 | 2018-04-27 | 2018-10-09 | 2018-10-09 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-12-28 | INPR | 2019-08-23 | COMP | Rule 16 | 76 | 115 | 102 | 1 |  |  | 409
3487 | 2018-01-10 | 2018-05-07 | 2018-08-28 | 2018-08-28 | COMP | 2018-09-21 | COMP | 2018-09-25 | COMP | 2018-11-25 | COMP | 2019-05-02 | COMP | Rule 16 | 82 | 80 | 18 | 3 | 41 | 110 | 330
3985 | 2018-01-10 | 2018-11-08 | 2019-01-26 | 2019-01-26 | COMP | 2019-03-07 | COMP | 2019-03-13 | COMP | 2019-06-21 | COMP | 2019-06-28 | COMP | Rule 16 | 212 | 51 | 28 | 5 | 72 | 6 | 370
4686 | 2018-01-10 | 2018-03-13 | 2018-07-19 | 2018-07-19 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2019-02-06 | COMP | 2019-03-13 | COMP | Rule 16 | 43 | 91 | 82 | 1 | 57 | 25 | 294
4687 | 2018-01-10 | 2018-03-13 | 2018-06-06 | 2019-05-03 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-05-01 | COMP | 2019-06-15 | COMP | Rule 16 | 43 | 61 | 8 | 1 | 0 | 23 | 360
5067 | 2018-01-10 | 2018-04-28 | 2019-05-11 | 2019-05-11 | COMP | 2019-07-26 | COMP | 2019-08-23 | COMP | 2020-01-10 | COMP | 2020-02-22 | COMP | Rule 15/16 | 76 | 260 | 53 | 21 | 95 | 29 | 531
5146 | 2018-01-10 | 2018-05-03 | 2018-08-31 | 2018-08-31 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-06-06 | COMP | 2019-07-16 | COMP | Rule 16 | 80 | 85 | 67 | 1 | 125 | 28 | 381
6397 | 2018-01-10 | 2018-08-15 | 2018-10-22 | 2018-10-22 | COMP | 2018-11-01 | COMP | 2018-12-20 | COMP | 2018-11-07 | COMP | 2019-01-29 | COMP | Rule 16 | 152 | 48 | 9 | 33 | 0 | 26 | 264
7486 | 2018-01-10 | 2018-10-17 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-21 | COMP | 2019-01-02 | COMP | 2019-03-19 | COMP | 2019-04-29 | COMP | Rule 16 | 196 | 22 | 23 | 7 | 53 | 30 | 327
9772 | 2018-01-10 | 2019-02-15 | 2019-06-03 | 2019-07-23 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-09-04 | COMP | 2019-09-18 | COMP | Rule 16 | 277 | 75 | 21 | 1 | 11 | 11 | 426
10830 | 2018-01-10 | 2019-04-01 | 2019-11-08 | 2019-11-08 | COMP | 2019-12-23 | NOTN | 2020-02-11 | COMP | 2019-12-23 | COMP | 2020-06-05 | COMP | Other | 307 | 157 |  | 62 | 0 | 82 | 605
18696 | 2018-01-10 | 2020-04-03 | 2020-09-03 | 2020-10-26 | COMP | 2020-12-03 | COMP | 2021-02-05 | COMP | 2021-02-03 | COMP | 2021-02-18 | COMP | Other | 561 | 109 | 26 | 44 | 0 | 9 | 781
2789 | 2018-01-11 | 2018-01-31 | 2018-08-09 | 2018-08-09 | COMP | 2018-09-13 | COMP | 2018-09-14 | COMP | 2020-01-18 | INPR | 2019-02-28 | COMP | Rule 16 | 14 | 134 | 25 | 2 |  |  | 284
2806 | 2018-01-11 | 2018-02-02 | 2018-05-26 | 2018-12-15 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2019-06-03 | COMP | 2019-07-19 | COMP | Rule 16 | 16 | 80 | 125 | 1 | 0 | 25 | 383
2975 | 2018-01-11 | 2018-02-23 | 2018-05-20 | 2018-05-20 | COMP | 2018-08-02 | COMP | 2018-08-02 | COMP | 2019-01-04 | COMP | 2022-04-07 | COMP | Rule 16 | 30 | 61 | 52 | 1 | 106 | 821 | 1067
3048 | 2018-01-11 | 2018-03-02 | 2018-12-06 | 2018-12-06 | COMP | 2019-04-17 | COMP | 2019-04-19 | INPR | 2020-02-29 | REQD | 2019-06-04 | COMP | Rule 15/16 | 35 | 194 | 91 |  |  |  | 351
3056 | 2018-01-11 | 2018-03-06 | 2018-07-16 | 2018-07-16 | COMP | 2018-12-18 | COMP | 2018-12-20 | COMP | 2020-06-22 | COMP | 2021-01-18 | COMP | Rule 15/16 | 37 | 93 | 108 | 3 | 378 | 144 | 758
3090 | 2018-01-11 | 2018-03-06 | 2018-04-24 | 2018-04-24 | COMP | 2019-10-02 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2019-11-04 | COMP | Rule 16 | 37 | 36 | 364 | 3 | 1 | 22 | 458
3137 | 2018-01-11 | 2018-03-12 | 2018-10-09 | 2018-10-09 | COMP | 2018-12-28 | COMP | 2019-01-08 | COMP | 2019-11-07 | COMP | 2019-11-24 | COMP | Rule 16 | 41 | 149 | 55 | 7 | 213 | 11 | 471
3281 | 2018-01-11 | 2018-03-31 | 2018-09-23 | 2018-09-23 | COMP | 2019-03-12 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-16 | COMP | Rule 16 | 55 | 122 | 115 | 105 | 1 | 28 | 423
3354 | 2018-01-11 | 2018-04-11 | 2019-02-10 | 2019-02-10 | COMP | 2019-03-20 | COMP | 2019-05-17 | NOTN | 2019-05-21 | COMP | 2019-05-24 | COMP | Rule 16 | 63 | 209 | 27 |  |  |  | 345
3385 | 2018-01-11 | 2018-04-17 | 2018-07-27 | 2018-07-27 | COMP | 2019-05-13 | COMP | 2018-09-20 | COMP | 2019-07-03 | COMP | 2019-08-07 | COMP | Rule 16 | 67 | 72 | 199 |  | 197 | 25 | 396
3426 | 2018-01-11 | 2018-04-24 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-23 | COMP | 2018-12-04 | COMP | 2018-11-04 | COMP | 2019-01-09 | COMP | Rule 16 | 72 | 106 | 23 | 28 | 0 | 25 | 250
3795 | 2018-01-11 | 2018-07-17 | 2018-08-27 | 2018-08-27 | COMP | 2019-03-05 | COMP | 2019-06-29 | REQD | 2019-03-11 | COMP | 2019-03-12 | COMP | Rule 15/16 | 130 | 30 | 129 |  |  |  | 292
4527 | 2018-01-11 | 2018-01-23 | 2018-10-30 | 2018-10-30 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-10-21 | INPR | 2019-06-17 | COMP | Rule 15/16 | 8 | 197 | 89 | 1 |  |  | 360
4907 | 2018-01-11 | 2018-04-11 | 2018-09-14 | 2018-09-14 | COMP | 2018-09-21 | COMP | 2018-09-21 | COMP | 2018-12-18 | COMP | 2019-01-08 | COMP | Rule 16 | 63 | 110 | 6 | 1 | 60 | 14 | 249
4933 | 2018-01-11 | 2018-04-12 | 2018-10-27 | 2018-10-27 | COMP | 2019-02-01 | COMP | 2019-04-11 | COMP | 2019-03-25 | COMP | 2019-05-14 | COMP | Rule 16 | 64 | 139 | 64 | 49 | 0 | 24 | 337
7206 | 2018-01-11 | 2018-10-03 | 2018-11-26 | 2018-12-31 | COMP | 2019-03-11 | COMP | 2019-06-05 | COMP | 2019-03-26 | COMP | 2019-06-18 | COMP | Rule 16 | 185 | 36 | 48 | 62 | 0 | 10 | 361
7569 | 2018-01-11 | 2018-10-19 | 2019-01-09 | 2019-02-14 | COMP | 2020-07-29 | COMP | 2019-06-24 | COMP | 2019-12-11 | COMP | 2020-01-29 | COMP | Rule 15/16 | 197 | 54 | 368 |  | 118 | 33 | 514
2801 | 2018-01-12 | 2018-02-01 | 2018-06-12 | 2018-06-12 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2019-01-04 | COMP | 2019-03-18 | COMP | Rule 16 | 14 | 92 | 78 | 1 | 65 | 50 | 295
2907 | 2018-01-12 | 2018-02-14 | 2018-10-09 | 2018-10-09 | COMP | 2019-05-17 | COMP | 2020-07-15 | COMP | 2020-07-02 | COMP | 2020-08-20 | COMP | Rule 15/16 | 23 | 166 | 152 | 293 | 0 | 27 | 657
2953 | 2018-01-12 | 2018-02-22 | 2018-08-07 | 2018-08-07 | COMP | 2018-12-17 | COMP | 2019-01-30 | COMP | 2019-05-29 | COMP | 2019-08-05 | COMP | Rule 15/16 | 28 | 117 | 91 | 30 | 84 | 48 | 393
3228 | 2018-01-12 | 2018-03-26 | 2018-03-29 | 2018-03-29 | COMP | 2018-12-11 | COMP | 2019-03-21 | COMP | 2020-03-28 | INPR | 2019-12-05 | COMP | Rule 16 | 50 | 4 | 178 | 69 |  |  | 477
3371 | 2018-01-12 | 2018-04-14 | 2018-04-16 | 2018-04-16 | COMP | 2018-05-23 | COMP | 2018-05-23 | COMP | 2019-01-14 | COMP | 2019-01-02 | COMP | Rule 16 | 64 | 1 | 28 | 1 | 161 |  | 244
3373 | 2018-01-12 | 2018-04-16 | 2018-12-30 | 2020-03-01 | REQD | 2019-02-22 | COMP | 2019-03-27 | COMP | 2019-04-02 | COMP | 2019-05-19 | COMP | Rule 15/16 | 65 |  |  |  | 5 | 34 | 339
3401 | 2018-01-12 | 2018-04-18 | 2018-10-31 | 2018-10-31 | COMP | 2018-12-17 | COMP | 2019-09-25 | COMP | 2019-12-20 | COMP | 2020-02-28 | COMP | Rule 15/16 | 67 | 138 | 31 | 196 | 60 | 47 | 534
3853 | 2018-01-12 | 2018-08-16 | 2018-09-28 | 2018-09-28 | COMP | 2019-02-28 | COMP | 2019-04-05 | COMP | 2019-03-11 | COMP | 2019-04-28 | COMP | Rule 15/16 | 151 | 31 | 103 | 27 | 0 | 16 | 324
3882 | 2018-01-12 | 2018-09-12 | 2019-04-04 | 2019-04-04 | COMP | 2020-02-14 | COMP | 2020-03-27 | COMP | 2020-11-17 | COMP | 2020-12-16 | COMP | Rule 16 | 169 | 140 | 218 | 30 | 165 | 20 | 737
4776 | 2018-01-12 | 2018-03-29 | 2018-05-25 | 2018-05-25 | COMP | 2018-07-05 | COMP | 2018-07-09 | COMP | 2020-01-19 | INPR | 2019-10-03 | COMP | Rule 16 | 53 | 42 | 28 | 3 |  |  | 435
4972 | 2018-01-12 | 2018-04-17 | 2019-02-14 | 2019-04-30 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-05-22 | COMP | 2019-07-30 | COMP | Rule 16 | 66 | 209 | 23 | 1 | 0 | 42 | 389
5323 | 2018-01-12 | 2018-05-22 | 2018-10-08 | 2018-10-08 | COMP | 2019-05-17 | COMP | 2020-07-24 | COMP | 2020-10-20 | COMP | 2020-12-05 | COMP | Rule 16 | 91 | 97 | 153 | 300 | 62 | 31 | 729
5352 | 2018-01-12 | 2018-05-23 | 2018-08-17 | 2018-08-17 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-03-08 | COMP | Rule 16 | 92 | 61 | 120 | 1 | 1 | 19 | 289
6188 | 2018-01-12 | 2018-08-02 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-21 | COMP | 2018-12-06 | COMP | 2019-01-07 | COMP | 2019-03-21 | COMP | Rule 16 | 141 | 34 | 45 | 10 | 21 | 52 | 298
6486 | 2018-01-12 | 2018-08-21 | 2018-12-16 | 2018-12-16 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-03-05 | COMP | 2019-04-12 | COMP | Rule 16 | 154 | 80 | 19 | 1 | 35 | 29 | 314
6992 | 2018-01-12 | 2018-09-22 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-09 | COMP | 2019-07-11 | COMP | 2021-01-12 | COMP | 2021-02-05 | COMP | Rule 16 | 176 | 50 | 24 | 128 | 379 | 18 | 771
10138 | 2018-01-12 | 2019-03-04 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-28 | COMP | 2019-09-03 | COMP | 2019-09-23 | COMP | 2019-12-13 | COMP | Rule 15/16 | 285 | 40 | 22 | 69 | 15 | 57 | 483
11741 | 2018-01-12 | 2019-05-09 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-15 | COMP | 2019-08-22 | COMP | 2019-08-28 | COMP | 2019-09-27 | COMP | Rule 15/16 | 333 | 48 | 22 | 6 | 5 | 22 | 431
2968 | 2018-01-13 | 2018-02-23 | 2018-07-18 | 2018-07-18 | COMP | 2018-11-15 | COMP | 2018-12-21 | COMP |  | INPR | 2019-04-11 | COMP | Rule 15/16 | 28 | 102 | 85 | 25 |  |  | 312
4652 | 2018-01-13 | 2018-03-01 | 2018-06-12 | 2018-07-16 | COMP | 2019-02-20 | COMP | 2019-08-20 | COMP | 2021-02-27 | COMP | 2021-09-03 | COMP | Rule 16 | 32 | 73 | 150 | 128 | 382 | 133 | 917
2685 | 2018-01-15 | 2018-01-18 | 2018-12-21 | 2018-12-21 | COMP | 2019-03-22 | COMP | 2019-03-27 | NOTN | 2019-04-05 | COMP | 2019-04-12 | COMP | Rule 16 | 3 | 235 | 62 |  |  |  | 313
2686 | 2018-01-15 | 2018-01-18 | 2018-04-05 | 2018-04-05 | COMP | 2018-12-28 | COMP | 2019-01-07 | NOTN | 2019-01-18 | COMP | 2019-01-24 | COMP | Rule 16 | 3 | 55 | 185 |  |  |  | 258
3142 | 2018-01-15 | 2018-03-13 | 2018-06-14 | 2018-06-08 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-06-30 | COMP | 2020-06-10 | COMP | Rule 16 | 40 | 67 | 316 | 1 | 203 |  | 605
3241 | 2018-01-15 | 2018-03-27 | 2019-02-10 | 2019-02-10 | COMP | 2019-07-02 | COMP | 2019-03-20 | COMP | 2019-06-14 | COMP | 2019-08-13 | COMP | Rule 15/16 | 50 | 220 | 100 |  | 62 | 42 | 398
3248 | 2018-01-15 | 2018-03-27 | 2018-11-12 | 2018-11-12 | COMP | 2019-05-23 | COMP | 2020-02-19 | COMP | 2020-02-28 | COMP | 2020-04-08 | COMP | Rule 15/16 | 50 | 161 | 132 | 185 | 8 | 29 | 561
3374 | 2018-01-15 | 2018-04-16 | 2018-07-09 | 2018-07-09 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-07-21 | INPR | 2019-04-23 | COMP | Rule 15/16 | 64 | 59 | 99 | 1 |  |  | 320
3446 | 2018-01-15 | 2018-04-27 | 2019-02-21 | 2019-02-21 | COMP | 2019-06-11 | COMP | 2020-03-25 | COMP | 2020-03-24 | COMP | 2020-06-16 | COMP | Rule 15/16 | 73 | 205 | 78 | 198 | 0 | 59 | 609
4559 | 2018-01-15 | 2018-01-29 | 2018-07-13 | 2018-07-13 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-07-02 | COMP | 2019-07-22 | COMP | Rule 16 | 10 | 117 | 132 | 1 | 113 | 14 | 382
4591 | 2018-01-15 | 2018-02-09 | 2018-04-10 | 2018-04-10 | COMP | 2018-04-17 | COMP | 2018-04-17 | COMP | 2019-08-30 | COMP | 2019-09-03 | COMP | Rule 16 | 19 | 42 | 6 | 1 | 347 | 2 | 412
4641 | 2018-01-15 | 2018-02-24 | 2018-10-02 | 2019-10-18 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-12-15 | COMP | Rule 16 | 28 | 154 | 10 | 1 | 1 | 29 | 482
5570 | 2018-01-15 | 2018-06-14 | 2018-09-20 | 2018-09-20 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-05-14 | COMP | 2019-06-03 | COMP | Rule 16 | 106 | 69 | 55 | 1 | 108 | 14 | 348
13423 | 2018-01-15 | 2019-07-25 | 2019-09-25 | 2020-04-17 | COMP | 2020-06-04 | COMP | 2020-06-04 | COMP | 2020-10-16 | COMP | 2020-11-19 | COMP | Rule 16 | 385 | 44 | 34 | 1 | 96 | 24 | 719
2736 | 2018-01-16 | 2018-01-25 | 2018-05-03 | 2018-05-03 | COMP | 2018-08-09 | COMP | 2018-11-14 | COMP | 2018-10-05 | COMP | 2019-02-25 | COMP | Rule 15/16 | 8 | 70 | 69 | 68 | 0 | 68 | 279
2767 | 2018-01-16 | 2018-01-30 | 2018-02-02 | 2018-02-02 | COMP | 2018-03-01 | COMP | 2018-03-01 | COMP | 2022-05-22 | INPR | 2021-04-18 | COMP | Rule 16 | 11 | 4 | 19 | 1 |  |  | 819
2934 | 2018-01-16 | 2018-02-20 | 2018-04-24 | 2018-11-08 | COMP | 2018-08-08 | COMP | 2018-12-06 | COMP | 2019-04-20 | INPR | 2019-01-04 | COMP | Rule 16 | 25 | 46 |  | 83 |  |  | 245
3100 | 2018-01-16 | 2018-03-08 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-19 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-08-02 | COMP | Rule 16 | 37 | 149 | 51 | 116 | 1 | 42 | 391
3231 | 2018-01-16 | 2018-03-28 | 2018-08-29 | 2018-08-29 | COMP | 2018-09-06 | COMP | 2018-10-08 | COMP | 2018-10-30 | COMP | 2019-01-10 | COMP | Rule 16 | 51 | 109 | 6 | 23 | 17 | 48 | 249
3405 | 2018-01-16 | 2018-04-19 | 2018-05-23 | 2018-05-23 | COMP | 2018-11-30 | COMP | 2019-11-21 | INPR | 2023-11-11 | CANC | 2020-01-06 | COMP | Rule 15/16 | 67 | 25 | 132 |  |  |  | 496
3669 | 2018-01-16 | 2018-06-05 | 2018-12-24 | 2018-12-24 | COMP | 2019-02-25 | COMP | 2021-12-10 | COMP | 2021-12-08 | COMP | 2022-01-10 | COMP | Rule 16 | 99 | 140 | 42 | 705 | 0 | 22 | 1004
3670 | 2018-01-16 | 2018-06-05 | 2018-11-28 | 2018-11-09 | COMP | 2018-12-14 | COMP | 2019-07-08 | COMP |  |  | 2019-08-05 | COMP | Rule 15/16 | 99 | 122 | 23 | 141 |  |  | 392
3816 | 2018-01-16 | 2018-07-28 | 2019-07-31 | 2019-07-31 | COMP | 2020-09-30 | COMP | 2020-10-14 | COMP | 2021-04-13 | COMP | 2022-04-27 | COMP | Rule 15/16 | 136 | 253 | 296 | 11 | 123 | 264 | 1079
3877 | 2018-01-16 | 2018-09-11 | 2019-07-12 | 2019-07-12 | COMP | 2020-09-14 | COMP | 2020-09-25 | COMP | 2021-11-23 | COMP | 2021-12-10 | COMP | Rule 15/16 | 167 | 210 | 297 | 10 | 292 | 12 | 983
4642 | 2018-01-16 | 2018-02-24 | 2018-10-18 | 2019-10-25 | COMP | 2019-11-07 | COMP | 2019-11-19 | COMP | 2019-11-05 | COMP | 2020-01-07 | COMP | Rule 15/16 | 28 | 166 | 10 | 8 | 0 | 32 | 497
4644 | 2018-01-16 | 2018-02-26 | 2018-04-30 | 2018-04-30 | COMP | 2019-02-22 | COMP | 2020-05-22 | COMP | 2020-08-11 | COMP | 2020-08-13 | COMP | Rule 16 | 29 | 46 | 205 | 316 | 57 | 3 | 651
5469 | 2018-01-16 | 2018-06-01 | 2018-11-16 | 2018-11-16 | COMP | 2019-05-02 | COMP | 2019-07-01 | COMP |  | INPR | 2019-08-07 | COMP | Rule 16 | 97 | 118 | 114 | 42 |  |  | 394
5632 | 2018-01-16 | 2018-06-23 | 2018-10-30 | 2018-10-30 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-01-23 | COMP | 2019-03-08 | COMP | Rule 16 | 112 | 90 | 24 | 1 | 33 | 32 | 288
5650 | 2018-01-16 | 2018-06-23 | 2018-10-01 | 2018-10-01 | COMP | 2019-08-16 | COMP | 2019-09-14 | COMP | 2023-12-02 | INPR | 2020-07-10 | COMP | Rule 16 | 112 | 69 | 221 | 20 |  |  | 627
5674 | 2018-01-16 | 2018-06-25 | 2019-01-31 | 2019-01-31 | COMP | 2019-03-05 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2020-01-07 | COMP | Rule 16 | 113 | 151 | 23 | 105 | 1 | 109 | 497
6317 | 2018-01-16 | 2018-08-09 | 2018-10-10 | 2018-11-06 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-05-10 | COMP | 2019-06-03 | COMP | Rule 16 | 145 | 44 | 88 | 1 | 40 | 16 | 348
6385 | 2018-01-16 | 2018-08-14 | 2018-09-14 | 2018-09-14 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-01-26 | COMP | 2019-04-10 | COMP | Rule 16 | 148 | 23 | 94 | 1 | 0 | 49 | 311
7568 | 2018-01-16 | 2018-10-19 | 2019-01-08 | 2019-01-08 | COMP | 2019-01-30 | COMP | 2019-03-12 | COMP | 2019-03-21 | COMP | 2019-04-08 | COMP | Rule 16 | 195 | 53 | 16 | 29 | 8 | 13 | 309
8001 | 2018-01-16 | 2018-11-09 | 2019-01-14 | 2019-01-14 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-07-23 | COMP | 2020-01-10 | COMP | Rule 16 | 210 | 42 | 9 | 1 | 125 | 118 | 500
8376 | 2018-01-16 | 2018-11-28 | 2018-12-18 | 2018-12-18 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-24 | COMP | 2019-02-20 | COMP | Rule 16 | 220 | 15 | 3 | 1 | 23 | 19 | 276
9796 | 2018-01-16 | 2019-02-16 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-19 | COMP | 2019-06-20 | COMP | 2020-12-28 | COMP | 2021-02-02 | COMP | Rule 16 | 274 | 73 | 14 | 2 | 383 | 25 | 767
2799 | 2018-01-17 | 2018-02-01 | 2018-06-11 | 2018-06-11 | COMP | 2020-06-12 | COMP | 2020-08-25 | COMP | 2020-11-05 | COMP | 2020-12-22 | COMP | Rule 16 | 12 | 91 | 505 | 53 | 52 | 31 | 739
2994 | 2018-01-17 | 2018-02-26 | 2018-08-08 | 2018-08-08 | COMP | 2018-08-24 | COMP | 2020-06-29 | COMP | 2020-06-03 | COMP | 2020-08-12 | COMP | Rule 15/16 | 28 | 116 | 13 | 463 | 0 | 33 | 649
3068 | 2018-01-17 | 2018-03-05 | 2018-08-16 | 2018-08-16 | COMP | 2018-03-05 | NOTN | 2018-08-16 | COMP | 2020-02-03 | COMP | 2020-06-12 | COMP | Other | 33 | 117 |  | 1 | 366 | 93 | 606
3222 | 2018-01-17 | 2018-03-22 | 2018-05-11 | 2018-05-11 | COMP | 2019-12-12 | COMP | 2023-02-25 | REQD | 2019-12-09 | COMP | 2019-12-11 | COMP | Rule 16 | 46 | 37 | 399 |  |  |  | 479
3302 | 2018-01-17 | 2018-04-04 | 2018-10-18 | 2018-10-18 | COMP | 2018-10-18 | NOTN | 2018-12-13 | COMP | 2018-12-04 | COMP | 2019-01-07 | COMP | Other | 55 | 139 |  | 38 | 0 | 16 | 245
3582 | 2018-01-17 | 2018-05-19 | 2019-05-24 | 2019-05-24 | COMP | 2019-08-30 | COMP | 2020-05-07 | COMP | 2020-06-10 | COMP | 2020-07-10 | COMP | Rule 15/16 | 87 | 255 | 69 | 172 | 24 | 23 | 626
3593 | 2018-01-17 | 2018-05-22 | 2018-10-16 | 2018-10-16 | COMP | 2018-11-13 | COMP | 2018-11-15 | COMP | 2018-11-14 | COMP | 2019-01-11 | COMP | Rule 16 | 89 | 103 | 20 | 3 | 0 | 38 | 249
3603 | 2018-01-17 | 2018-05-23 | 2018-10-25 | 2018-10-25 | COMP | 2019-01-30 | COMP | 2019-02-13 | COMP | 2019-01-28 | COMP | 2019-03-25 | COMP | Rule 15/16 | 90 | 109 | 64 | 11 | 0 | 28 | 298
4569 | 2018-01-17 | 2018-02-01 | 2018-10-26 | 2018-10-26 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-07-21 | INPR | 2019-03-05 | COMP | Rule 16 | 12 | 188 | 51 | 1 |  |  | 284
4609 | 2018-01-17 | 2018-02-13 | 2018-05-01 | 2020-03-02 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-05-04 | COMP | 2020-05-07 | COMP | Rule 16 | 20 | 55 | 12 | 1 | 35 | 4 | 581
4789 | 2018-01-17 | 2018-03-30 | 2018-08-22 | 2018-08-22 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2019-03-28 | COMP | 2019-04-19 | COMP | Rule 16 | 52 | 102 | 61 | 1 | 89 | 17 | 317
4790 | 2018-01-17 | 2018-03-30 | 2018-10-08 | 2018-10-08 | COMP | 2018-12-31 | COMP | 2019-03-20 | COMP | 2019-02-22 | COMP | 2019-05-13 | COMP | Rule 16 | 52 | 134 | 57 | 55 | 0 | 39 | 333
4840 | 2018-01-17 | 2018-04-04 | 2019-01-23 | 2020-08-25 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-06-22 | COMP | 2021-07-24 | COMP | Rule 16 | 55 | 202 | 25 | 1 | 183 | 23 | 886
4947 | 2018-01-17 | 2018-04-13 | 2018-05-18 | 2018-05-18 | COMP | 2018-06-13 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-03-11 | COMP | Rule 16 | 62 | 26 | 18 | 165 | 1 | 21 | 288
5257 | 2018-01-17 | 2018-05-14 | 2018-08-13 | 2018-08-13 | COMP | 2018-10-25 | COMP | 2018-11-20 | COMP | 2018-11-14 | COMP | 2019-02-27 | COMP | Rule 15/16 | 83 | 64 | 53 | 18 | 0 | 66 | 280
8653 | 2018-01-17 | 2018-12-13 | 2019-02-20 | 2019-02-20 | COMP | 2019-03-07 | COMP | 2019-04-17 | COMP | 2019-03-19 | COMP | 2019-06-18 | COMP | Rule 15/16 | 230 | 46 | 12 | 30 | 0 | 44 | 358
9690 | 2018-01-17 | 2019-02-11 | 2019-05-20 | 2019-08-09 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2019-11-13 | COMP | Rule 16 | 269 | 70 | 34 | 1 | 1 | 34 | 461
12581 | 2018-01-17 | 2019-06-13 | 2019-09-11 | 2019-11-26 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2023-11-12 | INPR | 2020-01-07 | COMP | Rule 16 | 355 | 63 | 25 | 1 |  |  | 496
13182 | 2018-01-17 | 2019-07-16 | 2019-08-20 | 2019-08-20 | COMP | 2019-10-02 | COMP | 2019-11-21 | COMP | 2020-01-08 | COMP | 2020-03-12 | COMP | Rule 15/16 | 377 | 26 | 31 | 36 | 31 | 45 | 541
13193 | 2018-01-17 | 2019-07-15 | 2019-09-18 | 2019-09-18 | COMP | 2019-09-26 | COMP | 2019-10-08 | COMP | 2019-11-18 | COMP | 2019-12-19 | COMP | Rule 16 | 376 | 47 | 7 | 9 | 29 | 22 | 485
17730 | 2018-01-17 | 2020-02-25 | 2020-03-18 | 2020-03-18 | COMP | 2020-03-19 | COMP | 2020-03-20 | COMP | 2020-06-02 | COMP | 2020-06-06 | COMP | Rule 16 | 529 | 17 | 2 | 2 | 52 | 4 | 601
3028 | 2018-01-18 | 2018-02-28 | 2018-07-25 | 2018-05-08 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-06-27 | COMP | Rule 16 | 29 | 104 | 237 | 1 | 1 | 51 | 364
3139 | 2018-01-18 | 2018-03-13 | 2018-08-23 | 2018-08-23 | COMP | 2018-03-13 | NOTN | 2018-11-27 | COMP | 2018-12-03 | COMP | 2019-03-11 | COMP | Rule 16 | 38 | 116 |  | 65 | 5 | 67 | 287
3273 | 2018-01-18 | 2018-03-29 | 2018-05-07 | 2018-05-07 | COMP | 2020-07-07 | COMP | 2020-07-08 | COMP | 2020-10-15 | COMP | 2020-11-30 | COMP | Rule 16 | 50 | 28 | 546 | 2 | 71 | 30 | 722
3341 | 2018-01-18 | 2018-04-10 | 2018-08-20 | 2018-08-20 | COMP | 2018-10-01 | COMP | 2019-07-03 | COMP | 2020-09-26 | INPR | 2019-08-21 | COMP | Rule 16 | 58 | 93 | 30 | 190 |  |  | 402
3706 | 2018-01-18 | 2018-06-14 | 2018-08-23 | 2019-02-13 | COMP | 2019-05-14 | COMP | 2019-06-10 | COMP | 2019-04-25 | COMP | 2019-06-28 | COMP | Rule 15/16 | 104 | 50 | 64 | 19 | 0 | 15 | 365
4585 | 2018-01-18 | 2018-02-09 | 2018-03-22 | 2018-04-02 | COMP | 2018-07-16 | COMP | 2019-01-22 | COMP | 2019-01-28 | COMP | 2019-03-26 | COMP | Rule 16 | 17 | 29 | 74 | 130 | 5 | 41 | 298
4614 | 2018-01-18 | 2018-02-14 | 2018-05-07 | 2019-06-06 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2019-12-17 | COMP | 2020-01-24 | COMP | Rule 16 | 20 | 58 | 102 | 1 | 33 | 26 | 507
4722 | 2018-01-18 | 2018-03-23 | 2018-08-07 | 2018-08-07 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2020-01-13 | COMP | 2020-01-14 | COMP | Rule 16 | 46 | 96 | 39 | 1 | 321 | 2 | 500
4740 | 2018-01-18 | 2018-03-24 | 2018-06-30 | 2018-06-30 | COMP | 2018-07-13 | COMP | 2018-07-13 | COMP | 2018-07-17 | COMP | 2019-01-08 | COMP | Rule 16 | 46 | 69 | 9 | 1 | 3 | 120 | 245
5461 | 2018-01-18 | 2018-06-01 | 2018-09-15 | 2018-09-15 | COMP | 2018-09-27 | COMP | 2018-12-03 | COMP | 2020-02-25 | COMP | 2020-07-06 | COMP | Rule 16 | 95 | 74 | 9 | 45 | 308 | 94 | 621
5770 | 2018-01-18 | 2018-07-02 | 2018-11-01 | 2018-11-01 | COMP | 2019-03-12 | NOTN | 2019-03-12 | COMP | 2019-04-03 | COMP | 2019-04-22 | COMP | Other | 116 | 87 |  | 87 | 17 | 14 | 317
5874 | 2018-01-18 | 2018-07-10 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-25 | COMP | 2019-04-09 | COMP | 2019-04-18 | COMP | 2019-05-15 | COMP | Rule 16 | 121 | 138 | 40 | 12 | 8 | 20 | 334
5941 | 2018-01-18 | 2018-07-12 | 2018-12-18 | 2018-12-18 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-04-18 | COMP | 2019-08-13 | COMP | Rule 15/16 | 123 | 110 | 42 | 1 | 43 | 82 | 396
7175 | 2018-01-18 | 2018-10-01 | 2018-12-07 | 2018-12-07 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-03-05 | COMP | 2019-04-24 | COMP | Rule 16 | 179 | 47 | 58 | 1 | 2 | 37 | 319
7765 | 2018-01-18 | 2018-10-30 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-02-05 | COMP | 2019-03-16 | COMP | Rule 15/16 | 200 | 9 | 18 | 1 | 39 | 28 | 291
9119 | 2018-01-18 | 2019-01-18 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-21 | COMP | 2019-09-19 | COMP | 2019-09-06 | COMP | 2019-10-03 | COMP | Rule 16 | 253 | 55 | 32 | 85 | 0 | 11 | 432
9750 | 2018-01-18 | 2019-02-13 | 2019-05-28 | 2019-05-28 | COMP | 2019-09-05 | COMP | 2020-03-09 | COMP | 2023-11-11 | INPR | 2020-05-12 | COMP | Rule 16 | 270 | 73 | 71 | 126 |  |  | 583
12066 | 2018-01-18 | 2019-05-22 | 2019-10-19 | 2019-10-19 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-07-21 | COMP | 2020-10-05 | COMP | Rule 15/16 | 339 | 105 | 47 | 1 | 143 | 54 | 685
22166 | 2018-01-18 | 2020-09-12 | 2020-12-15 | 2020-12-15 | COMP | 2022-01-31 | COMP | 2022-01-31 | COMP | 2022-06-08 | COMP | 2022-10-03 | COMP | Rule 16 | 669 | 64 | 284 | 1 | 91 | 81 | 1186
2726 | 2018-01-19 | 2018-01-24 | 2018-09-26 | 2018-09-26 | COMP | 2018-12-12 | COMP | 2018-12-20 | COMP | 2019-05-29 | COMP | 2019-06-07 | COMP | Rule 16 | 4 | 172 | 53 | 7 | 110 | 8 | 349
2802 | 2018-01-19 | 2018-02-01 | 2018-04-07 | 2018-04-07 | COMP | 2019-04-24 | COMP | 2018-07-25 | COMP | 2019-01-30 | COMP | 2019-06-05 | COMP | Rule 15/16 | 10 | 46 | 263 |  | 129 | 89 | 347
3166 | 2018-01-19 | 2018-03-16 | 2018-04-18 | 2018-04-18 | COMP | 2018-10-12 | COMP | 2018-10-31 | COMP | 2019-11-18 | COMP | 2020-01-29 | COMP | Rule 15/16 | 40 | 24 | 125 | 14 | 263 | 48 | 509
3256 | 2018-01-19 | 2018-03-28 | 2018-05-28 | 2018-05-28 | COMP | 2018-05-31 | COMP | 2018-07-23 | COMP | 2018-11-14 | COMP | 2019-01-25 | COMP | Rule 16 | 48 | 43 | 3 | 37 | 81 | 48 | 256
4650 | 2018-01-19 | 2018-02-26 | 2018-04-20 | 2018-04-20 | COMP | 2018-05-10 | COMP | 2018-05-10 | COMP | 2020-04-26 | INPR | 2020-01-16 | COMP | Rule 16 | 26 | 40 | 15 | 1 |  |  | 501
4653 | 2018-01-19 | 2018-02-26 | 2018-08-06 | 2018-08-06 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2018-10-04 | COMP | 2019-01-31 | COMP | Rule 16 | 26 | 114 | 57 | 1 | 0 | 66 | 260
4737 | 2018-01-19 | 2018-03-23 | 2018-06-05 | 2018-06-05 | COMP | 2018-08-15 | COMP | 2018-09-06 | COMP | 2018-12-27 | COMP | 2019-03-12 | COMP | Rule 16 | 45 | 52 | 51 | 16 | 77 | 51 | 287
4770 | 2018-01-19 | 2018-03-28 | 2018-10-01 | 2018-10-01 | COMP | 2018-12-27 | COMP | 2019-01-03 | COMP | 2019-02-06 | COMP | 2019-04-03 | COMP | Rule 15/16 | 48 | 131 | 60 | 5 | 24 | 40 | 303
4876 | 2018-01-19 | 2018-04-06 | 2018-09-22 | 2018-10-29 | COMP | 2018-11-13 | COMP | 2019-02-07 | COMP | 2019-02-19 | NOTN | 2019-03-11 | COMP | Rule 16 | 55 | 118 | 11 | 58 |  |  | 286
4952 | 2018-01-19 | 2018-04-13 | 2019-05-06 | 2019-07-29 | COMP | 2019-09-16 | COMP | 2021-05-06 | COMP | 2021-04-26 | COMP | 2021-06-04 | COMP | Rule 16 | 60 | 267 | 35 | 413 | 0 | 21 | 850
5266 | 2018-01-19 | 2018-05-15 | 2018-07-02 | 2019-01-30 | COMP | 2019-05-20 | COMP | 2021-04-02 | COMP | 2021-04-27 | COMP | 2021-06-16 | COMP | Rule 16 | 82 | 34 | 78 | 471 | 18 | 36 | 858
7648 | 2018-01-19 | 2018-10-24 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-07-21 | INPR | 2019-04-16 | COMP | Rule 16 | 195 | 40 | 33 | 1 |  |  | 312
8778 | 2018-01-19 | 2018-12-26 | 2019-07-09 | 2019-07-09 | COMP | 2020-02-03 | COMP | 2020-03-16 | COMP | 2020-07-01 | COMP | 2020-08-11 | COMP | Rule 16 | 236 | 135 | 143 | 30 | 77 | 30 | 646
12235 | 2018-01-19 | 2019-05-28 | 2019-09-09 | 2019-09-09 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2020-11-16 | COMP | 2021-01-15 | COMP | Rule 16 | 341 | 73 | 262 | 1 | 40 | 41 | 753
14498 | 2018-01-19 | 2019-09-13 | 2020-05-12 | 2020-05-12 | COMP | 2020-07-16 | COMP | 2020-11-18 | COMP | 2023-12-30 | INPR | 2021-03-08 | COMP | Rule 15/16 | 417 | 166 | 47 | 88 |  |  | 787
4844 | 2018-01-20 | 2018-04-04 | 2018-09-06 | 2018-09-06 | COMP | 2018-10-24 | COMP | 2019-01-07 | COMP | 2019-01-23 | COMP | 2019-07-11 | COMP | Rule 16 | 52 | 109 | 35 | 49 | 12 | 119 | 371
3278 | 2018-01-21 | 2018-03-31 | 2018-09-23 | 2019-06-03 | COMP | 2019-06-13 | COMP | 2019-07-12 | COMP | 2019-12-13 | COMP | 2020-03-11 | COMP | Rule 16 | 49 | 122 | 9 | 21 | 107 | 60 | 537
3279 | 2018-01-21 | 2018-03-31 | 2019-05-28 | 2019-10-08 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-04-13 | COMP | 2020-06-26 | COMP | Rule 16 | 49 | 291 | 48 | 1 | 81 | 54 | 613
2893 | 2018-01-22 | 2018-02-12 | 2018-07-13 | 2018-07-13 | COMP | 2018-12-12 | COMP | 2019-01-14 | COMP |  | INPR | 2019-02-12 | COMP | Rule 15/16 | 16 | 107 | 105 | 22 |  |  | 267
2920 | 2018-01-22 | 2018-02-16 | 2018-03-29 | 2018-03-29 | COMP | 2018-07-31 | COMP | 2018-07-31 | COMP | 2019-08-07 | COMP | 2019-10-22 | COMP | Other | 20 | 29 | 87 | 1 | 257 | 54 | 443
2921 | 2018-01-22 | 2018-02-16 | 2018-04-15 | 2018-04-15 | COMP | 2018-07-31 | COMP | 2023-02-24 | COMP | 2023-02-24 | COMP | 2023-05-12 | COMP | Other | 20 | 40 | 75 | 1148 | 1 | 56 | 1336
2922 | 2018-01-22 | 2018-02-16 | 2018-04-15 | 2018-04-15 | COMP | 2018-07-31 | COMP | 2018-07-31 | COMP | 2019-08-08 | COMP | 2019-09-10 | COMP | Other | 20 | 40 | 75 | 1 | 258 | 23 | 413
2923 | 2018-01-22 | 2018-02-16 | 2018-04-15 | 2018-04-15 | COMP | 2018-07-31 | COMP | 2018-07-31 | COMP | 2019-08-07 | COMP | 2019-08-28 | COMP | Other | 20 | 40 | 75 | 1 | 257 | 16 | 405
2924 | 2018-01-22 | 2018-02-16 | 2018-04-25 | 2018-04-13 | COMP | 2018-07-31 | COMP | 2018-07-31 | COMP | 2019-08-07 | COMP | 2019-08-28 | COMP | Other | 20 | 48 | 76 | 1 | 257 | 16 | 405
2925 | 2018-01-22 | 2018-02-16 | 2018-04-15 | 2018-04-15 | COMP | 2018-07-31 | COMP | 2018-07-31 | INPR | 2019-08-07 | COMP | 2022-03-26 | COMP | Other | 20 | 40 | 75 |  |  |  | 1052
3031 | 2018-01-22 | 2018-02-28 | 2019-01-04 | 2019-01-04 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | 2019-06-18 | COMP | 2019-07-29 | COMP | Rule 15/16 | 27 | 215 | 106 | 6 | 5 | 29 | 383
3054 | 2018-01-22 | 2018-03-03 | 2018-08-14 | 2018-08-14 | COMP | 2018-10-02 | COMP | 2018-10-03 | COMP | 2020-01-18 | INPR | 2019-01-28 | COMP | Rule 16 | 29 | 115 | 35 | 2 |  |  | 256
3110 | 2018-01-22 | 2018-03-09 | 2018-05-22 | 2018-05-22 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-02-19 | COMP | 2019-02-15 | COMP | Rule 16 | 34 | 53 | 59 | 1 | 128 |  | 270
3610 | 2018-01-22 | 2018-05-24 | 2018-10-26 | 2018-10-26 | COMP | 2018-12-07 | COMP | 2019-03-26 | COMP | 2019-04-06 | COMP | 2019-04-03 | COMP | Rule 16 | 88 | 109 | 28 | 74 | 9 |  | 302
3611 | 2018-01-22 | 2018-05-24 | 2018-10-25 | 2018-10-25 | COMP | 2019-01-24 | COMP | 2019-05-25 | COMP | 2019-05-28 | COMP | 2019-06-06 | COMP | Rule 16 | 88 | 108 | 60 | 86 | 1 | 8 | 347
3612 | 2018-01-22 | 2018-05-24 | 2018-10-24 | 2018-10-24 | COMP | 2018-12-07 | COMP | 2019-06-10 | COMP | 2019-06-11 | COMP | 2019-07-03 | COMP | Rule 16 | 88 | 107 | 30 | 127 | 2 | 17 | 366
3613 | 2018-01-22 | 2018-05-24 | 2018-10-26 | 2018-10-26 | COMP | 2018-12-07 | COMP | 2019-06-10 | COMP | 2019-06-11 | COMP | 2019-07-03 | COMP | Rule 16 | 88 | 109 | 28 | 127 | 2 | 17 | 366
3671 | 2018-01-22 | 2018-06-05 | 2018-11-24 | 2018-11-16 | COMP | 2018-12-06 | COMP | 2019-07-08 | COMP |  |  | 2019-08-01 | COMP | Rule 16 | 95 | 119 | 13 | 147 |  |  | 386
3672 | 2018-01-22 | 2018-06-05 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-06 | COMP | 2019-05-28 | COMP |  |  | 2020-03-14 | COMP | Rule 16 | 95 | 115 | 14 | 119 |  |  | 539
3673 | 2018-01-22 | 2018-06-05 | 2018-11-24 | 2018-11-16 | COMP | 2018-12-06 | COMP | 2019-05-28 | COMP |  |  | 2019-07-25 | COMP | Rule 16 | 95 | 119 | 13 | 119 |  |  | 381
3674 | 2018-01-22 | 2018-06-05 | 2018-11-28 | 2018-10-31 | COMP | 2018-12-06 | COMP | 2019-05-28 | COMP |  |  | 2019-08-09 | COMP | Rule 15/16 | 95 | 122 | 24 | 119 |  |  | 392
3675 | 2018-01-22 | 2018-06-05 | 2018-11-24 | 2018-11-02 | COMP | 2018-12-06 | COMP | 2019-05-28 | COMP |  |  | 2019-07-24 | COMP | Rule 16 | 95 | 119 | 22 | 119 |  |  | 380
3676 | 2018-01-22 | 2018-06-05 | 2018-11-09 | 2018-11-07 | COMP | 2018-12-06 | COMP | 2019-07-08 | COMP |  |  | 2019-08-02 | COMP | Rule 16 | 95 | 112 | 19 | 147 |  |  | 387
3677 | 2018-01-22 | 2018-06-05 | 2018-12-12 | 2018-12-12 | COMP | 2019-02-25 | COMP | 2019-05-28 | COMP |  |  | 2019-07-24 | COMP | Rule 16 | 95 | 132 | 50 | 66 |  |  | 380
3684 | 2018-01-22 | 2018-06-07 | 2018-09-26 | 2018-09-26 | COMP | 2019-06-14 | COMP | 2019-06-19 | COMP | 2019-11-24 | INPR | 2019-08-16 | COMP | Rule 16 | 97 | 78 | 180 | 4 |  |  | 397
3685 | 2018-01-22 | 2018-06-07 | 2018-09-24 | 2018-09-24 | COMP | 2019-02-26 | COMP | 2019-04-04 | COMP | 2019-11-24 | INPR | 2019-08-14 | COMP | Rule 15/16 | 97 | 76 | 105 | 28 |  |  | 395
3686 | 2018-01-22 | 2018-06-07 | 2018-11-01 | 2018-11-01 | COMP | 2019-06-14 | COMP | 2019-06-19 | COMP | 2019-11-24 | INPR | 2019-08-14 | COMP | Rule 16 | 97 | 104 | 154 | 4 |  |  | 395
4563 | 2018-01-22 | 2018-01-31 | 2018-04-13 | 2018-04-13 | COMP | 2018-07-12 | COMP | 2018-07-12 | COMP | 2019-05-29 | COMP | 2019-06-04 | COMP | Rule 16 | 8 | 52 | 63 | 1 | 221 | 5 | 345
4601 | 2018-01-22 | 2018-02-13 | 2018-06-14 | 2018-06-14 | COMP | 2018-09-25 | COMP | 2018-09-25 | COMP | 2019-07-02 | COMP | 2019-07-30 | COMP | Rule 16 | 17 | 86 | 72 | 1 | 193 | 20 | 384
4891 | 2018-01-22 | 2018-04-10 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-05 | NOTN | 2019-05-15 | COMP | 2019-05-15 | COMP | 2019-07-17 | COMP | Other | 56 | 248 |  | 30 | 1 | 44 | 375
4908 | 2018-01-22 | 2018-04-11 | 2019-02-05 | 2019-02-05 | COMP | 2019-02-28 | COMP | 2019-02-28 | COMP | 2019-10-21 | INPR | 2019-04-25 | COMP | Rule 16 | 57 | 206 | 17 | 1 |  |  | 318
4920 | 2018-01-22 | 2018-04-12 | 2018-09-19 | 2018-09-19 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-08-13 | COMP | 2019-09-13 | COMP | Rule 16 | 58 | 112 | 208 | 1 | 19 | 23 | 416
5065 | 2018-01-22 | 2018-04-27 | 2018-05-09 | 2018-05-09 | COMP | 2018-06-06 | COMP | 2018-06-06 | COMP | 2019-07-21 | INPR | 2019-03-21 | COMP | Rule 16 | 69 | 9 | 20 | 1 |  |  | 293
5181 | 2018-01-22 | 2018-05-08 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-21 | COMP | 2018-08-21 | COMP | 2018-10-02 | COMP | 2019-01-10 | COMP | Rule 16 | 76 | 49 | 26 | 1 | 30 | 68 | 245
5234 | 2018-01-22 | 2018-05-14 | 2018-07-02 | 2018-07-02 | COMP | 2018-08-07 | COMP | 2018-11-08 | COMP | 2023-11-11 | INPR | 2019-05-10 | COMP | Rule 16 | 80 | 35 | 26 | 67 |  |  | 329
5362 | 2018-01-22 | 2018-05-24 | 2019-01-30 | 2020-02-12 | COMP | 2020-06-08 | COMP | 2019-12-06 | COMP | 2020-07-29 | COMP | 2020-10-08 | COMP | Rule 15/16 | 88 | 171 | 82 |  | 164 | 51 | 686
5363 | 2018-01-22 | 2018-05-24 | 2018-09-25 | 2018-09-25 | COMP | 2018-11-01 | COMP | 2019-02-28 | COMP | 2020-02-04 | COMP | 2020-07-01 | COMP | Rule 15/16 | 88 | 86 | 28 | 79 | 235 | 105 | 616
5364 | 2018-01-22 | 2018-05-24 | 2018-11-30 | 2018-11-30 | COMP | 2018-12-19 | COMP | 2018-12-21 | COMP | 2020-04-29 | COMP | 2020-06-05 | COMP | Rule 16 | 88 | 131 | 14 | 3 | 340 | 27 | 598
5365 | 2018-01-22 | 2018-05-24 | 2018-08-28 | 2018-08-28 | COMP | 2018-10-25 | COMP | 2020-04-15 | COMP | 2020-06-03 | COMP | 2020-07-14 | COMP | Rule 15/16 | 88 | 67 | 42 | 368 | 35 | 30 | 625
5370 | 2018-01-22 | 2018-05-24 | 2018-10-18 | 2018-10-18 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-06-03 | COMP | 2019-08-06 | COMP | Rule 15/16 | 88 | 103 | 93 | 1 | 63 | 46 | 389
5371 | 2018-01-22 | 2018-05-24 | 2018-07-12 | 2018-07-12 | COMP | 2018-10-18 | COMP | 2019-07-10 | COMP | 2020-06-08 | COMP | 2020-08-03 | COMP | Rule 15/16 | 88 | 34 | 70 | 181 | 230 | 41 | 639
5372 | 2018-01-22 | 2018-05-24 | 2018-07-12 | 2018-07-12 | COMP | 2018-08-02 | COMP | 2018-10-02 | COMP | 2020-06-22 | COMP | 2020-08-14 | COMP | Rule 16 | 88 | 34 | 16 | 43 | 432 | 40 | 648
5373 | 2018-01-22 | 2018-05-24 | 2018-10-25 | 2018-10-25 | COMP | 2018-11-13 | COMP | 2019-01-03 | COMP | 2019-03-29 | COMP | 2019-06-14 | COMP | Rule 15/16 | 88 | 108 | 13 | 34 | 60 | 55 | 353
5374 | 2018-01-22 | 2018-05-24 | 2018-10-04 | 2018-10-04 | COMP | 2018-10-30 | COMP | 2018-11-07 | COMP | 2019-10-21 | INPR | 2019-06-14 | COMP | Rule 15/16 | 88 | 93 | 19 | 7 |  |  | 353
5375 | 2018-01-22 | 2018-05-24 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-10 | COMP | 2019-02-12 | COMP | 2019-03-06 | COMP | 2019-04-18 | COMP | Rule 15/16 | 88 | 82 | 16 | 84 | 16 | 32 | 313
5376 | 2018-01-22 | 2018-05-24 | 2018-07-13 | 2018-07-13 | COMP | 2018-08-22 | COMP | 2018-11-14 | COMP | 2018-11-09 | COMP | 2020-08-11 | COMP | Rule 16 | 88 | 35 | 29 | 59 | 0 | 438 | 645
5377 | 2018-01-22 | 2018-05-24 | 2018-08-06 | 2018-08-06 | COMP | 2018-08-30 | COMP | 2019-06-28 | COMP | 2020-11-17 | COMP | 2021-02-18 | COMP | Rule 16 | 88 | 51 | 19 | 208 | 351 | 62 | 774
5378 | 2018-01-22 | 2018-05-24 | 2018-09-11 | 2018-09-11 | COMP | 2018-10-03 | COMP | 2018-11-14 | COMP | 2018-11-15 | COMP | 2019-01-19 | COMP | Rule 16 | 88 | 76 | 17 | 30 | 2 | 43 | 251
5379 | 2018-01-22 | 2018-05-24 | 2018-09-27 | 2018-09-27 | COMP | 2018-11-01 | COMP | 2019-01-10 | COMP | 2021-01-11 | COMP | 2021-01-22 | COMP | Rule 15/16 | 88 | 88 | 26 | 46 | 504 | 9 | 756
5380 | 2018-01-22 | 2018-05-24 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-27 | COMP | 2019-02-06 | COMP | 2019-04-15 | COMP | 2019-05-17 | COMP | Rule 15/16 | 88 | 139 | 11 | 28 | 48 | 25 | 334
5455 | 2018-01-22 | 2018-06-01 | 2018-10-10 | 2018-11-28 | COMP | 2018-12-31 | COMP | 2020-01-02 | COMP | 2019-12-04 | COMP | 2020-01-29 | COMP | Rule 16 | 93 | 92 | 23 | 253 | 0 | 19 | 508
5850 | 2018-01-22 | 2018-07-07 | 2018-11-13 | 2018-11-13 | COMP | 2019-01-03 | COMP | 2019-02-12 | COMP | 2019-01-08 | COMP | 2019-04-12 | COMP | Rule 16 | 117 | 90 | 34 | 28 | 0 | 43 | 309
6315 | 2018-01-22 | 2018-08-09 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-09 | NOTN | 2019-04-09 | COMP | 2019-05-08 | COMP | 2019-05-30 | COMP | Other | 141 | 166 |  | 1 | 22 | 16 | 342
6668 | 2018-01-22 | 2018-09-05 | 2018-11-14 | 2018-12-07 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-01-18 | COMP | 2021-03-08 | COMP | Rule 16 | 159 | 50 | 23 | 1 | 7 | 536 | 786
6761 | 2018-01-22 | 2018-09-11 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-04-15 | COMP | 2019-05-10 | COMP | Rule 16 | 163 | 83 | 9 | 1 | 58 | 20 | 329
8400 | 2018-01-22 | 2018-11-29 | 2018-12-17 | 2018-12-17 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-09-02 | INPR | 2019-05-06 | COMP | Rule 15/16 | 217 | 13 | 13 | 1 |  |  | 325
8559 | 2018-01-22 | 2018-12-10 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-10 | COMP | 2020-02-05 | COMP | 2020-03-16 | COMP | 2020-06-19 | COMP | Rule 15/16 | 224 | 108 | 19 | 165 | 28 | 69 | 608
9462 | 2018-01-22 | 2019-02-05 | 2019-10-10 | 2019-10-10 | COMP | 2020-06-10 | COMP | 2020-12-14 | COMP | 2020-06-17 | COMP | 2021-02-25 | COMP | Rule 16 | 262 | 174 | 167 | 130 | 0 | 50 | 779
24864 | 2018-01-22 | 2021-01-15 | 2022-09-14 | 2022-09-14 | COMP | 2022-09-27 | COMP | 2022-11-03 | COMP | 2022-11-15 | COMP | 2022-12-20 | COMP | Rule 15/16 | 752 | 420 | 10 | 28 | 8 | 24 | 1237
2813 | 2018-01-23 | 2018-02-05 | 2018-05-21 | 2018-05-21 | COMP | 2018-05-25 | COMP | 2018-09-07 | COMP | 2018-09-05 | COMP | 2019-02-01 | COMP | Rule 16 | 10 | 75 | 5 | 73 | 0 | 100 | 259
2977 | 2018-01-23 | 2018-02-23 | 2018-10-31 | 2018-10-31 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-12-19 | COMP | 2020-01-09 | COMP | Rule 15/16 | 23 | 176 | 245 | 1 | 40 | 14 | 494
3096 | 2018-01-23 | 2018-03-07 | 2020-03-27 | 2020-03-27 | COMP | 2022-10-31 | COMP | 2023-10-09 | COMP |  | INPR | 2023-10-03 | COMP | Rule 15/16 | 31 | 518 | 656 | 235 |  |  | 1433
3215 | 2018-01-23 | 2018-03-22 | 2018-09-21 | 2018-09-21 | COMP | 2018-11-28 | COMP | 2019-01-16 | COMP | 2019-07-21 | INPR | 2019-03-16 | COMP | Rule 15/16 | 42 | 129 | 46 | 34 |  |  | 288
3216 | 2018-01-23 | 2018-03-22 | 2018-09-27 | 2018-09-27 | COMP | 2019-04-10 | COMP | 2019-09-11 | COMP | 2019-09-10 | COMP | 2019-10-03 | COMP | Rule 15/16 | 42 | 133 | 133 | 108 | 0 | 17 | 429
3246 | 2018-01-23 | 2018-03-27 | 2018-04-09 | 2018-04-09 | COMP | 2019-06-27 | COMP | 2019-07-03 | COMP | 2019-06-28 | COMP | 2019-07-19 | COMP | Rule 16 | 45 | 10 | 308 | 5 | 0 | 12 | 376
3360 | 2018-01-23 | 2018-04-13 | 2018-05-20 | 2018-05-20 | COMP | 2018-07-16 | COMP | 2020-01-27 | COMP | 2021-03-27 | INPR | 2020-03-04 | COMP | Rule 16 | 58 | 26 | 39 | 384 |  |  | 531
3369 | 2018-01-23 | 2018-04-13 | 2018-11-19 | 2020-10-26 | COMP | 2020-04-24 | COMP | 2021-01-22 | COMP | 2021-01-12 | COMP | 2021-03-09 | COMP | Rule 15/16 | 58 | 153 |  | 188 | 0 | 32 | 786
3442 | 2018-01-23 | 2018-04-26 | 2018-08-15 | 2018-08-15 | COMP | 2018-12-03 | COMP | 2018-12-08 | COMP | 2019-08-31 | INPR | 2019-05-02 | COMP | Rule 16 | 67 | 78 | 75 | 5 |  |  | 322
3481 | 2018-01-23 | 2018-05-04 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-15 | COMP | 2018-12-05 | COMP | 2019-08-31 | INPR | 2019-05-10 | COMP | Rule 16 | 73 | 126 | 11 | 13 |  |  | 328
3609 | 2018-01-23 | 2018-05-24 | 2018-10-24 | 2018-10-24 | COMP | 2018-12-07 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-22 | COMP | Rule 16 | 87 | 107 | 30 | 59 | 1 | 14 | 293
3614 | 2018-01-23 | 2018-05-24 | 2018-10-26 | 2018-10-26 | COMP | 2018-12-07 | COMP | 2019-05-15 | COMP | 2019-09-21 | INPR | 2019-05-28 | COMP | Rule 16 | 87 | 109 | 28 | 110 |  |  | 339
3625 | 2018-01-23 | 2018-05-25 | 2018-10-25 | 2018-10-25 | COMP | 2018-12-07 | COMP | 2019-04-27 | COMP | 2019-04-30 | COMP | 2019-05-09 | COMP | Rule 16 | 88 | 107 | 29 | 97 | 2 | 8 | 327
3659 | 2018-01-23 | 2018-06-05 | 2019-01-28 | 2019-01-28 | COMP | 2019-05-08 | COMP | 2019-05-28 | COMP |  |  | 2019-07-23 | COMP | Rule 16 | 94 | 162 | 72 | 14 |  |  | 378
3660 | 2018-01-23 | 2018-06-05 | 2019-03-28 | 2019-03-28 | COMP | 2019-05-08 | COMP | 2019-05-28 | COMP |  |  | 2019-07-23 | COMP | Rule 16 | 94 | 204 | 30 | 14 |  |  | 378
3716 | 2018-01-23 | 2018-06-15 | 2019-03-27 | 2019-03-27 | COMP | 2019-04-11 | COMP | 2019-07-31 | COMP | 2019-10-15 | COMP | 2019-10-23 | COMP | Rule 16 | 102 | 195 | 12 | 78 | 54 | 7 | 443
4554 | 2018-01-23 | 2018-02-02 | 2018-04-20 | 2018-04-20 | COMP | 2018-05-16 | COMP | 2018-05-17 | COMP | 2018-07-03 | COMP | 2021-12-10 | COMP | Rule 16 | 9 | 55 | 19 | 2 | 33 | 865 | 978
4590 | 2018-01-23 | 2018-02-09 | 2018-03-23 | 2019-06-14 | COMP | 2019-06-25 | COMP | 2018-04-18 | COMP | 2019-11-19 | COMP | 2019-11-26 | COMP | Rule 16 | 14 | 30 | 8 |  | 401 | 6 | 466
4639 | 2018-01-23 | 2018-02-23 | 2018-04-30 | 2018-04-30 | COMP | 2018-07-24 | COMP | 2018-10-01 | COMP | 2019-02-19 | COMP | 2019-03-08 | COMP | Rule 16 | 23 | 47 | 60 | 49 | 95 | 14 | 283
5055 | 2018-01-23 | 2018-04-26 | 2018-10-10 | 2018-10-30 | COMP | 2018-12-17 | COMP | 2019-02-15 | COMP | 2019-01-23 | COMP | 2019-03-13 | COMP | Rule 15/16 | 67 | 117 | 32 | 42 | 0 | 18 | 286
5303 | 2018-01-23 | 2018-05-21 | 2018-11-07 | 2018-11-07 | COMP | 2018-12-04 | COMP | 2019-03-06 | COMP | 2019-02-22 | COMP | 2019-03-29 | COMP | Rule 16 | 84 | 120 | 17 | 63 | 0 | 18 | 298
5305 | 2018-01-23 | 2018-05-21 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-13 | COMP | 2019-11-14 | COMP | 2021-02-27 | INPR | 2019-11-19 | COMP | Rule 15/16 | 84 | 113 | 11 | 253 |  |  | 461
5306 | 2018-01-23 | 2018-05-21 | 2019-03-19 | 2019-03-19 | COMP | 2019-07-25 | COMP | 2020-02-24 | COMP | 2020-09-04 | COMP | 2020-11-04 | COMP | Rule 15/16 | 84 | 207 | 91 | 145 | 139 | 43 | 704
5888 | 2018-01-23 | 2018-07-09 | 2018-10-30 | 2018-10-30 | COMP | 2019-08-07 | COMP | 2019-11-04 | COMP | 2023-11-11 | INPR | 2021-03-17 | COMP | Rule 15/16 | 117 | 81 | 193 | 63 |  |  | 792
7543 | 2018-01-23 | 2018-10-19 | 2018-10-30 | 2018-10-30 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2020-03-24 | COMP | 2020-04-22 | COMP | Rule 16 | 190 | 8 | 237 | 1 | 113 | 22 | 566
7599 | 2018-01-23 | 2018-10-22 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-11 | COMP | 2019-09-30 | COMP | 2019-09-11 | COMP | 2019-11-07 | COMP | Rule 16 | 191 | 217 | 7 | 14 | 0 | 29 | 454
9539 | 2018-01-23 | 2019-02-07 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-24 | COMP | 2020-02-26 | COMP | 2023-11-11 | INPR | 2020-10-26 | COMP | Rule 16 | 263 | 80 | 17 | 169 |  |  | 697
2722 | 2018-01-24 | 2018-01-24 | 2018-05-31 | 2018-05-31 | COMP | 2018-08-09 | COMP | 2018-08-14 | COMP | 2019-08-08 | COMP | 2019-08-28 | COMP | Rule 15/16 | 1 | 90 | 50 | 4 | 248 | 15 | 403
2776 | 2018-01-24 | 2018-01-30 | 2018-03-13 | 2018-03-13 | COMP | 2018-03-28 | COMP | 2018-03-28 | INPR | 2018-04-24 | COMP | 2019-01-11 | COMP | Other | 5 | 30 | 12 |  |  |  | 244
2827 | 2018-01-24 | 2018-02-06 | 2018-04-18 | 2019-07-16 | COMP | 2019-01-03 | COMP | 2019-07-18 | COMP | 2019-02-04 | COMP | 2019-09-06 | COMP | Rule 16 | 10 | 51 |  | 137 | 0 | 36 | 409
2949 | 2018-01-24 | 2018-02-21 | 2018-03-22 | 2018-03-22 | COMP | 2018-04-05 | COMP | 2018-04-13 | COMP | 2018-06-12 | COMP | 2021-04-18 | COMP | Rule 16 | 20 | 22 | 11 | 7 | 42 | 716 | 813
2951 | 2018-01-24 | 2018-02-22 | 2018-09-06 | 2018-09-06 | COMP | 2018-11-02 | COMP | 2019-07-30 | COMP | 2019-07-29 | COMP | 2019-08-21 | COMP | Rule 15/16 | 21 | 138 | 42 | 184 | 0 | 17 | 398
2960 | 2018-01-24 | 2018-02-22 | 2018-04-17 | 2018-04-17 | COMP | 2018-08-29 | COMP | 2019-01-24 | COMP | 2023-02-25 | INPR | 2019-02-07 | COMP | Rule 16 | 21 | 39 | 95 | 100 |  |  | 262
3012 | 2018-01-24 | 2018-02-27 | 2019-02-08 | 2019-02-08 | COMP | 2019-10-17 | COMP | 2019-10-24 | COMP | 2020-03-24 | COMP | 2020-06-15 | COMP | Rule 16 | 24 | 240 | 176 | 6 | 102 | 59 | 602
3013 | 2018-01-24 | 2018-02-27 | 2018-10-01 | 2018-10-01 | COMP | 2018-11-19 | COMP | 2018-11-26 | COMP | 2020-09-23 | NOTN | 2019-02-06 | COMP | Rule 16 | 24 | 152 | 35 | 4 |  |  | 261
3014 | 2018-01-24 | 2018-02-27 | 2018-08-27 | 2018-08-27 | COMP | 2018-09-19 | COMP | 2019-10-31 | COMP | 2020-04-06 | COMP | 2021-07-06 | COMP | Rule 16 | 24 | 128 | 17 | 282 | 106 | 316 | 868
3015 | 2018-01-24 | 2018-02-27 | 2018-10-11 | 2018-09-27 | COMP | 2019-11-13 | COMP | 2019-12-12 | COMP | 2020-06-02 | COMP | 2020-03-13 | COMP | Rule 16 | 24 | 160 | 284 | 20 | 119 |  | 537
3016 | 2018-01-24 | 2018-02-27 | 2019-01-07 | 2019-01-07 | COMP | 2019-02-21 | COMP | 2019-02-26 | COMP | 2020-05-26 | COMP | 2020-01-23 | COMP | Rule 15/16 | 24 | 217 | 32 | 4 | 315 |  | 502
3150 | 2018-01-24 | 2018-03-14 | 2018-06-14 | 2018-06-14 | COMP | 2018-08-02 | NOTN | 2018-08-29 | COMP | 2018-12-31 | COMP | 2019-01-16 | COMP | Other | 35 | 66 |  | 54 | 84 | 12 | 247
3152 | 2018-01-24 | 2018-03-15 | 2018-06-13 | 2018-05-10 | COMP | 2018-07-02 | COMP | 2018-07-02 | COMP | 2019-04-20 | INPR | 2019-01-08 | COMP | Rule 16 | 36 | 64 | 37 | 1 |  |  | 241
3237 | 2018-01-24 | 2018-03-27 | 2018-06-28 | 2018-06-28 | COMP | 2019-04-23 | COMP | 2019-05-03 | COMP | 2019-04-23 | COMP | 2019-06-19 | COMP | Rule 15/16 | 44 | 67 | 205 | 9 | 0 | 33 | 354
3440 | 2018-01-24 | 2018-04-26 | 2018-11-22 | 2018-11-22 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-01-23 | COMP | 2019-04-01 | COMP | Rule 16 | 66 | 146 | 2 | 1 | 39 | 48 | 298
3766 | 2018-01-24 | 2018-07-06 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-28 | COMP | 2019-08-15 | COMP | 2019-12-16 | COMP | 2020-03-11 | COMP | Rule 15/16 | 115 | 161 | 22 | 99 | 84 | 59 | 535
3788 | 2018-01-24 | 2018-07-14 | 2018-10-07 | 2018-10-07 | COMP | 2018-12-18 | COMP | 2019-04-02 | COMP | 2022-12-31 | INPR | 2019-06-27 | COMP | Rule 16 | 120 | 59 | 49 | 72 |  |  | 360
3922 | 2018-01-24 | 2018-10-09 | 2018-11-06 | 2019-01-16 | COMP | 2019-02-07 | COMP | 2019-09-19 | COMP | 2019-09-23 | COMP | 2019-10-14 | COMP | Rule 15/16 | 181 | 21 | 16 | 157 | 3 | 16 | 435
4682 | 2018-01-24 | 2018-03-14 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-12 | COMP | 2018-10-12 | COMP | 2018-11-21 | COMP | 2019-03-08 | COMP | Rule 16 | 35 | 133 | 18 | 1 | 28 | 72 | 282
4689 | 2018-01-24 | 2018-03-15 | 2018-08-07 | 2018-08-07 | COMP | 2018-08-27 | COMP | 2019-01-17 | COMP | 2018-12-20 | COMP | 2019-03-14 | COMP | Rule 16 | 36 | 102 | 15 | 98 | 0 | 39 | 286
4705 | 2018-01-24 | 2018-03-19 | 2018-07-20 | 2018-07-20 | COMP | 2019-05-22 | COMP | 2020-01-07 | COMP | 2020-02-04 | COMP | 2020-02-28 | COMP | Rule 16 | 38 | 88 | 211 | 157 | 20 | 18 | 527
4736 | 2018-01-24 | 2018-03-23 | 2018-06-08 | 2018-06-08 | COMP | 2018-10-31 | COMP | 2018-11-01 | COMP | 2019-02-06 | COMP | 2019-03-09 | COMP | Rule 16 | 42 | 55 | 102 | 2 | 64 | 22 | 282
4762 | 2018-01-24 | 2018-03-29 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-16 | COMP | 2018-11-26 | COMP | 2018-11-15 | COMP | 2019-01-24 | COMP | Rule 16 | 46 | 122 | 42 | 5 | 0 | 41 | 252
5019 | 2018-01-24 | 2018-04-24 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-26 | COMP | 2019-05-01 | COMP | 2019-04-23 | COMP | 2019-06-18 | COMP | Rule 16 | 64 | 182 | 30 | 47 | 0 | 34 | 353
5178 | 2018-01-24 | 2018-05-07 | 2018-08-17 | 2018-08-24 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2018-11-20 | COMP | 2019-01-26 | COMP | Rule 15/16 | 73 | 73 | 13 | 1 | 49 | 44 | 253
5253 | 2018-01-24 | 2018-05-14 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-28 | COMP | 2018-12-28 | COMP | 2018-12-28 | COMP | 2019-02-21 | COMP | Rule 16 | 78 | 110 | 49 | 1 | 1 | 37 | 271
5696 | 2018-01-24 | 2018-06-25 | 2018-11-29 | 2018-11-29 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-05-07 | COMP | 2019-06-10 | COMP | Rule 15/16 | 107 | 109 | 102 | 1 | 9 | 24 | 347
6402 | 2018-01-24 | 2018-08-15 | 2018-10-03 | 2018-10-03 | COMP | 2018-12-06 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-04-12 | COMP | Rule 16 | 143 | 35 | 44 | 60 | 1 | 29 | 307
7663 | 2018-01-24 | 2018-10-24 | 2019-02-11 | 2019-02-11 | COMP | 2019-02-27 | COMP | 2019-03-29 | COMP | 2019-09-02 | INPR | 2019-04-25 | COMP | Rule 16 | 192 | 73 | 12 | 23 |  |  | 316
8403 | 2018-01-24 | 2018-11-29 | 2018-12-13 | 2018-12-13 | COMP | 2019-01-10 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-04-17 | COMP | Rule 16 | 215 | 11 | 19 | 44 | 1 | 25 | 310
8467 | 2018-01-24 | 2018-12-04 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-18 | COMP | 2020-01-27 | COMP | 2019-12-24 | COMP | 2020-02-24 | COMP | Rule 15/16 | 218 | 228 | 35 | 26 | 0 | 20 | 523
2927 | 2018-01-25 | 2018-02-17 | 2018-05-16 | 2018-05-16 | COMP | 2018-06-28 | COMP | 2018-08-04 | COMP | 2018-07-02 | COMP | 2019-01-05 | COMP | Rule 16 | 17 | 62 | 31 | 26 | 0 | 104 | 238
2987 | 2018-01-25 | 2018-02-26 | 2018-06-01 | 2019-02-02 | COMP | 2019-02-27 | COMP | 2019-04-25 | COMP | 2019-06-11 | COMP | 2019-06-12 | COMP | Rule 16 | 22 | 69 | 17 | 42 | 33 | 2 | 348
2997 | 2018-01-25 | 2018-02-26 | 2018-07-26 | 2018-07-26 | COMP | 2018-10-02 | COMP | 2018-10-30 | COMP | 2019-01-30 | COMP | 2019-03-12 | COMP | Rule 16 | 22 | 107 | 48 | 21 | 61 | 29 | 283
3138 | 2018-01-25 | 2018-03-13 | 2018-08-17 | 2018-08-17 | COMP | 2018-08-29 | COMP | 2018-12-12 | COMP | 2018-10-03 | COMP | 2019-03-06 | COMP | Rule 16 | 33 | 112 | 9 | 72 | 0 | 57 | 279
3254 | 2018-01-25 | 2018-03-28 | 2018-04-09 | 2018-04-09 | COMP | 2018-05-02 | COMP | 2018-05-03 | COMP | 2021-02-27 | INPR | 2020-01-28 | COMP | Rule 16 | 44 | 9 | 18 | 2 |  |  | 504
3314 | 2018-01-25 | 2018-04-06 | 2018-05-21 | 2018-05-21 | COMP | 2019-06-10 | COMP | 2019-06-12 | COMP | 2019-07-03 | COMP | 2019-08-19 | COMP | Rule 16 | 51 | 32 | 265 | 3 | 16 | 33 | 395
3411 | 2018-01-25 | 2018-04-20 | 2018-10-09 | 2018-10-09 | COMP | 2018-11-13 | COMP | 2018-12-12 | COMP | 2018-11-21 | COMP | 2019-01-19 | COMP | Rule 16 | 61 | 120 | 25 | 20 | 0 | 26 | 248
3438 | 2018-01-25 | 2018-04-26 | 2018-09-01 | 2018-09-01 | COMP | 2019-06-21 | COMP | 2019-06-22 | COMP | 2019-12-28 | INPR | 2019-08-13 | COMP | Rule 15/16 | 65 | 90 | 201 | 1 |  |  | 391
3439 | 2018-01-25 | 2018-04-26 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-08-31 | INPR | 2019-05-13 | COMP | Rule 16 | 65 | 232 | 9 | 1 |  |  | 327
3581 | 2018-01-25 | 2018-05-18 | 2018-06-11 | 2018-06-01 | COMP | 2018-12-10 | COMP | 2019-04-02 | COMP | 2019-05-09 | COMP | 2019-06-05 | COMP | Rule 15/16 | 81 | 16 | 132 | 78 | 28 | 19 | 343
3661 | 2018-01-25 | 2018-06-05 | 2019-01-23 | 2019-01-23 | COMP | 2019-05-08 | COMP | 2019-05-28 | COMP | 2020-05-30 | INPR | 2019-11-08 | COMP | Rule 16 | 92 | 159 | 75 | 14 |  |  | 453
3780 | 2018-01-25 | 2018-07-11 | 2019-02-20 | 2019-02-20 | COMP | 2019-04-08 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2020-12-22 | COMP | Rule 15/16 | 117 | 153 | 34 | 403 | 1 | 30 | 733
4608 | 2018-01-25 | 2018-02-13 | 2018-07-16 | 2018-07-16 | COMP | 2018-11-19 | COMP | 2019-10-23 | COMP | 2019-10-03 | COMP | 2019-11-08 | COMP | Rule 16 | 14 | 107 | 89 | 234 | 0 | 13 | 453
4656 | 2018-01-25 | 2018-02-27 | 2018-04-23 | 2019-07-01 | COMP | 2019-07-16 | COMP | 2019-05-23 | COMP | 2019-07-08 | COMP | 2019-08-06 | COMP | Rule 16 | 23 | 40 | 11 |  | 31 | 22 | 386
4843 | 2018-01-25 | 2018-04-04 | 2018-10-04 | 2018-10-04 | COMP | 2018-11-09 | COMP | 2019-01-07 | COMP | 2018-11-15 | COMP | 2019-08-27 | COMP | Rule 16 | 49 | 129 | 27 | 37 | 0 | 163 | 401
5911 | 2018-01-25 | 2018-07-10 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-05-21 | COMP | 2019-09-06 | COMP | Rule 16 | 116 | 103 | 11 | 1 | 106 | 76 | 408
9393 | 2018-01-25 | 2019-02-01 | 2019-04-12 | 2019-04-12 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-06-08 | COMP | 2020-07-09 | COMP | Rule 15/16 | 257 | 50 | 97 | 1 | 0 | 218 | 619
2881 | 2018-01-26 | 2018-02-11 | 2018-05-29 | 2018-05-29 | COMP | 2018-06-07 | COMP | 2018-07-09 | COMP | 2019-06-28 | COMP | 2019-08-12 | COMP | Rule 15/16 | 11 | 75 | 8 | 22 | 246 | 31 | 389
3303 | 2018-01-26 | 2018-04-04 | 2018-10-02 | 2018-10-02 | COMP | 2020-09-18 | COMP | 2020-10-15 | COMP | 2021-03-30 | COMP | 2021-05-05 | COMP | Rule 16 | 48 | 127 | 495 | 20 | 112 | 27 | 824
3323 | 2018-01-26 | 2018-04-09 | 2019-07-12 | 2020-05-13 | COMP | 2020-06-11 | COMP | 2020-06-17 | COMP | 2020-08-12 | COMP | 2020-08-10 | COMP | Rule 15/16 | 51 | 318 | 21 | 5 | 41 |  | 640
3335 | 2018-01-26 | 2018-04-10 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-14 | COMP | 2019-11-18 | COMP | 2020-04-01 | COMP | 2020-06-22 | COMP | Rule 15/16 | 52 | 136 | 18 | 254 | 92 | 58 | 605
3652 | 2018-01-26 | 2018-06-01 | 2018-06-08 | 2018-06-08 | COMP | 2018-10-09 | COMP | 2018-10-26 | COMP | 2018-11-21 | COMP | 2019-01-14 | COMP | Rule 16 | 89 | 6 | 86 | 14 | 18 | 35 | 243
3662 | 2018-01-26 | 2018-06-05 | 2019-02-05 | 2019-02-05 | COMP | 2019-02-25 | COMP | 2019-05-31 | COMP |  |  | 2019-07-23 | COMP | Rule 16 | 91 | 168 | 14 | 69 |  |  | 375
4598 | 2018-01-26 | 2018-02-13 | 2018-02-14 | 2018-02-14 | COMP | 2018-03-29 | COMP | 2018-03-10 | INPR | 2019-01-07 | COMP | 2019-02-05 | COMP | Rule 16 | 13 | 2 | 31 |  |  |  | 258
4664 | 2018-01-26 | 2018-03-05 | 2018-07-03 | 2018-07-03 | COMP | 2018-07-24 | COMP | 2018-07-24 | COMP | 2020-02-10 | COMP | 2022-07-04 | COMP | Rule 16 | 26 | 86 | 15 | 1 | 388 | 605 | 1116
4713 | 2018-01-26 | 2018-03-20 | 2018-08-16 | 2018-11-16 | COMP | 2019-11-14 | COMP | 2019-11-14 | COMP | 2019-12-24 | COMP | 2020-11-09 | COMP | Rule 16 | 37 | 106 | 250 | 1 | 27 | 224 | 704
4827 | 2018-01-26 | 2018-04-02 | 2018-06-23 | 2018-06-23 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-10-09 | COMP | 2020-10-30 | COMP | Rule 16 | 46 | 59 | 210 | 1 | 117 | 269 | 698
4834 | 2018-01-26 | 2018-04-03 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-01 | COMP | 2019-03-05 | COMP | Rule 16 | 47 | 209 | 8 | 1 | 0 | 16 | 277
5651 | 2018-01-26 | 2018-06-23 | 2018-09-25 | 2019-01-11 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2018-12-29 | COMP | 2019-01-30 | COMP | Rule 16 | 104 | 65 | 5 | 1 | 0 | 9 | 254
5678 | 2018-01-26 | 2018-06-25 | 2018-12-14 | 2018-12-14 | COMP | 2020-11-09 | COMP | 2021-01-22 | COMP | 2021-01-20 | COMP | 2021-02-18 | COMP | Rule 15/16 | 105 | 120 | 481 | 49 | 0 | 19 | 770
6816 | 2018-01-26 | 2018-09-12 | 2018-10-25 | 2020-06-03 | COMP | 2020-10-08 | COMP | 2020-11-30 | COMP | 2021-02-01 | COMP | 2021-03-10 | COMP | Rule 15/16 | 160 | 32 | 91 | 35 | 43 | 27 | 784
7616 | 2018-01-26 | 2018-10-23 | 2019-09-03 | 2019-09-03 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2022-01-11 | COMP | 2022-08-25 | COMP | Rule 15/16 | 189 | 216 | 197 | 1 | 398 | 158 | 1154
7715 | 2018-01-26 | 2018-10-27 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-03-29 | COMP | 2019-04-18 | COMP | Rule 16 | 192 | 21 | 5 | 1 | 79 | 15 | 309
9147 | 2018-01-26 | 2019-01-18 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-04 | COMP | 2019-02-25 | COMP | 2019-02-22 | COMP | 2019-03-15 | COMP | Rule 16 | 247 | 6 | 6 | 15 | 0 | 15 | 285
9735 | 2018-01-26 | 2019-02-13 | 2019-05-21 | 2019-05-21 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-10-15 | COMP | 2019-10-18 | COMP | Rule 15/16 | 264 | 69 | 77 | 1 | 27 | 4 | 437
10472 | 2018-01-26 | 2019-03-18 | 2019-08-30 | 2020-10-15 | COMP | 2020-11-13 | COMP | 2021-01-21 | COMP | 2021-01-21 | COMP | 2021-03-09 | COMP | Rule 15/16 | 286 | 118 | 21 | 45 | 1 | 33 | 783
14569 | 2018-01-26 | 2019-09-17 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-24 | COMP | 2019-12-26 | COMP | 2021-01-11 | COMP | 2021-03-01 | COMP | Rule 16 | 414 | 52 | 17 | 2 | 263 | 34 | 777
5593 | 2018-01-28 | 2018-06-18 | 2018-10-31 | 2018-10-31 | COMP | 2019-02-01 | COMP | 2019-02-25 | COMP | 2020-06-05 | COMP | 2020-07-21 | COMP | Rule 16 | 99 | 96 | 62 | 16 | 324 | 33 | 625
5988 | 2018-01-28 | 2018-07-17 | 2018-09-28 | 2018-09-28 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-04-02 | COMP | 2019-04-26 | COMP | Rule 15/16 | 119 | 53 | 47 | 1 | 80 | 19 | 314
2912 | 2018-01-29 | 2018-02-15 | 2018-08-04 | 2018-08-04 | COMP | 2018-08-10 | COMP | 2018-11-19 | COMP | 2019-05-17 | COMP | 2019-07-16 | COMP | Rule 16 | 14 | 119 | 5 | 70 | 124 | 41 | 369
2944 | 2018-01-29 | 2018-02-21 | 2018-09-10 | 2018-09-10 | COMP | 2018-10-17 | COMP | 2019-04-25 | COMP | 2019-08-10 | COMP | 2019-09-04 | COMP | Rule 15/16 | 17 | 141 | 28 | 130 | 75 | 17 | 404
3030 | 2018-01-29 | 2018-02-28 | 2018-12-05 | 2018-12-05 | COMP | 2019-03-06 | COMP | 2019-03-13 | COMP | 2019-10-08 | COMP | 2019-11-08 | COMP | Rule 15/16 | 22 | 195 | 62 | 6 | 147 | 24 | 451
3037 | 2018-01-29 | 2018-03-01 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-13 | COMP | 2019-06-17 | COMP | 2019-08-02 | COMP | 2019-09-06 | COMP | Rule 15/16 | 23 | 244 | 17 | 68 | 34 | 25 | 406
3081 | 2018-01-29 | 2018-03-06 | 2018-05-14 | 2018-05-14 | COMP | 2018-06-18 | COMP | 2018-06-19 | COMP | 2023-11-11 | INPR | 2019-05-06 | COMP | Rule 15/16 | 26 | 50 | 25 | 2 |  |  | 320
3258 | 2018-01-29 | 2018-03-28 | 2018-05-03 | 2018-05-03 | COMP | 2018-11-29 | COMP | 2019-01-07 | NOTN | 2019-10-11 | COMP | 2019-10-18 | COMP | Rule 16 | 42 | 27 | 145 |  |  |  | 436
3458 | 2018-01-29 | 2018-04-30 | 2018-09-26 | 2018-09-26 | COMP | 2019-03-05 | COMP | 2019-03-28 | COMP | 2019-12-28 | INPR | 2019-07-31 | COMP | Rule 15/16 | 65 | 105 | 108 | 18 |  |  | 380
3477 | 2018-01-29 | 2018-05-03 | 2018-12-03 | 2019-12-18 | COMP | 2023-04-29 | INPR | 2019-04-29 | COMP | 2019-04-26 | COMP | 2019-06-26 | COMP | Rule 15/16 | 68 | 147 |  |  | 0 | 42 | 356
3649 | 2018-01-29 | 2018-06-01 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-17 | COMP | 2018-10-30 | COMP | 2018-10-31 | COMP | 2019-01-25 | COMP | Rule 16 | 88 | 82 | 16 | 10 | 2 | 57 | 250
3678 | 2018-01-29 | 2018-06-06 | 2018-08-03 | 2018-08-03 | COMP | 2019-06-18 | COMP | 2019-09-04 | COMP | 2019-09-09 | COMP | 2019-10-16 | COMP | Rule 16 | 91 | 42 | 219 | 55 | 4 | 28 | 434
4651 | 2018-01-29 | 2018-02-26 | 2018-08-22 | 2018-08-22 | COMP | 2018-11-13 | COMP | 2018-11-13 | INPR | 2019-01-30 | COMP | 2019-03-04 | COMP | Rule 15/16 | 20 | 126 | 58 |  |  |  | 275
4833 | 2018-01-29 | 2018-04-04 | 2018-05-15 | 2018-05-15 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-02-12 | COMP | 2019-01-08 | COMP | Rule 16 | 47 | 30 | 64 | 1 | 124 |  | 238
4856 | 2018-01-29 | 2018-04-05 | 2018-07-26 | 2018-07-26 | COMP | 2018-09-07 | COMP | 2018-09-26 | COMP | 2020-03-30 | COMP | 2020-05-27 | COMP | Rule 16 | 48 | 79 | 31 | 14 | 377 | 42 | 586
4965 | 2018-01-29 | 2018-04-16 | 2018-08-07 | 2018-08-07 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-10-01 | COMP | 2019-12-05 | COMP | Rule 15/16 | 55 | 80 | 203 | 1 | 88 | 45 | 467
5102 | 2018-01-29 | 2018-04-30 | 2018-08-01 | 2018-08-01 | COMP | 2019-05-13 | COMP | 2019-06-03 | COMP | 2019-09-21 | COMP | 2019-12-13 | COMP | Rule 15/16 | 65 | 66 | 196 | 15 | 78 | 57 | 473
5254 | 2018-01-29 | 2018-05-14 | 2018-07-18 | 2018-07-18 | COMP | 2018-11-30 | COMP | 2019-06-12 | COMP | 2021-02-27 | INPR | 2019-06-20 | COMP | Rule 16 | 75 | 46 | 94 | 134 |  |  | 352
6016 | 2018-01-29 | 2018-07-18 | 2018-10-01 | 2018-10-01 | COMP | 2018-10-25 | COMP | 2018-11-30 | COMP | 2018-12-13 | COMP | 2019-01-28 | COMP | Rule 16 | 120 | 53 | 19 | 24 | 10 | 30 | 251
6147 | 2018-01-29 | 2018-07-30 | 2018-11-05 | 2018-11-05 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-01-04 | COMP | 2019-01-16 | COMP | Rule 15/16 | 128 | 70 | 10 | 1 | 31 | 9 | 244
6492 | 2018-01-29 | 2018-08-21 | 2018-10-08 | 2019-02-11 | COMP | 2019-03-01 | COMP | 2020-12-24 | COMP | 2020-12-23 | COMP | 2021-01-06 | COMP | Rule 16 | 144 | 34 | 14 | 460 | 0 | 8 | 740
7176 | 2018-01-29 | 2018-10-01 | 2020-07-07 | 2020-07-07 | COMP | 2021-03-02 | COMP | 2021-04-09 | COMP | 2021-07-30 | COMP | 2022-02-02 | COMP | Rule 15/16 | 172 | 444 | 163 | 29 | 79 | 129 | 1011
8498 | 2018-01-29 | 2018-12-05 | 2019-07-19 | 2019-07-19 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-10-01 | COMP | 2019-11-01 | COMP | Rule 16 | 216 | 157 | 10 | 1 | 43 | 24 | 446
2820 | 2018-01-30 | 2018-02-05 | 2018-06-14 | 2018-06-14 | COMP | 2018-08-01 | COMP | 2019-01-08 | COMP | 2019-11-16 | COMP | 2020-02-07 | COMP | Rule 16 | 5 | 92 | 34 | 109 | 218 | 55 | 509
3153 | 2018-01-30 | 2018-03-15 | 2018-06-14 | 2018-06-14 | COMP | 2018-06-29 | COMP | 2018-06-29 | COMP | 2021-05-29 | INPR | 2020-05-06 | COMP | Rule 16 | 32 | 65 | 12 | 1 |  |  | 571
3194 | 2018-01-30 | 2018-03-21 | 2018-08-10 | 2018-08-10 | COMP | 2018-08-30 | COMP | 2018-10-05 | COMP | 2018-11-14 | COMP | 2019-01-10 | COMP | Rule 15/16 | 36 | 101 | 15 | 26 | 28 | 38 | 239
3195 | 2018-01-30 | 2018-03-21 | 2018-08-11 | 2018-08-11 | COMP | 2018-09-06 | COMP | 2018-10-05 | COMP | 2018-11-14 | COMP | 2019-01-10 | COMP | Rule 15/16 | 36 | 101 | 18 | 22 | 28 | 38 | 239
3291 | 2018-01-30 | 2018-04-02 | 2018-06-12 | 2018-06-12 | COMP | 2019-07-08 | COMP | 2019-07-31 | COMP | 2019-07-08 | COMP | 2019-08-06 | COMP | Rule 16 | 44 | 51 | 269 | 18 | 0 | 5 | 383
3298 | 2018-01-30 | 2018-04-03 | 2018-07-23 | 2018-07-23 | COMP | 2019-07-24 | COMP | 2019-05-29 | COMP | 2021-06-16 | COMP | 2021-07-30 | COMP | Rule 16 | 45 | 78 | 253 |  | 517 | 32 | 882
3318 | 2018-01-30 | 2018-04-06 | 2018-10-12 | 2018-10-12 | COMP | 2019-02-04 | COMP | 2019-02-05 | COMP |  | INPR | 2019-03-19 | COMP | Rule 15/16 | 48 | 133 | 76 | 2 |  |  | 285
3521 | 2018-01-30 | 2018-05-10 | 2018-10-11 | 2018-10-11 | COMP | 2019-05-01 | COMP | 2019-07-12 | COMP | 2019-10-25 | COMP | 2019-12-10 | COMP | Rule 16 | 72 | 108 | 138 | 51 | 75 | 30 | 469
3767 | 2018-01-30 | 2018-07-06 | 2018-08-10 | 2018-08-10 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-04-20 | INPR | 2019-01-23 | COMP | Rule 15/16 | 111 | 26 | 90 | 1 |  |  | 247
3903 | 2018-01-30 | 2018-09-27 | 2019-07-01 | 2019-07-01 | COMP | 2020-01-08 | COMP | 2020-01-23 | COMP | 2020-03-04 | COMP | 2020-04-13 | COMP | Rule 15/16 | 169 | 190 | 131 | 11 | 29 | 29 | 554
3904 | 2018-01-30 | 2018-09-27 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-28 | COMP | 2019-11-20 | COMP | 2019-12-05 | COMP | 2020-07-08 | COMP | Rule 16 | 169 | 57 | 26 | 208 | 10 | 150 | 615
3907 | 2018-01-30 | 2018-09-28 | 2018-12-24 | 2018-12-21 | COMP | 2019-04-08 | COMP | 2019-04-10 | COMP | 2019-11-23 | INPR | 2019-08-10 | COMP | Rule 16 | 170 | 59 | 73 | 3 |  |  | 386
3933 | 2018-01-30 | 2018-10-22 | 2019-03-13 | 2019-03-13 | COMP | 2019-04-16 | COMP | 2019-05-31 | COMP |  |  | 2021-01-15 | COMP | Rule 16 | 186 | 96 | 25 | 33 |  |  | 746
3942 | 2018-01-30 | 2018-10-22 | 2019-07-08 | 2019-07-08 | COMP | 2019-09-24 | COMP | 2020-01-28 | COMP | 2020-07-28 | COMP | 2020-08-05 | COMP | Rule 16 | 186 | 177 | 56 | 85 | 129 | 7 | 635
4062 | 2018-01-30 | 2019-01-04 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-16 | COMP | 2020-10-26 | COMP | 2021-08-09 | COMP | 2021-08-25 | COMP | Rule 16 | 235 | 52 | 20 | 388 | 197 | 13 | 900
4265 | 2018-01-30 | 2020-01-14 | 2020-02-21 | 2020-02-21 | COMP | 2020-06-03 | COMP | 2020-06-11 | COMP | 2020-07-20 | COMP | 2020-12-01 | COMP | Rule 16 | 492 | 27 | 73 | 7 | 28 | 93 | 715
4647 | 2018-01-30 | 2018-02-26 | 2018-05-21 | 2018-05-21 | COMP | 2018-07-20 | COMP | 2018-07-20 | COMP | 2019-06-04 | COMP | 2019-07-22 | COMP | Rule 16 | 19 | 61 | 43 | 1 | 219 | 34 | 372
4813 | 2018-01-30 | 2018-03-31 | 2018-09-04 | 2018-09-04 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2021-09-27 | COMP | 2021-11-19 | COMP | Rule 16 | 43 | 109 | 119 | 1 | 653 | 39 | 960
4816 | 2018-01-30 | 2018-03-31 | 2018-09-19 | 2018-09-19 | COMP | 2019-02-19 | COMP | 2019-04-25 | COMP | 2022-12-06 | COMP | 2023-04-26 | COMP | Rule 16 | 43 | 120 | 103 | 48 | 910 | 98 | 1318
4855 | 2018-01-30 | 2018-04-05 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-21 | COMP | 2018-12-04 | COMP | 2018-12-06 | COMP | 2019-01-04 | COMP | Rule 15/16 | 47 | 149 | 13 | 8 | 3 | 20 | 235
5170 | 2018-01-30 | 2018-05-07 | 2018-10-29 | 2021-03-08 | COMP | 2021-03-15 | COMP | 2021-03-15 | COMP | 2021-03-19 | COMP | 2021-05-04 | COMP | Rule 16 | 69 | 123 | 6 | 1 | 5 | 33 | 821
5228 | 2018-01-30 | 2018-05-14 | 2018-07-26 | 2019-03-18 | COMP | 2019-04-08 | COMP | 2019-04-15 | COMP | 2019-04-30 | COMP | 2019-06-08 | COMP | Rule 15/16 | 74 | 52 | 16 | 6 | 12 | 28 | 342
5347 | 2018-01-30 | 2018-05-23 | 2019-01-04 | 2019-01-04 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-04-01 | COMP | 2019-04-18 | COMP | Rule 16 | 81 | 155 | 48 | 1 | 13 | 14 | 307
5607 | 2018-01-30 | 2018-06-19 | 2018-09-11 | 2018-09-11 | COMP | 2018-10-25 | COMP | 2018-11-30 | COMP | 2019-07-25 | COMP | 2019-11-17 | COMP | Rule 16 | 99 | 59 | 33 | 24 | 164 | 80 | 454
5801 | 2018-01-30 | 2018-07-03 | 2018-10-29 | 2019-12-05 | COMP | 2019-12-16 | COMP | 2019-12-23 | COMP | 2019-11-05 | COMP | 2020-01-15 | COMP | Rule 16 | 109 | 83 | 8 | 6 | 0 | 16 | 493
6156 | 2018-01-30 | 2018-08-01 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-21 | COMP | 2020-03-09 | COMP | 2020-02-13 | COMP | 2020-07-14 | COMP | Other | 129 | 185 | 18 | 200 | 0 | 91 | 619
6359 | 2018-01-30 | 2018-08-14 | 2018-11-10 | 2018-11-10 | COMP | 2018-11-15 | COMP | 2019-01-04 | COMP | 2018-12-12 | COMP | 2019-01-23 | COMP | Rule 16 | 138 | 63 | 3 | 33 | 0 | 13 | 247
6422 | 2018-01-30 | 2018-08-16 | 2019-01-30 | 2019-01-30 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-12-07 | COMP | 2020-12-10 | COMP | Other | 140 | 113 | 246 | 1 | 223 | 4 | 722
6974 | 2018-01-30 | 2018-09-19 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2018-12-18 | COMP | 2019-01-31 | COMP | Rule 16 | 163 | 40 | 25 | 1 | 0 | 28 | 253
7430 | 2018-01-30 | 2018-10-12 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-18 | COMP | 2019-04-24 | COMP | 2019-04-30 | COMP | 2019-06-04 | COMP | Rule 16 | 180 | 97 | 32 | 5 | 5 | 25 | 339
7586 | 2018-01-30 | 2018-10-22 | 2019-01-25 | 2019-02-05 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2021-05-06 | COMP | 2021-05-22 | COMP | Rule 16 | 186 | 64 | 49 | 1 | 520 | 12 | 834
8392 | 2018-01-30 | 2018-11-29 | 2019-02-14 | 2019-02-14 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-10-04 | COMP | 2019-11-03 | COMP | Rule 16 | 211 | 53 | 108 | 1 | 56 | 21 | 445
12707 | 2018-01-30 | 2019-06-19 | 2019-10-10 | 2020-03-25 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-04-09 | COMP | 2020-10-09 | COMP | Rule 15/16 | 350 | 80 | 52 | 1 | 0 | 90 | 681
14750 | 2018-01-30 | 2019-09-25 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-28 | COMP | 2020-01-31 | COMP | 2020-06-01 | COMP | 2020-07-21 | COMP | Rule 16 | 418 | 72 | 13 | 4 | 85 | 37 | 624
2919 | 2018-01-31 | 2018-02-16 | 2018-04-17 | 2018-10-02 | COMP | 2019-09-12 | COMP | 2019-05-10 | COMP | 2019-09-09 | COMP | 2019-12-19 | COMP | Rule 15/16 | 13 | 42 | 238 |  | 84 | 71 | 475
2943 | 2018-01-31 | 2018-02-21 | 2018-05-14 | 2018-05-14 | COMP | 2018-08-06 | COMP | 2019-10-15 | COMP | 2021-02-28 | INPR | 2019-12-12 | COMP | Rule 15/16 | 15 | 59 | 59 | 301 |  |  | 470
2950 | 2018-01-31 | 2018-02-21 | 2018-03-29 | 2018-03-29 | COMP | 2018-04-03 | NOTN | 2018-04-03 | COMP | 2018-12-27 | COMP | 2019-02-19 | COMP | Other | 15 | 27 |  | 4 | 186 | 36 | 264
2961 | 2018-01-31 | 2018-02-22 | 2018-07-31 | 2018-07-31 | COMP | 2019-09-09 | COMP | 2019-09-19 | COMP | 2020-04-14 | COMP | 2020-07-26 | COMP | Rule 15/16 | 16 | 112 | 279 | 9 | 142 | 73 | 626
3025 | 2018-01-31 | 2018-02-27 | 2018-08-16 | 2018-08-16 | COMP | 2020-02-05 | COMP | 2020-03-11 | COMP | 2020-04-24 | COMP | 2020-05-19 | COMP | Rule 15/16 | 19 | 121 | 368 | 25 | 33 | 18 | 579
3047 | 2018-01-31 | 2018-03-02 | 2018-08-02 | 2018-11-04 | COMP | 2019-03-14 | COMP | 2019-05-30 | COMP | 2019-05-14 | COMP | 2019-06-28 | COMP | Rule 15/16 | 22 | 108 | 87 | 55 | 0 | 22 | 356
3111 | 2018-01-31 | 2018-03-09 | 2018-11-15 | 2018-11-15 | COMP | 2019-02-28 | COMP | 2019-06-26 | COMP | 2019-05-29 | COMP | 2019-07-12 | COMP | Rule 15/16 | 27 | 176 | 70 | 84 | 0 | 12 | 365
3112 | 2018-01-31 | 2018-03-09 | 2018-11-02 | 2018-11-02 | COMP | 2020-03-16 | COMP | 2020-04-30 | COMP | 2020-05-21 | COMP | 2020-06-18 | COMP | Rule 15/16 | 27 | 168 | 340 | 34 | 16 | 20 | 600
3113 | 2018-01-31 | 2018-03-09 | 2018-09-11 | 2018-09-11 | COMP | 2019-04-16 | COMP | 2019-04-18 | COMP | 2019-06-26 | COMP | 2019-07-12 | COMP | Rule 15/16 | 27 | 130 | 149 | 3 | 49 | 12 | 365
3130 | 2018-01-31 | 2018-03-12 | 2018-05-23 | 2018-05-23 | COMP | 2018-06-05 | COMP | 2018-06-05 | COMP | 2019-01-23 | COMP | 2019-03-11 | COMP | Rule 16 | 28 | 53 | 9 | 1 | 159 | 33 | 278
3131 | 2018-01-31 | 2018-03-12 | 2018-05-23 | 2018-05-23 | COMP | 2019-02-25 | COMP | 2018-06-05 | COMP | 2018-11-04 | COMP | 2019-03-11 | COMP | Rule 16 | 28 | 53 | 189 |  | 107 | 84 | 278
3163 | 2018-01-31 | 2018-03-15 | 2018-06-08 | 2018-06-08 | COMP | 2018-06-13 | COMP | 2018-09-10 | COMP | 2019-02-05 | COMP | 2019-03-26 | COMP | Rule 16 | 31 | 61 | 4 | 62 | 101 | 35 | 289
3263 | 2018-01-31 | 2018-03-28 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-26 | COMP | 2019-09-06 | COMP | 2019-08-20 | COMP | 2019-10-17 | COMP | Rule 15/16 | 40 | 209 | 42 | 116 | 0 | 30 | 433
3597 | 2018-01-31 | 2018-05-22 | 2018-10-27 | 2018-10-27 | COMP | 2019-02-07 | COMP | 2019-04-17 | COMP | 2019-03-19 | COMP | 2019-05-15 | COMP | Rule 16 | 79 | 111 | 68 | 49 | 0 | 21 | 325
3743 | 2018-01-31 | 2018-06-26 | 2018-09-24 | 2018-09-24 | COMP | 2020-02-12 | NOTN | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-06-03 | COMP | Other | 103 | 63 |  | 347 | 1 | 79 | 589
4572 | 2018-01-31 | 2018-02-02 | 2018-06-05 | 2018-06-05 | COMP | 2018-09-26 | COMP | 2018-09-26 | COMP | 2020-04-16 | COMP | 2020-04-29 | COMP | Rule 16 | 3 | 86 | 80 | 1 | 390 | 10 | 565
5089 | 2018-01-31 | 2018-04-30 | 2018-12-07 | 2018-12-07 | COMP | 2021-06-11 | COMP | 2021-06-11 | COMP | 2021-07-15 | COMP | 2021-12-22 | COMP | Rule 16 | 63 | 154 | 632 | 1 | 24 | 111 | 980
5153 | 2018-01-31 | 2018-05-03 | 2018-08-13 | 2018-08-13 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2020-06-23 | COMP | 2020-06-29 | COMP | Rule 16 | 66 | 71 | 122 | 1 | 347 | 5 | 607
5431 | 2018-01-31 | 2018-05-30 | 2018-12-06 | 2018-12-06 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-02-07 | COMP | 2019-02-08 | COMP | Rule 16 | 84 | 132 | 10 | 1 | 34 | 2 | 258
5465 | 2018-01-31 | 2018-06-01 | 2018-09-26 | 2018-09-26 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-03-18 | COMP | 2019-04-26 | COMP | Rule 16 | 86 | 82 | 85 | 1 | 33 | 30 | 312
7896 | 2018-01-31 | 2018-11-05 | 2019-06-27 | 2019-06-27 | COMP | 2020-03-09 | COMP | 2021-07-24 | COMP | 2022-03-17 | COMP | 2022-04-22 | COMP | Rule 15/16 | 195 | 161 | 174 | 349 | 163 | 27 | 1065
8506 | 2018-01-31 | 2018-12-05 | 2020-04-06 | 2020-04-17 | COMP | 2020-05-28 | COMP | 2021-07-08 | COMP | 2021-06-14 | COMP | 2021-09-10 | COMP | Rule 15/16 | 214 | 335 | 29 | 281 | 0 | 46 | 910
14238 | 2018-01-31 | 2019-08-30 | 2020-01-15 | 2021-11-03 | COMP | 2021-12-02 | COMP | 2022-05-19 | COMP | 2023-08-15 | COMP | 2023-08-30 | COMP | Rule 16 | 400 | 93 | 19 | 119 | 310 | 12 | 1404
17014 | 2018-01-31 | 2020-01-27 | 2020-07-05 | 2020-07-05 | COMP | 2022-01-30 | INPR | 2020-08-03 | COMP | 2022-01-30 | INPR | 2020-08-04 | COMP | Rule 16 | 499 | 113 |  | 21 |  |  | 633
2797 | 2018-02-01 | 2018-02-01 | 2018-04-12 | 2018-04-12 | COMP | 2018-04-12 | NOTN |  | REQD |  | REQD | 2020-04-23 | COMP | Other | 1 | 50 |  |  |  |  | 560
2928 | 2018-02-01 | 2018-02-17 | 2018-07-16 | 2018-07-16 | COMP | 2018-10-24 | COMP | 2019-06-14 | COMP | 2019-06-19 | COMP | 2019-09-23 | COMP | Rule 15/16 | 12 | 103 | 72 | 160 | 4 | 67 | 414
3004 | 2018-02-01 | 2018-02-26 | 2018-05-25 | 2018-05-25 | COMP | 2018-09-13 | COMP | 2018-06-12 | COMP | 2019-01-03 | COMP | 2019-02-08 | COMP | Rule 16 | 17 | 65 | 77 |  | 141 | 26 | 257
3116 | 2018-02-01 | 2018-03-09 | 2018-09-04 | 2018-09-04 | COMP | 2018-12-12 | COMP | 2019-02-25 | COMP | 2019-02-28 | COMP | 2019-03-10 | COMP | Rule 15/16 | 26 | 125 | 69 | 50 | 4 | 7 | 276
3186 | 2018-02-01 | 2018-03-20 | 2018-10-26 | 2019-11-15 | COMP | 2019-02-01 | COMP | 2019-11-18 | COMP | 2020-06-16 | COMP | 2020-07-13 | COMP | Rule 15/16 | 33 | 156 |  | 202 | 145 | 20 | 616
3187 | 2018-02-01 | 2018-03-20 | 2018-06-01 | 2018-06-01 | COMP | 2018-06-19 | COMP | 2019-04-29 | COMP | 2019-06-20 | COMP | 2019-08-09 | COMP | Rule 16 | 33 | 53 | 13 | 216 | 38 | 36 | 384
3261 | 2018-02-01 | 2018-03-28 | 2018-07-09 | 2018-07-09 | COMP | 2018-11-08 | COMP | 2018-11-13 | COMP | 2023-11-11 | INPR | 2019-07-09 | COMP | Rule 15/16 | 39 | 72 | 88 | 3 |  |  | 361
3375 | 2018-02-01 | 2018-04-16 | 2018-08-14 | 2018-08-14 | COMP | 2019-05-14 | COMP | 2020-08-06 | COMP | 2020-07-24 | COMP | 2020-08-30 | COMP | Rule 16 | 52 | 85 | 188 | 312 | 0 | 17 | 650
3421 | 2018-02-01 | 2018-04-24 | 2018-12-04 | 2018-12-04 | COMP | 2019-02-20 | COMP | 2019-09-25 | COMP | 2020-04-26 | INPR | 2019-12-13 | COMP | Rule 15/16 | 58 | 155 | 53 | 153 |  |  | 470
4579 | 2018-02-01 | 2018-02-08 | 2018-04-18 | 2018-04-18 | COMP | 2018-12-07 | NOTN | 2018-12-10 | COMP | 2019-01-28 | COMP | 2019-03-18 | COMP | Other | 6 | 49 |  | 163 | 33 | 35 | 282
4658 | 2018-02-01 | 2018-03-02 | 2018-05-07 | 2018-05-07 | COMP | 2018-06-20 | COMP | 2018-06-20 | COMP | 2020-02-28 | COMP | 2021-04-18 | COMP | Rule 16 | 21 | 47 | 32 | 1 | 424 | 287 | 807
4677 | 2018-02-01 | 2018-03-09 | 2018-06-12 | 2018-06-12 | COMP | 2018-10-08 | COMP | 2019-04-30 | COMP | 2019-08-15 | COMP | 2019-10-03 | COMP | Rule 15/16 | 26 | 67 | 83 | 140 | 76 | 35 | 422
4720 | 2018-02-01 | 2018-03-22 | 2018-09-12 | 2018-09-12 | COMP | 2018-12-10 | COMP | 2021-01-07 | COMP | 2021-03-30 | COMP | 2021-04-09 | COMP | Rule 16 | 35 | 122 | 61 | 523 | 57 | 9 | 802
4725 | 2018-02-01 | 2018-03-21 | 2018-07-09 | 2018-07-09 | COMP | 2018-11-07 | COMP | 2019-06-19 | COMP | 2019-09-26 | COMP | 2019-12-06 | COMP | Rule 16 | 34 | 77 | 87 | 153 | 70 | 49 | 465
4760 | 2018-02-01 | 2018-03-27 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-07-23 | COMP | 2019-08-09 | COMP | Rule 15/16 | 38 | 219 | 27 | 1 | 90 | 14 | 384
4777 | 2018-02-01 | 2018-03-29 | 2018-05-18 | 2018-05-18 | COMP | 2018-06-29 | COMP | 2018-11-09 | COMP | 2019-10-14 | COMP | 2019-11-17 | COMP | Rule 16 | 40 | 37 | 30 | 94 | 232 | 24 | 452
4849 | 2018-02-01 | 2018-04-05 | 2018-09-05 | 2018-09-05 | COMP | 2018-10-24 | COMP | 2019-03-06 | COMP | 2019-09-16 | COMP | 2019-11-22 | COMP | Rule 16 | 45 | 107 | 36 | 89 | 136 | 49 | 457
4851 | 2018-02-01 | 2018-04-04 | 2018-06-01 | 2018-06-01 | COMP | 2018-05-30 | NOTN | 2018-06-01 | COMP | 2019-01-08 | COMP | 2019-01-30 | COMP | Other | 44 | 42 |  | 1 | 151 | 16 | 250
4872 | 2018-02-01 | 2018-04-07 | 2018-06-02 | 2018-06-02 | COMP | 2018-06-27 | COMP | 2018-06-27 | COMP | 2022-03-19 | INPR | 2021-03-05 | COMP | Rule 15/16 | 46 | 39 | 18 | 1 |  |  | 777
5033 | 2018-02-01 | 2018-04-24 | 2018-07-24 | 2018-08-27 | COMP | 2018-08-30 | COMP | 2018-09-19 | COMP | 2018-09-11 | COMP | 2019-01-02 | COMP | Rule 16 | 58 | 64 | 4 | 14 | 0 | 71 | 231
5036 | 2018-02-01 | 2018-04-24 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-04-16 | COMP | 2019-06-11 | COMP | Rule 16 | 58 | 104 | 32 | 1 | 112 | 40 | 342
5844 | 2018-02-01 | 2018-07-07 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-11 | COMP | 2019-10-31 | COMP | 2023-04-30 | INPR | 2020-08-30 | COMP | Rule 15/16 | 109 | 64 | 45 | 226 |  |  | 650
5976 | 2018-02-01 | 2018-07-16 | 2018-09-15 | 2022-01-03 | COMP | 2022-03-31 | COMP | 2022-02-28 | COMP | 2022-02-28 | COMP | 2022-03-21 | COMP | Rule 16 | 115 | 44 | 62 |  | 1 | 16 | 1040
6101 | 2018-02-01 | 2018-07-25 | 2018-09-01 | 2018-10-25 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-07-11 | COMP | 2019-08-20 | COMP | Rule 16 | 122 | 28 | 4 | 1 | 174 | 29 | 391
6296 | 2018-02-01 | 2018-08-08 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-29 | COMP | 2019-05-22 | COMP | 2019-04-30 | COMP | 2019-07-11 | COMP | Rule 16 | 132 | 175 | 7 | 18 | 0 | 35 | 363
6624 | 2018-02-01 | 2018-08-31 | 2019-02-05 | 2019-02-05 | COMP | 2019-02-13 | COMP | 2019-04-08 | COMP | 2019-02-13 | COMP | 2019-07-16 | COMP | Rule 15/16 | 149 | 106 | 7 | 38 | 0 | 70 | 366
6632 | 2018-02-01 | 2018-09-01 | 2019-02-15 | 2019-02-15 | COMP | 2019-04-26 | COMP | 2019-06-14 | COMP | 2019-07-26 | COMP | 2019-07-29 | COMP | Rule 16 | 149 | 113 | 50 | 35 | 30 | 2 | 375
7117 | 2018-02-01 | 2018-09-28 | 2018-12-05 | 2018-12-05 | COMP | 2019-07-01 | COMP | 2021-01-20 | COMP | 2021-06-10 | COMP | 2021-11-15 | COMP | Rule 16 | 168 | 46 | 144 | 391 | 100 | 110 | 954
10237 | 2018-02-01 | 2019-03-07 | 2019-09-09 | 2020-05-12 | COMP | 2020-05-27 | COMP | 2020-05-20 | COMP | 2020-03-16 | COMP | 2020-06-24 | COMP | Rule 16 | 275 | 130 | 11 |  | 0 | 25 | 603
11198 | 2018-02-01 | 2019-04-17 | 2019-12-24 | 2019-12-24 | COMP | 2020-05-18 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-09-18 | COMP | Rule 15/16 | 304 | 174 | 101 | 59 | 1 | 30 | 664
15071 | 2018-02-01 | 2019-10-10 | 2019-12-19 | 2019-12-19 | COMP | 2020-12-28 | COMP | 2021-02-25 | COMP | 2021-09-07 | COMP | 2021-10-13 | COMP | Rule 15/16 | 427 | 48 | 258 | 41 | 136 | 27 | 932
15947 | 2018-02-01 | 2019-12-03 | 2020-05-06 | 2020-06-03 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2021-04-20 | COMP | 2021-07-17 | COMP | Rule 15/16 | 462 | 108 | 50 | 1 | 173 | 62 | 870
2805 | 2018-02-02 | 2018-02-02 | 2018-03-01 | 2018-09-11 | COMP | 2019-01-30 | COMP | 2018-06-07 | COMP | 2019-03-18 | COMP | 2019-05-01 | COMP | Rule 16 | 1 | 19 | 96 |  | 194 | 33 | 313
2819 | 2018-02-02 | 2018-02-05 | 2018-09-06 | 2018-09-06 | COMP | 2018-12-31 | COMP | 2019-01-02 | COMP | 2019-01-03 | COMP | 2019-01-25 | COMP | Rule 15/16 | 2 | 150 | 79 | 2 | 2 | 16 | 246
2866 | 2018-02-02 | 2018-02-08 | 2018-10-22 | 2018-10-22 | COMP | 2018-10-22 | NOTN | 2018-10-22 | COMP | 2019-04-11 | COMP | 2019-04-27 | COMP | Other | 5 | 179 |  | 1 | 117 | 12 | 310
2938 | 2018-02-02 | 2018-02-20 | 2018-06-15 | 2018-06-15 | COMP | 2022-03-18 | COMP | 2022-03-19 | COMP | 2022-03-21 | COMP | 2022-08-03 | COMP | Rule 15/16 | 12 | 83 | 945 | 1 | 1 | 95 | 1133
2948 | 2018-02-02 | 2018-02-21 | 2018-04-24 | 2018-04-24 | COMP | 2018-06-13 | COMP | 2018-09-11 | COMP | 2019-08-31 | INPR | 2019-05-04 | COMP | Rule 16 | 13 | 45 | 36 | 63 |  |  | 315
3306 | 2018-02-02 | 2018-04-05 | 2018-11-06 | 2018-11-06 | COMP | 2019-01-07 | COMP | 2019-01-22 | COMP | 2019-09-05 | COMP | 2019-11-08 | COMP | Rule 16 | 44 | 151 | 40 | 11 | 159 | 47 | 447
3429 | 2018-02-02 | 2018-04-24 | 2018-08-17 | 2018-08-17 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-03-30 | COMP | 2019-04-17 | COMP | Rule 16 | 57 | 82 | 57 | 1 | 97 | 13 | 303
3562 | 2018-02-02 | 2018-05-16 | 2019-01-27 | 2019-07-12 | COMP | 2019-09-24 | COMP | 2019-10-02 | COMP | 2021-05-24 | COMP | 2021-07-07 | COMP | Rule 15/16 | 73 | 174 | 52 | 7 | 413 | 31 | 862
3579 | 2018-02-02 | 2018-05-18 | 2018-11-19 | 2018-11-19 | COMP | 2019-09-18 | COMP | 2021-03-10 | COMP | 2021-03-09 | COMP | 2021-05-13 | COMP | Rule 15/16 | 75 | 128 | 209 | 370 | 0 | 47 | 825
3607 | 2018-02-02 | 2018-05-23 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-17 | COMP | 2019-08-26 | COMP | 2020-01-13 | COMP | 2020-02-04 | COMP | Rule 15/16 | 78 | 261 | 29 | 29 | 95 | 16 | 503
4894 | 2018-02-02 | 2018-04-10 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-09 | NOTN | 2019-03-08 | COMP | 2019-01-09 | COMP | 2019-04-24 | COMP | Other | 47 | 189 |  | 41 | 0 | 34 | 308
5000 | 2018-02-02 | 2018-04-23 | 2018-09-09 | 2018-12-27 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-01-25 | COMP | 2019-03-12 | COMP | Rule 15/16 | 56 | 97 | 10 | 1 | 11 | 32 | 277
5299 | 2018-02-02 | 2018-05-18 | 2018-09-19 | 2018-09-19 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-01-11 | COMP | 2019-02-06 | COMP | Rule 16 | 75 | 86 | 72 | 1 | 7 | 18 | 254
5342 | 2018-02-02 | 2018-05-25 | 2019-01-14 | 2019-03-26 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-06-25 | COMP | 2019-07-11 | COMP | Rule 15/16 | 80 | 159 | 21 | 1 | 45 | 12 | 362
5493 | 2018-02-02 | 2018-06-04 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2018-12-19 | COMP | 2019-01-11 | COMP | Rule 16 | 85 | 117 | 21 | 1 | 2 | 16 | 237
5495 | 2018-02-02 | 2018-06-04 | 2018-09-19 | 2018-09-19 | COMP | 2018-12-31 | COMP | 2019-05-22 | COMP | 2021-01-28 | COMP | 2021-03-24 | COMP | Rule 16 | 85 | 76 | 70 | 100 | 424 | 39 | 789
5577 | 2018-02-02 | 2018-06-15 | 2018-10-10 | 2018-10-10 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2018-12-06 | COMP | 2019-02-07 | COMP | Rule 16 | 94 | 82 | 13 | 1 | 27 | 43 | 255
5869 | 2018-02-02 | 2018-07-09 | 2018-11-15 | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-02-01 | NOTN | 2018-08-01 | COMP | 2019-02-21 | COMP | Rule 16 | 109 | 92 | 2 |  |  |  | 264
7950 | 2018-02-02 | 2018-11-08 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-06-04 | COMP | 2019-07-05 | COMP | Rule 16 | 196 | 51 | 44 | 1 | 48 | 23 | 358
7958 | 2018-02-02 | 2018-11-07 | 2019-01-09 | 2019-03-11 | COMP | 2019-03-21 | NOTN | 2019-03-21 | COMP | 2019-02-06 | NOTN | 2019-04-16 | COMP | Other | 195 | 41 |  | 9 |  |  | 302
12780 | 2018-02-02 | 2019-06-21 | 2019-08-25 | 2019-08-25 | COMP | 2019-09-23 | COMP | 2019-09-27 | COMP |  |  | 2020-09-17 | COMP | Rule 16 | 349 | 45 | 20 | 5 |  |  | 662
13188 | 2018-02-02 | 2019-07-15 | 2019-10-09 | 2019-10-09 | COMP | 2020-04-08 | COMP | 2020-05-08 | COMP | 2020-09-22 | COMP | 2020-09-02 | COMP | Other | 364 | 62 | 124 | 23 | 96 |  | 652
2993 | 2018-02-03 | 2018-02-27 | 2018-07-09 | 2018-07-09 | COMP | 2018-07-25 | COMP | 2019-06-19 | COMP | 2019-05-23 | COMP | 2019-07-22 | COMP | Rule 15/16 | 16 | 93 | 13 | 227 | 0 | 23 | 368
24657 | 2018-02-04 | 2021-01-07 | 2021-09-22 | 2022-05-05 | COMP | 2022-05-27 | COMP | 2023-11-01 | INPR |  | REQD | 2022-08-03 | COMP | Rule 15/16 | 736 | 180 | 17 |  |  |  | 1132
24673 | 2018-02-04 | 2021-01-06 | 2021-09-22 | 2022-05-06 | COMP | 2022-05-26 | COMP | 2022-05-26 | COMP |  | INPR | 2022-08-03 | COMP | Rule 15/16 | 735 | 181 | 15 | 1 |  |  | 1132
2998 | 2018-02-05 | 2018-02-26 | 2018-10-22 | 2018-10-22 | COMP | 2018-10-26 | REQD | 2018-11-29 | COMP | 2018-10-28 | COMP | 2019-03-29 | COMP | Rule 16 | 15 | 168 |  | 26 | 0 | 83 | 289
3101 | 2018-02-05 | 2018-03-08 | 2018-06-18 | 2018-06-18 | COMP | 2018-05-25 | NOTN | 2019-10-14 | COMP | 2018-05-25 | NOTN | 2019-12-10 | COMP | Other | 23 | 72 |  | 334 |  |  | 465
3632 | 2018-02-05 | 2018-05-30 | 2019-04-13 | 2019-06-04 | COMP | 2019-05-17 | COMP | 2019-07-08 | COMP | 2019-09-16 | COMP | 2019-10-03 | COMP | Rule 15/16 | 81 | 219 |  | 35 | 50 | 14 | 420
3966 | 2018-02-05 | 2018-10-30 | 2019-02-12 | 2019-02-12 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2020-08-21 | COMP | 2020-09-03 | COMP | Rule 16 | 188 | 70 | 107 | 2 | 280 | 10 | 652
4013 | 2018-02-05 | 2018-11-29 | 2019-05-14 | 2019-05-14 | COMP | 2019-07-26 | COMP | 2019-07-30 | COMP | 2020-08-14 | COMP | 2020-09-23 | COMP | Rule 16 | 207 | 115 | 52 | 3 | 265 | 28 | 665
4666 | 2018-02-05 | 2018-03-06 | 2018-03-09 | 2018-03-09 | COMP | 2018-03-30 | COMP | 2018-03-30 | COMP | 2019-07-21 | INPR | 2019-03-20 | COMP | Rule 16 | 21 | 4 | 16 | 1 |  |  | 282
4684 | 2018-02-05 | 2018-03-14 | 2018-06-15 | 2018-06-15 | COMP | 2018-06-28 | COMP | 2018-06-28 | COMP | 2018-09-25 | COMP | 2020-11-07 | COMP | Rule 16 | 27 | 67 | 10 | 1 | 62 | 535 | 697
4809 | 2018-02-05 | 2018-03-31 | 2018-10-30 | 2018-10-30 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-03-05 | COMP | 2019-04-12 | COMP | Rule 16 | 39 | 149 | 83 | 1 | 2 | 29 | 299
4854 | 2018-02-05 | 2018-04-04 | 2018-06-11 | 2018-06-11 | COMP | 2018-07-12 | COMP | 2018-07-12 | COMP | 2019-04-11 | COMP | 2019-05-10 | COMP | Rule 16 | 42 | 48 | 23 | 1 | 188 | 22 | 319
4860 | 2018-02-05 | 2018-04-06 | 2018-05-18 | 2018-05-18 | COMP | 2018-08-28 | COMP | 2018-08-28 | COMP | 2019-01-28 | COMP | 2019-02-24 | COMP | Rule 16 | 44 | 31 | 71 | 1 | 103 | 19 | 264
4888 | 2018-02-05 | 2018-04-10 | 2018-12-21 | 2018-12-21 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-11-24 | INPR | 2019-07-19 | COMP | Rule 16 | 46 | 178 | 78 | 1 |  |  | 367
5050 | 2018-02-05 | 2018-04-26 | 2019-03-06 | 2019-07-11 | COMP | 2020-03-10 | COMP | 2020-06-01 | COMP | 2020-06-22 | COMP | 2020-07-30 | COMP | Rule 15/16 | 58 | 215 | 166 | 59 | 16 | 29 | 627
5125 | 2018-02-05 | 2018-05-02 | 2018-08-16 | 2018-08-16 | COMP | 2018-09-28 | COMP | 2018-11-30 | COMP | 2018-11-02 | COMP | 2019-01-14 | COMP | Rule 16 | 62 | 75 | 31 | 43 | 0 | 30 | 237
5354 | 2018-02-05 | 2018-05-23 | 2018-11-10 | 2019-04-21 | INPR | 2018-12-10 | COMP | 2018-12-17 | COMP | 2018-12-19 | COMP | 2019-01-23 | COMP | Unknown | 77 |  |  |  | 3 | 23 | 243
5357 | 2018-02-05 | 2018-05-23 | 2018-08-24 | 2018-08-24 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-01-14 | COMP | Rule 15/16 | 77 | 66 | 73 | 1 | 1 | 24 | 237
5578 | 2018-02-05 | 2018-06-15 | 2019-01-07 | 2019-01-07 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-04-02 | COMP | Rule 16 | 93 | 140 | 28 | 1 | 1 | 33 | 291
5611 | 2018-02-05 | 2018-06-19 | 2019-01-28 | 2019-12-19 | COMP | 2019-12-30 | COMP | 2020-03-03 | COMP | 2020-02-19 | COMP | 2020-03-20 | COMP | Rule 15/16 | 95 | 152 | 7 | 44 | 0 | 14 | 534
6033 | 2018-02-05 | 2018-07-19 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-02-11 | COMP | 2019-04-08 | COMP | Rule 16 | 116 | 85 | 23 | 1 | 35 | 40 | 295
6057 | 2018-02-05 | 2018-07-23 | 2018-08-21 | 2018-08-21 | COMP | 2018-10-01 | COMP | 2018-12-19 | COMP | 2019-11-07 | COMP | 2020-01-27 | COMP | Rule 16 | 118 | 22 | 29 | 55 | 225 | 52 | 496
6378 | 2018-02-05 | 2018-08-14 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-06-17 | COMP | 2019-07-21 | COMP | Rule 16 | 134 | 70 | 13 | 1 | 130 | 24 | 367
6911 | 2018-02-05 | 2018-09-17 | 2019-03-13 | 2019-10-16 | COMP | 2019-04-03 | COMP | 2019-08-19 | COMP | 2019-10-22 | COMP | 2019-11-25 | COMP | Rule 15/16 | 157 | 121 |  | 97 | 46 | 24 | 456
7077 | 2018-02-05 | 2018-09-25 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-04 | COMP | 2018-12-05 | COMP | 2019-09-12 | COMP | 2019-11-19 | COMP | Rule 16 | 163 | 34 | 14 | 2 | 195 | 48 | 452
7277 | 2018-02-05 | 2018-10-05 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-14 | COMP | 2019-08-30 | COMP | 2019-09-12 | COMP | 2019-10-04 | COMP | Rule 15/16 | 171 | 200 | 16 | 13 | 9 | 17 | 421
7726 | 2018-02-05 | 2018-10-26 | 2019-01-31 | 2019-02-26 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-05-01 | COMP | 2019-12-06 | COMP | Rule 16 | 186 | 64 | 30 | 1 | 18 | 152 | 463
9250 | 2018-02-05 | 2019-01-24 | 2019-09-04 | 2019-09-04 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-11-24 | COMP | 2020-12-10 | COMP | Rule 15/16 | 244 | 156 | 186 | 1 | 125 | 11 | 718
9522 | 2018-02-05 | 2019-02-06 | 2019-12-24 | 2019-12-24 | COMP | 2019-12-31 | COMP | 2022-03-27 | COMP | 2022-03-30 | COMP | 2022-04-24 | COMP | Rule 16 | 253 | 223 | 5 | 564 | 3 | 18 | 1062
10156 | 2018-02-05 | 2019-03-05 | 2019-05-17 | 2019-06-27 | COMP | 2019-08-20 | COMP | 2019-09-09 | COMP | 2020-01-10 | COMP | 2020-02-19 | COMP | Rule 15/16 | 271 | 54 | 38 | 14 | 85 | 27 | 512
12230 | 2018-02-05 | 2019-05-29 | 2019-09-12 | 2019-09-12 | COMP | 2019-09-20 | COMP | 2022-07-14 | COMP | 2022-07-20 | COMP | 2022-08-12 | COMP | Rule 15 | 331 | 75 | 7 | 708 | 5 | 18 | 1139
3178 | 2018-02-06 | 2018-03-19 | 2018-08-21 | 2018-08-21 | COMP | 2019-01-07 | COMP | 2019-01-07 | COMP | 2020-07-07 | COMP | 2020-07-29 | COMP | Rule 15/16 | 29 | 110 | 94 | 1 | 379 | 17 | 625
3236 | 2018-02-06 | 2018-03-26 | 2018-06-28 | 2018-06-28 | COMP | 2019-07-25 | COMP | 2019-07-31 | COMP | 2020-03-04 | COMP | 2020-06-05 | COMP | Rule 16 | 34 | 68 | 270 | 5 | 148 | 67 | 587
3285 | 2018-02-06 | 2018-04-02 | 2018-06-18 | 2018-06-18 | COMP | 2018-12-27 | COMP | 2019-02-19 | COMP | 2019-07-21 | INPR | 2019-03-28 | COMP | Rule 16 | 39 | 55 | 133 | 36 |  |  | 287
3427 | 2018-02-06 | 2018-04-24 | 2019-02-26 | 2019-02-26 | COMP | 2019-11-12 | COMP | 2020-08-05 | COMP | 2020-09-29 | COMP | 2020-10-19 | COMP | Rule 16 | 55 | 211 | 182 | 185 | 39 | 15 | 682
3588 | 2018-02-06 | 2018-05-22 | 2018-10-22 | 2018-10-22 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2018-12-17 | COMP | 2019-01-25 | COMP | Rule 16 | 75 | 107 | 29 | 1 | 10 | 27 | 244
3736 | 2018-02-06 | 2018-06-21 | 2018-07-10 | 2018-07-10 | COMP | 2018-08-14 | COMP | 2023-04-15 | CANC | 2023-04-15 | CANC | 2020-06-03 | COMP | Rule 16 | 96 | 13 | 26 |  |  |  | 585
4015 | 2018-02-06 | 2018-11-30 | 2019-10-16 | 2019-10-16 | COMP | 2020-01-07 | COMP | 2020-01-17 | COMP | 2020-04-02 | COMP | 2021-01-21 | COMP | Rule 16 | 207 | 222 | 55 | 9 | 53 | 203 | 744
4657 | 2018-02-06 | 2018-03-02 | 2018-05-09 | 2018-05-09 | COMP | 2018-05-29 | COMP | 2018-05-29 | COMP | 2018-06-15 | COMP | 2021-04-18 | COMP | Rule 16 | 18 | 49 | 14 | 1 | 14 | 713 | 804
4661 | 2018-02-06 | 2018-03-01 | 2018-08-22 | 2018-08-22 | COMP | 2018-09-13 | COMP | 2018-11-05 | COMP | 2018-12-04 | NOTN | 2019-01-14 | COMP | Rule 16 | 17 | 123 | 16 | 38 |  |  | 236
4672 | 2018-02-06 | 2018-03-07 | 2018-04-21 | 2018-11-19 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-02-06 | COMP | 2019-02-25 | COMP | Rule 16 | 21 | 33 | 14 | 1 | 40 | 13 | 264
4726 | 2018-02-06 | 2018-03-21 | 2018-10-01 | 2018-10-01 | COMP | 2018-10-18 | COMP | 2018-12-18 | COMP | 2019-01-04 | COMP | 2019-02-01 | COMP | Rule 16 | 31 | 136 | 14 | 41 | 12 | 20 | 249
4906 | 2018-02-06 | 2018-04-11 | 2018-12-04 | 2020-05-04 | COMP | 2020-06-03 | COMP | 2020-06-04 | COMP | 2020-08-04 | COMP | 2020-10-19 | COMP | Rule 16 | 46 | 164 | 22 | 2 | 44 | 54 | 682
5031 | 2018-02-06 | 2018-04-24 | 2018-06-25 | 2018-06-25 | COMP | 2018-09-05 | COMP | 2018-11-29 | COMP | 2019-10-21 | INPR | 2019-03-23 | COMP | Rule 16 | 55 | 44 | 51 | 59 |  |  | 283
5109 | 2018-02-06 | 2018-04-30 | 2018-09-17 | 2019-03-18 | COMP | 2019-04-10 | COMP | 2019-05-16 | COMP | 2019-09-30 | COMP | 2019-10-15 | COMP | Rule 15/16 | 59 | 98 | 18 | 27 | 95 | 12 | 427
5110 | 2018-02-06 | 2018-04-30 | 2018-09-25 | 2018-09-25 | COMP | 2018-10-25 | COMP | 2019-06-06 | COMP | 2019-08-07 | COMP | 2019-12-13 | COMP | Rule 15/16 | 59 | 104 | 23 | 153 | 44 | 89 | 467
5149 | 2018-02-06 | 2018-05-04 | 2018-10-16 | 2018-10-16 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP |  | INPR | 2021-06-23 | COMP | Rule 16 | 63 | 115 | 60 | 1 |  |  | 851
5320 | 2018-02-06 | 2018-05-22 | 2018-10-09 | 2019-01-08 | COMP | 2019-02-06 | COMP | 2019-05-13 | COMP | 2019-09-17 | COMP | 2019-10-16 | COMP | Rule 16 | 75 | 98 | 21 | 68 | 89 | 22 | 428
5466 | 2018-02-06 | 2018-06-01 | 2018-10-17 | 2018-10-17 | COMP | 2019-05-03 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-07-25 | COMP | Rule 16 | 82 | 97 | 136 | 10 | 1 | 49 | 370
5671 | 2018-02-06 | 2018-06-25 | 2019-03-13 | 2019-04-04 | COMP | 2021-05-25 | COMP | 2021-07-07 | COMP | 2021-06-24 | COMP | 2021-11-18 | COMP | Rule 15/16 | 98 | 179 | 540 | 30 | 0 | 95 | 954
6112 | 2018-02-06 | 2018-07-26 | 2018-08-27 | 2018-08-27 | COMP | 2018-10-16 | COMP | 2018-10-16 | COMP | 2019-05-21 | COMP | 2019-07-22 | COMP | Rule 16 | 120 | 23 | 36 | 1 | 149 | 43 | 367
6180 | 2018-02-06 | 2018-08-03 | 2018-12-03 | 2018-12-03 | COMP | 2018-12-17 | COMP | 2018-12-20 | COMP | 2018-12-26 | COMP | 2019-04-08 | COMP | Rule 16 | 126 | 83 | 11 | 4 | 4 | 71 | 294
6545 | 2018-02-06 | 2018-08-27 | 2019-03-10 | 2019-03-10 | COMP | 2019-10-10 | COMP | 2019-11-14 | COMP | 2019-11-26 | COMP | 2019-12-16 | COMP | Rule 16 | 142 | 132 | 151 | 25 | 9 | 13 | 468
6821 | 2018-02-06 | 2018-09-12 | 2018-12-30 | 2019-04-10 | COMP | 2019-04-18 | COMP | 2019-01-23 | COMP | 2019-07-22 | COMP | 2019-08-22 | COMP | Rule 16 | 153 | 74 | 7 |  | 126 | 24 | 390
7241 | 2018-02-06 | 2018-10-04 | 2018-11-10 | 2018-11-10 | COMP | 2019-03-25 | COMP | 2019-10-21 | REQD | 2019-10-21 | REQD | 2019-06-04 | COMP | Rule 16 | 169 | 27 | 89 |  |  |  | 334
8589 | 2018-02-06 | 2018-12-11 | 2019-03-06 | 2019-05-30 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-09-05 | COMP | 2019-09-26 | COMP | Rule 16 | 214 | 58 | 27 | 1 | 43 | 16 | 414
8824 | 2018-02-06 | 2019-01-02 | 2019-02-22 | 2019-02-22 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-06-19 | COMP | 2019-07-31 | COMP | Rule 16 | 228 | 36 | 53 | 1 | 31 | 30 | 374
12249 | 2018-02-06 | 2019-05-29 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-07 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-07-09 | COMP | Rule 16 | 330 | 1 | 8 | 19 | 1 | 4 | 358
12699 | 2018-02-06 | 2019-06-18 | 2019-07-15 | 2019-07-15 | COMP | 2019-08-01 | COMP | 2019-12-16 | COMP | 2019-12-17 | COMP | 2020-01-07 | COMP | Rule 16 | 344 | 19 | 14 | 94 | 2 | 14 | 482
3009 | 2018-02-07 | 2018-02-26 | 2019-03-20 | 2019-03-20 | COMP | 2019-06-10 | COMP | 2019-11-26 | COMP | 2019-11-25 | COMP | 2019-12-15 | COMP | Rule 16 | 13 | 268 | 58 | 119 | 0 | 12 | 466
3041 | 2018-02-07 | 2018-03-01 | 2018-05-03 | 2018-05-03 | COMP | 2019-06-10 | COMP | 2019-07-09 | COMP | 2019-12-29 | INPR | 2019-08-02 | COMP | Rule 15/16 | 16 | 46 | 277 | 21 |  |  | 375
3097 | 2018-02-07 | 2018-03-08 | 2018-10-27 | 2018-10-27 | COMP | 2019-02-07 | COMP | 2019-02-13 | COMP | 2019-03-22 | COMP | 2019-05-03 | COMP | Rule 16 | 21 | 164 | 68 | 5 | 27 | 31 | 312
3235 | 2018-02-07 | 2018-03-26 | 2018-06-22 | 2018-06-22 | COMP | 2019-01-28 | COMP | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-03-22 | COMP | Rule 16 | 33 | 64 | 149 | 3 | 7 | 31 | 282
3636 | 2018-02-07 | 2018-05-30 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-05 | COMP | 2020-01-03 | COMP | 2019-11-19 | COMP | 2020-01-24 | COMP | Rule 16 | 79 | 92 | 21 | 290 | 0 | 15 | 493
3701 | 2018-02-07 | 2018-06-12 | 2018-08-02 | 2018-08-02 | COMP | 2018-09-12 | COMP | 2018-11-30 | COMP | 2019-01-16 | COMP | 2019-03-15 | COMP | Rule 16 | 88 | 37 | 29 | 55 | 32 | 41 | 277
4660 | 2018-02-07 | 2018-02-28 | 2018-05-14 | 2018-05-14 | COMP | 2019-01-11 | COMP | 2019-03-13 | COMP | 2019-01-04 | COMP | 2019-03-26 | COMP | Rule 16 | 15 | 54 | 167 | 42 | 0 | 10 | 284
4693 | 2018-02-07 | 2018-03-14 | 2018-05-18 | 2018-05-18 | COMP | 2018-06-05 | COMP | 2018-09-18 | COMP | 2019-04-09 | COMP | 2019-06-13 | COMP | Rule 16 | 25 | 48 | 12 | 74 | 139 | 47 | 340
4793 | 2018-02-07 | 2018-03-30 | 2018-06-05 | 2018-06-05 | COMP | 2018-08-22 | COMP | 2018-09-11 | COMP | 2019-02-04 | COMP | 2019-03-29 | COMP | Rule 16 | 37 | 47 | 56 | 14 | 99 | 39 | 287
5154 | 2018-02-07 | 2018-05-03 | 2018-09-06 | 2018-09-06 | COMP | 2019-02-05 | COMP | 2019-04-05 | COMP | 2019-03-05 | COMP | 2019-04-24 | COMP | Rule 16 | 61 | 88 | 103 | 43 | 0 | 14 | 305
5203 | 2018-02-07 | 2018-05-10 | 2018-08-20 | 2018-08-20 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2020-03-06 | COMP | 2020-04-15 | COMP | Rule 16 | 66 | 71 | 216 | 1 | 172 | 29 | 550
5285 | 2018-02-07 | 2018-05-17 | 2018-07-18 | 2018-07-18 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-01-10 | COMP | 2019-04-08 | COMP | Rule 16 | 71 | 43 | 100 | 1 | 22 | 61 | 293
5331 | 2018-02-07 | 2018-05-22 | 2019-06-12 | 2020-03-05 | COMP | 2020-03-31 | COMP | 2020-05-11 | COMP | 2020-12-16 | COMP | 2021-02-26 | COMP | Rule 15/16 | 74 | 266 | 19 | 30 | 153 | 49 | 768
5356 | 2018-02-07 | 2018-05-23 | 2018-07-28 | 2018-07-28 | COMP | 2020-01-03 | COMP | 2019-12-11 | COMP | 2020-01-06 | COMP | 2020-02-06 | COMP | Rule 15/16 | 75 | 46 | 359 |  | 17 | 23 | 502
5646 | 2018-02-07 | 2018-06-22 | 2018-09-20 | 2018-09-20 | COMP | 2018-11-06 | COMP | 2019-01-07 | COMP | 2019-01-15 | COMP | 2019-01-10 | COMP | Rule 16 | 96 | 63 | 34 | 40 | 7 |  | 233
6058 | 2018-02-07 | 2018-07-23 | 2018-10-08 | 2018-10-08 | COMP | 2018-10-30 | COMP | 2018-11-30 | COMP | 2019-05-24 | COMP | 2019-07-12 | COMP | Rule 16 | 116 | 55 | 17 | 21 | 122 | 34 | 360
6173 | 2018-02-07 | 2018-08-01 | 2018-09-05 | 2018-09-05 | COMP | 2019-01-04 | COMP | 2019-01-04 | INPR | 2019-01-07 | COMP | 2019-01-08 | COMP | Rule 16 | 123 | 25 | 83 |  |  |  | 231
6206 | 2018-02-07 | 2018-08-03 | 2018-10-02 | 2018-10-02 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2019-01-22 | COMP | 2019-02-19 | COMP | Rule 16 | 125 | 42 | 35 | 1 | 41 | 20 | 259
6416 | 2018-02-07 | 2018-08-17 | 2018-09-24 | 2018-10-17 | COMP | 2018-11-05 | COMP | 2019-04-08 | COMP | 2019-05-16 | COMP | 2019-05-21 | COMP | Rule 16 | 135 | 26 | 14 | 104 | 29 | 4 | 324
7178 | 2018-02-07 | 2018-10-01 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2020-01-19 | INPR | 2019-10-01 | COMP | Rule 15/16 | 165 | 33 | 18 | 1 |  |  | 416
7428 | 2018-02-07 | 2018-10-12 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-08 | COMP | 2019-03-20 | COMP | 2020-01-19 | INPR | 2019-08-08 | COMP | Rule 15/16 | 174 | 48 | 33 | 28 |  |  | 379
7434 | 2018-02-07 | 2018-10-12 | 2019-01-22 | 2019-01-22 | COMP | 2019-04-11 | COMP | 2019-05-14 | COMP | 2019-06-26 | COMP | 2019-08-01 | COMP | Rule 16 | 174 | 67 | 57 | 24 | 31 | 26 | 374
8103 | 2018-02-07 | 2018-11-15 | 2019-03-08 | 2019-03-08 | COMP | 2019-05-09 | COMP | 2019-05-30 | COMP | 2019-05-20 | COMP | 2019-07-01 | COMP | Rule 16 | 197 | 76 | 45 | 15 | 0 | 23 | 352
8764 | 2018-02-07 | 2018-12-23 | 2020-02-10 | 2020-02-10 | COMP | 2020-05-04 | COMP | 2020-05-27 | COMP | 2021-10-23 | INPR | 2020-06-17 | COMP | Rule 16 | 221 | 283 | 60 | 17 |  |  | 594
8929 | 2018-02-07 | 2019-01-08 | 2019-08-30 | 2019-08-30 | COMP | 2021-01-04 | COMP | 2021-04-15 | COMP | 2021-04-06 | COMP | 2021-05-10 | COMP | Rule 15/16 | 231 | 165 | 337 | 72 | 0 | 18 | 819
10585 | 2018-02-07 | 2019-03-22 | 2020-03-04 | 2022-02-08 | COMP | 2020-04-25 | NOTN | 2022-10-28 | COMP | 2021-03-01 | COMP | 2023-08-10 | COMP | Other | 282 | 239 |  | 184 | 0 | 195 | 1385
11026 | 2018-02-07 | 2019-04-09 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-27 | COMP | 2019-11-26 | COMP | 2019-11-07 | COMP | 2019-12-09 | COMP | Rule 16 | 294 | 65 | 35 | 64 | 0 | 8 | 462
2957 | 2018-02-08 | 2018-02-22 | 2018-05-07 | 2018-05-07 | COMP | 2018-12-07 | NOTN | 2018-12-10 | COMP | 2018-12-26 | COMP | 2019-02-11 | COMP | Other | 10 | 53 |  | 150 | 12 | 32 | 253
3106 | 2018-02-08 | 2018-03-09 | 2018-07-23 | 2018-07-23 | COMP | 2018-08-21 | COMP | 2018-11-29 | COMP | 2018-10-31 | COMP | 2019-01-08 | COMP | Rule 16 | 21 | 95 | 22 | 69 | 0 | 27 | 230
3115 | 2018-02-08 | 2018-03-09 | 2018-05-03 | 2018-05-03 | COMP | 2018-05-23 | COMP | 2018-09-13 | COMP | 2018-12-10 | COMP | 2019-04-20 | COMP | Rule 16 | 21 | 40 | 15 | 79 | 60 | 91 | 301
3324 | 2018-02-08 | 2018-04-09 | 2018-10-04 | 2019-05-17 | COMP | 2019-06-10 | COMP | 2019-06-11 | COMP | 2019-06-17 | COMP | 2019-08-27 | COMP | Rule 16 | 42 | 126 | 16 | 2 | 5 | 51 | 391
3622 | 2018-02-08 | 2018-05-24 | 2018-06-26 | 2018-06-26 | COMP | 2019-06-24 | COMP | 2019-07-08 | COMP | 2019-07-03 | COMP | 2020-02-01 | COMP | Rule 15/16 | 75 | 23 | 250 | 10 | 0 | 143 | 497
3711 | 2018-02-08 | 2018-06-14 | 2019-01-25 | 2019-01-25 | COMP | 2019-06-18 | COMP | 2019-08-08 | COMP | 2019-09-03 | COMP | 2019-12-03 | COMP | Rule 15/16 | 89 | 154 | 101 | 37 | 18 | 63 | 457
3713 | 2018-02-08 | 2018-06-15 | 2019-01-25 | 2019-08-14 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-04-28 | COMP | Rule 15/16 | 90 | 153 | 114 | 1 | 1 | 64 | 558
3714 | 2018-02-08 | 2018-06-15 | 2019-01-25 | 2019-08-14 | COMP | 2021-04-15 | COMP | 2021-12-02 | COMP | 2021-11-12 | COMP | 2022-01-19 | COMP | Rule 15/16 | 90 | 153 | 420 | 160 | 0 | 34 | 993
3715 | 2018-02-08 | 2018-06-15 | 2019-01-25 | 2019-01-25 | COMP | 2021-04-15 | COMP | 2021-10-29 | COMP | 2022-02-08 | COMP | 2022-06-02 | COMP | Rule 15/16 | 90 | 153 | 560 | 139 | 69 | 81 | 1087
3835 | 2018-02-08 | 2018-08-08 | 2018-09-10 | 2018-09-10 | COMP | 2018-10-02 | COMP | 2018-11-08 | NOTN | 2020-01-28 | COMP | 2020-03-24 | COMP | Rule 16 | 127 | 23 | 17 |  |  |  | 533
4662 | 2018-02-08 | 2018-03-02 | 2018-03-03 | 2018-03-03 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-09-22 | INPR | 2019-05-28 | COMP | Rule 16 | 16 | 1 | 196 | 1 |  |  | 327
4663 | 2018-02-08 | 2018-03-02 | 2018-07-12 | 2019-02-11 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-04-19 | COMP | 2019-05-07 | COMP | Rule 15/16 | 16 | 93 | 46 | 1 | 4 | 13 | 313
4785 | 2018-02-08 | 2018-03-29 | 2018-08-22 | 2018-08-22 | COMP | 2019-01-10 | COMP | 2019-01-28 | COMP | 2019-01-03 | COMP | 2019-04-05 | COMP | Rule 16 | 35 | 103 | 96 | 12 | 0 | 49 | 291
4810 | 2018-02-08 | 2018-03-31 | 2018-10-10 | 2018-10-10 | COMP | 2019-01-24 | COMP | 2019-01-25 | COMP | 2019-04-05 | COMP | 2019-06-12 | COMP | Rule 15/16 | 36 | 135 | 71 | 2 | 50 | 48 | 338
4832 | 2018-02-08 | 2018-04-04 | 2018-06-05 | 2018-06-05 | COMP | 2018-10-10 | COMP | 2018-10-10 | COMP | 2019-10-02 | COMP | 2019-11-22 | COMP | Rule 16 | 39 | 44 | 90 | 1 | 246 | 37 | 452
4868 | 2018-02-08 | 2018-04-05 | 2018-07-18 | 2018-09-04 | COMP | 2018-10-10 | COMP | 2018-10-11 | COMP | 2018-12-11 | COMP | 2019-03-23 | COMP | Rule 16 | 40 | 73 | 27 | 2 | 41 | 70 | 281
4886 | 2018-02-08 | 2018-04-09 | 2019-01-10 | 2019-03-04 | COMP | 2019-04-22 | COMP | 2019-05-08 | COMP | 2019-04-23 | COMP | 2019-05-28 | COMP | Rule 15/16 | 42 | 191 | 36 | 13 | 0 | 14 | 327
4887 | 2018-02-08 | 2018-04-09 | 2018-11-26 | 2018-11-26 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-06-12 | COMP | 2019-07-28 | COMP | Rule 16 | 42 | 160 | 126 | 1 | 13 | 32 | 369
5006 | 2018-02-08 | 2018-04-23 | 2018-10-08 | 2018-10-08 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2018-12-10 | COMP | 2019-01-09 | COMP | Rule 15/16 | 52 | 118 | 17 | 1 | 27 | 21 | 231
5095 | 2018-02-08 | 2018-05-01 | 2018-09-07 | 2019-01-14 | COMP | 2019-02-06 | COMP | 2019-02-14 | COMP | 2019-02-13 | COMP | 2019-04-12 | COMP | Rule 16 | 58 | 91 | 17 | 7 | 0 | 41 | 296
5097 | 2018-02-08 | 2018-04-30 | 2018-11-14 | 2018-11-14 | COMP | 2019-01-03 | COMP | 2019-02-12 | COMP | 2020-12-07 | COMP | 2021-03-12 | COMP | Rule 15/16 | 57 | 139 | 33 | 28 | 459 | 66 | 777
5187 | 2018-02-08 | 2018-05-08 | 2018-07-10 | 2018-07-10 | COMP | 2018-10-17 | COMP | 2018-10-17 | COMP | 2019-09-01 | INPR | 2019-05-03 | COMP | Rule 16 | 63 | 44 | 71 | 1 |  |  | 311
6006 | 2018-02-08 | 2018-07-18 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2020-03-25 | COMP | 2020-05-20 | COMP | Rule 16 | 112 | 107 | 14 | 1 | 304 | 41 | 574
6111 | 2018-02-08 | 2018-07-26 | 2018-09-19 | 2018-09-19 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2018-12-21 | COMP | 2019-03-13 | COMP | Rule 16 | 118 | 39 | 42 | 1 | 24 | 55 | 274
6435 | 2018-02-08 | 2018-08-18 | 2018-10-01 | 2018-12-04 | COMP | 2019-01-25 | COMP | 2019-03-04 | COMP | 2019-03-03 | COMP | 2019-03-28 | COMP | Rule 16 | 134 | 30 | 36 | 26 | 0 | 19 | 285
6442 | 2018-02-08 | 2018-08-18 | 2019-01-14 | 2019-01-14 | COMP | 2019-03-18 | COMP | 2019-04-25 | COMP | 2020-01-25 | COMP | 2020-04-02 | COMP | Rule 16 | 134 | 100 | 44 | 29 | 188 | 48 | 540
7374 | 2018-02-08 | 2018-10-09 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-08 | COMP | 2019-08-21 | COMP | 2021-08-10 | COMP | 2021-09-18 | COMP | Rule 16 | 170 | 113 | 33 | 74 | 496 | 28 | 909
7545 | 2018-02-08 | 2018-10-19 | 2018-12-04 | 2018-12-04 | COMP | 2018-12-13 | COMP | 2019-02-11 | COMP | 2019-02-08 | COMP | 2019-03-29 | COMP | Rule 16 | 178 | 30 | 8 | 40 | 0 | 34 | 286
8018 | 2018-02-08 | 2018-11-09 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-30 | COMP | 2020-05-08 | COMP | 2020-04-30 | COMP | 2020-06-16 | COMP | Rule 16 | 193 | 39 | 15 | 322 | 0 | 27 | 592
9610 | 2018-02-08 | 2019-02-08 | 2019-10-24 | 2019-10-24 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2022-07-05 | COMP | 2022-07-22 | COMP | Rule 16 | 252 | 181 | 159 | 1 | 519 | 14 | 1121
10788 | 2018-02-08 | 2019-03-29 | 2019-06-06 | 2019-09-10 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-11-22 | COMP | 2020-02-24 | COMP | Rule 16 | 286 | 49 | 34 | 1 | 20 | 61 | 512
16990 | 2018-02-08 | 2020-01-27 | 2020-03-18 | 2020-03-18 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-12-01 | COMP | 2021-02-02 | COMP | Rule 16 | 493 | 37 | 57 | 1 | 124 | 43 | 750
17615 | 2018-02-08 | 2020-02-21 | 2020-06-26 | 2020-09-08 | COMP | 2020-11-30 | COMP | 2021-06-30 | COMP | 2021-09-07 | COMP | 2021-09-17 | COMP | Rule 16 | 511 | 90 | 57 | 148 | 48 | 9 | 909
2930 | 2018-02-09 | 2018-02-20 | 2018-06-02 | 2018-06-02 | COMP | 2018-10-31 | COMP | 2018-11-09 | COMP | 2019-02-24 | COMP | 2019-07-20 | COMP | Rule 15/16 | 7 | 73 | 106 | 8 | 69 | 103 | 363
3069 | 2018-02-09 | 2018-03-05 | 2018-09-04 | 2018-09-04 | COMP | 2018-03-05 | NOTN | 2018-09-04 | COMP | 2019-02-11 | COMP | 2019-03-08 | COMP | Other | 16 | 129 |  | 1 | 109 | 19 | 270
3099 | 2018-02-09 | 2018-03-08 | 2018-06-12 | 2018-06-12 | COMP | 2018-07-31 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-08-09 | COMP | Rule 16 | 19 | 68 | 35 | 188 | 3 | 70 | 378
3104 | 2018-02-09 | 2018-03-08 | 2019-05-24 | 2019-05-24 | COMP | 2019-11-04 | COMP | 2019-11-06 | COMP | 2019-11-12 | COMP | 2019-12-19 | COMP | Rule 15/16 | 19 | 307 | 114 | 3 | 4 | 26 | 468
3117 | 2018-02-09 | 2018-03-09 | 2018-08-21 | 2018-08-21 | COMP | 2020-08-24 | COMP | 2021-01-08 | COMP | 2021-02-22 | COMP | 2021-04-21 | COMP | Rule 15/16 | 20 | 116 | 506 | 94 | 30 | 43 | 804
3249 | 2018-02-09 | 2018-03-28 | 2018-08-17 | 2019-07-18 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-12-18 | COMP | 2020-01-06 | COMP | Rule 16 | 33 | 101 | 18 | 1 | 89 | 12 | 478
3250 | 2018-02-09 | 2018-03-28 | 2018-08-16 | 2018-08-16 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2019-03-12 | COMP | 2019-04-19 | COMP | Rule 15/16 | 33 | 100 | 50 | 1 | 92 | 29 | 300
3430 | 2018-02-09 | 2018-04-24 | 2018-08-15 | 2019-05-16 | COMP | 2019-08-01 | COMP | 2019-08-08 | COMP | 2020-05-11 | COMP | 2020-05-29 | COMP | Rule 15/16 | 52 | 80 | 54 | 6 | 190 | 14 | 579
3484 | 2018-02-09 | 2018-05-04 | 2018-05-24 | 2018-05-24 | COMP | 2018-08-20 | COMP | 2018-08-20 | COMP | 2018-09-29 | COMP | 2019-06-05 | COMP | Rule 15/16 | 60 | 15 | 61 | 1 | 29 | 170 | 332
3494 | 2018-02-09 | 2018-05-07 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-04 | COMP | 2018-10-04 | COMP | 2019-07-21 | INPR | 2019-03-08 | COMP | Rule 16 | 61 | 92 | 15 | 1 |  |  | 270
3535 | 2018-02-09 | 2018-05-12 | 2018-10-11 | 2018-10-11 | COMP | 2018-11-06 | COMP | 2018-12-27 | NOTN | 2018-11-30 | COMP | 2019-03-12 | COMP | Rule 16 | 65 | 106 | 19 |  |  |  | 272
3624 | 2018-02-09 | 2018-05-25 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-31 | COMP | 2019-07-29 | COMP | 2021-02-27 | INPR | 2019-09-26 | COMP | Rule 16 | 75 | 128 | 44 | 125 |  |  | 411
4885 | 2018-02-09 | 2018-04-09 | 2018-07-02 | 2018-07-02 | COMP | 2018-08-28 | COMP | 2018-11-13 | COMP | 2018-12-06 | COMP | 2019-01-03 | COMP | Rule 16 | 41 | 60 | 41 | 54 | 16 | 19 | 226
4921 | 2018-02-09 | 2018-04-12 | 2018-08-20 | 2018-08-20 | COMP | 2018-09-14 | NOTN | 2018-11-06 | COMP | 2018-11-20 | COMP | 2019-01-31 | COMP | Other | 44 | 91 |  | 56 | 10 | 48 | 245
5002 | 2018-02-09 | 2018-04-24 | 2018-06-18 | 2018-06-18 | COMP | 2018-10-10 | COMP | 2018-10-10 | COMP | 2020-01-13 | COMP | 2020-03-06 | COMP | Rule 15/16 | 52 | 39 | 81 | 1 | 314 | 38 | 520
6050 | 2018-02-09 | 2018-07-23 | 2018-11-10 | 2018-11-21 | COMP | 2018-11-29 | COMP | 2018-12-18 | COMP | 2018-12-19 | COMP | 2019-01-08 | COMP | Rule 16 | 114 | 79 | 5 | 14 | 2 | 13 | 229
6371 | 2018-02-09 | 2018-08-14 | 2018-09-20 | 2018-09-20 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-02-13 | COMP | 2019-03-12 | COMP | Rule 16 | 130 | 27 | 63 | 1 | 37 | 19 | 272
6569 | 2018-02-09 | 2018-08-30 | 2019-07-08 | 2019-07-08 | COMP | 2019-09-09 | COMP | 2020-07-02 | COMP | 2020-06-09 | COMP | 2020-09-21 | COMP | Rule 15/16 | 142 | 213 | 45 | 206 | 0 | 57 | 659
7423 | 2018-02-09 | 2018-10-12 | 2019-02-04 | 2019-04-13 | COMP | 2019-06-28 | COMP | 2019-08-13 | COMP | 2019-10-08 | COMP | 2019-11-08 | COMP | Rule 16 | 172 | 76 | 54 | 32 | 40 | 24 | 442
7685 | 2018-02-09 | 2018-10-25 | 2019-03-08 | 2019-03-08 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-08-09 | COMP | 2019-10-21 | COMP | Rule 16 | 181 | 90 | 76 | 1 | 34 | 51 | 428
8418 | 2018-02-09 | 2018-11-29 | 2019-02-11 | 2019-02-11 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-03-09 | COMP | 2019-05-10 | COMP | Rule 16 | 203 | 50 | 9 | 1 | 11 | 45 | 315
8766 | 2018-02-09 | 2018-12-23 | 2019-04-27 | 2019-04-27 | COMP | 2019-05-14 | COMP | 2019-12-11 | INPR | 2019-12-17 | COMP | 2020-01-02 | COMP | Rule 16 | 219 | 86 | 12 |  |  |  | 476
8808 | 2018-02-09 | 2018-12-30 | 2019-05-07 | 2019-05-07 | COMP | 2019-06-04 | COMP | 2019-08-07 | COMP | 2019-05-12 | COMP | 2020-06-03 | COMP | Rule 16 | 223 | 89 | 20 | 46 | 0 | 207 | 582
12554 | 2018-02-09 | 2019-06-12 | 2019-08-15 | 2019-08-15 | COMP | 2020-02-04 | NOTN | 2020-02-11 | COMP | 2020-02-04 | COMP | 2020-06-03 | COMP | Other | 337 | 46 |  | 122 | 0 | 80 | 582
39339 | 2018-02-09 | 2022-10-14 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-20 | NOTN | 2023-08-22 | COMP | 2023-10-07 | COMP | 2023-11-07 | COMP | Other | 1179 | 179 |  | 35 | 33 | 22 | 1445
39340 | 2018-02-09 | 2022-10-14 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-15 | NOTN | 2023-10-25 | COMP |  | INPR | 2023-11-29 | COMP | Other | 1179 | 197 |  | 62 |  |  | 1458
3280 | 2018-02-10 | 2018-03-31 | 2018-07-20 | 2018-07-20 | COMP | 2018-10-09 | COMP | 2018-12-07 | COMP | 2018-12-20 | COMP | 2019-01-31 | COMP | Rule 16 | 34 | 78 | 57 | 41 | 10 | 28 | 244
4981 | 2018-02-10 | 2018-04-19 | 2019-01-11 | 2019-01-11 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-07-23 | COMP | 2020-01-13 | COMP | Rule 16 | 48 | 184 | 14 | 1 | 121 | 119 | 482
5126 | 2018-02-11 | 2018-05-02 | 2018-08-17 | 2018-12-21 | COMP | 2019-02-26 | COMP | 2019-04-03 | COMP | 2019-03-04 | COMP | 2019-05-09 | COMP | Rule 16 | 57 | 76 | 44 | 27 | 0 | 27 | 313
2900 | 2018-02-12 | 2018-02-13 | 2018-03-12 | 2018-03-12 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP |  | INPR | 2020-11-25 | COMP | Other | 2 | 19 | 311 | 1 |  |  | 704
2909 | 2018-02-12 | 2018-02-14 | 2018-08-14 | 2018-08-14 | COMP | 2018-11-13 | COMP | 2018-11-21 | COMP | 2019-02-25 | COMP | 2019-04-05 | COMP | Rule 16 | 3 | 127 | 64 | 7 | 63 | 30 | 289
2992 | 2018-02-12 | 2018-02-26 | 2018-04-15 | 2018-04-15 | COMP | 2018-05-22 | COMP | 2018-05-10 | COMP | 2019-06-10 | COMP | 2019-06-19 | COMP | Rule 16 | 10 | 35 | 27 |  | 272 | 8 | 341
3214 | 2018-02-12 | 2018-03-22 | 2018-07-30 | 2018-07-30 | COMP | 2019-03-08 | COMP | 2019-03-11 | COMP | 2019-03-10 | COMP | 2019-04-26 | COMP | Rule 15/16 | 28 | 91 | 152 | 2 | 0 | 35 | 304
3295 | 2018-02-12 | 2018-04-03 | 2018-04-24 | 2018-04-24 | COMP | 2018-09-10 | COMP | 2018-12-06 | COMP | 2018-11-27 | COMP | 2019-03-13 | COMP | Rule 15/16 | 36 | 16 | 97 | 61 | 0 | 66 | 272
3600 | 2018-02-12 | 2018-05-23 | 2018-10-25 | 2018-10-25 | COMP | 2018-12-20 | COMP | 2019-03-11 | COMP | 2019-09-18 | COMP | 2019-10-05 | COMP | Rule 16 | 72 | 109 | 38 | 54 | 135 | 13 | 416
3601 | 2018-02-12 | 2018-05-23 | 2018-10-22 | 2018-10-22 | COMP | 2018-12-26 | COMP | 2019-01-14 | COMP | 2019-04-24 | COMP | 2019-05-11 | COMP | Rule 16 | 72 | 106 | 44 | 13 | 71 | 13 | 314
3741 | 2018-02-12 | 2018-06-26 | 2018-08-21 | 2018-08-21 | COMP | 2018-12-31 | COMP | 2019-01-08 | COMP | 2019-01-10 | COMP | 2019-03-19 | COMP | Rule 16 | 95 | 40 | 90 | 6 | 3 | 47 | 276
4096 | 2018-02-12 | 2019-01-30 | 2019-03-12 | 2019-03-12 | COMP | 2019-04-08 | COMP | 2019-05-06 | COMP | 2019-09-03 | COMP | 2019-08-30 | COMP | Rule 16 | 243 | 29 | 20 | 21 | 84 |  | 392
4621 | 2018-02-12 | 2018-02-16 | 2018-07-15 | 2018-07-15 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-07-30 | COMP | 2019-08-06 | COMP | Rule 16 | 5 | 103 | 121 | 1 | 142 | 6 | 374
4630 | 2018-02-12 | 2018-02-20 | 2018-04-29 | 2018-04-29 | COMP | 2018-05-24 | COMP | 2018-05-24 | COMP | 2018-05-29 | COMP | 2020-11-11 | COMP | Rule 16 | 6 | 49 | 19 | 1 | 3 | 620 | 694
4758 | 2018-02-12 | 2018-03-27 | 2018-06-15 | 2018-06-15 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2020-02-05 | COMP | 2020-04-14 | COMP | Rule 16 | 31 | 58 | 111 | 1 | 301 | 49 | 546
4819 | 2018-02-12 | 2018-04-01 | 2018-09-12 | 2018-09-12 | COMP | 2018-12-27 | COMP | 2019-01-03 | COMP | 2019-11-24 | INPR | 2019-07-03 | COMP | Rule 16 | 34 | 115 | 73 | 5 |  |  | 351
4915 | 2018-02-12 | 2018-04-11 | 2018-06-20 | 2018-07-11 | COMP | 2018-09-07 | COMP | 2018-10-03 | COMP | 2018-10-06 | COMP | 2019-03-20 | COMP | Rule 16 | 42 | 50 | 42 | 19 | 3 | 111 | 277
4917 | 2018-02-12 | 2018-04-11 | 2018-06-14 | 2018-06-14 | COMP | 2018-07-27 | COMP | 2018-07-27 | COMP | 2019-05-15 | COMP | 2019-07-07 | COMP | Rule 16 | 42 | 46 | 31 | 1 | 201 | 36 | 352
5007 | 2018-02-12 | 2018-04-23 | 2018-09-13 | 2018-09-13 | COMP | 2019-06-13 | COMP | 2019-06-18 | COMP | 2019-12-09 | COMP | 2020-01-27 | COMP | Rule 16 | 50 | 101 | 188 | 4 | 120 | 33 | 491
5061 | 2018-02-12 | 2018-04-27 | 2018-10-12 | 2018-10-12 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-08-30 | COMP | 2019-12-03 | COMP | Rule 15/16 | 54 | 118 | 89 | 1 | 134 | 64 | 455
5123 | 2018-02-12 | 2018-05-02 | 2018-09-08 | 2018-09-08 | COMP | 2018-11-06 | COMP | 2020-03-25 | COMP | 2020-04-14 | COMP | 2020-05-13 | COMP | Rule 16 | 57 | 90 | 42 | 345 | 15 | 22 | 567
5143 | 2018-02-12 | 2018-05-03 | 2018-12-10 | 2018-12-10 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-06-27 | COMP | 2019-08-06 | COMP | Rule 15/16 | 58 | 152 | 60 | 1 | 80 | 28 | 374
5561 | 2018-02-12 | 2018-06-14 | 2018-11-04 | 2018-11-04 | COMP | 2019-01-09 | COMP | 2019-04-24 | COMP | 2019-04-30 | COMP | 2019-07-05 | COMP | Rule 16 | 87 | 100 | 43 | 74 | 5 | 47 | 352
7442 | 2018-02-12 | 2018-10-12 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-06-19 | COMP | 2019-07-08 | COMP | Rule 15/16 | 171 | 25 | 26 | 1 | 121 | 13 | 353
7507 | 2018-02-12 | 2018-10-18 | 2019-01-02 | 2019-01-04 | COMP | 2019-01-04 | NOTN | 2019-04-02 | COMP | 2019-09-18 | COMP | 2019-10-18 | COMP | Other | 175 | 50 |  | 61 | 119 | 23 | 426
8303 | 2018-02-12 | 2018-11-26 | 2019-01-16 | 2020-07-31 | COMP | 2020-08-11 | COMP | 2019-01-22 | COMP | 2020-10-08 | COMP | 2020-11-16 | COMP | Rule 16 | 199 | 36 | 8 |  | 435 | 27 | 697
2981 | 2018-02-13 | 2018-02-26 | 2018-06-15 | 2018-09-21 | COMP | 2018-11-06 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-03-21 | COMP | Rule 16 | 9 | 79 | 33 | 45 | 1 | 47 | 277
2989 | 2018-02-13 | 2018-02-26 | 2018-08-02 | 2018-08-02 | COMP | 2018-08-17 | COMP | 2018-09-07 | COMP | 2019-01-22 | COMP | 2019-02-20 | COMP | Rule 16 | 9 | 112 | 12 | 15 | 92 | 21 | 256
2990 | 2018-02-13 | 2018-02-26 | 2018-06-26 | 2018-06-26 | COMP | 2018-07-06 | COMP | 2018-07-11 | COMP | 2019-04-20 | INPR | 2019-01-04 | COMP | Rule 16 | 9 | 86 | 8 | 4 |  |  | 225
3282 | 2018-02-13 | 2018-03-31 | 2018-10-18 | 2018-10-18 | COMP | 2018-11-06 | COMP | 2019-01-16 | COMP | 2019-05-06 | COMP | 2019-05-21 | COMP | Rule 15/16 | 33 | 141 | 14 | 47 | 77 | 12 | 320
3356 | 2018-02-13 | 2018-04-11 | 2020-06-04 | 2020-06-04 | COMP | 2019-11-19 | NOTN | 2020-07-24 | COMP | 2022-07-13 | COMP | 2022-12-28 | COMP | Other | 41 | 541 |  | 37 | 495 | 116 | 1226
3454 | 2018-02-13 | 2018-04-30 | 2018-10-08 | 2018-10-08 | COMP | 2018-10-18 | COMP | 2018-10-30 | COMP | 2019-02-20 | COMP | 2019-04-26 | COMP | Rule 16 | 54 | 113 | 9 | 9 | 75 | 48 | 303
3583 | 2018-02-13 | 2018-05-21 | 2018-06-21 | 2018-06-21 | COMP | 2018-09-12 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-21 | COMP | Other | 69 | 23 | 58 | 161 | 1 | 13 | 320
3584 | 2018-02-13 | 2018-05-21 | 2018-06-21 | 2018-06-21 | COMP | 2018-09-12 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-17 | COMP | Other | 69 | 23 | 58 | 161 | 1 | 11 | 318
3871 | 2018-02-13 | 2018-08-30 | 2018-10-05 | 2018-10-05 | COMP | 2019-03-19 | COMP | 2019-03-26 | COMP | 2019-04-09 | COMP | 2019-07-12 | COMP | Rule 15/16 | 140 | 26 | 111 | 6 | 11 | 67 | 356
3993 | 2018-02-13 | 2018-11-10 | 2019-01-08 | 2019-01-08 | COMP | 2019-03-04 | COMP | 2019-11-18 | COMP |  |  | 2019-12-10 | COMP | Rule 16 | 190 | 37 | 38 | 182 |  |  | 459
4063 | 2018-02-13 | 2019-01-04 | 2019-03-06 | 2019-03-06 | COMP | 2019-11-07 | COMP | 2019-12-03 | COMP | 2020-04-13 | COMP | 2020-05-11 | COMP | Rule 16 | 225 | 42 | 174 | 16 | 91 | 21 | 564
4646 | 2018-02-13 | 2018-02-26 | 2018-09-04 | 2018-09-04 | COMP | 2018-11-21 | COMP | 2018-12-10 | COMP | 2018-12-12 | COMP | 2019-01-22 | COMP | Rule 16 | 9 | 134 | 56 | 12 | 3 | 27 | 236
4900 | 2018-02-13 | 2018-04-12 | 2018-07-27 | 2018-07-30 | COMP | 2018-12-07 | COMP | 2019-02-21 | COMP | 2019-11-06 | COMP | 2020-01-14 | COMP | Rule 16 | 42 | 75 | 91 | 51 | 182 | 45 | 482
5137 | 2018-02-13 | 2018-05-03 | 2018-12-15 | 2018-12-15 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-07 | COMP | 2019-09-10 | COMP | Rule 16 | 57 | 156 | 72 | 1 | 5 | 109 | 397
5202 | 2018-02-13 | 2018-05-10 | 2018-10-16 | 2018-10-16 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-04-16 | COMP | 2019-04-24 | COMP | Rule 16 | 62 | 111 | 97 | 1 | 28 | 7 | 301
6654 | 2018-02-13 | 2018-09-08 | 2019-01-24 | 2019-03-20 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-08-09 | COMP | 2019-08-12 | COMP | Rule 16 | 145 | 93 | 28 | 1 | 74 | 2 | 377
6698 | 2018-02-13 | 2018-09-07 | 2018-11-16 | 2018-11-16 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-08-15 | COMP | 2020-02-06 | COMP | Rule 16 | 145 | 50 | 151 | 1 | 37 | 119 | 498
6759 | 2018-02-13 | 2018-09-11 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-14 | COMP | 2019-01-17 | COMP | 2019-02-13 | COMP | 2019-02-25 | COMP | Rule 15/16 | 147 | 55 | 31 | 4 | 19 | 8 | 259
6806 | 2018-02-13 | 2018-09-11 | 2018-11-13 | 2018-11-16 | COMP | 2018-11-28 | COMP | 2019-01-03 | COMP | 2018-11-28 | COMP | 2019-02-10 | COMP | Rule 16 | 147 | 45 | 7 | 25 | 0 | 26 | 249
7885 | 2018-02-13 | 2018-11-03 | 2018-12-13 | 2018-12-13 | COMP | 2019-01-16 | COMP | 2019-02-27 | COMP | 2019-05-30 | COMP | 2019-05-31 | COMP | Rule 16 | 185 | 26 | 23 | 29 | 66 | 2 | 327
8483 | 2018-02-13 | 2018-12-04 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-25 | COMP | 2019-01-31 | COMP | 2019-01-30 | COMP | 2019-02-24 | COMP | Rule 15/16 | 204 | 25 | 12 | 5 | 0 | 16 | 258
9063 | 2018-02-13 | 2019-01-15 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-06-06 | COMP | 2019-07-08 | COMP | Rule 15/16 | 232 | 30 | 10 | 1 | 62 | 22 | 352
10008 | 2018-02-13 | 2019-02-26 | 2019-07-25 | 2019-07-25 | COMP | 2019-11-22 | COMP | 2020-05-28 | COMP |  | INPR | 2020-06-16 | COMP | Rule 16 | 260 | 106 | 85 | 128 |  |  | 589
19481 | 2018-02-13 | 2020-05-08 | 2020-07-30 | 2020-07-30 | COMP | 2020-08-13 | COMP | 2020-09-15 | COMP | 2020-12-01 | COMP | 2021-02-01 | COMP | Rule 16 | 563 | 59 | 11 | 23 | 53 | 42 | 746
2917 | 2018-02-14 | 2018-02-17 | 2018-05-20 | 2018-05-20 | COMP | 2018-08-21 | COMP | 2019-02-19 | COMP | 2018-12-19 | COMP | 2019-04-26 | COMP | Rule 15/16 | 3 | 64 | 65 | 123 | 0 | 49 | 302
2996 | 2018-02-14 | 2018-02-26 | 2018-03-21 | 2019-07-24 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-01-07 | COMP | 2020-01-30 | COMP | Rule 16 | 8 | 18 | 97 | 1 | 18 | 17 | 492
3070 | 2018-02-14 | 2018-03-05 | 2018-08-20 | 2018-08-20 | COMP | 2018-03-05 | NOTN | 2018-08-20 | COMP | 2019-01-28 | COMP | 2019-02-25 | COMP | Other | 13 | 119 |  | 1 | 109 | 20 | 258
3238 | 2018-02-14 | 2018-03-26 | 2018-11-19 | 2018-11-19 | COMP | 2018-12-12 | COMP | 2019-01-09 | COMP | 2019-01-10 | COMP | 2019-03-16 | COMP | Rule 15/16 | 28 | 167 | 16 | 19 | 2 | 45 | 272
3243 | 2018-02-14 | 2018-03-28 | 2018-08-02 | 2018-08-02 | COMP | 2018-09-18 | COMP | 2018-09-18 | COMP | 2019-04-20 | INPR | 2019-01-28 | COMP | Rule 16 | 30 | 90 | 33 | 1 |  |  | 239
4909 | 2018-02-14 | 2018-04-11 | 2018-06-13 | 2018-06-26 | COMP | 2018-08-23 | COMP | 2018-09-18 | COMP | 2018-09-25 | COMP | 2019-04-23 | COMP | Rule 15/16 | 40 | 45 | 42 | 18 | 6 | 144 | 299
5032 | 2018-02-14 | 2018-04-24 | 2019-11-22 | 2021-06-30 | COMP | 2022-02-28 | COMP | 2022-02-28 | COMP |  | INPR | 2022-04-08 | COMP | Rule 15/16 | 49 | 400 | 167 | 1 |  |  | 1045
5075 | 2018-02-14 | 2018-04-27 | 2020-02-06 | 2021-06-29 | COMP | 2021-11-05 | COMP | 2022-03-01 | COMP | 2022-03-01 | COMP | 2022-04-07 | COMP | Rule 15/16 | 52 | 446 | 92 | 78 | 1 | 28 | 1044
5195 | 2018-02-14 | 2018-05-09 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2019-01-03 | COMP | 2019-03-28 | COMP | Rule 16 | 60 | 95 | 24 | 1 | 47 | 59 | 281
6282 | 2018-02-14 | 2018-08-08 | 2019-03-14 | 2019-03-14 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-12-03 | COMP | 2020-01-30 | COMP | Rule 16 | 123 | 149 | 26 | 1 | 158 | 40 | 492
7196 | 2018-02-14 | 2018-10-02 | 2018-12-10 | 2018-12-10 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-06-20 | COMP | 2019-06-28 | COMP | Rule 16 | 161 | 47 | 133 | 1 | 2 | 7 | 346
13752 | 2018-02-14 | 2019-08-08 | 2019-09-16 | 2020-05-19 | COMP | 2021-07-15 | COMP | 2021-10-26 | COMP | 2021-10-08 | COMP | 2021-12-03 | COMP | Other | 374 | 27 | 292 | 73 | 0 | 26 | 957
2978 | 2018-02-15 | 2018-02-24 | 2018-12-21 | 2021-09-10 | COMP | 2021-09-20 | COMP | 2023-01-27 | COMP | 2023-01-05 | COMP | 2023-03-27 | COMP | Rule 15/16 | 6 | 209 | 7 | 340 | 0 | 41 | 1284
2982 | 2018-02-15 | 2018-03-02 | 2018-03-29 | 2018-03-29 | COMP | 2018-06-06 | COMP | 2020-03-17 | COMP | 2020-02-12 | COMP | 2020-04-14 | COMP | Rule 15/16 | 11 | 20 | 49 | 446 | 0 | 21 | 543
3032 | 2018-02-15 | 2018-02-28 | 2018-05-14 | 2018-05-14 | COMP | 2018-09-10 | COMP | 2018-10-04 | COMP | 2019-07-09 | COMP | 2019-08-24 | COMP | Rule 15/16 | 9 | 54 | 83 | 19 | 190 | 34 | 384
3092 | 2018-02-15 | 2018-03-07 | 2018-03-22 | 2018-03-22 | COMP | 2018-04-05 | COMP | 2018-05-24 | COMP | 2018-06-12 | COMP | 2021-04-18 | COMP | Rule 16 | 14 | 12 | 11 | 36 | 13 | 716 | 797
3135 | 2018-02-15 | 2018-03-12 | 2019-08-16 | 2019-08-16 | COMP | 2018-09-21 | COMP | 2019-09-23 | COMP | 2019-08-14 | COMP | 2020-02-07 | COMP | Rule 16 | 17 | 363 |  | 252 | 0 | 94 | 497
3852 | 2018-02-15 | 2018-08-16 | 2019-02-08 | 2019-02-08 | COMP | 2019-02-20 | COMP | 2019-03-19 | COMP | 2019-03-13 | COMP | 2019-04-04 | COMP | Rule 16 | 128 | 120 | 8 | 20 | 0 | 13 | 285
4624 | 2018-02-15 | 2018-02-16 | 2018-04-27 | 2018-04-27 | COMP | 2018-12-03 | COMP | 2019-01-14 | COMP | 2018-10-29 | COMP | 2019-04-05 | COMP | Rule 16 | 2 | 50 | 151 | 29 | 0 | 58 | 286
4784 | 2018-02-15 | 2018-03-30 | 2018-08-23 | 2018-08-23 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2019-01-28 | COMP | 2019-02-27 | COMP | Rule 16 | 31 | 103 | 58 | 1 | 49 | 22 | 259
4823 | 2018-02-15 | 2018-04-04 | 2018-12-13 | 2019-01-31 | COMP | 2019-03-08 | COMP | 2019-03-11 | COMP | 2019-11-26 | COMP | 2020-01-02 | COMP | Rule 16 | 34 | 176 | 26 | 2 | 183 | 24 | 472
4893 | 2018-02-15 | 2018-04-10 | 2019-01-15 | 2019-01-15 | COMP | 2019-01-15 | NOTN | 2019-01-23 | COMP | 2019-01-15 | COMP | 2019-04-10 | COMP | Other | 38 | 193 |  | 6 | 0 | 55 | 289
4944 | 2018-02-15 | 2018-04-13 | 2018-08-01 | 2018-08-01 | COMP | 2018-10-01 | COMP | 2019-03-14 | COMP | 2018-09-28 | COMP | 2019-06-01 | COMP | Rule 16 | 41 | 77 | 43 | 112 | 0 | 56 | 325
5122 | 2018-02-15 | 2018-05-02 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-01-11 | COMP | 2019-01-23 | COMP | Rule 16 | 54 | 150 | 4 | 1 | 23 | 8 | 235
5144 | 2018-02-15 | 2018-05-03 | 2018-08-14 | 2019-01-28 | COMP | 2019-03-14 | COMP | 2019-07-29 | COMP | 2019-08-05 | COMP | 2019-09-04 | COMP | Rule 16 | 55 | 72 | 33 | 96 | 6 | 22 | 391
6595 | 2018-02-15 | 2018-08-29 | 2019-07-17 | 2020-02-11 | COMP | 2020-03-18 | COMP | 2020-05-13 | COMP | 2020-07-28 | COMP | 2020-09-28 | COMP | Rule 15/16 | 137 | 221 | 26 | 41 | 54 | 44 | 660
7433 | 2018-02-15 | 2018-10-12 | 2018-11-08 | 2018-11-08 | COMP | 2018-11-20 | COMP | 2018-12-03 | COMP | 2018-12-20 | COMP | 2019-01-28 | COMP | Rule 16 | 168 | 20 | 8 | 8 | 14 | 25 | 238
26003 | 2018-02-15 | 2021-03-04 | 2021-07-23 | 2021-07-23 | COMP | 2022-02-24 | COMP | 2023-01-05 | COMP | 2023-04-07 | COMP | 2023-04-14 | COMP | Rule 15/16 | 766 | 100 | 149 | 217 | 65 | 6 | 1298
3114 | 2018-02-16 | 2018-03-09 | 2018-09-25 | 2019-12-20 | COMP | 2020-03-27 | COMP | 2019-02-05 | COMP | 2019-04-11 | COMP | 2020-10-23 | COMP | Rule 15/16 | 15 | 140 | 67 |  | 47 | 390 | 678
3764 | 2018-02-16 | 2018-07-04 | 2018-10-15 | 2018-10-15 | COMP | 2018-12-12 | COMP | 2018-12-17 | COMP | 2018-12-13 | COMP | 2019-01-23 | COMP | Rule 15/16 | 96 | 72 | 40 | 4 | 0 | 25 | 234
3777 | 2018-02-16 | 2018-07-09 | 2018-09-18 | 2018-09-18 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2020-02-21 | COMP | 2020-05-23 | COMP | Rule 16 | 99 | 51 | 84 | 1 | 274 | 66 | 570
3872 | 2018-02-16 | 2018-08-30 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-13 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-01-07 | COMP | Rule 15/16 | 137 | 43 | 10 | 9 | 1 | 28 | 223
3892 | 2018-02-16 | 2018-09-19 | 2019-01-07 | 2019-01-07 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-01-22 | COMP | 2019-04-19 | COMP | Rule 16 | 150 | 74 | 32 | 1 | 0 | 42 | 295
4692 | 2018-02-16 | 2018-03-14 | 2018-06-21 | 2018-06-21 | COMP | 2018-07-23 | COMP | 2018-07-23 | COMP | 2019-01-19 | COMP | 2019-01-24 | COMP | Rule 16 | 18 | 71 | 22 | 1 | 124 | 3 | 235
4750 | 2018-02-16 | 2018-03-26 | 2019-05-24 | 2019-05-24 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-10-19 | COMP | 2020-12-16 | COMP | Rule 16 | 26 | 295 | 104 | 1 | 252 | 40 | 713
4814 | 2018-02-16 | 2018-03-31 | 2018-09-05 | 2018-09-05 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-04-24 | COMP | 2019-06-12 | COMP | Rule 16 | 30 | 110 | 154 | 1 | 6 | 35 | 332
4830 | 2018-02-16 | 2018-04-04 | 2018-08-16 | 2018-08-16 | COMP | 2018-09-12 | COMP | 2018-12-14 | COMP | 2019-10-21 | INPR | 2019-05-09 | COMP | Rule 16 | 33 | 95 | 19 | 65 |  |  | 309
4842 | 2018-02-16 | 2018-04-04 | 2018-07-25 | 2018-07-25 | COMP | 2018-08-21 | COMP | 2018-08-21 | COMP | 2019-07-21 | REQD | 2019-03-20 | COMP | Rule 16 | 33 | 79 | 20 | 1 |  |  | 273
4911 | 2018-02-16 | 2018-04-10 | 2019-01-28 | 2019-01-28 | COMP | 2019-01-28 | NOTN | 2019-02-13 | COMP | 2019-01-28 | COMP | 2019-04-22 | COMP | Other | 37 | 201 |  | 13 | 0 | 48 | 296
4960 | 2018-02-16 | 2018-04-16 | 2019-01-15 | 2021-06-17 | COMP | 2021-06-24 | COMP | 2019-11-25 | COMP | 2021-10-27 | COMP | 2021-10-19 | COMP | Rule 16 | 41 | 189 | 6 |  | 485 |  | 925
5252 | 2018-02-16 | 2018-05-14 | 2018-09-26 | 2018-09-26 | COMP | 2019-05-15 | COMP | 2019-08-19 | COMP | 2019-12-30 | COMP | 2020-02-05 | COMP | Rule 16 | 61 | 95 | 159 | 67 | 91 | 26 | 494
5264 | 2018-02-16 | 2018-05-15 | 2018-07-28 | 2018-07-28 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-04-21 | INPR | 2019-01-25 | COMP | Rule 16 | 62 | 52 | 81 | 1 |  |  | 236
5390 | 2018-02-16 | 2018-05-29 | 2019-02-21 | 2019-04-04 | COMP | 2019-05-17 | COMP | 2019-06-03 | COMP | 2019-06-06 | COMP | 2019-08-23 | COMP | Rule 16 | 71 | 184 | 32 | 11 | 4 | 56 | 383
5529 | 2018-02-16 | 2018-06-11 | 2018-10-04 | 2018-10-04 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-05-01 | COMP | Rule 16 | 80 | 82 | 92 | 1 | 1 | 52 | 303
5613 | 2018-02-16 | 2018-06-20 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-04 | COMP | 2019-04-05 | COMP | 2019-10-21 | INPR | 2019-04-16 | COMP | Rule 16 | 87 | 171 | 5 | 25 |  |  | 292
5641 | 2018-02-16 | 2018-06-22 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-10-15 | COMP | 2019-12-12 | COMP | Rule 16 | 89 | 144 | 48 | 1 | 141 | 40 | 458
5897 | 2018-02-16 | 2018-07-10 | 2018-11-02 | 2018-11-02 | COMP | 2018-12-28 | COMP | 2019-05-24 | COMP | 2019-06-06 | COMP | 2019-06-17 | COMP | Rule 15/16 | 100 | 83 | 37 | 103 | 9 | 8 | 335
6279 | 2018-02-16 | 2018-08-08 | 2018-12-07 | 2018-12-07 | COMP | 2019-01-11 | COMP | 2019-01-16 | COMP | 2019-01-22 | COMP | 2019-02-28 | COMP | Rule 15/16 | 121 | 84 | 24 | 4 | 4 | 27 | 259
6291 | 2018-02-16 | 2018-08-09 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-31 | COMP | 2019-04-02 | COMP | 2019-02-26 | COMP | 2019-05-07 | COMP | Rule 16 | 122 | 86 | 13 | 64 | 0 | 26 | 307
6414 | 2018-02-16 | 2018-08-16 | 2018-11-21 | 2018-11-21 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-02-06 | COMP | 2019-03-14 | COMP | Rule 15/16 | 127 | 68 | 35 | 1 | 17 | 26 | 269
6022 | 2018-02-17 | 2018-07-20 | 2018-10-22 | 2018-10-22 | COMP | 2019-02-15 | COMP | 2018-11-28 | COMP | 2019-02-20 | COMP | 2019-03-29 | COMP | Rule 16 | 107 | 66 | 79 |  | 57 | 28 | 279
6412 | 2018-02-17 | 2018-08-16 | 2018-10-24 | 2019-01-16 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-02-05 | COMP | 2019-03-13 | COMP | Rule 16 | 126 | 49 | 12 | 1 | 3 | 26 | 267
5922 | 2018-02-18 | 2018-07-11 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-02 | COMP | 2019-02-05 | COMP | 2019-01-11 | COMP | 2019-03-21 | COMP | Rule 16 | 100 | 72 | 11 | 62 | 0 | 32 | 273
3342 | 2018-02-19 | 2018-04-10 | 2018-04-25 | 2018-04-25 | COMP | 2018-06-07 | COMP | 2018-06-19 | COMP | 2018-12-04 | COMP | 2019-04-22 | COMP | Rule 16 | 36 | 12 | 31 | 9 | 116 | 96 | 295
4106 | 2018-02-19 | 2019-02-06 | 2019-06-13 | 2019-06-13 | COMP | 2020-01-28 | COMP | 2020-02-03 | COMP | 2020-05-05 | COMP | 2020-10-12 | COMP | Rule 16 | 243 | 90 | 156 | 5 | 66 | 113 | 668
4697 | 2018-02-19 | 2018-03-14 | 2018-05-07 | 2018-05-07 | COMP | 2018-05-22 | COMP | 2018-05-22 | COMP | 2018-06-21 | COMP | 2020-02-24 | COMP | Rule 16 | 17 | 39 | 12 | 1 | 22 | 419 | 505
5213 | 2018-02-19 | 2018-05-10 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-15 | COMP | 2018-12-12 | COMP | 2019-01-14 | COMP | 2019-04-06 | COMP | Other | 58 | 122 | 11 | 18 | 22 | 58 | 284
5265 | 2018-02-19 | 2018-05-16 | 2018-05-16 | 2018-08-18 | COMP | 2018-09-04 | COMP | 2018-06-26 | COMP | 2019-09-17 | COMP | 2019-10-15 | COMP | Rule 16 | 62 | 1 | 11 |  | 309 | 21 | 418
6464 | 2018-02-19 | 2018-08-21 | 2018-10-30 | 2018-10-30 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2018-11-29 | COMP | 2019-01-12 | COMP | Rule 16 | 129 | 50 | 25 | 1 | 0 | 25 | 226
9596 | 2018-02-19 | 2019-02-07 | 2019-06-09 | 2019-06-09 | COMP | 2019-06-18 | COMP | 2019-10-10 | COMP | 2020-02-29 | INPR | 2019-10-23 | COMP | Rule 16 | 244 | 85 | 7 | 81 |  |  | 424
10025 | 2018-02-19 | 2019-02-27 | 2019-05-03 | 2019-05-03 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2020-07-07 | COMP | 2020-09-17 | COMP | Rule 16 | 257 | 48 | 71 | 1 | 227 | 52 | 651
3210 | 2018-02-20 | 2018-03-22 | 2018-06-07 | 2018-07-09 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2018-12-07 | COMP | 2019-01-02 | COMP | Rule 15/16 | 23 | 55 | 85 | 1 | 22 | 17 | 219
3229 | 2018-02-20 | 2018-03-26 | 2018-05-21 | 2018-05-21 | COMP | 2018-08-02 | COMP | 2018-09-22 | COMP | 2020-05-19 | COMP | 2020-06-15 | COMP | Rule 16 | 25 | 41 | 52 | 36 | 415 | 19 | 584
3259 | 2018-02-20 | 2018-03-28 | 2018-07-24 | 2018-07-24 | COMP | 2018-08-24 | COMP | 2018-09-17 | COMP | 2020-03-28 | INPR | 2019-06-05 | COMP | Rule 16 | 27 | 83 | 24 | 16 |  |  | 326
3311 | 2018-02-20 | 2018-04-05 | 2018-06-16 | 2018-06-16 | COMP | 2018-07-09 | COMP | 2018-07-10 | COMP | 2018-11-07 | COMP | 2019-01-21 | COMP | Rule 15/16 | 33 | 51 | 15 | 2 | 86 | 48 | 231
3322 | 2018-02-20 | 2018-04-09 | 2018-07-20 | 2018-07-20 | COMP | 2018-12-27 | COMP | 2019-08-27 | COMP | 2019-07-15 | COMP | 2019-09-18 | COMP | Rule 15/16 | 35 | 73 | 110 | 169 | 0 | 16 | 399
3345 | 2018-02-20 | 2018-04-10 | 2018-05-23 | 2018-05-23 | COMP | 2018-06-18 | COMP | 2018-06-19 | COMP | 2019-01-22 | COMP | 2019-04-30 | COMP | Rule 15/16 | 36 | 32 | 18 | 2 | 148 | 70 | 301
3645 | 2018-02-20 | 2018-06-01 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-06 | COMP | 2019-10-03 | COMP |  | INPR | 2021-05-07 | COMP | Rule 15/16 | 73 | 227 | 7 | 106 |  |  | 810
4671 | 2018-02-20 | 2018-03-07 | 2018-05-29 | 2018-05-29 | COMP | 2019-01-10 | COMP | 2019-02-19 | COMP | 2019-07-21 | INPR | 2019-03-19 | COMP | Rule 16 | 12 | 59 | 156 | 27 |  |  | 271
4691 | 2018-02-20 | 2018-03-14 | 2018-09-13 | 2018-09-13 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2020-06-03 | COMP | 2020-07-25 | COMP | Rule 16 | 17 | 129 | 38 | 1 | 395 | 38 | 613
4897 | 2018-02-20 | 2018-04-13 | 2018-09-24 | 2019-01-09 | COMP | 2019-01-25 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-04-11 | COMP | Rule 16 | 39 | 114 | 12 | 41 | 1 | 14 | 288
5029 | 2018-02-20 | 2018-04-24 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-02 | COMP | 2018-12-26 | COMP | 2019-01-09 | COMP | 2019-01-29 | COMP | Rule 16 | 46 | 119 | 18 | 35 | 10 | 14 | 237
5104 | 2018-02-20 | 2018-04-30 | 2019-01-03 | 2019-01-03 | COMP | 2020-01-27 | COMP | 2020-06-08 | INPR | 2020-05-15 | COMP | 2020-05-20 | COMP | Rule 15/16 | 50 | 171 | 267 |  |  |  | 567
5295 | 2018-02-20 | 2018-05-18 | 2018-07-02 | 2018-08-29 | COMP | 2018-09-04 | COMP | 2018-10-08 | COMP | 2019-01-25 | COMP | 2019-03-30 | COMP | Rule 16 | 64 | 31 | 4 | 25 | 74 | 45 | 279
5614 | 2018-02-20 | 2018-06-21 | 2018-08-06 | 2018-09-17 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-01-16 | COMP | 2019-04-09 | COMP | Rule 16 | 87 | 32 | 54 | 1 | 30 | 58 | 286
5652 | 2018-02-20 | 2018-06-24 | 2018-09-27 | 2019-02-25 | COMP | 2019-02-25 | NOTN | 2019-02-25 | COMP | 2019-03-12 | COMP | 2019-03-31 | COMP | Other | 88 | 67 |  | 1 | 12 | 14 | 279
5845 | 2018-02-20 | 2018-07-07 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-16 | COMP | 2020-03-20 | COMP | 2022-08-21 | INPR | 2020-05-19 | COMP | Rule 16 | 97 | 79 | 14 | 335 |  |  | 566
5943 | 2018-02-20 | 2018-07-12 | 2018-11-30 | 2019-05-08 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP |  | INPR | 2020-01-24 | COMP | Other | 101 | 98 | 44 | 1 |  |  | 485
6214 | 2018-02-20 | 2018-08-03 | 2019-02-22 | 2019-02-22 | COMP | 2021-08-26 | NOTN | 2021-09-14 | COMP | 2021-11-05 | COMP | 2021-11-08 | COMP | Other | 117 | 138 |  | 646 | 39 | 2 | 938
6687 | 2018-02-20 | 2018-09-06 | 2019-03-11 | 2019-03-11 | COMP | 2019-04-22 | COMP | 2019-07-16 | COMP | 2020-03-10 | COMP | 2020-07-15 | COMP | Rule 15/16 | 140 | 126 | 31 | 60 | 163 | 91 | 606
6732 | 2018-02-20 | 2018-09-10 | 2018-10-25 | 2018-10-25 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2020-06-13 | COMP | 2020-07-11 | COMP | Rule 16 | 142 | 34 | 38 | 1 | 372 | 20 | 603
7191 | 2018-02-20 | 2018-10-02 | 2019-01-25 | 2019-01-25 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-06-14 | COMP | 2019-06-26 | COMP | Rule 16 | 158 | 78 | 74 | 1 | 26 | 9 | 341
9767 | 2018-02-20 | 2019-02-14 | 2019-08-27 | 2019-08-27 | COMP | 2019-10-15 | COMP | 2021-01-25 | COMP | 2022-11-28 | COMP | 2023-04-11 | COMP | Rule 15/16 | 249 | 136 | 35 | 320 | 465 | 93 | 1293
11408 | 2018-02-20 | 2019-04-25 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-07 | COMP | 2019-12-02 | COMP | 2019-12-17 | COMP | 2020-01-22 | COMP | Rule 16 | 298 | 120 | 19 | 15 | 12 | 24 | 483
3177 | 2018-02-21 | 2018-03-19 | 2018-09-06 | 2018-09-06 | COMP | 2019-06-14 | COMP | 2019-12-12 | COMP | 2019-10-29 | COMP | 2020-01-31 | COMP | Rule 15/16 | 19 | 121 | 194 | 125 | 0 | 34 | 489
3188 | 2018-02-21 | 2018-03-20 | 2018-07-30 | 2018-07-30 | COMP | 2018-09-05 | COMP | 2018-09-05 | COMP | 2020-01-09 | COMP | 2020-02-20 | COMP | Rule 16 | 20 | 93 | 27 | 1 | 337 | 29 | 502
3205 | 2018-02-21 | 2018-03-22 | 2018-08-13 | 2018-08-13 | COMP | 2019-02-14 | COMP | 2019-05-23 | COMP | 2023-04-29 | INPR | 2019-07-26 | COMP | Rule 15/16 | 22 | 101 | 127 | 70 |  |  | 361
3294 | 2018-02-21 | 2018-04-03 | 2018-10-30 | 2019-09-20 | COMP | 2019-10-31 | COMP | 2019-11-01 | COMP | 2019-10-31 | COMP | 2020-01-10 | COMP | Rule 16 | 30 | 148 | 30 | 2 | 0 | 46 | 475
3503 | 2018-02-21 | 2018-05-09 | 2019-01-04 | 2019-01-04 | COMP | 2019-02-11 | COMP | 2019-04-03 | COMP | 2019-04-20 | COMP | 2019-05-15 | COMP | Rule 15/16 | 56 | 165 | 26 | 37 | 13 | 18 | 311
3578 | 2018-02-21 | 2018-05-17 | 2019-01-17 | 2019-01-17 | COMP | 2021-07-28 | COMP | 2021-08-09 | COMP | 2021-07-27 | COMP | 2021-09-13 | COMP | Rule 16 | 62 | 168 | 637 | 9 | 0 | 25 | 897
3596 | 2018-02-21 | 2018-05-23 | 2019-01-19 | 2019-01-19 | COMP | 2019-10-21 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-03-23 | COMP | Rule 15/16 | 66 | 165 | 191 | 31 | 1 | 74 | 524
3615 | 2018-02-21 | 2018-05-24 | 2019-02-25 | 2019-02-25 | COMP | 2019-02-25 | NOTN | 2019-05-29 | COMP | 2020-02-18 | COMP | 2020-12-05 | COMP | Other | 67 | 188 |  | 67 | 181 | 204 | 703
3819 | 2018-02-21 | 2018-07-30 | 2019-04-17 | 2019-04-17 | COMP | 2020-03-23 | NOTN | 2020-11-12 | COMP | 2018-11-13 | COMP | 2021-01-08 | COMP | Other | 112 | 180 |  | 399 | 0 | 38 | 726
4023 | 2018-02-21 | 2018-12-06 | 2018-12-27 | 2018-12-27 | COMP | 2018-12-27 | NOTN | 2019-04-19 | COMP | 2018-05-25 | COMP | 2019-10-10 | COMP | Other | 201 | 15 |  | 79 | 0 | 122 | 414
4176 | 2018-02-21 | 2019-05-28 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-23 | NOTN | 2019-09-23 | COMP | 2019-09-24 | COMP | 2019-11-07 | COMP | Rule 16 | 319 | 52 |  | 32 | 2 | 33 | 434
4665 | 2018-02-21 | 2018-03-06 | 2018-05-18 | 2018-05-18 | COMP | 2019-02-07 | COMP | 2019-08-01 | COMP | 2019-10-09 | COMP | 2020-03-02 | COMP | Rule 16 | 10 | 54 | 181 | 123 | 49 | 97 | 509
4695 | 2018-02-21 | 2018-03-16 | 2018-08-24 | 2018-08-24 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2019-02-06 | COMP | 2019-02-07 | COMP | Rule 16 | 18 | 114 | 88 | 1 | 25 | 2 | 243
4747 | 2018-02-21 | 2018-03-26 | 2019-05-15 | 2019-05-15 | COMP | 2019-08-16 | COMP | 2020-02-11 | COMP | 2020-10-26 | COMP | 2020-12-10 | COMP | Rule 15/16 | 24 | 288 | 66 | 121 | 182 | 31 | 707
5043 | 2018-02-21 | 2018-04-26 | 2018-08-07 | 2018-08-07 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2019-01-25 | COMP | 2019-07-06 | COMP | Rule 16 | 47 | 72 | 101 | 1 | 17 | 113 | 346
5052 | 2018-02-21 | 2018-04-26 | 2018-08-22 | 2018-08-22 | COMP | 2018-10-16 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2019-09-11 | COMP | Rule 16 | 47 | 83 | 39 | 14 | 1 | 214 | 393
5082 | 2018-02-21 | 2018-04-30 | 2018-06-25 | 2018-10-30 | COMP | 2018-11-27 | COMP | 2019-03-15 | COMP | 2019-02-14 | COMP | 2019-04-22 | COMP | Rule 16 | 49 | 40 | 18 | 75 | 0 | 27 | 294
5169 | 2018-02-21 | 2018-05-07 | 2018-10-01 | 2018-10-01 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-10-14 | COMP | 2019-11-11 | COMP | Rule 16 | 54 | 103 | 186 | 1 | 76 | 20 | 435
5346 | 2018-02-21 | 2018-05-23 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-04-16 | COMP | 2019-05-16 | COMP | Rule 16 | 66 | 185 | 19 | 1 | 23 | 23 | 312
5626 | 2018-02-21 | 2018-06-21 | 2018-11-02 | 2018-11-02 | COMP | 2019-05-30 | COMP | 2019-07-25 | COMP | 2019-12-28 | INPR | 2019-09-05 | COMP | Rule 16 | 86 | 95 | 142 | 40 |  |  | 389
5904 | 2018-02-21 | 2018-07-10 | 2018-11-28 | 2019-03-11 | COMP | 2019-03-25 | COMP | 2019-04-15 | COMP | 2019-06-11 | COMP | 2019-06-17 | COMP | Rule 16 | 98 | 98 | 11 | 16 | 41 | 5 | 333
5998 | 2018-02-21 | 2018-07-18 | 2018-08-28 | 2018-08-28 | COMP | 2018-10-02 | COMP | 2018-10-02 | COMP | 2018-12-03 | COMP | 2019-01-09 | COMP | Rule 16 | 104 | 30 | 25 | 1 | 42 | 26 | 223
6320 | 2018-02-21 | 2018-08-10 | 2018-11-14 | 2018-11-14 | COMP | 2019-01-03 | COMP | 2019-06-10 | COMP | 2019-05-29 | COMP | 2019-06-19 | COMP | Rule 16 | 121 | 67 | 33 | 110 | 0 | 8 | 335
6858 | 2018-02-21 | 2018-09-13 | 2018-12-10 | 2018-12-10 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-05-14 | COMP | 2019-07-22 | COMP | Rule 16 | 144 | 60 | 53 | 1 | 56 | 48 | 357
7458 | 2018-02-21 | 2018-10-15 | 2018-12-04 | 2018-12-04 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-10-21 | INPR | 2019-07-10 | COMP | Rule 16 | 166 | 34 | 13 | 1 |  |  | 349
8201 | 2018-02-21 | 2018-11-17 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-03-18 | COMP | 2019-05-01 | COMP | Rule 16 | 189 | 41 | 37 | 1 | 4 | 33 | 301
26070 | 2018-02-21 | 2021-03-06 | 2021-04-20 | 2021-04-20 | COMP | 2021-06-24 | COMP | 2021-09-28 | COMP |  |  | 2022-01-14 | COMP | Rule 16 | 764 | 32 | 47 | 67 |  |  | 983
3128 | 2018-02-22 | 2018-03-12 | 2018-07-19 | 2018-07-19 | COMP | 2018-09-13 | COMP | 2018-09-14 | COMP | 2019-07-16 | COMP | 2019-07-23 | COMP | Rule 15 | 13 | 92 | 40 | 2 | 209 | 6 | 357
3196 | 2018-02-22 | 2018-03-21 | 2018-04-30 | 2018-04-30 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-07-06 | COMP | 2020-07-20 | COMP | Rule 15/16 | 20 | 29 | 508 | 1 | 43 | 11 | 607
3367 | 2018-02-22 | 2018-04-13 | 2018-05-29 | 2018-05-29 | COMP | 2019-08-14 | COMP | 2019-08-15 | COMP | 2019-08-02 | COMP | 2019-09-20 | COMP | Rule 16 | 37 | 32 | 306 | 2 | 0 | 26 | 399
3501 | 2018-02-22 | 2018-05-08 | 2019-02-02 | 2019-02-02 | COMP | 2019-04-23 | COMP | 2019-06-12 | COMP | 2019-05-28 | COMP | 2019-09-22 | COMP | Rule 15/16 | 54 | 185 | 56 | 36 | 0 | 71 | 399
4825 | 2018-02-22 | 2018-04-02 | 2018-08-02 | 2018-08-02 | COMP | 2018-08-21 | COMP | 2018-09-25 | COMP | 2018-11-26 | COMP | 2019-01-24 | COMP | Rule 16 | 28 | 87 | 14 | 25 | 42 | 41 | 232
4831 | 2018-02-22 | 2018-04-04 | 2018-06-21 | 2018-06-21 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-08-25 | COMP | Rule 15/16 | 30 | 56 | 262 | 1 | 1 | 35 | 380
4853 | 2018-02-22 | 2018-04-04 | 2018-05-30 | 2018-05-30 | COMP | 2018-08-28 | COMP | 2018-08-28 | COMP | 2019-04-08 | COMP | 2019-04-30 | COMP | Rule 16 | 30 | 40 | 64 | 1 | 152 | 17 | 299
5157 | 2018-02-22 | 2018-05-04 | 2018-10-10 | 2018-11-16 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-04-25 | COMP | 2019-05-15 | COMP | Rule 16 | 52 | 111 | 64 | 1 | 46 | 15 | 310
5221 | 2018-02-22 | 2018-05-11 | 2018-06-12 | 2018-06-12 | COMP | 2018-08-20 | COMP | 2018-09-25 | COMP | 2019-05-15 | COMP | 2019-07-25 | COMP | Rule 16 | 57 | 22 | 49 | 26 | 160 | 50 | 359
5417 | 2018-02-22 | 2018-05-31 | 2018-08-07 | 2018-08-07 | COMP | 2019-01-30 | COMP | 2019-01-31 | COMP | 2019-01-28 | COMP | 2019-04-25 | COMP | Rule 16 | 70 | 48 | 120 | 2 | 0 | 60 | 296
5446 | 2018-02-22 | 2018-05-31 | 2018-08-13 | 2018-08-13 | COMP | 2019-01-30 | COMP | 2019-02-28 | COMP | 2019-01-28 | COMP | 2019-03-12 | COMP | Rule 16 | 70 | 52 | 116 | 21 | 0 | 9 | 264
5470 | 2018-02-22 | 2018-06-01 | 2018-09-04 | 2018-09-04 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-07-15 | COMP | 2019-08-20 | COMP | Rule 16 | 71 | 66 | 170 | 1 | 47 | 27 | 377
5598 | 2018-02-22 | 2018-06-18 | 2018-12-03 | 2018-12-03 | COMP | 2019-01-25 | COMP | 2019-02-25 | COMP | 2019-02-22 | COMP | 2019-04-12 | COMP | Rule 16 | 82 | 116 | 37 | 21 | 0 | 35 | 287
5822 | 2018-02-22 | 2018-07-05 | 2019-01-14 | 2019-01-14 | COMP | 2019-03-27 | COMP | 2019-04-10 | COMP | 2019-04-11 | COMP | 2019-06-20 | COMP | Rule 16 | 94 | 132 | 51 | 11 | 2 | 50 | 335
6155 | 2018-02-22 | 2018-07-31 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-03-06 | COMP | 2019-04-04 | COMP | Rule 16 | 112 | 68 | 17 | 1 | 66 | 22 | 281
7710 | 2018-02-22 | 2018-10-26 | 2018-11-10 | 2018-11-10 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2018-11-26 | COMP | 2019-10-01 | COMP | Rule 16 | 174 | 11 | 10 | 1 | 0 | 213 | 406
8773 | 2018-02-22 | 2018-12-26 | 2019-03-28 | 2019-05-24 | COMP | 2019-05-24 | NOTN | 2019-05-24 | COMP | 2019-09-05 | COMP | 2020-04-29 | COMP | Other | 213 | 64 |  | 1 | 72 | 163 | 550
9155 | 2018-02-22 | 2019-01-18 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-24 | COMP | 2019-05-13 | COMP | 2019-05-07 | COMP | 2019-06-19 | COMP | Rule 16 | 229 | 49 | 19 | 14 | 0 | 27 | 334
12649 | 2018-02-22 | 2019-06-17 | 2019-11-17 | 2019-11-17 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | 2020-02-25 | COMP | 2020-05-13 | COMP | Rule 16 | 332 | 107 | 45 | 1 | 22 | 57 | 560
3164 | 2018-02-23 | 2018-03-15 | 2018-06-07 | 2018-06-07 | COMP | 2020-03-17 | COMP | 2020-04-03 | COMP | 2020-05-28 | COMP | 2020-06-12 | COMP | Rule 16 | 15 | 60 | 445 | 14 | 39 | 12 | 580
3554 | 2018-02-23 | 2018-05-15 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-02 | COMP | 2018-11-21 | COMP | 2018-10-19 | COMP | 2019-01-28 | COMP | Rule 15/16 | 58 | 91 | 8 | 36 | 0 | 44 | 233
3591 | 2018-02-23 | 2018-05-22 | 2018-10-11 | 2018-10-11 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-07-02 | COMP | 2019-08-28 | COMP | Rule 16 | 63 | 100 | 19 | 1 | 163 | 41 | 382
4729 | 2018-02-23 | 2018-03-22 | 2018-06-25 | 2018-06-25 | COMP | 2019-01-23 | COMP | 2019-01-24 | INPR | 2022-11-05 | REQD | 2019-03-04 | COMP | Rule 16 | 20 | 67 | 145 |  |  |  | 257
4956 | 2018-02-23 | 2018-04-14 | 2018-09-27 | 2018-09-27 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-03-06 | COMP | 2019-04-30 | COMP | Rule 16 | 36 | 116 | 49 | 1 | 60 | 40 | 298
5014 | 2018-02-23 | 2018-04-25 | 2018-08-22 | 2019-02-23 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-10-22 | COMP | 2019-11-07 | COMP | Rule 15/16 | 44 | 84 | 47 | 1 | 123 | 13 | 432
5093 | 2018-02-23 | 2018-04-30 | 2018-09-11 | 2018-09-11 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2021-01-02 | INPR | 2019-03-04 | COMP | Rule 16 | 47 | 94 | 52 | 1 |  |  | 257
5108 | 2018-02-23 | 2018-04-30 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-03-12 | COMP | 2019-04-24 | COMP | Rule 16 | 47 | 210 | 7 | 1 | 2 | 32 | 294
5411 | 2018-02-23 | 2018-05-29 | 2018-10-22 | 2018-11-16 | COMP | 2018-12-17 | COMP | 2019-01-23 | COMP | 2019-10-02 | COMP | 2019-10-24 | COMP | Rule 16 | 67 | 103 | 20 | 25 | 177 | 17 | 422
5535 | 2018-02-23 | 2018-06-12 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-11 | COMP | 2019-01-18 | NOTN | 2019-02-14 | NOTN | 2019-02-06 | COMP | Rule 16 | 77 | 118 | 9 |  |  |  | 240
5542 | 2018-02-23 | 2018-06-11 | 2018-11-11 | 2018-11-11 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2020-02-24 | COMP | 2020-05-11 | COMP | Rule 16 | 76 | 108 | 74 | 1 | 246 | 56 | 557
5597 | 2018-02-23 | 2018-06-18 | 2018-10-05 | 2018-10-05 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-01-17 | COMP | 2019-02-28 | COMP | Rule 16 | 81 | 78 | 18 | 1 | 53 | 29 | 255
5875 | 2018-02-23 | 2018-07-10 | 2018-09-27 | 2018-09-27 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-05-01 | COMP | 2019-05-17 | COMP | Rule 16 | 96 | 57 | 106 | 1 | 43 | 13 | 311
5881 | 2018-02-23 | 2018-07-09 | 2018-08-19 | 2018-08-19 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-05-21 | COMP | 2019-06-27 | COMP | Rule 16 | 95 | 30 | 96 | 1 | 94 | 27 | 339
6455 | 2018-02-23 | 2018-08-20 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-04-15 | COMP | 2019-03-18 | COMP | Rule 16 | 125 | 120 | 8 | 1 | 37 |  | 267
6688 | 2018-02-23 | 2018-09-06 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-26 | COMP | 2018-11-05 | COMP | 2018-11-01 | COMP | 2019-01-10 | COMP | Rule 15/16 | 137 | 39 | 17 |  | 0 | 44 | 222
6843 | 2018-02-23 | 2018-09-12 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-02-24 | COMP | Rule 15/16 | 141 | 54 | 32 | 1 | 1 | 27 | 251
4673 | 2018-02-24 | 2018-03-07 | 2018-09-10 | 2018-09-10 | COMP | 2018-12-27 | COMP | 2019-06-21 | COMP | 2019-07-16 | COMP | 2019-07-22 | COMP | Rule 15/16 | 8 | 131 | 75 | 123 | 17 | 5 | 354
5068 | 2018-02-24 | 2018-04-28 | 2018-09-10 | 2018-09-10 | COMP | 2018-11-14 | COMP | 2018-11-16 | COMP | 2019-09-20 | COMP | 2019-11-18 | COMP | Rule 16 | 45 | 93 | 47 | 3 | 212 | 41 | 437
5336 | 2018-02-24 | 2018-05-22 | 2018-10-19 | 2018-10-19 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2020-07-22 | COMP | 2020-09-16 | COMP | Rule 16 | 62 | 106 | 125 | 1 | 317 | 40 | 646
3865 | 2018-02-25 | 2018-08-27 | 2018-12-12 | 2018-12-07 | COMP | 2018-12-31 | COMP | 2019-06-05 | NOTN |  |  | 2019-06-26 | COMP | Rule 16 | 129 | 74 | 16 |  |  |  | 337
3868 | 2018-02-25 | 2018-08-28 | 2018-12-12 | 2018-12-05 | COMP | 2018-12-20 | COMP | 2019-05-20 | NOTN |  |  | 2019-09-19 | COMP | Rule 16 | 130 | 73 | 12 |  |  |  | 396
3893 | 2018-02-25 | 2018-09-25 | 2018-10-05 | 2018-09-26 | COMP | 2019-01-28 | COMP | 2019-04-29 | NOTN |  |  | 2019-06-26 | COMP | Rule 16 | 149 | 9 | 83 |  |  |  | 337
3930 | 2018-02-25 | 2018-10-18 | 2018-12-12 | 2018-12-06 | COMP | 2018-12-20 | COMP | 2019-03-04 | NOTN |  |  | 2019-04-03 | COMP | Rule 16 | 166 | 37 | 11 |  |  |  | 278
3931 | 2018-02-25 | 2018-10-18 | 2018-12-12 | 2018-12-07 | COMP | 2019-01-28 | COMP | 2019-02-13 | NOTN | 2019-09-13 | COMP | 2019-10-24 | COMP | Rule 16 | 166 | 37 | 34 |  |  |  | 421
3934 | 2018-02-25 | 2018-10-22 | 2019-01-14 | 2019-01-14 | COMP | 2019-05-01 | COMP | 2019-10-10 | COMP | 2019-11-07 | COMP | 2019-12-09 | COMP | Rule 16 | 168 | 56 | 76 | 114 | 21 | 20 | 450
3939 | 2018-02-25 | 2018-10-22 | 2018-12-12 | 2018-11-29 | COMP | 2018-12-31 | COMP | 2019-06-05 | NOTN |  |  | 2019-07-20 | COMP | Rule 16 | 168 | 35 | 22 |  |  |  | 353
3940 | 2018-02-25 | 2018-10-22 | 2018-12-24 | 2018-12-21 | COMP | 2018-12-31 | COMP | 2019-11-06 | COMP | 2019-11-07 | COMP | 2019-12-12 | COMP | Rule 16 | 168 | 43 | 6 | 217 | 2 | 23 | 453
3944 | 2018-02-25 | 2018-10-22 | 2019-01-14 | 2019-01-14 | COMP | 2019-04-08 | COMP | 2019-04-11 | NOTN | 2019-10-01 | COMP | 2019-10-24 | COMP | Rule 16 | 168 | 56 | 59 |  |  |  | 421
3955 | 2018-02-25 | 2018-10-30 | 2018-12-14 | 2018-12-14 | COMP | 2018-12-31 | COMP | 2019-10-15 | COMP | 2019-11-07 | COMP | 2019-11-06 | COMP | Rule 16 | 174 | 31 | 11 | 201 | 18 |  | 430
3957 | 2018-02-25 | 2018-10-30 | 2019-01-08 | 2019-01-08 | COMP | 2019-04-08 | COMP | 2019-10-02 | COMP | 2019-11-13 | COMP | 2019-11-22 | COMP | Rule 16 | 174 | 46 | 63 | 125 | 30 | 8 | 441
3958 | 2018-02-25 | 2018-10-30 | 2018-12-12 | 2018-12-06 | COMP | 2018-12-31 | COMP | 2019-11-05 | COMP | 2019-11-19 | COMP | 2019-12-09 | COMP | Rule 16 | 174 | 29 | 17 | 216 | 10 | 13 | 450
3963 | 2018-02-25 | 2018-10-30 | 2019-02-07 | 2019-02-04 | COMP | 2019-04-08 | COMP | 2019-04-10 | COMP |  |  | 2019-11-04 | COMP | Rule 16 | 174 | 67 | 45 | 3 |  |  | 428
3964 | 2018-02-25 | 2018-10-30 | 2020-04-17 | 2020-04-17 | COMP | 2020-07-29 | COMP | 2020-08-17 | COMP | 2020-09-02 | COMP | 2020-09-25 | COMP | Rule 16 | 174 | 367 | 73 | 14 | 13 | 17 | 653
3969 | 2018-02-25 | 2018-11-01 | 2018-12-24 | 2018-12-21 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-11-07 | COMP | 2019-12-26 | COMP | Rule 16 | 176 | 35 | 230 | 1 | 0 | 25 | 462
3970 | 2018-02-25 | 2018-11-01 | 2019-02-14 | 2019-02-14 | COMP | 2019-04-08 | COMP | 2019-11-05 | COMP | 2019-11-13 | COMP | 2019-12-06 | COMP | Rule 16 | 176 | 70 | 37 | 149 | 6 | 16 | 449
3971 | 2018-02-25 | 2018-11-01 | 2019-01-07 | 2019-01-03 | COMP | 2019-04-16 | COMP | 2019-05-06 | NOTN |  |  | 2019-09-20 | COMP | Rule 16 | 176 | 43 | 72 |  |  |  | 397
4017 | 2018-02-25 | 2018-12-03 | 2019-03-26 | 2019-03-26 | COMP | 2020-03-04 | COMP | 2020-03-12 | COMP | 2020-05-26 | COMP | 2020-06-22 | COMP | Rule 16 | 195 | 78 | 237 | 7 | 53 | 20 | 585
4259 | 2018-02-25 | 2019-12-11 | 2019-12-22 | 2019-12-22 | COMP | 2020-02-10 | COMP | 2020-03-03 | COMP | 2023-12-02 | INPR | 2020-03-13 | COMP | Rule 16 | 452 | 8 | 33 | 16 |  |  | 515
6372 | 2018-02-25 | 2018-08-14 | 2018-09-12 | 2018-09-12 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-07-21 | INPR | 2019-02-27 | COMP | Rule 16 | 120 | 21 | 70 | 1 |  |  | 253
6662 | 2018-02-25 | 2018-09-05 | 2018-11-07 | 2018-11-07 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-09-13 | COMP | 2019-09-20 | COMP | Rule 16 | 135 | 46 | 14 | 1 | 200 | 6 | 397
3266 | 2018-02-26 | 2018-03-29 | 2018-10-08 | 2020-01-10 | COMP | 2020-04-06 | COMP | 2020-07-07 | COMP | 2020-06-22 | COMP | 2020-10-29 | COMP | Rule 15/16 | 24 | 135 | 60 | 66 | 0 | 82 | 677
3287 | 2018-02-26 | 2018-04-02 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-26 | COMP | 2019-01-10 | COMP | 2019-01-09 | COMP | 2019-03-07 | COMP | Rule 15/16 | 26 | 135 | 31 | 32 | 0 | 39 | 259
3288 | 2018-02-26 | 2018-04-02 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-28 | COMP | 2019-01-15 | COMP | 2019-01-19 | COMP | 2019-03-07 | COMP | Rule 16 | 26 | 135 | 33 | 33 | 4 | 32 | 259
3635 | 2018-02-26 | 2018-05-30 | 2018-09-13 | 2018-09-13 | COMP | 2018-11-14 | COMP | 2019-01-18 | COMP | 2019-04-20 | INPR | 2019-01-24 | COMP | Rule 16 | 67 | 75 | 44 | 44 |  |  | 230
3928 | 2018-02-26 | 2018-10-15 | 2018-12-12 | 2018-12-01 | COMP | 2018-12-20 | COMP | 2019-10-30 | COMP |  |  | 2019-11-22 | COMP | Rule 16 | 163 | 40 | 14 | 218 |  |  | 441
3935 | 2018-02-26 | 2018-10-22 | 2018-12-12 | 2018-12-07 | COMP | 2019-01-14 | COMP | 2019-10-30 | COMP |  |  | 2019-11-30 | COMP | Rule 16 | 168 | 35 | 25 | 203 |  |  | 444
3941 | 2018-02-26 | 2018-10-22 | 2018-11-30 | 2018-11-30 | COMP | 2018-12-31 | COMP | 2019-01-08 | NOTN | 2021-02-27 | INPR | 2019-11-12 | COMP | Rule 15/16 | 168 | 27 | 21 |  |  |  | 433
3946 | 2018-02-26 | 2018-10-22 | 2018-11-24 | 2018-11-24 | COMP | 2018-12-05 | COMP | 2019-01-14 | NOTN |  |  | 2019-10-25 | COMP | Rule 16 | 168 | 22 | 8 |  |  |  | 422
3949 | 2018-02-26 | 2018-10-24 | 2018-12-14 | 2018-12-12 | COMP | 2018-12-28 | COMP | 2019-01-08 | NOTN |  |  | 2019-11-01 | COMP | Rule 16 | 170 | 35 | 12 |  |  |  | 427
3960 | 2018-02-26 | 2018-10-30 | 2018-12-12 | 2018-12-07 | COMP | 2019-11-01 | COMP | 2019-11-18 | COMP | 2020-04-06 | COMP | 2020-04-23 | COMP | Rule 16 | 174 | 29 | 229 | 11 | 95 | 14 | 544
3962 | 2018-02-26 | 2018-10-30 | 2019-01-07 | 2019-01-07 | COMP | 2019-02-12 | COMP | 2019-10-31 | COMP |  |  | 2019-12-06 | COMP | Rule 16 | 174 | 45 | 26 | 184 |  |  | 449
4002 | 2018-02-26 | 2018-11-16 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-16 | COMP | 2019-11-01 | COMP | 2019-11-13 | COMP | 2019-12-04 | COMP | Rule 16 | 186 | 86 | 17 | 141 | 8 | 14 | 447
4003 | 2018-02-26 | 2018-11-16 | 2019-06-05 | 2019-06-05 | COMP | 2019-11-01 | COMP | 2020-03-09 | COMP |  |  | 2020-04-02 | COMP | Rule 15/16 | 186 | 137 | 106 | 85 |  |  | 529
4012 | 2018-02-26 | 2018-11-29 | 2018-12-24 | 2018-12-21 | COMP | 2019-01-09 | COMP | 2019-10-28 | COMP |  |  | 2019-11-20 | COMP | Rule 16 | 193 | 18 | 12 | 204 |  |  | 439
4019 | 2018-02-26 | 2018-12-04 | 2019-04-18 | 2019-04-18 | COMP | 2019-05-01 | COMP | 2019-10-28 | COMP |  |  | 2019-12-04 | COMP | Rule 16 | 196 | 94 | 10 | 126 |  |  | 447
4020 | 2018-02-26 | 2018-12-04 | 2019-03-28 | 2019-03-28 | COMP | 2019-11-04 | COMP | 2020-04-17 | COMP |  |  | 2020-10-21 | COMP | Rule 16 | 196 | 79 | 155 | 113 |  |  | 671
4021 | 2018-02-26 | 2018-12-04 | 2019-03-27 | 2019-03-27 | COMP | 2019-04-16 | COMP | 2019-05-06 | NOTN |  |  | 2021-01-25 | COMP | Rule 15/16 | 196 | 78 | 15 |  |  |  | 733
4801 | 2018-02-26 | 2018-03-31 | 2018-10-23 | 2018-10-23 | COMP | 2018-12-20 | COMP | 2019-02-22 | COMP | 2019-01-28 | COMP | 2019-04-06 | COMP | Rule 16 | 25 | 144 | 40 | 43 | 0 | 31 | 280
4883 | 2018-02-26 | 2018-04-09 | 2018-09-24 | 2018-09-24 | COMP | 2018-12-18 | COMP | 2019-01-30 | COMP | 2018-12-19 | COMP | 2019-03-26 | COMP | Rule 16 | 31 | 118 | 59 | 29 | 0 | 39 | 272
4910 | 2018-02-26 | 2018-04-11 | 2018-05-30 | 2018-07-26 | COMP | 2018-08-22 | COMP | 2018-08-22 | COMP | 2018-10-02 | COMP | 2019-04-16 | COMP | Rule 16 | 33 | 35 | 20 | 1 | 29 | 134 | 287
4916 | 2018-02-26 | 2018-04-11 | 2018-06-08 | 2018-06-28 | COMP | 2018-08-27 | COMP | 2018-09-24 | COMP | 2018-09-25 | COMP | 2019-04-16 | COMP | Rule 15/16 | 33 | 42 | 42 | 20 | 2 | 139 | 287
4942 | 2018-02-26 | 2018-04-13 | 2018-06-25 | 2018-10-23 | COMP | 2019-07-17 | COMP | 2019-08-07 | COMP | 2023-11-11 | INPR | 2019-10-02 | COMP | Rule 16 | 35 | 51 | 183 | 16 |  |  | 405
4948 | 2018-02-26 | 2018-04-13 | 2018-05-14 | 2018-05-14 | COMP | 2018-08-20 | COMP | 2018-08-20 | COMP | 2019-03-21 | COMP | 2019-04-25 | COMP | Rule 16 | 35 | 22 | 69 | 1 | 146 | 26 | 294
4949 | 2018-02-26 | 2018-04-13 | 2018-06-05 | 2018-06-05 | COMP | 2018-07-06 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-07-03 | COMP | Rule 16 | 35 | 37 | 23 | 222 | 1 | 29 | 342
4951 | 2018-02-26 | 2018-04-13 | 2018-06-05 | 2018-07-10 | COMP | 2018-08-22 | COMP | 2018-08-22 | COMP | 2019-03-07 | COMP | 2019-04-15 | COMP | Rule 15/16 | 35 | 37 | 32 | 1 | 134 | 28 | 286
5018 | 2018-02-26 | 2018-04-24 | 2018-08-13 | 2018-08-13 | COMP | 2018-11-08 | COMP | 2018-11-08 | COMP | 2019-07-23 | COMP | 2019-08-02 | COMP | Rule 16 | 42 | 78 | 63 | 1 | 175 | 9 | 363
5078 | 2018-02-26 | 2018-04-28 | 2018-09-04 | 2018-09-04 | COMP | 2018-09-19 | COMP | 2018-09-19 | COMP | 2018-10-08 | COMP | 2019-01-12 | COMP | Rule 16 | 45 | 89 | 12 | 1 | 14 | 65 | 222
5118 | 2018-02-26 | 2018-05-01 | 2018-08-19 | 2018-08-19 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-07-21 | INPR | 2019-04-19 | COMP | Rule 15/16 | 47 | 77 | 70 | 1 |  |  | 290
5327 | 2018-02-26 | 2018-05-22 | 2018-10-17 | 2018-11-02 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-05-07 | COMP | 2019-05-15 | COMP | Rule 16 | 62 | 104 | 81 | 1 | 46 | 7 | 308
5553 | 2018-02-26 | 2018-06-14 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-30 | COMP | 2019-04-03 | COMP | 2019-10-14 | COMP | 2019-11-25 | COMP | Rule 15/16 | 78 | 69 | 29 | 105 | 136 | 30 | 442
5779 | 2018-02-26 | 2018-07-03 | 2018-09-27 | 2018-09-27 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2020-01-13 | COMP | 2020-02-12 | COMP | Rule 16 | 91 | 61 | 168 | 1 | 156 | 22 | 494
5980 | 2018-02-26 | 2018-07-16 | 2018-11-14 | 2019-02-21 | COMP | 2019-03-28 | COMP | 2019-05-10 | COMP | 2019-10-01 | COMP | 2019-10-08 | COMP | Rule 15/16 | 99 | 86 | 26 | 32 | 100 | 6 | 409
6244 | 2018-02-26 | 2018-08-06 | 2018-09-06 | 2020-02-07 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-12-18 | COMP | 2021-03-23 | COMP | Rule 16 | 114 | 23 | 35 | 1 | 186 | 64 | 773
6838 | 2018-02-26 | 2018-09-12 | 2018-11-07 | 2019-03-20 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-30 | COMP | 2019-05-08 | COMP | Rule 16 | 140 | 41 | 11 | 1 | 20 | 7 | 303
9095 | 2018-02-26 | 2019-01-16 | 2019-03-07 | 2019-04-25 | COMP | 2019-05-15 | COMP | 2019-05-15 | COMP | 2019-08-20 | COMP | 2019-09-19 | COMP | Rule 16 | 225 | 35 | 15 | 1 | 68 | 22 | 396
9192 | 2018-02-26 | 2019-01-21 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2021-10-15 | COMP | 2021-11-16 | COMP | Rule 16 | 227 | 41 | 4 | 1 | 648 | 22 | 939
9303 | 2018-02-26 | 2019-01-28 | 2019-04-03 | 2019-04-03 | COMP | 2020-02-26 | COMP | 2020-04-09 | COMP | 2020-09-29 | COMP | 2020-05-19 | COMP | Rule 16 | 232 | 47 | 226 | 32 | 122 |  | 562
9517 | 2018-02-26 | 2019-02-06 | 2019-05-30 | 2019-05-30 | COMP | 2019-11-08 | COMP | 2020-05-14 | COMP | 2020-10-20 | COMP | 2020-11-04 | COMP | Rule 16 | 239 | 80 | 115 | 128 | 112 | 12 | 681
9568 | 2018-02-26 | 2019-02-07 | 2019-07-24 | 2019-07-24 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP |  |  | 2020-11-05 | COMP | Rule 16 | 240 | 117 | 224 | 1 |  |  | 682
9582 | 2018-02-26 | 2019-02-08 | 2019-06-20 | 2019-06-20 | COMP | 2020-01-16 | COMP | 2020-03-16 | COMP |  |  | 2020-03-19 | COMP | Rule 16 | 241 | 93 | 144 | 41 |  |  | 519
10243 | 2018-02-26 | 2019-03-07 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-01-19 | INPR | 2019-09-20 | COMP | Rule 16 | 259 | 126 | 6 | 1 |  |  | 397
11459 | 2018-02-26 | 2019-04-29 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-12-29 | COMP | 2021-02-05 | COMP | Rule 16 | 296 | 118 | 28 | 1 | 277 | 27 | 742
3182 | 2018-02-27 | 2018-03-19 | 2019-01-17 | 2019-01-17 | COMP | 2019-08-16 | COMP | 2020-02-24 | COMP | 2021-07-27 | COMP | 2021-08-19 | COMP | Rule 15/16 | 15 | 211 | 148 | 129 | 361 | 18 | 877
3663 | 2018-02-27 | 2018-06-05 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-25 | COMP | 2019-05-28 | COMP |  |  | 2019-07-05 | COMP | Rule 16 | 70 | 153 | 29 | 66 |  |  | 342
3664 | 2018-02-27 | 2018-06-05 | 2019-05-24 | 2019-05-24 | COMP | 2019-07-12 | COMP | 2019-07-25 | COMP |  |  | 2019-10-30 | COMP | Rule 16 | 70 | 245 | 34 | 10 |  |  | 424
3665 | 2018-02-27 | 2018-06-05 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-08 | COMP | 2019-05-28 | COMP |  |  | 2019-07-24 | COMP | Rule 16 | 70 | 196 | 38 | 14 |  |  | 355
3666 | 2018-02-27 | 2018-06-05 | 2018-12-14 | 2018-12-13 | COMP | 2019-02-25 | COMP | 2020-04-21 | COMP |  |  | 2020-08-03 | COMP | Rule 16 | 70 | 134 | 49 | 292 |  |  | 614
3667 | 2018-02-27 | 2018-06-05 | 2019-03-14 | 2019-03-14 | COMP | 2019-05-08 | COMP | 2019-09-16 | COMP | 2021-11-24 | COMP | 2021-12-08 | COMP | Rule 16 | 70 | 194 | 40 | 91 | 553 | 9 | 952
4253 | 2018-02-27 | 2019-11-20 | 2020-02-11 | 2020-02-11 | COMP | 2020-09-11 | COMP | 2020-09-11 | COMP | 2020-09-15 | COMP | 2020-11-18 | COMP | Rule 16 | 438 | 55 | 151 | 1 | 3 | 46 | 689
4704 | 2018-02-27 | 2018-03-16 | 2018-07-24 | 2018-07-24 | COMP | 2018-11-26 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-05-31 | COMP | Rule 16 | 14 | 91 | 86 | 99 | 1 | 32 | 318
4771 | 2018-02-27 | 2018-03-28 | 2018-05-30 | 2019-10-17 | COMP | 2019-10-31 | COMP | 2019-12-13 | COMP | 2019-12-02 | COMP | 2020-01-07 | COMP | Rule 16 | 22 | 45 | 11 | 29 | 0 | 16 | 468
4817 | 2018-02-27 | 2018-04-01 | 2018-07-27 | 2019-05-31 | COMP | 2019-08-19 | COMP | 2019-08-30 | COMP | 2018-05-22 | COMP | 2019-08-30 | COMP | Rule 16 | 24 | 83 | 56 | 10 | 0 | 1 | 382
4874 | 2018-02-27 | 2018-04-09 | 2018-09-04 | 2019-04-01 | COMP | 2019-04-16 | COMP | 2019-04-26 | COMP | 2019-05-07 | COMP | 2019-06-05 | COMP | Rule 16 | 30 | 104 | 12 | 9 | 8 | 21 | 321
4884 | 2018-02-27 | 2018-04-09 | 2018-09-04 | 2018-09-04 | COMP | 2018-11-05 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-05-31 | COMP | Rule 16 | 30 | 104 | 45 | 116 | 1 | 27 | 318
4913 | 2018-02-27 | 2018-04-11 | 2018-08-13 | 2018-08-13 | COMP | 2018-09-07 | COMP | 2019-08-13 | COMP | 2020-07-08 | COMP | 2020-08-03 | COMP | Rule 16 | 32 | 87 | 19 | 234 | 228 | 19 | 614
5100 | 2018-02-27 | 2018-04-30 | 2018-07-13 | 2018-07-13 | COMP | 2018-08-17 | COMP | 2019-11-21 | COMP | 2020-04-20 | COMP | 2020-07-30 | COMP | Rule 15/16 | 45 | 53 | 26 | 318 | 102 | 73 | 612
5140 | 2018-02-27 | 2018-05-03 | 2018-08-08 | 2018-08-08 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-03-19 | COMP | 2019-05-09 | COMP | Rule 15/16 | 48 | 68 | 150 | 1 | 3 | 38 | 303
5196 | 2018-02-27 | 2018-05-09 | 2018-07-28 | 2018-07-28 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | 2019-12-17 | COMP | Rule 16 | 52 | 56 | 312 | 1 | 19 | 19 | 455
5283 | 2018-02-27 | 2018-05-16 | 2018-05-22 | 2018-05-22 | COMP | 2018-07-10 | COMP | 2018-07-10 | COMP | 2020-04-26 | INPR | 2019-04-01 | COMP | Rule 15/16 | 57 | 5 | 34 | 1 |  |  | 275
5817 | 2018-02-27 | 2018-07-05 | 2018-10-31 | 2018-10-31 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-01-10 | COMP | 2019-02-25 | COMP | Rule 15/16 | 91 | 84 | 21 | 1 | 27 | 31 | 250
7671 | 2018-02-27 | 2018-10-24 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-10-21 | INPR | 2019-05-23 | COMP | Rule 16 | 169 | 20 | 7 | 1 |  |  | 313
9228 | 2018-02-27 | 2019-01-23 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-03 | COMP | 2019-05-29 | NOTN | 2019-05-02 | COMP | 2020-08-04 | COMP | Rule 16 | 228 | 70 | 3 |  |  |  | 615
11113 | 2018-02-27 | 2019-04-13 | 2019-05-16 | 2019-07-17 | COMP | 2019-07-30 | COMP | 2019-11-04 | COMP | 2019-12-10 | COMP | 2019-12-30 | COMP | Rule 15/16 | 284 | 24 | 10 | 69 | 24 | 14 | 463
11901 | 2018-02-27 | 2019-05-15 | 2019-07-18 | 2019-07-18 | COMP | 2019-09-10 | COMP | 2020-05-31 | REQD | 2019-10-22 | COMP | 2020-01-03 | COMP | Rule 16 | 307 | 45 | 38 |  |  |  | 466
3376 | 2018-02-28 | 2018-04-16 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-02 | COMP | 2019-01-08 | COMP | 2019-08-09 | COMP | 2019-09-04 | COMP | Rule 16 | 34 | 143 | 38 | 5 | 150 | 18 | 383
3399 | 2018-02-28 | 2018-04-18 | 2018-08-08 | 2018-08-08 | COMP | 2018-09-06 | COMP | 2018-10-05 | COMP | 2019-08-14 | COMP | 2019-09-04 | COMP | Rule 15/16 | 36 | 79 | 21 | 22 | 215 | 15 | 383
3502 | 2018-02-28 | 2018-05-08 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-24 | COMP | 2019-06-04 | COMP | 2019-06-13 | COMP | 2019-07-26 | COMP | Rule 16 | 50 | 91 | 29 | 152 | 8 | 31 | 356
3616 | 2018-02-28 | 2018-05-24 | 2019-11-22 | 2019-11-22 | COMP | 2020-04-01 | COMP | 2020-07-17 | INPR | 2020-11-05 | COMP | 2020-10-02 | COMP | Rule 15/16 | 62 | 378 | 88 |  |  |  | 656
4051 | 2018-02-28 | 2018-12-31 | 2019-06-09 | 2019-06-09 | COMP | 2019-09-11 | COMP | 2020-11-16 | COMP | 2022-07-02 | INPR | 2020-11-20 | COMP | Rule 15/16 | 212 | 111 | 66 | 299 |  |  | 690
4808 | 2018-02-28 | 2018-03-31 | 2018-09-18 | 2018-09-18 | COMP | 2018-10-11 | COMP | 2018-11-26 | COMP | 2018-11-02 | COMP | 2019-01-02 | COMP | Rule 16 | 23 | 119 | 18 | 30 | 0 | 26 | 213
4896 | 2018-02-28 | 2018-04-10 | 2018-06-08 | 2018-06-08 | COMP | 2018-08-13 | COMP | 2020-05-22 | COMP | 2020-01-23 | COMP | 2020-08-13 | COMP | Rule 16 | 30 | 43 | 46 | 447 | 0 | 59 | 621
4996 | 2018-02-28 | 2018-04-21 | 2019-01-07 | 2019-01-07 | COMP | 2019-02-05 | COMP | 2019-02-15 | COMP |  |  | 2020-01-11 | COMP | Rule 16 | 38 | 178 | 21 | 9 |  |  | 470
5046 | 2018-02-28 | 2018-04-27 | 2018-10-23 | 2018-10-23 | COMP | 2018-11-27 | COMP | 2019-02-25 | COMP | 2019-01-30 | COMP | 2019-03-26 | COMP | Rule 15/16 | 43 | 125 | 23 | 61 | 0 | 22 | 270
5057 | 2018-02-28 | 2018-04-26 | 2018-09-18 | 2018-09-18 | COMP | 2019-08-19 | COMP | 2019-09-09 | INPR | 2019-08-20 | COMP | 2019-09-11 | COMP | Rule 16 | 42 | 101 | 231 |  |  |  | 388
5128 | 2018-02-28 | 2018-05-02 | 2018-12-20 | 2018-12-20 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-09-22 | INPR | 2019-06-02 | COMP | Rule 15/16 | 46 | 161 | 4 | 1 |  |  | 317
5174 | 2018-02-28 | 2018-05-07 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-22 | COMP | 2019-05-15 | COMP | 2019-06-21 | COMP | 2019-07-18 | COMP | Rule 16 | 49 | 225 | 17 | 18 | 27 | 19 | 350
5200 | 2018-02-28 | 2018-05-10 | 2018-11-03 | 2018-11-03 | COMP | 2019-04-08 | COMP | 2019-05-16 | COMP | 2019-07-01 | COMP | 2019-07-30 | COMP | Rule 16 | 52 | 124 | 104 | 29 | 32 | 21 | 358
5230 | 2018-02-28 | 2018-05-14 | 2018-10-08 | 2018-10-08 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-02-15 | COMP | 2019-03-25 | COMP | Rule 16 | 54 | 103 | 71 | 1 | 19 | 26 | 269
5231 | 2018-02-28 | 2018-05-14 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-02-05 | COMP | 2019-03-14 | COMP | Rule 16 | 54 | 147 | 10 | 1 | 28 | 27 | 262
5232 | 2018-02-28 | 2018-05-14 | 2019-01-15 | 2019-01-15 | COMP | 2019-01-24 | COMP | 2019-02-19 | COMP | 2019-02-15 | COMP | 2019-04-04 | COMP | Rule 16 | 54 | 169 | 7 | 18 | 0 | 33 | 277
5333 | 2018-02-28 | 2018-05-22 | 2018-10-27 | 2018-10-27 | COMP | 2019-05-20 | COMP | 2021-02-27 | REQD | 2019-05-24 | COMP | 2019-08-10 | COMP | Rule 15/16 | 60 | 111 | 139 |  |  |  | 366
5438 | 2018-02-28 | 2018-05-31 | 2018-08-09 | 2018-08-09 | COMP | 2018-09-27 | COMP | 2018-10-19 | COMP | 2018-12-07 | COMP | 2019-04-19 | COMP | Rule 16 | 66 | 50 | 35 | 17 | 33 | 92 | 288
5608 | 2018-02-28 | 2018-06-19 | 2018-10-18 | 2018-10-29 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2018-10-26 | COMP | 2019-02-26 | COMP | Rule 16 | 79 | 86 | 5 | 1 | 0 | 76 | 250
5719 | 2018-02-28 | 2018-06-26 | 2019-02-19 | 2019-02-19 | COMP | 2019-05-01 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-09-24 | COMP | Rule 15/16 | 84 | 162 | 52 | 7 | 1 | 96 | 397
6270 | 2018-02-28 | 2018-08-07 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-12 | COMP | 2018-11-01 | COMP | 2019-03-09 | COMP | 2019-03-25 | COMP | Rule 16 | 113 | 36 | 13 | 15 | 85 | 11 | 269
6829 | 2018-02-28 | 2018-09-12 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2020-02-25 | COMP | 2020-04-13 | COMP | Rule 16 | 138 | 61 | 30 | 1 | 274 | 35 | 534
6886 | 2018-02-28 | 2018-09-15 | 2018-12-05 | 2018-12-05 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2020-02-05 | COMP | 2020-03-04 | COMP | Rule 16 | 140 | 55 | 65 | 1 | 229 | 20 | 506
6887 | 2018-02-28 | 2018-09-15 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-11-19 | COMP | 2020-01-13 | COMP | Rule 16 | 140 | 65 | 36 | 1 | 197 | 36 | 471
6888 | 2018-02-28 | 2018-09-15 | 2019-01-01 | 2019-01-01 | COMP | 2019-02-11 | COMP | 2019-02-12 | COMP | 2020-03-31 | COMP | 2020-05-22 | COMP | Rule 16 | 140 | 72 | 28 | 2 | 285 | 39 | 563
7134 | 2018-02-28 | 2018-09-28 | 2018-12-06 | 2018-12-06 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-09-12 | COMP | 2019-10-01 | COMP | Rule 16 | 150 | 47 | 81 | 1 | 114 | 14 | 402
7348 | 2018-02-28 | 2018-10-10 | 2018-10-19 | 2018-10-19 | COMP | 2019-01-23 | COMP | 2019-11-25 | COMP | 2020-02-11 | COMP | 2020-03-05 | COMP | Rule 16 | 158 | 8 | 63 | 214 | 52 | 17 | 507
7512 | 2018-02-28 | 2018-10-18 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2018-12-11 | COMP | 2019-01-14 | COMP | Rule 16 | 164 | 35 | 9 | 1 | 0 | 16 | 221
8378 | 2018-02-28 | 2018-11-28 | 2019-01-24 | 2019-01-24 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-08-07 | COMP | 2019-09-06 | COMP | Rule 16 | 190 | 39 | 30 | 1 | 108 | 22 | 385
8640 | 2018-02-28 | 2018-12-13 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-01 | NOTN | 2019-03-27 | COMP | 2019-02-26 | NOTN | 2019-07-29 | COMP | Other | 201 | 52 |  | 20 |  |  | 357
9722 | 2018-02-28 | 2019-02-12 | 2019-04-16 | 2019-04-16 | COMP | 2019-04-29 | COMP | 2019-06-25 | COMP | 2019-06-18 | COMP | 2019-09-17 | COMP | Rule 16 | 241 | 45 | 10 | 41 | 0 | 59 | 392
17316 | 2018-02-28 | 2020-02-10 | 2020-03-20 | 2020-03-20 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2023-07-01 | INPR | 2021-03-10 | COMP | Rule 16 | 490 | 29 | 61 | 1 |  |  | 762
18127 | 2018-02-28 | 2020-03-11 | 2020-06-12 | 2020-06-12 | COMP | 2020-12-24 | COMP | 2021-01-04 | COMP | 2021-02-05 | COMP | 2021-05-03 | COMP | Rule 16 | 511 | 67 | 136 | 6 | 24 | 61 | 800
3200 | 2018-03-01 | 2018-03-21 | 2018-04-24 | 2018-04-24 | COMP | 2018-09-06 | COMP | 2018-09-18 | COMP | 2020-01-30 | COMP | 2020-02-19 | COMP | Rule 16 | 15 | 25 | 95 | 9 | 342 | 14 | 495
3465 | 2018-03-01 | 2018-05-01 | 2018-09-04 | 2018-09-04 | COMP | 2018-12-04 | COMP | 2019-01-17 | COMP | 2019-08-31 | INPR | 2019-05-13 | COMP | Rule 15/16 | 44 | 88 | 63 | 31 |  |  | 303
3513 | 2018-03-01 | 2018-05-09 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-09 | COMP | 2019-07-29 | COMP | 2019-11-23 | INPR | 2019-07-30 | COMP | Rule 16 | 50 | 227 | 26 | 56 |  |  | 357
3606 | 2018-03-01 | 2018-05-23 | 2018-07-20 | 2018-07-20 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-02-08 | COMP | 2019-06-21 | COMP | Rule 16 | 60 | 41 | 126 | 1 | 14 | 94 | 331
3655 | 2018-03-01 | 2018-06-05 | 2019-07-02 | 2019-07-02 | COMP | 2020-01-06 | COMP | 2020-01-09 | COMP | 2020-02-11 | COMP | 2020-07-21 | COMP | Rule 16 | 68 | 271 | 128 | 4 | 23 | 114 | 603
4138 | 2018-03-01 | 2019-03-26 | 2019-04-15 | 2019-04-15 | COMP | 2019-07-26 | COMP | 2019-07-31 | COMP | 2019-10-31 | COMP | 2019-12-11 | COMP | Rule 16 | 269 | 15 | 73 | 4 | 66 | 27 | 449
4744 | 2018-03-01 | 2018-03-26 | 2020-07-24 | 2020-07-24 | COMP | 2020-09-30 | COMP | 2021-01-21 | COMP | 2020-12-16 | COMP | 2021-01-22 | COMP | Rule 16 | 18 | 589 | 48 | 76 | 0 | 2 | 729
4745 | 2018-03-01 | 2018-03-26 | 2020-07-22 | 2020-10-27 | COMP | 2020-12-29 | COMP | 2021-02-02 | COMP | 2022-03-19 | INPR | 2021-02-24 | COMP | Rule 16 | 18 | 587 | 42 | 24 |  |  | 751
4746 | 2018-03-01 | 2018-03-26 | 2020-05-21 | 2020-05-21 | COMP | 2020-08-03 | COMP | 2020-10-14 | COMP | 2020-08-11 | COMP | 2020-12-01 | COMP | Rule 16 | 18 | 544 | 52 | 52 | 0 | 32 | 694
4749 | 2018-03-01 | 2018-03-26 | 2020-10-19 | 2020-10-19 | COMP | 2021-01-05 | COMP | 2021-02-22 | COMP | 2021-04-19 | COMP | 2021-05-09 | COMP | Rule 15/16 | 18 | 649 | 52 | 33 | 41 | 15 | 803
4751 | 2018-03-01 | 2018-03-26 | 2019-05-17 | 2019-05-17 | COMP | 2019-10-14 | COMP | 2019-10-28 | COMP | 2019-12-10 | COMP | 2020-02-12 | COMP | Rule 16 | 18 | 290 | 104 | 11 | 29 | 44 | 491
4755 | 2018-03-01 | 2018-03-26 | 2019-10-02 | 2019-10-02 | COMP | 2020-03-12 | COMP | 2020-05-31 | COMP | 2020-06-01 | COMP | 2020-08-06 | COMP | Rule 16 | 18 | 385 | 110 | 56 | 1 | 49 | 615
4788 | 2018-03-01 | 2018-03-30 | 2018-10-11 | 2018-10-11 | COMP | 2018-12-17 | COMP | 2019-01-22 | COMP | 2019-05-07 | COMP | 2019-06-07 | COMP | Rule 15/16 | 22 | 137 | 45 | 24 | 75 | 23 | 321
4873 | 2018-03-01 | 2018-04-09 | 2018-10-03 | 2018-10-08 | COMP | 2018-12-11 | COMP | 2019-02-25 | COMP | 2020-04-24 | COMP | 2020-05-06 | COMP | Rule 15/16 | 28 | 125 | 44 | 51 | 295 | 9 | 550
5111 | 2018-03-01 | 2018-04-30 | 2019-02-04 | 2019-02-04 | COMP | 2019-07-31 | COMP | 2019-09-05 | COMP | 2019-08-14 | COMP | 2019-10-16 | COMP | Rule 15/16 | 43 | 192 | 125 | 26 | 0 | 30 | 412
5112 | 2018-03-01 | 2018-04-30 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-21 | COMP | 2019-03-04 | COMP | 2019-08-06 | COMP | 2019-11-22 | COMP | Rule 15/16 | 43 | 132 | 13 | 68 | 110 | 77 | 438
5272 | 2018-03-01 | 2018-05-15 | 2018-08-27 | 2018-08-27 | COMP | 2018-10-17 | COMP | 2018-12-06 | COMP | 2018-10-30 | COMP | 2019-01-14 | COMP | Rule 16 | 54 | 73 | 37 | 34 | 0 | 26 | 220
5292 | 2018-03-01 | 2018-05-17 | 2018-06-15 | 2018-06-15 | COMP | 2018-09-12 | COMP | 2018-09-13 | COMP | 2018-12-03 | COMP | 2019-01-02 | COMP | Rule 16 | 56 | 21 | 62 | 2 | 55 | 21 | 212
6066 | 2018-03-01 | 2018-07-23 | 2018-09-29 | 2018-12-12 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2018-12-19 | COMP | 2019-03-11 | COMP | Rule 16 | 101 | 49 | 5 | 1 | 2 | 55 | 258
6367 | 2018-03-01 | 2018-08-13 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2019-04-21 | INPR | 2019-01-02 | COMP | Rule 16 | 116 | 44 | 24 | 1 |  |  | 212
6395 | 2018-03-01 | 2018-08-15 | 2018-12-26 | 2018-12-26 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-10-21 | INPR | 2019-03-19 | COMP | Rule 16 | 118 | 91 | 24 | 1 |  |  | 264
6540 | 2018-03-01 | 2018-08-27 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-01-25 | COMP | 2019-04-02 | COMP | Rule 16 | 126 | 79 | 24 | 1 | 2 | 47 | 274
7509 | 2018-03-01 | 2018-10-18 | 2018-12-28 | 2019-01-24 | COMP | 2019-02-22 | COMP | 2019-04-02 | COMP | 2019-03-27 | COMP | 2019-05-15 | COMP | Rule 16 | 163 | 48 | 21 | 28 | 0 | 32 | 305
7576 | 2018-03-01 | 2018-10-20 | 2019-03-17 | 2019-03-17 | COMP | 2019-02-11 | NOTN | 2019-03-17 | COMP | 2019-04-11 | COMP | 2019-05-10 | COMP | Other | 164 | 98 |  | 0 | 19 | 22 | 302
8633 | 2018-03-01 | 2018-12-13 | 2019-04-16 | 2019-08-29 | COMP | 2019-10-16 | COMP | 2019-10-25 | COMP | 2021-02-27 | INPR | 2019-11-14 | COMP | Rule 15/16 | 200 | 85 | 34 | 8 |  |  | 432
10169 | 2018-03-01 | 2019-03-05 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-17 | COMP | 2019-06-26 | COMP | 2019-08-06 | COMP | 2019-11-22 | COMP | Rule 16 | 254 | 47 | 8 | 28 | 29 | 77 | 438
11526 | 2018-03-01 | 2019-04-30 | 2019-11-06 | 2020-10-14 | COMP | 2021-02-05 | COMP | 2020-06-10 | COMP | 2021-02-25 | COMP | 2021-04-15 | COMP | Rule 15/16 | 294 | 134 | 77 |  | 179 | 36 | 787
11527 | 2018-03-01 | 2019-04-30 | 2019-11-06 | 2019-11-26 | COMP | 2020-01-27 | COMP | 2021-02-23 | COMP | 2021-02-25 | COMP | 2021-04-15 | COMP | Rule 15/16 | 294 | 134 | 40 | 272 | 3 | 36 | 787
3119 | 2018-03-02 | 2018-03-12 | 2018-08-28 | 2018-08-28 | COMP | 2018-09-27 | COMP | 2019-01-31 | COMP | 2021-02-27 | INPR | 2019-05-03 | COMP | Rule 16 | 7 | 120 | 22 | 85 |  |  | 296
3146 | 2018-03-02 | 2018-03-14 | 2018-07-18 | 2018-07-18 | COMP | 2018-08-23 | COMP | 2019-02-21 | COMP | 2019-02-20 | COMP | 2019-03-19 | COMP | Rule 16 | 9 | 89 | 27 | 123 | 0 | 19 | 263
3193 | 2018-03-02 | 2018-03-21 | 2018-09-23 | 2018-09-23 | COMP | 2018-12-06 | COMP | 2019-05-02 | COMP | 2019-09-21 | INPR | 2019-05-30 | COMP | Rule 16 | 14 | 130 | 51 | 102 |  |  | 314
3265 | 2018-03-02 | 2018-03-28 | 2018-08-17 | 2019-09-27 | COMP | 2020-01-08 | COMP | 2020-01-28 | COMP | 2020-01-08 | COMP | 2020-02-18 | COMP | Rule 16 | 19 | 101 | 69 | 14 | 0 | 15 | 493
3293 | 2018-03-02 | 2018-04-03 | 2018-08-21 | 2018-08-21 | COMP | 2018-09-18 | COMP | 2019-06-06 | COMP | 2019-11-05 | COMP | 2019-11-18 | COMP | Rule 16 | 23 | 99 | 20 | 180 | 107 | 9 | 433
3523 | 2018-03-02 | 2018-05-10 | 2018-12-10 | 2018-12-10 | COMP | 2019-03-22 | COMP | 2019-03-27 | COMP | 2020-05-28 | COMP | 2020-07-02 | COMP | Rule 16 | 50 | 147 | 71 | 4 | 296 | 26 | 589
4706 | 2018-03-02 | 2018-03-19 | 2018-09-25 | 2020-10-07 | COMP | 2020-10-29 | COMP | 2021-08-27 | COMP | 2021-10-19 | COMP | 2021-10-21 | COMP | Rule 15/16 | 12 | 134 | 17 | 208 | 37 | 3 | 918
4730 | 2018-03-02 | 2018-03-22 | 2018-08-16 | 2018-11-09 | COMP | 2018-12-12 | COMP | 2018-12-13 | COMP | 2018-12-05 | COMP | 2019-01-30 | COMP | Rule 15/16 | 15 | 104 | 21 | 2 | 0 | 32 | 230
4826 | 2018-03-02 | 2018-04-02 | 2018-09-06 | 2018-09-06 | COMP | 2018-12-31 | COMP | 2019-01-09 | COMP | 2019-08-19 | COMP | 2019-10-08 | COMP | Rule 16 | 22 | 111 | 79 | 7 | 155 | 36 | 405
5113 | 2018-03-02 | 2018-04-30 | 2018-07-31 | 2019-10-16 | COMP | 2020-02-13 | COMP | 2021-01-29 | COMP | 2021-03-29 | COMP | 2021-04-07 | COMP | Rule 16 | 42 | 65 | 81 | 243 | 41 | 8 | 780
5321 | 2018-03-02 | 2018-05-22 | 2018-07-19 | 2018-07-19 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2018-05-22 | COMP | 2021-10-06 | COMP | Rule 16 | 58 | 41 | 137 | 1 | 0 | 674 | 907
5765 | 2018-03-02 | 2018-07-02 | 2019-03-06 | 2019-07-24 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2021-01-30 | INPR | 2019-09-26 | COMP | Rule 16 | 86 | 169 | 2 | 1 |  |  | 397
6724 | 2018-03-02 | 2018-09-10 | 2019-09-23 | 2019-09-23 | COMP | 2019-09-30 | COMP | 2020-01-03 | COMP | 2020-07-20 | COMP | 2020-09-04 | COMP | Rule 15/16 | 134 | 261 | 6 | 65 | 139 | 35 | 635
6910 | 2018-03-02 | 2018-09-17 | 2018-12-17 | 2020-05-18 | COMP | 2020-08-10 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-10-28 | COMP | Rule 15/16 | 139 | 63 | 60 | 29 | 1 | 29 | 672
8332 | 2018-03-02 | 2018-11-27 | 2019-10-15 | 2021-12-01 | COMP | 2021-12-21 | COMP | 2021-05-06 | COMP | 2022-01-18 | COMP | 2022-04-14 | COMP | Rule 15/16 | 187 | 224 | 15 |  | 177 | 62 | 1038
9190 | 2018-03-02 | 2019-01-20 | 2019-05-06 | 2019-05-06 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2019-07-09 | COMP | 2019-07-11 | COMP | Rule 16 | 223 | 74 | 43 | 1 | 3 | 3 | 343
11770 | 2018-03-02 | 2019-05-10 | 2019-05-26 | 2019-05-26 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2020-09-26 | INPR | 2019-07-18 | COMP | Rule 16 | 301 | 11 | 3 | 1 |  |  | 348
14366 | 2018-03-02 | 2019-09-06 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2021-02-27 | INPR | 2020-01-28 | COMP | Rule 16 | 383 | 19 | 8 | 1 |  |  | 479
14401 | 2018-03-02 | 2019-09-09 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-09-17 | COMP | 2019-10-02 | COMP | Rule 16 | 384 | 18 | 8 | 1 | 0 |  | 401
3423 | 2018-03-03 | 2018-04-24 | 2018-07-31 | 2018-07-31 | COMP | 2019-05-21 | COMP | 2019-05-29 | COMP |  | INPR | 2020-05-22 | COMP | Rule 15/16 | 37 | 69 | 203 | 6 |  |  | 560
4728 | 2018-03-04 | 2018-03-21 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-24 | COMP | 2019-11-18 | COMP | 2019-12-20 | COMP | 2020-02-04 | COMP | Rule 15/16 | 13 | 255 | 22 | 145 | 23 | 30 | 483
3133 | 2018-03-05 | 2018-03-12 | 2018-08-17 | 2018-08-17 | COMP | 2018-09-18 | COMP | 2018-10-30 | COMP | 2019-01-22 | COMP | 2019-01-31 | COMP | Other | 6 | 113 | 22 | 31 | 55 | 8 | 230
3203 | 2018-03-05 | 2018-03-21 | 2018-05-30 | 2019-09-25 | COMP | 2019-10-14 | COMP | 2020-06-25 | COMP | 2020-06-09 | COMP | 2020-07-24 | COMP | Rule 15/16 | 13 | 50 | 14 | 176 | 0 | 22 | 604
3300 | 2018-03-05 | 2018-04-04 | 2018-08-27 | 2018-08-27 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2019-01-02 | COMP | Rule 16 | 23 | 102 | 60 | 1 | 1 | 28 | 210
3382 | 2018-03-05 | 2018-04-17 | 2018-09-21 | 2018-09-21 | COMP | 2019-02-05 | COMP | 2019-02-19 | COMP | 2019-03-21 | COMP | 2019-05-06 | COMP | Rule 15/16 | 32 | 111 | 92 | 10 | 23 | 33 | 296
3436 | 2018-03-05 | 2018-04-27 | 2018-08-21 | 2018-08-21 | COMP | 2019-02-25 | COMP | 2019-04-08 | COMP | 2020-08-24 | COMP | 2021-08-02 | COMP | Rule 15/16 | 40 | 81 | 127 | 31 | 350 | 236 | 860
3459 | 2018-03-05 | 2018-05-01 | 2019-02-04 | 2020-01-08 | COMP | 2020-01-27 | COMP | 2020-03-10 | COMP | 2020-03-23 | COMP | 2020-07-21 | COMP | Rule 15/16 | 42 | 191 | 13 | 31 | 10 | 86 | 601
3539 | 2018-03-05 | 2018-05-15 | 2019-05-09 | 2019-06-27 | COMP | 2020-02-14 | COMP | 2020-03-03 | COMP | 2020-02-25 | COMP | 2020-04-23 | COMP | Rule 15/16 | 52 | 248 | 159 | 12 | 0 | 38 | 539
3618 | 2018-03-05 | 2018-05-24 | 2018-08-15 | 2018-08-15 | COMP | 2018-10-05 | COMP | 2018-10-05 | COMP | 2018-11-07 | COMP | 2019-01-24 | COMP | Rule 16 | 59 | 58 | 37 | 1 | 24 | 51 | 225
3804 | 2018-03-05 | 2018-07-20 | 2018-10-30 | 2018-10-30 | COMP | 2018-12-27 | COMP | 2020-02-06 | COMP | 2020-03-11 | COMP | 2020-04-09 | COMP | Rule 16 | 98 | 72 | 39 | 279 | 24 | 22 | 529
4678 | 2018-03-05 | 2018-03-09 | 2018-03-09 | 2018-03-09 | COMP | 2018-05-14 | COMP | 2018-05-15 | COMP | 2018-11-05 | COMP | 2019-09-03 | COMP | Rule 16 | 5 | 1 | 47 | 2 | 122 | 207 | 379
4782 | 2018-03-05 | 2018-03-29 | 2018-07-18 | 2018-07-18 | COMP | 2019-01-18 | COMP | 2021-05-19 | COMP | 2021-05-19 | COMP | 2021-07-27 | COMP | Rule 15/16 | 19 | 78 | 127 | 588 | 1 | 48 | 856
4835 | 2018-03-05 | 2018-04-03 | 2018-07-26 | 2018-07-26 | COMP | 2018-10-17 | COMP | 2018-10-17 | COMP | 2018-11-20 | COMP | 2019-04-29 | COMP | Rule 16 | 22 | 81 | 59 | 1 | 24 | 109 | 291
4866 | 2018-03-05 | 2018-04-05 | 2018-06-05 | 2018-06-05 | COMP | 2018-08-28 | COMP | 2018-09-04 | COMP | 2018-09-25 | COMP | 2019-04-17 | COMP | Rule 16 | 24 | 43 | 60 | 5 | 16 | 140 | 283
4928 | 2018-03-05 | 2018-04-12 | 2018-06-14 | 2018-06-14 | COMP | 2018-09-06 | COMP | 2021-05-14 | COMP | 2021-06-21 | COMP | 2021-08-09 | COMP | Rule 16 | 29 | 45 | 59 | 676 | 26 | 35 | 865
4958 | 2018-03-05 | 2018-04-14 | 2018-10-29 | 2018-10-29 | COMP | 2020-11-20 | COMP | 2021-02-10 | COMP | 2021-02-10 | COMP | 2021-03-11 | COMP | Rule 16 | 30 | 138 | 520 | 54 | 1 | 21 | 760
4959 | 2018-03-05 | 2018-04-14 | 2018-10-29 | 2018-10-29 | COMP | 2021-06-25 | COMP | 2021-08-09 | COMP | 2022-05-18 | COMP | 2022-06-24 | COMP | Rule 16 | 30 | 138 | 668 | 31 | 197 | 26 | 1086
4969 | 2018-03-05 | 2018-04-17 | 2018-04-21 | 2018-04-21 | COMP | 2018-04-27 | COMP | 2020-02-19 | COMP | 2020-02-12 | COMP | 2020-03-06 | COMP | Rule 16 | 32 | 4 | 5 | 454 | 0 | 13 | 505
5096 | 2018-03-05 | 2018-05-04 | 2018-06-13 | 2018-06-21 | COMP | 2018-07-25 | COMP | 2018-07-25 | COMP | 2019-01-26 | COMP | 2019-03-12 | COMP | Rule 16 | 45 | 28 | 24 | 1 | 126 | 31 | 257
5204 | 2018-03-05 | 2018-05-10 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-02 | COMP | 2018-10-15 | COMP | 2019-01-28 | COMP | 2019-03-19 | COMP | Rule 16 | 49 | 94 | 8 | 10 | 70 | 36 | 262
5245 | 2018-03-05 | 2018-05-14 | 2018-08-04 | 2019-02-01 | COMP | 2019-02-12 | COMP | 2019-01-08 | COMP | 2019-03-01 | COMP | 2019-04-03 | COMP | Rule 16 | 51 | 58 | 8 |  | 37 | 24 | 273
5420 | 2018-03-05 | 2018-05-30 | 2018-10-11 | 2018-10-11 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-09-19 | COMP | 2019-10-28 | COMP | Rule 16 | 62 | 95 | 70 | 1 | 167 | 28 | 418
6104 | 2018-03-05 | 2018-07-26 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-05 | COMP | 2019-03-21 | COMP | 2019-03-06 | COMP | 2019-04-12 | COMP | Rule 16 | 102 | 54 | 19 | 92 | 0 | 17 | 280
6352 | 2018-03-05 | 2018-08-13 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-24 | COMP | 2019-05-20 | COMP |  | INPR | 2019-09-23 | COMP | Rule 15/16 | 114 | 174 | 24 |  |  |  | 393
6598 | 2018-03-05 | 2018-08-29 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-18 | COMP | 2019-02-19 | COMP | 2018-12-17 | COMP | 2019-03-07 | COMP | Rule 16 | 126 | 62 | 15 | 42 | 0 | 13 | 254
6793 | 2018-03-05 | 2018-09-11 | 2019-01-12 | 2019-01-12 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-09-12 | COMP | 2019-12-13 | COMP | Rule 16 | 134 | 84 | 99 | 1 | 71 | 64 | 449
7317 | 2018-03-05 | 2018-10-08 | 2018-12-19 | 2018-12-19 | COMP | 2019-05-03 | COMP | 2019-12-06 | COMP | 2020-01-22 | COMP | 2022-06-02 | COMP | Rule 15/16 | 153 | 50 | 94 | 150 | 31 | 598 | 1071
7397 | 2018-03-05 | 2018-10-11 | 2019-01-10 | 2019-01-10 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-04-06 | COMP | 2019-04-23 | COMP | Rule 16 | 156 | 61 | 30 | 1 | 31 | 12 | 287
8368 | 2018-03-05 | 2018-11-28 | 2019-03-31 | 2019-03-31 | COMP | 2020-10-01 | COMP | 2020-10-07 | COMP | 2021-06-01 | COMP | 2021-07-30 | COMP | Rule 16 | 187 | 84 | 382 | 5 | 162 | 43 | 859
9523 | 2018-03-05 | 2019-02-06 | 2019-05-29 | 2019-05-29 | COMP | 2019-08-01 | COMP | 2019-12-02 | COMP | 2019-11-21 | COMP | 2020-02-07 | COMP | Rule 15/16 | 234 | 79 | 46 | 84 | 0 | 47 | 486
9681 | 2018-03-05 | 2019-02-11 | 2019-04-22 | 2019-04-22 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2020-05-31 | INPR | 2019-11-06 | COMP | Rule 16 | 237 | 50 | 37 | 1 |  |  | 425
12771 | 2018-03-05 | 2019-06-21 | 2019-10-18 | 2019-10-18 | COMP | 2019-11-05 | COMP | 2022-06-15 | COMP | 2022-09-21 | COMP | 2023-01-27 | COMP | Rule 15/16 | 329 | 84 | 13 | 657 | 68 | 87 | 1233
14924 | 2018-03-05 | 2019-10-04 | 2020-03-23 | 2020-03-23 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-07-03 | COMP | 2020-07-22 | COMP | Rule 16 | 402 | 115 | 54 | 1 | 21 | 14 | 602
14989 | 2018-03-05 | 2019-10-08 | 2019-10-26 | 2019-10-26 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-12-06 | COMP | Rule 16 | 404 | 14 | 6 | 1 | 1 | 22 | 444
16020 | 2018-03-05 | 2019-12-05 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-15 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-04-17 | COMP | Rule 16 | 443 | 24 | 5 | 16 | 1 | 51 | 535
3085 | 2018-03-06 | 2018-03-06 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-24 | COMP | 2019-01-23 | COMP | 2020-04-06 | COMP | 2020-06-09 | COMP | Rule 15/16 | 1 | 156 | 49 | 20 | 303 | 46 | 570
3159 | 2018-03-06 | 2018-03-15 | 2018-06-13 | 2018-06-13 | COMP | 2019-06-24 | COMP | 2019-06-25 | COMP | 2019-10-01 | COMP | 2019-11-04 | COMP | Rule 16 | 8 | 64 | 259 | 2 | 69 | 25 | 422
3168 | 2018-03-06 | 2018-03-16 | 2018-09-01 | 2018-09-01 | COMP | 2018-09-27 | COMP | 2018-12-11 | COMP | 2019-01-04 | COMP | 2019-03-01 | COMP | Rule 15/16 | 9 | 119 | 18 | 51 | 17 | 39 | 249
3398 | 2018-03-06 | 2018-04-18 | 2018-07-14 | 2018-07-14 | COMP | 2018-08-15 | COMP | 2018-09-10 | COMP | 2018-10-01 | COMP | 2019-01-06 | COMP | Rule 16 | 32 | 61 | 23 | 18 | 16 | 65 | 211
3457 | 2018-03-06 | 2018-04-30 | 2019-01-17 | 2019-01-17 | COMP | 2019-02-06 | COMP | 2019-03-11 | COMP | 2019-08-23 | COMP | 2019-10-04 | COMP | Rule 15/16 | 40 | 181 | 14 | 23 | 118 | 30 | 401
3546 | 2018-03-06 | 2018-05-14 | 2018-12-30 | 2019-02-02 | COMP | 2019-02-26 | COMP | 2019-04-29 | COMP | 2019-05-06 | COMP | 2019-05-16 | COMP | Rule 15/16 | 50 | 158 | 16 | 45 | 6 | 9 | 303
3558 | 2018-03-06 | 2018-05-15 | 2018-10-24 | 2018-10-24 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | 2019-11-23 | INPR | 2019-07-29 | COMP | Rule 16 | 51 | 114 | 153 | 6 |  |  | 353
3568 | 2018-03-06 | 2018-05-17 | 2018-07-23 | 2018-07-23 | COMP | 2019-01-02 | COMP | 2019-01-02 | INPR | 2020-03-02 | COMP | 2020-03-04 | COMP | Other | 53 | 46 | 112 |  |  |  | 502
3691 | 2018-03-06 | 2018-06-08 | 2018-10-16 | 2018-10-16 | COMP | 2018-06-08 | NOTN | 2018-10-19 | NOTN | 2019-09-21 | INPR | 2019-06-03 | COMP | Rule 16 | 68 | 91 |  |  |  |  | 314
4690 | 2018-03-06 | 2018-03-13 | 2018-12-01 | 2018-12-01 | COMP | 2019-02-28 | COMP | 2019-02-28 | INPR | 2019-03-07 | COMP | 2019-04-12 | COMP | Rule 16 | 6 | 183 | 60 |  |  |  | 279
4878 | 2018-03-06 | 2018-04-09 | 2018-09-10 | 2018-09-10 | COMP | 2019-02-08 | NOTN | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-05-06 | COMP | Other | 25 | 108 |  | 104 | 1 | 61 | 295
4962 | 2018-03-06 | 2018-04-16 | 2018-08-24 | 2018-08-24 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2019-07-05 | COMP | 2019-09-27 | COMP | Rule 16 | 30 | 93 | 40 | 1 | 177 | 60 | 396
4999 | 2018-03-06 | 2018-04-23 | 2018-09-29 | 2018-09-29 | COMP | 2018-11-19 | COMP | 2018-12-04 | COMP | 2018-12-05 | COMP | 2019-01-18 | COMP | Rule 16 | 35 | 112 | 35 | 10 | 2 | 31 | 221
5020 | 2018-03-06 | 2018-04-24 | 2018-07-18 | 2018-07-18 | COMP | 2018-07-27 | COMP | 2019-04-08 | COMP | 2019-03-05 | COMP | 2019-04-11 | COMP | Rule 16 | 36 | 60 | 8 | 174 | 0 | 4 | 278
5056 | 2018-03-06 | 2018-04-26 | 2018-10-27 | 2018-10-27 | COMP | 2019-04-22 | COMP | 2019-04-24 | COMP | 2019-04-10 | COMP | 2019-05-03 | COMP | Other | 38 | 129 | 119 | 3 | 0 | 8 | 294
5083 | 2018-03-06 | 2018-04-30 | 2018-09-04 | 2018-09-04 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2022-01-12 | COMP | 2022-02-07 | COMP | Rule 16 | 40 | 89 | 356 | 1 | 490 | 18 | 989
5141 | 2018-03-06 | 2018-05-03 | 2018-08-04 | 2018-08-04 | COMP | 2018-09-04 | COMP | 2019-08-14 | COMP | 2019-08-05 | COMP | 2019-08-30 | COMP | Rule 16 | 43 | 65 | 21 | 238 | 0 | 13 | 377
5164 | 2018-03-06 | 2018-05-07 | 2018-08-24 | 2018-08-24 | COMP | 2018-10-18 | COMP | 2018-10-18 | COMP | 2019-07-21 | INPR | 2019-03-11 | COMP | Rule 16 | 45 | 78 | 39 | 1 |  |  | 255
5165 | 2018-03-06 | 2018-05-07 | 2018-07-18 | 2018-07-18 | COMP | 2018-10-18 | COMP | 2018-10-18 | COMP | 2018-12-24 | COMP | 2019-01-29 | COMP | Rule 16 | 45 | 51 | 66 | 1 | 45 | 24 | 227
5242 | 2018-03-06 | 2018-05-14 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-18 | COMP | 2018-10-18 | COMP | 2018-12-03 | COMP | 2019-01-28 | COMP | Rule 16 | 50 | 87 | 25 | 1 | 30 | 38 | 226
5243 | 2018-03-06 | 2018-05-14 | 2018-07-18 | 2018-07-18 | COMP | 2018-10-30 | COMP | 2018-12-14 | COMP | 2019-01-25 | COMP | 2019-02-26 | COMP | Rule 16 | 50 | 46 | 74 | 31 | 28 | 22 | 246
5337 | 2018-03-06 | 2018-05-22 | 2018-10-27 | 2018-11-16 | COMP | 2018-11-28 | COMP | 2018-12-03 | COMP | 2018-11-30 | COMP | 2019-01-24 | COMP | Rule 15/16 | 56 | 111 | 7 | 4 | 0 | 36 | 224
5384 | 2018-03-06 | 2018-05-25 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-20 | COMP | 2018-12-12 | COMP | 2019-11-24 | INPR | 2019-08-05 | COMP | Rule 16 | 59 | 110 | 15 | 15 |  |  | 358
5421 | 2018-03-06 | 2018-05-30 | 2018-10-11 | 2018-10-11 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP |  |  | 2019-10-10 | COMP | Rule 16 | 61 | 95 | 70 | 1 |  |  | 405
5693 | 2018-03-06 | 2018-06-26 | 2018-12-21 | 2018-12-21 | COMP | 2018-12-31 | COMP | 2019-03-20 | COMP | 2019-05-01 | COMP | 2019-07-05 | COMP | Rule 16 | 80 | 124 | 6 | 55 | 31 | 46 | 337
5743 | 2018-03-06 | 2018-06-28 | 2018-12-19 | 2019-02-12 | COMP | 2019-04-01 | COMP | 2020-01-24 | COMP | 2023-11-11 | INPR | 2020-06-08 | COMP | Rule 15/16 | 82 | 120 | 34 | 206 |  |  | 569
5816 | 2018-03-06 | 2018-07-05 | 2018-10-01 | 2018-11-28 | COMP | 2018-12-24 | COMP | 2018-12-24 | COMP | 2019-10-28 | COMP | 2019-12-20 | COMP | Rule 16 | 86 | 62 | 19 | 1 | 214 | 37 | 453
5868 | 2018-03-06 | 2018-07-09 | 2018-12-10 | 2019-02-20 | COMP | 2019-03-01 | COMP | 2019-03-25 | COMP | 2019-05-07 | COMP | 2019-05-22 | COMP | Rule 16 | 88 | 107 | 8 | 17 | 32 | 12 | 307
5921 | 2018-03-06 | 2018-07-11 | 2018-09-15 | 2018-09-15 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-02-15 | COMP | 2019-01-31 | COMP | Rule 16 | 90 | 47 | 65 | 1 | 40 |  | 229
6439 | 2018-03-06 | 2018-08-18 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-30 | COMP | 2019-06-06 | COMP | 2019-06-13 | COMP | 2019-11-21 | COMP | Rule 15/16 | 117 | 130 | 45 | 27 | 6 | 113 | 434
6760 | 2018-03-06 | 2018-09-11 | 2018-10-05 | 2018-10-05 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2019-02-26 | COMP | 2019-03-01 | COMP | Rule 16 | 133 | 19 | 29 | 1 | 68 | 4 | 249
7453 | 2018-03-06 | 2018-10-15 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-29 | COMP | 2019-05-07 | COMP | 2019-06-03 | COMP | 2019-07-25 | COMP | Rule 16 | 157 | 106 | 29 | 7 | 19 | 38 | 351
7588 | 2018-03-06 | 2018-10-22 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-25 | COMP | 2019-07-16 | COMP | 2019-11-07 | COMP | 2019-12-17 | COMP | Rule 15/16 | 162 | 86 | 19 | 80 | 82 | 26 | 450
7920 | 2018-03-06 | 2018-11-05 | 2019-03-20 | 2019-03-20 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-01-21 | COMP | 2020-02-11 | COMP | Rule 15/16 | 172 | 91 | 202 | 1 | 10 | 16 | 487
8144 | 2018-03-06 | 2018-11-17 | 2019-02-08 | 2019-02-08 | COMP | 2019-02-28 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2019-12-12 | COMP | Rule 16 | 180 | 55 | 14 | 188 | 1 | 13 | 447
11214 | 2018-03-06 | 2019-04-17 | 2019-07-29 | 2020-03-06 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-05-07 | COMP | 2020-05-08 | COMP | Rule 16 | 282 | 72 | 44 | 1 | 2 | 2 | 549
13829 | 2018-03-06 | 2019-08-12 | 2020-10-15 | 2020-10-15 | COMP | 2020-11-09 | COMP | 2021-02-10 | COMP | 2020-11-09 | COMP | 2021-04-26 | COMP | Rule 15/16 | 363 | 299 | 18 | 62 | 0 | 53 | 791
18345 | 2018-03-06 | 2020-03-20 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-18 | COMP | 2020-10-28 | COMP | 2020-11-20 | COMP | 2020-12-30 | COMP | Rule 16 | 514 | 116 | 14 | 29 | 17 | 26 | 711
3098 | 2018-03-07 | 2018-03-08 | 2018-03-19 | 2018-03-19 | COMP | 2019-06-03 | COMP | 2019-06-04 | COMP | 2019-06-18 | COMP | 2019-06-27 | COMP | Rule 16 | 2 | 8 | 305 | 2 | 11 | 8 | 331
3143 | 2018-03-07 | 2018-03-13 | 2018-04-25 | 2018-04-25 | COMP | 2018-04-25 | NOTN | 2018-06-14 | COMP | 2019-01-30 | COMP | 2019-04-23 | COMP | Other | 5 | 32 |  | 36 | 157 | 59 | 285
3206 | 2018-03-07 | 2018-03-22 | 2018-07-02 | 2018-07-02 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-03-12 | COMP | Rule 15/16 | 12 | 72 | 396 | 1 | 1 | 30 | 507
3379 | 2018-03-07 | 2018-04-16 | 2019-02-11 | 2019-02-25 | COMP | 2019-03-07 | COMP | 2019-03-12 | COMP | 2019-04-16 | COMP | 2019-04-24 | COMP | Rule 16 | 29 | 207 | 9 | 4 | 26 | 7 | 286
3505 | 2018-03-07 | 2018-05-08 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-28 | COMP | 2020-02-25 | COMP | 2020-05-11 | COMP | 2020-06-12 | COMP | Rule 16 | 45 | 281 | 50 | 122 | 55 | 24 | 572
3526 | 2018-03-07 | 2018-05-10 | 2018-09-11 | 2018-09-11 | COMP | 2018-11-08 | COMP | 2018-11-14 | COMP | 2019-01-02 | COMP | 2019-01-24 | COMP | Rule 15/16 | 47 | 86 | 43 | 4 | 32 | 16 | 223
3551 | 2018-03-07 | 2018-05-14 | 2018-05-24 | 2018-05-24 | COMP | 2018-06-12 | COMP | 2018-06-12 | COMP | 2019-03-05 | COMP | 2019-03-26 | COMP | Rule 16 | 49 | 9 | 13 | 1 | 182 | 16 | 265
3943 | 2018-03-07 | 2018-10-22 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-08 | COMP | 2019-10-02 | COMP |  |  | 2019-10-22 | COMP | Rule 16 | 161 | 77 | 38 | 125 |  |  | 412
4848 | 2018-03-07 | 2018-04-05 | 2018-06-21 | 2018-06-21 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2021-01-11 | COMP | 2021-03-09 | COMP | Rule 16 | 22 | 55 | 296 | 1 | 347 | 40 | 756
4903 | 2018-03-07 | 2018-04-10 | 2018-05-02 | 2018-05-02 | COMP | 2018-05-09 | COMP | 2018-05-09 | INPR | 2023-04-30 | CANC | 2021-11-19 | COMP | Rule 16 | 25 | 17 | 6 |  |  |  | 935
4974 | 2018-03-07 | 2018-04-17 | 2018-10-22 | 2018-10-22 | COMP | 2018-11-06 | COMP | 2018-11-06 | NOTN | 2019-09-01 | INPR | 2019-05-03 | COMP | Rule 16 | 30 | 132 | 12 |  |  |  | 293
4976 | 2018-03-07 | 2018-04-17 | 2018-10-11 | 2019-06-21 | COMP | 2019-07-02 | COMP | 2020-08-14 | COMP | 2021-03-22 | COMP | 2021-05-14 | COMP | Rule 15/16 | 30 | 125 | 8 | 284 | 149 | 40 | 804
5199 | 2018-03-07 | 2018-05-10 | 2018-08-02 | 2018-08-02 | COMP | 2018-09-12 | COMP | 2018-09-25 | COMP | 2019-04-22 | COMP | 2019-05-08 | COMP | Rule 16 | 47 | 59 | 29 | 10 | 143 | 13 | 296
5216 | 2018-03-07 | 2018-05-10 | 2018-11-01 | 2018-11-01 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-06-21 | COMP | 2019-07-24 | COMP | Rule 16 | 47 | 123 | 22 | 1 | 138 | 23 | 349
5339 | 2018-03-07 | 2018-05-24 | 2018-08-21 | 2018-09-03 | COMP | 2018-09-07 | COMP | 2019-05-15 | INPR | 2019-04-25 | COMP | 2019-05-15 | COMP | Rule 16 | 57 | 62 | 4 |  |  |  | 301
5348 | 2018-03-07 | 2018-05-23 | 2018-08-21 | 2018-10-05 | COMP | 2018-11-07 | COMP | 2018-12-06 | COMP | 2018-12-27 | COMP | 2019-02-04 | COMP | Rule 16 | 56 | 63 | 24 | 19 | 15 | 26 | 230
5688 | 2018-03-07 | 2018-06-26 | 2018-10-15 | 2018-10-15 | COMP | 2018-11-05 | COMP | 2019-01-12 | COMP | 2019-04-01 | COMP | 2019-04-13 | COMP | Rule 15/16 | 79 | 78 | 16 | 45 | 54 | 10 | 278
5815 | 2018-03-07 | 2018-07-05 | 2018-12-05 | 2020-02-15 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-06-09 | COMP | 2020-06-23 | COMP | Rule 15/16 | 85 | 106 | 16 | 1 | 65 | 11 | 579
5834 | 2018-03-07 | 2018-07-06 | 2018-12-05 | 2019-11-14 | COMP | 2020-05-13 | COMP | 2020-06-11 | COMP | 2021-10-23 | INPR | 2020-06-23 | COMP | Rule 16 | 86 | 105 | 124 | 21 |  |  | 579
5837 | 2018-03-07 | 2018-07-06 | 2018-10-05 | 2018-11-28 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-01-07 | COMP | 2019-03-13 | COMP | Rule 16 | 86 | 65 | 8 | 1 | 20 | 46 | 256
6095 | 2018-03-07 | 2018-07-25 | 2019-07-09 | 2019-07-09 | COMP | 2019-10-02 | COMP | 2020-01-30 | COMP | 2020-12-17 | COMP | 2021-05-06 | COMP | Rule 15/16 | 99 | 240 | 61 | 81 | 225 | 97 | 798
6384 | 2018-03-07 | 2018-08-14 | 2018-11-27 | 2018-11-27 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-04-03 | COMP | 2019-04-29 | COMP | Rule 16 | 113 | 72 | 46 | 1 | 43 | 19 | 289
6396 | 2018-03-07 | 2018-08-15 | 2018-10-30 | 2019-02-08 | COMP | 2019-03-01 | COMP | 2019-03-04 | COMP | 2019-03-19 | COMP | 2019-05-31 | COMP | Rule 15/16 | 114 | 54 | 15 | 2 | 12 | 53 | 312
6403 | 2018-03-07 | 2018-08-15 | 2018-09-17 | 2018-09-17 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-11-04 | COMP | 2019-11-21 | COMP | Rule 16 | 114 | 23 | 224 | 1 | 63 | 13 | 433
6860 | 2018-03-07 | 2018-09-14 | 2019-03-13 | 2019-03-13 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-08 | COMP | 2019-07-29 | COMP | Rule 16 | 135 | 122 | 63 | 1 | 20 | 16 | 352
7239 | 2018-03-07 | 2018-10-04 | 2018-10-24 | 2018-10-24 | COMP | 2019-02-01 | COMP | 2019-02-01 | INPR | 2019-09-22 | REQD | 2019-05-30 | COMP | Rule 16 | 149 | 15 | 67 |  |  |  | 311
7554 | 2018-03-07 | 2018-10-19 | 2019-02-16 | 2019-02-16 | COMP | 2019-05-01 | COMP | 2019-09-04 | COMP | 2020-01-08 | COMP | 2020-02-18 | COMP | Rule 16 | 160 | 80 | 52 | 88 | 86 | 28 | 490
8260 | 2018-03-07 | 2018-11-20 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-27 | COMP | 2019-04-12 | COMP | 2021-03-16 | COMP | 2021-03-30 | COMP | Rule 16 | 181 | 71 | 16 | 13 | 484 | 11 | 771
8471 | 2018-03-07 | 2018-12-04 | 2019-04-11 | 2019-04-11 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2020-11-02 | COMP | Rule 16 | 189 | 89 | 375 | 1 | 1 | 22 | 672
8676 | 2018-03-07 | 2018-12-14 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-08-27 | COMP | 2019-08-28 | COMP | Rule 15/16 | 197 | 92 | 13 | 1 | 74 | 2 | 374
10281 | 2018-03-07 | 2019-03-08 | 2019-05-18 | 2019-05-18 | COMP | 2019-06-06 | COMP | 2019-10-01 | COMP | 2019-10-15 | COMP | 2020-01-15 | COMP | Rule 16 | 253 | 51 | 13 | 82 | 11 | 62 | 468
10446 | 2018-03-07 | 2019-03-16 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2019-10-08 | COMP | 2019-11-13 | COMP | Rule 16 | 258 | 57 | 28 | 2 | 60 | 26 | 427
12378 | 2018-03-07 | 2019-06-04 | 2019-07-05 | 2019-07-05 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-12-29 | INPR | 2019-08-14 | COMP | Rule 16 | 314 | 23 | 10 | 1 |  |  | 364
13076 | 2018-03-07 | 2019-07-09 | 2019-12-03 | 2019-12-03 | COMP | 2020-03-25 | COMP | 2020-04-17 | COMP | 2020-04-16 | COMP | 2020-05-13 | COMP | Rule 16 | 338 | 102 | 78 | 18 | 0 | 19 | 551
16316 | 2018-03-07 | 2019-12-19 | 2020-03-06 | 2020-03-06 | COMP | 2020-05-15 | COMP | 2020-05-20 | COMP | 2020-09-21 | COMP | 2020-11-12 | COMP | Rule 15/16 | 451 | 53 | 51 | 4 | 87 | 38 | 679
3136 | 2018-03-08 | 2018-03-12 | 2018-09-14 | 2018-09-14 | COMP | 2018-12-04 | COMP | 2018-12-11 | COMP | 2019-05-14 | COMP | 2019-06-01 | COMP | Rule 16 | 3 | 132 | 55 | 6 | 107 | 13 | 311
3394 | 2018-03-08 | 2018-04-18 | 2018-08-20 | 2018-08-20 | COMP | 2018-10-01 | COMP | 2018-11-05 | COMP | 2018-10-09 | COMP | 2019-04-22 | COMP | Rule 15/16 | 30 | 87 | 30 | 26 | 0 | 114 | 283
3425 | 2018-03-08 | 2018-04-24 | 2020-03-10 | 2020-03-10 | COMP | 2021-05-28 | COMP | 2022-03-08 | COMP | 2022-03-07 | COMP | 2022-06-06 | COMP | Rule 15/16 | 34 | 471 | 310 | 195 | 0 | 64 | 1070
3561 | 2018-03-08 | 2018-05-16 | 2019-02-22 | 2019-02-22 | COMP | 2019-06-10 | COMP | 2020-08-04 | COMP | 2023-11-11 | INPR | 2020-12-13 | COMP | Rule 15/16 | 50 | 193 | 76 | 292 |  |  | 697
3647 | 2018-03-08 | 2018-06-01 | 2018-10-30 | 2018-10-30 | COMP | 2019-02-01 | COMP | 2019-02-05 | COMP | 2019-02-08 | COMP | 2019-07-24 | COMP | Rule 16 | 61 | 106 | 63 | 3 | 4 | 116 | 348
3696 | 2018-03-08 | 2018-06-12 | 2018-09-08 | 2018-09-08 | COMP | 2019-02-26 | COMP | 2019-04-01 | COMP | 2019-05-01 | COMP | 2019-05-20 | COMP | Other | 68 | 62 | 115 | 25 | 23 | 14 | 303
3789 | 2018-03-08 | 2018-07-14 | 2018-12-21 | 2018-12-21 | COMP | 2019-01-17 | NOTN | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-03-07 | COMP | Other | 90 | 111 |  | 18 | 1 | 34 | 251
4707 | 2018-03-08 | 2018-03-19 | 2018-09-07 | 2018-09-25 | COMP | 2018-10-09 | COMP | 2019-06-26 | COMP | 2019-07-12 | COMP | 2019-09-06 | COMP | Rule 15/16 | 8 | 122 | 11 | 179 | 12 | 40 | 379
4711 | 2018-03-08 | 2018-03-19 | 2018-05-22 | 2018-05-22 | COMP | 2018-06-13 | COMP | 2018-06-13 | COMP | 2020-01-22 | COMP | 2020-02-27 | COMP | Rule 15/16 | 8 | 47 | 16 | 1 | 403 | 26 | 496
5003 | 2018-03-08 | 2018-04-23 | 2018-06-20 | 2019-02-05 | COMP | 2019-02-04 | NOTN | 2019-02-05 | COMP | 2020-05-12 | COMP | 2020-06-08 | COMP | Rule 16 | 33 | 42 |  | 1 | 320 | 19 | 567
5058 | 2018-03-08 | 2018-04-26 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-08 | COMP | 2019-01-08 | COMP | 2018-11-13 | COMP | 2019-01-04 | COMP | Rule 16 | 36 | 124 | 15 | 39 | 0 |  | 209
5525 | 2018-03-08 | 2018-06-07 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-08 | COMP | 2019-01-08 | COMP | 2019-01-28 | COMP | 2019-04-26 | COMP | Rule 16 | 65 | 93 | 17 | 39 | 14 | 64 | 287
5536 | 2018-03-08 | 2018-06-12 | 2018-09-28 | 2018-09-28 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-04-19 | COMP | 2019-05-09 | COMP | Rule 16 | 68 | 77 | 71 | 1 | 69 | 15 | 296
5565 | 2018-03-08 | 2018-06-14 | 2018-09-25 | 2018-12-04 | COMP | 2019-04-25 | COMP | 2018-11-16 | COMP | 2019-05-07 | COMP | 2019-11-05 | COMP | Rule 16 | 70 | 72 | 99 |  | 117 | 128 | 421
5600 | 2018-03-08 | 2018-06-18 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-04 | COMP | 2018-12-17 | COMP | 2019-11-05 | COMP | 2020-01-23 | COMP | Rule 15/16 | 72 | 86 | 32 | 10 | 225 | 52 | 472
6278 | 2018-03-08 | 2018-08-07 | 2018-12-05 | 2018-12-05 | COMP | 2019-03-26 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-05-07 | COMP | Rule 16 | 107 | 83 | 76 | 2 | 1 | 30 | 294
7347 | 2018-03-08 | 2018-10-10 | 2019-01-25 | 2019-01-25 | COMP | 2019-06-11 | COMP | 2020-03-09 | COMP | 2020-02-18 | COMP | 2020-04-22 | COMP | Rule 15/16 | 152 | 72 | 96 | 186 | 0 | 33 | 535
9255 | 2018-03-08 | 2019-01-25 | 2019-03-31 | 2019-03-31 | COMP | 2019-06-03 | COMP | 2019-06-04 | COMP | 2019-07-03 | COMP | 2019-08-30 | COMP | Rule 16 | 223 | 45 | 45 | 2 | 22 | 42 | 375
9400 | 2018-03-08 | 2019-02-02 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-27 | COMP | 2019-07-03 | COMP | 2019-12-29 | INPR | 2019-09-12 | COMP | Rule 16 | 228 | 81 | 22 | 5 |  |  | 383
3108 | 2018-03-09 | 2018-03-09 | 2018-03-20 | 2018-03-20 | COMP | 2018-04-06 | COMP | 2018-05-08 | COMP | 2018-04-04 | COMP | 2022-05-13 | COMP | Rule 16 | 1 | 8 | 14 | 23 | 0 | 1012 | 1054
3144 | 2018-03-09 | 2018-03-14 | 2018-08-28 | 2019-09-03 | COMP | 2019-11-12 | COMP | 2019-11-12 | INPR | 2019-11-14 | COMP | 2019-11-20 | COMP | Rule 16 | 4 | 118 | 50 |  |  |  | 430
3176 | 2018-03-09 | 2018-03-19 | 2018-11-02 | 2018-11-02 | COMP | 2019-05-02 | COMP | 2019-06-01 | COMP | 2019-07-15 | COMP | 2019-12-10 | COMP | Rule 15/16 | 7 | 162 | 123 | 21 | 30 | 103 | 442
3183 | 2018-03-09 | 2018-03-19 | 2018-04-24 | 2018-04-24 | COMP | 2018-04-27 | COMP | 2018-04-30 | COMP | 2020-01-23 | COMP | 2020-02-05 | COMP | Rule 16 | 7 | 27 | 4 | 2 | 435 | 10 | 480
3207 | 2018-03-09 | 2018-03-22 | 2018-03-29 | 2018-03-29 | COMP | 2018-05-11 | COMP | 2018-05-11 | COMP | 2020-04-25 | INPR | 2019-12-30 | COMP | Rule 16 | 10 | 6 | 32 | 1 |  |  | 455
3305 | 2018-03-09 | 2018-04-05 | 2018-08-08 | 2019-10-07 | COMP | 2019-11-21 | COMP | 2020-02-18 | COMP | 2020-05-22 | COMP | 2020-06-16 | COMP | Rule 15/16 | 20 | 88 | 33 | 58 | 69 | 17 | 572
3325 | 2018-03-09 | 2018-04-09 | 2018-09-07 | 2018-09-07 | COMP | 2019-04-09 | COMP | 2019-04-11 | COMP | 2019-11-19 | COMP | 2020-01-03 | COMP | Rule 16 | 22 | 107 | 146 | 3 | 155 | 30 | 458
3357 | 2018-03-09 | 2018-04-11 | 2018-06-03 | 2018-06-03 | COMP | 2018-08-13 | COMP | 2018-12-17 | COMP | 2018-12-27 | COMP | 2019-01-09 | COMP | Rule 16 | 24 | 37 | 50 | 87 | 8 | 9 | 211
4752 | 2018-03-09 | 2018-03-26 | 2020-07-22 | 2020-07-22 | COMP | 2021-02-22 | COMP | 2021-05-21 | COMP | 2021-05-28 | COMP | 2021-07-26 | COMP | Rule 16 | 12 | 587 | 146 | 65 | 6 | 40 | 851
4753 | 2018-03-09 | 2018-03-26 | 2019-08-06 | 2019-08-06 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP |  | INPR | 2021-10-01 | COMP | Rule 15/16 | 12 | 345 | 141 | 1 |  |  | 899
4757 | 2018-03-09 | 2018-03-26 | 2021-01-29 | 2021-08-30 | COMP | 2021-11-01 | COMP | 2022-01-25 | COMP | 2023-04-15 | INPR | 2022-01-27 | COMP | Rule 16 | 12 | 717 | 45 | 58 |  |  | 979
4846 | 2018-03-09 | 2018-04-04 | 2018-10-08 | 2018-10-08 | COMP | 2018-04-04 | NOTN | 2019-03-12 | COMP | 2018-10-08 | COMP | 2019-04-26 | COMP | Other | 19 | 131 |  | 105 | 0 | 34 | 286
4940 | 2018-03-09 | 2018-04-13 | 2018-06-28 | 2018-06-28 | COMP | 2018-08-23 | COMP | 2018-08-23 | COMP | 2019-10-21 | INPR | 2019-06-22 | COMP | Rule 16 | 26 | 54 | 40 | 1 |  |  | 325
5124 | 2018-03-09 | 2018-05-02 | 2018-07-31 | 2018-09-12 | COMP | 2018-10-10 | COMP | 2019-06-20 | COMP | 2021-02-27 | INPR | 2019-12-24 | COMP | Rule 16 | 39 | 63 | 21 | 174 |  |  | 452
5167 | 2018-03-09 | 2018-05-07 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-13 | COMP | 2018-12-14 | COMP | 2018-12-13 | COMP | 2019-01-14 | COMP | Rule 16 | 42 | 138 | 16 | 2 | 0 | 20 | 214
5219 | 2018-03-09 | 2018-05-11 | 2018-08-01 | 2018-10-19 | COMP | 2018-11-20 | COMP | 2019-04-04 | COMP | 2019-03-06 | COMP | 2019-04-24 | COMP | Rule 16 | 46 | 57 | 22 | 92 | 0 | 15 | 284
5246 | 2018-03-09 | 2018-05-14 | 2018-07-18 | 2018-07-18 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-05-31 | COMP | 2019-07-24 | COMP | Rule 16 | 47 | 46 | 216 | 1 | 4 | 38 | 347
5448 | 2018-03-09 | 2018-06-01 | 2019-03-14 | 2019-03-14 | COMP | 2020-01-21 | NOTN | 2020-08-14 | COMP | 2020-01-21 | COMP | 2020-10-22 | COMP | Other | 60 | 196 |  | 361 | 0 | 49 | 663
5472 | 2018-03-09 | 2018-06-01 | 2018-11-16 | 2018-11-16 | COMP | 2020-10-28 | COMP | 2021-04-15 | COMP | 2021-04-15 | COMP | 2021-05-19 | COMP | Rule 16 | 60 | 118 | 491 | 115 | 1 | 25 | 805
5534 | 2018-03-09 | 2018-06-11 | 2018-07-10 | 2018-07-10 | COMP | 2018-08-20 | COMP | 2018-10-22 | COMP | 2019-04-01 | COMP | 2019-05-10 | COMP | Rule 16 | 66 | 21 | 30 | 45 | 109 | 30 | 296
5776 | 2018-03-09 | 2018-07-02 | 2018-10-09 | 2018-10-09 | COMP | 2018-11-14 | COMP | 2018-11-15 | COMP | 2019-02-04 | COMP | 2019-02-27 | COMP | Rule 16 | 81 | 70 | 26 | 2 | 53 | 17 | 244
6165 | 2018-03-09 | 2018-08-01 | 2018-10-24 | 2018-10-24 | COMP | 2019-03-14 | COMP | 2019-03-15 | COMP | 2019-04-11 | COMP | 2019-04-24 | COMP | Rule 16 | 102 | 60 | 95 | 2 | 20 | 10 | 284
6366 | 2018-03-09 | 2018-08-13 | 2019-01-19 | 2019-01-19 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-03-01 | COMP | 2019-04-05 | COMP | Rule 15/16 | 110 | 109 | 10 | 1 | 19 | 26 | 271
6470 | 2018-03-09 | 2018-08-20 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-04 | COMP | 2018-12-06 | COMP | 2018-12-18 | COMP | 2019-01-29 | COMP | Rule 16 | 115 | 39 | 35 | 3 | 9 | 28 | 224
6649 | 2018-03-09 | 2018-09-04 | 2019-04-27 | 2020-01-23 | COMP | 2020-02-25 | COMP | 2020-09-03 | COMP | 2020-09-14 | COMP | 2020-10-20 | COMP | Rule 15/16 | 125 | 162 | 23 | 137 | 7 | 27 | 661
6804 | 2018-03-09 | 2018-09-11 | 2018-12-10 | 2018-12-19 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-02-26 | COMP | 2019-05-03 | COMP | Rule 16 | 130 | 62 | 10 | 1 | 37 | 49 | 291
7640 | 2018-03-09 | 2018-10-23 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-03-22 | COMP | 2019-04-09 | COMP | Rule 16 | 160 | 39 | 44 | 1 | 21 | 13 | 273
9291 | 2018-03-09 | 2019-01-28 | 2019-02-28 | 2021-04-12 | COMP | 2021-05-06 | COMP | 2022-08-18 | COMP | 2022-08-16 | COMP | 2022-10-01 | COMP | Rule 15/16 | 223 | 23 | 19 | 325 | 0 | 31 | 1150
12931 | 2018-03-09 | 2019-07-01 | 2019-10-14 | 2019-10-14 | COMP | 2019-12-27 | COMP | 2020-05-21 | COMP | 2020-05-23 | COMP | 2020-06-19 | COMP | Rule 15/16 | 331 | 74 | 51 | 102 | 2 | 19 | 575
4679 | 2018-03-10 | 2018-03-10 | 2018-09-01 | 2018-09-01 | COMP | 2018-09-14 | COMP | 2018-09-14 | INPR | 2020-09-29 | COMP | 2020-10-15 | COMP | Rule 16 | 0 | 123 | 9 |  |  |  | 657
6325 | 2018-03-10 | 2018-08-10 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-29 | COMP | 2021-02-27 | REQD | 2021-02-27 | REQD | 2019-11-15 | COMP | Rule 15/16 | 108 | 149 | 52 |  |  |  | 426
3156 | 2018-03-11 | 2018-03-16 | 2018-10-01 | 2019-06-14 | COMP | 2019-08-29 | COMP | 2019-09-17 | NOTN | 2019-09-30 | COMP | 2019-09-25 | COMP | Rule 16 | 5 | 139 | 54 |  |  |  | 390
3418 | 2018-03-11 | 2018-04-23 | 2018-10-12 | 2018-10-12 | COMP | 2018-10-30 | COMP | 2018-12-17 | COMP | 2018-12-12 | COMP | 2019-01-25 | COMP | Rule 15/16 | 31 | 122 | 13 | 32 | 0 | 27 | 221
3948 | 2018-03-11 | 2018-10-24 | 2019-01-23 | 2019-01-23 | COMP | 2019-03-05 | COMP | 2019-03-06 | COMP | 2020-06-02 | COMP | 2020-08-05 | COMP | Rule 15/16 | 160 | 60 | 29 | 2 | 314 | 47 | 607
3257 | 2018-03-12 | 2018-03-28 | 2018-11-01 | 2018-11-01 | COMP | 2018-11-08 | COMP | 2019-09-11 | COMP | 2019-06-11 | COMP | 2019-10-03 | COMP | Rule 15/16 | 13 | 154 | 6 | 210 | 0 | 17 | 396
3260 | 2018-03-12 | 2018-03-28 | 2019-02-10 | 2019-05-24 | COMP | 2019-06-20 | COMP | 2019-08-14 | COMP | 2019-08-06 | COMP | 2019-09-25 | COMP | Rule 15/16 | 13 | 219 | 19 | 39 | 0 | 30 | 390
3289 | 2018-03-12 | 2018-04-02 | 2018-06-17 | 2018-06-17 | COMP | 2018-07-05 | NOTN | 2018-08-22 | COMP | 2018-04-02 | COMP | 2019-01-29 | COMP | Other | 16 | 54 |  | 47 | 0 | 108 | 223
3290 | 2018-03-12 | 2018-04-02 | 2019-02-15 | 2019-02-15 | COMP | 2019-04-12 | NOTN | 2019-04-12 | COMP | 2018-04-02 | COMP | 2019-05-09 | COMP | Other | 16 | 221 |  | 40 | 0 | 20 | 294
3317 | 2018-03-12 | 2018-04-06 | 2018-07-10 | 2018-07-10 | COMP | 2018-07-20 | COMP | 2018-08-13 | COMP | 2018-12-05 | COMP | 2019-01-02 | COMP | Rule 16 | 20 | 66 | 9 | 17 | 79 | 19 | 205
3555 | 2018-03-12 | 2018-05-15 | 2018-11-04 | 2018-11-04 | COMP | 2018-12-04 | COMP | 2018-12-11 | COMP | 2019-05-06 | COMP | 2019-06-24 | COMP | Rule 15/16 | 47 | 121 | 19 | 6 | 101 | 35 | 325
3702 | 2018-03-12 | 2018-06-12 | 2018-09-28 | 2018-09-28 | COMP | 2018-10-19 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-06-05 | COMP | Rule 15/16 | 66 | 77 | 16 | 46 | 1 | 111 | 312
3830 | 2018-03-12 | 2018-08-04 | 2019-02-21 | 2019-02-21 | COMP | 2019-02-21 | NOTN | 2019-02-21 | COMP | 2019-02-22 | COMP | 2019-02-26 | COMP | Rule 16 | 103 | 136 |  | 1 | 2 | 3 | 242
4811 | 2018-03-12 | 2018-03-31 | 2018-09-19 | 2019-07-08 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2020-02-07 | COMP | 2020-03-10 | COMP | Rule 16 | 15 | 120 | 8 | 1 | 141 | 22 | 502
4950 | 2018-03-12 | 2018-04-13 | 2018-07-09 | 2018-07-26 | COMP | 2018-08-22 | COMP | 2018-09-17 | COMP | 2018-10-02 | COMP | 2019-04-09 | COMP | Rule 16 | 25 | 60 | 20 | 18 | 12 | 129 | 272
4963 | 2018-03-12 | 2018-04-16 | 2019-02-04 | 2019-02-04 | COMP | 2020-09-17 | NOTN | 2020-10-26 | COMP | 2020-12-15 | COMP | 2020-12-16 | COMP | Other | 26 | 202 |  | 438 | 34 | 2 | 698
5077 | 2018-03-12 | 2018-04-28 | 2018-09-04 | 2018-09-04 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-02-16 | COMP | 2019-03-20 | COMP | Rule 16 | 35 | 89 | 110 | 1 | 4 | 22 | 258
5079 | 2018-03-12 | 2018-04-28 | 2018-09-04 | 2018-09-04 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2020-02-05 | COMP | 2020-03-05 | COMP | Rule 16 | 35 | 89 | 112 | 1 | 245 | 21 | 499
5229 | 2018-03-12 | 2018-05-14 | 2019-06-20 | 2019-06-20 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-01-29 | COMP | 2020-03-03 | COMP | Rule 15/16 | 46 | 278 | 111 | 1 | 42 | 24 | 497
5557 | 2018-03-12 | 2018-06-14 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-01-09 | COMP | 2019-03-06 | COMP | Rule 16 | 68 | 78 | 20 | 1 | 47 | 39 | 248
5637 | 2018-03-12 | 2018-06-22 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-15 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-12 | COMP | Rule 15/16 | 74 | 124 | 40 | 188 | 1 | 21 | 443
5802 | 2018-03-12 | 2018-07-03 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-12 | COMP | 2019-02-25 | COMP | 2019-02-11 | COMP | 2019-04-19 | COMP | Rule 15/16 | 81 | 142 | 12 | 9 | 0 | 40 | 280
5828 | 2018-03-12 | 2018-07-06 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-02-12 | COMP | 2019-02-18 | COMP | Rule 16 | 83 | 73 | 31 | 1 | 49 | 4 | 236
6117 | 2018-03-12 | 2018-07-27 | 2018-10-16 | 2018-10-16 | COMP | 2018-12-10 | COMP | 2021-10-12 | COMP | 2021-09-08 | COMP | 2021-10-06 | COMP | Rule 15/16 | 98 | 57 | 37 | 716 | 0 |  | 901
6294 | 2018-03-12 | 2018-08-08 | 2019-01-23 | 2019-05-10 | COMP | 2019-05-17 | COMP | 2020-04-03 | COMP | 2020-03-02 | COMP | 2020-06-19 | COMP | Rule 15/16 | 106 | 114 | 6 | 221 | 0 | 55 | 574
6828 | 2018-03-12 | 2018-09-12 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-04-02 | COMP | 2019-05-13 | COMP | Rule 16 | 130 | 58 | 34 | 1 | 48 | 30 | 296
7290 | 2018-03-12 | 2018-10-06 | 2018-12-07 | 2018-12-07 | COMP | 2018-12-17 | COMP | 2019-03-20 | COMP | 2019-02-15 | COMP | 2019-05-01 | COMP | Rule 15/16 | 147 | 42 | 7 | 64 | 0 | 31 | 288
7623 | 2018-03-12 | 2018-10-23 | 2018-11-27 | 2018-11-27 | COMP | 2018-11-30 | COMP | 2018-12-18 | COMP | 2018-12-06 | COMP | 2019-01-28 | COMP | Rule 15/16 | 159 | 23 | 4 | 13 | 0 | 27 | 222
8797 | 2018-03-12 | 2018-12-28 | 2019-05-12 | 2019-05-12 | COMP | 2019-05-29 | COMP | 2019-09-06 | COMP | 2021-01-06 | COMP | 2021-02-05 | COMP | Other | 203 | 93 | 12 | 71 | 335 | 22 | 732
10028 | 2018-03-12 | 2019-02-27 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-09 | COMP | 2019-05-23 | COMP | 2019-11-12 | COMP | 2020-01-06 | COMP | Rule 16 | 243 | 19 | 12 | 33 | 120 | 36 | 458
3141 | 2018-03-13 | 2018-03-13 | 2018-04-02 | 2018-04-02 | COMP | 2020-03-25 | COMP | 2020-09-17 | INPR | 2020-09-21 | COMP | 2020-09-28 | COMP | Rule 16 | 1 | 15 | 498 |  |  |  | 643
3181 | 2018-03-13 | 2018-03-20 | 2018-04-24 | 2018-04-24 | COMP | 2018-05-10 | COMP | 2018-06-06 | COMP | 2019-08-28 | COMP | 2019-09-23 | COMP | Other | 6 | 26 | 13 | 19 | 310 | 18 | 387
3269 | 2018-03-13 | 2018-03-29 | 2018-07-16 | 2019-06-04 | COMP | 2020-02-26 | COMP | 2020-04-16 | COMP | 2020-05-18 | COMP | 2020-07-10 | COMP | Rule 15/16 | 13 | 76 | 183 | 37 | 23 | 39 | 588
3270 | 2018-03-13 | 2018-03-29 | 2018-07-17 | 2019-06-03 | COMP | 2019-08-14 | COMP | 2019-08-20 | COMP | 2023-04-15 | INPR | 2020-07-10 | COMP | Rule 16 | 13 | 77 | 52 | 5 |  |  | 588
3331 | 2018-03-13 | 2018-04-09 | 2018-07-18 | 2018-06-11 | COMP | 2018-09-04 | COMP | 2018-09-27 | COMP | 2019-03-30 | COMP | 2019-06-03 | COMP | Rule 16 | 20 | 71 | 60 | 18 | 125 | 45 | 309
3560 | 2018-03-13 | 2018-05-16 | 2018-10-05 | 2018-10-05 | COMP | 2018-11-16 | COMP | 2018-11-28 | COMP | 2019-02-07 | COMP | 2019-03-08 | COMP | Rule 16 | 47 | 100 | 30 | 7 | 49 | 21 | 249
4865 | 2018-03-13 | 2018-04-05 | 2018-06-19 | 2018-06-19 | COMP | 2018-09-11 | COMP | 2018-09-11 | COMP | 2019-06-11 | COMP | 2019-07-23 | COMP | Rule 15/16 | 18 | 53 | 59 | 1 | 188 | 30 | 344
4871 | 2018-03-13 | 2018-04-06 | 2018-10-24 | 2018-10-24 | COMP | 2019-06-07 | COMP | 2019-07-08 | COMP | 2020-07-27 | COMP | 2020-10-16 | COMP | Rule 16 | 19 | 141 | 155 | 21 | 267 | 59 | 657
4935 | 2018-03-13 | 2018-04-13 | 2018-10-24 | 2018-10-24 | COMP | 2019-07-30 | COMP | 2019-07-31 | COMP | 2020-05-26 | COMP | 2020-06-03 | COMP | Rule 16 | 24 | 136 | 191 | 2 | 206 | 7 | 561
4991 | 2018-03-13 | 2018-04-19 | 2018-05-17 | 2018-05-17 | COMP | 2018-07-10 | COMP | 2018-07-10 | COMP | 2020-03-21 | INPR | 2019-12-07 | COMP | Rule 16 | 28 | 21 | 37 | 1 |  |  | 438
5175 | 2018-03-13 | 2018-05-08 | 2018-08-24 | 2018-12-05 | COMP | 2018-12-07 | COMP | 2019-01-02 | COMP | 2019-02-23 | COMP | 2019-04-04 | COMP | Rule 16 | 41 | 77 | 3 | 17 | 36 | 29 | 268
5215 | 2018-03-13 | 2018-05-10 | 2018-11-02 | 2018-11-02 | COMP | 2019-07-01 | COMP | 2019-08-12 | COMP | 2019-07-23 | COMP | 2019-09-06 | COMP | Rule 15/16 | 43 | 124 | 164 | 30 | 0 | 19 | 376
5240 | 2018-03-13 | 2018-05-14 | 2018-08-28 | 2018-08-28 | COMP | 2018-10-05 | COMP | 2018-10-05 | COMP | 2019-05-28 | COMP | 2019-07-11 | COMP | Rule 16 | 45 | 75 | 28 | 1 | 160 | 32 | 336
5247 | 2018-03-13 | 2018-05-14 | 2018-07-18 | 2018-07-18 | COMP | 2018-12-28 | COMP | 2019-03-01 | COMP | 2019-02-01 | COMP | 2019-03-20 | COMP | Rule 16 | 45 | 46 | 113 | 43 | 0 | 14 | 257
5509 | 2018-03-13 | 2018-06-05 | 2018-09-19 | 2018-09-25 | COMP | 2018-10-25 | COMP | 2019-07-09 | INPR | 2019-08-07 | COMP | 2019-09-07 | COMP | Rule 15/16 | 60 | 75 | 23 |  |  |  | 376
5645 | 2018-03-13 | 2018-06-22 | 2018-07-16 | 2019-11-12 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-01-28 | COMP | 2022-03-26 | COMP | Rule 16 | 73 | 16 | 11 | 1 | 41 | 546 | 1017
6741 | 2018-03-13 | 2018-09-10 | 2018-10-04 | 2018-10-04 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2020-06-29 | COMP | 2020-07-21 | COMP | Rule 16 | 127 | 19 | 239 | 1 | 197 | 17 | 595
6970 | 2018-03-13 | 2018-09-20 | 2018-10-03 | 2018-10-22 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2018-10-29 | COMP | 2019-12-18 | COMP | Rule 16 | 135 | 10 | 5 | 1 | 2 | 285 | 446
7948 | 2018-03-13 | 2018-11-08 | 2019-01-24 | 2019-01-24 | COMP | 2019-05-21 | COMP | 2019-06-11 | COMP | 2019-05-21 | COMP | 2019-07-02 | COMP | Rule 16 | 170 | 50 | 83 | 15 | 0 | 16 | 330
8255 | 2018-03-13 | 2018-11-21 | 2018-12-12 | 2019-04-09 | COMP | 2019-04-26 | COMP | 2019-05-03 | COMP | 2019-05-15 | COMP | 2019-07-26 | COMP | Rule 16 | 178 | 14 | 14 | 6 | 9 | 51 | 347
8817 | 2018-03-13 | 2018-12-31 | 2019-03-30 | 2019-03-30 | COMP | 2019-05-23 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-08-21 | COMP | Rule 16 | 203 | 62 | 39 | 44 | 1 | 20 | 365
9018 | 2018-03-13 | 2019-01-12 | 2019-02-07 | 2019-06-19 | COMP | 2019-07-15 | COMP | 2019-08-01 | COMP | 2019-07-16 | COMP | 2019-08-21 | COMP | Rule 16 | 211 | 18 | 18 | 14 | 0 | 15 | 365
10604 | 2018-03-13 | 2019-03-21 | 2019-07-19 | 2019-07-19 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2019-11-26 | COMP | 2020-01-15 | COMP | Rule 16 | 258 | 85 | 80 | 1 | 12 | 33 | 464
11096 | 2018-03-13 | 2019-04-11 | 2019-06-23 | 2019-06-23 | COMP | 2019-09-11 | COMP | 2019-09-27 | COMP | 2019-10-31 | COMP | 2019-12-04 | COMP | Rule 16 | 273 | 51 | 56 | 13 | 25 | 22 | 436
18507 | 2018-03-13 | 2020-03-26 | 2020-09-10 | 2020-09-10 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2022-04-04 | COMP | 2022-06-30 | COMP | Rule 16 | 513 | 119 | 175 | 1 | 219 | 62 | 1084
3390 | 2018-03-14 | 2018-04-18 | 2018-07-30 | 2018-07-30 | COMP | 2018-10-24 | COMP | 2019-02-20 | COMP | 2019-10-30 | COMP | 2019-11-21 | COMP | Rule 16 | 26 | 72 | 62 | 79 | 178 | 16 | 428
3452 | 2018-03-14 | 2018-04-30 | 2018-08-04 | 2018-08-04 | COMP | 2018-10-16 | COMP | 2018-10-30 | COMP | 2019-07-08 | COMP | 2019-07-23 | COMP | Rule 16 | 34 | 68 | 51 | 11 | 171 | 12 | 343
3693 | 2018-03-14 | 2018-06-08 | 2019-04-10 | 2019-04-10 | COMP | 2019-05-29 | COMP | 2019-08-02 | COMP | 2019-07-10 | COMP | 2019-09-25 | COMP | Rule 15/16 | 62 | 210 | 35 | 47 | 0 | 38 | 388
4764 | 2018-03-14 | 2018-03-30 | 2018-10-17 | 2019-02-23 | COMP | 2019-03-08 | COMP | 2019-03-14 | COMP | 2019-03-15 | COMP | 2019-04-16 | COMP | Rule 16 | 13 | 141 | 10 | 5 | 2 | 23 | 275
4821 | 2018-03-14 | 2018-04-01 | 2018-04-24 | 2018-04-24 | COMP | 2018-06-12 | COMP | 2018-06-12 | COMP | 2022-11-05 | INPR | 2021-10-17 | COMP | Rule 16 | 13 | 17 | 35 | 1 |  |  | 906
4967 | 2018-03-14 | 2018-04-16 | 2018-06-22 | 2018-08-04 | COMP | 2018-08-27 | COMP | 2018-09-25 | COMP | 2018-10-04 | COMP | 2019-05-10 | COMP | Rule 16 | 24 | 49 | 16 | 21 | 8 | 150 | 293
4979 | 2018-03-14 | 2018-04-18 | 2018-08-27 | 2018-08-27 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-04-12 | COMP | 2019-06-25 | COMP | Rule 16 | 26 | 92 | 115 | 1 | 43 | 52 | 324
5022 | 2018-03-14 | 2018-04-24 | 2018-08-04 | 2018-08-04 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-07-08 | COMP | 2019-08-16 | COMP | Rule 16 | 30 | 72 | 7 | 1 | 225 | 30 | 361
5023 | 2018-03-14 | 2018-04-24 | 2018-08-04 | 2018-08-04 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-07-08 | COMP | 2019-08-16 | COMP | Rule 16 | 30 | 72 | 7 | 1 | 225 | 30 | 361
5024 | 2018-03-14 | 2018-04-24 | 2018-08-04 | 2018-08-04 | COMP | 2018-09-14 | COMP | 2019-08-13 | COMP | 2019-08-14 | COMP | 2019-09-17 | COMP | Rule 16 | 30 | 72 | 29 | 229 | 2 | 24 | 382
5025 | 2018-03-14 | 2018-04-24 | 2018-08-04 | 2018-08-04 | COMP | 2018-08-28 | COMP | 2018-08-28 | COMP | 2019-08-06 | COMP | 2019-09-23 | COMP | Rule 16 | 30 | 72 | 17 | 1 | 236 | 34 | 386
5026 | 2018-03-14 | 2018-04-24 | 2018-08-04 | 2018-08-04 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-07-17 | COMP | 2019-08-26 | COMP | Rule 16 | 30 | 72 | 134 | 1 | 105 | 29 | 367
5088 | 2018-03-14 | 2018-04-30 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-17 | COMP | 2019-01-16 | COMP | 2023-04-30 | INPR | 2019-07-03 | COMP | Rule 15/16 | 34 | 112 | 49 | 21 |  |  | 330
5217 | 2018-03-14 | 2018-05-10 | 2018-11-16 | 2018-11-16 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2020-02-19 | COMP | 2020-04-30 | COMP | Rule 16 | 42 | 133 | 150 | 1 | 164 | 52 | 537
5248 | 2018-03-14 | 2018-05-14 | 2018-06-19 | 2018-06-19 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2018-12-17 | COMP | 2019-01-02 | COMP | Rule 16 | 44 | 26 | 116 | 1 | 10 | 11 | 203
5887 | 2018-03-14 | 2018-07-09 | 2019-03-28 | 2019-03-28 | COMP | 2020-06-18 | COMP | 2020-08-07 | COMP | 2020-09-24 | COMP | 2020-09-30 | COMP | Rule 16 | 82 | 181 | 310 | 37 | 34 | 5 | 644
5942 | 2018-03-14 | 2018-07-12 | 2018-08-17 | 2018-12-13 | COMP | 2020-01-31 | COMP | 2020-02-06 | COMP | 2020-02-05 | COMP | 2020-03-03 | COMP | Rule 16 | 85 | 27 | 284 | 5 | 0 | 18 | 495
6118 | 2018-03-14 | 2018-07-27 | 2018-07-30 | 2018-07-30 | COMP | 2018-08-20 | COMP | 2018-08-20 | INPR | 2020-01-19 | REQD | 2019-10-03 | COMP | Rule 16 | 96 | 2 | 16 |  |  |  | 394
6641 | 2018-03-14 | 2018-09-04 | 2019-03-08 | 2020-09-08 | COMP | 2020-12-08 | COMP | 2020-12-08 | COMP | 2021-04-07 | COMP | 2021-05-23 | COMP | Rule 15 | 122 | 127 | 63 | 1 | 83 | 33 | 804
6773 | 2018-03-14 | 2018-09-12 | 2018-10-22 | 2018-10-22 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-07-30 | COMP | 2019-11-06 | COMP | Rule 15/16 | 128 | 29 | 53 | 1 | 141 | 71 | 418
6965 | 2018-03-14 | 2018-09-20 | 2019-01-15 | 2019-01-15 | COMP | 2019-02-26 | COMP | 2019-06-25 | COMP | 2019-07-03 | COMP | 2019-08-29 | COMP | Rule 16 | 134 | 79 | 29 | 85 | 7 | 41 | 370
8120 | 2018-03-14 | 2018-11-15 | 2018-12-20 | 2019-02-01 | COMP | 2019-02-28 | COMP | 2019-02-26 | COMP | 2019-06-04 | COMP | 2019-10-07 | COMP | Rule 15/16 | 173 | 24 | 19 |  | 70 | 88 | 396
8287 | 2018-03-14 | 2018-11-26 | 2019-02-12 | 2019-02-12 | COMP | 2019-03-25 | COMP | 2019-04-02 | COMP | 2020-02-29 | INPR | 2019-11-08 | COMP | Rule 15 | 178 | 54 | 29 | 7 |  |  | 420
8586 | 2018-03-14 | 2018-12-10 | 2020-07-27 | 2020-07-27 | COMP | 2021-02-19 | COMP | 2021-03-11 | COMP | 2023-04-15 | INPR | 2021-04-19 | COMP | Rule 16 | 188 | 411 | 142 | 15 |  |  | 780
9704 | 2018-03-14 | 2019-02-12 | 2019-05-25 | 2019-10-31 | COMP | 2019-11-18 | COMP | 2019-12-04 | COMP | 2020-02-11 | COMP | 2020-03-17 | COMP | Rule 16 | 231 | 73 | 12 | 11 | 47 | 25 | 505
10168 | 2018-03-14 | 2019-03-05 | 2019-08-09 | 2019-08-09 | COMP | 2019-11-05 | COMP | 2020-06-15 | COMP | 2021-07-21 | COMP | 2021-09-01 | COMP | Rule 15/16 | 245 | 112 | 62 | 152 | 278 | 31 | 875
10292 | 2018-03-14 | 2019-03-09 | 2019-05-13 | 2019-07-30 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-09-28 | COMP | 2019-12-13 | COMP | Rule 16 | 248 | 46 | 6 | 1 | 38 | 52 | 442
12417 | 2018-03-14 | 2019-06-05 | 2019-08-24 | 2019-08-24 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-12-13 | COMP | 2020-02-01 | COMP | Rule 16 | 310 | 57 | 49 | 1 | 28 | 33 | 474
13346 | 2018-03-14 | 2019-07-23 | 2019-08-01 | 2019-09-18 | COMP | 2019-10-22 | COMP | 2022-07-16 | REQD | 2022-07-16 | REQD | 2020-09-18 | COMP | Rule 15 | 343 | 8 | 25 |  |  |  | 636
14197 | 2018-03-14 | 2019-08-28 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-07 | COMP | 2020-02-19 | COMP | 2020-02-12 | COMP | 2020-03-04 | COMP | Rule 16 | 369 | 33 | 19 | 68 | 0 | 11 | 496
16996 | 2018-03-14 | 2020-01-27 | 2020-05-02 | 2020-05-02 | COMP | 2021-04-02 | COMP | 2021-04-02 | COMP | 2022-04-15 | COMP | 2022-05-12 | COMP | Rule 16 | 470 | 69 | 231 | 1 | 263 | 20 | 1050
3212 | 2018-03-15 | 2018-03-22 | 2018-04-09 | 2018-04-09 | COMP | 2018-07-03 | COMP | 2018-07-11 | COMP | 2019-07-23 | COMP | 2019-09-14 | COMP | Rule 16 | 6 | 13 | 61 | 6 | 260 | 38 | 379
3213 | 2018-03-15 | 2018-03-22 | 2018-09-04 | 2018-09-04 | COMP | 2019-08-07 | COMP | 2020-06-10 | COMP | 2020-06-02 | COMP | 2020-07-06 | COMP | Rule 16 | 6 | 116 | 233 | 212 | 0 | 19 | 582
3559 | 2018-03-15 | 2018-05-16 | 2018-09-14 | 2018-09-14 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2020-07-20 | COMP | 2020-09-02 | COMP | Rule 16 | 45 | 85 | 208 | 2 | 256 | 33 | 624
3758 | 2018-03-15 | 2018-06-28 | 2018-08-18 | 2018-08-18 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2018-12-26 | COMP | 2019-03-12 | COMP | Rule 16 | 75 | 36 | 89 | 1 | 0 | 51 | 249
4049 | 2018-03-15 | 2018-12-29 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-20 | COMP | 2019-03-20 | COMP | 2019-12-28 | INPR | 2019-09-09 | COMP | Rule 16 | 200 | 42 | 14 | 1 |  |  | 375
4716 | 2018-03-15 | 2018-03-19 | 2018-07-09 | 2019-06-24 | COMP | 2019-07-10 | COMP | 2019-03-28 | COMP | 2019-07-16 | COMP | 2019-10-01 | COMP | Rule 16 | 3 | 79 | 12 |  | 77 | 55 | 391
4837 | 2018-03-15 | 2018-04-04 | 2018-07-24 | 2018-07-24 | COMP | 2018-08-31 | COMP | 2018-08-31 | COMP | 2018-11-26 | COMP | 2019-06-10 | COMP | Rule 16 | 15 | 78 | 29 | 1 | 58 | 136 | 312
4898 | 2018-03-15 | 2018-04-10 | 2018-04-16 | 2018-04-16 | COMP | 2018-07-10 | COMP | 2018-09-18 | COMP | 2019-09-22 | INPR | 2019-06-13 | COMP | Rule 16 | 19 | 5 | 60 | 50 |  |  | 315
5027 | 2018-03-15 | 2018-04-24 | 2018-08-04 | 2018-08-04 | COMP | 2018-09-14 | COMP | 2018-09-14 | COMP | 2019-08-01 | COMP | 2019-08-28 | COMP | Rule 16 | 29 | 72 | 29 | 1 | 221 | 20 | 368
5051 | 2018-03-15 | 2018-04-26 | 2018-07-24 | 2018-10-05 | COMP | 2018-10-25 | COMP | 2018-10-29 | COMP | 2018-10-26 | COMP | 2019-01-10 | COMP | Rule 16 | 31 | 62 | 15 | 3 | 0 | 49 | 208
5119 | 2018-03-15 | 2018-05-02 | 2018-07-28 | 2018-07-28 | COMP | 2019-03-19 | COMP | 2019-10-04 | COMP | 2019-08-13 | COMP | 2019-10-07 | COMP | Rule 16 | 35 | 61 | 159 | 141 | 0 | 2 | 395
5159 | 2018-03-15 | 2018-05-04 | 2018-09-06 | 2018-09-06 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-04-30 | COMP | 2019-05-20 | COMP | Rule 16 | 37 | 87 | 44 | 1 | 119 | 15 | 298
5160 | 2018-03-15 | 2018-05-04 | 2018-09-06 | 2018-09-06 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-04-16 | COMP | 2019-08-04 | COMP | Rule 16 | 37 | 87 | 44 | 1 | 109 | 77 | 350
5214 | 2018-03-15 | 2018-05-10 | 2019-09-11 | 2020-11-30 | COMP | 2020-12-24 | COMP | 2021-05-28 | COMP | 2022-02-17 | COMP | 2022-03-10 | COMP | Rule 16 | 41 | 337 | 19 | 108 | 183 | 15 | 1004
5329 | 2018-03-15 | 2018-05-22 | 2019-02-16 | 2019-02-16 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-09-23 | COMP | 2020-11-05 | COMP | Rule 16 | 49 | 185 | 377 | 1 | 29 | 32 | 669
5666 | 2018-03-15 | 2018-06-25 | 2018-08-19 | 2018-08-19 | COMP | 2018-10-03 | COMP | 2018-10-03 | COMP | 2018-12-05 | COMP | 2019-01-22 | COMP | Rule 16 | 72 | 39 | 32 | 1 | 43 | 32 | 215
6150 | 2018-03-15 | 2018-07-31 | 2018-10-12 | 2018-10-12 | COMP | 2019-03-26 | COMP | 2019-05-03 | COMP | 2019-05-08 | COMP | 2019-06-04 | COMP | Rule 16 | 97 | 53 | 111 | 29 | 4 | 19 | 308
6287 | 2018-03-15 | 2018-08-08 | 2018-09-25 | 2018-09-25 | COMP | 2018-10-18 | COMP | 2018-11-07 | COMP | 2018-12-12 | COMP | 2019-02-21 | COMP | Rule 15/16 | 103 | 34 | 18 | 15 | 23 | 48 | 236
6333 | 2018-03-15 | 2018-08-11 | 2019-08-26 | 2019-10-28 | COMP | 2019-12-23 | COMP | 2019-12-27 | COMP | 2020-03-24 | COMP | 2020-04-04 | COMP | Rule 15/16 | 105 | 261 | 38 | 4 | 60 | 9 | 517
6525 | 2018-03-15 | 2018-08-24 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2019-02-05 | COMP | 2019-04-03 | COMP | Rule 16 | 115 | 15 | 12 | 1 | 86 | 41 | 265
7133 | 2018-03-15 | 2018-09-28 | 2018-11-02 | 2019-01-24 | COMP | 2019-01-31 | COMP | 2018-11-13 | COMP | 2018-12-05 | COMP | 2019-04-22 | COMP | Rule 16 | 139 | 26 | 6 |  | 15 | 95 | 278
7510 | 2018-03-15 | 2018-10-18 | 2019-01-24 | 2019-01-30 | COMP | 2019-02-12 | COMP | 2019-02-13 | COMP | 2019-06-22 | COMP | 2019-08-14 | COMP | Rule 16 | 153 | 65 | 10 | 2 | 91 | 37 | 358
8098 | 2018-03-15 | 2018-11-15 | 2019-03-28 | 2019-04-08 | COMP | 2019-04-17 | COMP | 2019-05-03 | COMP | 2019-05-08 | COMP | 2019-06-12 | COMP | Rule 16 | 172 | 90 | 8 | 13 | 4 | 25 | 314
8973 | 2018-03-15 | 2019-01-10 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-27 | COMP | 2019-10-21 | COMP | 2019-09-21 | COMP | 2019-11-18 | COMP | Rule 16 | 208 | 20 | 34 | 146 | 0 | 20 | 424
10397 | 2018-03-15 | 2019-03-14 | 2019-06-04 | 2019-09-25 | COMP | 2019-10-18 | COMP | 2020-03-17 | COMP | 2020-03-24 | COMP | 2020-05-10 | COMP | Rule 15/16 | 251 | 58 | 18 | 101 | 6 | 34 | 542
10750 | 2018-03-15 | 2019-03-28 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-06-13 | COMP | 2019-06-14 | COMP | Rule 16 | 261 | 6 | 13 | 1 | 38 | 2 | 316
10751 | 2018-03-15 | 2019-03-28 | 2019-04-04 | 2019-04-04 | COMP | 2019-06-05 | COMP | 2019-06-05 | INPR | 2019-06-17 | COMP | 2019-06-17 | COMP | Rule 16 | 261 | 6 | 44 |  |  |  | 317
10948 | 2018-03-15 | 2019-04-05 | 2019-04-18 | 2019-04-18 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-05 | COMP | 2019-06-08 | COMP | Rule 16 | 267 | 10 | 24 | 1 | 11 | 3 | 311
14754 | 2018-03-15 | 2019-09-26 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-11-22 | COMP | 2019-12-03 | COMP | Rule 16 | 388 | 7 | 15 | 1 | 20 | 6 | 433
3347 | 2018-03-16 | 2018-04-10 | 2018-07-14 | 2018-07-14 | COMP | 2018-08-13 | COMP | 2018-10-17 | COMP | 2018-10-16 | COMP | 2019-04-30 | COMP | Rule 16 | 18 | 67 | 21 | 47 | 0 | 133 | 283
3353 | 2018-03-16 | 2018-04-11 | 2018-08-31 | 2018-12-28 | COMP | 2019-05-16 | COMP | 2019-05-23 | COMP |  | INPR | 2019-07-16 | COMP | Rule 15/16 | 19 | 101 | 97 | 6 |  |  | 336
3366 | 2018-03-16 | 2018-04-13 | 2018-07-14 | 2018-07-14 | COMP | 2018-08-13 | COMP | 2018-08-13 | COMP | 2018-11-03 | COMP | 2019-02-06 | COMP | Rule 15/16 | 21 | 64 | 21 | 1 | 59 | 62 | 225
3387 | 2018-03-16 | 2018-04-18 | 2018-09-04 | 2018-09-04 | COMP | 2018-12-06 | COMP | 2018-12-26 | COMP | 2019-09-03 | COMP | 2019-10-18 | COMP | Rule 16 | 24 | 97 | 65 | 14 | 174 | 34 | 403
3419 | 2018-03-16 | 2018-04-23 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-12 | COMP | 2019-05-06 | INPR | 2019-04-18 | COMP | 2019-05-23 | COMP | Rule 15/16 | 27 | 149 | 14 |  |  |  | 300
3420 | 2018-03-16 | 2018-04-23 | 2018-05-09 | 2018-05-09 | COMP | 2018-05-16 | COMP | 2018-05-16 | COMP | 2019-05-10 | COMP | 2019-08-05 | COMP | Rule 16 | 27 | 13 | 6 | 1 | 248 | 60 | 350
3504 | 2018-03-16 | 2018-05-08 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-18 | COMP | 2021-02-09 | COMP | 2021-02-16 | COMP | 2021-04-20 | COMP | Rule 15/16 | 38 | 448 | 20 | 227 | 5 | 46 | 779
3515 | 2018-03-16 | 2018-05-10 | 2018-09-04 | 2018-09-04 | COMP | 2021-03-15 | COMP | 2021-03-18 | COMP | 2021-05-01 | COMP | 2021-05-14 | COMP | Rule 15/16 | 40 | 81 | 634 | 4 | 32 | 10 | 797
3644 | 2018-03-16 | 2018-06-01 | 2018-08-23 | 2018-08-23 | COMP | 2019-02-04 | COMP | 2019-04-16 | COMP | 2019-01-28 | COMP | 2019-09-17 | COMP | Rule 15/16 | 55 | 59 | 111 | 51 | 0 | 108 | 380
3755 | 2018-03-16 | 2018-06-27 | 2018-12-30 | 2018-12-30 | COMP | 2019-05-22 | COMP | 2019-05-30 | COMP | 2019-11-24 | INPR | 2019-07-30 | COMP | Rule 15/16 | 73 | 127 | 100 | 6 |  |  | 346
3757 | 2018-03-16 | 2018-06-28 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-09 | COMP | 2020-03-09 | INPR | 2020-03-05 | COMP | 2020-03-10 | COMP | Rule 16 | 74 | 417 | 8 |  |  |  | 498
3864 | 2018-03-16 | 2018-08-23 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2019-02-02 | COMP | 2019-03-21 | COMP | Rule 16 | 113 | 32 | 28 | 1 | 52 | 33 | 255
4743 | 2018-03-16 | 2018-03-27 | 2018-03-28 | 2018-03-28 | COMP | 2018-06-06 | COMP | 2018-06-06 | COMP | 2021-04-09 | COMP | 2021-03-11 | COMP | Rule 16 | 8 | 2 | 50 | 1 | 715 |  | 751
4941 | 2018-03-16 | 2018-04-13 | 2019-03-14 | 2019-03-14 | COMP | 2019-07-11 | NOTN | 2019-10-22 | COMP | 2020-01-07 | COMP | 2020-02-13 | COMP | Other | 21 | 230 |  | 156 | 51 | 27 | 481
5012 | 2018-03-16 | 2018-04-25 | 2018-06-26 | 2018-06-26 | COMP | 2018-07-05 | COMP | 2018-10-04 | COMP | 2022-07-16 | INPR | 2020-07-08 | COMP | Rule 16 | 29 | 44 | 7 | 65 |  |  | 583
5094 | 2018-03-16 | 2018-05-01 | 2018-09-15 | 2018-09-15 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-03-06 | COMP | 2020-03-30 | COMP | Rule 16 | 33 | 96 | 371 | 1 | 0 | 14 | 512
5367 | 2018-03-16 | 2018-05-24 | 2018-09-27 | 2018-09-27 | COMP | 2018-10-10 | COMP | 2018-10-24 | COMP | 2018-12-06 | COMP | 2019-01-29 | COMP | Rule 16 | 50 | 88 | 10 | 11 | 29 | 36 | 219
5427 | 2018-03-16 | 2018-05-30 | 2018-08-01 | 2019-05-23 | COMP | 2019-07-08 | COMP | 2019-04-15 | COMP | 2019-06-24 | COMP | 2019-07-22 | COMP | Rule 16 | 53 | 45 | 31 |  | 50 | 20 | 340
5442 | 2018-03-16 | 2018-05-31 | 2018-10-01 | 2018-10-01 | COMP | 2018-10-16 | COMP | 2018-10-16 | COMP | 2019-03-27 | COMP | 2019-04-09 | COMP | Rule 16 | 54 | 86 | 12 | 1 | 110 | 10 | 268
6189 | 2018-03-16 | 2018-08-02 | 2019-03-11 | 2019-03-11 | COMP | 2020-01-17 | COMP | 2022-04-01 | COMP | 2022-04-28 | COMP | 2022-09-16 | COMP | Rule 15/16 | 98 | 150 | 217 | 557 | 20 | 98 | 1135
6586 | 2018-03-16 | 2018-08-28 | 2018-10-19 | 2018-10-19 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2018-12-06 | COMP | 2019-01-28 | COMP | Rule 16 | 116 | 38 | 29 | 1 | 4 | 35 | 218
7128 | 2018-03-16 | 2018-09-28 | 2019-01-28 | 2019-01-28 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-17 | COMP | 2019-10-16 | COMP | Rule 15/16 | 138 | 81 | 139 | 1 | 4 | 42 | 401
7865 | 2018-03-16 | 2018-11-03 | 2019-02-02 | 2019-02-02 | COMP | 2019-03-06 | COMP | 2019-06-24 | COMP | 2019-07-23 | COMP | 2019-09-11 | COMP | Rule 16 | 163 | 59 | 22 | 78 | 21 | 36 | 376
8402 | 2018-03-16 | 2018-11-29 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-09 | COMP | 2019-08-16 | COMP | 2019-08-05 | COMP | 2019-09-23 | COMP | Rule 16 | 179 | 98 | 15 | 70 | 0 | 26 | 384
8725 | 2018-03-16 | 2018-12-19 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-23 | COMP | 2019-04-24 | COMP | 2019-10-21 | INPR | 2019-07-09 | COMP | Rule 16 | 193 | 69 | 17 | 2 |  |  | 331
11246 | 2018-03-16 | 2019-04-18 | 2019-07-24 | 2019-07-24 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2021-04-07 | COMP | 2021-04-13 | COMP | Rule 16 | 275 | 68 | 43 | 1 | 387 | 5 | 774
16575 | 2018-03-16 | 2020-01-08 | 2020-01-13 | 2020-01-29 | COMP | 2020-05-14 | COMP | 2020-06-10 | COMP | 2020-05-18 | COMP | 2020-09-30 | COMP | Rule 15/16 | 456 | 4 | 76 | 19 | 0 | 80 | 642
5994 | 2018-03-18 | 2018-07-17 | 2018-11-16 | 2018-11-16 | COMP | 2019-02-08 | COMP | 2019-02-20 | COMP | 2019-03-29 | COMP | 2019-05-17 | COMP | Rule 16 | 85 | 87 | 56 | 8 | 28 | 36 | 295
3190 | 2018-03-19 | 2018-03-20 | 2018-07-26 | 2018-07-26 | COMP | 2018-08-21 | COMP | 2018-08-27 | COMP | 2019-06-04 | COMP | 2019-07-11 | COMP | Rule 16 | 2 | 91 | 19 | 5 | 193 | 27 | 332
3448 | 2018-03-19 | 2018-04-28 | 2018-05-13 | 2018-05-13 | COMP | 2018-05-30 | COMP | 2018-05-31 | COMP | 2019-12-19 | COMP | 2020-01-29 | COMP | Rule 16 | 30 | 10 | 12 | 2 | 391 | 27 | 469
3710 | 2018-03-19 | 2018-06-14 | 2018-08-27 | 2018-08-27 | COMP | 2018-11-07 | COMP | 2018-11-08 | COMP |  | INPR | 2019-04-25 | COMP | Rule 15/16 | 63 | 52 | 52 | 2 |  |  | 279
3752 | 2018-03-19 | 2018-06-27 | 2018-08-24 | 2018-08-24 | COMP | 2020-02-14 | NOTN | 2020-02-18 | COMP | 2020-02-14 | COMP | 2020-06-03 | COMP | Other | 72 | 42 |  | 370 | 0 | 76 | 557
3774 | 2018-03-19 | 2018-07-09 | 2018-09-19 | 2018-09-19 | COMP | 2019-01-08 | COMP | 2019-01-16 | COMP | 2019-05-09 | COMP | 2019-05-21 | COMP | Rule 15/16 | 79 | 52 | 75 | 7 | 80 | 9 | 297
4739 | 2018-03-19 | 2018-03-24 | 2018-04-10 | 2018-04-10 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-10-11 | COMP | 2019-11-06 | COMP | Rule 16 | 5 | 12 | 209 | 1 | 173 | 19 | 415
5035 | 2018-03-19 | 2018-04-24 | 2018-07-12 | 2018-07-12 | COMP | 2018-07-18 | COMP | 2020-02-26 | COMP | 2020-02-13 | COMP | 2020-06-11 | COMP | Rule 16 | 27 | 56 | 5 | 403 | 0 | 76 | 563
5302 | 2018-03-19 | 2018-05-20 | 2018-07-26 | 2019-02-23 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2018-08-13 | COMP | 2019-06-07 | COMP | Rule 16 | 45 | 47 | 21 | 1 | 0 | 54 | 309
5519 | 2018-03-19 | 2018-06-06 | 2018-08-09 | 2018-08-09 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2018-12-21 | COMP | 2019-01-30 | COMP | Rule 16 | 57 | 46 | 51 | 1 | 43 | 26 | 219
5575 | 2018-03-19 | 2018-06-15 | 2018-09-15 | 2019-03-14 | COMP | 2019-04-24 | COMP | 2019-08-15 | COMP | 2019-08-12 | COMP | 2019-08-27 | COMP | Rule 16 | 64 | 64 | 30 | 80 | 0 | 9 | 365
5576 | 2018-03-19 | 2018-06-15 | 2018-09-15 | 2019-02-02 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2020-07-29 | COMP | 2020-07-15 | COMP | Rule 16 | 64 | 64 | 11 | 1 | 366 |  | 587
6506 | 2018-03-19 | 2018-08-22 | 2018-10-02 | 2018-10-02 | COMP | 2018-10-19 | COMP | 2018-11-30 | COMP | 2019-09-23 | COMP | 2019-10-07 | COMP | Rule 16 | 111 | 29 | 14 | 28 | 205 | 11 | 393
7162 | 2018-03-19 | 2018-09-30 | 2018-11-15 | 2018-11-15 | COMP | 2018-11-21 | COMP | 2019-01-15 | COMP | 2019-01-11 | COMP | 2019-03-08 | COMP | Rule 16 | 137 | 33 | 5 | 36 | 0 | 37 | 245
8777 | 2018-03-19 | 2018-12-26 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-05 | COMP | 2019-04-08 | COMP | 2019-04-07 | COMP | 2019-04-15 | COMP | Rule 15/16 | 196 | 61 | 10 | 2 | 0 | 6 | 271
9273 | 2018-03-19 | 2019-01-26 | 2019-04-06 | 2019-04-06 | COMP | 2019-05-09 | COMP | 2019-05-20 | COMP | 2019-06-04 | COMP | 2019-06-10 | COMP | Rule 16 | 216 | 49 | 24 | 8 | 11 | 5 | 310
9543 | 2018-03-19 | 2019-02-06 | 2019-09-26 | 2019-12-19 | COMP | 2020-01-17 | COMP | 2021-02-23 | COMP | 2021-05-18 | COMP | 2021-08-02 | COMP | Rule 15/16 | 224 | 163 | 20 | 277 | 61 | 53 | 850
12232 | 2018-03-19 | 2019-05-28 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-20 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-03-10 | COMP | Rule 16 | 301 | 78 | 5 | 9 | 1 | 108 | 497
12636 | 2018-03-19 | 2019-06-17 | 2020-03-06 | 2020-10-06 | COMP | 2020-10-12 | COMP | 2020-11-16 | COMP | 2020-11-16 | COMP | 2020-12-06 | COMP | Rule 15/16 | 315 | 181 | 5 | 25 | 1 | 13 | 685
3365 | 2018-03-20 | 2018-04-13 | 2018-10-15 | 2018-10-15 | COMP | 2019-02-26 | COMP | 2019-03-06 | NOTN | 2019-08-15 | COMP | 2019-08-26 | COMP | Rule 15/16 | 19 | 129 | 90 |  |  |  | 363
3403 | 2018-03-20 | 2018-04-19 | 2018-05-31 | 2018-05-31 | COMP | 2019-08-12 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-09-05 | COMP | Rule 15/16 | 23 | 30 | 302 | 2 | 1 | 17 | 370
3545 | 2018-03-20 | 2018-05-14 | 2019-01-15 | 2019-03-07 | COMP | 2019-06-11 | COMP | 2019-11-20 | COMP | 2019-11-05 | COMP | 2019-12-07 | COMP | Rule 15/16 | 40 | 169 | 68 | 114 | 0 | 11 | 433
3638 | 2018-03-20 | 2018-05-31 | 2019-05-16 | 2019-05-16 | COMP | 2019-08-30 | COMP | 2021-09-21 | COMP | 2021-09-07 | COMP | 2021-11-30 | COMP | Rule 15/16 | 52 | 242 | 75 | 518 | 0 | 48 | 931
4741 | 2018-03-20 | 2018-03-24 | 2019-02-22 | 2020-04-28 | COMP | 2020-05-11 | COMP | 2020-07-22 | COMP | 2024-02-03 | INPR | 2020-10-31 | COMP | Rule 16 | 4 | 230 | 10 | 52 |  |  | 662
4768 | 2018-03-20 | 2018-03-29 | 2018-05-29 | 2018-05-29 | COMP | 2018-06-01 | COMP | 2018-06-01 | COMP | 2019-03-14 | COMP | 2019-04-15 | COMP | Rule 16 | 8 | 43 | 4 | 1 | 196 | 23 | 270
4892 | 2018-03-20 | 2018-04-10 | 2018-06-21 | 2018-06-21 | COMP | 2020-01-07 | NOTN | 2020-01-07 | COMP | 2021-02-27 | INPR | 2020-02-14 | COMP | Other | 16 | 52 |  | 387 |  |  | 480
5038 | 2018-03-20 | 2018-04-24 | 2018-06-30 | 2018-06-30 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-10-21 | INPR | 2019-04-30 | COMP | Rule 16 | 26 | 48 | 31 | 1 |  |  | 281
5069 | 2018-03-20 | 2018-04-28 | 2018-10-05 | 2018-10-05 | COMP | 2019-01-09 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-03-22 | COMP | Rule 16 | 29 | 112 | 64 | 2 | 1 | 50 | 254
5142 | 2018-03-20 | 2018-05-03 | 2018-08-28 | 2018-08-28 | COMP | 2018-09-18 | COMP | 2018-09-18 | COMP | 2018-10-17 | COMP | 2019-03-14 | COMP | Rule 16 | 33 | 82 | 15 | 1 | 22 | 100 | 248
5155 | 2018-03-20 | 2018-05-04 | 2018-06-11 | 2018-06-11 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-01-18 | COMP | 2019-01-30 | COMP | Rule 16 | 34 | 26 | 155 | 1 | 0 | 6 | 218
5220 | 2018-03-20 | 2018-05-11 | 2018-06-04 | 2018-06-04 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2020-06-23 | COMP | 2020-09-03 | COMP | Rule 16 | 39 | 16 | 163 | 1 | 355 | 53 | 622
5287 | 2018-03-20 | 2018-05-17 | 2019-02-01 | 2019-02-01 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2019-11-13 | COMP | 2020-01-13 | COMP | Rule 16 | 43 | 178 | 44 | 1 | 156 | 40 | 457
5748 | 2018-03-20 | 2018-06-29 | 2018-08-13 | 2018-12-03 | COMP | 2018-12-24 | COMP | 2018-12-24 | COMP | 2019-07-23 | COMP | 2019-08-07 | COMP | Rule 16 | 73 | 31 | 16 | 1 | 146 | 12 | 350
5793 | 2018-03-20 | 2018-07-03 | 2018-09-22 | 2018-12-06 | COMP | 2019-02-12 | COMP | 2019-03-29 | COMP | 2019-03-27 | COMP | 2019-04-30 | COMP | Rule 16 | 75 | 57 | 46 | 33 | 0 | 23 | 281
6326 | 2018-03-20 | 2018-08-10 | 2018-11-10 | 2018-11-10 | COMP | 2019-02-14 | COMP | 2019-04-03 | COMP | 2019-03-19 | COMP | 2019-04-19 | COMP | Rule 16 | 102 | 65 | 63 | 34 | 0 | 13 | 274
6391 | 2018-03-20 | 2018-08-15 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-07-21 | INPR | 2019-04-23 | COMP | Rule 16 | 105 | 62 | 19 | 1 |  |  | 276
6578 | 2018-03-20 | 2018-08-28 | 2018-10-04 | 2018-10-04 | COMP | 2019-03-25 | COMP | 2020-08-26 | INPR | 2020-08-05 | COMP | 2020-09-11 | COMP | Rule 15/16 | 114 | 27 | 116 |  |  |  | 627
6961 | 2018-03-20 | 2018-09-19 | 2018-12-06 | 2019-02-06 | COMP | 2019-07-31 | COMP | 2019-08-16 | COMP | 2020-04-29 | COMP | 2020-06-09 | COMP | Rule 15/16 | 129 | 54 | 123 | 13 | 176 | 29 | 560
7190 | 2018-03-20 | 2018-10-02 | 2018-10-24 | 2018-10-24 | COMP | 2018-10-31 | COMP | 2018-12-14 | COMP | 2018-11-26 | COMP | 2019-01-29 | COMP | Rule 15/16 | 138 | 17 | 6 | 30 | 0 | 30 | 217
7224 | 2018-03-20 | 2018-10-03 | 2018-12-21 | 2018-12-21 | COMP | 2019-01-22 | COMP | 2019-05-22 | COMP | 2019-07-26 | COMP | 2020-02-16 | COMP | Rule 16 | 139 | 55 | 20 | 86 | 46 | 139 | 480
7231 | 2018-03-20 | 2018-10-03 | 2018-10-06 | 2018-10-06 | COMP | 2018-11-02 | COMP | 2019-04-04 | INPR | 2019-04-04 | COMP | 2019-04-11 | COMP | Rule 16 | 139 | 3 | 20 |  |  |  | 268
8339 | 2018-03-20 | 2018-11-27 | 2018-12-12 | 2018-12-12 | COMP | 2019-01-28 | COMP | 2019-05-29 | COMP | 2019-05-28 | COMP | 2019-06-27 | COMP | Rule 15/16 | 175 | 12 | 31 | 86 | 0 | 22 | 322
9191 | 2018-03-20 | 2019-01-21 | 2019-03-24 | 2019-03-26 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-09-02 | INPR | 2019-05-02 | COMP | Rule 16 | 211 | 43 | 10 | 1 |  |  | 283
3329 | 2018-03-21 | 2018-04-10 | 2019-01-15 | 2019-01-15 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-11-19 | COMP | 2020-02-22 | COMP | Rule 15/16 | 15 | 193 | 28 | 1 | 188 | 63 | 483
3396 | 2018-03-21 | 2018-04-18 | 2018-06-09 | 2018-06-09 | COMP | 2018-08-08 | NOTN | 2018-08-13 | COMP |  | INPR | 2019-01-20 | COMP | Other | 21 | 37 |  | 45 |  |  | 210
3447 | 2018-03-21 | 2018-04-27 | 2018-04-28 | 2018-04-28 | COMP | 2018-05-02 | COMP | 2019-07-21 | REQD | 2018-05-22 | COMP | 2019-04-08 | COMP | Rule 16 | 28 | 1 | 3 |  |  |  | 264
3461 | 2018-03-21 | 2018-05-01 | 2018-07-11 | 2018-07-11 | COMP | 2018-07-27 | COMP | 2018-07-27 | COMP | 2019-02-05 | COMP | 2019-04-01 | COMP | Rule 15/16 | 30 | 50 | 13 | 1 | 131 | 39 | 259
3634 | 2018-03-21 | 2018-05-30 | 2019-01-27 | 2019-01-27 | COMP | 2019-05-03 | COMP | 2019-05-10 | COMP | 2020-04-09 | COMP | 2020-04-30 | COMP | Rule 15/16 | 50 | 165 | 69 | 6 | 230 | 16 | 532
3825 | 2018-03-21 | 2018-07-31 | 2019-11-21 | 2020-02-14 | COMP | 2020-03-11 | COMP | 2020-08-06 | COMP | 2020-07-03 | COMP | 2020-10-03 | COMP | Rule 15/16 | 93 | 331 | 18 | 106 | 0 | 41 | 641
3837 | 2018-03-21 | 2018-08-08 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-02-08 | COMP | 2019-03-18 | COMP | Rule 16 | 99 | 92 | 18 | 1 | 18 | 26 | 249
4110 | 2018-03-21 | 2019-02-13 | 2019-05-29 | 2019-05-29 | COMP | 2019-10-14 | COMP | 2019-10-21 | COMP | 2021-02-25 | COMP | 2021-04-20 | COMP | Rule 15/16 | 227 | 74 | 97 | 6 | 338 | 39 | 776
4742 | 2018-03-21 | 2018-03-24 | 2018-11-08 | 2018-11-20 | COMP | 2018-11-30 | COMP | 2019-08-30 | COMP | 2020-07-28 | COMP | 2020-10-09 | COMP | Rule 15/16 | 3 | 161 | 7 | 190 | 229 | 53 | 646
4779 | 2018-03-21 | 2018-03-30 | 2018-07-27 | 2018-07-27 | COMP | 2018-11-05 | COMP | 2019-02-11 | COMP | 2019-05-08 | COMP | 2019-05-29 | COMP | Rule 16 | 8 | 84 | 71 | 65 | 62 | 15 | 300
4905 | 2018-03-21 | 2018-04-11 | 2018-05-10 | 2018-05-10 | COMP | 2018-07-03 | COMP | 2018-07-03 | COMP | 2019-03-18 | COMP | 2019-03-27 | COMP | Rule 16 | 16 | 22 | 38 | 1 | 176 | 8 | 256
4919 | 2018-03-21 | 2018-04-12 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-12 | COMP | 2018-11-26 | COMP | 2019-01-08 | COMP | 2019-01-30 | COMP | Rule 15/16 | 17 | 109 | 21 | 29 | 30 | 16 | 217
5059 | 2018-03-21 | 2018-04-26 | 2018-09-18 | 2018-09-18 | COMP | 2018-10-05 | COMP | 2020-05-15 | COMP | 2020-09-08 | COMP | 2020-10-15 | COMP | Rule 16 | 27 | 101 | 14 | 404 | 81 | 28 | 650
5060 | 2018-03-21 | 2018-04-26 | 2018-09-18 | 2020-07-03 | COMP | 2020-07-31 | COMP | 2020-09-21 | COMP | 2020-09-08 | COMP | 2020-10-21 | COMP | Rule 16 | 27 | 101 | 21 | 36 | 0 | 23 | 654
5081 | 2018-03-21 | 2018-04-29 | 2018-09-18 | 2018-09-18 | COMP | 2018-10-31 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-03-14 | COMP | Rule 16 | 28 | 99 | 32 | 61 | 1 | 30 | 247
5136 | 2018-03-21 | 2018-05-03 | 2018-09-06 | 2018-09-06 | COMP | 2018-10-30 | COMP | 2018-12-13 | COMP | 2019-09-01 | INPR | 2019-02-25 | COMP | Rule 16 | 32 | 88 | 39 | 30 |  |  | 234
5179 | 2018-03-21 | 2018-05-07 | 2018-08-27 | 2018-08-27 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-10-21 | INPR | 2019-05-30 | COMP | Rule 16 | 34 | 79 | 46 | 1 |  |  | 301
5260 | 2018-03-21 | 2018-05-15 | 2018-07-18 | 2020-11-16 | COMP | 2021-03-15 | COMP | 2021-03-16 | COMP | 2021-03-17 | COMP | 2021-04-20 | COMP | Rule 16 | 40 | 45 | 80 | 2 | 2 | 25 | 776
5276 | 2018-03-21 | 2018-05-16 | 2018-08-06 | 2018-08-06 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2020-01-19 | INPR | 2019-08-19 | COMP | Rule 16 | 41 | 57 | 233 | 1 |  |  | 357
5284 | 2018-03-21 | 2018-05-17 | 2018-09-05 | 2018-09-05 | COMP | 2019-12-27 | NOTN | 2019-12-27 | COMP | 2019-12-27 | COMP | 2020-02-25 | COMP | Other | 42 | 77 |  | 329 | 1 | 40 | 485
5419 | 2018-03-21 | 2018-05-30 | 2019-02-08 | 2019-02-08 | COMP | 2019-04-03 | COMP | 2019-05-28 | COMP | 2019-05-15 | COMP | 2019-07-01 | COMP | Rule 16 | 50 | 175 | 38 | 39 | 0 | 25 | 323
5510 | 2018-03-21 | 2018-06-05 | 2018-06-05 | 2018-06-05 | COMP | 2018-07-11 | COMP | 2018-07-11 | COMP | 2019-09-22 | INPR | 2019-06-13 | COMP | Rule 16 | 54 | 1 | 26 | 1 |  |  | 311
5527 | 2018-03-21 | 2018-06-12 | 2018-12-16 | 2018-12-16 | COMP | 2018-12-17 | NOTN | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-03-28 | COMP | Other | 59 | 129 |  | 1 | 1 | 70 | 257
5799 | 2018-03-21 | 2018-07-03 | 2018-10-18 | 2018-10-18 | COMP | 2018-11-02 | COMP | 2019-01-28 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | Rule 16 | 74 | 76 | 12 | 56 | 7 | 1 | 221
5847 | 2018-03-21 | 2018-07-07 | 2018-12-08 | 2019-01-16 | COMP | 2019-02-26 | COMP | 2019-04-02 | COMP | 2019-04-01 | COMP | 2019-06-18 | COMP | Rule 15/16 | 76 | 106 | 28 | 26 | 0 | 55 | 314
5966 | 2018-03-21 | 2018-07-17 | 2018-11-27 | 2019-02-25 | COMP | 2019-03-05 | COMP | 2019-03-19 | COMP | 2019-03-08 | COMP | 2019-04-20 | COMP | Rule 16 | 83 | 92 | 7 | 11 | 0 | 24 | 273
6171 | 2018-03-21 | 2018-08-02 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-03-06 | COMP | 2019-03-18 | COMP | Rule 16 | 95 | 75 | 29 | 1 | 45 | 9 | 249
6361 | 2018-03-21 | 2018-08-14 | 2018-12-04 | 2018-12-04 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2020-10-02 | COMP | 2020-10-29 | COMP | Rule 16 | 103 | 77 | 131 | 1 | 333 | 20 | 660
6880 | 2018-03-21 | 2018-09-14 | 2018-09-19 | 2018-09-27 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2018-12-20 | COMP | 2019-01-04 | COMP | Rule 16 | 125 | 4 | 20 | 1 | 39 | 10 | 200
7497 | 2018-03-21 | 2018-10-16 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-02-07 | COMP | 2019-02-28 | COMP | Rule 16 | 147 | 59 | 7 | 1 | 12 | 15 | 237
7544 | 2018-03-21 | 2018-10-19 | 2018-10-22 | 2018-10-22 | COMP | 2018-10-31 | COMP | 2018-10-31 | COMP | 2019-10-17 | COMP | 2020-01-06 | COMP | Rule 16 | 150 | 2 | 8 | 1 | 242 | 53 | 451
8184 | 2018-03-21 | 2018-11-19 | 2019-02-04 | 2019-02-04 | COMP | 2019-03-18 | COMP | 2019-04-01 | COMP | 2020-01-19 | INPR | 2019-08-17 | COMP | Rule 16 | 170 | 51 | 30 | 11 |  |  | 356
8786 | 2018-03-21 | 2018-12-28 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-12 | COMP | 2019-06-19 | COMP | 2019-06-14 | COMP | 2019-07-09 | COMP | Rule 16 | 196 | 44 | 30 | 48 | 0 | 14 | 328
9486 | 2018-03-21 | 2019-02-06 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-12-29 | INPR | 2019-09-10 | COMP | Rule 16 | 222 | 91 | 7 | 1 |  |  | 372
3225 | 2018-03-22 | 2018-03-24 | 2018-06-14 | 2018-06-14 | COMP | 2018-07-03 | COMP | 2018-07-03 | COMP | 2019-08-01 | COMP | 2019-08-13 | COMP | Rule 16 | 2 | 58 | 14 | 1 | 272 | 9 | 352
3358 | 2018-03-22 | 2018-04-12 | 2018-06-13 | 2018-06-13 | COMP | 2019-06-13 | COMP | 2019-06-19 | COMP | 2019-07-03 | COMP | 2019-07-21 | COMP | Rule 16 | 16 | 44 | 252 | 5 | 11 | 12 | 335
3416 | 2018-03-22 | 2018-04-23 | 2018-06-05 | 2018-06-05 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2018-12-04 | COMP | 2019-01-31 | COMP | Rule 16 | 23 | 31 | 125 | 1 | 2 | 40 | 217
3544 | 2018-03-22 | 2018-05-14 | 2019-01-25 | 2019-01-25 | COMP | 2019-04-08 | COMP | 2019-04-10 | COMP | 2023-09-02 | INPR | 2019-10-04 | COMP | Rule 15/16 | 38 | 176 | 51 | 3 |  |  | 389
3874 | 2018-03-22 | 2018-09-04 | 2018-10-19 | 2018-10-19 | COMP | 2018-12-05 | COMP | 2018-12-12 | COMP | 2019-01-28 | COMP | 2019-02-28 | COMP | Rule 16 | 116 | 34 | 31 | 6 | 31 | 23 | 236
4068 | 2018-03-22 | 2019-01-07 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-10 | COMP | 2021-03-14 | COMP |  |  | 2022-05-07 | COMP | Rule 16 | 200 | 335 | 26 | 190 |  |  | 1040
4761 | 2018-03-22 | 2018-03-29 | 2018-06-18 | 2018-06-18 | COMP | 2018-08-21 | COMP | 2019-01-23 | COMP | 2020-01-17 | COMP | 2020-02-04 | COMP | Rule 16 | 6 | 57 | 46 | 105 | 249 | 12 | 470
4763 | 2018-03-22 | 2018-03-30 | 2018-06-01 | 2018-06-01 | COMP | 2019-07-01 | COMP | 2019-07-02 | COMP | 2019-07-08 | COMP | 2019-08-15 | COMP | Rule 16 | 7 | 45 | 272 | 2 | 4 | 29 | 354
4815 | 2018-03-22 | 2018-03-31 | 2018-09-19 | 2019-02-05 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-02-16 | COMP | 2019-03-20 | COMP | Rule 16 | 7 | 120 | 6 | 1 | 4 | 22 | 250
4852 | 2018-03-22 | 2018-04-04 | 2018-05-10 | 2018-05-10 | COMP | 2018-06-26 | COMP | 2018-06-26 | COMP | 2020-01-10 | COMP | 2020-01-15 | COMP | Rule 16 | 10 | 27 | 33 | 1 | 387 | 4 | 457
4870 | 2018-03-22 | 2018-04-05 | 2018-06-14 | 2018-08-01 | COMP | 2018-08-02 | NOTN | 2018-08-23 | COMP | 2018-06-20 | NOTN | 2021-01-21 | COMP | Other | 11 | 50 |  | 17 |  |  | 713
4918 | 2018-03-22 | 2018-04-11 | 2018-05-31 | 2018-05-31 | COMP | 2018-07-05 | NOTN | 2018-09-07 | COMP | 2019-03-07 | COMP | 2019-04-15 | COMP | Other | 15 | 36 |  | 70 | 123 | 28 | 268
4964 | 2018-03-22 | 2018-04-16 | 2018-09-19 | 2018-09-19 | COMP | 2018-09-24 | NOTN | 2018-12-10 | COMP | 2019-01-28 | COMP | 2019-02-06 | COMP | Other | 18 | 110 |  | 56 | 33 | 8 | 221
5017 | 2018-03-22 | 2018-04-24 | 2018-09-06 | 2018-09-06 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2018-11-26 | COMP | 2019-02-26 | COMP | Rule 16 | 24 | 95 | 43 | 1 | 13 | 63 | 234
5037 | 2018-03-22 | 2018-04-26 | 2018-09-07 | 2018-09-07 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2020-11-19 | COMP | 2020-12-22 | COMP | Rule 15/16 | 26 | 94 | 291 | 1 | 265 | 22 | 694
5049 | 2018-03-22 | 2018-04-26 | 2018-09-13 | 2018-09-13 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-02-26 | COMP | Rule 16 | 26 | 98 | 90 | 1 | 1 | 23 | 234
5139 | 2018-03-22 | 2018-05-03 | 2018-10-10 | 2018-10-10 | COMP | 2019-03-05 | COMP | 2019-03-19 | COMP | 2019-03-13 | COMP | 2019-06-13 | COMP | Rule 16 | 31 | 112 | 98 | 11 | 0 | 62 | 310
5197 | 2018-03-22 | 2018-05-09 | 2018-08-28 | 2018-08-28 | COMP | 2018-11-05 | COMP | 2019-05-02 | COMP | 2019-12-23 | COMP | 2020-01-28 | COMP | Rule 16 | 35 | 78 | 49 | 122 | 162 | 24 | 465
5456 | 2018-03-22 | 2018-06-01 | 2018-10-10 | 2018-10-10 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-01-18 | COMP | 2019-02-19 | COMP | Rule 16 | 51 | 92 | 36 | 1 | 33 | 21 | 229
5644 | 2018-03-22 | 2018-06-22 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-02-02 | COMP | 2019-03-01 | COMP | Rule 16 | 66 | 74 | 44 | 1 | 37 | 19 | 237
5676 | 2018-03-22 | 2018-06-25 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-03 | COMP | 2018-11-16 | COMP | 2018-10-28 | COMP | 2019-01-10 | COMP | Rule 16 | 67 | 61 | 11 | 32 | 0 | 36 | 203
11486 | 2018-03-22 | 2019-04-30 | 2019-06-23 | 2019-06-23 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-08-11 | COMP | 2019-09-06 | COMP | Rule 16 | 279 | 38 | 10 | 1 | 25 | 19 | 369
12994 | 2018-03-22 | 2019-07-03 | 2019-10-25 | 2019-11-05 | COMP | 2020-01-28 | COMP | 2020-02-06 | COMP | 2020-02-11 | COMP | 2020-07-01 | COMP | Rule 15/16 | 324 | 81 | 55 | 8 | 4 | 100 | 574
13351 | 2018-03-22 | 2019-07-22 | 2020-02-05 | 2022-05-13 | COMP | 2022-06-07 | COMP | 2022-07-13 | COMP |  | INPR | 2023-08-08 | COMP | Rule 16 | 336 | 136 | 17 | 25 |  |  | 1353
26750 | 2018-03-22 | 2021-04-01 | 2021-04-30 | 2021-04-30 | COMP | 2021-05-05 | COMP | 2021-08-30 | COMP |  |  | 2021-10-13 | COMP | Rule 16 | 762 | 22 | 4 | 82 |  |  | 898
3296 | 2018-03-23 | 2018-04-03 | 2018-08-24 | 2018-08-17 | COMP | 2018-09-07 | COMP | 2018-12-12 | COMP | 2018-12-23 | COMP | 2019-08-12 | COMP | Rule 15/16 | 8 | 102 | 15 | 66 | 8 | 160 | 350
3297 | 2018-03-23 | 2018-04-03 | 2018-05-03 | 2018-05-03 | COMP | 2018-05-08 | COMP | 2018-05-09 | COMP | 2019-04-02 | COMP | 2019-05-17 | COMP | Rule 16 | 8 | 23 | 4 | 2 | 225 | 34 | 291
3338 | 2018-03-23 | 2018-04-10 | 2018-05-18 | 2018-05-18 | COMP | 2018-06-21 | COMP | 2018-08-17 | COMP | 2021-03-16 | COMP | 2021-03-18 | COMP | Rule 16 | 13 | 29 | 24 | 41 | 646 | 3 | 751
3763 | 2018-03-23 | 2018-06-30 | 2019-10-01 | 2019-08-20 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2019-11-05 | COMP | 2019-12-24 | COMP | Rule 16 | 70 | 315 | 41 | 1 | 15 | 33 | 442
4961 | 2018-03-23 | 2018-04-16 | 2018-08-10 | 2019-01-12 | COMP | 2020-01-08 | NOTN | 2018-08-14 | COMP | 2018-08-14 | COMP | 2021-05-03 | COMP | Other | 17 | 83 |  |  | 1 | 683 | 783
5021 | 2018-03-23 | 2018-04-24 | 2018-10-03 | 2018-10-03 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-03-20 | COMP | 2019-04-18 | COMP | Rule 16 | 23 | 114 | 97 | 1 | 18 | 22 | 270
5317 | 2018-03-23 | 2018-05-21 | 2018-06-10 | 2018-06-10 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2021-01-12 | COMP | 2021-02-25 | COMP | Rule 16 | 42 | 14 | 339 | 1 | 313 | 31 | 736
5518 | 2018-03-23 | 2018-06-08 | 2019-01-30 | 2019-01-30 | COMP | 2019-04-08 | COMP | 2019-05-03 | COMP | 2019-09-19 | COMP | 2019-12-16 | COMP | Rule 15/16 | 55 | 161 | 48 | 20 | 97 | 60 | 436
5761 | 2018-03-23 | 2018-07-02 | 2018-09-26 | 2018-12-09 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-01-05 | COMP | 2019-02-07 | COMP | Rule 15/16 | 71 | 61 | 18 | 1 | 1 | 23 | 221
5927 | 2018-03-23 | 2018-07-12 | 2019-01-24 | 2019-01-24 | COMP | 2019-03-11 | COMP | 2020-02-25 | COMP | 2021-10-23 | INPR | 2020-08-25 | COMP | Rule 15/16 | 78 | 134 | 32 | 242 |  |  | 612
6077 | 2018-03-23 | 2018-07-23 | 2018-10-31 | 2018-10-31 | COMP | 2019-02-22 | COMP | 2019-03-27 | COMP | 2019-05-30 | COMP | 2019-06-24 | COMP | Rule 16 | 85 | 72 | 76 | 24 | 46 | 18 | 316
6250 | 2018-03-23 | 2018-08-07 | 2018-08-14 | 2018-08-14 | COMP | 2019-02-20 | COMP | 2019-02-20 | INPR | 2019-07-21 | REQD | 2019-04-04 | COMP | Rule 16 | 96 | 6 | 129 |  |  |  | 260
6524 | 2018-03-23 | 2018-08-25 | 2019-02-25 | 2019-04-13 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2021-02-27 | INPR | 2019-12-12 | COMP | Rule 16 | 109 | 123 | 7 | 1 |  |  | 434
6839 | 2018-03-23 | 2018-09-12 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-07 | COMP | 2019-01-07 | COMP | 2019-01-28 | COMP | 2019-03-11 | COMP | Rule 16 | 121 | 39 | 41 | 1 | 15 | 30 | 242
7001 | 2018-03-23 | 2018-09-22 | 2019-01-05 | 2019-01-05 | COMP | 2019-12-03 | COMP | 2019-12-30 | COMP | 2019-12-16 | COMP | 2020-02-06 | COMP | Rule 16 | 128 | 70 | 229 | 19 | 0 | 27 | 471
9592 | 2018-03-23 | 2019-02-08 | 2019-03-25 | 2019-03-25 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2019-08-22 | COMP | Rule 16 | 222 | 31 | 79 | 1 | 2 | 28 | 358
9806 | 2018-03-23 | 2019-02-19 | 2019-03-28 | 2019-11-05 | COMP | 2019-11-19 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-01-03 | COMP | Rule 16 | 228 | 28 | 10 | 6 | 1 | 25 | 448
10133 | 2018-03-23 | 2019-03-04 | 2019-04-11 | 2019-05-08 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-05-23 | COMP | 2019-06-20 | COMP | Rule 16 | 237 | 29 | 3 | 1 | 10 | 20 | 314
3510 | 2018-03-24 | 2018-05-09 | 2018-10-29 | 2018-10-29 | COMP | 2018-12-17 | COMP | 2019-03-19 | COMP | 2019-05-09 | COMP | 2019-07-21 | COMP | Rule 16 | 33 | 121 | 33 | 63 | 38 | 50 | 333
3968 | 2018-03-25 | 2018-11-01 | 2019-02-21 | 2019-02-21 | COMP | 2020-04-29 | COMP | 2020-04-24 | COMP | 2020-04-23 | COMP | 2020-09-01 | COMP | Rule 16 | 156 | 74 | 300 |  | 0 | 92 | 616
5524 | 2018-03-25 | 2018-06-07 | 2018-09-25 | 2018-09-25 | COMP | 2018-11-01 | COMP | 2018-12-21 | COMP | 2018-11-19 | COMP | 2019-02-01 | COMP | Rule 16 | 53 | 77 | 28 | 34 | 0 | 28 | 216
3409 | 2018-03-26 | 2018-04-20 | 2018-08-03 | 2018-08-03 | COMP | 2020-03-23 | COMP | 2020-04-07 | COMP | 2020-03-21 | COMP | 2020-05-06 | COMP | Other | 20 | 74 | 409 | 12 | 0 | 22 | 533
3417 | 2018-03-26 | 2018-04-23 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-24 | COMP | 2019-08-23 | INPR | 2019-08-20 | COMP | 2019-09-11 | COMP | Rule 15/16 | 21 | 230 | 24 |  |  |  | 370
3595 | 2018-03-26 | 2018-05-23 | 2018-09-06 | 2018-09-06 | COMP | 2018-11-01 | COMP | 2018-11-13 | COMP | 2019-04-23 | COMP | 2019-05-31 | COMP | Rule 16 | 43 | 74 | 41 | 8 | 110 | 28 | 299
3599 | 2018-03-26 | 2018-05-23 | 2018-06-18 | 2018-06-18 | COMP | 2018-07-25 | COMP | 2018-12-07 | COMP | 2018-12-22 | COMP | 2019-04-04 | COMP | Rule 16 | 43 | 18 | 27 | 94 | 11 | 70 | 259
3811 | 2018-03-26 | 2018-07-24 | 2019-04-03 | 2019-04-03 | COMP | 2019-09-04 | COMP | 2019-09-20 | COMP | 2020-06-07 | COMP | 2020-10-13 | COMP | Rule 15/16 | 85 | 174 | 108 | 13 | 178 | 91 | 645
3812 | 2018-03-26 | 2018-07-24 | 2019-02-26 | 2019-02-26 | COMP | 2020-03-17 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-11-02 | COMP | Rule 15/16 | 85 | 148 | 266 | 55 | 1 | 109 | 659
4867 | 2018-03-26 | 2018-04-05 | 2018-05-21 | 2018-05-21 | COMP | 2018-06-13 | COMP | 2018-06-13 | COMP | 2020-01-22 | COMP | 2020-02-27 | COMP | Rule 16 | 9 | 33 | 17 | 1 | 403 | 26 | 484
4968 | 2018-03-26 | 2018-04-16 | 2018-06-14 | 2018-06-14 | COMP | 2018-08-22 | COMP | 2019-04-29 | COMP | 2019-04-28 | COMP | 2019-06-11 | COMP | Rule 15/16 | 16 | 43 | 49 | 171 | 0 | 31 | 306
5105 | 2018-03-26 | 2018-04-30 | 2018-06-06 | 2018-06-06 | COMP | 2018-10-16 | COMP | 2018-07-17 | COMP | 2019-01-11 | COMP | 2019-01-24 | COMP | Rule 16 | 26 | 27 | 93 |  | 123 | 9 | 210
5457 | 2018-03-26 | 2018-06-01 | 2018-10-12 | 2018-10-12 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-02-15 | COMP | 2019-03-29 | COMP | Rule 16 | 49 | 94 | 61 | 1 | 25 | 30 | 255
5653 | 2018-03-26 | 2018-06-24 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-19 | COMP | 2019-07-09 | COMP | 2019-04-19 | COMP | 2019-08-08 | COMP | Rule 15/16 | 64 | 143 | 41 | 79 | 0 | 23 | 347
5903 | 2018-03-26 | 2018-07-10 | 2018-09-15 | 2018-09-15 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-21 | COMP | 2019-09-11 | COMP | Rule 16 | 75 | 48 | 228 | 1 | 7 | 15 | 370
6181 | 2018-03-26 | 2018-08-03 | 2018-11-29 | 2018-11-29 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-08-11 | COMP | 2019-09-04 | COMP | Rule 16 | 93 | 81 | 95 | 1 | 82 | 17 | 365
6274 | 2018-03-26 | 2018-08-07 | 2018-09-12 | 2018-09-12 | COMP | 2018-09-27 | COMP | 2018-09-27 | COMP | 2019-03-25 | COMP | 2019-05-09 | COMP | Rule 16 | 95 | 26 | 12 | 1 | 121 | 34 | 284
6415 | 2018-03-26 | 2018-08-16 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-04-12 | COMP | 2019-04-26 | COMP | Rule 16 | 102 | 86 | 18 | 1 | 62 | 11 | 275
6543 | 2018-03-26 | 2018-08-27 | 2018-10-31 | 2019-01-14 | COMP | 2019-01-15 | NOTN | 2019-01-15 | COMP | 2018-12-05 | COMP | 2019-01-24 | COMP | Other | 109 | 47 |  | 2 | 0 | 7 | 210
7116 | 2018-03-26 | 2018-09-28 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-08-12 | COMP | Rule 16 | 132 | 93 | 54 | 1 | 1 | 73 | 349
7204 | 2018-03-26 | 2018-10-02 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2018-11-30 | COMP | 2019-03-12 | COMP | Rule 16 | 134 | 33 | 9 | 1 | 0 | 68 | 242
9554 | 2018-03-26 | 2019-02-07 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-16 | COMP | 2019-06-24 | COMP | 2020-11-25 | COMP | 2020-12-10 | COMP | Rule 16 | 220 | 37 | 12 | 49 | 361 | 10 | 684
10433 | 2018-03-26 | 2019-03-15 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-19 | COMP | 2019-08-08 | COMP | 2020-07-22 | COMP | 2020-08-24 | COMP | Rule 16 | 245 | 53 | 37 | 15 | 241 | 24 | 610
11674 | 2018-03-26 | 2019-05-07 | 2019-07-30 | 2019-07-30 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-01-30 | COMP | 2020-03-04 | COMP | Rule 16 | 282 | 59 | 79 | 1 | 48 | 24 | 488
13292 | 2018-03-26 | 2019-07-18 | 2020-03-13 | 2020-03-13 | COMP | 2020-06-19 | COMP | 2020-07-17 | COMP | 2022-02-14 | COMP | 2020-11-11 | COMP | Rule 15/16 | 332 | 164 | 70 | 21 | 397 |  | 665
18181 | 2018-03-26 | 2020-03-13 | 2020-07-16 | 2020-07-16 | COMP | 2020-10-22 | COMP | 2020-10-23 | COMP | 2020-10-22 | COMP | 2020-11-18 | COMP | Rule 16 | 495 | 89 | 70 | 2 | 0 | 18 | 670
3370 | 2018-03-27 | 2018-04-14 | 2018-05-28 | 2018-05-28 | COMP | 2018-08-30 | COMP | 2018-09-05 | COMP | 2018-09-06 | COMP | 2019-05-09 | COMP | Rule 16 | 14 | 30 | 67 | 4 | 2 | 169 | 283
3450 | 2018-03-27 | 2018-04-30 | 2018-06-15 | 2018-06-15 | COMP | 2018-12-17 | COMP | 2018-09-26 | COMP | 2019-01-10 | COMP | 2019-01-12 | COMP | Rule 16 | 25 | 34 | 127 |  | 72 | 2 | 201
3573 | 2018-03-27 | 2018-05-18 | 2018-07-11 | 2018-07-11 | COMP | 2019-01-09 | COMP | 2019-01-16 | COMP | 2019-06-29 | INPR | 2019-02-07 | COMP | Rule 16 | 39 | 37 | 125 | 6 |  |  | 219
3992 | 2018-03-27 | 2018-11-13 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-02-08 | COMP | 2019-11-14 | COMP | Rule 16 | 162 | 36 | 5 | 1 | 20 | 195 | 414
4818 | 2018-03-27 | 2018-04-01 | 2018-04-24 | 2018-04-24 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2020-01-23 | COMP | 2020-02-18 | COMP | Rule 16 | 4 | 17 | 150 | 1 | 290 | 18 | 476
4954 | 2018-03-27 | 2018-04-14 | 2018-10-10 | 2019-03-26 | COMP | 2019-04-18 | COMP | 2019-04-19 | COMP | 2019-08-27 | COMP | 2019-09-04 | COMP | Rule 16 | 14 | 125 | 18 | 2 | 91 | 6 | 364
4993 | 2018-03-27 | 2018-04-20 | 2018-07-30 | 2019-04-03 | COMP | 2019-04-24 | COMP | 2019-10-01 | COMP | 2022-09-13 | COMP | 2023-05-06 | COMP | Rule 16 | 19 | 70 | 16 | 112 | 743 | 162 | 1286
5013 | 2018-03-27 | 2018-04-25 | 2018-05-30 | 2018-05-30 | COMP | 2018-09-06 | COMP | 2018-09-06 | COMP | 2019-03-19 | COMP | 2019-05-01 | COMP | Rule 16 | 22 | 25 | 70 | 1 | 132 | 32 | 277
5132 | 2018-03-27 | 2018-05-02 | 2018-08-25 | 2018-08-25 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2019-11-24 | INPR | 2019-07-31 | COMP | Rule 15/16 | 27 | 81 | 60 | 1 |  |  | 340
5298 | 2018-03-27 | 2018-05-18 | 2018-08-06 | 2018-11-28 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2020-02-29 | INPR | 2019-10-17 | COMP | Rule 16 | 39 | 55 | 112 | 1 |  |  | 395
5467 | 2018-03-27 | 2018-06-01 | 2018-09-04 | 2018-09-04 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-11-12 | COMP | 2020-01-14 | COMP | Rule 16 | 48 | 66 | 279 | 1 | 22 | 42 | 453
5500 | 2018-03-27 | 2018-06-05 | 2018-06-28 | 2018-12-05 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-11 | COMP | 2019-05-22 | COMP | Rule 16 | 50 | 18 | 67 | 1 | 22 | 30 | 292
5549 | 2018-03-27 | 2018-06-13 | 2018-11-01 | 2018-11-01 | COMP | 2019-03-08 | COMP | 2019-05-02 | COMP | 2019-04-09 | COMP | 2019-05-31 | COMP | Rule 16 | 56 | 100 | 85 | 40 | 0 | 21 | 298
5739 | 2018-03-27 | 2018-06-28 | 2018-09-12 | 2018-09-20 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-08-13 | COMP | 2019-09-28 | COMP | Rule 16 | 67 | 53 | 99 | 1 | 127 | 33 | 381
6233 | 2018-03-27 | 2018-08-06 | 2019-04-27 | 2019-06-27 | COMP | 2019-08-09 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-03-05 | COMP | Rule 15/16 | 93 | 182 | 31 | 120 | 1 | 23 | 488
6441 | 2018-03-27 | 2018-08-18 | 2018-12-05 | 2018-12-05 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-04-26 | COMP | 2019-05-03 | COMP | Rule 16 | 102 | 74 | 75 | 1 | 25 | 6 | 279
6622 | 2018-03-27 | 2018-08-31 | 2018-10-28 | 2018-10-28 | COMP | 2018-12-11 | COMP | 2019-02-14 | COMP | 2021-03-08 | COMP | 2020-02-06 | COMP | Rule 15/16 | 112 | 40 | 29 | 45 | 518 |  | 469
6849 | 2018-03-27 | 2018-09-13 | 2018-09-28 | 2018-09-28 | COMP | 2018-12-12 | NOTN | 2018-12-12 | COMP | 2019-07-21 | INPR | 2019-02-27 | COMP | Other | 120 | 12 |  | 51 |  |  | 232
6868 | 2018-03-27 | 2018-09-13 | 2018-10-01 | 2018-11-05 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2018-11-21 | COMP | 2019-01-23 | COMP | Rule 16 | 120 | 13 | 6 | 1 | 7 | 41 | 208
9593 | 2018-03-27 | 2019-02-08 | 2019-03-28 | 2019-04-04 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2021-05-30 | INPR | 2019-11-13 | COMP | Rule 16 | 220 | 34 | 141 | 1 |  |  | 413
10145 | 2018-03-27 | 2019-03-05 | 2019-06-11 | 2019-06-11 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2020-07-13 | COMP | 2020-11-04 | COMP | Rule 16 | 236 | 70 | 48 | 1 | 228 | 82 | 660
11950 | 2018-03-27 | 2019-05-17 | 2019-06-10 | 2019-06-10 | COMP | 2019-06-20 | COMP | 2019-06-20 | INPR | 2019-06-24 | COMP | 2019-06-24 | COMP | Rule 16 | 289 | 16 | 9 |  |  |  | 314
15900 | 2018-03-27 | 2019-11-26 | 2020-04-21 | 2020-04-21 | COMP | 2020-06-16 | COMP | 2020-07-14 | COMP | 2020-06-22 | COMP | 2020-08-14 | COMP | Rule 16 | 422 | 100 | 40 | 21 | 0 | 24 | 603
3455 | 2018-03-28 | 2018-04-30 | 2018-10-16 | 2018-10-16 | COMP | 2019-03-06 | COMP | 2019-03-11 | COMP | 2019-06-05 | COMP | 2019-07-10 | COMP | Rule 15/16 | 24 | 119 | 95 | 4 | 62 | 25 | 324
3463 | 2018-03-28 | 2018-05-01 | 2018-05-10 | 2018-05-10 | COMP | 2018-06-12 | COMP | 2018-06-25 | COMP | 2018-10-01 | COMP | 2022-05-10 | COMP | Rule 16 | 25 | 8 | 23 | 10 | 69 | 908 | 1038
3576 | 2018-03-28 | 2018-05-17 | 2018-09-05 | 2018-09-05 | COMP | 2018-10-01 | COMP | 2018-12-04 | COMP | 2018-11-08 | COMP | 2019-02-05 | COMP | Rule 16 | 37 | 77 | 19 | 44 | 0 | 43 | 216
3794 | 2018-03-28 | 2018-07-16 | 2018-10-01 | 2018-10-01 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-11-18 | COMP | 2019-11-25 | COMP | Rule 16 | 77 | 55 | 124 | 1 | 162 | 6 | 420
3885 | 2018-03-28 | 2018-09-13 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-22 | NOTN | 2018-11-22 | COMP | 2018-12-11 | COMP | 2019-05-07 | COMP | Other | 119 | 35 |  | 15 | 12 | 102 | 280
4795 | 2018-03-28 | 2018-03-31 | 2018-08-07 | 2019-01-17 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2021-02-27 | INPR | 2019-06-13 | COMP | Rule 15/16 | 3 | 90 | 13 | 1 |  |  | 306
4796 | 2018-03-28 | 2018-03-31 | 2018-12-04 | 2018-12-04 | COMP | 2019-01-09 | COMP | 2019-01-25 | COMP | 2019-09-22 | INPR | 2019-05-22 | COMP | Rule 15/16 | 3 | 171 | 25 | 12 |  |  | 291
4925 | 2018-03-28 | 2018-04-12 | 2018-07-18 | 2018-07-18 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-03-08 | COMP | 2019-10-23 | COMP | Rule 16 | 12 | 68 | 78 | 1 | 83 | 161 | 398
4926 | 2018-03-28 | 2018-04-12 | 2018-07-18 | 2018-07-18 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-03-08 | COMP | 2019-04-11 | COMP | Rule 16 | 12 | 68 | 78 | 1 | 83 | 25 | 262
4927 | 2018-03-28 | 2018-04-12 | 2018-06-14 | 2018-06-14 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-03-08 | COMP | 2019-07-16 | COMP | Rule 16 | 12 | 45 | 101 | 1 | 83 | 91 | 328
5133 | 2018-03-28 | 2018-05-02 | 2018-07-25 | 2018-07-25 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-11-24 | INPR | 2019-07-31 | COMP | Rule 16 | 26 | 59 | 71 | 1 |  |  | 339
5166 | 2018-03-28 | 2018-05-07 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-25 | COMP | 2019-09-17 | COMP | 2021-03-27 | INPR | 2020-03-03 | COMP | Rule 15/16 | 29 | 142 | 40 | 164 |  |  | 485
5237 | 2018-03-28 | 2018-05-14 | 2018-08-22 | 2018-08-22 | COMP | 2018-09-04 | COMP | 2018-10-01 | COMP | 2018-12-20 | COMP | 2019-01-28 | COMP | Rule 16 | 34 | 71 | 9 | 20 | 56 | 25 | 210
5282 | 2018-03-28 | 2018-05-17 | 2018-08-01 | 2018-10-05 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-03-30 | COMP | 2020-06-09 | COMP | Rule 16 | 37 | 53 | 363 | 1 | 8 | 51 | 554
5960 | 2018-03-28 | 2018-07-16 | 2019-03-27 | 2019-03-27 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-09-26 | COMP | 2019-09-30 | COMP | Rule 15/16 | 77 | 175 | 32 | 1 | 98 | 3 | 381
6248 | 2018-03-28 | 2018-08-06 | 2018-09-27 | 2018-09-27 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-01-28 | COMP | 2019-02-01 | COMP | Rule 16 | 92 | 38 | 55 | 1 | 28 | 5 | 214
6411 | 2018-03-28 | 2018-08-16 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-06 | COMP | 2019-03-14 | COMP | 2019-03-05 | COMP | 2019-03-16 | COMP | Rule 16 | 100 | 71 | 7 | 67 | 0 | 2 | 243
6556 | 2018-03-28 | 2018-08-27 | 2019-02-26 | 2019-02-26 | COMP | 2019-06-26 | COMP | 2019-07-08 | COMP |  | INPR | 2019-10-08 | COMP | Other | 107 | 124 | 86 | 8 |  |  | 387
7406 | 2018-03-28 | 2018-10-11 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-26 | COMP | 2019-05-14 | COMP | 2019-07-16 | COMP | 2019-08-17 | COMP | Rule 15/16 | 139 | 98 | 38 | 13 | 44 | 24 | 351
8593 | 2018-03-28 | 2018-12-11 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-25 | NOTN | 2019-03-25 | COMP | 2019-02-26 | NOTN | 2019-06-18 | COMP | Other | 179 | 46 |  | 26 |  |  | 309
8884 | 2018-03-28 | 2019-01-04 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-01 | COMP | 2019-03-08 | COMP | 2019-03-01 | COMP | 2019-05-28 | COMP | Rule 16 | 195 | 33 | 7 | 6 | 0 | 57 | 294
9516 | 2018-03-28 | 2019-02-06 | 2019-05-22 | 2019-05-22 | COMP | 2019-07-05 | COMP | 2020-03-19 | COMP |  |  | 2020-03-27 | COMP | Rule 16 | 217 | 75 | 31 | 177 |  |  | 503
10501 | 2018-03-28 | 2019-03-18 | 2019-04-17 | 2020-10-19 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2020-12-29 | COMP | 2021-02-16 | COMP | Rule 16 | 244 | 23 | 3 | 1 | 46 | 33 | 726
10668 | 2018-03-28 | 2019-03-25 | 2019-06-19 | 2020-04-21 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | Rule 16 | 249 | 62 | 21 | 1 | 69 | 1 | 608
12812 | 2018-03-28 | 2019-06-24 | 2019-10-01 | 2019-10-01 | COMP | 2020-04-20 | COMP | 2020-07-23 | INPR | 2020-07-27 | COMP | 2020-08-27 | COMP | Rule 16 | 313 | 70 | 138 |  |  |  | 611
3400 | 2018-03-29 | 2018-04-18 | 2018-08-09 | 2018-08-09 | COMP | 2018-10-19 | COMP | 2018-10-23 | COMP | 2019-04-19 | COMP | 2019-06-03 | COMP | Rule 16 | 15 | 80 | 51 | 3 | 122 | 31 | 297
3556 | 2018-03-29 | 2018-05-15 | 2018-09-03 | 2018-09-03 | COMP | 2019-01-31 | COMP | 2019-02-02 | COMP | 2019-09-21 | INPR | 2019-06-05 | COMP | Rule 16 | 34 | 77 | 102 | 2 |  |  | 299
3765 | 2018-03-29 | 2018-07-02 | 2018-08-28 | 2018-08-28 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-28 | COMP | Rule 16 | 67 | 41 | 171 | 1 | 1 | 17 | 293
4797 | 2018-03-29 | 2018-03-31 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-01 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-10-21 | COMP | Rule 15/16 | 2 | 120 | 9 | 214 | 1 | 53 | 395
4798 | 2018-03-29 | 2018-03-31 | 2018-12-07 | 2018-12-07 | COMP | 2019-01-25 | COMP | 2019-05-21 | COMP | 2019-05-06 | COMP | 2019-07-23 | COMP | Rule 16 | 2 | 174 | 33 | 82 | 0 | 44 | 332
4890 | 2018-03-29 | 2018-04-09 | 2018-09-20 | 2018-09-20 | COMP | 2019-02-27 | COMP | 2019-03-11 | COMP | 2019-04-18 | COMP | 2019-06-25 | COMP | Rule 15/16 | 8 | 116 | 108 | 9 | 29 | 48 | 313
4938 | 2018-03-29 | 2018-04-13 | 2019-01-25 | 2019-01-25 | COMP | 2019-01-31 | NOTN | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-04-10 | COMP | Other | 12 | 197 |  | 5 | 1 | 49 | 260
4939 | 2018-03-29 | 2018-04-13 | 2019-06-17 | 2019-06-17 | COMP | 2019-06-18 | NOTN | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-08-02 | COMP | Other | 12 | 296 |  | 4 | 1 | 31 | 340
4983 | 2018-03-29 | 2018-04-19 | 2018-09-21 | 2018-09-21 | COMP | 2019-01-08 | COMP | 2019-12-03 | COMP | 2019-12-10 | COMP | 2020-02-19 | COMP | Other | 16 | 109 | 73 | 228 | 6 | 48 | 475
5152 | 2018-03-29 | 2018-05-03 | 2018-09-05 | 2019-02-13 | COMP | 2019-05-23 | COMP | 2019-09-24 | COMP | 2019-09-06 | COMP | 2019-11-05 | COMP | Rule 15/16 | 26 | 87 | 71 | 86 | 0 | 31 | 406
5286 | 2018-03-29 | 2018-05-17 | 2018-06-26 | 2018-07-18 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-02-09 | COMP | 2019-04-26 | COMP | Rule 16 | 36 | 28 | 106 | 1 | 36 | 54 | 272
5301 | 2018-03-29 | 2018-05-20 | 2018-11-05 | 2018-11-05 | COMP | 2018-11-27 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-01-16 | COMP | Rule 16 | 37 | 118 | 14 | 11 | 1 | 25 | 202
6347 | 2018-03-29 | 2018-08-13 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-03-26 | COMP | 2019-04-13 | COMP | Rule 15/16 | 96 | 74 | 43 | 1 | 39 | 14 | 262
6733 | 2018-03-29 | 2018-09-10 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-04-23 | COMP | 2019-06-24 | COMP | Rule 15/16 | 115 | 148 | 9 | 1 | 0 | 43 | 312
7007 | 2018-03-29 | 2018-09-21 | 2018-09-29 | 2018-09-29 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-17 | COMP | Rule 16 | 124 | 6 | 124 | 1 | 1 | 13 | 265
7344 | 2018-03-29 | 2018-10-09 | 2018-11-01 | 2018-11-01 | COMP | 2018-12-28 | COMP | 2019-02-07 | COMP | 2019-02-05 | COMP | 2019-03-07 | COMP | Rule 16 | 136 | 18 | 38 | 28 | 0 | 20 | 236
7501 | 2018-03-29 | 2018-10-18 | 2020-02-12 | 2020-11-18 | COMP | 2021-01-15 | COMP | 2021-01-15 | COMP | 2020-12-16 | COMP | 2021-04-08 | COMP | Rule 15/16 | 143 | 329 | 39 | 1 | 0 | 58 | 762
8006 | 2018-03-29 | 2018-11-13 | 2019-04-29 | 2019-04-29 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-21 | COMP | 2019-09-05 | COMP | Rule 16 | 160 | 114 | 75 | 1 | 7 | 11 | 363
8325 | 2018-03-29 | 2018-11-27 | 2019-02-07 | 2019-02-07 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-08 | COMP | 2019-06-08 | COMP | Rule 16 | 168 | 50 | 39 | 1 | 4 | 44 | 301
8632 | 2018-03-29 | 2018-12-13 | 2019-08-28 | 2019-08-28 | COMP | 2019-10-15 | COMP | 2020-01-14 | INPR | 2023-04-15 | CANC | 2020-03-19 | COMP | Rule 15/16 | 180 | 179 | 34 |  |  |  | 496
8910 | 2018-03-29 | 2019-01-05 | 2019-08-09 | 2019-08-09 | COMP | 2019-10-23 | COMP | 2019-10-29 | COMP | 2021-02-27 | INPR | 2020-01-15 | COMP | Rule 15/16 | 194 | 151 | 53 | 5 |  |  | 452
10108 | 2018-03-29 | 2019-03-02 | 2019-04-27 | 2019-04-27 | COMP | 2019-05-06 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-08-22 | COMP | Rule 16 | 232 | 40 | 6 | 10 | 1 | 68 | 354
11442 | 2018-03-29 | 2019-04-27 | 2019-09-03 | 2019-09-03 | COMP | 2019-12-30 | COMP | 2020-01-08 | COMP | 2020-01-08 | COMP | 2020-02-26 | COMP | Rule 16 | 272 | 89 | 81 | 7 | 1 | 34 | 480
13635 | 2018-03-29 | 2019-08-02 | 2019-10-24 | 2019-12-18 | COMP | 2020-02-14 | COMP | 2020-03-20 | COMP | 2022-07-30 | INPR | 2020-04-23 | COMP | Rule 15/16 | 340 | 59 | 40 | 25 |  |  | 521
16357 | 2018-03-29 | 2019-12-26 | 2020-01-31 | 2020-01-31 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-11-20 | COMP | 2021-01-14 | COMP | Rule 15/16 | 439 | 25 | 92 | 1 | 116 | 36 | 704
20295 | 2018-03-29 | 2020-06-14 | 2020-11-16 | 2020-11-16 | COMP | 2021-03-02 | COMP | 2021-07-08 | COMP | 2021-04-05 | NOTN | 2021-07-11 | COMP | Rule 16 | 556 | 109 | 71 | 91 |  |  | 826
3292 | 2018-03-30 | 2018-04-03 | 2018-05-22 | 2018-05-22 | COMP | 2018-05-21 | NOTN | 2018-05-22 | COMP | 2018-04-25 | COMP | 2019-07-24 | COMP | Other | 3 | 36 |  | 1 | 0 | 295 | 332
3397 | 2018-03-30 | 2018-04-18 | 2018-08-02 | 2018-08-02 | COMP | 2018-10-30 | COMP | 2018-11-16 | COMP | 2019-03-25 | COMP | 2019-04-17 | COMP | Rule 16 | 14 | 75 | 63 | 13 | 86 | 18 | 264
3466 | 2018-03-30 | 2018-05-01 | 2018-08-02 | 2019-04-06 | COMP | 2019-05-07 | COMP | 2018-09-07 | COMP | 2019-04-22 | COMP | 2019-05-30 | COMP | Rule 16 | 23 | 66 | 22 |  | 155 | 28 | 294
3467 | 2018-03-30 | 2018-05-01 | 2018-07-02 | 2018-07-02 | COMP | 2018-12-13 | COMP | 2018-12-20 | COMP | 2019-02-27 | COMP | 2019-04-16 | COMP | Rule 16 | 23 | 44 | 114 | 6 | 46 | 35 | 263
3782 | 2018-03-30 | 2018-07-11 | 2018-12-30 | 2018-12-30 | COMP | 2019-11-20 | COMP | 2019-12-30 | COMP | 2021-05-12 | COMP | 2021-05-19 | COMP | Rule 16 | 72 | 118 | 226 | 26 | 346 | 6 | 790
3921 | 2018-03-30 | 2018-10-10 | 2019-02-14 | 2019-02-14 | COMP | 2019-06-17 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-07-18 | COMP | Rule 15/16 | 136 | 86 | 86 | 4 | 1 | 20 | 328
4237 | 2018-03-30 | 2019-09-25 | 2019-09-27 | 2019-09-27 | COMP | 2019-09-26 | NOTN | 2019-09-27 | COMP | 2020-02-04 | COMP | 2020-02-27 | COMP | Rule 16 | 376 | 3 |  | 1 | 87 | 17 | 480
4861 | 2018-03-30 | 2018-04-06 | 2018-06-07 | 2018-06-07 | COMP | 2019-03-15 | NOTN | 2019-07-26 | COMP | 2019-08-08 | COMP | 2019-09-09 | COMP | Other | 6 | 44 |  | 286 | 10 | 22 | 364
5304 | 2018-03-30 | 2018-05-21 | 2019-02-06 | 2019-02-06 | COMP | 2019-04-12 | COMP | 2019-09-16 | COMP | 2021-01-08 | COMP | 2021-01-19 | COMP | Rule 15/16 | 37 | 179 | 47 | 109 | 331 | 7 | 705
5307 | 2018-03-30 | 2018-05-21 | 2018-10-21 | 2018-10-21 | COMP | 2018-11-14 | COMP | 2019-01-04 | COMP | 2020-06-22 | COMP | 2020-11-06 | COMP | Rule 15/16 | 37 | 107 | 17 | 34 | 369 | 99 | 659
5340 | 2018-03-30 | 2018-05-25 | 2018-09-07 | 2018-09-07 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2020-02-01 | COMP | 2020-02-22 | COMP | Rule 16 | 41 | 73 | 59 | 1 | 292 | 14 | 476
5345 | 2018-03-30 | 2018-05-24 | 2018-12-21 | 2018-12-21 | COMP | 2018-05-31 | NOTN | 2018-12-21 | COMP | 2020-02-29 | INPR | 2019-10-25 | COMP | Other | 40 | 146 |  | 1 |  |  | 398
5454 | 2018-03-30 | 2018-06-01 | 2018-08-29 | 2018-08-29 | COMP | 2020-01-07 | COMP | 2021-02-17 | COMP | 2020-09-29 | COMP | 2021-03-19 | COMP | Rule 16 | 45 | 63 | 339 | 281 | 0 | 23 | 747
5460 | 2018-03-30 | 2018-06-01 | 2018-09-19 | 2018-09-19 | COMP | 2019-01-11 | COMP | 2019-08-02 | INPR | 2019-05-03 | COMP | 2019-07-28 | COMP | Rule 16 | 45 | 77 | 78 |  |  |  | 334
5477 | 2018-03-30 | 2018-06-02 | 2019-01-07 | 2019-01-07 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-07-16 | COMP | 2019-08-21 | COMP | Rule 16 | 45 | 149 | 135 | 1 | 0 | 25 | 352
5516 | 2018-03-30 | 2018-06-08 | 2018-08-07 | 2018-08-07 | COMP | 2018-08-29 | COMP | 2018-10-05 | COMP | 2023-11-11 | INPR | 2019-02-09 | COMP | Rule 15/16 | 50 | 42 | 17 | 27 |  |  | 217
5679 | 2018-03-30 | 2018-06-25 | 2018-08-22 | 2019-02-07 | COMP | 2019-03-14 | COMP | 2019-04-17 | COMP | 2019-04-18 | COMP | 2019-05-15 | COMP | Rule 16 | 61 | 42 | 25 | 25 | 2 | 20 | 284
5883 | 2018-03-30 | 2018-07-09 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-02-05 | COMP | 2019-03-22 | COMP | Rule 16 | 70 | 125 | 14 | 1 | 8 | 33 | 246
6018 | 2018-03-30 | 2018-07-19 | 2018-08-16 | 2018-08-16 | COMP | 2018-09-12 | COMP | 2019-12-23 | COMP | 2020-01-08 | COMP | 2020-01-09 | COMP | Rule 16 | 78 | 21 | 19 | 321 | 11 | 2 | 447
6124 | 2018-03-30 | 2018-07-27 | 2018-10-17 | 2019-03-25 | COMP | 2019-04-17 | COMP | 2019-08-05 | COMP | 2019-06-11 | COMP | 2019-08-09 | COMP | Rule 16 | 84 | 58 | 18 | 77 | 0 | 5 | 344
7189 | 2018-03-30 | 2018-10-02 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2018-12-10 | COMP | 2019-01-25 | COMP | Rule 16 | 130 | 40 | 14 | 1 | 0 | 26 | 207
8420 | 2018-03-30 | 2018-11-30 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-19 | COMP | 2019-09-06 | COMP | 2019-09-23 | COMP | 2020-01-14 | COMP | Rule 16 | 170 | 60 | 15 | 121 | 12 | 77 | 450
9378 | 2018-03-30 | 2019-01-31 | 2019-04-13 | 2019-07-22 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2019-10-16 | COMP | 2019-11-21 | COMP | Rule 16 | 211 | 51 | 8 | 1 | 55 | 26 | 416
8520 | 2018-03-31 | 2018-12-06 | 2019-01-03 | 2019-01-03 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-01-14 | COMP | 2019-02-06 | COMP | Rule 16 | 173 | 19 | 11 | 1 | 0 | 14 | 214
12205 | 2018-03-31 | 2019-05-28 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2020-02-04 | COMP | 2020-03-06 | COMP | Rule 15/16 | 291 | 34 | 53 | 1 | 88 | 23 | 485
13138 | 2018-04-01 | 2019-07-13 | 2020-10-09 | 2020-10-09 | COMP | 2021-09-14 | COMP | 2021-09-14 | COMP | 2022-02-11 | COMP | 2022-03-04 | COMP | Rule 15/16 | 323 | 315 | 233 | 1 | 105 | 15 | 988
3508 | 2018-04-02 | 2018-05-09 | 2018-06-04 | 2018-07-16 | COMP | 2018-11-30 | COMP | 2018-12-04 | COMP | 2019-03-18 | COMP | 2019-04-02 | COMP | Rule 16 | 28 | 18 | 96 | 3 | 71 | 12 | 252
3954 | 2018-04-02 | 2018-10-25 | 2019-01-10 | 2019-01-10 | COMP | 2019-03-04 | COMP | 2019-03-06 | COMP |  |  | 2019-09-17 | COMP | Rule 15/16 | 146 | 51 | 36 | 3 |  |  | 369
4229 | 2018-04-02 | 2019-09-13 | 2020-05-01 | 2020-05-01 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP |  | INPR | 2021-01-12 | COMP | Rule 15/16 | 367 | 159 | 149 | 1 |  |  | 700
4845 | 2018-04-02 | 2018-04-04 | 2018-06-20 | 2019-01-23 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-04-05 | COMP | 2019-04-09 | COMP | Rule 16 | 3 | 55 | 11 | 1 | 42 | 3 | 257
4895 | 2018-04-02 | 2018-04-10 | 2018-08-29 | 2018-08-29 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-12-16 | COMP | 2020-01-17 | COMP | Rule 16 | 7 | 100 | 77 | 1 | 249 | 23 | 452
4989 | 2018-04-02 | 2018-04-19 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-17 | COMP | 2018-12-18 | COMP | 2019-01-28 | COMP | 2020-09-18 | COMP | Rule 16 | 14 | 107 | 21 | 42 | 27 | 417 | 623
5138 | 2018-04-02 | 2018-05-03 | 2018-10-22 | 2018-10-22 | COMP | 2019-02-22 | COMP | 2019-02-26 | COMP | 2020-10-01 | COMP | 2020-10-16 | COMP | Rule 15 | 24 | 120 | 83 | 3 | 406 | 12 | 643
5532 | 2018-04-02 | 2018-06-12 | 2018-08-10 | 2019-02-02 | COMP | 2019-02-11 | COMP | 2018-10-05 | COMP | 2019-02-20 | COMP | 2019-04-01 | COMP | Rule 16 | 51 | 43 | 6 |  | 92 | 29 | 251
5574 | 2018-04-02 | 2018-06-14 | 2018-09-13 | 2019-04-30 | COMP | 2019-05-09 | COMP | 2019-01-30 | COMP | 2019-10-07 | COMP | 2019-12-31 | COMP | Rule 16 | 53 | 64 | 8 |  | 175 | 58 | 440
5727 | 2018-04-02 | 2018-06-27 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-02-25 | COMP | 2019-04-05 | COMP | Rule 16 | 62 | 100 | 17 | 1 | 50 | 30 | 255
5734 | 2018-04-02 | 2018-06-27 | 2018-11-05 | 2019-02-25 | COMP | 2019-03-18 | COMP | 2019-12-02 | COMP | 2021-02-16 | COMP | 2020-06-23 | COMP | Rule 15/16 | 62 | 92 | 16 | 180 | 304 |  | 561
5769 | 2018-04-02 | 2018-07-02 | 2018-11-11 | 2018-11-11 | COMP | 2020-01-17 | COMP | 2020-01-21 | COMP | 2020-02-18 | COMP | 2020-03-12 | COMP | Rule 16 | 65 | 93 | 295 | 2 | 20 | 18 | 489
6451 | 2018-04-02 | 2018-08-20 | 2018-10-27 | 2018-10-27 | COMP | 2019-04-01 | COMP | 2022-10-03 | COMP | 2022-08-24 | COMP | 2022-12-08 | COMP | Rule 16 | 99 | 49 | 104 | 885 | 0 | 46 | 1180
6454 | 2018-04-02 | 2018-08-20 | 2018-09-25 | 2018-09-25 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2018-12-12 | COMP | 2019-01-11 | COMP | Rule 16 | 99 | 26 | 38 | 1 | 17 | 21 | 197
6920 | 2018-04-02 | 2018-09-17 | 2018-10-23 | 2018-10-23 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2019-10-21 | INPR | 2019-06-24 | COMP | Rule 16 | 118 | 27 | 15 | 1 |  |  | 310
7312 | 2018-04-02 | 2018-10-08 | 2018-12-27 | 2019-07-12 | COMP | 2019-11-04 | COMP | 2020-05-26 | INPR | 2020-07-24 | COMP | 2020-11-02 | COMP | Rule 15/16 | 133 | 55 | 81 |  |  |  | 654
7431 | 2018-04-02 | 2018-10-12 | 2019-04-12 | 2019-04-26 | COMP | 2019-05-20 | COMP | 2019-08-06 | COMP | 2020-03-27 | COMP | 2020-05-05 | COMP | Rule 15/16 | 137 | 124 | 17 | 55 | 161 | 28 | 527
8922 | 2018-04-02 | 2019-01-07 | 2019-04-03 | 2021-05-28 | COMP | 2021-07-12 | COMP | 2019-07-01 | COMP | 2023-12-02 | INPR | 2019-11-15 | COMP | Rule 16 | 193 | 61 | 30 |  |  |  | 411
9709 | 2018-04-02 | 2019-02-12 | 2019-05-24 | 2019-05-24 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2020-10-20 | COMP | 2020-11-30 | COMP | Rule 16 | 218 | 73 | 31 | 1 | 326 | 27 | 671
9710 | 2018-04-02 | 2019-02-12 | 2019-05-31 | 2019-05-31 | COMP | 2019-08-07 | COMP | 2019-08-21 | COMP | 2020-01-31 | COMP | 2020-03-03 | COMP | Rule 16 | 218 | 77 | 48 | 11 | 111 | 22 | 482
10419 | 2018-04-02 | 2019-03-15 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-09 | COMP | 2019-11-13 | COMP |  |  | 2020-03-25 | COMP | Rule 16 | 240 | 59 | 23 | 90 |  |  | 498
15290 | 2018-04-02 | 2019-10-24 | 2019-12-02 | 2019-12-02 | COMP | 2021-03-17 | COMP | 2021-04-13 | COMP | 2021-04-15 | COMP | 2021-08-25 | COMP | Rule 16 | 396 | 25 | 325 | 20 | 3 | 93 | 857
19225 | 2018-04-02 | 2020-04-27 | 2020-11-05 | 2020-11-05 | COMP | 2022-11-30 | COMP | 2022-12-29 | COMP | 2023-02-01 | COMP | 2023-02-15 | COMP | Rule 15/16 | 521 | 137 | 518 | 21 | 23 | 11 | 1226
3378 | 2018-04-03 | 2018-04-16 | 2018-07-16 | 2018-07-16 | COMP | 2018-11-08 | COMP | 2019-05-31 | COMP | 2019-05-30 | COMP | 2019-06-07 | COMP | Rule 16 | 10 | 64 | 83 | 139 | 0 | 6 | 298
3431 | 2018-04-03 | 2018-04-24 | 2018-09-26 | 2018-09-26 | COMP | 2019-08-14 | COMP | 2019-08-21 | COMP | 2019-08-07 | COMP | 2020-01-09 | COMP | Rule 16 | 16 | 109 | 222 | 6 | 0 | 96 | 445
3630 | 2018-04-03 | 2018-05-26 | 2019-04-30 | 2019-04-30 | COMP | 2019-08-07 | COMP | 2019-08-21 | COMP | 2020-06-19 | COMP | 2020-12-08 | COMP | Rule 16 | 39 | 232 | 70 | 11 | 209 | 119 | 676
3761 | 2018-04-03 | 2018-06-29 | 2018-07-10 | 2018-07-10 | COMP | 2018-10-03 | COMP | 2018-10-04 | COMP | 2018-12-27 | COMP | 2019-01-28 | COMP | Rule 16 | 63 | 7 | 61 | 2 | 57 | 21 | 206
4922 | 2018-04-03 | 2018-04-12 | 2018-07-17 | 2018-07-17 | COMP | 2018-07-27 | COMP | 2019-01-19 | COMP | 2019-02-08 | COMP | 2019-04-09 | COMP | Rule 16 | 8 | 67 | 9 | 120 | 14 | 42 | 256
4957 | 2018-04-03 | 2018-04-14 | 2018-10-19 | 2018-10-19 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2018-10-27 | COMP | 2019-01-03 | COMP | Rule 16 | 9 | 132 | 6 | 1 | 1 | 44 | 190
5150 | 2018-04-03 | 2018-05-04 | 2018-12-11 | 2018-12-11 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2018-12-14 | COMP | 2019-03-11 | COMP | Rule 16 | 24 | 152 | 5 | 1 | 0 | 57 | 235
5212 | 2018-04-03 | 2018-05-10 | 2019-01-24 | 2019-05-29 | COMP | 2019-08-20 | COMP | 2019-08-21 | COMP | 2019-08-26 | COMP | 2020-02-10 | COMP | Rule 15/16 | 28 | 177 | 59 | 2 | 4 | 114 | 466
5274 | 2018-04-03 | 2018-05-15 | 2018-11-14 | 2021-03-08 | COMP | 2021-11-12 | COMP | 2022-03-24 | COMP | 2022-06-02 | COMP | 2022-06-18 | COMP | Rule 16 | 31 | 128 | 176 | 91 | 50 | 12 | 1061
5464 | 2018-04-03 | 2018-06-01 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-23 | COMP | 2018-10-23 | COMP | 2018-12-07 | COMP | 2019-01-08 | COMP | Rule 16 | 43 | 74 | 28 | 1 | 31 | 21 | 193
5514 | 2018-04-03 | 2018-06-06 | 2018-10-01 | 2018-10-01 | COMP | 2018-11-08 | COMP | 2018-11-08 | COMP | 2018-12-20 | COMP | 2019-01-10 | COMP | Rule 16 | 46 | 82 | 29 | 1 | 28 | 14 | 195
5550 | 2018-04-03 | 2018-06-13 | 2018-09-06 | 2018-10-30 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-10-21 | INPR | 2019-06-03 | COMP | Rule 16 | 51 | 60 | 41 | 1 |  |  | 294
5558 | 2018-04-03 | 2018-06-14 | 2018-06-23 | 2018-06-23 | COMP | 2018-06-29 | COMP | 2018-07-13 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | Rule 16 | 52 | 7 | 5 | 10 | 146 | 1 | 217
5564 | 2018-04-03 | 2018-06-13 | 2018-09-18 | 2018-09-18 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-05-23 | COMP | 2019-09-19 | COMP | Rule 15/16 | 51 | 68 | 31 | 1 | 141 | 83 | 370
5616 | 2018-04-03 | 2018-06-20 | 2019-02-28 | 2022-08-31 | COMP | 2022-11-14 | COMP | 2023-11-07 | COMP | 2023-11-14 | COMP | 2023-12-13 | COMP | Rule 15/16 | 56 | 173 | 52 | 247 | 5 | 20 | 1432
5873 | 2018-04-03 | 2018-07-10 | 2018-10-25 | 2018-10-25 | COMP | 2018-11-14 | COMP | 2018-10-30 | COMP | 2018-11-14 | COMP | 2019-02-15 | COMP | Rule 16 | 69 | 77 | 14 |  | 11 | 63 | 220
7065 | 2018-04-03 | 2018-09-25 | 2019-02-19 | 2019-02-19 | COMP | 2019-02-04 | NOTN | 2019-03-12 | COMP | 2019-01-25 | COMP | 2019-04-18 | COMP | Other | 123 | 99 |  | 16 | 0 | 28 | 263
9696 | 2018-04-03 | 2019-02-12 | 2019-03-30 | 2019-03-30 | COMP | 2019-07-26 | COMP | 2019-08-08 | NOTN | 2019-09-04 | COMP | 2019-09-10 | COMP | Rule 15/16 | 217 | 33 | 83 |  |  |  | 363
34312 | 2018-04-03 | 2022-02-08 | 2022-06-29 | 2022-06-29 | COMP | 2022-08-17 | COMP | 2023-04-26 | COMP | 2023-04-25 | COMP | 2023-07-11 | COMP | Rule 15/16 | 970 | 99 | 35 | 173 | 0 | 52 | 1325
3565 | 2018-04-04 | 2018-05-17 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-25 | COMP | 2018-10-29 | COMP | 2019-06-29 | INPR | 2019-03-01 | COMP | Rule 16 | 32 | 92 | 22 | 3 |  |  | 228
3803 | 2018-04-04 | 2018-07-19 | 2018-10-16 | 2018-10-16 | COMP | 2019-04-15 | COMP | 2019-04-17 | COMP | 2019-05-02 | COMP | 2019-07-12 | COMP | Rule 15/16 | 75 | 63 | 123 | 3 | 12 | 50 | 321
3848 | 2018-04-04 | 2018-08-15 | 2018-11-28 | 2018-11-28 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | 2020-03-27 | COMP | 2020-04-04 | COMP | Rule 16 | 94 | 72 | 290 | 1 | 45 | 6 | 503
3982 | 2018-04-04 | 2018-11-07 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-26 | COMP | 2019-03-06 | COMP | 2019-04-23 | COMP | 2019-05-07 | COMP | Rule 15/16 | 153 | 49 | 25 | 7 | 35 | 11 | 275
4048 | 2018-04-04 | 2018-12-29 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-08 | COMP | 2019-07-09 | COMP | 2019-08-14 | COMP | 2019-10-01 | COMP | Rule 16 | 186 | 84 | 7 | 43 | 27 | 34 | 377
4923 | 2018-04-04 | 2018-04-12 | 2018-09-25 | 2020-08-18 | COMP | 2020-09-09 | COMP | 2020-07-06 | COMP | 2020-08-28 | COMP | 2020-11-16 | COMP | Rule 16 | 7 | 116 | 16 |  | 40 | 55 | 661
4924 | 2018-04-04 | 2018-04-12 | 2018-11-26 | 2018-11-26 | COMP | 2018-12-06 | COMP | 2019-02-15 | COMP | 2019-03-11 | COMP | 2019-04-24 | COMP | Rule 15/16 | 7 | 157 | 9 | 49 | 16 | 33 | 266
5016 | 2018-04-04 | 2018-04-24 | 2019-08-27 | 2019-08-27 | COMP | 2020-04-24 | COMP | 2020-05-01 | COMP | 2020-12-30 | COMP | 2021-02-11 | COMP | Rule 16 | 15 | 339 | 166 | 6 | 168 | 30 | 719
5235 | 2018-04-04 | 2018-05-15 | 2019-08-09 | 2019-08-09 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-05-07 | COMP | 2020-06-04 | COMP | Rule 16 | 30 | 312 | 67 | 1 | 121 | 20 | 546
5440 | 2018-04-04 | 2018-05-31 | 2018-08-29 | 2018-08-29 | COMP | 2018-10-05 | COMP | 2018-12-04 | COMP | 2023-11-11 | INPR | 2019-08-20 | COMP | Rule 16 | 41 | 64 | 27 | 40 |  |  | 348
5594 | 2018-04-04 | 2018-06-18 | 2018-09-21 | 2018-09-21 | COMP | 2019-02-28 | COMP | 2019-06-14 | COMP | 2020-12-22 | COMP | 2021-05-13 | COMP | Rule 16 | 53 | 68 | 108 | 76 | 384 | 99 | 783
5623 | 2018-04-04 | 2018-06-20 | 2018-06-25 | 2018-06-25 | COMP | 2018-06-27 | COMP | 2018-06-27 | COMP | 2022-05-28 | INPR | 2021-04-24 | COMP | Rule 16 | 55 | 4 | 3 | 1 |  |  | 769
5695 | 2018-04-04 | 2018-06-25 | 2018-11-26 | 2021-11-02 | COMP | 2021-11-23 | COMP | 2021-11-23 | COMP | 2022-07-26 | COMP | 2022-08-12 | COMP | Rule 16 | 58 | 106 | 15 | 1 | 169 | 14 | 1098
5697 | 2018-04-04 | 2018-06-25 | 2018-09-15 | 2018-09-15 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-10-02 | COMP | 2019-10-09 | COMP | Rule 16 | 58 | 58 | 50 | 1 | 214 | 6 | 383
5890 | 2018-04-04 | 2018-07-09 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-10 | COMP | 2018-12-20 | COMP | 2019-03-08 | COMP | 2019-03-18 | COMP | Rule 16 | 67 | 104 | 4 | 9 | 53 | 7 | 239
7731 | 2018-04-04 | 2018-10-27 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-26 | COMP | 2019-04-12 | COMP | 2019-07-26 | COMP | 2019-08-05 | COMP | Rule 15/16 | 145 | 58 | 23 | 34 | 74 | 7 | 337
8126 | 2018-04-04 | 2018-11-16 | 2019-03-13 | 2019-04-10 | COMP | 2019-06-13 | COMP | 2019-08-08 | COMP | 2019-08-08 | COMP | 2019-08-15 | COMP | Rule 15/16 | 159 | 78 | 46 | 40 | 1 | 6 | 345
8156 | 2018-04-04 | 2018-11-17 | 2019-03-28 | 2019-03-28 | COMP | 2019-05-16 | COMP | 2019-05-23 | COMP | 2019-07-10 | COMP | 2019-08-26 | COMP | Rule 16 | 159 | 88 | 36 | 6 | 33 | 34 | 352
9409 | 2018-04-04 | 2019-02-01 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-09-17 | COMP | 2019-09-20 | COMP | Rule 15/16 | 209 | 59 | 26 | 1 | 76 | 4 | 370
9470 | 2018-04-04 | 2019-02-05 | 2020-02-12 | 2020-02-12 | COMP | 2020-05-04 | COMP | 2020-08-12 | COMP | 2021-02-11 | COMP | 2021-11-06 | COMP | Rule 16 | 211 | 257 | 58 | 72 | 125 | 188 | 906
11210 | 2018-04-04 | 2019-04-17 | 2019-08-05 | 2019-08-05 | COMP | 2020-05-04 | COMP | 2020-07-30 | COMP | 2020-09-25 | COMP | 2021-01-27 | COMP | Rule 15/16 | 261 | 77 | 188 | 63 | 41 | 83 | 708
12525 | 2018-04-04 | 2019-06-11 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-20 | COMP | 2020-07-08 | COMP | 2020-07-16 | COMP | 2020-08-12 | COMP | Rule 16 | 299 | 43 | 8 | 223 | 7 | 20 | 595
13200 | 2018-04-04 | 2019-07-16 | 2019-10-18 | 2019-10-18 | COMP | 2019-12-11 | COMP | 2020-06-04 | COMP |  |  | 2020-07-21 | COMP | Rule 16 | 323 | 68 | 36 | 122 |  |  | 579
14215 | 2018-04-04 | 2019-08-29 | 2019-11-20 | 2019-11-20 | COMP | 2020-01-30 | COMP | 2020-07-28 | COMP | 2020-07-14 | COMP | 2020-09-18 | COMP | Rule 15/16 | 355 | 58 | 47 | 127 | 0 | 38 | 621
3339 | 2018-04-05 | 2018-04-10 | 2018-05-31 | 2018-05-31 | COMP | 2019-10-08 | COMP | 2019-11-12 | COMP | 2018-12-05 | COMP | 2019-12-13 | COMP | Rule 16 | 4 | 37 | 342 | 25 | 0 | 22 | 426
3363 | 2018-04-05 | 2018-04-12 | 2018-08-10 | 2018-08-10 | COMP | 2020-07-07 | COMP | 2020-08-19 | COMP | 2020-09-10 | COMP | 2020-09-29 | COMP | Rule 16 | 6 | 85 | 479 | 32 | 16 | 14 | 627
3364 | 2018-04-05 | 2018-04-12 | 2018-08-09 | 2018-08-09 | COMP | 2020-07-07 | COMP | 2020-08-25 | COMP | 2020-09-10 | COMP | 2020-11-05 | COMP | Rule 16 | 6 | 84 | 480 | 36 | 12 | 41 | 654
3525 | 2018-04-05 | 2018-05-10 | 2018-07-09 | 2018-07-09 | COMP | 2018-12-24 | COMP | 2019-01-17 | COMP | 2019-01-23 | COMP | 2019-04-10 | COMP | Rule 16 | 26 | 41 | 117 | 17 | 4 | 55 | 255
4936 | 2018-04-05 | 2018-04-13 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-11 | NOTN | 2019-07-17 | COMP | 2019-07-22 | COMP | 2019-08-26 | COMP | Other | 7 | 304 |  | 14 | 4 | 26 | 351
4953 | 2018-04-05 | 2018-04-13 | 2018-06-19 | 2021-02-08 | COMP | 2021-02-12 | COMP | 2019-08-14 | COMP | 2021-03-22 | COMP | 2021-04-30 | COMP | Rule 16 | 7 | 47 | 5 |  | 402 | 30 | 773
5309 | 2018-04-05 | 2018-05-22 | 2018-08-22 | 2018-08-22 | COMP | 2018-08-30 | COMP | 2018-10-26 | COMP | 2018-12-05 | COMP | 2019-04-15 | COMP | Rule 16 | 34 | 65 | 7 | 41 | 26 | 90 | 258
5404 | 2018-04-05 | 2018-05-29 | 2018-10-27 | 2019-03-08 | COMP | 2020-04-27 | COMP | 2021-01-21 | COMP | 2020-09-08 | COMP | 2021-02-23 | COMP | Rule 16 | 38 | 107 | 287 | 186 | 0 | 23 | 725
5415 | 2018-04-05 | 2018-05-30 | 2018-08-28 | 2018-08-28 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-03-22 | COMP | 2019-05-06 | COMP | Rule 16 | 39 | 64 | 58 | 1 | 84 | 32 | 273
5686 | 2018-04-05 | 2018-06-25 | 2018-11-26 | 2019-03-04 | COMP | 2019-03-26 | COMP | 2019-09-30 | COMP | 2020-04-22 | COMP | 2020-05-26 | COMP | Rule 15/16 | 57 | 106 | 17 | 132 | 141 | 24 | 538
5705 | 2018-04-05 | 2018-06-27 | 2018-11-05 | 2023-02-19 | COMP | 2023-03-06 | COMP | 2019-03-18 | COMP | 2023-06-18 | COMP | 2023-07-27 | COMP | Rule 16 | 59 | 92 | 10 |  | 1071 | 27 | 1335
5706 | 2018-04-05 | 2018-06-27 | 2018-09-27 | 2023-02-17 | COMP | 2023-05-31 | COMP | 2023-07-05 | COMP | 2023-06-18 | COMP | 2023-07-27 | COMP | Rule 16 | 59 | 65 | 72 | 24 | 0 | 17 | 1335
5895 | 2018-04-05 | 2018-07-09 | 2018-09-17 | 2018-09-17 | COMP | 2018-10-31 | COMP | 2019-04-22 | COMP | 2019-07-30 | COMP | 2019-08-26 | COMP | Rule 15/16 | 66 | 50 | 33 | 117 | 70 | 20 | 351
6103 | 2018-04-05 | 2018-07-25 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-02-11 | COMP | 2019-02-27 | COMP | Rule 16 | 78 | 87 | 31 | 1 | 21 | 12 | 225
6446 | 2018-04-05 | 2018-08-20 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-08 | COMP | 2019-01-28 | COMP | 2019-01-10 | COMP | 2019-03-07 | COMP | Rule 16 | 96 | 47 | 12 | 52 | 0 | 28 | 231
6517 | 2018-04-05 | 2018-08-23 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-04 | COMP | 2019-03-06 | COMP | 2019-01-08 | COMP | 2019-03-27 | COMP | Rule 16 | 99 | 60 | 11 | 63 | 0 | 16 | 245
6621 | 2018-04-05 | 2018-08-31 | 2018-09-18 | 2018-09-18 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-01-08 | COMP | 2019-01-19 | COMP | Rule 16 | 105 | 12 | 33 | 1 | 44 | 9 | 199
7400 | 2018-04-05 | 2018-10-10 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-28 | COMP | 2019-06-20 | COMP | 2019-06-13 | COMP | 2019-08-07 | COMP | Rule 16 | 132 | 116 | 42 | 18 | 0 | 34 | 338
8683 | 2018-04-05 | 2018-12-17 | 2019-07-18 | 2019-07-18 | COMP | 2020-02-26 | COMP | 2020-04-01 | COMP | 2020-07-02 | COMP | 2020-09-19 | COMP | Rule 15/16 | 177 | 148 | 152 | 26 | 66 | 56 | 620
9256 | 2018-04-05 | 2019-01-25 | 2019-02-20 | 2019-02-20 | COMP | 2019-10-03 | COMP | 2019-10-07 | COMP | 2020-04-26 | INPR | 2020-01-13 | COMP | Rule 16 | 203 | 18 | 159 | 3 |  |  | 445
11610 | 2018-04-05 | 2019-05-05 | 2019-09-13 | 2019-09-13 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-06-23 | COMP | 2020-08-06 | COMP | Rule 15/16 | 272 | 92 | 170 | 1 | 26 | 33 | 590
12404 | 2018-04-05 | 2019-06-05 | 2019-12-05 | 2019-12-05 | COMP | 2020-08-06 | COMP | 2020-08-11 | COMP | 2020-08-13 | COMP | 2021-02-12 | COMP | Rule 15/16 | 294 | 127 | 171 | 4 | 3 | 125 | 719
14663 | 2018-04-05 | 2019-09-22 | 2020-02-06 | 2020-02-06 | COMP | 2020-09-28 | COMP | 2020-12-08 | COMP | 2021-08-02 | COMP | 2021-11-17 | COMP | Rule 16 | 369 | 93 | 165 | 49 | 164 | 76 | 912
15278 | 2018-04-05 | 2019-10-23 | 2019-12-31 | 2019-12-31 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2021-10-25 | COMP | 2021-12-02 | COMP | Rule 16 | 392 | 46 | 121 | 1 | 340 | 26 | 921
15279 | 2018-04-05 | 2019-10-23 | 2019-12-31 | 2019-12-31 | COMP | 2020-06-22 | COMP | 2020-07-17 | COMP | 2021-07-28 | COMP | 2021-09-28 | COMP | Rule 16 | 392 | 46 | 121 | 20 | 259 | 44 | 877
15289 | 2018-04-05 | 2019-10-24 | 2019-12-31 | 2020-02-21 | COMP | 2020-06-22 | COMP | 2020-06-30 | COMP | 2023-11-12 | INPR | 2022-02-14 | COMP | Rule 16 | 393 | 45 | 86 | 7 |  |  | 972
15292 | 2018-04-05 | 2019-10-24 | 2019-12-31 | 2020-04-14 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2021-08-10 | COMP | 2021-10-20 | COMP | Rule 16 | 393 | 45 | 49 | 1 | 287 | 51 | 893
15293 | 2018-04-05 | 2019-10-24 | 2020-01-02 | 2020-01-02 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2022-03-04 | COMP | 2022-04-20 | COMP | Rule 16 | 393 | 46 | 120 | 1 | 429 | 34 | 1018
15297 | 2018-04-05 | 2019-10-24 | 2020-01-14 | 2020-04-14 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2022-04-13 | COMP | 2022-04-19 | COMP | Rule 16 | 393 | 54 | 49 | 1 | 457 | 5 | 1017
15656 | 2018-04-05 | 2019-11-13 | 2020-02-26 | 2020-02-26 | COMP | 2020-06-22 | COMP | 2021-03-31 | COMP | 2022-01-04 | COMP | 2021-11-03 | COMP | Rule 16 | 406 | 70 | 83 | 195 | 194 |  | 903
3361 | 2018-04-06 | 2018-04-13 | 2018-06-18 | 2018-06-18 | COMP | 2018-09-07 | COMP | 2018-09-19 | COMP | 2019-02-21 | COMP | 2019-03-28 | COMP | Rule 16 | 6 | 46 | 58 | 9 | 105 | 26 | 245
3683 | 2018-04-06 | 2018-06-07 | 2018-12-17 | 2018-12-17 | COMP | 2019-10-31 | COMP | 2019-09-19 | COMP | 2021-02-28 | INPR | 2020-01-30 | COMP | Rule 15/16 | 44 | 133 | 222 |  |  |  | 456
3953 | 2018-04-06 | 2018-10-27 | 2019-09-11 | 2019-09-11 | COMP | 2020-02-26 | COMP | 2020-04-02 | COMP | 2020-10-19 | COMP | 2020-12-11 | COMP | Rule 16 | 143 | 218 | 114 | 27 | 141 | 37 | 676
4859 | 2018-04-06 | 2018-04-06 | 2018-06-02 | 2018-06-02 | COMP | 2018-10-02 | COMP | 2018-10-02 | COMP | 2018-11-20 | COMP | 2019-02-11 | COMP | Rule 16 | 1 | 40 | 85 | 1 | 35 | 55 | 213
5010 | 2018-04-06 | 2018-04-24 | 2018-08-07 | 2018-08-07 | COMP | 2018-11-06 | COMP | 2019-05-28 | COMP | 2019-07-29 | COMP | 2019-09-30 | COMP | Rule 16 | 13 | 74 | 65 | 138 | 44 | 45 | 374
5039 | 2018-04-06 | 2018-04-25 | 2018-06-28 | 2018-06-28 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-01-17 | COMP | 2019-04-15 | COMP | Rule 16 | 14 | 46 | 102 | 1 | 38 | 61 | 257
5244 | 2018-04-06 | 2018-05-14 | 2018-10-08 | 2018-10-27 | COMP | 2018-11-16 | COMP | 2019-02-21 | INPR | 2018-11-19 | COMP | 2019-04-05 | COMP | Rule 15/16 | 27 | 103 | 14 |  |  |  | 251
5270 | 2018-04-06 | 2018-05-15 | 2018-12-12 | 2018-12-12 | COMP | 2019-02-01 | COMP | 2020-01-17 | COMP | 2019-04-30 | COMP | 2021-02-26 | COMP | Rule 15/16 | 28 | 146 | 35 | 242 | 0 | 280 | 727
5335 | 2018-04-06 | 2018-05-22 | 2018-08-28 | 2018-08-28 | COMP | 2019-01-09 | COMP | 2020-01-27 | COMP | 2019-12-31 | COMP | 2020-02-04 | COMP | Rule 16 | 33 | 69 | 91 | 263 | 0 | 7 | 459
5489 | 2018-04-06 | 2018-06-04 | 2018-12-04 | 2018-12-04 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-06-07 | COMP | 2019-07-09 | COMP | Rule 16 | 41 | 127 | 109 | 1 | 21 | 22 | 316
5812 | 2018-04-06 | 2018-07-05 | 2018-11-28 | 2018-12-19 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2019-12-06 | COMP | 2020-01-24 | COMP | Rule 15/16 | 63 | 101 | 239 | 1 | 5 | 33 | 452
5947 | 2018-04-06 | 2018-07-13 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-04-05 | COMP | 2019-05-20 | COMP | Rule 15/16 | 69 | 152 | 43 | 1 | 0 | 21 | 282
6067 | 2018-04-06 | 2018-07-23 | 2018-10-31 | 2018-10-31 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2018-12-18 | COMP | 2019-03-21 | COMP | Rule 16 | 75 | 72 | 28 | 1 | 5 | 64 | 240
6204 | 2018-04-06 | 2018-08-03 | 2018-09-28 | 2019-01-08 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-10-21 | INPR | 2019-04-02 | COMP | Rule 15/16 | 84 | 40 | 10 | 1 |  |  | 248
6234 | 2018-04-06 | 2018-08-06 | 2018-12-13 | 2018-12-13 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2021-06-15 | COMP | 2021-08-17 | COMP | Rule 16 | 85 | 90 | 75 | 1 | 556 | 45 | 847
6289 | 2018-04-06 | 2018-08-08 | 2018-08-25 | 2018-08-25 | COMP | 2018-09-14 | COMP | 2018-09-14 | COMP | 2019-08-27 | COMP | 2019-11-01 | COMP | Rule 16 | 87 | 13 | 14 | 1 | 239 | 48 | 398
7318 | 2018-04-06 | 2018-10-08 | 2019-01-05 | 2019-01-05 | COMP | 2019-04-01 | COMP | 2019-01-22 | COMP | 2019-10-21 | INPR | 2019-03-08 | COMP | Rule 16 | 129 | 60 | 59 |  |  |  | 231
9078 | 2018-04-06 | 2019-01-16 | 2019-02-19 | 2019-02-19 | COMP | 2019-04-01 | COMP | 2019-02-26 | COMP | 2019-10-21 | INPR | 2019-03-28 | COMP | Rule 15/16 | 196 | 23 | 30 |  |  |  | 245
9886 | 2018-04-06 | 2019-02-21 | 2019-04-30 | 2019-04-30 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-10-18 | COMP | 2019-11-20 | COMP | Rule 16 | 220 | 49 | 114 | 1 | 8 | 23 | 410
10666 | 2018-04-06 | 2019-03-25 | 2019-12-03 | 2019-12-03 | COMP | 2020-01-02 | COMP | 2020-03-17 | COMP | 2020-05-06 | COMP | 2020-06-17 | COMP | Rule 15/16 | 242 | 176 | 21 | 52 | 37 | 30 | 553
5528 | 2018-04-07 | 2018-06-10 | 2018-07-30 | 2018-07-30 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-07-17 | COMP | 2019-09-20 | COMP | Rule 15/16 | 44 | 35 | 240 | 1 | 4 | 47 | 367
6078 | 2018-04-07 | 2018-07-23 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2020-01-25 | COMP | 2020-03-01 | COMP | Rule 16 | 74 | 89 | 56 | 1 | 235 | 24 | 475
6459 | 2018-04-07 | 2018-08-21 | 2018-08-27 | 2018-08-27 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-07-21 | INPR | 2019-02-12 | COMP | Rule 16 | 95 | 5 | 81 | 1 |  |  | 213
6716 | 2018-04-07 | 2018-09-11 | 2019-10-09 | 2019-10-09 | COMP | 2020-09-30 | COMP | 2021-11-19 | COMP | 2021-11-23 | COMP | 2021-12-10 | COMP | Rule 15/16 | 109 | 272 | 247 | 287 | 3 | 12 | 925
9574 | 2018-04-07 | 2019-02-07 | 2019-04-11 | 2019-04-11 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-11-01 | COMP | 2020-02-14 | COMP | Rule 16 | 210 | 45 | 75 | 1 | 70 | 70 | 466
4240 | 2018-04-08 | 2019-09-30 | 2020-02-06 | 2020-02-06 | COMP | 2020-03-25 | COMP | 2020-12-04 | INPR |  | REQD | 2021-03-02 | COMP | Rule 15/16 | 373 | 88 | 34 |  |  |  | 728
6261 | 2018-04-08 | 2018-08-07 | 2019-01-12 | 2019-01-12 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-03-18 | COMP | 2019-04-15 | COMP | Rule 16 | 85 | 108 | 22 | 1 | 23 | 21 | 256
3489 | 2018-04-09 | 2018-05-07 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-26 | COMP | 2019-03-14 | COMP | 2020-02-06 | COMP | 2020-04-02 | COMP | Rule 15/16 | 21 | 186 | 17 | 13 | 227 | 40 | 499
3499 | 2018-04-09 | 2018-05-08 | 2018-08-22 | 2018-08-22 | COMP | 2018-09-17 | COMP | 2019-02-01 | COMP | 2019-02-05 | COMP | 2019-02-22 | COMP | Rule 15/16 | 22 | 75 | 18 | 94 | 3 | 13 | 220
3552 | 2018-04-09 | 2018-05-15 | 2018-08-21 | 2018-08-21 | COMP | 2018-09-13 | COMP | 2018-10-05 | COMP | 2019-04-20 | INPR | 2019-01-27 | COMP | Rule 15/16 | 27 | 69 | 17 | 17 |  |  | 201
3553 | 2018-04-09 | 2018-05-15 | 2018-08-22 | 2018-08-22 | COMP | 2018-09-13 | COMP | 2018-10-05 | COMP | 2019-04-20 | INPR | 2019-01-27 | COMP | Rule 15/16 | 27 | 70 | 16 | 17 |  |  | 201
3648 | 2018-04-09 | 2018-06-01 | 2019-01-11 | 2019-01-11 | COMP | 2019-01-24 | COMP | 2019-06-06 | COMP | 2021-02-12 | COMP | 2021-06-09 | COMP | Rule 15/16 | 39 | 154 | 9 | 94 | 425 | 82 | 798
3703 | 2018-04-09 | 2018-06-12 | 2019-06-21 | 2019-06-21 | COMP | 2019-09-24 | COMP | 2020-01-13 | COMP |  |  | 2020-02-04 | COMP | Rule 16 | 46 | 259 | 66 | 75 |  |  | 458
3704 | 2018-04-09 | 2018-06-12 | 2019-08-15 | 2020-12-22 | COMP | 2021-01-15 | COMP | 2021-03-09 | COMP | 2021-03-30 | COMP | 2021-04-27 | COMP | Rule 16 | 46 | 297 | 17 | 36 | 16 | 21 | 768
3747 | 2018-04-09 | 2018-06-26 | 2019-01-16 | 2019-10-18 | COMP | 2020-12-07 | COMP | 2021-01-26 | COMP | 2020-12-15 | COMP | 2021-04-22 | COMP | Rule 15/16 | 56 | 140 | 285 | 34 | 0 | 62 | 765
3748 | 2018-04-09 | 2018-06-27 | 2018-12-11 | 2018-12-11 | COMP | 2019-04-01 | COMP | 2019-09-05 | COMP | 2019-12-18 | COMP | 2020-03-12 | COMP | Rule 15/16 | 57 | 115 | 76 | 111 | 72 | 58 | 484
3787 | 2018-04-09 | 2018-07-14 | 2019-07-22 | 2019-07-22 | COMP | 2019-07-22 | NOTN | 2019-09-04 | COMP | 2019-08-13 | COMP | 2020-03-12 | COMP | Other | 68 | 256 |  | 32 | 0 | 130 | 484
3815 | 2018-04-09 | 2018-07-26 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-19 | COMP | 2018-12-13 | COMP | 2018-12-13 | COMP | 2019-01-11 | COMP | Rule 15/16 | 77 | 51 | 51 |  | 1 | 20 | 192
3847 | 2018-04-09 | 2018-08-15 | 2019-09-12 | 2022-02-07 | COMP |  | INPR | 2021-05-22 | COMP |  | INPR | 2022-04-12 | COMP | Rule 15/16 | 91 | 271 |  |  |  |  | 1010
4930 | 2018-04-09 | 2018-04-12 | 2019-01-10 | 2019-09-25 | COMP | 2019-10-02 | COMP | 2019-10-18 | COMP | 2019-11-12 | COMP | 2020-03-26 | COMP | Rule 15/16 | 4 | 188 | 6 | 13 | 17 | 92 | 494
5087 | 2018-04-09 | 2018-04-30 | 2018-05-23 | 2018-06-08 | COMP | 2018-09-12 | COMP | 2018-12-13 | COMP | 2023-04-30 | INPR | 2019-04-13 | COMP | Rule 16 | 16 | 18 | 67 | 64 |  |  | 255
5249 | 2018-04-09 | 2018-05-15 | 2018-09-27 | 2018-09-27 | COMP | 2018-10-19 | COMP | 2018-10-22 | COMP | 2019-04-02 | COMP | 2019-05-10 | COMP | Rule 16 | 27 | 95 | 17 | 2 | 110 | 29 | 275
5399 | 2018-04-09 | 2018-05-29 | 2018-08-24 | 2018-08-24 | COMP | 2018-10-25 | COMP | 2018-11-28 | COMP | 2018-11-19 | COMP | 2019-01-16 | COMP | Rule 16 | 36 | 63 | 44 | 22 | 0 | 34 | 195
5416 | 2018-04-09 | 2018-05-30 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-02 | COMP | 2018-10-16 | COMP | 2019-02-26 | COMP | 2019-04-10 | COMP | Rule 16 | 37 | 79 | 10 | 11 | 89 | 32 | 253
5551 | 2018-04-09 | 2018-06-13 | 2018-08-28 | 2018-08-28 | COMP | 2018-09-25 | COMP | 2018-09-25 | COMP | 2020-02-29 | INPR | 2019-10-15 | COMP | Rule 16 | 47 | 54 | 20 | 1 |  |  | 384
5584 | 2018-04-09 | 2018-06-15 | 2018-10-05 | 2018-10-12 | COMP | 2018-10-22 | COMP | 2018-10-22 | COMP | 2019-01-04 | COMP | 2019-01-08 | COMP | Rule 16 | 49 | 79 | 7 | 1 | 50 | 3 | 189
5643 | 2018-04-09 | 2018-06-22 | 2018-08-09 | 2019-07-17 | COMP | 2019-09-10 | COMP | 2019-11-27 | COMP | 2020-02-24 | COMP | 2020-03-11 | COMP | Rule 16 | 54 | 34 | 39 | 56 | 58 | 13 | 483
5691 | 2018-04-09 | 2018-06-25 | 2019-03-06 | 2020-05-28 | COMP | 2020-12-11 | COMP | 2021-10-22 | COMP | 2022-02-08 | COMP | 2022-03-07 | COMP | Rule 16 | 55 | 174 | 138 | 219 | 74 | 19 | 984
5710 | 2018-04-09 | 2018-06-26 | 2020-01-09 | 2020-01-13 | COMP | 2020-01-29 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-05-02 | COMP | Rule 16 | 56 | 386 | 12 | 14 | 1 | 54 | 520
5786 | 2018-04-09 | 2018-07-02 | 2018-08-19 | 2018-08-19 | COMP | 2018-09-20 | COMP | 2018-09-20 | COMP | 2018-10-15 | COMP | 2019-01-16 | COMP | Rule 16 | 60 | 34 | 23 | 1 | 18 | 63 | 195
5944 | 2018-04-09 | 2018-07-13 | 2018-10-10 | 2019-05-18 | COMP | 2019-07-03 | COMP | 2019-07-09 | COMP | 2019-06-29 | COMP | 2019-07-05 | COMP | Rule 16 | 68 | 63 | 32 | 4 | 0 |  | 313
6383 | 2018-04-09 | 2018-08-14 | 2018-09-19 | 2018-09-19 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2020-04-26 | INPR | 2019-06-24 | COMP | Rule 16 | 90 | 26 | 160 | 1 |  |  | 305
6579 | 2018-04-09 | 2018-08-28 | 2018-09-28 | 2018-09-28 | COMP | 2019-01-22 | COMP | 2019-01-22 | NOTN | 2019-01-16 | COMP | 2019-01-28 | COMP | Rule 16 | 100 | 23 | 77 |  |  |  | 202
6924 | 2018-04-09 | 2018-09-18 | 2019-01-30 | 2019-01-30 | COMP | 2019-07-25 | COMP | 2019-07-30 | COMP | 2020-05-06 | COMP | 2020-06-09 | COMP | Rule 16 | 114 | 91 | 124 | 4 | 194 | 24 | 546
7345 | 2018-04-09 | 2018-10-09 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-20 | COMP | 2019-03-20 | COMP | 2019-12-28 | INPR | 2019-07-26 | COMP | Rule 16 | 129 | 69 | 42 | 1 |  |  | 328
3334 | 2018-04-10 | 2018-04-10 | 2018-07-13 | 2018-07-13 | COMP | 2019-02-28 | COMP | 2019-02-28 | COMP | 2019-05-21 | COMP | 2019-06-17 | COMP | Rule 16 | 1 | 67 | 157 | 1 | 59 | 19 | 299
3408 | 2018-04-10 | 2018-04-20 | 2019-01-09 | 2020-07-03 | COMP | 2020-07-30 | COMP | 2020-07-31 | COMP | 2020-07-30 | COMP | 2020-10-07 | COMP | Rule 15/16 | 9 | 181 | 20 | 2 | 0 | 48 | 630
3412 | 2018-04-10 | 2018-04-24 | 2018-10-25 | 2018-10-25 | COMP | 2019-01-10 | COMP | 2019-03-26 | COMP | 2018-12-05 | COMP | 2019-05-04 | COMP | Rule 15/16 | 11 | 130 | 51 | 52 | 0 | 29 | 269
3456 | 2018-04-10 | 2018-04-30 | 2018-07-19 | 2018-07-19 | COMP | 2018-08-15 | COMP | 2018-08-17 | COMP | 2019-02-12 | COMP | 2019-02-06 | COMP | Rule 15/16 | 15 | 57 | 20 | 3 | 121 |  | 208
3570 | 2018-04-10 | 2018-05-17 | 2018-07-02 | 2018-10-11 | COMP | 2018-11-13 | COMP | 2018-10-02 | COMP | 2019-02-25 | COMP | 2019-03-13 | COMP | Rule 16 | 28 | 32 | 23 |  | 98 | 13 | 232
3956 | 2018-04-10 | 2018-10-29 | 2019-01-16 | 2019-01-16 | COMP | 2019-02-12 | COMP | 2019-03-08 | COMP | 2019-08-10 | COMP | 2019-08-16 | COMP | Rule 16 | 142 | 53 | 19 | 18 | 109 | 5 | 342
4014 | 2018-04-10 | 2018-11-30 | 2019-10-24 | 2019-10-24 | COMP | 2020-01-06 | COMP | 2020-03-16 | COMP | 2020-05-26 | COMP | 2020-07-15 | COMP | Rule 16 | 163 | 228 | 48 | 49 | 51 | 37 | 571
4059 | 2018-04-10 | 2019-01-04 | 2019-10-24 | 2019-10-24 | COMP | 2020-01-06 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2021-04-14 | COMP | Rule 16 | 186 | 205 | 48 | 13 | 1 | 310 | 758
4060 | 2018-04-10 | 2019-01-04 | 2020-02-06 | 2020-02-06 | COMP | 2020-10-16 | COMP | 2020-10-27 | COMP | 2021-01-14 | COMP | 2021-02-04 | COMP | Rule 15/16 | 186 | 274 | 179 | 8 | 53 | 15 | 710
4070 | 2018-04-10 | 2019-01-08 | 2019-02-27 | 2019-02-27 | COMP | 2019-05-28 | NOTN | 2019-05-28 | COMP |  |  | 2019-07-22 | COMP | Other | 188 | 35 |  | 64 |  |  | 323
4931 | 2018-04-10 | 2018-04-12 | 2018-09-07 | 2019-01-14 | COMP | 2019-01-23 | COMP | 2019-03-13 | INPR | 2019-10-21 | REQD | 2019-05-16 | COMP | Rule 16 | 3 | 104 | 7 |  |  |  | 278
4934 | 2018-04-10 | 2018-04-13 | 2018-05-01 | 2018-05-01 | COMP | 2018-05-17 | COMP | 2018-05-17 | COMP | 2018-05-16 | COMP | 2021-03-20 | COMP | Rule 16 | 4 | 13 | 13 | 1 | 0 | 713 | 740
5090 | 2018-04-10 | 2018-04-30 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2020-07-13 | COMP | 2020-08-25 | COMP | Rule 15/16 | 15 | 100 | 26 | 1 | 431 | 32 | 600
5188 | 2018-04-10 | 2018-05-08 | 2018-07-05 | 2018-07-05 | COMP | 2018-09-06 | COMP | 2018-09-06 | COMP | 2019-04-08 | COMP | 2019-05-23 | COMP | Rule 16 | 21 | 41 | 45 | 1 | 146 | 34 | 283
5256 | 2018-04-10 | 2018-05-14 | 2018-08-24 | 2018-08-24 | COMP | 2018-09-24 | COMP | 2019-04-05 | COMP | 2019-04-24 | COMP | 2019-05-08 | COMP | Rule 16 | 25 | 73 | 21 | 133 | 14 | 11 | 272
5269 | 2018-04-10 | 2018-05-15 | 2018-08-23 | 2018-08-23 | COMP | 2018-09-21 | COMP | 2018-09-21 | COMP | 2020-06-02 | COMP | 2020-07-24 | COMP | Rule 16 | 26 | 71 | 21 | 1 | 425 | 39 | 578
5314 | 2018-04-10 | 2018-05-22 | 2018-10-03 | 2018-10-03 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-06-27 | COMP | 2019-08-09 | COMP | Rule 16 | 31 | 94 | 60 | 1 | 125 | 31 | 337
5412 | 2018-04-10 | 2018-05-29 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-08 | COMP | 2019-08-28 | COMP | 2019-06-07 | COMP | 2019-11-18 | COMP | Rule 15/16 | 35 | 77 | 17 | 224 | 0 | 57 | 406
5521 | 2018-04-10 | 2018-06-07 | 2018-08-13 | 2018-08-13 | COMP | 2018-10-10 | COMP | 2018-10-10 | COMP | 2020-07-02 | COMP | 2020-08-05 | COMP | Rule 16 | 42 | 47 | 42 | 1 | 434 | 25 | 586
5605 | 2018-04-10 | 2018-06-18 | 2018-06-22 | 2018-06-22 | COMP | 2018-07-02 | COMP | 2019-02-13 | COMP | 2019-01-16 | COMP | 2019-02-27 | COMP | Rule 16 | 49 | 5 | 7 | 155 | 0 | 10 | 222
5995 | 2018-04-10 | 2018-07-17 | 2018-10-06 | 2018-10-06 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-03-11 | COMP | 2019-03-22 | COMP | Rule 15/16 | 69 | 58 | 49 | 1 | 56 | 10 | 239
6343 | 2018-04-10 | 2018-08-13 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-11 | COMP | 2019-01-09 | COMP | 2018-11-26 | COMP | 2019-01-29 | COMP | Rule 16 | 88 | 60 | 24 | 20 | 0 | 14 | 202
6570 | 2018-04-10 | 2018-08-27 | 2019-03-04 | 2019-04-03 | COMP | 2020-01-16 | COMP | 2019-07-03 | COMP | 2019-09-12 | COMP | 2019-08-09 | COMP | Rule 16 | 98 | 128 | 199 |  | 50 |  | 337
7171 | 2018-04-10 | 2018-10-01 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-31 | COMP | 2019-05-21 | COMP | 2019-05-07 | COMP | 2019-09-27 | COMP | Rule 16 | 122 | 34 | 29 | 99 | 0 | 91 | 371
7994 | 2018-04-10 | 2018-11-09 | 2019-01-25 | 2019-01-25 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-07-09 | COMP | 2019-07-19 | COMP | Rule 16 | 151 | 50 | 73 | 1 | 43 | 9 | 322
9268 | 2018-04-10 | 2019-01-25 | 2019-04-09 | 2019-04-09 | COMP | 2019-05-14 | COMP | 2019-05-26 | COMP | 2019-06-10 | COMP | 2019-08-05 | COMP | Rule 16 | 200 | 52 | 26 | 9 | 10 | 40 | 333
9794 | 2018-04-10 | 2019-02-15 | 2019-02-15 | 2019-02-25 | COMP |  |  |  |  | 2019-06-10 | COMP | 2019-06-20 | COMP | Other | 215 | 1 |  |  |  |  | 302
11012 | 2018-04-10 | 2019-04-10 | 2019-07-02 | 2019-07-02 | COMP | 2019-09-23 | COMP | 2020-03-11 | COMP | 2020-04-09 | COMP | 2020-04-24 | COMP | Rule 16 | 252 | 59 | 58 | 116 | 22 | 12 | 514
11475 | 2018-04-10 | 2019-04-29 | 2019-07-05 | 2019-07-05 | COMP | 2019-07-30 | COMP | 2019-07-16 | COMP | 2019-08-02 | COMP | 2019-08-28 | COMP | Rule 16 | 265 | 48 | 18 |  | 14 | 19 | 350
13412 | 2018-04-10 | 2019-07-24 | 2019-12-26 | 2019-12-26 | COMP | 2020-03-30 | COMP | 2020-07-16 | COMP | 2021-08-12 | COMP | 2021-09-14 | COMP | Rule 16 | 325 | 107 | 65 | 78 | 271 | 23 | 864
13413 | 2018-04-10 | 2019-07-24 | 2019-10-01 | 2019-10-01 | COMP | 2019-11-12 | COMP | 2020-04-22 | COMP | 2021-08-12 | COMP | 2021-09-14 | COMP | Rule 16 | 325 | 49 | 30 | 111 | 331 | 23 | 864
34307 | 2018-04-10 | 2022-02-08 | 2022-12-03 | 2022-12-03 | COMP | 2023-03-07 | COMP | 2023-03-07 | COMP | 2023-07-03 | COMP | 2023-11-09 | COMP | Rule 15/16 | 965 | 206 | 63 | 1 | 83 | 92 | 1406
3352 | 2018-04-11 | 2018-04-11 | 2018-06-06 | 2018-06-06 | COMP | 2018-06-06 | COMP | 2018-06-08 | COMP | 2019-01-07 | COMP | 2019-01-22 | COMP | Rule 16 | 1 | 40 | 1 | 3 | 145 | 11 | 196
3383 | 2018-04-11 | 2018-04-16 | 2018-06-20 | 2018-06-20 | COMP | 2018-08-07 | COMP | 2018-08-08 | COMP | 2019-04-18 | COMP | 2019-05-08 | COMP | Rule 16 | 4 | 47 | 34 | 2 | 174 | 15 | 271
3428 | 2018-04-11 | 2018-04-25 | 2018-05-02 | 2018-05-02 | COMP | 2018-09-26 | COMP | 2019-08-07 | COMP | 2020-02-29 | INPR | 2019-11-12 | COMP | Rule 16 | 11 | 6 | 103 | 217 |  |  | 401
3493 | 2018-04-11 | 2018-05-07 | 2018-08-10 | 2018-08-10 | COMP | 2018-12-11 | COMP | 2019-02-04 | COMP | 2019-06-02 | COMP | 2019-08-21 | COMP | Rule 16 | 19 | 68 | 84 | 37 | 83 | 57 | 344
4986 | 2018-04-11 | 2018-04-18 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-02-11 | COMP | 2019-04-22 | COMP | Rule 16 | 6 | 156 | 42 | 1 | 9 | 50 | 259
5042 | 2018-04-11 | 2018-04-26 | 2018-11-26 | 2018-11-26 | COMP | 2018-12-06 | NOTN | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-02-27 | COMP | Other | 12 | 147 |  | 9 | 1 | 56 | 221
5210 | 2018-04-11 | 2018-05-09 | 2018-10-12 | 2018-10-12 | COMP | 2018-08-20 | NOTN | 2018-11-13 | COMP | 2018-11-13 | COMP | 2019-01-10 | COMP | Other | 21 | 110 |  | 22 | 1 | 39 | 189
5222 | 2018-04-11 | 2018-05-11 | 2018-08-21 | 2018-08-21 | COMP | 2018-09-27 | COMP | 2018-11-21 | COMP | 2019-07-21 | INPR | 2019-02-05 | COMP | Rule 16 | 23 | 71 | 27 | 39 |  |  | 206
5255 | 2018-04-11 | 2018-05-14 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-22 | COMP | 2019-03-22 | COMP | 2019-03-12 | COMP | 2019-04-26 | COMP | Rule 16 | 24 | 95 | 19 | 103 | 0 | 26 | 263
5397 | 2018-04-11 | 2018-05-29 | 2019-01-15 | 2019-01-15 | COMP | 2019-01-23 | COMP | 2019-01-24 | COMP | 2019-02-28 | COMP | 2019-03-15 | COMP | Rule 15/16 | 34 | 159 | 6 | 2 | 25 | 12 | 233
5520 | 2018-04-11 | 2018-06-06 | 2018-10-01 | 2018-10-01 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2019-11-24 | INPR | 2019-08-05 | COMP | Rule 15/16 | 40 | 82 | 19 | 1 |  |  | 332
5690 | 2018-04-11 | 2018-06-25 | 2018-10-05 | 2018-10-05 | COMP | 2018-10-22 | COMP | 2018-10-23 | COMP | 2019-04-21 | INPR | 2019-01-29 | COMP | Rule 16 | 53 | 73 | 12 | 2 |  |  | 201
5948 | 2018-04-11 | 2018-07-13 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-13 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-06-11 | COMP | Rule 15/16 | 66 | 169 | 41 | 2 | 1 | 20 | 294
5949 | 2018-04-11 | 2018-07-13 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-21 | COMP | 2019-03-21 | COMP | 2019-05-11 | COMP | 2019-03-25 | COMP | Rule 15/16 | 66 | 137 | 16 | 21 | 37 |  | 239
5950 | 2018-04-11 | 2018-07-13 | 2019-02-11 | 2019-02-11 | COMP | 2019-05-13 | COMP | 2019-05-14 | COMP |  | INPR | 2019-08-25 | COMP | Rule 15/16 | 66 | 145 | 65 | 2 |  |  | 346
5985 | 2018-04-11 | 2018-07-17 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-26 | COMP | 2018-12-11 | COMP | 2018-11-26 | COMP | 2019-03-11 | COMP | Rule 15/16 | 68 | 59 | 33 | 12 | 0 | 61 | 229
6037 | 2018-04-11 | 2018-07-20 | 2018-10-05 | 2018-10-05 | COMP | 2019-07-26 | COMP | 2019-08-19 | COMP | 2019-09-16 | COMP | 2020-01-03 | COMP | Rule 16 | 71 | 55 | 202 | 17 | 20 | 75 | 435
6051 | 2018-04-11 | 2018-07-23 | 2018-12-06 | 2018-12-19 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-04-25 | COMP | 2019-05-02 | COMP | Rule 15/16 | 72 | 95 | 24 | 1 | 65 | 6 | 267
6174 | 2018-04-11 | 2018-08-01 | 2018-11-05 | 2018-11-05 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-11-24 | INPR | 2019-08-01 | COMP | Rule 16 | 79 | 68 | 133 | 1 |  |  | 330
6386 | 2018-04-11 | 2018-08-14 | 2018-11-27 | 2018-11-27 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-06-22 | COMP | 2019-07-19 | COMP | Rule 16 | 88 | 72 | 33 | 1 | 112 | 19 | 321
6999 | 2018-04-11 | 2018-09-21 | 2018-12-04 | 2018-12-04 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2021-01-21 | COMP | 2021-02-22 | COMP | Rule 16 | 115 | 50 | 46 | 1 | 491 | 22 | 720
7604 | 2018-04-11 | 2018-10-23 | 2019-05-24 | 2019-05-24 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-11-12 | COMP | 2020-02-24 | COMP | Rule 15/16 | 137 | 147 | 28 | 1 | 92 | 69 | 469
7605 | 2018-04-11 | 2018-10-23 | 2019-04-12 | 2019-04-12 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-10-05 | COMP | 2019-10-19 | COMP | Rule 15/16 | 137 | 117 | 58 | 1 | 66 | 10 | 385
7880 | 2018-04-11 | 2018-11-03 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-05 | COMP | 2019-03-12 | COMP | 2019-04-30 | COMP | 2019-06-28 | COMP | Rule 16 | 145 | 69 | 12 | 6 | 36 | 43 | 307
8108 | 2018-04-11 | 2018-11-15 | 2019-03-27 | 2019-04-19 | COMP | 2019-04-30 | COMP | 2019-07-24 | COMP | 2019-07-25 | COMP | 2019-09-23 | COMP | Rule 16 | 153 | 89 | 8 | 60 | 2 | 42 | 366
9680 | 2018-04-11 | 2019-02-12 | 2019-04-13 | 2019-04-13 | COMP | 2019-06-10 | COMP | 2019-08-23 | COMP | 2019-07-23 | COMP | 2019-08-07 | COMP | Rule 16 | 211 | 43 | 40 | 54 | 0 |  | 334
10085 | 2018-04-11 | 2019-03-01 | 2019-03-27 | 2019-03-27 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-05-02 | COMP | 2019-05-15 | COMP | Rule 16 | 223 | 19 | 16 | 1 | 12 | 10 | 276
13634 | 2018-04-11 | 2019-08-03 | 2019-08-20 | 2019-08-20 | COMP | 2019-11-14 | COMP | 2019-11-14 | COMP | 2020-01-02 | COMP | 2020-01-28 | COMP | Rule 16 | 331 | 12 | 61 | 1 | 32 | 18 | 451
15035 | 2018-04-11 | 2019-10-11 | 2019-10-23 | 2019-10-23 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2019-11-21 | COMP | 2020-01-06 | COMP | Rule 16 | 380 | 9 | 5 | 1 | 17 | 29 | 436
3445 | 2018-04-12 | 2018-04-27 | 2018-06-09 | 2018-06-09 | COMP | 2020-03-13 | COMP | 2021-03-16 | COMP | 2022-09-27 | COMP | 2022-12-21 | COMP | Rule 16 | 12 | 30 | 441 | 254 | 389 | 59 | 1181
3572 | 2018-04-12 | 2018-05-17 | 2018-08-14 | 2018-08-14 | COMP | 2019-08-22 | COMP | 2018-10-17 | NOTN | 2023-12-02 | INPR | 2020-11-02 | COMP | Rule 16 | 26 | 62 | 258 |  |  |  | 646
3640 | 2018-04-12 | 2018-05-31 | 2018-06-07 | 2020-07-07 | COMP | 2020-11-17 | COMP | 2020-11-18 | COMP | 2020-11-17 | COMP | 2021-01-06 | COMP | Rule 16 | 35 | 6 | 94 | 2 | 0 | 32 | 688
3641 | 2018-04-12 | 2018-05-31 | 2018-10-19 | 2019-03-08 | COMP | 2019-01-30 | NOTN | 2019-03-08 | COMP | 2019-01-30 | COMP | 2019-04-11 | COMP | Other | 35 | 100 |  | 1 | 0 | 25 | 251
3861 | 2018-04-12 | 2018-08-22 | 2019-04-20 | 2019-04-20 | COMP | 2019-08-26 | COMP | 2020-04-14 | COMP | 2020-10-13 | COMP | 2021-01-06 | COMP | Rule 15/16 | 93 | 165 | 89 | 159 | 129 | 57 | 688
3951 | 2018-04-12 | 2018-10-24 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-20 | COMP | 2019-04-08 | COMP | 2018-12-10 | COMP | 2019-05-14 | COMP | Rule 16 | 137 | 80 | 20 | 14 | 0 | 27 | 274
4071 | 2018-04-12 | 2019-01-08 | 2019-11-08 | 2019-11-08 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP |  |  | 2021-08-24 | COMP | Rule 15/16 | 186 | 214 | 37 | 1 |  |  | 848
5062 | 2018-04-12 | 2018-04-28 | 2018-12-11 | 2019-05-14 | COMP | 2020-02-03 | COMP | 2020-03-12 | COMP | 2020-04-14 | COMP | 2020-07-24 | COMP | Rule 15/16 | 12 | 156 | 181 | 28 | 24 | 73 | 576
5115 | 2018-04-12 | 2018-05-01 | 2018-07-28 | 2018-07-28 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-01-15 | COMP | 2019-03-13 | COMP | Rule 16 | 14 | 62 | 114 | 1 | 3 | 40 | 230
5129 | 2018-04-12 | 2018-05-03 | 2018-07-27 | 2018-07-27 | COMP | 2018-09-04 | COMP | 2018-09-04 | INPR | 2022-09-24 | REQD | 2021-06-23 | COMP | Rule 16 | 16 | 60 | 27 |  |  |  | 805
5131 | 2018-04-12 | 2018-05-02 | 2018-08-14 | 2018-08-14 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-04-11 | COMP | 2019-04-30 | COMP | Rule 16 | 15 | 73 | 57 | 1 | 109 | 14 | 264
5462 | 2018-04-12 | 2018-06-01 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-01-10 | COMP | 2019-02-19 | COMP | Rule 16 | 36 | 94 | 51 | 1 | 10 | 27 | 214
5475 | 2018-04-12 | 2018-06-01 | 2018-10-10 | 2018-10-10 | COMP | 2018-12-13 | COMP | 2019-04-23 | COMP | 2019-05-02 | COMP | 2019-07-17 | COMP | Rule 16 | 36 | 92 | 44 | 90 | 8 | 53 | 318
5485 | 2018-04-12 | 2018-06-04 | 2018-11-16 | 2018-11-16 | COMP | 2019-07-09 | COMP | 2019-07-23 | COMP | 2019-07-10 | COMP | 2019-08-21 | COMP | Rule 16 | 37 | 117 | 160 | 11 | 0 | 22 | 343
5619 | 2018-04-12 | 2018-06-21 | 2019-01-28 | 2019-01-28 | COMP | 2019-05-28 | COMP | 2019-12-31 | COMP | 2020-01-06 | COMP | 2020-02-12 | COMP | Rule 16 | 50 | 150 | 85 | 150 | 4 | 27 | 461
6114 | 2018-04-12 | 2018-07-26 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-28 | COMP | 2019-01-14 | COMP | 2019-08-07 | COMP | 2019-11-05 | COMP | Rule 16 | 74 | 72 | 36 | 11 | 144 | 64 | 396
6316 | 2018-04-12 | 2018-08-09 | 2018-12-12 | 2018-12-12 | COMP | 2019-03-06 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-05-22 | COMP | Rule 16 | 84 | 86 | 57 | 37 | 1 | 20 | 280
6327 | 2018-04-12 | 2018-08-10 | 2018-11-28 | 2018-11-28 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-09-04 | COMP | Rule 15/16 | 85 | 75 | 178 | 1 | 1 | 17 | 352
6929 | 2018-04-12 | 2018-09-17 | 2018-11-03 | 2018-11-03 | COMP | 2019-01-07 | NOTN | 2019-01-07 | COMP | 2018-12-29 | COMP | 2019-02-12 | COMP | Other | 110 | 35 |  | 41 | 0 | 26 | 210
7183 | 2018-04-12 | 2018-10-02 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-16 | COMP | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-08-27 | COMP | Rule 16 | 121 | 44 | 29 | 117 | 1 | 40 | 347
7411 | 2018-04-12 | 2018-10-11 | 2018-12-03 | 2018-12-03 | COMP | 2019-01-22 | COMP | 2019-01-30 | COMP | 2019-03-22 | COMP | 2019-05-23 | COMP | Rule 16 | 128 | 35 | 34 | 7 | 37 | 45 | 281
8889 | 2018-04-12 | 2019-01-04 | 2019-09-24 | 2019-09-24 | COMP | 2021-04-01 | COMP | 2021-04-09 | COMP | 2021-10-19 | COMP | 2021-11-17 | COMP | Rule 15/16 | 184 | 183 | 382 | 7 | 135 | 21 | 907
9093 | 2018-04-12 | 2019-01-16 | 2019-03-05 | 2019-03-05 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-10-14 | COMP | 2019-10-22 | COMP | Rule 16 | 192 | 33 | 54 | 1 | 104 | 7 | 386
3490 | 2018-04-13 | 2018-05-07 | 2018-08-27 | 2018-08-27 | COMP | 2018-12-27 | COMP | 2019-01-10 | COMP | 2020-01-03 | COMP | 2020-02-12 | COMP | Rule 15/16 | 17 | 79 | 84 | 10 | 247 | 28 | 460
4995 | 2018-04-13 | 2018-04-20 | 2018-06-25 | 2018-06-25 | COMP | 2018-07-18 | COMP | 2018-07-18 | COMP | 2019-11-14 | COMP | 2020-01-07 | COMP | Rule 15/16 | 6 | 46 | 17 | 1 | 335 | 35 | 435
5009 | 2018-04-13 | 2018-04-23 | 2018-06-27 | 2018-06-27 | COMP | 2018-07-16 | COMP | 2018-07-16 | COMP | 2019-03-04 | COMP | 2019-04-29 | COMP | Rule 16 | 7 | 47 | 13 | 1 | 158 | 41 | 262
5156 | 2018-04-13 | 2018-05-04 | 2018-06-20 | 2018-08-01 | COMP | 2019-01-11 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-03-18 | COMP | Rule 16 | 16 | 33 | 112 | 30 | 1 | 16 | 232
5325 | 2018-04-13 | 2018-05-22 | 2018-10-05 | 2018-10-05 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2018-12-04 | COMP | 2019-01-29 | COMP | Rule 15/16 | 28 | 96 | 11 | 1 | 30 | 38 | 199
5388 | 2018-04-13 | 2018-05-25 | 2019-01-05 | 2019-01-05 | COMP | 2019-03-18 | COMP | 2021-10-08 | COMP | 2021-10-25 | COMP | 2021-11-19 | COMP | Rule 16 | 31 | 153 | 49 | 648 | 12 | 19 | 908
5463 | 2018-04-13 | 2018-06-01 | 2018-09-26 | 2018-09-26 | COMP | 2018-12-03 | COMP | 2019-04-21 | REQD | 2018-12-03 | COMP | 2019-01-06 | COMP | Rule 16 | 35 | 82 | 46 |  |  |  | 183
5492 | 2018-04-13 | 2018-06-04 | 2018-10-24 | 2018-10-24 | COMP | 2018-12-03 | COMP | 2019-01-07 | COMP | 2018-12-03 | COMP | 2019-02-05 | COMP | Rule 16 | 36 | 101 | 26 | 24 | 0 | 21 | 204
5579 | 2018-04-13 | 2018-06-15 | 2018-10-05 | 2018-10-05 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-05-06 | COMP | Rule 16 | 45 | 79 | 117 | 1 | 1 | 29 | 267
5580 | 2018-04-13 | 2018-06-15 | 2018-10-05 | 2018-10-05 | COMP | 2019-03-19 | COMP | 2019-03-21 | COMP | 2019-04-10 | COMP | 2019-07-12 | COMP | Rule 16 | 45 | 79 | 111 | 3 | 15 | 66 | 314
5731 | 2018-04-13 | 2018-06-27 | 2018-10-09 | 2019-03-07 | COMP | 2019-03-11 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-04-18 | COMP | Rule 16 | 53 | 73 | 3 | 21 | 1 | 9 | 255
5996 | 2018-04-13 | 2018-07-18 | 2018-11-06 | 2018-11-06 | COMP | 2018-12-06 | COMP | 2018-12-17 | COMP | 2019-01-22 | COMP | 2019-07-02 | COMP | Rule 16 | 67 | 79 | 20 | 8 | 24 | 114 | 307
6061 | 2018-04-13 | 2018-07-23 | 2018-09-25 | 2018-09-25 | COMP | 2019-02-04 | COMP | 2019-04-19 | COMP | 2019-04-18 | COMP | 2019-05-14 | COMP | Rule 16 | 70 | 46 | 89 | 54 | 0 | 18 | 273
6387 | 2018-04-13 | 2018-08-14 | 2018-09-12 | 2018-09-12 | COMP | 2018-10-04 | COMP | 2018-10-04 | COMP | 2018-11-03 | COMP | 2019-01-02 | COMP | Rule 16 | 86 | 21 | 17 | 1 | 22 | 38 | 181
6518 | 2018-04-13 | 2018-08-23 | 2018-10-30 | 2018-10-30 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-09-07 | COMP | Rule 16 | 93 | 48 | 153 | 1 | 1 | 62 | 353
6740 | 2018-04-13 | 2018-09-10 | 2018-11-01 | 2018-11-01 | COMP | 2018-11-21 | COMP | 2019-01-30 | COMP | 2019-01-24 | COMP | 2019-03-21 | COMP | Rule 16 | 104 | 39 | 14 | 46 | 0 | 36 | 235
7549 | 2018-04-13 | 2018-10-19 | 2019-01-30 | 2019-01-30 | COMP | 2021-11-23 | COMP | 2022-01-24 | COMP | 2022-11-15 | COMP | 2023-01-03 | COMP | Other | 133 | 68 | 711 | 42 | 206 | 32 | 1187
8084 | 2018-04-13 | 2018-11-15 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2020-10-01 | COMP | 2020-10-13 | COMP | Rule 15/16 | 151 | 46 | 12 | 1 | 417 | 9 | 631
9075 | 2018-04-13 | 2019-01-15 | 2019-05-06 | 2019-05-06 | COMP | 2019-05-23 | COMP | 2019-07-29 | COMP | 2019-07-23 | COMP | 2019-08-22 | COMP | Rule 16 | 190 | 78 | 14 | 46 | 0 | 19 | 343
9761 | 2018-04-13 | 2019-02-14 | 2019-04-06 | 2019-04-06 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2020-01-15 | COMP | 2020-01-27 | COMP | Rule 16 | 211 | 36 | 99 | 1 | 97 | 8 | 448
6039 | 2018-04-14 | 2018-07-20 | 2018-08-24 | 2018-08-24 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-04-16 | COMP | Rule 16 | 68 | 26 | 124 | 1 | 1 | 37 | 252
6476 | 2018-04-14 | 2018-08-20 | 2018-11-28 | 2018-11-28 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-03-07 | COMP | 2019-05-14 | COMP | Rule 16 | 89 | 69 | 96 | 1 | 0 | 21 | 272
7105 | 2018-04-14 | 2018-09-27 | 2018-11-20 | 2019-01-25 | COMP | 2019-03-15 | COMP | 2019-03-15 | INPR | 2018-11-29 | COMP | 2019-04-04 | COMP | Rule 16 | 116 | 38 | 35 |  |  |  | 244
5326 | 2018-04-15 | 2018-05-22 | 2018-11-28 | 2019-03-01 | COMP | 2019-05-07 | COMP | 2019-06-18 | COMP | 2020-01-31 | COMP | 2020-03-26 | COMP | Rule 16 | 27 | 131 | 48 | 30 | 156 | 39 | 489
3791 | 2018-04-16 | 2018-07-14 | 2018-10-08 | 2018-10-08 | COMP | 2019-01-31 | COMP | 2019-02-13 | COMP | 2019-10-19 | INPR | 2019-07-11 | COMP | Rule 16 | 63 | 60 | 78 | 10 |  |  | 312
3894 | 2018-04-16 | 2018-09-24 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-19 | COMP | 2019-02-05 | COMP | 2019-02-06 | COMP | 2019-03-07 | COMP | Rule 16 | 113 | 46 | 15 | 32 | 2 | 21 | 224
3990 | 2018-04-16 | 2018-11-13 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-25 | COMP | 2019-02-22 | COMP | 2020-09-26 | INPR | 2019-04-02 | COMP | Rule 16 | 148 | 39 | 11 | 20 |  |  | 242
5148 | 2018-04-16 | 2018-05-04 | 2018-09-10 | 2018-10-17 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-04-25 | COMP | 2019-05-03 | COMP | Rule 16 | 15 | 89 | 32 | 1 | 99 | 7 | 265
5151 | 2018-04-16 | 2018-05-03 | 2018-08-04 | 2018-08-04 | COMP | 2018-08-14 | COMP | 2018-11-15 | COMP | 2019-01-15 | COMP | 2019-02-12 | COMP | Rule 16 | 14 | 65 | 7 | 66 | 40 | 20 | 208
5163 | 2018-04-16 | 2018-05-04 | 2018-10-15 | 2018-10-15 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2018-12-31 | COMP | 2019-03-15 | COMP | Rule 16 | 15 | 114 | 53 | 1 | 0 | 51 | 230
5261 | 2018-04-16 | 2018-05-15 | 2018-06-28 | 2018-10-08 | COMP | 2018-11-21 | COMP | 2019-01-15 | COMP | 2019-10-21 | INPR | 2019-05-29 | COMP | Rule 16 | 22 | 32 | 32 | 36 |  |  | 282
5322 | 2018-04-16 | 2018-05-22 | 2018-08-20 | 2018-08-20 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2018-10-26 | COMP | 2019-01-03 | COMP | Rule 16 | 27 | 63 | 17 | 1 | 33 | 45 | 181
5429 | 2018-04-16 | 2018-05-31 | 2018-11-19 | 2018-11-19 | COMP | 2018-12-13 | COMP | 2018-12-13 | COMP | 2018-12-13 | COMP | 2019-02-27 | COMP | Rule 16 | 33 | 120 | 17 | 1 | 1 | 51 | 218
5447 | 2018-04-16 | 2018-05-31 | 2018-08-20 | 2018-08-20 | COMP | 2018-12-20 | COMP | 2019-01-23 | COMP | 2019-01-28 | COMP | 2019-02-27 | COMP | Rule 16 | 33 | 57 | 85 | 22 | 4 | 22 | 218
5784 | 2018-04-16 | 2018-07-02 | 2018-10-04 | 2018-10-04 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-04-04 | COMP | 2019-04-25 | COMP | Rule 16 | 55 | 67 | 73 | 1 | 52 | 16 | 259
6003 | 2018-04-16 | 2018-07-18 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2019-07-21 | INPR | 2019-02-19 | COMP | Rule 16 | 66 | 70 | 8 | 1 |  |  | 212
6034 | 2018-04-16 | 2018-07-19 | 2018-11-05 | 2018-11-05 | COMP | 2019-08-08 | COMP | 2019-08-08 | COMP | 2019-07-26 | COMP | 2019-09-26 | COMP | Other | 67 | 77 | 190 | 1 | 0 | 35 | 366
6119 | 2018-04-16 | 2018-07-30 | 2019-02-14 | 2019-02-14 | COMP | 2019-07-26 | COMP | 2020-06-10 | COMP | 2020-06-22 | COMP | 2020-07-17 | COMP | Rule 15/16 | 74 | 137 | 114 | 220 | 9 | 20 | 569
6201 | 2018-04-16 | 2018-08-03 | 2019-02-14 | 2020-01-22 | COMP | 2020-03-20 | COMP | 2020-03-20 | NOTN | 2021-04-23 | COMP | 2020-08-20 | COMP | Rule 15/16 | 78 | 133 | 42 |  |  |  | 593
6365 | 2018-04-16 | 2018-08-13 | 2018-11-14 | 2019-07-23 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2020-01-07 | COMP | 2020-01-10 | COMP | Rule 16 | 84 | 66 | 76 | 1 | 40 | 4 | 437
6393 | 2018-04-16 | 2018-08-15 | 2018-09-28 | 2018-09-18 | COMP | 2018-11-28 | COMP | 2018-12-05 | COMP | 2019-07-21 | INPR | 2019-04-17 | COMP | Rule 16 | 86 | 32 | 49 | 6 |  |  | 253
6413 | 2018-04-16 | 2018-08-16 | 2018-11-28 | 2020-02-19 | COMP | 2020-02-27 | COMP | 2020-02-28 | COMP | 2020-07-02 | COMP | 2020-08-10 | COMP | Rule 16 | 87 | 71 | 7 | 2 | 89 | 28 | 585
6599 | 2018-04-16 | 2018-08-29 | 2019-01-14 | 2019-01-14 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-11-25 | COMP | 2020-01-26 | COMP | Rule 15/16 | 96 | 93 | 129 | 1 | 92 | 40 | 446
6628 | 2018-04-16 | 2018-08-31 | 2018-11-07 | 2018-11-07 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-09-22 | INPR | 2019-05-28 | COMP | Rule 15/16 | 98 | 48 | 32 | 1 |  |  | 281
7416 | 2018-04-16 | 2018-10-12 | 2018-12-13 | 2018-12-13 | COMP | 2018-12-28 | COMP | 2019-01-03 | COMP | 2019-07-26 | COMP | 2019-09-03 | COMP | Rule 16 | 127 | 42 | 11 | 4 | 143 | 27 | 349
7849 | 2018-04-16 | 2018-11-02 | 2019-03-28 | 2021-12-22 | COMP | 2022-02-22 | COMP | 2022-05-20 | COMP | 2022-05-20 | COMP | 2022-08-01 | COMP | Rule 16 | 142 | 98 | 43 | 64 | 1 | 49 | 1081
8237 | 2018-04-16 | 2018-11-20 | 2019-01-31 | 2020-03-09 | COMP | 2020-10-13 | COMP | 2020-10-28 | COMP | 2020-10-23 | COMP | 2020-11-30 | COMP | Rule 16 | 153 | 48 | 155 | 12 | 0 | 21 | 661
8964 | 2018-04-16 | 2019-01-09 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-12-28 | INPR | 2019-09-03 | COMP | Rule 15/16 | 185 | 48 | 14 | 1 |  |  | 349
9629 | 2018-04-16 | 2019-02-09 | 2019-05-26 | 2019-05-26 | COMP | 2019-06-24 | COMP | 2019-06-24 | INPR | 2019-08-19 | COMP | 2019-09-30 | COMP | Rule 16 | 206 | 74 | 20 |  |  |  | 368
9803 | 2018-04-16 | 2019-02-16 | 2019-03-11 | 2019-05-09 | COMP | 2019-08-06 | COMP | 2019-08-15 | COMP | 2020-03-21 | INPR | 2019-10-08 | COMP | Rule 16 | 211 | 15 | 62 | 8 |  |  | 374
10714 | 2018-04-16 | 2019-03-27 | 2019-04-09 | 2019-04-09 | COMP | 2019-05-17 | COMP | 2019-08-21 | COMP | 2019-12-06 | COMP | 2020-01-17 | COMP | Rule 15/16 | 238 | 10 | 29 | 67 | 74 | 29 | 442
40653 | 2018-04-16 | 2023-01-20 | 2023-04-18 | 2023-04-18 | COMP | 2023-05-08 | NOTN | 2023-06-29 | COMP | 2023-07-12 | COMP | 2023-11-07 | COMP | Other | 1198 | 62 |  | 51 | 9 | 84 | 1400
3500 | 2018-04-17 | 2018-05-08 | 2018-10-02 | 2018-10-02 | COMP | 2019-01-02 | COMP | 2019-02-15 | COMP | 2019-02-19 | COMP | 2019-04-01 | COMP | Rule 15/16 | 16 | 103 | 62 | 32 | 2 | 30 | 240
4058 | 2018-04-17 | 2019-01-03 | 2020-06-12 | 2020-06-12 | COMP | 2020-09-24 | COMP | 2020-11-18 | COMP | 2020-11-06 | COMP | 2020-11-23 | COMP | Rule 16 | 180 | 364 | 74 | 39 | 0 | 4 | 657
4125 | 2018-04-17 | 2019-03-18 | 2019-08-12 | 2019-07-15 | COMP | 2020-12-29 | COMP | 2021-09-03 | COMP | 2021-06-07 | COMP | 2021-11-04 | COMP | Other | 230 | 104 | 368 | 174 | 0 | 44 | 896
5161 | 2018-04-17 | 2018-05-04 | 2018-07-03 | 2018-07-03 | COMP | 2018-07-25 | COMP | 2018-09-07 | COMP | 2018-11-20 | COMP | 2019-01-10 | COMP | Rule 16 | 14 | 42 | 16 | 32 | 52 | 34 | 185
5182 | 2018-04-17 | 2018-05-08 | 2018-06-26 | 2018-06-26 | COMP | 2018-07-13 | COMP | 2018-08-30 | COMP | 2019-10-03 | COMP | 2019-11-07 | COMP | Rule 16 | 16 | 35 | 13 | 35 | 275 | 26 | 395
5268 | 2018-04-17 | 2018-05-15 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-01 | COMP | 2019-01-22 | COMP | 2019-01-30 | COMP | 2019-04-04 | COMP | Rule 16 | 21 | 117 | 4 | 53 | 7 | 46 | 243
5398 | 2018-04-17 | 2018-05-29 | 2018-09-14 | 2018-09-14 | COMP | 2018-11-15 | COMP | 2019-01-02 | COMP | 2018-11-26 | COMP | 2019-01-16 | COMP | Rule 16 | 30 | 77 | 44 | 31 | 0 | 11 | 189
5406 | 2018-04-17 | 2018-05-29 | 2018-10-24 | 2018-11-15 | COMP | 2018-12-12 | COMP | 2019-04-22 | COMP | 2019-06-05 | COMP | 2019-07-31 | COMP | Rule 16 | 30 | 105 | 18 | 90 | 32 | 40 | 325
5422 | 2018-04-17 | 2018-05-30 | 2018-08-06 | 2018-08-06 | COMP | 2018-09-28 | COMP | 2018-09-28 | COMP | 2018-12-07 | COMP | 2019-01-16 | COMP | Rule 16 | 31 | 48 | 39 | 1 | 48 | 27 | 189
5923 | 2018-04-17 | 2018-07-11 | 2018-10-08 | 2018-10-08 | COMP | 2018-10-24 | COMP | 2018-12-13 | COMP | 2019-09-22 | INPR | 2019-05-22 | COMP | Rule 16 | 60 | 63 | 13 | 34 |  |  | 277
6276 | 2018-04-17 | 2018-08-07 | 2018-11-29 | 2018-11-29 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-07-21 | INPR | 2019-04-15 | COMP | Rule 16 | 79 | 79 | 57 | 1 |  |  | 250
6399 | 2018-04-17 | 2018-08-15 | 2018-10-27 | 2018-10-27 | COMP | 2018-10-29 | NOTN | 2018-10-29 | COMP | 2019-03-07 | COMP | 2019-04-12 | COMP | Other | 85 | 52 |  | 1 | 87 | 27 | 249
6546 | 2018-04-17 | 2018-08-27 | 2018-12-21 | 2018-12-21 | COMP | 2019-11-25 | COMP | 2019-11-30 | COMP | 2019-12-02 | COMP | 2020-01-24 | COMP | Rule 16 | 93 | 81 | 234 | 3 | 1 | 37 | 445
7303 | 2018-04-17 | 2018-10-06 | 2019-02-28 | 2019-02-28 | COMP | 2019-04-09 | COMP | 2019-07-03 | COMP | 2021-03-27 | INPR | 2019-08-05 | COMP | Rule 16 | 121 | 97 | 29 | 61 |  |  | 328
7386 | 2018-04-17 | 2018-10-09 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-05-19 | COMP | 2019-05-27 | COMP | Rule 16 | 123 | 39 | 25 | 1 | 90 | 5 | 279
8421 | 2018-04-17 | 2018-11-30 | 2019-02-13 | 2019-02-13 | COMP | 2019-12-04 | COMP | 2020-01-06 | COMP | 2020-08-10 | COMP | 2020-02-25 | COMP | Rule 15/16 | 158 | 51 | 204 | 22 | 153 |  | 466
9760 | 2018-04-17 | 2019-02-14 | 2019-11-21 | 2019-11-21 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP |  | INPR | 2021-08-10 | COMP | Rule 15/16 | 209 | 196 | 103 | 1 |  |  | 835
10462 | 2018-04-17 | 2019-03-18 | 2019-05-18 | 2019-05-18 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-12-29 | INPR | 2019-08-13 | COMP | Rule 16 | 230 | 45 | 13 | 1 |  |  | 334
10787 | 2018-04-17 | 2019-03-30 | 2019-12-02 | 2019-12-02 | COMP | 2020-02-04 | COMP | 2020-07-21 | COMP | 2020-04-14 | COMP | 2020-08-14 | COMP | Rule 16 | 239 | 170 | 44 | 119 | 0 | 19 | 588
11275 | 2018-04-17 | 2019-04-22 | 2019-06-10 | 2020-08-12 | COMP | 2020-08-31 | COMP | 2020-06-03 | COMP | 2020-06-11 | COMP | 2020-08-28 | COMP | Rule 16 | 255 | 35 | 14 |  | 7 | 57 | 598
3451 | 2018-04-18 | 2018-04-29 | 2018-05-17 | 2018-05-17 | COMP | 2019-01-17 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-04-01 | COMP | Rule 15/16 | 8 | 14 | 168 | 2 | 1 | 50 | 239
3469 | 2018-04-18 | 2018-05-01 | 2018-08-08 | 2018-08-08 | COMP | 2018-08-21 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-04-26 | COMP | Rule 15/16 | 10 | 70 | 10 | 148 | 1 | 24 | 258
3511 | 2018-04-18 | 2018-05-09 | 2018-11-04 | 2018-11-04 | COMP | 2019-01-15 | COMP | 2019-02-06 | COMP | 2019-02-05 | COMP | 2020-12-03 | COMP | Rule 15/16 | 16 | 125 | 47 | 16 | 0 | 461 | 662
3733 | 2018-04-18 | 2018-06-19 | 2018-09-12 | 2018-12-13 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-03-27 | COMP | 2019-04-17 | COMP | Rule 16 | 44 | 60 | 12 | 1 | 60 | 16 | 251
3888 | 2018-04-18 | 2018-09-17 | 2018-10-23 | 2018-10-23 | COMP | 2019-02-05 | COMP | 2019-05-02 | COMP | 2019-05-04 | COMP | 2019-06-19 | COMP | Rule 16 | 106 | 27 | 70 | 62 | 2 | 32 | 295
5091 | 2018-04-18 | 2018-04-30 | 2018-06-08 | 2018-06-08 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-03-13 | COMP | 2019-03-15 | COMP | Rule 16 | 9 | 29 | 126 | 1 | 65 | 3 | 228
5092 | 2018-04-18 | 2018-04-30 | 2018-07-18 | 2018-07-18 | COMP | 2018-08-15 | COMP | 2018-08-23 | COMP | 2019-01-24 | COMP | 2019-02-04 | COMP | Rule 16 | 9 | 56 | 21 | 7 | 104 | 8 | 200
5280 | 2018-04-18 | 2018-05-16 | 2018-05-31 | 2018-12-26 | COMP | 2019-01-09 | COMP | 2018-06-12 | COMP | 2019-10-30 | COMP | 2020-08-24 | COMP | Rule 16 | 21 | 11 | 10 |  | 350 | 206 | 593
5396 | 2018-04-18 | 2018-05-29 | 2018-09-07 | 2021-07-26 | COMP | 2021-09-20 | COMP | 2022-03-08 | COMP | 2022-01-27 | COMP | 2022-04-22 | COMP | Rule 16 | 29 | 72 | 40 | 117 | 0 | 34 | 1011
5675 | 2018-04-18 | 2018-06-25 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-09-10 | COMP | 2019-09-19 | COMP | Rule 16 | 48 | 61 | 30 | 1 | 216 | 8 | 359
5712 | 2018-04-18 | 2018-06-26 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-04-30 | COMP | 2019-07-31 | COMP | Rule 16 | 49 | 60 | 30 | 1 | 124 | 65 | 324
5759 | 2018-04-18 | 2018-07-02 | 2018-07-11 | 2018-07-11 | COMP | 2018-07-25 | COMP | 2018-07-25 | COMP | 2019-04-05 | COMP | 2019-04-26 | COMP | Rule 16 | 53 | 7 | 11 | 1 | 175 | 16 | 258
6537 | 2018-04-18 | 2018-08-27 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-13 | COMP | 2018-11-16 | COMP | 2019-01-03 | COMP | 2019-02-05 | COMP | Rule 16 | 92 | 37 | 19 | 4 | 31 | 23 | 201
7584 | 2018-04-18 | 2018-10-22 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-07-21 | INPR | 2019-03-08 | COMP | Rule 16 | 131 | 17 | 16 | 1 |  |  | 223
8323 | 2018-04-18 | 2018-11-27 | 2019-03-08 | 2019-03-08 | COMP | 2019-06-10 | COMP | 2019-05-08 | COMP | 2019-10-21 | INPR | 2019-07-10 | COMP | Rule 16 | 154 | 70 | 66 |  |  |  | 309
8966 | 2018-04-18 | 2019-01-09 | 2019-10-18 | 2020-08-31 | COMP | 2020-09-17 | COMP | 2020-10-13 | COMP | 2020-11-05 | COMP | 2020-12-04 | COMP | Rule 16 | 183 | 198 | 13 | 19 | 18 | 19 | 663
9415 | 2018-04-18 | 2019-02-02 | 2019-03-20 | 2019-03-20 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-10-21 | INPR | 2019-06-19 | COMP | Rule 16 | 199 | 32 | 31 | 1 |  |  | 295
9456 | 2018-04-18 | 2019-02-05 | 2019-05-21 | 2019-07-12 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2019-09-16 | COMP | 2019-09-17 | COMP | Rule 16 | 201 | 75 | 30 | 1 | 17 | 2 | 357
10069 | 2018-04-18 | 2019-03-01 | 2019-11-05 | 2020-04-13 | COMP | 2020-07-02 | COMP | 2020-11-19 | COMP |  | INPR | 2020-11-23 | COMP | Rule 15/16 | 218 | 175 | 58 | 99 |  |  | 656
13040 | 2018-04-18 | 2019-07-08 | 2019-10-22 | 2019-10-22 | COMP | 2020-01-27 | COMP | 2022-04-27 | COMP | 2022-04-19 | COMP | 2022-05-20 | COMP | Other | 307 | 76 | 64 | 570 | 0 | 18 | 1031
13196 | 2018-04-18 | 2019-07-15 | 2019-10-21 | 2019-10-21 | COMP | 2019-11-25 | COMP | 2019-12-06 | COMP | 2019-12-02 | COMP | 2020-01-08 | COMP | Rule 16 | 312 | 70 | 25 | 8 | 0 | 22 | 433
3598 | 2018-04-19 | 2018-05-22 | 2018-10-27 | 2018-10-27 | COMP | 2019-01-16 | COMP | 2019-01-18 | COMP | 2019-01-14 | COMP | 2019-01-24 | COMP | Rule 16 | 24 | 111 | 53 | 3 | 0 | 4 | 192
3719 | 2018-04-19 | 2018-06-15 | 2018-10-01 | 2018-10-01 | COMP | 2018-10-22 | COMP | 2018-12-11 | COMP | 2020-02-04 | COMP | 2020-03-12 | COMP | Rule 16 | 41 | 75 | 16 | 34 | 288 | 27 | 476
4233 | 2018-04-19 | 2019-09-21 | 2020-02-03 | 2020-02-03 | COMP | 2020-04-20 | COMP | 2020-09-28 | COMP | 2021-06-27 | COMP | 2021-08-06 | COMP | Rule 16 | 359 | 90 | 55 | 114 | 187 | 29 | 831
5053 | 2018-04-19 | 2018-04-26 | 2018-06-20 | 2018-06-20 | COMP | 2018-07-03 | COMP | 2018-07-03 | COMP | 2019-04-15 | COMP | 2019-05-06 | COMP | Rule 16 | 6 | 39 | 10 | 1 | 196 | 16 | 263
5130 | 2018-04-19 | 2018-05-04 | 2018-09-19 | 2018-10-12 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-01-19 | COMP | 2019-04-12 | COMP | Rule 16 | 12 | 96 | 66 | 1 | 1 | 58 | 247
5171 | 2018-04-19 | 2018-05-07 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-16 | NOTN | 2018-11-16 | COMP | 2018-11-16 | COMP | 2019-03-04 | COMP | Other | 13 | 136 |  | 1 | 1 | 71 | 218
5176 | 2018-04-19 | 2018-05-08 | 2018-08-07 | 2018-09-10 | COMP | 2018-09-19 | COMP | 2018-09-19 | COMP | 2018-10-15 | COMP | 2022-07-08 | COMP | Rule 15/16 | 14 | 64 | 8 | 1 | 19 | 938 | 1062
5236 | 2018-04-19 | 2018-05-14 | 2018-12-21 | 2022-05-27 | COMP | 2022-06-10 | NOTN | 2022-06-24 | COMP | 2022-06-15 | COMP | 2022-08-05 | COMP | Other | 18 | 154 |  | 19 | 0 | 30 | 1082
5267 | 2018-04-19 | 2018-05-16 | 2018-06-14 | 2018-06-14 | COMP | 2018-07-06 | COMP | 2018-07-06 | COMP | 2022-03-19 | INPR | 2021-03-11 | COMP | Rule 16 | 20 | 21 | 16 | 1 |  |  | 727
5443 | 2018-04-19 | 2018-05-31 | 2018-08-22 | 2021-09-09 | COMP | 2021-09-16 | COMP | 2021-10-05 | COMP | 2021-10-08 | COMP | 2021-11-15 | COMP | Rule 16 | 30 | 59 | 6 | 14 | 4 | 26 | 900
5664 | 2018-04-19 | 2018-06-25 | 2018-11-19 | 2018-11-19 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-08-26 | COMP | 2019-10-23 | COMP | Rule 16 | 47 | 103 | 194 | 1 | 0 | 41 | 382
5713 | 2018-04-19 | 2018-06-26 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-19 | NOTN | 2018-12-24 | COMP | 2019-04-21 | INPR | 2019-01-23 | COMP | Other | 48 | 101 |  | 25 |  |  | 191
6007 | 2018-04-19 | 2018-07-18 | 2018-12-07 | 2018-12-07 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2022-03-21 | COMP | 2022-04-23 | COMP | Rule 16 | 63 | 99 | 18 | 1 | 809 | 25 | 1010
6266 | 2018-04-19 | 2018-08-07 | 2019-01-11 | 2019-01-11 | COMP | 2019-05-21 | COMP | 2019-05-22 | COMP | 2019-06-04 | COMP | 2019-06-10 | COMP | Rule 16 | 77 | 108 | 91 | 2 | 9 | 5 | 287
6500 | 2018-04-19 | 2018-08-22 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-08-26 | COMP | 2019-10-07 | COMP | Rule 16 | 88 | 67 | 16 | 1 | 173 | 30 | 370
6720 | 2018-04-19 | 2018-09-10 | 2019-03-08 | 2019-03-18 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-12-12 | COMP | 2020-01-25 | COMP | Rule 16 | 100 | 123 | 19 | 1 | 170 | 29 | 443
6827 | 2018-04-19 | 2018-09-12 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-12 | COMP | 2018-12-14 | COMP | 2019-05-17 | COMP | 2019-07-22 | COMP | Rule 16 | 102 | 54 | 10 | 3 | 107 | 45 | 316
7368 | 2018-04-19 | 2018-10-11 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-12 | COMP | 2019-04-22 | COMP | 2019-05-13 | COMP | 2019-05-16 | COMP | Rule 16 | 123 | 22 | 20 | 90 | 16 | 4 | 271
7900 | 2018-04-19 | 2018-11-06 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-12 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-05-24 | COMP | Rule 16 | 141 | 61 | 5 | 32 | 1 | 42 | 277
7903 | 2018-04-19 | 2018-11-05 | 2018-12-11 | 2018-12-11 | COMP | 2018-12-13 | COMP | 2018-12-21 | COMP | 2019-01-11 | COMP | 2019-03-12 | COMP | Rule 16 | 140 | 24 | 3 | 7 | 14 | 41 | 224
8036 | 2018-04-19 | 2018-11-12 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-13 | COMP | 2019-03-11 | COMP | 2019-05-02 | COMP | 2019-05-15 | COMP | Rule 16 | 144 | 47 | 16 | 18 | 39 | 10 | 270
8602 | 2018-04-19 | 2018-12-11 | 2019-03-01 | 2019-03-01 | COMP | 2019-05-08 | COMP | 2019-07-31 | COMP | 2020-08-21 | COMP | 2020-09-25 | COMP | Rule 15/16 | 163 | 55 | 49 | 59 | 269 | 25 | 615
10015 | 2018-04-19 | 2019-02-26 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2021-02-02 | COMP | 2021-02-14 | COMP | Rule 15/16 | 214 | 71 | 30 | 1 | 389 | 9 | 709
10643 | 2018-04-19 | 2019-03-23 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-14 | COMP | 2019-09-26 | COMP | 2019-08-31 | COMP | 2020-03-02 | COMP | Rule 16 | 232 | 81 | 21 | 31 | 0 | 106 | 468
11114 | 2018-04-19 | 2019-04-13 | 2019-08-08 | 2019-08-08 | COMP | 2022-01-10 | COMP | 2022-01-10 | COMP | 2023-07-26 | COMP | 2023-09-13 | COMP | Rule 16 | 247 | 82 | 610 | 1 | 387 | 35 | 1358
12943 | 2018-04-19 | 2019-07-01 | 2019-09-11 | 2020-01-10 | COMP | 2020-04-09 | COMP | 2020-04-10 | COMP | 2020-06-30 | COMP | 2020-09-18 | COMP | Rule 16 | 302 | 51 | 63 | 2 | 57 | 58 | 610
13027 | 2018-04-19 | 2019-07-06 | 2019-08-03 | 2019-08-03 | COMP | 2019-09-26 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-10-21 | COMP | Rule 16 | 305 | 20 | 38 | 16 | 1 | 3 | 380
14010 | 2018-04-19 | 2019-08-21 | 2019-10-05 | 2019-10-17 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-13 | COMP | 2019-11-15 | COMP | Rule 16 | 338 | 32 | 18 | 1 | 2 | 3 | 398
14254 | 2018-04-19 | 2019-08-30 | 2020-01-29 | 2020-01-29 | COMP | 2020-08-20 | COMP | 2020-10-27 | COMP | 2020-10-22 | COMP | 2020-11-24 | COMP | Rule 16 | 345 | 102 | 145 | 48 | 0 | 20 | 656
14449 | 2018-04-19 | 2019-09-10 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-23 | COMP | 2020-03-24 | COMP | 2020-06-23 | COMP | 2020-07-20 | COMP | Rule 16 | 351 | 112 | 22 | 2 | 65 | 20 | 567
3433 | 2018-04-20 | 2018-04-25 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-17 | COMP | 2019-01-14 | COMP | 2019-01-23 | COMP | 2019-03-21 | COMP | Rule 15/16 | 4 | 115 | 49 | 19 | 7 | 41 | 230
3443 | 2018-04-20 | 2018-04-26 | 2018-05-01 | 2018-05-01 | COMP | 2018-05-08 | COMP | 2018-05-22 | COMP | 2019-09-17 | COMP | 2019-11-25 | COMP | Rule 16 | 5 | 4 | 6 | 11 | 333 | 49 | 403
3475 | 2018-04-20 | 2018-05-02 | 2018-07-02 | 2018-07-02 | COMP | 2018-12-11 | COMP | 2019-01-18 | INPR | 2018-12-06 | COMP | 2019-02-08 | COMP | Rule 16 | 9 | 43 | 112 |  |  |  | 202
3563 | 2018-04-20 | 2018-05-17 | 2018-05-22 | 2018-05-22 | COMP | 2018-07-31 | COMP | 2018-08-16 | COMP | 2019-10-04 | COMP | 2019-11-19 | COMP | Rule 16 | 20 | 4 | 49 | 13 | 286 | 32 | 399
3642 | 2018-04-20 | 2018-06-01 | 2018-09-19 | 2019-07-15 | COMP | 2019-09-16 | COMP | 2018-11-14 | COMP | 2019-09-26 | COMP | 2019-11-06 | COMP | Rule 16 | 30 | 77 | 45 |  | 218 | 30 | 391
3783 | 2018-04-20 | 2018-07-11 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-19 | COMP | 2018-11-20 | COMP | 2018-10-23 | COMP | 2019-09-09 | COMP | Rule 16 | 57 | 89 | 4 | 2 | 0 | 201 | 349
4072 | 2018-04-20 | 2019-01-08 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-23 | COMP | 2019-08-20 | COMP | 2020-01-18 | INPR | 2019-10-02 | COMP | Rule 16 | 180 | 63 | 34 | 62 |  |  | 366
5458 | 2018-04-20 | 2018-06-01 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-03 | COMP | 2019-02-06 | COMP | Rule 16 | 30 | 114 | 26 | 1 | 9 | 24 | 200
5468 | 2018-04-20 | 2018-06-01 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-25 | COMP | 2018-12-06 | COMP | 2018-12-21 | COMP | 2019-01-30 | COMP | Rule 16 | 30 | 82 | 22 | 28 | 12 | 26 | 195
5567 | 2018-04-20 | 2018-06-14 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-21 | COMP | 2018-11-21 | COMP | 2019-02-14 | COMP | 2019-03-23 | COMP | Rule 16 | 39 | 83 | 30 | 1 | 57 | 26 | 231
5610 | 2018-04-20 | 2018-06-19 | 2018-07-02 | 2018-07-02 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2018-12-26 | COMP | 2019-01-02 | COMP | Rule 16 | 42 | 10 | 97 | 1 | 26 | 5 | 176
5640 | 2018-04-20 | 2018-06-22 | 2018-09-08 | 2018-09-08 | COMP | 2018-11-15 | COMP | 2018-11-21 | COMP | 2020-04-14 | COMP | 2020-07-12 | COMP | Rule 16 | 45 | 54 | 48 | 5 | 349 | 63 | 560
5958 | 2018-04-20 | 2018-07-16 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-11 | COMP | 2019-06-28 | COMP | 2019-07-29 | COMP | 2019-08-17 | COMP | Rule 16 | 60 | 88 | 16 | 139 | 21 | 15 | 334
6047 | 2018-04-20 | 2018-07-23 | 2019-04-12 | 2019-04-12 | COMP | 2019-08-09 | COMP | 2021-01-19 | COMP | 2021-03-29 | COMP | 2021-04-09 | COMP | Rule 15/16 | 65 | 182 | 84 | 362 | 49 | 10 | 747
6083 | 2018-04-20 | 2018-07-24 | 2018-10-03 | 2018-10-03 | COMP | 2019-01-18 | COMP | 2019-04-08 | COMP | 2019-03-26 | COMP | 2019-05-21 | COMP | Rule 15/16 | 66 | 51 | 73 | 55 | 0 | 32 | 273
6107 | 2018-04-20 | 2018-07-26 | 2018-10-17 | 2018-12-19 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-01-11 | COMP | 2019-03-14 | COMP | Rule 16 | 68 | 59 | 23 | 1 | 0 | 36 | 225
6220 | 2018-04-20 | 2018-08-06 | 2019-06-18 | 2019-06-18 | COMP | 2019-08-16 | COMP | 2019-09-03 | COMP | 2019-09-09 | COMP | 2019-12-20 | COMP | Rule 15/16 | 75 | 218 | 43 | 12 | 5 | 72 | 420
6255 | 2018-04-20 | 2018-08-08 | 2018-08-22 | 2018-08-22 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | Rule 16 | 77 | 11 | 81 | 1 | 25 | 1 | 191
6295 | 2018-04-20 | 2018-08-08 | 2019-01-17 | 2019-10-21 | COMP | 2023-05-27 | INPR | 2023-05-27 | CANC | 2023-05-27 | CANC | 2019-10-18 | COMP | Rule 16 | 77 | 111 |  |  |  |  | 378
6611 | 2018-04-20 | 2018-08-30 | 2019-01-16 | 2019-01-16 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-05-23 | COMP | 2019-08-11 | COMP | Rule 15/16 | 93 | 94 | 88 | 1 | 3 | 55 | 329
6937 | 2018-04-20 | 2018-09-18 | 2018-12-26 | 2018-12-26 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-08-13 | COMP | 2019-09-03 | COMP | Rule 16 | 105 | 68 | 40 | 1 | 121 | 15 | 345
7083 | 2018-04-20 | 2018-09-26 | 2019-07-25 | 2019-07-25 | COMP | 2019-09-23 | COMP | 2020-04-21 | COMP | 2020-03-13 | COMP | 2020-06-18 | COMP | Rule 15/16 | 111 | 208 | 42 | 145 | 0 | 42 | 544
7403 | 2018-04-20 | 2018-10-11 | 2018-12-21 | 2018-12-21 | COMP | 2019-03-06 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-05-20 | COMP | Rule 16 | 122 | 49 | 50 | 16 | 1 | 39 | 272
7626 | 2018-04-20 | 2018-10-23 | 2019-03-20 | 2019-03-20 | COMP | 2019-09-09 | COMP | 2019-09-12 | COMP | 2023-12-02 | INPR | 2022-05-04 | COMP | Rule 16 | 130 | 100 | 121 | 4 |  |  | 1017
8031 | 2018-04-20 | 2018-11-12 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-27 | COMP | 2019-04-03 | COMP | 2023-05-27 | INPR | 2019-05-29 | COMP | Rule 15/16 | 143 | 58 | 34 | 6 |  |  | 278
9419 | 2018-04-20 | 2019-02-04 | 2019-07-23 | 2019-07-23 | COMP | 2019-10-22 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-08-04 | COMP | Rule 16 | 198 | 119 | 65 | 166 | 1 | 33 | 577
10497 | 2018-04-20 | 2019-03-18 | 2019-07-01 | 2019-07-01 | COMP | 2019-12-09 | COMP | 2020-02-06 | COMP | 2020-06-22 | COMP | 2020-07-30 | COMP | Rule 16 | 227 | 75 | 111 | 41 | 96 | 29 | 574
12538 | 2018-04-20 | 2019-06-11 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-18 | COMP | 2019-07-18 | INPR | 2019-09-09 | COMP | 2019-09-06 | COMP | Rule 16 | 287 | 16 | 12 |  |  |  | 348
12737 | 2018-04-20 | 2019-06-20 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-11 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-08-19 | COMP | Rule 16 | 294 | 8 | 8 | 12 | 1 | 17 | 335
13322 | 2018-04-20 | 2019-07-19 | 2019-07-26 | 2019-07-26 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-16 | COMP | 2019-08-19 | COMP | Rule 16 | 314 | 6 | 3 | 1 | 14 | 2 | 335
13807 | 2018-04-20 | 2019-08-12 | 2020-02-18 | 2020-02-18 | COMP | 2020-03-16 | COMP | 2020-05-29 | COMP | 2020-12-01 | COMP | 2021-01-15 | COMP | Rule 16 | 330 | 129 | 20 | 54 | 129 | 32 | 689
3548 | 2018-04-23 | 2018-05-14 | 2018-11-29 | 2019-10-09 | COMP | 2019-10-16 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-24 | COMP | Rule 16 | 16 | 138 | 6 | 3 | 1 | 5 | 381
3594 | 2018-04-23 | 2018-05-22 | 2018-08-10 | 2018-08-10 | COMP | 2019-08-16 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-10-07 | COMP | Rule 16 | 22 | 57 | 256 | 3 | 1 | 34 | 368
3917 | 2018-04-23 | 2018-10-04 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-07 | COMP | 2019-02-07 | COMP | 2019-05-14 | COMP | 2019-03-01 | COMP | Rule 16 | 116 | 31 | 13 | 42 | 68 |  | 215
5145 | 2018-04-23 | 2018-05-03 | 2018-10-10 | 2018-10-10 | COMP | 2019-05-20 | COMP | 2019-08-05 | COMP | 2020-01-10 | COMP | 2020-02-13 | COMP | Rule 16 | 9 | 112 | 152 | 54 | 109 | 24 | 455
5158 | 2018-04-23 | 2018-05-04 | 2018-08-28 | 2018-08-28 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2020-03-17 | COMP | 2020-06-18 | COMP | Rule 16 | 10 | 81 | 41 | 1 | 348 | 67 | 543
5192 | 2018-04-23 | 2018-05-08 | 2018-08-16 | 2018-08-16 | COMP | 2019-06-19 | COMP | 2019-08-06 | COMP | 2019-09-12 | COMP | 2019-10-23 | COMP | Rule 16 | 12 | 71 | 211 | 34 | 27 | 30 | 380
5290 | 2018-04-23 | 2018-05-17 | 2018-07-31 | 2018-07-31 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2020-01-31 | COMP | 2020-02-10 | COMP | Rule 16 | 19 | 52 | 58 | 1 | 320 | 7 | 452
5291 | 2018-04-23 | 2018-05-17 | 2018-09-17 | 2018-09-17 | COMP | 2018-10-24 | COMP | 2018-10-24 | NOTN | 2020-01-31 | COMP | 2020-02-10 | COMP | Rule 16 | 19 | 85 | 28 |  |  |  | 452
5324 | 2018-04-23 | 2018-05-22 | 2018-07-19 | 2018-07-19 | COMP | 2018-10-31 | COMP | 2018-10-31 | COMP | 2019-03-21 | COMP | 2019-06-18 | COMP | Rule 16 | 22 | 41 | 74 | 1 | 95 | 63 | 291
5655 | 2018-04-23 | 2018-06-24 | 2018-10-10 | 2018-10-10 | COMP | 2019-02-21 | COMP | 2019-04-10 | COMP | 2019-04-16 | COMP | 2019-06-05 | COMP | Rule 16 | 44 | 76 | 90 | 35 | 5 | 36 | 282
5656 | 2018-04-23 | 2018-06-24 | 2018-12-05 | 2018-12-05 | COMP | 2019-02-22 | COMP | 2019-04-11 | COMP | 2019-08-06 | COMP | 2019-08-12 | COMP | Rule 16 | 44 | 113 | 54 | 35 | 82 | 5 | 329
5692 | 2018-04-23 | 2018-06-26 | 2018-10-08 | 2018-10-08 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-01-10 | COMP | 2019-02-20 | COMP | Rule 16 | 46 | 73 | 17 | 1 | 48 | 28 | 208
5725 | 2018-04-23 | 2018-06-27 | 2018-12-21 | 2018-12-21 | COMP | 2019-03-28 | COMP | 2019-05-01 | COMP | 2019-05-14 | COMP | 2019-06-21 | COMP | Rule 16 | 47 | 123 | 66 | 25 | 10 | 28 | 294
5742 | 2018-04-23 | 2018-06-28 | 2018-12-03 | 2019-02-15 | COMP | 2019-02-19 | COMP | 2019-02-20 | COMP | 2019-03-11 | COMP | 2019-04-17 | COMP | Rule 16 | 48 | 108 | 2 | 2 | 14 | 28 | 248
5798 | 2018-04-23 | 2018-07-03 | 2018-10-22 | 2018-10-22 | COMP | 2018-11-09 | COMP | 2018-12-21 | COMP | 2021-06-14 | COMP | 2021-07-09 | COMP | Rule 16 | 51 | 78 | 15 | 28 | 623 | 19 | 809
5936 | 2018-04-23 | 2018-07-12 | 2018-10-12 | 2018-10-12 | COMP | 2019-04-08 | COMP | 2019-05-03 | COMP | 2019-04-26 | COMP | 2019-06-11 | COMP | Rule 16 | 57 | 66 | 120 | 20 | 0 | 27 | 286
5940 | 2018-04-23 | 2018-07-12 | 2018-10-10 | 2018-10-10 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-10-07 | COMP | 2019-10-23 | COMP | Rule 16 | 57 | 64 | 234 | 1 | 16 | 13 | 380
5957 | 2018-04-23 | 2018-07-16 | 2018-09-11 | 2018-09-11 | COMP | 2018-09-21 | COMP | 2018-12-06 | COMP | 2019-10-01 | COMP | 2019-09-27 | COMP | Rule 16 | 59 | 41 | 9 | 52 | 207 |  | 362
6136 | 2018-04-23 | 2018-07-30 | 2018-09-27 | 2018-09-27 | COMP | 2019-01-11 | COMP | 2019-08-21 | COMP | 2019-12-17 | COMP | 2020-01-13 | COMP | Rule 16 | 69 | 43 | 72 | 155 | 81 | 18 | 433
6179 | 2018-04-23 | 2018-08-01 | 2018-10-12 | 2020-01-29 | COMP | 2020-03-30 | COMP | 2019-02-22 | COMP | 2022-10-04 | COMP | 2023-05-17 | COMP | Rule 15/16 | 71 | 52 | 43 |  | 912 | 155 | 1275
6522 | 2018-04-23 | 2018-08-25 | 2019-01-19 | 2019-01-19 | COMP | 2019-03-11 | COMP | 2019-10-09 | COMP | 2020-03-21 | INPR | 2019-12-11 | COMP | Rule 16 | 88 | 99 | 34 | 150 |  |  | 412
6801 | 2018-04-23 | 2018-09-11 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-11 | COMP | 2019-03-12 | COMP | 2019-04-30 | COMP | 2019-06-13 | COMP | Rule 16 | 99 | 93 | 12 | 21 | 36 | 32 | 288
6912 | 2018-04-23 | 2018-09-17 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-08 | COMP | 2019-04-08 | COMP | 2019-04-03 | COMP | 2019-05-17 | COMP | Rule 16 | 103 | 105 | 14 | 22 | 0 | 30 | 270
6978 | 2018-04-23 | 2018-09-20 | 2018-11-04 | 2018-11-04 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2018-12-12 | COMP | 2019-01-09 | COMP | Rule 15/16 | 106 | 32 | 7 | 1 | 19 | 19 | 180
7031 | 2018-04-23 | 2018-09-23 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-16 | COMP | 2019-01-25 | COMP | 2019-01-22 | COMP | 2019-03-04 | COMP | Rule 16 | 107 | 71 | 8 | 7 | 0 | 26 | 216
7056 | 2018-04-23 | 2018-09-25 | 2018-12-05 | 2019-09-05 | COMP | 2019-10-16 | COMP | 2019-10-25 | COMP | 2021-02-27 | INPR | 2019-11-14 | COMP | Rule 16 | 109 | 49 | 30 | 8 |  |  | 395
7188 | 2018-04-23 | 2018-10-02 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2019-03-01 | COMP | 2019-04-15 | COMP | Rule 16 | 114 | 24 | 7 | 1 | 73 | 32 | 246
7200 | 2018-04-23 | 2018-10-02 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2018-12-14 | COMP | 2019-01-22 | COMP | Rule 16 | 114 | 39 | 11 | 1 | 3 | 25 | 188
8807 | 2018-04-23 | 2018-12-30 | 2019-10-03 | 2020-05-21 | COMP | 2020-12-30 | COMP | 2022-09-06 | COMP | 2022-09-20 | COMP | 2022-10-06 | COMP | Rule 15/16 | 173 | 193 | 154 | 425 | 11 | 13 | 1123
9161 | 2018-04-23 | 2019-01-18 | 2019-03-21 | 2019-03-21 | COMP | 2019-03-28 | COMP | 2019-06-27 | COMP | 2020-05-31 | INPR | 2019-08-02 | COMP | Rule 15/16 | 187 | 43 | 6 | 65 |  |  | 323
9230 | 2018-04-23 | 2019-01-23 | 2019-02-18 | 2019-02-18 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-04-05 | COMP | 2019-04-08 | COMP | Rule 16 | 189 | 18 | 11 | 1 | 24 | 2 | 241
9907 | 2018-04-23 | 2019-02-22 | 2019-05-23 | 2019-05-23 | COMP | 2019-06-14 | COMP | 2019-10-24 | COMP | 2020-05-31 | INPR | 2019-11-06 | COMP | Rule 16 | 210 | 65 | 16 | 93 |  |  | 390
10848 | 2018-04-23 | 2019-04-02 | 2019-05-09 | 2019-05-09 | COMP | 2019-06-07 | COMP | 2019-06-21 | COMP | 2019-06-27 | COMP | 2019-09-17 | COMP | Rule 15/16 | 237 | 28 | 21 | 11 | 5 | 57 | 354
11057 | 2018-04-23 | 2019-04-10 | 2020-03-18 | 2022-04-22 | COMP | 2022-04-19 | NOTN | 2022-05-12 | COMP | 2022-08-30 | COMP | 2022-10-06 | COMP | Other | 243 | 236 |  | 15 | 76 | 27 | 1123
11431 | 2018-04-23 | 2019-04-26 | 2019-08-12 | 2019-09-13 | COMP | 2019-09-30 | COMP | 2020-02-27 | COMP | 2020-03-02 | COMP | 2020-06-03 | COMP | Rule 16 | 255 | 75 | 12 | 102 | 3 | 67 | 532
11743 | 2018-04-23 | 2019-05-09 | 2019-09-06 | 2020-07-17 | COMP | 2020-08-14 | COMP | 2020-08-18 | COMP | 2020-10-06 | COMP | 2020-10-15 | COMP | Rule 16 | 264 | 84 | 21 | 3 | 35 | 8 | 627
12680 | 2018-04-23 | 2019-06-18 | 2019-10-23 | 2020-05-27 | COMP | 2020-07-21 | COMP | 2020-09-11 | COMP | 2020-11-30 | COMP | 2020-12-19 | COMP | Rule 15/16 | 291 | 90 | 40 | 38 | 54 | 15 | 670
13761 | 2018-04-23 | 2019-08-08 | 2020-03-18 | 2020-03-18 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-15 | COMP | 2020-07-10 | COMP | Rule 15/16 | 327 | 152 | 34 | 1 | 30 | 20 | 559
3567 | 2018-04-24 | 2018-05-17 | 2018-09-27 | 2018-09-27 | COMP | 2019-08-02 | COMP | 2019-09-10 | COMP | 2019-07-25 | COMP | 2019-09-11 | COMP | Rule 15/16 | 18 | 93 | 213 | 27 | 0 | 2 | 349
3587 | 2018-04-24 | 2018-05-22 | 2018-10-10 | 2018-10-10 | COMP | 2019-06-26 | COMP | 2019-07-22 | COMP | 2020-07-29 | COMP | 2020-08-24 | COMP | Rule 16 | 21 | 99 | 178 | 18 | 259 | 19 | 589
3737 | 2018-04-24 | 2018-06-21 | 2018-09-27 | 2018-09-27 | COMP | 2018-11-10 | NOTN | 2018-11-14 | COMP | 2018-12-28 | COMP | 2019-01-11 | COMP | Other | 42 | 69 |  | 34 | 30 | 10 | 181
3806 | 2018-04-24 | 2018-07-23 | 2018-10-08 | 2019-04-04 | COMP | 2019-08-01 | COMP | 2023-02-10 | COMP | 2023-05-24 | COMP | 2023-06-09 | COMP | Rule 16 | 63 | 55 | 84 | 887 | 73 | 12 | 1290
5063 | 2018-04-24 | 2018-04-28 | 2019-01-07 | 2019-03-29 | COMP | 2019-04-15 | COMP | 2019-08-28 | COMP | 2021-02-27 | INPR | 2019-10-07 | COMP | Rule 15/16 | 4 | 173 | 12 | 96 |  |  | 367
5121 | 2018-04-24 | 2018-05-02 | 2018-07-25 | 2018-07-25 | COMP | 2018-08-17 | COMP | 2018-08-17 | COMP | 2018-12-19 | COMP | 2019-03-25 | COMP | Rule 16 | 7 | 59 | 18 | 1 | 85 | 65 | 230
5209 | 2018-04-24 | 2018-05-09 | 2018-10-12 | 2018-10-12 | COMP | 2018-08-20 | NOTN | 2018-11-30 | COMP | 2019-01-03 | COMP | 2019-04-15 | COMP | Other | 12 | 110 |  | 33 | 23 | 71 | 245
5275 | 2018-04-24 | 2018-05-16 | 2018-06-05 | 2018-06-05 | COMP | 2018-06-12 | COMP | 2019-03-01 | COMP | 2022-11-05 | INPR | 2021-10-14 | COMP | Rule 16 | 17 | 14 | 6 | 180 |  |  | 876
5279 | 2018-04-24 | 2018-05-16 | 2018-09-19 | 2018-09-19 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-05-06 | COMP | 2019-06-05 | COMP | Rule 16 | 17 | 88 | 145 | 1 | 13 | 22 | 281
5289 | 2018-04-24 | 2018-05-17 | 2018-06-11 | 2018-06-11 | COMP | 2018-08-10 | COMP | 2018-08-10 | NOTN | 2019-03-04 | COMP | 2019-04-02 | COMP | Rule 16 | 18 | 17 | 44 |  |  |  | 236
5349 | 2018-04-24 | 2018-05-23 | 2018-08-04 | 2018-08-04 | COMP | 2018-08-27 | COMP | 2018-08-27 | COMP | 2018-10-24 | COMP | 2019-01-03 | COMP | Rule 16 | 22 | 51 | 16 | 1 | 42 | 47 | 175
5386 | 2018-04-24 | 2018-05-25 | 2018-08-23 | 2018-08-23 | COMP | 2018-09-14 | COMP | 2019-02-25 | COMP | 2019-07-21 | INPR | 2019-03-19 | COMP | Rule 15/16 | 24 | 63 | 16 | 110 |  |  | 226
5395 | 2018-04-24 | 2018-05-29 | 2018-08-28 | 2018-08-28 | COMP | 2018-09-12 | COMP | 2019-11-13 | COMP | 2019-10-24 | COMP | 2019-12-05 | COMP | Rule 16 | 25 | 65 | 11 | 295 | 0 | 15 | 407
5589 | 2018-04-24 | 2018-06-16 | 2018-06-26 | 2018-06-26 | COMP | 2018-10-10 | COMP | 2019-08-06 | COMP | 2018-10-11 | COMP | 2019-09-09 | COMP | Rule 16 | 38 | 7 | 75 | 206 | 0 | 24 | 347
5658 | 2018-04-24 | 2018-06-25 | 2018-07-02 | 2018-07-02 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2022-04-16 | INPR | 2021-03-26 | COMP | Rule 16 | 44 | 6 | 51 | 1 |  |  | 735
5663 | 2018-04-24 | 2018-06-25 | 2018-09-10 | 2018-09-10 | COMP | 2018-09-26 | COMP | 2018-09-26 | COMP | 2018-12-18 | COMP | 2019-01-29 | COMP | Rule 16 | 44 | 54 | 13 | 1 | 57 | 28 | 192
5782 | 2018-04-24 | 2018-07-03 | 2018-11-28 | 2018-11-28 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-06-10 | COMP | 2019-06-26 | COMP | Rule 15/16 | 50 | 102 | 106 | 3 | 27 | 13 | 296
5864 | 2018-04-24 | 2018-07-10 | 2018-09-07 | 2018-09-07 | COMP | 2018-09-27 | COMP | 2019-05-07 | COMP | 2019-10-21 | INPR | 2019-07-09 | COMP | Rule 15/16 | 54 | 43 | 15 | 152 |  |  | 304
5892 | 2018-04-24 | 2018-07-09 | 2018-10-05 | 2018-10-05 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-04-26 | COMP | 2019-05-27 | COMP | Rule 16 | 53 | 64 | 63 | 1 | 77 | 21 | 274
5906 | 2018-04-24 | 2018-07-11 | 2018-10-08 | 2018-12-21 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-02-28 | COMP | 2019-04-11 | COMP | Rule 16 | 55 | 63 | 44 | 1 | 3 | 31 | 243
5932 | 2018-04-24 | 2018-07-12 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-28 | COMP | 2019-01-03 | COMP | 2019-02-21 | COMP | 2019-06-13 | COMP | Rule 16 | 56 | 61 | 57 | 4 | 34 | 80 | 287
5978 | 2018-04-24 | 2018-07-16 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-06 | COMP | 2019-01-10 | COMP | 2019-01-08 | COMP | 2019-05-15 | COMP | Rule 16 | 58 | 83 | 18 | 24 | 0 | 88 | 267
5999 | 2018-04-24 | 2018-07-19 | 2019-02-19 | 2019-02-19 | COMP | 2019-10-07 | COMP | 2019-10-16 | COMP | 2019-10-20 | COMP | 2019-12-11 | COMP | Rule 16 | 61 | 146 | 162 | 8 | 3 | 35 | 411
6079 | 2018-04-24 | 2018-07-24 | 2019-04-06 | 2019-04-06 | COMP | 2019-06-27 | COMP | 2020-02-19 | COMP | 2020-02-28 | COMP | 2020-06-25 | COMP | Rule 15/16 | 64 | 176 | 58 | 161 | 8 | 84 | 547
6096 | 2018-04-24 | 2018-07-25 | 2018-11-16 | 2018-11-16 | COMP | 2019-02-12 | COMP | 2019-10-29 | COMP | 2021-02-27 | INPR | 2019-12-06 | COMP | Rule 15/16 | 65 | 81 | 58 | 182 |  |  | 408
6405 | 2018-04-24 | 2018-08-16 | 2018-09-07 | 2018-09-07 | COMP | 2018-09-13 | COMP | 2018-10-05 | COMP | 2018-12-17 | COMP | 2019-01-22 | COMP | Rule 16 | 81 | 16 | 5 | 17 | 49 | 24 | 187
6783 | 2018-04-24 | 2018-09-11 | 2019-01-01 | 2019-01-01 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-05-21 | COMP | 2019-08-08 | COMP | Rule 16 | 98 | 76 | 93 | 1 | 6 | 56 | 326
6861 | 2018-04-24 | 2018-09-14 | 2019-04-15 | 2019-04-15 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2020-10-22 | COMP | 2020-12-08 | COMP | Rule 16 | 101 | 145 | 94 | 1 | 294 | 31 | 661
6952 | 2018-04-24 | 2018-09-18 | 2018-12-05 | 2019-02-01 | COMP | 2019-02-26 | COMP | 2019-03-27 | COMP | 2019-03-07 | COMP | 2019-04-22 | COMP | Rule 15/16 | 103 | 54 | 17 | 22 | 0 | 19 | 250
7467 | 2018-04-24 | 2018-10-16 | 2019-03-07 | 2019-03-07 | COMP | 2019-05-14 | COMP | 2019-12-17 | COMP | 2019-11-06 | COMP | 2020-03-04 | COMP | Rule 15/16 | 123 | 96 | 49 | 150 | 0 | 53 | 467
7660 | 2018-04-24 | 2018-10-25 | 2019-01-18 | 2020-06-05 | COMP | 2020-06-02 | COMP | 2020-07-17 | COMP | 2023-09-30 | INPR | 2022-07-25 | COMP | Other | 130 | 57 |  | 34 |  |  | 1070
7661 | 2018-04-24 | 2018-10-25 | 2019-01-17 | 2020-06-05 | COMP | 2020-06-02 | COMP | 2020-06-29 | COMP | 2020-07-23 | COMP | 2022-07-25 | COMP | Other | 130 | 56 |  | 20 | 19 | 504 | 1070
7662 | 2018-04-24 | 2018-10-25 | 2019-01-17 | 2020-06-05 | COMP | 2020-06-03 | COMP | 2020-07-17 | COMP | 2020-09-02 | COMP | 2022-07-25 | COMP | Other | 130 | 56 |  | 33 | 34 | 475 | 1070
7735 | 2018-04-24 | 2018-10-29 | 2018-12-13 | 2018-12-13 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-29 | COMP | 2019-07-09 | COMP | Rule 16 | 132 | 31 | 55 | 1 | 19 | 71 | 304
8295 | 2018-04-24 | 2018-11-26 | 2019-04-03 | 2019-09-25 | COMP | 2019-10-08 | NOTN | 2019-10-08 | COMP | 2019-09-20 | COMP | 2019-11-22 | COMP | Other | 149 | 89 |  | 10 | 0 | 33 | 400
8453 | 2018-04-24 | 2018-12-03 | 2019-01-24 | 2019-01-24 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | Rule 16 | 154 | 36 | 140 | 1 | 21 | 1 | 348
10459 | 2018-04-24 | 2019-03-17 | 2019-08-20 | 2019-08-20 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-01-09 | COMP | 2020-02-14 | COMP | Rule 16 | 224 | 110 | 92 | 1 | 6 | 26 | 455
10869 | 2018-04-24 | 2019-04-02 | 2019-08-28 | 2019-08-28 | COMP | 2019-11-12 | NOTN | 2019-12-19 | COMP | 2019-11-16 | COMP | 2020-01-13 | COMP | Other | 236 | 105 |  | 78 | 0 | 16 | 432
11143 | 2018-04-24 | 2019-04-15 | 2019-08-22 | 2020-06-05 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-06-24 | COMP | 2020-07-29 | COMP | Rule 15/16 | 245 | 92 | 16 | 1 | 0 | 24 | 571
3643 | 2018-04-25 | 2018-06-01 | 2019-01-22 | 2019-01-22 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-04-23 | COMP | 2019-06-05 | COMP | Rule 15/16 | 27 | 160 | 66 | 1 | 0 | 30 | 280
3801 | 2018-04-25 | 2018-07-18 | 2018-08-24 | 2018-08-24 | COMP | 2018-09-14 | COMP | 2018-10-30 | COMP | 2018-12-11 | COMP | 2019-03-22 | COMP | Rule 16 | 59 | 28 | 15 | 33 | 28 | 70 | 228
3859 | 2018-04-25 | 2018-08-21 | 2018-08-24 | 2018-08-24 | COMP | 2018-09-04 | COMP | 2018-09-27 | COMP | 2019-10-14 | COMP | 2019-10-17 | COMP | Rule 16 | 83 | 4 | 7 | 18 | 263 | 4 | 374
5223 | 2018-04-25 | 2018-05-11 | 2018-07-17 | 2018-07-17 | COMP | 2018-08-17 | COMP | 2018-08-17 | COMP | 2019-06-19 | COMP | 2019-07-15 | COMP | Rule 16 | 13 | 46 | 24 | 1 | 210 | 18 | 307
5251 | 2018-04-25 | 2018-05-15 | 2018-10-30 | 2018-10-30 | COMP | 2018-12-10 | COMP | 2019-02-20 | COMP | 2019-01-02 | COMP | 2019-08-02 | COMP | Rule 15/16 | 15 | 118 | 27 | 49 | 0 | 116 | 321
5497 | 2018-04-25 | 2018-06-04 | 2018-11-16 | 2018-11-16 | COMP | 2019-01-03 | NOTN | 2019-01-03 | COMP | 2019-01-23 | COMP | 2019-02-08 | COMP | Other | 28 | 117 |  | 31 | 14 | 13 | 199
5508 | 2018-04-25 | 2018-06-05 | 2018-10-24 | 2019-04-04 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2021-03-27 | INPR | 2020-02-27 | COMP | Rule 16 | 29 | 100 | 22 | 1 |  |  | 462
5615 | 2018-04-25 | 2018-06-20 | 2018-08-20 | 2018-08-20 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-07-01 | COMP | 2019-08-20 | COMP | Rule 16 | 40 | 43 | 192 | 1 | 26 | 36 | 333
5733 | 2018-04-25 | 2018-06-27 | 2018-12-20 | 2018-12-20 | COMP | 2019-04-03 | COMP | 2019-04-10 | COMP | 2019-04-30 | COMP | 2019-07-13 | COMP | Rule 16 | 45 | 122 | 71 | 6 | 15 | 52 | 306
5975 | 2018-04-25 | 2018-07-16 | 2018-10-18 | 2018-10-18 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-02-28 | COMP | 2019-04-08 | COMP | Rule 16 | 57 | 68 | 31 | 1 | 59 | 28 | 239
6068 | 2018-04-25 | 2018-07-23 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-30 | COMP | 2018-11-30 | COMP | 2019-02-02 | COMP | 2019-03-19 | COMP | Rule 16 | 62 | 62 | 30 | 1 | 43 | 31 | 225
6346 | 2018-04-25 | 2018-08-13 | 2018-12-27 | 2018-12-27 | COMP | 2019-06-14 | COMP | 2020-05-18 | COMP | 2020-04-27 | COMP | 2020-07-06 | COMP | Rule 15/16 | 77 | 94 | 118 | 233 | 0 | 35 | 553
7322 | 2018-04-25 | 2018-10-08 | 2018-10-19 | 2018-10-27 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2018-11-20 | COMP | 2019-01-04 | COMP | Rule 16 | 116 | 10 | 4 | 1 | 13 | 30 | 175
8953 | 2018-04-25 | 2019-01-09 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-22 | COMP | 2019-05-10 | COMP | 2019-06-03 | COMP | 2019-06-11 | COMP | Rule 16 | 178 | 40 | 12 | 36 | 16 | 7 | 284
9367 | 2018-04-25 | 2019-01-31 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-08 | COMP | 2019-10-23 | COMP | 2019-11-18 | COMP | 2019-12-12 | COMP | Rule 16 | 193 | 45 | 25 | 118 | 18 | 17 | 411
11018 | 2018-04-25 | 2019-04-09 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-06-14 | COMP | 2019-07-19 | COMP | Rule 16 | 240 | 16 | 6 | 1 | 28 | 25 | 311
3495 | 2018-04-26 | 2018-05-08 | 2018-06-20 | 2018-06-20 | COMP | 2018-07-20 | COMP | 2018-09-20 | COMP | 2019-06-29 | INPR | 2019-03-12 | COMP | Rule 15/16 | 9 | 31 | 22 | 44 |  |  | 219
3724 | 2018-04-26 | 2018-06-19 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-11 | COMP | 2018-12-20 | COMP | 2021-02-27 | INPR | 2019-09-20 | COMP | Rule 16 | 38 | 106 | 16 | 8 |  |  | 354
3807 | 2018-04-26 | 2018-07-23 | 2018-09-18 | 2018-12-17 | COMP | 2019-03-04 | COMP |  | REQD | 2019-08-15 | COMP | 2019-09-10 | COMP | Rule 15/16 | 61 | 41 | 52 |  |  |  | 346
3920 | 2018-04-26 | 2018-10-10 | 2018-12-18 | 2018-12-18 | COMP | 2019-09-19 | COMP | 2020-04-27 | COMP | 2020-05-01 | COMP | 2020-11-24 | COMP | Rule 16 | 117 | 47 | 191 | 151 | 5 | 145 | 651
5183 | 2018-04-26 | 2018-05-08 | 2018-06-20 | 2018-06-20 | COMP | 2019-06-13 | COMP | 2019-06-13 | INPR |  | INPR | 2021-12-01 | COMP | Rule 16 | 9 | 31 | 247 |  |  |  | 905
5201 | 2018-04-26 | 2018-05-10 | 2018-09-14 | 2018-09-14 | COMP | 2018-10-17 | COMP | 2019-09-04 | COMP | 2019-12-19 | COMP | 2020-01-09 | COMP | Rule 16 | 11 | 89 | 24 | 221 | 74 | 14 | 428
5358 | 2018-04-26 | 2018-05-23 | 2018-09-19 | 2018-10-27 | COMP | 2018-10-29 | COMP | 2018-10-29 | COMP | 2019-10-21 | INPR | 2019-01-03 | COMP | Rule 16 | 20 | 83 | 1 | 1 |  |  | 173
5428 | 2018-04-26 | 2018-05-30 | 2018-09-04 | 2018-09-04 | COMP | 2018-09-14 | COMP | 2018-09-14 | COMP | 2018-12-12 | COMP | 2019-01-11 | COMP | Rule 15/16 | 24 | 68 | 9 | 1 | 61 | 21 | 179
5541 | 2018-04-26 | 2018-06-11 | 2018-09-07 | 2018-09-07 | COMP | 2018-09-17 | COMP | 2019-01-07 | COMP | 2019-01-22 | COMP | 2019-02-05 | COMP | Rule 16 | 32 | 63 | 7 | 76 | 11 | 11 | 195
5775 | 2018-04-26 | 2018-07-02 | 2018-08-16 | 2018-11-26 | COMP | 2019-01-10 | COMP | 2019-03-29 | COMP | 2019-09-03 | COMP | 2019-09-17 | COMP | Rule 16 | 47 | 33 | 32 | 55 | 110 | 11 | 351
5842 | 2018-04-26 | 2018-07-06 | 2018-11-15 | 2018-11-15 | COMP | 2018-11-16 | NOTN | 2018-11-16 | COMP | 2018-11-16 | COMP | 2019-01-23 | COMP | Other | 50 | 93 |  | 2 | 1 | 44 | 186
5925 | 2018-04-26 | 2018-07-11 | 2018-07-28 | 2018-07-28 | COMP | 2018-08-06 | COMP | 2019-04-03 | COMP | 2019-03-26 | COMP | 2019-04-04 | COMP | Rule 16 | 53 | 13 | 6 | 165 | 0 | 2 | 236
6215 | 2018-04-26 | 2018-08-03 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-10 | COMP | 2018-12-06 | COMP | 2020-02-29 | INPR | 2019-11-20 | COMP | Rule 16 | 70 | 34 | 15 | 39 |  |  | 396
6223 | 2018-04-26 | 2018-08-04 | 2019-01-30 | 2019-01-30 | COMP | 2019-03-25 | COMP | 2019-04-10 | COMP | 2019-06-25 | COMP | 2019-07-11 | COMP | Rule 16 | 70 | 121 | 38 | 13 | 54 | 12 | 304
6755 | 2018-04-26 | 2018-09-11 | 2019-02-12 | 2019-02-12 | COMP | 2019-04-11 | COMP | 2019-05-23 | COMP | 2019-08-28 | COMP | 2019-10-02 | COMP | Rule 15/16 | 96 | 105 | 42 | 31 | 68 | 25 | 362
7210 | 2018-04-26 | 2018-10-02 | 2019-01-14 | 2019-01-14 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-03-12 | COMP | 2019-03-20 | COMP | Rule 16 | 111 | 70 | 6 | 1 | 35 | 7 | 225
7409 | 2018-04-26 | 2018-10-12 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-04-19 | COMP | 2019-04-24 | COMP | Rule 16 | 119 | 39 | 10 | 1 | 82 | 4 | 250
8988 | 2018-04-26 | 2019-01-11 | 2019-05-13 | 2020-06-13 | COMP | 2020-07-13 | COMP | 2019-05-24 | COMP | 2020-10-20 | COMP | 2020-11-04 | COMP | Rule 16 | 179 | 85 | 21 |  | 356 | 12 | 638
9921 | 2018-04-26 | 2019-02-22 | 2019-06-29 | 2019-06-29 | COMP | 2019-08-14 | COMP | 2019-10-02 | COMP | 2019-09-16 | COMP | 2019-11-15 | COMP | Rule 15/16 | 207 | 90 | 32 | 35 | 0 | 32 | 393
13025 | 2018-04-26 | 2019-07-05 | 2019-09-24 | 2019-09-24 | COMP | 2019-12-09 | COMP | 2020-07-03 | COMP | 2020-08-24 | COMP | 2020-11-03 | COMP | Rule 15/16 | 300 | 57 | 52 | 145 | 37 | 51 | 637
14138 | 2018-04-26 | 2019-08-26 | 2020-03-11 | 2020-03-11 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-07-11 | COMP | 2020-11-20 | COMP | Rule 16 | 336 | 135 | 90 | 1 | 0 | 91 | 649
3730 | 2018-04-27 | 2018-06-19 | 2018-08-07 | 2019-06-17 | COMP | 2020-01-23 | COMP | 2020-01-27 | COMP | 2020-02-03 | COMP | 2020-04-13 | COMP | Rule 16 | 37 | 35 | 151 | 3 | 6 | 50 | 492
3790 | 2018-04-27 | 2018-07-14 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-15 | COMP | 2019-05-29 | COMP | 2023-04-22 | INPR | 2021-09-09 | COMP | Rule 15/16 | 54 | 201 | 10 | 10 |  |  | 848
5239 | 2018-04-27 | 2018-05-14 | 2018-08-13 | 2018-08-13 | COMP | 2019-01-23 | NOTN | 2019-01-23 | COMP | 2019-09-05 | COMP | 2019-11-04 | COMP | Other | 12 | 64 |  | 111 | 158 | 43 | 384
5369 | 2018-04-27 | 2018-05-24 | 2018-09-11 | 2018-11-08 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2020-07-25 | INPR | 2019-05-02 | COMP | Rule 16 | 20 | 76 | 49 | 1 |  |  | 255
5387 | 2018-04-27 | 2018-05-25 | 2018-09-04 | 2018-09-04 | COMP | 2018-11-29 | COMP | 2018-12-12 | COMP | 2019-03-04 | COMP | 2019-04-08 | COMP | Rule 15/16 | 21 | 70 | 60 | 10 | 55 | 26 | 237
5407 | 2018-04-27 | 2018-05-29 | 2018-08-01 | 2018-08-01 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2021-03-30 | COMP | 2021-04-19 | COMP | Rule 16 | 22 | 46 | 162 | 1 | 507 | 15 | 748
5441 | 2018-04-27 | 2018-05-31 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2018-11-10 | COMP | 2019-01-10 | COMP | Rule 16 | 24 | 103 | 9 | 1 | 5 | 39 | 177
5474 | 2018-04-27 | 2018-06-01 | 2018-08-29 | 2020-06-02 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | 2020-10-29 | COMP | 2020-12-11 | COMP | Rule 16 | 25 | 63 | 62 | 1 | 46 | 29 | 661
5496 | 2018-04-27 | 2018-06-04 | 2018-09-14 | 2018-09-14 | COMP | 2018-11-14 | COMP | 2018-10-09 | COMP | 2019-11-15 | COMP | 2020-01-07 | COMP | Rule 16 | 26 | 73 | 43 |  | 278 | 34 | 425
5499 | 2018-04-27 | 2018-06-05 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-29 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-08-05 | COMP | Rule 15/16 | 27 | 88 | 36 | 150 | 1 | 23 | 320
5531 | 2018-04-27 | 2018-06-12 | 2018-09-03 | 2018-09-03 | COMP | 2018-09-11 | COMP | 2018-09-11 | COMP | 2019-03-12 | COMP | 2019-03-21 | COMP | Rule 16 | 32 | 58 | 6 | 1 | 124 | 8 | 225
5582 | 2018-04-27 | 2018-06-15 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-03 | COMP | 2019-02-28 | COMP | 2019-03-13 | COMP | 2019-06-27 | COMP | Rule 16 | 35 | 103 | 15 | 60 | 10 | 76 | 294
5601 | 2018-04-27 | 2018-06-18 | 2018-10-12 | 2018-10-12 | COMP | 2020-05-05 | COMP | 2021-04-28 | COMP | 2021-04-16 | COMP | 2021-05-20 | COMP | Rule 16 | 36 | 83 | 391 | 248 | 0 | 17 | 771
5831 | 2018-04-27 | 2018-07-07 | 2018-11-05 | 2018-11-05 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-05-04 | COMP | Rule 16 | 49 | 85 | 92 | 1 | 1 | 32 | 256
6135 | 2018-04-27 | 2018-07-30 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-01-28 | COMP | 2019-03-01 | COMP | Rule 15/16 | 65 | 49 | 45 | 1 | 32 | 24 | 211
6139 | 2018-04-27 | 2018-07-30 | 2018-10-30 | 2018-10-30 | COMP | 2019-03-28 | COMP | 2019-05-06 | COMP | 2019-11-24 | INPR | 2019-07-24 | COMP | Rule 15/16 | 65 | 66 | 101 | 28 |  |  | 312
6453 | 2018-04-27 | 2018-08-20 | 2018-12-17 | 2018-12-17 | COMP | 2018-12-20 | COMP | 2019-03-01 | COMP | 2019-01-30 | COMP | 2019-03-26 | COMP | Rule 16 | 80 | 82 | 4 | 48 | 0 | 18 | 228
7533 | 2018-04-27 | 2018-10-18 | 2019-01-24 | 2019-01-24 | COMP | 2019-04-03 | COMP | 2019-10-30 | COMP | 2021-02-09 | COMP | 2021-03-18 | COMP | Rule 16 | 122 | 65 | 49 | 148 | 320 | 27 | 726
8008 | 2018-04-27 | 2018-11-09 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-05-15 | COMP | 2019-08-29 | COMP | Rule 15/16 | 138 | 103 | 23 | 1 | 3 | 75 | 338
11092 | 2018-04-27 | 2019-04-12 | 2019-09-09 | 2019-09-09 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-12-18 | COMP | 2020-02-04 | COMP | Rule 16 | 241 | 104 | 52 | 1 | 19 | 32 | 444
11438 | 2018-04-27 | 2019-04-27 | 2019-06-05 | 2019-06-05 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-09-20 | COMP | 2019-10-16 | COMP | Rule 15/16 | 251 | 27 | 60 | 1 | 17 | 19 | 371
6713 | 2018-04-28 | 2018-09-10 | 2019-03-13 | 2019-03-13 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-30 | COMP | 2019-11-13 | COMP | Rule 15/16 | 93 | 126 | 104 | 1 | 38 | 32 | 389
8779 | 2018-04-29 | 2018-12-26 | 2019-03-26 | 2019-03-26 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2020-04-14 | COMP | 2020-05-10 | COMP | Rule 16 | 166 | 62 | 178 | 1 | 89 | 19 | 510
9289 | 2018-04-29 | 2019-01-28 | 2019-04-15 | 2021-05-12 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2021-04-20 | COMP | 2021-06-15 | COMP | Rule 16 | 187 | 55 | 8 | 1 | 0 | 17 | 787
3519 | 2018-04-30 | 2018-05-10 | 2019-02-13 | 2019-02-13 | COMP | 2020-07-07 | COMP | 2020-07-15 | COMP | 2020-07-13 | COMP | 2020-08-25 | COMP | Rule 15/16 | 9 | 191 | 353 | 7 | 0 | 30 | 586
3524 | 2018-04-30 | 2018-05-10 | 2019-03-06 | 2019-03-06 | COMP | 2019-11-27 | COMP | 2020-01-31 | COMP | 2020-10-29 | COMP | 2020-12-01 | COMP | Rule 15/16 | 9 | 205 | 187 | 43 | 192 | 21 | 652
3569 | 2018-04-30 | 2018-05-17 | 2018-10-03 | 2018-10-03 | COMP | 2019-01-16 | COMP | 2019-04-10 | COMP | 2019-03-26 | COMP | 2019-05-17 | COMP | Rule 16 | 14 | 97 | 71 | 59 | 0 | 28 | 265
3628 | 2018-04-30 | 2018-05-25 | 2018-07-23 | 2018-07-23 | COMP | 2018-11-05 | COMP | 2018-11-13 | COMP | 2019-12-28 | INPR | 2019-07-09 | COMP | Rule 15/16 | 20 | 40 | 75 | 6 |  |  | 300
3867 | 2018-04-30 | 2018-08-28 | 2018-12-19 | 2018-12-19 | COMP | 2019-03-11 | COMP | 2019-04-03 | NOTN | 2020-04-28 | COMP | 2020-06-04 | COMP | Rule 15/16 | 85 | 78 | 55 |  |  |  | 528
5366 | 2018-04-30 | 2018-05-24 | 2018-07-19 | 2018-07-25 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2019-08-30 | COMP | 2019-09-11 | COMP | Rule 16 | 19 | 39 | 72 | 1 | 207 | 8 | 345
5445 | 2018-04-30 | 2018-05-31 | 2018-08-29 | 2018-08-29 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2018-12-10 | COMP | 2019-01-18 | COMP | Rule 16 | 23 | 64 | 48 | 1 | 23 | 28 | 182
5476 | 2018-04-30 | 2018-06-01 | 2018-11-10 | 2018-11-10 | COMP | 2019-05-24 | NOTN | 2019-12-09 | COMP | 2019-11-01 | COMP | 2020-01-09 | COMP | Other | 24 | 114 |  | 268 | 0 | 22 | 426
5481 | 2018-04-30 | 2018-06-05 | 2019-01-31 | 2019-12-17 | COMP | 2020-01-08 | COMP | 2019-09-25 | COMP | 2020-01-25 | COMP | 2020-03-04 | COMP | Rule 16 | 26 | 165 | 15 |  | 82 | 27 | 463
5486 | 2018-04-30 | 2018-06-04 | 2018-09-26 | 2018-09-26 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-05-29 | COMP | Rule 16 | 25 | 81 | 117 | 1 | 1 | 52 | 272
5726 | 2018-04-30 | 2018-06-27 | 2018-12-12 | 2020-07-07 | COMP | 2020-08-06 | COMP | 2019-10-25 | COMP | 2019-11-05 | COMP | 2020-11-30 | COMP | Rule 15/16 | 42 | 116 | 23 |  | 8 | 268 | 651
5843 | 2018-04-30 | 2018-07-06 | 2018-09-10 | 2018-09-10 | COMP | 2018-12-05 | COMP | 2019-01-30 | COMP | 2019-01-22 | COMP | 2019-03-11 | COMP | Rule 16 | 48 | 46 | 60 | 38 | 0 | 28 | 216
6113 | 2018-04-30 | 2018-07-26 | 2018-09-27 | 2018-09-27 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-10-02 | COMP | 2019-10-15 | COMP | Rule 16 | 62 | 45 | 122 | 1 | 134 | 10 | 369
6142 | 2018-04-30 | 2018-07-31 | 2018-10-24 | 2018-10-24 | COMP | 2019-01-02 | COMP | 2019-05-09 | COMP | 2019-07-19 | COMP | 2019-08-07 | COMP | Rule 16 | 65 | 61 | 46 | 90 | 50 | 14 | 321
6144 | 2018-04-30 | 2018-07-30 | 2018-12-13 | 2018-12-21 | COMP | 2019-01-31 | COMP | 2019-08-08 | COMP | 2019-08-12 | COMP | 2019-08-22 | COMP | Other | 64 | 95 | 27 | 133 | 3 | 9 | 332
6196 | 2018-04-30 | 2018-08-03 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-09-10 | COMP | 2019-07-29 | COMP | Rule 16 | 68 | 80 | 35 | 1 | 164 |  | 314
6273 | 2018-04-30 | 2018-08-07 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-19 | COMP | 2019-04-09 | COMP | 2020-05-23 | INPR | 2019-05-20 | COMP | Rule 16 | 70 | 48 | 46 | 76 |  |  | 266
6390 | 2018-04-30 | 2018-08-15 | 2018-11-05 | 2018-11-05 | COMP | 2018-11-26 | COMP | 2019-02-19 | COMP | 2019-07-21 | INPR | 2019-03-14 | COMP | Rule 16 | 76 | 58 | 13 | 58 |  |  | 219
6533 | 2018-04-30 | 2018-08-28 | 2019-02-28 | 2019-02-28 | COMP | 2019-12-04 | COMP | 2020-01-30 | COMP | 2020-05-12 | COMP | 2020-07-31 | COMP | Rule 16 | 85 | 125 | 194 | 39 | 73 | 58 | 569
6547 | 2018-04-30 | 2018-08-27 | 2019-02-15 | 2019-10-23 | COMP | 2020-03-24 | COMP | 2020-04-24 | COMP | 2021-04-05 | COMP | 2021-05-24 | COMP | Rule 16 | 84 | 118 | 103 | 24 | 238 | 36 | 772
6596 | 2018-04-30 | 2018-08-29 | 2018-10-12 | 2019-02-12 | COMP | 2019-04-02 | COMP | 2019-07-18 | INPR | 2019-07-25 | COMP | 2019-08-05 | COMP | Rule 15/16 | 86 | 32 | 35 |  |  |  | 319
6904 | 2018-04-30 | 2018-09-19 | 2019-05-01 | 2019-05-01 | COMP | 2019-10-29 | COMP | 2020-01-28 | COMP | 2020-02-19 | COMP | 2020-05-12 | COMP | Rule 16 | 100 | 154 | 127 | 60 | 16 | 60 | 512
7099 | 2018-04-30 | 2018-09-26 | 2018-10-19 | 2018-10-19 | COMP | 2018-12-12 | COMP | 2018-12-20 | COMP | 2018-12-19 | COMP | 2019-01-04 | COMP | Rule 16 | 105 | 18 | 36 | 7 | 0 | 10 | 172
7248 | 2018-04-30 | 2018-10-04 | 2018-10-31 | 2018-10-31 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-01-13 | COMP | 2019-03-04 | COMP | Rule 16 | 111 | 20 | 46 | 1 | 3 | 34 | 211
7414 | 2018-04-30 | 2018-10-12 | 2019-02-09 | 2019-02-09 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-10-25 | COMP | 2019-12-14 | COMP | Rule 16 | 117 | 80 | 17 | 1 | 165 | 33 | 409
7582 | 2018-04-30 | 2018-10-21 | 2018-12-03 | 2018-12-03 | COMP | 2019-02-11 | COMP | 2019-02-26 | COMP | 2019-07-21 | INPR | 2019-04-12 | COMP | Rule 16 | 122 | 28 | 48 | 11 |  |  | 240
8230 | 2018-04-30 | 2018-11-19 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-03-14 | COMP | 2019-03-26 | COMP | Rule 16 | 142 | 42 | 25 | 1 | 13 | 9 | 227
8495 | 2018-04-30 | 2018-12-05 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-10-14 | COMP | 2019-12-16 | COMP | Rule 16 | 152 | 80 | 6 | 1 | 133 | 43 | 410
10684 | 2018-04-30 | 2019-03-26 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-28 | COMP | 2019-07-26 | COMP | 2019-10-01 | COMP | 2019-11-15 | COMP | Rule 16 | 227 | 29 | 17 | 43 | 47 | 33 | 391
10861 | 2018-04-30 | 2019-04-03 | 2019-04-29 | 2019-04-29 | COMP | 2019-08-13 | COMP | 2019-12-06 | COMP | 2019-12-10 | COMP | 2020-01-18 | COMP | Rule 16 | 233 | 19 | 75 | 80 | 3 | 27 | 432
11765 | 2018-04-30 | 2019-05-10 | 2019-09-24 | 2019-09-24 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-05-14 | COMP | 2020-05-24 | COMP | Rule 15/16 | 260 | 95 | 48 | 1 | 114 | 7 | 520
12227 | 2018-04-30 | 2019-05-28 | 2019-08-07 | 2020-12-22 | COMP | 2021-01-04 | COMP | 2021-02-10 | COMP | 2021-01-25 | COMP | 2021-05-04 | COMP | Rule 15/16 | 271 | 51 | 8 | 27 | 0 | 59 | 758
3538 | 2018-05-01 | 2018-05-14 | 2019-01-25 | 2019-01-25 | COMP | 2021-06-08 | COMP | 2021-11-24 | COMP | 2021-11-30 | COMP | 2022-01-19 | COMP | Rule 15/16 | 10 | 176 | 597 | 119 | 3 | 36 | 936
3692 | 2018-05-01 | 2018-06-08 | 2019-02-10 | 2019-02-10 | COMP | 2019-04-12 | COMP | 2019-04-18 | COMP | 2019-06-11 | COMP | 2019-07-01 | COMP | Rule 15/16 | 28 | 168 | 44 | 5 | 38 | 15 | 294
3773 | 2018-05-01 | 2018-07-09 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-10 | COMP | 2018-10-19 | COMP | 2019-06-29 | INPR | 2019-01-26 | COMP | Rule 16 | 48 | 53 | 15 | 8 |  |  | 185
5190 | 2018-05-01 | 2018-05-08 | 2018-06-09 | 2018-06-09 | COMP | 2018-06-13 | COMP | 2018-06-13 | COMP | 2019-01-11 | COMP | 2019-01-30 | COMP | Rule 16 | 6 | 23 | 3 | 1 | 146 | 13 | 188
5208 | 2018-05-01 | 2018-05-09 | 2018-09-19 | 2018-09-19 | COMP | 2018-09-17 | NOTN | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-04-17 | COMP | Other | 7 | 93 |  | 72 | 1 | 73 | 242
5391 | 2018-05-01 | 2018-05-29 | 2018-08-27 | 2018-08-27 | COMP | 2018-09-28 | COMP | 2018-09-28 | COMP | 2018-12-27 | COMP | 2019-01-24 | COMP | Rule 16 | 20 | 64 | 24 | 1 | 61 | 19 | 184
5413 | 2018-05-01 | 2018-05-29 | 2018-08-01 | 2018-08-01 | COMP | 2018-08-07 | COMP | 2018-08-07 | COMP | 2018-08-06 | COMP | 2019-01-29 | COMP | Rule 16 | 20 | 46 | 5 | 1 | 0 | 119 | 187
5682 | 2018-05-01 | 2018-06-26 | 2018-10-03 | 2018-10-03 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-09-01 | INPR | 2019-05-08 | COMP | Rule 16 | 40 | 70 | 144 | 1 |  |  | 257
5732 | 2018-05-01 | 2018-06-27 | 2018-10-24 | 2018-10-24 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-05-03 | COMP | 2019-07-09 | COMP | Rule 16 | 41 | 84 | 158 | 1 | 0 | 19 | 299
5757 | 2018-05-01 | 2018-06-30 | 2018-10-08 | 2019-02-06 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-04-04 | COMP | 2019-05-24 | COMP | Rule 16 | 43 | 69 | 46 | 1 | 0 | 32 | 269
5777 | 2018-05-01 | 2018-07-03 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2019-03-08 | COMP | 2019-03-15 | COMP | Rule 15/16 | 45 | 65 | 17 | 1 | 90 | 6 | 219
5900 | 2018-05-01 | 2018-07-10 | 2018-09-10 | 2018-09-10 | COMP | 2018-10-03 | COMP | 2018-10-03 | COMP | 2018-12-20 | COMP | 2019-02-08 | COMP | Rule 16 | 49 | 44 | 18 | 1 | 54 | 34 | 195
5933 | 2018-05-01 | 2018-07-12 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-01 | COMP | 2018-11-02 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | Rule 16 | 51 | 64 | 17 | 2 | 91 | 1 | 221
6178 | 2018-05-01 | 2018-08-01 | 2019-05-11 | 2019-05-11 | COMP | 2019-08-02 | COMP | 2019-11-06 | COMP | 2019-09-20 | COMP | 2019-12-28 | COMP | Rule 16 | 65 | 195 | 58 | 68 | 0 | 34 | 417
6428 | 2018-05-01 | 2018-08-17 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-16 | COMP | 2018-12-07 | COMP | 2023-05-27 | INPR | 2019-04-09 | COMP | Rule 15/16 | 77 | 33 | 10 | 36 |  |  | 236
6495 | 2018-05-01 | 2018-08-22 | 2018-10-19 | 2018-10-19 | COMP | 2019-01-04 | COMP | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-03-19 | COMP | Rule 16 | 80 | 42 | 51 | 19 | 2 | 32 | 221
6738 | 2018-05-01 | 2018-09-10 | 2018-09-24 | 2019-07-06 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-12 | COMP | 2019-09-23 | COMP | Rule 16 | 92 | 11 | 25 | 1 | 2 | 30 | 352
7300 | 2018-05-01 | 2018-10-06 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-13 | COMP | 2019-06-27 | COMP | 2019-06-04 | COMP | 2019-12-17 | COMP | Rule 16 | 111 | 74 | 33 | 76 | 0 | 119 | 410
7332 | 2018-05-01 | 2018-10-08 | 2018-10-27 | 2018-12-21 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-01-02 | COMP | 2019-02-12 | COMP | Rule 16 | 112 | 15 | 8 | 1 | 0 | 28 | 197
7334 | 2018-05-01 | 2018-10-08 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-01-02 | COMP | 2019-02-11 | COMP | Rule 16 | 112 | 28 | 27 | 1 | 5 | 28 | 196
8128 | 2018-05-01 | 2018-11-16 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-10 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-07-23 | COMP | Rule 15/16 | 140 | 173 | 32 | 125 | 1 | 96 | 562
8366 | 2018-05-01 | 2018-11-28 | 2019-04-03 | 2019-04-11 | COMP | 2020-02-12 | COMP | 2020-03-09 | COMP | 2020-04-20 | COMP | 2020-10-19 | COMP | Rule 15/16 | 146 | 87 | 211 | 18 | 31 | 129 | 623
8699 | 2018-05-01 | 2018-12-18 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-04 | COMP | 2019-02-05 | COMP | 2019-04-10 | COMP | 2019-05-08 | COMP | Rule 16 | 160 | 24 | 9 | 2 | 46 | 21 | 257
8717 | 2018-05-01 | 2018-12-19 | 2019-03-27 | 2020-08-28 | COMP | 2020-09-08 | COMP | 2020-09-09 | COMP | 2020-10-26 | COMP | 2020-12-04 | COMP | Rule 16 | 161 | 67 | 7 | 2 | 34 | 27 | 654
17181 | 2018-05-01 | 2020-02-04 | 2020-04-04 | 2020-04-24 | COMP | 2020-05-27 | COMP |  | REQD |  | REQD | 2022-03-09 | COMP | Rule 15/16 | 442 | 43 | 23 |  |  |  | 970
3532 | 2018-05-02 | 2018-05-12 | 2019-04-23 | 2019-04-23 | COMP | 2019-04-19 | NOTN | 2019-04-23 | COMP | 2019-04-22 | COMP | 2019-06-17 | COMP | Rule 16 | 8 | 237 |  | 1 | 0 | 39 | 283
3547 | 2018-05-02 | 2018-05-14 | 2018-12-04 | 2019-10-09 | COMP | 2019-10-16 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-24 | COMP | Rule 16 | 9 | 141 | 6 | 3 | 1 | 5 | 374
3549 | 2018-05-02 | 2018-05-14 | 2019-04-19 | 2019-04-19 | COMP | 2019-10-16 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-24 | COMP | Rule 16 | 9 | 235 | 126 | 3 | 1 | 5 | 374
3550 | 2018-05-02 | 2018-05-14 | 2019-04-26 | 2019-04-26 | COMP | 2019-10-16 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-24 | COMP | Rule 16 | 9 | 240 | 121 | 3 | 1 | 5 | 374
3557 | 2018-05-02 | 2018-05-14 | 2019-07-05 | 2019-10-09 | COMP | 2019-10-16 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-24 | COMP | Other | 9 | 288 | 6 | 3 | 1 | 5 | 374
3585 | 2018-05-02 | 2018-05-21 | 2018-08-02 | 2018-08-02 | COMP | 2018-10-29 | COMP | 2023-02-25 | REQD | 2023-02-25 | REQD | 2019-07-11 | COMP | Rule 16 | 14 | 52 | 62 |  |  |  | 300
3619 | 2018-05-02 | 2018-05-24 | 2018-09-18 | 2019-01-22 | COMP | 2019-03-11 | COMP | 2019-04-01 | COMP | 2019-04-02 | COMP | 2019-05-14 | COMP | Rule 16 | 17 | 81 | 34 | 16 | 2 | 31 | 260
3849 | 2018-05-02 | 2018-08-16 | 2018-09-08 | 2018-09-08 | COMP | 2019-03-13 | COMP | 2019-03-14 | COMP | 2019-04-03 | COMP | 2019-05-02 | COMP | Rule 15/16 | 75 | 16 | 126 | 2 | 15 | 22 | 252
5338 | 2018-05-02 | 2018-05-22 | 2018-11-03 | 2018-11-03 | COMP | 2018-12-12 | COMP | 2019-08-06 | COMP | 2019-07-30 | COMP | 2019-09-14 | COMP | Rule 15/16 | 15 | 116 | 25 | 164 | 0 | 28 | 345
5343 | 2018-05-02 | 2018-05-23 | 2018-09-21 | 2018-09-21 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-03-11 | COMP | 2019-03-25 | COMP | Other | 16 | 85 | 74 | 1 | 42 | 11 | 224
5410 | 2018-05-02 | 2018-05-29 | 2018-09-28 | 2018-09-28 | COMP | 2018-10-23 | COMP | 2018-11-05 | COMP | 2019-08-01 | COMP | 2019-09-06 | COMP | Rule 16 | 19 | 87 | 18 | 10 | 185 | 26 | 340
5414 | 2018-05-02 | 2018-05-30 | 2018-09-27 | 2018-09-27 | COMP | 2018-10-03 | COMP | 2019-02-21 | COMP | 2019-02-22 | COMP | 2019-03-07 | COMP | Rule 16 | 20 | 85 | 5 | 95 | 2 | 10 | 212
5433 | 2018-05-02 | 2018-05-30 | 2018-11-09 | 2018-11-09 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-01-04 | COMP | 2019-04-05 | COMP | Rule 16 | 20 | 116 | 33 | 1 | 4 | 64 | 233
5451 | 2018-05-02 | 2018-05-31 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-31 | COMP | 2019-11-14 | COMP | 2019-11-15 | COMP | 2020-02-26 | COMP | Rule 16 | 21 | 95 | 53 | 222 | 2 | 68 | 456
5642 | 2018-05-02 | 2018-06-22 | 2018-09-11 | 2019-01-17 | COMP | 2019-02-01 | NOTN | 2019-02-06 | COMP | 2018-06-26 | NOTN | 2019-03-22 | COMP | Other | 37 | 56 |  | 14 |  |  | 223
6334 | 2018-05-02 | 2018-08-11 | 2018-09-26 | 2018-10-05 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2018-12-15 | COMP | 2019-01-16 | COMP | Rule 16 | 71 | 32 | 43 | 1 | 6 | 21 | 178
6925 | 2018-05-02 | 2018-09-18 | 2019-03-06 | 2019-03-13 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-06-18 | COMP | 2019-06-29 | COMP | Rule 16 | 97 | 115 | 22 | 1 | 48 | 9 | 292
7039 | 2018-05-02 | 2018-09-24 | 2019-01-03 | 2019-01-03 | COMP | 2018-12-28 | NOTN | 2019-04-02 | COMP | 2019-01-25 | COMP | 2019-04-30 | COMP | Other | 101 | 69 |  | 62 | 0 | 21 | 250
7743 | 2018-05-02 | 2018-10-29 | 2018-12-20 | 2019-03-11 | COMP | 2019-03-19 | COMP | 2019-05-03 | COMP | 2019-06-18 | COMP | 2019-07-01 | COMP | Rule 16 | 126 | 36 | 7 | 34 | 32 | 10 | 293
7789 | 2018-05-02 | 2018-11-01 | 2019-04-27 | 2019-04-27 | COMP | 2019-06-27 | COMP | 2019-09-12 | COMP | 2020-05-11 | COMP | 2019-12-13 | COMP | Rule 16 | 129 | 120 | 43 | 54 | 166 |  | 407
9520 | 2018-05-02 | 2019-02-06 | 2019-05-21 | 2019-05-21 | COMP | 2019-05-24 | COMP | 2019-10-22 | COMP | 2019-10-24 | COMP | 2019-11-27 | COMP | Rule 16 | 192 | 74 | 4 | 105 | 3 | 24 | 397
9935 | 2018-05-02 | 2019-02-22 | 2019-07-29 | 2020-01-15 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-05-24 | COMP | 2020-09-22 | COMP | Rule 16 | 203 | 110 | 12 | 1 | 80 | 85 | 603
10489 | 2018-05-02 | 2019-03-18 | 2019-08-06 | 2019-08-06 | COMP | 2019-10-02 | COMP | 2019-12-26 | COMP | 2020-06-10 | COMP | 2020-07-09 | COMP | Rule 16 | 219 | 100 | 41 | 58 | 116 | 22 | 551
13582 | 2018-05-02 | 2019-07-31 | 2019-11-21 | 2019-11-21 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2022-04-28 | COMP | 2022-05-31 | COMP | Rule 16 | 314 | 80 | 25 | 1 | 589 | 23 | 1027
3540 | 2018-05-03 | 2018-05-14 | 2018-05-29 | 2018-05-29 | COMP | 2018-06-28 | COMP | 2018-06-28 | COMP | 2019-01-28 | COMP | 2019-02-19 | COMP | Rule 15/16 | 8 | 11 | 23 | 1 | 145 | 16 | 199
3705 | 2018-05-03 | 2018-06-13 | 2019-02-13 | 2019-02-13 | COMP | 2020-01-23 | COMP | 2020-05-20 | COMP | 2020-12-03 | COMP | 2021-01-08 | COMP | Rule 16 | 29 | 168 | 237 | 84 | 137 | 25 | 675
3721 | 2018-05-03 | 2018-06-18 | 2019-01-15 | 2019-01-15 | COMP | 2019-05-09 | COMP | 2019-05-15 | COMP | 2023-04-29 | INPR | 2020-07-01 | COMP | Rule 15/16 | 32 | 145 | 81 | 5 |  |  | 544
3728 | 2018-05-03 | 2018-06-19 | 2018-10-24 | 2018-10-24 | COMP | 2019-05-13 | COMP | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-07-18 | COMP | Rule 15/16 | 33 | 90 | 137 | 32 | 4 | 13 | 304
5310 | 2018-05-03 | 2018-05-22 | 2018-10-11 | 2018-10-11 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2018-10-18 | COMP | 2020-01-06 | COMP | Rule 15/16 | 14 | 100 | 25 | 1 | 0 | 284 | 420
5330 | 2018-05-03 | 2018-05-23 | 2018-09-10 | 2018-11-05 | COMP | 2018-11-28 | COMP | 2019-02-04 | COMP | 2018-11-30 | COMP | 2019-02-26 | COMP | Rule 16 | 15 | 76 | 15 | 46 | 0 | 16 | 204
5389 | 2018-05-03 | 2018-05-25 | 2018-10-10 | 2018-10-10 | COMP | 2018-12-03 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-01-18 | COMP | Rule 16 | 17 | 96 | 36 | 2 | 1 | 32 | 179
5507 | 2018-05-03 | 2018-06-05 | 2018-11-27 | 2018-11-27 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2020-10-24 | INPR | 2019-09-24 | COMP | Rule 15/16 | 23 | 121 | 9 | 1 |  |  | 351
6073 | 2018-05-03 | 2018-07-23 | 2018-09-10 | 2018-09-10 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-01-23 | COMP | Other | 56 | 35 | 56 | 1 | 1 | 37 | 181
6134 | 2018-05-03 | 2018-07-30 | 2019-01-17 | 2019-01-17 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2022-04-04 | COMP | 2022-06-01 | COMP | Rule 16 | 61 | 118 | 27 | 1 | 783 | 42 | 1027
6217 | 2018-05-03 | 2018-08-04 | 2018-10-10 | 2019-12-26 | COMP | 2020-01-29 | COMP | 2020-02-21 | COMP | 2020-11-03 | COMP | 2020-12-02 | COMP | Rule 16 | 65 | 47 | 23 | 17 | 181 | 19 | 650
6457 | 2018-05-03 | 2018-08-20 | 2018-11-04 | 2018-11-04 | COMP | 2018-11-08 | COMP | 2018-11-08 | COMP | 2019-04-30 | COMP | 2019-06-04 | COMP | Rule 16 | 76 | 54 | 4 | 1 | 117 | 25 | 273
6987 | 2018-05-03 | 2018-09-20 | 2019-01-10 | 2019-03-22 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2021-06-21 | COMP | 2022-01-24 | COMP | Rule 16 | 98 | 76 | 27 | 1 | 541 | 150 | 937
7048 | 2018-05-03 | 2018-09-24 | 2019-01-03 | 2019-01-03 | COMP | 2018-12-28 | NOTN | 2019-01-03 | COMP | 2019-01-25 | COMP | 2019-04-17 | COMP | Other | 100 | 69 |  | 1 | 16 | 58 | 240
7373 | 2018-05-03 | 2018-10-09 | 2019-01-25 | 2020-10-21 | COMP | 2020-11-10 | COMP | 2020-11-09 | COMP | 2020-09-28 | COMP | 2020-12-22 | COMP | Rule 15/16 | 111 | 73 | 15 |  | 0 | 29 | 664
7843 | 2018-05-03 | 2018-11-02 | 2019-02-15 | 2019-03-14 | COMP | 2019-03-20 | COMP | 2019-03-21 | COMP | 2019-10-21 | INPR | 2019-04-11 | COMP | Rule 16 | 129 | 70 | 5 | 2 |  |  | 236
8113 | 2018-05-03 | 2018-11-15 | 2019-04-24 | 2019-04-24 | COMP | 2019-06-04 | COMP | 2019-06-20 | COMP | 2019-07-24 | COMP | 2019-08-29 | COMP | Rule 15/16 | 137 | 109 | 29 | 13 | 24 | 27 | 334
8308 | 2018-05-03 | 2018-11-26 | 2019-02-23 | 2020-04-11 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-02-03 | COMP | 2020-06-23 | COMP | Rule 15/16 | 142 | 61 | 40 | 1 | 0 | 12 | 538
8705 | 2018-05-03 | 2018-12-19 | 2019-01-28 | 2019-01-28 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2020-07-13 | COMP | 2020-09-04 | COMP | Rule 16 | 159 | 26 | 180 | 1 | 190 | 40 | 591
8880 | 2018-05-03 | 2019-01-03 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-03-25 | COMP | 2019-04-24 | COMP | Rule 16 | 168 | 28 | 8 | 1 | 22 | 23 | 245
8976 | 2018-05-03 | 2019-01-10 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-21 | COMP | 2019-04-30 | COMP | 2019-05-01 | COMP | 2019-05-22 | COMP | Rule 16 | 173 | 38 | 12 | 29 | 2 | 16 | 265
9762 | 2018-05-03 | 2019-02-13 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-04-24 | COMP | 2019-05-13 | COMP | Rule 16 | 196 | 37 | 8 | 1 | 6 | 14 | 258
15341 | 2018-05-03 | 2019-10-26 | 2020-06-13 | 2020-06-13 | COMP | 2020-06-25 | COMP | 2020-11-06 | COMP | 2020-10-30 | COMP | 2021-01-29 | COMP | Rule 16 | 374 | 157 | 9 | 96 | 0 | 55 | 689
17566 | 2018-05-03 | 2020-02-20 | 2020-06-08 | 2020-06-08 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-09-15 | COMP | 2020-11-06 | COMP | Rule 15/16 | 451 | 77 | 45 | 1 | 27 | 39 | 635
3496 | 2018-05-04 | 2018-05-07 | 2018-07-13 | 2018-07-13 | COMP | 2019-03-19 | COMP | 2019-08-30 | COMP | 2019-09-01 | COMP | 2019-10-08 | COMP | Rule 16 | 2 | 48 | 170 | 117 | 1 | 26 | 360
5168 | 2018-05-04 | 2018-05-07 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-10 | COMP | 2019-10-08 | COMP | 2020-01-17 | COMP | 2020-02-27 | COMP | Rule 15/16 | 2 | 142 | 9 | 210 | 69 | 28 | 455
5392 | 2018-05-04 | 2018-05-29 | 2019-01-02 | 2019-01-02 | COMP | 2019-02-19 | COMP | 2019-03-19 | COMP | 2019-03-20 | COMP | 2019-07-17 | COMP | Rule 16 | 17 | 150 | 33 | 21 | 2 | 84 | 302
5393 | 2018-05-04 | 2018-05-29 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-05 | COMP | 2018-11-27 | COMP | 2018-10-30 | COMP | 2019-01-11 | COMP | Rule 16 | 17 | 93 | 21 | 14 | 0 | 32 | 173
5482 | 2018-05-04 | 2018-06-05 | 2018-10-12 | 2018-10-12 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2020-07-14 | COMP | 2020-08-11 | COMP | Rule 16 | 22 | 92 | 172 | 1 | 269 | 21 | 572
5515 | 2018-05-04 | 2018-06-06 | 2018-08-28 | 2018-08-28 | COMP | 2019-03-01 | COMP | 2019-03-20 | COMP | 2019-03-01 | COMP | 2019-06-05 | COMP | Rule 16 | 23 | 59 | 126 | 14 | 0 | 55 | 273
5630 | 2018-05-04 | 2018-06-21 | 2018-07-23 | 2018-07-23 | COMP | 2018-12-13 | COMP | 2018-12-14 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | Rule 16 | 34 | 22 | 100 | 2 | 36 | 1 | 190
5659 | 2018-05-04 | 2018-06-25 | 2018-09-27 | 2018-09-27 | COMP | 2019-02-22 | COMP | 2018-12-07 | COMP | 2019-10-10 | COMP | 2019-11-15 | COMP | Rule 16 | 36 | 67 | 100 |  | 213 | 26 | 387
5660 | 2018-05-04 | 2018-06-25 | 2018-10-22 | 2018-10-22 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-10-10 | COMP | 2019-12-03 | COMP | Rule 16 | 36 | 84 | 83 | 1 | 162 | 36 | 397
5800 | 2018-05-04 | 2018-07-03 | 2018-10-17 | 2021-04-23 | COMP | 2021-04-30 | COMP | 2021-04-30 | COMP | 2021-07-13 | COMP | 2021-08-27 | COMP | Rule 16 | 42 | 75 | 6 | 1 | 51 | 34 | 835
6008 | 2018-05-04 | 2018-07-18 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2019-03-18 | COMP | 2019-04-17 | COMP | Rule 16 | 52 | 65 | 26 | 1 | 77 | 23 | 239
6009 | 2018-05-04 | 2018-07-18 | 2019-01-05 | 2019-01-05 | COMP | 2019-03-05 | COMP | 2019-05-07 | COMP | 2019-04-15 | COMP | 2019-05-30 | COMP | Rule 16 | 52 | 117 | 40 | 46 | 0 | 17 | 269
6024 | 2018-05-04 | 2018-07-20 | 2018-12-03 | 2018-12-19 | COMP | 2019-01-07 | COMP | 2019-01-07 | COMP | 2019-01-31 | COMP | 2019-02-19 | COMP | Rule 16 | 54 | 93 | 12 | 1 | 18 | 13 | 198
6027 | 2018-05-04 | 2018-07-18 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-06-19 | COMP | 2019-07-23 | COMP | Rule 16 | 52 | 65 | 32 | 1 | 137 | 24 | 306
6338 | 2018-05-04 | 2018-08-14 | 2019-03-13 | 2021-09-21 | COMP | 2021-10-13 | COMP | 2021-10-13 | COMP | 2021-10-18 | COMP | 2022-02-07 | COMP | Rule 15/16 | 71 | 144 | 17 | 1 | 4 | 77 | 946
6350 | 2018-05-04 | 2018-08-13 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2020-12-07 | COMP | 2020-11-09 | COMP | Rule 16 | 70 | 131 | 23 | 1 | 431 |  | 635
6452 | 2018-05-04 | 2018-08-20 | 2018-12-14 | 2018-12-14 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-10-21 | INPR | 2019-03-06 | COMP | Rule 16 | 75 | 81 | 9 | 1 |  |  | 209
7910 | 2018-05-04 | 2018-11-05 | 2019-03-12 | 2019-11-22 | COMP | 2020-02-10 | COMP | 2020-08-07 | COMP | 2020-06-18 | COMP | 2020-10-07 | COMP | Rule 15/16 | 129 | 85 | 52 | 128 | 0 | 43 | 612
9089 | 2018-05-04 | 2019-01-16 | 2019-03-04 | 2019-03-04 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-07-16 | COMP | 2019-08-27 | COMP | Rule 16 | 176 | 32 | 63 | 1 | 33 | 31 | 331
10548 | 2018-05-04 | 2019-03-20 | 2019-10-11 | 2019-10-11 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-10-29 | COMP | 2019-12-20 | COMP | Rule 16 | 219 | 145 | 33 | 1 | 0 | 16 | 410
12833 | 2018-05-04 | 2019-06-26 | 2019-07-10 | 2019-08-21 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2020-04-22 | COMP | 2020-05-12 | COMP | Rule 16 | 288 | 10 | 46 | 1 | 123 | 15 | 508
15168 | 2018-05-04 | 2019-10-16 | 2020-04-06 | 2020-04-06 | COMP | 2020-05-18 | COMP | 2020-09-25 | COMP | 2021-07-02 | COMP | 2021-07-21 | COMP | Rule 15/16 | 366 | 117 | 31 | 93 | 193 | 13 | 808
15446 | 2018-05-04 | 2019-11-02 | 2020-03-16 | 2020-03-16 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2021-06-22 | COMP | 2021-07-19 | COMP | Rule 16 | 378 | 89 | 115 | 1 | 208 | 19 | 806
15796 | 2018-05-04 | 2019-11-20 | 2020-01-04 | 2020-01-04 | COMP | 2020-01-13 | COMP | 2020-01-24 | INPR | 2020-01-16 | COMP | 2020-01-14 | COMP | Rule 16 | 390 | 29 | 6 |  |  |  | 425
3574 | 2018-05-07 | 2018-05-17 | 2018-12-30 | 2018-12-30 | COMP | 2019-03-13 | COMP | 2019-07-09 | COMP | 2019-07-29 | COMP | 2019-08-14 | COMP | Rule 15/16 | 9 | 155 | 50 | 83 | 15 | 13 | 321
5334 | 2018-05-07 | 2018-05-22 | 2019-01-12 | 2019-01-12 | COMP | 2019-07-08 | COMP | 2019-10-23 | COMP | 2019-11-14 | COMP | 2019-12-06 | COMP | Rule 16 | 12 | 161 | 122 | 77 | 16 | 15 | 399
5506 | 2018-05-07 | 2018-06-05 | 2018-08-19 | 2018-08-19 | COMP | 2018-09-14 | COMP | 2018-09-17 | COMP | 2019-04-21 | INPR | 2019-01-25 | COMP | Rule 15/16 | 21 | 53 | 19 | 2 |  |  | 181
5638 | 2018-05-07 | 2018-06-21 | 2018-08-27 | 2018-08-27 | COMP | 2018-09-21 | COMP | 2018-10-30 | COMP | 2018-11-21 | COMP | 2019-01-04 | COMP | Rule 16 | 33 | 47 | 19 | 28 | 16 | 29 | 167
5673 | 2018-05-07 | 2018-06-25 | 2018-10-29 | 2018-10-29 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2019-10-21 | INPR | 2019-06-26 | COMP | Rule 16 | 35 | 89 | 107 | 1 |  |  | 287
5752 | 2018-05-07 | 2018-06-29 | 2018-09-20 | 2018-09-20 | COMP | 2018-11-08 | COMP | 2018-11-08 | COMP | 2018-12-19 | COMP | 2019-01-16 | COMP | Rule 15/16 | 39 | 58 | 36 | 1 | 27 | 19 | 175
5791 | 2018-05-07 | 2018-07-03 | 2019-04-01 | 2019-04-22 | COMP | 2019-08-12 | COMP | 2019-09-05 | COMP | 2020-06-30 | COMP | 2021-01-12 | COMP | Rule 16 | 41 | 186 | 79 | 18 | 206 | 135 | 675
5856 | 2018-05-07 | 2018-07-09 | 2018-09-19 | 2018-09-19 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-04-12 | COMP | 2019-04-25 | COMP | Rule 16 | 44 | 52 | 122 | 1 | 20 | 10 | 244
6031 | 2018-05-07 | 2018-07-19 | 2018-09-04 | 2018-09-04 | COMP | 2018-09-26 | COMP | 2018-09-26 | COMP | 2018-12-19 | COMP | 2019-01-25 | COMP | Rule 15/16 | 52 | 33 | 17 | 1 | 58 | 25 | 181
6132 | 2018-05-07 | 2018-07-28 | 2019-02-01 | 2019-02-01 | COMP | 2019-04-22 | COMP | 2019-07-12 | COMP | 2020-01-27 | COMP | 2020-01-28 | COMP | Rule 16 | 58 | 128 | 56 | 58 | 135 | 2 | 433
6209 | 2018-05-07 | 2018-08-03 | 2018-12-04 | 2018-12-04 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-01-18 | COMP | 2019-03-14 | COMP | Rule 16 | 63 | 84 | 41 | 1 | 0 | 29 | 214
6246 | 2018-05-07 | 2018-08-06 | 2018-10-01 |  | REQD | 2022-10-11 | COMP |  | REQD |  | REQD | 2019-06-03 | COMP | Unknown | 64 | [5 empty] | 270
6259 | 2018-05-07 | 2018-08-07 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-31 | COMP | 2019-06-26 | COMP | 2019-09-10 | COMP | 2019-10-01 | COMP | Rule 16 | 65 | 48 | 53 | 124 | 53 | 16 | 354
6305 | 2018-05-07 | 2018-08-09 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-01 | COMP | 2019-03-04 | COMP | Rule 15/16 | 67 | 119 | 8 | 1 | 0 | 15 | 206
6617 | 2018-05-07 | 2018-08-30 | 2018-09-11 | 2018-09-11 | COMP | 2018-12-11 | COMP | 2019-01-24 | COMP | 2019-04-21 | INPR | 2019-01-29 | COMP | Rule 16 | 82 | 8 | 63 | 30 |  |  | 183
6627 | 2018-05-07 | 2018-08-31 | 2018-10-05 | 2018-11-20 | COMP | 2018-11-28 | COMP | 2018-12-12 | COMP | 2018-11-21 | COMP | 2019-01-08 | COMP | Rule 16 | 83 | 25 | 5 | 11 | 0 | 18 | 169
7284 | 2018-05-07 | 2018-10-05 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-03 | COMP | 2018-12-13 | COMP | 2018-12-12 | COMP | 2019-01-11 | COMP | Rule 16 | 107 | 28 | 12 | 9 | 0 | 20 | 172
7513 | 2018-05-07 | 2018-10-18 | 2019-01-10 | 2020-05-15 | COMP | 2020-03-18 | COMP | 2020-05-15 | COMP | 2020-05-14 | COMP | 2020-10-14 | COMP | Rule 15/16 | 116 | 56 |  | 43 | 0 | 107 | 616
7927 | 2018-05-07 | 2018-11-05 | 2019-03-04 | 2019-09-30 | COMP | 2019-10-03 | COMP | 2019-04-10 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | Rule 16 | 128 | 79 | 4 |  | 138 | 19 | 388
8030 | 2018-05-07 | 2018-11-10 | 2018-12-31 | 2018-12-31 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | 2019-06-05 | COMP | Rule 16 | 132 | 32 | 62 | 1 | 1 | 48 | 272
8360 | 2018-05-07 | 2018-11-28 | 2018-12-19 | 2019-03-25 | COMP | 2019-04-29 | COMP | 2019-06-18 | COMP | 2019-06-04 | COMP | 2019-07-03 | COMP | Rule 16 | 142 | 16 | 26 | 36 | 0 | 12 | 292
9053 | 2018-05-07 | 2019-01-14 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-16 | COMP | 2019-09-06 | COMP | 2021-02-27 | INPR | 2019-12-30 | COMP | Rule 15/16 | 173 | 59 | 29 | 79 |  |  | 414
10803 | 2018-05-07 | 2019-03-29 | 2019-05-29 | 2020-03-01 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-04-27 | COMP | 2020-05-22 | COMP | Rule 16 | 225 | 43 | 28 | 1 | 14 | 20 | 515
11032 | 2018-05-07 | 2019-04-09 | 2019-08-11 | 2019-08-11 | COMP | 2019-08-19 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-11-22 | COMP | Rule 16 | 232 | 87 | 6 | 30 | 1 | 39 | 391
12100 | 2018-05-07 | 2019-05-23 | 2019-05-30 | 2019-05-30 | COMP | 2019-09-04 | COMP | 2019-09-04 | NOTN | 2022-04-16 | INPR | 2021-04-06 | COMP | Rule 16 | 264 | 5 | 68 |  |  |  | 733
3522 | 2018-05-08 | 2018-05-10 | 2019-01-08 | 2019-01-08 | COMP | 2018-11-14 | NOTN | 2019-01-08 | COMP | 2019-01-05 | COMP | 2019-02-11 | COMP | Rule 16 | 3 | 166 |  | 1 | 0 | 24 | 191
3536 | 2018-05-08 | 2018-05-14 | 2018-08-04 | 2018-08-04 | COMP | 2018-10-18 | COMP | 2018-11-05 | COMP | 2019-06-13 | COMP | 2019-07-13 | COMP | Rule 16 | 5 | 58 | 53 | 13 | 151 | 21 | 297
3870 | 2018-05-08 | 2018-08-30 | 2018-09-23 | 2018-09-23 | COMP | 2018-12-11 | COMP | 2019-01-16 | COMP | 2019-07-21 | INPR | 2019-04-07 | COMP | Rule 16 | 81 | 16 | 54 | 25 |  |  | 229
5351 | 2018-05-08 | 2018-05-23 | 2018-09-10 | 2018-09-10 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-01-03 | COMP | 2019-02-06 | COMP | Rule 16 | 12 | 76 | 70 | 1 | 10 | 24 | 188
5459 | 2018-05-08 | 2018-06-01 | 2018-10-10 | 2018-10-10 | COMP | 2018-10-19 | COMP | 2019-01-08 | COMP | 2019-04-21 | INPR | 2019-01-31 | COMP | Rule 16 | 18 | 92 | 8 | 53 |  |  | 184
5502 | 2018-05-08 | 2018-06-05 | 2018-10-29 | 2018-10-29 | COMP | 2018-12-28 | COMP | 2019-02-19 | COMP | 2019-01-27 | COMP | 2019-04-04 | COMP | Rule 16 | 20 | 103 | 41 | 35 | 0 | 33 | 228
5547 | 2018-05-08 | 2018-06-12 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-01 | COMP | 2019-04-26 | COMP | 2021-02-27 | INPR | 2019-10-04 | COMP | Rule 16 | 25 | 176 | 5 | 41 |  |  | 356
5620 | 2018-05-08 | 2018-06-21 | 2020-08-25 | 2020-08-25 | COMP | 2020-11-12 | COMP | 2021-07-30 | COMP | 2022-01-11 | COMP | 2022-02-03 | COMP | Rule 16 | 32 | 549 | 56 | 179 | 114 | 17 | 942
5624 | 2018-05-08 | 2018-06-20 | 2018-10-05 | 2018-10-05 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-05-16 | COMP | 2019-06-27 | COMP | Rule 16 | 31 | 76 | 20 | 1 | 134 | 30 | 287
5687 | 2018-05-08 | 2018-06-25 | 2018-12-21 | 2018-12-21 | COMP | 2019-01-28 | COMP | 2019-04-09 | COMP | 2019-04-01 | COMP | 2019-05-11 | COMP | Rule 15/16 | 34 | 125 | 24 | 51 | 0 | 24 | 254
5703 | 2018-05-08 | 2018-06-26 | 2018-11-17 | 2018-11-17 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-04-26 | INPR | 2020-01-07 | COMP | Rule 15/16 | 35 | 101 | 266 | 1 |  |  | 418
5704 | 2018-05-08 | 2018-06-26 | 2018-11-17 | 2018-11-17 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2021-01-30 | INPR | 2020-01-07 | COMP | Rule 15/16 | 35 | 101 | 266 | 1 |  |  | 418
5723 | 2018-05-08 | 2018-06-27 | 2019-01-08 | 2019-01-08 | COMP | 2019-02-15 | COMP | 2019-04-30 | COMP | 2019-03-07 | COMP | 2019-11-04 | COMP | Rule 15/16 | 36 | 133 | 28 | 52 | 0 | 132 | 377
5746 | 2018-05-08 | 2018-06-28 | 2018-07-27 | 2018-07-27 | COMP | 2018-10-16 | COMP | 2018-10-16 | COMP | 2019-10-21 | INPR | 2019-03-23 | COMP | Rule 16 | 37 | 21 | 57 | 1 |  |  | 219
5898 | 2018-05-08 | 2018-07-10 | 2019-06-28 | 2019-06-28 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP |  | INPR | 2021-04-14 | COMP | Rule 15/16 | 44 | 245 | 139 | 1 |  |  | 738
5934 | 2018-05-08 | 2018-07-12 | 2018-10-19 | 2018-10-19 | COMP | 2018-12-06 | COMP | 2019-01-02 | COMP | 2019-04-01 | COMP | 2019-05-16 | COMP | Rule 16 | 46 | 71 | 32 | 18 | 62 | 34 | 258
5945 | 2018-05-08 | 2018-07-13 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2019-07-09 | COMP | 2019-08-08 | COMP | Rule 15/16 | 47 | 65 | 22 | 1 | 163 | 23 | 316
5953 | 2018-05-08 | 2018-07-16 | 2019-02-04 | 2019-02-04 | COMP | 2019-05-21 | COMP | 2019-10-30 | COMP | 2020-06-17 | COMP | 2020-09-10 | COMP | Rule 16 | 48 | 139 | 76 | 114 | 158 | 61 | 591
5984 | 2018-05-08 | 2018-07-17 | 2018-08-23 | 2018-08-23 | COMP | 2018-09-27 | COMP | 2019-03-19 | COMP | 2019-04-17 | COMP | 2019-04-24 | COMP | Rule 16 | 49 | 28 | 25 | 117 | 22 | 6 | 242
6745 | 2018-05-08 | 2018-09-10 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-05-31 | COMP | 2019-04-30 | COMP | Rule 16 | 87 | 113 | 18 | 1 | 53 |  | 246
6767 | 2018-05-08 | 2018-09-11 | 2018-11-14 | 2018-11-16 | COMP | 2019-01-23 | COMP | 2020-04-25 | COMP | 2020-05-12 | COMP | 2020-06-22 | COMP | Rule 15/16 | 88 | 46 | 44 | 317 | 12 | 29 | 534
6906 | 2018-05-08 | 2018-09-16 | 2019-01-14 | 2019-04-02 | COMP | 2019-04-22 | COMP | 2019-04-23 | COMP | 2019-05-01 | COMP | 2019-06-05 | COMP | Rule 16 | 91 | 81 | 15 | 2 | 7 | 25 | 271
6954 | 2018-05-08 | 2018-09-19 | 2018-12-07 | 2018-12-07 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-03-26 | COMP | 2019-06-07 | COMP | Rule 16 | 94 | 55 | 43 | 1 | 32 | 53 | 273
7052 | 2018-05-08 | 2018-09-24 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-30 | COMP | 2019-06-24 | COMP | 2019-07-06 | COMP | 2019-07-18 | COMP | Rule 16 | 97 | 159 | 13 | 18 | 9 | 9 | 301
7165 | 2018-05-08 | 2018-10-01 | 2019-01-18 | 2019-04-13 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-04-24 | COMP | 2019-07-10 | COMP | Rule 15/16 | 102 | 75 | 25 | 1 | 0 | 37 | 295
8114 | 2018-05-08 | 2018-11-15 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-13 | COMP | 2019-03-25 | COMP | 2019-05-07 | COMP | 2019-05-13 | COMP | Rule 16 | 134 | 75 | 5 | 9 | 32 | 5 | 255
8179 | 2018-05-08 | 2018-11-18 | 2019-02-13 | 2019-05-22 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-09 | COMP | 2019-07-31 | COMP | Rule 16 | 135 | 58 | 32 | 1 | 2 | 17 | 310
8202 | 2018-05-08 | 2018-11-17 | 2019-02-26 | 2019-02-26 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-07-31 | COMP | Rule 16 | 135 | 66 | 106 | 1 | 1 | 5 | 310
8370 | 2018-05-08 | 2018-11-28 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-06 | COMP | 2019-03-14 | COMP | 2019-03-27 | COMP | 2019-04-26 | COMP | Rule 16 | 141 | 49 | 19 | 7 | 10 | 23 | 244
8522 | 2018-05-08 | 2018-12-06 | 2019-04-03 | 2019-04-03 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-27 | COMP | 2019-09-23 | COMP | Rule 16 | 147 | 81 | 77 | 1 | 27 | 19 | 347
9126 | 2018-05-08 | 2019-01-17 | 2019-04-17 | 2019-04-22 | COMP | 2019-04-29 | COMP | 2019-06-27 | INPR | 2019-06-27 | COMP | 2019-08-03 | COMP | Rule 15/16 | 175 | 63 | 6 |  |  |  | 312
9508 | 2018-05-08 | 2019-02-06 | 2019-05-24 | 2019-05-24 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-07-18 | COMP | 2019-12-13 | COMP | Rule 15/16 | 188 | 77 | 113 | 1 | 0 | 28 | 403
10215 | 2018-05-08 | 2019-03-06 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-21 | COMP | 2019-09-12 | COMP | 2023-05-27 | INPR | 2019-11-08 | COMP | Rule 16 | 207 | 91 | 29 | 16 |  |  | 381
11058 | 2018-05-08 | 2019-04-10 | 2019-08-01 | 2019-08-09 | COMP | 2019-08-16 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-12-23 | COMP | Rule 15/16 | 232 | 80 | 6 | 57 | 1 | 32 | 409
15218 | 2018-05-08 | 2019-10-21 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-06 | COMP | 2020-01-17 | COMP | 2021-03-28 | INPR | 2020-02-03 | COMP | Rule 16 | 367 | 2 | 12 | 48 |  |  | 436
3518 | 2018-05-09 | 2018-05-09 | 2018-06-13 | 2018-06-13 | COMP | 2018-08-14 | COMP | 2018-08-14 | INPR |  | REQD | 2019-08-05 | COMP | Other | 1 | 25 | 44 |  |  |  | 312
3580 | 2018-05-09 | 2018-05-18 | 2018-07-19 | 2018-07-19 | COMP | 2018-12-04 | COMP | 2019-02-11 | COMP | 2019-01-15 | COMP | 2019-03-14 | COMP | Rule 15/16 | 8 | 43 | 95 | 47 | 0 | 23 | 212
3639 | 2018-05-09 | 2018-05-31 | 2018-06-12 | 2018-06-12 | COMP | 2018-09-20 | COMP | 2018-10-12 | COMP | 2019-03-09 | COMP | 2019-03-25 | COMP | Rule 16 | 16 | 9 | 71 | 17 | 99 | 11 | 219
3653 | 2018-05-09 | 2018-06-04 | 2018-09-11 | 2018-09-11 | COMP | 2018-09-24 | COMP | 2018-09-28 | COMP | 2018-11-01 | COMP | 2019-03-12 | COMP | Rule 16 | 18 | 70 | 10 | 5 | 25 | 87 | 210
3658 | 2018-05-09 | 2018-06-05 | 2019-03-13 | 2020-01-09 | COMP | 2019-05-24 | COMP | 2020-02-12 | COMP | 2020-01-10 | COMP | 2020-03-11 | COMP | Rule 15/16 | 19 | 193 |  | 180 | 0 | 20 | 461
3738 | 2018-05-09 | 2018-06-23 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-22 | COMP | 2019-04-16 | INPR | 2019-02-23 | COMP | 2019-06-13 | COMP | Rule 16 | 32 | 151 | 16 |  |  |  | 276
3769 | 2018-05-09 | 2018-07-06 | 2018-09-11 | 2018-09-11 | COMP | 2018-10-31 | COMP | 2018-11-09 | COMP | 2018-11-21 | COMP | 2019-02-24 | COMP | Rule 16 | 41 | 47 | 37 | 8 | 8 | 62 | 198
3793 | 2018-05-09 | 2018-07-14 | 2018-10-25 | 2018-10-25 | COMP | 2018-12-24 | COMP | 2019-02-02 | COMP |  | INPR | 2020-04-29 | COMP | Rule 16 | 46 | 73 | 40 | 27 |  |  | 496
4050 | 2018-05-09 | 2018-12-30 | 2018-12-31 | 2018-12-31 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2018-12-31 | COMP | 2019-02-08 | COMP | Rule 16 | 161 | 1 | 3 | 1 | 0 | 26 | 189
4127 | 2018-05-09 | 2019-03-19 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-25 | COMP | 2019-12-18 | COMP | 2020-01-17 | COMP | 2020-03-09 | COMP | Rule 15/16 | 215 | 10 | 19 | 164 | 21 | 35 | 459
5311 | 2018-05-09 | 2018-05-21 | 2019-01-17 | 2019-01-17 | COMP | 2019-05-08 | COMP | 2019-07-11 | COMP | 2019-10-01 | COMP | 2019-11-06 | COMP | Rule 16 | 9 | 166 | 78 | 45 | 58 | 27 | 378
5498 | 2018-05-09 | 2018-06-04 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-06 | COMP | 2019-05-22 | COMP | 2019-05-21 | COMP | 2019-08-08 | COMP | Rule 16 | 18 | 91 | 20 | 135 | 0 | 55 | 315
5504 | 2018-05-09 | 2018-06-05 | 2018-10-01 | 2018-10-01 | COMP | 2018-12-18 | COMP | 2020-10-20 | COMP | 2020-11-04 | COMP | 2020-12-09 | COMP | Rule 16 | 19 | 83 | 54 | 465 | 12 | 23 | 651
5505 | 2018-05-09 | 2018-06-05 | 2018-10-10 | 2018-10-10 | COMP | 2018-12-18 | COMP | 2019-01-17 | COMP | 2020-11-04 | COMP | 2020-12-10 | COMP | Rule 16 | 19 | 90 | 47 | 21 | 456 | 24 | 652
5740 | 2018-05-09 | 2018-06-29 | 2018-09-05 | 2018-09-05 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-08-26 | COMP | 2019-10-02 | COMP | Rule 16 | 37 | 47 | 110 | 1 | 136 | 27 | 353
5804 | 2018-05-09 | 2018-07-06 | 2018-09-21 | 2018-09-21 | COMP | 2018-11-01 | COMP | 2018-11-02 | NOTN | 2019-10-21 | INPR | 2019-01-19 | COMP | Rule 16 | 41 | 55 | 30 |  |  |  | 175
5972 | 2018-05-09 | 2018-07-17 | 2018-11-10 | 2018-12-18 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-03-22 | COMP | 2019-04-03 | COMP | Rule 15/16 | 48 | 83 | 7 | 1 | 59 | 9 | 226
6065 | 2018-05-09 | 2018-07-23 | 2018-09-17 | 2018-09-17 | COMP | 2018-11-28 | COMP | 2019-07-15 | COMP | 2019-07-18 | COMP | 2019-08-24 | COMP | Rule 16 | 52 | 40 | 50 | 158 | 4 | 27 | 326
6177 | 2018-05-09 | 2018-08-01 | 2018-12-12 | 2018-12-12 | COMP | 2019-04-16 | COMP | 2019-04-24 | COMP | 2019-10-21 | INPR | 2019-06-21 | COMP | Rule 15/16 | 59 | 92 | 86 | 7 |  |  | 282
6186 | 2018-05-09 | 2018-08-02 | 2018-09-28 | 2018-09-28 | COMP | 2018-10-25 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2019-11-13 | COMP | Rule 15/16 | 60 | 41 | 20 | 237 | 1 | 28 | 382
6194 | 2018-05-09 | 2018-08-03 | 2018-10-09 | 2018-10-09 | COMP | 2018-10-30 | COMP | 2018-12-20 | COMP | 2018-12-19 | COMP | 2019-01-09 | COMP | Rule 16 | 61 | 47 | 16 | 35 | 0 | 13 | 168
6216 | 2018-05-09 | 2018-08-03 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-03-25 | COMP | 2019-08-21 | COMP | Rule 16 | 61 | 58 | 24 | 1 | 79 | 106 | 324
7229 | 2018-05-09 | 2018-10-03 | 2019-03-04 | 2019-03-28 | COMP | 2019-04-05 | COMP | 2019-06-12 | COMP | 2019-07-26 | COMP | 2019-08-19 | COMP | Rule 15/16 | 103 | 102 | 7 | 48 | 32 | 17 | 322
7376 | 2018-05-09 | 2018-10-10 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-03 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2019-11-18 | COMP | Rule 16 | 108 | 97 | 23 | 129 | 1 | 32 | 385
7524 | 2018-05-09 | 2018-10-18 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-03-21 | COMP | 2019-07-10 | COMP | Rule 16 | 114 | 42 | 30 | 1 | 34 | 78 | 294
8432 | 2018-05-09 | 2018-12-01 | 2019-02-22 | 2019-02-22 | COMP | 2019-05-21 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2019-11-22 | COMP | Rule 15/16 | 142 | 56 | 63 | 113 | 1 | 18 | 389
8577 | 2018-05-09 | 2018-12-11 | 2019-06-12 | 2019-06-12 | COMP | 2020-06-03 | COMP | 2020-08-03 | COMP | 2020-08-04 | COMP | 2020-08-28 | COMP | Rule 16 | 149 | 127 | 246 | 44 | 2 | 19 | 582
8856 | 2018-05-09 | 2019-01-03 | 2019-05-16 | 2019-05-16 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2021-02-27 | INPR | 2020-02-03 | COMP | Rule 16 | 164 | 94 | 36 | 1 |  |  | 435
9074 | 2018-05-09 | 2019-01-15 | 2019-03-07 | 2019-03-07 | COMP | 2019-04-01 | COMP | 2019-04-04 | COMP | 2019-09-22 | INPR | 2019-05-28 | COMP | Rule 16 | 172 | 36 | 18 | 4 |  |  | 264
9167 | 2018-05-09 | 2019-01-18 | 2019-06-04 | 2019-06-04 | COMP | 2019-08-20 | COMP | 2020-03-25 | COMP | 2020-05-11 | COMP | 2020-05-22 | COMP | Rule 16 | 175 | 95 | 55 | 149 | 34 | 10 | 513
9504 | 2018-05-09 | 2019-02-06 | 2019-05-30 | 2019-08-16 | COMP | 2019-09-12 | COMP | 2019-09-16 | INPR | 2019-10-21 | COMP | 2019-11-17 | COMP | Rule 16 | 187 | 80 | 19 |  |  |  | 384
9515 | 2018-05-09 | 2019-02-06 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-07-25 | COMP | Rule 15/16 | 187 | 69 | 30 | 1 | 1 | 22 | 305
12342 | 2018-05-09 | 2019-06-01 | 2019-08-07 | 2019-08-07 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2021-03-27 | INPR | 2020-02-19 | COMP | Rule 16 | 267 | 47 | 113 | 1 |  |  | 446
18733 | 2018-05-09 | 2020-04-07 | 2020-08-11 | 2020-08-11 | COMP | 2020-08-21 | COMP | 2021-01-27 | COMP | 2021-01-21 | COMP | 2021-04-06 | COMP | Rule 16 | 480 | 90 | 9 | 107 | 0 | 49 | 731
3537 | 2018-05-10 | 2018-05-14 | 2018-07-01 | 2018-07-01 | COMP | 2018-07-18 | COMP | 2018-07-19 | COMP | 2019-05-01 | COMP | 2020-06-09 | COMP | Rule 16 | 3 | 34 | 12 | 2 | 197 | 279 | 523
5206 | 2018-05-10 | 2018-05-10 | 2018-08-21 | 2018-08-21 | COMP | 2018-08-18 | NOTN | 2018-08-21 | COMP | 2018-10-15 | COMP | 2019-03-12 | COMP | Other | 1 | 72 |  | 1 | 39 | 100 | 209
5997 | 2018-05-10 | 2018-07-18 | 2018-11-19 | 2018-11-19 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-05-03 | COMP | 2019-07-10 | COMP | Rule 15/16 | 48 | 87 | 22 | 1 | 93 | 47 | 293
6060 | 2018-05-10 | 2018-07-23 | 2018-08-27 | 2018-08-27 | COMP | 2018-10-31 | COMP | 2018-11-01 | COMP | 2018-11-21 | COMP | 2019-01-11 | COMP | Rule 16 | 51 | 26 | 47 | 2 | 14 | 34 | 169
6235 | 2018-05-10 | 2018-08-06 | 2019-02-26 | 2019-02-26 | COMP | 2019-05-20 | COMP | 2020-06-12 | COMP | 2020-11-03 | COMP | 2020-11-12 | COMP | Rule 15/16 | 61 | 139 | 60 | 269 | 102 | 7 | 633
6373 | 2018-05-10 | 2018-08-14 | 2019-05-13 | 2019-05-13 | COMP | 2020-07-24 | COMP | 2020-08-10 | COMP | 2020-08-23 | COMP | 2020-09-24 | COMP | Rule 16 | 67 | 187 | 304 | 12 | 10 | 23 | 599
6481 | 2018-05-10 | 2018-08-21 | 2018-10-15 | 2018-11-08 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2020-03-11 | COMP | 2020-03-23 | COMP | Rule 16 | 72 | 39 | 89 | 1 | 245 | 9 | 468
6513 | 2018-05-10 | 2018-08-23 | 2018-10-11 | 2018-10-23 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2018-12-04 | COMP | 2019-02-01 | COMP | Rule 16 | 74 | 35 | 27 | 1 | 2 | 41 | 183
6564 | 2018-05-10 | 2018-08-27 | 2019-10-24 | 2019-10-24 | COMP | 2020-04-14 | COMP | 2020-01-28 | COMP | 2020-01-31 | COMP | 2020-03-06 | COMP | Rule 15/16 | 76 | 293 | 117 |  | 4 | 25 | 457
6606 | 2018-05-10 | 2018-08-29 | 2019-01-14 | 2019-05-03 | COMP | 2019-07-01 | COMP | 2020-12-31 | COMP | 2021-01-05 | COMP | 2021-01-15 | COMP | Rule 15/16 | 78 | 93 | 41 | 379 | 3 | 9 | 675
6715 | 2018-05-10 | 2018-09-11 | 2018-09-17 | 2018-09-17 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-11-24 | INPR | 2019-08-13 | COMP | Rule 16 | 86 | 5 | 185 | 1 |  |  | 317
6763 | 2018-05-10 | 2018-09-11 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-04-24 | COMP | 2019-05-13 | COMP | Rule 16 | 86 | 82 | 25 | 1 | 50 | 14 | 253
7029 | 2018-05-10 | 2018-09-23 | 2019-07-25 | 2019-07-25 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2020-11-21 | INPR | 2019-11-16 | COMP | Rule 16 | 94 | 210 | 46 | 1 |  |  | 383
7470 | 2018-05-10 | 2018-10-15 | 2018-12-15 | 2018-12-15 | COMP | 2019-01-07 | COMP | 2019-08-09 | COMP | 2019-06-06 | COMP | 2020-01-03 | COMP | Rule 16 | 110 | 42 | 14 | 151 | 0 | 100 | 414
7645 | 2018-05-10 | 2018-10-24 | 2019-01-19 | 2019-01-19 | COMP | 2019-02-06 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-13 | COMP | Rule 15/16 | 117 | 58 | 12 | 19 | 1 | 7 | 210
7803 | 2018-05-10 | 2018-11-01 | 2019-10-06 | 2019-12-31 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-07-12 | COMP | 2021-05-26 | COMP | Rule 15/16 | 123 | 232 | 127 | 1 | 9 | 220 | 766
8205 | 2018-05-10 | 2018-11-17 | 2019-01-05 | 2019-01-05 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-04-24 | COMP | 2019-05-07 | COMP | Rule 15/16 | 133 | 31 | 49 | 1 | 28 | 10 | 249
9316 | 2018-05-10 | 2019-01-30 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-01 | COMP | 2019-05-01 | NOTN | 2019-04-26 | COMP | 2019-06-14 | COMP | Rule 16 | 181 | 61 | 5 |  |  |  | 276
9944 | 2018-05-10 | 2019-02-23 | 2019-04-24 | 2019-04-24 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-11-21 | COMP | 2019-12-05 | COMP | Rule 16 | 197 | 43 | 107 | 1 | 42 | 9 | 395
10278 | 2018-05-10 | 2019-03-08 | 2019-04-26 | 2019-07-12 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2019-08-27 | COMP | 2019-09-24 | COMP | Rule 16 | 207 | 36 | 26 | 1 | 8 | 20 | 346
10511 | 2018-05-10 | 2019-03-19 | 2019-04-13 | 2020-03-13 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-07-30 | COMP | 2020-10-19 | COMP | Rule 16 | 214 | 19 | 18 | 1 | 82 | 57 | 616
14265 | 2018-05-10 | 2019-09-03 | 2019-11-15 | 2020-04-27 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-07-08 | COMP | 2020-08-06 | COMP | Rule 15/16 | 331 | 53 | 12 | 1 | 41 | 22 | 565
14427 | 2018-05-10 | 2019-09-09 | 2019-11-07 | 2020-01-07 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2021-08-26 | COMP | 2021-10-09 | COMP | Rule 16 | 335 | 44 | 89 | 1 | 327 | 31 | 860
14998 | 2018-05-10 | 2019-10-10 | 2019-11-07 | 2020-10-19 | COMP | 2021-03-05 | COMP | 2021-03-05 | COMP |  | INPR | 2023-10-14 | COMP | Rule 15/16 | 358 | 21 | 93 | 1 |  |  | 1365
16473 | 2018-05-10 | 2020-01-02 | 2020-05-21 | 2020-06-17 | COMP | 2020-09-01 | COMP | 2020-10-29 | COMP | 2020-11-03 | COMP | 2020-12-02 | COMP | Rule 15/16 | 413 | 99 | 55 | 42 | 4 | 19 | 645
40243 | 2018-05-10 | 2022-12-14 | 2023-05-09 | 2023-05-09 | COMP | 2023-05-19 | NOTN | 2023-08-16 | COMP | 2023-09-19 | COMP | 2023-08-30 | COMP | Other | 1156 | 101 |  | 69 | 24 |  | 1334
3604 | 2018-05-11 | 2018-05-23 | 2018-07-18 | 2018-07-18 | COMP | 2018-08-06 | COMP | 2018-08-06 | COMP | 2018-10-23 | COMP | 2019-02-06 | COMP | Rule 16 | 9 | 39 | 14 | 1 | 56 | 71 | 185
3727 | 2018-05-11 | 2018-06-19 | 2018-09-28 | 2018-09-28 | COMP | 2018-11-06 | COMP | 2018-11-09 | COMP | 2019-11-06 | COMP | 2020-02-04 | COMP | Rule 16 | 27 | 72 | 28 | 4 | 249 | 59 | 434
3759 | 2018-05-11 | 2018-06-28 | 2018-09-11 | 2018-09-11 | COMP | 2018-10-17 | COMP | 2018-10-30 | COMP | 2019-06-14 | COMP | 2019-07-08 | COMP | Rule 16 | 34 | 52 | 27 | 10 | 156 | 16 | 290
3822 | 2018-05-11 | 2018-07-30 | 2018-10-08 | 2018-10-08 | COMP | 2019-06-25 | COMP | 2019-07-08 | COMP | 2019-09-27 | COMP | 2020-02-29 | COMP | Rule 15/16 | 55 | 50 | 179 | 9 | 59 | 104 | 451
5401 | 2018-05-11 | 2018-05-29 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-17 | COMP | 2018-10-17 | COMP | 2018-10-29 | COMP | 2019-01-25 | COMP | Other | 12 | 80 | 21 | 1 | 9 | 59 | 177
5452 | 2018-05-11 | 2018-05-31 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-06 | NOTN | 2019-04-12 | COMP | 2019-03-06 | COMP | 2019-06-27 | COMP | Other | 14 | 191 |  | 28 | 0 | 54 | 284
5562 | 2018-05-11 | 2018-06-15 | 2018-10-08 | 2018-10-08 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-10-28 | COMP | 2019-11-19 | COMP | Rule 16 | 25 | 80 | 106 | 1 | 161 | 16 | 384
5569 | 2018-05-11 | 2018-06-14 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-03 | COMP | 2018-10-03 | COMP | 2019-03-21 | COMP | 2019-07-12 | COMP | Rule 16 | 24 | 68 | 11 | 1 | 115 | 80 | 294
5756 | 2018-05-11 | 2018-06-29 | 2018-08-01 | 2018-08-01 | COMP | 2018-09-07 | COMP | 2018-09-07 | COMP | 2019-07-30 | COMP | 2019-08-01 | COMP | Rule 16 | 35 | 23 | 27 | 1 | 224 | 3 | 308
5792 | 2018-05-11 | 2018-07-03 | 2018-09-28 | 2018-12-12 | COMP | 2018-11-27 | NOTN | 2018-12-12 | COMP | 2019-01-25 | COMP | 2019-04-15 | COMP | Other | 37 | 62 |  | 1 | 30 | 56 | 232
5829 | 2018-05-11 | 2018-07-07 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-28 | COMP | 2019-02-28 | COMP | 2019-12-28 | INPR | 2019-09-06 | COMP | Rule 16 | 39 | 72 | 49 | 42 |  |  | 333
5896 | 2018-05-11 | 2018-07-10 | 2018-08-21 | 2018-08-21 | COMP | 2018-09-14 | COMP | 2018-09-17 | COMP | 2019-09-01 | INPR | 2019-05-01 | COMP | Rule 16 | 41 | 31 | 18 | 2 |  |  | 244
6131 | 2018-05-11 | 2018-07-28 | 2018-12-07 | 2018-12-07 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-04-29 | COMP | 2019-07-03 | COMP | Rule 16 | 54 | 91 | 46 | 1 | 53 | 47 | 288
6211 | 2018-05-11 | 2018-08-03 | 2018-09-28 | 2018-09-28 | COMP | 2019-01-04 | COMP | 2019-01-30 | COMP | 2019-01-22 | COMP | 2019-04-10 | COMP | Rule 16 | 59 | 40 | 66 | 18 | 0 | 50 | 229
6340 | 2018-05-11 | 2018-08-13 | 2018-12-04 | 2019-01-31 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-09-24 | COMP | 2019-12-27 | COMP | Rule 16 | 65 | 78 | 18 | 1 | 148 | 65 | 409
6351 | 2018-05-11 | 2018-08-13 | 2018-10-02 | 2018-10-02 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-06-18 | COMP | 2019-07-30 | COMP | Rule 16 | 65 | 36 | 148 | 1 | 31 | 30 | 306
6645 | 2018-05-11 | 2018-09-04 | 2019-02-21 | 2019-02-26 | COMP | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-08-29 | COMP | 2019-08-19 | COMP | Rule 16 | 80 | 116 | 19 | 1 | 113 |  | 320
6990 | 2018-05-11 | 2018-09-20 | 2019-04-05 | 2019-08-31 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-12-14 | COMP | 2021-01-08 | COMP | Rule 15/16 | 92 | 135 | 239 | 1 | 85 | 18 | 669
7041 | 2018-05-11 | 2018-09-24 | 2019-01-02 | 2019-01-02 | COMP | 2018-12-18 | NOTN | 2019-01-02 | COMP | 2019-01-25 | COMP | 2019-03-11 | COMP | Other | 94 | 68 |  | 1 | 17 | 31 | 207
7658 | 2018-05-11 | 2018-10-24 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-21 | COMP | 2019-04-02 | NOTN | 2019-03-21 | COMP | 2019-04-18 | COMP | Rule 16 | 116 | 54 | 27 |  |  |  | 235
7768 | 2018-05-11 | 2018-10-30 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-31 | COMP | 2019-07-31 | COMP | 2019-07-05 | COMP | 2019-08-08 | COMP | Rule 16 | 120 | 137 | 10 | 43 | 0 | 7 | 313
8436 | 2018-05-11 | 2018-12-01 | 2019-02-10 | 2019-03-01 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-09-30 | COMP | 2019-10-16 | COMP | Rule 15/16 | 140 | 47 | 132 | 1 | 18 | 13 | 361
9156 | 2018-05-11 | 2019-01-18 | 2019-05-07 | 2020-08-26 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2022-03-19 | INPR | 2021-02-05 | COMP | Rule 15/16 | 173 | 76 | 91 | 1 |  |  | 688
9439 | 2018-05-11 | 2019-02-04 | 2019-04-22 | 2019-04-22 | COMP | 2019-06-21 | COMP | 2019-09-16 | COMP | 2019-09-21 | COMP | 2020-01-31 | COMP | Rule 16 | 183 | 55 | 44 | 60 | 5 | 89 | 432
9770 | 2018-05-11 | 2019-02-14 | 2019-09-10 | 2019-09-10 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-11-10 | COMP | 2021-05-13 | COMP | Rule 16 | 191 | 145 | 157 | 1 | 141 | 126 | 756
10961 | 2018-05-11 | 2019-04-06 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-22 | COMP | 2019-08-07 | COMP | 2020-06-08 | COMP | 2020-07-10 | COMP | Rule 16 | 226 | 10 | 23 | 54 | 210 | 25 | 545
6005 | 2018-05-12 | 2018-07-18 | 2018-09-26 | 2019-03-08 | COMP | 2019-05-03 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-05-29 | COMP | Rule 16 | 46 | 50 | 41 | 7 | 1 | 12 | 262
5571 | 2018-05-13 | 2018-06-14 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-07-21 | INPR | 2019-02-01 | COMP | Rule 16 | 23 | 115 | 14 | 1 |  |  | 181
6538 | 2018-05-13 | 2018-08-27 | 2019-03-25 | 2019-03-25 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2020-02-29 | INPR | 2019-11-04 | COMP | Rule 16 | 74 | 143 | 127 | 1 |  |  | 373
3617 | 2018-05-14 | 2018-05-25 | 2018-07-31 | 2018-07-31 | COMP | 2018-12-28 | COMP | 2019-01-08 | COMP | 2019-02-06 | COMP | 2019-03-04 | COMP | Rule 15/16 | 10 | 46 | 104 | 7 | 21 | 18 | 201
3626 | 2018-05-14 | 2018-05-25 | 2018-07-16 | 2018-07-16 | COMP | 2018-12-27 | COMP | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-03-07 | COMP | Rule 15/16 | 10 | 35 | 114 | 23 | 7 | 20 | 204
3627 | 2018-05-14 | 2018-05-25 | 2018-07-16 | 2018-07-16 | COMP | 2018-12-27 | COMP | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-03-08 | COMP | Rule 15/16 | 10 | 35 | 114 | 23 | 7 | 21 | 205
3631 | 2018-05-14 | 2018-05-29 | 2018-12-30 | 2018-12-30 | COMP | 2019-01-31 | COMP | 2019-08-06 | COMP | 2019-08-05 | COMP | 2019-09-04 | COMP | Rule 15/16 | 11 | 148 | 22 | 131 | 0 | 21 | 330
3687 | 2018-05-14 | 2018-06-07 | 2018-09-06 | 2018-09-06 | COMP | 2019-10-15 | COMP | 2019-11-22 | COMP | 2020-11-02 | COMP | 2020-02-26 | COMP | Rule 15/16 | 18 | 64 | 279 | 28 | 239 |  | 448
3785 | 2018-05-14 | 2018-07-12 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-22 | COMP | 2019-03-28 | COMP | 2019-04-18 | COMP | 2019-06-04 | COMP | Rule 15/16 | 42 | 162 | 13 | 5 | 16 | 33 | 266
3823 | 2018-05-14 | 2018-07-30 | 2018-11-06 | 2018-11-06 | COMP | 2019-09-27 | COMP | 2019-10-01 | COMP | 2019-10-01 | COMP | 2020-02-29 | COMP | Rule 15/16 | 54 | 71 | 224 | 3 | 1 | 102 | 450
5480 | 2018-05-14 | 2018-06-05 | 2018-11-01 | 2018-12-13 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-02-24 | COMP | 2019-05-13 | COMP | Rule 16 | 16 | 106 | 72 | 1 | 0 | 33 | 251
5716 | 2018-05-14 | 2018-06-26 | 2018-07-19 | 2018-07-19 | COMP | 2018-08-31 | COMP | 2018-08-31 | COMP | 2019-01-14 | COMP | 2019-02-22 | COMP | Rule 16 | 31 | 17 | 32 | 1 | 91 | 28 | 195
6133 | 2018-05-14 | 2018-07-30 | 2018-08-06 | 2019-07-30 | COMP | 2019-08-28 | COMP | 2018-09-21 | INPR | 2022-06-18 | REQD | 2021-05-24 | COMP | Rule 16 | 54 | 6 | 22 |  |  |  | 762
6277 | 2018-05-14 | 2018-08-07 | 2018-11-05 | 2018-11-05 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2021-02-27 | INPR | 2019-07-26 | COMP | Rule 16 | 60 | 64 | 84 | 1 |  |  | 303
6775 | 2018-05-14 | 2018-09-11 | 2019-02-25 | 2019-04-29 | COMP | 2019-06-21 | COMP | 2019-10-01 | COMP | 2019-08-29 | COMP | 2019-12-06 | COMP | Rule 15/16 | 84 | 113 | 39 | 71 | 0 | 46 | 394
7089 | 2018-05-14 | 2018-09-26 | 2018-11-01 | 2018-11-01 | COMP | 2018-12-12 | COMP | 2018-11-08 | COMP | 2020-03-10 | COMP | 2020-03-18 | COMP | Rule 16 | 95 | 27 | 27 |  | 332 | 7 | 463
7820 | 2018-05-14 | 2018-11-02 | 2019-07-30 | 2019-07-30 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-10-01 | COMP | 2021-02-16 | COMP | Rule 15/16 | 122 | 184 | 153 | 1 | 146 | 92 | 693
7824 | 2018-05-14 | 2018-11-01 | 2019-01-01 | 2019-01-01 | COMP | 2019-02-08 | COMP | 2019-02-11 | COMP | 2020-01-10 | COMP | 2020-02-12 | COMP | Rule 16 | 121 | 39 | 27 | 2 | 231 | 23 | 439
9219 | 2018-05-14 | 2019-01-22 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-22 | COMP | 2019-04-25 | NOTN | 2019-05-03 | COMP | 2019-08-06 | COMP | Rule 16 | 173 | 47 | 18 |  |  |  | 310
10146 | 2018-05-14 | 2019-03-05 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-22 | COMP | 2019-05-13 | NOTN | 2019-05-24 | COMP | 2019-06-05 | COMP | Rule 16 | 202 | 39 | 19 |  |  |  | 267
12204 | 2018-05-14 | 2019-05-28 | 2019-10-27 | 2019-10-27 | COMP | 2020-01-17 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-08-24 | COMP | Rule 16 | 261 | 107 | 55 | 140 | 1 | 15 | 575
12488 | 2018-05-14 | 2019-06-10 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2020-03-14 | COMP | 2020-06-12 | COMP | Rule 16 | 270 | 62 | 7 | 1 | 124 | 64 | 524
23002 | 2018-05-14 | 2020-10-20 | 2020-12-22 | 2020-12-22 | COMP | 2020-12-23 | NOTN | 2021-02-04 | COMP | 2020-12-23 | COMP | 2021-03-16 | COMP | Other | 615 | 43 |  | 30 | 0 | 28 | 713
23029 | 2018-05-14 | 2020-10-20 | 2021-02-02 | 2021-02-02 | COMP | 2021-02-03 | NOTN | 2021-02-19 | COMP | 2021-02-03 | COMP | 2021-04-01 | COMP | Other | 615 | 70 |  | 13 | 0 | 30 | 725
3707 | 2018-05-15 | 2018-06-14 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-17 | COMP | 2019-01-12 | COMP | 2020-04-06 | COMP | 2020-04-07 | COMP | Rule 15/16 | 22 | 85 | 44 | 18 | 309 | 2 | 476
3708 | 2018-05-15 | 2018-06-15 | 2018-07-12 | 2018-07-12 | COMP | 2018-08-14 | COMP | 2018-09-26 | COMP | 2019-05-19 | COMP | 2019-03-11 | COMP | Rule 15/16 | 23 | 19 | 24 | 31 | 161 |  | 205
3781 | 2018-05-15 | 2018-07-11 | 2019-06-22 | 2019-06-22 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2019-06-25 | COMP | 2019-08-26 | COMP | Rule 16 | 40 | 239 | 9 | 1 | 0 | 37 | 323
3836 | 2018-05-15 | 2018-08-08 | 2018-08-29 | 2018-08-29 | COMP | 2018-08-29 | NOTN | 2018-08-29 | COMP | 2018-12-06 | NOTN | 2019-04-25 | COMP | Other | 60 | 16 |  | 1 |  |  | 238
5259 | 2018-05-15 | 2018-05-15 | 2018-05-22 | 2018-05-22 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2020-09-22 | COMP | 2021-01-05 | COMP | Rule 16 | 1 | 6 | 154 | 1 | 436 | 71 | 664
5271 | 2018-05-15 | 2018-05-15 | 2018-08-04 | 2018-08-04 | COMP | 2018-11-19 | COMP | 2018-11-19 | INPR | 2020-02-29 | REQD | 2019-11-14 | COMP | Rule 16 | 1 | 57 | 74 |  |  |  | 379
5368 | 2018-05-15 | 2018-05-24 | 2018-06-02 | 2018-06-11 | COMP | 2018-06-18 | COMP | 2018-06-18 | COMP | 2019-03-27 | COMP | 2019-04-23 | COMP | Rule 16 | 8 | 6 | 6 | 1 | 194 | 20 | 236
5426 | 2018-05-15 | 2018-05-30 | 2018-09-03 | 2018-09-15 | COMP | 2018-10-05 | COMP | 2018-10-16 | COMP | 2019-01-08 | COMP | 2019-01-29 | COMP | Rule 16 | 11 | 67 | 15 | 8 | 56 | 15 | 177
5501 | 2018-05-15 | 2018-06-05 | 2018-09-07 | 2018-09-07 | COMP | 2018-10-02 | COMP | 2018-12-06 | COMP | 2018-11-26 | COMP | 2020-08-10 | COMP | Rule 16 | 15 | 67 | 18 | 45 | 0 | 423 | 564
5545 | 2018-05-15 | 2018-06-14 | 2018-10-28 | 2018-10-28 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-01-22 | COMP | 2019-04-10 | COMP | Rule 16 | 22 | 95 | 23 | 1 | 34 | 56 | 227
5572 | 2018-05-15 | 2018-06-14 | 2018-11-05 | 2019-01-04 | COMP | 2019-03-04 | COMP | 2019-07-24 | COMP | 2019-04-30 | COMP | 2019-08-20 | COMP | Rule 16 | 22 | 101 | 40 | 101 | 0 | 20 | 319
5622 | 2018-05-15 | 2018-06-20 | 2018-06-26 | 2018-06-26 | COMP | 2018-07-18 | COMP | 2018-07-18 | COMP | 2018-05-14 | COMP | 2021-04-24 | COMP | Rule 16 | 26 | 5 | 16 | 1 | 0 | 696 | 740
5669 | 2018-05-15 | 2018-06-25 | 2018-11-02 | 2018-11-02 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2020-07-11 | INPR | 2019-04-15 | COMP | Rule 16 | 29 | 93 | 40 | 1 |  |  | 230
5694 | 2018-05-15 | 2018-06-25 | 2019-01-28 | 2019-01-28 | COMP | 2019-11-24 | COMP | 2019-06-11 | COMP | 2019-08-02 | COMP | 2019-08-13 | COMP | Rule 16 | 29 | 148 | 210 |  | 38 | 8 | 314
5848 | 2018-05-15 | 2018-07-07 | 2018-10-12 | 2018-10-12 | COMP | 2019-03-11 | COMP | 2019-03-12 | COMP | 2019-04-18 | COMP | 2019-05-23 | COMP | Rule 16 | 37 | 69 | 100 | 2 | 28 | 26 | 258
5910 | 2018-05-15 | 2018-07-10 | 2018-10-10 | 2018-10-10 | COMP | 2018-12-10 | COMP | 2019-02-11 | COMP | 2019-03-12 | COMP | 2019-07-10 | COMP | Rule 16 | 39 | 66 | 41 | 43 | 21 | 85 | 290
5935 | 2018-05-15 | 2018-07-12 | 2018-10-12 | 2018-10-12 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2020-02-26 | COMP | 2020-02-21 | COMP | Rule 16 | 41 | 66 | 100 | 1 | 243 |  | 444
6074 | 2018-05-15 | 2018-07-23 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-07-02 | COMP | 2019-08-12 | COMP | Rule 16 | 48 | 152 | 7 | 1 | 81 | 29 | 313
6236 | 2018-05-15 | 2018-08-06 | 2018-09-20 | 2018-09-20 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-10-21 | INPR | 2019-05-28 | COMP | Rule 16 | 58 | 33 | 62 | 1 |  |  | 260
6667 | 2018-05-15 | 2018-09-05 | 2018-12-11 | 2018-12-11 | COMP | 2018-12-17 | COMP | 2019-02-05 | COMP | 2019-06-10 | COMP | 2019-09-25 | COMP | Rule 16 | 79 | 67 | 5 | 34 | 88 | 76 | 344
6824 | 2018-05-15 | 2018-09-12 | 2019-01-01 | 2019-03-11 | COMP | 2019-03-14 | COMP | 2019-05-01 | COMP | 2019-03-14 | COMP | 2019-05-02 | COMP | Rule 16 | 84 | 75 | 4 | 35 | 0 | 2 | 243
6845 | 2018-05-15 | 2018-09-13 | 2019-04-22 | 2019-04-22 | COMP | 2019-06-11 | COMP | 2020-03-09 | COMP | 2020-04-16 | COMP | 2020-07-29 | COMP | Rule 15/16 | 85 | 151 | 36 | 186 | 29 | 74 | 556
6903 | 2018-05-15 | 2018-09-17 | 2018-09-20 | 2018-09-20 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-10-21 | INPR | 2019-05-28 | COMP | Rule 16 | 87 | 4 | 50 | 1 |  |  | 260
7725 | 2018-05-15 | 2018-10-26 | 2019-01-31 | 2019-04-05 | COMP | 2019-04-16 | COMP | 2019-04-29 | COMP | 2019-09-22 | INPR | 2019-06-06 | COMP | Rule 16 | 116 | 64 | 8 | 10 |  |  | 267
7797 | 2018-05-15 | 2018-10-31 | 2019-01-18 | 2019-01-18 | COMP | 2019-04-09 | COMP | 2019-04-11 | COMP | 2019-04-10 | COMP | 2019-07-25 | COMP | Rule 16 | 119 | 53 | 56 | 3 | 0 | 74 | 301
8135 | 2018-05-15 | 2018-11-16 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2020-05-20 | COMP | 2020-07-08 | COMP | Rule 16 | 130 | 90 | 32 | 1 | 258 | 35 | 541
9502 | 2018-05-15 | 2019-02-06 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-18 | COMP | 2019-05-18 | COMP | 2019-05-20 | COMP | 2019-06-28 | COMP | Rule 16 | 183 | 29 | 23 | 22 | 1 | 29 | 283
12899 | 2018-05-15 | 2019-06-27 | 2019-09-03 | 2019-09-03 | COMP | 2020-09-24 | COMP | 2020-10-16 | COMP | 2020-10-30 | COMP | 2020-12-07 | COMP | Rule 16 | 282 | 47 | 269 | 17 | 11 | 24 | 645
13975 | 2018-05-15 | 2019-08-19 | 2020-09-11 | 2020-09-11 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | 2021-01-15 | COMP | 2021-02-23 | COMP | Other | 318 | 270 | 54 | 1 | 33 | 26 | 697
3577 | 2018-05-16 | 2018-05-18 | 2018-09-24 | 2018-09-24 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-05-06 | COMP | 2019-07-19 | COMP | Other | 3 | 89 | 61 | 1 | 94 | 53 | 296
3760 | 2018-05-16 | 2018-06-29 | 2018-09-19 | 2018-09-19 | COMP |  |  |  |  | 2019-12-19 | COMP | 2020-01-07 | COMP | Rule 16 | 32 | 57 |  |  |  |  | 412
3981 | 2018-05-16 | 2018-11-05 | 2019-03-26 | 2019-03-26 | COMP | 2019-05-24 | COMP | 2019-08-05 | COMP |  |  | 2019-09-20 | COMP | Rule 15/16 | 121 | 95 | 44 | 50 |  |  | 340
5308 | 2018-05-16 | 2018-05-21 | 2018-10-01 | 2018-10-01 | COMP | 2018-08-06 | NOTN | 2018-12-07 | COMP | 2019-05-13 | COMP | 2019-06-19 | COMP | Other | 4 | 93 |  | 47 | 108 | 27 | 275
5503 | 2018-05-16 | 2018-06-05 | 2018-09-10 | 2018-09-10 | COMP | 2018-10-31 | COMP | 2018-10-31 | COMP | 2019-02-14 | COMP | 2019-03-26 | COMP | Rule 16 | 14 | 68 | 38 | 1 | 71 | 28 | 215
5523 | 2018-05-16 | 2018-06-07 | 2018-08-24 | 2018-08-24 | COMP | 2018-09-05 | COMP | 2018-09-05 | COMP | 2019-03-04 | COMP | 2019-03-12 | COMP | Rule 16 | 16 | 56 | 8 | 1 | 122 | 7 | 205
5588 | 2018-05-16 | 2018-06-15 | 2018-12-05 | 2019-02-06 | COMP | 2019-02-12 | COMP | 2019-06-20 | COMP | 2019-06-03 | COMP | 2019-07-08 | COMP | Rule 15/16 | 22 | 119 | 5 | 91 | 0 | 12 | 287
5609 | 2018-05-16 | 2018-06-19 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-01-07 | COMP | 2019-02-08 | COMP | Rule 16 | 24 | 113 | 9 | 1 | 18 | 24 | 184
5720 | 2018-05-16 | 2018-06-26 | 2018-08-06 | 2018-08-06 | COMP | 2018-08-13 | COMP | 2018-09-06 | COMP | 2019-09-11 | COMP | 2019-11-05 | COMP | Rule 16 | 29 | 29 | 6 | 18 | 255 | 40 | 372
5760 | 2018-05-16 | 2018-07-02 | 2018-07-27 | 2018-07-27 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-03-12 | COMP | 2019-04-12 | COMP | Rule 16 | 33 | 19 | 129 | 1 | 27 | 24 | 228
5763 | 2018-05-16 | 2018-07-02 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-15 | COMP | 2019-04-25 | COMP | 2019-06-05 | COMP | 2019-12-20 | COMP | Rule 16 | 33 | 78 | 19 | 110 | 29 | 138 | 402
5973 | 2018-05-16 | 2018-07-17 | 2019-02-01 | 2019-02-01 | COMP | 2019-04-03 | COMP | 2019-08-14 | COMP | 2019-09-06 | COMP | 2019-12-20 | COMP | Rule 15/16 | 43 | 137 | 43 | 94 | 17 | 73 | 402
6012 | 2018-05-16 | 2018-07-18 | 2019-03-07 | 2019-03-07 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-06-21 | COMP | 2019-08-02 | COMP | Rule 16 | 44 | 159 | 22 | 1 | 55 | 30 | 306
6070 | 2018-05-16 | 2018-07-24 | 2018-10-31 | 2018-10-31 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2018-12-07 | COMP | 2019-01-24 | COMP | Rule 16 | 48 | 71 | 40 | 1 | 0 | 17 | 173
6072 | 2018-05-16 | 2018-07-23 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-31 | COMP | 2019-07-11 | COMP | 2019-07-01 | COMP | 2019-08-02 | COMP | Rule 16 | 47 | 75 | 58 | 113 | 0 | 17 | 306
6097 | 2018-05-16 | 2018-07-25 | 2018-11-16 | 2018-11-16 | COMP | 2019-04-19 | COMP | 2019-04-19 | COMP | 2019-04-27 | COMP | 2019-06-07 | COMP | Rule 16 | 49 | 81 | 105 | 1 | 6 | 29 | 267
6129 | 2018-05-16 | 2018-07-28 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-01 | COMP | 2019-01-22 | COMP | 2018-11-09 | COMP | 2019-03-29 | COMP | Rule 16 | 51 | 64 | 4 | 53 | 0 | 48 | 218
6418 | 2018-05-16 | 2018-08-17 | 2018-09-27 | 2018-09-27 | COMP | 2018-10-09 | COMP | 2018-11-28 | COMP | 2019-02-14 | COMP | 2019-03-07 | COMP | Rule 16 | 66 | 29 | 9 | 34 | 54 | 15 | 202
6727 | 2018-05-16 | 2018-09-10 | 2018-10-02 | 2018-10-02 | COMP | 2018-12-12 | COMP | 2018-12-20 | COMP | 2019-07-02 | NOTN | 2019-07-19 | COMP | Rule 15/16 | 81 | 17 | 49 | 7 |  |  | 296
6976 | 2018-05-16 | 2018-09-20 | 2019-12-23 | 2019-12-23 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-02-18 | COMP | 2020-04-07 | COMP | Rule 15/16 | 89 | 315 | 39 | 1 | 0 | 35 | 475
7120 | 2018-05-16 | 2018-09-28 | 2018-11-16 | 2018-11-16 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-03-14 | COMP | 2019-04-06 | COMP | Rule 16 | 95 | 35 | 66 | 1 | 14 | 17 | 223
7999 | 2018-05-16 | 2018-11-09 | 2018-12-16 | 2018-12-16 | COMP | 2018-12-16 | NOTN | 2018-12-16 | COMP | 2019-05-14 | COMP | 2019-06-12 | COMP | Other | 125 | 23 |  | 0 | 103 | 21 | 270
8501 | 2018-05-16 | 2018-12-05 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-29 | COMP | 2019-06-20 | COMP | 2019-07-15 | COMP | 2019-08-01 | COMP | Rule 15/16 | 140 | 76 | 25 | 38 | 17 | 14 | 305
8939 | 2018-05-16 | 2019-01-08 | 2019-04-29 | 2019-04-29 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2020-02-21 | COMP | 2020-04-02 | COMP | Rule 16 | 162 | 78 | 54 | 2 | 151 | 30 | 472
8971 | 2018-05-16 | 2019-01-10 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-05 | COMP | 2019-03-06 | COMP | 2019-03-18 | COMP | 2019-04-16 | COMP | Rule 16 | 164 | 30 | 8 | 2 | 9 | 22 | 230
9455 | 2018-05-16 | 2019-02-05 | 2019-08-06 | 2019-08-07 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | Rule 16 | 181 | 128 | 19 | 1 | 105 | 1 | 431
9572 | 2018-05-16 | 2019-02-07 | 2019-04-13 | 2019-04-13 | COMP | 2020-03-04 | COMP | 2020-06-15 | COMP |  | INPR | 2020-06-30 | COMP | Rule 15/16 | 183 | 46 | 223 | 73 |  |  | 534
9888 | 2018-05-16 | 2019-02-21 | 2019-07-05 | 2019-07-29 | COMP | 2019-09-20 | COMP | 2021-04-27 | COMP |  |  | 2021-07-02 | COMP | Rule 16 | 192 | 95 | 39 | 402 |  |  | 788
10192 | 2018-05-16 | 2019-03-06 | 2019-05-17 | 2019-05-17 | COMP | 2019-11-20 | COMP | 2019-11-25 | COMP | 2019-12-16 | COMP | 2019-12-06 | COMP | Rule 16 | 201 | 53 | 130 | 4 | 14 |  | 392
11927 | 2018-05-16 | 2019-05-17 | 2019-08-15 | 2019-08-15 | COMP | 2020-09-25 | COMP | 2020-10-21 | COMP | 2021-01-12 | COMP | 2021-01-22 | COMP | Rule 16 | 253 | 63 | 282 | 19 | 55 | 8 | 675
40244 | 2018-05-16 | 2022-12-14 | 2023-04-18 | 2023-04-18 | COMP | 2023-04-18 | NOTN | 2023-07-21 | COMP | 2023-08-03 | COMP | 2023-11-02 | COMP | Other | 1152 | 86 |  | 66 | 10 | 65 | 1375
3695 | 2018-05-17 | 2018-06-11 | 2018-09-26 | 2018-09-26 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-04-29 | COMP | 2019-06-19 | COMP | Rule 16 | 17 | 76 | 150 | 1 | 0 | 34 | 274
3725 | 2018-05-17 | 2018-06-19 | 2018-11-17 | 2019-02-25 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-05-20 | COMP | 2019-07-27 | COMP | Rule 15/16 | 23 | 106 | 59 | 1 | 3 | 48 | 300
3746 | 2018-05-17 | 2018-06-26 | 2018-10-12 | 2018-10-12 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-08-31 | INPR | 2019-03-28 | COMP | Rule 16 | 28 | 77 | 95 | 1 |  |  | 216
4130 | 2018-05-17 | 2019-03-20 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-02 | NOTN | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-08-14 | COMP | Other | 210 | 50 |  | 25 | 1 | 31 | 313
5315 | 2018-05-17 | 2018-05-22 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-11 | COMP | 2019-02-12 | COMP | 2020-06-01 | COMP | 2020-07-21 | COMP | Rule 16 | 4 | 162 | 20 | 2 | 328 | 37 | 548
5818 | 2018-05-17 | 2018-07-05 | 2018-10-17 | 2018-10-17 | COMP | 2019-02-11 | COMP | 2019-02-13 | COMP | 2019-02-21 | COMP | 2019-03-29 | COMP | Rule 16 | 34 | 74 | 78 | 3 | 6 | 27 | 217
5824 | 2018-05-17 | 2018-07-05 | 2018-11-19 | 2018-11-19 | COMP | 2018-12-28 | COMP | 2019-01-03 | NOTN | 2018-12-28 | COMP | 2019-06-12 | COMP | Other | 34 | 96 | 27 |  |  |  | 269
6099 | 2018-05-17 | 2018-07-25 | 2018-11-08 | 2018-11-08 | COMP | 2019-02-25 | COMP | 2019-05-08 | COMP | 2019-11-05 | COMP | 2019-11-15 | COMP | Rule 15/16 | 48 | 76 | 71 | 53 | 127 | 8 | 378
6121 | 2018-05-17 | 2018-07-30 | 2018-10-19 | 2018-11-07 | COMP | 2018-11-09 | COMP | 2018-12-18 | COMP | 2019-02-11 | COMP | 2019-03-06 | COMP | Rule 16 | 51 | 59 | 3 | 25 | 37 | 17 | 200
6241 | 2018-05-17 | 2018-08-06 | 2018-09-27 | 2018-09-27 | COMP | 2019-01-10 | COMP | 2019-01-16 | COMP | 2019-06-11 | COMP | 2019-07-09 | COMP | Rule 16 | 56 | 38 | 71 | 5 | 102 | 20 | 287
6271 | 2018-05-17 | 2018-08-07 | 2018-10-03 | 2018-10-03 | COMP | 2018-11-05 | COMP | 2018-11-09 | COMP | 2019-06-12 | COMP | 2019-06-22 | COMP | Rule 16 | 57 | 41 | 24 | 5 | 146 | 8 | 276
6734 | 2018-05-17 | 2018-09-10 | 2019-01-23 | 2019-01-23 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2019-12-17 | COMP | 2020-01-31 | COMP | Rule 16 | 80 | 92 | 227 | 1 | 2 | 31 | 428
7042 | 2018-05-17 | 2018-09-24 | 2019-01-03 | 2019-01-03 | COMP | 2018-12-28 | NOTN | 2019-04-05 | COMP | 2019-01-25 | COMP | 2019-05-06 | COMP | Other | 90 | 69 |  | 65 | 0 | 22 | 243
7233 | 2018-05-17 | 2018-10-05 | 2020-12-08 | 2021-03-20 | COMP | 2021-07-16 | COMP | 2021-07-26 | COMP | 2021-09-11 | COMP | 2021-10-14 | COMP | Rule 15/16 | 99 | 546 | 83 | 7 | 34 | 24 | 859
7330 | 2018-05-17 | 2018-10-08 | 2018-11-02 | 2018-11-02 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-01-11 | COMP | 2019-01-12 | COMP | Rule 16 | 100 | 20 | 45 | 1 | 2 | 1 | 164
7502 | 2018-05-17 | 2018-10-17 | 2019-02-05 | 2019-02-25 | COMP | 2019-02-28 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-06-17 | COMP | Rule 16 | 107 | 74 | 4 | 20 | 1 | 58 | 272
7979 | 2018-05-17 | 2018-11-07 | 2019-02-01 | 2019-02-01 | COMP | 2019-05-14 | COMP | 2019-05-17 | COMP | 2019-06-11 | COMP | 2019-06-28 | COMP | Rule 16 | 122 | 57 | 72 | 4 | 17 | 14 | 281
10374 | 2018-05-17 | 2019-03-13 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-06 | COMP | 2019-09-18 | COMP | 2019-10-16 | COMP | 2019-12-12 | COMP | Rule 16 | 205 | 113 | 13 | 9 | 21 | 39 | 395
10705 | 2018-05-17 | 2019-03-27 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-14 | COMP | 2019-09-17 | COMP | 2019-10-23 | COMP | 2020-01-09 | COMP | Rule 16 | 215 | 88 | 12 | 24 | 27 | 52 | 413
11342 | 2018-05-17 | 2019-04-23 | 2019-07-25 | 2019-07-25 | COMP | 2019-10-03 | COMP | 2020-03-11 | COMP | 2020-06-03 | COMP | 2020-08-31 | COMP | Rule 16 | 234 | 66 | 50 | 108 | 60 | 64 | 577
12764 | 2018-05-17 | 2019-06-21 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2019-12-02 | COMP | 2020-01-02 | COMP | Rule 16 | 276 | 100 | 14 | 1 | 0 | 21 | 408
15324 | 2018-05-17 | 2019-10-25 | 2020-02-14 | 2020-02-14 | COMP | 2020-02-27 | COMP | 2020-09-03 | COMP | 2020-11-20 | COMP | 2021-03-23 | COMP | Rule 16 | 364 | 75 | 9 | 135 | 55 | 82 | 715
16269 | 2018-05-17 | 2019-12-18 | 2020-02-19 | 2020-02-19 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-03-20 | COMP | 2020-06-17 | COMP | Rule 16 | 399 | 42 | 5 | 1 | 19 | 63 | 524
17241 | 2018-05-17 | 2020-02-05 | 2020-03-24 | 2020-03-24 | COMP | 2021-02-17 | COMP | 2021-11-29 | COMP | 2021-11-30 | COMP | 2022-01-28 | COMP | Rule 15/16 | 431 | 34 | 228 | 198 | 2 | 43 | 931
3637 | 2018-05-18 | 2018-05-31 | 2018-09-28 | 2018-09-28 | COMP | 2019-04-05 | COMP | 2019-05-10 | COMP | 2019-04-08 | COMP | 2019-05-17 | COMP | Rule 15/16 | 9 | 85 | 129 | 26 | 0 | 6 | 251
4033 | 2018-05-18 | 2018-12-19 | 2019-02-06 | 2019-02-06 | COMP | 2020-02-03 | COMP | 2020-02-05 | COMP | 2019-01-08 | COMP | 2020-03-04 | COMP | Rule 16 | 148 | 33 | 249 | 3 | 0 | 20 | 449
5479 | 2018-05-18 | 2018-06-05 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2018-10-22 | COMP | 2019-01-04 | COMP | Rule 16 | 12 | 77 | 28 | 1 | 0 | 44 | 158
5737 | 2018-05-18 | 2018-06-29 | 2018-10-31 | 2018-10-31 | COMP | 2019-09-27 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-02-15 | COMP | Rule 16 | 30 | 87 | 228 | 42 | 1 | 54 | 437
5926 | 2018-05-18 | 2018-07-12 | 2018-11-14 | 2019-03-25 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-10-03 | COMP | 2019-11-16 | COMP | Rule 16 | 38 | 88 | 18 | 1 | 119 | 31 | 377
6102 | 2018-05-18 | 2018-07-25 | 2018-08-28 | 2018-12-18 | COMP | 2020-10-03 | REQD | 2019-05-23 | COMP | 2019-07-08 | NOTN | 2019-08-20 | COMP | Rule 15/16 | 47 | 25 |  | 109 |  |  | 316
6336 | 2018-05-18 | 2018-08-11 | 2018-11-01 | 2019-02-27 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-04-18 | COMP | 2019-08-29 | COMP | Rule 16 | 59 | 58 | 15 | 1 | 23 | 94 | 323
6675 | 2018-05-18 | 2018-09-05 | 2018-12-10 | 2018-12-10 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2020-05-12 | COMP | 2020-05-20 | COMP | Rule 16 | 76 | 66 | 105 | 1 | 254 | 7 | 504
8189 | 2018-05-18 | 2018-11-19 | 2019-03-31 | 2019-04-04 | COMP | 2019-06-27 | COMP | 2019-06-28 | COMP | 2019-07-10 | COMP | 2019-08-02 | COMP | Rule 16 | 128 | 89 | 60 | 2 | 8 | 18 | 304
8257 | 2018-05-18 | 2018-11-20 | 2019-02-07 | 2019-02-07 | COMP | 2019-02-27 | COMP | 2019-03-01 | COMP | 2019-04-10 | COMP | 2019-04-26 | COMP | Rule 16 | 129 | 53 | 14 | 3 | 29 | 13 | 236
10677 | 2018-05-18 | 2019-03-26 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2020-01-07 | COMP | 2020-01-04 | COMP | Rule 15/16 | 213 | 11 | 12 | 1 | 177 |  | 408
14166 | 2018-05-18 | 2019-08-28 | 2019-10-31 | 2019-12-10 | COMP | 2020-08-06 | COMP | 2020-09-10 | COMP | 2021-02-03 | COMP | 2021-05-28 | COMP | Rule 16 | 322 | 46 | 168 | 25 | 99 | 82 | 762
5661 | 2018-05-19 | 2018-06-25 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2018-12-21 | COMP | 2019-03-20 | COMP | Rule 16 | 25 | 109 | 15 | 1 | 3 | 60 | 208
6137 | 2018-05-19 | 2018-07-30 | 2018-12-08 | 2018-12-08 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-10-21 | INPR | 2019-07-12 | COMP | Rule 16 | 49 | 91 | 111 | 1 |  |  | 288
6370 | 2018-05-19 | 2018-08-14 | 2018-11-08 | 2018-11-08 | COMP | 2019-07-05 | COMP | 2019-05-30 | COMP | 2020-09-26 | INPR | 2019-07-16 | COMP | Rule 16 | 60 | 62 | 163 |  |  |  | 290
7404 | 2018-05-19 | 2018-10-11 | 2019-01-24 | 2019-01-24 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2021-04-08 | COMP | 2021-05-17 | COMP | Rule 16 | 101 | 70 | 101 | 1 | 456 | 28 | 752
7831 | 2018-05-19 | 2018-11-01 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-28 | COMP | 2019-03-01 | COMP | 2020-05-06 | COMP | 2020-06-04 | COMP | Rule 16 | 116 | 52 | 28 | 2 | 299 | 21 | 513
5795 | 2018-05-20 | 2018-07-03 | 2019-02-11 | 2019-02-11 | COMP | 2019-03-25 | COMP | 2019-12-03 | COMP | 2020-03-10 | COMP | 2020-06-30 | COMP | Rule 16 | 31 | 152 | 30 | 176 | 67 | 80 | 531
3700 | 2018-05-21 | 2018-06-12 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-15 | NOTN | 2018-12-04 | COMP | 2019-08-09 | COMP | 2019-09-03 | COMP | Other | 16 | 70 |  | 52 | 173 | 17 | 324
3929 | 2018-05-21 | 2018-10-19 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-19 | COMP | 2019-01-16 | COMP | 2019-01-18 | COMP | 2019-03-04 | COMP | Rule 16 | 107 | 18 | 4 | 39 | 3 | 30 | 196
5672 | 2018-05-21 | 2018-06-25 | 2019-04-05 | 2019-04-14 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-06-19 | COMP | 2020-07-28 | COMP | Rule 16 | 25 | 196 | 225 | 1 | 75 | 28 | 551
5699 | 2018-05-21 | 2018-06-25 | 2018-08-13 | 2018-08-13 | COMP | 2018-09-27 | COMP | 2018-09-27 | COMP | 2019-07-16 | COMP | 2019-07-25 | COMP | Rule 16 | 25 | 35 | 33 | 1 | 200 | 8 | 297
5774 | 2018-05-21 | 2018-07-05 | 2018-09-27 | 2018-12-12 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-01-25 | COMP | 2019-03-27 | COMP | Rule 16 | 32 | 60 | 29 | 1 | 2 | 43 | 213
5803 | 2018-05-21 | 2018-07-05 | 2018-08-20 | 2018-08-20 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2020-03-16 | COMP | 2020-04-15 | COMP | Rule 16 | 32 | 33 | 85 | 1 | 309 | 23 | 478
5854 | 2018-05-21 | 2018-07-09 | 2018-08-03 | 2018-08-03 | COMP | 2018-08-20 | COMP | 2018-08-20 | COMP | 2018-11-08 | COMP | 2019-02-06 | COMP | Rule 16 | 34 | 20 | 12 | 1 | 58 | 59 | 179
6052 | 2018-05-21 | 2018-07-23 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-14 | COMP | 2018-11-21 | COMP | 2018-12-17 | COMP | 2019-01-03 | COMP | Rule 15/16 | 44 | 71 | 11 | 6 | 17 | 12 | 156
6285 | 2018-05-21 | 2018-08-09 | 2018-12-20 | 2018-12-20 | COMP | 2018-12-20 | NOTN | 2019-02-06 | COMP | 2019-02-01 | COMP | 2019-09-24 | COMP | Other | 57 | 92 |  | 32 | 0 | 161 | 339
6293 | 2018-05-21 | 2018-08-09 | 2018-10-22 | 2018-10-22 | COMP | 2018-11-01 | COMP | 2018-11-29 | COMP | 2019-01-08 | COMP | 2019-01-29 | COMP | Rule 16 | 57 | 52 | 9 | 18 | 27 | 15 | 173
6319 | 2018-05-21 | 2018-08-10 | 2019-02-27 | 2019-02-27 | COMP | 2019-06-07 | COMP | 2019-10-02 | COMP | 2019-09-10 | COMP | 2019-12-20 | COMP | Rule 15/16 | 58 | 136 | 72 | 82 | 0 | 55 | 399
6380 | 2018-05-21 | 2018-08-14 | 2018-12-05 | 2018-12-05 | COMP | 2019-02-22 | COMP | 2019-07-25 | COMP | 2020-07-03 | COMP | 2020-08-12 | COMP | Rule 16 | 60 | 78 | 54 | 108 | 238 | 29 | 562
6426 | 2018-05-21 | 2018-08-17 | 2019-02-19 | 2019-02-19 | COMP | 2019-06-24 | COMP | 2021-05-10 | COMP | 2021-07-19 | COMP | 2021-07-27 | COMP | Rule 15/16 | 63 | 125 | 89 | 473 | 49 | 7 | 801
6588 | 2018-05-21 | 2018-08-31 | 2018-10-16 | 2018-11-19 | COMP | 2019-01-08 | COMP | 2019-03-21 | COMP | 2019-05-17 | COMP | 2019-06-06 | COMP | Rule 15/16 | 73 | 32 | 33 | 51 | 42 | 14 | 263
6729 | 2018-05-21 | 2018-09-10 | 2018-09-28 | 2018-09-28 | COMP | 2018-11-09 | COMP | 2018-12-27 | COMP | 2018-11-21 | COMP | 2019-10-14 | COMP | Rule 16 | 78 | 15 | 31 | 31 | 0 | 202 | 353
6918 | 2018-05-21 | 2018-09-17 | 2019-08-27 | 2019-08-27 | COMP | 2019-09-04 | COMP | 2019-10-14 | COMP |  | INPR | 2021-05-15 | COMP | Rule 16 | 83 | 238 | 6 | 29 |  |  | 751
6983 | 2018-05-21 | 2018-09-20 | 2019-01-07 | 2019-01-07 | COMP | 2019-02-12 | COMP | 2019-09-10 | INPR | 2019-08-02 | COMP | 2019-09-10 | COMP | Rule 16 | 86 | 73 | 26 |  |  |  | 329
7319 | 2018-05-21 | 2018-10-08 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-09-22 | INPR | 2019-05-28 | COMP | Rule 16 | 98 | 127 | 9 | 1 |  |  | 256
7349 | 2018-05-21 | 2018-10-10 | 2019-01-14 | 2019-03-07 | COMP | 2019-04-15 | COMP | 2019-07-12 | COMP | 2019-07-17 | COMP | 2019-09-21 | COMP | Rule 15/16 | 100 | 64 | 28 | 63 | 4 | 47 | 337
7390 | 2018-05-21 | 2018-10-10 | 2019-04-09 | 2019-04-09 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2020-06-05 | COMP | 2020-06-24 | COMP | Rule 16 | 100 | 123 | 105 | 1 | 189 | 14 | 527
7714 | 2018-05-21 | 2018-10-27 | 2019-01-31 | 2019-01-31 | COMP | 2019-03-07 | COMP | 2019-04-09 | COMP | 2019-07-21 | INPR | 2019-04-29 | COMP | Rule 16 | 112 | 63 | 25 | 24 |  |  | 236
7848 | 2018-05-21 | 2018-11-02 | 2019-02-15 | 2019-04-11 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2019-09-19 | COMP | 2020-02-04 | COMP | Rule 15/16 | 117 | 70 | 147 | 1 | 0 | 59 | 428
8185 | 2018-05-21 | 2018-11-19 | 2019-02-03 | 2019-05-15 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-04-26 | INPR | 2020-01-02 | COMP | Rule 16 | 127 | 50 | 130 | 1 |  |  | 406
8733 | 2018-05-21 | 2018-12-20 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | Rule 15/16 | 148 | 27 | 7 | 1 | 94 | 1 | 273
9405 | 2018-05-21 | 2019-02-01 | 2019-04-08 | 2019-04-08 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2020-08-24 | COMP | 2020-09-22 | COMP | Rule 16 | 176 | 46 | 63 | 1 | 288 | 21 | 590
9447 | 2018-05-21 | 2019-02-04 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-07 | COMP | 2019-06-25 | COMP | 2019-07-12 | COMP | 2019-07-19 | COMP | Rule 16 | 177 | 74 | 15 | 13 | 13 | 6 | 293
9862 | 2018-05-21 | 2019-02-20 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-09 | COMP | 2019-06-19 | COMP | 2019-10-21 | INPR | 2019-07-10 | COMP | Rule 16 | 188 | 40 | 18 | 29 |  |  | 286
10827 | 2018-05-21 | 2019-04-01 | 2019-05-21 | 2019-05-21 | COMP | 2019-06-07 | COMP | 2019-05-30 | COMP | 2020-04-26 | INPR | 2019-06-27 | COMP | Rule 16 | 216 | 37 | 13 |  |  |  | 278
11332 | 2018-05-21 | 2019-04-24 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-25 | COMP | 2019-10-21 | COMP | 2020-02-05 | COMP | 2020-03-04 | COMP | Rule 16 | 233 | 86 | 22 | 19 | 72 | 20 | 448
15117 | 2018-05-21 | 2019-10-14 | 2020-04-09 | 2020-04-09 | COMP | 2020-05-14 | COMP | 2020-09-02 | COMP | 2021-08-17 | COMP | 2021-10-01 | COMP | Rule 15/16 | 353 | 122 | 26 | 79 | 240 | 33 | 848
31554 | 2018-05-21 | 2021-10-13 | 2022-02-16 | 2022-02-16 | COMP | 2022-03-03 | COMP | 2022-03-03 | COMP | 2023-07-01 | INPR | 2022-04-25 | COMP | Rule 16 | 856 | 87 | 11 | 1 |  |  | 989
5512 | 2018-05-22 | 2018-06-05 | 2019-01-05 | 2019-01-05 | COMP | 2019-01-23 | NOTN | 2019-01-23 | COMP | 2019-06-28 | COMP | 2019-08-01 | COMP | Other | 10 | 147 |  | 12 | 111 | 24 | 301
5599 | 2018-05-22 | 2018-06-18 | 2018-09-04 | 2018-09-04 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-06-26 | COMP | 2019-07-02 | COMP | Rule 16 | 19 | 55 | 98 | 1 | 107 | 5 | 280
5677 | 2018-05-22 | 2018-06-25 | 2018-08-08 | 2018-08-08 | COMP | 2018-10-31 | COMP | 2018-11-01 | COMP | 2019-01-15 | COMP | 2019-01-25 | COMP | Rule 16 | 24 | 32 | 60 | 2 | 49 | 8 | 170
5721 | 2018-05-22 | 2018-06-26 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-21 | COMP | 2019-03-20 | COMP | 2019-02-27 | COMP | 2019-03-24 | COMP | Rule 16 | 25 | 107 | 58 | 20 | 0 | 3 | 209
5764 | 2018-05-22 | 2018-07-02 | 2018-10-04 | 2018-10-04 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-05-01 | COMP | 2019-05-06 | COMP | Rule 16 | 29 | 67 | 21 | 1 | 123 | 4 | 240
5788 | 2018-05-22 | 2018-07-02 | 2018-11-26 | 2018-11-26 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2018-12-27 | COMP | 2019-04-08 | COMP | Rule 16 | 29 | 101 | 27 | 1 | 0 | 66 | 220
5965 | 2018-05-22 | 2018-07-16 | 2019-04-06 | 2019-04-06 | COMP | 2019-07-29 | COMP | 2020-01-27 | COMP | 2020-03-29 | COMP | 2020-06-11 | COMP | Rule 15/16 | 38 | 182 | 79 | 124 | 44 | 53 | 517
6030 | 2018-05-22 | 2018-07-19 | 2019-03-01 | 2019-03-01 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-05-20 | COMP | 2019-05-24 | COMP | Rule 16 | 41 | 154 | 35 | 1 | 23 | 5 | 254
6205 | 2018-05-22 | 2018-08-03 | 2018-09-10 | 2018-09-10 | COMP | 2019-03-21 | COMP | 2019-07-22 | INPR | 2019-07-23 | COMP | 2019-07-24 | COMP | Rule 16 | 52 | 26 | 132 |  |  |  | 295
6230 | 2018-05-22 | 2018-08-04 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-29 | COMP | 2018-12-26 | COMP | 2019-01-08 | COMP | 2019-04-03 | COMP | Rule 16 | 52 | 62 | 19 | 19 | 9 | 60 | 217
6421 | 2018-05-22 | 2018-08-16 | 2018-10-10 | 2018-10-10 | COMP | 2019-04-20 | NOTN | 2019-04-20 | COMP | 2019-04-20 | NOTN | 2020-06-30 | COMP | Rule 16 | 61 | 39 |  | 131 |  |  | 530
6610 | 2018-05-22 | 2018-08-30 | 2018-12-22 | 2018-12-22 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-07-21 | INPR | 2019-02-08 | COMP | Rule 16 | 71 | 78 | 26 | 1 |  |  | 180
6850 | 2018-05-22 | 2018-09-13 | 2018-09-22 | 2018-09-22 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-08-17 | COMP | 2019-09-03 | COMP | Rule 16 | 80 | 7 | 90 | 1 | 137 | 11 | 323
6977 | 2018-05-22 | 2018-09-20 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-23 | COMP | 2019-06-21 | COMP | 2019-05-21 | COMP | 2019-07-20 | COMP | Rule 16 | 85 | 52 | 33 | 106 | 0 | 20 | 292
8004 | 2018-05-22 | 2018-11-13 | 2018-12-11 | 2020-01-08 | COMP | 2020-03-04 | COMP | 2019-04-03 | COMP | 2020-03-04 | COMP | 2020-02-07 | COMP | Rule 16 | 122 | 19 | 39 |  | 231 |  | 430
8138 | 2018-05-22 | 2018-11-16 | 2019-01-05 | 2019-01-05 | COMP | 2019-10-25 | COMP | 2020-08-26 | COMP | 2020-06-15 | COMP | 2020-10-16 | COMP | Rule 16 | 125 | 32 | 205 | 211 | 0 | 37 | 607
8139 | 2018-05-22 | 2018-11-16 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2020-02-20 | COMP | 2020-05-15 | COMP | Rule 16 | 125 | 86 | 28 | 1 | 202 | 62 | 499
9114 | 2018-05-22 | 2019-01-17 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-01 | COMP | 2019-03-13 | COMP | 2019-03-01 | COMP | 2019-03-14 | COMP | Rule 16 | 165 | 25 | 6 | 9 | 0 | 2 | 203
9715 | 2018-05-22 | 2019-02-12 | 2019-04-25 | 2019-04-25 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2020-10-12 | COMP | 2020-12-02 | COMP | Rule 15/16 | 182 | 52 | 55 | 1 | 317 | 35 | 637
10041 | 2018-05-22 | 2019-02-27 | 2019-05-21 | 2019-05-21 | COMP | 2019-08-08 | COMP | 2019-08-08 | COMP | 2020-09-01 | COMP | 2020-09-21 | COMP | Rule 16 | 192 | 60 | 56 | 1 | 270 | 14 | 588
10662 | 2018-05-22 | 2019-03-25 | 2019-07-03 | 2019-07-30 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-16 | COMP | Rule 15/16 | 210 | 72 | 74 | 1 | 1 | 23 | 394
11169 | 2018-05-22 | 2019-04-16 | 2019-07-12 | 2020-04-13 | COMP | 2020-11-13 | COMP | 2020-11-17 | COMP | 2020-11-24 | COMP | 2020-12-16 | COMP | Rule 16 | 226 | 62 | 152 | 3 | 6 | 15 | 647
11216 | 2018-05-22 | 2019-04-17 | 2019-09-06 | 2020-03-03 | COMP | 2020-11-13 | COMP | 2021-01-14 | COMP | 2020-11-25 | COMP | 2021-02-12 | COMP | Rule 15/16 | 227 | 100 | 181 | 41 | 0 | 21 | 686
12380 | 2018-05-22 | 2019-06-04 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-12-09 | COMP | 2020-01-15 | COMP | Rule 15/16 | 260 | 85 | 12 | 1 | 35 | 26 | 414
12754 | 2018-05-22 | 2019-06-20 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-07-22 | COMP | 2020-08-26 | COMP | Rule 16 | 272 | 157 | 15 | 1 | 105 | 26 | 571
13831 | 2018-05-22 | 2019-08-12 | 2020-03-02 | 2020-04-09 | COMP | 2020-05-04 | COMP | 2020-05-15 | COMP | 2021-04-06 | COMP | 2021-05-07 | COMP | Rule 15/16 | 308 | 138 | 18 | 10 | 224 | 24 | 745
14822 | 2018-05-22 | 2019-09-29 | 2019-12-18 | 2019-12-18 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-08-19 | COMP | 2020-11-04 | COMP | Rule 16 | 341 | 55 | 29 | 1 | 143 | 55 | 620
3983 | 2018-05-23 | 2018-11-06 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-05 | COMP | 2019-09-20 | COMP | 2019-09-25 | COMP | 2019-12-17 | COMP | Rule 16 | 117 | 171 | 38 | 12 | 4 | 57 | 394
4029 | 2018-05-23 | 2018-12-13 | 2019-01-03 | 2019-01-03 | COMP | 2019-01-08 | COMP | 2019-01-25 | COMP | 2019-01-08 | COMP | 2019-02-12 | COMP | Rule 16 | 141 | 14 | 4 | 13 | 0 | 13 | 181
4073 | 2018-05-23 | 2019-01-08 | 2019-03-14 | 2019-03-14 | COMP | 2019-05-24 | COMP | 2019-08-28 | COMP | 2020-04-23 | COMP | 2020-06-10 | COMP | Rule 15/16 | 157 | 46 | 52 | 67 | 164 | 34 | 515
4102 | 2018-05-23 | 2019-02-04 | 2019-05-17 | 2019-05-17 | COMP | 2019-08-07 | COMP | 2019-08-22 | COMP | 2020-02-03 | COMP | 2020-02-26 | COMP | Rule 15/16 | 175 | 74 | 57 | 12 | 111 | 17 | 441
5471 | 2018-05-23 | 2018-06-01 | 2018-10-12 | 2018-10-12 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2019-01-03 | COMP | 2019-01-28 | COMP | Rule 16 | 7 | 94 | 9 | 1 | 47 | 17 | 170
5487 | 2018-05-23 | 2018-06-04 | 2018-10-08 | 2018-10-08 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-03-04 | COMP | Rule 16 | 8 | 89 | 78 | 1 | 2 | 21 | 194
5488 | 2018-05-23 | 2018-06-04 | 2018-10-19 | 2018-10-19 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-03-27 | COMP | Rule 16 | 8 | 98 | 69 | 1 | 2 | 38 | 211
5555 | 2018-05-23 | 2018-06-13 | 2018-10-06 | 2018-10-06 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-03-25 | COMP | 2019-04-09 | COMP | Rule 16 | 15 | 81 | 17 | 1 | 98 | 12 | 220
5566 | 2018-05-23 | 2018-06-14 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-01-23 | COMP | 2019-03-09 | COMP | Rule 16 | 16 | 95 | 20 | 1 | 38 | 32 | 198
5744 | 2018-05-23 | 2018-06-28 | 2019-03-18 | 2019-03-19 | COMP | 2019-03-28 | COMP | 2019-06-03 | COMP | 2020-05-31 | INPR | 2019-07-14 | COMP | Rule 15/16 | 26 | 179 | 8 | 47 |  |  | 286
5754 | 2018-05-23 | 2018-06-29 | 2018-12-10 | 2018-12-10 | COMP | 2019-02-26 | COMP | 2019-08-28 | COMP | 2019-12-06 | COMP | 2020-01-24 | COMP | Rule 16 | 27 | 112 | 53 | 130 | 69 | 33 | 419
5778 | 2018-05-23 | 2018-07-03 | 2018-11-16 | 2019-04-19 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-09-01 | INPR | 2019-05-17 | COMP | Rule 16 | 29 | 96 | 9 | 1 |  |  | 248
5781 | 2018-05-23 | 2018-07-03 | 2018-09-26 | 2018-09-26 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2020-06-01 | COMP | 2020-06-22 | COMP | Rule 16 | 29 | 60 | 164 | 1 | 258 | 16 | 523
5867 | 2018-05-23 | 2018-07-09 | 2018-10-05 | 2018-10-05 | COMP | 2018-11-05 | COMP | 2018-10-31 | COMP | 2018-10-23 | COMP | 2019-02-02 | COMP | Rule 15/16 | 32 | 64 | 22 |  | 0 | 62 | 174
5968 | 2018-05-23 | 2018-07-16 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-01-11 | COMP | 2019-01-24 | COMP | Rule 16 | 37 | 94 | 10 | 1 | 22 | 9 | 168
6253 | 2018-05-23 | 2018-08-08 | 2018-11-09 | 2018-11-09 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2020-11-21 | INPR | 2019-07-10 | COMP | Rule 16 | 54 | 67 | 45 | 1 |  |  | 284
6358 | 2018-05-23 | 2018-08-13 | 2019-02-07 | 2021-02-18 | COMP | 2021-03-15 | COMP | 2021-03-22 | COMP | 2021-10-25 | COMP | 2022-01-12 | COMP | Rule 15/16 | 57 | 122 | 18 | 6 | 153 | 55 | 916
6710 | 2018-05-23 | 2018-09-10 | 2018-10-03 | 2018-10-03 | COMP | 2019-01-18 | COMP | 2019-01-22 | COMP | 2019-09-01 | INPR | 2019-04-18 | COMP | Rule 16 | 76 | 18 | 73 | 2 |  |  | 227
6889 | 2018-05-23 | 2018-09-14 | 2018-11-14 | 2018-11-14 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-06-11 | COMP | 2019-08-04 | COMP | Rule 15/16 | 80 | 43 | 40 | 1 | 104 | 38 | 301
8456 | 2018-05-23 | 2018-12-04 | 2019-04-03 | 2019-05-05 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | 2021-02-25 | COMP | 2021-04-30 | COMP | Rule 16 | 134 | 83 | 424 | 1 | 32 | 47 | 739
9003 | 2018-05-23 | 2019-01-11 | 2019-05-10 | 2019-05-10 | COMP | 2019-06-25 | COMP | 2019-11-21 | COMP | 2019-10-25 | COMP | 2019-12-02 | COMP | Rule 16 | 160 | 84 | 32 | 105 | 0 | 6 | 383
9029 | 2018-05-23 | 2019-01-14 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-20 | COMP | 2019-03-20 | INPR | 2019-12-03 | COMP | 2019-12-17 | COMP | Rule 16 | 161 | 28 | 19 |  |  |  | 394
10872 | 2018-05-23 | 2019-04-02 | 2020-04-15 | 2020-04-15 | COMP | 2020-06-05 | COMP | 2020-07-10 | COMP | 2020-12-29 | COMP | 2021-01-15 | COMP | Rule 15/16 | 215 | 262 | 37 | 26 | 118 | 13 | 666
11156 | 2018-05-23 | 2019-04-15 | 2019-08-13 | 2019-12-03 | COMP | 2019-12-30 | COMP | 2020-01-13 | COMP | 2020-03-17 | COMP | 2020-06-26 | COMP | Rule 15/16 | 224 | 85 | 19 | 10 | 45 | 73 | 527
12537 | 2018-05-23 | 2019-06-12 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-12 | COMP | 2021-08-24 | COMP | 2022-02-23 | COMP | 2022-03-16 | COMP | Rule 15/16 | 265 | 172 | 17 | 368 | 126 | 16 | 959
12990 | 2018-05-23 | 2019-07-03 | 2019-09-04 | 2019-09-04 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-03-01 | COMP | 2020-06-03 | COMP | Rule 15/16 | 280 | 44 | 62 | 1 | 60 | 67 | 510
3786 | 2018-05-24 | 2018-07-14 | 2018-09-11 | 2018-09-11 | COMP | 2018-11-09 | COMP | 2018-11-30 | COMP | 2019-04-15 | COMP | 2019-07-22 | COMP | Rule 16 | 35 | 41 | 44 | 13 | 93 | 69 | 291
5394 | 2018-05-24 | 2018-05-29 | 2018-08-31 | 2018-08-31 | COMP | 2018-09-13 | COMP | 2018-09-28 | COMP | 2019-04-23 | COMP | 2019-05-20 | COMP | Rule 16 | 3 | 68 | 9 | 12 | 141 | 20 | 248
5418 | 2018-05-24 | 2018-05-30 | 2018-08-21 | 2018-09-18 | COMP | 2018-10-04 | COMP | 2018-10-04 | COMP | 2019-04-29 | COMP | 2019-06-26 | COMP | Rule 16 | 4 | 59 | 13 | 1 | 141 | 42 | 274
5522 | 2018-05-24 | 2018-06-07 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2019-08-22 | COMP | 2019-09-10 | COMP | Rule 16 | 10 | 78 | 10 | 1 | 219 | 13 | 326
5595 | 2018-05-24 | 2018-06-18 | 2018-10-12 | 2018-10-12 | COMP | 2019-03-04 | COMP | 2019-03-05 | COMP | 2019-03-04 | COMP | 2019-04-13 | COMP | Rule 16 | 17 | 83 | 95 | 2 | 0 | 29 | 222
5657 | 2018-05-24 | 2018-06-24 | 2018-10-12 | 2018-10-12 | COMP | 2018-10-29 | COMP | 2018-10-29 | COMP | 2019-07-17 | COMP | 2019-10-08 | COMP | Rule 16 | 21 | 78 | 12 | 1 | 179 | 59 | 346
5685 | 2018-05-24 | 2018-06-25 | 2020-11-02 | 2021-02-09 | COMP | 2021-03-03 | COMP | 2021-03-09 | COMP | 2021-03-05 | COMP | 2021-04-16 | COMP | Rule 15/16 | 22 | 595 | 16 | 5 | 0 | 29 | 728
5735 | 2018-05-24 | 2018-06-27 | 2018-11-08 | 2019-04-12 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-04-30 | COMP | 2019-06-24 | COMP | Rule 16 | 24 | 95 | 12 | 1 | 2 | 39 | 272
5745 | 2018-05-24 | 2018-06-28 | 2019-03-01 | 2019-03-05 | COMP | 2019-04-03 | COMP | 2019-06-10 | COMP | 2019-06-07 | COMP | 2019-08-24 | COMP | Rule 16 | 25 | 168 | 22 | 48 | 0 | 54 | 315
5755 | 2018-05-24 | 2018-06-29 | 2018-10-20 | 2018-10-20 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-01-07 | COMP | 2019-01-14 | COMP | Rule 16 | 26 | 79 | 12 | 1 | 40 | 6 | 160
5768 | 2018-05-24 | 2018-07-02 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-04-04 | COMP | 2019-07-16 | COMP | Rule 16 | 27 | 158 | 14 | 1 | 20 | 72 | 287
5870 | 2018-05-24 | 2018-07-09 | 2018-10-23 | 2019-09-05 | COMP | 2019-09-16 | COMP | 2019-06-17 | COMP | 2020-02-27 | COMP | 2020-03-24 | COMP | Rule 16 | 31 | 76 | 8 |  | 175 | 19 | 459
6069 | 2018-05-24 | 2018-07-24 | 2018-08-25 | 2018-08-25 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-11-13 | COMP | 2019-12-11 | COMP | Rule 16 | 42 | 24 | 103 | 1 | 204 | 19 | 389
6082 | 2018-05-24 | 2018-07-24 | 2019-05-29 | 2019-07-11 | COMP | 2019-07-22 | COMP | 2019-08-01 | COMP | 2019-08-30 | COMP | 2019-09-17 | COMP | Rule 15/16 | 42 | 213 | 8 | 9 | 22 | 12 | 331
6115 | 2018-05-24 | 2018-07-27 | 2019-05-29 | 2019-05-29 | COMP | 2020-03-02 | COMP | 2021-04-15 | COMP | 2021-03-15 | COMP | 2021-05-11 | COMP | Rule 15/16 | 45 | 210 | 190 | 285 | 0 | 19 | 745
6297 | 2018-05-24 | 2018-08-09 | 2018-11-09 | 2018-11-09 | COMP | 2019-02-11 | COMP | 2019-09-18 | COMP | 2019-10-15 | COMP | 2019-11-08 | COMP | Rule 15/16 | 54 | 66 | 61 | 154 | 20 | 19 | 369
6322 | 2018-05-24 | 2018-08-10 | 2019-06-27 | 2021-06-07 | COMP | 2021-06-16 | COMP | 2021-12-22 | COMP | 2021-12-08 | COMP | 2022-02-03 | COMP | Rule 15/16 | 55 | 221 | 8 | 131 | 0 | 31 | 930
6424 | 2018-05-24 | 2018-08-17 | 2018-09-18 | 2018-09-18 | COMP | 2018-11-15 | COMP | 2019-02-08 | COMP | 2019-10-21 | INPR | 2019-03-21 | COMP | Rule 15/16 | 60 | 22 | 42 | 57 |  |  | 206
6873 | 2018-05-24 | 2018-09-14 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-08 | COMP | 2018-12-06 | COMP | 2018-11-26 | COMP | 2019-03-07 | COMP | Rule 16 | 79 | 24 | 17 | 18 | 0 | 62 | 196
7033 | 2018-05-24 | 2018-09-25 | 2019-09-21 | 2020-05-08 | COMP | 2020-06-08 | COMP | 2020-11-04 | COMP | 2021-04-29 | COMP | 2021-01-05 | COMP | Rule 15/16 | 86 | 249 | 21 | 107 | 120 |  | 657
7244 | 2018-05-24 | 2018-10-04 | 2019-05-17 | 2019-05-17 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-05-19 | COMP | 2020-05-26 | COMP | Rule 16 | 93 | 155 | 136 | 1 | 118 | 5 | 503
7328 | 2018-05-24 | 2018-10-09 | 2018-11-08 | 2018-11-08 | COMP | 2019-04-01 | COMP | 2019-03-18 | COMP | 2019-04-05 | COMP | 2019-04-17 | COMP | Rule 16 | 96 | 23 | 96 |  | 15 | 9 | 225
7405 | 2018-05-24 | 2018-10-11 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-04-18 | COMP | 2019-05-13 | COMP | Rule 16 | 98 | 91 | 12 | 1 | 28 | 18 | 243
7887 | 2018-05-24 | 2018-11-04 | 2018-12-07 | 2018-12-26 | COMP | 2018-12-31 | COMP | 2019-01-16 | COMP | 2019-02-09 | COMP | 2019-03-12 | COMP | Rule 16 | 114 | 22 | 4 | 12 | 17 | 21 | 199
8003 | 2018-05-24 | 2018-11-09 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-10-24 | COMP | 2019-12-11 | COMP | Rule 16 | 119 | 73 | 21 | 1 | 148 | 32 | 389
10055 | 2018-05-24 | 2019-02-28 | 2019-06-04 | 2019-07-02 | COMP | 2019-07-29 | COMP | 2020-12-09 | COMP | 2022-01-18 | COMP | 2022-02-17 | COMP | Rule 16 | 191 | 68 | 19 | 345 | 279 | 23 | 940
10184 | 2018-05-24 | 2019-03-05 | 2019-08-09 | 2019-10-22 | COMP | 2020-01-16 | COMP | 2020-05-29 | COMP | 2021-02-14 | COMP | 2021-03-29 | COMP | Rule 16 | 194 | 112 | 58 | 94 | 179 | 30 | 714
3745 | 2018-05-25 | 2018-06-26 | 2018-09-24 | 2019-06-12 | COMP | 2019-07-03 | COMP | 2019-07-02 | COMP | 2019-07-10 | COMP | 2019-08-01 | COMP | Rule 15/16 | 22 | 63 | 16 |  | 6 | 17 | 298
3820 | 2018-05-25 | 2018-07-30 | 2018-09-18 | 2018-09-18 | COMP | 2019-03-11 | COMP | 2019-03-13 | COMP | 2019-09-20 | COMP | 2020-02-29 | COMP | Rule 15/16 | 45 | 36 | 118 | 3 | 135 | 109 | 441
3841 | 2018-05-25 | 2018-08-13 | 2019-01-14 | 2019-01-14 | COMP | 2019-05-21 | COMP | 2019-05-29 | COMP | 2021-02-04 | COMP | 2021-01-07 | COMP | Rule 16 | 55 | 105 | 90 | 6 | 425 |  | 658
4173 | 2018-05-25 | 2019-05-23 | 2019-06-20 | 2019-06-20 | COMP | 2020-08-13 | COMP | 2021-04-17 | COMP | 2021-04-13 | COMP | 2021-04-18 | COMP | Rule 15/16 | 250 | 20 | 291 | 169 | 0 | 0 | 727
5478 | 2018-05-25 | 2018-06-04 | 2018-12-11 | 2019-08-30 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2020-01-17 | COMP | 2020-03-09 | COMP | Rule 15/16 | 6 | 132 | 10 | 1 | 86 | 35 | 447
5494 | 2018-05-25 | 2018-06-04 | 2018-12-07 | 2018-12-07 | COMP | 2019-05-24 | NOTN | 2019-12-16 | COMP | 2019-11-01 | COMP | 2020-01-03 | COMP | Other | 6 | 130 |  | 257 | 0 | 13 | 403
5538 | 2018-05-25 | 2018-06-12 | 2018-12-20 | 2019-01-15 | COMP | 2019-01-23 | COMP | 2019-06-11 | COMP | 2019-09-13 | COMP | 2019-12-20 | COMP | Rule 15/16 | 12 | 133 | 6 | 98 | 67 | 68 | 395
5539 | 2018-05-25 | 2018-06-12 | 2019-04-17 | 2019-04-17 | COMP | 2019-04-30 | COMP | 2020-08-04 | COMP | 2020-08-03 | COMP | 2020-09-11 | COMP | Rule 15/16 | 12 | 213 | 10 | 320 | 0 | 28 | 579
5602 | 2018-05-25 | 2018-06-19 | 2019-01-01 | 2019-02-23 | COMP | 2019-04-30 | COMP | 2019-05-06 | COMP | 2019-05-01 | COMP | 2019-06-13 | COMP | Rule 16 | 17 | 134 | 47 | 5 | 0 | 28 | 264
5603 | 2018-05-25 | 2018-06-19 | 2018-09-27 | 2018-09-27 | COMP | 2018-11-28 | COMP | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-03-21 | COMP | Rule 16 | 17 | 71 | 42 | 43 | 7 | 30 | 205
5889 | 2018-05-25 | 2018-07-09 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-18 | COMP | 2019-05-06 | COMP | 2019-05-21 | COMP | 2019-06-21 | COMP | Rule 15/16 | 30 | 89 | 24 | 96 | 12 | 23 | 270
5913 | 2018-05-25 | 2018-07-10 | 2019-11-06 | 2019-11-06 | COMP | 2020-03-06 | COMP | 2020-04-30 | COMP | 2021-09-08 | COMP | 2023-04-27 | COMP | Rule 15/16 | 31 | 336 | 81 | 40 | 343 | 411 | 1237
6026 | 2018-05-25 | 2018-07-18 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-07 | COMP | 2018-11-07 | COMP | 2018-11-13 | COMP | 2019-01-03 | COMP | Rule 16 | 37 | 74 | 7 | 1 | 4 | 34 | 152
6054 | 2018-05-25 | 2018-07-23 | 2018-10-10 | 2018-12-12 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-02-04 | COMP | 2019-03-25 | COMP | Rule 16 | 40 | 57 | 30 | 1 | 7 | 35 | 207
6381 | 2018-05-25 | 2018-08-15 | 2019-03-03 | 2019-03-03 | COMP | 2019-04-03 | COMP | 2019-05-10 | COMP | 2019-06-19 | COMP | 2019-05-19 | COMP | Rule 15/16 | 57 | 135 | 23 | 28 | 28 |  | 246
7311 | 2018-05-25 | 2018-10-08 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-05-11 | COMP | 2020-07-02 | COMP | Rule 16 | 94 | 290 | 18 | 1 | 93 | 38 | 529
7565 | 2018-05-25 | 2018-10-19 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-12 | NOTN | 2018-12-12 | COMP | 2018-12-06 | COMP | 2019-01-13 | COMP | Other | 103 | 19 |  | 18 | 0 | 21 | 158
8047 | 2018-05-25 | 2018-11-14 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-01-30 | COMP | 2019-03-13 | COMP | Rule 16 | 120 | 3 | 10 | 1 | 39 | 30 | 199
8275 | 2018-05-25 | 2018-11-25 | 2019-01-25 | 2019-08-21 | COMP | 2019-10-22 | COMP | 2019-11-08 | COMP | 2019-11-19 | COMP | 2020-01-02 | COMP | Rule 16 | 125 | 42 | 44 | 14 | 7 | 29 | 402
9885 | 2018-05-25 | 2019-02-21 | 2019-06-28 | 2019-06-28 | COMP | 2019-09-04 | COMP | 2020-08-10 | COMP | 2021-04-12 | COMP | 2021-06-05 | COMP | Rule 16 | 185 | 91 | 47 | 236 | 168 | 39 | 761
10621 | 2018-05-25 | 2019-03-22 | 2020-04-07 | 2021-03-09 | COMP | 2021-03-19 | COMP | 2021-04-10 | COMP | 2021-06-22 | COMP | 2023-08-24 | COMP | Rule 15/16 | 206 | 263 | 9 | 16 | 51 | 547 | 1319
5625 | 2018-05-26 | 2018-06-21 | 2018-10-12 | 2018-10-12 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2019-03-21 | COMP | 2019-04-25 | COMP | Rule 16 | 18 | 80 | 77 | 1 | 32 | 26 | 229
6304 | 2018-05-26 | 2018-08-09 | 2018-11-09 | 2018-11-09 | COMP | 2018-12-06 | COMP | 2018-12-07 | COMP | 2020-07-06 | COMP | 2020-09-29 | COMP | Rule 16 | 52 | 66 | 17 | 2 | 397 | 61 | 590
6625 | 2018-05-26 | 2018-08-31 | 2020-06-22 | 2020-06-22 | COMP | 2020-08-21 | COMP | 2020-08-31 | COMP | 2020-11-17 | COMP | 2021-04-09 | COMP | Rule 15/16 | 68 | 453 | 45 | 7 | 55 | 98 | 721
8364 | 2018-05-26 | 2018-11-28 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-01 | COMP | 2019-03-04 | COMP | 2019-02-28 | COMP | 2019-04-01 | COMP | Rule 16 | 127 | 60 | 5 | 2 | 0 | 21 | 211
5722 | 2018-05-27 | 2018-06-27 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2018-12-24 | COMP | 2019-01-12 | COMP | Rule 16 | 22 | 60 | 8 | 1 | 58 | 13 | 157
5993 | 2018-05-27 | 2018-07-17 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-01 | COMP | 2018-11-13 | COMP | 2018-11-02 | COMP | 2019-05-08 | COMP | Rule 16 | 35 | 74 | 4 | 8 | 0 | 121 | 238
5751 | 2018-05-28 | 2018-06-29 | 2018-08-03 | 2018-08-03 | COMP | 2018-08-20 | COMP | 2018-08-20 | COMP | 2019-03-05 | COMP | 2019-04-04 | COMP | Rule 15/16 | 24 | 25 | 12 | 1 | 134 | 23 | 214
5819 | 2018-05-28 | 2018-07-05 | 2019-03-13 | 2019-03-13 | COMP | 2019-04-11 | COMP | 2019-10-11 | COMP | 2019-10-23 | COMP | 2019-12-03 | COMP | Rule 15/16 | 27 | 172 | 22 | 129 | 9 | 27 | 381
3668 | 2018-05-29 | 2018-06-05 | 2018-07-01 | 2018-07-01 | COMP | 2018-07-10 | COMP | 2018-07-17 | COMP | 2019-04-19 | COMP | 2019-06-06 | COMP | Rule 16 | 6 | 19 | 6 | 6 | 191 | 34 | 258
3712 | 2018-05-29 | 2018-06-15 | 2019-08-09 | 2019-08-09 | COMP | 2020-11-12 | COMP | 2020-12-16 | COMP | 2020-12-16 | COMP | 2021-02-18 | COMP | Rule 15/16 | 14 | 290 | 319 | 23 | 1 | 43 | 685
3720 | 2018-05-29 | 2018-06-19 | 2019-01-24 | 2019-01-24 | COMP | 2019-10-08 | COMP | 2019-10-09 | COMP | 2019-10-10 | COMP | 2019-11-06 | COMP | Rule 15/16 | 16 | 150 | 180 | 2 | 2 | 20 | 365
3734 | 2018-05-29 | 2018-06-19 | 2018-06-29 | 2018-06-29 | COMP | 2018-07-09 | COMP | 2018-07-10 | COMP | 2018-07-19 | COMP | 2020-01-06 | COMP | Rule 16 | 16 | 9 | 6 | 2 | 8 | 367 | 403
3845 | 2018-05-29 | 2018-08-14 | 2018-12-13 | 2018-12-13 | COMP | 2019-07-24 | COMP | 2019-08-08 | COMP | 2020-01-02 | COMP | 2020-01-27 | COMP | Rule 15/16 | 55 | 84 | 154 | 12 | 100 | 17 | 417
5491 | 2018-05-29 | 2018-06-04 | 2019-10-10 | 2019-10-10 | COMP | 2019-10-30 | COMP | 2020-08-31 | COMP | 2020-01-17 | COMP | 2020-10-10 | COMP | Rule 16 | 5 | 342 | 15 | 211 | 0 | 29 | 598
5554 | 2018-05-29 | 2018-06-14 | 2018-10-19 | 2018-10-19 | COMP | 2018-12-07 | COMP | 2018-12-10 | COMP | 2019-01-24 | COMP | 2019-02-08 | COMP | Rule 16 | 13 | 90 | 33 | 2 | 31 | 12 | 176
5604 | 2018-05-29 | 2018-06-19 | 2018-09-14 | 2019-04-24 | COMP | 2020-01-14 | COMP | 2020-01-13 | COMP | 2021-02-27 | INPR | 2020-02-04 | COMP | Rule 16 | 16 | 62 | 182 |  |  |  | 423
5701 | 2018-05-29 | 2018-06-25 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2018-12-18 | COMP | 2019-01-10 | COMP | Rule 16 | 20 | 99 | 25 | 1 | 0 | 15 | 156
5715 | 2018-05-29 | 2018-06-26 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-04-20 | COMP | 2019-05-28 | COMP | Rule 16 | 21 | 115 | 24 | 1 | 68 | 26 | 251
5912 | 2018-05-29 | 2018-07-10 | 2019-02-14 | 2019-02-14 | COMP | 2019-06-06 | COMP | 2022-08-21 | REQD | 2019-06-12 | COMP | 2020-03-04 | COMP | Rule 15/16 | 30 | 151 | 79 |  |  |  | 443
6011 | 2018-05-29 | 2018-07-18 | 2018-10-08 | 2018-10-08 | COMP | 2018-12-05 | COMP | 2019-03-21 | COMP | 2019-03-14 | COMP | 2019-03-31 | COMP | Rule 16 | 36 | 58 | 40 | 73 | 0 | 7 | 210
6020 | 2018-05-29 | 2018-07-19 | 2018-11-21 | 2018-11-21 | COMP | 2019-02-28 | COMP | 2019-03-15 | COMP | 2019-03-06 | COMP | 2019-04-09 | COMP | Rule 16 | 37 | 88 | 66 | 12 | 0 | 18 | 217
6076 | 2018-05-29 | 2018-07-23 | 2018-10-12 | 2018-10-24 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-03-12 | COMP | 2019-05-28 | COMP | Rule 16 | 39 | 59 | 40 | 1 | 54 | 55 | 251
6106 | 2018-05-29 | 2018-07-26 | 2018-10-19 | 2019-02-11 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-01-14 | COMP | 2019-03-22 | COMP | Rule 16 | 42 | 61 | 15 | 1 | 0 | 15 | 205
6247 | 2018-05-29 | 2018-08-06 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-09 | COMP | 2019-02-28 | COMP | 2019-01-26 | COMP | 2019-04-18 | COMP | Rule 16 | 49 | 97 | 11 | 35 | 0 | 36 | 224
6344 | 2018-05-29 | 2018-08-13 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-19 | COMP | 2018-11-28 | COMP | 2019-02-27 | COMP | 2019-03-30 | COMP | Rule 16 | 54 | 29 | 21 | 26 | 62 | 23 | 210
6382 | 2018-05-29 | 2018-08-15 | 2019-01-17 | 2019-01-17 | COMP | 2019-04-03 | COMP | 2019-05-11 | COMP | 2019-06-19 | COMP | 2019-05-19 | COMP | Rule 15/16 | 56 | 106 | 53 | 28 | 27 |  | 245
6503 | 2018-05-29 | 2018-08-22 | 2018-11-28 | 2018-11-28 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-09-04 | COMP | 2019-09-30 | COMP | Rule 16 | 61 | 67 | 119 | 1 | 76 | 19 | 338
6847 | 2018-05-29 | 2018-09-13 | 2018-12-07 | 2021-03-19 | COMP | 2021-06-21 | COMP | 2021-12-17 | COMP | 2022-01-07 | COMP | 2022-03-14 | COMP | Rule 15/16 | 76 | 59 | 66 | 125 | 16 | 45 | 954
7402 | 2018-05-29 | 2018-10-11 | 2018-12-20 | 2018-12-20 | COMP | 2018-12-26 | COMP | 2019-02-06 | COMP | 2019-01-24 | COMP | 2019-03-19 | COMP | Rule 16 | 96 | 48 | 4 | 29 | 0 | 29 | 202
7904 | 2018-05-29 | 2018-11-05 | 2019-03-13 | 2019-03-13 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2020-05-04 | COMP | 2020-06-18 | COMP | Rule 16 | 113 | 86 | 64 | 1 | 226 | 33 | 518
8690 | 2018-05-29 | 2018-12-17 | 2019-02-13 | 2019-02-13 | COMP | 2019-05-14 | COMP | 2019-06-06 | COMP | 2019-06-24 | COMP | 2019-07-18 | COMP | Rule 16 | 140 | 40 | 64 | 17 | 13 | 18 | 287
9068 | 2018-05-29 | 2019-01-15 | 2019-04-03 | 2019-04-03 | COMP | 2019-05-07 | COMP | 2019-05-07 | NOTN | 2019-06-11 | COMP | 2020-12-07 | COMP | Rule 16 | 159 | 55 | 25 |  |  |  | 636
9204 | 2018-05-29 | 2019-01-22 | 2019-03-18 | 2019-09-03 | COMP | 2019-09-12 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-12-09 | COMP | Rule 15/16 | 163 | 39 | 8 | 39 | 1 | 22 | 385
9660 | 2018-05-29 | 2019-02-11 | 2019-05-09 | 2019-05-09 | COMP | 2019-06-24 | COMP | 2019-06-25 | COMP | 2019-10-18 | COMP | 2019-11-18 | COMP | Rule 16 | 177 | 63 | 32 | 2 | 82 | 21 | 372
9724 | 2018-05-29 | 2019-02-12 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-28 | COMP | 2019-04-23 | COMP | 2019-04-18 | COMP | 2019-06-25 | COMP | Rule 16 | 178 | 14 | 19 | 19 | 0 | 45 | 271
9857 | 2018-05-29 | 2019-02-20 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-13 | COMP | 2020-08-26 | COMP | 2020-07-06 | COMP | 2020-09-24 | COMP | Rule 16 | 183 | 63 | 19 | 305 | 0 | 21 | 587
9953 | 2018-05-29 | 2019-02-25 | 2019-04-13 | 2019-04-13 | COMP | 2019-09-27 | COMP | 2019-10-02 | COMP | 2019-10-03 | COMP | 2019-12-17 | COMP | Rule 15/16 | 186 | 35 | 117 | 4 | 2 | 51 | 391
10452 | 2018-05-29 | 2019-03-17 | 2019-06-06 | 2019-09-01 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-02-10 | COMP | 2020-02-28 | COMP | Rule 16 | 200 | 58 | 74 | 1 | 36 | 14 | 440
3742 | 2018-05-30 | 2018-06-25 | 2018-11-08 | 2018-10-18 | COMP | 2018-10-17 | NOTN | 2020-02-24 | COMP | 2020-02-12 | COMP | 2020-06-01 | COMP | Other | 19 | 97 |  | 336 | 0 | 70 | 504
3753 | 2018-05-30 | 2018-06-28 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-22 | COMP | 2019-07-30 | COMP | 2019-08-12 | COMP | 2019-09-02 | COMP | Rule 15/16 | 22 | 166 | 39 | 70 | 10 | 15 | 317
3797 | 2018-05-30 | 2018-07-17 | 2018-10-16 | 2018-10-16 | COMP | 2019-04-26 | COMP | 2019-05-02 | COMP | 2019-11-04 | COMP | 2020-02-05 | COMP | Rule 16 | 34 | 65 | 132 | 5 | 130 | 62 | 423
5606 | 2018-05-30 | 2018-06-19 | 2018-09-12 | 2018-09-12 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-01-16 | COMP | 2019-01-28 | COMP | Rule 16 | 15 | 60 | 35 | 1 | 52 | 8 | 166
5783 | 2018-05-30 | 2018-07-03 | 2018-09-27 | 2018-09-27 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2019-11-15 | COMP | 2019-12-30 | COMP | Rule 16 | 25 | 61 | 27 | 1 | 260 | 29 | 398
5820 | 2018-05-30 | 2018-07-06 | 2018-10-09 | 2018-10-09 | COMP | 2019-01-30 | COMP | 2019-06-26 | COMP | 2019-05-23 | COMP | 2019-07-19 | COMP | Rule 15/16 | 27 | 67 | 76 | 104 | 0 | 17 | 287
6218 | 2018-05-30 | 2018-08-04 | 2018-11-16 | 2018-11-16 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-05-13 | COMP | 2019-06-05 | COMP | Rule 16 | 47 | 73 | 92 | 1 | 30 | 17 | 256
6309 | 2018-05-30 | 2018-08-09 | 2018-09-28 | 2020-03-09 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2021-03-16 | COMP | 2021-04-01 | COMP | Rule 16 | 51 | 36 | 103 | 1 | 156 | 13 | 714
6623 | 2018-05-30 | 2018-08-31 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-19 | COMP | 2019-02-08 | COMP | 2019-07-02 | COMP | 2019-08-07 | COMP | Rule 15/16 | 67 | 23 | 13 | 75 | 101 | 26 | 300
6923 | 2018-05-30 | 2018-09-18 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-06 | COMP | 2019-02-07 | COMP | 2019-02-28 | COMP | 2019-03-14 | COMP | Rule 16 | 78 | 80 | 17 | 2 | 15 | 11 | 198
7429 | 2018-05-30 | 2018-10-12 | 2019-01-30 | 2019-01-30 | COMP | 2019-06-25 | COMP | 2019-11-06 | COMP | 2020-01-27 | COMP | 2020-03-05 | COMP | Rule 16 | 96 | 73 | 103 | 95 | 53 | 28 | 443
7610 | 2018-05-30 | 2018-10-22 | 2019-02-15 | 2019-02-25 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-06-07 | COMP | 2019-06-05 | COMP | Rule 15/16 | 102 | 79 | 11 | 1 | 64 |  | 256
7886 | 2018-05-30 | 2018-11-03 | 2019-01-09 | 2019-06-23 | COMP | 2019-08-29 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-11-04 | COMP | Rule 16 | 111 | 43 | 48 | 11 | 1 | 37 | 362
8220 | 2018-05-30 | 2018-11-19 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-07-02 | COMP | 2019-07-18 | COMP | Rule 16 | 121 | 45 | 9 | 1 | 103 | 12 | 286
8519 | 2018-05-30 | 2018-12-06 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-07-03 | COMP | 2019-08-06 | COMP | Rule 16 | 132 | 82 | 31 | 1 | 34 | 24 | 299
8990 | 2018-05-30 | 2019-01-11 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-01 | COMP | 2019-03-01 | NOTN | 2019-11-04 | COMP | 2019-11-11 | COMP | Rule 16 | 156 | 10 | 25 |  |  |  | 366
9662 | 2018-05-30 | 2019-02-11 | 2019-04-18 | 2019-04-18 | COMP | 2019-04-25 | COMP | 2019-04-29 | COMP | 2019-10-21 | INPR | 2019-05-06 | COMP | Rule 16 | 176 | 48 | 6 | 3 |  |  | 235
10012 | 2018-05-30 | 2019-02-27 | 2019-06-05 | 2020-08-24 | COMP | 2020-09-11 | COMP | 2020-11-03 | COMP | 2020-10-20 | COMP | 2020-12-13 | COMP | Rule 16 | 187 | 70 | 14 | 38 | 0 | 26 | 639
10130 | 2018-05-30 | 2019-03-04 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2020-11-21 | INPR | 2019-11-16 | COMP | Rule 16 | 190 | 101 | 28 | 1 |  |  | 370
10171 | 2018-05-30 | 2019-03-05 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-25 | COMP | 2019-07-12 | COMP | 2019-08-29 | COMP | 2019-09-18 | COMP | Rule 16 | 191 | 73 | 8 | 13 | 35 | 14 | 329
40180 | 2018-05-30 | 2022-12-09 | 2023-07-21 | 2023-07-21 | COMP | 2023-08-15 | NOTN | 2023-09-18 | COMP | 2023-09-05 | COMP | 2023-12-04 | COMP | Other | 1140 | 154 |  | 41 | 0 | 53 | 1385
3792 | 2018-05-31 | 2018-07-14 | 2018-10-29 | 2018-10-29 | COMP | 2019-08-21 | COMP | 2019-09-27 | COMP | 2019-12-18 | COMP | 2020-01-13 | COMP | Rule 16 | 31 | 75 | 204 | 27 | 56 | 17 | 406
4005 | 2018-05-31 | 2018-11-16 | 2019-05-17 | 2019-05-17 | COMP | 2020-04-06 | COMP | 2020-06-04 | COMP | 2020-04-07 | COMP | 2020-08-03 | COMP | Rule 16 | 119 | 125 | 222 | 43 | 0 | 43 | 548
5437 | 2018-05-31 | 2018-05-31 | 2019-10-01 | 2022-01-04 | COMP | 2022-03-04 | COMP | 2019-11-08 | COMP | 2022-05-10 | COMP | 2022-09-01 | COMP | Rule 15/16 | 1 | 337 | 42 |  | 629 | 80 | 1072
5449 | 2018-05-31 | 2018-06-02 | 2018-08-21 | 2018-08-21 | COMP | 2018-08-21 | NOTN | 2020-11-18 | COMP | 2021-06-16 | COMP | 2021-07-05 | COMP | Other | 2 | 56 |  | 566 | 144 | 13 | 778
5453 | 2018-05-31 | 2018-05-31 | 2018-10-01 | 2018-10-01 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-05-06 | COMP | 2019-06-25 | COMP | Rule 16 | 1 | 86 | 41 | 1 | 109 | 36 | 269
5702 | 2018-05-31 | 2018-06-26 | 2018-11-29 | 2019-01-09 | COMP | 2019-01-18 | COMP | 2019-02-21 | COMP | 2019-04-09 | COMP | 2019-04-29 | COMP | Rule 16 | 19 | 108 | 8 | 23 | 34 | 15 | 229
5849 | 2018-05-31 | 2018-07-07 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-01-15 | COMP | 2019-04-16 | COMP | Rule 16 | 26 | 88 | 20 | 1 | 25 | 64 | 220
5937 | 2018-05-31 | 2018-07-12 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-19 | COMP | 2019-01-02 | COMP | 2018-12-31 | COMP | 2019-03-12 | COMP | Rule 16 | 30 | 101 | 11 | 9 | 0 | 48 | 195
5938 | 2018-05-31 | 2018-07-12 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-28 | COMP | 2019-02-13 | COMP | 2018-12-31 | COMP | 2019-03-20 | COMP | Rule 16 | 30 | 101 | 17 | 32 | 0 | 25 | 201
5956 | 2018-05-31 | 2018-07-16 | 2018-08-01 | 2018-08-01 | COMP | 2018-08-08 | COMP | 2018-08-08 | COMP | 2018-08-08 | COMP | 2019-03-13 | COMP | Rule 16 | 32 | 13 | 6 | 1 | 1 | 148 | 196
6023 | 2018-05-31 | 2018-07-20 | 2019-03-15 | 2019-04-25 | COMP | 2019-05-07 | COMP | 2019-05-10 | COMP | 2019-06-11 | COMP | 2019-07-03 | COMP | Rule 15/16 | 36 | 163 | 9 | 4 | 22 | 17 | 275
6138 | 2018-05-31 | 2018-07-30 | 2019-03-27 | 2019-03-27 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2019-07-26 | COMP | 2019-07-31 | COMP | Rule 15/16 | 42 | 165 | 52 | 1 | 35 | 4 | 294
6541 | 2018-05-31 | 2018-08-27 | 2018-12-19 | 2020-12-14 | COMP | 2021-02-24 | COMP | 2021-03-09 | COMP | 2021-02-22 | COMP | 2021-04-07 | COMP | Other | 62 | 79 | 49 | 10 | 0 | 22 | 717
6766 | 2018-05-31 | 2018-09-11 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-03 | NOTN | 2019-01-03 | COMP | 2019-02-05 | COMP | 2019-03-06 | COMP | Other | 72 | 72 |  | 7 | 23 | 21 | 191
6979 | 2018-05-31 | 2018-09-20 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-04 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-01-03 | COMP | Rule 16 | 79 | 17 | 35 | 7 | 1 | 15 | 149
7198 | 2018-05-31 | 2018-10-02 | 2018-12-18 | 2018-12-18 | COMP | 2019-02-01 | COMP | 2019-02-07 | COMP | 2019-09-19 | COMP | 2019-10-25 | COMP | Rule 16 | 87 | 53 | 31 | 5 | 157 | 27 | 355
9202 | 2018-05-31 | 2019-01-22 | 2019-05-03 | 2019-05-03 | COMP | 2019-06-10 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-09-18 | COMP | Rule 16 | 161 | 73 | 26 | 47 | 1 | 25 | 328
9373 | 2018-05-31 | 2019-02-01 | 2019-07-01 | 2019-10-29 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-02-25 | COMP | 2020-05-20 | COMP | Rule 15/16 | 169 | 105 | 25 | 1 | 55 | 62 | 496
10321 | 2018-05-31 | 2019-03-11 | 2019-06-13 | 2019-06-13 | COMP | 2019-06-25 | COMP | 2019-08-15 | COMP | 2019-10-11 | COMP | 2019-10-15 | COMP | Rule 16 | 194 | 68 | 9 | 37 | 41 | 3 | 347
12153 | 2018-05-31 | 2019-05-24 | 2019-10-07 | 2019-10-07 | COMP | 2020-07-21 | COMP | 2020-06-25 | COMP | 2020-06-01 | COMP | 2020-07-21 | COMP | Rule 16 | 248 | 94 | 199 |  | 0 | 19 | 539
12661 | 2018-05-31 | 2019-06-17 | 2019-09-05 | 2020-02-06 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-04-01 | COMP | 2020-04-15 | COMP | Rule 16 | 263 | 57 | 13 | 1 | 27 | 11 | 471
12671 | 2018-05-31 | 2019-06-18 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-12 | COMP | 2019-07-12 | INPR | 2019-08-15 | COMP | 2019-08-15 | COMP | Rule 16 | 264 | 9 | 10 |  |  |  | 305
17423 | 2018-05-31 | 2020-02-13 | 2020-04-03 | 2020-04-03 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-10-12 | COMP | 2020-11-20 | COMP | Rule 16 | 428 | 36 | 71 | 1 | 65 | 29 | 625
3802 | 2018-06-01 | 2018-07-19 | 2018-09-17 | 2018-09-17 | COMP | 2018-10-30 | NOTN | 2018-12-13 | COMP | 2018-12-17 | COMP | 2019-01-31 | COMP | Rule 16 | 34 | 42 |  | 61 | 3 | 31 | 167
3839 | 2018-06-01 | 2018-08-10 | 2018-11-18 | 2018-11-18 | COMP | 2019-02-28 | COMP | 2019-05-16 | COMP | 2019-06-12 | COMP | 2019-08-30 | COMP | Rule 16 | 50 | 69 | 68 | 56 | 19 | 57 | 315
4028 | 2018-06-01 | 2018-12-10 | 2019-05-14 | 2019-05-14 | COMP | 2019-10-11 | COMP | 2020-06-22 | COMP | 2020-08-21 | COMP | 2020-11-06 | COMP | Rule 16 | 132 | 108 | 106 | 174 | 45 | 55 | 615
4037 | 2018-06-01 | 2018-12-26 | 2019-10-08 | 2019-10-08 | COMP | 2019-10-29 | COMP | 2021-04-21 | COMP | 2021-02-09 | COMP | 2021-06-15 | COMP | Rule 16 | 143 | 199 | 16 | 371 | 0 | 39 | 764
5568 | 2018-06-01 | 2018-06-14 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-01 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2019-12-10 | COMP | Rule 15/16 | 10 | 85 | 15 | 249 | 1 | 28 | 383
5583 | 2018-06-01 | 2018-06-15 | 2018-11-05 | 2018-11-05 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-07-08 | COMP | 2019-08-19 | COMP | Other | 11 | 100 | 64 | 1 | 104 | 31 | 306
5893 | 2018-06-01 | 2018-07-09 | 2018-07-13 | 2018-07-13 | COMP | 2018-07-20 | COMP | 2018-07-20 | INPR | 2019-10-21 | REQD | 2019-03-13 | COMP | Rule 16 | 26 | 5 | 6 |  |  |  | 195
5919 | 2018-06-01 | 2018-07-11 | 2018-12-06 | 2018-12-06 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-04-22 | COMP | 2019-07-01 | COMP | Rule 15/16 | 28 | 103 | 109 | 1 | 0 | 35 | 272
5920 | 2018-06-01 | 2018-07-11 | 2018-11-11 | 2019-05-28 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-07-08 | COMP | 2019-09-18 | COMP | Rule 16 | 28 | 87 | 71 | 1 | 0 | 10 | 327
6043 | 2018-06-01 | 2018-07-21 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-10 | COMP | 2019-03-04 | COMP | 2019-02-26 | COMP | 2019-04-17 | COMP | Rule 16 | 35 | 75 | 23 | 57 | 0 | 33 | 220
6116 | 2018-06-01 | 2018-07-27 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-26 | COMP | 2019-01-23 | COMP | 2019-07-21 | INPR | 2019-03-01 | COMP | Rule 16 | 40 | 78 | 27 | 19 |  |  | 187
6764 | 2018-06-01 | 2018-09-11 | 2018-11-28 | 2022-12-15 | COMP | 2023-03-10 | COMP | 2023-05-30 | COMP | 2021-09-27 | COMP | 2023-07-11 | COMP | Rule 15/16 | 71 | 54 | 58 | 57 | 0 | 29 | 1283
6797 | 2018-06-01 | 2018-09-11 | 2018-12-20 | 2018-12-20 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-11-26 | COMP | 2020-01-02 | COMP | Rule 16 | 71 | 70 | 15 | 1 | 222 | 24 | 398
7044 | 2018-06-01 | 2018-09-24 | 2019-01-25 | 2019-01-25 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-09-24 | COMP | 2019-11-08 | COMP | Rule 16 | 80 | 84 | 155 | 1 | 15 | 34 | 364
8235 | 2018-06-01 | 2018-11-20 | 2019-03-13 | 2019-03-29 | COMP | 2019-04-09 | COMP | 2019-06-24 | COMP | 2019-07-03 | COMP | 2019-08-02 | COMP | Rule 16 | 120 | 76 | 8 | 54 | 8 | 22 | 295
9276 | 2018-06-01 | 2019-01-26 | 2019-02-22 | 2019-02-22 | COMP | 2019-04-02 | COMP | 2019-04-22 | COMP | 2019-08-12 | COMP | 2019-09-06 | COMP | Rule 16 | 163 | 19 | 28 | 15 | 79 | 19 | 319
9524 | 2018-06-01 | 2019-02-06 | 2019-07-01 | 2019-10-27 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-02-12 | COMP | 2020-05-20 | COMP | Rule 16 | 171 | 102 | 26 | 1 | 47 | 70 | 495
9898 | 2018-06-01 | 2019-02-21 | 2019-09-24 | 2019-09-24 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP |  | INPR | 2023-11-11 | COMP | Rule 15/16 | 181 | 151 | 163 | 1 |  |  | 1369
10481 | 2018-06-01 | 2019-03-18 | 2019-04-11 | 2019-09-19 | COMP | 2019-10-18 | COMP | 2019-10-25 | COMP | 2021-01-29 | COMP | 2021-04-05 | COMP | Rule 16 | 198 | 19 | 22 | 6 | 316 | 46 | 714
11022 | 2018-06-01 | 2019-04-09 | 2019-06-29 | 2019-06-29 | COMP | 2019-08-01 | COMP | 2019-08-02 | COMP | 2019-08-01 | COMP | 2019-10-07 | COMP | Rule 16 | 214 | 58 | 23 | 2 | 0 | 46 | 340
12877 | 2018-06-01 | 2019-06-26 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-22 | COMP | 2019-12-02 | COMP | 2019-12-04 | COMP | 2020-02-18 | COMP | Rule 16 | 269 | 77 | 7 | 27 | 3 | 51 | 429
3829 | 2018-06-02 | 2018-08-03 | 2019-03-05 | 2019-03-05 | COMP | 2018-12-11 | NOTN | 2019-03-06 | COMP | 2019-03-13 | COMP | 2019-04-16 | COMP | Other | 44 | 145 |  | 2 | 6 | 25 | 218
3884 | 2018-06-02 | 2018-09-14 | 2018-12-04 | 2018-12-04 | COMP | 2019-02-19 | COMP | 2019-10-04 | COMP | 2019-09-05 | COMP | 2019-10-09 | COMP | Rule 16 | 73 | 55 | 52 | 161 | 0 | 4 | 341
7534 | 2018-06-02 | 2018-10-18 | 2018-12-04 | 2018-12-04 | COMP | 2019-01-10 | COMP | 2019-05-11 | COMP | 2019-05-08 | COMP | 2019-05-21 | COMP | Rule 16 | 97 | 31 | 26 | 85 | 0 | 7 | 243
5680 | 2018-06-03 | 2018-06-26 | 2018-09-03 | 2018-09-03 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-07-21 | INPR | 2019-04-25 | COMP | Rule 16 | 17 | 48 | 154 | 1 |  |  | 225
7842 | 2018-06-03 | 2018-11-02 | 2019-01-11 | 2019-01-11 | COMP | 2019-02-05 | COMP | 2019-04-10 | COMP | 2019-04-15 | COMP | 2019-06-05 | COMP | Rule 16 | 108 | 46 | 17 | 46 | 4 | 37 | 253
3768 | 2018-06-04 | 2018-07-06 | 2018-08-24 | 2018-08-24 | COMP | 2018-12-14 | NOTN | 2018-12-14 | COMP | 2018-12-14 | COMP | 2019-02-07 | COMP | Other | 24 | 36 |  | 77 | 1 | 37 | 171
3844 | 2018-06-04 | 2018-08-14 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-12 | COMP | 2019-08-26 | COMP | 2020-01-21 | COMP | 2020-04-02 | COMP | Rule 15/16 | 51 | 112 | 13 | 137 | 100 | 52 | 460
5548 | 2018-06-04 | 2018-06-12 | 2018-08-20 | 2018-08-20 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-12 | COMP | 2019-11-19 | COMP | Rule 16 | 7 | 49 | 297 | 1 | 14 | 6 | 369
5556 | 2018-06-04 | 2018-06-13 | 2018-06-30 | 2018-06-30 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-02-28 | COMP | 2019-04-09 | COMP | Rule 16 | 8 | 13 | 102 | 1 | 64 | 29 | 213
5633 | 2018-06-04 | 2018-06-23 | 2019-01-14 | 2019-01-14 | COMP | 2019-01-07 | NOTN | 2019-01-14 | COMP | 2019-01-31 | COMP | 2019-04-30 | COMP | Other | 15 | 139 |  | 1 | 13 | 63 | 228
5728 | 2018-06-04 | 2018-06-27 | 2018-11-11 | 2019-12-19 | COMP | 2020-03-25 | COMP | 2020-05-27 | COMP | 2020-09-08 | COMP | 2020-10-23 | COMP | Rule 16 | 18 | 96 | 66 | 45 | 74 | 34 | 604
5836 | 2018-06-04 | 2018-07-07 | 2018-07-13 | 2018-07-26 | COMP | 2018-08-10 | COMP | 2019-02-07 | COMP | 2018-10-12 | COMP | 2019-08-06 | COMP | Rule 16 | 24 | 5 | 12 | 123 | 0 | 126 | 296
5879 | 2018-06-04 | 2018-07-09 | 2018-09-15 | 2018-09-15 | COMP | 2018-09-21 | COMP | 2019-07-08 | COMP | 2022-01-30 | INPR | 2020-08-12 | COMP | Rule 16 | 25 | 49 | 5 | 198 |  |  | 553
5924 | 2018-06-04 | 2018-07-11 | 2018-10-15 | 2018-10-15 | COMP | 2018-12-03 | COMP | 2019-01-02 | COMP | 2019-02-06 | COMP | 2019-05-10 | COMP | Rule 16 | 27 | 68 | 33 | 21 | 25 | 67 | 236
5969 | 2018-06-04 | 2018-07-16 | 2018-11-19 | 2018-11-19 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2023-02-28 | COMP | 2023-03-09 | COMP | Rule 16 | 30 | 89 | 196 | 1 | 878 | 8 | 1197
5981 | 2018-06-04 | 2018-07-16 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-04 | COMP | 2018-12-10 | COMP | 2020-09-26 | INPR | 2019-01-02 | COMP | Rule 15/16 | 30 | 84 | 14 | 5 |  |  | 146
6038 | 2018-06-04 | 2018-07-20 | 2018-10-11 | 2018-10-11 | COMP | 2018-10-22 | COMP | 2018-10-22 | COMP | 2019-02-26 | COMP | 2019-04-16 | COMP | Rule 16 | 34 | 59 | 8 | 1 | 85 | 36 | 218
6040 | 2018-06-04 | 2018-07-20 | 2018-10-04 | 2018-10-04 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-03 | COMP | 2019-06-03 | COMP | Rule 15/16 | 34 | 54 | 108 | 1 | 16 | 43 | 251
6087 | 2018-06-04 | 2018-07-26 | 2018-10-12 | 2018-11-10 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-03-17 | COMP | 2019-05-13 | COMP | Rule 15/16 | 38 | 56 | 47 | 1 | 37 | 41 | 237
6152 | 2018-06-04 | 2018-07-31 | 2018-09-20 | 2019-02-12 | COMP | 2019-02-26 | COMP | 2018-11-06 | COMP | 2018-11-13 | COMP | 2019-04-09 | COMP | Rule 16 | 41 | 37 | 10 |  | 5 | 100 | 213
6175 | 2018-06-04 | 2018-08-01 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-17 | COMP | 2019-09-18 | COMP | 2019-09-18 | COMP | 2019-10-01 | COMP | Rule 16 | 42 | 276 | 9 | 2 | 1 | 10 | 335
6329 | 2018-06-04 | 2018-08-11 | 2018-11-16 | 2018-11-16 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-03-12 | COMP | 2019-04-19 | COMP | Rule 15/16 | 49 | 68 | 38 | 1 | 40 | 29 | 221
6480 | 2018-06-04 | 2018-08-21 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-25 | COMP | 2019-03-19 | COMP | 2019-04-03 | COMP | 2019-05-06 | COMP | Rule 16 | 56 | 68 | 60 | 17 | 12 | 24 | 232
6483 | 2018-06-04 | 2018-08-21 | 2018-10-12 | 2018-10-18 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-02-12 | COMP | 2019-03-20 | COMP | Rule 16 | 56 | 38 | 11 | 1 | 68 | 26 | 199
6501 | 2018-06-04 | 2018-08-22 | 2018-10-16 | 2018-10-16 | COMP | 2018-10-22 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-01-09 | COMP | Rule 15/16 | 57 | 39 | 5 | 25 | 1 | 29 | 151
6639 | 2018-06-04 | 2018-09-01 | 2019-01-22 | 2019-01-22 | COMP | 2019-03-19 | COMP | 2019-07-17 | COMP | 2019-07-30 | COMP | 2019-08-19 | COMP | Rule 16 | 64 | 95 | 40 | 85 | 10 | 15 | 305
6642 | 2018-06-04 | 2018-09-04 | 2019-06-14 | 2019-10-30 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-06-09 | COMP | 2020-07-23 | COMP | Rule 15/16 | 65 | 196 | 22 | 1 | 131 | 33 | 539
6692 | 2018-06-04 | 2018-09-07 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-03-13 | COMP | 2019-04-15 | COMP | Rule 16 | 68 | 56 | 59 | 1 | 14 | 24 | 217
6832 | 2018-06-04 | 2018-09-13 | 2018-10-21 | 2018-10-21 | COMP | 2018-11-09 | COMP | 2019-07-08 | COMP | 2019-11-05 | COMP | 2020-01-07 | COMP | Rule 15/16 | 72 | 27 | 15 | 163 | 86 | 41 | 400
6982 | 2018-06-04 | 2018-09-20 | 2019-05-28 | 2019-08-02 | COMP | 2019-08-30 | COMP | 2019-09-20 | COMP | 2019-10-22 | COMP | 2019-11-07 | COMP | Rule 15/16 | 77 | 171 | 21 | 15 | 23 | 13 | 362
7905 | 2018-06-04 | 2018-11-05 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-04-11 | COMP | Rule 16 | 109 | 53 | 14 | 1 | 1 | 42 | 215
8141 | 2018-06-04 | 2018-11-16 | 2019-07-15 | 2019-07-15 | COMP | 2019-11-12 | COMP | 2019-11-14 | COMP | 2020-04-08 | COMP | 2020-06-12 | COMP | Rule 15/16 | 117 | 164 | 85 | 3 | 99 | 47 | 510
8232 | 2018-06-04 | 2018-11-20 | 2019-07-24 | 2019-07-24 | COMP | 2020-09-10 | COMP | 2020-09-11 | COMP | 2020-09-16 | COMP | 2020-12-16 | COMP | Rule 15/16 | 119 | 169 | 287 | 2 | 4 | 63 | 639
8256 | 2018-06-04 | 2018-11-25 | 2019-07-15 | 2021-02-17 | COMP | 2021-04-27 | COMP | 2022-02-05 | COMP | 2022-01-28 | COMP | 2022-03-17 | COMP | Rule 15/16 | 120 | 160 | 50 | 197 | 0 | 28 | 953
9602 | 2018-06-04 | 2019-02-08 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-13 | COMP | 2019-05-07 | COMP | 2019-05-14 | COMP | 2019-05-13 | COMP | Rule 16 | 172 | 16 | 8 | 40 | 6 |  | 237
9778 | 2018-06-04 | 2019-02-15 | 2019-04-09 | 2019-04-13 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-09-05 | COMP | 2019-12-19 | COMP | Rule 16 | 177 | 37 | 22 | 1 | 80 | 73 | 389
11728 | 2018-06-04 | 2019-05-08 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-11-05 | COMP | 2019-12-09 | COMP | Rule 16 | 234 | 79 | 23 | 1 | 27 | 22 | 381
14632 | 2018-06-04 | 2019-09-20 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-31 | COMP | 2020-01-22 | COMP | 2021-11-09 | COMP | 2022-01-13 | COMP | Rule 16 | 328 | 37 | 33 | 15 | 457 | 45 | 910
15665 | 2018-06-04 | 2019-11-14 | 2020-07-13 | 2020-07-13 | COMP | 2020-09-28 | COMP | 2020-10-20 | COMP | 2020-10-29 | COMP | 2021-01-07 | COMP | Rule 15/16 | 366 | 166 | 55 | 17 | 8 | 46 | 653
3697 | 2018-06-05 | 2018-06-12 | 2018-07-23 | 2018-07-23 | COMP | 2018-08-14 | COMP | 2018-08-14 | COMP | 2019-08-15 | COMP | 2019-08-19 | COMP | Rule 16 | 6 | 29 | 17 | 1 | 253 | 3 | 304
3698 | 2018-06-05 | 2018-06-12 | 2018-08-16 | 2018-08-16 | COMP | 2018-09-04 | COMP | 2018-08-31 | COMP | 2019-02-08 | COMP | 2019-03-05 | COMP | Rule 16 | 6 | 47 | 13 |  | 109 | 17 | 187
3699 | 2018-06-05 | 2018-06-12 | 2018-08-16 | 2018-08-16 | COMP | 2018-09-04 | COMP | 2018-08-31 | COMP | 2019-05-14 | COMP | 2019-04-25 | COMP | Rule 16 | 6 | 47 | 13 |  | 175 |  | 224
4074 | 2018-06-05 | 2019-01-09 | 2019-10-28 | 2019-10-28 | COMP | 2020-01-27 | COMP | 2020-03-20 | COMP | 2022-09-21 | COMP | 2022-06-07 | COMP | Rule 16 | 150 | 204 | 60 | 39 | 633 |  | 1009
5796 | 2018-06-05 | 2018-07-03 | 2019-05-14 | 2022-06-07 | COMP | 2022-08-11 | COMP | 2022-08-11 | COMP | 2022-10-25 | COMP | 2022-11-10 | COMP | Rule 15/16 | 21 | 217 | 46 | 1 | 53 | 13 | 1118
5929 | 2018-06-05 | 2018-07-12 | 2018-09-01 | 2018-09-01 | COMP | 2019-02-06 | COMP | 2019-05-01 | COMP | 2019-05-03 | COMP | 2019-05-29 | COMP | Rule 16 | 27 | 37 | 106 | 60 | 3 | 18 | 247
6267 | 2018-06-05 | 2018-08-07 | 2019-01-08 | 2019-01-08 | COMP | 2019-02-26 | COMP | 2019-04-09 | COMP | 2019-06-18 | COMP | 2019-06-16 | COMP | Rule 16 | 45 | 105 | 34 | 31 | 50 |  | 259
6302 | 2018-06-05 | 2018-08-09 | 2018-12-19 | 2019-03-06 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-05-17 | COMP | 2019-06-19 | COMP | Rule 15/16 | 47 | 91 | 23 | 1 | 31 | 23 | 262
6489 | 2018-06-05 | 2018-08-22 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-18 | COMP | 2019-02-22 | COMP | 2019-04-16 | COMP | 2019-05-26 | COMP | Rule 16 | 56 | 97 | 5 | 24 | 38 | 29 | 245
6550 | 2018-06-05 | 2018-08-27 | 2018-11-10 | 2018-11-10 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2021-01-21 | COMP | 2021-02-18 | COMP | Rule 16 | 59 | 54 | 92 | 1 | 458 | 20 | 680
6553 | 2018-06-05 | 2018-08-28 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-25 | COMP | 2019-04-25 | COMP | 2019-05-13 | COMP | 2019-06-12 | COMP | Rule 15/16 | 60 | 63 | 60 | 44 | 13 | 22 | 257
6683 | 2018-06-05 | 2018-09-06 | 2019-02-02 | 2019-02-02 | COMP | 2019-05-15 | COMP | 2019-05-15 | COMP | 2021-05-17 | COMP | 2021-06-28 | COMP | Rule 15/16 | 66 | 101 | 72 | 1 | 505 | 30 | 771
6719 | 2018-06-05 | 2018-09-10 | 2018-10-09 | 2018-10-09 | COMP | 2018-10-17 | COMP | 2018-10-17 | COMP | 2018-11-13 | COMP | 2019-01-24 | COMP | Rule 16 | 68 | 22 | 7 | 1 | 19 | 48 | 160
6859 | 2018-06-05 | 2018-09-14 | 2018-10-28 | 2018-10-28 | COMP | 2018-12-07 | COMP | 2018-12-19 | COMP | 2019-02-12 | COMP | 2019-02-23 | COMP | Rule 16 | 72 | 31 | 27 | 9 | 37 | 8 | 180
6932 | 2018-06-05 | 2018-09-18 | 2019-01-23 | 2019-01-23 | COMP | 2020-01-28 | COMP | 2019-08-02 | COMP | 2019-10-12 | COMP | 2020-01-13 | COMP | Rule 16 | 74 | 86 | 255 |  | 50 | 61 | 403
7061 | 2018-06-05 | 2018-09-25 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-01-10 | COMP | 2019-04-01 | COMP | Rule 16 | 79 | 22 | 18 | 1 | 35 | 56 | 206
7119 | 2018-06-05 | 2018-09-28 | 2019-01-31 | 2019-01-31 | COMP | 2019-10-09 | COMP | 2020-08-05 | COMP | 2021-04-20 | COMP | 2021-06-23 | COMP | Rule 16 | 82 | 84 | 176 | 208 | 177 | 46 | 768
7129 | 2018-06-05 | 2018-09-28 | 2019-03-11 | 2019-11-18 | COMP | 2019-11-21 | COMP | 2019-11-22 | COMP | 2021-02-27 | INPR | 2020-01-13 | COMP | Rule 15/16 | 82 | 110 | 4 | 2 |  |  | 403
7304 | 2018-06-05 | 2018-10-06 | 2018-12-31 | 2018-12-31 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2020-01-07 | COMP | 2020-01-17 | COMP | Rule 16 | 87 | 57 | 49 | 1 | 208 | 9 | 407
7305 | 2018-06-05 | 2018-10-06 | 2018-12-15 | 2018-12-15 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-10-18 | COMP | 2019-12-09 | COMP | Rule 16 | 87 | 47 | 58 | 1 | 156 | 34 | 380
7829 | 2018-06-05 | 2018-11-01 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-03 | COMP | 2019-04-11 | COMP | 2019-04-03 | COMP | 2019-06-18 | COMP | Rule 16 | 106 | 74 | 30 | 7 | 0 | 48 | 261
7901 | 2018-06-05 | 2018-11-06 | 2019-01-16 | 2019-01-16 | COMP | 2019-01-22 | COMP | 2019-03-22 | COMP | 2019-07-21 | INPR | 2019-03-29 | COMP | Rule 16 | 109 | 47 | 4 | 43 |  |  | 205
8263 | 2018-06-05 | 2018-11-20 | 2019-01-16 | 2019-01-16 | COMP | 2019-02-25 | COMP | 2019-04-10 | COMP | 2019-06-08 | COMP | 2019-07-15 | COMP | Rule 16 | 118 | 38 | 27 | 33 | 42 | 25 | 279
8398 | 2018-06-05 | 2018-11-29 | 2019-02-12 | 2019-02-12 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-11-06 | COMP | 2019-12-04 | COMP | Rule 16 | 123 | 51 | 102 | 1 | 87 | 18 | 377
9617 | 2018-06-05 | 2019-02-08 | 2019-04-14 | 2019-06-06 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2020-10-22 | COMP | 2020-11-25 | COMP | Rule 16 | 171 | 45 | 24 | 1 | 327 | 24 | 625
10151 | 2018-06-05 | 2019-03-05 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-17 | COMP | 2020-01-19 | REQD | 2020-01-19 | REQD | 2019-10-01 | COMP | Rule 16 | 187 | 73 | 23 |  |  |  | 334
10337 | 2018-06-05 | 2019-03-12 | 2019-05-02 | 2019-05-30 | COMP | 2019-06-10 | COMP | 2019-06-24 | COMP | 2019-12-29 | INPR | 2019-08-05 | COMP | Rule 16 | 192 | 38 | 8 | 11 |  |  | 294
12390 | 2018-06-05 | 2019-06-05 | 2019-11-12 | 2019-11-12 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-03-16 | COMP | 2020-05-11 | COMP | Rule 16 | 252 | 112 | 56 | 1 | 29 | 41 | 486
12701 | 2018-06-05 | 2019-06-18 | 2019-10-07 | 2019-10-07 | COMP | 2020-06-02 | COMP | 2021-01-28 | COMP | 2021-01-28 | COMP | 2021-03-19 | COMP | Rule 15/16 | 261 | 78 | 164 | 166 | 1 | 36 | 701
13110 | 2018-06-05 | 2019-07-11 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2019-09-19 | COMP | 2019-11-19 | COMP | Rule 15/16 | 277 | 13 | 43 | 1 | 0 | 38 | 368
14952 | 2018-06-05 | 2019-10-06 | 2019-12-08 | 2019-12-08 | COMP | 2020-02-10 | COMP | 2020-07-18 | COMP | 2020-09-24 | COMP | 2021-03-18 | COMP | Rule 15/16 | 337 | 42 | 43 | 113 | 48 | 119 | 700
15235 | 2018-06-05 | 2019-10-22 | 2020-01-22 | 2020-01-22 | COMP | 2020-01-28 | COMP | 2020-02-25 | COMP | 2020-05-14 | COMP | 2020-07-28 | COMP | Rule 16 | 349 | 61 | 5 | 20 | 58 | 53 | 541
3726 | 2018-06-06 | 2018-06-19 | 2019-05-12 | 2019-05-12 | COMP | 2019-08-14 | COMP | 2020-12-24 | COMP | 2020-11-24 | COMP | 2021-01-22 | COMP | Rule 16 | 10 | 225 | 66 | 344 | 0 | 19 | 661
5648 | 2018-06-06 | 2018-06-22 | 2018-08-01 | 2018-08-01 | COMP | 2018-11-13 | COMP | 2019-02-08 | COMP | 2021-07-01 | COMP | 2021-07-13 | COMP | Rule 16 | 13 | 28 | 73 | 59 | 604 | 8 | 780
5654 | 2018-06-06 | 2018-06-24 | 2018-10-27 | 2020-08-11 | COMP | 2019-04-24 | COMP | 2019-05-07 | COMP | 2019-05-28 | COMP | 2019-09-21 | COMP | Rule 16 | 13 | 88 |  | 10 | 15 | 82 | 326
5808 | 2018-06-06 | 2018-07-05 | 2018-10-24 | 2018-11-10 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-04-25 | COMP | 2019-06-03 | COMP | Rule 16 | 21 | 79 | 15 | 1 | 98 | 27 | 249
5908 | 2018-06-06 | 2018-07-10 | 2018-12-04 | 2018-12-04 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-11-12 | COMP | 2021-06-15 | COMP | Rule 16 | 24 | 102 | 147 | 1 | 92 | 400 | 761
5964 | 2018-06-06 | 2018-07-17 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-08 | COMP | 2018-10-08 | COMP | 2019-04-06 | COMP | 2019-05-01 | COMP | Rule 16 | 29 | 47 | 13 | 1 | 123 | 18 | 227
5986 | 2018-06-06 | 2018-07-17 | 2018-10-04 | 2018-10-04 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2018-10-31 | COMP | 2019-01-04 | COMP | Rule 16 | 29 | 57 | 17 | 1 | 4 | 43 | 146
6044 | 2018-06-06 | 2018-07-21 | 2018-10-10 | 2018-10-10 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-04-27 | COMP | 2019-05-31 | COMP | Rule 16 | 32 | 57 | 20 | 1 | 117 | 24 | 248
6108 | 2018-06-06 | 2018-07-26 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-10 | COMP | 2019-01-07 | COMP | 2019-01-16 | COMP | 2019-03-01 | COMP | Rule 16 | 36 | 49 | 6 | 59 | 8 | 31 | 184
6159 | 2018-06-06 | 2018-07-31 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-30 | COMP | 2019-07-17 | COMP |  | INPR | 2019-08-16 | COMP | Rule 15/16 | 39 | 172 | 38 | 34 |  |  | 302
6488 | 2018-06-06 | 2018-08-22 | 2018-09-19 | 2018-09-19 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-09-05 | COMP | 2019-09-20 | COMP | Rule 15/16 | 55 | 20 | 235 | 1 | 8 | 12 | 326
6676 | 2018-06-06 | 2018-09-06 | 2018-10-03 | 2018-10-30 | COMP | 2018-11-19 | COMP | 2018-11-19 | COMP | 2019-09-01 | INPR | 2019-05-10 | COMP | Rule 16 | 65 | 20 | 14 | 1 |  |  | 234
6686 | 2018-06-06 | 2018-09-06 | 2018-10-29 | 2019-02-21 | COMP | 2019-03-13 | COMP | 2018-12-24 | COMP | 2019-03-13 | COMP | 2019-04-09 | COMP | Rule 16 | 65 | 38 | 15 |  | 54 | 20 | 211
6744 | 2018-06-06 | 2018-09-10 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-01-23 | COMP | Rule 16 | 67 | 48 | 14 | 1 | 1 | 32 | 158
6831 | 2018-06-06 | 2018-09-13 | 2018-10-19 | 2018-10-19 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-02-08 | COMP | 2019-02-25 | COMP | Rule 16 | 70 | 27 | 70 | 1 | 6 | 11 | 180
6883 | 2018-06-06 | 2018-09-15 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-07-01 | COMP | Rule 15/16 | 71 | 50 | 51 | 1 | 1 | 99 | 269
6884 | 2018-06-06 | 2018-09-15 | 2018-12-07 | 2018-12-07 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-04-24 | COMP | Rule 16 | 71 | 57 | 44 | 1 | 1 | 52 | 222
7156 | 2018-06-06 | 2018-09-29 | 2018-12-07 | 2018-12-07 | COMP | 2019-01-02 | COMP | 2019-01-08 | COMP | 2019-03-06 | COMP | 2019-05-02 | COMP | Rule 16 | 81 | 47 | 17 | 5 | 40 | 42 | 228
7472 | 2018-06-06 | 2018-10-16 | 2019-02-07 | 2019-02-07 | COMP | 2019-04-24 | COMP | 2019-04-29 | COMP | 2019-06-27 | COMP | 2019-07-23 | COMP | Rule 15/16 | 93 | 77 | 54 | 4 | 43 | 18 | 284
7578 | 2018-06-06 | 2018-10-21 | 2018-11-24 | 2019-04-03 | COMP | 2019-04-05 | COMP | 2019-04-18 | COMP | 2019-10-21 | INPR | 2019-04-19 | COMP | Rule 15/16 | 96 | 22 | 3 | 10 |  |  | 219
8180 | 2018-06-06 | 2018-11-18 | 2019-02-12 | 2019-02-12 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-08-08 | COMP | 2019-09-11 | COMP | Rule 16 | 115 | 57 | 35 | 1 | 91 | 24 | 319
8196 | 2018-06-06 | 2018-11-17 | 2019-01-15 | 2019-01-15 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-12-02 | COMP | 2020-02-18 | COMP | Rule 16 | 115 | 38 | 90 | 1 | 133 | 53 | 426
9150 | 2018-06-06 | 2019-01-19 | 2019-05-01 | 2019-05-01 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-06-11 | COMP | Rule 16 | 156 | 71 | 24 | 1 | 1 | 6 | 255
10818 | 2018-06-06 | 2019-04-01 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-16 | COMP | 2019-07-08 | COMP | 2019-06-07 | COMP | 2019-07-09 | COMP | Rule 16 | 205 | 23 | 12 | 36 | 0 | 2 | 274
11764 | 2018-06-06 | 2019-05-10 | 2019-11-06 | 2019-11-06 | COMP | 2020-01-15 | COMP | 2020-02-24 | COMP | 2020-07-09 | COMP | 2020-09-23 | COMP | Rule 16 | 234 | 126 | 46 | 27 | 98 | 54 | 580
13454 | 2018-06-06 | 2019-07-25 | 2019-11-19 | 2019-11-19 | COMP | 2020-06-10 | COMP | 2020-10-27 | COMP | 2020-09-22 | COMP | 2020-11-19 | COMP | Rule 16 | 286 | 82 | 140 | 99 | 0 | 17 | 620
15799 | 2018-06-06 | 2019-11-20 | 2020-07-29 | 2021-07-07 | COMP | 2021-07-29 | COMP | 2022-01-29 | COMP | 2022-04-28 | COMP | 2022-05-09 | COMP | Rule 16 | 368 | 174 | 17 | 127 | 63 | 8 | 988
5639 | 2018-06-07 | 2018-06-21 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-22 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-03-01 | COMP | Other | 11 | 96 | 51 | 3 | 1 | 26 | 183
5684 | 2018-06-07 | 2018-06-25 | 2018-12-12 | 2019-03-11 | COMP | 2019-04-10 | COMP | 2019-05-29 | COMP | 2019-07-03 | COMP | 2019-12-20 | COMP | Rule 16 | 13 | 118 | 23 | 35 | 26 | 118 | 387
5880 | 2018-06-07 | 2018-07-09 | 2018-09-24 | 2018-09-24 | COMP | 2018-12-19 | COMP | 2019-09-19 | COMP | 2019-03-11 | COMP | 2019-11-06 | COMP | Rule 15/16 | 22 | 55 | 60 | 190 | 0 | 35 | 358
6002 | 2018-06-07 | 2018-07-18 | 2018-09-26 | 2018-11-16 | COMP | 2018-12-10 | COMP | 2018-12-11 | COMP | 2019-01-28 | COMP | 2019-03-13 | COMP | Rule 16 | 29 | 50 | 15 | 2 | 32 | 32 | 191
6445 | 2018-06-07 | 2018-08-20 | 2018-10-03 | 2018-10-03 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-04-02 | COMP | 2019-03-19 | COMP | Rule 16 | 52 | 32 | 53 | 1 | 71 |  | 195
6551 | 2018-06-07 | 2018-08-27 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-03-04 | COMP | 2019-04-10 | COMP | Rule 16 | 57 | 79 | 11 | 1 | 40 | 28 | 211
6587 | 2018-06-07 | 2018-08-31 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-13 | NOTN | 2019-02-15 | COMP | 2019-02-27 | NOTN | 2019-05-15 | COMP | Other | 61 | 89 |  | 26 |  |  | 236
6691 | 2018-06-07 | 2018-09-06 | 2018-09-18 | 2018-09-18 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-01-09 | COMP | 2019-01-24 | COMP | Rule 16 | 64 | 9 | 59 | 1 | 19 | 11 | 158
6768 | 2018-06-07 | 2018-09-11 | 2018-11-07 | 2018-11-07 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-05-09 | COMP | 2019-06-28 | COMP | Rule 16 | 67 | 42 | 55 | 1 | 71 | 36 | 267
7067 | 2018-06-07 | 2018-09-26 | 2019-01-17 | 2021-04-21 | COMP | 2021-05-14 | COMP | 2021-05-14 | COMP | 2021-05-14 | COMP | 2021-07-16 | COMP | Rule 16 | 78 | 77 | 18 | 1 | 1 | 44 | 782
7491 | 2018-06-07 | 2018-10-16 | 2018-11-02 | 2019-06-18 | COMP | 2019-07-15 | COMP | 2018-12-04 | COMP | 2019-07-17 | COMP | 2019-07-31 | COMP | Rule 16 | 92 | 14 | 19 |  | 156 | 11 | 289
7673 | 2018-06-07 | 2018-10-24 | 2019-01-12 | 2019-01-12 | COMP | 2019-11-13 | COMP | 2019-11-14 | COMP | 2020-03-20 | COMP | 2020-05-06 | COMP | Rule 16 | 98 | 53 | 212 | 2 | 86 | 34 | 481
8284 | 2018-06-07 | 2018-11-26 | 2019-05-28 | 2019-05-28 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2021-02-27 | INPR | 2019-08-24 | COMP | Rule 16 | 118 | 127 | 29 | 1 |  |  | 306
8695 | 2018-06-07 | 2018-12-17 | 2019-09-18 | 2020-03-01 | COMP | 2020-03-05 | COMP | 2019-11-04 | COMP | 2020-03-05 | COMP | 2020-03-31 | COMP | Rule 16 | 133 | 191 | 4 |  | 82 | 19 | 455
8782 | 2018-06-07 | 2018-12-24 | 2019-01-08 | 2019-01-17 | COMP | 2019-01-25 | COMP | 2019-03-20 | COMP | 2019-01-27 | COMP | 2019-02-11 | COMP | Rule 16 | 138 | 10 | 6 | 38 | 0 |  | 170
9125 | 2018-06-07 | 2019-01-17 | 2019-02-14 | 2019-02-14 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-02-23 | COMP | 2019-03-20 | COMP | Rule 16 | 154 | 20 | 3 | 1 | 4 | 18 | 196
9777 | 2018-06-07 | 2019-02-15 | 2019-03-22 | 2019-03-22 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-10-17 | COMP | 2019-12-06 | COMP | Rule 16 | 174 | 25 | 75 | 1 | 73 | 34 | 377
10268 | 2018-06-07 | 2019-03-07 | 2019-05-03 | 2019-05-03 | COMP | 2019-06-20 | COMP | 2020-01-08 | COMP | 2019-10-15 | COMP | 2020-02-19 | COMP | Rule 16 | 187 | 42 | 34 | 138 | 0 | 29 | 426
10945 | 2018-06-07 | 2019-04-05 | 2019-06-26 | 2019-06-26 | COMP | 2019-08-28 | COMP | 2020-02-27 | COMP | 2023-04-30 | INPR | 2020-04-29 | COMP | Rule 16 | 208 | 58 | 45 | 124 |  |  | 476
12195 | 2018-06-07 | 2019-05-28 | 2019-07-18 | 2019-07-18 | COMP | 2019-09-24 | COMP | 2019-10-10 | COMP | 2021-05-10 | COMP | 2021-05-17 | COMP | Rule 16 | 244 | 37 | 48 | 13 | 397 | 6 | 740
16180 | 2018-06-07 | 2019-12-13 | 2020-01-09 | 2020-01-09 | COMP | 2020-04-27 | COMP | 2020-08-13 | COMP | 2020-04-27 | COMP | 2020-10-13 | COMP | Rule 16 | 382 | 18 | 76 | 78 | 0 | 43 | 593
17966 | 2018-06-07 | 2020-03-05 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2022-07-16 | INPR | 2020-08-26 | COMP | Rule 16 | 437 | 76 | 6 | 1 |  |  | 560
5753 | 2018-06-08 | 2018-06-29 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-21 | COMP | 2019-06-11 | COMP | 2019-04-19 | COMP | 2019-07-01 | COMP | Rule 16 | 16 | 167 | 15 | 58 | 0 | 15 | 267
5758 | 2018-06-08 | 2018-06-30 | 2019-01-25 | 2019-01-25 | COMP | 2019-01-26 | NOTN | 2019-01-26 | COMP | 2019-01-28 | COMP | 2019-03-07 | COMP | Other | 16 | 142 |  | 1 | 1 | 28 | 186
5823 | 2018-06-08 | 2018-07-05 | 2018-09-12 | 2018-12-05 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-04-24 | COMP | 2019-05-01 | COMP | Rule 16 | 19 | 49 | 36 | 1 | 62 | 6 | 225
5858 | 2018-06-08 | 2018-07-09 | 2018-11-10 | 2018-11-10 | COMP | 2018-11-16 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-01-26 | COMP | Rule 16 | 21 | 89 | 4 | 32 | 1 | 15 | 158
5859 | 2018-06-08 | 2018-07-09 | 2018-10-10 | 2018-10-10 | COMP | 2018-10-30 | COMP | 2018-11-20 | COMP | 2019-05-23 | COMP | 2019-06-13 | COMP | Rule 16 | 21 | 67 | 15 | 15 | 127 | 15 | 255
5916 | 2018-06-08 | 2018-07-11 | 2018-09-29 | 2018-09-29 | COMP | 2019-04-11 | COMP | 2019-04-23 | COMP | 2019-04-04 | COMP | 2019-05-29 | COMP | Rule 16 | 23 | 57 | 132 | 9 | 0 | 26 | 244
5917 | 2018-06-08 | 2018-07-11 | 2018-11-11 | 2019-03-18 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2019-09-12 | COMP | 2020-04-20 | COMP | Rule 16 | 23 | 87 | 98 | 1 | 29 | 151 | 468
5918 | 2018-06-08 | 2018-07-11 | 2018-12-12 | 2018-12-12 | COMP | 2019-04-11 | COMP | 2019-04-16 | COMP | 2019-04-04 | COMP | 2019-07-22 | COMP | Rule 16 | 23 | 107 | 83 | 4 | 0 | 68 | 281
6017 | 2018-06-08 | 2018-07-18 | 2018-07-23 | 2018-08-18 | COMP | 2018-09-11 | COMP | 2018-08-01 | COMP | 2020-05-31 | INPR | 2020-02-11 | COMP | Rule 16 | 28 | 4 | 16 |  |  |  | 420
6091 | 2018-06-08 | 2018-07-25 | 2018-10-01 | 2018-12-05 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-01-14 | COMP | 2019-03-30 | COMP | Rule 16 | 33 | 48 | 3 | 1 | 25 | 53 | 202
6125 | 2018-06-08 | 2018-07-27 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-08 | COMP | 2018-11-08 | COMP | 2019-03-02 | COMP | 2019-03-25 | COMP | Rule 16 | 35 | 58 | 17 | 1 | 75 | 16 | 198
6130 | 2018-06-08 | 2018-07-28 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2020-02-06 | COMP | 2020-05-29 | COMP | Rule 15 | 35 | 136 | 9 | 1 | 239 | 80 | 496
6148 | 2018-06-08 | 2018-07-30 | 2018-09-05 | 2018-09-05 | COMP | 2018-09-28 | COMP | 2018-10-29 | COMP | 2019-05-06 | COMP | 2019-06-24 | COMP | Rule 16 | 36 | 27 | 18 | 22 | 129 | 35 | 262
6166 | 2018-06-08 | 2018-08-01 | 2019-01-09 | 2019-05-21 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2020-01-28 | COMP | 2020-09-27 | COMP | Rule 16 | 38 | 110 | 82 | 1 | 91 | 171 | 580
6425 | 2018-06-08 | 2018-08-16 | 2018-12-19 | 2018-12-19 | COMP | 2019-03-05 | COMP | 2019-03-29 | COMP | 2019-09-18 | COMP | 2019-10-09 | COMP | Rule 15/16 | 49 | 86 | 51 | 19 | 121 | 16 | 337
6443 | 2018-06-08 | 2018-08-18 | 2018-11-05 | 2018-11-05 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2019-01-08 | COMP | 2019-01-16 | COMP | Rule 16 | 50 | 55 | 7 | 1 | 36 | 7 | 152
6626 | 2018-06-08 | 2018-08-31 | 2018-10-16 | 2018-10-18 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-09-22 | INPR | 2019-06-04 | COMP | Rule 16 | 60 | 32 | 43 | 1 |  |  | 248
6648 | 2018-06-08 | 2018-09-04 | 2018-09-24 | 2018-09-24 | COMP | 2018-11-05 | COMP | 2018-11-26 | COMP | 2019-01-04 | COMP | 2019-03-27 | COMP | Rule 16 | 61 | 15 | 31 | 13 | 28 | 57 | 200
7118 | 2018-06-08 | 2018-09-28 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-01 | COMP | 2018-12-18 | COMP | 2019-07-10 | COMP | 2019-08-05 | COMP | Rule 16 | 79 | 22 | 4 | 31 | 141 | 19 | 291
7280 | 2018-06-08 | 2018-10-05 | 2019-02-01 | 2019-02-01 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-09-15 | COMP | 2019-10-18 | COMP | Rule 16 | 84 | 80 | 116 | 1 | 42 | 25 | 344
7333 | 2018-06-08 | 2018-10-08 | 2019-07-11 | 2021-04-03 | COMP | 2021-04-12 | COMP | 2021-04-15 | COMP | 2021-04-20 | COMP | 2021-05-04 | COMP | Rule 15/16 | 85 | 190 | 6 | 4 | 4 | 11 | 730
8011 | 2018-06-08 | 2018-11-09 | 2019-02-11 | 2019-03-12 | COMP | 2019-04-11 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-06-19 | COMP | Rule 16 | 109 | 61 | 23 | 45 | 1 | 5 | 259
8154 | 2018-06-08 | 2018-11-17 | 2019-03-18 | 2019-03-18 | COMP | 2019-04-24 | COMP | 2019-06-12 | COMP | 2019-06-06 | COMP | 2019-08-28 | COMP | Rule 16 | 113 | 80 | 28 | 35 | 0 | 55 | 308
8474 | 2018-06-08 | 2018-12-05 | 2018-12-30 | 2018-12-30 | COMP | 2019-03-04 | COMP | 2019-02-19 | COMP | 2019-02-26 | COMP | 2019-05-03 | COMP | Rule 16 | 124 | 17 | 43 |  | 6 | 49 | 227
8512 | 2018-06-08 | 2018-12-06 | 2019-05-24 | 2020-08-12 | COMP | 2020-08-21 | COMP | 2019-09-09 | COMP | 2020-10-26 | COMP | 2020-11-24 | COMP | Rule 16 | 125 | 118 | 8 |  | 287 | 21 | 621
8838 | 2018-06-08 | 2018-12-31 | 2019-07-25 | 2021-01-28 | COMP | 2021-02-08 | COMP | 2021-02-08 | COMP | 2022-09-19 | COMP | 2023-06-30 | COMP | Rule 16 | 141 | 144 | 8 | 1 | 408 | 196 | 1272
9194 | 2018-06-08 | 2019-01-22 | 2019-02-22 | 2021-01-30 | REQD | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-12-20 | COMP | 2020-01-24 | COMP | Unknown | 155 |  |  |  | 100 | 23 | 408
9726 | 2018-06-08 | 2019-02-12 | 2019-02-19 | 2019-02-19 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-10-09 | COMP | 2019-10-26 | COMP | Rule 15/16 | 170 | 5 | 122 | 1 | 43 | 13 | 349
10469 | 2018-06-08 | 2019-03-18 | 2019-08-14 | 2019-08-29 | COMP | 2019-09-24 | COMP | 2019-10-29 | COMP | 2023-11-11 | INPR | 2019-12-20 | COMP | Rule 15/16 | 193 | 106 | 18 | 26 |  |  | 386
11164 | 2018-06-08 | 2019-04-16 | 2019-12-02 | 2019-12-02 | COMP | 2021-04-15 | COMP | 2022-02-08 | COMP |  | INPR | 2022-07-23 | COMP | Rule 15/16 | 214 | 159 | 346 | 207 |  |  | 1037
12820 | 2018-06-08 | 2019-06-24 | 2019-08-12 | 2020-04-13 | COMP | 2020-06-30 | COMP | 2020-07-17 | COMP | 2020-06-29 | COMP | 2020-08-10 | COMP | Rule 16 | 262 | 35 | 56 | 14 | 0 | 17 | 547
12913 | 2018-06-08 | 2019-06-28 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-20 | COMP | 2020-03-26 | COMP | 2020-05-11 | COMP | 2020-08-10 | COMP | Rule 15/16 | 266 | 77 | 25 | 86 | 33 | 65 | 547
15466 | 2018-06-08 | 2019-11-04 | 2020-03-31 | 2020-03-31 | COMP | 2021-06-22 | COMP | 2021-06-22 | COMP | 2021-09-16 | COMP | 2021-11-16 | COMP | Rule 16 | 355 | 100 | 311 | 1 | 61 | 43 | 866
15662 | 2018-06-08 | 2019-11-14 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-02 | COMP | 2020-04-28 | COMP | 2020-03-18 | COMP | 2020-07-29 | COMP | Rule 16 | 362 | 70 | 3 | 42 | 0 | 66 | 539
3897 | 2018-06-09 | 2018-09-27 | 2018-11-14 | 2018-11-14 | COMP | 2019-01-24 | COMP | 2019-01-30 | COMP | 2019-02-12 | COMP | 2019-04-12 | COMP | Rule 15/16 | 77 | 34 | 47 | 5 | 10 | 43 | 211
6164 | 2018-06-09 | 2018-08-02 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-16 | COMP | 2018-10-29 | COMP | 2019-03-14 | COMP | 2019-05-07 | COMP | Rule 16 | 38 | 39 | 15 | 10 | 92 | 39 | 228
6708 | 2018-06-09 | 2018-09-11 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-20 | NOTN | 2019-03-07 | COMP | 2019-03-14 | COMP | 2019-05-01 | COMP | Other | 65 | 98 |  | 24 | 6 | 35 | 224
9059 | 2018-06-09 | 2019-01-15 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-19 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-06-05 | COMP | Rule 16 | 150 | 38 | 7 | 39 | 1 | 18 | 248
3887 | 2018-06-11 | 2018-09-17 | 2018-10-29 | 2018-10-29 | COMP | 2019-07-24 | NOTN | 2019-07-24 | INPR | 2019-11-23 | REQD | 2019-07-28 | COMP | Rule 16 | 69 | 31 |  |  |  |  | 284
3986 | 2018-06-11 | 2018-11-08 | 2019-02-21 | 2019-02-21 | COMP | 2019-05-09 | COMP | 2019-09-10 | COMP | 2020-01-14 | COMP | 2020-02-04 | COMP | Rule 15/16 | 107 | 69 | 56 | 86 | 86 | 15 | 414
5546 | 2018-06-11 | 2018-06-12 | 2019-02-21 | 2019-05-14 | COMP | 2019-06-04 | COMP | 2019-09-16 | COMP | 2019-09-05 | COMP | 2019-11-08 | COMP | Rule 16 | 2 | 174 | 15 | 73 | 0 | 40 | 358
5729 | 2018-06-11 | 2018-06-27 | 2018-10-01 | 2018-10-01 | COMP | 2018-12-05 | COMP | 2018-12-12 | COMP | 2019-01-02 | COMP | 2019-05-14 | COMP | Rule 16 | 13 | 67 | 45 | 6 | 14 | 93 | 233
5813 | 2018-06-11 | 2018-07-05 | 2018-09-09 | 2018-12-12 | COMP | 2018-12-31 | COMP | 2019-02-12 | COMP | 2019-05-14 | COMP | 2019-05-29 | COMP | Rule 16 | 18 | 46 | 13 | 30 | 65 | 11 | 243
5909 | 2018-06-11 | 2018-07-10 | 2018-12-05 | 2018-12-05 | COMP | 2019-02-04 | COMP | 2019-03-22 | INPR | 2019-02-04 | COMP | 2019-03-22 | COMP | Rule 16 | 21 | 103 | 41 |  |  |  | 196
5974 | 2018-06-11 | 2018-07-16 | 2018-10-30 | 2018-10-30 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2020-03-17 | COMP | 2020-03-30 | COMP | Rule 16 | 25 | 76 | 71 | 1 | 274 | 10 | 452
6048 | 2018-06-11 | 2018-07-23 | 2018-08-15 | 2018-08-15 | COMP | 2018-08-30 | COMP | 2018-10-24 | COMP | 2018-10-01 | COMP | 2019-12-20 | COMP | Rule 16 | 30 | 18 | 12 | 39 | 0 | 290 | 385
6110 | 2018-06-11 | 2018-07-26 | 2018-10-01 | 2018-10-01 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-07-16 | COMP | 2019-07-19 | COMP | Rule 16 | 33 | 47 | 111 | 1 | 88 | 4 | 279
6210 | 2018-06-11 | 2018-08-03 | 2019-03-08 | 2019-03-08 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-08-26 | COMP | 2019-10-01 | COMP | Rule 16 | 39 | 148 | 53 | 1 | 68 | 26 | 330
6318 | 2018-06-11 | 2018-08-09 | 2019-03-02 | 2019-03-02 | COMP | 2019-04-30 | COMP | 2019-04-29 | COMP | 2019-05-20 | COMP | 2019-06-29 | COMP | Rule 16 | 43 | 139 | 42 |  | 16 | 29 | 265
6447 | 2018-06-11 | 2018-08-20 | 2018-11-10 | 2019-12-14 | COMP | 2020-02-14 | COMP | 2020-02-25 | COMP | 2020-03-30 | COMP | 2020-04-29 | COMP | Rule 16 | 50 | 59 | 42 | 7 | 25 | 23 | 474
6497 | 2018-06-11 | 2018-08-22 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2020-08-29 | INPR | 2019-04-13 | COMP | Rule 16 | 52 | 67 | 30 | 1 |  |  | 211
6872 | 2018-06-11 | 2018-09-14 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-11 | COMP | 2019-04-29 | COMP | 2019-07-01 | COMP | 2019-08-01 | COMP | Rule 16 | 68 | 43 | 18 | 96 | 45 | 23 | 288
6905 | 2018-06-11 | 2018-09-16 | 2019-01-18 | 2019-01-18 | COMP | 2019-05-01 | COMP | 2019-05-22 | COMP | 2019-05-02 | COMP | 2019-06-22 | COMP | Rule 16 | 68 | 85 | 72 | 16 | 0 | 22 | 260
7295 | 2018-06-11 | 2018-10-06 | 2018-12-27 | 2018-12-27 | COMP | 2019-02-15 | COMP | 2019-02-22 | COMP | 2019-04-16 | COMP | 2019-05-30 | COMP | Rule 16 | 83 | 55 | 35 | 5 | 38 | 32 | 244
7488 | 2018-06-11 | 2018-10-17 | 2018-11-16 | 2019-04-04 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-05-20 | COMP | Rule 16 | 91 | 22 | 13 | 1 | 1 | 21 | 237
7630 | 2018-06-11 | 2018-10-23 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-13 | COMP | 2018-12-13 | COMP | 2018-12-07 | COMP | 2019-01-04 | COMP | Rule 16 | 95 | 21 | 15 | 1 | 0 | 15 | 143
7836 | 2018-06-11 | 2018-11-01 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-05 | NOTN | 2019-03-05 | COMP | 2019-05-23 | COMP | 2019-07-22 | COMP | Other | 102 | 75 |  | 8 | 58 | 41 | 280
7867 | 2018-06-11 | 2018-11-03 | 2019-01-23 | 2019-01-23 | COMP | 2019-03-21 | COMP | 2020-04-20 | INPR | 2023-04-30 | CANC | 2019-08-22 | COMP | Rule 16 | 103 | 52 | 41 |  |  |  | 303
8465 | 2018-06-11 | 2018-12-04 | 2019-02-26 | 2019-02-26 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-07-01 | COMP | Rule 16 | 122 | 57 | 59 | 1 | 1 | 31 | 266
9013 | 2018-06-11 | 2019-01-12 | 2019-04-13 | 2019-04-13 | COMP | 2019-04-24 | COMP | 2019-07-03 | COMP | 2019-11-13 | COMP | 2019-12-11 | COMP | Rule 16 | 148 | 63 | 8 | 50 | 93 | 19 | 378
9473 | 2018-06-11 | 2019-02-05 | 2019-04-10 | 2019-04-10 | COMP | 2019-08-07 | COMP | 2020-10-19 | COMP | 2020-10-05 | COMP | 2020-12-17 | COMP | Rule 15/16 | 164 | 46 | 84 | 304 | 0 | 41 | 635
9933 | 2018-06-11 | 2019-02-22 | 2019-06-20 | 2019-06-20 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-12-15 | COMP | Rule 15/16 | 176 | 84 | 93 | 1 | 1 | 30 | 380
10161 | 2018-06-11 | 2019-03-05 | 2019-03-31 | 2019-03-31 | COMP | 2019-06-11 | COMP | 2020-01-07 | COMP | 2020-01-27 | COMP | 2020-02-24 | COMP | Rule 16 | 183 | 19 | 51 | 144 | 14 | 20 | 427
10242 | 2018-06-11 | 2019-03-07 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-05 | COMP | 2019-06-24 | COMP | 2019-04-30 | COMP | 2019-07-16 | COMP | Rule 16 | 185 | 17 | 5 | 56 | 0 | 16 | 276
10560 | 2018-06-11 | 2019-03-20 | 2019-08-15 | 2019-09-20 | COMP | 2019-11-08 | COMP | 2019-10-31 | COMP | 2019-11-22 | COMP | 2020-02-13 | COMP | Rule 16 | 194 | 105 | 36 |  | 16 | 55 | 421
10582 | 2018-06-11 | 2019-03-21 | 2019-08-27 | 2019-08-27 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-03-03 | COMP | 2020-06-25 | COMP | Rule 16 | 195 | 112 | 26 | 1 | 103 | 82 | 514
11095 | 2018-06-11 | 2019-04-11 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-20 | COMP | 2019-08-26 | COMP | 2019-08-23 | COMP | 2019-08-29 | COMP | Rule 16 | 210 | 80 | 12 | 5 | 0 | 4 | 308
11504 | 2018-06-11 | 2019-04-30 | 2020-04-27 | 2020-04-27 | COMP | 2021-06-08 | COMP | 2022-05-27 | COMP | 2022-05-26 | COMP | 2022-07-14 | COMP | Rule 15/16 | 223 | 250 | 282 | 247 | 0 | 32 | 1030
13602 | 2018-06-11 | 2019-08-01 | 2019-11-20 | 2019-11-20 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-05-19 | COMP | 2020-07-07 | COMP | Rule 16 | 288 | 78 | 69 | 1 | 56 | 35 | 522
3717 | 2018-06-12 | 2018-06-15 | 2018-10-04 | 2018-10-04 | COMP | 2018-11-06 | COMP | 2018-11-08 | COMP | 2018-11-21 | COMP | 2019-01-27 | COMP | Rule 16 | 4 | 78 | 24 | 3 | 9 | 43 | 156
5876 | 2018-06-12 | 2018-07-09 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-27 | COMP | 2019-01-03 | COMP | 2019-02-11 | COMP | 2019-03-13 | COMP | Rule 16 | 19 | 99 | 21 | 5 | 27 | 22 | 188
5967 | 2018-06-12 | 2018-07-16 | 2018-10-04 | 2018-10-04 | COMP | 2019-01-08 | COMP | 2019-01-15 | COMP | 2019-02-12 | COMP | 2019-03-14 | COMP | Rule 16 | 24 | 58 | 64 | 6 | 20 | 22 | 189
6392 | 2018-06-12 | 2018-08-15 | 2018-09-26 | 2018-09-26 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2019-07-02 | COMP | 2019-07-10 | COMP | Rule 16 | 46 | 30 | 18 | 1 | 175 | 6 | 271
6458 | 2018-06-12 | 2018-08-21 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-30 | COMP | 2019-06-12 | COMP | 2020-02-27 | COMP | 2020-03-17 | COMP | Rule 16 | 50 | 155 | 19 | 31 | 178 | 14 | 442
6558 | 2018-06-12 | 2018-08-27 | 2018-10-27 | 2018-10-27 | COMP | 2019-04-18 | COMP | 2019-07-24 | COMP | 2021-02-27 | INPR | 2019-09-16 | COMP | Rule 16 | 54 | 44 | 117 | 68 |  |  | 318
6725 | 2018-06-12 | 2018-09-10 | 2018-10-12 | 2018-10-12 | COMP | 2019-01-03 | COMP | 2019-09-04 | COMP | 2020-02-25 | COMP | 2020-04-15 | COMP | Rule 15/16 | 63 | 25 | 55 | 170 | 118 | 37 | 463
7101 | 2018-06-12 | 2018-09-27 | 2019-06-27 | 2019-06-27 | COMP | 2019-09-17 | COMP | 2020-03-17 | COMP | 2021-02-23 | COMP | 2021-03-08 | COMP | Rule 16 | 76 | 188 | 57 | 124 | 237 | 10 | 687
7170 | 2018-06-12 | 2018-10-01 | 2019-01-31 | 2020-04-14 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2021-08-31 | COMP | 2021-10-14 | COMP | Rule 16 | 78 | 83 | 117 | 1 | 234 | 32 | 842
7600 | 2018-06-12 | 2018-10-23 | 2019-02-11 | 2019-02-11 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-10-21 | INPR | 2019-07-03 | COMP | Rule 15/16 | 94 | 74 | 18 | 1 |  |  | 267
7631 | 2018-06-12 | 2018-10-23 | 2019-06-18 | 2019-06-18 | COMP | 2019-08-28 | COMP | 2022-03-24 | COMP | 2022-02-01 | COMP | 2022-05-23 | COMP | Rule 15/16 | 94 | 163 | 51 | 647 | 0 | 43 | 994
7632 | 2018-06-12 | 2018-10-23 | 2019-06-10 | 2019-06-10 | COMP | 2020-01-09 | COMP | 2022-01-13 | COMP | 2022-01-18 | COMP | 2022-03-28 | COMP | Rule 15/16 | 94 | 157 | 147 | 509 | 3 | 49 | 954
8245 | 2018-06-12 | 2018-11-21 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-24 | COMP | 2019-11-26 | INPR | 2022-04-16 | REQD | 2020-04-30 | COMP | Rule 15/16 | 114 | 106 | 22 |  |  |  | 474
9243 | 2018-06-12 | 2019-01-24 | 2019-10-12 | 2019-10-12 | COMP | 2019-11-04 | COMP | 2022-11-18 | COMP | 2022-11-18 | COMP | 2023-02-21 | COMP | Rule 15/16 | 155 | 183 | 16 | 766 | 1 | 62 | 1179
10082 | 2018-06-12 | 2019-03-01 | 2019-04-26 | 2019-04-26 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2019-11-20 | COMP | 2020-01-13 | COMP | Rule 16 | 180 | 41 | 146 | 1 | 0 | 34 | 398
10451 | 2018-06-12 | 2019-03-17 | 2019-07-24 | 2019-07-24 | COMP | 2019-10-07 | COMP | 2019-10-10 | COMP | 2021-05-25 | COMP | 2021-06-17 | COMP | Rule 15/16 | 190 | 91 | 53 | 4 | 408 | 17 | 759
11537 | 2018-06-12 | 2019-05-01 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-19 | COMP | 2019-09-09 | COMP | 2019-09-10 | COMP | 2020-01-02 | COMP | Rule 16 | 223 | 54 | 3 | 36 | 2 | 78 | 391
13534 | 2018-06-12 | 2019-07-30 | 2020-03-25 | 2020-08-06 | COMP | 2020-12-10 | COMP | 2021-01-06 | COMP | 2021-01-19 | COMP | 2021-03-05 | COMP | Rule 15/16 | 285 | 164 | 87 | 18 | 9 | 33 | 686
3817 | 2018-06-13 | 2018-07-30 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-18 | COMP | 2019-01-02 | COMP | 2018-11-26 | COMP | 2019-03-18 | COMP | Rule 16 | 33 | 38 | 21 | 50 | 0 | 52 | 190
5647 | 2018-06-13 | 2018-06-22 | 2018-10-08 | 2018-10-08 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2018-12-04 | COMP | 2019-01-08 | COMP | Rule 16 | 8 | 75 | 17 | 1 | 23 | 24 | 143
6126 | 2018-06-13 | 2018-07-27 | 2018-09-20 | 2018-10-03 | COMP | 2018-11-15 | COMP | 2018-12-10 | COMP | 2018-12-12 | COMP | 2019-01-24 | COMP | Rule 15/16 | 32 | 39 | 31 | 16 | 3 | 29 | 154
6519 | 2018-06-13 | 2018-08-23 | 2018-10-04 | 2018-10-04 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2019-07-22 | COMP | 2019-10-01 | COMP | Rule 16 | 51 | 30 | 12 | 1 | 188 | 51 | 328
6544 | 2018-06-13 | 2018-08-27 | 2018-10-08 | 2018-10-30 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-03-12 | COMP | 2019-04-23 | COMP | Rule 15/16 | 53 | 30 | 44 | 1 | 46 | 31 | 216
6875 | 2018-06-13 | 2018-09-14 | 2018-11-07 | 2018-11-07 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2020-01-09 | COMP | 2020-01-20 | COMP | Rule 16 | 66 | 39 | 131 | 1 | 162 | 7 | 401
8891 | 2018-06-13 | 2019-01-04 | 2019-04-07 | 2020-08-07 | COMP | 2020-11-13 | COMP | 2021-04-09 | COMP | 2021-05-25 | COMP | 2021-06-22 | COMP | Rule 15/16 | 141 | 64 | 69 | 100 | 33 | 20 | 761
9172 | 2018-06-13 | 2019-01-18 | 2019-03-18 | 2019-03-18 | COMP | 2019-04-08 | COMP | 2019-06-25 | COMP | 2019-08-15 | COMP | 2019-08-29 | COMP | Rule 16 | 151 | 40 | 16 | 56 | 37 | 11 | 306
9199 | 2018-06-13 | 2019-01-22 | 2019-05-06 | 2019-05-06 | COMP | 2019-05-15 | COMP | 2019-10-21 | REQD | 2019-06-11 | COMP | 2019-06-19 | COMP | Rule 16 | 152 | 74 | 8 |  |  |  | 256
9208 | 2018-06-13 | 2019-01-22 | 2019-12-06 | 2020-07-17 | COMP | 2020-08-26 | COMP | 2021-03-04 | COMP | 2021-04-08 | COMP | 2021-05-20 | COMP | Rule 16 | 152 | 222 | 29 | 129 | 26 | 31 | 739
10098 | 2018-06-13 | 2019-03-01 | 2019-05-03 | 2019-05-03 | COMP | 2019-06-06 | COMP | 2019-06-24 | COMP | 2019-06-07 | COMP | 2019-08-22 | COMP | Rule 16 | 179 | 46 | 24 | 13 | 0 | 43 | 301
11040 | 2018-06-13 | 2019-04-10 | 2019-12-06 | 2020-02-21 | COMP | 2020-03-27 | COMP | 2020-08-11 | COMP | 2020-07-06 | COMP | 2020-09-17 | COMP | Rule 16 | 207 | 167 | 26 | 97 | 0 | 27 | 571
12551 | 2018-06-13 | 2019-06-13 | 2020-01-26 | 2020-02-15 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2021-10-23 | INPR | 2020-10-09 | COMP | Rule 15/16 | 252 | 154 | 50 | 1 |  |  | 587
21035 | 2018-06-13 | 2020-07-20 | 2020-12-14 | 2020-12-14 | COMP | 2021-01-14 | COMP | 2021-02-23 | COMP | 2021-10-20 | COMP | 2021-11-29 | COMP | Rule 16 | 529 | 102 | 22 | 27 | 169 | 26 | 870
3873 | 2018-06-14 | 2018-09-04 | 2018-12-04 | 2018-12-04 | COMP | 2019-01-17 | NOTN | 2019-01-30 | COMP | 2019-01-17 | COMP | 2019-02-19 | COMP | Other | 57 | 63 |  | 39 | 0 | 14 | 170
5807 | 2018-06-14 | 2018-07-06 | 2018-09-26 | 2019-01-15 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-04-22 | COMP | 2019-07-31 | COMP | Rule 16 | 16 | 58 | 66 | 1 | 3 | 71 | 284
5987 | 2018-06-14 | 2018-07-17 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-17 | COMP | 2018-11-26 | COMP | 2019-02-13 | COMP | 2019-03-28 | COMP | Rule 16 | 23 | 48 | 19 | 26 | 55 | 31 | 197
6085 | 2018-06-14 | 2018-07-24 | 2018-09-24 | 2018-11-28 | COMP | 2018-12-07 | COMP | 2018-12-10 | COMP | 2019-10-21 | INPR | 2019-04-23 | COMP | Rule 16 | 28 | 44 | 8 | 2 |  |  | 215
6167 | 2018-06-14 | 2018-08-01 | 2018-10-12 | 2018-10-12 | COMP | 2018-12-19 | COMP | 2019-01-28 | COMP | 2019-07-21 | INPR | 2019-02-04 | COMP | Rule 16 | 34 | 52 | 46 | 26 |  |  | 160
6184 | 2018-06-14 | 2018-08-03 | 2019-01-11 | 2019-01-11 | COMP | 2019-01-24 | COMP | 2019-03-06 | COMP | 2019-05-01 | COMP | 2019-05-17 | COMP | Rule 16 | 36 | 110 | 9 | 29 | 41 | 13 | 233
6242 | 2018-06-14 | 2018-08-06 | 2018-09-19 | 2018-09-19 | COMP | 2018-09-26 | COMP | 2018-12-17 | COMP | 2018-11-19 | COMP | 2019-01-25 | COMP | Rule 16 | 37 | 32 | 6 | 56 | 0 | 27 | 154
6417 | 2018-06-14 | 2018-08-17 | 2018-11-10 | 2018-11-10 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-11-19 | COMP | 2019-12-30 | COMP | Rule 16 | 46 | 60 | 211 | 1 | 46 | 27 | 387
6633 | 2018-06-14 | 2018-09-01 | 2018-11-28 | 2019-01-10 | COMP | 2019-03-08 | NOTN | 2019-03-08 | COMP | 2018-11-29 | COMP | 2019-03-13 | COMP | Other | 56 | 59 |  | 40 | 0 | 4 | 186
6643 | 2018-06-14 | 2018-09-04 | 2019-01-23 | 2019-01-23 | COMP | 2019-12-28 | INPR | 2019-04-05 | COMP | 2019-03-29 | COMP | 2019-08-28 | COMP | Rule 16 | 57 | 96 |  | 52 | 0 | 102 | 304
6674 | 2018-06-14 | 2018-09-06 | 2018-12-05 | 2018-12-05 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-12-19 | COMP | 2020-01-17 | COMP | Rule 16 | 59 | 62 | 144 | 1 | 119 | 20 | 400
7446 | 2018-06-14 | 2018-10-12 | 2019-02-15 | 2019-03-05 | COMP | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-04-12 | COMP | 2019-05-03 | COMP | Rule 16 | 85 | 85 | 14 | 1 | 16 | 16 | 223
7479 | 2018-06-14 | 2018-10-16 | 2018-11-18 | 2019-01-26 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2020-06-05 | COMP | 2020-06-16 | COMP | Rule 16 | 87 | 23 | 9 | 1 | 335 | 8 | 504
8896 | 2018-06-14 | 2019-01-04 | 2019-02-26 | 2019-03-07 | COMP | 2019-03-12 | COMP | 2019-04-12 | COMP | 2019-05-08 | COMP | 2019-06-05 | COMP | Rule 16 | 140 | 36 | 4 | 24 | 19 | 20 | 245
9274 | 2018-06-14 | 2019-01-26 | 2019-04-23 | 2019-04-23 | COMP | 2019-07-19 | COMP | 2020-05-20 | COMP | 2020-07-01 | COMP | 2020-08-04 | COMP | Rule 16 | 154 | 61 | 62 | 211 | 30 | 25 | 539
9320 | 2018-06-14 | 2019-01-30 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-31 | COMP | 2020-05-12 | COMP | 2020-06-11 | COMP | 2021-02-01 | COMP | Rule 15/16 | 157 | 222 | 32 | 72 | 22 | 161 | 661
9391 | 2018-06-14 | 2019-02-01 | 2019-04-06 | 2019-05-10 | COMP | 2021-12-03 | COMP | 2021-12-03 | COMP | 2022-11-01 | COMP | 2023-02-14 | COMP | Rule 16 | 159 | 45 | 646 | 1 | 232 | 70 | 1173
9498 | 2018-06-14 | 2019-02-06 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-12 | COMP | 2019-04-22 | COMP | 2019-04-14 | COMP | 2019-05-09 | COMP | Rule 16 | 162 | 36 | 12 | 7 | 0 | 14 | 227
14175 | 2018-06-14 | 2019-08-28 | 2019-10-18 | 2019-10-26 | COMP | 2019-12-20 | NOTN | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-02-11 | COMP | Other | 304 | 37 |  | 37 | 1 | 35 | 416
16548 | 2018-06-14 | 2020-01-07 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-16 | COMP | 2020-09-28 | COMP | 2021-04-13 | COMP | 2021-05-06 | COMP | Rule 16 | 392 | 98 | 16 | 74 | 135 | 18 | 728
17993 | 2018-06-14 | 2020-03-06 | 2020-05-22 | 2020-05-22 | COMP | 2020-08-13 | COMP | 2020-09-28 | COMP | 2020-10-23 | COMP | 2020-12-01 | COMP | Rule 16 | 433 | 56 | 59 | 32 | 20 | 25 | 620
4008 | 2018-06-15 | 2018-11-26 | 2019-04-18 | 2019-04-18 | COMP | 2019-06-06 | COMP | 2019-06-12 | COMP | 2021-02-23 | COMP | 2021-03-04 | COMP | Rule 15/16 | 112 | 100 | 35 | 5 | 427 | 8 | 682
5618 | 2018-06-15 | 2018-06-21 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-05 | COMP | 2019-01-07 | COMP | 2018-11-17 | COMP | 2019-03-08 | COMP | Rule 16 | 5 | 90 | 6 | 41 | 0 | 43 | 182
5698 | 2018-06-15 | 2018-06-25 | 2018-10-11 | 2018-10-11 | COMP | 2019-02-01 | COMP | 2019-02-01 | INPR | 2019-02-04 | COMP | 2019-03-28 | COMP | Rule 16 | 7 | 77 | 76 |  |  |  | 196
5992 | 2018-06-15 | 2018-07-17 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2019-02-14 | COMP | 2019-03-08 | COMP | Rule 15/16 | 22 | 63 | 23 | 1 | 62 | 16 | 182
6071 | 2018-06-15 | 2018-07-24 | 2018-12-04 | 2018-12-04 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-10-21 | INPR | 2019-07-02 | COMP | Rule 16 | 27 | 92 | 25 | 1 |  |  | 263
6300 | 2018-06-15 | 2018-08-09 | 2018-11-16 | 2018-11-16 | COMP | 2019-02-19 | COMP | 2019-03-22 | COMP | 2019-02-20 | COMP | 2019-04-30 | COMP | Rule 16 | 39 | 70 | 62 | 24 | 0 | 28 | 219
6303 | 2018-06-15 | 2018-08-09 | 2018-12-04 | 2018-12-04 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-02-15 | COMP | 2019-05-02 | COMP | Rule 15/16 | 39 | 80 | 14 | 1 | 38 | 54 | 221
6460 | 2018-06-15 | 2018-08-21 | 2018-09-17 | 2018-09-17 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-01-09 | COMP | 2019-03-21 | COMP | Rule 16 | 47 | 19 | 32 | 1 | 47 | 50 | 191
6482 | 2018-06-15 | 2018-08-21 | 2019-01-17 | 2019-01-17 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2019-04-16 | COMP | 2019-07-22 | COMP | Rule 16 | 47 | 102 | 13 | 1 | 50 | 68 | 276
6812 | 2018-06-15 | 2018-09-12 | 2019-01-12 | 2019-01-12 | COMP | 2019-03-04 | COMP | 2019-08-21 | COMP | 2019-07-22 | COMP | 2019-10-07 | COMP | Rule 16 | 62 | 83 | 34 | 121 | 0 | 33 | 330
6935 | 2018-06-15 | 2018-09-18 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-07-26 | COMP | 2019-09-04 | COMP | Rule 16 | 66 | 103 | 29 | 1 | 85 | 28 | 307
6988 | 2018-06-15 | 2018-09-20 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-08 | COMP | 2018-11-28 | COMP | 2019-07-21 | INPR | 2019-04-01 | COMP | Rule 16 | 68 | 25 | 12 | 12 |  |  | 198
7163 | 2018-06-15 | 2018-10-01 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-05 | COMP | 2019-03-21 | COMP | 2019-08-23 | COMP | 2019-09-11 | COMP | Rule 16 | 75 | 76 | 11 | 32 | 110 | 13 | 312
7519 | 2018-06-15 | 2018-10-18 | 2019-01-02 | 2019-01-02 | COMP | 2019-02-19 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-02-14 | COMP | Rule 15/16 | 88 | 50 | 33 |  | 1 | 12 | 167
7642 | 2018-06-15 | 2018-10-24 | 2018-12-07 | 2018-12-07 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-01-26 | COMP | 2019-01-24 | COMP | Rule 16 | 92 | 30 | 3 | 1 | 31 |  | 152
8269 | 2018-06-15 | 2018-11-21 | 2019-04-18 | 2019-04-18 | COMP | 2020-08-10 | COMP | 2019-09-03 | COMP | 2021-07-13 | COMP | 2021-07-27 | COMP | Rule 16 | 111 | 101 | 332 |  | 468 | 11 | 783
9044 | 2018-06-15 | 2019-01-15 | 2019-02-26 | 2019-02-26 | COMP | 2019-10-16 | COMP | 2019-07-10 | COMP | 2020-05-15 | COMP | 2020-06-08 | COMP | Rule 16 | 146 | 29 | 164 |  | 215 | 16 | 497
10043 | 2018-06-15 | 2019-02-28 | 2019-04-06 | 2019-04-06 | COMP | 2019-07-29 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-09-20 | COMP | Rule 15/16 | 176 | 27 | 79 |  | 1 | 63 | 319
10987 | 2018-06-15 | 2019-04-08 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-10-22 | COMP | Rule 16 | 203 | 98 | 12 | 1 | 1 | 30 | 341
17567 | 2018-06-15 | 2020-02-20 | 2020-03-20 | 2020-12-29 | COMP | 2021-03-01 | COMP | 2021-05-26 | COMP | 2021-04-27 | COMP | 2021-09-15 | COMP | Rule 15/16 | 421 | 22 | 42 | 63 | 0 | 78 | 818
19369 | 2018-06-15 | 2020-05-04 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2022-01-31 | INPR | 2020-10-29 | COMP | Rule 16 | 473 | 21 | 8 | 1 |  |  | 599
5928 | 2018-06-17 | 2018-07-12 | 2018-08-17 | 2018-08-17 | COMP | 2018-09-24 | COMP | 2018-12-11 | COMP | 2018-12-12 | COMP | 2019-01-11 | COMP | Rule 16 | 18 | 27 | 26 | 54 | 2 | 21 | 143
6565 | 2018-06-17 | 2018-08-27 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-03 | COMP | 2018-12-10 | COMP | 2019-10-21 | INPR | 2019-01-03 | COMP | Rule 16 | 50 | 58 | 10 | 6 |  |  | 137
6584 | 2018-06-17 | 2018-08-28 | 2018-12-18 | 2018-12-18 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2019-12-28 | INPR | 2019-09-06 | COMP | Rule 16 | 51 | 77 | 125 | 1 |  |  | 308
6028 | 2018-06-18 | 2018-07-18 | 2018-12-12 | 2018-12-12 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-06-06 | COMP | 2019-07-29 | COMP | Rule 16 | 22 | 102 | 73 | 1 | 50 | 37 | 280
6053 | 2018-06-18 | 2018-07-23 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-01-02 | COMP | 2019-01-26 | COMP | Rule 16 | 25 | 89 | 9 | 1 | 16 | 17 | 152
6191 | 2018-06-18 | 2018-08-03 | 2018-10-18 | 2018-10-18 | COMP | 2018-10-25 | COMP | 2019-03-13 | INPR | 2018-11-07 | COMP | 2019-04-03 | COMP | Rule 16 | 34 | 54 | 6 |  |  |  | 199
6257 | 2018-06-18 | 2018-08-08 | 2019-03-28 | 2019-07-02 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-09-10 | COMP | 2019-09-30 | COMP | Rule 16 | 37 | 159 | 18 | 1 | 32 | 15 | 324
6419 | 2018-06-18 | 2018-08-17 | 2018-11-20 | 2018-11-20 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-05-28 | COMP | 2019-07-12 | COMP | Rule 16 | 44 | 66 | 111 | 1 | 19 | 33 | 269
6479 | 2018-06-18 | 2018-08-21 | 2018-09-25 | 2018-09-25 | COMP | 2019-01-24 | COMP | 2018-12-31 | COMP | 2019-03-21 | COMP | 2019-04-06 | COMP | Rule 16 | 46 | 25 | 82 |  | 56 | 12 | 201
6530 | 2018-06-18 | 2018-08-25 | 2018-10-16 | 2018-10-16 | COMP | 2019-02-08 | COMP | 2019-03-12 | COMP | 2019-05-08 | COMP | 2019-07-11 | COMP | Rule 16 | 49 | 36 | 78 | 22 | 42 | 45 | 268
6531 | 2018-06-18 | 2018-08-25 | 2018-11-10 | 2018-11-10 | COMP | 2019-02-04 | COMP | 2019-04-25 | COMP | 2019-10-24 | COMP | 2019-12-10 | COMP | Rule 16 | 49 | 54 | 55 | 58 | 128 | 31 | 372
6788 | 2018-06-18 | 2018-09-11 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-26 | COMP | 2019-02-08 | COMP | 2019-02-04 | COMP | 2019-03-29 | COMP | Rule 16 | 60 | 45 | 29 | 31 | 0 | 35 | 196
6862 | 2018-06-18 | 2018-09-14 | 2018-12-26 | 2018-12-26 | COMP | 2018-12-31 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2020-01-11 | COMP | Rule 16 | 63 | 70 | 4 | 2 | 1 | 258 | 393
6874 | 2018-06-18 | 2018-09-14 | 2018-11-06 | 2018-11-06 | COMP | 2018-11-28 | COMP | 2019-09-20 | COMP | 2019-09-12 | COMP | 2020-02-29 | COMP | Rule 16 | 63 | 38 | 14 | 206 | 0 | 109 | 426
6890 | 2018-06-18 | 2018-09-15 | 2019-01-14 | 2019-01-30 | COMP | 2019-02-11 | COMP | 2019-03-20 | COMP | 2019-10-22 | COMP | 2019-12-31 | COMP | Rule 16 | 63 | 81 | 9 | 27 | 152 | 47 | 386
7081 | 2018-06-18 | 2018-09-25 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-09-24 | COMP | 2019-11-06 | COMP | Rule 16 | 70 | 158 | 21 | 1 | 74 | 32 | 351
7207 | 2018-06-18 | 2018-10-03 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-05 | COMP | 2018-12-10 | COMP | 2019-01-09 | COMP | 2019-03-18 | COMP | Rule 16 | 76 | 31 | 13 | 4 | 21 | 47 | 187
7265 | 2018-06-18 | 2018-10-04 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-26 | COMP | 2019-02-27 | COMP | 2019-04-08 | COMP | 2019-04-23 | COMP | Rule 16 | 77 | 76 | 22 | 2 | 29 | 12 | 213
7734 | 2018-06-18 | 2018-10-29 | 2019-02-04 | 2019-05-29 | COMP | 2019-05-31 | COMP | 2019-06-01 | COMP | 2019-09-22 | INPR | 2019-06-06 | COMP | Rule 16 | 94 | 65 | 3 | 1 |  |  | 244
7736 | 2018-06-18 | 2018-10-29 | 2019-10-22 | 2019-10-22 | COMP | 2020-02-05 | COMP | 2020-03-13 | COMP | 2024-02-03 | INPR | 2021-11-06 | COMP | Rule 15/16 | 94 | 247 | 71 | 27 |  |  | 854
8172 | 2018-06-18 | 2018-11-19 | 2018-12-27 | 2018-12-27 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2021-01-05 | COMP | 2021-02-05 | COMP | Rule 16 | 108 | 26 | 5 | 1 | 505 | 23 | 663
10035 | 2018-06-18 | 2019-02-28 | 2019-06-13 | 2019-06-13 | COMP | 2021-03-09 | COMP | 2021-03-09 | COMP | 2021-10-04 | COMP | 2021-11-01 | COMP | Rule 16 | 175 | 75 | 436 | 1 | 147 | 21 | 850
10536 | 2018-06-18 | 2019-03-20 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2021-03-26 | COMP | 2021-06-02 | COMP | Rule 16 | 189 | 42 | 10 | 1 | 459 | 48 | 744
3828 | 2018-06-19 | 2018-08-02 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-18 | NOTN | 2018-12-26 | COMP | 2018-12-27 | COMP | 2019-02-08 | COMP | Other | 32 | 81 |  | 20 | 2 | 30 | 161
5681 | 2018-06-19 | 2018-06-26 | 2019-02-07 | 2019-02-07 | COMP | 2019-02-21 | COMP | 2019-03-21 | COMP | 2019-02-12 | COMP | 2019-05-02 | COMP | Rule 16 | 6 | 155 | 10 | 21 | 0 | 31 | 219
5762 | 2018-06-19 | 2018-07-02 | 2018-09-26 | 2018-10-31 | COMP | 2018-11-07 | COMP | 2018-11-07 | COMP | 2018-11-21 | COMP | 2019-03-26 | COMP | Rule 16 | 10 | 61 | 6 | 1 | 10 | 84 | 192
5787 | 2018-06-19 | 2018-07-02 | 2018-08-23 | 2018-08-23 | COMP | 2018-09-07 | COMP | 2018-09-07 | COMP | 2019-01-04 | COMP | 2019-04-16 | COMP | Rule 15/16 | 10 | 38 | 11 | 1 | 81 | 71 | 207
5825 | 2018-06-19 | 2018-07-06 | 2019-03-03 | 2019-03-03 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2019-11-06 | COMP | 2020-02-24 | COMP | Rule 15/16 | 13 | 163 | 88 | 1 | 88 | 72 | 421
5826 | 2018-06-19 | 2018-07-06 | 2019-03-13 | 2019-03-13 | COMP | 2019-11-15 | COMP | 2019-12-23 | COMP | 2019-11-06 | COMP | 2020-06-23 | COMP | Rule 15/16 | 13 | 171 | 174 | 25 | 0 | 127 | 506
5899 | 2018-06-19 | 2018-07-13 | 2018-09-01 | 2018-09-01 | COMP | 2019-01-16 | COMP | 2019-01-16 | COMP | 2019-05-13 | COMP | 2019-06-12 | COMP | Rule 16 | 18 | 36 | 92 | 1 | 82 | 22 | 247
5959 | 2018-06-19 | 2018-07-16 | 2018-12-06 | 2018-12-06 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2018-12-07 | COMP | 2019-03-13 | COMP | Other | 19 | 100 | 8 | 1 | 0 | 59 | 183
5970 | 2018-06-19 | 2018-07-16 | 2018-10-11 | 2018-10-11 | COMP | 2018-10-16 | COMP | 2018-10-16 | COMP | 2019-03-11 | COMP | 2019-07-25 | COMP | Rule 16 | 19 | 63 | 4 | 1 | 98 | 97 | 277
6183 | 2018-06-19 | 2018-08-03 | 2018-10-05 | 2018-10-05 | COMP | 2018-10-26 | COMP | 2019-03-08 | COMP | 2018-11-05 | COMP | 2019-04-24 | COMP | Rule 16 | 33 | 45 | 16 | 89 | 0 | 34 | 213
6224 | 2018-06-19 | 2018-08-04 | 2018-08-13 | 2018-08-13 | COMP | 2018-09-12 | COMP | 2018-09-12 | COMP | 2019-07-17 | COMP | 2019-08-26 | COMP | Rule 16 | 33 | 6 | 22 | 1 | 212 | 29 | 299
6469 | 2018-06-19 | 2018-08-20 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-22 | COMP | 2019-03-02 | COMP | 2019-09-24 | COMP | 2019-08-19 | COMP | Rule 16 | 44 | 84 | 22 | 28 | 144 |  | 294
6561 | 2018-06-19 | 2018-08-27 | 2019-01-17 | 2019-01-17 | COMP | 2019-01-26 | NOTN | 2019-01-26 | COMP | 2019-01-26 | COMP | 2019-03-17 | COMP | Other | 49 | 98 |  | 6 | 0 | 34 | 185
6604 | 2018-06-19 | 2018-08-29 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-03 | COMP | 2019-01-08 | COMP | 2019-01-26 | COMP | 2019-02-04 | COMP | Rule 16 | 51 | 80 | 7 | 4 | 13 | 6 | 157
6680 | 2018-06-19 | 2018-09-06 | 2018-12-18 | 2018-12-18 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2020-11-04 | COMP | 2020-12-20 | COMP | Rule 16 | 56 | 71 | 246 | 1 | 231 | 30 | 630
6682 | 2018-06-19 | 2018-09-06 | 2019-10-03 | 2022-03-30 | COMP | 2022-04-15 | COMP | 2021-04-07 | COMP | 2023-02-09 | COMP | 2023-07-25 | COMP | Rule 15/16 | 56 | 271 | 13 |  | 464 | 115 | 1281
6690 | 2018-06-19 | 2018-09-06 | 2018-12-21 | 2018-12-21 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-04-16 | COMP | 2019-06-27 | COMP | Rule 16 | 56 | 74 | 16 | 1 | 64 | 52 | 258
6789 | 2018-06-19 | 2018-09-11 | 2019-01-28 | 2019-01-28 | COMP | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-04-23 | COMP | 2019-06-03 | COMP | Rule 16 | 59 | 94 | 52 | 1 | 10 | 29 | 240
6825 | 2018-06-19 | 2018-09-12 | 2018-12-31 | 2019-11-21 | COMP | 2020-01-28 | COMP | 2020-05-27 | COMP | 2020-06-01 | COMP | 2021-03-25 | COMP | Rule 16 | 60 | 75 | 44 | 85 | 4 | 206 | 695
7032 | 2018-06-19 | 2018-09-24 | 2019-06-19 | 2020-04-06 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2020-10-06 | COMP | 2020-10-31 | COMP | Rule 15/16 | 68 | 185 | 65 | 1 | 66 | 19 | 598
7542 | 2018-06-19 | 2018-10-19 | 2018-12-17 | 2018-12-17 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-07-24 | COMP | 2019-07-30 | COMP | Rule 15/16 | 87 | 39 | 26 | 1 | 127 | 5 | 280
7567 | 2018-06-19 | 2018-10-19 | 2019-06-08 | 2019-06-08 | COMP | 2019-07-05 | COMP | 2019-08-19 | COMP | 2019-08-05 | COMP | 2019-09-09 | COMP | Rule 16 | 87 | 158 | 19 | 32 | 0 | 15 | 308
8111 | 2018-06-19 | 2018-11-15 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-23 | COMP | 2019-09-13 | COMP | 2019-10-10 | COMP | 2019-12-12 | COMP | Rule 16 | 105 | 96 | 13 | 101 | 20 | 43 | 373
8204 | 2018-06-19 | 2018-11-17 | 2019-03-15 | 2019-03-15 | COMP | 2019-03-25 | COMP | 2019-04-25 | COMP | 2019-04-29 | COMP | 2019-07-16 | COMP | Rule 15/16 | 106 | 79 | 7 | 24 | 3 | 55 | 270
8340 | 2018-06-19 | 2018-11-27 | 2019-01-25 | 2020-12-31 | COMP | 2021-02-24 | COMP | 2021-02-24 | COMP | 2020-10-28 | COMP | 2021-04-20 | COMP | Rule 16 | 111 | 41 | 37 | 1 | 0 | 40 | 713
8386 | 2018-06-19 | 2018-11-28 | 2019-01-15 | 2019-01-15 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-09-10 | COMP | 2019-09-30 | COMP | Rule 16 | 112 | 33 | 90 | 1 | 77 | 15 | 323
9027 | 2018-06-19 | 2019-01-14 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-20 | COMP | 2019-12-16 | COMP | 2020-03-24 | COMP | 2022-02-11 | COMP | Rule 15/16 | 143 | 156 | 20 | 59 | 68 | 478 | 919
9951 | 2018-06-19 | 2019-02-25 | 2019-03-08 | 2019-03-08 | COMP | 2019-04-22 | COMP | 2019-06-21 | COMP | 2019-05-21 | COMP | 2019-06-28 | COMP | Rule 16 | 171 | 10 | 32 | 44 | 0 | 6 | 259
10487 | 2018-06-19 | 2019-03-18 | 2019-05-21 | 2019-05-21 | COMP | 2020-02-19 | COMP | 2021-02-18 | COMP | 2023-12-02 | INPR | 2021-08-03 | COMP | Rule 16 | 186 | 47 | 187 | 253 |  |  | 786
10608 | 2018-06-19 | 2019-03-22 | 2019-05-30 | 2019-05-30 | COMP | 2019-07-10 | COMP | 2019-07-31 | COMP | 2023-04-30 | INPR | 2019-12-13 | COMP | Rule 16 | 190 | 49 | 29 | 16 |  |  | 374
11167 | 2018-06-19 | 2019-04-16 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-31 | COMP | 2019-12-03 | COMP | 2020-06-08 | COMP | 2020-08-10 | COMP | Rule 15/16 | 207 | 112 | 29 | 21 | 130 | 46 | 540
11689 | 2018-06-19 | 2019-05-07 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2019-07-30 | COMP | 2019-08-08 | COMP | Rule 16 | 222 | 14 | 15 | 1 | 32 | 8 | 287
12904 | 2018-06-19 | 2019-06-28 | 2020-01-15 | 2020-01-15 | COMP | 2020-03-23 | COMP | 2020-03-09 | COMP | 2020-05-22 | COMP | 2020-06-26 | COMP | Rule 15/16 | 259 | 137 | 47 |  | 55 | 25 | 509
14922 | 2018-06-19 | 2019-10-04 | 2019-12-02 | 2019-12-02 | COMP | 2020-01-10 | COMP | 2020-01-23 | COMP | 2020-01-28 | COMP | 2020-02-20 | COMP | Rule 16 | 327 | 39 | 28 | 9 | 4 | 17 | 419
3756 | 2018-06-20 | 2018-06-27 | 2018-11-20 | 2018-11-20 | COMP | 2019-03-20 | COMP | 2019-08-21 | COMP |  | INPR | 2020-02-14 | COMP | Rule 15/16 | 6 | 102 | 81 | 109 |  |  | 415
5662 | 2018-06-20 | 2018-06-25 | 2018-10-12 | 2018-10-12 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-10-10 | COMP | 2019-11-19 | COMP | Rule 15/16 | 4 | 78 | 62 | 1 | 189 | 28 | 357
5741 | 2018-06-20 | 2018-06-28 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-17 | COMP | 2018-12-17 | INPR | 2019-04-11 | COMP | 2019-04-30 | COMP | Rule 16 | 7 | 113 | 6 |  |  |  | 216
5827 | 2018-06-20 | 2018-07-06 | 2019-05-31 | 2021-02-18 | COMP | 2021-04-13 | COMP | 2021-11-05 | COMP | 2022-01-12 | COMP | 2022-04-26 | COMP | Rule 15/16 | 12 | 227 | 39 | 146 | 46 | 73 | 969
6149 | 2018-06-20 | 2018-07-30 | 2018-11-10 | 2018-11-10 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2020-03-24 | COMP | 2020-04-22 | COMP | Rule 16 | 28 | 74 | 54 | 1 | 287 | 22 | 462
6161 | 2018-06-20 | 2018-08-02 | 2018-11-05 | 2018-11-16 | COMP | 2018-12-12 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-09-23 | COMP | Rule 16 | 31 | 67 | 17 | 177 | 1 | 21 | 317
6200 | 2018-06-20 | 2018-08-02 | 2018-10-19 | 2018-10-19 | COMP | 2018-12-12 | COMP | 2019-01-04 | COMP | 2019-08-12 | COMP | 2019-09-25 | COMP | Rule 16 | 31 | 56 | 36 | 16 | 153 | 32 | 319
6240 | 2018-06-20 | 2018-08-06 | 2019-06-18 | 2019-06-18 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-08-13 | COMP | 2019-10-03 | COMP | Rule 15/16 | 33 | 218 | 3 | 1 | 38 | 37 | 325
6328 | 2018-06-20 | 2018-08-10 | 2018-11-10 | 2018-11-10 | COMP | 2019-02-07 | COMP | 2019-09-03 | COMP | 2019-11-26 | COMP | 2019-12-18 | COMP | Rule 16 | 37 | 65 | 58 | 145 | 60 | 15 | 376
6450 | 2018-06-20 | 2018-08-20 | 2018-11-05 | 2019-03-02 | COMP | 2019-03-05 | NOTN | 2019-03-05 | COMP | 2019-02-27 | COMP | 2019-04-02 | COMP | Other | 43 | 55 |  | 2 | 0 | 21 | 196
6487 | 2018-06-20 | 2018-08-22 | 2018-10-08 | 2018-10-08 | COMP | 2018-11-13 | COMP | 2019-02-07 | COMP | 2019-03-12 | COMP | 2019-03-19 | COMP | Rule 16 | 45 | 33 | 26 | 58 | 23 | 6 | 186
6562 | 2018-06-20 | 2018-08-27 | 2019-01-03 | 2020-01-10 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2021-04-24 | INPR | 2020-04-15 | COMP | Rule 16 | 48 | 88 | 16 | 1 |  |  | 457
6661 | 2018-06-20 | 2018-09-04 | 2018-10-29 | 2018-10-29 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-10-21 | INPR | 2019-04-04 | COMP | Rule 16 | 53 | 40 | 59 | 1 |  |  | 198
6701 | 2018-06-20 | 2018-09-07 | 2018-10-31 | 2019-11-05 | COMP | 2019-11-08 | COMP | 2019-04-11 | COMP | 2019-09-18 | COMP | 2020-02-28 | COMP | Rule 16 | 56 | 39 | 4 |  | 112 | 111 | 424
6704 | 2018-06-20 | 2018-09-10 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-04 | COMP | 2019-01-29 | COMP | Rule 15/16 | 57 | 41 | 31 | 1 | 10 | 17 | 152
6718 | 2018-06-20 | 2018-09-10 | 2019-01-01 | 2019-01-01 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2020-01-30 | COMP | 2020-03-06 | COMP | Rule 16 | 57 | 77 | 37 | 1 | 235 | 26 | 429
6795 | 2018-06-20 | 2018-09-11 | 2018-12-15 | 2018-12-15 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-06-28 | COMP | 2019-07-24 | COMP | Rule 16 | 58 | 66 | 19 | 1 | 117 | 18 | 275
6856 | 2018-06-20 | 2018-09-13 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-03 | COMP | 2019-07-26 | COMP | 2019-10-08 | COMP | 2020-01-29 | COMP | Rule 16 | 60 | 175 | 6 | 39 | 52 | 76 | 403
6878 | 2018-06-20 | 2018-09-15 | 2019-09-23 | 2019-09-23 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2021-04-13 | COMP | 2021-05-12 | COMP | Rule 16 | 61 | 256 | 83 | 1 | 309 | 22 | 728
6879 | 2018-06-20 | 2018-09-15 | 2019-01-14 | 2020-02-24 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2021-01-15 | COMP | 2021-05-11 | COMP | Rule 16 | 61 | 81 | 28 | 1 | 201 | 81 | 727
7114 | 2018-06-20 | 2018-09-28 | 2018-10-25 | 2018-10-25 | COMP | 2018-12-07 | COMP | 2018-12-07 | INPR | 2018-12-10 | COMP | 2019-04-29 | COMP | Rule 16 | 71 | 20 | 29 |  |  |  | 215
7306 | 2018-06-20 | 2018-10-06 | 2019-02-25 | 2019-03-18 | COMP | 2019-06-12 | COMP | 2020-01-14 | COMP | 2020-03-06 | COMP | 2020-04-11 | COMP | Rule 16 | 76 | 94 | 62 | 148 | 37 | 26 | 454
7443 | 2018-06-20 | 2018-10-12 | 2018-11-27 | 2018-12-06 | COMP | 2018-12-07 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-02-08 | COMP | Rule 16 | 81 | 30 | 2 | 2 | 1 | 42 | 160
7496 | 2018-06-20 | 2018-10-16 | 2019-01-10 | 2019-01-10 | COMP | 2019-02-19 | COMP | 2019-02-28 | COMP | 2019-05-21 | COMP | 2019-07-24 | COMP | Rule 15/16 | 83 | 58 | 27 | 8 | 59 | 45 | 275
7598 | 2018-06-20 | 2018-10-22 | 2018-11-08 | 2019-01-30 | COMP | 2019-07-01 | COMP | 2019-07-22 | COMP | 2019-07-29 | COMP | 2019-08-22 | COMP | Rule 16 | 87 | 14 | 107 | 15 | 6 | 19 | 296
7924 | 2018-06-20 | 2018-11-05 | 2019-04-24 | 2019-04-24 | COMP | 2019-09-03 | COMP | 2020-01-14 | COMP | 2020-02-11 | COMP | 2020-04-01 | COMP | Rule 15/16 | 97 | 116 | 92 | 91 | 20 | 36 | 447
8200 | 2018-06-20 | 2018-11-17 | 2019-03-06 | 2019-03-06 | COMP | 2019-05-03 | COMP | 2019-05-24 | COMP | 2019-12-28 | INPR | 2019-07-27 | COMP | Rule 16 | 105 | 72 | 43 | 16 |  |  | 277
8249 | 2018-06-20 | 2018-11-20 | 2019-02-15 | 2019-02-15 | COMP | 2019-02-19 | COMP | 2019-02-22 | COMP | 2019-04-03 | COMP | 2019-06-04 | COMP | Rule 16 | 107 | 59 | 2 | 4 | 29 | 44 | 240
8394 | 2018-06-20 | 2018-11-30 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-01 | COMP | 2019-05-10 | COMP | 2019-06-20 | COMP | 2019-08-25 | COMP | Rule 16 | 113 | 65 | 19 | 30 | 29 | 46 | 297
9271 | 2018-06-20 | 2019-01-25 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-05-02 | COMP | 2019-05-14 | COMP | Rule 16 | 150 | 37 | 14 | 1 | 20 | 9 | 226
10229 | 2018-06-20 | 2019-03-06 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-25 | COMP | 2019-08-20 | COMP | 2019-08-09 | COMP | 2019-10-16 | COMP | Rule 16 | 177 | 91 | 10 | 19 | 0 | 41 | 334
10693 | 2018-06-20 | 2019-03-26 | 2019-07-31 | 2020-05-21 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-08-26 | COMP | 2020-12-11 | COMP | Rule 16 | 191 | 90 | 59 | 1 | 11 | 74 | 624
5790 | 2018-06-21 | 2018-07-02 | 2018-07-28 | 2018-07-28 | COMP | 2018-08-06 | COMP | 2018-09-04 | COMP | 2020-05-20 | COMP | 2020-06-10 | COMP | Rule 16 | 8 | 19 | 6 | 21 | 430 | 15 | 495
6013 | 2018-06-21 | 2018-07-18 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-05 | COMP | 2019-02-04 | COMP | 2019-06-25 | COMP | 2019-09-25 | COMP | Other | 19 | 82 | 15 | 41 | 100 | 65 | 318
6140 | 2018-06-21 | 2018-07-31 | 2018-12-24 | 2018-12-24 | COMP | 2019-02-22 | COMP | 2019-03-20 | COMP | 2019-12-28 | INPR | 2019-08-21 | COMP | Rule 16 | 28 | 101 | 41 | 19 |  |  | 294
6262 | 2018-06-21 | 2018-08-07 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-02-05 | COMP | 2019-02-25 | COMP | Rule 16 | 33 | 51 | 42 | 1 | 33 | 14 | 169
6478 | 2018-06-21 | 2018-08-20 | 2019-03-14 | 2019-03-14 | COMP | 2019-05-20 | COMP | 2019-05-23 | COMP | 2019-06-06 | COMP | 2019-07-25 | COMP | Rule 16 | 42 | 141 | 48 | 4 | 10 | 35 | 275
6496 | 2018-06-21 | 2018-08-22 | 2018-09-22 | 2018-09-22 | COMP | 2018-11-15 | COMP | 2019-01-15 | COMP | 2019-04-21 | INPR | 2019-01-30 | COMP | Rule 15/16 | 44 | 22 | 38 | 40 |  |  | 152
6536 | 2018-06-21 | 2018-08-27 | 2019-01-04 | 2019-01-04 | COMP | 2019-03-18 | COMP | 2020-08-14 | COMP | 2020-12-22 | COMP | 2021-02-10 | COMP | Rule 15/16 | 47 | 89 | 50 | 359 | 89 | 34 | 663
6852 | 2018-06-21 | 2018-09-13 | 2019-01-05 | 2019-01-05 | COMP | 2019-02-11 | COMP | 2019-07-30 | COMP | 2019-09-04 | COMP | 2019-09-19 | COMP | Rule 16 | 59 | 77 | 25 | 119 | 26 | 12 | 314
6900 | 2018-06-21 | 2018-09-17 | 2018-12-22 | 2018-12-22 | COMP | 2019-01-14 | COMP | 2019-03-21 | COMP | 2019-04-29 | COMP | 2019-07-22 | COMP | Rule 16 | 61 | 67 | 14 | 47 | 28 | 59 | 272
7463 | 2018-06-21 | 2018-10-15 | 2019-01-23 | 2019-01-23 | COMP | 2019-03-14 | NOTN | 2019-04-03 | COMP | 2019-03-14 | COMP | 2019-05-08 | COMP | Other | 81 | 67 |  | 50 | 0 | 26 | 221
7650 | 2018-06-21 | 2018-10-24 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2020-11-25 | COMP | 2020-11-30 | COMP | Rule 16 | 88 | 101 | 18 | 1 | 409 | 2 | 614
7750 | 2018-06-21 | 2018-10-29 | 2019-01-05 | 2019-01-05 | COMP | 2019-01-23 | COMP | 2019-02-04 | COMP | 2019-02-02 | COMP | 2019-04-08 | COMP | Rule 16 | 91 | 45 | 12 | 9 | 0 | 45 | 199
8344 | 2018-06-21 | 2018-11-27 | 2019-04-09 | 2019-04-23 | COMP | 2019-12-16 | COMP | 2019-10-18 | COMP | 2020-01-16 | COMP | 2020-05-20 | COMP | Rule 16 | 109 | 92 | 164 |  | 60 | 88 | 481
8345 | 2018-06-21 | 2018-11-27 | 2020-03-18 | 2020-03-18 | COMP | 2020-10-09 | COMP | 2020-10-29 | COMP | 2022-04-11 | COMP | 2022-05-04 | COMP | Rule 15/16 | 109 | 328 | 146 | 15 | 363 | 18 | 974
8814 | 2018-06-21 | 2018-12-31 | 2019-03-26 | 2019-03-26 | COMP | 2019-05-24 | COMP | 2019-10-03 | COMP | 2019-07-22 | COMP | 2019-11-15 | COMP | Rule 15/16 | 132 | 59 | 44 | 92 | 0 | 31 | 354
8950 | 2018-06-21 | 2019-01-08 | 2019-03-04 | 2019-03-04 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-06-09 | COMP | 2019-09-04 | COMP | Rule 16 | 137 | 38 | 70 | 1 | 0 | 61 | 303
9014 | 2018-06-21 | 2019-01-12 | 2019-03-18 | 2019-07-25 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2020-03-21 | INPR | 2019-11-16 | COMP | Rule 16 | 140 | 44 | 13 | 1 |  |  | 354
9811 | 2018-06-21 | 2019-02-19 | 2019-06-17 | 2019-06-17 | COMP | 2019-07-16 | COMP | 2019-09-25 | COMP | 2019-10-15 | COMP | 2019-11-13 | COMP | Rule 16 | 165 | 84 | 21 | 51 | 15 | 21 | 352
9968 | 2018-06-21 | 2019-02-25 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP |  |  | 2019-12-12 | COMP | Rule 15/16 | 169 | 148 | 51 | 1 |  |  | 371
16035 | 2018-06-21 | 2019-12-06 | 2020-03-13 | 2020-03-13 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-10-26 | COMP | 2020-12-09 | COMP | Rule 15/16 | 367 | 67 | 58 | 1 | 103 | 30 | 621
5794 | 2018-06-22 | 2018-07-03 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2022-07-02 | INPR | 2021-04-27 | COMP | Rule 16 | 8 | 139 | 10 | 1 |  |  | 715
5878 | 2018-06-22 | 2018-07-09 | 2018-11-29 | 2018-11-29 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-05-09 | COMP | Rule 16 | 11 | 100 | 44 | 1 | 1 | 69 | 221
5885 | 2018-06-22 | 2018-07-09 | 2018-10-17 | 2018-10-17 | COMP | 2018-10-31 | COMP | 2018-10-31 | COMP | 2020-05-21 | COMP | 2020-06-03 | COMP | Rule 16 | 11 | 72 | 11 | 1 | 390 | 9 | 489
5989 | 2018-06-22 | 2018-07-17 | 2018-10-27 | 2018-10-27 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2020-02-05 | COMP | 2020-03-03 | COMP | Rule 16 | 17 | 73 | 66 | 1 | 252 | 19 | 424
6015 | 2018-06-22 | 2018-07-18 | 2019-01-01 | 2019-02-13 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-06-26 | COMP | 2019-07-31 | COMP | Other | 18 | 114 | 28 | 1 | 67 | 25 | 278
6056 | 2018-06-22 | 2018-07-23 | 2018-09-24 | 2018-09-24 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-10-21 | INPR | 2019-05-24 | COMP | Rule 15/16 | 21 | 45 | 60 | 1 |  |  | 232
6265 | 2018-06-22 | 2018-08-07 | 2019-01-15 | 2019-07-02 | COMP | 2019-11-25 | COMP | 2020-04-30 | COMP | 2020-01-24 | COMP | 2020-05-09 | COMP | Rule 15/16 | 32 | 110 | 102 | 108 | 0 | 7 | 472
6286 | 2018-06-22 | 2018-08-09 | 2018-10-02 | 2019-01-09 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-03-28 | COMP | 2019-04-16 | COMP | Rule 16 | 34 | 38 | 10 | 1 | 46 | 14 | 204
6398 | 2018-06-22 | 2018-08-15 | 2019-10-30 | 2019-12-05 | COMP | 2020-01-24 | COMP | 2020-03-04 | COMP | 2021-10-23 | INPR | 2020-05-15 | COMP | Rule 15 | 38 | 305 | 34 | 28 |  |  | 477
6408 | 2018-06-22 | 2018-08-16 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-02 | COMP | 2019-03-13 | COMP | 2019-03-28 | COMP | 2019-05-09 | COMP | Rule 15/16 | 39 | 71 | 24 | 49 | 12 | 31 | 221
6437 | 2018-06-22 | 2018-08-18 | 2019-03-18 | 2019-03-18 | COMP | 2019-07-17 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2019-12-09 | COMP | Rule 15/16 | 40 | 143 | 86 | 57 | 1 | 44 | 367
6615 | 2018-06-22 | 2018-08-30 | 2018-09-21 | 2018-09-21 | COMP | 2018-10-18 | COMP | 2018-10-18 | COMP | 2018-12-13 | COMP | 2019-01-10 | COMP | Rule 16 | 49 | 16 | 20 | 1 | 38 | 19 | 138
6647 | 2018-06-22 | 2018-09-04 | 2019-02-12 | 2019-02-12 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2020-10-28 | COMP | 2021-01-14 | COMP | Rule 15/16 | 51 | 110 | 441 | 1 | 0 | 45 | 644
6722 | 2018-06-22 | 2018-09-10 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-01-22 | COMP | 2019-02-28 | COMP | Rule 16 | 55 | 55 | 21 | 1 | 17 | 27 | 171
6871 | 2018-06-22 | 2018-09-14 | 2018-11-02 | 2018-11-13 | COMP | 2018-11-16 | COMP | 2018-11-16 | COMP | 2018-11-15 | COMP | 2019-08-12 | COMP | Rule 15/16 | 59 | 36 | 4 | 1 | 0 | 184 | 286
6896 | 2018-06-22 | 2018-09-15 | 2018-11-28 | 2018-11-28 | COMP | 2019-10-14 | COMP | 2020-05-14 | COMP | 2020-05-06 | COMP | 2020-06-02 | COMP | Rule 16 | 59 | 50 | 222 | 147 | 0 | 13 | 488
7100 | 2018-06-22 | 2018-09-27 | 2020-07-29 | 2021-09-12 | COMP | 2021-09-23 | COMP | 2021-09-28 | COMP | 2021-09-27 | COMP | 2021-10-14 | COMP | Rule 15/16 | 68 | 462 | 9 | 4 | 0 | 13 | 834
7313 | 2018-06-22 | 2018-10-08 | 2018-11-30 | 2018-11-30 | COMP | 2018-12-07 | COMP | 2018-12-20 | COMP | 2019-01-14 | COMP | 2019-01-21 | COMP | Rule 16 | 75 | 37 | 6 | 10 | 16 | 5 | 144
7733 | 2018-06-22 | 2018-10-27 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2020-03-26 | COMP | 2020-04-30 | COMP | Rule 16 | 89 | 99 | 36 | 1 | 219 | 26 | 466
7817 | 2018-06-22 | 2018-11-01 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-04-29 | COMP | 2019-05-29 | COMP | Rule 16 | 93 | 83 | 27 | 1 | 13 | 22 | 234
8329 | 2018-06-22 | 2018-11-27 | 2019-04-08 | 2020-01-09 | COMP | 2020-01-22 | COMP | 2020-02-10 | COMP | 2020-02-14 | COMP | 2020-06-08 | COMP | Rule 16 | 108 | 91 | 9 | 14 | 5 | 80 | 492
8552 | 2018-06-22 | 2018-12-08 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-02 | COMP | 2019-04-03 | COMP | 2019-08-05 | COMP | 2019-09-05 | COMP | Rule 16 | 116 | 71 | 8 | 2 | 87 | 23 | 303
8617 | 2018-06-22 | 2018-12-12 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-28 | COMP | 2019-04-09 | COMP | 2019-06-14 | COMP | 2019-08-15 | COMP | Rule 16 | 119 | 50 | 24 | 9 | 48 | 44 | 289
8805 | 2018-06-22 | 2018-12-29 | 2019-05-04 | 2019-05-04 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-06-18 | COMP | 2019-08-29 | COMP | Rule 16 | 130 | 87 | 25 | 1 | 7 | 52 | 299
9932 | 2018-06-22 | 2019-02-22 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP |  |  | 2020-01-31 | COMP | Rule 16 | 167 | 149 | 51 | 1 |  |  | 403
10272 | 2018-06-22 | 2019-03-08 | 2019-05-15 | 2019-05-15 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2021-04-09 | COMP | 2021-07-13 | COMP | Rule 16 | 177 | 49 | 267 | 1 | 213 | 66 | 768
11680 | 2018-06-22 | 2019-05-07 | 2019-10-22 | 2020-02-04 | COMP | 2020-09-22 | COMP | 2020-09-30 | COMP | 2020-10-26 | COMP | 2020-11-13 | COMP | Rule 16 | 219 | 118 | 163 | 7 | 19 | 14 | 604
11737 | 2018-06-22 | 2019-05-09 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2020-02-04 | COMP | 2020-03-13 | COMP | Rule 16 | 221 | 62 | 20 | 1 | 105 | 28 | 432
12420 | 2018-06-22 | 2019-06-05 | 2020-12-10 | 2020-12-10 | COMP | 2021-04-23 | COMP | 2021-04-23 | COMP | 2021-08-31 | COMP | 2021-06-29 | COMP | Rule 15/16 | 239 | 383 | 93 | 1 | 91 |  | 759
15347 | 2018-06-22 | 2019-10-28 | 2020-02-20 | 2020-02-20 | COMP | 2022-12-29 | COMP | 2022-12-29 | COMP | 2023-05-03 | COMP | 2023-05-28 | COMP | Rule 16 | 340 | 77 | 721 | 1 | 87 | 18 | 1239
15907 | 2018-06-22 | 2019-11-26 | 2020-05-01 | 2020-05-01 | COMP | 2020-07-08 | COMP | 2020-09-04 | COMP | 2022-06-24 | COMP | 2022-08-17 | COMP | Rule 16 | 360 | 108 | 48 | 43 | 453 | 38 | 1045
7955 | 2018-06-23 | 2018-11-07 | 2019-01-24 | 2019-01-24 | COMP | 2019-08-29 | COMP | 2020-02-04 | COMP | 2020-01-07 | COMP | 2020-03-02 | COMP | Rule 15/16 | 96 | 51 | 153 | 107 | 0 | 19 | 422
8975 | 2018-06-23 | 2019-01-10 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-06-06 | COMP | 2019-07-01 | COMP | Rule 16 | 137 | 55 | 10 | 1 | 40 | 18 | 256
10391 | 2018-06-24 | 2019-03-13 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-01 | COMP | 2019-07-26 | COMP | 2019-07-25 | COMP | 2019-08-09 | COMP | Rule 16 | 179 | 60 | 19 | 19 | 0 | 11 | 284
5861 | 2018-06-25 | 2018-07-09 | 2018-12-12 | 2018-12-12 | COMP | 2019-01-08 | NOTN | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-02-06 | COMP | Other | 10 | 109 |  | 18 | 1 | 21 | 155
6045 | 2018-06-25 | 2018-07-22 | 2018-10-12 | 2018-10-12 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2020-01-24 | COMP | 2020-02-04 | COMP | Rule 16 | 19 | 59 | 55 | 1 | 266 | 8 | 404
6063 | 2018-06-25 | 2018-07-23 | 2018-09-20 | 2018-09-20 | COMP | 2018-10-01 | COMP | 2018-10-25 | COMP | 2019-11-24 | INPR | 2019-08-06 | COMP | Rule 16 | 20 | 43 | 8 | 19 |  |  | 281
6120 | 2018-06-25 | 2018-07-30 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-03-25 | COMP | 2019-04-10 | COMP | Rule 16 | 25 | 78 | 10 | 1 | 77 | 13 | 199
6162 | 2018-06-25 | 2018-08-02 | 2018-12-12 | 2018-12-12 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-06-06 | COMP | 2020-07-15 | COMP | Rule 16 | 28 | 91 | 271 | 1 | 103 | 28 | 518
6163 | 2018-06-25 | 2018-08-02 | 2019-01-14 | 2019-01-14 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-07-22 | COMP | 2019-09-21 | COMP | Rule 16 | 28 | 112 | 126 | 1 | 7 | 44 | 313
6254 | 2018-06-25 | 2018-08-08 | 2019-01-14 | 2019-01-14 | COMP | 2019-03-12 | COMP | 2019-04-09 | COMP | 2019-05-17 | COMP | 2019-06-14 | COMP | Rule 16 | 32 | 108 | 40 | 21 | 29 | 20 | 245
6256 | 2018-06-25 | 2018-08-08 | 2018-09-19 | 2018-12-12 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-03-18 | COMP | 2019-04-11 | COMP | Rule 16 | 32 | 30 | 28 | 1 | 38 | 19 | 200
6281 | 2018-06-25 | 2018-08-08 | 2018-12-17 | 2018-12-17 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-01-28 | COMP | 2019-03-18 | COMP | Rule 16 | 32 | 90 | 20 | 1 | 9 | 35 | 182
6410 | 2018-06-25 | 2018-08-16 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-15 | COMP | 2019-01-30 | COMP | 2019-01-16 | COMP | 2019-03-14 | COMP | Rule 16 | 38 | 71 | 33 | 11 | 0 | 31 | 180
6438 | 2018-06-25 | 2018-08-18 | 2019-03-15 | 2019-03-15 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-11-01 | COMP | 2019-12-09 | COMP | Rule 15/16 | 39 | 142 | 111 | 1 | 53 | 24 | 366
6504 | 2018-06-25 | 2018-08-22 | 2018-09-19 | 2018-09-19 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2020-03-09 | COMP | 2020-03-27 | COMP | Rule 16 | 42 | 20 | 193 | 1 | 175 | 15 | 441
6631 | 2018-06-25 | 2018-09-01 | 2018-09-28 | 2019-01-17 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-05-01 | COMP | Rule 16 | 49 | 19 | 34 | 1 | 1 | 40 | 214
6656 | 2018-06-25 | 2018-09-08 | 2018-12-16 | 2018-12-16 | COMP | 2019-02-07 | COMP | 2019-03-11 | COMP | 2019-04-04 | COMP | 2019-05-31 | COMP | Rule 16 | 53 | 67 | 36 | 22 | 19 | 41 | 235
6778 | 2018-06-25 | 2018-09-11 | 2018-12-05 | 2018-12-05 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-03-19 | COMP | 2019-04-19 | COMP | Rule 16 | 55 | 59 | 47 | 1 | 25 | 24 | 206
6851 | 2018-06-25 | 2018-09-13 | 2018-10-11 | 2018-10-11 | COMP | 2018-11-06 | COMP | 2018-11-06 | COMP | 2019-01-09 | COMP | 2019-03-05 | COMP | Rule 16 | 57 | 21 | 19 | 1 | 42 | 38 | 173
6895 | 2018-06-25 | 2018-09-15 | 2018-12-12 | 2018-12-12 | COMP | 2020-01-22 | COMP | 2022-02-15 | COMP | 2022-02-04 | COMP | 2022-03-21 | COMP | Rule 16 | 58 | 60 | 278 | 523 | 0 | 24 | 940
6909 | 2018-06-25 | 2018-09-17 | 2018-10-16 | 2018-10-16 | COMP | 2018-10-30 | COMP | 2018-10-30 | COMP | 2019-05-15 | COMP | 2019-06-27 | COMP | Rule 16 | 59 | 22 | 11 | 1 | 135 | 31 | 254
7242 | 2018-06-25 | 2018-10-04 | 2019-01-04 | 2019-01-04 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2019-07-09 | COMP | 2019-09-10 | COMP | Rule 16 | 72 | 62 | 22 | 1 | 108 | 45 | 305
7385 | 2018-06-25 | 2018-10-09 | 2018-12-21 | 2018-12-21 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-01-12 | COMP | Rule 16 | 75 | 51 | 4 | 1 | 1 | 11 | 138
7551 | 2018-06-25 | 2018-10-19 | 2018-12-11 | 2018-12-11 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-01-17 | COMP | 2019-03-28 | COMP | Rule 16 | 83 | 35 | 20 | 1 | 7 | 49 | 190
7566 | 2018-06-25 | 2018-10-19 | 2019-01-28 | 2019-07-17 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-09-04 | COMP | 2019-10-01 | COMP | Rule 16 | 83 | 66 | 36 | 1 | 0 | 19 | 320
7708 | 2018-06-25 | 2018-10-26 | 2019-01-14 | 2019-01-14 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2019-06-06 | COMP | 2019-08-01 | COMP | Rule 16 | 88 | 52 | 102 | 1 | 0 | 39 | 278
7745 | 2018-06-25 | 2018-10-29 | 2019-04-02 | 2019-04-02 | COMP | 2019-05-30 | COMP | 2019-06-11 | COMP | 2019-06-10 | COMP | 2019-07-25 | COMP | Rule 16 | 89 | 105 | 42 | 9 | 0 | 32 | 273
7775 | 2018-06-25 | 2018-10-30 | 2019-07-02 | 2019-07-02 | COMP | 2019-09-18 | COMP | 2019-12-03 | COMP | 2020-01-23 | COMP | 2020-02-19 | COMP | Rule 16 | 90 | 168 | 55 | 52 | 35 | 19 | 414
7868 | 2018-06-25 | 2018-11-03 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-28 | COMP | 2019-10-22 | COMP | 2019-11-05 | COMP | 2020-01-13 | COMP | Rule 15/16 | 93 | 63 | 35 | 146 | 11 | 45 | 389
7965 | 2018-06-25 | 2018-11-07 | 2019-02-19 | 2019-02-19 | COMP | 2019-04-16 | COMP | 2019-03-14 | COMP | 2019-05-28 | COMP | 2019-06-18 | COMP | Rule 16 | 96 | 68 | 41 |  | 53 | 16 | 247
8177 | 2018-06-25 | 2018-11-18 | 2019-01-08 | 2019-01-08 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-03-18 | COMP | Rule 16 | 102 | 33 | 16 | 1 | 1 | 33 | 182
8410 | 2018-06-25 | 2018-11-29 | 2019-02-07 | 2019-02-07 | COMP | 2019-08-02 | COMP | 2019-08-05 | COMP | 2019-08-03 | COMP | 2019-08-09 | COMP | Rule 16 | 109 | 48 | 124 | 2 | 0 | 5 | 284
9414 | 2018-06-25 | 2019-02-02 | 2019-09-24 | 2019-09-24 | COMP | 2020-01-27 | COMP | 2021-05-17 | COMP | 2021-04-13 | COMP | 2021-06-25 | COMP | Rule 15/16 | 152 | 163 | 84 | 331 | 0 | 29 | 756
10277 | 2018-06-25 | 2019-03-08 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-03 | COMP | 2019-07-31 | COMP | 2019-08-06 | COMP | 2019-09-05 | COMP | Rule 16 | 176 | 56 | 5 | 42 | 5 | 22 | 302
11328 | 2018-06-25 | 2019-04-24 | 2020-05-19 | 2020-05-19 | COMP | 2020-11-16 | COMP | 2022-02-14 | COMP | 2022-07-12 | COMP | 2022-08-08 | COMP | Rule 15/16 | 209 | 270 | 127 | 313 | 103 | 20 | 1037
3775 | 2018-06-26 | 2018-07-09 | 2018-11-21 | 2018-11-21 | COMP | 2020-11-04 | COMP | 2020-11-10 | COMP | 2020-11-17 | COMP | 2021-03-09 | COMP | Rule 15/16 | 9 | 96 | 493 | 5 | 5 | 75 | 678
3778 | 2018-06-26 | 2018-07-10 | 2018-10-27 | 2018-10-27 | COMP | 2018-07-11 | NOTN | 2019-02-08 | COMP | 2020-03-19 | COMP | 2020-05-19 | COMP | Other | 10 | 78 |  | 69 | 279 | 44 | 477
3854 | 2018-06-26 | 2018-08-20 | 2018-08-29 | 2018-08-29 | COMP | 2018-12-18 | COMP | 2019-01-08 | COMP | 2021-02-16 | COMP | 2021-02-21 | COMP | Rule 16 | 39 | 8 | 76 | 14 | 530 | 4 | 666
5841 | 2018-06-26 | 2018-07-07 | 2019-03-13 | 2019-03-13 | COMP | 2019-04-12 | COMP | 2019-06-24 | COMP | 2019-10-10 | COMP | 2019-10-25 | COMP | Rule 15/16 | 8 | 170 | 23 | 51 | 77 | 12 | 337
5855 | 2018-06-26 | 2018-07-09 | 2018-09-28 | 2019-01-27 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-03-13 | COMP | 2019-03-27 | COMP | Rule 16 | 9 | 59 | 14 | 1 | 19 | 11 | 188
5877 | 2018-06-26 | 2018-07-09 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-01-07 | COMP | 2019-02-25 | COMP | Rule 16 | 9 | 69 | 32 | 1 | 26 | 34 | 166
5977 | 2018-06-26 | 2018-07-16 | 2018-10-30 | 2018-10-30 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-04-09 | COMP | Rule 16 | 14 | 76 | 62 | 1 | 2 | 47 | 197
6004 | 2018-06-26 | 2018-07-18 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-07-21 | INPR | 2019-04-10 | COMP | Rule 16 | 16 | 73 | 6 | 1 |  |  | 198
6098 | 2018-06-26 | 2018-07-25 | 2018-10-22 | 2019-03-27 | COMP | 2019-07-01 | COMP | 2019-07-02 | COMP | 2019-08-09 | COMP | 2019-09-16 | COMP | Rule 16 | 21 | 63 | 68 | 2 | 28 | 26 | 308
6160 | 2018-06-26 | 2018-08-02 | 2018-11-05 | 2018-11-05 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-05-01 | COMP | 2019-06-18 | COMP | Rule 16 | 27 | 67 | 114 | 1 | 8 | 34 | 246
6176 | 2018-06-26 | 2018-08-01 | 2018-10-15 | 2019-07-30 | COMP | 2019-08-12 | COMP | 2019-09-16 | COMP | 2019-08-07 | COMP | 2019-10-15 | COMP | Rule 16 | 26 | 53 | 10 | 25 | 0 | 22 | 329
6213 | 2018-06-26 | 2018-08-04 | 2018-08-07 | 2018-08-07 | COMP | 2018-09-05 | COMP | 2018-09-05 | INPR | 2019-11-16 | COMP | 2019-12-04 | COMP | Rule 16 | 28 | 2 | 21 |  |  |  | 362
6252 | 2018-06-26 | 2018-08-08 | 2018-09-19 | 2018-09-19 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2019-07-21 | INPR | 2019-03-15 | COMP | Rule 16 | 31 | 30 | 28 | 1 |  |  | 180
6264 | 2018-06-26 | 2018-08-07 | 2018-11-19 | 2018-11-19 | COMP | 2019-01-16 | COMP | 2019-03-13 | COMP | 2023-05-27 | INPR | 2019-08-03 | COMP | Rule 16 | 30 | 73 | 39 | 39 |  |  | 278
6288 | 2018-06-26 | 2018-08-08 | 2019-02-12 | 2019-02-12 | COMP | 2019-04-19 | COMP | 2019-06-12 | COMP | 2019-09-03 | COMP | 2019-08-26 | COMP | Rule 16 | 31 | 128 | 48 | 38 | 58 |  | 294
6306 | 2018-06-26 | 2018-08-09 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-20 | COMP | 2019-04-04 | COMP | 2019-05-28 | COMP | 2019-06-26 | COMP | Rule 15/16 | 32 | 131 | 22 | 12 | 38 | 22 | 252
6345 | 2018-06-26 | 2018-08-13 | 2018-10-15 | 2018-11-01 | COMP | 2018-11-13 | COMP | 2018-12-05 | COMP | 2021-04-23 | COMP | 2021-04-27 | COMP | Rule 16 | 34 | 45 | 8 | 15 | 600 | 3 | 713
6449 | 2018-06-26 | 2018-08-20 | 2019-05-03 | 2019-05-03 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-09-06 | COMP | 2019-12-06 | COMP | Rule 15/16 | 39 | 177 | 33 | 1 | 56 | 63 | 364
6739 | 2018-06-26 | 2018-09-10 | 2018-10-24 | 2018-10-24 | COMP | 2019-02-21 | COMP | 2019-03-05 | COMP | 2019-03-14 | COMP | 2019-04-02 | COMP | Rule 16 | 53 | 33 | 80 | 9 | 8 | 14 | 192
7079 | 2018-06-26 | 2018-09-25 | 2019-01-04 | 2019-01-04 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | Rule 16 | 64 | 69 | 14 | 1 | 121 | 1 | 265
7082 | 2018-06-26 | 2018-09-25 | 2019-01-05 | 2019-01-05 | COMP | 2019-05-29 | COMP | 2019-11-26 | COMP | 2019-10-16 | COMP | 2019-12-18 | COMP | Rule 16 | 64 | 69 | 100 | 127 | 0 | 15 | 372
7084 | 2018-06-26 | 2018-09-26 | 2019-03-13 | 2019-04-04 | COMP | 2019-05-09 | COMP | 2019-12-05 | COMP | 2019-12-19 | COMP | 2020-01-21 | COMP | Rule 15/16 | 65 | 114 | 26 | 145 | 11 | 21 | 393
7511 | 2018-06-26 | 2018-10-18 | 2019-04-06 | 2021-08-13 | COMP | 2021-09-03 | COMP | 2021-12-08 | COMP | 2022-06-23 | COMP | 2022-06-26 | COMP | Rule 16 | 81 | 115 | 16 | 65 | 138 | 2 | 1006
7518 | 2018-06-26 | 2018-10-18 | 2019-02-11 | 2019-05-08 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-25 | COMP | 2019-07-29 | COMP | Rule 16 | 81 | 77 | 10 | 1 | 25 | 24 | 274
7825 | 2018-06-26 | 2018-11-01 | 2019-01-03 | 2019-02-21 | COMP | 2019-03-13 | COMP | 2019-03-28 | COMP | 2019-04-08 | COMP | 2019-04-30 | COMP | Rule 16 | 91 | 41 | 15 | 12 | 8 | 17 | 212
8231 | 2018-06-26 | 2018-11-19 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-19 | COMP | 2019-07-26 | COMP | 2019-07-16 | COMP | 2019-08-29 | COMP | Rule 16 | 102 | 46 | 36 | 92 | 0 | 25 | 297
8524 | 2018-06-26 | 2018-12-06 | 2019-02-11 | 2019-02-11 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2020-07-21 | COMP | 2020-08-04 | COMP | Rule 16 | 113 | 45 | 92 | 1 | 274 | 11 | 531
8728 | 2018-06-26 | 2018-12-19 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-24 | COMP | 2019-06-03 | COMP | 2019-05-21 | COMP | 2019-06-26 | COMP | Rule 16 | 122 | 64 | 24 | 28 | 0 | 18 | 252
8763 | 2018-06-26 | 2018-12-22 | 2019-03-11 | 2019-03-11 | COMP | 2019-05-03 | COMP | 2019-06-21 | COMP | 2019-07-02 | COMP | 2019-08-06 | COMP | Rule 15/16 | 124 | 52 | 40 | 35 | 8 | 25 | 280
9123 | 2018-06-26 | 2019-01-17 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-15 | COMP | 2019-12-05 | COMP | 2019-11-21 | COMP | 2020-01-03 | COMP | Rule 15/16 | 141 | 60 | 23 | 141 | 0 | 20 | 382
9793 | 2018-06-26 | 2019-02-15 | 2019-05-06 | 2019-05-06 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-09-30 | COMP | 2019-10-16 | COMP | Rule 16 | 161 | 56 | 45 | 1 | 59 | 13 | 330
10431 | 2018-06-26 | 2019-03-15 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-06 | COMP | 2019-11-07 | COMP | 2019-11-13 | COMP | 2020-01-07 | COMP | Rule 16 | 180 | 44 | 16 | 109 | 4 | 36 | 384
11181 | 2018-06-26 | 2019-04-16 | 2019-07-08 | 2019-07-08 | COMP | 2019-10-15 | COMP | 2019-10-29 | COMP | 2019-10-16 | COMP | 2019-11-16 | COMP | Rule 16 | 202 | 58 | 71 | 11 | 0 | 13 | 351
11182 | 2018-06-26 | 2019-04-16 | 2019-07-17 | 2019-07-17 | COMP | 2019-09-18 | COMP | 2019-09-18 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | Rule 16 | 202 | 65 | 45 | 1 | 2 | 1 | 311
11978 | 2018-06-26 | 2019-05-20 | 2019-08-23 | 2019-08-23 | COMP | 2019-10-04 | COMP | 2019-10-24 | COMP | 2019-11-05 | COMP | 2020-02-28 | COMP | Rule 16 | 226 | 68 | 30 | 15 | 9 | 77 | 420
12858 | 2018-06-26 | 2019-06-25 | 2019-08-09 | 2019-08-09 | COMP | 2019-09-09 | COMP | 2019-09-26 | COMP | 2020-02-14 | COMP | 2020-03-02 | COMP | Rule 16 | 251 | 33 | 21 | 14 | 96 | 11 | 421
12960 | 2018-06-26 | 2019-07-01 | 2019-09-04 | 2021-01-14 | COMP | 2021-03-08 | COMP | 2021-03-09 | COMP | 2021-10-19 | COMP | 2022-01-24 | COMP | Rule 15/16 | 255 | 46 | 36 | 2 | 158 | 66 | 900
13020 | 2018-06-26 | 2019-07-05 | 2019-12-17 | 2021-05-12 | COMP | 2021-06-14 | COMP | 2021-06-14 | COMP | 2021-08-17 | COMP | 2021-09-28 | COMP | Rule 15/16 | 258 | 114 | 23 | 1 | 46 | 30 | 820
13656 | 2018-06-26 | 2019-08-06 | 2019-09-20 | 2019-09-20 | COMP | 2019-12-09 | COMP | 2020-02-09 | COMP | 2020-02-09 | COMP | 2020-03-09 | COMP | Rule 15/16 | 280 | 33 | 54 | 42 | 0 | 20 | 426
14742 | 2018-06-26 | 2019-09-25 | 2020-02-19 | 2020-09-11 | COMP | 2020-10-02 | COMP | 2021-04-27 | COMP | 2021-06-07 | COMP | 2021-08-23 | COMP | Rule 16 | 315 | 99 | 16 | 141 | 29 | 55 | 795
15160 | 2018-06-26 | 2019-10-16 | 2020-08-16 | 2022-04-20 | COMP | 2022-05-05 | COMP | 2020-12-15 | COMP | 2022-05-31 | COMP | 2022-06-04 | COMP | Rule 15/16 | 330 | 210 | 12 |  | 368 | 4 | 992
15393 | 2018-06-26 | 2019-10-30 | 2020-03-18 | 2020-03-18 | COMP | 2020-05-11 | COMP | 2020-06-04 | COMP | 2020-07-28 | COMP | 2020-09-17 | COMP | Rule 15/16 | 340 | 94 | 39 | 18 | 39 | 37 | 562
3891 | 2018-06-27 | 2018-09-19 | 2018-09-24 | 2018-09-24 | COMP | 2018-11-28 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-03-12 | COMP | Rule 16 | 59 | 4 | 45 | 10 | 1 | 62 | 176
3915 | 2018-06-27 | 2018-10-01 | 2018-11-01 | 2018-12-20 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-09-03 | COMP | 2019-09-27 | COMP | Rule 16 | 67 | 24 | 149 | 1 | 29 | 19 | 316
5738 | 2018-06-27 | 2018-06-29 | 2018-10-05 | 2018-10-05 | COMP | 2018-10-30 | COMP | 2018-11-08 | COMP | 2018-12-17 | COMP | 2019-03-13 | COMP | Rule 16 | 3 | 69 | 18 | 8 | 25 | 59 | 177
5839 | 2018-06-27 | 2018-07-07 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-31 | COMP | 2019-05-21 | COMP | 2019-06-13 | COMP | 2019-07-25 | COMP | Rule 16 | 7 | 114 | 29 | 78 | 17 | 30 | 271
5840 | 2018-06-27 | 2018-07-07 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-13 | COMP | 2019-02-20 | COMP | 2021-02-27 | INPR | 2019-08-29 | COMP | Rule 15/16 | 7 | 88 | 23 | 46 |  |  | 296
5907 | 2018-06-27 | 2018-07-12 | 2019-03-13 | 2019-04-29 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-05-15 | COMP | 2019-06-01 | COMP | Rule 15/16 | 11 | 167 | 6 | 1 | 8 | 12 | 233
6080 | 2018-06-27 | 2018-07-24 | 2018-09-29 | 2020-12-12 | COMP | 2020-12-31 | COMP | 2021-03-04 | COMP | 2021-03-09 | COMP | 2021-03-25 | COMP | Rule 16 | 19 | 48 | 13 | 43 | 4 | 13 | 689
6090 | 2018-06-27 | 2018-07-25 | 2018-09-07 | 2018-09-07 | COMP | 2018-10-29 | COMP | 2018-11-03 | COMP | 2018-11-09 | COMP | 2019-03-24 | COMP | Rule 16 | 20 | 32 | 37 | 5 | 5 | 89 | 184
6093 | 2018-06-27 | 2018-07-25 | 2018-12-13 | 2018-12-13 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-05-10 | COMP | 2019-05-31 | COMP | Rule 16 | 20 | 98 | 100 | 1 | 4 | 15 | 233
6141 | 2018-06-27 | 2018-07-31 | 2018-10-31 | 2018-10-31 | COMP | 2018-12-26 | COMP | 2019-01-09 | COMP | 2018-12-28 | COMP | 2019-02-06 | COMP | Rule 16 | 24 | 66 | 37 | 10 | 0 | 20 | 153
6249 | 2018-06-27 | 2018-08-07 | 2019-06-28 | 2019-06-28 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-09-21 | COMP | 2020-11-07 | COMP | Rule 15/16 | 29 | 225 | 142 | 1 | 170 | 35 | 597
6379 | 2018-06-27 | 2018-08-14 | 2018-10-05 | 2018-10-05 | COMP | 2018-10-25 | COMP | 2018-12-10 | COMP | 2018-11-02 | COMP | 2019-01-09 | COMP | Rule 16 | 34 | 38 | 15 | 30 | 0 | 21 | 134
6427 | 2018-06-27 | 2018-08-17 | 2018-12-05 | 2018-12-05 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-06-05 | COMP | 2019-07-30 | COMP | Rule 16 | 37 | 75 | 47 | 1 | 80 | 39 | 274
6490 | 2018-06-27 | 2018-08-21 | 2018-08-24 | 2019-03-13 | COMP | 2019-04-23 | COMP | 2019-03-25 | COMP | 2019-10-21 | INPR | 2019-06-28 | COMP | Rule 16 | 39 | 4 | 30 |  |  |  | 253
6499 | 2018-06-27 | 2018-08-22 | 2018-10-10 | 2018-10-10 | COMP | 2019-03-05 | COMP | 2019-03-11 | COMP | 2019-03-06 | COMP | 2019-05-15 | COMP | Rule 16 | 40 | 35 | 98 | 5 | 0 | 48 | 222
6514 | 2018-06-27 | 2018-08-23 | 2018-10-22 | 2018-10-22 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-03-26 | COMP | 2019-04-28 | COMP | Rule 16 | 41 | 42 | 35 | 1 | 71 | 24 | 209
6636 | 2018-06-27 | 2018-09-01 | 2018-11-28 | 2019-03-18 | COMP | 2019-04-08 | COMP | 2019-01-25 | COMP | 2019-02-05 | COMP | 2019-04-25 | COMP | Rule 16 | 47 | 59 | 16 |  | 8 | 57 | 208
6637 | 2018-06-27 | 2018-09-01 | 2019-03-14 | 2019-03-14 | COMP | 2019-08-07 | COMP | 2019-09-05 | COMP | 2020-04-26 | INPR | 2019-12-19 | COMP | Rule 16 | 47 | 131 | 103 | 21 |  |  | 372
6681 | 2018-06-27 | 2018-09-06 | 2018-12-21 | 2018-12-21 | COMP | 2019-03-05 | COMP | 2019-09-20 | COMP | 2019-09-21 | COMP | 2019-10-25 | COMP | Other | 50 | 74 | 49 | 141 | 1 | 25 | 336
6930 | 2018-06-27 | 2018-09-17 | 2018-10-22 | 2018-10-22 | COMP | 2019-01-07 | COMP | 2019-04-29 | COMP | 2019-02-06 | COMP | 2019-06-10 | COMP | Rule 16 | 57 | 26 | 51 | 79 | 0 | 30 | 239
6945 | 2018-06-27 | 2018-09-18 | 2019-01-31 | 2019-01-31 | COMP | 2020-01-27 | COMP | 2020-01-28 | COMP | 2021-06-29 | COMP | 2021-07-22 | COMP | Rule 16 | 58 | 92 | 248 | 2 | 360 | 17 | 772
6971 | 2018-06-27 | 2018-09-21 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-28 | COMP | 2019-02-28 | COMP | 2019-09-04 | COMP | 2019-12-17 | COMP | Rule 15/16 | 61 | 85 | 24 | 1 | 132 | 72 | 370
7034 | 2018-06-27 | 2018-09-24 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-08-21 | COMP | 2019-08-29 | COMP | Rule 16 | 62 | 53 | 6 | 1 | 172 | 7 | 296
7074 | 2018-06-27 | 2018-09-25 | 2018-11-30 | 2019-01-09 | COMP | 2018-12-03 | NOTN | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-04-07 | COMP | Other | 63 | 46 |  | 1 | 1 | 61 | 194
7161 | 2018-06-27 | 2018-09-30 | 2018-11-27 | 2018-11-27 | COMP | 2018-11-30 | COMP | 2019-02-25 | COMP | 2019-03-28 | COMP | 2019-05-08 | COMP | Rule 16 | 66 | 39 | 4 | 58 | 24 | 30 | 217
7481 | 2018-06-27 | 2018-10-16 | 2019-01-09 | 2019-01-09 | COMP | 2020-08-07 | COMP | 2020-08-11 | COMP | 2020-08-06 | COMP | 2020-09-12 | COMP | Rule 16 | 78 | 57 | 400 | 3 | 0 | 23 | 557
7682 | 2018-06-27 | 2018-10-25 | 2019-06-04 | 2019-08-20 | COMP | 2019-09-04 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-01-27 | COMP | Rule 16 | 85 | 151 | 11 | 63 | 1 | 36 | 396
7793 | 2018-06-27 | 2018-10-31 | 2019-03-28 | 2019-06-18 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-12-28 | INPR | 2019-08-05 | COMP | Rule 16 | 89 | 100 | 27 | 1 |  |  | 278
7998 | 2018-06-27 | 2018-11-09 | 2019-05-16 | 2019-05-16 | COMP | 2020-05-13 | COMP | 2020-05-14 | COMP | 2020-08-10 | COMP | 2020-09-18 | COMP | Rule 16 | 96 | 128 | 250 | 2 | 62 | 29 | 562
9635 | 2018-06-27 | 2019-02-09 | 2019-08-05 | 2020-07-10 | COMP | 2019-09-17 | COMP | 2020-08-05 | INPR | 2020-08-12 | COMP | 2020-09-02 | COMP | Other | 155 | 123 |  |  |  |  | 551
9838 | 2018-06-27 | 2019-02-20 | 2020-03-20 | 2020-03-20 | COMP | 2020-03-25 | COMP | 2020-06-01 | INPR | 2020-04-02 | COMP | 2020-05-19 | COMP | Rule 16 | 162 | 273 | 4 |  |  |  | 476
10903 | 2018-06-27 | 2019-04-03 | 2019-05-24 | 2019-05-29 | COMP | 2019-06-10 | COMP | 2019-06-11 | COMP | 2019-07-29 | COMP | 2019-09-10 | COMP | Rule 15/16 | 192 | 38 | 9 | 2 | 34 | 31 | 303
10965 | 2018-06-27 | 2019-04-06 | 2019-06-20 | 2019-06-20 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2020-09-22 | COMP | 2020-10-13 | COMP | Rule 16 | 194 | 53 | 90 | 1 | 229 | 16 | 579
11734 | 2018-06-27 | 2019-05-10 | 2019-07-09 | 2019-07-09 | COMP | 2020-03-27 | COMP | 2020-02-21 | COMP | 2022-07-16 | INPR | 2020-07-21 | COMP | Rule 16 | 219 | 41 | 181 |  |  |  | 520
4009 | 2018-06-28 | 2018-11-27 | 2019-05-30 | 2019-05-30 | COMP | 2020-03-31 | COMP | 2020-08-03 | COMP | 2020-07-17 | COMP | 2020-08-31 | COMP | Rule 16 | 104 | 128 | 210 | 89 | 0 | 21 | 548
5866 | 2018-06-28 | 2018-07-09 | 2018-09-27 | 2018-09-27 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-03-22 | COMP | 2019-06-04 | COMP | Rule 16 | 7 | 58 | 114 | 1 | 7 | 52 | 234
5990 | 2018-06-28 | 2018-07-20 | 2018-09-17 | 2018-09-17 | COMP | 2018-12-03 | COMP | 2019-02-28 | COMP | 2019-03-01 | COMP | 2019-04-11 | COMP | Rule 16 | 16 | 41 | 53 | 60 | 2 | 30 | 197
6029 | 2018-06-28 | 2018-07-18 | 2018-08-22 | 2018-08-22 | COMP | 2018-09-10 | COMP | 2018-09-10 | COMP | 2018-09-18 | COMP | 2019-07-17 | COMP | Rule 16 | 14 | 26 | 13 | 1 | 7 | 208 | 264
6203 | 2018-06-28 | 2018-08-03 | 2018-09-28 | 2018-10-09 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2019-11-24 | INPR | 2019-07-18 | COMP | Rule 16 | 26 | 40 | 14 | 1 |  |  | 265
6515 | 2018-06-28 | 2018-08-23 | 2019-02-19 | 2019-02-21 | COMP | 2019-03-06 | COMP | 2019-05-22 | COMP | 2019-08-15 | COMP | 2019-09-04 | COMP | Rule 15/16 | 40 | 121 | 10 | 56 | 60 | 14 | 298
6984 | 2018-06-28 | 2018-09-20 | 2018-10-29 | 2018-10-29 | COMP | 2019-06-06 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-08-06 | COMP | Rule 16 | 59 | 28 | 151 | 34 | 1 | 10 | 278
7018 | 2018-06-28 | 2018-09-23 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-11 | COMP | 2019-03-04 | COMP | 2019-07-23 | COMP | 2019-08-23 | COMP | Rule 16 | 60 | 76 | 20 | 15 | 100 | 24 | 291
7619 | 2018-06-28 | 2018-10-23 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-14 | COMP | 2019-07-02 | COMP | 2019-05-08 | COMP | 2019-08-07 | COMP | Rule 16 | 82 | 131 | 9 | 35 | 0 | 26 | 279
7752 | 2018-06-28 | 2018-10-29 | 2018-12-17 | 2018-12-17 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-01-23 | COMP | 2019-03-15 | COMP | Rule 16 | 86 | 33 | 15 | 1 | 11 | 37 | 178
7762 | 2018-06-28 | 2018-10-30 | 2018-12-26 | 2018-12-26 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-12-28 | INPR | 2019-08-16 | COMP | Rule 16 | 87 | 38 | 68 | 1 |  |  | 286
7766 | 2018-06-28 | 2018-10-30 | 2019-03-13 | 2019-03-13 | COMP | 2019-04-01 | COMP | 2019-09-10 | COMP | 2019-09-06 | COMP | 2019-10-01 | COMP | Rule 15/16 | 87 | 90 | 14 | 114 | 0 | 16 | 317
8685 | 2018-06-28 | 2018-12-17 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-04-03 | COMP | 2019-04-30 | COMP | Rule 16 | 118 | 48 | 18 | 1 | 10 | 20 | 210
8978 | 2018-06-28 | 2019-01-10 | 2019-02-07 | 2019-02-07 | COMP | 2019-02-13 | COMP | 2019-02-14 | COMP | 2019-05-31 | COMP | 2019-06-21 | COMP | Rule 16 | 134 | 20 | 5 | 2 | 75 | 16 | 247
10389 | 2018-06-28 | 2019-03-13 | 2019-03-15 | 2019-03-15 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-05-01 | COMP | 2019-05-08 | COMP | Rule 16 | 176 | 3 | 13 | 1 | 22 | 6 | 216
10401 | 2018-06-28 | 2019-03-14 | 2019-05-16 | 2019-05-16 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2020-01-08 | COMP | 2020-01-24 | COMP | Rule 16 | 177 | 46 | 45 | 1 | 118 | 12 | 394
3965 | 2018-06-29 | 2018-10-30 | 2019-01-14 | 2019-01-14 | COMP | 2019-05-09 | COMP | 2019-09-11 | COMP | 2020-02-25 | COMP | 2020-03-08 | COMP | Rule 16 | 86 | 50 | 82 | 87 | 113 | 9 | 422
3989 | 2018-06-29 | 2018-11-08 | 2019-07-10 | 2019-07-10 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2019-11-23 | COMP | 2020-01-12 | COMP | Rule 16 | 93 | 166 | 106 | 1 | 0 | 22 | 384
4088 | 2018-06-29 | 2019-01-22 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-26 | COMP | 2020-10-19 | COMP | 2020-10-05 | COMP | 2020-12-01 | COMP | Rule 15/16 | 140 | 154 | 21 | 269 | 0 | 29 | 609
5939 | 2018-06-29 | 2018-07-12 | 2018-10-12 | 2018-10-12 | COMP | 2018-11-08 | COMP | 2019-01-03 | COMP | 2019-01-04 | COMP | 2019-02-12 | COMP | Rule 16 | 9 | 66 | 20 | 36 | 2 | 27 | 155
6222 | 2018-06-29 | 2018-08-03 | 2020-02-20 | 2020-02-20 | COMP | 2021-04-22 | COMP | 2022-07-13 | COMP | 2022-10-31 | COMP | 2023-04-14 | COMP | Rule 15/16 | 25 | 387 | 297 | 309 | 78 | 113 | 1204
6388 | 2018-06-29 | 2018-08-14 | 2018-10-04 | 2018-10-04 | COMP | 2018-10-23 | COMP | 2018-10-23 | COMP | 2018-11-16 | COMP | 2019-06-17 | COMP | Rule 16 | 32 | 37 | 14 | 1 | 18 | 145 | 242
6468 | 2018-06-29 | 2018-08-20 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-29 | COMP | 2019-09-20 | COMP | 2019-08-27 | COMP | 2019-11-15 | COMP | Rule 16 | 36 | 153 | 21 | 102 | 0 | 40 | 348
6509 | 2018-06-29 | 2018-08-23 | 2019-03-11 | 2019-03-11 | COMP | 2019-04-09 | COMP | 2019-06-25 | COMP | 2019-06-17 | COMP | 2019-08-24 | COMP | Rule 15/16 | 39 | 135 | 22 | 55 | 0 | 43 | 290
6576 | 2018-06-29 | 2018-08-28 | 2018-10-04 | 2018-11-30 | COMP | 2018-12-28 | COMP | 2018-12-28 | COMP | 2019-04-12 | COMP | 2019-06-04 | COMP | Rule 16 | 42 | 27 | 20 | 1 | 73 | 37 | 233
6672 | 2018-06-29 | 2018-09-05 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-05 | COMP | 2019-01-04 | COMP | 2018-11-16 | COMP | 2019-01-30 | COMP | Rule 16 | 47 | 36 | 9 | 40 | 0 | 18 | 146
7062 | 2018-06-29 | 2018-09-25 | 2019-04-08 | 2019-04-08 | COMP | 2019-06-20 | COMP | 2019-11-20 | COMP | 2019-11-08 | COMP | 2020-01-19 | COMP | Rule 15/16 | 61 | 133 | 53 | 107 | 0 | 39 | 389
7193 | 2018-06-29 | 2018-10-01 | 2019-01-12 | 2019-01-12 | COMP | 2019-02-06 | COMP | 2019-03-19 | COMP | 2019-03-13 | COMP | 2019-05-02 | COMP | Rule 16 | 65 | 70 | 17 | 29 | 0 | 33 | 211
7262 | 2018-06-29 | 2018-10-04 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2018-11-14 | COMP | 2019-01-01 | COMP | Rule 16 | 68 | 17 | 5 | 1 | 8 | 31 | 126
8219 | 2018-06-29 | 2018-11-19 | 2019-01-03 | 2019-01-10 | COMP | 2019-01-10 | NOTN | 2019-01-10 | COMP | 2019-01-03 | COMP | 2019-03-14 | COMP | Rule 16 | 99 | 30 |  | 1 | 0 | 44 | 176
9215 | 2018-06-29 | 2019-01-22 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-08-28 | COMP | 2019-09-17 | COMP | Rule 16 | 140 | 27 | 5 | 1 | 124 | 14 | 306
9707 | 2018-06-29 | 2019-02-12 | 2019-11-07 | 2019-11-07 | COMP | 2020-03-19 | COMP | 2020-06-09 | COMP | 2020-09-17 | COMP | 2020-10-23 | COMP | Rule 16 | 155 | 189 | 89 | 58 | 72 | 27 | 585
10066 | 2018-06-29 | 2019-02-28 | 2019-03-11 | 2019-05-24 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-07-30 | COMP | 2020-03-26 | COMP | Rule 16 | 166 | 8 | 25 | 1 | 22 | 165 | 436
11120 | 2018-06-29 | 2019-04-13 | 2019-05-22 | 2019-05-22 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-08-23 | COMP | Rule 16 | 197 | 28 | 38 | 1 | 1 | 29 | 290
11258 | 2018-06-29 | 2019-04-19 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-10 | COMP | 2019-11-01 | COMP | 2022-04-06 | COMP | 2022-04-11 | COMP | Rule 16 | 202 | 86 | 15 | 39 | 610 | 4 | 951
26069 | 2018-06-29 | 2021-03-06 | 2021-04-14 | 2021-06-16 | COMP | 2022-04-04 | COMP | 2022-04-19 | COMP |  |  | 2022-05-25 | COMP | Rule 15/16 | 673 | 28 | 202 | 12 |  |  | 983
5806 | 2018-06-30 | 2018-07-06 | 2018-09-12 | 2018-09-12 | COMP | 2019-12-19 | NOTN | 2021-09-15 | NOTN | 2018-07-06 | COMP | 2020-04-23 | COMP | Other | 4 | 48 |  |  |  |  | 455
6938 | 2018-06-30 | 2018-09-18 | 2018-12-03 | 2019-02-06 | COMP | 2019-02-05 | NOTN | 2019-01-16 | COMP | 2018-12-04 | COMP | 2019-03-14 | COMP | Other | 55 | 52 |  |  | 0 | 40 | 175
4131 | 2018-07-02 | 2019-03-21 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-29 | COMP | 2019-05-02 | COMP | 2019-09-16 | COMP | 2019-11-17 | COMP | Rule 15/16 | 180 | 8 | 21 | 4 | 95 | 44 | 347
5946 | 2018-07-02 | 2018-07-13 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-11 | NOTN | 2018-11-16 | COMP | 2018-11-11 | COMP | 2019-01-22 | COMP | Other | 9 | 89 |  | 1 | 0 | 43 | 139
6049 | 2018-07-02 | 2018-07-23 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-10 | COMP | 2019-08-28 | COMP | 2019-08-31 | COMP | 2019-09-30 | COMP | Rule 16 | 15 | 52 | 6 | 222 | 3 | 20 | 314
6062 | 2018-07-02 | 2018-07-23 | 2018-09-11 | 2018-09-11 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-11-08 | COMP | 2020-01-22 | COMP | Rule 15/16 | 15 | 36 | 168 | 1 | 127 | 48 | 390
6086 | 2018-07-02 | 2018-07-25 | 2019-03-15 | 2023-05-04 | COMP | 2023-05-22 | COMP | 2023-08-28 | COMP | 2023-08-22 | COMP | 2023-09-27 | COMP | Rule 16 | 17 | 160 | 13 | 68 | 0 | 22 | 1317
6182 | 2018-07-02 | 2018-08-03 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-14 | COMP | 2019-04-03 | COMP | 2020-02-29 | INPR | 2019-09-12 | COMP | Rule 16 | 24 | 119 | 34 | 15 |  |  | 302
6226 | 2018-07-02 | 2018-08-06 | 2018-10-27 | 2018-10-27 | COMP | 2018-12-07 | COMP | 2019-01-02 | COMP | 2019-01-03 | COMP | 2019-02-05 | COMP | Rule 16 | 25 | 59 | 27 | 17 | 2 | 23 | 149
6665 | 2018-07-02 | 2018-09-05 | 2018-09-15 | 2018-10-31 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2020-05-06 | COMP | 2020-05-13 | COMP | Rule 16 | 46 | 8 | 18 | 1 | 362 | 6 | 469
6737 | 2018-07-02 | 2018-09-10 | 2018-09-28 | 2018-09-28 | COMP | 2018-12-03 | COMP | 2019-01-17 | COMP | 2019-09-11 | COMP | 2019-08-06 | COMP | Rule 16 | 49 | 15 | 44 | 32 | 165 |  | 276
6863 | 2018-07-02 | 2018-09-14 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2019-03-20 | COMP | 2019-04-10 | COMP | Rule 16 | 53 | 52 | 7 | 1 | 70 | 16 | 194
7055 | 2018-07-02 | 2018-09-25 | 2018-10-20 | 2018-10-20 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-03-01 | COMP | Rule 16 | 60 | 19 | 59 | 1 | 1 | 30 | 166
7097 | 2018-07-02 | 2018-09-26 | 2018-11-30 | 2018-11-30 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-07-30 | COMP | Rule 16 | 61 | 45 | 83 | 1 | 1 | 85 | 271
8497 | 2018-07-02 | 2018-12-05 | 2019-02-13 | 2019-02-13 | COMP | 2019-05-08 | COMP | 2019-05-31 | COMP | 2019-07-05 | COMP | 2019-09-09 | COMP | Rule 15/16 | 108 | 48 | 60 | 17 | 25 | 46 | 299
8827 | 2018-07-02 | 2019-01-02 | 2020-03-20 | 2020-08-17 | COMP | 2020-07-07 | COMP | 2020-08-17 | COMP | 2020-10-12 | COMP | 2020-12-11 | COMP | Rule 15/16 | 126 | 306 |  | 30 | 40 | 42 | 616
9550 | 2018-07-02 | 2019-02-07 | 2019-04-03 | 2019-04-03 | COMP | 2019-05-07 | COMP | 2019-06-20 | COMP | 2019-07-30 | COMP | 2019-09-11 | COMP | Rule 16 | 151 | 39 | 25 | 32 | 28 | 31 | 301
9771 | 2018-07-02 | 2019-02-14 | 2019-05-10 | 2019-05-10 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-10-30 | COMP | 2019-12-17 | COMP | Rule 16 | 156 | 61 | 115 | 1 | 7 | 32 | 367
9790 | 2018-07-02 | 2019-02-15 | 2019-05-10 | 2019-05-10 | COMP | 2019-06-12 | COMP | 2020-02-12 | COMP | 2020-02-18 | COMP | 2020-03-04 | COMP | Rule 16 | 157 | 60 | 23 | 168 | 4 | 12 | 419
9908 | 2018-07-02 | 2019-02-22 | 2019-05-28 | 2019-07-03 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-11-21 | COMP | 2020-01-02 | COMP | Rule 16 | 161 | 67 | 76 | 1 | 24 | 27 | 377
10003 | 2018-07-02 | 2019-02-26 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-05-23 | COMP | 2019-07-15 | COMP | Rule 16 | 163 | 57 | 5 | 1 | 3 | 36 | 260
10112 | 2018-07-02 | 2019-03-04 | 2019-03-26 | 2019-03-26 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-07-25 | COMP | Rule 16 | 167 | 17 | 71 | 1 | 1 | 16 | 268
11278 | 2018-07-02 | 2019-04-22 | 2019-06-04 | 2019-06-04 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2022-01-03 | COMP | 2020-02-17 | COMP | Rule 16 | 202 | 31 | 14 | 1 | 638 |  | 407
12068 | 2018-07-02 | 2019-05-22 | 2019-08-29 | 2019-08-29 | COMP | 2021-02-27 | INPR | 2019-11-12 | COMP | 2019-12-03 | COMP | 2020-01-13 | COMP | Rule 15/16 | 224 | 70 |  | 52 | 14 | 28 | 384
12491 | 2018-07-02 | 2019-06-10 | 2020-01-06 | 2020-01-06 | COMP | 2021-11-04 | COMP | 2022-07-14 | COMP | 2022-07-20 | COMP | 2022-08-25 | COMP | Rule 15/16 | 236 | 144 | 465 | 173 | 5 | 27 | 1045
13550 | 2018-07-02 | 2019-07-31 | 2020-01-16 | 2020-01-16 | COMP | 2020-04-29 | COMP | 2020-10-08 | COMP | 2021-01-07 | COMP | 2021-04-09 | COMP | Rule 16 | 272 | 116 | 73 | 115 | 61 | 65 | 697
3842 | 2018-07-03 | 2018-08-13 | 2019-02-26 | 2019-02-26 | COMP | 2019-05-09 | COMP | 2019-05-16 | COMP | 2020-02-29 | INPR | 2019-11-14 | COMP | Rule 15/16 | 29 | 134 | 53 | 6 |  |  | 345
4205 | 2018-07-03 | 2019-07-16 | 2019-07-20 | 2019-07-20 | COMP | 2019-07-25 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-08-27 | COMP | Rule 16 | 260 | 4 | 4 | 13 | 1 | 12 | 290
6158 | 2018-07-03 | 2018-08-01 | 2018-11-05 | 2019-02-02 | COMP | 2019-02-11 | NOTN | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-05-13 | COMP | Rule 16 | 21 | 68 |  | 6 | 1 | 65 | 216
6342 | 2018-07-03 | 2018-08-13 | 2018-11-13 | 2018-11-13 | COMP | 2019-01-14 | COMP | 2019-01-15 | COMP | 2019-01-14 | COMP | 2019-03-18 | COMP | Rule 16 | 29 | 65 | 41 | 2 | 0 | 43 | 176
6354 | 2018-07-03 | 2018-08-14 | 2018-10-27 | 2018-10-27 | COMP | 2018-12-18 | COMP | 2019-01-07 | INPR | 2019-01-15 | COMP | 2019-12-23 | COMP | Other | 30 | 53 | 34 |  |  |  | 370
6377 | 2018-07-03 | 2018-08-14 | 2018-11-27 | 2018-11-27 | COMP | 2019-07-15 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-08-23 | COMP | Rule 16 | 30 | 72 | 159 | 3 | 1 | 28 | 288
6429 | 2018-07-03 | 2018-08-17 | 2018-11-03 | 2018-11-03 | COMP | 2018-12-07 | COMP | 2019-02-12 | COMP | 2019-09-01 | INPR | 2019-05-10 | COMP | Rule 16 | 33 | 55 | 22 | 45 |  |  | 215
6430 | 2018-07-03 | 2018-08-17 | 2018-11-28 | 2018-11-28 | COMP | 2019-08-09 | COMP | 2019-08-21 | COMP | 2020-03-23 | COMP | 2021-10-27 | COMP | Rule 16 | 33 | 70 | 177 | 9 | 146 | 406 | 836
6440 | 2018-07-03 | 2018-08-20 | 2018-08-25 | 2018-08-25 | COMP | 2018-08-28 | COMP | 2018-08-28 | INPR | 2019-09-22 | REQD | 2019-06-11 | COMP | Rule 16 | 34 | 5 | 2 |  |  |  | 236
6444 | 2018-07-03 | 2018-08-18 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-03 | COMP | 2019-01-15 | COMP | 2019-01-22 | COMP | 2019-03-05 | COMP | Rule 16 | 33 | 74 | 20 | 9 | 5 | 30 | 167
6659 | 2018-07-03 | 2018-09-05 | 2019-06-22 | 2019-06-22 | COMP | 2019-10-22 | COMP | 2020-08-10 | COMP | 2020-09-04 | COMP | 2020-09-25 | COMP | Rule 15/16 | 45 | 200 | 85 | 202 | 20 | 15 | 563
6660 | 2018-07-03 | 2018-09-05 | 2019-06-17 | 2020-06-03 | COMP | 2020-06-17 | COMP | 2020-08-31 | COMP | 2020-11-12 | COMP | 2020-12-15 | COMP | Rule 15/16 | 45 | 196 | 11 | 54 | 52 | 22 | 617
6702 | 2018-07-03 | 2018-09-07 | 2019-02-05 | 2019-03-15 | COMP | 2019-06-06 | COMP | 2019-06-21 | COMP | 2021-02-27 | INPR | 2019-12-12 | COMP | Rule 16 | 47 | 102 | 59 | 12 |  |  | 363
6762 | 2018-07-03 | 2018-09-11 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-01-19 | COMP | 2019-02-12 | COMP | Rule 16 | 49 | 54 | 7 | 1 | 30 | 16 | 153
6844 | 2018-07-03 | 2018-09-12 | 2018-12-05 | 2018-12-05 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-04-30 | COMP | 2019-06-22 | COMP | Rule 16 | 50 | 58 | 70 | 1 | 32 | 38 | 244
6869 | 2018-07-03 | 2018-09-13 | 2018-11-03 | 2018-11-03 | COMP | 2018-12-19 | COMP | 2018-12-20 | COMP | 2018-12-28 | COMP | 2019-01-28 | COMP | Rule 16 | 51 | 37 | 30 | 2 | 6 | 20 | 142
6897 | 2018-07-03 | 2018-09-15 | 2018-12-10 | 2018-12-10 | COMP | 2019-03-12 | COMP | 2019-07-09 | COMP | 2020-05-14 | COMP | 2020-06-23 | COMP | Rule 16 | 52 | 58 | 63 | 84 | 215 | 28 | 496
6966 | 2018-07-03 | 2018-09-20 | 2019-01-12 | 2019-02-19 | COMP | 2019-02-19 | NOTN | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-04-30 | COMP | Rule 16 | 56 | 77 |  | 1 | 1 | 51 | 207
7259 | 2018-07-03 | 2018-10-04 | 2018-12-12 | 2018-12-12 | COMP | 2019-07-16 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-10-19 | COMP | Rule 16 | 66 | 47 | 149 | 43 | 1 | 26 | 327
7444 | 2018-07-03 | 2018-10-12 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-12 | COMP | 2019-04-18 | COMP | 2020-02-19 | COMP | 2020-03-18 | COMP | Rule 16 | 72 | 92 | 33 | 5 | 210 | 21 | 428
7564 | 2018-07-03 | 2018-10-19 | 2019-01-14 | 2019-03-11 | COMP | 2019-03-13 | NOTN | 2019-03-13 | COMP | 2019-02-28 | COMP | 2019-03-28 | COMP | Other | 77 | 57 |  | 3 | 0 | 12 | 184
7846 | 2018-07-03 | 2018-11-02 | 2019-09-10 | 2019-09-10 | COMP | 2019-09-30 | COMP | 2019-10-28 | COMP | 2019-10-17 | COMP | 2019-11-17 | COMP | Rule 16 | 87 | 213 | 15 | 21 | 0 | 14 | 346
7902 | 2018-07-03 | 2018-11-06 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-21 | COMP | 2019-03-21 | COMP | 2019-02-27 | COMP | 2019-04-23 | COMP | Rule 15/16 | 89 | 52 | 20 | 21 | 0 | 24 | 202
8028 | 2018-07-03 | 2018-11-14 | 2019-01-10 | 2021-07-27 | COMP | 2021-08-13 | COMP | 2021-08-13 | COMP | 2021-10-12 | COMP | 2021-10-21 | COMP | Rule 16 | 94 | 38 | 14 | 1 | 42 | 8 | 832
8264 | 2018-07-03 | 2018-11-20 | 2019-01-24 | 2019-04-30 | COMP | 2019-06-20 | COMP | 2019-07-11 | COMP | 2023-04-30 | INPR | 2019-08-01 | COMP | Rule 15/16 | 98 | 43 | 37 | 15 |  |  | 272
8441 | 2018-07-03 | 2018-12-03 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-01 | NOTN | 2019-05-17 | COMP | 2019-05-20 | COMP | 2019-07-22 | COMP | Other | 105 | 103 |  | 14 | 2 | 44 | 264
8698 | 2018-07-03 | 2018-12-18 | 2019-02-26 | 2019-02-26 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-10-08 | COMP | 2019-12-09 | COMP | Rule 16 | 116 | 47 | 51 | 1 | 108 | 42 | 360
8727 | 2018-07-03 | 2018-12-19 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-10 | COMP | 2019-05-11 | COMP | 2019-08-15 | COMP | 2019-09-13 | COMP | Rule 16 | 117 | 78 | 22 | 1 | 67 | 21 | 302
8809 | 2018-07-03 | 2018-12-30 | 2019-05-06 | 2019-05-06 | COMP | 2019-06-18 | COMP | 2019-06-18 | COMP | 2019-07-15 | COMP | 2019-11-20 | COMP | Rule 16 | 123 | 88 | 31 | 1 | 19 | 91 | 349
9939 | 2018-07-03 | 2019-02-23 | 2019-05-03 | 2019-10-03 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-10-21 | COMP | 2019-11-15 | COMP | Rule 16 | 160 | 50 | 14 | 1 | 0 | 18 | 346
10594 | 2018-07-03 | 2019-03-21 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-27 | COMP | 2022-09-07 | COMP | 2023-11-07 | INPR | 2022-09-15 | COMP | Rule 16 | 179 | 94 | 19 | 763 |  |  | 1058
10811 | 2018-07-03 | 2019-04-01 | 2019-08-28 | 2019-11-04 | COMP | 2019-09-19 | NOTN | 2019-11-12 | COMP | 2019-09-18 | COMP | 2020-01-14 | COMP | Other | 186 | 106 |  | 6 | 0 | 42 | 384
12171 | 2018-07-03 | 2019-05-28 | 2019-07-11 | 2019-08-16 | COMP | 2019-08-30 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-10-22 | COMP | Rule 16 | 226 | 32 | 11 | 16 | 1 | 22 | 329
14570 | 2018-07-03 | 2019-09-17 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-04 | COMP | 2019-10-04 | INPR | 2021-05-19 | NOTN | 2019-08-01 | COMP | Rule 15/16 | 304 | 2 | 13 |  |  |  | 272
6407 | 2018-07-04 | 2018-08-16 | 2019-01-04 | 2019-01-04 | COMP | 2019-01-11 | COMP | 2019-01-17 | COMP | 2019-02-07 | COMP | 2019-02-25 | COMP | Rule 16 | 31 | 96 | 6 | 5 | 15 | 12 | 160
7420 | 2018-07-04 | 2018-10-12 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-17 | COMP | 2019-01-17 | INPR | 2019-09-22 | REQD | 2019-05-21 | COMP | Rule 16 | 71 | 59 | 7 |  |  |  | 221
8151 | 2018-07-04 | 2018-11-16 | 2019-01-15 | 2019-01-15 | COMP | 2019-02-05 | COMP | 2019-02-06 | COMP | 2019-08-30 | COMP | 2019-09-18 | COMP | Rule 16 | 95 | 39 | 15 | 2 | 145 | 13 | 304
13115 | 2018-07-04 | 2019-07-11 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-10 | COMP | 2020-02-03 | COMP | 2020-01-30 | COMP | 2020-06-07 | COMP | Rule 16 | 256 | 31 | 13 | 99 | 0 | 88 | 483
3821 | 2018-07-05 | 2018-07-30 | 2018-10-16 | 2018-10-16 | COMP | 2019-06-14 | COMP | 2019-06-19 | COMP | 2019-10-14 | COMP | 2019-12-06 | COMP | Rule 15/16 | 18 | 56 | 166 | 4 | 82 | 37 | 358
3824 | 2018-07-05 | 2018-07-30 | 2018-09-26 | 2018-10-08 | COMP | 2019-05-13 | COMP | 2019-05-15 | COMP | 2019-08-13 | COMP | 2019-09-11 | COMP | Rule 15/16 | 18 | 42 | 149 | 3 | 63 | 21 | 299
5894 | 2018-07-05 | 2018-07-09 | 2019-01-28 | 2019-04-22 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2020-04-13 | COMP | 2020-06-25 | COMP | Rule 15/16 | 3 | 139 | 163 | 1 | 84 | 53 | 497
6307 | 2018-07-05 | 2018-08-09 | 2018-10-02 | 2018-12-14 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2020-08-28 | COMP | 2020-10-02 | COMP | Rule 16 | 26 | 38 | 45 | 1 | 387 | 25 | 567
6356 | 2018-07-05 | 2018-08-13 | 2018-09-01 | 2018-09-01 | COMP | 2018-12-04 | COMP | 2018-12-05 | COMP | 2018-11-30 | COMP | 2019-01-11 | COMP | Rule 16 | 28 | 15 | 63 | 2 | 0 | 26 | 131
6423 | 2018-07-05 | 2018-08-17 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2019-01-15 | COMP | Rule 16 | 32 | 33 | 16 | 1 | 1 | 55 | 133
6494 | 2018-07-05 | 2018-08-21 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-23 | COMP | 2019-04-04 | INPR | 2019-02-08 | COMP | 2019-04-04 | COMP | Rule 16 | 34 | 83 | 23 |  |  |  | 188
6580 | 2018-07-05 | 2018-08-28 | 2019-02-01 | 2019-04-22 | COMP | 2019-06-25 | COMP | 2019-10-08 | COMP | 2019-12-09 | COMP | 2020-02-12 | COMP | Rule 15/16 | 39 | 107 | 46 | 74 | 42 | 45 | 403
6891 | 2018-07-05 | 2018-09-15 | 2018-11-21 | 2018-11-21 | COMP | 2019-01-28 | COMP | 2019-01-30 | COMP | 2019-02-05 | COMP | 2019-03-18 | COMP | Rule 16 | 51 | 47 | 44 | 3 | 5 | 29 | 175
7174 | 2018-07-05 | 2018-10-01 | 2018-11-02 | 2018-11-02 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-10-08 | COMP | 2019-11-04 | COMP | Rule 15/16 | 62 | 25 | 224 | 1 | 10 | 20 | 337
7382 | 2018-07-05 | 2018-10-09 | 2019-01-08 | 2019-01-08 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-01-14 | COMP | 2019-03-03 | COMP | Rule 16 | 68 | 61 | 23 | 1 | 0 | 15 | 164
7454 | 2018-07-05 | 2018-10-15 | 2019-03-07 | 2019-03-07 | COMP | 2019-05-15 | COMP | 2019-05-03 | COMP | 2019-04-11 | COMP | 2019-05-29 | COMP | Rule 16 | 72 | 97 | 50 |  | 0 | 18 | 226
7520 | 2018-07-05 | 2018-10-18 | 2018-12-26 | 2018-12-26 | COMP | 2019-02-15 | COMP | 2019-02-15 | COMP | 2019-03-08 | COMP | 2019-04-03 | COMP | Rule 16 | 75 | 46 | 36 | 1 | 15 | 19 | 187
7749 | 2018-07-05 | 2018-10-29 | 2019-02-12 | 2019-06-05 | COMP | 2019-06-18 | COMP | 2019-03-15 | COMP | 2019-04-26 | COMP | 2019-08-13 | COMP | Rule 16 | 82 | 71 | 10 |  | 31 | 76 | 279
7794 | 2018-07-05 | 2018-10-31 | 2019-01-14 | 2019-01-14 | COMP | 2019-03-21 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-06-14 | COMP | Rule 16 | 84 | 49 | 47 | 38 | 1 | 24 | 238
9309 | 2018-07-05 | 2019-01-28 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-26 | COMP | 2019-04-30 | COMP | 2019-05-06 | COMP | 2019-05-28 | COMP | Rule 16 | 141 | 39 | 26 | 3 | 5 | 16 | 225
9845 | 2018-07-05 | 2019-02-20 | 2019-04-30 | 2019-10-29 | COMP | 2019-11-27 | COMP | 2019-08-02 | COMP | 2020-01-23 | COMP | 2020-01-27 | COMP | Rule 16 | 157 | 50 | 21 |  | 118 | 3 | 391
11493 | 2018-07-05 | 2019-04-30 | 2019-07-15 | 2019-07-30 | COMP | 2019-09-23 | COMP | 2019-10-22 | COMP | 2023-04-30 | INPR | 2019-11-04 | COMP | Rule 16 | 206 | 53 | 39 | 22 |  |  | 337
11833 | 2018-07-05 | 2019-05-14 | 2019-07-13 | 2019-07-13 | COMP | 2019-07-23 | COMP | 2019-09-13 | COMP | 2019-10-17 | COMP | 2019-11-05 | COMP | Rule 16 | 216 | 42 | 7 | 38 | 25 | 14 | 338
12476 | 2018-07-05 | 2019-06-11 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-08-22 | COMP | 2019-09-04 | COMP | Rule 15/16 | 235 | 32 | 9 | 1 | 13 | 9 | 294
12939 | 2018-07-05 | 2019-07-03 | 2019-09-16 | 2019-09-16 | COMP | 2019-10-07 | COMP | 2019-11-06 | COMP | 2020-08-26 | COMP | 2020-10-29 | COMP | Rule 16 | 251 | 52 | 16 | 23 | 203 | 46 | 586
4118 | 2018-07-06 | 2019-03-05 | 2019-03-14 | 2019-03-14 | COMP | 2019-05-23 | COMP | 2019-05-29 | INPR | 2019-07-02 | COMP | 2019-07-30 | COMP | Rule 16 | 165 | 8 | 51 |  |  |  | 268
5872 | 2018-07-06 | 2018-07-10 | 2019-01-08 | 2019-02-26 | COMP | 2019-02-26 | NOTN | 2019-03-14 | COMP | 2019-02-01 | COMP | 2019-07-24 | COMP | Other | 3 | 125 |  | 13 | 0 | 93 | 264
6601 | 2018-07-06 | 2018-08-29 | 2018-11-20 | 2019-10-23 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-06-08 | COMP | 2020-07-30 | COMP | Rule 16 | 39 | 58 | 27 | 1 | 130 | 39 | 521
6609 | 2018-07-06 | 2018-08-30 | 2018-12-05 | 2019-04-08 | COMP | 2019-07-01 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-01-17 | COMP | Rule 15/16 | 40 | 66 | 60 | 119 | 1 | 20 | 385
6893 | 2018-07-06 | 2018-09-15 | 2018-11-08 | 2018-11-08 | COMP | 2018-11-28 | COMP | 2018-11-29 | COMP | 2018-11-28 | COMP | 2019-01-02 | COMP | Rule 15/16 | 50 | 39 | 12 | 2 | 0 | 23 | 123
7098 | 2018-07-06 | 2018-09-26 | 2018-11-05 | 2018-11-28 | COMP | 2022-08-21 | REQD | 2019-01-15 | NOTN | 2018-12-31 | COMP | 2019-01-30 | COMP | Rule 16 | 58 | 29 |  |  |  |  | 142
7540 | 2018-07-06 | 2018-10-18 | 2019-01-02 | 2019-01-02 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2020-07-29 | COMP | 2020-09-08 | COMP | Rule 16 | 74 | 50 | 110 | 1 | 289 | 29 | 548
7560 | 2018-07-06 | 2018-10-19 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-08 | COMP | 2019-03-14 | COMP | 2019-10-21 | INPR | 2019-04-20 | COMP | Rule 15/16 | 75 | 74 | 21 | 5 |  |  | 198
7570 | 2018-07-06 | 2018-10-20 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-09-22 | INPR | 2019-05-20 | COMP | Rule 16 | 75 | 43 | 13 | 1 |  |  | 219
7776 | 2018-07-06 | 2018-10-30 | 2019-01-02 | 2019-01-02 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2019-09-20 | COMP | 2019-11-19 | COMP | Rule 16 | 82 | 42 | 159 | 1 | 25 | 42 | 346
8145 | 2018-07-06 | 2018-11-17 | 2019-05-21 | 2019-05-21 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2019-08-20 | COMP | 2019-09-04 | COMP | Rule 16 | 94 | 126 | 19 | 1 | 46 | 11 | 293
8234 | 2018-07-06 | 2018-11-20 | 2019-03-08 | 2019-03-08 | COMP | 2019-04-25 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-05-09 | COMP | Rule 16 | 96 | 73 | 35 | 5 | 1 | 7 | 212
8302 | 2018-07-06 | 2018-11-26 | 2019-01-02 | 2019-01-02 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2020-11-30 | COMP | 2020-12-30 | COMP | Rule 16 | 98 | 26 | 43 | 1 | 440 | 22 | 625
8313 | 2018-07-06 | 2018-11-26 | 2019-02-05 | 2019-07-23 | COMP | 2019-05-07 | NOTN | 2019-07-23 | COMP | 2019-05-07 | COMP | 2019-08-12 | COMP | Other | 98 | 49 |  | 1 | 0 | 15 | 277
8564 | 2018-07-06 | 2018-12-11 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-21 | COMP | 2019-04-19 | COMP | 2019-03-19 | COMP | 2019-06-05 | COMP | Rule 16 | 109 | 54 | 16 | 22 | 0 | 33 | 230
8947 | 2018-07-06 | 2019-01-08 | 2019-04-17 | 2019-04-17 | COMP | 2019-06-21 | NOTN | 2019-06-21 | COMP | 2019-07-09 | COMP | 2019-08-07 | COMP | Other | 127 | 70 |  | 47 | 12 | 22 | 274
9929 | 2018-07-06 | 2019-02-22 | 2019-03-15 | 2019-03-15 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-10-21 | INPR | 2019-07-11 | COMP | Rule 16 | 158 | 16 | 14 | 1 |  |  | 255
10308 | 2018-07-06 | 2019-03-11 | 2019-06-13 | 2019-06-13 | COMP | 2019-07-10 | COMP | 2019-07-11 | COMP | 2019-07-31 | COMP | 2019-08-07 | COMP | Rule 16 | 169 | 68 | 19 | 2 | 15 | 6 | 274
16912 | 2018-07-06 | 2020-01-23 | 2020-03-04 | 2020-03-04 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-12-24 | COMP | 2021-02-10 | COMP | Rule 16 | 388 | 29 | 29 | 1 | 179 | 32 | 653
6619 | 2018-07-08 | 2018-08-31 | 2019-02-07 | 2019-02-07 | COMP | 2019-02-14 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-04-01 | COMP | Rule 16 | 40 | 108 | 6 | 20 | 1 | 13 | 183
3906 | 2018-07-09 | 2018-09-28 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-04 | COMP | 2019-04-23 | COMP | 2019-05-15 | COMP | 2019-07-08 | COMP | Rule 16 | 59 | 30 | 16 | 97 | 17 | 37 | 251
3909 | 2018-07-09 | 2018-09-28 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-24 | COMP | 2019-01-31 | COMP | 2019-06-29 | INPR | 2019-03-07 | COMP | Rule 16 | 59 | 42 | 38 | 6 |  |  | 166
3998 | 2018-07-09 | 2018-11-10 | 2019-07-29 | 2019-07-29 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-11-05 | COMP | 2019-10-18 | COMP | Rule 16 | 89 | 177 | 23 | 1 | 49 |  | 324
5954 | 2018-07-09 | 2018-07-16 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-21 | COMP | 2019-06-05 | COMP | 2019-05-08 | COMP | 2019-09-20 | COMP | Rule 15/16 | 6 | 136 | 16 | 74 | 0 | 76 | 304
6010 | 2018-07-09 | 2018-07-18 | 2018-10-27 | 2018-10-27 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-03-08 | COMP | Rule 16 | 8 | 72 | 58 | 1 | 1 | 31 | 167
6055 | 2018-07-09 | 2018-07-23 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-07 | COMP | 2019-03-20 | COMP | 2019-09-01 | INPR | 2019-04-25 | COMP | Rule 16 | 11 | 90 | 26 | 51 |  |  | 201
6272 | 2018-07-09 | 2018-08-07 | 2018-12-21 | 2018-12-21 | COMP | 2019-01-11 | COMP | 2019-12-16 | COMP | 2020-03-31 | COMP | 2020-06-19 | COMP | Rule 16 | 22 | 95 | 14 | 234 | 73 | 58 | 491
6321 | 2018-07-09 | 2018-08-13 | 2018-08-21 | 2018-08-27 | COMP | 2018-09-06 | COMP | 2018-09-06 | COMP | 2019-05-06 | COMP | 2020-01-30 | COMP | Rule 16 | 26 | 7 | 8 | 1 | 166 | 185 | 392
6520 | 2018-07-09 | 2018-08-24 | 2018-10-05 | 2018-10-05 | COMP | 2018-12-21 | COMP | 2020-03-03 | COMP | 2020-02-12 | COMP | 2020-08-07 | COMP | Rule 16 | 35 | 30 | 53 | 299 | 0 | 113 | 526
6529 | 2018-07-09 | 2018-08-25 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-01-14 | COMP | 2019-02-25 | COMP | Rule 16 | 35 | 58 | 26 | 1 | 13 | 29 | 158
6557 | 2018-07-09 | 2018-08-27 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2020-01-21 | COMP | 2020-06-02 | COMP | Rule 15/16 | 36 | 79 | 17 | 1 | 256 | 94 | 478
6567 | 2018-07-09 | 2018-08-27 | 2019-02-11 | 2019-05-01 | COMP | 2019-06-10 | COMP | 2019-08-20 | COMP | 2019-10-23 | COMP | 2019-11-14 | COMP | Rule 16 | 36 | 114 | 28 | 51 | 46 | 16 | 342
6671 | 2018-07-09 | 2018-09-05 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-26 | COMP | 2019-04-15 | COMP | 2019-03-20 | COMP | 2019-04-29 | COMP | Rule 15/16 | 42 | 105 | 14 | 35 | 0 | 11 | 203
6731 | 2018-07-09 | 2018-09-10 | 2019-03-04 | 2019-03-04 | COMP | 2019-11-08 | COMP | 2019-08-23 | COMP | 2020-07-16 | COMP | 2020-07-29 | COMP | Rule 16 | 45 | 119 | 177 |  | 226 | 10 | 519
6782 | 2018-07-09 | 2018-09-11 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-03-12 | COMP | Rule 16 | 46 | 54 | 38 | 1 | 1 | 34 | 169
6864 | 2018-07-09 | 2018-09-14 | 2018-11-29 | 2018-12-20 | COMP | 2019-01-23 | COMP | 2019-02-20 | COMP | 2019-07-12 | COMP | 2019-07-20 | COMP | Rule 16 | 49 | 52 | 22 | 20 | 101 | 6 | 260
7329 | 2018-07-09 | 2018-10-08 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-04 | COMP | 2019-03-13 | COMP | 2023-04-30 | INPR | 2019-06-19 | COMP | Rule 16 | 65 | 74 | 26 | 8 |  |  | 239
7484 | 2018-07-09 | 2018-10-16 | 2018-11-19 | 2018-11-19 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-04-03 | COMP | Rule 16 | 71 | 24 | 14 | 1 | 1 | 79 | 185
7624 | 2018-07-09 | 2018-10-23 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-25 | COMP | 2019-04-08 | COMP | 2019-04-17 | COMP | 2019-07-01 | COMP | Rule 16 | 76 | 64 | 20 | 31 | 8 | 53 | 247
7791 | 2018-07-09 | 2018-10-31 | 2019-01-16 | 2019-02-14 | COMP | 2019-04-15 | COMP | 2019-05-03 | COMP | 2020-05-07 | COMP | 2020-06-10 | COMP | Rule 15/16 | 82 | 51 | 42 | 15 | 255 | 24 | 484
7881 | 2018-07-09 | 2018-11-03 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-02-01 | COMP | 2019-02-08 | COMP | Rule 15/16 | 84 | 20 | 12 | 1 | 29 | 6 | 148
8153 | 2018-07-09 | 2018-11-17 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-09 | COMP | 2020-05-23 | COMP | 2020-11-17 | COMP | 2021-01-13 | COMP | Rule 16 | 93 | 107 | 12 | 262 | 124 | 38 | 633
8207 | 2018-07-09 | 2018-11-19 | 2019-10-16 | 2020-04-23 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2021-07-08 | COMP | 2021-07-30 | COMP | Rule 15/16 | 94 | 229 | 27 | 1 | 279 | 17 | 771
8447 | 2018-07-09 | 2018-12-03 | 2019-02-23 | 2019-02-23 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-12-28 | INPR | 2019-09-05 | COMP | Rule 16 | 102 | 56 | 96 | 1 |  |  | 293
8720 | 2018-07-09 | 2018-12-19 | 2019-03-12 | 2019-03-12 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-05-29 | COMP | 2019-06-14 | COMP | Rule 16 | 114 | 56 | 19 | 1 | 38 | 13 | 236
8885 | 2018-07-09 | 2019-01-03 | 2019-01-18 | 2019-01-18 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-07-21 | INPR | 2019-03-13 | COMP | Rule 16 | 123 | 12 | 6 | 1 |  |  | 170
9038 | 2018-07-09 | 2019-01-15 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-02-21 | COMP | 2019-05-24 | COMP | Rule 16 | 131 | 8 | 7 | 1 | 13 | 67 | 222
9257 | 2018-07-09 | 2019-01-24 | 2019-06-11 | 2019-06-11 | COMP | 2019-07-03 | COMP | 2019-07-08 | COMP | 2019-11-09 | COMP | 2019-12-11 | COMP | Rule 16 | 137 | 97 | 17 | 3 | 89 | 20 | 359
9871 | 2018-07-09 | 2019-02-21 | 2019-06-20 | 2019-06-20 | COMP | 2019-09-19 | COMP | 2020-07-23 | COMP |  |  | 2020-12-29 | COMP | Rule 15/16 | 156 | 85 | 64 | 213 |  |  | 623
9902 | 2018-07-09 | 2019-02-22 | 2019-03-21 | 2019-03-21 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2021-02-27 | INPR | 2020-02-20 | COMP | Rule 16 | 157 | 20 | 98 | 1 |  |  | 406
11046 | 2018-07-09 | 2019-04-10 | 2019-06-23 | 2019-06-23 | COMP | 2019-12-27 | COMP | 2020-01-09 | COMP | 2020-02-28 | COMP | 2020-03-13 | COMP | Rule 16 | 190 | 52 | 129 | 9 | 35 | 11 | 422
11241 | 2018-07-09 | 2019-04-19 | 2019-07-17 | 2019-09-09 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-03-04 | COMP | 2020-03-22 | COMP | Rule 16 | 197 | 62 | 81 | 1 | 41 | 13 | 427
11374 | 2018-07-09 | 2019-04-24 | 2019-06-08 | 2019-06-08 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2019-08-12 | COMP | 2019-09-09 | COMP | Rule 15/16 | 200 | 32 | 29 | 1 | 17 | 20 | 295
13104 | 2018-07-09 | 2019-07-11 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-21 | COMP | 2019-10-02 | COMP | 2019-10-08 | COMP | 2019-11-12 | COMP | Rule 16 | 254 | 12 | 18 | 30 | 5 | 25 | 340
13272 | 2018-07-09 | 2019-07-18 | 2019-09-17 | 2019-09-17 | COMP | 2020-01-14 | COMP | 2019-11-13 | COMP | 2020-05-26 | COMP | 2020-08-12 | COMP | Rule 16 | 259 | 43 | 81 |  | 133 | 57 | 529
13754 | 2018-07-09 | 2019-08-08 | 2019-09-11 | 2019-09-11 | COMP | 2019-09-17 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-01-02 | COMP | Rule 16 | 274 | 24 | 5 | 46 | 1 | 28 | 373
6075 | 2018-07-10 | 2018-07-23 | 2018-10-27 | 2018-10-27 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2019-02-28 | COMP | 2019-04-02 | COMP | Rule 16 | 10 | 69 | 12 | 1 | 71 | 24 | 183
6154 | 2018-07-10 | 2018-07-31 | 2018-10-04 | 2019-01-14 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-01-24 | COMP | Rule 16 | 16 | 47 | 4 | 1 | 1 | 5 | 136
6238 | 2018-07-10 | 2018-08-06 | 2018-09-26 | 2018-09-26 | COMP | 2018-12-03 | COMP | 2018-12-17 | COMP | 2018-12-15 | COMP | 2019-05-02 | COMP | Rule 16 | 20 | 37 | 46 | 11 | 0 | 95 | 205
6314 | 2018-07-10 | 2018-08-09 | 2018-12-30 | 2018-12-30 | COMP | 2019-01-22 | COMP | 2019-11-05 | COMP | 2019-12-10 | COMP | 2020-01-18 | COMP | Rule 16 | 23 | 97 | 15 | 202 | 23 | 27 | 383
6368 | 2018-07-10 | 2018-08-13 | 2018-12-12 | 2019-06-26 | COMP | 2019-07-30 | COMP | 2021-08-30 | COMP | 2021-09-16 | COMP | 2022-06-27 | COMP | Other | 25 | 84 | 24 | 526 | 13 | 196 | 998
6389 | 2018-07-10 | 2018-08-14 | 2018-08-27 | 2018-08-27 | COMP | 2018-09-14 | COMP | 2019-04-25 | COMP | 2019-04-22 | COMP | 2019-05-20 | COMP | Rule 16 | 26 | 10 | 14 | 153 | 0 | 18 | 217
6448 | 2018-07-10 | 2018-08-20 | 2018-10-12 | 2018-10-12 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-10-21 | INPR | 2019-04-16 | COMP | Rule 16 | 30 | 39 | 95 | 1 |  |  | 193
6484 | 2018-07-10 | 2018-08-21 | 2018-12-10 | 2018-12-10 | COMP | 2019-03-29 | COMP | 2020-03-12 | COMP | 2020-04-30 | COMP | 2020-05-20 | COMP | Rule 15/16 | 31 | 76 | 76 | 240 | 36 | 15 | 469
6549 | 2018-07-10 | 2018-08-27 | 2019-01-14 | 2019-01-14 | COMP | 2019-05-02 | NOTN | 2019-05-29 | COMP | 2019-04-18 | COMP | 2019-07-13 | COMP | Rule 16 | 35 | 95 |  | 95 | 0 | 32 | 254
6575 | 2018-07-10 | 2018-08-28 | 2018-09-01 | 2018-09-01 | COMP | 2018-10-09 | COMP | 2018-10-09 | COMP | 2019-10-21 | INPR | 2019-02-22 | COMP | Rule 16 | 36 | 4 | 26 | 1 |  |  | 156
6597 | 2018-07-10 | 2018-08-29 | 2018-10-27 | 2020-01-23 | COMP | 2020-01-30 | COMP | 2020-10-12 | COMP | 2021-03-11 | COMP | 2021-04-30 | COMP | Rule 16 | 37 | 42 | 6 | 180 | 102 | 37 | 707
6651 | 2018-07-10 | 2018-09-04 | 2018-09-07 | 2018-09-07 | COMP | 2018-10-01 | COMP | 2018-10-01 | COMP | 2019-11-06 | COMP | 2019-11-07 | COMP | Rule 16 | 40 | 4 | 17 | 1 | 278 | 2 | 337
6794 | 2018-07-10 | 2018-09-11 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-03-29 | COMP | 2019-04-12 | COMP | Rule 16 | 45 | 50 | 25 | 1 | 64 | 11 | 191
6803 | 2018-07-10 | 2018-09-11 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-18 | COMP | 2019-04-19 | COMP | 2019-04-19 | COMP | 2019-04-29 | COMP | Rule 15/16 | 45 | 40 | 29 | 85 | 1 | 7 | 202
6811 | 2018-07-10 | 2018-09-12 | 2019-01-12 | 2019-01-12 | COMP | 2019-06-28 | COMP | 2020-03-23 | INPR | 2020-03-13 | COMP | 2020-05-01 | COMP | Rule 15/16 | 46 | 83 | 117 |  |  |  | 456
7053 | 2018-07-10 | 2018-09-25 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-10 | COMP | 2018-12-10 | COMP | 2019-07-16 | COMP | 2019-08-15 | COMP | Rule 16 | 55 | 45 | 8 | 1 | 151 | 23 | 278
7247 | 2018-07-10 | 2018-10-03 | 2019-02-01 | 2019-02-01 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-01-28 | COMP | 2020-02-24 | COMP | Rule 16 | 61 | 82 | 250 | 1 | 0 | 17 | 407
7421 | 2018-07-10 | 2018-10-12 | 2019-04-23 | 2019-04-23 | COMP | 2019-08-15 | COMP | 2019-10-31 | COMP | 2021-02-27 | INPR | 2019-12-06 | COMP | Rule 16 | 68 | 131 | 81 | 55 |  |  | 355
7432 | 2018-07-10 | 2018-10-12 | 2018-11-06 | 2018-11-06 | COMP | 2018-12-19 | COMP | 2019-01-09 | COMP | 2020-12-01 | COMP | 2020-12-03 | COMP | Rule 16 | 68 | 18 | 29 | 14 | 478 | 3 | 605
7618 | 2018-07-10 | 2018-10-23 | 2019-06-07 | 2019-09-30 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-01-03 | COMP | 2020-01-31 | COMP | Rule 15/16 | 75 | 156 | 16 | 1 | 50 | 20 | 392
7769 | 2018-07-10 | 2018-10-30 | 2018-12-07 | 2018-12-07 | COMP | 2019-01-02 | COMP | 2019-03-04 | COMP | 2019-03-25 | COMP | 2019-04-11 | COMP | Rule 16 | 80 | 26 | 17 | 42 | 16 | 14 | 190
7946 | 2018-07-10 | 2018-11-06 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-04-29 | COMP | 2019-04-30 | COMP | Rule 16 | 85 | 72 | 8 | 1 | 40 | 2 | 203
7959 | 2018-07-10 | 2018-11-07 | 2019-02-04 | 2019-02-04 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2022-01-30 | INPR | 2020-09-17 | COMP | Rule 16 | 86 | 58 | 33 | 1 |  |  | 553
8227 | 2018-07-10 | 2018-11-19 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-08 | COMP | 2019-03-11 | COMP | 2019-10-01 | COMP | 2019-12-19 | COMP | Rule 16 | 93 | 46 | 29 | 2 | 144 | 55 | 364
8262 | 2018-07-10 | 2018-11-20 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-06-05 | COMP | 2019-07-01 | COMP | Rule 16 | 94 | 62 | 11 | 1 | 64 | 19 | 246
8273 | 2018-07-10 | 2018-11-21 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-06-07 | COMP | 2019-06-18 | COMP | Rule 16 | 95 | 44 | 10 | 1 | 84 | 8 | 237
8377 | 2018-07-10 | 2018-11-28 | 2019-01-17 | 2019-01-17 | COMP | 2019-01-28 | COMP | 2019-01-30 | COMP | 2018-12-14 | COMP | 2019-02-08 | COMP | Rule 16 | 98 | 35 | 7 | 3 | 0 | 8 | 147
8443 | 2018-07-10 | 2018-12-03 | 2019-03-06 | 2019-03-18 | COMP | 2019-04-15 | COMP | 2019-05-07 | COMP | 2019-05-03 | COMP | 2019-08-28 | COMP | Rule 16 | 101 | 64 | 21 | 17 | 0 | 80 | 287
8563 | 2018-07-10 | 2018-12-10 | 2019-04-08 | 2019-04-08 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2020-02-04 | COMP | 2020-04-17 | COMP | Rule 15/16 | 106 | 82 | 95 | 1 | 114 | 53 | 446
8842 | 2018-07-10 | 2019-01-02 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | 2019-11-18 | COMP | 2019-12-04 | COMP | Rule 15/16 | 121 | 131 | 13 | 2 | 80 | 11 | 353
9584 | 2018-07-10 | 2019-02-07 | 2019-04-26 | 2019-08-20 | COMP | 2019-09-10 | COMP | 2019-09-17 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | Rule 16 | 146 | 56 | 15 | 6 | 20 | 1 | 319
10690 | 2018-07-10 | 2019-03-26 | 2019-04-03 | 2019-04-03 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-04-19 | COMP | 2019-05-22 | COMP | Rule 16 | 178 | 7 | 11 | 1 | 3 | 24 | 219
10747 | 2018-07-10 | 2019-03-28 | 2019-06-12 | 2019-06-12 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-12 | COMP | 2020-02-07 | COMP | Rule 16 | 180 | 54 | 142 | 1 | 5 | 19 | 397
12732 | 2018-07-10 | 2019-06-21 | 2019-09-21 | 2019-09-21 | COMP | 2019-10-10 | COMP | 2019-10-31 | COMP |  | INPR | 2019-12-18 | COMP | Rule 15/16 | 240 | 64 | 14 | 16 |  |  | 363
20600 | 2018-07-10 | 2020-06-29 | 2020-08-19 | 2020-08-19 | COMP | 2021-03-12 | COMP | 2021-03-12 | COMP | 2023-07-28 | COMP | 2023-12-22 | COMP | Rule 16 | 496 | 38 | 140 | 1 | 599 | 102 | 1371
5991 | 2018-07-11 | 2018-07-20 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-01-08 | COMP | 2019-03-11 | COMP | Rule 16 | 8 | 76 | 40 | 1 | 3 | 43 | 166
6064 | 2018-07-11 | 2018-07-23 | 2018-12-11 | 2018-12-11 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-07-21 | INPR | 2019-03-13 | COMP | Rule 15/16 | 9 | 98 | 28 | 1 |  |  | 168
6088 | 2018-07-11 | 2018-07-26 | 2018-11-07 | 2019-04-17 | COMP | 2019-06-14 | COMP | 2019-06-29 | COMP | 2019-11-12 | COMP | 2019-12-19 | COMP | Rule 15/16 | 12 | 74 | 42 | 11 | 94 | 26 | 363
6202 | 2018-07-11 | 2018-08-03 | 2018-09-24 | 2018-09-24 | COMP | 2018-10-02 | COMP | 2018-10-12 | COMP | 2018-10-23 | COMP | 2019-03-21 | COMP | Rule 16 | 18 | 36 | 7 | 9 | 8 | 101 | 174
6311 | 2018-07-11 | 2018-08-09 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-31 | COMP | 2020-01-10 | COMP | 2020-11-04 | COMP | 2020-11-07 | COMP | Rule 16 | 22 | 81 | 39 | 238 | 210 | 3 | 588
6374 | 2018-07-11 | 2018-08-14 | 2018-09-05 | 2018-09-05 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-01-18 | COMP | 2019-03-13 | COMP | Rule 15/16 | 25 | 16 | 75 | 1 | 19 | 37 | 168
6474 | 2018-07-11 | 2018-08-20 | 2018-11-16 | 2019-03-18 | COMP | 2019-07-15 | COMP | 2019-12-30 | COMP | 2019-11-26 | COMP | 2020-02-08 | COMP | Rule 16 | 29 | 63 | 84 | 116 | 0 | 28 | 396
6498 | 2018-07-11 | 2018-08-22 | 2019-03-24 | 2019-03-24 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-02-21 | COMP | 2020-03-13 | COMP | Rule 15/16 | 31 | 145 | 220 | 1 | 11 | 16 | 420
6554 | 2018-07-11 | 2018-08-27 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-05-07 | COMP | 2019-05-20 | COMP | Rule 16 | 34 | 115 | 9 | 1 | 52 | 10 | 216
6607 | 2018-07-11 | 2018-08-30 | 2019-06-19 | 2019-12-03 | COMP | 2020-05-26 | COMP | 2020-06-23 | COMP | 2020-05-27 | COMP | 2020-08-23 | COMP | Rule 15/16 | 37 | 201 | 121 | 21 | 0 | 44 | 534
6670 | 2018-07-11 | 2018-09-05 | 2018-12-19 | 2019-01-14 | COMP | 2019-01-23 | COMP | 2022-02-09 | COMP | 2022-06-16 | COMP | 2022-07-14 | COMP | Rule 16 | 40 | 73 | 7 | 769 | 90 | 19 | 1009
6693 | 2018-07-11 | 2018-09-06 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-15 | COMP | 2019-04-09 | COMP | 2019-03-13 | COMP | 2019-09-26 | COMP | Rule 16 | 41 | 57 | 33 | 59 | 0 | 120 | 306
6796 | 2018-07-11 | 2018-09-11 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-02-07 | COMP | Rule 16 | 44 | 80 | 9 | 1 | 1 | 15 | 145
6956 | 2018-07-11 | 2018-09-19 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-27 | COMP | 2019-01-16 | COMP | 2019-12-02 | COMP | 2020-02-14 | COMP | Rule 15/16 | 50 | 38 | 30 | 14 | 221 | 52 | 401
6960 | 2018-07-11 | 2018-09-19 | 2019-01-23 | 2019-01-23 | COMP | 2019-06-25 | COMP | 2019-08-14 | COMP | 2020-02-04 | COMP | 2020-02-13 | COMP | Rule 16 | 50 | 85 | 108 | 36 | 118 | 8 | 400
6980 | 2018-07-11 | 2018-09-20 | 2019-02-20 | 2019-03-07 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-06-08 | COMP | 2019-07-13 | COMP | Rule 16 | 51 | 103 | 15 | 1 | 52 | 24 | 253
7051 | 2018-07-11 | 2018-09-24 | 2018-11-01 | 2018-11-01 | COMP | 2018-12-06 | COMP | 2019-06-24 | COMP | 2019-12-28 | INPR | 2019-08-05 | COMP | Rule 16 | 53 | 29 | 23 | 138 |  |  | 269
7138 | 2018-07-11 | 2018-09-28 | 2019-01-22 | 2019-01-22 | COMP | 2019-01-30 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-04-12 | COMP | Rule 16 | 57 | 77 | 7 | 10 | 1 | 43 | 190
7225 | 2018-07-11 | 2018-10-03 | 2018-11-10 | 2018-11-10 | COMP | 2019-01-25 | COMP | 2019-02-07 | COMP | 2019-09-22 | INPR | 2019-06-12 | COMP | Rule 15/16 | 60 | 28 | 49 | 10 |  |  | 232
7226 | 2018-07-11 | 2018-10-03 | 2018-11-10 | 2018-11-10 | COMP | 2019-01-25 | COMP | 2019-02-07 | COMP | 2019-09-22 | INPR | 2019-06-12 | COMP | Rule 15/16 | 60 | 28 | 49 | 10 |  |  | 232
7245 | 2018-07-11 | 2018-10-04 | 2018-10-08 | 2018-10-08 | COMP | 2019-01-16 | NOTN | 2019-01-14 | COMP | 2022-01-30 | INPR | 2020-07-15 | COMP | Rule 16 | 61 | 3 |  | 66 |  |  | 507
7264 | 2018-07-11 | 2018-10-04 | 2019-02-12 | 2019-02-12 | COMP | 2019-04-26 | COMP | 2019-06-27 | COMP | 2019-05-08 | COMP | 2019-08-05 | COMP | Rule 16 | 61 | 88 | 53 | 44 | 0 | 27 | 269
7299 | 2018-07-11 | 2018-10-06 | 2018-10-24 | 2018-10-24 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-04-29 | COMP | 2019-05-03 | COMP | Rule 16 | 62 | 13 | 128 | 1 | 0 | 4 | 205
7323 | 2018-07-11 | 2018-10-08 | 2018-10-15 | 2019-01-17 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-03-04 | COMP | 2019-04-12 | COMP | Rule 16 | 63 | 6 | 19 | 1 | 13 | 30 | 190
7335 | 2018-07-11 | 2018-10-08 | 2018-11-01 | 2018-12-05 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-03-13 | COMP | 2019-04-11 | COMP | Rule 16 | 63 | 19 | 18 | 1 | 50 | 22 | 189
7389 | 2018-07-11 | 2018-10-10 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-05 | COMP | 2019-03-07 | COMP | 2019-03-08 | COMP | 2019-03-20 | COMP | Rule 16 | 65 | 29 | 10 | 63 | 2 | 9 | 173
7929 | 2018-07-11 | 2018-11-05 | 2018-11-14 | 2018-11-14 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-01-31 | COMP | 2019-03-27 | COMP | Rule 16 | 83 | 7 | 38 | 1 | 15 | 39 | 178
8143 | 2018-07-11 | 2018-11-17 | 2019-03-10 | 2019-03-10 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-10-22 | COMP | Rule 16 | 91 | 74 | 139 | 2 | 1 | 20 | 324
8175 | 2018-07-11 | 2018-11-16 | 2019-02-15 | 2019-02-25 | COMP | 2019-03-07 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-05-17 | COMP | Rule 16 | 91 | 61 | 9 | 5 | 1 | 48 | 215
8358 | 2018-07-11 | 2018-11-28 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-11-12 | COMP | 2020-02-25 | COMP | Rule 15/16 | 97 | 141 | 40 | 1 | 63 | 70 | 407
8517 | 2018-07-11 | 2018-12-06 | 2019-03-04 | 2019-03-04 | COMP | 2019-05-03 | COMP | 2019-11-04 | COMP | 2021-01-30 | INPR | 2020-01-21 | COMP | Rule 16 | 103 | 59 | 45 | 129 |  |  | 383
8663 | 2018-07-11 | 2018-12-13 | 2019-06-07 | 2019-06-07 | COMP | 2019-07-10 | COMP | 2019-09-05 | COMP | 2019-07-11 | COMP | 2019-09-27 | COMP | Rule 15/16 | 108 | 122 | 23 | 41 | 0 | 17 | 307
9094 | 2018-07-11 | 2019-01-16 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-30 | COMP | 2019-05-10 | COMP | 2019-06-10 | COMP | 2019-07-24 | COMP | Rule 16 | 130 | 58 | 16 | 9 | 21 | 32 | 261
10023 | 2018-07-11 | 2019-02-27 | 2019-04-02 | 2019-04-02 | COMP | 2019-04-05 | COMP | 2019-04-26 | COMP | 2019-04-11 | COMP | 2019-05-24 | COMP | Rule 16 | 158 | 25 | 4 | 16 | 0 | 21 | 220
10046 | 2018-07-11 | 2019-02-28 | 2019-07-19 | 2020-02-06 | COMP | 2020-02-28 | COMP | 2019-09-05 | COMP | 2020-04-28 | COMP | 2020-06-22 | COMP | Rule 16 | 159 | 100 | 16 |  | 162 | 39 | 490
10485 | 2018-07-11 | 2019-03-18 | 2019-06-11 | 2019-06-11 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-12-29 | INPR | 2019-08-16 | COMP | Rule 16 | 171 | 61 | 19 | 1 |  |  | 278
11251 | 2018-07-11 | 2019-04-20 | 2019-07-23 | 2019-07-23 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-05-26 | COMP | 2020-07-10 | COMP | Rule 15/16 | 195 | 65 | 204 | 1 | 9 | 34 | 504
3834 | 2018-07-12 | 2018-08-06 | 2019-02-28 | 2019-02-28 | COMP | 2019-04-10 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-10-14 | COMP | Rule 16 | 18 | 141 | 30 | 104 | 1 | 28 | 317
4027 | 2018-07-12 | 2018-12-10 | 2019-01-14 | 2018-12-28 | COMP | 2019-03-04 | COMP | 2019-06-11 | COMP | 2019-04-12 | COMP | 2019-08-09 | COMP | Rule 16 | 104 | 24 | 44 | 71 | 0 | 43 | 272
4046 | 2018-07-12 | 2018-12-29 | 2019-08-12 | 2019-07-30 | COMP | 2021-01-20 | COMP | 2021-01-20 | INPR | 2021-01-25 | COMP | 2021-02-19 | COMP | Rule 16 | 117 | 156 | 371 |  |  |  | 655
5951 | 2018-07-12 | 2018-07-16 | 2018-09-28 | 2019-06-20 | COMP | 2019-06-27 | COMP | 2018-10-11 | COMP | 2019-08-06 | COMP | 2019-09-04 | COMP | Rule 16 | 3 | 54 | 6 |  | 205 | 21 | 289
6081 | 2018-07-12 | 2018-07-24 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-01-20 | COMP | 2022-06-07 | COMP | Other | 9 | 96 | 25 | 1 | 4 | 852 | 983
6185 | 2018-07-12 | 2018-08-02 | 2018-10-03 | 2020-06-12 | COMP | 2020-06-29 | COMP | 2018-10-18 | COMP | 2020-10-29 | COMP | 2021-04-06 | COMP | Rule 16 | 16 | 44 | 12 |  | 512 | 107 | 687
6335 | 2018-07-12 | 2018-08-11 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-27 | COMP | 2019-01-03 | COMP | 2019-02-22 | COMP | 2019-03-22 | COMP | Rule 16 | 22 | 60 | 35 | 5 | 35 | 21 | 174
6364 | 2018-07-12 | 2018-08-13 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-03 | COMP | 2018-12-21 | COMP | 2019-03-20 | COMP | 2019-01-03 | COMP | Rule 16 | 23 | 68 | 10 | 15 | 60 |  | 120
6409 | 2018-07-12 | 2018-08-16 | 2018-09-20 | 2018-09-20 | COMP | 2018-11-21 | COMP | 2019-01-18 | COMP | 2020-02-07 | COMP | 2020-03-11 | COMP | Rule 16 | 26 | 25 | 44 | 39 | 265 | 23 | 417
6512 | 2018-07-12 | 2018-08-23 | 2018-11-28 | 2018-11-28 | COMP | 2019-05-23 | NOTN | 2019-05-23 | COMP | 2019-09-11 | COMP | 2019-10-02 | COMP | Other | 31 | 66 |  | 123 | 77 | 16 | 309
6723 | 2018-07-12 | 2018-09-10 | 2018-10-04 | 2018-10-04 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2019-04-24 | COMP | 2019-06-17 | COMP | Rule 16 | 42 | 19 | 17 | 1 | 122 | 38 | 234
6735 | 2018-07-12 | 2018-09-10 | 2018-09-24 | 2018-09-24 | COMP | 2018-10-19 | COMP | 2018-10-19 | COMP | 2018-10-25 | COMP | 2019-08-22 | COMP | Rule 16 | 42 | 11 | 20 | 1 | 5 | 207 | 281
6787 | 2018-07-12 | 2018-09-11 | 2019-02-19 | 2019-02-19 | COMP | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-04-12 | COMP | 2019-05-25 | COMP | Rule 16 | 43 | 109 | 37 | 1 | 3 | 31 | 219
7011 | 2018-07-12 | 2018-09-22 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-22 | COMP | 2019-05-14 | COMP | 2019-05-13 | COMP | 2019-06-17 | COMP | Rule 15/16 | 51 | 85 | 19 | 58 | 0 | 24 | 234
7361 | 2018-07-12 | 2018-10-09 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-04 | COMP | 2019-01-30 | COMP | 2018-12-11 | COMP | 2019-03-06 | COMP | Rule 16 | 63 | 35 | 25 | 18 | 0 | 25 | 162
7377 | 2018-07-12 | 2018-10-10 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-21 | COMP | 2019-05-20 | COMP | 2019-09-16 | COMP | 2019-10-18 | COMP | Rule 15/16 | 64 | 72 | 39 | 43 | 83 | 25 | 321
7633 | 2018-07-12 | 2018-10-23 | 2019-02-12 | 2019-02-12 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-04-08 | COMP | 2019-04-30 | COMP | Rule 16 | 73 | 75 | 32 | 1 | 8 | 17 | 201
7716 | 2018-07-12 | 2018-10-26 | 2019-03-18 | 2019-08-16 | COMP | 2019-08-29 | COMP | 2020-10-13 | COMP | 2022-04-19 | COMP | 2022-04-29 | COMP | Rule 16 | 76 | 95 | 10 | 284 | 381 | 9 | 957
7786 | 2018-07-12 | 2018-10-31 | 2019-01-03 | 2019-01-03 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-02-22 | COMP | 2019-02-05 | COMP | Rule 16 | 79 | 42 | 21 | 1 | 15 |  | 142
8032 | 2018-07-12 | 2018-11-12 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-03-16 | COMP | 2019-05-06 | COMP | Rule 16 | 86 | 64 | 29 | 1 | 0 | 28 | 205
8485 | 2018-07-12 | 2018-12-04 | 2019-02-05 | 2019-02-05 | COMP | 2019-03-12 | COMP | 2019-04-29 | COMP | 2020-04-01 | COMP | 2020-04-21 | COMP | Rule 16 | 100 | 43 | 25 | 35 | 233 | 15 | 446
9466 | 2018-07-12 | 2019-02-05 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-22 | COMP | 2019-04-08 | COMP | 2019-09-11 | COMP | 2019-10-21 | COMP | Rule 16 | 142 | 31 | 3 | 12 | 110 | 29 | 322
9565 | 2018-07-12 | 2019-02-07 | 2019-04-08 | 2019-07-15 | COMP | 2019-09-18 | COMP | 2019-10-14 | COMP | 2019-10-13 | COMP | 2019-12-19 | COMP | Rule 16 | 144 | 42 | 47 | 19 | 0 | 46 | 362
9984 | 2018-07-12 | 2019-02-26 | 2019-07-27 | 2019-07-27 | COMP | 2020-05-27 | COMP | 2020-10-26 | COMP | 2020-11-04 | COMP | 2020-12-02 | COMP | Rule 16 | 156 | 107 | 209 | 108 | 8 | 18 | 602
10738 | 2018-07-12 | 2019-03-28 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-11-07 | COMP | 2019-11-27 | COMP | Rule 16 | 178 | 66 | 2 | 1 | 92 | 14 | 348
11998 | 2018-07-12 | 2019-05-20 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-09-18 | COMP | 2019-10-18 | COMP | Rule 16 | 215 | 52 | 10 | 1 | 25 | 23 | 321
12281 | 2018-07-12 | 2019-05-30 | 2019-08-13 | 2019-08-13 | COMP | 2019-11-05 | COMP | 2020-01-13 | COMP | 2020-01-13 | COMP | 2020-01-25 | COMP | Rule 16 | 222 | 53 | 60 | 45 | 1 | 9 | 385
12412 | 2018-07-12 | 2019-06-07 | 2019-09-25 | 2019-09-25 | COMP | 2019-12-26 | COMP | 2019-12-26 | COMP | 2019-12-24 | COMP | 2020-03-18 | COMP | Rule 16 | 228 | 77 | 63 | 1 | 0 | 57 | 422
22640 | 2018-07-12 | 2020-10-02 | 2020-10-29 | 2020-10-29 | COMP | 2020-10-29 | NOTN | 2020-10-29 | COMP | 2020-11-10 | COMP | 2020-12-11 | COMP | Other | 562 | 20 |  | 1 | 9 | 21 | 609
6127 | 2018-07-13 | 2018-07-27 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2018-11-27 | COMP | 2019-01-02 | COMP | Rule 16 | 11 | 58 | 14 | 1 | 14 | 25 | 118
6742 | 2018-07-13 | 2018-09-10 | 2018-10-03 | 2018-10-03 | COMP | 2018-10-12 | COMP | 2023-02-25 | REQD | 2023-02-25 | REQD | 2020-04-02 | COMP | Rule 15/16 | 41 | 18 | 8 |  |  |  | 432
6950 | 2018-07-13 | 2018-09-18 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-09-01 | INPR | 2019-03-26 | COMP | Rule 16 | 47 | 75 | 17 | 1 |  |  | 175
7008 | 2018-07-13 | 2018-09-21 | 2018-10-29 | 2018-10-29 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-02-08 | COMP | 2019-02-25 | COMP | Rule 15/16 | 50 | 27 | 65 | 1 | 5 | 11 | 154
7370 | 2018-07-13 | 2018-10-11 | 2018-12-13 | 2018-12-13 | COMP | 2019-02-26 | COMP | 2019-03-20 | COMP | 2019-10-21 | COMP | 2019-06-15 | COMP | Rule 15/16 | 64 | 43 | 50 | 17 | 151 |  | 232
7448 | 2018-07-13 | 2018-10-15 | 2018-10-17 | 2018-12-12 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-02-12 | COMP | 2019-03-21 | COMP | Rule 16 | 66 | 3 | 31 | 1 | 12 | 27 | 172
7465 | 2018-07-13 | 2018-10-15 | 2019-01-14 | 2019-05-22 | COMP | 2019-09-04 | COMP | 2019-11-07 | COMP | 2019-11-08 | COMP | 2020-01-09 | COMP | Rule 16 | 66 | 61 | 73 | 47 | 2 | 40 | 374
7646 | 2018-07-13 | 2018-10-23 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-22 | COMP | 2019-02-25 | COMP | 2019-03-05 | COMP | 2019-04-01 | COMP | Rule 16 | 72 | 54 | 6 | 24 | 7 | 20 | 179
8119 | 2018-07-13 | 2018-11-15 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-06 | COMP | 2019-05-06 | COMP | 2019-10-21 | INPR | 2019-05-23 | COMP | Rule 15/16 | 88 | 71 | 4 | 44 |  |  | 217
8755 | 2018-07-13 | 2018-12-22 | 2019-03-29 | 2019-03-29 | COMP | 2019-07-23 | COMP | 2019-07-24 | COMP | 2019-08-27 | COMP | 2019-09-24 | COMP | Rule 16 | 112 | 66 | 81 | 2 | 25 | 20 | 302
8825 | 2018-07-13 | 2019-01-02 | 2019-11-08 | 2019-11-08 | COMP | 2020-02-18 | COMP | 2021-04-14 | COMP | 2021-04-14 | COMP | 2021-05-25 | COMP | Rule 15/16 | 118 | 218 | 66 | 293 | 1 | 30 | 721
9017 | 2018-07-13 | 2019-01-12 | 2019-03-22 | 2019-03-22 | COMP | 2019-12-20 | COMP | 2020-09-08 | COMP | 2020-10-30 | COMP | 2020-11-05 | COMP | Rule 16 | 125 | 48 | 190 | 182 | 39 | 5 | 585
9030 | 2018-07-13 | 2019-01-14 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-08-16 | COMP | 2019-08-29 | COMP | Rule 16 | 126 | 36 | 19 | 1 | 98 | 10 | 285
9152 | 2018-07-13 | 2019-01-19 | 2019-04-11 | 2019-04-11 | COMP | 2019-06-19 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-11-21 | COMP | Rule 16 | 130 | 57 | 49 | 54 | 1 | 56 | 343
9904 | 2018-07-13 | 2019-02-22 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2020-01-10 | COMP | 2020-01-24 | COMP | Rule 16 | 153 | 96 | 13 | 1 | 116 | 10 | 384
9926 | 2018-07-13 | 2019-02-22 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-23 | COMP | 2021-07-14 | COMP |  | INPR | 2021-09-27 | COMP | Rule 16 | 153 | 83 | 24 | 498 |  |  | 807
11690 | 2018-07-13 | 2019-05-07 | 2019-10-07 | 2019-10-07 | COMP | 2020-01-21 | COMP | 2020-03-05 | COMP | 2023-04-30 | CANC | 2020-06-12 | COMP | Rule 16 | 205 | 107 | 71 | 32 |  |  | 482
12226 | 2018-07-13 | 2019-05-28 | 2020-02-18 | 2021-09-17 | COMP | 2021-10-01 | COMP | 2022-04-01 | COMP | 2022-04-01 | COMP | 2022-06-25 | COMP | Rule 15/16 | 219 | 182 | 11 | 126 | 1 | 59 | 994
8609 | 2018-07-14 | 2018-12-12 | 2019-05-30 | 2020-03-19 | COMP | 2020-04-01 | COMP | 2020-10-13 | COMP | 2020-09-30 | COMP | 2020-11-25 | COMP | Rule 16 | 104 | 117 | 10 | 138 | 0 | 31 | 597
8994 | 2018-07-14 | 2019-01-11 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-09 | COMP | 2019-04-11 | COMP | 2019-09-26 | COMP | 2019-11-07 | COMP | Rule 16 | 124 | 37 | 25 | 3 | 118 | 31 | 333
3908 | 2018-07-15 | 2018-09-28 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-07 | COMP | 2018-11-07 | COMP | 2018-11-17 | COMP | 2019-01-29 | COMP | Rule 16 | 54 | 22 | 8 | 1 | 7 | 47 | 135
8007 | 2018-07-15 | 2018-11-09 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-13 | COMP | 2019-01-22 | INPR | 2019-02-06 | COMP | 2019-02-25 | COMP | Rule 16 | 84 | 39 | 25 |  |  |  | 153
13111 | 2018-07-15 | 2019-07-11 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-11-12 | COMP | 2019-12-13 | COMP | Rule 16 | 249 | 64 | 17 | 1 | 8 | 22 | 356
17200 | 2018-07-15 | 2020-02-05 | 2020-06-04 | 2020-08-11 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2022-01-30 | INPR | 2020-10-13 | COMP | Rule 16 | 391 | 85 | 21 | 1 |  |  | 567
6105 | 2018-07-16 | 2018-07-26 | 2019-03-03 | 2019-03-03 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-04-06 | COMP | 2020-05-16 | COMP | Rule 16 | 9 | 149 | 252 | 1 | 25 | 30 | 462
6237 | 2018-07-16 | 2018-08-06 | 2018-09-26 | 2018-09-26 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2018-12-15 | COMP | 2019-03-18 | COMP | Rule 16 | 16 | 37 | 44 | 1 | 12 | 62 | 168
6298 | 2018-07-16 | 2018-08-09 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-01-03 | COMP | 2019-02-26 | COMP | Rule 16 | 19 | 49 | 29 | 1 | 24 | 37 | 154
6313 | 2018-07-16 | 2018-08-09 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-14 | COMP | 2019-09-11 | COMP | 2023-04-30 | INPR | 2019-12-24 | COMP | Rule 16 | 19 | 183 | 9 | 84 |  |  | 363
6349 | 2018-07-16 | 2018-08-13 | 2018-09-21 | 2018-12-05 | COMP | 2019-01-17 | COMP | 2019-07-22 | COMP | 2019-04-22 | COMP | 2019-08-30 | COMP | Rule 16 | 21 | 29 | 30 | 129 | 0 | 30 | 285
6362 | 2018-07-16 | 2018-08-14 | 2018-08-31 | 2018-12-17 | COMP | 2018-12-31 | COMP | 2019-07-24 | COMP | 2022-01-19 | COMP | 2022-02-10 | COMP | Rule 16 | 22 | 14 | 10 | 143 | 627 | 17 | 900
6616 | 2018-07-16 | 2018-08-30 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-03-08 | COMP | 2019-04-30 | COMP | Rule 16 | 34 | 51 | 24 | 1 | 55 | 38 | 199
6736 | 2018-07-16 | 2018-09-10 | 2018-09-28 | 2018-09-28 | COMP | 2018-11-05 | COMP | 2018-12-10 | COMP | 2018-12-13 | COMP | 2019-02-01 | COMP | Rule 16 | 40 | 15 | 27 | 23 | 4 | 34 | 138
6772 | 2018-07-16 | 2018-09-12 | 2019-05-12 | 2019-05-12 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-01-31 | COMP | 2020-03-06 | COMP | Rule 15/16 | 42 | 166 | 180 | 1 | 2 | 25 | 412
6792 | 2018-07-16 | 2018-09-11 | 2018-12-06 | 2018-12-06 | COMP | 2019-02-15 | COMP | 2019-02-15 | COMP | 2018-10-02 | COMP | 2019-05-17 | COMP | Rule 16 | 41 | 60 | 49 | 1 | 0 | 65 | 212
7408 | 2018-07-16 | 2018-10-11 | 2019-01-04 | 2019-01-04 | COMP | 2019-02-11 | COMP | 2019-03-21 | COMP | 2020-09-16 | COMP | 2020-11-08 | COMP | Rule 16 | 63 | 57 | 26 | 28 | 378 | 38 | 585
7436 | 2018-07-16 | 2018-10-12 | 2019-02-21 | 2019-02-21 | COMP | 2019-07-10 | COMP | 2019-07-24 | COMP | 2019-07-18 | COMP | 2019-11-25 | COMP | Rule 16 | 64 | 88 | 98 | 11 | 0 | 87 | 344
8075 | 2018-07-16 | 2018-11-15 | 2019-05-01 | 2019-05-01 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-12-03 | COMP | 2020-02-05 | COMP | Rule 15/16 | 87 | 114 | 31 | 1 | 119 | 44 | 391
8088 | 2018-07-16 | 2018-11-16 | 2019-03-14 | 2019-03-14 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-06-19 | COMP | Rule 16 | 88 | 79 | 11 | 1 | 1 | 59 | 234
8297 | 2018-07-16 | 2018-11-26 | 2019-02-19 | 2020-03-02 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2021-03-31 | COMP | 2021-04-20 | COMP | Rule 16 | 92 | 58 | 171 | 1 | 104 | 15 | 695
8758 | 2018-07-16 | 2018-12-21 | 2019-03-26 | 2019-04-10 | COMP | 2019-06-14 | COMP | 2019-08-08 | COMP | 2019-08-30 | COMP | 2019-10-16 | COMP | Rule 16 | 111 | 64 | 47 | 39 | 17 | 33 | 317
8770 | 2018-07-16 | 2018-12-24 | 2019-02-28 | 2019-02-28 | COMP | 2019-04-15 | COMP | 2019-04-24 | COMP | 2019-09-02 | INPR | 2019-05-03 | COMP | Rule 16 | 112 | 45 | 33 | 8 |  |  | 202
9056 | 2018-07-16 | 2019-01-15 | 2019-03-25 | 2019-03-25 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-06-03 | COMP | 2019-07-24 | COMP | Rule 16 | 126 | 48 | 53 | 1 | 0 | 34 | 258
9195 | 2018-07-16 | 2019-01-22 | 2019-02-26 | 2019-02-26 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-12 | COMP | Rule 15/16 | 130 | 25 | 27 | 1 | 1 | 8 | 187
9369 | 2018-07-16 | 2019-01-31 | 2019-04-16 | 2019-04-16 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-09-16 | COMP | 2020-07-09 | COMP | Rule 15/16 | 137 | 53 | 64 | 1 | 44 | 206 | 500
9826 | 2018-07-16 | 2019-02-19 | 2020-08-07 | 2022-01-21 | COMP | 2022-06-06 | COMP | 2021-09-27 | COMP | 2022-08-24 | COMP | 2022-12-14 | COMP | Rule 15/16 | 149 | 373 | 95 |  | 230 | 77 | 1111
11711 | 2018-07-16 | 2019-05-08 | 2019-10-07 | 2019-10-07 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-02-21 | COMP | 2020-07-01 | COMP | Rule 16 | 205 | 106 | 30 | 1 | 64 | 93 | 494
13263 | 2018-07-16 | 2019-07-17 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | 2019-08-09 | COMP | 2019-11-04 | COMP | Rule 15/16 | 253 | 31 | 11 | 1 | 0 | 38 | 330
14544 | 2018-07-16 | 2019-09-16 | 2020-01-28 | 2020-01-28 | COMP | 2020-01-28 | NOTN | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-08-31 | COMP | Other | 295 | 91 |  | 1 | 1 | 153 | 537
16352 | 2018-07-16 | 2019-12-23 | 2020-04-21 | 2020-07-13 | COMP | 2020-09-03 | COMP | 2020-09-03 | COMP | 2020-11-06 | COMP | 2020-12-31 | COMP | Rule 16 | 362 | 83 | 39 | 1 | 46 | 36 | 620
23563 | 2018-07-16 | 2020-11-13 | 2020-12-17 | 2020-12-17 | COMP | 2021-06-23 | COMP | 2021-06-23 | COMP | 2022-01-19 | COMP | 2022-03-02 | COMP | Rule 15/16 | 589 | 23 | 130 | 1 | 145 | 30 | 913
3856 | 2018-07-17 | 2018-08-20 | 2019-01-03 | 2019-01-03 | COMP | 2018-12-27 | NOTN | 2019-01-03 | COMP | 2019-02-05 | COMP | 2019-04-08 | COMP | Other | 25 | 93 |  | 1 | 23 | 44 | 182
3889 | 2018-07-17 | 2018-09-17 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-21 | COMP | 2019-05-03 | COMP | 2019-05-18 | COMP | 2019-05-31 | COMP | Rule 16 | 44 | 39 | 29 | 92 | 11 | 9 | 220
3980 | 2018-07-17 | 2018-11-05 | 2019-04-24 | 2019-04-24 | COMP | 2019-07-02 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-09-12 | COMP | Rule 15/16 | 79 | 116 | 49 | 12 | 1 | 40 | 292
6170 | 2018-07-17 | 2018-08-02 | 2018-12-07 | 2018-12-07 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-03-13 | COMP | 2019-06-11 | COMP | Rule 15/16 | 13 | 88 | 46 | 1 | 20 | 64 | 227
6172 | 2018-07-17 | 2018-08-02 | 2019-01-01 | 2019-01-01 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-03-13 | COMP | 2019-06-14 | COMP | Rule 15/16 | 13 | 103 | 30 | 1 | 20 | 67 | 230
6190 | 2018-07-17 | 2018-08-02 | 2019-01-01 | 2019-01-01 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-03-13 | COMP | 2019-06-14 | COMP | Rule 16 | 13 | 103 | 30 | 1 | 20 | 67 | 230
6195 | 2018-07-17 | 2018-08-03 | 2018-10-27 | 2018-10-27 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-01-02 | COMP | 2019-04-29 | COMP | Rule 16 | 14 | 60 | 42 | 1 | 2 | 82 | 197
6221 | 2018-07-17 | 2018-08-03 | 2020-04-22 | 2022-10-25 | COMP | 2022-10-27 | COMP | 2022-11-01 | COMP | 2022-12-08 | COMP | 2023-02-15 | COMP | Rule 15/16 | 14 | 431 | 3 | 4 | 25 | 47 | 1152
6275 | 2018-07-17 | 2018-08-07 | 2018-10-31 | 2018-10-31 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-07-21 | INPR | 2019-01-14 | COMP | Rule 16 | 16 | 61 | 42 | 1 |  |  | 124
6404 | 2018-07-17 | 2018-08-16 | 2018-09-22 | 2018-09-22 | COMP | 2018-10-17 | COMP | 2018-11-29 | COMP | 2019-03-25 | COMP | 2019-04-25 | COMP | Rule 16 | 23 | 26 | 18 | 29 | 79 | 24 | 195
6581 | 2018-07-17 | 2018-08-28 | 2019-04-09 | 2020-04-17 | COMP | 2020-06-02 | COMP | 2020-07-06 | COMP | 2020-06-24 | COMP | 2021-10-24 | COMP | Rule 15/16 | 31 | 153 | 32 | 25 | 0 | 329 | 824
6582 | 2018-07-17 | 2018-08-28 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-27 | COMP | 2019-03-11 | COMP | 2019-08-15 | COMP | 2019-09-27 | COMP | Other | 31 | 55 | 29 | 50 | 112 | 31 | 303
6652 | 2018-07-17 | 2018-09-07 | 2018-09-17 | 2018-09-17 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-04 | COMP | 2019-05-06 | COMP | Rule 16 | 38 | 7 | 136 | 1 | 2 | 23 | 202
6799 | 2018-07-17 | 2018-09-11 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-02-19 | COMP | 2019-04-01 | COMP | Rule 16 | 40 | 62 | 20 | 1 | 29 | 30 | 177
6907 | 2018-07-17 | 2018-09-16 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-27 | COMP | 2018-12-31 | COMP | 2019-01-28 | COMP | 2019-05-02 | COMP | Rule 16 | 43 | 55 | 16 | 3 | 19 | 68 | 200
6934 | 2018-07-17 | 2018-09-18 | 2018-12-11 | 2018-12-11 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-11-04 | COMP | 2019-12-23 | COMP | Rule 16 | 45 | 58 | 225 | 1 | 4 | 33 | 361
6936 | 2018-07-17 | 2018-09-21 | 2018-11-04 | 2018-11-04 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-04-16 | COMP | 2019-05-08 | COMP | Rule 16 | 48 | 31 | 18 | 1 | 93 | 17 | 204
6953 | 2018-07-17 | 2018-09-18 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-23 | COMP | 2019-10-29 | COMP | 2019-10-24 | COMP | 2019-12-09 | COMP | Rule 15 | 45 | 269 | 9 | 5 | 0 | 27 | 351
7075 | 2018-07-17 | 2018-09-25 | 2018-10-09 | 2018-10-09 | COMP | 2018-12-18 | COMP | 2019-01-31 | COMP | 2019-03-12 | COMP | 2019-04-05 | COMP | Rule 16 | 50 | 11 | 48 | 30 | 28 | 19 | 181
7246 | 2018-07-17 | 2018-10-03 | 2018-11-19 | 2020-01-02 | COMP | 2020-05-22 | COMP | 2021-01-21 | COMP |  | INPR | 2021-07-30 | COMP | Rule 15/16 | 56 | 33 | 100 | 167 |  |  | 765
7407 | 2018-07-17 | 2018-10-11 | 2019-01-08 | 2019-01-30 | COMP | 2019-02-04 | COMP | 2019-02-04 | NOTN | 2019-02-04 | COMP | 2019-04-19 | COMP | Rule 16 | 62 | 59 | 4 |  |  |  | 191
7637 | 2018-07-17 | 2018-10-23 | 2019-02-14 | 2019-02-14 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2019-02-21 | COMP | 2019-03-26 | COMP | Rule 16 | 70 | 77 | 4 | 1 | 2 | 24 | 173
7717 | 2018-07-17 | 2018-10-26 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-12-28 | INPR | 2019-08-07 | COMP | Rule 16 | 73 | 167 | 7 | 1 |  |  | 267
7853 | 2018-07-17 | 2018-11-02 | 2018-12-03 | 2018-12-03 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-01-31 | COMP | 2019-03-12 | COMP | Rule 16 | 78 | 19 | 8 | 1 | 34 | 28 | 163
8010 | 2018-07-17 | 2018-11-09 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-28 | COMP | 2019-12-02 | COMP | 2023-04-30 | INPR | 2020-03-02 | COMP | Rule 15/16 | 83 | 65 | 29 | 172 |  |  | 407
8040 | 2018-07-17 | 2018-11-12 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-15 | COMP | 2019-07-22 | COMP | 2019-12-28 | INPR | 2019-09-12 | COMP | Rule 15/16 | 83 | 86 | 19 | 69 |  |  | 292
8079 | 2018-07-17 | 2018-11-14 | 2018-11-20 | 2018-11-20 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2018-12-14 | COMP | 2019-01-08 | COMP | Rule 16 | 85 | 5 | 4 | 1 | 14 | 16 | 120
8100 | 2018-07-17 | 2018-11-15 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-17 | COMP | 2019-01-03 | COMP | 2019-01-05 | COMP | 2019-02-25 | COMP | Rule 16 | 86 | 5 | 17 | 12 | 2 | 34 | 152
8605 | 2018-07-17 | 2018-12-11 | 2019-02-23 | 2019-02-23 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-06-05 | COMP | 2019-06-19 | COMP | Rule 15/16 | 102 | 50 | 11 | 1 | 62 | 11 | 233
8787 | 2018-07-17 | 2018-12-26 | 2019-03-21 | 2019-03-21 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-07-15 | COMP | 2019-08-30 | COMP | Rule 15/16 | 112 | 59 | 18 | 1 | 64 | 35 | 284
9092 | 2018-07-17 | 2019-01-16 | 2019-03-27 | 2019-03-27 | COMP | 2019-09-03 | COMP | 2020-11-30 | COMP | 2021-02-01 | COMP | 2021-03-19 | COMP | Rule 16 | 126 | 49 | 112 | 313 | 43 | 34 | 672
9117 | 2018-07-17 | 2019-01-18 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-09 | COMP | 2019-04-18 | COMP | 2019-05-02 | COMP | 2019-05-26 | COMP | Rule 16 | 128 | 45 | 12 | 8 | 11 | 17 | 216
9154 | 2018-07-17 | 2019-01-19 | 2019-03-08 | 2019-03-08 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-06-04 | COMP | 2019-07-10 | COMP | Rule 16 | 128 | 33 | 18 | 1 | 45 | 26 | 247
9315 | 2018-07-17 | 2019-01-30 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-29 | COMP | 2019-04-30 | COMP | 2019-07-01 | COMP | 2019-08-02 | COMP | Rule 16 | 135 | 41 | 23 | 2 | 44 | 24 | 264
9519 | 2018-07-17 | 2019-02-06 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-25 | COMP | 2019-08-12 | COMP | 2019-07-12 | COMP | 2019-08-26 | COMP | Rule 16 | 140 | 77 | 21 | 34 | 0 | 11 | 280
9905 | 2018-07-17 | 2019-02-22 | 2019-06-03 | 2019-06-03 | COMP | 2019-07-03 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-10-25 | COMP | Rule 16 | 151 | 71 | 23 | 72 | 1 | 10 | 323
10850 | 2018-07-17 | 2019-04-02 | 2019-05-13 | 2019-05-13 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-09 | COMP | 2020-06-22 | COMP | Rule 16 | 178 | 30 | 171 | 1 | 0 | 110 | 486
11269 | 2018-07-17 | 2019-04-19 | 2019-05-20 | 2019-05-20 | COMP | 2019-06-07 | COMP | 2019-06-07 | NOTN | 2019-06-19 | COMP | 2019-06-25 | COMP | Rule 16 | 191 | 22 | 14 |  |  |  | 237
11704 | 2018-07-17 | 2019-05-08 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-02 | COMP | 2019-08-02 | INPR | 2019-11-25 | COMP | 2019-12-03 | COMP | Rule 16 | 204 | 46 | 16 |  |  |  | 347
11706 | 2018-07-17 | 2019-05-08 | 2019-08-12 | 2019-08-12 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-22 | COMP | 2019-12-18 | COMP | Rule 16 | 204 | 67 | 49 | 1 | 3 | 39 | 358
16078 | 2018-07-17 | 2019-12-09 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-02 | COMP | 2020-04-27 | COMP | 2020-03-31 | COMP | 2020-06-04 | COMP | Rule 16 | 351 | 56 | 25 | 18 | 0 | 28 | 474
16080 | 2018-07-17 | 2019-12-09 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-13 | COMP | 2020-06-01 | COMP | 2020-05-26 | COMP | 2020-07-24 | COMP | Rule 16 | 351 | 97 | 13 | 13 | 0 | 40 | 510
21123 | 2018-07-17 | 2020-07-23 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-22 | COMP | 2020-12-22 | COMP | 2020-10-20 | COMP | 2021-03-08 | COMP | Rule 16 | 509 | 28 | 16 | 63 | 0 | 51 | 663
6239 | 2018-07-18 | 2018-08-06 | 2018-09-28 | 2019-05-07 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2019-07-01 | COMP | 2019-11-18 | COMP | Rule 16 | 14 | 39 | 19 | 1 | 21 | 98 | 337
6283 | 2018-07-18 | 2018-08-08 | 2018-10-28 | 2018-10-28 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-04-30 | COMP | 2019-07-26 | COMP | Rule 16 | 16 | 57 | 30 | 1 | 96 | 62 | 258
6434 | 2018-07-18 | 2018-08-18 | 2018-11-07 | 2018-11-29 | COMP | 2018-12-11 | COMP | 2019-02-12 | COMP | 2019-01-31 | COMP | 2019-03-12 | COMP | Rule 16 | 23 | 57 | 9 | 43 | 0 | 20 | 162
6526 | 2018-07-18 | 2018-08-25 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-20 | COMP | 2019-01-10 | COMP | 2019-01-02 | COMP | 2019-01-30 | COMP | Rule 16 | 28 | 50 | 31 | 14 | 0 | 14 | 134
6559 | 2018-07-18 | 2018-08-27 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2020-06-15 | COMP | 2020-07-30 | COMP | Rule 16 | 29 | 64 | 40 | 1 | 350 | 34 | 513
6655 | 2018-07-18 | 2018-09-08 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-04 | COMP | 2019-05-09 | COMP | 2019-05-21 | COMP | 2019-06-19 | COMP | Rule 16 | 37 | 94 | 7 | 68 | 9 | 21 | 232
6712 | 2018-07-18 | 2018-09-10 | 2018-10-11 | 2021-02-16 | COMP | 2021-03-19 | COMP | 2021-12-30 | COMP | 2019-08-06 | NOTN | 2022-02-09 | COMP | Rule 15/16 | 38 | 24 | 24 | 199 |  |  | 897
6946 | 2018-07-18 | 2018-09-18 | 2018-09-30 | 2019-08-21 | COMP | 2019-03-15 | COMP | 2019-10-30 | COMP | 2018-12-01 | COMP | 2019-12-13 | COMP | Rule 15/16 | 44 | 9 |  | 161 | 0 | 30 | 354
7146 | 2018-07-18 | 2018-09-28 | 2019-01-17 | 2019-01-17 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-03-19 | COMP | 2019-04-09 | COMP | Rule 16 | 52 | 75 | 9 | 1 | 34 | 16 | 182
7157 | 2018-07-18 | 2018-09-29 | 2019-02-07 | 2019-02-07 | COMP | 2019-05-14 | COMP | 2019-08-22 | COMP | 2020-06-05 | COMP | 2020-07-08 | COMP | Rule 15/16 | 52 | 88 | 68 | 71 | 198 | 24 | 497
7445 | 2018-07-18 | 2018-10-12 | 2019-01-02 | 2019-01-02 | COMP | 2019-05-31 | NOTN | 2019-08-21 | COMP | 2019-09-10 | COMP | 2019-09-17 | COMP | Other | 62 | 54 |  | 162 | 14 | 6 | 294
8069 | 2018-07-18 | 2018-11-14 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-10-01 | COMP | 2019-11-05 | COMP | Rule 16 | 84 | 61 | 4 | 1 | 158 | 26 | 329
8687 | 2018-07-18 | 2018-12-17 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-19 | COMP | 2019-07-22 | COMP | 2019-07-12 | COMP | 2019-08-13 | COMP | Rule 16 | 105 | 36 | 28 | 88 | 0 | 17 | 270
10554 | 2018-07-18 | 2019-03-20 | 2019-04-20 | 2019-04-20 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-11-20 | COMP | 2019-12-23 | COMP | Rule 15/16 | 168 | 23 | 121 | 1 | 29 | 22 | 360
12950 | 2018-07-18 | 2019-07-01 | 2019-11-06 | 2019-11-06 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2021-03-09 | COMP | 2021-03-11 | COMP | Rule 16 | 240 | 91 | 187 | 1 | 148 | 3 | 665
19107 | 2018-07-18 | 2020-04-21 | 2020-11-17 | 2020-11-17 | COMP | 2021-07-19 | COMP | 2021-07-19 | COMP | 2022-06-09 | COMP | 2023-02-09 | COMP | Rule 16 | 442 | 148 | 167 | 1 | 227 | 167 | 1147
3840 | 2018-07-19 | 2018-08-13 | 2019-01-14 | 2019-01-14 | COMP | 2020-09-24 | COMP | 2020-10-21 | COMP | 2020-12-11 | COMP | 2021-03-10 | COMP | Rule 15/16 | 18 | 105 | 430 | 20 | 35 | 60 | 663
3996 | 2018-07-19 | 2018-11-10 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-21 | COMP | 2019-10-29 | COMP | 2019-11-01 | COMP | 2019-12-19 | COMP | Rule 16 | 81 | 235 | 2 | 7 | 4 | 32 | 357
6212 | 2018-07-19 | 2018-08-03 | 2018-09-15 | 2018-09-15 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-04-18 | COMP | 2019-06-10 | COMP | Rule 15/16 | 12 | 30 | 110 | 1 | 38 | 37 | 224
6308 | 2018-07-19 | 2018-08-09 | 2018-08-17 | 2018-10-02 | COMP | 2018-10-10 | COMP | 2018-10-10 | COMP | 2019-03-05 | COMP | 2019-04-02 | COMP | Rule 16 | 16 | 7 | 7 | 1 | 98 | 21 | 176
6369 | 2018-07-19 | 2018-08-14 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-11-24 | INPR | 2019-08-01 | COMP | Rule 15/16 | 19 | 160 | 11 | 1 |  |  | 261
6848 | 2018-07-19 | 2018-09-13 | 2018-10-19 | 2018-10-19 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-09-01 | INPR | 2019-05-08 | COMP | Rule 16 | 40 | 27 | 85 | 1 |  |  | 202
7209 | 2018-07-19 | 2018-10-02 | 2019-01-01 | 2019-01-01 | COMP | 2019-03-18 | COMP | 2019-03-20 | COMP | 2021-01-07 | COMP | 2021-02-04 | COMP | Rule 16 | 53 | 61 | 52 | 3 | 455 | 20 | 640
7217 | 2018-07-19 | 2018-10-03 | 2018-11-17 | 2018-11-17 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-02-20 | COMP | 2019-03-12 | COMP | Rule 16 | 54 | 32 | 5 | 1 | 58 | 15 | 161
7238 | 2018-07-19 | 2018-10-03 | 2018-11-19 | 2018-11-19 | COMP | 2019-02-26 | COMP | 2019-04-04 | COMP | 2020-04-27 | COMP | 2020-07-29 | COMP | Rule 15/16 | 54 | 33 | 66 | 28 | 268 | 67 | 511
7260 | 2018-07-19 | 2018-10-04 | 2018-12-07 | 2018-12-07 | COMP | 2019-02-08 | COMP | 2019-02-11 | COMP | 2021-01-07 | COMP | 2021-02-06 | COMP | Rule 16 | 55 | 44 | 43 | 2 | 481 | 21 | 641
7391 | 2018-07-19 | 2018-10-10 | 2019-04-15 | 2019-07-26 | COMP | 2019-08-07 | COMP | 2019-09-10 | COMP | 2019-07-28 | COMP | 2020-01-21 | COMP | Rule 15/16 | 59 | 127 | 9 | 24 | 0 | 90 | 377
7579 | 2018-07-19 | 2018-10-21 | 2018-12-18 | 2018-12-18 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-07-21 | INPR | 2019-03-26 | COMP | Rule 16 | 66 | 39 | 29 | 1 |  |  | 171
7655 | 2018-07-19 | 2018-10-24 | 2019-03-19 | 2019-05-14 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-07-01 | COMP | 2019-10-07 | COMP | Rule 15/16 | 69 | 98 | 5 | 1 | 30 | 69 | 307
7784 | 2018-07-19 | 2018-10-31 | 2019-09-09 | 2019-09-09 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-05-13 | COMP | 2020-06-16 | COMP | Rule 15/16 | 74 | 214 | 168 | 1 | 4 | 24 | 480
7857 | 2018-07-19 | 2018-11-02 | 2018-12-13 | 2018-12-13 | COMP | 2019-01-10 | COMP | 2020-09-22 | COMP | 2020-09-17 | COMP | 2020-10-23 | COMP | Rule 16 | 76 | 27 | 19 | 430 | 0 | 24 | 572
8174 | 2018-07-19 | 2018-11-16 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-07-09 | COMP | 2019-08-06 | COMP | Rule 16 | 85 | 68 | 41 | 1 | 53 | 21 | 264
8178 | 2018-07-19 | 2018-11-18 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-14 | COMP | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-08-08 | COMP | Rule 15/16 | 85 | 89 | 33 | 35 | 1 | 27 | 266
8500 | 2018-07-19 | 2018-12-05 | 2019-02-10 | 2019-02-10 | COMP | 2019-03-13 | COMP | 2019-04-16 | COMP | 2019-04-01 | COMP | 2019-05-22 | COMP | Rule 16 | 96 | 45 | 22 | 25 | 0 | 27 | 212
9251 | 2018-07-19 | 2019-01-24 | 2019-02-20 | 2019-04-10 | COMP | 2019-04-23 | COMP | 2019-04-25 | COMP | 2019-08-01 | COMP | 2019-08-26 | COMP | Rule 16 | 129 | 19 | 10 | 3 | 69 | 18 | 278
12540 | 2018-07-19 | 2019-06-11 | 2019-09-15 | 2019-09-15 | COMP | 2019-11-13 | COMP | 2019-11-26 | COMP | 2020-02-13 | COMP | 2020-05-27 | COMP | Rule 16 | 225 | 67 | 42 | 10 | 53 | 73 | 466
14027 | 2018-07-19 | 2019-08-22 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-31 | COMP | 2020-02-18 | COMP | 2022-01-30 | INPR | 2020-09-24 | COMP | Rule 16 | 276 | 63 | 27 | 33 |  |  | 551
6284 | 2018-07-20 | 2018-08-09 | 2018-12-04 | 2018-12-18 | COMP | 2018-12-18 | NOTN | 2018-12-18 | COMP | 2018-12-11 | COMP | 2019-01-24 | COMP | Other | 15 | 80 |  | 1 | 0 | 25 | 128
6324 | 2018-07-20 | 2018-08-10 | 2018-11-16 | 2018-11-16 | COMP | 2019-01-02 | COMP | 2019-01-22 | COMP | 2019-02-26 | COMP | 2019-06-01 | COMP | Rule 16 | 16 | 69 | 30 | 14 | 25 | 68 | 217
6332 | 2018-07-20 | 2018-08-11 | 2018-12-18 | 2018-12-18 | COMP | 2018-12-18 | NOTN | 2019-02-11 | COMP | 2018-12-18 | COMP | 2019-03-19 | COMP | Other | 16 | 88 |  | 37 | 0 | 26 | 165
6339 | 2018-07-20 | 2018-08-15 | 2019-04-17 | 2019-04-17 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-06-07 | COMP | 2019-07-09 | COMP | Rule 15/16 | 19 | 168 | 5 | 1 | 33 | 22 | 243
6461 | 2018-07-20 | 2018-08-21 | 2018-10-05 | 2018-10-05 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2019-05-07 | COMP | 2019-06-27 | COMP | Rule 16 | 23 | 33 | 34 | 1 | 113 | 37 | 236
6534 | 2018-07-20 | 2018-08-28 | 2018-10-16 | 2018-10-16 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-09-12 | COMP | 2019-09-17 | COMP | Rule 16 | 28 | 35 | 76 | 1 | 153 | 4 | 292
6805 | 2018-07-20 | 2018-09-11 | 2018-11-28 | 2019-02-13 | COMP | 2019-02-25 | COMP | 2019-03-01 | COMP | 2019-04-23 | COMP | 2019-06-05 | COMP | Rule 16 | 37 | 54 | 8 | 5 | 38 | 31 | 220
7020 | 2018-07-20 | 2018-09-23 | 2019-01-28 | 2019-01-28 | COMP | 2019-01-31 | NOTN | 2019-04-09 | COMP | 2019-04-22 | COMP | 2019-09-14 | COMP | Other | 45 | 85 |  | 51 | 10 | 102 | 290
7054 | 2018-07-20 | 2018-09-25 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-01-24 | COMP | 2019-03-19 | COMP | Rule 16 | 47 | 52 | 29 | 1 | 3 | 38 | 165
7063 | 2018-07-20 | 2018-09-25 | 2019-01-26 | 2019-01-26 | COMP | 2018-12-13 | NOTN | 2019-03-06 | COMP | 2019-01-31 | COMP | 2019-04-17 | COMP | Other | 47 | 83 |  | 27 | 0 | 31 | 186
7132 | 2018-07-20 | 2018-09-28 | 2018-10-11 | 2019-01-25 | COMP | 2019-04-10 | COMP | 2019-01-10 | COMP | 2019-05-16 | COMP | 2019-05-30 | COMP | Rule 16 | 50 | 10 | 53 |  | 89 | 10 | 216
7292 | 2018-07-20 | 2018-10-06 | 2019-03-01 | 2019-03-01 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-04-05 | COMP | 2019-05-28 | COMP | Rule 16 | 55 | 98 | 23 | 1 | 4 | 37 | 214
7302 | 2018-07-20 | 2018-10-06 | 2018-12-27 | 2020-01-15 | COMP | 2020-03-10 | COMP | 2020-06-10 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | Rule 16 | 55 | 55 | 38 | 66 | 20 | 1 | 494
7951 | 2018-07-20 | 2018-11-08 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-26 | COMP | 2019-08-13 | NOTN | 2019-08-13 | COMP | 2019-08-23 | COMP | Rule 16 | 79 | 49 | 24 |  |  |  | 276
8388 | 2018-07-20 | 2018-11-28 | 2019-02-19 | 2019-07-22 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2020-03-02 | COMP | 2020-04-07 | COMP | Rule 15/16 | 90 | 56 | 25 | 1 | 129 | 27 | 430
8422 | 2018-07-20 | 2018-11-30 | 2019-01-24 | 2019-03-19 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-07-03 | COMP | 2019-06-25 | COMP | Rule 16 | 92 | 37 | 16 | 1 | 61 |  | 234
8494 | 2018-07-20 | 2018-12-06 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-19 | COMP | 2019-03-07 | COMP | 2019-03-27 | COMP | 2019-04-19 | COMP | Rule 16 | 96 | 33 | 18 | 13 | 15 | 18 | 188
8562 | 2018-07-20 | 2018-12-10 | 2019-05-10 | 2021-01-22 | COMP | 2021-02-02 | COMP | 2021-03-05 | COMP | 2021-02-05 | COMP | 2021-03-26 | COMP | Rule 15/16 | 98 | 106 | 8 | 23 | 0 | 16 | 674
10078 | 2018-07-20 | 2019-02-28 | 2019-06-27 | 2019-06-27 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-02-10 | COMP | 2020-02-14 | COMP | Rule 15/16 | 152 | 85 | 102 | 1 | 54 | 5 | 394
11440 | 2018-07-20 | 2019-04-27 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-07-19 | COMP | 2019-07-21 | COMP | Rule 16 | 193 | 22 | 18 | 1 | 20 | 1 | 251
12203 | 2018-07-20 | 2019-05-28 | 2019-08-29 | 2021-01-06 | COMP | 2021-08-23 | COMP | 2021-09-10 | COMP | 2023-04-30 | COMP | 2022-01-22 | COMP | Rule 15/16 | 214 | 67 | 160 | 14 | 410 |  | 882
12548 | 2018-07-20 | 2019-06-12 | 2019-08-25 | 2019-08-25 | COMP | 2019-12-18 | COMP | 2020-03-09 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | Rule 16 | 225 | 52 | 79 | 55 | 2 | 1 | 410
13712 | 2018-07-20 | 2019-08-06 | 2019-09-07 | 2021-04-07 | COMP | 2021-04-14 | COMP | 2019-12-03 | COMP | 2021-04-22 | COMP | 2021-05-17 | COMP | Rule 16 | 263 | 23 | 6 |  | 350 | 18 | 710
13749 | 2018-07-20 | 2019-08-07 | 2020-01-22 | 2020-01-23 | COMP | 2021-02-18 | COMP | 2021-03-01 | COMP | 2021-05-06 | COMP | 2021-07-11 | COMP | Rule 15/16 | 264 | 114 | 271 | 8 | 49 | 45 | 747
6791 | 2018-07-22 | 2018-09-11 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-26 | COMP | 2019-02-01 | COMP | 2019-01-08 | COMP | 2019-02-26 | COMP | Rule 16 | 36 | 48 | 5 | 47 | 0 | 17 | 149
4082 | 2018-07-23 | 2019-01-15 | 2019-08-05 | 2019-08-05 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-11-25 | COMP | 2019-12-11 | COMP | Rule 16 | 121 | 141 | 27 | 1 | 53 | 11 | 349
6251 | 2018-07-23 | 2018-08-07 | 2018-10-25 | 2018-10-25 | COMP | 2018-08-07 | NOTN | 2019-03-27 | COMP | 2018-10-30 | COMP | 2019-05-02 | COMP | Other | 12 | 57 |  | 103 | 0 | 27 | 196
6376 | 2018-07-23 | 2018-08-14 | 2018-10-03 | 2018-10-03 | COMP | 2019-07-15 | COMP | 2019-08-01 | COMP | 2019-08-02 | COMP | 2019-08-29 | COMP | Rule 16 | 17 | 36 | 195 | 14 | 2 | 20 | 279
6585 | 2018-07-23 | 2018-08-28 | 2018-11-01 | 2018-11-01 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-11-24 | INPR | 2019-08-07 | COMP | Rule 16 | 27 | 47 | 130 | 1 |  |  | 263
6630 | 2018-07-23 | 2018-08-31 | 2018-11-05 | 2018-11-05 | COMP | 2018-11-14 | COMP | 2018-12-03 | COMP | 2019-10-21 | INPR | 2019-01-15 | COMP | Rule 16 | 30 | 46 | 7 | 12 |  |  | 121
6640 | 2018-07-23 | 2018-08-31 | 2019-02-05 | 2019-02-25 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-06 | COMP | 2019-07-30 | COMP | Rule 16 | 30 | 106 | 75 | 1 | 19 | 17 | 257
6644 | 2018-07-23 | 2018-09-04 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2019-10-21 | INPR | 2019-01-30 | COMP | Rule 15/16 | 31 | 42 | 11 | 1 |  |  | 131
6770 | 2018-07-23 | 2018-09-11 | 2018-10-23 | 2018-10-23 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-01-03 | COMP | 2019-03-14 | COMP | Rule 16 | 36 | 31 | 8 | 1 | 41 | 49 | 161
7030 | 2018-07-23 | 2018-09-23 | 2019-01-10 | 2019-01-10 | COMP | 2019-04-22 | COMP | 2019-04-23 | COMP | 2019-07-19 | COMP | 2019-07-25 | COMP | Rule 16 | 44 | 74 | 71 | 2 | 62 | 5 | 254
7230 | 2018-07-23 | 2018-10-03 | 2019-01-22 | 2019-03-20 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-06-07 | COMP | 2019-06-24 | COMP | Rule 16 | 52 | 74 | 5 | 1 | 53 | 12 | 232
7396 | 2018-07-23 | 2018-10-11 | 2018-11-07 | 2018-11-07 | COMP | 2018-11-09 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-03-15 | COMP | Rule 16 | 58 | 20 | 3 | 47 | 1 | 38 | 162
7424 | 2018-07-23 | 2018-10-11 | 2018-10-12 | 2018-10-12 | COMP | 2018-10-25 | COMP | 2018-10-25 | COMP | 2019-03-11 | COMP | 2019-03-20 | COMP | Rule 16 | 58 | 2 | 10 | 1 | 91 | 8 | 165
7427 | 2018-07-23 | 2018-10-12 | 2019-02-12 | 2019-02-12 | COMP | 2019-04-24 | COMP | 2019-06-07 | COMP | 2019-06-11 | COMP | 2019-07-09 | COMP | Rule 16 | 59 | 82 | 51 | 32 | 3 | 20 | 242
7521 | 2018-07-23 | 2018-10-18 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-12 | COMP | 2019-04-20 | COMP | Rule 16 | 63 | 67 | 32 | 1 | 23 | 6 | 187
7721 | 2018-07-23 | 2018-10-26 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-08-21 | COMP | 2019-08-07 | COMP | 2019-11-07 | COMP | Rule 16 | 69 | 166 | 4 | 37 | 0 | 56 | 328
7778 | 2018-07-23 | 2018-10-30 | 2019-01-30 | 2019-01-30 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-04-12 | COMP | 2019-06-06 | COMP | Rule 16 | 71 | 61 | 32 | 1 | 21 | 39 | 220
7968 | 2018-07-23 | 2018-11-07 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-15 | COMP | 2019-02-15 | COMP | 2019-07-21 | INPR | 2019-03-07 | COMP | Rule 16 | 77 | 41 | 27 | 1 |  |  | 156
8288 | 2018-07-23 | 2018-11-26 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-15 | COMP | 2019-03-20 | COMP | 2019-09-22 | INPR | 2019-05-30 | COMP | Rule 16 | 87 | 46 | 12 | 23 |  |  | 215
8460 | 2018-07-23 | 2018-12-04 | 2019-03-29 | 2021-02-26 | COMP | 2021-08-19 | COMP | 2019-07-17 | COMP | 2022-05-04 | COMP | 2022-07-07 | COMP | Rule 15/16 | 93 | 80 | 123 |  | 706 | 44 | 996
8596 | 2018-07-23 | 2018-12-11 | 2019-01-28 | 2019-01-28 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-05-19 | COMP | 2019-04-19 | COMP | Rule 16 | 98 | 32 | 51 | 1 | 29 |  | 187
8772 | 2018-07-23 | 2018-12-26 | 2019-01-28 | 2019-01-28 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-04-29 | COMP | 2019-05-01 | COMP | Rule 16 | 108 | 22 | 64 | 1 | 2 | 3 | 195
8774 | 2018-07-23 | 2018-12-26 | 2019-02-13 | 2019-02-13 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2019-07-22 | COMP | 2019-08-06 | COMP | Rule 16 | 108 | 34 | 86 | 1 | 26 | 12 | 262
9200 | 2018-07-23 | 2019-01-22 | 2019-05-08 | 2019-05-08 | COMP | 2019-11-08 | COMP | 2019-11-12 | COMP | 2020-04-26 | INPR | 2020-01-06 | COMP | Rule 16 | 125 | 76 | 130 | 2 |  |  | 365
9628 | 2018-07-23 | 2019-02-09 | 2019-07-25 | 2019-07-25 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2020-03-16 | COMP | 2020-03-19 | COMP | Rule 16 | 138 | 116 | 65 | 1 | 96 | 4 | 416
10071 | 2018-07-23 | 2019-02-28 | 2019-04-29 | 2019-04-29 | COMP | 2019-05-02 | NOTN | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-06-07 | COMP | Other | 151 | 43 |  | 4 | 1 | 26 | 221
11085 | 2018-07-23 | 2019-04-12 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-04-27 | COMP | 2020-05-21 | COMP | Rule 16 | 182 | 49 | 12 | 1 | 203 | 19 | 461
11621 | 2018-07-23 | 2019-05-06 | 2019-05-30 | 2019-05-30 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-12-29 | INPR | 2019-08-27 | COMP | Rule 16 | 198 | 18 | 8 | 1 |  |  | 277
12210 | 2018-07-23 | 2019-05-28 | 2019-08-08 | 2019-08-08 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-01-07 | COMP | 2020-02-10 | COMP | Rule 16 | 213 | 52 | 50 | 1 | 54 | 24 | 389
13701 | 2018-07-23 | 2019-08-06 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-19 | COMP | 2020-02-21 | COMP | 2020-02-27 | COMP | 2020-03-24 | COMP | Rule 16 | 262 | 67 | 8 | 63 | 5 | 19 | 419
3860 | 2018-07-24 | 2018-08-22 | 2018-10-29 | 2018-10-29 | COMP |  |  |  |  | 2020-09-16 | COMP | 2020-10-07 | COMP | Other | 22 | 48 |  |  |  |  | 557
6092 | 2018-07-24 | 2018-07-25 | 2018-08-21 | 2018-08-21 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-01-03 | COMP | 2019-02-19 | COMP | Rule 16 | 2 | 20 | 83 | 1 | 10 | 32 | 143
6193 | 2018-07-24 | 2018-08-03 | 2018-10-27 | 2018-11-10 | COMP | 2018-12-03 | COMP | 2019-02-04 | COMP | 2019-01-23 | COMP | 2019-03-14 | COMP | Rule 16 | 9 | 60 | 13 | 43 | 0 | 28 | 160
6301 | 2018-07-24 | 2018-08-09 | 2019-02-23 | 2019-02-23 | COMP | 2019-03-04 | NOTN | 2019-03-08 | COMP | 2019-03-18 | COMP | 2019-06-11 | COMP | Other | 13 | 134 |  | 10 | 7 | 61 | 222
6375 | 2018-07-24 | 2018-08-14 | 2018-10-03 | 2018-10-03 | COMP | 2018-12-03 | COMP | 2018-12-03 | COMP | 2019-01-22 | COMP | 2019-01-28 | COMP | Rule 16 | 16 | 36 | 41 | 1 | 34 | 5 | 128
6472 | 2018-07-24 | 2018-08-20 | 2018-11-05 | 2018-11-05 | COMP | 2018-11-09 | COMP | 2018-11-09 | COMP | 2018-11-27 | COMP | 2019-01-11 | COMP | Rule 16 | 20 | 55 | 5 | 1 | 10 | 32 | 118
6521 | 2018-07-24 | 2018-08-24 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2018-12-18 | COMP | 2019-01-27 | COMP | Rule 15/16 | 24 | 61 | 18 | 1 | 2 | 26 | 127
6658 | 2018-07-24 | 2018-09-04 | 2019-02-20 | 2019-03-05 | COMP | 2019-03-13 | COMP | 2019-03-22 | COMP | 2019-07-21 | INPR | 2019-04-09 | COMP | Rule 16 | 30 | 115 | 7 | 8 |  |  | 178
6777 | 2018-07-24 | 2018-09-11 | 2019-01-03 | 2019-01-03 | COMP | 2018-09-11 | NOTN | 2019-01-03 | COMP | 2019-01-08 | COMP | 2019-02-22 | COMP | Other | 35 | 78 |  | 1 | 4 | 32 | 146
6989 | 2018-07-24 | 2018-09-20 | 2019-01-11 | 2019-01-11 | COMP | 2019-06-05 | NOTN | 2019-06-05 | COMP | 2019-06-21 | COMP | 2019-08-08 | COMP | Other | 42 | 77 |  | 101 | 13 | 34 | 263
6991 | 2018-07-24 | 2018-09-22 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-05 | COMP | 2018-11-05 | COMP | 2019-02-15 | COMP | 2019-01-03 | COMP | Rule 15/16 | 43 | 23 | 9 | 1 | 69 |  | 112
7227 | 2018-07-24 | 2018-10-03 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-06 | COMP | 2018-11-07 | COMP | 2018-11-07 | COMP | 2019-01-02 | COMP | Rule 16 | 51 | 16 | 10 | 2 | 1 | 36 | 111
7392 | 2018-07-24 | 2018-10-10 | 2018-12-03 | 2018-12-03 | COMP | 2019-01-16 | COMP | 2019-01-16 | COMP | 2019-07-21 | INPR | 2019-03-01 | COMP | Rule 16 | 56 | 36 | 31 | 1 |  |  | 151
7558 | 2018-07-24 | 2018-10-20 | 2019-01-02 | 2019-05-31 | COMP | 2019-06-11 | COMP | 2019-04-26 | COMP | 2019-04-24 | COMP | 2019-06-21 | COMP | Rule 15/16 | 63 | 48 | 8 |  | 0 | 40 | 230
7574 | 2018-07-24 | 2018-10-20 | 2019-02-05 | 2019-02-05 | COMP | 2019-04-04 | COMP | 2019-05-31 | COMP | 2022-11-05 | INPR | 2021-08-10 | COMP | Rule 16 | 63 | 71 | 42 | 41 |  |  | 767
7575 | 2018-07-24 | 2018-10-20 | 2019-07-13 | 2019-07-13 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-11-25 | COMP | 2020-01-14 | COMP | Rule 16 | 63 | 181 | 71 | 1 | 24 | 33 | 370
7678 | 2018-07-24 | 2018-10-25 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-03-27 | COMP | 2019-05-01 | COMP | Rule 15/16 | 67 | 23 | 6 | 1 | 76 | 26 | 194
7695 | 2018-07-24 | 2018-10-25 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-28 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-05-02 | COMP | Rule 16 | 67 | 73 | 12 | 19 | 1 | 28 | 195
7744 | 2018-07-24 | 2018-10-29 | 2019-01-17 | 2019-01-17 | COMP | 2019-01-23 | NOTN | 2019-01-31 | COMP | 2019-01-23 | COMP | 2019-03-16 | COMP | Other | 69 | 54 |  | 10 | 0 | 31 | 161
8210 | 2018-07-24 | 2018-11-19 | 2019-02-12 | 2019-02-12 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-12-28 | INPR | 2019-07-26 | COMP | Rule 16 | 83 | 57 | 40 | 1 |  |  | 254
8476 | 2018-07-24 | 2018-12-04 | 2019-02-15 | 2019-02-15 | COMP | 2019-05-01 | COMP | 2019-05-02 | COMP | 2019-07-30 | COMP | 2019-08-16 | COMP | Rule 16 | 92 | 51 | 53 | 2 | 62 | 14 | 269
8543 | 2018-07-24 | 2018-12-07 | 2019-03-09 | 2019-11-13 | COMP | 2019-12-05 | COMP | 2019-12-10 | COMP | 2019-12-05 | COMP | 2020-01-16 | COMP | Rule 15/16 | 95 | 62 | 15 | 4 | 0 | 26 | 372
9345 | 2018-07-24 | 2019-01-30 | 2019-05-09 | 2019-05-09 | COMP | 2019-12-11 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | 2020-05-22 | COMP | Rule 16 | 130 | 71 | 149 | 76 | 2 | 38 | 461
9538 | 2018-07-24 | 2019-02-07 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-29 | COMP | 2019-07-31 | COMP | 2019-08-09 | COMP | 2019-08-13 | COMP | Rule 16 | 136 | 51 | 27 | 45 | 8 | 3 | 266
9781 | 2018-07-24 | 2019-02-14 | 2019-05-21 | 2019-07-09 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2020-05-15 | COMP | 2020-05-04 | COMP | Rule 16 | 141 | 68 | 31 | 1 | 186 |  | 447
11087 | 2018-07-24 | 2019-04-12 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-07-30 | COMP | 2019-08-26 | COMP | Rule 16 | 181 | 48 | 6 | 1 | 24 | 20 | 275
11997 | 2018-07-24 | 2019-05-20 | 2019-11-20 | 2019-11-20 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-11-16 | COMP | 2021-01-07 | COMP | Rule 16 | 207 | 129 | 133 | 1 | 118 | 35 | 618
12215 | 2018-07-24 | 2019-05-28 | 2019-07-17 | 2019-07-17 | COMP | 2019-10-16 | COMP | 2019-10-17 | COMP | 2020-07-30 | COMP | 2020-09-01 | COMP | Rule 15/16 | 212 | 36 | 65 | 2 | 198 | 24 | 532
13318 | 2018-07-24 | 2019-07-20 | 2019-08-31 | 2019-08-31 | COMP | 2019-10-11 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-06 | COMP | Rule 16 | 249 | 30 | 29 | 18 | 1 | 2 | 326
15751 | 2018-07-24 | 2019-11-19 | 2020-02-04 | 2020-02-04 | COMP | 2020-04-07 | COMP | 2020-05-22 | COMP | 2020-06-17 | COMP | 2020-07-10 | COMP | Rule 16 | 334 | 51 | 45 | 34 | 18 | 18 | 495
3814 | 2018-07-25 | 2018-07-25 | 2018-07-27 | 2018-07-27 | COMP | 2018-12-17 | COMP | 2018-12-17 | INPR |  | REQD | 2019-01-25 | COMP | Other | 1 | 3 | 98 |  |  |  | 126
3862 | 2018-07-25 | 2018-08-22 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-04 | COMP | 2019-01-08 | COMP | 2019-02-08 | COMP | 2019-03-12 | COMP | Rule 16 | 21 | 72 | 21 | 3 | 23 | 22 | 157
6260 | 2018-07-25 | 2018-08-07 | 2019-05-02 | 2019-05-02 | COMP | 2019-08-07 | COMP | 2019-12-20 | COMP | 2020-02-20 | COMP | 2020-04-15 | COMP | Rule 16 | 10 | 185 | 68 | 94 | 41 | 40 | 433
6493 | 2018-07-25 | 2018-08-21 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-14 | COMP | 2019-05-07 | COMP | 2019-03-20 | COMP | 2019-05-10 | COMP | Rule 15/16 | 20 | 123 | 18 | 39 | 0 | 4 | 200
6618 | 2018-07-25 | 2018-08-31 | 2018-11-10 | 2018-11-10 | COMP | 2019-06-04 | COMP | 2020-01-02 | COMP | 2019-12-26 | COMP | 2020-02-07 | COMP | Rule 16 | 28 | 50 | 139 | 146 | 0 | 26 | 386
6673 | 2018-07-25 | 2018-09-06 | 2019-01-25 | 2019-03-07 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-03-22 | COMP | 2019-04-24 | COMP | Rule 16 | 31 | 96 | 11 | 1 | 2 | 24 | 188
6753 | 2018-07-25 | 2018-09-11 | 2018-12-11 | 2018-12-11 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-07-21 | INPR | 2019-03-12 | COMP | Rule 16 | 34 | 63 | 11 | 1 |  |  | 157
6779 | 2018-07-25 | 2018-09-11 | 2018-10-26 | 2018-12-19 | COMP | 2019-02-04 | COMP | 2019-07-15 | COMP | 2021-02-27 | INPR | 2019-11-07 | COMP | Rule 16 | 34 | 34 | 31 | 113 |  |  | 326
6837 | 2018-07-25 | 2018-09-12 | 2018-12-12 | 2018-12-12 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-02-22 | COMP | 2019-03-28 | COMP | Rule 16 | 35 | 63 | 28 | 1 | 22 | 25 | 169
6955 | 2018-07-25 | 2018-09-19 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-12 | COMP | 2019-02-25 | COMP | 2019-04-18 | COMP | 2019-05-28 | COMP | Rule 16 | 40 | 88 | 12 | 9 | 39 | 28 | 211
7076 | 2018-07-25 | 2018-09-25 | 2018-10-19 | 2018-11-14 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2019-04-21 | INPR | 2019-01-25 | COMP | Rule 16 | 44 | 19 | 5 | 1 |  |  | 126
7085 | 2018-07-25 | 2018-09-26 | 2018-11-10 | 2018-11-10 | COMP | 2019-01-28 | COMP | 2019-02-26 | COMP | 2019-04-08 | COMP | 2019-09-05 | COMP | Rule 16 | 45 | 33 | 50 | 21 | 30 | 106 | 281
7177 | 2018-07-25 | 2018-10-01 | 2018-11-01 | 2018-11-01 | COMP | 2019-04-17 | COMP | 2019-07-11 | COMP | 2019-07-29 | COMP | 2019-08-02 | COMP | Rule 16 | 48 | 24 | 113 | 60 | 13 | 5 | 258
7250 | 2018-07-25 | 2018-10-04 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-08-20 | COMP | 2019-09-24 | COMP | Rule 16 | 51 | 27 | 24 | 1 | 170 | 25 | 294
7724 | 2018-07-25 | 2018-10-26 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-27 | COMP | 2019-08-05 | COMP | 2019-08-16 | COMP | 2019-10-15 | COMP | Rule 16 | 67 | 144 | 24 | 27 | 10 | 42 | 309
7781 | 2018-07-25 | 2018-10-30 | 2019-01-23 | 2019-02-01 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-07-21 | INPR | 2019-04-10 | COMP | Rule 16 | 69 | 56 | 41 | 1 |  |  | 178
7811 | 2018-07-25 | 2018-11-03 | 2018-12-11 | 2018-12-11 | COMP | 2018-12-24 | COMP | 2018-12-24 | COMP | 2019-03-22 | COMP | 2019-01-10 | COMP | Rule 16 | 72 | 24 | 10 | 1 | 61 |  | 116
8105 | 2018-07-25 | 2018-11-15 | 2019-06-13 | 2019-06-13 | COMP | 2019-08-23 | COMP | 2019-10-18 | COMP | 2021-02-11 | COMP | 2021-02-24 | COMP | Rule 16 | 80 | 144 | 51 | 40 | 330 | 9 | 649
8122 | 2018-07-25 | 2018-11-15 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-25 | COMP | 2019-04-12 | COMP | 2019-10-21 | INPR | 2019-07-09 | COMP | Rule 16 | 80 | 84 | 4 | 15 |  |  | 240
8326 | 2018-07-25 | 2018-11-27 | 2019-02-11 | 2019-02-11 | COMP | 2019-03-11 | COMP | 2019-04-29 | COMP | 2019-06-11 | COMP | 2019-06-19 | COMP | Rule 16 | 86 | 52 | 20 | 36 | 31 | 7 | 227
8404 | 2018-07-25 | 2018-11-29 | 2019-02-14 | 2019-02-14 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-04-02 | COMP | 2019-08-21 | COMP | Rule 16 | 88 | 53 | 12 | 1 | 22 | 100 | 271
8681 | 2018-07-25 | 2018-12-15 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-15 | COMP | 2019-04-11 | COMP | 2019-04-09 | COMP | 2019-05-08 | COMP | Rule 16 | 99 | 28 | 15 | 39 | 0 | 20 | 198
9054 | 2018-07-25 | 2019-01-15 | 2019-05-22 | 2019-06-27 | COMP | 2019-06-27 | NOTN | 2019-12-06 | COMP | 2019-12-05 | COMP | 2020-01-08 | COMP | Other | 119 | 90 |  | 112 | 0 | 22 | 365
9835 | 2018-07-25 | 2019-02-20 | 2019-04-22 | 2019-04-22 | COMP | 2019-06-25 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-08-26 | COMP | Rule 16 | 143 | 44 | 46 | 43 | 1 | 2 | 274
9893 | 2018-07-25 | 2019-02-21 | 2020-01-23 | 2020-01-23 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-12-09 | COMP | 2021-02-05 | COMP | Rule 16 | 144 | 232 | 79 | 1 | 146 | 40 | 637
10256 | 2018-07-25 | 2019-03-07 | 2019-05-12 | 2019-05-12 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP | 2021-02-16 | COMP | 2021-03-03 | COMP | Rule 15/16 | 154 | 47 | 437 | 1 | 7 | 12 | 654
11033 | 2018-07-25 | 2019-04-09 | 2019-07-27 | 2019-09-26 | COMP | 2019-10-15 | COMP | 2019-10-17 | COMP | 2020-06-01 | COMP | 2020-07-28 | COMP | Rule 16 | 177 | 77 | 14 | 3 | 155 | 42 | 506
12755 | 2018-07-25 | 2019-06-20 | 2019-10-01 | 2019-10-01 | COMP | 2020-04-03 | COMP | 2020-04-06 | COMP | 2020-04-03 | COMP | 2020-06-01 | COMP | Rule 15/16 | 228 | 72 | 127 | 2 | 0 | 40 | 465
6228 | 2018-07-26 | 2018-08-03 | 2018-10-22 | 2020-04-19 | COMP | 2020-02-21 | COMP | 2020-04-19 | COMP | 2021-02-09 | COMP | 2021-03-10 | COMP | Other | 7 | 56 |  | 41 | 204 | 21 | 658
6292 | 2018-07-26 | 2018-08-09 | 2018-09-25 | 2018-09-25 | COMP | 2019-01-22 | COMP | 2019-04-05 | COMP | 2019-06-05 | COMP | 2019-06-04 | COMP | Rule 16 | 11 | 33 | 80 | 53 | 43 |  | 215
6337 | 2018-07-26 | 2018-08-13 | 2019-05-15 | 2019-12-30 | COMP | 2019-10-10 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2020-09-30 | COMP | Rule 15/16 | 13 | 190 |  | 217 | 1 | 30 | 550
6465 | 2018-07-26 | 2018-08-20 | 2018-10-04 | 2018-10-16 | COMP | 2018-11-01 | COMP | 2018-11-11 | COMP | 2018-11-11 | COMP | 2019-01-11 | COMP | Rule 16 | 18 | 33 | 13 | 7 | 0 | 40 | 116
6511 | 2018-07-26 | 2018-08-24 | 2019-01-07 | 2019-02-07 | COMP | 2019-06-19 | COMP | 2019-07-22 | COMP | 2019-08-30 | COMP | 2019-09-11 | COMP | Rule 15/16 | 22 | 91 | 93 | 23 | 30 | 8 | 284
6635 | 2018-07-26 | 2018-09-01 | 2019-02-04 | 2019-02-04 | COMP | 2019-02-05 | NOTN | 2019-02-08 | COMP | 2019-02-05 | COMP | 2020-02-13 | COMP | Other | 27 | 104 |  | 5 | 0 | 255 | 389
6730 | 2018-07-26 | 2018-09-10 | 2018-11-08 | 2018-11-08 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2020-01-19 | INPR | 2019-10-03 | COMP | Rule 16 | 32 | 44 | 16 | 1 |  |  | 300
7139 | 2018-07-26 | 2018-09-28 | 2018-10-08 | 2018-10-08 | COMP | 2018-10-19 | COMP | 2018-11-13 | COMP | 2018-10-29 | COMP | 2019-02-25 | COMP | Rule 16 | 46 | 7 | 10 | 17 | 0 | 69 | 145
7147 | 2018-07-26 | 2018-09-29 | 2019-04-09 | 2019-04-09 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2022-02-16 | COMP | 2022-03-26 | COMP | Rule 16 | 46 | 130 | 79 | 1 | 643 | 27 | 922
7364 | 2018-07-26 | 2018-10-09 | 2018-11-02 | 2018-11-02 | COMP | 2018-11-26 | COMP | 2019-01-31 | COMP | 2018-12-03 | COMP | 2021-09-03 | COMP | Rule 16 | 53 | 19 | 14 | 46 | 0 | 655 | 783
7461 | 2018-07-26 | 2018-10-15 | 2019-01-30 | 2019-01-30 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-05-20 | COMP | 2019-07-16 | COMP | Rule 16 | 57 | 72 | 64 | 1 | 15 | 40 | 244
7643 | 2018-07-26 | 2018-10-24 | 2019-03-08 | 2019-05-21 | COMP | 2019-07-08 | COMP | 2019-08-27 | INPR | 2019-07-22 | COMP | 2019-08-23 | COMP | Rule 15/16 | 64 | 91 | 33 |  |  |  | 272
7651 | 2018-07-26 | 2018-10-24 | 2018-12-01 | 2018-12-01 | COMP | 2018-12-10 | COMP | 2018-12-12 | COMP | 2019-04-21 | INPR | 2019-01-30 | COMP | Rule 16 | 64 | 25 | 6 | 3 |  |  | 128
8039 | 2018-07-26 | 2018-11-12 | 2019-03-26 | 2019-03-26 | COMP | 2019-08-26 | COMP | 2019-10-15 | COMP | 2019-09-16 | COMP | 2020-02-04 | COMP | Rule 16 | 76 | 90 | 108 | 36 | 0 | 75 | 382
8840 | 2018-07-26 | 2019-01-02 | 2019-01-24 | 2019-01-24 | COMP | 2019-03-06 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-03-26 | COMP | Rule 16 | 109 | 16 | 29 | 9 | 1 | 7 | 166
9218 | 2018-07-26 | 2019-01-22 | 2019-03-01 | 2019-03-01 | COMP | 2019-05-01 | COMP | 2019-10-25 | COMP | 2020-01-24 | COMP | 2020-03-31 | COMP | Rule 16 | 122 | 28 | 44 | 125 | 60 | 47 | 421
9226 | 2018-07-26 | 2019-01-23 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-06-28 | COMP | 2019-08-05 | COMP | Rule 16 | 123 | 81 | 17 | 1 | 15 | 26 | 258
9712 | 2018-07-26 | 2019-02-12 | 2019-06-01 | 2019-06-01 | COMP | 2019-07-22 | COMP | 2019-09-04 | COMP | 2021-09-16 | COMP | 2021-10-06 | COMP | Rule 16 | 137 | 77 | 35 | 32 | 513 | 15 | 805
9748 | 2018-07-26 | 2019-02-13 | 2019-03-06 | 2019-03-06 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-07-16 | COMP | 2019-09-24 | COMP | Rule 15/16 | 138 | 15 | 100 | 1 | 0 | 43 | 293
10093 | 2018-07-26 | 2019-03-02 | 2019-06-28 | 2019-06-28 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-01-14 | COMP | 2020-01-17 | COMP | Rule 16 | 149 | 84 | 78 | 1 | 59 | 4 | 371
10206 | 2018-07-26 | 2019-03-06 | 2019-05-12 | 2019-05-12 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-09-20 | COMP | 2020-02-18 | COMP | Rule 16 | 152 | 48 | 43 | 1 | 50 | 101 | 391
10437 | 2018-07-26 | 2019-03-16 | 2019-09-14 | 2019-09-14 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-03-16 | COMP | 2020-03-24 | COMP | Rule 16 | 159 | 127 | 123 | 1 | 2 | 7 | 416
12938 | 2018-07-26 | 2019-07-01 | 2019-12-04 | 2019-12-04 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-06-01 | COMP | 2020-07-10 | COMP | Rule 16 | 234 | 108 | 45 | 1 | 80 | 30 | 493
16622 | 2018-07-26 | 2020-01-10 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-19 | COMP | 2020-05-29 | COMP | 2020-10-16 | COMP | 2020-12-04 | COMP | Rule 16 | 366 | 65 | 27 | 8 | 100 | 33 | 594
40568 | 2018-07-26 | 2023-01-12 | 2023-03-27 | 2023-03-27 | COMP | 2023-03-22 | NOTN | 2023-06-16 | COMP | 2023-08-01 | COMP | 2023-12-07 | COMP | Other | 1122 | 51 |  | 59 | 31 | 89 | 1348
3973 | 2018-07-27 | 2018-11-03 | 2019-03-29 | 2019-03-29 | COMP | 2020-04-06 | COMP | 2020-07-01 | COMP | 2020-10-23 | COMP | 2021-02-26 | COMP | Rule 15/16 | 70 | 98 | 257 | 62 | 82 | 84 | 649
3979 | 2018-07-27 | 2018-11-05 | 2019-01-14 | 2019-01-15 | COMP | 2020-09-17 | COMP | 2020-09-18 | COMP | 2020-08-10 | COMP | 2020-11-13 | COMP | Rule 15/16 | 71 | 46 | 424 | 2 | 0 | 40 | 580
6269 | 2018-07-27 | 2018-08-07 | 2018-10-30 | 2018-11-13 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2020-07-04 | INPR | 2019-05-16 | COMP | Rule 16 | 8 | 60 | 83 | 1 |  |  | 202
6433 | 2018-07-27 | 2018-08-18 | 2018-10-04 | 2018-10-04 | COMP | 2018-11-02 | COMP | 2018-11-02 | COMP | 2018-11-20 | COMP | 2019-04-04 | COMP | Rule 16 | 16 | 33 | 22 | 1 | 12 | 92 | 172
6699 | 2018-07-27 | 2018-09-07 | 2019-01-18 | 2019-01-18 | COMP | 2019-01-25 | NOTN | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-02-25 | COMP | Other | 30 | 91 |  | 5 | 1 | 21 | 144
6714 | 2018-07-27 | 2018-09-11 | 2018-12-15 | 2018-12-15 | COMP | 2019-02-04 | COMP | 2019-03-05 | COMP | 2019-02-27 | COMP | 2019-04-18 | COMP | Rule 15/16 | 32 | 66 | 33 | 21 | 0 | 33 | 182
6771 | 2018-07-27 | 2018-09-11 | 2018-10-16 | 2018-10-19 | COMP | 2018-11-06 | COMP | 2019-01-14 | COMP | 2023-04-30 | INPR | 2019-02-07 | COMP | Rule 16 | 32 | 26 | 13 | 45 |  |  | 133
7024 | 2018-07-27 | 2018-09-24 | 2019-02-20 | 2019-02-20 | COMP | 2019-02-05 | NOTN | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-04-11 | COMP | Other | 41 | 101 |  | 5 | 1 | 33 | 177
7172 | 2018-07-27 | 2018-10-01 | 2019-01-31 | 2019-01-31 | COMP | 2019-05-22 | COMP | 2020-06-08 | COMP | 2020-06-23 | COMP | 2020-08-21 | COMP | Rule 16 | 46 | 83 | 79 | 263 | 12 | 44 | 522
7214 | 2018-07-27 | 2018-10-02 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-05-13 | COMP | 2019-06-18 | COMP | Rule 16 | 47 | 79 | 26 | 1 | 50 | 26 | 224
7271 | 2018-07-27 | 2018-10-04 | 2018-11-15 | 2018-11-15 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-01 | COMP | 2019-05-10 | COMP | Rule 16 | 49 | 30 | 94 | 1 | 0 | 28 | 198
7384 | 2018-07-27 | 2018-10-09 | 2018-12-19 | 2018-12-19 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-09-11 | COMP | 2020-10-21 | COMP | Rule 16 | 52 | 49 | 302 | 1 | 136 | 29 | 564
7591 | 2018-07-27 | 2018-10-22 | 2018-12-21 | 2018-12-21 | COMP | 2018-12-31 | COMP | 2019-03-12 | COMP | 2019-07-21 | INPR | 2019-04-03 | COMP | Rule 16 | 61 | 42 | 6 | 49 |  |  | 171
7644 | 2018-07-27 | 2018-10-24 | 2019-02-11 | 2019-02-11 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2020-08-24 | COMP | 2020-08-26 | COMP | Rule 16 | 63 | 73 | 75 | 1 | 315 | 3 | 525
7730 | 2018-07-27 | 2018-10-27 | 2019-03-14 | 2019-05-10 | COMP | 2019-05-29 | COMP | 2019-06-13 | COMP | 2019-08-06 | COMP | 2019-09-05 | COMP | Rule 16 | 65 | 92 | 13 | 12 | 38 | 22 | 279
7796 | 2018-07-27 | 2018-10-31 | 2019-01-24 | 2019-01-24 | COMP | 2019-04-16 | COMP | 2019-06-21 | COMP | 2019-06-20 | COMP | 2019-08-21 | COMP | Rule 15/16 | 68 | 56 | 58 | 48 | 0 | 43 | 269
7940 | 2018-07-27 | 2018-11-06 | 2019-01-08 | 2019-01-08 | COMP | 2019-02-06 | COMP | 2019-07-13 | COMP | 2021-04-26 | COMP | 2021-05-10 | COMP | Rule 16 | 72 | 41 | 21 | 110 | 449 | 11 | 700
8195 | 2018-07-27 | 2018-11-17 | 2018-12-21 | 2018-12-21 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-03-29 | COMP | 2019-04-05 | COMP | Rule 16 | 79 | 23 | 57 | 1 | 11 | 6 | 173
8666 | 2018-07-27 | 2018-12-14 | 2020-03-06 | 2020-03-06 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-12-08 | COMP | 2021-02-22 | COMP | Rule 16 | 97 | 307 | 42 | 1 | 152 | 51 | 645
8810 | 2018-07-27 | 2018-12-30 | 2019-05-29 | 2019-05-29 | COMP | 2019-08-20 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2021-04-23 | COMP | Rule 16 | 106 | 104 | 59 | 147 | 1 | 276 | 689
9184 | 2018-07-27 | 2019-01-20 | 2019-03-28 | 2019-03-28 | COMP | 2019-06-19 | COMP | 2019-08-13 | COMP | 2022-07-30 | INPR | 2020-05-06 | COMP | Rule 16 | 120 | 47 | 59 | 39 |  |  | 446
9282 | 2018-07-27 | 2019-01-27 | 2019-05-02 | 2019-05-02 | COMP | 2019-08-15 | COMP | 2019-08-26 | COMP | 2019-08-31 | COMP | 2019-11-10 | COMP | Rule 16 | 124 | 68 | 74 | 8 | 5 | 49 | 325
9359 | 2018-07-27 | 2019-01-31 | 2019-03-30 | 2019-03-30 | COMP | 2019-05-10 | COMP | 2019-07-16 | COMP | 2019-07-28 | COMP | 2019-08-27 | COMP | Rule 15/16 | 128 | 41 | 30 | 46 | 9 | 22 | 273
10064 | 2018-07-27 | 2019-02-28 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-07-18 | COMP | Rule 16 | 147 | 42 | 18 | 1 | 1 | 41 | 245
10285 | 2018-07-27 | 2019-03-08 | 2019-07-12 | 2019-07-12 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-12-10 | COMP | 2019-12-16 | COMP | Rule 16 | 153 | 89 | 58 | 1 | 47 | 5 | 348
11000 | 2018-07-27 | 2019-04-08 | 2019-10-25 | 2019-10-25 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-08-04 | COMP | 2020-10-05 | COMP | Rule 16 | 174 | 142 | 68 | 1 | 128 | 44 | 552
11105 | 2018-07-27 | 2019-04-12 | 2019-05-30 | 2019-05-30 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-01-19 | INPR | 2019-09-18 | COMP | Rule 16 | 178 | 34 | 27 | 1 |  |  | 288
12050 | 2018-07-27 | 2019-05-22 | 2019-07-16 | 2019-07-16 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2019-09-14 | COMP | 2019-10-08 | COMP | Rule 16 | 206 | 38 | 14 | 1 | 30 | 17 | 302
12627 | 2018-07-27 | 2019-06-17 | 2019-09-11 | 2019-09-11 | COMP | 2020-07-15 | COMP | 2020-07-29 | COMP | 2020-09-24 | COMP | 2020-10-13 | COMP | Rule 16 | 223 | 61 | 213 | 11 | 41 | 14 | 558
13211 | 2018-07-27 | 2019-07-16 | 2019-09-24 | 2019-09-24 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-07-13 | COMP | 2020-07-26 | COMP | Rule 16 | 243 | 50 | 174 | 1 | 29 | 10 | 502
40569 | 2018-07-27 | 2023-01-12 | 2023-04-10 | 2023-04-10 | COMP | 2023-04-10 | NOTN | 2023-10-06 | COMP | 2023-09-19 | COMP | 2023-10-11 | COMP | Other | 1121 | 61 |  | 126 | 0 | 4 | 1309
6355 | 2018-07-28 | 2018-08-13 | 2019-01-16 | 2019-07-01 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2019-10-28 | COMP | 2020-01-16 | COMP | Rule 15/16 | 11 | 107 | 68 | 1 | 17 | 54 | 368
7215 | 2018-07-28 | 2018-10-03 | 2019-04-10 | 2019-08-15 | COMP | 2019-08-20 | NOTN | 2019-08-20 | COMP | 2019-05-07 | COMP | 2019-09-18 | COMP | Other | 47 | 129 |  | 4 | 0 | 21 | 287
9739 | 2018-07-28 | 2019-02-13 | 2019-04-03 | 2019-04-03 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2021-07-01 | COMP | 2021-07-22 | COMP | Rule 15/16 | 136 | 35 | 318 | 1 | 250 | 15 | 750
4085 | 2018-07-29 | 2019-01-17 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-25 | COMP | 2019-04-02 | COMP | 2019-08-02 | COMP | 2019-08-03 | COMP | Rule 16 | 118 | 36 | 11 | 7 | 87 | 1 | 255
6964 | 2018-07-29 | 2018-09-20 | 2018-12-26 | 2018-12-26 | COMP | 2018-12-31 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-12 | COMP | Rule 16 | 38 | 66 | 4 | 44 | 1 | 6 | 154
7150 | 2018-07-29 | 2018-09-28 | 2019-01-05 | 2019-01-05 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-03-13 | COMP | 2019-04-17 | COMP | Rule 16 | 44 | 66 | 43 | 1 | 4 | 26 | 180
12951 | 2018-07-29 | 2019-07-01 | 2019-10-12 | 2019-10-12 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-11-18 | COMP | 2020-12-09 | COMP | Rule 16 | 232 | 73 | 32 | 1 | 247 | 14 | 595
4045 | 2018-07-30 | 2018-12-27 | 2019-05-31 | 2019-05-31 | COMP | 2019-08-09 | COMP | 2019-10-25 | COMP | 2020-08-19 | COMP | 2020-12-07 | COMP | Rule 16 | 104 | 108 | 50 | 55 | 206 | 75 | 593
6153 | 2018-07-30 | 2018-07-31 | 2018-09-28 | 2018-11-29 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2018-11-27 | COMP | 2019-03-07 | COMP | Rule 16 | 2 | 43 | 48 | 1 | 0 | 20 | 151
6231 | 2018-07-30 | 2018-08-06 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-19 | COMP | 2019-02-20 | COMP | 2019-01-31 | COMP | 2019-05-17 | COMP | Rule 15/16 | 6 | 115 | 20 | 2 | 0 | 63 | 202
6400 | 2018-07-30 | 2018-08-15 | 2018-11-27 | 2018-11-27 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-07-22 | COMP | 2019-08-19 | COMP | Rule 16 | 13 | 71 | 159 | 1 | 6 | 21 | 266
6485 | 2018-07-30 | 2018-08-21 | 2018-11-05 | 2019-04-26 | COMP | 2019-12-18 | COMP | 2018-11-28 | COMP | 2020-07-13 | COMP | 2020-08-21 | COMP | Rule 16 | 17 | 54 | 163 |  | 409 | 30 | 521
6527 | 2018-07-30 | 2018-08-25 | 2018-12-07 | 2019-04-26 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-12-04 | COMP | 2021-01-08 | COMP | Rule 16 | 20 | 71 | 163 | 1 | 244 | 24 | 615
6560 | 2018-07-30 | 2018-08-27 | 2019-08-18 | 2020-02-21 | COMP | 2020-04-08 | COMP | 2020-10-22 | INPR | 2020-08-15 | COMP | 2020-11-02 | COMP | Rule 15/16 | 21 | 245 | 34 |  |  |  | 571
6574 | 2018-07-30 | 2018-08-27 | 2019-02-14 | 2019-02-14 | COMP | 2019-11-12 | COMP | 2019-10-18 | INPR | 2019-11-19 | COMP | 2019-12-05 | COMP | Rule 16 | 21 | 117 | 189 |  |  |  | 340
6638 | 2018-07-30 | 2018-09-01 | 2019-02-15 | 2019-02-15 | COMP | 2019-02-19 | NOTN | 2019-09-03 | COMP | 2019-03-04 | COMP | 2020-02-14 | COMP | Other | 25 | 113 |  | 139 | 0 | 113 | 388
6700 | 2018-07-30 | 2018-09-07 | 2018-11-14 | 2018-11-14 | COMP | 2019-01-02 | COMP | 2019-01-30 | COMP | 2019-01-18 | COMP | 2019-02-08 | COMP | Rule 16 | 29 | 48 | 32 | 20 | 0 | 8 | 133
6750 | 2018-07-30 | 2018-09-10 | 2019-02-23 | 2019-04-26 | COMP | 2019-05-15 | COMP | 2019-07-18 | COMP | 2019-07-15 | COMP | 2019-08-17 | COMP | Rule 15/16 | 30 | 113 | 14 | 45 | 0 | 22 | 265
6752 | 2018-07-30 | 2018-09-11 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-06 | COMP | 2018-12-20 | COMP | 2019-07-21 | INPR | 2019-02-07 | COMP | Rule 16 | 31 | 51 | 10 | 11 |  |  | 132
6781 | 2018-07-30 | 2018-09-11 | 2018-11-21 | 2018-11-21 | COMP | 2018-11-28 | COMP | 2019-01-15 | COMP | 2020-02-24 | COMP | 2020-06-01 | COMP | Rule 16 | 31 | 51 | 4 | 33 | 278 | 70 | 462
6790 | 2018-07-30 | 2018-09-11 | 2018-11-12 | 2018-11-12 | COMP | 2018-12-31 | COMP | 2018-12-31 | COMP | 2019-02-20 | COMP | 2019-05-01 | COMP | Rule 16 | 31 | 44 | 32 | 1 | 35 | 51 | 190
6921 | 2018-07-30 | 2018-09-17 | 2018-12-05 | 2018-12-20 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-01-03 | COMP | 2019-03-04 | COMP | Rule 16 | 35 | 55 | 9 | 1 | 1 | 41 | 148
6944 | 2018-07-30 | 2018-09-18 | 2018-12-26 | 2019-01-31 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-03-15 | COMP | 2019-04-12 | COMP | Rule 16 | 36 | 68 | 8 | 1 | 24 | 21 | 177
7022 | 2018-07-30 | 2018-09-23 | 2019-07-15 | 2019-07-15 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-11-26 | COMP | 2019-12-19 | COMP | Rule 16 | 39 | 202 | 32 | 1 | 64 | 16 | 350
7023 | 2018-07-30 | 2018-09-23 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-16 | COMP | 2019-09-13 | COMP | 2019-10-07 | COMP | 2020-02-12 | COMP | Rule 15/16 | 39 | 128 | 35 | 84 | 17 | 87 | 386
7148 | 2018-07-30 | 2018-09-28 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-02 | COMP | 2019-04-03 | COMP | 2019-04-23 | COMP | 2019-05-23 | COMP | Rule 15/16 | 44 | 117 | 10 | 2 | 15 | 23 | 206
7152 | 2018-07-30 | 2018-09-29 | 2018-11-19 | 2018-11-19 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-02-20 | COMP | 2019-03-05 | COMP | Rule 16 | 44 | 35 | 19 | 1 | 44 | 10 | 149
7223 | 2018-07-30 | 2018-10-03 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-06-04 | COMP | 2019-06-29 | COMP | Rule 16 | 47 | 125 | 11 | 1 | 33 | 19 | 231
7291 | 2018-07-30 | 2018-10-05 | 2018-12-07 | 2018-12-07 | COMP | 2019-03-04 | COMP | 2019-04-25 | COMP | 2019-12-09 | COMP | 2019-12-20 | COMP | Rule 15/16 | 49 | 43 | 58 | 39 | 157 | 10 | 351
7398 | 2018-07-30 | 2018-10-10 | 2019-01-05 | 2019-01-05 | COMP | 2019-04-15 | COMP | 2019-05-10 | COMP | 2019-04-15 | COMP | 2019-05-30 | COMP | Rule 16 | 52 | 58 | 69 | 20 | 0 | 14 | 210
7471 | 2018-07-30 | 2018-10-16 | 2018-11-14 | 2019-03-18 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-08-13 | COMP | 2019-09-12 | COMP | Rule 15/16 | 56 | 21 | 37 | 1 | 69 | 22 | 283
7483 | 2018-07-30 | 2018-10-16 | 2019-02-04 | 2020-09-11 | COMP | 2020-11-06 | COMP | 2020-12-07 | COMP | 2021-02-01 | COMP | 2021-02-26 | COMP | Rule 15/16 | 56 | 74 | 41 | 19 | 38 | 19 | 648
7508 | 2018-07-30 | 2018-10-18 | 2018-12-18 | 2019-03-22 | COMP | 2019-01-15 | COMP | 2019-03-22 | COMP | 2020-07-04 | INPR | 2019-05-03 | COMP | Rule 16 | 58 | 41 |  | 47 |  |  | 192
7819 | 2018-07-30 | 2018-11-02 | 2018-11-06 | 2018-11-06 | COMP | 2018-11-29 | COMP | 2019-03-19 | COMP | 2021-11-19 | COMP | 2022-01-13 | COMP | Rule 16 | 69 | 3 | 15 | 75 | 676 | 38 | 871
7827 | 2018-07-30 | 2018-11-01 | 2019-01-14 | 2019-01-14 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-08-14 | COMP | 2019-09-25 | COMP | Rule 16 | 68 | 48 | 96 | 1 | 54 | 30 | 292
7856 | 2018-07-30 | 2018-11-02 | 2018-12-17 | 2018-12-17 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-03-14 | COMP | Rule 16 | 69 | 29 | 26 | 1 | 1 | 35 | 156
7899 | 2018-07-30 | 2018-11-05 | 2019-03-01 | 2019-08-14 | COMP | 2019-08-26 | COMP | 2019-08-28 | COMP | 2019-10-07 | COMP | 2020-01-08 | COMP | Rule 16 | 70 | 78 | 9 | 3 | 28 | 63 | 362
8053 | 2018-07-30 | 2018-11-13 | 2019-03-31 | 2019-03-31 | COMP | 2019-04-29 | COMP | 2019-05-06 | COMP | 2019-04-22 | COMP | 2019-06-07 | COMP | Rule 16 | 75 | 93 | 21 | 6 | 0 | 24 | 216
8107 | 2018-07-30 | 2018-11-15 | 2019-05-02 | 2019-05-02 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2021-10-04 | COMP | 2021-11-02 | COMP | Rule 16 | 77 | 115 | 25 | 1 | 587 | 22 | 822
8258 | 2018-07-30 | 2018-11-20 | 2018-12-17 | 2018-12-17 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-05-19 | COMP | 2019-03-14 | COMP | Rule 16 | 80 | 18 | 3 | 1 | 104 |  | 156
8486 | 2018-07-30 | 2018-12-04 | 2019-01-09 | 2019-01-09 | COMP | 2019-03-07 | COMP | 2021-02-27 | REQD | 2019-05-29 | COMP | 2019-06-18 | COMP | Rule 16 | 88 | 25 | 40 |  |  |  | 223
8823 | 2018-07-30 | 2019-01-02 | 2019-03-18 | 2019-03-18 | COMP | 2019-04-18 | COMP | 2019-04-22 | COMP | 2019-04-23 | COMP | 2019-05-06 | COMP | Rule 16 | 107 | 52 | 24 | 3 | 2 | 10 | 193
8986 | 2018-07-30 | 2019-01-10 | 2019-01-18 | 2019-01-18 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-08-06 | COMP | 2019-08-07 | COMP | Rule 16 | 113 | 7 | 5 | 1 | 135 | 2 | 258
9560 | 2018-07-30 | 2019-02-07 | 2019-05-01 | 2019-05-01 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-02-28 | COMP | 2020-03-12 | COMP | Rule 16 | 132 | 59 | 194 | 1 | 15 | 10 | 406
9561 | 2018-07-30 | 2019-02-07 | 2019-04-18 | 2019-04-18 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2019-09-19 | COMP | 2019-10-06 | COMP | Rule 16 | 132 | 50 | 65 | 1 | 44 | 12 | 299
9562 | 2018-07-30 | 2019-02-07 | 2019-04-18 | 2019-04-18 | COMP | 2019-10-18 | COMP | 2019-08-09 | COMP | 2019-10-10 | COMP | 2019-12-09 | COMP | Rule 16 | 132 | 50 | 129 |  | 44 | 40 | 342
10258 | 2018-07-30 | 2019-03-08 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-13 | COMP | 2020-03-31 | COMP | 2020-04-07 | COMP | 2020-10-15 | COMP | Rule 15/16 | 152 | 242 | 15 | 13 | 6 | 136 | 559
10855 | 2018-07-30 | 2019-04-02 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-24 | COMP | 2019-05-30 | COMP | 2019-05-28 | COMP | 2019-07-25 | COMP | Rule 16 | 169 | 33 | 7 | 4 | 0 | 40 | 249
11330 | 2018-07-30 | 2019-04-23 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-05 | COMP | 2019-09-24 | COMP | 2019-09-05 | COMP | 2019-10-14 | COMP | Rule 16 | 184 | 68 | 28 | 14 | 0 | 15 | 305
12775 | 2018-07-30 | 2019-06-21 | 2019-09-20 | 2019-09-20 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-12-15 | COMP | 2021-01-24 | COMP | Rule 16 | 226 | 64 | 141 | 1 | 171 | 26 | 624
12861 | 2018-07-30 | 2019-06-25 | 2019-09-17 | 2019-09-17 | COMP | 2021-02-26 | COMP | 2021-02-26 | COMP | 2021-05-19 | COMP | 2021-06-01 | COMP | Rule 16 | 228 | 59 | 363 | 1 | 59 | 9 | 714
12986 | 2018-07-30 | 2019-07-03 | 2019-09-17 | 2019-09-17 | COMP | 2021-04-30 | COMP | 2021-04-30 | COMP | 2022-01-18 | COMP | 2021-06-01 | COMP | Rule 16 | 234 | 53 | 408 | 1 | 181 |  | 714
14420 | 2018-07-30 | 2019-09-09 | 2019-11-26 | 2020-05-05 | COMP | 2020-07-06 | COMP | 2021-03-22 | COMP | 2021-08-10 | COMP | 2021-09-30 | COMP | Rule 16 | 280 | 56 | 44 | 178 | 100 | 37 | 799
20306 | 2018-07-30 | 2020-06-15 | 2020-06-29 | 2020-06-29 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2020-09-14 | COMP | 2020-10-21 | COMP | Rule 16 | 472 | 11 | 39 | 1 | 17 | 28 | 563
3883 | 2018-07-31 | 2018-09-12 | 2018-10-22 | 2019-01-31 | COMP |  |  |  |  | 2022-01-29 | INPR | 2020-07-05 | COMP | Other | 31 | 29 |  |  |  |  | 485
6646 | 2018-07-31 | 2018-09-04 | 2019-03-13 | 2019-03-13 | COMP | 2019-10-08 | COMP | 2019-10-21 | COMP | 2020-03-04 | COMP | 2020-05-22 | COMP | Rule 16 | 25 | 130 | 147 | 10 | 91 | 58 | 456
6705 | 2018-07-31 | 2018-09-10 | 2019-02-07 | 2019-03-31 | COMP | 2019-04-09 | COMP | 2019-05-02 | COMP | 2019-05-16 | COMP | 2019-06-24 | COMP | Rule 16 | 29 | 103 | 7 | 18 | 11 | 27 | 226
6798 | 2018-07-31 | 2018-09-11 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2020-01-13 | COMP | 2020-02-04 | COMP | Rule 16 | 30 | 62 | 6 | 1 | 269 | 16 | 379
6809 | 2018-07-31 | 2018-09-12 | 2018-11-17 | 2018-11-17 | COMP | 2019-01-31 | COMP | 2019-02-13 | COMP | 2019-03-27 | COMP | 2019-04-30 | COMP | Rule 16 | 31 | 47 | 49 | 10 | 30 | 25 | 188
7208 | 2018-07-31 | 2018-10-02 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-11-15 | COMP | 2020-01-02 | COMP | Rule 16 | 45 | 74 | 45 | 1 | 166 | 31 | 357
7216 | 2018-07-31 | 2018-10-03 | 2018-11-16 | 2019-09-13 | COMP | 2019-09-20 | COMP | 2019-01-11 | COMP | 2019-07-12 | COMP | 2019-11-08 | COMP | Rule 16 | 46 | 32 | 6 |  | 127 | 85 | 323
7243 | 2018-07-31 | 2018-10-04 | 2018-11-20 | 2018-11-20 | COMP | 2018-11-29 | COMP | 2019-02-28 | COMP | 2019-01-15 | COMP | 2019-04-11 | COMP | Rule 16 | 47 | 33 | 6 | 62 | 0 | 31 | 175
7722 | 2018-07-31 | 2018-10-26 | 2019-03-05 | 2019-03-05 | COMP | 2019-03-28 | COMP | 2019-06-19 | COMP | 2019-06-12 | COMP | 2019-07-10 | COMP | Rule 16 | 63 | 86 | 18 | 59 | 0 | 15 | 237
7832 | 2018-07-31 | 2018-11-01 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-03-27 | COMP | 2019-04-22 | COMP | Rule 16 | 67 | 52 | 46 | 1 | 2 | 19 | 182
8065 | 2018-07-31 | 2018-11-15 | 2019-02-25 | 2019-03-13 | COMP | 2019-03-20 | COMP | 2019-03-20 | COMP | 2019-10-21 | INPR | 2019-04-10 | COMP | Rule 16 | 76 | 67 | 6 | 1 |  |  | 174
8385 | 2018-07-31 | 2018-11-28 | 2019-04-30 | 2019-04-30 | COMP | 2019-06-24 | COMP | 2019-10-04 | COMP | 2021-03-02 | COMP | 2021-04-13 | COMP | Rule 16 | 83 | 106 | 39 | 73 | 352 | 31 | 679
8478 | 2018-07-31 | 2018-12-04 | 2019-01-24 | 2019-01-31 | COMP | 2019-02-28 | COMP | 2019-03-06 | COMP | 2020-05-31 | INPR | 2019-04-29 | COMP | Rule 16 | 87 | 35 | 20 | 5 |  |  | 187
8619 | 2018-07-31 | 2018-12-13 | 2019-01-15 | 2019-01-15 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-02-21 | COMP | 2019-06-21 | COMP | Rule 16 | 94 | 22 | 24 | 1 | 3 | 86 | 225
8831 | 2018-07-31 | 2019-01-02 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-03-21 | COMP | 2019-04-04 | COMP | Rule 16 | 106 | 21 | 5 | 1 | 31 | 11 | 170
8860 | 2018-07-31 | 2019-01-03 | 2019-02-26 | 2019-02-26 | COMP | 2021-03-25 | NOTN | 2021-03-25 | INPR | 2020-01-21 | COMP | 2020-06-25 | COMP | Rule 16 | 107 | 37 |  |  |  |  | 479
8962 | 2018-07-31 | 2019-01-09 | 2019-09-09 | 2019-09-09 | COMP | 2019-08-08 | NOTN | 2019-09-09 | COMP | 2019-02-27 | NOTN | 2020-01-27 | COMP | Other | 111 | 169 |  | 1 |  |  | 373
9648 | 2018-07-31 | 2019-02-11 | 2019-07-31 | 2019-07-31 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2021-03-27 | INPR | 2020-02-28 | COMP | Rule 16 | 133 | 120 | 15 | 1 |  |  | 396
9824 | 2018-07-31 | 2019-02-19 | 2019-04-26 | 2019-04-26 | COMP | 2019-08-09 | COMP | 2019-09-09 | COMP | 2023-06-26 | COMP | 2023-07-19 | COMP | Rule 16 | 138 | 49 | 74 | 21 | 954 | 17 | 1248
9847 | 2018-07-31 | 2019-02-20 | 2019-07-08 | 2019-07-08 | COMP | 2019-08-02 | COMP | 2019-09-03 | COMP | 2019-08-06 | COMP | 2019-10-07 | COMP | Rule 15/16 | 139 | 97 | 20 | 22 | 0 | 25 | 299
11937 | 2018-07-31 | 2019-05-18 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-23 | COMP | 2019-10-23 | COMP | 2019-12-11 | COMP | 2019-12-23 | COMP | Rule 16 | 201 | 38 | 31 | 43 | 33 | 9 | 351
12022 | 2018-07-31 | 2019-05-21 | 2019-06-18 | 2020-04-04 | COMP | 2020-04-20 | COMP | 2020-07-17 | COMP | 2022-07-16 | INPR | 2020-11-16 | COMP | Rule 15/16 | 203 | 20 | 11 | 64 |  |  | 579
12158 | 2018-07-31 | 2019-05-24 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-01 | COMP | 2019-11-20 | COMP | 2019-11-25 | COMP | 2020-09-15 | COMP | Rule 16 | 206 | 99 | 15 | 13 | 4 | 204 | 536
3832 | 2018-08-01 | 2018-08-06 | 2019-06-24 | 2019-06-24 | COMP |  | INPR | 2019-11-07 | COMP |  | INPR | 2020-07-01 | COMP | Other | 4 | 222 |  | 97 |  |  | 482
4052 | 2018-08-01 | 2019-01-02 | 2019-07-11 | 2019-07-11 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2023-11-11 | INPR | 2020-03-06 | COMP | Rule 16 | 105 | 133 | 54 | 1 |  |  | 400
4230 | 2018-08-01 | 2019-09-17 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-02 | COMP | 2019-12-10 | COMP | 2020-01-13 | COMP | 2020-01-24 | COMP | Rule 16 | 284 | 38 | 15 | 7 | 23 | 9 | 371
6312 | 2018-08-01 | 2018-08-09 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-12 | COMP | 2019-07-29 | COMP | 2019-08-21 | COMP | 2019-08-24 | COMP | Rule 15/16 | 7 | 140 | 7 | 98 | 18 | 3 | 268
6532 | 2018-08-01 | 2018-08-26 | 2019-06-07 | 2019-10-11 | COMP | 2019-11-04 | COMP | 2019-11-05 | COMP | 2020-01-14 | COMP | 2020-03-02 | COMP | Rule 15/16 | 18 | 196 | 17 | 2 | 46 | 33 | 396
6785 | 2018-08-01 | 2018-09-11 | 2018-11-17 | 2018-11-17 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-01-05 | COMP | 2019-02-26 | COMP | Rule 16 | 29 | 48 | 38 | 1 | 0 | 29 | 142
7169 | 2018-08-01 | 2018-10-01 | 2018-11-14 | 2018-11-14 | COMP | 2019-06-25 | COMP | 2019-06-26 | COMP | 2020-02-07 | COMP | 2020-03-17 | COMP | Rule 15/16 | 43 | 32 | 153 | 2 | 155 | 27 | 407
7326 | 2018-08-01 | 2018-10-08 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-28 | COMP | 2019-03-29 | COMP | 2019-07-26 | COMP | 2019-08-29 | COMP | Rule 15/16 | 48 | 74 | 44 | 2 | 84 | 25 | 272
7505 | 2018-08-01 | 2018-10-17 | 2019-01-12 | 2019-01-12 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-05-09 | COMP | 2019-08-29 | COMP | Rule 16 | 55 | 58 | 30 | 1 | 53 | 79 | 272
7525 | 2018-08-01 | 2018-10-19 | 2019-08-12 | 2020-02-29 | COMP | 2020-04-21 | COMP | 2020-06-10 | COMP | 2020-06-03 | COMP | 2020-06-22 | COMP | Rule 15/16 | 57 | 203 | 37 | 36 | 0 | 9 | 475
7681 | 2018-08-01 | 2018-10-25 | 2019-02-08 | 2019-02-08 | COMP | 2019-02-08 | NOTN | 2019-02-08 | COMP | 2019-02-26 | COMP | 2019-03-22 | COMP | Other | 61 | 71 |  | 1 | 12 | 19 | 160
7739 | 2018-08-01 | 2018-10-29 | 2019-03-27 | 2019-03-27 | COMP | 2019-04-09 | COMP | 2019-04-29 | COMP | 2019-06-04 | COMP | 2019-08-01 | COMP | Rule 16 | 63 | 101 | 10 | 15 | 26 | 42 | 252
7888 | 2018-08-01 | 2018-11-04 | 2019-03-11 | 2019-03-11 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-05-22 | COMP | 2019-08-13 | COMP | Rule 15/16 | 67 | 84 | 22 | 1 | 32 | 58 | 260
7971 | 2018-08-01 | 2018-11-08 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-22 | COMP | 2019-08-13 | COMP | 2023-04-30 | INPR | 2019-08-19 | COMP | Rule 16 | 71 | 78 | 13 | 101 |  |  | 264
8753 | 2018-08-01 | 2018-12-22 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-08-27 | COMP | 2019-10-04 | COMP | Rule 16 | 99 | 91 | 19 | 1 | 63 | 28 | 297
9010 | 2018-08-01 | 2019-01-12 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-10 | COMP | 2019-06-24 | COMP | 2019-05-04 | COMP | 2019-09-16 | COMP | Rule 16 | 112 | 44 | 40 | 31 | 0 | 59 | 283
9363 | 2018-08-01 | 2019-01-31 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-17 | COMP | 2019-05-14 | COMP | 2019-05-16 | COMP | 2019-07-25 | COMP | Rule 16 | 125 | 36 | 19 | 20 | 3 | 49 | 247
9663 | 2018-08-01 | 2019-02-11 | 2019-05-06 | 2019-05-06 | COMP | 2019-05-21 | COMP | 2019-06-07 | COMP | 2019-05-23 | COMP | 2019-07-30 | COMP | Rule 16 | 132 | 60 | 12 | 13 | 0 | 37 | 250
9741 | 2018-08-01 | 2019-02-13 | 2019-05-30 | 2019-05-30 | COMP | 2019-07-26 | COMP | 2021-02-10 | COMP | 2022-12-13 | COMP | 2023-04-12 | COMP | Rule 15/16 | 134 | 75 | 41 | 388 | 464 | 83 | 1180
10201 | 2018-08-01 | 2019-03-06 | 2019-05-16 | 2019-05-25 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2019-07-03 | COMP | 2019-08-01 | COMP | Rule 16 | 148 | 52 | 5 | 1 | 23 | 21 | 252
10732 | 2018-08-01 | 2019-03-28 | 2021-04-08 | 2022-06-06 | COMP | 2022-07-29 | COMP | 2023-01-09 | COMP | 2023-05-01 | COMP | 2023-07-18 | COMP | Rule 15/16 | 164 | 512 | 38 | 111 | 79 | 54 | 1246
11385 | 2018-08-01 | 2019-04-24 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-10-28 | COMP | 2020-01-08 | COMP | Rule 16 | 183 | 103 | 28 | 1 | 2 | 48 | 360
12192 | 2018-08-01 | 2019-05-29 | 2020-04-30 | 2021-08-03 | COMP | 2021-08-19 | COMP |  | REQD | 2021-11-19 | COMP | 2023-05-09 | COMP | Rule 15/16 | 207 | 233 | 13 |  |  |  | 1199
3878 | 2018-08-02 | 2018-09-10 | 2018-11-11 | 2018-11-11 | COMP | 2018-12-24 | NOTN | 2018-12-24 | COMP | 2019-06-29 | INPR | 2019-02-05 | COMP | Other | 27 | 45 |  | 28 |  |  | 127
6219 | 2018-08-02 | 2018-08-05 | 2018-11-19 | 2018-11-19 | COMP | 2019-08-02 | COMP | 2022-08-18 | COMP | 2022-08-25 | COMP | 2022-10-05 | COMP | Rule 16 | 2 | 74 | 177 | 767 | 6 | 29 | 1051
6360 | 2018-08-02 | 2018-08-14 | 2018-08-17 | 2018-08-17 | COMP | 2018-08-31 | COMP | 2018-08-31 | COMP | 2019-12-28 | INPR | 2019-08-29 | COMP | Rule 16 | 9 | 4 | 11 | 1 |  |  | 271
6523 | 2018-08-02 | 2018-08-25 | 2018-11-10 | 2018-11-10 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-01-14 | COMP | 2019-03-14 | COMP | Rule 16 | 17 | 54 | 39 | 1 | 3 | 42 | 153
6542 | 2018-08-02 | 2018-08-27 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2018-12-19 | COMP | 2019-01-23 | COMP | Rule 16 | 18 | 64 | 14 | 1 | 3 | 23 | 118
6571 | 2018-08-02 | 2018-08-27 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-02-12 | COMP | 2019-03-18 | COMP | Rule 16 | 18 | 69 | 35 | 1 | 13 | 24 | 155
6706 | 2018-08-02 | 2018-09-10 | 2019-08-14 | 2019-10-18 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2019-12-02 | COMP | 2020-01-02 | COMP | Rule 16 | 27 | 234 | 24 | 1 | 6 | 22 | 355
6786 | 2018-08-02 | 2018-09-11 | 2019-11-17 | 2019-11-17 | COMP | 2020-10-06 | COMP | 2020-10-06 | COMP | 2020-11-16 | COMP | 2021-01-15 | COMP | Rule 16 | 28 | 298 | 224 | 1 | 29 | 41 | 617
6807 | 2018-08-02 | 2018-09-11 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-27 | COMP | 2019-01-03 | COMP | 2019-01-17 | COMP | 2019-03-14 | COMP | Rule 16 | 28 | 48 | 27 | 5 | 11 | 39 | 153
6939 | 2018-08-02 | 2018-09-18 | 2018-10-03 | 2018-10-03 | COMP | 2018-12-26 | COMP | 2019-02-19 | COMP | 2019-02-21 | COMP | 2019-04-04 | COMP | Rule 16 | 33 | 12 | 57 | 37 | 3 | 31 | 168
7140 | 2018-08-02 | 2018-09-28 | 2018-12-16 | 2019-04-19 | COMP | 2019-05-03 | NOTN | 2019-05-03 | COMP | 2018-12-16 | COMP | 2019-06-06 | COMP | Other | 41 | 53 |  | 11 | 0 | 24 | 212
7218 | 2018-08-02 | 2018-10-03 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-01-02 | COMP | Rule 16 | 44 | 30 | 9 | 1 | 1 | 24 | 104
7536 | 2018-08-02 | 2018-10-18 | 2019-01-16 | 2019-01-16 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2019-08-15 | COMP | 2019-09-17 | COMP | Rule 16 | 55 | 60 | 55 | 1 | 94 | 23 | 283
7555 | 2018-08-02 | 2018-10-19 | 2019-01-31 | 2019-01-31 | COMP | 2019-07-10 | COMP | 2019-07-31 | COMP | 2019-09-17 | COMP | 2019-10-15 | COMP | Rule 16 | 56 | 69 | 112 | 16 | 34 | 21 | 303
8071 | 2018-08-02 | 2018-11-15 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-23 | COMP | 2019-02-05 | COMP | 2019-01-25 | COMP | 2019-03-04 | COMP | Rule 16 | 74 | 34 | 12 | 10 | 0 | 19 | 145
8163 | 2018-08-02 | 2018-11-16 | 2019-01-31 | 2019-03-09 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2020-02-12 | COMP | 2020-02-25 | COMP | Rule 16 | 75 | 50 | 11 | 1 | 224 | 9 | 391
8173 | 2018-08-02 | 2018-11-19 | 2019-01-16 | 2019-01-16 | COMP | 2019-01-16 | NOTN | 2019-01-30 | COMP | 2019-01-16 | COMP | 2019-03-21 | COMP | Other | 76 | 39 |  | 10 | 0 | 36 | 158
8289 | 2018-08-02 | 2018-11-26 | 2019-01-16 | 2019-01-16 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-04-26 | COMP | 2019-05-01 | COMP | Rule 16 | 79 | 36 | 50 | 1 | 22 | 4 | 187
8305 | 2018-08-02 | 2018-11-26 | 2019-01-02 | 2019-01-02 | COMP | 2019-03-05 | COMP | 2019-10-14 | COMP | 2019-04-09 | COMP | 2019-04-26 | COMP | Rule 16 | 79 | 26 | 43 | 157 | 0 |  | 184
8570 | 2018-08-02 | 2018-12-10 | 2019-09-20 | 2019-09-20 | COMP | 2019-10-11 | COMP | 2020-08-06 | COMP | 2021-02-10 | COMP | 2021-03-02 | COMP | Rule 16 | 89 | 198 | 16 | 207 | 128 | 14 | 647
8580 | 2018-08-02 | 2018-12-11 | 2019-06-12 | 2020-02-11 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-08-05 | COMP | 2020-08-24 | COMP | Rule 16 | 90 | 127 | 33 | 1 | 93 | 14 | 519
9422 | 2018-08-02 | 2019-02-04 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-06-04 | COMP | 2019-07-22 | COMP | Rule 16 | 126 | 59 | 17 | 1 | 11 | 34 | 243
9799 | 2018-08-02 | 2019-02-15 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-06-13 | COMP | 2019-06-20 | COMP | Rule 16 | 135 | 6 | 24 | 1 | 55 | 6 | 222
10132 | 2018-08-02 | 2019-03-04 | 2019-06-07 | 2019-06-14 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-07-05 | COMP | Rule 15/16 | 145 | 69 | 5 | 1 | 1 | 11 | 232
10615 | 2018-08-02 | 2019-03-23 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-27 | COMP | 2019-09-16 | COMP | 2019-10-17 | COMP | 2019-10-24 | COMP | Rule 15/16 | 159 | 62 | 7 | 56 | 24 | 6 | 310
11153 | 2018-08-02 | 2019-04-15 | 2019-07-27 | 2020-07-09 | COMP | 2020-10-09 | COMP | 2020-11-10 | COMP | 2020-10-28 | COMP | 2020-12-17 | COMP | Rule 15/16 | 175 | 73 | 66 | 23 | 0 | 25 | 598
11289 | 2018-08-02 | 2019-04-22 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-22 | COMP | 2019-08-28 | COMP | 2019-08-19 | COMP | 2019-10-14 | COMP | Rule 16 | 180 | 47 | 18 | 28 | 0 | 33 | 302
12366 | 2018-08-02 | 2019-06-03 | 2019-07-09 | 2019-07-09 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-10-14 | COMP | 2019-10-24 | COMP | Rule 16 | 209 | 26 | 31 | 1 | 39 | 9 | 310
12589 | 2018-08-02 | 2019-06-14 | 2019-08-14 | 2019-08-14 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-11-15 | COMP | 2020-01-14 | COMP | Rule 16 | 218 | 43 | 44 | 1 | 23 | 39 | 363
3881 | 2018-08-03 | 2018-09-13 | 2018-12-20 | 2018-12-20 | COMP | 2018-12-20 | NOTN | 2018-12-20 | COMP | 2019-06-29 | INPR | 2019-03-21 | COMP | Other | 29 | 68 |  | 1 |  |  | 157
6197 | 2018-08-03 | 2018-08-03 | 2018-11-19 | 2020-07-14 | COMP | 2019-10-14 | COMP | 2021-02-03 | COMP | 2020-09-03 | COMP | 2021-03-08 | COMP | Other | 1 | 75 |  | 328 | 0 | 23 | 650
6663 | 2018-08-03 | 2018-09-04 | 2018-12-08 | 2018-12-08 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-04-22 | COMP | 2019-08-08 | COMP | Rule 16 | 22 | 66 | 32 | 1 | 61 | 77 | 255
6986 | 2018-08-03 | 2018-09-20 | 2018-11-04 | 2018-11-04 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-04-04 | COMP | 2019-04-16 | COMP | Rule 16 | 34 | 32 | 14 | 1 | 89 | 9 | 175
7160 | 2018-08-03 | 2018-09-30 | 2018-11-01 | 2018-11-01 | COMP | 2018-11-07 | COMP | 2018-11-07 | COMP | 2019-11-18 | NOTN | 2020-06-29 | COMP | Rule 16 | 40 | 24 | 5 | 1 |  |  | 478
7380 | 2018-08-03 | 2018-10-09 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-03-08 | COMP | 2019-04-22 | COMP | Rule 16 | 47 | 49 | 44 | 1 | 11 | 32 | 179
7457 | 2018-08-03 | 2018-10-15 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-12 | NOTN | 2018-12-12 | COMP | 2019-04-21 | INPR | 2019-01-18 | COMP | Other | 51 | 31 |  | 10 |  |  | 115
7561 | 2018-08-03 | 2018-10-20 | 2020-02-04 | 2020-02-04 | COMP | 2020-07-24 | COMP | 2020-11-17 | COMP | 2021-02-25 | COMP | 2021-04-23 | COMP | Rule 15/16 | 55 | 321 | 122 | 81 | 67 | 42 | 684
7627 | 2018-08-03 | 2018-10-23 | 2019-02-01 | 2019-02-01 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2023-04-22 | INPR | 2019-09-27 | COMP | Rule 16 | 57 | 68 | 81 | 1 |  |  | 290
7799 | 2018-08-03 | 2018-10-31 | 2019-02-05 | 2019-02-05 | COMP | 2019-02-22 | COMP | 2019-03-02 | COMP | 2019-03-02 | COMP | 2019-04-16 | COMP | Rule 16 | 63 | 64 | 13 | 6 | 0 | 32 | 175
8016 | 2018-08-03 | 2018-11-12 | 2019-01-04 | 2019-02-22 | COMP | 2019-04-03 | COMP | 2019-08-19 | COMP | 2020-05-19 | COMP | 2020-05-27 | COMP | Rule 16 | 70 | 35 | 29 | 97 | 189 | 6 | 455
8020 | 2018-08-03 | 2018-11-09 | 2018-11-25 | 2018-11-25 | COMP | 2019-01-25 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-05-20 | COMP | Rule 16 | 70 | 8 | 42 | 310 | 1 | 24 | 451
8221 | 2018-08-03 | 2018-11-19 | 2019-02-15 | 2019-05-16 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2021-01-21 | COMP | 2021-02-25 | COMP | Rule 16 | 75 | 60 | 10 | 1 | 414 | 25 | 643
8280 | 2018-08-03 | 2018-11-26 | 2019-06-19 | 2019-06-19 | COMP | 2019-09-26 | COMP | 2019-11-22 | COMP | 2020-03-10 | COMP | 2020-04-07 | COMP | Rule 15/16 | 78 | 143 | 70 | 41 | 72 | 21 | 420
8390 | 2018-08-03 | 2018-11-29 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-10-21 | INPR | 2019-06-28 | COMP | Rule 16 | 81 | 66 | 17 | 1 |  |  | 227
8433 | 2018-08-03 | 2018-12-01 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | 2019-05-29 | COMP | 2019-06-14 | COMP | Rule 16 | 82 | 37 | 45 | 1 | 43 | 13 | 217
8455 | 2018-08-03 | 2018-12-04 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-14 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-07-08 | COMP | Rule 16 | 84 | 63 | 7 | 30 | 1 | 52 | 232
8747 | 2018-08-03 | 2018-12-21 | 2019-03-14 | 2019-07-30 | COMP | 2019-08-21 | COMP | 2020-02-21 | COMP | 2020-03-30 | COMP | 2020-07-11 | COMP | Rule 16 | 97 | 56 | 17 | 125 | 27 | 74 | 487
9127 | 2018-08-03 | 2019-01-17 | 2019-09-06 | 2019-09-06 | COMP | 2020-04-06 | COMP | 2020-06-13 | COMP | 2020-10-06 | COMP | 2020-12-03 | COMP | Rule 15/16 | 114 | 162 | 145 | 49 | 81 | 40 | 587
9319 | 2018-08-03 | 2019-01-30 | 2019-05-22 | 2019-05-22 | COMP | 2020-01-14 | COMP | 2020-01-27 | COMP | 2020-10-20 | COMP | 2021-01-06 | COMP | Rule 16 | 122 | 80 | 162 | 9 | 189 | 52 | 609
9549 | 2018-08-03 | 2019-02-07 | 2019-04-09 | 2021-09-08 | COMP | 2021-10-04 | COMP | 2021-11-09 | COMP | 2019-06-07 | COMP | 2021-12-09 | COMP | Rule 16 | 128 | 43 | 19 | 27 | 0 | 20 | 842
9947 | 2018-08-03 | 2019-02-25 | 2019-03-20 | 2019-03-24 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-11-13 | COMP | 2019-12-12 | COMP | Rule 16 | 139 | 18 | 40 | 1 | 125 | 20 | 341
9973 | 2018-08-03 | 2019-02-27 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-24 | COMP | 2019-09-27 | COMP | 2020-01-27 | COMP | 2021-02-18 | COMP | Rule 16 | 141 | 70 | 14 | 68 | 81 | 269 | 638
10449 | 2018-08-03 | 2019-03-17 | 2019-08-07 | 2019-08-09 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-10-21 | COMP | 2020-11-25 | COMP | Rule 16 | 153 | 101 | 145 | 1 | 160 | 25 | 583
10454 | 2018-08-03 | 2019-03-18 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-16 | COMP | 2019-10-14 | COMP | 2023-09-02 | INPR | 2020-07-20 | COMP | Rule 16 | 154 | 32 | 13 | 105 |  |  | 493
10458 | 2018-08-03 | 2019-03-18 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-12 | NOTN | 2019-08-15 | COMP | 2019-07-12 | COMP | 2019-10-14 | COMP | Other | 154 | 83 |  | 25 | 0 | 42 | 301
11732 | 2018-08-03 | 2019-05-09 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-26 | COMP | 2019-10-16 | INPR | 2019-10-31 | COMP | 2019-11-20 | COMP | Rule 16 | 192 | 20 | 36 |  |  |  | 327
10857 | 2018-08-04 | 2019-04-02 | 2019-08-12 | 2019-08-12 | COMP | 2019-10-14 | NOTN | 2020-01-27 | COMP | 2019-11-27 | COMP | 2020-12-07 | COMP | Other | 164 | 93 |  | 114 | 0 | 220 | 588
7096 | 2018-08-05 | 2018-09-26 | 2018-12-12 | 2018-12-12 | COMP | 2019-02-07 | COMP | 2019-04-05 | COMP | 2019-09-16 | COMP | 2019-10-15 | COMP | Rule 16 | 37 | 53 | 39 | 41 | 114 | 22 | 301
7309 | 2018-08-05 | 2018-10-08 | 2019-01-28 | 2019-02-11 | COMP | 2019-02-12 | NOTN | 2019-06-10 | COMP | 2019-07-20 | COMP | 2019-08-30 | COMP | Other | 45 | 75 |  | 84 | 29 | 30 | 270
8271 | 2018-08-05 | 2018-11-21 | 2019-01-17 | 2019-05-17 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-09-30 | COMP | 2019-10-01 | COMP | Rule 16 | 76 | 38 | 45 | 1 | 50 | 2 | 291
3901 | 2018-08-06 | 2018-09-26 | 2018-11-06 | 2018-11-06 | COMP | 2018-12-13 | COMP | 2019-01-02 | COMP | 2019-04-18 | COMP | 2019-06-14 | COMP | Rule 16 | 37 | 30 | 25 | 13 | 75 | 41 | 216
6677 | 2018-08-06 | 2018-09-06 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-11-24 | INPR | 2019-07-17 | COMP | Rule 16 | 23 | 53 | 18 | 1 |  |  | 238
6743 | 2018-08-06 | 2018-09-10 | 2018-11-29 | 2018-11-29 | COMP | 2019-01-14 | COMP | 2019-02-19 | COMP | 2019-07-21 | INPR | 2019-04-19 | COMP | Rule 16 | 25 | 56 | 31 | 25 |  |  | 177
6748 | 2018-08-06 | 2018-09-10 | 2018-11-16 | 2018-12-04 | COMP | 2018-12-27 | NOTN | 2018-12-27 | COMP | 2019-03-18 | COMP | 2019-04-23 | COMP | Other | 25 | 49 |  | 17 | 55 | 27 | 179
6749 | 2018-08-06 | 2018-09-10 | 2018-11-17 | 2018-11-17 | COMP | 2019-01-10 | COMP | 2019-01-10 | COMP | 2019-03-12 | COMP | 2019-04-23 | COMP | Rule 16 | 25 | 49 | 35 | 1 | 42 | 31 | 179
6784 | 2018-08-06 | 2018-09-11 | 2020-07-03 | 2020-07-03 | COMP | 2020-08-31 | COMP | 2020-09-21 | COMP | 2020-08-10 | COMP | 2020-10-29 | COMP | Rule 15/16 | 26 | 456 | 42 | 15 | 0 | 29 | 564
6969 | 2018-08-06 | 2018-09-19 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-22 | COMP | 2019-03-04 | COMP | 2019-04-08 | COMP | 2019-05-02 | COMP | Rule 16 | 32 | 63 | 44 | 7 | 26 | 19 | 186
7000 | 2018-08-06 | 2018-09-22 | 2018-12-28 | 2018-12-28 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-03-18 | COMP | 2019-04-24 | COMP | Rule 16 | 34 | 66 | 44 | 1 | 11 | 28 | 180
7186 | 2018-08-06 | 2018-10-02 | 2018-12-05 | 2018-12-05 | COMP | 2019-01-16 | COMP | 2019-05-07 | COMP | 2023-05-24 | COMP | 2023-07-25 | COMP | Rule 16 | 41 | 44 | 29 | 78 | 1019 | 42 | 1248
7274 | 2018-08-06 | 2018-10-04 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-02-04 | COMP | 2019-02-20 | COMP | Rule 16 | 43 | 42 | 6 | 1 | 36 | 12 | 135
7489 | 2018-08-06 | 2018-10-16 | 2018-11-18 | 2018-11-18 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-03-10 | COMP | 2019-04-03 | COMP | Rule 16 | 51 | 23 | 66 | 1 | 9 | 18 | 165
7611 | 2018-08-06 | 2018-10-22 | 2019-01-31 | 2019-05-25 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-06-25 | COMP | 2019-09-03 | COMP | Rule 16 | 55 | 68 | 20 | 1 | 2 | 49 | 271
7718 | 2018-08-06 | 2018-10-26 | 2019-01-04 | 2019-01-04 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-03-28 | COMP | 2019-05-09 | COMP | Rule 15/16 | 59 | 46 | 51 | 1 | 8 | 31 | 191
7723 | 2018-08-06 | 2018-10-26 | 2019-01-17 | 2019-01-17 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-07-21 | INPR | 2019-03-05 | COMP | Rule 16 | 59 | 55 | 11 | 1 |  |  | 144
8068 | 2018-08-06 | 2018-11-14 | 2019-01-17 | 2019-10-08 | COMP | 2019-11-08 | COMP | 2019-09-04 | COMP | 2020-04-20 | COMP | 2020-05-12 | COMP | Rule 15/16 | 71 | 43 | 24 |  | 157 | 17 | 444
8389 | 2018-08-06 | 2018-11-28 | 2019-02-01 | 2019-02-01 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-03-22 | COMP | 2019-06-10 | COMP | Rule 16 | 79 | 45 | 34 | 1 | 2 | 56 | 212
8414 | 2018-08-06 | 2018-11-30 | 2019-01-02 | 2019-01-02 | COMP | 2019-02-28 | COMP | 2019-03-12 | COMP | 2019-03-11 | COMP | 2019-04-19 | COMP | Rule 16 | 81 | 22 | 40 | 9 | 0 | 29 | 177
9238 | 2018-08-06 | 2019-01-24 | 2019-05-11 | 2019-05-11 | COMP | 2019-06-28 | COMP | 2019-10-16 | COMP | 2019-11-12 | COMP | 2019-11-23 | COMP | Rule 16 | 117 | 76 | 34 | 77 | 19 | 9 | 328
10351 | 2018-08-06 | 2019-03-12 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-06 | COMP | 2020-09-01 | COMP | 2020-09-22 | COMP | 2020-11-24 | COMP | Rule 15/16 | 149 | 239 | 11 | 127 | 15 | 45 | 581
10457 | 2018-08-06 | 2019-03-18 | 2019-07-09 | 2019-11-25 | COMP | 2019-11-25 | NOTN | 2019-11-25 | COMP | 2019-07-08 | COMP | 2020-01-31 | COMP | Other | 153 | 80 |  | 1 | 0 | 45 | 373
12579 | 2018-08-06 | 2019-06-13 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2020-08-10 | COMP | 2020-09-14 | COMP | Rule 15/16 | 215 | 22 | 54 | 1 | 219 | 25 | 531
14256 | 2018-08-06 | 2019-08-31 | 2019-10-29 | 2019-10-29 | COMP | 2020-03-10 | COMP | 2020-05-06 | COMP | 2020-04-09 | COMP | 2020-07-23 | COMP | Rule 16 | 270 | 41 | 89 | 42 | 0 | 56 | 495
16158 | 2018-08-06 | 2019-12-12 | 2020-02-05 | 2020-02-05 | COMP | 2020-03-16 | COMP | 2020-12-21 | COMP | 2021-01-22 | COMP | 2021-02-19 | COMP | Rule 16 | 340 | 37 | 28 | 196 | 22 | 20 | 638
16895 | 2018-08-06 | 2020-01-22 | 2020-02-26 | 2020-02-26 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-08-04 | COMP | 2020-08-11 | COMP | Rule 16 | 366 | 25 | 63 | 1 | 52 | 6 | 508
3863 | 2018-08-07 | 2018-08-22 | 2018-10-09 | 2018-10-09 | COMP | 2018-10-01 | NOTN | 2018-12-10 | COMP | 2023-04-29 | INPR | 2019-02-05 | COMP | Other | 12 | 34 |  | 42 |  |  | 124
3995 | 2018-08-07 | 2018-11-10 | 2019-08-21 | 2020-07-10 | COMP | 2020-08-07 | COMP | 2021-11-23 | COMP | 2022-04-19 | COMP | 2022-05-03 | COMP | Rule 15/16 | 68 | 194 | 21 | 326 | 102 | 11 | 941
6431 | 2018-08-07 | 2018-08-17 | 2018-10-04 | 2018-10-04 | COMP | 2019-03-20 | COMP | 2019-03-20 | COMP | 2020-07-04 | INPR | 2019-05-17 | COMP | Rule 16 | 9 | 34 | 113 | 1 |  |  | 196
6505 | 2018-08-07 | 2018-08-23 | 2019-01-31 | 2019-05-14 | COMP | 2019-06-26 | COMP | 2019-06-10 | COMP | 2020-03-21 | INPR | 2019-07-02 | COMP | Other | 13 | 109 | 31 |  |  |  | 227
6539 | 2018-08-07 | 2018-08-27 | 2018-10-30 | 2019-02-07 | COMP | 2019-02-13 | COMP | 2019-03-21 | COMP | 2019-02-15 | COMP | 2019-04-05 | COMP | Rule 15/16 | 15 | 46 | 5 | 26 | 0 | 12 | 166
6602 | 2018-08-07 | 2018-08-29 | 2019-03-10 | 2019-03-10 | COMP | 2019-04-15 | COMP | 2019-06-07 | COMP | 2019-12-28 | INPR | 2019-09-09 | COMP | Rule 15/16 | 17 | 130 | 26 | 39 |  |  | 274
6608 | 2018-08-07 | 2018-08-30 | 2019-01-17 | 2019-01-17 | COMP | 2019-06-10 | COMP | 2020-10-22 | COMP | 2020-11-05 | COMP | 2020-12-17 | COMP | Rule 15/16 | 18 | 95 | 100 | 348 | 11 | 28 | 595
6614 | 2018-08-07 | 2018-08-30 | 2019-06-10 | 2019-06-10 | COMP | 2019-09-03 | COMP | 2020-10-21 | COMP | 2020-10-11 | COMP | 2021-02-01 | COMP | Rule 15/16 | 18 | 194 | 60 | 288 | 0 | 68 | 624
6664 | 2018-08-07 | 2018-09-05 | 2018-11-17 | 2018-11-17 | COMP | 2019-01-09 | COMP | 2019-03-19 | COMP | 2019-03-25 | COMP | 2019-04-29 | COMP | Rule 16 | 21 | 52 | 34 | 48 | 5 | 26 | 182
6689 | 2018-08-07 | 2018-09-06 | 2018-09-27 | 2018-09-27 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-08-20 | COMP | 2019-08-29 | COMP | Rule 16 | 22 | 16 | 47 | 1 | 179 | 8 | 268
6697 | 2018-08-07 | 2018-09-07 | 2018-11-10 | 2018-11-10 | COMP | 2018-11-15 | COMP | 2018-12-31 | COMP | 2019-01-16 | COMP | 2019-01-29 | COMP | Rule 16 | 23 | 46 | 3 | 30 | 12 | 9 | 119
6822 | 2018-08-07 | 2018-09-12 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-07 | COMP | 2019-03-19 | COMP | 2019-06-06 | COMP | 2019-07-05 | COMP | Rule 16 | 26 | 70 | 32 | 28 | 57 | 21 | 229
6840 | 2018-08-07 | 2018-09-12 | 2018-11-01 | 2018-11-14 | COMP | 2018-11-27 | COMP | 2018-11-30 | COMP | 2019-01-09 | COMP | 2019-02-06 | COMP | Rule 16 | 26 | 37 | 8 | 4 | 27 | 20 | 125
7086 | 2018-08-07 | 2018-09-26 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-21 | COMP | 2019-04-18 | COMP | 2020-09-09 | COMP | 2020-09-24 | COMP | Rule 16 | 36 | 83 | 18 | 41 | 353 | 12 | 538
7113 | 2018-08-07 | 2018-09-28 | 2018-10-10 | 2018-10-10 | COMP | 2018-10-31 | COMP | 2018-11-19 | COMP | 2018-12-04 | COMP | 2019-02-04 | COMP | Rule 16 | 38 | 9 | 16 | 13 | 10 | 42 | 123
7181 | 2018-08-07 | 2018-10-01 | 2018-10-31 | 2019-04-10 | COMP | 2019-07-23 | COMP | 2019-05-08 | COMP | 2019-09-01 | INPR | 2019-05-09 | COMP | Rule 16 | 39 | 23 | 73 |  |  |  | 190
7228 | 2018-08-07 | 2018-10-03 | 2019-01-24 | 2019-01-24 | COMP | 2019-01-31 | COMP | 2019-02-04 | COMP | 2019-01-12 | COMP | 2019-03-04 | COMP | Rule 15/16 | 41 | 76 | 6 | 3 | 0 | 20 | 142
7541 | 2018-08-07 | 2018-10-19 | 2019-02-13 | 2019-02-13 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2019-10-21 | COMP | 2019-11-03 | COMP | Rule 16 | 53 | 78 | 172 | 1 | 4 | 10 | 313
7571 | 2018-08-07 | 2018-10-20 | 2019-03-04 | 2019-03-04 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-04-09 | COMP | 2020-05-13 | COMP | Rule 15/16 | 53 | 89 | 280 | 1 | 0 | 24 | 444
7659 | 2018-08-07 | 2018-10-24 | 2018-12-15 | 2018-12-15 | COMP | 2019-01-15 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-04-23 | COMP | Rule 16 | 56 | 35 | 20 | 58 | 1 | 12 | 178
7713 | 2018-08-07 | 2018-10-27 | 2018-12-06 | 2018-12-06 | COMP | 2018-12-20 | COMP | 2018-12-21 | COMP | 2019-05-03 | COMP | 2019-05-13 | COMP | Rule 16 | 58 | 26 | 11 | 2 | 92 | 7 | 192
7748 | 2018-08-07 | 2018-10-29 | 2018-12-18 | 2018-12-18 | COMP | 2019-02-11 | COMP | 2019-02-12 | COMP | 2019-04-16 | COMP | 2019-05-03 | COMP | Rule 16 | 59 | 34 | 37 | 2 | 45 | 14 | 186
7754 | 2018-08-07 | 2018-10-29 | 2019-02-11 | 2019-02-11 | COMP | 2019-02-19 | COMP | 2019-03-11 | COMP | 2019-05-08 | COMP | 2019-05-31 | COMP | Rule 16 | 59 | 70 | 6 | 15 | 43 | 17 | 205
7815 | 2018-08-07 | 2018-11-01 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-06 | COMP | 2019-02-15 | COMP | 2019-04-30 | COMP | 2019-05-30 | COMP | Rule 16 | 62 | 57 | 8 | 8 | 52 | 22 | 204
7837 | 2018-08-07 | 2018-11-02 | 2019-02-20 | 2019-02-20 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-12-28 | INPR | 2019-08-02 | COMP | Rule 16 | 63 | 72 | 90 | 1 |  |  | 249
7859 | 2018-08-07 | 2018-11-02 | 2019-01-05 | 2019-01-05 | COMP | 2019-01-16 | COMP | 2019-01-17 | COMP | 2019-01-16 | COMP | 2019-03-13 | COMP | Rule 16 | 63 | 41 | 8 | 2 | 0 | 38 | 149
7864 | 2018-08-07 | 2018-11-03 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-07 | COMP | 2018-12-07 | COMP | 2018-12-21 | COMP | 2019-03-11 | COMP | Rule 16 | 63 | 16 | 7 | 1 | 11 | 53 | 147
7872 | 2018-08-07 | 2018-11-03 | 2019-02-11 | 2019-02-11 | COMP | 2019-02-12 | NOTN | 2019-10-25 | COMP | 2019-10-25 | COMP | 2020-01-28 | COMP | Other | 63 | 65 |  | 181 | 1 | 62 | 369
8082 | 2018-08-07 | 2018-11-15 | 2018-11-29 | 2018-11-29 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2020-04-16 | COMP | 2020-04-22 | COMP | Rule 16 | 71 | 9 | 193 | 1 | 155 | 5 | 429
8281 | 2018-08-07 | 2018-11-26 | 2019-07-31 | 2019-07-31 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2020-05-22 | COMP | 2020-06-22 | COMP | Other | 76 | 172 | 17 | 1 | 189 | 21 | 471
8283 | 2018-08-07 | 2018-11-26 | 2019-08-20 | 2019-08-20 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-05-22 | COMP | 2020-06-22 | COMP | Other | 76 | 186 | 74 | 1 | 118 | 21 | 471
8342 | 2018-08-07 | 2018-11-28 | 2019-03-15 | 2019-03-15 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | 2019-04-27 | COMP | 2019-05-01 | COMP | Rule 16 | 78 | 74 | 11 | 1 | 21 | 3 | 184
8393 | 2018-08-07 | 2018-11-30 | 2019-02-23 | 2019-02-23 | COMP | 2019-08-05 | COMP | 2019-05-10 | COMP | 2019-08-02 | COMP | 2019-09-09 | COMP | Rule 16 | 80 | 57 | 114 |  | 59 | 26 | 274
8724 | 2018-08-07 | 2018-12-19 | 2019-03-14 | 2019-03-14 | COMP | 2019-03-21 | NOTN | 2019-05-15 | COMP | 2019-03-21 | NOTN | 2020-02-20 | COMP | Other | 93 | 58 |  | 45 |  |  | 385
9006 | 2018-08-07 | 2019-01-12 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-06-20 | COMP | 2019-07-30 | COMP | Rule 16 | 108 | 68 | 29 | 1 | 15 | 28 | 246
9011 | 2018-08-07 | 2019-01-12 | 2019-03-21 | 2019-03-21 | COMP | 2019-05-20 | COMP | 2019-06-06 | COMP | 2019-10-08 | COMP | 2020-01-24 | COMP | Rule 15/16 | 108 | 47 | 43 | 13 | 87 | 73 | 367
9016 | 2018-08-07 | 2019-01-12 | 2019-05-22 | 2019-05-22 | COMP | 2019-12-26 | COMP | 2019-09-27 | COMP | 2021-02-27 | INPR | 2019-11-04 | COMP | Rule 16 | 108 | 91 | 150 |  |  |  | 314
9131 | 2018-08-07 | 2019-01-17 | 2019-03-11 | 2019-03-15 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-08-19 | COMP | 2019-08-28 | COMP | Rule 16 | 112 | 36 | 12 | 1 | 99 | 8 | 267
9287 | 2018-08-07 | 2019-01-28 | 2019-02-12 | 2019-02-12 | COMP | 2019-03-06 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-04-23 | COMP | Rule 16 | 118 | 12 | 16 | 2 | 1 | 34 | 178
9371 | 2018-08-07 | 2019-02-01 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-10-15 | COMP | 2019-12-03 | COMP | Rule 16 | 122 | 63 | 5 | 1 | 113 | 33 | 332
10049 | 2018-08-07 | 2019-02-28 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-20 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-07-27 | COMP | Rule 16 | 140 | 57 | 24 | 2 | 1 | 25 | 244
10092 | 2018-08-07 | 2019-03-02 | 2019-05-08 | 2019-06-26 | COMP | 2019-09-23 | COMP | 2019-10-18 | COMP | 2020-06-16 | COMP | 2020-07-13 | COMP | Rule 16 | 141 | 48 | 62 | 20 | 165 | 20 | 486
10323 | 2018-08-07 | 2019-03-11 | 2019-06-27 | 2019-06-27 | COMP | 2020-02-04 | COMP | 2020-02-20 | COMP | 2020-04-16 | COMP | 2020-05-27 | COMP | Rule 15/16 | 147 | 78 | 151 | 12 | 41 | 29 | 453
10532 | 2018-08-07 | 2019-03-19 | 2019-08-31 | 2019-08-31 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-04-30 | COMP | 2020-05-24 | COMP | Rule 16 | 153 | 117 | 123 | 1 | 44 | 17 | 451
11102 | 2018-08-07 | 2019-04-12 | 2019-08-07 | 2019-08-07 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2021-02-04 | COMP | 2021-03-15 | COMP | Rule 16 | 171 | 82 | 182 | 1 | 195 | 27 | 653
11407 | 2018-08-07 | 2019-04-25 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-19 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2020-01-16 | COMP | Other | 180 | 71 | 11 | 9 | 1 | 95 | 362
11971 | 2018-08-07 | 2019-05-20 | 2019-10-15 | 2019-12-13 | COMP | 2020-01-21 | COMP | 2020-02-04 | COMP | 2020-03-12 | COMP | 2020-06-01 | COMP | Rule 15/16 | 197 | 104 | 25 | 11 | 27 | 57 | 456
13269 | 2018-08-07 | 2019-07-18 | 2020-01-07 | 2020-01-07 | COMP | 2020-04-27 | COMP | 2020-06-11 | COMP | 2021-09-21 | COMP | 2021-09-21 | COMP | Other | 238 | 118 | 78 | 33 | 323 | 1 | 786
6357 | 2018-08-08 | 2018-08-13 | 2018-11-01 |  | REQD | 2024-02-13 | COMP | 2018-12-18 | COMP | 2018-12-28 | COMP | 2019-01-29 | COMP | Rule 16 | 4 |  |  |  | 8 | 21 | 118
6528 | 2018-08-08 | 2018-08-25 | 2018-11-09 | 2018-11-09 | COMP | 2018-11-15 | COMP | 2018-11-15 | COMP | 2018-11-19 | COMP | 2019-01-07 | COMP | Rule 16 | 13 | 54 | 4 | 1 | 3 | 32 | 103
6548 | 2018-08-08 | 2018-08-27 | 2018-11-29 | 2018-11-29 | COMP | 2019-02-27 | COMP | 2019-03-04 | COMP | 2019-04-03 | COMP | 2019-04-06 | COMP | Rule 16 | 14 | 65 | 61 | 4 | 23 | 3 | 165
6769 | 2018-08-08 | 2018-09-11 | 2019-02-15 | 2019-02-15 | COMP | 2019-09-24 | COMP | 2019-10-03 | COMP | 2019-11-01 | COMP | 2019-12-06 | COMP | Rule 15/16 | 24 | 108 | 154 | 8 | 22 | 23 | 334
6835 | 2018-08-08 | 2018-09-12 | 2018-12-20 | 2018-12-20 | COMP | 2018-12-19 | NOTN | 2018-12-20 | COMP | 2019-01-08 | COMP | 2019-02-01 | COMP | Other | 25 | 69 |  | 1 | 12 | 18 | 121
6854 | 2018-08-08 | 2018-09-13 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-10 | COMP | 2018-11-29 | COMP | 2019-02-19 | COMP | 2019-04-12 | COMP | Rule 16 | 26 | 43 | 18 |  | 55 | 39 | 170
6926 | 2018-08-08 | 2018-09-19 | 2018-12-20 | 2018-12-20 | COMP | 2019-01-04 | COMP | 2019-02-04 | COMP | 2019-02-01 | COMP | 2019-02-28 | COMP | Rule 15/16 | 30 | 64 | 10 | 21 | 0 | 18 | 139
6949 | 2018-08-08 | 2018-09-18 | 2019-02-02 | 2019-02-02 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-03-15 | COMP | Rule 16 | 29 | 93 | 11 | 1 | 1 | 19 | 150
6967 | 2018-08-08 | 2018-09-19 | 2018-12-07 | 2018-12-07 | COMP | 2019-07-15 | COMP | 2019-11-06 | COMP | 2019-11-19 | COMP | 2019-12-10 | COMP | Rule 16 | 30 | 55 | 151 | 82 | 9 | 14 | 336
6994 | 2018-08-08 | 2018-09-21 | 2018-12-19 | 2018-12-19 | COMP | 2019-03-22 | COMP | 2019-03-22 | NOTN | 2019-07-21 | INPR | 2019-04-04 | COMP | Rule 16 | 32 | 61 | 64 |  |  |  | 164
7043 | 2018-08-08 | 2018-09-24 | 2018-11-09 | 2018-11-21 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2018-12-18 | COMP | 2019-02-26 | COMP | Rule 16 | 33 | 35 | 13 | 1 | 6 | 47 | 137
7142 | 2018-08-08 | 2018-09-28 | 2019-02-12 | 2019-02-12 | COMP | 2019-08-26 | COMP | 2020-04-27 | COMP | 2020-05-29 | COMP | 2020-10-06 | COMP | Rule 16 | 37 | 92 | 137 | 168 | 24 | 92 | 545
7351 | 2018-08-08 | 2018-10-09 | 2018-11-07 | 2018-11-07 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-03-26 | COMP | 2019-04-10 | COMP | Rule 16 | 44 | 22 | 44 | 1 | 50 | 12 | 168
7532 | 2018-08-08 | 2018-10-18 | 2018-12-12 | 2018-12-12 | COMP | 2019-04-23 | COMP | 2019-04-24 | COMP | 2019-03-11 | COMP | 2019-05-23 | COMP | Rule 16 | 51 | 37 | 91 | 2 | 0 | 22 | 199
7556 | 2018-08-08 | 2018-10-19 | 2019-01-10 | 2019-01-10 | COMP | 2019-06-27 | COMP | 2019-07-18 | COMP | 2019-07-11 | COMP | 2019-09-04 | COMP | Rule 16 | 52 | 55 | 118 | 15 | 0 | 34 | 270
7613 | 2018-08-08 | 2018-10-23 | 2018-11-15 | 2018-11-15 | COMP | 2019-01-10 | COMP | 2019-01-30 | COMP | 2019-01-08 | COMP | 2019-03-18 | COMP | Rule 16 | 54 | 17 | 37 | 14 | 0 | 33 | 151
7828 | 2018-08-08 | 2018-11-01 | 2019-01-24 | 2019-01-24 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2020-02-29 | INPR | 2019-09-30 | COMP | Rule 16 | 61 | 55 | 55 | 1 |  |  | 288
8253 | 2018-08-08 | 2018-11-21 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-17 | COMP | 2019-01-18 | COMP | 2019-08-28 | COMP | 2019-08-29 | COMP | Rule 16 | 74 | 32 | 7 | 2 | 155 | 2 | 267
8426 | 2018-08-08 | 2018-12-01 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-04-03 | COMP | 2019-05-03 | COMP | Rule 16 | 79 | 53 | 12 | 1 | 21 | 23 | 185
8470 | 2018-08-08 | 2018-12-04 | 2019-02-26 | 2019-02-26 | COMP | 2019-09-09 | COMP | 2019-10-29 | COMP | 2019-10-24 | COMP | 2020-04-29 | COMP | Rule 15/16 | 81 | 57 | 137 | 37 | 0 | 125 | 433
8530 | 2018-08-08 | 2018-12-07 | 2020-03-19 | 2020-03-19 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2023-04-15 | INPR | 2021-11-24 | COMP | Rule 16 | 84 | 321 | 7 | 1 |  |  | 830
8712 | 2018-08-08 | 2018-12-19 | 2019-02-26 | 2019-03-07 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-10-08 | COMP | 2020-02-07 | COMP | Rule 16 | 92 | 46 | 40 | 1 | 112 | 83 | 376
8723 | 2018-08-08 | 2018-12-19 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-21 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-04-04 | COMP | Rule 16 | 92 | 24 | 20 | 23 | 1 | 9 | 164
9564 | 2018-08-08 | 2019-02-07 | 2019-09-03 | 2019-10-07 | COMP | 2019-10-22 | COMP | 2020-02-13 | COMP | 2020-02-19 | COMP | 2020-04-16 | COMP | Rule 16 | 125 | 145 | 12 | 77 | 4 | 42 | 424
10010 | 2018-08-08 | 2019-02-26 | 2019-03-18 | 2019-03-18 | COMP | 2019-06-11 | COMP | 2019-08-27 | COMP | 2020-08-05 | COMP | 2020-10-21 | COMP | Rule 16 | 137 | 15 | 61 | 55 | 238 | 55 | 556
10296 | 2018-08-08 | 2019-03-09 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-31 | COMP | 2019-08-06 | COMP | Rule 16 | 145 | 55 | 10 | 1 | 37 | 5 | 250
10422 | 2018-08-08 | 2019-03-15 | 2019-05-18 | 2019-05-18 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-12-29 | INPR | 2019-08-12 | COMP | Rule 16 | 150 | 46 | 17 | 1 |  |  | 254
10436 | 2018-08-08 | 2019-03-16 | 2019-07-08 | 2019-07-08 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-09-06 | COMP | 2019-10-23 | COMP | Rule 16 | 150 | 79 | 8 | 1 | 37 | 34 | 305
10491 | 2018-08-08 | 2019-03-18 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2020-06-09 | COMP | 2020-06-10 | COMP | Rule 16 | 151 | 14 | 23 | 1 | 276 | 2 | 462
10513 | 2018-08-08 | 2019-03-19 | 2019-06-24 | 2019-06-24 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2019-09-06 | COMP | 2019-09-20 | COMP | Rule 15/16 | 152 | 69 | 15 | 2 | 38 | 11 | 282
10515 | 2018-08-08 | 2019-03-19 | 2019-04-26 | 2019-05-08 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-06-06 | COMP | 2019-07-01 | COMP | Rule 16 | 152 | 29 | 20 | 1 | 2 | 18 | 225
10610 | 2018-08-08 | 2019-03-22 | 2019-06-04 | 2019-06-04 | COMP | 2019-09-11 | COMP | 2019-09-16 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | Rule 16 | 155 | 52 | 70 | 4 | 28 | 19 | 323
10656 | 2018-08-08 | 2019-03-25 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-25 | COMP | 2019-08-19 | COMP | 2019-07-25 | COMP | 2019-09-25 | COMP | Rule 16 | 156 | 47 | 41 | 18 | 0 | 27 | 285
10796 | 2018-08-08 | 2019-03-30 | 2019-07-28 | 2019-07-28 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-08-22 | COMP | 2019-09-25 | COMP | Rule 16 | 160 | 83 | 18 | 1 | 2 | 24 | 285
11142 | 2018-08-08 | 2019-04-15 | 2019-07-08 | 2019-07-08 | COMP | 2019-07-16 | COMP | 2019-08-22 | COMP | 2019-08-27 | COMP | 2019-10-02 | COMP | Rule 16 | 171 | 59 | 7 | 28 | 4 | 26 | 290
11394 | 2018-08-08 | 2019-04-24 | 2019-08-12 | 2019-08-12 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-10-17 | COMP | Rule 16 | 178 | 77 | 18 | 1 | 1 | 31 | 301
12059 | 2018-08-08 | 2019-05-23 | 2019-07-30 | 2019-12-06 | COMP | 2020-01-17 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-06-17 | COMP | Rule 16 | 199 | 47 | 29 | 81 | 1 | 26 | 467
12072 | 2018-08-08 | 2019-05-22 | 2019-12-31 | 2019-12-31 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-02 | COMP | 2020-06-30 | COMP | Rule 15/16 | 198 | 153 | 34 | 1 | 9 | 86 | 476
14070 | 2018-08-08 | 2019-08-23 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-15 | COMP | 2019-11-22 | COMP | 2019-11-20 | COMP | 2020-02-19 | COMP | Rule 16 | 263 | 29 | 9 | 28 | 0 | 58 | 383
3838 | 2018-08-09 | 2018-08-09 | 2019-01-15 | 2019-01-15 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-09-27 | COMP | Rule 16 | 1 | 108 | 50 | 1 | 1 | 130 | 286
3923 | 2018-08-09 | 2018-10-09 | 2018-12-03 | 2018-12-03 | COMP | 2018-12-05 | COMP | 2019-01-23 | COMP | 2019-01-20 | COMP | 2019-01-30 | COMP | Rule 16 | 43 | 37 | 3 | 33 | 0 | 6 | 118
6462 | 2018-08-09 | 2018-08-21 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-27 | COMP | 2019-01-03 | COMP | 2019-09-01 | INPR | 2019-03-28 | COMP | Rule 15/16 | 9 | 60 | 29 | 5 |  |  | 158
6711 | 2018-08-09 | 2018-09-10 | 2018-09-19 | 2018-09-19 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-05-10 | COMP | 2019-06-21 | COMP | Rule 16 | 22 | 8 | 162 | 1 | 0 | 29 | 218
6758 | 2018-08-09 | 2018-09-10 | 2019-01-05 | 2019-01-05 | COMP | 2019-01-23 | NOTN | 2019-01-23 | COMP | 2019-07-12 | COMP | 2019-08-14 | COMP | Other | 22 | 80 |  | 12 | 120 | 24 | 255
6810 | 2018-08-09 | 2018-09-12 | 2019-02-23 | 2019-02-23 | COMP | 2019-04-16 | COMP | 2019-04-26 | COMP | 2019-05-23 | COMP | 2019-07-01 | COMP | Rule 16 | 24 | 111 | 37 | 9 | 20 | 27 | 224
6866 | 2018-08-09 | 2018-09-14 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-05 | COMP | 2018-11-30 | COMP | 2019-03-11 | COMP | 2019-03-28 | COMP | Rule 16 | 26 | 32 | 6 | 17 | 68 | 14 | 158
6867 | 2018-08-09 | 2018-09-13 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-03 | COMP | 2019-01-16 | COMP | 2019-01-15 | COMP | 2019-02-14 | COMP | Rule 16 | 25 | 70 | 7 | 10 | 0 | 21 | 129
6931 | 2018-08-09 | 2018-09-18 | 2018-12-15 | 2018-12-15 | COMP | 2018-12-20 | COMP | 2019-01-02 | COMP | 2019-01-02 | COMP | 2019-01-28 | COMP | Rule 16 | 28 | 61 | 4 | 8 | 1 | 18 | 116
6941 | 2018-08-09 | 2018-09-18 | 2019-03-06 | 2019-03-08 | COMP | 2019-03-07 | NOTN | 2019-03-22 | COMP | 2019-05-16 | COMP | 2019-08-20 | COMP | Other | 28 | 115 |  | 11 | 40 | 67 | 259
7164 | 2018-08-09 | 2018-10-01 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-13 | COMP | 2019-07-23 | COMP | 2019-08-12 | COMP | 2019-08-15 | COMP | Rule 16 | 37 | 170 | 7 | 28 | 15 | 4 | 256
7314 | 2018-08-09 | 2018-10-08 | 2019-03-05 | 2019-03-05 | COMP | 2019-03-14 | COMP | 2019-03-26 | COMP | 2019-05-10 | COMP | 2019-06-19 | COMP | Rule 15/16 | 42 | 100 | 8 | 9 | 34 | 28 | 216
7548 | 2018-08-09 | 2018-10-19 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-22 | COMP | 2019-03-01 | COMP | Rule 16 | 51 | 65 | 12 | 1 | 9 | 6 | 139
7583 | 2018-08-09 | 2018-10-21 | 2019-02-11 | 2019-04-06 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-05-22 | COMP | 2019-06-05 | COMP | Rule 16 | 51 | 75 | 29 | 1 | 5 | 10 | 206
7590 | 2018-08-09 | 2018-10-22 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2019-07-21 | INPR | 2019-04-01 | COMP | Rule 15/16 | 52 | 64 | 18 | 1 |  |  | 160
7805 | 2018-08-09 | 2018-11-01 | 2018-11-30 | 2018-11-30 | COMP | 2018-12-12 | COMP | 2018-12-27 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | Rule 16 | 60 | 19 | 9 | 11 | 52 | 1 | 147
8067 | 2018-08-09 | 2018-11-14 | 2019-01-28 | 2019-03-07 | COMP | 2019-03-27 | COMP | 2019-06-04 | COMP | 2019-09-02 | INPR | 2019-05-07 | COMP | Rule 15/16 | 68 | 49 | 15 | 49 |  |  | 186
8118 | 2018-08-09 | 2018-11-15 | 2019-03-12 | 2019-03-12 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-05-01 | COMP | 2020-06-29 | COMP | Rule 16 | 69 | 78 | 230 | 1 | 60 | 41 | 474
8357 | 2018-08-09 | 2018-11-28 | 2019-04-06 | 2019-04-06 | COMP | 2019-06-26 | COMP | 2019-07-08 | COMP | 2019-08-02 | COMP | 2019-08-16 | COMP | Rule 15/16 | 76 | 89 | 57 | 8 | 20 | 11 | 257
8457 | 2018-08-09 | 2018-12-04 | 2019-02-20 | 2019-02-20 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-05-03 | COMP | 2019-06-21 | COMP | Rule 16 | 80 | 53 | 60 | 1 | 0 | 28 | 218
9233 | 2018-08-09 | 2019-01-26 | 2019-03-29 | 2019-03-29 | COMP | 2019-09-09 | COMP | 2019-09-20 | COMP | 2019-09-09 | COMP | 2019-11-13 | COMP | Rule 15/16 | 115 | 44 | 114 | 10 | 0 | 38 | 318
9241 | 2018-08-09 | 2019-01-24 | 2019-02-04 | 2019-02-04 | COMP | 2019-02-25 | COMP | 2019-02-28 | COMP | 2019-05-15 | COMP | 2019-06-11 | COMP | Rule 16 | 114 | 8 | 15 | 4 | 55 | 19 | 210
9252 | 2018-08-09 | 2019-01-24 | 2019-03-12 | 2019-03-12 | COMP | 2019-04-01 | COMP | 2019-05-30 | COMP | 2019-05-21 | COMP | 2019-06-24 | COMP | Rule 16 | 114 | 33 | 15 | 43 | 0 | 18 | 219
9506 | 2018-08-09 | 2019-02-06 | 2019-05-26 | 2019-05-26 | COMP | 2019-06-27 | COMP | 2019-08-14 | COMP | 2019-08-15 | COMP | 2019-09-20 | COMP | Rule 16 | 123 | 77 | 23 | 34 | 2 | 26 | 281
10265 | 2018-08-09 | 2019-03-07 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-18 | COMP | 2019-05-07 | COMP | 2019-07-09 | COMP | 2019-08-09 | COMP | Rule 16 | 143 | 12 | 20 | 14 | 44 | 24 | 252
10667 | 2018-08-09 | 2019-03-25 | 2019-07-09 | 2020-07-03 | COMP | 2021-03-18 | COMP | 2021-04-20 | COMP | 2021-05-18 | COMP | 2021-06-12 | COMP | Rule 16 | 155 | 75 | 177 | 24 | 21 | 18 | 714
10798 | 2018-08-09 | 2019-03-29 | 2019-05-21 | 2019-05-21 | COMP | 2020-03-05 | COMP | 2020-09-21 | COMP | 2020-10-15 | COMP | 2020-12-01 | COMP | Rule 16 | 159 | 38 | 198 | 141 | 19 | 31 | 581
11259 | 2018-08-09 | 2019-04-19 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-27 | COMP | 2019-12-12 | COMP | 2019-11-25 | COMP | 2020-01-15 | COMP | Rule 16 | 174 | 43 | 7 | 116 | 0 | 23 | 359
12860 | 2018-08-09 | 2019-06-25 | 2020-04-29 | 2023-01-05 | COMP | 2023-02-07 | COMP | 2023-02-10 | COMP | 2023-01-23 | COMP | 2023-04-13 | COMP | Rule 15/16 | 220 | 213 | 23 | 4 | 0 | 44 | 1175
14448 | 2018-08-09 | 2019-09-10 | 2021-01-16 | 2022-08-30 | COMP | 2020-06-10 | NOTN | 2023-02-13 | COMP | 2021-11-01 | COMP | 2023-04-13 | COMP | Other | 273 | 340 |  | 113 | 0 | 43 | 1175
16394 | 2018-08-09 | 2019-12-26 | 2020-06-22 | 2020-06-22 | COMP | 2020-10-07 | COMP | 2022-05-12 | COMP | 2022-11-14 | COMP | 2023-02-14 | COMP | Rule 15/16 | 346 | 124 | 77 | 402 | 128 | 62 | 1134
3912 | 2018-08-10 | 2018-09-28 | 2019-08-09 | 2019-08-09 | COMP | 2019-10-28 | COMP | 2019-11-26 | COMP | 2019-10-21 | COMP | 2020-01-02 | COMP | Rule 15/16 | 35 | 217 | 56 | 21 | 0 | 24 | 349
4086 | 2018-08-10 | 2019-01-19 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-31 | COMP | 2019-06-14 | COMP | 2020-06-26 | COMP | 2020-09-10 | COMP | Rule 16 | 110 | 58 | 34 | 11 | 261 | 54 | 525
6780 | 2018-08-10 | 2018-09-11 | 2019-01-01 | 2019-01-01 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-08 | COMP | 2019-05-22 | COMP | Rule 16 | 22 | 76 | 64 | 1 | 4 | 33 | 196
7026 | 2018-08-10 | 2018-09-24 | 2019-03-27 | 2019-03-27 | COMP | 2019-03-27 | NOTN | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-07-10 | COMP | Other | 31 | 126 |  | 43 | 1 | 32 | 229
7092 | 2018-08-10 | 2018-09-26 | 2018-11-19 | 2018-11-19 | COMP | 2018-11-28 | COMP | 2018-12-10 | COMP | 2019-10-21 | INPR | 2019-04-19 | COMP | Rule 16 | 33 | 38 | 6 | 9 |  |  | 173
7257 | 2018-08-10 | 2018-10-05 | 2019-02-15 | 2019-02-15 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2019-09-03 | COMP | 2019-10-18 | COMP | Rule 15/16 | 40 | 90 | 138 | 1 | 2 | 34 | 300
7357 | 2018-08-10 | 2018-10-09 | 2018-12-26 | 2019-02-21 | COMP | 2019-02-21 | NOTN | 2019-02-21 | COMP | 2019-02-07 | COMP | 2019-03-26 | COMP | Other | 42 | 53 |  | 1 | 0 | 24 | 155
7614 | 2018-08-10 | 2018-10-23 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-07 | COMP | 2019-03-22 | COMP | 2019-03-08 | COMP | 2019-05-01 | COMP | Rule 16 | 52 | 59 | 33 | 12 | 0 | 29 | 181
7810 | 2018-08-10 | 2018-11-03 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-17 | NOTN | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-08-28 | COMP | Other | 60 | 174 |  | 1 | 1 | 31 | 264
7961 | 2018-08-10 | 2018-11-07 | 2019-05-10 | 2021-12-02 | COMP | 2021-12-10 | COMP | 2022-03-09 | COMP | 2022-04-11 | COMP | 2022-05-05 | COMP | Rule 15/16 | 63 | 126 | 7 | 62 | 24 | 19 | 940
8367 | 2018-08-10 | 2018-11-28 | 2019-02-15 | 2019-02-15 | COMP | 2019-11-04 | COMP | 2021-01-27 | COMP | 2022-07-16 | INPR | 2021-03-09 | COMP | Rule 16 | 75 | 55 | 183 | 308 |  |  | 646
8383 | 2018-08-10 | 2018-11-28 | 2019-01-31 | 2019-01-31 | COMP | 2019-05-02 | COMP | 2019-06-26 | COMP | 2021-06-08 | COMP | 2021-06-29 | COMP | Rule 16 | 75 | 44 | 65 | 39 | 491 | 16 | 725
8423 | 2018-08-10 | 2018-12-01 | 2019-02-14 | 2019-02-14 | COMP | 2020-04-06 | COMP | 2020-12-21 | COMP | 2020-10-29 | COMP | 2021-01-22 | COMP | Rule 16 | 77 | 51 | 287 | 181 | 0 | 22 | 615
8489 | 2018-08-10 | 2018-12-04 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-26 | COMP | 2019-04-09 | COMP | 2019-04-23 | COMP | 2019-05-17 | COMP | Rule 16 | 79 | 49 | 29 | 11 | 11 | 19 | 193
8634 | 2018-08-10 | 2018-12-13 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-04 | NOTN | 2019-03-04 | COMP | 2019-03-25 | COMP | 2019-04-15 | COMP | Other | 86 | 54 |  | 1 | 16 | 16 | 169
8646 | 2018-08-10 | 2018-12-14 | 2019-03-25 | 2019-03-25 | COMP | 2019-06-24 | COMP | 2019-09-06 | COMP | 2019-10-15 | COMP | 2019-10-16 | COMP | Rule 16 | 87 | 68 | 65 | 53 | 28 | 2 | 298
8849 | 2018-08-10 | 2019-01-03 | 2019-03-24 | 2019-03-24 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-05-07 | COMP | 2019-06-06 | COMP | Rule 16 | 99 | 55 | 33 | 1 | 0 | 21 | 206
9043 | 2018-08-10 | 2019-01-15 | 2019-03-06 | 2019-04-30 | COMP | 2019-05-22 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-07-05 | COMP | Rule 15/16 | 107 | 35 | 17 | 11 | 1 | 21 | 226
9277 | 2018-08-10 | 2019-01-26 | 2019-05-09 | 2019-05-29 | COMP | 2020-02-03 | COMP | 2020-04-06 | COMP | 2020-03-19 | COMP | 2020-05-01 | COMP | Rule 15/16 | 114 | 73 | 171 | 45 | 0 | 20 | 433
10074 | 2018-08-10 | 2019-03-01 | 2020-11-05 | 2020-11-05 | COMP | 2021-03-23 | COMP | 2021-06-03 | COMP | 2021-06-22 | COMP | 2021-09-13 | COMP | Rule 15/16 | 138 | 428 | 92 | 52 | 14 | 58 | 777
10328 | 2018-08-10 | 2019-03-11 | 2019-07-15 | 2019-07-15 | COMP | 2019-07-24 | COMP | 2019-08-16 | COMP | 2019-08-20 | COMP | 2019-09-19 | COMP | Rule 16 | 144 | 89 | 8 | 18 | 3 | 22 | 279
10432 | 2018-08-10 | 2019-03-15 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2021-05-25 | COMP | 2021-06-26 | COMP | Rule 15/16 | 148 | 149 | 31 | 1 | 376 | 23 | 723
11411 | 2018-08-10 | 2019-04-25 | 2019-08-01 | 2019-08-01 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-11-19 | COMP | 2019-12-27 | COMP | Rule 16 | 177 | 69 | 65 | 1 | 13 | 26 | 346
11412 | 2018-08-10 | 2019-04-25 | 2019-05-21 | 2019-05-21 | COMP | 2019-11-13 | COMP | 2019-11-12 | COMP | 2020-04-01 | COMP | 2020-06-02 | COMP | Rule 16 | 177 | 19 | 123 |  | 96 | 44 | 454
11483 | 2018-08-10 | 2019-04-29 | 2019-12-07 | 2019-12-07 | COMP | 2020-01-30 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2021-01-29 | COMP | Rule 15/16 | 179 | 154 | 36 | 99 | 1 | 155 | 620
12217 | 2018-08-10 | 2019-05-29 | 2019-12-19 | 2019-12-19 | COMP | 2020-02-24 | COMP | 2020-05-22 | COMP | 2020-05-26 | COMP | 2020-08-06 | COMP | Rule 16 | 200 | 142 | 44 | 65 | 2 | 53 | 501
14975 | 2018-08-10 | 2019-10-07 | 2019-11-20 | 2019-11-20 | COMP | 2020-07-01 | COMP | 2020-07-24 | COMP | 2020-07-15 | COMP | 2020-08-24 | COMP | Rule 16 | 291 | 32 | 154 | 18 | 0 | 22 | 513
6933 | 2018-08-11 | 2018-09-18 | 2019-02-22 | 2019-02-22 | COMP | 2019-04-25 | COMP | 2019-06-07 | COMP | 2019-06-06 | COMP | 2019-09-16 | COMP | Rule 16 | 26 | 107 | 45 | 31 | 0 | 70 | 275
6353 | 2018-08-13 | 2018-08-13 | 2019-01-03 | 2019-01-24 | COMP | 2019-01-30 | COMP | 2019-03-01 | COMP | 2019-03-11 | COMP | 2019-04-25 | COMP | Rule 16 | 1 | 98 | 5 | 22 | 7 | 34 | 176
6463 | 2018-08-13 | 2018-08-21 | 2018-10-18 | 2018-10-18 | COMP | 2018-12-07 | COMP | 2020-07-28 | COMP | 2020-11-30 | COMP | 2021-01-08 | COMP | Rule 16 | 7 | 42 | 34 | 413 | 86 | 28 | 605
6808 | 2018-08-13 | 2018-09-12 | 2019-02-26 | 2021-06-23 | COMP | 2021-07-13 | COMP | 2021-07-13 | COMP | 2022-11-05 | INPR | 2021-09-04 | COMP | Rule 16 | 22 | 113 | 14 | 1 |  |  | 771
6943 | 2018-08-13 | 2018-09-18 | 2019-02-11 | 2019-02-11 | COMP | 2019-03-13 | COMP | 2019-09-17 | COMP | 2019-09-22 | COMP | 2020-02-25 | COMP | Rule 16 | 26 | 99 | 22 | 132 | 4 | 105 | 384
7009 | 2018-08-13 | 2018-09-21 | 2019-01-25 | 2019-01-25 | COMP | 2019-06-10 | COMP | 2019-10-30 | COMP | 2020-02-27 | COMP | 2020-04-29 | COMP | Rule 16 | 29 | 85 | 95 | 101 | 80 | 45 | 430
7049 | 2018-08-13 | 2018-09-24 | 2018-12-19 | 2018-12-19 | COMP | 2018-12-18 | NOTN | 2019-04-21 | REQD | 2019-01-25 | COMP | 2019-01-17 | COMP | Other | 30 | 60 |  |  |  |  | 108
7115 | 2018-08-13 | 2018-09-28 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-18 | COMP | 2019-01-30 | COMP | 2018-12-18 | COMP | 2019-03-26 | COMP | Rule 16 | 34 | 35 | 21 | 29 | 0 | 39 | 154
7276 | 2018-08-13 | 2018-10-04 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-09 | COMP | 2019-03-20 | COMP | 2019-06-11 | COMP | 2019-07-12 | COMP | Rule 16 | 38 | 45 | 21 | 49 | 59 | 23 | 230
7490 | 2018-08-13 | 2018-10-16 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-16 | COMP | 2019-01-03 | COMP | 2019-01-04 | COMP | 2019-01-24 | COMP | Rule 16 | 46 | 10 | 14 | 31 | 2 | 14 | 112
7622 | 2018-08-13 | 2018-10-23 | 2019-01-03 | 2019-01-03 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-01-28 | COMP | 2020-02-18 | COMP | Rule 16 | 51 | 48 | 262 | 1 | 7 | 15 | 379
7665 | 2018-08-13 | 2018-10-24 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-05-02 | COMP | 2019-06-17 | COMP | Rule 16 | 52 | 58 | 21 | 1 | 53 | 32 | 212
7703 | 2018-08-13 | 2018-10-26 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-06 | COMP | 2018-12-06 | INPR | 2018-12-26 | COMP | 2019-01-02 | COMP | Rule 16 | 54 | 13 | 15 |  |  |  | 97
7806 | 2018-08-13 | 2018-11-01 | 2018-12-31 | 2018-12-31 | COMP | 2019-01-15 | COMP | 2019-03-04 | COMP | 2019-01-21 | COMP | 2019-04-15 | COMP | Rule 16 | 58 | 39 | 11 | 33 | 0 | 31 | 168
8162 | 2018-08-13 | 2018-11-16 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-23 | COMP | 2019-05-30 | COMP | 2019-05-06 | COMP | 2019-06-05 | COMP | Rule 15/16 | 68 | 37 | 7 | 90 | 0 | 5 | 204
8502 | 2018-08-13 | 2018-12-05 | 2019-02-03 | 2019-02-03 | COMP | 2019-03-07 | NOTN | 2019-08-20 | COMP | 2019-08-21 | COMP | 2019-09-24 | COMP | Other | 79 | 40 |  | 139 | 2 | 24 | 281
8637 | 2018-08-13 | 2018-12-13 | 2019-02-06 | 2019-02-06 | COMP | 2019-03-25 | COMP | 2020-12-07 | COMP | 2020-07-03 | COMP | 2020-12-09 | COMP | Rule 16 | 85 | 37 | 33 | 431 | 0 | 3 | 585
8658 | 2018-08-13 | 2018-12-13 | 2019-02-14 | 2019-08-16 | COMP | 2019-09-18 | COMP | 2019-08-10 | COMP | 2023-04-22 | INPR | 2019-09-26 | COMP | Rule 16 | 85 | 43 | 23 |  |  |  | 283
8713 | 2018-08-13 | 2018-12-18 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-19 | COMP | 2019-04-23 | COMP | 2019-04-30 | COMP | 2019-07-22 | COMP | Rule 16 | 88 | 39 | 4 | 46 | 6 | 58 | 236
8816 | 2018-08-13 | 2018-12-31 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-28 | COMP | 2019-03-11 | COMP | 2019-05-11 | COMP | 2019-07-02 | COMP | Rule 15/16 | 96 | 23 | 19 | 8 | 45 | 36 | 223
9020 | 2018-08-13 | 2019-01-13 | 2019-03-01 | 2019-03-01 | COMP | 2019-05-23 | COMP | 2019-08-08 | COMP | 2019-08-29 | COMP | 2019-09-24 | COMP | Rule 16 | 104 | 33 | 60 | 54 | 16 | 18 | 281
9911 | 2018-08-13 | 2019-02-22 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2020-01-19 | INPR | 2019-09-27 | COMP | Rule 16 | 132 | 46 | 18 | 1 |  |  | 284
9949 | 2018-08-13 | 2019-02-25 | 2019-06-05 | 2019-11-17 | COMP | 2019-12-06 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-02-19 | COMP | Rule 15/16 | 133 | 72 | 13 | 4 | 1 | 47 | 380
10405 | 2018-08-13 | 2019-03-14 | 2019-07-24 | 2020-07-13 | COMP | 2020-08-11 | COMP | 2021-01-19 | COMP | 2021-08-10 | COMP | 2021-09-21 | COMP | Rule 16 | 146 | 93 | 22 | 109 | 143 | 30 | 782
10640 | 2018-08-13 | 2019-03-23 | 2019-12-03 | 2019-12-03 | COMP | 2020-01-02 | NOTN | 2020-01-02 | COMP | 2020-01-07 | COMP | 2020-03-03 | COMP | Other | 152 | 176 |  | 21 | 4 | 39 | 389
11524 | 2018-08-13 | 2019-05-01 | 2019-08-01 | 2019-08-01 | COMP | 2019-09-12 | COMP | 2019-09-19 | COMP | 2023-04-30 | INPR | 2019-10-12 | COMP | Rule 15/16 | 180 | 65 | 30 | 6 |  |  | 294
11611 | 2018-08-13 | 2019-05-05 | 2019-08-26 | 2019-08-26 | COMP | 2020-02-14 | COMP | 2021-02-09 | COMP | 2024-02-03 | INPR | 2021-05-24 | COMP | Rule 16 | 182 | 79 | 118 | 249 |  |  | 699
11731 | 2018-08-13 | 2019-05-08 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-07-26 | COMP | 2019-08-02 | COMP | Rule 16 | 185 | 45 | 9 | 1 | 4 | 6 | 245
12344 | 2018-08-13 | 2019-06-01 | 2019-07-30 | 2019-07-30 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | 2020-09-17 | COMP | 2020-12-03 | COMP | Rule 15/16 | 201 | 41 | 287 | 1 | 2 | 53 | 581
12521 | 2018-08-13 | 2019-06-10 | 2019-08-01 | 2019-08-01 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-12-17 | COMP | 2020-01-21 | COMP | Rule 16 | 207 | 38 | 42 | 1 | 54 | 23 | 360
12956 | 2018-08-13 | 2019-07-01 | 2019-11-27 | 2019-11-27 | COMP | 2019-12-24 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | 2020-03-24 | COMP | Rule 15/16 | 222 | 105 | 18 | 41 | 1 | 22 | 404
14243 | 2018-08-13 | 2019-08-30 | 2020-01-13 | 2020-01-13 | COMP | 2020-06-29 | COMP | 2020-09-09 | COMP | 2020-06-19 | COMP | 2021-09-15 | COMP | Rule 16 | 265 | 91 | 118 | 52 | 0 | 256 | 778
14369 | 2018-08-13 | 2019-09-06 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-04 | COMP | 2020-06-08 | COMP | 2020-08-25 | COMP | 2020-10-07 | COMP | Rule 16 | 269 | 102 | 21 | 68 | 57 | 31 | 543
15698 | 2018-08-13 | 2019-11-17 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-02-12 | COMP | 2020-02-28 | COMP | Rule 16 | 318 | 17 | 4 | 1 | 39 | 12 | 387
16524 | 2018-08-13 | 2020-01-06 | 2020-05-26 | 2021-07-28 | COMP | 2021-08-06 | COMP | 2021-08-27 | COMP | 2021-08-05 | COMP | 2021-09-17 | COMP | Rule 16 | 350 | 99 | 8 | 16 | 0 | 15 | 780
16533 | 2018-08-13 | 2020-01-06 | 2020-04-24 | 2020-04-29 | COMP | 2020-04-27 | NOTN | 2020-04-29 | COMP | 2020-04-27 | COMP | 2020-06-09 | COMP | Other | 350 | 78 |  | 1 | 0 | 29 | 458
22189 | 2018-08-13 | 2020-09-14 | 2020-09-17 | 2020-09-17 | COMP | 2020-09-19 | NOTN | 2021-02-23 | COMP | 2021-02-17 | COMP | 2021-03-08 | COMP | Other | 526 | 4 |  | 107 | 0 | 10 | 644
3843 | 2018-08-14 | 2018-08-14 | 2018-09-11 | 2018-09-11 | COMP | 2018-10-03 | COMP | 2018-11-09 | COMP | 2019-05-30 | COMP | 2019-06-24 | COMP | Rule 15/16 | 1 | 20 | 17 | 28 | 137 | 18 | 216
3879 | 2018-08-14 | 2018-09-10 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-06 | NOTN | 2018-11-14 | COMP | 2018-11-06 | COMP | 2019-06-18 | COMP | Rule 16 | 19 | 47 |  | 1 | 0 | 148 | 212
6695 | 2018-08-14 | 2018-09-07 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-01-08 | COMP | 2019-03-14 | COMP | Rule 16 | 18 | 50 | 21 | 1 | 14 | 46 | 145
6751 | 2018-08-14 | 2018-09-11 | 2019-01-25 | 2019-01-25 | COMP | 2019-04-05 | COMP | 2019-04-10 | COMP | 2019-07-12 | COMP | 2019-08-19 | COMP | Rule 16 | 20 | 93 | 50 | 4 | 66 | 27 | 255
6948 | 2018-08-14 | 2018-09-18 | 2019-01-30 | 2019-01-30 | COMP | 2019-05-15 | COMP | 2019-05-15 | COMP | 2019-10-14 | COMP | 2019-11-04 | COMP | Rule 16 | 25 | 91 | 75 | 1 | 106 | 16 | 309
7028 | 2018-08-14 | 2018-09-23 | 2019-02-11 | 2019-02-11 | COMP | 2019-03-19 | COMP | 2019-03-19 | NOTN | 2019-03-15 | COMP | 2019-03-22 | COMP | Rule 16 | 28 | 95 | 26 |  |  |  | 151
7094 | 2018-08-14 | 2018-09-26 | 2019-01-31 | 2019-01-31 | COMP | 2019-01-30 | NOTN | 2019-04-12 | COMP | 2019-07-05 | COMP | 2019-07-30 | COMP | Other | 31 | 86 |  | 51 | 59 | 18 | 241
7112 | 2018-08-14 | 2018-09-28 | 2018-11-10 | 2018-11-10 | COMP | 2019-02-25 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-08-22 | COMP | Rule 16 | 33 | 31 | 69 | 48 | 1 | 80 | 258
7346 | 2018-08-14 | 2018-10-09 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-05 | COMP | 2018-11-07 | COMP | 2018-11-07 | NOTN | 2019-01-02 | COMP | Rule 16 | 40 | 16 | 5 | 3 |  |  | 96
7587 | 2018-08-14 | 2018-10-22 | 2018-12-31 | 2018-12-31 | COMP | 2019-01-18 | NOTN | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-03-13 | COMP | Other | 49 | 47 |  | 14 | 1 | 37 | 144
7755 | 2018-08-14 | 2018-10-30 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-22 | COMP | 2019-04-23 | COMP | 2019-04-22 | COMP | 2019-06-26 | COMP | Rule 16 | 55 | 109 | 10 | 2 | 0 | 46 | 218
7834 | 2018-08-14 | 2018-11-01 | 2019-03-01 | 2019-03-01 | COMP | 2019-04-15 | COMP | 2020-09-24 | COMP | 2021-03-02 | COMP | 2021-04-01 | COMP | Rule 15/16 | 57 | 80 | 32 | 367 | 107 | 23 | 661
8013 | 2018-08-14 | 2018-11-09 | 2018-11-28 | 2018-11-28 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2019-01-09 | COMP | 2019-01-22 | COMP | Rule 16 | 63 | 11 | 7 | 1 | 23 | 9 | 109
8083 | 2018-08-14 | 2018-11-15 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-10-21 | INPR | 2019-02-05 | COMP | Rule 16 | 66 | 8 | 33 | 1 |  |  | 119
8334 | 2018-08-14 | 2018-11-28 | 2019-01-25 | 2019-02-21 | COMP | 2019-03-06 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-03-19 | COMP | Rule 16 | 73 | 40 | 10 | 2 | 1 | 9 | 148
8874 | 2018-08-14 | 2019-01-04 | 2020-04-10 | 2020-04-10 | COMP | 2021-02-04 | COMP | 2021-02-04 | COMP | 2021-03-30 | COMP | 2021-04-28 | COMP | Rule 15/16 | 98 | 319 | 207 | 1 | 38 | 22 | 680
8887 | 2018-08-14 | 2019-01-03 | 2020-04-17 | 2020-04-17 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2020-11-12 | COMP | 2021-01-13 | COMP | Rule 15/16 | 97 | 325 | 88 | 1 | 60 | 41 | 607
8968 | 2018-08-14 | 2019-01-09 | 2019-03-14 | 2019-03-14 | COMP | 2019-03-21 | NOTN | 2019-04-09 | COMP | 2019-02-27 | NOTN | 2019-10-02 | COMP | Other | 101 | 45 |  | 19 |  |  | 286
9411 | 2018-08-14 | 2019-02-01 | 2019-03-13 | 2019-03-13 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-06-06 | COMP | 2019-09-18 | COMP | Rule 16 | 117 | 28 | 12 | 1 | 50 | 73 | 276
9507 | 2018-08-14 | 2019-02-06 | 2019-04-05 | 2019-04-05 | COMP | 2019-05-16 | COMP | 2019-07-24 | COMP | 2019-06-06 | COMP | 2019-08-09 | COMP | Rule 16 | 120 | 42 | 30 | 48 | 0 | 13 | 249
9647 | 2018-08-14 | 2019-02-11 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-28 | COMP | 2019-09-23 | COMP | 2023-04-30 | INPR | 2019-09-10 | COMP | Rule 16 | 123 | 27 | 7 | 125 |  |  | 270
9652 | 2018-08-14 | 2019-02-10 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-07-16 | COMP | 2019-08-07 | COMP | Rule 16 | 122 | 27 | 7 | 1 | 77 | 17 | 247
9832 | 2018-08-14 | 2019-02-19 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-10 | COMP | 2019-12-23 | COMP | 2019-12-24 | COMP | 2020-01-06 | COMP | Rule 15/16 | 128 | 132 | 11 | 72 | 2 | 8 | 349
10011 | 2018-08-14 | 2019-02-26 | 2019-04-26 | 2019-04-26 | COMP | 2019-07-31 | COMP | 2020-01-24 | COMP | 2020-01-27 | COMP | 2020-04-26 | COMP | Rule 15/16 | 133 | 44 | 67 | 121 | 2 | 64 | 426
11433 | 2018-08-14 | 2019-04-26 | 2019-08-01 | 2019-08-02 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2019-08-26 | COMP | 2019-09-20 | COMP | Rule 15/16 | 176 | 68 | 2 | 1 | 16 | 19 | 278
11944 | 2018-08-14 | 2019-05-17 | 2019-07-15 | 2019-07-15 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2020-01-24 | COMP | 2020-03-02 | COMP | Rule 15/16 | 191 | 40 | 58 | 1 | 76 | 26 | 387
16221 | 2018-08-14 | 2019-12-16 | 2020-03-13 | 2020-03-13 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | Rule 16 | 336 | 61 | 37 | 1 | 66 | 1 | 497
18073 | 2018-08-14 | 2020-03-10 | 2020-05-27 | 2020-05-27 | COMP | 2021-02-23 | COMP | 2021-02-23 | COMP | 2021-03-19 | COMP | 2023-02-14 | COMP | Rule 16 | 393 | 56 | 187 | 1 | 19 | 480 | 1131
3898 | 2018-08-15 | 2018-09-27 | 2018-10-19 | 2018-10-19 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2018-12-14 | COMP | 2019-04-10 | COMP | Rule 16 | 31 | 17 | 18 | 1 | 21 | 80 | 163
6394 | 2018-08-15 | 2018-08-15 | 2018-10-05 | 2018-10-05 | COMP | 2018-11-01 | COMP | 2019-01-18 | COMP | 2019-02-12 | COMP | 2019-03-07 | COMP | Rule 15/16 | 1 | 37 | 20 | 52 | 17 | 17 | 139
6592 | 2018-08-15 | 2018-08-29 | 2018-10-05 | 2020-07-13 | COMP | 2020-08-07 | COMP | 2020-09-20 | COMP | 2020-08-11 | COMP | 2020-10-02 | COMP | Rule 16 | 11 | 27 | 20 | 30 | 0 | 10 | 538
6826 | 2018-08-15 | 2018-09-12 | 2018-11-10 | 2018-11-10 | COMP | 2018-11-16 | COMP | 2019-01-09 | COMP | 2019-01-15 | COMP | 2019-02-11 | COMP | Rule 15/16 | 20 | 43 | 4 | 35 | 5 | 19 | 122
6942 | 2018-08-15 | 2018-09-18 | 2018-09-19 | 2018-09-19 | COMP | 2019-03-19 | COMP | 2018-11-26 | COMP | 2019-09-22 | INPR | 2019-06-14 | COMP | Rule 16 | 24 | 2 | 123 |  |  |  | 209
7111 | 2018-08-15 | 2018-09-28 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-19 | COMP | 2019-03-26 | COMP | 2019-12-28 | INPR | 2019-06-05 | COMP | Rule 16 | 32 | 58 | 39 | 26 |  |  | 202
7234 | 2018-08-15 | 2018-10-06 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-04 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-04-08 | COMP | Rule 16 | 37 | 66 | 15 | 14 | 1 | 32 | 161
7254 | 2018-08-15 | 2018-10-05 | 2018-11-02 | 2018-11-02 | COMP | 2019-02-26 | COMP | 2019-02-27 | COMP | 2019-11-04 | COMP | 2020-02-03 | COMP | Rule 16 | 37 | 21 | 76 | 2 | 176 | 60 | 367
7255 | 2018-08-15 | 2018-10-05 | 2018-10-27 | 2018-10-27 | COMP | 2019-03-01 | COMP | 2019-03-01 | COMP | 2019-11-04 | COMP | 2020-03-13 | COMP | Rule 16 | 37 | 16 | 83 | 1 | 174 | 88 | 395
7256 | 2018-08-15 | 2018-10-05 | 2018-10-27 | 2018-11-02 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2020-02-25 | COMP | 2020-03-18 | COMP | Rule 16 | 37 | 16 | 76 | 1 | 251 | 17 | 398
7337 | 2018-08-15 | 2018-10-08 | 2018-11-20 | 2018-11-20 | COMP | 2019-06-18 | COMP | 2019-07-09 | COMP | 2019-05-23 | COMP | 2019-08-06 | COMP | Rule 16 | 38 | 31 | 144 | 15 | 0 | 21 | 245
7367 | 2018-08-15 | 2018-10-11 | 2019-03-04 | 2019-03-04 | COMP | 2019-10-07 | COMP | 2019-10-07 | COMP | 2021-01-09 | COMP | 2021-03-04 | COMP | Rule 16 | 41 | 96 | 153 | 1 | 316 | 37 | 640
7410 | 2018-08-15 | 2018-10-11 | 2018-12-15 | 2018-12-15 | COMP | 2019-02-26 | COMP | 2019-03-26 | COMP | 2020-01-16 | COMP | 2020-04-07 | COMP | Rule 16 | 41 | 44 | 48 | 21 | 205 | 57 | 412
7418 | 2018-08-15 | 2018-10-12 | 2019-06-14 | 2019-06-14 | COMP | 2019-11-01 | COMP | 2019-11-25 | COMP | 2020-03-10 | COMP | 2020-03-03 | COMP | Rule 16 | 42 | 168 | 99 | 16 | 71 |  | 387
7419 | 2018-08-15 | 2018-10-12 | 2018-12-17 | 2018-12-17 | COMP | 2018-12-17 | NOTN | 2019-06-13 | COMP | 2019-01-28 | COMP | 2019-09-11 | COMP | Other | 42 | 44 |  | 124 | 0 | 63 | 270
7495 | 2018-08-15 | 2018-10-17 | 2018-12-07 | 2018-12-07 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2020-01-16 | COMP | 2020-04-09 | COMP | Rule 16 | 45 | 35 | 78 | 1 | 201 | 59 | 414
7522 | 2018-08-15 | 2018-10-18 | 2019-02-05 | 2019-02-05 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-07-21 | INPR | 2019-04-23 | COMP | Rule 16 | 46 | 73 | 39 | 1 |  |  | 172
7670 | 2018-08-15 | 2018-10-24 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-05-14 | COMP | 2019-07-02 | COMP | Rule 16 | 50 | 89 | 37 | 1 | 14 | 35 | 221
7814 | 2018-08-15 | 2018-11-01 | 2019-01-02 | 2019-01-02 | COMP | 2019-01-22 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-03-19 | COMP | Rule 16 | 56 | 40 | 14 | 13 | 1 | 28 | 147
7956 | 2018-08-15 | 2018-11-07 | 2019-02-13 | 2021-03-18 | COMP | 2021-03-31 | COMP | 2021-04-01 | COMP | 2021-02-16 | COMP | 2021-04-29 | COMP | Rule 15/16 | 60 | 65 | 10 | 2 | 0 | 21 | 680
8046 | 2018-08-15 | 2018-11-14 | 2019-01-28 | 2019-01-28 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-07-22 | COMP | 2019-06-17 | COMP | Rule 16 | 64 | 49 | 88 | 1 | 36 |  | 210
8109 | 2018-08-15 | 2018-11-15 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-21 | COMP | 2021-01-18 | COMP | 2021-01-19 | COMP | 2021-02-10 | COMP | Rule 15/16 | 65 | 235 | 22 | 289 | 1 | 17 | 625
8217 | 2018-08-15 | 2018-11-19 | 2019-04-02 | 2019-04-02 | COMP | 2019-09-16 | COMP | 2020-03-09 | COMP | 2020-03-03 | COMP | 2020-05-26 | COMP | Rule 16 | 67 | 91 | 117 | 119 | 0 | 56 | 446
8224 | 2018-08-15 | 2018-11-19 | 2019-01-17 | 2019-01-17 | COMP | 2019-02-12 | COMP | 2019-04-11 | COMP | 2019-04-02 | COMP | 2019-04-29 | COMP | Rule 16 | 67 | 40 | 18 | 42 | 0 | 13 | 176
8346 | 2018-08-15 | 2018-11-27 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2021-02-27 | INPR | 2019-07-22 | COMP | Rule 16 | 71 | 66 | 25 | 1 |  |  | 234
8445 | 2018-08-15 | 2018-12-03 | 2019-03-29 | 2019-03-29 | COMP | 2019-10-15 | COMP | 2020-01-06 | COMP | 2020-03-09 | COMP | 2020-04-18 | COMP | Rule 16 | 75 | 81 | 140 | 55 | 44 | 30 | 420
8629 | 2018-08-15 | 2018-12-12 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-03-13 | COMP | 2019-04-17 | COMP | Rule 16 | 82 | 39 | 21 | 1 | 4 | 26 | 168
8837 | 2018-08-15 | 2018-12-31 | 2019-03-15 | 2020-02-18 | COMP | 2020-03-06 | COMP | 2019-09-04 | COMP | 2019-09-05 | COMP | 2020-11-30 | COMP | Rule 16 | 94 | 52 | 14 |  | 2 | 311 | 576
8893 | 2018-08-15 | 2019-01-04 | 2020-09-18 | 2020-09-18 | COMP | 2021-02-02 | COMP | 2021-09-13 | COMP | 2021-09-14 | COMP | 2021-10-19 | COMP | Rule 15/16 | 97 | 432 | 92 | 156 | 2 | 26 | 800
8894 | 2018-08-15 | 2019-01-04 | 2020-09-18 | 2020-09-18 | COMP | 2021-02-02 | COMP | 2021-02-26 | COMP | 2021-07-20 | COMP | 2021-08-23 | COMP | Rule 15/16 | 97 | 432 | 92 | 18 | 101 | 25 | 760
9253 | 2018-08-15 | 2019-01-25 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-07 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-06-18 | COMP | Rule 16 | 111 | 60 | 13 | 3 | 1 | 28 | 211
9340 | 2018-08-15 | 2019-01-30 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-21 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2020-02-07 | COMP | Rule 16 | 114 | 57 | 23 | 140 | 1 | 41 | 371
9386 | 2018-08-15 | 2019-02-01 | 2019-06-10 | 2019-06-10 | COMP | 2019-07-02 | COMP | 2019-07-03 | COMP | 2020-01-16 | COMP | 2020-03-06 | COMP | Rule 15/16 | 116 | 90 | 17 | 2 | 135 | 35 | 390
9392 | 2018-08-15 | 2019-02-01 | 2019-06-12 | 2019-07-03 | COMP | 2019-07-22 | COMP | 2019-10-04 | COMP | 2019-10-21 | COMP | 2019-12-12 | COMP | Rule 16 | 116 | 92 | 13 | 54 | 12 | 36 | 333
9511 | 2018-08-15 | 2019-02-06 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-03 | COMP | 2019-04-10 | COMP | Rule 16 | 119 | 32 | 7 | 1 | 3 | 6 | 163
9971 | 2018-08-15 | 2019-02-27 | 2019-04-02 | 2019-04-02 | COMP | 2019-07-09 | COMP | 2019-11-27 | COMP | 2019-11-06 | COMP | 2019-12-26 | COMP | Rule 16 | 133 | 25 | 69 | 100 | 0 | 19 | 342
9980 | 2018-08-15 | 2019-02-25 | 2019-05-11 | 2019-05-11 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-06-19 | COMP | 2019-07-02 | COMP | Rule 16 | 131 | 55 | 16 | 1 | 12 | 10 | 221
10785 | 2018-08-15 | 2019-03-29 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-14 | COMP | 2020-01-22 | COMP | 2020-01-16 | COMP | 2020-03-14 | COMP | Rule 15/16 | 155 | 21 | 13 | 173 | 0 | 37 | 395
10981 | 2018-08-15 | 2019-04-08 | 2019-05-09 | 2019-05-09 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-06-26 | COMP | Rule 16 | 161 | 24 | 14 | 1 | 1 | 21 | 217
11075 | 2018-08-15 | 2019-04-11 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-24 | COMP | 2020-01-24 | COMP | 2021-11-22 | COMP | 2022-02-03 | COMP | Rule 16 | 164 | 101 | 16 | 83 | 463 | 51 | 873
11538 | 2018-08-15 | 2019-05-01 | 2019-07-15 | 2019-09-17 | COMP | 2019-09-20 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2022-07-25 | COMP | Rule 16 | 178 | 52 | 4 | 23 | 1 | 693 | 991
11544 | 2018-08-15 | 2019-05-01 | 2019-08-28 | 2019-08-28 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-12-16 | COMP | Rule 16 | 178 | 84 | 54 | 1 | 1 | 22 | 335
12197 | 2018-08-15 | 2019-05-28 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-15 | COMP | 2019-10-22 | COMP | 2019-09-25 | COMP | 2019-11-08 | COMP | Rule 16 | 196 | 48 | 10 | 48 | 0 | 14 | 312
13002 | 2018-08-15 | 2019-07-03 | 2019-09-12 | 2019-09-12 | COMP | 2020-03-10 | COMP | 2020-11-16 | COMP | 2022-06-14 | COMP | 2022-07-15 | COMP | Rule 15/16 | 222 | 50 | 122 | 177 | 397 | 22 | 985
13488 | 2018-08-15 | 2019-07-26 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-12 | COMP | 2019-09-13 | COMP | 2019-09-23 | COMP | 2019-10-14 | COMP | Rule 16 | 238 | 31 | 4 | 2 | 7 | 16 | 293
14473 | 2018-08-15 | 2019-09-12 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-01-10 | COMP | 2020-02-26 | COMP | Rule 16 | 271 | 35 | 9 | 1 | 40 | 32 | 383
3880 | 2018-08-16 | 2018-09-11 | 2018-10-17 | 2018-10-17 | COMP | 2018-10-24 | COMP | 2018-11-16 | COMP | 2018-11-08 | COMP | 2019-09-06 | COMP | Rule 16 | 18 | 27 | 6 | 17 | 0 | 202 | 266
6568 | 2018-08-16 | 2018-08-27 | 2018-09-11 | 2018-09-11 | COMP | 2018-10-24 | COMP | 2018-10-24 | COMP | 2019-04-21 | INPR | 2019-01-11 | COMP | Rule 16 | 8 | 11 | 32 | 1 |  |  | 101
6572 | 2018-08-16 | 2018-08-27 | 2018-11-10 | 2018-11-10 | COMP | 2018-11-27 | COMP | 2018-12-03 | COMP | 2019-06-07 | COMP | 2019-06-10 | COMP | Rule 16 | 8 | 54 | 9 | 5 | 130 | 2 | 204
6653 | 2018-08-16 | 2018-09-04 | 2018-12-17 | 2018-12-17 | COMP | 2019-01-08 | COMP | 2019-03-26 | COMP | 2020-04-14 | COMP | 2020-06-18 | COMP | Rule 16 | 13 | 72 | 15 | 54 | 266 | 47 | 462
6694 | 2018-08-16 | 2018-09-07 | 2018-12-12 | 2018-12-12 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-26 | COMP | Rule 16 | 16 | 66 | 62 | 1 | 1 | 33 | 174
6747 | 2018-08-16 | 2018-09-10 | 2018-11-10 | 2019-03-25 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-08-19 | COMP | 2019-09-09 | COMP | Rule 16 | 17 | 45 | 16 | 1 | 89 | 15 | 267
6882 | 2018-08-16 | 2018-09-15 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-18 | COMP | 2019-03-08 | COMP | 2018-12-19 | COMP | 2019-03-20 | COMP | Rule 16 | 21 | 58 | 7 | 55 | 0 | 9 | 147
7015 | 2018-08-16 | 2018-09-22 | 2018-12-18 | 2018-12-18 | COMP | 2019-01-03 | NOTN | 2019-01-03 | COMP | 2019-01-01 | COMP | 2019-02-07 | COMP | Other | 26 | 59 |  | 11 | 0 | 25 | 119
7080 | 2018-08-16 | 2018-09-25 | 2019-02-06 | 2019-02-06 | COMP | 2019-04-15 | COMP | 2019-04-19 | COMP | 2019-04-19 | COMP | 2019-05-31 | COMP | Rule 16 | 28 | 91 | 48 | 5 | 1 | 30 | 198
7336 | 2018-08-16 | 2018-10-08 | 2019-01-22 | 2019-01-22 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2020-11-02 | COMP | 2020-11-13 | COMP | Rule 16 | 37 | 71 | 155 | 1 | 298 | 9 | 566
7475 | 2018-08-16 | 2018-10-16 | 2019-06-12 | 2019-06-12 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-28 | COMP | 2019-10-05 | COMP | Rule 15/16 | 43 | 164 | 42 | 1 | 14 | 27 | 286
7503 | 2018-08-16 | 2018-10-17 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-09 | NOTN | 2019-02-01 | COMP | 2019-01-09 | COMP | 2019-02-27 | COMP | Other | 44 | 43 |  | 30 | 0 | 18 | 132
7602 | 2018-08-16 | 2018-10-23 | 2019-01-07 | 2019-01-07 | COMP | 2019-04-08 | COMP | 2019-08-08 | COMP | 2019-08-14 | COMP | 2019-10-22 | COMP | Rule 16 | 48 | 50 | 64 | 87 | 5 | 49 | 298
7680 | 2018-08-16 | 2018-10-25 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2018-12-06 | COMP | 2019-02-07 | COMP | Rule 16 | 50 | 19 | 8 | 1 | 3 | 43 | 119
7684 | 2018-08-16 | 2018-10-25 | 2019-02-20 | 2019-02-20 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-12-31 | COMP | 2020-01-14 | COMP | Rule 16 | 50 | 78 | 42 | 1 | 177 | 10 | 353
7838 | 2018-08-16 | 2018-11-02 | 2019-05-18 | 2019-05-18 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2020-07-01 | COMP | 2020-08-21 | COMP | Rule 16 | 56 | 134 | 56 | 1 | 227 | 38 | 508
7877 | 2018-08-16 | 2018-11-03 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-15 | COMP | 2019-02-08 | COMP | 2019-03-22 | COMP | 2019-04-10 | COMP | Rule 16 | 56 | 44 | 4 | 18 | 30 | 14 | 162
8021 | 2018-08-16 | 2018-11-09 | 2019-03-21 | 2019-03-21 | COMP | 2019-03-25 | COMP | 2019-04-04 | COMP | 2019-04-05 | COMP | 2019-06-05 | COMP | Rule 16 | 61 | 88 | 3 | 9 | 2 | 43 | 201
8203 | 2018-08-16 | 2018-11-17 | 2018-12-07 | 2018-12-07 | COMP | 2018-12-18 | COMP | 2019-01-09 | COMP | 2018-12-18 | COMP | 2019-01-23 | COMP | Rule 16 | 65 | 13 | 8 | 15 | 0 | 10 | 108
8408 | 2018-08-16 | 2018-11-29 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-07-29 | COMP | 2019-08-07 | COMP | Rule 16 | 72 | 121 | 10 | 1 | 38 | 8 | 245
8425 | 2018-08-16 | 2018-12-01 | 2019-03-01 | 2019-04-22 | COMP | 2019-04-23 | NOTN | 2019-04-23 | COMP | 2019-04-10 | COMP | 2019-06-03 | COMP | Other | 73 | 61 |  | 2 | 0 | 29 | 199
8815 | 2018-08-16 | 2018-12-31 | 2019-04-22 | 2019-04-22 | COMP | 2019-05-24 | COMP | 2019-10-07 | COMP | 2019-10-28 | COMP | 2020-01-21 | COMP | Rule 15/16 | 93 | 78 | 25 | 94 | 16 | 56 | 357
9132 | 2018-08-16 | 2019-01-17 | 2019-03-26 | 2019-05-09 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-08-13 | COMP | 2019-08-14 | COMP | Rule 16 | 105 | 47 | 62 | 1 | 6 | 2 | 250
9258 | 2018-08-16 | 2019-01-25 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-04 | COMP | 2019-04-24 | COMP | 2019-04-22 | COMP | 2019-05-03 | COMP | Rule 16 | 110 | 20 | 7 | 38 | 0 | 8 | 179
9302 | 2018-08-16 | 2019-01-28 | 2019-02-20 | 2019-02-26 | COMP | 2019-04-01 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-11-06 | COMP | Rule 16 | 111 | 17 | 25 | 135 | 1 | 21 | 309
9813 | 2018-08-16 | 2019-02-19 | 2019-03-12 | 2019-03-12 | COMP | 2019-04-02 | COMP | 2019-04-02 | NOTN | 2019-05-02 | COMP | 2019-05-10 | COMP | Rule 16 | 126 | 16 | 16 |  |  |  | 184
10116 | 2018-08-16 | 2019-03-04 | 2019-08-27 | 2019-09-23 | COMP | 2020-01-22 | COMP | 2020-11-03 | COMP | 2020-11-05 | COMP | 2021-01-11 | COMP | Rule 15/16 | 135 | 125 | 82 | 202 | 3 | 43 | 603
10212 | 2018-08-16 | 2019-03-06 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-05 | COMP | 2019-04-25 | COMP | 2019-07-21 | INPR | 2019-04-22 | COMP | Rule 16 | 137 | 13 | 11 | 15 |  |  | 170
10234 | 2018-08-16 | 2019-03-06 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-05 | COMP | 2019-04-25 | COMP | 2019-07-21 | INPR | 2019-04-22 | COMP | Rule 16 | 137 | 13 | 11 | 15 |  |  | 170
10356 | 2018-08-16 | 2019-03-12 | 2019-09-04 | 2019-09-04 | COMP | 2019-10-08 | NOTN | 2019-11-06 | COMP | 2019-12-18 | COMP | 2020-06-10 | COMP | Other | 141 | 124 |  | 46 | 28 | 121 | 456
10553 | 2018-08-16 | 2019-03-20 | 2019-03-29 | 2019-03-29 | COMP | 2019-06-24 | COMP | 2019-12-03 | COMP | 2020-06-10 | COMP | 2020-07-15 | COMP | Rule 16 | 147 | 8 | 61 | 112 | 132 | 26 | 481
14091 | 2018-08-16 | 2019-08-26 | 2019-09-19 | 2019-09-19 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2019-09-14 | COMP | 2020-01-29 | COMP | Rule 15/16 | 258 | 18 | 56 | 1 | 0 | 34 | 363
3869 | 2018-08-17 | 2018-08-29 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-22 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-04-25 | COMP | Rule 16 | 9 | 122 | 19 | 2 | 1 | 24 | 172
3905 | 2018-08-17 | 2018-09-27 | 2018-10-16 | 2018-10-16 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2018-12-04 | COMP | 2019-01-08 | COMP | Rule 16 | 29 | 14 | 56 | 1 | 0 | 1 | 97
6589 | 2018-08-17 | 2018-08-31 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-09 | COMP | 2018-12-21 | COMP | 2019-02-06 | COMP | 2019-03-14 | COMP | Rule 16 | 11 | 42 | 9 | 28 | 31 | 26 | 142
6721 | 2018-08-17 | 2018-09-10 | 2018-10-30 | 2018-10-30 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2019-10-18 | COMP | 2019-11-02 | COMP | Rule 16 | 16 | 37 | 36 | 1 | 209 | 11 | 305
6774 | 2018-08-17 | 2018-09-11 | 2019-01-16 | 2019-05-02 | COMP | 2019-09-10 | COMP | 2019-11-15 | COMP | 2019-11-15 | COMP | 2020-01-16 | COMP | Rule 15/16 | 17 | 87 | 91 | 48 | 1 | 41 | 354
7166 | 2018-08-17 | 2018-10-01 | 2018-11-28 | 2018-11-28 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2018-12-13 | COMP | 2019-01-08 | COMP | Rule 16 | 31 | 40 | 2 | 1 | 11 | 17 | 97
7526 | 2018-08-17 | 2018-10-19 | 2018-11-30 | 2018-11-30 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2019-01-09 | COMP | 2019-03-22 | COMP | Rule 16 | 45 | 28 | 4 | 1 | 24 | 51 | 148
7528 | 2018-08-17 | 2018-10-19 | 2018-11-30 | 2018-11-30 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-01-09 | COMP | 2019-04-04 | COMP | Rule 16 | 45 | 28 | 12 | 1 | 16 | 60 | 157
7601 | 2018-08-17 | 2018-10-23 | 2019-10-10 | 2019-10-10 | COMP | 2019-11-21 | COMP | 2019-12-11 | COMP | 2023-04-30 | INPR | 2020-02-27 | COMP | Rule 16 | 47 | 243 | 30 | 13 |  |  | 382
7634 | 2018-08-17 | 2018-10-23 | 2019-01-01 | 2020-07-07 | COMP | 2020-08-14 | COMP | 2020-09-04 | COMP | 2020-09-08 | COMP | 2020-10-22 | COMP | Rule 16 | 47 | 46 | 29 | 16 | 2 | 33 | 550
7654 | 2018-08-17 | 2018-10-24 | 2019-01-18 | 2021-04-14 | COMP | 2021-04-30 | COMP | 2021-05-12 | COMP | 2021-05-10 | COMP | 2021-07-16 | COMP | Rule 15/16 | 48 | 58 | 13 | 9 | 0 | 46 | 732
7691 | 2018-08-17 | 2018-10-26 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-27 | COMP | 2019-07-22 | COMP | 2019-09-29 | COMP | 2019-11-18 | COMP | Rule 16 | 50 | 52 | 31 | 102 | 49 | 35 | 315
7981 | 2018-08-17 | 2018-11-07 | 2019-07-15 | 2019-07-15 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2019-11-21 | COMP | 2020-01-21 | COMP | Rule 16 | 58 | 170 | 103 | 1 | 0 | 28 | 356
8301 | 2018-08-17 | 2018-11-26 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-09-02 | INPR | 2019-05-01 | COMP | Rule 16 | 68 | 43 | 21 | 1 |  |  | 176
8401 | 2018-08-17 | 2018-11-29 | 2019-03-31 | 2019-03-31 | COMP | 2019-05-20 | COMP | 2019-08-02 | COMP | 2019-11-21 | COMP | 2019-12-23 | COMP | Rule 16 | 71 | 83 | 36 | 53 | 78 | 21 | 338
8647 | 2018-08-17 | 2018-12-14 | 2019-03-11 | 2019-03-11 | COMP | 2019-05-03 | COMP | 2019-05-03 | NOTN | 2019-05-07 | COMP | 2019-08-29 | COMP | Rule 16 | 82 | 58 | 40 |  |  |  | 260
9140 | 2018-08-17 | 2019-01-17 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-08 | NOTN | 2019-03-08 | COMP | 2019-03-13 | COMP | 2019-04-15 | COMP | Other | 104 | 27 |  | 9 | 4 | 24 | 164
10209 | 2018-08-17 | 2019-03-06 | 2019-03-22 | 2019-03-22 | COMP | 2019-08-13 | COMP | 2019-09-05 | INPR | 2019-10-02 | COMP | 2019-10-16 | COMP | Rule 16 | 136 | 13 | 101 |  |  |  | 293
10371 | 2018-08-17 | 2019-03-13 | 2019-08-27 | 2019-08-27 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2022-01-03 | COMP | 2022-02-11 | COMP | Rule 16 | 141 | 118 | 167 | 1 | 426 | 29 | 877
10642 | 2018-08-17 | 2019-03-23 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-11 | NOTN | 2019-09-28 | COMP | 2019-09-11 | NOTN | 2020-02-20 | COMP | Other | 148 | 107 |  | 26 |  |  | 377
11657 | 2018-08-17 | 2019-05-07 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-18 | COMP | 2019-09-18 | COMP | 2020-02-01 | COMP | 2020-03-03 | COMP | Rule 16 | 180 | 78 | 17 | 1 | 92 | 21 | 385
13746 | 2018-08-17 | 2019-08-07 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-26 | COMP | 2019-10-21 | COMP | 2019-10-08 | COMP | 2019-10-23 | COMP | Rule 15/16 | 244 | 28 | 9 | 18 | 0 | 3 | 298
13748 | 2018-08-17 | 2019-08-07 | 2020-02-01 | 2020-02-01 | COMP | 2020-07-09 | COMP | 2020-07-22 | COMP | 2020-07-10 | COMP | 2020-12-18 | COMP | Rule 16 | 244 | 121 | 112 | 10 | 0 | 104 | 588
28165 | 2018-08-17 | 2021-05-21 | 2021-07-29 | 2021-07-29 | COMP | 2021-10-04 | COMP | 2022-05-17 | COMP | 2022-06-23 | COMP | 2022-07-18 | COMP | Rule 16 | 694 | 48 | 47 | 157 | 26 | 17 | 984
6471 | 2018-08-18 | 2018-08-20 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-01 | NOTN | 2019-04-17 | COMP | 2019-04-23 | COMP | 2019-05-15 | COMP | Other | 1 | 153 |  | 13 | 5 | 17 | 185
7464 | 2018-08-18 | 2018-10-15 | 2019-01-03 | 2019-01-03 | COMP | 2019-01-15 | COMP | 2019-01-16 | COMP | 2019-01-30 | COMP | 2019-02-11 | COMP | Rule 16 | 40 | 54 | 9 | 2 | 10 | 9 | 119
7192 | 2018-08-19 | 2018-10-01 | 2018-12-19 | 2019-01-11 | COMP | 2019-02-08 | COMP | 2019-06-04 | COMP | 2019-05-28 | COMP | 2019-08-28 | COMP | Rule 16 | 30 | 55 | 20 | 81 | 0 | 61 | 258
8090 | 2018-08-19 | 2018-11-16 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-05-06 | COMP | Rule 16 | 63 | 70 | 3 | 1 | 1 | 45 | 178
9084 | 2018-08-19 | 2019-01-16 | 2019-03-14 | 2019-04-04 | COMP | 2019-05-08 | COMP | 2019-07-10 | COMP | 2020-02-25 | COMP | 2020-05-28 | COMP | Rule 15/16 | 102 | 40 | 25 | 44 | 157 | 67 | 445
3916 | 2018-08-20 | 2018-10-03 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-20 | COMP | 2019-01-03 | COMP | 2019-02-06 | COMP | 2019-05-14 | COMP | Rule 16 | 32 | 28 | 26 | 9 | 24 | 69 | 184
3918 | 2018-08-20 | 2018-10-08 | 2018-10-29 | 2018-10-29 | COMP | 2018-11-14 | COMP | 2018-12-20 | COMP | 2019-02-08 | COMP | 2019-03-05 | COMP | Rule 16 | 35 | 16 | 12 | 25 | 34 | 17 | 134
3977 | 2018-08-20 | 2018-11-04 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-05 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-07-17 | COMP | Rule 16 | 54 | 70 | 11 | 2 | 1 | 94 | 228
6685 | 2018-08-20 | 2018-09-06 | 2018-11-05 | 2018-11-05 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-01-28 | COMP | 2019-03-08 | COMP | Rule 16 | 13 | 43 | 24 | 1 | 32 | 29 | 137
6776 | 2018-08-20 | 2018-09-11 | 2018-11-16 | 2018-11-16 | COMP | 2018-12-06 | COMP | 2018-12-06 | COMP | 2018-12-18 | COMP | 2019-01-04 | COMP | Rule 16 | 16 | 48 | 13 | 1 | 9 | 12 | 94
6815 | 2018-08-20 | 2018-09-12 | 2018-12-07 | 2018-12-07 | COMP | 2018-12-28 | COMP | 2019-01-03 | COMP | 2020-06-29 | COMP | 2020-08-04 | COMP | Rule 16 | 17 | 60 | 15 | 4 | 375 | 27 | 493
6817 | 2018-08-20 | 2018-09-12 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-11 | NOTN | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-03-15 | COMP | Other | 17 | 82 |  | 12 | 1 | 34 | 142
6842 | 2018-08-20 | 2018-09-12 | 2019-01-12 | 2019-01-12 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | 2020-01-15 | COMP | 2020-02-28 | COMP | Rule 16 | 17 | 83 | 53 | 1 | 201 | 31 | 382
6885 | 2018-08-20 | 2018-09-15 | 2018-11-28 | 2018-12-19 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-23 | COMP | 2019-02-12 | COMP | Rule 16 | 19 | 50 | 2 | 1 | 22 | 15 | 120
6993 | 2018-08-20 | 2018-09-21 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-08-01 | COMP | 2019-08-25 | COMP | Rule 16 | 24 | 104 | 8 | 1 | 106 | 17 | 255
7050 | 2018-08-20 | 2018-09-24 | 2018-11-07 | 2018-11-07 | COMP | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-02-26 | COMP | 2019-04-23 | COMP | Rule 16 | 25 | 33 | 55 | 7 | 13 | 41 | 169
7066 | 2018-08-20 | 2018-09-25 | 2019-09-06 | 2019-09-06 | COMP | 2019-10-14 | COMP | 2019-12-05 | COMP | 2019-12-03 | COMP | 2019-12-12 | COMP | Rule 15/16 | 26 | 239 | 27 | 36 | 0 | 6 | 330
7159 | 2018-08-20 | 2018-09-30 | 2018-10-29 | 2018-10-29 | COMP | 2019-03-04 | COMP | 2019-05-13 | COMP | 2019-05-02 | COMP | 2019-05-24 | COMP | Rule 16 | 29 | 21 | 84 | 51 | 0 | 10 | 192
7365 | 2018-08-20 | 2018-10-09 | 2019-01-17 | 2019-03-25 | COMP | 2019-04-01 | COMP | 2019-04-04 | COMP | 2019-03-29 | COMP | 2019-04-26 | COMP | Rule 16 | 36 | 68 | 6 | 4 | 0 | 17 | 172
7379 | 2018-08-20 | 2018-10-10 | 2018-11-06 | 2018-11-06 | COMP | 2018-11-13 | COMP | 2018-11-13 | COMP | 2022-01-30 | INPR | 2020-06-04 | COMP | Rule 16 | 37 | 20 | 5 | 1 |  |  | 450
7468 | 2018-08-20 | 2018-10-16 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2023-04-30 | INPR | 2020-12-04 | COMP | Rule 16 | 41 | 25 | 20 | 1 |  |  | 577
7527 | 2018-08-20 | 2018-10-19 | 2018-11-09 | 2018-11-09 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-02-02 | COMP | 2019-03-11 | COMP | Rule 16 | 44 | 16 | 27 | 1 | 29 | 25 | 138
7572 | 2018-08-20 | 2018-10-20 | 2019-02-11 | 2019-02-11 | COMP | 2019-06-13 | COMP | 2019-12-28 | REQD | 2019-12-28 | REQD | 2019-07-31 | COMP | Rule 15/16 | 44 | 75 | 87 |  |  |  | 238
7607 | 2018-08-20 | 2018-10-22 | 2018-11-19 | 2018-11-19 | COMP | 2018-12-03 | COMP | 2019-01-15 | COMP | 2019-05-16 | COMP | 2019-07-05 | COMP | Rule 16 | 45 | 20 | 9 | 30 | 86 | 35 | 220
7609 | 2018-08-20 | 2018-10-22 | 2018-11-30 | 2018-11-30 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-03-18 | COMP | Rule 16 | 45 | 27 | 50 | 1 | 1 | 24 | 143
7667 | 2018-08-20 | 2018-10-25 | 2019-05-29 | 2019-05-29 | COMP | 2021-01-06 | COMP | 2021-01-11 | COMP | 2021-01-13 | COMP | 2021-02-20 | COMP | Rule 15/16 | 48 | 147 | 405 | 4 | 3 | 26 | 628
7826 | 2018-08-20 | 2018-11-01 | 2019-01-23 | 2019-07-29 | COMP | 2019-09-30 | COMP | 2019-10-10 | COMP | 2019-11-13 | COMP | 2019-12-20 | COMP | Rule 16 | 53 | 54 | 45 | 9 | 24 | 26 | 336
7921 | 2018-08-20 | 2018-11-05 | 2019-12-30 | 2019-12-30 | COMP | 2021-02-23 | COMP | 2021-02-23 | COMP | 2021-03-02 | COMP | 2021-04-13 | COMP | Rule 15/16 | 55 | 287 | 290 | 1 | 6 | 31 | 665
8270 | 2018-08-20 | 2018-11-21 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-08-01 | COMP | 2019-09-12 | COMP | Rule 16 | 66 | 102 | 8 | 3 | 64 | 30 | 268
8348 | 2018-08-20 | 2018-11-27 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-30 | COMP | 2019-01-30 | NOTN | 2019-05-24 | COMP | 2019-05-31 | COMP | Rule 16 | 68 | 28 | 17 |  |  |  | 196
8365 | 2018-08-20 | 2018-11-28 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-06-20 | COMP | 2019-07-11 | COMP | Rule 16 | 69 | 101 | 12 | 1 | 31 | 15 | 224
8526 | 2018-08-20 | 2018-12-08 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-07 | NOTN | 2019-01-07 | COMP | 2019-02-26 | COMP | 2019-04-03 | COMP | Other | 76 | 8 |  | 12 | 35 | 27 | 155
8590 | 2018-08-20 | 2018-12-11 | 2019-03-07 | 2019-05-04 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-06-19 | COMP | 2020-07-15 | COMP | Rule 16 | 78 | 59 | 89 | 1 | 196 | 19 | 479
8654 | 2018-08-20 | 2018-12-13 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-06-11 | COMP | 2019-06-18 | COMP | Rule 16 | 80 | 52 | 8 | 1 | 66 | 6 | 208
8957 | 2018-08-20 | 2019-01-09 | 2019-01-25 | 2019-01-25 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-12-28 | INPR | 2019-07-31 | COMP | Rule 16 | 97 | 12 | 88 | 1 |  |  | 238
9383 | 2018-08-20 | 2019-01-31 | 2019-03-14 | 2019-03-14 | COMP | 2019-03-27 | COMP | 2019-05-11 | COMP | 2019-07-10 | COMP | 2019-08-26 | COMP | Rule 16 | 112 | 30 | 10 | 33 | 41 | 34 | 256
9808 | 2018-08-20 | 2019-02-19 | 2019-09-06 | 2019-09-19 | COMP | 2019-09-30 | COMP | 2019-10-04 | COMP | 2019-10-17 | COMP | 2019-11-08 | COMP | Rule 15/16 | 124 | 141 | 8 | 5 | 10 | 17 | 309
10104 | 2018-08-20 | 2019-03-02 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-12-03 | COMP | 2020-01-03 | COMP | Rule 16 | 132 | 53 | 11 | 1 | 129 | 22 | 344
10387 | 2018-08-20 | 2019-03-14 | 2019-05-24 | 2019-05-24 | COMP | 2019-08-12 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2020-01-08 | COMP | Rule 16 | 141 | 52 | 55 | 54 | 1 | 49 | 347
10480 | 2018-08-20 | 2019-03-18 | 2019-05-10 | 2019-05-10 | COMP | 2019-05-22 | COMP | 2020-02-04 | COMP | 2020-01-21 | COMP | 2020-03-04 | COMP | Rule 16 | 143 | 40 | 9 | 176 | 0 | 21 | 385
10698 | 2018-08-20 | 2019-03-27 | 2019-07-02 | 2019-07-02 | COMP | 2019-08-12 | COMP | 2019-08-29 | COMP | 2019-10-09 | COMP | 2020-01-15 | COMP | Rule 16 | 150 | 69 | 29 | 14 | 29 | 66 | 352
11031 | 2018-08-20 | 2019-04-09 | 2019-09-03 | 2020-03-25 | COMP | 2020-07-31 | COMP | 2020-10-07 | COMP |  | INPR | 2021-04-30 | COMP | Rule 16 | 159 | 103 | 92 | 48 |  |  | 678
11116 | 2018-08-20 | 2019-04-13 | 2019-05-26 | 2019-05-26 | COMP | 2019-06-18 | COMP | 2019-06-18 | COMP | 2019-07-18 | COMP | 2019-08-14 | COMP | Rule 16 | 162 | 30 | 16 | 1 | 22 | 20 | 248
11159 | 2018-08-20 | 2019-04-16 | 2019-06-27 | 2019-06-27 | COMP | 2019-10-10 | NOTN | 2020-02-13 | COMP | 2019-10-10 | COMP | 2020-06-17 | COMP | Other | 164 | 52 |  | 158 | 0 | 88 | 459
12997 | 2018-08-20 | 2019-07-03 | 2019-10-28 | 2019-10-28 | COMP | 2019-11-14 | COMP | 2019-12-11 | COMP | 2020-07-06 | COMP | 2020-07-31 | COMP | Rule 16 | 219 | 82 | 13 | 18 | 144 | 20 | 491
13792 | 2018-08-20 | 2019-08-10 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-17 | COMP | 2019-09-20 | COMP | 2023-12-03 | INPR | 2022-10-28 | COMP | Rule 16 | 245 | 16 | 11 | 4 |  |  | 1056
16901 | 2018-08-20 | 2020-01-23 | 2020-06-04 | 2021-09-14 | COMP |  | REQD | 2021-01-25 | COMP | 2021-07-30 | COMP | 2021-09-08 | COMP | Rule 16 | 357 | 94 |  |  | 132 | 28 | 768
3857 | 2018-08-21 | 2018-08-21 | 2018-08-31 | 2019-01-17 | COMP | 2019-04-17 | COMP | 2019-01-07 | COMP | 2019-05-13 | COMP | 2019-06-07 | COMP | Rule 16 | 1 | 9 | 63 |  | 89 | 19 | 200
4043 | 2018-08-21 | 2018-12-27 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-25 | COMP | 2019-08-29 | COMP | 2019-09-04 | COMP | 2019-09-20 | COMP | Rule 16 | 88 | 111 | 36 | 26 | 4 | 13 | 273
4111 | 2018-08-21 | 2019-02-19 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-10 | COMP | 2019-08-09 | COMP | 2019-12-28 | INPR | 2019-09-09 | COMP | Rule 16 | 123 | 40 | 20 | 64 |  |  | 264
4163 | 2018-08-21 | 2019-04-28 | 2020-03-24 | 2020-03-24 | COMP | 2020-05-18 | COMP | 2020-10-15 | COMP | 2021-02-08 | COMP | 2021-03-22 | COMP | Rule 16 | 171 | 227 | 40 | 107 | 77 | 30 | 648
6605 | 2018-08-21 | 2018-08-29 | 2018-10-31 | 2018-10-31 | COMP | 2018-10-31 | NOTN | 2018-10-31 | COMP | 2018-10-31 | COMP | 2019-01-22 | COMP | Other | 7 | 45 |  | 1 | 1 | 54 | 104
6613 | 2018-08-21 | 2018-08-30 | 2019-02-22 | 2019-02-22 | COMP | 2019-02-22 | NOTN | 2019-04-23 | COMP | 2019-04-08 | COMP | 2019-09-09 | COMP | Other | 8 | 119 |  | 43 | 0 | 97 | 264
6684 | 2018-08-21 | 2018-09-06 | 2018-11-05 | 2018-11-05 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-03-19 | COMP | Rule 16 | 12 | 43 | 57 | 1 | 1 | 34 | 143
6696 | 2018-08-21 | 2018-09-07 | 2018-12-07 | 2018-12-07 | COMP | 2019-03-22 | COMP | 2019-03-25 | COMP | 2020-08-08 | COMP | 2020-08-26 | COMP | Rule 16 | 13 | 63 | 72 | 2 | 349 | 13 | 508
6834 | 2018-08-21 | 2018-09-12 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-31 | COMP | 2019-03-07 | COMP | 2021-02-27 | INPR | 2019-12-19 | COMP | Rule 15/16 | 16 | 83 | 13 | 25 |  |  | 334
7035 | 2018-08-21 | 2018-09-24 | 2018-11-20 | 2019-01-31 | COMP | 2019-02-06 | COMP | 2019-03-20 | COMP | 2019-04-17 | COMP | 2019-06-07 | COMP | Rule 16 | 24 | 41 | 5 | 30 | 21 | 37 | 200
7087 | 2018-08-21 | 2018-09-26 | 2019-01-09 | 2019-01-25 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2020-01-19 | INPR | 2019-07-26 | COMP | Rule 15/16 | 26 | 71 | 88 | 1 |  |  | 234
7090 | 2018-08-21 | 2018-09-27 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-05-09 | COMP | 2019-06-13 | COMP | Rule 15/16 | 27 | 43 | 16 | 1 | 97 | 25 | 204
7091 | 2018-08-21 | 2018-09-27 | 2018-12-21 | 2019-03-06 | COMP | 2019-03-08 | COMP | 2019-03-29 | COMP | 2019-03-10 | COMP | 2019-04-04 | COMP | Rule 16 | 27 | 59 | 3 | 16 | 0 | 5 | 155
7136 | 2018-08-21 | 2018-09-28 | 2020-03-11 | 2020-03-11 | COMP | 2020-05-11 | COMP | 2020-11-17 | COMP | 2022-01-25 | COMP | 2022-04-04 | COMP | Rule 15/16 | 28 | 362 | 44 | 134 | 298 | 49 | 910
7201 | 2018-08-21 | 2018-10-02 | 2018-12-19 | 2018-12-19 | COMP | 2019-12-11 | NOTN | 2019-12-11 | COMP | 2020-01-28 | COMP | 2020-02-05 | COMP | Other | 30 | 54 |  | 246 | 32 | 7 | 365
7212 | 2018-08-21 | 2018-10-02 | 2019-01-05 | 2019-01-05 | COMP | 2019-01-25 | COMP | 2019-04-16 | COMP | 2019-04-17 | COMP | 2019-07-08 | COMP | Rule 16 | 30 | 64 | 14 | 57 | 2 | 57 | 220
7235 | 2018-08-21 | 2018-10-06 | 2019-01-28 | 2019-02-05 | COMP | 2019-02-26 | COMP | 2019-06-10 | COMP | 2021-03-16 | NOTN | 2019-08-08 | COMP | Rule 16 | 33 | 75 | 15 | 74 |  |  | 243
7301 | 2018-08-21 | 2018-10-06 | 2018-12-27 | 2019-02-04 | COMP | 2019-03-29 | COMP | 2019-06-04 | COMP | 2019-06-11 | COMP | 2019-09-24 | COMP | Rule 15/16 | 33 | 55 | 39 | 47 | 6 | 74 | 275
7355 | 2018-08-21 | 2018-10-09 | 2019-01-12 | 2019-01-12 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-04-11 | COMP | 2019-07-12 | COMP | Rule 16 | 35 | 64 | 43 | 1 | 20 | 65 | 224
7447 | 2018-08-21 | 2018-10-15 | 2018-12-06 | 2018-12-06 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-04-01 | COMP | 2019-05-08 | COMP | Rule 16 | 39 | 36 | 32 | 1 | 48 | 28 | 179
7473 | 2018-08-21 | 2018-10-15 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-24 | COMP | 2019-05-09 | COMP | 2019-06-04 | COMP | 2019-06-10 | COMP | Rule 16 | 39 | 110 | 22 | 12 | 18 | 5 | 201
7705 | 2018-08-21 | 2018-10-26 | 2019-01-10 | 2019-01-10 | COMP | 2019-03-06 | COMP | 2019-06-19 | COMP | 2019-12-04 | COMP | 2020-01-17 | COMP | Rule 16 | 48 | 50 | 38 | 75 | 116 | 31 | 353
7779 | 2018-08-21 | 2018-10-30 | 2018-12-06 | 2018-12-06 | COMP | 2019-03-08 | COMP | 2019-03-11 | COMP | 2019-11-22 | COMP | 2019-12-09 | COMP | Rule 16 | 50 | 25 | 63 | 2 | 181 | 10 | 326
7966 | 2018-08-21 | 2018-11-07 | 2019-03-08 | 2019-03-08 | COMP | 2020-07-01 | COMP | 2020-07-28 | COMP | 2021-10-05 | COMP | 2021-10-21 | COMP | Rule 16 | 56 | 81 | 333 | 20 | 300 | 13 | 798
7982 | 2018-08-21 | 2018-11-08 | 2019-06-27 | 2019-06-27 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2020-05-11 | COMP | 2020-06-10 | COMP | Rule 15/16 | 57 | 158 | 46 | 1 | 174 | 22 | 453
8085 | 2018-08-21 | 2018-11-15 | 2019-04-24 | 2019-05-09 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-09-05 | COMP | 2019-10-09 | COMP | Rule 16 | 61 | 109 | 6 | 1 | 78 | 25 | 286
8104 | 2018-08-21 | 2018-11-15 | 2019-03-12 | 2021-09-14 | COMP | 2021-10-28 | COMP | 2022-10-17 | COMP | 2022-11-02 | COMP | 2022-12-16 | COMP | Rule 15/16 | 61 | 78 | 33 | 244 | 13 | 30 | 1087
8159 | 2018-08-21 | 2018-11-16 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-06-13 | COMP | 2019-07-30 | COMP | Rule 16 | 62 | 49 | 4 | 1 | 92 | 33 | 236
8236 | 2018-08-21 | 2018-11-20 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-12-04 | COMP | 2020-01-14 | COMP | Rule 16 | 64 | 42 | 9 | 1 | 211 | 28 | 350
8242 | 2018-08-21 | 2018-11-20 | 2019-05-06 | 2020-01-25 | COMP | 2020-02-12 | COMP | 2020-02-13 | COMP | 2020-03-07 | COMP | 2020-06-10 | COMP | Rule 16 | 64 | 114 | 13 | 2 | 16 | 67 | 453
8643 | 2018-08-21 | 2018-12-13 | 2019-03-07 | 2019-03-07 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-10-21 | INPR | 2019-06-04 | COMP | Rule 15/16 | 79 | 57 | 28 | 1 |  |  | 197
8718 | 2018-08-21 | 2018-12-19 | 2019-01-16 | 2019-01-16 | COMP | 2019-01-30 | COMP | 2019-02-08 | COMP | 2019-02-01 | COMP | 2019-02-12 | COMP | Rule 16 | 83 | 19 | 10 | 8 | 0 | 3 | 119
8793 | 2018-08-21 | 2018-12-27 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-29 | COMP | 2019-05-09 | COMP | 2019-05-18 | COMP | 2019-07-05 | COMP | Rule 16 | 88 | 79 | 7 | 9 | 7 | 33 | 219
8952 | 2018-08-21 | 2019-01-09 | 2019-06-07 | 2019-06-07 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-06-25 | COMP | 2019-07-24 | COMP | Rule 16 | 96 | 105 | 11 | 1 | 3 | 21 | 232
9403 | 2018-08-21 | 2019-02-02 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-06 | COMP | 2020-12-04 | COMP | 2020-12-15 | COMP | 2021-01-03 | COMP | Rule 15/16 | 112 | 39 | 27 | 400 | 8 | 12 | 594
9495 | 2018-08-21 | 2019-02-06 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-12-29 | INPR | 2019-08-20 | COMP | Rule 16 | 115 | 77 | 11 | 1 |  |  | 251
9830 | 2018-08-21 | 2019-02-20 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-28 | COMP | 2019-05-17 | COMP | 2019-08-05 | COMP | 2019-07-17 | COMP | Rule 15/16 | 124 | 53 | 17 |  | 55 |  | 227
10709 | 2018-08-21 | 2019-03-27 | 2019-07-19 | 2019-07-19 | COMP | 2019-08-20 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-06-10 | COMP | Rule 16 | 149 | 81 | 23 | 134 | 1 | 70 | 453
11079 | 2018-08-21 | 2019-04-11 | 2019-06-25 | 2019-06-25 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-11-04 | COMP | Rule 16 | 160 | 53 | 10 | 1 | 1 | 84 | 304
13913 | 2018-08-21 | 2019-08-16 | 2019-11-06 | 2019-11-06 | COMP | 2020-02-03 | COMP | 2020-02-05 | COMP | 2020-03-13 | COMP | 2020-04-17 | COMP | Rule 16 | 249 | 58 | 58 | 3 | 27 | 26 | 416
14148 | 2018-08-21 | 2019-08-27 | 2019-12-05 | 2021-01-13 | COMP | 2021-01-22 | COMP | 2021-01-22 | COMP | 2021-02-09 | COMP | 2021-02-20 | COMP | Rule 15/16 | 256 | 69 | 7 | 1 | 13 | 8 | 627
15066 | 2018-08-21 | 2019-10-10 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-10 | COMP | 2020-02-26 | COMP | 2020-02-11 | COMP | 2020-06-08 | COMP | Rule 16 | 287 | 76 | 6 | 12 | 0 | 73 | 451
16026 | 2018-08-21 | 2019-12-05 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-25 | COMP | 2020-04-13 | COMP | 2020-06-23 | COMP | 2020-06-24 | COMP | Rule 16 | 324 | 64 | 13 | 14 | 51 | 2 | 463
16336 | 2018-08-21 | 2019-12-20 | 2020-08-16 | 2020-08-16 | COMP | 2020-12-21 | COMP | 2021-06-21 | COMP |  | INPR | 2021-08-27 | COMP | Rule 16 | 335 | 166 | 87 | 126 |  |  | 760
3900 | 2018-08-22 | 2018-09-26 | 2019-01-18 | 2019-01-18 | COMP | 2019-01-28 | COMP | 2019-04-04 | COMP | 2019-03-20 | COMP | 2019-05-04 | COMP | Rule 16 | 25 | 78 | 6 | 48 | 0 | 22 | 175
3987 | 2018-08-22 | 2018-11-08 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-18 | COMP | 2019-09-19 | COMP | 2020-02-29 | INPR | 2019-11-13 | COMP | Rule 16 | 56 | 195 | 21 | 2 |  |  | 309
6507 | 2018-08-22 | 2018-08-22 | 2019-03-20 | 2019-03-20 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2022-01-30 | INPR | 2020-09-02 | COMP | Rule 16 | 1 | 143 | 114 | 1 |  |  | 512
6612 | 2018-08-22 | 2018-08-30 | 2018-10-05 | 2018-10-05 | COMP | 2019-03-06 | COMP | 2019-04-22 | COMP | 2019-02-27 | COMP | 2019-04-22 | COMP | Rule 16 | 7 | 26 | 102 | 34 | 0 | 1 | 166
6678 | 2018-08-22 | 2018-09-06 | 2019-02-21 | 2019-06-19 | COMP | 2019-07-22 | COMP | 2019-09-11 | COMP | 2019-10-05 | COMP | 2019-12-12 | COMP | Rule 15/16 | 11 | 114 | 23 | 37 | 18 | 46 | 328
6813 | 2018-08-22 | 2018-09-12 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-28 | COMP | 2018-12-28 | COMP | 2019-01-02 | COMP | 2019-01-26 | COMP | Rule 16 | 15 | 61 | 14 | 1 | 3 | 17 | 106
6830 | 2018-08-22 | 2018-09-13 | 2019-01-05 | 2019-01-05 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-04-05 | COMP | 2019-07-09 | COMP | Rule 16 | 16 | 77 | 67 | 1 | 0 | 62 | 220
7025 | 2018-08-22 | 2018-09-24 | 2019-02-21 | 2019-02-21 | COMP | 2019-02-22 | NOTN | 2020-06-04 | COMP | 2020-06-15 | COMP | 2020-07-31 | COMP | Other | 23 | 102 |  | 325 | 8 | 35 | 489
7102 | 2018-08-22 | 2018-09-27 | 2018-10-05 | 2018-10-17 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2020-01-15 | COMP | 2020-02-07 | COMP | Rule 16 | 26 | 7 | 63 | 1 | 249 | 17 | 366
7617 | 2018-08-22 | 2018-10-23 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-25 | COMP | 2019-03-28 | COMP | Rule 16 | 44 | 32 | 9 | 1 | 24 | 44 | 149
7697 | 2018-08-22 | 2018-10-25 | 2019-01-16 | 2020-10-21 | COMP | 2020-12-14 | COMP | 2021-02-02 | COMP | 2021-02-24 | COMP | 2021-02-26 | COMP | Rule 16 | 46 | 55 | 36 | 34 | 16 | 3 | 631
7720 | 2018-08-22 | 2018-10-26 | 2019-01-28 | 2019-03-15 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-05-03 | COMP | Rule 16 | 47 | 61 | 18 | 1 | 1 | 19 | 175
7753 | 2018-08-22 | 2018-10-29 | 2018-12-17 | 2018-12-17 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2018-12-19 | COMP | 2019-03-12 | COMP | Rule 16 | 48 | 33 | 2 | 1 | 2 | 56 | 137
8062 | 2018-08-22 | 2018-11-14 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-03-25 | COMP | Rule 16 | 59 | 67 | 13 | 1 | 1 | 10 | 146
8110 | 2018-08-22 | 2018-11-15 | 2019-03-13 | 2019-03-13 | COMP | 2019-02-16 | NOTN | 2019-03-13 | NOTN | 2019-03-16 | COMP | 2019-04-23 | COMP | Other | 60 | 79 |  |  |  |  | 167
8130 | 2018-08-22 | 2018-11-16 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-08-02 | COMP | 2019-09-10 | COMP | Rule 16 | 61 | 24 | 28 | 1 | 128 | 27 | 264
8206 | 2018-08-22 | 2018-11-19 | 2018-12-26 | 2018-12-26 | COMP | 2019-03-22 | COMP | 2019-03-28 | COMP | 2019-09-23 | COMP | 2019-09-24 | COMP | Rule 15/16 | 62 | 25 | 60 | 5 | 125 | 2 | 274
8439 | 2018-08-22 | 2018-12-03 | 2019-01-18 | 2019-01-18 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2021-04-07 | COMP | 2021-05-13 | COMP | Other | 70 | 33 | 77 | 1 | 482 | 27 | 685
8588 | 2018-08-22 | 2018-12-11 | 2019-02-11 | 2019-02-11 | COMP | 2019-02-22 | COMP | 2019-04-26 | COMP | 2019-09-22 | INPR | 2019-06-03 | COMP | Rule 16 | 76 | 42 | 9 | 46 |  |  | 195
8642 | 2018-08-22 | 2018-12-13 | 2019-01-16 | 2019-01-16 | COMP | 2019-03-01 | COMP | 2019-08-07 | COMP | 2020-01-19 | INPR | 2019-09-25 | COMP | Rule 16 | 78 | 23 | 31 | 112 |  |  | 275
8864 | 2018-08-22 | 2019-01-03 | 2019-03-19 | 2019-03-19 | COMP | 2019-03-27 | COMP | 2019-05-15 | COMP | 2019-05-01 | COMP | 2019-06-06 | COMP | Rule 16 | 91 | 52 | 7 | 36 | 0 | 16 | 198
9138 | 2018-08-22 | 2019-01-17 | 2020-01-21 | 2020-11-09 | COMP | 2021-03-17 | COMP | 2021-10-08 | COMP | 2021-08-31 | COMP | 2021-11-27 | COMP | Rule 15/16 | 101 | 253 | 86 | 145 | 0 | 33 | 820
9566 | 2018-08-22 | 2019-02-07 | 2019-08-28 | 2019-08-28 | COMP | 2019-10-02 | COMP | 2019-10-25 | COMP | 2019-10-13 | COMP | 2020-03-10 | COMP | Rule 16 | 115 | 142 | 25 | 18 | 0 | 91 | 387
10518 | 2018-08-22 | 2019-03-19 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2020-05-07 | COMP | 2020-06-03 | COMP | Rule 16 | 142 | 100 | 9 | 1 | 181 | 19 | 447
11128 | 2018-08-22 | 2019-04-15 | 2019-07-30 | 2021-09-10 | COMP | 2021-09-17 | COMP | 2023-02-15 | COMP |  | INPR | 2023-06-24 | COMP | Rule 16 | 161 | 75 | 6 | 354 |  |  | 1215
11208 | 2018-08-22 | 2019-04-17 | 2019-05-14 | 2019-05-22 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-10-28 | COMP | 2020-01-14 | COMP | Rule 16 | 163 | 20 | 48 | 1 | 64 | 52 | 349
11443 | 2018-08-22 | 2019-04-27 | 2019-07-09 | 2019-07-26 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2020-01-21 | COMP | 2020-03-30 | COMP | Rule 16 | 170 | 50 | 26 | 1 | 96 | 49 | 401
11546 | 2018-08-22 | 2019-05-02 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-19 | COMP | 2019-09-12 | COMP | 2019-11-20 | COMP | 2020-01-27 | COMP | Rule 16 | 174 | 60 | 17 | 18 | 49 | 44 | 357
11705 | 2018-08-22 | 2019-05-08 | 2021-03-14 | 2021-09-24 | COMP | 2021-12-28 | COMP | 2021-12-15 | INPR | 2022-02-08 | COMP | 2022-02-03 | COMP | Rule 16 | 178 | 464 | 65 |  |  |  | 868
11823 | 2018-08-22 | 2019-05-16 | 2019-07-02 | 2019-07-02 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2019-08-21 | COMP | 2019-09-10 | COMP | Rule 15/16 | 184 | 33 | 37 | 1 | 0 | 13 | 264
13008 | 2018-08-22 | 2019-07-05 | 2019-10-15 | 2019-10-15 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-10-25 | COMP | 2020-01-06 | COMP | Rule 16 | 218 | 72 | 3 | 1 | 7 | 47 | 343
6563 | 2018-08-23 | 2018-08-27 | 2019-02-19 | 2019-02-19 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-11-24 | INPR | 2019-07-16 | COMP | Rule 15/16 | 3 | 119 | 65 | 1 |  |  | 224
6657 | 2018-08-23 | 2018-09-04 | 2019-06-19 | 2019-11-20 | COMP | 2020-01-22 | COMP | 2020-04-01 | COMP | 2020-03-13 | COMP | 2020-04-08 | COMP | Rule 15/16 | 8 | 199 | 41 | 50 | 0 | 6 | 407
6892 | 2018-08-23 | 2018-09-15 | 2018-12-14 | 2018-12-14 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-01-03 | COMP | 2019-02-25 | COMP | Rule 15/16 | 16 | 62 | 8 | 1 | 6 | 36 | 125
7060 | 2018-08-23 | 2018-09-25 | 2019-01-24 | 2020-02-06 | COMP | 2020-02-24 | COMP | 2020-05-13 | COMP | 2020-03-08 | COMP | 2020-07-20 | COMP | Rule 16 | 23 | 82 | 12 | 58 | 0 | 48 | 479
7185 | 2018-08-23 | 2018-10-02 | 2019-01-12 | 2019-01-12 | COMP | 2019-02-05 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-02 | COMP | Rule 16 | 28 | 69 | 16 | 26 | 1 | 15 | 151
7236 | 2018-08-23 | 2018-10-06 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-20 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-09-20 | COMP | Rule 15/16 | 31 | 70 | 22 | 108 | 1 | 43 | 271
7237 | 2018-08-23 | 2018-10-06 | 2019-01-25 | 2019-02-13 | COMP | 2019-05-08 | COMP | 2019-07-23 | COMP | 2019-08-22 | COMP | 2019-09-20 | COMP | Rule 16 | 31 | 74 | 60 | 53 | 23 | 21 | 271
7296 | 2018-08-23 | 2018-10-06 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-20 | COMP | 2019-03-01 | COMP | 2019-02-22 | COMP | 2019-04-18 | COMP | Rule 16 | 31 | 79 | 13 | 8 | 0 | 35 | 163
7298 | 2018-08-23 | 2018-10-06 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-03-27 | COMP | 2019-04-17 | COMP | Rule 16 | 31 | 35 | 61 | 1 | 22 | 16 | 162
7353 | 2018-08-23 | 2018-10-09 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-28 | COMP | 2019-07-30 | COMP | 2019-07-22 | COMP | 2019-08-29 | COMP | Rule 16 | 33 | 28 | 7 | 169 | 0 | 23 | 256
7360 | 2018-08-23 | 2018-10-09 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-01 | COMP | 2019-06-06 | COMP | 2019-06-20 | COMP | 2019-07-13 | COMP | Rule 15/16 | 33 | 69 | 29 | 69 | 11 | 16 | 222
7506 | 2018-08-23 | 2018-10-17 | 2018-12-21 | 2019-01-05 | COMP | 2019-04-08 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-06-04 | COMP | Rule 15/16 | 39 | 45 | 64 | 30 | 1 | 12 | 195
7529 | 2018-08-23 | 2018-10-18 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-30 | COMP | 2018-11-30 | COMP | 2018-12-12 | COMP | 2019-03-11 | COMP | Rule 16 | 40 | 19 | 11 | 1 | 9 | 60 | 135
7674 | 2018-08-23 | 2018-10-24 | 2019-01-04 | 2019-01-04 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-07-21 | INPR | 2019-01-28 | COMP | Rule 16 | 44 | 48 | 3 | 1 |  |  | 106
7757 | 2018-08-23 | 2018-10-30 | 2019-03-06 | 2019-04-05 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP |  | INPR | 2019-07-24 | COMP | Rule 15/16 | 48 | 85 | 39 | 1 |  |  | 230
7835 | 2018-08-23 | 2018-11-01 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-02-26 | COMP | 2019-03-20 | COMP | Rule 16 | 50 | 56 | 19 | 1 | 4 | 17 | 142
7916 | 2018-08-23 | 2018-11-05 | 2018-12-31 | 2018-12-31 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-09-02 | INPR | 2019-05-07 | COMP | Rule 16 | 52 | 37 | 24 | 1 |  |  | 176
8087 | 2018-08-23 | 2018-11-16 | 2019-02-20 | 2019-02-20 | COMP | 2019-05-03 | COMP | 2019-05-03 | NOTN | 2019-05-06 | COMP | 2019-05-17 | COMP | Rule 15/16 | 60 | 63 | 53 |  |  |  | 184
8233 | 2018-08-23 | 2018-11-20 | 2019-07-04 | 2019-07-04 | COMP | 2019-08-08 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2019-11-14 | COMP | Rule 15/16 | 62 | 155 | 25 | 40 | 1 | 30 | 309
8277 | 2018-08-23 | 2018-11-21 | 2019-05-10 | 2019-05-10 | COMP | 2019-05-16 | COMP | 2019-08-08 | COMP | 2019-08-14 | COMP | 2019-09-14 | COMP | Rule 16 | 63 | 117 | 5 | 59 | 5 | 22 | 266
9334 | 2018-08-23 | 2019-01-31 | 2019-03-25 | 2019-03-25 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-09-21 | COMP | 2020-11-06 | COMP | Rule 15/16 | 109 | 37 | 198 | 1 | 182 | 35 | 557
9446 | 2018-08-23 | 2019-02-04 | 2019-06-17 | 2019-06-17 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2019-08-13 | COMP | 2019-12-16 | COMP | Rule 16 | 111 | 94 | 24 | 1 | 18 | 86 | 329
9457 | 2018-08-23 | 2019-02-05 | 2019-04-13 | 2019-04-18 | COMP | 2019-05-29 | COMP | 2019-08-13 | COMP | 2020-01-23 | COMP | 2020-02-13 | COMP | Rule 16 | 112 | 48 | 29 | 54 | 111 | 16 | 369
9471 | 2018-08-23 | 2019-02-05 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-11 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-05-02 | COMP | Rule 15/16 | 112 | 7 | 18 | 16 | 1 | 24 | 173
9494 | 2018-08-23 | 2019-02-06 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-12-03 | COMP | 2020-01-14 | COMP | Rule 16 | 113 | 50 | 25 | 1 | 135 | 29 | 348
9706 | 2018-08-23 | 2019-02-12 | 2019-08-18 | 2020-05-07 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2020-09-24 | COMP | 2020-12-08 | COMP | Rule 15/16 | 117 | 131 | 108 | 1 | 0 | 42 | 576
9912 | 2018-08-23 | 2019-02-22 | 2019-04-25 | 2019-04-25 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2020-01-19 | INPR | 2019-09-27 | COMP | Rule 16 | 124 | 45 | 31 | 1 |  |  | 276
9928 | 2018-08-23 | 2019-02-22 | 2019-07-23 | 2019-07-23 | COMP | 2019-09-30 | COMP | 2020-07-01 | COMP | 2020-07-15 | COMP | 2020-07-24 | COMP | Rule 16 | 124 | 106 | 49 | 190 | 11 | 8 | 483
11586 | 2018-08-23 | 2019-05-03 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-12-20 | COMP | 2020-02-21 | COMP | Rule 16 | 174 | 79 | 16 | 1 | 67 | 42 | 374
12389 | 2018-08-23 | 2019-06-04 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2020-08-11 | COMP | 2020-10-09 | COMP | Rule 16 | 195 | 85 | 11 | 1 | 207 | 43 | 537
14222 | 2018-08-23 | 2019-08-29 | 2019-12-10 | 2019-12-10 | COMP | 2020-04-20 | COMP | 2020-08-27 | COMP | 2020-07-13 | COMP | 2020-10-19 | COMP | Rule 16 | 256 | 70 | 91 | 93 | 0 | 37 | 543
6552 | 2018-08-24 | 2018-08-28 | 2019-04-03 | 2019-08-28 | COMP | 2020-07-22 | COMP | 2023-05-02 | COMP | 2023-07-10 | COMP | 2023-06-26 | COMP | Rule 15/16 | 3 | 149 | 227 | 698 | 47 |  | 1214
6820 | 2018-08-24 | 2018-09-12 | 2018-10-31 | 2018-10-31 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2019-12-19 | COMP | 2020-02-05 | COMP | Rule 15/16 | 13 | 36 | 283 | 1 | 2 | 32 | 362
6833 | 2018-08-24 | 2018-09-12 | 2018-09-27 | 2018-09-27 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-01-03 | COMP | 2019-03-18 | COMP | Rule 16 | 13 | 12 | 56 | 1 | 11 | 51 | 139
6962 | 2018-08-24 | 2018-09-19 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2018-12-15 | COMP | 2019-02-23 | COMP | Rule 16 | 18 | 53 | 13 | 1 | 0 | 42 | 123
7002 | 2018-08-24 | 2018-09-22 | 2019-01-01 | 2019-01-01 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-07-24 | COMP | 2019-09-30 | COMP | Rule 16 | 20 | 67 | 134 | 1 | 9 | 48 | 276
7180 | 2018-08-24 | 2018-10-01 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-28 | COMP | 2019-06-03 | COMP | 2020-07-17 | COMP | 2020-09-03 | COMP | Rule 16 | 26 | 119 | 46 | 5 | 285 | 35 | 511
7202 | 2018-08-24 | 2018-10-02 | 2018-12-11 | 2018-12-11 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2020-01-21 | COMP | 2020-02-22 | COMP | Rule 16 | 27 | 48 | 162 | 1 | 117 | 23 | 373
7272 | 2018-08-24 | 2018-10-04 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-08-26 | COMP | 2019-11-12 | COMP | Rule 16 | 29 | 97 | 22 | 1 | 107 | 55 | 306
7363 | 2018-08-24 | 2018-10-09 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-20 | COMP | 2019-02-21 | COMP | 2019-04-09 | COMP | 2019-05-08 | COMP | Rule 16 | 32 | 74 | 17 | 2 | 34 | 22 | 176
7437 | 2018-08-24 | 2018-10-12 | 2018-10-30 | 2018-10-30 | COMP | 2018-11-15 | COMP | 2018-11-27 | COMP | 2019-06-03 | COMP | 2019-07-23 | COMP | Rule 16 | 35 | 13 | 12 | 7 | 130 | 36 | 228
7459 | 2018-08-24 | 2018-10-15 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-15 | COMP | 2019-01-16 | COMP | 2019-02-11 | COMP | 2019-03-08 | COMP | Rule 16 | 36 | 58 | 5 | 2 | 18 | 19 | 133
7813 | 2018-08-24 | 2018-11-01 | 2018-12-26 | 2018-12-26 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-01-10 | COMP | 2019-02-06 | COMP | Rule 16 | 49 | 36 | 10 | 1 | 2 | 19 | 112
7851 | 2018-08-24 | 2018-11-02 | 2019-01-18 | 2019-02-13 | COMP | 2019-03-27 | COMP | 2019-06-10 | COMP | 2019-07-01 | COMP | 2019-08-09 | COMP | Rule 16 | 50 | 51 | 30 | 53 | 16 | 29 | 241
7898 | 2018-08-24 | 2018-11-05 | 2019-02-08 | 2019-02-08 | COMP | 2019-02-28 | COMP | 2019-02-28 | COMP | 2019-03-05 | COMP | 2019-04-08 | COMP | Rule 16 | 51 | 64 | 14 | 1 | 4 | 25 | 154
7988 | 2018-08-24 | 2018-11-08 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-26 | COMP | 2019-04-05 | COMP | 2019-06-20 | COMP | 2019-06-21 | COMP | Rule 16 | 54 | 6 | 5 | 91 | 54 | 2 | 207
7991 | 2018-08-24 | 2018-11-09 | 2019-02-09 | 2019-02-09 | COMP | 2019-03-01 | COMP | 2019-03-06 | COMP | 2019-09-22 | INPR | 2019-05-31 | COMP | Rule 15/16 | 55 | 60 | 14 | 4 |  |  | 192
8336 | 2018-08-24 | 2018-11-28 | 2019-01-18 | 2019-01-18 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2020-08-29 | INPR | 2019-06-28 | COMP | Rule 15/16 | 65 | 36 | 58 | 1 |  |  | 212
8659 | 2018-08-24 | 2018-12-13 | 2019-02-11 | 2021-11-22 | COMP | 2022-05-19 | COMP | 2022-10-05 | COMP | 2022-07-27 | COMP | 2022-11-10 | COMP | Rule 16 | 76 | 40 | 125 | 96 | 0 | 27 | 1061
8801 | 2018-08-24 | 2018-12-28 | 2019-02-06 | 2019-04-16 | COMP | 2019-05-07 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-11-15 | COMP | Rule 16 | 86 | 27 | 16 | 95 | 1 | 41 | 309
9575 | 2018-08-24 | 2019-02-07 | 2019-05-28 | 2019-09-16 | COMP | 2019-09-16 | NOTN | 2019-10-28 | COMP | 2019-09-18 | COMP | 2019-12-17 | COMP | Other | 113 | 77 |  | 31 | 0 | 34 | 329
9699 | 2018-08-24 | 2019-02-11 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-29 | COMP | 2019-07-01 | COMP |  | INPR | 2019-07-29 | COMP | Rule 16 | 115 | 54 | 23 | 24 |  |  | 232
9740 | 2018-08-24 | 2019-02-13 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-24 | COMP | 2019-08-01 | COMP | 2019-06-25 | COMP | 2019-10-02 | COMP | Rule 16 | 117 | 80 | 13 | 28 | 0 | 44 | 278
9943 | 2018-08-24 | 2019-02-23 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-21 | COMP | 2020-01-07 | COMP | 2020-01-09 | COMP | 2020-01-31 | COMP | Rule 16 | 123 | 58 | 5 | 158 | 3 | 16 | 359
10646 | 2018-08-24 | 2019-03-25 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-22 | COMP | 2019-09-20 | COMP | 2020-01-02 | COMP | 2020-01-31 | COMP | Rule 16 | 144 | 86 | 22 | 21 | 70 | 21 | 359
11316 | 2018-08-24 | 2019-04-23 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-12 | COMP | 2019-10-04 | COMP | 2019-11-14 | COMP | 2019-12-24 | COMP | Rule 16 | 165 | 67 | 11 | 39 | 29 | 27 | 334
12262 | 2018-08-24 | 2019-05-30 | 2019-09-12 | 2019-09-12 | COMP | 2019-10-18 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2020-01-23 | COMP | Rule 16 | 191 | 74 | 27 | 37 | 1 | 28 | 353
14563 | 2018-08-24 | 2019-09-16 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-13 | COMP | 2020-04-24 | COMP | 2020-04-21 | COMP | 2020-06-17 | COMP | Rule 16 | 266 | 131 | 14 | 10 | 0 | 38 | 455
14929 | 2018-08-24 | 2019-10-04 | 2019-12-10 | 2020-05-05 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2020-07-17 | COMP | 2020-09-21 | COMP | Rule 15/16 | 280 | 45 | 44 | 1 | 10 | 46 | 522
7352 | 2018-08-25 | 2018-10-09 | 2018-11-01 | 2018-11-01 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2019-03-06 | COMP | 2019-04-23 | COMP | Rule 16 | 31 | 18 | 73 | 1 | 11 | 35 | 164
9344 | 2018-08-25 | 2019-01-30 | 2019-04-26 | 2019-04-26 | COMP | 2019-09-04 | COMP | 2019-10-16 | COMP | 2019-10-21 | COMP | 2019-12-20 | COMP | Rule 16 | 106 | 62 | 91 | 31 | 4 | 42 | 331
10613 | 2018-08-26 | 2019-03-22 | 2019-07-28 | 2019-07-28 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-03-02 | COMP | 2020-06-19 | COMP | Rule 16 | 142 | 89 | 144 | 1 | 5 | 79 | 456
4053 | 2018-08-27 | 2019-01-03 | 2019-02-21 | 2019-02-21 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2020-08-10 | COMP | 2020-08-26 | COMP | Rule 15/16 | 88 | 34 | 73 | 1 | 300 | 13 | 504
6818 | 2018-08-27 | 2018-09-12 | 2018-12-30 | 2018-12-30 | COMP | 2019-02-12 | COMP | 2019-03-13 | COMP | 2019-03-15 | COMP | 2019-05-03 | COMP | Rule 15/16 | 12 | 74 | 30 | 21 | 3 | 36 | 172
6841 | 2018-08-27 | 2018-09-12 | 2019-01-25 | 2019-01-25 | COMP | 2019-04-03 | COMP | 2019-04-24 | COMP | 2019-06-07 | COMP | 2019-06-18 | COMP | Rule 16 | 12 | 92 | 48 | 16 | 32 | 8 | 203
6855 | 2018-08-27 | 2018-09-13 | 2019-01-16 | 2019-01-16 | COMP | 2019-02-01 | COMP | 2019-02-04 | COMP | 2019-03-08 | COMP | 2019-03-28 | COMP | Rule 16 | 13 | 85 | 12 | 2 | 24 | 15 | 146
6881 | 2018-08-27 | 2018-09-14 | 2018-11-28 | 2018-11-28 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-03-29 | COMP | 2019-04-22 | COMP | Rule 16 | 14 | 51 | 32 | 1 | 53 | 17 | 163
6995 | 2018-08-27 | 2018-09-21 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-04-10 | COMP | 2019-07-26 | COMP | Rule 16 | 19 | 86 | 31 | 1 | 22 | 76 | 230
7012 | 2018-08-27 | 2018-09-22 | 2019-02-21 | 2019-02-21 | COMP | 2019-07-12 | NOTN | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-08-19 | COMP | Other | 19 | 102 |  | 100 | 1 | 27 | 246
7016 | 2018-08-27 | 2018-09-22 | 2019-01-14 | 2019-01-25 | COMP | 2019-02-12 | COMP | 2019-04-08 | COMP | 2019-05-31 | COMP | 2019-06-28 | COMP | Rule 16 | 19 | 76 | 13 | 39 | 39 | 21 | 211
7021 | 2018-08-27 | 2018-09-23 | 2019-01-28 | 2019-02-02 | COMP | 2019-04-12 | COMP | 2019-04-12 | COMP | 2019-06-05 | COMP | 2019-06-27 | COMP | Rule 16 | 19 | 85 | 49 | 1 | 38 | 17 | 210
7068 | 2018-08-27 | 2018-09-25 | 2018-10-24 | 2018-10-24 | COMP | 2018-11-28 | COMP | 2018-11-28 | COMP | 2019-06-18 | COMP | 2019-08-07 | COMP | Rule 16 | 21 | 22 | 23 | 1 | 140 | 36 | 238
7078 | 2018-08-27 | 2018-09-25 | 2019-01-23 | 2019-01-23 | COMP | 2019-04-16 | COMP | 2019-04-23 | COMP | 2019-12-28 | INPR | 2019-09-03 | COMP | Rule 16 | 21 | 81 | 59 | 6 |  |  | 256
7130 | 2018-08-27 | 2018-09-28 | 2018-12-28 | 2019-01-30 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2020-01-19 | INPR | 2019-10-09 | COMP | Rule 16 | 24 | 62 | 87 | 1 |  |  | 282
7182 | 2018-08-27 | 2018-10-01 | 2018-12-12 | 2018-12-18 | COMP | 2019-01-16 | COMP | 2019-04-10 | COMP | 2023-12-09 | INPR | 2019-09-09 | COMP | Rule 16 | 25 | 50 | 20 | 59 |  |  | 260
7278 | 2018-08-27 | 2018-10-05 | 2019-01-19 | 2019-01-19 | COMP | 2019-01-22 | NOTN | 2019-01-22 | COMP | 2019-12-04 | INPR | 2019-05-08 | COMP | Other | 29 | 71 |  | 1 |  |  | 175
7354 | 2018-08-27 | 2018-10-09 | 2019-02-20 | 2019-02-20 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-09-01 | INPR | 2019-05-10 | COMP | Rule 16 | 31 | 90 | 42 | 1 |  |  | 177
7362 | 2018-08-27 | 2018-10-09 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-11 | COMP | 2019-03-19 | COMP | 2019-08-16 | COMP | 2019-04-11 | COMP | Other | 31 | 42 | 23 | 46 | 107 |  | 156
7462 | 2018-08-27 | 2018-10-15 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-05 | COMP | 2019-03-07 | COMP | 2020-04-26 | INPR | 2019-06-18 | COMP | Rule 16 | 35 | 88 | 8 | 3 |  |  | 203
7474 | 2018-08-27 | 2018-10-17 | 2018-12-10 | 2018-12-10 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-02-14 | COMP | 2019-02-25 | COMP | Rule 16 | 37 | 36 | 25 | 1 | 22 | 7 | 123
7625 | 2018-08-27 | 2018-10-23 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-29 | COMP | 2018-12-10 | COMP | 2019-01-16 | COMP | 2019-01-28 | COMP | Rule 16 | 41 | 18 | 8 | 8 | 26 | 8 | 104
7854 | 2018-08-27 | 2018-11-02 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-04-01 | COMP | 2019-05-07 | COMP | Rule 15/16 | 49 | 54 | 8 | 1 | 40 | 27 | 174
7907 | 2018-08-27 | 2018-11-05 | 2019-02-15 | 2019-03-14 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-07-21 | INPR | 2019-04-09 | COMP | Rule 16 | 50 | 69 | 8 | 1 |  |  | 154
8686 | 2018-08-27 | 2018-12-17 | 2019-01-28 | 2019-02-05 | COMP | 2019-02-13 | COMP | 2019-02-25 | COMP | 2019-06-24 | COMP | 2019-07-18 | COMP | Rule 16 | 77 | 28 | 7 | 8 | 85 | 18 | 224
8737 | 2018-08-27 | 2018-12-20 | 2019-04-25 | 2019-04-25 | COMP | 2019-07-16 | COMP | 2019-08-20 | COMP | 2019-09-03 | COMP | 2019-09-30 | COMP | Rule 16 | 80 | 87 | 57 | 26 | 10 | 20 | 275
8916 | 2018-08-27 | 2019-01-07 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-09-04 | COMP | 2019-10-07 | COMP | Rule 16 | 90 | 15 | 42 | 1 | 113 | 24 | 280
10466 | 2018-08-27 | 2019-03-18 | 2019-05-28 | 2019-05-28 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP |  |  | 2020-01-29 | COMP | Rule 16 | 138 | 51 | 132 | 1 |  |  | 356
10495 | 2018-08-27 | 2019-03-18 | 2019-05-02 | 2019-07-06 | COMP | 2019-07-15 | COMP | 2019-06-04 | COMP | 2019-08-05 | COMP | 2019-08-13 | COMP | Rule 16 | 138 | 34 | 6 |  | 44 | 7 | 242
11045 | 2018-08-27 | 2019-04-10 | 2019-07-26 | 2019-07-26 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2020-06-15 | COMP | 2020-07-31 | COMP | Rule 16 | 155 | 76 | 96 | 1 | 128 | 35 | 486
11540 | 2018-08-27 | 2019-05-01 | 2019-05-20 | 2019-05-20 | COMP | 2019-05-24 | COMP | 2019-05-24 | NOTN | 2019-05-30 | COMP | 2019-06-05 | COMP | Rule 16 | 170 | 14 | 5 |  |  |  | 194
11750 | 2018-08-27 | 2019-05-09 | 2019-08-28 | 2019-08-28 | COMP | 2019-12-02 | COMP | 2019-11-21 | COMP | 2020-04-14 | COMP | 2020-05-06 | COMP | Rule 16 | 176 | 78 | 65 |  | 98 | 17 | 425
25288 | 2018-08-27 | 2021-02-03 | 2021-02-11 | 2021-02-11 | COMP | 2021-02-16 | NOTN | 2021-02-17 | COMP | 2021-07-01 | COMP | 2021-07-28 | COMP | Other | 612 | 7 |  | 4 | 96 | 19 | 734
3902 | 2018-08-28 | 2018-09-27 | 2018-11-26 | 2018-11-26 | COMP | 2018-11-19 | NOTN | 2018-11-26 | COMP | 2019-04-20 | INPR | 2019-01-25 | COMP | Other | 22 | 40 |  | 1 |  |  | 102
6577 | 2018-08-28 | 2018-08-28 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-26 | COMP | 2019-01-25 | COMP | 2019-01-08 | COMP | 2019-03-21 | COMP | Rule 16 | 1 | 56 | 27 | 21 | 0 | 39 | 140
6853 | 2018-08-28 | 2018-09-13 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-18 | COMP | 2019-02-01 | COMP | 2019-02-04 | COMP | 2019-03-28 | COMP | Rule 16 | 12 | 57 | 10 | 31 | 2 | 38 | 145
6899 | 2018-08-28 | 2018-09-17 | 2018-12-17 | 2019-01-31 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2020-04-27 | COMP | 2020-06-05 | COMP | Rule 16 | 14 | 63 | 32 | 1 | 281 | 29 | 445
6998 | 2018-08-28 | 2018-09-21 | 2019-01-17 | 2019-01-17 | COMP | 2019-02-05 | COMP | 2019-02-05 | COMP | 2019-03-21 | COMP | 2019-05-07 | COMP | Rule 16 | 18 | 80 | 13 | 1 | 32 | 34 | 173
7004 | 2018-08-28 | 2018-09-22 | 2018-12-07 | 2018-12-07 | COMP | 2019-02-01 | COMP | 2019-02-11 | COMP | 2019-06-20 | COMP | 2019-07-19 | COMP | Rule 16 | 18 | 52 | 38 | 7 | 92 | 21 | 224
7073 | 2018-08-28 | 2018-09-25 | 2019-07-19 | 2019-07-19 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-10-14 | COMP | 2020-01-11 | COMP | Rule 15/16 | 20 | 205 | 19 | 1 | 43 | 60 | 343
7266 | 2018-08-28 | 2018-10-04 | 2018-11-29 | 2018-12-21 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-01-04 | COMP | 2019-02-22 | COMP | Rule 16 | 27 | 38 | 9 | 1 | 1 | 34 | 121
7294 | 2018-08-28 | 2018-10-06 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-26 | COMP | 2019-02-25 | COMP | 2019-02-11 | COMP | 2019-03-11 | COMP | Rule 16 | 28 | 43 | 12 | 41 | 0 | 11 | 132
7774 | 2018-08-28 | 2018-10-30 | 2019-01-19 | 2019-01-19 | COMP | 2019-01-24 | NOTN | 2019-04-10 | COMP | 2019-10-21 | INPR | 2019-06-19 | COMP | Other | 45 | 54 |  | 56 |  |  | 203
8000 | 2018-08-28 | 2018-11-09 | 2019-02-15 | 2020-07-20 | COMP | 2020-08-12 | COMP | 2021-06-02 | COMP | 2021-06-01 | COMP | 2021-07-06 | COMP | Rule 16 | 53 | 65 | 18 | 202 | 0 | 24 | 717
8005 | 2018-08-28 | 2018-11-13 | 2019-10-06 | 2019-11-07 | COMP | 2020-01-21 | COMP | 2020-03-06 | COMP | 2020-10-05 | COMP | 2020-10-21 | COMP | Rule 16 | 54 | 225 | 48 | 33 | 150 | 13 | 542
8023 | 2018-08-28 | 2018-11-09 | 2019-03-18 | 2019-03-18 | COMP | 2019-06-03 | COMP | 2020-09-08 | COMP | 2020-09-14 | COMP | 2020-09-30 | COMP | Rule 16 | 53 | 85 | 55 | 321 | 5 | 13 | 527
8029 | 2018-08-28 | 2018-11-10 | 2019-03-01 | 2019-03-01 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2021-02-01 | COMP | 2021-03-18 | COMP | Rule 16 | 53 | 73 | 48 | 1 | 437 | 33 | 641
8070 | 2018-08-28 | 2018-11-14 | 2019-01-05 | 2019-01-05 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-03-20 | COMP | 2019-04-15 | COMP | Rule 16 | 55 | 34 | 20 | 1 | 32 | 19 | 157
8096 | 2018-08-28 | 2018-11-15 | 2019-02-21 | 2019-02-21 | COMP | 2019-02-27 | COMP | 2019-03-25 | COMP | 2019-04-17 | COMP | 2019-05-02 | COMP | Rule 16 | 56 | 65 | 5 | 19 | 18 | 12 | 170
8115 | 2018-08-28 | 2018-11-15 | 2019-05-28 | 2019-05-28 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-10-02 | COMP | 2019-10-22 | COMP | Rule 16 | 56 | 132 | 67 | 1 | 24 | 15 | 290
8142 | 2018-08-28 | 2018-11-16 | 2019-01-08 | 2019-01-14 | COMP | 2019-02-05 | COMP | 2019-03-14 | COMP | 2019-03-01 | COMP | 2019-08-06 | COMP | Rule 16 | 57 | 34 | 16 | 27 | 0 | 102 | 236
8150 | 2018-08-28 | 2018-11-16 | 2019-03-04 | 2019-03-04 | COMP | 2019-06-03 | COMP | 2020-03-12 | COMP | 2020-10-12 | COMP | 2020-12-16 | COMP | Rule 15/16 | 57 | 71 | 65 | 195 | 151 | 45 | 579
8307 | 2018-08-28 | 2018-11-26 | 2019-01-14 | 2019-03-07 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2020-09-09 | COMP | 2020-10-02 | COMP | Rule 16 | 61 | 34 | 62 | 1 | 322 | 18 | 529
8518 | 2018-08-28 | 2018-12-06 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-18 | COMP | 2019-04-29 | COMP | 2020-01-19 | INPR | 2019-10-02 | COMP | Rule 16 | 69 | 74 | 19 | 8 |  |  | 276
8630 | 2018-08-28 | 2018-12-13 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-17 | COMP | 2019-06-06 | COMP | 2019-05-14 | COMP | 2019-06-28 | COMP | Rule 16 | 74 | 64 | 45 | 14 | 0 | 17 | 210
8917 | 2018-08-28 | 2019-01-07 | 2019-04-05 | 2019-04-05 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2020-09-14 | COMP | 2021-06-16 | COMP | Rule 16 | 89 | 63 | 23 | 1 | 343 | 190 | 704
8983 | 2018-08-28 | 2019-01-11 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-15 | COMP | 2019-04-23 | COMP | 2019-09-02 | INPR | 2019-05-17 | COMP | Rule 16 | 93 | 51 | 15 | 7 |  |  | 181
9224 | 2018-08-28 | 2019-01-23 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2021-04-22 | COMP | 2021-07-19 | COMP | Rule 16 | 100 | 80 | 20 | 1 | 469 | 61 | 726
9236 | 2018-08-28 | 2019-01-23 | 2019-03-25 | 2020-12-24 | COMP | 2021-03-10 | COMP | 2021-03-10 | COMP | 2021-08-03 | COMP | 2021-08-20 | COMP | Rule 15/16 | 100 | 43 | 51 | 1 | 103 | 14 | 750
9244 | 2018-08-28 | 2019-01-24 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-09 | COMP | 2020-10-14 | COMP | 2020-10-27 | COMP | 2020-11-16 | COMP | Rule 16 | 101 | 20 | 34 | 385 | 10 | 14 | 559
9426 | 2018-08-28 | 2019-02-04 | 2019-06-11 | 2019-06-11 | COMP | 2019-07-22 | COMP | 2019-09-16 | COMP | 2019-11-19 | COMP | 2019-12-15 | COMP | Rule 15/16 | 108 | 90 | 29 | 40 | 46 | 17 | 325
9641 | 2018-08-28 | 2019-02-09 | 2019-03-04 | 2019-03-04 | COMP | 2019-11-22 | COMP | 2020-08-20 | COMP | 2020-08-19 | COMP | 2020-08-26 | COMP | Rule 16 | 112 | 15 | 186 | 188 | 0 | 5 | 503
10014 | 2018-08-28 | 2019-02-27 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-05 | COMP | 2020-02-18 | COMP | 2020-09-14 | COMP | 2020-09-29 | COMP | Rule 16 | 124 | 80 | 33 | 134 | 148 | 12 | 526
10311 | 2018-08-28 | 2019-03-11 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-13 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-11-13 | COMP | Rule 16 | 132 | 106 | 5 | 40 | 1 | 26 | 305
10933 | 2018-08-28 | 2019-04-05 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2021-03-08 | COMP | 2021-03-23 | COMP | Rule 15/16 | 151 | 232 | 54 | 1 | 199 | 12 | 644
11166 | 2018-08-28 | 2019-04-16 | 2019-06-13 | 2020-02-26 | COMP | 2020-06-13 | NOTN | 2020-01-06 | COMP | 2020-11-04 | NOTN | 2021-03-25 | COMP | Other | 158 | 42 |  |  |  |  | 646
11244 | 2018-08-28 | 2019-04-18 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-29 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-05-30 | COMP | Rule 16 | 160 | 2 | 7 | 22 | 1 | 2 | 189
11617 | 2018-08-28 | 2019-05-06 | 2019-09-14 | 2019-09-14 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-12-10 | COMP | 2021-01-04 | COMP | Rule 16 | 172 | 92 | 213 | 1 | 100 | 16 | 590
12623 | 2018-08-28 | 2019-06-18 | 2019-09-01 | 2019-09-01 | COMP | 2019-09-11 | COMP | 2019-12-03 | COMP | 2020-02-03 | COMP | 2020-03-06 | COMP | Rule 15/16 | 202 | 53 | 7 | 57 | 42 | 24 | 381
4241 | 2018-08-29 | 2019-10-09 | 2020-02-04 | 2020-02-03 | COMP | 2020-07-07 | COMP | 2020-12-11 | INPR | 2023-12-02 | CANC | 2021-01-23 | COMP | Rule 15/16 | 280 | 79 | 110 |  |  |  | 602
6902 | 2018-08-29 | 2018-09-17 | 2018-10-17 | 2018-10-17 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-07-15 | COMP | 2019-08-27 | COMP | Rule 16 | 13 | 23 | 48 | 1 | 138 | 32 | 250
6972 | 2018-08-29 | 2018-09-21 | 2018-11-26 | 2018-12-12 | COMP | 2019-01-17 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-07-01 | COMP | Rule 16 | 17 | 44 | 25 | 94 | 1 | 22 | 210
6973 | 2018-08-29 | 2018-09-21 | 2019-01-17 | 2019-03-08 | COMP | 2019-03-28 | COMP | 2019-06-07 | COMP | 2019-06-05 | COMP | 2019-07-25 | COMP | Rule 16 | 17 | 80 | 15 | 51 | 0 | 34 | 227
6975 | 2018-08-29 | 2018-09-20 | 2019-05-12 | 2019-05-12 | COMP | 2019-08-05 | COMP | 2019-10-16 | COMP | 2019-11-20 | COMP | 2020-02-07 | COMP | Rule 15/16 | 16 | 160 | 59 | 52 | 25 | 53 | 361
7003 | 2018-08-29 | 2018-09-22 | 2019-01-05 | 2019-01-05 | COMP | 2019-02-15 | COMP | 2019-06-07 | COMP | 2019-04-19 | COMP | 2019-07-18 | COMP | Rule 16 | 17 | 70 | 29 | 79 | 0 | 29 | 222
7110 | 2018-08-29 | 2018-09-28 | 2018-11-20 | 2018-11-20 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-12-10 | COMP | 2020-05-13 | COMP | Rule 16 | 22 | 37 | 86 | 1 | 179 | 108 | 428
7213 | 2018-08-29 | 2018-10-02 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-03-27 | COMP | Rule 16 | 24 | 69 | 10 | 1 | 1 | 42 | 143
7285 | 2018-08-29 | 2018-10-05 | 2019-02-25 | 2019-02-25 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-12-16 | COMP | 2020-01-07 | COMP | Rule 15/16 | 27 | 95 | 32 | 1 | 174 | 15 | 339
7603 | 2018-08-29 | 2018-10-23 | 2019-02-09 | 2019-02-09 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-09-02 | INPR | 2019-04-22 | COMP | Rule 16 | 39 | 73 | 19 | 1 |  |  | 161
7639 | 2018-08-29 | 2018-10-23 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-21 | COMP | 2018-12-14 | COMP | 2019-07-03 | COMP | 2019-07-10 | COMP | Rule 16 | 39 | 18 | 4 | 16 | 139 | 5 | 216
7706 | 2018-08-29 | 2018-10-26 | 2019-02-27 | 2019-03-01 | COMP | 2019-03-11 | NOTN | 2019-03-11 | COMP | 2019-04-23 | COMP | 2019-05-15 | COMP | Other | 42 | 82 |  | 7 | 32 | 17 | 178
7737 | 2018-08-29 | 2018-10-29 | 2019-02-25 | 2019-02-28 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-12-28 | INPR | 2019-08-29 | COMP | Rule 16 | 43 | 79 | 62 | 1 |  |  | 252
7756 | 2018-08-29 | 2018-10-30 | 2019-01-11 | 2019-01-11 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-04-04 | COMP | 2019-05-17 | COMP | Rule 16 | 44 | 49 | 56 | 1 | 3 | 32 | 180
7795 | 2018-08-29 | 2018-10-31 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-01 | NOTN | 2019-02-01 | COMP | 2019-02-01 | COMP | 2020-02-11 | COMP | Other | 45 | 61 |  | 2 | 1 | 258 | 363
8033 | 2018-08-29 | 2018-11-12 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-25 | COMP | 2019-02-04 | COMP | 2019-02-17 | COMP | 2019-02-25 | COMP | Rule 16 | 52 | 28 | 22 | 7 | 10 | 5 | 121
8215 | 2018-08-29 | 2018-11-19 | 2019-02-04 | 2019-02-04 | COMP | 2019-02-12 | NOTN | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-05-14 | COMP | Rule 16 | 57 | 51 |  | 7 | 1 | 65 | 177
8406 | 2018-08-29 | 2018-11-29 | 2019-03-02 | 2019-03-02 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-04-26 | COMP | 2019-05-01 | COMP | Rule 16 | 63 | 63 | 6 | 1 | 35 | 4 | 168
8767 | 2018-08-29 | 2018-12-23 | 2019-07-18 | 2020-05-07 | COMP | 2020-06-03 | COMP | 2020-06-03 | INPR | 2020-07-14 | COMP | 2020-07-17 | COMP | Rule 15/16 | 79 | 143 | 19 |  |  |  | 474
8927 | 2018-08-29 | 2019-01-08 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-15 | COMP | 2019-04-18 | COMP | 2019-04-23 | COMP | 2019-06-18 | COMP | Rule 16 | 89 | 35 | 13 | 25 | 4 | 40 | 201
8974 | 2018-08-29 | 2019-01-10 | 2019-04-19 | 2019-05-14 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-07-10 | COMP | 2019-07-15 | COMP | Rule 16 | 91 | 70 | 10 | 1 | 31 | 4 | 219
9247 | 2018-08-29 | 2019-01-24 | 2019-06-17 | 2020-01-29 | COMP | 2020-03-04 | COMP | 2020-08-28 | COMP | 2022-04-16 | INPR | 2020-12-10 | COMP | Rule 16 | 100 | 101 | 25 | 127 |  |  | 574
9382 | 2018-08-29 | 2019-02-01 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-01 | COMP | 2019-03-01 | COMP | 2019-05-14 | COMP | 2019-03-19 | COMP | Rule 16 | 106 | 9 | 12 | 1 | 53 |  | 137
9390 | 2018-08-29 | 2019-02-01 | 2019-04-09 | 2019-05-10 | COMP | 2019-06-07 | COMP | 2019-08-06 | COMP | 2019-10-15 | COMP | 2019-11-19 | COMP | Rule 15/16 | 106 | 47 | 20 | 42 | 50 | 25 | 308
9604 | 2018-08-29 | 2019-02-07 | 2019-05-16 | 2020-02-12 | COMP | 2020-03-25 | COMP | 2020-04-24 | COMP | 2020-04-23 | COMP | 2020-05-27 | COMP | Rule 15/16 | 110 | 70 | 30 | 23 | 0 | 23 | 437
9765 | 2018-08-29 | 2019-02-14 | 2019-04-13 | 2019-04-13 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-08-13 | COMP | 2019-09-10 | COMP | Rule 16 | 115 | 41 | 62 | 1 | 24 | 20 | 259
9779 | 2018-08-29 | 2019-02-15 | 2019-04-20 | 2019-04-20 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-13 | COMP | 2019-09-12 | COMP | Rule 16 | 116 | 45 | 64 | 1 | 17 | 22 | 261
9807 | 2018-08-29 | 2019-02-19 | 2019-04-26 | 2019-04-26 | COMP | 2020-07-07 | COMP | 2020-08-21 | COMP | 2020-08-31 | COMP | 2020-10-12 | COMP | Rule 15/16 | 117 | 49 | 302 | 34 | 7 | 30 | 534
9915 | 2018-08-29 | 2019-02-22 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-07-21 | INPR | 2019-03-27 | COMP | Rule 16 | 120 | 4 | 15 | 1 |  |  | 143
10188 | 2018-08-29 | 2019-03-05 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-24 | COMP | 2019-06-22 | INPR | 2019-06-17 | COMP | 2019-06-25 | COMP | Rule 16 | 127 | 52 | 8 |  |  |  | 206
10194 | 2018-08-29 | 2019-03-05 | 2019-04-13 | 2019-04-13 | COMP | 2019-04-29 | COMP | 2019-07-24 | COMP | 2019-08-06 | COMP | 2019-08-05 | COMP | Rule 16 | 127 | 29 | 11 | 61 | 10 |  | 234
10370 | 2018-08-29 | 2019-03-13 | 2019-05-13 | 2019-05-13 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2020-06-02 | COMP | 2020-06-17 | COMP | Rule 16 | 133 | 44 | 85 | 1 | 182 | 12 | 452
10877 | 2018-08-29 | 2019-04-03 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-23 | COMP | 2019-11-01 | COMP | 2021-03-27 | INPR | 2019-12-03 | COMP | Rule 16 | 148 | 74 | 28 | 50 |  |  | 316
10993 | 2018-08-29 | 2019-04-09 | 2019-10-25 | 2019-10-25 | COMP | 2021-09-24 | COMP | 2021-09-24 | COMP | 2021-09-30 | COMP | 2021-11-05 | COMP | Rule 15/16 | 152 | 141 | 482 | 1 | 5 | 27 | 803
11098 | 2018-08-29 | 2019-04-12 | 2019-05-26 | 2019-05-26 | COMP | 2019-06-06 | COMP | 2019-06-06 | NOTN | 2019-06-20 | COMP | 2019-07-22 | COMP | Rule 16 | 155 | 31 | 8 |  |  |  | 224
11552 | 2018-08-29 | 2019-05-01 | 2019-09-25 | 2019-12-23 | COMP | 2020-08-19 | COMP | 2021-01-12 | COMP | 2021-02-23 | COMP | 2021-03-04 | COMP | Rule 16 | 168 | 103 | 168 | 99 | 29 | 8 | 630
11601 | 2018-08-29 | 2019-05-03 | 2020-03-11 | 2020-03-11 | COMP | 2020-06-26 | COMP | 2020-07-29 | COMP | 2020-07-21 | COMP | 2020-09-10 | COMP | Rule 16 | 170 | 214 | 77 | 24 | 0 | 31 | 512
11865 | 2018-08-29 | 2019-05-15 | 2019-06-24 | 2019-06-29 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-08-13 | COMP | 2019-09-12 | COMP | Rule 16 | 178 | 28 | 16 | 1 | 16 | 22 | 261
15501 | 2018-08-29 | 2019-11-06 | 2020-02-03 | 2020-02-03 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2022-04-26 | COMP | 2022-05-11 | COMP | Rule 16 | 300 | 58 | 36 | 1 | 529 | 12 | 931
17766 | 2018-08-29 | 2020-02-26 | 2020-03-16 | 2020-03-16 | COMP | 2020-05-08 | COMP | 2020-05-12 | COMP | 2021-03-18 | COMP | 2021-04-05 | COMP | Rule 16 | 373 | 14 | 40 | 3 | 214 | 13 | 652
3911 | 2018-08-30 | 2018-09-28 | 2018-10-19 | 2019-08-29 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-10-07 | COMP | 2019-11-18 | COMP | Rule 15/16 | 21 | 16 | 17 | 1 | 11 | 30 | 306
6650 | 2018-08-30 | 2018-09-04 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-09 | NOTN | 2019-05-08 | COMP | 2019-04-18 | COMP | 2019-06-01 | COMP | Other | 3 | 149 |  | 22 | 0 | 17 | 188
6846 | 2018-08-30 | 2018-09-13 | 2019-02-19 | 2019-02-19 | COMP | 2019-04-29 | COMP | 2019-08-21 | COMP | 2019-08-18 | COMP | 2019-11-04 | COMP | Rule 15/16 | 10 | 107 | 50 | 81 | 0 | 53 | 297
6947 | 2018-08-30 | 2018-09-18 | 2019-01-30 | 2019-02-09 | COMP | 2019-02-13 | COMP | 2019-03-25 | COMP | 2019-02-13 | COMP | 2019-04-17 | COMP | Rule 16 | 13 | 91 | 3 | 28 | 0 | 18 | 157
7036 | 2018-08-30 | 2018-09-24 | 2018-12-04 | 2018-12-04 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-07-21 | INPR | 2019-03-28 | COMP | Rule 16 | 17 | 49 | 11 | 1 |  |  | 143
7125 | 2018-08-30 | 2018-09-28 | 2019-01-14 | 2019-01-14 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-08-07 | COMP | Rule 16 | 21 | 72 | 80 | 1 | 1 | 65 | 235
7273 | 2018-08-30 | 2018-10-04 | 2019-01-05 | 2019-01-05 | COMP | 2019-03-14 | COMP | 2019-04-11 | COMP | 2019-06-18 | COMP | 2019-07-30 | COMP | Rule 16 | 25 | 62 | 47 | 21 | 48 | 30 | 229
7279 | 2018-08-30 | 2018-10-05 | 2018-11-26 | 2018-11-26 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-07-08 | COMP | 2020-08-27 | COMP | Rule 16 | 26 | 34 | 267 | 1 | 142 | 37 | 502
7356 | 2018-08-30 | 2018-10-09 | 2019-08-06 | 2019-08-06 | COMP | 2020-01-08 | COMP | 2020-01-08 | COMP | 2020-02-27 | COMP | 2020-02-13 | COMP | Rule 16 | 28 | 207 | 106 | 1 | 35 |  | 364
7546 | 2018-08-30 | 2018-10-20 | 2019-01-23 | 2020-06-26 | COMP | 2020-09-02 | COMP | 2020-09-25 | COMP | 2023-12-02 | INPR | 2021-11-10 | COMP | Rule 16 | 36 | 62 | 49 | 17 |  |  | 805
7592 | 2018-08-30 | 2018-10-22 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-04-19 | COMP | 2019-06-04 | COMP | Rule 16 | 37 | 103 | 19 | 1 | 3 | 32 | 190
7747 | 2018-08-30 | 2018-10-29 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-04 | COMP | 2019-10-21 | REQD | 2019-10-21 | REQD | 2019-04-17 | COMP | Rule 16 | 42 | 81 | 4 |  |  |  | 157
7862 | 2018-08-30 | 2018-11-03 | 2018-12-31 | 2018-12-31 | COMP | 2019-05-10 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-07-03 | COMP | Rule 15/16 | 46 | 37 | 92 | 5 | 1 | 34 | 211
8372 | 2018-08-30 | 2018-11-28 | 2018-12-18 | 2018-12-18 | COMP | 2019-01-15 | COMP | 2019-04-01 | COMP | 2019-04-08 | COMP | 2019-05-10 | COMP | Rule 16 | 61 | 15 | 19 | 53 | 6 | 25 | 174
8373 | 2018-08-30 | 2018-11-28 | 2019-05-23 | 2019-11-04 | COMP | 2019-11-27 | NOTN | 2020-01-27 | COMP | 2019-11-27 | COMP | 2020-06-19 | COMP | Other | 61 | 123 |  | 55 | 0 | 103 | 453
8429 | 2018-08-30 | 2018-12-01 | 2019-02-02 | 2019-02-02 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-02-15 | COMP | 2019-04-29 | COMP | Rule 16 | 63 | 42 | 9 | 1 | 2 | 51 | 165
8621 | 2018-08-30 | 2018-12-12 | 2019-02-26 | 2019-02-26 | COMP | 2019-04-30 | COMP | 2019-05-01 | COMP | 2019-07-24 | COMP | 2019-09-27 | COMP | Rule 16 | 71 | 51 | 46 | 2 | 59 | 47 | 271
8868 | 2018-08-30 | 2019-01-03 | 2019-02-14 | 2019-02-14 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-07-08 | COMP | 2019-07-29 | COMP | Rule 16 | 85 | 30 | 8 | 1 | 93 | 16 | 228
8918 | 2018-08-30 | 2019-01-06 | 2019-01-24 | 2019-01-24 | COMP |  | INPR | 2019-05-08 | COMP | 2019-09-13 | COMP | 2019-12-14 | COMP | Rule 16 | 86 | 13 |  | 74 | 90 | 63 | 323
9619 | 2018-08-30 | 2019-02-08 | 2019-07-13 | 2019-07-13 | COMP | 2020-08-07 | COMP | 2020-11-14 | COMP | 2020-11-25 | COMP | 2021-01-24 | COMP | Rule 16 | 110 | 108 | 271 | 69 | 8 | 38 | 601
10547 | 2018-08-30 | 2019-03-20 | 2019-09-25 | 2021-06-10 | COMP | 2021-06-17 | COMP | 2021-09-09 | COMP | 2021-09-08 | COMP | 2021-10-15 | COMP | Rule 16 | 137 | 133 | 6 | 59 | 0 | 27 | 787
10824 | 2018-08-30 | 2019-04-01 | 2019-08-02 | 2019-08-02 | COMP | 2019-09-05 | COMP | 2019-12-06 | COMP | 2020-09-22 | COMP | 2020-11-10 | COMP | Rule 16 | 145 | 88 | 24 | 64 | 202 | 36 | 554
10999 | 2018-08-30 | 2019-04-08 | 2019-05-08 | 2019-07-26 | COMP | 2019-08-21 | COMP | 2019-09-03 | COMP | 2020-06-25 | COMP | 2020-09-14 | COMP | Rule 16 | 150 | 23 | 19 | 9 | 205 | 57 | 513
11952 | 2018-08-30 | 2019-05-20 | 2019-08-16 | 2019-08-16 | COMP | 2019-11-21 | COMP | 2020-10-26 | COMP | 2020-11-03 | COMP | 2021-01-06 | COMP | Rule 16 | 180 | 63 | 68 | 235 | 7 | 42 | 590
11973 | 2018-08-30 | 2019-05-20 | 2019-11-23 | 2019-11-23 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-02-11 | COMP | 2020-04-20 | COMP | Rule 16 | 180 | 131 | 45 | 1 | 8 | 49 | 410
12490 | 2018-08-30 | 2019-06-10 | 2019-11-12 | 2019-11-12 | COMP | 2020-01-08 | COMP | 2020-02-27 | COMP |  | INPR | 2020-09-22 | COMP | Rule 15/16 | 194 | 109 | 38 | 35 |  |  | 519
12562 | 2018-08-30 | 2019-06-12 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-07 | NOTN | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-12-07 | COMP | Other | 196 | 40 |  | 1 | 1 | 84 | 318
13577 | 2018-08-30 | 2019-07-31 | 2019-09-16 | 2019-09-16 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-02-21 | COMP | 2020-06-23 | COMP | Rule 16 | 230 | 33 | 47 | 1 | 62 | 87 | 455
14226 | 2018-08-30 | 2019-08-29 | 2019-09-16 | 2019-09-16 | COMP | 2019-11-07 | COMP | 2020-01-03 | INPR | 2020-09-10 | COMP | 2020-09-10 | COMP | Rule 16 | 251 | 12 | 39 |  |  |  | 511
17390 | 2018-08-30 | 2020-02-12 | 2020-04-06 | 2020-04-06 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-07-28 | COMP | 2020-07-29 | COMP | Rule 15/16 | 363 | 38 | 74 | 1 | 8 | 2 | 481
3972 | 2018-08-31 | 2018-11-03 | 2018-11-27 | 2018-11-27 | COMP | 2019-04-12 | COMP | 2019-06-10 | COMP | 2023-04-15 | INPR | 2019-06-12 | COMP | Rule 16 | 45 | 14 | 95 | 41 |  |  | 195
4041 | 2018-08-31 | 2018-12-28 | 2019-03-15 | 2019-03-15 | COMP | 2019-10-23 | COMP | 2020-04-08 | COMP | 2020-05-13 | COMP | 2020-05-26 | COMP | Rule 16 | 81 | 53 | 156 | 114 | 26 | 9 | 434
6756 | 2018-08-31 | 2018-09-11 | 2019-02-25 | 2019-02-25 | COMP | 2019-08-06 | NOTN | 2019-08-06 | COMP | 2019-05-14 | COMP | 2019-12-31 | COMP | Other | 7 | 113 |  | 115 | 0 | 101 | 333
6928 | 2018-08-31 | 2018-09-17 | 2018-11-30 | 2018-11-30 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-07-21 | INPR | 2019-04-05 | COMP | Rule 16 | 11 | 52 | 29 | 1 |  |  | 148
7057 | 2018-08-31 | 2018-09-25 | 2019-01-23 | 2019-01-23 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-03-13 | COMP | 2019-04-19 | COMP | Rule 16 | 17 | 81 | 34 | 1 | 2 | 28 | 158
7126 | 2018-08-31 | 2018-09-28 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-04-02 | COMP | Rule 16 | 20 | 72 | 14 | 1 | 1 | 42 | 145
7155 | 2018-08-31 | 2018-09-29 | 2018-11-26 | 2018-11-26 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-01-16 | COMP | 2019-03-18 | COMP | Rule 16 | 20 | 38 | 22 | 1 | 15 | 42 | 134
7158 | 2018-08-31 | 2018-09-29 | 2018-11-03 | 2019-02-05 | COMP | 2019-02-04 | NOTN | 2019-02-05 | COMP | 2019-02-01 | COMP | 2019-04-10 | COMP | Other | 20 | 25 |  | 1 | 0 | 46 | 151
7261 | 2018-08-31 | 2018-10-04 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-05 | COMP | 2019-04-15 | COMP | 2019-11-25 | COMP | 2019-12-10 | COMP | Rule 16 | 24 | 76 | 27 | 30 | 157 | 10 | 319
7358 | 2018-08-31 | 2018-10-09 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-03 | NOTN | 2018-12-03 | COMP | 2019-09-01 | INPR | 2019-01-19 | COMP | Rule 16 | 27 | 35 |  | 3 |  |  | 95
7476 | 2018-08-31 | 2018-10-16 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-26 | COMP | 2018-12-03 | COMP | 2018-12-18 | COMP | 2019-01-11 | COMP | Rule 16 | 32 | 21 | 7 | 6 | 12 | 17 | 90
7581 | 2018-08-31 | 2018-10-21 | 2019-01-25 | 2019-01-25 | COMP | 2019-01-26 | NOTN | 2019-10-21 | INPR | 2019-01-26 | COMP | 2019-03-04 | COMP | Rule 16 | 35 | 64 |  |  |  |  | 124
7847 | 2018-08-31 | 2018-11-02 | 2019-02-05 | 2019-03-15 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-05-20 | COMP | 2019-07-11 | COMP | Rule 16 | 45 | 62 | 20 | 1 | 28 | 37 | 215
8055 | 2018-08-31 | 2018-11-13 | 2019-02-19 | 2019-02-19 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-08-09 | COMP | 2020-07-14 | COMP | Rule 16 | 51 | 65 | 35 | 1 | 88 | 234 | 469
8058 | 2018-08-31 | 2018-11-14 | 2018-11-26 | 2018-11-26 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2021-02-27 | INPR | 2020-02-12 | COMP | Rule 16 | 52 | 7 | 270 | 1 |  |  | 362
8190 | 2018-08-31 | 2018-11-17 | 2019-03-13 | 2019-03-14 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-05-29 | COMP | 2019-07-02 | COMP | Rule 16 | 54 | 77 | 13 | 1 | 42 | 25 | 209
8240 | 2018-08-31 | 2018-11-20 | 2019-02-02 | 2019-02-02 | COMP | 2019-02-25 | COMP | 2019-03-08 | COMP | 2019-04-04 | COMP | 2019-04-25 | COMP | Rule 16 | 56 | 49 | 15 | 10 | 20 | 16 | 162
8267 | 2018-08-31 | 2018-11-21 | 2018-12-20 | 2018-12-20 | COMP | 2019-01-08 | COMP | 2019-01-08 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | Rule 16 | 57 | 20 | 12 | 1 | 87 | 1 | 173
8608 | 2018-08-31 | 2018-12-12 | 2019-01-03 | 2019-01-03 | COMP | 2019-10-18 | COMP | 2019-05-06 | INPR | 2021-01-30 | REQD | 2020-01-21 | COMP | Rule 16 | 70 | 15 | 202 |  |  |  | 346
8836 | 2018-08-31 | 2018-12-31 | 2019-02-02 | 2019-02-02 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-04-03 | COMP | 2019-06-03 | COMP | Rule 16 | 82 | 23 | 16 | 1 | 27 | 43 | 188
9719 | 2018-08-31 | 2019-02-12 | 2019-03-18 | 2019-03-18 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-12-29 | COMP | 2020-01-07 | COMP | Rule 16 | 111 | 24 | 67 | 1 | 132 | 6 | 337
10191 | 2018-08-31 | 2019-03-05 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-07-10 | COMP | Rule 16 | 125 | 67 | 11 | 1 | 1 | 14 | 214
10357 | 2018-08-31 | 2019-03-12 | 2019-04-02 | 2019-04-02 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-09-06 | COMP | 2019-10-16 | COMP | Rule 16 | 130 | 16 | 82 | 1 | 30 | 29 | 283
10541 | 2018-08-31 | 2019-03-19 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-22 | COMP | 2019-03-27 | INPR | 2019-04-17 | COMP | 2019-05-05 | COMP | Rule 16 | 135 | 2 | 24 |  |  |  | 168
11753 | 2018-08-31 | 2019-05-09 | 2019-09-04 | 2019-09-09 | COMP | 2019-10-30 | COMP | 2019-10-14 | COMP | 2019-08-27 | COMP | 2021-11-06 | COMP | Rule 16 | 172 | 82 | 38 |  | 0 | 521 | 801
14601 | 2018-08-31 | 2019-09-18 | 2020-01-28 | 2020-01-28 | COMP | 2020-01-28 | NOTN | 2020-03-17 | COMP | 2020-01-28 | COMP | 2021-03-17 | COMP | Other | 263 | 89 |  | 35 | 0 | 253 | 637
6908 | 2018-09-01 | 2018-09-17 | 2018-11-07 | 2018-11-07 | COMP | 2019-02-11 | COMP | 2019-03-21 | COMP | 2019-05-16 | COMP | 2019-07-23 | COMP | Rule 16 | 10 | 38 | 63 | 28 | 41 | 47 | 222
6963 | 2018-09-01 | 2018-09-19 | 2018-11-11 | 2018-11-11 | COMP | 2018-11-26 | COMP | 2018-11-26 | COMP | 2020-03-21 | INPR | 2019-12-10 | COMP | Rule 16 | 12 | 38 | 8 | 1 |  |  | 318
11650 | 2018-09-01 | 2019-05-06 | 2019-05-10 | 2019-05-10 | COMP | 2019-06-17 | COMP | 2019-06-17 | INPR | 2021-03-27 | REQD | 2020-03-12 | COMP | Rule 16 | 168 | 5 | 26 |  |  |  | 381
6898 | 2018-09-02 | 2018-09-15 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2019-03-20 | COMP | 2019-03-25 | COMP | Rule 16 | 9 | 50 | 57 | 1 | 21 | 4 | 138
7179 | 2018-09-02 | 2018-10-01 | 2019-01-05 | 2019-01-05 | COMP | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-08-22 | COMP | 2019-09-10 | COMP | Rule 16 | 20 | 65 | 66 | 1 | 95 | 13 | 256
7388 | 2018-09-02 | 2018-10-09 | 2019-02-02 | 2019-02-02 | COMP | 2019-02-12 | COMP | 2019-02-26 | COMP | 2019-04-16 | COMP | 2019-04-26 | COMP | Rule 16 | 26 | 78 | 7 | 10 | 36 | 9 | 162
7439 | 2018-09-02 | 2018-10-12 | 2018-11-01 | 2018-11-01 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-10-21 | INPR | 2019-01-03 | COMP | Rule 16 | 29 | 15 | 21 | 1 |  |  | 83
13504 | 2018-09-02 | 2019-07-29 | 2019-12-06 | 2019-12-06 | COMP | 2019-12-20 | COMP | 2020-02-08 | COMP | 2020-06-16 | COMP | 2020-07-10 | COMP | Rule 15/16 | 226 | 91 | 11 | 33 | 90 | 19 | 466
4116 | 2018-09-03 | 2019-02-27 | 2019-03-04 | 2019-03-04 | COMP | 2019-07-25 | COMP | 2019-07-30 | COMP | 2021-01-06 | COMP | 2021-02-09 | COMP | Rule 16 | 120 | 4 | 102 | 4 | 362 | 24 | 611
4099 | 2018-09-04 | 2019-02-02 | 2019-05-03 | 2020-06-19 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-05-11 | COMP | 2020-07-01 | COMP | Other | 103 | 64 | 8 | 1 | 0 | 2 | 459
7122 | 2018-09-04 | 2018-09-28 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-05-07 | COMP | 2019-05-28 | COMP | Rule 16 | 19 | 77 | 16 | 1 | 60 | 15 | 183
7153 | 2018-09-04 | 2018-09-29 | 2018-11-28 | 2018-11-28 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-07-01 | COMP | 2019-09-25 | COMP | Rule 16 | 19 | 40 | 54 | 1 | 96 | 61 | 267
7321 | 2018-09-04 | 2018-10-08 | 2018-12-12 | 2018-12-12 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-05-07 | COMP | 2019-05-15 | COMP | Rule 16 | 25 | 45 | 68 | 1 | 34 | 7 | 175
7482 | 2018-09-04 | 2018-10-16 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-05 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-03-25 | COMP | Rule 16 | 31 | 60 | 16 | 2 | 1 | 33 | 138
7523 | 2018-09-04 | 2018-10-18 | 2019-01-31 | 2019-04-11 | COMP | 2019-03-22 | NOTN | 2019-03-22 | COMP | 2019-04-24 | COMP | 2019-06-21 | COMP | Other | 33 | 70 |  |  | 24 | 42 | 201
7547 | 2018-09-04 | 2018-10-19 | 2019-01-02 | 2019-03-29 | COMP | 2019-04-08 | NOTN | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-04-30 | COMP | Other | 34 | 49 |  | 7 | 1 | 17 | 164
7606 | 2018-09-04 | 2018-10-23 | 2019-04-27 | 2019-04-27 | COMP | 2019-07-31 | COMP | 2019-08-13 | COMP | 2020-02-05 | COMP | 2020-02-25 | COMP | Rule 15/16 | 36 | 127 | 66 | 10 | 120 | 14 | 369
7629 | 2018-09-04 | 2018-10-23 | 2019-09-09 | 2019-09-09 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-02-18 | COMP | 2020-04-10 | COMP | Rule 15/16 | 36 | 220 | 38 | 1 | 73 | 39 | 402
7666 | 2018-09-04 | 2018-10-24 | 2019-02-05 | 2019-02-05 | COMP | 2019-02-27 | COMP | 2019-02-27 | COMP | 2019-03-25 | COMP | 2019-04-19 | COMP | Rule 16 | 37 | 69 | 16 | 1 | 19 | 20 | 157
7894 | 2018-09-04 | 2018-11-04 | 2019-01-18 | 2019-01-18 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-04-24 | COMP | 2019-05-06 | COMP | Rule 16 | 44 | 50 | 8 | 1 | 60 | 9 | 168
7945 | 2018-09-04 | 2018-11-06 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-02-14 | COMP | 2019-03-19 | COMP | Rule 16 | 46 | 31 | 39 | 1 | 0 | 21 | 134
7976 | 2018-09-04 | 2018-11-08 | 2019-01-15 | 2019-01-15 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-02-05 | COMP | 2019-03-21 | COMP | Rule 15/16 | 48 | 44 | 11 | 1 | 5 | 32 | 136
8066 | 2018-09-04 | 2018-11-15 | 2019-06-28 | 2020-08-26 | COMP | 2021-01-08 | COMP | 2021-01-27 | COMP | 2021-01-27 | COMP | 2021-02-20 | COMP | Rule 15/16 | 52 | 155 | 92 | 13 | 1 | 17 | 618
8081 | 2018-09-04 | 2018-11-14 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-15 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-07-09 | COMP | Rule 16 | 51 | 61 | 43 | 10 | 1 | 51 | 212
8229 | 2018-09-04 | 2018-11-19 | 2019-03-25 | 2019-03-25 | COMP | 2019-07-08 | COMP | 2020-07-28 | COMP | 2020-08-03 | COMP | 2020-09-15 | COMP | Rule 16 | 54 | 85 | 74 | 268 | 5 | 31 | 512
8272 | 2018-09-04 | 2018-11-21 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-02-14 | COMP | 2019-07-17 | COMP | Rule 16 | 56 | 42 | 12 | 1 | 5 | 107 | 218
8371 | 2018-09-04 | 2018-11-28 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-08 | COMP | 2019-03-11 | COMP | 2019-07-12 | COMP | 2019-07-29 | COMP | Rule 16 | 59 | 37 | 14 | 21 | 88 | 12 | 226
8516 | 2018-09-04 | 2018-12-06 | 2018-12-21 | 2019-01-23 | COMP | 2019-02-06 | COMP | 2019-02-07 | COMP | 2019-02-08 | COMP | 2019-03-19 | COMP | Rule 16 | 65 | 12 | 11 | 2 | 2 | 27 | 134
8536 | 2018-09-04 | 2018-12-07 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-04 | COMP | 2019-04-19 | COMP | 2019-09-22 | INPR | 2019-05-29 | COMP | Rule 16 | 66 | 51 | 8 | 35 |  |  | 184
8820 | 2018-09-04 | 2018-12-31 | 2019-03-13 | 2019-03-13 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-05-15 | COMP | Rule 16 | 81 | 50 | 257 | 1 | 1 | 42 | 427
9072 | 2018-09-04 | 2019-01-15 | 2019-02-21 | 2019-02-21 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2020-01-14 | COMP | 2020-02-19 | COMP | Rule 16 | 91 | 26 | 164 | 1 | 63 | 25 | 365
9159 | 2018-09-04 | 2019-01-18 | 2019-06-03 | 2019-06-03 | COMP | 2019-08-12 | NOTN | 2019-08-12 | COMP | 2019-08-12 | COMP | 2021-06-04 | COMP | Other | 94 | 94 |  | 50 | 1 | 457 | 692
9398 | 2018-09-04 | 2019-02-02 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-03-22 | COMP | 2019-04-24 | COMP | Rule 16 | 103 | 16 | 18 | 1 | 2 | 24 | 160
9655 | 2018-09-04 | 2019-02-10 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-24 | COMP | 2019-07-19 | COMP | 2019-08-29 | COMP | 2019-09-17 | COMP | Rule 16 | 108 | 66 | 29 | 19 | 30 | 13 | 261
9896 | 2018-09-04 | 2019-02-21 | 2019-09-21 | 2019-09-22 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-11-19 | COMP | 2019-12-17 | COMP | Rule 16 | 116 | 149 | 24 | 1 | 18 | 19 | 323
9996 | 2018-09-04 | 2019-02-26 | 2019-05-03 | 2019-05-03 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-12-16 | COMP | 2020-01-08 | COMP | Rule 16 | 119 | 49 | 112 | 1 | 45 | 16 | 337
10221 | 2018-09-04 | 2019-03-06 | 2019-04-22 | 2019-04-22 | COMP | 2019-05-03 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-07 | COMP | Rule 16 | 125 | 34 | 10 | 55 | 1 | 13 | 233
10298 | 2018-09-04 | 2019-03-11 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-13 | COMP | 2019-10-23 | COMP | Rule 16 | 128 | 24 | 17 | 1 | 7 | 115 | 287
10324 | 2018-09-04 | 2019-03-11 | 2019-06-03 | 2019-06-03 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-30 | COMP | 2019-08-20 | COMP | Rule 15/16 | 128 | 60 | 31 | 1 | 11 | 16 | 242
10558 | 2018-09-04 | 2019-03-20 | 2019-04-03 | 2019-04-03 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-04-24 | COMP | 2019-05-13 | COMP | Rule 16 | 135 | 11 | 15 | 1 | 2 | 14 | 173
10792 | 2018-09-04 | 2019-03-30 | 2019-08-07 | 2019-08-07 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-12-03 | COMP | 2020-12-29 | COMP | Rule 16 | 142 | 91 | 270 | 1 | 65 | 18 | 583
11339 | 2018-09-04 | 2019-04-23 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-09 | COMP | 2019-11-04 | COMP | 2019-11-20 | COMP | 2020-01-02 | COMP | Rule 16 | 159 | 68 | 30 | 41 | 12 | 28 | 333
11708 | 2018-09-04 | 2019-05-08 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-23 | COMP | 2020-10-28 | COMP | 2020-12-11 | COMP | 2021-02-19 | COMP | Rule 16 | 170 | 63 | 34 | 279 | 30 | 47 | 618
14303 | 2018-09-04 | 2019-09-04 | 2020-02-03 | 2020-02-03 | COMP | 2020-08-26 | COMP | 2020-12-23 | COMP | 2022-07-16 | INPR | 2021-01-24 | COMP | Rule 15/16 | 252 | 103 | 146 | 82 |  |  | 599
14579 | 2018-09-04 | 2019-09-17 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-26 | COMP | 2020-01-24 | COMP | 2020-04-28 | COMP | 2020-05-13 | COMP | Rule 16 | 261 | 60 | 10 | 20 | 67 | 12 | 425
15864 | 2018-09-04 | 2019-11-26 | 2020-02-07 | 2020-02-14 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2023-11-13 | INPR | 2020-06-16 | COMP | Rule 16 | 310 | 49 | 47 | 1 |  |  | 448
3913 | 2018-09-05 | 2018-10-01 | 2018-11-06 | 2018-11-06 | COMP | 2019-01-11 | COMP | 2018-11-27 | COMP | 2018-12-13 | COMP | 2019-04-23 | COMP | Rule 16 | 19 | 27 | 44 |  | 13 | 90 | 158
6959 | 2018-09-05 | 2018-09-19 | 2018-11-07 | 2019-04-03 | COMP | 2019-07-17 | COMP | 2019-09-27 | COMP | 2019-07-23 | COMP | 2019-11-13 | COMP | Rule 16 | 11 | 36 | 74 | 52 | 0 | 33 | 300
7005 | 2018-09-05 | 2018-09-21 | 2019-01-02 | 2019-01-02 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-02-05 | COMP | 2019-03-19 | COMP | Rule 15/16 | 13 | 69 | 23 | 1 | 2 | 30 | 133
7058 | 2018-09-05 | 2018-09-25 | 2018-10-07 | 2018-10-07 | COMP | 2018-11-01 | COMP | 2018-11-01 | COMP | 2019-01-31 | COMP | 2019-04-01 | COMP | Rule 16 | 15 | 9 | 19 | 1 | 60 | 42 | 142
7167 | 2018-09-05 | 2018-10-01 | 2018-10-29 | 2018-10-29 | COMP | 2018-12-10 | NOTN | 2018-12-10 | COMP | 2019-01-20 | COMP | 2019-01-29 | COMP | Other | 19 | 21 |  | 28 | 28 | 6 | 99
7211 | 2018-09-05 | 2018-10-02 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | Rule 16 | 20 | 69 | 9 | 1 | 13 | 1 | 109
7268 | 2018-09-05 | 2018-10-04 | 2018-12-16 | 2018-12-16 | COMP | 2019-01-17 | COMP | 2019-04-23 | NOTN | 2019-04-24 | COMP | 2019-05-01 | COMP | Rule 16 | 22 | 49 | 22 |  |  |  | 164
7282 | 2018-09-05 | 2018-10-05 | 2019-01-01 | 2019-01-01 | COMP | 2019-02-20 | COMP | 2019-04-17 | COMP | 2019-04-29 | COMP | 2019-06-06 | COMP | Rule 16 | 23 | 58 | 34 | 41 | 9 | 28 | 189
7669 | 2018-09-05 | 2018-10-24 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-12 | COMP | 2018-12-12 | NOTN | 2018-12-19 | COMP | 2019-01-11 | COMP | Rule 16 | 36 | 14 | 20 |  |  |  | 88
7863 | 2018-09-05 | 2018-11-03 | 2018-12-31 | 2018-12-31 | COMP | 2019-02-11 | NOTN | 2019-04-18 | COMP | 2021-03-05 | NOTN | 2021-05-19 | COMP | Other | 43 | 37 |  | 76 |  |  | 680
7938 | 2018-09-05 | 2018-11-06 | 2018-12-07 | 2018-12-07 | COMP | 2019-02-08 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-04-04 | COMP | Rule 16 | 45 | 21 | 43 | 24 | 1 | 16 | 145
8228 | 2018-09-05 | 2018-11-19 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-06-12 | COMP | 2019-06-26 | COMP | Rule 16 | 53 | 75 | 9 | 1 | 59 | 11 | 203
8492 | 2018-09-05 | 2018-12-06 | 2019-01-14 | 2019-01-14 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-05-03 | COMP | 2019-05-23 | COMP | Rule 16 | 64 | 26 | 47 | 1 | 32 | 15 | 180
8585 | 2018-09-05 | 2018-12-10 | 2019-04-23 | 2019-04-23 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2020-08-03 | COMP | 2020-10-09 | COMP | Rule 15/16 | 66 | 93 | 33 | 1 | 292 | 49 | 529
8638 | 2018-09-05 | 2018-12-13 | 2019-01-31 | 2019-01-31 | COMP | 2019-05-21 | COMP | 2019-08-08 | COMP | 2021-01-26 | COMP | 2021-02-12 | COMP | Rule 16 | 69 | 33 | 78 | 56 | 368 | 14 | 613
8696 | 2018-09-05 | 2018-12-17 | 2019-03-29 | 2019-03-29 | COMP | 2019-06-27 | COMP | 2019-07-03 | COMP | 2019-07-29 | COMP | 2019-08-28 | COMP | Rule 16 | 71 | 71 | 64 | 5 | 18 | 23 | 247
9149 | 2018-09-05 | 2019-01-19 | 2019-02-20 | 2019-02-20 | COMP | 2019-04-05 | COMP | 2019-04-11 | COMP | 2019-04-16 | COMP | 2019-06-11 | COMP | Rule 16 | 93 | 21 | 33 | 5 | 4 | 40 | 192
9164 | 2018-09-05 | 2019-01-18 | 2019-02-05 | 2019-03-25 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-04-30 | COMP | Rule 16 | 93 | 12 | 10 | 1 | 1 | 18 | 163
9232 | 2018-09-05 | 2019-01-23 | 2019-05-02 | 2019-05-29 | COMP | 2019-06-18 | COMP | 2019-06-18 | COMP | 2019-08-20 | COMP | 2020-01-31 | COMP | Rule 15 | 95 | 71 | 15 | 1 | 45 | 112 | 352
9384 | 2018-09-05 | 2019-01-31 | 2019-06-14 | 2020-06-01 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-06-18 | COMP | 2020-09-18 | COMP | Rule 16 | 101 | 95 | 17 | 1 | 0 | 63 | 514
9556 | 2018-09-05 | 2019-02-07 | 2019-04-15 | 2019-04-15 | COMP | 2019-04-18 | NOTN | 2019-07-15 | COMP | 2019-08-05 | COMP | 2019-08-27 | COMP | Other | 106 | 47 |  | 64 | 16 | 17 | 246
9844 | 2018-09-05 | 2019-02-20 | 2019-10-10 | 2019-10-10 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2022-01-06 | COMP | 2022-02-18 | COMP | Rule 15/16 | 114 | 164 | 133 | 1 | 432 | 31 | 870
10089 | 2018-09-05 | 2019-03-01 | 2019-09-15 | 2019-09-15 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-11-20 | COMP | 2021-01-25 | COMP | Rule 16 | 121 | 138 | 85 | 1 | 216 | 42 | 599
10254 | 2018-09-05 | 2019-03-07 | 2019-05-04 | 2019-05-04 | COMP | 2019-06-11 | COMP | 2020-10-01 | COMP | 2020-10-13 | COMP | 2020-11-13 | COMP | Rule 16 | 125 | 42 | 26 | 332 | 9 | 23 | 553
10332 | 2018-09-05 | 2019-03-11 | 2019-06-23 | 2019-06-23 | COMP | 2019-07-12 | COMP | 2019-10-08 | COMP | 2020-10-06 | COMP | 2020-11-02 | COMP | Rule 16 | 127 | 74 | 14 | 62 | 252 | 20 | 545
10516 | 2018-09-05 | 2019-03-19 | 2019-04-26 | 2019-04-26 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-12-11 | COMP | 2020-01-16 | COMP | Rule 16 | 133 | 29 | 34 | 1 | 125 | 25 | 342
10565 | 2018-09-05 | 2019-03-20 | 2019-06-14 | 2019-06-14 | COMP | 2019-12-26 | COMP | 2020-02-27 | COMP | 2020-02-12 | COMP | 2020-03-24 | COMP | Rule 16 | 134 | 62 | 134 | 43 | 0 | 19 | 388
12618 | 2018-09-05 | 2019-06-17 | 2020-01-10 | 2020-10-02 | COMP | 2020-10-08 | COMP | 2020-11-02 | COMP | 2020-12-21 | COMP | 2021-01-12 | COMP | Rule 15/16 | 196 | 143 | 5 | 18 | 33 | 15 | 591
12728 | 2018-09-05 | 2019-06-20 | 2019-08-29 | 2019-08-29 | COMP | 2019-11-05 | COMP | 2019-12-03 | COMP | 2020-06-09 | COMP | 2020-07-03 | COMP | Rule 15/16 | 199 | 50 | 48 | 18 | 131 | 19 | 460
12758 | 2018-09-05 | 2019-06-21 | 2019-09-10 | 2019-09-10 | COMP | 2019-10-04 | COMP | 2019-11-04 | COMP | 2020-03-01 | INPR | 2019-11-20 | COMP | Rule 16 | 200 | 56 | 19 | 22 |  |  | 305
13907 | 2018-09-05 | 2019-08-15 | 2019-10-20 | 2019-10-20 | COMP | 2019-10-31 | COMP | 2019-12-05 | COMP | 2020-08-07 | COMP | 2020-09-01 | COMP | Rule 16 | 238 | 46 | 9 | 23 | 172 | 18 | 502
3876 | 2018-09-06 | 2018-09-06 | 2018-09-09 | 2018-09-09 | COMP | 2018-12-04 | COMP | 2018-12-27 | COMP | 2020-10-24 | INPR | 2019-01-31 | COMP | Rule 15 | 1 | 2 | 59 | 17 |  |  | 100
3961 | 2018-09-06 | 2018-10-30 | 2019-10-18 | 2019-10-18 | COMP | 2020-08-18 | COMP | 2020-09-18 | COMP | 2020-11-15 | COMP | 2020-12-12 | COMP | Rule 16 | 39 | 244 | 210 | 23 | 40 | 18 | 570
3978 | 2018-09-06 | 2018-11-04 | 2018-12-18 | 2018-12-18 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-07-21 | INPR | 2019-04-24 | COMP | Rule 16 | 42 | 29 | 51 | 1 |  |  | 158
4025 | 2018-09-06 | 2018-12-07 | 2019-10-28 | 2019-10-28 | COMP | 2019-10-21 | COMP | 2019-10-28 | COMP | 2019-12-02 | COMP | 2019-12-30 | COMP | Rule 16 | 64 | 225 |  | 6 | 23 | 20 | 329
4124 | 2018-09-06 | 2019-03-18 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-05-16 | COMP | 2019-07-02 | COMP | Other | 131 | 9 | 21 | 1 | 16 | 33 | 206
6922 | 2018-09-06 | 2018-09-18 | 2019-04-06 | 2019-04-06 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2020-01-16 | COMP | 2020-02-25 | COMP | Rule 16 | 9 | 137 | 19 | 1 | 178 | 27 | 367
7219 | 2018-09-06 | 2018-10-03 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-19 | COMP | 2019-03-20 | COMP | 2019-04-25 | COMP | 2019-06-08 | COMP | Rule 16 | 20 | 77 | 37 | 2 | 27 | 31 | 189
7325 | 2018-09-06 | 2018-10-08 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-17 | COMP | 2019-01-31 | COMP | 2019-03-06 | COMP | 2019-03-08 | COMP | Rule 16 | 23 | 43 | 6 | 31 | 24 | 3 | 125
7350 | 2018-09-06 | 2018-10-10 | 2018-12-04 | 2018-12-04 | COMP | 2019-01-09 | COMP | 2019-02-20 | COMP | 2019-07-21 | INPR | 2019-02-26 | COMP | Rule 16 | 25 | 37 | 25 | 29 |  |  | 117
7378 | 2018-09-06 | 2018-10-10 | 2018-12-12 | 2018-12-12 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-04-18 | COMP | 2019-05-14 | COMP | Rule 16 | 25 | 43 | 70 | 1 | 19 | 19 | 172
7440 | 2018-09-06 | 2018-10-12 | 2019-01-31 | 2020-01-08 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-05-22 | COMP | 2020-05-23 | COMP | Rule 16 | 27 | 74 | 77 | 1 | 20 | 1 | 430
7478 | 2018-09-06 | 2018-10-16 | 2018-10-31 | 2018-10-31 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2018-12-04 | COMP | 2019-01-30 | COMP | Rule 16 | 29 | 12 | 22 | 1 | 1 | 39 | 99
7589 | 2018-09-06 | 2018-10-22 | 2019-02-01 | 2019-03-15 | COMP | 2019-05-14 | COMP | 2019-05-23 | COMP | 2019-05-22 | COMP | 2019-06-14 | COMP | Rule 15/16 | 33 | 69 | 43 | 8 | 0 | 16 | 194
7764 | 2018-09-06 | 2018-10-30 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-21 | COMP | 2018-12-21 | COMP | 2018-12-26 | COMP | 2019-01-02 | COMP | Rule 16 | 39 | 27 | 10 | 1 | 3 | 5 | 80
8211 | 2018-09-06 | 2018-11-19 | 2019-01-26 | 2019-01-26 | COMP | 2019-02-25 | COMP | 2019-04-10 | COMP | 2019-04-01 | COMP | 2019-05-22 | COMP | Rule 16 | 52 | 45 | 20 | 33 | 0 | 31 | 178
8584 | 2018-09-06 | 2018-12-10 | 2019-04-15 | 2019-04-15 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2020-01-19 | INPR | 2019-09-30 | COMP | Rule 16 | 65 | 87 | 85 | 1 |  |  | 268
9065 | 2018-09-06 | 2019-01-15 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-19 | COMP | 2019-04-29 | COMP | 2019-05-23 | COMP | 2019-07-09 | COMP | Rule 16 | 89 | 31 | 14 | 30 | 19 | 32 | 210
9128 | 2018-09-06 | 2019-01-17 | 2019-04-29 | 2019-04-29 | COMP | 2019-01-22 | NOTN | 2019-04-29 | COMP | 2019-11-26 | COMP | 2019-12-31 | COMP | Other | 91 | 71 |  | 1 | 148 | 23 | 330
9151 | 2018-09-06 | 2019-01-19 | 2019-03-01 | 2019-03-01 | COMP | 2019-05-21 | COMP | 2019-05-24 | COMP | 2019-09-20 | COMP | 2019-12-06 | COMP | Rule 16 | 92 | 28 | 58 | 4 | 83 | 53 | 314
9171 | 2018-09-06 | 2019-01-19 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-21 | COMP | 2019-10-28 | COMP | 2019-10-22 | COMP | 2019-12-23 | COMP | Rule 15/16 | 92 | 124 | 26 | 48 | 0 | 38 | 325
9816 | 2018-09-06 | 2019-02-19 | 2019-04-17 | 2019-04-17 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2020-05-27 | COMP | 2020-07-15 | COMP | Rule 16 | 112 | 42 | 272 | 1 | 9 | 36 | 467
10047 | 2018-09-06 | 2019-02-28 | 2019-03-14 | 2019-03-14 | COMP | 2019-05-29 | COMP | 2019-05-29 | INPR | 2019-08-29 | COMP | 2019-09-06 | COMP | Rule 16 | 119 | 11 | 54 |  |  |  | 252
10088 | 2018-09-06 | 2019-03-01 | 2020-12-09 | 2021-12-17 | COMP | 2022-08-16 | COMP | 2022-08-29 | COMP | 2022-08-09 | COMP | 2022-12-21 | COMP | Rule 15/16 | 120 | 449 | 168 | 10 | 0 | 79 | 1079
10233 | 2018-09-06 | 2019-03-07 | 2019-05-16 | 2019-05-29 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-08-05 | COMP | 2019-09-26 | COMP | Rule 16 | 124 | 51 | 9 | 1 | 40 | 38 | 266
10778 | 2018-09-06 | 2019-03-29 | 2019-08-21 | 2019-08-21 | COMP | 2020-03-05 | COMP | 2020-07-06 | COMP | 2022-03-24 | COMP | 2022-04-27 | COMP | Rule 16 | 140 | 102 | 134 | 87 | 433 | 25 | 916
10882 | 2018-09-06 | 2019-04-03 | 2019-08-12 | 2020-01-14 | COMP | 2020-01-22 | COMP | 2020-01-06 | COMP | 2020-01-03 | COMP | 2020-02-20 | COMP | Rule 16 | 143 | 92 | 6 |  | 0 | 32 | 364
10885 | 2018-09-06 | 2019-04-03 | 2019-04-16 | 2019-05-09 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-05-23 | COMP | 2019-06-21 | COMP | Rule 16 | 143 | 10 | 4 | 1 | 8 | 21 | 199
13178 | 2018-09-06 | 2019-07-15 | 2019-08-23 | 2019-08-23 | COMP | 2020-09-23 | COMP | 2021-02-26 | COMP | 2021-07-20 | COMP | 2021-08-24 | COMP | Rule 16 | 214 | 30 | 274 | 106 | 101 | 26 | 746
15234 | 2018-09-06 | 2019-10-22 | 2020-02-24 | 2020-02-24 | COMP | 2020-04-08 | COMP | 2020-09-17 | COMP | 2021-03-18 | COMP | 2021-04-05 | COMP | Rule 16 | 284 | 83 | 33 | 115 | 124 | 13 | 647
18522 | 2018-09-06 | 2020-03-27 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-04-23 | COMP | 2020-05-21 | COMP | Rule 16 | 390 | 12 | 4 | 1 | 6 | 21 | 429
3910 | 2018-09-07 | 2018-09-28 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-28 | COMP | 2018-11-30 | COMP | 2018-11-29 | COMP | 2019-01-30 | COMP | Rule 16 | 16 | 33 | 9 | 3 | 0 | 41 | 98
3927 | 2018-09-07 | 2018-10-15 | 2018-12-03 | 2018-12-03 | COMP | 2018-12-12 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-04-29 | COMP | Rule 16 | 27 | 33 | 8 | 56 | 1 | 40 | 160
6709 | 2018-09-07 | 2018-09-10 | 2018-10-03 | 2018-10-03 | COMP | 2019-01-24 | COMP | 2019-01-24 | COMP | 2019-03-22 | COMP | 2019-05-09 | COMP | Rule 16 | 2 | 18 | 76 | 1 | 41 | 35 | 168
6857 | 2018-09-07 | 2018-09-14 | 2019-02-12 | 2019-02-12 | COMP | 2019-03-06 | COMP | 2019-11-14 | COMP | 2019-11-20 | COMP | 2019-12-19 | COMP | Rule 15/16 | 6 | 102 | 16 | 178 | 5 | 20 | 322
6996 | 2018-09-07 | 2018-09-21 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-24 | COMP | 2019-05-13 | COMP | 2019-04-06 | COMP | 2019-06-20 | COMP | Rule 16 | 11 | 47 | 18 | 97 | 0 | 28 | 197
6997 | 2018-09-07 | 2018-09-21 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-24 | COMP | 2018-12-24 | COMP | 2019-06-03 | COMP | 2019-07-01 | COMP | Rule 16 | 11 | 47 | 18 | 1 | 111 | 21 | 204
7107 | 2018-09-07 | 2018-09-27 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-15 | COMP | 2019-02-28 | COMP | Rule 16 | 15 | 39 | 20 | 1 | 17 | 31 | 118
7121 | 2018-09-07 | 2018-09-28 | 2019-06-14 | 2019-06-14 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2020-02-06 | COMP | 2020-03-06 | COMP | Rule 16 | 16 | 178 | 35 | 1 | 128 | 21 | 374
7258 | 2018-09-07 | 2018-10-05 | 2018-12-21 | 2019-03-22 | COMP | 2019-03-28 | COMP | 2019-08-07 | COMP | 2019-08-14 | COMP | 2019-09-19 | COMP | Rule 16 | 21 | 53 | 5 | 93 | 6 | 26 | 260
7307 | 2018-09-07 | 2018-10-06 | 2019-01-04 | 2019-01-04 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-06-10 | COMP | 2019-07-16 | COMP | Rule 16 | 21 | 60 | 13 | 1 | 97 | 26 | 214
7308 | 2018-09-07 | 2018-10-06 | 2018-12-12 | 2018-12-12 | COMP | 2019-01-31 | COMP | 2019-03-14 | COMP | 2019-02-20 | COMP | 2019-04-20 | COMP | Rule 16 | 21 | 45 | 34 | 30 | 0 | 27 | 154
7359 | 2018-09-07 | 2018-10-09 | 2019-01-01 | 2019-01-01 | COMP | 2019-02-07 | COMP | 2019-04-30 | COMP | 2019-08-19 | COMP | 2019-09-13 | COMP | Rule 16 | 23 | 56 | 26 | 58 | 78 | 19 | 256
7441 | 2018-09-07 | 2018-10-12 | 2018-12-11 | 2018-12-11 | COMP | 2018-12-26 | COMP | 2018-12-26 | COMP | 2019-02-07 | COMP | 2019-03-03 | COMP | Rule 16 | 26 | 40 | 11 | 1 | 30 | 16 | 119
7460 | 2018-09-07 | 2018-10-16 | 2019-04-20 | 2019-04-20 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-10-03 | COMP | 2019-12-05 | COMP | Rule 15/16 | 28 | 127 | 49 | 1 | 68 | 43 | 312
7485 | 2018-09-07 | 2018-10-16 | 2018-12-11 | 2018-12-11 | COMP | 2019-01-03 | COMP | 2019-03-19 | COMP | 2019-09-02 | INPR | 2019-04-22 | COMP | Rule 16 | 28 | 38 | 16 | 52 |  |  | 155
7504 | 2018-09-07 | 2018-10-17 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-01-15 | COMP | 2019-03-07 | COMP | Rule 16 | 29 | 29 | 15 | 1 | 18 | 36 | 123
8152 | 2018-09-07 | 2018-11-17 | 2019-03-01 | 2019-03-01 | COMP | 2019-04-26 | COMP | 2019-05-16 | COMP | 2019-08-08 | COMP | 2019-08-29 | COMP | Rule 16 | 50 | 69 | 41 | 15 | 59 | 16 | 246
8183 | 2018-09-07 | 2018-11-18 | 2019-01-24 | 2019-04-23 | COMP | 2019-05-09 | COMP | 2019-07-01 | COMP | 2019-06-24 | COMP | 2019-07-30 | COMP | Rule 16 | 50 | 44 | 13 | 37 | 0 | 21 | 224
8391 | 2018-09-07 | 2018-11-29 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-07 | COMP | 2019-03-01 | COMP | 2019-02-28 | COMP | 2019-11-07 | COMP | Rule 16 | 57 | 40 | 9 | 16 | 0 | 177 | 295
8515 | 2018-09-07 | 2018-12-07 | 2019-02-06 | 2019-02-06 | COMP | 2019-04-15 | COMP | 2019-08-23 | COMP | 2019-08-07 | COMP | 2019-08-31 | COMP | Rule 16 | 63 | 41 | 48 | 93 | 0 | 6 | 247
9009 | 2018-09-07 | 2019-01-12 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-20 | COMP | 2019-05-02 | COMP | 2019-09-22 | INPR | 2019-06-13 | COMP | Rule 16 | 86 | 29 | 18 | 32 |  |  | 192
9332 | 2018-09-07 | 2019-01-30 | 2019-03-03 | 2019-03-03 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2020-10-13 | COMP | 2020-12-17 | COMP | Rule 16 | 98 | 22 | 21 | 1 | 390 | 45 | 573
9800 | 2018-09-07 | 2019-02-15 | 2019-09-17 | 2019-09-17 | COMP | 2019-11-07 | COMP | 2019-12-05 | COMP | 2020-06-19 | COMP | 2020-07-28 | COMP | Rule 16 | 110 | 149 | 38 | 18 | 137 | 28 | 475
9842 | 2018-09-07 | 2019-02-20 | 2019-05-13 | 2019-05-13 | COMP | 2019-07-03 | NOTN | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-09-11 | COMP | Other | 112 | 59 |  | 37 | 1 | 49 | 254
9891 | 2018-09-07 | 2019-02-21 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-09-25 | COMP | 2019-11-22 | COMP | Rule 16 | 113 | 103 | 7 | 1 | 44 | 42 | 305
10236 | 2018-09-07 | 2019-03-06 | 2019-05-13 | 2019-05-13 | COMP | 2019-09-26 | COMP | 2020-02-10 | COMP | 2020-01-06 | COMP | 2020-04-27 | COMP | Rule 16 | 122 | 49 | 96 | 92 | 0 | 55 | 410
10319 | 2018-09-07 | 2019-03-11 | 2019-07-18 | 2019-09-17 | COMP | 2019-10-10 | COMP | 2020-01-06 | COMP | 2020-02-18 | COMP | 2020-06-07 | COMP | Rule 16 | 125 | 92 | 18 | 58 | 30 | 78 | 438
10852 | 2018-09-07 | 2019-04-02 | 2019-09-15 | 2019-09-15 | COMP | 2019-10-16 | COMP | 2020-05-26 | COMP | 2020-07-17 | COMP | 2021-07-09 | COMP | Rule 16 | 141 | 116 | 23 | 152 | 39 | 246 | 713
12345 | 2018-09-07 | 2019-06-03 | 2019-07-12 | 2019-07-12 | COMP | 2019-09-11 | COMP | 2021-12-02 | COMP | 2021-11-09 | COMP | 2022-02-01 | COMP | Rule 16 | 184 | 29 | 43 | 560 | 0 | 43 | 855
12625 | 2018-09-07 | 2019-06-17 | 2019-09-16 | 2019-09-16 | COMP | 2019-10-14 | COMP | 2019-10-23 | COMP | 2019-11-21 | COMP | 2020-01-09 | COMP | Rule 16 | 194 | 64 | 21 | 8 | 21 | 32 | 335
7688 | 2018-09-08 | 2018-10-25 | 2019-01-28 | 2019-02-01 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-05-03 | COMP | Rule 16 | 34 | 62 | 7 | 1 | 1 | 59 | 163
13484 | 2018-09-08 | 2019-07-26 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-11-16 | COMP | 2020-01-06 | COMP | Rule 16 | 221 | 19 | 10 | 1 | 52 | 32 | 331
7804 | 2018-09-09 | 2018-11-01 | 2019-06-19 | 2019-06-19 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-10-23 | COMP | 2019-12-20 | COMP | Rule 16 | 39 | 157 | 88 | 1 | 2 | 40 | 322
8038 | 2018-09-09 | 2018-11-12 | 2018-12-24 | 2018-12-24 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-03-10 | COMP | 2019-04-18 | COMP | Rule 16 | 45 | 28 | 49 | 1 | 3 | 29 | 152
3899 | 2018-09-10 | 2018-09-27 | 2018-11-13 | 2018-11-13 | COMP | 2018-12-18 | COMP | 2019-01-07 | COMP | 2019-02-12 | COMP | 2019-02-26 | COMP | Rule 16 | 14 | 33 | 24 | 13 | 26 | 10 | 115
3984 | 2018-09-10 | 2018-11-09 | 2018-12-18 | 2018-12-18 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-11-23 | INPR | 2019-07-15 | COMP | Rule 16 | 45 | 25 | 26 | 1 |  |  | 212
4004 | 2018-09-10 | 2018-11-16 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-27 | COMP | 2019-03-06 | COMP | 2020-08-11 | COMP | 2020-09-14 | COMP | Rule 16 | 49 | 44 | 25 | 6 | 364 | 24 | 507
7095 | 2018-09-10 | 2018-09-26 | 2018-12-16 | 2018-12-16 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-04-01 | COMP | 2019-05-28 | COMP | Rule 16 | 13 | 55 | 67 | 1 | 6 | 41 | 179
7106 | 2018-09-10 | 2018-09-27 | 2018-12-12 | 2018-12-12 | COMP | 2019-01-09 | COMP | 2019-01-09 | COMP | 2019-04-29 | COMP | 2019-06-06 | COMP | Rule 16 | 14 | 52 | 19 | 1 | 77 | 28 | 186
7154 | 2018-09-10 | 2018-09-29 | 2018-12-07 | 2018-12-07 | COMP | 2019-01-09 | COMP | 2019-01-25 | COMP | 2019-02-01 | COMP | 2019-02-20 | COMP | Rule 16 | 15 | 47 | 22 | 12 | 6 | 13 | 111
7677 | 2018-09-10 | 2018-10-24 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-25 | COMP | 2019-02-25 | NOTN | 2019-03-28 | COMP | 2019-04-26 | COMP | Rule 16 | 33 | 67 | 16 |  |  |  | 158
7698 | 2018-09-10 | 2018-10-26 | 2019-02-25 | 2019-05-28 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2020-01-27 | COMP | 2020-02-13 | COMP | Rule 16 | 35 | 80 | 35 | 1 | 133 | 14 | 358
7809 | 2018-09-10 | 2018-11-02 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-04 | COMP | 2019-02-04 | COMP | 2019-04-08 | COMP | 2019-06-03 | COMP | Rule 16 | 40 | 58 | 4 | 1 | 45 | 40 | 183
7869 | 2018-09-10 | 2018-11-03 | 2019-01-08 | 2019-01-08 | COMP | 2019-01-15 | NOTN | 2019-01-15 | COMP | 2019-01-22 | NOTN | 2019-03-07 | COMP | Other | 40 | 42 |  | 6 |  |  | 122
7878 | 2018-09-10 | 2018-11-03 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-03-27 | COMP | 2019-06-25 | COMP | Rule 16 | 40 | 78 | 17 | 1 | 3 | 64 | 199
7893 | 2018-09-10 | 2018-11-04 | 2018-12-31 | 2018-12-31 | COMP | 2019-04-08 | COMP | 2019-06-25 | COMP | 2019-06-28 | COMP | 2019-07-03 | COMP | Rule 16 | 40 | 37 | 68 | 56 | 4 | 4 | 205
8147 | 2018-09-10 | 2018-11-17 | 2019-04-02 | 2019-04-02 | COMP | 2019-06-06 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-29 | COMP | Rule 15/16 | 49 | 91 | 47 | 3 | 1 | 35 | 222
8148 | 2018-09-10 | 2018-11-17 | 2019-03-29 | 2019-03-29 | COMP | 2019-10-08 | COMP | 2019-11-04 | COMP | 2019-10-09 | COMP | 2019-11-13 | COMP | Rule 16 | 49 | 89 | 135 | 20 | 0 | 7 | 297
8331 | 2018-09-10 | 2018-11-27 | 2019-03-11 | 2019-03-26 | COMP | 2019-05-09 | COMP | 2019-05-23 | COMP | 2019-09-04 | COMP | 2019-11-08 | COMP | Rule 15/16 | 54 | 71 | 33 | 11 | 72 | 48 | 295
9213 | 2018-09-10 | 2019-01-22 | 2019-01-31 | 2019-01-31 | COMP | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-05-22 | COMP | Rule 16 | 91 | 8 | 49 | 1 | 1 | 31 | 176
10065 | 2018-09-10 | 2019-02-28 | 2019-03-05 | 2019-04-15 | COMP | 2019-03-12 | COMP | 2019-05-13 | COMP | 2019-04-23 | COMP | 2019-08-02 | COMP | Rule 16 | 117 | 4 |  | 45 | 0 | 58 | 226
10287 | 2018-09-10 | 2019-03-09 | 2019-05-13 | 2019-12-30 | COMP | 2020-02-19 | COMP | 2020-02-25 | COMP | 2020-02-24 | COMP | 2020-03-25 | COMP | Rule 16 | 123 | 46 | 35 | 5 | 0 | 22 | 386
10688 | 2018-09-10 | 2019-03-26 | 2019-04-11 | 2019-04-11 | COMP | 2019-06-06 | COMP | 2019-06-24 | COMP | 2019-10-17 | COMP | 2019-10-21 | COMP | Rule 15/16 | 135 | 13 | 40 | 13 | 82 | 3 | 281
10779 | 2018-09-10 | 2019-03-29 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-26 | COMP | 2019-10-21 | COMP | 2020-03-04 | COMP | 2020-03-27 | COMP | Rule 16 | 138 | 105 | 23 | 18 | 91 | 18 | 388
10873 | 2018-09-10 | 2019-04-03 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-08 | COMP | 2019-08-12 | COMP | 2020-02-17 | COMP | 2020-03-30 | COMP | Rule 15/16 | 141 | 10 | 17 | 67 | 128 | 30 | 389
11069 | 2018-09-10 | 2019-04-11 | 2019-07-20 | 2019-07-20 | COMP | 2019-08-08 | COMP | 2019-08-08 | COMP | 2019-10-04 | COMP | 2019-10-23 | COMP | Rule 16 | 147 | 70 | 14 | 1 | 41 | 14 | 283
11337 | 2018-09-10 | 2019-04-23 | 2019-05-08 | 2019-05-08 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-08-01 | COMP | 2019-10-01 | COMP | Rule 16 | 155 | 12 | 78 | 1 | 0 | 25 | 267
12340 | 2018-09-10 | 2019-06-01 | 2019-07-24 | 2019-07-24 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-03-23 | COMP | 2020-06-01 | COMP | Rule 16 | 182 | 37 | 50 | 1 | 117 | 50 | 433
12357 | 2018-09-10 | 2019-06-03 | 2019-07-10 | 2019-07-10 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2021-03-27 | INPR | 2020-03-18 | COMP | Rule 16 | 183 | 27 | 43 | 1 |  |  | 381
14370 | 2018-09-10 | 2019-09-06 | 2019-11-26 | 2019-11-26 | COMP | 2021-07-07 | COMP | 2021-07-07 | COMP | 2022-01-18 | COMP | 2022-01-29 | COMP | Rule 16 | 250 | 57 | 405 | 1 | 135 | 9 | 852
6894 | 2018-09-11 | 2018-09-15 | 2019-03-26 | 2019-03-26 | COMP | 2019-06-25 | COMP | 2020-07-30 | COMP | 2020-06-16 | COMP | 2020-07-29 | COMP | Rule 15/16 | 4 | 130 | 65 | 278 | 0 |  | 474
6927 | 2018-09-11 | 2018-09-19 | 2019-03-24 | 2019-03-24 | COMP | 2019-07-18 | COMP | 2020-01-22 | COMP | 2020-11-18 | COMP | 2021-03-03 | COMP | Rule 15/16 | 7 | 126 | 82 | 128 | 212 | 70 | 621
7045 | 2018-09-11 | 2018-09-25 | 2020-01-29 | 2020-02-27 | COMP | 2020-06-22 | COMP | 2020-07-08 | COMP | 2020-08-14 | COMP | 2020-10-14 | COMP | Rule 15/16 | 11 | 336 | 82 | 13 | 28 | 43 | 528
7046 | 2018-09-11 | 2018-09-25 | 2019-08-09 | 2019-08-09 | COMP | 2020-06-08 | COMP | 2020-06-12 | COMP | 2020-08-14 | COMP | 2020-10-03 | COMP | Rule 15/16 | 11 | 220 | 208 | 5 | 46 | 35 | 520
7047 | 2018-09-11 | 2018-09-25 | 2019-07-23 | 2020-02-20 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-06-09 | COMP | 2020-07-25 | COMP | Rule 15/16 | 11 | 207 | 77 | 1 | 2 | 34 | 471
7104 | 2018-09-11 | 2018-09-27 | 2018-10-18 | 2018-10-19 | COMP | 2018-10-26 | COMP | 2018-10-26 | COMP | 2019-12-02 | COMP | 2019-12-18 | COMP | Rule 16 | 13 | 16 | 6 | 1 | 274 | 13 | 319
7168 | 2018-09-11 | 2018-10-01 | 2018-10-24 | 2018-10-24 | COMP | 2018-10-25 | NOTN | 2018-11-27 | COMP | 2019-01-28 | COMP | 2019-04-18 | COMP | Other | 15 | 18 |  | 22 | 42 | 58 | 151
7187 | 2018-09-11 | 2018-10-01 | 2019-02-22 | 2019-02-22 | COMP | 2019-06-21 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2020-01-30 | COMP | Rule 15/16 | 15 | 98 | 85 | 96 | 1 | 57 | 347
7269 | 2018-09-11 | 2018-10-04 | 2018-12-19 | 2018-12-19 | COMP | 2019-03-06 | COMP | 2019-04-05 | COMP | 2019-04-24 | COMP | 2019-05-20 | COMP | Rule 16 | 18 | 52 | 52 | 23 | 14 | 19 | 173
7297 | 2018-09-11 | 2018-10-06 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-21 | COMP | 2019-04-05 | COMP | 2019-03-26 | COMP | 2019-05-01 | COMP | Rule 16 | 19 | 74 | 19 | 32 | 0 | 19 | 160
7395 | 2018-09-11 | 2018-10-11 | 2019-03-15 | 2019-03-15 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-05-10 | COMP | 2019-08-04 | COMP | Rule 15/16 | 23 | 105 | 78 | 1 | 0 | 22 | 225
7435 | 2018-09-11 | 2018-10-12 | 2019-06-10 | 2019-06-10 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2020-02-29 | INPR | 2019-11-07 | COMP | Rule 16 | 24 | 164 | 74 | 1 |  |  | 293
7492 | 2018-09-11 | 2018-10-16 | 2018-11-26 | 2018-11-26 | COMP | 2019-02-05 | COMP | 2019-02-08 | COMP | 2019-03-01 | COMP | 2019-04-11 | COMP | Rule 16 | 26 | 27 | 49 | 4 | 15 | 30 | 146
7493 | 2018-09-11 | 2018-10-17 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-04-16 | COMP | 2019-06-10 | COMP | Rule 16 | 27 | 54 | 5 | 1 | 66 | 39 | 187
7798 | 2018-09-11 | 2018-10-31 | 2019-03-18 | 2019-03-18 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-04-09 | COMP | 2019-07-24 | COMP | Rule 16 | 37 | 92 | 6 | 1 | 12 | 75 | 218
7871 | 2018-09-11 | 2018-11-03 | 2018-11-20 | 2018-11-20 | COMP | 2018-12-12 | COMP | 2018-12-18 | COMP | 2018-12-17 | COMP | 2019-01-23 | COMP | Rule 16 | 39 | 11 | 15 | 5 | 0 | 24 | 91
7876 | 2018-09-11 | 2018-11-03 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-05-23 | COMP | 2019-06-18 | COMP | Rule 15/16 | 39 | 79 | 17 | 1 | 43 | 18 | 193
8117 | 2018-09-11 | 2018-11-15 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-04 | COMP | 2019-08-02 | COMP | 2023-04-30 | INPR | 2020-01-17 | COMP | Rule 15/16 | 47 | 45 | 9 | 127 |  |  | 339
8127 | 2018-09-11 | 2018-11-16 | 2019-05-30 | 2019-05-30 | COMP | 2019-10-04 | COMP | 2019-10-31 | COMP | 2019-12-03 | COMP | 2020-01-11 | COMP | Rule 15/16 | 48 | 133 | 90 | 20 | 21 | 27 | 334
8209 | 2018-09-11 | 2018-11-19 | 2019-01-31 | 2019-02-09 | COMP | 2019-02-27 | COMP | 2019-03-06 | COMP | 2019-03-13 | COMP | 2019-03-19 | COMP | Rule 16 | 49 | 49 | 12 | 6 | 6 | 5 | 129
8222 | 2018-09-11 | 2018-11-20 | 2019-02-12 | 2019-02-12 | COMP | 2019-01-07 | NOTN | 2019-02-12 | COMP | 2019-04-01 | COMP | 2019-04-08 | COMP | Other | 50 | 56 |  | 1 | 34 | 6 | 143
8285 | 2018-09-11 | 2018-11-26 | 2020-04-28 | 2022-01-25 | COMP | 2022-02-23 | COMP | 2022-12-06 | COMP | 2022-12-13 | COMP | 2023-02-09 | COMP | Rule 15/16 | 52 | 358 | 21 | 198 | 6 | 40 | 1109
8290 | 2018-09-11 | 2018-11-26 | 2018-12-20 | 2018-12-20 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2020-01-19 | INPR | 2019-10-03 | COMP | Rule 16 | 52 | 19 | 37 | 1 |  |  | 268
8614 | 2018-09-11 | 2018-12-12 | 2019-03-29 | 2019-03-29 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-11-18 | COMP | 2019-11-22 | COMP | Rule 16 | 64 | 74 | 95 | 1 | 69 | 5 | 303
8648 | 2018-09-11 | 2018-12-14 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-08-21 | COMP | 2019-09-26 | COMP | Rule 16 | 66 | 63 | 52 | 1 | 60 | 26 | 263
8882 | 2018-09-11 | 2019-01-03 | 2019-03-05 | 2019-09-30 | COMP | 2020-01-17 | COMP | 2020-01-27 | COMP | 2020-02-04 | COMP | 2020-08-14 | COMP | Rule 16 | 78 | 42 | 75 | 6 | 7 | 137 | 486
9372 | 2018-09-11 | 2019-02-01 | 2019-05-08 | 2019-05-08 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-08-06 | COMP | 2019-08-26 | COMP | Rule 16 | 98 | 68 | 30 | 1 | 34 | 15 | 241
9621 | 2018-09-11 | 2019-02-09 | 2019-04-20 | 2019-04-20 | COMP | 2019-06-07 | COMP | 2019-06-11 | COMP | 2019-06-27 | COMP | 2019-07-19 | COMP | Rule 16 | 103 | 49 | 34 | 3 | 13 | 16 | 215
10943 | 2018-09-11 | 2019-04-06 | 2019-09-23 | 2021-02-05 | COMP | 2021-07-13 | COMP | 2021-08-16 | COMP | 2022-08-23 | COMP | 2023-06-16 | COMP | Rule 16 | 142 | 118 | 110 | 25 | 258 | 205 | 1198
11367 | 2018-09-11 | 2019-04-25 | 2019-07-03 | 2019-07-03 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-09-26 | COMP | Rule 16 | 156 | 49 | 34 | 1 | 1 | 27 | 263
12113 | 2018-09-11 | 2019-05-23 | 2019-09-15 | 2019-10-01 | COMP | 2019-10-23 | COMP | 2019-10-31 | COMP | 2020-02-04 | COMP | 2020-03-18 | COMP | Rule 16 | 176 | 79 | 17 | 7 | 63 | 31 | 380
12135 | 2018-09-11 | 2019-05-24 | 2019-08-17 | 2019-08-17 | COMP | 2019-08-27 | COMP | 2020-06-17 | COMP | 2020-02-13 | COMP | 2020-07-14 | COMP | Rule 16 | 177 | 59 | 7 | 203 | 0 | 20 | 463
12446 | 2018-09-11 | 2019-06-07 | 2020-02-27 | 2020-02-27 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2021-03-10 | COMP | 2021-04-01 | COMP | Rule 16 | 186 | 181 | 126 | 1 | 136 | 17 | 642
20059 | 2018-09-11 | 2020-06-03 | 2020-07-21 | 2020-10-07 | COMP | 2021-08-16 | COMP | 2023-07-05 | COMP |  | INPR | 2023-09-16 | COMP | Rule 16 | 434 | 35 | 215 | 473 |  |  | 1260
3919 | 2018-09-12 | 2018-10-08 | 2018-11-14 | 2018-11-14 | COMP | 2018-11-29 | NOTN | 2018-12-05 | COMP | 2019-04-20 | INPR | 2019-01-22 | COMP | Other | 19 | 27 |  | 14 |  |  | 89
6913 | 2018-09-12 | 2018-09-17 | 2018-10-23 | 2018-10-23 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2019-04-19 | COMP | 2019-04-25 | COMP | Rule 16 | 4 | 27 | 23 | 1 | 100 | 5 | 155
6914 | 2018-09-12 | 2018-09-17 | 2018-10-23 | 2018-10-23 | COMP | 2019-01-30 | COMP | 2018-12-11 | COMP | 2019-04-19 | COMP | 2019-04-25 | COMP | Rule 16 | 4 | 27 | 66 |  | 90 | 5 | 155
6915 | 2018-09-12 | 2018-09-17 | 2018-10-23 | 2018-10-23 | COMP | 2018-12-12 | COMP | 2018-12-17 | COMP | 2019-03-18 | COMP | 2019-03-26 | COMP | Rule 16 | 4 | 27 | 34 | 4 | 62 | 7 | 133
6916 | 2018-09-12 | 2018-09-17 | 2018-10-23 | 2018-10-23 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2019-01-18 | COMP | 2019-02-04 | COMP | Rule 16 | 4 | 27 | 16 | 1 | 44 | 11 | 98
6917 | 2018-09-12 | 2018-09-17 | 2018-10-23 | 2018-10-23 | COMP | 2018-11-14 | COMP | 2018-11-14 | COMP | 2019-06-26 | COMP | 2019-04-04 | COMP | Rule 16 | 4 | 27 | 16 | 1 | 154 |  | 140
6968 | 2018-09-12 | 2018-09-19 | 2019-02-27 | 2019-04-26 | COMP | 2019-05-22 | COMP | 2019-03-25 | COMP | 2019-06-18 | COMP | 2019-07-10 | COMP | Rule 16 | 6 | 109 | 19 |  | 61 | 16 | 207
7017 | 2018-09-12 | 2018-09-23 | 2019-01-17 | 2019-01-17 | COMP | 2019-01-28 | COMP | 2019-04-12 | COMP | 2019-04-15 | COMP | 2019-05-16 | COMP | Rule 16 | 8 | 79 | 7 | 54 | 2 | 24 | 170
7124 | 2018-09-12 | 2018-09-28 | 2019-09-05 | 2019-11-21 | COMP | 2020-07-15 | COMP | 2021-02-25 | COMP | 2021-03-02 | COMP | 2021-03-17 | COMP | Rule 15/16 | 13 | 235 | 163 | 154 | 4 | 12 | 630
7288 | 2018-09-12 | 2018-10-05 | 2018-12-20 | 2019-01-09 | COMP | 2019-01-22 | COMP | 2019-03-05 | COMP | 2019-12-02 | COMP | 2020-01-24 | COMP | Rule 16 | 18 | 52 | 9 | 30 | 189 | 37 | 342
7498 | 2018-09-12 | 2018-10-16 | 2019-02-11 | 2019-02-11 | COMP | 2019-03-22 | COMP | 2019-06-21 | COMP | 2019-07-18 | COMP | 2019-08-30 | COMP | Rule 16 | 25 | 79 | 29 | 65 | 19 | 32 | 244
7649 | 2018-09-12 | 2018-10-24 | 2018-12-18 | 2019-03-12 | COMP | 2019-03-19 | COMP | 2019-01-28 | COMP | 2019-03-29 | COMP | 2019-05-16 | COMP | Rule 16 | 31 | 37 | 6 |  | 44 | 35 | 170
7704 | 2018-09-12 | 2018-10-26 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-13 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-04-15 | COMP | Rule 16 | 33 | 61 | 13 | 2 | 1 | 42 | 147
7767 | 2018-09-12 | 2018-10-30 | 2019-02-05 | 2019-02-05 | COMP | 2019-04-01 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-05-29 | COMP | Rule 16 | 35 | 65 | 39 | 2 | 1 | 41 | 178
7788 | 2018-09-12 | 2018-11-01 | 2019-07-02 | 2020-01-06 | COMP | 2020-12-04 | NOTN | 2021-03-03 | COMP | 2020-12-04 | COMP | 2021-03-25 | COMP | Rule 16 | 37 | 166 |  | 292 | 0 | 17 | 636
7883 | 2018-09-12 | 2018-11-03 | 2019-03-28 | 2019-03-28 | COMP | 2019-05-10 | COMP | 2019-05-25 | COMP | 2019-07-23 | COMP | 2019-07-24 | COMP | Rule 16 | 38 | 97 | 32 | 11 | 40 | 2 | 217
7934 | 2018-09-12 | 2018-11-06 | 2019-01-04 | 2019-01-04 | COMP | 2019-02-08 | COMP | 2019-09-10 | COMP | 2023-04-30 | INPR | 2020-01-08 | COMP | Rule 16 | 40 | 39 | 25 | 149 |  |  | 331
7983 | 2018-09-12 | 2018-11-08 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-11 | COMP | 2019-05-03 | COMP | 2019-06-10 | COMP | 2019-11-08 | COMP | Rule 16 | 42 | 100 | 5 | 17 | 26 | 108 | 293
8017 | 2018-09-12 | 2018-11-13 | 2019-09-10 | 2019-09-10 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-09-29 | COMP | 2021-01-07 | COMP | Rule 15/16 | 44 | 207 | 131 | 1 | 137 | 68 | 583
8121 | 2018-09-12 | 2018-11-15 | 2021-03-25 | 2021-03-25 | COMP | 2021-04-09 | COMP | 2021-07-08 | COMP | 2021-07-08 | COMP | 2021-11-30 | COMP | Rule 16 | 46 | 591 | 12 | 63 | 1 | 100 | 808
8282 | 2018-09-12 | 2018-11-26 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-30 | COMP | 2019-10-08 | COMP |  | INPR | 2020-01-23 | COMP | Rule 15/16 | 51 | 199 | 16 | 7 |  |  | 341
8700 | 2018-09-12 | 2018-12-18 | 2019-02-26 | 2019-02-26 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-07-19 | COMP | 2019-09-04 | COMP | Rule 16 | 67 | 47 | 65 | 1 | 38 | 33 | 246
8997 | 2018-09-12 | 2019-01-11 | 2019-04-24 | 2019-04-24 | COMP | 2019-04-30 | COMP | 2019-07-03 | COMP | 2019-06-18 | COMP | 2019-08-07 | COMP | Rule 16 | 83 | 72 | 5 | 46 | 0 | 25 | 227
9395 | 2018-09-12 | 2019-02-01 | 2019-04-29 | 2019-04-29 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-05-20 | COMP | 2019-05-25 | COMP | Rule 16 | 97 | 61 | 6 | 1 | 11 | 5 | 176
9421 | 2018-09-12 | 2019-02-04 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-03 | COMP | 2019-08-19 | COMP | 2019-06-17 | COMP | 2019-09-12 | COMP | Rule 16 | 98 | 51 | 14 | 75 | 0 | 18 | 252
9429 | 2018-09-12 | 2019-02-04 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-30 | COMP | 2019-11-19 | COMP | 2020-05-31 | INPR | 2020-01-17 | COMP | Rule 16 | 98 | 163 | 27 | 14 |  |  | 338
9450 | 2018-09-12 | 2019-02-04 | 2019-05-03 | 2020-09-23 | COMP | 2020-11-20 | COMP | 2019-07-15 | COMP | 2021-02-15 | COMP | 2021-03-16 | COMP | Rule 15/16 | 98 | 64 | 42 |  | 399 | 21 | 629
9528 | 2018-09-12 | 2019-02-06 | 2019-07-11 | 2019-07-11 | COMP | 2021-03-12 | COMP | 2021-11-15 | COMP | 2021-10-11 | NOTN | 2021-12-02 | COMP | Rule 16 | 100 | 109 | 420 | 173 |  |  | 810
9723 | 2018-09-12 | 2019-02-12 | 2019-06-04 | 2019-06-04 | COMP | 2019-06-27 | COMP | 2019-08-15 | INPR | 2020-08-29 | REQD | 2019-08-13 | COMP | Rule 15/16 | 104 | 79 | 18 |  |  |  | 231
9804 | 2018-09-12 | 2019-02-15 | 2019-04-20 | 2019-04-20 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-10-23 | COMP | 2019-12-20 | COMP | Rule 16 | 107 | 45 | 97 | 1 | 34 | 40 | 320
10044 | 2018-09-12 | 2019-02-28 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-28 | COMP | 2020-02-27 | COMP | 2020-06-08 | COMP | 2020-06-26 | COMP | Rule 15/16 | 115 | 47 | 17 | 189 | 72 | 15 | 450
11071 | 2018-09-12 | 2019-04-11 | 2019-06-20 | 2019-06-20 | COMP | 2019-08-24 | NOTN | 2019-09-11 | COMP | 2019-10-09 | COMP | 2019-11-14 | COMP | Other | 145 | 50 |  | 58 | 21 | 26 | 296
11491 | 2018-09-12 | 2019-04-30 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-31 | COMP | 2020-01-29 | COMP | 2020-02-18 | COMP | 2020-03-25 | COMP | Rule 16 | 158 | 110 | 21 | 59 | 14 | 27 | 384
13439 | 2018-09-12 | 2019-07-25 | 2019-10-02 | 2019-10-02 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-05-01 | COMP | 2020-05-26 | COMP | Other | 218 | 49 | 104 | 1 | 43 | 17 | 427
15699 | 2018-09-12 | 2019-11-17 | 2020-01-23 | 2020-01-23 | COMP | 2020-01-28 | COMP | 2020-01-28 | INPR | 2020-02-14 | COMP | 2020-02-20 | COMP | Rule 16 | 297 | 44 | 4 |  |  |  | 360
20768 | 2018-09-12 | 2020-07-07 | 2020-07-27 | 2021-02-02 | COMP | 2021-02-17 | COMP | 2021-02-17 | COMP | 2021-02-18 | COMP | 2021-03-02 | COMP | Rule 16 | 457 | 15 | 11 | 1 | 2 | 9 | 619
3896 | 2018-09-13 | 2018-09-26 | 2018-12-21 | 2019-08-02 | COMP | 2019-09-11 | COMP | 2020-08-19 | COMP | 2020-09-04 | COMP | 2020-10-07 | COMP | Rule 15/16 | 10 | 60 | 28 | 238 | 13 | 23 | 521
7027 | 2018-09-13 | 2018-09-23 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-14 | NOTN | 2019-09-03 | COMP | 2019-03-01 | COMP | 2020-11-09 | COMP | Other | 7 | 97 |  | 141 | 0 | 301 | 544
7194 | 2018-09-13 | 2018-10-01 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-20 | COMP | 2019-05-21 | COMP | 2019-05-08 | COMP | 2019-08-01 | COMP | Rule 16 | 13 | 75 | 42 | 45 | 0 | 51 | 222
7203 | 2018-09-13 | 2018-10-02 | 2018-12-17 | 2018-12-17 | COMP | 2019-01-09 | COMP | 2019-07-15 | COMP | 2019-07-13 | COMP | 2019-08-06 | COMP | Rule 15/16 | 14 | 52 | 16 | 130 | 0 | 17 | 225
7283 | 2018-09-13 | 2018-10-05 | 2019-01-12 | 2019-01-12 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-02-11 | COMP | 2019-03-03 | COMP | Rule 16 | 17 | 66 | 10 | 1 | 11 | 14 | 115
7293 | 2018-09-13 | 2018-10-06 | 2018-12-19 | 2018-12-19 | COMP | 2019-01-02 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-03-16 | COMP | Rule 16 | 17 | 50 | 9 | 29 | 1 | 23 | 125
7339 | 2018-09-13 | 2018-10-08 | 2018-11-11 | 2018-11-11 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-04-18 | COMP | 2019-06-27 | COMP | Rule 16 | 18 | 25 | 23 | 1 | 85 | 50 | 198
7401 | 2018-09-13 | 2018-10-11 | 2019-01-22 | 2019-01-22 | COMP | 2019-02-01 | COMP | 2019-04-09 | INPR | 2019-07-21 | REQD | 2019-02-28 | COMP | Rule 16 | 21 | 68 | 9 |  |  |  | 114
7559 | 2018-09-13 | 2018-10-19 | 2018-11-26 | 2018-11-26 | COMP | 2018-12-12 | COMP | 2019-03-12 | COMP | 2019-04-03 | COMP | 2019-04-24 | COMP | Rule 16 | 27 | 24 | 13 | 61 | 17 | 16 | 153
7620 | 2018-09-13 | 2018-10-23 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-18 | COMP | 2018-12-18 | COMP | 2019-05-07 | COMP | 2019-06-21 | COMP | Rule 16 | 29 | 34 | 5 | 1 | 97 | 33 | 194
7972 | 2018-09-13 | 2018-11-08 | 2019-03-05 | 2019-03-05 | COMP | 2019-04-11 | COMP | 2019-08-02 | COMP | 2019-12-28 | INPR | 2019-09-12 | COMP | Rule 16 | 41 | 77 | 28 | 80 |  |  | 251
8009 | 2018-09-13 | 2018-11-09 | 2019-01-08 | 2019-01-08 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-02-21 | COMP | 2019-03-21 | COMP | Rule 16 | 42 | 38 | 23 | 1 | 9 | 21 | 129
8091 | 2018-09-13 | 2018-11-16 | 2019-01-31 | 2019-02-20 | COMP | 2019-02-27 | COMP | 2019-09-22 | REQD | 2019-05-02 | COMP | 2019-06-04 | COMP | Rule 16 | 46 | 50 | 6 |  |  |  | 181
8446 | 2018-09-13 | 2018-12-03 | 2019-02-15 | 2019-02-15 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-05-13 | COMP | 2019-06-25 | COMP | Rule 16 | 55 | 52 | 59 | 1 | 3 | 31 | 196
8991 | 2018-09-13 | 2019-01-10 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-11 | COMP | 2019-03-08 | COMP | 2019-10-21 | INPR | 2019-03-18 | COMP | Rule 16 | 81 | 14 | 9 | 19 |  |  | 126
9024 | 2018-09-13 | 2019-01-13 | 2019-03-15 | 2019-03-22 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-05-20 | COMP | 2019-06-20 | COMP | Rule 15/16 | 82 | 43 | 19 | 1 | 24 | 23 | 193
9231 | 2018-09-13 | 2019-01-23 | 2019-05-15 | 2019-05-15 | COMP | 2019-07-12 | COMP | 2019-10-09 | COMP | 2019-12-02 | COMP | 2019-12-12 | COMP | Rule 16 | 89 | 80 | 41 | 63 | 36 | 9 | 313
9603 | 2018-09-13 | 2019-02-08 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-29 | COMP | 2019-05-31 | COMP | 2019-06-10 | COMP | 2019-08-01 | COMP | Rule 16 | 101 | 36 | 21 | 24 | 7 | 38 | 222
9671 | 2018-09-13 | 2019-02-11 | 2019-04-26 | 2019-04-26 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2020-01-22 | COMP | 2020-02-14 | COMP | Rule 16 | 102 | 54 | 71 | 1 | 115 | 18 | 356
10696 | 2018-09-13 | 2019-03-27 | 2019-05-30 | 2019-05-30 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2022-07-06 | COMP | 2022-08-12 | COMP | Rule 16 | 133 | 46 | 72 | 1 | 710 | 28 | 985
11009 | 2018-09-13 | 2019-04-09 | 2019-10-01 | 2021-01-07 | COMP | 2021-03-02 | COMP | 2020-03-31 | COMP | 2021-03-29 | COMP | 2021-04-17 | COMP | Rule 16 | 142 | 123 | 37 |  | 251 | 15 | 651
11329 | 2018-09-13 | 2019-04-23 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-07-15 | COMP | 2019-08-07 | COMP | Rule 16 | 152 | 49 | 9 | 1 | 2 | 18 | 226
11435 | 2018-09-13 | 2019-04-26 | 2019-12-05 | 2019-12-05 | COMP | 2019-12-17 | COMP | 2019-12-23 | COMP | 2020-01-28 | COMP | 2020-02-21 | COMP | Rule 16 | 155 | 154 | 9 | 5 | 24 | 18 | 360
11946 | 2018-09-13 | 2019-05-17 | 2019-09-01 | 2019-09-01 | COMP | 2019-10-08 | COMP | 2020-02-20 | COMP | 2020-03-10 | COMP | 2020-04-23 | COMP | Rule 15/16 | 170 | 74 | 26 | 91 | 14 | 33 | 404
12571 | 2018-09-13 | 2019-06-14 | 2019-07-11 | 2019-07-11 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-11-08 | COMP | 2019-11-25 | COMP | Rule 16 | 189 | 19 | 68 | 1 | 19 | 11 | 302
13789 | 2018-09-13 | 2019-08-09 | 2020-01-30 | 2020-01-30 | COMP | 2020-10-09 | COMP | 2021-12-07 | COMP | 2022-01-04 | COMP | 2022-04-13 | COMP | Rule 16 | 228 | 118 | 179 | 290 | 21 | 70 | 901
13828 | 2018-09-13 | 2019-08-12 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-30 | COMP | 2020-02-11 | COMP | 2022-03-15 | COMP | 2022-05-12 | COMP | Other | 229 | 38 | 20 | 69 | 528 | 43 | 922
14088 | 2018-09-13 | 2019-08-23 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2019-12-17 | COMP | 2020-02-05 | COMP | Rule 16 | 238 | 56 | 14 | 1 | 11 | 34 | 349
14353 | 2018-09-13 | 2019-09-05 | 2019-10-19 | 2019-10-19 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2019-12-31 | COMP | 2020-01-15 | COMP | Rule 16 | 246 | 32 | 23 | 1 | 26 | 11 | 335
40208 | 2018-09-13 | 2022-12-12 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-15 | NOTN | 2023-11-03 | COMP | 2023-09-19 | COMP | 2023-10-13 | COMP | Other | 1067 | 159 |  | 69 | 0 |  | 1278
7149 | 2018-09-14 | 2018-09-28 | 2019-01-04 | 2019-04-08 | COMP | 2019-01-04 | NOTN | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-07-31 | COMP | Other | 11 | 66 |  | 1 | 1 | 81 | 220
7240 | 2018-09-14 | 2018-10-04 | 2018-11-21 | 2019-01-30 | COMP | 2019-03-04 | COMP | 2020-07-24 | COMP | 2020-07-07 | COMP | 2020-08-24 | COMP | Rule 16 | 15 | 34 | 23 | 354 | 0 | 22 | 489
7286 | 2018-09-14 | 2018-10-05 | 2018-12-04 | 2018-12-11 | COMP | 2019-02-12 | COMP | 2019-02-15 | COMP | 2019-02-21 | COMP | 2019-04-12 | COMP | Rule 16 | 16 | 40 | 43 | 4 | 4 | 37 | 144
7381 | 2018-09-14 | 2018-10-09 | 2019-01-12 | 2019-01-12 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-09-25 | COMP | 2019-11-05 | COMP | Rule 16 | 18 | 64 | 77 | 1 | 102 | 30 | 288
7530 | 2018-09-14 | 2018-10-18 | 2018-12-16 | 2019-01-10 | COMP | 2019-01-10 | NOTN | 2019-01-10 | COMP | 2018-12-24 | COMP | 2019-06-25 | COMP | Other | 25 | 39 |  | 1 | 0 | 116 | 195
7553 | 2018-09-14 | 2018-10-19 | 2018-12-21 | 2018-12-21 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2021-05-04 | COMP | 2021-06-03 | COMP | Rule 15/16 | 26 | 43 | 44 | 1 | 552 | 22 | 683
7563 | 2018-09-14 | 2018-10-19 | 2018-12-18 | 2018-12-18 | COMP | 2019-03-20 | COMP | 2019-07-26 | COMP | 2019-11-14 | COMP | 2019-12-16 | COMP | Rule 16 | 26 | 40 | 63 | 91 | 78 | 21 | 314
7628 | 2018-09-14 | 2018-10-23 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-15 | COMP | 2019-01-16 | COMP | 2019-05-15 | COMP | 2019-06-03 | COMP | Rule 15/16 | 28 | 42 | 15 | 2 | 84 | 13 | 179
7712 | 2018-09-14 | 2018-10-27 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-25 | COMP | 2019-04-26 | COMP | 2019-10-21 | INPR | 2019-06-08 | COMP | Rule 16 | 31 | 108 | 15 | 2 |  |  | 183
7874 | 2018-09-14 | 2018-11-02 | 2018-12-27 | 2019-03-15 | COMP | 2019-04-24 | COMP | 2019-09-30 | COMP | 2019-09-13 | COMP | 2019-10-17 | COMP | Rule 16 | 36 | 36 | 29 | 111 | 0 | 14 | 275
7933 | 2018-09-14 | 2018-11-05 | 2019-03-07 | 2019-03-07 | COMP | 2019-08-02 | COMP | 2019-08-06 | COMP | 2020-05-12 | COMP | 2020-07-11 | COMP | Rule 16 | 37 | 82 | 105 | 3 | 193 | 43 | 458
8025 | 2018-09-14 | 2018-11-14 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-10 | COMP | 2019-05-15 | COMP | 2019-05-10 | COMP | 2019-07-09 | COMP | Rule 16 | 43 | 116 | 7 | 4 | 0 | 38 | 204
8035 | 2018-09-14 | 2018-11-12 | 2019-01-22 | 2019-01-22 | COMP | 2019-03-05 | COMP | 2019-04-09 | COMP | 2019-07-29 | COMP | 2019-07-30 | COMP | Rule 16 | 41 | 46 | 30 | 26 | 78 | 2 | 219
8037 | 2018-09-14 | 2018-11-12 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-12 | COMP | 2019-04-09 | COMP | 2019-10-21 | INPR | 2019-05-23 | COMP | Rule 16 | 41 | 67 | 14 | 21 |  |  | 173
8223 | 2018-09-14 | 2018-11-19 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-04-24 | COMP | 2019-06-11 | COMP | Rule 16 | 46 | 58 | 29 | 1 | 22 | 34 | 185
8513 | 2018-09-14 | 2018-12-06 | 2019-02-22 | 2019-02-22 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2020-06-25 | COMP | 2020-08-06 | COMP | Rule 16 | 57 | 53 | 83 | 1 | 257 | 31 | 477
8852 | 2018-09-14 | 2019-01-03 | 2019-02-20 | 2019-02-20 | COMP | 2019-03-12 | NOTN | 2019-04-25 | COMP | 2019-02-27 | NOTN | 2019-06-26 | COMP | Other | 75 | 33 |  | 47 |  |  | 196
9348 | 2018-09-14 | 2019-01-31 | 2019-02-07 | 2019-02-07 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2020-01-15 | COMP | 2020-01-20 | COMP | Rule 16 | 94 | 6 | 8 | 1 | 229 | 3 | 336
9420 | 2018-09-14 | 2019-02-04 | 2019-03-25 | 2019-04-09 | COMP | 2019-05-17 | COMP | 2019-05-28 | COMP | 2021-01-06 | COMP | 2021-02-09 | COMP | Rule 16 | 96 | 35 | 29 | 7 | 406 | 24 | 603
9476 | 2018-09-14 | 2019-02-06 | 2019-06-07 | 2019-06-07 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-10-22 | COMP | 2019-11-10 | COMP | Rule 16 | 98 | 86 | 76 | 1 | 21 | 14 | 291
9626 | 2018-09-14 | 2019-02-09 | 2019-04-26 | 2019-04-26 | COMP | 2019-11-04 | COMP | 2019-12-09 | COMP | 2019-11-05 | COMP | 2020-01-11 | COMP | Rule 16 | 100 | 54 | 134 | 23 | 0 | 23 | 331
9751 | 2018-09-14 | 2019-02-13 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-20 | COMP | 2019-12-02 | COMP | 2019-12-03 | COMP | 2020-01-02 | COMP | Rule 16 | 103 | 150 | 5 | 49 | 2 | 21 | 325
9883 | 2018-09-14 | 2019-02-21 | 2019-12-20 | 2020-05-20 | COMP | 2020-09-08 | COMP | 2020-12-22 | COMP | 2021-03-05 | COMP | 2021-04-17 | COMP | Rule 16 | 108 | 211 | 78 | 73 | 50 | 31 | 650
10021 | 2018-09-14 | 2019-02-27 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-19 | COMP | 2020-01-06 | COMP | 2021-03-30 | COMP | 2020-03-26 | COMP | Rule 15/16 | 112 | 134 | 11 | 73 | 311 |  | 383
10058 | 2018-09-14 | 2019-02-28 | 2019-06-25 | 2019-08-15 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-01-13 | COMP | 2020-02-14 | COMP | Rule 15/16 | 113 | 83 | 47 | 1 | 56 | 24 | 355
10059 | 2018-09-14 | 2019-02-28 | 2019-07-15 | 2019-07-15 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-11-06 | COMP | 2020-07-15 | COMP | Rule 15/16 | 113 | 96 | 70 | 1 | 13 | 173 | 461
10061 | 2018-09-14 | 2019-02-28 | 2019-04-29 | 2019-04-29 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-12-09 | COMP | 2020-02-14 | COMP | Rule 15/16 | 113 | 43 | 125 | 1 | 31 | 47 | 355
10091 | 2018-09-14 | 2019-03-01 | 2019-05-10 | 2019-05-10 | COMP | 2020-03-25 | COMP | 2020-04-06 | COMP | 2020-05-19 | COMP | 2020-08-10 | COMP | Rule 16 | 114 | 51 | 219 | 9 | 32 | 59 | 479
10588 | 2018-09-14 | 2019-03-23 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-06-05 | COMP | 2019-06-15 | COMP | Rule 16 | 129 | 22 | 14 | 1 | 18 | 8 | 188
10736 | 2018-09-14 | 2019-03-28 | 2019-07-15 | 2019-07-17 | COMP | 2019-08-06 | COMP | 2019-08-13 | COMP | 2019-09-03 | COMP | 2019-09-19 | COMP | Rule 16 | 133 | 76 | 15 | 6 | 15 | 13 | 255
10897 | 2018-09-14 | 2019-04-03 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-25 | COMP | 2019-08-30 | COMP | 2019-08-23 | COMP | 2019-09-25 | COMP | Rule 16 | 137 | 45 | 36 | 27 | 0 | 18 | 259
11106 | 2018-09-14 | 2019-04-12 | 2019-08-22 | 2019-08-22 | COMP | 2019-10-07 | COMP | 2019-12-07 | COMP | 2019-10-28 | COMP | 2020-01-06 | COMP | Rule 16 | 144 | 93 | 32 | 42 | 0 | 19 | 327
12489 | 2018-09-14 | 2019-06-10 | 2019-09-13 | 2019-09-13 | COMP | 2019-10-21 | NOTN | 2019-10-21 | COMP | 2019-12-31 | COMP | 2020-01-28 | COMP | Rule 16 | 184 | 68 |  | 27 | 48 | 19 | 342
13778 | 2018-09-14 | 2019-08-09 | 2019-11-08 | 2019-11-20 | COMP | 2020-01-06 | COMP | 2020-01-09 | COMP | 2020-05-26 | COMP | 2020-07-08 | COMP | Rule 15/16 | 227 | 65 | 30 | 4 | 96 | 32 | 456
6951 | 2018-09-15 | 2018-09-18 | 2019-01-07 | 2019-01-07 | COMP | 2019-03-19 | COMP | 2019-03-20 | COMP | 2019-03-23 | COMP | 2019-05-09 | COMP | Rule 16 | 2 | 75 | 50 | 2 | 3 | 34 | 162
7818 | 2018-09-16 | 2018-11-02 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-07-25 | COMP | 2019-08-02 | COMP | Rule 16 | 35 | 17 | 9 | 1 | 157 | 7 | 221
8293 | 2018-09-16 | 2018-11-26 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-19 | COMP | 2019-04-09 | COMP | 2019-02-04 | COMP | 2019-07-16 | COMP | Rule 16 | 48 | 43 | 36 | 16 | 0 | 69 | 208
9823 | 2018-09-16 | 2019-02-19 | 2019-04-20 | 2019-04-20 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-10-04 | COMP | 2019-11-05 | COMP | Rule 16 | 105 | 44 | 103 | 1 | 15 | 23 | 287
11808 | 2018-09-16 | 2019-05-13 | 2019-06-01 | 2019-06-01 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2020-02-07 | COMP | 2020-02-18 | COMP | Rule 16 | 164 | 14 | 81 | 1 | 92 | 7 | 355
4011 | 2018-09-17 | 2018-11-28 | 2019-01-15 | 2019-01-15 | COMP | 2019-05-01 | COMP | 2019-05-02 | COMP | 2020-09-26 | INPR | 2019-09-11 | COMP | Rule 15/16 | 50 | 33 | 75 | 2 |  |  | 248
4092 | 2018-09-17 | 2019-01-25 | 2019-10-09 | 2019-10-09 | COMP | 2020-01-06 | COMP | 2021-01-21 | COMP | 2021-01-04 | COMP | 2021-04-05 | COMP | Rule 15/16 | 89 | 180 | 59 | 264 | 0 | 52 | 640
7137 | 2018-09-17 | 2018-09-28 | 2018-10-29 | 2018-11-14 | COMP | 2018-11-20 | COMP | 2018-11-20 | COMP | 2018-11-30 | COMP | 2019-02-01 | COMP | Rule 16 | 10 | 22 | 5 | 1 | 7 | 43 | 94
7145 | 2018-09-17 | 2018-09-28 | 2019-01-19 | 2019-02-11 | COMP | 2019-03-20 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-08 | COMP | Other | 10 | 76 | 27 | 11 | 1 | 4 | 139
7249 | 2018-09-17 | 2018-10-04 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-06-21 | COMP | 2019-08-12 | COMP | Rule 16 | 14 | 97 | 8 | 1 | 76 | 36 | 227
7251 | 2018-09-17 | 2018-10-04 | 2019-01-01 | 2019-04-08 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-06-20 | COMP | 2019-07-01 | COMP | Rule 16 | 14 | 59 | 7 | 1 | 47 | 8 | 198
7263 | 2018-09-17 | 2018-10-04 | 2019-01-01 | 2019-01-01 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2021-06-18 | COMP | 2021-07-29 | COMP | Rule 16 | 14 | 59 | 93 | 1 | 529 | 29 | 721
7338 | 2018-09-17 | 2018-10-08 | 2019-01-30 | 2019-01-30 | COMP | 2019-03-14 | COMP | 2019-04-11 | COMP | 2019-03-16 | COMP | 2019-05-08 | COMP | Rule 16 | 16 | 77 | 31 | 21 | 0 | 20 | 161
7487 | 2018-09-17 | 2018-10-17 | 2019-01-18 | 2020-06-17 | COMP | 2020-07-02 | COMP | 2021-04-15 | COMP | 2021-04-12 | COMP | 2021-05-18 | COMP | Rule 16 | 23 | 63 | 12 | 198 | 0 | 24 | 671
7612 | 2018-09-17 | 2018-10-23 | 2019-02-23 | 2019-02-23 | COMP | 2019-02-25 | NOTN | 2019-02-25 | COMP | 2019-03-21 | COMP | 2019-03-25 | COMP | Other | 27 | 82 |  | 1 | 19 | 3 | 129
7732 | 2018-09-17 | 2018-10-27 | 2018-12-21 | 2018-12-21 | COMP | 2020-03-02 | COMP | 2020-03-31 | COMP | 2022-07-16 | INPR | 2020-09-11 | COMP | Rule 16 | 30 | 37 | 298 | 22 |  |  | 501
7975 | 2018-09-17 | 2018-11-08 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-05-13 | COMP | 2019-07-10 | COMP | Rule 15/16 | 39 | 104 | 10 | 1 | 14 | 41 | 204
8225 | 2018-09-17 | 2018-11-19 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-01 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-07-10 | COMP | Rule 16 | 45 | 58 | 33 | 2 | 1 | 70 | 204
8226 | 2018-09-17 | 2018-11-19 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-04-04 | COMP | 2019-07-01 | COMP | Rule 16 | 45 | 58 | 34 | 1 | 3 | 62 | 198
8311 | 2018-09-17 | 2018-11-26 | 2019-01-30 | 2019-02-21 | COMP | 2019-05-13 | COMP | 2020-02-21 | COMP | 2020-03-23 | COMP | 2020-05-14 | COMP | Rule 16 | 48 | 45 | 58 | 195 | 22 | 39 | 417
8314 | 2018-09-17 | 2018-11-27 | 2019-02-27 | 2019-02-27 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-11-13 | COMP | Rule 16 | 49 | 63 | 158 | 1 | 1 | 25 | 292
8315 | 2018-09-17 | 2018-11-27 | 2019-01-25 | 2019-01-25 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2020-07-14 | COMP | 2020-08-03 | COMP | Rule 16 | 49 | 41 | 95 | 1 | 277 | 15 | 473
8363 | 2018-09-17 | 2018-11-28 | 2019-01-28 | 2019-01-28 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2019-04-12 | COMP | 2019-04-26 | COMP | Rule 16 | 50 | 41 | 48 | 1 | 7 | 11 | 153
8477 | 2018-09-17 | 2018-12-04 | 2019-02-23 | 2019-02-26 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-10-21 | INPR | 2019-03-22 | COMP | Rule 16 | 54 | 55 | 9 | 1 |  |  | 128
8490 | 2018-09-17 | 2018-12-05 | 2019-03-20 | 2019-03-20 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-08-21 | COMP | 2019-12-06 | COMP | Rule 16 | 55 | 72 | 37 | 1 | 73 | 74 | 307
8623 | 2018-09-17 | 2018-12-12 | 2019-04-01 | 2019-08-26 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-07 | COMP | 2020-06-25 | COMP | Rule 15/16 | 60 | 75 | 51 | 1 | 3 | 158 | 446
8762 | 2018-09-17 | 2018-12-22 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-20 | COMP | 2019-06-07 | COMP | 2019-07-02 | COMP | 2019-08-01 | COMP | Rule 16 | 67 | 30 | 10 | 77 | 18 | 22 | 220
8795 | 2018-09-17 | 2018-12-27 | 2019-04-05 | 2019-04-05 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-09-10 | COMP | 2019-09-12 | COMP | Rule 16 | 70 | 69 | 37 | 1 | 74 | 3 | 249
8981 | 2018-09-17 | 2019-01-10 | 2019-02-15 | 2019-05-24 | COMP | 2019-06-14 | COMP | 2019-06-25 | INPR | 2021-02-27 | REQD | 2019-08-29 | COMP | Rule 16 | 79 | 26 | 15 |  |  |  | 240
9048 | 2018-09-17 | 2019-01-14 | 2019-04-17 | 2019-04-17 | COMP | 2019-04-22 | COMP | 2019-04-23 | COMP | 2019-12-29 | INPR | 2019-07-22 | COMP | Rule 16 | 81 | 66 | 4 | 2 |  |  | 212
9186 | 2018-09-17 | 2019-01-20 | 2019-03-05 | 2019-03-05 | COMP | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-04-04 | COMP | 2019-04-29 | COMP | Rule 16 | 85 | 30 | 14 | 1 | 10 | 18 | 154
9458 | 2018-09-17 | 2019-02-05 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-04 | COMP | 2019-07-02 | COMP | Rule 16 | 96 | 58 | 18 | 1 | 10 | 21 | 199
9651 | 2018-09-17 | 2019-02-10 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-31 | COMP | 2019-09-14 | COMP | 2019-09-09 | COMP | 2019-10-01 | COMP | Rule 16 | 99 | 81 | 40 | 32 | 0 | 12 | 262
9679 | 2018-09-17 | 2019-02-12 | 2019-06-24 | 2019-08-15 | COMP | 2019-09-20 | COMP | 2019-11-04 | COMP | 2019-10-17 | COMP | 2020-02-25 | COMP | Rule 16 | 101 | 93 | 26 | 32 | 0 | 75 | 360
9974 | 2018-09-17 | 2019-02-27 | 2019-05-25 | 2019-05-25 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-10-23 | COMP | 2019-11-12 | COMP | Rule 16 | 111 | 63 | 103 | 1 | 3 | 14 | 291
10302 | 2018-09-17 | 2019-03-11 | 2019-04-20 | 2019-04-20 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-07-31 | COMP | 2019-09-13 | COMP | Rule 16 | 119 | 30 | 46 | 1 | 26 | 32 | 250
10544 | 2018-09-17 | 2019-03-20 | 2019-06-13 | 2019-06-13 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-08-07 | COMP | Rule 16 | 126 | 61 | 31 | 1 | 1 | 9 | 224
10611 | 2018-09-17 | 2019-03-22 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-04-30 | COMP | 2019-05-13 | COMP | Rule 16 | 128 | 3 | 20 | 1 | 7 | 10 | 164
11758 | 2018-09-17 | 2019-05-09 | 2019-08-28 | 2019-08-28 | COMP | 2020-02-07 | COMP | 2020-02-21 | COMP | 2020-02-24 | COMP | 2020-04-04 | COMP | Rule 15/16 | 162 | 78 | 111 | 10 | 2 | 30 | 388
12806 | 2018-09-17 | 2019-06-24 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-20 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-10-14 | COMP | Rule 16 | 193 | 51 | 13 | 2 | 1 | 16 | 271
13387 | 2018-09-17 | 2019-07-23 | 2019-11-20 | 2019-11-25 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2019-11-25 | COMP | 2020-01-17 | COMP | Rule 16 | 213 | 85 | 8 | 1 | 0 | 29 | 335
16283 | 2018-09-17 | 2019-12-19 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2021-05-13 | COMP | 2021-05-25 | COMP | Rule 16 | 316 | 117 | 16 | 1 | 222 | 9 | 676
4040 | 2018-09-18 | 2018-12-26 | 2019-12-10 | 2019-12-10 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2023-04-29 | CANC | 2021-09-15 | COMP | Rule 16 | 68 | 241 | 53 | 1 |  |  | 753
4042 | 2018-09-18 | 2018-12-27 | 2019-09-16 | 2019-09-16 | COMP | 2019-10-22 | COMP | 2021-06-04 | COMP | 2022-02-14 | COMP | 2021-06-22 | COMP | Rule 16 | 69 | 182 | 27 | 407 | 176 |  | 694
7184 | 2018-09-18 | 2018-10-02 | 2019-01-05 | 2019-01-05 | COMP | 2019-01-25 | COMP | 2019-01-31 | COMP | 2019-01-15 | COMP | 2019-03-05 | COMP | Rule 16 | 11 | 64 | 14 | 5 | 0 | 23 | 114
7252 | 2018-09-18 | 2018-10-04 | 2019-01-16 | 2019-01-16 | COMP | 2019-01-23 | COMP | 2019-03-21 | COMP | 2019-01-16 | COMP | 2019-04-26 | COMP | Rule 16 | 13 | 70 | 5 | 41 | 0 | 27 | 152
7253 | 2018-09-18 | 2018-10-04 | 2019-01-28 | 2019-04-05 | COMP | 2019-05-10 | COMP | 2019-07-09 | COMP | 2019-06-20 | COMP | 2019-07-29 | COMP | Rule 16 | 13 | 77 | 26 | 41 | 0 | 15 | 216
7275 | 2018-09-18 | 2018-10-04 | 2018-11-29 | 2018-11-29 | COMP | 2018-12-19 | COMP | 2018-12-19 | COMP | 2019-01-04 | COMP | 2019-02-20 | COMP | Rule 16 | 13 | 38 | 15 | 1 | 11 | 32 | 105
7320 | 2018-09-18 | 2018-10-08 | 2018-12-05 | 2018-12-05 | COMP | 2019-02-01 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-07-25 | COMP | Rule 16 | 15 | 40 | 40 | 107 | 1 | 16 | 214
7343 | 2018-09-18 | 2018-10-09 | 2018-11-16 | 2018-11-30 | COMP | 2018-12-12 | COMP | 2019-02-04 | COMP | 2018-11-24 | COMP | 2019-04-30 | COMP | Rule 16 | 16 | 28 | 9 | 36 | 0 | 61 | 154
7369 | 2018-09-18 | 2018-10-11 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-12-28 | INPR | 2019-07-15 | COMP | Rule 16 | 18 | 83 | 8 | 1 |  |  | 206
7785 | 2018-09-18 | 2018-10-31 | 2019-10-06 | 2019-10-06 | COMP | 2020-01-10 | COMP | 2020-01-29 | COMP | 2020-01-03 | COMP | 2020-02-20 | COMP | Rule 15/16 | 32 | 233 | 65 | 13 | 0 | 16 | 356
7787 | 2018-09-18 | 2018-11-01 | 2019-03-27 | 2019-03-27 | COMP | 2019-04-16 | COMP | 2019-05-29 | COMP | 2019-05-31 | COMP | 2019-07-03 | COMP | Rule 15/16 | 33 | 98 | 15 | 31 | 3 | 24 | 199
7855 | 2018-09-18 | 2018-11-02 | 2019-01-17 | 2019-01-17 | COMP | 2019-02-08 | COMP | 2019-02-28 | COMP | 2019-07-01 | COMP | 2019-07-03 | COMP | Rule 15/16 | 34 | 50 | 16 | 14 | 87 | 3 | 199
7873 | 2018-09-18 | 2018-11-02 | 2018-12-14 | 2018-12-14 | COMP | 2019-05-17 | COMP | 2019-06-14 | COMP | 2019-05-17 | COMP | 2019-06-28 | COMP | Rule 16 | 34 | 28 | 107 | 20 | 0 | 11 | 196
8019 | 2018-09-18 | 2018-11-09 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-08 | COMP | 2019-03-13 | COMP | 2019-03-19 | COMP | 2019-05-02 | COMP | Rule 16 | 39 | 74 | 6 | 4 | 5 | 33 | 156
8061 | 2018-09-18 | 2018-11-14 | 2019-08-20 | 2020-12-11 | COMP | 2021-01-19 | COMP | 2021-02-17 | COMP | 2021-03-05 | COMP | 2021-05-24 | COMP | Rule 15/16 | 41 | 192 | 25 | 21 | 13 | 57 | 674
8072 | 2018-09-18 | 2018-11-15 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-04-29 | COMP | 2019-08-01 | COMP | Rule 16 | 42 | 86 | 26 | 1 | 2 | 67 | 219
8170 | 2018-09-18 | 2018-11-16 | 2019-01-17 | 2019-01-17 | COMP | 2019-01-31 | COMP | 2019-03-15 | COMP | 2019-03-29 | COMP | 2019-05-07 | COMP | Rule 16 | 43 | 41 | 10 | 31 | 11 | 28 | 159
8279 | 2018-09-18 | 2018-11-26 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-19 | COMP | 2019-09-03 | COMP | 2020-03-24 | COMP | 2020-04-15 | COMP | Rule 15/16 | 47 | 179 | 7 | 11 | 139 | 17 | 395
8349 | 2018-09-18 | 2018-11-27 | 2019-02-14 | 2019-04-13 | COMP | 2019-05-22 | COMP | 2019-07-03 | COMP | 2023-11-11 | INPR | 2019-08-14 | COMP | Rule 16 | 48 | 55 | 28 | 30 |  |  | 228
8463 | 2018-09-18 | 2018-12-04 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-10 | COMP | 2019-04-16 | COMP | 2019-04-10 | COMP | 2019-05-13 | COMP | Other | 53 | 49 | 40 | 5 | 0 | 20 | 163
8669 | 2018-09-18 | 2018-12-14 | 2019-01-24 | 2019-07-25 | COMP | 2021-03-27 | INPR | 2019-08-06 | COMP | 2021-03-27 | INPR | 2020-02-27 | COMP | Rule 16 | 61 | 27 |  | 9 |  |  | 361
8791 | 2018-09-18 | 2018-12-27 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-22 | COMP | 2019-04-25 | COMP | 2020-04-26 | INPR | 2019-06-25 | COMP | Rule 16 | 69 | 35 | 25 | 25 |  |  | 193
9211 | 2018-09-18 | 2019-01-22 | 2019-04-19 | 2019-04-19 | COMP | 2019-08-16 | COMP | 2019-12-17 | COMP | 2020-10-09 | COMP | 2020-11-17 | COMP | Rule 16 | 85 | 63 | 84 | 84 | 208 | 27 | 546
10038 | 2018-09-18 | 2019-02-28 | 2019-04-08 | 2019-04-08 | COMP | 2019-06-12 | COMP | 2019-08-14 | COMP | 2019-10-04 | COMP | 2020-01-04 | COMP | Rule 16 | 111 | 28 | 47 | 45 | 37 | 61 | 324
10533 | 2018-09-18 | 2019-03-19 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-23 | COMP | 2019-12-04 | COMP | 2021-01-30 | INPR | 2019-12-30 | COMP | Rule 16 | 124 | 66 | 24 | 93 |  |  | 321
10671 | 2018-09-18 | 2019-03-25 | 2019-07-13 | 2019-07-13 | COMP | 2019-07-13 | NOTN | 2019-07-13 | COMP | 2019-07-23 | COMP | 2019-08-26 | COMP | Other | 128 | 78 |  | 0 | 7 | 25 | 236
10765 | 2018-09-18 | 2019-03-28 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-24 | COMP | 2019-08-06 | COMP | 2019-08-23 | COMP | 2019-09-09 | COMP | Rule 16 | 131 | 78 | 6 | 10 | 14 | 11 | 245
10946 | 2018-09-18 | 2019-04-05 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-15 | COMP | 2019-10-16 | COMP | 2019-08-20 | COMP | 2019-12-18 | COMP | Rule 16 | 137 | 67 | 27 | 44 | 0 | 43 | 314
11556 | 2018-09-18 | 2019-05-02 | 2019-06-04 | 2019-06-19 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | Rule 16 | 156 | 23 | 6 | 1 | 21 | 2 | 215
11700 | 2018-09-18 | 2019-05-08 | 2019-06-11 | 2019-06-11 | COMP | 2019-07-11 | NOTN | 2019-08-01 | COMP | 2019-07-11 | COMP | 2019-08-05 | COMP | Other | 160 | 24 |  | 37 | 0 | 3 | 221
11881 | 2018-09-18 | 2019-05-15 | 2020-06-12 | 2021-03-26 | COMP | 2021-09-24 | COMP | 2021-10-19 | COMP | 2022-11-14 | COMP | 2023-02-06 | COMP | Rule 15/16 | 165 | 272 | 128 | 18 | 270 | 56 | 1101
12634 | 2018-09-18 | 2019-06-17 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-10 | COMP | 2019-09-18 | COMP | 2019-09-24 | COMP | 2019-10-15 | COMP | Rule 16 | 187 | 56 | 5 | 7 | 5 | 16 | 271
15186 | 2018-09-18 | 2019-10-17 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-24 | NOTN | 2020-01-24 | COMP | 2021-02-27 | INPR | 2020-02-14 | COMP | Other | 273 | 57 |  | 10 |  |  | 353
24412 | 2018-09-18 | 2020-12-22 | 2021-08-20 | 2023-02-10 | COMP | 2023-02-21 | COMP | 2023-04-05 | COMP | 2023-02-27 | COMP | 2023-05-12 | COMP | Rule 16 | 569 | 168 | 7 | 32 | 0 | 28 | 1169
3932 | 2018-09-19 | 2018-10-22 | 2018-11-24 | 2018-11-24 | COMP | 2018-12-04 | COMP | 2019-10-10 | COMP |  |  | 2019-10-30 | COMP | Rule 16 | 24 | 22 | 7 | 216 |  |  | 281
3938 | 2018-09-19 | 2018-10-22 | 2018-12-12 | 2018-12-07 | COMP | 2019-01-28 | COMP | 2019-10-28 | COMP |  |  | 2019-11-13 | COMP | Rule 16 | 24 | 35 | 34 | 192 |  |  | 290
6958 | 2018-09-19 | 2018-09-19 | 2018-10-04 | 2018-10-04 | COMP | 2020-12-30 | COMP | 2021-01-23 | COMP | 2021-01-26 | COMP | 2021-03-13 | COMP | Rule 15/16 | 1 | 12 | 562 | 16 | 2 | 33 | 622
7070 | 2018-09-19 | 2018-09-25 | 2018-11-10 | 2019-04-17 | COMP | 2019-05-09 | COMP | 2019-12-05 | COMP | 2019-09-18 | COMP | 2020-01-15 | COMP | Rule 15/16 | 5 | 34 | 17 | 145 | 0 | 28 | 331
7173 | 2018-09-19 | 2018-10-01 | 2018-11-16 | 2018-11-16 | COMP | 2018-11-29 | COMP | 2018-11-29 | COMP | 2019-01-04 | COMP | 2019-01-29 | COMP | Rule 16 | 9 | 34 | 8 | 1 | 25 | 17 | 89
7417 | 2018-09-19 | 2018-10-12 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-01-16 | COMP | 2019-04-25 | COMP | Rule 16 | 18 | 59 | 10 | 1 | 0 | 66 | 150
7517 | 2018-09-19 | 2018-10-18 | 2018-12-12 | 2018-12-12 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-08-05 | COMP | 2019-07-30 | COMP | Rule 15/16 | 22 | 37 | 132 | 1 | 32 |  | 216
7531 | 2018-09-19 | 2018-10-18 | 2018-11-21 | 2018-11-21 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-03-06 | COMP | 2019-04-03 | COMP | Rule 16 | 22 | 24 | 24 | 1 | 47 | 21 | 134
7635 | 2018-09-19 | 2018-10-23 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-15 | COMP | 2019-03-01 | COMP | 2019-10-21 | INPR | 2019-03-19 | COMP | Rule 16 | 25 | 50 | 7 | 32 |  |  | 123
7641 | 2018-09-19 | 2018-10-23 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-11 | COMP | 2019-04-23 | COMP | 2019-04-10 | COMP | 2019-05-28 | COMP | Rule 16 | 25 | 63 | 12 | 51 | 0 | 25 | 172
7686 | 2018-09-19 | 2018-10-25 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2019-07-23 | COMP | 2019-08-26 | COMP | Rule 16 | 27 | 74 | 5 | 1 | 108 | 25 | 235
8099 | 2018-09-19 | 2018-11-15 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-07 | COMP | 2019-05-08 | COMP | 2019-05-29 | COMP | 2019-07-10 | COMP | Rule 15/16 | 41 | 87 | 32 | 2 | 15 | 30 | 202
8375 | 2018-09-19 | 2018-11-28 | 2019-08-22 | 2019-08-22 | COMP | 2019-10-01 | COMP | 2020-09-14 | COMP | 2020-09-01 | COMP | 2020-10-22 | COMP | Rule 16 | 48 | 186 | 28 | 241 | 0 | 29 | 528
8649 | 2018-09-19 | 2018-12-14 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-08-13 | COMP | 2019-08-21 | COMP | Rule 15/16 | 60 | 92 | 22 | 1 | 55 | 7 | 232
9245 | 2018-09-19 | 2019-01-24 | 2019-06-01 | 2019-06-01 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-11-22 | COMP | 2019-12-17 | COMP | Rule 16 | 86 | 90 | 6 | 1 | 117 | 16 | 312
9355 | 2018-09-19 | 2019-02-01 | 2019-04-16 | 2019-04-16 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2020-04-03 | COMP | 2020-06-09 | COMP | Rule 16 | 92 | 52 | 89 | 1 | 156 | 47 | 432
9535 | 2018-09-19 | 2019-02-07 | 2019-04-01 | 2019-04-05 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-07-02 | COMP | 2019-07-22 | COMP | Rule 16 | 96 | 37 | 39 | 1 | 24 | 14 | 210
9766 | 2018-09-19 | 2019-02-14 | 2019-04-26 | 2019-04-26 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-08-07 | COMP | 2019-09-16 | COMP | Rule 16 | 101 | 51 | 46 | 1 | 27 | 28 | 249
10105 | 2018-09-19 | 2019-03-02 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-03 | COMP | 2019-05-13 | COMP | 2019-06-21 | COMP | 2019-07-24 | COMP | Rule 16 | 111 | 38 | 8 | 7 | 29 | 23 | 212
10114 | 2018-09-19 | 2019-03-04 | 2019-09-13 | 2019-09-13 | COMP | 2019-10-21 | COMP | 2019-10-18 | COMP | 2019-10-21 | COMP | 2019-10-23 | COMP | Rule 15/16 | 112 | 137 | 27 |  | 2 | 3 | 276
10124 | 2018-09-19 | 2019-03-04 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-09-25 | COMP | 2019-10-21 | COMP | Rule 16 | 112 | 51 | 13 | 1 | 83 | 19 | 274
10749 | 2018-09-19 | 2019-03-28 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2020-06-09 | COMP | 2020-08-10 | COMP | Rule 16 | 130 | 73 | 11 | 1 | 221 | 45 | 476
10911 | 2018-09-19 | 2019-04-06 | 2019-05-02 | 2019-05-02 | COMP | 2019-04-06 | NOTN | 2019-06-05 | COMP | 2019-06-17 | COMP | 2019-08-28 | COMP | Other | 136 | 19 |  | 24 | 9 | 52 | 237
11530 | 2018-09-19 | 2019-05-01 | 2019-08-28 | 2019-08-28 | COMP | 2020-01-06 | COMP | 2020-05-06 | COMP | 2020-04-15 | COMP | 2020-05-19 | COMP | Rule 16 | 154 | 84 | 88 | 86 | 0 | 10 | 418
12286 | 2018-09-19 | 2019-05-30 | 2019-08-15 | 2020-06-23 | COMP | 2020-08-20 | COMP | 2020-09-21 | COMP | 2022-07-16 | INPR | 2021-01-07 | COMP | Rule 16 | 174 | 55 | 43 | 22 |  |  | 578
12640 | 2018-09-19 | 2019-06-17 | 2020-01-10 | 2020-01-10 | COMP | 2020-06-04 | COMP | 2021-02-17 | COMP | 2021-01-05 | COMP | 2021-03-11 | COMP | Rule 15/16 | 186 | 143 | 102 | 177 | 0 | 17 | 621
12641 | 2018-09-19 | 2019-06-17 | 2020-01-17 | 2020-01-17 | COMP | 2020-04-13 | COMP | 2021-05-13 | COMP | 2021-10-19 | COMP | 2021-12-15 | COMP | Rule 15/16 | 186 | 148 | 60 | 275 | 111 | 39 | 814
14026 | 2018-09-19 | 2019-08-22 | 2020-01-13 | 2020-01-13 | COMP | 2020-03-02 | COMP | 2020-08-10 | COMP | 2021-08-16 | COMP | 2021-10-06 | COMP | Rule 15/16 | 233 | 97 | 34 | 115 | 256 | 37 | 767
14046 | 2018-09-19 | 2019-08-22 | 2019-11-21 | 2019-11-21 | COMP | 2019-12-23 | COMP | 2020-02-13 | COMP | 2020-01-13 | COMP | 2020-08-12 | COMP | Rule 15/16 | 233 | 64 | 21 | 36 | 0 | 128 | 478
14899 | 2018-09-19 | 2019-10-02 | 2020-02-25 | 2020-02-25 | COMP | 2020-03-10 | COMP | 2020-08-17 | INPR | 2020-08-14 | COMP | 2020-08-19 | COMP | Rule 16 | 261 | 98 | 11 |  |  |  | 483
17219 | 2018-09-19 | 2020-02-05 | 2020-04-01 | 2020-04-01 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2021-05-10 | COMP | 2021-05-11 | COMP | Rule 16 | 345 | 40 | 28 | 1 | 253 | 2 | 664
4036 | 2018-09-20 | 2018-12-26 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-04 | COMP | 2019-06-26 | COMP | 2019-11-23 | INPR | 2019-07-30 | COMP | Rule 16 | 66 | 60 | 10 | 59 |  |  | 215
4148 | 2018-09-20 | 2019-04-10 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-09 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-11-05 | COMP | Rule 16 | 138 | 18 | 5 | 4 | 1 | 123 | 284
4198 | 2018-09-20 | 2019-07-08 | [7 empty] | 2019-08-07 | COMP | 2019-07-18 | COMP | Other | 199 | [5 empty] | 207
7372 | 2018-09-20 | 2018-10-09 | 2019-01-02 | 2019-01-02 | COMP | 2019-02-07 | COMP | 2019-03-19 | COMP | 2019-04-25 | COMP | 2019-05-30 | COMP | Rule 16 | 14 | 57 | 26 | 28 | 28 | 25 | 173
7597 | 2018-09-20 | 2018-10-22 | 2018-12-12 | 2019-01-07 | COMP | 2019-01-16 | COMP | 2019-02-04 | COMP | 2019-02-08 | COMP | 2019-04-10 | COMP | Rule 16 | 23 | 35 | 8 | 13 | 5 | 43 | 138
7621 | 2018-09-20 | 2018-10-23 | 2018-11-08 | 2018-11-08 | COMP | 2018-11-27 | COMP | 2018-11-27 | COMP | 2018-11-29 | COMP | 2019-01-21 | COMP | Rule 16 | 24 | 13 | 11 | 1 | 3 | 35 | 82
7707 | 2018-09-20 | 2018-10-26 | 2019-03-08 | 2019-03-08 | COMP | 2019-07-18 | COMP | 2019-07-22 | COMP | 2019-07-29 | COMP | 2019-08-02 | COMP | Rule 15/16 | 27 | 89 | 93 | 3 | 6 | 5 | 218
7882 | 2018-09-20 | 2018-11-03 | 2019-04-06 | 2019-04-22 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-03-30 | COMP | 2020-05-20 | COMP | Rule 16 | 32 | 103 | 242 | 1 | 0 | 32 | 418
7897 | 2018-09-20 | 2018-11-05 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-22 | COMP | 2019-01-31 | COMP | 2019-02-28 | COMP | 2019-04-01 | COMP | Rule 16 | 33 | 43 | 9 | 8 | 20 | 23 | 131
7952 | 2018-09-20 | 2018-11-06 | 2019-01-11 | 2019-05-08 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-06-11 | COMP | 2019-07-15 | COMP | Rule 16 | 34 | 44 | 13 | 1 | 12 | 24 | 204
7980 | 2018-09-20 | 2018-11-07 | 2019-02-13 | 2019-03-29 | COMP | 2019-05-13 | COMP | 2019-08-07 | COMP |  | INPR | 2020-04-16 | COMP | Rule 16 | 35 | 65 | 32 | 61 |  |  | 394
8050 | 2018-09-20 | 2018-11-13 | 2019-01-08 | 2019-02-12 | COMP | 2019-02-26 | COMP | 2019-03-05 | COMP | 2019-01-28 | COMP | 2019-04-11 | COMP | Rule 16 | 38 | 37 | 10 | 6 | 0 | 28 | 139
8274 | 2018-09-20 | 2018-11-25 | 2019-02-20 | 2019-02-20 | COMP | 2019-03-01 | COMP | 2019-03-01 | COMP | 2019-03-22 | COMP | 2019-04-11 | COMP | Rule 16 | 44 | 59 | 8 | 1 | 16 | 15 | 139
8347 | 2018-09-20 | 2018-11-27 | 2019-01-24 | 2019-01-24 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-08-13 | COMP | 2019-08-15 | COMP | Rule 16 | 46 | 40 | 65 | 1 | 77 | 3 | 227
8448 | 2018-09-20 | 2018-12-03 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-15 | COMP | 2019-07-03 | COMP | 2019-07-12 | COMP | 2019-08-08 | COMP | Rule 15/16 | 50 | 35 | 18 | 97 | 7 | 20 | 222
8479 | 2018-09-20 | 2018-12-04 | 2019-03-20 | 2019-03-26 | COMP | 2019-03-27 | NOTN | 2019-03-27 | COMP | 2019-03-21 | COMP | 2019-07-13 | COMP | Other | 51 | 73 |  | 2 | 0 | 76 | 203
8508 | 2018-09-20 | 2018-12-05 | 2019-03-06 | 2019-03-06 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-07-03 | COMP | 2019-09-04 | COMP | Rule 15/16 | 52 | 62 | 80 | 1 | 6 | 44 | 240
8558 | 2018-09-20 | 2018-12-10 | 2019-01-17 | 2019-04-23 | COMP | 2019-05-17 | COMP | 2019-06-04 | COMP | 2019-06-13 | COMP | 2019-07-15 | COMP | Rule 16 | 55 | 27 | 19 | 12 | 8 | 22 | 204
8567 | 2018-09-20 | 2018-12-11 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-13 | COMP | 2019-03-22 | COMP | 2019-03-14 | COMP | 2019-04-08 | COMP | Rule 16 | 56 | 53 | 11 | 8 | 0 | 12 | 136
8721 | 2018-09-20 | 2018-12-19 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | Rule 16 | 62 | 76 | 13 | 1 | 19 | 1 | 167
8800 | 2018-09-20 | 2018-12-28 | 2019-02-12 | 2019-04-26 | COMP | 2019-04-30 | NOTN | 2019-04-30 | COMP | 2019-01-28 | COMP | 2019-06-25 | COMP | Rule 16 | 68 | 31 |  | 3 | 0 | 40 | 191
9135 | 2018-09-20 | 2019-01-17 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-29 | COMP | 2019-05-15 | COMP | 2019-09-23 | COMP | 2019-09-26 | COMP | Rule 16 | 81 | 33 | 39 | 13 | 91 | 4 | 256
9360 | 2018-09-20 | 2019-01-31 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-18 | NOTN | 2019-04-03 | COMP | 2019-04-22 | COMP | 2019-05-23 | COMP | Other | 90 | 25 |  | 20 | 14 | 24 | 169
9406 | 2018-09-20 | 2019-02-01 | 2019-05-12 | 2019-05-12 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-01-18 | COMP | 2020-02-26 | COMP | Rule 16 | 91 | 70 | 162 | 1 | 11 | 26 | 358
9688 | 2018-09-20 | 2019-02-11 | 2019-03-21 | 2019-03-21 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-05-30 | COMP | Rule 16 | 97 | 28 | 12 | 1 | 1 | 39 | 173
10039 | 2018-09-20 | 2019-02-28 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-06-19 | COMP | 2019-07-31 | COMP | Rule 16 | 109 | 53 | 13 | 1 | 15 | 30 | 216
10110 | 2018-09-20 | 2019-03-04 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-10-21 | INPR | 2019-06-23 | COMP | Rule 16 | 111 | 53 | 5 | 1 |  |  | 189
10499 | 2018-09-20 | 2019-03-18 | 2019-06-27 | 2019-09-16 | COMP | 2019-09-16 | NOTN | 2019-09-16 | COMP | 2019-09-18 | COMP | 2019-12-11 | COMP | Other | 121 | 73 |  | 1 | 3 | 58 | 307
10665 | 2018-09-20 | 2019-03-25 | 2019-08-27 | 2019-08-27 | COMP | 2019-12-02 | COMP | 2020-01-09 | COMP | 2020-01-14 | COMP | 2020-02-25 | COMP | Rule 15/16 | 126 | 110 | 66 | 27 | 4 | 29 | 357
10741 | 2018-09-20 | 2019-03-28 | 2019-05-24 | 2019-05-24 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-11-26 | COMP | 2020-01-13 | COMP | Rule 16 | 129 | 42 | 99 | 1 | 31 | 31 | 328
10930 | 2018-09-20 | 2019-04-04 | 2019-08-25 | 2019-08-25 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-10-28 | COMP | 2019-12-10 | COMP | Rule 16 | 134 | 100 | 6 | 1 | 40 | 29 | 306
10940 | 2018-09-20 | 2019-04-06 | 2019-07-16 | 2019-08-20 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-03-29 | INPR | 2019-11-21 | COMP | Rule 15/16 | 135 | 70 | 63 | 1 |  |  | 295
12657 | 2018-09-20 | 2019-06-18 | 2019-07-02 | 2019-07-02 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-10-01 | COMP | Rule 16 | 186 | 11 | 50 | 1 | 1 | 15 | 259
13078 | 2018-09-20 | 2019-07-09 | 2019-09-13 | 2019-09-13 | COMP | 2019-09-20 | COMP | 2019-10-30 | COMP | 2019-11-01 | COMP | 2019-12-19 | COMP | Rule 16 | 200 | 48 | 6 | 29 | 3 | 32 | 313
7340 | 2018-09-21 | 2018-10-08 | 2019-01-02 | 2019-01-17 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-03-19 | COMP | 2019-04-17 | COMP | Rule 15/16 | 12 | 58 | 34 | 1 | 9 | 22 | 142
7387 | 2018-09-21 | 2018-10-09 | 2018-12-19 | 2018-12-19 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-05-17 | COMP | Rule 15/16 | 13 | 49 | 74 | 1 | 1 | 31 | 164
7393 | 2018-09-21 | 2018-10-10 | 2019-02-06 | 2019-02-06 | COMP | 2019-03-08 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-05-22 | COMP | Rule 16 | 14 | 80 | 22 | 32 | 1 | 23 | 167
7394 | 2018-09-21 | 2018-10-10 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-22 | COMP | 2019-04-05 | COMP | 2019-04-04 | COMP | 2019-05-15 | COMP | Rule 16 | 14 | 77 | 15 | 31 | 0 | 29 | 162
7652 | 2018-09-21 | 2018-10-24 | 2019-03-20 | 2019-03-26 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-09-24 | COMP | 2019-10-16 | COMP | Rule 16 | 24 | 99 | 85 | 1 | 44 | 17 | 269
7687 | 2018-09-21 | 2018-10-25 | 2019-03-19 | 2019-03-19 | COMP | 2019-03-27 | COMP | 2019-10-02 | INPR | 2019-05-31 | COMP | 2020-07-31 | COMP | Rule 16 | 25 | 97 | 7 |  |  |  | 468
7699 | 2018-09-21 | 2018-10-26 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-02-28 | COMP | Rule 16 | 26 | 59 | 18 | 1 | 1 | 8 | 108
7969 | 2018-09-21 | 2018-11-08 | 2018-12-13 | 2019-01-22 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-04-09 | COMP | 2019-04-29 | COMP | Rule 16 | 35 | 23 | 60 | 1 | 0 | 10 | 150
7985 | 2018-09-21 | 2018-11-08 | 2019-03-07 | 2019-03-07 | COMP | 2019-06-05 | COMP | 2019-06-07 | COMP | 2019-06-06 | COMP | 2019-07-09 | COMP | Rule 16 | 35 | 79 | 64 | 3 | 0 | 22 | 199
8129 | 2018-09-21 | 2018-11-16 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-14 | COMP | Rule 16 | 40 | 17 | 7 | 1 | 1 | 16 | 77
8140 | 2018-09-21 | 2018-11-16 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-04-18 | COMP | Rule 16 | 40 | 59 | 22 | 1 | 1 | 25 | 143
8146 | 2018-09-21 | 2018-11-17 | 2019-03-07 | 2019-03-10 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-04-26 | COMP | 2019-05-18 | COMP | Rule 15/16 | 40 | 73 | 9 | 1 | 27 | 16 | 164
8250 | 2018-09-21 | 2018-11-20 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-25 | COMP | 2019-09-10 | COMP | 2019-08-22 | COMP | 2019-09-18 | COMP | Rule 15/16 | 42 | 151 | 20 | 33 | 0 | 7 | 249
8464 | 2018-09-21 | 2018-12-04 | 2019-01-31 | 2019-01-31 | COMP | 2019-04-11 | COMP | 2021-05-11 | COMP | 2022-03-17 | COMP | 2022-04-29 | COMP | Rule 15/16 | 50 | 40 | 50 | 525 | 215 | 32 | 907
8484 | 2018-09-21 | 2018-12-04 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-03-26 | COMP | 2019-04-22 | COMP | Rule 16 | 50 | 57 | 19 | 1 | 3 | 20 | 145
8595 | 2018-09-21 | 2018-12-11 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-02-13 | COMP | 2019-03-14 | COMP | Rule 16 | 55 | 35 | 7 | 1 | 4 | 21 | 118
8732 | 2018-09-21 | 2018-12-20 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-09 | COMP | 2019-01-09 | INPR | 2019-03-06 | COMP | 2021-07-08 | COMP | Rule 16 | 62 | 3 | 11 |  |  |  | 702
8946 | 2018-09-21 | 2019-01-08 | 2019-10-07 | 2019-11-27 | COMP | 2020-01-22 | COMP | 2020-01-24 | COMP | 2020-02-13 | COMP | 2020-06-11 | COMP | Rule 15/16 | 73 | 190 | 36 | 3 | 15 | 84 | 432
9349 | 2018-09-21 | 2019-01-31 | 2020-03-26 | 2020-03-26 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2020-09-23 | COMP | 2021-01-14 | COMP | Other | 89 | 290 | 119 | 1 | 10 | 77 | 581
10007 | 2018-09-21 | 2019-02-26 | 2019-07-06 | 2019-07-06 | COMP | 2019-08-06 | COMP | 2019-09-19 | COMP | 2020-02-05 | COMP | 2020-02-28 | COMP | Rule 15/16 | 106 | 92 | 22 | 32 | 94 | 17 | 359
10103 | 2018-09-21 | 2019-03-02 | 2022-08-17 | 2022-08-17 | COMP | 2022-09-13 | COMP | 2023-04-13 | COMP | 2023-01-25 | COMP | 2023-04-28 | COMP | Rule 16 | 109 | 873 | 19 | 146 | 0 | 12 | 1156
10185 | 2018-09-21 | 2019-03-05 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-09 | COMP | 2019-07-31 | COMP | 2019-11-05 | COMP | 2019-12-10 | COMP | Other | 111 | 73 | 17 | 17 | 69 | 23 | 305
10947 | 2018-09-21 | 2019-04-05 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-06 | COMP | 2019-06-07 | COMP | 2019-06-06 | COMP | 2019-08-08 | COMP | Rule 15/16 | 134 | 34 | 11 | 2 | 0 | 44 | 221
11188 | 2018-09-21 | 2019-04-16 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-30 | COMP | 2019-07-03 | COMP | 2019-06-24 | COMP | 2019-07-26 | COMP | Rule 16 | 141 | 9 | 24 | 25 | 0 | 17 | 212
11219 | 2018-09-21 | 2019-04-17 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-13 | COMP | 2019-09-09 | COMP | 2020-02-13 | COMP | 2020-04-09 | COMP | Rule 16 | 142 | 61 | 23 | 19 | 108 | 40 | 388
11346 | 2018-09-21 | 2019-04-26 | 2019-08-13 | 2019-08-13 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-10-18 | COMP | Rule 16 | 149 | 76 | 17 | 1 | 1 | 32 | 271
11980 | 2018-09-21 | 2019-05-20 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-12 | COMP | 2019-12-17 | COMP | 2019-12-16 | COMP | 2020-01-23 | COMP | Rule 15/16 | 165 | 110 | 14 | 24 | 0 | 25 | 334
12194 | 2018-09-21 | 2019-05-28 | 2019-08-06 | 2019-08-06 | COMP | 2019-11-06 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-12-19 | COMP | Rule 16 | 170 | 50 | 66 | 5 | 1 | 25 | 312
15980 | 2018-09-21 | 2019-12-04 | 2020-01-30 | 2020-01-30 | COMP | 2020-04-21 | COMP | 2020-07-07 | COMP | 2020-10-09 | COMP | 2020-11-05 | COMP | Rule 16 | 301 | 39 | 58 | 55 | 68 | 20 | 536
7936 | 2018-09-22 | 2018-11-06 | 2019-04-25 | 2019-04-25 | COMP | 2019-12-13 | COMP | 2020-01-16 | COMP | 2020-01-13 | COMP | 2020-03-04 | COMP | Rule 16 | 32 | 116 | 161 | 23 | 0 | 33 | 361
8598 | 2018-09-22 | 2018-12-11 | 2019-01-10 | 2019-01-10 | COMP | 2019-03-06 | COMP | 2019-03-06 | INPR | 2019-03-06 | COMP | 2019-02-06 | COMP | Rule 16 | 54 | 21 | 38 |  |  |  | 92
14005 | 2018-09-22 | 2019-08-21 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-02-25 | COMP | 2020-03-09 | COMP | Rule 16 | 229 | 88 | 21 | 1 | 19 | 10 | 364
8123 | 2018-09-23 | 2018-11-15 | 2019-01-02 | 2019-01-02 | COMP | 2019-01-04 | COMP | 2019-02-27 | COMP | 2019-02-27 | COMP | 2019-03-18 | COMP | Rule 16 | 38 | 31 | 3 | 37 | 1 | 14 | 119
8538 | 2018-09-23 | 2018-12-07 | 2019-05-24 | 2019-05-24 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2021-10-23 | INPR | 2020-05-15 | COMP | Rule 16 | 52 | 117 | 95 | 1 |  |  | 413
9829 | 2018-09-23 | 2019-02-19 | 2019-03-29 | 2019-03-29 | COMP | 2019-09-10 | COMP | 2019-09-23 | COMP | 2019-09-28 | COMP | 2019-10-21 | COMP | Rule 16 | 100 | 29 | 115 | 10 | 5 | 16 | 271
7415 | 2018-09-24 | 2018-10-12 | 2018-12-19 | 2018-12-19 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2019-01-29 | COMP | Rule 16 | 15 | 46 | 6 | 1 | 1 | 22 | 86
7425 | 2018-09-24 | 2018-10-12 | 2019-01-08 | 2019-01-08 | COMP | 2019-02-12 | COMP | 2019-03-04 | COMP | 2019-01-24 | COMP | 2019-03-28 | COMP | Rule 16 | 15 | 58 | 25 | 14 | 0 | 19 | 127
7499 | 2018-09-24 | 2018-10-16 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-04 | COMP | 2019-03-14 | COMP | 2019-03-26 | COMP | 2019-04-19 | COMP | Rule 15/16 | 17 | 64 | 11 | 28 | 9 | 19 | 143
7608 | 2018-09-24 | 2018-10-22 | 2018-10-31 | 2018-10-31 | COMP | 2018-11-21 | COMP | 2018-11-09 | COMP | 2018-11-09 | COMP | 2019-01-31 | COMP | Rule 16 | 21 | 8 | 15 |  | 1 | 54 | 88
7780 | 2018-09-24 | 2018-10-30 | 2018-11-14 | 2018-11-14 | COMP | 2018-12-05 | COMP | 2018-12-05 | COMP | 2020-03-21 | INPR | 2019-12-04 | COMP | Rule 16 | 27 | 11 | 14 | 1 |  |  | 300
7890 | 2018-09-24 | 2018-11-04 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-01-14 | COMP | 2019-04-01 | COMP | Rule 16 | 30 | 25 | 7 | 1 | 16 | 54 | 129
7992 | 2018-09-24 | 2018-11-09 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-04 | COMP | 2019-07-21 | REQD | 2019-07-21 | REQD | 2019-03-11 | COMP | Rule 16 | 35 | 70 | 6 |  |  |  | 114
7997 | 2018-09-24 | 2018-11-09 | 2019-02-07 | 2019-02-07 | COMP | 2019-03-15 | COMP | 2019-04-22 | COMP | 2019-06-13 | COMP | 2019-07-06 | COMP | Rule 16 | 35 | 59 | 26 | 27 | 38 | 16 | 196
8052 | 2018-09-24 | 2018-11-13 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-03-29 | COMP | 2019-05-13 | COMP | Rule 15/16 | 36 | 67 | 26 | 1 | 2 | 32 | 159
8158 | 2018-09-24 | 2018-11-16 | 2019-02-23 | 2019-02-23 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-11 | COMP | 2019-05-24 | COMP | Rule 16 | 39 | 65 | 26 | 1 | 9 | 32 | 168
8475 | 2018-09-24 | 2018-12-04 | 2019-03-21 | 2019-03-21 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2020-06-05 | COMP | 2020-07-15 | COMP | Rule 16 | 49 | 74 | 33 | 1 | 274 | 29 | 455
8496 | 2018-09-24 | 2018-12-05 | 2019-02-19 | 2021-03-05 | COMP | 2021-04-12 | COMP | 2021-04-12 | COMP | 2021-08-09 | COMP | 2021-09-08 | COMP | Rule 16 | 50 | 51 | 27 | 1 | 84 | 22 | 744
8534 | 2018-09-24 | 2018-12-07 | 2019-04-26 | 2019-04-26 | COMP | 2019-06-21 | COMP | 2019-06-27 | COMP | 2020-04-28 | COMP | 2020-05-21 | COMP | Rule 15/16 | 52 | 97 | 40 | 5 | 210 | 18 | 417
8756 | 2018-09-24 | 2018-12-22 | 2019-04-10 | 2019-04-10 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-06-07 | COMP | 2019-07-22 | COMP | Rule 16 | 62 | 74 | 39 | 1 | 4 | 31 | 207
9088 | 2018-09-24 | 2019-01-16 | 2019-03-27 | 2019-03-27 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2020-08-16 | COMP | 2020-10-09 | COMP | Rule 16 | 78 | 49 | 155 | 1 | 198 | 39 | 516
9109 | 2018-09-24 | 2019-01-17 | 2019-02-06 | 2019-02-06 | COMP | 2019-03-21 | COMP | 2019-06-18 | COMP | 2019-05-07 | COMP | 2019-06-24 | COMP | Rule 16 | 79 | 14 | 31 | 63 | 0 | 5 | 188
9162 | 2018-09-24 | 2019-01-18 | 2019-03-08 | 2019-03-08 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-10-21 | INPR | 2019-06-19 | COMP | Rule 16 | 80 | 34 | 57 | 1 |  |  | 185
9434 | 2018-09-24 | 2019-02-04 | 2019-05-06 | 2019-05-06 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-08-13 | COMP | 2019-08-29 | COMP | Rule 16 | 90 | 65 | 13 | 1 | 58 | 13 | 235
9559 | 2018-09-24 | 2019-02-07 | 2019-08-03 | 2019-10-18 | COMP | 2019-10-19 | NOTN | 2019-10-19 | COMP | 2019-08-09 | COMP | 2019-11-19 | COMP | Other | 93 | 124 |  | 1 | 0 | 21 | 291
9945 | 2018-09-24 | 2019-02-25 | 2019-05-21 | 2019-05-21 | COMP | 2019-06-11 | COMP | 2019-08-15 | COMP | 2019-09-09 | COMP | 2019-09-26 | COMP | Rule 15/16 | 104 | 62 | 15 | 47 | 17 | 14 | 254
10350 | 2018-09-24 | 2019-03-12 | 2019-12-17 | 2021-02-11 | COMP | 2021-06-23 | COMP | 2021-06-23 | COMP | 2021-11-08 | COMP | 2021-12-17 | COMP | Rule 16 | 115 | 195 | 93 | 1 | 97 | 27 | 813
11751 | 2018-09-24 | 2019-05-09 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-07 | COMP | 2019-06-28 | COMP | 2019-07-02 | COMP | 2019-08-05 | COMP | Rule 16 | 157 | 14 | 8 | 16 | 3 | 24 | 217
12314 | 2018-09-24 | 2019-05-30 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-08-01 | COMP | 2019-08-11 | COMP | Rule 16 | 171 | 22 | 21 | 1 | 4 | 7 | 221
12472 | 2018-09-24 | 2019-06-10 | 2019-07-13 | 2019-07-13 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-09-05 | COMP | 2020-02-14 | COMP | Rule 16 | 178 | 24 | 30 | 1 | 9 | 111 | 349
13054 | 2018-09-24 | 2019-07-08 | 2019-10-09 | 2019-10-09 | COMP | 2020-03-17 | NOTN | 2020-03-17 | COMP | 2021-05-26 | COMP | 2021-08-31 | COMP | Other | 197 | 67 |  | 108 | 303 | 68 | 739
13844 | 2018-09-24 | 2019-08-13 | 2019-09-30 | 2019-09-30 | COMP | 2021-02-05 | COMP | 2021-05-18 | COMP | 2021-02-05 | COMP | 2021-06-07 | COMP | Rule 16 | 223 | 34 | 340 | 72 | 0 | 14 | 679
14360 | 2018-09-24 | 2019-09-06 | 2019-09-13 | 2019-09-13 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-11-19 | COMP | 2021-01-13 | COMP | Rule 16 | 240 | 6 | 171 | 1 | 130 | 36 | 579
15249 | 2018-09-24 | 2019-10-23 | 2020-03-09 | 2020-09-28 | COMP | 2020-11-18 | COMP | 2020-11-18 | COMP | 2020-11-30 | COMP | 2020-12-08 | COMP | Rule 16 | 273 | 92 | 37 | 1 | 7 | 7 | 555
15986 | 2018-09-24 | 2019-12-04 | 2020-05-17 | 2020-05-18 | COMP | 2020-06-12 | COMP | 2020-07-29 | COMP | 2020-10-06 | COMP | 2020-11-05 | COMP | Rule 16 | 300 | 114 | 19 | 34 | 49 | 23 | 535
7103 | 2018-09-25 | 2018-09-27 | 2022-12-23 | 2022-12-23 | COMP | 2023-01-31 | COMP | 2023-04-06 | COMP | 2023-08-30 | COMP | 2023-11-28 | COMP | Rule 15/16 | 3 | 1066 | 25 | 47 | 102 | 61 | 1299
7289 | 2018-09-25 | 2018-10-06 | 2018-12-12 | 2018-12-12 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2019-02-14 | COMP | 2020-01-06 | COMP | Other | 9 | 45 | 7 | 1 | 38 | 224 | 320
7577 | 2018-09-25 | 2018-10-20 | 2019-01-14 | 2019-01-14 | COMP | 2019-04-30 | COMP | 2019-09-04 | COMP | 2019-08-20 | COMP | 2019-09-17 | COMP | Rule 16 | 19 | 56 | 75 | 89 | 0 | 10 | 246
7821 | 2018-09-25 | 2018-11-01 | 2019-03-19 | 2020-05-05 | COMP | 2019-08-07 | COMP | 2020-07-16 | COMP | 2020-01-31 | COMP | 2021-04-27 | COMP | Rule 16 | 28 | 92 |  | 238 | 0 | 196 | 650
7844 | 2018-09-25 | 2018-11-02 | 2018-12-26 | 2018-12-26 | COMP | 2019-01-17 | COMP | 2019-01-17 | COMP | 2019-07-21 | INPR | 2019-03-08 | COMP | Rule 16 | 29 | 35 | 16 | 1 |  |  | 112
7918 | 2018-09-25 | 2018-11-05 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-04-15 | COMP | Rule 16 | 30 | 55 | 21 | 1 | 1 | 35 | 138
7937 | 2018-09-25 | 2018-11-05 | 2019-02-12 | 2019-02-12 | COMP | 2019-05-01 | COMP | 2019-08-21 | COMP | 2019-11-25 | COMP | 2019-12-16 | COMP | Rule 15/16 | 30 | 66 | 56 | 79 | 67 | 14 | 307
7939 | 2018-09-25 | 2018-11-06 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-06 | COMP | 2019-02-07 | COMP | 2019-03-12 | COMP | 2019-04-22 | COMP | Rule 16 | 31 | 49 | 13 | 2 | 23 | 30 | 143
7941 | 2018-09-25 | 2018-11-06 | 2019-01-09 | 2019-01-09 | COMP | 2019-04-02 | COMP | 2019-04-02 | INPR | 2021-03-29 | COMP | 2021-04-05 | COMP | Rule 16 | 31 | 42 | 58 |  |  |  | 634
7942 | 2018-09-25 | 2018-11-06 | 2018-12-20 | 2018-12-20 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-02-01 | COMP | 2019-02-12 | COMP | Rule 16 | 31 | 30 | 27 | 1 | 3 | 8 | 95
8034 | 2018-09-25 | 2018-11-12 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-07-21 | INPR | 2019-04-01 | COMP | Rule 16 | 34 | 47 | 14 | 1 |  |  | 128
8086 | 2018-09-25 | 2018-11-16 | 2019-01-30 | 2019-01-30 | COMP | 2019-03-19 | COMP | 2019-05-22 | COMP | 2019-07-31 | COMP | 2019-09-18 | COMP | Rule 15/16 | 38 | 49 | 34 | 47 | 49 | 35 | 247
8155 | 2018-09-25 | 2018-11-17 | 2019-04-08 | 2019-05-31 | COMP | 2019-06-04 | COMP | 2019-07-15 | COMP | 2019-07-01 | COMP | 2019-08-31 | COMP | Rule 16 | 38 | 95 | 3 | 29 | 0 | 35 | 235
8913 | 2018-09-25 | 2019-01-05 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-06-27 | COMP | 2019-08-26 | COMP | Rule 16 | 69 | 77 | 20 | 1 | 26 | 42 | 231
9049 | 2018-09-25 | 2019-01-14 | 2019-04-15 | 2019-04-15 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-03-03 | COMP | 2020-03-04 | COMP | Rule 16 | 75 | 64 | 205 | 1 | 18 | 2 | 360
9872 | 2018-09-25 | 2019-02-21 | 2019-09-09 | 2021-11-04 | COMP | 2022-02-02 | COMP | 2022-06-21 | COMP | 2022-06-17 | COMP | 2022-08-03 | COMP | Rule 15/16 | 101 | 140 | 61 | 97 | 0 | 31 | 970
9875 | 2018-09-25 | 2019-02-21 | 2019-12-02 | 2019-12-02 | COMP | 2020-03-11 | COMP | 2020-10-07 | COMP | 2022-06-21 | COMP | 2022-08-02 | COMP | Rule 15/16 | 101 | 197 | 69 | 149 | 428 | 30 | 969
10076 | 2018-09-25 | 2019-03-01 | 2019-04-29 | 2019-10-16 | COMP | 2019-11-19 | COMP | 2019-09-24 | COMP | 2019-11-19 | COMP | 2020-01-12 | COMP | Rule 16 | 107 | 42 | 24 |  | 40 | 35 | 324
10687 | 2018-09-25 | 2019-03-26 | 2019-06-17 | 2019-06-17 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-12-29 | INPR | 2019-07-31 | COMP | Rule 16 | 124 | 59 | 11 | 1 |  |  | 213
13053 | 2018-09-25 | 2019-07-08 | 2019-11-13 | 2020-10-26 | COMP | 2021-01-05 | COMP | 2021-05-25 | COMP | 2021-07-26 | COMP | 2021-09-23 | COMP | Rule 16 | 196 | 91 | 47 | 99 | 43 | 43 | 754
7469 | 2018-09-26 | 2018-10-16 | 2019-01-11 | 2019-01-11 | COMP | 2019-02-21 | COMP | 2019-03-07 | COMP | 2019-03-19 | COMP | 2019-05-14 | COMP | Rule 16 | 15 | 59 | 28 | 11 | 9 | 41 | 158
7562 | 2018-09-26 | 2018-10-19 | 2018-11-30 | 2019-02-11 | COMP | 2019-03-08 | COMP | 2019-03-12 | COMP | 2019-04-26 | COMP | 2019-05-13 | COMP | Rule 16 | 18 | 28 | 19 | 3 | 34 | 12 | 157
7580 | 2018-09-26 | 2018-10-21 | 2018-11-18 | 2018-11-18 | COMP | 2019-02-28 | COMP | 2019-02-28 | COMP | 2019-07-21 | INPR | 2019-04-04 | COMP | Rule 16 | 18 | 19 | 68 | 1 |  |  | 130
7709 | 2018-09-26 | 2018-10-26 | 2019-01-12 | 2019-01-12 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-11 | COMP | 2019-05-04 | COMP | Rule 16 | 23 | 51 | 35 | 1 | 5 | 40 | 151
7728 | 2018-09-26 | 2018-10-26 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-04-23 | COMP | 2019-06-06 | COMP | Rule 16 | 23 | 100 | 14 | 1 | 9 | 32 | 174
7772 | 2018-09-26 | 2018-10-30 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-11 | COMP | 2019-01-11 | COMP | 2019-07-21 | INPR | 2019-04-02 | COMP | Rule 16 | 25 | 37 | 13 | 1 |  |  | 128
7833 | 2018-09-26 | 2018-11-01 | 2019-01-25 | 2019-01-25 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-05-22 | COMP | 2019-07-26 | COMP | Rule 16 | 27 | 56 | 82 | 1 | 2 | 46 | 209
7850 | 2018-09-26 | 2018-11-02 | 2019-01-02 | 2019-01-02 | COMP | 2019-02-06 | COMP | 2019-02-25 | COMP | 2019-01-31 | COMP | 2019-04-12 | COMP | Rule 16 | 28 | 39 | 25 | 13 | 0 | 35 | 136
7984 | 2018-09-26 | 2018-11-08 | 2018-11-15 | 2018-11-15 | COMP | 2018-12-12 | COMP | 2018-12-12 | COMP | 2019-07-21 | INPR | 2019-04-01 | COMP | Rule 16 | 32 | 5 | 18 | 1 |  |  | 127
8161 | 2018-09-26 | 2018-11-16 | 2019-01-26 | 2019-01-26 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-04-04 | COMP | Rule 16 | 37 | 46 | 18 | 1 | 1 | 31 | 130
8268 | 2018-09-26 | 2018-11-21 | 2018-12-14 | 2018-12-14 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-12-28 | INPR | 2019-02-01 | COMP | Rule 16 | 40 | 16 | 20 | 1 |  |  | 87
8480 | 2018-09-26 | 2018-12-04 | 2019-03-18 | 2019-03-18 | COMP | 2019-03-25 | COMP | 2019-03-28 | COMP | 2019-03-25 | COMP | 2019-04-04 | COMP | Rule 16 | 47 | 71 | 6 | 4 | 0 | 6 | 130
8657 | 2018-09-26 | 2018-12-13 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-03-07 | COMP | 2019-03-26 | COMP | Rule 16 | 54 | 28 | 14 | 1 | 17 | 14 | 123
8796 | 2018-09-26 | 2018-12-28 | 2019-11-05 | 2019-11-05 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2020-03-04 | COMP | 2020-04-25 | COMP | Rule 15/16 | 64 | 217 | 26 | 1 | 55 | 38 | 396
8811 | 2018-09-26 | 2018-12-31 | 2019-02-22 | 2019-07-19 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-08-29 | COMP | 2019-10-03 | COMP | Rule 16 | 65 | 37 | 29 | 1 | 2 | 25 | 257
8857 | 2018-09-26 | 2019-01-03 | 2019-03-25 | 2019-05-28 | COMP | 2019-06-25 | COMP | 2019-06-28 | COMP | 2019-06-25 | COMP | 2019-06-30 | COMP | Rule 16 | 67 | 56 | 21 | 4 | 0 | 1 | 190
8942 | 2018-09-26 | 2019-01-08 | 2019-04-16 | 2019-06-26 | COMP | 2019-07-16 | COMP | 2019-08-16 | COMP | 2019-11-07 | COMP | 2019-12-13 | COMP | Rule 15/16 | 70 | 69 | 14 | 24 | 59 | 24 | 305
9057 | 2018-09-26 | 2019-01-15 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-15 | COMP | 2019-05-16 | COMP | 2019-10-21 | INPR | 2019-06-06 | COMP | Rule 16 | 75 | 71 | 15 | 2 |  |  | 174
9137 | 2018-09-26 | 2019-01-17 | 2019-05-03 | 2019-05-03 | COMP | 2019-06-27 | NOTN | 2019-06-27 | COMP | 2019-08-15 | COMP | 2019-10-16 | COMP | Other | 77 | 75 |  | 39 | 35 | 44 | 266
9484 | 2018-09-26 | 2019-02-06 | 2019-02-09 | 2019-02-09 | COMP | 2019-02-19 | COMP | 2019-02-19 | INPR | 2022-06-18 | REQD | 2020-02-22 | COMP | Rule 16 | 90 | 3 | 6 |  |  |  | 351
9505 | 2018-09-26 | 2019-02-06 | 2019-12-23 | 2019-12-23 | COMP | 2020-05-15 | COMP | 2020-12-08 | COMP | 2020-12-08 | COMP | 2021-02-19 | COMP | Rule 15/16 | 90 | 222 | 101 | 143 | 1 | 50 | 602
9876 | 2018-09-26 | 2019-02-22 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-07-11 | COMP | 2019-08-28 | COMP | Rule 16 | 101 | 38 | 14 | 1 | 48 | 35 | 232
10002 | 2018-09-26 | 2019-02-26 | 2019-06-04 | 2019-06-07 | COMP | 2019-07-29 | COMP | 2019-08-23 | COMP | 2019-09-10 | COMP | 2019-09-23 | COMP | Rule 16 | 103 | 70 | 36 | 20 | 12 | 10 | 249
10476 | 2018-09-26 | 2019-03-18 | 2019-07-24 | 2019-10-18 | COMP | 2019-10-18 | NOTN | 2019-10-18 | COMP | 2020-06-09 | COMP | 2020-07-08 | COMP | Other | 117 | 91 |  | 1 | 160 | 22 | 448
11949 | 2018-09-26 | 2019-05-17 | 2019-09-05 | 2020-10-02 | COMP | 2021-02-17 | COMP | 2021-02-23 | COMP | 2022-06-08 | COMP | 2022-08-15 | COMP | Rule 16 | 161 | 77 | 92 | 5 | 328 | 47 | 977
16615 | 2018-09-26 | 2020-01-10 | 2020-03-25 | 2020-03-25 | COMP | 2020-05-19 | COMP | 2020-05-19 | INPR | 2022-03-08 | COMP | 2022-03-22 | COMP | Rule 16 | 323 | 52 | 40 |  |  |  | 876
19151 | 2018-09-26 | 2020-04-23 | 2020-08-21 | 2020-08-21 | COMP | 2020-12-28 | COMP | 2020-12-29 | COMP | 2023-03-07 | COMP | 2023-06-13 | COMP | Rule 16 | 395 | 86 | 87 | 2 | 549 | 70 | 1184
7220 | 2018-09-27 | 2018-10-03 | 2018-12-21 | 2018-12-21 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-05-15 | COMP | 2019-06-26 | COMP | Rule 15/16 | 5 | 55 | 23 | 1 | 78 | 30 | 187
7221 | 2018-09-27 | 2018-10-03 | 2018-12-17 | 2018-12-17 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-05 | COMP | Rule 16 | 5 | 51 | 59 | 1 | 1 | 18 | 130
7222 | 2018-09-27 | 2018-10-03 | 2018-12-17 | 2018-12-17 | COMP | 2018-12-27 | COMP | 2018-12-27 | COMP | 2018-12-23 | COMP | 2019-01-12 | COMP | Rule 16 | 5 | 51 | 8 | 1 | 0 | 11 | 72
7455 | 2018-09-27 | 2018-10-15 | 2019-02-13 | 2019-02-13 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-09 | COMP | 2019-11-12 | COMP | Rule 16 | 13 | 82 | 117 | 1 | 9 | 66 | 283
7514 | 2018-09-27 | 2018-10-18 | 2019-01-15 | 2019-02-15 | COMP | 2019-04-10 | COMP | 2019-04-23 | COMP | 2019-06-03 | COMP | 2019-05-15 | COMP | Rule 16 | 16 | 59 | 38 | 10 | 29 |  | 158
7535 | 2018-09-27 | 2018-10-18 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | Rule 16 | 16 | 66 | 6 | 1 | 128 | 1 | 213
7668 | 2018-09-27 | 2018-10-24 | 2018-11-10 | 2018-11-10 | COMP | 2018-12-18 | COMP | 2018-12-31 | COMP | 2019-03-25 | COMP | 2019-04-29 | COMP | Rule 16 | 20 | 13 | 24 | 9 | 58 | 26 | 146
7692 | 2018-09-27 | 2018-10-26 | 2019-05-15 | 2019-05-15 | COMP | 2020-03-20 | COMP | 2020-12-29 | COMP | 2021-01-25 | COMP | 2021-03-30 | COMP | Rule 15/16 | 22 | 137 | 213 | 197 | 18 | 46 | 628
7729 | 2018-09-27 | 2018-10-26 | 2019-03-11 | 2019-03-11 | COMP | 2019-04-10 | COMP | 2019-04-11 | COMP | 2019-09-02 | INPR | 2019-05-13 | COMP | Rule 16 | 22 | 90 | 23 | 2 |  |  | 156
7773 | 2018-09-27 | 2018-10-30 | 2018-11-26 | 2018-11-26 | COMP | 2018-11-14 | NOTN | 2019-02-13 | COMP | 2019-07-21 | INPR | 2019-03-11 | COMP | Other | 24 | 17 |  | 55 |  |  | 111
7830 | 2018-09-27 | 2018-11-01 | 2018-12-24 | 2019-05-29 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2020-02-24 | COMP | 2020-04-09 | COMP | Rule 16 | 26 | 35 | 10 | 1 | 176 | 34 | 384
8060 | 2018-09-27 | 2018-11-13 | 2019-05-24 | 2019-05-24 | COMP | 2019-08-23 | COMP | 2020-01-06 | COMP | 2020-09-28 | COMP | 2020-11-17 | COMP | Rule 16 | 33 | 133 | 64 | 91 | 187 | 36 | 539
8188 | 2018-09-27 | 2018-11-19 | 2019-03-18 | 2019-03-18 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2020-01-10 | COMP | 2020-02-13 | COMP | Rule 16 | 37 | 80 | 14 | 1 | 194 | 24 | 345
8320 | 2018-09-27 | 2018-11-27 | 2019-10-06 | 2019-10-06 | COMP | 2019-11-01 | COMP | 2020-01-10 | COMP | 2019-11-18 | COMP | 2020-01-31 | COMP | Rule 15/16 | 41 | 217 | 20 | 46 | 0 | 15 | 336
8337 | 2018-09-27 | 2018-11-27 | 2019-03-06 | 2019-03-06 | COMP | 2019-05-16 | COMP | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-07-16 | COMP | Rule 16 | 41 | 68 | 52 | 33 | 1 | 10 | 200
8888 | 2018-09-27 | 2019-01-04 | 2019-12-18 | 2019-12-18 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-01-08 | COMP | 2020-07-01 | COMP | Rule 15/16 | 67 | 241 | 50 | 1 | 0 | 87 | 442
8914 | 2018-09-27 | 2019-01-05 | 2019-04-29 | 2019-04-29 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-06-03 | COMP | 2019-06-26 | COMP | Rule 16 | 67 | 79 | 22 | 1 | 4 | 18 | 187
9179 | 2018-09-27 | 2019-01-20 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-10 | COMP | 2019-05-24 | COMP | Rule 16 | 77 | 5 | 32 | 1 | 21 | 33 | 165
9300 | 2018-09-27 | 2019-01-28 | 2019-03-18 | 2019-03-18 | COMP | 2019-04-16 | COMP | 2019-05-22 | COMP | 2019-05-21 | COMP | 2019-06-12 | COMP | Rule 16 | 82 | 35 | 22 | 27 | 0 | 15 | 177
9437 | 2018-09-27 | 2019-02-04 | 2019-04-12 | 2019-04-12 | COMP | 2021-02-01 | COMP | 2021-03-16 | COMP | 2021-03-11 | COMP | 2021-04-16 | COMP | Rule 15/16 | 87 | 49 | 454 | 31 | 0 | 24 | 641
10217 | 2018-09-27 | 2019-03-06 | 2019-05-22 | 2019-05-22 | COMP | 2019-10-01 | COMP | 2020-01-07 | COMP | 2021-03-27 | INPR | 2020-03-09 | COMP | Rule 16 | 108 | 56 | 92 | 66 |  |  | 361
10382 | 2018-09-27 | 2019-03-13 | 2019-04-20 | 2019-05-15 | COMP | 2019-07-17 | COMP | 2019-07-29 | COMP | 2019-12-29 | INPR | 2019-08-26 | COMP | Rule 16 | 113 | 28 | 44 | 9 |  |  | 229
10410 | 2018-09-27 | 2019-03-14 | 2019-03-15 | 2019-03-15 | COMP | 2019-04-11 | COMP | 2019-07-26 | COMP | 2019-08-05 | COMP | 2019-08-16 | COMP | Rule 16 | 114 | 2 | 20 | 75 | 7 | 10 | 223
10766 | 2018-09-27 | 2019-03-28 | 2019-06-07 | 2019-06-07 | COMP | 2019-06-24 | COMP | 2019-08-01 | COMP | 2019-07-01 | COMP | 2019-08-19 | COMP | Rule 16 | 124 | 51 | 12 | 28 | 0 | 13 | 224
11236 | 2018-09-27 | 2019-04-18 | 2020-01-15 | 2020-01-15 | COMP | 2020-07-22 | COMP | 2020-08-06 | COMP | 2020-07-28 | COMP | 2020-11-07 | COMP | Rule 15/16 | 139 | 187 | 133 | 12 | 0 | 66 | 533
11325 | 2018-09-27 | 2019-04-23 | 2019-07-03 | 2020-09-30 | COMP | 2020-10-07 | COMP | 2020-10-08 | COMP | 2020-10-12 | COMP | 2020-11-13 | COMP | Rule 15/16 | 142 | 51 | 6 | 2 | 3 | 24 | 537
12767 | 2018-09-27 | 2019-06-20 | 2019-06-28 | 2019-06-28 | COMP | 2019-09-20 | COMP | 2023-04-25 | INPR | 2023-05-27 | CANC | 2019-11-05 | COMP | Rule 16 | 183 | 7 | 59 |  |  |  | 279
13514 | 2018-09-27 | 2019-07-29 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-12-03 | COMP | 2020-01-07 | COMP | Rule 16 | 209 | 69 | 13 | 1 | 8 | 24 | 319
15395 | 2018-09-27 | 2019-10-30 | 2020-01-25 | 2020-05-15 | COMP | 2020-05-22 | COMP | 2020-05-29 | COMP | 2020-05-26 | COMP | 2020-07-09 | COMP | Rule 16 | 275 | 57 | 6 | 5 | 0 | 30 | 448
16576 | 2018-09-27 | 2020-01-08 | 2020-03-03 | 2020-05-14 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2021-02-18 | COMP | 2021-03-26 | COMP | Rule 15/16 | 320 | 38 | 13 | 1 | 180 | 27 | 626
7412 | 2018-09-28 | 2018-10-11 | 2019-01-16 | 2019-02-21 | COMP | 2019-02-21 | NOTN | 2019-03-12 | COMP | 2019-03-09 | COMP | 2019-05-08 | COMP | Other | 10 | 65 |  | 14 | 0 | 42 | 152
7742 | 2018-09-28 | 2018-10-29 | 2018-12-11 | 2018-12-11 | COMP | 2019-02-12 | COMP | 2019-06-13 | COMP | 2020-05-31 | INPR | 2019-08-19 | COMP | Rule 16 | 22 | 29 | 43 | 86 |  |  | 223
7761 | 2018-09-28 | 2018-10-30 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-04-23 | COMP | 2019-06-06 | COMP | Rule 16 | 23 | 47 | 15 | 1 | 59 | 32 | 172
7974 | 2018-09-28 | 2018-11-08 | 2019-01-08 | 2019-01-08 | COMP | 2019-01-23 | NOTN | 2019-03-19 | COMP | 2019-03-12 | NOTN | 2019-04-17 | COMP | Other | 30 | 39 |  | 49 |  |  | 137
8077 | 2018-09-28 | 2018-11-14 | 2019-03-04 | 2019-03-04 | COMP | 2019-05-02 | COMP | 2020-06-12 | COMP | 2020-05-08 | COMP | 2020-08-17 | COMP | Rule 16 | 33 | 73 | 44 | 281 | 0 | 47 | 474
8078 | 2018-09-28 | 2018-11-14 | 2019-03-11 | 2019-03-11 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2020-10-22 | COMP | 2020-12-02 | COMP | Rule 16 | 33 | 78 | 39 | 1 | 374 | 27 | 547
8080 | 2018-09-28 | 2018-11-14 | 2019-01-31 | 2019-01-31 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2020-07-06 | COMP | 2020-07-23 | COMP | Rule 16 | 33 | 52 | 65 | 1 | 297 | 14 | 457
8095 | 2018-09-28 | 2018-11-15 | 2019-01-25 | 2019-01-25 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2020-05-08 | COMP | 2020-07-24 | COMP | Rule 16 | 34 | 47 | 69 | 1 | 257 | 55 | 458
8381 | 2018-09-28 | 2018-11-28 | 2020-01-13 | 2020-10-02 | COMP | 2020-12-14 | COMP | 2021-05-14 | COMP | 2021-09-01 | COMP | 2021-09-17 | COMP | Rule 16 | 41 | 282 | 49 | 106 | 77 | 12 | 747
8488 | 2018-09-28 | 2018-12-04 | 2019-01-03 | 2019-01-03 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-04-05 | COMP | Rule 16 | 45 | 21 | 58 | 1 | 1 | 8 | 129
8878 | 2018-09-28 | 2019-01-03 | 2020-01-28 | 2020-07-21 | COMP | 2020-08-06 | COMP | 2020-09-11 | COMP | 2020-10-07 | COMP | 2021-03-23 | COMP | Rule 15/16 | 65 | 268 | 13 | 26 | 19 | 113 | 622
8948 | 2018-09-28 | 2019-01-08 | 2020-01-16 | 2022-09-08 | COMP | 2022-11-10 | COMP | 2023-03-22 | COMP | 2023-09-14 | COMP | 2023-11-17 | COMP | Rule 16 | 68 | 258 | 46 | 88 | 123 | 46 | 1291
9181 | 2018-09-28 | 2019-01-20 | 2019-03-08 | 2019-03-08 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-07-22 | COMP | 2019-08-05 | COMP | Rule 16 | 76 | 33 | 93 | 1 | 3 | 11 | 213
9182 | 2018-09-28 | 2019-01-20 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-04-29 | COMP | 2019-05-04 | COMP | Rule 16 | 76 | 29 | 6 | 1 | 36 | 5 | 149
9209 | 2018-09-28 | 2019-01-22 | 2019-04-16 | 2019-04-16 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2020-01-07 | COMP | 2020-01-15 | COMP | Rule 16 | 77 | 60 | 141 | 1 | 43 | 7 | 324
9408 | 2018-09-28 | 2019-02-01 | 2019-05-11 | 2019-05-11 | COMP | 2019-05-22 | COMP | 2019-06-04 | COMP | 2019-05-22 | COMP | 2019-07-18 | COMP | Rule 16 | 85 | 70 | 8 | 9 | 0 | 32 | 201
9477 | 2018-09-28 | 2019-02-05 | 2019-09-13 | 2019-10-12 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-08-20 | COMP | 2020-10-05 | COMP | Rule 15/16 | 87 | 155 | 27 | 1 | 190 | 32 | 508
9489 | 2018-09-28 | 2019-02-06 | 2019-07-05 | 2021-05-21 | COMP | 2021-05-25 | COMP |  | REQD | 2021-06-30 | COMP | 2021-09-18 | COMP | Rule 16 | 88 | 105 | 3 |  |  |  | 747
10390 | 2018-09-28 | 2019-03-13 | 2019-03-29 | 2019-03-29 | COMP | 2019-06-18 | COMP | 2019-07-01 | COMP | 2019-07-09 | COMP | 2019-07-31 | COMP | Rule 16 | 112 | 13 | 57 | 10 | 6 | 17 | 210
10691 | 2018-09-28 | 2019-03-26 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-15 | COMP | 2019-06-10 | COMP | 2019-12-29 | INPR | 2019-08-13 | COMP | Rule 15/16 | 121 | 27 | 11 | 18 |  |  | 219
11514 | 2018-09-28 | 2019-04-30 | 2019-08-07 | 2019-08-07 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2019-11-25 | COMP | 2020-01-09 | COMP | Rule 15/16 | 146 | 70 | 67 | 1 | 11 | 30 | 320
11976 | 2018-09-28 | 2019-05-20 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2020-10-08 | COMP | 2020-10-21 | COMP | Rule 16 | 160 | 23 | 19 | 1 | 312 | 10 | 520
11977 | 2018-09-28 | 2019-05-20 | 2019-07-10 | 2019-10-09 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-12-20 | COMP | 2020-01-10 | COMP | Rule 16 | 160 | 36 | 20 | 1 | 31 | 14 | 321
12859 | 2018-09-28 | 2019-06-25 | 2020-04-17 | 2020-04-17 | COMP | 2020-04-23 | COMP | 2020-09-24 | COMP | 2020-08-03 | COMP | 2020-10-08 | COMP | Rule 16 | 185 | 205 | 5 | 109 | 0 | 11 | 511
7585 | 2018-09-29 | 2018-10-22 | 2019-01-10 | 2019-01-10 | COMP | 2019-01-25 | COMP | 2019-03-13 | COMP | 2019-04-22 | COMP | 2019-05-09 | COMP | Rule 15/16 | 16 | 54 | 11 | 33 | 29 | 14 | 152
10629 | 2018-09-29 | 2019-03-23 | 2019-05-25 | 2021-03-10 | COMP | 2021-03-25 | COMP | 2021-10-13 | COMP | 2021-09-13 | COMP | 2021-12-09 | COMP | Rule 16 | 118 | 45 | 12 | 142 | 0 | 39 | 802
16896 | 2018-09-29 | 2020-01-22 | 2021-01-11 | 2021-01-11 | COMP | 2021-03-16 | COMP | 2021-03-16 | COMP | 2022-07-30 | INPR | 2021-07-22 | COMP | Rule 16 | 327 | 246 | 45 | 1 |  |  | 706
10106 | 2018-09-30 | 2019-03-02 | 2019-05-03 | 2019-05-03 | COMP | 2019-07-31 | COMP | 2019-10-16 | COMP | 2020-12-09 | COMP | 2021-01-26 | COMP | Rule 16 | 103 | 45 | 62 | 55 | 289 | 32 | 582
4119 | 2018-10-01 | 2019-03-06 | 2019-03-08 | 2019-03-08 | COMP | 2019-03-07 | NOTN | 2019-03-11 | COMP | 2019-03-15 | COMP | 2019-05-30 | COMP | Rule 16 | 106 | 3 |  | 2 | 5 | 54 | 166
7205 | 2018-10-01 | 2018-10-02 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-12 | COMP | 2019-07-26 | COMP | 2019-07-25 | COMP | 2019-08-30 | COMP | Rule 15/16 | 2 | 121 | 12 | 74 | 0 | 26 | 231
7315 | 2018-10-01 | 2018-10-08 | 2019-06-10 | 2019-06-10 | COMP | 2019-06-13 | COMP | 2019-06-26 | COMP | 2019-06-13 | COMP | 2019-07-28 | COMP | Rule 15/16 | 6 | 168 | 4 | 10 | 0 | 22 | 206
7327 | 2018-10-01 | 2018-10-08 | 2019-02-05 | 2019-02-05 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-04 | COMP | 2019-05-18 | COMP | Rule 16 | 6 | 81 | 41 | 1 | 2 | 32 | 158
7366 | 2018-10-01 | 2018-10-09 | 2019-01-03 | 2019-01-03 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-03-28 | COMP | 2019-05-02 | COMP | Rule 16 | 7 | 58 | 57 | 1 | 3 | 26 | 147
7371 | 2018-10-01 | 2018-10-09 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-17 | COMP | 2019-08-23 | COMP | 2020-01-23 | COMP | 2020-02-10 | COMP | Rule 16 | 7 | 117 | 36 | 69 | 103 | 13 | 340
7399 | 2018-10-01 | 2018-10-10 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-02-27 | COMP | 2019-02-08 | COMP | 2019-03-25 | COMP | Rule 16 | 8 | 75 | 7 | 14 | 0 | 19 | 119
7615 | 2018-10-01 | 2018-10-23 | 2019-02-23 | 2019-02-23 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2020-05-08 | COMP | 2020-07-15 | COMP | Rule 16 | 17 | 82 | 49 | 1 | 257 | 48 | 450
7672 | 2018-10-01 | 2018-10-24 | 2018-12-07 | 2018-12-07 | COMP | 2018-12-18 | COMP | 2019-01-16 | COMP | 2019-01-07 | COMP | 2019-03-06 | COMP | Rule 16 | 18 | 30 | 8 | 20 | 0 | 34 | 106
7895 | 2018-10-01 | 2018-11-05 | 2018-11-19 | 2018-11-19 | COMP | 2018-11-28 | COMP | 2018-12-03 | COMP | 2018-12-04 | COMP | 2019-01-04 | COMP | Rule 16 | 26 | 10 | 6 | 4 | 2 | 22 | 65
7917 | 2018-10-01 | 2018-11-05 | 2019-01-25 | 2019-07-16 | COMP | 2019-07-18 | COMP | 2019-07-18 | INPR | 2019-02-11 | COMP | 2019-02-12 | COMP | Rule 16 | 26 | 54 | 3 |  |  |  | 91
8112 | 2018-10-01 | 2018-11-15 | 2019-09-24 | 2020-04-08 | COMP | 2021-03-15 | COMP | 2022-04-14 | COMP | 2022-02-04 | COMP | 2022-06-23 | COMP | Rule 15/16 | 33 | 215 | 235 | 276 | 0 | 49 | 938
8278 | 2018-10-01 | 2018-11-23 | 2019-03-23 | 2019-03-23 | COMP | 2019-12-27 | NOTN | 2019-12-27 | COMP | 2020-02-06 | NOTN | 2020-03-06 | COMP | Other | 37 | 81 |  | 193 |  |  | 358
8291 | 2018-10-01 | 2018-11-26 | 2019-02-13 | 2019-03-29 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-04-23 | COMP | 2019-05-28 | COMP | Rule 16 | 38 | 55 | 12 | 1 | 7 | 25 | 164
8544 | 2018-10-01 | 2018-12-08 | 2018-12-20 | 2019-01-16 | COMP | 2019-01-18 | COMP | 2019-01-18 | COMP | 2019-07-21 | INPR | 2019-03-05 | COMP | Rule 15/16 | 47 | 9 | 3 | 1 |  |  | 105
8556 | 2018-10-01 | 2018-12-10 | 2019-01-25 | 2019-01-25 | COMP | 2019-04-22 | COMP | 2019-03-12 | COMP | 2019-10-21 | INPR | 2019-07-05 | COMP | Rule 16 | 48 | 32 | 61 |  |  |  | 191
8604 | 2018-10-01 | 2018-12-11 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-06-10 | COMP | 2019-07-17 | COMP | Rule 16 | 49 | 50 | 24 | 1 | 53 | 27 | 199
8613 | 2018-10-01 | 2018-12-11 | 2019-01-07 | 2019-02-11 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-04-03 | COMP | 2019-04-26 | COMP | Rule 16 | 49 | 18 | 23 | 1 | 15 | 18 | 143
8645 | 2018-10-01 | 2018-12-14 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-14 | COMP | 2019-10-19 | COMP | 2020-03-16 | COMP | 2020-06-17 | COMP | Rule 16 | 52 | 192 | 19 | 5 | 99 | 67 | 430
8667 | 2018-10-01 | 2018-12-14 | 2019-03-06 | 2019-03-06 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-07-11 | COMP | Rule 16 | 52 | 55 | 43 | 1 | 1 | 48 | 195
8707 | 2018-10-01 | 2018-12-19 | 2019-01-28 | 2019-02-13 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-08-13 | COMP | 2019-09-10 | COMP | Rule 16 | 55 | 26 | 15 | 1 | 113 | 20 | 237
8734 | 2018-10-01 | 2018-12-20 | 2019-01-31 | 2019-01-31 | COMP | 2019-03-20 | COMP | 2019-03-20 | COMP | 2019-04-24 | COMP | 2019-06-05 | COMP | Rule 16 | 56 | 28 | 34 | 1 | 26 | 30 | 170
8999 | 2018-10-01 | 2019-01-11 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-11 | COMP | 2019-03-12 | COMP | 2019-03-08 | COMP | 2019-04-13 | COMP | Rule 16 | 70 | 6 | 16 | 21 | 0 | 24 | 133
9076 | 2018-10-01 | 2019-01-16 | 2019-07-09 | 2019-07-09 | COMP | 2019-12-17 | COMP | 2020-01-08 | COMP | 2023-01-28 | INPR | 2020-08-31 | COMP | Rule 16 | 73 | 121 | 112 | 15 |  |  | 483
9684 | 2018-10-01 | 2019-02-11 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-09 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-07-31 | COMP | Rule 16 | 90 | 53 | 11 | 11 | 1 | 48 | 209
9992 | 2018-10-01 | 2019-02-26 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-11 | NOTN | 2019-05-14 | COMP | 2019-05-21 | COMP | 2019-06-10 | COMP | Other | 100 | 33 |  | 24 | 6 | 14 | 173
10263 | 2018-10-01 | 2019-03-07 | 2019-05-25 | 2019-06-29 | COMP | 2019-08-20 | COMP | 2019-05-30 | COMP | 2019-12-30 | COMP | 2020-02-12 | COMP | Rule 15/16 | 107 | 57 | 36 |  | 147 | 31 | 342
10795 | 2018-10-01 | 2019-03-30 | 2019-05-21 | 2020-01-04 | COMP | 2020-01-16 | COMP | 2020-02-13 | COMP | 2020-03-10 | COMP | 2020-06-10 | COMP | Rule 16 | 123 | 37 | 9 | 20 | 18 | 66 | 425
11149 | 2018-10-01 | 2019-04-15 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-21 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2019-12-09 | COMP | Rule 16 | 134 | 63 | 29 | 67 | 1 | 9 | 298
11722 | 2018-10-01 | 2019-05-08 | 2019-09-01 | 2019-09-01 | COMP | 2019-11-01 | COMP | 2019-11-27 | COMP | 2019-11-04 | COMP | 2019-12-31 | COMP | Rule 16 | 151 | 81 | 44 | 18 | 0 | 22 | 313
11749 | 2018-10-01 | 2019-05-09 | 2019-08-20 | 2019-08-20 | COMP | 2019-12-11 | COMP | 2020-01-07 | COMP | 2020-02-05 | COMP | 2020-03-06 | COMP | Rule 16 | 152 | 72 | 78 | 18 | 21 | 22 | 358
12364 | 2018-10-01 | 2019-06-03 | 2019-09-28 | 2019-09-28 | COMP | 2019-10-24 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-01-15 | COMP | Rule 15/16 | 168 | 83 | 19 | 17 | 1 | 39 | 323
12925 | 2018-10-01 | 2019-07-02 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2021-03-27 | INPR | 2020-02-28 | COMP | Rule 16 | 189 | 11 | 4 | 1 |  |  | 353
13609 | 2018-10-01 | 2019-08-02 | 2019-09-21 | 2019-09-21 | COMP | 2019-11-13 | COMP | 2022-02-02 | COMP | 2021-12-23 | COMP | 2022-03-16 | COMP | Rule 16 | 211 | 35 | 37 | 559 | 0 | 30 | 869
17685 | 2018-10-01 | 2020-02-24 | 2020-05-07 | 2020-05-07 | COMP | 2020-06-03 | COMP | 2020-06-25 | COMP | 2020-11-24 | COMP | 2021-03-19 | COMP | Rule 15/16 | 349 | 54 | 19 | 17 | 107 | 78 | 619
20704 | 2018-10-01 | 2020-07-02 | 2021-05-18 | 2021-05-18 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2021-05-24 | COMP | 2021-08-27 | COMP | Rule 16 | 441 | 221 | 4 | 1 | 2 | 68 | 732
3976 | 2018-10-02 | 2018-11-04 | 2018-12-18 | 2018-12-18 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-01 | COMP | 2019-03-08 | COMP | Rule 16 | 24 | 29 | 30 | 1 | 2 | 25 | 107
4016 | 2018-10-02 | 2018-11-30 | 2019-02-08 | 2019-02-02 | COMP | 2019-02-26 | COMP | 2019-06-19 | COMP | 2019-02-26 | COMP | 2019-06-18 | COMP | Other | 41 | 48 | 16 | 81 | 0 |  | 178
7383 | 2018-10-02 | 2018-10-09 | 2018-12-21 | 2018-12-21 | COMP | 2018-12-28 | NOTN | 2018-12-28 | COMP | 2018-12-21 | COMP | 2019-01-25 | COMP | Other | 6 | 51 |  | 5 | 0 | 19 | 78
7449 | 2018-10-02 | 2018-10-15 | 2018-12-08 | 2018-12-08 | COMP | 2019-06-12 | COMP | 2018-12-19 | COMP | 2020-04-26 | INPR | 2020-01-06 | COMP | Rule 16 | 10 | 37 | 128 |  |  |  | 315
7450 | 2018-10-02 | 2018-10-15 | 2018-12-08 | 2018-12-08 | COMP | 2019-06-12 | COMP | 2018-12-19 | COMP | 2020-04-26 | INPR | 2020-01-06 | COMP | Rule 16 | 10 | 37 | 128 |  |  |  | 315
7451 | 2018-10-02 | 2018-10-15 | 2018-12-08 | 2018-12-08 | COMP | 2019-06-26 | COMP | 2018-12-19 | COMP | 2020-04-26 | INPR | 2020-01-06 | COMP | Rule 16 | 10 | 37 | 138 |  |  |  | 315
7452 | 2018-10-02 | 2018-10-15 | 2018-12-08 | 2018-12-08 | COMP | 2019-06-12 | COMP | 2018-12-19 | COMP | 2020-04-26 | INPR | 2020-01-06 | COMP | Rule 16 | 10 | 37 | 128 |  |  |  | 315
7480 | 2018-10-02 | 2018-10-16 | 2018-12-19 | 2018-12-19 | COMP | 2019-02-08 | COMP | 2019-02-13 | COMP | 2019-02-11 | COMP | 2019-03-22 | COMP | Rule 16 | 11 | 44 | 35 | 4 | 0 | 27 | 117
7593 | 2018-10-02 | 2018-10-23 | 2019-09-06 | 2019-09-06 | COMP | 2020-01-15 | COMP | 2020-08-07 | COMP | 2020-08-27 | COMP | 2020-09-09 | COMP | Rule 15/16 | 16 | 219 | 89 | 145 | 15 | 9 | 488
7594 | 2018-10-02 | 2018-10-23 | 2019-09-06 | 2019-09-06 | COMP | 2020-06-13 | COMP | 2020-08-21 | COMP | 2020-08-27 | COMP | 2020-09-09 | COMP | Rule 15/16 | 16 | 219 | 193 | 50 | 5 | 9 | 488
7595 | 2018-10-02 | 2018-10-23 | 2019-09-06 | 2019-09-06 | COMP | 2020-06-13 | COMP | 2020-06-13 | COMP | 2020-08-27 | COMP | 2020-09-09 | COMP | Rule 15/16 | 16 | 219 | 193 | 0 | 54 | 9 | 488
7696 | 2018-10-02 | 2018-10-25 | 2019-01-03 | 2019-01-03 | COMP | 2019-02-01 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-05-13 | COMP | Rule 16 | 18 | 46 | 21 | 43 | 1 | 29 | 153
7719 | 2018-10-02 | 2018-10-26 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-25 | COMP | 2019-03-07 | COMP | 2019-07-21 | INPR | 2019-04-13 | COMP | Rule 16 | 19 | 64 | 17 | 9 |  |  | 132
7911 | 2018-10-02 | 2018-11-05 | 2019-01-21 | 2019-01-21 | COMP | 2019-02-25 | COMP | 2019-03-20 | COMP | 2019-03-30 | COMP | 2019-05-15 | COMP | Rule 15/16 | 25 | 50 | 24 | 18 | 8 | 33 | 155
7993 | 2018-10-02 | 2018-11-09 | 2019-02-26 | 2019-02-26 | COMP | 2019-05-03 | COMP | 2019-05-20 | COMP | 2022-06-07 | COMP | 2022-07-08 | COMP | Rule 16 | 29 | 71 | 49 | 12 | 769 | 22 | 947
8024 | 2018-10-02 | 2018-11-11 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-23 | COMP | 2019-07-29 | COMP | 2023-11-11 | INPR | 2020-03-02 | COMP | Rule 16 | 29 | 157 | 17 | 5 |  |  | 353
8197 | 2018-10-02 | 2018-11-17 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-04-09 | COMP | 2019-04-06 | COMP | Rule 16 | 33 | 82 | 5 | 1 | 11 |  | 127
8300 | 2018-10-02 | 2018-11-26 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-10 | COMP | 2019-06-18 | COMP | 2019-09-05 | COMP | 2019-10-03 | COMP | Rule 16 | 37 | 98 | 19 | 27 | 56 | 21 | 253
8554 | 2018-10-02 | 2018-12-10 | 2019-01-26 | 2019-01-26 | COMP | 2019-02-12 | COMP | 2019-04-11 | COMP | 2019-09-02 | INPR | 2019-05-13 | COMP | Rule 16 | 47 | 32 | 12 | 42 |  |  | 153
8912 | 2018-10-02 | 2019-01-05 | 2019-04-13 | 2019-04-13 | COMP | 2019-07-16 | COMP | 2019-07-17 | COMP | 2019-08-13 | COMP | 2019-08-30 | COMP | Rule 16 | 64 | 68 | 65 | 2 | 20 | 14 | 230
9317 | 2018-10-02 | 2019-01-30 | 2019-03-07 | 2019-07-27 | COMP | 2019-09-23 | COMP | 2019-04-23 | COMP | 2019-10-02 | COMP | 2020-01-02 | COMP | Rule 16 | 81 | 26 | 40 |  | 114 | 62 | 313
9587 | 2018-10-02 | 2019-02-07 | 2019-04-10 | 2019-04-10 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-12-17 | COMP | 2020-01-13 | COMP | Rule 16 | 87 | 44 | 16 | 1 | 159 | 18 | 320
10060 | 2018-10-02 | 2019-02-28 | 2019-05-24 | 2019-05-30 | COMP | 2019-06-17 | COMP | 2019-07-02 | COMP | 2020-10-26 | COMP | 2020-12-01 | COMP | Rule 15/16 | 101 | 62 | 13 | 12 | 334 | 24 | 544
10079 | 2018-10-02 | 2019-03-01 | 2019-03-27 | 2019-03-27 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-06-11 | COMP | 2020-08-14 | COMP | Rule 15/16 | 102 | 19 | 226 | 1 | 81 | 47 | 471
10274 | 2018-10-02 | 2019-03-08 | 2019-06-25 | 2019-06-25 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | 2019-07-25 | COMP | 2019-09-06 | COMP | Rule 16 | 107 | 77 | 22 | 2 | 0 | 30 | 234
10325 | 2018-10-02 | 2019-03-11 | 2019-11-12 | 2019-11-12 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | 2023-03-17 | COMP | 2023-06-21 | COMP | Rule 16 | 108 | 173 | 264 | 1 | 577 | 67 | 1185
10722 | 2018-10-02 | 2019-03-28 | 2019-05-31 | 2019-05-31 | COMP | 2020-11-13 | COMP | 2019-11-25 | COMP | 2021-12-14 | COMP | 2022-02-03 | COMP | Rule 15/16 | 121 | 46 | 369 |  | 516 | 37 | 840
10910 | 2018-10-02 | 2019-04-06 | 2019-06-28 | 2019-06-28 | COMP | 2020-02-03 | COMP | 2020-03-23 | COMP | 2020-10-06 | COMP | 2020-10-08 | COMP | Rule 15/16 | 127 | 59 | 149 | 35 | 140 | 3 | 509
11041 | 2018-10-02 | 2019-04-10 | 2019-07-18 | 2019-07-18 | COMP | 2021-02-25 | COMP | 2021-03-10 | COMP | 2021-03-18 | COMP | 2021-04-21 | COMP | Rule 15/16 | 130 | 70 | 404 | 10 | 7 | 25 | 641
11146 | 2018-10-02 | 2019-04-15 | 2019-10-25 | 2019-10-25 | COMP | 2019-12-23 | COMP | 2020-07-20 | COMP | 2021-08-17 | COMP | 2021-09-02 | COMP | Rule 16 | 133 | 137 | 39 | 146 | 272 | 13 | 735
11848 | 2018-10-02 | 2019-05-14 | 2019-07-30 | 2019-12-16 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-06-09 | COMP | 2020-07-17 | COMP | Rule 16 | 154 | 54 | 123 | 1 | 0 | 28 | 451
12196 | 2018-10-02 | 2019-05-28 | 2019-08-28 | 2019-09-16 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2019-10-31 | COMP | 2020-07-14 | COMP | Rule 16 | 163 | 66 | 40 | 1 | 0 | 170 | 448
12615 | 2018-10-02 | 2019-06-17 | 2020-05-21 | 2020-05-21 | COMP | 2020-09-08 | COMP | 2020-11-04 | COMP | 2021-05-03 | COMP | 2022-06-12 | COMP | Rule 15/16 | 177 | 235 | 77 | 42 | 122 | 281 | 929
12874 | 2018-10-02 | 2019-06-26 | 2019-09-21 | 2019-09-21 | COMP | 2020-01-07 | COMP | 2019-11-22 | COMP | 2020-03-24 | COMP | 2020-04-03 | COMP | Rule 16 | 184 | 61 | 72 |  | 82 | 9 | 377
4137 | 2018-10-03 | 2019-03-25 | 2019-07-16 | 2019-07-16 | COMP | 2019-07-30 | COMP | 2019-09-16 | COMP | 2019-10-18 | COMP | 2020-02-19 | COMP | Rule 16 | 117 | 80 | 11 | 34 | 25 | 82 | 344
7310 | 2018-10-03 | 2018-10-07 | 2019-04-05 | 2019-04-05 | COMP | 2019-06-24 | COMP | 2019-08-05 | COMP | 2019-08-07 | COMP | 2021-08-04 | COMP | Rule 16 | 3 | 123 | 56 | 30 | 3 | 502 | 713
7413 | 2018-10-03 | 2018-10-12 | 2018-12-21 | 2018-12-21 | COMP | 2018-12-20 | NOTN | 2019-01-02 | COMP | 2018-12-20 | COMP | 2019-02-21 | COMP | Other | 8 | 48 |  | 7 | 0 | 35 | 95
7676 | 2018-10-03 | 2018-10-25 | 2019-03-05 | 2019-03-05 | COMP | 2019-03-05 | NOTN | 2019-04-17 | COMP | 2019-03-05 | COMP | 2019-05-14 | COMP | Other | 17 | 87 |  | 32 | 0 | 20 | 153
7861 | 2018-10-03 | 2018-11-02 | 2018-12-20 | 2019-05-24 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-04-22 | COMP | 2019-07-15 | COMP | Rule 16 | 23 | 32 | 18 | 1 | 0 | 18 | 195
7947 | 2018-10-03 | 2018-11-08 | 2019-01-30 | 2019-01-31 | COMP | 2019-04-09 | COMP | 2019-04-19 | COMP | 2019-04-17 | COMP | 2019-05-23 | COMP | Rule 16 | 27 | 54 | 48 | 9 | 0 | 25 | 160
8043 | 2018-10-03 | 2018-11-13 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-06 | COMP | 2019-04-10 | COMP | 2019-04-23 | COMP | 2019-05-13 | COMP | Rule 16 | 29 | 72 | 5 | 26 | 10 | 15 | 152
8097 | 2018-10-03 | 2018-11-15 | 2019-03-12 | 2019-03-12 | COMP | 2019-03-21 | COMP | 2019-04-03 | INPR | 2019-03-13 | COMP | 2019-11-25 | COMP | Rule 16 | 31 | 78 | 8 |  |  |  | 288
8252 | 2018-10-03 | 2018-11-21 | 2019-02-12 | 2019-02-12 | COMP | 2019-03-19 | COMP | 2019-06-24 | COMP | 2019-07-09 | COMP | 2019-07-17 | COMP | Rule 16 | 35 | 55 | 25 | 69 | 11 | 7 | 197
8352 | 2018-10-03 | 2018-11-27 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-02 | COMP | 2019-05-05 | COMP | 2019-04-24 | COMP | 2019-06-15 | COMP | Rule 16 | 37 | 80 | 8 | 24 | 0 | 29 | 175
8359 | 2018-10-03 | 2018-11-28 | 2019-03-16 | 2019-03-16 | COMP | 2019-08-05 | COMP | 2019-08-19 | COMP | 2020-10-19 | COMP | 2020-12-01 | COMP | Rule 15/16 | 38 | 74 | 99 | 11 | 296 | 29 | 543
8431 | 2018-10-03 | 2018-11-30 | 2019-01-28 | 2019-01-28 | COMP | 2019-04-02 | COMP | 2019-05-22 | COMP | 2019-05-24 | COMP | 2019-07-09 | COMP | Rule 16 | 40 | 39 | 46 | 37 | 3 | 31 | 191
8803 | 2018-10-03 | 2018-12-29 | 2019-05-18 | 2019-05-18 | COMP | 2019-06-10 | COMP | 2019-06-11 | COMP | 2019-06-17 | COMP | 2019-07-22 | COMP | Rule 16 | 59 | 97 | 15 | 2 | 5 | 25 | 200
9005 | 2018-10-03 | 2019-01-12 | 2019-04-02 | 2019-04-02 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-12-28 | INPR | 2019-08-05 | COMP | Rule 16 | 68 | 55 | 80 | 1 |  |  | 210
9237 | 2018-10-03 | 2019-01-24 | 2019-02-07 | 2019-02-07 | COMP | 2019-06-04 | COMP | 2019-06-05 | INPR | 2020-02-29 | REQD | 2019-11-03 | COMP | Rule 16 | 76 | 11 | 82 |  |  |  | 273
9308 | 2018-10-03 | 2019-01-28 | 2019-07-23 | 2020-03-30 | COMP | 2020-12-08 | COMP | 2020-12-08 | INPR | 2023-02-25 | REQD | 2020-11-06 | COMP | Rule 15/16 | 78 | 124 | 177 |  |  |  | 529
9311 | 2018-10-03 | 2019-01-28 | 2019-08-14 | 2019-08-14 | COMP | 2019-10-04 | COMP | 2019-10-31 | COMP | 2019-12-03 | COMP | 2020-02-29 | COMP | Rule 15/16 | 78 | 140 | 37 | 20 | 21 | 60 | 351
9412 | 2018-10-03 | 2019-02-01 | 2019-03-29 | 2019-04-03 | COMP | 2019-04-15 | COMP | 2019-04-16 | COMP | 2019-09-25 | COMP | 2019-10-02 | COMP | Rule 16 | 82 | 40 | 9 | 2 | 114 | 6 | 251
10406 | 2018-10-03 | 2019-03-14 | 2019-05-29 | 2019-05-29 | COMP | 2019-10-21 | COMP | 2019-12-30 | COMP | 2020-01-08 | COMP | 2020-01-15 | COMP | Rule 15/16 | 110 | 54 | 102 | 47 | 7 | 6 | 321
10475 | 2018-10-03 | 2019-03-18 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-29 | COMP | 2019-10-09 | COMP | 2019-10-11 | COMP | 2019-12-12 | COMP | Rule 16 | 112 | 35 | 18 | 94 | 3 | 42 | 299
10868 | 2018-10-03 | 2019-04-02 | 2019-06-01 | 2019-06-01 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-11-14 | COMP | 2019-12-06 | COMP | Rule 16 | 123 | 43 | 60 | 1 | 57 | 15 | 295
11059 | 2018-10-03 | 2019-04-11 | 2019-04-25 | 2019-04-25 | COMP | 2019-07-12 | COMP | 2019-07-12 | INPR | 2019-08-19 | COMP | 2019-10-01 | COMP | Rule 16 | 130 | 11 | 55 |  |  |  | 250
11400 | 2018-10-03 | 2019-04-25 | 2019-09-17 | 2019-10-15 | COMP | 2019-10-24 | COMP | 2019-12-12 | COMP | 2019-12-09 | COMP | 2020-01-17 | COMP | Rule 15/16 | 140 | 101 | 8 | 33 | 0 | 25 | 323
11421 | 2018-10-03 | 2019-04-26 | 2019-05-21 | 2019-05-21 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2020-06-11 | COMP | 2020-07-07 | COMP | Rule 16 | 141 | 18 | 85 | 1 | 183 | 19 | 442
11482 | 2018-10-03 | 2019-04-29 | 2019-11-26 | 2019-11-26 | COMP | 2020-01-09 | COMP | 2020-05-11 | COMP | 2020-06-09 | COMP | 2020-07-09 | COMP | Rule 16 | 142 | 148 | 29 | 86 | 21 | 23 | 444
11724 | 2018-10-03 | 2019-05-08 | 2019-07-11 | 2019-07-27 | COMP | 2019-08-02 | COMP | 2019-10-04 | COMP | 2019-09-10 | COMP | 2020-02-08 | COMP | Rule 15/16 | 149 | 45 | 5 | 45 | 0 | 85 | 337
12108 | 2018-10-03 | 2019-05-23 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-23 | COMP | 2020-02-28 | COMP | 2020-05-06 | COMP | 2021-02-06 | COMP | Rule 16 | 160 | 33 | 10 | 151 | 49 | 190 | 588
12980 | 2018-10-03 | 2019-07-02 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2019-12-17 | COMP | 2020-01-15 | COMP | Rule 16 | 187 | 93 | 20 | 1 | 5 | 20 | 321
13158 | 2018-10-03 | 2019-07-13 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-21 | COMP | 2019-11-06 | COMP | 2019-11-12 | COMP | 2020-01-07 | COMP | Rule 15/16 | 194 | 58 | 13 | 13 | 4 | 37 | 315
13355 | 2018-10-03 | 2019-07-22 | 2020-01-07 | 2020-01-07 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2022-01-25 | COMP | 2022-02-07 | COMP | Rule 16 | 200 | 116 | 227 | 1 | 292 | 10 | 841
13596 | 2018-10-03 | 2019-08-01 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-10 | COMP | 2019-11-04 | COMP | 2020-07-14 | COMP | 2020-09-16 | COMP | Rule 16 | 208 | 37 | 14 | 18 | 174 | 46 | 492
7270 | 2018-10-04 | 2018-10-04 | 2019-01-12 | 2019-01-12 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-04-15 | COMP | 2019-06-17 | COMP | Rule 16 | 1 | 67 | 41 | 1 | 24 | 45 | 175
7516 | 2018-10-04 | 2018-10-18 | 2018-11-10 | 2018-11-10 | COMP | 2019-03-07 | COMP | 2019-04-01 | COMP | 2019-03-20 | COMP | 2019-04-11 | COMP | Rule 16 | 11 | 17 | 77 | 18 | 0 | 9 | 129
7664 | 2018-10-04 | 2018-10-24 | 2019-02-01 | 2019-02-01 | COMP | 2019-02-01 | NOTN | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-03-13 | COMP | Other | 15 | 67 |  | 1 | 1 | 28 | 108
7746 | 2018-10-04 | 2018-10-29 | 2019-03-29 | 2019-08-24 | COMP | 2019-10-30 | COMP | 2019-11-06 | COMP | 2019-05-22 | COMP | 2019-12-20 | COMP | Rule 16 | 18 | 103 | 47 | 6 | 0 | 30 | 304
8102 | 2018-10-04 | 2018-11-15 | 2019-05-09 | 2019-05-09 | COMP | 2019-05-31 | COMP | 2019-09-10 | COMP | 2019-07-12 | COMP | 2020-03-10 | COMP | Rule 16 | 30 | 120 | 16 | 71 | 0 | 124 | 357
8116 | 2018-10-04 | 2018-11-15 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-10 | COMP | 2019-04-11 | COMP | 2019-05-29 | COMP | 2019-07-08 | COMP | Rule 16 | 30 | 92 | 8 | 2 | 34 | 28 | 189
8409 | 2018-10-04 | 2018-11-29 | 2019-02-01 | 2019-02-01 | COMP | 2019-03-20 | COMP | 2019-03-28 | COMP | 2019-08-13 | COMP | 2019-08-22 | COMP | Rule 16 | 38 | 44 | 33 | 7 | 97 | 8 | 222
8541 | 2018-10-04 | 2018-12-07 | 2019-03-11 | 2021-03-01 | COMP | 2021-04-05 | COMP | 2021-04-16 | COMP | 2022-02-15 | COMP | 2022-03-18 | COMP | Rule 15/16 | 44 | 63 | 26 | 10 | 211 | 23 | 868
8549 | 2018-10-04 | 2018-12-08 | 2019-01-31 | 2019-01-31 | COMP | 2019-03-26 | COMP | 2019-04-06 | COMP | 2019-04-07 | COMP | 2019-05-08 | COMP | Rule 16 | 44 | 36 | 38 | 9 | 0 | 23 | 148
8710 | 2018-10-04 | 2018-12-18 | 2019-01-15 | 2019-01-15 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-05-07 | COMP | 2019-05-14 | COMP | Rule 16 | 51 | 19 | 35 | 1 | 45 | 6 | 152
9022 | 2018-10-04 | 2019-01-13 | 2019-03-01 | 2019-03-01 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-07-04 | COMP | 2019-07-18 | COMP | Other | 67 | 33 | 59 | 1 | 30 | 10 | 197
9101 | 2018-10-04 | 2019-01-16 | 2019-03-31 | 2019-03-31 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-09-22 | INPR | 2019-06-15 | COMP | Rule 16 | 70 | 51 | 12 | 1 |  |  | 174
9304 | 2018-10-04 | 2019-01-28 | 2019-04-26 | 2019-04-26 | COMP | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-10-29 | COMP | 2019-12-14 | COMP | Rule 16 | 77 | 64 | 47 | 1 | 84 | 31 | 299
9333 | 2018-10-04 | 2019-01-30 | 2019-03-27 | 2019-03-27 | COMP | 2019-06-10 | COMP | 2019-07-03 | COMP | 2019-11-21 | COMP | 2020-01-15 | COMP | Rule 16 | 79 | 40 | 53 | 18 | 99 | 36 | 320
9425 | 2018-10-04 | 2019-02-04 | 2019-05-01 | 2019-12-17 | COMP | 2020-01-30 | COMP | 2020-02-11 | COMP | 2020-11-18 | COMP | 2021-02-26 | COMP | Rule 16 | 82 | 62 | 30 | 9 | 198 | 67 | 601
9676 | 2018-10-04 | 2019-02-11 | 2019-05-25 | 2019-05-25 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-07-11 | COMP | 2019-11-15 | COMP | Rule 16 | 87 | 74 | 84 | 1 | 0 | 38 | 281
9720 | 2018-10-04 | 2019-02-12 | 2019-04-05 | 2019-04-05 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-14 | COMP | 2019-05-30 | COMP | Rule 16 | 88 | 38 | 20 | 1 | 9 | 12 | 163
9776 | 2018-10-04 | 2019-02-15 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-09-22 | INPR | 2019-06-04 | COMP | Rule 16 | 91 | 43 | 11 | 1 |  |  | 166
9785 | 2018-10-04 | 2019-02-14 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-30 | COMP | 2019-05-31 | COMP | 2019-09-27 | COMP | 2019-11-05 | COMP | Rule 16 | 90 | 51 | 24 | 2 | 84 | 28 | 274
9884 | 2018-10-04 | 2019-02-21 | 2019-05-07 | 2019-05-07 | COMP | 2019-05-21 | COMP | 2019-08-08 | COMP | 2019-07-24 | COMP | 2019-09-13 | COMP | Rule 16 | 94 | 54 | 11 | 56 | 0 | 26 | 237
11662 | 2018-10-04 | 2019-05-07 | 2019-07-29 | 2019-09-12 | COMP | 2019-10-15 | COMP | 2019-12-04 | COMP | 2020-01-21 | COMP | 2020-03-12 | COMP | Rule 15/16 | 147 | 58 | 24 | 34 | 32 | 37 | 359
11843 | 2018-10-04 | 2019-05-14 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-08 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-01-07 | COMP | Rule 16 | 152 | 96 | 31 | 2 | 1 | 37 | 314
12933 | 2018-10-04 | 2019-07-01 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2020-06-04 | COMP | 2020-07-21 | COMP | Rule 15/16 | 185 | 39 | 9 | 1 | 187 | 34 | 451
13654 | 2018-10-04 | 2019-08-06 | 2019-10-06 | 2019-10-06 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-10-16 | COMP | 2020-11-16 | COMP | Rule 15/16 | 210 | 43 | 256 | 1 | 6 | 21 | 533
13681 | 2018-10-04 | 2019-08-05 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-11-06 | COMP | 2019-12-03 | COMP | Rule 16 | 209 | 35 | 14 | 1 | 20 | 17 | 291
17079 | 2018-10-04 | 2020-01-29 | 2020-05-15 | 2020-05-15 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2021-09-10 | COMP | 2021-10-15 | COMP | Rule 16 | 329 | 77 | 118 | 1 | 217 | 26 | 763
7281 | 2018-10-05 | 2018-10-05 | 2018-10-17 | 2018-10-17 | COMP | 2018-11-14 | COMP | 2019-03-01 | COMP | 2019-03-12 | COMP | 2019-03-28 | COMP | Rule 16 | 1 | 9 | 20 | 72 | 8 | 13 | 118
7316 | 2018-10-05 | 2018-10-08 | 2018-12-03 | 2018-12-03 | COMP | 2019-01-10 | COMP | 2019-01-31 | COMP | 2019-07-21 | INPR | 2019-03-13 | COMP | Rule 16 | 2 | 38 | 27 | 15 |  |  | 107
7596 | 2018-10-05 | 2018-10-23 | 2019-06-01 | 2019-06-01 | COMP | 2019-07-01 | COMP | 2019-07-23 | COMP | 2019-07-30 | COMP | 2019-08-20 | COMP | Rule 15/16 | 13 | 151 | 21 | 16 | 6 | 16 | 219
7751 | 2018-10-05 | 2018-10-29 | 2018-12-31 | 2018-12-31 | COMP | 2019-03-13 | COMP | 2019-08-13 | COMP | 2019-08-19 | COMP | 2019-09-13 | COMP | Rule 16 | 17 | 42 | 50 | 108 | 5 | 19 | 236
7792 | 2018-10-05 | 2018-10-31 | 2018-12-07 | 2019-04-01 | COMP | 2021-05-27 | NOTN | 2021-05-27 | COMP | 2023-11-22 | COMP | 2023-10-23 | COMP | Rule 16 | 19 | 25 |  | 545 | 626 |  | 1268
8181 | 2018-10-05 | 2018-11-18 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-20 | NOTN | 2019-05-20 | COMP | 2019-05-03 | COMP | 2019-06-24 | COMP | Rule 16 | 30 | 124 |  | 2 | 0 | 25 | 179
8397 | 2018-10-05 | 2018-11-30 | 2019-03-05 | 2019-03-05 | COMP | 2019-05-22 | COMP | 2019-06-04 | COMP | 2019-06-05 | COMP | 2019-07-02 | COMP | Rule 16 | 38 | 64 | 57 | 9 | 2 | 20 | 185
9249 | 2018-10-05 | 2019-01-24 | 2019-05-09 | 2019-05-09 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-10-30 | COMP | 2019-11-22 | COMP | Rule 16 | 74 | 75 | 41 | 1 | 82 | 17 | 285
9301 | 2018-10-05 | 2019-01-28 | 2019-04-26 | 2019-05-01 | COMP | 2019-05-07 | COMP | 2019-05-07 | NOTN | 2019-07-30 | COMP | 2019-08-14 | COMP | Rule 16 | 76 | 64 | 5 |  |  |  | 215
9448 | 2018-10-05 | 2019-02-04 | 2019-04-10 | 2019-04-10 | COMP | 2019-07-10 | COMP | 2019-07-25 | COMP | 2019-08-07 | COMP | 2019-09-12 | COMP | Rule 16 | 81 | 47 | 64 | 12 | 10 | 26 | 235
9521 | 2018-10-05 | 2019-02-06 | 2019-02-27 | 2021-02-11 | COMP | 2021-10-14 | COMP | 2022-04-13 | COMP | 2022-06-21 | COMP | 2022-07-15 | COMP | Rule 16 | 83 | 15 | 172 | 125 | 48 | 18 | 949
10659 | 2018-10-05 | 2019-03-25 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-19 | COMP | 2020-06-01 | COMP | 2020-06-18 | COMP | 2020-07-29 | COMP | Rule 16 | 115 | 47 | 16 | 239 | 14 | 30 | 456
10681 | 2018-10-05 | 2019-03-25 | 2019-07-08 | 2019-07-17 | COMP | 2019-08-06 | COMP | 2019-08-07 | COMP | 2019-08-27 | COMP | 2019-09-19 | COMP | Rule 16 | 115 | 74 | 15 | 2 | 15 | 17 | 240
10683 | 2018-10-05 | 2019-03-25 | 2019-05-25 | 2019-05-25 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-06-18 | COMP | 2020-08-01 | COMP | Rule 16 | 115 | 45 | 129 | 1 | 140 | 32 | 458
10791 | 2018-10-05 | 2019-03-29 | 2019-05-13 | 2019-07-17 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2019-08-22 | COMP | 2019-09-24 | COMP | Rule 16 | 119 | 32 | 24 | 1 | 4 | 23 | 243
11641 | 2018-10-05 | 2019-05-06 | 2019-06-11 | 2019-06-11 | COMP | 2019-06-26 | COMP | 2019-07-17 | COMP | 2019-07-22 | COMP | 2019-08-27 | COMP | Rule 16 | 145 | 26 | 12 | 15 | 4 | 27 | 224
11760 | 2018-10-05 | 2019-05-10 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-18 | COMP | 2019-11-21 | COMP | 2019-11-19 | COMP | 2020-02-05 | COMP | Rule 16 | 149 | 98 | 36 | 4 | 0 | 50 | 333
11842 | 2018-10-05 | 2019-05-14 | 2019-06-18 | 2019-06-18 | COMP | 2019-07-03 | COMP | 2019-07-29 | COMP | 2019-08-28 | COMP | 2019-10-04 | COMP | Rule 16 | 151 | 25 | 12 | 18 | 23 | 27 | 251
11866 | 2018-10-05 | 2019-05-15 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-26 | COMP | 2019-08-28 | COMP | 2020-01-08 | COMP | 2020-02-06 | COMP | Rule 16 | 152 | 53 | 20 | 3 | 90 | 21 | 334
13728 | 2018-10-05 | 2019-08-07 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-12 | COMP | 2020-02-10 | COMP | 2020-10-20 | COMP | 2020-11-17 | COMP | Rule 16 | 210 | 62 | 7 | 60 | 179 | 20 | 533
15483 | 2018-10-05 | 2019-11-04 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-06 | COMP | 2020-04-07 | COMP | 2020-07-28 | COMP | 2020-11-03 | COMP | Rule 15/16 | 272 | 78 | 27 | 2 | 80 | 70 | 524
8898 | 2018-10-06 | 2019-01-04 | 2019-02-05 | 2019-02-05 | COMP | 2019-03-21 | NOTN | 2019-03-21 | COMP | 2019-02-26 | NOTN | 2019-04-25 | COMP | Other | 60 | 22 |  | 32 |  |  | 137
9606 | 2018-10-06 | 2019-02-08 | 2019-07-15 | 2019-07-15 | COMP | 2020-01-10 | COMP | 2020-06-22 | COMP | 2023-11-11 | INPR | 2020-08-11 | COMP | Rule 16 | 84 | 109 | 124 | 114 |  |  | 464
3936 | 2018-10-07 | 2018-10-22 | 2018-12-17 | 2018-12-14 | COMP | 2019-01-28 | COMP | 2019-10-30 | COMP | 2019-11-05 | COMP | 2019-12-09 | COMP | Rule 16 | 11 | 38 | 29 | 194 | 5 | 22 | 293
3937 | 2018-10-07 | 2018-10-22 | 2019-06-21 | 2019-06-21 | COMP | 2019-09-24 | COMP | 2019-12-17 | COMP | 2021-01-19 | COMP | 2021-02-02 | COMP | Rule 16 | 11 | 167 | 66 | 58 | 274 | 11 | 582
3945 | 2018-10-07 | 2018-10-22 | 2018-12-17 | 2018-12-12 | COMP | 2018-12-31 | COMP | 2020-04-02 | COMP | 2020-06-02 | COMP | 2020-12-09 | COMP | Rule 16 | 11 | 38 | 13 | 316 | 43 | 133 | 546
7675 | 2018-10-07 | 2018-10-25 | 2019-01-11 | 2019-02-12 | COMP | 2019-02-19 | COMP | 2019-05-08 | COMP | 2019-03-18 | COMP | 2019-03-16 | COMP | Rule 16 | 14 | 52 | 5 | 57 | 0 |  | 108
9481 | 2018-10-07 | 2019-02-05 | 2019-04-02 | 2019-05-07 | COMP | 2019-05-31 | COMP | 2019-07-16 | COMP | 2019-08-24 | COMP | 2019-08-19 | COMP | Rule 16 | 81 | 40 | 18 | 32 | 29 |  | 217
3975 | 2018-10-08 | 2018-11-04 | 2019-01-08 | 2019-01-08 | COMP | 2019-01-25 | COMP | 2019-01-26 | COMP | 2019-02-16 | COMP | 2019-04-15 | COMP | Rule 16 | 20 | 42 | 13 | 1 | 15 | 40 | 129
7538 | 2018-10-08 | 2018-10-18 | 2019-01-08 | 2019-01-08 | COMP | 2019-06-10 | COMP | 2019-06-19 | COMP | 2020-02-06 | COMP | 2020-06-10 | COMP | Rule 16 | 9 | 54 | 107 | 8 | 159 | 88 | 420
7539 | 2018-10-08 | 2018-10-18 | 2018-12-15 | 2018-12-15 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-11-22 | COMP | 2019-12-17 | COMP | Rule 16 | 9 | 39 | 46 | 1 | 192 | 16 | 299
7777 | 2018-10-08 | 2018-10-30 | 2018-12-18 | 2018-12-18 | COMP | 2018-12-28 | COMP | 2018-12-28 | COMP | 2019-01-28 | COMP | 2019-02-20 | COMP | Rule 16 | 17 | 33 | 8 | 1 | 20 | 17 | 91
7816 | 2018-10-08 | 2018-11-01 | 2018-12-10 | 2018-12-10 | COMP | 2018-12-24 | COMP | 2019-01-03 | COMP | 2018-12-26 | COMP | 2019-01-25 | COMP | Rule 16 | 19 | 25 | 11 | 7 | 0 | 16 | 74
7919 | 2018-10-08 | 2018-11-05 | 2019-01-16 | 2019-01-16 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-02-11 | COMP | Rule 16 | 21 | 48 | 5 | 1 | 1 | 14 | 85
7928 | 2018-10-08 | 2018-11-05 | 2019-03-24 | 2019-03-24 | COMP | 2019-04-03 | COMP | 2019-04-03 | NOTN | 2019-04-08 | COMP | 2019-04-18 | COMP | Rule 16 | 21 | 93 | 8 |  |  |  | 132
7953 | 2018-10-08 | 2018-11-06 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-28 | COMP | 2019-03-15 | COMP | 2019-09-02 | INPR | 2019-04-18 | COMP | Rule 16 | 22 | 53 | 24 | 12 |  |  | 132
8012 | 2018-10-08 | 2018-11-09 | 2018-12-24 | 2018-12-24 | COMP | 2019-02-08 | COMP | 2019-02-08 | COMP | 2019-03-12 | COMP | 2019-03-13 | COMP | Rule 16 | 25 | 29 | 32 | 1 | 22 | 2 | 106
8213 | 2018-10-08 | 2018-11-20 | 2019-09-20 | 2019-09-20 | COMP | 2020-07-13 | COMP | 2020-07-14 | COMP | 2020-12-28 | COMP | 2021-02-12 | COMP | Rule 15/16 | 31 | 210 | 204 | 2 | 115 | 33 | 590
8214 | 2018-10-08 | 2018-11-20 | 2019-01-05 | 2019-01-05 | COMP | 2019-01-22 | COMP | 2019-01-22 | COMP | 2019-01-30 | COMP | 2019-02-22 | COMP | Rule 16 | 31 | 30 | 11 | 1 | 7 | 17 | 93
8238 | 2018-10-08 | 2018-11-20 | 2019-02-02 | 2019-02-02 | COMP | 2019-02-20 | COMP | 2019-04-15 | COMP | 2019-04-23 | COMP | 2019-05-07 | COMP | Rule 16 | 31 | 49 | 12 | 39 | 7 | 11 | 145
8247 | 2018-10-08 | 2018-11-20 | 2019-03-05 | 2019-03-26 | COMP | 2019-04-02 | COMP | 2019-04-10 | COMP | 2019-04-02 | COMP | 2019-04-23 | COMP | Rule 16 | 31 | 70 | 6 | 7 | 0 | 10 | 135
8276 | 2018-10-08 | 2018-11-21 | 2019-04-03 | 2019-08-11 | COMP | 2019-08-14 | COMP | 2019-09-17 | INPR | 2019-06-19 | COMP | 2019-08-23 | COMP | Rule 15/16 | 32 | 90 | 3 |  |  |  | 221
8537 | 2018-10-08 | 2018-12-07 | 2019-03-06 | 2019-03-18 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-07-21 | INPR | 2019-04-23 | COMP | Rule 16 | 42 | 60 | 6 | 1 |  |  | 135
8578 | 2018-10-08 | 2018-12-11 | 2019-04-03 | 2019-04-03 | COMP | 2019-04-12 | COMP | 2019-09-10 | COMP | 2019-10-08 | COMP | 2019-12-02 | COMP | Rule 16 | 44 | 78 | 8 | 105 | 21 | 37 | 288
8611 | 2018-10-08 | 2018-12-11 | 2019-07-01 | 2019-08-23 | COMP | 2019-09-09 | COMP | 2019-09-27 | COMP | 2019-11-07 | COMP | 2019-12-14 | COMP | Rule 15/16 | 44 | 140 | 11 | 15 | 30 | 24 | 297
8620 | 2018-10-08 | 2018-12-13 | 2019-05-22 | 2019-05-22 | COMP | 2020-06-01 | COMP | 2020-10-30 | COMP | 2020-12-16 | COMP | 2021-01-22 | COMP | Rule 15 | 46 | 111 | 258 | 109 | 31 | 25 | 575
8812 | 2018-10-08 | 2018-12-31 | 2019-03-04 | 2019-03-04 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-08-19 | COMP | 2019-08-24 | COMP | Rule 16 | 57 | 43 | 45 | 1 | 75 | 5 | 221
8847 | 2018-10-08 | 2019-01-02 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-09-23 | COMP | 2019-10-04 | COMP | Rule 16 | 58 | 42 | 34 | 1 | 110 | 10 | 250
9033 | 2018-10-08 | 2019-01-14 | 2019-05-11 | 2019-05-11 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2019-08-09 | COMP | Rule 16 | 66 | 83 | 19 | 1 | 1 | 45 | 211
9036 | 2018-10-08 | 2019-01-14 | 2019-03-19 | 2019-03-19 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2020-05-31 | INPR | 2019-08-22 | COMP | Rule 15/16 | 66 | 45 | 52 | 1 |  |  | 220
9188 | 2018-10-08 | 2019-01-20 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-04-08 | COMP | 2019-06-10 | COMP | Rule 16 | 70 | 22 | 16 | 1 | 18 | 45 | 168
9264 | 2018-10-08 | 2019-01-25 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-12 | NOTN | 2019-06-18 | COMP | 2019-02-26 | NOTN | 2020-01-30 | COMP | Other | 74 | 55 |  | 47 |  |  | 328
9299 | 2018-10-08 | 2019-01-28 | 2019-04-09 | 2020-01-16 | COMP | 2020-02-11 | COMP | 2019-06-17 | COMP | 2021-04-08 | COMP | 2021-04-26 | COMP | Rule 16 | 75 | 51 | 18 |  | 456 | 13 | 640
9351 | 2018-10-08 | 2019-01-31 | 2019-09-12 | 2019-09-12 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-11-08 | COMP | 2020-01-09 | COMP | Rule 15/16 | 78 | 157 | 29 | 1 | 14 | 40 | 314
9352 | 2018-10-08 | 2019-01-31 | 2019-10-06 | 2019-10-06 | COMP | 2019-11-25 | INPR | 2020-02-05 | COMP | 2019-12-19 | COMP | 2020-03-04 | COMP | Rule 15/16 | 78 | 173 |  | 82 | 0 | 20 | 351
9557 | 2018-10-08 | 2019-02-07 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-12-02 | COMP | 2020-01-06 | COMP | Rule 16 | 83 | 36 | 12 | 1 | 159 | 24 | 311
9957 | 2018-10-08 | 2019-02-25 | 2019-08-06 | 2019-08-06 | COMP | 2019-10-23 | COMP | 2020-01-10 | COMP |  | INPR | 2020-03-04 | COMP | Rule 15/16 | 94 | 115 | 56 | 53 |  |  | 351
10395 | 2018-10-08 | 2019-03-14 | 2019-03-30 | 2019-03-30 | COMP | 2019-06-27 | COMP | 2019-07-16 | COMP | 2019-07-09 | COMP | 2019-10-01 | COMP | Rule 16 | 107 | 12 | 63 | 13 | 0 | 55 | 247
10482 | 2018-10-08 | 2019-03-18 | 2019-08-29 | 2019-08-29 | COMP | 2019-11-07 | COMP | 2019-11-21 | COMP | 2020-11-02 | COMP | 2020-12-02 | COMP | Rule 15/16 | 109 | 117 | 50 | 10 | 240 | 20 | 541
10716 | 2018-10-08 | 2019-03-28 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | Rule 16 | 117 | 73 | 33 | 1 | 9 | 1 | 229
10822 | 2018-10-08 | 2019-04-01 | 2019-05-09 | 2019-05-09 | COMP | 2019-05-23 | COMP | 2019-05-30 | COMP | 2019-06-05 | COMP | 2019-07-19 | COMP | Rule 16 | 119 | 29 | 11 | 5 | 5 | 32 | 196
11965 | 2018-10-08 | 2019-05-20 | 2019-09-26 | 2019-09-26 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-08-25 | COMP | 2021-01-29 | COMP | Rule 16 | 154 | 91 | 65 | 1 | 167 | 107 | 580
22670 | 2018-10-08 | 2020-10-04 | 2020-11-13 | 2020-11-13 | COMP | 2021-02-16 | COMP | 2021-04-12 | COMP | 2021-04-08 | COMP | 2021-05-10 | COMP | Rule 16 | 501 | 29 | 62 | 40 | 0 | 21 | 650
4195 | 2018-10-09 | 2019-07-01 | 2019-11-27 | 2019-11-27 | COMP | 2020-04-22 | COMP | 2020-09-02 | COMP | 2020-09-01 | COMP | 2020-10-30 | COMP | Rule 15/16 | 182 | 105 | 100 | 95 | 0 | 42 | 520
7456 | 2018-10-09 | 2018-10-15 | 2019-01-03 | 2019-01-03 | COMP | 2019-02-05 | COMP | 2019-05-17 | COMP | 2019-05-20 | COMP | 2019-06-27 | COMP | Rule 16 | 5 | 54 | 23 | 73 | 2 | 28 | 180
7656 | 2018-10-09 | 2018-10-24 | 2018-12-12 | 2018-12-12 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2018-12-22 | COMP | 2019-02-27 | COMP | Other | 12 | 33 | 28 | 1 | 0 | 25 | 95
7683 | 2018-10-09 | 2018-10-25 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-15 | COMP | 2019-06-04 | COMP | 2019-06-06 | COMP | 2019-09-04 | COMP | Rule 16 | 13 | 110 | 7 | 36 | 3 | 63 | 227
7689 | 2018-10-09 | 2018-10-25 | 2019-04-10 | 2019-04-10 | COMP | 2019-07-17 | COMP | 2019-08-06 | COMP | 2019-08-27 | COMP | 2019-09-11 | COMP | Rule 16 | 13 | 113 | 69 | 15 | 16 | 11 | 232
7801 | 2018-10-09 | 2018-11-01 | 2019-05-24 | 2019-05-24 | COMP | 2019-07-02 | COMP | 2019-07-23 | COMP | 2019-08-01 | COMP | 2019-08-20 | COMP | Rule 15/16 | 18 | 140 | 27 | 15 | 8 | 14 | 217
7802 | 2018-10-09 | 2018-11-01 | 2019-04-19 | 2019-07-22 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-01 | COMP | 2019-08-20 | COMP | Rule 15/16 | 18 | 115 | 7 | 1 | 3 | 14 | 217
7957 | 2018-10-09 | 2018-11-07 | 2019-01-07 | 2019-01-07 | COMP | 2019-02-11 | COMP | 2019-03-20 | COMP | 2019-04-29 | COMP | 2019-05-29 | COMP | Rule 16 | 22 | 39 | 25 | 27 | 29 | 22 | 159
8176 | 2018-10-09 | 2018-11-16 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-12 | NOTN | 2019-05-14 | COMP | 2019-04-10 | COMP | 2019-05-21 | COMP | Other | 28 | 69 |  | 54 | 0 | 6 | 154
8182 | 2018-10-09 | 2018-11-18 | 2019-01-16 | 2019-01-16 | COMP | 2019-03-07 | COMP | 2019-08-05 | COMP | 2019-07-26 | COMP | 2019-08-26 | COMP | Rule 16 | 28 | 39 | 35 | 106 | 0 | 16 | 221
8266 | 2018-10-09 | 2018-11-21 | 2019-01-15 | 2019-01-15 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-03-29 | INPR | 2019-12-05 | COMP | Rule 16 | 31 | 36 | 202 | 1 |  |  | 290
8395 | 2018-10-09 | 2018-11-30 | 2019-02-19 | 2019-02-19 | COMP | 2019-05-16 | COMP | 2019-06-21 | COMP | 2021-02-27 | INPR | 2019-08-01 | COMP | Rule 15/16 | 36 | 54 | 63 | 26 |  |  | 204
8528 | 2018-10-09 | 2018-12-08 | 2019-03-27 | 2019-03-27 | COMP | 2019-10-31 | COMP | 2019-11-05 | COMP | 2019-10-29 | COMP | 2019-12-16 | COMP | Rule 16 | 41 | 74 | 154 | 4 | 0 | 27 | 297
8540 | 2018-10-09 | 2018-12-07 | 2019-03-26 | 2019-12-19 | COMP | 2020-04-06 | COMP | 2020-04-21 | COMP | 2019-09-05 | COMP | 2020-05-19 | COMP | Rule 16 | 41 | 74 | 74 | 12 | 0 | 21 | 404
9217 | 2018-10-09 | 2019-01-22 | 2019-03-04 | 2019-07-05 | COMP | 2019-11-06 | COMP | 2020-01-08 | COMP | 2020-01-28 | COMP | 2020-02-20 | COMP | Rule 16 | 70 | 29 | 88 | 41 | 14 | 17 | 341
9424 | 2018-10-09 | 2019-02-04 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-08 | COMP | 2019-05-06 | COMP | 2019-04-11 | COMP | 2019-06-04 | COMP | Rule 16 | 79 | 35 | 11 | 21 | 0 | 21 | 163
9531 | 2018-10-09 | 2019-02-06 | 2019-10-18 | 2020-06-26 | COMP | 2021-03-12 | COMP | 2021-06-25 | COMP | 2023-12-02 | INPR | 2021-06-29 | COMP | Rule 16 | 81 | 179 | 178 | 75 |  |  | 684
9583 | 2018-10-09 | 2019-02-08 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-21 | COMP | 2019-05-21 | NOTN | 2023-08-04 | COMP | 2023-08-30 | COMP | Rule 16 | 83 | 59 | 14 |  |  |  | 1229
9673 | 2018-10-09 | 2019-02-11 | 2019-06-10 | 2019-06-10 | COMP | 2019-06-26 | COMP | 2019-07-08 | COMP | 2019-08-08 | COMP | 2019-09-13 | COMP | Rule 16 | 84 | 84 | 13 | 8 | 24 | 26 | 234
9734 | 2018-10-09 | 2019-02-13 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-29 | COMP | 2019-05-24 | COMP | 2019-07-15 | COMP | 2019-08-05 | COMP | Rule 16 | 86 | 31 | 23 | 20 | 35 | 16 | 206
9817 | 2018-10-09 | 2019-02-19 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-08-12 | COMP | 2019-09-17 | COMP | Rule 16 | 89 | 51 | 16 | 1 | 58 | 26 | 236
10365 | 2018-10-09 | 2019-03-12 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-24 | COMP | 2019-05-13 | COMP | 2019-09-22 | INPR | 2019-05-24 | COMP | Rule 16 | 104 | 7 | 26 | 14 |  |  | 157
10447 | 2018-10-09 | 2019-03-16 | 2019-06-03 | 2019-06-14 | COMP | 2019-07-08 | COMP | 2019-07-18 | COMP | 2019-08-13 | COMP | 2019-08-16 | COMP | Rule 16 | 107 | 55 | 16 | 9 | 19 | 4 | 215
11266 | 2018-10-09 | 2019-04-19 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-21 | COMP | 2019-09-30 | COMP | Rule 15/16 | 132 | 74 | 8 | 1 | 7 | 28 | 245
11306 | 2018-10-09 | 2019-04-22 | 2019-09-03 | 2019-09-03 | COMP | 2019-10-15 | COMP | 2019-12-10 | COMP | 2019-11-19 | COMP | 2020-01-11 | COMP | Rule 16 | 133 | 94 | 31 | 38 | 0 | 22 | 314
11403 | 2018-10-09 | 2019-04-25 | 2019-12-08 | 2020-05-12 | COMP | 2020-10-07 | COMP | 2020-12-14 | COMP | 2022-02-26 | INPR | 2021-01-12 | COMP | Rule 16 | 136 | 156 | 105 | 46 |  |  | 567
12234 | 2018-10-09 | 2019-05-28 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-29 | COMP | 2019-08-29 | INPR | 2020-05-18 | COMP | 2020-06-03 | COMP | Rule 16 | 158 | 17 | 51 |  |  |  | 414
13177 | 2018-10-09 | 2019-07-15 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-02 | NOTN | 2020-02-03 | COMP | 2020-01-07 | COMP | 2020-03-13 | COMP | Other | 191 | 97 |  | 43 | 0 | 29 | 357
14605 | 2018-10-09 | 2019-09-18 | 2020-03-26 | 2020-03-31 | COMP | 2020-04-15 | COMP | 2020-05-22 | COMP | 2020-09-15 | COMP | 2020-10-15 | COMP | Rule 15 | 237 | 130 | 12 | 28 | 81 | 23 | 509
15464 | 2018-10-09 | 2019-11-04 | 2020-01-25 | 2020-01-25 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-12-30 | COMP | Rule 16 | 270 | 54 | 40 | 1 | 1 | 197 | 559
16472 | 2018-10-09 | 2020-01-02 | 2020-02-03 | 2020-02-03 | COMP | 2020-07-03 | COMP | 2020-09-30 | COMP | 2020-10-02 | COMP | 2020-11-12 | COMP | Rule 16 | 308 | 22 | 108 | 63 | 3 | 29 | 528
19721 | 2018-10-09 | 2020-05-19 | 2020-10-09 | 2020-10-09 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2021-03-23 | COMP | 2021-04-26 | COMP | Rule 16 | 404 | 102 | 48 | 1 | 64 | 25 | 639
7782 | 2018-10-10 | 2018-10-30 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-10 | NOTN | 2019-01-10 | COMP | 2019-10-11 | COMP | 2019-12-10 | COMP | Other | 15 | 47 |  | 2 | 192 | 40 | 292
7954 | 2018-10-10 | 2018-11-07 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2020-07-10 | COMP | 2020-08-19 | COMP | Rule 15/16 | 21 | 153 | 38 | 1 | 231 | 29 | 468
7962 | 2018-10-10 | 2018-11-07 | 2019-01-03 | 2019-01-17 | COMP | 2019-01-16 | NOTN | 2019-01-17 | COMP | 2019-10-21 | INPR | 2019-06-27 | COMP | Rule 16 | 21 | 37 |  | 1 |  |  | 179
7963 | 2018-10-10 | 2018-11-07 | 2018-12-21 | 2019-01-17 | COMP | 2019-01-16 | NOTN | 2019-01-17 | INPR | 2022-07-30 | REQD | 2021-07-05 | COMP | Rule 16 | 21 | 30 |  |  |  |  | 686
8212 | 2018-10-10 | 2018-11-19 | 2019-01-26 | 2019-01-26 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-10-21 | INPR | 2019-06-13 | COMP | Rule 16 | 28 | 45 | 67 | 1 |  |  | 169
8265 | 2018-10-10 | 2018-11-21 | 2019-01-05 | 2019-01-05 | COMP | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-09-16 | COMP | 2019-09-21 | COMP | Rule 16 | 30 | 29 | 124 | 1 | 53 | 5 | 238
8461 | 2018-10-10 | 2018-12-04 | 2019-03-08 | 2019-03-08 | COMP | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-06-21 | COMP | 2019-07-12 | COMP | Rule 16 | 37 | 65 | 11 | 1 | 65 | 15 | 189
8560 | 2018-10-10 | 2018-12-10 | 2019-02-15 | 2019-02-15 | COMP | 2019-11-20 | COMP | 2020-01-16 | COMP | 2020-05-15 | COMP | 2020-07-20 | COMP | Rule 15/16 | 41 | 47 | 194 | 38 | 85 | 46 | 446
8575 | 2018-10-10 | 2018-12-11 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-21 | COMP | 2019-04-22 | COMP | 2019-05-29 | COMP | 2020-06-10 | COMP | Rule 16 | 42 | 44 | 26 | 23 | 27 | 261 | 418
8693 | 2018-10-10 | 2018-12-17 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-19 | NOTN | 2019-03-19 | COMP | 2019-04-23 | COMP | 2019-04-22 | COMP | Other | 46 | 55 |  | 9 | 26 |  | 132
8843 | 2018-10-10 | 2019-01-02 | 2019-04-05 | 2019-04-05 | COMP | 2019-10-08 | COMP | 2019-11-25 | COMP | 2020-07-02 | COMP | 2020-08-08 | COMP | Rule 16 | 56 | 66 | 130 | 34 | 152 | 27 | 460
8908 | 2018-10-10 | 2019-01-05 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-13 | COMP | 2019-04-16 | COMP | 2019-04-03 | COMP | 2019-05-15 | COMP | Other | 58 | 36 | 11 | 25 | 0 | 22 | 149
9153 | 2018-10-10 | 2019-01-19 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-05-16 | COMP | 2019-07-01 | COMP | Rule 16 | 68 | 71 | 8 | 1 | 5 | 32 | 181
9158 | 2018-10-10 | 2019-01-18 | 2019-04-26 | 2019-04-26 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-12-29 | INPR | 2019-09-03 | COMP | Rule 16 | 68 | 69 | 41 | 1 |  |  | 225
9207 | 2018-10-10 | 2019-01-22 | 2019-11-22 | 2020-04-06 | COMP | 2020-05-20 | COMP | 2020-06-16 | COMP | 2020-09-08 | COMP | 2021-03-08 | COMP | Rule 15/16 | 69 | 214 | 33 | 19 | 60 | 123 | 603
9553 | 2018-10-10 | 2019-02-07 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-06-21 | COMP | 2019-07-02 | COMP | Rule 16 | 81 | 31 | 11 | 1 | 55 | 8 | 182
9614 | 2018-10-10 | 2019-02-08 | 2019-04-10 | 2019-04-10 | COMP | 2019-08-26 | COMP | 2019-08-27 | COMP | 2020-03-16 | COMP | 2020-06-13 | COMP | Rule 16 | 82 | 43 | 97 | 2 | 137 | 64 | 420
9749 | 2018-10-10 | 2019-02-13 | 2019-05-23 | 2019-05-23 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-11-20 | COMP | 2019-11-25 | COMP | Rule 16 | 85 | 71 | 103 | 1 | 24 | 4 | 283
9924 | 2018-10-10 | 2019-02-22 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-30 | COMP | 2019-05-01 | COMP | 2019-12-07 | COMP | 2020-01-13 | COMP | Rule 16 | 91 | 36 | 13 | 2 | 152 | 24 | 314
10075 | 2018-10-10 | 2019-03-01 | 2019-07-01 | 2019-07-01 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2022-01-25 | COMP | 2022-02-08 | COMP | Rule 15/16 | 96 | 86 | 230 | 1 | 418 | 11 | 837
11229 | 2018-10-10 | 2019-04-17 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-09 | COMP | 2019-07-11 | COMP | 2019-07-16 | COMP | 2019-08-21 | COMP | Rule 16 | 129 | 45 | 14 | 3 | 4 | 27 | 217
11376 | 2018-10-10 | 2019-04-24 | 2019-09-23 | 2019-09-23 | COMP | 2020-06-18 | COMP | 2021-04-29 | COMP | 2021-06-23 | COMP | 2021-08-03 | COMP | Rule 15/16 | 134 | 106 | 186 | 218 | 39 | 29 | 707
13123 | 2018-10-10 | 2019-07-11 | 2019-10-23 | 2019-10-23 | COMP | 2020-03-02 | COMP | 2020-09-10 | COMP |  |  | 2020-12-01 | COMP | Rule 16 | 188 | 74 | 87 | 137 |  |  | 538
13282 | 2018-10-10 | 2019-07-18 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-11-01 | COMP | 2019-11-18 | COMP | Rule 16 | 193 | 36 | 16 | 1 | 26 | 11 | 278
13998 | 2018-10-10 | 2019-08-20 | 2019-11-23 | 2019-11-23 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-02-04 | COMP | 2020-02-27 | COMP | Rule 16 | 216 | 67 | 37 | 1 | 11 | 17 | 345
4115 | 2018-10-11 | 2019-02-26 | 2019-03-13 | 2019-03-13 | COMP | 2019-06-07 | COMP | 2019-07-19 | COMP | 2019-11-15 | COMP | 2020-02-05 | COMP | Rule 16 | 92 | 12 | 62 | 30 | 84 | 54 | 329
7515 | 2018-10-11 | 2018-10-18 | 2018-12-28 | 2018-12-28 | COMP | 2019-05-29 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-07-19 | COMP | Rule 16 | 6 | 48 | 105 | 3 | 1 | 35 | 193
7653 | 2018-10-11 | 2018-10-24 | 2019-01-18 | 2019-06-14 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-07-25 | COMP | 2019-08-29 | COMP | Rule 16 | 10 | 58 | 12 | 1 | 18 | 26 | 222
7908 | 2018-10-11 | 2018-11-05 | 2019-02-01 | 2019-02-01 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-03-21 | COMP | 2019-04-24 | COMP | Rule 16 | 18 | 59 | 38 | 1 | 0 | 21 | 133
7909 | 2018-10-11 | 2018-11-05 | 2018-12-24 | 2018-12-24 | COMP | 2019-01-23 | COMP | 2019-01-23 | COMP | 2019-01-27 | COMP | 2019-01-30 | COMP | Rule 16 | 18 | 33 | 20 | 1 | 3 | 3 | 74
7914 | 2018-10-11 | 2018-11-05 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-07-27 | COMP | 2019-08-05 | COMP | Rule 16 | 18 | 55 | 21 | 1 | 107 | 6 | 204
7915 | 2018-10-11 | 2018-11-05 | 2019-01-16 | 2019-01-16 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-04-10 | COMP | 2019-05-31 | COMP | Rule 16 | 18 | 48 | 60 | 1 | 0 | 36 | 159
7960 | 2018-10-11 | 2018-11-07 | 2019-03-22 | 2019-04-30 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2020-05-11 | COMP | 2020-06-10 | COMP | Rule 16 | 20 | 91 | 33 | 1 | 228 | 22 | 417
8208 | 2018-10-11 | 2018-11-19 | 2019-10-14 | 2021-02-03 | COMP | 2021-02-12 | COMP | 2020-01-14 | COMP | 2021-07-14 | COMP | 2021-08-27 | COMP | Rule 15/16 | 27 | 227 | 8 |  | 379 | 33 | 724
8254 | 2018-10-11 | 2018-11-21 | 2018-12-31 | 2018-12-31 | COMP | 2019-01-15 | COMP | 2019-09-11 | COMP | 2019-01-24 | COMP | 2020-02-24 | COMP | Rule 16 | 29 | 26 | 11 | 167 | 0 | 112 | 341
8399 | 2018-10-11 | 2018-11-29 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2020-01-16 | COMP | 2020-02-18 | COMP | Rule 16 | 33 | 28 | 23 | 1 | 235 | 22 | 337
8535 | 2018-10-11 | 2018-12-07 | 2019-11-08 | 2019-11-08 | COMP | 2019-12-30 | COMP | 2020-01-15 | COMP | 2020-02-27 | COMP | 2020-03-06 | COMP | Rule 15/16 | 39 | 234 | 33 | 12 | 30 | 7 | 350
8651 | 2018-10-11 | 2018-12-14 | 2019-04-06 | 2019-04-06 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-05-30 | COMP | 2020-01-29 | COMP | Rule 16 | 44 | 77 | 43 | 1 | 0 | 162 | 324
8788 | 2018-10-11 | 2018-12-27 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-02 | COMP | 2020-05-26 | COMP | 2020-06-16 | COMP | 2020-07-24 | COMP | Rule 15/16 | 52 | 300 | 19 | 38 | 16 | 29 | 449
8965 | 2018-10-11 | 2019-01-09 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-23 | COMP | 2019-04-23 | INPR | 2022-02-26 | REQD | 2021-01-29 | COMP | Rule 16 | 60 | 49 | 25 |  |  |  | 577
9746 | 2018-10-11 | 2019-02-13 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-16 | COMP | 2019-05-28 | COMP | 2019-05-24 | NOTN | 2019-07-11 | COMP | Rule 16 | 84 | 60 | 7 | 8 |  |  | 187
10107 | 2018-10-11 | 2019-03-02 | 2019-05-17 | 2019-05-17 | COMP | 2019-09-30 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2020-10-07 | COMP | Rule 15/16 | 95 | 55 | 94 | 228 | 1 | 32 | 501
10127 | 2018-10-11 | 2019-03-04 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-30 | COMP | 2019-08-26 | COMP | 2023-04-30 | INPR | 2020-08-05 | COMP | Rule 16 | 96 | 67 | 39 | 20 |  |  | 457
10158 | 2018-10-11 | 2019-03-05 | 2019-05-01 | 2019-05-01 | COMP | 2019-08-29 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-01-14 | COMP | Rule 16 | 97 | 42 | 85 | 59 | 1 | 35 | 314
10531 | 2018-10-11 | 2019-03-19 | 2019-04-28 | 2019-04-28 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-05-13 | COMP | 2019-05-23 | COMP | Rule 16 | 107 | 29 | 10 | 1 | 2 | 9 | 154
10887 | 2018-10-11 | 2019-04-03 | 2019-05-10 | 2019-05-10 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-07-03 | COMP | 2019-06-25 | COMP | Rule 16 | 118 | 28 | 8 | 1 | 31 |  | 176
10998 | 2018-10-11 | 2019-04-08 | 2019-04-17 | 2019-09-13 | COMP | 2019-11-01 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-18 | COMP | Rule 16 | 121 | 8 | 36 | 7 | 1 | 5 | 277
11043 | 2018-10-11 | 2019-04-10 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2020-09-22 | COMP | 2020-09-18 | COMP | Rule 16 | 123 | 81 | 21 | 1 | 268 |  | 488
11104 | 2018-10-11 | 2019-04-12 | 2019-05-30 | 2019-05-30 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-08-13 | COMP | 2019-09-17 | COMP | Rule 16 | 125 | 34 | 21 | 1 | 33 | 25 | 234
11903 | 2018-10-11 | 2019-05-15 | 2019-07-15 | 2019-07-24 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-10-30 | COMP | 2019-12-10 | COMP | Rule 16 | 148 | 42 | 57 | 1 | 14 | 27 | 291
14176 | 2018-10-11 | 2019-08-28 | 2019-10-21 | 2020-06-01 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2020-12-23 | COMP | 2021-01-08 | COMP | Rule 16 | 221 | 38 | 44 | 1 | 101 | 11 | 563
14793 | 2018-10-11 | 2019-09-27 | 2020-01-02 | 2020-01-02 | COMP | 2020-05-01 | COMP | 2020-06-17 | COMP | 2020-09-08 | COMP | 2021-04-02 | COMP | Rule 16 | 242 | 65 | 85 | 33 | 59 | 142 | 621
16160 | 2018-10-11 | 2019-12-12 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-19 | COMP | 2020-03-24 | COMP | 2020-11-25 | COMP | 2021-01-23 | COMP | Rule 16 | 293 | 36 | 32 | 4 | 174 | 38 | 572
7860 | 2018-10-12 | 2018-11-02 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-22 | COMP | 2019-02-22 | COMP | 2019-04-10 | COMP | 2019-04-19 | COMP | Rule 16 | 16 | 63 | 12 | 1 | 34 | 8 | 129
7866 | 2018-10-12 | 2018-11-03 | 2019-01-31 | 2019-01-31 | COMP | 2019-04-01 | COMP | 2019-04-02 | COMP | 2019-09-02 | INPR | 2019-05-06 | COMP | Rule 16 | 16 | 58 | 42 | 2 |  |  | 140
7930 | 2018-10-12 | 2018-11-06 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-09-17 | COMP | 2019-10-14 | COMP | Rule 16 | 18 | 42 | 21 | 1 | 155 | 20 | 252
7964 | 2018-10-12 | 2018-11-07 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-03-18 | COMP | 2019-05-02 | COMP | Rule 16 | 19 | 52 | 9 | 1 | 28 | 34 | 138
8063 | 2018-10-12 | 2018-11-14 | 2019-01-08 | 2019-01-10 | COMP | 2019-01-15 | COMP | 2019-02-01 | COMP | 2019-03-04 | COMP | 2019-04-07 | COMP | Rule 16 | 23 | 36 | 4 | 13 | 21 | 25 | 119
8125 | 2018-10-12 | 2018-11-16 | 2019-03-19 | 2020-04-13 | COMP | 2020-07-20 | COMP | 2020-10-30 | COMP | 2021-11-17 | COMP | 2021-02-23 | COMP | Rule 15/16 | 25 | 82 | 70 | 74 | 263 |  | 592
8157 | 2018-10-12 | 2018-11-16 | 2019-01-24 | 2019-01-24 | COMP | 2019-02-06 | COMP | 2019-03-05 | COMP | 2019-02-06 | COMP | 2019-03-12 | COMP | Rule 16 | 25 | 45 | 10 | 19 | 0 | 6 | 101
8193 | 2018-10-12 | 2018-11-17 | 2018-12-20 | 2018-12-20 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-04-19 | COMP | 2019-05-23 | COMP | Rule 16 | 25 | 22 | 49 | 1 | 35 | 25 | 153
8354 | 2018-10-12 | 2018-11-28 | 2019-04-17 | 2019-04-17 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-09-18 | COMP | 2019-11-05 | COMP | Rule 16 | 31 | 97 | 106 | 1 | 3 | 35 | 268
8449 | 2018-10-12 | 2018-12-03 | 2019-01-31 | 2019-01-31 | COMP | 2019-04-08 | COMP | 2019-04-19 | COMP | 2019-04-03 | COMP | 2019-05-14 | COMP | Rule 16 | 34 | 41 | 47 | 10 | 0 | 18 | 146
8655 | 2018-10-12 | 2018-12-13 | 2019-01-15 | 2019-01-15 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-07-18 | COMP | 2019-08-29 | COMP | Rule 16 | 42 | 22 | 36 | 1 | 94 | 31 | 221
8794 | 2018-10-12 | 2018-12-27 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-22 | COMP | 2019-05-06 | COMP | 2019-06-04 | COMP | 2019-07-18 | COMP | Rule 16 | 51 | 21 | 19 | 52 | 21 | 32 | 191
9672 | 2018-10-12 | 2019-02-11 | 2019-03-11 | 2019-05-16 | COMP | 2019-05-16 | NOTN | 2019-05-16 | COMP | 2019-05-17 | NOTN | 2019-06-25 | COMP | Rule 16 | 81 | 20 |  | 1 |  |  | 175
10253 | 2018-10-12 | 2019-03-07 | 2019-07-08 | 2019-07-08 | COMP | 2019-08-07 | COMP | 2019-08-08 | COMP | 2020-02-25 | COMP | 2020-03-13 | COMP | Rule 15/16 | 98 | 86 | 23 | 2 | 136 | 14 | 354
10757 | 2018-10-12 | 2019-03-29 | 2020-07-13 | 2021-08-21 | COMP | 2021-11-15 | COMP | 2022-04-29 | COMP | 2022-02-01 | COMP | 2022-06-15 | COMP | Rule 15/16 | 114 | 326 | 59 | 116 | 0 | 33 | 924
10886 | 2018-10-12 | 2019-04-03 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-09-13 | COMP | 2019-09-16 | COMP | Rule 16 | 117 | 3 | 11 | 1 | 102 | 2 | 232
13237 | 2018-10-12 | 2019-07-17 | 2019-07-19 | 2019-07-19 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2020-02-07 | COMP | 2020-03-12 | COMP | Rule 16 | 190 | 3 | 23 | 1 | 117 | 24 | 353
13825 | 2018-10-12 | 2019-08-12 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-27 | COMP | 2020-04-06 | COMP | 2020-02-18 | COMP | 2020-05-04 | COMP | Rule 16 | 208 | 56 | 21 | 88 | 0 | 21 | 390
13840 | 2018-10-12 | 2019-08-13 | 2019-10-14 | 2019-11-08 | COMP | 2019-12-27 | COMP | 2020-01-22 | COMP | 2020-06-16 | COMP | 2020-07-24 | COMP | Rule 15/16 | 209 | 44 | 32 | 17 | 103 | 29 | 448
13909 | 2018-10-12 | 2019-08-16 | 2019-11-14 | 2019-11-14 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-07-07 | COMP | 2020-07-19 | COMP | Rule 16 | 212 | 63 | 135 | 1 | 28 | 9 | 443
14411 | 2018-10-12 | 2019-09-09 | 2019-11-01 | 2019-12-19 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-02-10 | COMP | 2020-02-12 | COMP | Rule 16 | 227 | 40 | 15 | 1 | 21 | 3 | 333
3997 | 2018-10-15 | 2018-11-10 | 2019-06-28 | 2019-06-28 | COMP | 2020-05-11 | COMP | 2020-05-22 | COMP | 2020-07-21 | NOTN | 2020-08-22 | COMP | Rule 15/16 | 20 | 157 | 218 | 10 |  |  | 467
4026 | 2018-10-15 | 2018-12-10 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-03-26 | COMP | 2019-04-08 | COMP | Rule 16 | 38 | 51 | 13 | 1 | 11 | 10 | 119
7477 | 2018-10-15 | 2018-10-16 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-20 | COMP | 2019-02-28 | COMP | 2019-01-31 | COMP | 2019-04-02 | COMP | Rule 15/16 | 2 | 23 | 22 | 47 | 0 | 24 | 115
7690 | 2018-10-15 | 2018-10-26 | 2018-12-16 | 2019-03-12 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | 2019-06-17 | COMP | 2019-07-20 | COMP | Rule 15/16 | 10 | 33 | 14 | 1 | 56 | 24 | 191
7711 | 2018-10-15 | 2018-10-27 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-23 | COMP | 2019-05-13 | COMP | 2019-10-21 | INPR | 2019-06-10 | COMP | Rule 15/16 | 10 | 107 | 14 | 15 |  |  | 163
7800 | 2018-10-15 | 2018-10-31 | 2019-01-23 | 2019-01-23 | COMP | 2019-03-19 | COMP | 2019-03-25 | COMP | 2019-03-18 | COMP | 2019-04-30 | COMP | Rule 16 | 13 | 55 | 39 | 5 | 0 | 27 | 135
7870 | 2018-10-15 | 2018-11-03 | 2019-01-11 | 2019-01-11 | COMP | 2019-01-16 | NOTN | 2019-01-16 | COMP | 2019-01-16 | NOTN | 2019-04-04 | COMP | Other | 15 | 45 |  | 4 |  |  | 117
7879 | 2018-10-15 | 2018-11-03 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-09 | NOTN | 2019-04-09 | COMP | 2019-04-09 | COMP | 2020-03-13 | COMP | Other | 15 | 103 |  | 3 | 1 | 234 | 353
7986 | 2018-10-15 | 2018-11-08 | 2019-02-26 | 2019-02-26 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-08-27 | COMP | 2019-10-28 | COMP | Rule 16 | 19 | 72 | 76 | 1 | 54 | 44 | 261
7996 | 2018-10-15 | 2018-11-09 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-06 | COMP | 2019-03-11 | COMP | 2019-03-21 | COMP | 2019-05-03 | COMP | Rule 16 | 20 | 74 | 4 | 4 | 9 | 32 | 138
8164 | 2018-10-15 | 2018-11-17 | 2019-03-05 | 2019-03-05 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-07-21 | INPR | 2019-03-19 | COMP | Rule 16 | 24 | 71 | 6 | 1 |  |  | 105
8165 | 2018-10-15 | 2018-11-17 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-07-21 | INPR | 2019-04-10 | COMP | Rule 16 | 24 | 75 | 4 | 1 |  |  | 121
8166 | 2018-10-15 | 2018-11-17 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-07-21 | INPR | 2019-03-19 | COMP | Rule 16 | 24 | 75 | 4 | 1 |  |  | 105
8167 | 2018-10-15 | 2018-11-17 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-18 | COMP | 2019-03-18 | INPR | 2019-07-21 | REQD | 2019-04-10 | COMP | Rule 16 | 24 | 75 | 6 |  |  |  | 121
8168 | 2018-10-15 | 2018-11-17 | 2019-03-12 | 2019-03-12 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-07-21 | INPR | 2019-04-10 | COMP | Rule 16 | 24 | 76 | 3 | 1 |  |  | 121
8191 | 2018-10-15 | 2018-11-17 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-14 | COMP | 2019-03-14 | INPR | 2019-07-21 | REQD | 2019-04-10 | COMP | Rule 16 | 24 | 75 | 4 |  |  |  | 121
8192 | 2018-10-15 | 2018-11-17 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-07-21 | INPR | 2019-04-10 | COMP | Rule 16 | 24 | 75 | 4 | 1 |  |  | 121
8239 | 2018-10-15 | 2018-11-20 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-20 | COMP | 2019-04-09 | COMP | 2019-03-19 | COMP | 2019-05-01 | COMP | Rule 16 | 26 | 60 | 22 | 15 | 0 | 17 | 136
8350 | 2018-10-15 | 2018-11-27 | 2019-04-23 | 2019-04-23 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2019-06-25 | COMP | 2019-07-01 | COMP | Rule 16 | 29 | 102 | 38 | 1 | 8 | 5 | 178
8361 | 2018-10-15 | 2018-11-28 | 2019-05-15 | 2019-05-15 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-10-14 | COMP | 2019-10-15 | COMP | Rule 16 | 30 | 117 | 75 | 1 | 32 | 2 | 252
8539 | 2018-10-15 | 2018-12-07 | 2019-01-17 | 2019-01-17 | COMP | 2019-01-28 | COMP | 2019-01-28 | COMP | 2019-03-25 | COMP | 2019-03-27 | COMP | Rule 16 | 37 | 28 | 7 | 1 | 40 | 3 | 111
8573 | 2018-10-15 | 2018-12-11 | 2019-01-18 | 2019-01-18 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-03-28 | COMP | 2019-05-02 | COMP | Rule 16 | 39 | 27 | 41 | 1 | 8 | 26 | 137
8574 | 2018-10-15 | 2018-12-11 | 2019-01-16 | 2019-01-16 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-03-28 | COMP | 2019-05-02 | COMP | Rule 16 | 39 | 25 | 42 | 1 | 9 | 26 | 137
8576 | 2018-10-15 | 2018-12-11 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-03 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-05-06 | COMP | Rule 16 | 39 | 56 | 23 | 20 | 1 | 5 | 139
8594 | 2018-10-15 | 2018-12-11 | 2019-02-06 | 2019-02-06 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-04-16 | COMP | 2019-05-09 | COMP | Rule 16 | 39 | 39 | 19 | 1 | 31 | 18 | 142
8610 | 2018-10-15 | 2018-12-11 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2020-04-30 | COMP | 2020-06-08 | COMP | Rule 16 | 39 | 52 | 22 | 1 | 277 | 27 | 413
8665 | 2018-10-15 | 2018-12-13 | 2019-03-18 | 2019-03-18 | COMP | 2020-06-23 | COMP | 2020-06-23 | INPR | 2020-06-24 | COMP | 2019-02-01 | COMP | Rule 16 | 41 | 64 | 321 |  |  |  | 74
8675 | 2018-10-15 | 2018-12-14 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-20 | COMP | 2019-02-20 | INPR | 2022-07-30 | REQD | 2021-07-07 | COMP | Rule 16 | 42 | 31 | 15 |  |  |  | 685
8775 | 2018-10-15 | 2018-12-26 | 2019-08-08 | 2019-08-08 | COMP | 2019-11-20 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2020-04-21 | COMP | Rule 15/16 | 49 | 157 | 73 | 16 | 1 | 89 | 380
8897 | 2018-10-15 | 2019-01-04 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-09-02 | INPR | 2019-05-06 | COMP | Rule 16 | 55 | 33 | 28 | 1 |  |  | 139
9115 | 2018-10-15 | 2019-01-17 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-17 | COMP | 2019-05-14 | COMP | 2019-04-29 | COMP | 2019-07-03 | COMP | Rule 16 | 64 | 43 | 21 | 20 | 0 | 36 | 180
9413 | 2018-10-15 | 2019-02-01 | 2019-06-14 | 2019-06-20 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-12-01 | COMP | 2020-12-15 | COMP | Rule 16 | 74 | 94 | 73 | 1 | 293 | 11 | 545
9430 | 2018-10-15 | 2019-02-04 | 2020-04-10 | 2020-04-17 | COMP | 2020-04-17 | NOTN | 2020-04-17 | INPR | 2020-07-04 | REQD | 2019-04-09 | COMP | Rule 16 | 75 | 299 |  |  |  |  | 120
9759 | 2018-10-15 | 2019-02-13 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-16 | COMP | 2019-04-30 | COMP | 2019-10-01 | COMP | 2019-11-09 | COMP | Rule 15/16 | 82 | 15 | 30 | 11 | 108 | 29 | 270
10073 | 2018-10-15 | 2019-03-01 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-08 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-07-06 | COMP | Rule 16 | 93 | 30 | 20 | 2 | 1 | 40 | 181
10435 | 2018-10-15 | 2019-03-15 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-25 | COMP | 2019-08-07 | COMP | 2019-12-10 | COMP | 2020-01-22 | COMP | Rule 16 | 103 | 68 | 26 | 10 | 86 | 29 | 317
10567 | 2018-10-15 | 2019-03-20 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-23 | COMP | 2019-08-01 | COMP | 2019-08-09 | COMP | 2019-09-10 | COMP | Rule 16 | 106 | 55 | 34 | 8 | 7 | 22 | 227
10586 | 2018-10-15 | 2019-03-22 | 2019-11-06 | 2020-02-10 | COMP | 2020-03-12 | COMP | 2020-03-17 | COMP | 2023-12-02 | INPR | 2020-11-30 | COMP | Rule 15/16 | 108 | 161 | 23 | 4 |  |  | 534
10623 | 2018-10-15 | 2019-03-22 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-22 | COMP | 2019-09-30 | COMP | 2019-11-05 | COMP | 2019-11-17 | COMP | Rule 15/16 | 108 | 70 | 16 | 50 | 27 | 8 | 274
10685 | 2018-10-15 | 2019-03-27 | 2019-07-15 | 2019-07-15 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-10-09 | COMP | 2021-09-30 | COMP | Rule 16 | 111 | 77 | 158 | 1 | 158 | 245 | 745
10721 | 2018-10-15 | 2019-03-28 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-12 | COMP | 2019-07-15 | COMP | 2020-01-07 | COMP | 2019-08-29 | COMP | Rule 16 | 112 | 42 | 13 | 23 | 121 |  | 220
10790 | 2018-10-15 | 2019-03-29 | 2019-11-13 | 2019-11-13 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2020-10-15 | COMP | 2020-12-04 | COMP | Rule 16 | 113 | 160 | 20 | 1 | 215 | 34 | 538
10810 | 2018-10-15 | 2019-04-01 | 2019-10-09 | 2019-10-09 | COMP | 2020-01-27 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-07-20 | COMP | Rule 15/16 | 114 | 135 | 73 | 43 | 1 | 82 | 443
10905 | 2018-10-15 | 2019-04-04 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-07 | NOTN | 2020-01-22 | COMP | 2020-01-07 | COMP | 2020-02-26 | COMP | Other | 117 | 191 |  | 11 | 0 | 25 | 341
11011 | 2018-10-15 | 2019-04-10 | 2019-09-17 | 2019-09-17 | COMP | 2019-09-20 | COMP | 2019-11-19 | COMP | 2023-11-11 | INPR | 2020-01-29 | COMP | Rule 16 | 121 | 112 | 4 | 42 |  |  | 322
11186 | 2018-10-15 | 2019-04-16 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-30 | COMP | 2019-11-18 | COMP | 2019-11-21 | COMP | 2020-01-07 | COMP | Rule 16 | 125 | 109 | 31 | 13 | 4 | 30 | 307
11773 | 2018-10-15 | 2019-05-09 | 2019-07-08 | 2019-07-08 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-08-27 | COMP | 2019-10-01 | COMP | Rule 16 | 142 | 41 | 36 | 1 | 2 | 25 | 242
12385 | 2018-10-15 | 2019-06-05 | 2019-08-14 | 2019-08-14 | COMP | 2019-08-26 | COMP | 2019-09-20 | COMP | 2020-02-19 | COMP | 2020-02-28 | COMP | Rule 16 | 160 | 50 | 9 | 19 | 102 | 8 | 343
12827 | 2018-10-15 | 2019-06-25 | 2019-09-03 | 2019-09-03 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2020-07-07 | COMP | 2020-07-28 | COMP | Rule 16 | 174 | 49 | 77 | 1 | 137 | 16 | 449
16829 | 2018-10-15 | 2020-01-17 | 2020-05-03 | 2020-05-03 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-08-05 | COMP | 2020-09-18 | COMP | Rule 16 | 315 | 74 | 24 | 1 | 44 | 32 | 486
19950 | 2018-10-15 | 2020-05-30 | 2021-03-09 | 2021-03-09 | COMP | 2021-05-17 | COMP | 2021-08-09 | COMP | 2021-10-11 | COMP | 2021-11-13 | COMP | Rule 16 | 407 | 194 | 50 | 59 | 45 | 24 | 775
4123 | 2018-10-16 | 2019-03-13 | 2019-04-20 | 2019-04-20 | COMP | 2019-04-22 | COMP | 2019-04-29 | COMP | 2019-04-18 | COMP | 2020-02-04 | COMP | Rule 16 | 100 | 28 | 1 | 6 | 0 | 193 | 325
7573 | 2018-10-16 | 2018-10-20 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-23 | COMP | 2019-06-05 | COMP | 2019-07-08 | COMP | 2019-07-12 | COMP | Rule 16 | 4 | 112 | 14 | 31 | 23 | 5 | 185
7638 | 2018-10-16 | 2018-10-23 | 2019-06-27 | 2019-06-27 | COMP | 2020-01-28 | COMP | 2020-03-06 | COMP | 2020-01-28 | COMP | 2020-03-17 | COMP | Rule 16 | 6 | 170 | 146 | 28 | 0 | 8 | 354
7740 | 2018-10-16 | 2018-10-29 | 2019-01-15 | 2019-01-15 | COMP | 2019-02-26 | COMP | 2019-04-06 | COMP | 2019-02-27 | COMP | 2019-05-20 | COMP | Rule 16 | 10 | 52 | 29 | 29 | 0 | 31 | 148
7808 | 2018-10-16 | 2018-11-02 | 2019-01-28 | 2019-02-07 | COMP | 2019-02-20 | COMP | 2019-04-24 | COMP | 2019-04-18 | COMP | 2019-06-24 | COMP | Rule 15/16 | 14 | 56 | 9 | 46 | 0 | 43 | 172
7926 | 2018-10-16 | 2018-11-06 | 2019-02-07 | 2019-02-07 | COMP | 2019-02-14 | COMP | 2019-03-11 | NOTN | 2019-03-11 | COMP | 2019-03-13 | COMP | Rule 16 | 16 | 62 | 6 |  |  |  | 100
7935 | 2018-10-16 | 2018-11-06 | 2019-01-10 | 2019-01-10 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2023-04-30 | INPR | 2019-08-08 | COMP | Rule 16 | 16 | 43 | 74 | 1 |  |  | 204
7944 | 2018-10-16 | 2018-11-06 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-08 | COMP | 2019-02-13 | NOTN | 2019-03-11 | COMP | 2019-03-13 | COMP | Rule 16 | 16 | 57 | 7 |  |  |  | 100
8041 | 2018-10-16 | 2018-11-13 | 2019-01-03 | 2019-01-03 | COMP | 2019-01-22 | COMP | 2019-01-30 | COMP | 2019-01-22 | COMP | 2019-02-25 | COMP | Rule 16 | 20 | 34 | 13 | 7 | 0 | 18 | 88
8051 | 2018-10-16 | 2018-11-13 | 2019-01-09 | 2019-01-09 | COMP | 2019-02-07 | NOTN | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-04-15 | COMP | Other | 20 | 38 |  | 21 | 1 | 47 | 123
8198 | 2018-10-16 | 2018-11-17 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-11-12 | COMP | 2019-12-05 | COMP | Rule 15/16 | 23 | 45 | 41 | 1 | 163 | 16 | 285
8362 | 2018-10-16 | 2018-11-28 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-04-28 | COMP | 2019-08-14 | COMP | Rule 16 | 29 | 88 | 16 | 1 | 2 | 76 | 208
8417 | 2018-10-16 | 2018-11-29 | 2019-05-12 | 2019-05-12 | COMP | 2019-06-18 | COMP | 2019-08-20 | COMP | 2021-01-02 | INPR | 2019-12-20 | COMP | Rule 16 | 30 | 113 | 26 | 45 |  |  | 296
8565 | 2018-10-16 | 2018-12-11 | 2019-03-15 | 2019-03-15 | COMP | 2019-04-09 | COMP | 2019-04-08 | COMP | 2019-04-10 | COMP | 2019-04-18 | COMP | Rule 16 | 38 | 65 | 18 |  | 3 | 7 | 126
8581 | 2018-10-16 | 2018-12-10 | 2019-02-02 | 2019-03-05 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-03-30 | COMP | 2019-05-14 | COMP | Rule 16 | 37 | 37 | 16 | 1 | 4 | 32 | 144
8600 | 2018-10-16 | 2018-12-13 | 2019-01-24 | 2019-01-24 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-03-06 | COMP | 2019-04-01 | COMP | Rule 16 | 40 | 28 | 28 | 1 | 2 | 19 | 113
8993 | 2018-10-16 | 2019-01-11 | 2019-10-06 | 2019-10-06 | COMP | 2020-01-06 | COMP | 2020-05-29 | COMP | 2020-09-29 | COMP | 2020-10-06 | COMP | Rule 15/16 | 59 | 186 | 61 | 102 | 87 | 6 | 497
9032 | 2018-10-16 | 2019-01-14 | 2019-02-10 | 2019-02-10 | COMP | 2019-02-14 | COMP | 2019-02-22 | COMP | 2019-02-21 | COMP | 2019-03-13 | COMP | Rule 16 | 60 | 19 | 4 | 6 | 0 | 14 | 100
9106 | 2018-10-16 | 2019-01-17 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-23 | COMP | 2019-04-25 | COMP | 2019-04-24 | COMP | 2019-06-10 | COMP | Rule 16 | 63 | 50 | 17 | 3 | 0 | 32 | 162
9133 | 2018-10-16 | 2019-01-17 | 2019-03-26 | 2019-03-26 | COMP | 2019-05-07 | COMP | 2019-10-23 | COMP | 2020-02-29 | INPR | 2019-11-05 | COMP | Rule 16 | 63 | 47 | 31 | 119 |  |  | 266
9337 | 2018-10-16 | 2019-01-30 | 2019-03-18 | 2019-03-18 | COMP | 2019-06-06 | COMP | 2019-08-19 | COMP | 2019-10-01 | COMP | 2019-11-12 | COMP | Rule 16 | 71 | 33 | 58 | 52 | 31 | 30 | 270
9356 | 2018-10-16 | 2019-01-30 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-09-05 | COMP | 2019-10-15 | COMP | Rule 16 | 71 | 100 | 8 | 1 | 47 | 29 | 251
10029 | 2018-10-16 | 2019-02-27 | 2019-04-29 | 2019-04-29 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-07-08 | COMP | 2019-07-12 | COMP | Rule 16 | 90 | 44 | 45 | 1 | 5 | 5 | 185
10034 | 2018-10-16 | 2019-02-27 | 2019-04-20 | 2019-04-20 | COMP | 2019-06-18 | COMP | 2019-06-18 | COMP | 2019-06-20 | COMP | 2019-08-19 | COMP | Rule 16 | 90 | 38 | 41 | 1 | 3 | 42 | 211
10580 | 2018-10-16 | 2019-03-21 | 2019-05-29 | 2021-03-25 | COMP | 2021-05-10 | COMP | 2021-05-24 | COMP | 2021-07-06 | COMP | 2021-07-19 | COMP | Rule 15/16 | 106 | 49 | 33 | 11 | 30 | 10 | 692
10700 | 2018-10-16 | 2019-03-26 | 2019-06-04 | 2019-06-04 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2020-09-01 | COMP | 2020-09-22 | COMP | Rule 16 | 109 | 50 | 23 | 1 | 294 | 15 | 487
10922 | 2018-10-16 | 2019-04-04 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-09-22 | INPR | 2019-06-12 | COMP | Rule 16 | 116 | 21 | 12 | 1 |  |  | 164
11130 | 2018-10-16 | 2019-04-15 | 2019-07-16 | 2020-06-22 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-10-07 | COMP | Rule 15/16 | 123 | 65 | 47 | 1 | 1 | 31 | 498
11245 | 2018-10-16 | 2019-04-18 | 2019-09-24 | 2019-09-24 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2022-09-22 | COMP | 2022-11-01 | COMP | Rule 16 | 126 | 111 | 231 | 1 | 525 | 29 | 1018
11254 | 2018-10-16 | 2019-04-20 | 2019-06-19 | 2019-06-23 | COMP | 2019-07-26 | COMP | 2020-02-14 | COMP | 2023-04-30 | INPR | 2020-05-07 | COMP | Other | 127 | 42 | 24 | 139 |  |  | 391
11302 | 2018-10-16 | 2019-04-22 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2021-11-17 | COMP | 2019-08-01 | COMP | Rule 16 | 128 | 29 | 10 | 1 | 613 |  | 199
11320 | 2018-10-16 | 2019-04-23 | 2019-07-22 | 2019-11-01 | COMP | 2019-11-13 | COMP | 2019-08-12 | COMP | 2019-08-27 | COMP | 2019-12-27 | COMP | Rule 16 | 129 | 63 | 8 |  | 12 | 84 | 300
11338 | 2018-10-16 | 2019-04-23 | 2019-07-06 | 2019-07-06 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-02 | COMP | 2019-08-30 | COMP | Rule 16 | 129 | 52 | 11 | 1 | 10 | 21 | 220
11498 | 2018-10-16 | 2019-04-30 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-10-07 | COMP | 2019-10-14 | COMP | Rule 16 | 134 | 43 | 24 | 1 | 47 | 6 | 250
11651 | 2018-10-16 | 2019-05-06 | 2019-09-13 | 2020-02-21 | COMP | 2020-10-30 | COMP | 2020-04-21 | INPR | 2020-10-01 | COMP | 2020-10-04 | COMP | Rule 15/16 | 138 | 92 | 179 |  |  |  | 495
12216 | 2018-10-16 | 2019-05-28 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2020-04-14 | COMP | 2020-04-30 | COMP | Rule 16 | 153 | 24 | 9 | 1 | 191 | 13 | 386
13573 | 2018-10-16 | 2019-07-31 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-27 | COMP | 2019-08-27 | INPR | 2019-10-02 | COMP | 2019-10-09 | COMP | Rule 16 | 198 | 6 | 15 |  |  |  | 247
13772 | 2018-10-16 | 2019-08-08 | 2020-01-14 | 2020-01-14 | COMP | 2020-03-05 | COMP | 2020-06-05 | COMP | 2020-08-03 | COMP | 2020-08-31 | COMP | Rule 16 | 204 | 108 | 36 | 66 | 42 | 21 | 472
18118 | 2018-10-16 | 2020-03-11 | 2020-12-09 | 2020-12-09 | COMP | 2021-04-30 | COMP | 2021-09-07 | COMP | 2023-12-03 | INPR | 2021-09-28 | COMP | Rule 16 | 350 | 191 | 99 | 90 |  |  | 742
7700 | 2018-10-17 | 2018-10-26 | 2018-11-01 | 2018-11-01 | COMP | 2019-02-01 | COMP | 2019-02-01 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | Rule 16 | 8 | 5 | 61 | 1 | 111 | 1 | 182
7758 | 2018-10-17 | 2018-10-30 | 2020-03-03 | 2021-12-23 | COMP | 2022-08-29 | COMP | 2022-04-13 | COMP | 2023-04-11 | COMP | 2023-05-04 | COMP | Rule 16 | 10 | 334 | 173 |  | 249 | 18 | 1142
7783 | 2018-10-17 | 2018-10-30 | 2019-04-30 | 2019-10-30 | COMP | 2020-01-07 | COMP | 2020-03-17 | INPR | 2020-03-17 | COMP | 2020-07-27 | COMP | Rule 16 | 10 | 124 | 45 |  |  |  | 446
7990 | 2018-10-17 | 2018-11-09 | 2018-11-27 | 2018-11-27 | COMP | 2019-01-14 | COMP | 2019-01-14 | COMP | 2019-10-21 | INPR | 2019-01-29 | COMP | Rule 16 | 18 | 10 | 33 | 1 |  |  | 69
8054 | 2018-10-17 | 2018-11-13 | 2019-02-01 | 2019-02-01 | COMP | 2019-03-12 | NOTN | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-04-22 | COMP | Other | 19 | 54 |  | 27 | 1 | 30 | 127
8057 | 2018-10-17 | 2018-11-14 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-10-02 | COMP | 2019-10-16 | COMP | Rule 16 | 20 | 44 | 26 | 1 | 154 | 11 | 251
8327 | 2018-10-17 | 2018-11-27 | 2019-02-04 | 2019-02-04 | COMP | 2019-02-22 | COMP | 2019-07-09 | COMP | 2019-10-26 | COMP | 2019-10-31 | COMP | Rule 16 | 27 | 47 | 14 | 96 | 78 | 4 | 262
8353 | 2018-10-17 | 2018-11-27 | 2019-02-01 | 2019-02-01 | COMP | 2019-05-14 | COMP | 2019-06-25 | COMP | 2019-10-26 | COMP | 2019-10-31 | COMP | Rule 16 | 27 | 46 | 72 | 30 | 87 | 4 | 262
8487 | 2018-10-17 | 2018-12-04 | 2019-01-18 | 2020-02-01 | COMP | 2020-02-10 | COMP | 2019-12-02 | COMP | 2020-05-05 | COMP | 2020-06-25 | COMP | Rule 16 | 32 | 32 | 6 |  | 108 | 37 | 424
8523 | 2018-10-17 | 2018-12-06 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-14 | COMP | 2019-02-14 | COMP | 2019-06-26 | COMP | 2019-07-03 | COMP | Rule 16 | 34 | 42 | 7 | 1 | 93 | 6 | 178
8722 | 2018-10-17 | 2018-12-19 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-27 | COMP | 2019-10-28 | COMP | 2019-09-11 | COMP | 2020-01-07 | COMP | Rule 16 | 43 | 62 | 6 | 151 | 0 | 47 | 305
8876 | 2018-10-17 | 2019-01-03 | 2019-10-06 | 2020-06-12 | COMP | 2021-03-16 | COMP | 2021-03-16 | COMP | 2021-03-17 | COMP | 2021-04-27 | COMP | Rule 15/16 | 52 | 192 | 190 | 1 | 2 | 30 | 634
8921 | 2018-10-17 | 2019-01-07 | 2019-05-21 | 2019-05-21 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-10-21 | INPR | 2019-07-11 | COMP | Rule 16 | 54 | 95 | 3 | 1 |  |  | 183
8972 | 2018-10-17 | 2019-01-10 | 2019-02-15 | 2019-08-23 | COMP | 2019-09-22 | REQD | 2019-03-27 | COMP | 2019-04-17 | COMP | 2019-04-27 | COMP | Rule 16 | 57 | 26 |  |  | 16 | 8 | 131
8977 | 2018-10-17 | 2019-01-10 | 2019-02-26 | 2019-04-26 | COMP | 2019-05-01 | COMP | 2019-03-27 | COMP | 2019-05-08 | COMP | 2019-05-14 | COMP | Rule 16 | 57 | 32 | 4 |  | 31 | 5 | 143
9459 | 2018-10-17 | 2019-02-05 | 2019-03-08 | 2019-05-03 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-08-16 | COMP | 2019-09-19 | COMP | Rule 16 | 74 | 23 | 8 | 1 | 67 | 24 | 232
9526 | 2018-10-17 | 2019-02-06 | 2019-04-30 | 2020-10-27 | COMP | 2020-12-09 | COMP | 2022-02-24 | COMP | 2022-02-28 | COMP | 2022-04-11 | COMP | Rule 15/16 | 75 | 59 | 29 | 305 | 3 | 31 | 875
9600 | 2018-10-17 | 2019-02-08 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-17 | COMP | 2020-01-15 | COMP | 2020-02-27 | COMP | 2020-03-20 | COMP | Rule 16 | 77 | 127 | 28 | 82 | 30 | 17 | 356
9825 | 2018-10-17 | 2019-02-20 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2021-01-25 | COMP | 2021-03-01 | COMP | Rule 16 | 84 | 68 | 13 | 1 | 406 | 25 | 593
9856 | 2018-10-17 | 2019-02-20 | 2019-05-10 | 2019-05-10 | COMP | 2019-06-27 | COMP | 2020-01-10 | COMP | 2020-01-07 | COMP | 2020-03-10 | COMP | Rule 16 | 84 | 58 | 34 | 135 | 0 | 41 | 348
9950 | 2018-10-17 | 2019-02-25 | 2019-06-17 | 2019-06-17 | COMP | 2020-02-28 | COMP | 2019-07-01 | COMP | 2020-07-17 | COMP | 2020-08-24 | COMP | Rule 16 | 87 | 80 | 176 |  | 265 | 27 | 466
10239 | 2018-10-17 | 2019-03-07 | 2019-04-24 | 2019-04-24 | COMP | 2019-04-24 | NOTN | 2019-04-24 | COMP | 2019-05-21 | COMP | 2019-06-27 | COMP | Other | 95 | 35 |  | 1 | 20 | 27 | 174
10763 | 2018-10-17 | 2019-03-28 | 2019-08-11 | 2019-08-11 | COMP | 2020-03-12 | COMP | 2021-02-25 | COMP | 2022-03-25 | COMP | 2022-04-29 | COMP | Rule 15/16 | 110 | 95 | 146 | 242 | 274 | 26 | 889
10906 | 2018-10-17 | 2019-04-04 | 2019-05-25 | 2019-05-25 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-12-23 | COMP | 2020-01-30 | COMP | Rule 16 | 115 | 37 | 25 | 1 | 121 | 26 | 321
11119 | 2018-10-17 | 2019-04-12 | 2019-06-23 | 2019-06-23 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-10-16 | COMP | 2019-09-13 | COMP | Rule 16 | 121 | 50 | 25 | 1 | 57 |  | 228
11125 | 2018-10-17 | 2019-04-15 | 2019-09-27 | 2019-09-27 | COMP | 2020-01-29 | COMP | 2020-08-03 | COMP | 2023-11-11 | INPR | 2021-06-30 | COMP | Rule 15/16 | 122 | 117 | 83 | 132 |  |  | 679
11220 | 2018-10-17 | 2019-04-18 | 2019-08-16 | 2019-08-16 | COMP | 2020-01-24 | COMP | 2019-09-09 | COMP | 2020-03-14 | COMP | 2020-04-22 | COMP | Rule 15/16 | 125 | 85 | 109 |  | 128 | 28 | 379
12048 | 2018-10-17 | 2019-05-22 | 2019-05-23 | 2019-05-23 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2020-01-21 | COMP | 2020-01-30 | COMP | Rule 16 | 149 | 2 | 25 | 1 | 141 | 8 | 321
12162 | 2018-10-17 | 2019-05-24 | 2019-08-09 | 2019-11-04 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-07-26 | COMP | 2020-07-27 | COMP | Rule 16 | 151 | 54 | 20 | 1 | 163 | 1 | 446
12283 | 2018-10-17 | 2019-05-31 | 2019-10-11 | 2021-06-02 | COMP | 2021-07-15 | COMP | 2022-06-21 | COMP | 2022-08-23 | COMP | 2022-09-15 | COMP | Rule 15/16 | 155 | 94 | 31 | 236 | 45 | 17 | 984
12772 | 2018-10-17 | 2019-06-22 | 2019-08-21 | 2019-08-21 | COMP | 2019-12-23 | COMP | 2020-01-09 | COMP | 2021-07-09 | COMP | 2021-07-27 | COMP | Rule 16 | 170 | 42 | 85 | 12 | 379 | 13 | 697
12916 | 2018-10-17 | 2019-06-29 | 2019-11-20 | 2019-11-20 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-02-04 | COMP | 2020-06-01 | COMP | Rule 16 | 175 | 100 | 40 | 1 | 11 | 83 | 406
17201 | 2018-10-17 | 2020-02-05 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-12 | COMP | 2020-04-09 | COMP | 2020-11-17 | COMP | 2020-12-15 | COMP | Rule 16 | 325 | 15 | 12 | 21 | 156 | 19 | 543
3999 | 2018-10-18 | 2018-11-13 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-01 | COMP | 2019-04-04 | COMP | 2019-08-14 | COMP | 2019-09-10 | COMP | Rule 15/16 | 18 | 62 | 33 | 4 | 93 | 19 | 224
7679 | 2018-10-18 | 2018-10-25 | 2018-12-05 | 2018-12-05 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-12 | COMP | 2019-03-27 | COMP | Rule 16 | 6 | 27 | 46 | 1 | 2 | 31 | 108
7812 | 2018-10-18 | 2018-11-03 | 2019-01-03 | 2019-09-03 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-02 | COMP | 2019-11-25 | COMP | Rule 16 | 12 | 39 | 26 | 1 | 0 | 34 | 277
7839 | 2018-10-18 | 2018-11-02 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-03-28 | COMP | Rule 16 | 12 | 47 | 27 | 1 | 1 | 26 | 109
7858 | 2018-10-18 | 2018-11-02 | 2019-01-24 | 2019-01-24 | COMP | 2019-01-25 | NOTN | 2019-04-29 | COMP | 2019-01-25 | NOTN | 2019-06-17 | COMP | Other | 12 | 54 |  | 67 |  |  | 165
8002 | 2018-10-18 | 2018-11-09 | 2019-05-24 | 2020-01-08 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-06-30 | COMP | 2020-08-20 | COMP | Rule 15 | 17 | 134 | 48 | 1 | 75 | 38 | 463
8042 | 2018-10-18 | 2018-11-13 | 2019-01-16 | 2019-01-16 | COMP | 2019-02-05 | COMP | 2019-03-26 | COMP | 2019-04-04 | COMP | 2019-05-30 | COMP | Rule 16 | 18 | 43 | 14 | 35 | 8 | 40 | 153
8092 | 2018-10-18 | 2018-11-15 | 2019-01-31 | 2019-02-12 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2020-04-26 | INPR | 2019-06-26 | COMP | Rule 16 | 20 | 51 | 18 | 1 |  |  | 172
8458 | 2018-10-18 | 2018-12-03 | 2019-02-06 | 2019-04-06 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-05-10 | COMP | 2019-06-06 | COMP | Rule 16 | 30 | 45 | 31 | 1 | 0 | 13 | 158
8462 | 2018-10-18 | 2018-12-04 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-23 | COMP | 2019-07-29 | COMP | 2019-11-22 | COMP | 2020-01-21 | COMP | Rule 16 | 31 | 61 | 37 | 68 | 83 | 38 | 313
8466 | 2018-10-18 | 2018-12-04 | 2019-01-24 | 2019-01-24 | COMP | 2019-01-30 | COMP | 2019-02-07 | COMP | 2019-02-07 | COMP | 2019-03-08 | COMP | Rule 15/16 | 31 | 35 | 5 | 7 | 1 | 21 | 95
8569 | 2018-10-18 | 2018-12-12 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-23 | COMP | 2019-06-19 | COMP | 2019-06-06 | COMP | 2019-08-08 | COMP | Rule 15/16 | 37 | 79 | 12 | 41 | 0 | 36 | 202
8615 | 2018-10-18 | 2018-12-12 | 2018-12-28 | 2018-12-28 | COMP | 2019-02-12 | COMP | 2019-04-30 | COMP | 2019-12-28 | INPR | 2019-07-16 | COMP | Rule 16 | 37 | 12 | 31 | 55 |  |  | 185
8624 | 2018-10-18 | 2018-12-13 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-09-14 | COMP | 2019-09-25 | COMP | Rule 16 | 38 | 65 | 18 | 1 | 109 | 8 | 235
8625 | 2018-10-18 | 2018-12-13 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-10-25 | COMP | 2019-11-07 | COMP | Rule 16 | 38 | 65 | 18 | 1 | 139 | 10 | 266
8626 | 2018-10-18 | 2018-12-13 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-11 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2019-11-20 | COMP | Rule 16 | 38 | 65 | 18 | 148 | 1 | 9 | 274
8627 | 2018-10-18 | 2018-12-13 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2020-03-12 | COMP | 2020-04-08 | COMP | Rule 16 | 38 | 65 | 18 | 1 | 231 | 20 | 368
8628 | 2018-10-18 | 2018-12-13 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-11-07 | COMP | 2019-11-20 | COMP | Rule 16 | 38 | 65 | 18 | 1 | 148 | 9 | 274
8641 | 2018-10-18 | 2018-12-13 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-11 | COMP | 2020-03-23 | COMP | 2021-04-24 | INPR | 2020-04-09 | COMP | Rule 16 | 38 | 65 | 18 | 238 |  |  | 369
8740 | 2018-10-18 | 2018-12-20 | 2019-03-15 | 2019-03-15 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-06-18 | COMP | 2019-07-24 | COMP | Rule 16 | 43 | 58 | 12 | 1 | 56 | 26 | 191
8742 | 2018-10-18 | 2018-12-20 | 2019-03-15 | 2019-03-15 | COMP | 2019-03-26 | COMP | 2019-04-11 | COMP | 2019-05-30 | COMP | 2019-06-27 | COMP | Rule 16 | 43 | 58 | 8 | 13 | 35 | 21 | 173
9079 | 2018-10-18 | 2019-01-16 | 2019-02-21 | 2019-02-21 | COMP | 2019-02-28 | COMP | 2019-04-02 | COMP | 2019-09-02 | INPR | 2019-05-07 | COMP | Rule 16 | 60 | 25 | 6 | 24 |  |  | 137
9143 | 2018-10-18 | 2019-01-18 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-28 | COMP | 2019-03-29 | COMP | 2019-04-08 | COMP | 2019-04-30 | COMP | Rule 16 | 62 | 23 | 26 | 2 | 7 | 17 | 132
9375 | 2018-10-18 | 2019-01-31 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-10 | COMP | 2019-04-29 | COMP | 2019-09-02 | INPR | 2019-05-08 | COMP | Rule 16 | 70 | 45 | 5 | 14 |  |  | 138
9377 | 2018-10-18 | 2019-01-31 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | Rule 16 | 70 | 18 | 7 | 1 | 20 | 1 | 112
9440 | 2018-10-18 | 2019-02-04 | 2019-03-15 | 2019-07-23 | COMP | 2019-08-06 | COMP | 2019-08-16 | COMP | 2019-10-31 | COMP | 2019-11-18 | COMP | Rule 16 | 72 | 29 | 11 | 9 | 54 | 12 | 272
10279 | 2018-10-18 | 2019-03-08 | 2019-05-18 | 2019-08-14 | COMP | 2019-09-09 | COMP | 2019-09-17 | COMP | 2019-10-08 | COMP | 2019-11-25 | COMP | Rule 15/16 | 95 | 51 | 18 | 7 | 16 | 34 | 277
10441 | 2018-10-18 | 2019-03-16 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-16 | COMP | 2019-07-23 | COMP | Rule 16 | 100 | 50 | 10 | 1 | 26 | 6 | 190
11221 | 2018-10-18 | 2019-04-18 | 2019-06-17 | 2019-06-17 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-02-12 | COMP | 2020-03-10 | COMP | Rule 16 | 124 | 42 | 60 | 1 | 106 | 19 | 347
14621 | 2018-10-18 | 2019-09-19 | 2020-01-09 | 2020-01-09 | COMP | 2020-03-18 | COMP | 2021-02-03 | COMP | 2020-04-20 | COMP | 2021-04-21 | COMP | Rule 16 | 231 | 76 | 48 | 223 | 0 | 55 | 629
16706 | 2018-10-18 | 2020-01-14 | 2020-05-01 | 2020-05-04 | COMP | 2021-12-23 | COMP | 2022-12-07 | COMP | 2022-11-18 | COMP | 2023-02-07 | COMP | Rule 15/16 | 309 | 77 | 414 | 241 | 0 | 42 | 1080
7552 | 2018-10-19 | 2018-10-19 | 2018-10-29 | 2018-10-29 | COMP | 2018-12-07 | COMP | 2019-01-18 | COMP | 2023-04-30 | INPR | 2019-07-25 | COMP | Rule 16 | 1 | 7 | 27 | 29 |  |  | 191
7701 | 2018-10-19 | 2018-10-26 | 2020-01-15 | 2020-01-15 | COMP | 2021-08-03 | COMP | 2021-09-17 | COMP | 2022-07-11 | COMP | 2022-08-04 | COMP | Rule 15/16 | 6 | 304 | 392 | 33 | 204 | 19 | 953
7841 | 2018-10-19 | 2018-11-02 | 2019-02-13 | 2019-08-16 | COMP | 2019-09-11 | COMP | 2019-09-12 | COMP | 2019-10-01 | COMP | 2019-11-22 | COMP | Rule 15/16 | 11 | 68 | 18 | 2 | 14 | 38 | 275
7923 | 2018-10-19 | 2018-11-05 | 2019-03-16 | 2019-03-16 | COMP | 2019-03-22 | COMP | 2019-05-31 | COMP | 2019-07-02 | COMP | 2019-07-23 | COMP | Rule 16 | 12 | 88 | 5 | 50 | 23 | 15 | 189
8044 | 2018-10-19 | 2018-11-13 | 2018-12-22 | 2018-12-22 | COMP | 2019-01-25 | COMP | 2019-01-25 | COMP | 2019-01-31 | COMP | 2019-04-09 | COMP | Rule 16 | 17 | 27 | 22 | 1 | 5 | 48 | 116
8134 | 2018-10-19 | 2018-11-16 | 2019-01-25 | 2019-01-25 | COMP | 2019-03-04 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-05-03 | COMP | Rule 15/16 | 20 | 46 | 26 | 18 | 1 | 28 | 134
8136 | 2018-10-19 | 2018-11-16 | 2019-03-06 | 2019-03-06 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-05-06 | COMP | 2019-06-21 | COMP | Rule 16 | 20 | 73 | 45 | 1 | 0 | 33 | 168
8186 | 2018-10-19 | 2018-11-19 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-03 | COMP | 2019-07-19 | COMP | 2019-06-04 | COMP | 2019-09-20 | COMP | Rule 15/16 | 21 | 104 | 11 | 54 | 0 | 45 | 231
8243 | 2018-10-19 | 2018-11-20 | 2019-02-07 | 2019-02-07 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-11 | COMP | 2020-01-01 | COMP | Rule 15/16 | 22 | 53 | 194 | 1 | 20 | 14 | 299
8384 | 2018-10-19 | 2018-11-28 | 2019-02-14 | 2019-02-14 | COMP | 2019-03-18 | COMP | 2019-03-18 | COMP | 2019-05-28 | COMP | 2019-06-27 | COMP | Rule 16 | 26 | 54 | 22 | 1 | 51 | 23 | 172
8607 | 2018-10-19 | 2018-12-12 | 2019-01-02 | 2019-01-02 | COMP | 2019-01-15 | COMP | 2019-01-18 | COMP | 2019-01-24 | COMP | 2019-01-31 | COMP | Rule 16 | 36 | 14 | 10 | 4 | 4 | 6 | 69
8714 | 2018-10-19 | 2018-12-18 | 2019-03-18 | 2019-03-18 | COMP | 2019-04-01 | COMP | 2019-06-05 | COMP | 2019-04-09 | COMP | 2019-07-11 | COMP | Rule 16 | 40 | 61 | 11 | 47 | 0 | 26 | 181
8818 | 2018-10-19 | 2018-12-31 | 2019-02-22 | 2019-02-22 | COMP | 2021-03-09 | COMP | 2021-03-09 | COMP | 2021-04-20 | COMP | 2021-05-19 | COMP | Rule 16 | 48 | 37 | 514 | 1 | 31 | 22 | 648
8855 | 2018-10-19 | 2019-01-02 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-12 | COMP | 2019-03-21 | COMP | 2019-06-24 | COMP | 2019-05-24 | COMP | Rule 16 | 49 | 42 | 7 | 8 | 67 |  | 149
8862 | 2018-10-19 | 2019-01-03 | 2019-12-14 | 2019-12-14 | COMP | 2020-09-14 | COMP | 2021-04-13 | COMP | 2022-05-26 | COMP | 2022-07-14 | COMP | Rule 15/16 | 50 | 239 | 190 | 145 | 285 | 33 | 938
9035 | 2018-10-19 | 2019-01-14 | 2019-04-20 | 2019-04-20 | COMP | 2019-07-01 | COMP | 2019-08-28 | COMP | 2019-08-13 | COMP | 2019-09-18 | COMP | Rule 16 | 57 | 68 | 50 | 42 | 0 | 15 | 229
9082 | 2018-10-19 | 2019-01-16 | 2019-02-28 | 2019-02-28 | COMP | 2019-05-14 | COMP | 2019-05-29 | COMP | 2020-08-29 | INPR | 2019-07-31 | COMP | Rule 15/16 | 59 | 30 | 54 | 11 |  |  | 195
9157 | 2018-10-19 | 2019-01-18 | 2019-04-24 | 2019-04-24 | COMP | 2019-06-14 | COMP | 2019-09-16 | COMP | 2020-03-21 | INPR | 2019-11-19 | COMP | Rule 16 | 61 | 67 | 37 | 65 |  |  | 272
9581 | 2018-10-19 | 2019-02-08 | 2019-05-03 | 2019-05-03 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-09-25 | COMP | 2019-09-30 | COMP | Rule 16 | 75 | 60 | 71 | 1 | 31 | 4 | 237
10216 | 2018-10-19 | 2019-03-06 | 2019-06-03 | 2019-06-03 | COMP | 2019-10-01 | COMP | 2019-10-29 | COMP | 2023-04-30 | INPR | 2019-11-14 | COMP | Rule 16 | 92 | 63 | 85 | 21 |  |  | 269
10315 | 2018-10-19 | 2019-03-11 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-19 | COMP | 2019-08-26 | COMP | 2019-09-05 | COMP | 2021-06-09 | COMP | Rule 15/16 | 95 | 79 | 15 | 27 | 8 | 443 | 662
10400 | 2018-10-19 | 2019-03-14 | 2019-05-08 | 2019-05-08 | COMP | 2019-08-12 | COMP | 2019-09-30 | COMP | 2020-02-17 | COMP | 2020-03-25 | COMP | Rule 16 | 98 | 40 | 67 | 35 | 94 | 27 | 357
10572 | 2018-10-19 | 2019-03-20 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-08-20 | COMP | 2019-09-25 | COMP | Rule 16 | 102 | 62 | 16 | 1 | 32 | 26 | 234
10661 | 2018-10-19 | 2019-03-25 | 2019-06-20 | 2019-06-20 | COMP | 2019-06-24 | COMP | 2019-07-15 | COMP | 2019-09-05 | COMP | 2019-12-06 | COMP | Rule 16 | 105 | 63 | 3 | 15 | 38 | 64 | 283
11520 | 2018-10-19 | 2019-04-30 | 2020-01-31 | 2022-04-13 | COMP | 2022-05-09 | COMP | 2021-08-23 | COMP | 2022-05-17 | COMP | 2022-07-14 | COMP | Rule 15/16 | 131 | 190 | 19 |  | 186 | 40 | 938
14347 | 2018-10-19 | 2019-09-06 | 2021-01-28 | 2021-01-28 | COMP | 2021-03-10 | COMP | 2021-03-29 | COMP | 2022-05-26 | COMP | 2022-07-19 | COMP | Rule 16 | 221 | 350 | 29 | 14 | 296 | 36 | 941
14592 | 2018-10-19 | 2019-09-17 | 2019-11-06 | 2019-11-06 | COMP | 2019-12-11 | COMP | 2019-12-19 | COMP | 2021-10-23 | INPR | 2020-05-18 | COMP | Rule 15/16 | 228 | 37 | 23 | 7 |  |  | 395
14696 | 2018-10-19 | 2019-09-23 | 2020-03-05 | 2020-03-05 | COMP | 2020-03-30 | COMP | 2020-03-31 | COMP | 2020-04-02 | COMP | 2020-05-15 | COMP | Rule 16 | 232 | 112 | 18 | 2 | 3 | 32 | 394
8171 | 2018-10-20 | 2018-11-16 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-22 | COMP | 2019-04-04 | COMP | 2019-05-08 | COMP | 2019-06-04 | COMP | Rule 16 | 19 | 71 | 15 | 10 | 25 | 19 | 154
9263 | 2018-10-20 | 2019-01-25 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-07 | COMP | 2019-07-11 | COMP | 2019-05-15 | COMP | 2019-07-30 | COMP | Rule 16 | 64 | 65 | 8 | 46 | 0 | 14 | 193
14308 | 2018-10-20 | 2019-09-04 | 2019-11-06 | 2020-01-31 | COMP | 2020-06-02 | COMP | 2021-06-17 | COMP | 2021-06-14 | COMP | 2021-08-05 | COMP | Rule 15/16 | 218 | 46 | 86 | 264 | 0 | 35 | 701
8644 | 2018-10-21 | 2018-12-13 | 2019-03-26 | 2019-03-26 | COMP | 2019-12-05 | COMP | 2019-12-12 | COMP | 2020-01-14 | COMP | 2020-01-31 | COMP | Rule 15/16 | 36 | 70 | 177 | 6 | 22 | 13 | 319
3974 | 2018-10-22 | 2018-11-02 | 2019-01-16 | 2019-01-16 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-07-21 | INPR | 2019-04-09 | COMP | Rule 16 | 10 | 49 | 36 | 1 |  |  | 115
7636 | 2018-10-22 | 2018-10-23 | 2019-01-28 | 2019-01-28 | COMP | 2019-03-08 | COMP | 2019-04-03 | COMP | 2019-05-20 | COMP | 2019-07-01 | COMP | Other | 2 | 64 | 29 | 19 | 34 | 30 | 173
7647 | 2018-10-22 | 2018-10-24 | 2018-11-17 | 2018-11-17 | COMP | 2018-12-11 | COMP | 2018-12-11 | COMP | 2019-02-01 | COMP | 2019-03-05 | COMP | Rule 16 | 3 | 17 | 15 | 1 | 36 | 22 | 90
7845 | 2018-10-22 | 2018-11-02 | 2018-12-16 | 2019-02-08 | COMP | 2019-03-15 | COMP | 2019-04-08 | COMP | 2019-04-30 | COMP | 2019-05-09 | COMP | Rule 15/16 | 10 | 28 | 25 | 17 | 17 | 8 | 137
7912 | 2018-10-22 | 2018-11-05 | 2019-03-22 | 2019-03-22 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2020-05-31 | INPR | 2019-09-10 | COMP | Rule 16 | 11 | 93 | 103 | 1 |  |  | 222
7970 | 2018-10-22 | 2018-11-08 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-25 | COMP | 2019-04-30 | COMP | Rule 16 | 14 | 43 | 20 | 1 | 10 | 47 | 130
8026 | 2018-10-22 | 2018-11-14 | 2019-03-18 | 2019-03-18 | COMP | 2019-03-28 | COMP | 2019-06-04 | COMP | 2019-06-06 | COMP | 2019-07-23 | COMP | Rule 16 | 17 | 83 | 9 | 48 | 3 | 33 | 188
8048 | 2018-10-22 | 2018-11-14 | 2019-01-09 | 2019-01-09 | COMP | 2019-03-11 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2019-07-01 | COMP | Other | 17 | 37 | 42 | 60 | 1 | 21 | 173
8059 | 2018-10-22 | 2018-11-14 | 2019-01-15 | 2019-01-15 | COMP | 2019-02-04 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-03-08 | COMP | Rule 16 | 17 | 41 | 14 | 8 | 1 | 17 | 93
8106 | 2018-10-22 | 2018-11-15 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-05-28 | COMP | 2019-08-08 | COMP | Rule 15/16 | 18 | 72 | 32 | 1 | 30 | 52 | 200
8241 | 2018-10-22 | 2018-11-20 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-19 | COMP | 2020-05-20 | COMP | 2019-07-30 | COMP | 2020-07-07 | COMP | Rule 16 | 21 | 44 | 17 | 317 | 0 | 34 | 429
8430 | 2018-10-22 | 2018-12-01 | 2019-02-01 | 2019-02-01 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-05-07 | COMP | 2019-06-20 | COMP | Rule 16 | 27 | 42 | 26 | 1 | 42 | 32 | 166
8664 | 2018-10-22 | 2018-12-13 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-05-06 | COMP | 2019-06-03 | COMP | Rule 16 | 36 | 51 | 21 | 1 | 29 | 20 | 153
8933 | 2018-10-22 | 2019-01-08 | 2019-01-16 | 2019-01-16 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-05-21 | COMP | 2019-05-29 | COMP | Rule 16 | 52 | 7 | 39 | 1 | 50 | 6 | 150
9055 | 2018-10-22 | 2019-01-15 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-29 | COMP | 2019-07-10 | COMP | 2019-06-19 | COMP | 2019-07-17 | COMP | Rule 16 | 57 | 35 | 39 | 51 | 0 | 6 | 184
9397 | 2018-10-22 | 2019-02-01 | 2019-04-09 | 2019-04-09 | COMP | 2019-05-10 | COMP | 2019-05-13 | COMP | 2019-05-10 | COMP | 2019-05-20 | COMP | Rule 16 | 69 | 47 | 24 | 2 | 0 | 6 | 144
9747 | 2018-10-22 | 2019-02-13 | 2019-04-10 | 2019-08-24 | COMP | 2019-11-07 | COMP | 2020-01-13 | INPR | 2020-01-17 | COMP | 2020-01-31 | COMP | Rule 16 | 77 | 40 | 53 |  |  |  | 319
10498 | 2018-10-22 | 2019-03-18 | 2019-06-17 | 2019-06-17 | COMP | 2019-08-23 | COMP | 2019-10-18 | COMP | 2019-10-15 | COMP | 2020-02-19 | COMP | Rule 16 | 99 | 65 | 49 | 40 | 0 | 82 | 331
10517 | 2018-10-22 | 2019-03-19 | 2019-08-13 | 2019-08-13 | COMP | 2019-10-08 | COMP | 2019-10-30 | COMP | 2023-04-30 | INPR | 2019-11-19 | COMP | Rule 16 | 100 | 104 | 40 | 17 |  |  | 271
11049 | 2018-10-22 | 2019-04-10 | 2020-04-29 | 2021-11-15 | COMP | 2021-11-17 | COMP | 2021-10-06 | COMP | 2021-11-17 | COMP | 2023-07-24 | COMP | Rule 15/16 | 116 | 266 | 3 |  | 30 | 421 | 1193
11179 | 2018-10-22 | 2019-04-16 | 2019-07-27 | 2019-07-27 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-06-08 | COMP | 2020-07-14 | COMP | Rule 16 | 120 | 72 | 153 | 1 | 65 | 27 | 434
11619 | 2018-10-22 | 2019-05-06 | 2019-07-08 | 2019-07-08 | COMP | 2019-08-06 | COMP | 2019-09-12 | COMP | 2019-08-12 | COMP | 2019-09-26 | COMP | Rule 16 | 134 | 44 | 22 | 27 | 0 | 11 | 234
11646 | 2018-10-22 | 2019-05-06 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-12 | COMP | 2019-08-06 | COMP | 2019-10-16 | COMP | 2019-11-07 | COMP | Rule 16 | 134 | 8 | 20 | 39 | 51 | 17 | 264
11648 | 2018-10-22 | 2019-05-06 | 2019-06-08 | 2019-06-08 | COMP | 2019-07-18 | COMP | 2019-07-30 | COMP | 2019-07-22 | COMP | 2019-08-19 | COMP | Rule 16 | 134 | 24 | 28 | 9 | 0 | 15 | 207
12147 | 2018-10-22 | 2019-05-24 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-28 | COMP | 2019-09-18 | COMP | 2023-11-12 | INPR | 2019-11-13 | COMP | Rule 16 | 148 | 43 | 25 | 15 |  |  | 267
12292 | 2018-10-22 | 2019-05-30 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2019-09-03 | COMP | Rule 16 | 151 | 29 | 32 | 1 | 1 | 8 | 217
12815 | 2018-10-22 | 2019-06-24 | 2019-08-08 | 2019-09-05 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2020-01-31 | COMP | 2020-03-06 | COMP | Rule 16 | 168 | 33 | 8 | 1 | 94 | 25 | 343
12823 | 2018-10-22 | 2019-06-24 | 2019-07-30 | 2019-07-30 | COMP | 2019-09-05 | COMP | 2021-05-05 | COMP | 2019-12-26 | COMP | 2021-12-04 | COMP | Rule 16 | 168 | 26 | 27 | 419 | 0 | 147 | 783
12984 | 2018-10-22 | 2019-07-03 | 2019-11-27 | 2019-11-27 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-02-04 | COMP | 2020-06-08 | COMP | Rule 16 | 175 | 103 | 50 | 1 | 0 | 83 | 408
13731 | 2018-10-22 | 2019-08-07 | 2020-01-24 | 2020-01-24 | COMP | 2020-09-02 | COMP | 2020-12-01 | COMP | 2021-01-26 | COMP | 2021-02-20 | COMP | Rule 16 | 199 | 116 | 157 | 61 | 38 | 18 | 584
14971 | 2018-10-22 | 2019-10-07 | 2019-12-13 | 2019-12-13 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2021-04-15 | COMP | 2021-05-17 | COMP | Rule 16 | 241 | 47 | 36 | 1 | 302 | 23 | 645
18630 | 2018-10-22 | 2020-04-01 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2022-09-27 | COMP | 2022-10-10 | COMP | Rule 16 | 361 | 74 | 5 | 1 | 552 | 10 | 998
19777 | 2018-10-22 | 2020-05-21 | 2020-10-15 | 2020-10-15 | COMP | 2020-11-18 | COMP | 2021-01-25 | COMP | 2022-03-08 | COMP | 2022-03-11 | COMP | Rule 16 | 397 | 104 | 24 | 44 | 283 | 4 | 851
4057 | 2018-10-23 | 2019-01-03 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-17 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-11-04 | COMP | Rule 16 | 48 | 91 | 25 | 93 | 1 | 7 | 260
4065 | 2018-10-23 | 2019-01-04 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-08-31 | INPR | 2019-05-16 | COMP | Rule 16 | 49 | 74 | 4 | 1 |  |  | 141
7790 | 2018-10-23 | 2018-11-01 | 2019-03-13 | 2019-03-13 | COMP | 2019-04-15 | COMP | 2020-05-14 | COMP | 2020-08-26 | COMP | 2020-09-10 | COMP | Rule 16 | 8 | 88 | 24 | 274 | 74 | 11 | 474
7913 | 2018-10-23 | 2018-11-05 | 2018-12-21 | 2018-12-21 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-05-29 | COMP | 2020-07-27 | COMP | Rule 16 | 10 | 32 | 78 | 1 | 32 | 294 | 442
7922 | 2018-10-23 | 2018-11-05 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-04-04 | COMP | Rule 16 | 10 | 46 | 30 | 1 | 1 | 28 | 111
7977 | 2018-10-23 | 2018-11-09 | 2018-12-11 | 2018-12-11 | COMP | 2018-12-17 | COMP | 2018-12-17 | COMP | 2019-01-16 | COMP | 2019-01-23 | COMP | Rule 16 | 14 | 20 | 5 | 1 | 21 | 5 | 61
8064 | 2018-10-23 | 2018-11-14 | 2019-04-16 | 2019-04-16 | COMP | 2019-04-25 | COMP | 2019-06-03 | COMP | 2019-07-18 | COMP | 2019-12-17 | COMP | Rule 16 | 16 | 104 | 8 | 27 | 33 | 105 | 288
8076 | 2018-10-23 | 2018-11-15 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-07-21 | INPR | 2019-04-30 | COMP | Rule 16 | 17 | 74 | 31 | 1 |  |  | 129
8343 | 2018-10-23 | 2018-11-27 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-05 | NOTN | 2019-03-05 | COMP | 2019-07-21 | INPR | 2019-04-09 | COMP | Other | 23 | 64 |  | 4 |  |  | 114
8405 | 2018-10-23 | 2018-11-29 | 2019-04-13 | 2020-05-22 | COMP | 2020-06-08 | COMP | 2020-05-07 | COMP | 2020-06-21 | COMP | 2020-08-06 | COMP | Rule 16 | 25 | 93 | 11 |  | 31 | 34 | 450
8776 | 2018-10-23 | 2018-12-26 | 2019-06-28 | 2019-06-28 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-01-07 | COMP | 2020-02-14 | COMP | Rule 15/16 | 43 | 129 | 114 | 1 | 18 | 28 | 328
9417 | 2018-10-23 | 2019-02-01 | 2019-04-02 | 2019-04-02 | COMP | 2019-04-17 | COMP | 2019-04-26 | COMP | 2019-12-29 | INPR | 2019-08-09 | COMP | Rule 16 | 68 | 42 | 12 | 8 |  |  | 200
9589 | 2018-10-23 | 2019-02-07 | 2019-05-09 | 2019-06-21 | COMP | 2019-07-08 | COMP | 2019-07-09 | COMP | 2019-07-30 | COMP | 2019-08-24 | COMP | Rule 16 | 72 | 65 | 11 | 2 | 16 | 19 | 210
9590 | 2018-10-23 | 2019-02-07 | 2019-04-24 | 2019-04-24 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-08-31 | COMP | 2019-10-21 | COMP | Rule 16 | 72 | 54 | 90 | 1 | 2 | 35 | 250
9682 | 2018-10-23 | 2019-02-11 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-30 | NOTN | 2019-03-30 | COMP | 2019-12-29 | INPR | 2019-05-17 | COMP | Other | 74 | 27 |  | 8 |  |  | 142
9782 | 2018-10-23 | 2019-02-14 | 2019-04-16 | 2019-04-16 | COMP | 2019-10-04 | COMP | 2019-10-17 | COMP | 2020-02-22 | COMP | 2020-04-26 | COMP | Rule 16 | 77 | 43 | 121 | 10 | 85 | 45 | 377
9784 | 2018-10-23 | 2019-02-14 | 2019-07-15 | 2020-03-02 | COMP | 2020-03-16 | COMP | 2020-04-16 | COMP | 2020-03-16 | COMP | 2020-04-26 | COMP | Rule 16 | 77 | 105 | 11 | 24 | 0 | 7 | 377
10384 | 2018-10-23 | 2019-03-13 | 2019-06-13 | 2019-06-18 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2020-01-10 | COMP | 2020-03-14 | COMP | Rule 16 | 95 | 66 | 20 | 1 | 123 | 44 | 347
10528 | 2018-10-23 | 2019-03-19 | 2019-05-17 | 2019-05-17 | COMP | 2019-09-05 | COMP | 2019-10-08 | COMP | 2020-01-09 | COMP | 2020-02-26 | COMP | Rule 16 | 99 | 44 | 77 | 24 | 63 | 33 | 335
10566 | 2018-10-23 | 2019-03-20 | 2019-06-05 | 2019-06-05 | COMP | 2019-08-26 | COMP | 2019-10-30 | COMP | 2019-11-13 | COMP | 2020-02-19 | COMP | Rule 16 | 100 | 55 | 58 | 47 | 10 | 65 | 330
10614 | 2018-10-23 | 2019-03-22 | 2019-05-25 | 2019-05-25 | COMP | 2019-07-26 | COMP | 2019-09-18 | COMP | 2019-10-07 | COMP | 2020-03-17 | COMP | Rule 16 | 102 | 46 | 43 | 38 | 14 | 110 | 349
10833 | 2018-10-23 | 2019-04-01 | 2019-08-07 | 2019-08-07 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2019-11-12 | COMP | 2019-12-23 | COMP | Rule 16 | 108 | 91 | 50 | 1 | 19 | 28 | 292
10929 | 2018-10-23 | 2019-04-04 | 2019-06-27 | 2019-06-27 | COMP | 2020-08-27 | COMP | 2021-03-30 | COMP |  | INPR | 2021-05-28 | COMP | Rule 15/16 | 111 | 60 | 296 | 146 |  |  | 653
10991 | 2018-10-23 | 2019-04-09 | 2019-05-21 | 2019-05-21 | COMP | 2019-05-30 | COMP | 2019-08-08 | COMP | 2020-04-26 | INPR | 2019-12-19 | COMP | Rule 16 | 114 | 31 | 7 | 50 |  |  | 290
11048 | 2018-10-23 | 2019-04-10 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-02 | COMP | 2019-09-20 | COMP | 2019-08-02 | COMP | 2020-02-19 | COMP | Rule 16 | 115 | 57 | 25 | 35 | 0 | 102 | 330
11262 | 2018-10-23 | 2019-04-19 | 2019-07-30 | 2019-08-08 | COMP | 2019-08-12 | COMP | 2019-10-31 | COMP | 2019-10-02 | COMP | 2020-01-29 | COMP | Rule 16 | 122 | 71 | 3 | 58 | 0 | 59 | 316
11356 | 2018-10-23 | 2019-04-24 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-04 | COMP | 2020-05-31 | REQD | 2020-05-31 | REQD | 2019-11-19 | COMP | Rule 16 | 125 | 98 | 18 |  |  |  | 270
12296 | 2018-10-23 | 2019-05-31 | 2019-12-16 | 2019-12-16 | COMP | 2020-07-22 | COMP | 2020-06-25 | COMP | 2020-09-21 | COMP | 2020-11-18 | COMP | Rule 16 | 151 | 137 | 153 |  | 62 | 42 | 522
13730 | 2018-10-23 | 2019-08-07 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-15 | COMP | 2019-11-19 | COMP | 2019-12-26 | COMP | 2020-02-27 | COMP | Rule 16 | 198 | 27 | 22 | 25 | 25 | 43 | 336
4132 | 2018-10-24 | 2019-03-20 | 2019-03-28 | 2019-03-28 | COMP | 2021-01-20 | COMP | 2021-11-05 | COMP | 2021-05-12 | COMP | 2022-02-03 | COMP | Rule 15/16 | 99 | 7 | 457 | 204 | 0 | 61 | 824
7727 | 2018-10-24 | 2018-10-26 | 2019-01-11 | 2019-01-11 | COMP | 2019-05-09 | COMP | 2019-09-19 | INPR | 2023-04-30 | CANC | 2019-09-21 | COMP | Rule 16 | 3 | 51 | 83 |  |  |  | 228
7973 | 2018-10-24 | 2018-11-08 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-18 | COMP | 2019-04-10 | COMP | 2019-09-02 | INPR | 2019-05-01 | COMP | Rule 16 | 12 | 76 | 11 | 18 |  |  | 129
7987 | 2018-10-24 | 2018-11-08 | 2019-05-01 | 2019-05-01 | COMP | 2019-08-13 | COMP | 2019-09-09 | COMP | 2020-12-07 | COMP | 2021-02-25 | COMP | Rule 16 | 12 | 118 | 73 | 19 | 314 | 55 | 586
8160 | 2018-10-24 | 2018-11-16 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-11-08 | COMP | 2019-12-19 | COMP | Rule 15/16 | 17 | 68 | 34 | 1 | 147 | 27 | 289
8296 | 2018-10-24 | 2018-11-26 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-06-18 | COMP | 2019-07-18 | COMP | Rule 16 | 21 | 38 | 25 | 1 | 81 | 22 | 183
8321 | 2018-10-24 | 2018-11-27 | 2020-02-09 | 2020-02-09 | COMP | 2021-03-30 | COMP | 2021-11-29 | COMP | 2022-02-07 | COMP | 2022-03-03 | COMP | Rule 15/16 | 22 | 301 | 287 | 169 | 50 | 18 | 843
8338 | 2018-10-24 | 2018-11-27 | 2019-02-27 | 2019-02-27 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-09-03 | COMP | 2019-09-28 | COMP | Rule 16 | 22 | 63 | 47 | 1 | 86 | 19 | 233
8341 | 2018-10-24 | 2018-11-27 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-22 | COMP | 2019-02-25 | COMP | 2019-02-22 | COMP | 2019-05-06 | COMP | Rule 16 | 22 | 49 | 12 | 2 | 0 | 51 | 132
8382 | 2018-10-24 | 2018-11-28 | 2019-04-20 | 2019-04-20 | COMP | 2019-04-24 | NOTN | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-07-16 | COMP | Other | 23 | 99 |  | 3 | 1 | 58 | 181
8415 | 2018-10-24 | 2018-11-30 | 2019-08-01 | 2019-08-01 | COMP | 2021-01-20 | COMP | 2021-08-12 | COMP | 2021-05-14 | COMP | 2022-02-04 | COMP | Rule 15/16 | 25 | 169 | 369 | 144 | 0 | 122 | 825
8416 | 2018-10-24 | 2018-11-30 | 2019-08-22 | 2020-10-14 | COMP | 2021-02-10 | COMP | 2021-02-10 | COMP | 2021-07-16 | COMP | 2022-02-04 | COMP | Rule 15/16 | 25 | 184 | 80 | 1 | 110 | 141 | 825
8468 | 2018-10-24 | 2018-12-04 | 2019-03-19 | 2019-03-19 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2021-10-23 | INPR | 2020-10-14 | COMP | Rule 15/16 | 27 | 72 | 77 | 1 |  |  | 497
8493 | 2018-10-24 | 2018-12-06 | 2019-03-18 | 2019-03-18 | COMP | 2019-03-25 | COMP | 2019-07-26 | NOTN | 2020-05-31 | REQD | 2019-07-16 | COMP | Rule 16 | 29 | 69 | 6 |  |  |  | 181
8529 | 2018-10-24 | 2018-12-06 | 2019-02-25 | 2019-02-25 | COMP | 2019-02-25 | NOTN | 2019-02-25 | COMP | 2019-09-17 | COMP | 2019-11-05 | COMP | Rule 16 | 29 | 54 |  | 1 | 144 | 36 | 260
8618 | 2018-10-24 | 2018-12-12 | 2019-03-29 | 2019-05-13 | COMP | 2019-06-07 | NOTN | 2019-06-07 | COMP | 2019-06-17 | COMP | 2019-07-18 | COMP | Other | 33 | 74 |  | 19 | 7 | 23 | 183
8639 | 2018-10-24 | 2018-12-13 | 2019-01-07 | 2019-01-07 | COMP | 2021-03-18 | NOTN |  | REQD |  | REQD | 2019-02-02 | COMP | Rule 16 | 34 | 16 |  |  |  |  | 67
8760 | 2018-10-24 | 2018-12-21 | 2019-02-12 | 2019-02-19 | COMP | 2019-02-27 | COMP | 2019-04-01 | COMP | 2019-09-02 | INPR | 2019-05-07 | COMP | Rule 16 | 40 | 35 | 7 | 24 |  |  | 133
9275 | 2018-10-24 | 2019-01-26 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-18 | COMP | 2020-04-24 | INPR | 2021-12-25 | REQD | 2019-05-01 | COMP | Rule 16 | 62 | 28 | 8 |  |  |  | 129
9329 | 2018-10-24 | 2019-01-30 | 2019-09-20 | 2019-09-20 | COMP | 2020-09-14 | COMP | 2021-07-12 | COMP | 2022-03-03 | COMP | 2022-04-19 | COMP | Rule 15/16 | 65 | 164 | 248 | 207 | 163 | 34 | 876
9379 | 2018-10-24 | 2019-01-31 | 2019-02-27 | 2019-02-27 | COMP | 2019-07-16 | COMP | 2019-07-17 | COMP | 2020-02-26 | COMP | 2020-04-08 | COMP | Rule 15/16 | 66 | 19 | 98 | 2 | 153 | 31 | 364
9427 | 2018-10-24 | 2019-02-04 | 2019-08-09 | 2019-08-14 | COMP | 2019-10-10 | COMP | 2021-01-20 | COMP | 2021-01-14 | COMP | 2021-02-11 | COMP | Rule 15/16 | 68 | 132 | 41 | 320 | 0 | 17 | 577
9668 | 2018-10-24 | 2019-02-11 | 2019-03-08 | 2019-03-08 | COMP | 2019-03-25 | COMP | 2019-05-14 | COMP | 2019-03-26 | COMP | 2019-05-23 | COMP | Rule 16 | 73 | 19 | 12 | 37 | 0 | 8 | 145
9697 | 2018-10-24 | 2019-02-11 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-05-08 | COMP | 2019-05-22 | COMP | Other | 73 | 40 | 22 | 1 | 2 | 11 | 144
9755 | 2018-10-24 | 2019-02-13 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-27 | COMP | 2019-04-23 | COMP | 2019-08-15 | COMP | 2019-10-22 | COMP | Rule 16 | 75 | 18 | 13 | 20 | 81 | 48 | 250
9814 | 2018-10-24 | 2019-02-19 | 2019-03-12 | 2019-03-12 | COMP | 2019-04-02 | COMP | 2019-04-02 | NOTN | 2019-05-08 | COMP | 2019-05-10 | COMP | Rule 16 | 78 | 16 | 16 |  |  |  | 136
9956 | 2018-10-24 | 2019-02-25 | 2019-07-09 | 2019-07-09 | COMP | 2019-09-05 | COMP | 2019-10-01 | COMP | 2019-12-17 | COMP | 2019-12-26 | COMP | Rule 15/16 | 82 | 95 | 42 | 19 | 53 | 7 | 293
10017 | 2018-10-24 | 2019-02-26 | 2019-07-15 | 2019-07-15 | COMP | 2019-10-14 | NOTN | 2019-12-06 | COMP | 2019-12-05 | COMP | 2020-01-23 | COMP | Other | 83 | 98 |  | 101 | 0 | 32 | 311
10186 | 2018-10-24 | 2019-03-05 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-09 | COMP | 2019-04-09 | NOTN | 2019-04-10 | COMP | 2019-04-17 | COMP | Rule 16 | 88 | 19 | 7 |  |  |  | 119
10246 | 2018-10-24 | 2019-03-06 | 2019-10-30 | 2020-09-18 | COMP | 2020-10-15 | COMP | 2020-10-15 | COMP | 2020-10-13 | COMP | 2021-01-17 | COMP | Rule 16 | 89 | 168 | 20 | 1 | 0 | 62 | 559
10312 | 2018-10-24 | 2019-03-11 | 2019-07-08 | 2019-07-11 | COMP | 2019-07-26 | COMP | 2019-07-28 | COMP | 2019-09-06 | COMP | 2019-10-18 | COMP | Rule 16 | 92 | 84 | 12 | 1 | 29 | 31 | 248
10592 | 2018-10-24 | 2019-03-23 | 2019-08-09 | 2019-08-09 | COMP | 2020-01-03 | COMP | 2021-04-14 | COMP | 2021-04-16 | COMP | 2021-05-06 | COMP | Rule 16 | 101 | 98 | 100 | 323 | 3 | 15 | 636
10893 | 2018-10-24 | 2019-04-03 | 2019-09-27 | 2019-09-30 | COMP | 2019-10-14 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-06-29 | COMP | Rule 15/16 | 109 | 125 | 11 | 141 | 1 | 38 | 421
11161 | 2018-10-24 | 2019-04-15 | 2019-10-25 | 2019-12-12 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2019-12-30 | COMP | 2020-01-30 | COMP | Rule 16 | 117 | 137 | 3 | 1 | 10 | 22 | 316
11294 | 2018-10-24 | 2019-04-22 | 2019-08-05 | 2019-08-05 | COMP | 2019-11-04 | COMP | 2019-12-03 | COMP | 2020-01-30 | COMP | 2020-02-28 | COMP | Rule 16 | 122 | 74 | 65 | 19 | 40 | 21 | 336
11350 | 2018-10-24 | 2019-04-23 | 2019-08-09 | 2019-08-16 | COMP | 2019-10-28 | COMP | 2020-02-25 | COMP | 2020-06-30 | COMP | 2020-07-16 | COMP | Rule 16 | 123 | 77 | 51 | 80 | 90 | 13 | 434
11736 | 2018-10-24 | 2019-05-09 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-11-25 | COMP | 2020-01-23 | COMP | Rule 16 | 135 | 45 | 21 | 1 | 75 | 39 | 311
12274 | 2018-10-24 | 2019-05-29 | 2020-05-20 | 2020-05-20 | COMP | 2021-02-26 | COMP | 2021-04-15 | COMP | 2021-07-20 | COMP | 2021-08-19 | COMP | Rule 15/16 | 148 | 247 | 194 | 35 | 67 | 23 | 709
13060 | 2018-10-24 | 2019-07-09 | 2019-12-20 | 2019-12-20 | COMP | 2020-02-05 | COMP | 2020-02-06 | COMP | 2020-02-11 | COMP | 2020-02-18 | COMP | Rule 16 | 176 | 115 | 31 | 2 | 4 | 5 | 328
13150 | 2018-10-24 | 2019-07-12 | 2019-11-17 | 2019-11-17 | COMP | 2020-02-26 | COMP | 2020-05-18 | COMP | 2021-01-23 | COMP | 2021-03-05 | COMP | Rule 16 | 179 | 89 | 67 | 59 | 172 | 29 | 592
17029 | 2018-10-24 | 2020-01-29 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-07-27 | COMP | 2020-08-31 | COMP | Rule 16 | 315 | 41 | 44 | 1 | 44 | 26 | 466
4103 | 2018-10-25 | 2019-02-05 | 2019-10-28 | 2019-10-28 | COMP | 2020-06-29 | COMP | 2020-06-22 | COMP | 2020-06-10 | COMP | 2020-07-10 | COMP | Rule 16 | 68 | 186 | 168 |  | 0 | 15 | 429
7840 | 2018-10-25 | 2018-11-02 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-15 | COMP | 2019-03-01 | COMP | 2019-04-16 | COMP | 2019-05-22 | COMP | Rule 16 | 7 | 51 | 20 | 10 | 33 | 27 | 143
7875 | 2018-10-25 | 2018-11-03 | 2019-01-28 | 2019-02-01 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2019-02-20 | COMP | 2019-03-27 | COMP | Rule 16 | 7 | 55 | 13 | 1 | 1 | 26 | 103
7884 | 2018-10-25 | 2018-11-03 | 2018-12-18 | 2022-05-16 | COMP | 2022-06-24 | COMP | 2022-08-16 | COMP | 2022-08-15 | COMP | 2022-09-30 | COMP | Rule 15/16 | 7 | 29 | 28 | 37 | 0 | 33 | 989
7995 | 2018-10-25 | 2018-11-08 | 2018-12-15 | 2018-12-15 | COMP | 2019-01-17 | COMP | 2019-03-28 | COMP | 2019-04-09 | COMP | 2019-04-12 | COMP | Rule 15/16 | 11 | 24 | 22 | 49 | 9 | 4 | 115
8022 | 2018-10-25 | 2018-11-09 | 2019-03-21 | 2019-03-21 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-04-26 | COMP | Rule 16 | 12 | 88 | 16 | 1 | 1 | 12 | 125
8093 | 2018-10-25 | 2018-11-15 | 2019-01-26 | 2019-01-26 | COMP | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-05-14 | COMP | 2019-06-15 | COMP | Rule 16 | 15 | 47 | 52 | 1 | 25 | 23 | 159
8351 | 2018-10-25 | 2018-11-27 | 2019-04-08 | 2019-04-08 | COMP | 2019-04-30 | COMP | 2019-06-12 | COMP | 2019-08-01 | COMP | 2019-09-04 | COMP | Rule 16 | 21 | 91 | 17 | 31 | 36 | 24 | 215
8656 | 2018-10-25 | 2018-12-13 | 2019-02-23 | 2019-02-23 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-06-22 | COMP | 2019-06-27 | COMP | Rule 16 | 33 | 48 | 48 | 1 | 37 | 4 | 168
8738 | 2018-10-25 | 2018-12-20 | 2019-04-14 | 2019-04-14 | COMP | 2019-05-09 | COMP | 2019-05-15 | COMP | 2019-08-20 | COMP | 2019-09-12 | COMP | Rule 16 | 38 | 78 | 19 | 5 | 68 | 17 | 221
8743 | 2018-10-25 | 2018-12-20 | 2019-05-16 | 2022-04-28 | COMP | 2022-06-08 | COMP | 2023-06-23 | COMP | 2023-05-31 | COMP | 2023-07-22 | COMP | Rule 15/16 | 38 | 102 | 29 | 261 | 0 | 20 | 1189
8771 | 2018-10-25 | 2018-12-26 | 2019-03-05 | 2019-03-05 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-03-29 | COMP | 2019-05-21 | COMP | Rule 16 | 41 | 47 | 15 | 1 | 5 | 38 | 142
8784 | 2018-10-25 | 2018-12-24 | 2019-02-10 | 2019-02-10 | COMP | 2019-03-05 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-04-17 | COMP | Rule 16 | 40 | 32 | 16 | 4 | 1 | 29 | 118
8853 | 2018-10-25 | 2019-01-03 | 2019-04-02 | 2019-12-11 | COMP | 2019-08-07 | COMP | 2020-04-10 | COMP | 2020-06-29 | COMP | 2020-08-11 | COMP | Rule 15/16 | 46 | 62 |  | 170 | 56 | 32 | 451
8869 | 2018-10-25 | 2019-01-03 | 2019-05-02 | 2020-01-21 | COMP | 2020-02-21 | COMP | 2020-04-10 | COMP | 2020-06-29 | COMP | 2020-08-11 | COMP | Rule 16 | 46 | 84 | 23 | 36 | 56 | 32 | 451
8870 | 2018-10-25 | 2019-01-03 | 2019-04-02 | 2020-01-21 | COMP | 2020-02-21 | COMP | 2020-04-13 | COMP | 2020-10-06 | COMP | 2020-10-10 | COMP | Rule 16 | 46 | 62 | 23 | 37 | 125 | 4 | 493
8944 | 2018-10-25 | 2019-01-08 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-07 | COMP | 2019-02-19 | COMP |  | INPR | 2019-04-19 | COMP | Rule 16 | 49 | 17 | 6 | 8 |  |  | 120
8960 | 2018-10-25 | 2019-01-09 | 2019-04-11 | 2020-03-18 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-05-26 | COMP | 2020-06-12 | COMP | Rule 16 | 50 | 65 | 7 | 1 | 43 | 14 | 409
9085 | 2018-10-25 | 2019-01-16 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-27 | COMP | 2019-06-14 | COMP | 2019-08-05 | COMP | 2019-09-06 | COMP | Rule 16 | 55 | 31 | 19 | 57 | 36 | 24 | 217
9435 | 2018-10-25 | 2019-02-04 | 2019-07-24 | 2021-05-26 | COMP | 2021-07-14 | COMP | 2021-07-26 | COMP | 2021-07-20 | COMP | 2021-09-17 | COMP | Rule 15/16 | 67 | 120 | 34 | 9 | 0 | 39 | 728
9585 | 2018-10-25 | 2019-02-07 | 2019-04-29 | 2019-04-29 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-08-02 | COMP | 2019-09-05 | COMP | Rule 16 | 70 | 57 | 7 | 1 | 62 | 24 | 216
9633 | 2018-10-25 | 2019-02-09 | 2019-05-12 | 2019-05-12 | COMP | 2019-06-03 | COMP | 2019-06-27 | COMP | 2019-08-05 | COMP | 2019-09-05 | COMP | Rule 16 | 71 | 64 | 15 | 19 | 27 | 23 | 216
9729 | 2018-10-25 | 2019-02-12 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-14 | COMP | 2019-05-28 | COMP | 2019-05-29 | COMP | 2019-06-27 | COMP | Rule 16 | 73 | 58 | 8 | 10 | 2 | 22 | 168
10020 | 2018-10-25 | 2019-02-27 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-25 | COMP | 2019-05-09 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | Rule 16 | 83 | 30 | 13 | 11 | 115 | 2 | 249
10134 | 2018-10-25 | 2019-03-04 | 2019-09-10 | 2019-09-10 | COMP | 2019-11-08 | COMP | 2019-11-13 | COMP | 2019-11-27 | COMP | 2020-01-03 | COMP | Rule 16 | 86 | 134 | 44 | 3 | 11 | 24 | 297
10303 | 2018-10-25 | 2019-03-11 | 2019-03-27 | 2019-03-27 | COMP | 2019-05-01 | COMP | 2019-10-07 | COMP | 2020-03-29 | INPR | 2019-12-10 | COMP | Rule 16 | 91 | 13 | 26 | 111 |  |  | 281
10398 | 2018-10-25 | 2019-03-14 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-12 | COMP | 2019-07-08 | COMP | 2019-07-02 | COMP | 2019-08-19 | COMP | Rule 16 | 94 | 47 | 18 | 18 | 0 | 31 | 204
10510 | 2018-10-25 | 2019-03-19 | 2019-07-01 | 2019-07-01 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2020-05-31 | INPR | 2019-10-14 | COMP | Rule 16 | 97 | 74 | 37 | 1 |  |  | 243
10631 | 2018-10-25 | 2019-03-23 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-03 | COMP | 2019-07-16 | COMP | 2019-07-24 | COMP | 2019-07-28 | COMP | Rule 16 | 100 | 47 | 4 | 31 | 7 | 3 | 188
10682 | 2018-10-25 | 2019-03-25 | 2019-06-05 | 2019-06-05 | COMP | 2019-08-06 | COMP | 2019-12-17 | COMP | 2019-10-28 | COMP | 2020-01-03 | COMP | Rule 16 | 101 | 52 | 44 | 92 | 0 | 12 | 297
10753 | 2018-10-25 | 2019-03-28 | 2019-05-17 | 2019-05-17 | COMP | 2019-07-25 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-08-26 | COMP | Rule 16 | 104 | 37 | 48 | 6 | 1 | 18 | 209
11281 | 2018-10-25 | 2019-04-22 | 2019-09-10 | 2019-09-10 | COMP | 2019-10-07 | COMP | 2019-10-07 | COMP | 2020-03-13 | COMP | 2020-07-17 | COMP | Rule 16 | 121 | 99 | 20 | 1 | 108 | 90 | 434
11295 | 2018-10-25 | 2019-04-22 | 2019-06-24 | 2019-06-25 | COMP | 2019-09-04 | COMP | 2019-09-05 | COMP | 2019-09-25 | COMP | 2019-11-06 | COMP | Rule 16 | 121 | 45 | 50 | 2 | 15 | 31 | 260
11506 | 2018-10-25 | 2019-04-30 | 2019-08-24 | 2019-08-24 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2020-01-29 | COMP | 2020-02-11 | COMP | Rule 16 | 127 | 82 | 76 | 1 | 31 | 10 | 323
11609 | 2018-10-25 | 2019-05-05 | 2019-09-06 | 2020-02-04 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2019-12-10 | COMP | 2020-03-03 | COMP | Rule 16 | 130 | 87 | 2 | 1 | 0 | 19 | 337
12773 | 2018-10-25 | 2019-06-21 | 2019-07-18 | 2019-07-18 | COMP | 2019-08-08 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2019-08-23 | COMP | Rule 16 | 164 | 19 | 16 | 6 | 1 | 7 | 208
13466 | 2018-10-25 | 2019-07-26 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-18 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-06-19 | COMP | Rule 16 | 188 | 68 | 13 | 125 | 1 | 24 | 414
14701 | 2018-10-25 | 2019-09-23 | 2019-11-14 | 2019-11-14 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2022-01-30 | INPR | 2020-06-25 | COMP | Rule 16 | 228 | 38 | 35 | 1 |  |  | 418
14786 | 2018-10-25 | 2019-09-27 | 2020-01-14 | 2020-08-03 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2021-02-09 | COMP | 2021-04-15 | COMP | Rule 15/16 | 232 | 73 | 28 | 1 | 103 | 47 | 620
14835 | 2018-10-25 | 2019-09-30 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-29 | COMP | 2020-05-05 | COMP | 2020-07-01 | COMP | 2020-07-30 | COMP | Rule 16 | 233 | 125 | 22 | 5 | 41 | 22 | 443
17109 | 2018-10-25 | 2020-01-31 | 2021-06-16 | 2021-06-16 | COMP | 2021-07-27 | COMP | 2022-09-08 | COMP | 2023-08-11 | COMP | 2023-11-15 | COMP | Rule 15/16 | 316 | 348 | 29 | 283 | 232 | 67 | 1270
34597 | 2018-10-25 | 2022-02-22 | 2022-04-28 | 2022-04-28 | COMP | 2022-06-08 | COMP | 2023-09-18 | COMP | 2023-09-18 | COMP | 2023-10-25 | COMP | Rule 15/16 | 835 | 48 | 29 | 320 | 1 | 28 | 1256
8259 | 2018-10-26 | 2018-11-20 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-23 | COMP | 2019-02-13 | INPR | 2019-03-06 | COMP | 2019-03-29 | COMP | Rule 16 | 17 | 33 | 10 |  |  |  | 104
8309 | 2018-10-26 | 2018-11-26 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-27 | COMP | 2019-02-27 | COMP | 2019-03-13 | COMP | 2019-04-01 | COMP | Rule 16 | 19 | 55 | 10 | 1 | 11 | 14 | 105
8356 | 2018-10-26 | 2018-11-28 | 2019-02-11 | 2019-04-10 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2022-01-30 | INPR | 2020-09-17 | COMP | Rule 16 | 21 | 51 | 28 | 1 |  |  | 476
8482 | 2018-10-26 | 2018-12-04 | 2019-01-23 | 2019-01-23 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-05-20 | COMP | 2019-08-01 | COMP | Rule 15/16 | 25 | 34 | 95 | 1 | 0 | 40 | 191
8547 | 2018-10-26 | 2018-12-07 | 2019-03-26 | 2019-03-26 | COMP | 2019-05-28 | COMP | 2019-06-04 | COMP | 2019-05-17 | COMP | 2019-07-15 | COMP | Rule 16 | 28 | 74 | 45 | 6 | 0 | 29 | 178
8603 | 2018-10-26 | 2018-12-11 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-20 | COMP | 2019-08-20 | COMP | Rule 16 | 30 | 86 | 27 | 1 | 22 | 43 | 204
8635 | 2018-10-26 | 2018-12-13 | 2019-01-23 | 2019-01-23 | COMP | 2019-02-08 | COMP | 2019-02-12 | NOTN | 2018-12-17 | COMP | 2019-03-12 | COMP | Rule 16 | 32 | 27 | 13 |  |  |  | 91
8662 | 2018-10-26 | 2018-12-13 | 2019-03-18 | 2019-03-18 | COMP | 2019-07-18 | COMP | 2019-07-22 | COMP | 2019-07-09 | COMP | 2019-08-20 | COMP | Rule 16 | 32 | 64 | 87 | 3 | 0 | 22 | 204
8691 | 2018-10-26 | 2018-12-17 | 2019-01-02 | 2019-01-02 | COMP | 2019-01-17 | COMP | 2019-01-17 | INPR | 2019-01-17 | COMP | 2019-01-22 | COMP | Rule 16 | 34 | 11 | 12 |  |  |  | 57
8877 | 2018-10-26 | 2019-01-03 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-05-08 | COMP | 2019-05-31 | COMP | Rule 16 | 45 | 68 | 14 | 1 | 8 | 17 | 148
8892 | 2018-10-26 | 2019-01-05 | 2020-03-06 | 2020-03-06 | COMP | 2021-01-05 | COMP | 2021-03-08 | COMP | 2021-03-02 | COMP | 2021-04-22 | COMP | Rule 15/16 | 46 | 293 | 211 | 43 | 0 | 34 | 624
9060 | 2018-10-26 | 2019-01-15 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-07-08 | COMP | 2019-08-26 | COMP | Rule 16 | 53 | 58 | 19 | 1 | 46 | 36 | 208
9177 | 2018-10-26 | 2019-01-20 | 2019-03-04 | 2019-03-04 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | 2019-08-30 | COMP | 2019-09-03 | COMP | Rule 16 | 56 | 29 | 67 | 6 | 57 | 2 | 213
9189 | 2018-10-26 | 2019-01-20 | 2019-04-19 | 2019-06-29 | COMP | 2019-07-17 | COMP | 2019-05-16 | COMP | 2019-08-02 | COMP | 2019-08-10 | COMP | Rule 16 | 56 | 63 | 12 |  | 55 | 6 | 197
9966 | 2018-10-26 | 2019-02-25 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-01 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-11-23 | COMP | Rule 16 | 80 | 72 | 19 | 46 | 1 | 57 | 270
10170 | 2018-10-26 | 2019-03-05 | 2019-06-14 | 2019-06-14 | COMP | 2019-11-18 | COMP | 2019-11-19 | COMP | 2019-11-18 | COMP | 2020-01-05 | COMP | Rule 15/16 | 86 | 73 | 109 | 2 | 0 | 30 | 296
10275 | 2018-10-26 | 2019-03-08 | 2019-06-04 | 2019-06-04 | COMP | 2019-11-21 | COMP | 2019-09-06 | COMP | 2019-10-04 | COMP | 2020-01-17 | COMP | Rule 16 | 89 | 62 | 120 |  | 21 | 71 | 306
11050 | 2018-10-26 | 2019-04-10 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-08-26 | COMP | 2019-09-10 | COMP | Rule 16 | 112 | 16 | 5 | 1 | 78 | 11 | 218
11358 | 2018-10-26 | 2019-04-24 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-03 | COMP | 2019-10-14 | COMP | 2019-10-07 | COMP | 2019-10-21 | COMP | Rule 15/16 | 122 | 80 | 13 | 30 | 0 | 6 | 247
11785 | 2018-10-26 | 2019-05-11 | 2019-08-16 | 2019-08-16 | COMP | 2019-09-11 | COMP | 2019-10-11 | COMP | 2019-10-25 | COMP | 2019-12-04 | COMP | Rule 16 | 134 | 68 | 18 | 23 | 11 | 26 | 276
12109 | 2018-10-26 | 2019-05-23 | 2019-07-01 | 2019-07-01 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-08-02 | COMP | 2019-08-29 | COMP | Rule 16 | 143 | 27 | 23 | 1 | 2 | 20 | 211
13325 | 2018-10-26 | 2019-07-19 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-10 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2020-01-09 | COMP | Rule 16 | 182 | 95 | 5 | 3 | 1 | 19 | 300
13490 | 2018-10-26 | 2019-07-26 | 2019-10-18 | 2021-01-05 | COMP | 2021-02-23 | COMP | 2022-06-18 | REQD | 2020-06-22 | COMP | 2021-06-04 | COMP | Rule 16 | 187 | 60 | 34 |  |  |  | 654
23250 | 2018-10-26 | 2020-10-30 | 2021-01-16 | 2021-01-16 | COMP | 2021-02-23 | COMP | 2021-06-07 | COMP | 2021-08-10 | COMP | 2021-09-09 | COMP | Rule 15/16 | 507 | 51 | 25 | 74 | 46 | 22 | 721
7738 | 2018-10-27 | 2018-10-29 | 2019-01-08 | 2019-01-08 | COMP | 2019-03-08 | NOTN | 2019-03-08 | COMP | 2018-06-08 | COMP | 2019-04-16 | COMP | Other | 1 | 47 |  | 42 | 0 | 28 | 115
8261 | 2018-10-27 | 2018-11-20 | 2019-01-24 | 2019-01-24 | COMP | 2019-01-23 | NOTN | 2019-01-24 | COMP | 2019-01-30 | NOTN | 2019-04-01 | COMP | Other | 16 | 43 |  | 1 |  |  | 104
8306 | 2018-10-27 | 2018-11-26 | 2019-05-31 | 2019-05-31 | COMP | 2019-08-09 | COMP | 2019-09-30 | COMP | 2019-10-25 | COMP | 2019-12-06 | COMP | Rule 15/16 | 18 | 130 | 50 | 36 | 20 | 28 | 277
10096 | 2018-10-27 | 2019-03-01 | 2019-05-25 | 2019-05-25 | COMP | 2019-10-07 | COMP | 2020-02-07 | COMP | 2020-04-06 | COMP | 2020-06-11 | COMP | Rule 16 | 83 | 61 | 93 | 84 | 41 | 48 | 406
10368 | 2018-10-27 | 2019-03-12 | 2019-05-25 | 2019-05-25 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-01-23 | COMP | 2020-04-14 | COMP | Rule 16 | 90 | 54 | 130 | 1 | 36 | 58 | 365
11409 | 2018-10-27 | 2019-04-25 | 2019-07-22 | 2019-08-21 | COMP | 2019-09-03 | COMP | 2019-12-30 | COMP | 2020-02-03 | COMP | 2020-02-27 | COMP | Rule 15/16 | 122 | 61 | 9 | 81 | 24 | 18 | 332
7931 | 2018-10-28 | 2018-11-07 | 2019-01-22 | 2019-04-29 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-09-17 | COMP | 2020-01-21 | COMP | Rule 15/16 | 8 | 49 | 19 | 1 | 81 | 85 | 306
7932 | 2018-10-28 | 2018-11-07 | 2018-12-26 | 2019-06-25 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP |  | INPR | 2020-05-13 | COMP | Rule 15/16 | 8 | 32 | 23 | 1 |  |  | 386
11264 | 2018-10-28 | 2019-04-19 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2020-01-19 | INPR | 2019-10-07 | COMP | Rule 15/16 | 118 | 76 | 6 | 1 |  |  | 236
4022 | 2018-10-29 | 2018-12-04 | 2019-01-03 | 2019-01-03 | COMP | 2019-02-06 | COMP | 2019-02-09 | COMP | 2019-03-01 | COMP | 2019-04-11 | COMP | Rule 15/16 | 24 | 21 | 24 | 3 | 14 | 30 | 112
7889 | 2018-10-29 | 2018-11-04 | 2018-12-12 | 2019-03-01 | COMP | 2019-03-27 | COMP | 2019-07-30 | COMP | 2019-08-05 | COMP | 2019-09-03 | COMP | Rule 16 | 5 | 25 | 19 | 88 | 5 | 21 | 212
7892 | 2018-10-29 | 2018-11-04 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-13 | COMP | 2019-04-08 | COMP | 2019-12-28 | INPR | 2019-07-16 | COMP | Rule 16 | 5 | 54 | 14 | 38 |  |  | 178
7906 | 2018-10-29 | 2018-11-05 | 2019-01-31 | 2019-01-31 | COMP | 2019-02-13 | COMP | 2019-02-13 | COMP | 2019-02-19 | COMP | 2019-03-28 | COMP | Rule 16 | 6 | 58 | 10 | 1 | 4 | 28 | 102
8089 | 2018-10-29 | 2018-11-16 | 2019-04-17 | 2019-04-17 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-05 | COMP | 2019-09-13 | COMP | Rule 15/16 | 14 | 103 | 73 | 1 | 5 | 29 | 220
8094 | 2018-10-29 | 2018-11-15 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-27 | COMP | 2019-02-28 | COMP | 2019-01-28 | COMP | 2019-03-15 | COMP | Rule 16 | 13 | 48 | 22 | 2 | 0 | 12 | 93
8304 | 2018-10-29 | 2018-11-26 | 2019-09-09 | 2019-09-09 | COMP | 2019-10-16 | COMP | 2019-12-12 | COMP | 2020-01-02 | COMP | 2019-12-31 | COMP | Rule 15/16 | 18 | 199 | 28 | 39 | 14 |  | 293
8310 | 2018-10-29 | 2018-11-26 | 2019-03-29 | 2019-03-29 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-08-06 | COMP | 2019-08-19 | COMP | Rule 15/16 | 18 | 86 | 59 | 1 | 33 | 10 | 202
8379 | 2018-10-29 | 2018-11-28 | 2020-01-28 | 2020-01-28 | COMP | 2020-12-07 | NOTN | 2020-12-07 | COMP | 2021-04-19 | COMP | 2021-05-21 | COMP | Other | 20 | 292 |  | 219 | 92 | 25 | 644
8407 | 2018-10-29 | 2018-11-30 | 2018-12-05 | 2018-12-05 | COMP | 2018-12-20 | COMP | 2018-12-20 | COMP | 2018-12-21 | COMP | 2019-01-05 | COMP | Rule 16 | 22 | 4 | 12 | 1 | 2 | 9 | 45
8424 | 2018-10-29 | 2018-12-01 | 2018-12-11 | 2019-05-21 | COMP | 2019-06-18 | COMP | 2019-06-18 | COMP | 2020-02-29 | INPR | 2019-11-18 | COMP | Rule 15/16 | 22 | 7 | 20 | 1 |  |  | 265
8546 | 2018-10-29 | 2018-12-07 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-26 | COMP | 2019-04-17 | COMP | 2021-02-27 | INPR | 2020-02-14 | COMP | Rule 16 | 27 | 63 | 12 | 17 |  |  | 324
8678 | 2018-10-29 | 2018-12-15 | 2019-01-08 | 2019-07-08 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-07-23 | COMP | 2019-08-19 | COMP | Rule 16 | 32 | 15 | 5 | 1 | 8 | 20 | 202
8706 | 2018-10-29 | 2018-12-19 | 2019-03-26 | 2019-03-26 | COMP | 2020-09-29 | COMP | 2021-04-09 | COMP | 2024-02-03 | INPR | 2021-10-02 | COMP | Rule 16 | 35 | 66 | 384 | 132 |  |  | 736
8844 | 2018-10-29 | 2019-01-02 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-09-03 | COMP | 2019-10-02 | COMP | Rule 16 | 43 | 39 | 39 | 1 | 94 | 22 | 233
8969 | 2018-10-29 | 2019-01-09 | 2019-04-10 | 2019-07-15 | COMP | 2019-08-06 | COMP | 2019-08-15 | COMP | 2019-08-09 | COMP | 2019-09-16 | COMP | Rule 15/16 | 48 | 64 | 17 | 8 | 0 | 22 | 221
9007 | 2018-10-29 | 2019-01-12 | 2019-03-08 | 2019-04-01 | COMP | 2019-04-11 | COMP | 2019-08-28 | COMP | 2019-09-15 | COMP | 2019-09-20 | COMP | Rule 16 | 50 | 38 | 9 | 98 | 12 | 5 | 225
9262 | 2018-10-29 | 2019-01-25 | 2019-03-08 | 2019-03-08 | COMP | 2019-03-22 | COMP | 2019-04-26 | COMP | 2019-04-23 | COMP | 2019-06-05 | COMP | Rule 16 | 59 | 30 | 11 | 26 | 0 | 28 | 150
9361 | 2018-10-29 | 2019-01-31 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-23 | COMP | 2019-08-23 | COMP | 2019-09-05 | COMP | 2020-01-28 | COMP | Rule 16 | 63 | 50 | 31 | 65 | 9 | 98 | 311
9376 | 2018-10-29 | 2019-01-31 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-05-22 | COMP | 2019-08-06 | COMP | Rule 16 | 63 | 49 | 13 | 1 | 19 | 53 | 193
9827 | 2018-10-29 | 2019-02-19 | 2019-09-09 | 2020-01-28 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-03-05 | COMP | 2020-04-30 | COMP | Rule 15/16 | 75 | 142 | 20 | 1 | 8 | 41 | 377
9858 | 2018-10-29 | 2019-02-20 | 2019-06-03 | 2020-01-30 | COMP | 2021-08-30 | COMP | 2019-08-01 | COMP | 2022-03-14 | COMP | 2022-04-24 | COMP | Rule 16 | 76 | 73 | 401 |  | 658 | 30 | 876
10282 | 2018-10-29 | 2019-03-08 | 2019-07-26 | 2019-07-26 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2020-06-22 | COMP | 2020-08-25 | COMP | Rule 16 | 88 | 99 | 93 | 1 | 136 | 47 | 459
10777 | 2018-10-29 | 2019-03-29 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-23 | COMP | 2019-11-25 | COMP | 2019-10-21 | COMP | 2020-06-18 | COMP | Rule 15/16 | 103 | 77 | 28 | 65 | 0 | 142 | 411
10920 | 2018-10-29 | 2019-04-04 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-12-29 | INPR | 2019-08-21 | COMP | Rule 16 | 107 | 61 | 4 | 1 |  |  | 204
11735 | 2018-10-29 | 2019-05-09 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-07 | COMP | 2019-09-23 | COMP | 2019-09-10 | COMP | 2019-11-12 | COMP | Rule 16 | 132 | 36 | 28 | 33 | 0 | 36 | 261
13181 | 2018-10-29 | 2019-07-16 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-18 | COMP | 2019-11-20 | COMP | 2020-02-25 | COMP | 2020-03-11 | COMP | Rule 16 | 178 | 64 | 5 | 23 | 64 | 12 | 341
13357 | 2018-10-29 | 2019-07-22 | 2020-01-09 | 2020-01-09 | COMP | 2020-04-03 | COMP | 2020-06-10 | COMP | 2023-09-02 | INPR | 2020-08-05 | COMP | Rule 15/16 | 182 | 118 | 60 | 48 |  |  | 445
14334 | 2018-10-29 | 2019-09-05 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-07 | NOTN | 2020-01-07 | COMP | 2023-04-30 | INPR | 2020-06-15 | COMP | Other | 214 | 84 |  | 1 |  |  | 408
14946 | 2018-10-29 | 2019-10-05 | 2020-01-10 | 2020-01-31 | COMP | 2020-02-27 | COMP | 2020-03-27 | COMP | 2022-08-21 | INPR | 2020-06-18 | COMP | Rule 16 | 235 | 65 | 19 | 22 |  |  | 411
20374 | 2018-10-29 | 2020-06-18 | 2021-03-16 | 2021-05-20 | COMP | 2021-06-07 | COMP |  | REQD | 2021-08-06 | COMP | 2021-08-11 | COMP | Rule 15/16 | 411 | 186 | 12 |  |  |  | 700
4084 | 2018-10-30 | 2019-01-17 | 2019-03-21 | 2019-03-21 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-06-18 | COMP | 2019-07-11 | COMP | Rule 15/16 | 53 | 44 | 60 | 1 | 4 | 17 | 174
4154 | 2018-10-30 | 2019-04-16 | 2019-05-03 | 2019-08-05 | COMP | 2019-08-26 | COMP | 2019-08-29 | COMP | 2019-10-16 | COMP | 2019-11-13 | COMP | Rule 16 | 114 | 14 | 16 | 4 | 34 | 20 | 261
7760 | 2018-10-30 | 2018-10-30 | 2019-02-25 | 2019-02-25 | COMP | 2019-02-25 | NOTN | 2019-09-05 | COMP | 2019-09-06 | COMP | 2020-06-02 | COMP | Other | 1 | 78 |  | 136 | 2 | 185 | 398
7852 | 2018-10-30 | 2018-11-02 | 2019-01-03 | 2019-01-03 | COMP | 2019-04-30 | COMP | 2019-05-06 | COMP | 2019-09-22 | INPR | 2019-06-05 | COMP | Rule 16 | 4 | 40 | 82 | 5 |  |  | 149
8073 | 2018-10-30 | 2018-11-14 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-24 | COMP | 2019-05-14 | COMP | 2019-08-15 | COMP | 2019-09-09 | COMP | Rule 16 | 11 | 105 | 28 |  | 66 | 17 | 215
8074 | 2018-10-30 | 2018-11-14 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-03 | NOTN | 2019-07-03 | COMP | 2020-01-07 | COMP | 2020-03-11 | COMP | Rule 16 | 11 | 146 |  | 14 | 128 | 45 | 340
8124 | 2018-10-30 | 2018-11-16 | 2019-10-16 | 2019-10-16 | COMP | 2020-04-29 | COMP | 2020-06-23 | COMP | 2020-07-10 | COMP | 2020-08-24 | COMP | Rule 15/16 | 13 | 230 | 134 | 39 | 14 | 32 | 457
8286 | 2018-10-30 | 2018-11-26 | 2019-01-03 | 2019-01-03 | COMP | 2019-01-15 | COMP | 2019-01-15 | COMP | 2019-03-01 | COMP | 2019-03-26 | COMP | Rule 16 | 17 | 27 | 9 | 1 | 32 | 18 | 99
8316 | 2018-10-30 | 2018-11-27 | 2019-03-24 | 2019-03-24 | COMP | 2019-04-17 | COMP | 2020-05-22 | INPR | 2020-06-17 | COMP | 2020-07-06 | COMP | Rule 15/16 | 18 | 80 | 18 |  |  |  | 422
8413 | 2018-10-30 | 2018-11-30 | 2019-03-22 | 2019-03-22 | COMP | 2019-10-23 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-02-26 | COMP | Rule 16 | 21 | 77 | 151 | 28 | 1 | 57 | 330
8469 | 2018-10-30 | 2018-12-04 | 2019-03-19 | 2019-03-19 | COMP | 2019-03-23 | NOTN | 2019-03-23 | COMP | 2019-05-30 | COMP | 2019-07-08 | COMP | Other | 23 | 72 |  | 4 | 48 | 27 | 171
8555 | 2018-10-30 | 2018-12-10 | 2019-02-05 | 2019-02-05 | COMP | 2019-02-19 | COMP | 2019-02-19 | COMP | 2019-07-21 | INPR | 2019-03-13 | COMP | Rule 16 | 27 | 39 | 10 | 1 |  |  | 90
8601 | 2018-10-30 | 2018-12-11 | 2019-03-14 | 2019-03-14 | COMP | 2019-05-10 | COMP | 2019-08-08 | COMP | 2020-01-08 | COMP | 2020-03-13 | COMP | Rule 16 | 28 | 64 | 42 | 63 | 104 | 46 | 342
8616 | 2018-10-30 | 2018-12-12 | 2019-03-18 | 2019-03-18 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-12-31 | COMP | 2020-01-23 | COMP | Rule 16 | 29 | 65 | 6 | 1 | 195 | 16 | 307
8688 | 2018-10-30 | 2018-12-17 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-10-21 | INPR | 2019-05-17 | COMP | Rule 16 | 32 | 55 | 9 | 1 |  |  | 137
8704 | 2018-10-30 | 2018-12-19 | 2019-01-22 | 2019-03-25 | COMP | 2021-01-15 | COMP | 2021-09-15 | COMP | 2021-11-08 | COMP | 2021-12-09 | COMP | Rule 16 | 34 | 22 | 458 | 169 | 39 | 21 | 781
8741 | 2018-10-30 | 2018-12-20 | 2019-02-10 | 2019-02-10 | COMP | 2019-02-19 | COMP | 2019-03-29 | COMP | 2019-03-18 | COMP | 2019-06-20 | COMP | Rule 16 | 35 | 34 | 6 | 29 | 0 | 59 | 160
8859 | 2018-10-30 | 2019-01-03 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-03-12 | COMP | 2019-04-05 | COMP | Rule 16 | 43 | 37 | 8 | 1 | 4 | 19 | 107
8982 | 2018-10-30 | 2019-01-10 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-14 | NOTN | 2019-03-15 | COMP | 2019-03-28 | COMP | 2019-04-10 | COMP | Other | 48 | 24 |  | 22 | 10 | 10 | 110
9067 | 2018-10-30 | 2019-01-15 | 2019-03-15 | 2019-03-15 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2021-05-30 | INPR | 2020-04-23 | COMP | Rule 16 | 51 | 42 | 212 | 1 |  |  | 371
9225 | 2018-10-30 | 2019-01-23 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-29 | COMP | 2019-08-23 | COMP | 2019-10-08 | COMP | 2019-10-15 | COMP | Rule 16 | 56 | 75 | 15 | 62 | 32 | 6 | 241
9280 | 2018-10-30 | 2019-01-27 | 2019-03-22 | 2019-03-22 | COMP | 2019-06-10 | COMP | 2019-06-19 | COMP | 2019-09-16 | COMP | 2019-10-15 | COMP | Rule 15/16 | 58 | 39 | 56 | 8 | 62 | 22 | 241
9512 | 2018-10-30 | 2019-02-06 | 2019-03-22 | 2019-03-22 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2021-10-22 | COMP | 2021-11-08 | COMP | Rule 16 | 66 | 32 | 103 | 1 | 552 | 12 | 761
9691 | 2018-10-30 | 2019-02-11 | 2019-11-07 | 2019-11-07 | COMP | 2020-04-03 | COMP | 2020-05-21 | COMP | 2020-05-04 | COMP | 2020-07-13 | COMP | Rule 15/16 | 69 | 190 | 100 | 35 | 0 | 37 | 427
9837 | 2018-10-30 | 2019-02-20 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-06-18 | COMP | 2019-08-09 | COMP | Rule 16 | 75 | 43 | 23 | 1 | 19 | 38 | 195
10293 | 2018-10-30 | 2019-03-09 | 2019-05-17 | 2019-05-17 | COMP | 2019-07-10 | COMP | 2019-07-11 | COMP | 2020-02-29 | INPR | 2019-11-07 | COMP | Rule 16 | 87 | 50 | 37 | 2 |  |  | 258
10535 | 2018-10-30 | 2019-03-19 | 2019-07-15 | 2019-08-12 | COMP | 2019-08-30 | COMP | 2019-09-30 | COMP | 2019-08-30 | COMP | 2019-10-18 | COMP | Rule 15/16 | 94 | 83 | 15 | 21 | 0 | 15 | 244
10616 | 2018-10-30 | 2019-03-23 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-09 | COMP | 2019-08-27 | COMP | 2019-08-06 | COMP | 2019-09-25 | COMP | Rule 16 | 97 | 63 | 13 | 36 | 0 | 21 | 227
11115 | 2018-10-30 | 2019-04-13 | 2019-06-23 | 2019-06-23 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-11-08 | COMP | 2019-12-09 | COMP | Rule 16 | 112 | 49 | 47 | 1 | 52 | 19 | 277
11439 | 2018-10-30 | 2019-04-27 | 2019-07-23 | 2019-07-23 | COMP | 2019-09-10 | COMP | 2019-10-04 | COMP | 2019-12-10 | COMP | 2019-11-25 | COMP | Rule 16 | 122 | 60 | 35 | 19 | 45 |  | 269
11757 | 2018-10-30 | 2019-05-09 | 2019-11-20 | 2019-11-20 | COMP | 2019-11-27 | COMP | 2020-01-31 | COMP | 2020-01-16 | COMP | 2020-04-07 | COMP | Rule 16 | 131 | 136 | 6 | 43 | 0 | 47 | 359
12453 | 2018-10-30 | 2019-06-08 | 2019-07-28 | 2019-07-28 | COMP | 2019-08-14 | COMP | 2019-10-08 | COMP | 2019-10-15 | COMP | 2019-11-20 | COMP | Rule 16 | 151 | 34 | 13 | 39 | 6 | 26 | 266
13015 | 2018-10-30 | 2019-07-03 | 2019-09-30 | 2020-04-17 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-04-28 | COMP | 2020-04-26 | COMP | Rule 16 | 169 | 62 | 3 | 1 | 6 |  | 372
15847 | 2018-10-30 | 2019-11-25 | 2021-02-23 | 2021-02-23 | COMP | 2021-04-30 | COMP | 2021-08-25 | COMP | 2023-03-27 | COMP | 2023-06-21 | COMP | Rule 16 | 269 | 312 | 49 | 82 | 397 | 61 | 1165
16092 | 2018-10-30 | 2019-12-09 | 2020-05-18 | 2020-05-18 | COMP | 2020-06-10 | COMP | 2020-07-23 | COMP | 2020-08-26 | COMP | 2020-10-31 | COMP | Rule 16 | 277 | 112 | 17 | 32 | 25 | 47 | 505
26770 | 2018-10-30 | 2021-04-01 | 2021-12-17 | 2021-12-17 | COMP | 2022-01-04 | COMP | 2022-05-05 | COMP | 2022-05-03 | COMP | 2022-06-10 | COMP | Rule 15/16 | 607 | 181 | 13 | 86 | 0 | 26 | 909
8015 | 2018-10-31 | 2018-11-09 | 2019-02-02 | 2019-02-02 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2022-01-30 | INPR | 2020-12-16 | COMP | Rule 16 | 8 | 55 | 51 | 1 |  |  | 534
8137 | 2018-10-31 | 2018-11-16 | 2019-01-28 | 2019-03-21 | COMP | 2019-03-22 | NOTN | 2019-03-22 | COMP | 2019-03-22 | COMP | 2019-05-30 | COMP | Other | 12 | 47 |  | 2 | 1 | 49 | 144
8218 | 2018-10-31 | 2018-11-19 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-04-02 | COMP | 2019-05-03 | COMP | Rule 16 | 13 | 58 | 19 | 1 | 16 | 24 | 126
8531 | 2018-10-31 | 2018-12-07 | 2019-10-25 | 2019-10-25 | COMP | 2020-04-06 | COMP | 2019-11-22 | COMP | 2020-07-23 | COMP | 2020-10-06 | COMP | Rule 15/16 | 25 | 224 | 110 |  | 168 | 53 | 486
8532 | 2018-10-31 | 2018-12-07 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-21 | COMP | 2020-07-07 | COMP | 2020-07-23 | COMP | 2020-10-06 | COMP | Rule 15/16 | 25 | 223 | 20 | 157 | 13 | 53 | 486
8533 | 2018-10-31 | 2018-12-07 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-21 | COMP | 2020-07-29 | COMP | 2020-08-17 | COMP | 2020-11-18 | COMP | Rule 15/16 | 25 | 223 | 20 | 173 | 14 | 66 | 516
8668 | 2018-10-31 | 2018-12-14 | 2019-03-12 | 2020-02-01 | COMP | 2020-02-19 | COMP | 2020-03-19 | COMP | 2020-02-20 | COMP | 2020-04-21 | COMP | Rule 16 | 30 | 59 | 12 | 22 | 0 | 24 | 368
8697 | 2018-10-31 | 2018-12-17 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-05 | COMP | 2019-04-22 | COMP | 2019-02-12 | COMP | 2019-05-28 | COMP | Rule 16 | 31 | 23 | 12 | 54 | 0 | 26 | 142
8754 | 2018-10-31 | 2018-12-22 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-15 | COMP | 2019-03-25 | COMP | 2019-02-13 | COMP | 2019-04-17 | COMP | Rule 16 | 35 | 34 | 4 | 26 | 0 | 18 | 114
8923 | 2018-10-31 | 2019-01-07 | 2019-04-02 | 2019-04-18 | COMP | 2019-05-06 | COMP | 2019-08-01 | COMP | 2019-08-21 | COMP | 2019-09-10 | COMP | Rule 16 | 44 | 60 | 13 | 62 | 15 | 14 | 215
9105 | 2018-10-31 | 2019-01-17 | 2019-03-30 | 2019-03-30 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2020-01-08 | COMP | 2020-01-10 | COMP | Rule 16 | 52 | 50 | 23 | 1 | 173 | 3 | 298
9108 | 2018-10-31 | 2019-01-17 | 2019-03-28 | 2019-03-28 | COMP | 2019-07-19 | COMP | 2019-08-12 | COMP | 2019-08-14 | COMP | 2019-09-18 | COMP | Rule 15/16 | 52 | 49 | 80 | 17 | 3 | 25 | 221
9638 | 2018-10-31 | 2019-02-09 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-23 | COMP | 2019-08-21 | COMP | Rule 16 | 67 | 91 | 19 | 1 | 6 | 22 | 202
9738 | 2018-10-31 | 2019-02-13 | 2020-06-28 | 2020-06-28 | COMP | 2021-04-16 | COMP | 2021-04-16 | COMP | 2021-05-04 | COMP | 2021-06-10 | COMP | Rule 16 | 70 | 346 | 202 | 1 | 13 | 27 | 655
9753 | 2018-10-31 | 2019-02-13 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2021-10-23 | INPR | 2020-08-05 | COMP | Rule 16 | 70 | 72 | 19 | 1 |  |  | 443
9754 | 2018-10-31 | 2019-02-13 | 2019-06-26 | 2019-06-26 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP |  | INPR | 2019-12-19 | COMP | Rule 15/16 | 70 | 94 | 61 | 1 |  |  | 284
9855 | 2018-10-31 | 2019-02-20 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-16 | COMP | 2019-05-30 | COMP | 2019-05-31 | COMP | 2019-08-05 | COMP | Rule 16 | 74 | 59 | 4 | 10 | 2 | 46 | 190
10027 | 2018-10-31 | 2019-02-27 | 2019-04-26 | 2019-04-26 | COMP | 2019-06-26 | COMP | 2019-09-17 | COMP | 2019-07-17 | COMP | 2019-09-23 | COMP | Rule 16 | 79 | 43 | 43 | 58 | 0 | 5 | 224
10033 | 2018-10-31 | 2019-02-27 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-12-29 | INPR | 2019-09-04 | COMP | Rule 16 | 79 | 54 | 17 | 1 |  |  | 211
10045 | 2018-10-31 | 2019-02-28 | 2019-04-20 | 2019-04-20 | COMP | 2019-08-28 | COMP | 2020-06-04 | COMP | 2020-07-14 | COMP | 2020-07-21 | COMP | Rule 15/16 | 80 | 37 | 91 | 193 | 29 | 6 | 432
10115 | 2018-10-31 | 2019-03-04 | 2019-04-06 | 2019-04-06 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-12-24 | COMP | 2020-01-14 | COMP | Rule 16 | 82 | 25 | 123 | 1 | 59 | 14 | 300
10392 | 2018-10-31 | 2019-03-14 | 2021-05-05 | 2022-08-24 | COMP | 2022-09-12 | COMP | 2022-12-02 | COMP | 2023-04-07 | COMP | 2023-04-15 | COMP | Rule 15/16 | 90 | 541 | 13 | 57 | 87 | 6 | 1118
11086 | 2018-10-31 | 2019-04-12 | 2019-06-27 | 2019-06-27 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-04-16 | COMP | 2020-08-05 | COMP | Rule 15/16 | 111 | 54 | 88 | 1 | 115 | 79 | 443
11436 | 2018-10-31 | 2019-04-26 | 2019-06-22 | 2019-06-22 | COMP | 2019-07-12 | COMP | 2019-07-15 | COMP | 2020-01-19 | INPR | 2019-08-14 | COMP | Rule 15/16 | 121 | 40 | 14 | 2 |  |  | 197
11469 | 2018-10-31 | 2019-04-29 | 2019-07-15 | 2019-07-15 | COMP | 2019-10-22 | COMP | 2020-01-31 | COMP | 2020-05-29 | COMP | 2020-07-08 | COMP | Rule 16 | 122 | 54 | 71 | 68 | 84 | 29 | 423
11565 | 2018-10-31 | 2019-05-02 | 2019-08-28 | 2019-08-28 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-18 | COMP | 2020-04-10 | COMP | Rule 16 | 125 | 83 | 130 | 1 | 9 | 18 | 361
11995 | 2018-10-31 | 2019-05-20 | 2019-08-16 | 2019-08-16 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2020-10-01 | COMP | 2020-11-03 | COMP | Rule 16 | 137 | 63 | 21 | 1 | 265 | 24 | 506
12396 | 2018-10-31 | 2019-06-04 | 2019-09-04 | 2019-09-04 | COMP | 2019-11-13 | COMP | 2019-11-19 | COMP | 2020-06-09 | COMP | 2020-07-23 | COMP | Rule 16 | 147 | 65 | 50 | 5 | 139 | 33 | 434
12486 | 2018-10-31 | 2019-06-10 | 2019-08-15 | 2019-08-15 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-08-27 | COMP | 2019-09-10 | COMP | Rule 16 | 151 | 48 | 8 | 1 | 2 | 10 | 215
15094 | 2018-10-31 | 2019-10-11 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-05-22 | COMP | 2020-06-13 | COMP | Rule 16 | 238 | 30 | 16 | 1 | 110 | 15 | 405
20967 | 2018-10-31 | 2020-07-15 | 2020-09-03 | 2020-09-03 | COMP | 2020-09-16 | COMP | 2020-10-21 | COMP | 2020-12-27 | COMP | 2020-11-26 | COMP | Rule 16 | 428 | 37 | 9 | 26 | 44 |  | 521
8244 | 2018-11-01 | 2018-11-21 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-01 | NOTN | 2019-05-10 | COMP | 2019-10-22 | NOTN | 2020-03-03 | COMP | Other | 14 | 88 |  | 30 |  |  | 332
8330 | 2018-11-01 | 2018-11-27 | 2019-02-21 | 2019-02-21 | COMP | 2019-03-15 | COMP | 2019-03-15 | COMP | 2019-04-28 | COMP | 2019-06-17 | COMP | Rule 16 | 16 | 59 | 17 | 1 | 31 | 35 | 155
8412 | 2018-11-01 | 2018-11-30 | 2019-01-30 | 2019-01-30 | COMP | 2019-02-27 | COMP | 2019-03-06 | COMP | 2019-06-18 | COMP | 2019-06-29 | COMP | Rule 16 | 19 | 41 | 20 | 6 | 74 | 9 | 164
8428 | 2018-11-01 | 2018-12-01 | 2019-02-13 | 2019-02-13 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-08-09 | COMP | 2019-09-11 | COMP | Rule 16 | 19 | 50 | 57 | 1 | 69 | 23 | 215
8454 | 2018-11-01 | 2018-12-04 | 2019-05-31 | 2019-05-31 | COMP | 2019-08-14 | COMP | 2020-02-28 | COMP | 2020-03-24 | COMP | 2020-03-31 | COMP | Rule 16 | 21 | 124 | 53 | 135 | 18 | 6 | 352
8511 | 2018-11-01 | 2018-12-06 | 2019-09-10 | 2019-09-10 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-12-03 | COMP | 2020-01-13 | COMP | Rule 15/16 | 23 | 192 | 9 | 1 | 50 | 28 | 298
8748 | 2018-11-01 | 2018-12-21 | 2019-04-08 | 2019-04-08 | COMP | 2019-06-05 | COMP | 2019-09-11 | COMP | 2019-11-03 | COMP | 2019-12-19 | COMP | Rule 16 | 34 | 73 | 42 | 69 | 38 | 31 | 283
8749 | 2018-11-01 | 2018-12-21 | 2019-03-18 | 2019-08-05 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-11-18 | COMP | 2020-03-05 | COMP | Rule 15/16 | 34 | 58 | 53 | 1 | 22 | 73 | 334
8750 | 2018-11-01 | 2018-12-21 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-12 | COMP | 2019-04-12 | COMP | 2019-11-18 | COMP | 2020-03-05 | COMP | Rule 16 | 34 | 63 | 15 | 1 | 153 | 73 | 334
8751 | 2018-11-01 | 2018-12-21 | 2019-02-23 | 2019-02-23 | COMP | 2019-04-05 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-03-05 | COMP | Rule 16 | 34 | 42 | 30 | 155 | 1 | 76 | 334
8752 | 2018-11-01 | 2018-12-21 | 2019-04-08 | 2019-10-23 | COMP | 2019-10-30 | COMP | 2019-11-15 | COMP | 2019-10-30 | COMP | 2019-12-19 | COMP | Rule 16 | 34 | 73 | 6 | 12 | 0 | 23 | 283
8924 | 2018-11-01 | 2019-01-07 | 2019-08-20 | 2019-10-28 | COMP | 2019-12-03 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2020-01-15 | COMP | Rule 15/16 | 43 | 158 | 24 | 4 | 1 | 27 | 300
9102 | 2018-11-01 | 2019-01-16 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-25 | COMP | 2019-05-15 | COMP | 2019-05-02 | COMP | 2019-07-10 | COMP | Rule 16 | 50 | 56 | 15 | 15 | 0 | 39 | 171
9116 | 2018-11-01 | 2019-01-17 | 2020-01-24 | 2020-05-06 | COMP | 2020-06-02 | COMP | 2022-02-16 | COMP | 2023-12-06 | COMP | 2023-05-01 | COMP | Rule 15/16 | 51 | 256 | 19 | 432 | 452 |  | 1128
9261 | 2018-11-01 | 2019-01-25 | 2019-03-22 | 2019-03-22 | COMP | 2019-07-08 | COMP | 2019-12-30 | INPR | 2019-12-30 | COMP | 2020-07-21 | COMP | Rule 16 | 56 | 40 | 75 |  |  |  | 431
9780 | 2018-11-01 | 2019-02-15 | 2019-04-05 | 2019-04-05 | COMP | 2019-05-09 | COMP | 2019-08-08 | COMP | 2019-12-17 | COMP | 2020-01-26 | COMP | Rule 16 | 71 | 35 | 25 | 64 | 90 | 26 | 306
9787 | 2018-11-01 | 2019-02-15 | 2019-06-04 | 2019-06-04 | COMP | 2019-10-29 | COMP | 2019-12-06 | COMP | 2019-11-26 | COMP | 2020-01-27 | COMP | Rule 15/16 | 71 | 76 | 104 | 26 | 0 | 34 | 307
9805 | 2018-11-01 | 2019-02-19 | 2020-08-22 | 2020-08-22 | COMP | 2020-12-01 | COMP | 2021-09-29 | COMP | 2022-03-24 | COMP | 2022-04-18 | COMP | Rule 16 | 72 | 383 | 68 | 210 | 122 | 18 | 869
9818 | 2018-11-01 | 2019-02-19 | 2019-06-26 | 2019-06-26 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP |  | INPR | 2020-03-10 | COMP | Rule 15/16 | 72 | 91 | 61 | 1 |  |  | 337
10218 | 2018-11-01 | 2019-03-06 | 2019-03-22 | 2019-03-22 | COMP | 2019-06-11 | COMP | 2019-11-30 | COMP | 2019-09-05 | COMP | 2019-12-24 | COMP | Rule 15/16 | 83 | 13 | 57 | 119 | 0 | 17 | 286
10260 | 2018-11-01 | 2019-03-07 | 2019-05-31 | 2020-02-21 | COMP | 2020-04-13 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-09-30 | COMP | Rule 16 | 84 | 61 | 37 | 51 | 1 | 71 | 481
10570 | 2018-11-01 | 2019-03-20 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-17 | NOTN | 2019-06-17 | COMP | 2019-06-17 | COMP | 2019-07-26 | COMP | Other | 93 | 62 |  | 2 | 1 | 29 | 183
10707 | 2018-11-01 | 2019-03-27 | 2019-08-08 | 2019-08-09 | COMP | 2019-08-15 | COMP | 2019-10-18 | COMP | 2019-10-31 | COMP | 2019-11-14 | COMP | Rule 16 | 98 | 95 | 5 | 46 | 10 | 10 | 260
12258 | 2018-11-01 | 2019-05-29 | 2019-08-15 | 2019-08-15 | COMP | 2019-10-18 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2019-12-27 | COMP | Rule 16 | 142 | 56 | 46 | 41 | 1 | 7 | 288
12339 | 2018-11-01 | 2019-06-01 | 2019-08-16 | 2019-08-16 | COMP | 2019-12-18 | COMP | 2020-01-08 | COMP | 2020-01-29 | COMP | 2020-02-04 | COMP | Rule 15/16 | 144 | 54 | 85 | 14 | 15 | 5 | 313
13620 | 2018-11-01 | 2019-08-02 | 2019-08-05 | 2019-08-05 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-05-05 | COMP | 2020-07-22 | COMP | Rule 16 | 188 | 2 | 185 | 1 | 5 | 56 | 432
8014 | 2018-11-02 | 2018-11-09 | 2019-02-02 | 2019-02-02 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-23 | COMP | 2020-07-14 | COMP | Rule 16 | 6 | 55 | 134 | 1 | 9 | 224 | 425
8056 | 2018-11-02 | 2018-11-13 | 2019-03-07 | 2019-05-11 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-07-30 | COMP | 2019-08-12 | COMP | Rule 16 | 7 | 77 | 54 | 1 | 2 | 10 | 193
8132 | 2018-11-02 | 2018-11-16 | 2018-11-27 | 2018-11-27 | COMP | 2019-02-25 | COMP | 2019-03-20 | COMP | 2019-10-21 | INPR | 2019-05-28 | COMP | Rule 16 | 10 | 6 | 61 | 18 |  |  | 140
8133 | 2018-11-02 | 2018-11-16 | 2018-12-03 | 2018-12-03 | COMP | 2019-04-15 | COMP | 2019-05-23 | COMP | 2019-10-21 | INPR | 2019-06-03 | COMP | Rule 16 | 10 | 10 | 92 | 29 |  |  | 144
8187 | 2018-11-02 | 2018-11-19 | 2019-03-31 | 2019-03-31 | COMP | 2019-04-16 | COMP | 2019-09-17 | COMP | 2019-11-07 | COMP | 2019-12-11 | COMP | Rule 16 | 11 | 89 | 12 | 108 | 38 | 22 | 276
8322 | 2018-11-02 | 2018-11-27 | 2019-03-26 | 2019-03-26 | COMP | 2019-05-29 | COMP | 2019-11-22 | COMP | 2019-10-26 | COMP | 2019-12-20 | COMP | Rule 16 | 15 | 82 | 46 | 125 | 0 | 19 | 283
8355 | 2018-11-02 | 2018-11-28 | 2019-06-07 | 2020-08-10 | COMP | 2020-11-09 | COMP | 2021-01-04 | COMP | 2021-01-05 | COMP | 2021-02-18 | COMP | Rule 15/16 | 16 | 133 | 65 | 36 | 2 | 31 | 574
8673 | 2018-11-02 | 2018-12-15 | 2019-02-27 | 2019-02-27 | COMP | 2019-06-20 | COMP | 2019-06-21 | COMP | 2019-06-20 | COMP | 2019-11-07 | COMP | Rule 16 | 28 | 49 | 81 | 2 | 0 | 98 | 255
8702 | 2018-11-02 | 2018-12-19 | 2019-03-14 | 2019-03-14 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-08-27 | COMP | 2020-03-04 | COMP | Rule 16 | 31 | 58 | 59 | 1 | 59 | 129 | 332
8716 | 2018-11-02 | 2018-12-18 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-06 | COMP | 2019-03-06 | COMP | 2019-03-13 | COMP | 2019-04-15 | COMP | Other | 30 | 49 | 5 | 1 | 6 | 24 | 110
8765 | 2018-11-02 | 2018-12-23 | 2019-05-01 | 2019-05-01 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2020-03-25 | COMP | 2020-05-21 | COMP | Rule 16 | 33 | 89 | 38 | 1 | 189 | 42 | 388
8881 | 2018-11-02 | 2019-01-03 | 2019-04-15 | 2020-08-21 | COMP | 2020-10-01 | COMP | 2019-11-05 | COMP | 2020-11-10 | COMP | 2020-12-01 | COMP | Rule 15/16 | 40 | 71 | 29 |  | 257 | 13 | 521
8949 | 2018-11-02 | 2019-01-08 | 2019-05-14 | 2019-07-26 | COMP | 2019-08-20 | COMP | 2019-09-23 | COMP | 2019-12-09 | COMP | 2020-01-31 | COMP | Rule 15/16 | 43 | 89 | 18 | 24 | 53 | 37 | 310
8959 | 2018-11-02 | 2019-01-09 | 2019-03-19 | 2019-05-16 | COMP | 2019-06-11 | COMP | 2019-07-01 | COMP | 2019-07-09 | COMP | 2019-07-26 | COMP | Rule 16 | 44 | 48 | 18 | 15 | 6 | 14 | 182
8961 | 2018-11-02 | 2019-01-09 | 2019-03-06 | 2019-03-06 | COMP | 2019-06-11 | COMP | 2019-07-22 | COMP | 2020-12-28 | COMP | 2021-01-13 | COMP | Rule 16 | 44 | 39 | 69 | 29 | 362 | 12 | 550
8979 | 2018-11-02 | 2019-01-10 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-13 | COMP | 2019-04-01 | COMP | 2019-05-07 | NOTN | 2019-07-30 | COMP | Rule 16 | 45 | 30 | 14 | 14 |  |  | 184
9039 | 2018-11-02 | 2019-01-14 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-26 | COMP | 2020-01-31 | COMP | 2020-02-11 | COMP | 2020-06-09 | COMP | Rule 16 | 47 | 62 | 12 | 192 | 8 | 84 | 400
9047 | 2018-11-02 | 2019-01-14 | 2019-03-04 | 2019-03-04 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-12-29 | INPR | 2019-09-05 | COMP | Rule 16 | 47 | 34 | 56 | 1 |  |  | 210
9083 | 2018-11-02 | 2019-01-16 | 2019-03-25 | 2019-03-25 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2020-08-04 | COMP | 2020-08-31 | COMP | Rule 16 | 49 | 47 | 72 | 1 | 275 | 20 | 459
9357 | 2018-11-02 | 2019-01-30 | 2019-05-22 | 2019-05-22 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2021-01-30 | INPR | 2019-12-19 | COMP | Rule 16 | 58 | 80 | 122 | 1 |  |  | 282
9479 | 2018-11-02 | 2019-02-05 | 2019-05-30 | 2019-05-30 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP |  | INPR | 2021-01-22 | COMP | Rule 15/16 | 62 | 81 | 56 | 1 |  |  | 556
9510 | 2018-11-02 | 2019-02-06 | 2019-04-19 | 2019-04-29 | COMP | 2019-04-29 | NOTN | 2019-04-19 | COMP | 2019-04-29 | COMP | 2019-06-01 | COMP | Other | 63 | 52 |  |  | 7 | 24 | 143
9990 | 2018-11-02 | 2019-02-26 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-07-23 | COMP | 2019-09-03 | COMP | Rule 15/16 | 76 | 81 | 7 | 1 | 18 | 30 | 208
10189 | 2018-11-02 | 2019-03-05 | 2019-04-17 | 2019-04-17 | COMP | 2019-06-10 | COMP | 2019-06-14 | COMP | 2019-09-27 | COMP | 2019-10-15 | COMP | Rule 15/16 | 81 | 32 | 38 | 5 | 74 | 13 | 238
10203 | 2018-11-02 | 2019-03-05 | 2019-04-09 | 2019-07-11 | COMP | 2019-07-16 | COMP | 2019-05-22 | COMP | 2019-12-29 | INPR | 2019-08-29 | COMP | Rule 16 | 81 | 26 | 4 |  |  |  | 206
10336 | 2018-11-02 | 2019-03-11 | 2019-04-01 | 2019-04-01 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-09-10 | COMP | 2019-09-11 | COMP | Rule 15/16 | 85 | 16 | 85 | 1 | 30 | 2 | 214
10589 | 2018-11-02 | 2019-03-23 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-06-26 | COMP | 2019-07-15 | COMP | Rule 16 | 94 | 30 | 16 | 1 | 23 | 13 | 173
11366 | 2018-11-02 | 2019-04-24 | 2019-09-10 | 2019-09-10 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-06-02 | COMP | 2020-07-01 | COMP | Rule 16 | 117 | 97 | 105 | 1 | 79 | 22 | 416
13000 | 2018-11-02 | 2019-07-05 | 2019-11-03 | 2019-11-03 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-03-21 | INPR | 2019-01-16 | COMP | Rule 16 | 167 | 85 | 18 | 1 |  |  | 49
14050 | 2018-11-02 | 2019-08-23 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-06 | COMP | 2020-02-21 | COMP | 2020-02-12 | COMP | 2020-06-02 | COMP | Rule 16 | 202 | 59 | 14 | 52 | 0 | 72 | 395
14639 | 2018-11-02 | 2019-09-21 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-02-14 | COMP | 2020-03-20 | COMP | Rule 16 | 221 | 75 | 11 | 1 | 15 | 25 | 344
4181 | 2018-11-03 | 2019-06-05 | 2019-10-04 | 2019-10-04 | COMP | 2019-10-24 | COMP | 2020-03-03 | COMP | 2020-02-21 | COMP | 2020-03-24 | COMP | Other | 145 | 86 | 15 | 87 | 0 | 16 | 345
11333 | 2018-11-03 | 2019-04-24 | 2019-08-16 | 2019-08-16 | COMP | 2019-09-04 | COMP | 2019-10-05 | COMP | 2019-11-20 | COMP | 2020-01-14 | COMP | Rule 16 | 116 | 81 | 13 | 23 | 32 | 36 | 297
13682 | 2018-11-03 | 2019-08-05 | 2019-10-05 | 2019-10-05 | COMP | 2019-11-22 | COMP | 2019-12-02 | COMP | 2019-12-09 | COMP | 2020-01-09 | COMP | Rule 16 | 187 | 44 | 34 | 5 | 6 | 22 | 294
8841 | 2018-11-04 | 2019-01-02 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-04-08 | COMP | 2019-05-24 | COMP | Rule 16 | 38 | 41 | 15 | 1 | 13 | 35 | 138
9227 | 2018-11-04 | 2019-01-23 | 2019-06-20 | 2019-06-20 | COMP | 2019-06-27 | COMP | 2019-10-25 | COMP | 2020-09-08 | COMP | 2020-11-06 | COMP | Rule 16 | 52 | 105 | 6 | 85 | 219 | 44 | 506
10310 | 2018-11-04 | 2019-03-11 | 2019-06-12 | 2021-07-23 | COMP | 2021-08-13 | COMP | 2021-08-13 | COMP | 2023-01-28 | INPR | 2022-01-12 | COMP | Rule 16 | 84 | 67 | 16 | 1 |  |  | 801
10909 | 2018-11-04 | 2019-04-04 | 2019-06-12 | 2019-06-12 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-13 | COMP | 2019-09-20 | COMP | Rule 16 | 102 | 49 | 34 | 1 | 11 | 28 | 220
11754 | 2018-11-04 | 2019-05-09 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-25 | COMP | 2019-09-26 | COMP | 2019-09-27 | COMP | 2019-10-21 | COMP | Rule 16 | 127 | 78 | 20 | 2 | 2 | 17 | 241
4105 | 2018-11-05 | 2019-02-06 | 2019-08-05 | 2019-08-05 | COMP | 2020-04-24 | COMP | 2020-12-29 | COMP |  |  | 2021-02-01 | COMP | Rule 16 | 62 | 126 | 182 | 172 |  |  | 561
7891 | 2018-11-05 | 2018-11-04 | 2019-02-12 | 2019-02-12 | COMP | 2019-04-09 | COMP | 2019-06-11 | COMP | 2019-05-22 | COMP | 2019-07-25 | COMP | Rule 15/16 |  | 66 | 40 | 45 | 0 | 32 | 180
8045 | 2018-11-05 | 2018-11-13 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-17 | NOTN | 2019-08-08 | COMP | 2019-09-05 | COMP | 2019-10-02 | COMP | Rule 16 | 6 | 128 |  | 58 | 20 | 20 | 228
8216 | 2018-11-05 | 2018-11-19 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-08-22 | COMP | Rule 16 | 10 | 75 | 14 | 1 | 1 | 104 | 200
8292 | 2018-11-05 | 2018-11-26 | 2019-01-28 | 2019-01-28 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-02-26 | COMP | 2019-04-29 | COMP | Rule 16 | 13 | 43 | 50 | 1 | 0 | 16 | 119
8374 | 2018-11-05 | 2018-11-28 | 2019-02-21 | 2019-02-21 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-04-28 | COMP | 2019-09-04 | COMP | Rule 16 | 15 | 58 | 43 | 1 | 5 | 90 | 208
8509 | 2018-11-05 | 2018-12-05 | 2019-01-12 | 2019-01-12 | COMP | 2019-02-12 | COMP | 2019-02-12 | COMP | 2019-03-18 | COMP | 2019-04-08 | COMP | Rule 16 | 20 | 26 | 21 | 1 | 24 | 16 | 104
8521 | 2018-11-05 | 2018-12-06 | 2019-01-31 | 2019-10-15 | COMP | 2019-10-24 | COMP | 2019-04-01 | COMP | 2019-10-01 | COMP | 2019-11-05 | COMP | Rule 16 | 21 | 38 | 8 |  | 129 | 26 | 252
8694 | 2018-11-05 | 2018-12-18 | 2019-04-29 | 2019-04-29 | COMP | 2020-02-19 | COMP | 2020-02-27 | COMP | 2020-12-03 | COMP | 2021-02-05 | COMP | Rule 15/16 | 29 | 91 | 203 | 7 | 196 | 44 | 565
8701 | 2018-11-05 | 2018-12-18 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-14 | COMP | 2019-06-28 | COMP | 2021-02-27 | INPR | 2019-10-08 | COMP | Rule 16 | 29 | 79 | 24 | 33 |  |  | 232
8729 | 2018-11-05 | 2018-12-19 | 2019-03-13 | 2019-03-13 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-06-05 | COMP | 2019-07-02 | COMP | Rule 16 | 30 | 57 | 11 | 1 | 50 | 20 | 164
8903 | 2018-11-05 | 2019-01-04 | 2019-03-06 | 2019-03-18 | COMP | 2019-04-24 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-09-12 | COMP | Rule 16 | 40 | 42 | 28 | 73 | 1 | 27 | 214
8938 | 2018-11-05 | 2019-01-08 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-07 | COMP | 2019-06-03 | COMP | Rule 15/16 | 42 | 72 | 11 | 1 | 3 | 19 | 143
8989 | 2018-11-05 | 2019-01-11 | 2019-03-04 | 2019-03-06 | COMP | 2019-03-28 | COMP | 2019-03-29 | COMP | 2019-03-29 | COMP | 2019-04-27 | COMP | Rule 16 | 45 | 35 | 17 | 2 | 1 | 21 | 118
9129 | 2018-11-05 | 2019-01-17 | 2019-02-19 | 2019-02-19 | COMP | 2019-02-26 | COMP | 2019-03-08 | COMP | 2019-04-10 | COMP | 2019-04-11 | COMP | Rule 16 | 49 | 22 | 6 | 9 | 24 | 2 | 107
9168 | 2018-11-05 | 2019-01-18 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-05-01 | COMP | Rule 16 | 50 | 26 | 5 | 1 | 1 | 43 | 121
9436 | 2018-11-05 | 2019-02-05 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-04-10 | COMP | 2019-05-22 | COMP | Rule 16 | 61 | 16 | 20 | 1 | 12 | 31 | 136
9469 | 2018-11-05 | 2019-02-05 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-25 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-09-20 | COMP | Rule 16 | 61 | 35 | 23 | 82 | 1 | 23 | 220
9475 | 2018-11-05 | 2019-02-05 | 2019-08-14 | 2019-08-14 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP |  |  | 2021-05-12 | COMP | Rule 16 | 61 | 134 | 109 | 1 |  |  | 632
9640 | 2018-11-05 | 2019-02-09 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-18 | COMP | 2019-10-30 | COMP | 2019-10-31 | COMP | 2019-11-15 | COMP | Rule 16 | 64 | 11 | 15 | 160 | 2 | 11 | 259
9687 | 2018-11-05 | 2019-02-11 | 2019-04-16 | 2019-04-16 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-10-01 | COMP | 2019-10-02 | COMP | Rule 16 | 65 | 46 | 85 | 1 | 34 | 2 | 228
10067 | 2018-11-05 | 2019-03-01 | 2019-03-22 | 2019-03-22 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-10-25 | COMP | 2019-12-30 | COMP | Rule 16 | 78 | 16 | 123 | 1 | 31 | 43 | 287
10596 | 2018-11-05 | 2019-03-21 | 2019-07-15 | 2019-08-09 | COMP | 2019-08-16 | COMP | 2019-11-25 | COMP | 2019-12-03 | COMP | 2019-12-10 | COMP | Rule 16 | 92 | 81 | 6 | 70 | 5 | 6 | 274
11935 | 2018-11-05 | 2019-05-18 | 2019-09-17 | 2019-09-17 | COMP | 2019-09-23 | COMP | 2019-10-01 | COMP | 2019-10-10 | COMP | 2019-11-07 | COMP | Rule 15/16 | 133 | 84 | 5 | 7 | 8 | 21 | 254
12270 | 2018-11-05 | 2019-05-29 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | 2020-01-30 | COMP | 2020-03-04 | COMP | Rule 16 | 140 | 51 | 25 | 1 | 95 | 24 | 331
12637 | 2018-11-05 | 2019-06-17 | 2019-11-07 | 2020-06-05 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-08-10 | COMP | 2020-09-18 | COMP | Rule 16 | 153 | 102 | 61 | 1 | 0 | 15 | 471
12776 | 2018-11-05 | 2019-06-21 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2021-03-27 | INPR | 2020-03-02 | COMP | Rule 16 | 157 | 24 | 24 | 1 |  |  | 329
13630 | 2018-11-05 | 2019-08-02 | 2019-11-20 | 2019-11-20 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-17 | COMP | 2020-06-28 | COMP | Rule 16 | 186 | 77 | 113 | 1 | 32 | 8 | 412
13915 | 2018-11-05 | 2019-08-16 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-05 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-02-28 | COMP | Rule 16 | 196 | 67 | 10 | 46 | 1 | 13 | 328
3991 | 2018-11-06 | 2018-11-13 | 2019-01-07 | 2019-01-07 | COMP | 2019-01-11 | COMP | 2019-02-05 | COMP | 2019-06-29 | INPR | 2019-03-13 | COMP | Rule 16 | 5 | 36 | 5 | 17 |  |  | 85
4055 | 2018-11-06 | 2019-01-03 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-07 | COMP | 2019-06-03 | COMP | 2019-11-23 | INPR | 2019-07-22 | COMP | Rule 16 | 38 | 60 | 28 | 19 |  |  | 176
4076 | 2018-11-06 | 2019-01-09 | 2020-07-08 | 2020-06-19 | COMP | 2020-09-24 | COMP | 2021-02-03 | COMP | 2021-01-25 | COMP | 2021-02-23 | COMP | Rule 15/16 | 42 | 378 | 69 | 89 | 0 | 14 | 575
7978 | 2018-11-06 | 2018-11-07 | 2018-11-20 | 2018-11-20 | COMP | 2019-05-16 | COMP | 2019-05-21 | COMP | 2019-05-17 | COMP | 2019-06-24 | COMP | Rule 16 | 2 | 9 | 122 | 4 | 0 | 24 | 157
8427 | 2018-11-06 | 2018-12-01 | 2019-02-06 | 2019-02-06 | COMP | 2019-03-01 | COMP | 2019-04-19 | COMP | 2019-04-22 | COMP | 2019-06-07 | COMP | Rule 16 | 16 | 45 | 17 | 36 | 2 | 34 | 146
8437 | 2018-11-06 | 2018-12-03 | 2019-02-23 | 2019-02-23 | COMP | 2019-05-06 | COMP | 2019-08-06 | COMP |  | INPR | 2020-06-17 | COMP | Rule 16 | 17 | 56 | 51 | 65 |  |  | 404
8473 | 2018-11-06 | 2018-12-04 | 2019-01-24 | 2019-01-24 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-06-25 | COMP | 2019-08-09 | COMP | Rule 16 | 18 | 35 | 38 | 1 | 70 | 33 | 190
8579 | 2018-11-06 | 2018-12-11 | 2019-04-03 | 2019-12-24 | COMP | 2020-01-22 | COMP | 2019-10-16 | COMP | 2020-02-25 | COMP | 2020-03-09 | COMP | Rule 16 | 23 | 78 | 19 |  | 88 | 10 | 333
8597 | 2018-11-06 | 2018-12-11 | 2019-04-20 | 2019-04-29 | COMP | 2019-05-14 | COMP | 2019-06-05 | COMP | 2019-10-21 | INPR | 2019-06-17 | COMP | Rule 16 | 23 | 90 | 12 | 16 |  |  | 152
8850 | 2018-11-06 | 2019-01-03 | 2019-02-15 | 2019-02-15 | COMP | 2019-02-20 | NOTN | 2019-03-25 | COMP | 2019-03-22 | NOTN | 2019-04-30 | COMP | Other | 38 | 31 |  | 26 |  |  | 119
8919 | 2018-11-06 | 2019-01-06 | 2019-02-06 | 2019-02-06 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-06-21 | COMP | 2019-07-17 | COMP | Rule 16 | 39 | 22 | 64 | 1 | 33 | 18 | 173
9091 | 2018-11-06 | 2019-01-16 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-11 | COMP | 2019-07-23 | COMP | 2019-07-22 | COMP | 2019-09-03 | COMP | Rule 16 | 47 | 52 | 9 | 72 | 0 | 30 | 206
9278 | 2018-11-06 | 2019-01-27 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-20 | COMP | Rule 16 | 53 | 55 | 14 | 1 | 1 | 13 | 133
9530 | 2018-11-06 | 2019-02-06 | 2019-06-04 | 2019-06-04 | COMP | 2019-07-08 | COMP | 2020-01-09 | COMP | 2020-01-21 | COMP | 2020-02-24 | COMP | Rule 16 | 61 | 83 | 24 | 128 | 8 | 24 | 323
9552 | 2018-11-06 | 2019-02-07 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-20 | COMP | 2019-09-19 | COMP | 2019-08-20 | COMP | 2019-10-04 | COMP | Rule 16 | 62 | 48 | 25 | 86 | 0 | 12 | 229
9588 | 2018-11-06 | 2019-02-07 | 2019-03-19 | 2019-03-19 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-10-10 | COMP | 2019-11-06 | COMP | Rule 16 | 62 | 28 | 51 | 1 | 95 | 20 | 252
9609 | 2018-11-06 | 2019-02-08 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-30 | COMP | 2019-05-08 | COMP | 2019-06-26 | COMP | 2019-08-26 | COMP | Rule 16 | 63 | 31 | 27 | 7 | 35 | 43 | 201
9637 | 2018-11-06 | 2019-02-09 | 2019-05-20 | 2019-05-20 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-07-28 | COMP | 2020-10-13 | COMP | Rule 15/16 | 63 | 70 | 267 | 1 | 35 | 55 | 487
9702 | 2018-11-06 | 2019-02-12 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-08 | COMP | 2020-09-23 | COMP | 2021-02-22 | COMP | 2021-03-18 | COMP | Rule 16 | 65 | 291 | 23 | 97 | 102 | 19 | 592
9705 | 2018-11-06 | 2019-02-12 | 2019-12-07 | 2019-12-07 | COMP | 2020-02-14 | COMP | 2020-08-17 | COMP | 2020-08-24 | COMP | 2021-06-07 | COMP | Rule 15/16 | 65 | 207 | 47 | 130 | 6 | 197 | 648
9718 | 2018-11-06 | 2019-02-12 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-09 | COMP | 2019-05-14 | COMP | 2019-06-17 | COMP | 2019-07-08 | COMP | Rule 16 | 65 | 43 | 19 | 4 | 24 | 15 | 166
9757 | 2018-11-06 | 2019-02-13 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | Rule 15/16 | 66 | 42 | 29 | 1 | 47 | 1 | 182
10284 | 2018-11-06 | 2019-03-08 | 2019-05-21 | 2019-05-21 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-09-16 | COMP | 2019-09-30 | COMP | Rule 16 | 82 | 53 | 48 | 1 | 35 | 11 | 225
10295 | 2018-11-06 | 2019-03-09 | 2019-05-02 | 2019-07-27 | COMP | 2019-08-12 | COMP | 2019-08-20 | COMP | 2019-10-25 | COMP | 2019-12-13 | COMP | Rule 16 | 82 | 39 | 11 | 7 | 48 | 33 | 276
10383 | 2018-11-06 | 2019-03-13 | 2019-04-10 | 2019-04-10 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-12-29 | INPR | 2019-09-08 | COMP | Rule 16 | 85 | 21 | 63 | 1 |  |  | 209
13334 | 2018-11-06 | 2019-07-23 | 2019-10-21 | 2019-10-21 | COMP | 2019-11-01 | COMP | 2019-12-10 | COMP | 2020-01-14 | COMP | 2020-01-21 | COMP | Rule 16 | 177 | 64 | 10 | 25 | 24 | 5 | 300
8472 | 2018-11-07 | 2018-12-04 | 2019-03-22 | 2019-03-22 | COMP | 2019-06-19 | COMP | 2019-06-19 | NOTN | 2019-06-20 | COMP | 2019-07-02 | COMP | Rule 16 | 17 | 75 | 63 |  |  |  | 162
8545 | 2018-11-07 | 2018-12-08 | 2019-01-31 | 2019-01-31 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-12-28 | INPR | 2019-08-28 | COMP | Rule 16 | 20 | 36 | 67 | 1 |  |  | 202
8561 | 2018-11-07 | 2018-12-10 | 2019-04-03 | 2019-04-03 | COMP | 2020-04-28 | COMP | 2019-07-01 | COMP | 2023-05-27 | INPR | 2020-06-01 | COMP | Rule 15/16 | 21 | 79 | 270 |  |  |  | 391
8828 | 2018-11-07 | 2019-01-02 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-18 | COMP | 2019-05-15 | COMP | 2019-08-20 | COMP | 2019-08-19 | COMP | Rule 16 | 36 | 39 | 37 | 20 | 68 |  | 195
8984 | 2018-11-07 | 2019-01-11 | [7 empty] | 2019-01-12 | COMP | 2019-01-28 | COMP | Unknown | 43 | [5 empty] | 53
9041 | 2018-11-07 | 2019-01-15 | 2019-02-13 | 2019-02-20 | COMP | 2019-05-02 | COMP | 2019-05-03 | COMP | 2020-05-13 | COMP | 2020-11-04 | COMP | Rule 16 | 45 | 21 | 52 | 2 | 259 | 124 | 502
9130 | 2018-11-07 | 2019-01-17 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-04-19 | COMP | 2019-08-02 | COMP | Rule 16 | 47 | 49 | 9 | 1 | 9 | 74 | 184
9166 | 2018-11-07 | 2019-01-18 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-22 | COMP | 2019-07-19 | COMP | 2019-07-29 | COMP | 2019-08-14 | COMP | Rule 16 | 48 | 32 | 34 | 63 | 7 | 13 | 192
9229 | 2018-11-07 | 2019-01-23 | 2019-11-16 | 2019-11-16 | COMP | 2019-11-20 | COMP | 2020-01-02 | COMP | 2019-11-20 | COMP | 2020-01-28 | COMP | Rule 16 | 50 | 208 | 3 | 28 | 0 | 18 | 304
9328 | 2018-11-07 | 2019-01-30 | 2019-05-29 | 2019-05-29 | COMP | 2019-09-19 | COMP | 2019-10-07 | COMP | 2020-02-04 | COMP | 2020-02-24 | COMP | Rule 16 | 55 | 84 | 80 | 13 | 81 | 14 | 322
9464 | 2018-11-07 | 2019-02-05 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-08 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-07-22 | COMP | Other | 59 | 38 | 29 | 21 | 1 | 32 | 175
9618 | 2018-11-07 | 2019-02-08 | 2019-04-06 | 2019-04-06 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-08-06 | COMP | 2019-08-08 | COMP | Rule 16 | 62 | 40 | 45 | 1 | 41 | 3 | 188
9774 | 2018-11-07 | 2019-02-15 | 2019-03-10 | 2019-03-10 | COMP | 2019-03-26 | COMP | 2019-04-09 | NOTN | 2019-04-09 | COMP | 2019-07-24 | COMP | Rule 15/16 | 67 | 15 | 12 |  |  |  | 177
10163 | 2018-11-07 | 2019-03-05 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2020-10-24 | INPR | 2019-09-14 | COMP | Rule 16 | 78 | 31 | 28 | 1 |  |  | 213
10245 | 2018-11-07 | 2019-03-07 | 2019-05-21 | 2019-05-21 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2020-09-09 | COMP | 2020-11-02 | COMP | Rule 15/16 | 80 | 54 | 10 | 1 | 321 | 39 | 500
10551 | 2018-11-07 | 2019-03-20 | 2019-06-28 | 2022-08-02 | COMP | 2022-10-03 | COMP | 2022-10-03 | COMP | 2023-03-02 | COMP | 2023-05-01 | COMP | Rule 15/16 | 89 | 72 | 44 | 1 | 102 | 43 | 1124
10581 | 2018-11-07 | 2019-03-21 | 2019-04-01 | 2019-04-03 | COMP | 2019-05-28 | COMP | 2020-02-11 | COMP | 2019-12-09 | COMP | 2020-03-04 | COMP | Rule 15/16 | 90 | 8 | 39 | 178 | 0 | 16 | 329
10639 | 2018-11-07 | 2019-03-23 | 2019-06-25 | 2019-06-25 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2020-04-29 | COMP | 2020-05-06 | COMP | Rule 16 | 91 | 66 | 59 | 1 | 155 | 6 | 374
10652 | 2018-11-07 | 2019-03-25 | 2019-06-04 | 2019-06-04 | COMP | 2019-07-08 | COMP | 2019-08-26 | COMP | 2019-09-10 | COMP | 2019-10-03 | COMP | Rule 15/16 | 92 | 51 | 24 | 36 | 11 | 18 | 227
11139 | 2018-11-07 | 2019-04-15 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-09-09 | COMP | 2019-09-05 | COMP | Rule 15/16 | 107 | 54 | 16 | 1 | 34 |  | 207
11323 | 2018-11-07 | 2019-04-23 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-15 | COMP | 2020-04-20 | COMP | 2020-01-30 | COMP | 2020-07-17 | COMP | Rule 15/16 | 113 | 113 | 11 | 128 | 0 | 64 | 425
11622 | 2018-11-07 | 2019-05-06 | 2019-07-23 | 2020-03-24 | COMP | 2020-04-02 | COMP | 2019-08-29 | COMP | 2020-01-16 | COMP | 2020-05-27 | COMP | Rule 16 | 122 | 55 | 8 |  | 95 | 92 | 388
11645 | 2018-11-07 | 2019-05-06 | 2019-06-11 | 2019-06-11 | COMP | 2019-10-08 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-12-13 | COMP | Rule 16 | 122 | 26 | 84 | 26 | 1 | 21 | 275
11923 | 2018-11-07 | 2019-05-17 | 2019-10-10 | 2019-10-10 | COMP | 2019-11-04 | COMP | 2020-07-23 | COMP | 2020-08-17 | COMP | 2020-09-03 | COMP | Rule 16 | 131 | 102 | 18 | 181 | 18 | 14 | 459
12437 | 2018-11-07 | 2019-06-06 | 2020-04-01 | 2020-04-01 | COMP | 2020-11-18 | COMP | 2021-01-14 | COMP | 2021-03-01 | COMP | 2021-03-04 | COMP | Rule 15/16 | 144 | 206 | 163 | 38 | 31 | 4 | 581
12822 | 2018-11-07 | 2019-06-24 | 2019-10-10 | 2019-10-10 | COMP | 2019-11-13 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-04-17 | COMP | Rule 16 | 156 | 77 | 24 | 80 | 1 | 28 | 361
13729 | 2018-11-07 | 2019-08-07 | 2019-12-13 | 2019-12-13 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-03-16 | COMP | 2020-06-23 | COMP | Rule 15/16 | 187 | 89 | 70 | 1 | 0 | 64 | 407
14297 | 2018-11-07 | 2019-09-03 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-26 | COMP | 2020-02-12 | COMP | Rule 16 | 205 | 34 | 12 | 1 | 15 | 52 | 315
14457 | 2018-11-07 | 2019-09-11 | 2019-12-09 | 2019-12-09 | COMP | 2019-12-30 | COMP | 2020-01-10 | COMP | 2022-05-31 | COMP | 2022-06-17 | COMP | Rule 16 | 211 | 61 | 15 | 9 | 603 | 14 | 908
17376 | 2018-11-07 | 2020-02-12 | 2020-03-24 | 2020-03-24 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-10-16 | COMP | 2020-11-30 | COMP | Rule 16 | 315 | 29 | 16 | 1 | 132 | 29 | 517
26371 | 2018-11-07 | 2021-03-18 | 2022-01-07 | 2022-01-07 | COMP | 2022-03-09 | COMP | 2022-05-30 | COMP | 2023-03-27 | COMP | 2023-07-21 | COMP | Rule 15 | 591 | 206 | 42 | 58 | 205 | 82 | 1180
4077 | 2018-11-08 | 2019-01-10 | 2019-02-09 | 2019-02-09 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-06-11 | COMP | 2019-07-26 | COMP | Rule 15/16 | 41 | 21 | 16 | 1 | 70 | 33 | 178
8317 | 2018-11-08 | 2018-11-27 | 2019-04-17 | 2019-04-17 | COMP | 2019-09-09 | COMP | 2019-09-10 | COMP | 2019-11-01 | COMP | 2019-12-04 | COMP | Rule 15/16 | 11 | 98 | 101 | 2 | 39 | 21 | 267
8380 | 2018-11-08 | 2018-11-28 | 2019-05-01 | 2019-05-03 | COMP | 2019-05-02 | NOTN | 2019-08-05 | COMP | 2019-08-28 | COMP | 2019-10-23 | COMP | Other | 12 | 107 |  | 65 | 18 | 40 | 240
8504 | 2018-11-08 | 2018-12-05 | 2019-01-19 | 2019-01-19 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2020-02-18 | COMP | 2020-04-10 | COMP | Rule 16 | 17 | 31 | 227 | 1 | 44 | 39 | 355
8527 | 2018-11-08 | 2018-12-08 | 2019-03-14 | 2019-03-14 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2019-06-13 | COMP | 2019-07-31 | COMP | Rule 16 | 19 | 65 | 61 | 1 | 5 | 34 | 181
8550 | 2018-11-08 | 2018-12-08 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-10-21 | INPR | 2019-06-10 | COMP | Rule 15/16 | 19 | 68 | 27 | 1 |  |  | 145
8671 | 2018-11-08 | 2018-12-14 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-04-23 | COMP | 2019-07-11 | COMP | Rule 16 | 24 | 50 | 34 | 1 | 7 | 56 | 167
8674 | 2018-11-08 | 2018-12-15 | 2019-04-02 | 2019-04-02 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2021-02-18 | COMP | 2021-03-11 | COMP | Rule 16 | 24 | 73 | 413 | 1 | 62 | 16 | 585
9136 | 2018-11-08 | 2019-01-17 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-04-26 | COMP | 2019-05-15 | COMP | Rule 16 | 46 | 33 | 4 | 1 | 35 | 14 | 128
9346 | 2018-11-08 | 2019-01-30 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-07-25 | COMP | Rule 16 | 54 | 57 | 16 | 1 | 1 | 52 | 177
9366 | 2018-11-08 | 2019-01-31 | 2019-08-01 | 2019-08-01 | COMP | 2019-12-09 | COMP | 2020-03-17 | COMP | 2020-03-02 | COMP | 2020-07-25 | COMP | Rule 15/16 | 55 | 128 | 89 | 68 | 0 | 93 | 429
9368 | 2018-11-08 | 2019-01-31 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-25 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-05-28 | COMP | Rule 16 | 55 | 51 | 10 | 4 | 1 | 20 | 136
9659 | 2018-11-08 | 2019-02-11 | 2019-03-08 | 2019-03-08 | COMP | 2019-04-12 | COMP | 2019-04-12 | COMP | 2019-10-21 | INPR | 2019-06-27 | COMP | Rule 15/16 | 62 | 19 | 26 | 1 |  |  | 158
9693 | 2018-11-08 | 2019-02-11 | 2019-09-09 | 2019-09-09 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP |  |  | 2020-01-21 | COMP | Rule 16 | 62 | 147 | 57 | 1 |  |  | 298
9925 | 2018-11-08 | 2019-02-22 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-07 | COMP | 2019-05-23 | COMP | 2019-06-06 | COMP | 2019-06-19 | COMP | Rule 15/16 | 70 | 46 | 8 | 13 | 10 | 10 | 152
10080 | 2018-11-08 | 2019-03-01 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-23 | COMP | 2019-07-30 | COMP | 2019-11-26 | COMP | 2020-01-07 | COMP | Rule 16 | 75 | 97 | 5 | 6 | 84 | 27 | 289
10463 | 2018-11-08 | 2019-03-18 | 2019-07-12 | 2019-07-12 | COMP | 2019-09-04 | COMP | 2019-09-23 | COMP | 2020-05-04 | COMP | 2020-07-26 | COMP | Rule 16 | 86 | 83 | 38 | 14 | 154 | 59 | 429
10664 | 2018-11-08 | 2019-03-25 | 2019-07-13 | 2019-07-13 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP |  | INPR | 2022-05-24 | COMP | Other | 91 | 78 | 69 | 1 |  |  | 890
10727 | 2018-11-08 | 2019-03-28 | 2019-08-01 | 2019-08-01 | COMP | 2020-07-10 | COMP | 2020-07-20 | COMP | 2020-06-29 | COMP | 2020-09-04 | COMP | Rule 16 | 94 | 89 | 238 | 7 | 0 | 35 | 459
10880 | 2018-11-08 | 2019-04-02 | 2019-07-04 | 2019-08-20 | COMP | 2019-08-21 | COMP | 2019-07-22 | COMP | 2019-07-23 | COMP | 2019-10-18 | COMP | Rule 16 | 97 | 66 | 2 |  | 2 | 63 | 237
11148 | 2018-11-08 | 2019-04-15 | 2019-08-09 | 2019-08-09 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2023-12-03 | INPR | 2020-04-27 | COMP | Rule 16 | 106 | 83 | 66 | 1 |  |  | 366
11274 | 2018-11-08 | 2019-04-22 | 2019-05-31 | 2019-05-31 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-08-29 | COMP | 2019-10-11 | COMP | Rule 16 | 111 | 29 | 31 | 1 | 34 | 31 | 232
11691 | 2018-11-08 | 2019-05-07 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-11-20 | COMP | 2019-12-04 | COMP | Rule 16 | 122 | 39 | 7 | 1 | 94 | 9 | 267
11729 | 2018-11-08 | 2019-05-08 | 2019-10-07 | 2019-10-07 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2021-02-04 | COMP | 2021-03-05 | COMP | Rule 15/16 | 123 | 106 | 31 | 1 | 304 | 21 | 581
11767 | 2018-11-08 | 2019-05-10 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-07-08 | COMP | 2019-07-09 | COMP | Rule 16 | 125 | 29 | 9 | 1 | 4 | 2 | 165
12107 | 2018-11-08 | 2019-05-23 | 2019-06-19 | 2019-06-19 | COMP | 2019-10-16 | COMP | 2019-10-28 | COMP | 2021-02-27 | INPR | 2019-11-18 | COMP | Rule 16 | 134 | 19 | 84 | 9 |  |  | 257
12228 | 2018-11-08 | 2019-05-28 | 2019-07-29 | 2019-07-29 | COMP | 2020-06-08 | COMP | 2020-11-14 | COMP | 2020-12-17 | COMP | 2021-02-10 | COMP | Rule 16 | 136 | 44 | 217 | 113 | 22 | 37 | 565
12917 | 2018-11-08 | 2019-06-29 | 2019-08-13 | 2019-08-13 | COMP | 2019-11-18 | COMP | 2020-10-07 | COMP | 2019-11-18 | COMP | 2020-12-15 | COMP | Rule 15/16 | 159 | 31 | 68 | 225 | 0 | 47 | 527
13049 | 2018-11-08 | 2019-07-08 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-03 | COMP | 2020-02-05 | COMP | 2020-07-27 | COMP | 2020-10-01 | COMP | Rule 16 | 164 | 132 | 13 | 3 | 122 | 48 | 477
13702 | 2018-11-08 | 2019-08-06 | 2019-10-31 | 2019-10-31 | COMP | 2019-12-13 | COMP | 2020-01-13 | COMP | 2020-02-11 | COMP | 2020-03-18 | COMP | Rule 15/16 | 185 | 62 | 29 | 20 | 21 | 26 | 338
14178 | 2018-11-08 | 2019-08-28 | 2019-12-09 | 2019-12-09 | COMP | 2019-12-12 | COMP | 2020-02-04 | COMP | 2020-05-19 | COMP | 2020-06-08 | COMP | Rule 16 | 201 | 70 | 4 | 36 | 75 | 14 | 395
15075 | 2018-11-08 | 2019-10-11 | 2020-06-13 | 2020-06-13 | COMP | 2020-06-16 | NOTN | 2021-04-22 | COMP | 2021-05-18 | COMP | 2021-05-26 | COMP | Other | 232 | 168 |  | 216 | 19 | 7 | 639
15205 | 2018-11-08 | 2019-10-19 | 2020-05-01 | 2020-05-01 | COMP | 2020-05-08 | COMP | 2020-06-18 | COMP | 2022-05-11 | COMP | 2022-05-31 | COMP | Rule 16 | 237 | 133 | 6 | 29 | 479 | 14 | 894
19166 | 2018-11-08 | 2020-04-22 | 2020-06-02 | 2020-06-02 | COMP | 2021-02-10 | COMP | 2021-02-17 | COMP | 2021-02-04 | COMP | 2021-03-05 | COMP | Other | 363 | 29 | 175 | 5 | 0 | 13 | 581
20873 | 2018-11-08 | 2020-07-10 | 2020-08-04 | 2020-08-04 | COMP | 2020-09-04 | COMP | 2020-09-24 | COMP | 2020-11-30 | COMP | 2021-01-06 | COMP | Rule 15/16 | 419 | 18 | 24 | 14 | 45 | 26 | 541
8294 | 2018-11-09 | 2018-11-26 | 2019-03-25 | 2019-09-17 | COMP | 2019-10-03 | NOTN | 2019-10-24 | COMP | 2019-09-18 | COMP | 2019-11-22 | COMP | Other | 9 | 82 |  | 28 | 0 | 21 | 260
8299 | 2018-11-09 | 2018-11-26 | 2019-01-28 | 2019-01-28 | COMP | 2019-01-30 | NOTN | 2019-01-30 | COMP | 2019-01-30 | COMP | 2019-03-05 | COMP | Other | 9 | 43 |  | 3 | 1 | 24 | 76
8670 | 2018-11-09 | 2018-12-14 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-07-15 | COMP | 2019-09-18 | COMP | Rule 16 | 23 | 41 | 37 | 1 | 70 | 47 | 214
8934 | 2018-11-09 | 2019-01-08 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-16 | NOTN | 2019-04-30 | COMP | 2019-04-16 | COMP | 2019-06-13 | COMP | Other | 38 | 66 |  | 14 | 0 | 32 | 147
8987 | 2018-11-09 | 2019-01-11 | 2019-04-02 | 2019-04-02 | COMP | 2019-05-10 | COMP | 2019-07-15 | COMP | 2023-04-30 | INPR | 2019-08-12 | COMP | Rule 16 | 41 | 56 | 29 | 45 |  |  | 188
9242 | 2018-11-09 | 2019-01-24 | 2019-08-09 | 2019-08-09 | COMP | 2019-10-23 | COMP | 2019-11-25 | COMP | 2020-03-23 | COMP | 2020-04-27 | COMP | Rule 15/16 | 49 | 139 | 53 | 23 | 80 | 26 | 365
9487 | 2018-11-09 | 2019-02-06 | 2019-06-03 | 2019-06-03 | COMP | 2019-07-08 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-08-29 | COMP | Rule 16 | 58 | 82 | 25 | 33 | 1 | 7 | 201
9513 | 2018-11-09 | 2019-02-06 | 2019-04-05 | 2019-04-05 | COMP | 2019-06-19 | COMP | 2019-09-13 | COMP | 2019-08-29 | COMP | 2020-07-23 | COMP | Rule 15/16 | 58 | 42 | 53 | 61 | 0 | 217 | 427
9752 | 2018-11-09 | 2019-02-13 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-30 | COMP | 2019-08-19 | COMP | 2019-08-30 | COMP | 2019-09-19 | COMP | Rule 16 | 63 | 96 | 21 | 15 | 10 | 14 | 215
9839 | 2018-11-09 | 2019-02-20 | 2019-04-20 | 2019-04-20 | COMP | 2019-04-22 | NOTN | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-05-15 | COMP | Other | 67 | 43 |  | 1 | 1 | 18 | 127
10026 | 2018-11-09 | 2019-02-27 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-14 | COMP | 2019-12-10 | COMP | 2019-12-11 | COMP | 2019-12-31 | COMP | Rule 16 | 72 | 56 | 22 | 123 | 2 | 14 | 284
10090 | 2018-11-09 | 2019-03-01 | 2019-07-29 | 2019-07-29 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2020-04-26 | INPR | 2020-01-07 | COMP | Rule 15/16 | 74 | 105 | 13 | 1 |  |  | 288
10372 | 2018-11-09 | 2019-03-13 | 2019-07-23 | 2020-05-05 | COMP | 2020-05-27 | COMP | 2020-09-09 | COMP | 2020-08-12 | COMP | 2020-11-18 | COMP | Rule 16 | 82 | 93 | 16 | 75 | 0 | 50 | 509
10442 | 2018-11-09 | 2019-03-16 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2020-05-15 | COMP | 2020-06-23 | COMP | Rule 16 | 84 | 52 | 44 | 1 | 201 | 27 | 405
11062 | 2018-11-09 | 2019-04-10 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-10 | COMP | 2019-05-10 | INPR | 2019-09-22 | REQD | 2019-05-30 | COMP | Rule 16 | 102 | 8 | 16 |  |  |  | 137
11255 | 2018-11-09 | 2019-04-19 | 2019-07-30 | 2019-07-30 | COMP | 2020-07-28 | COMP | 2020-07-13 | COMP | 2021-06-02 | COMP | 2021-07-02 | COMP | Rule 16 | 109 | 71 | 252 |  | 224 | 23 | 664
11461 | 2018-11-09 | 2019-04-29 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-10 | COMP | 2019-08-14 | COMP | 2019-08-16 | COMP | 2020-06-22 | COMP | Rule 16 | 115 | 43 | 9 | 26 | 3 | 213 | 404
12005 | 2018-11-09 | 2019-05-20 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-09-06 | COMP | 2019-10-01 | COMP | Rule 15/16 | 130 | 56 | 5 | 1 | 18 | 18 | 223
12884 | 2018-11-09 | 2019-06-26 | 2020-09-22 | 2020-09-22 | COMP | 2020-12-18 | COMP | 2021-03-31 | COMP | 2021-04-26 | COMP | 2021-06-25 | COMP | Rule 15/16 | 156 | 314 | 61 | 70 | 19 | 44 | 659
13117 | 2018-11-09 | 2019-07-12 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-11 | COMP | 2019-10-02 | COMP | 2019-10-11 | COMP | 2019-10-14 | COMP | Rule 16 | 167 | 25 | 19 | 16 | 8 | 2 | 232
13521 | 2018-11-09 | 2019-07-29 | 2019-09-09 | 2019-09-09 | COMP | 2019-12-06 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2021-06-24 | COMP | Rule 16 | 178 | 30 | 62 | 8 | 1 | 384 | 658
13988 | 2018-11-09 | 2019-08-20 | 2020-01-21 | 2020-01-21 | COMP | 2020-01-31 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-05-19 | COMP | Rule 16 | 194 | 104 | 9 | 27 | 1 | 51 | 381
15620 | 2018-11-09 | 2019-11-12 | 2020-01-22 | 2020-01-22 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-07-15 | COMP | 2020-07-18 | COMP | Rule 16 | 252 | 47 | 63 | 1 | 62 | 3 | 423
15644 | 2018-11-09 | 2019-11-13 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-13 | COMP | 2020-10-07 | COMP | 2020-11-13 | COMP | 2020-12-14 | COMP | Rule 16 | 253 | 68 | 15 | 147 | 27 | 20 | 525
8246 | 2018-11-10 | 2018-11-21 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-26 | COMP | 2020-01-29 | COMP | 2020-08-20 | COMP | 2020-11-03 | COMP | Rule 15/16 | 7 | 205 | 9 | 84 | 145 | 53 | 498
8491 | 2018-11-10 | 2018-12-04 | 2018-12-19 | 2019-04-22 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-03-22 | COMP | 2019-05-06 | COMP | Rule 16 | 14 | 12 | 3 | 1 | 0 | 9 | 119
9314 | 2018-11-10 | 2019-01-30 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-15 | COMP | 2019-05-16 | COMP | 2019-11-25 | COMP | 2020-01-30 | COMP | Rule 16 | 52 | 48 | 28 | 2 | 134 | 44 | 303
9501 | 2018-11-10 | 2019-02-06 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-11 | NOTN | 2019-06-28 | COMP | 2019-07-16 | COMP | 2019-08-09 | COMP | Other | 57 | 45 |  | 57 | 12 | 19 | 186
12434 | 2018-11-10 | 2019-06-06 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-05 | COMP | 2020-07-24 | COMP | 2021-06-23 | COMP | 2021-08-11 | COMP | Rule 16 | 141 | 242 | 11 | 36 | 230 | 35 | 690
8606 | 2018-11-12 | 2018-12-11 | 2019-07-10 | 2019-07-17 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-09-18 | COMP | 2020-01-13 | COMP | Rule 16 | 19 | 146 | 36 | 1 | 10 | 79 | 291
9716 | 2018-11-12 | 2019-02-12 | 2019-03-30 | 2019-07-15 | COMP | 2019-08-08 | COMP | 2019-08-15 | COMP | 2019-09-14 | COMP | 2019-12-03 | COMP | Rule 16 | 61 | 33 | 19 | 6 | 21 | 54 | 264
10593 | 2018-11-12 | 2019-03-21 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-06-05 | COMP | 2019-06-19 | COMP | Rule 16 | 87 | 11 | 37 | 1 | 8 | 11 | 150
10622 | 2018-11-12 | 2019-03-22 | 2019-06-11 | 2019-06-11 | COMP | 2019-06-19 | COMP | 2019-06-19 | INPR | 2019-06-20 | COMP | 2019-07-05 | COMP | Rule 16 | 88 | 57 | 7 |  |  |  | 161
10658 | 2018-11-12 | 2019-03-25 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-17 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-15 | COMP | Rule 16 | 89 | 47 | 35 | 4 | 1 | 19 | 190
12133 | 2018-11-12 | 2019-05-23 | 2020-02-06 | 2020-02-06 | REQD | 2020-02-06 | REQD | 2020-02-06 | REQD | 2020-02-06 | REQD | 2019-09-30 | COMP | Unknown | 132 | [5 empty] | 221
12620 | 2018-11-12 | 2019-06-17 | 2019-08-16 | 2019-08-16 | COMP | 2019-08-29 | COMP | 2019-09-17 | COMP | 2020-06-15 | COMP | 2020-07-10 | COMP | Rule 16 | 148 | 44 | 10 | 13 | 187 | 20 | 417
12673 | 2018-11-12 | 2019-06-19 | 2019-08-27 | 2019-09-07 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | 2019-11-09 | COMP | 2019-11-09 | COMP | Rule 16 | 150 | 49 | 4 | 1 | 42 | 0 | 250
12912 | 2018-11-12 | 2019-06-28 | 2020-02-21 | 2020-02-21 | COMP | 2020-02-28 | COMP | 2021-03-08 | COMP | 2021-06-27 | COMP | 2022-02-23 | COMP | Rule 15/16 | 157 | 162 | 6 | 258 | 79 | 166 | 824
13268 | 2018-11-12 | 2019-07-17 | 2019-11-13 | 2019-11-13 | COMP | 2020-01-27 | COMP | 2020-08-10 | COMP | 2020-08-10 | COMP | 2020-08-26 | COMP | Rule 16 | 169 | 84 | 49 | 139 | 1 | 13 | 450
13450 | 2018-11-12 | 2019-07-26 | 2020-01-14 | 2020-03-10 | COMP | 2020-03-24 | COMP | 2020-12-03 | COMP | 2020-12-04 | COMP | 2020-12-30 | COMP | Rule 15/16 | 176 | 117 | 11 | 178 | 2 | 18 | 535
13917 | 2018-11-12 | 2019-08-16 | 2019-11-12 | 2019-11-12 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-10-14 | COMP | 2020-11-13 | COMP | Rule 16 | 191 | 61 | 7 | 1 | 228 | 22 | 505
4031 | 2018-11-13 | 2018-12-17 | 2019-03-19 | 2019-03-19 | COMP | 2019-05-21 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-07-23 | COMP | Rule 16 | 23 | 63 | 46 | 23 | 1 | 22 | 173
4064 | 2018-11-13 | 2019-01-04 | 2019-12-16 | 2019-12-16 | COMP | 2020-03-27 | NOTN | 2020-03-27 | COMP | 2020-05-05 | NOTN | 2020-06-02 | COMP | Other | 35 | 239 |  | 71 |  |  | 389
8411 | 2018-11-13 | 2018-11-29 | 2018-12-21 | 2019-01-09 | COMP | 2019-01-18 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-05-01 | COMP | Rule 16 | 11 | 17 | 8 | 36 | 1 | 37 | 116
8525 | 2018-11-13 | 2018-12-06 | 2019-03-31 | 2019-06-26 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-09-10 | COMP | 2019-09-18 | COMP | Rule 15/16 | 16 | 78 | 52 | 1 | 2 | 7 | 213
8542 | 2018-11-13 | 2018-12-07 | 2019-06-22 | 2019-06-22 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-04-28 | COMP | 2020-07-10 | COMP | Rule 15/16 | 17 | 136 | 177 | 1 | 37 | 53 | 417
8622 | 2018-11-13 | 2018-12-12 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-09-11 | COMP | 2019-09-23 | COMP | Rule 16 | 20 | 147 | 32 | 1 | 12 | 9 | 216
8679 | 2018-11-13 | 2018-12-15 | 2019-02-23 | 2019-02-23 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-03-12 | COMP | 2019-04-04 | COMP | Rule 16 | 22 | 46 | 11 | 1 | 2 | 18 | 97
8768 | 2018-11-13 | 2018-12-23 | 2019-04-17 | 2019-04-17 | COMP | 2019-08-02 | COMP | 2020-07-14 | COMP | 2020-10-13 | COMP | 2020-12-02 | COMP | Rule 16 | 27 | 79 | 76 | 239 | 65 | 34 | 516
8834 | 2018-11-13 | 2018-12-31 | 2019-03-11 | 2019-04-08 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-06-10 | COMP | 2019-07-26 | COMP | Rule 16 | 32 | 48 | 16 | 1 | 30 | 34 | 176
8846 | 2018-11-13 | 2019-01-02 | 2019-01-23 | 2019-01-23 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-06-10 | COMP | 2019-06-14 | COMP | Rule 16 | 33 | 15 | 65 | 1 | 33 | 5 | 147
8854 | 2018-11-13 | 2019-01-02 | 2019-06-12 | 2019-06-12 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-08-27 | COMP | 2019-09-19 | COMP | Rule 16 | 33 | 113 | 53 | 1 | 2 | 17 | 214
9004 | 2018-11-13 | 2019-01-12 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-22 | COMP | 2019-12-10 | COMP | 2020-04-29 | COMP | 2020-07-14 | COMP | Rule 16 | 40 | 49 | 43 | 139 | 98 | 54 | 419
9110 | 2018-11-13 | 2019-01-17 | 2019-03-19 | 2019-03-25 | COMP | 2019-04-01 | COMP | 2019-04-02 | COMP | 2019-05-07 | COMP | 2019-05-29 | COMP | Rule 16 | 44 | 42 | 6 | 2 | 26 | 16 | 135
9441 | 2018-11-13 | 2019-02-04 | 2019-04-29 | 2019-04-29 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-04-30 | COMP | 2019-07-03 | COMP | Rule 16 | 55 | 60 | 31 | 1 | 0 | 17 | 160
9527 | 2018-11-13 | 2019-02-06 | 2019-02-13 | 2019-02-13 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2021-02-27 | INPR | 2020-02-07 | COMP | Rule 16 | 57 | 6 | 120 | 1 |  |  | 309
9529 | 2018-11-13 | 2019-02-06 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-13 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2020-07-21 | COMP | Rule 16 | 57 | 85 | 6 | 20 | 1 | 260 | 424
9546 | 2018-11-13 | 2019-02-07 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-26 | COMP | 2019-05-06 | COMP | 2019-05-07 | COMP | 2019-05-09 | COMP | Rule 16 | 58 | 33 | 24 | 7 | 2 | 3 | 122
9654 | 2018-11-13 | 2019-02-10 | 2019-03-13 | 2021-01-05 | COMP | 2021-01-11 | COMP | 2021-01-14 | COMP | 2021-01-10 | COMP | 2021-02-13 | COMP | Rule 16 | 59 | 22 | 5 | 4 | 0 | 21 | 565
9946 | 2018-11-13 | 2019-02-25 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2020-03-10 | COMP | 2020-02-28 | COMP | Rule 16 | 69 | 40 | 16 | 1 | 207 |  | 323
10018 | 2018-11-13 | 2019-02-27 | 2019-04-23 | 2019-04-23 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-06-14 | COMP | 2019-07-12 | COMP | Rule 16 | 71 | 40 | 4 | 1 | 35 | 20 | 166
10120 | 2018-11-13 | 2019-03-04 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-20 | COMP | 2019-06-24 | COMP | 2019-06-20 | COMP | 2019-08-27 | COMP | Rule 16 | 74 | 31 | 26 | 25 | 0 | 46 | 198
10300 | 2018-11-13 | 2019-03-11 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-10 | COMP | 2019-04-18 | COMP | 2019-04-22 | COMP | 2019-04-23 | COMP | Rule 16 | 79 | 15 | 8 | 7 | 3 | 2 | 110
10813 | 2018-11-13 | 2019-04-01 | 2019-12-07 | 2022-05-23 | COMP | 2022-06-02 | COMP | 2022-06-09 | COMP | 2022-06-28 | COMP | 2022-06-28 | COMP | Rule 15/16 | 94 | 174 | 8 | 6 | 13 | 1 | 911
10902 | 2018-11-13 | 2019-04-03 | 2019-08-05 | 2019-08-05 | COMP | 2019-10-23 | COMP | 2019-12-18 | COMP | 2020-01-15 | COMP | 2020-02-14 | COMP | Rule 16 | 96 | 87 | 57 | 38 | 19 | 22 | 314
10996 | 2018-11-13 | 2019-04-08 | 2019-05-06 | 2019-05-06 | COMP | 2019-06-05 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2019-07-17 | COMP | Rule 16 | 99 | 21 | 22 | 8 | 1 | 23 | 169
11117 | 2018-11-13 | 2019-04-13 | 2019-09-03 | 2020-02-10 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-05-07 | COMP | 2020-06-20 | COMP | Rule 15/16 | 103 | 99 | 20 | 1 | 44 | 31 | 402
11547 | 2018-11-13 | 2019-05-02 | 2019-08-03 | 2020-07-27 | COMP | 2020-07-31 | COMP | 2020-06-13 | COMP | 2021-10-25 | COMP | 2021-12-01 | COMP | Rule 16 | 117 | 65 | 5 |  | 345 | 25 | 766
11702 | 2018-11-13 | 2019-05-08 | 2019-07-24 | 2019-07-29 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2020-01-07 | COMP | 2020-01-11 | COMP | Unknown | 121 | 54 | 69 | 1 | 43 | 4 | 290
11924 | 2018-11-13 | 2019-05-16 | 2019-10-01 | 2019-10-01 | COMP | 2020-02-21 | COMP | 2020-03-09 | COMP | 2022-07-30 | INPR | 2020-04-02 | COMP | Rule 16 | 127 | 96 | 97 | 12 |  |  | 347
12009 | 2018-11-13 | 2019-05-20 | 2019-09-01 | 2019-09-01 | COMP | 2019-09-16 | COMP | 2020-01-31 | COMP | 2020-11-23 | COMP | 2021-01-29 | COMP | Rule 16 | 129 | 73 | 10 | 94 | 208 | 45 | 555
12029 | 2018-11-13 | 2019-05-21 | 2019-10-07 | 2019-10-07 | COMP | 2020-02-14 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-03-06 | COMP | Rule 16 | 130 | 97 | 89 | 2 | 1 | 14 | 328
12285 | 2018-11-13 | 2019-05-31 | 2019-10-25 | 2019-10-25 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-06-10 | COMP | 2020-08-13 | COMP | Rule 16 | 137 | 104 | 70 | 1 | 87 | 47 | 441
12681 | 2018-11-13 | 2019-06-18 | 2019-09-07 | 2019-09-07 | COMP | 2019-09-13 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-10-21 | COMP | Rule 16 | 149 | 57 | 5 | 7 | 1 | 21 | 236
12691 | 2018-11-13 | 2019-06-18 | 2019-08-07 | 2019-08-20 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2020-01-14 | COMP | 2020-01-16 | COMP | Rule 15/16 | 149 | 36 | 12 | 1 | 89 | 3 | 294
14044 | 2018-11-13 | 2019-08-22 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-02-08 | COMP | 2020-02-25 | COMP | Rule 16 | 195 | 60 | 23 | 1 | 34 | 11 | 320
14290 | 2018-11-13 | 2019-09-03 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | 2020-05-31 | INPR | 2020-02-15 | COMP | Rule 16 | 202 | 86 | 13 | 1 |  |  | 314
17921 | 2018-11-13 | 2020-03-05 | 2020-10-02 | 2021-03-03 | COMP | 2021-05-18 | COMP | 2021-05-20 | COMP | 2023-06-07 | COMP | 2023-08-09 | COMP | Rule 16 | 327 | 150 | 55 | 3 | 515 | 44 | 1190
19897 | 2018-11-13 | 2020-05-27 | 2021-03-24 | 2021-03-24 | COMP | 2022-04-15 | COMP | 2022-08-15 | COMP | 2022-11-28 | COMP | 2022-12-08 | COMP | Rule 16 | 385 | 208 | 270 | 84 | 72 | 9 | 1023
4056 | 2018-11-14 | 2019-01-03 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-05 | NOTN | 2019-12-10 | COMP | 2019-08-22 | COMP | 2020-06-09 | COMP | Other | 33 | 149 |  | 88 | 0 | 126 | 393
8131 | 2018-11-14 | 2018-11-16 | 2019-02-12 | 2019-02-12 | COMP | 2019-06-12 | COMP | 2019-06-12 | INPR | 2019-10-21 | REQD | 2019-06-11 | COMP | Rule 16 | 3 | 58 | 85 |  |  |  | 143
8319 | 2018-11-14 | 2018-11-27 | 2019-03-27 | 2019-03-27 | COMP | 2019-10-29 | COMP | 2019-09-10 | COMP | 2019-11-16 | COMP | 2019-11-23 | COMP | Rule 15/16 | 8 | 83 | 152 |  | 48 | 5 | 258
8481 | 2018-11-14 | 2018-12-04 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-25 | COMP | 2019-02-25 | COMP | 2019-06-10 | COMP | 2019-07-25 | COMP | Rule 16 | 13 | 49 | 8 | 1 | 75 | 33 | 174
8510 | 2018-11-14 | 2018-12-05 | 2019-02-15 | 2019-02-15 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-08-23 | COMP | 2019-09-21 | COMP | Rule 15/16 | 14 | 50 | 43 | 1 | 91 | 20 | 214
8886 | 2018-11-14 | 2019-01-03 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-08 | COMP | 2019-03-01 | COMP | 2019-10-21 | INPR | 2019-04-03 | COMP | Rule 16 | 33 | 12 | 15 | 15 |  |  | 95
9015 | 2018-11-14 | 2019-01-12 | 2019-02-08 | 2019-02-08 | COMP | 2019-02-13 | COMP | 2019-02-22 | COMP | 2019-02-13 | COMP | 2019-02-21 | COMP | Rule 16 | 39 | 19 | 4 | 7 | 0 |  | 66
9040 | 2018-11-14 | 2019-01-14 | 2019-03-06 | 2019-03-06 | COMP | 2019-06-06 | COMP | 2019-06-06 | INPR | 2019-07-15 | COMP | 2019-07-29 | COMP | Rule 16 | 40 | 36 | 66 |  |  |  | 176
10057 | 2018-11-14 | 2019-02-28 | 2020-03-11 | 2020-03-11 | COMP | 2020-05-14 | COMP | 2020-06-20 | COMP | 2020-10-06 | COMP | 2020-11-19 | COMP | Rule 15/16 | 71 | 260 | 47 | 26 | 76 | 32 | 508
10126 | 2018-11-14 | 2019-03-04 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-06 | COMP | 2019-07-10 | COMP | 2019-12-16 | COMP | 2023-04-18 | COMP | Rule 15/16 | 73 | 51 | 18 | 24 | 110 | 840 | 1111
10269 | 2018-11-14 | 2019-03-08 | 2019-06-07 | 2019-06-07 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-09-30 | COMP | 2019-10-17 | COMP | Rule 16 | 77 | 65 | 35 | 1 | 46 | 14 | 233
10618 | 2018-11-14 | 2019-03-23 | 2019-04-24 | 2019-04-24 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-11-07 | COMP | 2019-12-09 | COMP | Rule 16 | 87 | 23 | 129 | 1 | 11 | 20 | 267
10657 | 2018-11-14 | 2019-03-25 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-17 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-15 | COMP | Rule 16 | 88 | 47 | 35 | 4 | 1 | 19 | 189
10758 | 2018-11-14 | 2019-03-28 | 2019-07-28 | 2019-07-28 | COMP | 2020-01-08 | COMP | 2020-03-19 | COMP | 2020-04-20 | COMP | 2020-06-05 | COMP | Rule 16 | 91 | 85 | 112 | 50 | 23 | 34 | 391
10838 | 2018-11-14 | 2019-04-01 | 2019-07-11 | 2019-07-11 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-11-12 | COMP | Rule 16 | 93 | 72 | 63 | 1 | 1 | 25 | 250
10839 | 2018-11-14 | 2019-04-01 | 2019-06-05 | 2019-06-05 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-08-12 | COMP | 2019-09-10 | COMP | Rule 16 | 93 | 47 | 44 | 1 | 5 | 21 | 206
10919 | 2018-11-14 | 2019-04-04 | 2019-07-15 | 2019-07-15 | COMP | 2019-08-21 | COMP | 2019-11-12 | COMP | 2019-11-19 | COMP | 2019-12-18 | COMP | Rule 16 | 96 | 71 | 28 | 58 | 6 | 20 | 274
11569 | 2018-11-14 | 2019-05-02 | 2019-05-09 | 2019-05-09 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-12-29 | INPR | 2019-08-05 | COMP | Rule 16 | 116 | 6 | 33 | 1 |  |  | 181
11714 | 2018-11-14 | 2019-05-08 | 2019-09-27 | 2019-10-10 | COMP | 2019-12-13 | COMP | 2019-10-18 | COMP | 2020-01-29 | COMP | 2020-03-05 | COMP | Rule 16 | 120 | 100 | 44 |  | 68 | 26 | 326
11933 | 2018-11-14 | 2019-05-16 | 2019-07-22 | 2019-07-22 | COMP | 2020-01-08 | COMP | 2020-01-08 | COMP | 2020-11-02 | COMP | 2020-12-08 | COMP | Rule 16 | 126 | 46 | 117 | 1 | 210 | 24 | 519
12386 | 2018-11-14 | 2019-06-03 | 2019-09-26 | 2019-09-26 | COMP | 2019-11-07 | COMP | 2020-11-20 | COMP | 2021-01-28 | COMP | 2021-03-04 | COMP | Rule 15/16 | 137 | 82 | 31 | 262 | 45 | 25 | 577
12630 | 2018-11-14 | 2019-06-17 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-12-29 | INPR | 2019-08-05 | COMP | Rule 16 | 147 | 3 | 4 | 1 |  |  | 181
13367 | 2018-11-14 | 2019-07-22 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-09 | COMP | 2019-12-31 | COMP | 2020-03-24 | COMP | 2020-06-16 | COMP | Rule 16 | 171 | 86 | 12 | 16 | 58 | 60 | 398
13732 | 2018-11-14 | 2019-08-07 | 2019-11-25 | 2020-07-27 | COMP | 2020-08-28 | COMP | 2021-07-20 | COMP | 2021-09-29 | COMP | 2021-11-01 | COMP | Rule 16 | 183 | 77 | 25 | 223 | 51 | 24 | 746
13736 | 2018-11-14 | 2019-08-07 | 2020-03-30 | 2020-03-30 | COMP | 2020-07-13 | COMP | 2021-02-08 | COMP | 2021-03-09 | COMP | 2021-04-30 | COMP | Rule 15/16 | 183 | 161 | 75 | 144 | 21 | 39 | 618
14943 | 2018-11-14 | 2019-10-05 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-29 | COMP | 2020-02-04 | COMP | 2021-02-27 | INPR | 2020-02-11 | COMP | Rule 16 | 224 | 64 | 14 | 5 |  |  | 310
40219 | 2018-11-14 | 2022-12-13 | 2023-07-06 | 2023-07-06 | COMP | 2023-07-21 | NOTN | 2023-08-22 | COMP | 2023-10-07 | COMP | 2023-10-20 | COMP | Other | 1025 | 141 |  | 34 | 33 | 10 | 1240
4000 | 2018-11-15 | 2018-11-15 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-11 | COMP | 2019-02-12 | COMP | 2018-12-19 | COMP | 2019-02-26 | COMP | Rule 16 | 1 | 39 | 20 | 2 | 0 | 10 | 68
4001 | 2018-11-15 | 2018-11-15 | 2019-01-14 | 2019-01-14 | COMP | 2019-01-15 | COMP | 2019-01-18 | COMP | 2018-11-27 | COMP | 2019-02-27 | COMP | Rule 16 | 1 | 39 | 2 | 4 | 0 | 27 | 69
8318 | 2018-11-15 | 2018-11-27 | 2019-03-03 | 2019-03-03 | COMP | 2019-03-04 | NOTN | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-04-22 | COMP | Other | 7 | 65 |  | 1 | 1 | 36 | 107
8387 | 2018-11-15 | 2018-11-28 | 2019-04-20 | 2019-04-20 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-12-24 | COMP | 2020-02-04 | COMP | Rule 16 | 8 | 99 | 95 | 1 | 77 | 28 | 304
8761 | 2018-11-15 | 2018-12-22 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-09-12 | COMP | Rule 16 | 25 | 57 | 49 | 1 | 1 | 78 | 207
8940 | 2018-11-15 | 2019-01-08 | 2019-04-01 | 2019-04-01 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2021-02-27 | INPR | 2019-07-22 | COMP | Rule 16 | 35 | 58 | 28 | 1 |  |  | 170
9087 | 2018-11-15 | 2019-01-16 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-29 | COMP | 2019-07-24 | COMP | 2020-01-08 | COMP | 2020-02-12 | COMP | Rule 15/16 | 41 | 51 | 22 | 61 | 115 | 25 | 310
9134 | 2018-11-15 | 2019-01-17 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-08 | COMP | 2019-05-07 | COMP | 2019-05-09 | COMP | 2019-05-10 | COMP | Rule 16 | 42 | 47 | 10 | 22 | 3 | 2 | 121
9148 | 2018-11-15 | 2019-01-18 | 2019-02-10 | 2019-02-10 | COMP | 2019-03-21 | NOTN | 2019-04-10 | COMP | 2019-03-21 | COMP | 2019-07-24 | COMP | Other | 43 | 15 |  | 42 | 0 | 74 | 172
9176 | 2018-11-15 | 2019-01-20 | 2019-03-26 | 2019-04-17 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-06-18 | COMP | 2019-06-28 | COMP | Rule 16 | 43 | 45 | 11 | 1 | 34 | 9 | 155
9216 | 2018-11-15 | 2019-01-22 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-18 | COMP | 2019-04-24 | COMP | 2019-06-24 | COMP | 2019-08-06 | COMP | Rule 16 | 44 | 40 | 23 | 5 | 43 | 31 | 181
9266 | 2018-11-15 | 2019-01-25 | 2019-04-06 | 2019-04-06 | COMP | 2019-11-14 | COMP | 2020-09-09 | COMP | 2021-01-26 | COMP | 2021-03-06 | COMP | Rule 15/16 | 47 | 50 | 155 | 207 | 94 | 28 | 577
9318 | 2018-11-15 | 2019-01-30 | 2019-03-19 | 2019-03-19 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-07-16 | COMP | 2019-08-26 | COMP | Rule 16 | 50 | 34 | 33 | 1 | 52 | 30 | 195
9452 | 2018-11-15 | 2019-02-04 | 2019-04-26 | 2019-04-26 | COMP | 2019-07-08 | COMP | 2019-08-29 | COMP | 2019-09-16 | COMP | 2019-11-07 | COMP | Rule 16 | 53 | 59 | 50 | 39 | 12 | 39 | 247
9460 | 2018-11-15 | 2019-02-05 | 2019-08-03 | 2019-08-03 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-06-16 | COMP | 2021-05-13 | COMP | Rule 16 | 54 | 126 | 113 | 1 | 106 | 230 | 626
9463 | 2018-11-15 | 2019-02-05 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-15 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-07-02 | COMP | Rule 16 | 54 | 38 | 34 | 2 | 1 | 33 | 157
9490 | 2018-11-15 | 2019-02-06 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-29 | COMP | 2019-12-30 | COMP | 2020-05-31 | INPR | 2020-01-22 | COMP | Rule 15/16 | 55 | 47 | 12 | 169 |  |  | 295
9563 | 2018-11-15 | 2019-02-07 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-07 | COMP | 2020-01-14 | COMP | 2020-01-14 | COMP | 2020-02-14 | COMP | Rule 16 | 56 | 70 | 16 | 151 | 1 | 23 | 312
9601 | 2018-11-15 | 2019-02-08 | 2019-02-26 | 2019-02-26 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2019-07-28 | COMP | 2019-08-28 | COMP | Rule 16 | 57 | 12 | 79 | 1 | 29 | 23 | 197
9834 | 2018-11-15 | 2019-02-19 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-11 | COMP | 2019-05-03 | COMP | 2019-09-22 | INPR | 2019-05-30 | COMP | Rule 16 | 63 | 24 | 15 | 17 |  |  | 134
10062 | 2018-11-15 | 2019-02-28 | 2019-05-03 | 2019-05-03 | COMP | 2019-06-04 | COMP | 2019-07-16 | COMP | 2019-06-20 | COMP | 2019-08-21 | COMP | Rule 16 | 70 | 47 | 22 | 30 | 0 | 27 | 192
10291 | 2018-11-15 | 2019-03-09 | 2019-06-04 | 2019-06-04 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-07-11 | COMP | 2019-08-10 | COMP | Rule 16 | 76 | 61 | 26 | 1 | 2 | 22 | 184
10339 | 2018-11-15 | 2019-03-11 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-17 | COMP | 2019-09-23 | COMP | Rule 15/16 | 77 | 55 | 10 | 1 | 27 | 48 | 214
10626 | 2018-11-15 | 2019-03-22 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-11-21 | COMP | 2020-01-11 | COMP | Rule 16 | 86 | 60 | 16 | 1 | 97 | 33 | 288
11056 | 2018-11-15 | 2019-04-10 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-14 | NOTN | 2019-04-29 | COMP | 2020-04-26 | INPR | 2020-01-02 | COMP | Other | 99 | 24 |  |  |  |  | 282
11496 | 2018-11-15 | 2019-04-30 | 2020-04-06 | 2020-10-20 | COMP | 2021-01-22 | COMP | 2020-08-06 | COMP | 2020-12-24 | COMP | 2021-03-18 | COMP | Rule 15/16 | 113 | 235 | 63 |  | 97 | 57 | 586
12164 | 2018-11-15 | 2019-05-24 | 2019-06-22 | 2019-11-07 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-09-08 | COMP | 2020-10-21 | COMP | Rule 16 | 131 | 20 | 10 | 1 | 201 | 32 | 487
13001 | 2018-11-15 | 2019-07-03 | 2019-08-29 | 2019-08-29 | COMP | 2019-10-16 | COMP | 2020-03-11 | COMP | 2020-03-17 | COMP | 2020-07-09 | COMP | Rule 16 | 158 | 41 | 34 | 99 | 5 | 82 | 414
13447 | 2018-11-15 | 2019-07-26 | 2019-07-31 | 2019-07-31 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | 2020-01-13 | COMP | 2020-01-11 | COMP | Rule 16 | 174 | 4 | 31 | 1 | 83 |  | 288
14006 | 2018-11-15 | 2019-08-20 | 2020-03-01 | 2020-03-01 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2022-08-21 | INPR | 2021-07-28 | COMP | Rule 16 | 191 | 131 | 21 | 1 |  |  | 678
16505 | 2018-11-15 | 2020-01-07 | 2020-03-03 | 2020-03-03 | COMP | 2021-12-10 | COMP | 2022-02-23 | COMP | 2022-06-28 | COMP | 2022-07-08 | COMP | Rule 16 | 285 | 39 | 449 | 52 | 88 | 8 | 916
18207 | 2018-11-15 | 2020-03-16 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-04-02 | COMP | 2021-05-18 | COMP | Rule 16 | 332 | 84 | 33 | 1 | 151 | 33 | 629
21174 | 2018-11-15 | 2020-07-24 | 2020-08-12 | 2020-08-12 | COMP | 2020-09-12 | NOTN | 2021-01-25 | COMP | 2021-01-25 | COMP | 2021-04-25 | COMP | Other | 425 | 14 |  | 112 | 1 | 64 | 612
8251 | 2018-11-16 | 2018-11-20 | 2019-08-18 | 2019-08-18 | COMP | 2019-10-11 | COMP | 2020-03-09 | COMP | 2020-05-05 | COMP | 2020-05-23 | COMP | Rule 15/16 | 3 | 186 | 39 | 100 | 42 | 14 | 380
8440 | 2018-11-16 | 2018-12-03 | 2019-01-18 | 2019-01-18 | COMP | 2019-06-06 | COMP | 2019-06-05 | COMP | 2019-10-21 | INPR | 2019-05-22 | COMP | Rule 16 | 10 | 33 | 97 |  |  |  | 128
8503 | 2018-11-16 | 2018-12-05 | 2019-02-22 | 2019-02-22 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2019-04-03 | COMP | 2019-04-17 | COMP | Rule 16 | 12 | 54 | 30 | 1 | 0 | 10 | 103
8587 | 2018-11-16 | 2018-12-10 | 2019-02-26 | 2019-02-26 | COMP | 2019-09-12 | NOTN | 2019-09-12 | COMP | 2019-09-12 | COMP | 2020-01-03 | COMP | Other | 15 | 53 |  | 140 | 1 | 77 | 282
8806 | 2018-11-16 | 2018-12-30 | 2019-02-12 | 2019-02-12 | COMP | 2019-03-15 | COMP | 2019-04-24 | COMP | 2019-04-06 | COMP | 2019-05-15 | COMP | Rule 16 | 28 | 30 | 23 | 29 | 0 | 16 | 123
8895 | 2018-11-16 | 2019-01-04 | 2019-02-11 | 2019-02-11 | COMP | 2019-08-06 | COMP | 2019-07-22 | COMP | 2019-11-04 | COMP | 2020-07-14 | COMP | Rule 16 | 32 | 26 | 124 |  | 75 | 174 | 416
9160 | 2018-11-16 | 2019-01-18 | 2019-12-07 | 2020-06-16 | COMP | 2021-06-15 | COMP | 2022-09-14 | COMP | 2022-10-24 | COMP | 2023-02-13 | COMP | Rule 15/16 | 42 | 223 | 252 | 316 | 29 | 75 | 1064
9290 | 2018-11-16 | 2019-01-28 | 2019-04-15 | 2019-04-15 | COMP | 2019-06-07 | COMP | 2019-09-23 | COMP | 2019-10-01 | COMP | 2019-12-23 | COMP | Rule 15/16 | 47 | 55 | 39 | 75 | 7 | 57 | 275
9428 | 2018-11-16 | 2019-02-04 | 2019-10-03 | 2019-10-03 | COMP | 2021-01-20 | COMP | 2021-11-23 | COMP | 2021-12-03 | COMP | 2021-12-28 | COMP | Rule 15/16 | 52 | 170 | 325 | 215 | 7 | 18 | 782
9499 | 2018-11-16 | 2019-02-06 | 2019-03-13 | 2019-03-13 | COMP | 2019-10-23 | COMP |  | REQD |  | REQD | 2019-10-29 | COMP | Other | 54 | 25 | 158 |  |  |  | 239
9910 | 2018-11-16 | 2019-02-22 | 2019-09-04 | 2019-09-04 | COMP | 2019-10-09 | COMP | 2019-11-27 | COMP | 2023-11-11 | INPR | 2020-02-24 | COMP | Rule 15/16 | 65 | 136 | 26 | 35 |  |  | 316
9930 | 2018-11-16 | 2019-02-23 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-24 | COMP | 2019-04-24 | COMP | 2019-12-29 | INPR | 2019-07-31 | COMP | Rule 16 | 65 | 29 | 15 | 1 |  |  | 176
9961 | 2018-11-16 | 2019-02-25 | 2019-04-30 | 2019-04-30 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-07-03 | COMP | 2019-08-28 | COMP | Rule 16 | 66 | 47 | 66 | 1 | 0 | 20 | 196
10331 | 2018-11-16 | 2019-03-11 | 2019-04-24 | 2019-04-24 | COMP | 2020-08-04 | COMP | 2020-08-05 | COMP | 2020-08-10 | COMP | 2020-09-27 | COMP | Rule 16 | 76 | 33 | 324 | 2 | 4 | 34 | 468
10334 | 2018-11-16 | 2019-03-11 | 2019-06-03 | 2019-06-03 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2020-01-02 | COMP | 2020-01-06 | COMP | Rule 16 | 76 | 60 | 51 | 1 | 97 | 3 | 283
10421 | 2018-11-16 | 2019-03-15 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP |  |  | 2020-02-07 | COMP | Rule 15/16 | 80 | 111 | 16 | 1 |  |  | 306
11307 | 2018-11-16 | 2019-04-22 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-14 | COMP | 2019-08-30 | COMP | 2019-09-03 | COMP | 2019-09-30 | COMP | Rule 16 | 106 | 73 | 9 | 13 | 2 | 20 | 218
11392 | 2018-11-16 | 2019-04-24 | 2019-09-24 | 2019-09-24 | COMP | 2020-05-14 | COMP | 2021-01-20 | COMP | 2021-02-09 | COMP | 2021-03-20 | COMP | Rule 16 | 108 | 107 | 161 | 172 | 15 | 28 | 586
11426 | 2018-11-16 | 2019-04-26 | 2019-08-09 | 2019-08-09 | COMP | 2019-09-05 | COMP | 2019-11-06 | COMP | 2019-12-20 | COMP | 2020-01-21 | COMP | Rule 16 | 110 | 74 | 19 | 45 | 30 | 20 | 293
11434 | 2018-11-16 | 2019-04-26 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-01-23 | COMP | 2020-03-02 | COMP | Rule 16 | 110 | 85 | 11 | 1 | 92 | 27 | 321
12432 | 2018-11-16 | 2019-06-06 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2019-08-07 | COMP | 2019-09-01 | COMP | Rule 16 | 138 | 40 | 3 | 1 | 3 | 18 | 198
12914 | 2018-11-16 | 2019-06-29 | 2020-03-05 | 2020-06-02 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-06 | COMP | 2020-10-17 | COMP | Rule 16 | 154 | 170 | 5 | 1 | 21 | 74 | 483
13063 | 2018-11-16 | 2019-07-09 | 2020-01-18 | 2020-01-18 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-06-01 | COMP | 2020-07-13 | COMP | Rule 16 | 160 | 133 | 61 | 1 | 33 | 31 | 415
15375 | 2018-11-16 | 2019-10-29 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-07-14 | COMP | 2020-08-10 | COMP | Rule 16 | 239 | 142 | 6 | 1 | 32 | 20 | 435
18887 | 2018-11-16 | 2020-04-11 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-07-06 | COMP | 2020-07-29 | COMP | Rule 16 | 350 | 22 | 16 | 1 | 24 | 18 | 427
9272 | 2018-11-18 | 2019-01-25 | 2019-02-14 | 2019-02-14 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-03-15 | COMP | 2019-04-04 | COMP | Rule 16 | 45 | 15 | 12 | 1 | 10 | 15 | 93
8592 | 2018-11-19 | 2018-12-11 | 2019-01-24 | 2019-01-24 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-03-13 | COMP | 2019-05-08 | COMP | Rule 16 | 15 | 30 | 48 | 1 | 0 | 27 | 117
8636 | 2018-11-19 | 2018-12-13 | 2019-02-19 | 2019-02-19 | COMP | 2019-04-01 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-07-30 | COMP | Rule 16 | 17 | 45 | 30 | 42 | 1 | 44 | 174
8781 | 2018-11-19 | 2018-12-24 | 2019-01-09 | 2019-01-09 | COMP | 2019-01-31 | COMP | 2019-01-31 | COMP | 2019-02-13 | COMP | 2019-03-25 | COMP | Rule 16 | 24 | 11 | 16 | 1 | 10 | 28 | 85
8804 | 2018-11-19 | 2018-12-28 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-06-08 | COMP | 2019-06-13 | COMP | Rule 16 | 27 | 40 | 9 | 1 | 65 | 4 | 142
9298 | 2018-11-19 | 2019-01-28 | 2019-05-11 | 2019-05-11 | COMP | 2019-05-28 | COMP | 2019-06-27 | COMP | 2019-07-19 | COMP | 2019-07-25 | COMP | Rule 16 | 46 | 74 | 11 | 23 | 16 | 5 | 171
9544 | 2018-11-19 | 2019-02-07 | 2019-06-17 | 2019-06-17 | COMP | 2019-12-16 | COMP | 2020-03-31 | COMP | 2020-03-30 | COMP | 2020-07-20 | COMP | Rule 15/16 | 54 | 91 | 126 | 73 | 0 | 79 | 419
9711 | 2018-11-19 | 2019-02-12 | 2019-09-26 | 2019-09-26 | COMP | 2019-11-12 | COMP | 2020-01-22 | COMP | 2019-11-19 | COMP | 2020-04-26 | COMP | Rule 16 | 57 | 159 | 33 | 47 | 0 | 67 | 359
9958 | 2018-11-19 | 2019-02-25 | 2019-03-26 | 2019-09-23 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-09-26 | COMP | 2021-03-10 | COMP | Rule 16 | 65 | 22 | 253 | 1 | 4 | 111 | 578
10077 | 2018-11-19 | 2019-03-01 | 2020-04-06 | 2021-09-03 | COMP | 2022-08-16 | COMP | 2022-08-16 | COMP | 2022-12-22 | COMP | 2023-03-25 | COMP | Rule 15/16 | 69 | 277 | 239 | 1 | 89 | 63 | 1091
10125 | 2018-11-19 | 2019-03-04 | 2019-04-29 | 2019-04-29 | COMP | 2019-06-10 | COMP | 2019-06-21 | COMP | 2019-06-06 | COMP | 2019-07-08 | COMP | Rule 16 | 70 | 41 | 30 | 10 | 0 | 11 | 158
10238 | 2018-11-19 | 2019-03-07 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-01 | COMP | 2019-08-02 | COMP | Rule 16 | 73 | 48 | 20 | 1 | 16 | 24 | 177
10249 | 2018-11-19 | 2019-03-08 | 2020-11-21 | 2020-11-21 | COMP | 2021-07-02 | COMP | 2021-11-18 | COMP | 2021-11-30 | COMP | 2022-01-26 | COMP | Rule 15/16 | 74 | 433 | 153 | 97 | 7 | 41 | 801
10283 | 2018-11-19 | 2019-03-08 | 2020-06-15 | 2020-06-15 | COMP | 2020-08-07 | COMP | 2020-09-21 | COMP | 2020-08-14 | COMP | 2020-10-20 | COMP | Rule 16 | 74 | 321 | 40 | 31 | 0 | 22 | 484
10624 | 2018-11-19 | 2019-03-22 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-08-31 | COMP | 2019-10-08 | COMP | Rule 16 | 84 | 89 | 28 | 1 | 0 | 25 | 223
10860 | 2018-11-19 | 2019-04-03 | 2019-04-29 | 2019-04-29 | COMP | 2019-05-17 | COMP | 2019-05-22 | COMP | 2020-05-31 | INPR | 2019-07-17 | COMP | Rule 16 | 92 | 19 | 15 | 4 |  |  | 165
10892 | 2018-11-19 | 2019-04-03 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-10-23 | COMP | Rule 16 | 92 | 62 | 19 | 1 | 1 | 64 | 234
11004 | 2018-11-19 | 2019-04-09 | 2019-10-30 | 2022-05-27 | COMP | 2022-06-23 | COMP | 2021-09-16 | COMP | 2022-07-12 | COMP | 2022-08-09 | COMP | Rule 15/16 | 96 | 144 | 18 |  | 206 | 21 | 936
11361 | 2018-11-19 | 2019-04-24 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-08-01 | COMP | 2019-09-06 | COMP | Rule 15/16 | 107 | 27 | 20 | 1 | 25 | 26 | 201
11455 | 2018-11-19 | 2019-04-29 | 2019-07-29 | 2019-07-29 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-05-08 | COMP | 2020-06-02 | COMP | Rule 16 | 110 | 64 | 161 | 1 | 37 | 17 | 385
11664 | 2018-11-19 | 2019-05-07 | 2019-06-28 | 2019-06-28 | COMP | 2019-06-29 | NOTN | 2019-06-29 | COMP | 2020-01-07 | COMP | 2020-06-25 | COMP | Other | 116 | 38 |  | 1 | 130 | 120 | 402
13750 | 2018-11-19 | 2019-08-07 | 2019-10-29 | 2019-12-02 | COMP | 2019-12-03 | COMP | 2020-06-09 | COMP | 2019-12-28 | COMP | 2020-06-16 | COMP | Rule 16 | 180 | 59 | 2 | 131 | 0 | 6 | 395
14580 | 2018-11-19 | 2019-09-17 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-12-04 | COMP | 2019-12-13 | COMP | Rule 16 | 208 | 37 | 10 | 1 | 9 | 8 | 268
15180 | 2018-11-19 | 2019-10-17 | 2020-07-21 | 2020-07-21 | COMP | 2020-08-03 | COMP | 2020-08-27 | COMP | 2020-09-09 | COMP | 2020-09-18 | COMP | Rule 16 | 230 | 191 | 10 | 19 | 9 | 8 | 462
15835 | 2018-11-19 | 2019-11-23 | 2020-01-09 | 2020-01-09 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-11-13 | COMP | 2021-06-24 | COMP | Rule 16 | 255 | 30 | 65 | 1 | 153 | 153 | 653
15836 | 2018-11-19 | 2019-11-23 | 2020-01-12 | 2020-01-12 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2021-07-13 | COMP | 2022-10-24 | COMP | Rule 16 | 255 | 31 | 63 | 1 | 317 | 325 | 989
4047 | 2018-11-20 | 2018-12-29 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-12 | NOTN | 2019-06-26 | COMP | 2019-07-16 | COMP | 2020-02-20 | COMP | Other | 26 | 116 |  | 9 | 14 | 150 | 312
8324 | 2018-11-20 | 2018-11-27 | 2019-01-23 | 2019-02-15 | COMP | 2019-03-04 | COMP | 2019-03-29 | COMP | 2019-03-04 | COMP | 2019-05-10 | COMP | Rule 16 | 4 | 39 | 11 | 20 | 0 | 31 | 118
8450 | 2018-11-20 | 2018-12-04 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-27 | COMP | 2019-08-05 | COMP | 2019-11-18 | COMP | 2019-12-06 | COMP | Rule 16 | 9 | 48 | 11 | 112 | 74 | 13 | 262
8451 | 2018-11-20 | 2018-12-04 | 2019-02-09 | 2019-02-09 | COMP | 2019-02-27 | COMP | 2019-04-24 | COMP | 2020-01-10 | COMP | 2020-03-09 | COMP | Rule 16 | 9 | 46 | 12 | 41 | 180 | 40 | 324
8452 | 2018-11-20 | 2018-12-04 | 2019-02-25 | 2019-02-25 | COMP | 2019-03-08 | COMP | 2019-06-14 | COMP | 2020-01-10 | COMP | 2020-02-27 | COMP | Rule 16 | 9 | 56 | 10 | 70 | 144 | 33 | 317
8568 | 2018-11-20 | 2018-12-11 | 2019-03-11 | 2019-03-11 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2020-10-25 | COMP | 2020-11-20 | COMP | Rule 16 | 14 | 61 | 67 | 1 | 347 | 19 | 505
8612 | 2018-11-20 | 2018-12-11 | 2019-03-21 | 2019-03-27 | COMP | 2019-04-15 | COMP | 2019-04-24 | COMP | 2019-05-15 | COMP | 2019-06-10 | COMP | Rule 15/16 | 14 | 69 | 14 | 8 | 16 | 18 | 138
8680 | 2018-11-20 | 2018-12-15 | 2019-02-13 | 2019-02-27 | COMP | 2019-03-07 | COMP | 2019-04-18 | COMP | 2019-04-23 | COMP | 2019-05-22 | COMP | Rule 16 | 17 | 40 | 7 | 31 | 4 | 22 | 126
8848 | 2018-11-20 | 2019-01-03 | 2019-07-02 | 2019-11-27 | COMP | 2020-08-31 | COMP | 2021-04-19 | COMP | 2022-03-09 | COMP | 2022-04-11 | COMP | Rule 15/16 | 29 | 126 | 192 | 158 | 225 | 24 | 852
8851 | 2018-11-20 | 2019-01-03 | 2019-02-07 | 2019-02-07 | COMP | 2019-02-08 | NOTN | 2019-02-12 | COMP | 2019-02-26 | NOTN | 2019-04-17 | COMP | Other | 29 | 25 |  | 4 |  |  | 101
8928 | 2018-11-20 | 2019-01-08 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-26 | COMP | 2019-03-13 | COMP | 2019-03-13 | COMP | 2019-05-09 | COMP | Rule 15/16 | 32 | 26 | 9 | 12 | 1 | 42 | 117
9066 | 2018-11-20 | 2019-01-15 | 2019-03-08 | 2019-03-08 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-10-07 | COMP | Rule 16 | 37 | 37 | 127 | 1 | 1 | 23 | 221
9170 | 2018-11-20 | 2019-01-19 | 2019-05-12 | 2019-05-12 | COMP | 2019-05-20 | COMP | 2019-07-25 | INPR | 2019-06-11 | COMP | 2019-07-23 | COMP | Rule 15/16 | 40 | 78 | 6 |  |  |  | 168
9438 | 2018-11-20 | 2019-02-04 | 2019-05-20 | 2019-05-20 | COMP | 2019-08-21 | COMP | 2020-04-11 | COMP | 2020-06-02 | COMP | 2020-07-11 | COMP | Rule 16 | 50 | 75 | 66 | 160 | 36 | 29 | 412
9461 | 2018-11-20 | 2019-02-05 | 2019-04-14 | 2019-04-14 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-12-10 | COMP | 2019-12-14 | COMP | Rule 16 | 51 | 48 | 129 | 1 | 38 | 4 | 267
9959 | 2018-11-20 | 2019-02-25 | 2019-05-17 | 2019-05-17 | COMP | 2019-10-07 | COMP | 2019-10-08 | COMP | 2021-02-27 | INPR | 2020-02-24 | COMP | Rule 16 | 64 | 60 | 99 | 2 |  |  | 314
10214 | 2018-11-20 | 2019-03-06 | 2019-06-07 | 2019-06-07 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-03-06 | COMP | 2020-06-08 | COMP | Rule 16 | 71 | 67 | 216 | 1 | 0 | 37 | 388
10304 | 2018-11-20 | 2019-03-11 | 2019-05-11 | 2020-01-09 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-03-05 | COMP | Rule 16 | 74 | 45 | 20 | 1 | 1 | 20 | 322
10468 | 2018-11-20 | 2019-03-18 | 2019-07-11 | 2019-07-19 | COMP | 2019-07-24 | NOTN | 2019-07-24 | COMP | 2019-07-11 | COMP | 2020-08-31 | COMP | Rule 15 | 79 | 82 |  | 4 | 0 | 280 | 448
10802 | 2018-11-20 | 2019-03-29 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-07-19 | COMP | Rule 16 | 88 | 21 | 12 | 1 | 1 | 48 | 166
11365 | 2018-11-20 | 2019-04-24 | 2019-08-20 | 2019-08-20 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2020-02-11 | COMP | 2020-02-25 | COMP | Rule 16 | 106 | 83 | 56 | 1 | 64 | 10 | 315
11395 | 2018-11-20 | 2019-04-24 | 2019-07-22 | 2019-07-22 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-12-09 | COMP | 2020-01-02 | COMP | Rule 16 | 106 | 62 | 69 | 1 | 29 | 17 | 279
11410 | 2018-11-20 | 2019-04-25 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-07 | COMP | 2019-09-09 | COMP | 2019-09-10 | COMP | 2019-10-06 | COMP | Rule 16 | 107 | 58 | 16 | 23 | 2 | 19 | 220
11505 | 2018-11-20 | 2019-04-30 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-11 | COMP | 2020-06-24 | COMP | 2020-09-29 | COMP | 2020-10-15 | COMP | Rule 15/16 | 110 | 127 | 30 | 136 | 69 | 13 | 480
11583 | 2018-11-20 | 2019-05-04 | 2019-06-24 | 2019-06-24 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2020-01-07 | COMP | 2020-01-06 | COMP | Rule 16 | 113 | 35 | 60 | 1 | 76 |  | 281
12944 | 2018-11-20 | 2019-07-01 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-08 | COMP | 2020-01-31 | COMP | 2020-09-18 | COMP | 2020-09-30 | COMP | Rule 16 | 153 | 78 | 15 | 55 | 163 | 9 | 469
13045 | 2018-11-20 | 2019-07-08 | 2019-08-31 | 2019-08-31 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-07-20 | COMP | 2020-10-29 | COMP | Rule 16 | 157 | 40 | 99 | 1 | 124 | 73 | 490
13845 | 2018-11-20 | 2019-08-13 | 2020-01-02 | 2020-01-02 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-03-30 | COMP | 2020-05-13 | COMP | Rule 16 | 183 | 97 | 70 | 1 | 0 | 24 | 371
15222 | 2018-11-20 | 2019-10-21 | 2019-12-12 | 2019-12-12 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-25 | COMP | Rule 16 | 231 | 36 | 58 | 1 | 1 | 14 | 336
8333 | 2018-11-21 | 2018-11-28 | 2019-01-23 | 2019-01-23 | COMP | 2019-03-20 | COMP | 2019-03-20 | COMP | 2019-10-21 | INPR | 2019-05-03 | COMP | Rule 16 | 4 | 38 | 40 | 1 |  |  | 112
8572 | 2018-11-21 | 2018-12-11 | 2019-01-28 | 2019-01-28 | COMP | 2019-02-20 | COMP | 2019-02-22 | COMP | 2019-02-20 | COMP | 2019-04-12 | COMP | Rule 16 | 13 | 32 | 17 | 3 | 0 | 36 | 97
8599 | 2018-11-21 | 2018-12-13 | 2019-02-12 | 2019-02-12 | COMP | 2019-02-12 | NOTN | 2019-02-12 | COMP | 2019-02-14 | COMP | 2019-04-02 | COMP | Other | 15 | 41 |  | 1 | 3 | 33 | 89
8845 | 2018-11-21 | 2019-01-02 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-24 | COMP | 2019-06-05 | COMP | 2020-06-03 | COMP | 2020-06-08 | COMP | Other | 27 | 65 | 15 | 30 | 251 | 4 | 387
9071 | 2018-11-21 | 2019-01-15 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-03-14 | COMP | 2019-04-15 | COMP | Rule 16 | 36 | 33 | 14 | 1 | 0 | 18 | 98
9077 | 2018-11-21 | 2019-01-16 | 2019-05-23 | 2019-05-23 | COMP | 2019-07-09 | COMP | 2019-05-29 | COMP | 2019-07-09 | COMP | 2019-07-24 | COMP | Rule 16 | 37 | 90 | 32 |  | 29 | 12 | 168
9174 | 2018-11-21 | 2019-01-20 | 2019-03-27 | 2019-03-27 | COMP | 2019-08-15 | COMP | 2020-02-03 | COMP | 2019-09-05 | COMP | 2020-03-12 | COMP | Rule 16 | 39 | 46 | 100 | 116 | 0 | 28 | 326
9239 | 2018-11-21 | 2019-01-24 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-24 | COMP | 2019-07-15 | COMP | 2019-07-29 | COMP | 2019-08-26 | COMP | Rule 16 | 42 | 37 | 50 | 35 | 11 | 21 | 191
9288 | 2018-11-21 | 2019-01-28 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-16 | COMP | 2019-09-25 | COMP | 2019-09-29 | COMP | 2019-11-15 | COMP | Rule 16 | 44 | 49 | 8 | 114 | 3 | 34 | 248
9571 | 2018-11-21 | 2019-02-07 | 2019-04-18 | 2019-04-18 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-05-03 | NOTN | 2019-06-02 | COMP | Rule 16 | 52 | 50 | 48 | 1 |  |  | 131
9577 | 2018-11-21 | 2019-02-08 | 2019-03-15 | 2019-03-15 | COMP | 2019-04-15 | COMP | 2019-04-17 | COMP | 2019-04-16 | COMP | 2019-07-03 | COMP | Rule 16 | 53 | 25 | 22 | 3 | 0 | 55 | 154
9620 | 2018-11-21 | 2019-02-08 | 2019-05-12 | 2019-05-12 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-06-25 | COMP | 2019-07-02 | COMP | Rule 16 | 53 | 65 | 11 | 1 | 21 | 6 | 153
9664 | 2018-11-21 | 2019-02-11 | 2019-04-15 | 2019-04-15 | COMP | 2019-04-29 | COMP | 2019-06-21 | COMP | 2019-11-19 | COMP | 2020-03-05 | COMP | Rule 16 | 54 | 45 | 11 | 39 | 105 | 72 | 321
10155 | 2018-11-21 | 2019-03-05 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-07 | COMP | 2019-10-23 | COMP | 2020-02-05 | COMP | 2020-02-24 | COMP | Rule 15/16 | 69 | 53 | 16 | 97 | 70 | 13 | 313
10197 | 2018-11-21 | 2019-03-06 | 2019-05-25 | 2019-05-25 | COMP | 2019-07-23 | COMP | 2019-07-25 | COMP | 2019-06-24 | COMP | 2019-08-15 | COMP | Rule 16 | 70 | 58 | 40 | 3 | 0 | 16 | 184
10230 | 2018-11-21 | 2019-03-07 | 2019-05-23 | 2019-05-23 | COMP | 2019-07-01 | COMP | 2019-07-22 | COMP | 2020-05-26 | COMP | 2020-06-02 | COMP | Rule 16 | 71 | 56 | 27 | 15 | 213 | 6 | 383
10255 | 2018-11-21 | 2019-03-07 | 2020-03-13 | 2020-03-13 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2021-05-17 | COMP | 2021-07-01 | COMP | Rule 16 | 71 | 257 | 43 | 1 | 256 | 33 | 656
10470 | 2018-11-21 | 2019-03-18 | 2020-07-20 | 2020-07-20 | COMP | 2020-11-02 | COMP | 2022-09-29 | COMP | 2022-12-13 | COMP | 2023-01-29 | COMP | Rule 15/16 | 78 | 340 | 75 | 480 | 51 | 31 | 1050
10832 | 2018-11-21 | 2019-04-01 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-06-05 | COMP | 2019-07-11 | COMP | Rule 16 | 88 | 22 | 17 | 1 | 10 | 26 | 159
10908 | 2018-11-21 | 2019-04-04 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-14 | COMP | 2019-11-20 | COMP | 2019-09-16 | COMP | 2020-01-23 | COMP | Rule 16 | 91 | 86 | 8 | 69 | 0 | 42 | 292
11042 | 2018-11-21 | 2019-04-10 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-12 | COMP | 2019-08-22 | COMP | 2019-09-04 | COMP | 2019-10-04 | COMP | Rule 16 | 95 | 59 | 8 | 30 | 9 | 23 | 219
11789 | 2018-11-21 | 2019-05-11 | 2019-09-05 | 2019-09-05 | COMP | 2021-02-08 | COMP | 2021-07-12 | COMP | 2023-09-11 | COMP | 2023-10-09 | COMP | Rule 16 | 117 | 81 | 358 | 108 | 545 | 21 | 1226
12718 | 2018-11-21 | 2019-06-19 | 2019-08-01 | 2019-08-01 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-09-20 | COMP | 2019-11-11 | COMP | Rule 16 | 144 | 31 | 44 | 1 | 0 | 28 | 244
12756 | 2018-11-21 | 2019-06-20 | 2019-09-23 | 2020-02-21 | COMP | 2020-03-10 | COMP | 2020-03-11 | COMP | 2020-07-01 | COMP | 2020-07-29 | COMP | Rule 16 | 145 | 66 | 13 | 2 | 80 | 21 | 424
13022 | 2018-11-21 | 2019-07-05 | 2019-11-12 | 2020-07-30 | COMP | 2020-09-04 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2020-11-12 | COMP | Rule 15/16 | 155 | 91 | 27 | 16 | 1 | 33 | 498
13087 | 2018-11-21 | 2019-07-10 | 2019-11-12 | 2019-12-10 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-05-14 | COMP | 2020-07-09 | COMP | Rule 16 | 158 | 88 | 27 | 1 | 83 | 40 | 410
13088 | 2018-11-21 | 2019-07-11 | 2020-08-07 | 2020-09-23 | COMP | 2020-11-12 | COMP | 2020-11-12 | COMP | 2021-02-04 | COMP | 2021-03-31 | COMP | Rule 15/16 | 159 | 273 | 36 | 1 | 56 | 39 | 591
9758 | 2018-11-24 | 2019-02-13 | 2019-04-16 | 2019-04-16 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | Rule 15/16 | 55 | 44 | 214 | 1 | 33 | 1 | 343
4109 | 2018-11-26 | 2019-02-11 | 2019-10-15 | 2019-02-15 | COMP | 2019-04-29 | COMP | 2019-10-16 | INPR |  | REQD | 2019-11-07 | COMP | Other | 53 | 173 | 51 |  |  |  | 242
8312 | 2018-11-26 | 2018-11-26 | 2018-12-05 | 2018-12-05 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-10-30 | COMP | 2020-01-16 | COMP | Rule 16 | 1 | 8 | 230 | 1 | 0 | 51 | 287
8631 | 2018-11-26 | 2018-12-13 | 2019-04-05 | 2019-04-05 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2020-10-20 | COMP | 2020-11-10 | COMP | Rule 16 | 14 | 78 | 19 | 1 | 373 | 16 | 496
8937 | 2018-11-26 | 2019-01-08 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-01 | COMP | 2019-07-08 | COMP | 2019-06-26 | COMP | 2019-07-14 | COMP | Rule 16 | 30 | 35 | 3 | 90 | 0 | 5 | 159
9111 | 2018-11-26 | 2019-01-17 | 2019-04-02 | 2019-04-02 | COMP | 2019-05-02 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-08-06 | COMP | Rule 16 | 37 | 52 | 23 | 44 | 1 | 24 | 176
9124 | 2018-11-26 | 2019-01-17 | 2019-07-18 | 2019-07-18 | COMP | 2019-11-07 | COMP | 2020-03-27 | COMP | 2021-03-07 | COMP | 2021-03-26 | COMP | Rule 15/16 | 37 | 127 | 80 | 95 | 237 | 15 | 587
9193 | 2018-11-26 | 2019-01-22 | 2019-04-24 | 2019-04-24 | COMP | 2019-04-30 | NOTN | 2019-04-30 | COMP | 2019-04-01 | COMP | 2019-06-10 | COMP | Other | 39 | 66 |  | 5 | 0 | 29 | 136
9364 | 2018-11-26 | 2019-01-31 | 2019-03-05 | 2019-03-05 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-07-12 | COMP | 2019-07-31 | COMP | Rule 16 | 46 | 23 | 8 | 1 | 85 | 14 | 172
10005 | 2018-11-26 | 2019-02-26 | 2019-06-29 | 2019-06-29 | COMP | 2019-08-07 | COMP | 2019-08-20 | COMP | 2019-09-13 | COMP | 2019-09-24 | COMP | Rule 15/16 | 63 | 88 | 27 | 10 | 18 | 8 | 210
10199 | 2018-11-26 | 2019-03-06 | 2019-05-02 | 2019-10-29 | COMP | 2019-11-19 | COMP | 2019-11-25 | COMP | 2019-11-22 | COMP | 2020-02-12 | COMP | Rule 16 | 69 | 42 | 15 | 5 | 0 | 53 | 305
10232 | 2018-11-26 | 2019-03-07 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-11-12 | COMP | 2019-12-28 | COMP | Rule 16 | 70 | 52 | 17 | 1 | 108 | 31 | 274
10509 | 2018-11-26 | 2019-03-19 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-07-15 | COMP | 2019-07-24 | COMP | Rule 16 | 78 | 63 | 17 | 1 | 5 | 8 | 167
11509 | 2018-11-26 | 2019-04-30 | 2019-05-22 | 2019-05-22 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-12-18 | COMP | 2020-02-11 | COMP | Rule 16 | 108 | 17 | 113 | 1 | 33 | 37 | 304
11658 | 2018-11-26 | 2019-05-07 | 2019-08-16 | 2019-08-16 | COMP | 2019-10-07 | COMP | 2019-10-07 | COMP | 2023-09-02 | INPR | 2020-10-13 | COMP | Rule 16 | 113 | 72 | 36 | 1 |  |  | 476
11875 | 2018-11-26 | 2019-05-15 | 2019-09-05 | 2019-09-05 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-07-02 | COMP | 2020-08-12 | COMP | Rule 16 | 119 | 79 | 151 | 1 | 58 | 30 | 433
12326 | 2018-11-26 | 2019-05-31 | 2019-08-29 | 2020-02-08 | COMP | 2020-02-20 | COMP | 2019-10-26 | COMP | 2020-05-29 | COMP | 2020-09-24 | COMP | Rule 16 | 130 | 64 | 8 |  | 147 | 84 | 463
12915 | 2018-11-26 | 2019-06-29 | 2019-10-14 | 2019-12-06 | COMP | 2020-02-04 | COMP | 2020-03-06 | COMP |  | INPR | 2021-02-25 | COMP | Rule 16 | 150 | 74 | 40 | 23 |  |  | 566
13041 | 2018-11-26 | 2019-07-08 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-14 | NOTN | 2020-01-13 | COMP | 2020-10-23 | COMP | 2021-02-03 | COMP | Other | 155 | 65 |  | 66 | 201 | 68 | 551
13103 | 2018-11-26 | 2019-07-11 | 2019-10-27 | 2019-10-27 | COMP | 2019-11-05 | COMP | 2019-12-30 | COMP | 2021-02-27 | INPR | 2020-02-24 | COMP | Rule 16 | 158 | 76 | 7 | 36 |  |  | 312
13916 | 2018-11-26 | 2019-08-16 | 2019-12-24 | 2019-12-24 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-05-04 | COMP | 2020-07-30 | COMP | Rule 16 | 184 | 89 | 85 | 1 | 7 | 63 | 424
14248 | 2018-11-26 | 2019-08-30 | 2019-10-23 | 2019-10-23 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2020-02-12 | COMP | 2020-02-25 | COMP | Rule 15/16 | 194 | 38 | 7 | 1 | 69 | 9 | 313
15386 | 2018-11-26 | 2019-10-29 | 2019-12-31 | 2019-12-31 | COMP | 2020-02-03 | COMP | 2020-08-29 | COMP | 2021-08-24 | COMP | 2021-09-03 | COMP | Rule 16 | 235 | 42 | 23 | 148 | 247 | 9 | 700
34358 | 2018-11-26 | 2022-02-10 | 2022-02-18 | 2022-04-01 | COMP | 2022-06-03 | COMP | 2022-06-08 | COMP | 2022-11-30 | COMP | 2023-05-03 | COMP | Rule 15/16 | 809 | 7 | 45 | 4 | 120 | 107 | 1116
4095 | 2018-11-27 | 2019-01-28 | 2019-03-21 | 2019-03-21 | COMP | 2019-05-13 | COMP | 2019-05-21 | COMP | 2019-06-06 | COMP | 2019-07-17 | COMP | Rule 16 | 42 | 38 | 38 | 7 | 12 | 29 | 161
4120 | 2018-11-27 | 2019-03-06 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-06 | NOTN | 2019-03-06 | INPR | 2019-03-12 | COMP | 2019-03-11 | COMP | Other | 68 | 1 |  |  |  |  | 71
4142 | 2018-11-27 | 2019-04-03 | 2019-09-23 | 2019-09-23 | COMP | 2019-11-21 | COMP | 2020-04-04 | COMP | 2020-12-20 | COMP | 2021-03-08 | COMP | Rule 15/16 | 88 | 121 | 43 | 91 | 180 | 52 | 572
8328 | 2018-11-27 | 2018-11-27 | 2019-03-04 | 2020-03-09 | COMP | 2020-03-12 | COMP | 2020-03-16 | COMP | 2020-03-20 | COMP | 2020-04-16 | COMP | Rule 16 | 1 | 66 | 4 | 3 | 5 | 20 | 349
8335 | 2018-11-27 | 2018-11-28 | 2019-01-02 | 2019-01-02 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-09-22 | INPR | 2019-02-07 | COMP | Rule 16 | 2 | 24 | 28 | 1 |  |  | 50
8505 | 2018-11-27 | 2018-12-05 | 2019-02-27 | 2019-02-27 | COMP | 2019-03-01 | COMP | 2019-03-04 | COMP | 2019-04-26 | COMP | 2019-01-22 | COMP | Rule 16 | 7 | 57 | 3 | 2 | 40 |  | 38
8866 | 2018-11-27 | 2019-01-03 | 2019-04-03 | 2019-04-03 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-06-29 | COMP | 2019-09-23 | COMP | Rule 16 | 26 | 63 | 44 | 1 | 19 | 59 | 208
9021 | 2018-11-27 | 2019-01-13 | 2019-04-23 | 2020-10-29 | COMP | 2020-11-05 | COMP | 2020-11-05 | COMP | 2020-10-30 | COMP | 2020-12-14 | COMP | Rule 16 | 32 | 70 | 6 | 1 | 0 | 25 | 516
9037 | 2018-11-27 | 2019-01-14 | 2019-03-23 | 2019-03-23 | COMP | 2019-04-02 | COMP | 2019-04-05 | COMP | 2019-09-02 | INPR | 2019-05-02 | COMP | Rule 16 | 33 | 48 | 7 | 4 |  |  | 109
9144 | 2018-11-27 | 2019-01-17 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-08 | COMP | 2019-04-17 | COMP | 2019-05-20 | COMP | 2019-06-25 | COMP | Rule 15/16 | 36 | 50 | 6 | 8 | 24 | 26 | 146
9221 | 2018-11-27 | 2019-01-23 | 2019-05-11 | 2019-05-11 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-09 | COMP | 2019-10-07 | COMP | Rule 16 | 39 | 77 | 39 | 1 | 2 | 64 | 218
9293 | 2018-11-27 | 2019-01-28 | 2019-05-23 | 2019-05-23 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2020-03-25 | COMP | 2020-04-28 | COMP | Rule 16 | 42 | 83 | 72 | 1 | 139 | 25 | 357
9321 | 2018-11-27 | 2019-01-30 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-12-29 | INPR | 2019-08-14 | COMP | Rule 16 | 44 | 57 | 12 | 1 |  |  | 181
9341 | 2018-11-27 | 2019-01-30 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-05-04 | COMP | 2019-05-21 | COMP | Rule 16 | 44 | 55 | 14 | 1 | 0 | 12 | 122
9374 | 2018-11-27 | 2019-01-31 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-09 | NOTN | 2019-05-07 | COMP | 2019-04-09 | COMP | 2019-06-24 | COMP | Other | 45 | 46 |  | 22 | 0 | 34 | 145
9468 | 2018-11-27 | 2019-02-05 | 2019-04-19 | 2019-04-19 | COMP | 2019-06-18 | COMP | 2019-06-18 | COMP | 2019-09-27 | COMP | 2019-10-02 | COMP | Rule 16 | 48 | 53 | 42 | 1 | 72 | 4 | 215
9483 | 2018-11-27 | 2019-02-06 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-29 | COMP | 2019-05-30 | COMP | 2019-07-15 | COMP | 2019-10-16 | COMP | Rule 16 | 49 | 62 | 18 | 2 | 32 | 67 | 225
9624 | 2018-11-27 | 2019-02-09 | 2019-05-03 | 2019-11-27 | COMP | 2020-04-26 | REQD | 2019-07-19 | COMP | 2019-12-19 | COMP | 2020-01-16 | COMP | Rule 16 | 51 | 59 |  |  | 106 | 19 | 286
9833 | 2018-11-27 | 2019-02-19 | 2019-10-06 | 2019-10-06 | COMP | 2020-04-13 | COMP | 2020-10-23 | COMP | 2020-11-09 | COMP | 2021-01-15 | COMP | Rule 15/16 | 57 | 161 | 129 | 138 | 12 | 45 | 538
9836 | 2018-11-27 | 2019-02-20 | 2019-08-28 | 2019-08-28 | COMP | 2020-02-21 | COMP | 2020-07-17 | COMP | 2021-03-29 | COMP | 2021-04-20 | COMP | Rule 16 | 58 | 134 | 120 | 105 | 174 | 17 | 603
9981 | 2018-11-27 | 2019-02-25 | 2019-03-22 | 2019-03-22 | COMP | 2019-03-29 | COMP | 2019-03-29 | NOTN | 2019-04-03 | COMP | 2019-04-09 | COMP | Rule 16 | 61 | 20 | 6 |  |  |  | 92
10070 | 2018-11-27 | 2019-02-28 | 2019-05-18 | 2019-05-18 | COMP | 2019-06-19 | COMP | 2019-06-25 | COMP | 2019-07-09 | COMP | 2019-11-05 | COMP | Rule 16 | 64 | 57 | 22 | 5 | 10 | 85 | 239
10467 | 2018-11-27 | 2019-03-18 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-03 | COMP | 2019-06-24 | COMP | 2020-05-31 | INPR | 2019-07-25 | COMP | Rule 16 | 76 | 42 | 14 | 16 |  |  | 167
10950 | 2018-11-27 | 2019-04-05 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-08 | COMP | 2019-09-26 | COMP | 2019-09-27 | COMP | 2020-01-28 | COMP | Rule 16 | 90 | 61 | 5 | 58 | 2 | 82 | 293
11077 | 2018-11-27 | 2019-04-11 | 2019-05-07 | 2019-05-07 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-07-30 | COMP | 2019-08-23 | COMP | Rule 16 | 94 | 19 | 31 | 1 | 29 | 19 | 188
12136 | 2018-11-27 | 2019-05-24 | 2019-07-29 | 2019-07-29 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2021-05-20 | COMP | 2021-07-09 | COMP | Rule 16 | 125 | 45 | 6 | 1 | 452 | 35 | 659
13671 | 2018-11-27 | 2019-08-05 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-13 | COMP | 2020-03-06 | COMP | 2020-05-20 | COMP | 2020-06-02 | COMP | Rule 16 | 174 | 62 | 10 | 77 | 54 | 9 | 381
13976 | 2018-11-27 | 2019-08-19 | 2020-06-28 | 2020-06-28 | COMP | 2021-02-04 | COMP | 2021-02-04 | COMP | 2021-10-13 | COMP | 2021-12-09 | COMP | Rule 15/16 | 184 | 216 | 152 | 1 | 176 | 39 | 764
14482 | 2018-11-27 | 2019-09-11 | 2019-11-22 | 2019-11-22 | COMP | 2020-05-19 | COMP | 2020-09-03 | COMP | 2020-08-14 | COMP | 2020-09-30 | COMP | Rule 16 | 200 | 52 | 122 | 77 | 0 | 19 | 466
16596 | 2018-11-27 | 2020-01-09 | 2020-02-13 | 2020-02-13 | COMP | 2020-03-24 | COMP | 2020-06-04 | COMP | 2020-09-18 | COMP | 2020-10-08 | COMP | Rule 16 | 281 | 25 | 28 | 52 | 76 | 15 | 472
17306 | 2018-11-27 | 2020-02-08 | 2020-02-12 | 2020-02-12 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-03-31 | COMP | 2020-04-16 | COMP | Rule 16 | 301 | 3 | 10 | 1 | 25 | 13 | 349
18016 | 2018-11-27 | 2020-03-09 | 2020-05-28 | 2020-05-28 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2022-01-30 | INPR | 2020-06-30 | COMP | Rule 16 | 321 | 58 | 8 | 1 |  |  | 401
20848 | 2018-11-27 | 2020-07-08 | 2020-09-24 | 2020-09-24 | COMP | 2020-10-26 | COMP | 2023-05-11 | COMP |  |  | 2023-08-26 | COMP | Rule 16 | 407 | 56 | 23 | 638 |  |  | 1194
4038 | 2018-11-28 | 2018-12-26 | 2019-03-15 | 2019-03-15 | COMP | 2019-04-25 | COMP | 2019-05-16 | COMP | 2019-11-23 | INPR | 2019-07-24 | COMP | Rule 16 | 20 | 55 | 30 | 16 |  |  | 165
4087 | 2018-11-28 | 2019-01-20 | 2019-04-22 | 2019-04-22 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-05-31 | COMP | 2019-08-04 | COMP | Rule 16 | 36 | 64 | 19 | 1 | 11 | 45 | 172
8459 | 2018-11-28 | 2018-12-04 | 2019-01-01 | 2019-01-01 | COMP | 2019-01-09 | COMP | 2019-02-04 | COMP | 2019-01-14 | COMP | 2019-02-26 | COMP | Rule 16 | 5 | 19 | 6 | 18 | 0 | 16 | 61
8551 | 2018-11-28 | 2018-12-08 | 2018-12-16 | 2018-12-16 | COMP | 2018-12-16 | NOTN | 2018-12-16 | COMP | 2019-05-07 | COMP | 2019-05-11 | COMP | Other | 8 | 5 |  | 0 | 98 | 4 | 114
8557 | 2018-11-28 | 2018-12-10 | 2019-03-11 | 2019-03-11 | COMP | 2019-03-28 | NOTN | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-05-08 | COMP | Other | 9 | 62 |  | 14 | 1 | 30 | 112
8672 | 2018-11-28 | 2018-12-15 | 2019-02-02 | 2019-04-20 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-12-28 | INPR | 2019-07-18 | COMP | Rule 15/16 | 13 | 32 | 27 | 1 |  |  | 161
8757 | 2018-11-28 | 2018-12-22 | 2019-03-08 | 2019-03-08 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-04-18 | COMP | 2019-06-07 | COMP | Rule 15/16 | 18 | 51 | 19 | 1 | 12 | 36 | 133
8832 | 2018-11-28 | 2018-12-31 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-06-29 | COMP | 2019-11-06 | COMP | Rule 16 | 23 | 90 | 17 | 1 | 21 | 91 | 239
8931 | 2018-11-28 | 2019-01-09 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-25 | COMP | 2019-04-25 | COMP | 2019-05-16 | COMP | 2019-07-16 | COMP | Rule 16 | 29 | 64 | 12 | 1 | 16 | 42 | 159
8985 | 2018-11-28 | 2019-01-11 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-04-30 | COMP | 2019-05-14 | COMP | Rule 16 | 31 | 35 | 7 | 1 | 36 | 11 | 116
9090 | 2018-11-28 | 2019-01-16 | 2019-04-13 | 2019-04-13 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-08-29 | COMP | 2019-12-09 | COMP | Rule 15/16 | 34 | 61 | 93 | 1 | 5 | 69 | 259
9178 | 2018-11-28 | 2019-01-20 | 2019-03-30 | 2019-03-30 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-09-05 | COMP | 2019-12-10 | COMP | Rule 16 | 36 | 48 | 37 | 1 | 75 | 66 | 260
9205 | 2018-11-28 | 2019-01-22 | 2019-03-19 | 2019-03-19 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-06-17 | COMP | 2019-07-01 | COMP | Rule 16 | 37 | 40 | 52 | 1 | 13 | 11 | 149
9795 | 2018-11-28 | 2019-02-15 | 2019-10-25 | 2019-10-25 | COMP | 2021-08-20 | COMP | 2021-11-04 | COMP | 2021-11-05 | COMP | 2022-01-26 | COMP | Rule 15/16 | 55 | 177 | 458 | 54 | 2 | 55 | 796
9909 | 2018-11-28 | 2019-02-22 | 2019-05-16 | 2019-05-16 | COMP | 2020-02-13 | COMP | 2020-06-09 | COMP | 2023-09-02 | INPR | 2020-07-24 | COMP | Rule 16 | 59 | 60 | 187 | 82 |  |  | 418
9920 | 2018-11-28 | 2019-02-22 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-26 | COMP | 2019-05-23 | COMP | 2019-05-13 | COMP | 2019-06-22 | COMP | Rule 16 | 59 | 30 | 17 | 20 | 0 | 21 | 143
10001 | 2018-11-28 | 2019-02-26 | 2019-04-29 | 2019-04-29 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2021-04-03 | COMP | 2021-05-13 | COMP | Rule 16 | 61 | 45 | 65 | 1 | 422 | 29 | 619
10183 | 2018-11-28 | 2019-03-05 | 2019-07-17 | 2019-07-17 | COMP | 2019-09-03 | COMP | 2019-09-25 | COMP | 2020-04-29 | COMP | 2020-06-02 | COMP | Rule 16 | 66 | 95 | 34 | 17 | 149 | 24 | 380
10326 | 2018-11-28 | 2019-03-11 | 2019-06-04 | 2019-06-04 | COMP | 2019-06-27 | COMP | 2020-01-10 | COMP | 2021-02-27 | INPR | 2020-02-01 | COMP | Rule 16 | 70 | 61 | 18 | 135 |  |  | 295
10743 | 2018-11-28 | 2019-03-28 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-16 | COMP | 2019-08-26 | COMP | 2019-08-30 | COMP | 2019-09-16 | COMP | Rule 16 | 83 | 56 | 22 | 30 | 5 | 11 | 202
11180 | 2018-11-28 | 2019-04-16 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-07 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-10-03 | COMP | Rule 16 | 96 | 72 | 8 | 20 | 1 | 22 | 215
11598 | 2018-11-28 | 2019-05-03 | 2019-08-15 | 2019-08-15 | COMP | 2019-08-26 | COMP | 2019-10-10 | COMP | 2019-10-18 | COMP | 2019-12-10 | COMP | Rule 16 | 109 | 73 | 8 | 33 | 7 | 35 | 260
11972 | 2018-11-28 | 2019-05-20 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | Rule 16 | 120 | 29 | 13 | 1 | 16 | 1 | 175
12621 | 2018-11-28 | 2019-06-17 | 2019-08-16 | 2020-12-09 | COMP | 2020-12-17 | COMP | 2020-12-17 | COMP | 2020-12-29 | COMP | 2021-02-16 | COMP | Rule 16 | 139 | 44 | 7 | 1 | 8 | 33 | 557
13471 | 2018-11-28 | 2019-07-26 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-29 | COMP | 2020-05-31 | COMP | 2020-09-01 | COMP | 2021-01-12 | COMP | Rule 16 | 167 | 173 | 19 | 22 | 67 | 90 | 534
13581 | 2018-11-28 | 2019-07-31 | 2019-12-27 | 2019-12-27 | COMP | 2020-01-16 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-04-15 | COMP | Rule 16 | 170 | 103 | 14 | 42 | 1 | 22 | 347
4090 | 2018-11-29 | 2019-01-22 | 2019-04-01 | 2019-04-01 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-07-30 | COMP | Rule 16 | 36 | 49 | 47 | 6 | 1 | 34 | 168
8438 | 2018-11-29 | 2018-12-03 | 2019-02-13 | 2019-02-13 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-04-03 | COMP | 2019-05-30 | COMP | Other | 3 | 50 | 39 | 1 | 0 | 37 | 126
8514 | 2018-11-29 | 2018-12-06 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-29 | COMP | 2019-05-23 | COMP | 2019-05-08 | COMP | 2019-06-14 | COMP | Rule 16 | 6 | 61 | 39 | 19 | 0 | 16 | 137
8548 | 2018-11-29 | 2018-12-07 | 2019-01-03 | 2019-01-03 | COMP | 2019-03-05 | COMP | 2019-03-12 | COMP | 2019-07-21 | INPR | 2019-04-10 | COMP | Rule 16 | 7 | 18 | 42 | 6 |  |  | 91
8566 | 2018-11-29 | 2018-12-11 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-25 | COMP | 2019-03-27 | COMP | 2019-03-25 | COMP | 2019-05-02 | COMP | Rule 16 | 9 | 58 | 14 | 3 | 0 | 27 | 107
8652 | 2018-11-29 | 2018-12-14 | 2019-01-25 | 2019-01-25 | COMP | 2019-01-30 | COMP | 2019-02-05 | COMP | 2019-09-02 | INPR | 2019-04-20 | COMP | Rule 16 | 12 | 28 | 4 | 5 |  |  | 98
8689 | 2018-11-29 | 2018-12-17 | 2019-05-06 | 2019-05-06 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2020-05-11 | COMP | 2020-06-18 | COMP | Rule 15/16 | 13 | 97 | 131 | 1 | 126 | 28 | 391
8790 | 2018-11-29 | 2018-12-27 | 2019-09-19 | 2019-09-19 | COMP | 2019-09-26 | COMP | 2019-10-29 | COMP | 2019-12-03 | COMP | 2019-12-14 | COMP | Rule 15/16 | 20 | 185 | 6 | 24 | 23 | 9 | 262
8951 | 2018-11-29 | 2019-01-09 | 2019-04-09 | 2019-07-15 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-09 | COMP | 2019-10-22 | COMP | Rule 15/16 | 28 | 63 | 61 | 1 | 2 | 10 | 227
8998 | 2018-11-29 | 2019-01-11 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-11 | COMP | 2019-03-12 | COMP | 2019-03-25 | COMP | 2019-04-24 | COMP | Rule 16 | 30 | 35 | 6 | 2 | 10 | 23 | 101
9122 | 2018-11-29 | 2019-01-17 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2020-03-21 | INPR | 2019-11-21 | COMP | Rule 16 | 34 | 92 | 37 | 1 |  |  | 248
9173 | 2018-11-29 | 2019-01-20 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-09-04 | COMP | 2019-10-15 | COMP | Rule 15/16 | 35 | 44 | 41 | 1 | 75 | 30 | 222
9240 | 2018-11-29 | 2019-01-23 | 2019-02-03 | 2019-02-03 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-04-16 | COMP | 2019-04-23 | COMP | Rule 16 | 37 | 8 | 31 | 1 | 21 | 6 | 100
9370 | 2018-11-29 | 2019-02-01 | 2019-04-20 | 2019-04-20 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2020-02-06 | COMP | 2020-02-26 | COMP | Rule 16 | 44 | 55 | 32 | 1 | 169 | 14 | 311
9443 | 2018-11-29 | 2019-02-04 | 2019-02-26 | 2019-02-26 | COMP | 2019-03-01 | COMP | 2019-03-01 | COMP | 2019-06-21 | COMP | 2019-07-09 | COMP | Rule 16 | 45 | 16 | 4 | 1 | 80 | 12 | 153
9983 | 2018-11-29 | 2019-02-25 | 2019-03-19 | 2019-03-19 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-08-07 | COMP | 2019-09-11 | COMP | Rule 16 | 59 | 17 | 90 | 1 | 11 | 25 | 198
10117 | 2018-11-29 | 2019-03-04 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-08 | COMP | 2019-05-31 | COMP | 2019-05-29 | COMP | 2019-07-05 | COMP | Rule 15/16 | 64 | 20 | 29 | 17 | 0 | 25 | 151
10636 | 2018-11-29 | 2019-03-23 | 2019-06-05 | 2019-06-05 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-03-16 | COMP | 2020-03-23 | COMP | Rule 16 | 78 | 52 | 179 | 1 | 17 | 6 | 329
10875 | 2018-11-29 | 2019-04-03 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-30 | COMP | 2019-06-17 | COMP | 2021-05-26 | COMP | 2021-07-21 | COMP | Rule 16 | 86 | 33 | 9 | 13 | 490 | 39 | 665
10939 | 2018-11-29 | 2019-04-06 | 2019-07-17 | 2019-07-17 | COMP | 2022-02-18 | COMP | 2022-02-18 | COMP | 2022-11-30 | COMP | 2023-04-19 | COMP | Rule 16 | 88 | 71 | 654 | 1 | 196 | 97 | 1103
11074 | 2018-11-29 | 2019-04-11 | 2019-07-17 | 2019-08-12 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-12-10 | COMP | 2019-12-18 | COMP | Rule 16 | 92 | 68 | 32 | 1 | 52 | 7 | 265
11109 | 2018-11-29 | 2019-04-12 | 2019-06-08 | 2019-06-08 | COMP | 2019-06-25 | COMP | 2019-09-05 | COMP | 2019-09-06 | COMP | 2019-09-17 | COMP | Rule 16 | 93 | 40 | 12 | 51 | 2 | 8 | 202
11232 | 2018-11-29 | 2019-04-18 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2023-01-28 | INPR | 2019-06-25 | COMP | Rule 16 | 97 | 27 | 18 | 1 |  |  | 144
11471 | 2018-11-29 | 2019-04-29 | 2019-09-20 | 2019-10-02 | COMP | 2019-10-08 | COMP | 2019-12-13 | COMP | 2020-04-08 | COMP | 2020-04-10 | COMP | Rule 15/16 | 104 | 102 | 5 | 46 | 80 | 3 | 343
11712 | 2018-11-29 | 2019-05-08 | 2019-10-02 | 2019-10-07 | COMP | 2019-12-13 | COMP | 2020-01-06 | COMP | 2020-01-29 | COMP | 2020-03-05 | COMP | Rule 15/16 | 111 | 103 | 47 | 15 | 17 | 26 | 317
11832 | 2018-11-29 | 2019-05-14 | 2019-10-10 | 2019-10-10 | COMP | 2019-12-02 | NOTN | 2019-12-17 | COMP | 2019-12-03 | COMP | 2020-02-04 | COMP | Other | 115 | 105 |  | 46 | 0 | 33 | 296
11920 | 2018-11-29 | 2019-05-16 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-08 | COMP | 2019-09-11 | COMP | 2019-08-28 | COMP | 2019-11-18 | COMP | Rule 16 | 117 | 50 | 9 | 24 | 0 | 48 | 245
11990 | 2018-11-29 | 2019-05-20 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2019-11-21 | COMP | 2020-01-08 | COMP | Rule 16 | 119 | 92 | 31 | 1 | 9 | 31 | 278
12064 | 2018-11-29 | 2019-05-21 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-11-20 | COMP | 2020-01-08 | COMP | Rule 16 | 120 | 91 | 37 | 1 | 2 | 32 | 278
12272 | 2018-11-29 | 2019-05-30 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-31 | COMP | 2019-11-25 | COMP | 2020-05-26 | COMP | 2020-06-04 | COMP | Rule 16 | 126 | 90 | 19 | 17 | 125 | 8 | 381
12277 | 2018-11-29 | 2019-05-30 | 2019-08-13 | 2020-09-23 | COMP | 2020-10-27 | COMP | 2021-01-27 | COMP | 2021-01-28 | COMP | 2021-06-15 | COMP | Rule 15/16 | 126 | 53 | 25 | 61 | 2 | 97 | 640
12496 | 2018-11-29 | 2019-06-10 | 2019-10-19 | 2019-10-19 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-03-23 | COMP | Rule 16 | 133 | 93 | 74 | 1 | 1 | 31 | 329
12869 | 2018-11-29 | 2019-06-26 | 2019-07-02 | 2019-07-15 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-10-03 | COMP | 2019-09-30 | COMP | Rule 16 | 145 | 5 | 11 | 1 | 48 |  | 211
13133 | 2018-11-29 | 2019-07-11 | 2019-10-11 | 2020-08-18 | COMP | 2021-11-03 | COMP | 2022-02-08 | COMP | 2022-01-20 | COMP | 2022-03-03 | COMP | Rule 16 | 155 | 66 | 306 | 66 | 0 | 17 | 820
13198 | 2018-11-29 | 2019-07-15 | 2019-12-13 | 2019-12-13 | COMP | 2020-03-25 | COMP | 2020-06-05 | COMP | 2022-03-16 | COMP | 2022-06-14 | COMP | Rule 16 | 157 | 106 | 70 | 52 | 448 | 64 | 892
13271 | 2018-11-29 | 2019-07-18 | 2019-12-24 | 2019-12-24 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-11-02 | COMP | 2020-11-16 | COMP | Rule 16 | 160 | 110 | 162 | 1 | 58 | 10 | 496
13391 | 2018-11-29 | 2019-07-24 | 2019-11-06 | 2019-11-06 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2022-04-19 | COMP | 2022-05-09 | COMP | Rule 15/16 | 164 | 75 | 189 | 1 | 428 | 15 | 867
14160 | 2018-11-29 | 2019-08-28 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2022-07-16 | INPR | 2020-06-30 | COMP | Rule 15/16 | 189 | 7 | 6 | 1 |  |  | 399
15867 | 2018-11-29 | 2019-11-26 | 2020-01-30 | 2020-01-30 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-04-07 | COMP | 2020-07-28 | COMP | Rule 16 | 251 | 43 | 39 | 1 | 10 | 80 | 419
22175 | 2018-11-29 | 2020-09-14 | 2020-11-06 | 2020-11-06 | COMP | 2020-12-29 | COMP | 2020-12-30 | COMP | 2022-12-22 | COMP | 2023-02-06 | COMP | Rule 16 | 452 | 40 | 34 | 2 | 499 | 30 | 1052
4152 | 2018-11-30 | 2019-04-16 | 2019-04-25 | 2019-04-25 | COMP | 2019-08-13 | COMP | 2019-09-06 | COMP | 2019-10-02 | COMP | 2019-11-20 | COMP | Other | 94 | 8 | 77 | 18 | 19 | 35 | 246
8499 | 2018-11-30 | 2018-12-05 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-04-30 | COMP | 2019-05-14 | COMP | Rule 16 | 4 | 80 | 21 | 1 | 2 | 11 | 114
8682 | 2018-11-30 | 2018-12-15 | 2019-02-15 | 2019-02-15 | COMP | 2019-03-05 | COMP | 2019-03-05 | COMP | 2019-07-21 | INPR | 2019-04-12 | COMP | Rule 15/16 | 11 | 42 | 12 | 1 |  |  | 92
8744 | 2018-11-30 | 2018-12-21 | 2019-08-20 | 2019-08-20 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-07-16 | COMP | 2020-08-13 | COMP | Rule 15/16 | 16 | 167 | 92 | 1 | 138 | 21 | 430
8745 | 2018-11-30 | 2018-12-21 | 2019-07-26 | 2019-10-03 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-07-16 | COMP | 2020-08-11 | COMP | Rule 15/16 | 16 | 150 | 61 | 1 | 138 | 19 | 428
8829 | 2018-11-30 | 2019-01-02 | 2019-02-26 | 2019-02-26 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | 2019-05-24 | COMP | 2019-06-19 | COMP | Rule 16 | 22 | 38 | 46 | 3 | 17 | 18 | 139
9297 | 2018-11-30 | 2019-01-28 | 2019-03-26 | 2019-03-26 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2019-09-16 | COMP | 2019-10-07 | COMP | Rule 16 | 39 | 41 | 58 | 1 | 65 | 16 | 215
9339 | 2018-11-30 | 2019-01-30 | 2019-03-25 | 2019-03-25 | COMP | 2019-05-02 | COMP | 2019-08-01 | COMP | 2019-11-12 | COMP | 2019-12-16 | COMP | Rule 16 | 41 | 38 | 29 | 64 | 72 | 23 | 262
9809 | 2018-11-30 | 2019-02-19 | 2019-03-27 | 2019-03-27 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2019-05-16 | COMP | 2019-06-21 | COMP | Rule 16 | 54 | 27 | 29 | 1 | 9 | 26 | 141
9923 | 2018-11-30 | 2019-02-22 | 2019-05-06 | 2019-06-20 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-12-29 | INPR | 2019-08-29 | COMP | Rule 15/16 | 57 | 52 | 20 | 1 |  |  | 189
10051 | 2018-11-30 | 2019-02-28 | 2019-05-03 | 2019-05-03 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-10-30 | COMP | 2020-03-30 | COMP | Rule 15/16 | 61 | 47 | 56 | 1 | 71 | 102 | 333
10407 | 2018-11-30 | 2019-03-14 | 2019-05-24 | 2019-05-24 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2020-05-31 | INPR | 2019-11-18 | COMP | Rule 16 | 71 | 52 | 95 | 1 |  |  | 244
10612 | 2018-11-30 | 2019-03-22 | 2019-05-30 | 2019-05-30 | COMP | 2019-06-11 | COMP | 2019-08-12 | COMP | 2019-06-12 | COMP | 2019-09-13 | COMP | Rule 16 | 77 | 49 | 9 | 44 | 0 | 24 | 199
10781 | 2018-11-30 | 2019-03-29 | 2019-07-17 | 2019-07-17 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-08-04 | COMP | 2020-10-16 | COMP | Rule 16 | 82 | 77 | 89 | 1 | 178 | 53 | 475
11314 | 2018-11-30 | 2019-04-23 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-12-11 | COMP | 2019-09-03 | COMP | Rule 16 | 99 | 41 | 31 | 1 | 91 |  | 191
11613 | 2018-11-30 | 2019-05-06 | 2019-09-23 | 2019-09-23 | COMP | 2022-03-24 | COMP | 2020-04-17 | COMP | 2020-04-20 | COMP | 2020-06-01 | COMP | Rule 16 | 108 | 98 | 630 |  | 2 | 30 | 377
11683 | 2018-11-30 | 2019-05-07 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-11 | COMP | 2019-10-23 | COMP | 2023-09-02 | INPR | 2019-12-04 | COMP | Rule 16 | 109 | 58 | 32 | 31 |  |  | 254
11989 | 2018-11-30 | 2019-05-20 | 2019-08-07 | 2019-08-07 | COMP | 2019-09-23 | COMP | 2020-11-16 | COMP | 2021-06-23 | COMP | 2021-08-04 | COMP | Rule 16 | 118 | 56 | 33 | 291 | 151 | 30 | 674
12882 | 2018-11-30 | 2019-06-26 | 2019-11-06 | 2019-11-06 | COMP | 2021-03-04 | COMP | 2021-03-08 | COMP | 2021-03-04 | COMP | 2021-04-12 | COMP | Rule 16 | 144 | 94 | 331 | 3 | 0 | 26 | 594
13613 | 2018-11-30 | 2019-08-01 | 2019-12-17 | 2019-12-17 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-04-02 | COMP | 2020-07-29 | COMP | Rule 16 | 169 | 95 | 58 | 1 | 17 | 84 | 419
13614 | 2018-11-30 | 2019-08-01 | 2020-02-15 | 2020-05-15 | COMP | 2021-05-18 | COMP | 2021-05-24 | COMP | 2022-06-28 | COMP | 2022-07-03 | COMP | Rule 16 | 169 | 135 | 254 | 5 | 277 | 4 | 903
14582 | 2018-11-30 | 2019-09-17 | 2020-03-23 | 2020-05-08 | COMP | 2020-09-04 | COMP | 2021-11-22 | COMP | 2022-02-23 | COMP | 2022-03-11 | COMP | Rule 15/16 | 201 | 128 | 85 | 305 | 64 | 13 | 825
15460 | 2018-11-30 | 2019-11-02 | 2020-02-21 | 2020-02-21 | COMP | 2020-02-27 | COMP | 2020-05-16 | COMP | 2020-09-04 | COMP | 2020-10-05 | COMP | Rule 16 | 234 | 73 | 5 | 57 | 79 | 21 | 466
9183 | 2018-12-01 | 2019-01-20 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-03-07 | COMP | 2019-05-06 | COMP | Rule 16 | 33 | 27 | 6 | 1 | 1 | 43 | 107
9265 | 2018-12-01 | 2019-01-25 | 2019-04-16 | 2019-07-02 | COMP | 2019-08-22 | COMP | 2019-11-20 | COMP | 2020-10-16 | COMP | 2021-03-15 | COMP | Rule 16 | 37 | 57 | 37 | 63 | 230 | 100 | 573
11094 | 2018-12-01 | 2019-04-11 | 2019-09-01 | 2019-09-01 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2019-11-04 | COMP | 2020-01-21 | COMP | Rule 16 | 90 | 100 | 48 | 1 | 0 | 48 | 284
12952 | 2018-12-01 | 2019-07-02 | 2019-11-04 | 2019-11-04 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-02-24 | COMP | 2020-04-10 | COMP | Rule 16 | 147 | 88 | 11 | 1 | 64 | 35 | 341
10453 | 2018-12-02 | 2019-03-18 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-01 | COMP | 2019-05-06 | COMP | 2019-06-09 | COMP | 2019-07-02 | COMP | Rule 16 | 72 | 14 | 20 | 4 | 24 | 17 | 147
8719 | 2018-12-03 | 2018-12-19 | 2019-01-14 | 2019-01-14 | COMP | 2019-01-14 | NOTN | 2019-01-14 | COMP | 2019-05-17 | COMP | 2019-07-29 | COMP | Other | 13 | 17 |  | 1 | 88 | 50 | 165
8839 | 2018-12-03 | 2018-12-31 | 2019-03-20 | 2019-03-20 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2020-08-17 | COMP | 2020-09-24 | COMP | Rule 16 | 20 | 55 | 48 | 1 | 311 | 28 | 458
8904 | 2018-12-03 | 2019-01-04 | 2019-03-06 | 2019-03-06 | COMP | 2019-06-11 | COMP | 2019-06-20 | COMP | 2019-07-02 | COMP | 2019-07-01 | COMP | Rule 16 | 23 | 42 | 69 | 8 | 9 |  | 146
8936 | 2018-12-03 | 2019-01-08 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-03 | COMP | 2019-04-04 | COMP | 2019-04-03 | COMP | 2019-04-29 | COMP | Rule 16 | 25 | 54 | 7 | 2 | 0 | 18 | 102
8958 | 2018-12-03 | 2019-01-09 | 2020-03-30 | 2021-03-08 | COMP | 2021-05-24 | COMP | 2022-01-27 | COMP | 2022-04-01 | COMP | 2022-05-02 | COMP | Rule 15/16 | 26 | 307 | 56 | 172 | 46 | 22 | 860
9099 | 2018-12-03 | 2019-01-16 | 2019-04-13 | 2019-04-13 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-05-24 | COMP | 2019-06-26 | COMP | Rule 16 | 31 | 61 | 10 | 1 | 21 | 23 | 143
9165 | 2018-12-03 | 2019-01-18 | 2019-05-30 | 2019-05-30 | COMP | 2019-07-30 | COMP | 2019-08-08 | COMP | 2019-12-19 | COMP | 2019-12-28 | COMP | Rule 15/16 | 33 | 92 | 43 | 8 | 92 | 6 | 269
9234 | 2018-12-03 | 2019-01-23 | 2019-05-08 | 2019-05-08 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2022-09-27 | COMP | 2022-11-04 | COMP | Rule 16 | 35 | 75 | 64 | 1 | 791 | 29 | 990
9285 | 2018-12-03 | 2019-01-27 | 2019-08-21 | 2019-08-22 | COMP | 2019-09-06 | COMP | 2020-01-13 | COMP | 2023-04-30 | INPR | 2020-04-22 | COMP | Rule 15/16 | 37 | 145 | 11 | 87 |  |  | 349
9286 | 2018-12-03 | 2019-01-27 | 2019-09-12 | 2019-09-12 | COMP | 2019-10-11 | COMP | 2020-08-12 | COMP | 2020-10-05 | COMP | 2020-12-22 | COMP | Rule 15/16 | 37 | 160 | 22 | 211 | 38 | 54 | 518
9296 | 2018-12-03 | 2019-01-28 | 2019-03-19 | 2019-05-01 | COMP | 2019-08-15 | COMP | 2019-09-18 | COMP | 2019-09-23 | COMP | 2019-11-07 | COMP | Rule 16 | 38 | 36 | 75 | 24 | 4 | 34 | 237
9310 | 2018-12-03 | 2019-01-28 | 2019-04-30 | 2019-08-26 | COMP | 2019-09-09 | COMP | 2019-09-12 | COMP | 2019-05-20 | COMP | 2019-10-07 | COMP | Rule 16 | 38 | 66 | 10 | 4 | 0 | 18 | 214
9534 | 2018-12-03 | 2019-02-07 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-17 | COMP | 2019-06-19 | COMP | 2020-01-25 | COMP | 2020-02-24 | COMP | Rule 16 | 46 | 67 | 25 | 3 | 150 | 20 | 307
9536 | 2018-12-03 | 2019-02-07 | 2019-04-04 | 2019-04-04 | COMP | 2019-11-07 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-01-13 | COMP | Rule 15/16 | 46 | 40 | 153 | 13 | 1 | 31 | 279
9542 | 2018-12-03 | 2019-02-06 | 2019-06-10 | 2019-06-14 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2021-02-18 | COMP | 2021-05-10 | COMP | Rule 16 | 45 | 87 | 20 | 1 | 403 | 58 | 613
9919 | 2018-12-03 | 2019-02-22 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-25 | COMP | 2019-05-07 | COMP | 2019-08-10 | COMP | 2019-07-31 | COMP | Rule 16 | 56 | 41 | 5 | 9 | 67 |  | 167
10393 | 2018-12-03 | 2019-03-14 | 2019-07-04 | 2019-07-04 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-07-23 | COMP | 2019-08-24 | COMP | Rule 16 | 70 | 79 | 9 | 1 | 5 | 24 | 184
10507 | 2018-12-03 | 2019-03-19 | 2019-06-19 | 2021-08-21 | COMP | 2021-09-02 | COMP | 2021-12-06 | COMP | 2021-11-22 | COMP | 2021-12-06 | COMP | Rule 15/16 | 73 | 66 | 9 | 64 | 0 | 1 | 757
10982 | 2018-12-03 | 2019-04-08 | 2019-10-15 | 2019-10-15 | COMP | 2020-02-26 | COMP | 2020-03-23 | COMP | 2020-12-18 | COMP | 2021-02-17 | COMP | Rule 15/16 | 87 | 134 | 90 | 19 | 190 | 40 | 555
11478 | 2018-12-03 | 2019-04-29 | 2019-09-13 | 2019-09-13 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2020-02-29 | INPR | 2019-11-12 | COMP | Rule 15/16 | 102 | 97 | 9 | 1 |  |  | 239
11599 | 2018-12-03 | 2019-05-03 | 2019-06-25 | 2019-06-25 | COMP | 2019-07-15 | COMP | 2019-10-02 | COMP | 2020-06-09 | COMP | 2020-06-18 | COMP | Rule 16 | 106 | 37 | 14 | 57 | 172 | 8 | 389
11720 | 2018-12-03 | 2019-05-08 | 2019-08-30 | 2019-08-30 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2022-12-22 | COMP | 2023-04-10 | COMP | Rule 16 | 109 | 81 | 279 | 1 | 555 | 74 | 1094
12520 | 2018-12-03 | 2019-06-10 | 2019-07-22 | 2019-12-19 | COMP | 2019-12-27 | COMP | 2019-12-11 | COMP | 2020-05-13 | COMP | 2020-06-16 | COMP | Rule 16 | 131 | 30 | 6 |  | 107 | 24 | 387
12524 | 2018-12-03 | 2019-06-11 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-27 | COMP | 2019-10-21 | COMP | 2019-12-23 | COMP | 2020-01-29 | COMP | Rule 16 | 132 | 40 | 38 | 17 | 43 | 25 | 290
12577 | 2018-12-03 | 2019-06-13 | 2019-08-09 | 2019-08-09 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2020-02-15 | COMP | 2020-03-23 | COMP | Rule 16 | 134 | 41 | 30 | 1 | 100 | 25 | 327
13291 | 2018-12-03 | 2019-07-18 | 2019-10-27 | 2020-02-21 | COMP | 2020-02-27 | COMP | 2019-12-06 | NOTN | 2019-12-05 | COMP | 2020-05-18 | COMP | Rule 16 | 158 | 71 | 5 |  |  |  | 367
13912 | 2018-12-03 | 2019-08-15 | 2019-11-21 | 2019-11-21 | COMP | 2019-12-09 | COMP | 2019-12-09 | NOTN | 2019-12-09 | COMP | 2020-01-08 | COMP | Rule 16 | 178 | 69 | 11 |  |  |  | 276
14277 | 2018-12-03 | 2019-09-02 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-19 | COMP | 2020-02-10 | COMP | 2020-10-28 | COMP | 2021-02-12 | COMP | Rule 16 | 189 | 56 | 20 | 35 | 185 | 72 | 553
16816 | 2018-12-03 | 2020-01-16 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-06-03 | COMP | 2020-06-09 | COMP | Rule 16 | 282 | 74 | 9 | 1 | 16 | 5 | 382
16875 | 2018-12-03 | 2020-01-22 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-18 | COMP | 2020-06-28 | COMP | 2020-07-07 | COMP | 2020-10-06 | COMP | Rule 16 | 285 | 80 | 26 | 7 | 7 | 65 | 466
18186 | 2018-12-03 | 2020-03-13 | 2020-09-01 | 2020-09-01 | COMP | 2021-01-22 | COMP | 2021-01-22 | COMP | 2023-04-11 | COMP | 2023-05-19 | COMP | Rule 16 | 321 | 122 | 97 | 1 | 558 | 29 | 1123
8731 | 2018-12-04 | 2018-12-20 | 2019-01-31 | 2019-06-25 | COMP | 2019-07-08 | COMP | 2019-07-09 | COMP | 2019-07-24 | COMP | 2020-06-09 | COMP | Rule 16 | 13 | 28 | 9 | 2 | 12 | 221 | 381
8736 | 2018-12-04 | 2018-12-20 | 2019-01-14 | 2019-01-14 | COMP | 2019-02-26 | COMP | 2019-02-26 | INPR | 2019-02-26 | COMP | 2019-03-08 | COMP | Rule 16 | 13 | 16 | 30 |  |  |  | 65
8780 | 2018-12-04 | 2018-12-26 | 2019-02-26 | 2019-07-12 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-11 | COMP | 2020-04-09 | COMP | Rule 16 | 16 | 42 | 162 | 1 | 5 | 22 | 339
8835 | 2018-12-04 | 2018-12-31 | 2019-04-15 | 2019-04-15 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-09-17 | COMP | 2019-10-03 | COMP | Rule 16 | 19 | 73 | 11 | 1 | 99 | 13 | 211
8875 | 2018-12-04 | 2019-01-03 | 2019-04-20 | 2019-04-20 | COMP | 2019-04-30 | COMP | 2019-05-15 | COMP | 2019-04-30 | COMP | 2019-07-31 | COMP | Rule 16 | 21 | 75 | 7 | 12 | 0 | 54 | 166
9019 | 2018-12-04 | 2019-01-13 | 2019-03-12 | 2019-03-12 | COMP | 2019-05-14 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-08-14 | COMP | Rule 16 | 27 | 40 | 46 | 30 | 1 | 36 | 176
9023 | 2018-12-04 | 2019-01-13 | 2019-02-20 | 2019-02-20 | COMP | 2019-02-22 | NOTN | 2019-03-29 | COMP | 2019-02-27 | COMP | 2019-05-08 | COMP | Other | 27 | 26 |  | 28 | 0 | 29 | 108
9644 | 2018-12-04 | 2019-02-09 | 2019-03-26 | 2019-03-26 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | 2019-08-30 | COMP | Rule 16 | 46 | 31 | 51 | 1 | 6 | 57 | 188
9986 | 2018-12-04 | 2019-02-26 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-03 | NOTN | 2019-05-03 | COMP | 2021-04-21 | COMP | 2021-06-21 | COMP | Other | 57 | 44 |  | 6 | 495 | 43 | 641
10022 | 2018-12-04 | 2019-02-27 | 2019-07-16 | 2019-07-16 | COMP | 2019-08-09 | COMP | 2019-08-16 | COMP | 2019-08-20 | COMP | 2019-09-30 | COMP | Rule 16 | 58 | 98 | 19 | 6 | 3 | 29 | 208
10438 | 2018-12-04 | 2019-03-16 | 2019-05-12 | 2019-05-12 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2020-04-25 | COMP | 2020-05-30 | COMP | Rule 16 | 70 | 40 | 42 | 1 | 199 | 24 | 374
10923 | 2018-12-04 | 2019-04-04 | 2019-08-15 | 2019-08-15 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-29 | COMP | 2020-05-04 | COMP | Rule 16 | 84 | 94 | 97 | 1 | 17 | 68 | 356
11093 | 2018-12-04 | 2019-04-11 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-27 | NOTN | 2019-07-27 | COMP | 2019-07-27 | COMP | 2019-09-05 | COMP | Other | 89 | 56 |  | 19 | 0 | 28 | 191
11122 | 2018-12-04 | 2019-04-13 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2020-01-29 | COMP | 2020-10-01 | COMP | Rule 16 | 90 | 73 | 5 | 1 | 122 | 174 | 462
11378 | 2018-12-04 | 2019-04-24 | 2019-06-29 | 2019-06-29 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-10-10 | COMP | 2019-12-18 | COMP | Rule 16 | 98 | 47 | 37 | 1 | 36 | 47 | 262
11386 | 2018-12-04 | 2019-04-24 | 2019-07-18 | 2022-04-21 | COMP | 2022-06-22 | COMP | 2022-06-28 | COMP | 2022-07-26 | COMP | 2022-08-26 | COMP | Rule 15/16 | 98 | 60 | 43 | 5 | 20 | 24 | 940
11543 | 2018-12-04 | 2019-05-01 | 2019-07-09 | 2019-07-09 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-05-29 | COMP | 2020-07-17 | COMP | Rule 16 | 103 | 48 | 165 | 1 | 61 | 36 | 409
11738 | 2018-12-04 | 2019-05-09 | 2019-08-02 | 2021-04-02 | COMP | 2021-11-22 | COMP | 2021-11-22 | COMP | 2021-11-30 | COMP | 2022-07-18 | COMP | Rule 16 | 109 | 60 | 163 | 1 | 5 | 160 | 911
11884 | 2018-12-04 | 2019-05-15 | 2019-09-20 | 2019-09-20 | COMP | 2020-03-18 | COMP | 2020-06-17 | COMP | 2020-10-27 | COMP | 2020-11-12 | COMP | Rule 16 | 113 | 90 | 122 | 65 | 94 | 12 | 491
12125 | 2018-12-04 | 2019-05-24 | 2019-05-28 | 2019-05-28 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-10-18 | COMP | 2019-09-13 | COMP | Rule 16 | 120 | 2 | 13 | 1 | 90 |  | 197
12131 | 2018-12-04 | 2019-05-23 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2019-10-17 | COMP | 2019-12-05 | COMP | Other | 119 | 95 | 17 | 1 | 0 | 25 | 253
12237 | 2018-12-04 | 2019-05-28 | 2019-09-13 | 2019-09-13 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2020-02-10 | COMP | 2020-07-14 | COMP | Rule 16 | 121 | 77 | 41 | 1 | 61 | 110 | 406
12359 | 2018-12-04 | 2019-06-03 | 2019-06-25 | 2019-06-25 | COMP | 2019-08-16 | COMP | 2019-08-23 | COMP | 2019-12-29 | INPR | 2019-08-26 | COMP | Rule 16 | 125 | 17 | 38 | 6 |  |  | 184
12422 | 2018-12-04 | 2019-06-05 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-07-26 | COMP | 2019-08-21 | COMP | Rule 16 | 127 | 37 | 5 | 1 | 0 | 15 | 181
12692 | 2018-12-04 | 2019-06-18 | 2019-10-16 | 2019-10-16 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-06-29 | COMP | 2020-08-06 | COMP | Rule 16 | 136 | 85 | 149 | 1 | 28 | 29 | 423
13199 | 2018-12-04 | 2019-07-16 | 2019-09-20 | 2019-09-20 | COMP | 2019-10-24 | COMP | 2019-10-08 | INPR | 2022-07-16 | REQD | 2020-06-19 | COMP | Rule 16 | 155 | 48 | 25 |  |  |  | 389
15032 | 2018-12-04 | 2019-10-11 | 2020-10-05 | 2020-10-05 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2020-10-20 | COMP | 2020-12-08 | COMP | Rule 16 | 217 | 248 | 25 | 1 | 0 | 20 | 507
15033 | 2018-12-04 | 2019-10-11 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-22 | COMP | 2020-11-03 | COMP | 2020-10-20 | COMP | 2020-12-16 | COMP | Rule 16 | 217 | 115 | 40 | 116 | 0 | 29 | 513
15034 | 2018-12-04 | 2019-10-11 | 2020-03-02 | 2020-04-02 | COMP | 2020-05-22 | COMP | 2020-11-03 | COMP | 2020-11-20 | COMP | 2021-02-17 | COMP | Rule 15/16 | 217 | 95 | 37 | 116 | 13 | 58 | 554
16273 | 2018-12-04 | 2019-12-18 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-15 | COMP | 2021-08-12 | COMP | 2021-07-28 | COMP | 2021-08-18 | COMP | Rule 16 | 262 | 60 | 23 | 336 | 0 | 5 | 682
17374 | 2018-12-04 | 2020-02-12 | 2020-03-08 | 2020-03-08 | COMP | 2021-03-26 | COMP | 2021-04-05 | COMP | 2021-04-05 | COMP | 2021-05-13 | COMP | Rule 15/16 | 299 | 17 | 266 | 7 | 1 | 29 | 615
17469 | 2018-12-04 | 2020-02-14 | 2021-02-02 | 2021-04-29 | COMP | 2021-05-05 | COMP | 2021-05-17 | COMP | 2023-12-03 | INPR | 2021-05-24 | COMP | Rule 16 | 301 | 244 | 5 | 9 |  |  | 622
20951 | 2018-12-04 | 2020-07-14 | 2021-01-18 | 2021-01-18 | COMP | 2021-01-27 | COMP | 2021-06-22 | COMP | 2021-09-16 | COMP | 2021-10-18 | COMP | Rule 16 | 406 | 128 | 7 | 103 | 61 | 23 | 724
8583 | 2018-12-05 | 2018-12-10 | 2020-02-12 | 2020-02-12 | COMP | 2020-07-21 | COMP | 2020-05-11 | COMP | 2020-05-18 | COMP | 2020-06-09 | COMP | Rule 15/16 | 4 | 295 | 113 |  | 6 | 16 | 380
8692 | 2018-12-05 | 2018-12-17 | 2019-03-14 | 2019-03-14 | COMP | 2019-03-20 | COMP | 2019-04-17 | COMP | 2019-09-17 | COMP | 2019-10-18 | COMP | Rule 15/16 | 9 | 60 | 5 | 21 | 107 | 24 | 221
8715 | 2018-12-05 | 2018-12-18 | 2019-02-23 | 2019-02-23 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-05 | COMP | 2019-07-02 | COMP | Rule 16 | 10 | 45 | 62 | 1 | 11 | 20 | 145
8930 | 2018-12-05 | 2019-01-08 | 2019-04-02 | 2019-04-02 | COMP | 2019-04-11 | COMP | 2019-04-11 | COMP | 2019-09-02 | INPR | 2019-05-10 | COMP | Rule 16 | 23 | 59 | 8 | 1 |  |  | 109
8967 | 2018-12-05 | 2019-01-09 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-23 | COMP | 2019-09-20 | COMP | 2019-08-27 | COMP | 2019-11-01 | COMP | Rule 16 | 24 | 66 | 8 | 106 | 0 | 31 | 231
9025 | 2018-12-05 | 2019-01-13 | 2019-02-04 | 2019-02-04 | COMP | 2019-02-05 | NOTN | 2019-06-07 | COMP | 2019-06-07 | COMP | 2019-07-05 | COMP | Other | 26 | 15 |  | 88 | 1 | 20 | 147
9141 | 2018-12-05 | 2019-01-17 | 2019-02-13 | 2019-02-13 | COMP | 2019-06-11 | COMP | 2019-07-17 | COMP | 2019-06-18 | NOTN | 2019-08-19 | COMP | Rule 16 | 30 | 19 | 83 | 26 |  |  | 178
9163 | 2018-12-05 | 2019-01-18 | 2019-03-29 | 2019-03-29 | COMP | 2020-01-14 | COMP | 2020-01-15 | COMP | 2020-01-16 | COMP | 2020-02-14 | COMP | Rule 16 | 31 | 49 | 200 | 2 | 2 | 21 | 300
9210 | 2018-12-05 | 2019-01-22 | 2019-03-26 | 2019-08-10 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-11-08 | COMP | 2019-12-14 | COMP | Rule 16 | 32 | 45 | 10 | 1 | 55 | 23 | 258
9598 | 2018-12-05 | 2019-02-07 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-28 | COMP | 2019-10-11 | COMP | 2020-02-05 | COMP | 2020-02-25 | COMP | Rule 16 | 44 | 69 | 9 | 97 | 78 | 14 | 306
9649 | 2018-12-05 | 2019-02-11 | 2019-04-03 | 2019-04-03 | COMP | 2019-05-03 | COMP | 2020-10-14 | COMP | 2020-11-24 | COMP | 2020-12-10 | COMP | Rule 16 | 46 | 37 | 23 | 367 | 29 | 11 | 508
9763 | 2018-12-05 | 2019-02-13 | 2019-05-31 | 2019-05-31 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2019-12-11 | COMP | 2020-01-23 | COMP | Rule 16 | 48 | 76 | 138 | 1 | 0 | 25 | 284
9764 | 2018-12-05 | 2019-02-13 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-04 | COMP | 2019-08-31 | COMP | 2019-11-05 | COMP | 2019-12-05 | COMP | Rule 16 | 48 | 63 | 16 | 63 | 46 | 20 | 252
10009 | 2018-12-05 | 2019-02-26 | 2019-07-17 | 2019-08-27 | COMP | 2019-09-19 | COMP | 2019-12-06 | COMP | 2019-07-17 | NOTN | 2020-01-08 | COMP | Rule 15/16 | 56 | 100 | 17 | 54 |  |  | 274
10583 | 2018-12-05 | 2019-03-21 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-17 | COMP | 2019-08-09 | COMP | 2019-06-24 | COMP | 2019-09-16 | COMP | Rule 16 | 73 | 54 | 9 | 39 | 0 | 26 | 197
10783 | 2018-12-05 | 2019-03-29 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-07-23 | COMP | 2019-08-27 | COMP | Rule 16 | 79 | 59 | 22 | 1 | 2 | 26 | 184
10828 | 2018-12-05 | 2019-04-01 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-18 | COMP | 2019-04-29 | COMP | 2019-05-02 | COMP | 2019-05-06 | COMP | Rule 16 | 80 | 5 | 9 | 8 | 4 | 3 | 105
10847 | 2018-12-05 | 2019-04-02 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-06-11 | COMP | 2019-06-15 | COMP | Rule 16 | 81 | 43 | 7 | 1 | 2 | 4 | 133
11437 | 2018-12-05 | 2019-04-26 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | Rule 16 | 99 | 43 | 7 | 1 | 89 | 1 | 235
11518 | 2018-12-05 | 2019-04-30 | 2019-11-07 | 2019-11-07 | COMP | 2021-02-10 | COMP | 2021-08-16 | COMP | 2021-04-06 | COMP | 2021-09-27 | COMP | Rule 15/16 | 101 | 135 | 315 | 131 | 0 | 30 | 708
11845 | 2018-12-05 | 2019-05-14 | 2019-07-08 | 2019-07-08 | COMP | 2019-08-02 | COMP | 2020-01-29 | COMP | 2019-09-10 | COMP | 2020-02-27 | COMP | Rule 15/16 | 111 | 38 | 20 | 122 | 0 | 21 | 308
12110 | 2018-12-05 | 2019-05-23 | 2019-11-19 | 2020-12-02 | COMP | 2021-04-26 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2021-06-02 | COMP | Rule 15/16 | 118 | 125 | 100 | 20 | 1 | 8 | 627
12377 | 2018-12-05 | 2019-06-04 | 2019-10-12 | 2019-10-12 | COMP | 2020-04-23 | COMP | 2020-04-24 | COMP | 2020-07-16 | COMP | 2020-08-27 | COMP | Rule 16 | 125 | 92 | 132 | 2 | 59 | 31 | 437
13169 | 2018-12-05 | 2019-07-15 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-11-12 | COMP | 2019-11-06 | COMP | Rule 15/16 | 153 | 33 | 19 | 1 | 35 |  | 234
13485 | 2018-12-05 | 2019-07-26 | 2019-08-28 | 2019-09-30 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | Rule 16 | 162 | 24 | 7 | 1 | 10 | 1 | 222
14123 | 2018-12-05 | 2019-08-27 | 2019-12-04 | 2020-07-16 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2020-11-10 | COMP | 2021-03-05 | COMP | Rule 15/16 | 184 | 68 | 108 | 1 | 0 | 52 | 565
14209 | 2018-12-05 | 2019-08-29 | 2019-10-31 | 2019-10-31 | COMP | 2019-12-20 | COMP | 2020-04-06 | COMP | 2020-05-26 | COMP | 2020-04-29 | COMP | Rule 16 | 186 | 45 | 34 | 73 | 36 |  | 352
15833 | 2018-12-05 | 2019-11-22 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-03-09 | COMP | 2020-05-21 | COMP | Rule 16 | 245 | 60 | 8 | 1 | 5 | 54 | 368
16043 | 2018-12-05 | 2019-12-06 | 2020-02-28 | 2020-04-01 | COMP | 2020-08-07 | COMP | 2020-08-28 | COMP |  | INPR | 2020-09-08 | COMP | Rule 16 | 253 | 57 | 92 | 16 |  |  | 444
24021 | 2018-12-05 | 2020-12-08 | 2021-02-18 | 2021-02-18 | COMP | 2021-03-18 | COMP | 2021-03-18 | COMP | 2021-03-29 | COMP | 2021-07-20 | COMP | Rule 15/16 | 506 | 49 | 21 | 1 | 8 | 80 | 660
4158 | 2018-12-06 | 2019-04-22 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-05 | COMP | 2019-09-26 | COMP |  | INPR | 2019-10-12 | COMP | Other | 94 | 93 | 4 | 16 |  |  | 215
8571 | 2018-12-06 | 2018-12-10 | 2019-03-04 | 2019-03-04 | COMP | 2019-04-04 | COMP | 2019-04-04 | COMP | 2019-03-27 | COMP | 2019-04-09 | COMP | Rule 16 | 3 | 57 | 24 | 1 | 0 | 4 | 85
8661 | 2018-12-06 | 2018-12-14 | 2019-03-12 | 2019-03-12 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2019-04-25 | COMP | 2019-06-03 | COMP | Rule 16 | 7 | 59 | 20 | 1 | 14 | 27 | 123
8739 | 2018-12-06 | 2018-12-20 | 2019-01-18 | 2019-01-18 | COMP | 2019-02-06 | COMP | 2019-02-06 | COMP | 2019-03-26 | COMP | 2019-04-05 | COMP | Rule 16 | 11 | 20 | 13 | 1 | 34 | 9 | 83
8867 | 2018-12-06 | 2019-01-03 | 2019-04-09 | 2019-04-09 | COMP | 2019-05-08 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-07-02 | COMP | Rule 15/16 | 19 | 67 | 22 | 15 | 1 | 25 | 144
8906 | 2018-12-06 | 2019-01-05 | 2019-04-15 | 2019-04-15 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-09-05 | COMP | 2019-12-09 | COMP | Rule 15/16 | 20 | 69 | 38 | 1 | 64 | 65 | 253
9034 | 2018-12-06 | 2019-01-14 | 2019-03-18 | 2019-07-31 | COMP | 2019-07-31 | NOTN | 2019-07-31 | COMP | 2019-07-31 | COMP | 2019-09-24 | COMP | Other | 26 | 44 |  | 1 | 1 | 39 | 202
9058 | 2018-12-06 | 2019-01-15 | 2019-03-01 | 2019-04-29 | COMP | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-06-28 | COMP | 2019-08-09 | COMP | Rule 16 | 27 | 32 | 42 | 4 | 0 | 29 | 171
9267 | 2018-12-06 | 2019-01-25 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-25 | COMP | 2019-10-21 | REQD | 2019-10-21 | REQD | 2019-04-30 | COMP | Rule 16 | 34 | 54 | 11 |  |  |  | 100
9350 | 2018-12-06 | 2019-01-31 | 2019-03-08 | 2019-03-08 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-09-03 | COMP | 2019-09-12 | COMP | Rule 16 | 38 | 26 | 17 | 1 | 109 | 8 | 194
9418 | 2018-12-06 | 2019-02-04 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-01 | COMP | 2019-05-20 | COMP | 2019-06-11 | COMP | 2019-06-18 | COMP | Rule 16 | 40 | 52 | 11 | 14 | 16 | 6 | 134
9525 | 2018-12-06 | 2019-02-06 | 2019-06-11 | 2020-10-31 | COMP | 2021-01-08 | COMP | 2022-03-04 | COMP | 2022-03-04 | COMP | 2023-04-14 | COMP | Rule 15/16 | 42 | 88 | 45 | 291 | 1 | 280 | 1095
9594 | 2018-12-06 | 2019-02-08 | 2019-08-24 | 2019-08-24 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2020-05-05 | COMP | 2020-05-28 | COMP | Other | 44 | 138 | 72 | 1 | 103 | 17 | 371
9597 | 2018-12-06 | 2019-02-07 | 2019-07-08 | 2019-07-08 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-07-28 | COMP | 2020-09-18 | COMP | Rule 16 | 43 | 105 | 190 | 1 | 79 | 38 | 451
9698 | 2018-12-06 | 2019-02-11 | 2019-05-06 | 2019-05-06 | COMP | 2019-05-31 | COMP | 2019-06-28 | COMP | 2019-12-29 | INPR | 2019-08-12 | COMP | Rule 16 | 45 | 60 | 19 | 21 |  |  | 172
10042 | 2018-12-06 | 2019-02-28 | 2019-05-03 | 2019-05-03 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-12-29 | INPR | 2019-08-27 | COMP | Rule 16 | 57 | 47 | 23 | 1 |  |  | 183
10187 | 2018-12-06 | 2019-03-05 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-30 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-30 | COMP | Rule 16 | 60 | 54 | 9 | 33 | 1 | 11 | 163
10464 | 2018-12-06 | 2019-03-18 | 2019-04-10 | 2019-04-10 | COMP | 2019-06-05 | COMP | 2019-06-13 | COMP | 2019-06-14 | COMP | 2019-06-19 | COMP | Rule 16 | 69 | 18 | 40 | 7 | 2 | 4 | 135
10799 | 2018-12-06 | 2019-03-29 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-10 | COMP | 2019-09-26 | COMP | 2019-10-08 | COMP | 2019-12-17 | COMP | Rule 16 | 78 | 75 | 41 | 13 | 9 | 48 | 259
10876 | 2018-12-06 | 2019-04-03 | 2019-07-19 | 2019-07-19 | COMP | 2019-08-30 | COMP | 2019-09-16 | COMP | 2019-10-08 | COMP | 2019-10-19 | COMP | Rule 15/16 | 81 | 76 | 31 | 11 | 17 | 9 | 220
11099 | 2018-12-06 | 2019-04-12 | 2019-09-03 | 2019-09-03 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | 2021-02-27 | INPR | 2020-01-31 | COMP | Rule 15/16 | 88 | 100 | 35 | 2 |  |  | 289
11268 | 2018-12-06 | 2019-04-19 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-21 | COMP | 2019-09-03 | COMP | 2019-09-10 | COMP | 2019-09-27 | COMP | Rule 16 | 93 | 50 | 38 | 9 | 6 | 14 | 205
11347 | 2018-12-06 | 2019-04-26 | 2019-08-12 | 2019-08-12 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-01-29 | COMP | Rule 16 | 98 | 75 | 103 | 1 | 1 | 14 | 287
11649 | 2018-12-06 | 2019-05-06 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-10-23 | COMP | 2019-10-31 | COMP | Rule 16 | 104 | 3 | 5 | 1 | 114 | 7 | 229
12140 | 2018-12-06 | 2019-05-24 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2019-09-03 | COMP | 2019-09-25 | COMP | Rule 16 | 118 | 40 | 24 | 1 | 8 | 17 | 203
12334 | 2018-12-06 | 2019-05-31 | 2019-06-25 | 2019-07-22 | COMP | 2019-12-04 | COMP | 2019-12-04 | INPR | 2021-02-27 | REQD | 2020-02-04 | COMP | Rule 16 | 122 | 18 | 94 |  |  |  | 291
12423 | 2018-12-06 | 2019-06-05 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-24 | COMP | 2019-10-30 | COMP | 2020-08-04 | COMP | 2020-08-14 | COMP | Rule 16 | 125 | 87 | 14 | 5 | 192 | 9 | 427
12482 | 2018-12-06 | 2019-06-11 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-24 | COMP | 2019-10-23 | COMP | 2019-11-21 | COMP | 2019-12-06 | COMP | Rule 16 | 129 | 53 | 21 | 22 | 21 | 10 | 252
12706 | 2018-12-06 | 2019-06-19 | 2019-08-28 | 2019-08-28 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-12-02 | COMP | 2020-02-12 | COMP | Rule 16 | 135 | 50 | 64 | 1 | 2 | 50 | 297
13667 | 2018-12-06 | 2019-08-06 | 2020-01-09 | 2020-01-09 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-08-10 | COMP | 2020-10-23 | COMP | Rule 16 | 168 | 107 | 22 | 1 | 129 | 54 | 476
14235 | 2018-12-06 | 2019-08-30 | 2019-12-07 | 2020-03-13 | COMP | 2020-04-10 | COMP | 2020-04-21 | COMP | 2020-04-25 | COMP | 2020-04-30 | COMP | Rule 16 | 186 | 67 | 21 | 8 | 4 | 4 | 352
14637 | 2018-12-06 | 2019-09-20 | 2019-11-09 | 2019-11-09 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-04-26 | INPR | 2020-01-14 | COMP | Rule 16 | 200 | 36 | 15 | 1 |  |  | 277
18091 | 2018-12-06 | 2020-03-10 | 2020-03-12 | 2020-04-07 | COMP | 2020-05-06 | COMP | 2020-05-08 | COMP | 2020-04-14 | COMP | 2020-11-21 | COMP | Rule 15 | 315 | 3 | 22 | 3 | 0 | 138 | 495
18325 | 2018-12-06 | 2020-03-20 | 2020-06-25 | 2021-01-13 | COMP | 2021-02-19 | COMP | 2022-06-02 | COMP | 2022-06-06 | COMP | 2022-07-15 | COMP | Rule 15/16 | 323 | 69 | 26 | 326 | 3 | 28 | 908
19674 | 2018-12-06 | 2020-05-17 | 2020-07-31 | 2020-07-31 | COMP | 2021-03-11 | COMP | 2021-03-30 | COMP | 2022-06-27 | COMP | 2022-10-26 | COMP | Rule 15/16 | 363 | 54 | 152 | 14 | 315 | 86 | 980
40925 | 2018-12-06 | 2023-02-09 | 2023-04-28 | 2023-04-28 | COMP | 2023-06-05 | COMP | 2023-06-05 | COMP | 2023-07-11 | COMP | 2023-08-16 | COMP | Other | 1050 | 56 | 26 | 1 | 25 | 27 | 1180
4078 | 2018-12-07 | 2019-01-10 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-20 | COMP | 2019-10-01 | COMP |  |  | 2020-07-09 | COMP | Rule 16 | 23 | 163 | 15 | 8 |  |  | 400
8785 | 2018-12-07 | 2018-12-27 | 2019-06-18 | 2019-06-18 | COMP | 2019-07-16 | COMP | 2019-09-24 | COMP | 2019-12-03 | COMP | 2019-12-31 | COMP | Rule 15/16 | 14 | 120 | 20 | 50 | 48 | 20 | 267
8813 | 2018-12-07 | 2018-12-31 | 2019-02-26 | 2019-02-26 | COMP | 2019-05-24 | COMP | 2019-05-26 | COMP | 2019-05-28 | COMP | 2019-06-28 | COMP | Rule 16 | 16 | 39 | 64 | 1 | 1 | 24 | 141
8833 | 2018-12-07 | 2018-12-31 | 2019-04-01 | 2019-04-01 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-10-21 | INPR | 2019-07-08 | COMP | Rule 16 | 16 | 63 | 35 | 1 |  |  | 146
8865 | 2018-12-07 | 2019-01-03 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-05-21 | COMP | 2019-06-04 | COMP | Rule 16 | 18 | 71 | 25 | 1 | 3 | 10 | 123
9008 | 2018-12-07 | 2019-01-12 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-23 | COMP | 2019-06-13 | COMP | 2019-05-28 | COMP | 2019-07-17 | COMP | Rule 16 | 24 | 53 | 18 | 37 | 0 | 24 | 153
9051 | 2018-12-07 | 2019-01-14 | 2019-03-07 | 2019-03-07 | COMP | 2019-04-09 | COMP | 2019-04-15 | COMP | 2019-06-29 | COMP | 2019-08-01 | COMP | Rule 16 | 25 | 37 | 24 | 5 | 54 | 23 | 164
9222 | 2018-12-07 | 2019-01-23 | 2019-03-16 | 2019-04-20 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-06-17 | COMP | 2019-07-11 | COMP | Rule 16 | 31 | 37 | 25 | 1 | 16 | 18 | 149
9381 | 2018-12-07 | 2019-01-31 | 2019-03-01 | 2019-03-25 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-04-06 | COMP | 2019-05-07 | COMP | Rule 16 | 37 | 21 | 10 | 1 | 1 | 22 | 104
9567 | 2018-12-07 | 2019-02-07 | 2019-04-24 | 2019-04-24 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2019-05-30 | COMP | 2019-07-07 | COMP | Rule 16 | 42 | 54 | 28 | 1 | 0 | 24 | 145
9607 | 2018-12-07 | 2019-02-08 | 2020-01-18 | 2020-01-24 | COMP | 2020-03-06 | COMP | 2020-03-10 | COMP | 2020-04-21 | COMP | 2020-07-13 | COMP | Rule 16 | 43 | 237 | 30 | 3 | 31 | 59 | 402
9608 | 2018-12-07 | 2019-02-08 | 2020-01-18 | 2020-01-24 | COMP | 2020-03-06 | COMP | 2020-03-25 | COMP | 2020-04-07 | COMP | 2020-05-04 | COMP | Rule 16 | 43 | 237 | 30 | 14 | 10 | 20 | 353
9658 | 2018-12-07 | 2019-02-11 | 2019-05-08 | 2019-06-05 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-06-05 | COMP | 2019-08-06 | COMP | Rule 16 | 44 | 62 | 25 | 1 | 0 | 20 | 167
9861 | 2018-12-07 | 2019-02-20 | 2019-05-01 | 2019-07-15 | COMP | 2019-08-13 | COMP | 2019-09-19 | COMP | 2020-04-07 | COMP | 2020-06-19 | COMP | Rule 15/16 | 50 | 51 | 22 | 27 | 137 | 53 | 386
10198 | 2018-12-07 | 2019-03-06 | 2019-05-18 | 2019-05-18 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2021-01-31 | COMP | 2021-04-16 | COMP | Other | 60 | 53 | 124 | 1 | 304 | 54 | 593
10211 | 2018-12-07 | 2019-03-06 | 2019-04-29 | 2019-04-29 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-08-20 | COMP | 2020-09-28 | COMP | Other | 60 | 39 | 142 | 1 | 192 | 27 | 456
10329 | 2018-12-07 | 2019-03-11 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-20 | COMP | 2019-05-28 | COMP | 2019-06-14 | COMP | 2019-07-12 | COMP | Rule 16 | 63 | 40 | 12 | 6 | 14 | 20 | 150
10413 | 2018-12-07 | 2019-03-14 | 2020-08-26 | 2020-08-26 | COMP | 2020-12-08 | COMP | 2020-12-08 | COMP | 2021-10-31 | COMP | 2022-02-07 | COMP | Rule 15/16 | 66 | 369 | 71 | 1 | 227 | 67 | 797
10523 | 2018-12-07 | 2019-03-19 | 2019-05-15 | 2020-07-07 | COMP | 2020-07-13 | COMP | 2020-09-21 | COMP | 2020-10-14 | COMP | 2020-11-10 | COMP | Rule 16 | 69 | 42 | 5 | 50 | 18 | 20 | 487
10634 | 2018-12-07 | 2019-03-23 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-11-04 | COMP | 2019-09-27 | COMP | Rule 16 | 72 | 63 | 23 | 1 | 74 |  | 204
11028 | 2018-12-07 | 2019-04-09 | 2019-10-19 | 2019-10-19 | COMP | 2019-11-22 | COMP | 2020-02-21 | COMP | 2020-03-01 | COMP | 2020-07-29 | COMP | Rule 16 | 84 | 136 | 24 | 60 | 6 | 107 | 414
11676 | 2018-12-07 | 2019-05-07 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-12 | COMP | 2020-01-13 | COMP | 2020-01-15 | COMP | 2020-02-05 | COMP | Rule 16 | 104 | 57 | 34 | 83 | 3 | 15 | 291
13733 | 2018-12-07 | 2019-08-07 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-19 | NOTN | 2020-01-31 | COMP | 2020-06-10 | COMP | 2020-07-21 | COMP | Other | 168 | 55 |  | 67 | 92 | 30 | 408
14020 | 2018-12-07 | 2019-08-21 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-05 | COMP | 2020-05-31 | REQD | 2019-12-08 | COMP | 2020-01-10 | COMP | Rule 16 | 178 | 71 | 3 |  |  |  | 274
14108 | 2018-12-07 | 2019-08-26 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-17 | COMP | 2019-11-13 | COMP | 2020-08-24 | COMP | 2019-11-25 | COMP | Rule 16 | 181 | 32 | 7 | 19 | 197 |  | 244
14236 | 2018-12-07 | 2019-08-30 | 2019-11-23 | 2019-11-23 | COMP | 2020-01-15 | COMP | 2020-01-15 | COMP | 2020-04-25 | COMP | 2020-05-01 | COMP | Rule 16 | 185 | 59 | 34 | 1 | 71 | 5 | 352
10701 | 2018-12-08 | 2019-03-27 | 2019-04-03 | 2019-04-03 | COMP | 2019-04-23 | COMP | 2019-04-24 | COMP | 2019-04-23 | COMP | 2019-04-22 | COMP | Rule 16 | 74 | 6 | 15 | 2 | 0 |  | 92
13112 | 2018-12-08 | 2019-07-11 | 2019-11-25 | 2020-01-24 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP |  |  | 2020-03-03 | COMP | Rule 16 | 148 | 96 | 8 | 1 |  |  | 308
11548 | 2018-12-09 | 2019-05-02 | 2019-07-27 | 2019-07-27 | COMP | 2021-05-30 | INPR | 2021-05-30 | REQD | 2020-05-04 | COMP | 2020-05-06 | COMP | Rule 16 | 100 | 60 |  |  |  |  | 354
12838 | 2018-12-09 | 2019-06-24 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2022-01-30 | INPR | 2020-07-15 | COMP | Rule 16 | 136 | 74 | 11 | 1 |  |  | 403
4066 | 2018-12-10 | 2019-01-04 | 2019-04-08 | 2019-04-08 | COMP | 2019-05-13 | COMP | 2019-05-15 | COMP | 2019-05-16 | COMP | 2019-06-06 | COMP | Rule 16 | 18 | 65 | 26 | 3 | 2 | 15 | 124
4217 | 2018-12-10 | 2019-08-01 | 2019-08-21 | 2019-08-21 | COMP | 2020-01-18 | REQD | 2019-09-19 | COMP | 2019-10-18 | COMP | 2019-10-01 | COMP | Rule 16 | 163 | 15 |  | 21 | 22 |  | 205
8650 | 2018-12-10 | 2018-12-14 | 2019-02-21 | 2019-02-21 | COMP | 2019-11-19 | COMP | 2019-11-20 | COMP | 2019-11-21 | COMP | 2020-07-07 | COMP | Rule 16 | 5 | 46 | 190 | 2 | 2 | 157 | 397
8709 | 2018-12-10 | 2018-12-18 | 2019-01-23 | 2019-03-13 | COMP | 2019-05-07 | COMP | 2019-02-05 | COMP | 2019-05-06 | COMP | 2019-05-07 | COMP | Rule 16 | 7 | 24 | 40 |  | 64 | 2 | 103
8792 | 2018-12-10 | 2018-12-27 | 2019-01-31 | 2019-02-11 | COMP | 2019-02-26 | COMP | 2019-05-06 | COMP | 2023-11-11 | INPR | 2019-06-04 | COMP | Rule 16 | 13 | 24 | 11 | 50 |  |  | 122
8902 | 2018-12-10 | 2019-01-05 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-16 | NOTN | 2019-03-16 | COMP | 2019-03-16 | COMP | 2019-04-22 | COMP | Other | 18 | 41 |  | 8 | 0 | 26 | 92
9100 | 2018-12-10 | 2019-01-16 | 2019-04-02 | 2019-04-02 | COMP | 2019-06-11 | COMP | 2019-08-23 | COMP | 2020-03-10 | COMP | 2020-04-22 | COMP | Rule 16 | 26 | 53 | 50 | 53 | 135 | 32 | 344
9121 | 2018-12-10 | 2019-01-17 | 2019-03-06 | 2019-03-06 | COMP | 2019-06-04 | COMP | 2020-03-26 | COMP | 2020-03-24 | COMP | 2020-06-03 | COMP | Rule 15/16 | 27 | 33 | 64 | 204 | 0 | 49 | 373
9294 | 2018-12-10 | 2019-01-28 | 2019-03-22 | 2019-03-22 | COMP | 2019-04-16 | COMP | 2019-05-22 | COMP | 2019-05-28 | COMP | 2019-06-13 | COMP | Rule 16 | 33 | 39 | 18 | 27 | 4 | 13 | 129
9306 | 2018-12-10 | 2019-01-28 | 2019-05-30 | 2019-05-30 | COMP | 2019-07-09 | COMP | 2019-08-22 | COMP | 2019-08-15 | COMP | 2019-11-06 | COMP | Rule 15/16 | 33 | 87 | 28 | 33 | 0 | 54 | 231
9576 | 2018-12-10 | 2019-02-08 | 2019-03-26 | 2019-03-26 | COMP | 2019-05-24 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-09-03 | COMP | Rule 16 | 42 | 32 | 44 | 44 | 1 | 27 | 185
9630 | 2018-12-10 | 2019-02-09 | 2019-02-20 | 2019-02-20 | COMP | 2019-02-27 | COMP | 2019-03-26 | COMP | 2019-05-14 | COMP | 2019-05-23 | COMP | Rule 16 | 42 | 7 | 6 | 20 | 36 | 8 | 115
9639 | 2018-12-10 | 2019-02-09 | 2019-06-05 | 2019-06-05 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-05-08 | COMP | 2020-05-27 | COMP | Rule 16 | 42 | 81 | 227 | 1 | 8 | 13 | 368
9802 | 2018-12-10 | 2019-02-16 | 2019-06-14 | 2021-11-16 | COMP | 2021-11-19 | COMP | 2022-03-03 | COMP | 2022-03-15 | COMP | 2022-04-19 | COMP | Rule 16 | 47 | 83 | 4 | 71 | 9 | 26 | 846
9873 | 2018-12-10 | 2019-02-21 | 2019-04-30 | 2019-04-30 | COMP | 2019-09-23 | COMP | 2019-10-04 | COMP | 2019-09-25 | COMP | 2019-11-06 | COMP | Rule 16 | 50 | 49 | 102 | 10 | 0 | 24 | 231
10153 | 2018-12-10 | 2019-03-05 | 2019-05-31 | 2019-05-31 | COMP | 2019-07-18 | COMP | 2019-09-18 | COMP | 2020-04-01 | COMP | 2020-05-19 | COMP | Rule 16 | 58 | 63 | 34 | 44 | 134 | 35 | 363
10248 | 2018-12-10 | 2019-03-07 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-07 | COMP | 2019-07-26 | COMP | 2019-08-21 | COMP | 2019-09-27 | COMP | Rule 15/16 | 60 | 51 | 16 | 35 | 19 | 27 | 203
10313 | 2018-12-10 | 2019-03-11 | 2019-08-09 | 2020-08-05 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2021-01-05 | COMP | 2021-02-26 | COMP | Other | 62 | 108 | 85 | 1 | 20 | 37 | 557
10320 | 2018-12-10 | 2019-03-11 | 2019-08-22 | 2019-11-21 | COMP | 2019-11-19 | NOTN | 2019-11-21 | COMP | 2019-11-26 | COMP | 2020-01-10 | COMP | Other | 62 | 117 |  | 1 | 4 | 30 | 273
10699 | 2018-12-10 | 2019-03-27 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-06 | COMP | 2019-08-07 | COMP | 2019-08-14 | COMP | 2019-08-28 | COMP | Rule 15/16 | 74 | 67 | 27 | 2 | 6 | 11 | 182
11008 | 2018-12-10 | 2019-04-09 | 2019-09-04 | 2019-09-09 | COMP | 2019-10-04 | COMP | 2020-11-12 | COMP | 2020-11-17 | COMP | 2021-01-12 | COMP | Rule 16 | 83 | 104 | 20 | 280 | 4 | 37 | 526
11291 | 2018-12-10 | 2019-04-22 | 2019-07-16 | 2019-07-16 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP |  | INPR | 2019-09-23 | COMP | Rule 16 | 92 | 60 | 32 | 1 |  |  | 199
11324 | 2018-12-10 | 2019-04-23 | 2019-06-28 | 2019-07-01 | COMP | 2019-08-20 | COMP | 2019-09-20 | COMP | 2019-09-04 | COMP | 2019-11-21 | COMP | Rule 16 | 93 | 48 | 36 | 23 | 0 | 44 | 241
11983 | 2018-12-10 | 2019-05-20 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2020-01-19 | INPR | 2019-09-30 | COMP | Rule 16 | 112 | 44 | 12 | 1 |  |  | 204
12094 | 2018-12-10 | 2019-05-23 | 2019-08-07 | 2019-08-07 | COMP | 2019-09-30 | COMP | 2021-08-13 | COMP | 2023-03-29 | COMP | 2023-07-10 | COMP | Rule 16 | 115 | 53 | 38 | 472 | 407 | 71 | 1151
12256 | 2018-12-10 | 2019-05-29 | 2019-07-30 | 2019-07-30 | COMP | 2020-05-05 | COMP | 2020-06-17 | COMP | 2020-09-25 | COMP | 2021-03-23 | COMP | Rule 15/16 | 118 | 44 | 193 | 31 | 72 | 121 | 574
14968 | 2018-12-10 | 2019-10-07 | 2019-10-21 | 2019-10-21 | COMP | 2019-10-29 | COMP | 2019-11-22 | COMP | 2019-11-26 | COMP | 2019-12-20 | COMP | Rule 16 | 209 | 11 | 7 | 18 | 3 | 17 | 260
8735 | 2018-12-11 | 2018-12-20 | 2019-03-04 | 2019-03-04 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2020-01-27 | COMP | 2020-02-07 | COMP | Rule 15/16 | 8 | 49 | 159 | 1 | 69 | 10 | 291
8746 | 2018-12-11 | 2018-12-21 | 2019-11-08 | 2020-04-20 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-04-22 | COMP | 2020-05-15 | COMP | Rule 16 | 9 | 224 | 4 | 1 | 0 | 17 | 360
8783 | 2018-12-11 | 2018-12-24 | 2019-01-26 | 2019-01-26 | COMP | 2019-03-04 | COMP | 2019-03-04 | COMP | 2019-03-05 | COMP | 2019-04-12 | COMP | Rule 16 | 10 | 22 | 25 | 1 | 2 | 29 | 85
8789 | 2018-12-11 | 2018-12-27 | 2019-04-17 | 2019-04-17 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-12-28 | INPR | 2019-08-07 | COMP | Rule 15/16 | 12 | 77 | 52 | 1 |  |  | 166
8901 | 2018-12-11 | 2019-01-05 | 2019-02-20 | 2019-02-20 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2021-08-05 | COMP | 2021-09-21 | COMP | Rule 16 | 17 | 31 | 261 | 1 | 361 | 33 | 700
8907 | 2018-12-11 | 2019-01-05 | 2019-04-12 | 2019-04-12 | COMP | 2019-07-24 | COMP | 2020-08-25 | COMP | 2020-09-09 | COMP | 2020-10-14 | COMP | Rule 16 | 17 | 68 | 72 | 276 | 11 | 26 | 466
8932 | 2018-12-11 | 2019-01-09 | 2019-12-18 | 2019-12-18 | COMP | 2020-04-13 | COMP |  | REQD | 2020-05-06 | COMP | 2020-07-20 | COMP | Rule 15/16 | 20 | 238 | 80 |  |  |  | 405
8935 | 2018-12-11 | 2019-01-08 | 2019-04-17 | 2019-04-17 | COMP | 2019-07-16 | COMP | 2019-07-22 | COMP | 2020-01-18 | COMP | 2020-03-03 | COMP | Rule 16 | 19 | 70 | 63 | 5 | 124 | 30 | 307
8995 | 2018-12-11 | 2019-01-11 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-08-07 | COMP | 2019-08-21 | COMP | Rule 16 | 22 | 45 | 44 | 1 | 58 | 11 | 176
9169 | 2018-12-11 | 2019-01-18 | 2019-06-10 | 2019-06-10 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-02-25 | COMP | 2020-03-11 | COMP | Rule 16 | 27 | 99 | 141 | 1 | 38 | 12 | 313
9185 | 2018-12-11 | 2019-01-20 | 2019-03-26 | 2019-03-26 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-08-14 | COMP | 2019-09-13 | COMP | Rule 16 | 27 | 45 | 69 | 1 | 32 | 22 | 192
9467 | 2018-12-11 | 2019-02-06 | 2019-10-06 | 2019-10-06 | COMP | 2019-10-30 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-01-25 | COMP | Rule 15/16 | 39 | 169 | 18 | 33 | 1 | 25 | 281
9683 | 2018-12-11 | 2019-02-11 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-08 | COMP | 2019-05-21 | COMP | 2019-09-22 | INPR | 2019-06-12 | COMP | Rule 16 | 42 | 34 | 7 | 32 |  |  | 127
9828 | 2018-12-11 | 2019-02-19 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-10 | COMP | 2019-05-22 | COMP | 2019-06-11 | COMP | 2019-08-09 | COMP | Rule 16 | 47 | 44 | 16 | 9 | 14 | 43 | 168
9887 | 2018-12-11 | 2019-02-21 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-14 | COMP | 2020-01-07 | COMP | 2020-03-02 | COMP | 2020-10-30 | COMP | Rule 16 | 49 | 59 | 23 | 141 | 38 | 173 | 478
10040 | 2018-12-11 | 2019-02-28 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-30 | COMP | 2019-06-10 | COMP | 2019-06-04 | COMP | 2019-08-06 | COMP | Rule 16 | 54 | 53 | 13 | 8 | 0 | 41 | 165
10309 | 2018-12-11 | 2019-03-11 | 2019-06-03 | 2019-06-03 | COMP | 2019-06-24 | COMP | 2019-08-28 | COMP | 2019-11-01 | COMP | 2019-12-06 | COMP | Rule 16 | 61 | 60 | 16 | 47 | 47 | 23 | 249
10333 | 2018-12-11 | 2019-03-11 | 2019-04-29 | 2019-04-29 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-07-12 | COMP | 2019-07-31 | COMP | Rule 16 | 61 | 36 | 42 | 1 | 12 | 14 | 161
10429 | 2018-12-11 | 2019-03-15 | 2019-08-02 | 2019-08-02 | COMP | 2019-11-13 | COMP | 2020-04-17 | COMP | 2020-07-31 | COMP | 2020-09-15 | COMP | Rule 16 | 65 | 99 | 72 | 107 | 75 | 32 | 445
10742 | 2018-12-11 | 2019-03-28 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-11 | COMP | 2019-09-06 | COMP | 2019-08-05 | COMP | 2019-09-26 | COMP | Rule 16 | 74 | 66 | 9 | 41 | 0 | 15 | 201
12086 | 2018-12-11 | 2019-05-23 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-14 | COMP | 2019-09-20 | COMP | 2019-10-04 | COMP | 2019-11-08 | COMP | Rule 15/16 | 114 | 47 | 12 | 27 | 11 | 26 | 232
12896 | 2018-12-11 | 2019-06-27 | 2019-09-20 | 2019-09-27 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-06-09 | COMP | 2020-06-13 | COMP | Rule 16 | 138 | 60 | 17 | 1 | 159 | 4 | 379
13079 | 2018-12-11 | 2019-07-09 | 2019-07-16 | 2019-07-16 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-07-19 | COMP | 2019-09-17 | COMP | Rule 16 | 145 | 6 | 5 | 1 | 0 | 41 | 194
13545 | 2018-12-11 | 2019-07-30 | 2020-02-24 | 2020-12-18 | COMP | 2021-04-28 | COMP | 2021-08-12 | COMP | 2022-03-03 | COMP | 2022-08-10 | COMP | Rule 16 | 160 | 142 | 90 | 75 | 140 | 112 | 923
14613 | 2018-12-11 | 2019-09-18 | 2019-12-05 | 2019-12-05 | COMP | 2020-01-29 | COMP | 2020-04-03 | COMP | 2020-06-01 | COMP | 2020-06-12 | COMP | Rule 15/16 | 195 | 54 | 37 | 47 | 41 | 10 | 379
14862 | 2018-12-11 | 2019-10-01 | 2020-03-03 | 2020-03-03 | COMP | 2020-05-27 | COMP | 2020-10-27 | COMP | 2022-01-30 | INPR | 2020-12-10 | COMP | Rule 16 | 204 | 104 | 61 | 109 |  |  | 504
15074 | 2018-12-11 | 2019-10-11 | 2020-02-03 | 2020-02-03 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2023-03-03 | COMP | 2023-05-01 | COMP | Rule 16 | 212 | 76 | 38 | 1 | 739 | 42 | 1103
15448 | 2018-12-11 | 2019-11-01 | 2020-04-06 | 2020-04-06 | COMP | 2020-09-28 | COMP | 2021-01-04 | COMP | 2021-04-06 | COMP | 2021-04-21 | COMP | Rule 15/16 | 227 | 105 | 124 | 66 | 65 | 12 | 594
20091 | 2018-12-11 | 2020-06-04 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-07-30 | COMP | 2020-08-04 | COMP | Rule 16 | 373 | 19 | 6 | 1 | 18 | 4 | 416
4104 | 2018-12-12 | 2019-02-07 | 2019-03-15 | 2019-03-15 | COMP | 2019-06-19 | COMP | 2019-06-24 | COMP | 2019-07-17 | COMP | 2019-07-26 | COMP | Rule 16 | 39 | 26 | 68 | 4 | 17 | 8 | 157
4150 | 2018-12-12 | 2019-04-12 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-29 | COMP | 2019-09-27 | COMP | 2019-12-27 | COMP | 2020-02-03 | COMP | Other | 84 | 55 | 44 | 21 | 62 | 25 | 286
4177 | 2018-12-12 | 2019-05-29 | 2019-11-04 | 2019-11-04 | COMP | 2020-02-12 | COMP | 2020-09-28 | COMP | 2020-10-13 | COMP | 2020-11-13 | COMP | Other | 116 | 112 | 67 | 161 | 12 | 23 | 486
4178 | 2018-12-12 | 2019-05-30 | 2019-07-23 | 2019-07-23 | COMP | 2019-12-20 | COMP | 2020-09-24 | COMP | 2020-10-07 | COMP | 2020-12-03 | COMP | Other | 117 | 38 | 105 | 194 | 10 | 39 | 498
4179 | 2018-12-12 | 2019-05-30 | 2019-11-04 | 2019-11-04 | COMP | 2020-02-18 | COMP | 2020-09-24 | COMP | 2020-10-13 | COMP | 2021-01-28 | COMP | Rule 15 | 117 | 111 | 70 | 156 | 14 | 72 | 535
8872 | 2018-12-12 | 2019-01-03 | 2019-02-14 | 2019-02-14 | COMP | 2019-02-14 | NOTN | 2019-02-14 | COMP | 2019-09-02 | INPR | 2019-03-24 | COMP | Rule 16 | 15 | 30 |  | 1 |  |  | 69
9145 | 2018-12-12 | 2019-01-17 | 2019-03-26 | 2019-03-26 | COMP | 2019-06-10 | COMP | 2019-06-26 | COMP | 2019-07-15 | COMP | 2019-08-05 | COMP | Rule 16 | 25 | 47 | 54 | 13 | 13 | 16 | 163
9295 | 2018-12-12 | 2019-01-28 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-05-29 | COMP | 2019-08-20 | COMP | Rule 16 | 31 | 44 | 44 | 1 | 0 | 58 | 174
9387 | 2018-12-12 | 2019-02-01 | 2019-08-18 | 2020-07-06 | COMP | 2020-07-14 | COMP | 2019-09-04 | COMP | 2020-02-24 | COMP | 2020-08-11 | COMP | Rule 15/16 | 35 | 138 | 7 |  | 117 | 121 | 420
9478 | 2018-12-12 | 2019-02-05 | 2019-06-29 | 2019-07-15 | COMP | 2019-11-27 | COMP | 2019-08-02 | COMP | 2020-01-07 | COMP | 2020-01-17 | COMP | Rule 16 | 37 | 102 | 96 |  | 107 | 9 | 276
9878 | 2018-12-12 | 2019-02-22 | 2019-05-10 | 2019-08-02 | COMP | 2020-05-01 | COMP | 2020-12-31 | COMP | 2021-06-01 | COMP | 2021-07-02 | COMP | Rule 15/16 | 49 | 56 | 188 | 169 | 105 | 24 | 644
10086 | 2018-12-12 | 2019-03-01 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-01 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-07-08 | COMP | Rule 16 | 54 | 33 | 12 | 17 | 1 | 31 | 143
10154 | 2018-12-12 | 2019-03-05 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-13 | COMP | 2019-06-26 | COMP | 2020-03-17 | COMP | 2020-06-04 | COMP | Rule 16 | 56 | 67 | 6 | 10 | 181 | 57 | 372
10793 | 2018-12-12 | 2019-03-30 | 2019-07-15 | 2019-07-15 | COMP | 2019-08-27 | COMP | 2019-09-13 | COMP | 2019-08-27 | COMP | 2019-10-10 | COMP | Rule 15/16 | 74 | 74 | 32 | 13 | 0 | 20 | 210
10980 | 2018-12-12 | 2019-04-07 | 2019-07-27 | 2019-07-28 | COMP | 2019-08-22 | COMP | 2020-01-22 | COMP | 2020-06-01 | COMP | 2020-06-26 | COMP | Rule 16 | 79 | 78 | 19 | 103 | 92 | 20 | 388
11344 | 2018-12-12 | 2019-04-26 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-20 | COMP | 2019-09-18 | COMP | 2019-08-20 | COMP | 2019-10-17 | COMP | Rule 15/16 | 94 | 57 | 25 | 21 | 0 | 22 | 215
11532 | 2018-12-12 | 2019-05-01 | 2019-09-03 | 2019-10-28 | COMP | 2020-11-23 | COMP | 2021-03-01 | COMP | 2022-02-01 | COMP | 2023-04-26 | COMP | Rule 16 | 97 | 87 | 271 | 65 | 235 | 310 | 1099
11626 | 2018-12-12 | 2019-05-06 | 2019-07-23 | 2019-07-23 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-07-26 | COMP | 2019-08-26 | COMP | Rule 16 | 100 | 55 | 5 | 1 | 0 | 21 | 178
11719 | 2018-12-12 | 2019-05-08 | 2019-08-05 | 2019-08-05 | COMP | 2019-10-04 | COMP | 2019-10-10 | COMP | 2019-10-14 | COMP | 2019-11-07 | COMP | Rule 16 | 102 | 62 | 44 | 5 | 3 | 19 | 230
12160 | 2018-12-12 | 2019-05-24 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2020-02-29 | INPR | 2019-11-07 | COMP | Rule 16 | 114 | 34 | 15 | 1 |  |  | 230
12418 | 2018-12-12 | 2019-06-05 | 2019-06-23 | 2019-07-09 | COMP | 2019-07-11 | COMP | 2019-06-27 | INPR | 2019-07-11 | COMP | 2019-07-16 | COMP | Rule 16 | 121 | 13 | 3 |  |  |  | 149
12978 | 2018-12-12 | 2019-07-02 | 2019-12-11 | 2020-01-08 | COMP | 2020-07-10 | COMP | 2020-02-06 | COMP | 2020-07-29 | COMP | 2021-05-21 | COMP | Rule 15/16 | 140 | 112 | 130 |  | 123 | 205 | 615
13260 | 2018-12-12 | 2019-07-17 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-10-16 | COMP | 2019-12-03 | COMP | Rule 16 | 150 | 13 | 19 | 1 | 34 | 32 | 245
13487 | 2018-12-12 | 2019-07-26 | 2019-08-13 | 2019-08-13 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2019-12-10 | COMP | 2020-01-09 | COMP | Other | 157 | 13 | 62 | 1 | 21 | 21 | 270
15170 | 2018-12-12 | 2019-10-16 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2021-03-27 | INPR | 2020-03-09 | COMP | Rule 16 | 214 | 67 | 17 | 1 |  |  | 310
15174 | 2018-12-12 | 2019-10-17 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-17 | COMP | 2019-12-20 | COMP | Rule 16 | 215 | 16 | 13 | 1 | 14 | 4 | 258
15627 | 2018-12-12 | 2019-11-12 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-12 | COMP | 2020-05-20 | INPR |  | REQD | 2020-06-11 | COMP | Rule 16 | 232 | 79 | 47 |  |  |  | 377
15756 | 2018-12-12 | 2019-11-20 | 2020-05-02 | 2020-12-16 | COMP | 2020-12-23 | COMP | 2020-12-30 | COMP | 2020-12-17 | COMP | 2021-01-20 | COMP | Rule 15/16 | 238 | 112 | 6 | 5 | 0 | 14 | 529
15880 | 2018-12-12 | 2019-11-25 | 2020-02-14 | 2020-02-14 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-03-16 | COMP | 2020-06-03 | COMP | Rule 16 | 241 | 55 | 8 | 1 | 14 | 57 | 371
16634 | 2018-12-12 | 2020-01-10 | 2020-02-10 | 2020-02-10 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-06-19 | COMP | Rule 16 | 271 | 21 | 61 | 1 | 1 | 33 | 383
18018 | 2018-12-12 | 2020-03-09 | 2021-01-14 | 2021-01-14 | COMP | 2021-01-29 | COMP | 2021-03-13 | INPR | 2023-12-03 | CANC | 2021-06-10 | COMP | Rule 16 | 310 | 217 | 11 |  |  |  | 628
4067 | 2018-12-13 | 2019-01-06 | 2019-02-19 | 2019-02-19 | COMP | 2019-02-26 | COMP | 2019-03-08 | NOTN | 2019-11-23 | INPR | 2019-07-15 | COMP | Rule 16 | 15 | 30 | 6 |  |  |  | 147
4165 | 2018-12-13 | 2019-05-07 | 2019-08-19 | 2019-08-19 | COMP | 2019-10-08 | COMP | 2019-10-12 | COMP | 2020-10-12 | COMP | 2020-10-21 | COMP | Rule 16 | 100 | 73 | 36 | 4 | 252 | 8 | 469
8871 | 2018-12-13 | 2019-01-03 | 2019-03-13 | 2019-03-13 | COMP | 2019-03-21 | NOTN | 2019-05-06 | COMP | 2019-03-21 | COMP | 2019-06-22 | COMP | Other | 14 | 48 |  | 39 | 0 | 34 | 132
8909 | 2018-12-13 | 2019-01-05 | 2019-03-08 | 2019-03-08 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-03-12 | COMP | 2019-04-03 | COMP | Rule 16 | 15 | 43 | 3 | 1 | 1 | 17 | 76
8955 | 2018-12-13 | 2019-01-09 | 2019-01-25 | 2019-01-25 | COMP | 2019-02-21 | COMP | 2019-02-21 | COMP | 2019-03-12 | COMP | 2019-03-18 | COMP | Rule 16 | 18 | 12 | 19 | 1 | 14 | 5 | 64
9000 | 2018-12-13 | 2019-01-11 | 2019-03-18 | 2019-03-29 | COMP | 2019-04-16 | COMP | 2019-05-07 | COMP | 2019-04-26 | COMP | 2019-05-30 | COMP | Rule 15/16 | 20 | 45 | 13 | 16 | 0 | 17 | 116
9073 | 2018-12-13 | 2019-01-16 | 2019-02-05 | 2019-02-05 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | Rule 16 | 23 | 14 | 170 | 1 | 121 | 2 | 326
9103 | 2018-12-13 | 2019-01-17 | 2019-02-26 | 2019-06-18 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-06-10 | COMP | 2019-06-19 | COMP | Rule 16 | 24 | 27 | 12 | 1 | 0 |  | 130
9107 | 2018-12-13 | 2019-01-17 | 2019-04-08 | 2019-04-08 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-06-24 | COMP | 2019-07-15 | COMP | Rule 16 | 24 | 56 | 45 | 1 | 11 | 15 | 147
9206 | 2018-12-13 | 2019-01-22 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-05 | COMP | 2019-05-01 | COMP | 2019-04-25 | COMP | 2019-06-17 | COMP | Rule 16 | 26 | 44 | 10 | 19 | 0 | 33 | 128
9246 | 2018-12-13 | 2019-01-24 | 2019-06-18 | 2019-06-18 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-05-18 | COMP | 2020-06-20 | COMP | Rule 15/16 | 28 | 102 | 59 | 1 | 173 | 24 | 382
9248 | 2018-12-13 | 2019-01-24 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-07 | COMP | 2020-03-27 | COMP | 2020-01-08 | COMP | 2020-05-01 | COMP | Rule 15/16 | 28 | 236 | 5 | 57 | 0 | 26 | 348
9480 | 2018-12-13 | 2019-02-05 | 2019-04-10 | 2019-04-10 | COMP | 2019-02-05 | NOTN | 2019-04-10 | COMP | 2019-04-10 | COMP | 2019-06-09 | COMP | Other | 36 | 46 |  | 1 | 1 | 42 | 122
9613 | 2018-12-13 | 2019-02-08 | 2019-03-04 | 2019-03-04 | COMP | 2019-03-20 | COMP | 2019-03-20 | INPR | 2022-06-18 | REQD | 2020-02-22 | COMP | Rule 16 | 39 | 16 | 13 |  |  |  | 298
9656 | 2018-12-13 | 2019-02-10 | 2019-05-22 | 2019-05-22 | COMP | 2019-07-26 | COMP | 2019-08-08 | COMP | 2019-11-08 | COMP | 2019-11-27 | COMP | Rule 16 | 39 | 72 | 46 | 10 | 66 | 13 | 242
9846 | 2018-12-13 | 2019-02-20 | 2019-03-01 | 2019-03-04 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-08-26 | COMP | 2019-08-28 | COMP | Rule 16 | 46 | 8 | 16 | 1 | 109 | 3 | 179
10147 | 2018-12-13 | 2019-03-04 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-21 | COMP | 2019-05-31 | COMP | 2019-09-10 | COMP | 2019-10-16 | COMP | Rule 15/16 | 54 | 42 | 16 | 8 | 71 | 27 | 213
10207 | 2018-12-13 | 2019-03-06 | 2019-03-18 | 2019-03-18 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-06-03 | COMP | 2019-07-05 | COMP | Rule 16 | 56 | 9 | 8 | 1 | 48 | 24 | 141
10267 | 2018-12-13 | 2019-03-07 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-13 | COMP | 2019-05-13 | NOTN | 2019-05-13 | COMP | 2019-05-21 | COMP | Rule 16 | 57 | 32 | 17 |  |  |  | 110
10411 | 2018-12-13 | 2019-03-14 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-10-07 | COMP | 2019-11-04 | COMP | Rule 16 | 62 | 136 | 12 | 1 | 0 | 19 | 226
10418 | 2018-12-13 | 2019-03-15 | 2019-04-23 | 2019-04-23 | COMP | 2019-06-06 | COMP | 2019-06-25 | COMP | 2019-05-29 | COMP | 2019-07-11 | COMP | Rule 16 | 63 | 28 | 32 | 14 | 0 | 12 | 145
10428 | 2018-12-13 | 2019-03-15 | 2019-04-17 | 2019-04-17 | COMP | 2019-04-25 | COMP | 2019-06-27 | COMP | 2020-03-16 | COMP | 2020-03-24 | COMP | Rule 16 | 63 | 24 | 7 | 45 | 179 | 7 | 320
10561 | 2018-12-13 | 2019-03-20 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-09-10 | COMP | 2019-10-07 | COMP | Rule 16 | 66 | 55 | 16 | 1 | 53 | 20 | 206
10653 | 2018-12-13 | 2019-03-25 | 2019-08-12 | 2020-01-17 | COMP | 2020-03-30 | COMP | 2020-06-03 | COMP | 2020-04-20 | COMP | 2020-06-07 | COMP | Rule 16 | 69 | 99 | 50 | 47 | 0 | 3 | 372
10654 | 2018-12-13 | 2019-03-25 | 2019-09-26 | 2019-09-26 | COMP | 2020-06-25 | COMP | 2020-06-25 | COMP |  | INPR | 2020-11-13 | COMP | Rule 15/16 | 69 | 131 | 188 | 1 |  |  | 485
10990 | 2018-12-13 | 2019-04-09 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-07-02 | COMP | 2019-09-10 | COMP | Rule 16 | 80 | 12 | 15 | 1 | 35 | 49 | 187
11317 | 2018-12-13 | 2019-04-23 | 2019-05-06 | 2019-05-06 | COMP | 2019-05-15 | COMP | 2019-05-15 | COMP | 2019-06-05 | COMP | 2019-06-14 | COMP | Rule 16 | 90 | 10 | 8 | 1 | 15 | 8 | 127
11811 | 2018-12-13 | 2019-05-13 | 2019-09-05 | 2019-09-05 | COMP | 2019-11-13 | COMP | 2019-11-25 | COMP | 2019-11-13 | COMP | 2019-12-27 | COMP | Rule 16 | 104 | 81 | 49 | 9 | 0 | 22 | 261
11878 | 2018-12-13 | 2019-05-15 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-05 | COMP | 2019-07-05 | INPR | 2020-05-19 | COMP | 2020-06-02 | COMP | Rule 16 | 106 | 16 | 21 |  |  |  | 369
12159 | 2018-12-13 | 2019-05-24 | 2019-07-25 | 2019-07-25 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-11-08 | COMP | 2019-11-18 | COMP | Rule 16 | 113 | 43 | 3 | 1 | 74 | 6 | 235
12257 | 2018-12-13 | 2019-05-29 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-23 | COMP | 2019-08-16 | COMP | Rule 15/16 | 115 | 24 | 5 | 1 | 12 | 19 | 171
12576 | 2018-12-13 | 2019-06-13 | 2019-09-01 | 2019-09-01 | COMP | 2019-11-18 | COMP | 2019-11-19 | COMP | 2019-11-25 | COMP | 2019-12-12 | COMP | Rule 15/16 | 126 | 56 | 54 | 2 | 5 | 12 | 251
12945 | 2018-12-13 | 2019-07-01 | 2019-09-09 | 2019-09-11 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2020-05-13 | COMP | 2020-07-29 | COMP | Rule 16 | 138 | 49 | 31 | 1 | 139 | 55 | 410
14165 | 2018-12-13 | 2019-08-28 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-14 | COMP | 2019-11-15 | COMP | 2020-03-13 | COMP | 2020-03-25 | COMP | Rule 16 | 179 | 44 | 12 | 2 | 80 | 9 | 321
8708 | 2018-12-14 | 2018-12-18 | 2019-06-03 | 2020-09-15 | COMP | 2020-09-25 | COMP | 2020-10-16 | COMP | 2020-06-03 | COMP | 2020-12-18 | COMP | Rule 15/16 | 3 | 115 | 9 | 16 | 0 | 43 | 507
8769 | 2018-12-14 | 2018-12-23 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-15 | COMP | 2019-06-10 | COMP | 2019-08-07 | COMP | 2019-11-13 | COMP | Rule 15/16 | 6 | 67 | 11 | 40 | 42 | 69 | 231
8911 | 2018-12-14 | 2019-01-05 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-25 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-08-21 | COMP | Rule 16 | 14 | 38 | 17 | 80 | 1 | 27 | 173
8941 | 2018-12-14 | 2019-01-08 | 2019-04-14 | 2019-04-14 | COMP | 2019-06-10 | COMP | 2019-11-08 | COMP | 2022-08-06 | INPR | 2019-12-13 | COMP | Rule 16 | 16 | 67 | 40 | 108 |  |  | 251
9146 | 2018-12-14 | 2019-01-18 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-28 | COMP | 2019-08-28 | COMP | 2019-08-09 | COMP | 2019-09-04 | COMP | Rule 16 | 24 | 69 | 22 | 66 | 0 | 5 | 182
9540 | 2018-12-14 | 2019-02-07 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-25 | COMP | 2019-03-25 | COMP | 2019-03-26 | COMP | 2019-06-07 | COMP | Rule 16 | 37 | 29 | 4 | 1 | 2 | 53 | 121
9569 | 2018-12-14 | 2019-02-07 | 2019-02-25 | 2019-02-25 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-04-30 | COMP | 2019-05-02 | COMP | Rule 16 | 37 | 12 | 37 | 1 | 11 | 3 | 96
9848 | 2018-12-14 | 2019-02-20 | 2019-04-09 | 2019-08-29 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-11-22 | COMP | 2020-01-25 | COMP | Rule 16 | 45 | 35 | 41 | 1 | 20 | 41 | 278
9849 | 2018-12-14 | 2019-02-20 | 2019-03-13 | 2019-03-13 | COMP | 2019-06-07 | COMP | 2019-09-20 | COMP | 2019-11-05 | COMP | 2019-12-12 | COMP | Rule 15/16 | 45 | 16 | 62 | 74 | 33 | 25 | 250
9879 | 2018-12-14 | 2019-02-21 | 2019-04-16 | 2019-04-16 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-06-05 | COMP | 2019-06-28 | COMP | Rule 16 | 46 | 39 | 6 | 1 | 31 | 18 | 136
9963 | 2018-12-14 | 2019-02-25 | 2019-03-19 | 2019-03-19 | COMP | 2019-09-04 | COMP | 2019-10-02 | COMP | 2019-09-04 | COMP | 2019-10-11 | COMP | Rule 16 | 48 | 17 | 119 | 21 | 0 | 8 | 209
10164 | 2018-12-14 | 2019-03-05 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | 2019-06-19 | COMP | 2019-08-21 | COMP | Rule 16 | 54 | 37 | 27 | 1 | 14 | 45 | 173
10338 | 2018-12-14 | 2019-03-11 | 2019-06-20 | 2019-06-20 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2019-12-17 | COMP | 2020-01-21 | COMP | Rule 16 | 58 | 73 | 118 | 1 | 7 | 23 | 275
10669 | 2018-12-14 | 2019-03-25 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2020-01-07 | COMP | 2020-07-11 | COMP | Rule 16 | 68 | 128 | 54 | 1 | 19 | 131 | 396
11129 | 2018-12-14 | 2019-04-15 | 2019-06-28 | 2019-08-02 | COMP | 2020-02-19 | COMP | 2020-02-21 | COMP | 2020-02-20 | COMP | 2020-04-21 | COMP | Rule 15/16 | 83 | 54 | 136 | 3 | 0 | 43 | 339
11822 | 2018-12-14 | 2019-05-16 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | Rule 16 | 106 | 29 | 4 | 1 | 7 | 1 | 143
12198 | 2018-12-14 | 2019-05-28 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-12-03 | COMP | 2020-02-13 | COMP | Rule 15/16 | 113 | 52 | 30 | 1 | 51 | 50 | 292
14719 | 2018-12-14 | 2019-09-24 | 2020-02-19 | 2020-02-19 | COMP | 2020-10-07 | COMP | 2020-10-29 | COMP | 2020-12-18 | COMP | 2021-02-03 | COMP | Rule 16 | 196 | 100 | 164 | 17 | 34 | 31 | 537
9180 | 2018-12-15 | 2019-01-20 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-04-29 | COMP | 2019-07-26 | COMP | Rule 16 | 23 | 63 | 15 | 1 | 0 | 54 | 154
8858 | 2018-12-16 | 2019-01-03 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-10 | COMP | 2019-08-06 | COMP | 2019-08-14 | COMP | 2019-09-21 | COMP | Rule 16 | 12 | 93 | 18 | 41 | 7 | 27 | 193
9113 | 2018-12-16 | 2019-01-18 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-11 | COMP | 2019-06-27 | COMP | 2019-08-30 | COMP | 2019-09-09 | COMP | Rule 16 | 23 | 48 | 11 | 55 | 46 | 6 | 184
10346 | 2018-12-16 | 2019-03-12 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-11 | COMP | 2019-04-05 | COMP | 2019-09-02 | INPR | 2019-05-09 | COMP | Rule 16 | 58 | 11 | 13 |  |  |  | 100
13262 | 2018-12-16 | 2019-07-17 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-11-14 | COMP | 2019-12-18 | COMP | Rule 16 | 147 | 51 | 9 | 1 | 27 | 23 | 253
8711 | 2018-12-17 | 2018-12-18 | 2019-01-03 | 2019-01-03 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-30 | COMP | Rule 16 | 2 | 11 | 153 | 1 | 1 | 16 | 179
8798 | 2018-12-17 | 2018-12-28 | 2019-02-19 | 2019-02-19 | COMP | 2019-02-25 | COMP | 2019-05-30 | COMP | 2019-08-28 | COMP | 2019-10-15 | COMP | Rule 16 | 9 | 35 | 5 | 68 | 64 | 34 | 210
8799 | 2018-12-17 | 2018-12-28 | 2020-05-21 | 2020-06-08 | COMP | 2021-06-10 | COMP | 2022-03-15 | COMP | 2022-02-24 | COMP | 2022-04-22 | COMP | Rule 15/16 | 9 | 352 | 255 | 192 | 0 | 29 | 844
8925 | 2018-12-17 | 2019-01-07 | 2019-02-19 | 2019-02-19 | COMP | 2019-03-07 | COMP | 2019-04-26 | COMP | 2019-03-18 | COMP | 2019-06-10 | COMP | Rule 15/16 | 14 | 30 | 13 | 37 | 0 | 31 | 121
8963 | 2018-12-17 | 2019-01-09 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-04-22 | COMP | 2019-05-15 | COMP | Rule 16 | 16 | 52 | 7 | 1 | 15 | 18 | 104
9061 | 2018-12-17 | 2019-01-15 | 2019-02-13 | 2019-02-13 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-04-24 | COMP | 2019-05-20 | COMP | Rule 15/16 | 20 | 21 | 30 | 1 | 21 | 19 | 107
9449 | 2018-12-17 | 2019-02-04 | 2019-05-12 | 2019-05-12 | COMP | 2019-11-12 | COMP | 2019-12-24 | COMP | 2019-12-05 | COMP | 2020-01-15 | COMP | Rule 16 | 33 | 69 | 128 | 29 | 0 | 15 | 271
9493 | 2018-12-17 | 2019-02-06 | 2019-05-23 | 2019-08-15 | COMP | 2019-06-10 | NOTN | 2019-08-15 | COMP | 2019-09-24 | COMP | 2019-10-16 | COMP | Other | 35 | 76 |  | 1 | 28 | 17 | 211
9548 | 2018-12-17 | 2019-02-07 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-26 | COMP | 2019-04-26 | COMP | 2019-04-21 | COMP | 2019-06-18 | COMP | Rule 16 | 36 | 44 | 13 | 1 | 0 | 37 | 127
9646 | 2018-12-17 | 2019-02-11 | 2019-06-11 | 2019-06-11 | COMP | 2019-07-26 | COMP | 2019-07-28 | COMP | 2019-09-24 | COMP | 2019-10-24 | COMP | Rule 15/16 | 38 | 85 | 33 | 1 | 41 | 23 | 217
9700 | 2018-12-17 | 2019-02-12 | 2019-03-15 | 2019-03-15 | COMP | 2019-05-08 | COMP | 2019-05-09 | COMP | 2019-08-13 | COMP | 2019-09-04 | COMP | Rule 16 | 39 | 23 | 39 | 2 | 67 | 16 | 181
9851 | 2018-12-17 | 2019-02-20 | 2019-05-11 | 2019-05-11 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-06-26 | COMP | 2019-07-02 | COMP | Rule 16 | 44 | 58 | 22 | 1 | 11 | 5 | 137
9999 | 2018-12-17 | 2019-02-26 | 2019-06-07 | 2019-06-07 | COMP | 2019-09-05 | COMP | 2019-10-24 | COMP | 2019-10-14 | COMP | 2019-12-05 | COMP | Rule 16 | 48 | 73 | 63 | 36 | 0 | 28 | 244
10247 | 2018-12-17 | 2019-03-07 | 2019-04-29 | 2019-04-29 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2019-07-08 | COMP | 2019-08-30 | COMP | Rule 15/16 | 55 | 38 | 66 | 1 | 0 | 23 | 179
10297 | 2018-12-17 | 2019-03-11 | 2019-06-22 | 2019-07-25 | COMP | 2019-08-08 | COMP | 2019-08-08 | COMP | 2020-02-13 | COMP | 2020-04-02 | COMP | Rule 16 | 57 | 74 | 11 | 1 | 129 | 35 | 325
10307 | 2018-12-17 | 2019-03-11 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-12 | COMP | 2019-08-22 | COMP | 2019-09-10 | COMP | 2019-09-20 | COMP | Rule 16 | 57 | 79 | 31 | 9 | 13 | 9 | 193
10359 | 2018-12-17 | 2019-03-12 | 2019-07-15 | 2019-07-15 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-02 | COMP | 2020-06-11 | COMP | Rule 16 | 58 | 88 | 150 | 1 | 9 | 73 | 374
10627 | 2018-12-17 | 2019-03-22 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2020-06-04 | COMP | 2020-06-10 | COMP | Rule 15/16 | 66 | 28 | 14 | 1 | 264 | 5 | 373
10633 | 2018-12-17 | 2019-03-23 | 2019-06-05 | 2019-07-08 | COMP | 2019-06-17 | NOTN | 2019-07-08 | COMP | 2019-06-17 | COMP | 2019-08-16 | COMP | Other | 66 | 52 |  | 1 | 0 | 30 | 169
10863 | 2018-12-17 | 2019-04-02 | 2019-07-11 | 2019-07-11 | COMP | 2019-10-01 | COMP | 2019-10-01 | COMP | 2019-10-01 | COMP | 2019-12-05 | COMP | Rule 16 | 73 | 71 | 58 | 1 | 1 | 45 | 244
12987 | 2018-12-17 | 2019-07-03 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2020-07-02 | COMP | 2020-07-08 | COMP | Rule 16 | 138 | 59 | 27 | 1 | 168 | 5 | 393
13167 | 2018-12-17 | 2019-07-15 | 2019-12-19 | 2019-12-19 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-03-14 | COMP | 2020-05-13 | COMP | Rule 16 | 145 | 110 | 55 | 1 | 4 | 43 | 354
13629 | 2018-12-17 | 2019-08-02 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-18 | COMP | 2020-04-30 | COMP | 2020-05-27 | COMP | 2021-07-14 | COMP | Rule 15/16 | 159 | 59 | 17 | 113 | 19 | 286 | 648
17233 | 2018-12-17 | 2020-02-05 | 2020-03-16 | 2023-09-02 | CANC | 2023-09-02 | CANC | 2020-04-29 | COMP | 2020-06-26 | COMP | 2020-08-27 | COMP | Rule 16 | 285 |  |  |  | 42 | 45 | 429
8819 | 2018-12-18 | 2018-12-31 | 2019-03-31 | 2019-03-31 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2019-10-21 | INPR | 2019-07-09 | COMP | Rule 16 | 9 | 62 | 34 | 1 |  |  | 140
8945 | 2018-12-18 | 2019-01-08 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2021-02-27 | INPR | 2019-08-01 | COMP | Rule 16 | 14 | 75 | 23 | 1 |  |  | 157
9012 | 2018-12-18 | 2019-01-12 | 2019-06-07 | 2019-06-07 | COMP | 2019-07-11 | COMP | 2019-08-19 | COMP | 2019-08-23 | COMP | 2019-10-08 | COMP | Rule 16 | 17 | 102 | 24 | 28 | 5 | 32 | 204
9080 | 2018-12-18 | 2019-01-16 | 2019-04-17 | 2019-04-17 | COMP | 2019-07-10 | COMP | 2019-09-10 | COMP | 2023-11-11 | INPR | 2019-11-22 | COMP | Rule 16 | 20 | 64 | 59 | 44 |  |  | 236
9097 | 2018-12-18 | 2019-01-16 | 2019-02-23 | 2019-02-23 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-05-14 | COMP | 2019-07-10 | COMP | Rule 16 | 20 | 26 | 36 | 1 | 22 | 40 | 141
9120 | 2018-12-18 | 2019-01-17 | 2019-05-30 | 2019-05-30 | COMP | 2019-01-17 | NOTN | 2019-05-30 | COMP | 2019-05-31 | COMP | 2019-08-16 | COMP | Other | 21 | 93 |  | 1 | 2 | 55 | 168
9187 | 2018-12-18 | 2019-01-20 | 2019-03-27 | 2019-03-27 | COMP | 2019-07-09 | COMP | 2019-07-09 | INPR | 2019-04-12 | COMP | 2019-04-17 | COMP | Rule 16 | 22 | 46 | 73 |  |  |  | 83
9362 | 2018-12-18 | 2019-01-31 | 2019-12-30 | 2019-12-30 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-06-02 | COMP | 2020-06-03 | COMP | Rule 16 | 30 | 230 | 47 | 1 | 62 | 2 | 367
9402 | 2018-12-18 | 2019-02-02 | 2019-03-29 | 2019-03-29 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-08-08 | COMP | 2019-08-30 | COMP | Other | 31 | 39 | 73 | 1 | 21 | 17 | 178
9532 | 2018-12-18 | 2019-02-07 | 2019-03-13 | 2020-09-15 | COMP | 2020-11-06 | COMP | 2021-09-14 | COMP | 2021-10-12 | COMP | 2021-11-10 | COMP | Rule 15/16 | 35 | 24 | 39 | 213 | 21 | 22 | 731
9545 | 2018-12-18 | 2019-02-07 | 2019-07-10 | 2019-07-10 | COMP | 2019-05-01 | NOTN | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-07-30 | COMP | Other | 35 | 107 |  | 1 | 1 | 15 | 155
9674 | 2018-12-18 | 2019-02-11 | 2020-05-26 | 2021-01-26 | COMP | 2021-02-22 | COMP | 2021-03-02 | COMP | 2021-03-03 | COMP | 2021-08-12 | COMP | Rule 15/16 | 37 | 325 | 19 | 7 | 2 | 115 | 668
9859 | 2018-12-18 | 2019-02-20 | 2019-05-31 | 2019-05-31 | COMP | 2019-10-14 | COMP | 2020-03-10 | COMP | 2020-06-30 | COMP | 2020-09-10 | COMP | Rule 16 | 43 | 72 | 95 | 100 | 80 | 52 | 437
9895 | 2018-12-18 | 2019-02-21 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-05-08 | COMP | 2019-07-11 | COMP | Rule 16 | 44 | 46 | 11 | 1 | 0 | 44 | 142
10404 | 2018-12-18 | 2019-03-14 | 2019-08-17 | 2020-06-15 | COMP | 2020-08-18 | COMP | 2020-10-16 | COMP | 2020-08-18 | COMP | 2021-02-10 | COMP | Rule 15/16 | 59 | 110 | 47 | 43 | 0 | 78 | 540
10409 | 2018-12-18 | 2019-03-14 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-05 | COMP | 2019-04-16 | COMP | 2019-05-10 | COMP | 2019-06-06 | COMP | Rule 16 | 59 | 8 | 10 | 8 | 19 | 19 | 118
11020 | 2018-12-18 | 2019-04-09 | 2019-05-21 | 2019-05-21 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-11-05 | COMP | 2019-12-20 | COMP | Rule 16 | 77 | 31 | 36 | 1 | 83 | 31 | 254
11447 | 2018-12-18 | 2019-04-29 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-09-10 | COMP | 2019-11-07 | COMP | Rule 16 | 91 | 83 | 7 | 1 | 5 | 43 | 226
11454 | 2018-12-18 | 2019-04-29 | 2019-08-22 | 2019-10-24 | COMP | 2019-10-28 | COMP | 2019-10-28 | COMP | 2019-10-30 | COMP | 2019-12-09 | COMP | Rule 16 | 91 | 82 | 3 | 1 | 3 | 26 | 245
11574 | 2018-12-18 | 2019-05-02 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | 2019-12-03 | COMP | Rule 16 | 94 | 86 | 16 | 1 | 2 | 47 | 241
11791 | 2018-12-18 | 2019-05-13 | 2019-07-24 | 2019-08-13 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-10-14 | COMP | 2021-02-24 | COMP | Rule 16 | 101 | 51 | 166 | 1 | 132 | 89 | 549
12729 | 2018-12-18 | 2019-06-20 | 2019-10-08 | 2019-10-08 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2023-04-30 | INPR | 2020-08-11 | COMP | Rule 16 | 128 | 77 | 31 | 1 |  |  | 416
13698 | 2018-12-18 | 2019-08-06 | 2019-09-18 | 2019-09-18 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-10 | COMP | 2020-01-03 | COMP | Rule 16 | 160 | 31 | 49 | 1 | 9 | 17 | 262
14219 | 2018-12-18 | 2019-08-29 | 2020-02-20 | 2020-02-20 | COMP | 2020-07-21 | COMP | 2021-09-16 | COMP | 2021-09-08 | COMP | 2021-10-06 | COMP | Rule 15/16 | 177 | 118 | 108 | 292 | 0 | 15 | 706
14854 | 2018-12-18 | 2019-09-30 | 2020-08-02 | 2020-08-02 | COMP | 2020-09-09 | COMP | 2021-03-10 | COMP | 2021-03-26 | COMP | 2021-05-21 | COMP | Rule 15/16 | 198 | 212 | 27 | 124 | 13 | 41 | 611
25222 | 2018-12-18 | 2021-02-02 | 2021-04-22 | 2021-05-17 | COMP | 2021-06-03 | COMP | 2022-04-15 | COMP | 2022-07-06 | COMP | 2022-09-28 | COMP | Other | 534 | 57 | 13 | 220 | 56 | 60 | 952
34041 | 2018-12-18 | 2022-01-28 | 2022-06-06 | 2022-06-06 | COMP | 2022-06-21 | COMP | 2023-12-05 | CANC | 2023-12-05 | INPR | 2022-10-07 | COMP | Rule 16 | 784 | 90 | 11 |  |  |  | 959
4143 | 2018-12-19 | 2019-04-03 | 2019-06-28 | 2019-06-28 | COMP | 2021-05-11 | COMP | 2020-10-15 | COMP | 2022-05-02 | COMP | 2022-06-03 | COMP | Other | 72 | 62 | 470 |  | 388 | 24 | 871
8730 | 2018-12-19 | 2018-12-19 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-05-20 | COMP | 2019-06-19 | COMP | Rule 16 | 1 | 60 | 37 | 1 | 10 | 22 | 126
8759 | 2018-12-19 | 2018-12-21 | 2019-02-15 | 2019-07-17 | COMP | 2019-09-04 | COMP | 2019-09-23 | COMP | 2019-09-25 | COMP | 2020-01-22 | COMP | Rule 15/16 | 3 | 38 | 35 | 14 | 3 | 80 | 273
8943 | 2018-12-19 | 2019-01-08 | 2019-02-23 | 2019-02-23 | COMP | 2019-03-08 | COMP | 2019-03-08 | COMP | 2019-05-21 | COMP | 2019-05-30 | COMP | Rule 16 | 13 | 32 | 10 | 1 | 53 | 7 | 112
9444 | 2018-12-19 | 2019-02-04 | 2019-03-14 | 2019-03-14 | COMP | 2019-04-04 | COMP | 2019-04-30 | COMP | 2019-05-15 | NOTN | 2019-05-30 | COMP | Rule 16 | 31 | 28 | 16 | 19 |  |  | 112
9533 | 2018-12-19 | 2019-02-07 | 2019-05-21 | 2019-05-21 | COMP | 2019-05-24 | COMP | 2019-05-24 | COMP | 2019-07-10 | COMP | 2019-07-15 | COMP | Rule 16 | 34 | 73 | 4 | 1 | 32 | 4 | 143
9743 | 2018-12-19 | 2019-02-13 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-12-29 | INPR | 2019-07-30 | COMP | Rule 16 | 38 | 65 | 26 | 1 |  |  | 154
9840 | 2018-12-19 | 2019-02-20 | 2019-05-25 | 2019-11-16 | COMP | 2020-01-13 | COMP | 2020-04-01 | COMP | 2020-05-12 | COMP | 2020-06-09 | COMP | Rule 16 | 42 | 68 | 37 | 56 | 30 | 20 | 370
9962 | 2018-12-19 | 2019-02-25 | 2019-04-29 | 2019-04-29 | COMP | 2019-04-30 | NOTN | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-05-31 | COMP | Other | 45 | 46 |  | 2 | 1 | 23 | 113
10129 | 2018-12-19 | 2019-03-04 | 2019-08-16 | 2019-08-16 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-10-15 | COMP | 2019-12-09 | COMP | Rule 16 | 50 | 118 | 13 | 1 | 30 | 37 | 244
10157 | 2018-12-19 | 2019-03-05 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-10-21 | INPR | 2019-07-10 | COMP | Rule 16 | 51 | 47 | 12 | 1 |  |  | 140
11603 | 2018-12-19 | 2019-05-03 | 2019-08-21 | 2019-08-21 | COMP | 2019-10-01 | COMP | 2019-10-22 | COMP | 2020-03-21 | INPR | 2019-12-18 | COMP | Rule 16 | 94 | 77 | 29 | 16 |  |  | 251
12352 | 2018-12-19 | 2019-06-03 | 2019-07-24 | 2021-01-29 | COMP | 2021-02-09 | COMP | 2021-02-09 | COMP | 2022-09-28 | COMP | 2023-01-24 | COMP | Rule 16 | 114 | 37 | 8 | 1 | 414 | 79 | 1029
13607 | 2018-12-19 | 2019-08-01 | 2019-10-22 | 2019-10-23 | COMP | 2019-11-21 | COMP | 2020-04-16 | COMP | 2020-04-21 | COMP | 2020-05-05 | COMP | Rule 16 | 156 | 58 | 21 | 100 | 4 | 11 | 346
4035 | 2018-12-20 | 2018-12-21 | 2019-05-17 | 2019-05-17 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-09-13 | COMP | 2019-11-06 | COMP | Rule 15/16 | 2 | 102 | 76 | 1 | 8 | 39 | 223
8802 | 2018-12-20 | 2018-12-29 | 2019-04-20 | 2019-04-20 | COMP | 2019-07-03 | COMP | 2019-08-05 | COMP | 2020-04-20 | COMP | 2020-06-05 | COMP | Rule 16 | 6 | 77 | 52 | 23 | 178 | 34 | 367
8821 | 2018-12-20 | 2018-12-31 | 2019-09-22 | 2019-10-20 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-03-30 | COMP | 2020-04-03 | COMP | Rule 15/16 | 7 | 184 | 22 | 1 | 88 | 5 | 323
9002 | 2018-12-20 | 2019-01-12 | 2019-04-11 | 2019-04-11 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-08-06 | COMP | Rule 16 | 15 | 62 | 55 | 1 | 1 | 28 | 158
9050 | 2018-12-20 | 2019-01-14 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-15 | COMP | 2019-04-15 | COMP | 2019-07-25 | COMP | 2019-09-11 | COMP | Rule 16 | 16 | 36 | 8 | 22 | 72 | 34 | 183
9142 | 2018-12-20 | 2019-01-18 | 2019-02-15 | 2019-10-22 | COMP | 2019-11-20 | COMP | 2019-04-08 | COMP | 2019-11-22 | COMP | 2019-12-09 | COMP | Rule 16 | 20 | 20 | 21 |  | 161 | 10 | 243
9259 | 2018-12-20 | 2019-01-25 | 2019-05-24 | 2019-05-24 | COMP | 2019-08-19 | COMP | 2019-08-27 | COMP | 2019-07-16 | COMP | 2019-10-16 | COMP | Rule 15/16 | 24 | 85 | 60 | 7 | 0 | 36 | 208
9537 | 2018-12-20 | 2019-02-07 | 2019-06-07 | 2019-06-07 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-07-30 | COMP | 2019-08-15 | COMP | Rule 16 | 33 | 85 | 12 | 1 | 26 | 13 | 165
9695 | 2018-12-20 | 2019-02-11 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-30 | COMP | 2019-06-26 | COMP | 2019-05-01 | COMP | 2019-08-07 | COMP | Rule 16 | 35 | 41 | 16 | 41 | 0 | 30 | 159
10353 | 2018-12-20 | 2019-03-12 | 2019-07-23 | 2019-07-23 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-11-05 | COMP | 2019-11-06 | COMP | Rule 15/16 | 55 | 94 | 44 | 1 | 32 | 2 | 223
10426 | 2018-12-20 | 2019-03-15 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-13 | COMP | 2019-08-20 | COMP | 2019-08-06 | COMP | 2019-08-26 | COMP | Rule 16 | 58 | 29 | 14 | 70 | 0 | 5 | 172
10534 | 2018-12-20 | 2019-03-19 | 2019-10-18 | 2019-10-18 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-06-24 | COMP | 2020-11-23 | COMP | Rule 15/16 | 60 | 151 | 23 | 1 | 149 | 107 | 486
11296 | 2018-12-20 | 2019-04-22 | 2019-06-28 | 2020-05-23 | COMP | 2020-12-29 | COMP | 2021-01-07 | COMP | 2020-12-29 | COMP | 2021-03-24 | COMP | Other | 84 | 49 | 151 | 7 | 0 | 53 | 567
11727 | 2018-12-20 | 2019-05-08 | 2019-07-09 | 2019-07-17 | COMP | 2019-11-04 | COMP | 2019-10-29 | COMP | 2019-11-06 | COMP | 2019-12-20 | COMP | Rule 16 | 96 | 43 | 78 |  | 7 | 30 | 252
12319 | 2018-12-20 | 2019-05-30 | 2019-11-27 | 2019-11-27 | COMP | 2020-02-19 | COMP | 2020-07-31 | COMP | 2020-09-30 | COMP | 2020-12-14 | COMP | Rule 16 | 111 | 127 | 55 | 117 | 43 | 51 | 499
12328 | 2018-12-20 | 2019-05-31 | 2019-10-08 | 2019-10-08 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-11-20 | COMP | 2019-11-21 | COMP | Rule 16 | 112 | 91 | 6 | 1 | 26 | 2 | 233
12371 | 2018-12-20 | 2019-06-04 | 2019-08-15 | 2019-08-15 | COMP | 2020-01-08 | COMP | 2020-02-03 | COMP | 2020-01-17 | COMP | 2020-03-02 | COMP | Rule 16 | 114 | 52 | 99 | 18 | 0 | 20 | 299
12393 | 2018-12-20 | 2019-06-05 | 2019-10-10 | 2019-12-12 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2021-09-02 | COMP | 2021-10-08 | COMP | Rule 16 | 115 | 90 | 40 | 1 | 397 | 26 | 706
12471 | 2018-12-20 | 2019-06-08 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-08-16 | COMP | 2019-12-20 | COMP | Rule 16 | 117 | 88 | 9 | 1 | 0 | 40 | 252
12662 | 2018-12-20 | 2019-06-18 | 2019-09-12 | 2019-09-12 | COMP | 2019-09-19 | COMP | 2019-09-20 | COMP | 2019-10-19 | COMP | 2019-11-07 | COMP | Rule 16 | 124 | 61 | 6 | 2 | 21 | 14 | 224
13523 | 2018-12-20 | 2019-07-29 | 2019-12-05 | 2019-12-05 | COMP | 2019-12-05 | NOTN | 2019-12-05 | COMP | 2020-01-08 | COMP | 2020-02-06 | COMP | Other | 152 | 90 |  | 1 | 23 | 21 | 283
15051 | 2018-12-20 | 2019-10-10 | 2019-12-04 | 2019-12-04 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-08-13 | COMP | 2020-11-02 | COMP | Rule 16 | 204 | 37 | 140 | 1 | 38 | 57 | 472
15526 | 2018-12-20 | 2019-11-05 | 2020-02-11 | 2020-02-11 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2022-02-26 | INPR | 2020-07-20 | COMP | Rule 16 | 222 | 65 | 10 | 1 |  |  | 398
15527 | 2018-12-20 | 2019-11-05 | 2020-02-12 | 2020-02-12 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2021-05-30 | INPR | 2020-05-18 | COMP | Rule 16 | 222 | 66 | 9 | 1 |  |  | 354
15528 | 2018-12-20 | 2019-11-05 | 2020-02-12 | 2020-02-12 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2022-01-30 | INPR | 2020-06-10 | COMP | Rule 16 | 222 | 66 | 9 | 1 |  |  | 370
17223 | 2018-12-20 | 2020-02-05 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2021-01-20 | COMP | 2021-03-04 | COMP | Rule 16 | 282 | 94 | 14 | 1 | 136 | 31 | 553
17839 | 2018-12-20 | 2020-03-01 | 2020-04-10 | 2020-04-10 | COMP | 2020-09-10 | COMP | 2020-12-18 | COMP | 2021-07-08 | COMP | 2021-07-29 | COMP | Rule 16 | 298 | 30 | 108 | 69 | 139 | 16 | 656
4286 | 2018-12-21 | 2020-03-26 | 2020-04-15 | 2020-04-15 | COMP | 2021-08-30 | COMP | 2021-08-30 | COMP | 2023-11-04 | INPR | 2022-07-07 | COMP | Rule 16 | 316 | 15 | 348 | 1 |  |  | 891
8822 | 2018-12-21 | 2018-12-31 | 2019-06-10 | 2019-06-10 | COMP | 2019-10-16 | COMP | 2019-10-22 | COMP | 2020-03-30 | COMP | 2020-04-03 | COMP | Rule 15/16 | 6 | 112 | 91 | 5 | 108 | 5 | 322
8980 | 2018-12-21 | 2019-01-10 | 2019-02-20 | 2019-02-20 | COMP | 2021-05-30 | INPR | 2019-10-14 | COMP | 2021-05-30 | INPR | 2019-06-02 | COMP | Rule 16 | 13 | 28 |  | 166 |  |  | 111
9260 | 2018-12-21 | 2019-01-25 | 2019-03-16 | 2019-03-16 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-05-31 | COMP | 2019-06-13 | COMP | Rule 16 | 23 | 35 | 24 | 1 | 31 | 10 | 120
9335 | 2018-12-21 | 2019-01-31 | 2019-02-23 | 2019-02-23 | COMP | 2019-03-08 | COMP | 2019-09-02 | REQD | 2019-05-08 | COMP | 2019-05-07 | COMP | Rule 15/16 | 27 | 16 | 10 |  |  |  | 94
9410 | 2018-12-21 | 2019-02-02 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-08 | COMP | 2019-06-21 | COMP | 2019-09-27 | COMP | 2019-11-16 | COMP | Rule 16 | 28 | 49 | 18 | 32 | 69 | 35 | 228
9665 | 2018-12-21 | 2019-02-11 | 2019-03-07 | 2019-03-11 | COMP | 2019-03-25 | COMP | 2019-04-05 | COMP | 2019-04-16 | COMP | 2019-05-08 | COMP | Rule 16 | 34 | 18 | 11 | 10 | 8 | 17 | 95
9773 | 2018-12-21 | 2019-02-15 | 2019-04-27 | 2019-04-27 | COMP | 2019-06-10 | COMP | 2020-04-27 | COMP | 2020-05-19 | COMP | 2020-05-20 | COMP | Rule 16 | 38 | 50 | 30 | 222 | 17 | 2 | 355
10094 | 2018-12-21 | 2019-03-01 | 2019-05-03 | 2019-05-03 | COMP | 2019-07-16 | COMP | 2019-08-29 | COMP | 2019-08-19 | COMP | 2019-09-10 | COMP | Rule 15/16 | 47 | 46 | 51 | 33 | 0 | 8 | 181
10195 | 2018-12-21 | 2019-03-05 | 2019-05-13 | 2019-05-13 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-12-31 | COMP | 2020-01-13 | COMP | Rule 16 | 49 | 50 | 60 | 1 | 101 | 9 | 265
10461 | 2018-12-21 | 2019-03-18 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-12-11 | COMP | 2020-01-13 | COMP | Rule 16 | 58 | 93 | 23 | 1 | 73 | 22 | 265
10710 | 2018-12-21 | 2019-03-29 | 2019-09-19 | 2019-09-19 | COMP | 2021-04-02 | COMP | 2021-08-17 | COMP | 2021-08-11 | COMP | 2021-08-26 | COMP | Rule 15 | 67 | 122 | 386 | 96 | 0 | 8 | 675
10891 | 2018-12-21 | 2019-04-03 | 2019-05-30 | 2019-05-30 | COMP | 2019-06-03 | COMP | 2019-06-11 | COMP | 2019-06-25 | COMP | 2019-07-22 | COMP | Rule 15/16 | 70 | 41 | 3 | 7 | 11 | 19 | 146
11228 | 2018-12-21 | 2019-04-17 | 2019-04-26 | 2019-04-26 | COMP | 2019-08-26 | COMP | 2019-09-18 | COMP | 2019-07-26 | COMP | 2019-10-07 | COMP | Rule 16 | 80 | 8 | 85 | 17 | 0 | 14 | 200
11448 | 2018-12-21 | 2019-04-29 | 2019-08-19 | 2019-08-19 | COMP | 2019-09-19 | COMP | 2020-06-16 | COMP | 2020-06-17 | COMP | 2020-07-20 | COMP | Rule 15/16 | 88 | 79 | 23 | 186 | 2 | 24 | 397
12213 | 2018-12-21 | 2019-05-28 | 2019-07-19 | 2019-07-19 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-10-16 | COMP | 2020-03-31 | COMP | Rule 16 | 108 | 38 | 61 | 1 | 3 | 113 | 319
12570 | 2018-12-21 | 2019-06-14 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-12-17 | COMP | 2020-01-08 | COMP | Rule 16 | 121 | 78 | 16 | 1 | 36 | 15 | 262
14051 | 2018-12-21 | 2019-08-23 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-09 | NOTN | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-07-06 | COMP | Other | 170 | 134 |  | 1 | 1 | 85 | 387
9028 | 2018-12-22 | 2019-01-14 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-28 | COMP | 2019-06-11 | COMP | 2019-08-13 | COMP | 2019-09-25 | COMP | Rule 15/16 | 14 | 70 | 25 | 11 | 45 | 31 | 191
9196 | 2018-12-22 | 2019-01-22 | 2019-03-04 | 2019-03-04 | COMP | 2019-05-31 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-06-25 | COMP | Rule 16 | 19 | 29 | 64 | 3 | 1 | 16 | 127
10505 | 2018-12-22 | 2019-03-19 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2019-08-07 | COMP | Rule 16 | 58 | 79 | 5 | 1 | 2 | 17 | 157
8970 | 2018-12-24 | 2019-01-09 | 2019-02-13 | 2019-02-13 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-10-23 | COMP | 2019-12-04 | COMP | Rule 16 | 11 | 25 | 171 | 1 | 7 | 28 | 238
9235 | 2018-12-24 | 2019-01-24 | 2019-03-11 | 2019-05-09 | COMP | 2019-05-09 | NOTN | 2019-05-09 | COMP | 2019-05-21 | NOTN | 2019-07-11 | COMP | Other | 21 | 32 |  | 1 |  |  | 138
10330 | 2018-12-24 | 2019-03-11 | 2019-07-11 | 2019-07-11 | COMP | 2019-11-27 | COMP | 2019-12-02 | COMP | 2021-02-27 | INPR | 2019-12-21 | COMP | Rule 16 | 52 | 87 | 98 | 2 |  |  | 250
13801 | 2018-12-24 | 2019-08-12 | 2019-08-13 | 2019-08-13 | COMP | 2019-09-19 | COMP | 2019-09-09 | COMP | 2019-09-20 | COMP | 2019-10-25 | COMP | Rule 15/16 | 160 | 2 | 27 |  | 10 | 26 | 213
8879 | 2018-12-26 | 2019-01-03 | 2019-02-13 | 2020-08-20 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-10-07 | COMP | 2020-11-02 | COMP | Rule 16 | 6 | 29 | 8 | 1 | 27 | 19 | 469
8899 | 2018-12-26 | 2019-01-05 | 2019-03-23 | 2019-03-23 | COMP | 2019-04-09 | COMP | 2019-05-25 | COMP | 2019-10-21 | INPR | 2019-06-25 | COMP | Rule 16 | 7 | 53 | 12 | 34 |  |  | 126
9322 | 2018-12-26 | 2019-01-30 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-08-30 | COMP | 2019-09-26 | COMP | Rule 16 | 24 | 99 | 9 | 1 | 44 | 19 | 191
9342 | 2018-12-26 | 2019-01-30 | 2019-03-16 | 2019-03-16 | COMP | 2019-05-01 | COMP | 2019-05-30 | COMP | 2019-07-08 | COMP | 2019-07-10 | COMP | Rule 16 | 24 | 32 | 33 | 21 | 27 | 3 | 136
9407 | 2018-12-26 | 2019-02-01 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-09-25 | COMP | 2019-12-04 | COMP | Rule 16 | 26 | 55 | 14 | 1 | 97 | 48 | 237
9551 | 2018-12-26 | 2019-02-07 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-16 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-05-01 | COMP | Rule 16 | 30 | 36 | 13 | 3 | 1 | 10 | 88
9854 | 2018-12-26 | 2019-02-20 | 2019-04-30 | 2019-04-30 | COMP | 2020-12-01 | COMP | 2020-12-01 | COMP | 2022-11-18 | COMP | 2023-01-30 | COMP | Rule 16 | 38 | 50 | 401 | 1 | 497 | 47 | 1029
10024 | 2018-12-26 | 2019-02-27 | 2019-05-24 | 2020-05-15 | COMP | 2020-07-20 | COMP | 2019-12-02 | COMP | 2021-08-27 | COMP | 2021-09-29 | COMP | Rule 16 | 43 | 63 | 46 |  | 440 | 23 | 696
10525 | 2018-12-26 | 2019-03-19 | 2019-05-07 | 2019-05-07 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-08-11 | COMP | 2020-09-21 | COMP | Rule 16 | 57 | 36 | 237 | 1 | 84 | 29 | 439
11283 | 2018-12-26 | 2019-04-23 | 2019-05-15 | 2021-02-26 | COMP | 2021-02-08 | NOTN | 2021-04-27 | COMP | 2021-11-03 | COMP | 2022-01-31 | COMP | Other | 82 | 17 |  | 43 | 134 | 60 | 780
11698 | 2018-12-26 | 2019-05-08 | 2019-09-09 | 2019-09-09 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-14 | COMP | 2020-01-15 | COMP | Rule 16 | 93 | 86 | 46 | 1 | 22 | 21 | 265
12895 | 2018-12-26 | 2019-06-27 | 2019-10-03 | 2019-10-03 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-01-29 | COMP | 2020-05-24 | COMP | Rule 16 | 128 | 69 | 80 | 1 | 0 | 81 | 355
13352 | 2018-12-26 | 2019-07-22 | 2019-10-23 | 2019-10-23 | COMP | 2019-12-05 | COMP | 2020-01-07 | COMP | 2020-06-12 | COMP | 2020-07-28 | COMP | Rule 16 | 144 | 67 | 29 | 22 | 111 | 33 | 401
14040 | 2018-12-26 | 2019-08-22 | 2020-10-15 | 2021-02-09 | COMP | 2022-05-27 | COMP | 2023-01-24 | COMP | 2023-03-15 | COMP | 2023-04-10 | COMP | Rule 15/16 | 167 | 291 | 330 | 163 | 36 | 19 | 1078
14981 | 2018-12-26 | 2019-10-07 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-07 | COMP | 2020-03-02 | COMP | 2020-02-22 | COMP | 2020-05-04 | COMP | Rule 16 | 198 | 72 | 13 | 16 | 0 | 46 | 341
14982 | 2018-12-26 | 2019-10-07 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-14 | COMP | 2020-04-17 | COMP | 2021-02-25 | COMP | 2021-03-26 | COMP | Rule 16 | 198 | 82 | 8 | 45 | 216 | 22 | 566
4094 | 2018-12-27 | 2019-01-28 | 2019-03-07 | 2019-03-07 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-06-03 | COMP | 2019-07-15 | COMP | Rule 16 | 21 | 28 | 52 | 1 | 11 | 30 | 138
4121 | 2018-12-27 | 2019-03-12 | 2019-04-01 | 2019-04-01 | COMP | 2019-11-26 | COMP | 2019-11-26 | INPR | 2019-12-10 | COMP | 2020-01-31 | COMP | Rule 16 | 51 | 15 | 168 |  |  |  | 275
8954 | 2018-12-27 | 2019-01-09 | 2019-01-25 | 2019-03-15 | COMP | 2019-03-28 | COMP | 2019-04-09 | COMP | 2019-09-22 | INPR | 2019-05-09 | COMP | Rule 16 | 9 | 12 | 10 | 9 |  |  | 93
9139 | 2018-12-27 | 2019-01-17 | 2019-11-07 | 2020-01-28 | COMP | 2020-02-27 | COMP | 2021-05-05 | COMP | 2021-04-27 | COMP | 2021-06-22 | COMP | Rule 15/16 | 15 | 206 | 22 | 301 | 0 | 34 | 626
9254 | 2018-12-27 | 2019-01-25 | 2019-03-11 | 2021-05-13 | COMP | 2021-08-17 | COMP | 2021-10-29 | COMP | 2021-11-22 | COMP | 2021-12-14 | COMP | Rule 15/16 | 20 | 31 | 67 | 53 | 16 | 15 | 746
9269 | 2018-12-27 | 2019-01-25 | 2019-04-13 | 2019-04-13 | COMP | 2019-12-20 | COMP | 2020-01-08 | COMP | 2020-01-08 | COMP | 2020-02-04 | COMP | Rule 15/16 | 20 | 55 | 174 | 12 | 1 | 19 | 277
9324 | 2018-12-27 | 2019-01-30 | 2020-03-04 | 2020-03-04 | COMP | 2020-11-24 | COMP | 2021-02-09 | COMP | 2021-02-16 | COMP | 2021-06-22 | COMP | Rule 15/16 | 23 | 275 | 187 | 51 | 5 | 90 | 626
9325 | 2018-12-27 | 2019-01-30 | 2020-02-29 | 2020-02-29 | COMP | 2021-07-16 | COMP | 2021-07-16 | COMP | 2021-09-28 | COMP | 2021-11-23 | COMP | Rule 15/16 | 23 | 272 | 349 | 1 | 52 | 40 | 733
9326 | 2018-12-27 | 2019-01-30 | 2020-03-09 | 2020-03-09 | COMP | 2021-05-14 | COMP | 2021-06-02 | COMP | 2021-09-28 | COMP | 2021-11-23 | COMP | Rule 15/16 | 23 | 278 | 301 | 13 | 83 | 40 | 733
9358 | 2018-12-27 | 2019-01-30 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-17 | COMP | 2019-06-17 | COMP | 2019-04-18 | COMP | 2019-06-21 | COMP | Rule 16 | 23 | 47 | 8 | 43 | 0 | 5 | 123
9365 | 2018-12-27 | 2019-01-31 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-29 | COMP | 2019-06-19 | COMP | 2019-07-18 | COMP | 2019-08-27 | COMP | Rule 16 | 24 | 76 | 8 | 16 | 21 | 29 | 169
9380 | 2018-12-27 | 2019-01-31 | 2019-04-08 | 2019-04-08 | COMP | 2019-04-15 | COMP | 2019-10-11 | COMP | 2019-09-09 | COMP | 2019-10-31 | COMP | Rule 16 | 24 | 47 | 6 | 127 | 0 | 15 | 215
9394 | 2018-12-27 | 2019-02-01 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-18 | COMP | 2019-04-22 | COMP | 2019-08-12 | COMP | 2019-12-17 | COMP | Rule 16 | 25 | 40 | 15 | 3 | 79 | 88 | 245
9465 | 2018-12-27 | 2019-02-05 | 2019-04-25 | 2019-05-08 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2020-06-02 | COMP | 2020-09-09 | COMP | Rule 16 | 27 | 57 | 15 | 1 | 255 | 71 | 430
9661 | 2018-12-27 | 2019-02-11 | 2019-06-18 | 2019-06-18 | COMP | 2019-07-09 | COMP | 2019-08-13 | COMP | 2019-08-15 | COMP | 2019-09-13 | COMP | Rule 15/16 | 31 | 90 | 15 | 26 | 3 | 21 | 181
9970 | 2018-12-27 | 2019-02-26 | 2019-03-06 | 2019-03-06 | COMP | 2019-05-08 | COMP | 2019-05-08 | INPR | 2019-05-08 | COMP | 2019-05-10 | COMP | Rule 16 | 41 | 7 | 46 |  |  |  | 94
10376 | 2018-12-27 | 2019-03-13 | 2019-06-29 | 2019-06-29 | COMP | 2019-09-05 | COMP | 2019-09-12 | COMP | 2019-10-18 | COMP | 2019-11-04 | COMP | Rule 15/16 | 52 | 77 | 47 | 6 | 27 | 12 | 217
10448 | 2018-12-27 | 2019-03-16 | 2019-07-17 | 2019-07-17 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-03-27 | COMP | 2020-05-12 | COMP | Rule 16 | 54 | 86 | 173 | 1 | 3 | 33 | 346
10578 | 2018-12-27 | 2019-03-21 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-08-23 | COMP | 2019-08-26 | COMP | Rule 16 | 58 | 31 | 20 | 1 | 61 | 2 | 168
10900 | 2018-12-27 | 2019-04-04 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-24 | COMP | 2020-07-22 | COMP | 2020-07-21 | COMP | 2020-08-05 | COMP | Rule 16 | 68 | 259 | 9 | 63 | 0 | 11 | 406
10926 | 2018-12-27 | 2019-04-04 | 2019-07-15 | 2019-12-13 | COMP | 2020-01-27 | COMP | 2020-04-27 | COMP | 2020-05-11 | COMP | 2020-06-09 | COMP | Rule 15/16 | 68 | 71 | 29 | 65 | 11 | 21 | 365
10985 | 2018-12-27 | 2019-04-08 | 2019-08-16 | 2019-08-16 | COMP | 2019-08-16 | NOTN | 2019-08-16 | COMP | 2019-08-16 | COMP | 2019-09-23 | COMP | Other | 70 | 93 |  | 1 | 1 | 26 | 187
12052 | 2018-12-27 | 2019-05-22 | 2019-08-26 | 2020-01-28 | COMP | 2020-03-02 | COMP | 2020-01-21 | COMP | 2020-01-07 | COMP | 2020-03-07 | COMP | Rule 16 | 102 | 67 | 24 |  | 0 | 33 | 299
12409 | 2018-12-27 | 2019-06-06 | 2019-06-28 | 2019-07-17 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-12-10 | COMP | 2020-01-10 | COMP | Rule 16 | 112 | 17 | 49 | 1 | 53 | 22 | 261
8861 | 2018-12-28 | 2019-01-03 | 2019-03-16 | 2019-03-16 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-03-21 | COMP | 2019-05-13 | COMP | Rule 16 | 4 | 50 | 4 | 1 | 1 | 38 | 94
8996 | 2018-12-28 | 2019-01-11 | 2019-04-05 | 2019-04-05 | COMP | 2019-05-06 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-06-29 | COMP | Rule 16 | 10 | 59 | 22 | 2 | 1 | 38 | 127
9197 | 2018-12-28 | 2019-01-22 | 2019-03-06 | 2019-03-06 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-09-02 | INPR | 2019-05-09 | COMP | Rule 16 | 16 | 31 | 19 | 1 |  |  | 92
9305 | 2018-12-28 | 2019-01-28 | 2019-05-23 | 2019-05-23 | COMP | 2019-06-11 | COMP | 2019-06-28 | COMP | 2019-07-01 | COMP | 2019-09-26 | COMP | Rule 16 | 20 | 83 | 13 | 14 | 2 | 62 | 189
9347 | 2018-12-28 | 2019-01-31 | 2019-03-27 | 2019-03-27 | COMP | 2019-04-15 | COMP | 2019-04-30 | COMP | 2019-12-29 | INPR | 2019-08-08 | COMP | Rule 16 | 23 | 39 | 14 | 12 |  |  | 155
9396 | 2018-12-28 | 2019-02-01 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-03 | COMP | 2019-04-29 | COMP | 2019-05-14 | COMP | 2019-09-17 | COMP | Rule 16 | 24 | 33 | 11 | 19 | 12 | 88 | 182
9445 | 2018-12-28 | 2019-02-04 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-14 | COMP | 2019-09-20 | COMP | 2019-10-07 | COMP | 2019-11-15 | COMP | Rule 16 | 25 | 81 | 13 | 69 | 12 | 29 | 224
9653 | 2018-12-28 | 2019-02-10 | 2019-02-27 | 2019-04-11 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | Rule 16 | 29 | 12 | 13 | 1 | 54 | 1 | 137
9801 | 2018-12-28 | 2019-02-15 | 2019-06-24 | 2019-06-24 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2020-07-21 | COMP | 2020-08-10 | COMP | Rule 16 | 34 | 90 | 63 | 1 | 210 | 15 | 408
9900 | 2018-12-28 | 2019-02-22 | 2019-04-06 | 2019-04-06 | COMP | 2019-05-09 | COMP | 2019-05-08 | COMP | 2019-10-21 | INPR | 2019-05-06 | COMP | Rule 16 | 38 | 31 | 24 |  |  |  | 89
10072 | 2018-12-28 | 2019-02-28 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-06-25 | COMP | 2019-07-25 | COMP | Rule 16 | 42 | 62 | 18 | 1 | 4 | 22 | 145
10262 | 2018-12-28 | 2019-03-09 | 2019-05-17 | 2019-05-17 | COMP | 2019-04-26 | NOTN | 2019-05-17 | COMP | 2019-04-26 | COMP | 2019-08-13 | COMP | Other | 48 | 50 |  | 1 | 0 | 61 | 158
10352 | 2018-12-28 | 2019-03-12 | 2019-04-18 | 2019-04-18 | COMP | 2019-05-07 | COMP | 2019-05-10 | COMP | 2020-04-07 | COMP | 2020-04-10 | COMP | Rule 16 | 50 | 28 | 14 | 4 | 228 | 4 | 323
10563 | 2018-12-28 | 2019-03-20 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-22 | COMP | 2019-08-29 | COMP | Rule 16 | 56 | 50 | 34 | 1 | 5 | 29 | 170
10761 | 2018-12-28 | 2019-03-28 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-09 | COMP | 2019-12-03 | COMP | 2019-12-13 | COMP | 2020-02-23 | COMP | Rule 16 | 62 | 90 | 5 | 79 | 9 | 47 | 288
10768 | 2018-12-28 | 2019-03-28 | 2019-06-17 | 2019-06-17 | COMP | 2019-11-06 | COMP | 2019-07-15 | COMP | 2019-11-19 | COMP | 2020-04-02 | COMP | Rule 16 | 62 | 57 | 101 |  | 90 | 92 | 317
10951 | 2018-12-28 | 2019-04-05 | 2019-07-13 | 2019-07-13 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2021-05-04 | COMP | 2021-06-07 | COMP | Rule 16 | 68 | 69 | 76 | 1 | 380 | 24 | 614
11267 | 2018-12-28 | 2019-04-19 | 2019-08-07 | 2019-11-17 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-03-27 | COMP | 2020-06-11 | COMP | Rule 16 | 78 | 77 | 5 | 1 | 85 | 54 | 366
15488 | 2018-12-28 | 2019-11-04 | 2020-02-21 | 2020-02-21 | COMP | 2020-06-05 | COMP | 2021-10-07 | COMP | 2020-09-18 | COMP | 2021-11-17 | COMP | Rule 15/16 | 216 | 73 | 75 | 339 | 0 | 29 | 728
9913 | 2018-12-29 | 2019-02-22 | 2019-07-15 | 2019-07-15 | COMP | 2019-07-22 | COMP | 2019-07-30 | COMP | 2019-07-31 | COMP | 2019-09-05 | COMP | Rule 15/16 | 37 | 100 | 6 | 7 | 2 | 26 | 173
9914 | 2018-12-29 | 2019-02-22 | 2019-11-04 | 2019-11-04 | COMP | 2020-01-23 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-08-07 | COMP | Rule 15/16 | 37 | 179 | 53 | 8 | 1 | 133 | 406
19030 | 2018-12-29 | 2020-04-17 | 2020-06-12 | 2020-06-12 | COMP | 2020-08-05 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2020-11-16 | COMP | Rule 15/16 | 327 | 40 | 39 | 39 | 1 | 34 | 475
10503 | 2018-12-30 | 2019-03-19 | 2019-04-09 | 2019-04-09 | COMP | 2019-07-08 | COMP | 2019-08-01 | COMP | 2019-12-29 | INPR | 2019-08-02 | COMP | Rule 16 | 54 | 16 | 63 | 19 |  |  | 150
21980 | 2018-12-30 | 2020-09-07 | 2020-12-15 | 2020-12-15 | COMP | 2021-01-25 | COMP | 2021-02-24 | COMP | 2021-11-09 | COMP | 2022-02-05 | COMP | Rule 16 | 426 | 68 | 27 | 22 | 182 | 60 | 781
8900 | 2018-12-31 | 2019-01-05 | 2019-05-04 | 2019-05-04 | COMP | 2019-07-16 | COMP | 2019-07-24 | COMP | 2020-02-27 | COMP | 2022-08-30 | COMP | Rule 15/16 | 4 | 83 | 50 | 7 | 149 | 634 | 924
8915 | 2018-12-31 | 2019-01-06 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-12 | COMP | 2019-04-12 | COMP | 2019-04-23 | COMP | 2019-06-03 | COMP | Rule 16 | 4 | 59 | 10 | 1 | 8 | 29 | 107
9578 | 2018-12-31 | 2019-02-08 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-09-03 | COMP | 2019-10-22 | COMP | Rule 16 | 28 | 99 | 13 | 1 | 34 | 36 | 206
9686 | 2018-12-31 | 2019-02-11 | 2019-04-16 | 2019-04-16 | COMP | 2019-10-01 | NOTN | 2019-10-02 | COMP | 2019-10-01 | COMP | 2020-01-28 | COMP | Other | 29 | 46 |  | 119 | 0 | 79 | 270
10529 | 2018-12-31 | 2019-03-19 | 2019-09-06 | 2019-09-06 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP |  | INPR | 2020-09-18 | COMP | Rule 16 | 54 | 121 | 130 | 1 |  |  | 435
11051 | 2018-12-31 | 2019-04-10 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-10-21 | INPR | 2019-06-17 | COMP | Rule 16 | 70 | 18 | 8 | 1 |  |  | 117
12142 | 2018-12-31 | 2019-05-23 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-26 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | Rule 16 | 101 | 57 | 10 | 59 | 1 | 1 | 224
12411 | 2018-12-31 | 2019-06-06 | 2019-06-27 | 2019-07-16 | COMP | 2019-07-22 | COMP | 2019-09-03 | COMP | 2020-05-31 | INPR | 2019-09-12 | COMP | Rule 16 | 110 | 16 | 5 | 31 |  |  | 178
13338 | 2018-12-31 | 2019-07-24 | 2019-08-27 | 2019-08-27 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2019-11-15 | COMP | 2019-12-04 | COMP | Rule 16 | 143 | 25 | 10 | 1 | 48 | 12 | 234
9482 | 2019-01-02 | 2019-02-05 | 2019-04-15 | 2019-07-25 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2021-05-30 | INPR | 2020-02-24 | COMP | Rule 16 | 24 | 49 | 68 | 1 |  |  | 287
9497 | 2019-01-02 | 2019-02-06 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-18 | COMP | 2019-04-18 | COMP | 2019-04-25 | COMP | 2019-05-17 | COMP | Rule 16 | 25 | 42 | 10 | 1 | 6 | 17 | 96
9605 | 2019-01-02 | 2019-02-08 | 2019-07-08 | 2019-07-08 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2020-01-19 | INPR | 2019-10-08 | COMP | Rule 16 | 27 | 104 | 34 | 1 |  |  | 195
9632 | 2019-01-02 | 2019-02-09 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-15 | COMP | 2019-04-24 | COMP | 2019-05-17 | COMP | 2019-05-30 | COMP | Rule 16 | 27 | 31 | 15 | 8 | 18 | 9 | 104
9733 | 2019-01-02 | 2019-02-13 | 2019-04-02 | 2020-02-19 | COMP | 2020-10-23 | COMP | 2020-10-23 | COMP | 2020-11-05 | COMP | 2020-11-23 | COMP | Rule 16 | 30 | 34 | 176 | 1 | 10 | 12 | 479
9960 | 2019-01-02 | 2019-02-25 | 2019-04-30 | 2019-04-30 | COMP | 2019-07-26 | COMP | 2020-02-07 | COMP | 2020-02-18 | COMP | 2020-03-04 | COMP | Rule 16 | 37 | 47 | 62 | 134 | 7 | 12 | 294
9967 | 2019-01-02 | 2019-02-25 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-17 | COMP | 2019-07-29 | COMP | 2019-06-17 | COMP | 2019-08-01 | COMP | Rule 16 | 37 | 65 | 15 | 30 | 0 | 4 | 148
10140 | 2019-01-02 | 2019-03-04 | 2019-05-13 | 2019-05-13 | COMP | 2019-09-10 | COMP | 2019-10-23 | COMP | 2020-01-09 | COMP | 2020-01-31 | COMP | Rule 15/16 | 42 | 51 | 84 | 32 | 52 | 16 | 272
10317 | 2019-01-02 | 2019-03-11 | 2019-04-23 | 2019-04-23 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2023-11-11 | INPR | 2020-10-01 | COMP | Rule 15/16 | 47 | 32 | 64 | 1 |  |  | 443
10385 | 2019-01-02 | 2019-03-13 | 2019-04-20 | 2019-10-07 | COMP | 2019-10-15 | COMP | 2019-11-08 | COMP | 2019-10-15 | COMP | 2019-11-26 | COMP | Rule 16 | 49 | 28 | 7 | 19 | 0 | 12 | 229
10522 | 2019-01-02 | 2019-03-19 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-13 | COMP | 2019-05-24 | COMP | 2019-05-28 | COMP | 2019-06-03 | COMP | Rule 16 | 53 | 27 | 14 | 10 | 2 | 5 | 106
11127 | 2019-01-02 | 2019-04-15 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-12-30 | COMP | 2020-02-15 | COMP | Rule 15/16 | 72 | 128 | 14 | 1 | 39 | 33 | 282
11279 | 2019-01-02 | 2019-04-22 | 2019-08-30 | 2019-08-30 | COMP | 2019-11-06 | COMP | 2019-11-15 | COMP | 2021-01-12 | COMP | 2021-02-08 | COMP | Rule 16 | 77 | 93 | 48 | 7 | 290 | 19 | 529
11497 | 2019-01-02 | 2019-04-30 | 2019-10-23 | 2019-10-23 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | 2020-05-06 | COMP | Rule 16 | 83 | 124 | 108 | 1 | 2 | 26 | 339
11670 | 2019-01-02 | 2019-05-07 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-04 | COMP | 2019-09-05 | COMP | 2019-11-04 | COMP | 2019-12-11 | COMP | Rule 16 | 88 | 57 | 28 | 2 | 43 | 25 | 238
11695 | 2019-01-02 | 2019-05-08 | 2019-09-16 | 2019-09-16 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-11-19 | COMP | 2021-02-10 | COMP | Rule 16 | 89 | 91 | 13 | 1 | 287 | 55 | 531
12061 | 2019-01-02 | 2019-05-23 | 2019-08-06 | 2019-08-06 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-11-22 | COMP | Rule 16 | 100 | 52 | 41 | 1 | 1 | 37 | 227
12212 | 2019-01-02 | 2019-05-28 | 2019-09-12 | 2020-04-27 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-08-03 | COMP | Rule 15/16 | 102 | 76 | 21 | 1 | 1 | 50 | 401
12492 | 2019-01-02 | 2019-06-10 | 2019-11-08 | 2019-11-08 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-08-18 | COMP | 2020-09-21 | COMP | Rule 16 | 111 | 108 | 34 | 1 | 162 | 24 | 435
12752 | 2019-01-02 | 2019-06-20 | 2019-08-09 | 2019-08-09 | COMP | 2019-09-23 | COMP | 2019-12-19 | COMP | 2019-12-05 | COMP | 2020-02-27 | COMP | Rule 16 | 119 | 36 | 31 | 61 | 0 | 47 | 290
13469 | 2019-01-02 | 2019-07-25 | 2020-02-10 | 2020-03-20 | COMP | 2020-03-24 | COMP | 2020-05-05 | COMP | 2020-05-22 | COMP | 2020-06-08 | COMP | Rule 16 | 143 | 136 | 3 | 31 | 14 | 11 | 361
13617 | 2019-01-02 | 2019-08-02 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-10-02 | COMP | 2019-10-03 | COMP | Rule 16 | 149 | 23 | 15 | 1 | 7 | 2 | 192
13618 | 2019-01-02 | 2019-08-02 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-24 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-10-03 | COMP | Rule 16 | 149 | 23 | 15 | 7 | 1 | 2 | 192
13619 | 2019-01-02 | 2019-08-02 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-24 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-10-03 | COMP | Rule 16 | 149 | 23 | 15 | 7 | 1 | 2 | 192
14214 | 2019-01-02 | 2019-08-29 | 2019-12-17 | 2019-12-17 | COMP | 2021-03-15 | COMP | 2021-03-16 | COMP | 2023-12-03 | INPR | 2021-08-18 | COMP | Rule 16 | 168 | 75 | 312 | 2 |  |  | 663
15203 | 2019-01-02 | 2019-10-19 | 2020-02-21 | 2020-02-21 | COMP | 2020-02-26 | COMP | 2020-09-03 | COMP | 2020-09-29 | COMP | 2020-12-03 | COMP | Rule 16 | 203 | 83 | 4 | 136 | 18 | 45 | 485
16359 | 2019-01-02 | 2019-12-23 | 2020-03-06 | 2020-03-06 | COMP | 2020-04-15 | NOTN | 2020-07-08 | COMP | 2020-04-15 | COMP | 2020-07-29 | COMP | Other | 246 | 51 |  | 88 | 0 | 16 | 398
17271 | 2019-01-02 | 2020-02-07 | 2020-03-04 | 2020-03-04 | COMP | 2021-01-29 | COMP | 2021-01-29 | COMP | 2022-05-03 | COMP | 2022-06-04 | COMP | Rule 16 | 277 | 18 | 230 | 1 | 319 | 23 | 863
8956 | 2019-01-03 | 2019-01-09 | 2019-03-16 | 2019-03-16 | COMP | 2019-04-12 | COMP | 2019-07-26 | INPR | 2019-05-30 | COMP | 2019-07-26 | COMP | Rule 16 | 5 | 46 | 20 |  |  |  | 143
9031 | 2019-01-03 | 2019-01-14 | 2019-02-22 | 2019-02-22 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2021-09-20 | COMP | 2021-12-04 | COMP | Rule 16 | 8 | 28 | 25 | 1 | 626 | 52 | 735
9064 | 2019-01-03 | 2019-01-15 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-13 | NOTN | 2019-02-13 | COMP | 2019-02-22 | COMP | 2019-04-26 | COMP | Other | 9 | 16 |  | 6 | 7 | 46 | 80
9175 | 2019-01-03 | 2019-01-20 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-20 | COMP | 2019-05-23 | COMP | 2019-12-29 | INPR | 2019-07-30 | COMP | Rule 16 | 12 | 70 | 15 | 4 |  |  | 145
9336 | 2019-01-03 | 2019-01-30 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-28 | COMP | 2019-08-13 | COMP | 2019-09-17 | COMP | 2019-10-25 | COMP | Rule 16 | 19 | 77 | 7 | 55 | 25 | 29 | 207
9404 | 2019-01-03 | 2019-02-02 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-14 | COMP | 2019-03-14 | COMP | 2019-10-21 | INPR | 2019-04-15 | COMP | Rule 16 | 21 | 22 | 7 | 1 |  |  | 71
9431 | 2019-01-03 | 2019-02-04 | 2019-04-08 | 2019-04-08 | COMP | 2019-04-30 | COMP | 2019-05-06 | COMP | 2019-10-01 | COMP | 2019-10-30 | COMP | Rule 16 | 22 | 45 | 17 | 5 | 104 | 22 | 210
9454 | 2019-01-03 | 2019-02-05 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-01 | COMP | 2019-06-10 | COMP | 2019-06-18 | COMP | 2019-06-08 | COMP | Rule 16 | 23 | 56 | 6 | 28 | 7 |  | 109
9678 | 2019-01-03 | 2019-02-12 | 2019-07-01 | 2019-07-11 | COMP | 2019-12-13 | COMP | 2021-02-18 | COMP | 2021-12-07 | COMP | 2022-01-14 | COMP | Rule 16 | 28 | 98 | 108 | 297 | 203 | 29 | 765
9725 | 2019-01-03 | 2019-02-12 | 2019-04-03 | 2020-10-23 | COMP | 2021-04-27 | COMP | 2021-05-18 | COMP | 2021-05-12 | COMP | 2021-06-30 | COMP | Rule 16 | 28 | 36 | 126 | 16 | 0 | 31 | 628
10095 | 2019-01-03 | 2019-03-01 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-16 | COMP | 2019-05-30 | COMP | 2019-05-08 | COMP | 2019-07-15 | COMP | Rule 16 | 40 | 41 | 15 | 10 | 0 | 32 | 134
10213 | 2019-01-03 | 2019-03-06 | 2019-03-22 | 2019-03-22 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-07-21 | INPR | 2019-04-22 | COMP | Rule 16 | 43 | 13 | 5 | 1 |  |  | 76
10740 | 2019-01-03 | 2019-03-28 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-19 | COMP | 2019-11-27 | COMP | 2019-09-12 | COMP | 2020-01-02 | COMP | Rule 16 | 59 | 66 | 15 | 92 | 0 | 23 | 251
11029 | 2019-01-03 | 2019-04-09 | 2019-06-18 | 2019-06-18 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-07-10 | COMP | 2019-07-18 | COMP | Rule 16 | 67 | 50 | 9 | 1 | 8 | 7 | 137
11315 | 2019-01-03 | 2019-04-23 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-08-14 | COMP | 2020-11-04 | COMP | Rule 15/16 | 77 | 288 | 15 | 1 | 32 | 58 | 466
11322 | 2019-01-03 | 2019-04-23 | 2019-05-20 | 2019-05-20 | COMP | 2019-08-06 | INPR | 2019-06-12 | NOTN | 2019-08-06 | REQD | 2019-06-18 | COMP | Rule 16 | 77 | 20 |  |  |  |  | 116
11591 | 2019-01-03 | 2019-05-03 | 2019-06-18 | 2019-06-18 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-12-06 | COMP | Rule 16 | 85 | 32 | 92 | 1 | 1 | 28 | 234
11817 | 2019-01-03 | 2019-05-13 | 2019-09-14 | 2019-09-23 | COMP | 2019-09-19 | NOTN | 2019-09-23 | COMP | 2019-09-19 | COMP | 2019-09-30 | COMP | Other | 91 | 87 |  | 1 | 0 | 6 | 188
11938 | 2019-01-03 | 2019-05-18 | 2019-12-20 | 2021-05-18 | COMP | 2021-06-04 | COMP | 2021-06-04 | COMP | 2021-11-19 | COMP | 2021-07-23 | COMP | Rule 15/16 | 95 | 149 | 13 | 1 | 118 |  | 644
12080 | 2019-01-03 | 2019-05-22 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | Rule 15/16 | 98 | 35 | 11 | 1 | 24 | 1 | 165
12365 | 2019-01-03 | 2019-06-03 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-03 | COMP | 2019-12-12 | COMP | 2021-01-02 | INPR | 2019-12-20 | COMP | Rule 15/16 | 105 | 79 | 49 | 8 |  |  | 244
13106 | 2019-01-03 | 2019-07-10 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-08 | NOTN | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-11-14 | COMP | Rule 16 | 131 | 54 |  | 11 | 1 | 27 | 220
13273 | 2019-01-03 | 2019-07-18 | 2019-11-22 | 2019-11-22 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-07-01 | COMP | 2020-07-30 | COMP | Rule 16 | 137 | 90 | 51 | 1 | 102 | 22 | 398
13301 | 2019-01-03 | 2019-07-18 | 2019-12-04 | 2019-12-04 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-09-02 | COMP | 2020-11-13 | COMP | Rule 16 | 137 | 96 | 62 | 1 | 130 | 51 | 472
13372 | 2019-01-03 | 2019-07-22 | 2019-08-08 | 2019-08-08 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-27 | COMP | 2019-12-11 | COMP | Rule 15/16 | 139 | 14 | 63 | 1 | 16 | 9 | 237
14128 | 2019-01-03 | 2019-08-26 | 2020-01-14 | 2020-05-27 | COMP | 2020-04-16 | NOTN | 2020-06-05 | COMP | 2020-08-18 | COMP | 2020-11-05 | COMP | Other | 164 | 96 |  | 8 | 53 | 57 | 467
14633 | 2019-01-03 | 2019-09-21 | 2020-01-17 | 2020-01-17 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2022-12-03 | INPR | 2021-09-27 | COMP | Rule 16 | 182 | 80 | 132 | 1 |  |  | 689
15214 | 2019-01-03 | 2019-10-21 | 2020-02-18 | 2020-02-18 | COMP | 2020-04-01 | COMP | 2020-04-10 | COMP | 2020-04-20 | COMP | 2020-06-29 | COMP | Rule 16 | 203 | 80 | 32 | 8 | 7 | 50 | 375
15772 | 2019-01-03 | 2019-11-21 | 2020-01-09 | 2020-01-09 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-11-13 | COMP | 2021-03-15 | COMP | Rule 15/16 | 225 | 32 | 65 | 1 | 153 | 81 | 552
19787 | 2019-01-03 | 2020-05-22 | 2021-01-19 | 2021-01-19 | COMP | 2021-01-20 | NOTN | 2021-08-09 | COMP | 2021-07-14 | COMP | 2021-08-09 | COMP | Other | 350 | 165 |  | 142 | 0 | 1 | 655
8883 | 2019-01-04 | 2019-01-04 | 2019-01-08 | 2019-04-16 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2019-09-17 | COMP | 2019-12-23 | COMP | Rule 16 | 1 | 3 | 44 | 1 | 65 | 67 | 244
9026 | 2019-01-04 | 2019-01-14 | 2019-03-20 | 2019-03-20 | COMP | 2019-03-22 | COMP | 2019-03-25 | COMP | 2019-06-04 | COMP | 2019-06-12 | COMP | Rule 16 | 7 | 46 | 3 | 2 | 51 | 7 | 111
9385 | 2019-01-04 | 2019-01-31 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-28 | COMP | 2019-06-17 | COMP | Rule 15/16 | 19 | 51 | 15 | 1 | 17 | 15 | 114
9485 | 2019-01-04 | 2019-02-06 | 2019-09-20 | 2019-09-20 | COMP | 2019-10-21 | COMP | 2020-03-19 | COMP | 2020-03-10 | COMP | 2020-04-27 | COMP | Rule 15/16 | 23 | 159 | 22 | 102 | 0 | 28 | 330
9488 | 2019-01-04 | 2019-02-06 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-18 | COMP | 2019-04-23 | COMP | 2019-04-25 | COMP | 2019-06-20 | COMP | Rule 16 | 23 | 45 | 7 | 4 | 3 | 40 | 117
9514 | 2019-01-04 | 2019-02-06 | 2019-03-19 | 2019-03-19 | COMP | 2019-03-25 | COMP | 2019-04-12 | COMP | 2019-07-23 | COMP | 2019-08-30 | COMP | Rule 16 | 23 | 29 | 5 | 15 | 71 | 29 | 167
9555 | 2019-01-04 | 2019-02-07 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-22 | COMP | 2019-06-06 | COMP | 2019-08-21 | COMP | 2019-11-12 | COMP | Rule 16 | 24 | 53 | 22 | 11 | 54 | 58 | 217
9650 | 2019-01-04 | 2019-02-10 | 2019-04-03 | 2019-04-03 | COMP | 2019-05-07 | COMP | 2019-05-08 | COMP | 2019-06-14 | COMP | 2019-06-25 | COMP | Rule 16 | 25 | 37 | 25 | 2 | 27 | 8 | 120
10101 | 2019-01-04 | 2019-03-01 | 2019-11-08 | 2019-11-08 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2021-06-22 | COMP | 2021-07-21 | COMP | Rule 15/16 | 39 | 178 | 105 | 1 | 302 | 21 | 641
10162 | 2019-01-04 | 2019-03-05 | 2019-09-24 | 2019-09-24 | COMP | 2020-04-16 | COMP | 2020-12-01 | COMP | 2020-10-16 | COMP | 2021-02-09 | COMP | Rule 15/16 | 41 | 143 | 141 | 159 | 0 | 48 | 528
10771 | 2019-01-04 | 2019-03-29 | 2019-06-07 | 2019-06-07 | COMP | 2019-06-25 | COMP | 2019-07-03 | COMP | 2020-05-31 | INPR | 2019-09-03 | COMP | Rule 16 | 59 | 50 | 13 | 7 |  |  | 168
10834 | 2019-01-04 | 2019-04-01 | 2019-09-03 | 2019-10-01 | COMP | 2019-10-23 | NOTN | 2019-10-30 | COMP | 2019-11-26 | COMP | 2019-12-09 | COMP | Other | 60 | 109 |  | 22 | 19 | 8 | 234
11485 | 2019-01-04 | 2019-04-30 | 2019-05-08 | 2019-05-08 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-07-23 | COMP | Rule 16 | 81 | 7 | 30 | 1 | 1 | 24 | 139
11636 | 2019-01-04 | 2019-05-07 | 2019-06-07 | 2019-06-07 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2020-06-09 | COMP | 2020-07-31 | COMP | Rule 16 | 86 | 23 | 11 | 1 | 243 | 39 | 398
11909 | 2019-01-04 | 2019-05-16 | 2019-06-04 | 2019-07-08 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-11-14 | COMP | 2020-01-22 | COMP | Rule 16 | 93 | 13 | 94 | 1 | 0 | 43 | 263
11957 | 2019-01-04 | 2019-05-19 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-19 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-10-15 | COMP | Rule 16 | 94 | 56 | 9 | 26 | 1 | 16 | 198
12568 | 2019-01-04 | 2019-06-14 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-29 | COMP | 2019-09-30 | INPR | 2019-10-03 | COMP | 2019-11-19 | COMP | Rule 16 | 113 | 38 | 17 |  |  |  | 222
12835 | 2019-01-04 | 2019-06-24 | 2019-08-25 | 2019-08-25 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-01-22 | COMP | Rule 16 | 119 | 44 | 61 | 1 | 1 | 41 | 263
13077 | 2019-01-04 | 2019-07-10 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-08-16 | COMP | 2019-08-23 | COMP | Rule 16 | 130 | 13 | 8 | 1 | 8 | 6 | 162
13183 | 2019-01-04 | 2019-07-16 | 2020-01-10 | 2020-01-10 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | 2021-01-19 | COMP | 2021-03-05 | COMP | Other | 134 | 123 | 225 | 1 | 34 | 33 | 545
13814 | 2019-01-04 | 2019-08-13 | 2019-11-20 | 2019-11-20 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2020-03-02 | COMP | 2020-03-27 | COMP | Rule 15/16 | 154 | 70 | 4 | 1 | 65 | 20 | 309
14690 | 2019-01-04 | 2019-09-23 | 2019-10-30 | 2019-10-30 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2019-12-19 | COMP | 2020-01-16 | COMP | Rule 16 | 182 | 28 | 21 | 1 | 14 | 19 | 260
15199 | 2019-01-04 | 2019-10-18 | 2020-01-09 | 2020-01-09 | COMP | 2020-03-11 | COMP | 2022-02-02 | COMP | 2022-02-24 | COMP | 2022-03-07 | COMP | Rule 16 | 201 | 55 | 43 | 480 | 16 | 8 | 798
16867 | 2019-01-04 | 2020-01-21 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-18 | COMP | 2020-05-11 | COMP | 2020-05-18 | COMP | 2020-06-30 | COMP | Rule 16 | 262 | 29 | 13 | 39 | 6 | 31 | 375
18275 | 2019-01-04 | 2020-03-18 | 2020-05-12 | 2020-05-12 | COMP | 2021-12-02 | COMP | 2021-12-02 | COMP | 2022-05-17 | COMP | 2022-06-23 | COMP | Rule 15/16 | 302 | 40 | 393 | 1 | 117 | 26 | 874
10250 | 2019-01-05 | 2019-03-08 | 2019-07-24 | 2020-10-15 | COMP | 2020-11-06 | COMP | 2020-11-17 | COMP | 2021-04-05 | COMP | 2021-04-22 | COMP | Rule 16 | 43 | 97 | 17 | 7 | 94 | 14 | 578
12186 | 2019-01-05 | 2019-05-28 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-27 | COMP | 2020-01-24 | COMP | 2020-01-30 | COMP | 2020-03-07 | COMP | Rule 16 | 99 | 109 | 21 | 38 | 5 | 26 | 293
10136 | 2019-01-06 | 2019-03-04 | 2019-05-20 | 2019-05-20 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP |  | INPR | 2020-10-14 | COMP | Rule 15/16 | 39 | 56 | 48 | 1 |  |  | 449
10979 | 2019-01-06 | 2019-04-07 | 2019-06-19 | 2020-03-16 | COMP | 2020-05-07 | COMP | 2019-07-17 | COMP | 2020-05-21 | COMP | 2020-09-22 | COMP | Rule 16 | 63 | 52 | 39 |  | 214 | 87 | 433
8926 | 2019-01-07 | 2019-01-08 | 2019-02-02 | 2021-12-09 | COMP | 2021-12-30 | COMP | 2021-12-30 | COMP | 2022-02-22 | COMP | 2022-02-22 | COMP | Rule 16 | 2 | 18 | 16 | 1 | 37 | 1 | 788
9212 | 2019-01-07 | 2019-01-22 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-16 | COMP | 2019-06-13 | COMP | 2019-12-29 | INPR | 2019-07-16 | COMP | Rule 16 | 11 | 57 | 4 | 42 |  |  | 133
9279 | 2019-01-07 | 2019-01-27 | 2019-04-17 | 2019-04-17 | COMP | 2019-04-18 | NOTN | 2019-04-18 | COMP | 2019-06-12 | COMP | 2019-07-15 | COMP | Other | 14 | 57 |  | 2 | 39 | 23 | 132
9323 | 2019-01-07 | 2019-01-30 | 2019-06-10 | 2019-07-05 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-08-21 | COMP | 2019-09-12 | COMP | Rule 15/16 | 17 | 92 | 10 | 1 | 25 | 16 | 174
9666 | 2019-01-07 | 2019-02-11 | 2019-04-26 | 2019-04-26 | COMP | 2019-04-30 | NOTN | 2019-04-30 | COMP | 2019-09-25 | COMP | 2019-10-14 | COMP | Other | 25 | 54 |  | 3 | 104 | 14 | 196
9669 | 2019-01-07 | 2019-02-11 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-26 | COMP | 2019-03-26 | COMP | 2019-07-21 | INPR | 2019-03-01 | COMP | Rule 16 | 25 | 17 | 15 | 1 |  |  | 38
9820 | 2019-01-07 | 2019-02-19 | 2019-04-13 | 2019-04-15 | COMP | 2019-04-16 | NOTN | 2019-04-16 | COMP | 2020-04-13 | COMP | 2020-04-23 | COMP | Other | 30 | 39 |  | 2 | 250 | 9 | 327
9821 | 2019-01-07 | 2019-02-19 | 2019-04-26 | 2019-04-26 | COMP | 2020-02-12 | NOTN | 2020-02-12 | COMP | 2020-04-13 | COMP | 2020-04-30 | COMP | Other | 30 | 49 |  | 200 | 43 | 14 | 332
9822 | 2019-01-07 | 2019-02-19 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-17 | NOTN | 2019-05-17 | COMP | 2020-04-13 | COMP | 2020-04-24 | COMP | Other | 30 | 63 |  | 2 | 227 | 10 | 328
10052 | 2019-01-07 | 2019-02-28 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-05-29 | COMP | 2019-05-30 | COMP | Rule 16 | 37 | 53 | 5 | 1 | 8 | 2 | 101
10286 | 2019-01-07 | 2019-03-08 | 2019-05-18 | 2019-05-18 | COMP | 2019-08-20 | COMP | 2020-01-13 | COMP | 2020-01-29 | COMP | 2020-02-03 | COMP | Rule 16 | 43 | 51 | 65 | 99 | 12 | 4 | 270
10417 | 2019-01-07 | 2019-03-15 | 2019-05-01 | 2019-05-01 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-09-20 | COMP | 2020-04-02 | COMP | Rule 15/16 | 48 | 34 | 52 | 1 | 49 | 133 | 312
10562 | 2019-01-07 | 2019-03-20 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-02 | COMP | 2019-10-31 | COMP | 2020-05-31 | INPR | 2019-11-07 | COMP | Rule 16 | 51 | 84 | 13 | 64 |  |  | 214
10602 | 2019-01-07 | 2019-03-21 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-24 | COMP | 2021-03-10 | COMP | 2021-03-02 | COMP | 2021-03-17 | COMP | Rule 16 | 52 | 47 | 21 | 430 | 0 | 6 | 552
11118 | 2019-01-07 | 2019-04-13 | 2019-08-08 | 2019-08-08 | COMP | 2019-12-06 | COMP | 2019-11-13 | COMP | 2019-11-26 | COMP | 2019-12-17 | COMP | Rule 16 | 68 | 82 | 83 |  | 10 | 14 | 239
11915 | 2019-01-07 | 2019-05-16 | 2019-10-07 | 2019-10-07 | COMP | 2019-12-30 | COMP | 2020-05-14 | COMP | 2021-02-10 | COMP | 2021-03-01 | COMP | Rule 16 | 92 | 100 | 57 | 96 | 187 | 13 | 540
11934 | 2019-01-07 | 2019-05-16 | 2019-08-22 | 2019-08-22 | COMP | 2019-10-01 | COMP | 2019-10-01 | COMP | 2020-06-10 | COMP | 2020-07-22 | COMP | Rule 16 | 92 | 69 | 28 | 1 | 174 | 31 | 390
11968 | 2019-01-07 | 2019-05-20 | 2019-08-21 | 2019-09-10 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2020-03-31 | COMP | 2020-07-01 | COMP | Rule 15/16 | 94 | 66 | 14 | 1 | 126 | 66 | 375
12369 | 2019-01-07 | 2019-06-04 | 2020-02-06 | 2020-02-06 | COMP | 2020-08-13 | COMP | 2021-03-02 | COMP | 2021-04-30 | COMP | 2021-09-01 | COMP | Rule 15/16 | 104 | 170 | 134 | 136 | 44 | 87 | 670
12402 | 2019-01-07 | 2019-06-05 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-19 | NOTN | 2019-06-19 | COMP | 2020-10-24 | INPR | 2019-08-27 | COMP | Other | 105 | 11 |  | 1 |  |  | 163
12619 | 2019-01-07 | 2019-06-17 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-08 | COMP | 2019-09-09 | COMP | 2019-12-06 | COMP | 2019-12-17 | COMP | Rule 16 | 113 | 29 | 9 | 22 | 62 | 8 | 239
12635 | 2019-01-07 | 2019-06-17 | 2019-08-06 | 2019-08-06 | COMP | 2019-12-18 | COMP | 2020-01-22 | COMP | 2019-12-19 | COMP | 2020-02-14 | COMP | Rule 16 | 113 | 36 | 93 | 23 | 0 | 18 | 279
13597 | 2019-01-07 | 2019-08-01 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-08 | COMP | 2020-01-14 | COMP | 2020-02-05 | COMP | 2020-03-05 | COMP | Rule 16 | 145 | 93 | 17 | 5 | 16 | 21 | 292
13644 | 2019-01-07 | 2019-08-05 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-30 | COMP | 2019-10-08 | COMP | 2019-12-11 | COMP | 2020-01-07 | COMP | Rule 16 | 147 | 20 | 21 | 7 | 44 | 18 | 252
28186 | 2019-01-07 | 2021-05-21 | 2021-06-10 | 2021-06-10 | COMP | 2021-07-14 | COMP | 2021-07-14 | COMP |  |  | 2021-09-13 | COMP | Rule 16 | 599 | 14 | 24 | 1 |  |  | 677
4151 | 2019-01-08 | 2019-04-15 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-08 | NOTN | 2019-08-08 | COMP | 2020-01-13 | COMP | 2020-12-17 | COMP | Other | 68 | 82 |  | 1 | 107 | 237 | 491
9118 | 2019-01-08 | 2019-01-18 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-07-22 | COMP | 2019-08-13 | COMP | Rule 16 | 9 | 40 | 51 | 1 | 39 | 17 | 152
9284 | 2019-01-08 | 2019-01-27 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-06-08 | COMP | 2019-07-09 | COMP | Rule 16 | 13 | 76 | 17 | 1 | 2 | 21 | 127
9599 | 2019-01-08 | 2019-02-07 | 2019-04-19 | 2019-04-19 | COMP | 2019-06-12 | COMP | 2020-01-21 | COMP | 2020-01-13 | COMP | 2020-02-25 | COMP | Rule 16 | 22 | 51 | 38 | 152 | 0 | 25 | 284
9623 | 2019-01-08 | 2019-02-09 | 2019-04-03 | 2019-05-13 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-06-04 | COMP | 2019-07-02 | COMP | Rule 16 | 23 | 37 | 2 | 1 | 15 | 21 | 123
9634 | 2019-01-08 | 2019-02-09 | 2019-05-26 | 2019-05-26 | COMP | 2019-06-11 | COMP | 2019-06-29 | COMP | 2019-07-24 | COMP | 2019-09-04 | COMP | Rule 16 | 23 | 74 | 11 | 14 | 17 | 30 | 167
9642 | 2019-01-08 | 2019-02-09 | 2019-04-18 | 2019-04-18 | COMP | 2019-05-10 | COMP | 2019-08-08 | COMP | 2023-04-30 | INPR | 2019-09-05 | COMP | Rule 16 | 23 | 48 | 17 | 63 |  |  | 168
9685 | 2019-01-08 | 2019-02-11 | 2019-04-17 | 2019-04-26 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-09-10 | COMP | 2019-10-07 | COMP | Rule 16 | 24 | 47 | 60 | 1 | 36 | 20 | 190
9708 | 2019-01-08 | 2019-02-12 | 2019-04-09 | 2019-04-09 | COMP | 2019-12-12 | COMP | 2020-01-16 | COMP | 2020-01-13 | COMP | 2020-02-19 | COMP | Rule 15/16 | 25 | 40 | 172 | 24 | 0 | 23 | 280
9812 | 2019-01-08 | 2019-02-19 | 2019-04-20 | 2019-04-20 | COMP | 2019-04-30 | COMP | 2019-11-01 | COMP | 2019-10-05 | COMP | 2019-11-05 | COMP | Rule 16 | 29 | 44 | 7 | 131 | 0 | 3 | 211
9927 | 2019-01-08 | 2019-02-22 | 2019-03-21 | 2019-04-04 | COMP | 2019-04-08 | COMP | 2019-04-09 | COMP | 2019-04-17 | COMP | 2019-05-07 | COMP | Rule 16 | 32 | 20 | 3 | 2 | 7 | 15 | 84
9931 | 2019-01-08 | 2019-02-23 | 2019-03-16 | 2019-03-16 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-07-09 | COMP | 2019-07-27 | COMP | Rule 16 | 32 | 15 | 58 | 1 | 23 | 14 | 140
9940 | 2019-01-08 | 2019-02-23 | 2019-05-10 | 2019-09-10 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2022-07-18 | COMP | 2023-04-20 | COMP | Rule 16 | 32 | 55 | 116 | 1 | 603 | 191 | 1078
10152 | 2019-01-08 | 2019-03-05 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-11 | COMP | 2019-07-11 | INPR | 2019-10-21 | REQD | 2019-07-13 | COMP | Rule 16 | 39 | 83 | 8 |  |  |  | 130
10264 | 2019-01-08 | 2019-03-07 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-22 | COMP | 2019-08-16 | COMP | 2019-09-19 | NOTN | 2019-11-15 | COMP | Rule 16 | 41 | 24 | 10 | 83 |  |  | 218
10290 | 2019-01-08 | 2019-03-09 | 2019-06-13 | 2019-06-13 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-07-30 | COMP | 2019-08-06 | COMP | Rule 16 | 42 | 68 | 25 | 1 | 9 | 6 | 147
10305 | 2019-01-08 | 2019-03-11 | 2019-08-21 | 2020-03-03 | COMP | 2020-09-17 | COMP | 2021-05-28 | COMP | 2021-07-30 | COMP | 2021-08-31 | COMP | Rule 15/16 | 43 | 116 | 141 | 175 | 44 | 23 | 668
10676 | 2019-01-08 | 2019-03-26 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-03 | COMP | 2019-06-17 | COMP | 2019-09-12 | COMP | 2019-10-25 | COMP | Rule 15/16 | 54 | 37 | 13 | 11 | 62 | 32 | 204
10800 | 2019-01-08 | 2019-03-29 | 2019-06-14 | 2019-06-14 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2019-10-23 | COMP | 2020-01-31 | COMP | Rule 16 | 57 | 55 | 36 | 1 | 57 | 67 | 268
10826 | 2019-01-08 | 2019-04-01 | 2019-08-20 | 2019-08-20 | COMP | 2019-12-13 | COMP | 2019-12-19 | COMP | 2019-11-22 | COMP | 2020-02-26 | COMP | Rule 15/16 | 58 | 100 | 80 | 5 | 0 | 46 | 285
11052 | 2019-01-08 | 2019-04-10 | 2019-11-08 | 2019-11-08 | COMP | 2019-11-22 | COMP | 2020-07-17 | COMP | 2020-08-13 | COMP | 2020-08-28 | COMP | Rule 15/16 | 65 | 150 | 10 | 164 | 20 | 12 | 416
11061 | 2019-01-08 | 2019-04-11 | 2019-06-17 | 2019-06-17 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-03-02 | COMP | 2020-07-25 | COMP | Rule 16 | 66 | 47 | 170 | 1 | 8 | 104 | 391
11372 | 2019-01-08 | 2019-04-24 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-21 | COMP | 2019-07-17 | COMP | 2020-06-03 | COMP | 2020-06-24 | COMP | Rule 16 | 75 | 16 | 5 | 40 | 222 | 16 | 369
11620 | 2019-01-08 | 2019-05-06 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-07 | COMP | 2019-08-08 | COMP | 2020-01-03 | COMP | 2020-02-04 | COMP | Rule 16 | 83 | 51 | 16 | 2 | 101 | 22 | 270
11723 | 2019-01-08 | 2019-05-08 | 2019-10-10 | 2019-10-10 | COMP | 2020-01-02 | COMP | 2020-02-26 | COMP | 2020-01-09 | COMP | 2020-03-09 | COMP | Rule 16 | 85 | 109 | 56 | 38 | 0 | 9 | 293
11855 | 2019-01-08 | 2019-05-14 | 2019-09-18 | 2019-09-18 | COMP | 2019-11-12 | COMP | 2019-11-25 | COMP | 2019-11-18 | COMP | 2019-12-14 | COMP | Rule 16 | 89 | 89 | 39 | 10 | 0 | 13 | 236
12166 | 2019-01-08 | 2019-05-24 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-03 | COMP | 2020-01-15 | COMP | 2020-01-03 | COMP | 2020-02-11 | COMP | Rule 16 | 97 | 101 | 32 | 30 | 0 | 19 | 275
12202 | 2019-01-08 | 2019-05-28 | 2019-07-29 | 2021-02-24 | COMP | 2021-03-22 | COMP | 2019-09-05 | COMP | 2022-05-17 | COMP | 2022-07-01 | COMP | Rule 16 | 98 | 44 | 19 |  | 680 | 32 | 878
12248 | 2019-01-08 | 2019-05-29 | 2020-04-09 | 2020-04-09 | COMP | 2020-05-12 | COMP | 2020-08-31 | COMP | 2020-08-25 | COMP | 2020-09-15 | COMP | Rule 16 | 99 | 218 | 24 | 79 | 0 | 11 | 427
13648 | 2019-01-08 | 2019-08-05 | 2019-08-31 | 2019-08-31 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-05-12 | COMP | 2020-05-28 | COMP | Rule 16 | 146 | 20 | 74 | 1 | 101 | 12 | 350
14266 | 2019-01-08 | 2019-09-03 | 2019-11-19 | 2020-07-07 | COMP | 2020-07-27 | COMP | 2020-12-28 | COMP | 2020-12-17 | COMP | 2021-01-13 | COMP | Rule 16 | 166 | 55 | 15 | 106 | 0 | 12 | 508
14827 | 2019-01-08 | 2019-09-30 | 2019-11-14 | 2019-11-14 | COMP | 2019-11-27 | COMP | 2019-12-09 | COMP |  | INPR | 2020-02-11 | COMP | Rule 16 | 185 | 33 | 10 | 7 |  |  | 275
15863 | 2019-01-08 | 2019-11-25 | 2020-02-13 | 2020-02-13 | COMP | 2020-03-03 | COMP | 2020-05-13 | COMP | 2020-03-13 | COMP | 2020-06-05 | COMP | Rule 16 | 224 | 54 | 13 | 52 | 0 | 17 | 356
16883 | 2019-01-08 | 2020-01-22 | 2020-03-09 | 2020-06-25 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-06-29 | COMP | 2020-08-13 | COMP | Rule 16 | 261 | 33 | 6 | 1 | 0 | 31 | 405
16885 | 2019-01-08 | 2020-01-22 | 2020-03-31 | 2020-06-02 | COMP | 2020-07-02 | COMP | 2020-04-24 | COMP | 2020-06-12 | COMP | 2020-07-01 | COMP | Rule 16 | 261 | 49 | 23 |  | 35 | 14 | 374
17864 | 2019-01-08 | 2020-03-03 | 2020-09-04 | 2020-09-04 | COMP | 2020-09-28 | COMP | 2022-03-25 | COMP |  | INPR | 2022-04-06 | COMP | Rule 16 | 289 | 133 | 16 | 375 |  |  | 818
22502 | 2019-01-08 | 2020-09-28 | 2020-12-10 | 2020-12-10 | COMP | 2021-02-16 | COMP | 2021-04-14 | COMP | 2021-04-21 | COMP | 2021-04-29 | COMP | Rule 16 | 436 | 51 | 45 | 42 | 6 | 7 | 582
4075 | 2019-01-09 | 2019-01-09 | 2019-02-13 | 2019-02-13 | COMP | 2019-02-25 | COMP | 2019-05-02 | COMP | 2019-06-18 | COMP | 2019-08-09 | COMP | Rule 16 | 1 | 25 | 8 | 49 | 33 | 38 | 149
9062 | 2019-01-09 | 2019-01-15 | 2019-04-19 | 2019-06-03 | COMP | 2019-07-08 | COMP | 2019-08-21 | COMP | 2019-07-08 | COMP | 2019-12-02 | COMP | Rule 16 | 5 | 67 | 25 | 33 | 0 | 70 | 226
9081 | 2019-01-09 | 2019-01-16 | 2019-02-15 | 2019-04-06 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-12-29 | INPR | 2019-08-31 | COMP | Rule 15/16 | 6 | 22 | 45 | 1 |  |  | 164
9096 | 2019-01-09 | 2019-01-16 | 2019-07-02 | 2019-07-02 | COMP | 2019-08-06 | COMP | 2019-10-10 | COMP | 2019-10-15 | COMP | 2019-11-07 | COMP | Rule 16 | 6 | 117 | 25 | 47 | 4 | 18 | 212
9104 | 2019-01-09 | 2019-01-17 | 2019-05-22 | 2019-05-22 | COMP | 2019-05-30 | COMP | 2019-07-29 | COMP | 2019-07-17 | COMP | 2019-08-12 | COMP | Rule 15/16 | 7 | 88 | 6 | 42 | 0 | 11 | 150
9518 | 2019-01-09 | 2019-02-06 | 2019-07-13 | 2020-08-10 | COMP | 2020-09-23 | COMP | 2020-11-28 | COMP | 2021-01-06 | COMP | 2021-02-09 | COMP | Rule 16 | 20 | 110 | 32 | 45 | 26 | 24 | 525
9547 | 2019-01-09 | 2019-02-07 | 2019-03-18 | 2019-03-18 | COMP | 2019-05-24 | COMP | 2019-08-13 | COMP | 2019-10-28 | COMP | 2019-11-14 | COMP | Rule 16 | 21 | 27 | 50 | 56 | 54 | 13 | 216
9570 | 2019-01-09 | 2019-02-07 | 2019-03-07 | 2019-03-07 | COMP | 2019-04-11 | COMP | 2019-04-12 | COMP | 2019-04-09 | COMP | 2019-04-22 | COMP | Rule 16 | 21 | 20 | 26 | 2 | 0 | 7 | 72
9573 | 2019-01-09 | 2019-02-07 | 2019-04-09 | 2019-04-09 | COMP | 2019-05-01 | COMP | 2019-05-01 | COMP | 2019-09-22 | INPR | 2019-05-23 | COMP | Rule 16 | 21 | 43 | 17 | 1 |  |  | 95
9769 | 2019-01-09 | 2019-02-14 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-01 | COMP | 2019-05-25 | COMP | Rule 16 | 26 | 49 | 7 | 1 | 0 | 17 | 96
9938 | 2019-01-09 | 2019-02-23 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-14 | COMP | 2019-12-16 | COMP | 2019-11-21 | COMP | 2020-01-06 | COMP | Rule 16 | 31 | 45 | 13 | 149 | 0 | 14 | 249
9969 | 2019-01-09 | 2019-02-25 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-17 | NOTN | 2019-05-17 | COMP | 2019-07-11 | COMP | 2019-08-23 | COMP | Other | 32 | 59 |  | 2 | 38 | 32 | 159
10030 | 2019-01-09 | 2019-02-27 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-03 | COMP | 2019-06-12 | COMP | 2019-06-03 | COMP | 2019-07-11 | COMP | Rule 16 | 34 | 63 | 5 | 8 | 0 | 21 | 128
10109 | 2019-01-09 | 2019-03-04 | 2019-05-16 | 2019-05-16 | COMP | 2019-07-10 | COMP | 2019-08-23 | COMP | 2019-11-05 | COMP | 2019-11-09 | COMP | Rule 16 | 37 | 54 | 38 | 33 | 52 | 4 | 213
10443 | 2019-01-09 | 2019-03-16 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-06 | COMP | 2020-02-06 | COMP | 2020-05-20 | COMP | 2020-07-21 | COMP | Rule 16 | 46 | 94 | 29 | 104 | 74 | 44 | 387
10486 | 2019-01-09 | 2019-03-18 | 2019-06-20 | 2019-06-20 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2019-11-01 | COMP | 2019-12-30 | COMP | Rule 16 | 47 | 68 | 31 | 1 | 65 | 38 | 245
10638 | 2019-01-09 | 2019-03-23 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2019-11-04 | COMP | 2019-12-31 | COMP | Rule 16 | 51 | 87 | 8 | 1 | 65 | 38 | 246
10769 | 2019-01-09 | 2019-03-29 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-24 | COMP | 2019-08-31 | COMP | Rule 16 | 56 | 67 | 10 | 1 | 7 | 28 | 164
10846 | 2019-01-09 | 2019-04-02 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-18 | COMP | 2019-04-29 | COMP | 2019-05-02 | COMP | 2019-05-06 | COMP | Rule 16 | 58 | 4 | 9 | 8 | 4 | 3 | 82
10955 | 2019-01-09 | 2019-04-05 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-05-14 | COMP | 2019-07-17 | COMP | Rule 16 | 61 | 16 | 6 | 1 | 8 | 45 | 132
11027 | 2019-01-09 | 2019-04-09 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-05-28 | COMP | 2019-05-29 | COMP | Rule 16 | 63 | 3 | 27 | 1 | 7 | 2 | 98
11992 | 2019-01-09 | 2019-05-20 | 2019-08-29 | 2019-08-29 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-10-14 | COMP | 2020-02-19 | COMP | Rule 16 | 92 | 72 | 31 | 1 | 2 | 86 | 279
12291 | 2019-01-09 | 2019-05-30 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-21 | COMP | 2019-12-16 | COMP | 2019-11-27 | COMP | 2020-01-27 | COMP | Rule 16 | 99 | 85 | 39 | 16 | 0 | 28 | 263
12444 | 2019-01-09 | 2019-06-06 | 2019-10-12 | 2019-10-12 | COMP | 2020-01-08 | COMP | 2020-06-16 | INPR | 2020-06-16 | COMP | 2020-06-29 | COMP | Rule 15/16 | 104 | 90 | 58 |  |  |  | 371
12494 | 2019-01-09 | 2019-06-10 | 2019-09-17 | 2019-09-17 | COMP | 2019-10-04 | COMP | 2019-10-28 | COMP | 2023-09-02 | INPR | 2020-12-02 | COMP | Rule 16 | 106 | 70 | 14 | 17 |  |  | 479
12675 | 2019-01-09 | 2019-06-19 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-09 | COMP | 2020-01-10 | COMP | 2020-05-31 | INPR | 2020-02-13 | COMP | Rule 15/16 | 113 | 116 | 25 | 2 |  |  | 276
12875 | 2019-01-09 | 2019-06-26 | 2020-02-24 | 2020-02-24 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-11-12 | COMP | 2020-12-23 | COMP | Rule 16 | 118 | 165 | 40 | 1 | 147 | 28 | 494
13598 | 2019-01-09 | 2019-08-01 | 2020-01-17 | 2020-01-17 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-08-29 | COMP | 2021-06-05 | COMP | Rule 15/16 | 143 | 116 | 79 | 1 | 80 | 191 | 606
13780 | 2019-01-09 | 2019-08-09 | 2020-01-17 | 2020-01-17 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-08-29 | COMP | 2020-09-21 | COMP | Rule 15/16 | 149 | 110 | 79 | 1 | 80 | 15 | 430
14090 | 2019-01-09 | 2019-08-24 | 2019-11-21 | 2019-11-21 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-04-22 | COMP | 2020-06-03 | COMP | Rule 16 | 159 | 62 | 60 | 1 | 45 | 30 | 353
14440 | 2019-01-09 | 2019-09-10 | 2020-05-26 | 2020-05-26 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2021-02-23 | COMP | 2021-03-26 | COMP | Rule 15/16 | 170 | 178 | 109 | 1 | 80 | 24 | 557
14596 | 2019-01-09 | 2019-09-18 | 2019-10-04 | 2019-10-04 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2019-12-10 | COMP | 2020-01-06 | COMP | Rule 16 | 176 | 13 | 35 | 1 | 11 | 18 | 249
14641 | 2019-01-09 | 2019-09-21 | 2019-10-31 | 2019-10-31 | COMP | 2019-11-07 | COMP | 2020-02-26 | COMP | 2020-05-20 | COMP | 2020-06-08 | COMP | Rule 16 | 178 | 29 | 6 | 73 | 61 | 13 | 356
15943 | 2019-01-09 | 2019-12-02 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-23 | COMP | 2020-01-29 | COMP | 2020-02-10 | COMP | 2020-02-24 | COMP | Rule 16 | 226 | 28 | 9 | 5 | 9 | 10 | 282
18357 | 2019-01-09 | 2020-03-20 | 2020-11-18 | 2021-02-23 | COMP | 2021-03-03 | COMP | 2021-12-02 | COMP | 2021-12-01 | COMP | 2022-02-02 | COMP | Rule 16 | 301 | 171 | 7 | 191 | 0 | 44 | 773
18493 | 2019-01-09 | 2020-03-26 | 2021-03-03 | 2021-03-03 | COMP | 2021-03-11 | COMP | 2021-03-11 | COMP | 2023-10-10 | COMP | 2023-10-26 | COMP | Rule 16 | 305 | 236 | 7 | 1 | 651 | 13 | 1208
4133 | 2019-01-10 | 2019-03-21 | 2019-07-08 | 2019-11-21 | COMP | 2020-07-14 | COMP | 2020-08-26 | COMP |  | INPR | 2020-12-09 | COMP | Rule 15/16 | 49 | 76 | 162 | 32 |  |  | 483
8992 | 2019-01-10 | 2019-01-11 | 2021-05-25 | 2022-03-24 | COMP | 2022-05-26 | COMP | 2022-12-09 | COMP | 2022-11-30 | COMP | 2023-02-08 | COMP | Rule 16 | 2 | 597 | 46 | 135 | 0 | 41 | 1026
9098 | 2019-01-10 | 2019-01-16 | 2019-02-23 | 2019-02-23 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-07-10 | COMP | 2019-07-23 | COMP | Rule 16 | 5 | 26 | 97 | 1 | 0 | 9 | 135
9292 | 2019-01-10 | 2019-01-28 | 2019-03-16 | 2019-03-16 | COMP | 2019-06-25 | COMP | 2019-06-26 | COMP | 2019-07-19 | COMP | 2019-08-05 | COMP | Rule 16 | 12 | 34 | 71 | 2 | 17 | 12 | 144
9354 | 2019-01-10 | 2019-02-01 | 2019-11-27 | 2020-06-22 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-08-05 | COMP | 2021-01-25 | COMP | Rule 15/16 | 16 | 209 | 32 | 1 | 2 | 117 | 513
9453 | 2019-01-10 | 2019-02-04 | 2019-04-20 | 2019-04-20 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-08-23 | COMP | 2019-10-11 | COMP | Rule 16 | 17 | 54 | 32 | 1 | 57 | 35 | 192
10048 | 2019-01-10 | 2019-02-28 | 2019-05-07 | 2019-05-07 | COMP | 2019-07-30 | COMP | 2019-09-10 | COMP | 2019-12-03 | COMP | 2020-01-07 | COMP | Rule 16 | 34 | 49 | 59 | 30 | 58 | 24 | 249
10360 | 2019-01-10 | 2019-03-12 | 2019-05-09 | 2019-05-09 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-05-22 | COMP | 2019-07-09 | COMP | Rule 16 | 42 | 43 | 7 | 1 | 4 | 33 | 125
10396 | 2019-01-10 | 2019-03-14 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-26 | COMP | 2019-08-05 | COMP | 2020-02-29 | INPR | 2019-11-06 | COMP | Rule 16 | 44 | 52 | 22 | 28 |  |  | 210
10526 | 2019-01-10 | 2019-03-19 | 2019-06-24 | 2019-06-24 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-12-29 | INPR | 2019-08-15 | COMP | Rule 16 | 47 | 69 | 17 | 1 |  |  | 152
10527 | 2019-01-10 | 2019-03-19 | 2019-05-29 | 2019-05-29 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2020-05-21 | COMP | 2020-07-01 | COMP | Rule 16 | 47 | 51 | 66 | 1 | 183 | 29 | 372
10543 | 2019-01-10 | 2019-03-20 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-19 | COMP | 2019-08-29 | COMP | 2019-09-12 | COMP | 2019-10-01 | COMP | Rule 15/16 | 48 | 87 | 21 | 9 | 10 | 14 | 184
10789 | 2019-01-10 | 2019-03-29 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-14 | COMP | 2019-08-12 | COMP | 2023-11-11 | INPR | 2019-09-12 | COMP | Rule 16 | 55 | 49 | 7 | 41 |  |  | 171
10809 | 2019-01-10 | 2019-04-01 | 2019-11-25 | 2019-11-25 | COMP | 2020-01-29 | COMP | 2020-09-09 | COMP | 2023-08-04 | COMP | 2023-08-14 | COMP | Rule 16 | 56 | 167 | 43 | 158 | 729 | 7 | 1155
10871 | 2019-01-10 | 2019-04-02 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-14 | COMP | 2020-02-10 | COMP | 2020-02-07 | COMP | 2020-03-05 | COMP | Rule 16 | 57 | 22 | 10 | 186 | 0 | 18 | 289
10997 | 2019-01-10 | 2019-04-08 | 2019-05-14 | 2019-05-14 | COMP | 2019-07-02 | COMP | 2019-07-03 | COMP | 2019-07-30 | COMP | 2019-08-21 | COMP | Rule 16 | 61 | 27 | 35 | 2 | 19 | 17 | 156
11132 | 2019-01-10 | 2019-04-15 | 2019-06-07 | 2019-06-07 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2021-01-02 | INPR | 2019-11-15 | COMP | Rule 16 | 66 | 39 | 31 | 1 |  |  | 216
11185 | 2019-01-10 | 2019-04-16 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-16 | NOTN | 2019-05-16 | COMP | 2019-05-21 | COMP | 2019-07-29 | COMP | Other | 67 | 23 |  | 1 | 4 | 48 | 139
11226 | 2019-01-10 | 2019-04-18 | 2019-07-26 | 2019-07-27 | COMP | 2019-07-31 | COMP | 2019-09-09 | COMP | 2019-08-01 | COMP | 2019-11-14 | COMP | Rule 16 | 69 | 70 | 3 | 28 | 0 | 48 | 215
11444 | 2019-01-10 | 2019-04-27 | 2019-09-12 | 2022-09-21 | COMP | 2022-10-19 | COMP | 2022-10-25 | COMP | 2023-06-29 | COMP | 2023-07-26 | COMP | Rule 16 | 75 | 96 | 21 | 5 | 169 | 19 | 1142
11501 | 2019-01-10 | 2019-04-30 | 2019-08-22 | 2019-08-27 | COMP | 2019-09-16 | COMP | 2019-11-19 | COMP | 2019-12-04 | COMP | 2019-12-19 | COMP | Rule 16 | 77 | 81 | 14 | 46 | 10 | 12 | 238
11812 | 2019-01-10 | 2019-05-13 | 2019-09-05 | 2019-09-05 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-25 | COMP | 2020-01-16 | COMP | Rule 16 | 86 | 81 | 44 | 1 | 14 | 35 | 256
12231 | 2019-01-10 | 2019-05-29 | 2019-09-16 | 2020-11-05 | COMP | 2020-11-23 | COMP | 2021-02-24 | COMP | 2023-12-03 | INPR | 2021-04-16 | COMP | Rule 16 | 97 | 77 | 12 | 62 |  |  | 571
12269 | 2019-01-10 | 2019-05-29 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-01-08 | COMP | 2020-02-23 | COMP | Rule 16 | 97 | 90 | 14 | 1 | 52 | 31 | 280
12811 | 2019-01-10 | 2019-06-24 | 2019-09-28 | 2019-11-28 | COMP | 2020-02-26 | COMP | 2020-04-07 | COMP | 2020-02-18 | COMP | 2020-06-23 | COMP | Rule 15/16 | 115 | 68 | 59 | 30 | 0 | 55 | 366
13651 | 2019-01-10 | 2019-08-06 | 2019-09-16 | 2019-09-16 | COMP | 2019-12-02 | COMP | 2020-02-21 | COMP | 2020-02-20 | COMP | 2020-04-07 | COMP | Rule 16 | 145 | 29 | 53 | 56 | 0 | 33 | 312
13774 | 2019-01-10 | 2019-08-08 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-09-12 | COMP | 2019-09-26 | COMP | Rule 16 | 147 | 12 | 8 | 1 | 7 | 11 | 181
14423 | 2019-01-10 | 2019-09-10 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-01-13 | COMP | 2020-01-20 | COMP | Rule 16 | 169 | 51 | 14 | 1 | 22 | 5 | 257
14502 | 2019-01-10 | 2019-09-13 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-03-06 | COMP | 2020-06-01 | COMP | Rule 16 | 172 | 79 | 16 | 1 | 26 | 61 | 350
14738 | 2019-01-10 | 2019-09-25 | 2020-01-25 | 2020-01-25 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2021-03-04 | COMP | 2021-03-23 | COMP | Rule 16 | 180 | 82 | 19 | 1 | 261 | 14 | 553
16194 | 2019-01-10 | 2019-12-13 | 2020-03-30 | 2020-03-30 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2021-03-26 | COMP | 2021-04-27 | COMP | Rule 16 | 234 | 73 | 59 | 1 | 193 | 23 | 578
9001 | 2019-01-11 | 2019-01-12 | 2019-02-09 | 2019-02-09 | COMP | 2019-05-29 | COMP | 2019-06-21 | COMP | 2021-01-30 | INPR | 2020-01-24 | COMP | Rule 16 | 1 | 19 | 76 | 18 |  |  | 260
9880 | 2019-01-11 | 2019-02-21 | 2019-04-12 | 2019-04-12 | COMP | 2019-04-12 | NOTN | 2020-01-30 | COMP | 2020-02-07 | NOTN | 2020-07-03 | COMP | Other | 28 | 37 |  | 201 |  |  | 373
9982 | 2019-01-11 | 2019-02-25 | 2019-05-09 | 2019-06-17 | COMP | 2019-07-12 | COMP | 2019-07-18 | COMP | 2019-08-21 | COMP | 2019-07-31 | COMP | Rule 16 | 30 | 54 | 19 | 5 | 25 |  | 140
10342 | 2019-01-11 | 2019-03-12 | 2019-08-09 | 2019-08-13 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-11-18 | COMP | 2019-12-20 | COMP | Rule 15/16 | 41 | 107 | 19 | 1 | 50 | 23 | 238
10735 | 2019-01-11 | 2019-03-28 | 2019-07-13 | 2019-07-13 | COMP | 2019-09-13 | COMP | 2019-10-01 | COMP | 2020-11-23 | COMP | 2020-12-11 | COMP | Rule 16 | 53 | 75 | 44 | 13 | 290 | 13 | 484
11844 | 2019-01-11 | 2019-05-14 | 2019-06-24 | 2019-06-24 | COMP | 2019-09-09 | NOTN | 2019-09-11 | COMP | 2019-09-09 | COMP | 2019-09-13 | COMP | Other | 86 | 29 |  | 56 | 0 | 3 | 171
12008 | 2019-01-11 | 2019-05-20 | 2019-07-01 | 2019-07-01 | COMP | 2019-08-05 | COMP | 2019-08-21 | INPR | 2021-02-27 | REQD | 2019-08-28 | COMP | Rule 16 | 90 | 30 | 25 |  |  |  | 160
12177 | 2019-01-11 | 2019-05-29 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-17 | COMP | 2020-03-06 | COMP | 2020-05-15 | COMP | 2020-06-29 | COMP | Rule 16 | 96 | 143 | 19 | 34 | 51 | 31 | 369
12207 | 2019-01-11 | 2019-05-28 | 2020-02-10 | 2020-02-13 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-06-26 | COMP | 2020-08-19 | COMP | Rule 16 | 95 | 177 | 54 | 1 | 42 | 39 | 406
12310 | 2019-01-11 | 2019-05-30 | 2019-09-18 | 2019-09-21 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-03-05 | COMP | 2020-04-01 | COMP | Rule 16 | 97 | 78 | 82 | 1 | 31 | 20 | 307
12374 | 2019-01-11 | 2019-06-04 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-07-01 | COMP | 2019-09-23 | COMP | Rule 16 | 100 | 28 | 15 | 1 | 0 | 37 | 177
12704 | 2019-01-11 | 2019-06-19 | 2019-08-02 | 2019-08-02 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-12-19 | NOTN | 2020-01-29 | COMP | Rule 16 | 111 | 32 | 36 | 1 |  |  | 263
12788 | 2019-01-11 | 2019-06-21 | 2019-08-30 | 2019-08-30 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-06-24 | COMP | 2020-08-10 | COMP | Rule 16 | 113 | 50 | 204 | 1 | 2 | 34 | 399
14076 | 2019-01-11 | 2019-08-24 | 2019-12-23 | 2020-03-08 | COMP | 2020-05-18 | COMP | 2020-05-19 | COMP | 2021-01-06 | COMP | 2021-03-22 | COMP | Rule 16 | 157 | 82 | 51 | 2 | 160 | 52 | 551
14383 | 2019-01-11 | 2019-09-08 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-12 | COMP | 2020-02-05 | COMP | 2021-08-11 | COMP | 2021-08-16 | COMP | Rule 16 | 166 | 30 | 16 | 57 | 384 | 4 | 654
14534 | 2019-01-11 | 2019-09-17 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-05-26 | COMP | 2020-06-05 | COMP | Rule 16 | 173 | 106 | 26 | 1 | 43 | 9 | 353
14681 | 2019-01-11 | 2019-09-23 | 2019-11-25 | 2019-11-25 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2020-10-28 | COMP | 2020-12-11 | COMP | Rule 16 | 177 | 45 | 19 | 1 | 217 | 30 | 484
14767 | 2019-01-11 | 2019-09-26 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-17 | COMP |  | REQD |  | REQD | 2021-12-02 | COMP | Rule 15/16 | 180 | 155 | 50 |  |  |  | 728
18949 | 2019-01-11 | 2020-04-14 | 2020-07-21 | 2020-07-21 | COMP | 2020-07-27 | COMP | 2020-08-22 | COMP | 2020-09-15 | COMP | 2020-09-23 | COMP | Rule 16 | 316 | 70 | 5 | 20 | 16 | 7 | 430
22426 | 2019-01-11 | 2020-09-24 | 2020-10-23 | 2021-02-25 | COMP | 2021-03-22 | COMP | 2021-03-22 | COMP | 2021-04-06 | COMP | 2021-05-07 | COMP | Rule 16 | 431 | 22 | 18 | 1 | 12 | 24 | 585
10775 | 2019-01-12 | 2019-03-29 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-07-30 | COMP | 2019-08-03 | COMP | Rule 16 | 53 | 36 | 8 | 1 | 44 | 4 | 141
11287 | 2019-01-12 | 2019-04-22 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-08-29 | COMP | 2020-02-28 | COMP | Rule 16 | 69 | 49 | 17 | 1 | 28 | 124 | 283
13751 | 2019-01-12 | 2019-08-07 | 2019-10-11 | 2019-12-20 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-10-23 | COMP | 2021-01-05 | COMP | Rule 15/16 | 144 | 47 | 60 | 1 | 156 | 48 | 498
16850 | 2019-01-12 | 2020-01-22 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-04 | COMP | 2020-06-22 | COMP | 2022-07-30 | INPR | 2020-09-21 | COMP | Rule 16 | 257 | 87 | 9 | 13 |  |  | 427
9451 | 2019-01-13 | 2019-02-05 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-09 | COMP | 2019-04-11 | COMP | 2019-06-17 | COMP | 2019-07-18 | COMP | Rule 16 | 16 | 37 | 9 | 3 | 47 | 23 | 130
9797 | 2019-01-13 | 2019-02-16 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-20 | NOTN | 2019-09-30 | COMP | 2019-09-20 | COMP | 2019-12-18 | COMP | Other | 24 | 119 |  | 39 | 0 | 55 | 235
13492 | 2019-01-13 | 2019-07-28 | 2020-02-07 | 2020-02-07 | COMP | 2020-03-16 | COMP | 2020-04-10 | COMP | 2020-07-21 | COMP | 2020-09-25 | COMP | Rule 15/16 | 136 | 133 | 26 | 20 | 72 | 48 | 431
16941 | 2019-01-13 | 2020-01-24 | 2020-03-06 | 2020-04-14 | COMP | 2020-05-13 | COMP | 2021-02-12 | COMP | 2021-02-09 | COMP | 2021-03-17 | COMP | Rule 15/16 | 259 | 30 | 22 | 190 | 0 | 23 | 547
9086 | 2019-01-14 | 2019-01-16 | 2019-04-24 | 2019-05-02 | COMP | 2019-05-03 | NOTN | 2019-06-12 | COMP | 2019-07-15 | COMP | 2019-09-03 | COMP | Other | 3 | 69 |  | 29 | 23 | 36 | 162
9112 | 2019-01-14 | 2019-01-17 | 2019-04-10 | 2019-04-10 | COMP | 2019-05-08 | COMP | 2019-09-04 | COMP | 2019-10-22 | COMP | 2019-11-05 | COMP | Rule 16 | 4 | 58 | 21 | 83 | 35 | 11 | 207
9327 | 2019-01-14 | 2019-01-30 | 2019-02-22 | 2019-02-22 | COMP | 2019-02-26 | COMP | 2019-02-26 | COMP | 2019-02-28 | COMP | 2019-04-02 | COMP | Rule 16 | 12 | 17 | 3 | 1 | 3 | 24 | 55
9491 | 2019-01-14 | 2019-02-06 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-17 | COMP | 2019-07-01 | COMP | 2021-02-24 | COMP | 2021-04-14 | COMP | Rule 16 | 17 | 57 | 16 | 31 | 415 | 36 | 567
9627 | 2019-01-14 | 2019-02-08 | 2019-04-11 | 2019-04-11 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-07-15 | COMP | 2019-07-22 | COMP | Rule 16 | 19 | 44 | 13 | 1 | 54 | 6 | 132
9731 | 2019-01-14 | 2019-02-13 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-03-09 | COMP | 2020-03-11 | COMP | Rule 15/16 | 22 | 231 | 27 | 1 | 12 | 3 | 291
9732 | 2019-01-14 | 2019-02-13 | 2019-11-06 | 2019-11-06 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-03-19 | COMP | 2020-04-04 | COMP | Rule 15/16 | 22 | 187 | 91 | 1 | 0 | 11 | 308
9742 | 2019-01-14 | 2019-02-13 | 2020-06-02 | 2020-06-02 | COMP | 2020-10-21 | COMP | 2020-11-04 | COMP | 2020-12-28 | COMP | 2021-01-29 | COMP | Rule 16 | 22 | 328 | 101 | 11 | 35 | 23 | 515
9941 | 2019-01-14 | 2019-02-23 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-15 | COMP | 2019-05-15 | COMP | 2019-09-24 | COMP | 2019-10-09 | COMP | Rule 16 | 28 | 53 | 6 | 1 | 92 | 12 | 188
10081 | 2019-01-14 | 2019-03-01 | 2019-03-29 | 2019-03-29 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2021-08-24 | COMP | Rule 16 | 33 | 21 | 278 | 1 | 1 | 330 | 659
10087 | 2019-01-14 | 2019-03-01 | 2019-05-09 | 2021-08-11 | COMP | 2021-08-23 | COMP | 2021-08-23 | COMP |  | INPR | 2023-08-10 | COMP | Rule 15/16 | 33 | 50 | 9 | 1 |  |  | 1151
10179 | 2019-01-14 | 2019-03-05 | 2019-11-25 | 2019-11-25 | COMP | 2020-03-09 | COMP | 2021-09-18 | COMP | 2021-09-18 | COMP | 2021-11-03 | COMP | Rule 15/16 | 35 | 186 | 70 | 388 | 0 | 33 | 709
10294 | 2019-01-14 | 2019-03-09 | 2019-05-11 | 2019-05-11 | COMP | 2019-07-22 | COMP | 2019-07-26 | COMP | 2020-01-07 | COMP | 2020-02-07 | COMP | Rule 16 | 38 | 45 | 49 | 5 | 112 | 23 | 269
10327 | 2019-01-14 | 2019-03-11 | 2019-07-12 | 2020-01-16 | COMP | 2020-01-24 | COMP | 2019-10-04 | COMP | 2020-08-14 | COMP | 2020-11-20 | COMP | Rule 16 | 39 | 88 | 6 |  | 218 | 69 | 470
10348 | 2019-01-14 | 2019-03-12 | 2019-03-19 | 2019-03-19 | COMP | 2019-03-25 | COMP | 2019-03-25 | INPR | 2019-04-22 | COMP | 2019-04-23 | COMP | Rule 16 | 40 | 6 | 5 |  |  |  | 70
10542 | 2019-01-14 | 2019-03-20 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-24 | NOTN | 2019-06-24 | COMP | 2019-08-08 | COMP | 2019-09-04 | COMP | Other | 46 | 46 |  | 23 | 33 | 19 | 163
10663 | 2019-01-14 | 2019-03-25 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-09-05 | COMP | Rule 16 | 49 | 68 | 19 | 1 | 1 | 31 | 164
10870 | 2019-01-14 | 2019-04-02 | 2019-06-27 | 2019-06-27 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-10-01 | COMP | 2019-11-15 | COMP | Rule 16 | 55 | 62 | 56 | 1 | 12 | 33 | 214
10913 | 2019-01-14 | 2019-04-04 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-19 | COMP | 2020-01-31 | COMP | 2019-12-20 | COMP | 2020-03-04 | COMP | Rule 16 | 57 | 45 | 10 | 155 | 0 | 23 | 286
11151 | 2019-01-14 | 2019-04-15 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-23 | COMP | 2019-07-31 | COMP | 2019-07-30 | COMP | 2019-08-19 | COMP | Rule 16 | 64 | 63 | 8 | 7 | 0 | 14 | 152
11829 | 2019-01-14 | 2019-05-14 | 2019-10-10 | 2019-10-10 | COMP | 2019-11-01 | COMP | 2020-07-08 | COMP | 2020-07-09 | COMP | 2020-08-11 | COMP | Rule 16 | 85 | 105 | 17 | 171 | 2 | 24 | 399
11982 | 2019-01-14 | 2019-05-20 | 2019-07-11 | 2019-07-24 | COMP | 2019-08-19 | COMP | 2019-10-08 | INPR | 2019-09-23 | COMP | 2019-10-17 | COMP | Rule 16 | 89 | 37 | 19 |  |  |  | 194
11984 | 2019-01-14 | 2019-05-20 | 2019-07-13 | 2019-07-13 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-03 | COMP | 2020-04-17 | COMP | Rule 15/16 | 89 | 38 | 158 | 1 | 2 | 34 | 318
12229 | 2019-01-14 | 2019-05-28 | 2020-08-25 | 2020-08-25 | COMP | 2020-12-04 | COMP | 2021-08-19 | COMP |  |  | 2021-09-22 | COMP | Rule 16 | 94 | 316 | 70 | 179 |  |  | 679
12410 | 2019-01-14 | 2019-06-06 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-15 | COMP | 2022-08-21 | REQD | 2022-08-21 | REQD | 2019-09-06 | COMP | Rule 16 | 101 | 16 | 12 |  |  |  | 165
12495 | 2019-01-14 | 2019-06-10 | 2019-07-31 | 2019-07-31 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-09-12 | COMP | 2019-10-14 | COMP | Rule 16 | 103 | 37 | 30 | 1 | 2 | 23 | 191
12624 | 2019-01-14 | 2019-06-18 | 2019-08-29 | 2019-08-29 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-10-31 | COMP | 2020-01-27 | COMP | Rule 15/16 | 109 | 52 | 21 | 1 | 25 | 57 | 260
13062 | 2019-01-14 | 2019-07-09 | 2020-03-08 | 2020-08-31 | COMP | 2020-10-05 | COMP | 2021-02-23 | COMP | 2020-12-02 | COMP | 2021-06-04 | COMP | Rule 15/16 | 123 | 166 | 25 | 95 | 0 | 73 | 603
13421 | 2019-01-14 | 2019-07-24 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-11 | COMP | 2019-10-18 | COMP | 2020-01-23 | COMP | 2020-02-26 | COMP | Rule 16 | 134 | 32 | 4 | 28 | 64 | 24 | 281
13664 | 2019-01-14 | 2019-08-05 | 2019-11-21 | 2019-11-21 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2021-01-20 | COMP | 2021-03-02 | COMP | Rule 16 | 142 | 77 | 48 | 1 | 244 | 29 | 536
14410 | 2019-01-14 | 2019-09-09 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-25 | COMP | 2021-09-10 | COMP | 2022-03-23 | COMP | 2022-05-02 | COMP | Rule 16 | 166 | 30 | 25 | 452 | 134 | 29 | 832
15115 | 2019-01-14 | 2019-10-14 | 2020-05-20 | 2020-12-07 | COMP | 2021-01-13 | COMP | 2021-05-20 | COMP | 2021-09-06 | COMP | 2021-10-04 | COMP | Rule 15/16 | 191 | 151 | 26 | 90 | 75 | 20 | 687
9201 | 2019-01-15 | 2019-01-22 | 2019-02-26 | 2019-02-26 | COMP | 2019-04-08 | COMP | 2019-04-08 | COMP | 2020-04-26 | INPR | 2019-06-21 | COMP | Rule 16 | 5 | 25 | 30 | 1 |  |  | 111
9220 | 2019-01-15 | 2019-01-23 | 2019-12-16 | 2019-12-16 | COMP | 2019-12-20 | COMP | 2020-01-14 | COMP | 2020-03-13 | COMP | 2020-07-03 | COMP | Rule 15/16 | 6 | 227 | 5 | 16 | 42 | 80 | 371
9281 | 2019-01-15 | 2019-01-27 | 2019-03-26 | 2019-03-26 | COMP | 2019-07-09 | COMP | 2019-08-13 | COMP | 2019-07-11 | COMP | 2019-09-10 | COMP | Rule 16 | 8 | 41 | 74 | 26 | 0 | 20 | 166
9283 | 2019-01-15 | 2019-01-27 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-28 | COMP | 2019-06-04 | COMP | 2019-06-27 | COMP | 2019-08-06 | COMP | Rule 15/16 | 8 | 68 | 18 | 6 | 18 | 28 | 142
9496 | 2019-01-15 | 2019-02-06 | 2019-03-21 | 2019-03-26 | COMP | 2019-04-17 | COMP | 2019-04-17 | COMP | 2019-10-29 | COMP | 2019-11-26 | COMP | Rule 15/16 | 16 | 31 | 17 | 1 | 137 | 20 | 220
9503 | 2019-01-15 | 2019-02-06 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-22 | NOTN | 2019-05-07 | COMP | 2019-04-22 | COMP | 2019-07-30 | COMP | Other | 16 | 52 |  | 13 | 0 | 59 | 137
9509 | 2019-01-15 | 2019-02-06 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-31 | COMP | 2020-01-23 | COMP | 2019-12-27 | COMP | 2020-03-13 | COMP | Rule 15/16 | 16 | 113 | 11 | 120 | 0 | 36 | 292
9612 | 2019-01-15 | 2019-02-08 | 2019-03-16 | 2019-03-16 | COMP | 2019-04-16 | COMP | 2019-04-16 | COMP | 2019-07-03 | COMP | 2019-07-30 | COMP | Rule 16 | 18 | 25 | 22 | 1 | 56 | 19 | 137
9622 | 2019-01-15 | 2019-02-09 | 2019-04-10 | 2019-04-10 | COMP | 2019-08-14 | COMP | 2019-09-27 | COMP | 2019-09-26 | COMP | 2019-09-27 | COMP | Rule 16 | 18 | 42 | 89 | 32 | 0 | 1 | 179
9645 | 2019-01-15 | 2019-02-11 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-30 | COMP | 2019-05-03 | COMP | 2019-06-14 | COMP | 2019-07-02 | COMP | Rule 16 | 19 | 42 | 15 | 4 | 30 | 13 | 118
9667 | 2019-01-15 | 2019-02-11 | 2019-03-25 | 2019-03-25 | COMP | 2019-04-03 | COMP | 2019-04-03 | COMP | 2019-11-18 | COMP | 2019-12-23 | COMP | Rule 16 | 19 | 30 | 8 | 1 | 160 | 24 | 237
9972 | 2019-01-15 | 2019-02-27 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2020-01-03 | COMP | 2020-03-13 | COMP | Rule 16 | 30 | 70 | 27 | 1 | 120 | 49 | 292
10703 | 2019-01-15 | 2019-03-26 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-27 | COMP | 2019-08-30 | COMP | 2020-07-13 | COMP | 2020-09-14 | COMP | Rule 16 | 49 | 95 | 15 | 4 | 218 | 45 | 421
10755 | 2019-01-15 | 2019-03-28 | 2019-07-15 | 2019-12-17 | COMP | 2020-02-03 | COMP | 2020-03-12 | COMP | 2023-04-30 | INPR | 2020-08-26 | COMP | Rule 16 | 51 | 76 | 32 | 28 |  |  | 409
10842 | 2019-01-15 | 2019-04-02 | 2019-05-11 | 2019-05-11 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-03-13 | COMP | 2020-04-09 | COMP | Rule 16 | 54 | 29 | 134 | 1 | 77 | 20 | 311
10856 | 2019-01-15 | 2019-04-02 | 2019-08-06 | 2019-08-06 | COMP | 2019-12-13 | COMP | 2019-12-16 | COMP | 2019-12-18 | COMP | 2020-03-04 | COMP | Rule 15/16 | 54 | 89 | 90 | 2 | 3 | 52 | 285
11021 | 2019-01-15 | 2019-04-09 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-14 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2019-09-11 | COMP | Rule 16 | 59 | 38 | 11 | 45 | 1 | 18 | 167
11762 | 2019-01-15 | 2019-05-10 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-15 | COMP | 2019-11-19 | COMP | Rule 16 | 82 | 95 | 11 | 1 | 6 | 25 | 215
12308 | 2019-01-15 | 2019-05-30 | 2019-11-20 | 2019-11-20 | COMP | 2020-01-21 | COMP | 2020-01-27 | COMP | 2020-05-15 | COMP | 2020-06-19 | COMP | Rule 15/16 | 95 | 122 | 40 | 5 | 79 | 25 | 361
13388 | 2019-01-15 | 2019-07-24 | 2020-05-18 | 2020-05-21 | COMP | 2020-05-28 | COMP | 2020-05-28 | COMP | 2020-05-29 | COMP | 2020-08-19 | COMP | Rule 16 | 133 | 206 | 5 | 1 | 2 | 59 | 404
14211 | 2019-01-15 | 2019-08-29 | 2019-11-22 | 2019-11-22 | COMP | 2020-02-24 | COMP | 2020-10-09 | COMP | 2020-09-02 | COMP | 2020-11-13 | COMP | Rule 16 | 159 | 60 | 61 | 163 | 0 | 25 | 464
16361 | 2019-01-15 | 2019-12-24 | 2020-05-10 | 2020-05-10 | COMP | 2020-06-11 | COMP | 2020-10-20 | COMP | 2020-10-21 | COMP | 2020-12-01 | COMP | Rule 16 | 238 | 95 | 23 | 93 | 2 | 27 | 474
4089 | 2019-01-16 | 2019-01-23 | 2019-03-05 | 2019-03-05 | COMP | 2019-05-14 | NOTN | 2019-05-14 | COMP | 2019-06-11 | COMP | 2019-07-23 | COMP | Other | 5 | 29 |  | 51 | 20 | 30 | 131
9223 | 2019-01-16 | 2019-01-23 | 2019-03-06 | 2019-03-06 | COMP | 2019-05-09 | COMP | 2019-05-09 | INPR | 2022-01-30 | REQD | 2020-06-30 | COMP | Rule 16 | 5 | 30 | 47 |  |  |  | 367
9389 | 2019-01-16 | 2019-01-31 | 2019-11-18 | 2020-02-10 | COMP | 2020-03-05 | COMP | 2020-03-16 | COMP | 2020-07-07 | COMP | 2020-11-20 | COMP | Rule 16 | 11 | 203 | 18 | 8 | 81 | 97 | 468
9580 | 2019-01-16 | 2019-02-08 | 2019-04-24 | 2019-04-24 | COMP | 2019-05-21 | COMP | 2019-08-20 | COMP | 2019-08-09 | COMP | 2019-09-23 | COMP | Rule 16 | 17 | 53 | 20 | 64 | 0 | 24 | 174
9586 | 2019-01-16 | 2019-02-07 | 2019-04-26 | 2019-04-26 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-06-23 | COMP | 2020-07-01 | COMP | Rule 16 | 16 | 56 | 282 | 1 | 11 | 7 | 368
9717 | 2019-01-16 | 2019-02-12 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-03 | COMP | 2019-09-05 | COMP | 2019-07-13 | COMP | 2019-09-30 | COMP | Rule 15 | 19 | 97 | 4 | 45 | 0 | 18 | 179
9788 | 2019-01-16 | 2019-02-15 | 2019-04-12 | 2019-04-12 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-11-19 | COMP | 2019-12-11 | COMP | Rule 16 | 22 | 40 | 19 | 1 | 136 | 15 | 228
9810 | 2019-01-16 | 2019-02-19 | 2020-09-21 | 2020-09-21 | COMP | 2021-06-29 | COMP | 2021-07-13 | COMP | 2022-02-02 | COMP | 2022-03-31 | COMP | Rule 15/16 | 23 | 403 | 194 | 10 | 142 | 41 | 808
9841 | 2019-01-16 | 2019-02-20 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-30 | COMP | 2019-08-07 | COMP | 2020-02-14 | COMP | 2020-05-06 | COMP | Rule 15/16 | 24 | 43 | 28 | 49 | 131 | 58 | 329
9894 | 2019-01-16 | 2019-02-21 | 2019-06-17 | 2019-06-19 | COMP | 2019-06-20 | COMP | 2019-07-01 | COMP | 2019-07-29 | COMP | 2019-08-19 | COMP | Rule 16 | 25 | 82 | 2 | 8 | 20 | 16 | 150
10016 | 2019-01-16 | 2019-02-26 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-05-21 | COMP | 2019-08-28 | COMP | Rule 16 | 28 | 57 | 6 | 1 | 0 | 69 | 157
10068 | 2019-01-16 | 2019-02-28 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-24 | COMP | 2019-05-29 | COMP | 2019-11-24 | INPR | 2019-07-03 | COMP | Rule 16 | 30 | 39 | 24 | 3 |  |  | 118
10100 | 2019-01-16 | 2019-03-01 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-24 | COMP | 2019-05-29 | COMP | 2019-08-26 | COMP | 2019-08-27 | COMP | Rule 16 | 31 | 38 | 24 | 3 | 63 | 2 | 156
10131 | 2019-01-16 | 2019-03-04 | 2019-06-04 | 2019-06-04 | COMP | 2019-09-13 | COMP | 2019-09-16 | COMP | 2019-09-13 | COMP | 2019-10-15 | COMP | Rule 16 | 32 | 66 | 72 | 2 | 0 | 22 | 190
10340 | 2019-01-16 | 2019-03-12 | 2019-09-06 | 2020-06-22 | COMP | 2020-08-05 | COMP | 2020-07-09 | COMP | 2020-09-21 | COMP | 2020-11-15 | COMP | Rule 16 | 38 | 126 | 33 |  | 52 | 39 | 463
10479 | 2019-01-16 | 2019-03-18 | 2019-05-31 | 2019-08-07 | COMP | 2019-08-09 | NOTN | 2019-08-12 | COMP | 2020-03-21 | INPR | 2019-09-27 | COMP | Other | 42 | 54 |  | 4 |  |  | 178
10949 | 2019-01-16 | 2019-04-05 | 2019-05-21 | 2019-05-21 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-07-10 | COMP | 2019-08-05 | COMP | Rule 16 | 56 | 33 | 24 | 1 | 12 | 19 | 140
10969 | 2019-01-16 | 2019-04-06 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-12-09 | COMP | 2020-01-21 | COMP | Rule 16 | 56 | 59 | 41 | 1 | 72 | 29 | 254
11015 | 2019-01-16 | 2019-04-09 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2020-03-16 | COMP | 2020-04-07 | COMP | Rule 16 | 58 | 58 | 22 | 1 | 157 | 17 | 308
11247 | 2019-01-16 | 2019-04-18 | 2019-11-29 | 2019-11-29 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2022-01-30 | INPR | 2020-10-19 | COMP | Rule 16 | 65 | 156 | 33 | 1 |  |  | 445
11309 | 2019-01-16 | 2019-04-22 | 2019-07-27 | 2019-07-27 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-10-28 | COMP | 2019-11-04 | COMP | Rule 16 | 67 | 68 | 29 | 1 | 37 | 6 | 204
11596 | 2019-01-16 | 2019-05-03 | 2019-08-17 | 2019-08-17 | COMP | 2019-09-13 | COMP | 2019-09-24 | COMP | 2020-01-31 | COMP | 2020-03-10 | COMP | Rule 16 | 76 | 74 | 19 | 8 | 88 | 27 | 288
11687 | 2019-01-16 | 2019-05-07 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-07-18 | COMP | 2019-07-23 | COMP | Rule 16 | 78 | 21 | 6 | 1 | 26 | 4 | 131
12000 | 2019-01-16 | 2019-05-20 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-10-14 | COMP | Rule 16 | 87 | 75 | 13 | 1 | 1 | 17 | 189
12760 | 2019-01-16 | 2019-06-20 | 2019-07-16 | 2019-07-16 | COMP | 2019-12-31 | COMP | 2019-07-31 | COMP | 2019-12-30 | COMP | 2020-01-09 | COMP | Rule 16 | 109 | 18 | 116 |  | 104 | 8 | 247
13098 | 2019-01-16 | 2019-07-11 | 2019-09-07 | 2019-09-07 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-02-24 | COMP | 2020-03-25 | COMP | Rule 16 | 123 | 41 | 72 | 1 | 43 | 23 | 299
13565 | 2019-01-16 | 2019-07-31 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-21 | COMP | 2019-11-08 | COMP | 2019-12-19 | COMP | 2019-12-14 | COMP | Other | 137 | 35 | 24 | 15 | 27 |  | 230
13760 | 2019-01-16 | 2019-08-08 | 2020-04-10 | 2021-04-13 | COMP | 2021-05-07 | COMP | 2021-06-10 | COMP | 2021-06-08 | NOTN | 2021-07-26 | COMP | Rule 16 | 143 | 169 | 19 | 24 |  |  | 636
13855 | 2019-01-16 | 2019-08-14 | 2019-10-18 | 2020-06-17 | COMP | 2020-08-11 | COMP | 2021-01-14 | COMP | 2020-06-22 | COMP | 2021-02-23 | COMP | Rule 15/16 | 147 | 47 | 40 | 107 | 0 | 27 | 529
14934 | 2019-01-16 | 2019-10-04 | 2019-12-06 | 2020-01-29 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2021-05-24 | COMP | Rule 16 | 183 | 43 | 212 | 1 | 1 | 123 | 593
15993 | 2019-01-16 | 2019-12-04 | 2019-12-18 | 2019-12-18 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-02-11 | COMP | 2020-03-23 | COMP | Rule 15/16 | 223 | 11 | 28 | 1 | 10 | 29 | 297
16674 | 2019-01-16 | 2020-01-10 | 2020-04-10 | 2020-04-10 | COMP | 2020-10-20 | COMP | 2021-04-22 | COMP | 2021-04-22 | COMP | 2021-06-10 | COMP | Rule 16 | 248 | 64 | 136 | 126 | 1 | 35 | 605
4097 | 2019-01-17 | 2019-01-30 | 2019-03-21 | 2019-03-21 | COMP | 2019-05-13 | COMP | 2019-07-03 | COMP | 2019-11-23 | INPR | 2019-07-31 | COMP | Rule 15/16 | 9 | 36 | 38 | 37 |  |  | 136
9312 | 2019-01-17 | 2019-01-28 | 2019-02-06 | 2019-02-06 | COMP | 2019-02-20 | COMP | 2019-02-25 | COMP | 2019-03-05 | COMP | 2019-03-13 | COMP | Rule 15/16 | 7 | 8 | 10 | 4 | 7 | 7 | 38
9331 | 2019-01-17 | 2019-01-30 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-31 | COMP | 2021-02-23 | COMP | 2021-07-27 | COMP | 2021-11-17 | COMP | Rule 15/16 | 9 | 266 | 29 | 227 | 109 | 80 | 715
9730 | 2019-01-17 | 2019-02-12 | 2019-11-07 | 2019-11-07 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-04 | COMP | 2020-06-22 | COMP | Rule 15/16 | 18 | 189 | 68 | 1 | 11 | 78 | 360
9922 | 2019-01-17 | 2019-02-22 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-12-12 | COMP | 2020-01-07 | COMP | Rule 16 | 25 | 61 | 8 | 1 | 137 | 17 | 244
10119 | 2019-01-17 | 2019-03-04 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-02 | COMP | 2019-05-08 | COMP | 2019-05-06 | COMP | 2019-06-21 | COMP | Rule 16 | 31 | 35 | 9 | 5 | 0 | 32 | 109
10208 | 2019-01-17 | 2019-03-06 | 2019-07-15 | 2019-07-15 | COMP | 2019-07-22 | COMP | 2019-10-08 | COMP | 2019-08-28 | COMP | 2019-10-24 | COMP | Rule 15/16 | 33 | 92 | 6 | 56 | 0 | 13 | 196
10259 | 2019-01-17 | 2019-03-07 | 2019-05-02 | 2019-05-10 | COMP | 2019-05-15 | COMP | 2019-07-02 | COMP | 2019-10-21 | COMP | 2019-12-16 | COMP | Rule 16 | 34 | 41 | 4 | 34 | 78 | 38 | 230
10341 | 2019-01-17 | 2019-03-12 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-02 | COMP | 2019-08-06 | COMP | 2019-08-13 | COMP | 2019-09-03 | COMP | Rule 16 | 37 | 72 | 9 | 25 | 6 | 15 | 159
10394 | 2019-01-17 | 2019-03-14 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-31 | COMP | 2019-08-15 | COMP | 2019-08-07 | COMP | 2019-09-24 | COMP | Rule 16 | 39 | 59 | 40 | 12 | 0 | 28 | 174
10587 | 2019-01-17 | 2019-03-22 | 2019-05-30 | 2019-05-30 | COMP | 2019-07-10 | COMP | 2019-08-20 | COMP | 2020-06-13 | COMP | 2020-06-29 | COMP | Rule 16 | 45 | 49 | 29 | 30 | 205 | 11 | 365
10745 | 2019-01-17 | 2019-03-28 | 2019-06-28 | 2019-10-16 | COMP |  | INPR | 2019-08-20 | COMP | 2020-03-11 | COMP | 2020-05-07 | COMP | Rule 16 | 49 | 66 |  |  | 139 | 42 | 329
10806 | 2019-01-17 | 2019-03-30 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2020-03-31 | COMP | 2020-04-10 | COMP | Rule 15/16 | 50 | 71 | 10 | 1 | 173 | 9 | 310
10907 | 2019-01-17 | 2019-04-04 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2020-02-19 | COMP | 2020-04-02 | COMP | Rule 16 | 54 | 91 | 13 | 1 | 118 | 32 | 304
10975 | 2019-01-17 | 2019-04-06 | 2019-08-13 | 2019-11-27 | COMP | 2020-02-10 | COMP | 2020-02-12 | COMP | 2020-02-11 | COMP | 2020-03-05 | COMP | Rule 16 | 55 | 90 | 49 | 3 | 0 | 16 | 284
11806 | 2019-01-17 | 2019-05-13 | 2019-10-05 | 2019-10-05 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-03-06 | COMP | 2020-10-21 | COMP | Rule 15/16 | 81 | 102 | 45 | 1 | 59 | 162 | 446
11908 | 2019-01-17 | 2019-05-16 | 2019-08-02 | 2019-08-02 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2022-05-24 | COMP | 2022-06-22 | COMP | Rule 15/16 | 84 | 55 | 296 | 1 | 413 | 20 | 864
13403 | 2019-01-17 | 2019-07-24 | 2020-05-19 | 2020-08-02 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2021-07-15 | COMP | Rule 16 | 131 | 207 | 202 | 1 | 1 | 38 | 628
14359 | 2019-01-17 | 2019-09-05 | 2020-03-06 | 2020-03-06 | COMP | 2020-04-07 | COMP | 2020-04-20 | COMP | 2022-01-30 | INPR | 2020-05-22 | COMP | Rule 16 | 161 | 125 | 23 | 10 |  |  | 340
14599 | 2019-01-17 | 2019-09-17 | 2020-03-13 | 2020-03-13 | COMP | 2020-07-27 | NOTN | 2020-09-16 | COMP | 2021-02-10 | COMP | 2021-03-04 | COMP | Other | 169 | 122 |  | 132 | 100 | 16 | 535
14900 | 2019-01-17 | 2019-10-02 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-16 | COMP | 2020-01-29 | COMP | 2020-02-07 | COMP | 2020-01-31 | COMP | Rule 16 | 180 | 43 | 9 | 30 | 8 |  | 261
18076 | 2019-01-17 | 2020-03-10 | 2020-04-07 | 2020-04-07 | COMP | 2020-07-21 | COMP | 2020-10-06 | COMP | 2020-11-13 | COMP | 2020-12-04 | COMP | Rule 16 | 287 | 21 | 75 | 55 | 28 | 14 | 475
4114 | 2019-01-18 | 2019-02-23 | 2019-02-28 | 2019-02-28 | COMP | 2019-03-14 | COMP | 2019-03-11 | COMP | 2019-03-11 | COMP | 2019-04-10 | COMP | Rule 16 | 24 | 4 | 11 |  | 1 | 23 | 57
4134 | 2019-01-18 | 2019-03-21 | 2019-08-31 | 2019-08-31 | COMP | 2019-12-17 | COMP | 2020-08-04 | COMP | 2021-11-12 | COMP | 2022-01-19 | COMP | Other | 43 | 115 | 73 | 161 | 322 | 46 | 756
4144 | 2019-01-18 | 2019-04-03 | 2019-08-03 | 2019-08-03 | COMP | 2019-10-29 | COMP | 2023-06-30 | COMP | 2022-09-09 | COMP | 2023-08-23 | COMP | Other | 52 | 86 | 61 | 922 | 0 | 38 | 1156
4145 | 2019-01-18 | 2019-04-03 | 2019-08-30 | 2019-08-30 | COMP | 2019-11-27 | COMP | 2019-12-02 | COMP | 2023-09-06 | COMP | 2023-11-21 | COMP | Other | 52 | 106 | 62 | 2 | 947 | 54 | 1218
4161 | 2019-01-18 | 2019-04-25 | 2019-06-17 | 2019-06-17 | COMP |  |  |  |  | 2021-08-26 | COMP | 2021-12-03 | COMP | Other | 68 | 37 |  |  |  |  | 724
4256 | 2019-01-18 | 2019-11-23 | 2020-05-27 | 2020-05-27 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-08-04 | COMP | 2022-01-10 | COMP | Rule 16 | 215 | 126 | 49 | 1 | 2 | 361 | 750
9198 | 2019-01-18 | 2019-01-22 | 2019-03-07 | 2019-03-07 | COMP | 2019-04-03 | COMP | 2019-05-28 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | Rule 16 | 2 | 32 | 20 | 39 | 34 | 2 | 124
9416 | 2019-01-18 | 2019-02-02 | 2019-04-09 | 2019-04-09 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-10-08 | COMP | 2019-11-06 | COMP | Rule 16 | 10 | 46 | 116 | 1 | 13 | 22 | 204
9442 | 2019-01-18 | 2019-02-04 | 2019-03-07 | 2021-09-08 | COMP | 2021-10-01 | COMP | 2021-10-01 | COMP | 2022-03-09 | COMP | 2022-04-06 | COMP | Other | 11 | 23 | 18 | 1 | 109 | 21 | 810
9948 | 2019-01-18 | 2019-02-25 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-07-24 | COMP | 2019-08-08 | COMP | Rule 16 | 25 | 56 | 8 | 1 | 44 | 12 | 141
9952 | 2019-01-18 | 2019-02-25 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-23 | COMP | 2019-04-23 | COMP | 2019-04-18 | COMP | 2019-05-29 | COMP | Rule 16 | 25 | 22 | 21 | 1 | 0 | 26 | 91
10050 | 2019-01-18 | 2019-02-28 | 2019-06-05 | 2019-06-05 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-11-06 | COMP | 2019-11-15 | COMP | Rule 16 | 28 | 69 | 65 | 1 | 45 | 7 | 210
10118 | 2019-01-18 | 2019-03-04 | 2019-05-03 | 2019-07-31 | COMP | 2019-08-22 | COMP | 2019-09-17 | COMP | 2019-10-10 | COMP | 2019-10-18 | COMP | Rule 15/16 | 30 | 45 | 17 | 18 | 18 | 7 | 191
10625 | 2019-01-18 | 2019-03-22 | 2019-05-25 | 2019-05-25 | COMP | 2019-08-20 | COMP | 2019-09-04 | COMP | 2019-12-09 | COMP | 2019-12-16 | COMP | Rule 16 | 44 | 46 | 60 | 11 | 66 | 6 | 229
10720 | 2019-01-18 | 2019-03-27 | 2019-07-28 | 2019-07-28 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2020-02-18 | COMP | 2020-03-23 | COMP | Rule 16 | 47 | 86 | 17 | 1 | 123 | 25 | 295
11581 | 2019-01-18 | 2019-05-04 | 2019-09-18 | 2020-01-15 | COMP | 2020-02-14 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-02-08 | COMP | Rule 16 | 74 | 95 | 22 | 136 | 1 | 113 | 517
11820 | 2019-01-18 | 2019-05-14 | 2019-09-18 | 2019-10-02 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2023-04-04 | COMP | 2023-05-22 | COMP | Other | 81 | 89 | 30 | 1 | 851 | 35 | 1092
12011 | 2019-01-18 | 2019-05-21 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-12-29 | INPR | 2019-09-11 | COMP | Rule 16 | 86 | 66 | 9 | 1 |  |  | 164
12103 | 2019-01-18 | 2019-05-23 | 2019-06-28 | 2019-06-28 | COMP | 2019-09-04 | NOTN | 2019-09-04 | COMP | 2019-10-01 | COMP | 2019-11-15 | COMP | Other | 88 | 26 |  | 47 | 20 | 33 | 210
12322 | 2019-01-18 | 2019-05-31 | 2019-08-07 | 2019-08-07 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2019-09-27 | COMP | 2019-10-15 | COMP | Rule 15/16 | 93 | 48 | 24 | 1 | 14 | 13 | 188
12800 | 2019-01-18 | 2019-06-24 | 2019-09-11 | 2020-11-20 | COMP | 2021-01-08 | COMP | 2021-01-08 | COMP | 2021-06-15 | COMP | 2021-07-08 | COMP | Rule 16 | 109 | 56 | 32 | 1 | 110 | 17 | 622
12891 | 2019-01-18 | 2019-06-27 | 2019-09-25 | 2019-11-26 | COMP | 2019-11-26 | NOTN | 2019-12-05 | COMP | 2019-11-26 | COMP | 2020-01-11 | COMP | Other | 112 | 63 |  | 6 | 0 | 25 | 246
13515 | 2019-01-18 | 2019-07-29 | 2019-11-06 | 2019-11-06 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2021-08-27 | COMP | 2021-10-21 | COMP | Other | 133 | 72 | 27 | 1 | 429 | 39 | 696
13561 | 2019-01-18 | 2019-07-31 | 2019-12-08 | 2020-06-24 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2023-12-02 | COMP | 2023-12-21 | COMP | Other | 135 | 89 | 31 | 1 | 834 | 14 | 1238
14322 | 2019-01-18 | 2019-09-04 | 2020-02-24 | 2020-02-24 | COMP | 2020-08-19 | COMP | 2020-09-04 | COMP | 2020-08-19 | COMP | 2020-10-19 | COMP | Rule 16 | 159 | 117 | 127 | 13 | 0 | 31 | 443
14386 | 2019-01-18 | 2019-09-08 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-23 | COMP | 2020-07-14 | COMP | 2022-02-26 | INPR | 2020-08-25 | COMP | Rule 16 | 161 | 126 | 9 | 81 |  |  | 405
4147 | 2019-01-19 | 2019-04-08 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-26 | COMP | 2019-07-03 | COMP | 2019-08-20 | COMP | 2019-09-19 | COMP | Rule 16 | 54 | 52 | 6 | 6 | 34 | 22 | 169
9906 | 2019-01-19 | 2019-02-22 | 2019-05-13 | 2019-05-13 | COMP | 2019-02-22 | NOTN | 2019-06-19 | COMP | 2019-07-31 | NOTN | 2019-09-30 | COMP | Other | 23 | 57 |  | 27 |  |  | 176
13961 | 2019-01-19 | 2019-08-21 | 2020-01-27 | 2020-01-27 | COMP | 2020-02-21 | COMP | 2020-03-19 | COMP | 2020-03-23 | COMP | 2020-04-01 | COMP | Rule 15/16 | 149 | 107 | 19 | 20 | 3 | 8 | 301
9203 | 2019-01-20 | 2019-01-22 | 2019-03-08 | 2019-03-08 | COMP | 2019-03-11 | COMP | 2019-08-02 | COMP | 2019-08-07 | COMP | 2019-08-26 | COMP | Rule 16 | 1 | 33 | 2 | 103 | 4 | 14 | 152
11351 | 2019-01-20 | 2019-04-23 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-20 | COMP | 2019-08-30 | COMP | 2019-09-10 | COMP | 2019-10-17 | COMP | Rule 16 | 65 | 67 | 17 | 9 | 7 | 28 | 189
9353 | 2019-01-21 | 2019-01-31 | 2020-06-06 | 2023-06-20 | COMP | 2023-09-07 | COMP | 2023-09-08 | COMP | 2023-09-07 | COMP | 2023-12-07 | COMP | Rule 15/16 | 8 | 340 | 56 | 2 | 0 | 62 | 1227
9714 | 2019-01-21 | 2019-02-12 | 2019-03-30 | 2019-03-30 | COMP | 2019-06-19 | COMP | 2019-06-24 | COMP | 2019-09-05 | COMP | 2019-09-18 | COMP | Rule 16 | 16 | 33 | 57 | 4 | 52 | 10 | 168
10439 | 2019-01-21 | 2019-03-16 | 2019-06-05 | 2019-10-12 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2020-01-14 | COMP | 2020-02-17 | COMP | Other | 38 | 57 | 51 | 1 | 12 | 23 | 269
11502 | 2019-01-21 | 2019-04-30 | 2019-05-12 | 2019-05-12 | COMP | 2019-05-15 | COMP | 2019-07-23 | NOTN | 2019-08-01 | COMP | 2019-08-07 | COMP | Rule 16 | 70 | 9 | 3 |  |  |  | 139
11896 | 2019-01-21 | 2019-05-15 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2019-10-11 | COMP | 2019-11-04 | COMP | Rule 16 | 81 | 71 | 23 | 1 | 12 | 17 | 201
14630 | 2019-01-21 | 2019-09-20 | 2020-01-14 | 2020-01-14 | COMP | 2022-06-29 | COMP | 2022-08-03 | COMP | 2023-02-10 | COMP | 2023-04-16 | COMP | Rule 16 | 170 | 78 | 621 | 25 | 131 | 45 | 1065
14860 | 2019-01-21 | 2019-10-01 | 2020-02-10 | 2020-04-09 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-11-03 | COMP | 2020-12-09 | COMP | Rule 16 | 177 | 89 | 63 | 1 | 85 | 24 | 476
16002 | 2019-01-21 | 2019-12-06 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-05-20 | COMP | 2020-05-26 | COMP | Rule 16 | 222 | 59 | 5 | 1 | 53 | 4 | 339
16303 | 2019-01-21 | 2019-12-19 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-26 | COMP | 2020-07-06 | COMP | 2020-09-01 | COMP | 2020-09-10 | COMP | Rule 16 | 231 | 112 | 21 | 7 | 42 | 7 | 415
19555 | 2019-01-21 | 2020-05-12 | 2020-08-13 | 2021-01-08 | COMP | 2021-06-25 | COMP | 2021-11-03 | COMP | 2021-12-13 | COMP | 2022-01-28 | COMP | Rule 15/16 | 330 | 67 | 118 | 92 | 26 | 34 | 762
4091 | 2019-01-22 | 2019-01-22 | 2019-04-02 | 2019-04-02 | COMP | 2019-04-26 | COMP | 2019-04-26 | INPR | 2019-04-01 | COMP | 2019-04-03 | COMP | Rule 16 | 1 | 50 | 19 |  |  |  | 51
9756 | 2019-01-22 | 2019-02-13 | 2019-04-26 | 2019-04-26 | COMP | 2019-06-26 | COMP | 2019-06-26 | COMP | 2019-07-30 | COMP | 2019-08-22 | COMP | Rule 16 | 17 | 52 | 43 | 1 | 24 | 18 | 150
9870 | 2019-01-22 | 2019-02-21 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-15 | COMP | 2019-12-17 | COMP | 2020-01-07 | COMP | 2020-02-27 | COMP | Rule 15/16 | 22 | 142 | 25 | 43 | 14 | 36 | 277
9985 | 2019-01-22 | 2019-02-26 | 2019-05-12 | 2019-05-12 | COMP | 2019-05-20 | COMP | 2019-06-18 | COMP | 2019-05-23 | COMP | 2019-07-27 | COMP | Rule 16 | 25 | 54 | 6 | 21 | 0 | 28 | 131
9987 | 2019-01-22 | 2019-02-26 | 2019-05-01 | 2019-05-01 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2019-12-15 | COMP | 2020-02-07 | COMP | Rule 15/16 | 25 | 47 | 46 | 1 | 112 | 37 | 264
10165 | 2019-01-22 | 2019-03-05 | 2019-05-28 | 2019-05-28 | COMP | 2019-06-10 | COMP | 2019-07-10 | COMP | 2019-06-12 | COMP | 2019-08-17 | COMP | Rule 16 | 30 | 60 | 10 | 22 | 0 | 28 | 146
10508 | 2019-01-22 | 2019-03-19 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-10 | COMP | 2019-05-03 | COMP | 2019-05-04 | COMP | 2019-06-13 | COMP | Rule 16 | 40 | 9 | 31 |  | 1 | 28 | 101
10620 | 2019-01-22 | 2019-03-22 | 2019-04-03 | 2019-04-03 | COMP | 2019-06-25 | COMP | 2019-07-18 | COMP | 2019-07-22 | COMP | 2019-08-30 | COMP | Rule 16 | 43 | 9 | 59 | 17 | 3 | 30 | 156
10752 | 2019-01-22 | 2019-03-28 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2019-12-10 | COMP | 2020-02-12 | COMP | Rule 16 | 47 | 59 | 33 | 1 | 88 | 44 | 267
10968 | 2019-01-22 | 2019-04-06 | 2019-06-11 | 2019-06-11 | COMP | 2019-06-24 | COMP | 2019-06-25 | COMP | 2020-05-04 | COMP | 2020-06-23 | COMP | Rule 16 | 53 | 46 | 10 | 2 | 216 | 36 | 359
10971 | 2019-01-22 | 2019-04-06 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2020-01-14 | COMP | 2020-02-27 | COMP | Rule 16 | 53 | 71 | 14 | 1 | 111 | 31 | 277
11239 | 2019-01-22 | 2019-04-19 | 2019-06-20 | 2019-06-20 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-09-17 | COMP | 2019-12-16 | COMP | Rule 16 | 63 | 44 | 61 | 1 | 2 | 62 | 228
11787 | 2019-01-22 | 2019-05-11 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-22 | COMP | 2019-07-30 | NOTN | 2019-08-14 | COMP | 2019-08-22 | COMP | Rule 16 | 78 | 41 | 9 |  |  |  | 150
11834 | 2019-01-22 | 2019-05-14 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-04 | COMP | 2020-05-16 | COMP | 2020-05-05 | COMP | 2020-06-10 | COMP | Rule 15/16 | 80 | 109 | 33 | 114 | 0 | 17 | 350
11860 | 2019-01-22 | 2019-05-15 | 2019-08-20 | 2020-08-06 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2020-08-14 | COMP | 2020-10-16 | COMP | Rule 15/16 | 81 | 68 | 9 | 1 | 0 | 43 | 441
11861 | 2019-01-22 | 2019-05-15 | 2019-08-17 | 2019-08-17 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-02-11 | COMP | 2020-03-05 | COMP | Rule 16 | 81 | 66 | 110 | 1 | 11 | 17 | 282
12003 | 2019-01-22 | 2019-05-20 | 2019-07-14 | 2019-07-14 | COMP | 2019-07-24 | COMP | 2019-09-10 | COMP | 2019-09-06 | COMP | 2019-09-20 | COMP | Rule 16 | 84 | 38 | 8 | 34 | 0 | 9 | 170
12012 | 2019-01-22 | 2019-05-21 | 2019-11-25 | 2020-02-12 | COMP | 2020-06-17 | COMP | 2021-02-25 | COMP | 2021-08-10 | COMP | 2021-04-25 | COMP | Rule 16 | 85 | 131 | 89 | 174 | 117 |  | 569
12123 | 2019-01-22 | 2019-05-23 | 2019-10-04 | 2020-07-13 | COMP | 2020-08-05 | COMP | 2019-11-27 | COMP | 2021-03-02 | COMP | 2021-04-20 | COMP | Rule 16 | 87 | 94 | 18 |  | 315 | 36 | 566
12330 | 2019-01-22 | 2019-05-31 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2020-01-24 | COMP | 2020-03-11 | COMP | Rule 16 | 92 | 38 | 23 | 1 | 104 | 33 | 286
12992 | 2019-01-22 | 2019-07-03 | 2019-10-02 | 2019-10-02 | COMP | 2019-12-03 | COMP | 2019-12-05 | COMP | 2020-03-18 | COMP | 2020-07-08 | COMP | Rule 15/16 | 115 | 64 | 42 | 3 | 71 | 80 | 370
13337 | 2019-01-22 | 2019-07-22 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-10-16 | COMP | 2019-12-11 | COMP | Rule 16 | 127 | 51 | 9 | 1 | 4 | 38 | 225
13420 | 2019-01-22 | 2019-07-24 | 2019-09-05 | 2019-09-05 | COMP | 2019-10-23 | COMP | 2019-10-29 | COMP | 2019-10-30 | COMP | 2019-11-15 | COMP | Rule 16 | 129 | 31 | 35 | 5 | 2 | 12 | 209
13685 | 2019-01-22 | 2019-08-05 | 2019-11-14 | 2019-11-14 | COMP | 2020-01-02 | COMP | 2020-01-03 | COMP | 2020-03-05 | COMP | 2020-06-04 | COMP | Rule 16 | 137 | 72 | 32 | 2 | 43 | 65 | 346
14170 | 2019-01-22 | 2019-08-27 | 2020-06-17 | 2020-11-10 | COMP | 2021-03-05 | COMP | 2021-11-18 | COMP | 2021-09-30 | COMP | 2022-02-25 | COMP | Rule 16 | 153 | 203 | 77 | 181 | 0 | 68 | 781
17640 | 2019-01-22 | 2020-02-24 | 2021-07-19 | 2022-09-14 | COMP | 2023-03-13 | COMP |  | REQD | 2022-08-30 | COMP | 2023-10-03 | COMP | Rule 16 | 274 | 355 | 122 |  |  |  | 1183
17729 | 2019-01-22 | 2020-02-25 | 2020-10-25 | 2022-06-08 | COMP | 2022-07-18 | COMP | 2022-12-20 | COMP | 2023-12-06 | COMP | 2023-02-01 | COMP | Rule 16 | 275 | 172 | 27 | 108 | 241 |  | 1014
18170 | 2019-01-22 | 2020-03-13 | 2020-07-08 | 2020-07-08 | COMP | 2020-10-13 | COMP | 2020-10-22 | COMP | 2022-05-26 | COMP | 2022-07-08 | COMP | Rule 15/16 | 288 | 83 | 69 | 8 | 401 | 29 | 873
20928 | 2019-01-22 | 2020-07-14 | 2020-08-11 | 2020-08-11 | COMP | 2020-11-09 | COMP | 2020-11-09 | COMP | 2021-01-25 | COMP | 2021-02-25 | COMP | Rule 15/16 | 374 | 21 | 64 | 1 | 50 | 23 | 528
9432 | 2019-01-23 | 2019-02-04 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-09-22 | INPR | 2019-05-23 | COMP | Rule 16 | 9 | 52 | 16 | 1 |  |  | 86
9433 | 2019-01-23 | 2019-02-04 | 2019-03-30 | 2019-03-30 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-04-24 | COMP | 2019-05-22 | COMP | Rule 16 | 9 | 39 | 28 | 1 | 0 | 11 | 85
9474 | 2019-01-23 | 2019-02-05 | 2020-04-06 | 2020-04-06 | COMP | 2020-05-06 | COMP | 2020-07-07 | COMP | 2020-07-06 | COMP | 2020-07-27 | COMP | Rule 15/16 | 10 | 294 | 23 | 44 | 0 | 15 | 382
9936 | 2019-01-23 | 2019-02-23 | 2019-05-24 | 2019-10-22 | COMP | 2019-11-25 | COMP | 2020-07-18 | COMP | 2020-10-06 | COMP | 2020-11-18 | COMP | Rule 16 | 22 | 65 | 24 | 163 | 56 | 31 | 462
10122 | 2019-01-23 | 2019-03-04 | 2019-04-04 | 2019-04-22 | COMP | 2019-04-24 | COMP | 2019-05-01 | COMP | 2019-04-30 | COMP | 2019-06-03 | COMP | Rule 16 | 28 | 24 | 3 | 6 | 0 | 23 | 92
10502 | 2019-01-23 | 2019-03-18 | 2019-10-06 | 2020-04-21 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2020-10-30 | COMP | 2021-01-23 | COMP | Rule 15/16 | 38 | 142 | 67 | 1 | 71 | 55 | 504
10569 | 2019-01-23 | 2019-03-20 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | 2019-08-15 | COMP | 2019-10-07 | COMP | Rule 15/16 | 40 | 62 | 29 | 2 | 15 | 37 | 180
10599 | 2019-01-23 | 2019-03-21 | 2019-06-28 | 2019-07-01 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-10-21 | COMP | Rule 16 | 41 | 71 | 77 | 1 | 1 | 3 | 190
10715 | 2019-01-23 | 2019-03-28 | 2019-04-02 | 2019-05-24 | COMP | 2021-05-30 | REQD | 2021-05-30 | REQD | 2019-04-07 | COMP | 2019-04-23 | COMP | Rule 16 | 46 | 4 |  |  |  |  | 64
10776 | 2019-01-23 | 2019-03-29 | 2019-07-18 | 2019-07-18 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-16 | COMP | 2019-10-30 | COMP | Rule 16 | 47 | 78 | 15 | 1 | 28 | 33 | 197
10782 | 2019-01-23 | 2019-03-29 | 2019-06-05 | 2019-06-05 | COMP | 2019-09-12 | COMP | 2019-09-24 | COMP | 2019-09-16 | COMP | 2019-11-24 | COMP | Rule 16 | 47 | 48 | 70 | 9 | 0 | 43 | 213
10849 | 2019-01-23 | 2019-04-02 | 2019-06-17 | 2019-06-17 | COMP | 2019-08-29 | COMP | 2020-08-11 | COMP | 2021-01-28 | COMP | 2021-03-15 | COMP | Rule 16 | 49 | 54 | 53 | 240 | 116 | 32 | 539
10986 | 2019-01-23 | 2019-04-08 | 2019-06-22 | 2019-06-22 | COMP | 2019-10-04 | COMP | 2019-10-07 | COMP | 2020-01-07 | COMP | 2019-11-15 | COMP | Rule 16 | 53 | 54 | 73 | 2 | 62 |  | 208
11002 | 2019-01-23 | 2019-04-09 | 2019-05-20 | 2019-05-20 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-29 | COMP | 2019-09-09 | COMP | Rule 16 | 54 | 30 | 40 | 1 | 10 | 30 | 160
11047 | 2019-01-23 | 2019-04-10 | 2019-06-13 | 2019-06-13 | COMP | 2019-06-13 | NOTN | 2019-06-13 | COMP | 2019-09-12 | COMP | 2019-11-06 | COMP | Other | 55 | 46 |  | 1 | 64 | 40 | 202
11054 | 2019-01-23 | 2019-04-10 | 2019-08-29 | 2019-10-03 | COMP | 2019-10-22 | COMP | 2019-10-28 | COMP | 2019-10-16 | COMP | 2020-02-15 | COMP | Rule 16 | 55 | 100 | 14 | 5 | 0 | 74 | 268
11154 | 2019-01-23 | 2019-04-15 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-10-21 | INPR | 2019-07-11 | COMP | Rule 16 | 58 | 47 | 8 | 1 |  |  | 119
11579 | 2019-01-23 | 2019-05-04 | 2019-10-02 | 2019-10-02 | COMP | 2021-08-23 | COMP | 2021-09-13 | COMP | 2021-08-12 | COMP | 2021-12-06 | COMP | Rule 16 | 72 | 105 | 476 | 15 | 0 | 58 | 723
11666 | 2019-01-23 | 2019-05-07 | 2019-09-10 | 2019-09-10 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-10-28 | COMP | 2020-02-05 | COMP | Rule 16 | 74 | 88 | 31 | 1 | 5 | 67 | 261
11914 | 2019-01-23 | 2019-05-16 | 2019-09-16 | 2019-09-16 | COMP | 2019-10-02 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-02-04 | COMP | Rule 16 | 81 | 85 | 13 | 64 | 1 | 21 | 260
12185 | 2019-01-23 | 2019-05-28 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-29 | COMP | 2019-09-06 | COMP | 2019-09-12 | COMP | 2019-09-20 | COMP | Rule 16 | 88 | 36 | 9 | 29 | 5 | 7 | 169
12241 | 2019-01-23 | 2019-05-30 | 2019-09-01 | 2019-09-01 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2020-01-07 | COMP | 2020-01-31 | COMP | Rule 16 | 90 | 66 | 46 | 1 | 41 | 18 | 258
13643 | 2019-01-23 | 2019-08-05 | 2020-02-26 | 2020-02-26 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-03-10 | COMP | 2020-06-04 | COMP | Rule 15/16 | 136 | 140 | 3 | 1 | 8 | 62 | 345
14247 | 2019-01-23 | 2019-08-30 | 2019-12-20 | 2020-02-25 | COMP | 2020-03-05 | COMP | 2020-01-02 | COMP | 2020-03-09 | COMP | 2020-04-03 | COMP | Rule 15/16 | 155 | 77 | 8 |  | 46 | 20 | 302
14597 | 2019-01-23 | 2019-09-18 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-05 | NOTN | 2020-05-11 | COMP | 2019-12-24 | COMP | 2020-07-15 | COMP | Other | 167 | 95 |  | 68 | 0 | 47 | 374
14702 | 2019-01-23 | 2019-09-23 | 2019-11-10 | 2019-11-10 | COMP | 2019-11-25 | COMP | 2019-11-26 | COMP | 2020-01-06 | COMP | 2020-06-12 | COMP | Rule 16 | 170 | 35 | 10 | 2 | 26 | 112 | 351
15090 | 2019-01-23 | 2019-10-11 | 2019-11-21 | 2019-11-21 | COMP | 2019-11-21 | NOTN | 2020-02-26 | COMP | 2019-12-11 | COMP | 2020-05-27 | COMP | Other | 184 | 29 |  | 64 | 0 | 65 | 339
15402 | 2019-01-23 | 2019-10-31 | 2020-02-24 | 2020-02-24 | COMP | 2020-04-30 | COMP | 2020-05-05 | COMP | 2020-08-13 | COMP | 2020-09-03 | COMP | Rule 16 | 198 | 76 | 49 | 4 | 72 | 16 | 410
16135 | 2019-01-23 | 2019-12-11 | 2020-01-23 | 2020-01-23 | COMP | 2020-02-06 | COMP | 2020-03-26 | COMP | 2020-07-09 | COMP | 2020-07-30 | COMP | Rule 16 | 224 | 29 | 11 | 35 | 75 | 16 | 385
16992 | 2019-01-23 | 2020-01-27 | 2020-03-30 | 2020-03-30 | COMP | 2020-04-20 | COMP | 2020-07-10 | COMP | 2020-07-28 | COMP | 2020-10-06 | COMP | Rule 15/16 | 254 | 45 | 16 | 59 | 13 | 50 | 432
17239 | 2019-01-23 | 2020-02-05 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-04 | COMP | 2020-09-22 | COMP | 2020-09-28 | COMP | 2020-12-05 | COMP | Rule 15/16 | 261 | 67 | 62 | 35 | 5 | 47 | 472
17777 | 2019-01-23 | 2020-02-26 | 2020-06-04 | 2020-06-04 | COMP | 2021-03-24 | COMP | 2021-03-24 | COMP | 2022-03-04 | COMP | 2022-04-08 | COMP | Rule 16 | 275 | 71 | 202 | 1 | 240 | 26 | 810
4183 | 2019-01-24 | 2019-06-05 | 2019-07-08 | 2019-07-08 | COMP | 2019-08-23 | COMP | 2019-11-08 | COMP | 2019-12-10 | COMP | 2020-02-13 | COMP | Other | 93 | 23 | 35 | 55 | 20 | 45 | 266
4199 | 2019-01-24 | 2019-07-08 | 2019-08-15 | 2019-08-15 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-22 | COMP | 2020-02-13 | COMP | Other | 115 | 29 | 49 | 1 | 22 | 55 | 266
9343 | 2019-01-24 | 2019-01-30 | 2019-07-19 | 2019-07-19 | COMP | 2019-01-30 | NOTN | 2020-06-09 | COMP | 2021-05-11 | COMP | 2021-06-01 | COMP | Other | 5 | 120 |  | 224 | 233 | 15 | 593
9399 | 2019-01-24 | 2019-02-02 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-11 | COMP | 2019-05-06 | COMP | 2019-04-11 | COMP | 2019-05-20 | COMP | Rule 16 | 7 | 39 | 9 | 18 | 0 | 11 | 82
9492 | 2019-01-24 | 2019-02-06 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-07 | COMP | 2019-05-14 | COMP | 2019-05-08 | COMP | 2019-07-17 | COMP | Rule 16 | 10 | 50 | 15 | 6 | 0 | 45 | 122
9500 | 2019-01-24 | 2019-02-06 | 2019-04-09 | 2019-04-09 | COMP | 2019-04-10 | NOTN | 2019-06-26 | COMP | 2019-04-10 | NOTN | 2019-12-09 | COMP | Other | 10 | 44 |  | 56 |  |  | 221
9786 | 2019-01-24 | 2019-02-14 | 2019-03-29 | 2019-03-29 | COMP | 2019-07-18 | COMP | 2019-07-18 | INPR | 2019-12-29 | REQD | 2019-08-05 | COMP | Rule 16 | 16 | 31 | 78 |  |  |  | 135
10004 | 2019-01-24 | 2019-02-26 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-30 | COMP | 2019-09-11 | COMP | 2020-05-13 | COMP | 2020-06-26 | COMP | Rule 16 | 23 | 95 | 15 | 31 | 169 | 32 | 360
10037 | 2019-01-24 | 2019-02-27 | 2019-04-16 | 2019-04-16 | COMP | 2019-05-01 | COMP | 2019-05-24 | COMP | 2019-05-28 | COMP | 2019-06-19 | COMP | Rule 16 | 24 | 35 | 12 | 18 | 2 | 17 | 103
10097 | 2019-01-24 | 2019-03-01 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-19 | COMP | 2019-12-29 | REQD | 2019-07-10 | COMP | 2019-07-15 | COMP | Rule 16 | 26 | 5 | 9 |  |  |  | 120
10167 | 2019-01-24 | 2019-03-05 | 2019-04-26 | 2019-05-09 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-06-17 | COMP | 2019-07-12 | COMP | Rule 16 | 28 | 39 | 24 | 1 | 4 | 19 | 119
10180 | 2019-01-24 | 2019-03-05 | 2019-05-29 | 2019-05-29 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-03-29 | INPR | 2019-12-09 | COMP | Rule 16 | 28 | 61 | 130 | 1 |  |  | 221
10196 | 2019-01-24 | 2019-03-06 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-28 | COMP | 2019-07-17 | COMP | 2019-07-18 | COMP | 2019-08-06 | COMP | Rule 16 | 29 | 60 | 23 | 13 | 2 | 14 | 136
10220 | 2019-01-24 | 2019-03-06 | 2019-05-23 | 2019-05-23 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2023-02-15 | COMP | 2023-04-07 | COMP | Rule 16 | 29 | 57 | 27 | 1 | 912 | 37 | 1058
10276 | 2019-01-24 | 2019-03-08 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-06-13 | COMP | 2019-06-20 | COMP | Rule 16 | 31 | 31 | 22 | 1 | 18 | 6 | 104
10343 | 2019-01-24 | 2019-03-12 | 2019-04-19 | 2019-05-15 | COMP | 2019-08-27 | NOTN | 2019-08-27 | COMP | 2019-09-18 | COMP | 2019-10-02 | COMP | Other | 33 | 29 |  | 73 | 16 | 11 | 176
10373 | 2019-01-24 | 2019-03-13 | 2019-05-10 | 2019-05-10 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-12-29 | INPR | 2019-08-07 | COMP | Rule 16 | 34 | 43 | 19 | 1 |  |  | 137
10399 | 2019-01-24 | 2019-03-14 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-29 | COMP | 2019-05-29 | COMP | 2019-12-29 | INPR | 2019-08-19 | COMP | Rule 16 | 35 | 47 | 8 | 1 |  |  | 145
10605 | 2019-01-24 | 2019-03-21 | 2019-05-01 | 2019-05-01 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-04-17 | COMP | Rule 16 | 40 | 30 | 218 | 1 | 1 | 26 | 311
10770 | 2019-01-24 | 2019-03-29 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2021-05-03 | COMP | Rule 16 | 46 | 55 | 16 | 1 | 1 | 459 | 573
10918 | 2019-01-24 | 2019-04-04 | 2019-06-14 | 2019-06-14 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-12-03 | COMP | 2020-01-22 | COMP | Rule 16 | 50 | 51 | 111 | 1 | 8 | 34 | 250
10924 | 2019-01-24 | 2019-04-04 | 2019-06-28 | 2019-06-28 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-11-21 | COMP | 2020-02-07 | COMP | Rule 16 | 50 | 61 | 101 | 1 | 2 | 52 | 262
10927 | 2019-01-24 | 2019-04-04 | 2019-04-10 | 2019-04-10 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-06-18 | COMP | 2020-01-13 | COMP | Rule 16 | 50 | 5 | 14 | 1 | 36 | 143 | 244
10957 | 2019-01-24 | 2019-04-05 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2020-03-06 | COMP | 2020-05-12 | COMP | Rule 16 | 51 | 54 | 15 | 1 | 164 | 48 | 328
10958 | 2019-01-24 | 2019-04-05 | 2019-08-17 | 2019-09-16 | COMP | 2019-09-24 | COMP | 2020-06-04 | COMP | 2020-05-26 | COMP | 2020-07-31 | COMP | Rule 16 | 51 | 94 | 7 | 175 | 0 | 42 | 385
11225 | 2019-01-24 | 2019-04-17 | 2020-10-21 | 2020-10-21 | COMP | 2020-12-01 | COMP | 2021-05-04 | COMP | 2021-08-16 | COMP | 2021-10-30 | COMP | Rule 15/16 | 59 | 384 | 27 | 107 | 73 | 54 | 699
11313 | 2019-01-24 | 2019-04-23 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-09-12 | COMP | 2019-09-13 | COMP | Rule 16 | 63 | 28 | 7 | 1 | 67 | 2 | 163
11359 | 2019-01-24 | 2019-04-24 | 2019-08-10 | 2021-06-09 | COMP | 2021-08-16 | COMP | 2021-08-23 | COMP | 2021-10-26 | COMP | 2021-10-27 | COMP | Rule 16 | 64 | 76 | 48 | 6 | 46 | 2 | 697
11800 | 2019-01-24 | 2019-05-13 | 2019-11-04 | 2019-11-04 | COMP | 2020-04-17 | COMP | 2020-04-30 | COMP | 2023-04-30 | INPR | 2020-05-30 | COMP | Rule 16 | 77 | 123 | 113 | 10 |  |  | 340
11803 | 2019-01-24 | 2019-05-13 | 2019-10-07 | 2019-10-07 | COMP | 2019-12-31 | COMP | 2020-01-09 | COMP | 2020-01-02 | COMP | 2020-02-11 | COMP | Rule 16 | 77 | 103 | 58 | 7 | 0 | 23 | 264
11988 | 2019-01-24 | 2019-05-20 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-04 | NOTN | 2019-08-04 | COMP | 2019-08-04 | COMP | 2019-08-29 | COMP | Other | 82 | 47 |  | 7 | 0 | 19 | 153
12531 | 2019-01-24 | 2019-06-11 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-03 | COMP | 2020-02-28 | COMP | 2020-05-14 | COMP | 2020-06-19 | COMP | Rule 15/16 | 97 | 151 | 12 | 19 | 55 | 26 | 355
12556 | 2019-01-24 | 2019-06-12 | 2019-11-04 | 2019-11-04 | COMP | 2020-01-12 | NOTN | 2020-10-15 | COMP | 2021-04-12 | COMP | 2021-04-28 | COMP | Other | 98 | 102 |  | 240 | 121 | 13 | 570
14727 | 2019-01-24 | 2019-09-25 | 2019-12-07 | 2019-12-07 | COMP | 2019-12-24 | COMP | 2020-01-28 | COMP | 2020-03-17 | COMP | 2020-04-29 | COMP | Rule 16 | 171 | 50 | 12 | 23 | 35 | 32 | 319
16298 | 2019-01-24 | 2019-12-19 | 2020-04-16 | 2020-04-16 | COMP | 2022-01-30 | INPR | 2020-08-13 | COMP | 2020-11-04 | COMP | 2021-01-08 | COMP | Rule 16 | 229 | 82 |  | 85 | 59 | 43 | 494
16601 | 2019-01-24 | 2020-01-09 | 2020-06-15 | 2020-06-15 | COMP | 2020-06-17 | NOTN | 2020-09-09 | COMP | 2020-06-17 | COMP | 2020-10-30 | COMP | Other | 242 | 110 |  | 62 | 0 | 38 | 449
17504 | 2019-01-24 | 2020-02-19 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-11 | COMP | 2020-10-02 | COMP | 2021-01-13 | COMP | 2021-02-05 | COMP | Rule 16 | 269 | 42 | 18 | 103 | 69 | 17 | 513
4093 | 2019-01-25 | 2019-01-26 | 2019-06-08 | 2019-06-08 | COMP | 2019-08-13 | COMP | 2022-07-16 | COMP | 2022-07-29 | COMP | 2022-08-27 | COMP | Other | 1 | 93 | 46 | 736 | 10 | 21 | 905
4113 | 2019-01-25 | 2019-02-21 | 2019-05-13 | 2019-05-13 | COMP | 2019-08-13 | COMP | 2020-02-12 | COMP | 2020-01-23 | COMP | 2020-02-23 | COMP | Other | 19 | 58 | 65 | 125 | 0 | 7 | 270
9330 | 2019-01-25 | 2019-01-30 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2020-07-03 | COMP | 2020-08-11 | COMP | Rule 16 | 4 | 113 | 23 | 1 | 227 | 28 | 391
9643 | 2019-01-25 | 2019-02-09 | 2019-04-10 | 2019-04-10 | COMP | 2019-05-01 | COMP | 2019-05-29 | COMP | 2023-04-30 | INPR | 2019-08-06 | COMP | Rule 16 | 11 | 42 | 16 | 20 |  |  | 135
9675 | 2019-01-25 | 2019-02-11 | 2020-10-05 | 2020-10-08 | COMP | 2021-02-18 | COMP | 2021-03-18 | COMP | 2021-03-19 | COMP | 2021-05-05 | COMP | Rule 15/16 | 12 | 418 | 89 | 21 | 2 | 34 | 574
10456 | 2019-01-25 | 2019-03-18 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-08 | COMP | 2019-05-09 | COMP | 2020-02-29 | INPR | 2019-09-18 | COMP | Rule 16 | 36 | 30 | 9 | 2 |  |  | 165
10504 | 2019-01-25 | 2019-03-19 | 2019-04-22 | 2019-04-22 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-08-17 | COMP | 2019-08-24 | COMP | Rule 16 | 37 | 25 | 21 | 1 | 63 | 5 | 148
11078 | 2019-01-25 | 2019-04-11 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-16 | COMP | 2019-09-06 | COMP | 2019-09-13 | COMP | 2019-10-07 | COMP | Rule 16 | 54 | 86 | 5 | 15 | 6 | 17 | 178
11589 | 2019-01-25 | 2019-05-03 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-24 | COMP | 2019-07-23 | COMP | 2019-03-14 | COMP | 2019-08-26 | COMP | Rule 16 | 70 | 18 | 19 | 21 | 0 | 25 | 149
11899 | 2019-01-25 | 2019-05-15 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2020-05-14 | COMP | 2020-06-16 | COMP | Rule 15/16 | 78 | 105 | 4 | 1 | 145 | 23 | 351
11958 | 2019-01-25 | 2019-05-19 | 2019-08-08 | 2019-08-27 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-12-10 | COMP | 2020-02-03 | COMP | Rule 16 | 80 | 57 | 14 | 1 | 59 | 37 | 257
12019 | 2019-01-25 | 2019-05-21 | 2019-06-20 | 2019-06-20 | COMP | 2019-06-20 | NOTN | 2019-08-27 | COMP | 2019-06-20 | COMP | 2020-05-16 | COMP | Other | 82 | 22 |  | 48 | 0 | 181 | 330
12067 | 2019-01-25 | 2019-05-22 | 2019-08-09 | 2019-08-09 | COMP | 2019-10-28 | COMP | 2019-10-31 | COMP | 2020-04-29 | COMP | 2020-06-04 | COMP | Rule 16 | 83 | 56 | 56 | 4 | 123 | 26 | 343
12114 | 2019-01-25 | 2019-05-23 | 2019-07-17 | 2019-07-17 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-05-01 | COMP | 2020-05-05 | COMP | Rule 16 | 84 | 38 | 98 | 1 | 103 | 3 | 322
13510 | 2019-01-25 | 2019-07-29 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-16 | COMP | 2019-09-24 | COMP | 2019-10-07 | COMP | 2019-11-06 | COMP | Rule 16 | 129 | 26 | 10 | 7 | 10 | 23 | 200
14150 | 2019-01-25 | 2019-08-27 | 2020-01-10 | 2020-01-10 | COMP | 2020-02-13 | COMP | 2020-03-16 | COMP | 2020-03-21 | COMP | 2020-05-20 | COMP | Rule 16 | 150 | 93 | 24 | 22 | 5 | 43 | 333
15044 | 2019-01-25 | 2019-10-10 | 2020-01-25 | 2020-01-25 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-11-12 | COMP | 2020-11-25 | COMP | Rule 16 | 181 | 71 | 34 | 1 | 172 | 10 | 465
9388 | 2019-01-26 | 2019-01-31 | 2019-07-23 | 2020-09-10 | COMP | 2020-09-17 | COMP | 2020-09-18 | COMP | 2020-10-20 | COMP | 2020-10-23 | COMP | Rule 16 | 4 | 121 | 6 | 2 | 23 | 4 | 442
9993 | 2019-01-26 | 2019-02-26 | 2019-04-06 | 2019-04-11 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-10-21 | INPR | 2019-06-10 | COMP | Rule 15/16 | 21 | 29 | 8 | 1 |  |  | 94
10767 | 2019-01-26 | 2019-03-28 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-11-13 | COMP | 2019-12-18 | COMP | Rule 16 | 43 | 56 | 26 | 1 | 81 | 24 | 226
10784 | 2019-01-26 | 2019-03-29 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-11-13 | COMP | 2019-12-16 | COMP | Rule 16 | 44 | 23 | 8 | 1 | 131 | 22 | 224
12922 | 2019-01-26 | 2019-06-29 | 2019-11-07 | 2020-02-07 | COMP | 2020-03-04 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-06-04 | COMP | Rule 16 | 108 | 92 | 18 |  | 1 | 134 | 342
10178 | 2019-01-27 | 2019-03-05 | 2019-03-21 | 2019-03-21 | COMP | 2019-03-27 | COMP | 2019-03-27 | COMP | 2019-10-21 | INPR | 2019-05-04 | COMP | Rule 16 | 26 | 13 | 5 | 1 |  |  | 69
10225 | 2019-01-27 | 2019-03-06 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-16 | COMP | 2019-05-16 | COMP | 2020-06-30 | COMP | 2020-07-03 | COMP | Rule 16 | 27 | 31 | 22 | 1 | 283 | 4 | 363
10546 | 2019-01-27 | 2019-03-20 | 2019-07-23 | 2019-07-23 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2023-07-01 | INPR | 2020-06-17 | COMP | Rule 16 | 37 | 88 | 10 | 1 |  |  | 351
4235 | 2019-01-28 | 2019-09-26 | 2019-11-01 | 2019-11-01 | COMP | 2020-10-13 | COMP | 2021-05-17 | COMP |  | INPR | 2022-04-21 | COMP | Rule 15/16 | 170 | 27 | 239 | 148 |  |  | 816
9401 | 2019-01-28 | 2019-02-02 | 2019-04-06 | 2019-04-06 | COMP | 2019-04-25 | COMP | 2019-04-29 | COMP | 2019-05-01 | COMP | 2019-09-18 | COMP | Rule 16 | 5 | 44 | 14 | 3 | 3 | 98 | 164
9541 | 2019-01-28 | 2019-02-06 | 2019-03-27 | 2019-03-27 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-07-30 | COMP | 2019-09-04 | COMP | Rule 16 | 8 | 35 | 63 | 1 | 26 | 26 | 154
9670 | 2019-01-28 | 2019-02-11 | 2019-03-01 | 2019-03-01 | COMP | 2019-03-01 | NOTN | 2019-03-01 | COMP | 2019-03-01 | COMP | 2019-04-17 | COMP | Rule 16 | 11 | 14 |  | 1 | 1 | 34 | 57
9789 | 2019-01-28 | 2019-02-15 | 2019-03-06 | 2019-03-06 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-03-19 | COMP | 2019-04-08 | COMP | Rule 16 | 15 | 13 | 10 | 1 | 1 | 15 | 50
9843 | 2019-01-28 | 2019-02-20 | 2019-03-11 | 2019-03-11 | COMP | 2019-04-08 | COMP | 2019-04-09 | COMP | 2019-05-31 | COMP | 2019-05-31 | COMP | Rule 16 | 17 | 14 | 21 | 2 | 38 | 1 | 88
9850 | 2019-01-28 | 2019-02-20 | 2019-05-11 | 2019-05-11 | COMP | 2019-05-21 | COMP | 2019-05-28 | COMP | 2019-05-21 | COMP | 2019-07-05 | COMP | Rule 16 | 17 | 58 | 7 | 5 | 0 | 28 | 112
9901 | 2019-01-28 | 2019-02-22 | 2019-03-13 | 2019-03-13 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-09-22 | INPR | 2019-05-30 | COMP | Rule 16 | 19 | 14 | 37 | 1 |  |  | 87
10000 | 2019-01-28 | 2019-02-26 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-17 | NOTN | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-06-28 | COMP | Other | 21 | 58 |  | 2 | 1 | 30 | 108
10173 | 2019-01-28 | 2019-03-05 | 2019-04-04 | 2019-04-22 | COMP | 2019-04-24 | COMP | 2019-05-01 | COMP | 2019-04-30 | COMP | 2019-06-04 | COMP | Rule 16 | 26 | 23 | 3 | 6 | 0 | 24 | 90
10175 | 2019-01-28 | 2019-03-05 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-27 | COMP | 2019-07-10 | COMP | 2019-06-25 | COMP | 2019-09-06 | COMP | Rule 16 | 26 | 73 | 10 | 9 | 0 | 42 | 156
10273 | 2019-01-28 | 2019-03-08 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-22 | COMP | 2019-06-04 | COMP | 2019-07-09 | COMP | 2019-07-24 | COMP | Rule 16 | 29 | 49 | 6 | 9 | 25 | 12 | 125
10289 | 2019-01-28 | 2019-03-09 | 2019-06-20 | 2019-06-20 | COMP | 2019-08-21 | COMP | 2019-09-04 | COMP | 2019-09-10 | COMP | 2019-09-20 | COMP | Rule 16 | 29 | 73 | 44 | 10 | 5 | 9 | 166
10301 | 2019-01-28 | 2019-03-11 | 2019-06-10 | 2019-06-10 | COMP | 2019-07-02 | COMP | 2019-07-03 | COMP | 2022-04-16 | INPR | 2019-11-19 | COMP | Rule 16 | 30 | 65 | 17 | 2 |  |  | 207
10440 | 2019-01-28 | 2019-03-16 | 2019-06-20 | 2019-06-20 | COMP | 2019-09-24 | COMP | 2019-10-11 | COMP | 2020-02-29 | INPR | 2019-10-31 | COMP | Rule 16 | 34 | 68 | 67 | 14 |  |  | 195
10539 | 2019-01-28 | 2019-03-20 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-17 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | 2020-01-22 | COMP | Rule 16 | 37 | 56 | 8 | 70 | 2 | 80 | 248
10601 | 2019-01-28 | 2019-03-21 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-30 | COMP | 2019-06-17 | COMP | Rule 16 | 38 | 22 | 10 | 1 | 20 | 13 | 99
10630 | 2019-01-28 | 2019-03-23 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-19 | COMP | 2019-07-10 | COMP | 2019-08-26 | COMP | 2019-09-09 | COMP | Rule 16 | 39 | 52 | 11 | 15 | 34 | 10 | 157
10963 | 2019-01-28 | 2019-04-05 | 2019-07-19 | 2019-12-19 | COMP | 2020-02-04 | COMP | 2019-08-21 | COMP | 2020-01-23 | COMP | 2020-03-09 | COMP | Rule 16 | 49 | 74 | 31 |  | 105 | 32 | 280
11007 | 2019-01-28 | 2019-04-09 | 2020-02-11 | 2021-03-31 | COMP | 2021-04-27 | COMP | 2021-03-19 | COMP | 2021-07-01 | COMP | 2022-06-03 | COMP | Rule 15/16 | 51 | 212 | 20 |  | 74 | 234 | 846
11037 | 2019-01-28 | 2019-04-09 | 2019-06-21 | 2019-06-21 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-09-10 | COMP | 2019-09-18 | COMP | Rule 16 | 51 | 53 | 36 | 1 | 21 | 7 | 164
11170 | 2019-01-28 | 2019-04-16 | 2019-06-17 | 2019-06-17 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2020-03-06 | COMP | 2020-06-04 | COMP | Rule 16 | 56 | 44 | 9 | 1 | 173 | 64 | 342
11310 | 2019-01-28 | 2019-04-22 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2020-03-26 | COMP | 2020-04-10 | COMP | Rule 15/16 | 60 | 80 | 10 | 1 | 146 | 12 | 304
11319 | 2019-01-28 | 2019-04-23 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-16 | COMP | 2019-06-13 | INPR | 2019-10-11 | COMP | 2019-10-25 | COMP | Rule 16 | 61 | 9 | 10 |  |  |  | 191
11495 | 2019-01-28 | 2019-04-30 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-07 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-30 | COMP | Rule 16 | 66 | 19 | 10 | 110 | 1 | 32 | 233
11573 | 2019-01-28 | 2019-05-02 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-23 | COMP | 2019-10-02 | COMP | 2019-12-26 | COMP | 2020-01-13 | COMP | Rule 16 | 68 | 87 | 14 | 8 | 58 | 12 | 242
11871 | 2019-01-28 | 2019-05-15 | 2019-06-17 | 2019-06-17 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-09-09 | COMP | 2023-06-11 | COMP | Rule 16 | 77 | 23 | 6 | 1 | 54 | 944 | 1100
12214 | 2019-01-28 | 2019-05-28 | 2019-08-08 | 2019-08-27 | COMP | 2019-09-10 | COMP | 2019-09-20 | COMP | 2019-09-18 | COMP | 2019-10-15 | COMP | Rule 15/16 | 85 | 52 | 10 | 9 | 0 | 18 | 183
12596 | 2019-01-28 | 2019-06-14 | 2019-07-30 | 2019-07-30 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2021-04-24 | INPR | 2020-03-26 | COMP | Rule 16 | 98 | 32 | 34 | 1 |  |  | 293
12942 | 2019-01-28 | 2019-07-01 | 2019-10-08 | 2019-10-08 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2019-12-30 | COMP | 2020-01-17 | COMP | Rule 16 | 109 | 70 | 51 | 1 | 6 | 14 | 246
12971 | 2019-01-28 | 2019-07-02 | 2019-07-16 | 2019-07-16 | COMP | 2019-11-07 | COMP | 2020-04-07 | INPR | 2020-04-26 | REQD | 2020-01-03 | COMP | Rule 16 | 110 | 10 | 82 |  |  |  | 236
13011 | 2019-01-28 | 2019-07-05 | 2019-10-19 | 2021-02-12 | COMP | 2021-03-10 | COMP | 2021-04-14 | COMP | 2021-04-18 | COMP | 2021-05-12 | COMP | Rule 16 | 112 | 75 | 18 | 26 | 3 | 18 | 578
13364 | 2019-01-28 | 2019-07-22 | 2019-10-25 | 2021-03-19 | COMP | 2021-04-21 | COMP | 2020-02-19 | COMP | 2021-06-18 | COMP | 2021-08-03 | COMP | Rule 15/16 | 123 | 69 | 24 |  | 338 | 32 | 635
13697 | 2019-01-28 | 2019-08-06 | 2019-10-27 | 2020-03-26 | COMP | 2020-07-09 | COMP | 2020-07-18 | COMP | 2020-06-30 | COMP | 2020-09-21 | COMP | Rule 16 | 134 | 58 | 75 | 7 | 0 | 45 | 418
15190 | 2019-01-28 | 2019-10-18 | 2020-02-08 | 2020-02-08 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2022-07-16 | INPR | 2020-12-01 | COMP | Rule 16 | 186 | 75 | 15 | 1 |  |  | 466
15933 | 2019-01-28 | 2019-12-02 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-11 | COMP | 2020-07-20 | COMP | 2020-09-28 | COMP | 2020-12-18 | COMP | Rule 16 | 214 | 109 | 26 | 28 | 50 | 57 | 479
18747 | 2019-01-28 | 2020-04-06 | 2020-07-29 | 2020-07-29 | COMP | 2021-01-20 | COMP | 2021-02-18 | COMP |  | INPR | 2021-04-24 | COMP | Rule 16 | 300 | 82 | 119 | 21 |  |  | 565
10063 | 2019-01-29 | 2019-02-28 | 2019-04-29 | 2019-04-29 | COMP | 2019-07-22 | COMP | 2019-08-01 | COMP | 2020-08-21 | COMP | 2020-11-18 | COMP | Rule 16 | 22 | 43 | 59 | 9 | 268 | 62 | 458
10858 | 2019-01-29 | 2019-04-02 | 2019-08-28 | 2019-09-06 | COMP | 2019-09-19 | NOTN | 2019-09-19 | COMP | 2019-09-18 | COMP | 2019-11-18 | COMP | Other | 45 | 105 |  | 10 | 0 | 42 | 205
11468 | 2019-01-29 | 2019-04-29 | 2019-07-24 | 2019-07-24 | COMP | 2019-07-24 | NOTN | 2019-07-26 | COMP | 2019-07-31 | NOTN | 2019-09-18 | COMP | Other | 64 | 61 |  | 3 |  |  | 163
12224 | 2019-01-29 | 2019-05-28 | 2019-11-03 | 2019-11-03 | COMP | 2019-11-04 | NOTN | 2020-01-10 | COMP | 2020-01-28 | COMP | 2020-03-03 | COMP | Other | 84 | 112 |  | 45 | 12 | 25 | 275
14416 | 2019-01-29 | 2019-09-09 | 2019-10-28 | 2020-01-28 | COMP | 2020-02-06 | COMP | 2020-02-10 | COMP | 2020-02-24 | COMP | 2020-03-03 | COMP | Rule 16 | 156 | 36 | 8 | 3 | 10 | 7 | 275
4140 | 2019-01-30 | 2019-04-01 | 2019-07-22 | 2019-07-22 | COMP | 2019-07-22 | NOTN | 2019-09-09 | COMP | 2019-07-23 | COMP | 2019-10-02 | COMP | Other | 43 | 79 |  | 35 | 0 | 18 | 172
9625 | 2019-01-30 | 2019-02-09 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-03 | COMP | 2019-06-17 | COMP | Rule 16 | 8 | 34 | 25 | 1 | 2 | 31 | 97
9657 | 2019-01-30 | 2019-02-11 | 2019-02-23 | 2019-02-23 | COMP | 2019-04-29 | COMP | 2019-04-30 | COMP | 2019-09-02 | INPR | 2019-05-15 | COMP | Rule 16 | 9 | 9 | 46 | 2 |  |  | 75
9677 | 2019-01-30 | 2019-02-11 | 2019-04-03 | 2019-04-03 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-05-03 | COMP | 2019-06-18 | COMP | Rule 16 | 9 | 37 | 22 | 1 | 2 | 32 | 98
9775 | 2019-01-30 | 2019-02-15 | 2019-04-23 | 2019-05-15 | COMP | 2019-06-03 | COMP | 2019-06-17 | COMP | 2019-06-14 | COMP | 2019-07-22 | COMP | Rule 15/16 | 13 | 47 | 13 | 11 | 0 | 25 | 121
10121 | 2019-01-30 | 2019-03-04 | 2019-06-07 | 2019-06-07 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-08-21 | COMP | 2019-09-29 | COMP | Rule 16 | 23 | 69 | 43 | 1 | 11 | 27 | 169
10159 | 2019-01-30 | 2019-03-05 | 2019-05-21 | 2019-05-21 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-04-07 | COMP | 2020-04-22 | COMP | Rule 16 | 24 | 56 | 206 | 1 | 16 | 12 | 310
10181 | 2019-01-30 | 2019-03-05 | 2019-04-02 | 2019-04-02 | COMP | 2019-04-02 | NOTN | 2019-04-02 | COMP | 2019-04-02 | COMP | 2019-05-16 | COMP | Rule 16 | 24 | 21 |  | 1 | 1 | 33 | 76
10204 | 2019-01-30 | 2019-03-06 | 2019-04-19 | 2019-04-19 | COMP | 2019-04-26 | COMP | 2019-08-08 | COMP | 2019-12-29 | INPR | 2019-08-30 | COMP | Rule 15/16 | 25 | 33 | 6 | 73 |  |  | 150
10306 | 2019-01-30 | 2019-03-11 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2019-08-15 | COMP | 2019-09-01 | COMP | Rule 16 | 28 | 100 | 4 | 1 | 10 | 12 | 150
10402 | 2019-01-30 | 2019-03-14 | 2019-08-20 | 2019-11-27 | COMP | 2020-03-03 | COMP | 2020-03-13 | COMP | 2020-03-11 | COMP | 2020-05-26 | COMP | Rule 15/16 | 31 | 112 | 64 | 9 | 0 | 52 | 333
10460 | 2019-01-30 | 2019-03-18 | 2019-06-26 | 2019-06-26 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2019-12-29 | INPR | 2019-09-03 | COMP | Rule 16 | 33 | 72 | 27 | 1 |  |  | 151
10490 | 2019-01-30 | 2019-03-18 | 2019-12-24 | 2019-12-24 | COMP | 2021-01-19 | COMP | 2021-11-15 | COMP | 2021-12-03 | COMP | 2021-12-28 | COMP | Rule 15/16 | 33 | 196 | 269 | 210 | 13 | 18 | 734
10537 | 2019-01-30 | 2019-03-20 | 2019-05-14 | 2019-05-14 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-06 | COMP | 2019-06-10 | COMP | Rule 16 | 35 | 40 | 6 | 1 | 12 | 3 | 92
10579 | 2019-01-30 | 2019-03-21 | 2019-07-09 | 2020-01-30 | COMP | 2020-02-05 | COMP | 2019-09-19 | COMP | 2020-03-31 | COMP | 2020-06-08 | COMP | Rule 16 | 36 | 77 | 5 |  | 132 | 49 | 342
10590 | 2019-01-30 | 2019-03-23 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-05 | COMP | 2019-09-18 | COMP | 2019-06-06 | COMP | 2019-11-12 | COMP | Rule 16 | 37 | 49 | 4 | 74 | 0 | 39 | 200
10713 | 2019-01-30 | 2019-03-28 | 2019-06-08 | 2019-06-08 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-04-23 | COMP | Rule 16 | 41 | 51 | 199 | 1 | 1 | 22 | 311
10797 | 2019-01-30 | 2019-03-29 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-11-26 | COMP | 2020-01-02 | COMP | Rule 16 | 42 | 65 | 9 | 1 | 97 | 24 | 233
10881 | 2019-01-30 | 2019-04-03 | 2019-06-25 | 2019-06-25 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-07-18 | COMP | 2019-08-03 | COMP | Rule 16 | 45 | 59 | 4 | 1 | 14 | 12 | 130
10973 | 2019-01-30 | 2019-04-06 | 2019-07-26 | 2020-07-22 | COMP | 2020-09-02 | COMP | 2019-10-10 | COMP | 2020-11-19 | COMP | 2021-02-11 | COMP | Rule 15/16 | 47 | 78 | 31 |  | 281 | 56 | 513
10978 | 2019-01-30 | 2019-04-07 | 2019-07-18 | 2019-07-18 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-04-05 | COMP | 2020-08-14 | COMP | Rule 16 | 47 | 72 | 177 | 1 | 3 | 94 | 391
11034 | 2019-01-30 | 2019-04-10 | 2019-08-02 | 2019-08-02 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-05-23 | COMP | 2020-07-22 | COMP | Rule 16 | 50 | 81 | 186 | 1 | 18 | 42 | 374
11063 | 2019-01-30 | 2019-04-10 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-22 | COMP | 2019-07-11 | COMP | 2019-09-17 | COMP | 2019-11-05 | COMP | Rule 16 | 50 | 26 | 6 | 35 | 48 | 36 | 196
11162 | 2019-01-30 | 2019-04-16 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-24 | COMP | 2019-06-03 | INPR | 2019-06-06 | COMP | 2019-06-11 | COMP | Rule 16 | 54 | 23 | 7 |  |  |  | 93
11242 | 2019-01-30 | 2019-04-19 | 2019-08-15 | 2019-08-15 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-05-23 | COMP | 2020-08-15 | COMP | Rule 16 | 57 | 83 | 177 | 1 | 18 | 59 | 391
11257 | 2019-01-30 | 2019-04-19 | 2019-07-09 | 2019-07-09 | COMP | 2019-09-13 | COMP | 2019-12-03 | COMP |  | INPR | 2020-01-13 | COMP | Rule 15/16 | 57 | 56 | 48 | 55 |  |  | 240
11270 | 2019-01-30 | 2019-04-20 | 2019-08-06 | 2019-08-06 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-11-25 | COMP | 2020-01-06 | COMP | Rule 16 | 57 | 75 | 48 | 1 | 31 | 27 | 235
11282 | 2019-01-30 | 2019-04-22 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-12-29 | INPR | 2019-08-28 | COMP | Rule 16 | 58 | 57 | 6 | 1 |  |  | 148
11285 | 2019-01-30 | 2019-04-23 | 2020-02-21 | 2020-02-21 | COMP | 2020-09-28 | COMP | 2021-11-01 | COMP | 2022-04-14 | COMP | 2022-05-18 | COMP | Rule 15/16 | 59 | 209 | 155 | 276 | 114 | 25 | 833
11318 | 2019-01-30 | 2019-04-23 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2020-06-15 | COMP | 2020-07-20 | COMP | Rule 16 | 59 | 60 | 11 | 1 | 220 | 26 | 372
11377 | 2019-01-30 | 2019-04-24 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-07-31 | COMP | 2019-08-13 | COMP | Rule 16 | 60 | 30 | 15 | 1 | 26 | 10 | 137
11413 | 2019-01-30 | 2019-04-25 | 2019-06-06 | 2019-08-27 | COMP | 2020-04-26 | INPR | 2019-10-30 | COMP | 2019-12-03 | COMP | 2019-12-30 | COMP | Rule 16 | 61 | 30 |  | 46 | 22 | 19 | 231
11415 | 2019-01-30 | 2019-04-25 | 2019-08-24 | 2019-08-24 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2022-04-19 | COMP | 2022-05-03 | COMP | Other | 61 | 85 | 61 | 1 | 607 | 11 | 822
11441 | 2019-01-30 | 2019-04-27 | 2019-06-25 | 2019-06-25 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-12-03 | COMP | 2020-01-28 | COMP | Rule 16 | 62 | 41 | 64 | 1 | 48 | 38 | 250
11449 | 2019-01-30 | 2019-04-29 | 2019-09-09 | 2019-09-09 | COMP | 2020-04-06 | COMP | 2020-06-24 | COMP | 2020-06-22 | COMP | 2020-07-22 | COMP | Rule 16 | 63 | 93 | 144 | 57 | 0 | 21 | 374
11452 | 2019-01-30 | 2019-04-29 | 2019-05-25 | 2019-05-25 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-07-19 | COMP | 2019-10-01 | COMP | Rule 16 | 63 | 20 | 32 | 1 | 7 | 52 | 171
11456 | 2019-01-30 | 2019-04-29 | 2019-08-31 | 2019-08-31 | COMP | 2019-12-12 | COMP | 2020-06-04 | COMP | 2020-06-16 | COMP | 2020-07-15 | COMP | Rule 15/16 | 63 | 88 | 70 | 121 | 9 | 22 | 369
11476 | 2019-01-30 | 2019-04-29 | 2019-09-27 | 2019-09-27 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-05-31 | INPR | 2020-01-28 | COMP | Rule 16 | 63 | 107 | 44 | 1 |  |  | 250
11558 | 2019-01-30 | 2019-05-03 | 2019-05-21 | 2019-05-21 | COMP | 2019-06-11 | COMP | 2019-06-18 | COMP | 2019-07-09 | COMP | 2019-07-29 | COMP | Rule 16 | 67 | 13 | 15 | 6 | 15 | 15 | 126
12032 | 2019-01-30 | 2019-05-21 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-20 | COMP | 2019-10-02 | COMP | 2019-12-16 | COMP | 2020-01-13 | COMP | Rule 15/16 | 79 | 54 | 11 | 31 | 51 | 19 | 240
12033 | 2019-01-30 | 2019-05-21 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-20 | COMP | 2019-08-29 | COMP | 2019-12-16 | COMP | 2020-01-13 | COMP | Rule 16 | 79 | 52 | 13 | 8 | 74 | 19 | 240
12190 | 2019-01-30 | 2019-05-28 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-12-11 | COMP | 2020-02-01 | COMP | Rule 16 | 83 | 77 | 24 | 1 | 37 | 35 | 253
12200 | 2019-01-30 | 2019-05-28 | 2019-10-04 | 2019-10-04 | COMP | 2019-11-12 | COMP | 2020-02-19 | COMP | 2020-02-25 | COMP | 2020-07-08 | COMP | Rule 16 | 83 | 92 | 27 | 66 | 5 | 96 | 364
12527 | 2019-01-30 | 2019-06-11 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2022-10-11 | COMP | 2022-11-30 | COMP | Rule 16 | 93 | 76 | 16 | 1 | 751 | 34 | 966
12843 | 2019-01-30 | 2019-06-24 | 2019-10-24 | 2020-02-12 | COMP | 2020-02-10 | NOTN | 2020-07-03 | COMP | 2020-02-12 | COMP | 2020-08-12 | COMP | Other | 102 | 87 |  | 101 | 0 | 29 | 389
12854 | 2019-01-30 | 2019-06-25 | 2019-09-20 | 2019-09-20 | COMP | 2019-09-26 | COMP | 2019-09-30 | COMP | 2019-10-05 | COMP | 2019-11-07 | COMP | Rule 16 | 103 | 62 | 5 | 3 | 5 | 24 | 198
12926 | 2019-01-30 | 2019-07-02 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2019-07-12 | COMP | 2019-10-03 | COMP | Rule 16 | 108 | 23 | 12 | 1 | 0 | 33 | 173
13558 | 2019-01-30 | 2019-07-30 | 2020-02-01 | 2020-02-01 | COMP | 2020-03-24 | COMP | 2020-07-10 | COMP | 2020-06-12 | COMP | 2020-08-07 | COMP | Rule 15/16 | 127 | 127 | 36 | 78 | 0 | 21 | 386
13683 | 2019-01-30 | 2019-08-05 | 2019-11-26 | 2019-11-26 | COMP | 2019-12-04 | COMP | 2020-02-07 | COMP | 2020-02-26 | COMP | 2020-03-12 | COMP | Rule 16 | 131 | 80 | 5 | 45 | 13 | 12 | 281
13759 | 2019-01-30 | 2019-08-08 | 2020-01-23 | 2020-01-23 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-07-30 | COMP | 2020-09-23 | COMP | Rule 16 | 134 | 114 | 27 | 1 | 108 | 39 | 418
13867 | 2019-01-30 | 2019-08-14 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-12-24 | COMP | Rule 16 | 138 | 38 | 15 | 1 | 1 | 40 | 228
13968 | 2019-01-30 | 2019-08-19 | 2020-04-07 | 2020-05-21 | COMP | 2020-08-18 | COMP | 2020-10-01 | COMP | 2020-10-20 | COMP | 2021-04-05 | COMP | Rule 15/16 | 141 | 159 | 63 | 32 | 14 | 113 | 549
14098 | 2019-01-30 | 2019-08-26 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-09 | NOTN | 2020-03-11 | COMP | 2020-03-12 | COMP | 2020-06-18 | COMP | Other | 146 | 135 |  | 1 | 2 | 70 | 350
14125 | 2019-01-30 | 2019-08-26 | 2020-12-16 | 2020-12-16 | COMP | 2020-12-16 | NOTN | 2020-12-16 | COMP | 2020-12-16 | COMP | 2021-03-01 | COMP | Other | 146 | 330 |  | 1 | 1 | 50 | 524
14436 | 2019-01-30 | 2019-09-09 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-05 | COMP | 2020-04-21 | COMP | 2022-01-30 | INPR | 2020-07-21 | COMP | Rule 16 | 155 | 118 | 5 | 34 |  |  | 373
14936 | 2019-01-30 | 2019-10-04 | 2019-11-15 | 2020-01-08 | COMP | 2020-01-31 | COMP | 2020-02-02 | COMP | 2020-04-29 | COMP | 2020-06-12 | COMP | Rule 16 | 174 | 30 | 17 | 1 | 62 | 32 | 346
15261 | 2019-01-30 | 2019-10-23 | 2020-01-31 | 2020-01-31 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-10-14 | COMP | 2020-11-12 | COMP | Rule 16 | 187 | 67 | 180 | 1 | 2 | 21 | 453
17253 | 2019-01-30 | 2020-02-06 | 2020-03-20 | 2020-03-20 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2020-11-30 | COMP | 2021-02-17 | COMP | Rule 16 | 257 | 31 | 176 | 1 | 2 | 54 | 516
4122 | 2019-01-31 | 2019-03-12 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-24 | NOTN | 2019-06-24 | COMP | 2019-07-03 | COMP | 2019-08-09 | COMP | Other | 28 | 68 |  | 7 | 8 | 27 | 134
4136 | 2019-01-31 | 2019-03-21 | 2019-06-19 | 2019-06-19 | COMP | 2020-01-23 | COMP |  | REQD | 2020-02-27 | COMP | 2020-05-28 | COMP | Other | 35 | 64 | 149 |  |  |  | 334
9591 | 2019-01-31 | 2019-02-08 | 2019-03-13 | 2019-03-13 | COMP | 2019-04-15 | COMP | 2019-05-03 | COMP | 2019-07-24 | COMP | 2019-09-20 | COMP | Rule 16 | 7 | 23 | 24 | 15 | 57 | 42 | 163
9689 | 2019-01-31 | 2019-02-11 | 2019-04-11 | 2019-04-11 | COMP | 2019-05-06 | COMP | 2019-07-26 | COMP | 2019-07-03 | COMP | 2019-09-11 | COMP | Rule 16 | 8 | 43 | 18 | 58 | 0 | 33 | 156
9694 | 2019-01-31 | 2019-02-11 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-07 | COMP | 2019-11-13 | COMP | 2019-11-20 | COMP | 2020-01-03 | COMP | Rule 15/16 | 8 | 186 | 5 | 4 | 6 | 29 | 233
9713 | 2019-01-31 | 2019-02-12 | 2019-03-20 | 2019-03-20 | COMP | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-05-29 | COMP | 2019-07-29 | COMP | Rule 16 | 9 | 26 | 24 | 1 | 27 | 43 | 125
9737 | 2019-01-31 | 2019-02-13 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-09-16 | COMP | 2019-10-03 | COMP | Rule 15/16 | 10 | 74 | 34 | 1 | 44 | 14 | 172
9954 | 2019-01-31 | 2019-02-25 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-06 | COMP | 2019-06-06 | COMP | 2019-09-05 | COMP | 2019-08-30 | COMP | Rule 16 | 17 | 65 | 9 | 1 | 64 |  | 149
10019 | 2019-01-31 | 2019-02-26 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-10 | NOTN | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-07-02 | COMP | Other | 18 | 49 |  | 6 | 1 | 37 | 107
10363 | 2019-01-31 | 2019-03-12 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-06-03 | COMP | 2019-07-29 | COMP | Rule 16 | 28 | 47 | 5 | 1 | 9 | 40 | 125
10538 | 2019-01-31 | 2019-03-20 | 2019-05-09 | 2019-05-09 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-06-02 | COMP | 2020-06-03 | COMP | Rule 16 | 34 | 37 | 214 | 1 | 55 | 2 | 338
10555 | 2019-01-31 | 2019-03-20 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-21 | NOTN | 2019-07-08 | INPR | 2019-06-21 | COMP | 2019-08-22 | COMP | Other | 34 | 56 |  |  |  |  | 143
10595 | 2019-01-31 | 2019-03-21 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-28 | COMP | 2019-07-10 | COMP | 2019-08-26 | COMP | 2019-09-16 | COMP | Rule 16 | 35 | 47 | 25 | 8 | 34 | 15 | 159
10606 | 2019-01-31 | 2019-03-21 | 2019-05-25 | 2019-05-25 | COMP | 2019-10-09 | COMP | 2019-12-02 | COMP | 2019-11-22 | COMP | 2019-12-15 | COMP | Rule 16 | 35 | 47 | 95 | 36 | 0 | 10 | 220
10628 | 2019-01-31 | 2019-03-23 | 2019-08-05 | 2019-08-05 | COMP | 2019-09-04 | COMP | 2020-03-10 | COMP | 2020-07-30 | COMP | 2020-09-12 | COMP | Rule 15/16 | 36 | 94 | 22 | 128 | 102 | 31 | 409
10632 | 2019-01-31 | 2019-03-23 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-30 | COMP | 2019-08-22 | COMP | 2020-09-26 | INPR | 2019-09-12 | COMP | Rule 16 | 36 | 59 | 32 | 18 |  |  | 157
10637 | 2019-01-31 | 2019-03-23 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-08-21 | COMP | 2019-09-10 | COMP | Rule 16 | 36 | 33 | 4 | 1 | 71 | 14 | 155
10650 | 2019-01-31 | 2019-03-25 | 2019-05-30 | 2019-05-30 | COMP | 2019-06-14 | COMP | 2019-07-31 | COMP | 2019-12-02 | COMP | 2020-01-03 | COMP | Rule 16 | 37 | 48 | 12 | 33 | 85 | 23 | 233
10674 | 2019-01-31 | 2019-03-25 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-10 | COMP | 2019-06-28 | COMP | 2019-08-08 | COMP | 2019-08-29 | COMP | Rule 16 | 37 | 45 | 11 | 15 | 29 | 16 | 148
10843 | 2019-01-31 | 2019-04-02 | 2019-06-11 | 2020-02-05 | COMP | 2020-04-15 | COMP | 2020-07-27 | COMP | 2020-06-29 | COMP | 2020-12-18 | COMP | Rule 15/16 | 43 | 50 | 50 | 73 | 0 | 101 | 476
10890 | 2019-01-31 | 2019-04-03 | 2019-07-22 | 2019-07-22 | COMP | 2019-10-17 | COMP | 2020-03-06 | COMP | 2020-04-23 | COMP | 2020-06-06 | COMP | Rule 15/16 | 44 | 77 | 63 | 95 | 35 | 31 | 340
10995 | 2019-01-31 | 2019-04-08 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-14 | COMP | 2019-07-10 | INPR | 2023-09-02 | CANC | 2019-07-23 | COMP | Rule 16 | 47 | 20 | 8 |  |  |  | 121
11001 | 2019-01-31 | 2019-04-08 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-01 | NOTN | 2019-09-17 | COMP | 2019-08-01 | COMP | 2019-10-08 | COMP | Other | 47 | 71 |  | 44 | 0 | 16 | 175
11276 | 2019-01-31 | 2019-04-22 | 2019-05-10 | 2019-05-10 | COMP | 2019-05-30 | COMP | 2019-05-31 | COMP | 2019-05-09 | COMP | 2019-06-12 | COMP | Rule 16 | 57 | 15 | 14 | 2 | 0 | 9 | 93
11831 | 2019-01-31 | 2019-05-14 | 2019-09-12 | 2021-08-03 | COMP | 2021-08-18 | COMP | 2021-11-15 | COMP | 2021-11-16 | COMP | 2021-12-02 | COMP | Rule 16 | 73 | 85 | 12 | 62 | 2 | 11 | 715
11939 | 2019-01-31 | 2019-05-17 | 2019-12-19 | 2019-12-19 | COMP | 2020-03-20 | COMP | 2020-04-07 | COMP | 2020-04-17 | COMP | 2020-05-29 | COMP | Rule 16 | 76 | 149 | 63 | 13 | 9 | 30 | 335
11940 | 2019-01-31 | 2019-05-17 | 2019-09-01 | 2019-09-01 | COMP | 2020-04-17 | COMP | 2020-07-01 | COMP | 2020-06-03 | COMP | 2020-07-10 | COMP | Rule 16 | 76 | 74 | 157 | 53 | 0 | 8 | 365
12037 | 2019-01-31 | 2019-05-21 | 2019-12-24 | 2019-12-24 | COMP | 2020-06-17 | COMP | 2020-06-26 | COMP | 2020-08-13 | COMP | 2020-09-09 | COMP | Rule 16 | 78 | 150 | 122 | 8 | 35 | 19 | 407
12137 | 2019-01-31 | 2019-05-24 | 2019-06-21 | 2019-06-21 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-08-14 | COMP | 2019-08-30 | COMP | Rule 16 | 81 | 20 | 16 | 1 | 23 | 13 | 149
12299 | 2019-01-31 | 2019-05-30 | 2019-06-22 | 2019-06-22 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-24 | COMP | 2019-07-27 | COMP | Rule 16 | 84 | 17 | 10 | 1 | 13 | 3 | 124
12650 | 2019-01-31 | 2019-06-17 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-03 | COMP | 2019-10-14 | INPR | 2019-10-17 | COMP | 2019-11-23 | COMP | Rule 16 | 96 | 38 | 18 |  |  |  | 207
12797 | 2019-01-31 | 2019-06-24 | 2019-07-20 | 2019-07-20 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2019-09-10 | COMP | 2019-10-17 | COMP | Rule 16 | 101 | 19 | 10 | 1 | 27 | 28 | 182
12918 | 2019-01-31 | 2019-06-29 | 2019-09-04 | 2019-09-04 | COMP | 2019-11-19 | COMP | 2019-12-31 | COMP | 2020-01-07 | COMP | 2020-02-14 | COMP | Rule 15/16 | 105 | 46 | 54 | 28 | 5 | 28 | 262
13493 | 2019-01-31 | 2019-07-28 | 2019-08-19 | 2020-01-17 | COMP | 2020-06-24 | COMP | 2019-09-18 | COMP | 2020-09-02 | COMP | 2020-11-02 | COMP | Rule 16 | 124 | 16 | 111 |  | 243 | 43 | 445
13551 | 2019-01-31 | 2019-07-31 | 2019-11-25 | 2020-02-10 | COMP | 2020-03-06 | COMP | 2020-08-05 | COMP | 2020-08-24 | COMP | 2020-11-20 | COMP | Rule 16 | 127 | 82 | 19 | 108 | 14 | 63 | 458
14094 | 2019-01-31 | 2019-08-26 | 2020-04-26 | 2020-04-26 | COMP | 2020-06-02 | COMP | 2021-04-08 | COMP | 2021-04-07 | COMP | 2021-07-14 | COMP | Rule 15/16 | 145 | 167 | 26 | 215 | 0 | 68 | 618
14357 | 2019-01-31 | 2019-09-05 | 2020-01-29 | 2020-01-29 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2021-06-02 | COMP | 2021-06-29 | COMP | Rule 16 | 152 | 99 | 69 | 1 | 272 | 20 | 608
14409 | 2019-01-31 | 2019-09-09 | 2020-01-29 | 2020-01-29 | COMP | 2020-05-05 | COMP | 2021-01-26 | COMP | 2021-04-07 | COMP | 2021-05-24 | COMP | Rule 16 | 154 | 97 | 69 | 183 | 51 | 34 | 583
15573 | 2019-01-31 | 2019-11-07 | 2019-11-08 | 2019-11-20 | COMP | 2020-01-28 | COMP | 2020-02-07 | COMP | 2020-02-18 | COMP | 2020-05-06 | COMP | Rule 15/16 | 197 | 2 | 45 | 9 | 7 | 57 | 319
15577 | 2019-01-31 | 2019-11-08 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-19 | COMP | 2020-11-09 | COMP | Rule 16 | 198 | 120 | 29 | 1 | 6 | 101 | 450
16070 | 2019-01-31 | 2019-12-08 | 2020-03-08 | 2020-04-21 | COMP | 2020-05-20 | COMP | 2020-09-04 | COMP | 2020-09-08 | COMP | 2020-09-25 | COMP | Rule 16 | 215 | 61 | 22 | 77 | 2 | 14 | 419
16444 | 2019-01-31 | 2019-12-31 | 2020-05-28 | 2020-05-28 | COMP | 2020-10-22 | COMP | 2021-04-19 | COMP | 2021-08-31 | COMP | 2021-09-14 | COMP | Rule 16 | 231 | 104 | 105 | 121 | 95 | 10 | 661
9616 | 2019-02-01 | 2019-02-08 | 2019-03-22 | 2019-03-22 | COMP | 2019-05-15 | COMP | 2019-05-15 | COMP | 2019-04-27 | COMP | 2019-06-03 | COMP | Rule 16 | 6 | 30 | 39 | 1 | 0 | 13 | 85
9703 | 2019-02-01 | 2019-02-12 | 2019-06-07 | 2020-06-23 | COMP | 2020-09-02 | COMP | 2020-10-02 | COMP | 2021-01-25 | COMP | 2021-02-21 | COMP | Rule 15/16 | 8 | 82 | 52 | 22 | 76 | 19 | 516
9727 | 2019-02-01 | 2019-02-12 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-15 | COMP | 2019-08-12 | COMP | 2019-07-23 | COMP | 2019-08-15 | COMP | Rule 16 | 8 | 38 | 7 | 84 | 0 | 4 | 137
9897 | 2019-02-01 | 2019-02-21 | 2019-04-30 | 2019-05-15 | COMP | 2019-08-16 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-11-18 | COMP | Rule 16 | 14 | 49 | 66 | 27 | 1 | 39 | 202
9964 | 2019-02-01 | 2019-02-25 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-24 | NOTN | 2019-05-24 | COMP | 2019-06-03 | COMP | 2019-06-28 | COMP | Other | 16 | 38 |  | 28 | 6 | 20 | 104
10036 | 2019-02-01 | 2019-02-27 | 2019-03-29 | 2019-03-29 | COMP | 2019-07-15 | COMP | 2019-08-02 | COMP | 2020-04-26 | INPR | 2019-12-31 | COMP | Rule 16 | 18 | 23 | 75 | 15 |  |  | 230
10054 | 2019-02-01 | 2019-02-28 | 2019-06-27 | 2019-06-27 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-03-27 | COMP | 2020-05-26 | COMP | Rule 16 | 19 | 85 | 79 | 1 | 110 | 42 | 331
10182 | 2019-02-01 | 2019-03-05 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-06 | NOTN | 2019-05-06 | COMP | 2019-08-14 | NOTN | 2019-09-04 | COMP | Other | 22 | 32 |  | 14 |  |  | 150
10228 | 2019-02-01 | 2019-03-06 | 2019-05-17 | 2019-05-17 | COMP | 2019-07-26 | COMP | 2019-09-17 | COMP | 2019-07-29 | COMP | 2019-10-03 | COMP | Rule 16 | 23 | 53 | 49 | 37 | 0 | 13 | 171
10344 | 2019-02-01 | 2019-03-12 | 2019-07-08 | 2019-07-08 | COMP | 2019-07-17 | COMP | 2019-07-30 | COMP |  | INPR | 2019-08-19 | COMP | Rule 16 | 27 | 83 | 8 | 10 |  |  | 139
10414 | 2019-02-01 | 2019-03-14 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-21 | COMP | 2019-05-21 | COMP | 2019-10-21 | INPR | 2019-06-10 | COMP | Rule 15/16 | 29 | 45 | 5 | 1 |  |  | 90
10530 | 2019-02-01 | 2019-03-19 | 2019-05-20 | 2019-05-20 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-12-29 | INPR | 2019-08-22 | COMP | Rule 16 | 32 | 45 | 26 | 1 |  |  | 142
10670 | 2019-02-01 | 2019-03-25 | 2019-10-22 | 2019-10-22 | COMP | 2020-01-09 | COMP | 2020-08-27 | COMP | 2020-11-16 | COMP | 2021-01-13 | COMP | Rule 16 | 36 | 149 | 53 | 163 | 56 | 39 | 491
10689 | 2019-02-01 | 2019-03-26 | 2019-06-14 | 2019-06-14 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-10-02 | COMP | 2020-02-26 | COMP | Rule 16 | 37 | 58 | 47 | 1 | 31 | 99 | 268
10746 | 2019-02-01 | 2019-03-28 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-27 | NOTN | 2019-09-20 | COMP | 2019-07-27 | COMP | 2019-10-18 | COMP | Other | 39 | 66 |  | 58 | 0 | 21 | 182
10759 | 2019-02-01 | 2019-03-28 | 2019-08-13 | 2019-08-13 | COMP | 2020-02-05 | COMP | 2020-02-14 | COMP | 2020-02-10 | COMP | 2020-03-10 | COMP | Rule 16 | 39 | 97 | 120 | 8 | 0 | 17 | 277
10819 | 2019-02-01 | 2019-04-01 | 2019-07-06 | 2019-07-06 | COMP | 2019-10-04 | COMP | 2020-08-20 | COMP | 2021-03-02 | COMP | 2021-11-19 | COMP | Rule 16 | 41 | 68 | 64 | 222 | 131 | 185 | 707
10944 | 2019-02-01 | 2019-04-05 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-02 | COMP | 2019-08-02 | COMP | 2019-08-03 | COMP | 2019-08-20 | COMP | Rule 16 | 45 | 81 | 4 | 1 | 1 | 12 | 140
11152 | 2019-02-01 | 2019-04-15 | 2019-06-11 | 2019-06-11 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-08-01 | COMP | 2019-08-10 | COMP | Rule 16 | 51 | 41 | 15 | 1 | 23 | 7 | 133
11155 | 2019-02-01 | 2019-04-15 | 2019-08-01 | 2019-08-01 | COMP | 2019-09-04 | COMP | 2019-09-05 | COMP | 2019-09-17 | COMP | 2019-10-08 | COMP | Rule 16 | 51 | 77 | 24 | 2 | 9 | 16 | 174
11380 | 2019-02-01 | 2019-04-24 | 2019-04-29 | 2019-04-29 | COMP | 2019-05-08 | COMP | 2019-05-20 | COMP | 2019-10-21 | INPR | 2019-06-28 | COMP | Rule 16 | 58 | 4 | 8 | 9 |  |  | 104
11453 | 2019-02-01 | 2019-04-29 | 2019-05-28 | 2019-06-08 | COMP | 2019-07-01 | COMP | 2019-08-07 | INPR | 2019-07-09 | COMP | 2020-08-22 | COMP | Rule 16 | 61 | 21 | 16 |  |  |  | 394
11607 | 2019-02-01 | 2019-05-04 | 2019-07-30 | 2019-07-30 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-07 | COMP | 2019-12-13 | COMP | Rule 15/16 | 65 | 60 | 70 | 1 | 3 | 24 | 219
11805 | 2019-02-01 | 2019-05-13 | 2019-07-09 | 2019-08-14 | COMP | 2019-08-14 | NOTN | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-09-12 | COMP | Other | 71 | 40 |  | 1 | 1 | 21 | 156
11887 | 2019-02-01 | 2019-05-15 | 2019-11-07 | 2020-04-06 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2021-04-05 | COMP | 2021-05-05 | COMP | Rule 15/16 | 73 | 124 | 165 | 1 | 88 | 23 | 569
12250 | 2019-02-01 | 2019-05-29 | 2019-07-30 | 2019-08-16 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-11-18 | COMP | 2019-12-12 | COMP | Rule 16 | 82 | 44 | 25 | 1 | 41 | 17 | 218
12320 | 2019-02-01 | 2019-05-31 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-22 | COMP | 2021-06-17 | COMP | 2022-02-17 | COMP | 2021-08-01 | COMP | Rule 15/16 | 84 | 211 | 15 | 292 | 170 |  | 629
12516 | 2019-02-01 | 2019-06-10 | 2019-09-16 | 2019-10-28 | COMP | 2019-12-10 | COMP | 2019-10-08 | COMP | 2020-08-17 | COMP | 2020-10-07 | COMP | Rule 16 | 90 | 69 | 29 |  | 217 | 37 | 426
13137 | 2019-02-01 | 2019-07-11 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-09 | COMP | 2020-01-02 | COMP | 2020-06-10 | COMP | 2020-07-07 | COMP | Rule 16 | 112 | 101 | 4 | 17 | 112 | 20 | 361
13625 | 2019-02-01 | 2019-08-02 | 2019-12-27 | 2019-12-27 | COMP | 2020-01-08 | COMP | 2020-02-06 | COMP | 2020-01-27 | COMP | 2020-06-24 | COMP | Rule 15/16 | 128 | 101 | 8 | 21 | 0 | 98 | 352
15260 | 2019-02-01 | 2019-10-23 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-02-28 | COMP | 2020-03-11 | COMP | Rule 15/16 | 185 | 52 | 7 | 1 | 29 | 9 | 278
15339 | 2019-02-01 | 2019-10-26 | 2020-03-11 | 2020-08-06 | COMP | 2020-08-06 | NOTN | 2020-09-14 | COMP | 2020-08-06 | COMP | 2020-12-10 | COMP | Other | 187 | 91 |  | 27 | 0 | 61 | 469
19265 | 2019-02-01 | 2020-04-28 | 2020-08-23 | 2020-08-23 | COMP | 2020-08-19 | NOTN | 2020-08-23 | COMP | 2020-08-19 | COMP | 2020-09-15 | COMP | Other | 312 | 83 |  | 0 | 0 | 16 | 410
10200 | 2019-02-02 | 2019-03-06 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-11 | COMP | 2019-10-02 | COMP | 2019-10-07 | COMP | 2019-11-07 | COMP | Rule 15/16 | 22 | 49 | 21 | 80 | 4 | 24 | 195
11458 | 2019-02-02 | 2019-04-29 | 2019-08-12 | 2019-08-12 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-11-24 | COMP | 2020-02-07 | COMP | Rule 16 | 60 | 74 | 57 | 1 | 17 | 50 | 255
12057 | 2019-02-02 | 2019-05-22 | 2019-09-25 | 2021-09-03 | COMP | 2021-09-13 | COMP | 2019-11-14 | COMP | 2021-09-13 | COMP | 2021-09-22 | COMP | Rule 15/16 | 77 | 88 | 6 |  | 460 | 8 | 665
12949 | 2019-02-02 | 2019-07-01 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-03-03 | COMP | 2020-06-02 | COMP | Rule 16 | 104 | 131 | 10 | 1 | 29 | 65 | 335
13042 | 2019-02-02 | 2019-07-08 | 2019-08-20 | 2019-08-20 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2020-06-03 | COMP | Rule 16 | 108 | 32 | 4 | 1 | 1 | 195 | 336
13313 | 2019-02-02 | 2019-07-20 | 2019-10-24 | 2019-10-24 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2022-02-14 | COMP | 2022-03-20 | COMP | Rule 16 | 117 | 68 | 88 | 1 | 493 | 24 | 787
14553 | 2019-02-02 | 2019-09-16 | 2019-12-04 | 2019-12-16 | COMP | 2020-03-03 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-09-03 | COMP | Rule 15/16 | 157 | 55 | 53 | 75 | 1 | 58 | 402
10377 | 2019-02-03 | 2019-03-13 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-08-29 | INPR | 2019-08-13 | COMP | Rule 16 | 27 | 60 | 23 | 1 |  |  | 134
10378 | 2019-02-03 | 2019-03-13 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-09-26 | INPR | 2019-08-30 | COMP | Rule 16 | 27 | 61 | 22 | 1 |  |  | 147
10379 | 2019-02-03 | 2019-03-13 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-08-29 | INPR | 2019-08-13 | COMP | Rule 16 | 27 | 61 | 22 | 1 |  |  | 134
10380 | 2019-02-03 | 2019-03-13 | 2019-06-06 | 2019-06-06 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2020-08-29 | INPR | 2019-08-14 | COMP | Rule 16 | 27 | 61 | 22 | 1 |  |  | 135
10381 | 2019-02-03 | 2019-03-13 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-12-29 | INPR | 2019-08-14 | COMP | Rule 16 | 27 | 60 | 23 | 1 |  |  | 135
9615 | 2019-02-04 | 2019-02-08 | 2019-05-09 | 2019-05-09 | COMP | 2019-05-16 | COMP | 2019-06-10 | NOTN | 2019-06-10 | COMP | 2019-06-21 | COMP | Rule 16 | 5 | 64 | 6 |  |  |  | 98
9692 | 2019-02-04 | 2019-02-11 | 2019-02-15 | 2019-02-15 | COMP | 2019-02-16 | NOTN | 2019-02-21 | COMP | 2019-02-16 | COMP | 2019-04-03 | COMP | Other | 6 | 5 |  | 4 | 0 | 30 | 42
9791 | 2019-02-04 | 2019-02-15 | 2019-02-27 | 2019-02-27 | COMP | 2019-04-24 | COMP | 2019-05-30 | COMP | 2019-05-25 | COMP | 2019-07-10 | COMP | Rule 15/16 | 10 | 8 | 41 | 26 | 0 | 29 | 110
9942 | 2019-02-04 | 2019-02-23 | 2019-05-25 | 2019-05-25 | COMP | 2019-06-25 | COMP | 2019-09-20 | COMP | 2021-02-27 | INPR | 2019-10-04 | COMP | Rule 16 | 14 | 65 | 21 | 62 |  |  | 171
9979 | 2019-02-04 | 2019-02-26 | 2019-03-14 | 2019-03-15 | COMP | 2019-03-20 | COMP | 2019-03-28 | COMP | 2019-03-22 | COMP | 2019-04-17 | COMP | Rule 16 | 16 | 13 | 4 | 7 | 0 | 15 | 52
10424 | 2019-02-04 | 2019-03-15 | 2019-06-14 | 2019-06-14 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-02-04 | COMP | 2020-02-08 | COMP | Rule 16 | 29 | 65 | 156 | 1 | 5 | 4 | 255
10597 | 2019-02-04 | 2019-03-21 | 2019-05-04 | 2019-05-04 | COMP | 2019-05-21 | COMP | 2019-06-28 | COMP | 2019-10-15 | COMP | 2019-11-20 | COMP | Rule 16 | 33 | 32 | 12 | 28 | 76 | 26 | 203
10694 | 2019-02-04 | 2019-03-26 | 2019-07-08 | 2020-01-15 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2021-10-23 | INPR | 2020-07-23 | COMP | Rule 15/16 | 36 | 73 | 45 | 1 |  |  | 372
10764 | 2019-02-04 | 2019-03-28 | 2019-11-02 | 2020-11-17 | COMP | 2021-01-13 | COMP | 2021-08-09 | COMP | 2021-08-18 | COMP | 2021-11-19 | COMP | Rule 15/16 | 38 | 154 | 38 | 145 | 8 | 66 | 706
10912 | 2019-02-04 | 2019-04-04 | 2019-05-01 | 2019-05-01 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-06-13 | COMP | Rule 16 | 43 | 20 | 10 | 1 | 1 | 22 | 92
10942 | 2019-02-04 | 2019-04-06 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-27 | COMP | 2020-03-10 | COMP | 2020-02-11 | COMP | 2020-03-20 | COMP | Rule 16 | 44 | 85 | 38 | 111 | 0 | 9 | 284
10970 | 2019-02-04 | 2019-04-06 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-15 | COMP | 2019-09-05 | COMP | 2020-02-11 | COMP | 2020-03-24 | COMP | Rule 16 | 44 | 53 | 17 | 38 | 108 | 30 | 286
11136 | 2019-02-04 | 2019-04-15 | 2019-05-08 | 2019-05-08 | COMP | 2019-06-10 | COMP | 2019-07-03 | COMP | 2019-09-23 | COMP | 2019-09-30 | COMP | Rule 16 | 50 | 18 | 23 | 18 | 57 | 6 | 167
11685 | 2019-02-04 | 2019-05-08 | 2019-09-09 | 2019-09-14 | COMP | 2019-09-20 | COMP | 2019-09-23 | COMP | 2019-10-02 | COMP | 2020-01-28 | COMP | Rule 16 | 67 | 86 | 5 | 2 | 8 | 79 | 247
11772 | 2019-02-04 | 2019-05-10 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2022-07-16 | INPR | 2020-08-07 | COMP | Rule 16 | 69 | 56 | 15 | 1 |  |  | 383
12474 | 2019-02-04 | 2019-06-10 | 2019-07-15 | 2019-07-15 | COMP | 2019-07-23 | COMP | 2019-07-25 | COMP | 2019-07-24 | COMP | 2019-08-03 | COMP | Rule 16 | 89 | 25 | 7 | 3 | 0 | 7 | 127
12787 | 2019-02-04 | 2019-06-21 | 2019-10-14 | 2019-11-06 | COMP | 2019-11-06 | NOTN | 2019-11-06 | COMP | 2019-11-06 | COMP | 2020-01-21 | COMP | Other | 98 | 80 |  | 1 | 1 | 49 | 242
13179 | 2019-02-04 | 2019-07-15 | 2020-01-28 | 2020-01-28 | COMP | 2021-03-11 | NOTN | 2021-03-25 | COMP | 2021-03-11 | COMP | 2021-04-21 | COMP | Other | 113 | 135 |  | 293 | 0 | 20 | 558
14535 | 2019-02-04 | 2019-09-16 | 2020-01-13 | 2020-01-13 | COMP | 2020-01-24 | NOTN | 2020-04-27 | COMP | 2020-01-28 | COMP | 2020-06-11 | COMP | Other | 157 | 81 |  | 74 | 0 | 33 | 342
14676 | 2019-02-04 | 2019-09-23 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-12 | COMP | 2020-08-12 | COMP | 2021-02-16 | COMP | 2021-04-04 | COMP | Rule 16 | 162 | 82 | 16 | 129 | 127 | 34 | 545
15063 | 2019-02-04 | 2019-10-10 | 2019-11-26 | 2019-11-26 | COMP | 2019-12-27 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-04-29 | COMP | Rule 16 | 175 | 33 | 21 | 53 | 1 | 34 | 312
15713 | 2019-02-04 | 2019-11-18 | 2020-04-27 | 2020-04-27 | COMP | 2021-06-23 | COMP | 2022-10-11 | COMP | 2022-09-16 | COMP | 2023-07-06 | COMP | Rule 15/16 | 201 | 110 | 293 | 329 | 0 | 183 | 1112
17621 | 2019-02-04 | 2020-02-21 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-07-07 | COMP | 2020-07-14 | COMP | Rule 16 | 264 | 54 | 8 | 1 | 37 | 6 | 365
17902 | 2019-02-04 | 2020-03-03 | 2020-06-12 | 2020-06-12 | COMP | 2020-08-24 | COMP | 2021-05-19 | COMP | 2021-06-04 | COMP | 2021-06-30 | COMP | Rule 16 | 271 | 73 | 52 | 185 | 12 | 19 | 607
4149 | 2019-02-05 | 2019-04-10 | 2019-05-27 | 2019-05-27 | COMP | 2019-07-31 | COMP | 2019-09-16 | COMP | 2020-06-09 | COMP | 2020-07-14 | COMP | Rule 16 | 46 | 33 | 46 | 33 | 184 | 26 | 364
9874 | 2019-02-05 | 2019-02-21 | 2019-05-31 | 2019-05-31 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-07-02 | COMP | 2019-07-19 | COMP | Rule 16 | 12 | 71 | 27 | 1 | 0 | 9 | 116
10148 | 2019-02-05 | 2019-03-05 | 2019-09-17 | 2019-09-17 | COMP | 2019-10-02 | COMP | 2020-04-07 | COMP | 2020-04-06 | COMP | 2020-05-20 | COMP | Rule 15/16 | 20 | 138 | 12 | 128 | 0 | 32 | 326
10172 | 2019-02-05 | 2019-03-05 | 2019-04-14 | 2019-04-14 | COMP | 2019-04-22 | COMP | 2019-04-29 | NOTN | 2019-05-07 | COMP | 2019-05-09 | COMP | Rule 16 | 20 | 29 | 6 |  |  |  | 67
10174 | 2019-02-05 | 2019-03-05 | 2019-08-30 | 2019-08-30 | COMP | 2019-10-01 | COMP | 2019-12-27 | COMP | 2020-05-27 | COMP | 2020-06-20 | COMP | Rule 15/16 | 20 | 127 | 22 | 60 | 105 | 18 | 347
10483 | 2019-02-05 | 2019-03-18 | 2019-10-10 | 2019-10-10 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-07-07 | COMP | 2020-08-27 | COMP | Rule 16 | 29 | 146 | 79 | 1 | 108 | 38 | 396
10866 | 2019-02-05 | 2019-04-02 | 2019-08-17 | 2019-08-17 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2020-03-18 | COMP | 2020-06-01 | COMP | Rule 16 | 40 | 97 | 36 | 1 | 110 | 53 | 333
10867 | 2019-02-05 | 2019-04-02 | 2019-08-12 | 2019-08-12 | COMP | 2019-09-30 | COMP | 2019-12-31 | COMP | 2020-03-18 | COMP | 2020-05-06 | COMP | Rule 16 | 40 | 93 | 35 | 63 | 54 | 36 | 316
11070 | 2019-02-05 | 2019-04-11 | 2019-06-29 | 2019-06-29 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | Rule 16 | 47 | 56 | 26 | 1 | 121 | 1 | 248
11089 | 2019-02-05 | 2019-04-12 | 2019-07-27 | 2019-07-27 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-10-02 | COMP | 2019-10-17 | COMP | Rule 16 | 48 | 74 | 29 | 1 | 19 | 12 | 179
11212 | 2019-02-05 | 2019-04-17 | 2019-06-25 | 2019-06-25 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2020-06-15 | COMP | 2020-07-17 | COMP | Rule 16 | 51 | 49 | 20 | 1 | 226 | 25 | 367
11562 | 2019-02-05 | 2019-05-03 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-06-21 | COMP | 2019-09-11 | COMP | Rule 16 | 63 | 24 | 10 | 1 | 3 | 57 | 153
11654 | 2019-02-05 | 2019-05-07 | 2019-09-10 | 2019-09-10 | COMP | 2020-01-27 | COMP | 2021-03-01 | COMP | 2021-01-12 | COMP | 2021-04-01 | COMP | Rule 16 | 65 | 88 | 94 | 276 | 0 | 24 | 543
11922 | 2019-02-05 | 2019-05-16 | 2019-08-31 | 2020-07-01 | COMP | 2020-07-22 | COMP | 2019-11-06 | COMP | 2020-09-22 | COMP | 2020-10-16 | COMP | Rule 16 | 72 | 75 | 16 |  | 221 | 19 | 431
12121 | 2019-02-05 | 2019-05-23 | 2019-07-30 | 2019-07-30 | COMP | 2019-05-23 | NOTN | 2019-07-30 | COMP | 2020-03-31 | COMP | 2020-04-30 | COMP | Other | 77 | 47 |  | 1 | 168 | 23 | 312
12435 | 2019-02-05 | 2019-06-05 | 2019-07-15 | 2019-07-15 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-12-10 | COMP | 2020-02-13 | COMP | Rule 16 | 85 | 28 | 69 | 1 | 35 | 45 | 258
12515 | 2019-02-05 | 2019-06-12 | 2019-08-16 | 2019-11-20 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP |  |  | 2020-02-26 | COMP | Rule 16 | 90 | 47 | 44 | 1 |  |  | 266
12959 | 2019-02-05 | 2019-07-01 | 2019-12-16 | 2019-12-16 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2022-05-17 | COMP | 2022-05-31 | COMP | Rule 15/16 | 103 | 116 | 62 | 1 | 550 | 10 | 837
13171 | 2019-02-05 | 2019-07-15 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2023-06-07 | COMP | 2023-08-03 | COMP | Rule 16 | 112 | 22 | 5 | 1 | 956 | 40 | 1131
13204 | 2019-02-05 | 2019-07-16 | 2019-07-18 | 2019-07-18 | COMP | 2021-10-27 | COMP | 2021-11-05 | COMP | 2021-09-27 | COMP | 2021-11-10 | COMP | Rule 16 | 113 | 3 | 575 | 8 | 0 | 4 | 699
13771 | 2019-02-05 | 2019-08-08 | 2019-12-16 | 2019-12-16 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2021-01-12 | COMP | 2021-02-04 | COMP | Rule 16 | 130 | 89 | 35 | 1 | 237 | 17 | 504
13973 | 2019-02-05 | 2019-08-20 | 2019-12-05 | 2019-12-05 | COMP | 2020-02-21 | COMP | 2020-05-29 | COMP | 2020-08-17 | COMP | 2020-10-29 | COMP | Rule 15/16 | 138 | 74 | 53 | 70 | 57 | 53 | 440
14566 | 2019-02-05 | 2019-09-17 | 2019-12-06 | 2019-12-06 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-07-07 | COMP | 2020-08-06 | COMP | Rule 16 | 157 | 56 | 85 | 1 | 64 | 23 | 381
14746 | 2019-02-05 | 2019-09-25 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-04-03 | COMP | 2020-05-21 | COMP | Rule 15/16 | 163 | 55 | 13 | 1 | 65 | 35 | 327
14826 | 2019-02-05 | 2019-09-30 | 2019-11-02 | 2019-11-02 | COMP | 2019-12-09 | COMP | 2020-01-14 | COMP | 2020-11-09 | COMP | 2021-01-08 | COMP | Rule 16 | 166 | 25 | 23 | 25 | 211 | 40 | 486
14942 | 2019-02-05 | 2019-10-05 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-24 | COMP | 2020-09-22 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | Rule 16 | 170 | 165 | 16 | 64 | 17 | 1 | 429
15579 | 2019-02-05 | 2019-11-09 | 2020-03-22 | 2021-09-17 | COMP | 2021-10-12 | COMP | 2021-10-12 | COMP | 2020-08-20 | COMP | 2021-12-28 | COMP | Rule 16 | 195 | 88 | 18 | 1 | 0 | 53 | 730
16175 | 2019-02-05 | 2019-12-13 | 2020-02-23 | 2020-02-23 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | 2020-05-14 | COMP | 2020-06-16 | COMP | Rule 16 | 217 | 47 | 27 | 2 | 32 | 23 | 344
16625 | 2019-02-05 | 2020-01-10 | 2020-09-04 | 2020-09-04 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2021-07-16 | COMP | 2021-08-05 | COMP | Rule 16 | 235 | 168 | 16 | 1 | 201 | 15 | 631
17152 | 2019-02-05 | 2020-02-03 | 2020-03-12 | 2020-03-12 | COMP | 2020-03-13 | NOTN | 2020-03-13 | COMP |  | INPR | 2020-03-17 | COMP | Other | 250 | 28 |  | 2 |  |  | 280
17407 | 2019-02-05 | 2020-02-12 | 2020-07-27 | 2020-10-09 | COMP | 2020-10-26 | COMP | 2020-12-10 | COMP | 2021-01-13 | COMP | 2021-03-12 | COMP | Rule 15/16 | 257 | 117 | 12 | 31 | 23 | 41 | 529
17954 | 2019-02-05 | 2020-03-05 | 2020-05-29 | 2020-05-29 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-08-17 | COMP | 2020-10-08 | COMP | Rule 16 | 272 | 61 | 26 | 1 | 32 | 38 | 425
9783 | 2019-02-06 | 2019-02-14 | 2019-04-08 | 2019-05-13 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | Rule 15/16 | 7 | 37 | 152 | 1 | 13 | 1 | 231
9916 | 2019-02-06 | 2019-02-23 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-23 | COMP | 2019-08-02 | COMP | 2019-09-25 | COMP | 2019-11-15 | COMP | Rule 16 | 12 | 96 | 10 | 9 | 38 | 37 | 198
9955 | 2019-02-06 | 2019-02-25 | 2019-03-28 | 2019-04-03 | COMP | 2019-04-09 | COMP | 2019-04-09 | COMP | 2019-04-10 | COMP | 2019-05-28 | COMP | Rule 16 | 13 | 24 | 5 | 1 | 2 | 34 | 78
9994 | 2019-02-06 | 2019-02-26 | 2019-03-23 | 2019-03-23 | COMP | 2019-04-17 | COMP | 2019-05-16 | COMP | 2019-10-21 | INPR | 2019-06-17 | COMP | Rule 16 | 14 | 19 | 18 | 22 |  |  | 92
10111 | 2019-02-06 | 2019-03-04 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-03 | COMP | 2019-06-10 | COMP | 2019-08-19 | COMP | 2019-09-25 | COMP | Rule 16 | 18 | 54 | 12 | 6 | 50 | 27 | 162
10135 | 2019-02-06 | 2019-03-04 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-14 | COMP | 2019-08-20 | COMP | 2019-08-21 | COMP | 2019-09-27 | COMP | Rule 16 | 18 | 62 | 13 | 47 | 2 | 27 | 164
10149 | 2019-02-06 | 2019-03-05 | 2019-04-22 | 2019-04-22 | COMP | 2019-07-11 | COMP | 2019-11-21 | COMP | 2020-01-28 | COMP | 2020-07-11 | COMP | Rule 15/16 | 19 | 35 | 57 | 94 | 44 | 117 | 361
10314 | 2019-02-06 | 2019-03-11 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-02 | COMP | 2019-07-01 | COMP | 2019-07-10 | NOTN | 2019-10-15 | COMP | Rule 16 | 23 | 32 | 8 | 42 |  |  | 176
10484 | 2019-02-06 | 2019-03-18 | 2019-05-18 | 2019-05-18 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-12-29 | INPR | 2019-08-02 | COMP | Rule 16 | 28 | 45 | 8 | 1 |  |  | 125
10506 | 2019-02-06 | 2019-03-19 | 2019-06-14 | 2019-06-20 | COMP | 2019-07-08 | NOTN | 2019-07-08 | COMP | 2019-06-14 | COMP | 2019-08-27 | COMP | Other | 29 | 63 |  | 12 | 0 | 37 | 142
10564 | 2019-02-06 | 2019-03-20 | 2019-08-20 | 2019-08-20 | COMP | 2020-03-16 | COMP | 2020-04-28 | COMP | 2020-06-08 | COMP | 2020-07-29 | COMP | Rule 16 | 30 | 108 | 142 | 32 | 29 | 38 | 374
10660 | 2019-02-06 | 2019-03-25 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-26 | COMP | 2019-06-27 | COMP | 2019-07-03 | COMP | 2019-07-29 | COMP | Rule 16 | 33 | 59 | 9 | 2 | 5 | 18 | 121
10823 | 2019-02-06 | 2019-04-01 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-08-06 | COMP | 2019-08-07 | COMP | Rule 16 | 38 | 42 | 20 | 1 | 30 | 2 | 128
10977 | 2019-02-06 | 2019-04-06 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-08 | COMP | 2019-10-07 | COMP | 2019-09-04 | COMP | 2019-12-06 | COMP | Rule 16 | 42 | 71 | 17 | 42 | 0 | 42 | 211
11135 | 2019-02-06 | 2019-04-15 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-06-27 | COMP | 2019-07-01 | COMP | Rule 16 | 48 | 15 | 6 | 1 | 34 | 3 | 102
11140 | 2019-02-06 | 2019-04-15 | 2019-06-21 | 2019-06-21 | COMP | 2019-10-08 | COMP | 2020-06-11 | COMP | 2020-06-12 | COMP | 2020-07-21 | COMP | Rule 16 | 48 | 49 | 76 | 170 | 2 | 28 | 368
11183 | 2019-02-06 | 2019-04-16 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-08-27 | COMP | 2019-10-14 | COMP | Rule 16 | 49 | 79 | 21 | 1 | 0 | 29 | 175
11203 | 2019-02-06 | 2019-04-17 | 2019-07-17 | 2019-12-05 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-01-13 | COMP | 2020-02-04 | COMP | Rule 16 | 50 | 64 | 17 | 1 | 10 | 16 | 250
11211 | 2019-02-06 | 2019-04-17 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-09-30 | COMP | 2019-10-01 | COMP | Rule 16 | 50 | 23 | 4 | 1 | 91 | 2 | 166
11215 | 2019-02-06 | 2019-04-17 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-08-27 | COMP | 2019-10-15 | COMP | Rule 16 | 50 | 78 | 23 | 1 | 0 | 28 | 176
11252 | 2019-02-06 | 2019-04-20 | 2019-07-22 | 2019-07-22 | COMP | 2019-07-29 | COMP | 2019-07-30 | COMP | 2020-01-08 | COMP | 2020-01-09 | COMP | Rule 16 | 52 | 64 | 6 | 2 | 111 | 2 | 233
11312 | 2019-02-06 | 2019-04-23 | 2019-05-29 | 2019-09-25 | COMP | 2019-10-31 | COMP | 2021-01-27 | COMP | 2021-02-12 | COMP | 2021-03-04 | COMP | Rule 15/16 | 54 | 26 | 27 | 310 | 13 | 14 | 522
11481 | 2019-02-06 | 2019-04-29 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-08-28 | COMP | 2019-08-29 | COMP | Rule 16 | 58 | 37 | 9 | 1 | 42 | 2 | 144
11513 | 2019-02-06 | 2019-04-30 | 2019-07-15 | 2019-07-15 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-10-28 | COMP | 2019-07-15 | COMP | Rule 16 | 59 | 53 | 10 | 1 | 66 |  | 111
11572 | 2019-02-06 | 2019-05-04 | 2019-06-01 | 2019-06-01 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-07-02 | COMP | 2019-08-23 | COMP | Rule 16 | 62 | 19 | 20 | 1 | 3 | 38 | 140
11587 | 2019-02-06 | 2019-05-03 | 2019-07-23 | 2019-07-23 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-10-18 | COMP | 2019-11-07 | COMP | Rule 16 | 62 | 56 | 42 | 1 | 22 | 15 | 193
11852 | 2019-02-06 | 2019-05-14 | 2019-09-23 | 2019-09-23 | COMP | 2019-09-25 | COMP | 2019-10-07 | COMP | 2019-11-08 | COMP | 2019-11-26 | COMP | Rule 16 | 69 | 92 | 3 | 9 | 25 | 12 | 205
11853 | 2019-02-06 | 2019-05-14 | 2019-08-08 | 2019-08-08 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-01-29 | COMP | 2020-03-08 | COMP | Rule 16 | 69 | 61 | 52 | 1 | 67 | 27 | 272
12044 | 2019-02-06 | 2019-05-21 | 2019-10-21 | 2019-10-21 | COMP | 2019-12-09 | COMP | 2019-12-17 | COMP | 2020-06-30 | COMP | 2020-10-14 | COMP | Rule 15/16 | 74 | 107 | 33 | 7 | 136 | 76 | 428
12794 | 2019-02-06 | 2019-06-24 | 2019-10-02 | 2020-02-15 | COMP | 2020-03-09 | COMP | 2019-10-17 | COMP | 2020-04-03 | COMP | 2020-05-29 | COMP | Rule 16 | 97 | 71 | 15 |  | 115 | 40 | 331
13122 | 2019-02-06 | 2019-07-11 | 2019-09-10 | 2019-09-10 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2020-03-01 | INPR | 2019-11-18 | COMP | Rule 15/16 | 109 | 43 | 25 | 1 |  |  | 199
13684 | 2019-02-06 | 2019-08-05 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2020-03-01 | INPR | 2019-11-14 | COMP | Rule 16 | 126 | 37 | 8 | 1 |  |  | 197
13966 | 2019-02-06 | 2019-08-19 | 2019-11-07 | 2019-11-07 | COMP | 2020-02-20 | COMP | 2020-02-28 | COMP | 2023-04-30 | INPR | 2020-08-29 | COMP | Rule 16 | 136 | 58 | 69 | 7 |  |  | 396
15183 | 2019-02-06 | 2019-10-17 | 2020-01-24 | 2020-01-24 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-07-07 | COMP | 2020-08-13 | COMP | Rule 15/16 | 178 | 66 | 55 | 1 | 62 | 28 | 385
16049 | 2019-02-06 | 2019-12-07 | 2020-02-26 | 2020-02-26 | COMP | 2020-02-26 | NOTN | 2020-02-26 | COMP | 2020-03-03 | COMP | 2020-05-02 | COMP | Other | 211 | 54 |  | 1 | 5 | 44 | 312
16882 | 2019-02-06 | 2020-01-22 | 2020-03-14 | 2020-03-14 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-09-21 | COMP | 2020-10-09 | COMP | Rule 16 | 241 | 37 | 61 | 1 | 74 | 15 | 425
26250 | 2019-02-06 | 2021-03-13 | 2021-05-06 | 2021-05-06 | COMP | 2021-06-09 | COMP | 2021-06-11 | COMP | 2021-05-28 | COMP | 2021-08-16 | COMP | Rule 15 | 528 | 39 | 24 | 3 | 0 | 46 | 637
9892 | 2019-02-07 | 2019-02-21 | 2019-03-12 | 2019-06-09 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-07-30 | COMP | 2019-08-16 | COMP | Rule 16 | 10 | 14 | 12 | 1 | 25 | 14 | 134
9988 | 2019-02-07 | 2019-02-26 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-14 | NOTN | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-06-28 | COMP | Other | 13 | 55 |  | 2 | 1 | 33 | 100
9989 | 2019-02-07 | 2019-02-26 | 2019-04-20 | 2019-04-20 | COMP | 2019-04-22 | NOTN | 2019-04-22 | COMP | 2019-04-22 | COMP | 2019-06-06 | COMP | Other | 13 | 39 |  | 1 | 1 | 33 | 84
10316 | 2019-02-07 | 2019-03-11 | 2019-05-23 | 2019-05-23 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-11-15 | COMP | Other | 22 | 54 | 87 | 1 | 1 | 37 | 197
10361 | 2019-02-07 | 2019-03-12 | 2020-03-07 | 2020-05-07 | COMP | 2020-08-12 | COMP | 2021-02-10 | COMP |  | INPR | 2021-04-09 | COMP | Rule 15/16 | 23 | 249 | 69 | 124 |  |  | 547
10415 | 2019-02-07 | 2019-03-14 | 2019-03-26 | 2019-03-26 | COMP | 2019-04-15 | COMP | 2019-04-15 | COMP | 2019-12-29 | INPR | 2019-07-26 | COMP | Rule 16 | 25 | 9 | 15 | 1 |  |  | 119
10568 | 2019-02-07 | 2019-03-20 | 2019-07-28 | 2020-03-13 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-10-13 | COMP | 2020-11-21 | COMP | Rule 16 | 29 | 91 | 44 | 1 | 108 | 28 | 453
10675 | 2019-02-07 | 2019-03-25 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-29 | COMP | 2019-06-03 | COMP | 2019-06-04 | COMP | 2019-07-09 | COMP | Rule 16 | 32 | 33 | 15 | 4 | 2 | 25 | 106
10711 | 2019-02-07 | 2019-03-27 | 2019-07-16 | 2019-07-16 | COMP | 2019-10-09 | COMP | 2019-10-14 | COMP | 2020-09-28 | COMP | 2021-02-26 | COMP | Rule 15/16 | 34 | 78 | 61 | 4 | 242 | 103 | 517
10725 | 2019-02-07 | 2019-03-28 | 2019-05-24 | 2019-05-24 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2020-01-15 | COMP | 2020-02-06 | COMP | Rule 16 | 35 | 42 | 51 | 1 | 111 | 16 | 251
10984 | 2019-02-07 | 2019-04-08 | 2019-06-27 | 2019-06-27 | COMP | 2021-03-16 | COMP | 2021-05-05 | COMP | 2021-03-30 | COMP | 2021-06-13 | COMP | Rule 16 | 42 | 58 | 431 | 37 | 0 | 27 | 591
11133 | 2019-02-07 | 2019-04-15 | 2019-09-06 | 2019-09-06 | COMP | 2019-10-01 | COMP | 2020-01-15 | COMP | 2020-03-16 | COMP | 2020-06-27 | COMP | Rule 15/16 | 47 | 102 | 18 | 72 | 42 | 74 | 350
11418 | 2019-02-07 | 2019-04-26 | 2019-07-25 | 2019-07-25 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-11-26 | COMP | 2020-01-06 | COMP | Rule 16 | 56 | 63 | 62 | 1 | 26 | 26 | 229
11656 | 2019-02-07 | 2019-05-07 | 2019-08-14 | 2019-08-14 | COMP | 2019-10-21 | COMP | 2019-11-14 | COMP | 2019-11-14 | COMP | 2019-12-19 | COMP | Rule 15/16 | 63 | 70 | 48 | 18 | 1 | 24 | 219
11733 | 2019-02-07 | 2019-05-09 | 2019-10-14 | 2019-10-22 | COMP | 2020-01-08 | COMP | 2020-05-27 | COMP | 2020-05-28 | COMP | 2020-11-16 | COMP | Rule 15/16 | 65 | 110 | 52 | 98 | 2 | 121 | 449
11931 | 2019-02-07 | 2019-05-17 | 2019-09-30 | 2019-11-21 | COMP | 2019-12-03 | COMP | 2019-12-11 | COMP | 2019-12-27 | COMP | 2020-04-13 | COMP | Rule 16 | 71 | 94 | 7 | 7 | 12 | 74 | 297
11953 | 2019-02-07 | 2019-05-20 | 2019-08-12 | 2019-08-12 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP |  | INPR | 2020-05-08 | COMP | Rule 16 | 72 | 59 | 43 | 1 |  |  | 316
12644 | 2019-02-07 | 2019-06-17 | 2020-04-20 | 2020-04-20 | COMP | 2021-06-24 | COMP | 2022-12-29 | COMP | 2023-01-23 | COMP | 2023-03-09 | COMP | Rule 15/16 | 91 | 212 | 299 | 381 | 16 | 33 | 1027
13050 | 2019-02-07 | 2019-07-09 | 2019-09-12 | 2019-12-06 | COMP | 2019-12-10 | COMP | 2020-07-24 | COMP | 2020-08-11 | COMP | 2020-09-24 | COMP | Rule 15/16 | 106 | 47 | 3 | 159 | 13 | 32 | 413
13332 | 2019-02-07 | 2019-07-23 | 2019-12-04 | 2019-12-26 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-05-22 | COMP | 2020-06-15 | COMP | Rule 16 | 116 | 93 | 3 | 1 | 102 | 16 | 341
14296 | 2019-02-07 | 2019-09-04 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2023-04-30 | INPR | 2020-06-15 | COMP | Rule 16 | 146 | 71 | 23 | 1 |  |  | 341
14358 | 2019-02-07 | 2019-09-05 | 2020-02-01 | 2020-02-01 | COMP | 2020-08-05 | COMP | 2020-08-21 | COMP | 2020-08-20 | COMP | 2020-09-14 | COMP | Rule 16 | 147 | 101 | 131 | 13 | 0 | 16 | 405
9636 | 2019-02-08 | 2019-02-09 | 2019-05-06 | 2019-05-06 | COMP | 2019-05-02 | NOTN | 2019-09-09 | COMP | 2019-09-24 | NOTN | 2020-01-28 | COMP | Other | 1 | 60 |  | 88 |  |  | 243
9701 | 2019-02-08 | 2019-02-12 | 2019-04-06 | 2019-04-06 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-09-22 | INPR | 2019-06-06 | COMP | Rule 16 | 3 | 38 | 22 | 1 |  |  | 83
9745 | 2019-02-08 | 2019-02-13 | 2019-06-14 | 2019-06-14 | COMP | 2019-10-28 | COMP | 2019-08-09 | COMP |  | INPR | 2020-12-19 | COMP | Rule 15/16 | 4 | 86 | 95 |  |  |  | 470
9860 | 2019-02-08 | 2019-02-20 | 2019-05-02 | 2019-05-02 | COMP | 2019-06-25 | COMP | 2019-10-22 | COMP | 2019-12-09 | COMP | 2020-01-13 | COMP | Rule 16 | 8 | 52 | 38 | 84 | 32 | 24 | 233
9965 | 2019-02-08 | 2019-02-25 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-15 | COMP | 2019-11-19 | COMP | 2019-10-29 | COMP | 2019-12-20 | COMP | Rule 15/16 | 11 | 83 | 17 | 90 | 0 | 22 | 219
9997 | 2019-02-08 | 2019-02-25 | 2019-06-28 | 2019-06-28 | COMP | 2019-09-04 | COMP | 2019-11-20 | COMP | 2019-10-29 | COMP | 2019-12-20 | COMP | Rule 15/16 | 11 | 89 | 47 | 55 | 0 | 21 | 219
10084 | 2019-02-08 | 2019-03-01 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-28 | COMP | 2019-06-12 | COMP | 2019-07-11 | COMP | 2019-07-18 | COMP | Rule 15/16 | 15 | 56 | 7 | 12 | 21 | 6 | 112
10113 | 2019-02-08 | 2019-03-04 | 2019-04-26 | 2019-04-26 | COMP | 2019-04-29 | NOTN | 2019-05-07 | COMP | 2019-04-30 | COMP | 2019-06-18 | COMP | Other | 16 | 40 |  | 8 | 0 | 30 | 91
10139 | 2019-02-08 | 2019-03-04 | 2019-05-09 | 2019-05-09 | COMP | 2019-05-13 | COMP | 2019-05-16 | COMP | 2019-05-14 | COMP | 2019-07-29 | COMP | Rule 16 | 16 | 49 | 3 | 4 | 0 | 51 | 119
10853 | 2019-02-08 | 2019-04-02 | 2019-07-16 | 2020-02-14 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-06-22 | COMP | 2020-07-20 | COMP | Rule 15/16 | 37 | 74 | 21 | 1 | 70 | 21 | 365
11187 | 2019-02-08 | 2019-04-16 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-07-01 | COMP | 2019-08-27 | COMP | Rule 16 | 47 | 36 | 28 | 1 | 0 | 32 | 140
11490 | 2019-02-08 | 2019-04-29 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2019-12-05 | COMP | 2020-05-20 | COMP | Rule 16 | 56 | 62 | 22 | 1 | 71 | 116 | 323
11624 | 2019-02-08 | 2019-05-06 | 2019-05-26 | 2019-05-26 | COMP | 2019-09-23 | COMP | 2020-01-21 | COMP | 2020-01-23 | COMP | 2020-03-10 | COMP | Rule 16 | 61 | 15 | 83 | 81 | 3 | 33 | 272
11688 | 2019-02-08 | 2019-05-07 | 2019-08-03 | 2019-08-03 | COMP | 2019-09-12 | COMP | 2020-01-23 | COMP | 2020-08-03 | COMP | 2020-12-03 | COMP | Rule 16 | 62 | 62 | 28 | 90 | 136 | 85 | 459
11748 | 2019-02-08 | 2019-05-09 | 2019-10-01 | 2019-10-01 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2021-04-22 | COMP | 2021-06-15 | COMP | Rule 16 | 64 | 101 | 38 | 1 | 355 | 38 | 592
11786 | 2019-02-08 | 2019-05-10 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-15 | COMP | 2019-09-11 | COMP | 2020-01-19 | INPR | 2019-09-14 | COMP | Rule 16 | 65 | 35 | 11 | 42 |  |  | 152
11890 | 2019-02-08 | 2019-05-15 | 2019-06-20 | 2019-06-20 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2020-01-08 | COMP | 2020-01-24 | COMP | Rule 15/16 | 68 | 26 | 53 | 1 | 86 | 12 | 241
11891 | 2019-02-08 | 2019-05-15 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-05 | COMP | 2019-11-12 | COMP |  |  | 2020-01-19 | COMP | Rule 16 | 68 | 52 | 28 | 48 |  |  | 237
11892 | 2019-02-08 | 2019-05-15 | 2019-07-29 | 2019-07-29 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2020-05-27 | COMP | 2020-03-03 | COMP | Rule 16 | 68 | 52 | 11 | 1 | 199 |  | 267
11893 | 2019-02-08 | 2019-05-15 | 2019-07-29 | 2019-07-29 | COMP | 2019-08-06 | COMP | 2019-09-16 | COMP | 2019-11-26 | COMP | 2019-12-09 | COMP | Rule 16 | 68 | 52 | 7 | 29 | 51 | 8 | 210
11926 | 2019-02-08 | 2019-05-16 | 2019-07-22 | 2019-07-22 | COMP | 2019-07-23 | NOTN | 2019-07-23 | COMP | 2019-08-15 | COMP | 2019-10-07 | COMP | Other | 69 | 46 |  | 2 | 18 | 37 | 168
11985 | 2019-02-08 | 2019-05-20 | 2019-06-18 | 2022-04-08 | COMP | 2022-05-18 | COMP | 2022-05-18 | COMP | 2024-03-02 | INPR | 2023-01-18 | COMP | Rule 16 | 71 | 21 | 29 | 1 |  |  | 991
12148 | 2019-02-08 | 2019-05-24 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-04 | NOTN | 2019-12-06 | COMP | 2019-12-23 | COMP | 2020-02-05 | COMP | Other | 75 | 133 |  | 3 | 12 | 30 | 249
12433 | 2019-02-08 | 2019-06-06 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-08 | COMP | 2020-09-11 | COMP | 2020-11-23 | COMP | 2020-12-15 | COMP | Rule 16 | 83 | 76 | 12 | 235 | 51 | 15 | 467
12726 | 2019-02-08 | 2019-06-20 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2021-01-12 | COMP | 2021-02-17 | COMP | Rule 16 | 93 | 58 | 28 | 1 | 309 | 25 | 509
13876 | 2019-02-08 | 2019-08-14 | 2019-11-08 | 2019-11-08 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-05-05 | COMP | 2020-05-26 | COMP | Rule 16 | 131 | 62 | 65 | 1 | 57 | 15 | 326
14155 | 2019-02-08 | 2019-08-28 | 2020-08-04 | 2020-08-04 | COMP | 2020-11-04 | COMP | 2021-11-01 | COMP | 2023-12-03 | INPR | 2022-09-21 | COMP | Rule 16 | 141 | 236 | 66 | 249 |  |  | 912
16371 | 2019-02-08 | 2019-12-23 | 2020-05-19 | 2020-07-23 | COMP | 2020-09-09 | COMP | 2020-11-23 | COMP | 2021-08-24 | COMP | 2021-09-24 | COMP | Rule 15/16 | 220 | 103 | 34 | 53 | 189 | 23 | 663
21061 | 2019-02-08 | 2020-07-20 | 2020-09-28 | 2020-09-29 | COMP | 2020-10-08 | COMP | 2020-11-30 | COMP | 2021-03-16 | COMP | 2021-04-22 | COMP | Rule 16 | 365 | 50 | 8 | 35 | 73 | 28 | 555
27829 | 2019-02-08 | 2021-05-11 | 2021-05-12 | 2021-05-12 | COMP | 2021-05-26 | NOTN | 2021-05-26 | COMP | 2021-07-23 | COMP | 2021-08-26 | COMP | Other | 568 | 2 |  | 11 | 41 | 25 | 643
11191 | 2019-02-09 | 2019-04-17 | 2019-08-13 | 2019-08-13 | COMP | 2020-08-31 | COMP | 2020-09-02 | COMP | 2020-08-07 | COMP | 2020-09-29 | COMP | Rule 16 | 47 | 83 | 266 | 3 | 0 | 19 | 414
11293 | 2019-02-09 | 2019-04-22 | 2019-05-24 | 2019-05-24 | COMP | 2019-05-30 | COMP | 2019-07-02 | COMP | 2019-09-23 | COMP | 2019-10-14 | COMP | Rule 16 | 50 | 25 | 4 | 24 | 58 | 16 | 172
11994 | 2019-02-09 | 2019-05-20 | 2019-08-16 | 2019-08-16 | COMP | 2019-08-27 | COMP | 2019-09-23 | COMP | 2019-10-04 | COMP | 2019-11-18 | COMP | Rule 15/16 | 70 | 63 | 8 | 19 | 10 | 31 | 196
14536 | 2019-02-09 | 2019-09-16 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-05 | NOTN | 2020-02-10 | COMP | 2020-02-13 | COMP | 2020-06-19 | COMP | Other | 152 | 96 |  | 5 | 4 | 90 | 343
10210 | 2019-02-10 | 2019-03-06 | 2019-04-13 | 2019-10-24 | COMP | 2019-11-27 | COMP | 2021-02-11 | COMP | 2021-03-22 | COMP | 2021-04-02 | COMP | Rule 16 | 17 | 28 | 24 | 303 | 27 | 10 | 540
9728 | 2019-02-11 | 2019-02-12 | 2019-04-25 | 2019-04-25 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2019-10-21 | INPR | 2019-07-10 | COMP | Rule 16 | 2 | 52 | 7 | 1 |  |  | 105
9852 | 2019-02-11 | 2019-02-20 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-28 | COMP | 2019-03-28 | COMP | 2019-04-23 | COMP | 2019-05-22 | COMP | Rule 16 | 7 | 12 | 16 | 1 | 19 | 22 | 72
9853 | 2019-02-11 | 2019-02-20 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-28 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-06-13 | COMP | Rule 16 | 7 | 12 | 16 | 54 | 1 | 2 | 87
9863 | 2019-02-11 | 2019-02-20 | 2019-03-07 | 2019-03-07 | COMP | 2019-03-28 | COMP | 2019-04-23 | COMP | 2019-04-24 | COMP | 2019-06-12 | COMP | Rule 16 | 7 | 12 | 16 | 19 | 2 | 35 | 86
9877 | 2019-02-11 | 2019-02-22 | 2019-09-10 | 2019-09-10 | COMP | 2019-11-15 | COMP | 2019-11-26 | COMP | 2020-01-02 | COMP | 2019-12-31 | COMP | Rule 15/16 | 9 | 140 | 48 | 8 | 24 |  | 224
10205 | 2019-02-11 | 2019-03-06 | 2019-06-04 | 2019-06-07 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-07-03 | COMP | 2019-09-12 | COMP | Rule 16 | 17 | 64 | 12 | 1 | 8 | 50 | 150
10244 | 2019-02-11 | 2019-03-07 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-03 | COMP | 2019-05-03 | COMP | 2020-01-14 | COMP | 2020-02-05 | COMP | Rule 16 | 18 | 32 | 11 | 1 | 175 | 16 | 248
10270 | 2019-02-11 | 2019-03-08 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-29 | COMP | 2019-07-02 | COMP | 2020-03-21 | INPR | 2019-12-04 | COMP | Rule 16 | 19 | 51 | 8 | 25 |  |  | 206
10519 | 2019-02-11 | 2019-03-19 | 2019-06-13 | 2019-06-13 | COMP | 2019-07-01 | COMP | 2019-07-15 | COMP | 2019-07-26 | COMP | 2019-08-07 | COMP | Rule 16 | 26 | 62 | 13 | 10 | 10 | 9 | 125
10571 | 2019-02-11 | 2019-03-20 | 2019-08-09 | 2019-08-09 | COMP | 2019-11-20 | COMP | 2020-08-13 | COMP | 2021-08-17 | COMP | 2021-09-02 | COMP | Rule 16 | 27 | 101 | 72 | 185 | 254 | 13 | 647
10609 | 2019-02-11 | 2019-03-22 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-18 | COMP | 2019-09-13 | COMP | 2019-10-11 | COMP | 2019-12-18 | COMP | Rule 16 | 29 | 60 | 24 | 41 | 21 | 46 | 216
10845 | 2019-02-11 | 2019-04-01 | 2019-07-25 | 2019-07-25 | COMP | 2019-11-05 | COMP | 2020-05-22 | COMP | 2021-12-08 | COMP | 2022-01-10 | COMP | Rule 15/16 | 35 | 82 | 73 | 137 | 389 | 24 | 735
11053 | 2019-02-11 | 2019-04-10 | 2019-07-12 | 2019-07-12 | COMP | 2019-10-04 | COMP | 2019-11-19 | COMP | 2023-04-30 | INPR | 2020-08-07 | COMP | Rule 16 | 42 | 66 | 60 | 32 |  |  | 378
11137 | 2019-02-11 | 2019-04-15 | 2019-06-17 | 2019-06-22 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-07-04 | COMP | Rule 16 | 45 | 45 | 5 | 1 | 1 | 4 | 101
11451 | 2019-02-11 | 2019-04-29 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-01 | COMP | 2020-01-07 | COMP | 2019-11-05 | COMP | 2020-01-30 | COMP | Rule 16 | 55 | 100 | 10 | 66 | 0 | 17 | 244
11678 | 2019-02-11 | 2019-05-07 | 2019-06-08 | 2019-06-08 | COMP | 2019-08-02 | COMP | 2019-08-27 | COMP | 2019-08-30 | COMP | 2019-10-03 | COMP | Rule 16 | 61 | 23 | 39 | 18 | 4 | 24 | 165
11701 | 2019-02-11 | 2019-05-08 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-22 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2019-12-13 | COMP | Rule 16 | 62 | 113 | 27 | 2 | 1 | 13 | 213
11703 | 2019-02-11 | 2019-05-08 | 2019-11-06 | 2019-11-25 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-07-07 | COMP | 2020-07-14 | COMP | Rule 16 | 62 | 128 | 24 | 1 | 132 | 6 | 360
11930 | 2019-02-11 | 2019-05-17 | 2019-06-27 | 2019-06-27 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-10-04 | COMP | 2019-10-18 | COMP | Rule 16 | 69 | 29 | 47 | 1 | 24 | 11 | 176
11986 | 2019-02-11 | 2019-05-20 | 2019-07-27 | 2019-07-27 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2019-12-05 | COMP | 2019-12-29 | COMP | Rule 16 | 70 | 48 | 36 | 1 | 55 | 16 | 222
12279 | 2019-02-11 | 2019-05-30 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2019-08-07 | COMP | 2019-09-06 | COMP | Rule 16 | 77 | 41 | 6 | 1 | 3 | 22 | 146
12532 | 2019-02-11 | 2019-06-12 | 2019-08-14 | 2019-08-14 | COMP | 2020-02-04 | COMP | 2020-02-05 | COMP | 2020-06-30 | COMP | 2020-09-22 | COMP | Rule 16 | 86 | 45 | 118 | 2 | 103 | 60 | 409
12679 | 2019-02-11 | 2019-06-18 | 2019-08-16 | 2019-09-09 | COMP | 2019-09-17 | COMP | 2020-05-21 | COMP | 2020-10-02 | COMP | 2020-12-08 | COMP | Rule 16 | 90 | 43 | 7 | 171 | 95 | 45 | 461
12796 | 2019-02-11 | 2019-06-24 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-30 | COMP | 2020-01-17 | COMP | 2020-01-27 | COMP | 2020-02-14 | COMP | Rule 16 | 94 | 99 | 32 | 14 | 6 | 15 | 255
12845 | 2019-02-11 | 2019-06-25 | 2020-05-11 | 2020-05-11 | COMP | 2020-08-06 | COMP | 2020-08-18 | COMP | 2021-07-26 | COMP | 2020-12-14 | COMP | Rule 15/16 | 95 | 221 | 63 | 9 | 235 |  | 465
13212 | 2019-02-11 | 2019-07-16 | 2019-12-06 | 2020-01-27 | COMP | 2020-04-22 | COMP | 2020-09-01 | COMP | 2020-09-21 | COMP | 2020-10-08 | COMP | Rule 15/16 | 109 | 100 | 62 | 94 | 14 | 14 | 421
13416 | 2019-02-11 | 2019-07-25 | 2020-01-07 | 2020-01-07 | COMP | 2020-11-18 | NOTN | 2020-12-14 | COMP | 2020-11-18 | COMP | 2021-02-16 | COMP | Other | 116 | 113 |  | 238 | 0 | 43 | 507
14124 | 2019-02-11 | 2019-08-26 | 2019-11-19 | 2019-11-19 | COMP | 2020-02-20 | COMP | 2020-09-30 | COMP | 2023-12-03 | INPR | 2020-11-03 | COMP | Rule 16 | 138 | 60 | 62 | 158 |  |  | 439
14288 | 2019-02-11 | 2019-09-03 | 2020-03-20 | 2020-03-20 | COMP | 2020-06-09 | COMP | 2020-08-13 | COMP | 2020-06-29 | COMP | 2020-12-12 | COMP | Rule 15/16 | 143 | 137 | 57 | 48 | 0 | 83 | 464
15215 | 2019-02-11 | 2019-10-21 | 2020-01-12 | 2020-01-22 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-04-28 | COMP | 2020-05-11 | COMP | Rule 15/16 | 177 | 55 | 55 | 1 | 15 | 10 | 315
15606 | 2019-02-11 | 2019-11-09 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-17 | COMP | 2020-05-27 | INPR | 2022-01-30 | REQD | 2020-07-28 | COMP | Rule 16 | 191 | 38 | 8 |  |  |  | 370
17684 | 2019-02-11 | 2020-02-24 | 2020-06-04 | 2020-06-04 | COMP | 2020-07-03 | COMP | 2020-06-19 | COMP | 2020-07-20 | COMP | 2020-12-30 | COMP | Rule 16 | 260 | 73 | 22 |  | 22 | 113 | 476
20297 | 2019-02-11 | 2020-06-15 | 2020-08-25 | 2020-08-25 | COMP | 2020-09-15 | COMP | 2021-03-31 | COMP | 2021-08-05 | COMP | 2021-05-11 | COMP | Rule 16 | 339 | 52 | 15 | 135 | 90 |  | 567
9819 | 2019-02-12 | 2019-02-19 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-14 | NOTN | 2019-11-07 | COMP | 2021-04-12 | COMP | 2021-04-21 | COMP | Other | 5 | 167 |  | 19 | 357 | 8 | 552
9937 | 2019-02-12 | 2019-02-23 | 2019-05-25 | 2019-06-07 | COMP | 2019-10-08 | COMP | 2020-01-08 | COMP | 2020-05-04 | COMP | 2020-07-20 | COMP | Rule 16 | 8 | 65 | 86 | 62 | 82 | 55 | 363
10257 | 2019-02-12 | 2019-03-07 | 2019-06-07 | 2019-06-07 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-07 | COMP | 2019-10-14 | COMP | Rule 16 | 17 | 66 | 37 | 1 | 7 | 48 | 171
10366 | 2019-02-12 | 2019-03-12 | 2019-05-04 | 2019-08-12 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-12-10 | COMP | 2020-02-14 | COMP | Rule 16 | 20 | 39 | 31 | 1 | 53 | 46 | 254
10388 | 2019-02-12 | 2019-03-13 | 2019-07-03 | 2020-06-05 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-06-29 | COMP | 2020-09-04 | COMP | Rule 15/16 | 21 | 80 | 14 | 1 | 4 | 50 | 397
10708 | 2019-02-12 | 2019-03-27 | 2019-07-16 | 2020-05-29 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2023-01-28 | INPR | 2020-09-16 | COMP | Rule 16 | 31 | 78 | 48 | 1 |  |  | 404
10786 | 2019-02-12 | 2019-03-30 | 2019-08-07 | 2019-08-07 | COMP | 2019-03-30 | NOTN | 2019-10-03 | COMP | 2019-07-20 | COMP | 2020-08-13 | COMP | Other | 33 | 91 |  | 41 | 0 | 218 | 381
10804 | 2019-02-12 | 2019-03-30 | 2019-04-23 | 2019-04-23 | COMP | 2019-06-13 | COMP | 2019-06-13 | INPR | 2019-06-20 | COMP | 2019-06-25 | COMP | Rule 16 | 33 | 17 | 37 |  |  |  | 94
11003 | 2019-02-12 | 2019-04-09 | 2019-06-21 | 2019-07-08 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-07-19 | COMP | 2019-08-20 | COMP | Rule 16 | 40 | 53 | 4 | 1 | 7 | 23 | 133
11036 | 2019-02-12 | 2019-04-09 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-20 | COMP | 2019-09-06 | COMP | 2019-09-17 | COMP | 2019-10-02 | COMP | Rule 16 | 40 | 29 | 24 | 55 | 8 | 12 | 163
11304 | 2019-02-12 | 2019-04-22 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-26 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-11-05 | COMP | Rule 16 | 49 | 61 | 8 | 19 | 1 | 54 | 187
11335 | 2019-02-12 | 2019-04-23 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-12-02 | COMP | 2020-01-09 | COMP | Rule 16 | 50 | 57 | 7 | 1 | 92 | 27 | 229
11387 | 2019-02-12 | 2019-04-25 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-26 | COMP | 2020-07-23 | COMP | 2020-07-14 | COMP | 2020-11-19 | COMP | Rule 15/16 | 52 | 250 | 24 | 43 | 0 | 84 | 449
11771 | 2019-02-12 | 2019-05-10 | 2019-07-16 | 2019-09-19 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-11-25 | COMP | 2020-01-13 | COMP | Rule 15/16 | 63 | 46 | 27 | 1 | 21 | 32 | 231
11960 | 2019-02-12 | 2019-05-20 | 2019-08-13 | 2020-10-22 | COMP | 2021-02-12 | COMP | 2021-05-05 | COMP | 2021-09-20 | COMP | 2021-10-06 | COMP | Rule 15/16 | 69 | 60 | 76 | 58 | 96 | 13 | 669
11996 | 2019-02-12 | 2019-05-20 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-26 | COMP | 2020-12-30 | COMP | 2020-10-08 | COMP | 2021-02-03 | COMP | Rule 16 | 69 | 74 | 18 | 317 | 0 | 24 | 498
12716 | 2019-02-12 | 2019-06-19 | 2019-08-29 | 2019-11-05 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-02-27 | COMP | 2020-04-14 | COMP | Rule 16 | 90 | 51 | 54 | 1 | 23 | 34 | 295
12717 | 2019-02-12 | 2019-06-19 | 2019-08-28 | 2019-08-28 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2021-04-24 | INPR | 2020-04-02 | COMP | Rule 16 | 90 | 50 | 25 | 1 |  |  | 287
13195 | 2019-02-12 | 2019-07-15 | 2020-01-09 | 2020-01-09 | COMP | 2020-02-10 | COMP | 2020-07-30 | COMP | 2020-09-29 | COMP | 2021-01-05 | COMP | Rule 16 | 107 | 123 | 22 | 122 | 43 | 66 | 478
13547 | 2019-02-12 | 2019-07-31 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2019-09-11 | COMP | 2019-09-14 | COMP | Rule 16 | 119 | 6 | 8 | 1 | 18 | 3 | 150
13798 | 2019-02-12 | 2019-08-10 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-07 | COMP | 2020-06-01 | COMP | 2021-05-04 | COMP | 2021-06-14 | COMP | Rule 16 | 126 | 86 | 16 | 102 | 234 | 29 | 589
14872 | 2019-02-12 | 2019-10-01 | 2019-11-25 | 2019-11-25 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-02-18 | COMP | 2020-02-19 | COMP | Rule 16 | 162 | 39 | 14 | 1 | 43 | 2 | 256
15671 | 2019-02-12 | 2019-11-14 | 2020-01-14 | 2020-01-14 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-09-14 | COMP | 2020-11-05 | COMP | Rule 16 | 193 | 40 | 54 | 1 | 118 | 39 | 440
15987 | 2019-02-12 | 2019-12-04 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-28 | COMP | 2021-01-27 | COMP | 2021-02-02 | COMP | 2021-02-24 | COMP | Rule 15/16 | 205 | 143 | 22 | 125 | 5 | 16 | 512
17133 | 2019-02-12 | 2020-01-31 | 2020-12-12 | 2021-01-15 | COMP | 2021-03-10 | COMP | 2021-03-13 | COMP | 2021-03-10 | COMP | 2021-04-01 | COMP | Rule 15/16 | 244 | 220 | 37 | 3 | 0 | 14 | 538
18382 | 2019-02-12 | 2020-03-22 | 2020-07-21 | 2020-07-21 | COMP | 2020-08-14 | COMP | 2021-02-02 | COMP | 2020-10-28 | COMP | 2021-03-09 | COMP | Rule 16 | 278 | 86 | 19 | 116 | 0 | 25 | 521
4194 | 2019-02-13 | 2019-06-27 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-27 | COMP | 2019-10-29 | COMP | 2020-01-15 | COMP | 2020-02-18 | COMP | Rule 16 | 95 | 39 | 27 | 23 | 52 | 23 | 254
9903 | 2019-02-13 | 2019-02-22 | 2019-03-08 | 2019-03-08 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-04-09 | COMP | 2019-04-17 | COMP | Rule 16 | 7 | 11 | 21 | 1 | 3 | 7 | 45
10425 | 2019-02-13 | 2019-03-15 | 2019-06-27 | 2019-06-27 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2021-06-08 | COMP | 2021-06-30 | COMP | Rule 16 | 22 | 74 | 479 | 1 | 12 | 17 | 600
10556 | 2019-02-13 | 2019-03-20 | 2019-05-03 | 2019-11-20 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-06-09 | COMP | 2020-07-22 | COMP | Rule 16 | 25 | 33 | 30 | 1 | 109 | 32 | 364
10686 | 2019-02-13 | 2019-03-26 | 2019-07-15 | 2019-07-15 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-09-21 | COMP | 2020-11-20 | COMP | Rule 16 | 29 | 78 | 152 | 1 | 150 | 44 | 449
10719 | 2019-02-13 | 2019-03-28 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-07-01 | COMP | 2019-08-08 | COMP | Rule 16 | 31 | 56 | 7 | 1 | 6 | 28 | 124
10733 | 2019-02-13 | 2019-03-29 | 2019-12-07 | 2019-12-18 | COMP | 2020-01-03 | COMP | 2020-01-07 | COMP | 2020-02-03 | NOTN | 2020-03-27 | COMP | Rule 16 | 32 | 175 | 11 | 3 |  |  | 282
10862 | 2019-02-13 | 2019-04-02 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-22 | COMP | 2019-05-23 | COMP | 2019-07-09 | COMP | 2019-07-29 | COMP | Rule 16 | 34 | 10 | 28 | 2 | 32 | 15 | 116
10931 | 2019-02-13 | 2019-04-04 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-09-27 | COMP | 2019-10-15 | COMP | Rule 16 | 36 | 80 | 31 | 1 | 15 | 13 | 171
10988 | 2019-02-13 | 2019-04-08 | 2019-05-18 | 2019-05-18 | COMP | 2019-06-05 | COMP | 2019-08-29 | COMP | 2019-09-03 | COMP | 2019-09-10 | COMP | Rule 16 | 38 | 30 | 12 | 61 | 3 | 6 | 146
10992 | 2019-02-13 | 2019-04-09 | 2019-07-23 | 2019-07-23 | COMP | 2019-10-31 | COMP | 2020-01-22 | COMP | 2020-02-11 | COMP | 2020-04-10 | COMP | Rule 16 | 39 | 74 | 72 | 54 | 15 | 43 | 292
11076 | 2019-02-13 | 2019-04-11 | 2019-08-31 | 2019-08-31 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-10-23 | COMP | 2020-12-09 | COMP | Rule 16 | 41 | 100 | 114 | 1 | 177 | 31 | 460
11175 | 2019-02-13 | 2019-04-16 | 2019-07-27 | 2019-07-27 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2020-08-19 | COMP | 2020-10-12 | COMP | Rule 15/16 | 44 | 72 | 41 | 1 | 229 | 38 | 421
11375 | 2019-02-13 | 2019-04-24 | 2019-05-18 | 2019-05-18 | COMP | 2019-05-28 | COMP | 2019-07-01 | COMP | 2019-05-29 | COMP | 2019-07-14 | COMP | Rule 16 | 50 | 18 | 6 | 25 | 0 | 9 | 105
11379 | 2019-02-13 | 2019-04-24 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2020-04-14 | COMP | 2020-06-05 | COMP | Rule 15 | 50 | 77 | 11 | 1 | 159 | 38 | 331
11816 | 2019-02-13 | 2019-05-13 | 2019-09-18 | 2021-04-21 | COMP | 2021-05-05 | COMP | 2022-01-11 | COMP | 2022-01-06 | COMP | 2022-02-15 | COMP | Rule 16 | 63 | 90 | 11 | 174 | 0 | 25 | 758
12275 | 2019-02-13 | 2019-05-29 | 2020-02-27 | 2020-02-27 | COMP | 2020-04-01 | COMP | 2020-07-27 | COMP | 2020-10-21 | COMP | 2020-11-20 | COMP | Rule 15/16 | 74 | 188 | 25 | 83 | 62 | 22 | 449
12311 | 2019-02-13 | 2019-05-30 | 2019-08-28 | 2019-08-28 | COMP | 2020-06-11 | COMP | 2020-10-21 | COMP | 2020-11-16 | COMP | 2020-12-11 | COMP | Rule 16 | 75 | 64 | 198 | 94 | 18 | 18 | 462
12498 | 2019-02-13 | 2019-06-10 | 2019-07-26 | 2019-08-08 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2020-01-06 | COMP | 2020-01-16 | COMP | Rule 15/16 | 82 | 34 | 21 | 1 | 82 | 9 | 233
12740 | 2019-02-13 | 2019-06-20 | 2019-09-16 | 2019-09-16 | COMP | 2019-11-14 | COMP | 2019-12-10 | COMP | 2020-02-11 | COMP | 2020-02-21 | COMP | Rule 16 | 90 | 61 | 43 | 17 | 43 | 8 | 257
12763 | 2019-02-13 | 2019-06-21 | 2019-08-05 | 2019-09-14 | COMP | 2019-09-16 | NOTN | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-11-13 | COMP | Other | 91 | 31 |  | 1 | 1 | 42 | 191
13021 | 2019-02-13 | 2019-07-05 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2020-07-02 | COMP | 2020-07-07 | COMP | Rule 15/16 | 100 | 91 | 18 | 1 | 144 | 4 | 353
13356 | 2019-02-13 | 2019-07-22 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-15 | COMP | 2020-02-18 | COMP | 2020-03-03 | COMP | 2020-07-16 | COMP | Rule 16 | 111 | 119 | 4 | 23 | 11 | 97 | 360
13435 | 2019-02-13 | 2019-07-24 | 2020-01-02 | 2020-12-31 | COMP | 2021-03-03 | COMP | 2021-03-03 | COMP | 2020-12-31 | COMP | 2023-09-06 | COMP | Rule 16 | 113 | 111 | 42 | 1 | 0 | 633 | 1148
14122 | 2019-02-13 | 2019-08-26 | 2019-10-30 | 2019-10-30 | COMP | 2020-07-27 | COMP | 2021-02-25 | COMP | 2021-12-08 | COMP | 2022-02-01 | COMP | Rule 15/16 | 136 | 47 | 186 | 146 | 199 | 39 | 748
19416 | 2019-02-13 | 2020-05-05 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-12-01 | COMP | 2020-12-16 | COMP | Rule 16 | 309 | 33 | 29 | 1 | 86 | 12 | 465
4164 | 2019-02-14 | 2019-05-02 | 2019-05-13 | 2019-09-23 | COMP | 2019-12-02 | COMP | 2019-12-12 | COMP | 2019-08-02 | COMP | 2020-01-15 | COMP | Rule 16 | 55 | 8 | 48 | 9 | 0 | 23 | 231
9768 | 2019-02-14 | 2019-02-14 | 2019-03-18 | 2019-03-18 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2020-04-16 | COMP | 2020-05-20 | COMP | Rule 16 | 1 | 22 | 163 | 1 | 112 | 25 | 319
9975 | 2019-02-14 | 2019-02-25 | 2019-12-04 | 2020-08-02 | COMP | 2020-08-14 | COMP | 2020-03-10 | COMP | 2020-08-19 | COMP | 2020-10-08 | COMP | Rule 15/16 | 7 | 197 | 10 |  | 116 | 36 | 418
10056 | 2019-02-14 | 2019-02-28 | 2019-05-01 | 2019-05-09 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-07-09 | COMP | Rule 16 | 10 | 45 | 25 | 1 | 1 | 18 | 101
10099 | 2019-02-14 | 2019-03-01 | 2019-04-20 | 2019-04-20 | COMP | 2019-04-22 | NOTN | 2019-04-22 | COMP | 2019-05-20 | COMP | 2019-06-07 | COMP | Other | 11 | 36 |  | 1 | 21 | 14 | 80
10137 | 2019-02-14 | 2019-03-04 | 2019-06-07 | 2019-06-07 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-06-20 | COMP | 2019-07-24 | COMP | Rule 16 | 12 | 69 | 9 | 1 | 2 | 24 | 112
10224 | 2019-02-14 | 2019-03-06 | 2019-05-20 | 2019-05-20 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2020-02-04 | COMP | 2020-03-13 | COMP | Rule 16 | 14 | 54 | 45 | 1 | 134 | 28 | 271
10235 | 2019-02-14 | 2019-03-06 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-01 | COMP | 2019-04-01 | COMP | 2019-04-09 | COMP | 2019-04-15 | COMP | Rule 16 | 14 | 17 | 3 | 1 | 7 | 5 | 42
10364 | 2019-02-14 | 2019-03-12 | 2020-01-10 | 2020-01-10 | COMP | 2020-12-02 | COMP | 2020-12-17 | COMP | 2021-02-17 | COMP | 2021-05-13 | COMP | Rule 15/16 | 18 | 211 | 227 | 12 | 41 | 62 | 566
10724 | 2019-02-14 | 2019-03-28 | 2020-08-27 | 2020-08-27 | COMP | 2020-12-30 | COMP | 2020-12-30 | COMP | 2021-01-12 | COMP | 2021-02-22 | COMP | Rule 16 | 30 | 360 | 85 | 1 | 9 | 28 | 508
10730 | 2019-02-14 | 2019-03-28 | 2019-11-06 | 2021-03-10 | COMP | 2021-05-27 | COMP | 2023-06-12 | COMP |  | INPR | 2023-07-18 | COMP | Rule 15/16 | 30 | 157 | 57 | 513 |  |  | 1112
10879 | 2019-02-14 | 2019-04-03 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-11-15 | COMP | 2019-11-19 | COMP | Rule 16 | 34 | 62 | 6 | 1 | 92 | 3 | 194
10895 | 2019-02-14 | 2019-04-03 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-29 | COMP | 2019-11-25 | COMP | 2019-12-20 | NOTN | 2020-01-14 | COMP | Rule 16 | 34 | 62 | 21 | 84 |  |  | 230
11019 | 2019-02-14 | 2019-04-09 | 2019-09-14 | 2022-02-09 | COMP | 2022-03-21 | COMP | 2022-10-15 | COMP | 2022-10-31 | COMP | 2023-02-02 | COMP | Rule 15/16 | 38 | 111 | 28 | 146 | 11 | 63 | 998
11272 | 2019-02-14 | 2019-04-22 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-08-26 | COMP | 2019-08-29 | COMP | 2019-09-05 | COMP | Rule 16 | 47 | 47 | 4 | 40 | 4 | 5 | 142
11290 | 2019-02-14 | 2019-04-22 | 2019-05-16 | 2019-08-19 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2020-02-13 | COMP | 2020-03-20 | COMP | Rule 16 | 47 | 19 | 21 | 1 | 102 | 26 | 276
11336 | 2019-02-14 | 2019-04-23 | 2019-12-24 | 2020-05-11 | COMP | 2020-10-30 | COMP | 2020-12-07 | COMP | 2020-12-18 | COMP | 2021-01-26 | COMP | Rule 15/16 | 48 | 170 | 123 | 24 | 10 | 25 | 490
11355 | 2019-02-14 | 2019-04-24 | 2020-04-21 | 2020-11-07 | COMP | 2020-12-17 | COMP | 2020-12-11 | COMP | 2021-01-03 | COMP | 2021-01-25 | COMP | Rule 15/16 | 49 | 250 | 26 |  | 14 | 15 | 489
11397 | 2019-02-14 | 2019-04-24 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-11-27 | COMP | 2020-01-22 | COMP | Rule 16 | 49 | 80 | 27 | 1 | 47 | 36 | 235
11404 | 2019-02-14 | 2019-04-25 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-06-17 | COMP | 2019-07-30 | COMP | Rule 16 | 50 | 20 | 16 | 1 | 3 | 31 | 116
11429 | 2019-02-14 | 2019-04-27 | 2019-08-13 | 2019-08-13 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-11-01 | COMP | 2020-01-02 | COMP | Rule 16 | 51 | 75 | 57 | 1 | 2 | 40 | 222
11686 | 2019-02-14 | 2019-05-07 | 2019-09-18 | 2019-09-18 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2022-06-18 | INPR | 2021-06-11 | COMP | Rule 16 | 58 | 94 | 63 | 1 |  |  | 586
11964 | 2019-02-14 | 2019-05-20 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-21 | COMP | 2020-01-06 | COMP | 2020-02-11 | COMP | 2020-03-03 | COMP | Rule 16 | 67 | 58 | 9 | 93 | 26 | 15 | 263
12035 | 2019-02-14 | 2019-05-21 | 2019-10-03 | 2019-10-03 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-20 | COMP | 2019-12-17 | COMP | Rule 15/16 | 68 | 95 | 24 | 1 | 11 | 18 | 212
12039 | 2019-02-14 | 2019-05-21 | 2019-09-12 | 2019-11-08 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-04-26 | INPR | 2019-12-20 | COMP | Rule 16 | 68 | 80 | 10 | 1 |  |  | 215
12578 | 2019-02-14 | 2019-06-13 | 2019-08-24 | 2019-08-24 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2020-01-07 | COMP | 2020-01-23 | COMP | Rule 16 | 84 | 51 | 46 | 1 | 46 | 12 | 236
12616 | 2019-02-14 | 2019-06-17 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-26 | COMP | 2019-11-05 | COMP | 2019-10-08 | COMP | 2019-12-06 | COMP | Rule 16 | 86 | 50 | 23 | 29 | 0 | 21 | 205
12642 | 2019-02-14 | 2019-06-17 | 2020-02-04 | 2020-11-20 | COMP | 2020-12-09 | COMP | 2020-07-03 | COMP | 2020-09-29 | COMP | 2021-01-15 | COMP | Rule 15/16 | 86 | 159 | 12 |  | 62 | 74 | 484
12919 | 2019-02-14 | 2019-06-28 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-10-15 | COMP | 2019-10-31 | COMP | Rule 16 | 95 | 38 | 21 | 1 | 19 | 13 | 182
13058 | 2019-02-14 | 2019-07-09 | 2019-09-27 | 2019-09-27 | COMP | 2020-11-13 | COMP | 2020-11-13 | COMP | 2022-03-19 | INPR | 2021-01-14 | COMP | Rule 15/16 | 101 | 58 | 286 | 1 |  |  | 483
13090 | 2019-02-14 | 2019-07-10 | 2019-10-07 | 2019-10-07 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2020-10-30 | COMP | 2020-11-30 | COMP | Rule 16 | 102 | 63 | 270 | 1 | 2 | 19 | 452
13572 | 2019-02-14 | 2019-07-31 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-22 | COMP | 2021-08-03 | COMP | 2021-08-11 | COMP | 2021-09-30 | COMP | Rule 15/16 | 117 | 221 | 27 | 260 | 7 | 36 | 663
14013 | 2019-02-14 | 2019-08-21 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-07 | COMP | 2020-05-26 | COMP | 2020-08-04 | COMP | 2020-08-21 | COMP | Rule 15/16 | 132 | 94 | 23 | 76 | 51 | 14 | 385
14453 | 2019-02-14 | 2019-09-11 | 2020-03-08 | 2020-03-08 | COMP | 2020-04-08 | COMP | 2020-04-14 | COMP | 2020-04-09 | COMP | 2020-05-20 | COMP | Rule 16 | 146 | 121 | 23 | 5 | 0 | 27 | 319
15086 | 2019-02-14 | 2019-10-11 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-03-23 | COMP | 2020-04-24 | COMP | Rule 16 | 168 | 72 | 14 | 1 | 26 | 25 | 301
15642 | 2019-02-14 | 2019-11-13 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-15 | COMP | 2020-06-17 | COMP | 2020-07-21 | COMP | 2020-08-04 | COMP | Rule 16 | 190 | 134 | 14 | 3 | 25 | 11 | 372
17048 | 2019-02-14 | 2020-01-30 | 2020-08-13 | 2020-08-21 | COMP | 2020-08-31 | COMP | 2021-06-23 | COMP |  | INPR | 2021-06-26 | COMP | Rule 16 | 241 | 139 | 7 | 204 |  |  | 596
17191 | 2019-02-14 | 2020-02-04 | 2020-06-15 | 2020-06-15 | COMP | 2020-09-02 | COMP | 2021-01-28 | COMP | 2020-10-14 | COMP | 2021-03-24 | COMP | Rule 16 | 244 | 93 | 58 | 100 | 0 | 39 | 530
18219 | 2019-02-14 | 2020-03-16 | 2020-08-02 | 2020-08-02 | COMP | 2020-09-21 | COMP | 2021-08-11 | COMP | 2021-08-24 | COMP | 2021-09-02 | COMP | Rule 15/16 | 272 | 99 | 35 | 224 | 10 | 8 | 644
18458 | 2019-02-14 | 2020-03-25 | 2020-11-13 | 2020-11-13 | COMP | 2021-03-15 | COMP | 2022-06-10 | COMP | 2022-06-10 | COMP | 2022-08-05 | COMP | Rule 15/16 | 279 | 165 | 81 | 316 | 1 | 39 | 876
20638 | 2019-02-14 | 2020-06-30 | 2020-08-27 | 2020-08-27 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-10-28 | COMP | 2020-11-23 | COMP | Rule 16 | 347 | 43 | 13 | 1 | 32 | 18 | 449
9864 | 2019-02-15 | 2019-02-20 | 2019-05-04 | 2019-05-04 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-06-26 | COMP | 2019-07-05 | COMP | Rule 16 | 3 | 53 | 28 | 1 | 10 | 7 | 98
9865 | 2019-02-15 | 2019-02-20 | 2019-03-29 | 2019-03-29 | COMP | 2019-05-10 | COMP | 2019-04-19 | COMP | 2019-08-01 | COMP | 2019-08-12 | COMP | Rule 16 | 3 | 28 | 31 |  | 73 | 8 | 124
9866 | 2019-02-15 | 2019-02-20 | 2019-04-03 | 2019-04-03 | COMP | 2019-06-14 | COMP | 2019-04-19 | COMP | 2019-08-01 | COMP | 2019-08-12 | COMP | Rule 16 | 3 | 31 | 52 |  | 73 | 8 | 124
9867 | 2019-02-15 | 2019-02-20 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-06-13 | COMP | 2019-06-17 | COMP | Rule 16 | 3 | 38 | 26 | 1 | 18 | 3 | 85
9868 | 2019-02-15 | 2019-02-20 | 2019-03-27 | 2019-03-27 | COMP | 2019-05-20 | COMP | 2019-06-03 | COMP | 2019-10-07 | COMP | 2019-10-15 | COMP | Rule 16 | 3 | 26 | 39 | 10 | 89 | 7 | 169
9869 | 2019-02-15 | 2019-02-20 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-08-01 | COMP | 2019-08-13 | COMP | Rule 16 | 3 | 38 | 26 | 1 | 52 | 9 | 125
9991 | 2019-02-15 | 2019-02-26 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-11-14 | COMP | 2019-11-22 | COMP | Rule 15/16 | 7 | 78 | 16 | 1 | 92 | 7 | 196
10053 | 2019-02-15 | 2019-02-28 | 2019-04-01 | 2019-04-03 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-07-22 | COMP | 2019-08-08 | COMP | Rule 16 | 9 | 23 | 62 | 1 | 16 | 14 | 122
10280 | 2019-02-15 | 2019-03-08 | 2019-06-05 | 2019-06-28 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-11-05 | COMP | 2019-12-11 | COMP | Rule 16 | 15 | 63 | 81 | 1 | 11 | 24 | 207
10318 | 2019-02-15 | 2019-03-11 | 2019-05-29 | 2020-01-28 | COMP | 2020-01-28 | NOTN | 2020-01-28 | COMP | 2019-12-16 | COMP | 2020-03-03 | COMP | Other | 16 | 57 |  | 1 | 0 | 25 | 262
10423 | 2019-02-15 | 2019-03-15 | 2019-06-14 | 2019-07-16 | COMP | 2019-08-08 | COMP | 2019-08-08 | COMP | 2019-07-31 | COMP | 2019-09-16 | COMP | Rule 16 | 20 | 65 | 18 | 1 | 0 | 27 | 148
10427 | 2019-02-15 | 2019-03-15 | 2019-04-15 | 2019-04-15 | COMP | 2019-04-29 | COMP | 2019-04-30 | NOTN | 2019-04-26 | COMP | 2019-05-03 | COMP | Rule 16 | 20 | 22 | 11 |  |  |  | 55
10465 | 2019-02-15 | 2019-03-18 | 2019-04-08 | 2019-04-08 | COMP | 2019-03-18 | NOTN | 2019-04-08 | COMP | 2023-02-24 | COMP | 2023-04-24 | COMP | Other | 21 | 16 |  | 1 | 977 | 42 | 1053
10471 | 2019-02-15 | 2019-03-19 | 2021-08-17 | 2022-06-09 | COMP | 2022-08-26 | COMP | 2023-07-06 | COMP | 2023-07-10 | COMP | 2023-08-16 | COMP | Rule 15/16 | 22 | 610 | 55 | 214 | 3 | 28 | 1132
10600 | 2019-02-15 | 2019-03-21 | 2019-06-25 | 2019-06-25 | COMP | 2020-04-06 | COMP | 2020-04-07 | COMP | 2020-09-09 | COMP | 2020-10-05 | COMP | Rule 16 | 24 | 68 | 196 | 2 | 110 | 19 | 414
10801 | 2019-02-15 | 2019-03-29 | 2019-06-11 | 2019-06-11 | COMP | 2019-06-20 | COMP | 2019-06-21 | COMP | 2019-07-30 | COMP | 2019-08-05 | COMP | Rule 16 | 30 | 52 | 8 | 2 | 27 | 5 | 119
10878 | 2019-02-15 | 2019-04-03 | 2019-07-15 | 2019-07-15 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-08-28 | COMP | Rule 16 | 33 | 72 | 14 | 1 | 1 | 20 | 136
10904 | 2019-02-15 | 2019-04-04 | 2019-09-25 | 2019-09-25 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2022-06-18 | INPR | 2020-11-13 | COMP | Rule 16 | 34 | 122 | 254 | 1 |  |  | 442
11299 | 2019-02-15 | 2019-04-23 | 2019-07-11 | 2019-07-11 | COMP | 2019-08-09 | COMP | 2019-09-15 | COMP | 2020-02-29 | INPR | 2019-11-05 | COMP | Rule 16 | 47 | 56 | 22 | 25 |  |  | 184
11308 | 2019-02-15 | 2019-04-22 | 2019-07-18 | 2019-07-18 | COMP | 2019-08-07 | COMP | 2019-08-26 | COMP | 2019-08-30 | COMP | 2019-09-19 | COMP | Rule 16 | 46 | 62 | 15 | 14 | 5 | 14 | 151
11311 | 2019-02-15 | 2019-04-23 | 2019-05-15 | 2019-05-15 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-09-03 | COMP | 2019-11-07 | COMP | Rule 15/16 | 47 | 17 | 35 | 1 | 43 | 48 | 186
11446 | 2019-02-15 | 2019-04-29 | 2019-08-28 | 2019-08-28 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-19 | COMP | 2020-01-22 | COMP | Rule 16 | 51 | 86 | 53 | 1 | 6 | 42 | 234
11477 | 2019-02-15 | 2019-04-29 | 2019-06-11 | 2019-06-11 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2019-08-06 | COMP | 2019-08-22 | COMP | Rule 16 | 51 | 31 | 5 | 1 | 36 | 13 | 132
11629 | 2019-02-15 | 2019-05-06 | 2019-12-17 | 2019-12-17 | COMP | 2020-02-27 | COMP | 2020-05-12 | COMP |  | INPR | 2020-09-10 | COMP | Rule 15/16 | 56 | 156 | 49 | 54 |  |  | 397
11642 | 2019-02-15 | 2019-05-07 | 2019-05-24 | 2019-05-24 | COMP | 2019-05-25 | NOTN | 2019-05-25 | COMP | 2019-05-25 | COMP | 2019-06-28 | COMP | Other | 57 | 14 |  | 1 | 0 | 24 | 94
11717 | 2019-02-15 | 2019-05-09 | 2019-09-12 | 2019-09-12 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-06-17 | COMP | 2020-09-24 | COMP | Rule 16 | 59 | 88 | 65 | 1 | 128 | 71 | 407
11907 | 2019-02-15 | 2019-05-16 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-02 | COMP | 2019-09-19 | COMP | 2020-01-07 | COMP | 2020-01-14 | COMP | Rule 16 | 64 | 48 | 8 | 34 | 74 | 6 | 229
12397 | 2019-02-15 | 2019-06-04 | 2019-07-12 | 2019-07-12 | COMP | 2020-05-08 | COMP | 2019-10-02 | COMP | 2020-09-23 | COMP | 2021-04-25 | COMP | Rule 16 | 76 | 28 | 208 |  | 247 | 146 | 551
13019 | 2019-02-15 | 2019-07-05 | 2019-09-17 | 2019-09-17 | COMP | 2019-12-03 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-06-24 | COMP | Rule 16 | 98 | 52 | 53 | 66 | 1 | 77 | 342
13868 | 2019-02-15 | 2019-08-14 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-18 | COMP | 2019-11-04 | COMP | 2019-11-15 | COMP | 2019-12-10 | COMP | Rule 16 | 126 | 42 | 6 | 12 | 9 | 16 | 206
14611 | 2019-02-15 | 2019-09-18 | 2019-11-03 | 2019-11-03 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-25 | COMP | 2020-01-08 | COMP | Rule 16 | 150 | 33 | 7 | 1 | 9 | 29 | 225
15670 | 2019-02-15 | 2019-11-14 | 2020-01-27 | 2020-01-27 | COMP | 2020-04-22 | COMP | 2020-05-07 | COMP | 2020-05-26 | COMP | 2020-06-10 | COMP | Rule 15/16 | 190 | 48 | 62 | 12 | 13 | 12 | 332
16748 | 2019-02-15 | 2020-01-15 | 2020-02-17 | 2020-02-17 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2021-10-23 | INPR | 2020-06-04 | COMP | Rule 16 | 230 | 22 | 29 | 1 |  |  | 328
16845 | 2019-02-15 | 2020-01-21 | 2020-04-02 | 2020-04-02 | COMP | 2020-05-28 | COMP | 2020-05-28 | COMP | 2020-07-13 | COMP | 2020-08-11 | COMP | Rule 16 | 233 | 52 | 40 | 1 | 33 | 22 | 376
18730 | 2019-02-15 | 2020-04-06 | 2020-09-02 | 2020-09-02 | COMP | 2020-09-21 | COMP | 2021-01-07 | COMP |  | INPR | 2021-02-08 | COMP | Rule 15/16 | 286 | 107 | 13 | 74 |  |  | 498
10358 | 2019-02-16 | 2019-03-12 | 2019-06-28 | 2019-06-28 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-13 | COMP | 2020-01-22 | COMP | Rule 15/16 | 16 | 78 | 130 | 1 | 6 | 7 | 233
10500 | 2019-02-16 | 2019-03-18 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-17 | COMP | 2019-05-17 | COMP | 2019-10-07 | COMP | 2019-10-15 | COMP | Rule 16 | 20 | 21 | 25 | 1 | 99 | 7 | 168
11360 | 2019-02-16 | 2019-04-24 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-30 | COMP | 2019-09-03 | COMP | 2019-10-18 | COMP | 2019-11-13 | COMP | Rule 16 | 47 | 74 | 18 | 2 | 34 | 18 | 188
11835 | 2019-02-16 | 2019-05-14 | 2019-10-01 | 2019-10-01 | COMP | 2020-02-05 | COMP | 2020-02-27 | COMP | 2020-02-07 | COMP | 2020-03-09 | COMP | Rule 16 | 61 | 98 | 86 | 16 | 0 | 8 | 265
11918 | 2019-02-16 | 2019-05-16 | 2019-10-16 | 2019-10-16 | COMP | 2020-01-15 | COMP | 2020-01-30 | COMP | 2020-01-15 | COMP | 2020-02-26 | COMP | Rule 16 | 63 | 107 | 61 | 11 | 0 | 19 | 257
10552 | 2019-02-17 | 2019-03-20 | 2019-07-05 | 2019-07-05 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2020-02-29 | INPR | 2019-11-14 | COMP | Rule 15/16 | 22 | 76 | 29 | 1 |  |  | 189
11171 | 2019-02-17 | 2019-04-16 | 2019-06-19 | 2019-06-26 | COMP | 2019-07-05 | COMP | 2019-07-12 | COMP | 2019-07-01 | COMP | 2019-08-13 | COMP | Rule 16 | 41 | 46 | 7 | 6 | 0 | 23 | 124
4192 | 2019-02-18 | 2019-06-21 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-04 | COMP | 2019-10-30 | COMP | 2020-03-16 | COMP | 2020-05-20 | COMP | Rule 16 | 88 | 62 | 13 | 19 | 92 | 48 | 317
9917 | 2019-02-18 | 2019-02-22 | 2020-12-22 | 2020-12-22 | COMP | 2021-04-20 | COMP | 2022-09-02 | COMP | 2022-09-21 | COMP | 2022-10-21 | COMP | Rule 15/16 | 4 | 463 | 82 | 348 | 13 | 23 | 928
9918 | 2019-02-18 | 2019-02-22 | 2020-03-31 | 2020-04-13 | COMP | 2021-05-18 | COMP | 2022-05-23 | COMP | 2022-05-23 | COMP | 2022-07-16 | COMP | Rule 15/16 | 4 | 278 | 278 | 257 | 1 | 37 | 859
9976 | 2019-02-18 | 2019-02-25 | 2019-03-19 | 2019-03-19 | COMP | 2019-04-12 | COMP | 2019-12-23 | COMP | 2020-04-22 | COMP | 2020-06-01 | COMP | Rule 15/16 | 5 | 17 | 19 | 176 | 84 | 28 | 324
9977 | 2019-02-18 | 2019-02-25 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-25 | COMP | 2019-12-05 | COMP | 2019-12-27 | COMP | 2020-01-28 | COMP | Rule 16 | 5 | 57 | 30 | 113 | 16 | 21 | 237
10369 | 2019-02-18 | 2019-03-12 | 2019-05-12 | 2020-08-24 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2021-01-19 | COMP | 2021-03-23 | COMP | Rule 16 | 16 | 44 | 47 | 1 | 54 | 45 | 527
10445 | 2019-02-18 | 2019-03-16 | 2019-08-05 | 2021-05-06 | COMP | 2021-05-19 | COMP | 2021-07-12 | COMP | 2021-07-09 | COMP | 2021-08-06 | COMP | Rule 16 | 19 | 99 | 10 | 37 | 0 | 20 | 623
10450 | 2019-02-18 | 2019-03-17 | 2019-07-13 | 2019-07-13 | COMP | 2019-07-26 | COMP | 2019-08-22 | COMP | 2019-08-30 | COMP | 2019-09-30 | COMP | Rule 16 | 19 | 83 | 10 | 20 | 7 | 21 | 157
11218 | 2019-02-18 | 2019-04-17 | 2019-07-09 | 2019-07-09 | COMP | 2019-08-08 | COMP | 2019-08-13 | COMP | 2019-08-12 | COMP | 2019-09-11 | COMP | Rule 16 | 42 | 58 | 23 | 4 | 0 | 21 | 144
11665 | 2019-02-18 | 2019-05-07 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2021-08-28 | COMP | 2021-09-10 | COMP | Rule 16 | 56 | 138 | 16 | 1 | 431 | 9 | 647
12682 | 2019-02-18 | 2019-06-18 | 2019-09-05 | 2019-09-06 | COMP | 2019-09-18 | COMP | 2019-09-18 | COMP | 2020-03-01 | INPR | 2019-10-03 | COMP | Rule 16 | 85 | 56 | 9 | 1 |  |  | 160
13064 | 2019-02-18 | 2019-07-08 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-03 | COMP | 2019-12-02 | COMP | 2019-12-06 | COMP | 2019-12-23 | COMP | Rule 16 | 98 | 58 | 6 | 40 | 5 | 12 | 214
14808 | 2019-02-18 | 2019-09-28 | 2019-12-14 | 2019-12-14 | COMP | 2020-03-09 | COMP | 2020-12-16 | COMP | 2020-12-18 | COMP | 2021-02-04 | COMP | Rule 16 | 156 | 52 | 57 | 198 | 3 | 32 | 495
9889 | 2019-02-19 | 2019-02-21 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-18 | COMP | 2019-11-15 | COMP | 2020-07-02 | COMP | 2020-01-08 | COMP | Rule 16 | 3 | 152 | 18 | 20 | 158 |  | 224
10102 | 2019-02-19 | 2019-03-01 | 2019-07-01 | 2019-07-02 | COMP | 2021-06-18 | COMP | 2021-07-06 | COMP |  | INPR | 2021-07-12 | COMP | Rule 16 | 9 | 86 | 495 | 12 |  |  | 604
10190 | 2019-02-19 | 2019-03-05 | 2019-05-11 | 2019-05-11 | COMP | 2019-06-18 | COMP | 2019-06-18 | COMP | 2019-06-26 | COMP | 2019-08-02 | COMP | Rule 16 | 11 | 49 | 26 | 1 | 7 | 27 | 117
10231 | 2019-02-19 | 2019-03-07 | 2019-06-08 | 2019-06-11 | COMP | 2019-07-15 | COMP | 2019-10-03 | COMP | 2019-09-09 | COMP | 2019-11-07 | COMP | Rule 16 | 13 | 66 | 24 | 58 | 0 | 26 | 185
10252 | 2019-02-19 | 2019-03-07 | 2019-10-06 | 2020-01-31 | COMP | 2020-06-10 | COMP | 2020-11-02 | COMP | 2020-12-28 | COMP | 2021-01-22 | COMP | Rule 15/16 | 13 | 149 | 92 | 103 | 37 | 18 | 486
10362 | 2019-02-19 | 2019-03-12 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-11-05 | COMP | 2019-11-06 | COMP | Rule 16 | 16 | 78 | 22 | 1 | 70 | 2 | 184
10412 | 2019-02-19 | 2019-03-15 | 2019-04-13 | 2019-04-13 | COMP | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-10-21 | INPR | 2019-06-14 | COMP | Rule 16 | 19 | 21 | 11 | 1 |  |  | 83
10430 | 2019-02-19 | 2019-03-15 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-09 | COMP | 2019-05-07 | NOTN | 2019-05-09 | COMP | 2019-05-13 | COMP | Rule 16 | 19 | 35 | 6 |  |  |  | 60
10444 | 2019-02-19 | 2019-03-16 | 2019-05-29 | 2019-05-29 | COMP | 2019-06-06 | COMP | 2019-06-12 | COMP | 2019-06-13 | COMP | 2019-08-08 | COMP | Rule 16 | 19 | 52 | 7 | 5 | 2 | 40 | 121
10524 | 2019-02-19 | 2019-03-19 | 2019-04-17 | 2019-04-17 | COMP | 2019-05-07 | COMP | 2019-05-22 | COMP | 2019-05-23 | COMP | 2019-06-21 | COMP | Rule 16 | 21 | 22 | 15 | 12 | 2 | 21 | 88
10603 | 2019-02-19 | 2019-03-21 | 2019-06-07 | 2019-06-07 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-05-01 | COMP | 2020-05-04 | COMP | Rule 16 | 23 | 56 | 110 | 1 | 118 | 2 | 305
10607 | 2019-02-19 | 2019-03-22 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-08-09 | COMP | 2019-08-15 | COMP | Rule 16 | 24 | 46 | 22 | 1 | 33 | 5 | 126
10678 | 2019-02-19 | 2019-03-26 | 2019-06-08 | 2020-09-02 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2021-01-04 | COMP | 2021-03-19 | COMP | Rule 16 | 26 | 53 | 38 | 1 | 46 | 53 | 525
11209 | 2019-02-19 | 2019-04-17 | 2019-08-26 | 2019-08-26 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2020-01-07 | COMP | 2020-02-10 | COMP | Rule 15/16 | 42 | 92 | 29 | 1 | 63 | 24 | 246
11484 | 2019-02-19 | 2019-04-29 | 2019-09-13 | 2020-02-10 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-03-10 | COMP | 2020-04-15 | COMP | Rule 16 | 50 | 97 | 17 | 1 | 5 | 27 | 292
11511 | 2019-02-19 | 2019-04-30 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-02-27 | COMP | 2020-06-08 | COMP | Rule 16 | 51 | 102 | 48 | 1 | 60 | 72 | 329
11536 | 2019-02-19 | 2019-05-01 | 2019-08-24 | 2019-08-24 | COMP | 2020-01-03 | COMP | 2020-01-27 | COMP | 2020-01-17 | COMP | 2020-02-15 | COMP | Rule 16 | 52 | 81 | 89 | 16 | 0 | 15 | 250
11625 | 2019-02-19 | 2019-05-06 | 2019-08-26 | 2019-08-26 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-11-13 | COMP | 2019-12-17 | COMP | Rule 16 | 55 | 79 | 3 | 1 | 54 | 23 | 210
11769 | 2019-02-19 | 2019-05-09 | 2019-07-31 | 2021-04-16 | COMP | 2021-09-30 | COMP | 2021-11-27 | COMP | 2023-11-12 | INPR | 2022-03-10 | COMP | Rule 16 | 58 | 58 | 117 | 39 |  |  | 771
11827 | 2019-02-19 | 2019-05-14 | 2019-08-16 | 2019-08-16 | COMP | 2019-09-24 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-12-10 | COMP | Other | 61 | 67 | 27 | 12 | 1 | 42 | 205
11836 | 2019-02-19 | 2019-05-14 | 2020-05-22 | 2021-02-09 | COMP | 2021-03-01 | COMP | 2023-04-05 | COMP | 2022-10-13 | COMP | 2023-06-14 | COMP | Rule 15/16 | 61 | 259 | 14 | 529 | 0 | 50 | 1088
11837 | 2019-02-19 | 2019-05-14 | 2019-07-08 | 2019-07-08 | COMP | 2019-07-17 | COMP | 2021-04-23 | COMP | 2019-08-05 | COMP | 2022-07-13 | COMP | Rule 16 | 61 | 38 | 8 | 446 | 0 | 308 | 857
11888 | 2019-02-19 | 2019-05-15 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-10 | COMP | 2019-11-04 | COMP | 2019-10-12 | COMP | 2019-11-13 | COMP | Rule 16 | 62 | 91 | 14 | 18 | 0 | 7 | 188
12368 | 2019-02-19 | 2019-06-03 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-08-20 | COMP | 2019-09-24 | COMP | Rule 16 | 74 | 37 | 11 | 1 | 10 | 25 | 153
13029 | 2019-02-19 | 2019-07-07 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-21 | COMP | 2020-01-02 | COMP | 2020-02-14 | COMP | 2020-07-14 | COMP | Rule 15/16 | 97 | 70 | 28 | 27 | 31 | 106 | 355
13440 | 2019-02-19 | 2019-07-25 | 2019-09-30 | 2019-09-30 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2021-05-30 | INPR | 2020-05-20 | COMP | Other | 111 | 47 | 106 | 1 |  |  | 317
13441 | 2019-02-19 | 2019-07-25 | 2019-10-29 | 2019-10-29 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-05-01 | COMP | 2020-05-16 | COMP | Other | 111 | 68 | 85 | 1 | 43 | 11 | 314
13442 | 2019-02-19 | 2019-07-25 | 2019-10-09 | 2019-10-09 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2021-05-30 | INPR | 2020-05-26 | COMP | Other | 111 | 54 | 99 | 1 |  |  | 320
13443 | 2019-02-19 | 2019-07-25 | 2019-10-09 | 2019-10-09 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2022-01-30 | INPR | 2020-06-05 | COMP | Other | 111 | 54 | 99 | 1 |  |  | 328
14259 | 2019-02-19 | 2019-09-03 | 2020-01-06 | 2021-05-18 | COMP | 2022-10-24 | COMP | 2023-01-13 | COMP | 2022-11-10 | COMP | 2023-02-14 | COMP | Rule 16 | 138 | 85 | 363 | 55 | 0 | 22 | 1004
14339 | 2019-02-19 | 2019-09-05 | 2019-11-23 | 2019-11-23 | COMP | 2020-01-28 | COMP | 2021-12-14 | COMP | 2022-01-20 | COMP | 2022-11-15 | COMP | Rule 16 | 140 | 56 | 42 | 475 | 27 | 208 | 944
14638 | 2019-02-19 | 2019-09-21 | 2019-11-05 | 2019-11-05 | COMP | 2019-12-05 | COMP | 2020-03-26 | COMP | 2020-03-19 | COMP | 2020-06-19 | COMP | Rule 16 | 151 | 32 | 20 | 77 | 0 | 61 | 338
16870 | 2019-02-19 | 2020-01-21 | 2020-03-25 | 2020-03-25 | COMP | 2020-08-31 | COMP | 2020-10-16 | COMP | 2020-10-28 | COMP | 2020-11-17 | COMP | Rule 16 | 232 | 46 | 113 | 34 | 9 | 14 | 443
17176 | 2019-02-19 | 2020-02-03 | 2020-05-09 | 2020-05-09 | COMP | 2020-06-08 | COMP | 2020-07-09 | COMP | 2020-09-29 | COMP | 2020-10-21 | COMP | Other | 241 | 69 | 20 | 24 | 58 | 17 | 425
17654 | 2019-02-19 | 2020-02-24 | 2020-06-18 | 2020-07-28 | COMP | 2020-07-30 | COMP | 2020-06-25 | COMP | 2020-08-03 | COMP | 2020-09-25 | COMP | Rule 16 | 255 | 83 | 3 |  | 28 | 39 | 407
18251 | 2019-02-19 | 2020-03-17 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-08-06 | COMP | 2020-11-03 | COMP | Rule 15/16 | 271 | 44 | 27 | 1 | 33 | 63 | 434
9881 | 2019-02-20 | 2019-02-21 | 2019-04-17 | 2019-04-17 | COMP | 2019-04-30 | COMP | 2019-04-30 | COMP | 2019-05-20 | COMP | 2019-06-28 | COMP | Rule 16 | 2 | 40 | 10 | 1 | 15 | 29 | 92
9882 | 2019-02-20 | 2019-02-21 | 2019-04-17 | 2019-04-17 | COMP | 2019-06-06 | COMP | 2019-04-30 | COMP | 2019-06-05 | COMP | 2019-06-28 | COMP | Rule 16 | 2 | 40 | 36 |  | 26 | 18 | 92
9978 | 2019-02-20 | 2019-02-26 | 2019-03-27 | 2019-04-02 | COMP | 2019-04-15 | COMP | 2019-05-03 | COMP | 2019-12-29 | INPR | 2019-08-09 | COMP | Rule 16 | 5 | 22 | 10 | 15 |  |  | 121
9995 | 2019-02-20 | 2019-02-26 | 2019-04-06 | 2019-04-06 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-09-22 | INPR | 2019-06-08 | COMP | Rule 16 | 5 | 29 | 24 | 1 |  |  | 77
10177 | 2019-02-20 | 2019-03-05 | 2019-09-12 | 2019-12-02 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2019-11-18 | COMP | 2020-03-22 | COMP | Rule 15/16 | 10 | 135 | 16 | 1 | 0 | 61 | 273
10193 | 2019-02-20 | 2019-03-06 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-01 | COMP | 2019-09-22 | REQD | 2019-09-22 | REQD | 2019-06-12 | COMP | Rule 16 | 11 | 33 | 8 |  |  |  | 80
10222 | 2019-02-20 | 2019-03-06 | 2019-04-04 | 2019-04-04 | COMP | 2019-05-21 | COMP | 2019-05-29 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | Rule 16 | 11 | 22 | 34 | 6 | 6 | 6 | 80
10223 | 2019-02-20 | 2019-03-06 | 2019-04-13 | 2019-04-13 | COMP | 2019-04-29 | COMP | 2019-05-10 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | Rule 16 | 11 | 28 | 11 | 10 | 18 | 6 | 80
10403 | 2019-02-20 | 2019-03-14 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-09-28 | COMP | 2020-09-30 | COMP | Rule 16 | 17 | 154 | 27 | 1 | 211 | 3 | 409
10473 | 2019-02-20 | 2019-03-18 | 2019-05-24 | 2020-04-22 | COMP | 2020-05-14 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-24 | COMP | Rule 16 | 19 | 50 | 17 | 9 | 1 | 21 | 340
10680 | 2019-02-20 | 2019-03-25 | 2019-08-05 | 2019-08-05 | COMP | 2019-03-25 | NOTN | 2019-09-28 | COMP | 2019-10-15 | NOTN | 2020-01-07 | COMP | Other | 24 | 94 |  | 39 |  |  | 222
10739 | 2019-02-20 | 2019-03-28 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-09-04 | COMP | 2019-09-24 | COMP | Rule 16 | 27 | 81 | 15 | 1 | 18 | 15 | 152
10829 | 2019-02-20 | 2019-04-01 | 2019-06-29 | 2019-06-29 | COMP | 2019-08-07 | COMP | 2019-08-08 | COMP | 2019-08-15 | COMP | 2019-09-12 | COMP | Rule 16 | 29 | 64 | 27 | 2 | 6 | 20 | 144
10864 | 2019-02-20 | 2019-04-02 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-15 | COMP | 2019-09-18 | COMP | Rule 16 | 30 | 71 | 14 | 1 | 13 | 24 | 148
11017 | 2019-02-20 | 2019-04-09 | 2019-09-18 | 2019-09-18 | COMP | 2019-11-04 | COMP | 2020-03-09 | COMP | 2021-03-27 | INPR | 2020-03-07 | COMP | Rule 16 | 35 | 114 | 34 | 84 |  |  | 263
11147 | 2019-02-20 | 2019-04-15 | 2019-07-06 | 2019-11-07 | COMP | 2019-12-12 | COMP | 2019-12-31 | COMP | 2020-02-06 | COMP | 2020-02-25 | COMP | Rule 16 | 39 | 58 | 23 | 13 | 26 | 13 | 255
11205 | 2019-02-20 | 2019-04-17 | 2019-06-12 | 2019-06-12 | COMP | 2019-07-08 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-09-03 | COMP | Rule 16 | 41 | 40 | 18 | 15 | 1 | 27 | 137
11655 | 2019-02-20 | 2019-05-07 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-22 | COMP | 2019-11-04 | COMP | 2019-12-10 | COMP | 2020-02-26 | COMP | Rule 16 | 55 | 47 | 30 | 52 | 24 | 53 | 256
11682 | 2019-02-20 | 2019-05-07 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-11-27 | COMP | 2020-01-29 | COMP | Rule 16 | 55 | 75 | 12 | 1 | 58 | 41 | 237
11710 | 2019-02-20 | 2019-05-08 | 2019-07-18 | 2019-07-18 | COMP | 2019-07-31 | COMP | 2019-08-05 | COMP | 2019-08-14 | COMP | 2019-08-15 | COMP | Rule 16 | 56 | 50 | 10 | 4 | 8 | 2 | 125
11742 | 2019-02-20 | 2019-05-09 | 2019-09-04 | 2019-09-04 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-06-23 | COMP | 2020-07-06 | COMP | Rule 16 | 57 | 82 | 174 | 1 | 29 | 10 | 348
11763 | 2019-02-20 | 2019-05-10 | 2019-07-02 | 2019-07-03 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2019-09-10 | COMP | 2019-09-17 | COMP | Rule 16 | 58 | 37 | 31 | 1 | 18 | 6 | 147
11784 | 2019-02-20 | 2019-05-11 | 2019-06-26 | 2019-07-02 | COMP | 2019-07-11 | COMP | 2019-07-11 | COMP | 2019-12-29 | INPR | 2019-09-02 | COMP | Rule 16 | 58 | 32 | 7 | 1 |  |  | 136
11870 | 2019-02-20 | 2019-05-15 | 2019-09-04 | 2021-01-15 | COMP | 2021-01-27 | COMP | 2020-10-27 | COMP | 2020-11-09 | COMP | 2021-02-24 | COMP | Rule 16 | 61 | 78 | 8 |  | 10 | 71 | 507
11905 | 2019-02-20 | 2019-05-15 | 2019-06-27 | 2019-06-27 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-09-27 | COMP | 2019-10-21 | COMP | Rule 16 | 61 | 31 | 59 | 1 | 7 | 17 | 171
12165 | 2019-02-20 | 2019-05-24 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-17 | COMP | 2019-06-17 | COMP | 2019-08-18 | COMP | 2019-09-25 | COMP | Rule 16 | 68 | 9 | 8 | 1 | 44 | 27 | 153
12535 | 2019-02-20 | 2019-06-11 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-07-08 | COMP | 2019-07-31 | COMP | Rule 16 | 79 | 14 | 8 | 1 | 0 | 16 | 114
12593 | 2019-02-20 | 2019-06-14 | 2019-06-21 | 2019-06-21 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-09-06 | COMP | 2019-12-07 | COMP | Rule 16 | 82 | 6 | 17 | 1 | 38 | 63 | 202
12712 | 2019-02-20 | 2019-06-19 | 2019-11-08 | 2019-11-08 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-08-27 | COMP | 2020-09-25 | COMP | Rule 15/16 | 85 | 101 | 148 | 1 | 55 | 21 | 406
12730 | 2019-02-20 | 2019-06-20 | 2019-09-17 | 2019-09-17 | COMP | 2019-10-22 | COMP | 2019-11-13 | COMP | 2019-10-25 | COMP | 2019-12-30 | COMP | Rule 16 | 86 | 62 | 26 | 16 | 0 | 31 | 217
13299 | 2019-02-20 | 2019-07-19 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-10-17 | COMP | 2019-11-05 | COMP | Rule 16 | 106 | 13 | 18 | 1 | 35 | 14 | 182
13344 | 2019-02-20 | 2019-07-22 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2019-10-04 | COMP | 2019-10-22 | COMP | Rule 16 | 107 | 22 | 27 | 1 | 7 | 13 | 172
13622 | 2019-02-20 | 2019-08-02 | 2019-10-10 | 2019-10-10 | COMP | 2019-11-21 | COMP | 2020-02-25 | COMP | 2020-06-29 | COMP | 2020-08-12 | COMP | Rule 16 | 116 | 49 | 30 | 63 | 89 | 33 | 375
13710 | 2019-02-20 | 2019-08-06 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2020-03-01 | INPR | 2019-10-16 | COMP | Rule 16 | 118 | 14 | 15 | 1 |  |  | 168
14548 | 2019-02-20 | 2019-09-16 | 2020-01-29 | 2020-01-29 | COMP | 2020-04-01 | COMP | 2020-07-17 | COMP | 2020-10-23 | COMP | 2020-11-25 | COMP | Rule 16 | 146 | 92 | 45 | 77 | 70 | 23 | 448
15046 | 2019-02-20 | 2019-10-10 | 2019-11-15 | 2019-11-15 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-12-01 | COMP | 2020-12-30 | COMP | Rule 16 | 164 | 26 | 65 | 1 | 198 | 21 | 470
15909 | 2019-02-20 | 2019-11-27 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-07-03 | COMP | 2020-07-29 | COMP | Rule 16 | 197 | 36 | 9 | 1 | 108 | 19 | 365
15935 | 2019-02-20 | 2019-12-02 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-09 | COMP | 2020-04-09 | COMP | 2021-09-28 | COMP | 2022-01-18 | COMP | Rule 16 | 198 | 72 | 19 | 1 | 372 | 77 | 734
16863 | 2019-02-20 | 2020-01-21 | 2020-04-17 | 2021-02-22 | COMP | 2021-03-19 | COMP | 2021-07-03 | COMP | 2021-08-24 | COMP | 2021-10-13 | COMP | Rule 16 | 231 | 63 | 20 | 75 | 36 | 36 | 669
4112 | 2019-02-21 | 2019-02-21 | 2019-02-22 | 2019-02-22 | COMP | 2019-06-14 | COMP | 2019-06-19 | COMP | 2020-02-29 | INPR | 2019-10-23 | COMP | Rule 16 | 1 | 2 | 80 | 4 |  |  | 172
9899 | 2019-02-21 | 2019-02-21 | 2019-04-01 | 2019-04-01 | COMP | 2019-04-11 | COMP | 2019-08-26 | COMP | 2020-08-21 | COMP | 2020-08-28 | COMP | Rule 15/16 | 1 | 28 | 9 | 96 | 251 | 6 | 386
10434 | 2019-02-21 | 2019-03-15 | 2019-06-04 | 2019-06-04 | COMP | 2019-06-14 | COMP | 2019-06-14 | COMP | 2019-06-17 | COMP | 2019-09-05 | COMP | Rule 16 | 17 | 57 | 9 | 1 | 2 | 57 | 138
10574 | 2019-02-21 | 2019-03-20 | 2019-06-27 | 2019-07-25 | COMP | 2019-09-11 | COMP | 2019-09-26 | COMP | 2020-07-30 | COMP | 2020-09-01 | COMP | Rule 16 | 20 | 71 | 34 | 12 | 213 | 24 | 388
10728 | 2019-02-21 | 2019-03-28 | 2019-09-23 | 2019-09-23 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2021-02-01 | COMP | 2021-03-10 | COMP | Rule 15/16 | 26 | 125 | 44 | 1 | 298 | 27 | 516
10780 | 2019-02-21 | 2019-03-29 | 2019-09-14 | 2019-09-14 | COMP | 2020-03-26 | COMP | 2020-09-01 | COMP | 2020-08-25 | COMP | 2020-12-18 | COMP | Rule 15/16 | 27 | 118 | 132 | 113 | 0 | 75 | 462
10938 | 2019-02-21 | 2019-04-06 | 2019-07-18 | 2019-07-18 | COMP | 2019-10-17 | COMP | 2019-11-01 | COMP | 2019-10-23 | COMP | 2020-01-06 | COMP | Rule 16 | 32 | 72 | 65 | 12 | 0 | 42 | 220
10976 | 2019-02-21 | 2019-04-06 | 2019-07-19 | 2019-07-19 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-11-14 | COMP | Rule 16 | 32 | 73 | 6 | 1 | 1 | 78 | 187
11066 | 2019-02-21 | 2019-04-11 | 2019-04-26 | 2019-04-26 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-11-14 | COMP | 2019-12-19 | COMP | Rule 16 | 36 | 12 | 143 | 1 | 0 | 22 | 210
11202 | 2019-02-21 | 2019-04-17 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-06 | NOTN | 2019-07-09 | COMP | 2019-10-07 | COMP | 2019-12-26 | COMP | Other | 40 | 58 |  | 1 | 64 | 55 | 214
11206 | 2019-02-21 | 2019-04-17 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-20 | NOTN | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-07-17 | COMP | Other | 40 | 45 |  | 2 | 1 | 19 | 103
11213 | 2019-02-21 | 2019-04-17 | 2019-07-06 | 2019-07-06 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2020-01-27 | COMP | 2020-02-20 | COMP | Rule 16 | 40 | 56 | 17 | 1 | 123 | 18 | 251
11364 | 2019-02-21 | 2019-04-24 | 2019-06-17 | 2019-06-17 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-09-25 | COMP | 2019-10-22 | COMP | Rule 16 | 45 | 38 | 17 | 1 | 55 | 20 | 171
11873 | 2019-02-21 | 2019-05-15 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-02 | COMP | 2019-10-24 | COMP | 2019-10-17 | COMP | 2019-11-08 | COMP | Rule 15/16 | 60 | 88 | 11 | 17 | 0 | 12 | 184
11941 | 2019-02-21 | 2019-05-17 | 2019-08-29 | 2019-09-01 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-14 | COMP | Rule 15/16 | 62 | 73 | 192 | 1 | 1 | 27 | 353
11945 | 2019-02-21 | 2019-05-17 | 2019-10-07 | 2019-10-07 | COMP | 2019-11-04 | COMP | 2020-01-10 | COMP | 2020-03-04 | COMP | 2020-05-04 | COMP | Rule 16 | 62 | 99 | 21 | 45 | 37 | 44 | 303
12006 | 2019-02-21 | 2019-05-20 | 2019-07-01 | 2019-07-01 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2020-03-24 | COMP | 2020-06-12 | COMP | Rule 16 | 63 | 30 | 38 | 1 | 146 | 58 | 331
13290 | 2019-02-21 | 2019-07-19 | 2019-08-22 | 2019-08-22 | COMP | 2019-08-26 | NOTN | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-09-16 | COMP | Other | 105 | 25 |  | 3 | 1 | 15 | 145
13785 | 2019-02-21 | 2019-08-09 | 2019-10-12 | 2019-11-06 | COMP | 2019-11-21 | COMP | 2019-11-23 | COMP | 2019-12-10 | COMP | 2019-12-30 | COMP | Rule 16 | 120 | 45 | 11 | 2 | 10 | 14 | 216
14169 | 2019-02-21 | 2019-08-27 | 2020-01-13 | 2020-01-13 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-06 | COMP | 2020-03-16 | COMP | Rule 16 | 132 | 94 | 37 | 1 | 2 | 7 | 268
21408 | 2019-02-21 | 2020-08-05 | 2020-09-25 | 2020-09-25 | COMP | 2020-10-01 | NOTN | 2020-10-09 | COMP | 2020-10-01 | COMP | 2021-01-05 | COMP | Other | 369 | 37 |  | 11 | 0 | 58 | 472
10271 | 2019-02-22 | 2019-03-08 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-17 | COMP | 2019-09-12 | NOTN | 2019-09-12 | COMP | 2019-09-24 | COMP | Rule 16 | 11 | 50 | 22 |  |  |  | 150
10697 | 2019-02-22 | 2019-03-27 | 2019-06-05 | 2019-06-05 | COMP | 2019-06-12 | COMP | 2019-08-06 | COMP | 2019-09-17 | COMP | 2019-10-02 | COMP | Rule 16 | 24 | 50 | 6 | 39 | 30 | 12 | 156
10936 | 2019-02-22 | 2019-04-06 | 2019-09-01 | 2019-12-24 | COMP | 2020-02-06 | COMP | 2020-05-27 | COMP | 2020-06-26 | COMP | 2020-07-10 | COMP | Rule 16 | 31 | 103 | 30 | 78 | 23 | 11 | 350
10989 | 2019-02-22 | 2019-04-08 | 2019-06-04 | 2019-06-04 | COMP | 2019-06-24 | COMP | 2019-06-24 | COMP | 2019-07-15 | COMP | 2019-07-30 | COMP | Rule 16 | 32 | 41 | 15 | 1 | 15 | 12 | 111
11006 | 2019-02-22 | 2019-04-08 | 2019-05-21 | 2019-05-21 | COMP | 2019-05-22 | COMP | 2019-05-23 | COMP | 2019-06-25 | COMP | 2019-11-05 | COMP | Rule 16 | 32 | 32 | 2 | 2 | 23 | 94 | 180
11010 | 2019-02-22 | 2019-04-09 | 2019-05-29 | 2019-05-29 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-09-25 | COMP | 2019-10-07 | COMP | Rule 16 | 33 | 36 | 30 | 1 | 55 | 9 | 159
11064 | 2019-02-22 | 2019-04-10 | 2019-04-10 | 2019-04-10 | NOTN | 2019-04-10 | NOTN | 2019-04-10 | INPR | 2021-05-30 | REQD | 2019-04-19 | COMP | Unknown | 34 | [5 empty] | 41
11108 | 2019-02-22 | 2019-04-12 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-07 | COMP | 2019-05-07 | COMP | 2019-05-10 | COMP | 2019-05-23 | COMP | Rule 16 | 36 | 13 | 6 | 1 | 4 | 10 | 65
11217 | 2019-02-22 | 2019-04-17 | 2019-05-10 | 2019-05-10 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-10-21 | INPR | 2019-06-24 | COMP | Rule 16 | 39 | 18 | 10 | 1 |  |  | 86
11334 | 2019-02-22 | 2019-04-23 | 2019-08-19 | 2020-08-19 | COMP | 2020-09-01 | COMP | 2020-09-08 | COMP | 2020-07-07 | COMP | 2020-10-09 | COMP | Rule 15/16 | 43 | 83 | 10 | 5 | 0 | 24 | 414
11402 | 2019-02-22 | 2019-04-25 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-21 | COMP | 2019-10-02 | COMP | 2019-10-24 | COMP | 2020-01-23 | COMP | Rule 15/16 | 45 | 73 | 11 | 30 | 17 | 60 | 231
11512 | 2019-02-22 | 2019-04-30 | 2019-07-30 | 2019-07-30 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2020-08-04 | COMP | 2020-09-15 | COMP | Other | 48 | 64 | 65 | 1 | 193 | 30 | 396
11542 | 2019-02-22 | 2019-05-01 | 2019-09-15 | 2019-09-15 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2020-05-15 | COMP | 2020-06-30 | COMP | Other | 49 | 95 | 32 | 1 | 137 | 32 | 342
11576 | 2019-02-22 | 2019-05-02 | 2019-08-01 | 2019-11-04 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-01-23 | COMP | Other | 50 | 64 | 17 | 1 | 1 | 37 | 231
11577 | 2019-02-22 | 2019-05-02 | 2019-08-17 | 2019-08-17 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2020-03-31 | COMP | 2020-04-22 | COMP | Other | 50 | 75 | 51 | 1 | 104 | 17 | 294
11821 | 2019-02-22 | 2019-05-14 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-23 | COMP | 2020-07-27 | COMP | 2021-03-09 | COMP | 2021-04-06 | COMP | Rule 15/16 | 58 | 140 | 15 | 151 | 154 | 21 | 534
12259 | 2019-02-22 | 2019-05-29 | 2019-08-08 | 2019-08-08 | COMP | 2019-10-25 | COMP | 2020-05-23 | COMP | 2020-06-18 | COMP | 2020-08-12 | COMP | Rule 15/16 | 68 | 51 | 56 | 144 | 18 | 40 | 373
12647 | 2019-02-22 | 2019-06-17 | 2019-10-09 | 2019-10-09 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2021-07-01 | COMP | 2021-07-14 | COMP | Rule 16 | 81 | 81 | 34 | 1 | 402 | 9 | 603
12666 | 2019-02-22 | 2019-06-17 | 2019-10-14 | 2019-10-14 | COMP | 2020-04-02 | COMP | 2020-09-17 | COMP | 2021-01-20 | COMP | 2021-02-16 | COMP | Rule 15/16 | 81 | 84 | 117 | 119 | 84 | 19 | 499
12962 | 2019-02-22 | 2019-07-02 | 2019-08-28 | 2019-08-28 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-01-10 | COMP | 2020-05-04 | COMP | Rule 16 | 92 | 41 | 57 | 1 | 36 | 80 | 302
13009 | 2019-02-22 | 2019-07-05 | 2020-05-19 | 2020-11-10 | COMP | 2021-04-09 | COMP | 2021-04-09 | COMP | 2021-08-17 | COMP | 2021-10-07 | COMP | Rule 15/16 | 94 | 220 | 102 | 1 | 91 | 37 | 663
13192 | 2019-02-22 | 2019-07-15 | 2019-08-15 | 2019-08-15 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-02-27 | COMP | 2020-02-28 | COMP | Rule 16 | 100 | 24 | 129 | 1 | 5 | 2 | 256
13390 | 2019-02-22 | 2019-07-24 | 2019-12-16 | 2019-12-16 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-24 | COMP | 2020-06-09 | COMP | Other | 107 | 100 | 44 | 1 | 25 | 55 | 327
13943 | 2019-02-22 | 2019-08-17 | 2019-09-25 | 2019-09-25 | COMP | 2019-09-27 | NOTN | 2019-09-27 | COMP | 2019-10-11 | COMP | 2019-12-18 | COMP | Other | 124 | 27 |  | 3 | 11 | 46 | 208
14858 | 2019-02-22 | 2019-10-01 | 2020-03-10 | 2020-04-06 | COMP | 2020-12-14 | COMP | 2020-12-14 | COMP | 2021-01-11 | COMP | 2021-02-05 | COMP | Rule 16 | 155 | 109 | 176 | 1 | 19 | 19 | 493
14886 | 2019-02-22 | 2019-10-02 | 2020-02-26 | 2020-05-15 | COMP | 2020-08-03 | COMP | 2020-08-18 | COMP | 2020-08-04 | COMP | 2020-10-24 | COMP | Rule 16 | 156 | 99 | 56 | 12 | 0 | 48 | 424
16237 | 2019-02-22 | 2019-12-17 | 2020-01-30 | 2020-02-19 | COMP | 2020-07-23 | COMP | 2020-10-22 | COMP | 2021-05-05 | COMP | 2021-06-22 | COMP | Rule 15/16 | 207 | 30 | 111 | 65 | 133 | 34 | 588
9998 | 2019-02-23 | 2019-02-26 | 2019-04-23 | 2019-04-23 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-06-27 | COMP | 2019-08-30 | COMP | Rule 16 | 2 | 41 | 31 | 1 | 17 | 46 | 133
10013 | 2019-02-23 | 2019-02-27 | 2019-03-25 | 2019-03-25 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2019-09-19 | COMP | 2019-09-26 | COMP | Rule 16 | 3 | 19 | 51 | 1 | 76 | 6 | 151
10455 | 2019-02-23 | 2019-03-18 | 2019-04-10 | 2019-04-10 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2020-08-29 | INPR | 2019-07-12 | COMP | Rule 16 | 16 | 18 | 23 | 1 |  |  | 98
10748 | 2019-02-23 | 2019-03-28 | 2019-05-14 | 2019-08-02 | COMP | 2019-08-14 | COMP | 2019-06-12 | COMP | 2019-08-21 | COMP | 2019-09-19 | COMP | Rule 16 | 24 | 34 | 9 |  | 50 | 21 | 146
11828 | 2019-02-23 | 2019-05-14 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-02 | COMP | 2019-07-02 | COMP | 2019-10-10 | COMP | 2019-10-30 | COMP | Rule 16 | 57 | 32 | 4 | 1 | 71 | 15 | 175
12862 | 2019-02-23 | 2019-06-25 | 2019-09-16 | 2019-09-16 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-02-24 | COMP | 2020-03-03 | COMP | Rule 16 | 86 | 58 | 45 | 1 | 65 | 7 | 257
10141 | 2019-02-24 | 2019-03-05 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-05 | COMP | 2019-07-25 | COMP | 2019-09-19 | COMP | 2019-10-15 | COMP | Rule 16 | 7 | 52 | 15 | 36 | 40 | 19 | 164
10142 | 2019-02-24 | 2019-03-05 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-05 | COMP | 2019-08-21 | COMP | 2019-10-10 | COMP | 2020-02-06 | COMP | Rule 15/16 | 7 | 52 | 15 | 55 | 36 | 80 | 240
10717 | 2019-02-24 | 2019-03-28 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2021-05-25 | COMP | 2021-06-14 | COMP | Rule 16 | 24 | 66 | 11 | 1 | 470 | 14 | 581
11885 | 2019-02-24 | 2019-05-15 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-30 | COMP | 2019-10-09 | COMP | 2021-02-27 | INPR | 2019-11-25 | COMP | Rule 16 | 58 | 71 | 26 | 8 |  |  | 192
10266 | 2019-02-25 | 2019-03-07 | 2019-05-12 | 2019-10-12 | COMP | 2019-10-23 | COMP | 2019-10-31 | INPR | 2019-10-31 | COMP | 2019-11-19 | COMP | Rule 16 | 9 | 47 | 8 |  |  |  | 188
10416 | 2019-02-25 | 2019-03-14 | 2019-03-28 | 2019-03-28 | COMP | 2019-05-06 | COMP | 2019-05-06 | COMP | 2020-02-29 | INPR | 2019-09-28 | COMP | Rule 16 | 14 | 11 | 28 | 1 |  |  | 152
10492 | 2019-02-25 | 2019-03-18 | 2019-04-23 | 2019-04-23 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2019-06-25 | COMP | 2019-08-02 | COMP | Rule 16 | 16 | 27 | 37 | 1 | 9 | 28 | 113
10635 | 2019-02-25 | 2019-03-23 | 2019-04-30 | 2019-04-30 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-05-23 | COMP | 2019-07-03 | COMP | Rule 16 | 20 | 27 | 8 | 1 | 11 | 29 | 92
10704 | 2019-02-25 | 2019-03-27 | 2020-02-21 | 2020-11-06 | COMP | 2020-08-31 | COMP | 2020-11-18 | COMP | 2020-11-06 | COMP | 2020-12-19 | COMP | Rule 15/16 | 23 | 228 |  | 56 | 0 | 21 | 460
10744 | 2019-02-25 | 2019-03-28 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-08-19 | COMP | 2019-09-20 | COMP | Rule 16 | 24 | 66 | 31 | 1 | 6 | 24 | 147
10840 | 2019-02-25 | 2019-04-02 | 2019-07-16 | 2019-07-16 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-24 | COMP | 2019-10-07 | COMP | Rule 16 | 27 | 74 | 17 | 1 | 34 | 10 | 158
10959 | 2019-02-25 | 2019-04-06 | 2019-05-11 | 2019-05-11 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-10-22 | COMP | 2020-01-06 | COMP | Rule 16 | 30 | 25 | 46 | 1 | 69 | 50 | 218
11073 | 2019-02-25 | 2019-04-11 | 2019-07-01 | 2019-07-16 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-02 | COMP | 2019-08-27 | COMP | Rule 16 | 34 | 57 | 5 | 1 | 10 | 18 | 130
11263 | 2019-02-25 | 2019-04-19 | 2019-07-06 | 2019-07-06 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-11-06 | COMP | 2019-12-12 | COMP | Rule 16 | 40 | 54 | 28 | 1 | 60 | 24 | 203
11305 | 2019-02-25 | 2019-04-22 | 2019-07-16 | 2019-07-16 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-07-29 | COMP | 2019-08-20 | COMP | Rule 16 | 41 | 60 | 6 | 1 | 5 | 17 | 125
11331 | 2019-02-25 | 2019-04-24 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-10 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-11-18 | COMP | Rule 16 | 43 | 113 | 7 | 3 | 1 | 25 | 187
11427 | 2019-02-25 | 2019-04-27 | 2019-06-27 | 2019-07-15 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-11-22 | COMP | Rule 16 | 45 | 43 | 28 | 1 | 1 | 66 | 191
11643 | 2019-02-25 | 2019-05-07 | 2019-06-27 | 2019-06-27 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2022-01-30 | INPR | 2021-01-20 | COMP | Rule 16 | 52 | 37 | 28 | 1 |  |  | 480
11824 | 2019-02-25 | 2019-05-16 | 2019-08-15 | 2019-11-26 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2019-12-12 | COMP | 2020-01-15 | COMP | Rule 16 | 59 | 64 | 5 | 1 | 7 | 23 | 225
12152 | 2019-02-25 | 2019-05-24 | 2019-09-14 | 2019-09-14 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2019-10-23 | COMP | 2020-03-02 | COMP | Rule 16 | 65 | 78 | 79 | 1 | 0 | 36 | 256
12188 | 2019-02-25 | 2019-05-28 | 2019-10-07 | 2019-10-07 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2020-03-09 | COMP | 2020-03-25 | COMP | Rule 15/16 | 66 | 93 | 53 | 1 | 52 | 13 | 273
12240 | 2019-02-25 | 2019-05-30 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-25 | COMP | 2019-10-25 | COMP | 2019-11-06 | COMP | 2019-11-22 | COMP | Rule 16 | 68 | 24 | 17 | 66 | 9 | 12 | 191
12392 | 2019-02-25 | 2019-06-05 | 2019-10-23 | 2019-10-23 | COMP | 2020-01-31 | COMP | 2021-09-22 | COMP | 2022-07-13 | COMP | 2022-07-24 | COMP | Rule 15/16 | 72 | 99 | 67 | 416 | 203 | 8 | 860
12419 | 2019-02-25 | 2019-06-05 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-10-31 | COMP | 2019-11-25 | COMP | Rule 16 | 72 | 58 | 14 | 1 | 35 | 17 | 192
12470 | 2019-02-25 | 2019-06-07 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-19 | COMP | 2020-09-15 | COMP | 2020-07-27 | COMP | 2020-10-22 | COMP | Rule 15/16 | 74 | 98 | 18 | 208 | 0 | 28 | 422
12656 | 2019-02-25 | 2019-06-17 | 2019-10-25 | 2019-10-25 | COMP | 2020-02-05 | COMP | 2020-04-03 | COMP | 2019-12-05 | COMP | 2020-04-28 | COMP | Rule 16 | 80 | 93 | 68 | 42 | 0 | 18 | 297
12676 | 2019-02-25 | 2019-06-19 | 2019-11-01 | 2019-11-01 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-01-27 | COMP | 2020-02-13 | COMP | Rule 16 | 82 | 96 | 45 | 1 | 12 | 14 | 245
12784 | 2019-02-25 | 2019-06-21 | 2019-11-25 | 2021-03-22 | COMP | 2021-09-03 | COMP | 2021-09-17 | COMP | 2021-10-21 | COMP | 2021-10-29 | COMP | Rule 15/16 | 84 | 109 | 118 | 10 | 25 | 7 | 678
12920 | 2019-02-25 | 2019-06-28 | 2019-08-15 | 2019-08-15 | COMP | 2019-08-20 | COMP | 2019-10-21 | COMP | 2019-11-05 | COMP | 2019-12-17 | COMP | Rule 16 | 89 | 34 | 4 | 44 | 12 | 28 | 206
13034 | 2019-02-25 | 2019-07-08 | 2019-09-20 | 2019-09-20 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-09-23 | COMP | 2019-12-17 | COMP | Rule 16 | 94 | 54 | 9 | 1 | 0 | 52 | 206
14720 | 2019-02-25 | 2019-09-24 | 2019-11-12 | 2019-11-12 | COMP | 2020-01-03 | COMP | 2020-01-06 | COMP | 2020-01-09 | COMP | 2020-02-04 | COMP | Rule 16 | 149 | 35 | 35 | 2 | 4 | 18 | 238
15038 | 2019-02-25 | 2019-10-09 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-02-20 | COMP | 2020-02-26 | COMP | Rule 16 | 160 | 50 | 10 | 1 | 32 | 5 | 253
15683 | 2019-02-25 | 2019-11-15 | 2020-03-19 | 2020-03-19 | COMP | 2020-03-24 | COMP | 2020-03-26 | COMP | 2020-03-23 | COMP | 2020-07-07 | COMP | Rule 16 | 186 | 84 | 4 | 3 | 0 | 73 | 346
16050 | 2019-02-25 | 2019-12-07 | 2020-01-23 | 2020-01-23 | COMP | 2020-02-03 | COMP | 2020-04-13 | COMP | 2020-05-14 | COMP | 2020-08-08 | COMP | Rule 16 | 199 | 31 | 8 | 50 | 24 | 61 | 369
16306 | 2019-02-25 | 2019-12-20 | 2020-02-07 | 2020-02-07 | COMP | 2020-03-13 | COMP | 2020-05-22 | COMP | 2020-07-13 | COMP | 2020-06-29 | COMP | Rule 16 | 209 | 33 | 25 | 51 | 36 |  | 340
16604 | 2019-02-25 | 2020-01-09 | 2020-02-07 | 2020-02-18 | COMP | 2020-03-10 | COMP | 2020-05-22 | COMP | 2020-07-13 | COMP | 2020-06-29 | COMP | Rule 16 | 221 | 21 | 16 | 54 | 36 |  | 340
16642 | 2019-02-25 | 2020-01-09 | 2020-01-28 | 2020-07-07 | COMP | 2020-09-09 | NOTN | 2021-06-02 | COMP | 2023-12-03 | INPR | 2021-07-16 | COMP | Other | 221 | 13 |  | 228 |  |  | 604
17858 | 2019-02-25 | 2020-03-02 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2022-01-30 | INPR | 2020-07-15 | COMP | Rule 16 | 256 | 79 | 3 | 1 |  |  | 352
18466 | 2019-02-25 | 2020-03-25 | 2020-12-03 | 2020-12-10 | COMP | 2021-01-26 | COMP | 2021-04-08 | COMP | 2021-09-08 | COMP | 2021-10-02 | COMP | Rule 16 | 273 | 177 | 31 | 52 | 107 | 18 | 658
21450 | 2019-02-25 | 2020-08-06 | 2021-02-17 | 2021-05-21 | COMP | 2021-07-26 | COMP | 2021-10-08 | COMP |  | INPR | 2022-02-10 | COMP | Rule 15/16 | 368 | 132 | 45 | 54 |  |  | 748
21451 | 2019-02-25 | 2020-08-06 | 2020-10-23 | 2020-12-22 | COMP | 2021-07-26 | COMP | 2021-10-08 | COMP | 2021-10-14 | COMP | 2022-01-21 | COMP | Rule 15/16 | 368 | 56 | 149 | 54 | 5 | 68 | 734
34033 | 2019-02-25 | 2022-01-28 | 2022-02-02 | 2022-02-02 | COMP | 2022-02-03 | NOTN | 2022-02-03 | COMP | 2022-02-03 | COMP | 2022-03-16 | COMP | Other | 739 | 4 |  | 2 | 1 | 29 | 771
4117 | 2019-02-26 | 2019-03-04 | 2019-03-12 | 2019-03-12 | COMP | 2019-03-19 | COMP | 2019-07-01 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | Rule 16 | 5 | 7 | 6 | 74 | 0 |  | 83
10032 | 2019-02-26 | 2019-02-27 | 2019-09-20 | 2019-09-20 | COMP | 2019-10-22 | COMP | 2019-12-31 | COMP | 2019-12-16 | COMP | 2020-01-22 | COMP | Rule 15/16 | 2 | 145 | 23 | 47 | 0 | 15 | 228
10408 | 2019-02-26 | 2019-03-14 | 2019-06-05 | 2019-06-05 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2020-02-29 | INPR | 2019-10-21 | COMP | Rule 15/16 | 13 | 59 | 37 | 1 |  |  | 167
10420 | 2019-02-26 | 2019-03-15 | 2019-10-12 | 2019-10-12 | COMP | 2020-01-23 | COMP | 2019-12-02 | COMP | 2020-03-13 | COMP | 2020-04-20 | COMP | Rule 15/16 | 14 | 148 | 68 |  | 71 | 27 | 290
10649 | 2019-02-26 | 2019-03-25 | 2019-04-13 | 2019-04-13 | COMP | 2019-05-06 | COMP | 2019-06-06 | COMP | 2019-05-31 | COMP | 2019-06-27 | COMP | Rule 16 | 20 | 15 | 16 | 23 | 0 | 16 | 87
10772 | 2019-02-26 | 2019-03-29 | 2019-06-29 | 2020-07-17 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP |  | INPR | 2021-08-16 | COMP | Rule 15/16 | 24 | 65 | 62 | 1 |  |  | 624
10773 | 2019-02-26 | 2019-03-29 | 2019-07-10 | 2020-07-17 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP |  | INPR | 2021-12-06 | COMP | Rule 16 | 24 | 72 | 62 | 1 |  |  | 700
10774 | 2019-02-26 | 2019-03-29 | 2019-06-29 | 2020-07-17 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2022-08-21 | INPR | 2021-08-16 | COMP | Rule 16 | 24 | 65 | 62 | 1 |  |  | 624
10883 | 2019-02-26 | 2019-04-02 | 2019-05-16 | 2019-05-16 | COMP | 2019-07-02 | COMP | 2019-07-03 | COMP | 2020-05-12 | COMP | 2020-06-08 | COMP | Rule 16 | 26 | 33 | 33 | 2 | 216 | 19 | 324
10964 | 2019-02-26 | 2019-04-06 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-09-11 | COMP | 2019-10-21 | COMP | Rule 16 | 29 | 67 | 5 | 1 | 40 | 29 | 167
11103 | 2019-02-26 | 2019-04-12 | 2019-06-29 | 2019-07-09 | COMP | 2019-08-07 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-09-02 | COMP | Rule 16 | 34 | 55 | 22 |  | 1 | 19 | 132
11168 | 2019-02-26 | 2019-04-16 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-25 | COMP | 2019-06-25 | COMP | 2019-06-26 | COMP | 2019-07-03 | COMP | Rule 16 | 36 | 46 | 5 | 1 | 2 | 6 | 91
11406 | 2019-02-26 | 2019-04-25 | 2019-09-10 | 2019-09-10 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-08-11 | COMP | 2020-10-12 | COMP | Rule 15/16 | 43 | 96 | 212 | 1 | 22 | 44 | 413
11460 | 2019-02-26 | 2019-04-29 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-07-25 | COMP | 2019-08-26 | COMP | Rule 15/16 | 45 | 56 | 8 | 1 | 0 | 22 | 128
11500 | 2019-02-26 | 2019-04-30 | 2019-08-20 | 2019-08-20 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-11 | COMP | 2020-03-09 | COMP | Rule 16 | 46 | 79 | 95 | 1 | 25 | 19 | 260
11516 | 2019-02-26 | 2019-04-30 | 2019-07-26 | 2019-07-26 | COMP | 2020-03-03 | COMP | 2020-07-15 | COMP | 2020-06-27 | COMP | 2020-08-07 | COMP | Rule 15/16 | 46 | 62 | 150 | 96 | 0 | 18 | 368
11594 | 2019-02-26 | 2019-05-03 | 2019-08-16 | 2020-01-10 | COMP | 2020-02-20 | COMP | 2020-08-21 | COMP | 2021-02-25 | COMP | 2021-04-02 | COMP | Rule 16 | 49 | 74 | 28 | 131 | 127 | 27 | 530
11652 | 2019-02-26 | 2019-05-07 | 2019-07-16 | 2019-07-16 | COMP | 2019-07-25 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-12-20 | COMP | Rule 16 | 51 | 49 | 8 | 70 | 1 | 34 | 208
11919 | 2019-02-26 | 2019-05-16 | 2019-08-27 | 2019-08-27 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-12-23 | COMP | Rule 16 | 58 | 72 | 55 | 1 | 1 | 27 | 209
11942 | 2019-02-26 | 2019-05-17 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-21 | COMP | 2020-02-15 | COMP | 2020-01-27 | COMP | 2020-02-28 | COMP | Rule 16 | 59 | 89 | 21 | 79 | 0 | 9 | 254
12116 | 2019-02-26 | 2019-05-23 | 2019-06-27 | 2019-06-27 | COMP | 2019-08-19 | COMP | 2019-12-03 | COMP | 2020-01-21 | COMP | 2020-02-13 | COMP | Rule 16 | 63 | 25 | 37 | 73 | 33 | 18 | 244
12151 | 2019-02-26 | 2019-05-24 | 2019-08-12 | 2019-08-12 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-01-25 | COMP | 2020-02-21 | COMP | Rule 16 | 64 | 55 | 51 | 1 | 63 | 19 | 249
12161 | 2019-02-26 | 2019-05-24 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2019-08-26 | COMP | 2019-10-18 | COMP | Rule 16 | 64 | 32 | 29 | 1 | 6 | 39 | 166
12449 | 2019-02-26 | 2019-06-06 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-30 | COMP | 2019-09-05 | COMP | Rule 16 | 72 | 11 | 12 | 1 | 17 | 27 | 135
12591 | 2019-02-26 | 2019-06-14 | 2019-08-05 | 2019-08-05 | COMP | 2019-12-30 | COMP | 2020-05-01 | COMP | 2021-09-28 | COMP | 2021-10-22 | COMP | Rule 16 | 78 | 36 | 101 | 87 | 356 | 19 | 672
12605 | 2019-02-26 | 2019-06-14 | 2019-07-31 | 2019-07-31 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-09-30 | COMP | 2019-11-18 | COMP | Rule 16 | 78 | 33 | 8 | 1 | 36 | 35 | 186
12638 | 2019-02-26 | 2019-06-18 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-13 | COMP | 2020-06-13 | COMP | 2020-12-11 | COMP | 2020-12-15 | COMP | Rule 15/16 | 80 | 233 | 17 | 0 | 126 | 3 | 456
12779 | 2019-02-26 | 2019-06-21 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-04 | COMP | 2020-03-06 | COMP | 2021-05-10 | COMP | 2021-09-17 | COMP | Rule 16 | 83 | 141 | 15 | 23 | 298 | 92 | 647
13120 | 2019-02-26 | 2019-07-11 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-13 | COMP | 2019-12-30 | COMP | 2020-01-07 | COMP | 2020-02-18 | COMP | Rule 16 | 96 | 74 | 15 | 31 | 6 | 29 | 246
13448 | 2019-02-26 | 2019-07-26 | 2019-08-29 | 2019-08-29 | COMP | 2019-09-19 | COMP | 2019-11-25 | COMP | 2020-06-02 | COMP | 2020-07-01 | COMP | Rule 16 | 107 | 25 | 15 | 47 | 130 | 22 | 341
13554 | 2019-02-26 | 2019-07-30 | 2019-10-18 | 2019-11-06 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2019-12-10 | COMP | 2019-12-26 | COMP | Rule 16 | 109 | 58 | 11 | 1 | 12 | 12 | 211
13665 | 2019-02-26 | 2019-08-05 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-06 | COMP | 2020-02-13 | COMP | 2020-01-31 | COMP | 2020-06-09 | COMP | Rule 15/16 | 113 | 76 | 11 | 47 | 0 | 82 | 325
13669 | 2019-02-26 | 2019-08-05 | 2019-10-02 | 2019-10-02 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-12-16 | COMP | 2019-12-30 | COMP | Rule 16 | 113 | 42 | 30 | 1 | 22 | 10 | 213
13718 | 2019-02-26 | 2019-08-06 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-20 | COMP | 2019-12-03 | COMP | 2020-12-07 | COMP | 2021-01-07 | COMP | Rule 15/16 | 114 | 53 | 22 | 8 | 256 | 22 | 471
13902 | 2019-02-26 | 2019-08-15 | 2020-01-30 | 2020-01-30 | COMP | 2020-05-12 | COMP | 2020-07-15 | COMP | 2020-06-10 | COMP | 2020-08-12 | COMP | Rule 16 | 121 | 114 | 73 | 46 | 0 | 21 | 371
14187 | 2019-02-26 | 2019-08-28 | 2019-10-18 | 2019-10-18 | COMP | 2020-02-04 | COMP | 2020-03-02 | COMP | 2020-08-19 | COMP | 2020-09-28 | COMP | Rule 16 | 130 | 37 | 72 | 19 | 122 | 28 | 403
14546 | 2019-02-26 | 2019-09-16 | 2020-02-21 | 2020-02-21 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-09-29 | COMP | 2020-10-07 | COMP | Rule 16 | 142 | 108 | 90 | 1 | 67 | 7 | 410
14600 | 2019-02-26 | 2019-09-17 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-19 | COMP | 2019-12-03 | COMP | 2020-10-14 | COMP | 2020-11-03 | COMP | Rule 16 | 143 | 32 | 14 | 9 | 221 | 15 | 429
14728 | 2019-02-26 | 2019-09-25 | 2019-12-05 | 2020-02-18 | COMP | 2020-03-20 | COMP | 2019-12-23 | COMP | 2020-01-02 | COMP | 2020-11-19 | COMP | Rule 16 | 149 | 49 | 24 |  | 7 | 226 | 440
15257 | 2019-02-26 | 2019-10-23 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-31 | COMP | 2020-07-24 | COMP | 2020-07-28 | COMP | 2020-09-29 | COMP | Rule 16 | 169 | 69 | 40 | 83 | 3 | 45 | 404
16830 | 2019-02-26 | 2020-01-17 | 2020-03-23 | 2020-03-23 | COMP | 2020-06-15 | COMP | 2020-07-21 | COMP | 2022-09-28 | COMP | 2022-11-29 | COMP | Other | 226 | 45 | 60 | 27 | 552 | 42 | 947
25812 | 2019-02-26 | 2021-02-25 | 2021-06-09 | 2021-06-09 | COMP | 2021-07-20 | COMP | 2021-09-17 | COMP | 2022-01-18 | COMP | 2022-01-19 | COMP | Rule 15/16 | 504 | 74 | 29 | 43 | 84 | 2 | 731
28137 | 2019-02-26 | 2021-05-20 | 2021-07-20 | 2021-08-06 | COMP | 2021-08-31 | COMP | 2022-03-25 | COMP | 2022-03-10 | COMP | 2022-04-25 | COMP | Rule 16 | 564 | 42 | 18 | 143 | 0 | 22 | 798
10150 | 2019-02-27 | 2019-03-05 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-19 | COMP | 2020-03-03 | COMP | 2020-06-15 | COMP | 2020-06-29 | COMP | Rule 16 | 5 | 95 | 24 | 134 | 74 | 11 | 338
10322 | 2019-02-27 | 2019-03-11 | 2019-04-11 | 2019-04-11 | COMP | 2019-06-05 | COMP | 2019-07-03 | COMP | 2019-07-09 | COMP | 2019-07-19 | COMP | Rule 16 | 9 | 24 | 39 | 21 | 4 | 9 | 101
10345 | 2019-02-27 | 2019-03-12 | 2019-09-06 | 2019-09-06 | COMP | 2019-11-25 | COMP | 2020-01-07 | COMP | 2020-01-08 | COMP | 2020-02-21 | COMP | Rule 15/16 | 10 | 126 | 56 | 28 | 2 | 31 | 248
10794 | 2019-02-27 | 2019-03-30 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-15 | NOTN | 2019-09-04 | COMP | 2019-07-23 | COMP | 2019-10-07 | COMP | Other | 23 | 73 |  | 38 | 0 | 24 | 156
11145 | 2019-02-27 | 2019-04-15 | 2019-08-21 | 2020-03-30 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2021-06-01 | COMP | 2021-08-19 | COMP | Rule 16 | 34 | 91 | 158 | 1 | 140 | 57 | 626
11230 | 2019-02-27 | 2019-04-17 | 2019-04-29 | 2019-04-29 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2019-06-06 | COMP | 2019-06-11 | COMP | Rule 16 | 36 | 9 | 11 | 1 | 18 | 4 | 74
11303 | 2019-02-27 | 2019-04-22 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-07-09 | COMP | 2019-08-12 | COMP | Rule 16 | 39 | 39 | 18 | 1 | 0 | 24 | 117
11363 | 2019-02-27 | 2019-04-24 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-04 | COMP | 2019-06-04 | COMP | 2020-05-11 | COMP | 2020-06-15 | COMP | Rule 16 | 41 | 23 | 7 | 1 | 236 | 25 | 328
11388 | 2019-02-27 | 2019-04-24 | 2019-06-17 | 2019-06-17 | COMP | 2019-07-10 | COMP | 2019-07-12 | COMP | 2019-09-12 | COMP | 2019-10-15 | COMP | Rule 16 | 41 | 38 | 17 | 3 | 44 | 24 | 162
11465 | 2019-02-27 | 2019-04-29 | 2019-08-09 | 2019-11-22 | COMP | 2020-01-02 | COMP | 2020-01-23 | COMP | 2020-07-06 | COMP | 2020-07-22 | COMP | Rule 16 | 44 | 73 | 26 | 15 | 116 | 13 | 355
11709 | 2019-02-27 | 2019-05-08 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-21 | COMP | 2019-12-06 | COMP | 2020-02-11 | COMP | 2020-03-13 | COMP | Rule 16 | 51 | 62 | 13 | 74 | 45 | 23 | 263
11718 | 2019-02-27 | 2019-05-08 | 2019-09-05 | 2019-09-05 | COMP | 2020-01-27 | COMP | 2020-03-05 | COMP | 2020-06-03 | COMP | 2020-11-14 | COMP | Rule 16 | 51 | 84 | 97 | 28 | 64 | 116 | 435
12087 | 2019-02-27 | 2019-05-23 | 2019-07-31 | 2019-07-31 | COMP | 2019-10-02 | COMP | 2020-02-04 | COMP | 2021-03-27 | INPR | 2020-03-03 | COMP | Rule 16 | 62 | 48 | 45 | 84 |  |  | 255
12102 | 2019-02-27 | 2019-05-23 | 2019-07-18 | 2019-07-18 | COMP | 2019-07-22 | COMP | 2019-07-23 | COMP | 2019-07-23 | COMP | 2019-09-13 | COMP | Rule 16 | 62 | 39 | 3 | 2 | 1 | 38 | 140
12119 | 2019-02-27 | 2019-05-23 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-04 | COMP | 2019-10-08 | COMP | 2020-03-03 | COMP | 2020-09-03 | COMP | Rule 16 | 62 | 62 | 11 | 25 | 99 | 132 | 386
12144 | 2019-02-27 | 2019-05-24 | 2019-07-31 | 2019-07-31 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-11-21 | COMP | 2020-06-04 | COMP | Rule 16 | 63 | 47 | 43 | 1 | 38 | 134 | 321
12145 | 2019-02-27 | 2019-05-24 | 2019-07-31 | 2019-07-31 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2020-01-06 | COMP | 2020-06-04 | COMP | Rule 16 | 63 | 47 | 43 | 1 | 66 | 106 | 321
12454 | 2019-02-27 | 2019-06-08 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-19 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-08-22 | COMP | Rule 16 | 72 | 22 | 8 | 2 | 1 | 24 | 125
12846 | 2019-02-27 | 2019-06-25 | 2019-12-07 | 2019-12-07 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2022-07-16 | INPR | 2020-04-30 | COMP | Rule 15/16 | 84 | 114 | 63 | 1 |  |  | 297
12856 | 2019-02-27 | 2019-06-25 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-10-21 | COMP | 2019-12-17 | COMP | Rule 16 | 84 | 64 | 18 | 1 | 3 | 39 | 204
13184 | 2019-02-27 | 2019-07-16 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-17 | COMP | 2019-12-18 | COMP | 2020-01-14 | COMP | 2020-02-21 | COMP | Rule 15/16 | 98 | 74 | 34 | 2 | 18 | 27 | 248
13863 | 2019-02-27 | 2019-08-14 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-02-14 | COMP | 2020-02-20 | COMP | Rule 16 | 119 | 71 | 6 | 1 | 51 | 4 | 247
14146 | 2019-02-27 | 2019-08-27 | 2019-11-25 | 2019-11-25 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2020-01-07 | COMP | 2020-02-12 | COMP | Rule 16 | 128 | 63 | 9 | 1 | 20 | 26 | 242
14437 | 2019-02-27 | 2019-09-09 | 2019-10-20 | 2019-10-20 | COMP | 2019-10-29 | COMP | 2019-12-09 | COMP | 2019-12-20 | COMP | 2020-03-05 | COMP | Rule 16 | 136 | 30 | 7 | 27 | 10 | 51 | 257
14509 | 2019-02-27 | 2019-09-13 | 2019-12-23 | 2019-12-23 | COMP | 2020-01-14 | COMP | 2020-01-14 | COMP | 2020-01-15 | COMP | 2020-02-18 | COMP | Rule 16 | 140 | 69 | 15 | 1 | 2 | 23 | 245
15378 | 2019-02-27 | 2019-10-29 | 2019-12-20 | 2019-12-20 | COMP | 2019-12-27 | COMP | 2019-12-31 | COMP | 2020-02-03 | COMP | 2020-02-25 | COMP | Rule 16 | 172 | 36 | 5 | 3 | 23 | 16 | 250
15433 | 2019-02-27 | 2019-10-31 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-24 | COMP | 2020-08-25 | COMP | 2020-09-15 | COMP | 2020-10-15 | COMP | Rule 15/16 | 174 | 194 | 12 | 2 | 15 | 23 | 415
15445 | 2019-02-27 | 2019-11-02 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2020-06-16 | COMP | 2020-10-19 | COMP | Rule 16 | 175 | 131 | 23 | 1 | 2 | 89 | 417
16592 | 2019-02-27 | 2020-01-08 | 2020-08-17 | 2020-08-17 | COMP | 2020-09-24 | COMP | 2020-09-24 | COMP |  | INPR | 2020-10-29 | COMP | Rule 15/16 | 218 | 156 | 28 | 1 |  |  | 425
16676 | 2019-02-27 | 2020-01-11 | 2020-04-21 | 2020-04-21 | COMP | 2020-04-27 | COMP | 2020-08-03 | COMP | 2020-09-19 | COMP | 2020-10-22 | COMP | Rule 16 | 220 | 70 | 5 | 70 | 34 | 24 | 420
17945 | 2019-02-27 | 2020-03-05 | 2020-03-20 | 2020-03-20 | COMP | 2020-03-26 | COMP | 2020-06-03 | COMP | 2020-06-16 | COMP | 2020-06-30 | COMP | Rule 16 | 257 | 12 | 5 | 49 | 10 | 11 | 339
18954 | 2019-02-27 | 2020-04-14 | 2020-07-17 | 2020-07-17 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2020-09-25 | COMP | 2020-11-03 | COMP | Rule 16 | 285 | 68 | 23 | 1 | 28 | 28 | 428
10083 | 2019-02-28 | 2019-03-01 | 2019-03-05 | 2019-03-05 | COMP | 2019-06-20 | COMP | 2019-06-20 | COMP | 2019-03-06 | COMP | 2019-08-05 | COMP | Rule 16 | 2 | 3 | 77 | 1 | 0 | 32 | 111
10573 | 2019-02-28 | 2019-03-20 | 2019-04-03 | 2019-04-03 | COMP | 2019-04-23 | COMP | 2019-06-06 | COMP | 2019-06-19 | COMP | 2019-08-14 | COMP | Rule 16 | 15 | 11 | 15 | 32 | 10 | 40 | 118
10584 | 2019-02-28 | 2019-03-21 | 2019-04-04 | 2019-04-04 | COMP | 2019-04-16 | COMP | 2019-04-17 | COMP | 2019-04-10 | COMP | 2019-04-16 | COMP | Rule 16 | 16 | 11 | 9 | 2 | 0 |  | 34
10644 | 2019-02-28 | 2019-03-23 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-30 | COMP | 2019-09-23 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | Rule 16 | 17 | 36 | 13 | 81 | 0 |  | 119
10934 | 2019-02-28 | 2019-04-04 | 2019-04-23 | 2019-04-23 | COMP | 2019-05-02 | COMP | 2019-05-02 | COMP | 2019-10-04 | COMP | 2019-10-23 | COMP | Rule 16 | 26 | 14 | 8 | 1 | 109 | 14 | 167
11141 | 2019-02-28 | 2019-04-15 | 2019-05-16 | 2019-05-16 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-05-31 | COMP | Rule 16 | 33 | 24 | 10 | 1 | 1 | 2 | 66
11144 | 2019-02-28 | 2019-04-15 | 2019-08-10 | 2019-08-10 | COMP | 2019-09-11 | COMP | 2019-09-11 | COMP | 2019-09-17 | COMP | 2019-11-12 | COMP | Rule 16 | 33 | 83 | 22 | 1 | 5 | 40 | 180
11463 | 2019-02-28 | 2019-04-29 | 2019-08-28 | 2019-08-28 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2021-09-04 | COMP | 2021-10-06 | COMP | Rule 15/16 | 43 | 86 | 88 | 1 | 422 | 22 | 658
11715 | 2019-02-28 | 2019-05-09 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-20 | COMP | 2019-09-04 | COMP | 2019-09-05 | COMP | 2019-10-17 | COMP | Rule 16 | 51 | 51 | 22 | 11 | 2 | 31 | 163
12373 | 2019-02-28 | 2019-06-04 | 2019-08-14 | 2019-08-14 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-10-22 | COMP | 2021-03-24 | COMP | Rule 15/16 | 68 | 51 | 48 | 1 | 255 | 103 | 521
12430 | 2019-02-28 | 2019-06-05 | 2019-09-01 | 2019-09-01 | COMP | 2019-11-15 | COMP | 2019-11-15 | COMP | 2020-04-28 | COMP | 2020-06-12 | COMP | Rule 16 | 69 | 62 | 53 | 1 | 112 | 33 | 326
12477 | 2019-02-28 | 2019-06-11 | 2019-06-24 | 2019-06-24 | COMP | 2019-08-13 | COMP | 2019-08-15 | COMP | 2019-08-27 | COMP | 2019-09-05 | COMP | Rule 16 | 73 | 10 | 36 | 3 | 9 | 7 | 133
12480 | 2019-02-28 | 2019-06-11 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-12 | COMP | 2019-07-24 | COMP | 2019-07-12 | COMP | 2019-08-01 | COMP | Rule 16 | 73 | 14 | 10 | 9 | 0 | 7 | 109
12559 | 2019-02-28 | 2019-06-13 | 2019-09-25 | 2019-09-25 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-01-28 | COMP | 2020-02-23 | COMP | Rule 16 | 75 | 73 | 83 | 1 | 2 | 18 | 247
12606 | 2019-02-28 | 2019-06-14 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2021-03-27 | INPR | 2020-02-27 | COMP | Rule 16 | 76 | 21 | 38 | 1 |  |  | 251
12793 | 2019-02-28 | 2019-06-24 | 2019-10-12 | 2020-03-24 | COMP | 2020-04-09 | COMP | 2020-04-09 | COMP | 2020-05-12 | COMP | 2020-06-12 | COMP | Rule 16 | 82 | 78 | 13 | 1 | 24 | 23 | 326
12947 | 2019-02-28 | 2019-07-01 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-04 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-12-20 | COMP | Rule 16 | 87 | 51 | 18 | 20 | 1 | 34 | 206
13036 | 2019-02-28 | 2019-07-09 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | 2019-10-05 | COMP | 2019-11-13 | COMP | Rule 15/16 | 92 | 51 | 13 | 1 | 1 | 27 | 181
13830 | 2019-02-28 | 2019-08-12 | 2020-02-21 | 2020-02-21 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2022-07-16 | INPR | 2020-10-21 | COMP | Rule 16 | 116 | 132 | 93 | 1 |  |  | 418
13834 | 2019-02-28 | 2019-08-12 | 2020-02-21 | 2020-02-21 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2022-07-16 | INPR | 2020-10-31 | COMP | Rule 16 | 116 | 132 | 41 | 1 |  |  | 425
14979 | 2019-02-28 | 2019-10-07 | 2020-04-10 | 2020-06-01 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-11-10 | COMP | 2021-01-07 | COMP | Rule 16 | 155 | 128 | 47 | 1 | 70 | 38 | 469
14999 | 2019-02-28 | 2019-10-08 | 2020-03-02 | 2020-09-22 | COMP | 2020-11-17 | COMP | 2020-03-17 | COMP | 2020-10-13 | COMP | 2021-02-10 | COMP | Rule 16 | 156 | 98 | 40 |  | 149 | 81 | 492
15064 | 2019-02-28 | 2019-10-10 | 2020-03-30 | 2020-03-30 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-05-15 | COMP | 2020-07-17 | COMP | Rule 16 | 158 | 116 | 19 | 1 | 17 | 45 | 351
15704 | 2019-02-28 | 2019-11-18 | 2020-05-01 | 2020-06-03 | COMP | 2020-07-29 | COMP | 2020-06-24 | COMP | 2020-07-24 | COMP | 2020-08-31 | COMP | Rule 15/16 | 184 | 114 | 41 |  | 23 | 27 | 382
15739 | 2019-02-28 | 2019-11-19 | 2020-12-03 | 2020-12-03 | COMP | 2020-12-14 | COMP | 2020-12-14 | COMP | 2022-10-05 | COMP | 2022-12-07 | COMP | Rule 16 | 185 | 262 | 8 | 1 | 457 | 43 | 951
15740 | 2019-02-28 | 2019-11-19 | 2020-08-31 | 2020-08-31 | COMP | 2020-12-02 | COMP | 2021-02-02 | COMP | 2022-10-05 | COMP | 2022-12-05 | COMP | Rule 16 | 185 | 198 | 64 | 42 | 424 | 41 | 949
15748 | 2019-02-28 | 2019-11-19 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-18 | COMP | 2020-06-17 | COMP | 2020-08-18 | COMP | 2020-10-12 | COMP | Rule 16 | 185 | 74 | 51 | 22 | 45 | 39 | 411
15816 | 2019-02-28 | 2019-11-21 | 2020-03-13 | 2020-03-13 | COMP | 2020-04-16 | COMP | 2020-07-24 | INPR | 2020-04-27 | COMP | 2020-07-10 | COMP | Rule 16 | 187 | 76 | 25 |  |  |  | 346
15844 | 2019-02-28 | 2019-11-24 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-21 | COMP | 2021-05-10 | COMP | 2021-05-25 | COMP | 2021-07-31 | COMP | Rule 16 | 188 | 95 | 7 | 266 | 12 | 47 | 611
15904 | 2019-02-28 | 2019-11-26 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-01 | COMP | 2020-09-28 | COMP |  | INPR | 2021-01-14 | COMP | Rule 16 | 190 | 79 | 8 | 127 |  |  | 474
16104 | 2019-02-28 | 2019-12-09 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-06-16 | COMP | 2020-08-07 | COMP | Rule 16 | 197 | 86 | 5 | 1 | 43 | 39 | 366
16703 | 2019-02-28 | 2020-01-13 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-06-11 | COMP | 2020-08-12 | COMP | Rule 16 | 220 | 46 | 27 | 1 | 35 | 45 | 369
16736 | 2019-02-28 | 2020-01-14 | 2020-02-21 | 2020-02-21 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-07-20 | COMP | 2020-08-27 | COMP | Rule 16 | 221 | 27 | 41 | 1 | 66 | 29 | 380
17695 | 2019-02-28 | 2020-02-24 | 2020-05-27 | 2020-05-27 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2020-12-08 | COMP | 2021-01-05 | COMP | Rule 16 | 248 | 67 | 29 | 1 | 108 | 19 | 467
4166 | 2019-03-01 | 2019-05-09 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-24 | COMP | 2019-10-01 | COMP | 2019-09-25 | COMP | 2019-10-22 | COMP | Other | 50 | 82 | 15 | 6 | 0 | 16 | 165
10144 | 2019-03-01 | 2019-03-05 | 2019-04-17 | 2019-05-02 | COMP | 2019-08-13 | COMP | 2019-08-21 | COMP | 2019-09-11 | COMP | 2019-11-04 | COMP | Rule 15/16 | 3 | 32 | 72 | 7 | 15 | 39 | 174
10347 | 2019-03-01 | 2019-03-12 | 2020-02-21 | 2020-02-21 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2020-07-17 | COMP | 2020-08-19 | COMP | Rule 15/16 | 8 | 239 | 60 | 1 | 46 | 24 | 373
10349 | 2019-03-01 | 2019-03-12 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-10 | COMP | 2020-06-23 | COMP | 2020-06-19 | COMP | 2020-07-22 | COMP | Rule 15/16 | 8 | 310 | 7 | 10 | 0 | 22 | 353
10493 | 2019-03-01 | 2019-03-18 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-11 | COMP | 2019-07-09 | COMP | 2019-12-30 | COMP | 2020-03-06 | COMP | Rule 16 | 12 | 45 | 17 | 20 | 120 | 47 | 256
10521 | 2019-03-01 | 2019-03-19 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-14 | COMP | 2019-08-05 | COMP | 2019-11-27 | COMP | 2020-01-06 | COMP | Rule 16 | 13 | 47 | 17 | 36 | 81 | 25 | 214
10559 | 2019-03-01 | 2019-03-20 | 2019-09-22 | 2019-09-22 | COMP | 2020-01-10 | COMP | 2022-01-30 | REQD | 2020-09-29 | COMP | 2020-09-11 | COMP | Rule 16 | 14 | 130 | 75 |  |  |  | 389
10651 | 2019-03-01 | 2019-03-25 | 2019-05-14 | 2019-05-14 | COMP | 2019-05-20 | COMP | 2019-05-20 | COMP | 2019-05-17 | COMP | 2019-05-19 | COMP | Rule 16 | 17 | 37 | 5 | 1 | 0 |  | 56
10718 | 2019-03-01 | 2019-03-28 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-11 | COMP | 2019-04-15 | COMP | 2019-04-11 | COMP | 2019-04-16 | COMP | Rule 16 | 20 | 7 | 5 | 3 | 0 | 2 | 33
10932 | 2019-03-01 | 2019-04-04 | 2019-05-15 | 2019-05-15 | COMP | 2019-05-24 | COMP | 2019-06-24 | COMP | 2019-07-16 | COMP | 2019-08-01 | COMP | Rule 16 | 25 | 30 | 8 | 21 | 16 | 13 | 108
11193 | 2019-03-01 | 2019-04-17 | 2019-08-08 | 2019-08-08 | COMP | 2021-04-06 | COMP | 2021-04-06 | COMP | 2021-05-17 | COMP | 2022-03-14 | COMP | Rule 16 | 34 | 80 | 417 | 1 | 30 | 208 | 765
11292 | 2019-03-01 | 2019-04-22 | 2019-09-15 | 2019-09-15 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-02-04 | COMP | Rule 16 | 37 | 102 | 54 | 1 | 1 | 43 | 234
11297 | 2019-03-01 | 2019-04-22 | 2019-10-28 | 2019-12-13 | COMP | 2020-01-22 | COMP | 2020-01-27 | COMP | 2023-04-30 | INPR | 2020-06-17 | COMP | Rule 16 | 37 | 133 | 26 | 4 |  |  | 328
11414 | 2019-03-01 | 2019-04-25 | 2019-06-20 | 2019-06-20 | COMP | 2019-06-26 | COMP | 2019-08-20 | COMP | 2023-04-30 | INPR | 2019-09-18 | COMP | Rule 16 | 40 | 40 | 5 | 39 |  |  | 141
11416 | 2019-03-01 | 2019-04-25 | 2019-07-17 | 2019-07-17 | COMP | 2019-11-05 | COMP | 2019-11-15 | COMP | 2020-08-20 | COMP | 2020-10-16 | COMP | Rule 15/16 | 40 | 58 | 79 | 8 | 193 | 41 | 414
11519 | 2019-03-01 | 2019-05-01 | 2019-05-30 | 2019-05-30 | COMP | 2019-07-05 | COMP | 2019-07-30 | COMP | 2019-07-29 | COMP | 2019-08-28 | COMP | Rule 16 | 44 | 21 | 26 | 18 | 0 | 22 | 127
11653 | 2019-03-01 | 2019-05-07 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-20 | COMP | 2019-09-13 | COMP | 2020-10-15 | COMP | 2020-12-16 | COMP | Rule 16 | 48 | 69 | 6 | 18 | 276 | 42 | 454
11779 | 2019-03-01 | 2019-05-10 | 2019-08-23 | 2019-08-23 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-01-07 | COMP | 2021-03-25 | COMP | Rule 16 | 51 | 74 | 41 | 1 | 52 | 307 | 521
12790 | 2019-03-01 | 2019-06-22 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-01 | COMP | 2019-10-01 | COMP | 2019-10-08 | COMP | 2019-11-18 | COMP | Rule 16 | 80 | 56 | 15 | 1 | 6 | 29 | 183
13113 | 2019-03-01 | 2019-07-11 | 2020-01-15 | 2020-12-11 | COMP | 2021-06-04 | COMP | 2021-06-04 | COMP |  | INPR | 2022-11-29 | COMP | Rule 16 | 93 | 129 | 121 | 1 |  |  | 944
13170 | 2019-03-01 | 2019-07-15 | 2019-10-27 | 2019-12-16 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-05-13 | COMP | 2020-05-28 | COMP | Rule 16 | 95 | 74 | 26 | 1 | 79 | 11 | 314
13675 | 2019-03-01 | 2019-08-05 | 2019-09-12 | 2019-09-12 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-10-02 | COMP | 2019-10-04 | COMP | Rule 16 | 110 | 28 | 10 | 1 | 6 | 3 | 153
15200 | 2019-03-01 | 2019-10-18 | 2020-03-03 | 2022-02-24 | COMP | 2023-02-17 | COMP | 2023-08-17 | COMP | 2023-08-15 | COMP | 2023-10-19 | COMP | Rule 15/16 | 163 | 91 | 247 | 126 | 0 | 45 | 1168
16177 | 2019-03-01 | 2019-12-13 | 2020-02-26 | 2020-02-26 | COMP | 2020-04-20 | COMP | 2020-05-11 | COMP | 2020-05-01 | COMP | 2020-06-01 | COMP | Rule 16 | 200 | 50 | 39 | 16 | 0 | 15 | 316
16600 | 2019-03-01 | 2020-01-09 | 2020-05-21 | 2020-05-21 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-11-16 | COMP | 2020-12-08 | COMP | Rule 16 | 217 | 94 | 53 | 1 | 73 | 15 | 448
12001 | 2019-03-02 | 2019-05-21 | 2019-12-27 | 2019-12-27 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2023-11-07 | INPR | 2022-09-08 | COMP | Rule 16 | 57 | 152 | 78 | 1 |  |  | 888
17016 | 2019-03-02 | 2020-01-28 | 2020-04-01 | 2020-04-01 | COMP | 2020-08-04 | COMP | 2021-01-22 | COMP | 2021-01-22 | COMP | 2021-02-23 | COMP | Rule 16 | 228 | 46 | 89 | 117 | 1 | 22 | 498
10474 | 2019-03-03 | 2019-03-18 | 2019-10-03 | 2019-12-18 | COMP | 2020-01-06 | COMP | 2020-02-24 | COMP | 2020-03-28 | COMP | 2020-05-19 | COMP | Rule 15/16 | 11 | 141 | 12 | 34 | 25 | 37 | 307
10494 | 2019-03-03 | 2019-03-18 | 2019-03-28 | 2019-03-28 | COMP | 2019-04-05 | COMP | 2019-04-05 | COMP | 2019-06-06 | COMP | 2019-06-08 | COMP | Rule 16 | 11 | 9 | 7 | 1 | 44 | 2 | 69
15681 | 2019-03-03 | 2019-11-14 | 2020-02-06 | 2020-02-06 | COMP | 2020-02-19 | COMP | 2020-03-31 | COMP | 2020-10-26 | COMP | 2020-11-14 | COMP | Rule 16 | 180 | 56 | 9 | 30 | 148 | 14 | 432
17891 | 2019-03-03 | 2020-03-03 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-04-17 | COMP | 2020-05-06 | COMP | Rule 16 | 252 | 17 | 13 | 1 | 6 | 14 | 298
10299 | 2019-03-04 | 2019-03-11 | 2019-05-22 | 2019-06-28 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-09-05 | COMP | 2019-12-09 | COMP | Rule 16 | 6 | 53 | 8 | 1 | 41 | 65 | 195
10617 | 2019-03-04 | 2019-03-23 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-13 | COMP | 2019-09-19 | COMP | 2019-09-18 | COMP | 2020-07-25 | COMP | Rule 16 | 15 | 79 | 44 | 5 | 0 | 214 | 354
10737 | 2019-03-04 | 2019-03-28 | 2019-07-15 | 2019-07-15 | COMP | 2019-11-14 | NOTN | 2020-03-09 | COMP | 2020-02-21 | COMP | 2020-06-23 | COMP | Other | 19 | 76 |  | 163 | 0 | 76 | 331
11158 | 2019-03-04 | 2019-04-15 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-11-13 | COMP | 2019-12-19 | COMP | Rule 16 | 31 | 110 | 32 | 1 | 9 | 25 | 203
11503 | 2019-03-04 | 2019-04-30 | 2019-05-29 | 2019-05-29 | COMP | 2019-08-16 | COMP | 2020-01-10 | COMP | 2019-12-12 | COMP | 2020-01-25 | COMP | Rule 16 | 42 | 21 | 57 | 100 | 0 | 10 | 226
11671 | 2019-03-04 | 2019-05-07 | 2020-05-06 | 2020-05-06 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2021-09-24 | COMP | 2021-10-27 | COMP | Rule 16 | 47 | 252 | 69 | 1 | 283 | 24 | 671
11672 | 2019-03-04 | 2019-05-07 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2021-03-30 | COMP | 2021-04-05 | COMP | Rule 16 | 47 | 254 | 67 | 1 | 158 | 5 | 527
11756 | 2019-03-04 | 2019-05-09 | 2019-06-17 | 2019-06-17 | COMP | 2019-08-06 | COMP | 2019-10-23 | COMP | 2020-07-01 | COMP | 2020-07-30 | COMP | Rule 15/16 | 49 | 27 | 36 | 56 | 173 | 22 | 358
11819 | 2019-03-04 | 2019-05-14 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-12-31 | COMP | 2020-01-14 | COMP | Rule 16 | 52 | 89 | 16 | 1 | 56 | 10 | 219
11882 | 2019-03-04 | 2019-05-15 | 2019-07-27 | 2019-07-27 | COMP | 2019-10-29 | COMP | 2021-11-30 | COMP | 2021-11-30 | COMP | 2022-04-29 | COMP | Rule 16 | 53 | 51 | 66 | 524 | 1 | 107 | 798
11954 | 2019-03-04 | 2019-05-20 | 2019-07-11 | 2019-07-11 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-10-10 | COMP | 2019-11-11 | COMP | Rule 16 | 56 | 37 | 33 | 1 | 33 | 22 | 177
11961 | 2019-03-04 | 2019-05-20 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-17 | NOTN | 2019-11-12 | COMP | 2019-09-17 | COMP | 2020-02-24 | COMP | Rule 16 | 56 | 83 |  | 41 | 0 | 69 | 246
12659 | 2019-03-04 | 2019-06-18 | 2019-08-09 | 2019-08-09 | COMP | 2019-10-21 | COMP | 2020-03-17 | COMP | 2020-02-27 | COMP | 2020-08-14 | COMP | Rule 16 | 76 | 38 | 51 | 100 | 0 | 108 | 369
13384 | 2019-03-04 | 2019-07-23 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-06 | COMP | 2020-01-09 | COMP | 2019-12-13 | COMP | 2020-03-26 | COMP | Rule 16 | 100 | 82 | 13 | 23 | 0 | 54 | 269
13415 | 2019-03-04 | 2019-07-25 | 2020-02-21 | 2020-02-21 | COMP | 2020-05-12 | COMP | 2020-07-30 | COMP | 2020-10-05 | COMP | 2020-11-05 | COMP | Rule 16 | 102 | 144 | 58 | 57 | 47 | 24 | 427
13479 | 2019-03-04 | 2019-07-26 | 2020-05-01 | 2020-05-01 | COMP | 2020-06-12 | COMP | 2020-07-23 | COMP | 2023-12-03 | INPR | 2022-10-28 | COMP | Rule 15/16 | 103 | 193 | 30 | 30 |  |  | 924
13527 | 2019-03-04 | 2019-07-29 | 2019-09-12 | 2019-09-12 | COMP | 2019-09-23 | COMP | 2019-10-04 | COMP | 2019-09-23 | COMP | 2019-10-31 | COMP | Rule 16 | 104 | 33 | 8 | 10 | 0 | 20 | 171
13530 | 2019-03-04 | 2019-07-30 | 2019-12-04 | 2019-12-04 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-03-10 | COMP | 2020-03-27 | COMP | Rule 16 | 105 | 88 | 53 | 1 | 14 | 14 | 270
13762 | 2019-03-04 | 2019-08-08 | 2019-08-22 | 2019-08-22 | COMP | 2019-12-02 | COMP | 2020-10-15 | COMP | 2020-08-24 | COMP | 2020-12-18 | COMP | Rule 16 | 112 | 11 | 69 | 223 | 0 | 44 | 455
13781 | 2019-03-04 | 2019-08-09 | 2019-10-15 | 2019-12-09 | COMP | 2019-12-20 | COMP | 2020-01-31 | COMP | 2020-01-28 | COMP | 2020-02-06 | COMP | Rule 16 | 113 | 47 | 10 | 28 | 0 | 5 | 235
13843 | 2019-03-04 | 2019-08-13 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-11-06 | COMP | 2019-12-18 | COMP | Rule 16 | 115 | 32 | 13 | 1 | 18 | 28 | 202
14055 | 2019-03-04 | 2019-08-22 | 2020-10-25 | 2020-10-25 | COMP | 2022-02-17 | COMP | 2022-02-17 | COMP | 2022-07-12 | COMP | 2022-08-11 | COMP | Rule 15/16 | 122 | 297 | 330 | 1 | 100 | 23 | 869
14159 | 2019-03-04 | 2019-08-28 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-20 | COMP | 2020-08-20 | COMP | 2020-09-29 | COMP | 2020-10-22 | COMP | Rule 16 | 126 | 56 | 24 | 170 | 28 | 18 | 417
14337 | 2019-03-04 | 2019-09-05 | 2019-10-08 | 2019-10-08 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-11-13 | COMP | 2019-12-05 | COMP | Rule 16 | 131 | 24 | 10 | 1 | 17 | 15 | 193
14643 | 2019-03-04 | 2019-09-21 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-24 | COMP | 2020-05-21 | COMP | 2022-01-30 | INPR | 2020-06-05 | COMP | Rule 16 | 142 | 108 | 18 | 43 |  |  | 319
14679 | 2019-03-04 | 2019-09-23 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-18 | COMP | 2020-01-08 | COMP | 2022-05-10 | COMP | 2022-06-18 | COMP | Rule 16 | 143 | 26 | 35 | 14 | 591 | 28 | 832
14967 | 2019-03-04 | 2019-10-07 | 2020-05-02 | 2020-05-02 | COMP | 2021-03-10 | COMP | 2021-03-16 | COMP | 2021-03-10 | COMP | 2021-04-16 | COMP | Rule 16 | 153 | 143 | 214 | 5 | 0 | 24 | 536
15164 | 2019-03-04 | 2019-10-18 | 2019-11-12 | 2019-11-12 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2021-02-11 | COMP | 2021-07-29 | COMP | Rule 16 | 162 | 17 | 114 | 1 | 201 | 118 | 608
15435 | 2019-03-04 | 2019-10-31 | 2020-01-16 | 2020-01-16 | COMP | 2020-01-27 | COMP | 2020-05-13 | COMP | 2020-06-30 | COMP | 2020-07-14 | COMP | Rule 16 | 171 | 51 | 7 | 77 | 34 | 11 | 346
15691 | 2019-03-04 | 2019-11-15 | 2020-03-14 | 2020-05-07 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP |  |  | 2020-12-10 | COMP | Rule 16 | 181 | 80 | 83 | 1 |  |  | 449
17579 | 2019-03-04 | 2020-02-20 | 2020-05-14 | 2020-05-14 | COMP | 2020-06-08 | COMP | 2020-06-24 | COMP | 2020-07-21 | COMP | 2020-09-28 | COMP | Rule 16 | 244 | 61 | 17 | 13 | 20 | 49 | 399
34249 | 2019-03-04 | 2022-02-06 | 2022-04-21 | 2022-04-21 | COMP | 2022-12-22 | COMP | 2022-12-22 | COMP | 2023-04-06 | COMP | 2023-04-07 | COMP | Rule 16 | 739 | 53 | 169 | 1 | 72 | 2 | 1032
4128 | 2019-03-05 | 2019-03-20 | 2019-06-04 | 2019-06-04 | COMP | 2019-12-18 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-07-07 | COMP | Rule 15/16 | 12 | 54 | 137 | 3 | 1 | 138 | 340
10202 | 2019-03-05 | 2019-03-05 | 2020-02-12 | 2020-02-12 | COMP | 2020-02-19 | COMP | 2020-03-03 | COMP | 2020-03-04 | COMP | 2020-06-22 | COMP | Rule 15/16 | 1 | 238 | 5 | 10 | 2 | 78 | 329
10219 | 2019-03-05 | 2019-03-06 | 2019-09-07 | 2019-09-07 | COMP | 2019-09-24 | COMP | 2019-10-18 | COMP | 2019-11-25 | COMP | 2020-01-15 | COMP | Rule 16 | 2 | 130 | 12 | 19 | 26 | 34 | 219
10226 | 2019-03-05 | 2019-03-06 | 2019-07-11 | 2019-11-21 | COMP | 2021-06-22 | COMP | 2022-03-16 | COMP | 2021-12-28 | COMP | 2022-04-25 | COMP | Other | 2 | 90 | 398 | 185 | 0 | 29 | 793
10227 | 2019-03-05 | 2019-03-06 | 2019-06-27 | 2019-11-16 | COMP | 2021-07-06 | COMP | 2022-02-19 | COMP | 2021-12-06 | COMP | 2022-05-10 | COMP | Other | 2 | 81 | 410 | 159 | 0 | 56 | 804
10477 | 2019-03-05 | 2019-03-19 | 2019-08-02 | 2020-01-17 | COMP | 2020-01-31 | COMP | 2020-03-20 | COMP | 2020-03-17 | COMP | 2020-07-16 | COMP | Rule 16 | 11 | 97 | 10 | 35 | 0 | 84 | 347
10520 | 2019-03-05 | 2019-03-19 | 2019-06-12 | 2019-06-12 | COMP | 2019-06-14 | COMP | 2019-08-30 | COMP | 2019-09-28 | COMP | 2019-11-13 | COMP | Rule 16 | 11 | 61 | 3 | 55 | 20 | 32 | 178
10837 | 2019-03-05 | 2019-04-01 | 2019-09-01 | 2019-09-01 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | 2020-03-06 | COMP | 2020-07-02 | COMP | Rule 16 | 20 | 108 | 16 | 2 | 111 | 84 | 337
10925 | 2019-03-05 | 2019-04-04 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-05 | COMP | 2019-07-17 | COMP | 2019-07-11 | COMP | 2019-08-14 | COMP | Rule 15/16 | 23 | 51 | 15 | 9 | 0 | 21 | 115
11204 | 2019-03-05 | 2019-04-17 | 2019-07-15 | 2019-10-20 | COMP | 2019-10-28 | COMP | 2019-09-20 | COMP | 2019-11-26 | COMP | 2019-12-17 | COMP | Rule 15/16 | 32 | 62 | 6 |  | 47 | 14 | 200
11422 | 2019-03-05 | 2019-04-26 | 2019-10-10 | 2019-10-21 | COMP | 2019-11-07 | COMP | 2019-12-30 | COMP | 2019-12-02 | COMP | 2020-06-01 | COMP | Rule 16 | 39 | 117 | 14 | 34 | 0 | 107 | 314
11880 | 2019-03-05 | 2019-05-15 | 2019-07-22 | 2019-07-22 | COMP | 2019-10-02 | COMP | 2019-10-16 | COMP | 2019-08-26 | COMP | 2019-12-13 | COMP | Rule 16 | 52 | 47 | 52 | 11 | 0 | 40 | 198
11906 | 2019-03-05 | 2019-05-16 | 2019-09-27 | 2019-09-27 | COMP | 2019-12-02 | COMP | 2020-01-31 | COMP | 2020-01-14 | COMP | 2020-02-03 | COMP | Rule 16 | 53 | 94 | 44 | 42 | 0 | 2 | 231
12447 | 2019-03-05 | 2019-06-06 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-05 | COMP | 2019-07-05 | INPR | 2020-03-01 | REQD | 2019-10-21 | COMP | Rule 16 | 67 | 11 | 11 |  |  |  | 162
12522 | 2019-03-05 | 2019-06-11 | 2019-07-25 | 2020-04-14 | COMP | 2020-06-22 | COMP | 2019-12-02 | COMP |  |  | 2020-07-27 | COMP | Rule 16 | 70 | 32 | 49 |  |  |  | 354
12652 | 2019-03-05 | 2019-06-17 | 2019-10-18 | 2019-10-18 | COMP | 2020-04-20 | COMP | 2021-01-15 | COMP | 2021-01-07 | COMP | 2021-02-26 | COMP | Rule 16 | 74 | 88 | 125 | 188 | 0 | 29 | 500
12762 | 2019-03-05 | 2019-06-21 | 2019-07-13 | 2019-07-13 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-12-29 | INPR | 2019-08-26 | COMP | Rule 16 | 78 | 15 | 27 | 1 |  |  | 123
12855 | 2019-03-05 | 2019-06-25 | 2019-10-22 | 2019-10-22 | COMP | 2020-06-09 | COMP | 2020-06-30 | COMP | 2023-07-29 | INPR | 2021-03-05 | COMP | Rule 15/16 | 80 | 84 | 158 | 16 |  |  | 505
13046 | 2019-03-05 | 2019-07-08 | 2019-10-22 | 2019-10-22 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-04-26 | INPR | 2019-12-26 | COMP | Rule 16 | 88 | 76 | 7 | 1 |  |  | 206
13172 | 2019-03-05 | 2019-07-15 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2021-01-08 | COMP | 2021-02-24 | COMP | Rule 15/16 | 93 | 106 | 7 | 1 | 264 | 32 | 498
13345 | 2019-03-05 | 2019-07-23 | 2020-04-22 | 2020-06-22 | COMP | 2020-07-14 | COMP | 2020-08-04 | COMP | 2020-09-01 | COMP | 2020-11-04 | COMP | Rule 16 | 99 | 189 | 17 | 16 | 21 | 46 | 425
13360 | 2019-03-05 | 2019-07-23 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-07 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-06-23 | COMP | Rule 16 | 99 | 133 | 5 | 2 | 1 | 95 | 330
13525 | 2019-03-05 | 2019-07-29 | 2019-10-20 | 2020-09-04 | COMP | 2021-02-03 | COMP | 2021-02-03 | COMP | 2021-04-05 | COMP | 2021-05-10 | COMP | Rule 16 | 103 | 59 | 102 | 1 | 43 | 26 | 551
14441 | 2019-03-05 | 2019-09-10 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-18 | COMP | 2020-02-11 | COMP | 2020-03-03 | COMP | 2020-06-09 | COMP | Rule 16 | 133 | 59 | 11 | 37 | 15 | 70 | 320
14523 | 2019-03-05 | 2019-09-14 | 2019-10-31 | 2019-10-31 | COMP | 2019-12-23 | COMP | 2019-11-18 | COMP | 2021-01-05 | COMP | 2021-01-15 | COMP | Rule 16 | 136 | 34 | 35 |  | 284 | 9 | 472
14571 | 2019-03-05 | 2019-09-17 | 2019-10-27 | 2019-10-27 | COMP | 2020-01-31 | COMP | 2020-01-31 | INPR | 2022-01-30 | REQD | 2021-01-18 | COMP | Rule 16 | 138 | 29 | 64 |  |  |  | 472
14629 | 2019-03-05 | 2019-09-19 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-13 | COMP | 2020-04-23 | COMP | 2021-04-23 | COMP | 2021-05-27 | COMP | Rule 15/16 | 140 | 104 | 17 | 30 | 253 | 25 | 564
15036 | 2019-03-05 | 2019-10-12 | 2020-02-11 | 2020-03-06 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-04 | COMP | 2020-09-21 | COMP | Other | 156 | 81 | 100 | 1 | 8 | 34 | 393
15179 | 2019-03-05 | 2019-10-17 | 2020-02-14 | 2020-02-14 | COMP | 2020-11-18 | COMP | 2020-11-18 | COMP | 2020-12-14 | COMP | 2021-01-08 | COMP | Rule 16 | 160 | 81 | 195 | 1 | 17 | 18 | 467
15408 | 2019-03-05 | 2019-10-30 | 2020-02-20 | 2020-02-20 | COMP | 2020-02-24 | COMP | 2020-03-12 | COMP | 2020-03-23 | COMP | 2020-06-08 | COMP | Rule 16 | 169 | 75 | 3 | 14 | 8 | 55 | 319
15934 | 2019-03-05 | 2019-12-02 | 2020-01-14 | 2020-03-12 | COMP | 2020-04-16 | COMP | 2022-04-19 | COMP | 2022-05-03 | COMP | 2022-05-05 | COMP | Rule 16 | 189 | 30 | 26 | 507 | 11 | 3 | 801
16555 | 2019-03-05 | 2020-01-08 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-24 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-05-27 | COMP | Rule 16 | 214 | 42 | 35 | 2 | 1 | 22 | 311
17495 | 2019-03-05 | 2020-02-19 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-02 | COMP | 2021-01-25 | COMP | 2021-01-12 | COMP | 2021-02-17 | COMP | Rule 15/16 | 242 | 86 | 11 | 141 | 0 | 17 | 493
17791 | 2019-03-05 | 2020-02-27 | 2020-06-16 | 2020-07-28 | COMP | 2020-08-13 | COMP | 2020-10-06 | COMP | 2022-01-30 | INPR | 2020-11-02 | COMP | Rule 16 | 248 | 78 | 13 | 38 |  |  | 423
18077 | 2019-03-05 | 2020-03-10 | 2020-03-25 | 2020-03-25 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-14 | COMP | 2020-05-04 | COMP | Rule 16 | 256 | 12 | 5 | 1 | 11 | 15 | 295
18306 | 2019-03-05 | 2020-03-20 | 2020-05-14 | 2020-07-31 | COMP | 2021-05-04 | COMP | 2021-05-28 | COMP |  |  | 2021-07-21 | COMP | Rule 15/16 | 264 | 40 | 190 | 19 |  |  | 601
18315 | 2019-03-05 | 2020-03-19 | 2020-05-31 | 2020-05-31 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | 2020-12-04 | COMP | 2020-12-15 | COMP | Rule 15/16 | 263 | 51 | 127 | 1 | 5 | 8 | 451
19382 | 2019-03-05 | 2020-05-04 | 2020-07-09 | 2020-07-09 | COMP | 2020-09-11 | COMP | 2020-09-11 | COMP | 2020-09-13 | COMP | 2020-11-23 | COMP | Rule 16 | 295 | 48 | 46 | 1 | 1 | 50 | 437
10354 | 2019-03-06 | 2019-03-12 | 2021-11-23 | 2021-11-23 | COMP | 2022-05-18 | COMP | 2022-11-01 | COMP | 2022-11-01 | COMP | 2022-12-05 | COMP | Rule 15/16 | 5 | 683 | 123 | 116 | 1 | 22 | 945
10540 | 2019-03-06 | 2019-03-20 | 2019-06-03 | 2019-06-03 | COMP | 2019-06-25 | COMP | 2019-08-14 | COMP | 2020-05-31 | INPR | 2019-08-13 | COMP | Rule 15/16 | 11 | 53 | 17 | 36 |  |  | 113
10898 | 2019-03-06 | 2019-04-04 | 2020-08-13 | 2020-08-13 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2021-10-26 | COMP | 2022-01-27 | COMP | Rule 16 | 22 | 345 | 49 | 1 | 255 | 64 | 731
10954 | 2019-03-06 | 2019-04-05 | 2021-02-09 | 2021-08-23 | COMP | 2021-10-19 | COMP | 2021-10-21 | COMP | 2022-01-28 | COMP | 2022-03-11 | COMP | Rule 15/16 | 23 | 465 | 41 | 3 | 68 | 30 | 761
11100 | 2019-03-06 | 2019-04-12 | 2019-08-12 | 2019-08-12 | COMP | 2019-09-03 | COMP | 2019-10-01 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | Rule 16 | 28 | 85 | 16 | 21 | 10 | 1 | 156
11184 | 2019-03-06 | 2019-04-16 | 2019-07-15 | 2019-07-15 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-08-08 | COMP | 2019-09-25 | COMP | Rule 16 | 30 | 63 | 32 | 1 | 0 | 21 | 143
11207 | 2019-03-06 | 2019-04-17 | 2019-06-17 | 2019-06-17 | COMP | 2019-06-19 | COMP | 2019-06-19 | COMP | 2019-07-16 | COMP | 2019-07-23 | COMP | Rule 16 | 31 | 43 | 3 | 1 | 19 | 6 | 98
11260 | 2019-03-06 | 2019-04-19 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-11 | COMP | 2019-07-15 | COMP | 2019-07-17 | COMP | 2019-08-26 | COMP | Rule 15/16 | 33 | 43 | 16 | 3 | 3 | 29 | 122
11271 | 2019-03-06 | 2019-04-19 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-07-18 | COMP | Rule 15/16 | 33 | 51 | 12 | 1 | 1 | 2 | 95
11352 | 2019-03-06 | 2019-04-25 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2020-01-06 | COMP | 2020-02-07 | COMP | Rule 15/16 | 37 | 83 | 27 | 1 | 67 | 24 | 234
11635 | 2019-03-06 | 2019-05-07 | 2019-09-18 | 2019-09-18 | COMP | 2019-11-27 | COMP | 2019-12-03 | COMP | 2020-02-15 | COMP | 2020-03-25 | COMP | Rule 16 | 45 | 94 | 50 | 3 | 51 | 27 | 266
11696 | 2019-03-06 | 2019-05-08 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-25 | COMP | 2019-12-11 | COMP | 2023-11-12 | INPR | 2020-03-12 | COMP | Rule 16 | 46 | 111 | 30 | 11 |  |  | 257
12015 | 2019-03-06 | 2019-05-21 | 2019-08-07 | 2019-08-07 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2020-01-21 | COMP | 2020-06-01 | COMP | Rule 16 | 55 | 55 | 19 | 1 | 95 | 93 | 313
12081 | 2019-03-06 | 2019-05-22 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-15 | COMP | 2020-02-24 | COMP | 2020-05-13 | COMP | 2020-07-10 | COMP | Rule 16 | 56 | 144 | 20 | 27 | 58 | 42 | 342
12138 | 2019-03-06 | 2019-05-24 | 2019-07-03 | 2019-07-03 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-11-15 | COMP | 2020-03-02 | COMP | Rule 16 | 58 | 28 | 7 | 1 | 89 | 71 | 249
12169 | 2019-03-06 | 2019-05-25 | 2019-10-01 | 2019-10-01 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2023-05-23 | COMP | 2023-06-13 | COMP | Rule 16 | 58 | 89 | 97 | 1 | 820 | 15 | 1076
12189 | 2019-03-06 | 2019-05-28 | 2019-10-07 | 2019-10-07 | COMP | 2020-06-09 | NOTN | 2020-06-12 | COMP | 2020-06-09 | COMP | 2020-07-17 | COMP | Other | 59 | 93 |  | 172 | 0 | 26 | 347
12276 | 2019-03-06 | 2019-05-30 | 2020-06-17 | 2020-11-05 | COMP | 2021-04-26 | COMP | 2021-05-21 | COMP | 2023-06-01 | COMP | 2023-12-15 | COMP | Rule 15/16 | 61 | 265 | 116 | 20 | 510 | 136 | 1203
12585 | 2019-03-06 | 2019-06-14 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-23 | COMP | 2020-01-15 | COMP | 2020-11-03 | COMP | 2020-02-04 | COMP | Rule 16 | 72 | 65 | 6 | 78 | 206 |  | 231
12595 | 2019-03-06 | 2019-06-14 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-06 | COMP | 2020-06-12 | COMP | 2020-07-14 | COMP | 2020-09-03 | COMP | Rule 16 | 72 | 30 | 30 | 193 | 23 | 38 | 381
12697 | 2019-03-06 | 2019-06-18 | 2019-09-12 | 2019-09-12 | COMP | 2019-10-04 | COMP | 2019-11-01 | COMP | 2019-10-19 | COMP | 2019-12-16 | COMP | Rule 16 | 74 | 61 | 17 | 21 | 0 | 29 | 198
13434 | 2019-03-06 | 2019-07-24 | 2020-04-30 | 2020-04-30 | COMP | 2020-11-24 | COMP | 2020-11-24 | COMP | 2020-06-22 | COMP | 2021-01-25 | COMP | Rule 16 | 99 | 194 | 146 | 1 | 0 | 40 | 476
13921 | 2019-03-06 | 2019-08-16 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-20 | COMP | 2020-09-29 | COMP | 2021-01-26 | COMP | 2020-10-02 | COMP | Rule 16 | 116 | 184 | 8 | 93 | 80 |  | 401
14962 | 2019-03-06 | 2019-10-07 | 2020-06-21 | 2020-06-21 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP |  | INPR | 2021-02-22 | COMP | Rule 15/16 | 151 | 177 | 21 | 1 |  |  | 495
15288 | 2019-03-06 | 2019-10-24 | 2020-01-25 | 2020-01-25 | COMP | 2020-03-04 | COMP | 2020-04-04 | COMP | 2020-07-13 | COMP | 2020-08-06 | COMP | Rule 16 | 164 | 61 | 27 | 23 | 70 | 19 | 361
15840 | 2019-03-06 | 2019-11-24 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-05 | COMP | 2020-09-16 | COMP | 2020-10-09 | COMP | 2020-10-29 | COMP | Rule 16 | 184 | 85 | 27 | 95 | 18 | 15 | 420
16539 | 2019-03-06 | 2020-01-08 | 2020-01-11 | 2020-01-11 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-01-29 | COMP | 2020-02-19 | COMP | Rule 16 | 213 | 3 | 11 | 1 | 2 | 15 | 241
10335 | 2019-03-07 | 2019-03-11 | 2019-04-05 | 2019-04-05 | COMP | 2019-04-26 | COMP | 2019-10-16 | COMP | 2019-10-15 | COMP | 2019-12-03 | COMP | Rule 16 | 3 | 20 | 16 | 121 | 0 | 32 | 188
10731 | 2019-03-07 | 2019-03-28 | 2019-12-07 | 2019-12-07 | COMP | 2020-03-23 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2021-02-13 | COMP | Rule 15/16 | 16 | 176 | 72 | 19 | 1 | 209 | 489
10754 | 2019-03-07 | 2019-03-28 | 2019-07-15 | 2019-07-15 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2019-12-18 | COMP | 2020-02-05 | COMP | Rule 16 | 16 | 76 | 107 | 1 | 3 | 33 | 231
10937 | 2019-03-07 | 2019-04-06 | 2019-07-15 | 2019-07-15 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2020-01-27 | COMP | 2020-08-27 | COMP | Rule 16 | 22 | 69 | 76 | 1 | 59 | 152 | 375
10974 | 2019-03-07 | 2019-04-06 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-15 | COMP | 2019-09-03 | COMP | 2019-09-12 | COMP | 2019-11-13 | COMP | Rule 16 | 22 | 60 | 10 | 36 | 8 | 44 | 176
11014 | 2019-03-07 | 2019-04-09 | 2019-06-27 | 2021-02-04 | COMP | 2021-01-28 | NOTN | 2021-02-04 | COMP | 2021-02-05 | NOTN | 2021-03-08 | COMP | Other | 24 | 57 |  | 1 |  |  | 504
11038 | 2019-03-07 | 2019-04-10 | 2019-05-24 | 2019-05-24 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-14 | COMP | 2019-09-12 | COMP | Rule 16 | 25 | 33 | 54 | 1 | 4 | 21 | 133
11600 | 2019-03-07 | 2019-05-03 | 2019-08-21 | 2019-08-21 | COMP | 2019-08-23 | COMP | 2019-11-06 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | Rule 16 | 42 | 77 | 3 | 53 | 9 | 1 | 180
11818 | 2019-03-07 | 2019-05-14 | 2019-09-07 | 2019-09-07 | COMP | 2019-10-29 | COMP | 2020-03-31 | COMP | 2020-10-20 | COMP | 2021-07-30 | COMP | Rule 15/16 | 49 | 81 | 37 | 104 | 144 | 195 | 606
12047 | 2019-03-07 | 2019-05-21 | 2019-06-07 | 2020-03-23 | COMP | 2020-06-09 | COMP | 2020-12-23 | COMP | 2020-12-23 | COMP | 2021-01-21 | COMP | Rule 16 | 54 | 13 | 56 | 138 | 1 | 19 | 473
12405 | 2019-03-07 | 2019-06-05 | 2019-07-23 | 2019-07-23 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-11-15 | COMP | 2020-02-13 | COMP | Rule 16 | 64 | 34 | 30 | 1 | 53 | 60 | 237
12810 | 2019-03-07 | 2019-06-24 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-04-26 | INPR | 2020-01-10 | COMP | Rule 16 | 77 | 71 | 14 | 1 |  |  | 214
13131 | 2019-03-07 | 2019-07-12 | 2019-08-16 | 2019-08-16 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-09 | COMP | 2019-11-15 | COMP | Rule 16 | 90 | 26 | 37 | 1 | 2 | 27 | 178
13563 | 2019-03-07 | 2019-07-31 | 2019-10-26 | 2019-10-26 | COMP | 2019-12-12 | COMP | 2020-05-19 | COMP | 2020-05-06 | COMP | 2020-06-13 | COMP | Rule 16 | 103 | 62 | 31 | 110 | 0 | 18 | 321
14007 | 2019-03-07 | 2019-08-20 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-20 | COMP | 2020-10-02 | COMP | 2020-10-03 | COMP | 2020-11-14 | COMP | Rule 15/16 | 117 | 129 | 18 | 139 | 1 | 29 | 429
14045 | 2019-03-07 | 2019-08-22 | 2019-10-30 | 2019-10-30 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-08-31 | COMP | 2020-09-29 | COMP | Rule 15/16 | 119 | 49 | 53 | 1 | 159 | 21 | 397
14320 | 2019-03-07 | 2019-09-04 | 2020-04-20 | 2020-09-18 | COMP | 2020-11-13 | COMP | 2022-09-27 | COMP | 2022-09-27 | COMP | 2023-04-16 | COMP | Rule 15/16 | 127 | 157 | 40 | 470 | 1 | 137 | 1034
14390 | 2019-03-07 | 2019-09-08 | 2020-06-15 | 2020-06-15 | COMP | 2020-08-05 | NOTN | 2020-10-16 | COMP | 2020-11-19 | NOTN | 2021-03-05 | COMP | Other | 129 | 193 |  | 89 |  |  | 503
14945 | 2019-03-07 | 2019-10-05 | 2019-12-01 | 2020-04-28 | COMP | 2020-04-15 | NOTN | 2020-04-15 | COMP | 2022-02-26 | INPR | 2020-05-27 | COMP | Other | 149 | 37 |  |  |  |  | 309
18875 | 2019-03-07 | 2020-04-09 | 2020-05-19 | 2020-11-03 | COMP | 2020-11-12 | COMP | 2020-07-09 | COMP | 2020-11-13 | COMP | 2020-12-24 | COMP | Rule 16 | 276 | 29 | 7 |  | 90 | 28 | 456
10288 | 2019-03-08 | 2019-03-09 | 2019-06-18 | 2019-09-07 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | 2019-10-23 | COMP | 2019-11-05 | COMP | Rule 16 | 1 | 71 | 12 | 2 | 21 | 10 | 170
10576 | 2019-03-08 | 2019-03-21 | 2019-05-15 | 2019-05-15 | COMP | 2019-08-13 | COMP | 2019-06-17 | COMP | 2019-12-29 | INPR | 2019-07-24 | COMP | Rule 16 | 10 | 40 | 63 |  |  |  | 97
10577 | 2019-03-08 | 2019-03-21 | 2019-06-18 | 2019-06-18 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-12-29 | INPR | 2019-07-24 | COMP | Rule 16 | 10 | 63 | 4 | 1 |  |  | 97
10706 | 2019-03-08 | 2019-03-27 | 2019-07-23 | 2019-07-25 | COMP | 2019-08-22 | COMP | 2019-11-07 | COMP | 2023-04-30 | INPR | 2019-11-19 | COMP | Rule 16 | 14 | 83 | 21 | 55 |  |  | 179
10812 | 2019-03-08 | 2019-04-01 | 2019-08-01 | 2019-12-12 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-07-21 | COMP | 2020-07-29 | COMP | Rule 16 | 17 | 87 | 13 | 1 | 142 | 7 | 353
11341 | 2019-03-08 | 2019-04-23 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-26 | COMP | 2019-10-14 | COMP | 2019-11-22 | COMP | 2020-01-28 | COMP | Rule 16 | 33 | 79 | 10 | 35 | 29 | 43 | 224
11370 | 2019-03-08 | 2019-04-24 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-11 | COMP | 2019-11-20 | COMP | 2023-12-30 | INPR | 2019-12-20 | COMP | Rule 16 | 34 | 113 | 8 | 28 |  |  | 200
11398 | 2019-03-08 | 2019-04-24 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-26 | COMP | 2019-08-16 | COMP | 2019-08-01 | COMP | 2019-09-06 | COMP | Rule 16 | 34 | 41 | 26 | 16 | 0 | 15 | 128
11766 | 2019-03-08 | 2019-05-10 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-30 | COMP | 2019-09-13 | COMP | 2019-11-06 | COMP | 2019-12-04 | COMP | Rule 16 | 46 | 54 | 25 | 10 | 39 | 18 | 188
11955 | 2019-03-08 | 2019-05-19 | 2019-08-19 | 2020-05-20 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-08-11 | COMP | 2020-10-14 | COMP | Rule 16 | 51 | 64 | 25 | 1 | 35 | 46 | 407
11999 | 2019-03-08 | 2019-05-20 | 2019-10-31 | 2019-10-31 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2021-02-27 | INPR | 2020-02-04 | COMP | Rule 16 | 52 | 116 | 28 | 1 |  |  | 229
12222 | 2019-03-08 | 2019-05-28 | 2019-10-14 | 2019-10-14 | COMP | 2019-12-02 | COMP | 2019-12-02 | INPR | 2021-03-27 | REQD | 2020-03-24 | COMP | Rule 16 | 57 | 98 | 33 |  |  |  | 263
13276 | 2019-03-08 | 2019-07-18 | 2019-10-07 | 2019-10-07 | COMP | 2019-11-12 | COMP | 2019-12-23 | COMP | 2020-02-03 | COMP | 2020-02-24 | COMP | Rule 15/16 | 93 | 57 | 26 | 28 | 28 | 15 | 242
13693 | 2019-03-08 | 2019-08-05 | 2019-10-03 | 2020-05-26 | COMP | 2020-06-24 | COMP | 2022-06-07 | COMP | 2022-06-03 | COMP | 2022-08-02 | COMP | Rule 15/16 | 105 | 43 | 22 | 493 | 0 | 39 | 858
14908 | 2019-03-08 | 2019-10-03 | 2020-02-26 | 2021-03-23 | COMP | 2021-04-29 | COMP | 2021-08-25 | COMP | 2021-08-24 | COMP | 2021-11-30 | COMP | Rule 15/16 | 147 | 98 | 28 | 83 | 0 | 66 | 688
15182 | 2019-03-08 | 2019-10-17 | 2020-02-12 | 2020-07-17 | COMP | 2020-07-21 | COMP | 2020-09-30 | COMP | 2022-07-16 | INPR | 2020-11-25 | COMP | Rule 16 | 157 | 79 | 3 | 51 |  |  | 436
15771 | 2019-03-08 | 2019-11-20 | 2020-03-22 | 2020-04-05 | COMP | 2020-04-13 | COMP | 2022-05-08 | COMP | 2022-05-18 | COMP | 2022-06-22 | COMP | Rule 15/16 | 180 | 82 | 6 | 523 | 8 | 24 | 830
17479 | 2019-03-08 | 2020-02-18 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-05-08 | COMP | 2020-05-09 | COMP | Rule 15/16 | 238 | 9 | 42 | 1 | 10 | 1 | 296
17596 | 2019-03-08 | 2020-02-20 | 2020-05-15 | 2020-05-15 | COMP | 2021-05-05 | COMP | 2021-10-12 | COMP | 2021-10-13 | COMP | 2021-12-22 | COMP | Rule 16 | 240 | 62 | 245 | 112 | 2 | 48 | 704
42059 | 2019-03-08 | 2023-06-05 | 2023-10-24 | 2023-10-24 | COMP | 2023-10-24 | NOTN | 2023-11-01 | COMP | 2023-11-27 | COMP | 2023-12-13 | COMP | Other | 1068 | 99 |  | 7 | 16 | 13 | 1199
10367 | 2019-03-09 | 2019-03-12 | 2019-06-05 | 2019-06-05 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2019-09-19 | COMP | 2019-10-02 | COMP | Rule 16 | 2 | 61 | 73 | 1 | 3 | 10 | 145
10702 | 2019-03-10 | 2019-03-27 | 2019-06-20 | 2019-06-20 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-09-05 | COMP | 2019-10-14 | COMP | Rule 16 | 13 | 61 | 13 | 1 | 42 | 28 | 153
10575 | 2019-03-11 | 2019-03-20 | 2019-06-08 | 2019-06-08 | COMP | 2019-07-15 | COMP | 2019-07-16 | COMP | 2019-11-18 | COMP | 2019-12-03 | COMP | Rule 16 | 8 | 57 | 25 | 2 | 88 | 10 | 186
10641 | 2019-03-11 | 2019-03-23 | 2019-07-09 | 2019-07-09 | COMP | 2019-09-18 | COMP | 2021-01-06 | COMP | 2021-03-30 | COMP | 2021-04-06 | COMP | Other | 10 | 75 | 51 | 327 | 58 | 6 | 523
10756 | 2019-03-11 | 2019-03-28 | 2019-04-26 | 2019-04-26 | COMP | 2019-05-17 | COMP | 2019-06-04 | COMP | 2019-08-08 | COMP | 2019-08-14 | COMP | Rule 16 | 14 | 22 | 16 | 12 | 47 | 5 | 111
10817 | 2019-03-11 | 2019-04-01 | 2019-09-11 | 2020-12-24 | COMP | 2021-04-16 | COMP | 2021-04-16 | COMP | 2022-09-20 | COMP | 2022-11-16 | COMP | Rule 16 | 16 | 115 | 78 | 1 | 361 | 41 | 931
10941 | 2019-03-11 | 2019-04-06 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2019-08-28 | COMP | 2019-09-10 | COMP | Rule 16 | 20 | 84 | 11 | 1 | 8 | 9 | 129
10953 | 2019-03-11 | 2019-04-05 | 2019-07-18 | 2019-07-18 | COMP | 2019-10-21 | COMP | 2021-02-18 | COMP | 2021-04-07 | COMP | 2021-04-27 | COMP | Rule 16 | 20 | 73 | 67 | 333 | 35 | 15 | 538
11172 | 2019-03-11 | 2019-04-16 | 2019-10-04 | 2019-10-04 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-03-26 | COMP | 2020-06-10 | COMP | Rule 16 | 27 | 121 | 50 | 1 | 69 | 54 | 317
11420 | 2019-03-11 | 2019-04-26 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-08-13 | COMP | 2019-10-02 | COMP | Rule 16 | 35 | 64 | 8 | 1 | 5 | 36 | 145
11541 | 2019-03-11 | 2019-05-01 | 2019-08-09 | 2019-08-09 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-09 | COMP | 2019-11-13 | COMP | Rule 15 | 38 | 71 | 42 | 1 | 2 | 25 | 174
11716 | 2019-03-11 | 2019-05-09 | 2019-08-12 | 2019-09-11 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2021-01-20 | COMP | 2021-02-23 | COMP | Rule 16 | 44 | 66 | 14 | 1 | 328 | 24 | 493
11752 | 2019-03-11 | 2019-05-09 | 2019-08-28 | 2019-08-28 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-10-21 | COMP | 2019-11-15 | COMP | Rule 16 | 44 | 78 | 30 | 1 | 9 | 19 | 176
11959 | 2019-03-11 | 2019-05-19 | 2019-08-09 | 2019-09-17 | COMP | 2019-09-20 | COMP | 2019-10-07 | COMP | 2019-10-21 | COMP | 2019-12-12 | COMP | Rule 16 | 50 | 58 | 4 | 12 | 11 | 36 | 193
12007 | 2019-03-11 | 2019-05-20 | 2019-08-02 | 2019-08-02 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2022-03-29 | COMP | 2022-05-17 | COMP | Rule 16 | 51 | 53 | 58 | 1 | 611 | 36 | 805
12010 | 2019-03-11 | 2019-05-20 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-07-22 | COMP | 2019-10-21 | COMP | Rule 16 | 51 | 22 | 9 | 1 | 15 | 65 | 158
12025 | 2019-03-11 | 2019-05-21 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-23 | COMP | 2019-12-18 | COMP | 2019-11-19 | COMP | 2020-01-15 | COMP | Rule 16 | 52 | 87 | 23 | 38 | 0 | 19 | 215
12075 | 2019-03-11 | 2019-05-22 | 2019-07-01 | 2019-07-01 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2021-04-24 | INPR | 2020-03-31 | COMP | Rule 16 | 53 | 28 | 165 | 1 |  |  | 267
12083 | 2019-03-11 | 2019-05-22 | 2019-07-22 | 2019-07-22 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-03-30 | COMP | 2020-03-31 | COMP | Rule 16 | 53 | 42 | 151 | 1 | 23 | 2 | 267
12120 | 2019-03-11 | 2019-05-23 | 2019-08-16 | 2019-08-16 | COMP | 2019-09-03 | COMP | 2019-09-20 | COMP | 2019-10-23 | COMP | 2019-11-18 | COMP | Rule 16 | 54 | 60 | 12 | 14 | 24 | 18 | 177
12253 | 2019-03-11 | 2019-05-29 | 2019-06-13 | 2019-06-13 | COMP | 2019-06-25 | COMP | 2019-10-07 | COMP | 2019-10-09 | COMP | 2019-10-16 | COMP | Rule 16 | 57 | 12 | 9 | 73 | 3 | 6 | 155
12376 | 2019-03-11 | 2019-06-04 | 2020-02-06 | 2020-02-28 | COMP | 2020-03-24 | COMP | 2020-04-17 | COMP | 2021-12-16 | COMP | 2021-01-05 | COMP | Rule 16 | 61 | 170 | 18 | 19 | 420 |  | 460
12646 | 2019-03-11 | 2019-06-17 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-23 | COMP | 2019-12-05 | COMP | 2019-12-06 | COMP | 2020-02-19 | COMP | Rule 16 | 70 | 29 | 21 | 71 | 2 | 50 | 238
12669 | 2019-03-11 | 2019-06-18 | 2019-12-02 | 2019-12-02 | COMP | 2020-01-15 | COMP | 2020-02-25 | COMP | 2021-04-17 | INPR | 2020-04-23 | COMP | Rule 15/16 | 71 | 115 | 31 | 28 |  |  | 284
13249 | 2019-03-11 | 2019-07-18 | 2020-01-17 | 2021-09-23 | COMP | 2021-11-04 | COMP | 2022-01-07 | COMP | 2022-01-06 | COMP | 2022-06-01 | COMP | Rule 15/16 | 92 | 126 | 31 | 44 | 0 | 101 | 815
13930 | 2019-03-11 | 2019-08-16 | 2019-11-22 | 2020-03-26 | COMP | 2020-03-31 | COMP | 2020-05-08 | COMP | 2020-05-04 | COMP | 2020-06-11 | COMP | Rule 16 | 113 | 69 | 4 | 29 | 0 | 24 | 318
13941 | 2019-03-11 | 2019-08-16 | 2019-12-23 | 2019-12-23 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-03-02 | COMP | 2020-06-12 | COMP | Rule 16 | 113 | 88 | 30 | 1 | 18 | 74 | 319
13980 | 2019-03-11 | 2019-08-19 | 2020-04-29 | 2020-04-29 | COMP | 2020-06-11 | COMP | 2021-02-03 | COMP | 2021-08-31 | COMP | 2021-10-05 | COMP | Rule 15/16 | 114 | 175 | 31 | 163 | 147 | 25 | 650
14434 | 2019-03-11 | 2019-09-09 | 2020-01-27 | 2020-01-27 | COMP | 2020-08-11 | COMP | 2020-09-04 | COMP | 2020-12-14 | COMP | 2021-01-07 | COMP | Rule 16 | 128 | 95 | 140 | 19 | 68 | 17 | 462
14759 | 2019-03-11 | 2019-09-26 | 2020-03-20 | 2020-05-01 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2021-02-23 | COMP | 2021-04-11 | COMP | Rule 15/16 | 141 | 120 | 47 | 1 | 158 | 34 | 526
15224 | 2019-03-11 | 2019-10-21 | 2020-04-16 | 2020-04-16 | COMP | 2021-02-24 | COMP | 2021-03-10 | COMP | 2021-04-01 | COMP | 2021-04-28 | COMP | Rule 16 | 158 | 122 | 216 | 11 | 17 | 20 | 539
15494 | 2019-03-11 | 2019-11-04 | 2020-04-02 | 2020-04-02 | COMP | 2021-06-17 | COMP | 2021-06-21 | COMP | 2022-06-08 | COMP | 2022-07-06 | COMP | Rule 16 | 168 | 102 | 306 | 3 | 245 | 19 | 838
15500 | 2019-03-11 | 2019-11-06 | 2020-03-05 | 2020-03-05 | COMP | 2020-03-16 | COMP | 2020-06-18 | COMP | 2020-10-14 | COMP | 2020-09-24 | COMP | Rule 15/16 | 170 | 80 | 8 | 68 | 84 |  | 392
16226 | 2019-03-11 | 2019-12-17 | 2020-04-23 | 2020-09-30 | COMP | 2020-11-17 | COMP | 2020-12-11 | COMP | 2020-12-01 | COMP | 2021-02-01 | COMP | Rule 15 | 196 | 89 | 34 | 17 | 0 | 34 | 478
17034 | 2019-03-11 | 2020-01-28 | 2020-03-02 | 2020-03-02 | COMP | 2021-07-01 | COMP | 2021-07-06 | COMP | 2021-08-17 | COMP | 2021-10-05 | COMP | Rule 16 | 223 | 24 | 339 | 3 | 31 | 35 | 650
10760 | 2019-03-12 | 2019-03-28 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-08 | COMP | 2019-08-21 | COMP | 2019-08-29 | COMP | 2019-09-20 | COMP | Rule 15/16 | 13 | 92 | 3 | 10 | 7 | 16 | 136
10805 | 2019-03-12 | 2019-03-30 | 2019-07-04 | 2019-07-04 | COMP | 2019-07-16 | COMP | 2020-01-06 | COMP |  | INPR | 2023-05-03 | COMP | Rule 16 | 14 | 67 | 8 | 119 |  |  | 1044
10807 | 2019-03-12 | 2019-03-30 | 2019-05-07 | 2019-05-07 | COMP | 2019-05-13 | COMP | 2019-05-13 | COMP | 2020-02-11 | COMP | 2020-03-21 | COMP | Rule 16 | 14 | 27 | 5 | 1 | 188 | 28 | 259
10825 | 2019-03-12 | 2019-04-01 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-11-05 | COMP | 2019-11-18 | COMP | Rule 16 | 15 | 97 | 27 | 1 | 32 | 9 | 176
10831 | 2019-03-12 | 2019-04-01 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-24 | COMP | 2019-07-23 | COMP | 2019-09-03 | COMP | 2019-09-05 | COMP | Rule 16 | 15 | 57 | 4 | 21 | 30 | 3 | 125
10888 | 2019-03-12 | 2019-04-03 | 2019-06-30 | 2019-06-30 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-08-30 | COMP | Rule 15/16 | 17 | 62 | 20 | 1 | 1 | 25 | 122
10894 | 2019-03-12 | 2019-04-03 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | 2019-07-25 | COMP | 2019-08-01 | COMP | Rule 16 | 17 | 74 | 7 | 2 | 0 | 5 | 101
11124 | 2019-03-12 | 2019-04-15 | 2019-07-26 | 2019-07-26 | COMP | 2019-07-26 | NOTN | 2019-10-11 | COMP | 2019-07-26 | COMP | 2020-02-04 | COMP | Other | 25 | 73 |  | 55 | 0 | 77 | 227
11178 | 2019-03-12 | 2019-04-17 | 2019-05-08 | 2019-06-26 | COMP | 2019-07-12 | COMP | 2019-07-12 | INPR | 2020-04-26 | REQD | 2019-07-24 | COMP | Rule 16 | 27 | 16 | 12 |  |  |  | 95
11231 | 2019-03-12 | 2019-04-18 | 2019-05-21 | 2019-05-21 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2022-12-15 | COMP | 2019-08-02 | COMP | Rule 16 | 28 | 24 | 16 | 1 | 884 |  | 102
11233 | 2019-03-12 | 2019-04-18 | 2019-07-08 | 2019-07-08 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-09-30 | COMP | 2019-10-18 | COMP | Rule 16 | 28 | 56 | 42 | 1 | 19 | 15 | 156
11362 | 2019-03-12 | 2019-04-24 | 2019-07-05 | 2019-07-05 | COMP | 2019-07-09 | NOTN | 2019-07-09 | COMP | 2019-07-10 | COMP | 2019-08-06 | COMP | Other | 32 | 51 |  | 3 | 2 | 20 | 104
11425 | 2019-03-12 | 2019-04-26 | 2019-08-11 | 2019-08-11 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-10-01 | COMP | 2019-11-08 | COMP | Rule 16 | 34 | 74 | 17 | 1 | 20 | 29 | 171
11707 | 2019-03-12 | 2019-05-08 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-05 | COMP | 2019-09-20 | COMP | 2019-09-21 | COMP | 2019-10-03 | COMP | Rule 16 | 42 | 56 | 6 | 34 | 1 | 9 | 145
11966 | 2019-03-12 | 2019-05-20 | 2019-08-27 | 2019-08-27 | COMP | 2019-10-14 | COMP | 2021-01-26 | COMP | 2021-03-09 | COMP | 2021-04-29 | COMP | Rule 16 | 50 | 70 | 34 | 322 | 30 | 38 | 539
11987 | 2019-03-12 | 2019-05-20 | 2019-09-27 | 2019-10-02 | COMP | 2019-10-22 | COMP | 2019-11-20 | COMP | 2019-12-04 | COMP | 2020-02-04 | COMP | Rule 16 | 50 | 92 | 15 | 21 | 9 | 42 | 227
12031 | 2019-03-12 | 2019-05-21 | 2019-07-18 | 2019-07-18 | COMP | 2019-08-06 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2019-08-16 | COMP | Rule 16 | 51 | 41 | 14 | 8 | 1 | 2 | 112
13016 | 2019-03-12 | 2019-07-03 | 2020-03-26 | 2020-03-26 | COMP | 2020-03-26 | NOTN | 2020-04-16 | COMP | 2020-08-26 | COMP | 2020-09-19 | COMP | Other | 81 | 183 |  | 16 | 94 | 17 | 387
13051 | 2019-03-12 | 2019-07-09 | 2019-11-27 | 2019-11-27 | COMP | 2020-02-14 | COMP | 2020-03-20 | COMP | 2020-03-26 | COMP | 2020-04-15 | COMP | Rule 16 | 84 | 100 | 53 | 25 | 5 | 15 | 277
13349 | 2019-03-12 | 2019-07-22 | 2019-09-14 | 2019-09-14 | COMP | 2019-12-11 | COMP | 2020-04-20 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | Other | 93 | 39 | 60 | 90 | 51 | 1 | 330
13422 | 2019-03-12 | 2019-07-24 | 2019-08-26 | 2019-08-26 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2021-01-19 | COMP | 2021-02-04 | COMP | Rule 16 | 95 | 24 | 40 | 1 | 312 | 13 | 480
13496 | 2019-03-12 | 2019-07-29 | 2020-01-06 | 2020-04-06 | COMP | 2020-06-12 | COMP | 2020-12-14 | COMP | 2021-03-30 | COMP | 2021-04-13 | COMP | Rule 16 | 98 | 110 | 49 | 128 | 73 | 11 | 527
13942 | 2019-03-12 | 2019-08-17 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-04 | COMP | 2020-06-02 | COMP | 2020-06-04 | COMP | 2020-06-18 | COMP | Rule 16 | 112 | 30 | 5 | 165 | 3 | 11 | 322
14412 | 2019-03-12 | 2019-09-09 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-17 | COMP | 2021-11-09 | COMP | 2021-11-22 | COMP | 2021-12-17 | COMP | Rule 16 | 127 | 52 | 18 | 480 | 9 | 18 | 699
14612 | 2019-03-12 | 2019-09-18 | 2020-02-11 | 2020-02-11 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-03-04 | COMP | 2020-09-24 | COMP | Rule 15/16 | 134 | 99 | 12 | 1 | 5 | 145 | 391
14988 | 2019-03-12 | 2019-10-08 | 2019-11-14 | 2019-11-14 | COMP | 2019-12-02 | COMP | 2020-01-26 | COMP | 2020-04-20 | COMP | 2020-06-12 | COMP | Rule 16 | 148 | 27 | 11 | 37 | 60 | 39 | 318
16679 | 2019-03-12 | 2020-01-11 | 2020-05-21 | 2020-05-21 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2021-08-24 | COMP | 2021-09-15 | COMP | Rule 16 | 211 | 92 | 60 | 1 | 259 | 16 | 635
17091 | 2019-03-12 | 2020-01-30 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-13 | COMP | 2020-09-09 | COMP | 2020-07-02 | COMP | 2020-10-07 | COMP | Rule 16 | 224 | 68 | 7 | 84 | 0 | 21 | 400
17734 | 2019-03-12 | 2020-02-25 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-05-04 | COMP | 2020-05-29 | COMP | Rule 16 | 241 | 43 | 21 | 1 | 0 | 6 | 308
4207 | 2019-03-13 | 2019-07-18 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-30 | COMP | 2020-02-18 | COMP | 2020-04-01 | COMP | 2020-09-14 | COMP | Rule 16 | 90 | 103 | 11 | 34 | 32 | 117 | 382
10557 | 2019-03-13 | 2019-03-20 | 2019-08-30 | 2019-08-30 | COMP | 2020-01-07 | COMP | 2020-02-27 | COMP | 2020-02-28 | COMP | 2020-05-15 | COMP | Rule 15/16 | 6 | 116 | 87 | 36 | 2 | 56 | 298
10851 | 2019-03-13 | 2019-04-02 | 2019-05-21 | 2019-05-21 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-09-06 | COMP | 2020-02-27 | COMP | Rule 16 | 15 | 36 | 77 | 1 | 0 | 117 | 242
10899 | 2019-03-13 | 2019-04-04 | 2019-06-07 | 2019-06-11 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2019-08-07 | COMP | 2019-07-11 | COMP | Rule 16 | 17 | 46 | 260 | 1 | 0 |  | 85
11025 | 2019-03-13 | 2019-04-10 | 2019-08-06 | 2019-08-06 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | 2020-11-10 | COMP | 2021-01-04 | COMP | Other | 21 | 83 | 282 | 1 | 40 | 35 | 457
11039 | 2019-03-13 | 2019-04-10 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-12-03 | COMP | 2019-12-23 | COMP | Rule 15/16 | 21 | 108 | 37 | 1 | 21 | 15 | 198
11280 | 2019-03-13 | 2019-04-22 | 2019-08-02 | 2019-08-02 | COMP | 2020-01-17 | COMP | 2020-02-03 | COMP | 2020-01-28 | COMP | 2020-03-11 | COMP | Rule 16 | 29 | 73 | 115 | 11 | 0 | 27 | 251
11349 | 2019-03-13 | 2019-04-23 | 2021-02-18 | 2021-02-18 | COMP | 2021-08-12 | COMP | 2021-10-14 | COMP | 2022-02-08 | COMP | 2022-03-23 | COMP | Rule 16 | 30 | 459 | 124 | 45 | 80 | 31 | 764
11510 | 2019-03-13 | 2019-04-30 | 2019-05-29 | 2019-05-29 | COMP | 2020-03-20 | COMP | 2020-03-22 | COMP | 2020-07-31 | COMP | 2020-08-11 | COMP | Rule 16 | 35 | 21 | 204 | 1 | 94 | 8 | 359
11631 | 2019-03-13 | 2019-05-06 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-10-03 | COMP | 2019-10-04 | COMP | Rule 16 | 39 | 60 | 9 | 1 | 39 | 2 | 145
11947 | 2019-03-13 | 2019-05-17 | 2019-10-18 | 2019-10-28 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-01-22 | COMP | 2020-02-10 | COMP | Rule 16 | 48 | 108 | 19 | 1 | 39 | 14 | 230
12065 | 2019-03-13 | 2019-05-21 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-15 | COMP | 2019-08-26 | COMP | 2020-02-29 | INPR | 2019-11-13 | COMP | Rule 16 | 50 | 34 | 5 | 31 |  |  | 172
12172 | 2019-03-13 | 2019-05-28 | 2019-09-07 | 2020-03-07 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-03 | COMP | 2020-07-07 | COMP | Rule 15/16 | 54 | 72 | 41 | 1 | 22 | 25 | 334
12173 | 2019-03-13 | 2019-05-28 | 2019-06-27 | 2019-06-27 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-11-12 | COMP | 2019-11-13 | COMP | Rule 16 | 54 | 23 | 79 | 1 | 18 | 2 | 172
12401 | 2019-03-13 | 2019-06-04 | 2019-11-08 | 2020-02-18 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | 2020-03-04 | COMP | 2020-04-01 | COMP | Rule 16 | 59 | 112 | 5 | 1 | 8 | 21 | 266
12733 | 2019-03-13 | 2019-06-21 | 2019-09-12 | 2019-09-12 | COMP | 2019-09-26 | COMP | 2019-10-02 | COMP | 2019-09-27 | COMP | 2019-11-25 | COMP | Rule 16 | 72 | 58 | 11 | 5 | 0 | 38 | 180
12808 | 2019-03-13 | 2019-06-25 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2019-10-03 | COMP | 2019-10-26 | COMP | Rule 16 | 74 | 13 | 6 | 1 | 54 | 17 | 160
13978 | 2019-03-13 | 2019-08-19 | 2019-08-31 | 2019-08-31 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-10-31 | COMP | 2019-12-18 | COMP | Rule 15/16 | 112 | 10 | 44 | 1 | 0 | 31 | 195
14625 | 2019-03-13 | 2019-09-19 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-01-09 | COMP | 2020-01-15 | COMP | Rule 16 | 134 | 44 | 20 | 1 | 14 | 5 | 213
15194 | 2019-03-13 | 2019-10-18 | 2020-02-05 | 2020-09-17 | COMP | 2021-01-29 | COMP | 2021-03-03 | COMP | 2021-02-10 | COMP | 2021-04-23 | COMP | Rule 15/16 | 155 | 73 | 91 | 23 | 0 | 38 | 534
15520 | 2019-03-13 | 2019-11-05 | 2020-02-05 | 2020-02-05 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2021-05-27 | COMP | 2021-06-24 | COMP | Rule 16 | 167 | 61 | 146 | 1 | 187 | 20 | 577
15768 | 2019-03-13 | 2019-11-20 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-03 | COMP | 2020-05-01 | COMP | 2020-10-21 | COMP | 2020-12-03 | COMP | Rule 15/16 | 177 | 78 | 15 | 21 | 122 | 29 | 437
15845 | 2019-03-13 | 2019-11-24 | 2020-06-13 | 2020-06-13 | COMP | 2020-08-20 | COMP | 2020-10-22 | COMP | 2020-12-22 | COMP | 2021-02-01 | COMP | Rule 16 | 179 | 138 | 49 | 45 | 41 | 27 | 476
16248 | 2019-03-13 | 2019-12-17 | 2020-03-30 | 2020-03-30 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-08-24 | COMP | Rule 15/16 | 194 | 71 | 74 | 1 | 1 | 32 | 368
16458 | 2019-03-13 | 2020-01-02 | 2020-08-16 | 2021-03-01 | COMP | 2021-03-15 | COMP | 2021-03-15 | COMP | 2022-01-28 | COMP | 2022-03-02 | COMP | Rule 16 | 204 | 159 | 11 | 1 | 223 | 23 | 749
17099 | 2019-03-13 | 2020-01-30 | 2020-02-25 | 2020-02-25 | COMP | 2020-04-30 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-11 | COMP | Rule 16 | 223 | 18 | 48 | 3 | 1 | 28 | 316
17366 | 2019-03-13 | 2020-02-11 | 2020-03-30 | 2021-03-23 | COMP | 2021-05-07 | COMP | 2020-08-28 | COMP | 2023-07-01 | INPR | 2021-09-02 | COMP | Rule 16 | 231 | 34 | 34 |  |  |  | 626
17431 | 2019-03-13 | 2020-02-13 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-29 | COMP | 2020-06-26 | COMP | 2020-09-22 | COMP | 2020-10-22 | COMP | Rule 16 | 233 | 64 | 12 | 21 | 62 | 23 | 410
17546 | 2019-03-13 | 2020-02-19 | 2020-04-21 | 2020-04-21 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-06-24 | COMP | 2020-08-10 | COMP | Rule 16 | 236 | 45 | 44 | 1 | 3 | 34 | 358
19038 | 2019-03-13 | 2020-04-20 | 2020-08-13 | 2020-08-13 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2021-03-01 | COMP | 2021-08-13 | COMP | Rule 15/16 | 279 | 83 | 28 | 1 | 108 | 118 | 612
21397 | 2019-03-13 | 2020-08-05 | 2020-10-13 | 2020-10-13 | COMP | 2020-11-12 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2020-12-11 | COMP | Other | 355 | 49 | 22 | 4 | 1 | 17 | 443
26224 | 2019-03-13 | 2021-03-12 | 2021-05-10 | 2021-05-10 | COMP | 2021-06-07 | COMP | 2021-07-07 | COMP | 2021-07-14 | COMP | 2021-09-07 | COMP | Rule 16 | 504 | 42 | 20 | 22 | 6 | 39 | 628
10512 | 2019-03-14 | 2019-03-19 | 2019-09-28 | 2019-09-28 | COMP | 2019-10-18 | COMP | 2020-01-27 | COMP | 2020-02-14 | COMP | 2020-03-31 | COMP | Rule 16 | 4 | 136 | 15 | 66 | 15 | 32 | 264
10673 | 2019-03-14 | 2019-03-25 | 2019-03-30 | 2019-03-30 | COMP | 2019-04-17 | COMP | 2019-05-21 | INPR | 2019-05-21 | COMP | 2019-05-24 | COMP | Rule 16 | 8 | 5 | 13 |  |  |  | 52
10679 | 2019-03-14 | 2019-03-25 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-31 | COMP | 2020-09-14 | COMP | 2020-09-10 | COMP | 2020-10-28 | COMP | Rule 15/16 | 8 | 195 | 22 | 159 | 0 | 33 | 413
10808 | 2019-03-14 | 2019-03-30 | 2019-04-18 | 2019-04-18 | COMP | 2019-05-07 | COMP | 2019-05-07 | INPR | 2019-11-06 | COMP | 2019-11-08 | COMP | Rule 16 | 12 | 14 | 14 |  |  |  | 169
10960 | 2019-03-14 | 2019-04-06 | 2019-05-18 | 2019-05-18 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-02-07 | COMP | 2020-02-27 | COMP | Rule 15/16 | 17 | 30 | 167 | 1 | 15 | 14 | 241
11013 | 2019-03-14 | 2019-04-09 | 2019-07-28 | 2019-07-28 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-09-23 | COMP | 2019-10-29 | COMP | Rule 16 | 19 | 77 | 12 | 1 | 29 | 27 | 161
11023 | 2019-03-14 | 2019-04-09 | 2019-12-20 | 2020-10-20 | COMP | 2020-11-04 | COMP | 2020-11-04 | COMP | 2021-01-20 | COMP | 2021-01-22 | COMP | Rule 15/16 | 19 | 178 | 12 | 1 | 50 | 3 | 469
11165 | 2019-03-14 | 2019-04-16 | 2020-04-01 | 2020-04-01 | COMP | 2020-08-24 | COMP | 2020-10-23 | COMP | 2020-11-16 | COMP | 2021-01-22 | COMP | Rule 15/16 | 24 | 242 | 103 | 44 | 16 | 45 | 469
11286 | 2019-03-14 | 2019-04-22 | 2020-02-20 | 2020-02-20 | COMP | 2020-06-26 | COMP | 2021-03-09 | COMP | 2021-03-09 | COMP | 2021-05-06 | COMP | Rule 15/16 | 28 | 209 | 91 | 175 | 1 | 43 | 542
11868 | 2019-03-14 | 2019-05-15 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-12 | COMP | 2019-10-15 | COMP | 2020-01-21 | COMP | 2020-01-24 | COMP | Rule 16 | 45 | 70 | 15 | 24 | 65 | 4 | 218
12063 | 2019-03-14 | 2019-05-21 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2019-09-25 | COMP | 2019-11-23 | COMP | Rule 16 | 49 | 54 | 25 | 1 | 12 | 42 | 178
12304 | 2019-03-14 | 2019-05-30 | 2019-08-05 | 2019-08-05 | COMP | 2020-02-14 | COMP | 2020-06-29 | COMP | 2020-09-23 | COMP | 2020-10-29 | COMP | Rule 16 | 55 | 47 | 133 | 95 | 62 | 27 | 414
12306 | 2019-03-14 | 2019-05-30 | 2019-08-05 | 2020-11-23 | COMP | 2021-02-02 | COMP | 2021-02-09 | COMP | 2020-09-23 | COMP | 2021-03-16 | COMP | Rule 15/16 | 55 | 47 | 47 | 6 | 0 | 25 | 505
12346 | 2019-03-14 | 2019-06-03 | 2019-10-08 | 2019-10-08 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-09-22 | COMP | 2020-12-18 | COMP | Rule 16 | 57 | 90 | 30 | 1 | 213 | 61 | 447
12427 | 2019-03-14 | 2019-06-05 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-13 | COMP | 2019-08-23 | COMP | 2019-08-28 | COMP | 2019-09-26 | COMP | Rule 16 | 59 | 44 | 6 | 9 | 4 | 21 | 138
12478 | 2019-03-14 | 2019-06-11 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-10-21 | INPR | 2019-07-04 | COMP | Rule 16 | 63 | 12 | 4 | 1 |  |  | 79
12518 | 2019-03-14 | 2019-06-10 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-08-13 | COMP | 2019-09-04 | COMP | Rule 16 | 62 | 23 | 13 | 1 | 12 | 16 | 122
12795 | 2019-03-14 | 2019-06-24 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-06 | COMP | 2019-08-27 | COMP | 2020-01-19 | INPR | 2019-10-02 | COMP | Rule 16 | 72 | 33 | 21 |  |  |  | 142
12886 | 2019-03-14 | 2019-06-27 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-05 | COMP | 2019-11-06 | COMP | 2019-11-13 | COMP | 2020-01-23 | COMP | Other | 75 | 78 | 15 | 2 | 5 | 47 | 217
12903 | 2019-03-14 | 2019-06-28 | 2019-11-18 | 2019-11-18 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2019-12-12 | COMP | 2020-03-12 | COMP | Rule 16 | 76 | 99 | 14 | 1 | 4 | 62 | 251
13013 | 2019-03-14 | 2019-07-05 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-01-06 | COMP | 2020-02-27 | COMP | Rule 16 | 80 | 41 | 7 | 1 | 80 | 37 | 241
13035 | 2019-03-14 | 2019-07-09 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-09 | COMP | 2020-01-24 | COMP | 2020-01-28 | COMP | 2020-02-15 | COMP | Rule 16 | 82 | 95 | 12 | 32 | 3 | 14 | 233
13243 | 2019-03-14 | 2019-07-17 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2021-05-27 | COMP | 2021-07-01 | COMP | Rule 16 | 88 | 53 | 23 | 1 | 396 | 25 | 581
13283 | 2019-03-14 | 2019-07-19 | 2019-12-23 | 2019-12-23 | COMP | 2020-03-30 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2020-12-03 | COMP | Rule 16 | 90 | 108 | 67 | 147 | 1 | 28 | 436
13326 | 2019-03-14 | 2019-07-19 | 2020-01-02 | 2020-01-02 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-06-30 | COMP | 2020-07-31 | COMP | Rule 16 | 90 | 114 | 22 | 1 | 105 | 24 | 351
13397 | 2019-03-14 | 2019-07-24 | 2019-10-12 | 2019-11-05 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2019-12-10 | COMP | 2019-12-31 | COMP | Rule 15/16 | 93 | 57 | 18 | 1 | 6 | 15 | 202
14227 | 2019-03-14 | 2019-08-29 | 2020-01-09 | 2020-03-10 | COMP | 2020-03-23 | COMP | 2020-03-26 | COMP | 2020-04-06 | COMP | 2020-07-15 | COMP | Rule 16 | 119 | 90 | 10 | 4 | 8 | 72 | 339
15258 | 2019-03-14 | 2019-10-23 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-26 | COMP | 2019-12-26 | COMP | 2020-03-10 | COMP | 2020-03-30 | COMP | Rule 16 | 157 | 35 | 9 | 1 | 51 | 15 | 263
15758 | 2019-03-14 | 2019-11-20 | 2020-02-24 | 2020-03-02 | COMP | 2020-06-16 | COMP | 2020-08-24 | COMP | 2020-08-03 | COMP | 2020-10-05 | COMP | Rule 15/16 | 176 | 63 | 76 | 50 | 0 | 30 | 396
15789 | 2019-03-14 | 2019-11-20 | 2020-05-12 | 2020-05-12 | COMP | 2021-06-14 | COMP | 2023-03-29 | COMP |  | INPR | 2023-09-06 | COMP | Rule 16 | 176 | 119 | 275 | 450 |  |  | 1128
16692 | 2019-03-14 | 2020-01-13 | 2020-02-14 | 2021-02-19 | COMP | 2021-03-09 | COMP | 2021-04-02 | COMP | 2021-04-02 | COMP | 2021-04-23 | COMP | Rule 16 | 210 | 24 | 13 | 19 | 1 | 16 | 533
10488 | 2019-03-15 | 2019-03-18 | 2019-05-16 | 2019-08-07 | COMP | 2019-08-07 | NOTN | 2019-08-12 | COMP | 2019-06-19 | COMP | 2019-09-30 | COMP | Other | 2 | 44 |  | 4 | 0 | 35 | 139
10496 | 2019-03-15 | 2019-03-18 | 2019-03-29 | 2019-03-29 | COMP | 2019-04-08 | COMP | 2019-06-07 | COMP | 2019-06-25 | COMP | 2019-06-27 | COMP | Rule 15/16 | 2 | 10 | 7 | 44 | 13 | 3 | 74
10545 | 2019-03-15 | 2019-03-19 | 2020-03-20 | 2020-03-20 | COMP | 2020-04-24 | COMP | 2020-07-14 | COMP | 2020-07-22 | COMP | 2021-01-04 | COMP | Rule 15/16 | 3 | 254 | 26 | 57 | 7 | 113 | 455
10655 | 2019-03-15 | 2019-03-25 | 2019-05-17 | 2019-05-17 | COMP | 2019-05-24 | COMP | 2019-06-12 | COMP | 2019-06-21 | COMP | 2019-07-23 | COMP | Rule 15 | 7 | 40 | 6 | 13 | 8 | 22 | 91
10865 | 2019-03-15 | 2019-04-02 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-08-29 | COMP | 2019-10-15 | COMP | Rule 16 | 13 | 63 | 37 | 1 | 8 | 33 | 150
10972 | 2019-03-15 | 2019-04-06 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-10-08 | COMP | 2019-12-09 | COMP | Rule 15/16 | 16 | 52 | 11 | 1 | 68 | 42 | 186
11055 | 2019-03-15 | 2019-04-10 | 2019-04-29 | 2019-04-29 | COMP | 2019-06-10 | COMP | 2019-08-23 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | Rule 15/16 | 19 | 14 | 30 | 54 | 41 | 2 | 155
11072 | 2019-03-15 | 2019-04-11 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-12 | NOTN | 2019-07-12 | COMP | 2019-08-13 | COMP | 2019-08-16 | COMP | Other | 20 | 63 |  | 3 | 23 | 4 | 109
11101 | 2019-03-15 | 2019-04-12 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-09 | COMP | 2019-08-23 | COMP | 2020-09-18 | COMP | 2020-10-28 | COMP | Rule 16 | 21 | 72 | 13 | 11 | 271 | 29 | 412
11107 | 2019-03-15 | 2019-04-12 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-12 | COMP | 2019-10-01 | COMP | 2023-07-01 | INPR | 2019-12-05 | COMP | Rule 16 | 21 | 70 | 16 | 36 |  |  | 184
11134 | 2019-03-15 | 2019-04-15 | 2019-10-22 | 2019-10-22 | COMP | 2020-02-07 | COMP | 2020-02-20 | COMP | 2020-03-24 | COMP | 2020-04-10 | COMP | Rule 15/16 | 22 | 134 | 73 | 9 | 24 | 14 | 271
11189 | 2019-03-15 | 2019-04-17 | 2019-05-24 | 2019-05-30 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-08-08 | COMP | 2019-08-26 | COMP | Rule 16 | 24 | 28 | 25 | 1 | 26 | 13 | 115
11464 | 2019-03-15 | 2019-04-29 | 2019-08-28 | 2019-08-28 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-10-20 | COMP | 2020-11-10 | COMP | Rule 15/16 | 32 | 86 | 88 | 1 | 203 | 16 | 421
11515 | 2019-03-15 | 2019-04-30 | 2019-08-28 | 2019-08-28 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2021-09-04 | COMP | 2021-10-05 | COMP | Rule 15/16 | 33 | 85 | 88 | 1 | 422 | 21 | 646
11663 | 2019-03-15 | 2019-05-07 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2020-04-26 | INPR | 2020-01-06 | COMP | Rule 16 | 38 | 89 | 17 | 1 |  |  | 204
12101 | 2019-03-15 | 2019-05-23 | 2019-09-14 | 2022-05-10 | COMP | 2022-06-06 | COMP | 2023-04-27 | COMP | 2022-11-15 | COMP | 2023-07-05 | COMP | Rule 15/16 | 50 | 79 | 19 | 224 | 0 | 47 | 1083
12466 | 2019-03-15 | 2019-06-07 | 2019-09-18 | 2019-09-18 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-05-29 | COMP | 2020-10-13 | COMP | Rule 16 | 60 | 72 | 61 | 1 | 115 | 97 | 401
12847 | 2019-03-15 | 2019-06-25 | 2019-07-18 | 2019-07-18 | COMP | 2019-11-06 | COMP | 2019-12-09 | COMP | 2019-11-12 | COMP | 2019-12-16 | COMP | Rule 16 | 72 | 17 | 79 | 21 | 0 | 6 | 191
13700 | 2019-03-15 | 2019-08-06 | 2019-10-28 | 2019-10-28 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2022-01-30 | INPR | 2020-12-14 | COMP | Rule 16 | 101 | 59 | 57 | 1 |  |  | 442
14228 | 2019-03-15 | 2019-08-29 | 2020-01-15 | 2020-03-10 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-04-03 | COMP | 2020-07-15 | COMP | Rule 16 | 118 | 94 | 7 | 1 | 13 | 73 | 338
14332 | 2019-03-15 | 2019-09-04 | 2019-12-20 | 2019-12-20 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-07-19 | COMP | 2020-10-22 | COMP | Rule 16 | 121 | 75 | 126 | 1 | 21 | 68 | 408
14443 | 2019-03-15 | 2019-09-10 | 2019-12-20 | 2019-12-20 | COMP | 2020-08-04 | COMP | 2020-11-23 | COMP | 2020-12-23 | COMP | 2021-03-20 | COMP | Rule 15/16 | 125 | 71 | 158 | 78 | 21 | 59 | 507
15286 | 2019-03-15 | 2019-10-24 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-20 | COMP | 2022-09-15 | COMP | 2022-08-29 | COMP | 2022-10-03 | COMP | Rule 16 | 157 | 158 | 28 | 544 | 0 | 13 | 896
15603 | 2019-03-15 | 2019-11-08 | 2020-03-22 | 2020-04-05 | COMP | 2020-07-28 | COMP | 2021-08-16 | COMP | 2021-12-21 | COMP | 2021-12-30 | COMP | Rule 15/16 | 168 | 89 | 81 | 265 | 88 | 8 | 705
17584 | 2019-03-15 | 2020-02-21 | 2020-06-08 | 2020-06-08 | COMP | 2020-09-03 | COMP | 2020-09-13 | COMP | 2020-11-17 | COMP | 2021-01-11 | COMP | Rule 16 | 236 | 76 | 64 | 6 | 46 | 36 | 460
19515 | 2019-03-15 | 2020-05-11 | 2021-09-02 | 2022-04-01 | COMP | 2022-04-20 | COMP | 2022-11-21 | COMP |  | INPR | 2023-12-20 | COMP | Rule 15/16 | 292 | 333 | 14 | 149 |  |  | 1199
20081 | 2019-03-15 | 2020-06-04 | 2020-08-07 | 2020-08-07 | COMP | 2020-09-18 | NOTN | 2021-12-14 | COMP | 2021-12-15 | COMP | 2022-04-30 | COMP | Other | 309 | 47 |  | 339 | 2 | 96 | 789
21570 | 2019-03-15 | 2020-08-13 | 2020-09-11 | 2020-09-11 | COMP | 2020-11-09 | COMP | 2020-11-09 | INPR | 2022-07-16 | REQD | 2021-01-26 | COMP | Rule 16 | 359 | 21 | 42 |  |  |  | 470
11507 | 2019-03-16 | 2019-04-30 | 2019-09-04 | 2019-09-04 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-01-07 | COMP | 2020-02-05 | COMP | Rule 16 | 32 | 89 | 57 | 1 | 29 | 21 | 224
11981 | 2019-03-16 | 2019-05-20 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-09-27 | COMP | 2019-10-02 | COMP | Rule 16 | 46 | 41 | 4 | 1 | 49 | 4 | 140
14585 | 2019-03-16 | 2019-09-17 | 2021-08-16 | 2021-08-16 | COMP | 2021-09-14 | COMP | 2021-11-12 | COMP | 2021-12-21 | COMP | 2022-02-04 | COMP | Rule 15/16 | 129 | 482 | 21 | 43 | 26 | 33 | 729
10549 | 2019-03-17 | 2019-03-20 | 2019-06-20 | 2019-08-03 | COMP | 2019-06-25 | NOTN | 2020-01-08 | COMP | 2020-01-06 | COMP | 2020-01-29 | COMP | Other | 3 | 66 |  | 107 | 0 | 15 | 219
10884 | 2019-03-17 | 2019-04-03 | 2019-05-29 | 2019-05-29 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2020-03-17 | COMP | 2020-03-24 | COMP | Rule 15/16 | 13 | 40 | 110 | 1 | 92 | 6 | 257
10514 | 2019-03-18 | 2019-03-19 | 2019-04-06 | 2019-04-06 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-10-21 | INPR | 2019-06-14 | COMP | Rule 16 | 2 | 14 | 25 | 1 |  |  | 64
11035 | 2019-03-18 | 2019-04-10 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2019-10-21 | COMP | 2019-11-19 | COMP | Rule 16 | 18 | 104 | 9 | 1 | 25 | 21 | 173
11121 | 2019-03-18 | 2019-04-13 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-07-24 | COMP | 2019-08-09 | COMP | Rule 16 | 20 | 54 | 2 | 1 | 17 | 13 | 103
11195 | 2019-03-18 | 2019-04-17 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-13 | COMP | 2019-09-26 | COMP | 2019-10-14 | COMP | 2019-10-03 | COMP | Rule 16 | 23 | 81 | 3 | 32 | 13 |  | 141
11227 | 2019-03-18 | 2019-04-17 | 2019-05-15 | 2019-05-15 | COMP | 2019-06-07 | COMP | 2019-06-07 | COMP | 2019-11-15 | COMP | 2020-02-06 | COMP | Rule 16 | 23 | 21 | 17 | 1 | 113 | 55 | 225
11248 | 2019-03-18 | 2019-04-19 | 2019-10-12 | 2019-10-16 | COMP | 2019-10-30 | COMP | 2019-11-22 | COMP | 2019-12-31 | COMP | 2020-01-06 | COMP | Rule 16 | 25 | 123 | 11 | 17 | 25 | 4 | 203
11345 | 2019-03-18 | 2019-04-26 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2019-09-05 | COMP | 2019-09-13 | COMP | Rule 16 | 30 | 73 | 8 | 1 | 13 | 7 | 127
11381 | 2019-03-18 | 2019-04-24 | 2019-07-30 | 2019-07-30 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-09-25 | COMP | 2019-11-14 | COMP | Rule 16 | 28 | 68 | 39 | 1 | 3 | 36 | 170
11462 | 2019-03-18 | 2019-04-29 | 2019-07-19 | 2019-07-19 | COMP | 2019-07-29 | COMP | 2019-09-20 | COMP | 2019-08-28 | COMP | 2019-11-19 | COMP | Rule 16 | 31 | 58 | 7 | 39 | 0 | 42 | 173
11467 | 2019-03-18 | 2019-04-29 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-29 | COMP | 2019-10-11 | COMP | 2020-06-26 | COMP | 2020-07-15 | COMP | Rule 16 | 31 | 71 | 17 | 31 | 178 | 14 | 337
11470 | 2019-03-18 | 2019-04-29 | 2019-08-08 | 2019-08-08 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-01-08 | COMP | 2020-01-28 | COMP | Rule 16 | 31 | 72 | 81 | 1 | 24 | 14 | 218
11759 | 2019-03-18 | 2019-05-09 | 2019-11-20 | 2020-06-18 | COMP | 2020-08-04 | NOTN | 2020-08-04 | COMP | 2020-08-18 | COMP | 2020-11-02 | COMP | Other | 39 | 136 |  | 34 | 11 | 54 | 414
11768 | 2019-03-18 | 2019-05-10 | 2019-10-18 | 2019-10-18 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2020-03-17 | COMP | 2020-04-03 | COMP | Rule 16 | 40 | 113 | 44 | 1 | 58 | 14 | 265
11894 | 2019-03-18 | 2019-05-15 | 2019-08-01 | 2019-08-01 | COMP | 2019-09-25 | COMP | 2019-09-13 | COMP | 2019-12-10 | COMP | 2020-02-03 | COMP | Rule 16 | 43 | 55 | 39 |  | 60 | 37 | 222
11912 | 2019-03-18 | 2019-05-16 | 2019-07-29 | 2019-07-29 | COMP | 2019-10-16 | COMP | 2019-11-27 | COMP | 2020-05-31 | INPR | 2019-12-02 | COMP | Rule 16 | 44 | 51 | 57 | 30 |  |  | 180
12021 | 2019-03-18 | 2019-05-21 | 2019-11-03 | 2019-11-03 | COMP | 2020-01-10 | COMP | 2020-08-06 | COMP | 2020-12-08 | COMP | 2021-01-25 | COMP | Rule 16 | 47 | 116 | 45 | 147 | 85 | 32 | 468
12287 | 2019-03-18 | 2019-05-30 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2021-03-26 | COMP | 2021-04-26 | COMP | Rule 16 | 53 | 46 | 9 | 1 | 406 | 22 | 532
12503 | 2019-03-18 | 2019-06-10 | 2019-08-22 | 2019-08-22 | COMP | 2021-05-30 | INPR | 2019-08-30 | COMP | 2019-08-30 | COMP | 2019-09-03 | COMP | Rule 16 | 60 | 53 |  | 7 | 1 | 2 | 119
13121 | 2019-03-18 | 2019-07-11 | 2019-10-05 | 2019-11-28 | COMP | 2020-01-21 | COMP | 2020-01-22 | COMP | 2020-03-10 | COMP | 2020-03-27 | COMP | Rule 16 | 82 | 61 | 34 | 2 | 34 | 14 | 260
13359 | 2019-03-18 | 2019-07-23 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2019-12-31 | COMP | 2020-02-06 | COMP | Rule 16 | 90 | 77 | 22 | 1 | 14 | 26 | 225
13624 | 2019-03-18 | 2019-08-02 | 2020-01-10 | 2020-01-10 | COMP | 2020-02-26 | COMP | 2020-04-02 | COMP | 2021-10-23 | INPR | 2020-05-22 | COMP | Rule 16 | 98 | 110 | 32 | 27 |  |  | 300
13740 | 2019-03-18 | 2019-08-07 | 2019-10-05 | 2019-10-05 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2019-11-12 | COMP | 2019-12-23 | COMP | Rule 16 | 101 | 42 | 23 | 1 | 4 | 28 | 195
13806 | 2019-03-18 | 2019-08-12 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-25 | COMP | 2020-03-10 | COMP | 2020-12-08 | COMP | 2021-01-09 | COMP | Rule 16 | 104 | 115 | 20 | 11 | 191 | 22 | 458
14240 | 2019-03-18 | 2019-08-31 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2020-01-19 | INPR | 2019-09-21 | COMP | Rule 16 | 118 | 5 | 7 | 1 |  |  | 132
14313 | 2019-03-18 | 2019-09-04 | 2019-10-20 | 2019-10-20 | COMP | 2019-10-31 | COMP | 2019-11-25 | COMP | 2019-12-11 | COMP | 2020-01-08 | COMP | Rule 16 | 120 | 33 | 9 | 17 | 11 | 19 | 205
14318 | 2019-03-18 | 2019-09-04 | 2019-12-05 | 2019-12-05 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2021-03-09 | COMP | 2021-03-17 | COMP | Other | 120 | 64 | 193 | 1 | 124 | 7 | 504
14500 | 2019-03-18 | 2019-09-12 | 2019-09-27 | 2019-09-27 | COMP | 2019-10-08 | COMP | 2019-10-08 | INPR | 2020-01-19 | REQD | 2019-10-10 | COMP | Rule 16 | 126 | 12 | 8 |  |  |  | 146
14551 | 2019-03-18 | 2019-09-16 | 2019-11-18 | 2021-01-19 | COMP | 2021-02-02 | COMP | 2021-02-02 | COMP | 2021-02-12 | COMP | 2021-02-21 | COMP | Rule 16 | 128 | 45 | 11 | 1 | 9 | 5 | 486
17882 | 2019-03-18 | 2020-03-02 | 2020-05-15 | 2020-05-15 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-08-11 | COMP | Rule 16 | 241 | 55 | 46 | 1 | 1 | 17 | 356
11024 | 2019-03-19 | 2019-04-09 | 2019-10-18 | 2019-10-18 | COMP | 2020-02-14 | COMP | 2019-12-06 | COMP | 2019-12-02 | COMP | 2020-01-02 | COMP | Rule 15/16 | 16 | 136 | 80 |  | 0 | 18 | 200
11201 | 2019-03-19 | 2019-04-17 | 2019-07-25 | 2019-08-29 | COMP | 2019-08-30 | NOTN | 2019-08-30 | COMP | 2019-07-25 | NOTN | 2019-10-07 | COMP | Other | 22 | 70 |  | 2 |  |  | 142
11224 | 2019-03-19 | 2019-04-19 | 2019-06-17 | 2019-06-17 | COMP | 2019-06-21 | COMP | 2019-08-28 | COMP | 2019-07-24 | COMP | 2019-12-13 | COMP | Rule 16 | 24 | 41 | 5 | 48 | 0 | 74 | 188
11396 | 2019-03-19 | 2019-04-24 | 2019-08-15 | 2019-08-15 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-11-05 | COMP | 2019-12-13 | COMP | Rule 16 | 27 | 80 | 57 | 1 | 2 | 26 | 188
11815 | 2019-03-19 | 2019-05-13 | 2019-09-15 | 2019-09-15 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-06-04 | COMP | 2020-08-07 | COMP | Rule 16 | 40 | 87 | 24 | 1 | 158 | 47 | 353
11854 | 2019-03-19 | 2019-05-14 | 2019-09-03 | 2019-09-03 | COMP | 2019-10-18 | COMP | 2020-01-28 | COMP | 2020-02-14 | COMP | 2020-05-13 | COMP | Rule 16 | 41 | 78 | 34 | 67 | 14 | 63 | 292
11864 | 2019-03-19 | 2019-05-15 | 2019-07-19 | 2019-07-19 | COMP | 2019-07-22 | NOTN | 2019-07-25 | COMP | 2019-09-03 | COMP | 2019-10-01 | COMP | Other | 42 | 46 |  | 5 | 28 | 21 | 138
12428 | 2019-03-19 | 2019-06-05 | 2019-08-15 | 2019-10-29 | COMP | 2019-08-27 | NOTN | 2019-12-09 | COMP | 2019-08-27 | COMP | 2019-12-30 | COMP | Other | 56 | 51 |  | 27 | 0 | 15 | 198
12629 | 2019-03-19 | 2019-06-17 | 2019-08-14 | 2019-09-16 | COMP | 2019-10-24 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-06-15 | COMP | Rule 16 | 64 | 42 | 29 | 52 | 1 | 109 | 314
12977 | 2019-03-19 | 2019-07-03 | 2019-10-04 | 2019-10-04 | COMP | 2020-01-16 | COMP | 2020-11-03 | COMP | 2021-02-01 | COMP | 2021-02-26 | COMP | Rule 16 | 76 | 66 | 70 | 205 | 59 | 19 | 490
13105 | 2019-03-19 | 2019-07-10 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2020-01-14 | COMP | 2020-01-15 | COMP | Rule 16 | 80 | 56 | 9 | 1 | 66 | 2 | 209
13371 | 2019-03-19 | 2019-07-22 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-09-24 | COMP | 2019-09-26 | COMP | Rule 16 | 88 | 16 | 8 | 1 | 24 | 3 | 135
13385 | 2019-03-19 | 2019-07-23 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-16 | COMP | 2020-02-25 | COMP | 2020-03-09 | COMP | 2020-06-11 | COMP | Rule 16 | 89 | 115 | 8 | 27 | 10 | 68 | 312
13633 | 2019-03-19 | 2019-08-02 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-11-21 | COMP | 2019-12-11 | COMP | Rule 16 | 97 | 53 | 25 | 1 | 2 | 13 | 186
14876 | 2019-03-19 | 2019-10-02 | 2020-01-30 | 2020-01-30 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-10-14 | COMP | 2020-11-04 | COMP | Rule 16 | 139 | 81 | 81 | 1 | 102 | 16 | 415
14941 | 2019-03-19 | 2019-10-04 | 2019-11-25 | 2020-03-02 | COMP | 2020-04-13 | COMP | 2020-04-14 | COMP |  |  | 2020-06-09 | COMP | Rule 15/16 | 141 | 36 | 31 | 2 |  |  | 310
14993 | 2019-03-19 | 2019-10-09 | 2020-01-27 | 2020-01-28 | COMP | 2020-01-31 | COMP | 2020-02-18 | COMP | 2020-06-04 | COMP | 2020-07-14 | COMP | Rule 16 | 144 | 73 | 4 | 12 | 77 | 29 | 335
16048 | 2019-03-19 | 2019-12-07 | 2020-04-24 | 2021-04-02 | COMP | 2021-07-29 | COMP | 2021-09-10 | COMP | 2021-09-10 | COMP | 2021-10-15 | COMP | Rule 16 | 183 | 96 | 83 | 31 | 1 | 26 | 652
16383 | 2019-03-19 | 2019-12-23 | 2020-02-28 | 2020-04-10 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP |  |  | 2020-12-02 | COMP | Rule 16 | 194 | 46 | 42 | 1 |  |  | 432
16385 | 2019-03-19 | 2019-12-23 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-17 | COMP | 2020-06-01 | COMP | 2020-10-27 | COMP | 2021-01-12 | COMP | Rule 16 | 194 | 42 | 17 | 54 | 106 | 51 | 459
16386 | 2019-03-19 | 2019-12-23 | 2020-03-22 | 2020-04-04 | COMP | 2020-04-29 | COMP | 2020-06-02 | COMP | 2020-09-24 | COMP | 2020-11-14 | COMP | Rule 16 | 194 | 61 | 18 | 24 | 82 | 36 | 421
16784 | 2019-03-19 | 2020-01-15 | 2020-03-22 | 2020-03-22 | COMP | 2020-05-05 | COMP | 2020-06-17 | COMP | 2020-06-10 | COMP | 2020-08-08 | COMP | Rule 16 | 209 | 46 | 32 | 31 | 0 | 38 | 353
17415 | 2019-03-19 | 2020-02-13 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-19 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-09-21 | COMP | Rule 15/16 | 229 | 66 | 25 | 38 | 1 | 29 | 383
17426 | 2019-03-19 | 2020-02-13 | 2020-06-05 | 2020-06-05 | COMP | 2021-01-05 | COMP | 2020-08-12 | COMP | 2021-02-01 | COMP | 2021-02-02 | COMP | Rule 16 | 229 | 80 | 147 |  | 117 | 2 | 473
17646 | 2019-03-19 | 2020-02-24 | 2020-08-06 | 2020-08-06 | COMP | 2020-09-18 | COMP | 2021-08-25 | COMP | 2022-01-07 | COMP | 2022-02-25 | COMP | Rule 16 | 235 | 118 | 31 | 235 | 94 | 34 | 742
4129 | 2019-03-20 | 2019-03-20 | 2019-07-09 | 2019-07-09 | COMP | 2020-04-06 | COMP | 2020-05-26 | COMP | 2020-09-01 | COMP | 2020-11-02 | COMP | Other | 1 | 78 | 187 | 36 | 71 | 44 | 412
10815 | 2019-03-20 | 2019-04-01 | 2019-04-20 | 2019-04-20 | COMP | 2019-07-22 | COMP | 2019-07-31 | COMP | 2019-12-29 | INPR | 2019-08-02 | COMP | Rule 16 | 9 | 15 | 64 | 8 |  |  | 96
10821 | 2019-03-20 | 2019-04-01 | 2019-04-24 | 2019-04-24 | COMP | 2019-06-19 | COMP | 2019-08-29 | COMP | 2019-12-12 | COMP | 2020-01-06 | COMP | Rule 16 | 9 | 18 | 40 | 51 | 72 | 16 | 201
10928 | 2019-03-20 | 2019-04-04 | 2019-04-10 | 2019-05-28 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-06-10 | COMP | 2019-06-11 | COMP | Rule 16 | 12 | 5 | 3 | 1 | 8 | 2 | 59
10994 | 2019-03-20 | 2019-04-08 | 2019-11-04 | 2019-11-04 | COMP | 2020-07-21 | COMP | 2020-10-02 | COMP | 2023-12-02 | INPR | 2021-01-14 | COMP | Rule 16 | 14 | 148 | 179 | 53 |  |  | 460
11044 | 2019-03-20 | 2019-04-10 | 2019-08-09 | 2019-10-25 | COMP | 2019-11-01 | NOTN | 2019-11-01 | COMP | 2019-09-17 | COMP | 2019-12-06 | COMP | Other | 16 | 86 |  | 6 | 0 | 23 | 182
11068 | 2019-03-20 | 2019-04-12 | 2019-05-13 | 2019-05-13 | COMP | 2019-05-21 | COMP | 2019-06-04 | COMP | 2019-08-19 | COMP | 2019-10-07 | COMP | Rule 16 | 18 | 22 | 7 | 10 | 54 | 35 | 141
11194 | 2019-03-20 | 2019-04-17 | 2019-08-22 | 2019-08-22 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2021-04-05 | COMP | 2021-05-03 | COMP | Rule 16 | 21 | 90 | 277 | 1 | 130 | 21 | 535
11369 | 2019-03-20 | 2019-04-24 | 2019-12-20 | 2019-12-20 | COMP | 2019-12-24 | NOTN | 2020-03-05 | COMP | 2020-03-10 | COMP | 2020-07-17 | COMP | Other | 26 | 167 |  | 51 | 4 | 93 | 337
11508 | 2019-03-20 | 2019-04-30 | 2019-07-17 | 2019-07-17 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-01-07 | COMP | 2020-01-15 | COMP | Rule 16 | 30 | 55 | 89 | 1 | 31 | 7 | 208
11605 | 2019-03-20 | 2019-05-04 | 2019-07-24 | 2019-10-04 | COMP | 2019-10-18 | COMP | 2020-10-06 | COMP | 2020-10-09 | COMP | 2020-11-10 | COMP | Rule 16 | 33 | 56 | 11 | 244 | 4 | 23 | 418
11608 | 2019-03-20 | 2019-05-04 | 2019-08-02 | 2019-08-02 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-05-06 | COMP | 2020-05-27 | COMP | Rule 16 | 33 | 63 | 182 | 1 | 10 | 15 | 300
11615 | 2019-03-20 | 2019-05-06 | 2019-08-08 | 2019-08-08 | COMP | 2020-01-19 | INPR | 2019-08-26 | COMP | 2019-08-27 | COMP | 2019-09-25 | COMP | Rule 16 | 34 | 67 |  | 13 | 2 | 21 | 133
11628 | 2019-03-20 | 2019-05-06 | 2019-09-06 | 2021-08-23 | COMP | 2021-09-08 | COMP | 2021-10-04 | COMP | 2022-08-10 | COMP | 2022-12-01 | COMP | Rule 16 | 34 | 87 | 12 | 19 | 215 | 78 | 933
11948 | 2019-03-20 | 2019-05-17 | 2019-11-17 | 2020-03-16 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-07-02 | COMP | Rule 16 | 43 | 127 | 36 | 1 | 1 | 43 | 326
11993 | 2019-03-20 | 2019-05-20 | 2019-11-12 | 2019-11-12 | COMP | 2019-11-20 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-02-21 | COMP | Rule 16 | 44 | 123 | 7 | 48 | 1 | 15 | 233
12078 | 2019-03-20 | 2019-05-22 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-25 | COMP | 2019-09-09 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | Rule 16 | 46 | 33 | 13 | 32 | 0 |  | 91
12183 | 2019-03-20 | 2019-05-28 | 2019-08-24 | 2019-08-24 | COMP | 2019-08-29 | COMP | 2019-11-06 | COMP | 2020-01-11 | COMP | 2020-02-26 | COMP | Rule 16 | 49 | 63 | 4 | 49 | 43 | 31 | 236
12343 | 2019-03-20 | 2019-05-31 | 2020-03-25 | 2020-03-25 | COMP | 2020-03-27 | COMP | 2020-04-22 | COMP | 2020-03-25 | COMP | 2020-04-28 | COMP | Rule 16 | 52 | 205 | 3 | 19 | 0 | 5 | 280
12347 | 2019-03-20 | 2019-06-03 | 2019-09-20 | 2019-09-20 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-02-24 | COMP | 2020-06-01 | COMP | Rule 16 | 53 | 78 | 97 | 1 | 9 | 70 | 303
12370 | 2019-03-20 | 2019-06-04 | 2019-09-16 | 2019-09-16 | COMP | 2019-10-31 | COMP | 2019-11-04 | COMP | 2019-11-26 | COMP | 2019-12-30 | COMP | Rule 15/16 | 54 | 73 | 34 | 3 | 16 | 22 | 197
12609 | 2019-03-20 | 2019-06-14 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-09-20 | COMP | 2019-10-17 | COMP | Rule 16 | 62 | 42 | 7 | 1 | 22 | 20 | 149
12830 | 2019-03-20 | 2019-06-25 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-15 | COMP | 2019-09-26 | COMP | 2019-09-30 | COMP | 2019-11-14 | COMP | Rule 16 | 69 | 28 | 9 | 30 | 3 | 33 | 168
13141 | 2019-03-20 | 2019-07-11 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-09-30 | COMP | 2019-12-06 | COMP | Rule 16 | 80 | 42 | 15 | 1 | 2 | 47 | 182
13142 | 2019-03-20 | 2019-07-12 | 2019-07-19 | 2019-07-19 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2019-09-03 | COMP | 2019-09-04 | COMP | Rule 16 | 81 | 6 | 9 | 1 | 24 | 2 | 118
13436 | 2019-03-20 | 2019-07-25 | 2020-03-12 | 2020-03-12 | COMP | 2020-04-28 | COMP | 2020-05-28 | COMP | 2021-01-23 | INPR | 2020-07-25 | COMP | Rule 15/16 | 90 | 158 | 34 | 22 |  |  | 342
13714 | 2019-03-20 | 2019-08-06 | 2019-09-10 | 2019-09-10 | COMP | 2019-10-02 | COMP | 2019-12-09 | COMP | 2020-02-07 | COMP | 2020-02-28 | COMP | Rule 16 | 98 | 25 | 17 | 46 | 42 | 15 | 238
13858 | 2019-03-20 | 2019-08-13 | 2020-02-01 | 2020-02-01 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2021-04-28 | COMP | 2021-07-07 | COMP | Rule 16 | 103 | 117 | 183 | 1 | 131 | 49 | 580
13996 | 2019-03-20 | 2019-08-20 | 2020-01-22 | 2020-01-22 | COMP | 2020-05-27 | COMP | 2020-04-29 | COMP | 2020-10-08 | COMP | 2020-11-18 | COMP | Rule 15/16 | 108 | 105 | 89 |  | 115 | 29 | 423
14622 | 2019-03-20 | 2019-09-19 | 2019-11-04 | 2019-11-04 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-02-06 | COMP | 2020-03-02 | COMP | Rule 16 | 129 | 33 | 14 | 1 | 50 | 17 | 239
15480 | 2019-03-20 | 2019-11-04 | 2020-01-10 | 2020-01-10 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-11-30 | COMP | 2021-01-07 | COMP | Rule 16 | 161 | 45 | 68 | 1 | 158 | 27 | 455
15964 | 2019-03-20 | 2019-12-03 | 2020-04-06 | 2020-05-13 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2022-06-28 | COMP | 2022-08-01 | COMP | Rule 16 | 179 | 86 | 84 | 1 | 453 | 24 | 849
16880 | 2019-03-20 | 2020-01-22 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-26 | COMP | 2020-03-31 | COMP | Rule 16 | 212 | 18 | 11 | 1 | 19 | 4 | 260
17951 | 2019-03-20 | 2020-03-05 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-12 | COMP | 2020-12-14 | COMP | 2020-12-01 | COMP | 2021-03-16 | COMP | Rule 16 | 242 | 67 | 5 | 128 | 0 | 63 | 501
4135 | 2019-03-21 | 2019-03-21 | 2019-05-22 | 2020-02-18 | COMP | 2020-04-14 | COMP | 2020-07-11 | COMP | 2020-06-23 | COMP | 2020-09-28 | COMP | Rule 15 | 1 | 45 | 41 | 63 | 0 | 55 | 386
4157 | 2019-03-21 | 2019-04-17 | 2019-04-26 | 2019-04-26 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2020-12-08 | COMP | 2020-12-07 | COMP | Other | 20 | 8 | 48 | 1 | 361 |  | 433
10619 | 2019-03-21 | 2019-03-22 | 2019-07-09 | 2019-08-27 | COMP | 2019-07-08 | NOTN | 2019-08-27 | COMP | 2019-07-08 | COMP | 2019-09-30 | COMP | Other | 2 | 76 |  | 1 | 0 | 24 | 135
10835 | 2019-03-21 | 2019-04-01 | 2019-06-26 | 2019-06-26 | COMP | 2019-06-27 | NOTN | 2019-08-28 | COMP | 2019-08-07 | COMP | 2019-09-25 | COMP | Other | 8 | 62 |  | 45 | 0 | 20 | 132
10841 | 2019-03-21 | 2019-04-02 | 2019-08-29 | 2020-08-05 | COMP | 2020-08-20 | COMP | 2020-09-03 | COMP | 2020-10-27 | COMP | 2021-06-21 | COMP | Rule 16 | 9 | 106 | 12 | 11 | 38 | 162 | 568
10914 | 2019-03-21 | 2019-04-05 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-03 | COMP | 2019-05-10 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | Rule 16 | 12 | 11 | 11 | 6 | 18 | 6 | 59
10915 | 2019-03-21 | 2019-04-05 | 2019-05-14 | 2019-05-14 | COMP | 2019-05-22 | COMP | 2019-05-22 | COMP | 2019-06-05 | COMP | 2019-06-12 | COMP | Rule 16 | 12 | 28 | 7 | 1 | 10 | 6 | 59
11399 | 2019-03-21 | 2019-04-25 | 2019-08-06 | 2019-08-06 | COMP | 2020-04-17 | COMP | 2020-05-11 | COMP | 2020-04-20 | COMP | 2020-07-27 | COMP | Rule 15/16 | 26 | 72 | 176 | 17 | 0 | 55 | 342
11417 | 2019-03-21 | 2019-04-26 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-07 | COMP | 2019-10-16 | COMP | 2019-09-09 | COMP | 2020-01-30 | COMP | Rule 16 | 27 | 68 | 5 | 50 | 0 | 71 | 217
11525 | 2019-03-21 | 2019-05-01 | 2019-08-12 | 2019-08-12 | COMP | 2019-10-11 | COMP | 2019-10-14 | COMP | 2019-10-15 | COMP | 2019-10-29 | COMP | Rule 16 | 30 | 72 | 44 | 2 | 2 | 11 | 156
11761 | 2019-03-21 | 2019-05-10 | 2019-06-24 | 2019-06-24 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-08-26 | COMP | 2019-09-06 | COMP | Rule 15/16 | 37 | 31 | 6 | 1 | 40 | 9 | 119
11898 | 2019-03-21 | 2019-05-16 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-09 | COMP | 2020-01-13 | COMP | 2020-01-27 | COMP | 2020-02-20 | COMP | Rule 16 | 41 | 146 | 18 | 3 | 10 | 18 | 231
12024 | 2019-03-21 | 2019-05-21 | 2019-10-07 | 2019-10-07 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-01-07 | COMP | 2020-01-10 | COMP | Rule 16 | 44 | 97 | 45 | 1 | 18 | 4 | 204
12254 | 2019-03-21 | 2019-05-29 | 2019-09-28 | 2021-11-22 | COMP | 2023-03-16 | COMP | 2023-04-06 | COMP | 2023-11-22 | COMP | 2023-07-17 | COMP | Rule 15/16 | 49 | 86 | 329 | 16 | 160 |  | 1087
12348 | 2019-03-21 | 2019-06-03 | 2019-09-01 | 2019-09-01 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-03-02 | COMP | 2020-05-01 | COMP | Rule 16 | 52 | 64 | 85 | 1 | 39 | 45 | 282
12653 | 2019-03-21 | 2019-06-17 | 2019-12-27 | 2019-12-27 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-06-22 | COMP | 2020-07-31 | COMP | Rule 16 | 62 | 134 | 32 | 1 | 92 | 30 | 346
12689 | 2019-03-21 | 2019-06-18 | 2019-10-24 | 2019-11-01 | COMP | 2020-02-05 | COMP | 2020-05-04 | COMP | 2020-07-07 | COMP | 2020-07-27 | COMP | Rule 16 | 63 | 91 | 63 | 63 | 46 | 15 | 342
12778 | 2019-03-21 | 2019-06-21 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-18 | COMP | 2019-11-14 | COMP | 2019-11-21 | COMP | 2019-12-13 | COMP | Rule 16 | 66 | 67 | 18 | 19 | 6 | 15 | 186
13017 | 2019-03-21 | 2019-07-03 | 2019-09-04 | 2019-10-11 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-12-04 | COMP | 2019-12-14 | COMP | Rule 16 | 74 | 44 | 5 | 1 | 32 | 8 | 186
13153 | 2019-03-21 | 2019-07-12 | 2019-08-16 | 2019-08-16 | COMP | 2020-07-30 | COMP | 2022-01-30 | REQD | 2020-11-04 | COMP | 2020-11-30 | COMP | Other | 80 | 26 | 241 |  |  |  | 428
14053 | 2019-03-21 | 2019-08-22 | 2019-12-26 | 2019-12-26 | COMP | 2020-02-10 | COMP | 2020-03-30 | COMP | 2023-11-12 | INPR | 2020-04-20 | COMP | Rule 15/16 | 109 | 86 | 31 | 35 |  |  | 273
14054 | 2019-03-21 | 2019-08-22 | 2020-02-08 | 2020-02-08 | COMP | 2020-04-14 | COMP | 2020-04-29 | COMP | 2020-05-01 | COMP | 2020-05-22 | COMP | Rule 16 | 109 | 115 | 46 | 12 | 3 | 16 | 297
14258 | 2019-03-21 | 2019-09-01 | 2019-12-20 | 2019-12-20 | COMP | 2020-04-14 | COMP | 2020-04-29 | COMP | 2020-05-01 | COMP | 2020-05-20 | COMP | Rule 16 | 115 | 76 | 79 | 12 | 3 | 14 | 295
14393 | 2019-03-21 | 2019-09-09 | 2019-12-16 | 2019-12-16 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2021-10-23 | INPR | 2020-04-02 | COMP | Rule 16 | 120 | 68 | 61 | 1 |  |  | 261
15206 | 2019-03-21 | 2019-10-20 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2021-10-11 | COMP | 2021-12-08 | COMP | Rule 16 | 149 | 84 | 16 | 1 | 399 | 40 | 685
15404 | 2019-03-21 | 2019-10-31 | 2020-01-06 | 2020-01-06 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-03-04 | COMP | 2020-04-24 | COMP | Rule 16 | 158 | 43 | 37 | 1 | 5 | 38 | 277
16051 | 2019-03-21 | 2019-12-07 | 2020-01-23 | 2020-01-23 | COMP | 2020-02-13 | COMP | 2020-02-27 | COMP | 2020-05-14 | COMP | 2020-08-13 | COMP | Rule 16 | 181 | 31 | 16 | 10 | 56 | 65 | 355
16416 | 2019-03-21 | 2019-12-27 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-08 | NOTN | 2020-07-18 | COMP | 2020-06-09 | COMP | 2020-11-13 | COMP | Other | 195 | 107 |  | 36 | 0 | 83 | 419
17620 | 2019-03-21 | 2020-02-21 | 2020-05-06 | 2020-06-09 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2022-04-04 | COMP | 2022-04-04 | COMP | Rule 16 | 232 | 54 | 47 | 1 | 413 | 1 | 766
17787 | 2019-03-21 | 2020-02-28 | 2020-04-07 | 2020-04-07 | COMP | 2020-04-10 | COMP | 2020-05-21 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | Rule 16 | 237 | 28 | 4 | 30 | 31 | 1 | 326
10591 | 2019-03-22 | 2019-03-23 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-19 | NOTN | 2019-09-19 | COMP | 2020-01-07 | COMP | 2020-03-11 | COMP | Other | 1 | 79 |  | 48 | 74 | 45 | 244
10820 | 2019-03-22 | 2019-04-01 | 2019-06-14 | 2019-06-28 | COMP | 2019-07-15 | COMP | 2019-09-03 | COMP | 2019-07-16 | COMP | 2019-10-01 | COMP | Rule 16 | 7 | 54 | 11 | 36 | 0 | 21 | 135
11173 | 2019-03-22 | 2019-04-16 | 2019-07-15 | 2019-07-15 | COMP | 2020-07-06 | NOTN | 2020-09-15 | COMP | 2020-07-20 | NOTN | 2021-03-04 | COMP | Other | 18 | 63 |  | 297 |  |  | 491
11326 | 2019-03-22 | 2019-04-23 | 2020-01-28 | 2020-01-28 | COMP | 2020-03-26 | COMP | 2020-10-14 | COMP |  | INPR | 2020-11-17 | COMP | Rule 15/16 | 23 | 192 | 42 | 143 |  |  | 420
11327 | 2019-03-22 | 2019-04-23 | 2020-02-09 | 2020-02-09 | COMP | 2020-03-26 | COMP | 2020-10-14 | COMP | 2020-10-06 | COMP | 2020-11-17 | COMP | Rule 15/16 | 23 | 200 | 33 | 143 | 0 | 24 | 420
11575 | 2019-03-22 | 2019-05-02 | 2019-10-02 | 2019-10-02 | COMP | 2019-11-21 | COMP | 2020-01-16 | COMP | 2020-04-21 | COMP | 2020-04-28 | COMP | Rule 16 | 30 | 107 | 36 | 37 | 67 | 6 | 278
11740 | 2019-03-22 | 2019-05-09 | 2019-07-15 | 2019-07-17 | COMP | 2019-08-15 | COMP | 2019-09-30 | COMP | 2019-10-03 | COMP | 2019-10-07 | COMP | Rule 16 | 35 | 46 | 22 | 32 | 4 | 3 | 139
11902 | 2019-03-22 | 2019-05-15 | 2019-09-26 | 2019-09-26 | COMP | 2020-02-25 | COMP | 2020-04-20 | COMP | 2022-01-26 | COMP | 2022-01-17 | COMP | Rule 16 | 39 | 94 | 102 | 40 | 447 |  | 711
12271 | 2019-03-22 | 2019-05-31 | 2019-10-24 | 2019-10-24 | COMP | 2019-12-04 | COMP | 2020-08-27 | COMP | 2020-08-23 | COMP | 2020-11-10 | COMP | Rule 15/16 | 50 | 103 | 27 | 187 | 0 | 53 | 416
12303 | 2019-03-22 | 2019-05-30 | 2019-08-03 | 2019-08-03 | COMP | 2019-09-04 | COMP | 2019-09-26 | COMP | 2019-09-13 | COMP | 2019-10-22 | COMP | Rule 16 | 49 | 46 | 22 | 17 | 0 | 19 | 150
12312 | 2019-03-22 | 2019-05-30 | 2019-06-24 | 2019-06-24 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-12-29 | INPR | 2019-08-07 | COMP | Rule 16 | 49 | 18 | 35 | 1 |  |  | 97
12384 | 2019-03-22 | 2019-06-04 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-06 | COMP | 2019-08-06 | COMP | 2019-12-31 | COMP | 2020-01-06 | COMP | Rule 16 | 52 | 28 | 18 | 1 | 101 | 4 | 199
12781 | 2019-03-22 | 2019-06-21 | 2019-11-01 | 2020-03-25 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-08-26 | COMP | 2020-09-02 | COMP | Rule 16 | 65 | 94 | 78 | 1 | 33 | 6 | 368
13161 | 2019-03-22 | 2019-07-15 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-06 | NOTN | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-11-05 | COMP | Other | 80 | 24 |  | 16 | 1 | 43 | 160
13233 | 2019-03-22 | 2019-07-18 | 2019-10-02 | 2019-10-02 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-03-25 | COMP | 2020-04-16 | COMP | Rule 16 | 83 | 54 | 93 | 1 | 27 | 17 | 270
13244 | 2019-03-22 | 2019-07-17 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-24 | COMP | 2019-10-16 | COMP | 2020-05-31 | INPR | 2019-11-25 | COMP | Rule 16 | 82 | 38 | 12 | 17 |  |  | 173
13373 | 2019-03-22 | 2019-07-23 | 2019-10-02 | 2019-10-02 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2021-01-05 | COMP | 2021-03-02 | COMP | Rule 16 | 86 | 51 | 96 | 1 | 221 | 39 | 489
13398 | 2019-03-22 | 2019-07-24 | 2019-12-14 | 2019-12-14 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-09-23 | COMP | 2020-10-13 | COMP | Rule 16 | 87 | 99 | 133 | 1 | 65 | 15 | 396
14204 | 2019-03-22 | 2019-08-29 | 2019-11-26 | 2019-11-26 | COMP | 2019-12-23 | COMP | 2020-01-21 | COMP | 2020-01-31 | COMP | 2020-02-26 | COMP | Rule 16 | 113 | 62 | 18 | 19 | 9 | 18 | 234
14508 | 2019-03-22 | 2019-09-13 | 2019-09-25 | 2019-09-25 | COMP | 2019-11-13 | COMP | 2019-11-13 | NOTN | 2019-12-10 | COMP | 2019-12-13 | COMP | Rule 16 | 123 | 9 | 35 |  |  |  | 185
15233 | 2019-03-22 | 2019-10-22 | 2020-01-21 | 2020-01-21 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-10-16 | COMP | 2020-11-02 | COMP | Rule 16 | 150 | 60 | 66 | 1 | 126 | 12 | 410
15345 | 2019-03-22 | 2019-10-29 | 2020-04-22 | 2020-04-22 | COMP | 2021-02-12 | COMP | 2021-03-05 | COMP | 2021-09-22 | COMP | 2022-02-03 | COMP | Rule 16 | 155 | 120 | 205 | 15 | 141 | 93 | 724
15960 | 2019-03-22 | 2019-12-03 | 2020-12-29 | 2021-06-11 | COMP | 2021-07-06 | COMP | 2023-01-24 | COMP | 2023-06-30 | COMP | 2023-08-01 | COMP | Rule 15/16 | 177 | 271 | 17 | 390 | 111 | 22 | 1097
16071 | 2019-03-22 | 2019-12-08 | 2020-06-15 | 2020-06-15 | COMP | 2020-06-23 | COMP | 2020-09-16 | COMP | 2022-01-30 | INPR | 2020-11-02 | COMP | Rule 16 | 180 | 131 | 7 | 61 |  |  | 410
16347 | 2019-03-22 | 2019-12-23 | 2020-03-22 | 2020-04-14 | COMP | 2020-05-13 | COMP | 2021-03-16 | COMP | 2022-05-28 | INPR | 2021-05-13 | COMP | Rule 16 | 191 | 61 | 22 | 211 |  |  | 541
18313 | 2019-03-22 | 2020-03-19 | 2020-07-31 | 2020-07-31 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2020-10-28 | COMP | 2021-01-04 | COMP | Rule 15/16 | 250 | 96 | 64 | 1 | 0 | 43 | 450
18418 | 2019-03-22 | 2020-03-23 | 2020-08-04 | 2020-08-04 | COMP | 2020-09-02 | COMP | 2020-08-20 | COMP | 2020-11-16 | COMP | 2021-02-12 | COMP | Rule 15/16 | 252 | 96 | 22 |  | 61 | 60 | 478
18750 | 2019-03-22 | 2020-04-06 | 2020-12-10 | 2020-12-10 | COMP | 2021-03-25 | COMP | 2021-12-02 | COMP | 2021-12-14 | COMP | 2022-01-25 | COMP | Rule 15/16 | 262 | 174 | 72 | 175 | 9 | 30 | 717
19314 | 2019-03-22 | 2020-04-30 | 2020-08-11 | 2020-08-11 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2020-10-20 | COMP | 2020-11-13 | COMP | Rule 15/16 | 280 | 73 | 42 | 1 | 9 | 18 | 418
19510 | 2019-03-22 | 2020-05-11 | 2020-10-20 | 2020-10-20 | COMP | 2021-01-06 | COMP | 2021-01-06 | COMP | 2021-01-11 | COMP | 2021-01-13 | COMP | Rule 16 | 287 | 115 | 52 | 1 | 4 | 3 | 457
10647 | 2019-03-23 | 2019-03-25 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-17 | COMP | 2019-07-18 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | Rule 16 | 1 | 68 | 14 | 2 | 31 | 1 | 112
11249 | 2019-03-23 | 2019-04-18 | 2019-09-20 | 2019-09-20 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-11-12 | COMP | 2019-12-06 | COMP | Rule 15/16 | 19 | 109 | 18 | 1 | 20 | 17 | 179
13680 | 2019-03-23 | 2019-08-05 | 2019-08-31 | 2019-10-22 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2020-03-13 | COMP | 2020-06-01 | COMP | Rule 16 | 94 | 20 | 42 | 1 | 56 | 56 | 300
10729 | 2019-03-24 | 2019-03-28 | 2019-07-16 | 2019-07-16 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2020-02-11 | COMP | 2020-02-12 | COMP | Rule 16 | 4 | 77 | 43 | 1 | 102 | 2 | 224
12598 | 2019-03-24 | 2019-06-14 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-04-07 | COMP | 2020-04-23 | COMP | Rule 16 | 59 | 137 | 19 | 1 | 50 | 13 | 274
13285 | 2019-03-24 | 2019-07-19 | 2019-09-23 | 2019-09-30 | COMP | 2019-10-22 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-06-29 | COMP | Rule 16 | 83 | 46 | 17 | 94 | 1 | 79 | 320
13900 | 2019-03-24 | 2019-08-15 | 2020-02-10 | 2020-02-10 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-08-07 | COMP | 2020-11-05 | COMP | Rule 15/16 | 102 | 121 | 95 | 1 | 34 | 64 | 412
13901 | 2019-03-24 | 2019-08-15 | 2020-02-13 | 2020-02-13 | COMP | 2020-06-23 | COMP | 2020-08-10 | COMP | 2020-08-07 | COMP | 2021-01-14 | COMP | Rule 15/16 | 102 | 124 | 92 | 35 | 0 | 108 | 457
13947 | 2019-03-24 | 2019-08-17 | 2020-01-23 | 2020-01-23 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-08-07 | COMP | 2020-10-29 | COMP | Rule 16 | 103 | 107 | 108 | 1 | 33 | 59 | 407
14521 | 2019-03-24 | 2019-09-13 | 2019-11-25 | 2019-11-25 | COMP | 2019-12-24 | COMP | 2020-12-14 | COMP | 2021-02-02 | COMP | 2021-03-05 | COMP | Rule 16 | 122 | 51 | 20 | 246 | 34 | 23 | 491
10672 | 2019-03-25 | 2019-03-25 | 2019-04-20 | 2019-04-20 | COMP | 2019-05-02 | COMP | 2019-05-16 | COMP | 2019-10-21 | INPR | 2019-07-05 | COMP | Rule 16 | 1 | 20 | 9 | 11 |  |  | 73
10695 | 2019-03-25 | 2019-03-26 | 2019-05-15 | 2019-05-15 | COMP | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-10-04 | COMP | 2019-10-20 | COMP | Rule 16 | 2 | 37 | 41 | 1 | 60 | 11 | 147
10814 | 2019-03-25 | 2019-04-01 | 2019-04-03 | 2019-04-03 | COMP | 2019-04-09 | COMP | 2019-04-18 | COMP | 2019-04-25 | COMP | 2019-04-26 | COMP | Rule 16 | 6 | 3 | 5 | 8 | 6 | 2 | 25
10854 | 2019-03-25 | 2019-04-02 | 2019-05-11 | 2019-11-16 | COMP | 2019-11-21 | COMP | 2019-11-21 | INPR | 2019-11-18 | COMP | 2019-12-12 | COMP | Rule 16 | 7 | 29 | 4 |  |  |  | 183
10901 | 2019-03-25 | 2019-04-04 | 2019-04-18 | 2019-04-18 | COMP | 2019-06-05 | COMP | 2019-06-05 | COMP | 2019-10-21 | INPR | 2019-07-01 | COMP | Rule 16 | 9 | 11 | 34 | 1 |  |  | 70
10921 | 2019-03-25 | 2019-04-04 | 2019-07-15 | 2019-07-15 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | 2019-12-03 | COMP | Rule 16 | 9 | 71 | 72 | 1 | 19 | 9 | 176
10952 | 2019-03-25 | 2019-04-05 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-09-05 | COMP | 2019-09-06 | COMP | Rule 16 | 10 | 60 | 2 | 1 | 47 | 2 | 117
10966 | 2019-03-25 | 2019-04-06 | 2019-06-17 | 2019-11-20 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-10-14 | COMP | 2020-12-15 | COMP | Rule 16 | 10 | 50 | 50 | 1 | 179 | 42 | 437
11284 | 2019-03-25 | 2019-04-23 | 2019-06-08 | 2019-06-08 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-08-26 | COMP | Rule 16 | 22 | 33 | 21 | 1 | 1 | 35 | 109
11559 | 2019-03-25 | 2019-05-03 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP |  |  | 2019-08-26 | COMP | Rule 16 | 30 | 47 | 19 | 1 |  |  | 109
11561 | 2019-03-25 | 2019-05-03 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-11-27 | COMP | 2020-07-06 | COMP | Rule 16 | 30 | 69 | 8 | 1 | 70 | 152 | 325
11570 | 2019-03-25 | 2019-05-04 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-07-31 | COMP | 2019-08-01 | COMP | Rule 16 | 30 | 9 | 19 | 1 | 35 | 2 | 92
11606 | 2019-03-25 | 2019-05-04 | 2019-10-12 | 2019-10-20 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-02-09 | COMP | Rule 16 | 30 | 112 | 60 | 1 | 1 | 15 | 221
11677 | 2019-03-25 | 2019-05-07 | 2019-08-17 | 2019-08-17 | COMP | 2019-08-23 | COMP | 2019-09-23 | NOTN | 2019-09-23 | COMP | 2019-10-03 | COMP | Rule 16 | 32 | 72 | 5 |  |  |  | 136
11886 | 2019-03-25 | 2019-05-15 | 2020-09-04 | 2020-09-04 | COMP | 2020-11-09 | COMP | 2021-01-21 | COMP |  | INPR | 2021-03-15 | COMP | Rule 15/16 | 38 | 332 | 46 | 48 |  |  | 497
12036 | 2019-03-25 | 2019-05-21 | 2019-10-28 | 2019-10-28 | COMP | 2020-01-21 | COMP | 2020-06-01 | COMP | 2021-01-06 | COMP | 2021-02-05 | COMP | Rule 16 | 42 | 112 | 56 | 93 | 152 | 22 | 472
12046 | 2019-03-25 | 2019-05-21 | 2019-10-08 | 2019-10-08 | COMP | 2019-11-12 | COMP | 2019-11-06 | COMP | 2020-04-08 | COMP | 2020-05-03 | COMP | Rule 16 | 42 | 98 | 25 |  | 104 | 18 | 280
12443 | 2019-03-25 | 2019-06-06 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-10-30 | COMP | 2019-10-25 | COMP | Rule 16 | 53 | 16 | 3 | 1 | 86 |  | 152
12483 | 2019-03-25 | 2019-06-11 | 2019-10-05 | 2019-10-23 | COMP | 2019-10-30 | COMP | 2019-11-05 | COMP | 2019-11-25 | COMP | 2019-12-17 | COMP | Rule 16 | 56 | 82 | 6 | 5 | 14 | 15 | 186
13400 | 2019-03-25 | 2019-07-24 | 2019-08-19 | 2019-08-19 | COMP | 2019-08-29 | COMP | 2019-11-04 | COMP | 2020-07-21 | COMP | 2020-08-03 | COMP | Rule 16 | 86 | 19 | 9 | 47 | 179 | 10 | 345
14189 | 2019-03-25 | 2019-08-28 | 2019-11-13 | 2019-11-13 | COMP | 2020-03-31 | COMP | 2020-04-07 | COMP | 2020-04-27 | COMP | 2020-06-08 | COMP | Rule 16 | 111 | 54 | 94 | 6 | 15 | 30 | 305
14341 | 2019-03-25 | 2019-09-06 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-11 | COMP | 2020-03-27 | COMP | 2021-06-30 | COMP | 2021-09-08 | COMP | Rule 15/16 | 117 | 108 | 20 | 13 | 319 | 49 | 621
14406 | 2019-03-25 | 2019-09-09 | 2020-01-17 | 2020-01-17 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2020-09-23 | COMP | 2020-11-07 | COMP | Rule 16 | 118 | 90 | 46 | 1 | 130 | 33 | 413
14955 | 2019-03-25 | 2019-10-07 | 2019-10-11 | 2020-01-09 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-01-21 | COMP | 2020-01-24 | COMP | Rule 16 | 138 | 5 | 7 | 1 | 2 | 4 | 211
15072 | 2019-03-25 | 2019-10-10 | 2020-02-14 | 2020-05-22 | COMP | 2020-06-22 | COMP | 2020-07-16 | COMP | 2020-07-24 | COMP | 2020-09-29 | COMP | Rule 16 | 141 | 86 | 21 | 19 | 7 | 47 | 385
15458 | 2019-03-25 | 2019-11-02 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-08-19 | COMP | 2020-09-10 | COMP | Rule 16 | 157 | 145 | 8 | 1 | 49 | 16 | 372
15525 | 2019-03-25 | 2019-11-05 | 2020-04-22 | 2020-04-22 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-06-29 | COMP | 2020-07-22 | COMP | Rule 16 | 159 | 115 | 47 | 1 | 2 | 18 | 337
16025 | 2019-03-25 | 2019-12-05 | 2020-04-15 | 2020-10-28 | COMP | 2020-11-06 | COMP | 2021-10-26 | COMP | 2021-10-28 | COMP | 2021-12-01 | COMP | Rule 16 | 178 | 91 | 8 | 243 | 3 | 22 | 678
16561 | 2019-03-25 | 2020-01-08 | 2020-03-10 | 2020-03-10 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-04-21 | COMP | 2020-05-29 | COMP | Rule 16 | 200 | 43 | 4 | 1 | 28 | 28 | 299
16879 | 2019-03-25 | 2020-01-22 | 2021-01-11 | 2021-01-11 | COMP | 2021-03-11 | COMP | 2021-05-25 | COMP | 2023-12-03 | INPR | 2021-05-28 | COMP | Rule 16 | 209 | 246 | 42 | 54 |  |  | 551
4285 | 2019-03-26 | 2020-03-26 | 2020-12-16 | 2020-12-16 | COMP | 2021-02-09 | COMP | 2021-05-03 | COMP | 2021-06-25 | COMP | 2022-10-21 | COMP | Rule 15/16 | 253 | 185 | 37 | 59 | 39 | 335 | 903
10712 | 2019-03-26 | 2019-03-27 | 2019-08-01 | 2019-08-01 | COMP | 2020-03-12 | COMP | 2021-06-10 | COMP | 2021-07-20 | COMP | 2021-07-13 | COMP | Rule 16 | 2 | 90 | 153 | 316 | 28 |  | 580
10935 | 2019-03-26 | 2019-04-05 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-09 | COMP | 2019-05-09 | COMP | 2019-06-11 | COMP | 2019-07-03 | COMP | Rule 16 | 9 | 11 | 15 | 1 | 23 | 17 | 71
10956 | 2019-03-26 | 2019-04-05 | 2019-04-09 | 2019-04-09 | COMP | 2019-05-06 | NOTN | 2019-05-06 | COMP | 2019-05-16 | COMP | 2019-05-31 | COMP | Other | 9 | 3 |  | 20 | 9 | 11 | 48
11060 | 2019-03-26 | 2019-04-11 | 2019-08-03 | 2019-08-03 | COMP | 2019-07-28 | NOTN | 2019-08-03 | COMP | 2021-03-27 | INPR | 2020-03-24 | COMP | Other | 13 | 80 |  | 0 |  |  | 251
11065 | 2019-03-26 | 2019-04-10 | 2019-07-26 | 2019-07-26 | COMP | 2019-07-26 | NOTN | 2019-07-26 | COMP | 2020-02-25 | COMP | 2020-03-24 | COMP | Other | 12 | 76 |  | 1 | 145 | 21 | 251
11088 | 2019-03-26 | 2019-04-12 | 2019-06-20 | 2019-06-28 | COMP | 2019-07-05 | COMP | 2019-07-05 | COMP | 2019-06-07 | COMP | 2019-08-04 | COMP | Rule 16 | 14 | 49 | 5 | 1 | 0 | 21 | 92
11177 | 2019-03-26 | 2019-04-17 | 2019-06-26 | 2019-06-26 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-10-07 | COMP | 2019-10-02 | COMP | Rule 16 | 17 | 50 | 40 | 1 | 33 |  | 134
11237 | 2019-03-26 | 2019-04-18 | 2019-06-25 | 2019-06-25 | COMP | 2019-06-25 | NOTN | 2019-08-12 | COMP | 2019-08-02 | COMP | 2019-09-11 | COMP | Other | 18 | 48 |  | 34 | 0 | 22 | 119
11261 | 2019-03-26 | 2019-04-19 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-21 | COMP | 2019-08-22 | COMP | 2020-02-18 | COMP | 2020-03-24 | COMP | Rule 16 | 19 | 65 | 23 | 2 | 121 | 26 | 251
11384 | 2019-03-26 | 2019-04-24 | 2019-08-12 | 2019-08-31 | COMP | 2019-09-10 | NOTN | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-01-03 | COMP | Other | 22 | 77 |  | 6 | 1 | 79 | 196
11390 | 2019-03-26 | 2019-04-25 | 2019-05-20 | 2019-05-20 | COMP | 2019-05-22 | COMP | 2019-05-31 | COMP | 2019-05-29 | COMP | 2019-06-12 | COMP | Rule 16 | 23 | 18 | 3 | 7 | 0 | 9 | 56
11391 | 2019-03-26 | 2019-04-25 | 2019-05-08 | 2019-05-08 | COMP | 2019-05-16 | COMP | 2019-06-11 | COMP | 2019-06-19 | COMP | 2019-06-29 | COMP | Rule 16 | 23 | 10 | 7 | 18 | 7 | 8 | 68
11445 | 2019-03-26 | 2019-04-29 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2020-04-14 | COMP | 2020-05-15 | COMP | Other | 25 | 83 | 10 | 1 | 151 | 24 | 289
11450 | 2019-03-26 | 2019-04-29 | 2019-05-25 | 2019-05-25 | COMP | 2019-07-25 | COMP | 2019-08-23 | COMP | 2019-08-05 | COMP | 2019-09-03 | COMP | Rule 16 | 25 | 20 | 42 | 22 | 0 | 7 | 113
11563 | 2019-03-26 | 2019-05-02 | 2019-10-17 | 2019-10-17 | COMP | 2019-10-31 | COMP | 2020-04-01 | COMP | 2020-04-16 | COMP | 2020-05-01 | COMP | Rule 15/16 | 28 | 118 | 11 | 103 | 12 | 12 | 279
11614 | 2019-03-26 | 2019-05-06 | 2019-06-18 | 2019-07-17 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-09-17 | COMP | 2019-10-23 | COMP | Rule 16 | 30 | 31 | 19 | 1 | 26 | 27 | 149
11699 | 2019-03-26 | 2019-05-08 | 2019-06-08 | 2019-06-08 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-08-19 | COMP | 2019-09-06 | COMP | Rule 16 | 32 | 22 | 20 | 1 | 31 | 14 | 116
11730 | 2019-03-26 | 2019-05-08 | 2019-07-25 | 2019-07-25 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-06-05 | COMP | 2020-07-02 | COMP | Rule 16 | 32 | 55 | 103 | 1 | 116 | 20 | 322
11877 | 2019-03-26 | 2019-05-15 | 2020-01-31 | 2020-03-09 | COMP | 2020-06-01 | COMP | 2020-08-26 | COMP | 2020-10-14 | COMP | 2020-11-17 | COMP | Rule 16 | 37 | 179 | 60 | 63 | 35 | 24 | 418
11969 | 2019-03-26 | 2019-05-20 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-08-26 | COMP | 2019-09-18 | COMP | Rule 16 | 40 | 53 | 9 | 1 | 9 | 17 | 124
12045 | 2019-03-26 | 2019-05-21 | 2019-10-12 | 2019-10-12 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-01-28 | COMP | 2020-03-02 | COMP | Rule 16 | 41 | 101 | 59 | 1 | 13 | 24 | 235
12260 | 2019-03-26 | 2019-05-29 | 2019-08-14 | 2019-10-22 | COMP | 2019-12-19 | COMP | 2020-01-15 | COMP | 2020-02-11 | COMP | 2020-03-02 | COMP | Rule 16 | 46 | 55 | 40 | 18 | 19 | 14 | 235
12436 | 2019-03-26 | 2019-06-06 | 2019-07-27 | 2019-07-27 | COMP | 2021-03-18 | COMP | 2021-03-18 | INPR | 2022-03-07 | COMP | 2022-07-29 | COMP | Other | 52 | 36 | 412 |  |  |  | 844
12467 | 2019-03-26 | 2019-06-07 | 2019-10-12 | 2019-10-12 | COMP | 2020-06-13 | COMP | 2020-06-13 | COMP | 2020-06-14 | COMP | 2020-07-21 | COMP | Other | 53 | 89 | 167 | 0 | 0 | 27 | 335
12555 | 2019-03-26 | 2019-06-13 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-11 | COMP | 2019-09-20 | COMP | 2019-09-24 | COMP | 2019-10-16 | COMP | Rule 15/16 | 57 | 56 | 8 | 8 | 3 | 17 | 144
12592 | 2019-03-26 | 2019-06-14 | 2019-07-19 | 2019-07-19 | COMP | 2019-08-07 | COMP | 2019-08-09 | COMP | 2019-11-27 | COMP | 2020-01-02 | COMP | Rule 16 | 58 | 25 | 14 | 3 | 77 | 23 | 195
12603 | 2019-03-26 | 2019-06-14 | 2019-07-04 | 2019-07-04 | COMP | 2019-07-18 | COMP | 2019-07-18 | INPR | 2019-07-29 | COMP | 2019-07-31 | COMP | Rule 16 | 58 | 14 | 10 |  |  |  | 90
12683 | 2019-03-26 | 2019-06-18 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-26 | COMP | 2019-11-06 | COMP | 2020-03-14 | COMP | 2020-03-14 | COMP | Rule 16 | 60 | 35 | 15 | 52 | 86 | 0 | 244
12819 | 2019-03-26 | 2019-06-24 | 2019-11-07 | 2021-11-01 | COMP | 2021-12-06 | COMP | 2023-03-21 | COMP | 2022-09-02 | COMP | 2023-05-16 | COMP | Other | 64 | 97 | 23 | 324 | 0 | 41 | 1043
12842 | 2019-03-26 | 2019-06-24 | 2019-09-30 | 2019-10-30 | COMP | 2019-11-25 | COMP | 2019-12-02 | COMP | 2020-06-12 | COMP | 2020-08-14 | COMP | Rule 15/16 | 64 | 69 | 18 | 4 | 135 | 46 | 353
12940 | 2019-03-26 | 2019-07-01 | 2019-08-29 | 2019-08-29 | COMP | 2020-03-09 | COMP | 2021-03-26 | COMP | 2021-08-04 | COMP | 2021-09-10 | COMP | Rule 16 | 69 | 43 | 130 | 266 | 92 | 27 | 622
12941 | 2019-03-26 | 2019-07-01 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-07 | NOTN | 2019-10-07 | COMP | 2019-10-07 | NOTN | 2020-02-17 | COMP | Other | 69 | 68 |  | 1 |  |  | 225
13203 | 2019-03-26 | 2019-07-16 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2020-04-15 | COMP | 2020-04-09 | COMP | Rule 16 | 79 | 13 | 3 | 1 | 175 |  | 263
13310 | 2019-03-26 | 2019-07-20 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2020-03-21 | INPR | 2019-12-06 | COMP | Rule 16 | 82 | 67 | 13 | 1 |  |  | 178
13350 | 2019-03-26 | 2019-07-22 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-01-09 | COMP | 2020-01-15 | COMP | Rule 16 | 83 | 42 | 11 | 1 | 67 | 5 | 204
13361 | 2019-03-26 | 2019-07-23 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-12 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2019-12-17 | COMP | Rule 16 | 84 | 59 | 21 | 15 | 1 | 10 | 185
13539 | 2019-03-26 | 2019-07-31 | 2019-11-26 | 2019-12-04 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-03-17 | COMP | 2020-06-02 | COMP | Rule 16 | 90 | 83 | 30 | 1 | 42 | 55 | 300
13882 | 2019-03-26 | 2019-08-14 | 2019-11-09 | 2019-11-09 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-02-10 | COMP | 2020-03-02 | COMP | Rule 16 | 100 | 62 | 36 | 1 | 25 | 15 | 235
13954 | 2019-03-26 | 2019-08-19 | 2019-10-23 | 2019-10-23 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2021-01-05 | COMP | 2021-02-22 | COMP | Rule 16 | 103 | 47 | 48 | 1 | 254 | 33 | 481
14479 | 2019-03-26 | 2019-09-11 | 2019-12-04 | 2019-12-04 | COMP | 2020-03-11 | COMP | 2020-05-29 | COMP | 2021-10-23 | INPR | 2020-08-04 | COMP | Rule 16 | 119 | 58 | 67 | 57 |  |  | 345
14497 | 2019-03-26 | 2019-09-12 | 2020-01-06 | 2020-04-10 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-07-17 | COMP | 2020-08-07 | COMP | Rule 16 | 120 | 78 | 14 | 1 | 57 | 16 | 348
14626 | 2019-03-26 | 2019-09-20 | 2020-01-09 | 2020-01-09 | COMP | 2020-05-12 | COMP | 2020-08-06 | COMP | 2021-03-09 | COMP | 2021-03-17 | COMP | Rule 15/16 | 126 | 75 | 87 | 62 | 146 | 7 | 498
15229 | 2019-03-26 | 2019-10-21 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-12 | NOTN | 2019-12-20 | COMP | 2020-01-09 | COMP | 2020-03-06 | COMP | Other | 147 | 36 |  | 7 | 13 | 40 | 239
4139 | 2019-03-27 | 2019-03-27 | 2019-03-30 | 2019-03-30 | COMP | 2019-05-03 | COMP | 2019-04-24 | COMP | 2019-05-03 | COMP | 2019-05-10 | COMP | Rule 15/16 | 1 | 3 | 25 |  | 8 | 6 | 33
10723 | 2019-03-27 | 2019-03-28 | 2019-04-15 | 2019-04-15 | COMP | 2019-05-28 | COMP | 2019-05-28 | COMP | 2019-11-26 | COMP | 2019-12-05 | COMP | Rule 15/16 | 2 | 13 | 31 | 1 | 128 | 6 | 176
10726 | 2019-03-27 | 2019-03-28 | 2019-05-24 | 2019-05-24 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-07-26 | COMP | 2021-10-05 | COMP | Rule 16 | 2 | 42 | 317 | 1 | 230 | 51 | 638
10816 | 2019-03-27 | 2019-04-01 | 2019-04-29 | 2019-04-29 | COMP | 2019-07-12 | COMP | 2019-07-12 | INPR | 2019-12-29 | REQD | 2019-08-13 | COMP | Rule 16 | 4 | 21 | 53 |  |  |  | 98
10836 | 2019-03-27 | 2019-04-01 | 2019-08-11 | 2019-08-11 | COMP | 2019-04-01 | NOTN | 2019-10-17 | COMP | 2019-09-18 | NOTN | 2020-01-31 | COMP | Other | 4 | 93 |  | 48 |  |  | 214
11298 | 2019-03-27 | 2019-04-22 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-19 | NOTN | 2019-07-22 | COMP | 2019-07-19 | COMP | 2019-08-28 | COMP | Rule 16 | 19 | 61 |  | 4 | 0 | 28 | 109
11545 | 2019-03-27 | 2019-05-01 | 2019-08-28 | 2019-08-28 | COMP | 2020-01-23 | COMP | 2020-04-20 | COMP | 2020-08-03 | COMP | 2020-10-02 | COMP | Rule 16 | 26 | 84 | 100 | 62 | 75 | 44 | 386
11592 | 2019-03-27 | 2019-05-03 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-14 | NOTN | 2019-06-14 | COMP | 2019-07-23 | COMP | 2019-08-21 | COMP | Rule 16 | 28 | 16 |  | 15 | 27 | 22 | 104
12141 | 2019-03-27 | 2019-05-24 | 2019-07-31 | 2019-07-31 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-09-10 | COMP | 2019-09-27 | COMP | Rule 16 | 43 | 47 | 8 | 1 | 22 | 14 | 130
12388 | 2019-03-27 | 2019-06-03 | 2020-02-20 | 2020-02-20 | COMP | 2020-07-07 | COMP | 2020-10-28 | COMP | 2020-10-12 | COMP | 2021-03-05 | COMP | Rule 15/16 | 48 | 180 | 98 | 81 | 0 | 86 | 489
12448 | 2019-03-27 | 2019-06-06 | 2019-08-07 | 2019-08-07 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-03-12 | COMP | 2020-06-23 | COMP | Rule 16 | 51 | 44 | 142 | 1 | 8 | 73 | 314
12731 | 2019-03-27 | 2019-06-21 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-09-05 | COMP | 2019-10-22 | COMP | Rule 16 | 62 | 43 | 12 | 1 | 0 | 33 | 147
12866 | 2019-03-27 | 2019-06-26 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2022-01-30 | INPR | 2020-04-17 | COMP | Rule 16 | 65 | 67 | 17 | 1 |  |  | 268
13014 | 2019-03-27 | 2019-07-03 | 2019-10-21 | 2019-10-21 | COMP | 2019-11-06 | COMP | 2019-11-19 | COMP | 2019-11-08 | COMP | 2020-01-02 | COMP | Rule 16 | 70 | 77 | 13 | 9 | 0 | 29 | 194
13107 | 2019-03-27 | 2019-07-10 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2019-11-18 | COMP | 2019-12-03 | COMP | Rule 16 | 74 | 31 | 14 | 1 | 49 | 10 | 174
14771 | 2019-03-27 | 2019-09-26 | 2020-11-12 | 2020-11-12 | COMP | 2021-02-05 | COMP | 2021-08-23 | COMP | 2022-01-24 | COMP | 2022-02-05 | COMP | Rule 16 | 129 | 286 | 57 | 139 | 106 | 10 | 722
15477 | 2019-03-27 | 2019-11-04 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-23 | NOTN | 2020-04-30 | COMP | 2020-06-23 | COMP | 2020-10-07 | COMP | Other | 156 | 100 |  | 23 | 38 | 76 | 389
16583 | 2019-03-27 | 2020-01-08 | 2020-07-21 | 2020-07-21 | COMP | 2021-03-09 | COMP | 2021-07-20 | COMP | 2021-12-21 | COMP | 2022-02-04 | COMP | Rule 15/16 | 198 | 137 | 158 | 94 | 107 | 33 | 722
17515 | 2019-03-27 | 2020-02-18 | 2021-02-24 | 2021-02-24 | COMP | 2021-05-14 | COMP | 2021-05-14 | COMP | 2021-09-30 | COMP | 2021-10-15 | COMP | Rule 15/16 | 225 | 258 | 58 | 1 | 97 | 12 | 646
10762 | 2019-03-28 | 2019-03-28 | 2019-04-20 | 2019-04-26 | COMP | 2019-04-26 | NOTN | 2019-05-10 | COMP | 2019-04-26 | COMP | 2019-06-28 | COMP | Other | 1 | 17 |  | 11 | 0 | 35 | 66
10859 | 2019-03-28 | 2019-04-02 | 2019-06-12 | 2019-06-12 | COMP | 2019-06-12 | NOTN | 2019-06-12 | NOTN | 2019-06-12 | COMP | 2019-07-17 | COMP | Other | 4 | 51 |  |  |  |  | 78
10916 | 2019-03-28 | 2019-04-05 | 2019-04-19 | 2019-04-19 | COMP | 2019-05-14 | COMP | 2019-05-14 | COMP | 2019-07-10 | COMP | 2019-07-19 | COMP | Rule 16 | 7 | 11 | 18 | 1 | 40 | 8 | 80
10962 | 2019-03-28 | 2019-04-05 | 2019-05-03 | 2019-05-03 | COMP | 2019-05-10 | COMP | 2019-05-10 | COMP | 2019-07-19 | COMP | 2019-08-01 | COMP | Rule 16 | 7 | 21 | 6 | 1 | 49 | 10 | 89
10967 | 2019-03-28 | 2019-04-06 | 2019-06-04 | 2019-06-04 | COMP | 2019-06-19 | COMP | 2019-07-18 | INPR | 2019-07-18 | COMP | 2019-08-01 | COMP | Rule 16 | 7 | 41 | 12 |  |  |  | 89
11081 | 2019-03-28 | 2019-04-11 | 2019-05-28 | 2019-05-28 | COMP | 2019-07-15 | COMP | 2020-05-01 | COMP | 2020-05-08 | COMP | 2020-05-27 | COMP | Rule 16 | 11 | 33 | 34 | 202 | 6 | 13 | 294
11082 | 2019-03-28 | 2019-04-11 | 2019-04-26 | 2019-10-28 | COMP | 2020-02-28 | COMP | 2020-07-24 | COMP | 2020-08-04 | COMP | 2020-10-06 | COMP | Rule 16 | 11 | 12 | 83 | 105 | 8 | 45 | 387
11083 | 2019-03-28 | 2019-04-11 | 2019-07-26 | 2019-07-26 | COMP | 2019-11-12 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2020-10-01 | COMP | Rule 15/16 | 11 | 75 | 76 | 209 | 1 | 17 | 384
11256 | 2019-03-28 | 2019-04-19 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-26 | COMP | 2019-08-30 | COMP | 2019-10-08 | COMP | 2019-10-23 | COMP | Rule 16 | 17 | 75 | 16 | 5 | 27 | 12 | 147
11424 | 2019-03-28 | 2019-04-26 | 2019-09-15 | 2019-09-15 | COMP | 2020-04-03 | COMP | 2020-06-02 | NOTN | 2020-05-19 | COMP | 2020-06-03 | COMP | Rule 15/16 | 22 | 98 | 138 |  |  |  | 299
11522 | 2019-03-28 | 2019-04-30 | 2019-07-25 | 2019-07-25 | COMP | 2019-07-26 | NOTN | 2019-09-09 | COMP | 2019-08-19 | NOTN | 2019-09-16 | COMP | Other | 24 | 61 |  | 32 |  |  | 120
11554 | 2019-03-28 | 2019-05-02 | 2019-08-14 | 2019-08-14 | COMP | 2019-08-30 | COMP | 2019-08-30 | COMP | 2019-11-12 | COMP | 2019-11-19 | COMP | Rule 16 | 26 | 73 | 13 | 1 | 51 | 6 | 165
11681 | 2019-03-28 | 2019-05-07 | 2019-09-21 | 2019-10-10 | COMP | 2019-11-04 | NOTN | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-12-21 | COMP | Other | 29 | 96 |  | 18 | 1 | 32 | 186
11841 | 2019-03-28 | 2019-05-14 | 2019-06-01 | 2019-06-01 | COMP | 2019-08-06 | COMP | 2019-08-07 | COMP | 2019-07-31 | COMP | 2019-10-15 | COMP | Rule 16 | 34 | 13 | 46 | 2 | 0 | 49 | 141
11849 | 2019-03-28 | 2019-05-14 | 2019-09-18 | 2019-09-18 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2021-12-06 | COMP | 2022-01-11 | COMP | Rule 16 | 34 | 89 | 272 | 1 | 286 | 27 | 704
12020 | 2019-03-28 | 2019-05-21 | 2019-08-14 | 2019-08-14 | COMP | 2019-08-26 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-11-15 | COMP | Rule 16 | 39 | 60 | 9 | 50 | 1 | 9 | 163
12179 | 2019-03-28 | 2019-05-28 | 2019-08-09 | 2019-08-09 | COMP | 2019-09-12 | COMP | 2020-05-06 | COMP | 2020-06-16 | COMP | 2020-07-27 | COMP | Rule 16 | 43 | 53 | 24 | 163 | 29 | 30 | 337
12263 | 2019-03-28 | 2019-05-30 | 2019-11-14 | 2020-06-01 | COMP | 2020-06-18 | COMP | 2020-06-22 | COMP | 2020-07-14 | COMP | 2020-08-10 | COMP | Rule 16 | 45 | 118 | 14 | 3 | 17 | 20 | 347
12514 | 2019-03-28 | 2019-06-11 | 2019-09-10 | 2019-09-10 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-12-16 | COMP | 2020-02-14 | COMP | Rule 16 | 53 | 64 | 39 | 1 | 29 | 42 | 223
12710 | 2019-03-28 | 2019-06-19 | 2019-09-17 | 2019-09-17 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-12-10 | COMP | Rule 16 | 59 | 63 | 9 | 1 | 1 | 50 | 178
12751 | 2019-03-28 | 2019-06-20 | 2019-09-30 | 2019-09-30 | COMP | 2020-03-18 | COMP | 2020-01-27 | COMP | 2020-03-16 | COMP | 2020-06-11 | COMP | Rule 16 | 60 | 71 | 116 |  | 35 | 63 | 305
12786 | 2019-03-28 | 2019-06-21 | 2019-09-16 | 2019-09-16 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-25 | COMP | 2019-12-17 | COMP | Rule 15/16 | 61 | 60 | 17 | 1 | 14 | 35 | 183
12897 | 2019-03-28 | 2019-06-27 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-21 | COMP | 2020-01-17 | COMP | 2020-09-01 | COMP | 2020-10-11 | COMP | Rule 16 | 65 | 93 | 11 | 38 | 160 | 28 | 390
12961 | 2019-03-28 | 2019-07-01 | 2019-10-28 | 2019-10-28 | COMP | 2020-07-31 | COMP | 2021-01-11 | COMP | 2021-03-23 | COMP | 2021-04-23 | COMP | Rule 15/16 | 67 | 84 | 192 | 111 | 50 | 24 | 523
13314 | 2019-03-28 | 2019-07-20 | 2019-09-27 | 2019-09-30 | COMP | 2019-10-15 | COMP | 2020-02-19 | COMP | 2020-01-23 | COMP | 2020-06-12 | COMP | Rule 15/16 | 80 | 49 | 12 | 85 | 0 | 82 | 306
13765 | 2019-03-28 | 2019-08-08 | 2020-01-16 | 2020-01-16 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-09-02 | COMP | 2020-09-25 | COMP | Rule 16 | 94 | 110 | 156 | 1 | 7 | 17 | 380
13987 | 2019-03-28 | 2019-08-20 | 2019-09-14 | 2019-09-14 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | 2019-11-04 | COMP | 2019-11-20 | COMP | Rule 16 | 102 | 18 | 7 | 2 | 29 | 12 | 166
14349 | 2019-03-28 | 2019-09-07 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-04 | COMP | 2019-11-14 | COMP | 2020-03-31 | COMP | 2020-05-18 | COMP | Rule 16 | 114 | 26 | 16 | 8 | 93 | 35 | 288
14659 | 2019-03-28 | 2019-09-21 | 2020-02-04 | 2020-03-18 | COMP | 2020-04-13 | COMP | 2020-08-10 | COMP | 2020-12-01 | COMP | 2021-02-19 | COMP | Rule 16 | 124 | 91 | 19 | 85 | 78 | 55 | 478
14675 | 2019-03-28 | 2019-09-23 | 2020-03-31 | 2020-03-31 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-08-31 | COMP | 2020-10-19 | COMP | Rule 16 | 125 | 130 | 122 | 1 | 0 | 22 | 396
14958 | 2019-03-28 | 2019-10-07 | 2019-11-14 | 2019-11-14 | COMP | 2019-12-03 | COMP | 2019-12-09 | COMP | 2020-01-31 | COMP | 2020-07-14 | COMP | Rule 15/16 | 135 | 28 | 12 | 5 | 37 | 116 | 328
15421 | 2019-03-28 | 2019-10-31 | 2020-03-26 | 2020-03-26 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2022-01-30 | INPR | 2020-12-03 | COMP | Rule 16 | 153 | 99 | 91 | 1 |  |  | 426
15508 | 2019-03-28 | 2019-11-05 | 2020-01-10 | 2020-11-13 | COMP | 2021-02-10 | COMP | 2021-03-09 | COMP | 2021-07-02 | COMP | 2022-03-31 | COMP | Rule 16 | 156 | 44 | 59 | 19 | 83 | 188 | 759
10844 | 2019-03-29 | 2019-04-02 | 2019-10-21 | 2019-10-21 | COMP | 2020-02-21 | COMP | 2020-05-08 | COMP | 2020-10-23 | COMP | 2020-11-20 | COMP | Rule 16 | 3 | 142 | 83 | 56 | 119 | 20 | 418
10874 | 2019-03-29 | 2019-04-03 | 2019-05-24 | 2019-05-24 | COMP | 2019-05-24 | NOTN | 2019-07-09 | COMP | 2019-05-29 | COMP | 2019-11-06 | COMP | Other | 4 | 38 |  | 31 | 0 | 86 | 156
10896 | 2019-03-29 | 2019-04-03 | 2019-06-19 | 2019-06-19 | COMP | 2021-02-07 | NOTN | 2022-09-16 | COMP | 2022-01-24 | COMP | 2023-01-24 | COMP | Other | 4 | 55 |  | 818 | 0 | 87 | 961
11197 | 2019-03-29 | 2019-04-17 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-26 | COMP | 2019-10-07 | COMP | 2023-05-27 | INPR | 2019-12-10 | COMP | Rule 16 | 14 | 81 | 12 | 30 |  |  | 177
11300 | 2019-03-29 | 2019-04-22 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-16 | COMP | 2019-10-02 | COMP | 2020-12-07 | COMP | 2020-07-11 | COMP | Rule 16 | 17 | 42 | 19 | 56 | 297 |  | 325
11368 | 2019-03-29 | 2019-04-24 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-12-22 | COMP | 2020-01-24 | COMP | Rule 16 | 19 | 71 | 6 | 1 | 91 | 22 | 207
11582 | 2019-03-29 | 2019-05-04 | 2019-08-16 | 2019-08-16 | COMP | 2019-11-05 | COMP | 2019-11-05 | NOTN | 2019-11-12 | COMP | 2019-11-26 | COMP | Rule 16 | 26 | 73 | 57 |  |  |  | 169
11590 | 2019-03-29 | 2019-05-03 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-08-06 | COMP | 2019-08-09 | COMP | Rule 16 | 26 | 40 | 4 | 1 | 24 | 4 | 94
11684 | 2019-03-29 | 2019-05-07 | 2019-08-04 | 2019-09-03 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-12-02 | COMP | 2020-04-01 | COMP | Rule 16 | 28 | 62 | 5 | 1 | 58 | 84 | 254
11879 | 2019-03-29 | 2019-05-15 | 2019-07-24 | 2019-07-24 | COMP | 2019-09-12 | COMP | 2019-09-20 | COMP | 2019-11-12 | COMP | 2020-02-11 | COMP | Rule 16 | 34 | 49 | 36 | 7 | 37 | 61 | 219
12239 | 2019-03-29 | 2019-05-30 | 2019-11-18 | 2019-11-18 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP |  | INPR | 2020-08-14 | COMP | Rule 15/16 | 44 | 120 | 139 | 1 |  |  | 350
12245 | 2019-03-29 | 2019-05-29 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-11-22 | COMP | 2019-12-16 | COMP | Rule 15/16 | 43 | 92 | 14 | 1 | 21 | 15 | 181
12246 | 2019-03-29 | 2019-05-29 | 2019-10-03 | 2020-03-16 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2021-01-07 | COMP | 2021-02-04 | COMP | Rule 16 | 43 | 90 |  | 1 | 231 | 20 | 467
12323 | 2019-03-29 | 2019-05-31 | 2019-07-13 | 2019-07-13 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-09-05 | COMP | 2019-10-21 | COMP | Rule 16 | 45 | 30 | 10 | 1 | 29 | 33 | 144
12363 | 2019-03-29 | 2019-06-03 | 2019-09-16 | 2019-11-04 | COMP | 2019-11-15 | COMP | 2019-11-26 | COMP | 2022-07-30 | INPR | 2020-07-08 | COMP | Rule 16 | 46 | 74 | 9 | 8 |  |  | 323
12622 | 2019-03-29 | 2019-06-18 | 2019-07-09 | 2021-03-16 | COMP | 2021-03-29 | COMP | 2019-10-03 | COMP | 2021-03-30 | COMP | 2021-05-11 | COMP | Rule 16 | 57 | 15 | 10 |  | 373 | 31 | 534
13257 | 2019-03-29 | 2019-07-17 | 2019-10-08 | 2019-10-08 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2021-10-23 | INPR | 2020-04-16 | COMP | Rule 16 | 77 | 59 | 85 | 1 |  |  | 265
13482 | 2019-03-29 | 2019-07-26 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-15 | COMP | 2019-10-22 | COMP | 2020-04-26 | INPR | 2020-01-10 | COMP | Rule 16 | 84 | 48 | 10 | 6 |  |  | 198
14008 | 2019-03-29 | 2019-08-20 | 2020-01-28 | 2020-01-28 | COMP | 2020-03-31 | COMP | 2020-07-02 | COMP | 2020-10-13 | COMP | 2020-12-09 | COMP | Rule 16 | 101 | 109 | 45 | 67 | 73 | 39 | 429
14429 | 2019-03-29 | 2019-09-09 | 2019-10-19 | 2019-10-19 | COMP | 2020-01-17 | COMP | 2022-02-15 | COMP | 2022-03-08 | COMP | 2022-04-06 | COMP | Rule 16 | 114 | 30 | 60 | 525 | 15 | 22 | 762
11382 | 2019-03-30 | 2019-04-24 | 2019-11-19 | 2019-11-19 | COMP | 2019-12-05 | COMP | 2020-03-24 | COMP | 2020-06-19 | COMP | 2020-08-14 | COMP | Rule 15/16 | 18 | 146 | 11 | 75 | 63 | 41 | 349
12473 | 2019-03-30 | 2019-06-10 | 2019-10-14 | 2019-10-14 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2019-12-23 | COMP | 2020-01-27 | COMP | Rule 16 | 50 | 89 | 34 | 1 | 15 | 23 | 207
11739 | 2019-03-31 | 2019-05-09 | 2019-08-27 | 2019-08-27 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-02-29 | COMP | 2020-08-10 | COMP | Rule 16 | 29 | 77 | 37 | 1 | 90 | 115 | 345
12953 | 2019-03-31 | 2019-07-01 | 2019-10-27 | 2019-10-27 | COMP | 2019-11-05 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-03-05 | COMP | Rule 16 | 65 | 83 | 7 | 56 | 1 | 26 | 234
14425 | 2019-03-31 | 2019-09-10 | 2019-09-13 | 2019-09-13 | COMP | 2019-09-26 | COMP | 2019-10-22 | COMP | 2019-09-27 | COMP | 2019-11-22 | COMP | Rule 16 | 114 | 4 | 10 | 19 | 0 | 23 | 166
14896 | 2019-03-31 | 2019-10-03 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-01-13 | COMP | 2020-01-15 | COMP | Rule 16 | 131 | 42 | 13 | 1 | 15 | 3 | 200
4211 | 2019-04-01 | 2019-07-24 | 2019-09-30 | 2019-09-30 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-07-17 | COMP | 2020-08-25 | COMP | Rule 16 | 81 | 48 | 201 | 1 | 2 | 28 | 356
11243 | 2019-04-01 | 2019-04-18 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-06-26 | COMP | 2019-09-10 | COMP | Rule 16 | 14 | 35 | 12 | 1 | 4 | 53 | 114
11265 | 2019-04-01 | 2019-04-19 | 2019-05-16 | 2019-05-16 | COMP | 2019-06-04 | COMP | 2019-06-07 | COMP | 2019-05-20 | COMP | 2019-06-10 | COMP | Rule 16 | 15 | 20 | 13 | 4 | 0 | 2 | 50
11432 | 2019-04-01 | 2019-04-26 | 2019-07-15 | 2019-07-15 | COMP | 2019-07-22 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2019-09-09 | COMP | Rule 16 | 20 | 55 | 6 | 8 | 1 | 28 | 113
11480 | 2019-04-01 | 2019-04-29 | 2019-07-10 | 2019-07-10 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2020-10-16 | COMP | 2020-12-18 | COMP | Rule 16 | 21 | 51 | 24 | 1 | 300 | 43 | 435
11564 | 2019-04-01 | 2019-05-02 | 2020-06-29 | 2020-06-29 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-11-13 | COMP | 2020-11-30 | COMP | Rule 16 | 24 | 292 | 77 | 1 | 22 | 10 | 421
11585 | 2019-04-01 | 2019-05-03 | 2019-08-02 | 2019-08-02 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-12-10 | COMP | 2019-12-21 | COMP | Rule 16 | 25 | 64 | 54 | 1 | 36 | 9 | 184
11637 | 2019-04-01 | 2019-05-06 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-11-12 | COMP | 2019-11-22 | COMP | Rule 16 | 26 | 48 | 28 | 1 | 59 | 9 | 166
11694 | 2019-04-01 | 2019-05-08 | 2019-05-21 | 2019-05-21 | COMP | 2019-05-30 | COMP | 2019-05-30 | COMP | 2019-08-15 | COMP | 2019-09-12 | COMP | Rule 16 | 28 | 10 | 7 | 1 | 55 | 20 | 116
11792 | 2019-04-01 | 2019-05-13 | 2019-09-09 | 2019-09-09 | COMP | 2019-11-20 | COMP | 2020-03-31 | COMP | 2020-03-20 | COMP | 2020-04-04 | COMP | Rule 15/16 | 31 | 83 | 52 | 89 | 0 | 4 | 255
11814 | 2019-04-01 | 2019-05-13 | 2019-08-09 | 2019-08-09 | COMP | 2019-09-19 | COMP | 2021-12-28 | COMP | 2021-12-28 | COMP | 2022-01-24 | COMP | Rule 16 | 31 | 63 | 29 | 572 | 1 | 19 | 710
11839 | 2019-04-01 | 2019-05-14 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2021-03-27 | INPR | 2020-03-13 | COMP | Rule 15/16 | 32 | 93 | 16 | 1 |  |  | 240
11876 | 2019-04-01 | 2019-05-15 | 2019-07-29 | 2019-07-29 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2020-01-17 | COMP | 2020-02-04 | COMP | Rule 16 | 33 | 52 | 3 | 1 | 117 | 12 | 213
12043 | 2019-04-01 | 2019-05-21 | 2020-05-20 | 2020-05-20 | COMP | 2020-11-05 | COMP | 2020-12-22 | COMP | 2021-02-08 | COMP | 2021-04-14 | COMP | Rule 15/16 | 37 | 252 | 120 | 31 | 32 | 47 | 514
12335 | 2019-04-01 | 2019-05-31 | 2019-06-17 | 2019-06-17 | COMP | 2019-09-04 | COMP | 2019-09-04 | NOTN | 2019-10-09 | COMP | 2019-10-17 | COMP | Rule 16 | 44 | 12 | 56 |  |  |  | 141
12425 | 2019-04-01 | 2019-06-06 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-09-03 | COMP | 2019-09-09 | COMP | Rule 16 | 48 | 41 | 9 | 1 | 14 | 5 | 113
12510 | 2019-04-01 | 2019-06-10 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-24 | COMP | 2021-02-05 | COMP | 2021-05-11 | COMP | 2021-05-19 | COMP | Rule 15/16 | 50 | 243 | 21 | 156 | 67 | 7 | 539
12816 | 2019-04-01 | 2019-06-24 | 2019-08-14 | 2019-08-27 | COMP | 2019-09-12 | COMP | 2019-11-04 | COMP | 2020-01-16 | COMP | 2020-07-02 | COMP | Rule 16 | 60 | 37 | 12 | 38 | 49 | 118 | 318
13074 | 2019-04-01 | 2019-07-10 | 2019-09-21 | 2019-09-24 | COMP | 2019-11-27 | COMP | 2019-12-03 | COMP | 2020-01-13 | COMP | 2020-02-05 | COMP | Rule 16 | 71 | 52 | 46 | 3 | 28 | 17 | 214
13302 | 2019-04-01 | 2019-07-18 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-09-02 | COMP | 2020-10-02 | COMP | Rule 16 | 77 | 103 | 14 | 1 | 171 | 22 | 383
13333 | 2019-04-01 | 2019-07-23 | 2020-02-26 | 2020-02-26 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-09 | COMP | 2020-06-24 | COMP | Rule 16 | 80 | 149 | 65 | 1 | 10 | 12 | 312
13437 | 2019-04-01 | 2019-07-25 | 2019-09-03 | 2019-09-07 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-04-26 | INPR | 2020-01-08 | COMP | Rule 16 | 82 | 28 | 65 | 1 |  |  | 195
13529 | 2019-04-01 | 2019-07-30 | 2019-12-19 | 2019-12-19 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-07-30 | COMP | 2020-08-12 | COMP | Rule 16 | 85 | 99 | 130 | 1 | 27 | 10 | 347
13603 | 2019-04-01 | 2019-08-02 | 2020-01-07 | 2021-12-08 | COMP | 2022-01-03 | COMP | 2023-03-15 | COMP | 2022-01-04 | COMP | 2023-05-09 | COMP | Rule 15/16 | 88 | 107 | 19 | 300 | 0 | 40 | 1034
13804 | 2019-04-01 | 2019-08-12 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-18 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-02-20 | COMP | Rule 16 | 94 | 57 | 13 | 40 | 1 | 24 | 224
13892 | 2019-04-01 | 2019-08-15 | 2019-09-25 | 2021-02-27 | INPR | 2019-10-23 | COMP | 2019-10-23 | COMP | 2020-02-05 | COMP | 2020-02-08 | COMP | Unknown | 97 |  |  |  | 70 | 3 | 216
14422 | 2019-04-01 | 2019-09-10 | 2019-09-17 | 2019-09-17 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-23 | COMP | Rule 16 | 114 | 6 | 105 | 1 | 1 | 24 | 246
14751 | 2019-04-01 | 2019-09-25 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2020-09-22 | COMP | 2020-11-11 | COMP | Rule 16 | 125 | 76 | 21 | 1 | 156 | 36 | 410
15134 | 2019-04-01 | 2019-10-15 | 2020-02-03 | 2020-02-03 | COMP | 2021-02-03 | COMP | 2021-03-09 | COMP | 2021-02-10 | COMP | 2021-05-12 | COMP | Rule 16 | 139 | 74 | 254 | 24 | 0 | 47 | 534
16197 | 2019-04-01 | 2019-12-13 | 2020-05-22 | 2021-02-22 | COMP | 2021-02-26 | COMP | 2020-08-07 | COMP | 2021-03-15 | COMP | 2021-04-06 | COMP | Rule 16 | 179 | 112 | 5 |  | 149 | 17 | 508
16844 | 2019-04-01 | 2020-01-22 | 2020-05-29 | 2020-08-12 | COMP | 2020-09-21 | COMP | 2021-03-24 | COMP | 2021-03-30 | COMP | 2021-05-04 | COMP | Rule 15/16 | 204 | 91 | 28 | 126 | 5 | 26 | 528
17583 | 2019-04-01 | 2020-02-20 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-09-09 | COMP | 2020-09-22 | COMP | Rule 16 | 224 | 77 | 8 | 1 | 60 | 10 | 375
19707 | 2019-04-01 | 2020-05-19 | 2020-07-27 | 2020-07-27 | COMP | 2020-11-12 | COMP | 2020-11-12 | COMP | 2020-11-24 | COMP | 2020-12-09 | COMP | Rule 16 | 287 | 49 | 77 | 1 | 9 | 10 | 428
27218 | 2019-04-01 | 2021-04-20 | 2021-04-21 | 2021-04-21 | COMP | 2021-04-21 | NOTN | 2021-05-05 | COMP | 2021-05-05 | COMP | 2021-05-12 | COMP | Other | 518 | 2 |  | 11 | 1 | 6 | 534
10917 | 2019-04-02 | 2019-04-05 | 2019-04-18 | 2019-04-18 | COMP | 2019-04-30 | COMP | 2019-05-10 | COMP | 2019-06-04 | COMP | 2019-06-12 | COMP | Rule 16 | 4 | 10 | 9 | 9 | 17 | 7 | 51
11090 | 2019-04-02 | 2019-04-12 | 2019-07-09 | 2019-07-09 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-03-29 | INPR | 2019-12-05 | COMP | Rule 16 | 9 | 61 | 74 | 1 |  |  | 172
11110 | 2019-04-02 | 2019-04-12 | 2019-07-31 | 2019-08-28 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-12-06 | COMP | 2019-12-13 | COMP | Other | 9 | 77 | 46 | 1 | 24 | 6 | 178
11373 | 2019-04-02 | 2019-04-24 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-12-18 | COMP | 2020-03-12 | COMP | Rule 16 | 17 | 73 | 18 | 1 | 76 | 58 | 238
11487 | 2019-04-02 | 2019-04-30 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-09 | COMP | 2019-08-12 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | Rule 16 | 21 | 43 | 6 | 25 | 31 | 2 | 124
11555 | 2019-04-02 | 2019-05-02 | 2019-10-10 | 2019-10-10 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2019-10-17 | COMP | 2019-10-29 | COMP | Rule 16 | 23 | 113 | 5 | 1 | 2 | 9 | 148
11604 | 2019-04-02 | 2019-05-04 | 2019-07-01 | 2019-07-09 | COMP | 2019-07-09 | NOTN | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-08-19 | COMP | Other | 24 | 40 |  | 1 | 1 | 30 | 98
11638 | 2019-04-02 | 2019-05-06 | 2019-12-07 | 2019-12-07 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2021-10-23 | INPR | 2020-08-20 | COMP | Rule 15/16 | 25 | 149 | 132 | 1 |  |  | 352
11697 | 2019-04-02 | 2019-05-08 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-11 | COMP | 2019-06-11 | COMP | 2019-08-02 | COMP | 2019-08-05 | COMP | Rule 16 | 27 | 21 | 4 | 1 | 38 | 2 | 88
11781 | 2019-04-02 | 2019-05-10 | 2019-10-23 | 2020-06-17 | COMP | 2020-06-22 | COMP | 2020-06-24 | COMP | 2020-06-23 | COMP | 2020-08-13 | COMP | Rule 16 | 29 | 116 | 4 | 3 | 0 | 37 | 347
11826 | 2019-04-02 | 2019-05-13 | 2019-09-15 | 2019-09-15 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-06-09 | COMP | 2020-08-05 | COMP | Rule 15/16 | 30 | 87 | 127 | 1 | 58 | 42 | 341
11916 | 2019-04-02 | 2019-05-16 | 2019-07-03 | 2019-07-03 | COMP | 2019-07-10 | COMP | 2019-07-10 | COMP | 2019-08-01 | COMP | 2019-08-09 | COMP | Rule 16 | 33 | 34 | 5 | 1 | 17 | 7 | 92
11956 | 2019-04-02 | 2019-05-19 | 2019-05-31 | 2019-05-31 | COMP | 2019-06-13 | COMP | 2019-06-13 | COMP | 2020-02-29 | INPR | 2019-10-22 | COMP | Rule 16 | 34 | 9 | 10 | 1 |  |  | 143
12034 | 2019-04-02 | 2019-05-21 | 2019-09-12 | 2019-09-12 | COMP | 2019-10-02 | COMP | 2019-10-17 | COMP | 2019-11-20 | COMP | 2019-12-09 | COMP | Rule 16 | 36 | 80 | 15 | 12 | 24 | 12 | 174
12095 | 2019-04-02 | 2019-05-23 | 2019-07-02 | 2019-07-02 | COMP | 2019-08-19 | COMP | 2019-12-06 | COMP |  |  | 2019-12-12 | COMP | Rule 16 | 38 | 28 | 34 | 76 |  |  | 177
12096 | 2019-04-02 | 2019-05-23 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-29 | COMP | 2019-11-27 | COMP |  |  | 2019-12-12 | COMP | Rule 16 | 38 | 38 | 32 | 63 |  |  | 177
12106 | 2019-04-02 | 2019-05-23 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | Rule 16 | 38 | 38 | 8 | 1 | 34 | 1 | 115
12354 | 2019-04-02 | 2019-06-03 | 2019-08-21 | 2019-08-21 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2021-02-22 | COMP | 2021-03-18 | COMP | Rule 16 | 44 | 57 | 58 | 1 | 320 | 19 | 494
12549 | 2019-04-02 | 2019-06-12 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-12 | COMP | 2019-09-13 | COMP | Rule 16 | 51 | 22 | 21 | 1 | 2 | 24 | 116
12561 | 2019-04-02 | 2019-06-12 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2019-07-10 | COMP | 2019-10-01 | COMP | Rule 16 | 51 | 12 | 5 | 1 | 5 | 59 | 128
12583 | 2019-04-02 | 2019-06-14 | 2019-11-04 | 2019-11-04 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2020-02-10 | COMP | Other | 53 | 100 | 22 | 1 | 1 | 44 | 216
12655 | 2019-04-02 | 2019-06-17 | 2020-03-30 | 2020-03-30 | COMP | 2021-01-06 | COMP | 2021-04-20 | COMP | 2021-04-01 | COMP | 2021-05-22 | COMP | Rule 15/16 | 54 | 197 | 196 | 73 | 0 | 24 | 540
12686 | 2019-04-02 | 2019-06-18 | 2019-08-14 | 2019-08-14 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-10-18 | COMP | 2019-10-21 | COMP | Rule 16 | 55 | 41 | 41 | 1 | 7 | 2 | 142
12868 | 2019-04-02 | 2019-06-26 | 2019-10-24 | 2019-10-24 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-14 | COMP | 2020-03-11 | COMP | Rule 16 | 61 | 85 | 49 | 1 | 28 | 18 | 237
13270 | 2019-04-02 | 2019-07-18 | 2020-02-24 | 2020-03-02 | COMP | 2020-08-24 | COMP | 2020-03-30 | COMP | 2021-04-28 | COMP | 2021-06-03 | COMP | Rule 16 | 76 | 150 | 125 |  | 274 | 26 | 548
13713 | 2019-04-02 | 2019-08-06 | 2020-03-13 | 2020-03-13 | COMP | 2020-03-31 | COMP | 2020-05-22 | COMP | 2020-11-19 | COMP | 2020-12-29 | COMP | Rule 15/16 | 89 | 151 | 13 | 39 | 127 | 26 | 440
13877 | 2019-04-02 | 2019-08-14 | 2019-12-03 | 2019-12-03 | COMP | 2020-07-03 | COMP | 2020-10-30 | COMP | 2020-11-16 | NOTN | 2020-12-18 | COMP | Rule 16 | 95 | 76 | 149 | 85 |  |  | 434
14293 | 2019-04-02 | 2019-09-03 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-19 | COMP | 2020-03-12 | COMP | 2020-03-10 | COMP | 2020-04-08 | COMP | Rule 16 | 108 | 32 | 24 | 77 | 0 | 20 | 257
14782 | 2019-04-02 | 2019-09-27 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | 2019-11-22 | COMP | Rule 16 | 126 | 16 | 4 | 1 | 19 | 4 | 165
14906 | 2019-04-02 | 2019-10-02 | 2020-01-06 | 2020-01-06 | COMP | 2020-02-18 | COMP | 2020-02-20 | COMP | 2020-05-21 | COMP | 2020-07-13 | COMP | Rule 16 | 129 | 64 | 30 | 3 | 66 | 37 | 324
14919 | 2019-04-02 | 2019-10-05 | 2019-11-18 | 2020-02-13 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-03-23 | COMP | 2020-04-09 | COMP | Rule 15/16 | 131 | 30 | 31 | 1 | 0 | 10 | 258
15095 | 2019-04-02 | 2019-10-12 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-16 | COMP | 2020-03-04 | COMP | 2020-03-06 | COMP | 2020-07-10 | COMP | Rule 16 | 136 | 60 | 5 | 33 | 3 | 90 | 323
15952 | 2019-04-02 | 2019-12-03 | 2019-12-30 | 2019-12-30 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-20 | COMP | 2020-06-12 | COMP | Rule 16 | 170 | 19 | 88 | 1 | 13 | 17 | 303
16340 | 2019-04-02 | 2019-12-23 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-09 | COMP | 2020-04-06 | COMP | 2020-07-21 | COMP | 2021-02-02 | COMP | Rule 16 | 184 | 35 | 18 | 21 | 76 | 134 | 463
16661 | 2019-04-02 | 2020-01-10 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-05-05 | COMP | 2020-06-20 | COMP | Rule 15/16 | 196 | 24 | 11 | 1 | 48 | 33 | 308
16662 | 2019-04-02 | 2020-01-10 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-28 | COMP | 2020-06-15 | COMP | 2020-06-16 | COMP | 2020-06-21 | COMP | Rule 16 | 196 | 24 | 11 | 76 | 2 | 4 | 308
17394 | 2019-04-02 | 2020-02-12 | 2020-06-13 | 2021-04-13 | COMP | 2021-04-27 | COMP | 2021-10-13 | COMP | 2021-10-19 | COMP | 2021-11-30 | COMP | Rule 16 | 218 | 86 | 11 | 119 | 5 | 28 | 671
17940 | 2019-04-02 | 2020-03-05 | 2020-07-25 | 2020-07-25 | COMP | 2020-08-24 | COMP | 2021-01-07 | COMP | 2021-01-12 | COMP | 2021-03-05 | COMP | Rule 16 | 233 | 101 | 21 | 93 | 4 | 37 | 485
21117 | 2019-04-02 | 2020-07-23 | 2020-09-10 | 2020-09-10 | COMP | 2020-12-22 | COMP | 2021-03-11 | COMP | 2021-11-06 | COMP | 2022-02-24 | COMP | Rule 16 | 332 | 35 | 71 | 54 | 169 | 74 | 731
11131 | 2019-04-03 | 2019-04-15 | 2019-08-26 | 2019-08-26 | COMP | 2022-08-25 | COMP | 2023-03-03 | COMP | 2020-05-13 | COMP | 2023-08-04 | COMP | Rule 15/16 | 9 | 94 | 756 | 129 | 0 | 108 | 1092
11150 | 2019-04-03 | 2019-04-15 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-08-19 | COMP | 2019-09-04 | COMP | 2019-09-26 | COMP | Rule 16 | 9 | 52 | 4 | 35 | 12 | 17 | 124
11200 | 2019-04-03 | 2019-04-17 | 2019-07-19 | 2019-07-19 | COMP | 2021-03-05 | COMP | 2021-03-05 | COMP | 2021-07-07 | COMP | 2021-08-03 | COMP | Rule 16 | 11 | 66 | 409 | 1 | 87 | 20 | 589
11489 | 2019-04-03 | 2019-04-29 | 2019-06-27 | 2019-06-27 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-08-31 | COMP | Rule 16 | 19 | 43 | 43 | 1 | 1 | 4 | 106
11616 | 2019-04-03 | 2019-05-06 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-02 | COMP | 2020-05-22 | COMP | 2020-09-08 | COMP | 2020-10-15 | COMP | Rule 16 | 24 | 92 | 13 | 161 | 76 | 28 | 390
11644 | 2019-04-03 | 2019-05-07 | 2019-08-22 | 2019-08-22 | COMP | 2019-05-07 | NOTN | 2019-08-22 | COMP | 2019-09-17 | COMP | 2019-10-14 | COMP | Other | 25 | 76 |  | 1 | 18 | 20 | 136
11692 | 2019-04-03 | 2019-05-08 | 2019-07-17 | 2019-09-09 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2021-01-02 | INPR | 2019-12-10 | COMP | Rule 16 | 26 | 49 | 53 | 1 |  |  | 174
11858 | 2019-04-03 | 2019-05-14 | 2019-06-25 | 2019-06-25 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-12-29 | INPR | 2019-08-14 | COMP | Rule 16 | 30 | 30 | 27 | 1 |  |  | 94
11895 | 2019-04-03 | 2019-05-15 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-15 | COMP | 2019-09-05 | COMP | 2019-08-19 | COMP | 2019-09-27 | COMP | Rule 15/16 | 31 | 56 | 9 | 15 | 0 | 17 | 125
12062 | 2019-04-03 | 2019-05-23 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-24 | COMP | 2019-10-23 | COMP | 2019-11-05 | COMP | 2019-12-06 | COMP | Rule 16 | 37 | 35 | 9 | 65 | 10 | 21 | 172
12406 | 2019-04-03 | 2019-06-05 | 2019-07-19 | 2019-07-19 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-04-21 | COMP | 2020-06-21 | COMP | Rule 16 | 45 | 32 | 112 | 1 | 79 | 43 | 307
12590 | 2019-04-03 | 2019-06-14 | 2019-11-01 | 2019-11-01 | COMP | 2020-01-27 | COMP | 2020-03-02 | COMP | 2020-02-21 | COMP | 2020-03-24 | COMP | Rule 16 | 52 | 99 | 56 | 25 | 0 | 17 | 245
12626 | 2019-04-03 | 2019-06-17 | 2019-08-21 | 2019-10-30 | COMP | 2019-11-06 | COMP | 2020-01-08 | COMP | 2023-04-30 | INPR | 2020-02-26 | COMP | Rule 16 | 53 | 47 | 6 | 41 |  |  | 226
12628 | 2019-04-03 | 2019-06-17 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-13 | COMP | 2019-10-17 | COMP | 2019-10-19 | COMP | 2020-02-06 | COMP | Rule 16 | 53 | 33 | 9 | 47 | 2 | 73 | 213
12696 | 2019-04-03 | 2019-06-18 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-23 | COMP | 2019-11-06 | COMP | 2019-11-04 | COMP | 2019-11-05 | COMP | Rule 16 | 54 | 15 | 11 | 76 | 0 |  | 152
13376 | 2019-04-03 | 2019-07-23 | 2019-08-27 | 2019-10-18 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-12-06 | COMP | 2019-12-19 | COMP | Rule 16 | 78 | 26 | 9 | 1 | 25 | 10 | 181
13695 | 2019-04-03 | 2019-08-06 | 2019-09-07 | 2019-09-07 | COMP | 2019-09-19 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-11-22 | COMP | Rule 16 | 88 | 23 | 9 | 2 | 1 | 45 | 164
13822 | 2019-04-03 | 2019-08-12 | 2020-01-10 | 2020-01-10 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-11-12 | COMP | Rule 16 | 92 | 104 | 195 | 1 | 1 | 21 | 409
13832 | 2019-04-03 | 2019-08-12 | 2019-10-05 | 2019-10-05 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-02-10 | NOTN | 2020-02-27 | COMP | Rule 16 | 92 | 39 | 79 | 1 |  |  | 227
14231 | 2019-04-03 | 2019-08-29 | 2019-11-20 | 2020-10-13 | COMP | 2020-12-03 | COMP | 2021-01-04 | COMP | 2021-03-23 | COMP | 2021-04-24 | COMP | Rule 16 | 105 | 58 | 35 | 21 | 55 | 24 | 519
14518 | 2019-04-03 | 2019-09-13 | 2019-10-01 | 2020-12-22 | COMP | 2021-01-04 | COMP | 2021-04-05 | COMP | 2023-11-12 | INPR | 2022-07-07 | COMP | Rule 16 | 115 | 13 | 8 | 64 |  |  | 822
14811 | 2019-04-03 | 2019-09-28 | 2020-07-20 | 2020-10-29 | COMP | 2020-12-04 | COMP | 2021-01-21 | COMP | 2021-02-22 | COMP | 2021-05-07 | COMP | Rule 16 | 125 | 203 | 24 | 32 | 22 | 55 | 529
14849 | 2019-04-03 | 2019-09-30 | 2019-11-23 | 2019-11-23 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-01-03 | COMP | 2020-01-31 | COMP | Rule 16 | 126 | 39 | 16 | 1 | 11 | 20 | 209
15008 | 2019-04-03 | 2019-10-08 | 2020-02-12 | 2020-02-12 | COMP | 2020-09-22 | COMP | 2020-10-14 | COMP | 2020-09-29 | COMP | 2020-11-06 | COMP | Rule 16 | 132 | 86 | 157 | 17 | 0 | 18 | 406
16077 | 2019-04-03 | 2019-12-09 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-20 | COMP | 2020-06-05 | COMP | 2020-06-22 | COMP | 2020-08-26 | COMP | Rule 16 | 173 | 88 | 5 | 34 | 12 | 48 | 355
18971 | 2019-04-03 | 2020-04-15 | 2020-08-15 | 2020-08-15 | COMP | 2020-12-03 | COMP | 2020-12-03 | COMP | 2021-06-28 | COMP | 2021-07-12 | COMP | Rule 16 | 261 | 87 | 75 | 1 | 143 | 10 | 573
26911 | 2019-04-03 | 2021-04-07 | 2021-05-22 | 2021-07-28 | COMP | 2021-09-30 | COMP | 2021-09-30 | COMP | 2021-10-25 | COMP | 2022-01-12 | COMP | Rule 16 | 507 | 33 | 46 | 1 | 18 | 55 | 701
4212 | 2019-04-04 | 2019-07-25 | 2019-10-18 | 2019-10-11 | COMP | 2020-01-08 | COMP | 2020-07-02 | COMP | 2020-08-07 | COMP | 2020-10-01 | COMP | Rule 16 | 79 | 61 | 59 | 124 | 27 | 39 | 379
4261 | 2019-04-04 | 2019-12-21 | 2021-01-07 | 2021-01-07 | COMP | 2021-02-19 | COMP | 2021-02-19 | COMP | 2023-07-29 | INPR | 2021-04-28 | COMP | Rule 15/16 | 181 | 263 | 30 | 1 |  |  | 521
11222 | 2019-04-04 | 2019-04-19 | 2019-09-06 | 2019-09-06 | COMP | 2019-04-19 | NOTN | 2019-12-11 | COMP | 2019-11-27 | COMP | 2020-08-13 | COMP | Other | 12 | 98 |  | 66 | 0 | 172 | 345
11354 | 2019-04-04 | 2019-04-24 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-06-14 | COMP | 2019-08-23 | COMP | Rule 16 | 15 | 21 | 15 | 1 | 3 | 50 | 100
11383 | 2019-04-04 | 2019-04-24 | 2019-08-05 | 2019-08-05 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-09-04 | COMP | 2019-10-25 | COMP | Rule 16 | 15 | 72 | 21 | 1 | 2 | 38 | 144
11428 | 2019-04-04 | 2019-04-27 | 2019-06-06 | 2019-06-06 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2020-02-29 | INPR | 2019-11-13 | COMP | Rule 16 | 17 | 28 | 16 | 1 |  |  | 156
11492 | 2019-04-04 | 2019-04-30 | 2019-08-12 | 2019-08-12 | COMP | 2020-05-12 | COMP | 2019-11-14 | COMP | 2019-10-24 | COMP | 2019-12-05 | COMP | Rule 16 | 19 | 73 | 189 |  | 0 | 14 | 170
11529 | 2019-04-04 | 2019-05-01 | 2019-07-05 | 2019-07-05 | COMP | 2019-07-15 | NOTN | 2019-08-27 | COMP | 2019-08-06 | COMP | 2019-10-16 | COMP | Other | 20 | 46 |  | 38 | 0 | 36 | 137
11535 | 2019-04-04 | 2019-05-01 | 2019-08-05 | 2019-08-05 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-07-06 | COMP | 2020-09-30 | COMP | Rule 16 | 20 | 67 | 231 | 1 | 2 | 62 | 378
11566 | 2019-04-04 | 2019-05-02 | 2019-06-08 | 2019-06-08 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2019-09-05 | COMP | 2019-09-25 | COMP | Rule 16 | 21 | 26 | 50 | 1 | 13 | 15 | 122
11780 | 2019-04-04 | 2019-05-10 | 2019-06-03 | 2019-06-03 | COMP | 2019-06-12 | COMP | 2019-06-12 | COMP | 2019-06-17 | COMP | 2019-06-24 | COMP | Rule 15/16 | 27 | 16 | 8 | 1 | 4 | 6 | 57
11794 | 2019-04-04 | 2019-05-13 | 2019-08-16 | 2019-08-16 | COMP | 2019-08-26 | COMP | 2019-09-25 | COMP | 2019-09-24 | COMP | 2019-10-25 | COMP | Rule 16 | 28 | 68 | 7 | 22 | 0 | 23 | 144
12056 | 2019-04-04 | 2019-05-22 | 2019-08-27 | 2019-08-27 | COMP | 2019-09-09 | COMP | 2019-09-18 | COMP | 2020-02-29 | INPR | 2019-10-18 | COMP | Rule 15/16 | 35 | 68 | 9 | 8 |  |  | 139
12117 | 2019-04-04 | 2019-05-23 | 2019-06-19 | 2019-06-19 | COMP | 2019-06-21 | COMP | 2019-06-25 | COMP | 2019-10-07 | COMP | 2019-11-13 | COMP | Rule 16 | 36 | 19 | 3 | 3 | 73 | 27 | 156
12128 | 2019-04-04 | 2019-05-23 | 2019-09-14 | 2019-09-14 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2020-07-08 | COMP | 2020-08-19 | COMP | Rule 16 | 36 | 79 | 37 | 1 | 169 | 31 | 349
12146 | 2019-04-04 | 2019-05-24 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-25 | COMP | 2019-11-01 | COMP | 2019-12-03 | COMP | 2019-12-05 | COMP | Rule 16 | 37 | 78 | 30 | 6 | 20 | 3 | 170
12284 | 2019-04-04 | 2019-05-31 | 2019-09-24 | 2019-09-24 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-03-30 | COMP | 2020-05-08 | COMP | Rule 16 | 41 | 81 | 110 | 1 | 19 | 30 | 277
12362 | 2019-04-04 | 2019-06-03 | 2019-09-01 | 2019-09-07 | COMP | 2019-10-16 | COMP | 2019-11-20 | COMP | 2020-02-03 | COMP | 2020-02-21 | COMP | Rule 16 | 42 | 64 | 28 | 25 | 49 | 14 | 222
12783 | 2019-04-04 | 2019-06-21 | 2019-10-10 | 2019-10-10 | COMP | 2019-10-30 | COMP | 2019-11-22 | COMP | 2020-01-21 | COMP | 2020-02-03 | COMP | Rule 16 | 56 | 78 | 15 | 17 | 38 | 10 | 209
12865 | 2019-04-04 | 2019-06-26 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-12-09 | COMP | Rule 16 | 59 | 68 | 8 | 1 | 1 | 40 | 172
13275 | 2019-04-04 | 2019-07-18 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-09 | COMP | 2019-12-17 | COMP | 2019-12-09 | COMP | 2020-01-21 | COMP | Rule 16 | 74 | 80 | 20 | 7 | 0 | 23 | 200
13984 | 2019-04-04 | 2019-08-20 | 2020-03-13 | 2020-05-21 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2021-05-04 | COMP | 2021-06-01 | COMP | Rule 16 | 97 | 141 | 33 | 1 | 208 | 20 | 544
14099 | 2019-04-04 | 2019-08-25 | 2019-11-05 | 2019-11-05 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-09-18 | COMP | 2020-10-19 | COMP | Rule 15/16 | 100 | 51 | 66 | 1 | 155 | 22 | 391
14168 | 2019-04-04 | 2019-08-28 | 2019-11-04 | 2019-11-04 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-03-02 | COMP | 2020-01-14 | COMP | Rule 16 | 103 | 48 | 11 | 1 | 69 |  | 196
14251 | 2019-04-04 | 2019-08-30 | 2019-10-20 | 2019-10-20 | COMP | 2019-12-30 | COMP | 2020-02-11 | COMP | 2023-03-16 | COMP | 2023-06-05 | COMP | Rule 16 | 105 | 35 | 47 | 30 | 779 | 57 | 1049
14856 | 2019-04-04 | 2019-10-01 | 2020-08-19 | 2020-08-19 | COMP | 2021-07-22 | COMP | 2021-07-22 | COMP | 2021-08-31 | COMP | 2021-09-21 | COMP | Rule 16 | 126 | 224 | 232 | 1 | 29 | 15 | 622
17049 | 2019-04-04 | 2020-01-30 | 2020-06-16 | 2020-06-16 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-12-22 | COMP | 2021-02-17 | COMP | Rule 16 | 207 | 97 | 55 | 1 | 78 | 38 | 471
17322 | 2019-04-04 | 2020-02-10 | 2020-08-12 | 2020-09-03 | COMP | 2020-09-22 | COMP | 2020-10-07 | COMP | 2020-10-20 | COMP | 2020-12-10 | COMP | Rule 16 | 214 | 131 | 13 | 12 | 10 | 35 | 426
21172 | 2019-04-04 | 2020-07-24 | 2020-12-14 | 2021-07-23 | COMP | 2022-02-11 | COMP | 2022-06-21 | COMP |  | INPR | 2023-06-21 | COMP | Rule 15/16 | 331 | 98 | 141 | 90 |  |  | 1060
26169 | 2019-04-04 | 2021-03-10 | 2021-04-20 | 2021-04-20 | COMP | 2021-06-22 | COMP | 2021-07-12 | COMP |  |  | 2022-12-02 | COMP | Rule 16 | 486 | 30 | 45 | 14 |  |  | 923
11273 | 2019-04-05 | 2019-04-22 | 2019-06-22 | 2019-06-22 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-11-25 | COMP | 2020-01-02 | COMP | Rule 16 | 12 | 44 | 36 | 1 | 73 | 25 | 187
11277 | 2019-04-05 | 2019-04-22 | 2019-07-11 | 2019-07-11 | COMP | 2020-03-17 | COMP | 2020-04-23 | COMP | 2020-06-16 | COMP | 2020-06-25 | COMP | Rule 16 | 12 | 57 | 171 | 28 | 38 | 8 | 309
11321 | 2019-04-05 | 2019-04-23 | 2019-05-07 | 2019-05-07 | COMP | 2019-05-15 | COMP | 2019-05-15 | NOTN | 2019-09-22 | INPR | 2019-05-21 | COMP | Rule 16 | 13 | 11 | 7 |  |  |  | 33
11393 | 2019-04-05 | 2019-04-24 | 2019-10-01 | 2019-10-01 | COMP | 2020-05-01 | COMP | 2020-12-16 | COMP | 2020-10-21 | COMP | 2021-02-12 | COMP | Rule 16 | 14 | 112 | 147 | 159 | 0 | 40 | 468
11419 | 2019-04-05 | 2019-04-26 | 2019-05-18 | 2019-05-18 | COMP | 2019-05-29 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2019-06-04 | COMP | Rule 16 | 16 | 16 | 7 | 4 | 1 | 2 | 42
11466 | 2019-04-05 | 2019-04-29 | 2019-07-03 | 2019-07-03 | COMP | 2019-11-05 | COMP | 2020-06-12 | COMP | 2020-08-18 | COMP | 2020-10-07 | COMP | Rule 16 | 17 | 47 | 88 | 151 | 48 | 36 | 382
11488 | 2019-04-05 | 2019-04-29 | 2019-06-25 | 2019-06-25 | COMP | 2019-06-28 | COMP | 2019-06-28 | COMP | 2019-07-08 | COMP | 2019-08-21 | COMP | Rule 16 | 17 | 41 | 4 | 1 | 6 | 33 | 97
11673 | 2019-04-05 | 2019-05-07 | 2019-09-24 | 2019-09-24 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2021-02-02 | COMP | 2021-03-04 | COMP | Rule 16 | 23 | 98 | 42 | 1 | 300 | 22 | 481
12016 | 2019-04-05 | 2019-05-21 | 2019-07-22 | 2019-07-22 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-10-14 | COMP | 2019-11-18 | COMP | Rule 16 | 33 | 43 | 13 | 1 | 48 | 25 | 158
12175 | 2019-04-05 | 2019-05-29 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-09-25 | COMP | 2019-11-06 | COMP | Rule 16 | 38 | 76 | 22 | 1 | 0 | 17 | 151
12367 | 2019-04-05 | 2019-06-03 | 2019-08-25 | 2019-08-25 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-11-18 | COMP | 2019-12-09 | COMP | Rule 16 | 41 | 59 | 44 | 1 | 16 | 14 | 171
12382 | 2019-04-05 | 2019-06-04 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-16 | COMP | 2019-09-03 | COMP | 2019-09-04 | COMP | 2019-10-07 | COMP | Rule 16 | 42 | 48 | 6 | 12 | 2 | 24 | 129
12575 | 2019-04-05 | 2019-06-13 | 2019-09-16 | 2019-11-21 | COMP | 2019-11-21 | NOTN | 2019-11-21 | COMP | 2019-11-14 | NOTN | 2020-02-11 | COMP | Other | 49 | 66 |  | 1 |  |  | 214
12610 | 2019-04-05 | 2019-06-14 | 2020-05-08 | 2020-05-28 | COMP | 2020-09-08 | COMP | 2022-07-08 | COMP | 2022-06-29 | COMP | 2022-09-02 | COMP | Rule 15/16 | 50 | 227 | 73 | 461 | 0 | 41 | 861
12674 | 2019-04-05 | 2019-06-19 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-10-07 | COMP | 2019-10-17 | COMP | Rule 16 | 53 | 34 | 15 | 1 | 30 | 9 | 137
12766 | 2019-04-05 | 2019-06-21 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-07 | COMP | 2020-07-02 | COMP | 2020-06-27 | COMP | 2020-07-07 | COMP | Rule 15/16 | 55 | 69 | 30 | 163 | 0 | 4 | 317
12848 | 2019-04-05 | 2019-06-25 | 2019-11-25 | 2019-12-20 | COMP | 2020-05-28 | COMP | 2020-06-24 | COMP | 2020-09-27 | COMP | 2020-12-04 | COMP | Rule 16 | 57 | 107 | 110 | 20 | 67 | 47 | 421
12906 | 2019-04-05 | 2019-06-28 | 2019-10-21 | 2019-10-21 | COMP | 2019-12-16 | COMP | 2020-02-06 | COMP | 2020-01-06 | COMP | 2020-03-04 | COMP | Rule 16 | 60 | 80 | 38 | 36 | 0 | 19 | 229
13010 | 2019-04-05 | 2019-07-05 | 2019-11-22 | 2019-11-22 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2021-04-06 | COMP | 2021-11-12 | COMP | Rule 16 | 64 | 99 | 68 | 1 | 276 | 155 | 658
13265 | 2019-04-05 | 2019-07-18 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2020-04-10 | COMP | 2020-06-05 | COMP | Rule 16 | 73 | 53 | 10 | 1 | 123 | 40 | 295
13287 | 2019-04-05 | 2019-07-18 | 2019-09-26 | 2019-12-06 | COMP | 2019-12-13 | COMP | 2019-10-02 | COMP | 2019-10-14 | COMP | 2020-01-09 | COMP | Rule 16 | 73 | 50 | 6 |  | 9 | 59 | 192
13320 | 2019-04-05 | 2019-07-19 | 2019-11-25 | 2019-11-25 | COMP | 2019-12-16 | COMP | 2020-02-13 | COMP | 2022-07-30 | INPR | 2020-03-18 | COMP | Rule 16 | 74 | 90 | 14 | 41 |  |  | 239
13321 | 2019-04-05 | 2019-07-19 | 2019-10-27 | 2019-10-27 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-01-22 | COMP | 2020-01-30 | COMP | Rule 16 | 74 | 70 | 21 | 1 | 37 | 7 | 206
13769 | 2019-04-05 | 2019-08-08 | 2019-12-04 | 2019-12-04 | COMP | 2020-05-14 | COMP | 2020-06-23 | COMP | 2020-05-28 | COMP | 2020-07-13 | COMP | Rule 16 | 88 | 81 | 113 | 28 | 0 | 15 | 321
13959 | 2019-04-05 | 2019-08-18 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-26 | COMP | 2020-11-23 | COMP |  |  | 2020-12-28 | COMP | Rule 16 | 94 | 51 | 20 | 251 |  |  | 436
14057 | 2019-04-05 | 2019-08-22 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-23 | COMP | 2020-02-19 | COMP | 2020-07-15 | COMP | 2020-10-02 | COMP | Rule 15/16 | 98 | 69 | 16 | 39 | 105 | 57 | 379
14116 | 2019-04-05 | 2019-08-26 | 2019-10-23 | 2019-10-23 | COMP | 2020-01-06 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-12 | COMP | Rule 16 | 100 | 42 | 49 | 2 | 1 | 26 | 215
14552 | 2019-04-05 | 2019-09-16 | 2020-03-13 | 2021-01-05 | COMP | 2021-10-12 | COMP | 2021-10-12 | COMP | 2022-08-15 | COMP | 2022-09-25 | COMP | Rule 15 | 114 | 123 | 196 | 1 | 212 | 29 | 875
14664 | 2019-04-05 | 2019-09-22 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-16 | COMP | 2020-02-14 | COMP | 2020-01-06 | COMP | 2020-03-16 | COMP | Rule 15/16 | 118 | 44 | 15 | 42 | 0 | 21 | 237
16039 | 2019-04-05 | 2019-12-06 | 2020-05-07 | 2020-05-07 | COMP | 2020-07-09 | COMP | 2020-07-23 | COMP | 2020-07-31 | COMP | 2020-10-12 | COMP | Rule 15/16 | 170 | 106 | 45 | 11 | 7 | 51 | 385
16133 | 2019-04-05 | 2019-12-11 | 2020-03-26 | 2020-03-26 | COMP | 2020-08-12 | COMP | 2020-08-24 | COMP | 2022-01-30 | INPR | 2020-09-03 | COMP | Rule 16 | 173 | 73 | 99 | 9 |  |  | 359
17857 | 2019-04-05 | 2020-03-02 | 2020-10-01 | 2020-10-01 | COMP | 2020-11-24 | COMP | 2021-03-02 | COMP | 2022-03-20 | INPR | 2021-03-08 | COMP | Rule 16 | 227 | 152 | 38 | 65 |  |  | 483
18298 | 2019-04-05 | 2020-03-19 | 2020-04-29 | 2020-06-30 | COMP | 2020-09-08 | COMP | 2021-04-22 | COMP | 2022-05-28 | INPR | 2021-05-11 | COMP | Rule 16 | 240 | 30 | 50 | 156 |  |  | 529
14911 | 2019-04-06 | 2019-10-03 | 2020-06-22 | 2020-06-22 | COMP | 2021-01-07 | COMP | 2021-03-17 | COMP | 2022-12-02 | COMP | 2022-03-01 | COMP | Rule 16 | 126 | 180 | 138 | 48 | 433 |  | 730
11240 | 2019-04-07 | 2019-04-19 | 2019-07-12 | 2019-07-25 | COMP | 2019-08-14 | COMP | 2019-09-24 | COMP | 2023-12-03 | INPR | 2020-01-22 | COMP | Rule 15/16 | 10 | 59 | 15 | 29 |  |  | 199
11389 | 2019-04-07 | 2019-04-24 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-27 | COMP | 2019-09-19 | COMP | 2019-10-17 | COMP | 2019-11-06 | COMP | Rule 15/16 | 13 | 73 | 16 | 17 | 21 | 15 | 150
12643 | 2019-04-07 | 2019-06-17 | 2019-07-30 | 2019-07-30 | COMP | 2020-07-10 | COMP | 2020-09-11 | COMP | 2020-09-21 | COMP | 2020-10-30 | COMP | Rule 16 | 50 | 31 | 240 | 45 | 7 | 30 | 398
15476 | 2019-04-07 | 2019-11-04 | 2019-12-23 | 2019-12-23 | COMP | 2020-02-03 | COMP | 2020-04-09 | COMP | 2020-04-13 | COMP | 2020-05-14 | COMP | Rule 16 | 148 | 33 | 28 | 48 | 3 | 24 | 279
16991 | 2019-04-07 | 2020-01-27 | 2020-04-01 | 2020-09-23 | COMP | 2021-03-16 | COMP | 2021-05-06 | COMP | 2021-07-19 | COMP | 2021-08-10 | COMP | Rule 16 | 202 | 47 | 118 | 38 | 51 | 17 | 591
11091 | 2019-04-08 | 2019-04-12 | 2019-05-11 | 2019-05-11 | COMP | 2019-05-23 | COMP | 2019-05-23 | COMP | 2019-05-16 | COMP | 2019-05-23 | COMP | Rule 16 | 5 | 21 | 9 | 1 | 0 | 1 | 34
11097 | 2019-04-08 | 2019-04-12 | 2019-11-08 | 2019-11-08 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-02-05 | COMP | 2020-05-01 | COMP | Rule 15/16 | 5 | 148 | 48 | 1 | 11 | 62 | 270
11138 | 2019-04-08 | 2019-04-15 | 2019-05-25 | 2019-05-25 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-01-09 | COMP | Rule 16 | 6 | 30 | 143 | 1 | 1 | 14 | 191
11192 | 2019-04-08 | 2019-04-17 | 2019-05-11 | 2019-05-11 | COMP | 2019-05-16 | COMP | 2019-05-29 | COMP | 2019-07-15 | COMP | 2019-07-17 | COMP | Rule 16 | 8 | 18 | 4 | 9 | 33 | 3 | 71
11340 | 2019-04-08 | 2019-04-23 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-22 | COMP | 2019-12-04 | COMP | 2020-05-13 | COMP | 2020-06-09 | COMP | Rule 16 | 12 | 57 | 7 | 94 | 112 | 19 | 296
11560 | 2019-04-08 | 2019-05-03 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-12-17 | COMP | 2020-01-12 | COMP | Rule 16 | 20 | 80 | 15 | 1 | 64 | 17 | 192
11567 | 2019-04-08 | 2019-05-02 | 2019-12-07 | 2019-12-07 | COMP | 2020-04-30 | COMP | 2021-02-12 | COMP | 2021-06-08 | COMP | 2021-08-18 | COMP | Rule 15/16 | 19 | 151 | 100 | 199 | 81 | 51 | 597
11578 | 2019-04-08 | 2019-05-04 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2022-03-08 | COMP | 2020-11-05 | COMP | Rule 15/16 | 20 | 99 | 27 | 1 | 591 |  | 402
11721 | 2019-04-08 | 2019-05-08 | 2019-09-27 | 2019-09-27 | COMP | 2021-04-07 | COMP | 2021-04-07 | COMP | 2021-12-10 | COMP | 2022-01-25 | COMP | Rule 16 | 23 | 100 | 383 | 1 | 172 | 32 | 706
11921 | 2019-04-08 | 2019-05-16 | 2019-10-03 | 2019-10-03 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2021-02-24 | COMP | 2021-03-19 | COMP | Rule 16 | 29 | 98 | 23 | 1 | 327 | 18 | 491
11962 | 2019-04-08 | 2019-05-20 | 2019-07-26 | 2019-07-26 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2019-12-09 | COMP | 2020-01-06 | COMP | Rule 16 | 31 | 48 | 44 | 1 | 50 | 19 | 188
12053 | 2019-04-08 | 2019-05-22 | 2019-08-24 | 2019-08-24 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-11-22 | COMP | 2019-12-27 | COMP | Rule 16 | 33 | 66 | 59 | 1 | 5 | 23 | 183
12090 | 2019-04-08 | 2019-05-23 | 2019-07-05 | 2019-07-08 | COMP | 2019-08-19 | COMP | 2019-09-26 | COMP |  |  | 2019-11-26 | COMP | Rule 16 | 34 | 30 | 31 | 28 |  |  | 163
12091 | 2019-04-08 | 2019-05-23 | 2019-07-05 | 2019-07-09 | COMP | 2019-08-20 | COMP | 2019-10-14 | COMP | 2019-10-11 | COMP | 2019-12-16 | COMP | Rule 16 | 34 | 30 | 31 | 39 | 0 | 43 | 175
12092 | 2019-04-08 | 2019-05-23 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP |  |  | 2019-09-27 | COMP | Rule 16 | 34 | 45 | 19 | 1 |  |  | 122
12093 | 2019-04-08 | 2019-05-23 | 2019-07-16 | 2019-07-16 | COMP | 2019-08-22 | COMP | 2019-10-11 | COMP |  |  | 2019-11-13 | COMP | Rule 16 | 34 | 37 | 28 | 36 |  |  | 154
12097 | 2019-04-08 | 2019-05-23 | 2019-07-17 | 2019-07-18 | COMP | 2019-08-29 | COMP | 2019-09-24 | COMP |  |  | 2019-10-04 | COMP | Rule 16 | 34 | 38 | 31 | 18 |  |  | 127
12251 | 2019-04-08 | 2019-05-29 | 2019-06-12 | 2019-06-12 | COMP | 2019-07-17 | COMP | 2019-07-18 | INPR | 2019-08-08 | COMP | 2019-09-24 | COMP | Rule 16 | 37 | 11 | 25 |  |  |  | 119
12360 | 2019-04-08 | 2019-06-03 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-13 | COMP | 2019-10-24 | COMP | 2021-02-27 | INPR | 2020-01-13 | COMP | Rule 16 | 40 | 41 | 11 | 52 |  |  | 193
12408 | 2019-04-08 | 2019-06-04 | 2019-07-09 | 2019-07-09 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-08-14 | COMP | Rule 16 | 41 | 25 | 24 | 1 | 1 | 4 | 91
12438 | 2019-04-08 | 2019-06-06 | 2019-11-22 | 2019-11-22 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-03-27 | COMP | 2020-05-01 | COMP | Rule 16 | 43 | 119 | 81 | 1 | 5 | 26 | 270
12509 | 2019-04-08 | 2019-06-10 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2020-08-05 | COMP | 2021-03-16 | COMP | Rule 16 | 45 | 69 | 8 | 1 | 218 | 152 | 488
12530 | 2019-04-08 | 2019-06-11 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-04-28 | COMP | 2020-06-01 | COMP | Rule 16 | 46 | 40 | 25 | 1 | 159 | 24 | 290
12533 | 2019-04-08 | 2019-06-12 | 2019-07-08 | 2019-07-08 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-12-12 | COMP | 2019-12-30 | COMP | Rule 16 | 47 | 18 | 85 | 1 | 26 | 12 | 184
12975 | 2019-04-08 | 2019-07-03 | 2019-11-17 | 2019-11-17 | COMP | 2020-02-12 | NOTN | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-03-24 | COMP | Other | 62 | 95 |  | 58 | 1 | 29 | 242
12995 | 2019-04-08 | 2019-07-03 | 2019-11-19 | 2019-11-19 | COMP | 2020-11-10 | COMP | 2020-11-16 | COMP | 2020-11-24 | COMP | 2020-12-18 | COMP | Rule 15/16 | 62 | 97 | 248 | 4 | 7 | 17 | 430
13126 | 2019-04-08 | 2019-07-11 | 2019-07-15 | 2019-07-15 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-09-16 | COMP | 2020-10-13 | COMP | Rule 16 | 67 | 3 | 154 | 1 | 145 | 20 | 385
13247 | 2019-04-08 | 2019-07-18 | 2019-08-21 | 2019-08-21 | COMP | 2019-08-28 | COMP | 2020-06-26 | NOTN | 2020-11-12 | COMP | 2022-02-02 | COMP | Rule 16 | 72 | 25 | 6 |  |  |  | 712
13503 | 2019-04-08 | 2019-07-29 | 2019-12-13 | 2019-12-13 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-05-19 | COMP | 2020-06-17 | COMP | Rule 16 | 79 | 96 | 35 | 1 | 75 | 21 | 302
13543 | 2019-04-08 | 2019-07-30 | 2019-09-09 | 2019-09-09 | COMP | 2019-11-26 | COMP | 2020-02-04 | COMP | 2021-10-04 | COMP | 2021-10-21 | COMP | Rule 15/16 | 80 | 29 | 56 | 46 | 422 | 14 | 642
13875 | 2019-04-08 | 2019-08-14 | 2019-10-23 | 2020-03-27 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2021-02-09 | COMP | 2021-03-03 | COMP | Rule 16 | 91 | 50 | 82 | 1 | 139 | 16 | 479
13920 | 2019-04-08 | 2019-08-16 | 2020-06-24 | 2020-06-24 | COMP | 2020-07-03 | COMP | 2020-07-09 | COMP | 2020-07-10 | COMP | 2020-07-22 | COMP | Rule 16 | 93 | 215 | 8 | 5 | 2 | 9 | 327
14024 | 2019-04-08 | 2019-08-21 | 2019-10-15 | 2019-10-15 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-12-16 | COMP | 2020-01-02 | COMP | Rule 16 | 96 | 39 | 8 | 1 | 35 | 12 | 186
14577 | 2019-04-08 | 2019-09-17 | 2020-03-06 | 2020-03-06 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2023-04-18 | COMP | 2023-05-17 | COMP | Rule 16 | 114 | 117 | 18 | 1 | 768 | 22 | 1035
15507 | 2019-04-08 | 2019-11-05 | 2019-12-05 | 2019-12-05 | COMP | 2021-03-23 | COMP | 2021-06-07 | COMP | 2021-07-13 | COMP | 2021-08-25 | COMP | Rule 16 | 149 | 20 | 326 | 54 | 26 | 32 | 602
15716 | 2019-04-08 | 2019-11-18 | 2019-12-28 | 2019-12-28 | COMP | 2020-02-18 | COMP | 2020-04-01 | COMP | 2022-01-30 | INPR | 2020-06-02 | COMP | Rule 16 | 157 | 27 | 34 | 32 |  |  | 291
15937 | 2019-04-08 | 2019-12-02 | 2020-02-25 | 2020-02-25 | COMP | 2020-03-10 | COMP | 2020-04-06 | COMP | 2020-05-26 | COMP | 2020-11-30 | COMP | Rule 16 | 165 | 58 | 11 | 20 | 36 | 131 | 416
15959 | 2019-04-08 | 2019-12-03 | 2020-01-24 | 2020-03-30 | COMP | 2020-04-10 | COMP | 2020-02-12 | COMP | 2020-05-06 | COMP | 2020-06-29 | COMP | Rule 16 | 166 | 36 | 10 |  | 60 | 38 | 310
16977 | 2019-04-08 | 2020-01-27 | 2020-04-10 | 2020-06-03 | COMP | 2020-06-08 | COMP | 2020-09-25 | COMP | 2020-11-17 | COMP | 2020-12-19 | COMP | Rule 15/16 | 202 | 54 | 4 | 79 | 37 | 22 | 430
17410 | 2019-04-08 | 2020-02-12 | 2020-04-17 | 2020-06-23 | COMP | 2021-06-02 | COMP | 2021-06-03 | COMP | 2021-08-02 | COMP | 2021-09-14 | COMP | Rule 16 | 214 | 47 | 238 | 2 | 42 | 31 | 615
18338 | 2019-04-08 | 2020-03-19 | 2020-05-03 | 2020-05-03 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-05-26 | COMP | 2020-06-01 | COMP | Rule 16 | 239 | 32 | 12 | 1 | 5 | 5 | 290
19275 | 2019-04-08 | 2020-04-28 | 2020-11-24 | 2021-02-25 | COMP | 2021-05-19 | COMP | 2021-11-29 | COMP | 2021-09-21 | COMP | 2023-04-29 | COMP | Rule 15/16 | 267 | 148 | 60 | 133 | 0 | 357 | 1022
4167 | 2019-04-09 | 2019-05-10 | 2019-08-22 | 2020-05-18 | COMP | 2020-07-02 | COMP | 2021-07-14 | COMP | 2021-07-15 | COMP | 2021-08-07 | COMP | Rule 15/16 | 24 | 73 | 33 | 260 | 2 | 17 | 588
11080 | 2019-04-09 | 2019-04-11 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-09 | COMP | 2020-01-23 | COMP |  | INPR | 2020-03-18 | COMP | Rule 15/16 | 3 | 172 | 17 | 10 |  |  | 237
11357 | 2019-04-09 | 2019-04-24 | 2019-06-08 | 2019-07-02 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-07-01 | COMP | 2019-08-20 | COMP | Rule 16 | 12 | 32 | 14 | 1 | 0 | 22 | 94
11580 | 2019-04-09 | 2019-05-04 | 2019-09-03 | 2019-09-03 | COMP | 2019-10-08 | COMP | 2019-10-21 | COMP | 2020-01-15 | COMP | 2020-03-12 | COMP | Rule 16 | 19 | 84 | 26 | 10 | 58 | 40 | 233
11788 | 2019-04-09 | 2019-05-11 | 2019-08-31 | 2020-02-29 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-04-16 | COMP | 2020-06-03 | COMP | Rule 15/16 | 24 | 78 | 33 | 1 | 2 | 34 | 291
11869 | 2019-04-09 | 2019-05-15 | 2019-10-02 | 2019-10-02 | COMP | 2019-11-04 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-12-15 | COMP | Rule 16 | 27 | 98 | 24 | 2 | 1 | 26 | 173
11900 | 2019-04-09 | 2019-05-15 | 2019-06-08 | 2019-06-08 | COMP | 2019-06-10 | COMP | 2019-06-10 | COMP | 2019-07-01 | COMP | 2019-07-30 | COMP | Rule 16 | 27 | 17 | 1 | 1 | 16 | 21 | 79
11913 | 2019-04-09 | 2019-05-16 | 2019-06-28 | 2019-07-08 | COMP | 2019-07-29 | COMP | 2019-10-17 | COMP | 2019-08-14 | COMP | 2019-11-12 | COMP | Rule 16 | 28 | 31 | 16 | 58 | 0 | 18 | 152
12074 | 2019-04-09 | 2019-05-22 | 2019-07-11 | 2019-07-30 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-07-22 | COMP | 2019-09-05 | COMP | Rule 16 | 32 | 35 | 12 | 1 | 0 | 16 | 105
12077 | 2019-04-09 | 2019-05-22 | 2019-09-11 | 2019-09-11 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-20 | COMP | 2019-12-09 | COMP | Rule 16 | 32 | 78 | 44 | 1 | 7 | 12 | 169
12111 | 2019-04-09 | 2019-05-23 | 2019-09-20 | 2019-10-23 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-19 | COMP | 2020-01-15 | COMP | Rule 15/16 | 33 | 84 | 10 | 1 | 10 | 38 | 194
12168 | 2019-04-09 | 2019-05-24 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-17 | COMP | 2019-08-16 | COMP | 2019-08-15 | COMP | 2020-03-26 | COMP | Rule 16 | 34 | 26 | 12 | 23 | 0 | 152 | 243
12264 | 2019-04-09 | 2019-05-29 | 2019-09-23 | 2019-09-23 | COMP | 2019-11-15 | COMP | 2019-11-15 | COMP | 2020-02-07 | COMP | 2020-03-30 | COMP | Rule 16 | 36 | 82 | 39 | 1 | 56 | 36 | 245
12395 | 2019-04-09 | 2019-06-05 | 2019-09-18 | 2019-09-26 | COMP | 2019-10-02 | COMP | 2019-10-03 | COMP | 2019-11-04 | COMP | 2019-11-15 | COMP | Rule 16 | 41 | 74 | 5 | 2 | 23 | 9 | 155
12558 | 2019-04-09 | 2019-06-13 | 2019-08-03 | 2019-08-03 | COMP | 2020-09-01 | COMP | 2020-09-02 | COMP | 2020-10-01 | COMP | 2020-10-29 | COMP | Rule 16 | 47 | 36 | 273 | 2 | 21 | 21 | 396
12739 | 2019-04-09 | 2019-06-20 | 2019-06-27 | 2019-06-27 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2022-06-18 | INPR | 2020-02-22 | COMP | Rule 16 | 52 | 6 | 72 | 1 |  |  | 219
12750 | 2019-04-09 | 2019-06-20 | 2019-07-18 | 2019-07-18 | COMP | 2019-08-30 | COMP | 2019-08-30 | INPR | 2019-12-11 | COMP | 2021-08-17 | COMP | Rule 16 | 52 | 20 | 32 |  |  |  | 595
12804 | 2019-04-09 | 2019-06-24 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2019-12-16 | COMP | 2020-04-07 | COMP | Rule 16 | 54 | 99 | 24 | 1 | 0 | 77 | 251
12834 | 2019-04-09 | 2019-06-24 | 2020-01-17 | 2020-01-17 | COMP | 2021-08-13 | COMP | 2021-09-21 | COMP | 2021-08-24 | COMP | 2021-11-09 | COMP | Rule 16 | 54 | 143 | 398 | 27 | 0 | 36 | 654
13031 | 2019-04-09 | 2019-07-08 | 2019-09-13 | 2019-09-13 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-10-09 | COMP | 2019-12-21 | COMP | Rule 16 | 63 | 49 | 14 | 1 | 6 | 50 | 178
13102 | 2019-04-09 | 2019-07-11 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-16 | COMP | 2019-09-19 | COMP | 2020-04-22 | COMP | 2020-08-27 | COMP | Rule 16 | 66 | 39 | 9 | 4 | 148 | 91 | 352
13201 | 2019-04-09 | 2019-07-16 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-16 | COMP | 2020-05-08 | COMP | 2021-08-06 | COMP | 2021-09-20 | COMP | Rule 16 | 69 | 116 | 12 | 80 | 315 | 31 | 618
13202 | 2019-04-09 | 2019-07-16 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-18 | COMP | 2020-09-11 | COMP | 2022-03-21 | COMP | 2022-04-11 | COMP | Rule 15/16 | 69 | 267 | 11 | 18 | 382 | 16 | 758
13309 | 2019-04-09 | 2019-07-20 | 2019-08-31 | 2019-08-31 | COMP | 2019-10-29 | COMP | 2020-06-26 | COMP | 2021-05-16 | COMP | 2021-05-29 | COMP | Rule 15/16 | 72 | 30 | 41 | 166 | 223 | 10 | 540
13535 | 2019-04-09 | 2019-07-31 | 2020-03-21 | 2020-03-21 | COMP | 2020-04-06 | COMP | 2021-02-11 | COMP | 2021-08-11 | COMP | 2021-09-02 | COMP | Rule 16 | 80 | 160 | 11 | 216 | 127 | 17 | 607
13574 | 2019-04-09 | 2019-08-01 | 2019-12-23 | 2020-01-15 | COMP | 2020-10-01 | COMP | 2020-10-22 | COMP | 2020-10-20 | COMP | 2020-12-04 | COMP | Rule 15/16 | 81 | 99 | 183 | 16 | 0 | 29 | 419
13676 | 2019-04-09 | 2019-08-05 | 2019-10-15 | 2019-10-15 | COMP | 2020-01-09 | COMP | 2020-01-29 | COMP | 2021-02-27 | INPR | 2020-02-21 | COMP | Rule 16 | 83 | 51 | 58 | 14 |  |  | 219
14071 | 2019-04-09 | 2019-08-23 | 2020-05-20 | 2020-05-20 | COMP | 2020-07-15 | COMP | 2020-09-01 | COMP | 2022-07-16 | INPR | 2020-11-06 | COMP | Rule 15/16 | 97 | 186 | 40 | 35 |  |  | 402
14244 | 2019-04-09 | 2019-08-30 | 2019-11-25 | 2019-11-25 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2021-02-16 | COMP | 2021-04-01 | COMP | Rule 16 | 102 | 60 | 126 | 1 | 182 | 33 | 499
14581 | 2019-04-09 | 2019-09-17 | 2020-05-26 | 2021-03-05 | COMP | 2021-03-23 | COMP | 2021-03-23 | COMP | 2021-04-05 | COMP | 2021-05-06 | COMP | Rule 15/16 | 113 | 173 | 13 | 1 | 10 | 24 | 524
15082 | 2019-04-09 | 2019-10-11 | 2020-02-28 | 2020-12-17 | COMP | 2021-03-24 | COMP | 2021-04-23 | COMP | 2021-04-06 | COMP | 2021-05-05 | COMP | Rule 16 | 131 | 94 | 66 | 23 | 0 | 9 | 523
16887 | 2019-04-09 | 2020-01-22 | 2020-02-26 | 2020-02-29 | COMP | 2020-02-29 | NOTN | 2020-03-03 | COMP | 2020-04-16 | NOTN | 2020-05-20 | COMP | Other | 198 | 25 |  | 2 |  |  | 282
18449 | 2019-04-09 | 2020-03-24 | 2020-03-25 | 2020-03-25 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2020-07-03 | COMP | 2020-10-22 | COMP | Other | 241 | 2 | 70 | 1 | 3 | 79 | 391
11348 | 2019-04-10 | 2019-04-26 | 2019-07-22 | 2019-07-22 | COMP | 2019-07-22 | NOTN | 2019-07-22 | COMP | 2019-11-25 | COMP | 2020-01-09 | COMP | Other | 13 | 60 |  | 1 | 89 | 30 | 189
11430 | 2019-04-10 | 2019-04-27 | 2019-11-12 | 2019-11-12 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-20 | COMP | 2020-07-21 | COMP | Rule 16 | 13 | 138 | 95 | 1 | 15 | 66 | 324
11499 | 2019-04-10 | 2019-04-30 | 2019-08-20 | 2019-08-20 | COMP | 2019-08-20 | NOTN | 2020-01-03 | COMP | 2019-12-16 | COMP | 2020-03-11 | COMP | Other | 15 | 79 |  | 93 | 0 | 47 | 231
11517 | 2019-04-10 | 2019-04-30 | 2019-08-01 | 2019-09-10 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2023-07-25 | COMP | 2023-08-14 | COMP | Rule 15/16 | 15 | 66 | 239 | 1 | 735 | 15 | 1093
11539 | 2019-04-10 | 2019-05-01 | 2019-07-03 | 2019-07-03 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-07-31 | COMP | 2019-08-29 | COMP | Rule 16 | 16 | 45 | 16 | 1 | 5 | 22 | 100
11588 | 2019-04-10 | 2019-05-03 | 2019-07-27 | 2019-07-27 | COMP | 2019-09-24 | COMP | 2020-04-23 | COMP | 2020-05-15 | COMP | 2020-06-24 | COMP | Rule 16 | 18 | 59 | 41 | 146 | 17 | 28 | 305
11774 | 2019-04-10 | 2019-05-10 | 2019-06-22 | 2019-06-22 | COMP | 2019-07-09 | COMP | 2019-08-22 | COMP | 2019-07-22 | COMP | 2019-09-24 | COMP | Rule 16 | 23 | 30 | 11 | 33 | 0 | 23 | 117
11813 | 2019-04-10 | 2019-05-13 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-06-04 | COMP | 2020-08-07 | COMP | Rule 16 | 24 | 90 | 22 | 1 | 158 | 47 | 337
11825 | 2019-04-10 | 2019-05-13 | 2019-09-04 | 2019-09-04 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-02-26 | COMP | 2020-07-01 | COMP | Rule 16 | 24 | 80 | 32 | 1 | 88 | 90 | 310
12004 | 2019-04-10 | 2019-05-20 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2019-10-14 | COMP | 2019-11-22 | COMP | Rule 16 | 29 | 98 | 8 | 1 | 0 | 27 | 159
12071 | 2019-04-10 | 2019-05-22 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-14 | COMP | 2020-04-20 | COMP | 2020-02-25 | COMP | 2020-06-01 | COMP | Rule 16 | 31 | 115 | 9 | 107 | 0 | 30 | 288
12184 | 2019-04-10 | 2019-05-28 | 2019-08-14 | 2019-10-24 | COMP | 2020-02-25 | COMP | 2020-12-03 | COMP | 2020-10-29 | COMP | 2021-02-09 | COMP | Rule 15/16 | 34 | 56 | 82 | 198 | 0 | 46 | 462
12211 | 2019-04-10 | 2019-05-28 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-09-18 | COMP | 2019-11-07 | COMP | Rule 16 | 34 | 52 | 14 | 1 | 16 | 37 | 149
12469 | 2019-04-10 | 2019-06-10 | 2019-07-15 | 2019-11-12 | COMP | 2019-11-27 | COMP | 2019-09-09 | COMP | 2019-12-04 | COMP | 2019-12-16 | COMP | Rule 16 | 43 | 25 | 12 |  | 60 | 9 | 173
12664 | 2019-04-10 | 2019-06-18 | 2019-12-23 | 2019-12-23 | COMP | 2020-03-20 | COMP | 2020-04-29 | COMP | 2020-08-04 | COMP | 2020-08-07 | COMP | Rule 15/16 | 49 | 130 | 61 | 29 | 69 | 4 | 337
12824 | 2019-04-10 | 2019-06-24 | 2019-08-29 | 2019-08-29 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-05-22 | COMP | 2020-06-24 | COMP | Rule 16 | 53 | 48 | 90 | 1 | 95 | 23 | 305
13220 | 2019-04-10 | 2019-07-16 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-16 | COMP | 2021-01-20 | COMP | 2022-07-13 | COMP | 2022-08-15 | COMP | Rule 15/16 | 68 | 96 | 11 | 276 | 374 | 24 | 844
13221 | 2019-04-10 | 2019-07-16 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2022-01-19 | COMP | 2022-02-17 | COMP | Rule 15/16 | 68 | 132 | 13 | 1 | 490 | 22 | 721
13222 | 2019-04-10 | 2019-07-16 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-16 | COMP | 2020-11-09 | COMP | 2021-05-04 | COMP | 2021-05-06 | COMP | Rule 16 | 68 | 106 | 22 | 209 | 120 | 3 | 523
13223 | 2019-04-10 | 2019-07-16 | 2019-12-08 | 2019-12-08 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2022-01-06 | COMP | 2022-02-15 | COMP | Rule 15/16 | 68 | 100 | 14 | 1 | 512 | 28 | 719
13224 | 2019-04-10 | 2019-07-16 | 2020-04-12 | 2020-04-12 | COMP | 2020-04-29 | COMP | 2020-07-27 | COMP | 2022-04-01 | COMP | 2022-05-12 | COMP | Rule 15/16 | 68 | 186 | 13 | 63 | 424 | 30 | 780
13225 | 2019-04-10 | 2019-07-16 | 2020-09-02 | 2020-11-24 | COMP | 2020-12-16 | COMP | 2021-03-23 | COMP | 2022-04-15 | COMP | 2022-05-23 | COMP | Rule 16 | 68 | 288 | 15 | 66 | 271 | 27 | 787
13226 | 2019-04-10 | 2019-07-16 | 2019-10-28 | 2019-11-21 | COMP | 2019-11-12 | COMP | 2022-05-18 | COMP | 2022-04-15 | COMP | 2022-06-10 | COMP | Rule 15/16 | 68 | 74 |  | 634 | 0 | 17 | 800
13227 | 2019-04-10 | 2019-07-16 | 2019-10-20 | 2020-02-21 | COMP | 2020-03-11 | COMP | 2022-04-28 | COMP | 2022-04-11 | COMP | 2022-05-13 | COMP | Rule 16 | 68 | 68 | 14 | 540 | 0 | 12 | 781
13242 | 2019-04-10 | 2019-07-17 | 2019-10-20 | 2020-07-15 | COMP | 2020-11-12 | COMP | 2021-08-10 | COMP | 2022-01-05 | COMP | 2022-02-01 | COMP | Rule 16 | 69 | 67 | 85 | 186 | 103 | 19 | 709
13252 | 2019-04-10 | 2019-07-17 | 2019-09-30 | 2019-09-30 | COMP | 2020-03-18 | COMP | 2022-02-02 | COMP | 2022-02-01 | COMP | 2022-02-24 | COMP | Other | 69 | 53 | 116 | 475 | 0 | 16 | 725
13253 | 2019-04-10 | 2019-07-17 | 2019-10-20 | 2020-11-12 | COMP | 2020-12-01 | COMP | 2022-03-14 | COMP |  | INPR | 2022-03-30 | COMP | Rule 16 | 69 | 67 | 12 | 323 |  |  | 749
13254 | 2019-04-10 | 2019-07-17 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-09 | COMP | 2020-11-09 | COMP | 2022-02-01 | COMP | 2022-02-22 | COMP | Rule 15/16 | 69 | 86 | 14 | 235 | 308 | 15 | 723
13256 | 2019-04-10 | 2019-07-17 | 2019-10-20 | 2019-10-20 | COMP | 2019-12-27 | COMP | 2022-02-07 | COMP | 2022-01-19 | COMP | 2022-02-16 | COMP | Rule 16 | 69 | 67 | 46 | 533 | 0 | 8 | 720
13305 | 2019-04-10 | 2019-07-20 | 2019-09-17 | 2019-09-17 | COMP | 2019-10-14 | NOTN | 2019-12-11 | COMP | 2019-11-27 | COMP | 2020-03-04 | COMP | Other | 71 | 41 |  | 59 | 0 | 57 | 226
13513 | 2019-04-10 | 2019-07-29 | 2019-11-21 | 2019-11-21 | COMP | 2019-12-09 | COMP | 2020-02-10 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | Rule 16 | 77 | 82 | 11 | 43 | 16 | 1 | 225
13536 | 2019-04-10 | 2019-07-31 | 2020-09-09 | 2020-09-09 | COMP | 2020-09-28 | COMP | 2022-04-21 | COMP | 2022-04-01 | COMP | 2022-05-09 | COMP | Rule 16 | 79 | 281 | 14 | 394 | 0 | 13 | 777
13537 | 2019-04-10 | 2019-07-31 | 2020-08-15 | 2020-08-15 | COMP | 2020-09-01 | COMP | 2021-06-10 | COMP | 2021-10-13 | COMP | 2021-11-01 | COMP | Rule 15/16 | 79 | 264 | 12 | 194 | 88 | 14 | 647
13538 | 2019-04-10 | 2019-07-31 | 2020-04-04 | 2020-04-04 | COMP | 2020-04-20 | COMP | 2020-12-29 | COMP | 2021-12-09 | COMP | 2022-01-18 | COMP | Rule 16 | 79 | 170 | 11 | 176 | 239 | 28 | 699
13567 | 2019-04-10 | 2019-07-31 | 2020-01-14 | 2020-06-18 | COMP | 2020-07-17 | COMP | 2020-04-23 | COMP | 2019-07-31 | COMP | 2020-10-30 | COMP | Rule 16 | 79 | 114 | 22 |  | 0 | 135 | 396
14173 | 2019-04-10 | 2019-08-28 | 2019-12-19 | 2020-02-24 | COMP | 2020-03-02 | COMP | 2020-03-03 | COMP | 2020-03-10 | COMP | 2020-04-01 | COMP | Rule 16 | 99 | 78 | 6 | 2 | 6 | 17 | 246
14271 | 2019-04-10 | 2019-09-03 | 2019-12-27 | 2019-12-27 | COMP | 2020-02-19 | COMP | 2020-03-09 | COMP | 2020-03-17 | COMP | 2020-06-15 | COMP | Rule 15/16 | 102 | 80 | 36 | 14 | 7 | 64 | 298
14363 | 2019-04-10 | 2019-09-06 | 2019-11-10 | 2019-11-10 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2022-01-19 | COMP | 2022-02-15 | COMP | Rule 16 | 105 | 46 | 87 | 1 | 464 | 20 | 719
14623 | 2019-04-10 | 2019-09-19 | 2020-04-22 | 2021-03-17 | COMP | 2023-03-23 | COMP | 2023-08-24 | COMP | 2023-08-02 | COMP | 2023-10-27 | COMP | Rule 15/16 | 114 | 148 | 508 | 108 | 0 | 46 | 1146
15003 | 2019-04-10 | 2019-10-08 | 2019-11-19 | 2019-11-19 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-01-16 | COMP | 2020-01-22 | COMP | Rule 16 | 127 | 30 | 3 | 1 | 37 | 4 | 197
15121 | 2019-04-10 | 2019-10-15 | 2020-06-28 | 2020-06-28 | COMP | 2020-08-03 | COMP | 2020-08-14 | COMP | 2020-11-03 | COMP | 2020-11-20 | COMP | Rule 16 | 132 | 176 | 26 | 10 | 57 | 13 | 410
15888 | 2019-04-10 | 2019-11-25 | 2020-02-14 | 2020-02-14 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-04-15 | COMP | 2020-06-04 | COMP | Rule 16 | 160 | 55 | 41 | 1 | 3 | 36 | 291
16121 | 2019-04-10 | 2019-12-10 | 2020-04-29 | 2020-04-29 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-08-06 | COMP | 2020-09-25 | COMP | Rule 16 | 169 | 98 | 31 | 1 | 41 | 36 | 371
16828 | 2019-04-10 | 2020-01-17 | 2020-07-07 | 2021-08-20 | COMP | 2023-04-28 | COMP | 2023-04-28 | COMP | 2023-04-28 | COMP | 2023-06-01 | COMP | Rule 15/16 | 195 | 120 | 424 | 1 | 1 | 24 | 1043
19781 | 2019-04-10 | 2020-05-22 | 2020-07-30 | 2020-07-30 | COMP | 2021-04-14 | COMP | 2021-04-14 | COMP | 2021-06-25 | COMP | 2021-11-09 | COMP | Rule 16 | 283 | 49 | 177 | 1 | 52 | 96 | 653
21355 | 2019-04-10 | 2020-08-04 | 2020-09-03 | 2020-09-03 | COMP | 2020-09-23 | COMP | 2021-02-17 | COMP | 2021-12-21 | COMP | 2022-01-31 | COMP | Rule 16 | 334 | 23 | 14 | 99 | 214 | 29 | 708
11160 | 2019-04-11 | 2019-04-16 | 2019-11-18 | 2020-06-24 | COMP | 2020-07-02 | COMP | 2020-08-24 | COMP | 2020-11-01 | COMP | 2020-11-01 | COMP | Rule 15/16 | 4 | 151 | 7 | 38 | 49 | 0 | 395
11190 | 2019-04-11 | 2019-04-16 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-07 | COMP | 2021-03-10 | COMP | 2021-03-29 | COMP | 2021-04-02 | COMP | Rule 15/16 | 4 | 233 | 14 | 233 | 14 | 5 | 498
11196 | 2019-04-11 | 2019-04-17 | 2019-09-09 | 2019-09-09 | COMP | 2019-04-17 | NOTN | 2019-12-11 | COMP | 2019-11-27 | COMP | 2020-06-17 | COMP | Other | 5 | 101 |  | 65 | 0 | 131 | 299
11223 | 2019-04-11 | 2019-04-19 | 2019-12-07 | 2020-01-16 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-02-04 | COMP | 2020-03-04 | COMP | Rule 15/16 | 7 | 160 | 15 | 1 | 0 | 19 | 225
11353 | 2019-04-11 | 2019-04-25 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-18 | COMP | 2019-10-22 | COMP | 2019-12-19 | COMP | 2020-01-21 | COMP | Rule 15/16 | 11 | 108 | 17 | 3 | 40 | 21 | 195
11405 | 2019-04-11 | 2019-04-25 | 2019-08-13 | 2019-08-13 | COMP | 2019-09-20 | COMP | 2019-10-30 | COMP | 2020-02-04 | COMP | 2020-02-05 | COMP | Rule 15/16 | 11 | 77 | 28 | 29 | 64 | 2 | 206
11472 | 2019-04-11 | 2019-04-29 | 2019-07-02 | 2019-07-02 | COMP | 2019-08-13 | COMP | 2019-10-04 | COMP | 2019-10-02 | COMP | 2019-11-06 | COMP | Rule 16 | 13 | 46 | 30 | 38 | 0 | 24 | 147
11602 | 2019-04-11 | 2019-05-03 | 2019-07-18 | 2019-07-18 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-08-20 | COMP | 2019-09-12 | COMP | Rule 16 | 17 | 53 | 25 | 1 | 0 | 16 | 108
11618 | 2019-04-11 | 2019-05-06 | 2019-06-19 | 2019-06-19 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-07-01 | COMP | 2019-09-01 | COMP | Rule 16 | 18 | 32 | 45 | 1 | 0 | 8 | 100
11669 | 2019-04-11 | 2019-05-07 | 2019-08-05 | 2019-08-05 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-02-29 | INPR | 2019-10-18 | COMP | Rule 16 | 19 | 63 | 53 | 1 |  |  | 134
11851 | 2019-04-11 | 2019-05-14 | 2019-07-05 | 2019-07-05 | COMP | 2019-07-10 | COMP | 2019-08-09 | COMP | 2021-02-27 | INPR | 2019-08-23 | COMP | Rule 16 | 24 | 37 | 4 | 23 |  |  | 95
11856 | 2019-04-11 | 2019-05-14 | 2019-06-01 | 2019-06-01 | COMP | 2019-07-09 | COMP | 2019-07-26 | COMP | 2020-07-05 | COMP | 2020-09-02 | COMP | Rule 16 | 24 | 13 | 26 | 14 | 237 | 43 | 354
11991 | 2019-04-11 | 2019-05-20 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2020-03-29 | INPR | 2019-12-17 | COMP | Rule 16 | 28 | 52 | 12 | 1 |  |  | 173
12098 | 2019-04-11 | 2019-05-23 | 2019-08-15 | 2019-08-15 | COMP | 2019-08-28 | COMP | 2020-12-11 | COMP | 2021-03-24 | COMP | 2021-04-09 | COMP | Rule 16 | 31 | 59 | 10 | 325 | 70 | 13 | 503
12104 | 2019-04-11 | 2019-05-23 | 2019-10-23 | 2019-10-23 | COMP | 2020-06-08 | COMP | 2020-07-01 | COMP | 2020-07-07 | COMP | 2020-07-21 | COMP | Rule 16 | 31 | 107 | 156 | 18 | 5 | 11 | 323
12180 | 2019-04-11 | 2019-05-28 | 2020-05-08 | 2020-05-08 | COMP | 2021-06-09 | COMP | 2021-06-30 | COMP | 2021-09-30 | COMP | 2021-11-23 | COMP | Rule 16 | 33 | 240 | 274 | 16 | 65 | 38 | 661
12355 | 2019-04-11 | 2019-06-03 | 2019-08-12 | 2019-08-12 | COMP | 2019-10-22 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2021-01-15 | COMP | Rule 15/16 | 37 | 50 | 51 | 271 | 1 | 40 | 445
12459 | 2019-04-11 | 2019-06-07 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-11-07 | COMP | 2019-11-19 | COMP | Rule 16 | 41 | 49 | 14 | 1 | 47 | 8 | 155
12460 | 2019-04-11 | 2019-06-07 | 2019-08-26 | 2019-08-26 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-12-24 | COMP | 2020-01-02 | COMP | Rule 16 | 41 | 56 | 51 | 1 | 33 | 6 | 183
12749 | 2019-04-11 | 2019-06-20 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-30 | COMP | 2019-10-16 | COMP | 2019-11-12 | COMP | 2019-11-20 | COMP | Rule 15/16 | 50 | 56 | 16 | 13 | 19 | 7 | 156
12887 | 2019-04-11 | 2019-06-27 | 2019-08-13 | 2019-08-13 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-09-12 | COMP | 2019-10-07 | COMP | Rule 16 | 55 | 33 | 15 | 1 | 8 | 18 | 125
12948 | 2019-04-11 | 2019-07-03 | 2019-10-01 | 2019-10-01 | COMP | 2019-11-05 | COMP | 2019-12-10 | COMP | 2022-07-16 | INPR | 2020-06-29 | COMP | Rule 16 | 59 | 63 | 26 | 23 |  |  | 307
13129 | 2019-04-11 | 2019-07-11 | 2019-09-28 | 2019-09-28 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2019-12-30 | COMP | 2020-03-02 | COMP | Rule 16 | 64 | 56 | 53 | 1 | 10 | 43 | 223
13924 | 2019-04-11 | 2019-08-16 | 2019-12-06 | 2019-12-06 | COMP | 2020-02-10 | NOTN | 2020-02-10 | COMP | 2020-03-17 | COMP | 2020-06-04 | COMP | Other | 90 | 77 |  | 44 | 26 | 57 | 290
13981 | 2019-04-11 | 2019-08-19 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-11-12 | COMP | 2019-12-30 | COMP | Rule 16 | 91 | 19 | 19 | 1 | 23 | 32 | 181
13999 | 2019-04-11 | 2019-08-20 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2020-01-10 | COMP | 2019-12-14 | COMP | Rule 16 | 92 | 46 | 23 | 1 | 31 |  | 171
14087 | 2019-04-11 | 2019-08-23 | 2019-12-06 | 2019-12-06 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-01-30 | COMP | 2020-02-04 | COMP | Rule 16 | 95 | 72 | 8 | 1 | 30 | 4 | 205
14755 | 2019-04-11 | 2019-09-26 | 2019-10-11 | 2019-11-15 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-02-20 | COMP | 2020-02-24 | COMP | Rule 16 | 118 | 12 | 9 | 1 | 56 | 3 | 218
15065 | 2019-04-11 | 2019-10-10 | 2019-11-04 | 2019-11-04 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-02-26 | COMP | 2020-04-15 | COMP | Rule 16 | 128 | 18 | 18 | 1 | 59 | 36 | 255
15517 | 2019-04-11 | 2019-11-05 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-24 | COMP | 2021-01-21 | COMP | 2023-05-27 | INPR | 2021-01-26 | COMP | Rule 15/16 | 146 | 124 | 36 | 145 |  |  | 451
16038 | 2019-04-11 | 2019-12-06 | 2020-06-18 | 2020-09-14 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2020-09-28 | COMP | 2020-10-13 | COMP | Rule 16 | 166 | 135 | 6 | 1 | 6 | 12 | 382
16090 | 2019-04-11 | 2019-12-09 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-26 | COMP | 2020-09-02 | COMP | 2020-08-17 | COMP | 2020-09-03 | COMP | Rule 16 | 167 | 109 | 9 | 72 | 0 | 2 | 355
16721 | 2019-04-11 | 2020-01-13 | 2020-09-11 | 2020-09-11 | COMP | 2020-12-21 | COMP | 2021-03-02 | COMP | 2021-02-02 | COMP | 2021-03-11 | COMP | Rule 16 | 190 | 171 | 69 | 48 | 0 | 8 | 482
16926 | 2019-04-11 | 2020-01-23 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-07-08 | COMP | 2020-03-25 | COMP | Rule 15/16 | 197 | 44 | 24 | 1 | 52 |  | 240
18823 | 2019-04-11 | 2020-04-08 | 2021-10-12 | 2021-10-12 | COMP | 2022-05-11 | COMP | 2022-05-12 | INPR | 2024-03-18 | CANC | 2022-02-02 | COMP | Rule 15/16 | 250 | 383 | 147 |  |  |  | 709
4292 | 2019-04-12 | 2020-04-16 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | NOTN | 2020-07-02 | COMP | 2022-07-16 | INPR | 2020-08-29 | COMP | Other | 255 | 18 |  | 38 |  |  | 350
11253 | 2019-04-12 | 2019-04-20 | 2019-05-08 | 2019-05-08 | COMP | 2019-06-06 | COMP | 2019-06-06 | NOTN | 2019-10-10 | COMP | 2019-10-17 | COMP | Rule 16 | 6 | 13 | 21 |  |  |  | 132
11744 | 2019-04-12 | 2019-05-09 | 2019-07-15 | 2019-07-15 | COMP | 2019-07-25 | COMP | 2019-08-30 | COMP | 2019-09-10 | COMP | 2019-09-27 | COMP | Rule 16 | 20 | 46 | 9 | 27 | 7 | 14 | 118
11799 | 2019-04-12 | 2019-05-13 | 2020-01-15 | 2020-01-15 | COMP | 2020-05-11 | COMP | 2020-08-13 | COMP | 2022-01-30 | INPR | 2020-11-10 | COMP | Rule 15/16 | 22 | 170 | 82 | 68 |  |  | 401
11801 | 2019-04-12 | 2019-05-13 | 2020-01-21 | 2020-01-21 | COMP | 2020-05-11 | COMP | 2020-07-13 | COMP |  | INPR | 2020-11-10 | COMP | Rule 15/16 | 22 | 173 | 79 | 45 |  |  | 401
11802 | 2019-04-12 | 2019-05-13 | 2020-01-31 | 2020-01-31 | COMP | 2020-11-18 | COMP | 2021-02-02 | COMP | 2021-03-02 | COMP | 2021-04-20 | COMP | Rule 15/16 | 22 | 181 | 205 | 50 | 20 | 36 | 509
11929 | 2019-04-12 | 2019-05-17 | 2019-07-23 | 2019-07-23 | COMP | 2019-07-29 | COMP | 2019-08-08 | COMP | 2019-09-20 | COMP | 2019-10-13 | COMP | Rule 16 | 26 | 46 | 5 | 9 | 31 | 16 | 128
12099 | 2019-04-12 | 2019-05-23 | 2019-09-05 | 2019-09-05 | COMP | 2020-01-31 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-05-21 | COMP | Rule 15/16 | 30 | 73 | 101 | 21 | 1 | 59 | 280
12242 | 2019-04-12 | 2019-05-29 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-15 | COMP | 2019-08-15 | COMP | 2020-03-24 | COMP | 2020-04-30 | COMP | Rule 16 | 33 | 41 | 16 | 1 | 151 | 28 | 265
12290 | 2019-04-12 | 2019-05-30 | 2019-09-27 | 2019-09-27 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-10-03 | COMP | 2019-12-18 | COMP | Rule 16 | 34 | 85 | 10 | 1 | 0 | 47 | 173
12497 | 2019-04-12 | 2019-06-10 | 2019-07-05 | 2019-07-05 | COMP | 2019-08-14 | COMP | 2019-08-14 | NOTN | 2020-06-15 | COMP | 2020-06-25 | COMP | Rule 16 | 41 | 19 | 29 |  |  |  | 304
12695 | 2019-04-12 | 2019-06-18 | 2019-08-21 | 2019-08-21 | COMP | 2020-04-14 | NOTN | 2020-04-14 | COMP | 2020-10-06 | COMP | 2020-11-04 | COMP | Other | 47 | 46 |  | 162 | 124 | 22 | 397
12708 | 2019-04-12 | 2019-06-19 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-17 | COMP | 2019-07-17 | COMP | 2019-10-16 | COMP | 2019-11-18 | COMP | Rule 16 | 48 | 16 | 5 | 1 | 65 | 23 | 153
12713 | 2019-04-12 | 2019-06-20 | 2020-04-22 | 2020-04-22 | COMP | 2020-09-14 | COMP | 2020-08-18 | COMP | 2021-06-08 | COMP | 2021-07-14 | COMP | Rule 15/16 | 49 | 211 | 102 |  | 202 | 26 | 568
12714 | 2019-04-12 | 2019-06-20 | 2020-05-11 | 2020-05-11 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-12-02 | COMP | 2022-02-23 | COMP | Rule 15/16 | 49 | 224 | 76 | 1 | 319 | 58 | 722
13311 | 2019-04-12 | 2019-07-20 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-01-13 | COMP | 2020-01-15 | COMP | Rule 16 | 69 | 64 | 22 | 1 | 35 | 3 | 191
14417 | 2019-04-12 | 2019-09-09 | 2019-12-17 | 2019-12-17 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2021-05-11 | COMP | 2021-06-24 | COMP | Rule 15/16 | 104 | 69 | 45 | 1 | 309 | 32 | 555
15322 | 2019-04-12 | 2019-10-25 | 2020-02-28 | 2021-02-23 | COMP | 2021-02-26 | COMP | 2021-02-26 | COMP | 2021-04-20 | COMP | 2021-04-21 | COMP | Rule 16 | 138 | 84 | 4 | 1 | 38 | 2 | 510
15516 | 2019-04-12 | 2019-11-05 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-16 | COMP | 2020-08-06 | COMP | 2020-08-07 | COMP | 2020-08-29 | COMP | Rule 16 | 145 | 134 | 20 | 38 | 2 | 16 | 350
16694 | 2019-04-12 | 2020-01-13 | 2020-05-28 | 2020-05-28 | COMP | 2020-08-12 | COMP | 2020-11-13 | COMP | 2021-03-24 | COMP | 2021-04-01 | COMP | Rule 16 | 189 | 96 | 55 | 66 | 88 | 7 | 496
18283 | 2019-04-12 | 2020-03-18 | 2020-05-18 | 2020-05-18 | COMP | 2021-07-09 | COMP | 2021-07-09 | COMP | 2021-08-31 | COMP | 2021-09-08 | COMP | Rule 16 | 234 | 44 | 289 | 1 | 38 | 6 | 607
11126 | 2019-04-13 | 2019-04-15 | 2019-08-20 | 2019-10-14 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-07-14 | COMP | 2020-08-06 | COMP | Rule 16 | 1 | 90 | 119 | 1 | 71 | 18 | 333
11371 | 2019-04-13 | 2019-04-24 | 2019-05-20 | 2019-05-20 | COMP | 2019-05-22 | NOTN | 2019-05-22 | COMP | 2019-06-12 | COMP | 2019-06-14 | COMP | Other | 8 | 19 |  | 3 | 15 | 3 | 44
11713 | 2019-04-13 | 2019-05-08 | 2019-05-29 | 2019-05-29 | COMP | 2019-05-31 | NOTN | 2019-05-31 | COMP | 2019-06-10 | COMP | 2019-06-12 | COMP | Other | 18 | 15 |  | 3 | 7 | 3 | 42
12199 | 2019-04-13 | 2019-05-28 | 2019-09-19 | 2019-09-19 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-11-19 | COMP | 2019-12-18 | COMP | Rule 16 | 31 | 81 | 8 | 1 | 36 | 20 | 172
13810 | 2019-04-13 | 2019-08-12 | 2020-01-21 | 2020-01-21 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-02-06 | COMP | 2020-03-23 | COMP | Rule 16 | 84 | 110 | 10 | 1 | 4 | 32 | 236
11199 | 2019-04-14 | 2019-04-17 | 2019-07-18 | 2019-07-18 | COMP | 2019-04-17 | NOTN | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-11-12 | COMP | Other | 3 | 65 |  | 37 | 1 | 46 | 148
12458 | 2019-04-14 | 2019-06-07 | 2019-06-24 | 2019-06-24 | COMP | 2019-06-24 | NOTN | 2019-06-24 | COMP | 2019-06-25 | COMP | 2019-08-01 | COMP | Rule 16 | 39 | 12 |  | 1 | 2 | 27 | 77
14796 | 2019-04-14 | 2019-09-27 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-07 | COMP | 2020-02-21 | COMP | 2020-06-17 | COMP | 2020-10-09 | COMP | Rule 16 | 117 | 74 | 17 | 10 | 83 | 82 | 378
15728 | 2019-04-14 | 2019-11-19 | 2020-05-03 | 2020-05-03 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-12-09 | COMP | 2021-01-26 | COMP | Rule 16 | 153 | 113 | 116 | 1 | 38 | 32 | 449
11157 | 2019-04-15 | 2019-04-15 | 2019-05-01 | 2019-10-20 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-05-09 | COMP | 2020-07-30 | COMP | Rule 16 | 1 | 13 | 51 | 1 | 88 | 58 | 328
11176 | 2019-04-15 | 2019-04-17 | 2019-06-28 | 2019-06-28 | COMP | 2019-08-27 | COMP | 2019-09-27 | COMP | 2019-09-09 | COMP | 2019-11-07 | COMP | Rule 15/16 | 3 | 52 | 42 | 23 | 0 | 30 | 146
11595 | 2019-04-15 | 2019-05-03 | 2019-11-08 | 2019-11-08 | COMP | 2020-01-15 | COMP | 2020-01-22 | COMP | 2020-10-29 | COMP | 2020-11-09 | COMP | Rule 16 | 15 | 133 | 44 | 5 | 199 | 8 | 399
11597 | 2019-04-15 | 2019-05-03 | 2019-06-06 | 2019-06-06 | COMP | 2019-09-06 | COMP | 2019-09-24 | COMP | 2020-01-07 | COMP | 2020-01-27 | COMP | Rule 16 | 15 | 24 | 65 | 13 | 71 | 14 | 197
11659 | 2019-04-15 | 2019-05-07 | 2019-07-27 | 2019-11-05 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-01-17 | COMP | 2020-02-14 | COMP | Rule 16 | 17 | 57 | 15 | 1 | 35 | 20 | 211
11745 | 2019-04-15 | 2019-05-09 | 2019-06-13 | 2019-06-13 | COMP | 2019-06-17 | COMP | 2019-07-02 | COMP | 2019-10-15 | COMP | 2019-11-13 | COMP | Rule 16 | 19 | 25 | 3 | 12 | 74 | 21 | 149
11746 | 2019-04-15 | 2019-05-09 | 2019-06-21 | 2019-06-21 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-12-29 | INPR | 2019-09-11 | COMP | Rule 16 | 19 | 31 | 19 | 1 |  |  | 105
11804 | 2019-04-15 | 2019-05-13 | 2019-08-26 | 2019-08-26 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-19 | COMP | 2019-12-19 | COMP | Rule 15/16 | 21 | 74 | 39 | 1 | 1 | 41 | 173
11889 | 2019-04-15 | 2019-05-15 | 2019-07-30 | 2019-09-04 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2019-10-15 | COMP | 2019-10-23 | COMP | Rule 16 | 23 | 53 | 10 | 1 | 21 | 7 | 135
11904 | 2019-04-15 | 2019-05-15 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-16 | COMP | 2019-08-28 | COMP | 2019-08-21 | COMP | 2019-10-05 | COMP | Rule 16 | 23 | 39 | 5 | 32 | 0 | 27 | 122
12060 | 2019-04-15 | 2019-05-23 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-20 | COMP | 2019-09-10 | COMP | 2019-08-27 | NOTN | 2019-11-08 | COMP | Rule 16 | 29 | 38 | 25 | 15 |  |  | 147
12079 | 2019-04-15 | 2019-05-22 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-21 | COMP | 2019-09-19 | COMP | 2019-08-30 | COMP | 2019-10-04 | COMP | Rule 16 | 28 | 58 | 7 | 21 | 0 | 12 | 122
12134 | 2019-04-15 | 2019-05-24 | 2019-08-16 | 2019-08-16 | COMP | 2019-10-07 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-03-02 | COMP | Rule 16 | 30 | 59 | 36 | 81 | 1 | 19 | 221
12201 | 2019-04-15 | 2019-05-28 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-13 | COMP | 2019-10-15 | COMP | 2019-12-04 | COMP | 2020-01-01 | COMP | Rule 16 | 31 | 43 | 13 | 45 | 34 | 19 | 180
12265 | 2019-04-15 | 2019-05-29 | 2019-09-23 | 2019-09-23 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-10-03 | COMP | 2019-11-03 | COMP | Rule 16 | 32 | 82 | 5 | 1 | 5 | 22 | 142
12305 | 2019-04-15 | 2019-05-30 | 2019-06-27 | 2019-06-27 | COMP | 2019-08-16 | COMP | 2019-08-19 | COMP | 2019-11-05 | COMP | 2019-11-22 | COMP | Rule 16 | 33 | 21 | 36 | 2 | 56 | 13 | 156
12439 | 2019-04-15 | 2019-06-06 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-08-20 | COMP | 2019-09-05 | COMP | Rule 15/16 | 38 | 23 | 6 | 1 | 26 | 12 | 101
12511 | 2019-04-15 | 2019-06-11 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-08 | COMP | 2019-10-02 | COMP | 2019-09-19 | COMP | 2019-11-13 | COMP | Rule 16 | 41 | 33 | 10 | 39 | 0 | 30 | 149
12545 | 2019-04-15 | 2019-06-12 | 2019-09-20 | 2019-09-20 | COMP | 2019-09-24 | COMP | 2019-11-07 | COMP | 2019-11-18 | COMP | 2019-12-11 | COMP | Rule 16 | 42 | 71 | 3 | 33 | 7 | 16 | 167
12572 | 2019-04-15 | 2019-06-13 | 2019-09-05 | 2019-09-05 | COMP | 2019-10-11 | COMP | 2019-10-21 | COMP | 2019-11-27 | COMP | 2019-12-18 | COMP | Rule 16 | 43 | 59 | 27 | 7 | 27 | 14 | 172
12604 | 2019-04-15 | 2019-06-14 | 2019-07-13 | 2019-07-13 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-08 | COMP | 2019-09-13 | COMP | Rule 16 | 44 | 20 | 22 | 1 | 0 | 23 | 107
12836 | 2019-04-15 | 2019-06-24 | 2019-09-12 | 2019-09-12 | COMP | 2019-10-01 | COMP | 2019-10-01 | COMP | 2019-10-07 | COMP | 2019-11-12 | COMP | Rule 16 | 50 | 57 | 14 | 1 | 5 | 26 | 148
12905 | 2019-04-15 | 2019-06-28 | 2019-11-13 | 2019-11-25 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2021-08-17 | COMP | 2021-10-08 | COMP | Rule 16 | 54 | 96 | 55 | 1 | 381 | 38 | 628
12932 | 2019-04-15 | 2019-07-01 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2020-11-21 | INPR | 2019-11-02 | COMP | Rule 16 | 55 | 24 | 12 | 1 |  |  | 142
12954 | 2019-04-15 | 2019-07-01 | 2019-10-27 | 2019-10-29 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2020-01-29 | COMP | 2020-03-04 | COMP | Rule 16 | 55 | 83 | 6 | 1 | 56 | 25 | 223
12955 | 2019-04-15 | 2019-07-01 | 2019-10-27 | 2019-10-27 | COMP | 2019-11-05 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-03-05 | COMP | Rule 16 | 55 | 83 | 7 | 56 | 1 | 26 | 224
14346 | 2019-04-15 | 2019-09-05 | 2020-02-05 | 2020-02-05 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2022-01-30 | INPR | 2020-09-24 | COMP | Rule 16 | 101 | 104 | 33 | 1 |  |  | 367
14352 | 2019-04-15 | 2019-09-05 | 2019-12-05 | 2020-03-03 | COMP | 2020-04-28 | COMP | 2020-05-04 | COMP | 2020-10-23 | COMP | 2020-11-13 | COMP | Rule 15/16 | 101 | 63 | 41 | 5 | 123 | 15 | 402
16952 | 2019-04-15 | 2020-01-24 | 2020-04-30 | 2020-08-14 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-07-13 | COMP | 2020-11-30 | COMP | Other | 196 | 69 |  | 1 | 24 | 97 | 411
18593 | 2019-04-15 | 2020-03-30 | 2020-09-10 | 2020-09-10 | COMP | 2020-09-24 | COMP | 2021-01-06 | COMP | 2021-01-15 | COMP | 2021-01-19 | COMP | Rule 16 | 241 | 117 | 11 | 70 | 8 | 2 | 444
11163 | 2019-04-16 | 2019-04-16 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-06 | COMP | 2019-07-16 | INPR | 2019-08-13 | COMP | 2019-09-09 | COMP | Rule 16 | 1 | 21 | 17 |  |  |  | 102
11234 | 2019-04-16 | 2019-04-18 | 2019-10-24 | 2019-10-24 | COMP | 2021-04-23 | COMP | 2021-04-23 | COMP | 2022-08-09 | COMP | 2022-08-31 | COMP | Rule 16 | 3 | 133 | 376 | 1 | 327 | 17 | 852
11235 | 2019-04-16 | 2019-04-18 | 2019-07-31 | 2019-07-31 | COMP | 2021-02-25 | COMP | 2021-02-26 | COMP | 2022-07-11 | COMP | 2022-08-15 | COMP | Rule 16 | 3 | 73 | 395 | 2 | 346 | 26 | 840
11288 | 2019-04-16 | 2019-04-22 | 2019-12-30 | 2019-12-30 | COMP | 2020-06-02 | COMP | 2020-06-12 | COMP | 2020-07-23 | COMP | 2020-09-02 | COMP | Rule 16 | 5 | 174 | 108 | 9 | 30 | 30 | 351
11523 | 2019-04-16 | 2019-05-01 | 2019-08-16 | 2019-08-16 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-12-30 | COMP | 2020-01-08 | COMP | Rule 16 | 12 | 76 | 21 | 1 | 72 | 7 | 184
11533 | 2019-04-16 | 2019-05-01 | 2019-08-16 | 2019-08-16 | COMP | 2019-05-01 | NOTN | 2019-10-10 | COMP | 2019-11-05 | COMP | 2019-12-10 | COMP | Other | 12 | 76 |  | 39 | 19 | 23 | 165
11593 | 2019-04-16 | 2019-05-03 | 2019-08-27 | 2019-08-27 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-09-30 | COMP | Rule 16 | 14 | 81 | 5 | 1 | 1 | 20 | 117
11679 | 2019-04-16 | 2019-05-07 | 2019-06-08 | 2019-06-08 | COMP | 2019-06-09 | NOTN | 2019-06-09 | COMP | 2019-06-07 | COMP | 2019-07-19 | COMP | Other | 16 | 23 |  | 0 | 0 | 29 | 67
11778 | 2019-04-16 | 2019-05-10 | 2019-08-31 | 2019-08-31 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-07-02 | COMP | 2020-08-24 | COMP | Rule 16 | 19 | 79 | 207 | 1 | 4 | 38 | 344
11797 | 2019-04-16 | 2019-05-13 | 2019-11-08 | 2019-11-08 | COMP | 2019-11-19 | COMP | 2020-03-31 | COMP | 2020-03-24 | COMP | 2020-04-09 | COMP | Rule 15/16 | 20 | 127 | 7 | 90 | 0 | 8 | 248
11883 | 2019-04-16 | 2019-05-15 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-08-21 | COMP | 2019-08-31 | COMP | Rule 16 | 22 | 59 | 10 | 1 | 2 | 8 | 97
12076 | 2019-04-16 | 2019-05-22 | 2019-10-21 | 2019-10-21 | COMP | 2019-11-07 | COMP | 2019-11-25 | COMP | 2020-02-06 | COMP | 2020-03-31 | COMP | Rule 16 | 27 | 106 | 14 | 12 | 49 | 38 | 241
12233 | 2019-04-16 | 2019-05-28 | 2019-08-01 | 2019-08-01 | COMP | 2019-08-08 | COMP | 2019-09-18 | COMP | 2020-01-06 | COMP | 2020-01-07 | COMP | Rule 16 | 30 | 47 | 6 | 29 | 74 | 2 | 183
12244 | 2019-04-16 | 2019-05-29 | 2019-09-09 | 2019-09-10 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2021-03-27 | INPR | 2020-03-23 | COMP | Rule 16 | 31 | 72 | 54 | 1 |  |  | 235
12300 | 2019-04-16 | 2019-05-30 | 2019-07-25 | 2019-08-20 | COMP | 2019-09-09 | COMP | 2019-11-02 | COMP | 2019-09-19 | COMP | 2020-01-03 | COMP | Rule 16 | 32 | 40 | 14 | 40 | 0 | 40 | 181
12301 | 2019-04-16 | 2019-05-31 | 2019-07-29 | 2019-07-29 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-10-19 | COMP | 2020-12-30 | COMP | Rule 16 | 33 | 41 | 312 | 1 | 0 | 48 | 431
12302 | 2019-04-16 | 2019-05-30 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-20 | COMP | 2019-09-21 | COMP | 2019-10-24 | COMP | 2019-12-10 | COMP | Rule 16 | 32 | 43 | 16 | 23 | 24 | 31 | 165
12487 | 2019-04-16 | 2019-06-10 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-10-04 | COMP | 2019-10-04 | COMP | Rule 16 | 39 | 39 | 18 | 1 | 27 | 1 | 121
12552 | 2019-04-16 | 2019-06-12 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2020-04-27 | COMP | 2020-05-30 | COMP | Rule 16 | 41 | 87 | 18 | 1 | 117 | 24 | 283
12553 | 2019-04-16 | 2019-06-12 | 2019-09-07 | 2019-09-07 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2021-01-14 | COMP | 2021-02-18 | COMP | Rule 16 | 41 | 61 | 227 | 1 | 114 | 24 | 464
12825 | 2019-04-16 | 2019-06-24 | 2020-01-06 | 2020-01-06 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-09-17 | COMP | 2020-10-27 | COMP | Rule 15/16 | 49 | 134 | 122 | 1 | 59 | 29 | 389
13136 | 2019-04-16 | 2019-07-11 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-23 | COMP | 2019-10-10 | COMP | 2019-11-19 | COMP | 2019-12-03 | COMP | Rule 16 | 61 | 35 | 18 | 14 | 28 | 9 | 160
13166 | 2019-04-16 | 2019-07-15 | 2020-01-15 | 2020-10-20 | COMP | 2020-01-16 | NOTN | 2020-11-23 | COMP | 2020-12-08 | COMP | 2021-01-12 | COMP | Other | 63 | 127 |  | 24 | 10 | 24 | 439
13266 | 2019-04-16 | 2019-07-18 | 2019-09-13 | 2019-09-13 | COMP | 2019-11-08 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-18 | COMP | Rule 16 | 66 | 41 | 41 | 3 | 1 | 4 | 151
13284 | 2019-04-16 | 2019-07-19 | 2020-01-28 | 2020-01-28 | COMP | 2020-03-30 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-07-09 | COMP | Rule 16 | 67 | 131 | 44 | 31 | 1 | 43 | 312
13402 | 2019-04-16 | 2019-07-24 | 2019-11-13 | 2019-11-13 | COMP | 2020-10-23 | COMP | 2020-07-06 | COMP | 2021-02-02 | COMP | 2021-03-19 | COMP | Rule 16 | 70 | 79 | 240 |  | 145 | 33 | 485
13502 | 2019-04-16 | 2019-07-29 | 2019-08-01 | 2019-08-01 | COMP | 2019-09-05 | COMP | 2019-08-12 | COMP | 2019-08-05 | COMP | 2019-09-27 | COMP | Rule 16 | 73 | 4 | 25 |  | 0 | 34 | 116
13673 | 2019-04-16 | 2019-08-05 | 2020-08-04 | 2020-08-04 | COMP | 2020-12-24 | COMP | 2020-12-24 | COMP | 2021-02-02 | COMP | 2021-03-25 | COMP | Rule 16 | 78 | 253 | 99 | 1 | 26 | 37 | 489
13717 | 2019-04-16 | 2019-08-06 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-02-07 | COMP | 2020-05-21 | COMP | Rule 16 | 79 | 124 | 23 | 1 | 0 | 55 | 278
13784 | 2019-04-16 | 2019-08-09 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-22 | COMP | 2020-01-24 | COMP | 2020-11-20 | COMP | 2020-12-07 | COMP | Rule 16 | 82 | 98 | 15 | 3 | 212 | 10 | 415
13870 | 2019-04-16 | 2019-08-14 | 2019-10-26 | 2019-10-26 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-01-30 | COMP | 2020-04-20 | COMP | Rule 16 | 85 | 52 | 11 | 1 | 53 | 57 | 255
13953 | 2019-04-16 | 2019-08-19 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-17 | COMP | 2019-12-20 | COMP | Rule 16 | 88 | 46 | 25 | 1 | 14 | 4 | 173
14286 | 2019-04-16 | 2019-09-03 | 2020-01-13 | 2020-03-24 | COMP | 2020-04-01 | COMP | 2020-08-03 | COMP | 2020-10-14 | COMP | 2020-11-17 | COMP | Rule 16 | 98 | 90 | 7 | 88 | 52 | 24 | 403
14631 | 2019-04-16 | 2019-09-20 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-19 | COMP | 2020-04-16 | COMP | 2020-12-15 | COMP | 2021-03-16 | COMP | Rule 16 | 111 | 83 | 20 | 42 | 169 | 62 | 482
14948 | 2019-04-16 | 2019-10-05 | 2020-03-11 | 2020-03-11 | COMP | 2020-05-11 | COMP | 2020-07-24 | COMP | 2023-09-02 | INPR | 2020-08-27 | COMP | Rule 16 | 121 | 106 | 44 | 54 |  |  | 347
15411 | 2019-04-16 | 2019-11-01 | 2020-03-11 | 2020-03-11 | COMP | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-09-08 | COMP | 2020-10-05 | COMP | Rule 16 | 141 | 87 | 112 | 1 | 17 | 20 | 373
15990 | 2019-04-16 | 2019-12-05 | 2020-03-27 | 2020-03-27 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-05-19 | COMP | 2020-05-28 | COMP | Rule 16 | 162 | 78 | 25 | 1 | 14 | 7 | 282
16663 | 2019-04-16 | 2020-01-10 | 2020-02-21 | 2020-02-21 | COMP | 2020-05-07 | COMP | 2020-05-18 | COMP | 2020-05-15 | COMP | 2020-05-20 | COMP | Rule 16 | 186 | 29 | 55 | 8 | 0 | 3 | 277
16782 | 2019-04-16 | 2020-01-15 | 2020-06-16 | 2020-06-16 | COMP | 2020-06-16 | NOTN | 2020-06-19 | COMP | 2020-06-25 | COMP | 2021-03-22 | COMP | Other | 189 | 107 |  | 4 | 5 | 185 | 486
16853 | 2019-04-16 | 2020-01-21 | 2020-06-18 | 2020-07-15 | COMP | 2020-07-20 | COMP | 2020-08-31 | COMP | 2020-08-03 | COMP | 2020-10-22 | COMP | Rule 16 | 192 | 106 | 4 | 31 | 0 | 38 | 386
11557 | 2019-04-17 | 2019-05-03 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-26 | COMP | 2019-10-17 | COMP | 2019-11-05 | COMP | 2019-11-29 | COMP | Rule 16 | 13 | 88 | 15 | 16 | 14 | 16 | 157
11793 | 2019-04-17 | 2019-05-13 | 2019-06-19 | 2019-06-19 | COMP | 2019-07-01 | COMP | 2019-07-25 | COMP | 2019-12-29 | INPR | 2019-07-31 | COMP | Rule 16 | 19 | 27 | 9 | 18 |  |  | 74
11796 | 2019-04-17 | 2019-05-13 | 2019-12-07 | 2019-12-07 | COMP | 2020-02-11 | COMP | 2020-05-12 | COMP | 2020-05-19 | COMP | 2020-06-27 | COMP | Rule 15/16 | 19 | 144 | 44 | 65 | 6 | 28 | 302
11846 | 2019-04-17 | 2019-05-14 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-22 | COMP | 2019-10-21 | COMP | 2019-11-12 | COMP | 2020-03-05 | COMP | Rule 16 | 20 | 62 | 10 | 42 | 16 | 77 | 222
11910 | 2019-04-17 | 2019-05-16 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-29 | COMP | 2019-09-19 | COMP | 2019-10-21 | COMP | 2019-12-15 | COMP | Rule 16 | 22 | 60 | 15 | 15 | 23 | 37 | 167
12027 | 2019-04-17 | 2019-05-21 | 2019-09-14 | 2021-02-24 | COMP | 2021-03-24 | COMP | 2021-12-23 | COMP | 2021-12-04 | COMP | 2022-01-25 | COMP | Rule 16 | 25 | 81 | 21 | 191 | 0 | 23 | 699
12028 | 2019-04-17 | 2019-05-21 | 2019-09-14 | 2019-09-14 | COMP | 2020-03-30 | COMP | 2020-07-03 | COMP | 2020-06-29 | COMP | 2020-08-14 | COMP | Rule 16 | 25 | 81 | 134 | 69 | 0 | 31 | 337
12182 | 2019-04-17 | 2019-05-28 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-24 | COMP | 2019-09-27 | COMP | 2019-11-04 | COMP | 2019-12-05 | COMP | Rule 16 | 29 | 44 | 41 | 4 | 27 | 21 | 161
12236 | 2019-04-17 | 2019-05-28 | 2019-07-26 | 2019-07-26 | COMP | 2019-08-13 | COMP | 2019-09-04 | COMP | 2019-11-12 | COMP | 2020-02-21 | COMP | Rule 16 | 29 | 43 | 13 | 16 | 49 | 68 | 213
12289 | 2019-04-17 | 2019-05-30 | 2019-06-07 | 2019-06-07 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-30 | COMP | 2019-08-15 | COMP | Rule 16 | 31 | 7 | 27 | 1 | 11 | 13 | 85
12413 | 2019-04-17 | 2019-06-07 | 2019-08-12 | 2019-08-12 | COMP | 2020-03-27 | COMP | 2020-03-30 | COMP | 2020-04-10 | COMP | 2020-05-10 | COMP | Rule 16 | 37 | 46 | 157 | 2 | 10 | 21 | 268
12541 | 2019-04-17 | 2019-06-11 | 2019-08-10 | 2019-08-10 | COMP | 2019-09-03 | COMP | 2019-10-02 | COMP | 2020-09-22 | COMP | 2020-12-11 | COMP | Rule 16 | 39 | 43 | 16 | 22 | 246 | 56 | 418
12564 | 2019-04-17 | 2019-06-12 | 2019-08-27 | 2020-12-16 | COMP | 2021-02-18 | COMP | 2021-04-09 | COMP | 2020-12-21 | COMP | 2021-08-24 | COMP | Rule 16 | 40 | 54 | 43 | 37 | 0 | 96 | 594
12753 | 2019-04-17 | 2019-06-20 | 2019-10-29 | 2019-10-29 | COMP | 2020-01-09 | COMP | 2020-05-14 | COMP | 2020-05-01 | COMP | 2020-06-10 | COMP | Rule 15/16 | 46 | 92 | 48 | 89 | 0 | 19 | 290
12839 | 2019-04-17 | 2019-06-24 | 2019-11-01 | 2019-11-01 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-07 | COMP | 2020-02-18 | COMP | Rule 16 | 48 | 93 | 50 | 1 | 0 | 22 | 210
12930 | 2019-04-17 | 2019-07-01 | 2019-08-19 | 2019-08-19 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-10-15 | COMP | 2019-11-19 | COMP | Rule 16 | 53 | 35 | 15 | 1 | 27 | 25 | 151
13132 | 2019-04-17 | 2019-07-12 | 2019-09-10 | 2019-09-10 | COMP | 2019-09-16 | COMP | 2019-10-28 | COMP | 2019-09-23 | COMP | 2019-12-05 | COMP | Rule 16 | 61 | 42 | 5 | 31 | 0 | 26 | 161
13187 | 2019-04-17 | 2019-07-15 | 2019-08-17 | 2019-08-17 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-10-23 | COMP | 2019-11-09 | COMP | Rule 16 | 62 | 25 | 30 | 1 | 18 | 13 | 145
13205 | 2019-04-17 | 2019-07-16 | 2020-10-15 | 2020-10-15 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP | 2021-04-06 | COMP | 2021-05-06 | COMP | Rule 15/16 | 63 | 318 | 76 | 1 | 42 | 23 | 518
13343 | 2019-04-17 | 2019-07-22 | 2019-09-24 | 2019-09-26 | COMP | 2019-11-04 | COMP | 2019-11-14 | COMP | 2019-11-05 | COMP | 2020-01-23 | COMP | Rule 16 | 67 | 46 | 28 | 8 | 0 | 46 | 193
13849 | 2019-04-17 | 2019-08-13 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-18 | COMP | 2020-01-24 | COMP | 2019-12-24 | COMP | 2020-01-31 | COMP | Rule 16 | 83 | 70 | 19 | 25 | 0 | 6 | 199
13944 | 2019-04-17 | 2019-08-17 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2020-07-14 | COMP | 2020-08-28 | COMP | Rule 16 | 86 | 40 | 10 | 1 | 180 | 34 | 347
14060 | 2019-04-17 | 2019-08-23 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-18 | COMP | 2021-02-16 | COMP | 2021-02-16 | COMP | 2021-03-22 | COMP | Rule 16 | 91 | 159 | 26 | 188 | 1 | 25 | 485
15824 | 2019-04-17 | 2019-11-22 | 2020-01-16 | 2020-01-16 | COMP | 2020-04-01 | COMP | 2020-04-13 | COMP | 2020-05-04 | COMP | 2020-05-13 | COMP | Rule 16 | 154 | 36 | 53 | 9 | 16 | 8 | 271
16068 | 2019-04-17 | 2019-12-09 | 2020-02-07 | 2020-02-07 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-06-25 | COMP | 2020-08-13 | COMP | Rule 16 | 163 | 42 | 12 | 1 | 87 | 36 | 336
16307 | 2019-04-17 | 2019-12-19 | 2020-03-26 | 2020-03-26 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2020-08-28 | COMP | 2020-09-30 | COMP | Rule 16 | 171 | 67 | 72 | 1 | 40 | 23 | 369
19002 | 2019-04-17 | 2020-04-16 | 2020-06-30 | 2020-07-24 | COMP | 2020-08-10 | COMP | 2020-09-30 | COMP | 2020-11-02 | COMP | 2020-12-02 | COMP | Rule 15/16 | 252 | 53 | 12 | 37 | 24 | 20 | 411
20186 | 2019-04-17 | 2020-06-09 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-11 | COMP | 2020-08-29 | COMP | 2020-09-29 | COMP | 2020-11-03 | COMP | Rule 16 | 289 | 24 | 23 | 14 | 21 | 26 | 393
11238 | 2019-04-18 | 2019-04-18 | 2019-04-18 | 2019-04-18 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-10-21 | INPR | 2019-06-19 | COMP | Rule 16 | 1 | 1 | 15 | 1 |  |  | 44
12082 | 2019-04-18 | 2019-05-22 | 2019-10-14 | 2019-10-14 | COMP | 2019-12-09 | COMP | 2020-02-27 | COMP | 2020-02-04 | COMP | 2020-03-08 | COMP | Rule 16 | 25 | 101 | 38 | 55 | 0 | 7 | 222
12112 | 2019-04-18 | 2019-05-23 | 2019-08-26 | 2019-08-30 | COMP | 2020-08-21 | COMP | 2020-09-08 | COMP | 2020-08-30 | COMP | 2020-10-07 | COMP | Rule 16 | 26 | 66 | 247 | 12 | 0 | 22 | 373
12149 | 2019-04-18 | 2019-05-24 | 2019-07-05 | 2019-07-05 | COMP | 2019-07-05 | NOTN | 2019-07-05 | COMP | 2019-07-04 | COMP | 2019-08-16 | COMP | Other | 27 | 29 |  | 1 | 0 | 31 | 85
12176 | 2019-04-18 | 2019-05-29 | 2019-09-30 | 2019-10-28 | COMP | 2019-11-20 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-01-02 | COMP | Rule 15/16 | 29 | 87 | 17 | 17 | 1 | 12 | 178
12612 | 2019-04-18 | 2019-06-17 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-21 | COMP | 2019-11-14 | COMP | 2020-01-31 | COMP | 2020-06-13 | COMP | Rule 15/16 | 42 | 66 | 24 | 18 | 52 | 94 | 291
12639 | 2019-04-18 | 2019-06-17 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-03-04 | COMP | 2020-03-10 | COMP | Rule 16 | 42 | 66 | 31 | 1 | 84 | 5 | 224
12711 | 2019-04-18 | 2019-06-19 | 2019-06-29 | 2019-06-29 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | Rule 16 | 44 | 8 | 11 | 1 | 12 | 1 | 73
12747 | 2019-04-18 | 2019-06-20 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-04 | COMP | 2020-05-31 | REQD | 2019-11-14 | COMP | 2019-12-02 | COMP | Rule 16 | 45 | 89 | 8 |  |  |  | 157
12748 | 2019-04-18 | 2019-06-20 | 2019-08-24 | 2019-08-24 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-10-10 | COMP | 2019-11-05 | COMP | Rule 16 | 45 | 46 | 9 | 1 | 25 | 19 | 141
12826 | 2019-04-18 | 2019-06-24 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-11-08 | COMP | 2019-11-21 | COMP | Rule 16 | 47 | 43 | 17 | 1 | 40 | 9 | 152
12850 | 2019-04-18 | 2019-06-25 | 2019-09-10 | 2019-11-14 | COMP | 2019-12-09 | COMP | 2020-02-28 | COMP | 2021-03-04 | COMP | 2021-03-13 | COMP | Rule 16 | 48 | 54 | 16 | 56 | 256 | 7 | 478
12963 | 2019-04-18 | 2019-07-02 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-07 | COMP | 2019-11-12 | COMP | 2020-06-10 | COMP | 2020-06-17 | COMP | Rule 15/16 | 53 | 77 | 14 | 3 | 145 | 6 | 294
12982 | 2019-04-18 | 2019-07-02 | 2019-12-04 | 2019-12-04 | COMP | 2020-03-19 | COMP | 2020-07-08 | COMP | 2020-04-22 | COMP | 2020-08-11 | COMP | Rule 16 | 53 | 107 | 73 | 79 | 0 | 25 | 333
13067 | 2019-04-18 | 2019-07-08 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-10-23 | COMP | 2019-11-12 | COMP | Rule 16 | 56 | 8 | 19 | 1 | 52 | 14 | 145
13125 | 2019-04-18 | 2019-07-11 | 2019-08-29 | 2019-08-29 | COMP | 2019-09-13 | COMP | 2020-11-13 | COMP | 2021-02-17 | COMP | 2022-03-23 | COMP | Rule 16 | 59 | 36 | 11 | 296 | 63 | 278 | 738
13495 | 2019-04-18 | 2019-07-29 | 2019-08-22 | 2019-08-22 | COMP | 2019-08-29 | COMP | 2019-09-10 | COMP | 2019-10-19 | COMP | 2019-11-09 | COMP | Rule 16 | 71 | 19 | 6 | 8 | 29 | 15 | 144
13815 | 2019-04-18 | 2019-08-13 | 2020-02-05 | 2020-02-05 | COMP | 2020-03-10 | COMP | 2020-11-30 | COMP | 2020-11-19 | COMP | 2020-12-14 | COMP | Rule 15/16 | 82 | 120 | 24 | 185 | 0 | 11 | 418
13817 | 2019-04-18 | 2019-08-12 | 2019-10-18 | 2019-10-18 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-11-20 | COMP | 2019-11-25 | COMP | Rule 16 | 81 | 49 | 11 | 1 | 13 | 4 | 154
13922 | 2019-04-18 | 2019-08-16 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-01 | COMP | 2020-06-04 | COMP | 2022-08-21 | INPR | 2020-06-18 | COMP | Rule 16 | 85 | 48 | 8 | 147 |  |  | 295
14038 | 2019-04-18 | 2019-08-22 | 2019-10-16 | 2019-10-16 | COMP | 2020-01-15 | COMP | 2020-01-15 | COMP | 2020-01-16 | COMP | 2020-04-02 | COMP | Rule 16 | 89 | 39 | 61 | 1 | 2 | 54 | 241
14272 | 2019-04-18 | 2019-09-04 | 2020-05-07 | 2020-07-21 | COMP | 2020-07-31 | COMP | 2020-10-16 | COMP | 2020-10-15 | COMP | 2020-12-03 | COMP | Rule 16 | 97 | 170 | 9 | 55 | 0 | 32 | 411
14787 | 2019-04-18 | 2019-09-27 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-13 | COMP | 2020-01-07 | COMP | Rule 16 | 114 | 18 | 15 | 1 | 2 | 36 | 181
14992 | 2019-04-18 | 2019-10-09 | 2020-01-16 | 2020-02-11 | COMP | 2020-02-24 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-06-26 | COMP | Rule 15/16 | 122 | 67 | 9 | 81 | 1 | 9 | 301
15226 | 2019-04-18 | 2019-10-21 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-09-17 | COMP | 2020-10-09 | COMP | Rule 16 | 130 | 58 | 30 | 1 | 144 | 17 | 375
15858 | 2019-04-18 | 2019-11-25 | 2020-02-18 | 2020-02-24 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-02-25 | COMP | 2020-10-07 | COMP | Rule 16 | 154 | 56 | 9 | 1 | 0 | 153 | 373
11568 | 2019-04-19 | 2019-05-02 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-07 | NOTN | 2019-10-21 | COMP | 2023-04-30 | INPR | 2019-12-10 | COMP | Other | 10 | 86 |  | 35 |  |  | 162
11627 | 2019-04-19 | 2019-05-06 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-01 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2020-01-07 | COMP | Rule 15/16 | 12 | 95 | 10 | 28 | 1 | 39 | 180
11726 | 2019-04-19 | 2019-05-08 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-02 | COMP | 2020-01-08 | COMP | 2020-01-14 | COMP | 2020-01-27 | COMP | Rule 16 | 14 | 96 | 48 | 26 | 5 | 9 | 193
11943 | 2019-04-19 | 2019-05-17 | 2019-09-27 | 2019-09-27 | COMP | 2019-12-11 | COMP | 2020-05-08 | COMP | 2020-05-21 | COMP | 2020-07-31 | COMP | Rule 16 | 21 | 93 | 51 | 104 | 10 | 51 | 325
11970 | 2019-04-19 | 2019-05-20 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-12 | COMP | 2019-10-14 | COMP | 2019-12-09 | COMP | 2020-01-08 | COMP | Rule 16 | 22 | 66 | 16 | 23 | 38 | 21 | 181
12058 | 2019-04-19 | 2019-05-23 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-09 | COMP | 2019-09-17 | COMP | 2021-02-27 | INPR | 2020-02-20 | COMP | Rule 16 | 25 | 25 | 8 | 50 |  |  | 210
12084 | 2019-04-19 | 2019-05-23 | 2019-09-23 | 2019-09-23 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2020-02-14 | COMP | 2020-03-25 | COMP | Rule 16 | 25 | 85 | 98 | 1 | 2 | 28 | 234
12105 | 2019-04-19 | 2019-05-23 | 2019-10-07 | 2019-10-07 | COMP | 2019-12-09 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-04-07 | COMP | Rule 16 | 25 | 95 | 43 | 51 | 1 | 33 | 243
12129 | 2019-04-19 | 2019-05-23 | 2019-12-06 | 2019-12-06 | COMP | 2020-01-02 | COMP | 2020-02-06 | COMP | 2020-01-28 | COMP | 2020-03-10 | COMP | Rule 16 | 25 | 136 | 18 | 25 | 0 | 23 | 223
12350 | 2019-04-19 | 2019-06-03 | 2019-09-12 | 2019-09-12 | COMP | 2019-10-30 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-02-03 | COMP | Rule 15/16 | 31 | 72 | 35 | 23 | 1 | 41 | 198
12741 | 2019-04-19 | 2019-06-20 | 2019-10-14 | 2019-10-14 | COMP | 2020-02-03 | COMP | 2020-02-24 | COMP | 2020-02-21 | COMP | 2020-03-25 | COMP | Rule 16 | 44 | 81 | 75 | 15 | 0 | 23 | 234
12770 | 2019-04-19 | 2019-06-22 | 2019-12-06 | 2019-12-06 | COMP | 2019-12-12 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-07-24 | COMP | Rule 16 | 45 | 115 | 5 | 91 | 1 | 67 | 320
12867 | 2019-04-19 | 2019-06-26 | 2019-08-29 | 2019-08-29 | COMP | 2019-12-09 | COMP | 2019-12-14 | COMP | 2020-01-03 | COMP | 2020-02-04 | COMP | Rule 15/16 | 48 | 46 | 69 | 5 | 13 | 22 | 199
13154 | 2019-04-19 | 2019-07-12 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-08-20 | COMP | 2020-09-28 | COMP | Rule 16 | 59 | 72 | 15 | 1 | 196 | 27 | 365
13426 | 2019-04-19 | 2019-07-25 | 2019-10-03 | 2019-12-10 | COMP | 2020-01-16 | COMP | 2020-07-07 | COMP | 2020-07-03 | COMP | 2020-08-29 | COMP | Rule 15/16 | 68 | 50 | 26 | 121 | 0 | 39 | 345
13427 | 2019-04-19 | 2019-07-25 | 2019-10-03 | 2019-10-03 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-10-12 | COMP | 2020-10-29 | COMP | Rule 16 | 68 | 50 | 61 | 1 | 199 | 14 | 388
13494 | 2019-04-19 | 2019-07-28 | 2019-12-06 | 2020-03-08 | COMP | 2020-05-12 | COMP | 2020-06-08 | COMP | 2020-06-05 | COMP | 2020-07-26 | COMP | Rule 16 | 69 | 91 | 47 | 19 | 0 | 35 | 320
13709 | 2019-04-19 | 2019-08-06 | 2019-12-18 | 2020-05-27 | COMP | 2020-07-23 | COMP | 2020-08-27 | COMP | 2020-09-14 | COMP | 2020-10-20 | COMP | Rule 15/16 | 76 | 93 | 42 | 26 | 12 | 27 | 381
13763 | 2019-04-19 | 2019-08-08 | 2019-09-25 | 2019-09-25 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2022-01-30 | INPR | 2020-06-22 | COMP | Rule 16 | 78 | 34 | 44 | 1 |  |  | 296
13983 | 2019-04-19 | 2019-08-20 | 2019-10-10 | 2019-10-10 | COMP | 2019-11-05 | COMP | 2019-11-06 | COMP | 2019-11-13 | COMP | 2020-01-06 | COMP | Rule 16 | 86 | 37 | 19 | 2 | 5 | 35 | 179
14379 | 2019-04-19 | 2019-09-09 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-11-25 | COMP | 2019-11-26 | COMP | Rule 16 | 99 | 13 | 19 | 1 | 25 | 2 | 154
14400 | 2019-04-19 | 2019-09-09 | 2020-02-25 | 2020-03-05 | COMP | 2020-05-20 | COMP | 2020-08-27 | COMP | 2020-11-19 | COMP | 2021-04-09 | COMP | Rule 15/16 | 99 | 115 | 55 | 71 | 59 | 96 | 497
14683 | 2019-04-19 | 2019-09-23 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-31 | COMP | 2020-02-14 | COMP | Rule 16 | 109 | 18 | 19 | 1 | 33 | 32 | 207
15641 | 2019-04-19 | 2019-11-13 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-10 | COMP | 2021-02-02 | COMP | 2023-12-03 | INPR | 2021-05-25 | COMP | Rule 16 | 145 | 67 | 13 | 228 |  |  | 529
16562 | 2019-04-19 | 2020-01-08 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-01 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-07-16 | COMP | Rule 16 | 181 | 54 | 6 | 10 | 1 | 67 | 314
19386 | 2019-04-19 | 2020-05-04 | 2020-07-05 | 2020-07-05 | COMP | 2020-07-14 | COMP | 2021-02-27 | COMP | 2021-06-22 | COMP | 2021-07-26 | COMP | Rule 16 | 262 | 44 | 7 | 156 | 81 | 24 | 571
12358 | 2019-04-20 | 2019-06-03 | 2019-07-31 | 2019-07-31 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2019-08-09 | COMP | 2019-08-10 | COMP | Rule 16 | 30 | 42 | 4 | 1 | 5 | 1 | 78
11928 | 2019-04-21 | 2019-05-17 | 2019-08-13 | 2019-08-13 | COMP | 2020-02-26 | COMP | 2020-02-27 | COMP | 2023-11-12 | INPR | 2020-08-05 | COMP | Rule 16 | 20 | 61 | 134 | 2 |  |  | 327
12316 | 2019-04-21 | 2019-05-30 | 2019-07-19 | 2019-07-19 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-06 | COMP | 2019-10-01 | COMP | Rule 16 | 28 | 36 | 14 | 1 | 22 | 18 | 114
13852 | 2019-04-21 | 2019-08-13 | 2019-09-23 | 2019-09-23 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2020-03-01 | INPR | 2019-10-15 | COMP | Rule 16 | 80 | 29 | 5 | 1 |  |  | 124
14037 | 2019-04-21 | 2019-08-22 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-06 | COMP | 2019-12-12 | COMP | 2019-11-19 | COMP | 2020-01-25 | COMP | Rule 16 | 87 | 49 | 6 | 24 | 0 | 29 | 191
11401 | 2019-04-22 | 2019-04-25 | 2019-05-06 | 2019-05-06 | COMP | 2019-07-30 | COMP | 2019-07-30 | INPR | 2023-04-30 | CANC | 2019-09-18 | COMP | Rule 16 | 4 | 8 | 60 |  |  |  | 105
11531 | 2019-04-22 | 2019-04-30 | 2019-06-21 | 2019-07-09 | COMP | 2019-07-15 | COMP | 2019-07-15 | COMP | 2019-12-17 | COMP | 2019-12-18 | COMP | Rule 16 | 7 | 38 | 5 | 1 | 108 | 2 | 167
11667 | 2019-04-22 | 2019-05-07 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-11-05 | COMP | 2019-11-07 | COMP | Rule 16 | 12 | 86 | 17 | 1 | 27 | 3 | 141
11755 | 2019-04-22 | 2019-05-09 | 2019-07-31 | 2019-07-31 | COMP | 2019-05-09 | NOTN | 2019-07-31 | COMP | 2019-08-02 | COMP | 2019-09-16 | COMP | Other | 14 | 58 |  | 1 | 3 | 31 | 103
12023 | 2019-04-22 | 2019-05-21 | 2019-06-28 | 2019-06-28 | COMP | 2019-07-30 | COMP | 2019-10-10 | COMP | 2019-10-02 | COMP | 2019-11-12 | COMP | Rule 16 | 22 | 28 | 22 | 52 | 0 | 23 | 143
12400 | 2019-04-22 | 2019-06-04 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-14 | COMP | 2019-11-13 | COMP | 2019-11-14 | COMP | 2019-12-06 | COMP | Rule 16 | 31 | 31 | 21 | 64 | 2 | 15 | 159
12663 | 2019-04-22 | 2019-06-18 | 2019-06-20 | 2019-06-20 | COMP | 2019-08-14 | NOTN | 2019-08-14 | COMP | 2020-01-19 | INPR | 2019-09-24 | COMP | Other | 41 | 3 |  | 39 |  |  | 109
12677 | 2019-04-22 | 2019-06-18 | 2019-09-01 | 2019-09-01 | COMP | 2020-09-10 | COMP | 2021-06-09 | COMP | 2021-06-15 | COMP | 2021-07-16 | COMP | Rule 16 | 41 | 53 | 259 | 187 | 5 | 23 | 564
12694 | 2019-04-22 | 2019-06-19 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-09-12 | COMP | 2019-09-13 | COMP | Rule 16 | 42 | 16 | 10 | 1 | 36 | 2 | 102
12698 | 2019-04-22 | 2019-06-18 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-19 | COMP | 2019-09-23 | COMP | 2019-10-01 | COMP | 2019-10-02 | COMP | Rule 16 | 41 | 53 | 14 | 3 | 7 | 2 | 115
12746 | 2019-04-22 | 2019-06-21 | 2019-10-25 | 2019-10-25 | COMP | 2020-01-27 | COMP | 2020-06-08 | COMP | 2020-04-01 | COMP | 2020-06-22 | COMP | Rule 16 | 44 | 89 | 61 | 94 | 0 | 11 | 295
12841 | 2019-04-22 | 2019-06-24 | 2019-10-11 | 2019-10-11 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-05-28 | COMP | 2020-07-01 | COMP | Rule 16 | 45 | 78 | 23 | 1 | 135 | 25 | 302
12878 | 2019-04-22 | 2019-06-26 | 2019-07-27 | 2019-07-30 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-03 | COMP | 2019-09-11 | COMP | Rule 16 | 47 | 22 | 7 | 1 | 19 | 7 | 100
13109 | 2019-04-22 | 2019-07-10 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-03-27 | COMP | 2020-07-28 | COMP | Rule 16 | 56 | 96 | 25 | 1 | 61 | 87 | 321
13428 | 2019-04-22 | 2019-07-25 | 2019-10-04 | 2019-12-04 | COMP | 2020-01-23 | COMP | 2020-04-06 | COMP | 2020-07-03 | COMP | 2020-08-29 | COMP | Rule 16 | 67 | 51 | 34 | 52 | 64 | 41 | 344
13429 | 2019-04-22 | 2019-07-25 | 2019-09-18 | 2019-09-18 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-09-17 | COMP | 2020-10-29 | COMP | Rule 16 | 67 | 39 | 71 | 1 | 183 | 31 | 387
13505 | 2019-04-22 | 2019-07-29 | 2019-10-18 | 2019-10-18 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-12-18 | COMP | 2021-01-15 | COMP | Rule 16 | 69 | 59 | 27 | 1 | 268 | 19 | 438
13744 | 2019-04-22 | 2019-08-07 | 2019-12-06 | 2019-12-06 | COMP | 2019-12-23 | COMP | 2020-01-09 | COMP | 2020-01-19 | COMP | 2020-02-16 | COMP | Rule 16 | 76 | 84 | 12 | 12 | 7 | 19 | 206
13847 | 2019-04-22 | 2019-08-13 | 2019-08-29 | 2019-08-29 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | Rule 16 | 80 | 13 | 20 | 1 | 68 | 1 | 178
13956 | 2019-04-22 | 2019-08-19 | 2019-10-05 | 2019-11-21 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2019-12-18 | COMP | 2020-01-03 | COMP | Rule 16 | 84 | 34 | 17 | 1 | 2 | 11 | 177
14281 | 2019-04-22 | 2019-09-03 | 2019-10-20 | 2019-10-20 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-11-10 | COMP | 2021-01-12 | COMP | Rule 16 | 94 | 34 | 42 | 1 | 227 | 41 | 435
15317 | 2019-04-22 | 2019-10-26 | 2020-09-08 | 2020-09-08 | COMP | 2020-09-17 | COMP | 2021-07-27 | INPR | 2022-12-03 | REQD | 2021-08-06 | COMP | Rule 16 | 132 | 218 | 8 |  |  |  | 579
15364 | 2019-04-22 | 2019-10-28 | 2019-12-16 | 2019-12-16 | COMP | 2021-06-23 | COMP | 2022-05-23 | COMP | 2022-07-27 | COMP | 2022-08-23 | COMP | Rule 15/16 | 133 | 33 | 384 | 232 | 45 | 20 | 842
15669 | 2019-04-22 | 2019-11-14 | 2020-01-04 | 2020-01-04 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-01-22 | COMP | 2020-02-21 | COMP | Rule 16 | 145 | 33 | 11 | 1 | 2 | 22 | 210
15727 | 2019-04-22 | 2019-11-19 | 2020-06-10 | 2020-06-10 | COMP | 2020-07-03 | COMP | 2020-08-17 | COMP | 2022-07-16 | INPR | 2020-12-23 | COMP | Rule 16 | 148 | 140 | 18 | 32 |  |  | 423
15738 | 2019-04-22 | 2019-11-20 | 2020-07-22 | 2020-07-22 | COMP | 2021-02-24 | COMP | 2021-02-24 | COMP | 2021-09-22 | COMP | 2021-11-30 | COMP | Rule 15/16 | 149 | 169 | 148 | 1 | 148 | 47 | 657
16136 | 2019-04-22 | 2019-12-11 | 2019-12-12 | 2019-12-16 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-02-05 | COMP | 2020-02-26 | COMP | Rule 16 | 162 | 2 | 4 | 1 | 32 | 15 | 213
16326 | 2019-04-22 | 2019-12-20 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-10 | COMP | 2020-06-11 | COMP | 2022-07-30 | INPR | 2020-11-05 | COMP | Rule 16 | 169 | 26 | 29 | 67 |  |  | 392
16835 | 2019-04-22 | 2020-01-18 | 2020-05-19 | 2020-05-19 | COMP | 2021-03-25 | COMP | 2021-03-25 | COMP | 2021-07-23 | COMP | 2021-09-20 | COMP | Rule 16 | 187 | 85 | 214 | 1 | 85 | 41 | 609
18330 | 2019-04-22 | 2020-03-21 | 2020-05-05 | 2020-05-05 | COMP | 2020-11-10 | COMP | 2021-01-25 | COMP | 2020-12-14 | COMP | 2021-07-27 | COMP | Rule 16 | 230 | 32 | 134 | 49 | 0 | 129 | 571
19735 | 2019-04-22 | 2020-05-20 | 2020-08-16 | 2020-08-16 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2021-02-17 | COMP | 2021-04-01 | COMP | Rule 16 | 273 | 62 | 47 | 1 | 79 | 32 | 490
11553 | 2019-04-23 | 2019-05-02 | 2019-05-13 | 2019-05-13 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-06-27 | COMP | 2019-07-24 | COMP | Rule 16 | 8 | 8 | 33 | 1 | 1 | 19 | 65
11584 | 2019-04-23 | 2019-05-03 | 2019-07-06 | 2019-07-06 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-13 | COMP | 2019-08-28 | COMP | Rule 16 | 9 | 44 | 27 | 1 | 1 | 12 | 90
11807 | 2019-04-23 | 2019-05-13 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-06 | NOTN | 2019-10-28 | COMP | 2019-09-10 | COMP | 2020-01-08 | COMP | Other | 15 | 82 |  | 37 | 0 | 48 | 179
11932 | 2019-04-23 | 2019-05-16 | 2019-12-02 | 2019-12-14 | COMP | 2019-12-31 | COMP | 2020-08-05 | COMP | 2020-07-28 | COMP | 2020-09-03 | COMP | Rule 16 | 18 | 137 | 11 | 153 | 0 | 22 | 347
12002 | 2019-04-23 | 2019-05-20 | 2019-08-02 | 2020-01-26 | COMP | 2020-02-25 | COMP | 2019-08-09 | COMP | 2020-06-01 | COMP | 2020-07-13 | COMP | Rule 15/16 | 20 | 53 | 21 |  | 203 | 31 | 309
12070 | 2019-04-23 | 2019-05-22 | 2019-06-08 | 2019-06-08 | COMP | 2019-06-26 | COMP | 2019-07-22 | COMP | 2019-12-02 | COMP | 2019-12-16 | COMP | Rule 16 | 22 | 12 | 13 | 18 | 92 | 11 | 164
12336 | 2019-04-23 | 2019-05-31 | 2019-08-08 | 2019-08-08 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | 2020-02-15 | COMP | Rule 16 | 28 | 49 | 54 | 1 | 19 | 59 | 205
12441 | 2019-04-23 | 2019-06-06 | 2019-08-15 | 2019-08-15 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-11-20 | COMP | 2020-01-02 | COMP | Rule 16 | 32 | 50 | 11 | 1 | 58 | 28 | 175
12934 | 2019-04-23 | 2019-07-01 | 2020-03-18 | 2020-05-13 | COMP | 2020-06-03 | COMP | 2020-10-21 | COMP | 2020-09-29 | COMP | 2020-11-12 | COMP | Rule 16 | 49 | 179 | 15 | 100 | 0 | 16 | 395
13206 | 2019-04-23 | 2019-07-16 | 2019-09-17 | 2019-10-07 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2020-05-01 | COMP | 2020-05-06 | COMP | Rule 16 | 59 | 45 | 8 | 1 | 136 | 4 | 262
13379 | 2019-04-23 | 2019-07-23 | 2019-09-20 | 2019-09-20 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-09-26 | COMP | 2020-01-08 | COMP | Rule 15/16 | 64 | 43 | 23 | 1 | 0 | 52 | 179
13472 | 2019-04-23 | 2019-07-26 | 2020-02-21 | 2020-02-21 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-07-10 | COMP | 2020-07-18 | COMP | Rule 15/16 | 67 | 143 | 99 | 1 | 2 | 6 | 313
13542 | 2019-04-23 | 2019-07-30 | 2019-11-07 | 2019-11-07 | COMP | 2020-04-26 | INPR | 2019-12-04 | COMP | 2019-12-05 | COMP | 2020-01-06 | COMP | Rule 15/16 | 69 | 72 |  | 17 | 2 | 21 | 177
13812 | 2019-04-23 | 2019-08-12 | 2019-12-20 | 2020-02-18 | COMP | 2020-02-24 | COMP | 2020-10-15 | COMP | 2020-10-16 | COMP | 2020-11-10 | COMP | Rule 16 | 78 | 91 | 5 | 167 | 2 | 18 | 394
14789 | 2019-04-23 | 2019-09-27 | 2020-03-31 | 2020-03-31 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-13 | COMP | 2020-07-08 | COMP | Rule 16 | 111 | 126 | 25 | 1 | 8 | 40 | 306
14815 | 2019-04-23 | 2019-09-30 | 2020-02-09 | 2020-02-09 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-04-17 | COMP | Rule 16 | 112 | 89 | 19 | 1 | 1 | 31 | 249
16204 | 2019-04-23 | 2019-12-14 | 2020-01-16 | 2020-02-05 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-06-11 | COMP | 2020-06-20 | COMP | Rule 16 | 163 | 22 | 16 | 1 | 75 | 7 | 293
16606 | 2019-04-23 | 2020-01-09 | 2020-01-28 | 2020-03-06 | COMP | 2020-03-17 | COMP | 2020-04-15 | COMP | 2023-10-21 | INPR | 2021-06-01 | COMP | Rule 16 | 180 | 13 | 8 | 22 |  |  | 531
16759 | 2019-04-23 | 2020-01-15 | 2020-04-09 | 2020-04-09 | COMP | 2020-07-30 | COMP | 2020-09-14 | COMP | 2021-03-17 | COMP | 2021-04-02 | COMP | Rule 15/16 | 184 | 60 | 80 | 32 | 126 | 13 | 490
11479 | 2019-04-24 | 2019-04-29 | 2019-05-24 | 2019-05-24 | COMP | 2019-06-05 | COMP | 2019-06-20 | COMP | 2019-07-22 | COMP | 2019-07-29 | COMP | Rule 16 | 4 | 20 | 8 | 12 | 22 | 6 | 67
11630 | 2019-04-24 | 2019-05-06 | 2019-05-17 | 2019-05-17 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2019-12-29 | INPR | 2019-08-05 | COMP | Rule 16 | 9 | 10 | 11 | 1 |  |  | 72
11634 | 2019-04-24 | 2019-05-07 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-19 | COMP | 2019-08-01 | COMP | 2019-08-15 | COMP | 2019-08-31 | COMP | Rule 16 | 10 | 46 | 7 | 10 | 11 | 12 | 91
11639 | 2019-04-24 | 2019-05-06 | 2019-10-28 | 2019-10-28 | COMP | 2020-05-14 | COMP | 2020-06-16 | COMP | 2020-08-28 | COMP | 2020-09-10 | COMP | Rule 15/16 | 9 | 123 | 137 | 23 | 54 | 9 | 350
11867 | 2019-04-24 | 2019-05-15 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-26 | COMP | 2019-09-13 | COMP | 2019-11-16 | COMP | 2020-01-08 | COMP | Rule 16 | 16 | 49 | 24 | 14 | 45 | 34 | 178
12017 | 2019-04-24 | 2019-05-21 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-10 | COMP | 2019-07-11 | COMP | 2019-07-30 | COMP | 2019-09-23 | COMP | Rule 16 | 20 | 27 | 9 | 2 | 14 | 39 | 106
12154 | 2019-04-24 | 2019-05-24 | 2019-07-23 | 2019-07-23 | COMP | 2019-08-01 | COMP | 2019-10-28 | COMP | 2019-10-27 | COMP | 2019-12-10 | COMP | Rule 16 | 23 | 41 | 8 | 62 | 0 | 29 | 159
12247 | 2019-04-24 | 2019-05-29 | 2020-04-10 | 2020-04-10 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2021-05-28 | COMP | 2021-10-07 | COMP | Rule 15/16 | 25 | 219 | 137 | 1 | 151 | 92 | 620
12282 | 2019-04-24 | 2019-05-30 | 2019-07-22 | 2019-07-22 | COMP | 2019-09-25 | COMP | 2019-08-09 | COMP | 2019-10-07 | COMP | 2020-01-29 | COMP | Rule 16 | 26 | 37 | 47 |  | 41 | 77 | 192
12399 | 2019-04-24 | 2019-06-04 | 2020-06-06 | 2020-06-06 | COMP | 2020-10-20 | COMP | 2021-02-16 | COMP | 2021-03-30 | COMP | 2021-04-07 | COMP | Rule 15/16 | 29 | 254 | 96 | 79 | 31 | 7 | 492
12429 | 2019-04-24 | 2019-06-05 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-06 | COMP | 2020-06-16 | COMP | 2020-05-26 | COMP | 2020-07-10 | COMP | Rule 15/16 | 30 | 154 | 16 | 92 | 0 | 19 | 307
12485 | 2019-04-24 | 2019-06-10 | 2019-07-31 | 2019-07-31 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-09-11 | COMP | 2019-10-03 | COMP | Rule 16 | 33 | 37 | 24 | 1 | 7 | 17 | 114
12586 | 2019-04-24 | 2019-06-14 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-04 | COMP | 2019-09-04 | COMP | 2019-10-15 | COMP | 2019-10-18 | COMP | Rule 16 | 37 | 50 | 8 | 1 | 30 | 4 | 125
12632 | 2019-04-24 | 2019-06-17 | 2019-11-17 | 2019-11-17 | COMP | 2019-11-20 | COMP | 2020-01-06 | COMP | 2020-03-09 | COMP | 2020-03-13 | COMP | Rule 16 | 38 | 107 | 3 | 30 | 44 | 5 | 223
12709 | 2019-04-24 | 2019-06-19 | 2019-11-25 | 2021-10-28 | COMP | 2022-02-16 | COMP | 2023-06-04 | COMP | 2023-08-08 | COMP | 2023-09-07 | COMP | Rule 16 | 40 | 111 | 76 | 325 | 45 | 22 | 1100
12807 | 2019-04-24 | 2019-06-24 | 2019-08-07 | 2019-08-07 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-10-08 | COMP | Rule 16 | 43 | 32 | 33 | 1 | 1 | 12 | 117
13039 | 2019-04-24 | 2019-07-08 | 2019-10-07 | 2020-04-26 | COMP | 2020-09-23 | COMP | 2019-12-30 | COMP | 2020-09-23 | COMP | 2020-11-10 | COMP | Rule 16 | 52 | 65 | 106 |  | 188 | 35 | 393
13335 | 2019-04-24 | 2019-07-23 | 2019-10-02 | 2019-10-02 | COMP | 2019-11-18 | COMP | 2020-02-24 | COMP | 2020-03-03 | COMP | 2020-03-04 | COMP | Rule 16 | 63 | 51 | 33 | 65 | 7 | 2 | 216
13659 | 2019-04-24 | 2019-08-05 | 2019-11-16 | 2019-11-16 | COMP | 2020-01-08 | COMP | 2020-01-08 | COMP | 2020-05-07 | COMP | 2020-06-08 | COMP | Rule 16 | 72 | 73 | 34 | 1 | 85 | 22 | 283
14012 | 2019-04-24 | 2019-08-21 | 2020-02-26 | 2020-02-26 | COMP | 2020-09-03 | COMP | 2020-09-03 | COMP | 2022-07-16 | INPR | 2020-10-04 | COMP | Rule 16 | 84 | 128 | 136 | 1 |  |  | 366
14188 | 2019-04-24 | 2019-08-28 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-26 | COMP | 2020-03-27 | COMP | 2020-08-25 | COMP | 2020-09-07 | COMP | Rule 16 | 89 | 125 | 20 | 2 | 107 | 9 | 347
14242 | 2019-04-24 | 2019-08-30 | 2019-12-24 | 2019-12-24 | COMP | 2020-01-24 | COMP | 2020-03-07 | COMP | 2020-05-21 | COMP | 2020-05-16 | COMP | Rule 16 | 91 | 79 | 21 | 30 | 54 |  | 268
14340 | 2019-04-24 | 2019-09-05 | 2019-12-23 | 2019-12-23 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-10-06 | COMP | 2020-12-03 | COMP | Rule 16 | 94 | 75 | 20 | 1 | 182 | 40 | 407
14824 | 2019-04-24 | 2019-10-01 | 2019-11-29 | 2019-11-29 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-04-01 | COMP | 2020-04-04 | COMP | Rule 16 | 112 | 41 | 20 | 1 | 65 | 3 | 238
14832 | 2019-04-24 | 2019-09-30 | 2020-01-25 | 2020-01-25 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-07-21 | COMP | 2020-10-01 | COMP | Rule 16 | 111 | 79 | 8 | 1 | 118 | 52 | 365
15045 | 2019-04-24 | 2019-10-10 | 2019-11-19 | 2019-11-19 | COMP | 2020-06-29 | COMP | 2020-09-14 | COMP | 2020-07-07 | COMP | 2021-04-13 | COMP | Rule 16 | 119 | 28 | 153 | 55 | 0 | 145 | 496
15453 | 2019-04-24 | 2019-11-02 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-02-18 | COMP | 2020-03-23 | COMP | Rule 16 | 135 | 28 | 22 | 1 | 22 | 25 | 229
16327 | 2019-04-24 | 2019-12-20 | 2020-02-07 | 2020-05-27 | COMP | 2020-08-18 | COMP | 2020-10-28 | COMP | 2020-11-12 | COMP | 2020-11-23 | COMP | Rule 16 | 167 | 33 | 60 | 51 | 11 | 8 | 401
16345 | 2019-04-24 | 2019-12-23 | 2020-04-21 | 2020-05-11 | COMP | 2020-06-12 | COMP | 2020-07-01 | COMP | 2023-06-26 | COMP | 2023-12-15 | COMP | Rule 15/16 | 168 | 83 | 24 | 14 | 750 | 120 | 1168
18308 | 2019-04-24 | 2020-03-20 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-19 | COMP | 2020-06-24 | COMP | 2020-07-21 | COMP | 2020-09-16 | COMP | Rule 16 | 228 | 30 | 14 | 26 | 20 | 41 | 354
18669 | 2019-04-24 | 2020-04-03 | 2020-09-21 | 2021-10-20 | COMP | 2021-10-28 | COMP | 2021-11-08 | COMP | 2022-10-18 | COMP | 2022-10-28 | COMP | Rule 16 | 238 | 120 | 7 | 8 | 238 | 9 | 887
4162 | 2019-04-25 | 2019-04-25 | 2019-04-29 | 2019-04-29 | COMP | 2019-04-29 | NOTN | 2019-04-29 | COMP | 2019-04-29 | COMP | 2019-05-05 | COMP | Other | 1 | 3 |  | 1 | 1 | 5 | 7
4276 | 2019-04-25 | 2020-02-28 | 2020-06-01 | 2020-06-01 | COMP | 2020-08-06 | NOTN | 2020-08-07 | COMP | 2020-08-07 | NOTN | 2020-11-09 | COMP | Other | 212 | 66 |  | 50 |  |  | 391
11343 | 2019-04-25 | 2019-04-25 | 2019-08-21 | 2019-08-21 | COMP | 2019-09-18 | COMP | 2019-11-14 | COMP | 2019-11-14 | COMP | 2020-02-06 | COMP | Rule 16 | 1 | 83 | 20 | 41 | 1 | 56 | 197
11549 | 2019-04-25 | 2019-05-01 | 2019-07-09 | 2019-09-04 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-03-25 | COMP | 2020-07-21 | COMP | Rule 15/16 | 5 | 48 | 74 | 1 | 66 | 84 | 313
11725 | 2019-04-25 | 2019-05-08 | 2019-07-30 | 2019-07-30 | COMP | 2019-10-28 | NOTN | 2019-10-28 | COMP | 2019-10-28 | COMP | 2019-12-03 | COMP | Other | 10 | 58 |  | 64 | 1 | 24 | 153
11775 | 2019-04-25 | 2019-05-10 | 2019-06-07 | 2019-06-07 | COMP | 2019-07-17 | COMP | 2019-07-18 | COMP | 2019-12-29 | INPR | 2019-07-31 | COMP | Rule 16 | 12 | 20 | 28 | 2 |  |  | 68
11776 | 2019-04-25 | 2019-05-10 | 2019-06-10 | 2019-06-10 | COMP | 2019-07-31 | COMP | 2019-08-01 | COMP | 2019-12-29 | INPR | 2019-08-13 | COMP | Rule 16 | 12 | 21 | 37 | 2 |  |  | 77
11782 | 2019-04-25 | 2019-05-10 | 2019-08-02 | 2019-08-02 | COMP | 2019-05-10 | NOTN | 2019-09-05 | COMP | 2019-08-29 | COMP | 2019-11-18 | COMP | Other | 12 | 59 |  | 24 | 0 | 52 | 144
12030 | 2019-04-25 | 2019-05-21 | 2019-09-14 | 2019-09-14 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-11-06 | COMP | 2019-12-28 | COMP | Rule 16 | 19 | 81 | 25 | 1 | 14 | 34 | 170
12085 | 2019-04-25 | 2019-05-23 | 2019-07-05 | 2019-07-09 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP |  |  | 2019-09-23 | COMP | Rule 16 | 21 | 30 | 30 | 1 |  |  | 105
12088 | 2019-04-25 | 2019-05-23 | 2019-07-05 | 2019-07-09 | COMP | 2019-08-19 | COMP | 2019-12-09 | COMP |  |  | 2019-12-13 | COMP | Rule 16 | 21 | 30 | 30 | 77 |  |  | 161
12089 | 2019-04-25 | 2019-05-23 | 2019-07-09 | 2019-07-09 | COMP | 2019-08-29 | COMP | 2019-09-16 | COMP |  |  | 2019-12-15 | COMP | Rule 15/16 | 21 | 32 | 38 | 12 |  |  | 161
12261 | 2019-04-25 | 2019-05-29 | 2019-07-15 | 2019-07-15 | COMP | 2021-07-13 | COMP | 2021-08-30 | COMP | 2021-08-27 | COMP | 2021-10-01 | COMP | Rule 16 | 24 | 33 | 503 | 35 | 0 | 24 | 615
12529 | 2019-04-25 | 2019-06-11 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-10 | COMP | 2019-09-20 | COMP | 2020-05-31 | INPR | 2019-10-03 | COMP | Rule 16 | 33 | 61 | 4 | 9 |  |  | 113
12546 | 2019-04-25 | 2019-06-12 | 2019-09-15 | 2019-09-15 | COMP | 2019-09-15 | NOTN | 2019-09-15 | COMP | 2019-09-16 | COMP | 2019-11-13 | COMP | Other | 34 | 66 |  | 0 | 1 | 42 | 141
12557 | 2019-04-25 | 2019-06-13 | 2019-10-23 | 2019-10-23 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-04-22 | COMP | 2020-06-17 | COMP | Rule 16 | 35 | 93 | 123 | 1 | 2 | 40 | 289
12765 | 2019-04-25 | 2019-06-21 | 2019-10-23 | 2019-10-23 | COMP | 2019-10-29 | COMP | 2019-11-06 | COMP | 2019-11-19 | COMP | 2019-12-18 | COMP | Rule 15/16 | 41 | 87 | 5 | 7 | 9 | 20 | 164
12831 | 2019-04-25 | 2019-06-25 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-18 | COMP | 2019-12-20 | COMP | 2020-04-07 | COMP | 2020-04-16 | COMP | Rule 16 | 43 | 84 | 19 | 23 | 74 | 8 | 246
12901 | 2019-04-25 | 2019-06-28 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-09-18 | COMP | 2019-10-03 | COMP | Rule 16 | 46 | 29 | 18 | 1 | 12 | 12 | 113
12923 | 2019-04-25 | 2019-06-29 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-23 | COMP | 2019-11-13 | COMP | 2019-11-19 | COMP | 2019-12-20 | COMP | Rule 16 | 46 | 67 | 15 | 15 | 5 | 22 | 166
13449 | 2019-04-25 | 2019-07-26 | 2019-09-01 | 2019-09-01 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-12-02 | COMP | 2019-12-17 | COMP | Rule 16 | 65 | 26 | 56 | 1 | 7 | 12 | 163
13753 | 2019-04-25 | 2019-08-08 | 2019-10-11 | 2019-10-14 | COMP | 2020-01-14 | COMP | 2020-01-14 | COMP | 2020-01-21 | COMP | 2020-02-21 | COMP | Rule 16 | 74 | 46 | 62 | 1 | 5 | 23 | 207
13899 | 2019-04-25 | 2019-08-15 | 2019-12-12 | 2019-12-12 | COMP | 2020-01-14 | COMP | 2020-01-22 | COMP | 2020-02-07 | COMP | 2020-03-04 | COMP | Rule 16 | 79 | 82 | 22 | 6 | 13 | 18 | 215
13986 | 2019-04-25 | 2019-08-20 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-07 | COMP | 2020-03-12 | COMP | 2020-05-20 | COMP | 2020-06-08 | COMP | Rule 16 | 82 | 81 | 15 | 46 | 50 | 13 | 282
15344 | 2019-04-25 | 2019-10-29 | 2019-12-13 | 2019-12-13 | COMP | 2021-02-16 | COMP | 2022-05-25 | COMP | 2022-07-29 | COMP | 2023-02-20 | COMP | Rule 16 | 131 | 31 | 295 | 324 | 45 | 139 | 960
16094 | 2019-04-25 | 2019-12-11 | 2021-02-26 | 2021-02-26 | COMP | 2021-03-30 | COMP | 2021-06-10 | COMP | 2022-07-18 | COMP | 2022-09-01 | COMP | Rule 15/16 | 159 | 305 | 23 | 52 | 278 | 34 | 846
16343 | 2019-04-25 | 2019-12-23 | 2020-03-22 | 2020-04-14 | COMP | 2020-05-13 | COMP | 2020-11-17 | COMP | 2021-03-08 | COMP | 2021-04-02 | COMP | Rule 16 | 167 | 61 | 22 | 132 | 74 | 20 | 488
16779 | 2019-04-25 | 2020-01-15 | 2020-03-14 | 2020-09-17 | COMP | 2020-11-04 | COMP | 2021-05-05 | COMP | 2021-03-16 | COMP | 2021-07-26 | COMP | Rule 16 | 182 | 41 | 35 | 124 | 0 | 57 | 567
16813 | 2019-04-25 | 2020-01-16 | 2020-06-09 | 2020-06-09 | COMP | 2020-07-17 | COMP | 2020-10-05 | COMP | 2020-12-16 | COMP | 2021-02-19 | COMP | Rule 16 | 183 | 101 | 29 | 56 | 50 | 44 | 458
17467 | 2019-04-25 | 2020-02-14 | 2020-12-15 | 2020-12-15 | COMP | 2021-02-25 | COMP | 2021-02-25 | COMP | 2022-06-18 | INPR | 2021-06-04 | COMP | Rule 16 | 203 | 212 | 49 | 1 |  |  | 532
17487 | 2019-04-25 | 2020-02-18 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-26 | COMP | 2020-06-04 | COMP | 2023-04-30 | INPR | 2020-06-22 | COMP | Rule 16 | 204 | 60 | 11 | 8 |  |  | 292
4171 | 2019-04-26 | 2019-05-22 | 2019-07-15 | 2019-07-15 | COMP | 2019-09-23 | COMP | 2019-10-02 | COMP | 2020-05-15 | COMP | 2020-07-19 | COMP | Rule 16 | 19 | 37 | 50 | 8 | 156 | 45 | 310
11457 | 2019-04-26 | 2019-04-29 | 2019-06-18 | 2019-06-18 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2020-04-15 | COMP | 2020-05-13 | COMP | Rule 16 | 2 | 36 | 99 | 1 | 110 | 21 | 264
11647 | 2019-04-26 | 2019-05-06 | 2019-07-17 | 2019-07-17 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-04-22 | COMP | 2020-04-29 | COMP | Rule 16 | 7 | 51 | 192 | 1 | 2 | 6 | 254
11830 | 2019-04-26 | 2019-05-14 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2019-10-16 | COMP | 2019-11-06 | COMP | Rule 16 | 13 | 39 | 9 | 1 | 63 | 16 | 136
11847 | 2019-04-26 | 2019-05-14 | 2019-08-14 | 2019-08-14 | COMP | 2019-09-09 | COMP | 2020-03-07 | COMP | 2020-06-02 | COMP | 2020-06-15 | COMP | Rule 16 | 13 | 65 | 18 | 123 | 61 | 10 | 286
12073 | 2019-04-26 | 2019-05-22 | 2019-07-23 | 2019-07-23 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-11-27 | COMP | 2019-12-27 | COMP | Rule 16 | 19 | 43 | 75 | 1 | 16 | 20 | 169
12318 | 2019-04-26 | 2019-05-30 | 2019-10-02 | 2019-10-02 | COMP | 2021-10-18 | COMP | 2021-10-18 | COMP | 2021-10-18 | COMP | 2022-03-16 | COMP | Rule 16 | 24 | 88 | 515 | 1 | 1 | 103 | 727
12332 | 2019-04-26 | 2019-05-31 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2020-04-13 | COMP | 2020-04-14 | COMP | Rule 16 | 25 | 20 | 3 | 1 | 197 | 2 | 243
12361 | 2019-04-26 | 2019-06-03 | 2019-08-16 | 2019-08-26 | COMP | 2019-09-30 | COMP | 2019-10-04 | COMP | 2019-09-30 | COMP | 2019-11-22 | COMP | Rule 16 | 26 | 54 | 25 | 5 | 0 | 35 | 147
12461 | 2019-04-26 | 2019-06-07 | 2019-07-03 | 2019-07-03 | COMP | 2019-07-11 | COMP | 2019-07-11 | INPR | 2019-09-24 | COMP | 2019-09-26 | COMP | Rule 16 | 30 | 19 | 6 |  |  |  | 107
12479 | 2019-04-26 | 2019-06-11 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-16 | COMP | 2019-08-06 | COMP | 2019-08-28 | COMP | 2019-09-24 | COMP | Rule 16 | 32 | 20 | 6 | 16 | 17 | 19 | 105
12523 | 2019-04-26 | 2019-06-10 | 2020-07-29 | 2020-07-29 | COMP | 2020-11-19 | COMP | 2020-11-19 | COMP | 2021-02-01 | COMP | 2021-03-28 | COMP | Rule 16 | 31 | 288 | 80 | 1 | 48 | 39 | 482
12651 | 2019-04-26 | 2019-06-17 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-01-28 | COMP | 2020-02-20 | COMP | Rule 16 | 36 | 84 | 7 | 1 | 65 | 17 | 205
12654 | 2019-04-26 | 2019-06-17 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-08-22 | COMP | 2019-09-17 | COMP | Rule 16 | 36 | 38 | 3 | 1 | 9 | 18 | 100
13238 | 2019-04-26 | 2019-07-17 | 2019-10-11 | 2019-10-11 | COMP | 2020-08-05 | COMP | 2020-12-29 | COMP | 2021-02-19 | COMP | 2021-04-16 | COMP | Rule 15/16 | 57 | 62 | 206 | 100 | 36 | 41 | 497
13239 | 2019-04-26 | 2019-07-17 | 2019-10-11 | 2019-10-11 | COMP | 2020-01-03 | COMP | 2020-06-24 | COMP | 2020-09-16 | COMP | 2020-10-06 | COMP | Rule 15/16 | 57 | 62 | 56 | 121 | 60 | 15 | 366
13240 | 2019-04-26 | 2019-07-17 | 2019-10-11 | 2019-10-11 | COMP | 2020-01-02 | COMP | 2020-06-24 | COMP | 2020-09-16 | COMP | 2020-10-06 | COMP | Rule 15/16 | 57 | 62 | 55 | 122 | 60 | 15 | 366
13241 | 2019-04-26 | 2019-07-17 | 2019-10-11 | 2019-10-11 | COMP | 2020-08-05 | COMP | 2020-12-29 | COMP |  | INPR | 2021-04-16 | COMP | Rule 15/16 | 57 | 62 | 206 | 100 |  |  | 497
13497 | 2019-04-26 | 2019-07-29 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-12 | COMP | 2020-01-15 | COMP | 2021-02-09 | COMP | 2021-02-23 | COMP | Rule 16 | 65 | 57 | 39 | 23 | 270 | 10 | 459
13512 | 2019-04-26 | 2019-07-29 | 2019-10-02 | 2019-12-06 | COMP | 2020-01-21 | COMP | 2020-01-24 | COMP | 2021-05-24 | COMP | 2021-06-23 | COMP | Rule 16 | 65 | 47 | 30 | 4 | 337 | 22 | 544
13799 | 2019-04-26 | 2019-08-12 | 2019-11-09 | 2019-11-09 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-01-08 | COMP | Rule 16 | 75 | 64 | 12 | 1 | 1 | 27 | 176
14807 | 2019-04-26 | 2019-09-28 | 2020-03-03 | 2020-03-08 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-07-07 | COMP | 2020-09-22 | COMP | Rule 15/16 | 108 | 105 | 8 | 1 | 79 | 55 | 356
14879 | 2019-04-26 | 2019-10-02 | 2019-12-04 | 2019-12-04 | COMP | 2020-05-03 | COMP | 2020-05-03 | COMP | 2020-05-03 | COMP | 2020-05-03 | COMP | Rule 16 | 111 | 43 | 104 | 0 | 0 | 0 | 256
16042 | 2019-04-26 | 2019-12-06 | 2020-06-19 | 2020-06-19 | COMP | 2020-08-21 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2020-08-28 | COMP | Rule 16 | 155 | 136 | 46 |  | 1 | 17 | 340
18525 | 2019-04-26 | 2020-03-27 | 2020-08-22 | 2020-08-22 | COMP | 2020-12-04 | COMP | 2020-12-04 | COMP | 2021-02-23 | COMP | 2021-03-08 | COMP | Rule 16 | 231 | 105 | 71 | 1 | 54 | 10 | 468
11783 | 2019-04-27 | 2019-05-11 | 2019-09-11 | 2019-09-11 | COMP | 2019-11-05 | COMP | 2019-11-08 | COMP | 2020-04-26 | INPR | 2019-12-11 | COMP | Rule 16 | 10 | 85 | 40 | 4 |  |  | 157
12278 | 2019-04-27 | 2019-05-30 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-02 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-01-15 | COMP | Rule 16 | 23 | 81 | 48 | 2 | 1 | 30 | 180
13511 | 2019-04-27 | 2019-07-29 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2020-05-14 | COMP | 2020-05-28 | COMP | Rule 16 | 64 | 54 | 15 | 1 | 134 | 10 | 273
14179 | 2019-04-28 | 2019-08-28 | 2020-01-24 | 2020-01-24 | COMP | 2020-08-19 | COMP | 2020-09-02 | COMP | 2020-09-22 | COMP | 2020-11-05 | COMP | Rule 15/16 | 86 | 101 | 147 | 11 | 14 | 33 | 387
11534 | 2019-04-29 | 2019-05-01 | 2019-08-08 | 2019-08-08 | COMP | 2019-09-20 | COMP | 2019-12-06 | COMP | 2020-03-29 | INPR | 2019-12-05 | COMP | Rule 16 | 3 | 70 | 31 | 53 |  |  | 153
11872 | 2019-04-29 | 2019-05-15 | 2019-05-21 | 2019-05-21 | COMP | 2019-07-30 | COMP | 2019-07-30 | COMP | 2019-08-20 | COMP | 2019-09-11 | COMP | Rule 16 | 13 | 5 | 49 | 1 | 16 | 16 | 95
12013 | 2019-04-29 | 2019-05-21 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-16 | COMP | 2019-09-03 | COMP | 2019-09-16 | COMP | 2019-09-27 | COMP | Rule 16 | 17 | 35 | 5 | 35 | 10 | 10 | 107
12018 | 2019-04-29 | 2019-05-21 | 2019-09-03 | 2019-09-03 | COMP | 2020-02-12 | COMP | 2020-02-13 | COMP | 2020-02-18 | COMP | 2020-03-25 | COMP | Rule 15/16 | 17 | 73 | 111 | 2 | 3 | 27 | 228
12130 | 2019-04-29 | 2019-05-23 | 2019-07-01 | 2019-07-01 | COMP | 2019-08-01 | COMP | 2019-09-12 | COMP | 2019-08-28 | COMP | 2019-09-26 | COMP | Rule 16 | 19 | 27 | 23 | 30 | 0 | 11 | 106
12209 | 2019-04-29 | 2019-05-28 | 2019-07-17 | 2019-07-17 | COMP | 2019-07-26 | COMP | 2019-07-26 | COMP | 2019-07-25 | COMP | 2019-08-03 | COMP | Rule 16 | 21 | 36 | 8 | 1 | 0 | 6 | 68
12293 | 2019-04-29 | 2019-05-30 | 2019-10-12 | 2019-10-12 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-01 | COMP | 2020-07-21 | COMP | Rule 16 | 23 | 95 | 163 | 1 | 18 | 15 | 311
12450 | 2019-04-29 | 2019-06-06 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-12 | COMP | 2019-08-13 | COMP | 2019-09-24 | COMP | 2019-10-08 | COMP | Rule 15/16 | 28 | 44 | 4 | 2 | 30 | 11 | 114
12499 | 2019-04-29 | 2019-06-10 | 2019-07-12 | 2019-11-27 | COMP | 2020-02-25 | COMP | 2020-02-26 | COMP | 2020-03-10 | COMP | 2020-03-12 | COMP | Rule 16 | 30 | 24 | 59 | 2 | 10 | 3 | 219
12648 | 2019-04-29 | 2019-06-17 | 2019-08-16 | 2019-08-16 | COMP | 2019-08-21 | COMP | 2019-08-28 | COMP | 2020-01-19 | INPR | 2019-10-01 | COMP | Rule 16 | 35 | 44 | 4 | 6 |  |  | 109
12678 | 2019-04-29 | 2019-06-18 | 2019-09-07 | 2019-09-07 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2020-06-26 | COMP | 2020-08-03 | COMP | Rule 16 | 36 | 57 | 14 | 1 | 189 | 27 | 320
12801 | 2019-04-29 | 2019-06-24 | 2019-08-03 | 2019-08-03 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-12-18 | COMP | 2019-12-20 | COMP | Rule 16 | 40 | 29 | 12 | 1 | 83 | 3 | 164
13094 | 2019-04-29 | 2019-07-10 | 2019-08-16 | 2019-08-16 | COMP | 2019-10-08 | COMP | 2020-02-26 | COMP | 2020-02-18 | COMP | 2020-05-13 | COMP | Rule 16 | 51 | 28 | 37 | 95 | 0 | 56 | 263
13168 | 2019-04-29 | 2019-07-15 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-01-08 | COMP | 2020-01-28 | COMP | Rule 16 | 54 | 99 | 20 | 1 | 5 | 14 | 188
13214 | 2019-04-29 | 2019-07-16 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-14 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-02-13 | COMP | Rule 15/16 | 55 | 107 | 19 | 5 | 1 | 18 | 200
13382 | 2019-04-29 | 2019-07-23 | 2019-10-28 | 2019-10-28 | COMP | 2019-11-04 | COMP | 2020-01-03 | COMP | 2020-01-07 | COMP | 2020-01-22 | COMP | Rule 16 | 60 | 69 | 6 | 40 | 3 | 11 | 184
13468 | 2019-04-29 | 2019-07-25 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-07 | COMP | 2019-11-14 | COMP | 2020-11-09 | COMP | 2020-12-21 | COMP | Rule 16 | 62 | 71 | 5 | 5 | 250 | 28 | 416
13549 | 2019-04-29 | 2019-07-31 | 2019-12-16 | 2020-09-09 | COMP | 2020-09-30 | COMP | 2020-03-06 | COMP | 2020-10-06 | COMP | 2020-11-10 | COMP | Rule 16 | 66 | 95 | 16 |  | 151 | 26 | 390
13616 | 2019-04-29 | 2019-08-02 | 2019-12-19 | 2019-12-19 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-01-09 | COMP | 2020-01-18 | COMP | Rule 16 | 68 | 96 | 10 | 1 | 5 | 7 | 182
13775 | 2019-04-29 | 2019-08-08 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-01-02 | COMP | 2020-01-03 | COMP | Rule 16 | 72 | 39 | 15 | 1 | 48 | 2 | 172
14079 | 2019-04-29 | 2019-08-23 | 2019-10-31 | 2019-10-31 | COMP | 2020-06-30 | COMP | 2020-07-29 | COMP | 2021-10-23 | INPR | 2020-09-03 | COMP | Rule 16 | 83 | 49 | 166 | 22 |  |  | 343
14110 | 2019-04-29 | 2019-08-26 | 2019-10-03 | 2019-10-31 | COMP | 2019-12-17 | COMP | 2020-12-16 | COMP | 2020-12-02 | COMP | 2020-12-31 | COMP | Rule 16 | 84 | 28 | 31 | 253 | 0 | 11 | 423
14718 | 2019-04-29 | 2019-09-24 | 2020-02-26 | 2020-12-17 | COMP | 2021-03-15 | COMP | 2021-06-14 | COMP | 2021-05-10 | COMP | 2021-07-22 | COMP | Rule 16 | 104 | 105 | 59 | 65 | 0 | 28 | 563
14839 | 2019-04-29 | 2019-09-30 | 2020-01-29 | 2020-11-23 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2021-05-10 | COMP | 2021-06-11 | COMP | Rule 16 | 108 | 82 | 20 | 1 | 96 | 24 | 535
15178 | 2019-04-29 | 2019-10-17 | 2019-12-04 | 2020-01-28 | COMP | 2020-01-31 | COMP | 2020-03-26 | INPR | 2023-12-09 | CANC | 2020-05-19 | COMP | Rule 16 | 121 | 32 | 4 |  |  |  | 267
15467 | 2019-04-29 | 2019-11-04 | 2020-03-04 | 2020-03-04 | COMP | 2020-04-20 | COMP | 2020-07-21 | COMP | 2020-08-28 | COMP | 2020-11-23 | COMP | Rule 16 | 133 | 81 | 34 | 66 | 29 | 60 | 398
15621 | 2019-04-29 | 2019-11-12 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-02-25 | COMP | 2020-03-04 | COMP | Rule 16 | 138 | 24 | 23 | 1 | 25 | 7 | 213
16705 | 2019-04-29 | 2020-01-14 | 2020-04-24 | 2020-09-02 | COMP | 2020-09-18 | COMP | 2020-11-05 | COMP | 2020-11-02 | COMP | 2020-11-30 | COMP | Rule 16 | 179 | 72 | 12 | 35 | 0 | 15 | 401
11528 | 2019-04-30 | 2019-04-30 | 2019-05-02 | 2019-05-02 | COMP | 2019-05-08 | COMP | 2019-05-08 | COMP | 2019-10-01 | COMP | 2019-11-05 | COMP | Rule 15/16 | 1 | 3 | 5 | 1 | 102 | 26 | 133
11551 | 2019-04-30 | 2019-05-03 | 2019-06-13 | 2019-07-23 | COMP | 2019-09-17 | COMP | 2019-09-18 | COMP | 2019-10-02 | COMP | 2019-12-24 | COMP | Rule 16 | 4 | 29 | 40 | 2 | 11 | 57 | 165
11571 | 2019-04-30 | 2019-05-04 | 2019-06-08 | 2019-06-08 | COMP | 2019-08-08 | COMP | 2019-08-08 | INPR | 2019-08-13 | COMP | 2020-02-22 | COMP | Rule 16 | 4 | 24 | 43 |  |  |  | 204
11633 | 2019-04-30 | 2019-05-06 | 2019-11-27 | 2019-11-27 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-02-24 | COMP | 2020-03-19 | COMP | Rule 16 | 5 | 144 | 56 | 1 | 3 | 19 | 223
11795 | 2019-04-30 | 2019-05-13 | 2019-10-30 | 2019-10-30 | COMP | 2019-12-12 | COMP | 2020-06-17 | COMP | 2020-04-28 | COMP | 2020-07-25 | COMP | Rule 15/16 | 10 | 120 | 29 | 130 | 0 | 28 | 313
11838 | 2019-04-30 | 2019-05-14 | 2019-08-07 | 2019-08-07 | COMP | 2019-08-08 | NOTN | 2019-08-08 | COMP | 2019-08-08 | COMP | 2019-09-30 | COMP | Rule 16 | 11 | 60 |  | 2 | 1 | 37 | 107
12041 | 2019-04-30 | 2019-05-21 | 2020-04-13 | 2020-04-13 | COMP | 2020-10-20 | COMP | 2020-11-23 | COMP | 2021-06-18 | COMP | 2021-10-07 | COMP | Rule 15/16 | 16 | 225 | 135 | 24 | 143 | 78 | 616
12225 | 2019-04-30 | 2019-05-28 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-15 | COMP | 2019-09-18 | COMP | 2019-09-04 | COMP | 2019-10-02 | COMP | Rule 16 | 20 | 49 | 9 | 24 | 0 | 11 | 109
12313 | 2019-04-30 | 2019-05-30 | 2019-08-28 | 2019-08-28 | COMP | 2019-11-13 | COMP | 2020-04-23 | COMP | 2020-08-27 | COMP | 2020-10-08 | COMP | Rule 16 | 22 | 64 | 54 | 111 | 90 | 30 | 366
12337 | 2019-04-30 | 2019-06-01 | 2020-01-31 | 2023-03-06 | COMP | 2023-03-08 | NOTN | 2023-03-16 | COMP | 2022-01-31 | COMP | 2023-07-20 | COMP | Rule 16 | 23 | 167 |  | 9 | 0 | 88 | 1062
12391 | 2019-04-30 | 2019-06-05 | 2019-09-25 | 2019-09-25 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-07-22 | COMP | 2021-01-13 | COMP | Rule 16 | 26 | 79 | 178 | 1 | 31 | 120 | 430
12463 | 2019-04-30 | 2019-06-08 | 2020-07-13 | 2020-07-13 | COMP | 2020-12-14 | COMP | 2021-03-10 | COMP | 2021-03-05 | COMP | 2021-04-29 | COMP | Rule 15/16 | 28 | 276 | 107 | 59 | 0 | 37 | 504
12507 | 2019-04-30 | 2019-06-10 | 2019-08-04 | 2019-08-04 | COMP | 2019-08-08 | COMP | 2019-08-08 | COMP | 2020-03-01 | INPR | 2019-11-15 | COMP | Rule 16 | 29 | 39 | 4 | 1 |  |  | 140
12519 | 2019-04-30 | 2019-06-10 | 2019-07-24 | 2019-07-24 | COMP | 2019-09-18 | COMP | 2019-10-08 | COMP | 2019-10-15 | COMP | 2019-10-28 | COMP | Rule 16 | 29 | 32 | 40 | 15 | 6 | 10 | 127
12542 | 2019-04-30 | 2019-06-11 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-24 | COMP | 2019-07-29 | COMP | 2019-12-29 | INPR | 2019-09-04 | COMP | Rule 16 | 30 | 12 | 20 | 4 |  |  | 89
12543 | 2019-04-30 | 2019-06-11 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-24 | COMP | 2019-08-12 | COMP | 2020-01-19 | INPR | 2019-09-26 | COMP | Rule 16 | 30 | 20 | 12 | 14 |  |  | 105
12876 | 2019-04-30 | 2019-06-26 | 2019-10-25 | 2019-10-25 | COMP | 2019-11-20 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-12-29 | COMP | Rule 15/16 | 41 | 86 | 18 | 29 | 1 | 250 | 420
12893 | 2019-04-30 | 2019-06-27 | 2020-06-08 | 2020-06-08 | COMP | 2020-07-15 | COMP | 2021-03-13 | COMP | 2021-07-15 | COMP | 2021-10-29 | COMP | Rule 15/16 | 42 | 238 | 28 | 165 | 87 | 76 | 632
13004 | 2019-04-30 | 2019-07-04 | 2020-01-23 | 2020-01-23 | COMP | 2020-02-12 | COMP | 2020-03-13 | COMP | 2020-03-24 | COMP | 2020-07-27 | COMP | Rule 15/16 | 46 | 138 | 15 | 22 | 8 | 89 | 314
13012 | 2019-04-30 | 2019-07-05 | 2019-09-17 | 2019-09-17 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2020-12-15 | COMP | 2020-12-22 | COMP | Rule 16 | 47 | 52 | 35 | 1 | 280 | 6 | 416
13175 | 2019-04-30 | 2019-07-16 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-30 | COMP | 2020-02-03 | COMP | 2020-09-08 | COMP | 2020-09-12 | COMP | Rule 15/16 | 54 | 90 | 26 | 24 | 154 | 4 | 347
13793 | 2019-04-30 | 2019-08-10 | 2020-01-28 | 2020-01-28 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-11-02 | COMP | 2020-12-18 | COMP | Rule 16 | 72 | 115 | 25 | 1 | 173 | 32 | 414
13854 | 2019-04-30 | 2019-08-14 | 2019-10-14 | 2019-10-14 | COMP | 2020-01-07 | COMP | 2020-01-15 | COMP | 2020-09-22 | COMP | 2020-11-10 | COMP | Rule 15/16 | 75 | 43 | 57 | 7 | 176 | 36 | 389
14075 | 2019-04-30 | 2019-08-24 | 2020-03-11 | 2020-03-11 | COMP | 2021-09-09 | COMP | 2021-10-06 | COMP | 2021-10-19 | COMP | 2022-02-15 | COMP | Rule 16 | 82 | 135 | 380 | 20 | 10 | 82 | 705
14646 | 2019-04-30 | 2019-09-21 | 2020-04-12 | 2020-06-13 | COMP | 2022-07-30 | REQD | 2022-07-30 | REQD | 2022-07-30 | REQD | 2020-06-18 | COMP | Rule 16 | 101 | 138 |  |  |  |  | 287
14895 | 2019-04-30 | 2019-10-03 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2020-01-07 | COMP | 2020-03-06 | COMP | Rule 16 | 110 | 19 | 8 | 1 | 39 | 42 | 214
14928 | 2019-04-30 | 2019-10-04 | 2020-02-01 | 2020-05-07 | COMP | 2020-05-21 | COMP | 2020-06-05 | COMP | 2020-06-06 | COMP | 2020-07-02 | COMP | Rule 16 | 111 | 80 | 11 | 11 | 1 | 19 | 297
16253 | 2019-04-30 | 2019-12-17 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-01 | COMP | 2020-08-15 | COMP | 2021-06-10 | COMP | 2022-02-09 | COMP | Rule 16 | 160 | 123 | 15 | 33 | 205 | 169 | 701
16439 | 2019-04-30 | 2019-12-31 | 2020-08-09 | 2020-08-09 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2022-07-16 | INPR | 2020-09-23 | COMP | Rule 16 | 169 | 155 | 10 | 1 |  |  | 355
16655 | 2019-04-30 | 2020-01-10 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-03-30 | COMP | 2020-04-08 | COMP | Rule 16 | 176 | 29 | 17 | 1 | 11 | 8 | 237
16918 | 2019-04-30 | 2020-01-23 | 2020-06-13 | 2020-07-01 | COMP | 2020-10-01 | COMP | 2020-11-07 | COMP | 2021-02-09 | COMP | 2021-03-02 | COMP | Rule 16 | 184 | 100 | 66 | 27 | 61 | 15 | 462
17792 | 2019-04-30 | 2020-02-27 | 2020-08-26 | 2020-08-26 | COMP | 2020-11-09 | COMP | 2021-03-01 | COMP | 2021-02-22 | COMP | 2021-06-17 | COMP | Rule 15/16 | 208 | 129 | 53 | 74 | 0 | 78 | 538
18100 | 2019-04-30 | 2020-03-11 | 2021-01-15 | 2021-04-06 | COMP | 2021-06-28 | COMP | 2021-12-17 | COMP | 2022-01-03 | COMP | 2022-02-05 | COMP | Rule 15/16 | 217 | 216 | 59 | 120 | 12 | 24 | 698
18113 | 2019-04-30 | 2020-03-11 | 2020-04-10 | 2020-05-19 | COMP | 2020-06-01 | NOTN | 2020-06-01 | INPR | 2020-06-01 | COMP | 2020-06-25 | COMP | Other | 217 | 23 |  |  |  |  | 292
20010 | 2019-04-30 | 2020-06-01 | 2020-08-25 | 2020-08-25 | COMP | 2020-09-09 | NOTN | 2023-10-03 | COMP | 2023-10-03 | NOTN | 2023-12-11 | COMP | Other | 274 | 62 |  | 780 |  |  | 1160
11550 | 2019-05-01 | 2019-05-01 | 2019-08-22 | 2019-08-22 | COMP | 2019-11-27 | COMP | 2019-11-27 | INPR | 2019-12-29 | REQD | 2019-09-11 | COMP | Rule 16 | 1 | 80 | 68 |  |  |  | 93
11640 | 2019-05-01 | 2019-05-06 | 2019-12-14 | 2019-12-14 | COMP | 2020-02-05 | COMP | 2021-03-29 | INPR |  | REQD | 2020-11-12 | COMP | Rule 15/16 | 4 | 154 | 35 |  |  |  | 389
11660 | 2019-05-01 | 2019-05-06 | 2019-06-27 | 2019-06-27 | COMP | 2019-07-22 | COMP | 2019-07-22 | COMP | 2019-10-08 | COMP | 2019-11-19 | COMP | Rule 16 | 4 | 38 | 17 | 1 | 56 | 30 | 141
11661 | 2019-05-01 | 2019-05-06 | 2019-07-13 | 2019-07-13 | COMP | 2019-07-26 | COMP | 2019-08-07 | COMP | 2019-10-08 | COMP | 2019-11-18 | COMP | Rule 16 | 4 | 48 | 10 | 9 | 44 | 29 | 140
11874 | 2019-05-01 | 2019-05-15 | 2019-10-14 | 2019-10-14 | COMP | 2020-01-17 | COMP | 2020-10-08 | COMP | 2021-03-21 | COMP | 2021-04-29 | COMP | Rule 16 | 11 | 106 | 65 | 186 | 110 | 29 | 503
12054 | 2019-05-01 | 2019-05-22 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-09 | COMP | 2019-07-09 | COMP | 2019-12-29 | INPR | 2019-08-19 | COMP | Rule 16 | 16 | 29 | 5 | 1 |  |  | 77
12132 | 2019-05-01 | 2019-05-23 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2020-02-28 | COMP | 2020-04-15 | COMP | Rule 16 | 17 | 120 | 31 | 1 | 43 | 34 | 241
12163 | 2019-05-01 | 2019-05-24 | 2019-07-23 | 2019-07-23 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-12-05 | COMP | 2020-01-24 | COMP | Rule 15/16 | 18 | 41 | 72 | 1 | 23 | 34 | 184
12223 | 2019-05-01 | 2019-05-28 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-22 | COMP | 2019-09-03 | COMP | 2019-08-19 | COMP | 2019-09-20 | COMP | Rule 15/16 | 19 | 26 | 14 | 31 | 0 | 14 | 100
12238 | 2019-05-01 | 2019-05-29 | 2019-06-14 | 2019-06-14 | COMP | 2019-07-23 | COMP | 2019-07-23 | NOTN | 2019-09-18 | COMP | 2019-09-23 | COMP | Rule 16 | 20 | 13 | 27 |  |  |  | 101
12341 | 2019-05-01 | 2019-06-01 | 2019-07-17 | 2019-07-17 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-02-19 | COMP | Rule 16 | 22 | 32 | 84 | 1 | 1 | 65 | 201
12452 | 2019-05-01 | 2019-06-07 | 2020-01-10 | 2020-01-10 | COMP | 2020-03-31 | COMP | 2020-06-01 | COMP | 2020-07-03 | COMP | 2020-08-12 | COMP | Rule 15/16 | 27 | 149 | 56 | 44 | 25 | 29 | 325
12462 | 2019-05-01 | 2019-06-08 | 2020-04-29 | 2020-04-29 | COMP | 2020-12-14 | COMP | 2021-03-14 | COMP | 2021-08-19 | COMP | 2021-09-20 | COMP | Rule 15/16 | 27 | 224 | 159 | 61 | 112 | 22 | 602
12464 | 2019-05-01 | 2019-06-08 | 2020-03-06 | 2020-03-06 | COMP | 2020-07-22 | COMP | 2020-12-29 | COMP | 2021-09-09 | COMP | 2021-10-08 | COMP | Rule 15/16 | 27 | 186 | 98 | 110 | 177 | 22 | 616
12631 | 2019-05-01 | 2019-06-17 | 2019-08-20 | 2019-08-20 | COMP | 2019-11-13 | COMP | 2019-12-20 | COMP | 2021-09-27 | COMP | 2021-12-02 | COMP | Rule 16 | 33 | 46 | 60 | 26 | 446 | 46 | 652
12742 | 2019-05-01 | 2019-06-21 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-03 | COMP | 2020-03-26 | COMP | 2020-07-10 | COMP | 2020-07-31 | COMP | Rule 15/16 | 37 | 155 | 20 | 18 | 76 | 16 | 317
12818 | 2019-05-01 | 2019-06-24 | 2019-10-18 | 2019-10-18 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-08-03 | COMP | 2020-10-20 | COMP | Rule 16 | 38 | 83 | 29 | 1 | 171 | 56 | 373
12946 | 2019-05-01 | 2019-07-01 | 2019-12-31 | 2019-12-31 | COMP | 2020-03-26 | COMP | 2020-06-08 | COMP | 2021-07-19 | COMP | 2021-08-03 | COMP | Rule 16 | 43 | 126 | 60 | 52 | 281 | 12 | 569
13083 | 2019-05-01 | 2019-07-09 | 2020-01-15 | 2020-01-15 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | 2021-02-01 | COMP | 2021-03-08 | COMP | Rule 15/16 | 48 | 131 | 250 | 1 | 15 | 25 | 465
13084 | 2019-05-01 | 2019-07-09 | 2020-01-10 | 2020-01-10 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | 2021-01-29 | COMP | 2021-03-08 | COMP | Rule 16 | 48 | 128 | 253 | 1 | 14 | 26 | 465
13085 | 2019-05-01 | 2019-07-09 | 2020-02-04 | 2020-02-04 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2021-01-07 | COMP | 2021-02-04 | COMP | Rule 15/16 | 48 | 144 | 49 | 1 | 187 | 20 | 444
13146 | 2019-05-01 | 2019-07-12 | 2020-02-04 | 2020-02-04 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2021-01-07 | COMP | 2021-02-03 | COMP | Rule 16 | 51 | 141 | 83 | 1 | 153 | 19 | 443
13451 | 2019-05-01 | 2019-07-25 | 2019-09-12 | 2019-09-13 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-10-07 | COMP | Rule 16 | 60 | 35 | 7 | 1 | 1 | 11 | 111
13857 | 2019-05-01 | 2019-08-13 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2020-01-23 | COMP | 2020-03-05 | COMP | Rule 16 | 73 | 19 | 16 | 1 | 78 | 30 | 212
13889 | 2019-05-01 | 2019-08-15 | 2019-10-25 | 2019-10-25 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-08-13 | COMP | 2020-11-24 | COMP | Rule 15/16 | 75 | 51 | 66 | 1 | 137 | 72 | 397
14333 | 2019-05-01 | 2019-09-05 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-12-20 | COMP | 2020-01-29 | COMP | Rule 16 | 89 | 30 | 14 | 1 | 32 | 26 | 187
14402 | 2019-05-01 | 2019-09-09 | 2020-01-24 | 2020-01-24 | COMP | 2020-01-26 | NOTN | 2020-03-17 | COMP | 2020-12-09 | COMP | 2020-12-11 | COMP | Rule 16 | 91 | 94 |  | 37 | 187 | 3 | 408
14644 | 2019-05-01 | 2019-09-21 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-15 | COMP | 2020-10-08 | COMP | 2021-05-26 | COMP | 2021-06-24 | COMP | Rule 16 | 100 | 186 | 20 | 61 | 158 | 21 | 542
14703 | 2019-05-01 | 2019-09-23 | 2020-02-28 | 2020-02-28 | COMP | 2020-05-18 | COMP | 2021-02-05 | COMP | 2022-05-19 | COMP | 2022-05-25 | COMP | Rule 16 | 101 | 108 | 57 | 182 | 326 | 5 | 774
15335 | 2019-05-01 | 2019-10-26 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-14 | COMP | 2020-03-20 | COMP | 2023-04-30 | INPR | 2020-06-19 | COMP | Rule 16 | 125 | 52 | 23 | 25 |  |  | 287
15365 | 2019-05-01 | 2019-10-29 | 2019-12-07 | 2020-01-14 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-02-24 | COMP | 2020-05-07 | COMP | Rule 16 | 127 | 26 | 13 | 1 | 16 | 54 | 257
15427 | 2019-05-01 | 2019-10-31 | 2020-03-09 | 2020-03-09 | COMP | 2020-06-04 | COMP | 2020-06-04 | COMP | 2020-10-13 | COMP | 2020-11-05 | COMP | Rule 16 | 129 | 86 | 63 | 1 | 93 | 18 | 385
16795 | 2019-05-01 | 2020-01-16 | 2020-04-30 | 2020-04-30 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-09-01 | COMP | 2020-10-16 | COMP | Rule 16 | 179 | 74 | 87 | 1 | 2 | 33 | 371
20131 | 2019-05-01 | 2020-06-09 | 2020-08-24 | 2021-01-12 | COMP | 2021-07-07 | COMP | 2023-05-04 | COMP | 2023-05-08 | COMP | 2023-08-23 | COMP | Rule 15/16 | 279 | 55 | 123 | 460 | 3 | 75 | 1085
4196 | 2019-05-02 | 2019-07-02 | 2019-07-15 | 2019-07-15 | COMP | 2019-11-06 | COMP | 2019-11-18 | COMP | 2019-11-05 | COMP | 2020-01-17 | COMP | Rule 16 | 43 | 9 | 82 | 8 | 0 | 41 | 179
11790 | 2019-05-02 | 2019-05-13 | 2019-07-17 | 2019-07-17 | COMP |  | INPR |  | REQD |  | REQD | 2019-08-20 | COMP | Rule 16 | 8 | 46 |  |  |  |  | 77
11798 | 2019-05-02 | 2019-05-13 | 2019-12-07 | 2019-12-07 | COMP | 2020-01-15 | COMP | 2020-01-15 | COMP | 2020-02-07 | COMP | 2020-03-13 | COMP | Rule 15/16 | 8 | 144 | 26 | 1 | 17 | 25 | 217
11810 | 2019-05-02 | 2019-05-13 | 2019-12-13 | 2019-12-19 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2022-01-30 | INPR | 2020-12-12 | COMP | Rule 16 | 8 | 149 | 64 | 1 |  |  | 407
11850 | 2019-05-02 | 2019-05-14 | 2019-09-25 | 2019-09-26 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-08-18 | COMP | 2020-09-13 | COMP | Rule 16 | 9 | 94 | 90 | 1 | 137 | 18 | 345
12118 | 2019-05-02 | 2019-05-23 | 2019-07-01 | 2019-07-01 | COMP | 2019-07-30 | COMP | 2019-07-17 | COMP | 2019-07-30 | COMP | 2019-08-02 | COMP | Rule 16 | 16 | 27 | 21 |  | 10 | 4 | 65
12126 | 2019-05-02 | 2019-05-23 | 2019-10-02 | 2019-11-16 | COMP | 2019-12-11 | COMP | 2020-02-19 | COMP | 2020-02-27 | COMP | 2020-05-13 | COMP | Rule 16 | 16 | 92 | 16 | 47 | 7 | 55 | 260
12155 | 2019-05-02 | 2019-05-24 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-08-07 | COMP | 2019-09-11 | COMP | Rule 16 | 17 | 53 | 3 | 1 | 0 | 22 | 92
12181 | 2019-05-02 | 2019-05-28 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-20 | COMP | 2019-11-20 | COMP | 2020-03-18 | COMP | 2020-08-14 | COMP | Rule 16 | 18 | 54 | 7 | 65 | 80 | 107 | 326
12375 | 2019-05-02 | 2019-06-04 | 2019-10-28 | 2019-10-28 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-09-19 | COMP | 2020-11-04 | COMP | Rule 15/16 | 23 | 103 | 68 | 1 | 159 | 33 | 383
12416 | 2019-05-02 | 2019-06-05 | 2019-10-04 | 2019-10-04 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-12 | COMP | 2019-11-09 | COMP | Rule 16 | 24 | 86 | 14 | 1 | 14 |  | 134
12481 | 2019-05-02 | 2019-06-11 | 2019-10-21 | 2019-10-21 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-04-17 | COMP | 2020-05-28 | COMP | Rule 16 | 28 | 93 | 119 | 1 | 5 | 29 | 270
12493 | 2019-05-02 | 2019-06-10 | 2019-09-24 | 2019-09-24 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-05-15 | COMP | 2020-06-15 | COMP | Rule 16 | 27 | 75 | 115 | 1 | 48 | 21 | 282
12547 | 2019-05-02 | 2019-06-12 | 2019-09-20 | 2019-09-20 | COMP | 2019-09-20 | NOTN | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-02-20 | COMP | Other | 29 | 71 |  | 51 | 1 | 53 | 201
12633 | 2019-05-02 | 2019-06-17 | 2019-10-25 | 2019-10-25 | COMP | 2019-12-11 | COMP | 2019-12-13 | COMP | 2020-01-02 | COMP | 2020-02-17 | COMP | Rule 16 | 32 | 93 | 31 | 3 | 13 | 31 | 198
12789 | 2019-05-02 | 2019-06-22 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-08 | COMP | 2020-11-03 | COMP | 2020-12-04 | COMP | 2021-01-13 | COMP | Rule 16 | 36 | 66 | 10 | 272 | 21 | 27 | 428
13116 | 2019-05-02 | 2019-07-11 | 2019-11-05 | 2019-11-05 | COMP | 2019-11-27 | COMP | 2020-02-26 | COMP | 2020-05-28 | COMP | 2020-07-09 | COMP | Rule 16 | 49 | 83 | 16 | 60 | 66 | 31 | 300
13462 | 2019-05-02 | 2019-07-26 | 2019-09-10 | 2019-09-10 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-12-17 | COMP | 2020-01-13 | COMP | Rule 16 | 60 | 32 | 10 | 1 | 59 | 18 | 175
13777 | 2019-05-02 | 2019-08-08 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-11-20 | COMP | 2020-01-06 | COMP | Rule 16 | 69 | 38 | 11 | 1 | 26 | 30 | 170
13862 | 2019-05-02 | 2019-08-13 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-11 | COMP | 2020-02-26 | COMP | 2020-03-11 | COMP | 2020-05-19 | COMP | Rule 16 | 72 | 106 | 19 | 11 | 11 | 50 | 264
13971 | 2019-05-02 | 2019-08-20 | 2020-01-06 | 2020-01-06 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-06-01 | COMP | 2020-07-15 | COMP | Rule 16 | 77 | 94 | 43 | 1 | 61 | 33 | 304
14086 | 2019-05-02 | 2019-08-23 | 2020-03-16 | 2020-03-16 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2021-11-15 | COMP | 2022-05-04 | COMP | Rule 16 | 80 | 139 | 79 | 1 | 345 | 119 | 758
14161 | 2019-05-02 | 2019-08-28 | 2019-10-16 | 2019-10-16 | COMP | 2019-10-23 | COMP | 2019-10-28 | COMP | 2019-10-21 | COMP | 2019-11-21 | COMP | Rule 16 | 83 | 35 | 6 | 4 | 0 | 18 | 142
14344 | 2019-05-02 | 2019-09-05 | 2019-10-04 | 2019-10-04 | COMP | 2019-10-22 | COMP | 2019-11-18 | COMP | 2020-01-06 | COMP | 2020-01-28 | COMP | Rule 16 | 88 | 22 | 13 | 19 | 32 | 16 | 185
14920 | 2019-05-02 | 2019-10-05 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-27 | COMP | 2020-02-19 | COMP | 2020-02-05 | COMP | 2020-02-27 | COMP | Rule 16 | 109 | 65 | 11 | 17 | 0 | 7 | 206
15585 | 2019-05-02 | 2019-11-08 | 2020-03-02 | 2020-03-02 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2022-01-12 | COMP | 2022-02-07 | COMP | Rule 16 | 134 | 75 | 74 | 1 | 400 | 18 | 697
15598 | 2019-05-02 | 2019-11-08 | 2020-01-27 | 2020-01-27 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-02-28 | COMP | 2020-03-24 | COMP | Rule 16 | 134 | 51 | 18 | 1 | 7 | 18 | 224
15690 | 2019-05-02 | 2019-11-15 | 2020-03-14 | 2020-03-14 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-09-01 | COMP | Rule 15/16 | 138 | 80 | 88 | 1 | 1 | 34 | 338
17019 | 2019-05-02 | 2020-01-28 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2022-02-28 | COMP | 2023-03-20 | COMP | Rule 15/16 | 185 | 73 | 58 | 1 | 398 | 265 | 975
17522 | 2019-05-02 | 2020-02-19 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-19 | COMP | 2020-07-23 | COMP | 2021-09-16 | COMP | 2021-11-03 | COMP | Rule 16 | 200 | 61 | 27 | 25 | 290 | 35 | 633
26249 | 2019-05-02 | 2021-03-13 | 2021-04-23 | 2021-09-28 | COMP | 2021-11-16 | COMP | 2021-12-29 | COMP | 2021-11-18 | COMP | 2022-02-02 | COMP | Rule 16 | 468 | 30 | 35 | 30 | 0 | 25 | 694
4174 | 2019-05-03 | 2019-05-24 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-07 | COMP | 2019-12-13 | COMP | 2019-11-14 | COMP | 2019-12-13 | COMP | Rule 16 | 16 | 88 | 30 | 24 | 0 | 1 | 155
11668 | 2019-05-03 | 2019-05-07 | 2019-05-21 | 2019-05-22 | COMP | 2019-06-20 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-06-27 | COMP | Rule 15/16 | 3 | 11 | 21 | 2 | 1 | 5 | 39
11897 | 2019-05-03 | 2019-05-15 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-05 | COMP | 2019-07-10 | COMP | 2019-07-08 | COMP | 2019-12-20 | COMP | Rule 16 | 9 | 30 | 7 | 4 | 0 | 114 | 160
11925 | 2019-05-03 | 2019-05-16 | 2019-08-09 | 2020-10-29 | COMP | 2020-11-13 | COMP | 2020-01-22 | COMP | 2021-03-15 | COMP | 2021-05-07 | COMP | Rule 16 | 10 | 60 | 11 |  | 289 | 40 | 507
12014 | 2019-05-03 | 2019-05-21 | 2019-07-21 | 2019-07-21 | COMP | 2019-08-22 | COMP | 2019-08-22 | COMP | 2019-08-27 | COMP | 2019-11-13 | COMP | Rule 16 | 13 | 42 | 24 | 1 | 4 | 55 | 135
12157 | 2019-05-03 | 2019-05-24 | 2019-10-06 | 2019-10-06 | COMP | 2019-10-31 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2020-01-15 | COMP | Rule 15/16 | 16 | 93 | 19 | 7 | 1 | 44 | 176
12338 | 2019-05-03 | 2019-06-01 | 2019-07-13 | 2019-07-13 | COMP | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-09-05 | COMP | 2020-01-08 | COMP | Rule 16 | 20 | 29 | 32 | 1 | 7 | 85 | 171
12536 | 2019-05-03 | 2019-06-11 | 2019-07-10 | 2019-07-10 | COMP | 2019-07-29 | COMP | 2019-07-29 | COMP | 2019-08-07 | COMP | 2019-08-13 | COMP | Rule 16 | 27 | 21 | 14 | 1 | 8 | 5 | 71
12658 | 2019-05-03 | 2019-06-17 | 2019-10-12 | 2019-10-12 | COMP | 2019-10-30 | COMP | 2019-11-26 | COMP | 2019-12-30 | COMP | 2020-01-28 | COMP | Rule 16 | 31 | 83 | 13 | 19 | 22 | 20 | 184
12690 | 2019-05-03 | 2019-06-18 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-21 | COMP | 2019-12-13 | COMP | 2020-01-10 | COMP | 2020-01-30 | COMP | Rule 16 | 32 | 90 | 21 | 15 | 19 | 14 | 186
12700 | 2019-05-03 | 2019-06-18 | 2019-08-13 | 2019-09-07 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2020-07-31 | COMP | 2020-08-03 | COMP | Rule 15/16 | 32 | 40 | 67 | 1 | 161 | 2 | 316
12723 | 2019-05-03 | 2019-06-19 | 2019-10-19 | 2019-10-19 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2020-12-29 | COMP | 2021-06-29 | COMP | Rule 16 | 33 | 86 | 278 | 1 | 22 | 127 | 543
12727 | 2019-05-03 | 2019-06-20 | 2019-12-24 | 2019-12-24 | COMP | 2020-03-06 | COMP | 2020-04-20 | COMP | 2020-03-23 | COMP | 2020-04-22 | COMP | Rule 16 | 34 | 129 | 50 | 32 | 0 | 3 | 244
13089 | 2019-05-03 | 2019-07-09 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2020-03-21 | INPR | 2019-09-26 | COMP | Rule 16 | 46 | 21 | 5 | 1 |  |  | 102
13584 | 2019-05-03 | 2019-07-31 | 2020-01-08 | 2020-01-08 | COMP | 2021-01-12 | COMP | 2021-12-24 | COMP | 2021-12-27 | COMP | 2022-02-25 | COMP | Rule 15/16 | 62 | 110 | 256 | 241 | 2 | 43 | 709
13827 | 2019-05-03 | 2019-08-12 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-08 | COMP | 2020-04-20 | COMP | 2021-03-08 | COMP | 2021-04-21 | COMP | Rule 16 | 70 | 155 | 11 | 9 | 222 | 33 | 495
14141 | 2019-05-03 | 2019-08-27 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2020-04-28 | COMP | 2020-04-30 | COMP | Rule 16 | 81 | 29 | 7 | 1 | 134 | 3 | 250
14289 | 2019-05-03 | 2019-09-03 | 2020-02-26 | 2020-02-26 | COMP | 2023-03-22 | COMP | 2021-02-04 | COMP | 2023-09-27 | COMP | 2023-10-24 | COMP | Rule 16 | 85 | 120 | 773 |  | 666 | 20 | 1126
11623 | 2019-05-04 | 2019-05-06 | 2019-05-14 | 2019-05-14 | COMP | 2019-06-03 | COMP | 2019-06-03 | COMP | 2019-04-18 | COMP | 2019-07-11 | COMP | Rule 16 | 1 | 7 | 14 | 1 | 0 | 28 | 47
12539 | 2019-05-04 | 2019-06-11 | 2019-09-07 | 2019-09-07 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2020-02-04 | COMP | 2020-02-05 | COMP | Rule 16 | 26 | 62 | 28 | 1 | 74 | 2 | 189
17672 | 2019-05-04 | 2020-02-24 | 2020-06-11 | 2020-11-20 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP | 2021-02-26 | COMP | 2021-03-15 | COMP | Rule 16 | 201 | 78 | 7 | 1 | 59 | 12 | 467
11693 | 2019-05-06 | 2019-05-08 | 2019-06-25 | 2019-06-25 | COMP | 2019-07-11 | COMP | 2019-09-08 | COMP | 2019-07-24 | COMP | 2019-09-27 | COMP | Rule 15/16 | 3 | 34 | 12 | 41 | 0 | 15 | 102
11809 | 2019-05-06 | 2019-05-13 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-09-17 | COMP | 2019-10-03 | COMP | Rule 16 | 6 | 74 | 10 | 1 | 7 | 13 | 106
11936 | 2019-05-06 | 2019-05-18 | 2019-07-29 | 2019-07-29 | COMP | 2019-09-12 | COMP | 2019-10-31 | COMP | 2019-11-19 | COMP | 2019-11-26 | COMP | Rule 16 | 10 | 49 | 33 | 36 | 13 | 6 | 143
11975 | 2019-05-06 | 2019-05-20 | 2019-07-08 | 2019-07-08 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-12-29 | INPR | 2019-09-04 | COMP | Rule 16 | 11 | 34 | 9 | 1 |  |  | 85
12026 | 2019-05-06 | 2019-05-21 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-21 | COMP | 2019-11-19 | COMP | 2019-11-18 | COMP | 2020-01-03 | COMP | Rule 16 | 12 | 87 | 21 | 21 | 0 | 30 | 167
12038 | 2019-05-06 | 2019-05-21 | 2019-06-13 | 2019-06-13 | COMP | 2019-07-03 | COMP | 2019-07-03 | COMP | 2021-10-23 | INPR | 2020-05-01 | COMP | Rule 16 | 12 | 17 | 15 | 1 |  |  | 250
12069 | 2019-05-06 | 2019-05-22 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-29 | COMP | 2019-09-24 | COMP | 2019-12-09 | COMP | 2020-01-03 | COMP | Rule 16 | 13 | 45 | 26 | 18 | 52 | 18 | 167
12122 | 2019-05-06 | 2019-05-23 | 2019-07-30 | 2019-07-30 | COMP | 2019-05-23 | NOTN | 2019-07-30 | COMP | 2019-08-20 | COMP | 2019-09-03 | COMP | Other | 14 | 47 |  | 1 | 16 | 10 | 84
12455 | 2019-05-06 | 2019-06-10 | 2019-08-02 | 2019-08-02 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-05-31 | INPR | 2019-12-31 | COMP | Rule 16 | 25 | 39 | 57 | 1 |  |  | 165
12508 | 2019-05-06 | 2019-06-10 | 2019-08-14 | 2019-10-19 | COMP | 2019-11-19 | COMP | 2020-08-12 | COMP | 2020-10-20 | COMP | 2020-12-05 | COMP | Rule 15/16 | 25 | 47 | 21 | 185 | 49 | 31 | 400
12563 | 2019-05-06 | 2019-06-12 | 2019-06-21 | 2019-06-21 | COMP | 2019-06-27 | COMP | 2019-06-22 | COMP | 2019-06-28 | COMP | 2019-07-04 | COMP | Rule 16 | 27 | 8 | 5 |  | 5 | 4 | 42
12588 | 2019-05-06 | 2019-06-14 | 2019-11-14 | 2019-11-14 | COMP | 2019-12-13 | COMP | 2021-06-04 | COMP | 2021-07-01 | COMP | 2021-08-06 | COMP | Rule 15/16 | 29 | 107 | 20 | 372 | 20 | 26 | 569
12684 | 2019-05-06 | 2019-06-18 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-30 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2020-01-08 | COMP | Rule 16 | 31 | 57 | 17 | 40 | 1 | 29 | 170
12792 | 2019-05-06 | 2019-06-22 | 2019-11-06 | 2019-11-06 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2021-04-27 | COMP | 2021-05-06 | COMP | Rule 16 | 34 | 96 | 37 | 1 | 333 | 8 | 505
13057 | 2019-05-06 | 2019-07-08 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-06 | COMP | 2019-11-20 | COMP | 2020-02-27 | COMP | 2020-03-05 | COMP | Rule 16 | 44 | 84 | 4 | 10 | 66 | 6 | 209
13281 | 2019-05-06 | 2019-07-18 | 2019-10-20 | 2019-10-20 | COMP | 2019-10-30 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-05-04 | COMP | Rule 16 | 52 | 66 | 8 | 82 | 1 | 46 | 251
13662 | 2019-05-06 | 2019-08-05 | 2019-11-25 | 2019-11-25 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2023-04-27 | COMP | 2023-10-03 | COMP | Rule 16 | 64 | 79 | 164 | 1 | 697 | 110 | 1110
14032 | 2019-05-06 | 2019-08-22 | 2020-12-28 | 2020-12-28 | COMP | 2021-02-18 | COMP | 2021-08-25 | COMP | 2022-08-10 | COMP | 2023-02-01 | COMP | Rule 15/16 | 77 | 339 | 36 | 133 | 242 | 119 | 941
14033 | 2019-05-06 | 2019-08-22 | 2020-12-18 | 2020-12-18 | COMP | 2021-02-18 | COMP | 2022-03-28 | COMP | 2022-10-22 | COMP | 2023-04-21 | COMP | Rule 15/16 | 77 | 334 | 41 | 280 | 146 | 123 | 997
14216 | 2019-05-06 | 2019-08-29 | 2019-12-23 | 2019-12-23 | COMP | 2020-03-11 | COMP | 2020-03-30 | COMP | 2020-04-05 | COMP | 2020-06-26 | COMP | Rule 15/16 | 82 | 79 | 54 | 14 | 5 | 59 | 289
14450 | 2019-05-06 | 2019-09-10 | 2020-04-06 | 2020-04-06 | COMP | 2020-10-02 | COMP | 2020-08-17 | COMP | 2021-11-10 | COMP | 2021-12-02 | COMP | Rule 16 | 89 | 143 | 128 |  | 312 | 14 | 649
14890 | 2019-05-06 | 2019-10-02 | 2019-10-24 | 2019-10-24 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-17 | COMP | 2020-02-27 | COMP | Rule 16 | 105 | 17 | 56 | 1 | 2 | 28 | 204
15802 | 2019-05-06 | 2019-11-20 | 2020-01-02 | 2020-01-02 | COMP | 2020-09-23 | COMP | 2021-03-03 | COMP | 2021-03-22 | COMP | 2021-06-04 | COMP | Rule 16 | 139 | 28 | 186 | 109 | 14 | 54 | 525
16605 | 2019-05-06 | 2020-01-09 | 2020-02-01 | 2020-04-05 | COMP | 2020-04-15 | COMP | 2020-06-26 | COMP | 2020-07-24 | COMP | 2020-09-03 | COMP | Rule 16 | 171 | 16 | 8 | 52 | 21 | 30 | 338
16608 | 2019-05-06 | 2020-01-09 | 2020-01-31 | 2020-01-31 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-06-04 | COMP | 2020-05-13 | COMP | Rule 16 | 171 | 16 | 30 | 1 | 59 |  | 258
16609 | 2019-05-06 | 2020-01-09 | 2020-04-14 | 2020-06-23 | COMP | 2020-09-09 | NOTN | 2021-11-18 | COMP | 2021-04-09 | NOTN | 2022-06-21 | COMP | Rule 16 | 171 | 67 |  | 356 |  |  | 788
16945 | 2019-05-06 | 2020-01-24 | 2020-11-09 | 2020-11-09 | COMP | 2021-04-20 | COMP | 2021-09-08 | COMP |  |  | 2021-12-10 | COMP | Rule 16 | 181 | 204 | 110 | 99 |  |  | 655
17299 | 2019-05-06 | 2020-02-07 | 2020-07-08 | 2020-07-08 | COMP | 2020-11-04 | COMP | 2020-11-09 | COMP | 2020-12-14 | COMP | 2020-12-29 | COMP | Rule 16 | 191 | 107 | 85 | 4 | 23 | 11 | 416
17988 | 2019-05-06 | 2020-03-06 | 2020-05-11 | 2020-05-11 | COMP | 2020-08-19 | COMP | 2020-10-19 | COMP | 2020-12-08 | COMP | 2020-12-22 | COMP | Rule 16 | 210 | 47 | 72 | 43 | 34 | 11 | 412
18633 | 2019-05-06 | 2020-04-01 | 2020-05-28 | 2020-05-28 | COMP | 2020-09-23 | COMP | 2020-09-30 | COMP | 2020-10-14 | COMP | 2020-10-22 | COMP | Rule 16 | 228 | 41 | 84 | 6 | 11 | 7 | 372
20528 | 2019-05-06 | 2020-06-24 | 2020-08-31 | 2020-08-31 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2020-10-02 | NOTN | 2020-11-18 | COMP | Rule 16 | 287 | 49 | 28 | 1 |  |  | 390
11747 | 2019-05-07 | 2019-05-09 | 2019-06-24 | 2019-10-10 | COMP | 2019-10-08 | NOTN | 2019-10-10 | COMP | 2019-10-14 | COMP | 2020-01-15 | COMP | Other | 3 | 32 |  | 1 | 3 | 63 | 174
12115 | 2019-05-07 | 2019-05-23 | 2019-06-23 | 2019-06-23 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-10-22 | COMP | 2019-10-23 | COMP | Rule 16 | 13 | 21 | 59 | 1 | 27 | 2 | 119
12252 | 2019-05-07 | 2019-05-29 | 2019-07-30 | 2019-09-07 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-12-24 | COMP | 2019-12-17 | COMP | Rule 16 | 16 | 44 | 11 | 1 | 64 |  | 155
12266 | 2019-05-07 | 2019-05-29 | 2019-10-12 | 2019-10-12 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-03-11 | COMP | 2020-04-25 | COMP | Rule 16 | 16 | 96 | 21 | 1 | 81 | 33 | 244
12294 | 2019-05-07 | 2019-05-30 | 2019-09-12 | 2019-09-12 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2021-03-09 | COMP | 2021-04-02 | COMP | Rule 15/16 | 17 | 74 | 272 | 1 | 102 | 19 | 480
12324 | 2019-05-07 | 2019-05-31 | 2019-09-07 | 2019-09-07 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-12-09 | COMP | Rule 16 | 18 | 69 | 31 | 2 | 1 | 32 | 149
12349 | 2019-05-07 | 2019-06-03 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-09 | COMP | 2019-08-09 | COMP | 2019-09-09 | COMP | 2019-09-22 | COMP | Rule 16 | 19 | 48 | 2 | 1 | 21 | 10 | 96
12457 | 2019-05-07 | 2019-06-07 | 2020-01-08 | 2020-07-15 | COMP | 2020-08-12 | COMP | 2020-07-07 | COMP | 2020-05-23 | COMP | 2021-02-25 | COMP | Rule 16 | 23 | 147 | 21 |  | 0 | 160 | 454
13306 | 2019-05-07 | 2019-07-20 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-14 | NOTN | 2019-12-11 | COMP | 2019-11-27 | COMP | 2020-07-20 | COMP | Other | 52 | 52 |  | 48 | 0 | 154 | 304
13342 | 2019-05-07 | 2019-07-22 | 2019-10-01 | 2019-10-01 | COMP | 2019-11-04 | COMP | 2019-11-18 | COMP | 2019-11-19 | COMP | 2019-12-23 | COMP | Rule 16 | 53 | 51 | 25 | 10 | 2 | 23 | 159
13678 | 2019-05-07 | 2019-08-05 | 2019-10-22 | 2019-10-22 | COMP | 2019-10-28 | COMP | 2019-10-29 | COMP | 2023-11-13 | COMP | 2023-12-20 | COMP | Rule 16 | 63 | 56 | 5 | 2 | 1015 | 26 | 1162
13686 | 2019-05-07 | 2019-08-05 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-16 | NOTN | 2019-10-07 | COMP | 2019-09-16 | COMP | 2019-11-25 | COMP | Other | 63 | 30 |  | 16 | 0 | 35 | 141
13906 | 2019-05-07 | 2019-08-15 | 2019-10-17 | 2020-04-09 | COMP | 2020-04-22 | COMP | 2019-12-23 | COMP | 2020-07-02 | COMP | 2020-08-05 | COMP | Rule 16 | 71 | 45 | 10 |  | 134 | 25 | 316
13928 | 2019-05-07 | 2019-08-17 | 2019-11-05 | 2019-11-05 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-01-18 | COMP | 2020-02-21 | COMP | Rule 16 | 72 | 56 | 18 | 1 | 32 | 23 | 199
14074 | 2019-05-07 | 2019-08-24 | 2020-02-18 | 2020-08-04 | COMP | 2020-09-18 | COMP | 2020-06-02 | COMP | 2020-11-24 | COMP | 2021-01-06 | COMP | Rule 15/16 | 77 | 119 | 33 |  | 124 | 28 | 420
15013 | 2019-05-07 | 2019-10-09 | 2019-10-28 | 2019-10-28 | COMP | 2020-03-05 | COMP | 2020-02-13 | COMP | 2020-02-18 | COMP | 2020-04-15 | COMP | Rule 16 | 109 | 14 | 87 |  | 3 | 42 | 237
16174 | 2019-05-07 | 2019-12-13 | 2020-03-23 | 2020-03-23 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2022-09-10 | COMP | 2022-10-26 | COMP | Rule 16 | 153 | 68 | 35 | 1 | 590 | 33 | 876
18340 | 2019-05-07 | 2020-03-19 | 2020-03-25 | 2020-03-25 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2021-11-18 | COMP | 2021-12-30 | COMP | Other | 218 | 5 | 86 | 1 | 334 | 29 | 668
19785 | 2019-05-07 | 2020-05-21 | 2020-07-17 | 2020-07-17 | COMP | 2020-07-21 | NOTN | 2020-09-17 | COMP | 2021-01-06 | COMP | 2021-02-23 | COMP | Other | 263 | 41 |  | 44 | 75 | 33 | 452
25564 | 2019-05-07 | 2021-02-16 | 2021-05-04 | 2021-05-04 | COMP | 2021-06-22 | COMP | 2021-06-22 | COMP | 2021-06-22 | COMP | 2022-01-28 | COMP | Rule 16 | 447 | 56 | 35 | 1 | 1 | 153 | 688
11840 | 2019-05-08 | 2019-05-14 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2023-04-30 | INPR | 2020-04-28 | COMP | Rule 15/16 | 5 | 133 | 21 | 1 |  |  | 245
11862 | 2019-05-08 | 2019-05-15 | 2019-08-12 | 2021-02-25 | COMP | 2021-03-03 | COMP | 2019-09-06 | COMP | 2021-06-08 | COMP | 2021-07-12 | COMP | Rule 16 | 6 | 62 | 5 |  | 441 | 24 | 548
11967 | 2019-05-08 | 2019-05-20 | 2020-01-08 | 2020-01-08 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-06-11 | COMP | 2020-07-10 | COMP | Rule 15/16 | 9 | 160 | 64 | 1 | 46 | 22 | 297
11974 | 2019-05-08 | 2019-05-20 | 2019-07-10 | 2019-07-10 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2020-01-21 | COMP | 2020-02-04 | COMP | Rule 16 | 9 | 36 | 87 | 1 | 47 | 11 | 186
12124 | 2019-05-08 | 2019-05-23 | 2019-09-11 | 2019-09-11 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-09-27 | COMP | 2019-10-14 | COMP | Rule 16 | 12 | 77 | 4 | 1 | 10 | 12 | 111
12139 | 2019-05-08 | 2019-05-24 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-09-04 | COMP | 2019-09-05 | COMP | Rule 16 | 13 | 54 | 12 | 1 | 7 | 2 | 84
12150 | 2019-05-08 | 2019-05-24 | 2019-08-12 | 2019-08-12 | COMP | 2019-09-30 | COMP | 2019-10-23 | COMP | 2021-01-02 | INPR | 2019-12-19 | COMP | Rule 16 | 13 | 55 | 35 | 18 |  |  | 156
12208 | 2019-05-08 | 2019-05-28 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-06 | COMP | 2019-09-06 | COMP | 2019-12-11 | COMP | 2020-01-13 | COMP | Rule 16 | 14 | 68 | 5 | 1 | 66 | 22 | 171
12268 | 2019-05-08 | 2019-05-29 | 2019-09-18 | 2019-09-27 | COMP | 2019-10-03 | NOTN | 2019-10-03 | COMP | 2019-07-12 | COMP | 2019-12-19 | COMP | Other | 15 | 79 |  | 5 | 0 | 53 | 156
12353 | 2019-05-08 | 2019-06-03 | 2019-08-28 | 2019-08-28 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-08-08 | COMP | 2020-10-14 | COMP | Rule 16 | 18 | 62 | 57 | 1 | 183 | 47 | 364
12379 | 2019-05-08 | 2019-06-04 | 2019-07-23 | 2019-07-23 | COMP | 2019-08-05 | COMP | 2019-08-06 | COMP | 2019-11-21 | COMP | 2019-12-19 | COMP | Rule 16 | 19 | 35 | 10 | 2 | 76 | 19 | 156
12415 | 2019-05-08 | 2019-06-05 | 2019-09-27 | 2019-09-27 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-11-04 | COMP | 2019-12-06 | COMP | Rule 16 | 20 | 81 | 26 | 1 | 2 | 22 | 147
12736 | 2019-05-08 | 2019-06-19 | 2019-10-15 | 2019-10-15 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2021-03-02 | COMP | 2021-04-16 | COMP | Rule 16 | 30 | 83 | 193 | 1 | 153 | 34 | 489
12813 | 2019-05-08 | 2019-06-25 | 2019-09-11 | 2019-09-11 | COMP | 2019-09-24 | COMP | 2019-10-15 | COMP | 2019-09-24 | COMP | 2019-11-07 | COMP | Rule 16 | 34 | 55 | 10 | 16 | 0 | 18 | 129
12885 | 2019-05-08 | 2019-06-27 | 2019-09-28 | 2019-09-28 | COMP | 2019-10-08 | COMP | 2020-07-28 | INPR | 2022-01-30 | REQD | 2020-07-13 | COMP | Rule 16 | 36 | 65 | 7 |  |  |  | 298
12965 | 2019-05-08 | 2019-07-02 | 2019-11-04 | 2019-11-04 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-03-19 | COMP | 2020-04-24 | COMP | Rule 16 | 39 | 88 | 94 | 1 | 0 | 25 | 243
13028 | 2019-05-08 | 2019-07-06 | 2019-07-16 | 2019-07-16 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2020-03-17 | COMP | 2020-03-18 | COMP | Rule 16 | 41 | 7 | 22 | 1 | 147 | 2 | 216
13092 | 2019-05-08 | 2019-07-10 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-12-17 | COMP | 2019-12-26 | COMP | Rule 16 | 44 | 55 | 15 | 1 | 43 | 7 | 160
13147 | 2019-05-08 | 2019-07-12 | 2020-04-15 | 2021-03-08 | COMP | 2021-03-26 | COMP | 2021-05-05 | COMP | 2021-04-29 | COMP | 2021-06-13 | COMP | Rule 16 | 46 | 191 | 15 | 29 | 0 | 27 | 528
13176 | 2019-05-08 | 2019-07-16 | 2019-11-16 | 2019-11-18 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-06-16 | COMP | 2020-06-24 | COMP | Rule 16 | 48 | 87 | 49 | 1 | 97 | 7 | 285
14284 | 2019-05-08 | 2019-09-03 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-04-24 | COMP | 2020-08-04 | COMP | Rule 16 | 82 | 105 | 11 | 1 | 48 | 72 | 314
14737 | 2019-05-08 | 2019-09-25 | 2019-11-16 | 2019-11-16 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-02-05 | COMP | 2020-03-12 | COMP | Rule 16 | 98 | 37 | 52 | 1 | 2 | 26 | 212
15387 | 2019-05-08 | 2019-10-29 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2022-01-30 | INPR | 2020-11-30 | COMP | Rule 16 | 122 | 142 | 9 | 1 |  |  | 394
15470 | 2019-05-08 | 2019-11-04 | 2019-12-09 | 2019-12-27 | COMP | 2020-01-15 | COMP | 2020-03-31 | COMP | 2020-06-16 | COMP | 2020-08-05 | COMP | Rule 16 | 126 | 23 | 13 | 53 | 55 | 37 | 315
15472 | 2019-05-08 | 2019-11-04 | 2020-10-27 | 2020-10-27 | COMP | 2021-01-07 | COMP | 2021-01-13 | COMP | 2021-02-19 | COMP | 2021-02-17 | COMP | Rule 16 | 126 | 248 | 48 | 5 | 26 |  | 447
15783 | 2019-05-08 | 2019-11-21 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2021-06-08 | COMP | 2021-07-12 | COMP | Rule 16 | 138 | 79 | 24 | 1 | 287 | 24 | 548
15975 | 2019-05-08 | 2019-12-04 | 2020-10-16 | 2020-10-16 | COMP | 2020-11-18 | COMP | 2021-01-25 | COMP | 2021-02-02 | NOTN | 2021-02-23 | COMP | Rule 16 | 145 | 222 | 23 | 44 |  |  | 451
17039 | 2019-05-08 | 2020-01-28 | 2020-03-24 | 2020-03-24 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-06-22 | COMP | 2020-07-17 | COMP | Rule 15/16 | 181 | 40 | 36 | 1 | 29 | 20 | 302
18505 | 2019-05-08 | 2020-03-26 | 2020-05-28 | 2020-05-28 | COMP | 2020-08-27 | COMP | 2020-11-25 | COMP | 2021-05-17 | COMP | 2021-06-30 | COMP | Rule 16 | 222 | 45 | 66 | 63 | 118 | 32 | 541
4243 | 2019-05-09 | 2019-10-16 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-12-19 | COMP | 2020-02-19 | COMP | Rule 15/16 | 112 | 7 | 8 | 1 | 31 | 41 | 195
12049 | 2019-05-09 | 2019-05-21 | 2019-06-26 | 2019-06-26 | COMP | 2019-07-01 | COMP | 2019-07-01 | COMP | 2019-10-21 | INPR | 2019-07-06 | COMP | Rule 16 | 9 | 26 | 4 | 1 |  |  | 40
12288 | 2019-05-09 | 2019-05-30 | 2019-09-18 | 2019-09-23 | COMP | 2019-09-25 | NOTN | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-11-08 | COMP | Other | 15 | 78 |  | 3 | 1 | 33 | 129
12309 | 2019-05-09 | 2019-05-30 | 2019-07-02 | 2019-07-02 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2019-12-13 | COMP | 2020-01-03 | COMP | Rule 16 | 15 | 24 | 36 | 1 | 79 | 14 | 164
12315 | 2019-05-09 | 2019-05-30 | 2019-07-08 | 2019-07-17 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2020-01-30 | COMP | 2020-02-07 | COMP | Rule 16 | 15 | 27 | 43 | 1 | 93 | 7 | 188
12325 | 2019-05-09 | 2019-05-31 | 2019-08-20 | 2019-08-20 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-12-19 | COMP | 2020-02-29 | COMP | Rule 16 | 16 | 57 | 36 | 1 | 49 | 48 | 202
12333 | 2019-05-09 | 2019-05-31 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-16 | COMP | 2019-09-26 | COMP | 2019-08-16 | COMP | 2020-01-08 | COMP | Rule 16 | 16 | 42 | 14 | 29 | 0 | 70 | 167
12512 | 2019-05-09 | 2019-06-11 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-30 | COMP | 2019-10-09 | COMP | 2019-12-06 | COMP | 2019-12-30 | COMP | Rule 16 | 23 | 63 | 16 | 8 | 40 | 16 | 161
12802 | 2019-05-09 | 2019-06-24 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2020-03-27 | COMP | 2020-05-05 | COMP | Rule 16 | 32 | 67 | 26 | 1 | 100 | 28 | 249
13096 | 2019-05-09 | 2019-07-10 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-01-14 | COMP | 2020-01-15 | COMP | Rule 16 | 43 | 96 | 24 | 1 | 11 | 2 | 172
13888 | 2019-05-09 | 2019-08-16 | 2019-12-09 | 2019-12-09 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-01-16 | COMP | 2020-02-18 | COMP | Rule 16 | 70 | 78 | 22 | 1 | 6 | 22 | 194
13990 | 2019-05-09 | 2019-08-20 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-13 | COMP | 2020-01-24 | COMP | 2019-12-13 | COMP | 2020-02-05 | COMP | Rule 16 | 72 | 67 | 14 | 28 | 0 | 9 | 186
14047 | 2019-05-09 | 2019-08-22 | 2020-02-03 | 2020-02-03 | COMP | 2020-05-01 | COMP | 2020-06-05 | COMP | 2020-06-01 | COMP | 2020-08-06 | COMP | Rule 16 | 74 | 111 | 64 | 25 | 0 | 45 | 315
14317 | 2019-05-09 | 2019-09-04 | 2019-12-09 | 2019-12-09 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | Rule 16 | 82 | 66 | 43 | 1 | 10 | 1 | 198
14512 | 2019-05-09 | 2019-09-13 | 2019-11-23 | 2019-11-23 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2020-12-15 | COMP | 2021-01-26 | COMP | Rule 16 | 89 | 50 | 54 | 1 | 213 | 28 | 431
14574 | 2019-05-09 | 2019-09-17 | 2019-12-16 | 2019-12-16 | COMP | 2020-03-31 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-07-23 | COMP | Rule 16 | 91 | 62 | 73 | 64 | 1 | 19 | 305
15099 | 2019-05-09 | 2019-10-11 | 2019-10-28 | 2019-10-28 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-02-06 | COMP | 2020-03-19 | COMP | Rule 16 | 109 | 12 | 74 | 1 | 0 | 24 | 216
15108 | 2019-05-09 | 2019-10-14 | 2020-06-03 | 2022-08-24 | COMP | 2022-10-28 | COMP | 2021-04-02 | COMP | 2022-12-22 | COMP | 2023-02-10 | COMP | Rule 15/16 | 110 | 160 | 47 |  | 435 | 34 | 945
16930 | 2019-05-09 | 2020-01-25 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-13 | COMP | 2020-05-29 | COMP | 2020-07-17 | COMP | 2020-07-18 | COMP | Rule 16 | 178 | 68 | 10 | 12 | 36 | 1 | 301
17100 | 2019-05-09 | 2020-01-30 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-01 | COMP | 2020-05-01 | COMP | 2022-01-30 | INPR | 2020-10-09 | COMP | Rule 16 | 182 | 59 | 8 | 1 |  |  | 360
17392 | 2019-05-09 | 2020-02-12 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-17 | COMP | 2020-08-20 | COMP | 2020-06-23 | COMP | 2020-09-15 | COMP | Rule 16 | 191 | 77 | 13 | 47 | 0 | 18 | 342
17673 | 2019-05-09 | 2020-02-25 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-18 | COMP | 2020-07-09 | COMP | 2020-07-20 | COMP | 2020-10-02 | COMP | Rule 16 | 199 | 10 | 51 | 38 | 8 | 54 | 355
19986 | 2019-05-09 | 2020-06-02 | 2020-09-15 | 2020-09-15 | COMP | 2021-05-24 | COMP | 2021-08-20 | COMP |  | INPR | 2023-09-14 | COMP | Rule 16 | 268 | 75 | 173 | 63 |  |  | 1094
21526 | 2019-05-09 | 2020-08-11 | 2020-09-25 | 2020-09-25 | COMP | 2020-11-09 | COMP | 2020-11-09 | COMP | 2022-01-31 | INPR | 2020-11-23 | COMP | Rule 15/16 | 318 | 33 | 32 | 1 |  |  | 390
11777 | 2019-05-10 | 2019-05-10 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-05 | COMP | 2019-09-05 | COMP | 2019-11-25 | COMP | 2020-02-26 | COMP | Rule 16 | 1 | 71 | 12 | 1 | 57 | 62 | 199
11911 | 2019-05-10 | 2019-05-16 | 2019-11-18 | 2019-11-20 | COMP | 2020-02-18 | COMP | 2020-02-26 | COMP | 2023-12-30 | INPR | 2021-04-24 | COMP | Rule 16 | 5 | 129 | 59 | 7 |  |  | 492
11963 | 2019-05-10 | 2019-05-20 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-06 | NOTN | 2019-08-08 | COMP | 2019-08-06 | COMP | 2020-01-07 | COMP | Other | 7 | 54 |  | 4 | 0 | 103 | 165
12218 | 2019-05-10 | 2019-05-28 | 2020-01-22 | 2020-01-22 | COMP | 2020-03-23 | COMP | 2020-05-28 | COMP | 2020-06-05 | COMP | 2020-07-31 | COMP | Rule 15/16 | 12 | 164 | 43 | 48 | 7 | 41 | 310
12219 | 2019-05-10 | 2019-05-28 | 2020-01-22 | 2020-01-22 | COMP | 2020-05-06 | COMP | 2020-08-15 | COMP | 2020-10-29 | COMP | 2020-12-14 | COMP | Rule 15/16 | 12 | 164 | 75 | 72 | 53 | 30 | 402
12220 | 2019-05-10 | 2019-05-28 | 2020-01-22 | 2020-01-22 | COMP | 2020-05-06 | COMP | 2020-12-01 | COMP | 2020-12-01 | COMP | 2021-01-10 | COMP | Rule 15/16 | 12 | 164 | 75 | 145 | 1 | 27 | 419
12221 | 2019-05-10 | 2019-05-28 | 2020-01-22 | 2020-01-22 | COMP | 2020-05-05 | COMP | 2020-05-12 | COMP | 2021-02-02 | COMP | 2021-02-24 | COMP | Rule 16 | 12 | 164 | 74 | 6 | 183 | 16 | 450
12331 | 2019-05-10 | 2019-05-31 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-21 | COMP | 2019-11-04 | COMP | 2020-03-12 | COMP | 2020-03-18 | COMP | Rule 16 | 15 | 50 | 9 | 53 | 87 | 5 | 214
12351 | 2019-05-10 | 2019-06-03 | 2020-06-12 | 2021-01-12 | COMP | 2021-03-03 | COMP | 2021-03-18 | COMP | 2021-03-04 | COMP | 2021-04-30 | COMP | Rule 15/16 | 16 | 260 | 35 | 12 | 0 | 32 | 497
12881 | 2019-05-10 | 2019-06-26 | 2019-07-13 | 2019-07-13 | COMP | 2019-07-23 | COMP | 2019-07-23 | NOTN | 2019-07-22 | COMP | 2019-07-25 | COMP | Rule 16 | 33 | 12 | 7 |  |  |  | 53
12991 | 2019-05-10 | 2019-07-03 | 2019-11-06 | 2019-11-06 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2022-01-30 | INPR | 2020-10-29 | COMP | Rule 16 | 38 | 89 | 57 | 1 |  |  | 373
13653 | 2019-05-10 | 2019-08-06 | 2019-10-14 | 2020-11-23 | COMP | 2020-12-07 | COMP | 2021-07-06 | COMP | 2021-11-02 | COMP | 2021-11-19 | COMP | Rule 16 | 61 | 49 | 9 | 146 | 85 | 13 | 638
14399 | 2019-05-10 | 2019-09-09 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-25 | COMP | 2020-06-02 | COMP | 2020-06-08 | COMP | 2020-07-20 | COMP | Rule 16 | 84 | 108 | 8 | 70 | 5 | 31 | 301
14654 | 2019-05-10 | 2019-09-20 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-27 | COMP | 2019-12-30 | COMP | 2020-02-04 | COMP | 2020-02-24 | COMP | Rule 16 | 93 | 35 | 33 | 2 | 25 | 14 | 197
14838 | 2019-05-10 | 2019-09-30 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-23 | COMP | 2020-02-03 | COMP | 2020-02-07 | COMP | 2020-03-12 | COMP | Rule 16 | 99 | 54 | 25 | 8 | 5 | 24 | 210
15197 | 2019-05-10 | 2019-10-18 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-18 | COMP | 2020-05-04 | COMP | 2020-06-08 | COMP | 2020-06-23 | COMP | Rule 16 | 113 | 90 | 13 | 34 | 25 | 12 | 282
15207 | 2019-05-10 | 2019-10-21 | 2019-12-12 | 2019-12-12 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP |  | INPR | 2020-04-08 | COMP | Rule 16 | 114 | 36 | 42 | 1 |  |  | 229
15876 | 2019-05-10 | 2019-11-25 | 2020-01-27 | 2020-01-27 | COMP | 2020-10-02 | COMP | 2020-12-04 | COMP | 2021-12-14 | COMP | 2022-01-21 | COMP | Rule 16 | 138 | 41 | 177 | 43 | 258 | 28 | 680
16832 | 2019-05-10 | 2020-01-17 | 2020-06-04 | 2020-07-27 | COMP | 2020-07-30 | COMP | 2020-08-11 | COMP | 2020-09-24 | COMP | 2020-10-29 | COMP | Rule 15/16 | 173 | 97 | 4 | 9 | 32 | 26 | 373
18386 | 2019-05-10 | 2020-03-23 | 2020-07-03 | 2020-07-13 | COMP | 2020-11-16 | COMP |  | REQD |  | REQD | 2022-09-13 | COMP | Rule 15/16 | 217 | 74 | 89 |  |  |  | 842
11951 | 2019-05-11 | 2019-05-20 | 2019-08-06 | 2019-10-07 | COMP | 2019-10-10 | COMP | 2019-09-17 | COMP | 2019-10-22 | COMP | 2019-12-03 | COMP | Rule 16 | 6 | 55 | 4 |  | 26 | 28 | 141
13737 | 2019-05-11 | 2019-08-07 | 2019-12-24 | 2019-12-24 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | 2020-03-09 | COMP | 2020-04-28 | COMP | Rule 16 | 61 | 96 | 21 | 1 | 31 | 37 | 242
16250 | 2019-05-11 | 2019-12-17 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-06-23 | COMP | 2020-07-24 | COMP | Rule 16 | 151 | 58 | 6 | 1 | 69 | 24 | 304
12809 | 2019-05-12 | 2019-06-24 | 2019-08-08 | 2019-11-27 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-02-21 | COMP | 2020-02-27 | COMP | Rule 16 | 30 | 33 | 46 | 1 | 12 | 5 | 199
4172 | 2019-05-13 | 2019-05-23 | 2019-09-23 | 2019-09-23 | COMP | 2020-03-02 | COMP | 2020-03-09 | COMP | 2020-03-05 | COMP | 2020-03-25 | COMP | Rule 16 | 9 | 85 | 109 | 6 | 0 | 13 | 218
12170 | 2019-05-13 | 2019-05-25 | 2019-06-22 | 2019-06-22 | COMP | 2019-06-26 | COMP | 2019-06-26 | INPR | 2022-06-18 | REQD | 2020-02-22 | COMP | Rule 16 | 10 | 19 | 3 |  |  |  | 195
12383 | 2019-05-13 | 2019-06-04 | 2019-07-11 | 2019-07-11 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-04-26 | INPR | 2019-12-27 | COMP | Rule 16 | 16 | 27 | 72 | 1 |  |  | 158
12670 | 2019-05-13 | 2019-06-18 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2021-10-23 | INPR | 2020-09-02 | COMP | Rule 16 | 26 | 85 | 49 | 1 |  |  | 332
12759 | 2019-05-13 | 2019-06-20 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-10 | COMP | 2020-01-16 | COMP | 2020-01-08 | COMP | 2020-01-24 | COMP | Rule 15/16 | 28 | 91 | 29 | 26 | 0 | 6 | 176
12791 | 2019-05-13 | 2019-06-22 | 2019-10-08 | 2019-10-08 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-06-16 | COMP | 2020-07-31 | COMP | Rule 15/16 | 29 | 75 | 100 | 1 | 74 | 34 | 309
12852 | 2019-05-13 | 2019-06-25 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-20 | COMP | 2019-10-02 | COMP | 2020-03-01 | INPR | 2019-11-19 | COMP | Rule 16 | 31 | 32 | 9 | 31 |  |  | 133
12894 | 2019-05-13 | 2019-06-27 | 2019-09-14 | 2019-09-14 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-10-28 | COMP | 2020-12-04 | COMP | Rule 16 | 33 | 55 | 173 | 1 | 112 | 25 | 395
12902 | 2019-05-13 | 2019-06-28 | 2019-08-30 | 2019-08-30 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-10-28 | COMP | 2020-12-04 | COMP | Rule 16 | 34 | 45 | 183 | 1 | 112 | 25 | 395
13286 | 2019-05-13 | 2019-07-19 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2020-05-04 | COMP | 2020-05-10 | COMP | Rule 16 | 48 | 46 | 23 | 1 | 132 | 5 | 250
13296 | 2019-05-13 | 2019-07-19 | 2019-11-22 | 2019-11-22 | COMP | 2020-02-25 | COMP | 2020-05-27 | COMP | 2020-05-21 | COMP | 2020-06-18 | COMP | Rule 16 | 48 | 89 | 62 | 66 | 0 | 17 | 278
13347 | 2019-05-13 | 2019-07-22 | 2019-10-12 | 2019-10-12 | COMP | 2019-10-21 | COMP | 2019-10-21 | NOTN | 2022-05-23 | COMP | 2022-06-01 | COMP | Rule 16 | 49 | 59 | 6 |  |  |  | 770
13418 | 2019-05-13 | 2019-07-24 | 2019-10-28 | 2019-11-14 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-12-26 | COMP | 2020-03-12 | COMP | Rule 16 | 51 | 68 | 4 | 1 | 25 | 53 | 209
13465 | 2019-05-13 | 2019-07-26 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-01-27 | COMP | 2020-02-01 | COMP | Rule 16 | 53 | 41 | 68 | 1 | 18 | 5 | 181
14568 | 2019-05-13 | 2019-09-17 | 2019-12-09 | 2019-12-09 | COMP | 2020-03-26 | COMP | 2020-05-12 | COMP | 2020-04-23 | COMP | 2020-05-22 | COMP | Rule 16 | 89 | 57 | 75 | 34 | 0 | 9 | 260
14828 | 2019-05-13 | 2019-09-30 | 2019-12-02 | 2021-07-24 | COMP | 2021-11-18 | COMP | 2022-06-13 | COMP | 2022-06-09 | COMP | 2022-07-07 | COMP | Rule 15/16 | 98 | 43 | 82 | 143 | 0 | 17 | 794
14864 | 2019-05-13 | 2019-10-01 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-01-15 | COMP | Rule 16 | 99 | 24 | 11 | 1 | 1 | 39 | 170
14901 | 2019-05-13 | 2019-10-02 | 2020-04-01 | 2020-04-01 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-08-14 | COMP | 2020-10-07 | COMP | Rule 15/16 | 100 | 124 | 52 | 1 | 46 | 38 | 356
15058 | 2019-05-13 | 2019-10-10 | 2019-12-13 | 2019-12-13 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2022-11-29 | COMP | 2022-05-11 | COMP | Rule 16 | 106 | 44 | 87 | 1 | 659 |  | 756
15216 | 2019-05-13 | 2019-10-21 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-01-30 | COMP | 2020-02-02 | COMP | Rule 16 | 113 | 39 | 14 | 1 | 17 | 2 | 181
15248 | 2019-05-13 | 2019-10-22 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-09-01 | COMP | 2020-09-23 | COMP | Rule 16 | 114 | 127 | 23 | 1 | 70 | 16 | 346
15398 | 2019-05-13 | 2019-10-30 | 2019-11-19 | 2019-11-19 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2019-12-12 | COMP | 2020-01-09 | COMP | Rule 16 | 120 | 14 | 26 | 1 | 0 | 9 | 166
15714 | 2019-05-13 | 2019-11-18 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-06 | COMP | 2020-02-26 | COMP | 2020-03-09 | COMP | 2020-04-03 | COMP | Rule 16 | 132 | 49 | 6 | 14 | 9 | 20 | 225
15946 | 2019-05-13 | 2019-12-02 | 2020-05-15 | 2020-07-10 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2021-05-24 | COMP | 2021-07-14 | COMP | Rule 15/16 | 140 | 116 | 19 | 1 | 201 | 36 | 547
16072 | 2019-05-13 | 2019-12-08 | 2020-04-27 | 2020-04-27 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP |  | INPR | 2021-02-04 | COMP | Rule 16 | 144 | 97 | 37 | 1 |  |  | 436
16255 | 2019-05-13 | 2019-12-18 | 2020-05-14 | 2020-05-14 | COMP | 2020-06-05 | COMP | 2020-10-20 | COMP | 2020-10-21 | COMP | 2020-11-24 | COMP | Rule 16 | 152 | 103 | 16 | 97 | 2 | 24 | 389
16565 | 2019-05-13 | 2020-01-08 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-02-25 | COMP | 2020-03-13 | COMP | Rule 16 | 165 | 16 | 20 | 1 | 0 | 12 | 210
18722 | 2019-05-13 | 2020-04-03 | 2020-05-11 | 2020-05-18 | COMP | 2020-07-27 | COMP | 2020-09-29 | COMP | 2020-08-11 | COMP | 2020-10-21 | COMP | Rule 16 | 225 | 27 | 50 | 46 | 0 | 17 | 366
4170 | 2019-05-14 | 2019-05-20 | 2019-06-21 | 2019-06-21 | COMP | 2019-06-24 | COMP | 2019-07-02 | COMP | 2019-07-27 | COMP | 2019-08-12 | COMP | Rule 16 | 5 | 24 | 2 | 7 | 18 | 11 | 63
12191 | 2019-05-14 | 2019-05-28 | 2019-09-23 | 2019-09-23 | COMP | 2019-11-12 | COMP | 2020-07-07 | COMP | 2020-06-10 | COMP | 2020-08-04 | COMP | Rule 16 | 10 | 83 | 36 | 164 | 0 | 21 | 310
12193 | 2019-05-14 | 2019-05-28 | 2019-06-29 | 2019-06-29 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP | 2020-01-19 | INPR | 2019-09-17 | COMP | Rule 15/16 | 10 | 24 | 39 | 1 |  |  | 88
12280 | 2019-05-14 | 2019-05-30 | 2019-07-29 | 2019-07-29 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2020-05-25 | COMP | 2020-06-03 | COMP | Rule 16 | 12 | 42 | 51 | 1 | 157 | 7 | 266
12513 | 2019-05-14 | 2019-06-11 | 2020-01-16 | 2020-07-29 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-08-24 | COMP | Rule 16 | 20 | 151 | 4 | 1 | 1 | 16 | 324
12582 | 2019-05-14 | 2019-06-14 | 2019-07-26 | 2019-08-16 | COMP | 2019-09-10 | COMP | 2019-09-13 | COMP | 2019-10-28 | COMP | 2019-11-25 | COMP | Rule 16 | 23 | 30 | 17 | 4 | 32 | 20 | 136
12594 | 2019-05-14 | 2019-06-14 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-17 | COMP | 2019-08-09 | COMP | 2019-11-01 | COMP | 2019-11-02 | COMP | Rule 16 | 23 | 17 | 7 | 18 | 60 | 1 | 121
12597 | 2019-05-14 | 2019-06-14 | 2019-08-06 | 2019-08-06 | COMP | 2019-10-29 | COMP | 2020-01-07 | COMP | 2020-01-08 | COMP | 2020-02-17 | COMP | Rule 16 | 23 | 37 | 60 | 46 | 2 | 27 | 190
12645 | 2019-05-14 | 2019-06-17 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-12 | NOTN | 2019-08-22 | COMP | 2019-08-22 | COMP | 2019-10-07 | COMP | Other | 24 | 40 |  | 9 | 1 | 32 | 102
12724 | 2019-05-14 | 2019-06-20 | 2019-09-27 | 2019-09-27 | COMP | 2019-10-15 | COMP | 2020-02-04 | COMP | 2019-12-26 | COMP | 2020-03-20 | COMP | Rule 16 | 27 | 70 | 13 | 75 | 0 | 33 | 214
12844 | 2019-05-14 | 2019-06-25 | 2020-01-07 | 2020-01-07 | COMP | 2020-05-05 | COMP | 2020-05-11 | COMP | 2020-05-22 | COMP | 2020-07-09 | COMP | Rule 16 | 30 | 134 | 84 | 5 | 10 | 34 | 292
13135 | 2019-05-14 | 2019-07-11 | 2019-09-13 | 2019-09-13 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-10-18 | COMP | Rule 16 | 41 | 46 | 8 | 1 | 1 | 19 | 111
13392 | 2019-05-14 | 2019-07-24 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2021-05-25 | COMP | 2021-06-29 | COMP | Rule 16 | 50 | 92 | 31 | 1 | 342 | 25 | 536
13395 | 2019-05-14 | 2019-07-23 | 2019-10-02 | 2019-10-02 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-06-25 | COMP | 2020-07-06 | COMP | Rule 16 | 49 | 51 | 55 | 1 | 130 | 8 | 289
13516 | 2019-05-14 | 2019-07-29 | 2020-04-23 | 2020-04-23 | COMP | 2021-03-01 | COMP | 2021-03-31 | COMP | 2021-08-17 | COMP | 2022-01-24 | COMP | Rule 15/16 | 53 | 186 | 214 | 23 | 98 | 110 | 679
13604 | 2019-05-14 | 2019-08-02 | 2020-03-02 | 2020-04-13 | COMP | 2020-06-16 | COMP | 2020-12-15 | COMP | 2021-07-01 | COMP | 2021-09-03 | COMP | Rule 16 | 57 | 144 | 46 | 127 | 138 | 46 | 583
13628 | 2019-05-14 | 2019-08-02 | 2020-01-31 | 2020-01-31 | COMP | 2020-04-15 | NOTN | 2020-04-15 | COMP | 2020-05-26 | COMP | 2020-07-31 | COMP | Other | 57 | 124 |  | 53 | 29 | 49 | 308
13649 | 2019-05-14 | 2019-08-05 | 2019-11-13 | 2019-11-13 | COMP | 2019-12-10 | COMP | 2020-01-06 | COMP | 2021-03-17 | COMP | 2021-04-21 | COMP | Rule 16 | 58 | 71 | 18 | 18 | 302 | 26 | 488
13670 | 2019-05-14 | 2019-08-05 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2020-02-06 | COMP | 2020-02-07 | COMP | Rule 16 | 58 | 40 | 24 | 1 | 65 | 2 | 185
13898 | 2019-05-14 | 2019-08-15 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-25 | NOTN | 2020-03-27 | COMP | 2020-12-15 | COMP | 2021-03-12 | COMP | Other | 66 | 116 |  | 39 | 183 | 60 | 460
14029 | 2019-05-14 | 2019-08-21 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-09 | COMP | 2019-10-09 | COMP | 2019-12-03 | COMP | 2019-12-16 | COMP | Rule 16 | 70 | 20 | 16 | 1 | 37 | 10 | 149
14134 | 2019-05-14 | 2019-08-26 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-03 | COMP | 2020-03-09 | COMP | 2020-03-01 | COMP | 2020-03-10 | COMP | Rule 16 | 73 | 63 | 6 | 66 | 0 | 2 | 206
14432 | 2019-05-14 | 2019-09-09 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-01-27 | COMP | 2020-03-13 | COMP | Rule 16 | 82 | 82 | 9 | 1 | 6 | 34 | 209
14433 | 2019-05-14 | 2019-09-09 | 2020-01-29 | 2020-01-29 | COMP | 2020-02-10 | COMP | 2020-03-12 | COMP | 2020-02-05 | COMP | 2020-04-13 | COMP | Rule 16 | 82 | 97 | 9 | 23 | 0 | 23 | 230
15846 | 2019-05-14 | 2019-11-24 | 2020-04-27 | 2020-04-27 | COMP | 2020-06-18 | COMP | 2020-09-03 | COMP | 2021-03-19 | COMP | 2021-04-28 | COMP | Rule 16 | 135 | 105 | 38 | 56 | 134 | 29 | 493
17694 | 2019-05-14 | 2020-02-24 | 2020-05-22 | 2020-05-22 | COMP | 2020-12-16 | COMP | 2021-01-04 | COMP | 2021-01-04 | COMP | 2021-04-22 | COMP | Rule 16 | 195 | 65 | 144 | 12 | 1 | 77 | 489
17703 | 2019-05-14 | 2020-02-25 | 2020-07-01 | 2020-08-31 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-05-28 | COMP | 2021-10-30 | COMP | Rule 16 | 196 | 91 | 21 | 1 | 167 | 108 | 622
26725 | 2019-05-14 | 2021-03-31 | 2021-04-28 | 2021-04-28 | COMP | 2021-07-19 | COMP | 2021-09-20 | COMP | 2021-09-27 | COMP | 2021-11-10 | COMP | Rule 15/16 | 473 | 21 | 57 | 45 | 6 | 33 | 630
4287 | 2019-05-15 | 2020-04-08 |  |  | REQD |  | REQD |  | REQD |  | REQD | 2020-05-21 | COMP | Other | 226 | [5 empty] | 257
12255 | 2019-05-15 | 2019-05-29 | 2019-08-06 | 2019-08-06 | COMP | 2019-08-09 | NOTN | 2020-05-12 | COMP | 2023-08-28 | COMP | 2023-09-08 | COMP | Other | 10 | 49 |  | 193 | 829 | 9 | 1086
12267 | 2019-05-15 | 2019-05-29 | 2019-10-23 | 2021-12-14 | COMP | 2021-12-17 | COMP | 2021-12-17 | COMP | 2022-08-09 | COMP | 2022-08-26 | COMP | Rule 16 | 10 | 104 | 4 | 1 | 163 | 14 | 828
12273 | 2019-05-15 | 2019-05-29 | 2020-03-07 | 2022-09-21 | COMP | 2022-12-09 | COMP | 2023-03-16 | COMP | 2023-04-14 | COMP | 2023-05-01 | COMP | Rule 16 | 10 | 194 | 55 | 66 | 22 | 12 | 996
12394 | 2019-05-15 | 2019-06-05 | 2019-07-18 | 2019-07-18 | COMP | 2019-07-25 | NOTN | 2019-08-04 | COMP | 2019-08-13 | COMP | 2019-10-08 | COMP | Other | 15 | 31 |  | 12 | 7 | 40 | 102
12421 | 2019-05-15 | 2019-06-05 | 2019-10-22 | 2019-10-22 | COMP | 2019-10-31 | COMP | 2020-06-17 | COMP | 2020-06-03 | COMP | 2020-06-22 | COMP | Rule 15/16 | 15 | 98 | 8 | 157 | 0 | 4 | 278
12468 | 2019-05-15 | 2019-06-10 | 2019-09-11 | 2019-09-11 | COMP | 2019-09-12 | NOTN | 2019-09-12 | COMP | 2019-09-12 | COMP | 2019-12-17 | COMP | Other | 18 | 66 |  | 2 | 1 | 66 | 149
12560 | 2019-05-15 | 2019-06-13 | 2019-10-12 | 2019-10-12 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2021-03-27 | INPR | 2020-02-29 | COMP | Other | 21 | 85 | 75 | 1 |  |  | 198
12840 | 2019-05-15 | 2019-06-24 | 2019-09-17 | 2019-09-17 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | Rule 16 | 28 | 60 | 12 | 1 | 14 | 2 | 112
12879 | 2019-05-15 | 2019-06-26 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-28 | COMP | 2019-10-28 | COMP | 2020-02-24 | COMP | 2020-06-11 | COMP | Rule 16 | 30 | 67 | 21 | 1 | 79 | 78 | 271
13055 | 2019-05-15 | 2019-07-08 | 2019-11-17 | 2019-11-17 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-01-27 | COMP | 2020-03-03 | COMP | Rule 16 | 37 | 93 | 20 | 1 | 27 | 26 | 200
13315 | 2019-05-15 | 2019-07-20 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-02-11 | COMP | 2020-02-18 | COMP | Rule 16 | 46 | 67 | 15 | 1 | 60 | 5 | 190
13362 | 2019-05-15 | 2019-07-23 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-12 | COMP | 2019-12-27 | COMP | 2020-03-19 | COMP | 2020-04-02 | COMP | Rule 16 | 48 | 79 | 21 | 11 | 57 | 11 | 222
13508 | 2019-05-15 | 2019-07-29 | 2019-09-30 | 2019-12-12 | COMP | 2019-12-18 | COMP | 2019-11-13 | COMP | 2019-12-18 | COMP | 2020-03-12 | COMP | Rule 15/16 | 52 | 45 | 5 |  | 24 | 58 | 207
13585 | 2019-05-15 | 2019-07-31 | 2019-11-16 | 2019-11-16 | COMP | 2021-02-25 | COMP | 2021-02-25 | COMP | 2021-02-25 | COMP | 2021-04-05 | COMP | Rule 16 | 54 | 76 | 319 | 1 | 1 | 28 | 475
13658 | 2019-05-15 | 2019-08-05 | 2019-10-26 | 2019-10-26 | COMP | 2019-11-20 | COMP | 2019-11-20 | NOTN | 2020-01-08 | COMP | 2020-01-14 | COMP | Rule 16 | 57 | 59 | 17 |  |  |  | 167
13853 | 2019-05-15 | 2019-08-13 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-11-12 | COMP | 2019-11-25 | COMP | Rule 16 | 63 | 38 | 11 | 1 | 16 | 10 | 135
13932 | 2019-05-15 | 2019-08-16 | 2019-09-30 | 2019-09-30 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-06-29 | COMP | 2020-07-24 | COMP | Rule 16 | 66 | 31 | 189 | 1 | 0 | 19 | 302
13955 | 2019-05-15 | 2019-08-19 | 2019-10-10 | 2019-10-10 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-07-16 | COMP | 2021-04-27 | COMP | Rule 16 | 67 | 38 | 192 | 1 | 2 | 196 | 491
14021 | 2019-05-15 | 2019-08-22 | 2019-10-16 | 2019-10-23 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-02-11 | COMP | 2020-02-13 | COMP | Rule 16 | 70 | 39 | 14 | 1 | 61 | 3 | 188
14144 | 2019-05-15 | 2019-08-27 | 2020-04-01 | 2020-04-01 | COMP | 2020-10-20 | COMP | 2021-08-19 | COMP | 2021-08-06 | COMP | 2021-09-10 | COMP | Rule 15/16 | 73 | 149 | 143 | 209 | 0 | 16 | 586
14154 | 2019-05-15 | 2019-08-28 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-23 | COMP | 2020-06-09 | INPR | 2020-06-30 | COMP | 2020-03-03 | COMP | Rule 16 | 74 | 85 | 16 |  |  |  | 200
14408 | 2019-05-15 | 2019-09-09 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2022-02-26 | INPR | 2020-07-28 | COMP | Rule 16 | 81 | 87 | 16 | 1 |  |  | 304
14598 | 2019-05-15 | 2019-09-18 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-12-19 | COMP | Rule 16 | 88 | 13 | 10 | 1 | 1 | 42 | 151
14619 | 2019-05-15 | 2019-09-20 | 2019-12-11 | 2019-12-11 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-05-15 | COMP | 2020-06-27 | COMP | Rule 16 | 90 | 56 | 33 | 1 | 77 | 30 | 282
15015 | 2019-05-15 | 2019-10-08 | 2020-02-14 | 2020-02-14 | COMP | 2020-02-26 | COMP | 2020-03-09 | COMP | 2020-02-27 | COMP | 2020-03-26 | COMP | Rule 15/16 | 102 | 88 | 8 | 9 | 0 | 14 | 217
15301 | 2019-05-15 | 2019-10-25 | 2019-12-18 | 2019-12-18 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-04-06 | COMP | 2020-04-08 | COMP | Rule 16 | 115 | 36 | 53 | 1 | 23 | 3 | 226
16031 | 2019-05-15 | 2019-12-06 | 2020-06-25 | 2020-09-22 | COMP | 2020-10-02 | COMP | 2020-10-13 | COMP | 2020-12-30 | COMP | 2021-04-09 | COMP | Rule 15/16 | 142 | 140 | 9 | 8 | 53 | 70 | 479
16290 | 2019-05-15 | 2019-12-19 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-08-04 | COMP | 2020-09-21 | COMP | Rule 16 | 151 | 72 | 15 | 1 | 74 | 34 | 342
16803 | 2019-05-15 | 2020-01-16 | 2020-01-30 | 2020-01-30 | COMP | 2020-03-20 | COMP | 2020-03-23 | COMP | 2020-01-16 | COMP | 2020-05-05 | COMP | Rule 16 | 169 | 10 | 36 | 2 | 0 | 32 | 245
16831 | 2019-05-15 | 2020-01-17 | 2020-04-11 | 2020-04-11 | COMP | 2020-04-27 | COMP | 2020-07-09 | COMP | 2020-12-10 | COMP | 2021-02-14 | COMP | Rule 15/16 | 170 | 59 | 11 | 53 | 107 | 44 | 440
17652 | 2019-05-15 | 2020-02-24 | 2020-04-12 | 2020-04-12 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | Rule 16 | 194 | 35 | 43 | 1 | 55 | 1 | 325
18421 | 2019-05-15 | 2020-03-23 | 2020-08-06 | 2020-08-06 | COMP | 2020-11-05 | COMP | 2020-11-05 | COMP | 2020-11-30 | COMP | 2020-12-16 | COMP | Rule 16 | 214 | 98 | 65 | 1 | 15 | 13 | 401
4208 | 2019-05-16 | 2019-07-18 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-16 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-11-13 | COMP | Rule 16 | 44 | 21 | 22 |  | 1 | 53 | 126
12127 | 2019-05-16 | 2019-05-23 | 2019-06-28 | 2019-06-28 | COMP | 2019-09-11 | COMP | 2019-09-11 | NOTN | 2019-12-04 | COMP | 2019-12-13 | COMP | Rule 16 | 6 | 26 | 52 |  |  |  | 146
12174 | 2019-05-16 | 2019-05-29 | 2019-10-04 | 2019-10-04 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2021-02-27 | INPR | 2020-02-19 | COMP | Rule 16 | 9 | 91 | 21 | 1 |  |  | 190
12187 | 2019-05-16 | 2019-05-28 | 2019-10-14 | 2019-10-14 | COMP | 2020-01-15 | COMP | 2020-01-15 | COMP | 2020-04-10 | COMP | 2020-03-12 | COMP | Rule 16 | 8 | 98 | 63 | 1 | 61 |  | 206
12295 | 2019-05-16 | 2019-05-31 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-24 | COMP | 2019-11-04 | COMP | 2020-02-05 | COMP | 2020-02-21 | COMP | Rule 16 | 11 | 90 | 14 | 8 | 62 | 12 | 192
12329 | 2019-05-16 | 2019-05-31 | 2020-03-10 | 2020-09-04 | COMP | 2020-11-13 | COMP | 2021-01-27 | COMP | 2020-11-18 | COMP | 2021-08-04 | COMP | Rule 15/16 | 11 | 194 | 49 | 49 | 0 | 133 | 559
12445 | 2019-05-16 | 2019-06-06 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2021-02-27 | INPR | 2020-02-06 | COMP | Rule 15/16 | 15 | 95 | 10 | 1 |  |  | 182
12526 | 2019-05-16 | 2019-06-11 | 2019-08-05 | 2019-08-05 | COMP | 2019-10-15 | COMP | 2019-11-13 | COMP | 2020-02-04 | COMP | 2020-02-28 | COMP | Rule 16 | 18 | 39 | 51 | 21 | 55 | 18 | 197
12693 | 2019-05-16 | 2019-06-19 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-30 | COMP | 2020-01-09 | COMP | 2020-08-04 | COMP | 2020-09-26 | COMP | Rule 16 | 24 | 72 | 23 | 47 | 146 | 38 | 345
13070 | 2019-05-16 | 2019-07-09 | 2019-11-26 | 2019-12-06 | COMP | 2019-12-27 | COMP | 2020-05-26 | COMP | 2020-05-22 | COMP | 2020-09-18 | COMP | Rule 16 | 37 | 99 | 15 | 104 | 0 | 83 | 340
13073 | 2019-05-16 | 2019-07-09 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-16 | COMP | 2019-10-09 | COMP | 2019-12-10 | COMP | 2020-01-09 | COMP | Rule 16 | 37 | 41 | 9 | 18 | 42 | 21 | 163
13394 | 2019-05-16 | 2019-07-23 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2020-03-03 | COMP | 2020-05-04 | COMP | Rule 16 | 47 | 49 | 17 | 1 | 89 | 45 | 243
13453 | 2019-05-16 | 2019-07-25 | 2019-09-12 | 2020-02-11 | COMP | 2020-06-08 | COMP | 2020-07-14 | COMP | 2021-10-05 | COMP | 2022-03-16 | COMP | Rule 16 | 49 | 35 | 83 | 27 | 310 | 112 | 713
13655 | 2019-05-16 | 2019-08-06 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-14 | COMP | 2020-10-23 | COMP | 2020-11-23 | COMP | 2020-12-15 | COMP | Rule 16 | 57 | 44 | 6 | 261 | 21 | 15 | 399
13927 | 2019-05-16 | 2019-08-17 | 2020-01-17 | 2020-01-17 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2021-03-27 | INPR | 2020-03-24 | COMP | Rule 16 | 65 | 104 | 20 | 1 |  |  | 214
14120 | 2019-05-16 | 2019-08-26 | 2019-12-31 | 2019-12-31 | COMP | 2020-02-05 | COMP | 2020-12-02 | COMP |  | INPR | 2021-01-04 | COMP | Rule 16 | 71 | 87 | 25 | 210 |  |  | 411
14312 | 2019-05-16 | 2019-09-04 | 2019-11-21 | 2019-11-21 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-03-02 | COMP | 2020-03-16 | COMP | Rule 16 | 77 | 56 | 52 | 1 | 16 | 11 | 208
14700 | 2019-05-16 | 2019-09-23 | 2019-12-13 | 2019-12-13 | COMP | 2020-10-21 | COMP | 2021-02-12 | COMP | 2021-05-07 | COMP | 2021-06-03 | COMP | Rule 16 | 90 | 57 | 218 | 77 | 60 | 19 | 516
14741 | 2019-05-16 | 2019-09-25 | 2019-11-13 | 2019-11-14 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-01-02 | COMP | 2020-01-22 | COMP | Rule 16 | 92 | 35 | 6 | 1 | 27 | 14 | 171
15016 | 2019-05-16 | 2019-10-09 | 2020-05-28 | 2020-06-12 | COMP | 2021-02-01 | COMP | 2021-03-09 | COMP | 2021-03-29 | COMP | 2021-05-14 | COMP | Rule 15/16 | 102 | 159 | 160 | 26 | 15 | 35 | 503
15017 | 2019-05-16 | 2019-10-09 | 2020-06-13 | 2020-06-13 | COMP | 2021-02-05 | COMP | 2021-08-30 | COMP | 2021-09-04 | COMP | 2021-11-23 | COMP | Rule 15/16 | 102 | 170 | 163 | 144 | 5 | 55 | 636
15593 | 2019-05-16 | 2019-11-08 | 2020-03-01 | 2020-03-01 | COMP | 2020-03-30 | COMP | 2020-04-14 | COMP | 2020-04-03 | COMP | 2020-06-23 | COMP | Rule 16 | 124 | 74 | 21 | 12 | 0 | 50 | 278
16299 | 2019-05-16 | 2019-12-19 | 2020-04-08 | 2020-04-08 | COMP | 2021-05-03 | COMP | 2021-05-11 | COMP | 2021-10-05 | COMP | 2022-01-28 | COMP | Rule 16 | 150 | 76 | 270 | 7 | 103 | 80 | 681
16334 | 2019-05-16 | 2019-12-20 | 2020-03-10 | 2020-03-10 | COMP | 2020-04-09 | COMP | 2020-04-09 | COMP | 2020-04-21 | COMP | 2020-05-11 | COMP | Rule 16 | 151 | 54 | 23 | 1 | 9 | 15 | 248
16426 | 2019-05-16 | 2019-12-30 | 2020-02-12 | 2020-03-12 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2021-04-24 | INPR | 2020-04-04 | COMP | Rule 16 | 156 | 31 | 5 | 1 |  |  | 222
18951 | 2019-05-16 | 2020-04-13 | 2020-09-24 | 2020-09-24 | COMP | 2020-12-21 | COMP |  | REQD |  | REQD | 2021-09-14 | COMP | Rule 15/16 | 228 | 117 | 60 |  |  |  | 587
21169 | 2019-05-16 | 2020-07-24 | 2020-08-11 | 2020-08-11 | COMP | 2020-08-17 | COMP | 2020-10-19 | COMP | 2020-10-29 | COMP | 2020-12-15 | COMP | Rule 16 | 301 | 13 | 5 | 45 | 9 | 31 | 399
12327 | 2019-05-17 | 2019-05-31 | 2019-10-14 | 2019-10-14 | COMP | 2019-12-23 | COMP | 2020-01-08 | COMP | 2020-05-15 | COMP | 2020-07-16 | COMP | Rule 16 | 10 | 95 | 48 | 11 | 91 | 44 | 294
12387 | 2019-05-17 | 2019-06-03 | 2020-05-08 | 2020-05-08 | COMP | 2021-02-25 | COMP | 2021-07-29 | COMP | 2021-10-26 | COMP | 2021-12-15 | COMP | Rule 15/16 | 11 | 236 | 201 | 109 | 63 | 34 | 649
12440 | 2019-05-17 | 2019-06-06 | 2019-08-26 | 2019-08-26 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | 2019-09-17 | COMP | 2019-10-07 | COMP | Rule 16 | 14 | 57 | 13 | 1 | 4 | 15 | 99
12544 | 2019-05-17 | 2019-06-11 | 2019-10-12 | 2019-10-12 | COMP | 2019-11-04 | COMP | 2019-11-05 | COMP | 2020-04-26 | INPR | 2020-01-08 | COMP | Rule 16 | 17 | 87 | 16 | 2 |  |  | 161
12573 | 2019-05-17 | 2019-06-13 | 2019-07-18 | 2019-07-18 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | Rule 16 | 19 | 25 | 15 | 1 | 44 | 1 | 100
13065 | 2019-05-17 | 2019-07-08 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-26 | COMP | 2019-09-25 | COMP | 2019-11-26 | COMP | 2019-12-06 | COMP | Rule 16 | 35 | 43 | 16 |  | 44 | 7 | 140
13210 | 2019-05-17 | 2019-07-16 | 2019-08-27 | 2019-08-27 | COMP | 2019-09-12 | COMP | 2019-09-23 | COMP | 2019-10-21 | COMP | 2019-11-19 | COMP | Rule 16 | 41 | 31 | 12 | 8 | 21 | 21 | 129
13213 | 2019-05-17 | 2019-07-16 | 2019-12-13 | 2019-12-13 | COMP | 2020-06-29 | NOTN | 2020-07-16 | COMP | 2020-06-29 | COMP | 2020-07-27 | COMP | Other | 41 | 105 |  | 150 | 0 | 8 | 301
13407 | 2019-05-17 | 2019-07-24 | 2020-02-10 | 2020-02-10 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-07-01 | COMP | 2020-08-04 | COMP | Rule 16 | 47 | 137 | 66 | 1 | 36 | 25 | 307
13608 | 2019-05-17 | 2019-08-01 | 2019-09-11 | 2019-09-11 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-03-30 | COMP | 2020-05-20 | COMP | Rule 16 | 53 | 29 | 136 | 1 | 2 | 38 | 254
13995 | 2019-05-17 | 2019-08-20 | 2019-10-23 | 2019-11-07 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2020-07-06 | COMP | 2020-07-09 | COMP | Rule 16 | 66 | 46 | 12 | 1 | 154 | 4 | 289
14321 | 2019-05-17 | 2019-09-04 | 2019-11-18 | 2019-11-18 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-02-10 | COMP | 2020-03-04 | COMP | Rule 16 | 76 | 53 | 12 | 1 | 45 | 17 | 199
14933 | 2019-05-17 | 2019-10-04 | 2019-10-26 | 2019-10-26 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-12-29 | COMP | 2020-01-10 | COMP | Rule 15/16 | 98 | 16 | 6 | 1 | 36 | 9 | 163
15139 | 2019-05-17 | 2019-10-15 | 2020-01-28 | 2020-01-28 | COMP | 2020-05-15 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-10-30 | COMP | Rule 16 | 105 | 70 | 78 | 24 | 1 | 96 | 369
16680 | 2019-05-17 | 2020-01-11 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-30 | COMP | 2020-08-13 | COMP | 2020-07-30 | COMP | 2021-02-12 | COMP | Rule 15/16 | 163 | 117 | 24 | 11 | 0 | 125 | 438
13119 | 2019-05-18 | 2019-07-11 | 2019-08-21 | 2019-08-21 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2020-04-15 | COMP | 2020-04-24 | COMP | Rule 16 | 37 | 30 | 4 | 1 | 160 | 8 | 235
14669 | 2019-05-18 | 2019-09-23 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-30 | NOTN | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-03-09 | COMP | Other | 88 | 77 |  | 12 | 1 | 27 | 201
14117 | 2019-05-19 | 2019-08-26 | 2019-11-14 | 2019-11-14 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2021-01-02 | INPR | 2019-12-11 | COMP | Rule 16 | 69 | 57 | 10 | 1 |  |  | 142
15428 | 2019-05-19 | 2019-10-31 | 2020-01-17 | 2020-01-17 | COMP | 2021-02-16 | COMP | 2021-02-16 | COMP |  | INPR | 2021-08-06 | COMP | Rule 16 | 116 | 52 | 272 | 1 |  |  | 559
12042 | 2019-05-20 | 2019-05-21 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-03 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-08-28 | COMP | Rule 15/16 | 2 | 172 | 5 | 121 | 1 | 28 | 324
12580 | 2019-05-20 | 2019-06-13 | 2020-02-24 | 2020-02-24 | COMP | 2021-09-21 | COMP | 2021-09-21 | COMP | 2021-09-27 | COMP | 2021-12-06 | COMP | Rule 16 | 18 | 174 | 400 | 1 | 5 | 48 | 641
12672 | 2019-05-20 | 2019-06-18 | 2019-08-30 | 2019-08-30 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-02-06 | COMP | 2020-03-03 | COMP | Rule 16 | 21 | 53 | 107 | 1 | 2 | 18 | 197
12757 | 2019-05-20 | 2019-06-20 | 2019-08-21 | 2019-08-21 | COMP | 2019-08-27 | NOTN | 2019-10-07 | COMP | 2020-03-01 | INPR | 2019-10-21 | COMP | Rule 16 | 23 | 44 |  | 33 |  |  | 108
12937 | 2019-05-20 | 2019-07-01 | 2019-12-06 | 2019-12-06 | COMP | 2020-05-21 | COMP | 2020-12-07 | COMP | 2021-03-02 | COMP | 2021-06-08 | COMP | Rule 16 | 30 | 110 | 116 | 138 | 58 | 70 | 517
12966 | 2019-05-20 | 2019-07-02 | 2019-11-06 | 2019-11-06 | COMP | 2020-04-06 | COMP | 2020-04-15 | COMP | 2020-06-17 | COMP | 2020-07-30 | COMP | Rule 16 | 31 | 90 | 102 | 8 | 45 | 32 | 303
13082 | 2019-05-20 | 2019-07-09 | 2020-05-08 | 2020-05-08 | COMP | 2021-05-24 | COMP | 2023-05-02 | COMP | 2023-06-06 | COMP | 2023-07-25 | COMP | Rule 15/16 | 35 | 211 | 263 | 488 | 25 | 34 | 1051
13118 | 2019-05-20 | 2019-07-11 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-20 | COMP | 2019-10-21 | COMP | 2019-11-07 | COMP | 2019-11-14 | COMP | Rule 16 | 37 | 39 | 13 | 22 | 14 | 5 | 125
13365 | 2019-05-20 | 2019-07-22 | 2019-09-09 | 2019-09-09 | COMP | 2019-10-07 | COMP | 2019-10-29 | COMP | 2019-11-15 | COMP | 2019-11-10 | COMP | Rule 16 | 44 | 35 | 21 | 17 | 13 |  | 122
13374 | 2019-05-20 | 2019-07-23 | 2019-11-15 | 2019-11-15 | COMP | 2020-02-25 | COMP | 2020-03-03 | COMP | 2020-02-08 | COMP | 2020-04-17 | COMP | Rule 16 | 45 | 82 | 67 | 6 | 0 | 34 | 230
13386 | 2019-05-20 | 2019-07-23 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-03-17 | COMP | 2020-04-03 | COMP | Rule 16 | 45 | 87 | 25 | 1 | 53 | 14 | 220
14241 | 2019-05-20 | 2019-08-30 | 2020-03-18 | 2020-04-20 | COMP | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-06-16 | COMP | 2020-07-01 | COMP | Rule 16 | 73 | 136 | 11 | 6 | 26 | 12 | 282
14356 | 2019-05-20 | 2019-09-05 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-11 | COMP | 2020-10-05 | COMP | 2021-06-03 | COMP | 2021-07-30 | COMP | Rule 16 | 76 | 90 | 19 | 167 | 166 | 41 | 554
14385 | 2019-05-20 | 2019-09-08 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-02 | COMP | 2020-03-17 | COMP | 2020-04-14 | COMP | 2020-06-04 | COMP | Rule 15/16 | 77 | 107 | 13 | 12 | 21 | 37 | 263
14722 | 2019-05-20 | 2019-09-25 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2020-02-04 | COMP | 2020-03-17 | COMP | Rule 16 | 90 | 32 | 12 | 1 | 47 | 30 | 207
14749 | 2019-05-20 | 2019-09-25 | 2020-01-06 | 2020-01-06 | COMP | 2020-01-21 | COMP | 2020-07-13 | COMP | 2020-07-09 | COMP | 2020-07-15 | COMP | Rule 16 | 90 | 69 | 11 | 123 | 0 | 3 | 292
15184 | 2019-05-20 | 2019-10-17 | 2019-12-14 | 2019-12-14 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-04-29 | COMP | Rule 16 | 106 | 39 | 63 | 1 | 1 | 32 | 238
15212 | 2019-05-20 | 2019-10-21 | 2019-11-25 | 2019-11-25 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2020-11-13 | COMP | 2020-12-08 | COMP | Rule 16 | 108 | 25 | 8 | 1 | 239 | 16 | 392
15274 | 2019-05-20 | 2019-10-24 | 2020-03-06 | 2020-03-06 | COMP | 2020-07-07 | COMP | 2020-08-07 | COMP | 2020-09-25 | COMP | 2020-12-10 | COMP | Rule 15/16 | 111 | 90 | 87 | 24 | 35 | 52 | 394
15318 | 2019-05-20 | 2019-10-26 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-01 | COMP | 2020-05-22 | COMP | 2020-04-01 | COMP | 2020-06-26 | COMP | Rule 16 | 112 | 99 | 8 | 38 | 0 | 25 | 279
17326 | 2019-05-20 | 2020-02-10 | 2020-05-18 | 2020-05-18 | COMP | 2020-05-26 | COMP | 2020-06-25 | INPR | 2020-08-27 | COMP | 2020-09-06 | COMP | Rule 16 | 182 | 70 | 6 |  |  |  | 329
18371 | 2019-05-20 | 2020-03-21 | 2020-06-24 | 2020-06-24 | COMP | 2021-05-06 | NOTN | 2021-05-06 | COMP | 2021-05-06 | COMP | 2021-07-09 | COMP | Other | 210 | 67 |  | 219 | 1 | 45 | 539
19747 | 2019-05-20 | 2020-05-20 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-08-11 | COMP | 2020-08-17 | COMP | Rule 16 | 253 | 26 | 19 | 1 | 16 | 5 | 315
4215 | 2019-05-21 | 2019-07-27 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-13 | COMP | 2019-09-19 | COMP | 2020-02-29 | INPR | 2019-11-13 | COMP | Rule 16 | 47 | 23 | 12 | 5 |  |  | 123
12040 | 2019-05-21 | 2019-05-21 | 2019-06-22 | 2019-06-22 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2019-08-18 | COMP | Rule 16 | 1 | 23 | 39 | 1 | 1 | 1 | 62
12051 | 2019-05-21 | 2019-05-22 | 2019-08-03 | 2019-08-03 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-06-13 | COMP | Rule 16 | 2 | 51 | 70 | 1 | 1 | 147 | 268
12055 | 2019-05-21 | 2019-05-21 | 2019-05-22 | 2019-05-22 | COMP | 2019-06-07 | COMP | 2019-06-10 | COMP | 2019-07-01 | COMP | 2019-09-06 | COMP | Rule 16 | 1 | 2 | 12 | 2 | 16 | 48 | 76
12381 | 2019-05-21 | 2019-06-04 | 2019-07-09 | 2019-10-31 | COMP | 2019-11-21 | COMP | 2019-12-05 | COMP | 2019-11-26 | COMP | 2020-01-28 | COMP | Rule 16 | 10 | 25 | 15 | 9 | 0 | 36 | 172
12403 | 2019-05-21 | 2019-06-05 | 2019-09-07 | 2019-09-07 | COMP | 2019-10-08 | COMP | 2019-10-09 | COMP | 2019-10-10 | COMP | 2019-11-06 | COMP | Rule 16 | 11 | 66 | 22 | 2 | 2 | 20 | 119
12668 | 2019-05-21 | 2019-06-18 | 2019-09-24 | 2019-09-24 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-09-23 | COMP | 2020-09-25 | COMP | Rule 16 | 20 | 69 | 184 | 1 | 70 | 3 | 342
12814 | 2019-05-21 | 2019-06-25 | 2019-12-20 | 2019-12-20 | COMP | 2020-03-11 | COMP | 2020-03-27 | COMP | 2020-03-30 | COMP | 2020-07-15 | COMP | Rule 16 | 25 | 124 | 55 | 13 | 2 | 77 | 291
12853 | 2019-05-21 | 2019-06-25 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-20 | COMP | 2019-12-09 | COMP | 2019-12-01 | COMP | 2020-01-31 | COMP | Rule 16 | 25 | 84 | 21 | 12 | 0 | 37 | 175
13038 | 2019-05-21 | 2019-07-08 | 2019-09-30 | 2019-09-30 | COMP | 2019-12-12 | COMP | 2019-12-09 | COMP | 2020-02-01 | COMP | 2020-02-07 | COMP | Rule 16 | 33 | 60 | 51 |  | 37 | 5 | 180
13140 | 2019-05-21 | 2019-07-11 | 2019-11-06 | 2019-11-06 | COMP | 2019-12-11 | COMP | 2019-12-19 | COMP | 2019-12-10 | COMP | 2020-01-23 | COMP | Rule 16 | 36 | 84 | 23 | 7 | 0 | 23 | 169
13159 | 2019-05-21 | 2019-07-15 | 2019-09-13 | 2019-09-13 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | Rule 16 | 38 | 44 | 9 | 1 | 34 | 1 | 122
13317 | 2019-05-21 | 2019-07-19 | 2019-12-03 | 2019-12-03 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2022-01-30 | INPR | 2020-11-23 | COMP | Rule 15/16 | 42 | 94 | 65 | 1 |  |  | 382
13375 | 2019-05-21 | 2019-07-22 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-26 | COMP | 2019-10-15 | COMP | 2019-12-17 | COMP | 2019-12-31 | COMP | Rule 16 | 43 | 40 | 9 | 14 | 43 | 10 | 154
13864 | 2019-05-21 | 2019-08-14 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-12 | COMP | 2020-04-30 | COMP | 2020-05-11 | COMP | 2020-07-02 | COMP | Rule 15/16 | 60 | 114 | 31 | 36 | 8 | 38 | 282
14279 | 2019-05-21 | 2019-09-03 | 2019-09-19 | 2019-09-19 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-08-20 | COMP | 2020-09-10 | COMP | Rule 16 | 73 | 13 | 113 | 1 | 121 | 15 | 331
14387 | 2019-05-21 | 2019-09-08 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-25 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2020-10-23 | COMP | Rule 16 | 76 | 100 | 16 | 125 | 1 | 48 | 362
14607 | 2019-05-21 | 2019-09-18 | 2019-10-29 | 2019-10-29 | COMP | 2019-12-05 | COMP | 2019-12-19 | COMP | 2019-10-29 | COMP | 2019-12-30 | COMP | Rule 16 | 84 | 30 | 25 | 11 | 0 | 7 | 153
15245 | 2019-05-21 | 2019-10-23 | 2020-02-10 | 2020-02-10 | COMP | 2020-06-18 | COMP | 2020-07-23 | COMP | 2022-01-30 | INPR | 2020-07-31 | COMP | Rule 16 | 109 | 73 | 92 | 26 |  |  | 303
15484 | 2019-05-21 | 2019-11-04 | 2019-12-30 | 2019-12-30 | COMP | 2020-03-25 | COMP | 2020-05-21 | COMP | 2020-08-21 | COMP | 2020-09-25 | COMP | Rule 16 | 117 | 37 | 60 | 42 | 66 | 25 | 342
15631 | 2019-05-21 | 2019-11-12 | 2020-02-28 | 2020-02-28 | COMP | 2020-06-26 | COMP | 2020-07-25 | COMP | 2022-07-16 | INPR | 2020-10-09 | COMP | Rule 15/16 | 122 | 73 | 85 | 21 |  |  | 352
15633 | 2019-05-21 | 2019-11-13 | 2020-01-02 | 2020-01-02 | COMP | 2020-01-28 | NOTN | 2020-03-23 | COMP | 2020-04-06 | NOTN | 2020-06-01 | COMP | Other | 123 | 33 |  | 56 |  |  | 259
15745 | 2019-05-21 | 2019-11-19 | 2020-06-17 | 2020-06-17 | COMP | 2020-10-13 | COMP | 2021-11-18 | COMP | 2022-05-02 | COMP | 2022-06-05 | COMP | Rule 15/16 | 127 | 145 | 84 | 277 | 114 | 24 | 766
17817 | 2019-05-21 | 2020-02-28 | 2020-03-12 | 2020-04-10 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP |  | INPR | 2020-05-28 | COMP | Rule 15/16 | 194 | 10 | 26 | 1 |  |  | 257
18346 | 2019-05-21 | 2020-03-20 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-07 | COMP | 2021-01-08 | COMP | 2020-12-07 | COMP | 2021-02-13 | COMP | Rule 16 | 209 | 69 | 32 | 105 | 0 | 25 | 436
12243 | 2019-05-22 | 2019-05-29 | 2019-06-11 | 2019-07-12 | COMP | 2019-08-23 | COMP | 2019-09-03 | COMP | 2019-08-31 | COMP | 2019-11-13 | COMP | Rule 16 | 5 | 10 | 31 | 7 | 0 | 51 | 122
12504 | 2019-05-22 | 2019-06-10 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2020-01-06 | COMP | 2020-01-09 | COMP | Rule 16 | 13 | 21 | 12 | 1 | 113 | 4 | 159
12601 | 2019-05-22 | 2019-06-14 | 2019-10-18 | 2019-10-22 | COMP | 2019-10-23 | NOTN | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-12-20 | COMP | Other | 17 | 89 |  | 2 | 1 | 40 | 147
12685 | 2019-05-22 | 2019-06-18 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-09-26 | COMP | 2019-10-21 | COMP | Rule 16 | 19 | 53 | 10 | 1 | 10 | 18 | 106
12721 | 2019-05-22 | 2019-06-19 | 2019-09-29 | 2019-11-26 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-11-23 | COMP | 2021-02-03 | COMP | Rule 16 | 20 | 71 | 5 | 1 | 247 | 48 | 428
12777 | 2019-05-22 | 2019-06-21 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-02 | COMP | 2019-11-20 | COMP | 2019-12-09 | COMP | 2020-01-21 | COMP | Rule 16 | 22 | 65 | 8 | 35 | 12 | 29 | 166
12985 | 2019-05-22 | 2019-07-03 | 2019-10-18 | 2019-10-18 | COMP | 2019-11-07 | NOTN | 2019-11-07 | COMP | 2020-01-13 | NOTN | 2020-02-13 | COMP | Other | 30 | 76 |  | 15 |  |  | 183
13128 | 2019-05-22 | 2019-07-11 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-10 | COMP | 2019-11-04 | COMP | 2020-03-23 | COMP | 2020-05-27 | COMP | Rule 16 | 35 | 44 | 22 | 18 | 94 | 47 | 255
13151 | 2019-05-22 | 2019-07-12 | 2020-10-09 | 2020-10-09 | COMP | 2021-06-17 | COMP | 2021-06-17 | COMP | 2021-09-27 | COMP | 2021-11-08 | COMP | Rule 15/16 | 36 | 316 | 172 | 1 | 71 | 31 | 622
13308 | 2019-05-22 | 2019-07-20 | 2019-09-05 | 2020-02-14 | COMP | 2020-02-20 | COMP | 2020-02-21 | COMP | 2020-02-24 | COMP | 2020-03-11 | COMP | Rule 16 | 41 | 33 | 4 | 2 | 2 | 13 | 201
13353 | 2019-05-22 | 2019-07-22 | 2019-10-20 | 2019-10-20 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-06-11 | COMP | 2020-07-21 | COMP | Rule 16 | 42 | 64 | 127 | 1 | 35 | 29 | 294
13509 | 2019-05-22 | 2019-07-29 | 2019-10-08 | 2019-10-08 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-06-15 | COMP | 2020-07-30 | COMP | Rule 16 | 47 | 51 | 131 | 1 | 42 | 34 | 301
13546 | 2019-05-22 | 2019-07-30 | 2019-12-30 | 2019-12-30 | COMP | 2020-01-15 | COMP | 2020-04-21 | COMP | 2020-08-07 | COMP | 2020-10-07 | COMP | Rule 16 | 48 | 105 | 12 | 68 | 78 | 43 | 349
13705 | 2019-05-22 | 2019-08-06 | 2019-12-05 | 2019-12-05 | COMP | 2020-01-14 | COMP | 2020-01-14 | COMP | 2020-02-24 | COMP | 2020-03-18 | COMP | Rule 15/16 | 53 | 84 | 27 | 1 | 28 | 18 | 206
13816 | 2019-05-22 | 2019-08-13 | 2020-02-19 | 2020-02-19 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2022-03-15 | COMP | 2022-04-11 | COMP | Rule 16 | 58 | 129 | 128 | 1 | 396 | 20 | 727
14263 | 2019-05-22 | 2019-09-03 | 2019-12-20 | 2020-04-02 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-12-30 | COMP | Rule 15/16 | 72 | 76 | 135 | 1 | 1 | 55 | 405
14460 | 2019-05-22 | 2019-09-11 | 2020-03-18 | 2020-03-18 | COMP | 2020-05-08 | COMP | 2020-09-28 | COMP | 2021-02-24 | COMP | 2021-03-30 | COMP | Rule 16 | 78 | 129 | 38 | 100 | 101 | 25 | 466
14649 | 2019-05-22 | 2019-09-20 | 2020-02-24 | 2020-02-28 | COMP | 2020-05-13 | COMP | 2020-06-17 | COMP | 2020-05-20 | COMP | 2020-06-24 | COMP | Rule 15/16 | 85 | 105 | 54 | 25 | 0 | 6 | 275
14697 | 2019-05-22 | 2019-09-23 | 2019-12-16 | 2019-12-16 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2021-05-04 | COMP | 2021-06-09 | COMP | Rule 15/16 | 86 | 58 | 142 | 1 | 208 | 26 | 516
17347 | 2019-05-22 | 2020-02-10 | 2020-04-19 | 2020-04-19 | COMP | 2020-04-22 | COMP | 2020-06-09 | COMP | 2023-12-03 | INPR | 2020-11-25 | COMP | Rule 15/16 | 180 | 49 | 3 | 34 |  |  | 383
12143 | 2019-05-23 | 2019-05-23 | 2019-06-13 | 2019-06-13 | COMP | 2019-07-01 | COMP | 2019-07-17 | COMP | 2019-12-29 | INPR | 2019-07-23 | COMP | Rule 15/16 | 1 | 15 | 13 | 12 |  |  | 42
12297 | 2019-05-23 | 2019-05-31 | 2019-12-18 | 2019-12-18 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-10-16 | COMP | 2020-10-29 | COMP | Rule 16 | 6 | 139 | 96 | 1 | 117 | 10 | 364
12500 | 2019-05-23 | 2019-06-10 | 2019-08-17 | 2019-08-17 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-12-14 | COMP | 2021-01-12 | COMP | Rule 16 | 12 | 49 | 277 | 1 | 57 | 20 | 412
12936 | 2019-05-23 | 2019-07-01 | 2020-02-07 | 2020-05-20 | COMP | 2020-06-01 | COMP | 2020-07-09 | COMP | 2020-09-02 | COMP | 2020-10-08 | COMP | Rule 15/16 | 27 | 152 | 8 | 29 | 40 | 26 | 349
13207 | 2019-05-23 | 2019-07-16 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-31 | COMP | 2019-11-14 | COMP | 2019-12-02 | COMP | 2019-12-30 | COMP | Rule 16 | 37 | 55 | 23 | 10 | 11 | 20 | 151
13277 | 2019-05-23 | 2019-07-18 | 2019-07-31 | 2019-07-31 | COMP | 2019-08-15 | COMP | 2021-05-30 | REQD | 2019-08-15 | COMP | 2019-08-30 | COMP | Other | 39 | 10 | 12 |  |  |  | 70
13278 | 2019-05-23 | 2019-07-18 | 2019-08-02 | 2019-08-06 | COMP | 2019-08-19 | COMP | 2021-05-30 | REQD | 2021-05-30 | REQD | 2019-08-28 | COMP | Other | 39 | 12 | 10 |  |  |  | 68
13425 | 2019-05-23 | 2019-07-25 | 2020-01-27 | 2020-01-27 | COMP | 2020-04-30 | COMP | 2020-05-22 | COMP | 2021-03-19 | COMP | 2021-05-25 | COMP | Rule 15/16 | 44 | 126 | 68 | 17 | 207 | 48 | 505
13926 | 2019-05-23 | 2019-08-16 | 2020-03-13 | 2020-03-13 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-08-24 | COMP | 2020-10-06 | COMP | Rule 15/16 | 60 | 143 | 65 | 1 | 52 | 31 | 347
14107 | 2019-05-23 | 2019-08-26 | 2020-01-28 | 2020-08-12 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2020-09-01 | COMP | 2021-01-08 | COMP | Rule 15/16 | 66 | 105 | 8 | 1 | 8 | 88 | 410
14195 | 2019-05-23 | 2019-08-29 | 2019-10-03 | 2019-10-03 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2020-09-14 | COMP | 2020-10-01 | COMP | Rule 16 | 69 | 25 | 25 | 1 | 215 | 14 | 344
14395 | 2019-05-23 | 2019-09-09 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2021-01-30 | INPR | 2020-01-24 | COMP | Rule 16 | 75 | 28 | 20 | 1 |  |  | 168
14415 | 2019-05-23 | 2019-09-09 | 2019-10-15 | 2019-10-15 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2021-01-30 | INPR | 2020-01-24 | COMP | Rule 16 | 75 | 27 | 26 | 1 |  |  | 168
14884 | 2019-05-23 | 2019-10-02 | 2019-11-06 | 2019-11-06 | COMP | 2020-02-10 | COMP | 2020-02-14 | COMP | 2020-08-07 | COMP | 2020-09-03 | COMP | Rule 15/16 | 92 | 26 | 63 | 5 | 124 | 20 | 325
14994 | 2019-05-23 | 2019-10-09 | 2020-02-10 | 2020-02-10 | COMP | 2020-07-01 | COMP | 2021-08-23 | COMP | 2022-12-03 | INPR | 2021-11-03 | COMP | Rule 16 | 97 | 83 | 101 | 289 |  |  | 618
15362 | 2019-05-23 | 2019-10-29 | 2020-04-23 | 2020-04-23 | COMP | 2020-06-18 | COMP | 2020-08-22 | COMP | 2020-12-21 | COMP | 2021-02-01 | COMP | Rule 15/16 | 111 | 121 | 40 | 47 | 82 | 28 | 425
16056 | 2019-05-23 | 2019-12-07 | 2020-02-02 | 2020-02-02 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-08-17 | COMP | 2020-08-21 | COMP | Rule 16 | 136 | 37 | 12 | 1 | 128 | 5 | 316
16342 | 2019-05-23 | 2019-12-23 | 2020-03-22 | 2020-03-22 | COMP | 2020-06-25 | COMP | 2020-06-25 | COMP |  |  | 2020-08-12 | COMP | Rule 15/16 | 147 | 61 | 68 | 1 |  |  | 309
19104 | 2019-05-23 | 2020-04-21 | 2020-08-20 | 2020-08-20 | COMP | 2020-09-24 | COMP | 2020-10-06 | COMP | 2020-10-26 | COMP | 2020-12-10 | COMP | Rule 16 | 229 | 87 | 25 | 9 | 15 | 31 | 391
12167 | 2019-05-24 | 2019-05-24 | 2019-10-14 | 2020-02-28 | COMP | 2020-04-08 | COMP | 2019-10-29 | COMP | 2020-06-25 | COMP | 2020-07-14 | COMP | Rule 16 | 1 | 99 | 29 |  | 165 | 14 | 287
12426 | 2019-05-24 | 2019-06-05 | 2019-08-14 | 2019-08-14 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2020-04-26 | INPR | 2019-09-13 | COMP | Rule 16 | 8 | 50 | 5 | 1 |  |  | 78
12451 | 2019-05-24 | 2019-06-07 | 2019-06-14 | 2019-06-14 | COMP | 2019-06-21 | COMP | 2019-06-21 | COMP | 2019-09-20 | COMP | 2019-09-27 | COMP | Rule 16 | 10 | 6 | 6 | 1 | 64 | 6 | 88
12456 | 2019-05-24 | 2019-06-07 | 2019-10-12 | 2019-10-12 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2020-01-27 | COMP | 2020-02-18 | COMP | Rule 16 | 10 | 89 | 18 | 1 | 53 | 16 | 183
12566 | 2019-05-24 | 2019-06-14 | 2019-09-13 | 2019-09-13 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-01-07 | COMP | 2020-02-25 | COMP | Rule 16 | 15 | 64 | 42 | 1 | 37 | 34 | 188
12665 | 2019-05-24 | 2019-06-18 | 2019-08-01 | 2019-08-01 | COMP | 2020-04-13 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-04-20 | COMP | Rule 16 | 17 | 32 | 175 | 2 | 1 | 5 | 227
12768 | 2019-05-24 | 2019-06-20 | 2020-02-06 | 2020-02-06 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2021-04-13 | COMP | 2021-04-20 | COMP | Rule 16 | 19 | 158 | 9 | 1 | 291 | 6 | 479
12889 | 2019-05-24 | 2019-06-27 | 2020-01-28 | 2020-01-28 | COMP | 2020-06-15 | COMP | 2020-11-04 | COMP | 2020-12-15 | COMP | 2021-01-03 | COMP | Rule 15/16 | 24 | 146 | 98 | 102 | 27 | 12 | 404
12898 | 2019-05-24 | 2019-06-27 | 2019-08-12 | 2019-09-12 | COMP | 2019-10-08 | NOTN | 2019-10-08 | COMP | 2019-09-16 | COMP | 2020-01-06 | COMP | Other | 24 | 32 |  | 19 | 0 | 60 | 154
12972 | 2019-05-24 | 2019-07-01 | 2019-10-21 | 2019-10-21 | COMP | 2019-10-31 | COMP | 2019-12-18 | COMP | 2019-11-01 | COMP | 2020-02-18 | COMP | Rule 16 | 26 | 79 | 9 | 32 | 0 | 41 | 183
13052 | 2019-05-24 | 2019-07-09 | 2019-10-28 | 2019-10-28 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-14 | COMP | 2019-12-10 | COMP | Rule 16 | 31 | 79 | 12 | 1 | 2 | 17 | 137
13194 | 2019-05-24 | 2019-07-15 | 2019-09-18 | 2019-09-18 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-09-26 | COMP | 2019-09-30 | COMP | Rule 16 | 35 | 47 | 6 | 1 | 2 | 3 | 89
13518 | 2019-05-24 | 2019-07-30 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-10-25 | COMP | 2019-12-17 | COMP | Rule 16 | 46 | 41 | 12 | 1 | 12 | 35 | 142
13579 | 2019-05-24 | 2019-08-01 | 2019-09-16 | 2019-09-16 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-04 | COMP | 2020-03-11 | COMP | Rule 16 | 48 | 32 | 118 | 1 | 0 | 4 | 199
13805 | 2019-05-24 | 2019-08-12 | 2019-10-09 | 2019-10-09 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-01-13 | COMP | Rule 16 | 55 | 42 | 29 | 1 | 1 | 36 | 159
15312 | 2019-05-24 | 2019-10-25 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | Rule 16 | 108 | 66 | 7 | 1 | 163 | 1 | 341
15604 | 2019-05-24 | 2019-11-08 | 2020-02-24 | 2020-08-31 | COMP | 2020-09-15 | COMP | 2020-10-14 | COMP | 2020-11-23 | COMP | 2020-12-23 | COMP | Rule 16 | 118 | 70 | 11 | 22 | 28 | 21 | 399
20073 | 2019-05-24 | 2020-06-03 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-09-01 | COMP | 2021-01-26 | COMP | Rule 16 | 258 | 64 | 14 | 1 | 0 | 87 | 420
12298 | 2019-05-25 | 2019-05-31 | 2019-08-21 | 2019-08-21 | COMP | 2019-08-26 | COMP | 2019-09-23 | COMP | 2019-11-18 | COMP | 2019-12-05 | COMP | Rule 16 | 4 | 58 | 4 | 20 | 40 | 12 | 133
14282 | 2019-05-25 | 2019-09-03 | 2019-10-14 | 2020-03-24 | COMP | 2020-05-07 | COMP | 2020-01-24 | COMP | 2020-05-27 | COMP | 2020-07-01 | COMP | Rule 16 | 69 | 30 | 33 |  | 87 | 26 | 277
18825 | 2019-05-25 | 2020-04-08 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-02 | COMP | 2020-08-18 | COMP | 2020-11-09 | COMP | 2020-12-10 | COMP | Rule 16 | 218 | 56 | 6 | 34 | 59 | 21 | 389
12587 | 2019-05-27 | 2019-06-14 | 2019-09-21 | 2019-09-21 | COMP | 2019-09-27 | COMP | 2019-10-30 | COMP | 2019-10-25 | COMP | 2019-11-14 | COMP | Rule 16 | 14 | 69 | 5 | 24 | 0 | 11 | 120
12799 | 2019-05-27 | 2019-06-24 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2019-09-13 | COMP | 2019-09-26 | COMP | Rule 16 | 20 | 43 | 13 | 1 | 4 | 10 | 86
4186 | 2019-05-28 | 2019-06-11 | 2019-09-21 | 2019-09-21 | COMP | 2019-11-07 | COMP | 2020-01-06 | COMP | 2020-02-04 | COMP | 2020-02-11 | COMP | Rule 16 | 11 | 72 | 34 | 38 | 21 | 6 | 178
12321 | 2019-05-28 | 2019-05-31 | 2019-10-01 | 2019-10-01 | COMP | 2019-11-01 | NOTN | 2019-11-18 | COMP | 2019-11-01 | COMP | 2020-06-12 | COMP | Other | 4 | 86 |  | 34 | 0 | 143 | 264
12407 | 2019-05-28 | 2019-06-07 | 2019-07-09 | 2019-07-09 | COMP | 2019-07-16 | COMP | 2019-07-16 | COMP | 2022-01-30 | INPR | 2020-07-17 | COMP | Rule 16 | 9 | 22 | 6 | 1 |  |  | 289
12424 | 2019-05-28 | 2019-06-06 | 2019-10-03 | 2019-10-03 | COMP | 2019-12-17 | COMP | 2020-06-25 | COMP | 2020-07-01 | COMP | 2020-07-14 | COMP | Rule 15/16 | 8 | 84 | 51 | 133 | 5 | 10 | 286
12501 | 2019-05-28 | 2019-06-10 | 2019-08-14 | 2019-08-14 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2020-01-08 | COMP | 2020-01-15 | COMP | Rule 16 | 10 | 47 | 23 | 1 | 78 | 6 | 160
12602 | 2019-05-28 | 2019-06-14 | 2019-07-24 | 2019-07-24 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-09-13 | COMP | 2019-10-04 | COMP | Rule 16 | 14 | 28 | 11 | 1 | 27 | 16 | 92
12703 | 2019-05-28 | 2019-06-19 | 2019-10-10 | 2019-10-10 | COMP | 2019-12-02 | COMP | 2020-12-24 | COMP | 2020-12-23 | COMP | 2021-03-03 | COMP | Rule 16 | 17 | 80 | 35 | 270 | 0 | 46 | 444
12782 | 2019-05-28 | 2019-06-21 | 2019-08-05 | 2019-08-05 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2021-04-24 | INPR | 2020-03-30 | COMP | Rule 16 | 19 | 31 | 131 | 1 |  |  | 211
12863 | 2019-05-28 | 2019-06-26 | 2019-10-07 | 2019-10-08 | COMP | 2019-10-16 | COMP | 2019-11-25 | COMP | 2019-12-06 | COMP | 2020-01-07 | COMP | Rule 16 | 22 | 72 | 7 | 28 | 8 | 21 | 154
13030 | 2019-05-28 | 2019-07-08 | 2019-09-17 | 2019-09-17 | COMP | 2019-12-03 | NOTN | 2019-12-03 | COMP | 2019-12-16 | NOTN | 2020-01-07 | COMP | Other | 29 | 51 |  | 53 |  |  | 154
13185 | 2019-05-28 | 2019-07-16 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-29 | COMP | 2019-12-06 | COMP | 2019-10-30 | COMP | 2020-01-07 | COMP | Rule 16 | 35 | 58 | 17 | 26 | 0 | 21 | 154
13368 | 2019-05-28 | 2019-07-22 | 2019-10-26 | 2019-10-26 | COMP | 2021-03-05 | COMP | 2021-03-05 | COMP | 2021-10-28 | COMP | 2021-11-24 | COMP | Rule 16 | 39 | 69 | 339 | 1 | 167 | 19 | 630
13638 | 2019-05-28 | 2019-08-03 | 2019-11-06 | 2019-11-12 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-12-03 | COMP | 2019-12-17 | COMP | Rule 16 | 48 | 67 | 5 | 1 | 10 | 11 | 141
13818 | 2019-05-28 | 2019-08-12 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-31 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-03-09 | COMP | Rule 16 | 54 | 106 | 13 | 2 | 1 | 25 | 196
14068 | 2019-05-28 | 2019-08-23 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2019-11-14 | COMP | Rule 16 | 63 | 38 | 17 | 1 | 1 | 5 | 120
14078 | 2019-05-28 | 2019-08-24 | 2020-03-04 | 2020-03-04 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2021-04-24 | INPR | 2020-04-09 | COMP | Rule 16 | 63 | 130 | 21 | 1 |  |  | 219
14603 | 2019-05-28 | 2019-09-18 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-09 | COMP | 2020-04-21 | COMP | Rule 16 | 80 | 27 | 13 | 1 | 18 | 93 | 227
14846 | 2019-05-28 | 2019-10-01 | 2019-11-21 | 2019-11-21 | COMP | 2020-02-07 | COMP | 2020-04-22 | COMP | 2020-07-07 | COMP | 2020-07-02 | COMP | Rule 15/16 | 89 | 37 | 52 | 53 | 54 |  | 278
15223 | 2019-05-28 | 2019-10-21 | 2019-12-30 | 2019-12-30 | COMP | 2020-03-24 | COMP | 2020-04-02 | COMP | 2021-04-24 | INPR | 2020-04-22 | COMP | Rule 16 | 103 | 47 | 59 | 8 |  |  | 228
15303 | 2019-05-28 | 2019-10-25 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-30 | COMP | 2020-04-08 | COMP | 2020-03-30 | COMP | 2020-05-15 | COMP | Rule 16 | 107 | 90 | 16 | 8 | 0 | 28 | 245
16445 | 2019-05-28 | 2019-12-31 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-26 | COMP | 2020-12-02 | COMP | 2021-04-14 | COMP | 2021-08-04 | COMP | Rule 15/16 | 150 | 137 | 32 | 67 | 92 | 79 | 552
17208 | 2019-05-28 | 2020-02-04 | 2020-03-12 | 2020-03-12 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-08-03 | COMP | 2020-11-06 | COMP | Rule 16 | 173 | 27 | 34 | 1 | 69 | 69 | 368
17758 | 2019-05-28 | 2020-02-26 | 2020-05-19 | 2021-05-07 | COMP | 2021-05-20 | COMP | 2021-05-22 | COMP | 2021-06-07 | COMP | 2021-10-19 | COMP | Rule 16 | 188 | 60 | 10 | 2 | 10 | 95 | 605
18026 | 2019-05-28 | 2020-03-09 | 2020-05-22 | 2020-05-22 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-07-23 | COMP | 2020-10-07 | COMP | Rule 15/16 | 196 | 55 | 42 | 1 | 3 | 54 | 346
12178 | 2019-05-29 | 2019-05-29 | 2019-07-15 | 2019-07-15 | COMP | 2020-09-11 | COMP | 2020-09-13 | COMP | 2020-09-11 | COMP | 2020-11-03 | COMP | Rule 16 | 1 | 33 | 295 | 1 | 0 | 37 | 364
12505 | 2019-05-29 | 2019-06-10 | 2019-07-08 | 2019-07-08 | COMP | 2019-07-18 | COMP | 2019-07-18 | COMP | 2019-09-03 | COMP | 2019-09-30 | COMP | Rule 16 | 9 | 20 | 9 | 1 | 33 | 20 | 87
12528 | 2019-05-29 | 2019-06-11 | 2019-08-02 | 2019-08-02 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-11-26 | COMP | 2019-12-09 | COMP | Rule 16 | 10 | 38 | 26 | 1 | 56 | 8 | 134
12864 | 2019-05-29 | 2019-06-26 | 2019-10-22 | 2019-10-22 | COMP | 2019-12-09 | COMP | 2020-01-14 | COMP | 2020-05-31 | INPR | 2020-02-03 | COMP | Rule 16 | 21 | 83 | 32 | 25 |  |  | 171
12880 | 2019-05-29 | 2019-06-26 | 2019-07-25 | 2019-07-25 | COMP | 2019-11-08 | COMP | 2019-11-08 | INPR | 2020-03-29 | REQD | 2019-11-08 | COMP | Rule 16 | 21 | 21 | 76 |  |  |  | 116
12892 | 2019-05-29 | 2019-06-27 | 2019-09-09 | 2019-09-09 | COMP | 2019-11-08 | COMP | 2020-01-24 | COMP | 2020-01-27 | COMP | 2020-02-07 | COMP | Rule 16 | 22 | 51 | 45 | 50 | 2 | 10 | 175
12958 | 2019-05-29 | 2019-07-02 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-05 | COMP | 2019-11-19 | COMP | 2021-02-27 | INPR | 2020-02-20 | COMP | Rule 16 | 25 | 84 | 6 | 10 |  |  | 183
12983 | 2019-05-29 | 2019-07-02 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2020-06-10 | COMP | 2020-07-21 | COMP | Rule 15/16 | 25 | 99 | 8 | 1 | 132 | 30 | 290
13005 | 2019-05-29 | 2019-07-05 | 2019-10-15 | 2020-05-19 | COMP | 2021-03-16 | COMP | 2021-07-01 | COMP | 2021-08-13 | COMP | 2021-09-08 | COMP | Rule 15/16 | 27 | 72 | 207 | 77 | 31 | 18 | 575
13007 | 2019-05-29 | 2019-07-05 | 2019-10-15 | 2020-05-19 | COMP | 2020-06-26 | COMP | 2020-10-28 | COMP | 2020-12-08 | COMP | 2020-12-22 | COMP | Rule 15/16 | 27 | 72 | 28 | 88 | 27 | 11 | 396
13069 | 2019-05-29 | 2019-07-08 | 2020-04-27 | 2020-09-15 | COMP | 2020-10-23 | COMP | 2020-10-23 | COMP | 2020-12-21 | COMP | 2021-01-15 | COMP | Rule 16 | 28 | 203 | 29 | 1 | 39 | 18 | 412
13209 | 2019-05-29 | 2019-07-16 | 2019-08-15 | 2019-08-15 | COMP | 2019-09-20 | COMP | 2020-03-19 | COMP | 2019-11-20 | COMP | 2020-04-27 | COMP | Rule 16 | 34 | 23 | 26 | 123 | 0 | 28 | 230
13217 | 2019-05-29 | 2019-07-17 | 2019-08-14 | 2019-08-14 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-05-05 | COMP | 2020-05-25 | COMP | Rule 16 | 35 | 21 | 69 | 1 | 114 | 14 | 249
13393 | 2019-05-29 | 2019-07-24 | 2019-12-10 | 2019-12-10 | COMP | 2019-12-12 | NOTN | 2019-12-12 | COMP | 2020-01-30 | COMP | 2020-07-25 | COMP | Other | 40 | 96 |  | 3 | 33 | 125 | 293
13790 | 2019-05-29 | 2019-08-09 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-18 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-05-21 | COMP | Rule 16 | 52 | 58 | 13 | 99 | 1 | 30 | 248
14072 | 2019-05-29 | 2019-08-23 | 2019-10-06 | 2019-10-23 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-27 | COMP | 2020-01-14 | COMP | Rule 16 | 62 | 30 | 14 | 1 | 12 | 31 | 158
14287 | 2019-05-29 | 2019-09-03 | 2019-12-23 | 2019-12-23 | COMP | 2020-02-26 | COMP | 2020-05-01 | COMP | 2020-08-04 | COMP | 2020-10-22 | COMP | Rule 16 | 68 | 77 | 44 | 48 | 67 | 57 | 356
14350 | 2019-05-29 | 2019-09-05 | 2019-09-27 | 2019-09-27 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2020-01-21 | COMP | 2020-02-10 | COMP | Rule 16 | 70 | 17 | 5 | 1 | 73 | 15 | 176
14526 | 2019-05-29 | 2019-09-14 | 2019-10-31 | 2019-10-31 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-02-04 | COMP | 2020-02-18 | COMP | Rule 15/16 | 76 | 34 | 14 | 1 | 50 | 10 | 181
14834 | 2019-05-29 | 2019-09-30 | 2020-01-23 | 2020-01-23 | COMP | 2020-02-04 | COMP | 2020-02-20 | COMP | 2020-02-10 | COMP | 2020-02-25 | COMP | Rule 16 | 87 | 78 | 9 | 12 | 0 | 4 | 186
16222 | 2019-05-29 | 2019-12-17 | 2020-02-12 | 2020-02-18 | COMP | 2020-03-24 | COMP | 2020-05-20 | COMP | 2020-03-04 | COMP | 2020-07-14 | COMP | Rule 16 | 140 | 39 | 26 | 42 | 0 | 39 | 285
16309 | 2019-05-29 | 2019-12-19 | 2020-03-12 | 2020-03-12 | COMP | 2020-03-26 | COMP | 2020-04-15 | COMP | 2020-06-24 | COMP | 2020-07-14 | COMP | Rule 16 | 142 | 57 | 11 | 15 | 50 | 15 | 285
4180 | 2019-05-30 | 2019-05-30 | 2019-07-12 | 2019-07-12 | COMP | 2020-03-27 | COMP | 2020-04-28 | COMP | 2020-06-29 | COMP | 2020-07-28 | COMP | Rule 15/16 | 1 | 31 | 178 | 23 | 44 | 22 | 294
12307 | 2019-05-30 | 2019-05-30 | 2020-03-05 | 2021-02-05 | COMP | 2021-03-15 | COMP | 2021-03-15 | COMP | 2021-11-05 | COMP | 2021-12-06 | COMP | Rule 16 | 1 | 192 | 26 | 1 | 167 | 19 | 634
12317 | 2019-05-30 | 2019-05-30 | 2019-10-08 | 2019-10-08 | COMP | 2019-11-26 | COMP | 2021-03-23 | COMP | 2021-09-13 | COMP | 2021-10-19 | COMP | Rule 15/16 | 1 | 92 | 35 | 331 | 122 | 27 | 603
12506 | 2019-05-30 | 2019-06-10 | 2019-07-25 | 2019-07-25 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2019-11-13 | COMP | 2020-01-27 | COMP | Rule 16 | 8 | 33 | 113 | 1 | 0 | 14 | 165
12567 | 2019-05-30 | 2019-06-14 | 2019-09-11 | 2019-09-11 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-06-08 | COMP | Rule 16 | 12 | 62 | 151 | 1 | 1 | 36 | 258
12617 | 2019-05-30 | 2019-06-17 | 2019-09-07 | 2019-09-07 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-04-28 | COMP | 2020-02-21 | COMP | Rule 16 | 13 | 58 | 82 | 1 | 79 |  | 183
12719 | 2019-05-30 | 2019-06-19 | 2019-08-14 | 2019-08-14 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-12-30 | COMP | 2020-01-10 | COMP | Rule 15/16 | 15 | 40 | 39 | 1 | 56 | 9 | 155
12720 | 2019-05-30 | 2019-06-19 | 2019-07-27 | 2019-09-10 | COMP | 2019-09-17 | COMP | 2019-08-07 | COMP | 2019-10-28 | COMP | 2019-10-31 | COMP | Rule 16 | 15 | 27 | 6 |  | 58 | 4 | 109
12908 | 2019-05-30 | 2019-06-28 | 2019-07-11 | 2019-07-11 | COMP | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-10-01 | COMP | 2019-10-21 | COMP | Rule 16 | 22 | 9 | 38 | 1 | 21 | 15 | 101
13023 | 2019-05-30 | 2019-07-05 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-03 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2020-12-30 | COMP | Rule 15/16 | 26 | 258 | 16 | 55 | 1 | 49 | 400
13024 | 2019-05-30 | 2019-07-05 | 2020-05-12 | 2020-05-13 | COMP | 2020-07-10 | COMP | 2021-01-08 | COMP | 2020-12-28 | COMP | 2021-03-24 | COMP | Rule 15/16 | 26 | 215 | 42 | 125 | 0 | 52 | 457
13048 | 2019-05-30 | 2019-07-08 | 2019-12-07 | 2019-12-07 | COMP | 2020-01-27 | COMP | 2020-02-26 | COMP | 2020-02-13 | COMP | 2020-09-14 | COMP | Rule 16 | 27 | 106 | 33 | 22 | 0 | 142 | 327
13232 | 2019-05-30 | 2019-07-18 | 2019-09-25 | 2020-04-15 | COMP | 2020-05-08 | COMP | 2019-11-20 | COMP | 2020-09-08 | COMP | 2021-02-03 | COMP | Rule 15/16 | 35 | 49 | 18 |  | 202 | 101 | 423
13316 | 2019-05-30 | 2019-07-20 | 2019-10-20 | 2019-10-21 | COMP | 2019-11-18 | NOTN | 2019-11-18 | COMP | 2020-02-19 | COMP | 2020-02-23 | COMP | Rule 16 | 36 | 64 |  | 20 | 62 | 3 | 183
13414 | 2019-05-30 | 2019-07-25 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-20 | COMP | 2020-02-12 | COMP | 2020-02-03 | COMP | 2020-03-18 | COMP | Rule 16 | 40 | 59 | 45 | 36 | 0 | 25 | 201
14136 | 2019-05-30 | 2019-08-26 | 2019-10-31 | 2019-10-31 | COMP | 2019-11-20 | COMP | 2019-12-16 | COMP | 2019-12-19 | COMP | 2020-02-05 | COMP | Rule 16 | 62 | 48 | 14 | 17 | 4 | 32 | 172
14488 | 2019-05-30 | 2019-09-11 | 2019-10-21 | 2019-10-21 | COMP | 2019-11-14 | COMP | 2019-12-16 | COMP | 2020-04-26 | INPR | 2019-12-20 | COMP | Rule 16 | 73 | 29 | 18 | 21 |  |  | 142
14842 | 2019-05-30 | 2019-09-30 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-01-21 | COMP | 2020-06-29 | COMP | Rule 16 | 86 | 63 | 13 | 1 | 2 | 113 | 273
14944 | 2019-05-30 | 2019-10-05 | 2019-12-08 | 2019-12-08 | COMP | 2019-12-31 | COMP | 2020-01-29 | COMP | 2021-02-27 | INPR | 2020-02-20 | COMP | Rule 16 | 90 | 42 | 16 | 20 |  |  | 182
15037 | 2019-05-30 | 2019-10-09 | 2020-01-21 | 2020-01-21 | COMP | 2020-01-28 | COMP | 2020-05-04 | COMP | 2020-05-07 | COMP | 2020-07-10 | COMP | Rule 16 | 93 | 69 | 6 | 69 | 4 | 46 | 282
15336 | 2019-05-30 | 2019-10-26 | 2020-05-06 | 2020-05-06 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2021-02-08 | COMP | Rule 16 | 105 | 131 | 106 | 1 | 1 | 86 | 426
15941 | 2019-05-30 | 2019-12-02 | 2020-01-29 | 2020-01-29 | COMP | 2020-02-24 | COMP | 2020-03-17 | COMP | 2020-04-20 | COMP | 2020-06-22 | COMP | Rule 16 | 128 | 40 | 18 | 17 | 25 | 45 | 268
15989 | 2019-05-30 | 2019-12-04 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-08-17 | COMP | 2020-09-23 | COMP | Rule 16 | 130 | 72 | 19 | 1 | 90 | 27 | 334
16024 | 2019-05-30 | 2019-12-05 | 2020-02-05 | 2020-02-06 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-13 | COMP | 2020-03-20 | COMP | Rule 16 | 131 | 42 | 9 | 1 | 18 | 6 | 203
16165 | 2019-05-30 | 2019-12-12 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-07-14 | COMP | 2020-07-22 | COMP | Rule 16 | 136 | 67 | 13 | 1 | 71 | 7 | 290
17411 | 2019-05-30 | 2020-02-12 | 2020-08-08 | 2020-08-08 | COMP | 2020-08-26 | COMP | 2020-10-21 | COMP |  | INPR | 2020-01-20 | COMP | Rule 16 | 177 | 126 | 13 | 40 |  |  | 160
17808 | 2019-05-30 | 2020-02-27 | 2020-07-06 | 2020-07-06 | COMP | 2020-08-13 | COMP | 2020-11-30 | COMP | 2021-01-25 | COMP | 2021-02-18 | COMP | Rule 15/16 | 187 | 92 | 29 | 74 | 38 | 18 | 433
12414 | 2019-05-31 | 2019-06-10 | 2019-07-19 | 2019-07-19 | COMP | 2019-07-17 | NOTN | 2019-09-10 | COMP | 2019-08-07 | COMP | 2019-09-25 | COMP | Other | 7 | 29 |  | 37 | 0 | 12 | 82
12550 | 2019-05-31 | 2019-06-13 | 2020-03-13 | 2020-03-13 | COMP | 2020-04-16 | COMP | 2020-08-31 | COMP | 2020-10-07 | COMP | 2020-10-30 | COMP | Rule 16 | 10 | 188 | 25 | 97 | 27 | 18 | 360
12565 | 2019-05-31 | 2019-06-12 | 2019-07-24 | 2019-07-24 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-07-16 | COMP | 2020-08-21 | COMP | Rule 16 | 9 | 30 | 148 | 1 | 101 | 27 | 311
12907 | 2019-05-31 | 2019-06-28 | 2019-08-27 | 2019-08-27 | COMP | 2019-09-05 | COMP | 2019-09-20 | COMP | 2019-09-06 | COMP | 2019-10-21 | COMP | Rule 15/16 | 21 | 42 | 7 | 12 | 0 | 22 | 100
13068 | 2019-05-31 | 2019-07-09 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-10 | NOTN | 2019-09-10 | COMP | 2020-03-01 | INPR | 2019-10-24 | COMP | Other | 27 | 44 |  | 2 |  |  | 103
13148 | 2019-05-31 | 2019-07-12 | 2019-09-25 | 2019-09-25 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-10-01 | COMP | 2019-11-15 | COMP | Rule 16 | 30 | 53 | 4 | 1 | 2 | 33 | 118
13248 | 2019-05-31 | 2019-07-18 | 2019-12-20 | 2023-03-21 | COMP | 2023-05-15 | COMP | 2023-06-07 | COMP | 2023-07-24 | COMP | 2023-08-15 | COMP | Rule 15/16 | 34 | 108 | 40 | 17 | 32 | 17 | 1058
13636 | 2019-05-31 | 2019-08-03 | 2019-10-29 | 2019-10-29 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-02-11 | COMP | 2020-03-16 | COMP | Rule 16 | 45 | 61 | 29 | 1 | 42 | 24 | 198
13767 | 2019-05-31 | 2019-08-08 | 2019-09-13 | 2021-12-17 | COMP | 2022-07-12 | COMP | 2023-07-12 | COMP | 2023-05-09 | COMP | 2023-08-01 | COMP | Rule 16 | 49 | 26 | 143 | 251 | 0 | 15 | 1048
13960 | 2019-05-31 | 2019-08-21 | 2019-09-28 | 2019-09-28 | COMP | 2020-01-10 | COMP | 2020-01-14 | COMP | 2020-01-16 | COMP | 2020-01-27 | COMP | Rule 15/16 | 58 | 27 | 70 | 3 | 3 | 7 | 164
13991 | 2019-05-31 | 2019-08-20 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-04-21 | COMP | 2020-05-21 | COMP | Rule 16 | 57 | 36 | 9 | 1 | 125 | 23 | 246
14354 | 2019-05-31 | 2019-09-06 | 2019-12-16 | 2019-12-16 | COMP | 2019-12-26 | COMP | 2019-12-26 | COMP | 2020-01-16 | COMP | 2020-03-05 | COMP | Rule 16 | 69 | 69 | 8 | 1 | 15 | 34 | 191
14389 | 2019-05-31 | 2019-09-08 | 2020-01-15 | 2020-01-15 | COMP | 2020-01-23 | COMP | 2020-02-27 | COMP | 2020-04-01 | COMP | 2020-06-03 | COMP | Rule 16 | 69 | 88 | 6 | 25 | 25 | 45 | 254
14405 | 2019-05-31 | 2019-09-09 | 2020-01-08 | 2020-01-08 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-10-19 | COMP | 2020-10-29 | COMP | Rule 16 | 70 | 83 | 110 | 1 | 91 | 9 | 359
14522 | 2019-05-31 | 2019-09-14 | 2020-01-06 | 2020-01-06 | COMP | 2020-06-17 | COMP | 2020-07-17 | COMP | 2020-07-19 | COMP | 2020-08-12 | COMP | Rule 16 | 74 | 76 | 115 | 23 | 1 | 18 | 304
14587 | 2019-05-31 | 2019-09-17 | 2020-03-19 | 2020-11-30 | COMP | 2021-01-04 | COMP | 2021-01-04 | COMP | 2020-12-07 | COMP | 2021-02-20 | COMP | Rule 15/16 | 76 | 126 | 24 | 1 | 0 | 33 | 433
14817 | 2019-05-31 | 2019-09-30 | 2020-02-26 | 2020-02-26 | COMP | 2021-04-01 | COMP | 2021-04-01 | COMP | 2021-03-30 | COMP | 2021-05-05 | COMP | Rule 15/16 | 85 | 101 | 278 | 1 | 0 | 25 | 486
14830 | 2019-05-31 | 2019-10-01 | 2020-09-18 | 2020-09-18 | COMP | 2021-08-10 | COMP | 2021-08-10 | COMP | 2021-12-14 | COMP | 2022-02-19 | COMP | Rule 15/16 | 86 | 245 | 224 | 1 | 87 | 48 | 686
14836 | 2019-05-31 | 2019-09-30 | 2020-07-01 | 2020-12-28 | COMP | 2021-03-03 | COMP | 2021-03-05 | COMP | 2021-02-23 | COMP | 2021-05-04 | COMP | Rule 15/16 | 85 | 190 | 45 | 3 | 0 | 43 | 485
15158 | 2019-05-31 | 2019-10-16 | 2020-01-02 | 2020-01-02 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2021-03-23 | COMP | 2021-03-24 | COMP | Rule 15/16 | 97 | 52 | 22 | 1 | 287 | 2 | 456
17339 | 2019-05-31 | 2020-02-10 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2021-04-20 | COMP | 2021-04-21 | COMP | Rule 16 | 174 | 37 | 16 | 1 | 251 | 2 | 476
12356 | 2019-06-01 | 2019-06-03 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-15 | NOTN | 2020-01-16 | COMP | 2020-01-31 | COMP | 2020-03-03 | COMP | Other | 1 | 49 |  | 109 | 11 | 22 | 188
12607 | 2019-06-01 | 2019-06-14 | 2019-08-29 | 2019-08-29 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-03-01 | INPR | 2019-10-18 | COMP | Rule 16 | 10 | 54 | 8 | 1 |  |  | 98
13381 | 2019-06-01 | 2019-07-23 | 2019-12-24 | 2019-12-24 | COMP | 2020-01-03 | COMP | 2020-01-10 | COMP | 2020-03-02 | COMP | 2020-06-03 | COMP | Rule 15/16 | 36 | 107 | 7 | 6 | 35 | 67 | 253
26015 | 2019-06-01 | 2021-03-04 | 2021-06-25 | 2021-06-25 | COMP | 2022-01-26 | COMP | 2022-01-28 | COMP | 2022-01-26 | COMP | 2022-03-26 | COMP | Rule 16 | 441 | 81 | 148 | 3 | 0 | 40 | 709
15114 | 2019-06-02 | 2019-10-14 | 2020-01-13 | 2020-03-09 | COMP | 2020-06-04 | COMP | 2020-06-09 | COMP | 2020-07-10 | COMP | 2020-07-23 | COMP | Rule 16 | 94 | 61 | 63 | 4 | 24 | 10 | 289
12442 | 2019-06-03 | 2019-06-06 | 2019-06-22 | 2019-06-22 | COMP | 2019-07-15 | NOTN | 2019-07-12 | COMP | 2019-07-12 | COMP | 2019-07-15 | COMP | Rule 16 | 4 | 12 |  | 14 | 1 | 2 | 30
12803 | 2019-06-03 | 2019-06-24 | 2019-08-24 | 2019-09-14 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-11-05 | COMP | 2020-01-03 | COMP | Rule 16 | 16 | 44 | 13 | 1 | 25 | 39 | 148
12883 | 2019-06-03 | 2019-06-26 | 2019-10-23 | 2019-10-23 | COMP | 2019-10-29 | COMP | 2019-12-09 | COMP | 2019-12-17 | COMP | 2020-01-08 | COMP | Rule 16 | 18 | 84 | 5 | 27 | 7 | 15 | 151
12888 | 2019-06-03 | 2019-06-28 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2020-02-04 | COMP | 2020-03-04 | COMP | Rule 16 | 20 | 81 | 10 | 1 | 61 | 21 | 189
13059 | 2019-06-03 | 2019-07-09 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-12-09 | COMP | Rule 16 | 26 | 57 | 19 | 1 | 1 | 32 | 131
13108 | 2019-06-03 | 2019-07-10 | 2019-12-06 | 2019-12-06 | COMP | 2019-12-20 | COMP | 2020-07-07 | COMP | 2020-07-08 | COMP | 2020-09-16 | COMP | Rule 16 | 27 | 104 | 11 | 138 | 2 | 50 | 327
13231 | 2019-06-03 | 2019-07-17 | 2020-01-28 | 2020-01-28 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-09-29 | COMP | 2020-11-14 | COMP | Rule 16 | 32 | 133 | 27 | 1 | 147 | 33 | 368
13267 | 2019-06-03 | 2019-07-18 | 2019-09-17 | 2019-09-17 | COMP | 2019-09-26 | COMP | 2019-09-26 | COMP | 2019-11-06 | COMP | 2019-12-20 | COMP | Rule 16 | 33 | 43 | 8 | 1 | 30 | 30 | 140
13552 | 2019-06-03 | 2019-07-31 | 2019-12-19 | 2019-12-19 | COMP | 2019-12-20 | NOTN | 2020-01-30 | COMP | 2020-01-31 | COMP | 2020-07-02 | COMP | Other | 42 | 98 |  | 28 | 2 | 108 | 274
13904 | 2019-06-03 | 2019-08-15 | 2019-10-01 | 2019-10-20 | COMP | 2019-10-25 | COMP | 2019-12-02 | COMP | 2019-12-03 | COMP | 2019-12-05 | COMP | Rule 16 | 53 | 33 | 5 | 24 | 2 | 3 | 129
14745 | 2019-06-03 | 2019-09-25 | 2020-01-04 | 2020-01-24 | COMP | 2020-01-24 | NOTN | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-06-26 | COMP | Other | 81 | 68 |  |  | 1 | 122 | 270
14753 | 2019-06-03 | 2019-09-25 | 2019-11-19 | 2020-11-25 | COMP | 2021-01-05 | COMP | 2021-02-24 | INPR | 2021-01-25 | COMP | 2021-02-23 | COMP | Rule 15/16 | 81 | 39 | 26 |  |  |  | 434
15392 | 2019-06-03 | 2019-10-30 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-16 | COMP | 2020-08-28 | COMP | 2021-06-29 | COMP | 2021-07-13 | COMP | Rule 16 | 106 | 30 | 23 | 159 | 209 | 10 | 532
15638 | 2019-06-03 | 2019-11-13 | 2020-01-14 | 2020-01-18 | COMP | 2020-03-02 | COMP | 2020-03-09 | COMP | 2020-04-06 | COMP | 2020-08-29 | COMP | Rule 16 | 115 | 41 | 29 | 6 | 21 | 104 | 315
15724 | 2019-06-03 | 2019-11-18 | 2020-05-19 | 2020-06-04 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-06-18 | COMP | 2020-08-07 | COMP | Rule 16 | 118 | 126 | 14 | 1 | 0 | 34 | 300
16139 | 2019-06-03 | 2019-12-11 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-02 | COMP | 2020-04-28 | COMP | 2020-06-08 | COMP | 2020-07-09 | COMP | Rule 15/16 | 133 | 68 | 11 | 19 | 29 | 24 | 279
16346 | 2019-06-03 | 2019-12-23 | 2020-03-20 | 2020-03-20 | COMP | 2020-07-13 | COMP | 2020-10-01 | COMP | 2021-01-25 | COMP | 2021-02-23 | COMP | Rule 16 | 141 | 61 | 81 | 58 | 77 | 21 | 434
16399 | 2019-06-03 | 2019-12-27 | 2020-02-14 | 2020-02-14 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2021-09-07 | COMP | 2021-10-15 | COMP | Rule 16 | 144 | 34 | 71 | 1 | 325 | 29 | 599
16419 | 2019-06-03 | 2019-12-31 | 2020-05-03 | 2020-05-03 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-07-28 | COMP | 2020-08-10 | COMP | Rule 16 | 146 | 86 | 10 | 1 | 52 | 10 | 301
16489 | 2019-06-03 | 2020-01-04 | 2020-01-18 | 2020-01-18 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-24 | COMP | 2020-03-05 | COMP | Rule 16 | 148 | 10 | 15 | 1 | 10 | 9 | 190
16817 | 2019-06-03 | 2020-01-16 | 2020-03-14 | 2020-03-14 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-12-02 | COMP | 2020-12-21 | COMP | Rule 15/16 | 157 | 40 | 89 | 1 | 95 | 14 | 392
16936 | 2019-06-03 | 2020-01-25 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-15 | COMP | 2020-10-14 | COMP | 2021-01-19 | COMP | 2021-02-11 | COMP | Rule 15/16 | 162 | 47 | 11 | 129 | 64 | 18 | 427
17980 | 2019-06-03 | 2020-03-06 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-31 | COMP | 2020-09-11 | COMP | 2020-11-10 | COMP | 2021-01-08 | COMP | Rule 16 | 191 | 111 | 16 | 9 | 43 | 39 | 404
32095 | 2019-06-03 | 2021-11-03 | 2022-02-24 | 2022-02-24 | COMP | 2022-02-26 | NOTN | 2022-03-15 | COMP | 2022-04-11 | COMP | 2022-05-03 | COMP | Other | 612 | 77 |  | 14 | 20 | 17 | 736
4213 | 2019-06-04 | 2019-07-26 | 2019-11-06 | 2019-11-06 | COMP | 2021-03-23 | COMP | 2022-03-09 | COMP | 2022-05-05 | COMP | 2022-05-19 | COMP | Rule 16 | 38 | 73 | 344 | 244 | 42 | 11 | 747
4214 | 2019-06-04 | 2019-07-26 | 2019-11-13 | 2019-11-13 | COMP | 2021-03-23 | COMP | 2022-05-11 | COMP | 2022-07-19 | COMP | 2022-09-02 | COMP | Rule 16 | 38 | 77 | 340 | 289 | 47 | 34 | 820
12372 | 2019-06-04 | 2019-06-04 | 2019-06-25 | 2019-06-25 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2021-01-30 | INPR | 2020-01-03 | COMP | Rule 16 | 1 | 16 | 105 | 1 |  |  | 147
12534 | 2019-06-04 | 2019-06-12 | 2019-09-07 | 2019-09-07 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-10-10 | COMP | 2019-11-04 | COMP | Rule 16 | 7 | 61 | 9 | 1 | 16 | 18 | 108
12584 | 2019-06-04 | 2019-06-14 | 2019-10-25 | 2019-10-25 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-04-30 | COMP | 2020-06-19 | COMP | Rule 16 | 9 | 94 | 34 | 1 | 95 | 36 | 264
12611 | 2019-06-04 | 2019-06-17 | 2019-07-21 | 2019-07-21 | COMP | 2020-03-16 | COMP | 2020-04-22 | COMP | 2020-08-05 | COMP | 2020-09-04 | COMP | Rule 16 | 10 | 24 | 163 | 28 | 75 | 23 | 319
12688 | 2019-06-04 | 2019-06-18 | 2019-10-08 | 2019-10-08 | COMP | 2020-04-10 | NOTN | 2020-05-20 | COMP | 2020-04-13 | COMP | 2020-06-26 | COMP | Other | 11 | 79 |  | 155 | 0 | 27 | 269
12722 | 2019-06-04 | 2019-06-19 | 2019-07-25 | 2019-07-25 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-09-19 | COMP | 2020-02-04 | COMP | Rule 16 | 12 | 26 | 37 | 1 | 4 | 93 | 168
12828 | 2019-06-04 | 2019-06-25 | 2019-07-31 | 2019-07-31 | COMP | 2019-08-09 | COMP | 2020-01-23 | COMP | 2020-01-17 | COMP | 2019-08-12 | COMP | Rule 16 | 16 | 26 | 8 | 113 | 0 |  | 49
12900 | 2019-06-04 | 2019-06-27 | 2019-10-23 | 2019-10-23 | COMP | 2019-12-19 | NOTN | 2019-12-31 | COMP | 2019-12-19 | COMP | 2020-03-25 | COMP | Other | 18 | 83 |  | 46 | 0 | 59 | 203
13044 | 2019-06-04 | 2019-07-08 | 2019-08-23 | 2019-08-26 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2021-03-27 | INPR | 2020-03-06 | COMP | Rule 16 | 24 | 35 | 80 | 1 |  |  | 190
13215 | 2019-06-04 | 2019-07-16 | 2019-11-17 | 2019-11-17 | COMP | 2019-12-02 | COMP | 2019-12-16 | COMP | 2020-01-27 | COMP | 2020-02-19 | COMP | Rule 15/16 | 30 | 87 | 9 | 11 | 28 | 17 | 178
13216 | 2019-06-04 | 2019-07-17 | 2019-10-23 | 2019-11-06 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2023-05-19 | COMP | 2023-10-12 | COMP | Rule 16 | 31 | 70 | 213 | 1 | 676 | 101 | 1097
13476 | 2019-06-04 | 2019-07-26 | 2020-06-03 | 2020-06-03 | COMP | 2020-07-22 | COMP | 2020-09-18 | COMP | 2020-12-03 | COMP | 2021-01-20 | COMP | Rule 15/16 | 38 | 215 | 36 | 42 | 52 | 32 | 410
13640 | 2019-06-04 | 2019-08-03 | 2020-04-30 | 2020-05-08 | COMP | 2020-07-13 | COMP | 2021-02-11 | COMP | 2021-02-11 | COMP | 2021-03-27 | COMP | Rule 16 | 43 | 186 | 46 | 147 | 1 | 31 | 456
13719 | 2019-06-04 | 2019-08-06 | 2019-10-28 | 2019-10-28 | COMP | 2019-11-05 | COMP | 2019-12-27 | COMP | 2019-12-23 | COMP | 2020-06-09 | COMP | Rule 16 | 45 | 59 | 7 | 35 | 0 | 114 | 256
13764 | 2019-06-04 | 2019-08-08 | 2019-08-13 | 2019-08-13 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | Rule 16 | 47 | 4 | 13 | 1 | 66 | 1 | 127
13786 | 2019-06-04 | 2019-08-09 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | 2020-04-22 | COMP | 2020-08-14 | COMP | Rule 15/16 | 48 | 102 | 33 | 1 | 43 | 82 | 304
13820 | 2019-06-04 | 2019-08-12 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-07 | NOTN | 2020-01-16 | COMP | 2020-01-07 | COMP | 2020-02-18 | COMP | Other | 49 | 101 |  | 8 | 0 | 22 | 177
13918 | 2019-06-04 | 2019-08-16 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-02-19 | COMP | 2020-03-09 | COMP | Rule 16 | 53 | 82 | 31 | 1 | 15 | 14 | 191
14564 | 2019-06-04 | 2019-09-16 | 2020-01-26 | 2020-01-26 | COMP | 2020-02-10 | COMP | 2020-02-21 | COMP | 2020-03-06 | COMP | 2020-03-17 | COMP | Rule 16 | 73 | 89 | 11 | 9 | 11 | 8 | 197
15247 | 2019-06-04 | 2019-10-22 | 2020-03-27 | 2020-03-27 | COMP | 2020-05-11 | COMP | 2020-11-04 | COMP | 2023-09-02 | INPR | 2020-11-13 | COMP | Rule 16 | 99 | 107 | 32 | 126 |  |  | 367
15356 | 2019-06-04 | 2019-10-29 | 2020-04-03 | 2020-04-30 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-06-22 | COMP | 2020-07-22 | COMP | Rule 16 | 104 | 107 | 15 | 1 | 23 | 23 | 287
15991 | 2019-06-04 | 2019-12-04 | 2020-03-12 | 2020-03-12 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2021-11-09 | COMP | 2021-12-03 | COMP | Rule 16 | 127 | 68 | 24 | 1 | 399 | 16 | 630
16069 | 2019-06-04 | 2019-12-08 | 2020-02-14 | 2020-02-14 | COMP | 2020-02-25 | COMP | 2020-03-18 | COMP | 2020-03-31 | COMP | 2020-06-01 | COMP | Rule 16 | 129 | 47 | 7 | 17 | 10 | 44 | 250
16780 | 2019-06-04 | 2020-01-15 | 2020-02-03 | 2020-02-12 | COMP | 2020-04-27 | COMP | 2020-05-02 | COMP | 2020-04-28 | COMP | 2020-06-05 | COMP | Rule 16 | 155 | 13 | 53 | 5 | 0 | 24 | 254
17560 | 2019-06-04 | 2020-02-20 | 2020-05-28 | 2020-05-28 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2022-11-21 | COMP | 2022-12-19 | COMP | Rule 16 | 179 | 70 | 82 | 1 | 546 | 19 | 892
17892 | 2019-06-04 | 2020-03-03 | 2020-04-28 | 2022-05-31 | COMP | 2022-06-29 | COMP | 2023-01-24 | COMP | 2023-01-24 | COMP | 2023-03-08 | COMP | Rule 16 | 187 | 41 | 21 | 142 | 1 | 31 | 945
12465 | 2019-06-05 | 2019-06-08 | 2019-06-28 | 2019-06-28 | COMP | 2019-06-24 | NOTN | 2019-06-28 | COMP | 2019-06-24 | COMP | 2019-07-11 | COMP | Other | 3 | 15 |  | 1 | 0 | 9 | 26
12502 | 2019-06-05 | 2019-06-10 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-25 | COMP | 2019-12-27 | COMP | 2020-04-27 | COMP | 2020-06-03 | COMP | Rule 16 | 4 | 88 | 11 | 42 | 84 | 27 | 251
12600 | 2019-06-05 | 2019-06-14 | 2019-07-11 | 2019-07-11 | COMP | 2020-01-14 | COMP | 2020-01-14 | COMP | 2020-02-25 | COMP | 2020-02-22 | COMP | Rule 16 | 8 | 19 | 128 | 1 | 29 |  | 179
12761 | 2019-06-05 | 2019-06-21 | 2019-08-15 | 2019-08-15 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2020-02-25 | COMP | 2020-04-02 | COMP | Rule 16 | 13 | 39 | 42 | 1 | 90 | 28 | 208
12909 | 2019-06-05 | 2019-06-28 | 2019-10-22 | 2019-10-22 | COMP | 2019-12-03 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2020-01-28 | COMP | Rule 15/16 | 18 | 81 | 28 | 6 | 1 | 33 | 162
12928 | 2019-06-05 | 2019-07-03 | 2019-09-03 | 2019-10-24 | COMP | 2019-12-27 | COMP | 2020-01-08 | COMP |  |  | 2020-02-14 | COMP | Rule 15/16 | 21 | 43 | 43 | 8 |  |  | 175
12929 | 2019-06-05 | 2019-07-03 | 2019-11-25 | 2019-11-25 | COMP | 2020-11-18 | COMP | 2020-11-18 | COMP |  |  | 2021-01-22 | COMP | Rule 16 | 21 | 101 | 249 | 1 |  |  | 411
13274 | 2019-06-05 | 2019-07-18 | 2019-10-31 | 2019-10-31 | COMP | 2019-11-12 | COMP | 2019-11-21 | COMP | 2019-11-19 | COMP | 2019-11-29 | COMP | Rule 15/16 | 31 | 75 | 8 | 8 | 0 | 5 | 123
13327 | 2019-06-05 | 2019-07-21 | 2019-11-22 | 2019-11-22 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-01-27 | COMP | 2020-01-28 | COMP | Rule 16 | 32 | 88 | 4 | 1 | 39 | 2 | 162
13354 | 2019-06-05 | 2019-07-22 | 2020-07-06 | 2020-07-06 | COMP | 2021-03-17 | COMP | 2021-04-30 | COMP | 2021-03-28 | COMP | 2021-06-26 | COMP | Rule 16 | 33 | 242 | 175 | 33 | 0 | 40 | 519
13409 | 2019-06-05 | 2019-07-24 | 2019-10-31 | 2019-10-31 | COMP | 2019-12-17 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-05-29 | COMP | Rule 16 | 35 | 71 | 31 | 47 | 1 | 68 | 248
13526 | 2019-06-05 | 2019-07-29 | 2019-11-16 | 2019-11-16 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2021-09-13 | COMP | 2021-10-22 | COMP | Rule 16 | 38 | 78 | 108 | 1 | 351 | 30 | 602
13699 | 2019-06-05 | 2019-08-06 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-26 | COMP | 2019-10-09 | COMP | 2020-06-30 | COMP | 2020-07-27 | COMP | Rule 16 | 44 | 29 | 9 | 10 | 182 | 20 | 289
14232 | 2019-06-05 | 2019-08-29 | 2020-02-05 | 2020-04-20 | COMP | 2020-07-06 | COMP | 2020-09-23 | COMP | 2020-12-17 | COMP | 2021-02-22 | COMP | Rule 16 | 61 | 108 | 55 | 57 | 59 | 44 | 431
14515 | 2019-06-05 | 2019-09-13 | 2019-11-20 | 2020-04-08 | COMP | 2020-04-13 | COMP | 2020-06-11 | COMP | 2020-07-09 | COMP | 2020-06-13 | COMP | Rule 16 | 71 | 48 | 4 | 43 | 21 |  | 258
14736 | 2019-06-05 | 2019-09-25 | 2019-11-12 | 2019-11-12 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-02-14 | COMP | Rule 16 | 79 | 34 | 40 | 1 | 1 | 25 | 175
15025 | 2019-06-05 | 2019-10-09 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-31 | COMP | 2021-12-27 | COMP | 2021-11-19 | COMP | 2022-02-08 | COMP | Rule 15/16 | 89 | 210 | 17 | 332 | 0 | 31 | 675
15068 | 2019-06-05 | 2019-10-10 | 2019-11-03 | 2019-11-03 | COMP | 2021-03-23 | COMP | 2021-03-23 | INPR | 2021-04-12 | COMP | 2021-04-20 | COMP | Rule 16 | 90 | 17 | 346 |  |  |  | 472
15069 | 2019-06-05 | 2019-10-10 | 2019-11-19 | 2021-02-23 | COMP | 2021-03-23 | COMP | 2021-03-23 | COMP | 2021-04-12 | COMP | 2021-04-20 | COMP | Rule 16 | 90 | 28 | 21 | 1 | 15 | 7 | 472
15100 | 2019-06-05 | 2019-10-11 | 2020-02-03 | 2020-02-07 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-06-16 | COMP | 2020-08-07 | COMP | Rule 16 | 91 | 76 | 41 | 1 | 51 | 39 | 298
15263 | 2019-06-05 | 2019-10-23 | 2019-12-04 | 2019-12-04 | COMP | 2020-03-25 | COMP | 2020-03-26 | COMP | 2020-08-21 | COMP | 2020-10-23 | COMP | Rule 16 | 99 | 28 | 77 | 2 | 106 | 45 | 352
15331 | 2019-06-05 | 2019-10-28 | 2020-02-20 | 2020-02-20 | COMP | 2020-05-19 | COMP | 2021-04-29 | COMP | 2021-04-23 | COMP | 2021-07-12 | COMP | Rule 16 | 102 | 77 | 64 | 239 | 0 | 51 | 529
15645 | 2019-06-05 | 2019-11-13 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-27 | COMP | 2020-07-15 | COMP | 2021-01-13 | COMP | 2021-03-03 | COMP | Rule 15/16 | 113 | 106 | 29 | 36 | 125 | 34 | 438
15719 | 2019-06-05 | 2019-11-18 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-22 | COMP | 2020-06-24 | COMP | 2020-08-10 | COMP | 2020-09-18 | COMP | Rule 15/16 | 116 | 80 | 28 | 45 | 34 | 29 | 327
16033 | 2019-06-05 | 2019-12-06 | 2020-03-26 | 2020-03-26 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2023-02-06 | COMP | 2023-03-08 | COMP | Rule 16 | 128 | 76 | 93 | 1 | 629 | 22 | 944
16242 | 2019-06-05 | 2019-12-17 | 2020-05-02 | 2020-10-06 | COMP | 2020-10-12 | COMP | 2020-10-26 | COMP | 2023-12-03 | INPR | 2020-11-10 | COMP | Rule 16 | 135 | 95 | 5 | 11 |  |  | 364
17003 | 2019-06-05 | 2020-01-27 | 2020-02-15 | 2020-02-15 | COMP | 2020-03-12 | COMP | 2020-03-22 | COMP | 2020-04-17 | COMP | 2020-04-20 | COMP | Rule 16 | 161 | 15 | 18 | 7 | 20 | 2 | 220
18015 | 2019-06-05 | 2020-03-09 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2021-03-23 | COMP | 2021-05-06 | COMP | Rule 16 | 190 | 48 | 17 | 1 | 200 | 33 | 484
18387 | 2019-06-05 | 2020-03-23 | 2020-08-13 | 2020-08-13 | COMP | 2020-12-03 | COMP | 2020-12-03 | COMP | 2021-03-04 | COMP | 2021-11-15 | COMP | Rule 15/16 | 200 | 103 | 77 | 1 | 62 | 179 | 617
18731 | 2019-06-05 | 2020-04-06 | 2020-08-06 | 2020-08-06 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2022-07-16 | INPR | 2021-04-02 | COMP | Rule 16 | 210 | 88 | 4 | 1 |  |  | 460
18797 | 2019-06-05 | 2020-04-07 | 2020-07-10 | 2020-10-14 | COMP | 2021-02-11 | COMP | 2021-04-20 | COMP | 2021-07-26 | COMP | 2022-02-14 | COMP | Rule 15/16 | 211 | 68 | 81 | 48 | 68 | 141 | 679
19089 | 2019-06-05 | 2020-04-20 | 2020-08-11 | 2020-08-11 | COMP | 2020-11-30 | COMP | 2020-12-08 | COMP | 2021-02-08 | COMP | 2021-03-13 | COMP | Rule 16 | 220 | 81 | 76 | 7 | 42 | 24 | 445
19804 | 2019-06-05 | 2020-05-22 | 2020-09-25 | 2020-09-25 | COMP | 2020-11-30 | COMP | 2020-12-29 | COMP | 2020-12-29 | COMP | 2021-01-21 | COMP | Rule 15/16 | 244 | 89 | 44 | 21 | 1 | 16 | 410
12569 | 2019-06-06 | 2019-06-14 | 2019-07-09 | 2019-07-09 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2021-04-27 | COMP | 2021-05-06 | COMP | Rule 16 | 7 | 17 | 70 | 1 | 385 | 8 | 483
12725 | 2019-06-06 | 2019-06-20 | 2019-08-30 | 2019-08-30 | COMP | 2019-09-12 | COMP | 2019-10-03 | COMP | 2019-10-04 | COMP | 2019-12-06 | COMP | Rule 16 | 11 | 51 | 9 | 16 | 2 | 43 | 127
12821 | 2019-06-06 | 2019-06-24 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-30 | COMP | 2020-10-08 | COMP | 2020-11-02 | COMP | 2021-02-18 | COMP | Rule 15/16 | 13 | 258 | 22 | 50 | 18 | 72 | 428
12979 | 2019-06-06 | 2019-07-02 | 2020-01-31 | 2020-01-31 | COMP | 2020-04-23 | COMP | 2021-01-26 | COMP | 2021-02-23 | COMP | 2021-05-19 | COMP | Rule 15/16 | 19 | 146 | 59 | 191 | 20 | 62 | 492
13071 | 2019-06-06 | 2019-07-09 | 2019-08-27 | 2019-08-27 | COMP | 2019-09-24 | COMP | 2019-11-18 | COMP | 2019-11-23 | COMP | 2020-01-14 | COMP | Rule 16 | 23 | 36 | 20 | 39 | 5 | 33 | 152
13097 | 2019-06-06 | 2019-07-10 | 2019-07-19 | 2019-07-19 | COMP | 2019-07-25 | COMP | 2019-07-25 | COMP | 2019-09-19 | COMP | 2019-10-07 | COMP | Rule 16 | 24 | 8 | 5 | 1 | 40 | 13 | 86
13189 | 2019-06-06 | 2019-07-15 | 2019-09-12 | 2019-09-13 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2021-02-02 | COMP | 2021-03-31 | COMP | Rule 15/16 | 27 | 43 | 15 | 1 | 334 | 41 | 457
13197 | 2019-06-06 | 2019-07-16 | 2019-09-13 | 2019-09-13 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-11-15 | COMP | 2019-10-10 | COMP | Rule 16 | 28 | 43 | 14 | 1 | 32 |  | 89
13294 | 2019-06-06 | 2019-07-19 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-12 | COMP | 2020-02-10 | COMP | 2019-12-04 | COMP | 2020-03-10 | COMP | Rule 15/16 | 31 | 89 | 13 | 40 | 0 | 21 | 190
13951 | 2019-06-06 | 2019-08-19 | 2019-12-15 | 2019-12-15 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-03-17 | COMP | 2020-07-20 | COMP | Rule 16 | 52 | 81 | 43 | 1 | 21 | 89 | 283
13974 | 2019-06-06 | 2019-08-19 | 2019-10-21 | 2019-10-21 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2019-11-08 | COMP | 2020-04-16 | COMP | Rule 16 | 52 | 45 | 11 | 1 | 5 | 108 | 217
14210 | 2019-06-06 | 2019-08-29 | 2019-10-22 | 2020-02-06 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2021-10-23 | INPR | 2020-05-13 | COMP | Rule 15/16 | 60 | 38 | 25 | 1 |  |  | 236
14285 | 2019-06-06 | 2019-09-03 | 2019-11-20 | 2019-11-20 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | 2020-03-13 | COMP | 2020-06-12 | COMP | Rule 16 | 62 | 56 | 43 | 1 | 35 | 65 | 257
14567 | 2019-06-06 | 2019-09-17 | 2020-01-30 | 2020-01-30 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-06-23 | COMP | 2020-07-16 | COMP | Rule 15/16 | 72 | 92 | 99 | 1 | 4 | 18 | 281
14709 | 2019-06-06 | 2019-09-24 | 2019-10-21 | 2019-10-21 | COMP | 2019-10-24 | COMP | 2019-10-25 | COMP | 2023-05-27 | INPR | 2020-02-26 | COMP | Rule 16 | 77 | 20 | 4 | 2 |  |  | 181
14775 | 2019-06-06 | 2019-09-26 | 2020-03-02 | 2020-03-02 | COMP | 2020-05-13 | COMP | 2020-04-28 | COMP | 2020-11-02 | COMP | 2021-01-08 | COMP | Rule 16 | 79 | 106 | 53 |  | 133 | 45 | 401
14812 | 2019-06-06 | 2019-09-28 | 2019-12-17 | 2020-04-15 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-06-01 | COMP | 2020-09-29 | COMP | Rule 16 | 80 | 54 |  | 1 | 79 | 86 | 333
14893 | 2019-06-06 | 2019-10-02 | 2019-11-25 | 2020-01-13 | COMP | 2020-02-20 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-07-14 | COMP | Rule 15/16 | 83 | 38 | 27 | 79 | 1 | 25 | 279
15450 | 2019-06-06 | 2019-11-02 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-03 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-02-11 | COMP | Rule 16 | 105 | 14 | 6 | 26 | 1 | 23 | 171
15971 | 2019-06-06 | 2019-12-04 | 2020-02-13 | 2020-02-13 | COMP | 2020-05-08 | COMP | 2020-02-21 | COMP | 2020-06-01 | COMP | 2020-07-07 | COMP | Rule 15/16 | 125 | 49 | 61 |  | 71 | 27 | 274
16015 | 2019-06-06 | 2019-12-04 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-31 | COMP | 2020-02-14 | COMP | 2020-02-05 | COMP | 2020-03-11 | COMP | Rule 16 | 125 | 26 | 15 | 11 | 0 | 18 | 191
17244 | 2019-06-06 | 2020-02-05 | 2020-03-20 | 2020-03-20 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-12-24 | COMP | 2021-01-25 | COMP | Rule 16 | 167 | 32 | 20 | 1 | 176 | 20 | 411
17818 | 2019-06-06 | 2020-02-28 | 2020-12-24 | 2020-12-24 | COMP | 2020-12-30 | COMP | 2020-12-30 | COMP | 2022-06-18 | INPR | 2021-05-21 | COMP | Rule 16 | 183 | 210 | 4 | 1 |  |  | 494
22666 | 2019-06-06 | 2020-10-06 | 2021-04-07 | 2021-04-07 | COMP | 2021-07-12 | COMP | 2021-07-12 | COMP | 2023-07-29 | INPR | 2022-01-18 | COMP | Rule 15/16 | 338 | 125 | 67 | 1 |  |  | 659
4188 | 2019-06-07 | 2019-06-19 | 2019-10-09 | 2019-10-09 | COMP | 2020-10-13 | COMP | 2020-10-14 | COMP | 2021-08-06 | COMP | 2021-09-16 | COMP | Rule 16 | 9 | 79 | 256 | 2 | 204 | 29 | 574
12608 | 2019-06-07 | 2019-06-14 | 2019-07-04 | 2019-07-04 | COMP | 2019-08-19 | COMP | 2019-08-19 | COMP | 2021-10-23 | INPR | 2020-04-24 | COMP | Rule 16 | 6 | 14 | 32 | 1 |  |  | 222
12715 | 2019-06-07 | 2019-06-20 | 2019-08-06 | 2020-01-11 | COMP | 2020-01-31 | COMP | 2019-11-08 | COMP | 2019-09-19 | COMP | 2020-08-05 | COMP | Rule 16 | 10 | 33 | 14 |  | 0 | 186 | 294
12734 | 2019-06-07 | 2019-06-19 | 2019-07-20 | 2019-07-20 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2019-07-31 | COMP | 2019-08-10 | COMP | Rule 16 | 9 | 22 | 8 | 1 | 1 | 8 | 45
12890 | 2019-06-07 | 2019-06-27 | 2019-09-06 | 2019-09-06 | COMP | 2019-09-23 | COMP | 2019-11-04 | COMP | 2019-11-15 | COMP | 2020-01-10 | COMP | Rule 16 | 15 | 50 | 12 | 31 | 9 | 37 | 149
13072 | 2019-06-07 | 2019-07-09 | 2019-09-24 | 2019-09-24 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2020-05-31 | INPR | 2019-12-06 | COMP | Rule 16 | 22 | 55 | 8 | 1 |  |  | 126
13157 | 2019-06-07 | 2019-07-13 | 2019-09-07 | 2019-09-07 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | 2020-04-26 | INPR | 2019-12-19 | COMP | Rule 16 | 25 | 39 | 4 | 1 |  |  | 135
13191 | 2019-06-07 | 2019-07-15 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-25 | COMP | 2019-10-15 | COMP | 2019-10-28 | COMP | 2019-11-18 | COMP | Rule 16 | 26 | 36 | 17 | 15 | 10 | 15 | 114
13452 | 2019-06-07 | 2019-07-25 | 2019-09-26 | 2019-09-26 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2019-12-12 | COMP | 2019-12-30 | COMP | Rule 16 | 34 | 45 | 29 | 1 | 25 | 12 | 141
13459 | 2019-06-07 | 2019-07-26 | 2019-08-28 | 2019-08-28 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-09-25 | COMP | 2019-12-18 | COMP | Rule 16 | 35 | 24 | 31 | 1 | 0 | 47 | 134
13519 | 2019-06-07 | 2019-07-29 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-17 | COMP | 2019-11-04 | COMP | 2019-11-12 | COMP | 2019-12-05 | COMP | Rule 16 | 36 | 50 | 9 | 13 | 6 | 16 | 125
13647 | 2019-06-07 | 2019-08-05 | 2019-09-18 | 2019-09-18 | COMP | 2019-12-10 | COMP | 2019-12-18 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | Rule 16 | 41 | 32 | 57 | 7 | 30 | 1 | 163
13674 | 2019-06-07 | 2019-08-05 | 2019-09-30 | 2019-09-30 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2020-02-05 | COMP | 2020-02-10 | COMP | Rule 16 | 41 | 40 | 50 | 1 | 38 | 4 | 169
13692 | 2019-06-07 | 2019-08-06 | 2019-08-23 | 2019-08-23 | COMP | 2019-09-09 | COMP | 2019-09-09 | COMP | 2019-09-30 | COMP | 2019-11-05 | COMP | Rule 16 | 42 | 14 | 11 | 1 | 16 | 27 | 106
13894 | 2019-06-07 | 2019-08-15 | 2019-08-20 | 2019-08-20 | COMP | 2019-09-13 | COMP | 2019-11-14 | COMP | 2019-11-08 | COMP | 2019-11-14 | COMP | Rule 16 | 49 | 4 | 18 | 44 | 0 | 1 | 112
13895 | 2019-06-07 | 2019-08-15 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-13 | COMP | 2019-11-14 | COMP | 2019-11-08 | COMP | 2019-11-14 | COMP | Rule 16 | 49 | 6 | 16 | 44 | 0 | 1 | 112
14059 | 2019-06-07 | 2019-08-23 | 2020-02-05 | 2020-02-05 | COMP | 2020-04-01 | COMP | 2020-09-28 | COMP | 2021-02-09 | COMP | 2021-03-25 | COMP | Rule 16 | 55 | 112 | 40 | 127 | 91 | 32 | 452
14142 | 2019-06-07 | 2019-08-27 | 2019-11-22 | 2019-11-22 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-05-19 | COMP | 2020-06-17 | COMP | Rule 16 | 57 | 62 | 45 | 1 | 78 | 21 | 259
14326 | 2019-06-07 | 2019-09-04 | 2019-10-24 | 2019-10-24 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-02-14 | COMP | Rule 16 | 62 | 37 | 57 | 1 | 1 | 20 | 173
14435 | 2019-06-07 | 2019-09-09 | 2019-09-27 | 2019-09-27 | COMP | 2019-10-08 | COMP | 2019-10-09 | INPR | 2020-01-19 | REQD | 2019-10-10 | COMP | Rule 16 | 65 | 15 | 8 |  |  |  | 88
14501 | 2019-06-07 | 2019-09-12 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-05 | COMP | 2020-04-03 | COMP | 2020-06-09 | COMP | 2020-06-11 | COMP | Rule 16 | 68 | 93 | 7 | 42 | 47 | 3 | 255
15563 | 2019-06-07 | 2019-11-07 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-26 | COMP | 2020-01-06 | COMP | 2020-01-13 | COMP | 2020-01-18 | COMP | Rule 16 | 108 | 24 | 9 | 7 | 6 | 5 | 154
15798 | 2019-06-07 | 2019-11-20 | 2020-02-27 | 2020-02-27 | COMP | 2021-05-24 | COMP | 2021-05-25 | COMP | 2021-09-26 | COMP | 2021-11-01 | COMP | Rule 16 | 116 | 66 | 314 | 2 | 86 | 26 | 606
18120 | 2019-06-07 | 2020-03-11 | 2020-08-01 | 2020-08-01 | COMP | 2020-08-11 | COMP | 2020-08-27 | COMP | 2020-11-02 | COMP | 2020-11-03 | COMP | Rule 16 | 190 | 102 | 7 | 13 | 47 | 2 | 357
18526 | 2019-06-07 | 2020-03-27 | 2020-09-21 | 2020-09-21 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2021-01-22 | COMP | 2021-02-26 | COMP | Rule 15/16 | 202 | 125 | 53 | 1 | 32 | 25 | 433
19607 | 2019-06-07 | 2020-05-16 | 2020-06-12 | 2020-06-12 | COMP | 2020-09-02 | COMP | 2020-10-22 | COMP | 2021-01-07 | COMP | 2021-02-10 | COMP | Rule 16 | 237 | 19 | 59 | 36 | 51 | 24 | 422
12517 | 2019-06-08 | 2019-06-10 | 2019-08-09 | 2019-08-09 | COMP | 2019-08-13 | NOTN | 2019-09-18 | COMP | 2019-10-01 | NOTN | 2019-11-05 | COMP | Other | 1 | 44 |  | 28 |  |  | 105
14270 | 2019-06-08 | 2019-09-03 | 2019-09-16 | 2019-09-16 | COMP | 2019-09-23 | COMP | 2019-12-24 | COMP | 2020-02-24 | COMP | 2020-03-05 | COMP | Rule 16 | 60 | 10 | 6 | 64 | 41 | 9 | 185
13061 | 2019-06-09 | 2019-07-09 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-11 | COMP | 2019-09-24 | COMP | 2019-10-21 | COMP | 2019-10-31 | COMP | Rule 16 | 21 | 41 | 6 | 10 | 20 | 9 | 102
13571 | 2019-06-09 | 2019-07-31 | 2020-04-26 | 2020-04-26 | COMP | 2020-06-13 | COMP | 2020-11-04 | COMP | 2021-06-14 | COMP | 2021-07-07 | COMP | Rule 16 | 37 | 185 | 34 | 102 | 151 | 17 | 523
18977 | 2019-06-09 | 2020-04-15 | 2020-05-19 | 2020-06-03 | COMP | 2020-06-08 | COMP | 2020-06-09 | COMP | 2020-06-19 | COMP | 2020-07-18 | COMP | Rule 16 | 214 | 25 | 4 | 2 | 9 | 21 | 280
12798 | 2019-06-10 | 2019-06-24 | 2019-09-06 | 2019-09-06 | COMP | 2019-11-27 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-20 | COMP | Rule 16 | 11 | 53 | 58 |  | 1 | 17 | 135
12967 | 2019-06-10 | 2019-07-02 | 2019-11-14 | 2019-11-14 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2019-12-19 | COMP | 2020-01-10 | COMP | Rule 16 | 17 | 95 | 8 | 1 | 17 | 15 | 148
13208 | 2019-06-10 | 2019-07-16 | 2019-10-01 | 2020-03-09 | COMP | 2020-03-20 | COMP | 2019-10-22 | COMP | 2020-02-25 | COMP | 2020-03-31 | COMP | Rule 16 | 26 | 55 | 10 |  | 84 | 26 | 203
13295 | 2019-06-10 | 2019-07-19 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-18 | COMP | 2019-12-20 | COMP | 2021-02-27 | INPR | 2020-02-16 | COMP | Rule 16 | 29 | 68 | 18 | 23 |  |  | 172
13580 | 2019-06-10 | 2019-08-01 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-02 | COMP | 2020-03-27 | COMP | 2020-04-07 | COMP | 2020-05-19 | COMP | Rule 15/16 | 38 | 138 | 8 | 20 | 8 | 31 | 238
13819 | 2019-06-10 | 2019-08-12 | 2020-02-24 | 2020-02-24 | COMP | 2021-06-24 | COMP | 2022-04-22 | COMP | 2022-04-21 | COMP | 2022-06-27 | COMP | Rule 16 | 45 | 133 | 339 | 210 | 0 | 45 | 768
13887 | 2019-06-10 | 2019-08-16 | 2019-12-06 | 2019-12-06 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-03-17 | COMP | 2020-04-15 | COMP | Rule 16 | 49 | 77 | 28 | 1 | 42 | 22 | 214
14062 | 2019-06-10 | 2019-08-23 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-14 | COMP | 2020-02-21 | COMP | 2020-02-13 | COMP | 2020-02-26 | COMP | Rule 16 | 54 | 38 | 21 | 66 | 0 | 4 | 179
14336 | 2019-06-10 | 2019-09-05 | 2020-01-06 | 2020-01-06 | COMP | 2020-04-20 | COMP | 2020-10-21 | COMP | 2020-12-10 | COMP | 2021-01-22 | COMP | Rule 16 | 62 | 83 | 74 | 131 | 34 | 29 | 408
15389 | 2019-06-10 | 2019-10-29 | 2020-01-21 | 2020-01-21 | COMP | 2020-02-24 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP | 2020-12-29 | COMP | Rule 16 | 100 | 55 | 24 | 198 | 1 | 19 | 392
15596 | 2019-06-10 | 2019-11-09 | 2020-03-04 | 2020-03-04 | COMP | 2020-06-13 | COMP | 2020-10-28 | COMP | 2020-10-30 | COMP | 2020-11-18 | COMP | Rule 15/16 | 108 | 76 | 72 | 97 | 3 | 13 | 366
16034 | 2019-06-10 | 2019-12-06 | 2019-12-30 | 2019-12-30 | COMP | 2020-02-14 | COMP | 2020-02-26 | COMP | 2020-05-05 | COMP | 2020-06-04 | COMP | Rule 16 | 125 | 16 | 33 | 8 | 50 | 22 | 249
16140 | 2019-06-10 | 2019-12-11 | 2020-04-23 | 2020-04-23 | COMP | 2020-06-18 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2021-01-05 | COMP | Rule 15/16 | 128 | 93 | 40 | 95 | 1 | 44 | 396
16341 | 2019-06-10 | 2019-12-23 | 2020-03-22 | 2020-03-22 | COMP | 2020-06-18 | COMP | 2023-04-20 | COMP | 2023-06-07 | COMP | 2023-07-28 | COMP | Rule 16 | 136 | 61 | 63 | 714 | 34 | 36 | 1040
16587 | 2019-06-10 | 2020-01-08 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-05-13 | COMP | 2020-06-10 | COMP | Rule 16 | 146 | 36 | 24 | 1 | 31 | 20 | 253
18592 | 2019-06-10 | 2020-03-30 | 2020-11-09 | 2020-11-09 | COMP | 2021-02-18 | COMP | 2021-02-18 | COMP | 2021-07-20 | COMP | 2021-07-07 | COMP | Other | 202 | 159 | 67 | 1 | 107 |  | 523
12484 | 2019-06-11 | 2019-06-11 | 2019-07-11 | 2019-07-11 | COMP | 2019-07-18 | COMP | 2019-07-24 | COMP | 2019-07-25 | COMP | 2019-07-26 | COMP | Rule 16 | 1 | 22 | 6 | 5 | 2 | 2 | 33
12705 | 2019-06-11 | 2019-06-19 | 2019-08-31 | 2019-08-31 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-09-23 | COMP | 2020-10-27 | COMP | Rule 15/16 | 7 | 52 | 253 | 1 | 16 | 25 | 350
12738 | 2019-06-11 | 2019-06-20 | 2019-07-02 | 2019-07-02 | COMP | 2019-07-08 | COMP | 2019-07-08 | COMP | 2019-07-01 | COMP | 2019-07-10 | COMP | Rule 16 | 8 | 9 | 4 | 1 | 0 | 3 | 21
12832 | 2019-06-11 | 2019-06-25 | 2019-07-25 | 2019-07-25 | COMP | 2019-08-05 | COMP | 2019-08-05 | COMP | 2020-01-16 | COMP | 2020-01-17 | COMP | Rule 16 | 11 | 22 | 8 | 1 | 113 | 2 | 152
12857 | 2019-06-11 | 2019-06-25 | 2019-07-02 | 2019-07-02 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2019-09-30 | COMP | 2019-10-18 | COMP | Rule 16 | 11 | 6 | 54 | 1 | 10 | 15 | 92
12870 | 2019-06-11 | 2019-06-26 | 2019-08-27 | 2019-08-27 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-01-16 | COMP | 2020-01-25 | COMP | Rule 16 | 12 | 44 | 87 | 1 | 11 | 6 | 156
12911 | 2019-06-11 | 2019-06-28 | 2019-10-06 | 2019-10-06 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-03-25 | COMP | 2020-05-04 | COMP | Rule 16 | 14 | 69 | 64 | 1 | 53 | 29 | 226
13006 | 2019-06-11 | 2019-07-05 | 2020-02-21 | 2020-02-21 | COMP | 2020-08-11 | COMP | 2020-09-03 | COMP | 2020-08-22 | COMP | 2020-10-22 | COMP | Rule 15/16 | 18 | 158 | 122 | 18 | 0 | 35 | 347
13043 | 2019-06-11 | 2019-07-08 | 2019-08-31 | 2019-08-31 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2022-06-18 | INPR | 2021-03-23 | COMP | Rule 15/16 | 19 | 40 | 265 | 1 |  |  | 448
13162 | 2019-06-11 | 2019-07-15 | 2019-09-11 | 2021-10-12 | COMP | 2021-10-19 | COMP | 2021-10-19 | COMP | 2021-10-20 | COMP | 2022-05-05 | COMP | Rule 16 | 24 | 42 | 6 | 1 | 2 | 137 | 732
13560 | 2019-06-11 | 2019-07-31 | 2020-01-17 | 2020-01-17 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | 2020-09-18 | COMP | 2020-10-16 | COMP | Rule 16 | 36 | 117 | 156 | 1 | 17 | 21 | 343
13587 | 2019-06-11 | 2019-07-31 | 2019-10-25 | 2019-10-25 | COMP | 2021-04-24 | INPR | 2019-12-13 | COMP | 2020-03-10 | COMP | 2020-03-27 | COMP | Rule 16 | 36 | 62 |  | 33 | 59 | 14 | 200
13722 | 2019-06-11 | 2019-08-07 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2020-03-21 | INPR | 2019-11-22 | COMP | Rule 16 | 41 | 41 | 9 | 1 |  |  | 116
13865 | 2019-06-11 | 2019-08-14 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-13 | COMP | 2019-11-14 | COMP | 2019-12-09 | COMP | 2020-03-05 | COMP | Rule 16 | 46 | 51 | 14 | 2 | 16 | 60 | 184
13931 | 2019-06-11 | 2019-08-16 | 2021-03-18 | 2021-03-18 | COMP | 2021-03-29 | COMP | 2021-04-28 | COMP | 2021-05-06 | COMP | 2021-06-02 | COMP | Rule 16 | 48 | 398 | 8 | 23 | 7 | 19 | 498
13935 | 2019-06-11 | 2019-08-16 | 2019-11-26 | 2019-11-26 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-07-21 | COMP | 2020-07-30 | COMP | Rule 16 | 48 | 71 | 82 | 1 | 83 | 8 | 288
13936 | 2019-06-11 | 2019-08-16 | 2020-04-22 | 2020-08-31 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2023-12-09 | INPR | 2020-12-08 | COMP | Rule 16 | 48 | 171 | 24 | 1 |  |  | 377
14309 | 2019-06-11 | 2019-09-04 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-04 | COMP | 2020-04-23 | COMP | 2020-09-03 | COMP | 2020-09-09 | COMP | Rule 16 | 60 | 36 | 9 | 117 | 95 | 4 | 316
14462 | 2019-06-11 | 2019-09-11 | 2019-10-08 | 2019-10-08 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2020-08-25 | COMP | 2020-08-26 | COMP | Rule 16 | 65 | 20 | 220 | 1 | 4 | 2 | 307
14463 | 2019-06-11 | 2019-09-11 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-09-03 | COMP | 2020-09-09 | COMP | Rule 16 | 65 | 28 | 17 | 1 | 205 | 4 | 316
14685 | 2019-06-11 | 2019-09-23 | 2020-01-24 | 2020-01-24 | COMP | 2020-01-29 | COMP | 2020-02-04 | COMP | 2020-01-29 | COMP | 2020-02-13 | COMP | Rule 16 | 73 | 84 | 4 | 5 | 0 | 8 | 170
14704 | 2019-06-11 | 2019-09-24 | 2019-12-17 | 2019-12-17 | COMP | 2019-12-23 | COMP | 2020-01-13 | COMP | 2020-01-30 | COMP | 2020-02-24 | COMP | Rule 16 | 74 | 58 | 5 | 14 | 13 | 17 | 176
15518 | 2019-06-11 | 2019-11-05 | 2020-01-21 | 2020-01-21 | COMP | 2020-01-27 | COMP | 2020-02-18 | COMP | 2020-02-27 | COMP | 2020-04-23 | COMP | Rule 16 | 104 | 50 | 5 | 16 | 8 | 41 | 219
15803 | 2019-06-11 | 2019-11-20 | 2020-02-29 | 2020-02-29 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-05-13 | COMP | 2020-08-25 | COMP | Rule 16 | 114 | 67 | 106 | 1 | 0 | 21 | 306
15834 | 2019-06-11 | 2019-11-22 | 2020-04-08 | 2020-04-08 | COMP | 2022-02-09 | COMP | 2022-02-09 | COMP | 2022-03-02 | COMP | 2022-04-03 | COMP | Rule 16 | 116 | 93 | 465 | 1 | 15 | 23 | 708
15950 | 2019-06-11 | 2019-12-03 | 2020-02-15 | 2020-02-15 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-05-18 | COMP | 2020-07-14 | COMP | Rule 15/16 | 121 | 51 | 21 | 1 | 45 | 41 | 276
16547 | 2019-06-11 | 2020-01-07 | 2020-04-20 | 2020-10-02 | COMP | 2020-10-06 | COMP | 2020-10-06 | COMP | 2021-03-16 | COMP | 2021-04-30 | COMP | Rule 16 | 144 | 73 | 3 | 1 | 109 | 34 | 476
18427 | 2019-06-11 | 2020-03-23 | 2020-07-25 | 2020-11-16 | COMP | 2021-01-27 | COMP | 2021-01-27 | COMP | 2021-09-21 | COMP | 2021-10-06 | COMP | Rule 16 | 196 | 89 | 48 | 1 | 166 | 12 | 586
18715 | 2019-06-11 | 2020-04-03 | 2020-09-09 | 2023-01-28 | COMP | 2023-02-09 | COMP | 2023-03-09 | COMP | 2023-04-25 | COMP | 2023-05-31 | COMP | Rule 16 | 205 | 112 | 9 | 20 | 34 | 26 | 999
4189 | 2019-06-12 | 2019-06-19 | 2019-08-14 | 2019-08-14 | COMP | 2019-09-19 | COMP | 2019-10-01 | COMP | 2021-04-22 | COMP | 2021-05-26 | COMP | Rule 15/16 | 6 | 40 | 26 | 9 | 392 | 25 | 493
12574 | 2019-06-12 | 2019-06-13 | 2019-06-29 | 2019-10-05 | COMP | 2019-10-14 | COMP | 2019-10-08 | COMP | 2019-09-11 | COMP | 2019-10-21 | COMP | Rule 16 | 2 | 12 | 6 |  | 0 | 10 | 92
12613 | 2019-06-12 | 2019-06-17 | 2019-12-24 | 2020-07-20 | COMP | 2020-09-14 | COMP | 2021-01-12 | COMP | 2021-02-08 | COMP | 2021-03-29 | COMP | Rule 16 | 4 | 132 | 40 | 82 | 19 | 35 | 451
12614 | 2019-06-12 | 2019-06-17 | 2019-11-05 | 2019-11-12 | COMP | 2020-01-07 | COMP | 2020-09-15 | COMP | 2021-02-01 | COMP | 2021-02-02 | COMP | Rule 15/16 | 4 | 100 | 37 | 177 | 94 | 2 | 413
12735 | 2019-06-12 | 2019-06-19 | 2019-07-30 | 2019-07-30 | COMP | 2019-08-07 | COMP | 2019-08-07 | COMP | 2019-08-05 | COMP | 2019-08-10 | COMP | Rule 16 | 6 | 29 | 7 | 1 | 0 | 3 | 42
12774 | 2019-06-12 | 2019-06-21 | 2019-10-05 | 2019-10-05 | COMP | 2019-11-27 | COMP | 2019-11-19 | COMP | 2019-10-23 | COMP | 2019-12-26 | COMP | Rule 16 | 8 | 74 | 37 |  | 0 | 25 | 136
12805 | 2019-06-12 | 2019-06-24 | 2019-12-13 | 2019-12-13 | COMP | 2020-02-26 | COMP | 2020-04-07 | COMP | 2020-06-16 | COMP | 2020-07-30 | COMP | Rule 15/16 | 9 | 120 | 50 | 30 | 50 | 33 | 287
12837 | 2019-06-12 | 2019-06-24 | 2020-05-27 | 2020-10-06 | COMP | 2020-12-24 | COMP | 2021-10-11 | COMP | 2021-10-11 | COMP | 2021-11-18 | COMP | Rule 16 | 9 | 233 | 55 | 201 | 1 | 28 | 615
12970 | 2019-06-12 | 2019-07-02 | 2019-10-05 | 2019-10-05 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2020-03-12 | COMP | 2020-05-26 | COMP | Rule 16 | 15 | 67 | 53 | 1 | 55 | 53 | 240
13075 | 2019-06-12 | 2019-07-10 | 2019-10-11 | 2020-04-15 | COMP | 2020-04-28 | COMP | 2019-12-06 | COMP | 2020-05-11 | COMP | 2020-05-22 | COMP | Rule 16 | 20 | 67 | 10 |  | 108 | 10 | 239
13101 | 2019-06-12 | 2019-07-10 | 2020-01-23 | 2020-01-23 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-04-06 | COMP | 2020-06-22 | COMP | Rule 16 | 20 | 135 | 11 | 1 | 42 | 55 | 259
13228 | 2019-06-12 | 2019-07-17 | 2020-01-02 | 2020-01-02 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2021-09-20 | COMP | 2021-10-18 | COMP | Rule 15/16 | 25 | 116 | 26 | 1 | 409 | 21 | 593
13289 | 2019-06-12 | 2019-07-18 | 2020-02-01 | 2020-05-08 | COMP | 2020-12-14 | COMP | 2020-12-16 | COMP | 2022-11-05 | INPR | 2021-09-30 | COMP | Rule 16 | 26 | 135 | 152 | 3 |  |  | 581
13410 | 2019-06-12 | 2019-07-24 | 2019-11-27 | 2019-11-27 | COMP | 2020-01-07 | COMP | 2020-04-13 | COMP | 2020-02-10 | COMP | 2020-05-06 | COMP | Rule 15/16 | 30 | 89 | 26 | 68 | 0 | 18 | 227
13559 | 2019-06-12 | 2019-07-30 | 2019-09-20 | 2019-09-20 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-09-29 | COMP | 2020-10-21 | COMP | Rule 15/16 | 34 | 38 | 96 | 1 | 164 | 17 | 345
13590 | 2019-06-12 | 2019-07-31 | 2019-09-29 | 2020-05-28 | COMP | 2020-08-11 | COMP | 2020-11-20 | COMP | 2020-12-17 | COMP | 2021-02-10 | COMP | Rule 15/16 | 35 | 42 | 54 | 72 | 18 | 37 | 419
13704 | 2019-06-12 | 2019-08-06 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-16 | COMP | 2019-10-05 | COMP | 2019-09-08 | COMP | 2019-12-04 | COMP | Rule 15/16 | 39 | 17 | 13 | 15 | 0 | 40 | 121
13734 | 2019-06-12 | 2019-08-07 | 2020-05-30 | 2020-05-30 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-08-17 | COMP | 2020-10-27 | COMP | Rule 16 | 40 | 204 | 7 | 1 | 50 | 51 | 349
14025 | 2019-06-12 | 2019-08-21 | 2019-11-12 | 2019-11-12 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-02-04 | COMP | 2020-03-15 | COMP | Rule 16 | 50 | 58 | 66 | 1 | 0 | 18 | 189
14302 | 2019-06-12 | 2019-09-04 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-19 | COMP | 2019-11-20 | COMP | 2020-03-30 | COMP | 2020-06-12 | COMP | Rule 16 | 59 | 35 | 20 | 2 | 88 | 54 | 253
14327 | 2019-06-12 | 2019-09-05 | 2020-03-06 | 2020-03-30 | COMP | 2020-08-31 | COMP | 2020-09-15 | COMP | 2020-09-22 | COMP | 2020-11-05 | COMP | Rule 15/16 | 60 | 125 | 110 | 11 | 6 | 33 | 356
14491 | 2019-06-12 | 2019-09-11 | 2019-12-28 | 2019-12-28 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-06-23 | COMP | 2020-08-11 | COMP | Rule 16 | 64 | 74 | 77 | 1 | 47 | 36 | 295
14492 | 2019-06-12 | 2019-09-11 | 2020-01-08 | 2020-01-08 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-06-11 | COMP | 2020-08-11 | COMP | Rule 15/16 | 64 | 81 | 20 | 1 | 90 | 44 | 295
14688 | 2019-06-12 | 2019-09-23 | 2020-02-01 | 2020-02-01 | COMP | 2020-05-13 | COMP | 2020-05-19 | COMP | 2020-09-10 | COMP | 2020-09-23 | COMP | Rule 15/16 | 72 | 89 | 72 | 5 | 81 | 10 | 325
14844 | 2019-06-12 | 2019-09-30 | 2019-12-14 | 2019-12-14 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-02-04 | COMP | 2020-02-21 | COMP | Rule 16 | 77 | 52 | 17 | 1 | 18 | 13 | 174
14980 | 2019-06-12 | 2019-10-07 | 2020-02-10 | 2020-02-10 | COMP | 2020-02-28 | COMP | 2020-06-30 | COMP | 2020-05-05 | COMP | 2020-07-27 | COMP | Rule 16 | 82 | 85 | 14 | 87 | 0 | 20 | 284
15105 | 2019-06-12 | 2019-10-14 | 2019-12-05 | 2019-12-05 | COMP | 2020-01-08 | COMP | 2020-01-08 | COMP | 2020-02-26 | COMP | 2020-03-05 | COMP | Rule 16 | 87 | 36 | 23 | 1 | 34 | 7 | 183
15154 | 2019-06-12 | 2019-10-16 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-11 | COMP | 2021-07-02 | COMP | 2021-07-02 | COMP | 2021-08-02 | COMP | Rule 16 | 89 | 134 | 9 | 290 | 1 | 21 | 539
15440 | 2019-06-12 | 2019-11-01 | 2020-01-13 | 2020-01-13 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2021-04-24 | INPR | 2020-04-09 | COMP | Rule 16 | 101 | 47 | 39 | 1 |  |  | 208
15706 | 2019-06-12 | 2019-11-18 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2023-04-30 | INPR | 2020-07-24 | COMP | Rule 16 | 111 | 23 | 14 | 1 |  |  | 283
16876 | 2019-06-12 | 2020-01-22 | 2020-09-16 | 2020-12-11 | COMP | 2021-04-01 | COMP | 2021-04-13 | COMP | 2021-05-26 | COMP | 2021-06-09 | COMP | Rule 16 | 153 | 168 | 76 | 9 | 32 | 10 | 502
17086 | 2019-06-12 | 2020-01-30 | 2020-04-03 | 2020-04-03 | COMP | 2020-08-04 | COMP | 2020-09-01 | COMP | 2021-01-15 | COMP | 2021-02-15 | COMP | Rule 16 | 159 | 46 | 87 | 21 | 93 | 20 | 421
18440 | 2019-06-12 | 2020-03-24 | 2020-06-29 | 2020-10-29 | COMP | 2020-11-04 | COMP | 2020-11-04 | COMP | 2020-11-07 | COMP | 2020-11-19 | COMP | Rule 16 | 196 | 69 | 5 | 1 | 3 | 8 | 365
22813 | 2019-06-12 | 2020-10-13 | 2020-12-09 | 2020-12-11 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | 2021-11-08 | COMP | 2021-11-15 | COMP | Rule 16 | 339 | 39 | 20 | 1 | 211 | 5 | 612
4200 | 2019-06-13 | 2019-07-09 | [7 empty] | 2019-10-30 | COMP | 2019-10-08 | COMP | Other | 18 | [5 empty] | 82
12743 | 2019-06-13 | 2019-06-20 | 2019-12-21 | 2021-02-02 | COMP | 2021-02-10 | COMP | 2021-02-13 | COMP | 2021-03-03 | COMP | 2021-03-27 | COMP | Rule 15/16 | 6 | 127 | 7 | 3 | 12 | 18 | 449
12744 | 2019-06-13 | 2019-06-20 | 2019-07-17 | 2019-07-17 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-12-20 | COMP | 2020-01-02 | COMP | Rule 16 | 6 | 19 | 63 | 1 | 47 | 8 | 139
12829 | 2019-06-13 | 2019-06-25 | 2019-08-12 | 2019-08-12 | COMP | 2019-09-03 | COMP | 2019-09-18 | COMP | 2021-10-15 | COMP | 2019-10-30 | COMP | Rule 16 | 9 | 34 | 16 | 12 | 524 |  | 98
12976 | 2019-06-13 | 2019-07-02 | 2019-09-17 | 2019-09-17 | COMP | 2019-11-04 | NOTN | 2019-11-27 | COMP | 2019-11-21 | COMP | 2020-01-23 | COMP | Other | 14 | 54 |  | 51 | 0 | 37 | 153
13018 | 2019-06-13 | 2019-07-03 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-07 | COMP | 2019-11-06 | COMP | 2020-12-14 | COMP | 2021-01-08 | COMP | Rule 16 | 15 | 64 | 4 | 23 | 277 | 18 | 396
13100 | 2019-06-13 | 2019-07-11 | 2019-09-06 | 2019-09-06 | COMP | 2020-02-26 | COMP | 2020-04-06 | COMP | 2020-03-26 | COMP | 2020-05-15 | COMP | Rule 15/16 | 20 | 41 | 117 | 29 | 0 | 30 | 233
13186 | 2019-06-13 | 2019-07-15 | 2019-08-06 | 2019-08-06 | COMP | 2019-10-30 | COMP | 2019-12-10 | COMP | 2020-01-07 | COMP | 2020-02-07 | COMP | Rule 16 | 22 | 17 | 61 | 27 | 19 | 23 | 164
13234 | 2019-06-13 | 2019-07-17 | 2019-10-18 | 2019-10-24 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2020-02-05 | COMP | 2020-02-14 | COMP | Rule 16 | 24 | 67 | 12 | 1 | 58 | 8 | 169
13261 | 2019-06-13 | 2019-07-17 | 2019-09-03 | 2019-09-03 | COMP | 2019-09-03 | NOTN | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-09-14 | COMP | Other | 24 | 34 |  | 1 | 1 | 9 | 65
13288 | 2019-06-13 | 2019-07-18 | 2019-10-24 | 2022-10-19 | COMP | 2022-10-27 | COMP | 2022-12-14 | COMP | 2019-07-18 | COMP | 2023-08-03 | COMP | Rule 16 | 25 | 70 | 7 | 32 | 0 | 160 | 1041
13312 | 2019-06-13 | 2019-07-20 | 2019-12-08 | 2020-03-01 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2021-10-23 | INPR | 2020-10-20 | COMP | Rule 16 | 26 | 96 | 21 | 1 |  |  | 343
13639 | 2019-06-13 | 2019-08-02 | 2019-09-18 | 2019-09-18 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-09-11 | COMP | 2020-09-30 | COMP | Rule 16 | 36 | 33 | 178 | 1 | 72 | 14 | 329
13657 | 2019-06-13 | 2019-08-05 | 2019-12-17 | 2019-12-17 | COMP | 2019-12-26 | COMP | 2019-12-26 | COMP | 2021-04-12 | COMP | 2021-05-08 | COMP | Rule 16 | 37 | 93 | 7 | 1 | 326 | 20 | 479
14056 | 2019-06-13 | 2019-08-22 | 2019-10-04 | 2019-10-04 | COMP | 2019-11-20 | COMP | 2020-01-31 | COMP | 2020-02-29 | COMP | 2020-02-26 | COMP | Rule 16 | 50 | 31 | 33 | 48 | 20 |  | 176
14082 | 2019-06-13 | 2019-08-23 | 2020-01-24 | 2021-10-17 | COMP | 2021-11-18 | COMP | 2021-12-16 | COMP | 2022-02-22 | COMP | 2022-03-10 | COMP | Rule 15/16 | 51 | 104 | 23 | 19 | 47 | 13 | 690
14109 | 2019-06-13 | 2019-08-26 | 2019-10-28 | 2019-10-28 | COMP | 2019-10-31 | COMP | 2019-12-23 | COMP | 2020-05-04 | COMP | 2020-05-13 | COMP | Rule 16 | 52 | 45 | 4 | 35 | 92 | 8 | 231
14115 | 2019-06-13 | 2019-08-26 | 2019-10-16 | 2019-10-16 | COMP | 2020-09-08 | COMP | 2020-09-08 | INPR | 2020-09-08 | COMP | 2020-09-12 | COMP | Rule 16 | 52 | 37 | 226 |  |  |  | 316
14133 | 2019-06-13 | 2019-08-26 | 2019-09-10 | 2019-09-10 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-12-01 | COMP | 2020-01-30 | COMP | Rule 16 | 52 | 11 | 50 | 1 | 7 | 41 | 158
14152 | 2019-06-13 | 2019-08-27 | 2019-09-27 | 2019-09-27 | COMP | 2019-10-16 | COMP | 2019-10-31 | COMP | 2020-03-09 | COMP | 2020-03-13 | COMP | Rule 16 | 53 | 23 | 14 | 12 | 86 | 5 | 188
14384 | 2019-06-13 | 2019-09-08 | 2020-03-05 | 2020-03-05 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-07-14 | COMP | 2020-08-03 | COMP | Rule 16 | 60 | 122 | 46 | 1 | 48 | 15 | 288
14660 | 2019-06-13 | 2019-09-21 | 2019-12-26 | 2019-12-26 | COMP | 2020-01-14 | COMP | 2020-02-05 | COMP | 2020-06-16 | COMP | 2020-08-13 | COMP | Rule 16 | 70 | 65 | 13 | 16 | 93 | 43 | 296
14996 | 2019-06-13 | 2019-10-09 | 2019-12-16 | 2020-05-04 | COMP | 2020-06-24 | COMP | 2020-07-06 | COMP | 2020-06-08 | COMP | 2020-08-14 | COMP | Rule 15/16 | 83 | 46 | 37 | 9 | 0 | 30 | 297
15211 | 2019-06-13 | 2019-10-21 | 2019-11-18 | 2019-11-18 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-05-20 | COMP | 2020-04-15 | COMP | Rule 15/16 | 91 | 20 | 60 | 1 | 68 |  | 211
16513 | 2019-06-13 | 2020-01-06 | 2020-04-30 | 2021-02-02 | COMP | 2021-01-27 | COMP | 2021-08-09 | COMP | 2021-08-05 | COMP | 2021-09-01 | COMP | Rule 16 | 141 | 82 |  | 136 | 0 | 18 | 560
16812 | 2019-06-13 | 2020-01-16 | 2020-05-01 | 2020-05-01 | COMP | 2020-06-08 | COMP | 2020-07-02 | COMP | 2020-06-10 | COMP | 2020-07-30 | COMP | Rule 15/16 | 149 | 75 | 26 | 19 | 0 | 21 | 286
16826 | 2019-06-13 | 2020-01-17 | 2020-07-16 | 2020-12-23 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP | 2021-04-12 | COMP | 2021-05-18 | COMP | Rule 15/16 | 150 | 127 | 30 | 1 | 46 | 27 | 486
17085 | 2019-06-13 | 2020-01-30 | 2020-04-24 | 2020-04-24 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-09-14 | COMP | 2020-11-14 | COMP | Rule 16 | 158 | 61 | 77 | 1 | 24 | 44 | 360
17502 | 2019-06-13 | 2020-02-19 | 2020-06-12 | 2021-08-27 | COMP | 2021-09-03 | COMP | 2023-02-01 | COMP | 2023-01-13 | COMP | 2023-04-01 | COMP | Rule 15/16 | 171 | 82 | 6 | 353 | 0 | 42 | 955
17544 | 2019-06-13 | 2020-02-19 | 2020-06-21 | 2020-06-21 | COMP | 2020-09-30 | COMP | 2020-09-30 | COMP | 2020-10-23 | COMP | 2020-11-12 | COMP | Rule 16 | 171 | 87 | 72 | 1 | 18 | 14 | 359
12599 | 2019-06-14 | 2019-06-14 | 2019-10-25 | 2019-10-25 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-03-04 | COMP | 2020-04-07 | COMP | Rule 16 | 1 | 94 | 67 | 1 | 21 | 25 | 204
13033 | 2019-06-14 | 2019-07-08 | 2019-09-17 | 2019-09-17 | COMP | 2019-10-21 | COMP | 2019-11-04 | COMP | 2019-10-31 | COMP | 2019-12-31 | COMP | Rule 15/16 | 16 | 51 | 25 | 11 | 0 | 38 | 137
13190 | 2019-06-14 | 2019-07-15 | 2019-10-03 | 2019-10-03 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-09-17 | COMP | 2020-09-25 | COMP | Rule 16 | 21 | 58 | 240 | 1 | 3 | 7 | 325
13370 | 2019-06-14 | 2019-07-22 | 2019-10-25 | 2020-01-31 | COMP | 2020-02-19 | COMP | 2020-06-04 | COMP | 2021-10-23 | INPR | 2020-10-16 | COMP | Rule 16 | 26 | 69 | 13 | 76 |  |  | 340
13524 | 2019-06-14 | 2019-07-31 | 2019-09-17 | 2019-09-17 | COMP | 2019-10-03 | COMP | 2019-12-03 | COMP | 2020-02-27 | COMP | 2020-02-28 | COMP | Rule 15/16 | 33 | 34 | 13 | 41 | 59 | 2 | 177
13531 | 2019-06-14 | 2019-07-30 | 2019-08-17 | 2019-08-17 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-09-30 | COMP | Rule 16 | 32 | 14 | 9 | 1 | 1 | 22 | 75
13687 | 2019-06-14 | 2019-08-06 | 2019-10-08 | 2019-10-08 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | Rule 15/16 | 37 | 45 | 17 | 1 | 92 | 1 | 188
13747 | 2019-06-14 | 2019-08-07 | 2019-12-19 | 2019-12-19 | COMP | 2020-01-13 | COMP | 2020-01-31 | COMP | 2020-02-03 | COMP | 2020-02-19 | COMP | Rule 16 | 38 | 93 | 16 | 14 | 2 | 12 | 170
13866 | 2019-06-14 | 2019-08-14 | 2020-01-11 | 2020-01-11 | COMP | 2020-02-12 | COMP | 2020-02-20 | COMP | 2020-02-13 | COMP | 2021-05-25 | COMP | Rule 16 | 43 | 102 | 22 | 6 | 0 | 320 | 490
14089 | 2019-06-14 | 2019-08-24 | 2019-10-21 | 2019-10-21 | COMP | 2019-12-03 | COMP | 2020-06-12 | COMP | 2020-11-24 | COMP | 2020-12-21 | COMP | Rule 16 | 50 | 40 | 29 | 134 | 116 | 18 | 383
14220 | 2019-06-14 | 2019-08-29 | 2019-10-26 | 2019-10-26 | COMP | 2020-02-14 | COMP | 2020-02-21 | COMP | 2020-02-26 | COMP | 2020-04-09 | COMP | Rule 16 | 54 | 41 | 74 | 5 | 4 | 32 | 206
14923 | 2019-06-14 | 2019-10-04 | 2019-12-12 | 2019-12-12 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2020-10-15 | COMP | 2020-10-20 | COMP | Rule 16 | 79 | 47 | 177 | 1 | 39 | 4 | 342
15287 | 2019-06-14 | 2019-10-24 | 2020-01-04 | 2020-01-04 | COMP | 2020-02-19 | COMP | 2020-05-06 | COMP | 2020-04-28 | COMP | 2020-06-10 | COMP | Rule 16 | 93 | 47 | 31 | 56 | 0 | 25 | 249
16333 | 2019-06-14 | 2019-12-20 | 2020-04-02 | 2022-11-03 | COMP | 2023-01-20 | COMP | 2023-06-06 | COMP | 2023-05-18 | COMP | 2023-08-11 | COMP | Rule 15/16 | 131 | 71 | 51 | 96 | 0 | 47 | 1046
16881 | 2019-06-14 | 2020-01-22 | 2020-03-09 | 2020-08-23 | COMP | 2020-08-28 | COMP | 2020-03-30 | COMP | 2020-11-24 | COMP | 2021-01-11 | COMP | Rule 16 | 151 | 33 | 5 |  | 169 | 31 | 396
17375 | 2019-06-14 | 2020-02-11 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-06-10 | COMP | 2020-06-22 | COMP | Rule 16 | 165 | 14 | 16 | 1 | 57 | 9 | 257
17557 | 2019-06-14 | 2020-02-22 | 2020-04-20 | 2020-06-19 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-07-27 | COMP | 2020-09-04 | COMP | Rule 16 | 172 | 41 | 14 | 1 | 14 | 30 | 311
4250 | 2019-06-17 | 2019-11-12 | 2020-05-22 | 2020-03-03 | COMP | 2020-07-30 | COMP | 2020-09-29 | COMP | 2020-08-25 | COMP | 2020-10-20 | COMP | Other | 104 | 133 | 107 | 43 | 0 | 16 | 341
12851 | 2019-06-17 | 2019-06-26 | 2019-10-15 | 2019-10-30 | COMP | 2019-11-08 | COMP | 2019-11-12 | COMP | 2019-11-21 | COMP | 2020-01-02 | COMP | Rule 15/16 | 8 | 78 | 8 | 2 | 8 | 27 | 137
13026 | 2019-06-17 | 2019-07-06 | 2019-07-17 | 2019-07-17 | COMP | 2019-10-08 | COMP | 2019-10-14 | INPR | 2021-10-23 | REQD | 2020-05-15 | COMP | Rule 16 | 14 | 8 | 59 |  |  |  | 231
13080 | 2019-06-17 | 2019-07-10 | 2019-08-06 | 2019-08-06 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-08-27 | COMP | 2020-10-11 | COMP | Other | 17 | 20 | 39 | 1 | 0 | 261 | 334
13099 | 2019-06-17 | 2019-07-11 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-10-24 | INPR | 2020-02-26 | COMP | Rule 16 | 18 | 60 | 13 | 1 |  |  | 174
13323 | 2019-06-17 | 2019-07-19 | 2019-07-27 | 2019-07-27 | COMP | 2019-09-12 | COMP | 2019-09-12 | COMP | 2020-01-19 | INPR | 2019-09-16 | COMP | Rule 16 | 24 | 6 | 33 | 1 |  |  | 64
13401 | 2019-06-17 | 2019-07-24 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-29 | COMP | 2020-01-13 | COMP | 2020-02-18 | COMP | 2020-02-28 | COMP | Rule 16 | 27 | 62 | 8 | 50 | 25 | 9 | 176
13463 | 2019-06-17 | 2019-07-26 | 2020-02-09 | 2020-02-09 | COMP | 2020-04-10 | COMP | 2020-06-01 | COMP | 2020-09-28 | COMP | 2020-12-03 | COMP | Rule 16 | 29 | 134 | 44 | 36 | 85 | 46 | 370
14093 | 2019-06-17 | 2019-08-26 | 2019-12-07 | 2019-12-07 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-03-02 | COMP | 2020-04-09 | COMP | Rule 16 | 50 | 71 | 23 | 1 | 35 | 29 | 205
14129 | 2019-06-17 | 2019-08-26 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2022-07-16 | INPR | 2020-10-08 | COMP | Rule 16 | 50 | 39 | 9 | 1 |  |  | 333
14276 | 2019-06-17 | 2019-09-02 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-03-10 | COMP | 2020-03-23 | COMP | Rule 16 | 54 | 73 | 23 | 1 | 35 | 10 | 192
14524 | 2019-06-17 | 2019-09-14 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-11 | COMP | 2020-07-06 | COMP | 2020-11-02 | COMP | 2020-11-10 | COMP | Rule 16 | 63 | 95 | 7 | 103 | 85 | 7 | 356
14533 | 2019-06-17 | 2019-09-16 | 2019-10-20 | 2019-11-04 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-03-10 | COMP | 2020-03-24 | COMP | Rule 16 | 64 | 25 | 41 | 1 | 45 | 11 | 193
14594 | 2019-06-17 | 2019-09-17 | 2019-11-03 | 2020-03-17 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-09-11 | COMP | 2020-10-12 | COMP | Rule 16 | 65 | 34 | 66 | 1 | 62 | 22 | 335
14604 | 2019-06-17 | 2019-09-18 | 2019-09-30 | 2019-09-30 | COMP | 2023-11-12 | INPR | 2019-11-18 | COMP | 2020-05-04 | COMP | 2020-06-10 | COMP | Rule 15/16 | 66 | 9 |  | 35 | 115 | 27 | 248
14912 | 2019-06-17 | 2019-10-03 | 2020-02-20 | 2020-02-20 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-07-08 | COMP | 2020-07-15 | COMP | Rule 15/16 | 77 | 94 | 66 | 1 | 34 | 6 | 273
14915 | 2019-06-17 | 2019-10-03 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-08 | COMP | 2020-02-24 | COMP | 2020-01-24 | COMP | 2020-02-28 | COMP | Rule 16 | 77 | 42 | 24 | 32 | 0 | 5 | 176
14978 | 2019-06-17 | 2019-10-07 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-19 | COMP | 2020-05-07 | COMP | 2020-06-01 | COMP | 2020-06-10 | COMP | Rule 16 | 79 | 94 | 19 | 36 | 17 | 8 | 248
15305 | 2019-06-17 | 2019-10-25 | 2019-12-08 | 2019-12-08 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | 2020-01-29 | COMP | 2020-02-28 | COMP | Rule 16 | 93 | 28 | 32 | 1 | 4 | 22 | 176
15651 | 2019-06-17 | 2019-11-13 | 2020-04-12 | 2020-04-12 | COMP | 2020-04-21 | COMP | 2020-05-15 | COMP | 2020-07-22 | COMP | 2020-07-29 | COMP | Rule 16 | 105 | 102 | 7 | 19 | 48 | 6 | 283
15915 | 2019-06-17 | 2019-11-27 | 2020-02-20 | 2020-02-20 | COMP | 2020-06-11 | COMP | 2020-07-08 | COMP | 2020-11-03 | COMP | 2020-12-14 | COMP | Rule 16 | 115 | 56 | 80 | 20 | 84 | 27 | 377
16170 | 2019-06-17 | 2019-12-13 | 2020-03-24 | 2020-03-24 | COMP | 2020-11-09 | COMP | 2020-11-09 | COMP | 2020-11-09 | COMP | 2020-12-16 | COMP | Rule 16 | 125 | 69 | 163 | 1 | 1 | 25 | 379
16571 | 2019-06-17 | 2020-01-08 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2021-05-30 | INPR | 2020-05-05 | COMP | Rule 16 | 141 | 20 | 10 | 1 |  |  | 223
18754 | 2019-06-17 | 2020-04-06 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-25 | COMP | 2020-08-14 | COMP | 2020-08-13 | COMP | 2020-09-23 | COMP | Rule 16 | 202 | 49 | 10 | 37 | 0 | 28 | 322
19470 | 2019-06-17 | 2020-05-08 | 2020-06-23 | 2020-06-23 | COMP | 2020-12-23 | COMP | 2021-02-08 | COMP | 2021-02-10 | COMP | 2021-03-18 | COMP | Rule 16 | 226 | 32 | 128 | 31 | 3 | 26 | 441
4203 | 2019-06-18 | 2019-07-12 | 2019-09-04 | 2019-09-04 | COMP | 2019-10-14 | COMP | 2019-10-14 | INPR | 2020-08-12 | COMP | 2020-10-11 | COMP | Other | 18 | 38 | 29 |  |  |  | 333
4221 | 2019-06-18 | 2019-08-10 | 2020-04-21 | 2020-04-21 | COMP | [5 empty] | INPR | 2020-01-10 | COMP | Other | 38 | 174 |  |  |  |  | 142
12687 | 2019-06-18 | 2019-06-18 | 2019-09-15 | 2021-04-05 | COMP | 2021-04-27 | COMP | 2021-02-03 | COMP | 2021-02-09 | COMP | 2021-02-25 | COMP | Rule 16 | 1 | 62 | 17 |  | 5 | 12 | 425
12745 | 2019-06-18 | 2019-06-21 | 2019-11-17 | 2019-11-17 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-07-18 | COMP | 2020-08-05 | COMP | Rule 16 | 4 | 103 | 167 | 1 | 2 | 13 | 287
12924 | 2019-06-18 | 2019-06-29 | 2019-11-01 | 2019-11-01 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2019-12-13 | COMP | 2020-01-16 | COMP | Rule 16 | 9 | 88 | 27 | 1 | 2 | 23 | 146
12935 | 2019-06-18 | 2019-07-01 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-02 | COMP | 2019-12-17 | COMP | 2019-12-03 | COMP | 2020-01-21 | COMP | Rule 16 | 10 | 94 | 13 | 12 | 0 | 23 | 148
12993 | 2019-06-18 | 2019-07-03 | 2019-10-09 | 2019-10-31 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-12-31 | COMP | 2020-06-10 | COMP | Rule 15/16 | 12 | 69 | 13 | 1 | 28 | 113 | 247
12998 | 2019-06-18 | 2019-07-03 | 2019-08-31 | 2019-08-31 | COMP | 2019-11-05 | COMP | 2019-11-20 | COMP | 2019-11-19 | COMP | 2019-12-24 | COMP | Rule 16 | 12 | 42 | 46 | 11 | 0 | 23 | 131
13127 | 2019-06-18 | 2019-07-11 | 2019-10-20 | 2019-10-20 | COMP | 2020-01-28 | NOTN | 2020-06-09 | COMP | 2020-01-28 | COMP | 2020-08-11 | COMP | Other | 17 | 71 |  | 159 | 0 | 46 | 291
13152 | 2019-06-18 | 2019-07-12 | 2019-09-03 | 2019-09-03 | COMP | 2020-01-03 | COMP | 2020-01-03 | INPR | 2020-08-12 | COMP | 2020-10-11 | COMP | Other | 18 | 37 | 84 |  |  |  | 333
13164 | 2019-06-18 | 2019-07-15 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-11 | COMP | 2020-04-16 | COMP | 2020-07-13 | COMP | 2020-07-31 | COMP | Rule 15/16 | 19 | 140 | 26 | 27 | 62 | 15 | 284
13329 | 2019-06-18 | 2019-07-22 | 2019-08-27 | 2019-08-27 | COMP | 2019-08-27 | NOTN | 2019-08-27 | COMP | 2019-08-27 | COMP | 2019-09-27 | COMP | Other | 24 | 27 |  | 1 | 1 | 23 | 72
13363 | 2019-06-18 | 2019-07-23 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-30 | COMP | 2020-05-02 | COMP | 2020-03-31 | COMP | 2020-06-02 | COMP | Rule 16 | 25 | 93 | 39 | 66 | 0 | 21 | 241
13424 | 2019-06-18 | 2019-07-25 | 2019-10-17 | 2019-10-17 | COMP | 2020-01-02 | COMP | 2020-01-15 | COMP | 2020-01-29 | COMP | 2020-02-06 | COMP | Rule 16 | 27 | 60 | 51 | 10 | 10 | 7 | 160
13475 | 2019-06-18 | 2019-07-26 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-02-20 | COMP | Rule 15/16 | 28 | 49 | 11 | 1 | 1 | 84 | 169
13721 | 2019-06-18 | 2019-08-07 | 2019-09-09 | 2019-10-24 | COMP | 2019-10-16 | NOTN | 2019-10-16 | COMP | 2019-10-16 | COMP | 2020-01-14 | COMP | Rule 16 | 36 | 23 |  |  | 1 | 60 | 144
13755 | 2019-06-18 | 2019-08-08 | 2019-09-03 | 2020-02-18 | COMP | 2021-06-18 | COMP | 2021-07-08 | COMP | 2021-11-03 | COMP | 2021-11-05 | COMP | Rule 16 | 37 | 18 | 339 | 14 | 84 | 3 | 603
13945 | 2019-06-18 | 2019-08-17 | 2020-02-01 | 2020-02-01 | COMP | 2020-06-09 | COMP | 2020-07-21 | COMP | 2020-06-30 | COMP | 2020-08-20 | COMP | Rule 16 | 43 | 113 | 90 | 31 | 0 | 23 | 298
13965 | 2019-06-18 | 2019-08-21 | 2021-04-16 | 2021-04-16 | COMP | 2021-05-12 | COMP | 2021-06-24 | COMP | 2021-06-25 | NOTN | 2021-07-20 | COMP | Rule 15/16 | 46 | 416 | 19 | 31 |  |  | 526
14121 | 2019-06-18 | 2019-08-26 | 2020-02-03 | 2020-02-03 | COMP | 2020-07-15 | COMP | 2020-08-05 | COMP | 2020-08-12 | COMP | 2020-09-28 | COMP | Rule 16 | 49 | 109 | 116 | 16 | 6 | 33 | 324
14181 | 2019-06-18 | 2019-08-28 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | 2020-03-06 | COMP | 2020-04-03 | COMP | Rule 16 | 51 | 106 | 16 | 1 | 10 | 21 | 200
14476 | 2019-06-18 | 2019-09-11 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-29 | COMP | 2020-01-14 | COMP | 2020-01-30 | COMP | 2020-01-28 | COMP | Rule 16 | 60 | 18 | 17 | 51 | 12 |  | 153
14588 | 2019-06-18 | 2019-09-20 | 2019-11-21 | 2019-11-21 | COMP | 2020-01-23 | COMP | 2020-02-28 | COMP | 2020-05-13 | COMP | 2020-05-27 | COMP | Rule 16 | 67 | 44 | 41 | 26 | 54 | 10 | 237
14735 | 2019-06-18 | 2019-09-25 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-24 | COMP | 2020-07-01 | COMP | 2021-06-16 | COMP | 2021-08-06 | COMP | Rule 15/16 | 70 | 158 | 31 | 6 | 242 | 37 | 539
14803 | 2019-06-18 | 2019-09-27 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-01-03 | COMP | 2020-01-10 | COMP | Rule 15/16 | 72 | 32 | 16 | 1 | 20 | 6 | 142
14959 | 2019-06-18 | 2019-10-07 | 2020-01-18 | 2020-01-18 | COMP | 2020-07-14 | COMP | 2020-07-14 | COMP | 2020-07-02 | COMP | 2020-08-14 | COMP | Rule 16 | 78 | 70 | 124 | 1 | 0 | 24 | 294
15231 | 2019-06-18 | 2019-10-22 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-05 | COMP | 2020-01-17 | COMP | 2020-01-14 | COMP | 2020-01-28 | COMP | Rule 16 | 89 | 27 | 4 | 30 | 0 | 7 | 153
16001 | 2019-06-18 | 2019-12-06 | 2020-04-28 | 2020-04-28 | COMP | 2020-07-16 | COMP | 2020-09-15 | COMP | 2020-08-31 | COMP | 2020-10-02 | COMP | Rule 16 | 119 | 99 | 57 | 43 | 0 | 14 | 328
16483 | 2019-06-18 | 2020-01-02 | 2020-04-06 | 2020-07-07 | COMP | 2020-07-23 | COMP | 2020-05-22 | COMP | 2021-01-15 | COMP | 2021-03-01 | COMP | Rule 16 | 136 | 66 | 13 |  | 164 | 30 | 427
16588 | 2019-06-18 | 2020-01-09 | 2020-02-05 | 2020-02-05 | COMP | 2021-07-26 | COMP | 2021-07-26 | COMP | 2021-09-03 | COMP | 2021-10-08 | COMP | Rule 16 | 141 | 19 | 372 | 1 | 30 | 25 | 583
16649 | 2019-06-18 | 2020-01-09 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-03 | COMP | 2020-10-14 | COMP | 2021-01-11 | COMP | 2021-02-22 | COMP | Rule 15/16 | 141 | 130 | 16 | 52 | 59 | 29 | 422
16724 | 2019-06-18 | 2020-01-13 | 2020-01-24 | 2020-01-30 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-25 | COMP | Rule 16 | 143 | 9 | 8 | 1 | 1 | 11 | 172
17362 | 2019-06-18 | 2020-02-11 | 2020-03-20 | 2020-03-20 | COMP | 2020-03-27 | COMP | 2020-03-30 | COMP | 2020-07-06 | COMP | 2020-08-04 | COMP | Rule 16 | 163 | 28 | 6 | 2 | 70 | 22 | 286
18062 | 2019-06-18 | 2020-03-10 | 2020-04-15 | 2020-04-15 | COMP | 2020-06-05 | COMP | 2020-06-08 | COMP | 2021-08-05 | COMP | 2021-09-22 | COMP | Rule 16 | 182 | 27 | 37 | 2 | 294 | 34 | 571
18611 | 2019-06-18 | 2020-03-31 | 2020-04-23 | 2020-04-23 | COMP | 2020-07-15 | COMP | 2020-09-30 | COMP | 2021-08-12 | COMP | 2021-09-16 | COMP | Rule 16 | 197 | 18 | 59 | 55 | 218 | 25 | 567
18815 | 2019-06-18 | 2020-04-08 | 2020-05-23 | 2021-05-12 | COMP | 2021-07-19 | COMP | 2021-07-19 | COMP | 2022-03-08 | COMP | 2022-03-23 | COMP | Rule 16 | 203 | 33 | 47 | 1 | 161 | 12 | 696
22075 | 2019-06-18 | 2020-09-10 | 2020-10-29 | 2020-10-29 | COMP | 2020-11-10 | COMP | 2021-01-08 | COMP | 2021-01-08 | COMP | 2021-02-09 | COMP | Rule 16 | 312 | 36 | 9 | 39 | 1 | 22 | 414
22615 | 2019-06-18 | 2020-10-01 | 2021-06-19 | 2023-02-25 | COMP | 2023-03-03 | COMP | 2022-01-03 | COMP | 2023-03-07 | COMP | 2023-03-30 | COMP | Rule 16 | 327 | 179 | 5 |  | 294 | 18 | 951
12968 | 2019-06-19 | 2019-07-02 | 2019-10-10 | 2019-10-10 | COMP | 2020-01-21 | COMP | 2020-06-29 | COMP | 2020-06-08 | COMP | 2020-07-15 | COMP | Rule 16 | 10 | 71 | 68 | 113 | 0 | 13 | 271
13095 | 2019-06-19 | 2019-07-10 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-04 | NOTN | 2019-11-04 | COMP | 2019-11-04 | COMP | 2020-01-08 | COMP | Other | 15 | 82 |  | 2 | 1 | 43 | 139
13219 | 2019-06-19 | 2019-07-17 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-25 | COMP | 2019-11-15 | COMP | 2020-01-13 | COMP | 2020-01-14 | COMP | Rule 16 | 20 | 58 | 15 | 15 | 38 | 2 | 143
13348 | 2019-06-19 | 2019-07-22 | 2019-12-16 | 2019-12-16 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-01 | COMP | 2020-06-29 | COMP | Rule 16 | 23 | 102 | 113 | 1 | 4 | 21 | 259
13369 | 2019-06-19 | 2019-07-22 | 2019-09-25 | 2019-09-25 | COMP | 2020-01-21 | COMP | 2020-04-07 | INPR | 2020-04-06 | COMP | 2020-05-07 | COMP | Rule 15/16 | 23 | 47 | 79 |  |  |  | 223
13396 | 2019-06-19 | 2019-07-23 | 2020-04-29 | 2020-04-29 | COMP | 2020-10-30 | COMP | 2022-05-04 | COMP | 2022-04-20 | COMP | 2022-06-07 | COMP | Rule 15/16 | 24 | 194 | 131 | 379 | 0 | 24 | 748
13399 | 2019-06-19 | 2019-07-24 | 2019-09-19 | 2019-09-19 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2020-01-02 | COMP | 2020-01-08 | COMP | Rule 16 | 25 | 41 | 16 | 1 | 56 | 5 | 139
13438 | 2019-06-19 | 2019-07-25 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-12-06 | COMP | Rule 16 | 26 | 47 | 11 | 1 | 1 | 37 | 118
13481 | 2019-06-19 | 2019-07-26 | 2019-09-12 | 2019-10-11 | COMP | 2019-11-12 | COMP | 2019-11-13 | COMP | 2019-11-14 | COMP | 2019-12-20 | COMP | Rule 16 | 27 | 34 | 22 | 2 | 2 | 25 | 128
13506 | 2019-06-19 | 2019-07-29 | 2019-09-25 | 2019-12-10 | COMP | 2019-12-19 | COMP | 2020-02-19 | COMP | 2019-09-30 | COMP | 2020-03-12 | COMP | Rule 16 | 28 | 42 | 8 | 41 | 0 | 17 | 183
13588 | 2019-06-19 | 2019-07-31 | 2019-09-23 | 2019-09-23 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-12-11 | COMP | Rule 15/16 | 30 | 38 | 30 | 1 | 1 | 26 | 121
13589 | 2019-06-19 | 2019-07-31 | 2019-09-29 | 2019-09-29 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-12-11 | COMP | Rule 16 | 30 | 42 | 25 | 1 | 1 | 26 | 121
13605 | 2019-06-19 | 2019-08-01 | 2019-10-23 | 2019-10-23 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-03-09 | COMP | 2020-04-15 | COMP | Rule 16 | 31 | 59 | 98 | 1 | 0 | 22 | 207
13660 | 2019-06-19 | 2019-08-05 | 2019-11-06 | 2019-11-06 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-03-18 | COMP | 2020-05-07 | COMP | Rule 16 | 33 | 67 | 36 | 1 | 54 | 37 | 223
13813 | 2019-06-19 | 2019-08-12 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-28 | COMP | 2020-01-28 | INPR | 2021-11-18 | COMP | 2019-09-26 | COMP | Rule 16 | 38 | 104 | 12 |  |  |  | 70
13949 | 2019-06-19 | 2019-08-17 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-13 | COMP | 2020-01-13 | COMP | 2020-02-21 | COMP | 2020-03-26 | COMP | Rule 16 | 42 | 86 | 15 | 1 | 28 | 25 | 193
14043 | 2019-06-19 | 2019-08-22 | 2020-02-29 | 2020-02-29 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-04-01 | COMP | 2020-06-18 | COMP | Rule 15/16 | 46 | 129 | 24 | 1 | 0 | 55 | 252
14183 | 2019-06-19 | 2019-08-28 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-14 | COMP | 2019-11-18 | COMP | 2019-11-19 | COMP | 2020-01-05 | COMP | Rule 15/16 | 50 | 50 | 6 | 3 | 2 | 30 | 136
14468 | 2019-06-19 | 2019-09-11 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-04-01 | COMP | 2020-05-04 | COMP | Rule 16 | 59 | 100 | 11 | 1 | 30 | 24 | 220
14840 | 2019-06-19 | 2019-09-30 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-01-25 | COMP | Rule 16 | 72 | 57 | 20 | 1 | 1 | 4 | 150
14950 | 2019-06-19 | 2019-10-06 | 2019-12-22 | 2019-12-22 | COMP | 2020-02-21 | COMP | 2020-12-22 | COMP | 2022-02-26 | INPR | 2020-12-31 | COMP | Rule 16 | 76 | 52 | 41 | 213 |  |  | 387
15167 | 2019-06-19 | 2019-10-19 | 2019-12-26 | 2020-01-12 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2021-03-27 | INPR | 2020-03-04 | COMP | Rule 16 | 86 | 45 | 7 | 1 |  |  | 177
15361 | 2019-06-19 | 2019-10-29 | 2020-01-17 | 2020-01-30 | COMP | 2020-01-27 | NOTN | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-02-09 | COMP | Other | 93 | 54 |  | 1 | 1 | 7 | 160
15958 | 2019-06-19 | 2019-12-03 | 2020-01-27 | 2020-01-27 | COMP | 2020-03-09 | COMP | 2020-06-22 | COMP | 2020-10-12 | COMP | 2020-10-19 | COMP | Rule 16 | 115 | 37 | 30 | 75 | 80 | 6 | 338
17398 | 2019-06-19 | 2020-02-12 | 2020-07-10 | 2021-09-20 | COMP | 2021-09-29 | COMP | 2020-12-15 | COMP | 2021-12-20 | COMP | 2022-01-12 | COMP | Rule 16 | 163 | 106 | 8 |  | 255 | 18 | 647
17514 | 2019-06-19 | 2020-02-19 | 2020-02-21 | 2020-02-21 | COMP | 2020-02-21 | NOTN | 2020-02-21 | COMP | 2020-06-12 | NOTN | 2020-07-02 | COMP | Rule 16 | 167 | 3 |  | 1 |  |  | 262
20071 | 2019-06-19 | 2020-06-04 | 2020-08-10 | 2020-08-10 | COMP | 2020-09-03 | COMP | 2020-09-03 | COMP | 2020-12-08 | COMP | 2020-12-29 | COMP | Rule 15/16 | 242 | 48 | 19 | 1 | 65 | 15 | 385
20620 | 2019-06-19 | 2020-06-30 | 2020-08-26 | 2020-08-26 | COMP | 2021-08-24 | COMP | 2022-07-13 | COMP | 2022-07-12 | COMP | 2022-08-09 | COMP | Other | 260 | 42 | 250 | 223 | 0 | 20 | 791
12785 | 2019-06-20 | 2019-06-21 | 2019-09-09 | 2019-09-09 | COMP | 2019-10-02 | COMP | 2019-11-25 | COMP | 2019-11-12 | COMP | 2019-12-19 | COMP | Rule 16 | 2 | 55 | 18 | 38 | 0 | 17 | 126
12871 | 2019-06-20 | 2019-06-26 | 2019-09-09 | 2019-09-18 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-10-07 | COMP | 2019-11-13 | COMP | Rule 16 | 5 | 52 | 8 | 1 | 7 | 27 | 102
12872 | 2019-06-20 | 2019-06-26 | 2019-07-02 | 2019-07-02 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2019-09-30 | COMP | 2019-10-18 | COMP | Rule 16 | 5 | 5 | 54 | 1 | 10 | 15 | 85
12873 | 2019-06-20 | 2019-06-26 | 2019-09-09 | 2019-09-18 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2020-03-01 | INPR | 2019-11-13 | COMP | Rule 16 | 5 | 52 | 8 | 1 |  |  | 102
12969 | 2019-06-20 | 2019-07-02 | 2019-11-22 | 2019-11-22 | COMP | 2020-01-06 | COMP | 2020-01-15 | COMP | 2020-01-24 | COMP | 2020-02-18 | COMP | Rule 15/16 | 9 | 101 | 28 | 8 | 7 | 17 | 165
13032 | 2019-06-20 | 2019-07-08 | 2019-07-12 | 2019-07-12 | COMP | 2019-07-19 | COMP | 2019-07-19 | COMP | 2019-07-22 | COMP | 2019-07-24 | COMP | Rule 16 | 12 | 5 | 6 | 1 | 2 | 3 | 24
13047 | 2019-06-20 | 2019-07-08 | 2019-09-12 | 2019-09-12 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-06-22 | COMP | Rule 16 | 12 | 48 | 170 | 1 | 1 | 26 | 253
13056 | 2019-06-20 | 2019-07-08 | 2019-11-27 | 2019-11-27 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-03-02 | COMP | 2020-03-06 | COMP | Rule 16 | 12 | 101 | 36 | 1 | 28 | 5 | 178
13093 | 2019-06-20 | 2019-07-10 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-02-18 | COMP | 2020-02-28 | COMP | Rule 16 | 14 | 102 | 34 | 1 | 18 | 9 | 173
13160 | 2019-06-20 | 2019-07-15 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-02 | COMP | 2019-11-21 | COMP | 2019-11-04 | COMP | 2020-01-07 | COMP | Rule 16 | 17 | 42 | 16 | 36 | 0 | 30 | 137
13245 | 2019-06-20 | 2019-07-17 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2020-03-10 | COMP | 2020-08-06 | COMP | Rule 16 | 19 | 50 | 18 | 1 | 96 | 107 | 286
13298 | 2019-06-20 | 2019-07-19 | 2019-09-23 | 2019-09-23 | COMP | 2019-09-27 | COMP | 2019-10-02 | COMP | 2019-10-09 | COMP | 2019-11-05 | COMP | Rule 16 | 21 | 46 | 5 | 4 | 6 | 20 | 97
13341 | 2019-06-20 | 2019-07-22 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-22 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | 2020-04-03 | COMP | Rule 16 | 22 | 71 | 18 | 61 | 1 | 30 | 198
13380 | 2019-06-20 | 2019-07-23 | 2019-09-21 | 2019-09-21 | COMP | 2019-09-27 | COMP | 2019-10-14 | COMP | 2019-11-20 | COMP | 2019-12-09 | COMP | Rule 16 | 23 | 43 | 5 | 12 | 27 | 12 | 118
13383 | 2019-06-20 | 2019-07-23 | 2020-04-28 | 2020-04-28 | COMP | 2020-12-16 | COMP | 2022-05-04 | COMP | 2022-04-20 | COMP | 2022-06-07 | COMP | Rule 16 | 23 | 193 | 162 | 349 | 0 | 24 | 747
13417 | 2019-06-20 | 2019-07-25 | 2020-09-20 | 2020-09-20 | COMP | 2021-01-25 | COMP | 2021-01-25 | COMP | 2021-08-12 | COMP | 2022-04-02 | COMP | Rule 15/16 | 25 | 292 | 85 | 1 | 141 | 161 | 701
13480 | 2019-06-20 | 2019-07-26 | 2022-05-02 | 2022-05-23 | COMP | 2022-05-27 | COMP | 2023-08-04 | COMP |  | INPR | 2023-09-08 | COMP | Rule 15/16 | 26 | 697 | 5 | 297 |  |  | 1061
13548 | 2019-06-20 | 2019-07-31 | 2019-09-23 | 2019-09-23 | COMP | 2019-09-30 | COMP | 2019-09-30 | COMP | 2020-03-01 | INPR | 2019-10-15 | COMP | Rule 16 | 29 | 38 | 6 | 1 |  |  | 82
13803 | 2019-06-20 | 2019-08-12 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2020-08-19 | COMP | 2020-08-18 | COMP | Rule 16 | 37 | 1 | 5 | 1 | 255 |  | 294
14140 | 2019-06-20 | 2019-08-27 | 2019-11-07 | 2019-11-07 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-04-08 | COMP | 2020-05-13 | COMP | Rule 16 | 48 | 52 | 60 | 1 | 44 | 26 | 226
14503 | 2019-06-20 | 2019-09-13 | 2019-10-07 | 2019-10-07 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-12 | COMP | 2020-04-20 | COMP | Rule 16 | 60 | 17 | 99 | 1 | 9 | 28 | 209
15128 | 2019-06-20 | 2019-10-16 | 2020-03-06 | 2020-03-06 | COMP | 2020-05-19 | COMP | 2020-06-03 | COMP | 2020-06-13 | COMP | 2020-07-06 | COMP | Rule 16 | 83 | 96 | 53 | 11 | 8 | 16 | 263
15583 | 2019-06-20 | 2019-11-07 | 2020-01-08 | 2020-02-07 | COMP | 2020-02-13 | COMP | 2020-03-11 | COMP | 2020-04-07 | COMP | 2020-12-01 | COMP | Rule 16 | 99 | 40 | 5 | 19 | 20 | 166 | 365
15630 | 2019-06-20 | 2019-11-12 | 2020-01-30 | 2020-06-25 | COMP | 2020-07-06 | COMP | 2021-10-22 | COMP | 2021-10-21 | COMP | 2021-12-06 | COMP | Rule 15/16 | 101 | 53 | 8 | 329 | 0 | 29 | 619
16063 | 2019-06-20 | 2019-12-07 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-12 | COMP | 2020-06-16 | COMP | 2020-10-20 | COMP | 2020-12-18 | COMP | Rule 16 | 117 | 103 | 28 | 3 | 90 | 41 | 378
16233 | 2019-06-20 | 2019-12-17 | 2020-04-30 | 2020-06-12 | COMP | 2020-07-02 | COMP | 2020-12-17 | INPR | 2020-06-02 | COMP | 2021-02-22 | COMP | Rule 15/16 | 124 | 94 | 15 |  |  |  | 420
16589 | 2019-06-20 | 2020-01-08 | 2020-05-06 | 2020-05-26 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-06-04 | COMP | 2020-07-10 | COMP | Rule 16 | 138 | 84 | 6 | 1 | 3 | 27 | 267
16818 | 2019-06-20 | 2020-01-17 | 2020-03-01 | 2020-03-01 | COMP | 2020-04-14 | COMP | 2020-05-28 | COMP | 2020-08-17 | COMP | 2020-09-02 | COMP | Rule 16 | 145 | 29 | 32 | 32 | 58 | 13 | 305
17193 | 2019-06-20 | 2020-02-04 | 2020-07-31 | 2020-10-21 | COMP | 2021-03-05 | COMP | 2021-03-06 | COMP | 2021-12-03 | COMP | 2022-01-19 | COMP | Rule 15/16 | 156 | 127 | 91 | 1 | 189 | 33 | 650
17335 | 2019-06-20 | 2020-02-11 | 2020-03-17 | 2020-03-17 | COMP | 2020-11-18 | COMP | 2020-11-18 | COMP | 2021-01-13 | COMP | 2021-02-19 | COMP | Rule 16 | 161 | 25 | 174 | 1 | 37 | 26 | 419
17432 | 2019-06-20 | 2020-02-13 | 2020-03-18 | 2020-03-18 | COMP | 2020-09-22 | COMP | 2021-03-01 | COMP | 2020-10-14 | COMP | 2021-04-02 | COMP | Rule 16 | 163 | 24 | 133 | 108 | 0 | 25 | 449
17436 | 2019-06-20 | 2020-02-13 | 2020-04-23 | 2020-04-23 | COMP | 2020-06-11 | COMP | 2020-06-16 | COMP | 2020-08-27 | COMP | 2020-10-05 | COMP | Rule 15/16 | 163 | 50 | 35 | 4 | 53 | 27 | 327
18326 | 2019-06-20 | 2020-03-19 | 2020-07-24 | 2020-07-24 | COMP | 2021-01-11 | COMP | 2021-04-20 | COMP | 2021-02-08 | COMP | 2021-05-10 | COMP | Rule 16 | 187 | 91 | 116 | 70 | 0 | 15 | 475
18513 | 2019-06-20 | 2020-03-28 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-22 | COMP | 2020-07-07 | COMP | Rule 16 | 193 | 40 | 14 | 1 | 8 | 12 | 264
19187 | 2019-06-20 | 2020-04-23 | 2020-08-05 | 2020-08-05 | COMP | 2021-01-19 | COMP | 2021-01-20 | COMP | 2021-10-26 | COMP | 2021-12-07 | COMP | Rule 15/16 | 212 | 74 | 113 | 2 | 196 | 28 | 620
20180 | 2019-06-20 | 2020-06-09 | 2020-08-19 | 2022-08-16 | COMP | 2023-03-14 | COMP | 2023-03-14 | COMP | 2023-09-19 | COMP | 2023-11-01 | COMP | Rule 15/16 | 244 | 52 | 143 | 1 | 132 | 32 | 1099
12910 | 2019-06-21 | 2019-06-28 | 2019-10-16 | 2019-10-16 | COMP | 2020-01-17 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-03-30 | COMP | Rule 16 | 6 | 77 | 63 | 36 | 1 | 15 | 193
13139 | 2019-06-21 | 2019-07-13 | 2019-08-21 | 2019-09-10 | COMP | 2019-09-18 | COMP | 2019-11-26 | COMP | 2020-02-14 | COMP | 2020-03-05 | COMP | Rule 16 | 15 | 28 | 7 | 49 | 54 | 14 | 176
13149 | 2019-06-21 | 2019-07-12 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2020-07-21 | COMP | 2020-08-12 | COMP | Rule 16 | 15 | 51 | 8 | 1 | 202 | 17 | 289
13557 | 2019-06-21 | 2019-07-30 | 2019-11-16 | 2021-08-20 | COMP | 2021-09-27 | COMP | 2021-09-27 | COMP | 2022-08-19 | COMP | 2022-10-27 | COMP | Rule 16 | 27 | 77 | 26 | 1 | 227 | 49 | 845
13621 | 2019-06-21 | 2019-08-02 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-16 | COMP | 2020-03-09 | COMP | 2020-03-07 | COMP | 2020-04-21 | COMP | Rule 16 | 30 | 53 | 41 | 57 | 0 | 32 | 209
13711 | 2019-06-21 | 2019-08-06 | 2019-09-28 | 2019-09-28 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-10 | COMP | 2019-11-12 | COMP | Rule 16 | 32 | 38 | 7 | 1 | 3 | 23 | 100
13715 | 2019-06-21 | 2019-08-06 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-10 | COMP | 2020-10-21 | COMP | 2020-09-17 | COMP | 2021-01-07 | COMP | Rule 15/16 | 32 | 221 | 15 | 73 | 0 | 52 | 389
13716 | 2019-06-21 | 2019-08-06 | 2020-07-13 | 2020-11-04 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2021-02-11 | COMP | Rule 15/16 | 32 | 236 | 9 | 1 | 1 | 58 | 413
14198 | 2019-06-21 | 2019-08-29 | 2020-01-15 | 2020-01-15 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-03-09 | COMP | 2020-05-27 | COMP | Rule 16 | 49 | 94 | 44 | 1 | 0 | 50 | 234
14224 | 2019-06-21 | 2019-08-29 | 2019-10-02 | 2019-10-02 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-01 | COMP | 2020-01-21 | COMP | Rule 16 | 49 | 24 | 39 | 1 | 2 | 34 | 145
14464 | 2019-06-21 | 2019-09-11 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-16 | COMP | 2023-01-03 | COMP | 2020-07-10 | COMP | 2023-02-14 | COMP | Rule 16 | 57 | 118 | 10 | 706 | 0 | 30 | 917
14511 | 2019-06-21 | 2019-09-13 | 2019-10-11 | 2019-10-11 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-12-17 | COMP | 2019-12-23 | COMP | Rule 16 | 59 | 21 | 16 | 1 | 30 | 5 | 127
14973 | 2019-06-21 | 2019-10-08 | 2020-01-30 | 2020-01-30 | COMP | 2021-05-06 | COMP | 2021-05-06 | COMP | 2022-03-07 | COMP | 2022-03-28 | COMP | Rule 16 | 76 | 77 | 321 | 1 | 210 | 16 | 696
15141 | 2019-06-21 | 2019-10-15 | 2020-01-24 | 2020-01-24 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-04-20 | COMP | 2020-06-18 | COMP | Rule 16 | 81 | 68 | 48 | 1 | 14 | 43 | 250
15330 | 2019-06-21 | 2019-10-28 | 2020-04-17 | 2020-04-17 | COMP | 2020-06-23 | COMP | 2021-05-28 | COMP | 2021-07-29 | COMP | 2021-08-05 | COMP | Rule 16 | 90 | 118 | 47 | 236 | 43 | 6 | 535
15655 | 2019-06-21 | 2019-11-14 | 2020-03-23 | 2020-03-23 | COMP | 2020-06-24 | COMP | 2020-07-03 | COMP | 2023-01-03 | COMP | 2023-03-07 | COMP | Rule 15/16 | 102 | 87 | 67 | 8 | 628 | 44 | 931
16308 | 2019-06-21 | 2019-12-19 | 2020-03-18 | 2020-03-18 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-14 | COMP | 2020-07-29 | COMP | Rule 16 | 125 | 61 | 83 | 1 | 2 | 12 | 279
17187 | 2019-06-21 | 2020-02-04 | 2020-08-28 | 2020-10-09 | COMP | 2020-12-22 | COMP | 2021-04-14 | COMP | 2022-05-17 | COMP | 2022-06-02 | COMP | Rule 15/16 | 155 | 147 | 50 | 78 | 277 | 12 | 743
17194 | 2019-06-21 | 2020-02-04 | 2020-04-25 | 2020-04-25 | COMP | 2021-02-17 | COMP | 2021-02-22 | COMP | 2022-02-22 | COMP | 2022-03-08 | COMP | Rule 16 | 155 | 58 | 204 | 4 | 254 | 11 | 682
17207 | 2019-06-21 | 2020-02-04 | 2020-05-02 | 2020-10-05 | COMP | 2021-03-24 | COMP | 2021-03-26 | COMP | 2021-05-07 | COMP | 2021-07-09 | COMP | Rule 16 | 155 | 63 | 116 | 3 | 31 | 44 | 516
17209 | 2019-06-21 | 2020-02-04 | 2020-07-01 | 2020-08-12 | COMP | 2020-09-23 | COMP | 2021-01-20 | COMP | 2021-12-31 | COMP | 2022-01-13 | COMP | Rule 16 | 155 | 105 | 30 | 80 | 241 | 10 | 646
17428 | 2019-06-21 | 2020-02-13 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-24 | COMP | 2020-06-03 | COMP | 2021-01-21 | COMP | 2021-03-16 | COMP | Rule 16 | 162 | 29 | 23 | 28 | 160 | 38 | 435
17984 | 2019-06-21 | 2020-03-06 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-08-10 | COMP | 2020-09-24 | COMP | Rule 16 | 177 | 79 | 32 | 1 | 2 | 33 | 319
18252 | 2019-06-21 | 2020-03-17 | 2020-05-31 | 2020-08-07 | COMP | 2020-11-12 | COMP | 2021-02-09 | COMP | 2021-05-14 | COMP | 2021-06-19 | COMP | Rule 15/16 | 184 | 53 | 68 | 59 | 68 | 25 | 502
13003 | 2019-06-22 | 2019-07-04 | 2019-09-25 | 2019-09-25 | COMP | 2019-09-30 | COMP | 2019-10-02 | COMP | 2019-09-30 | COMP | 2019-10-31 | COMP | Rule 16 | 8 | 58 | 4 | 3 | 0 | 22 | 92
14527 | 2019-06-22 | 2019-09-16 | 2020-01-17 | 2020-01-17 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-11-10 | COMP | 2020-12-21 | COMP | Rule 16 | 59 | 85 | 44 | 1 | 166 | 27 | 377
14783 | 2019-06-22 | 2019-09-27 | 2019-11-01 | 2019-11-01 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2021-05-30 | INPR | 2020-05-07 | COMP | Rule 16 | 68 | 26 | 24 | 1 |  |  | 220
14798 | 2019-06-22 | 2019-09-27 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-04 | NOTN | 2020-03-27 | COMP | 2020-02-05 | COMP | 2020-07-16 | COMP | Other | 68 | 87 |  | 38 | 0 | 79 | 269
18234 | 2019-06-22 | 2020-03-16 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-31 | COMP | 2020-09-18 | COMP | 2023-11-13 | INPR | 2021-09-30 | COMP | Rule 15/16 | 182 | 71 | 29 | 35 |  |  | 573
13037 | 2019-06-24 | 2019-07-10 | 2019-10-24 | 2020-04-23 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-06-24 | COMP | 2020-07-17 | COMP | Rule 15/16 | 12 | 76 | 33 | 1 | 12 | 18 | 270
13114 | 2019-06-24 | 2019-07-11 | 2019-09-25 | 2019-09-30 | COMP | 2020-03-21 | REQD | 2019-10-08 | COMP | 2019-11-21 | COMP | 2019-12-17 | COMP | Rule 16 | 13 | 54 |  | 7 | 32 | 17 | 122
13331 | 2019-06-24 | 2019-07-22 | 2019-12-08 | 2020-02-13 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-02-25 | COMP | 2020-05-27 | COMP | Rule 16 | 20 | 96 | 2 | 1 | 7 | 66 | 233
13464 | 2019-06-24 | 2019-07-26 | 2019-09-18 | 2019-09-18 | COMP | 2019-09-24 | COMP | 2019-09-24 | COMP | 2019-09-19 | COMP | 2019-11-08 | COMP | Rule 16 | 24 | 38 | 5 | 1 | 0 | 34 | 98
13483 | 2019-06-24 | 2019-07-26 | 2019-08-12 | 2019-08-12 | COMP | 2019-11-15 | COMP | 2019-11-15 | COMP | 2022-03-08 | COMP | 2022-03-17 | COMP | Rule 16 | 24 | 12 | 68 | 1 | 580 | 8 | 688
13599 | 2019-06-24 | 2019-08-01 | 2019-11-16 | 2019-11-16 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2019-12-03 | COMP | 2019-12-02 | COMP | Rule 16 | 28 | 75 | 6 | 1 | 5 |  | 111
13612 | 2019-06-24 | 2019-08-01 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-07 | COMP | 2019-11-22 | COMP | 2019-12-27 | COMP | 2020-01-24 | COMP | Rule 16 | 28 | 64 | 7 | 11 | 23 | 19 | 147
13642 | 2019-06-24 | 2019-08-05 | 2019-11-19 | 2020-09-18 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-12-14 | COMP | 2022-02-05 | COMP | Rule 16 | 30 | 75 | 8 | 1 | 303 | 38 | 660
13677 | 2019-06-24 | 2019-08-05 | 2019-12-14 | 2019-12-14 | COMP | 2019-12-23 | COMP | 2020-01-06 | COMP | 2020-01-15 | COMP | 2020-03-06 | COMP | Rule 15/16 | 30 | 91 | 6 | 9 | 8 | 36 | 176
13707 | 2019-06-24 | 2019-08-07 | 2019-09-18 | 2019-09-18 | COMP | 2020-01-15 | COMP | 2020-01-15 | COMP | 2020-05-31 | INPR | 2020-02-07 | COMP | Rule 16 | 32 | 30 | 81 | 1 |  |  | 157
13738 | 2019-06-24 | 2019-08-07 | 2020-01-07 | 2020-01-07 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-07-06 | COMP | 2020-09-19 | COMP | Rule 16 | 32 | 104 | 49 | 1 | 79 | 54 | 314
13739 | 2019-06-24 | 2019-08-07 | 2020-01-07 | 2020-01-07 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-08-17 | COMP | 2020-10-01 | COMP | Rule 16 | 32 | 104 | 49 | 1 | 109 | 33 | 323
13776 | 2019-06-24 | 2019-08-08 | 2019-11-11 | 2019-11-11 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-07-07 | COMP | 2021-01-12 | COMP | Rule 16 | 33 | 66 | 25 | 1 | 140 | 130 | 391
13982 | 2019-06-24 | 2019-08-20 | 2019-10-17 | 2019-10-17 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-11-26 | COMP | 2019-12-26 | COMP | Rule 16 | 41 | 42 | 18 | 1 | 11 | 20 | 128
14004 | 2019-06-24 | 2019-08-21 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2020-04-01 | COMP | 2020-06-04 | COMP | Rule 15/16 | 42 | 70 | 7 | 1 | 78 | 46 | 239
14019 | 2019-06-24 | 2019-08-21 | 2019-12-09 | 2019-12-09 | COMP | 2019-12-12 | COMP | 2019-12-18 | COMP | 2019-12-12 | COMP | 2020-02-12 | COMP | Rule 16 | 42 | 75 | 4 | 5 | 0 | 38 | 160
14158 | 2019-06-24 | 2019-08-27 | 2019-10-31 | 2019-10-31 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-01-31 | COMP | 2020-03-21 | COMP | Rule 16 | 46 | 47 | 23 | 1 | 39 | 35 | 186
14196 | 2019-06-24 | 2019-08-29 | 2019-11-17 | 2019-11-17 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-07-13 | COMP | 2020-08-10 | COMP | Rule 16 | 48 | 55 | 44 | 1 | 121 | 21 | 286
14202 | 2019-06-24 | 2019-08-29 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-03-02 | COMP | 2020-06-15 | COMP | Rule 16 | 48 | 42 | 25 | 1 | 60 | 75 | 246
14208 | 2019-06-24 | 2019-08-29 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2019-10-15 | COMP | 2019-11-29 | COMP | Rule 16 | 48 | 20 | 15 | 1 | 0 | 30 | 110
14233 | 2019-06-24 | 2019-08-29 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2021-02-27 | INPR | 2020-02-22 | COMP | Rule 16 | 48 | 55 | 10 | 1 |  |  | 166
14255 | 2019-06-24 | 2019-08-31 | 2019-11-05 | 2019-11-05 | COMP | 2020-01-08 | COMP | 2021-02-19 | COMP | 2021-03-09 | COMP | 2021-03-24 | COMP | Rule 16 | 49 | 46 | 42 | 282 | 13 | 12 | 440
14731 | 2019-06-24 | 2019-09-24 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-12 | COMP | 2020-08-19 | COMP | 2020-10-30 | COMP | 2020-12-01 | COMP | Rule 16 | 65 | 100 | 17 | 114 | 52 | 20 | 363
14874 | 2019-06-24 | 2019-10-02 | 2020-02-19 | 2020-02-19 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-06-01 | COMP | 2020-09-04 | COMP | Rule 16 | 71 | 94 | 34 | 1 | 40 | 70 | 305
15228 | 2019-06-24 | 2019-10-22 | 2019-12-27 | 2020-04-08 | COMP | 2020-08-26 | COMP | 2020-08-28 | COMP | 2020-09-02 | COMP | 2020-12-16 | COMP | Rule 15/16 | 85 | 45 | 100 | 3 | 4 | 72 | 374
15503 | 2019-06-24 | 2019-11-05 | 2019-12-19 | 2019-12-19 | COMP | 2019-12-24 | COMP | 2020-01-23 | COMP | 2020-01-21 | COMP | 2020-02-12 | COMP | Rule 15/16 | 95 | 30 | 4 | 20 | 0 | 15 | 160
16095 | 2019-06-24 | 2019-12-09 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-06-02 | COMP | 2020-06-16 | COMP | Rule 16 | 116 | 39 | 32 | 1 | 53 | 11 | 247
16486 | 2019-06-24 | 2020-01-03 | 2020-03-25 | 2020-03-25 | COMP | 2020-06-08 | COMP | 2020-06-12 | COMP | 2020-06-15 | COMP | 2020-07-21 | COMP | Rule 16 | 133 | 57 | 53 | 5 | 2 | 27 | 272
16567 | 2019-06-24 | 2020-01-08 | 2020-03-06 | 2020-03-06 | COMP | 2020-07-07 | COMP | 2020-08-01 | COMP | 2020-07-08 | COMP | 2020-12-30 | COMP | Rule 15/16 | 136 | 41 | 87 | 19 | 0 | 103 | 383
16741 | 2019-06-24 | 2020-01-13 | 2020-04-30 | 2020-04-30 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-10-06 | COMP | 2020-10-14 | COMP | Rule 16 | 139 | 77 | 66 | 1 | 47 | 7 | 332
17097 | 2019-06-24 | 2020-02-01 | 2020-08-05 | 2020-08-05 | COMP | 2021-05-26 | COMP | 2022-01-13 | NOTN | 2021-11-22 | COMP | 2022-01-26 | COMP | Other | 152 | 131 | 203 |  |  |  | 653
17713 | 2019-06-24 | 2020-02-24 | 2020-03-30 | 2020-03-30 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-09-04 | COMP | Rule 16 | 167 | 26 | 65 | 1 | 1 | 50 | 305
20070 | 2019-06-24 | 2020-06-03 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-07-21 | COMP | 2020-08-04 | COMP | Rule 16 | 238 | 14 | 15 | 1 | 8 | 11 | 282
20364 | 2019-06-24 | 2020-06-17 | 2020-08-07 | 2020-08-07 | COMP | 2021-02-01 | COMP | 2021-02-01 | COMP | 2022-06-18 | INPR | 2021-03-13 | COMP | Rule 16 | 248 | 38 | 120 | 1 |  |  | 432
22226 | 2019-06-24 | 2020-09-15 | 2020-12-18 | 2021-03-30 | COMP | 2021-05-28 | COMP | 2021-07-11 | COMP | 2023-12-04 | INPR | 2021-07-16 | COMP | Rule 15/16 | 311 | 66 | 44 | 29 |  |  | 520
4210 | 2019-06-25 | 2019-07-22 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-06 | COMP | 2019-12-10 | COMP | 2019-12-03 | COMP | 2020-01-15 | COMP | Rule 16 | 19 | 88 | 9 | 3 | 0 | 25 | 140
12849 | 2019-06-25 | 2019-06-25 | 2019-11-22 | 2020-05-29 | COMP | 2020-08-03 | COMP | 2020-09-14 | COMP | 2021-09-07 | COMP | 2021-09-17 | COMP | Other | 1 | 106 | 47 | 30 | 247 | 9 | 563
13134 | 2019-06-25 | 2019-07-11 | 2019-10-21 | 2019-12-30 | COMP | 2020-02-19 | COMP | 2020-04-01 | COMP | 2020-05-11 | COMP | 2020-06-04 | COMP | Rule 16 | 12 | 72 | 35 | 31 | 29 | 18 | 238
13163 | 2019-06-25 | 2019-07-15 | 2019-08-13 | 2019-08-13 | COMP | 2019-09-18 | COMP | 2019-09-18 | COMP | 2019-12-18 | COMP | 2019-12-20 | COMP | Rule 16 | 14 | 22 | 26 | 1 | 63 | 3 | 124
13173 | 2019-06-25 | 2019-07-15 | 2019-11-13 | 2019-11-13 | COMP | 2019-12-10 | COMP | 2020-06-09 | COMP | 2021-04-09 | COMP | 2021-07-16 | COMP | Rule 16 | 14 | 86 | 18 | 126 | 211 | 69 | 519
13293 | 2019-06-25 | 2019-07-19 | 2019-08-30 | 2019-08-30 | COMP | 2019-10-03 | COMP | 2019-12-17 | COMP | 2019-07-19 | COMP | 2019-12-31 | COMP | Rule 16 | 18 | 31 | 24 | 51 | 0 | 10 | 130
13304 | 2019-06-25 | 2019-07-20 | 2019-09-18 | 2019-09-18 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2021-01-30 | INPR | 2020-01-09 | COMP | Rule 16 | 18 | 42 | 37 | 1 |  |  | 136
13430 | 2019-06-25 | 2019-07-25 | 2019-10-24 | 2019-10-24 | COMP | 2019-12-20 | COMP | 2019-12-24 | COMP | 2019-12-24 | COMP | 2020-02-26 | COMP | Rule 16 | 22 | 65 | 39 | 3 | 1 | 43 | 168
13470 | 2019-06-25 | 2019-07-25 | 2019-12-19 | 2019-12-19 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | 2020-02-03 | COMP | 2020-03-10 | COMP | Rule 16 | 22 | 102 | 24 | 1 | 7 | 26 | 177
13477 | 2019-06-25 | 2019-07-26 | 2019-12-20 | 2020-05-28 | COMP | 2020-09-30 | COMP | 2020-09-30 | COMP | 2021-06-25 | COMP | 2021-07-13 | COMP | Rule 16 | 23 | 102 | 89 | 1 | 185 | 12 | 516
13553 | 2019-06-25 | 2019-07-30 | 2019-09-09 | 2019-09-25 | COMP | 2019-10-03 | COMP | 2019-10-30 | COMP | 2019-12-16 | COMP | 2020-01-18 | COMP | Rule 16 | 25 | 29 | 7 | 20 | 31 | 23 | 142
13766 | 2019-06-25 | 2019-08-08 | 2019-12-10 | 2019-12-10 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2021-03-27 | INPR | 2020-02-27 | COMP | Rule 15/16 | 32 | 85 | 6 | 1 |  |  | 169
13833 | 2019-06-25 | 2019-08-12 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-30 | COMP | 2019-10-21 | COMP | 2019-09-17 | COMP | 2020-01-08 | COMP | Rule 16 | 34 | 18 | 18 | 16 | 0 | 53 | 135
13979 | 2019-06-25 | 2019-08-19 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-24 | COMP | 2020-03-27 | COMP | 2020-07-23 | COMP | 2020-09-08 | COMP | Rule 15/16 | 39 | 140 | 10 | 4 | 84 | 33 | 305
14003 | 2019-06-25 | 2019-08-21 | 2019-11-20 | 2019-11-20 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-08-04 | COMP | Rule 16 | 41 | 64 | 122 | 1 | 1 | 57 | 281
14135 | 2019-06-25 | 2019-08-26 | 2019-11-25 | 2019-12-16 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-05-01 | COMP | 2020-06-18 | COMP | Rule 16 | 44 | 64 | 54 | 1 | 43 | 34 | 248
14245 | 2019-06-25 | 2019-08-30 | 2019-11-22 | 2019-11-22 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-04-22 | COMP | 2020-03-12 | COMP | Rule 16 | 48 | 59 | 26 | 1 | 78 |  | 179
14355 | 2019-06-25 | 2019-09-06 | 2019-12-31 | 2019-12-31 | COMP | 2021-03-05 | COMP | 2021-03-05 | COMP | 2021-04-07 | COMP | 2021-06-22 | COMP | Rule 16 | 52 | 79 | 297 | 1 | 24 | 54 | 502
14525 | 2019-06-25 | 2019-09-14 | 2020-02-09 | 2020-02-09 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-16 | COMP | 2020-08-03 | COMP | Rule 16 | 57 | 99 | 87 | 1 | 4 | 35 | 280
14740 | 2019-06-25 | 2019-09-25 | 2020-01-04 | 2020-01-04 | COMP | 2020-01-15 | COMP | 2020-02-03 | COMP | 2020-01-15 | COMP | 2020-03-04 | COMP | Rule 16 | 65 | 68 | 8 | 13 | 0 | 22 | 173
15239 | 2019-06-25 | 2019-10-22 | 2019-12-08 | 2019-12-08 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2022-03-02 | COMP | 2022-05-06 | COMP | Rule 16 | 84 | 31 | 36 | 1 | 527 | 48 | 723
15605 | 2019-06-25 | 2019-11-09 | 2021-01-20 | 2021-01-20 | COMP | 2021-01-22 | COMP | 2021-09-08 | COMP |  | INPR | 2021-09-21 | COMP | Rule 16 | 97 | 298 | 3 | 160 |  |  | 565
15842 | 2019-06-25 | 2019-11-24 | 2020-03-05 | 2020-03-05 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2020-07-21 | COMP | 2020-08-05 | COMP | Rule 16 | 106 | 68 | 72 | 1 | 27 | 12 | 282
16720 | 2019-06-25 | 2020-01-13 | 2020-08-06 | 2020-08-07 | COMP | 2020-08-13 | COMP | 2022-01-30 | REQD | 2020-08-24 | COMP | 2020-09-30 | COMP | Rule 16 | 138 | 146 | 5 |  |  |  | 321
17135 | 2019-06-25 | 2020-02-01 | 2020-03-17 | 2020-10-27 | COMP | 2020-10-30 | COMP | 2020-05-21 | COMP | 2020-12-01 | COMP | 2021-01-07 | COMP | Rule 15/16 | 151 | 31 | 4 |  | 134 | 26 | 387
18123 | 2019-06-25 | 2020-03-11 | 2020-07-16 | 2020-07-16 | COMP | 2020-08-28 | COMP | 2020-11-18 | COMP | 2020-11-17 | COMP | 2020-12-31 | COMP | Rule 16 | 178 | 91 | 32 | 57 | 0 | 29 | 383
18316 | 2019-06-25 | 2020-03-19 | 2020-06-11 | 2020-06-11 | COMP | 2021-04-26 | COMP | 2021-04-28 | COMP | 2021-05-17 | COMP | 2021-06-09 | COMP | Rule 16 | 184 | 60 | 220 | 3 | 14 | 17 | 493
20531 | 2019-06-25 | 2020-06-25 | 2020-08-20 | 2020-08-20 | COMP | 2020-09-01 | COMP | 2020-10-07 | COMP | 2020-09-14 | COMP | 2020-12-29 | COMP | Rule 16 | 253 | 41 | 9 | 26 | 0 | 56 | 381
33401 | 2019-06-25 | 2021-12-27 | 2023-03-25 | 2023-04-20 | COMP | 2023-07-26 | COMP |  | REQD | 2023-08-15 | COMP | 2023-09-03 | COMP | Rule 16 | 631 | 312 | 67 |  |  |  | 1054
12996 | 2019-06-26 | 2019-07-03 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2020-03-09 | COMP | 2020-04-14 | COMP | Rule 16 | 6 | 100 | 10 | 1 | 62 | 27 | 201
13156 | 2019-06-26 | 2019-07-13 | 2019-08-24 | 2019-08-24 | COMP | 2019-08-30 | COMP | 2019-10-25 | COMP | 2019-12-02 | COMP | 2019-12-05 | COMP | Rule 16 | 12 | 30 | 5 | 40 | 24 | 4 | 112
13229 | 2019-06-26 | 2019-07-17 | 2019-12-06 | 2019-12-06 | COMP | 2020-07-23 | COMP | 2020-08-25 | COMP | 2020-08-31 | COMP | 2020-09-22 | COMP | Rule 16 | 15 | 99 | 160 | 24 | 5 | 16 | 314
13340 | 2019-06-26 | 2019-07-22 | 2019-10-05 | 2019-10-05 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-02-05 | COMP | 2020-02-24 | COMP | Rule 16 | 18 | 54 | 38 | 1 | 45 | 13 | 165
13566 | 2019-06-26 | 2019-07-30 | 2019-11-16 | 2019-11-16 | COMP | 2019-11-17 | NOTN | 2019-11-17 | COMP | 2019-11-18 | COMP | 2019-12-18 | COMP | Other | 24 | 77 |  | 0 | 1 | 21 | 121
13595 | 2019-06-26 | 2019-08-01 | 2019-11-18 | 2019-11-18 | COMP | 2019-11-21 | NOTN | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-02-25 | COMP | Other | 26 | 76 |  | 4 | 1 | 63 | 166
13650 | 2019-06-26 | 2019-08-05 | 2019-08-31 | 2019-08-31 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2019-11-12 | COMP | 2019-12-06 | COMP | Rule 16 | 28 | 20 | 6 | 1 | 45 | 17 | 113
13668 | 2019-06-26 | 2019-08-05 | 2019-11-04 | 2019-11-04 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-12-01 | COMP | 2020-02-11 | COMP | Rule 16 | 28 | 65 | 12 | 1 | 6 | 49 | 157
14164 | 2019-06-26 | 2019-08-29 | 2019-09-30 | 2019-10-09 | COMP | 2019-11-05 | COMP | 2019-11-05 | COMP | 2021-02-27 | INPR | 2020-02-05 | COMP | Rule 16 | 46 | 22 | 20 | 1 |  |  | 153
14294 | 2019-06-26 | 2019-09-03 | 2019-10-31 | 2019-10-31 | COMP | 2019-11-15 | COMP | 2019-11-15 | COMP | 2019-09-03 | COMP | 2020-06-11 | COMP | Rule 16 | 48 | 43 | 11 | 1 | 0 | 143 | 242
14388 | 2019-06-26 | 2019-09-08 | 2020-01-23 | 2020-01-23 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | 2021-03-27 | INPR | 2020-03-13 | COMP | Rule 16 | 51 | 93 | 22 | 1 |  |  | 179
14721 | 2019-06-26 | 2019-09-25 | 2019-10-26 | 2019-10-26 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-12-10 | COMP | Rule 16 | 64 | 23 | 12 | 1 | 1 | 18 | 115
15055 | 2019-06-26 | 2019-10-10 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2020-01-13 | COMP | 2020-02-09 | COMP | Rule 16 | 75 | 21 | 19 | 1 | 25 | 19 | 155
15062 | 2019-06-26 | 2019-10-10 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-09 | COMP | 2020-03-18 | COMP | 2020-03-24 | COMP | 2020-06-11 | COMP | Rule 16 | 75 | 84 | 18 | 8 | 5 | 57 | 242
15582 | 2019-06-26 | 2019-11-07 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-15 | COMP | 2020-01-15 | COMP | 2020-02-07 | COMP | 2020-02-20 | COMP | Rule 16 | 95 | 26 | 20 | 1 | 17 | 9 | 163
15678 | 2019-06-26 | 2019-11-15 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-27 | COMP | 2020-10-05 | COMP | 2020-10-23 | COMP | 2020-11-13 | COMP | Rule 16 | 100 | 154 | 22 | 50 | 15 | 15 | 351
16422 | 2019-06-26 | 2019-12-30 | 2020-02-18 | 2020-02-18 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-05-11 | COMP | 2020-06-24 | COMP | Rule 16 | 128 | 34 | 47 | 1 | 14 | 32 | 251
17385 | 2019-06-26 | 2020-02-12 | 2020-06-17 | 2020-07-30 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2020-12-08 | COMP | 2021-02-04 | COMP | Rule 15/16 | 158 | 89 | 35 | 1 | 56 | 40 | 405
18335 | 2019-06-26 | 2020-03-20 | 2020-09-01 | 2020-09-01 | COMP | 2020-09-24 | COMP | 2020-09-24 | COMP | 2022-01-30 | INPR | 2020-10-30 | COMP | Rule 16 | 184 | 117 | 17 | 1 |  |  | 342
18341 | 2019-06-26 | 2020-03-20 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2022-01-30 | INPR | 2020-07-09 | COMP | Rule 16 | 184 | 8 | 19 | 1 |  |  | 262
19093 | 2019-06-26 | 2020-04-21 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-08-24 | COMP | 2020-10-14 | COMP | Rule 16 | 206 | 69 | 15 | 1 | 7 | 37 | 330
4239 | 2019-06-27 | 2019-09-30 | [7 empty] | 2019-10-18 | COMP | 2019-11-01 | COMP | Other | 66 | [5 empty] | 90
12927 | 2019-06-27 | 2019-07-02 | 2019-10-16 | 2019-10-16 | COMP | 2019-12-31 | COMP | 2020-02-11 | COMP | 2023-11-12 | INPR | 2020-07-30 | COMP | Rule 16 | 4 | 75 | 51 | 29 |  |  | 276
13145 | 2019-06-27 | 2019-07-12 | 2019-08-12 | 2019-08-20 | COMP | 2019-09-16 | COMP | 2019-09-18 | COMP | 2019-10-01 | COMP | 2019-11-19 | COMP | Rule 16 | 11 | 22 | 19 | 3 | 10 | 35 | 101
13627 | 2019-06-27 | 2019-08-02 | 2019-09-21 | 2019-09-21 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-01-10 | COMP | 2020-02-25 | COMP | Rule 16 | 26 | 35 | 69 | 1 | 7 | 31 | 165
13743 | 2019-06-27 | 2019-08-07 | 2019-08-12 | 2019-08-12 | COMP | 2019-08-14 | COMP | 2019-08-14 | COMP | 2019-09-11 | COMP | 2019-09-12 | COMP | Rule 16 | 29 | 4 | 3 | 1 | 20 | 2 | 54
13905 | 2019-06-27 | 2019-08-15 | 2019-09-12 | 2020-01-12 | COMP | 2020-01-29 | COMP | 2020-02-27 | COMP | 2020-03-20 | COMP | 2020-04-13 | COMP | Rule 16 | 35 | 20 | 12 | 21 | 17 | 17 | 199
14030 | 2019-06-27 | 2019-08-22 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-06-23 | COMP | 2020-07-16 | COMP | Rule 16 | 40 | 154 | 14 | 1 | 44 | 18 | 266
14102 | 2019-06-27 | 2019-08-27 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-15 | COMP | 2019-11-19 | COMP | 2019-11-06 | COMP | 2019-12-12 | COMP | Rule 16 | 43 | 22 | 14 | 25 | 0 | 16 | 116
14249 | 2019-06-27 | 2019-08-30 | 2020-01-06 | 2020-01-06 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-06-09 | COMP | 2020-08-06 | COMP | Rule 16 | 46 | 86 | 85 | 1 | 25 | 43 | 281
14319 | 2019-06-27 | 2019-09-04 | 2019-11-06 | 2019-11-06 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-08-20 | COMP | 2020-09-01 | COMP | Rule 16 | 48 | 46 | 16 | 1 | 184 | 9 | 299
14375 | 2019-06-27 | 2019-09-06 | 2019-12-09 | 2019-12-09 | COMP | 2022-07-27 | COMP | 2022-07-27 | COMP | 2022-07-27 | COMP | 2022-12-16 | COMP | Rule 16 | 50 | 64 | 664 | 1 | 1 | 99 | 874
14743 | 2019-06-27 | 2019-09-25 | 2019-12-13 | 2019-12-13 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2023-04-11 | COMP | 2023-06-27 | COMP | Rule 16 | 63 | 55 | 67 | 1 | 770 | 54 | 1005
14837 | 2019-06-27 | 2019-09-30 | 2020-02-20 | 2020-02-20 | COMP | 2020-02-27 | COMP | 2020-03-05 | INPR | 2022-02-26 | REQD | 2021-01-11 | COMP | Rule 16 | 66 | 97 | 6 |  |  |  | 387
15181 | 2019-06-27 | 2019-10-17 | 2020-03-12 | 2020-03-12 | COMP | 2020-06-17 | COMP | 2020-06-10 | COMP | 2020-06-30 | COMP | 2020-07-10 | COMP | Rule 16 | 79 | 99 | 69 |  | 15 | 9 | 262
16938 | 2019-06-27 | 2020-01-25 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-04 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-12-16 | COMP | Rule 16 | 144 | 81 | 12 | 28 | 1 | 109 | 371
18175 | 2019-06-27 | 2020-03-13 | 2020-08-26 | 2020-08-26 | COMP | 2020-10-12 | COMP | 2020-10-12 | COMP | 2022-09-13 | COMP | 2022-09-19 | COMP | Rule 16 | 178 | 118 | 33 | 1 | 483 | 5 | 813
19119 | 2019-06-27 | 2020-04-22 | 2020-10-15 | 2020-10-15 | COMP | 2021-01-27 | COMP | 2021-01-27 | COMP | 2021-03-08 | COMP | 2021-04-28 | COMP | Rule 16 | 206 | 125 | 69 | 1 | 28 | 38 | 462
12921 | 2019-06-28 | 2019-06-28 | 2019-08-22 | 2019-08-22 | COMP | 2019-08-22 | NOTN | 2019-08-22 | COMP | 2020-01-03 | COMP | 2020-10-22 | COMP | Other | 1 | 39 |  | 1 | 91 | 206 | 334
13235 | 2019-06-28 | 2019-07-17 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-04 | COMP | 2019-12-19 | COMP | 2019-12-30 | COMP | 2020-01-23 | COMP | Rule 16 | 13 | 75 | 4 | 31 | 7 | 17 | 142
13251 | 2019-06-28 | 2019-07-18 | 2019-09-17 | 2019-09-17 | COMP | 2019-11-26 | COMP | 2020-05-07 | COMP | 2020-04-01 | COMP | 2020-06-29 | COMP | Rule 15/16 | 14 | 43 | 50 | 112 | 0 | 37 | 252
13330 | 2019-06-28 | 2019-07-22 | 2019-12-12 | 2019-12-12 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-05-31 | INPR | 2020-02-12 | COMP | Rule 16 | 16 | 100 | 25 | 1 |  |  | 156
13486 | 2019-06-28 | 2019-07-26 | 2019-08-11 | 2019-08-11 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-09-03 | COMP | 2019-10-01 | COMP | Rule 16 | 20 | 11 | 14 | 1 | 3 | 21 | 66
13489 | 2019-06-28 | 2019-07-26 | 2019-08-28 | 2019-08-28 | COMP | 2019-09-10 | COMP | 2019-09-10 | COMP | 2020-03-01 | INPR | 2019-11-12 | COMP | Rule 16 | 20 | 24 | 9 | 1 |  |  | 95
13499 | 2019-06-28 | 2019-07-29 | 2019-12-04 | 2019-12-04 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-03-09 | COMP | Rule 16 | 21 | 89 | 46 | 1 | 1 | 20 | 173
13520 | 2019-06-28 | 2019-07-29 | 2019-10-04 | 2019-10-04 | COMP | 2019-10-18 | COMP | 2019-10-18 | INPR | 2019-11-07 | COMP | 2019-11-14 | COMP | Rule 16 | 21 | 49 | 11 |  |  |  | 97
13528 | 2019-06-28 | 2019-07-30 | 2019-11-12 | 2020-04-20 | COMP | 2020-06-01 | COMP | 2020-06-08 | COMP | 2020-06-16 | COMP | 2020-07-22 | COMP | Rule 15/16 | 22 | 74 | 30 | 6 | 7 | 27 | 269
13578 | 2019-06-28 | 2019-07-31 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-25 | COMP | 2019-12-10 | COMP | Rule 16 | 23 | 48 | 13 | 1 | 23 | 10 | 113
13641 | 2019-06-28 | 2019-08-03 | 2020-01-07 | 2020-01-07 | COMP | 2020-05-29 | COMP | 2020-06-02 | COMP | 2020-05-07 | COMP | 2020-07-07 | COMP | Rule 16 | 25 | 106 | 101 | 3 | 0 | 26 | 258
13661 | 2019-06-28 | 2019-08-05 | 2019-12-08 | 2019-12-08 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-06-14 | COMP | 2020-07-03 | COMP | Rule 16 | 26 | 86 | 86 | 1 | 45 | 15 | 256
13869 | 2019-06-28 | 2019-08-14 | 2019-09-06 | 2019-09-06 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-12-14 | COMP | 2020-12-15 | COMP | Rule 16 | 33 | 17 | 73 | 1 | 248 | 2 | 369
13873 | 2019-06-28 | 2019-08-14 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-18 | COMP | 2019-09-18 | COMP | 2020-03-10 | COMP | 2020-03-28 | COMP | Rule 16 | 33 | 18 | 8 | 1 | 118 | 14 | 187
13885 | 2019-06-28 | 2019-08-14 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-08-03 | COMP | 2020-09-30 | COMP | Rule 15/16 | 33 | 185 | 71 | 1 | 0 | 32 | 318
14298 | 2019-06-28 | 2019-09-03 | 2019-11-13 | 2020-01-16 | COMP | 2020-01-28 | COMP | 2020-10-23 | COMP | 2021-01-25 | COMP | 2021-04-08 | COMP | Rule 16 | 46 | 51 | 8 | 191 | 61 | 53 | 447
14537 | 2019-06-28 | 2019-09-16 | 2020-02-07 | 2020-02-07 | COMP | 2020-03-23 | COMP | 2020-04-13 | COMP | 2020-04-07 | COMP | 2020-04-18 | COMP | Rule 15/16 | 55 | 99 | 31 | 16 | 0 | 5 | 202
14549 | 2019-06-28 | 2019-09-16 | 2020-02-07 | 2020-02-07 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-04-03 | COMP | 2020-05-12 | COMP | Rule 16 | 55 | 99 | 36 | 1 | 5 | 28 | 219
15138 | 2019-06-28 | 2019-10-15 | 2020-03-03 | 2020-04-23 | COMP | 2020-06-08 | COMP | 2020-10-09 | COMP | 2021-07-01 | COMP | 2021-07-14 | COMP | Rule 15 | 76 | 94 | 32 | 89 | 182 | 9 | 514
15155 | 2019-06-28 | 2019-10-16 | 2019-12-02 | 2020-03-27 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-06-29 | COMP | 2020-07-21 | COMP | Rule 16 | 77 | 31 | 22 | 1 | 45 | 17 | 268
15209 | 2019-06-28 | 2019-10-21 | 2020-04-03 | 2020-04-03 | COMP | 2020-05-04 | COMP | 2020-08-12 | COMP | 2020-10-08 | COMP | 2020-12-03 | COMP | Rule 15/16 | 80 | 113 | 22 | 72 | 41 | 38 | 361
15695 | 2019-06-28 | 2019-11-15 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-05 | COMP | 2020-12-23 | COMP | 2022-03-08 | COMP | 2022-04-15 | COMP | Rule 16 | 98 | 48 | 7 | 225 | 303 | 29 | 705
16551 | 2019-06-28 | 2020-01-07 | 2020-03-08 | 2020-03-08 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-07-03 | COMP | 2020-08-04 | COMP | Rule 16 | 131 | 42 | 19 | 1 | 66 | 23 | 278
16722 | 2019-06-28 | 2020-01-13 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2022-01-30 | INPR | 2020-06-09 | COMP | Rule 16 | 135 | 44 | 6 | 1 |  |  | 238
20294 | 2019-06-28 | 2020-06-15 | 2020-08-21 | 2020-08-21 | COMP | 2020-09-21 | COMP | 2020-11-23 | COMP | 2020-12-28 | COMP | 2021-02-09 | COMP | Rule 15/16 | 242 | 50 | 21 | 45 | 23 | 30 | 406
13797 | 2019-06-29 | 2019-08-10 | 2019-09-14 | 2019-09-14 | COMP | 2019-09-25 | COMP | 2019-09-25 | COMP | 2019-10-07 | COMP | 2019-11-25 | COMP | Rule 16 | 29 | 24 | 8 | 1 | 9 | 35 | 103
15148 | 2019-06-29 | 2019-10-16 | 2020-02-10 | 2020-02-10 | COMP | 2020-04-20 | COMP | 2020-04-30 | COMP | 2022-07-30 | INPR | 2020-08-12 | COMP | Rule 16 | 76 | 78 | 50 | 9 |  |  | 283
18863 | 2019-06-29 | 2020-04-09 | 2020-04-27 | 2020-04-27 | COMP | 2020-06-01 | COMP | 2020-06-01 | INPR | 2023-01-28 | REQD | 2021-07-09 | COMP | Rule 16 | 195 | 13 | 25 |  |  |  | 510
13500 | 2019-06-30 | 2019-07-29 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2020-01-13 | COMP | Rule 16 | 20 | 27 | 9 | 1 | 1 | 81 | 134
13967 | 2019-06-30 | 2019-08-19 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-13 | COMP | 2020-06-30 | COMP | 2020-08-12 | COMP | 2020-10-20 | COMP | Rule 16 | 35 | 151 | 35 | 34 | 32 | 49 | 331
14111 | 2019-06-30 | 2019-08-26 | 2019-10-09 | 2019-10-09 | COMP | 2019-11-21 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-12-17 | COMP | Rule 15/16 | 40 | 32 | 31 |  | 1 | 39 | 117
14474 | 2019-06-30 | 2019-09-12 | 2019-12-23 | 2019-12-23 | COMP | 2020-01-27 | COMP | 2020-02-24 | COMP | 2020-06-30 | COMP | 2020-08-18 | COMP | Rule 16 | 52 | 70 | 23 | 20 | 91 | 36 | 287
17033 | 2019-06-30 | 2020-01-28 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-03-16 | COMP | 2020-04-10 | COMP | Rule 15/16 | 144 | 25 | 6 | 1 | 5 | 20 | 196
17399 | 2019-06-30 | 2020-02-12 | 2020-05-27 | 2020-05-27 | COMP | 2020-05-29 | NOTN | 2020-09-23 | COMP | 2021-04-20 | COMP | 2021-05-03 | COMP | Other | 155 | 74 |  | 85 | 143 | 10 | 463
12957 | 2019-07-01 | 2019-07-01 | 2019-08-28 | 2019-08-28 | COMP | 2019-10-15 | COMP | 2019-12-02 | COMP | 2023-04-30 | INPR | 2020-01-15 | COMP | Rule 16 | 1 | 42 | 34 | 32 |  |  | 136
12974 | 2019-07-01 | 2019-07-03 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2019-12-18 | COMP | 2020-02-03 | COMP | Rule 16 | 3 | 100 | 8 | 1 | 10 | 31 | 148
12988 | 2019-07-01 | 2019-07-03 | 2019-10-31 | 2019-10-31 | COMP | 2020-02-03 | COMP | 2020-05-04 | COMP | 2020-04-28 | COMP | 2020-05-28 | COMP | Rule 16 | 3 | 85 | 62 | 65 | 0 | 18 | 229
12989 | 2019-07-01 | 2019-07-03 | 2019-11-23 | 2019-11-23 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-03-10 | COMP | 2020-04-29 | COMP | Rule 16 | 3 | 100 | 46 | 1 | 26 | 37 | 209
12999 | 2019-07-01 | 2019-07-03 | 2019-11-22 | 2019-11-22 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-03-30 | COMP | 2020-04-15 | COMP | Rule 16 | 3 | 100 | 47 | 1 | 40 | 13 | 199
13174 | 2019-07-01 | 2019-07-15 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-21 | COMP | 2019-11-06 | COMP | 2021-03-27 | INPR | 2020-01-02 | COMP | Rule 16 | 10 | 58 | 13 | 13 |  |  | 127
13404 | 2019-07-01 | 2019-07-24 | 2019-09-10 | 2019-09-10 | COMP | 2019-09-18 | COMP | 2019-12-09 | COMP | 2019-10-24 | COMP | 2020-01-03 | COMP | Rule 15/16 | 17 | 34 | 7 | 56 | 0 | 18 | 128
13433 | 2019-07-01 | 2019-07-25 | 2019-09-13 | 2019-11-19 | COMP | 2019-12-04 | COMP | 2019-11-02 | COMP | 2019-07-25 | COMP | 2020-01-06 | COMP | Rule 16 | 18 | 36 | 10 |  | 0 | 41 | 129
13444 | 2019-07-01 | 2019-07-25 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2021-07-23 | COMP | 2021-09-03 | COMP | Rule 16 | 18 | 59 | 19 | 1 | 427 | 31 | 550
13457 | 2019-07-01 | 2019-07-26 | 2019-09-30 | 2020-02-24 | COMP | 2020-03-03 | COMP | 2019-10-11 | COMP | 2020-04-07 | COMP | 2020-11-16 | COMP | Rule 15/16 | 19 | 46 | 7 |  | 121 | 157 | 349
13473 | 2019-07-01 | 2019-07-26 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-23 | COMP | 2019-09-23 | INPR | 2019-09-18 | COMP | 2019-09-18 | COMP | Rule 16 | 19 | 29 | 13 |  |  |  | 56
13533 | 2019-07-01 | 2019-07-30 | 2019-11-02 | 2019-12-13 | COMP | 2020-02-03 | COMP | 2020-01-14 | COMP | 2020-01-02 | COMP | 2020-02-05 | COMP | Rule 16 | 21 | 68 | 34 |  | 0 | 16 | 150
13623 | 2019-07-01 | 2019-08-02 | 2019-12-04 | 2020-02-01 | COMP | 2020-02-06 | COMP | 2020-03-19 | COMP | 2020-02-10 | COMP | 2020-04-22 | COMP | Rule 16 | 24 | 85 | 4 | 30 | 0 | 25 | 204
13989 | 2019-07-01 | 2019-08-20 | 2019-09-27 | 2019-11-05 | COMP | 2021-02-07 | NOTN | 2021-02-23 | COMP | 2019-09-30 | COMP | 2021-04-27 | COMP | Other | 36 | 28 |  | 325 | 0 | 46 | 459
14031 | 2019-07-01 | 2019-08-22 | 2019-11-14 | 2019-11-14 | COMP | 2020-01-16 | COMP | 2020-02-10 | COMP | 2020-02-11 | COMP | 2020-04-03 | COMP | Rule 15/16 | 38 | 59 | 42 | 17 | 2 | 38 | 191
14048 | 2019-07-01 | 2019-08-22 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-30 | COMP | 2020-05-26 | COMP | 2020-04-02 | COMP | 2020-06-18 | COMP | Rule 15/16 | 38 | 80 | 30 | 82 | 0 | 18 | 244
14261 | 2019-07-01 | 2019-09-03 | 2020-01-16 | 2020-01-16 | COMP | 2020-05-06 | COMP | 2020-05-09 | COMP | 2020-06-18 | COMP | 2020-07-22 | COMP | Rule 15/16 | 45 | 93 | 78 | 3 | 28 | 25 | 268
14362 | 2019-07-01 | 2019-09-05 | 2019-12-03 | 2019-12-03 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2021-02-10 | COMP | 2021-06-02 | COMP | Rule 16 | 47 | 61 | 133 | 1 | 168 | 79 | 484
14635 | 2019-07-01 | 2019-09-20 | 2019-11-13 | 2019-11-13 | COMP | 2019-12-19 | COMP | 2020-01-21 | COMP | 2020-02-18 | COMP | 2020-03-03 | COMP | Rule 16 | 58 | 38 | 25 | 21 | 20 | 11 | 168
14665 | 2019-07-01 | 2019-09-22 | 2020-01-21 | 2020-01-21 | COMP | 2020-06-19 | COMP | 2020-08-10 | COMP | 2020-07-20 | COMP | 2020-09-21 | COMP | Rule 15/16 | 58 | 81 | 107 | 37 | 0 | 30 | 310
15080 | 2019-07-01 | 2019-10-10 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-09-27 | COMP | 2020-10-30 | COMP | Rule 15/16 | 72 | 101 | 52 | 1 | 92 | 25 | 339
15316 | 2019-07-01 | 2019-10-25 | 2020-01-22 | 2020-02-06 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2021-05-30 | INPR | 2020-05-06 | COMP | Rule 16 | 83 | 58 | 4 | 1 |  |  | 214
15591 | 2019-07-01 | 2019-11-08 | 2019-12-09 | 2019-12-09 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-01-06 | COMP | 2020-01-30 | COMP | Rule 16 | 93 | 19 | 10 | 1 | 10 | 18 | 146
15966 | 2019-07-01 | 2019-12-04 | 2020-02-19 | 2020-02-19 | COMP | 2020-02-24 | COMP | 2020-04-10 | COMP | 2020-07-07 | COMP | 2020-07-29 | COMP | Rule 16 | 108 | 52 | 4 | 35 | 62 | 17 | 273
16268 | 2019-07-01 | 2019-12-18 | 2020-09-09 | 2020-09-22 | COMP | 2020-09-29 | COMP | 2020-10-14 | COMP | 2022-01-30 | INPR | 2020-11-04 | COMP | Rule 16 | 118 | 185 | 6 | 12 |  |  | 342
16400 | 2019-07-01 | 2019-12-27 | 2020-12-01 | 2020-12-01 | COMP | 2021-01-11 | COMP | 2021-01-25 | COMP | 2021-06-25 | COMP | 2021-08-16 | COMP | Rule 16 | 124 | 235 | 28 | 10 | 108 | 36 | 536
16428 | 2019-07-01 | 2019-12-30 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-07-01 | COMP | 2020-09-22 | COMP | Rule 16 | 125 | 86 | 41 | 1 | 4 | 59 | 311
16647 | 2019-07-01 | 2020-01-09 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-04 | COMP | 2020-10-22 | NOTN | 2021-01-04 | COMP | 2021-01-19 | COMP | Rule 16 | 132 | 16 | 2 |  |  |  | 390
16648 | 2019-07-01 | 2020-01-09 | 2020-04-22 | 2020-04-22 | COMP | 2020-04-30 | COMP | 2020-08-13 | COMP | 2020-08-14 | COMP | 2020-10-06 | COMP | Rule 15/16 | 132 | 73 | 7 | 75 | 2 | 37 | 321
17448 | 2019-07-01 | 2020-02-13 | 2020-12-23 | 2020-12-23 | COMP | 2020-12-31 | COMP | 2022-10-05 | COMP | 2022-10-04 | COMP | 2022-10-14 | COMP | Rule 16 | 156 | 219 | 6 | 445 | 0 | 8 | 830
17780 | 2019-07-01 | 2020-02-26 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-29 | COMP | 2020-05-06 | COMP | 2020-07-20 | COMP | 2020-08-10 | COMP | Rule 16 | 164 | 42 | 5 | 6 | 53 | 16 | 281
18654 | 2019-07-01 | 2020-04-02 | 2020-08-14 | 2020-08-14 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2021-05-17 | COMP | 2021-07-16 | COMP | Rule 16 | 190 | 96 | 40 | 1 | 150 | 43 | 515
19004 | 2019-07-01 | 2020-04-16 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-10-22 | COMP | 2020-11-18 | COMP | Rule 16 | 200 | 11 | 30 | 1 | 95 | 19 | 351
21474 | 2019-07-01 | 2020-08-10 | 2020-08-20 | 2020-08-20 | COMP | 2020-08-21 | NOTN | 2020-09-08 | COMP | 2020-08-21 | COMP | 2020-10-06 | COMP | Other | 281 | 9 |  | 13 | 0 | 21 | 321
12964 | 2019-07-02 | 2019-07-02 | 2019-09-28 | 2019-09-28 | COMP | 2020-01-06 | COMP | 2020-06-09 | COMP | 2020-06-10 | COMP | 2020-10-14 | COMP | Rule 15/16 | 1 | 62 | 66 | 109 | 2 | 90 | 326
12973 | 2019-07-02 | 2019-07-02 | 2019-09-26 | 2020-01-29 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-03-03 | COMP | 2020-05-15 | COMP | Rule 16 | 1 | 61 | 17 | 1 | 8 | 54 | 220
13377 | 2019-07-02 | 2019-07-23 | 2019-10-12 | 2019-10-12 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-12-30 | COMP | Rule 16 | 15 | 58 | 13 | 1 | 1 | 40 | 124
13458 | 2019-07-02 | 2019-07-26 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-03-03 | COMP | 2020-04-13 | COMP | Rule 16 | 18 | 90 | 21 | 1 | 41 | 30 | 196
13467 | 2019-07-02 | 2019-07-25 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-06 | COMP | 2020-05-20 | COMP | 2020-04-16 | COMP | 2020-05-27 | COMP | Rule 15/16 | 17 | 91 | 22 | 96 | 0 | 5 | 227
13474 | 2019-07-02 | 2019-07-26 | 2019-08-21 | 2019-08-21 | COMP | 2019-10-01 | COMP | 2019-10-14 | COMP | 2019-09-16 | COMP | 2019-10-22 | COMP | Rule 16 | 18 | 19 | 29 | 10 | 0 | 7 | 79
13611 | 2019-07-02 | 2019-08-02 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-23 | COMP | 2020-02-04 | COMP | 2021-02-10 | COMP | 2021-03-30 | COMP | Rule 16 | 23 | 92 | 7 | 29 | 258 | 34 | 438
13756 | 2019-07-02 | 2019-08-07 | 2020-01-03 | 2020-03-23 | COMP | 2020-04-07 | COMP | 2020-07-30 | COMP | 2020-07-20 | COMP | 2020-09-21 | COMP | Rule 15/16 | 26 | 102 | 12 | 82 | 0 | 37 | 309
13757 | 2019-07-02 | 2019-08-07 | 2020-02-08 | 2020-02-08 | COMP | 2020-03-27 | COMP | 2020-04-06 | COMP | 2020-07-24 | COMP | 2020-09-02 | COMP | Rule 16 | 26 | 126 | 34 | 7 | 79 | 29 | 297
13896 | 2019-07-02 | 2019-08-15 | 2019-11-20 | 2019-11-20 | COMP | 2020-02-28 | COMP | 2020-03-19 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | Rule 16 | 32 | 68 | 67 | 15 | 62 | 1 | 240
13939 | 2019-07-02 | 2019-08-16 | 2020-02-11 | 2020-02-11 | COMP | 2020-03-02 | COMP | 2020-05-21 | COMP | 2020-07-28 | COMP | 2020-12-02 | COMP | Rule 15/16 | 33 | 121 | 14 | 59 | 48 | 88 | 358
14018 | 2019-07-02 | 2019-08-21 | 2019-10-03 | 2019-10-03 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-05-07 | COMP | 2020-07-01 | COMP | Rule 16 | 36 | 31 | 73 | 1 | 77 | 39 | 252
14067 | 2019-07-02 | 2019-08-23 | 2019-10-23 | 2019-10-23 | COMP | 2019-10-28 | COMP | 2019-10-28 | COMP | 2020-03-10 | COMP | 2020-03-26 | COMP | Rule 15/16 | 38 | 43 | 4 | 1 | 90 | 13 | 184
14153 | 2019-07-02 | 2019-08-27 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-09-23 | COMP | 2019-10-18 | COMP | Rule 16 | 40 | 9 | 11 | 1 | 1 | 20 | 77
14237 | 2019-07-02 | 2019-08-30 | 2019-10-04 | 2019-10-04 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-11-15 | COMP | 2019-12-04 | COMP | Rule 16 | 43 | 25 | 12 | 1 | 19 | 12 | 107
14338 | 2019-07-02 | 2019-09-05 | 2019-11-25 | 2019-11-25 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2021-10-15 | COMP | 2022-03-14 | COMP | Rule 16 | 46 | 57 | 94 | 1 | 384 | 102 | 679
14378 | 2019-07-02 | 2019-09-09 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-11-14 | COMP | 2019-11-14 | COMP | Rule 16 | 48 | 21 | 4 | 1 | 25 | 1 | 95
14438 | 2019-07-02 | 2019-09-10 | 2020-05-11 | 2020-05-11 | COMP | 2021-03-23 | COMP | 2022-05-05 | COMP | 2022-06-23 | COMP | 2022-08-05 | COMP | Rule 15/16 | 49 | 168 | 218 | 285 | 34 | 31 | 780
14483 | 2019-07-02 | 2019-09-12 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-02-25 | COMP | Rule 16 | 51 | 75 | 15 | 1 | 1 | 24 | 162
14677 | 2019-07-02 | 2019-09-23 | 2019-12-13 | 2020-08-03 | COMP | 2020-11-03 | COMP | 2020-11-03 | COMP | 2021-01-07 | COMP | 2021-01-22 | COMP | Rule 16 | 58 | 57 | 66 | 1 | 43 | 11 | 392
14726 | 2019-07-02 | 2019-09-25 | 2019-11-23 | 2020-06-16 | COMP | 2020-06-30 | COMP | 2020-06-23 | INPR | 2020-06-11 | COMP | 2020-07-29 | COMP | Rule 16 | 60 | 42 | 11 |  |  |  | 272
14752 | 2019-07-02 | 2019-09-25 | 2020-02-05 | 2020-02-05 | COMP | 2020-03-10 | COMP | 2020-06-19 | COMP | 2020-08-31 | COMP | 2020-10-02 | COMP | Rule 16 | 60 | 90 | 24 | 73 | 52 | 24 | 318
14809 | 2019-07-02 | 2019-09-28 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-09-15 | COMP | 2021-01-11 | COMP | Rule 16 | 62 | 73 | 17 | 1 | 155 | 80 | 384
14848 | 2019-07-02 | 2019-10-01 | 2019-11-21 | 2019-11-21 | COMP | 2019-11-21 | NOTN | 2019-11-21 | COMP | 2019-12-02 | COMP | 2019-12-31 | COMP | Other | 64 | 37 |  | 1 | 6 | 21 | 125
14938 | 2019-07-02 | 2019-10-04 | 2020-03-22 | 2020-06-09 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-07-01 | COMP | 2020-08-11 | COMP | Rule 16 | 67 | 114 | 6 | 1 | 12 | 30 | 281
15043 | 2019-07-02 | 2019-10-10 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-11 | COMP | 2020-03-06 | COMP | 2021-03-27 | INPR | 2020-03-09 | COMP | Rule 16 | 71 | 94 | 10 |  |  |  | 171
15097 | 2019-07-02 | 2019-10-12 | 2020-03-13 | 2020-09-09 | COMP | 2021-02-12 | COMP | 2021-03-31 | COMP | 2021-04-13 | COMP | 2021-05-24 | COMP | Rule 15/16 | 72 | 103 | 107 | 33 | 10 | 30 | 477
15308 | 2019-07-02 | 2019-10-25 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-26 | COMP | 2020-10-21 | COMP | 2021-11-02 | COMP | 2021-11-19 | COMP | Rule 16 | 82 | 90 | 56 | 106 | 260 | 13 | 602
15320 | 2019-07-02 | 2019-10-26 | 2020-05-08 | 2020-05-08 | COMP | 2020-06-04 | COMP | 2020-06-17 | INPR | 2020-07-24 | COMP | 2020-07-03 | COMP | Rule 16 | 82 | 133 | 19 |  |  |  | 254
15601 | 2019-07-02 | 2019-11-08 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-06-24 | COMP | 2020-08-19 | COMP | Rule 16 | 92 | 93 | 6 | 1 | 59 | 41 | 287
15826 | 2019-07-02 | 2019-11-22 | 2020-02-09 | 2020-03-04 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-05-29 | COMP | 2020-06-24 | COMP | Rule 16 | 101 | 51 | 36 | 1 | 27 | 19 | 247
16478 | 2019-07-02 | 2020-01-03 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-03-31 | COMP | 2020-04-28 | COMP | Rule 16 | 127 | 30 | 17 | 1 | 16 | 21 | 207
16821 | 2019-07-02 | 2020-01-17 | 2020-04-10 | 2020-04-10 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2021-05-27 | COMP | 2021-07-02 | COMP | Rule 16 | 137 | 59 | 59 | 1 | 228 | 26 | 505
16841 | 2019-07-02 | 2020-01-21 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-17 | COMP | 2020-07-29 | COMP | 2020-08-10 | COMP | 2020-09-15 | COMP | Rule 15/16 | 138 | 57 | 7 | 73 | 9 | 26 | 305
16842 | 2019-07-02 | 2020-01-21 | 2020-03-19 | 2020-03-19 | COMP | 2020-03-27 | COMP | 2020-07-17 | COMP | 2020-07-24 | COMP | 2020-08-17 | COMP | Rule 16 | 138 | 42 | 7 | 80 | 6 | 17 | 285
16908 | 2019-07-02 | 2020-01-23 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-15 | COMP | 2020-07-07 | COMP | 2020-07-22 | COMP | 2020-08-05 | COMP | Rule 15/16 | 140 | 72 | 10 | 37 | 12 | 11 | 277
16922 | 2019-07-02 | 2020-01-23 | 2020-05-27 | 2020-05-27 | COMP | 2020-10-21 | COMP | 2022-01-30 | REQD | 2022-01-30 | REQD | 2020-11-06 | COMP | Rule 16 | 140 | 88 | 105 |  |  |  | 343
17151 | 2019-07-02 | 2020-02-03 | 2020-09-06 | 2020-09-06 | COMP | 2020-10-26 | COMP | 2023-11-13 | CANC | 2023-11-13 | CANC | 2021-01-11 | COMP | Rule 16 | 147 | 153 | 35 |  |  |  | 384
17626 | 2019-07-02 | 2020-02-22 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-17 | COMP | 2020-10-14 | COMP | 2020-11-04 | COMP | 2020-11-30 | COMP | Rule 16 | 160 | 89 | 15 | 63 | 16 | 16 | 356
17820 | 2019-07-02 | 2020-02-28 | 2020-07-10 | 2020-08-02 | COMP | 2020-08-28 | COMP | 2020-09-29 | COMP | 2021-05-11 | COMP | 2021-06-08 | COMP | Rule 16 | 165 | 95 | 20 | 22 | 154 | 20 | 487
18964 | 2019-07-02 | 2020-04-14 | 2020-11-21 | 2020-11-21 | COMP | 2021-03-24 | COMP | 2021-03-30 | COMP | 2022-08-24 | COMP | 2023-02-02 | COMP | Rule 16 | 197 | 156 | 82 | 5 | 356 | 110 | 902
19322 | 2019-07-02 | 2020-04-30 | 2020-09-29 | 2020-09-29 | COMP | 2021-01-11 | COMP | 2021-04-12 | COMP | 2021-02-19 | COMP | 2021-05-18 | COMP | Rule 16 | 209 | 107 | 70 | 64 | 0 | 27 | 473
24830 | 2019-07-02 | 2021-01-14 | 2021-02-02 | 2021-02-02 | COMP | 2021-02-09 | COMP | 2021-03-22 | COMP | 2021-04-27 | COMP | 2021-11-30 | COMP | Rule 16 | 387 | 13 | 6 | 29 | 27 | 150 | 607
27833 | 2019-07-02 | 2021-05-11 | 2021-05-28 | 2021-05-28 | COMP | 2021-06-22 | COMP | 2021-07-09 | NOTN | 2021-07-10 | COMP | 2021-07-14 | COMP | Rule 16 | 468 | 14 | 17 |  |  |  | 512
13165 | 2019-07-03 | 2019-07-15 | 2021-08-12 | 2021-08-12 | COMP | 2021-08-24 | COMP | 2021-10-26 | COMP | 2021-11-10 | COMP | 2021-12-07 | COMP | Rule 15/16 | 8 | 525 | 9 | 45 | 12 | 17 | 611
13246 | 2019-07-03 | 2019-07-17 | 2019-09-17 | 2019-09-17 | COMP | 2019-09-20 | NOTN | 2019-09-20 | COMP | 2019-09-20 | COMP | 2019-10-22 | COMP | Rule 16 | 10 | 44 |  | 4 | 1 | 23 | 78
13250 | 2019-07-03 | 2019-07-18 | 2019-10-11 | 2019-10-11 | COMP | 2020-01-27 | COMP | 2020-02-12 | COMP | 2020-02-07 | COMP | 2020-03-09 | COMP | Rule 15/16 | 11 | 61 | 71 | 13 | 0 | 18 | 170
13255 | 2019-07-03 | 2019-07-17 | 2019-12-05 | 2019-12-05 | COMP | 2020-01-28 | COMP | 2020-08-06 | COMP | 2020-10-15 | COMP | 2020-11-23 | COMP | Rule 16 | 10 | 98 | 36 | 136 | 50 | 27 | 352
13300 | 2019-07-03 | 2019-07-18 | 2019-08-10 | 2019-08-10 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2020-12-01 | COMP | 2021-01-06 | COMP | Rule 16 | 11 | 17 | 14 | 1 | 316 | 25 | 380
13461 | 2019-07-03 | 2019-07-26 | 2019-10-19 | 2019-10-19 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-10-25 | COMP | 2019-12-16 | COMP | Rule 16 | 17 | 60 | 4 | 1 | 2 | 34 | 114
13544 | 2019-07-03 | 2019-07-30 | 2019-11-23 | 2019-11-23 | COMP | 2019-12-20 | COMP | 2020-02-03 | COMP | 2020-02-05 | COMP | 2020-03-12 | COMP | Rule 16 | 19 | 82 | 18 | 29 | 3 | 26 | 173
13808 | 2019-07-03 | 2019-08-12 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-03-04 | COMP | 2020-03-27 | COMP | Rule 16 | 28 | 101 | 29 | 1 | 12 | 18 | 184
13823 | 2019-07-03 | 2019-08-12 | 2019-09-26 | 2019-09-26 | COMP | 2019-11-08 | NOTN | 2019-11-08 | COMP | 2019-11-08 | COMP | 2019-12-15 | COMP | Other | 28 | 33 |  | 32 | 1 | 23 | 113
13919 | 2019-07-03 | 2019-08-15 | 2019-10-15 | 2019-10-17 | COMP | 2019-11-07 | COMP | 2019-11-07 | COMP | 2019-11-15 | COMP | 2019-11-21 | COMP | Rule 16 | 31 | 43 | 16 | 1 | 6 | 5 | 99
13929 | 2019-07-03 | 2019-08-16 | 2019-11-26 | 2019-11-26 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-03-25 | COMP | 2020-04-02 | COMP | Rule 16 | 32 | 71 | 34 | 1 | 48 | 7 | 188
14291 | 2019-07-03 | 2019-09-03 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-03-30 | COMP | 2020-04-28 | COMP | Rule 16 | 43 | 106 | 15 | 1 | 24 | 22 | 206
14758 | 2019-07-03 | 2019-09-25 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2019-12-18 | COMP | 2020-01-25 | COMP | Rule 16 | 59 | 46 | 8 | 1 | 6 | 25 | 140
15127 | 2019-07-03 | 2019-10-14 | 2019-12-18 | 2019-12-18 | COMP | 2019-12-18 | NOTN | 2019-12-18 | COMP | 2019-12-30 | COMP | 2020-02-02 | COMP | Other | 72 | 45 |  | 1 | 8 | 23 | 145
15461 | 2019-07-03 | 2019-11-04 | 2019-12-06 | 2020-01-31 | COMP | 2020-08-27 | COMP | 2020-08-27 | COMP | 2020-11-12 | COMP | 2021-01-21 | COMP | Rule 16 | 87 | 22 | 148 | 1 | 54 | 46 | 390
15469 | 2019-07-03 | 2019-11-04 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-17 | COMP | 2020-07-24 | COMP | 2020-09-01 | COMP | 2020-10-09 | COMP | Rule 16 | 87 | 164 | 14 | 6 | 28 | 28 | 322
15486 | 2019-07-03 | 2019-11-04 | 2019-12-28 | 2019-12-28 | COMP | 2020-04-09 | COMP | 2020-04-09 | COMP | 2020-05-01 | COMP | 2020-06-10 | COMP | Rule 16 | 87 | 36 | 71 | 1 | 17 | 28 | 236
17255 | 2019-07-03 | 2020-02-06 | 2020-04-02 | 2020-04-02 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2021-01-11 | COMP | 2023-10-29 | COMP | Rule 15/16 | 149 | 40 | 46 | 1 | 151 | 705 | 1087
17320 | 2019-07-03 | 2020-02-10 | 2020-03-28 | 2020-04-01 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-17 | COMP | 2020-11-04 | COMP | Rule 16 | 151 | 34 | 52 | 1 | 26 | 78 | 340
20838 | 2019-07-03 | 2020-07-08 | 2020-08-20 | 2020-08-20 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2020-11-05 | COMP | 2020-11-24 | COMP | Rule 16 | 256 | 32 | 45 | 1 | 11 | 13 | 353
13456 | 2019-07-04 | 2019-07-25 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2019-12-27 | COMP | 2020-02-29 | COMP | Rule 16 | 15 | 68 | 19 | 1 | 22 | 43 | 163
13086 | 2019-07-05 | 2019-07-10 | 2019-10-10 | 2019-10-10 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-01-07 | COMP | 2020-03-12 | COMP | Rule 15/16 | 4 | 66 | 54 | 1 | 6 | 46 | 172
13358 | 2019-07-05 | 2019-07-23 | 2019-10-02 | 2019-10-02 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2020-04-07 | COMP | 2020-04-24 | COMP | Rule 16 | 13 | 51 | 118 | 1 | 11 | 14 | 203
13569 | 2019-07-05 | 2019-07-31 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2019-10-16 | COMP | 2020-01-10 | COMP | Rule 16 | 19 | 47 | 7 | 1 | 2 | 58 | 130
13859 | 2019-07-05 | 2019-08-13 | 2019-11-27 | 2019-11-27 | COMP | 2019-12-23 | COMP | 2020-03-06 | COMP | 2020-02-03 | COMP | 2020-04-15 | COMP | Rule 16 | 28 | 75 | 17 | 51 | 0 | 29 | 196
13897 | 2019-07-05 | 2019-08-15 | 2020-01-06 | 2020-01-06 | COMP | 2020-02-26 | COMP | 2020-03-04 | COMP | 2020-03-24 | COMP | 2020-06-16 | COMP | Rule 16 | 30 | 97 | 36 | 6 | 15 | 60 | 239
13933 | 2019-07-05 | 2019-08-16 | 2019-09-26 | 2019-09-26 | COMP | 2020-01-21 | NOTN | 2020-01-21 | COMP | 2019-12-23 | COMP | 2020-04-28 | COMP | Rule 16 | 31 | 29 |  | 78 | 0 | 70 | 205
14640 | 2019-07-05 | 2019-09-20 | 2020-02-28 | 2020-02-28 | COMP | 2020-06-22 | COMP | 2020-07-08 | COMP | 2020-07-09 | COMP | 2020-11-17 | COMP | Rule 16 | 55 | 109 | 81 | 13 | 2 | 92 | 347
14695 | 2019-07-05 | 2019-09-24 | 2019-11-13 | 2020-07-06 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2022-08-29 | COMP | 2022-10-10 | COMP | Rule 16 | 57 | 36 | 101 | 1 | 442 | 30 | 823
14851 | 2019-07-05 | 2019-09-30 | 2019-11-14 | 2019-11-14 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-17 | COMP | Rule 16 | 61 | 33 | 72 | 1 | 1 | 12 | 175
15096 | 2019-07-05 | 2019-10-12 | 2019-12-30 | 2019-12-30 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2021-02-27 | INPR | 2020-01-28 | COMP | Rule 16 | 70 | 52 | 13 | 1 |  |  | 141
15557 | 2019-07-05 | 2019-11-06 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-27 | COMP | 2020-04-17 | COMP | 2020-10-13 | COMP | 2020-11-04 | COMP | Rule 16 | 88 | 82 | 15 | 16 | 126 | 17 | 339
13155 | 2019-07-06 | 2019-07-12 | 2020-04-29 | 2020-04-29 | COMP | 2020-07-21 | COMP | 2021-11-15 | COMP | 2021-10-12 | COMP | 2021-12-03 | COMP | Rule 16 | 5 | 201 | 59 | 333 | 0 | 13 | 607
13389 | 2019-07-06 | 2019-07-24 | 2019-10-30 | 2019-10-30 | COMP | 2020-02-05 | COMP | 2020-02-13 | COMP | 2020-04-16 | COMP | 2021-01-11 | COMP | Other | 13 | 70 | 65 | 7 | 45 | 186 | 381
14049 | 2019-07-06 | 2019-08-22 | 2019-09-27 | 2019-09-27 | COMP | 2020-01-02 | COMP | 2020-03-10 | COMP | 2020-11-24 | COMP | 2020-12-05 | COMP | Rule 16 | 34 | 26 | 65 | 47 | 183 | 7 | 357
14097 | 2019-07-06 | 2019-08-26 | 2019-10-20 | 2019-10-20 | COMP | 2019-12-03 | COMP | 2019-12-03 | COMP | 2019-11-24 | COMP | 2020-01-10 | COMP | Rule 16 | 36 | 39 | 29 | 1 | 0 | 27 | 129
15106 | 2019-07-06 | 2019-10-14 | 2019-11-25 | 2019-11-25 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-09-03 | COMP | 2020-10-12 | COMP | Rule 16 | 70 | 30 | 133 | 1 | 65 | 27 | 321
13091 | 2019-07-07 | 2019-07-10 | 2019-08-14 | 2019-08-14 | COMP | 2019-09-20 | COMP | 2020-01-02 | COMP | 2019-12-30 | COMP | 2020-02-16 | COMP | Rule 16 | 3 | 26 | 27 | 70 | 0 | 31 | 153
13066 | 2019-07-08 | 2019-07-08 | 2019-07-22 | 2019-07-23 | COMP | 2019-07-24 | COMP | 2019-07-24 | COMP | 2019-12-29 | INPR | 2019-08-22 | COMP | Rule 16 | 1 | 11 | 2 | 1 |  |  | 34
13180 | 2019-07-08 | 2019-07-15 | 2019-09-17 | 2019-09-17 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-11-26 | COMP | 2019-12-09 | COMP | Rule 16 | 6 | 46 | 45 | 1 | 6 | 8 | 107
13378 | 2019-07-08 | 2019-07-23 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-12 | COMP | 2019-11-07 | COMP | 2019-11-08 | COMP | 2019-12-03 | COMP | Rule 16 | 12 | 34 | 4 | 41 | 2 | 15 | 103
13541 | 2019-07-08 | 2019-07-30 | 2019-10-16 | 2019-10-16 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-12-02 | COMP | 2019-12-09 | COMP | Rule 16 | 17 | 56 | 7 | 1 | 25 | 6 | 107
13556 | 2019-07-08 | 2019-07-30 | 2019-09-11 | 2019-09-11 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-10-22 | COMP | 2019-12-03 | COMP | Rule 16 | 17 | 31 | 30 | 1 | 1 | 28 | 103
13564 | 2019-07-08 | 2019-07-31 | 2019-12-28 | 2021-04-23 | COMP | 2021-08-13 | COMP | 2021-08-23 | COMP | 2022-12-05 | COMP | 2023-02-06 | COMP | Rule 16 | 18 | 103 | 79 | 7 | 323 | 43 | 901
13645 | 2019-07-08 | 2019-08-05 | 2019-10-06 | 2019-10-06 | COMP | 2019-11-22 | COMP | 2019-12-04 | COMP | 2019-12-23 | COMP | 2020-01-08 | COMP | Rule 16 | 21 | 44 | 34 | 7 | 14 | 11 | 127
13646 | 2019-07-08 | 2019-08-05 | 2019-11-08 | 2019-11-08 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2023-04-30 | INPR | 2020-06-12 | COMP | Rule 16 | 21 | 69 | 6 | 1 |  |  | 236
13691 | 2019-07-08 | 2019-08-06 | 2019-10-31 | 2020-04-28 | COMP | 2020-05-06 | COMP | 2020-02-19 | COMP | 2020-05-07 | COMP | 2020-07-21 | COMP | Rule 16 | 22 | 62 | 7 |  | 57 | 53 | 263
13696 | 2019-07-08 | 2019-08-06 | 2019-12-04 | 2020-09-01 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2020-11-13 | COMP | 2021-01-15 | COMP | Rule 16 | 22 | 83 | 7 | 1 | 46 | 42 | 385
14207 | 2019-07-08 | 2019-08-29 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-20 | COMP | 2019-12-16 | COMP | 2019-12-13 | COMP | 2020-01-21 | COMP | Rule 16 | 39 | 49 | 10 | 17 | 0 | 24 | 135
14246 | 2019-07-08 | 2019-08-30 | 2020-01-17 | 2020-01-17 | COMP | 2021-01-07 | COMP | 2022-07-03 | REQD | 2022-07-03 | REQD | 2022-07-03 | COMP | Rule 16 | 40 | 95 | 246 |  |  |  | 753
14426 | 2019-07-08 | 2019-09-10 | 2020-08-18 | 2020-08-18 | COMP | 2020-09-10 | COMP | 2020-11-19 | COMP | 2022-07-16 | INPR | 2021-05-21 | COMP | Rule 16 | 46 | 238 | 17 | 50 |  |  | 473
14504 | 2019-07-08 | 2019-09-12 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-31 | COMP | 2020-01-22 | COMP | 2020-05-12 | COMP | 2020-06-12 | COMP | Rule 16 | 48 | 55 | 21 | 15 | 79 | 23 | 236
14561 | 2019-07-08 | 2019-09-16 | 2020-01-15 | 2020-03-02 | COMP | 2020-03-10 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-06-17 | COMP | Rule 16 | 50 | 83 | 7 |  | 1 | 103 | 239
14882 | 2019-07-08 | 2019-10-02 | 2020-01-17 | 2020-09-19 | COMP | 2020-11-06 | COMP | 2021-01-07 | COMP | 2020-07-08 | COMP | 2021-01-15 | COMP | Rule 16 | 62 | 73 | 35 | 40 | 0 | 7 | 385
15984 | 2019-07-08 | 2019-12-04 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-23 | COMP | 2020-06-25 | COMP | 2022-01-30 | INPR | 2020-07-23 | COMP | Rule 16 | 104 | 119 | 21 | 3 |  |  | 265
16005 | 2019-07-08 | 2019-12-05 | 2020-03-26 | 2020-03-26 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2021-10-22 | COMP | 2022-02-22 | COMP | Rule 16 | 105 | 77 | 99 | 1 | 302 | 83 | 662
16112 | 2019-07-08 | 2019-12-11 | 2020-01-30 | 2020-01-30 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-06-12 | COMP | 2020-06-22 | COMP | Rule 16 | 109 | 34 | 26 | 1 | 70 | 7 | 242
16120 | 2019-07-08 | 2019-12-10 | 2020-01-22 | 2020-01-22 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-11-10 | COMP | 2020-11-30 | COMP | Rule 16 | 108 | 29 | 38 | 1 | 170 | 12 | 353
16205 | 2019-07-08 | 2019-12-13 | 2020-03-15 | 2020-03-15 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2021-10-22 | COMP | 2022-02-24 | COMP | Rule 16 | 111 | 62 | 107 | 1 | 302 | 85 | 664
16553 | 2019-07-08 | 2020-01-07 | 2020-01-25 | 2020-01-25 | COMP | 2020-02-06 | COMP | 2020-02-10 | INPR | 2022-06-18 | REQD | 2020-02-22 | COMP | Rule 16 | 126 | 13 | 9 |  |  |  | 157
16570 | 2019-07-08 | 2020-01-08 | 2020-02-01 | 2020-02-01 | COMP | 2020-03-20 | COMP | 2020-03-30 | COMP | 2020-04-17 | COMP | 2020-04-28 | COMP | Rule 16 | 127 | 17 | 34 | 7 | 15 | 8 | 204
18441 | 2019-07-08 | 2020-03-24 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-24 | COMP | 2020-08-18 | COMP | 2021-04-12 | COMP | 2021-06-03 | COMP | Rule 16 | 179 | 64 | 25 | 18 | 162 | 38 | 481
22528 | 2019-07-08 | 2020-09-28 | 2021-01-12 | 2021-01-12 | COMP | 2021-01-12 | NOTN | 2021-04-13 | COMP | 2021-01-12 | COMP | 2021-04-30 | COMP | Other | 311 | 72 |  | 64 | 0 | 14 | 458
4262 | 2019-07-09 | 2020-01-06 | 2020-05-01 | 2021-03-19 | COMP | 2021-05-07 | COMP | 2021-06-11 | COMP | 2021-06-09 | COMP | 2022-08-15 | COMP | Rule 15/16 | 124 | 83 | 36 | 25 | 0 | 297 | 782
13218 | 2019-07-09 | 2019-07-17 | 2019-08-14 | 2019-08-14 | COMP | 2019-08-26 | COMP | 2019-08-26 | COMP | 2019-10-07 | COMP | 2019-12-03 | COMP | Rule 16 | 7 | 21 | 9 | 1 | 30 | 39 | 102
13258 | 2019-07-09 | 2019-07-17 | 2019-08-07 | 2019-08-07 | COMP | 2019-09-09 | NOTN | 2019-09-09 | COMP | 2019-10-09 | COMP | 2019-12-23 | COMP | Other | 7 | 16 |  | 23 | 23 | 51 | 116
13324 | 2019-07-09 | 2019-07-19 | 2020-02-26 | 2020-02-26 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-07-09 | COMP | 2020-09-30 | COMP | Rule 16 | 9 | 151 | 95 | 1 | 2 | 59 | 312
13455 | 2019-07-09 | 2019-07-26 | 2019-08-20 | 2019-08-20 | COMP | 2019-08-23 | NOTN | 2019-08-23 | COMP | 2019-11-05 | COMP | 2019-12-10 | COMP | Other | 14 | 18 |  | 4 | 52 | 23 | 107
13478 | 2019-07-09 | 2019-07-26 | 2019-10-22 | 2019-10-22 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-08-20 | COMP | 2020-09-10 | COMP | Rule 16 | 14 | 62 | 29 | 1 | 182 | 15 | 298
13517 | 2019-07-09 | 2019-07-30 | 2019-11-13 | 2019-12-13 | COMP | 2020-01-13 | COMP | 2020-01-14 | COMP | 2020-01-30 | COMP | 2020-02-19 | COMP | Rule 16 | 16 | 75 | 20 | 2 | 12 | 14 | 154
13583 | 2019-07-09 | 2019-07-31 | 2019-12-14 | 2019-12-14 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-09-08 | COMP | 2020-10-21 | COMP | Rule 16 | 17 | 94 | 14 | 1 | 173 | 32 | 327
13672 | 2019-07-09 | 2019-08-05 | 2019-10-21 | 2019-10-21 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-08 | COMP | 2020-02-28 | COMP | Rule 15/16 | 20 | 55 | 52 | 1 | 23 | 14 | 161
13856 | 2019-07-09 | 2019-08-14 | 2019-09-24 | 2019-09-24 | COMP | 2019-09-25 | NOTN | 2019-09-25 | COMP | 2019-09-25 | NOTN | 2019-11-07 | COMP | Other | 27 | 29 |  | 2 |  |  | 87
13878 | 2019-07-09 | 2019-08-14 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-13 | COMP | 2019-11-18 | COMP | 2019-12-30 | COMP | 2020-02-18 | COMP | Rule 16 | 27 | 60 | 5 | 4 | 28 | 34 | 153
14028 | 2019-07-09 | 2019-08-22 | 2020-01-03 | 2020-01-03 | COMP | 2020-01-14 | COMP | 2020-04-28 | COMP | 2021-04-13 | COMP | 2021-06-11 | COMP | Rule 16 | 33 | 91 | 8 | 74 | 242 | 43 | 486
14092 | 2019-07-09 | 2019-08-26 | 2019-10-20 | 2019-10-20 | COMP | 2019-12-18 | COMP | 2019-12-24 | COMP | 2020-01-28 | COMP | 2020-02-21 | COMP | Rule 15/16 | 35 | 39 | 40 | 5 | 23 | 18 | 156
14118 | 2019-07-09 | 2019-08-26 | 2019-09-26 | 2019-09-26 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2020-01-08 | COMP | 2020-01-13 | COMP | Rule 16 | 35 | 23 | 42 | 1 | 29 | 4 | 129
14151 | 2019-07-09 | 2019-08-28 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-01 | NOTN | 2019-10-01 | COMP | 2019-10-02 | COMP | 2019-11-16 | COMP | Other | 37 | 24 |  | 1 | 2 | 32 | 92
14431 | 2019-07-09 | 2019-09-09 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-11-26 | COMP | 2019-12-25 | COMP | Rule 16 | 44 | 26 | 6 | 1 | 26 | 19 | 117
14456 | 2019-07-09 | 2019-09-11 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-27 | COMP | 2020-06-20 | COMP | 2020-11-17 | COMP | 2021-03-03 | COMP | Rule 16 | 46 | 30 | 26 | 141 | 105 | 71 | 415
14458 | 2019-07-09 | 2019-09-11 | 2019-10-12 | 2019-10-12 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-03-23 | COMP | 2020-04-15 | COMP | Rule 16 | 46 | 23 | 79 | 1 | 31 | 18 | 194
14484 | 2019-07-09 | 2019-09-12 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-16 | COMP | 2019-10-16 | COMP | 2019-11-26 | COMP | 2019-12-10 | COMP | Rule 16 | 47 | 17 | 8 | 1 | 29 | 9 | 107
14931 | 2019-07-09 | 2019-10-04 | 2020-01-06 | 2020-01-09 | COMP | 2020-04-23 | COMP | 2020-06-16 | COMP | 2020-01-16 | COMP | 2020-08-08 | COMP | Rule 16 | 63 | 62 | 74 | 38 | 0 | 39 | 275
14987 | 2019-07-09 | 2019-10-08 | 2020-07-24 | 2020-07-24 | COMP | 2020-10-07 | COMP | 2021-02-02 | COMP | 2021-04-29 | COMP | 2021-05-13 | COMP | Rule 16 | 65 | 201 | 53 | 79 | 62 | 11 | 466
15000 | 2019-07-09 | 2019-10-08 | 2020-02-29 | 2020-02-29 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-11 | COMP | 2020-07-25 | COMP | Rule 16 | 65 | 97 | 74 | 1 | 0 | 31 | 265
15415 | 2019-07-09 | 2019-10-31 | 2020-03-18 | 2020-03-18 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2021-05-24 | COMP | 2021-06-26 | COMP | Rule 15/16 | 82 | 93 | 66 | 1 | 235 | 24 | 496
15471 | 2019-07-09 | 2019-11-04 | 2020-06-13 | 2020-06-15 | COMP | 2020-08-12 | COMP | 2020-09-16 | COMP | 2022-07-16 | INPR | 2020-10-10 | COMP | Rule 16 | 84 | 152 | 43 | 25 |  |  | 319
15972 | 2019-07-09 | 2019-12-04 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-24 | COMP | 2020-07-10 | COMP | 2020-05-26 | COMP | 2020-08-12 | COMP | Rule 16 | 103 | 39 | 17 | 99 | 0 | 24 | 278
16027 | 2019-07-09 | 2019-12-06 | 2020-03-16 | 2020-03-16 | COMP | 2020-06-01 | COMP | 2020-06-09 | COMP | 2020-12-22 | COMP | 2020-09-04 | COMP | Other | 105 | 68 | 55 | 7 | 137 |  | 295
16183 | 2019-07-09 | 2019-12-13 | 2020-04-29 | 2020-04-29 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP | 2021-01-26 | COMP | 2021-07-20 | COMP | Rule 16 | 110 | 95 | 151 | 1 | 37 | 123 | 512
16199 | 2019-07-09 | 2019-12-14 | 2020-08-11 | 2020-08-11 | COMP | 2020-08-18 | COMP | 2020-09-15 | COMP | 2022-01-30 | INPR | 2020-11-16 | COMP | Rule 16 | 110 | 167 | 6 | 20 |  |  | 344
16202 | 2019-07-09 | 2019-12-13 | 2020-04-10 | 2020-04-10 | COMP | 2020-11-10 | COMP | 2020-11-10 | COMP | 2022-04-21 | COMP | 2022-05-25 | COMP | Rule 16 | 110 | 82 | 151 | 1 | 363 | 25 | 727
16375 | 2019-07-09 | 2019-12-23 | 2020-09-04 | 2020-12-18 | COMP | 2021-01-04 | COMP | 2021-07-16 | COMP | 2021-09-20 | COMP | 2021-10-20 | COMP | Rule 15/16 | 116 | 180 | 10 | 136 | 46 | 23 | 577
17139 | 2019-07-09 | 2020-01-31 | 2020-05-14 | 2020-05-14 | COMP | 2020-09-02 | COMP | 2020-09-02 | COMP | 2020-10-12 | COMP | 2021-01-07 | COMP | Rule 16 | 142 | 74 | 79 | 1 | 28 | 59 | 378
17333 | 2019-07-09 | 2020-02-10 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-07-22 | COMP | Rule 16 | 148 | 65 | 23 | 1 | 1 | 30 | 263
17536 | 2019-07-09 | 2020-02-20 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-23 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2021-08-09 | COMP | Rule 16 | 155 | 81 | 8 | 20 | 1 | 266 | 526
17602 | 2019-07-09 | 2020-02-21 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-28 | COMP | 2020-07-08 | COMP | 2020-06-19 | COMP | 2020-08-18 | COMP | Rule 16 | 156 | 45 | 4 | 51 | 0 | 30 | 282
18342 | 2019-07-09 | 2020-03-19 | 2020-05-14 | 2020-05-14 | COMP | 2020-05-28 | COMP | 2020-06-19 | COMP | 2020-11-16 | COMP | 2021-01-12 | COMP | Rule 16 | 175 | 41 | 10 | 17 | 105 | 38 | 381
19684 | 2019-07-09 | 2020-05-18 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-10-07 | COMP | 2020-11-18 | COMP | Rule 16 | 217 | 24 | 21 | 1 | 58 | 30 | 346
24460 | 2019-07-09 | 2020-12-24 | 2021-05-06 | 2021-05-06 | COMP | 2021-05-14 | COMP | 2021-05-14 | COMP | 2021-05-18 | COMP | 2021-06-14 | COMP | Rule 16 | 370 | 92 | 7 | 1 | 3 | 19 | 487
13230 | 2019-07-10 | 2019-07-17 | 2020-01-02 | 2020-01-02 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-05-18 | COMP | 2020-06-11 | COMP | Rule 15/16 | 6 | 116 | 77 | 1 | 20 | 18 | 233
13264 | 2019-07-10 | 2019-07-17 | 2019-08-28 | 2019-08-28 | COMP | 2019-08-29 | COMP | 2019-08-29 | COMP | 2019-10-01 | COMP | 2019-10-08 | COMP | Rule 16 | 6 | 31 | 2 | 1 | 23 | 6 | 64
13303 | 2019-07-10 | 2019-07-19 | 2019-08-30 | 2019-08-30 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2020-12-16 | COMP | 2021-01-04 | COMP | Rule 16 | 8 | 31 | 273 | 1 | 54 | 12 | 374
13501 | 2019-07-10 | 2019-07-29 | 2019-10-03 | 2019-10-03 | COMP | 2019-11-12 | COMP | 2019-12-02 | COMP | 2019-11-12 | COMP | 2020-01-06 | COMP | Rule 16 | 14 | 48 | 28 | 13 | 0 | 24 | 123
13522 | 2019-07-10 | 2019-07-29 | 2019-09-28 | 2019-09-28 | COMP | 2019-11-13 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-01-23 | COMP | Rule 16 | 14 | 44 | 32 | 8 | 1 | 40 | 135
13593 | 2019-07-10 | 2019-08-01 | 2019-10-18 | 2019-10-18 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2020-07-28 | COMP | 2020-08-13 | COMP | Rule 16 | 17 | 56 | 17 | 1 | 179 | 13 | 278
13663 | 2019-07-10 | 2019-08-05 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2019-12-02 | COMP | Rule 16 | 19 | 47 | 3 | 1 | 1 | 34 | 100
13703 | 2019-07-10 | 2019-08-06 | 2019-09-07 | 2019-09-24 | COMP | 2019-11-04 | COMP | 2019-11-04 | COMP | 2020-02-19 | COMP | 2020-02-22 | COMP | Rule 16 | 20 | 23 | 30 | 1 | 71 | 3 | 155
13735 | 2019-07-10 | 2019-08-07 | 2019-09-14 | 2019-09-14 | COMP | 2019-12-02 | COMP | 2019-12-06 | COMP | 2020-01-24 | COMP | 2020-01-24 | COMP | Rule 16 | 21 | 27 | 53 | 5 | 33 | 1 | 136
13994 | 2019-07-10 | 2019-08-20 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-06-03 | COMP | 2020-06-17 | COMP | Rule 16 | 30 | 56 | 15 | 1 | 129 | 11 | 237
14085 | 2019-07-10 | 2019-08-23 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-15 | COMP | 2019-11-18 | COMP | 2019-11-21 | COMP | 2019-12-13 | COMP | Rule 16 | 33 | 27 | 11 | 24 | 4 | 15 | 109
14139 | 2019-07-10 | 2019-08-27 | 2019-10-15 | 2019-10-15 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-03-30 | COMP | 2020-04-23 | COMP | Rule 16 | 35 | 35 | 32 | 1 | 82 | 19 | 199
14252 | 2019-07-10 | 2019-08-30 | 2020-01-15 | 2020-06-04 | COMP | 2020-09-03 | COMP | 2020-09-04 | COMP | 2023-11-12 | INPR | 2021-03-08 | COMP | Rule 16 | 38 | 93 | 66 | 2 |  |  | 417
14335 | 2019-07-10 | 2019-09-05 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-05 | COMP | 2020-03-23 | COMP | 2023-09-02 | INPR | 2020-06-24 | COMP | Rule 16 | 41 | 103 | 22 | 13 |  |  | 242
14470 | 2019-07-10 | 2019-09-11 | 2020-01-27 | 2020-01-27 | COMP | 2020-03-30 | COMP | 2020-06-08 | COMP | 2020-06-12 | COMP | 2020-07-23 | COMP | Rule 16 | 45 | 93 | 45 | 50 | 5 | 30 | 263
14617 | 2019-07-10 | 2019-09-20 | 2019-11-27 | 2019-11-27 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-01-22 | COMP | 2020-01-30 | COMP | Rule 16 | 52 | 48 | 37 | 1 | 0 | 6 | 140
15084 | 2019-07-10 | 2019-10-11 | 2020-02-01 | 2020-06-29 | COMP | 2020-11-06 | COMP | 2021-01-07 | COMP | 2021-01-04 | COMP | 2021-02-22 | COMP | Rule 16 | 67 | 75 | 94 | 40 | 0 | 31 | 407
15300 | 2019-07-10 | 2019-10-25 | 2020-01-21 | 2020-09-11 | COMP | 2020-10-16 | COMP | 2020-10-20 | COMP | 2020-05-13 | COMP | 2020-11-11 | COMP | Rule 16 | 77 | 57 | 26 | 3 | 0 | 16 | 340
15703 | 2019-07-10 | 2019-11-18 | 2020-06-03 | 2020-06-03 | COMP | 2020-09-24 | COMP | 2021-03-31 | COMP | 2021-04-26 | COMP | 2022-05-26 | COMP | Rule 15/16 | 92 | 136 | 81 | 128 | 19 | 276 | 727
16669 | 2019-07-10 | 2020-01-10 | 2020-04-15 | 2020-04-15 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2021-02-02 | NOTN | 2021-03-12 | COMP | Rule 15/16 | 127 | 67 | 49 | 1 |  |  | 421
19993 | 2019-07-10 | 2020-06-01 | 2020-07-20 | 2020-09-22 | COMP | 2020-10-22 | COMP | 2021-02-16 | COMP | 2021-03-23 | COMP | 2021-04-09 | COMP | Rule 16 | 225 | 36 | 23 | 77 | 26 | 14 | 441
20899 | 2019-07-10 | 2020-07-13 | 2020-09-12 | 2020-09-12 | COMP | 2020-10-01 | COMP | 2020-10-20 | COMP | 2020-10-12 | COMP | 2020-11-07 | COMP | Rule 16 | 255 | 44 | 14 | 14 | 0 | 14 | 338
13143 | 2019-07-11 | 2019-07-11 | 2019-07-17 | 2019-07-17 | COMP | 2019-08-05 | COMP | 2019-08-29 | COMP | 2019-12-29 | INPR | 2019-09-06 | COMP | Rule 16 | 1 | 5 | 14 | 19 |  |  | 41
13144 | 2019-07-11 | 2019-07-11 | 2019-07-12 | 2019-07-12 | COMP | 2019-08-28 | COMP | 2019-08-28 | COMP | 2019-08-29 | COMP | 2019-09-24 | COMP | Rule 16 | 1 | 2 | 34 | 1 | 2 | 18 | 53
13279 | 2019-07-11 | 2019-07-18 | 2019-09-23 | 2019-09-23 | COMP | 2020-09-21 | COMP | 2020-05-21 | COMP | 2020-09-18 | COMP | 2020-11-05 | COMP | Rule 16 | 6 | 47 | 252 |  | 85 | 35 | 336
13307 | 2019-07-11 | 2019-07-19 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-18 | COMP | 2019-09-19 | COMP | 2019-09-16 | COMP | 2019-10-18 | COMP | Rule 15/16 | 7 | 33 | 11 | 2 | 0 | 22 | 71
13336 | 2019-07-11 | 2019-07-22 | 2020-03-31 | 2021-03-24 | COMP | 2021-06-02 | COMP | 2021-06-02 | COMP | 2021-12-29 | COMP | 2022-08-22 | COMP | Rule 15/16 | 8 | 174 | 50 | 1 | 146 | 164 | 785
13445 | 2019-07-11 | 2019-07-25 | 2019-09-23 | 2019-09-23 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-01-31 | COMP | 2020-02-18 | COMP | Rule 16 | 11 | 42 | 50 | 1 | 40 | 12 | 151
13708 | 2019-07-11 | 2019-08-07 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | 2019-11-14 | COMP | Rule 16 | 20 | 43 | 11 | 1 | 2 | 17 | 89
13723 | 2019-07-11 | 2019-08-07 | 2019-09-20 | 2019-10-31 | COMP | 2019-11-15 | COMP | 2019-12-30 | COMP | 2020-01-07 | COMP | 2020-01-08 | COMP | Rule 16 | 20 | 32 | 11 | 29 | 6 | 2 | 124
13787 | 2019-07-11 | 2019-08-09 | 2019-11-15 | 2020-07-24 | COMP | 2020-08-17 | COMP | 2020-09-30 | COMP | 2020-10-13 | COMP | 2020-11-02 | COMP | Rule 15/16 | 22 | 69 | 17 | 32 | 10 | 15 | 333
13835 | 2019-07-11 | 2019-08-12 | 2019-09-27 | 2019-09-27 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | Rule 16 | 23 | 34 | 12 | 1 | 18 | 1 | 84
14000 | 2019-07-11 | 2019-08-21 | 2019-10-29 | 2019-11-06 | COMP | 2019-10-29 | NOTN | 2019-11-06 | COMP | 2019-10-29 | COMP | 2020-01-15 | COMP | Other | 30 | 49 |  | 1 | 0 | 46 | 129
14966 | 2019-07-11 | 2019-10-08 | 2019-11-09 | 2019-11-09 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-01-28 | COMP | 2020-02-06 | COMP | Rule 16 | 63 | 24 | 26 | 1 | 26 | 8 | 144
15332 | 2019-07-11 | 2019-10-28 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-09 | COMP | 2019-12-09 | COMP | 2019-12-23 | COMP | 2020-02-05 | COMP | Rule 15/16 | 77 | 14 | 15 | 1 | 11 | 30 | 143
15793 | 2019-07-11 | 2019-11-20 | 2020-03-24 | 2020-03-24 | COMP | 2020-06-22 | COMP | 2020-06-23 | COMP | 2020-07-05 | COMP | 2020-09-02 | COMP | Rule 16 | 93 | 84 | 64 | 2 | 9 | 43 | 291
15968 | 2019-07-11 | 2019-12-03 | 2020-03-08 | 2020-06-09 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2023-12-30 | INPR | 2021-07-08 | COMP | Rule 15/16 | 100 | 65 | 21 | 1 |  |  | 502
16393 | 2019-07-11 | 2019-12-24 | 2020-04-02 | 2020-06-20 | COMP | 2020-07-13 | COMP | 2020-08-06 | COMP | 2020-08-24 | COMP | 2020-09-11 | COMP | Rule 16 | 115 | 69 | 16 | 19 | 13 | 14 | 297
16577 | 2019-07-11 | 2020-01-08 | 2020-02-06 | 2020-02-06 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-06-09 | COMP | 2020-06-24 | COMP | Rule 16 | 124 | 21 | 23 | 1 | 65 | 12 | 241
18489 | 2019-07-11 | 2020-03-26 | 2020-05-12 | 2020-10-14 | COMP | 2020-11-05 | COMP | 2020-11-05 | COMP | 2020-12-01 | COMP | 2021-01-13 | COMP | Rule 16 | 178 | 34 | 17 | 1 | 16 | 30 | 380
18595 | 2019-07-11 | 2020-03-30 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-29 | COMP | 2020-05-09 | COMP | 2020-05-28 | COMP | 2020-06-15 | COMP | Rule 16 | 180 | 11 | 13 | 8 | 13 | 13 | 234
19381 | 2019-07-11 | 2020-05-04 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-08 | COMP | 2020-07-31 | COMP | 2020-06-10 | COMP | 2020-09-16 | COMP | Rule 16 | 205 | 20 | 6 | 40 | 0 | 33 | 300
34808 | 2019-07-11 | 2022-03-02 | 2022-07-08 | 2022-07-08 | COMP | 2022-08-01 | COMP | 2022-12-20 | COMP | 2022-08-22 | COMP | 2022-12-20 | COMP | Rule 16 | 665 | 90 | 17 | 98 | 0 | 1 | 867
4209 | 2019-07-12 | 2019-07-22 | 2019-10-10 | 2019-10-10 | COMP | 2022-01-14 | COMP | 2022-03-21 | COMP | 2022-04-15 | COMP | 2022-05-23 | COMP | Rule 15/16 | 7 | 58 | 570 | 45 | 20 | 27 | 722
13280 | 2019-07-12 | 2019-07-18 | 2019-07-27 | 2019-07-27 | COMP | 2019-08-01 | COMP | 2019-08-01 | COMP | 2019-09-03 | COMP | 2019-09-10 | COMP | Rule 16 | 5 | 7 | 4 | 1 | 23 | 6 | 42
13297 | 2019-07-12 | 2019-07-19 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-30 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-04-10 | COMP | Rule 16 | 6 | 89 | 24 | 43 | 1 | 30 | 188
13626 | 2019-07-12 | 2019-08-02 | 2020-03-08 | 2020-03-08 | COMP | 2020-04-01 | COMP | 2020-05-22 | COMP | 2020-07-04 | COMP | 2020-09-18 | COMP | Rule 15/16 | 16 | 148 | 18 | 38 | 30 | 54 | 301
13689 | 2019-07-12 | 2019-08-05 | 2019-09-01 | 2019-09-01 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-09-18 | COMP | Rule 16 | 17 | 20 | 9 | 1 | 1 | 4 | 48
13720 | 2019-07-12 | 2019-08-08 | 2019-10-10 | 2019-10-10 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-11-14 | COMP | 2019-11-21 | COMP | Rule 16 | 20 | 45 | 11 | 1 | 15 | 6 | 93
13783 | 2019-07-12 | 2019-08-09 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-09 | COMP | 2019-12-31 | COMP | 2019-12-11 | COMP | 2020-01-24 | COMP | Rule 16 | 21 | 66 | 18 | 16 | 0 | 17 | 134
13800 | 2019-07-12 | 2019-08-12 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-22 | COMP | 2019-11-05 | COMP | 2019-11-26 | COMP | 2019-12-16 | COMP | Rule 16 | 22 | 40 | 12 | 11 | 15 | 13 | 108
13874 | 2019-07-12 | 2019-08-14 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-21 | COMP | 2019-11-21 | COMP | 2019-12-02 | COMP | 2019-12-31 | COMP | Rule 16 | 24 | 45 | 26 | 1 | 6 | 21 | 118
14063 | 2019-07-12 | 2019-08-23 | 2019-11-25 | 2019-11-25 | COMP | 2020-01-10 | COMP | 2020-02-18 | COMP | 2020-03-24 | COMP | 2020-03-26 | COMP | Rule 16 | 31 | 65 | 31 | 26 | 26 | 3 | 177
14103 | 2019-07-12 | 2019-08-27 | 2019-09-05 | 2019-09-05 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2020-02-05 | COMP | 2020-02-14 | COMP | Rule 16 | 33 | 7 | 8 | 1 | 97 | 8 | 149
14186 | 2019-07-12 | 2019-08-28 | 2019-10-08 | 2019-10-08 | COMP | 2019-10-30 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-06-27 | COMP | Rule 16 | 34 | 29 | 17 | 129 | 1 | 37 | 242
14307 | 2019-07-12 | 2019-09-03 | 2020-01-02 | 2020-01-02 | COMP | 2020-05-18 | COMP | 2020-05-20 | COMP | 2020-06-15 | COMP | 2020-07-02 | COMP | Rule 15/16 | 37 | 83 | 96 | 3 | 18 | 14 | 246
14467 | 2019-07-12 | 2019-09-10 | 2019-11-08 | 2019-11-08 | COMP | 2019-12-16 | COMP | 2020-04-02 | COMP | 2019-09-10 | COMP | 2020-06-16 | COMP | Rule 16 | 42 | 44 | 24 | 75 | 0 | 53 | 234
14636 | 2019-07-12 | 2019-09-20 | 2019-09-30 | 2019-09-30 | COMP | 2019-11-13 | COMP | 2019-10-17 | COMP | 2019-11-19 | COMP | 2019-11-22 | COMP | Rule 16 | 50 | 7 | 32 |  | 23 | 4 | 94
14763 | 2019-07-12 | 2019-09-27 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-04 | COMP | 2020-07-27 | COMP | 2020-09-10 | COMP | 2021-07-31 | COMP | Rule 16 | 55 | 80 | 8 | 123 | 33 | 223 | 517
14921 | 2019-07-12 | 2019-10-05 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-06 | COMP | 2020-05-31 | COMP | 2020-06-30 | COMP | 2020-09-01 | COMP | Rule 16 | 60 | 98 | 6 | 60 | 22 | 46 | 289
15236 | 2019-07-12 | 2019-10-21 | 2019-12-24 | 2020-03-31 | COMP | 2020-05-11 | COMP | 2020-09-11 | COMP | 2020-02-11 | COMP | 2020-08-13 | COMP | Rule 15/16 | 71 | 44 | 30 | 88 | 0 |  | 276
15482 | 2019-07-12 | 2019-11-04 | 2020-02-19 | 2021-04-06 | COMP | 2021-04-27 | COMP | 2020-07-15 | COMP | 2021-06-21 | COMP | 2021-09-14 | COMP | Other | 81 | 71 | 16 |  | 235 | 60 | 548
15547 | 2019-07-12 | 2019-11-06 | 2019-12-19 | 2020-01-10 | COMP | 2020-01-27 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-04-21 | COMP | Rule 16 | 83 | 29 | 11 | 60 | 1 | 2 | 195
16281 | 2019-07-12 | 2019-12-19 | 2020-01-22 | 2021-03-13 | COMP | 2021-03-19 | COMP | 2021-03-19 | COMP | 2021-10-19 | COMP | 2021-12-01 | COMP | Rule 16 | 111 | 22 | 5 | 1 | 150 | 29 | 601
17056 | 2019-07-12 | 2020-01-29 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-16 | COMP | 2020-09-23 | COMP | 2021-04-07 | COMP | 2021-04-28 | COMP | Rule 16 | 137 | 82 | 16 | 71 | 134 | 16 | 452
17286 | 2019-07-12 | 2020-02-07 | 2020-03-09 | 2020-03-09 | COMP | 2020-07-24 | NOTN | 2020-08-04 | COMP | 2020-03-09 | COMP | 2020-09-04 | COMP | Other | 144 | 21 |  | 106 | 0 | 24 | 292
19193 | 2019-07-12 | 2020-04-24 | 2020-12-15 | 2020-12-15 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2022-07-16 | INPR | 2021-03-18 | COMP | Rule 16 | 198 | 163 | 6 | 1 |  |  | 423
14147 | 2019-07-13 | 2019-08-27 | 2019-12-14 | 2019-12-14 | COMP | 2020-03-20 | COMP | 2020-03-25 | COMP | 2020-04-20 | COMP | 2020-06-04 | COMP | Rule 16 | 32 | 75 | 66 | 4 | 19 | 33 | 225
14575 | 2019-07-14 | 2019-09-17 | 2020-01-27 | 2020-01-27 | COMP | 2020-01-30 | COMP | 2020-02-24 | COMP | 2020-03-12 | COMP | 2020-06-11 | COMP | Rule 16 | 46 | 89 | 4 | 17 | 14 | 65 | 230
14850 | 2019-07-14 | 2019-09-30 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-04-27 | COMP | 2020-05-11 | COMP | Rule 16 | 55 | 34 | 29 | 1 | 82 | 11 | 208
13259 | 2019-07-15 | 2019-07-17 | 2019-08-05 | 2019-08-05 | COMP | 2019-08-21 | COMP | 2019-08-21 | COMP | 2020-05-19 | COMP | 2020-06-17 | COMP | Rule 16 | 3 | 14 | 13 | 1 | 187 | 21 | 234
13446 | 2019-07-15 | 2019-07-25 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-10-14 | COMP | 2019-11-12 | COMP | Rule 16 | 9 | 54 | 4 | 1 | 1 | 21 | 85
13498 | 2019-07-15 | 2019-07-29 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-18 | COMP | 2020-01-08 | COMP | 2019-12-26 | COMP | 2020-01-14 | COMP | Rule 16 | 11 | 95 | 5 | 14 | 0 | 5 | 126
13570 | 2019-07-15 | 2019-07-31 | 2019-09-10 | 2019-09-10 | COMP | 2019-09-16 | COMP | 2019-09-16 | COMP | 2019-10-21 | COMP | 2019-11-05 | COMP | Rule 16 | 13 | 29 | 5 | 1 | 26 | 12 | 81
13631 | 2019-07-15 | 2019-08-02 | 2019-11-13 | 2019-11-13 | COMP | 2019-12-04 | COMP | 2020-01-02 | COMP | 2019-12-13 | COMP | 2020-02-05 | COMP | Rule 16 | 15 | 72 | 14 | 20 | 0 | 24 | 141
13688 | 2019-07-15 | 2019-08-06 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-10-10 | COMP | 2019-12-04 | COMP | Rule 16 | 17 | 31 | 17 | 1 | 1 | 37 | 99
13725 | 2019-07-15 | 2019-08-07 | 2019-12-08 | 2019-12-08 | COMP | 2019-12-30 | COMP | 2020-01-10 | COMP | 2020-07-20 | COMP | 2020-08-25 | COMP | Other | 18 | 84 | 15 | 9 | 134 | 27 | 283
13795 | 2019-07-15 | 2019-08-10 | 2019-11-18 | 2019-11-18 | COMP | 2020-03-10 | COMP | 2020-04-16 | COMP | 2020-06-02 | COMP | 2020-07-07 | COMP | Rule 16 | 20 | 69 | 76 | 28 | 33 | 26 | 248
13796 | 2019-07-15 | 2019-08-10 | 2019-10-24 | 2019-11-04 | COMP | 2019-11-07 | COMP | 2019-11-11 | COMP | 2020-02-04 | COMP | 2020-02-27 | COMP | Rule 16 | 20 | 53 | 4 | 2 | 56 | 17 | 156
13884 | 2019-07-15 | 2019-08-14 | 2019-09-30 | 2019-09-30 | COMP | 2019-09-26 | NOTN | 2019-10-29 | COMP | 2019-10-10 | COMP | 2019-12-06 | COMP | Rule 16 | 23 | 33 |  | 22 | 0 | 26 | 101
13977 | 2019-07-15 | 2019-08-19 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-27 | COMP | 2020-05-08 | COMP | 2020-04-24 | COMP | 2020-06-05 | COMP | Rule 15/16 | 26 | 54 | 18 | 112 | 0 | 20 | 226
14011 | 2019-07-15 | 2019-08-21 | 2020-02-26 | 2020-02-26 | COMP | 2020-09-01 | COMP | 2020-11-05 | COMP | 2020-12-08 | COMP | 2020-12-16 | COMP | Rule 15/16 | 28 | 128 | 134 | 47 | 21 | 7 | 360
14130 | 2019-07-15 | 2019-08-26 | 2019-10-11 | 2019-10-11 | COMP | 2020-06-09 | COMP | 2020-07-29 | COMP | 2020-07-09 | COMP | 2020-08-25 | COMP | Rule 16 | 31 | 34 | 165 | 37 | 0 | 20 | 283
14608 | 2019-07-15 | 2019-09-18 | 2019-12-05 | 2019-12-05 | COMP | 2020-01-03 | COMP | 2020-01-03 | INPR | 2021-04-24 | REQD | 2020-04-10 | COMP | Rule 16 | 47 | 54 | 20 |  |  |  | 187
14645 | 2019-07-15 | 2019-09-21 | 2020-01-06 | 2020-01-06 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-05-19 | COMP | 2020-06-03 | COMP | Rule 16 | 49 | 71 | 87 | 1 | 9 | 11 | 224
14963 | 2019-07-15 | 2019-10-07 | 2020-02-13 | 2020-02-13 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-09-10 | COMP | 2020-11-17 | COMP | Rule 16 | 60 | 88 | 27 | 1 | 122 | 48 | 341
14969 | 2019-07-15 | 2019-10-07 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-25 | COMP | 2020-03-26 | COMP | 2020-05-05 | COMP | 2020-06-10 | COMP | Rule 16 | 60 | 91 | 26 | 2 | 29 | 26 | 229
15021 | 2019-07-15 | 2019-10-09 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-21 | COMP | 2020-04-07 | COMP | 2020-02-25 | COMP | 2020-06-07 | COMP | Rule 16 | 62 | 86 | 6 | 33 | 0 | 43 | 226
15040 | 2019-07-15 | 2019-10-10 | 2020-02-12 | 2020-02-28 | COMP | 2020-04-01 | COMP | 2020-05-01 | COMP | 2020-05-05 | COMP | 2020-06-30 | COMP | Rule 16 | 63 | 84 | 24 | 23 | 3 | 40 | 243
15922 | 2019-07-15 | 2019-12-02 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-28 | COMP | 2020-05-22 | COMP | 2021-10-23 | INPR | 2020-08-14 | COMP | Rule 16 | 97 | 90 | 14 | 19 |  |  | 276
16227 | 2019-07-15 | 2019-12-16 | 2020-01-29 | 2020-01-29 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-03-05 | COMP | 2020-03-16 | COMP | Rule 16 | 107 | 30 | 6 | 1 | 21 | 8 | 168
16960 | 2019-07-15 | 2020-01-25 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-26 | COMP | 2020-11-06 | COMP | 2021-02-03 | COMP | 2021-02-19 | COMP | Rule 16 | 133 | 98 | 11 | 95 | 58 | 12 | 403
17315 | 2019-07-15 | 2020-02-10 | 2020-03-14 | 2020-03-14 | COMP | 2020-04-03 | COMP | 2020-04-03 | COMP | 2020-04-03 | COMP | 2020-06-22 | COMP | Rule 16 | 144 | 24 | 15 | 1 | 1 | 56 | 237
17597 | 2019-07-15 | 2020-02-20 | 2020-07-01 | 2020-07-01 | COMP | 2020-10-26 | COMP | 2020-11-11 | COMP |  | INPR | 2020-11-26 | COMP | Rule 16 | 151 | 94 | 83 | 12 |  |  | 347
19399 | 2019-07-15 | 2020-05-04 | 2021-02-10 | 2021-02-10 | COMP | 2021-03-04 | COMP | 2021-08-03 | COMP | 2021-08-24 | COMP | 2021-09-22 | COMP | Rule 15 | 203 | 195 | 16 | 107 | 16 | 21 | 553
21742 | 2019-07-15 | 2020-08-24 | 2020-12-17 | 2020-12-17 | COMP | 2020-12-29 | COMP | 2021-01-12 | COMP | 2021-02-19 | COMP | 2021-03-03 | COMP | Rule 16 | 282 | 80 | 8 | 10 | 27 | 9 | 411
27382 | 2019-07-15 | 2021-04-26 | 2021-10-20 | 2021-10-20 | COMP | 2021-11-16 | COMP | 2022-01-10 | COMP | 2022-09-14 | COMP | 2022-12-22 | COMP | Rule 16 | 449 | 125 | 19 | 38 | 172 | 69 | 867
13339 | 2019-07-16 | 2019-07-22 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-01-16 | COMP | 2020-02-07 | COMP | Rule 16 | 5 | 83 | 22 | 1 | 19 | 16 | 142
13419 | 2019-07-16 | 2019-07-24 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-13 | COMP | 2019-11-20 | COMP | 2019-12-03 | COMP | 2019-11-29 | COMP | Rule 16 | 7 | 75 | 5 | 6 | 8 |  | 95
13632 | 2019-07-16 | 2019-08-02 | 2019-12-08 | 2019-12-08 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-03-23 | COMP | 2020-03-24 | COMP | Rule 16 | 14 | 87 | 6 | 1 | 67 | 2 | 173
13811 | 2019-07-16 | 2019-08-12 | 2019-08-29 | 2019-08-29 | COMP | 2019-09-09 | NOTN | 2019-09-18 | COMP | 2019-10-14 | COMP | 2019-11-15 | COMP | Other | 20 | 14 |  | 14 | 19 | 24 | 87
13992 | 2019-07-16 | 2019-08-20 | 2019-10-20 | 2019-10-20 | COMP | 2019-10-24 | COMP | 2019-11-19 | COMP | 2019-10-23 | COMP | 2019-12-10 | COMP | Rule 16 | 26 | 43 | 4 | 18 | 0 | 14 | 102
14036 | 2019-07-16 | 2019-08-21 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-21 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-03-17 | COMP | Rule 15/16 | 27 | 26 | 18 | 55 | 1 | 46 | 168
14112 | 2019-07-16 | 2019-08-26 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-08 | COMP | Rule 16 | 30 | 29 | 13 | 1 | 1 | 13 | 83
14194 | 2019-07-16 | 2019-08-29 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-27 | COMP | 2020-05-20 | COMP | Rule 16 | 33 | 40 | 13 | 1 | 31 | 101 | 214
14444 | 2019-07-16 | 2019-09-10 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-01-30 | COMP | 2020-02-06 | COMP | Rule 16 | 40 | 67 | 13 | 1 | 19 | 6 | 141
14538 | 2019-07-16 | 2019-09-16 | 2019-11-22 | 2019-11-22 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-07-24 | COMP | 2020-10-06 | COMP | Rule 16 | 44 | 49 | 96 | 1 | 74 | 52 | 311
14572 | 2019-07-16 | 2019-09-17 | 2020-01-03 | 2020-01-03 | COMP | 2020-01-17 | COMP | 2020-01-24 | COMP | 2020-02-25 | COMP | 2020-03-20 | COMP | Rule 16 | 45 | 74 | 11 | 5 | 22 | 19 | 171
14729 | 2019-07-16 | 2019-09-25 | 2019-11-16 | 2019-11-16 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-12-02 | COMP | 2019-12-26 | COMP | Rule 16 | 51 | 37 | 8 | 1 | 2 | 18 | 113
14730 | 2019-07-16 | 2019-09-25 | 2019-11-20 | 2019-11-20 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-11-21 | COMP | 2019-12-27 | COMP | Rule 16 | 51 | 40 | 6 | 1 | 0 | 20 | 114
15151 | 2019-07-16 | 2019-10-16 | 2020-02-25 | 2020-02-25 | COMP | 2020-02-27 | COMP | 2020-03-06 | COMP | 2020-06-02 | COMP | 2020-06-26 | COMP | Rule 16 | 66 | 88 | 3 | 7 | 62 | 19 | 240
15253 | 2019-07-16 | 2019-10-23 | 2019-12-08 | 2020-06-29 | COMP | 2020-07-24 | COMP | 2020-01-17 | COMP | 2020-07-24 | COMP | 2020-08-31 | COMP | Rule 16 | 71 | 30 | 20 |  | 133 | 27 | 286
15254 | 2019-07-16 | 2019-10-23 | 2020-02-25 | 2020-02-25 | COMP | 2020-05-04 | COMP | 2020-05-07 | COMP | 2020-05-04 | COMP | 2020-05-14 | COMP | Rule 16 | 71 | 83 | 50 | 4 | 0 | 6 | 210
15430 | 2019-07-16 | 2019-10-31 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2021-05-18 | COMP | 2021-07-03 | COMP | Rule 16 | 77 | 71 | 30 | 1 | 289 | 33 | 496
15504 | 2019-07-16 | 2019-11-05 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-12 | COMP | 2020-03-31 | COMP | 2020-10-25 | COMP | 2020-11-24 | COMP | Rule 16 | 80 | 58 | 8 | 34 | 147 | 21 | 345
15684 | 2019-07-16 | 2019-11-15 | 2020-03-24 | 2020-03-24 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-11-24 | COMP | 2020-12-01 | COMP | Rule 16 | 87 | 87 | 114 | 1 | 60 | 4 | 348
15726 | 2019-07-16 | 2019-11-19 | 2020-09-22 | 2020-09-22 | COMP | 2021-06-24 | COMP | 2021-10-22 | COMP | 2022-03-14 | COMP | 2022-05-18 | COMP | Rule 15/16 | 89 | 213 | 190 | 85 | 97 | 48 | 717
15769 | 2019-07-16 | 2019-11-20 | 2020-04-06 | 2020-04-06 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-10-05 | COMP | 2020-11-03 | COMP | Rule 16 | 90 | 93 | 35 | 1 | 95 | 22 | 331
15821 | 2019-07-16 | 2019-11-22 | 2020-06-03 | 2020-06-03 | COMP | 2020-09-24 | COMP | 2020-09-24 | COMP | 2021-10-15 | COMP | 2021-10-30 | COMP | Rule 15/16 | 92 | 132 | 81 | 1 | 267 | 11 | 579
15878 | 2019-07-16 | 2019-11-25 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-10 | COMP | 2020-08-13 | COMP | 2020-05-28 | COMP | 2020-09-18 | COMP | Rule 15/16 | 93 | 58 | 14 | 112 | 0 | 26 | 299
15942 | 2019-07-16 | 2019-12-02 | 2020-01-04 | 2020-01-04 | COMP | 2020-01-17 | COMP | 2020-02-05 | COMP | 2020-02-04 | COMP | 2020-04-28 | COMP | Rule 16 | 96 | 23 | 10 | 13 | 0 | 59 | 198
16159 | 2019-07-16 | 2019-12-12 | 2020-02-06 | 2020-03-12 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-07-09 | COMP | 2020-08-14 | COMP | Rule 16 | 104 | 38 | 61 | 1 | 25 | 27 | 275
16888 | 2019-07-16 | 2020-01-22 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2021-05-24 | COMP | 2021-06-16 | COMP | Rule 16 | 130 | 27 | 6 | 1 | 308 | 17 | 484
4218 | 2019-07-17 | 2019-08-03 | 2020-06-25 | 2021-01-11 | COMP | 2022-01-20 | COMP | 2022-02-03 | COMP | 2022-02-01 | COMP | 2022-02-24 | COMP | Rule 16 | 13 | 225 | 260 | 11 | 0 | 15 | 657
13328 | 2019-07-17 | 2019-07-21 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-22 | NOTN | 2019-11-22 | COMP | 2019-12-03 | COMP | 2020-01-10 | COMP | Other | 3 | 77 |  | 12 | 6 | 27 | 122
13491 | 2019-07-17 | 2019-07-27 | 2019-08-13 | 2019-08-13 | COMP | 2019-09-13 | COMP | 2019-09-13 | COMP | 2019-09-21 | COMP | 2019-10-18 | COMP | Rule 16 | 8 | 12 | 23 | 1 | 6 | 20 | 67
13690 | 2019-07-17 | 2019-08-06 | 2019-09-30 | 2019-09-30 | COMP | 2019-12-24 | COMP | 2020-05-19 | COMP | 2020-05-07 | COMP | 2020-05-20 | COMP | Rule 16 | 15 | 39 | 59 | 102 | 0 | 2 | 213
13741 | 2019-07-17 | 2019-08-07 | 2019-08-21 | 2019-08-21 | COMP | 2019-08-26 | COMP | 2019-08-26 | INPR | 2019-08-27 | COMP | 2019-09-16 | COMP | Rule 16 | 16 | 11 | 4 |  |  |  | 43
13957 | 2019-07-17 | 2019-08-19 | 2020-04-05 | 2020-04-05 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-06-03 | COMP | 2020-06-22 | COMP | Rule 16 | 24 | 157 | 7 | 1 | 36 | 14 | 235
14100 | 2019-07-17 | 2019-08-27 | 2019-10-02 | 2020-02-08 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-04-15 | COMP | 2020-04-24 | COMP | Rule 16 | 30 | 26 | 19 | 1 | 29 | 8 | 195
14184 | 2019-07-17 | 2019-08-28 | 2020-02-09 | 2020-02-09 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-17 | COMP | 2020-03-25 | COMP | Rule 16 | 31 | 111 | 7 | 1 | 20 | 7 | 173
14305 | 2019-07-17 | 2019-09-05 | 2019-12-14 | 2019-12-14 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2021-10-23 | INPR | 2020-06-13 | COMP | Rule 16 | 36 | 69 | 87 | 1 |  |  | 229
14325 | 2019-07-17 | 2019-09-04 | 2020-09-04 | 2021-12-21 | COMP | 2022-01-20 | COMP | 2022-02-01 | COMP | 2023-12-03 | INPR | 2022-10-06 | COMP | Rule 15/16 | 35 | 255 | 22 | 9 |  |  | 813
14805 | 2019-07-17 | 2019-09-28 | 2021-02-18 | 2021-02-18 | COMP | 2021-02-25 | NOTN | 2021-05-17 | COMP | 2021-05-18 | COMP | 2021-08-03 | COMP | Other | 52 | 348 |  | 63 | 2 | 54 | 516
15313 | 2019-07-17 | 2019-10-25 | 2020-03-18 | 2020-03-18 | COMP | 2020-03-31 | COMP | 2020-08-24 | COMP | 2020-08-19 | COMP | 2020-10-01 | COMP | Rule 16 | 72 | 97 | 10 | 104 | 0 | 28 | 307
15354 | 2019-07-17 | 2019-10-28 | 2020-04-26 | 2020-04-26 | COMP | 2021-01-06 | COMP | 2021-01-06 | COMP | 2021-01-07 | COMP | 2021-02-09 | COMP | Rule 16 | 73 | 123 | 176 | 1 | 2 | 23 | 394
15625 | 2019-07-17 | 2019-11-12 | 2020-01-09 | 2020-01-09 | COMP | 2020-05-28 | COMP | 2021-04-05 | COMP | 2021-04-05 | COMP | 2021-04-22 | COMP | Rule 15/16 | 83 | 39 | 98 | 215 | 1 | 14 | 445
15708 | 2019-07-17 | 2019-11-18 | 2020-03-23 | 2020-03-23 | COMP | 2020-03-27 | COMP | 2020-05-04 | COMP | 2020-06-22 | NOTN | 2020-06-30 | COMP | Rule 16 | 87 | 85 | 5 | 27 |  |  | 241
15812 | 2019-07-17 | 2019-11-21 | 2020-04-28 | 2020-04-28 | COMP | 2020-05-04 | COMP | 2020-05-29 | COMP | 2020-05-03 | COMP | 2020-10-31 | COMP | Rule 16 | 90 | 108 | 5 | 19 | 0 | 110 | 328
15841 | 2019-07-17 | 2019-11-24 | 2020-12-10 | 2020-12-10 | COMP | 2020-12-17 | COMP | 2021-03-05 | COMP | 2021-02-24 | COMP | 2021-03-14 | COMP | Rule 16 | 91 | 263 | 6 | 53 | 0 | 6 | 416
16289 | 2019-07-17 | 2019-12-19 | 2020-03-19 | 2020-03-19 | COMP | 2020-03-27 | COMP | 2020-08-17 | COMP | 2021-02-22 | COMP | 2021-04-14 | COMP | Rule 16 | 108 | 62 | 7 | 101 | 128 | 38 | 439
16431 | 2019-07-17 | 2019-12-30 | 2020-04-24 | 2020-04-24 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-09-14 | COMP | 2020-10-19 | COMP | Other | 114 | 82 | 91 | 1 | 10 | 26 | 319
16443 | 2019-07-17 | 2019-12-31 | 2020-07-17 | 2020-07-17 | COMP | 2020-09-04 | COMP | 2021-03-10 | COMP | 2021-03-06 | COMP | 2021-03-30 | COMP | Rule 15/16 | 115 | 140 | 36 | 126 | 0 | 15 | 428
16654 | 2019-07-17 | 2020-01-11 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-06 | COMP | 2020-10-08 | COMP | 2020-12-14 | COMP | 2021-02-04 | COMP | Rule 15/16 | 122 | 112 | 12 | 68 | 45 | 36 | 391
16789 | 2019-07-17 | 2020-01-16 | 2020-05-13 | 2020-05-13 | COMP | 2022-07-11 | COMP | 2023-10-17 | COMP | 2023-09-20 | COMP | 2023-11-27 | COMP | Rule 16 | 126 | 83 | 544 | 320 | 0 | 27 | 1096
17128 | 2019-07-17 | 2020-01-31 | 2020-04-09 | 2020-04-09 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-07-24 | COMP | 2020-08-18 | COMP | Rule 16 | 136 | 49 | 36 | 1 | 41 | 18 | 276
17408 | 2019-07-17 | 2020-02-12 | 2020-09-04 | 2020-09-04 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2022-01-10 | COMP | 2022-04-15 | COMP | Rule 16 | 144 | 146 | 74 | 1 | 265 | 68 | 693
18672 | 2019-07-17 | 2020-04-02 | 2020-04-28 | 2020-04-28 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-16 | COMP | 2020-07-30 | COMP | Rule 15/16 | 179 | 19 | 26 | 1 | 10 | 33 | 263
13694 | 2019-07-18 | 2019-08-06 | 2019-10-20 | 2019-10-20 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-06-30 | COMP | 2020-10-28 | COMP | Rule 16 | 14 | 53 | 22 | 1 | 153 | 86 | 325
13768 | 2019-07-18 | 2019-08-08 | 2020-01-10 | 2020-01-10 | COMP | 2020-03-30 | COMP | 2020-05-06 | COMP | 2020-10-29 | COMP | 2020-11-10 | COMP | Rule 15/16 | 16 | 106 | 55 | 28 | 125 | 9 | 334
13910 | 2019-07-18 | 2019-08-15 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-05-08 | COMP | 2020-06-08 | COMP | Rule 16 | 21 | 100 | 14 | 1 | 72 | 21 | 224
13950 | 2019-07-18 | 2019-08-19 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2020-01-14 | COMP | 2020-02-05 | COMP | Rule 16 | 23 | 30 | 10 | 1 | 63 | 16 | 138
13958 | 2019-07-18 | 2019-08-19 | 2019-10-28 | 2019-10-28 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-02-26 | COMP | Rule 16 | 23 | 50 | 66 | 1 | 1 | 16 | 152
14016 | 2019-07-18 | 2019-08-21 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-23 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2019-12-09 | COMP | Rule 15/16 | 25 | 42 | 4 | 19 | 1 | 13 | 99
14081 | 2019-07-18 | 2019-08-23 | 2019-10-10 | 2019-10-10 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-08-25 | COMP | 2020-09-17 | COMP | Rule 16 | 27 | 34 | 15 | 1 | 207 | 17 | 296
14480 | 2019-07-18 | 2019-09-11 | 2020-03-06 | 2020-03-06 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2021-05-26 | COMP | 2023-05-22 | COMP | Rule 16 | 39 | 121 | 65 | 1 | 246 | 500 | 967
14651 | 2019-07-18 | 2019-09-20 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-04-14 | COMP | 2020-05-27 | COMP | Rule 15/16 | 46 | 73 | 28 | 1 | 42 | 31 | 216
14716 | 2019-07-18 | 2019-09-24 | 2020-01-11 | 2020-05-13 | COMP | 2020-06-03 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-30 | COMP | Rule 15/16 | 48 | 74 | 15 | 8 | 1 | 35 | 262
14717 | 2019-07-18 | 2019-09-25 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-23 | COMP | 2019-11-21 | COMP | 2020-01-06 | COMP | 2020-01-23 | COMP | Rule 16 | 49 | 14 | 8 | 21 | 29 | 13 | 129
14744 | 2019-07-18 | 2019-09-25 | 2020-01-04 | 2020-01-04 | COMP | 2020-01-15 | COMP | 2020-01-15 | INPR | 2020-04-09 | COMP | 2020-04-17 | COMP | Rule 16 | 49 | 68 | 8 |  |  |  | 189
14905 | 2019-07-18 | 2019-10-02 | 2020-02-29 | 2020-02-29 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-08-21 | COMP | 2020-09-03 | COMP | Rule 15/16 | 54 | 101 | 28 | 1 | 97 | 10 | 287
15137 | 2019-07-18 | 2019-10-15 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-18 | COMP | 2019-12-04 | COMP | 2020-08-31 | COMP | 2020-11-09 | COMP | Rule 16 | 63 | 18 | 7 | 11 | 189 | 50 | 333
15432 | 2019-07-18 | 2019-10-31 | 2019-12-31 | 2020-04-30 | COMP | 2020-08-04 | COMP | 2020-09-14 | COMP | 2020-12-24 | COMP | 2020-10-01 | COMP | Rule 16 | 75 | 40 | 68 | 29 | 71 |  | 306
15962 | 2019-07-18 | 2019-12-03 | 2020-02-11 | 2020-02-11 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-08-13 | COMP | 2020-09-02 | COMP | Rule 16 | 95 | 48 | 21 | 1 | 111 | 15 | 286
16295 | 2019-07-18 | 2019-12-19 | 2020-03-24 | 2020-03-24 | COMP | 2020-11-02 | COMP | 2020-12-16 | COMP |  | INPR | 2021-03-21 | COMP | Rule 16 | 107 | 65 | 158 | 30 |  |  | 420
16778 | 2019-07-18 | 2020-01-15 | 2020-02-25 | 2020-02-25 | COMP | 2020-03-26 | COMP | 2020-04-01 | INPR | 2021-10-23 | REQD | 2020-05-22 | COMP | Rule 16 | 124 | 28 | 23 |  |  |  | 214
16924 | 2019-07-18 | 2020-01-23 | 2020-12-11 | 2020-12-11 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2022-04-16 | INPR | 2021-02-09 | COMP | Rule 16 | 129 | 226 | 8 | 1 |  |  | 393
17807 | 2019-07-18 | 2020-02-27 | 2020-06-12 | 2020-06-12 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2023-01-01 | COMP | 2023-04-25 | COMP | Rule 16 | 153 | 76 | 94 | 1 | 549 | 79 | 948
17835 | 2019-07-18 | 2020-02-29 | 2020-08-21 | 2020-10-21 | COMP | 2021-07-02 | COMP | 2021-07-28 | COMP | 2021-07-27 | COMP | 2021-08-06 | COMP | Rule 16 | 154 | 124 | 175 | 18 | 0 | 8 | 518
18008 | 2019-07-18 | 2020-03-09 | 2020-08-13 | 2020-08-13 | COMP | 2020-08-26 | COMP | 2020-09-20 | COMP | 2020-09-11 | COMP | 2020-10-19 | COMP | Rule 16 | 160 | 113 | 10 | 17 | 0 | 21 | 318
18211 | 2019-07-18 | 2020-03-16 | 2020-07-03 | 2020-07-03 | COMP | 2020-08-25 | COMP | 2020-12-31 | COMP | 2021-04-01 | COMP | 2021-04-29 | COMP | Rule 16 | 165 | 79 | 38 | 88 | 63 | 21 | 449
18655 | 2019-07-18 | 2020-04-02 | 2020-06-23 | 2021-02-25 | COMP | 2021-03-15 | NOTN | 2021-04-21 | COMP |  |  | 2021-06-28 | COMP | Other | 178 | 58 |  | 40 |  |  | 490
23921 | 2019-07-18 | 2020-12-02 | 2021-03-01 | 2022-04-18 | COMP | 2022-05-05 | COMP | 2022-06-24 | COMP | 2023-03-09 | COMP | 2023-08-19 | COMP | Rule 15/16 | 347 | 60 | 14 | 35 | 176 | 114 | 1028
13319 | 2019-07-19 | 2019-07-19 | 2019-08-30 | 2019-08-30 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2019-12-30 | COMP | 2020-01-24 | COMP | Rule 15/16 | 1 | 31 | 81 | 1 | 2 | 18 | 129
13532 | 2019-07-19 | 2019-07-30 | 2019-08-21 | 2019-08-21 | COMP | 2019-08-30 | COMP | 2019-09-13 | COMP | 2019-10-14 | COMP | 2019-10-25 | COMP | Rule 16 | 8 | 17 | 8 | 10 | 22 | 10 | 70
13592 | 2019-07-19 | 2019-08-01 | 2019-11-08 | 2019-11-08 | COMP | 2020-01-07 | COMP | 2020-07-13 | COMP | 2020-07-29 | COMP | 2020-11-07 | COMP | Rule 16 | 10 | 71 | 38 | 132 | 13 | 72 | 331
14064 | 2019-07-19 | 2019-08-23 | 2019-11-23 | 2019-11-23 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-06 | COMP | 2020-05-03 | COMP | Rule 15/16 | 26 | 64 | 68 | 1 | 2 | 41 | 198
14104 | 2019-07-19 | 2019-08-27 | 2019-09-26 | 2019-09-26 | COMP | 2019-12-16 | COMP | 2019-12-17 | COMP | 2019-12-16 | COMP | 2020-02-04 | COMP | Rule 15 | 28 | 22 | 55 | 2 | 0 | 33 | 136
14105 | 2019-07-19 | 2019-08-27 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-27 | COMP | 2019-09-27 | COMP | 2019-10-28 | COMP | 2019-10-31 | COMP | Rule 16 | 28 | 6 | 18 | 1 | 22 | 4 | 74
14114 | 2019-07-19 | 2019-08-26 | 2019-12-23 | 2019-12-23 | COMP | 2020-01-23 | COMP | 2020-09-17 | COMP | 2020-10-08 | COMP | 2020-12-08 | COMP | Rule 15/16 | 27 | 82 | 21 | 168 | 16 | 41 | 350
14156 | 2019-07-19 | 2019-08-28 | 2020-04-01 | 2020-04-01 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-08-23 | COMP | 2020-11-17 | COMP | Rule 15/16 | 29 | 148 | 104 | 1 | 0 | 59 | 337
14225 | 2019-07-19 | 2019-08-29 | 2019-11-21 | 2019-11-21 | COMP | 2019-12-02 | COMP | 2020-01-13 | COMP | 2020-01-13 | COMP | 2020-02-05 | COMP | Rule 16 | 30 | 59 | 6 | 29 | 1 | 17 | 137
14280 | 2019-07-19 | 2019-09-03 | 2020-02-05 | 2020-02-05 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-06-19 | COMP | 2020-09-01 | COMP | Rule 16 | 32 | 106 | 83 | 1 | 14 | 53 | 284
14413 | 2019-07-19 | 2019-09-09 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2019-12-02 | COMP | 2019-12-31 | COMP | Rule 16 | 36 | 14 | 18 | 1 | 28 | 21 | 113
14414 | 2019-07-19 | 2019-09-09 | 2020-09-18 | 2020-09-18 | COMP | 2021-02-22 | COMP | 2021-03-17 | COMP | 2022-06-18 | INPR | 2021-04-23 | COMP | Rule 15/16 | 36 | 261 | 105 | 18 |  |  | 444
14620 | 2019-07-19 | 2019-09-18 | 2020-10-22 | 2020-10-22 | COMP | 2021-03-10 | COMP | 2021-03-15 | COMP | 2021-03-23 | COMP | 2021-05-06 | COMP | Rule 15/16 | 43 | 278 | 93 | 4 | 7 | 33 | 453
14779 | 2019-07-19 | 2019-09-27 | 2020-01-15 | 2020-01-15 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-18 | COMP | 2020-07-09 | COMP | Rule 15/16 | 50 | 74 | 86 | 1 | 2 | 38 | 246
17026 | 2019-07-19 | 2020-01-28 | 2020-04-01 | 2020-04-01 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-08-27 | COMP | 2020-10-06 | COMP | Rule 16 | 131 | 46 | 98 | 1 | 9 | 28 | 308
17377 | 2019-07-19 | 2020-02-12 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-06-02 | COMP | 2020-06-25 | COMP | Rule 16 | 142 | 37 | 11 | 1 | 32 | 18 | 236
17845 | 2019-07-19 | 2020-03-02 | 2020-05-18 | 2020-05-18 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2021-01-21 | COMP | 2021-02-18 | COMP | Rule 16 | 154 | 56 | 3 | 1 | 169 | 20 | 398
17893 | 2019-07-19 | 2020-03-03 | 2020-04-28 | 2020-04-28 | COMP | 2020-06-03 | COMP | 2022-01-10 | COMP | 2022-03-10 | COMP | 2022-04-04 | COMP | Rule 15/16 | 155 | 41 | 26 | 405 | 42 | 18 | 682
17909 | 2019-07-19 | 2020-03-04 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-23 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-10-29 | COMP | Rule 16 | 156 | 24 | 14 | 107 | 1 | 28 | 325
14560 | 2019-07-20 | 2019-09-16 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2020-07-17 | COMP | 2020-08-05 | COMP | Rule 16 | 40 | 47 | 11 | 1 | 156 | 14 | 264
14868 | 2019-07-20 | 2019-10-01 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-30 | COMP | 2020-02-26 | COMP | 2020-02-24 | COMP | 2020-06-05 | COMP | Rule 16 | 51 | 71 | 12 | 19 | 0 | 72 | 221
14689 | 2019-07-21 | 2019-09-23 | 2020-04-21 | 2020-04-21 | COMP | 2020-07-14 | COMP | 2020-11-03 | COMP | 2020-11-16 | COMP | 2020-12-01 | COMP | Rule 16 | 45 | 145 | 60 | 80 | 9 | 10 | 344
14691 | 2019-07-21 | 2019-09-23 | 2020-04-23 | 2020-04-23 | COMP | 2020-07-14 | COMP | 2020-11-03 | COMP | 2020-11-16 | COMP | 2020-12-01 | COMP | Rule 16 | 45 | 147 | 58 | 80 | 9 | 10 | 344
14692 | 2019-07-21 | 2019-09-23 | 2020-04-21 | 2020-04-21 | COMP | 2020-07-14 | COMP | 2020-11-03 | COMP | 2020-10-22 | COMP | 2020-12-01 | COMP | Rule 15/16 | 45 | 145 | 60 | 80 | 0 | 18 | 344
14818 | 2019-07-21 | 2019-09-29 | 2020-07-10 | 2020-08-25 | COMP | 2021-02-17 | COMP | 2021-02-22 | COMP | 2021-06-27 | COMP | 2021-11-19 | COMP | Rule 15/16 | 49 | 197 | 119 | 4 | 89 | 102 | 589
16325 | 2019-07-21 | 2019-12-20 | 2020-05-09 | 2020-05-09 | COMP | 2020-05-18 | COMP | 2020-06-12 | COMP | 2020-10-07 | COMP | 2020-10-28 | COMP | Rule 16 | 106 | 97 | 6 | 19 | 83 | 16 | 323
17889 | 2019-07-21 | 2020-03-03 | 2020-04-02 | 2020-04-02 | COMP | 2020-05-12 | COMP | 2020-12-09 | COMP | 2021-03-23 | COMP | 2021-05-04 | COMP | Rule 16 | 154 | 23 | 29 | 147 | 71 | 31 | 450
17949 | 2019-07-21 | 2020-03-05 | 2020-11-04 | 2020-11-04 | COMP | 2020-11-13 | COMP | 2020-11-13 | COMP | 2022-03-20 | INPR | 2021-02-26 | COMP | Rule 16 | 156 | 173 | 7 | 1 |  |  | 403
13406 | 2019-07-22 | 2019-07-24 | 2020-01-08 | 2020-01-08 | COMP | 2020-03-31 | COMP | 2020-08-06 | COMP | 2020-04-22 | COMP | 2020-09-25 | COMP | Rule 16 | 3 | 115 | 58 | 92 | 0 | 36 | 300
13408 | 2019-07-22 | 2019-07-24 | 2019-11-01 | 2019-11-01 | COMP | 2020-02-24 | COMP | 2020-03-25 | COMP | 2020-04-06 | COMP | 2020-05-07 | COMP | Rule 16 | 3 | 72 | 75 | 23 | 9 | 24 | 201
13460 | 2019-07-22 | 2019-07-26 | 2019-09-01 | 2019-09-01 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-10-04 | COMP | 2019-10-17 | COMP | Rule 16 | 5 | 26 | 22 | 1 | 3 | 10 | 63
13507 | 2019-07-22 | 2019-07-29 | 2019-09-30 | 2019-09-30 | COMP | 2020-01-21 | COMP | 2020-02-12 | COMP | 2020-02-10 | COMP | 2020-03-23 | COMP | Rule 16 | 6 | 45 | 76 | 17 | 0 | 28 | 168
13568 | 2019-07-22 | 2019-07-31 | 2019-10-24 | 2019-10-31 | COMP | 2019-12-23 | COMP | 2020-01-14 | COMP | 2020-01-28 | COMP | 2020-07-21 | COMP | Rule 16 | 8 | 61 | 35 | 15 | 10 | 124 | 253
13606 | 2019-07-22 | 2019-08-01 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-28 | COMP | 2019-10-28 | COMP | 2019-08-01 | COMP | 2020-01-17 | COMP | Rule 16 | 9 | 39 | 24 | 1 | 0 | 55 | 124
13706 | 2019-07-22 | 2019-08-06 | 2019-08-26 | 2019-08-26 | COMP | 2019-08-29 | NOTN | 2019-08-29 | COMP | 2019-09-04 | COMP | 2019-09-26 | COMP | Rule 16 | 12 | 15 |  | 4 | 4 | 17 | 48
13742 | 2019-07-22 | 2019-08-07 | 2019-09-04 | 2019-09-04 | COMP | 2019-09-17 | COMP | 2019-09-18 | COMP | 2019-10-07 | COMP | 2019-10-03 | COMP | Rule 16 | 13 | 20 | 10 | 2 | 14 |  | 53
13826 | 2019-07-22 | 2019-08-12 | 2019-11-13 | 2019-11-13 | COMP | 2020-03-04 | COMP | 2020-11-13 | COMP | 2020-12-08 | COMP | 2021-01-14 | COMP | Rule 16 | 16 | 66 | 75 | 180 | 16 | 26 | 374
13838 | 2019-07-22 | 2019-08-13 | 2019-11-01 | 2019-11-01 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | 2020-02-03 | COMP | Rule 16 | 17 | 58 | 46 | 1 | 1 | 16 | 134
13841 | 2019-07-22 | 2019-08-13 | 2020-06-24 | 2020-07-09 | COMP | 2020-07-20 | COMP | 2020-11-18 | COMP | 2021-10-12 | COMP | 2021-10-17 | COMP | Rule 16 | 17 | 218 | 8 | 86 | 226 | 4 | 565
13903 | 2019-07-22 | 2019-08-15 | 2019-09-30 | 2019-09-30 | COMP | 2020-02-24 | NOTN | 2020-02-24 | COMP | 2020-02-24 | COMP | 2020-04-09 | COMP | Other | 19 | 32 |  | 99 | 1 | 34 | 181
14002 | 2019-07-22 | 2019-08-21 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-06-19 | COMP | 2020-07-25 | COMP | Rule 16 | 23 | 38 | 31 | 1 | 142 | 26 | 256
14084 | 2019-07-22 | 2019-08-23 | 2019-10-10 | 2019-10-10 | COMP | 2020-05-05 | COMP | 2020-06-27 | COMP | 2020-06-12 | COMP | 2020-07-24 | COMP | Rule 16 | 25 | 34 | 142 | 38 | 0 | 20 | 256
14095 | 2019-07-22 | 2019-08-26 | 2020-04-02 | 2020-04-02 | COMP | 2020-11-16 | COMP | 2020-11-16 | COMP | 2021-01-19 | COMP | 2021-03-16 | COMP | Rule 15/16 | 26 | 151 | 160 | 1 | 42 | 40 | 415
14101 | 2019-07-22 | 2019-08-27 | 2019-10-08 | 2019-10-08 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-18 | COMP | 2020-01-02 | COMP | Rule 16 | 27 | 30 | 26 | 1 | 4 | 30 | 113
14172 | 2019-07-22 | 2019-08-28 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-14 | COMP | 2019-11-08 | COMP | Rule 16 | 28 | 23 | 7 | 1 | 5 | 20 | 79
14217 | 2019-07-22 | 2019-08-29 | 2020-01-17 | 2020-01-17 | COMP | 2020-02-24 | COMP | 2020-02-25 | COMP | 2020-06-18 | COMP | 2020-07-22 | COMP | Rule 16 | 29 | 96 | 25 | 2 | 82 | 25 | 254
14223 | 2019-07-22 | 2019-08-29 | 2019-12-12 | 2020-01-29 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-03-24 | COMP | 2020-04-08 | COMP | Rule 16 | 29 | 72 | 37 | 1 | 3 | 12 | 180
14650 | 2019-07-22 | 2019-09-20 | 2020-01-13 | 2020-01-13 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-07-06 | COMP | Rule 16 | 44 | 77 | 79 | 1 | 1 | 45 | 242
14684 | 2019-07-22 | 2019-09-23 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-10-16 | COMP | 2020-12-11 | COMP | Rule 15/16 | 45 | 89 | 17 | 1 | 167 | 38 | 352
14888 | 2019-07-22 | 2019-10-02 | 2019-10-26 | 2019-10-26 | COMP | 2019-12-09 | COMP | 2019-12-10 | COMP | 2019-12-09 | COMP | 2020-01-06 | COMP | Rule 16 | 52 | 18 | 28 | 2 | 0 | 18 | 115
14939 | 2019-07-22 | 2019-10-04 | 2019-12-19 | 2022-02-22 | COMP | 2022-08-22 | COMP | 2020-02-18 | COMP |  |  | 2022-11-07 | COMP | Rule 15/16 | 54 | 52 | 127 |  |  |  | 832
15122 | 2019-07-22 | 2019-10-15 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-03 | COMP | 2020-07-17 | COMP | 2022-01-30 | INPR | 2020-08-26 | COMP | Rule 16 | 61 | 103 | 15 | 75 |  |  | 279
15382 | 2019-07-22 | 2019-10-29 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-25 | COMP | 2020-03-26 | COMP | 2020-04-09 | COMP | 2020-05-04 | COMP | Rule 15/16 | 71 | 78 | 23 | 2 | 11 | 18 | 198
16214 | 2019-07-22 | 2019-12-16 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-05 | COMP | 2020-03-24 | COMP | 2020-03-21 | COMP | 2020-05-06 | COMP | Rule 16 | 102 | 51 | 5 | 14 | 0 | 32 | 200
17257 | 2019-07-22 | 2020-02-06 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-23 | COMP | 2020-08-21 | COMP | 2021-06-28 | COMP | 2021-07-27 | COMP | Rule 16 | 137 | 71 | 27 | 44 | 213 | 21 | 508
22902 | 2019-07-22 | 2020-10-15 | 2020-11-17 | 2020-11-17 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2022-02-26 | INPR | 2021-02-06 | COMP | Rule 16 | 314 | 23 | 24 | 1 |  |  | 389
13366 | 2019-07-23 | 2019-07-24 | 2019-09-14 | 2019-09-14 | COMP | 2019-09-19 | COMP | 2019-09-20 | COMP | 2019-10-30 | COMP | 2019-10-01 | COMP | Rule 16 | 2 | 37 | 4 | 2 | 29 |  | 50
13562 | 2019-07-23 | 2019-07-31 | 2019-10-15 | 2019-10-15 | COMP | 2019-12-03 | COMP | 2020-08-12 | COMP | 2020-09-02 | COMP | 2023-05-05 | COMP | Rule 15/16 | 7 | 54 | 33 | 177 | 16 | 671 | 953
13610 | 2019-07-23 | 2019-08-02 | 2019-09-04 | 2019-09-04 | COMP | 2019-10-18 | COMP | 2019-11-14 | COMP | 2020-02-08 | COMP | 2020-01-28 | COMP | Rule 16 | 9 | 23 | 33 | 19 | 57 |  | 129
13652 | 2019-07-23 | 2019-08-06 | 2019-10-25 | 2019-10-25 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-11-04 | COMP | 2019-11-15 | COMP | Rule 16 | 11 | 58 | 4 | 1 | 4 | 9 | 82
13779 | 2019-07-23 | 2019-08-09 | 2020-01-25 | 2020-01-25 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-06-16 | COMP | 2020-07-30 | COMP | Rule 16 | 14 | 114 | 84 | 1 | 17 | 33 | 259
13846 | 2019-07-23 | 2019-08-13 | 2019-11-21 | 2019-11-21 | COMP | 2020-10-20 | COMP | 2021-12-23 | COMP | 2021-11-18 | COMP | 2022-02-10 | COMP | Rule 15/16 | 16 | 71 | 231 | 295 | 0 | 35 | 644
13848 | 2019-07-23 | 2019-08-13 | 2019-10-17 | 2019-11-27 | COMP | 2019-12-10 | COMP | 2020-06-02 | COMP | 2019-11-06 | COMP | 2020-06-10 | COMP | Rule 16 | 16 | 47 | 8 | 121 | 0 | 7 | 223
13886 | 2019-07-23 | 2019-08-14 | 2019-11-20 | 2019-11-22 | COMP | 2019-12-09 | COMP | 2019-12-12 | COMP | 2020-01-21 | COMP | 2020-09-14 | COMP | Rule 16 | 17 | 69 | 10 | 4 | 26 | 167 | 290
13940 | 2019-07-23 | 2019-08-16 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-15 | COMP | 2020-06-19 | COMP | 2020-12-01 | COMP | 2021-02-05 | COMP | Rule 15/16 | 19 | 133 | 34 | 47 | 114 | 46 | 388
13993 | 2019-07-23 | 2019-08-20 | 2019-10-11 | 2019-10-15 | COMP | 2019-10-18 | COMP | 2019-12-16 | COMP | 2020-09-19 | COMP | 2020-09-30 | COMP | Rule 16 | 21 | 38 | 4 | 39 | 194 | 8 | 302
14126 | 2019-07-23 | 2019-08-26 | 2019-12-16 | 2020-08-16 | COMP | 2022-03-22 | COMP | 2022-04-08 | COMP | 2022-04-07 | COMP | 2022-05-10 | COMP | Rule 16 | 25 | 77 | 401 | 14 | 0 | 23 | 706
14193 | 2019-07-23 | 2019-08-29 | 2020-02-01 | 2020-02-01 | COMP | 2020-03-05 | COMP | 2020-05-01 | COMP | 2020-11-05 | COMP | 2021-01-03 | COMP | Rule 16 | 28 | 105 | 23 | 42 | 133 | 37 | 364
14301 | 2019-07-23 | 2019-09-04 | 2019-09-24 | 2019-09-24 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-18 | COMP | 2019-11-19 | COMP | Rule 16 | 31 | 15 | 36 | 1 | 4 | 2 | 84
14529 | 2019-07-23 | 2019-09-16 | 2019-12-13 | 2019-12-13 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-04-21 | COMP | 2020-05-06 | COMP | Rule 15/16 | 39 | 62 | 45 | 1 | 45 | 12 | 199
14550 | 2019-07-23 | 2019-09-16 | 2019-11-07 | 2019-12-11 | COMP | 2020-04-21 | COMP | 2020-05-08 | COMP | 2020-07-13 | COMP | 2020-08-14 | COMP | Rule 16 | 39 | 39 | 91 | 14 | 46 | 25 | 270
14687 | 2019-07-23 | 2019-09-23 | 2020-01-24 | 2020-01-24 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-04-24 | COMP | 2020-05-27 | COMP | Rule 16 | 44 | 84 | 26 | 1 | 40 | 23 | 213
14739 | 2019-07-23 | 2019-09-25 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-27 | COMP | 2020-03-02 | COMP | 2020-03-05 | COMP | 2020-03-31 | COMP | Rule 16 | 46 | 80 | 26 | 3 | 4 | 19 | 173
14800 | 2019-07-23 | 2019-09-27 | 2019-12-16 | 2019-12-16 | COMP | 2019-12-27 | COMP | 2020-02-04 | COMP | 2020-12-28 | COMP | 2021-02-08 | COMP | Rule 16 | 48 | 54 | 9 | 26 | 228 | 29 | 389
15048 | 2019-07-23 | 2019-10-10 | 2020-01-15 | 2020-01-15 | COMP | 2020-03-10 | COMP | 2020-03-26 | COMP | 2020-02-20 | COMP | 2020-04-08 | COMP | Rule 16 | 57 | 65 | 38 | 13 | 0 | 10 | 179
15198 | 2019-07-23 | 2019-10-18 | 2020-06-03 | 2020-06-03 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2021-08-04 | COMP | 2021-09-10 | COMP | Rule 16 | 63 | 156 | 69 | 1 | 228 | 27 | 539
15272 | 2019-07-23 | 2019-10-25 | 2019-12-09 | 2019-12-09 | COMP | 2019-12-27 | COMP | 2020-04-30 | COMP | 2021-05-30 | INPR | 2020-05-14 | COMP | Rule 16 | 68 | 29 | 14 | 87 |  |  | 205
15401 | 2019-07-23 | 2019-10-31 | 2019-12-05 | 2019-12-05 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2022-04-11 | COMP | 2022-04-13 | COMP | Rule 16 | 72 | 23 | 52 | 1 | 541 | 3 | 687
15741 | 2019-07-23 | 2019-11-19 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-24 | COMP | 2020-01-29 | COMP | 2020-01-28 | COMP | 2020-03-09 | COMP | Rule 16 | 84 | 33 | 12 | 4 | 0 | 28 | 157
15773 | 2019-07-23 | 2019-11-20 | 2020-03-31 | 2020-05-12 | COMP | 2020-04-02 | NOTN | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-07-08 | COMP | Other | 85 | 89 |  | 1 | 1 | 41 | 243
15865 | 2019-07-23 | 2019-11-26 | 2020-01-21 | 2020-01-21 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-04-24 | COMP | 2020-05-16 | COMP | Rule 16 | 89 | 36 | 28 | 1 | 41 | 16 | 206
16517 | 2019-07-23 | 2020-01-06 | 2020-03-13 | 2020-03-13 | COMP | 2020-04-06 | COMP | 2020-06-01 | COMP | 2020-06-09 | COMP | 2020-07-07 | COMP | Rule 16 | 114 | 48 | 17 | 40 | 7 | 21 | 242
17098 | 2019-07-23 | 2020-02-01 | 2020-05-05 | 2021-11-10 | COMP | 2021-12-09 | COMP | 2023-03-14 | COMP | 2023-03-13 | COMP | 2023-06-13 | COMP | Rule 16 | 132 | 66 | 19 | 316 | 0 | 65 | 979
17971 | 2019-07-23 | 2020-03-06 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-22 | COMP | 2020-08-19 | COMP | 2020-08-24 | COMP | 2021-04-11 | COMP | Rule 15/16 | 156 | 49 | 8 | 63 | 4 | 157 | 432
18666 | 2019-07-23 | 2020-04-01 | 2020-05-03 | 2020-05-03 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-10-21 | COMP | 2020-11-12 | COMP | Rule 16 | 174 | 23 | 115 | 1 | 7 | 16 | 332
19599 | 2019-07-23 | 2020-05-15 | 2020-08-03 | 2020-08-03 | COMP | 2020-08-28 | COMP | 2023-12-27 | INPR | 2023-10-09 | COMP | 2023-11-14 | COMP | Rule 16 | 206 | 56 | 20 |  |  |  | 1085
19895 | 2019-07-23 | 2020-05-27 | 2020-09-04 | 2020-09-04 | COMP | 2020-09-28 | COMP | 2020-11-06 | COMP | 2022-01-31 | INPR | 2020-12-09 | COMP | Rule 16 | 213 | 73 | 16 | 30 |  |  | 349
13432 | 2019-07-24 | 2019-07-25 | 2019-08-28 | 2019-09-01 | COMP | 2019-09-03 | NOTN | 2019-09-03 | COMP | 2019-09-03 | COMP | 2019-10-03 | COMP | Other | 2 | 25 |  | 1 | 1 | 23 | 51
13576 | 2019-07-24 | 2019-07-31 | 2019-08-13 | 2019-08-13 | COMP | 2019-10-02 | COMP | 2019-10-02 | COMP | 2019-09-20 | COMP | 2019-11-11 | COMP | Rule 16 | 6 | 10 | 36 | 1 | 0 | 28 | 77
13724 | 2019-07-24 | 2019-08-07 | 2019-10-09 | 2019-10-09 | COMP | 2019-12-23 | COMP | 2019-12-23 | COMP | 2020-01-07 | COMP | 2020-01-22 | COMP | Rule 16 | 11 | 45 | 51 | 1 | 10 | 11 | 124
13727 | 2019-07-24 | 2019-08-07 | 2019-08-27 | 2019-08-27 | COMP | 2020-01-08 | COMP | 2020-03-09 | COMP | 2020-05-01 | COMP | 2020-05-06 | COMP | Other | 11 | 15 | 91 | 42 | 40 | 4 | 198
13791 | 2019-07-24 | 2019-08-10 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-26 | COMP | 2020-03-04 | COMP | 2023-07-29 | INPR | 2020-03-24 | COMP | Rule 15/16 | 13 | 127 | 9 | 6 |  |  | 167
13794 | 2019-07-24 | 2019-08-10 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-14 | COMP | 2019-10-15 | COMP | 2019-11-20 | COMP | 2019-12-23 | COMP | Rule 16 | 13 | 38 | 8 | 2 | 26 | 22 | 105
13850 | 2019-07-24 | 2019-08-13 | 2019-09-24 | 2019-10-07 | COMP | 2019-10-16 | COMP | 2019-11-14 | COMP | 2019-11-13 | COMP | 2019-12-31 | COMP | Rule 16 | 15 | 30 | 8 | 21 | 0 | 31 | 110
13923 | 2019-07-24 | 2019-08-16 | 2020-04-01 | 2020-04-01 | COMP | 2020-08-17 | COMP | 2021-01-12 | COMP | 2020-11-09 | COMP | 2021-02-16 | COMP | Rule 15/16 | 18 | 156 | 98 | 101 | 0 | 24 | 393
14182 | 2019-07-24 | 2019-08-28 | 2019-09-12 | 2019-09-17 | COMP | 2019-09-18 | NOTN | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-11-19 | COMP | Other | 26 | 11 |  | 3 | 1 | 43 | 83
14192 | 2019-07-24 | 2019-08-29 | 2020-05-19 | 2021-02-09 | COMP | 2021-04-20 | COMP | 2022-04-18 | COMP | 2022-05-11 | COMP | 2022-07-19 | COMP | Rule 15/16 | 27 | 181 | 50 | 252 | 18 | 47 | 752
14212 | 2019-07-24 | 2019-08-29 | 2020-06-28 | 2021-02-05 | COMP | 2021-04-13 | COMP | 2022-04-18 | COMP | 2022-05-11 | COMP | 2022-07-19 | COMP | Rule 15/16 | 27 | 208 | 47 | 257 | 18 | 47 | 752
14465 | 2019-07-24 | 2019-09-11 | 2019-11-21 | 2019-11-21 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-06-05 | COMP | 2020-08-04 | COMP | Rule 15/16 | 35 | 51 | 43 | 1 | 93 | 43 | 261
14466 | 2019-07-24 | 2019-09-11 | 2019-11-21 | 2019-11-21 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-06-05 | COMP | 2020-07-21 | COMP | Rule 16 | 35 | 51 | 43 | 1 | 93 | 33 | 251
14624 | 2019-07-24 | 2019-09-19 | 2019-11-12 | 2019-11-12 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-02-15 | COMP | 2020-06-23 | COMP | Rule 16 | 41 | 38 | 12 | 1 | 53 | 90 | 231
14714 | 2019-07-24 | 2019-09-24 | 2020-01-24 | 2021-01-22 | COMP | 2021-02-08 | COMP | 2021-07-01 | COMP | 2021-06-28 | COMP | 2021-08-03 | COMP | Rule 15/16 | 44 | 83 | 12 | 102 | 0 | 23 | 511
15116 | 2019-07-24 | 2019-10-14 | 2020-01-14 | 2020-03-23 | COMP | 2020-04-28 | COMP | 2020-04-29 | COMP | 2020-06-25 | COMP | 2020-07-29 | COMP | Rule 15/16 | 58 | 62 | 27 | 2 | 41 | 25 | 257
15403 | 2019-07-24 | 2019-10-31 | 2020-01-08 | 2020-01-08 | COMP | 2020-03-05 | COMP | 2020-10-21 | COMP | 2021-05-19 | COMP | 2021-06-11 | COMP | Rule 16 | 71 | 45 | 40 | 163 | 144 | 17 | 475
15449 | 2019-07-24 | 2019-11-01 | 2020-01-24 | 2020-02-18 | COMP | 2020-05-15 | COMP | 2020-06-11 | COMP | 2020-06-15 | COMP | 2020-07-10 | COMP | Rule 16 | 72 | 55 | 64 | 19 | 3 | 20 | 244
15653 | 2019-07-24 | 2019-11-13 | 2020-04-10 | 2020-04-13 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-06-29 | COMP | 2020-08-26 | COMP | Rule 16 | 79 | 102 | 39 | 1 | 17 | 43 | 277
16349 | 2019-07-24 | 2019-12-23 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2021-02-22 | COMP | 2021-03-25 | COMP | Rule 16 | 105 | 77 | 23 | 1 | 195 | 24 | 420
16526 | 2019-07-24 | 2020-01-06 | 2020-05-21 | 2022-06-01 | COMP | 2022-06-06 | COMP | 2022-09-27 | COMP | 2022-10-31 | COMP | 2023-06-12 | COMP | Rule 16 | 113 | 97 | 4 | 79 | 25 | 153 | 977
19043 | 2019-07-24 | 2020-04-19 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-25 | COMP | 2020-07-09 | COMP | 2022-01-30 | INPR | 2021-01-14 | COMP | Rule 16 | 185 | 32 | 17 | 11 |  |  | 372
13555 | 2019-07-25 | 2019-07-30 | 2019-09-09 | 2019-09-09 | COMP | 2019-09-16 | COMP | 2020-03-09 | COMP | 2020-10-02 | COMP | 2020-11-25 | COMP | Rule 16 | 4 | 29 | 6 | 119 | 148 | 38 | 339
13575 | 2019-07-25 | 2019-07-31 | 2019-08-22 | 2019-08-22 | COMP | 2019-09-26 | COMP | 2020-03-06 | COMP | 2020-02-27 | COMP | 2020-03-11 | COMP | Rule 16 | 5 | 17 | 25 | 110 | 0 | 4 | 157
13594 | 2019-07-25 | 2019-08-01 | 2020-10-02 | 2021-06-09 | COMP | 2021-06-22 | COMP | 2021-07-08 | COMP | 2021-08-17 | COMP | 2021-10-20 | COMP | Rule 15/16 | 6 | 297 | 10 | 12 | 29 | 46 | 565
13726 | 2019-07-25 | 2019-08-07 | 2019-12-27 | 2019-12-27 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-23 | COMP | 2020-02-24 | COMP | Rule 16 | 10 | 98 | 14 | 1 | 5 | 22 | 145
13891 | 2019-07-25 | 2019-08-15 | 2019-12-11 | 2019-12-11 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2020-12-22 | COMP | 2021-02-16 | COMP | Rule 16 | 16 | 81 | 207 | 1 | 55 | 37 | 392
13938 | 2019-07-25 | 2019-08-16 | 2019-10-02 | 2019-11-09 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-04-06 | COMP | 2020-04-30 | COMP | Rule 16 | 17 | 33 | 9 | 1 | 91 | 19 | 193
14001 | 2019-07-25 | 2019-08-21 | 2019-10-16 | 2019-10-16 | COMP | 2020-03-17 | COMP | 2020-04-02 | COMP | 2021-04-20 | COMP | 2021-04-26 | COMP | Rule 16 | 20 | 40 | 103 | 13 | 265 | 5 | 441
14066 | 2019-07-25 | 2019-08-23 | 2019-09-26 | 2019-09-26 | COMP | 2019-09-30 | COMP | 2019-10-11 | COMP | 2019-10-16 | COMP | 2019-11-18 | COMP | Rule 16 | 22 | 24 | 3 | 10 | 4 | 23 | 81
14274 | 2019-07-25 | 2019-09-04 | 2019-12-31 | 2020-07-28 | COMP | 2020-08-25 | COMP | 2020-10-29 | COMP | 2020-10-30 | COMP | 2021-02-19 | COMP | Rule 16 | 29 | 81 | 21 | 47 | 2 | 74 | 395
14283 | 2019-07-25 | 2019-09-03 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-10-09 | COMP | 2019-12-13 | COMP | Rule 16 | 28 | 18 | 9 | 1 | 2 | 45 | 98
14300 | 2019-07-25 | 2019-09-04 | 2019-09-24 | 2019-09-24 | COMP | 2019-11-07 | COMP | 2019-11-08 | COMP | 2019-11-14 | COMP | 2019-11-18 | COMP | Rule 16 | 29 | 15 | 33 | 2 | 4 | 3 | 81
14330 | 2019-07-25 | 2019-09-05 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-08-12 | COMP | 2020-08-20 | COMP | Rule 16 | 30 | 99 | 33 | 1 | 107 | 7 | 272
14351 | 2019-07-25 | 2019-09-05 | 2019-09-23 | 2019-09-23 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2022-07-16 | INPR | 2020-11-10 | COMP | Rule 16 | 30 | 13 | 19 | 1 |  |  | 329
14428 | 2019-07-25 | 2019-09-09 | 2019-11-18 | 2019-11-18 | COMP | 2020-05-08 | COMP | 2020-05-13 | COMP | 2020-05-11 | COMP | 2020-07-08 | COMP | Rule 16 | 32 | 50 | 119 | 4 | 0 | 40 | 241
14698 | 2019-07-25 | 2019-09-23 | 2019-11-13 | 2019-11-13 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2020-02-05 | COMP | 2020-02-25 | COMP | Rule 16 | 42 | 37 | 11 | 1 | 46 | 14 | 146
14847 | 2019-07-25 | 2019-10-01 | 2019-11-05 | 2019-11-05 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2020-01-16 | COMP | 2020-02-19 | COMP | Rule 16 | 48 | 26 | 9 | 1 | 40 | 23 | 142
15001 | 2019-07-25 | 2019-10-08 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-09 | COMP | 2020-05-20 | COMP | 2020-06-06 | COMP | 2020-07-24 | COMP | Rule 16 | 53 | 110 | 17 | 30 | 12 | 35 | 253
15489 | 2019-07-25 | 2019-11-04 | 2020-02-19 | 2020-06-19 | COMP | 2020-06-23 | NOTN | 2020-06-23 | COMP | 2020-08-27 | COMP | 2020-10-14 | COMP | Other | 72 | 71 |  | 3 | 48 | 34 | 310
15663 | 2019-07-25 | 2019-11-14 | 2020-01-09 | 2020-01-09 | COMP | 2020-02-26 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-03-30 | COMP | Rule 16 | 79 | 37 | 33 | 5 | 1 | 20 | 170
16134 | 2019-07-25 | 2019-12-11 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-07 | COMP | 2020-03-10 | COMP | 2020-04-14 | COMP | 2020-08-28 | COMP | Rule 16 | 96 | 34 | 7 | 22 | 26 | 98 | 278
16241 | 2019-07-25 | 2019-12-17 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-15 | COMP | 2020-05-19 | COMP | 2020-04-15 | COMP | 2020-06-12 | COMP | Rule 16 | 100 | 69 | 15 | 25 | 0 | 18 | 223
16270 | 2019-07-25 | 2019-12-18 | 2020-01-29 | 2020-01-29 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-07-29 | COMP | 2020-08-19 | COMP | Rule 15/16 | 101 | 28 | 5 | 1 | 125 | 16 | 271
17245 | 2019-07-25 | 2020-02-05 | 2020-04-29 | 2020-04-29 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-11-09 | COMP | Rule 16 | 133 | 60 | 74 | 1 | 1 | 64 | 328
17311 | 2019-07-25 | 2020-02-08 | 2020-06-29 | 2021-08-20 | COMP | 2021-10-27 | COMP | 2022-02-23 | COMP | 2022-04-10 | COMP | 2022-05-19 | COMP | Rule 15/16 | 135 | 99 | 48 | 81 | 33 | 29 | 711
17585 | 2019-07-25 | 2020-02-21 | 2020-04-11 | 2020-04-11 | COMP | 2020-09-04 | COMP | 2020-09-04 | COMP | 2020-09-30 | COMP | 2020-10-29 | COMP | Rule 16 | 144 | 36 | 104 | 1 | 18 | 22 | 321
18701 | 2019-07-25 | 2020-04-02 | 2020-07-09 | 2020-07-09 | COMP | 2021-09-27 | COMP | 2021-09-27 | COMP | 2022-10-14 | COMP | 2022-12-22 | COMP | Rule 16 | 173 | 70 | 307 | 1 | 266 | 47 | 859
20137 | 2019-07-25 | 2020-06-08 | 2020-08-06 | 2020-08-06 | COMP | 2020-08-24 | COMP | 2020-11-10 | COMP | 2020-12-01 | COMP | 2020-12-21 | COMP | Rule 16 | 219 | 44 | 13 | 56 | 13 | 15 | 355
20556 | 2019-07-25 | 2020-06-26 | 2020-08-14 | 2020-08-14 | COMP | 2021-05-21 | COMP | 2021-05-25 | COMP | 2021-08-24 | COMP | 2021-10-01 | COMP | Rule 16 | 233 | 36 | 193 | 3 | 64 | 28 | 552
4299 | 2019-07-26 | 2020-05-12 | 2020-05-15 | 2020-05-15 | COMP | 2020-11-17 | COMP | 2020-12-01 | COMP | 2020-12-01 | COMP | 2021-01-22 | COMP | Other | 200 | 4 | 130 | 9 | 1 | 36 | 375
13601 | 2019-07-26 | 2019-08-01 | 2019-08-08 | 2019-08-08 | COMP | 2019-08-16 | COMP | 2019-08-16 | COMP | 2020-01-19 | INPR | 2019-10-08 | COMP | Rule 16 | 5 | 6 | 7 | 1 |  |  | 52
13871 | 2019-07-26 | 2019-08-14 | 2020-01-08 | 2020-01-08 | COMP | 2020-02-06 | COMP | 2020-04-01 | COMP | 2020-04-20 | COMP | 2020-04-29 | COMP | Rule 16 | 14 | 100 | 21 | 39 | 14 | 8 | 191
13964 | 2019-07-26 | 2019-08-20 | 2019-11-12 | 2020-01-16 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2019-08-20 | COMP | 2020-08-27 | COMP | Rule 16 | 18 | 59 | 16 | 1 | 0 | 143 | 276
14041 | 2019-07-26 | 2019-08-22 | 2019-11-27 | 2019-11-27 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-07 | COMP | 2020-01-23 | COMP | Rule 16 | 20 | 68 | 25 | 1 | 2 | 12 | 123
14253 | 2019-07-26 | 2019-08-30 | 2019-10-20 | 2019-10-20 | COMP | 2019-10-29 | COMP | 2019-10-29 | COMP | 2019-11-26 | COMP | 2019-12-26 | COMP | Rule 16 | 26 | 35 | 7 | 1 | 20 | 20 | 105
14269 | 2019-07-26 | 2019-09-03 | 2020-01-06 | 2020-01-06 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-03-16 | COMP | 2020-04-21 | COMP | Rule 16 | 27 | 85 | 48 | 1 | 2 | 27 | 185
14275 | 2019-07-26 | 2019-09-04 | 2019-11-06 | 2020-08-04 | COMP | 2020-08-13 | COMP | 2020-01-21 | COMP | 2020-09-17 | COMP | 2021-01-19 | COMP | Rule 16 | 28 | 46 | 8 |  | 170 | 83 | 372
14555 | 2019-07-26 | 2019-09-16 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2019-12-23 | COMP | 2020-04-15 | COMP | Rule 16 | 36 | 44 | 22 | 1 | 4 | 79 | 181
14589 | 2019-07-26 | 2019-09-17 | 2020-01-23 | 2020-01-23 | COMP | 2020-01-24 | NOTN | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-06-16 | COMP | Other | 37 | 87 |  | 14 | 1 | 89 | 224
14590 | 2019-07-26 | 2019-09-17 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-03-20 | COMP | Rule 16 | 37 | 93 | 8 | 1 | 1 | 27 | 163
14724 | 2019-07-26 | 2019-09-25 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-03-16 | COMP | 2020-05-13 | COMP | Rule 16 | 43 | 55 | 29 | 1 | 35 | 43 | 201
14898 | 2019-07-26 | 2019-10-02 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-02-10 | COMP | 2020-03-11 | COMP | Rule 16 | 48 | 65 | 22 | 1 | 3 | 22 | 156
15022 | 2019-07-26 | 2019-10-09 | 2020-01-30 | 2020-01-30 | COMP | 2021-02-01 | COMP | 2021-03-01 | COMP | 2021-03-15 | COMP | 2021-04-20 | COMP | Rule 16 | 53 | 76 | 254 | 20 | 11 | 27 | 436
15024 | 2019-07-26 | 2019-10-09 | 2020-02-01 | 2020-05-02 | COMP | 2020-07-31 | COMP | 2020-12-04 | COMP | 2020-11-25 | COMP | 2021-01-06 | COMP | Rule 16 | 53 | 77 | 64 | 87 | 0 | 22 | 364
15161 | 2019-07-26 | 2019-10-16 | 2020-03-06 | 2020-03-06 | COMP | 2020-05-26 | COMP | 2020-07-16 | COMP | 2020-07-08 | COMP | 2020-08-17 | COMP | Rule 16 | 58 | 96 | 57 | 38 | 0 | 23 | 268
15237 | 2019-07-26 | 2019-10-22 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-25 | COMP | 2020-02-27 | COMP | 2020-06-09 | COMP | 2020-07-17 | COMP | Rule 16 | 62 | 68 | 16 | 3 | 73 | 29 | 247
15242 | 2019-07-26 | 2019-10-22 | 2020-02-01 | 2020-02-01 | COMP | 2020-04-15 | COMP | 2020-04-21 | NOTN | 2020-04-15 | COMP | 2020-05-15 | COMP | Rule 16 | 62 | 68 | 52 |  |  |  | 203
15747 | 2019-07-26 | 2019-11-19 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-05-19 | COMP | 2020-06-26 | COMP | Rule 16 | 81 | 99 | 13 | 1 | 15 | 28 | 232
16614 | 2019-07-26 | 2020-01-10 | 2020-03-23 | 2020-04-02 | COMP | 2020-04-23 | COMP | 2021-01-05 | COMP | 2020-12-15 | COMP | 2021-01-12 | COMP | Rule 15/16 | 115 | 50 | 16 | 177 | 0 | 6 | 368
16746 | 2019-07-26 | 2020-01-14 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-13 | COMP | 2020-04-09 | COMP | 2020-04-13 | COMP | 2020-06-02 | COMP | Rule 16 | 117 | 31 | 12 | 20 | 3 | 36 | 214
17802 | 2019-07-26 | 2020-02-27 | 2020-04-20 | 2020-04-20 | COMP | 2020-07-28 | COMP | 2020-11-16 | COMP | 2020-04-20 | COMP | 2021-03-26 | COMP | Rule 16 | 147 | 38 | 71 | 78 | 0 | 89 | 419
17822 | 2019-07-26 | 2020-02-28 | 2020-06-24 | 2020-06-24 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2021-04-02 | COMP | 2021-04-24 | COMP | Rule 16 | 148 | 83 | 7 | 1 | 189 | 16 | 439
14348 | 2019-07-27 | 2019-09-07 | 2020-06-04 | 2021-01-28 | COMP | 2021-03-01 | COMP | 2021-03-03 | COMP | 2021-03-01 | COMP | 2021-04-19 | COMP | Other | 29 | 186 | 22 | 3 | 0 | 34 | 434
14710 | 2019-07-27 | 2019-09-24 | 2020-02-01 | 2020-10-06 | COMP | 2020-11-25 | COMP | 2022-04-04 | COMP | 2022-08-11 | COMP | 2022-08-29 | COMP | Other | 41 | 88 | 36 | 340 | 91 | 13 | 778
14711 | 2019-07-27 | 2019-09-24 | 2020-02-01 | 2020-10-06 | COMP | 2020-11-25 | COMP | 2021-02-26 | COMP | 2021-02-01 | COMP | 2021-02-26 | COMP | Other | 41 | 88 | 36 | 62 | 0 | 1 | 398
14926 | 2019-07-27 | 2019-10-04 | 2020-03-11 | 2020-03-11 | COMP | 2021-02-16 | COMP | 2022-09-23 | COMP | 2022-08-31 | COMP | 2022-11-03 | COMP | Rule 15/16 | 49 | 107 | 236 | 407 | 0 | 30 | 825
14927 | 2019-07-27 | 2019-10-04 | 2020-02-29 | 2020-06-11 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2022-08-11 | COMP | 2022-08-29 | COMP | Rule 15/16 | 49 | 99 | 118 | 1 | 430 | 13 | 778
15902 | 2019-07-27 | 2019-11-26 | 2020-04-20 | 2020-04-20 | COMP | 2020-04-21 | COMP | 2020-05-08 | COMP | 2022-07-30 | INPR | 2020-10-15 | COMP | Rule 16 | 85 | 99 | 2 | 14 |  |  | 309
16141 | 2019-07-27 | 2019-12-11 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-14 | COMP | 2020-05-26 | COMP | 2020-05-12 | COMP | 2020-12-17 | COMP | Rule 16 | 94 | 105 | 4 | 8 | 0 | 144 | 351
16514 | 2019-07-27 | 2020-01-06 | 2020-07-02 | 2020-07-02 | COMP | 2020-08-20 | COMP | 2020-09-16 | INPR | 2022-01-30 | REQD | 2020-10-01 | COMP | Rule 16 | 110 | 126 | 36 |  |  |  | 299
14234 | 2019-07-28 | 2019-08-30 | 2019-12-04 | 2020-04-28 | COMP | 2020-06-22 | COMP | 2020-01-22 | COMP | 2020-06-24 | COMP | 2020-08-10 | COMP | Rule 15/16 | 25 | 65 | 39 |  | 109 | 34 | 262
14454 | 2019-07-28 | 2019-09-11 | 2019-10-28 | 2019-10-28 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-01-03 | COMP | 2020-02-05 | COMP | Rule 16 | 32 | 34 | 26 | 1 | 20 | 23 | 131
13615 | 2019-07-29 | 2019-08-01 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-10 | COMP | 2020-06-15 | COMP | 2020-07-10 | COMP | 2020-07-27 | COMP | Rule 15/16 | 4 | 138 | 14 | 69 | 20 | 12 | 252
13679 | 2019-07-29 | 2019-08-05 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-19 | COMP | 2019-12-10 | COMP | 2019-12-13 | COMP | 2019-12-28 | COMP | Rule 16 | 6 | 58 | 18 | 14 | 4 | 10 | 105
13836 | 2019-07-29 | 2019-08-12 | 2019-09-14 | 2019-09-14 | COMP | 2019-09-16 | NOTN | 2020-06-26 | COMP | 2020-08-31 | COMP | 2020-09-16 | COMP | Other | 11 | 24 |  | 197 | 47 | 12 | 288
13860 | 2019-07-29 | 2019-08-13 | 2019-09-10 | 2019-09-17 | COMP | 2019-10-08 | COMP | 2019-10-08 | COMP | 2019-11-05 | COMP | 2019-11-25 | COMP | Rule 16 | 12 | 20 | 16 | 1 | 21 | 14 | 84
13952 | 2019-07-29 | 2019-08-19 | 2019-09-30 | 2019-09-30 | COMP | 2019-10-28 | COMP | 2019-10-28 | COMP | 2020-12-15 | COMP | 2021-01-12 | COMP | Rule 16 | 16 | 30 | 21 | 1 | 285 | 19 | 367
14203 | 2019-07-29 | 2019-08-28 | 2019-11-01 | 2019-11-01 | COMP | 2019-11-21 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-06-22 | COMP | Rule 15/16 | 23 | 47 | 14 | 80 | 1 | 67 | 227
14221 | 2019-07-29 | 2019-08-29 | 2020-02-04 | 2020-05-15 | COMP | 2020-06-05 | COMP | 2020-06-09 | COMP | 2020-06-02 | COMP | 2020-07-23 | COMP | Rule 16 | 24 | 107 | 15 | 3 | 0 | 33 | 250
14403 | 2019-07-29 | 2019-09-09 | 2019-11-18 | 2019-11-18 | COMP | 2019-11-27 | COMP | 2019-11-27 | COMP | 2019-12-10 | COMP | 2020-01-13 | COMP | Rule 16 | 30 | 50 | 8 | 1 | 8 | 23 | 115
14725 | 2019-07-29 | 2019-09-25 | 2020-02-08 | 2020-04-28 | COMP | 2020-05-06 | COMP | 2020-02-21 | COMP | 2020-05-06 | COMP | 2020-06-18 | COMP | Rule 16 | 42 | 92 | 7 |  | 54 | 31 | 225
14732 | 2019-07-29 | 2019-09-24 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2019-12-06 | COMP | 2020-01-10 | COMP | Rule 16 | 41 | 19 | 9 | 1 | 25 | 24 | 114
14877 | 2019-07-29 | 2019-10-02 | 2020-07-02 | 2020-07-02 | COMP | 2020-12-09 | COMP | 2020-12-22 | COMP | 2020-12-23 | COMP | 2021-02-08 | COMP | Rule 16 | 47 | 189 | 111 | 10 | 2 | 31 | 385
14892 | 2019-07-29 | 2019-10-02 | 2020-01-04 | 2020-01-04 | COMP | 2020-01-13 | COMP | 2020-05-04 | COMP | 2021-03-16 | COMP | 2021-04-07 | COMP | Rule 16 | 47 | 63 | 6 | 79 | 218 | 17 | 426
15002 | 2019-07-29 | 2019-10-08 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-09 | COMP | 2020-01-09 | NOTN | 2020-01-13 | COMP | 2020-01-21 | COMP | Rule 16 | 51 | 55 | 8 |  |  |  | 120
15462 | 2019-07-29 | 2019-11-04 | 2019-12-30 | 2020-01-13 | COMP | 2020-02-12 | COMP | 2022-08-21 | REQD | 2022-08-21 | REQD | 2020-05-27 | COMP | Rule 16 | 70 | 37 | 22 |  |  |  | 209
15965 | 2019-07-29 | 2019-12-04 | 2020-03-18 | 2020-03-18 | COMP | 2020-11-05 | COMP | 2020-11-05 | COMP | 2021-05-25 | COMP | 2021-05-26 | COMP | Rule 16 | 89 | 72 | 165 | 1 | 137 | 2 | 461
16129 | 2019-07-29 | 2019-12-11 | 2020-04-06 | 2020-04-06 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2020-12-18 | COMP | Rule 16 | 94 | 80 | 132 | 1 | 1 | 49 | 352
16311 | 2019-07-29 | 2019-12-20 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2021-05-12 | COMP | 2021-05-31 | COMP | Rule 16 | 101 | 97 | 65 | 1 | 191 | 13 | 463
16392 | 2019-07-29 | 2019-12-24 | 2020-02-29 | 2020-02-29 | COMP | 2020-05-13 | COMP | 2021-07-06 | COMP | 2021-07-06 | COMP | 2021-08-09 | COMP | Rule 16 | 103 | 45 | 53 | 289 | 1 | 25 | 512
17593 | 2019-07-29 | 2020-02-20 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-08 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-01 | COMP | Rule 16 | 141 | 20 | 16 | 19 | 1 | 20 | 212
17769 | 2019-07-29 | 2020-02-26 | 2020-05-19 | 2021-07-29 | COMP | 2021-08-05 | COMP | 2021-08-05 | COMP | 2021-08-19 | COMP | 2021-10-21 | COMP | Rule 16 | 145 | 60 | 6 | 1 | 11 | 45 | 564
18071 | 2019-07-29 | 2020-03-10 | 2020-07-02 | 2020-10-08 | COMP | 2020-12-16 | COMP | 2020-12-16 | COMP | 2020-12-16 | COMP | 2021-02-01 | COMP | Rule 16 | 154 | 82 | 47 | 1 | 1 | 31 | 380
18240 | 2019-07-29 | 2020-03-16 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-17 | COMP | 2020-05-07 | COMP | 2020-05-06 | COMP | 2020-06-23 | COMP | Rule 16 | 158 | 20 | 6 | 15 | 0 | 33 | 228
18322 | 2019-07-29 | 2020-03-20 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-29 | COMP | 2020-07-03 | COMP | 2021-05-24 | COMP | 2020-08-11 | COMP | Rule 16 | 162 | 32 | 19 | 26 | 224 |  | 263
18355 | 2019-07-29 | 2020-03-20 | 2020-06-22 | 2020-06-23 | COMP | 2020-07-21 | COMP | 2020-09-23 | COMP | 2020-12-30 | COMP | 2021-02-11 | COMP | Other | 162 | 66 | 21 | 46 | 67 | 30 | 388
18602 | 2019-07-29 | 2020-03-30 | 2020-05-14 | 2020-05-14 | COMP | 2020-09-01 | COMP | 2020-09-02 | COMP | 2020-10-02 | COMP | 2021-02-23 | COMP | Rule 15/16 | 168 | 34 | 78 | 2 | 22 | 96 | 395
20584 | 2019-07-29 | 2020-06-27 | 2020-10-15 | 2020-10-15 | COMP | 2021-02-18 | COMP | 2021-04-28 | COMP | 2022-06-18 | INPR | 2021-06-07 | COMP | Rule 16 | 231 | 78 | 84 | 50 |  |  | 468
31525 | 2019-07-29 | 2021-10-13 | 2021-11-17 | 2021-11-17 | COMP | 2021-11-17 | NOTN | 2022-01-14 | COMP | 2022-02-05 | COMP | 2022-04-27 | COMP | Other | 558 | 25 |  | 41 | 15 | 57 | 693
13540 | 2019-07-30 | 2019-07-30 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-23 | COMP | 2019-08-23 | COMP |  | INPR | 2019-09-09 | COMP | Other | 1 | 4 | 16 | 1 |  |  | 29
13586 | 2019-07-30 | 2019-07-31 | 2019-10-16 | 2019-10-16 | COMP | 2020-11-09 | COMP | 2021-02-12 | COMP | 2021-11-15 | COMP | 2022-01-24 | COMP | Rule 16 | 2 | 55 | 270 | 64 | 192 | 48 | 626
13745 | 2019-07-30 | 2019-08-07 | 2019-12-06 | 2019-12-06 | COMP | 2020-05-28 | COMP | 2020-05-28 | COMP | 2020-06-11 | COMP | 2020-07-25 | COMP | Rule 15/16 | 7 | 84 | 120 | 1 | 11 | 32 | 250
13773 | 2019-07-30 | 2019-08-08 | 2019-09-25 | 2020-04-06 | COMP | 2020-06-01 | COMP | 2020-06-09 | COMP | 2020-06-03 | COMP | 2020-07-14 | COMP | Rule 16 | 8 | 34 | 40 | 7 | 0 | 26 | 242
13851 | 2019-07-30 | 2019-08-13 | 2019-09-04 | 2019-09-04 | COMP | 2019-10-02 | COMP | 2019-10-16 | COMP | 2019-10-22 | COMP | 2019-11-03 | COMP | Rule 16 | 11 | 16 | 21 | 11 | 5 | 9 | 68
13997 | 2019-07-30 | 2019-08-20 | 2020-12-20 | 2020-12-20 | COMP | 2021-01-27 | COMP | 2021-05-10 | COMP | 2023-12-03 | INPR | 2022-06-28 | COMP | Rule 16 | 16 | 336 | 25 | 73 |  |  | 734
14145 | 2019-07-30 | 2019-08-27 | 2020-08-02 | 2020-12-20 | COMP | 2021-04-29 | COMP | 2021-05-12 | COMP |  | INPR | 2022-02-10 | COMP | Rule 15/16 | 21 | 235 | 90 | 10 |  |  | 639
14185 | 2019-07-30 | 2019-08-28 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-03 | COMP | 2020-02-12 | COMP | 2020-02-13 | COMP | 2020-03-19 | COMP | Rule 16 | 22 | 95 | 13 | 8 | 2 | 25 | 160
14273 | 2019-07-30 | 2019-09-04 | 2020-04-03 | 2020-04-03 | COMP | 2020-06-08 | COMP | 2021-09-08 | COMP | 2021-09-30 | COMP | 2021-10-01 | COMP | Rule 16 | 26 | 146 | 46 | 317 | 17 | 2 | 549
14292 | 2019-07-30 | 2019-09-03 | 2019-12-06 | 2019-12-06 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-03-10 | COMP | 2020-07-31 | COMP | Rule 16 | 25 | 66 | 41 | 1 | 24 | 103 | 255
14295 | 2019-07-30 | 2019-09-04 | 2019-12-11 | 2019-12-11 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-06-24 | COMP | 2020-08-03 | COMP | Rule 16 | 26 | 68 | 13 | 1 | 124 | 29 | 256
14316 | 2019-07-30 | 2019-09-04 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-10 | COMP | 2020-01-31 | COMP | 2020-03-04 | COMP | 2020-03-13 | COMP | Rule 16 | 26 | 63 | 26 | 15 | 23 | 8 | 156
14445 | 2019-07-30 | 2019-09-10 | 2019-10-24 | 2020-01-27 | COMP | 2020-05-31 | REQD | 2019-12-11 | COMP | 2019-12-19 | COMP | 2020-01-30 | COMP | Rule 16 | 30 | 33 |  |  | 7 | 28 | 126
14446 | 2019-07-30 | 2019-09-10 | 2019-10-15 | 2020-01-18 | COMP | 2020-05-31 | REQD | 2019-12-23 | COMP | 2019-12-19 | COMP | 2020-01-31 | COMP | Rule 16 | 30 | 26 |  |  | 0 | 27 | 127
14451 | 2019-07-30 | 2019-09-10 | 2020-01-29 | 2020-01-29 | COMP | 2020-06-12 | COMP | 2020-10-30 | COMP | 2023-09-02 | INPR | 2020-11-09 | COMP | Rule 16 | 30 | 96 | 96 | 100 |  |  | 325
14455 | 2019-07-30 | 2019-09-11 | 2019-10-30 | 2019-10-30 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-07-28 | COMP | 2020-07-29 | COMP | Rule 16 | 31 | 36 | 183 | 1 | 5 | 2 | 253
14494 | 2019-07-30 | 2019-09-13 | 2019-11-10 | 2019-11-10 | COMP | 2020-01-15 | COMP | 2020-01-09 | COMP | 2020-03-09 | COMP | 2020-08-21 | COMP | Rule 16 | 33 | 41 | 43 |  | 41 | 119 | 270
14734 | 2019-07-30 | 2019-09-25 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-15 | COMP | 2020-02-08 | COMP | 2020-02-10 | COMP | 2020-03-12 | COMP | Rule 16 | 41 | 64 | 12 | 17 | 1 | 23 | 155
14790 | 2019-07-30 | 2019-09-27 | 2019-10-22 | 2019-10-22 | COMP | 2019-10-30 | COMP | 2020-01-07 | COMP | 2020-03-03 | COMP | 2020-03-02 | COMP | Rule 16 | 43 | 18 | 7 | 45 | 39 |  | 147
14806 | 2019-07-30 | 2019-09-27 | 2020-02-11 | 2020-02-11 | COMP | 2020-12-23 | COMP | 2020-12-23 | COMP | 2022-05-12 | COMP | 2022-06-01 | COMP | Rule 15/16 | 43 | 92 | 221 | 1 | 350 | 14 | 716
14823 | 2019-07-30 | 2019-10-01 | 2019-10-28 | 2019-10-28 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-04-30 | COMP | 2020-06-01 | COMP | Rule 16 | 45 | 20 | 46 | 1 | 82 | 22 | 211
14865 | 2019-07-30 | 2019-10-01 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2022-01-30 | INPR | 2020-08-28 | COMP | Rule 16 | 45 | 78 | 15 | 1 |  |  | 275
14916 | 2019-07-30 | 2019-10-03 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-22 | COMP | 2020-08-19 | COMP | 2020-07-31 | COMP | 2020-09-15 | COMP | Rule 16 | 47 | 158 | 23 | 43 | 0 | 19 | 286
15147 | 2019-07-30 | 2019-10-16 | 2020-10-23 | 2020-10-23 | COMP | 2021-02-01 | COMP | 2021-06-07 | COMP | 2021-07-20 | COMP | 2021-08-18 | COMP | Rule 15/16 | 56 | 259 | 66 | 89 | 31 | 22 | 518
15323 | 2019-07-30 | 2019-10-25 | 2020-01-16 | 2020-01-16 | COMP | 2020-03-17 | COMP | 2021-06-21 | COMP | 2021-11-01 | COMP | 2021-12-07 | COMP | Rule 15/16 | 63 | 55 | 42 | 320 | 94 | 24 | 593
15475 | 2019-07-30 | 2019-11-05 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-29 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-04-15 | COMP | Rule 16 | 70 | 26 | 31 | 54 | 1 | 2 | 179
15611 | 2019-07-30 | 2019-11-12 | 2020-02-07 | 2020-02-07 | COMP | 2020-03-18 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-04-16 | COMP | Rule 16 | 74 | 59 | 28 |  | 1 | 23 | 180
15797 | 2019-07-30 | 2019-11-20 | 2020-01-27 | 2020-05-05 | COMP | 2020-05-29 | COMP | 2020-06-01 | COMP | 2021-02-04 | COMP | 2021-03-11 | COMP | Rule 15/16 | 80 | 44 | 18 | 2 | 172 | 25 | 406
15967 | 2019-07-30 | 2019-12-03 | 2020-04-13 | 2020-04-13 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-28 | COMP | 2020-11-13 | COMP | Rule 15/16 | 87 | 91 | 61 | 1 | 39 | 54 | 328
16157 | 2019-07-30 | 2019-12-12 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-25 | COMP | 2020-02-26 | COMP | 2020-02-05 | COMP | 2020-05-12 | COMP | Rule 16 | 94 | 33 | 18 | 2 | 0 | 55 | 198
16389 | 2019-07-30 | 2019-12-24 | 2020-03-02 | 2020-03-02 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-07-29 | COMP | 2020-08-31 | COMP | Rule 16 | 102 | 46 | 102 | 1 | 6 | 24 | 276
17043 | 2019-07-30 | 2020-01-28 | 2020-05-14 | 2020-05-14 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2021-04-27 | COMP | 2021-07-10 | COMP | Rule 16 | 124 | 77 | 67 | 1 | 174 | 52 | 490
18870 | 2019-07-30 | 2020-04-09 | 2020-10-03 | 2020-10-03 | COMP | 2020-11-16 | COMP | 2020-11-16 | COMP | 2021-04-16 | COMP | 2021-04-29 | COMP | Rule 16 | 175 | 125 | 30 | 1 | 104 | 10 | 441
4226 | 2019-07-31 | 2019-09-06 | 2019-09-30 | 2019-09-30 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2019-12-03 | COMP | 2020-01-27 | COMP | Rule 16 | 27 | 17 | 43 | 1 | 2 | 37 | 122
4232 | 2019-07-31 | 2019-09-18 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-29 | COMP | 2023-02-25 | REQD | 2019-10-29 | COMP | 2019-11-15 | COMP | Rule 16 | 35 | 13 | 17 |  |  |  | 76
13788 | 2019-07-31 | 2019-08-09 | 2020-04-15 | 2020-04-16 | COMP | 2020-04-22 | COMP | 2020-04-16 | COMP | 2020-04-27 | COMP | 2020-06-04 | COMP | Rule 16 | 8 | 171 | 5 |  | 8 | 28 | 213
13821 | 2019-07-31 | 2019-08-12 | 2019-09-30 | 2019-09-30 | COMP | 2020-03-30 | COMP | 2020-06-30 | COMP | 2020-03-31 | COMP | 2020-07-30 | COMP | Rule 16 | 9 | 35 | 124 | 66 | 0 | 23 | 253
13837 | 2019-07-31 | 2019-08-13 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-21 | COMP | 2019-10-21 | COMP | 2020-08-12 | COMP | 2020-10-13 | COMP | Rule 16 | 10 | 43 | 7 | 1 | 205 | 44 | 305
14035 | 2019-07-31 | 2019-08-21 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2020-02-10 | COMP | 2020-02-28 | COMP | Rule 16 | 16 | 35 | 5 | 1 | 79 | 14 | 145
14143 | 2019-07-31 | 2019-08-27 | 2019-09-30 | 2019-11-12 | COMP | 2019-12-03 | COMP | 2019-12-26 | COMP | 2020-08-29 | COMP | 2021-06-14 | COMP | Rule 16 | 20 | 24 | 14 | 17 | 173 | 197 | 471
14314 | 2019-07-31 | 2019-09-04 | 2020-03-08 | 2020-09-18 | COMP | 2020-12-03 | COMP | 2021-07-23 | INPR | 2021-07-23 | COMP | 2022-01-18 | COMP | Rule 15/16 | 25 | 126 | 52 |  |  |  | 621
14323 | 2019-07-31 | 2019-09-04 | 2020-01-07 | 2020-01-07 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-05-14 | COMP | 2021-03-23 | COMP | Other | 25 | 85 | 98 | 1 | 0 | 208 | 413
14374 | 2019-07-31 | 2019-09-06 | 2019-12-20 | 2020-05-29 | COMP | 2020-06-26 | COMP | 2020-04-20 | COMP | 2020-07-01 | COMP | 2020-11-12 | COMP | Rule 16 | 27 | 73 | 21 |  | 52 | 95 | 326
14519 | 2019-07-31 | 2019-09-13 | 2019-10-26 | 2019-10-26 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-03-03 | COMP | Rule 16 | 32 | 31 | 60 | 1 | 1 | 26 | 147
14554 | 2019-07-31 | 2019-09-16 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2019-11-27 | COMP | 2019-12-27 | COMP | Rule 16 | 33 | 44 | 9 | 1 | 0 | 19 | 103
14762 | 2019-07-31 | 2019-09-27 | 2019-12-10 | 2019-12-10 | COMP | 2019-12-17 | COMP | 2019-12-20 | COMP | 2019-12-19 | COMP | 2020-02-25 | COMP | Rule 16 | 42 | 50 | 6 | 4 | 0 | 44 | 142
14914 | 2019-07-31 | 2019-10-03 | 2020-01-07 | 2020-01-08 | COMP | 2020-01-23 | COMP | 2020-01-24 | COMP | 2020-01-03 | COMP | 2020-01-31 | COMP | Rule 16 | 46 | 64 | 11 | 2 | 0 | 6 | 126
15173 | 2019-07-31 | 2019-10-17 | 2019-11-07 | 2019-11-16 | COMP | 2019-11-26 | COMP | 2020-04-09 | COMP | 2020-03-10 | COMP | 2020-07-06 | COMP | Rule 16 | 56 | 16 | 7 | 92 | 0 | 62 | 235
15692 | 2019-07-31 | 2019-11-15 | 2020-06-23 | 2022-08-11 | COMP | 2022-09-20 | COMP | 2022-12-12 | COMP | 2022-12-20 | COMP | 2022-12-28 | COMP | Rule 15/16 | 76 | 151 | 28 | 57 | 7 | 6 | 858
15862 | 2019-07-31 | 2019-11-25 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-06 | COMP | 2020-10-06 | COMP | 2020-09-30 | COMP | 2020-11-06 | COMP | Rule 15/16 | 82 | 80 | 11 | 130 | 0 | 24 | 323
16535 | 2019-07-31 | 2020-01-06 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-06 | COMP | 2020-06-23 | COMP | 2021-01-13 | COMP | 2021-01-20 | COMP | Rule 16 | 108 | 49 | 16 | 56 | 141 | 5 | 370
16900 | 2019-07-31 | 2020-01-22 | 2020-03-08 | 2020-03-08 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2022-01-30 | INPR | 2020-10-27 | COMP | Rule 16 | 119 | 32 | 13 | 1 |  |  | 315
17262 | 2019-07-31 | 2020-02-06 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-10 | COMP | 2020-07-21 | COMP | 2020-09-01 | COMP | 2020-10-02 | COMP | Rule 16 | 130 | 66 | 45 | 8 | 31 | 23 | 298
17464 | 2019-07-31 | 2020-02-14 | 2020-04-29 | 2020-04-29 | COMP | 2020-06-22 | COMP | 2020-09-17 | COMP |  | INPR | 2020-12-09 | COMP | Rule 15/16 | 136 | 53 | 38 | 63 |  |  | 343
18230 | 2019-07-31 | 2020-03-16 | 2020-07-16 | 2020-07-16 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-12-16 | COMP | 2021-01-11 | COMP | Rule 16 | 156 | 88 | 23 | 1 | 84 | 17 | 364
18296 | 2019-07-31 | 2020-03-19 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP |  |  | 2020-12-08 | COMP | Rule 16 | 159 | 19 | 11 | 1 |  |  | 342
19609 | 2019-07-31 | 2020-05-14 | 2020-09-18 | 2022-01-24 | COMP | 2022-05-04 | COMP | 2021-05-01 | COMP |  | INPR | 2022-02-22 | COMP | Rule 15/16 | 199 | 90 | 72 |  |  |  | 645
29248 | 2019-07-31 | 2021-07-14 | 2022-04-19 | 2022-04-19 | COMP | 2022-04-19 | NOTN | 2022-05-20 | COMP | 2022-05-18 | COMP | 2022-07-15 | COMP | Other | 492 | 194 |  | 24 | 0 | 38 | 745
4313 | 2019-08-01 | 2020-08-10 | 2021-01-05 | 2021-01-05 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP |  | INPR | 2021-05-07 | COMP | Rule 16 | 259 | 101 | 23 | 1 |  |  | 445
13600 | 2019-08-01 | 2019-08-01 | 2019-08-02 | 2019-08-02 | COMP | 2019-08-12 | COMP | 2019-08-12 | COMP | 2019-08-14 | COMP | 2019-09-23 | COMP | Rule 15/16 | 1 | 2 | 7 | 1 | 3 | 28 | 37
13770 | 2019-08-01 | 2019-08-08 | 2019-11-08 | 2019-11-08 | COMP | 2019-12-02 | COMP | 2019-12-03 | COMP | 2019-12-17 | COMP | 2020-01-10 | COMP | Rule 16 | 6 | 66 | 14 | 2 | 11 | 17 | 111
14065 | 2019-08-01 | 2019-08-23 | 2019-11-23 | 2019-11-23 | COMP | 2019-12-26 | COMP | 2019-12-26 | COMP | 2020-01-07 | COMP | 2020-02-11 | COMP | Rule 16 | 17 | 64 | 21 | 1 | 8 | 25 | 132
14167 | 2019-08-01 | 2019-08-28 | 2019-11-06 | 2019-11-06 | COMP | 2019-12-06 | COMP | 2019-12-12 | COMP | 2020-10-19 | COMP | 2021-03-23 | COMP | Rule 16 | 20 | 50 | 20 | 5 | 217 | 105 | 412
14299 | 2019-08-01 | 2019-09-03 | 2020-01-27 | 2020-01-27 | COMP | 2020-02-11 | COMP | 2020-03-02 | COMP | 2020-02-13 | COMP | 2020-04-13 | COMP | Rule 16 | 23 | 99 | 12 | 14 | 0 | 31 | 175
14361 | 2019-08-01 | 2019-09-06 | 2019-11-12 | 2019-11-12 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-01-06 | COMP | 2020-01-22 | COMP | Rule 16 | 26 | 47 | 6 | 1 | 31 | 12 | 118
14419 | 2019-08-01 | 2019-09-09 | 2019-12-05 | 2019-12-05 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-07-21 | COMP | 2020-07-30 | COMP | Rule 16 | 27 | 61 | 47 | 1 | 113 | 8 | 252
14472 | 2019-08-01 | 2019-09-11 | 2020-05-30 | 2021-04-26 | COMP | 2021-09-09 | COMP | 2021-09-09 | INPR |  | REQD | 2023-06-07 | COMP | Rule 15/16 | 29 | 180 | 96 |  |  |  | 968
14485 | 2019-08-01 | 2019-09-12 | 2019-10-14 | 2019-10-14 | COMP | 2019-10-15 | NOTN | 2019-10-15 | COMP | 2020-04-26 | INPR | 2020-01-15 | COMP | Other | 30 | 23 |  | 2 |  |  | 114
14499 | 2019-08-01 | 2019-09-13 | 2019-11-04 | 2019-11-04 | COMP | 2019-12-02 | COMP | 2020-02-28 | COMP | 2020-05-11 | COMP | 2020-05-13 | COMP | Rule 15/16 | 31 | 37 | 18 | 61 | 52 | 3 | 197
14528 | 2019-08-01 | 2019-09-16 | 2019-10-12 | 2019-10-12 | COMP | 2019-10-23 | COMP | 2019-10-23 | COMP | 2019-11-26 | COMP | 2019-12-03 | COMP | Rule 16 | 32 | 20 | 8 | 1 | 24 | 4 | 85
14565 | 2019-08-01 | 2019-09-16 | 2019-10-10 | 2019-10-10 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2019-10-22 | COMP | 2020-01-09 | COMP | Rule 16 | 32 | 19 | 7 | 1 | 3 | 53 | 110
14653 | 2019-08-01 | 2019-09-20 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2019-09-20 | COMP | 2020-02-25 | COMP | Rule 16 | 36 | 37 | 15 | 1 | 0 | 56 | 141
15107 | 2019-08-01 | 2019-10-14 | 2019-11-06 | 2019-11-06 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-22 | COMP | 2020-01-27 | COMP | Rule 16 | 52 | 18 | 39 | 1 | 12 | 4 | 121
15264 | 2019-08-01 | 2019-10-23 | 2020-02-12 | 2020-02-12 | COMP | 2021-02-03 | COMP | 2021-02-16 | COMP | 2022-07-18 | COMP | 2022-09-13 | COMP | Other | 59 | 75 | 247 | 9 | 359 | 41 | 785
15609 | 2019-08-01 | 2019-11-10 | 2020-02-25 | 2020-02-25 | COMP | 2020-03-06 | COMP | 2020-08-14 | COMP | 2021-01-13 | COMP | 2021-02-17 | COMP | Rule 16 | 71 | 70 | 9 | 115 | 103 | 24 | 388
15646 | 2019-08-01 | 2019-11-13 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-06 | COMP | 2020-06-02 | COMP | 2020-06-16 | COMP | 2020-06-25 | COMP | Rule 16 | 73 | 91 | 8 | 41 | 11 | 8 | 227
15754 | 2019-08-01 | 2019-11-20 | 2020-03-06 | 2020-03-06 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-04-22 | COMP | 2020-05-27 | COMP | Rule 16 | 78 | 72 | 17 | 1 | 18 | 25 | 206
16262 | 2019-08-01 | 2019-12-20 | 2020-05-16 | 2022-04-05 | COMP | 2023-04-20 | COMP | 2023-05-04 | COMP | 2023-05-05 | COMP | 2023-06-23 | COMP | Rule 16 | 98 | 102 | 262 | 11 | 2 | 34 | 979
17353 | 2019-08-01 | 2020-02-10 | 2020-06-28 | 2020-10-05 | COMP | 2020-10-26 | COMP | 2021-02-16 | COMP | 2021-03-20 | COMP | 2021-04-09 | COMP | Rule 15/16 | 131 | 98 | 16 | 75 | 24 | 15 | 425
17355 | 2019-08-01 | 2020-02-10 | 2020-10-16 | 2020-10-16 | COMP | 2020-11-23 | COMP | 2021-02-22 | COMP | 2021-06-09 | COMP | 2021-06-29 | COMP | Rule 15/16 | 131 | 177 | 26 | 60 | 77 | 15 | 481
17760 | 2019-08-01 | 2020-02-26 | 2020-03-27 | 2020-04-01 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | Rule 16 | 142 | 23 | 17 | 1 | 118 | 1 | 300
18121 | 2019-08-01 | 2020-03-11 | 2020-06-24 | 2020-06-24 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP |  | INPR | 2023-07-20 | COMP | Rule 16 | 152 | 75 | 33 | 1 |  |  | 997
18285 | 2019-08-01 | 2020-03-19 | 2020-06-16 | 2020-06-16 | COMP | 2020-06-24 | COMP | 2020-12-07 | COMP |  | INPR | 2021-06-10 | COMP | Rule 15/16 | 158 | 63 | 7 | 115 |  |  | 468
18297 | 2019-08-01 | 2020-03-19 | 2020-05-07 | 2020-05-07 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP |  |  | 2022-02-24 | COMP | Rule 16 | 158 | 36 | 82 | 1 |  |  | 646
18749 | 2019-08-01 | 2020-04-07 | 2020-07-18 | 2020-07-18 | COMP | 2020-07-23 | COMP | 2021-02-09 | COMP | 2021-05-25 | COMP | 2021-07-01 | COMP | Rule 16 | 171 | 73 | 4 | 137 | 75 | 27 | 483
20264 | 2019-08-01 | 2020-06-12 | 2020-08-21 | 2020-08-21 | COMP | 2020-10-07 | COMP | 2020-12-15 | COMP |  | INPR | 2021-02-19 | COMP | Rule 16 | 218 | 51 | 33 | 47 |  |  | 390
13782 | 2019-08-02 | 2019-08-09 | 2019-10-22 | 2020-03-08 | COMP | 2020-03-13 | COMP | 2020-01-27 | COMP | 2021-03-27 | INPR | 2020-03-25 | COMP | Rule 16 | 6 | 52 | 5 |  |  |  | 161
13842 | 2019-08-02 | 2019-08-12 | 2019-08-15 | 2019-08-15 | COMP | 2019-08-20 | COMP | 2019-08-20 | COMP | 2019-09-20 | COMP | 2019-09-20 | COMP | Rule 16 | 7 | 4 | 4 | 1 | 23 | 1 | 35
13881 | 2019-08-02 | 2019-08-14 | 2020-01-31 | 2020-01-31 | COMP | 2020-03-06 | COMP | 2020-06-23 | COMP | 2020-06-24 | COMP | 2020-07-06 | COMP | Rule 15/16 | 9 | 116 | 25 | 77 | 2 | 9 | 233
14023 | 2019-08-02 | 2019-08-22 | 2019-11-19 | 2020-04-09 | COMP | 2020-04-10 | COMP | 2020-04-16 | COMP | 2020-03-30 | COMP | 2020-04-30 | COMP | Rule 16 | 15 | 62 | 2 | 5 | 0 | 11 | 187
14250 | 2019-08-02 | 2019-08-30 | 2020-01-08 | 2020-01-08 | COMP | 2020-11-18 | COMP | 2020-11-18 | COMP | 2021-03-15 | COMP | 2021-05-25 | COMP | Rule 16 | 21 | 88 | 221 | 1 | 78 | 52 | 456
14371 | 2019-08-02 | 2019-09-06 | 2019-10-22 | 2019-10-22 | COMP | 2019-10-29 | COMP | 2019-11-14 | COMP | 2019-09-06 | COMP | 2020-01-17 | COMP | Rule 16 | 25 | 33 | 6 | 12 | 0 | 43 | 115
14376 | 2019-08-02 | 2019-09-07 | 2019-12-24 | 2019-12-24 | COMP | 2020-02-18 | COMP | 2020-03-12 | COMP | 2020-07-12 | COMP | 2020-09-21 | COMP | Rule 16 | 25 | 74 | 37 | 18 | 86 | 50 | 287
14477 | 2019-08-02 | 2019-09-12 | 2020-02-01 | 2020-02-01 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-05-12 | COMP | 2020-06-11 | COMP | Rule 16 | 29 | 96 | 37 | 1 | 35 | 22 | 216
14514 | 2019-08-02 | 2019-09-13 | 2020-02-07 | 2020-02-07 | COMP | 2020-02-07 | NOTN | 2020-03-03 | COMP | 2020-03-04 | COMP | 2020-07-24 | COMP | Other | 30 | 100 |  | 17 | 2 | 102 | 247
15102 | 2019-08-02 | 2019-10-12 | 2020-03-18 | 2020-05-07 | COMP | 2020-05-07 | NOTN | 2020-05-07 | COMP | 2020-05-19 | COMP | 2020-07-16 | COMP | Other | 50 | 106 |  | 1 | 9 | 42 | 241
15371 | 2019-08-02 | 2019-10-30 | 2020-03-01 | 2020-03-01 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2020-03-17 | COMP | 2020-05-05 | COMP | Rule 16 | 63 | 81 | 9 | 1 | 4 | 36 | 190
15399 | 2019-08-02 | 2019-10-30 | 2020-03-07 | 2020-03-07 | COMP | 2020-03-27 | COMP | 2020-04-13 | COMP | 2020-04-29 | COMP | 2020-06-02 | COMP | Rule 16 | 63 | 86 | 15 | 12 | 13 | 24 | 209
15584 | 2019-08-02 | 2019-11-08 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-10 | COMP | 2020-06-01 | COMP | 2020-05-04 | COMP | 2020-06-04 | COMP | Rule 16 | 70 | 87 | 18 | 36 | 0 | 4 | 211
16210 | 2019-08-02 | 2019-12-16 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | Rule 16 | 93 | 32 | 4 | 1 | 15 | 1 | 141
17321 | 2019-08-02 | 2020-02-10 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-07-16 | COMP | Rule 16 | 130 | 62 | 39 | 1 | 1 | 13 | 241
17345 | 2019-08-02 | 2020-02-10 | 2020-03-11 | 2020-04-13 | COMP | 2020-04-08 | NOTN | 2020-04-13 | COMP | 2020-04-14 | COMP | 2020-05-04 | COMP | Other | 130 | 22 |  | 1 | 2 | 15 | 189
18707 | 2019-08-02 | 2020-04-03 | 2021-02-08 | 2021-02-08 | COMP | 2021-05-06 | COMP | 2021-06-10 | COMP | 2023-12-03 | INPR | 2021-06-16 | COMP | Rule 16 | 168 | 214 | 63 | 25 |  |  | 471
18776 | 2019-08-02 | 2020-04-06 | 2020-05-22 | 2020-05-22 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2023-09-01 | COMP | 2023-10-12 | COMP | Rule 16 | 169 | 35 | 99 | 1 | 727 | 29 | 1055
13637 | 2019-08-03 | 2019-08-03 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-12 | NOTN | 2020-09-18 | COMP | 2021-04-13 | COMP | 2021-05-05 | COMP | Other | 0 | 142 |  | 144 | 141 | 17 | 441
14058 | 2019-08-03 | 2019-08-23 | 2020-05-06 | 2020-05-29 | COMP | 2020-06-16 | COMP | 2020-08-17 | COMP | 2021-09-26 | COMP | 2021-10-24 | COMP | Rule 16 | 15 | 176 | 13 | 45 | 279 | 20 | 560
14766 | 2019-08-03 | 2019-09-26 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-27 | COMP | 2020-02-25 | COMP | 2020-02-26 | COMP | 2020-06-05 | COMP | Rule 16 | 38 | 74 | 9 | 21 | 2 | 72 | 211
14421 | 2019-08-04 | 2019-09-09 | 2019-10-21 | 2019-10-21 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-11-25 | COMP | 2020-01-07 | COMP | Rule 15/16 | 25 | 31 | 20 | 1 | 6 | 28 | 106
15201 | 2019-08-04 | 2019-10-18 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-09 | COMP | 2020-06-09 | COMP | 2021-01-19 | COMP | 2021-03-04 | COMP | Rule 16 | 54 | 108 | 11 | 43 | 154 | 32 | 397
16878 | 2019-08-04 | 2020-01-21 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-08 | COMP | 2020-06-17 | COMP | 2020-05-26 | COMP | 2020-06-26 | COMP | Rule 16 | 115 | 68 | 11 | 28 | 0 | 8 | 226
13893 | 2019-08-05 | 2019-08-15 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-04-26 | INPR | 2019-12-27 | COMP | Rule 16 | 9 | 35 | 20 | 1 |  |  | 100
13962 | 2019-08-05 | 2019-08-19 | 2020-02-09 | 2020-02-09 | COMP | 2021-01-22 | COMP | 2021-03-17 | COMP | 2021-10-20 | COMP | 2022-02-18 | COMP | Rule 15/16 | 11 | 118 | 241 | 38 | 153 | 84 | 641
14162 | 2019-08-05 | 2019-08-28 | 2020-01-13 | 2020-01-13 | COMP | 2020-01-27 | COMP | 2020-05-29 | COMP | 2020-08-11 | COMP | 2020-09-10 | COMP | Rule 16 | 18 | 93 | 10 | 88 | 53 | 22 | 279
14199 | 2019-08-05 | 2019-08-29 | 2019-09-28 | 2019-09-28 | COMP | 2019-12-23 | COMP | 2020-01-15 | COMP | 2020-09-11 | COMP | 2020-09-24 | COMP | Rule 16 | 19 | 21 | 58 | 16 | 169 | 10 | 289
14200 | 2019-08-05 | 2019-08-29 | 2020-01-12 | 2020-01-12 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-03-11 | COMP | 2020-06-15 | COMP | Rule 16 | 19 | 91 | 6 | 1 | 36 | 68 | 217
14394 | 2019-08-05 | 2019-09-09 | 2019-10-03 | 2019-10-29 | COMP | 2019-12-02 | COMP | 2019-12-18 | COMP | 2019-09-09 | COMP | 2020-01-30 | COMP | Rule 16 | 25 | 19 | 22 | 13 | 0 | 29 | 122
14496 | 2019-08-05 | 2019-09-12 | 2019-11-27 | 2019-11-27 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2020-04-26 | INPR | 2020-01-09 | COMP | Rule 16 | 28 | 54 | 11 | 1 |  |  | 108
14628 | 2019-08-05 | 2019-09-20 | 2019-10-18 | 2019-10-18 | COMP |  |  |  |  | 2020-05-11 | COMP | 2019-12-16 | COMP | Other | 34 | 21 |  |  |  |  | 92
14795 | 2019-08-05 | 2019-09-27 | 2020-02-06 | 2020-02-06 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-17 | COMP | 2020-07-09 | COMP | Rule 16 | 39 | 89 | 62 | 1 | 32 | 17 | 235
14871 | 2019-08-05 | 2019-10-01 | 2020-02-19 | 2020-02-19 | COMP | 2020-04-29 | COMP | 2020-04-30 | COMP | 2020-05-04 | COMP | 2020-06-01 | COMP | Rule 16 | 41 | 95 | 51 | 2 | 3 | 20 | 207
14910 | 2019-08-05 | 2019-10-03 | 2020-02-04 | 2020-02-04 | COMP | 2020-04-10 | COMP | 2020-05-18 | COMP | 2020-04-20 | COMP | 2020-07-03 | COMP | Rule 16 | 43 | 83 | 48 | 27 | 0 | 34 | 231
14947 | 2019-08-05 | 2019-10-05 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-03 | NOTN | 2020-03-03 | COMP | 2020-04-28 | COMP | 2020-05-13 | COMP | Other | 44 | 100 |  | 1 | 41 | 12 | 195
15294 | 2019-08-05 | 2019-10-24 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2020-01-22 | COMP | 2020-01-27 | COMP | Rule 16 | 58 | 11 | 23 | 1 | 27 | 4 | 119
15491 | 2019-08-05 | 2019-11-05 | 2020-02-01 | 2020-02-01 | COMP | 2020-03-19 | COMP | 2020-07-10 | COMP | 2020-05-30 | COMP | 2020-08-25 | COMP | Rule 16 | 66 | 58 | 33 | 81 | 0 | 33 | 268
15666 | 2019-08-05 | 2019-11-14 | 2020-05-04 | 2020-05-04 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-10-19 | COMP | 2020-11-20 | COMP | Rule 16 | 72 | 117 | 46 | 1 | 74 | 24 | 329
16064 | 2019-08-05 | 2019-12-07 | 2020-05-19 | 2020-05-19 | COMP | 2021-01-08 | COMP | 2021-03-26 | COMP | 2023-12-03 | INPR | 2021-07-20 | COMP | Rule 16 | 86 | 113 | 162 | 54 |  |  | 493
16125 | 2019-08-05 | 2019-12-11 | 2020-04-09 | 2020-04-09 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-07-28 | COMP | 2020-11-30 | COMP | Rule 16 | 89 | 83 | 34 | 1 | 45 | 86 | 333
16192 | 2019-08-05 | 2019-12-13 | 2020-08-20 | 2020-08-20 | COMP | 2020-10-13 | COMP | 2021-03-16 | COMP | 2021-03-17 | COMP | 2021-05-23 | COMP | Rule 15/16 | 91 | 175 | 38 | 104 | 2 | 48 | 453
16623 | 2019-08-05 | 2020-01-10 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-07 | COMP | 2020-06-30 | COMP | 2020-06-23 | COMP | 2020-10-05 | COMP | Rule 16 | 109 | 57 | 5 | 60 | 0 | 69 | 296
16847 | 2019-08-05 | 2020-01-21 | 2020-05-28 | 2020-05-28 | COMP | 2020-06-05 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2021-11-01 | COMP | Rule 16 | 115 | 91 | 7 | 40 | 1 | 317 | 566
17325 | 2019-08-05 | 2020-02-10 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-03 | COMP | 2020-10-28 | COMP | 2020-12-02 | COMP | 2021-02-12 | COMP | Rule 16 | 129 | 100 | 4 | 83 | 23 | 50 | 384
17412 | 2019-08-05 | 2020-02-12 | 2020-06-01 | 2020-06-01 | COMP | 2020-07-27 | COMP | 2020-08-03 | COMP | 2020-09-01 | COMP | 2021-12-03 | COMP | Rule 16 | 131 | 77 | 41 | 6 | 22 | 315 | 587
17979 | 2019-08-05 | 2020-03-06 | 2020-05-21 | 2020-05-21 | COMP | 2020-05-26 | COMP | 2020-06-02 | COMP | 2020-06-12 | COMP | 2020-07-14 | COMP | Rule 15/16 | 147 | 55 | 3 | 6 | 9 | 23 | 238
18383 | 2019-08-05 | 2020-03-22 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-18 | COMP | 2021-08-04 | COMP | 2021-08-04 | COMP | 2021-08-24 | COMP | Rule 16 | 157 | 99 | 8 | 242 | 1 | 15 | 518
19185 | 2019-08-05 | 2020-04-23 | 2020-08-13 | 2020-08-13 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-10-09 | COMP | 2020-10-22 | COMP | Rule 16 | 181 | 80 | 12 | 1 | 30 | 10 | 309
19871 | 2019-08-05 | 2020-05-27 | 2020-07-03 | 2020-07-03 | COMP | 2020-08-20 | COMP | 2020-10-08 | COMP | 2020-10-27 | COMP | 2020-12-23 | COMP | Rule 16 | 204 | 28 | 35 | 35 | 14 | 39 | 350
20641 | 2019-08-05 | 2020-06-30 | 2020-10-12 | 2020-10-12 | COMP | 2021-12-20 | COMP | 2021-12-20 | COMP | 2021-12-20 | COMP | 2022-02-01 | COMP | Rule 16 | 228 | 74 | 298 | 1 | 1 | 31 | 628
20988 | 2019-08-05 | 2020-07-16 | 2020-12-22 | 2020-12-22 | COMP | 2021-01-13 | COMP | 2022-03-24 | COMP | 2022-06-22 | COMP | 2022-06-28 | COMP | Rule 15/16 | 240 | 110 | 15 | 302 | 63 | 5 | 730
13758 | 2019-08-06 | 2019-08-09 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-09 | NOTN | 2019-10-09 | COMP | 2019-10-10 | COMP | 2019-11-25 | COMP | Other | 4 | 43 |  | 1 | 2 | 32 | 78
13879 | 2019-08-06 | 2019-08-14 | 2019-11-04 | 2019-11-04 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | Rule 16 | 7 | 58 | 12 | 1 | 64 | 1 | 138
13914 | 2019-08-06 | 2019-08-16 | 2019-10-09 | 2019-10-09 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-14 | COMP | 2020-08-27 | COMP | Rule 16 | 9 | 38 | 60 | 1 | 28 | 138 | 269
14017 | 2019-08-06 | 2019-08-21 | 2020-01-14 | 2020-01-14 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-04-29 | COMP | Rule 16 | 12 | 99 | 53 | 1 | 1 | 23 | 184
14042 | 2019-08-06 | 2019-08-22 | 2019-11-09 | 2019-11-09 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2019-12-03 | COMP | 2020-02-03 | COMP | Rule 16 | 13 | 56 | 13 | 1 | 2 | 42 | 123
14163 | 2019-08-06 | 2019-08-29 | 2019-11-05 | 2019-11-05 | COMP | 2019-12-05 | COMP | 2019-12-05 | COMP | 2020-05-31 | INPR | 2020-02-03 | COMP | Rule 16 | 18 | 48 | 20 | 1 |  |  | 123
14239 | 2019-08-06 | 2019-08-30 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-05-21 | COMP | 2020-06-23 | COMP | Rule 16 | 19 | 139 | 29 | 1 | 16 | 23 | 222
14424 | 2019-08-06 | 2019-09-10 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-13 | COMP | 2020-04-29 | COMP | 2020-05-18 | COMP | 2020-06-12 | COMP | Rule 16 | 25 | 27 | 20 | 115 | 14 | 19 | 215
14461 | 2019-08-06 | 2019-09-11 | 2020-05-08 | 2021-07-15 | COMP | 2022-02-09 | COMP | 2021-03-26 | COMP | 2022-03-29 | COMP | 2022-05-05 | COMP | Rule 16 | 26 | 166 | 145 |  | 255 | 28 | 693
14699 | 2019-08-06 | 2019-09-23 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-24 | COMP | 2020-01-27 | COMP | 2020-01-28 | COMP | 2020-02-15 | COMP | Rule 16 | 34 | 73 | 12 | 2 | 2 | 14 | 132
14764 | 2019-08-06 | 2019-09-26 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-16 | COMP | 2019-11-25 | COMP | 2019-11-26 | COMP | 2020-01-08 | COMP | Rule 16 | 37 | 10 | 6 | 28 | 2 | 28 | 106
14773 | 2019-08-06 | 2019-09-26 | 2019-10-11 | 2019-10-11 | COMP | 2019-10-23 | COMP | 2019-10-30 | COMP | 2019-11-08 | COMP | 2019-12-06 | COMP | Rule 16 | 37 | 12 | 9 | 6 | 8 | 18 | 85
14873 | 2019-08-06 | 2019-10-03 | 2020-02-18 | 2020-02-18 | COMP | 2020-02-24 | COMP | 2020-03-18 | COMP | 2020-02-13 | COMP | 2020-05-06 | COMP | Rule 15/16 | 42 | 92 | 5 | 18 | 0 | 36 | 189
14957 | 2019-08-06 | 2019-10-07 | 2019-11-17 | 2019-11-17 | COMP | 2019-12-12 | COMP | 2020-01-27 | COMP | 2020-01-10 | COMP | 2020-02-15 | COMP | Rule 16 | 44 | 29 | 17 | 30 | 0 | 15 | 132
15073 | 2019-08-06 | 2019-10-11 | 2019-12-20 | 2019-12-20 | COMP | 2021-02-27 | INPR | 2020-01-08 | COMP | 2021-02-27 | INPR | 2020-02-07 | COMP | Rule 16 | 48 | 48 |  | 12 |  |  | 127
15119 | 2019-08-06 | 2019-10-15 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-15 | COMP | 2019-11-15 | INPR | 2019-11-25 | COMP | 2019-12-30 | COMP | Rule 16 | 50 | 18 | 6 |  |  |  | 100
15291 | 2019-08-06 | 2019-10-24 | 2020-04-21 | 2020-04-21 | COMP | 2020-04-27 | COMP | 2020-08-10 | COMP | 2020-07-24 | COMP | 2020-09-03 | COMP | Rule 16 | 57 | 122 | 5 | 75 | 0 | 19 | 274
15569 | 2019-08-06 | 2019-11-07 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-02-18 | COMP | 2020-03-09 | COMP | Rule 16 | 67 | 17 | 40 | 1 | 12 | 15 | 147
16040 | 2019-08-06 | 2019-12-06 | 2020-02-02 | 2020-02-02 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-10-23 | COMP | 2020-11-05 | COMP | Rule 16 | 85 | 38 | 42 | 1 | 146 | 10 | 318
16178 | 2019-08-06 | 2019-12-16 | 2020-01-02 | 2020-01-02 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-02-08 | COMP | 2020-03-09 | COMP | Rule 16 | 91 | 12 | 14 | 1 | 13 | 20 | 147
16190 | 2019-08-06 | 2019-12-14 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-04 | COMP | 2020-06-04 | COMP | 2021-09-01 | COMP | 2021-10-08 | COMP | Rule 15/16 | 90 | 112 | 8 | 1 | 315 | 27 | 549
16315 | 2019-08-06 | 2019-12-19 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-24 | COMP | 2020-05-26 | COMP | 2020-06-24 | COMP | 2020-08-06 | COMP | Rule 16 | 94 | 64 | 25 | 22 | 22 | 32 | 254
19059 | 2019-08-06 | 2020-04-20 | 2020-06-05 | 2020-06-05 | COMP | 2021-09-02 | COMP | 2021-09-07 | COMP | 2021-11-10 | COMP | 2022-01-29 | COMP | Rule 16 | 177 | 34 | 315 | 3 | 47 | 54 | 625
19581 | 2019-08-06 | 2020-05-14 | 2020-11-02 | 2020-11-02 | COMP | 2021-01-12 | COMP | 2021-02-19 | COMP | 2021-03-01 | COMP | 2021-06-03 | COMP | Rule 15/16 | 195 | 121 | 47 | 27 | 7 | 68 | 460
23692 | 2019-08-06 | 2020-11-18 | 2021-06-24 | 2023-01-22 | COMP | 2023-03-07 | COMP | 2023-05-01 | COMP | 2023-03-28 | COMP | 2023-05-26 | COMP | Rule 15/16 | 326 | 150 | 31 | 40 | 0 | 20 | 958
25247 | 2019-08-06 | 2021-02-03 | 2022-03-09 | 2022-03-09 | COMP | 2022-04-28 | COMP | 2022-05-02 | COMP |  | INPR | 2022-12-23 | COMP | Rule 15/16 | 376 | 277 | 37 | 3 |  |  | 852
13802 | 2019-08-07 | 2019-08-13 | 2019-10-23 | 2019-10-23 | COMP | 2019-11-08 | COMP | 2020-01-16 | COMP | 2019-12-14 | COMP | 2020-01-20 | COMP | Rule 16 | 5 | 51 | 13 | 45 | 0 | 2 | 112
13824 | 2019-08-07 | 2019-08-12 | 2019-10-07 | 2019-12-06 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-11 | COMP | 2020-03-20 | COMP | Other | 4 | 40 | 21 | 1 | 25 | 28 | 155
13925 | 2019-08-07 | 2019-08-16 | 2019-10-01 | 2019-10-01 | COMP | 2019-10-15 | COMP | 2019-10-15 | COMP | 2020-03-01 | INPR | 2019-11-07 | COMP | Rule 16 | 8 | 32 | 11 | 1 |  |  | 66
13937 | 2019-08-07 | 2019-08-16 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-11 | COMP | 2020-07-09 | COMP | Rule 16 | 8 | 113 | 8 | 1 | 2 | 106 | 233
13972 | 2019-08-07 | 2019-08-20 | 2019-09-21 | 2019-09-21 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-01-24 | COMP | Rule 16 | 10 | 23 | 58 | 1 | 1 | 27 | 116
14052 | 2019-08-07 | 2019-08-23 | 2019-10-16 | 2019-10-31 | COMP | 2019-11-06 | COMP | 2019-11-07 | COMP | 2019-11-15 | COMP | 2020-01-10 | COMP | Rule 16 | 13 | 38 | 5 | 2 | 6 | 37 | 107
14127 | 2019-08-07 | 2019-08-26 | 2020-01-28 | 2020-10-29 | COMP | 2020-11-13 | COMP | 2021-02-17 | COMP | 2021-05-20 | COMP | 2021-06-28 | COMP | Rule 15/16 | 14 | 105 | 11 | 63 | 67 | 27 | 476
14201 | 2019-08-07 | 2019-08-29 | 2019-10-04 | 2019-10-04 | COMP | 2019-10-21 | COMP | 2019-10-22 | COMP | 2019-11-26 | COMP | 2019-12-05 | COMP | Rule 16 | 17 | 26 | 12 | 2 | 25 | 6 | 83
14230 | 2019-08-07 | 2019-08-29 | 2020-01-17 | 2020-01-17 | COMP | 2021-01-26 | COMP | 2021-01-27 | COMP | 2021-01-27 | COMP | 2021-03-06 | COMP | Rule 16 | 17 | 96 | 258 | 2 | 1 | 27 | 396
14268 | 2019-08-07 | 2019-09-03 | 2019-10-16 | 2019-10-16 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2020-11-30 | COMP | 2020-12-07 | COMP | Rule 16 | 19 | 32 | 13 | 1 | 270 | 6 | 336
14493 | 2019-08-07 | 2019-09-13 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-09-15 | COMP | 2020-09-23 | COMP | Rule 16 | 27 | 97 | 33 | 1 | 126 | 7 | 286
14616 | 2019-08-07 | 2019-09-19 | 2020-02-03 | 2021-08-07 | COMP | 2021-08-25 | COMP | 2021-09-09 | COMP | 2020-07-20 | COMP | 2022-07-26 | COMP | Rule 15/16 | 31 | 92 | 13 | 11 | 0 | 221 | 747
14757 | 2019-08-07 | 2019-09-25 | 2019-12-17 | 2019-12-17 | COMP | 2020-02-07 | COMP | 2020-04-06 | COMP | 2020-06-15 | COMP | 2020-08-11 | COMP | Rule 15/16 | 35 | 57 | 36 | 41 | 50 | 42 | 256
14855 | 2019-08-07 | 2019-09-30 | 2019-10-10 | 2019-10-10 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2020-01-22 | COMP | 2020-02-19 | COMP | Rule 16 | 38 | 9 | 24 | 1 | 46 | 20 | 133
14953 | 2019-08-07 | 2019-10-07 | 2019-12-12 | 2020-02-25 | COMP | 2020-03-11 | COMP | 2020-03-17 | COMP | 2020-02-04 | COMP | 2020-05-30 | COMP | Rule 15/16 | 43 | 46 | 12 | 5 | 0 | 53 | 204
15060 | 2019-08-07 | 2019-10-10 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-05-15 | COMP | 2020-05-04 | COMP | Rule 16 | 46 | 74 | 43 | 1 | 35 |  | 186
15140 | 2019-08-07 | 2019-10-15 | 2019-12-16 | 2019-12-16 | COMP | 2020-03-20 | COMP | 2020-05-16 | COMP | 2020-07-08 | COMP | 2020-07-14 | COMP | Rule 16 | 49 | 42 | 66 | 41 | 37 | 5 | 236
15271 | 2019-08-07 | 2019-10-23 | 2019-12-06 | 2019-12-06 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2019-12-16 | COMP | 2019-12-18 | COMP | Rule 16 | 55 | 30 | 3 | 1 | 5 | 3 | 92
15273 | 2019-08-07 | 2019-10-24 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | Rule 16 | 56 | 25 | 13 | 1 | 13 | 1 | 104
15367 | 2019-08-07 | 2019-10-29 | 2020-03-04 | 2020-03-04 | COMP | 2020-04-14 | COMP | 2020-05-29 | INPR | 2023-04-30 | CANC | 2020-06-26 | COMP | Rule 16 | 59 | 85 | 30 |  |  |  | 224
15594 | 2019-08-07 | 2019-11-08 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2020-04-14 | COMP | 2020-06-16 | COMP | Rule 16 | 67 | 75 | 9 | 1 | 24 | 45 | 216
15654 | 2019-08-07 | 2019-11-14 | 2020-02-06 | 2021-08-11 | COMP | 2021-08-24 | COMP | 2021-10-01 | COMP | 2022-08-02 | COMP | 2022-09-15 | COMP | Rule 15/16 | 70 | 56 | 10 | 28 | 210 | 32 | 783
15801 | 2019-08-07 | 2019-11-20 | 2020-03-03 | 2020-03-03 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-09-23 | COMP | 2020-10-30 | COMP | Rule 16 | 74 | 69 | 39 | 1 | 107 | 28 | 313
16610 | 2019-08-07 | 2020-01-10 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-24 | COMP | 2020-07-29 | COMP | 2020-12-01 | COMP | 2021-01-05 | COMP | Rule 16 | 107 | 65 | 10 | 68 | 86 | 24 | 355
16611 | 2019-08-07 | 2020-01-10 | 2020-04-21 | 2020-10-13 | COMP | 2020-10-20 | COMP | 2021-06-10 | COMP | 2021-08-19 | COMP | 2021-09-15 | COMP | Rule 16 | 107 | 71 | 6 | 160 | 50 | 19 | 531
17232 | 2019-08-07 | 2020-02-05 | 2020-03-04 | 2020-03-04 | COMP | 2020-03-24 | COMP | 2020-03-27 | COMP | 2020-03-24 | COMP | 2020-04-04 | COMP | Rule 16 | 124 | 20 | 15 | 4 | 0 | 6 | 165
17393 | 2019-08-07 | 2020-02-12 | 2020-06-19 | 2020-06-19 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2020-11-25 | COMP | 2021-01-08 | COMP | Rule 16 | 129 | 91 | 59 | 1 | 54 | 29 | 358
17438 | 2019-08-07 | 2020-02-13 | 2020-07-30 | 2020-10-23 | COMP | 2020-11-30 | COMP | 2021-03-19 | COMP | 2022-12-09 | COMP | 2023-04-15 | COMP | Rule 16 | 130 | 119 | 24 | 76 | 436 | 87 | 927
17801 | 2019-08-07 | 2020-02-27 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-22 | COMP | 2020-09-03 | COMP | 2021-07-27 | COMP | 2021-09-01 | COMP | Rule 16 | 139 | 38 | 25 | 74 | 224 | 27 | 522
18629 | 2019-08-07 | 2020-03-31 | 2020-07-06 | 2021-03-12 | COMP | 2021-03-30 | COMP | 2021-04-10 | COMP | 2021-06-22 | COMP | 2021-07-19 | COMP | Rule 16 | 162 | 69 | 13 | 9 | 51 | 19 | 490
19029 | 2019-08-07 | 2020-04-17 | 2020-06-03 | 2020-07-01 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-07-21 | COMP | 2020-09-01 | COMP | Rule 16 | 175 | 33 | 12 | 1 | 4 | 31 | 271
19472 | 2019-08-07 | 2020-05-08 | 2020-10-02 | 2021-04-21 | COMP | 2021-10-07 | COMP | 2021-10-08 | COMP | 2022-05-23 | COMP | 2022-10-05 | COMP | Rule 15/16 | 190 | 104 | 119 | 2 | 157 | 94 | 797
13809 | 2019-08-08 | 2019-08-12 | 2019-12-20 | 2019-12-20 | COMP | 2020-06-22 | COMP | 2020-10-27 | COMP | 2021-01-06 | COMP | 2021-04-02 | COMP | Rule 15/16 | 3 | 91 | 127 | 91 | 47 | 61 | 415
13883 | 2019-08-08 | 2019-08-14 | 2019-10-15 | 2019-10-15 | COMP | 2020-01-08 | COMP | 2020-03-12 | COMP | 2020-03-31 | COMP | 2020-04-10 | COMP | Rule 15/16 | 5 | 44 | 57 | 45 | 14 | 9 | 169
13908 | 2019-08-08 | 2019-08-16 | 2019-12-11 | 2020-02-21 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-08-25 | COMP | 2020-09-01 | COMP | Rule 16 | 7 | 80 | 95 | 1 | 38 | 6 | 270
13946 | 2019-08-08 | 2019-08-17 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-16 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-06-03 | COMP | Rule 16 | 7 | 83 | 21 | 22 | 1 | 76 | 206
13948 | 2019-08-08 | 2019-08-17 | 2020-06-09 | 2020-12-03 | COMP | 2021-03-16 | COMP | 2021-03-23 | COMP | 2021-06-03 | COMP | 2021-09-14 | COMP | Rule 15/16 | 7 | 203 | 70 | 6 | 52 | 72 | 529
13963 | 2019-08-08 | 2019-08-20 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | Rule 16 | 9 | 59 | 24 | 1 | 28 | 1 | 117
14157 | 2019-08-08 | 2019-08-27 | 2019-09-18 | 2019-09-18 | COMP | 2019-09-24 | COMP | 2019-09-25 | COMP | 2019-10-07 | COMP | 2019-10-23 | COMP | Rule 16 | 14 | 16 | 5 | 2 | 9 | 13 | 54
14171 | 2019-08-08 | 2019-08-28 | 2019-09-18 | 2019-09-18 | COMP | 2019-09-24 | COMP | 2019-09-24 | INPR | 2019-10-07 | COMP | 2019-10-23 | COMP | Rule 16 | 15 | 15 | 5 |  |  |  | 54
14392 | 2019-08-08 | 2019-09-09 | 2020-04-05 | 2020-04-14 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2021-05-27 | COMP | 2021-06-29 | COMP | Rule 16 | 22 | 143 | 42 | 1 | 243 | 23 | 476
14634 | 2019-08-08 | 2019-09-20 | 2020-07-07 | 2020-07-07 | COMP | 2021-06-02 | COMP | 2021-08-13 | COMP | 2021-10-22 | COMP | 2022-02-23 | COMP | Rule 15/16 | 31 | 200 | 228 | 52 | 50 | 84 | 640
14662 | 2019-08-08 | 2019-09-21 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2021-04-14 | COMP | 2021-05-04 | COMP | Rule 15/16 | 31 | 108 | 27 | 1 | 259 | 15 | 437
14715 | 2019-08-08 | 2019-09-24 | 2020-03-07 | 2020-03-07 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-06-19 | COMP | 2020-07-15 | COMP | Rule 16 | 33 | 112 | 37 | 1 | 38 | 19 | 236
14821 | 2019-08-08 | 2019-09-30 | 2019-10-14 | 2019-10-14 | COMP | 2019-11-20 | COMP | 2019-11-20 | COMP | 2019-11-21 | COMP | 2020-01-06 | COMP | Rule 16 | 37 | 11 | 27 | 1 | 2 | 29 | 102
14940 | 2019-08-08 | 2019-10-04 | 2020-01-28 | 2021-03-12 | COMP | 2021-04-26 | COMP | 2021-06-29 | COMP | 2021-06-29 | COMP | 2021-10-11 | COMP | Rule 16 | 41 | 77 | 32 | 46 | 1 | 73 | 548
15391 | 2019-08-08 | 2019-10-30 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-01-03 | COMP | 2020-01-06 | COMP | Rule 16 | 59 | 35 | 8 | 1 | 2 | 2 | 102
15534 | 2019-08-08 | 2019-11-07 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-23 | COMP | 2020-01-06 | COMP | 2020-04-21 | COMP | 2020-06-29 | COMP | Rule 16 | 65 | 15 | 16 | 9 | 75 | 49 | 224
15560 | 2019-08-08 | 2019-11-08 | 2020-02-06 | 2020-02-06 | COMP | 2020-02-26 | COMP | 2020-03-31 | COMP | 2023-11-12 | INPR | 2020-07-08 | COMP | Rule 15/16 | 66 | 59 | 14 | 25 |  |  | 231
15955 | 2019-08-08 | 2019-12-02 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-20 | COMP | 2020-07-29 | COMP | 2020-07-07 | COMP | 2020-09-04 | COMP | Rule 16 | 79 | 74 | 24 | 72 | 0 | 28 | 273
15969 | 2019-08-08 | 2019-12-03 | 2020-01-18 | 2020-01-18 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-02-24 | COMP | 2020-03-05 | COMP | Rule 16 | 80 | 32 | 21 | 1 | 4 | 9 | 143
16171 | 2019-08-08 | 2019-12-12 | 2020-04-06 | 2020-04-06 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-07-16 | COMP | 2020-09-24 | COMP | Rule 16 | 87 | 79 | 26 | 1 | 48 | 50 | 286
16176 | 2019-08-08 | 2019-12-13 | 2020-05-27 | 2020-05-27 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-09-22 | COMP | 2020-10-30 | COMP | Rule 16 | 88 | 114 | 38 | 1 | 47 | 29 | 312
16213 | 2019-08-08 | 2019-12-16 | 2020-04-29 | 2020-04-30 | COMP | 2020-07-30 | COMP | 2020-08-03 | COMP | 2020-10-02 | COMP | 2020-10-06 | COMP | Rule 16 | 89 | 94 | 65 | 3 | 44 | 3 | 294
16452 | 2019-08-08 | 2019-12-31 | 2020-04-05 | 2020-04-05 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-08-21 | COMP | 2020-11-23 | COMP | Rule 15/16 | 99 | 66 | 55 | 1 | 45 | 65 | 327
16783 | 2019-08-08 | 2020-01-15 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-13 | COMP | 2020-07-13 | COMP | 2020-07-11 | COMP | 2020-10-07 | COMP | Rule 16 | 109 | 59 | 26 | 43 | 0 | 62 | 295
17781 | 2019-08-08 | 2020-02-27 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-04-17 | COMP | 2020-06-30 | COMP | Rule 16 | 138 | 21 | 8 | 1 | 10 | 52 | 225
17812 | 2019-08-08 | 2020-02-28 | 2020-06-01 | 2020-06-01 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2021-04-06 | COMP | 2021-04-26 | COMP | Other | 139 | 66 | 37 | 1 | 178 | 15 | 431
17815 | 2019-08-08 | 2020-02-28 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2021-04-12 | COMP | 2021-05-08 | COMP | Other | 139 | 53 | 35 | 1 | 197 | 20 | 440
18876 | 2019-08-08 | 2020-04-09 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP |  | INPR | 2020-08-13 | COMP | Rule 16 | 168 | 55 | 5 | 1 |  |  | 257
19614 | 2019-08-08 | 2020-05-15 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-09-03 | COMP | 2020-11-06 | COMP | Rule 16 | 194 | 15 | 8 | 1 | 58 | 46 | 317
21968 | 2019-08-08 | 2020-09-04 | 2020-11-04 | 2020-11-04 | COMP | 2022-04-01 | COMP | 2022-04-06 | COMP | 2022-05-20 | COMP | 2022-08-24 | COMP | Rule 16 | 273 | 43 | 353 | 4 | 33 | 66 | 767
13861 | 2019-08-09 | 2019-08-13 | 2019-09-17 | 2019-09-17 | COMP | 2019-09-25 | COMP | 2019-11-05 | COMP | 2019-10-17 | COMP | 2019-12-18 | COMP | Rule 16 | 3 | 25 | 7 | 30 | 0 | 29 | 90
13880 | 2019-08-09 | 2019-08-14 | 2020-04-10 | 2020-04-10 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2020-12-14 | COMP | Rule 15/16 | 4 | 165 | 145 | 1 | 1 | 28 | 339
14190 | 2019-08-09 | 2019-08-28 | 2019-09-07 | 2019-09-07 | COMP | 2019-10-11 | COMP | 2019-10-11 | COMP | 2020-04-26 | INPR | 2019-12-20 | COMP | Rule 16 | 14 | 7 | 25 | 1 |  |  | 92
14257 | 2019-08-09 | 2019-08-31 | 2019-09-06 | 2019-09-06 | COMP | 2019-12-11 | COMP | 2019-12-11 | COMP | 2022-07-16 | INPR | 2020-06-10 | COMP | Rule 16 | 16 | 4 | 66 | 1 |  |  | 210
14380 | 2019-08-09 | 2019-09-09 | 2020-01-10 | 2020-01-10 | COMP | 2020-02-04 | COMP | 2020-02-06 | COMP | 2020-02-24 | COMP | 2020-03-30 | COMP | Rule 16 | 21 | 85 | 17 | 3 | 12 | 26 | 159
14469 | 2019-08-09 | 2019-09-11 | 2020-01-27 | 2020-01-27 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-07-22 | COMP | 2020-08-10 | COMP | Rule 16 | 23 | 93 | 58 | 1 | 69 | 14 | 253
14593 | 2019-08-09 | 2019-09-17 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-22 | COMP | 2019-12-03 | COMP | 2020-01-10 | COMP | 2020-01-10 | COMP | Rule 16 | 27 | 38 | 11 | 6 | 27 | 1 | 105
14673 | 2019-08-09 | 2019-09-23 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-10 | COMP | 2019-12-10 | COMP | 2020-03-05 | COMP | 2020-05-06 | COMP | Rule 16 | 31 | 48 | 7 | 1 | 59 | 45 | 186
14707 | 2019-08-09 | 2019-09-24 | 2020-01-10 | 2020-01-10 | REQD | 2020-02-03 | REQD | 2020-02-03 | COMP | 2020-03-10 | COMP | 2020-05-07 | COMP | Rule 16 | 32 |  |  |  | 26 | 43 | 187
14712 | 2019-08-09 | 2019-09-24 | 2019-11-04 | 2019-11-04 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-03-24 | COMP | 2020-03-17 | COMP | Rule 16 | 32 | 30 | 62 | 1 | 34 |  | 150
14776 | 2019-08-09 | 2019-09-26 | 2020-01-14 | 2021-10-05 | COMP | 2021-10-20 | COMP | 2021-10-21 | COMP | 2021-12-20 | COMP | 2022-03-03 | COMP | Rule 16 | 34 | 74 | 12 | 2 | 40 | 52 | 645
15213 | 2019-08-09 | 2019-10-23 | 2020-03-01 | 2020-03-01 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-05-11 | COMP | 2020-05-29 | COMP | Rule 15/16 | 53 | 86 | 11 | 1 | 41 | 14 | 202
15510 | 2019-08-09 | 2019-11-05 | 2020-01-10 | 2021-04-01 | COMP | 2021-04-21 | COMP | 2021-04-21 | COMP | 2021-09-01 | COMP | 2021-11-20 | COMP | Rule 16 | 62 | 44 | 15 | 1 | 94 | 56 | 575
15626 | 2019-08-09 | 2019-11-12 | 2020-02-28 | 2020-03-04 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-04-27 | COMP | 2020-05-12 | COMP | Rule 16 | 66 | 73 | 21 | 1 | 19 | 12 | 190
15647 | 2019-08-09 | 2019-11-13 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-03-30 | COMP | 2020-04-14 | COMP | Rule 16 | 67 | 61 | 32 | 1 | 2 | 12 | 170
15861 | 2019-08-09 | 2019-11-25 | 2020-03-13 | 2020-03-13 | COMP | 2020-03-23 | COMP | 2020-04-08 | COMP | 2020-05-26 | COMP | 2020-06-23 | COMP | Rule 16 | 75 | 74 | 7 | 13 | 34 | 21 | 219
16267 | 2019-08-09 | 2019-12-18 | 2020-03-27 | 2020-03-27 | COMP | 2021-01-25 | COMP | 2021-01-25 | COMP | 2021-05-25 | COMP | 2021-06-26 | COMP | Rule 16 | 90 | 69 | 209 | 1 | 86 | 23 | 473
16276 | 2019-08-09 | 2019-12-18 | 2020-01-27 | 2020-01-27 | COMP | 2020-03-12 | COMP | 2020-03-19 | COMP | 2020-09-22 | COMP | 2020-10-05 | COMP | Rule 16 | 90 | 26 | 33 | 6 | 132 | 10 | 292
16296 | 2019-08-09 | 2019-12-19 | 2020-08-20 | 2020-12-14 | COMP | 2021-01-28 | COMP | 2021-03-08 | COMP | 2021-03-12 | COMP | 2021-04-09 | COMP | Rule 15/16 | 91 | 171 | 31 | 27 | 5 | 21 | 419
16339 | 2019-08-09 | 2019-12-20 | 2020-03-22 | 2020-03-22 | COMP | 2020-06-12 | COMP | 2020-09-28 | COMP | 2020-09-11 | COMP | 2020-10-30 | COMP | Rule 15/16 | 92 | 62 | 59 | 76 | 0 | 25 | 311
16574 | 2019-08-09 | 2020-01-08 | 2020-02-05 | 2020-02-05 | COMP | 2020-03-16 | COMP | 2020-04-23 | COMP | 2020-05-26 | COMP | 2020-07-01 | COMP | Rule 16 | 103 | 20 | 28 | 29 | 23 | 27 | 225
16914 | 2019-08-09 | 2020-01-23 | 2020-10-20 | 2020-10-20 | COMP | 2021-06-03 | COMP | 2021-06-03 | COMP | 2021-06-23 | COMP | 2021-08-26 | COMP | Rule 15/16 | 113 | 191 | 155 | 1 | 15 | 46 | 516
16985 | 2019-08-09 | 2020-01-29 | 2020-08-17 | 2020-08-17 | COMP | 2022-02-08 | COMP | 2022-02-08 | COMP | 2022-02-08 | COMP | 2022-03-30 | COMP | Rule 15/16 | 117 | 142 | 372 | 1 | 1 | 36 | 664
17243 | 2019-08-09 | 2020-02-05 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-06-01 | COMP | 2020-07-08 | COMP | Rule 16 | 122 | 15 | 23 | 1 | 46 | 28 | 230
18143 | 2019-08-09 | 2020-03-12 | 2020-06-17 | 2020-06-17 | COMP | 2020-06-26 | COMP | 2020-08-14 | COMP | 2020-06-09 | COMP | 2020-10-20 | COMP | Rule 16 | 147 | 69 | 8 | 36 | 0 | 47 | 303
18560 | 2019-08-09 | 2020-03-28 | 2020-08-10 | 2020-08-10 | COMP | 2021-03-02 | COMP | 2021-05-03 | COMP | 2021-08-30 | COMP | 2021-10-05 | COMP | Rule 16 | 158 | 95 | 139 | 45 | 84 | 26 | 543
18718 | 2019-08-09 | 2020-04-04 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-15 | COMP | 2020-08-20 | COMP | 2022-01-30 | INPR | 2020-12-04 | COMP | Rule 16 | 163 | 32 | 19 | 49 |  |  | 333
13839 | 2019-08-12 | 2019-08-13 | 2019-10-03 | 2019-11-04 | COMP | 2019-11-08 | COMP | 2019-11-08 | COMP | 2019-12-03 | COMP | 2019-12-10 | COMP | Rule 16 | 2 | 37 | 5 | 1 | 15 | 6 | 83
14073 | 2019-08-12 | 2019-08-23 | 2021-02-23 | 2021-03-03 | COMP | 2021-06-08 | COMP | 2021-07-02 | COMP | 2022-11-16 | COMP | 2023-02-02 | COMP | Rule 15/16 | 10 | 376 | 69 | 19 | 347 | 52 | 874
14106 | 2019-08-12 | 2019-08-27 | 2019-10-02 | 2019-10-02 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2019-10-23 | COMP | 2019-11-06 | COMP | Rule 16 | 12 | 26 | 12 | 1 | 5 | 11 | 62
14149 | 2019-08-12 | 2019-08-28 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-19 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-05-11 | COMP | Rule 16 | 13 | 95 | 24 | 32 | 1 | 28 | 188
14206 | 2019-08-12 | 2019-08-29 | 2019-09-24 | 2019-09-24 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-03-24 | COMP | 2020-03-30 | COMP | Rule 15/16 | 14 | 18 | 73 | 1 | 52 | 5 | 158
14260 | 2019-08-12 | 2019-09-03 | 2019-10-24 | 2019-10-24 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-02-18 | COMP | 2020-05-28 | COMP | Rule 16 | 16 | 38 | 23 | 1 | 55 | 72 | 200
14343 | 2019-08-12 | 2019-09-05 | 2019-12-08 | 2019-12-30 | COMP | 2022-03-28 | COMP | 2022-06-10 | COMP | 2022-05-06 | COMP | 2022-07-02 | COMP | Rule 16 | 18 | 64 | 566 | 54 | 0 | 15 | 728
14345 | 2019-08-12 | 2019-09-05 | 2020-01-23 | 2020-01-23 | COMP | 2022-03-29 | COMP | 2022-03-29 | COMP | 2022-05-06 | COMP | 2022-07-07 | COMP | Rule 16 | 18 | 95 | 551 | 1 | 29 | 42 | 731
14368 | 2019-08-12 | 2019-09-06 | 2019-12-14 | 2019-12-14 | COMP | 2020-01-24 | COMP | 2020-02-14 | COMP | 2020-06-01 | COMP | 2020-07-28 | COMP | Rule 16 | 19 | 68 | 27 | 16 | 75 | 42 | 243
14372 | 2019-08-12 | 2019-09-06 | 2019-12-14 | 2020-02-03 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2022-01-30 | INPR | 2020-06-11 | COMP | Rule 16 | 19 | 68 | 29 | 1 |  |  | 210
14373 | 2019-08-12 | 2019-09-06 | 2019-11-19 | 2019-11-21 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-01-07 | COMP | 2020-02-08 | COMP | Rule 16 | 19 | 52 | 18 | 1 | 13 | 23 | 123
14459 | 2019-08-12 | 2019-09-11 | 2020-01-06 | 2020-01-06 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-02-13 | COMP | 2020-03-18 | COMP | Rule 16 | 22 | 79 | 16 | 1 | 13 | 24 | 150
14481 | 2019-08-12 | 2019-09-11 | 2019-11-18 | 2019-11-18 | COMP | 2019-11-27 | COMP | 2019-12-11 | COMP | 2020-04-13 | COMP | 2020-04-20 | COMP | Rule 16 | 22 | 48 | 8 | 9 | 85 | 6 | 173
14510 | 2019-08-12 | 2019-09-13 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2020-01-13 | COMP | 2020-01-29 | COMP | Rule 16 | 24 | 34 | 6 | 1 | 44 | 12 | 116
14547 | 2019-08-12 | 2019-09-16 | 2020-02-24 | 2020-02-24 | COMP | 2020-07-06 | COMP | 2020-08-27 | COMP | 2021-10-23 | INPR | 2020-10-08 | COMP | Rule 16 | 25 | 109 | 95 | 39 |  |  | 294
14615 | 2019-08-12 | 2019-09-19 | 2020-03-14 | 2020-03-14 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP |  |  | 2022-04-14 | COMP | Rule 16 | 28 | 120 | 162 | 1 |  |  | 674
14765 | 2019-08-12 | 2019-09-26 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-21 | COMP | 2020-02-10 | COMP | 2020-02-05 | COMP | 2020-04-25 | COMP | Rule 16 | 33 | 81 | 20 |  | 0 | 54 | 177
14930 | 2019-08-12 | 2019-10-05 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-19 | COMP | 2020-03-17 | COMP | 2020-06-05 | COMP | 2020-07-17 | COMP | Rule 16 | 39 | 79 | 13 | 20 | 58 | 31 | 236
14949 | 2019-08-12 | 2019-10-06 | 2020-03-04 | 2020-03-04 | COMP | 2020-03-13 | COMP | 2020-09-03 | COMP | 2020-09-03 | COMP | 2020-09-22 | COMP | Rule 16 | 39 | 101 | 8 | 124 | 1 | 13 | 282
14990 | 2019-08-12 | 2019-10-08 | 2019-12-04 | 2020-03-09 | COMP | 2020-03-19 | COMP | 2020-09-04 | COMP | 2020-09-22 | COMP | 2020-09-26 | COMP | Rule 16 | 41 | 39 | 9 | 121 | 12 | 4 | 285
15629 | 2019-08-12 | 2019-11-12 | 2019-11-26 | 2019-11-26 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-03-27 | COMP | 2020-04-01 | COMP | Rule 16 | 65 | 11 | 34 | 1 | 50 | 4 | 160
15634 | 2019-08-12 | 2019-11-13 | 2020-01-15 | 2020-01-15 | COMP | 2021-03-12 | COMP | 2021-05-14 | COMP | 2021-06-08 | COMP | 2021-07-07 | COMP | Rule 16 | 66 | 42 | 292 | 46 | 17 | 21 | 479
15977 | 2019-08-12 | 2019-12-04 | 2020-02-24 | 2020-10-31 | COMP | 2020-11-24 | COMP | 2021-02-01 | COMP | 2021-01-29 | COMP | 2021-04-09 | COMP | Rule 16 | 79 | 55 | 16 | 45 | 0 | 49 | 418
16058 | 2019-08-12 | 2019-12-07 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-09-17 | COMP | 2020-10-08 | COMP | Rule 16 | 81 | 137 | 12 | 1 | 51 | 16 | 294
17101 | 2019-08-12 | 2020-01-30 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-25 | COMP | 2020-04-02 | COMP | Rule 16 | 117 | 20 | 3 | 1 | 18 | 7 | 161
18119 | 2019-08-12 | 2020-03-11 | 2020-06-01 | 2020-06-01 | COMP | 2020-08-27 | COMP | 2021-02-11 | COMP | 2021-10-08 | COMP | 2022-02-17 | COMP | Rule 16 | 145 | 58 | 64 | 114 | 168 | 91 | 635
18142 | 2019-08-12 | 2020-03-12 | 2020-06-16 | 2020-06-16 | COMP | 2020-06-29 | COMP | 2020-09-03 | COMP | 2020-09-21 | COMP | 2020-10-29 | COMP | Rule 16 | 146 | 68 | 10 | 49 | 12 | 29 | 309
20040 | 2019-08-12 | 2020-06-02 | 2020-07-03 | 2020-07-03 | COMP | 2022-01-31 | INPR | 2020-08-24 | COMP | 2022-01-31 | INPR | 2020-08-27 | COMP | Rule 16 | 203 | 24 |  | 37 |  |  | 265
13872 | 2019-08-13 | 2019-08-14 | 2019-12-22 | 2020-02-07 | COMP | 2020-02-13 | COMP | 2020-06-30 | COMP | 2021-01-20 | COMP | 2021-03-12 | COMP | Rule 16 | 2 | 89 | 5 | 97 | 140 | 37 | 397
14113 | 2019-08-13 | 2019-08-26 | 2019-11-14 | 2019-11-27 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-05-20 | COMP | 2020-06-29 | COMP | Rule 15/16 | 10 | 57 | 66 | 1 | 55 | 28 | 221
14177 | 2019-08-13 | 2019-08-28 | 2019-11-19 | 2019-11-19 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-02-18 | COMP | 2020-05-06 | COMP | Rule 16 | 12 | 58 | 66 | 1 | 0 | 51 | 184
14367 | 2019-08-13 | 2019-09-06 | 2019-10-10 | 2019-11-05 | COMP | 2019-11-13 | COMP | 2019-10-17 | COMP | 2019-10-17 | COMP | 2020-02-20 | COMP | Rule 16 | 18 | 25 | 6 |  | 1 | 84 | 130
14407 | 2019-08-13 | 2019-09-09 | 2019-12-27 | 2020-06-10 | COMP | 2020-06-12 | COMP | 2020-06-19 | COMP | 2021-04-07 | COMP | 2021-06-16 | COMP | Rule 15/16 | 19 | 76 | 3 | 6 | 201 | 50 | 464
14430 | 2019-08-13 | 2019-09-09 | 2019-10-19 | 2019-10-19 | COMP | 2019-10-30 | COMP | 2019-12-18 | COMP | 2021-02-28 | COMP | 2021-04-02 | COMP | Rule 16 | 19 | 30 | 8 | 33 | 300 | 25 | 412
14520 | 2019-08-13 | 2019-09-13 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-24 | COMP | 2020-04-06 | COMP | 2020-08-12 | COMP | 2020-09-16 | COMP | Rule 16 | 23 | 95 | 15 | 31 | 92 | 25 | 277
14530 | 2019-08-13 | 2019-09-16 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-17 | COMP | 2020-03-10 | COMP | 2020-04-06 | COMP | 2020-06-05 | COMP | Rule 16 | 24 | 71 | 14 | 36 | 20 | 44 | 205
14532 | 2019-08-13 | 2019-09-16 | 2019-12-28 | 2019-12-28 | COMP | 2020-05-05 | COMP | 2020-06-11 | COMP | 2020-06-12 | COMP | 2020-08-08 | COMP | Rule 16 | 24 | 71 | 89 | 27 | 2 | 41 | 250
14540 | 2019-08-13 | 2019-09-16 | 2020-01-17 | 2020-07-21 | COMP | 2020-10-09 | COMP | 2020-12-15 | COMP | 2020-11-30 | COMP | 2022-06-15 | COMP | Rule 15/16 | 24 | 85 | 58 | 45 | 0 | 379 | 716
14558 | 2019-08-13 | 2019-09-16 | 2020-01-13 | 2020-01-13 | COMP | 2020-01-29 | COMP | 2020-01-30 | COMP | 2020-06-09 | COMP | 2020-08-06 | COMP | Rule 16 | 24 | 81 | 12 | 2 | 92 | 43 | 249
14674 | 2019-08-13 | 2019-09-23 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-01-10 | COMP | 2020-01-15 | COMP | Rule 16 | 29 | 49 | 10 | 1 | 18 | 4 | 106
14797 | 2019-08-13 | 2019-09-27 | 2019-11-27 | 2019-11-27 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-01-29 | COMP | 2020-04-15 | COMP | Rule 15/16 | 33 | 43 | 40 | 1 | 2 | 55 | 169
14841 | 2019-08-13 | 2019-09-30 | 2020-01-22 | 2020-01-22 | COMP | 2020-01-28 | COMP | 2020-02-04 | COMP | 2023-04-30 | INPR | 2020-02-28 | COMP | Rule 16 | 34 | 77 | 5 | 6 |  |  | 136
14964 | 2019-08-13 | 2019-10-08 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-02-03 | COMP | 2020-02-07 | COMP | Rule 16 | 40 | 48 | 23 | 1 | 10 | 5 | 122
14986 | 2019-08-13 | 2019-10-08 | 2020-02-06 | 2020-08-31 | COMP | 2021-02-19 | COMP | 2020-09-15 | COMP | 2020-10-26 | COMP | 2021-01-08 | COMP | Rule 16 | 40 | 82 | 117 |  | 30 | 50 | 354
15011 | 2019-08-13 | 2019-10-09 | 2019-12-18 | 2019-12-18 | COMP | 2019-12-30 | COMP | 2020-01-28 | COMP | 2020-01-29 | COMP | 2020-02-28 | COMP | Rule 16 | 41 | 48 | 8 | 20 | 2 | 22 | 136
15637 | 2019-08-13 | 2019-11-13 | 2020-02-07 | 2020-02-07 | COMP | 2020-03-20 | COMP | 2020-08-28 | COMP | 2022-05-05 | COMP | 2022-08-06 | COMP | Rule 15/16 | 65 | 58 | 30 | 115 | 424 | 64 | 751
15661 | 2019-08-13 | 2019-11-14 | 2020-02-24 | 2020-02-24 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2021-09-17 | COMP | 2022-09-08 | COMP | Rule 15/16 | 66 | 67 | 60 | 1 | 339 | 246 | 774
16236 | 2019-08-13 | 2019-12-17 | 2020-01-25 | 2020-01-25 | COMP | 2020-02-21 | COMP | 2020-06-24 | COMP | 2020-08-05 | COMP | 2020-09-14 | COMP | Rule 16 | 87 | 26 | 19 | 88 | 31 | 28 | 275
16243 | 2019-08-13 | 2019-12-17 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-04-23 | COMP | 2020-04-27 | COMP | Rule 16 | 87 | 30 | 8 | 1 | 53 | 3 | 177
16493 | 2019-08-13 | 2020-01-03 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-05-29 | COMP | 2020-06-12 | COMP | Rule 16 | 98 | 65 | 5 | 1 | 35 | 11 | 210
17655 | 2019-08-13 | 2020-02-24 | 2020-04-26 | 2020-04-26 | COMP | 2020-07-31 | COMP | 2021-02-02 | COMP | 2021-02-02 | COMP | 2021-03-18 | COMP | Rule 16 | 132 | 45 | 69 | 126 | 1 | 32 | 401
19523 | 2019-08-13 | 2020-05-11 | 2020-08-03 | 2020-08-03 | COMP | 2020-09-04 | COMP | 2020-09-04 | COMP | 2020-09-08 | COMP | 2020-10-16 | COMP | Rule 16 | 187 | 60 | 25 | 1 | 2 | 29 | 299
21309 | 2019-08-13 | 2020-07-31 | 2020-10-03 | 2020-10-03 | COMP | 2021-01-08 | COMP | 2021-01-08 | COMP | 2023-01-27 | COMP | 2023-05-20 | COMP | Rule 16 | 245 | 45 | 65 | 1 | 516 | 80 | 948
22901 | 2019-08-13 | 2020-10-15 | 2021-01-21 | 2021-01-21 | COMP | 2021-02-03 | COMP | 2021-03-12 | COMP | 2021-03-29 | COMP | 2021-04-21 | COMP | Rule 16 | 298 | 65 | 10 | 27 | 12 | 18 | 425
4249 | 2019-08-14 | 2019-11-06 | 2019-12-17 | 2019-12-17 | COMP | 2020-04-15 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-06-10 | COMP | Rule 16 | 60 | 27 | 83 | 20 | 1 | 21 | 207
14647 | 2019-08-14 | 2019-09-20 | 2019-10-29 | 2020-09-10 | COMP | 2020-11-04 | COMP | 2021-01-12 | COMP | 2020-11-18 | COMP | 2021-03-16 | COMP | Rule 16 | 27 | 28 | 40 | 45 | 0 | 44 | 398
14713 | 2019-08-14 | 2019-09-24 | 2019-10-10 | 2019-10-10 | COMP | 2019-10-17 | COMP | 2019-11-01 | COMP | 2020-01-21 | COMP | 2020-03-13 | COMP | Rule 16 | 29 | 13 | 6 | 12 | 52 | 38 | 145
14885 | 2019-08-14 | 2019-10-02 | 2019-12-12 | 2019-12-12 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-05-22 | COMP | 2020-06-02 | COMP | Rule 16 | 35 | 49 | 89 | 1 | 25 | 7 | 201
14918 | 2019-08-14 | 2019-10-04 | 2019-11-22 | 2019-11-22 | COMP | 2019-11-22 | NOTN | 2019-11-22 | COMP | 2019-12-03 | COMP | 2020-01-17 | COMP | Other | 37 | 35 |  | 1 | 6 | 32 | 107
14972 | 2019-08-14 | 2019-10-08 | 2019-11-21 | 2019-11-21 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-02-24 | COMP | 2020-03-10 | COMP | Rule 16 | 39 | 32 | 50 | 1 | 13 | 12 | 142
15217 | 2019-08-14 | 2019-10-21 | 2020-06-13 | 2020-10-09 | COMP | 2020-10-15 | COMP | 2021-06-22 | COMP | 2021-06-22 | COMP | 2021-06-28 | COMP | Rule 16 | 48 | 162 | 5 | 171 | 1 | 5 | 471
15355 | 2019-08-14 | 2019-10-29 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-06 | COMP | 2020-03-13 | COMP | 2020-03-31 | COMP | 2020-06-09 | COMP | Rule 16 | 54 | 76 | 12 | 6 | 13 | 50 | 206
15422 | 2019-08-14 | 2019-10-31 | 2020-02-03 | 2020-05-05 | COMP | 2020-05-12 | COMP | 2020-06-25 | COMP | 2020-02-08 | COMP | 2020-07-09 | COMP | Rule 15/16 | 56 | 62 | 6 | 32 | 0 | 11 | 228
15454 | 2019-08-14 | 2019-11-02 | 2020-02-03 | 2020-06-24 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2020-06-29 | COMP | 2021-05-31 | COMP | Rule 16 | 57 | 60 | 61 | 1 | 0 | 175 | 451
15545 | 2019-08-14 | 2019-11-06 | 2019-11-26 | 2019-11-26 | COMP | 2019-12-11 | COMP | 2020-06-01 | NOTN | 2020-05-30 | COMP | 2020-06-25 | COMP | Rule 16 | 60 | 14 | 10 |  |  |  | 218
15613 | 2019-08-14 | 2019-11-12 | 2020-04-13 | 2020-04-13 | COMP | 2020-12-09 | COMP | 2021-01-27 | COMP | 2022-03-28 | COMP | 2022-04-07 | COMP | Rule 16 | 63 | 104 | 168 | 33 | 295 | 9 | 667
15823 | 2019-08-14 | 2019-11-21 | 2020-04-15 | 2020-04-15 | COMP | 2020-06-16 | COMP | 2020-08-06 | COMP | 2020-12-01 | COMP | 2021-02-08 | COMP | Rule 15/16 | 70 | 99 | 44 | 38 | 80 | 47 | 373
15871 | 2019-08-14 | 2019-11-26 | 2020-10-21 | 2020-10-21 | COMP | 2020-12-14 | COMP | 2020-12-14 | COMP | 2022-01-30 | INPR | 2020-12-30 | COMP | Rule 16 | 73 | 229 | 36 | 1 |  |  | 347
16009 | 2019-08-14 | 2019-12-06 | 2020-01-21 | 2020-01-21 | COMP | 2020-01-28 | COMP | 2020-01-29 | COMP | 2020-01-21 | COMP | 2020-02-24 | COMP | Rule 15/16 | 79 | 30 | 6 | 2 | 0 | 18 | 131
16172 | 2019-08-14 | 2019-12-12 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2021-12-06 | COMP | 2021-12-09 | COMP | Rule 16 | 83 | 104 | 26 | 1 | 371 | 4 | 584
16398 | 2019-08-14 | 2019-12-27 | 2020-06-19 | 2020-06-19 | COMP | 2020-08-27 | COMP | 2021-05-28 | COMP | 2020-06-22 | COMP | 2021-07-21 | COMP | Rule 16 | 93 | 122 | 50 | 189 | 0 | 37 | 487
16403 | 2019-08-14 | 2019-12-27 | 2020-04-05 | 2020-05-28 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-01 | COMP | 2021-06-30 | COMP | Rule 16 | 93 | 68 | 11 | 1 | 0 | 266 | 473
16464 | 2019-08-14 | 2020-01-03 | 2020-04-27 | 2020-07-13 | COMP | 2020-08-10 | COMP | 2020-11-18 | COMP | 2020-12-15 | COMP | 2021-03-12 | COMP | Rule 15/16 | 97 | 80 | 21 | 71 | 18 | 60 | 396
16479 | 2019-08-14 | 2020-01-03 | 2020-07-08 | 2020-07-08 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2020-11-07 | COMP | 2021-05-13 | COMP | Rule 16 | 97 | 131 | 87 | 1 | 1 | 127 | 440
16688 | 2019-08-14 | 2020-01-12 | 2021-02-17 | 2021-02-17 | COMP | 2021-04-16 | COMP | 2021-12-21 | COMP | 2021-12-17 | COMP | 2022-01-12 | COMP | Rule 15/16 | 102 | 277 | 43 | 172 | 0 | 17 | 608
16739 | 2019-08-14 | 2020-01-13 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-14 | COMP | 2020-03-26 | COMP | 2020-10-13 | COMP | 2021-01-07 | COMP | Rule 16 | 103 | 9 | 16 | 29 | 142 | 58 | 352
17088 | 2019-08-14 | 2020-01-30 | 2020-04-13 | 2020-04-13 | COMP | 2021-03-25 | COMP | 2021-03-27 | COMP | 2021-08-09 | COMP | 2021-09-10 | COMP | Rule 16 | 115 | 52 | 240 | 2 | 94 | 24 | 523
17458 | 2019-08-14 | 2020-02-15 | 2021-02-24 | 2021-03-26 | COMP | 2021-04-22 | COMP | 2021-08-11 | COMP | 2021-07-27 | COMP | 2021-09-14 | COMP | Rule 15/16 | 126 | 258 | 20 | 78 | 0 | 24 | 525
17650 | 2019-08-14 | 2020-02-24 | 2020-03-25 | 2020-10-13 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-12-23 | COMP | Rule 16 | 131 | 23 | 2 | 1 | 1 | 48 | 343
19223 | 2019-08-14 | 2020-04-27 | 2021-07-23 | 2022-02-08 | COMP | 2022-03-01 | COMP | 2022-06-29 | COMP | 2022-07-09 | COMP | 2022-11-17 | COMP | Rule 15/16 | 176 | 314 | 15 | 85 | 7 | 92 | 822
23217 | 2019-08-14 | 2020-10-28 | 2021-04-05 | 2021-05-20 | COMP | 2023-04-24 | COMP | 2023-10-25 | COMP | 2023-10-03 | COMP | 2023-11-10 | COMP | Rule 15/16 | 306 | 107 | 484 | 129 | 0 | 12 | 1067
40276 | 2019-08-14 | 2022-12-16 | 2023-04-12 | 2023-04-12 | COMP | 2023-04-20 | COMP | 2023-04-25 | COMP | 2023-04-24 | COMP | 2023-06-09 | COMP | Rule 15/16 | 841 | 80 | 7 | 4 | 0 | 33 | 961
4231 | 2019-08-15 | 2019-09-17 | [7 empty] | 2019-10-01 | COMP | 2020-01-31 | COMP | Other | 23 | [5 empty] | 115
13934 | 2019-08-15 | 2019-08-16 | 2019-09-18 | 2019-09-18 | COMP | 2019-10-03 | COMP | 2019-10-03 | COMP | 2020-03-01 | INPR | 2019-10-21 | COMP | Rule 16 | 2 | 23 | 12 | 1 |  |  | 47
14015 | 2019-08-15 | 2019-08-22 | 2019-12-16 | 2021-02-18 | COMP | 2021-02-22 | COMP | 2021-04-26 | COMP | 2021-04-12 | COMP | 2021-09-14 | COMP | Rule 16 | 6 | 79 | 3 | 46 | 0 | 99 | 524
14119 | 2019-08-15 | 2019-08-27 | 2020-04-13 | 2021-03-30 | COMP | 2021-04-29 | COMP | 2021-05-01 | COMP | 2021-07-14 | COMP | 2021-09-11 | COMP | Rule 15/16 | 9 | 157 | 23 | 2 | 51 | 42 | 522
14132 | 2019-08-15 | 2019-08-26 | 2019-10-18 | 2019-10-18 | COMP | 2019-10-28 | COMP | 2019-10-28 | COMP | 2020-01-05 | COMP | 2020-01-09 | COMP | Rule 16 | 8 | 39 | 7 | 1 | 45 | 4 | 100
14267 | 2019-08-15 | 2019-09-03 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2021-02-27 | INPR | 2020-02-11 | COMP | Rule 16 | 13 | 47 | 14 | 1 |  |  | 122
14306 | 2019-08-15 | 2019-09-05 | 2019-10-09 | 2019-10-09 | COMP | 2019-10-18 | COMP | 2019-10-18 | COMP | 2020-01-09 | COMP | 2020-01-23 | COMP | Rule 16 | 15 | 25 | 8 | 1 | 55 | 10 | 109
14324 | 2019-08-15 | 2019-09-04 | 2019-12-24 | 2021-02-24 | COMP | 2021-03-19 | COMP | 2021-03-19 | COMP | 2021-03-25 | COMP | 2021-03-31 | COMP | Rule 16 | 14 | 77 | 18 | 1 | 5 | 5 | 408
14391 | 2019-08-15 | 2019-09-09 | 2019-11-13 | 2019-11-13 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2020-11-16 | COMP | 2021-01-08 | COMP | Rule 16 | 17 | 47 | 211 | 1 | 45 | 36 | 352
14439 | 2019-08-15 | 2019-09-10 | 2019-11-20 | 2019-12-28 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-02-01 | COMP | 2020-02-21 | COMP | Rule 16 | 18 | 51 | 15 | 1 | 9 | 14 | 129
15020 | 2019-08-15 | 2019-10-09 | 2020-02-28 | 2020-02-28 | COMP | 2020-05-26 | COMP | 2020-06-10 | COMP | 2020-06-15 | COMP | 2020-08-20 | COMP | Rule 16 | 39 | 96 | 62 | 12 | 4 | 49 | 257
15088 | 2019-08-15 | 2019-10-11 | 2020-02-07 | 2020-02-07 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-11-23 | COMP | 2021-03-02 | COMP | Rule 15/16 | 41 | 80 | 133 | 1 | 71 | 66 | 387
15311 | 2019-08-15 | 2019-10-25 | 2020-03-09 | 2020-06-10 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-25 | COMP | 2020-10-08 | COMP | Rule 16 | 51 | 90 | 20 | 1 | 36 | 32 | 291
15405 | 2019-08-15 | 2019-10-31 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-04 | COMP | 2020-06-03 | COMP | 2020-06-01 | COMP | 2020-06-22 | COMP | Rule 16 | 55 | 51 | 13 | 85 | 0 | 14 | 214
15451 | 2019-08-15 | 2019-11-02 | 2019-12-17 | 2020-01-15 | COMP | 2020-01-27 | COMP | 2020-01-30 | COMP | 2020-05-12 | COMP | 2020-05-26 | COMP | Rule 15/16 | 56 | 29 | 8 | 4 | 73 | 10 | 195
15895 | 2019-08-15 | 2019-11-27 | 2020-04-16 | 2020-12-09 | COMP | 2020-12-14 | COMP | 2020-12-14 | COMP | 2021-04-17 | COMP | 2021-03-29 | COMP | Rule 15/16 | 73 | 96 | 4 | 1 | 86 |  | 406
15930 | 2019-08-15 | 2019-12-02 | 2020-01-10 | 2020-02-26 | COMP | 2020-05-13 | COMP | 2020-05-14 | COMP | 2020-06-02 | COMP | 2020-07-03 | COMP | Rule 16 | 74 | 28 | 56 | 2 | 13 | 24 | 223
16003 | 2019-08-15 | 2019-12-04 | 2020-03-16 | 2020-03-16 | COMP | 2021-02-18 | COMP | 2021-06-08 | COMP | 2021-06-03 | COMP | 2021-07-09 | COMP | Rule 16 | 76 | 70 | 235 | 78 | 0 | 23 | 478
16148 | 2019-08-15 | 2019-12-12 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-21 | COMP | 2020-06-12 | COMP | 2020-06-15 | COMP | 2020-11-24 | COMP | Rule 16 | 82 | 110 | 3 | 16 | 2 | 115 | 323
16173 | 2019-08-15 | 2019-12-12 | 2020-04-15 | 2020-04-15 | COMP | 2020-08-04 | COMP | 2020-12-04 | COMP | 2021-10-14 | COMP | 2021-11-30 | COMP | Rule 16 | 82 | 86 | 79 | 85 | 218 | 31 | 576
16198 | 2019-08-15 | 2019-12-13 | 2020-02-28 | 2020-03-07 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-12-17 | COMP | 2021-02-10 | COMP | Rule 16 | 83 | 52 | 64 | 1 | 136 | 37 | 374
16448 | 2019-08-15 | 2020-01-02 | 2020-02-06 | 2020-02-06 | COMP | 2020-02-26 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-06-17 | COMP | Rule 16 | 95 | 25 | 14 | 3 | 1 | 78 | 211
16715 | 2019-08-15 | 2020-01-13 | 2020-05-15 | 2020-08-06 | COMP | 2020-10-02 | COMP | 2022-06-16 | COMP | 2022-04-05 | COMP | 2022-07-20 | COMP | Rule 15/16 | 102 | 88 | 41 | 429 | 0 | 23 | 737
17258 | 2019-08-15 | 2020-02-06 | 2020-03-18 | 2020-03-18 | COMP | 2020-03-31 | NOTN | 2020-03-31 | COMP | 2020-04-06 | NOTN | 2020-06-04 | COMP | Other | 119 | 29 |  | 10 |  |  | 202
18295 | 2019-08-15 | 2020-03-19 | 2020-05-07 | 2020-05-08 | COMP | 2020-06-08 | COMP | 2020-06-10 | COMP | 2021-11-23 | COMP | 2022-02-04 | COMP | Rule 16 | 148 | 36 | 21 | 3 | 368 | 51 | 623
14022 | 2019-08-16 | 2019-08-22 | 2019-09-07 | 2019-09-07 | COMP | 2019-09-07 | NOTN | 2019-09-07 | COMP | 2019-09-07 | COMP | 2020-01-30 | COMP | Other | 5 | 11 |  | 0 | 0 | 98 | 113
14080 | 2019-08-16 | 2019-08-23 | 2019-09-12 | 2019-09-23 | COMP | 2019-09-12 | NOTN | 2019-09-23 | COMP | 2019-09-12 | COMP | 2019-10-02 | COMP | Other | 6 | 14 |  | 1 | 0 | 8 | 33
14096 | 2019-08-16 | 2019-08-26 | 2019-10-14 | 2019-10-14 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | Rule 16 | 7 | 35 | 52 | 1 | 72 | 1 | 163
14213 | 2019-08-16 | 2019-08-29 | 2019-09-07 | 2019-09-13 | COMP | 2019-09-19 | COMP | 2019-09-19 | COMP | 2019-09-25 | COMP | 2019-09-27 | COMP | Rule 16 | 10 | 6 | 5 | 1 | 5 | 3 | 30
14218 | 2019-08-16 | 2019-08-29 | 2019-12-09 | 2019-12-09 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-01-29 | COMP | 2020-02-24 | COMP | Rule 16 | 10 | 69 | 34 | 1 | 2 | 18 | 129
14576 | 2019-08-16 | 2019-09-17 | 2020-02-25 | 2020-04-30 | COMP | 2020-07-01 | COMP | 2020-08-03 | COMP | 2020-07-29 | COMP | 2020-10-01 | COMP | Rule 16 | 22 | 109 | 44 | 24 | 0 | 43 | 285
14829 | 2019-08-16 | 2019-09-30 | 2020-02-01 | 2020-02-01 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2021-10-23 | INPR | 2020-08-08 | COMP | Rule 15/16 | 31 | 84 | 121 | 1 |  |  | 247
14932 | 2019-08-16 | 2019-10-04 | 2020-02-18 | 2020-02-18 | COMP | 2020-03-28 | NOTN | 2020-05-18 | COMP | 2020-05-19 | COMP | 2020-06-12 | COMP | Other | 35 | 91 |  | 65 | 2 | 18 | 207
14997 | 2019-08-16 | 2019-10-09 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-12-01 | COMP | 2020-12-28 | COMP | Rule 15/16 | 38 | 65 | 27 | 1 | 198 | 19 | 343
15014 | 2019-08-16 | 2019-10-09 | 2020-01-16 | 2020-01-16 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-07-13 | COMP | 2020-10-06 | COMP | Rule 16 | 38 | 67 | 35 | 1 | 91 | 61 | 288
15535 | 2019-08-16 | 2019-11-06 | 2020-01-07 | 2022-07-26 | COMP | 2023-05-08 | COMP | 2023-06-27 | COMP | 2023-06-21 | COMP | 2023-08-24 | COMP | Rule 16 | 58 | 40 | 197 | 35 | 0 | 42 | 1011
15565 | 2019-08-16 | 2019-11-07 | 2020-03-06 | 2020-03-06 | COMP | 2020-04-03 | COMP | 2020-04-09 | COMP | 2020-05-26 | COMP | 2020-06-30 | COMP | Rule 16 | 59 | 80 | 21 | 5 | 33 | 26 | 219
15640 | 2019-08-16 | 2019-11-13 | 2019-12-30 | 2019-12-30 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-02-04 | COMP | 2020-06-03 | COMP | Rule 16 | 62 | 31 | 23 | 1 | 3 | 85 | 200
15800 | 2019-08-16 | 2019-11-21 | 2020-01-09 | 2020-01-09 | COMP | 2020-03-11 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-03-31 | COMP | Rule 16 | 68 | 32 | 43 | 9 | 1 | 7 | 155
16127 | 2019-08-16 | 2019-12-11 | 2020-05-07 | 2020-05-07 | COMP | 2021-06-18 | COMP | 2021-06-18 | COMP | 2021-07-06 | COMP | 2021-09-02 | COMP | Rule 16 | 80 | 103 | 282 | 1 | 12 | 43 | 516
16521 | 2019-08-16 | 2020-01-06 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-26 | COMP | 2020-10-06 | COMP | 2020-08-05 | COMP | 2020-11-22 | COMP | Rule 16 | 96 | 117 | 6 | 72 | 0 | 33 | 320
17319 | 2019-08-16 | 2020-02-10 | 2020-03-27 | 2020-03-27 | COMP | 2020-06-23 | NOTN | 2020-06-23 | COMP | 2020-07-28 | COMP | 2020-08-11 | COMP | Rule 16 | 120 | 34 |  | 62 | 26 | 11 | 249
17741 | 2019-08-16 | 2020-02-25 | 2020-06-30 | 2020-06-30 | COMP | 2020-08-27 | COMP | 2020-08-31 | COMP | 2023-02-27 | COMP | 2023-05-22 | COMP | Rule 16 | 130 | 90 | 43 | 3 | 624 | 61 | 946
18279 | 2019-08-16 | 2020-03-18 | 2020-04-05 | 2020-04-05 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-09-15 | COMP | 2020-09-21 | COMP | Rule 16 | 146 | 13 | 5 | 1 | 111 | 5 | 277
18708 | 2019-08-16 | 2020-04-03 | 2021-05-25 | 2021-05-25 | COMP | 2022-03-04 | COMP | 2023-05-19 | COMP | 2023-05-19 | COMP | 2023-08-04 | COMP | Rule 15/16 | 158 | 289 | 196 | 305 | 1 | 53 | 997
14328 | 2019-08-17 | 2019-09-05 | 2019-10-16 | 2019-11-07 | COMP | 2020-02-04 | COMP | 2020-02-21 | COMP | 2019-09-05 | COMP | 2020-03-26 | COMP | Rule 16 | 13 | 30 | 58 | 13 | 0 | 25 | 151
14365 | 2019-08-17 | 2019-09-06 | 2019-09-25 | 2019-09-25 | COMP | 2019-10-01 | COMP | 2019-10-01 | COMP | 2019-10-14 | COMP | 2019-11-01 | COMP | Rule 16 | 14 | 14 | 5 | 1 | 10 | 15 | 54
15280 | 2019-08-18 | 2019-10-24 | 2020-01-02 | 2020-01-02 | COMP | 2020-01-23 | COMP | 2020-01-29 | COMP | 2020-02-04 | COMP | 2020-02-25 | COMP | Rule 16 | 48 | 46 | 15 | 5 | 5 | 15 | 129
16011 | 2019-08-18 | 2019-12-04 | 2019-12-24 | 2019-12-24 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-23 | COMP | 2020-01-28 | COMP | Rule 16 | 74 | 15 | 16 | 1 | 5 | 4 | 110
17531 | 2019-08-18 | 2020-02-19 | 2020-04-23 | 2020-04-23 | COMP | 2020-08-17 | COMP | 2020-09-04 | COMP | 2020-09-04 | COMP | 2020-11-05 | COMP | Rule 16 | 125 | 47 | 82 | 15 | 1 | 44 | 309
17534 | 2019-08-18 | 2020-02-19 | 2020-05-07 | 2020-05-07 | COMP | 2020-05-18 | COMP | 2020-06-03 | COMP | 2020-06-16 | COMP | 2020-06-24 | COMP | Rule 16 | 125 | 57 | 8 | 12 | 10 | 7 | 214
4223 | 2019-08-19 | 2019-08-29 | [7 empty] | 2019-10-14 | COMP | 2019-10-24 | COMP | Other | 9 | [5 empty] | 48
4224 | 2019-08-19 | 2019-09-03 | [7 empty] | 2019-09-18 | COMP | 2019-09-25 | COMP | Other | 11 | [5 empty] | 27
14039 | 2019-08-19 | 2019-08-22 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-16 | COMP | 2019-10-30 | COMP | 2019-12-09 | COMP | 2019-12-17 | COMP | Rule 16 | 4 | 32 | 8 | 11 | 26 | 7 | 83
14205 | 2019-08-19 | 2019-08-29 | 2019-10-03 | 2019-10-03 | COMP | 2019-10-23 | COMP | 2019-11-21 | COMP | 2020-01-30 | COMP | 2020-02-13 | COMP | Rule 16 | 9 | 25 | 15 | 21 | 46 | 11 | 122
14398 | 2019-08-19 | 2019-09-09 | 2019-11-14 | 2019-11-14 | COMP | 2019-12-26 | COMP | 2019-12-26 | COMP | 2019-12-27 | COMP | 2020-01-25 | COMP | Rule 15/16 | 15 | 48 | 28 | 1 | 2 | 19 | 108
14418 | 2019-08-19 | 2019-09-09 | 2019-09-16 | 2019-10-25 | COMP | 2019-11-22 | COMP | 2019-11-22 | COMP | 2020-02-08 | COMP | 2019-12-20 | COMP | Rule 16 | 15 | 6 | 20 | 1 | 51 |  | 86
14490 | 2019-08-19 | 2019-09-11 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | Rule 15/16 | 17 | 164 | 10 | 1 | 29 | 1 | 217
14559 | 2019-08-19 | 2019-09-16 | 2019-10-12 | 2019-10-12 | COMP | 2019-11-07 | COMP | 2020-02-28 | COMP | 2020-07-14 | COMP | 2020-08-07 | COMP | Rule 16 | 20 | 20 | 19 | 75 | 97 | 19 | 246
14655 | 2019-08-19 | 2019-09-20 | 2019-12-12 | 2019-12-12 | COMP | 2020-01-13 | COMP | 2020-02-28 | COMP | 2020-01-24 | COMP | 2020-07-09 | COMP | Rule 16 | 24 | 57 | 21 | 33 | 0 | 94 | 225
14904 | 2019-08-19 | 2019-10-03 | 2019-10-14 | 2019-10-14 | COMP | 2020-01-14 | COMP | 2020-01-14 | COMP | 2020-06-04 | COMP | 2020-06-25 | COMP | Rule 16 | 33 | 8 | 62 | 1 | 100 | 16 | 215
15089 | 2019-08-19 | 2019-10-11 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-04-27 | COMP | 2020-06-17 | COMP | Rule 16 | 39 | 87 | 9 | 1 | 41 | 37 | 209
15152 | 2019-08-19 | 2019-10-16 | 2020-01-13 | 2020-01-13 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-06-01 | COMP | 2020-07-06 | COMP | Rule 16 | 42 | 59 | 69 | 1 | 30 | 26 | 222
15493 | 2019-08-19 | 2019-11-05 | 2019-12-16 | 2019-12-16 | COMP | 2020-01-29 | COMP | 2020-02-24 | COMP | 2020-03-25 | COMP | 2020-04-27 | COMP | Rule 16 | 56 | 27 | 30 | 18 | 23 | 24 | 173
15851 | 2019-08-19 | 2019-11-26 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-17 | COMP | 2020-08-05 | COMP | 2020-08-21 | COMP | 2020-10-06 | COMP | Rule 16 | 70 | 86 | 13 | 78 | 13 | 32 | 287
15929 | 2019-08-19 | 2019-12-02 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-15 | COMP | 2020-06-09 | COMP | 2020-05-15 | COMP | 2020-07-13 | COMP | Rule 16 | 72 | 89 | 28 | 17 | 0 | 25 | 227
15957 | 2019-08-19 | 2019-12-03 | 2020-01-06 | 2020-01-06 | COMP | 2020-01-17 | COMP | 2020-02-05 | COMP | 2021-02-27 | INPR | 2020-02-18 | COMP | Rule 16 | 73 | 23 | 10 | 13 |  |  | 124
16179 | 2019-08-19 | 2019-12-13 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-06 | COMP | 2020-06-25 | COMP | 2020-07-28 | COMP | 2020-08-05 | COMP | Rule 16 | 81 | 71 | 30 | 36 | 24 | 7 | 244
16461 | 2019-08-19 | 2019-12-31 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-21 | COMP | 2022-10-13 | COMP | 2022-10-16 | COMP | 2023-09-14 | COMP | Rule 16 | 92 | 155 | 11 | 540 | 2 | 228 | 1024
16740 | 2019-08-19 | 2020-01-13 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2022-01-30 | INPR | 2020-09-10 | COMP | Rule 16 | 100 | 76 | 11 | 1 |  |  | 269
16894 | 2019-08-19 | 2020-01-22 | 2020-11-09 | 2020-11-09 | COMP | 2020-12-07 | COMP | 2020-12-15 | COMP | 2021-01-19 | COMP | 2021-07-07 | COMP | Rule 16 | 106 | 206 | 18 | 7 | 23 | 119 | 474
17007 | 2019-08-19 | 2020-01-27 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-06-24 | COMP | Rule 16 | 109 | 57 | 14 | 1 | 6 | 32 | 214
17661 | 2019-08-19 | 2020-02-24 | 2020-05-07 | 2020-05-07 | COMP | 2020-05-19 | COMP | 2020-07-02 | COMP | 2020-07-28 | COMP | 2020-09-16 | COMP | Rule 16 | 128 | 54 | 9 | 32 | 19 | 36 | 273
17814 | 2019-08-19 | 2020-02-28 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-10-30 | COMP | 2020-12-01 | COMP | Other | 132 | 51 | 52 | 1 | 73 | 20 | 324
17830 | 2019-08-19 | 2020-02-28 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2021-04-05 | COMP | 2021-04-27 | COMP | Other | 132 | 51 | 52 | 1 | 177 | 17 | 425
17907 | 2019-08-19 | 2020-03-03 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2021-04-09 | COMP | 2021-06-02 | COMP | Rule 16 | 134 | 60 | 26 | 1 | 196 | 38 | 450
18658 | 2019-08-19 | 2020-04-01 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-02 | COMP | 2020-07-22 | COMP | 2020-07-10 | COMP | 2020-08-06 | COMP | Rule 16 | 155 | 33 | 12 | 37 | 0 | 12 | 245
19419 | 2019-08-19 | 2020-05-06 | 2020-11-20 | 2020-11-20 | COMP | 2020-11-30 | COMP | 2020-12-22 | COMP | 2022-01-31 | INPR | 2020-12-23 | COMP | Rule 16 | 180 | 140 | 5 | 17 |  |  | 340
21065 | 2019-08-19 | 2020-07-20 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-14 | COMP | 2020-10-12 | COMP | 2022-01-31 | INPR | 2020-11-18 | COMP | Rule 16 | 232 | 31 | 10 | 21 |  |  | 317
14009 | 2019-08-20 | 2019-08-21 | 2019-10-18 | 2020-05-12 | COMP | 2020-05-12 | NOTN | 2020-05-12 | COMP | 2019-11-12 | COMP | 2020-06-09 | COMP | Other | 2 | 42 |  | 1 | 0 | 20 | 202
14014 | 2019-08-20 | 2019-08-22 | 2020-02-04 | 2020-02-04 | COMP | 2020-04-10 | COMP | 2021-01-06 | COMP | 2020-09-23 | COMP | 2021-01-30 | COMP | Rule 16 | 3 | 112 | 48 | 187 | 0 | 17 | 363
14061 | 2019-08-20 | 2019-08-23 | 2020-03-05 | 2020-04-10 | COMP | 2020-05-20 | COMP | 2020-05-21 | COMP | 2020-05-20 | COMP | 2020-06-30 | COMP | Rule 15/16 | 4 | 132 | 29 | 2 | 0 | 28 | 217
14077 | 2019-08-20 | 2019-08-24 | 2020-01-28 | 2020-04-28 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-07-27 | COMP | 2020-08-27 | COMP | Rule 16 | 4 | 105 | 26 | 1 | 39 | 24 | 259
14083 | 2019-08-20 | 2019-08-23 | 2020-09-21 | 2021-10-27 | COMP | 2021-11-08 | COMP | 2021-01-08 | COMP | 2021-09-03 | COMP | 2021-11-16 | COMP | Rule 16 | 4 | 272 | 9 |  | 167 | 51 | 565
14377 | 2019-08-20 | 2019-09-07 | 2019-12-24 | 2019-12-24 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2021-05-30 | INPR | 2020-05-07 | COMP | Rule 16 | 13 | 74 | 32 | 1 |  |  | 180
14471 | 2019-08-20 | 2019-09-11 | 2019-11-06 | 2019-11-06 | COMP | 2019-11-12 | COMP | 2019-11-12 | COMP | 2019-12-03 | COMP | 2019-12-05 | COMP | Rule 16 | 16 | 41 | 4 | 1 | 14 | 3 | 74
14506 | 2019-08-20 | 2019-09-13 | 2019-12-31 | 2019-12-31 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-06-17 | COMP | 2020-07-24 | COMP | Rule 16 | 18 | 74 | 90 | 1 | 29 | 28 | 235
14678 | 2019-08-20 | 2019-09-23 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-10 | COMP | 2020-03-05 | COMP | 2020-07-08 | COMP | 2020-07-29 | COMP | Rule 16 | 24 | 79 | 17 | 18 | 89 | 16 | 238
14799 | 2019-08-20 | 2019-09-27 | 2019-11-20 | 2019-11-20 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2020-08-07 | COMP | 2020-08-11 | COMP | Rule 16 | 28 | 38 | 142 | 1 | 40 | 3 | 247
14913 | 2019-08-20 | 2019-10-03 | 2020-03-02 | 2021-05-19 | COMP | 2022-01-26 | COMP | 2022-04-20 | COMP | 2022-05-10 | COMP | 2022-06-25 | COMP | Rule 16 | 32 | 101 | 174 | 60 | 15 | 32 | 717
15091 | 2019-08-20 | 2019-10-11 | 2019-12-16 | 2019-12-16 | COMP | 2020-02-26 | COMP | 2020-05-27 | COMP | 2020-07-14 | COMP | 2020-07-11 | COMP | Rule 15/16 | 38 | 44 | 49 | 65 | 35 |  | 225
15104 | 2019-08-20 | 2019-10-12 | 2020-06-09 | 2020-06-09 | COMP | 2020-07-27 | COMP | 2020-09-21 | COMP | 2020-09-29 | COMP | 2020-11-08 | COMP | Rule 15/16 | 38 | 164 | 35 | 40 | 7 | 29 | 309
15196 | 2019-08-20 | 2019-10-18 | 2019-12-28 | 2019-12-30 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-17 | COMP | 2020-01-31 | COMP | Rule 16 | 43 | 47 | 13 | 1 | 2 | 10 | 112
15210 | 2019-08-20 | 2019-10-21 | 2020-04-03 | 2020-05-20 | COMP | 2020-06-13 | COMP | 2020-09-25 | COMP | 2020-10-08 | COMP | 2020-12-03 | COMP | Rule 15/16 | 44 | 113 | 17 | 74 | 10 | 38 | 325
15397 | 2019-08-20 | 2019-10-30 | 2020-02-24 | 2020-02-24 | COMP | 2020-04-13 | COMP | 2020-04-30 | COMP | 2020-04-22 | COMP | 2020-06-18 | COMP | Rule 16 | 51 | 77 | 36 | 14 | 0 | 35 | 209
15429 | 2019-08-20 | 2019-10-31 | 2019-12-16 | 2019-12-16 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-03-31 | COMP | 2020-04-21 | COMP | Rule 16 | 52 | 30 | 59 | 1 | 15 | 16 | 168
15778 | 2019-08-20 | 2019-11-21 | 2020-02-11 | 2020-02-11 | COMP | 2020-02-26 | COMP | 2020-09-29 | COMP | 2020-07-02 | COMP | 2020-10-15 | COMP | Rule 16 | 66 | 54 | 11 | 153 | 0 | 13 | 293
15781 | 2019-08-20 | 2019-11-21 | 2020-01-08 | 2020-01-08 | COMP | 2020-06-10 | COMP | 2020-12-16 | COMP | 2020-12-03 | COMP | 2021-01-22 | COMP | Rule 16 | 66 | 31 | 108 | 132 | 0 | 25 | 358
15828 | 2019-08-20 | 2019-11-22 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-17 | COMP | 2020-07-09 | COMP | 2020-07-13 | COMP | 2020-09-18 | COMP | Rule 15/16 | 67 | 76 | 25 | 59 | 3 | 49 | 274
15992 | 2019-08-20 | 2019-12-04 | 2020-05-27 | 2020-05-27 | COMP |  | INPR | 2023-02-13 | COMP | 2023-04-18 | COMP | 2023-05-19 | COMP | Rule 15/16 | 73 | 121 |  | 683 | 46 | 24 | 943
16061 | 2019-08-20 | 2019-12-06 | 2020-05-04 | 2020-05-04 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2020-12-24 | COMP | 2021-01-19 | COMP | Rule 16 | 75 | 103 | 153 | 1 | 12 | 16 | 355
16097 | 2019-08-20 | 2019-12-09 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-02-12 | COMP | 2020-02-18 | COMP | Rule 16 | 76 | 20 | 8 | 1 | 19 | 4 | 123
16362 | 2019-08-20 | 2019-12-24 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-12 | COMP | 2020-02-13 | COMP | 2020-02-27 | COMP | 2020-03-25 | COMP | Rule 16 | 87 | 15 | 20 | 2 | 10 | 20 | 149
16890 | 2019-08-20 | 2020-01-22 | 2020-03-07 | 2020-03-07 | COMP | 2020-06-23 | COMP | 2020-07-03 | COMP | 2023-12-30 | INPR | 2021-03-09 | COMP | Rule 16 | 105 | 32 | 76 | 9 |  |  | 389
17297 | 2019-08-20 | 2020-02-07 | 2020-03-05 | 2020-03-05 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-04-09 | COMP | 2020-04-17 | COMP | Rule 16 | 117 | 19 | 24 | 1 | 3 | 7 | 166
17298 | 2019-08-20 | 2020-02-07 | 2020-05-09 | 2020-05-09 | COMP | 2020-06-12 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2020-09-30 | COMP | Rule 16 | 117 | 65 | 24 | 32 | 1 | 47 | 282
17586 | 2019-08-20 | 2020-02-21 | 2020-04-20 | 2020-05-13 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-11-23 | COMP | 2020-12-18 | COMP | Rule 15/16 | 126 | 42 | 106 | 1 | 31 | 18 | 336
17617 | 2019-08-20 | 2020-02-21 | 2020-06-03 | 2020-06-03 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2021-06-30 | COMP | 2021-10-17 | COMP | Rule 15/16 | 126 | 73 | 57 | 1 | 216 | 76 | 544
17700 | 2019-08-20 | 2020-02-25 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-07-24 | COMP | 2020-10-28 | COMP | Rule 16 | 128 | 80 | 27 | 1 | 3 | 68 | 302
18400 | 2019-08-20 | 2020-03-23 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-13 | COMP | 2020-07-17 | COMP | 2023-11-13 | INPR | 2020-11-12 | COMP | Rule 16 | 147 | 43 | 17 | 25 |  |  | 312
18973 | 2019-08-20 | 2020-04-16 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-05 | COMP | 2020-07-22 | COMP | 2020-07-27 | COMP | 2020-08-26 | COMP | Rule 16 | 165 | 28 | 9 | 34 | 4 | 23 | 258
20082 | 2019-08-20 | 2020-06-03 | 2020-11-02 | 2020-11-02 | COMP | 2021-04-05 | COMP | 2021-06-30 | COMP | 2021-07-13 | COMP | 2021-07-16 | COMP | Rule 16 | 198 | 108 | 104 | 62 | 9 | 4 | 480
20168 | 2019-08-20 | 2020-06-08 | 2020-06-23 | 2020-06-23 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-08-12 | COMP | 2020-09-03 | COMP | Rule 16 | 201 | 12 | 5 | 1 | 33 | 17 | 264
14180 | 2019-08-21 | 2019-08-28 | 2019-11-21 | 2019-11-21 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2022-01-30 | INPR | 2020-06-18 | COMP | Rule 16 | 6 | 60 | 17 | 1 |  |  | 208
14191 | 2019-08-21 | 2019-08-28 | 2019-10-11 | 2019-10-11 | COMP | 2019-12-09 | COMP | 2019-12-09 | INPR | 2021-01-08 | COMP | 2021-01-26 | COMP | Rule 16 | 6 | 32 | 39 |  |  |  | 359
14517 | 2019-08-21 | 2019-09-13 | 2020-01-03 | 2020-01-03 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-23 | COMP | 2020-02-05 | COMP | Rule 16 | 17 | 76 | 10 | 1 | 5 | 10 | 114
14591 | 2019-08-21 | 2019-09-17 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2019-12-16 | COMP | 2020-01-14 | COMP | Rule 16 | 19 | 38 | 15 | 1 | 11 | 20 | 99
14866 | 2019-08-21 | 2019-10-01 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-06 | COMP | 2020-03-02 | COMP | 2020-03-30 | COMP | 2020-05-12 | COMP | Rule 15/16 | 29 | 71 | 17 | 17 | 21 | 32 | 182
14883 | 2019-08-21 | 2019-10-02 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-21 | COMP | 2020-06-22 | COMP | Rule 16 | 30 | 43 | 22 | 1 | 11 | 108 | 210
15125 | 2019-08-21 | 2019-10-15 | 2020-01-15 | 2020-01-15 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-05-12 | COMP | 2020-06-12 | COMP | Rule 16 | 39 | 62 | 82 | 1 | 2 | 23 | 204
15146 | 2019-08-21 | 2019-10-16 | 2020-03-24 | 2020-03-24 | COMP | 2021-06-23 | COMP | 2021-07-19 | COMP | 2021-10-07 | COMP | 2022-01-12 | COMP | Rule 15/16 | 40 | 108 | 317 | 18 | 58 | 67 | 603
15406 | 2019-08-21 | 2019-10-31 | 2019-12-19 | 2019-12-19 | COMP | 2020-02-14 | COMP | 2020-02-18 | COMP | 2020-05-11 | COMP | 2020-05-29 | COMP | Rule 16 | 51 | 33 | 39 | 2 | 60 | 14 | 194
15530 | 2019-08-21 | 2019-11-07 | 2020-03-04 | 2020-03-04 | COMP | 2020-04-06 | COMP | 2020-06-22 | COMP | 2020-12-01 | COMP | 2021-01-19 | COMP | Rule 16 | 56 | 78 | 24 | 55 | 113 | 33 | 354
15554 | 2019-08-21 | 2019-11-09 | 2020-05-04 | 2020-05-04 | COMP | 2021-03-23 | COMP | 2022-03-25 | COMP | 2022-07-09 | COMP | 2022-08-24 | COMP | Rule 15/16 | 57 | 119 | 223 | 256 | 73 | 33 | 758
15562 | 2019-08-21 | 2019-11-07 | 2020-01-10 | 2020-01-10 | COMP | 2020-02-03 | COMP | 2020-03-02 | COMP | 2020-05-01 | COMP | 2020-05-29 | COMP | Rule 16 | 56 | 42 | 16 | 20 | 45 | 20 | 194
15581 | 2019-08-21 | 2019-11-07 | 2020-01-16 | 2020-01-16 | COMP | 2020-03-16 | COMP | 2020-05-20 | COMP | 2020-05-27 | COMP | 2020-07-09 | COMP | Rule 16 | 56 | 46 | 41 | 48 | 5 | 32 | 223
15668 | 2019-08-21 | 2019-11-14 | 2020-01-12 | 2020-01-12 | COMP | 2020-01-23 | COMP | 2020-03-09 | COMP | 2021-03-01 | COMP | 2021-04-08 | COMP | Rule 15/16 | 60 | 38 | 8 | 32 | 247 | 29 | 410
15945 | 2019-08-21 | 2019-12-02 | 2020-07-27 | 2020-07-27 | COMP | 2020-10-27 | COMP | 2021-03-03 | COMP | 2022-06-18 | INPR | 2021-05-28 | COMP | Rule 16 | 70 | 166 | 66 | 85 |  |  | 446
16098 | 2019-08-21 | 2019-12-09 | 2020-01-30 | 2020-01-30 | COMP | 2020-04-02 | COMP | 2020-05-04 | COMP | 2020-04-28 | COMP | 2020-06-03 | COMP | Rule 15/16 | 75 | 36 | 45 | 23 | 0 | 22 | 197
16650 | 2019-08-21 | 2020-01-09 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-05-28 | COMP | 2020-07-15 | COMP | Rule 16 | 96 | 63 | 37 | 1 | 0 | 34 | 227
16775 | 2019-08-21 | 2020-01-17 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-09-03 | COMP | 2020-10-13 | COMP | Rule 16 | 102 | 25 | 10 | 1 | 129 | 28 | 290
17119 | 2019-08-21 | 2020-01-31 | 2020-03-18 | 2020-03-18 | COMP | 2020-05-08 | COMP | 2020-10-07 | COMP | 2020-09-21 | COMP | 2021-02-25 | COMP | Rule 16 | 111 | 33 | 38 | 107 | 0 | 95 | 380
17155 | 2019-08-21 | 2020-02-04 | 2020-09-02 | 2020-09-02 | COMP | 2020-09-21 | COMP | 2020-10-30 | COMP | 2020-09-24 | COMP | 2020-12-13 | COMP | Rule 16 | 113 | 150 | 13 | 30 | 0 | 28 | 330
17799 | 2019-08-21 | 2020-02-27 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2021-05-24 | COMP | 2021-07-09 | COMP | Rule 16 | 129 | 38 | 25 | 1 | 253 | 33 | 474
19583 | 2019-08-21 | 2020-05-14 | 2020-06-16 | 2020-06-16 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2021-01-14 | COMP | 2021-02-10 | COMP | Rule 15/16 | 184 | 23 | 41 | 1 | 107 | 19 | 370
4321 | 2019-08-22 | 2020-11-17 | 2021-03-03 | 2021-03-03 | COMP | 2021-07-30 | COMP | 2022-03-24 | COMP | 2022-02-25 | COMP | 2022-04-08 | COMP | Rule 15/16 | 313 | 71 | 106 | 164 | 0 | 12 | 662
14137 | 2019-08-22 | 2019-08-26 | 2020-01-10 | 2020-01-10 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-08-10 | COMP | 2020-09-22 | COMP | Rule 16 | 3 | 94 | 74 | 1 | 76 | 31 | 274
14404 | 2019-08-22 | 2019-09-09 | 2019-10-08 | 2019-10-08 | COMP | 2019-12-12 | COMP | 2019-12-12 | COMP | 2019-12-13 | COMP | 2019-12-20 | COMP | Rule 16 | 12 | 22 | 45 | 1 | 2 | 6 | 83
14442 | 2019-08-22 | 2019-09-10 | 2019-11-11 | 2019-11-19 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-02-19 | COMP | 2020-03-09 | COMP | Rule 16 | 13 | 44 | 8 | 1 | 54 | 14 | 135
14543 | 2019-08-22 | 2019-09-16 | 2019-11-14 | 2019-11-14 | COMP | 2019-12-02 | COMP | 2020-01-03 | COMP | 2020-01-13 | COMP | 2020-02-21 | COMP | Rule 16 | 17 | 43 | 11 | 23 | 7 | 28 | 124
14618 | 2019-08-22 | 2019-09-20 | 2019-11-27 | 2019-11-27 | COMP | 2020-03-27 | COMP | 2020-02-03 | COMP | 2021-03-27 | INPR | 2020-03-06 | COMP | Rule 16 | 21 | 48 | 82 |  |  |  | 134
14706 | 2019-08-22 | 2019-09-23 | 2019-10-22 | 2019-10-22 | COMP | 2020-05-13 | COMP | 2020-04-13 | COMP | 2020-06-01 | COMP | 2020-07-14 | COMP | Rule 16 | 22 | 22 | 140 |  | 35 | 32 | 225
14768 | 2019-08-22 | 2019-09-26 | 2019-11-24 | 2019-11-24 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-01-13 | COMP | 2020-02-26 | COMP | Rule 16 | 25 | 41 | 14 | 1 | 19 | 31 | 127
14902 | 2019-08-22 | 2019-10-04 | 2019-12-17 | 2019-12-17 | COMP | 2020-03-30 | COMP | 2020-05-12 | COMP | 2020-03-30 | COMP | 2020-06-02 | COMP | Rule 16 | 31 | 50 | 71 | 32 | 0 | 15 | 195
15047 | 2019-08-22 | 2019-10-10 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-16 | COMP | 2020-05-28 | COMP | 2020-06-05 | COMP | 2020-07-02 | COMP | Rule 16 | 35 | 101 | 6 | 53 | 7 | 20 | 217
15252 | 2019-08-22 | 2019-10-24 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-09-30 | COMP | 2020-12-06 | COMP | Rule 16 | 45 | 91 | 18 | 1 | 129 | 45 | 324
15343 | 2019-08-22 | 2019-10-29 | 2019-12-06 | 2019-12-06 | COMP | 2020-11-12 | COMP | 2021-01-28 | COMP | 2021-01-29 | COMP | 2021-03-01 | COMP | Rule 16 | 48 | 26 | 238 | 51 | 2 | 21 | 381
15350 | 2019-08-22 | 2019-10-28 | 2019-12-20 | 2019-12-20 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-03-31 | COMP | 2020-04-14 | COMP | Rule 16 | 47 | 37 | 59 | 1 | 11 | 11 | 161
15363 | 2019-08-22 | 2019-10-28 | 2020-07-07 | 2020-07-07 | COMP | 2020-08-07 | COMP | 2020-11-09 | COMP | 2020-07-15 | COMP | 2021-03-12 | COMP | Rule 16 | 47 | 174 | 24 | 66 | 0 | 83 | 390
15369 | 2019-08-22 | 2019-10-31 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-18 | COMP | 2020-06-22 | COMP | 2020-06-23 | COMP | 2020-07-18 | COMP | Rule 16 | 50 | 86 | 8 | 68 | 2 | 19 | 228
15407 | 2019-08-22 | 2019-10-30 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-26 | COMP | 2020-02-28 | COMP | 2020-02-26 | COMP | 2020-07-22 | COMP | Rule 16 | 49 | 71 | 9 | 3 | 0 | 103 | 231
15439 | 2019-08-22 | 2019-11-01 | 2019-12-20 | 2022-01-13 | COMP | 2022-01-14 | COMP | 2022-01-12 | COMP | 2021-12-30 | COMP | 2022-02-22 | COMP | Rule 16 | 51 | 33 | 2 |  | 0 | 28 | 629
15444 | 2019-08-22 | 2019-11-01 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-04-08 | COMP | Rule 16 | 51 | 79 | 4 | 1 | 1 | 26 | 157
15550 | 2019-08-22 | 2019-11-06 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-08 | COMP | 2020-07-06 | COMP | 2020-08-19 | COMP | 2020-09-26 | COMP | Rule 16 | 54 | 87 | 18 | 63 | 33 | 27 | 277
15597 | 2019-08-22 | 2019-11-08 | 2020-02-06 | 2020-02-06 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-05-07 | COMP | 2020-06-14 | COMP | Rule 16 | 56 | 59 | 50 | 1 | 16 | 26 | 203
15707 | 2019-08-22 | 2019-11-18 | 2020-02-18 | 2020-02-18 | COMP | 2020-02-26 | COMP | 2020-06-04 | INPR | 2022-03-19 | REQD | 2020-07-22 | COMP | Rule 16 | 61 | 61 | 7 |  |  |  | 231
15995 | 2019-08-22 | 2019-12-04 | 2020-01-25 | 2021-01-08 | COMP | 2021-01-19 | COMP | 2021-04-05 | COMP | 2021-04-22 | COMP | 2021-06-02 | COMP | Rule 16 | 71 | 35 | 7 | 54 | 14 | 29 | 447
16695 | 2019-08-22 | 2020-01-13 | 2020-05-19 | 2020-10-22 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2021-01-08 | COMP | 2021-02-01 | COMP | Rule 16 | 97 | 90 | 22 | 1 | 31 | 16 | 362
17087 | 2019-08-22 | 2020-01-30 | 2020-06-05 | 2020-06-05 | COMP | 2020-07-17 | COMP | 2020-11-02 | COMP | 2020-12-16 | COMP | 2021-06-08 | COMP | Rule 16 | 109 | 90 | 31 | 76 | 30 | 120 | 451
17582 | 2019-08-22 | 2020-02-20 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-05-29 | COMP | 2020-06-26 | COMP | Rule 16 | 123 | 55 | 15 | 1 | 3 | 21 | 213
17965 | 2019-08-22 | 2020-03-05 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-09-02 | COMP | 2020-09-26 | COMP | Rule 16 | 133 | 62 | 12 | 1 | 57 | 17 | 277
18144 | 2019-08-22 | 2020-03-12 | 2020-06-18 | 2020-07-28 | COMP | 2020-08-21 | COMP | 2020-10-21 | COMP | 2020-10-15 | COMP | 2020-11-21 | COMP | Rule 16 | 138 | 70 | 19 | 43 | 0 | 22 | 316
18155 | 2019-08-22 | 2020-03-12 | 2020-10-30 | 2021-10-02 | COMP | 2021-10-06 | COMP | 2022-09-02 | COMP |  | INPR | 2022-09-01 | COMP | Rule 15/16 | 138 | 165 | 3 | 230 |  |  | 763
18208 | 2019-08-22 | 2020-03-16 | 2020-07-15 | 2020-07-15 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-10-09 | COMP | 2020-11-30 | COMP | Rule 15/16 | 140 | 87 | 11 | 1 | 52 | 34 | 320
19159 | 2019-08-22 | 2020-04-23 | 2020-12-28 | 2021-09-15 | COMP | 2021-11-29 | COMP | 2021-11-29 | COMP | 2021-10-25 | COMP | 2022-02-04 | COMP | Rule 15/16 | 168 | 172 | 51 | 1 | 0 | 49 | 618
19824 | 2019-08-22 | 2020-05-26 | 2020-10-26 | 2020-10-26 | COMP | 2020-12-29 | COMP | 2021-03-01 | COMP | 2021-07-07 | COMP | 2021-08-11 | COMP | Rule 16 | 190 | 109 | 43 | 42 | 91 | 26 | 496
25823 | 2019-08-22 | 2021-02-25 | 2021-12-07 | 2021-12-07 | COMP | 2022-02-14 | COMP | 2022-04-14 | COMP | 2022-04-13 | COMP | 2022-07-08 | COMP | Rule 15/16 | 379 | 198 | 49 | 43 | 0 | 59 | 724
14174 | 2019-08-23 | 2019-08-28 | 2019-09-30 | 2019-09-30 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2020-01-22 | COMP | 2020-02-01 | COMP | Rule 16 | 4 | 23 | 75 | 1 | 3 | 8 | 109
14478 | 2019-08-23 | 2019-09-11 | 2019-10-29 | 2019-10-29 | COMP | 2019-10-31 | COMP | 2019-10-31 | COMP | 2019-11-26 | COMP | 2019-12-05 | COMP | Rule 16 | 13 | 35 | 3 | 1 | 18 | 6 | 71
14907 | 2019-08-23 | 2019-10-02 | 2020-03-13 | 2020-04-16 | COMP | 2020-11-17 | COMP | 2020-12-16 | COMP | 2020-11-30 | COMP | 2021-01-05 | COMP | Rule 16 | 28 | 111 | 151 | 20 | 0 | 13 | 343
15238 | 2019-08-23 | 2019-10-22 | 2019-11-20 | 2019-11-20 | COMP | 2019-11-25 | COMP | 2019-11-25 | COMP | 2020-01-22 | COMP | 2020-01-28 | COMP | Rule 16 | 42 | 21 | 4 | 1 | 38 | 5 | 106
15441 | 2019-08-23 | 2019-11-01 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2021-11-02 | COMP | 2021-11-23 | COMP | Rule 16 | 50 | 28 | 24 | 1 | 454 | 15 | 567
15502 | 2019-08-23 | 2019-11-05 | 2019-12-17 | 2019-12-17 | COMP | 2020-01-31 | COMP | 2020-06-02 | COMP | 2021-11-17 | COMP | 2021-12-30 | COMP | Rule 15/16 | 52 | 28 | 31 | 86 | 370 | 30 | 592
15519 | 2019-08-23 | 2019-11-05 | 2020-01-15 | 2020-01-15 | COMP | 2020-03-03 | COMP | 2020-08-20 | COMP | 2022-07-16 | INPR | 2020-09-04 | COMP | Rule 16 | 52 | 47 | 33 | 122 |  |  | 262
15827 | 2019-08-23 | 2019-11-22 | 2019-12-29 | 2019-12-29 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2021-05-30 | INPR | 2020-05-20 | COMP | Rule 16 | 64 | 23 | 32 | 1 |  |  | 186
15905 | 2019-08-23 | 2019-11-26 | 2019-12-29 | 2019-12-29 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-06-02 | COMP | 2020-06-05 | COMP | Rule 16 | 66 | 21 | 20 | 1 | 89 | 4 | 197
15956 | 2019-08-23 | 2019-12-03 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-02 | COMP | 2020-06-02 | COMP | 2020-05-20 | COMP | 2020-07-07 | COMP | Rule 16 | 69 | 73 | 12 | 43 | 0 | 26 | 219
16028 | 2019-08-23 | 2019-12-06 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2021-03-01 | COMP | 2021-04-14 | COMP | Rule 16 | 72 | 46 | 17 | 1 | 248 | 33 | 412
16324 | 2019-08-23 | 2019-12-20 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-06 | COMP | 2020-06-05 | COMP | 2020-07-07 | COMP | 2020-07-27 | COMP | Rule 16 | 82 | 93 | 3 | 22 | 23 | 15 | 233
16794 | 2019-08-23 | 2020-01-15 | 2020-02-13 | 2020-02-13 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-07-21 | COMP | 2020-07-30 | COMP | Rule 16 | 98 | 21 | 44 | 1 | 69 | 8 | 236
16866 | 2019-08-23 | 2020-01-21 | 2020-03-20 | 2020-03-20 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-05-11 | COMP | 2020-06-05 | COMP | Rule 16 | 101 | 43 | 16 | 1 | 22 | 19 | 197
16897 | 2019-08-23 | 2020-01-23 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-31 | COMP | 2020-07-27 | COMP | 2021-05-27 | COMP | 2020-12-03 | COMP | Rule 15/16 | 103 | 105 | 31 |  | 211 |  | 322
17210 | 2019-08-23 | 2020-02-04 | 2020-06-25 | 2020-08-12 | COMP | 2020-09-15 | COMP | 2021-01-29 | COMP | 2021-05-25 | COMP | 2021-06-02 | COMP | Rule 16 | 111 | 101 | 24 | 93 | 82 | 6 | 446
17521 | 2019-08-23 | 2020-02-19 | 2020-06-17 | 2020-06-17 | COMP | 2020-11-05 | COMP | 2020-11-18 | COMP | 2020-12-23 | COMP | 2021-02-18 | COMP | Rule 15/16 | 121 | 85 | 101 | 9 | 24 | 38 | 373
17779 | 2019-08-23 | 2020-02-26 | 2020-03-18 | 2020-03-18 | COMP | 2020-03-20 | NOTN | 2020-07-02 | COMP | 2023-11-13 | INPR | 2020-07-30 | COMP | Other | 126 | 16 |  | 76 |  |  | 236
18806 | 2019-08-23 | 2020-04-08 | 2020-10-09 | 2020-10-09 | COMP | 2020-12-10 | COMP | 2021-01-05 | COMP | 2021-04-06 | COMP | 2021-04-19 | COMP | Rule 16 | 156 | 131 | 42 | 17 | 64 | 10 | 415
18878 | 2019-08-23 | 2020-04-10 | 2020-10-08 | 2020-10-08 | COMP | 2020-12-10 | COMP | 2020-12-10 | COMP | 2021-06-21 | COMP | 2021-07-16 | COMP | Rule 16 | 158 | 128 | 43 | 1 | 133 | 19 | 477
19060 | 2019-08-23 | 2020-04-20 | 2020-06-12 | 2021-04-09 | COMP | 2021-04-15 | COMP | 2021-06-12 | COMP | 2021-06-14 | COMP | 2021-07-14 | COMP | Rule 16 | 164 | 39 | 5 | 41 | 1 | 22 | 475
14310 | 2019-08-24 | 2019-09-04 | 2019-11-14 | 2019-12-04 | COMP | 2019-12-16 | COMP | 2019-12-16 | INPR | 2019-12-10 | COMP | 2020-01-15 | COMP | Rule 16 | 7 | 51 | 9 |  |  |  | 97
14311 | 2019-08-24 | 2019-09-04 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-01 | COMP | 2019-12-23 | COMP | 2019-12-12 | COMP | 2020-01-15 | COMP | Rule 16 | 7 | 41 | 3 | 34 | 0 | 16 | 97
14331 | 2019-08-24 | 2019-09-04 | 2019-10-30 | 2019-10-30 | COMP | 2019-11-01 | COMP | 2019-11-01 | COMP | 2019-11-08 | COMP | 2019-12-16 | COMP | Rule 16 | 7 | 41 | 3 | 1 | 6 | 24 | 77
24905 | 2019-08-24 | 2021-01-19 | 2021-04-22 | 2021-09-13 | COMP | 2021-10-05 | COMP | 2021-10-25 | COMP | 2021-11-17 | COMP | 2022-01-18 | COMP | Rule 16 | 351 | 67 | 17 | 15 | 17 | 42 | 603
14486 | 2019-08-25 | 2019-09-12 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-05 | COMP | 2019-12-30 | COMP | 2020-01-06 | COMP | 2020-01-27 | COMP | Rule 16 | 13 | 49 | 10 | 17 | 5 | 15 | 104
15338 | 2019-08-25 | 2019-10-26 | 2020-05-06 | 2020-05-06 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2020-10-06 | COMP | 2020-11-03 | COMP | Rule 16 | 44 | 131 | 95 | 1 | 14 | 21 | 302
16572 | 2019-08-25 | 2020-01-08 | 2020-03-06 | 2020-03-06 | COMP | 2020-03-30 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-06-09 | COMP | Rule 16 | 92 | 41 | 17 | 18 | 1 | 34 | 198
17952 | 2019-08-25 | 2020-03-05 | 2020-04-20 | 2020-04-20 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2021-03-23 | COMP | 2021-04-29 | COMP | Rule 16 | 131 | 33 | 86 | 1 | 148 | 28 | 422
4222 | 2019-08-26 | 2019-08-27 | [7 empty] | 2019-09-12 | COMP | 2020-02-07 | COMP | Other | 2 | [5 empty] | 113
14278 | 2019-08-26 | 2019-09-03 | 2019-09-10 | 2019-09-10 | COMP | 2019-09-17 | COMP | 2019-09-17 | COMP | 2019-09-20 | COMP | 2019-09-30 | COMP | Rule 16 | 6 | 6 | 6 | 1 | 4 | 7 | 25
14329 | 2019-08-26 | 2019-09-05 | 2020-08-16 | 2023-02-08 | COMP | 2023-03-06 | COMP | 2023-10-20 | COMP | 2023-10-20 | COMP | 2023-12-07 | COMP | Rule 15/16 | 8 | 239 | 18 | 161 | 1 | 32 | 1076
14447 | 2019-08-26 | 2019-09-10 | 2019-10-15 | 2019-10-15 | COMP | 2019-10-30 | COMP | 2019-10-30 | COMP | 2020-02-28 | COMP | 2020-03-02 | COMP | Rule 16 | 11 | 26 | 12 | 1 | 81 | 2 | 128
14648 | 2019-08-26 | 2019-09-20 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2019-12-07 | COMP | 2020-01-15 | COMP | Rule 16 | 19 | 37 | 17 | 1 | 1 | 26 | 97
14658 | 2019-08-26 | 2019-09-21 | 2019-12-11 | 2019-12-11 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2020-02-07 | COMP | 2020-02-12 | COMP | Rule 16 | 19 | 55 | 8 | 1 | 33 | 4 | 116
14670 | 2019-08-26 | 2019-09-23 | 2019-12-12 | 2020-02-20 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-03-31 | COMP | 2020-04-24 | COMP | Rule 16 | 20 | 56 | 31 | 1 | 0 | 17 | 167
14780 | 2019-08-26 | 2019-09-26 | 2019-10-30 | 2019-10-30 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-07-27 | COMP | 2020-08-20 | COMP | Rule 16 | 23 | 25 | 21 | 1 | 166 | 19 | 250
14887 | 2019-08-26 | 2019-10-02 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-13 | COMP | 2019-11-13 | COMP | 2019-11-15 | COMP | 2019-12-03 | COMP | Rule 16 | 27 | 27 | 4 | 1 | 3 | 11 | 68
14977 | 2019-08-26 | 2019-10-07 | 2019-11-02 | 2019-11-02 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2019-11-27 | COMP | 2019-12-23 | COMP | Rule 16 | 30 | 20 | 3 | 1 | 15 | 17 | 82
14983 | 2019-08-26 | 2019-10-07 | 2020-02-26 | 2020-02-26 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-06-09 | COMP | 2020-07-26 | COMP | Rule 16 | 30 | 96 | 26 | 1 | 49 | 34 | 231
14985 | 2019-08-26 | 2019-10-08 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-04 | COMP | 2020-04-03 | COMP | 2020-03-20 | COMP | 2020-05-11 | COMP | Rule 15/16 | 31 | 76 | 25 | 23 | 0 | 27 | 178
15177 | 2019-08-26 | 2019-10-17 | 2020-07-06 | 2020-09-22 | COMP | 2020-10-06 | COMP | 2021-04-23 | COMP | 2022-09-28 | COMP | 2022-12-05 | COMP | Rule 16 | 38 | 180 | 11 | 137 | 362 | 46 | 824
15353 | 2019-08-26 | 2019-10-28 | 2020-03-06 | 2020-03-06 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-08-24 | COMP | 2020-09-11 | COMP | Rule 16 | 45 | 88 | 94 | 1 | 28 | 14 | 265
15479 | 2019-08-26 | 2019-11-04 | 2020-02-18 | 2020-02-18 | COMP | 2020-03-24 | COMP | 2020-09-29 | COMP | 2020-09-28 | COMP | 2020-10-30 | COMP | Rule 16 | 50 | 70 | 26 | 134 | 0 | 24 | 300
15492 | 2019-08-26 | 2019-11-05 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-18 | COMP | 2020-06-27 | COMP | 2020-05-29 | COMP | 2020-07-28 | COMP | Rule 16 | 51 | 124 | 10 | 29 | 0 | 22 | 233
15543 | 2019-08-26 | 2019-11-06 | 2020-01-27 | 2020-01-27 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2022-01-30 | INPR | 2020-04-01 | COMP | Rule 16 | 52 | 53 | 4 | 1 |  |  | 150
15580 | 2019-08-26 | 2019-11-07 | 2020-01-21 | 2020-01-21 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-06-01 | COMP | 2020-06-27 | COMP | Rule 15/16 | 53 | 48 | 38 | 1 | 56 | 20 | 211
15643 | 2019-08-26 | 2019-11-13 | 2020-02-25 | 2021-01-14 | COMP | 2021-02-03 | COMP | 2020-04-02 | COMP | 2021-06-22 | COMP | 2021-07-02 | COMP | Rule 16 | 56 | 69 | 14 |  | 309 | 9 | 467
15687 | 2019-08-26 | 2019-11-15 | 2019-12-12 | 2019-12-12 | COMP | 2020-01-15 | COMP | 2020-03-17 | COMP | 2020-04-23 | COMP | 2020-04-30 | COMP | Rule 16 | 58 | 18 | 23 | 43 | 28 | 6 | 171
15859 | 2019-08-26 | 2019-11-25 | 2020-03-02 | 2020-03-02 | COMP | 2020-04-22 | COMP | 2020-07-24 | COMP | 2020-07-28 | COMP | 2020-09-11 | COMP | Rule 16 | 64 | 65 | 38 | 67 | 3 | 33 | 265
15891 | 2019-08-26 | 2019-11-25 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-29 | COMP | 2020-09-11 | COMP | 2020-11-02 | COMP | 2020-12-03 | COMP | Rule 16 | 64 | 137 | 13 | 54 | 37 | 21 | 321
16021 | 2019-08-26 | 2019-12-05 | 2020-05-04 | 2020-05-04 | COMP | 2021-01-20 | COMP | 2021-05-13 | COMP | 2021-05-05 | COMP | 2021-06-14 | COMP | Other | 70 | 104 | 180 | 81 | 0 | 22 | 453
16082 | 2019-08-26 | 2019-12-09 | 2020-02-07 | 2020-02-07 | COMP | 2020-04-24 | COMP | 2021-01-05 | COMP | 2021-12-12 | COMP | 2022-02-04 | COMP | Rule 16 | 72 | 42 | 55 | 176 | 236 | 39 | 616
16117 | 2019-08-26 | 2019-12-10 | 2020-03-30 | 2020-03-30 | COMP | 2020-08-24 | COMP | 2020-09-15 | COMP | 2020-10-23 | COMP | 2020-12-10 | COMP | Rule 16 | 73 | 76 | 105 | 16 | 29 | 32 | 326
16259 | 2019-08-26 | 2019-12-18 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-17 | COMP | 2020-07-16 | COMP | 2020-09-03 | COMP | 2020-09-23 | COMP | Rule 16 | 79 | 75 | 10 | 64 | 36 | 14 | 273
16294 | 2019-08-26 | 2019-12-19 | 2020-08-26 | 2021-10-25 | COMP | 2021-10-29 | COMP | 2022-01-18 | COMP | 2022-07-06 | COMP | 2022-07-21 | COMP | Rule 15/16 | 80 | 175 | 5 | 54 | 118 | 12 | 731
16304 | 2019-08-26 | 2019-12-19 | 2020-04-23 | 2020-08-15 | COMP | 2020-09-02 | COMP | 2021-01-25 | COMP | 2021-02-01 | COMP | 2021-03-16 | COMP | Rule 15/16 | 80 | 87 | 13 | 97 | 6 | 31 | 390
16420 | 2019-08-26 | 2019-12-30 | 2020-03-02 | 2020-06-05 | COMP | 2020-07-28 | COMP | 2021-01-13 | COMP | 2021-12-07 | COMP | 2022-01-21 | COMP | Rule 16 | 86 | 43 | 38 | 116 | 227 | 33 | 606
16957 | 2019-08-26 | 2020-01-25 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-17 | COMP | 2020-11-20 | COMP | 2020-11-03 | COMP | 2021-01-06 | COMP | Rule 16 | 103 | 108 | 15 | 89 | 0 | 30 | 343
17127 | 2019-08-26 | 2020-01-31 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-27 | COMP | 2020-10-01 | COMP | 2020-04-24 | COMP | 2020-11-05 | COMP | Rule 16 | 108 | 59 | 3 | 112 | 0 | 26 | 304
17465 | 2019-08-26 | 2020-02-14 | 2020-10-30 | 2020-10-30 | COMP | 2021-01-15 | COMP | 2021-05-13 | INPR | 2023-12-03 | CANC | 2021-08-18 | COMP | Rule 16 | 118 | 183 | 51 |  |  |  | 499
18462 | 2019-08-26 | 2020-03-25 | 2020-06-25 | 2020-07-24 | COMP | 2020-08-13 | COMP | 2020-08-28 | COMP | 2020-12-16 | COMP | 2021-01-15 | COMP | Other | 145 | 66 | 15 | 12 | 75 | 21 | 350
18900 | 2019-08-26 | 2020-04-10 | 2020-06-17 | 2020-07-14 | COMP | 2020-07-17 | COMP | 2020-10-05 | COMP | 2020-12-28 | COMP | 2021-02-12 | COMP | Rule 15/16 | 157 | 48 | 4 | 56 | 57 | 33 | 369
20891 | 2019-08-26 | 2020-07-13 | 2020-09-23 | 2020-09-23 | COMP | 2020-10-14 | COMP | 2020-11-09 | COMP | 2023-05-27 | INPR | 2020-12-04 | COMP | Rule 16 | 222 | 52 | 16 | 19 |  |  | 322
25901 | 2019-08-26 | 2021-03-01 | 2021-04-02 | 2021-04-02 | COMP | 2021-06-25 | COMP | 2021-06-25 | COMP |  | INPR | 2021-09-23 | COMP | Rule 15/16 | 379 | 25 | 60 | 1 |  |  | 524
14262 | 2019-08-27 | 2019-09-03 | 2020-03-24 | 2020-03-24 | COMP | 2020-04-02 | COMP | 2020-04-08 | COMP | 2020-04-20 | COMP | 2020-05-12 | COMP | Rule 15/16 | 5 | 139 | 8 | 5 | 9 | 17 | 178
14556 | 2019-08-27 | 2019-09-16 | 2019-11-14 | 2019-11-14 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2021-04-03 | COMP | 2021-04-16 | COMP | Rule 16 | 14 | 43 | 60 | 1 | 288 | 10 | 412
14778 | 2019-08-27 | 2019-09-27 | 2019-12-26 | 2019-12-26 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-01-27 | COMP | 2020-01-31 | COMP | Rule 16 | 23 | 61 | 6 | 1 | 16 | 5 | 107
14810 | 2019-08-27 | 2019-09-28 | 2020-02-24 | 2020-12-10 | COMP | 2020-12-18 | COMP | 2020-04-27 | COMP | 2020-12-30 | COMP | 2021-03-03 | COMP | Rule 15/16 | 23 | 99 | 7 |  | 172 | 43 | 380
15145 | 2019-08-27 | 2019-10-16 | 2019-11-07 | 2019-11-07 | COMP | 2019-12-03 | COMP | 2019-12-31 | COMP | 2020-07-14 | COMP | 2020-08-03 | COMP | Rule 16 | 36 | 17 | 16 | 20 | 137 | 15 | 236
15153 | 2019-08-27 | 2019-10-16 | 2020-01-09 | 2020-01-09 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-02-18 | COMP | 2020-04-03 | COMP | Rule 16 | 36 | 57 | 29 | 1 | 0 | 32 | 151
15495 | 2019-08-27 | 2019-11-05 | 2020-03-06 | 2020-03-23 | COMP | 2020-06-02 | COMP | 2020-06-17 | COMP | 2020-06-30 | COMP | 2020-07-02 | COMP | Rule 16 | 50 | 82 | 51 | 12 | 10 | 3 | 214
15506 | 2019-08-27 | 2019-11-05 | 2020-03-02 | 2020-03-02 | COMP | 2020-06-09 | COMP | 2020-08-18 | COMP | 2021-02-27 | COMP | 2021-04-01 | COMP | Rule 15/16 | 50 | 78 | 71 | 51 | 131 | 24 | 401
15770 | 2019-08-27 | 2019-11-20 | 2020-02-09 | 2020-02-09 | COMP | 2020-05-15 | COMP | 2020-04-22 | COMP | 2020-05-21 | COMP | 2020-07-29 | COMP | Rule 15/16 | 60 | 53 | 69 |  | 22 | 49 | 233
15831 | 2019-08-27 | 2019-11-22 | 2020-03-16 | 2020-03-16 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-09-01 | COMP | 2020-09-15 | COMP | Rule 16 | 62 | 76 | 72 | 1 | 50 | 10 | 266
15883 | 2019-08-27 | 2019-11-25 | 2020-04-23 | 2021-08-24 | COMP | 2021-09-27 | COMP | 2022-03-25 | COMP | 2022-03-25 | COMP | 2022-04-25 | COMP | Rule 16 | 63 | 103 | 24 | 125 | 1 | 22 | 670
15997 | 2019-08-27 | 2019-12-04 | 2019-12-28 | 2019-12-28 | COMP | 2020-02-12 | COMP | 2020-02-12 | INPR | 2020-03-18 | COMP | 2020-03-18 | COMP | Rule 16 | 68 | 17 | 31 |  |  |  | 139
16004 | 2019-08-27 | 2019-12-05 | 2020-01-25 | 2020-01-25 | COMP | 2020-02-11 | NOTN | 2020-02-11 | COMP | 2020-03-10 | COMP | 2020-04-02 | COMP | Rule 16 | 69 | 34 |  | 12 | 20 | 18 | 150
16152 | 2019-08-27 | 2019-12-12 | 2020-02-20 | 2020-02-20 | COMP | 2020-06-02 | COMP | 2020-08-18 | COMP | 2021-04-07 | COMP | 2021-06-29 | COMP | Rule 16 | 74 | 47 | 73 | 56 | 159 | 59 | 463
16718 | 2019-08-27 | 2020-01-14 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-01 | COMP | 2020-04-20 | COMP | 2020-07-22 | COMP | 2020-08-01 | COMP | Rule 16 | 95 | 38 | 18 | 14 | 67 | 8 | 235
17434 | 2019-08-27 | 2020-02-13 | 2020-09-11 | 2020-09-16 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2022-02-26 | INPR | 2021-02-11 | COMP | Rule 16 | 116 | 149 | 8 | 1 |  |  | 367
17494 | 2019-08-27 | 2020-02-18 | 2020-05-13 | 2020-05-13 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2020-10-20 | COMP | 2020-11-20 | COMP | Rule 16 | 118 | 62 | 87 | 1 | 27 | 23 | 313
17526 | 2019-08-27 | 2020-02-19 | 2020-04-09 | 2020-09-25 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2022-07-11 | COMP | 2022-07-25 | COMP | Rule 15/16 | 119 | 37 | 13 | 1 | 437 | 11 | 732
17819 | 2019-08-27 | 2020-02-28 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-06-11 | COMP | 2020-06-18 | COMP | Rule 16 | 126 | 7 | 8 | 1 | 61 | 6 | 204
18391 | 2019-08-27 | 2020-03-23 | 2020-04-27 | 2020-04-27 | COMP | 2021-04-22 | COMP | 2021-04-22 | COMP | 2022-03-11 | COMP | 2022-04-15 | COMP | Rule 16 | 142 | 26 | 250 | 1 | 224 | 26 | 664
18461 | 2019-08-27 | 2020-03-25 | 2020-06-30 | 2020-07-28 | COMP | 2020-08-13 | COMP | 2020-12-19 | COMP | 2020-12-22 | COMP | 2021-01-11 | COMP | Other | 144 | 69 | 13 | 88 | 2 | 13 | 345
19282 | 2019-08-27 | 2020-04-29 | 2020-06-14 | 2020-07-09 | COMP | 2020-07-20 | COMP | 2020-10-20 | COMP | 2020-10-28 | COMP | 2020-12-08 | COMP | Rule 16 | 169 | 32 | 8 | 66 | 7 | 27 | 323
24767 | 2019-08-27 | 2021-01-12 | 2021-01-28 | 2021-01-28 | COMP | 2021-03-08 | COMP | 2021-03-08 | COMP | 2021-04-01 | COMP | 2021-04-27 | COMP | Rule 16 | 346 | 12 | 27 | 1 | 19 | 19 | 419
40722 | 2019-08-27 | 2023-01-25 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-08 | NOTN | 2023-06-16 | COMP | 2023-05-09 | COMP | 2023-09-11 | COMP | Other | 857 | 66 |  | 36 | 0 | 59 | 1015
14264 | 2019-08-28 | 2019-09-03 | 2020-03-30 | 2020-03-30 | COMP | 2020-04-13 | COMP | 2020-07-21 | COMP | 2020-07-28 | COMP | 2020-08-27 | COMP | Rule 15/16 | 4 | 143 | 11 | 71 | 6 | 23 | 253
14452 | 2019-08-28 | 2019-09-10 | 2020-01-07 | 2020-01-07 | COMP | 2020-01-31 | COMP | 2020-12-29 | COMP | 2022-01-30 | INPR | 2021-01-22 | COMP | Rule 16 | 9 | 81 | 18 | 231 |  |  | 352
14507 | 2019-08-28 | 2019-09-13 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-08 | COMP | 2020-01-08 | COMP | 2020-01-10 | COMP | 2020-03-09 | COMP | Rule 16 | 12 | 56 | 24 | 1 | 3 | 40 | 131
14557 | 2019-08-28 | 2019-09-16 | 2019-11-15 | 2019-11-15 | COMP | 2020-10-26 | NOTN | 2020-10-26 | COMP | 2021-04-02 | COMP | 2021-04-24 | COMP | Other | 13 | 44 |  | 239 | 108 | 16 | 416
14686 | 2019-08-28 | 2019-09-23 | 2019-10-22 | 2019-10-22 | COMP | 2019-11-12 | COMP | 2019-12-31 | COMP | 2020-01-30 | COMP | 2020-03-03 | COMP | Rule 16 | 18 | 22 | 15 | 33 | 21 | 23 | 127
14801 | 2019-08-28 | 2019-09-27 | 2019-10-17 | 2019-10-17 | COMP | 2019-11-21 | NOTN | 2019-11-21 | COMP | 2019-11-21 | COMP | 2020-01-23 | COMP | Rule 16 | 22 | 15 |  | 25 | 1 | 41 | 100
14814 | 2019-08-28 | 2019-09-30 | 2020-02-26 | 2020-02-26 | COMP | 2020-06-23 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-06 | COMP | Rule 16 | 23 | 101 | 84 | 11 | 1 | 23 | 238
14853 | 2019-08-28 | 2019-09-30 | 2020-01-31 | 2020-01-31 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-04-14 | COMP | 2020-05-01 | COMP | Rule 16 | 23 | 84 | 26 | 1 | 27 | 14 | 170
14889 | 2019-08-28 | 2019-10-02 | 2019-10-20 | 2019-10-29 | COMP | 2020-09-24 | COMP | 2020-09-24 | COMP | 2020-10-09 | COMP | 2020-11-04 | COMP | Rule 16 | 25 | 13 | 229 | 1 | 12 | 19 | 301
15159 | 2019-08-28 | 2019-10-16 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-16 | NOTN | 2019-12-16 | COMP | 2019-12-05 | COMP | 2020-01-02 | COMP | Rule 16 | 35 | 40 |  | 2 | 0 | 12 | 86
15219 | 2019-08-28 | 2019-10-21 | 2019-12-14 | 2019-12-14 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-02-27 | COMP | 2020-03-08 | COMP | Rule 16 | 38 | 37 | 33 | 1 | 18 | 7 | 130
15388 | 2019-08-28 | 2019-10-29 | 2020-01-08 | 2020-04-15 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-07-16 | COMP | Rule 16 | 44 | 47 | 46 | 1 | 1 | 21 | 223
15556 | 2019-08-28 | 2019-11-06 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-03 | COMP | 2020-01-23 | COMP | 2020-01-22 | COMP | 2020-02-05 | COMP | Rule 16 | 50 | 10 | 8 | 35 | 0 | 10 | 109
15659 | 2019-08-28 | 2019-11-14 | 2020-10-22 | 2020-10-22 | COMP | 2021-04-19 | COMP | 2021-10-01 | COMP | 2021-09-16 | COMP | 2022-08-16 | COMP | Rule 15/16 | 55 | 238 | 121 | 117 | 0 | 220 | 747
15790 | 2019-08-28 | 2019-11-20 | 2020-09-02 | 2020-09-02 | COMP | 2020-03-31 | NOTN | 2020-11-10 | COMP | 2020-12-21 | COMP | 2021-03-13 | COMP | Other | 59 | 199 |  | 49 | 27 | 56 | 386
15819 | 2019-08-28 | 2019-11-21 | 2020-04-01 | 2020-04-01 | COMP | 2020-05-26 | COMP | 2020-06-05 | COMP | 2020-07-21 | COMP | 2020-10-30 | COMP | Rule 16 | 60 | 89 | 39 | 9 | 33 | 73 | 298
15994 | 2019-08-28 | 2019-12-04 | 2020-01-29 | 2020-01-29 | COMP | 2020-02-27 | COMP | 2020-06-22 | COMP | 2020-07-01 | COMP | 2020-07-13 | COMP | Rule 16 | 67 | 38 | 21 | 82 | 8 | 9 | 220
16147 | 2019-08-28 | 2019-12-12 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-14 | COMP | 2020-04-29 | COMP | 2020-05-15 | COMP | 2020-05-29 | COMP | Rule 15/16 | 73 | 36 | 9 | 53 | 13 | 10 | 189
16321 | 2019-08-28 | 2019-12-20 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-04 | COMP | 2020-10-05 | COMP | 2020-08-25 | COMP | 2020-11-13 | COMP | Rule 16 | 79 | 87 | 7 | 109 | 0 | 29 | 307
16529 | 2019-08-28 | 2020-01-07 | 2020-03-06 | 2020-03-06 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-09-11 | COMP | 2020-10-13 | COMP | Rule 16 | 89 | 42 | 54 | 1 | 81 | 23 | 285
16530 | 2019-08-28 | 2020-01-07 | 2020-04-07 | 2020-04-07 | COMP | 2020-05-19 | COMP | 2020-07-13 | COMP | 2020-09-08 | COMP | 2020-08-13 | COMP | Rule 16 | 89 | 64 | 31 | 39 | 41 |  | 243
16988 | 2019-08-28 | 2020-01-27 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-09 | COMP | 2020-03-16 | COMP | 2020-04-23 | COMP | 2020-04-27 | COMP | Rule 16 | 102 | 26 | 5 | 6 | 29 | 3 | 166
17309 | 2019-08-28 | 2020-02-08 | 2020-06-15 | 2021-04-21 | COMP | 2021-05-06 | COMP | 2021-05-21 | COMP | 2021-05-13 | COMP | 2021-06-24 | COMP | Rule 16 | 111 | 89 | 12 | 12 | 0 | 24 | 459
17970 | 2019-08-28 | 2020-03-05 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2023-12-03 | INPR | 2022-10-28 | COMP | Rule 16 | 129 | 70 | 8 | 1 |  |  | 799
19194 | 2019-08-28 | 2020-04-24 | 2020-10-22 | 2020-10-22 | COMP | 2020-11-05 | COMP | 2022-09-01 | COMP | 2022-08-17 | COMP | 2022-10-31 | COMP | Rule 16 | 165 | 128 | 11 | 458 | 0 | 42 | 800
19409 | 2019-08-28 | 2020-05-05 | 2020-06-25 | 2020-06-25 | COMP | 2020-09-18 | COMP | 2020-09-23 | COMP | 2020-09-29 | COMP | 2020-10-01 | COMP | Rule 16 | 172 | 37 | 61 | 4 | 5 | 3 | 277
20909 | 2019-08-28 | 2020-07-14 | 2020-08-27 | 2020-08-27 | COMP | 2021-10-12 | COMP | 2021-10-12 | COMP | 2021-11-02 | COMP | 2021-11-22 | COMP | Rule 16 | 221 | 33 | 283 | 1 | 16 | 14 | 563
14489 | 2019-08-29 | 2019-09-11 | 2019-10-16 | 2019-10-16 | COMP | 2019-10-28 | COMP | 2019-12-19 | COMP | 2020-01-07 | COMP | 2020-01-17 | COMP | Rule 16 | 9 | 26 | 9 | 36 | 12 | 9 | 96
14531 | 2019-08-29 | 2019-09-16 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-06-02 | COMP | Rule 16 | 12 | 83 | 28 | 1 | 1 | 70 | 190
14562 | 2019-08-29 | 2019-09-16 | 2019-11-13 | 2019-11-14 | COMP | 2020-02-27 | NOTN | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-03-27 | COMP | Rule 16 | 12 | 42 |  | 77 | 1 | 15 | 144
14578 | 2019-08-29 | 2019-09-16 | 2019-10-11 | 2019-10-11 | COMP | 2020-01-25 | NOTN | 2020-01-25 | COMP | 2020-01-25 | COMP | 2020-03-06 | COMP | Rule 16 | 12 | 20 |  | 70 | 0 | 29 | 129
14602 | 2019-08-29 | 2019-09-18 | 2019-12-07 | 2019-12-07 | COMP | 2020-01-14 | NOTN | 2020-01-14 | COMP | 2020-01-10 | COMP | 2020-02-04 | COMP | Rule 16 | 14 | 55 |  | 25 | 0 | 15 | 107
14614 | 2019-08-29 | 2019-09-18 | 2019-12-28 | 2019-12-28 | COMP | 2020-02-11 | NOTN | 2020-02-11 | COMP | 2020-02-24 | COMP | 2020-03-09 | COMP | Rule 16 | 14 | 69 |  | 30 | 9 | 11 | 130
14785 | 2019-08-29 | 2019-09-27 | 2019-12-05 | 2019-12-05 | COMP | 2020-01-03 | COMP | 2020-01-17 | COMP | 2019-12-17 | COMP | 2020-02-25 | COMP | Rule 16 | 21 | 47 | 20 | 11 | 0 | 26 | 121
15067 | 2019-08-29 | 2019-10-10 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-27 | COMP | 2020-06-03 | COMP | 2020-07-07 | COMP | 2020-08-19 | COMP | Rule 16 | 30 | 124 | 13 | 27 | 25 | 32 | 246
15092 | 2019-08-29 | 2019-10-11 | 2019-12-19 | 2019-12-19 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-06-19 | COMP | Rule 16 | 31 | 47 | 52 | 1 | 1 | 76 | 203
15103 | 2019-08-29 | 2019-10-12 | 2019-11-07 | 2019-11-07 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-06-15 | COMP | 2020-07-09 | COMP | Rule 16 | 31 | 19 | 48 | 1 | 103 | 19 | 217
15250 | 2019-08-29 | 2019-10-24 | 2020-02-29 | 2020-02-29 | COMP | 2020-03-30 | COMP | 2020-05-15 | COMP | 2020-06-01 | COMP | 2020-07-14 | COMP | Rule 15/16 | 40 | 85 | 21 | 35 | 11 | 32 | 220
15255 | 2019-08-29 | 2019-10-23 | 2019-12-08 | 2019-12-19 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-02-06 | COMP | Rule 16 | 39 | 30 | 11 | 1 | 1 | 23 | 109
15296 | 2019-08-29 | 2019-10-24 | 2019-12-05 | 2019-12-05 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-01-13 | COMP | 2020-01-13 | COMP | Rule 16 | 40 | 28 | 8 | 1 | 19 | 1 | 92
15342 | 2019-08-29 | 2019-10-29 | 2020-01-23 | 2021-03-16 | COMP | 2022-02-11 | COMP | 2023-02-15 | COMP | 2022-10-24 | COMP | 2023-04-28 | COMP | Rule 15/16 | 43 | 57 | 232 | 253 | 0 | 52 | 921
15420 | 2019-08-29 | 2019-10-31 | 2020-01-17 | 2020-01-17 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-07-29 | COMP | 2020-09-29 | COMP | Rule 16 | 45 | 52 | 37 | 1 | 100 | 44 | 274
15485 | 2019-08-29 | 2019-11-04 | 2020-01-16 | 2020-01-16 | COMP | 2020-01-28 | COMP | 2020-03-10 | COMP | 2020-07-03 | COMP | 2020-10-05 | COMP | Rule 16 | 47 | 49 | 8 | 30 | 83 | 66 | 278
15743 | 2019-08-29 | 2019-11-20 | 2020-02-07 | 2022-06-16 | COMP | 2023-03-14 | COMP | 2023-03-14 | COMP |  | INPR | 2023-11-28 | COMP | Rule 15/16 | 58 | 53 | 184 | 1 |  |  | 1066
15893 | 2019-08-29 | 2019-11-26 | 2019-12-13 | 2020-04-27 | COMP | 2020-06-16 | COMP | 2021-01-19 | INPR | 2021-01-13 | COMP | 2021-02-02 | COMP | Rule 16 | 62 | 12 | 36 |  |  |  | 358
16278 | 2019-08-29 | 2019-12-18 | 2020-02-05 | 2020-02-05 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-06-18 | COMP | Rule 16 | 76 | 33 | 63 | 1 | 6 | 28 | 202
16282 | 2019-08-29 | 2019-12-18 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-08-24 | COMP | 2020-08-27 | COMP | Rule 16 | 76 | 68 | 39 | 1 | 69 | 4 | 252
16328 | 2019-08-29 | 2019-12-20 | 2020-04-11 | 2020-04-11 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-08-18 | COMP | 2020-09-10 | COMP | Rule 16 | 78 | 77 | 8 | 1 | 84 | 17 | 261
16423 | 2019-08-29 | 2019-12-30 | 2020-01-26 | 2020-01-26 | COMP | 2020-04-08 | COMP | 2020-10-07 | COMP | 2020-11-09 | COMP | 2020-11-23 | COMP | Rule 16 | 83 | 18 | 52 | 129 | 24 | 10 | 312
16440 | 2019-08-29 | 2019-12-31 | 2020-02-24 | 2020-02-24 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2022-07-16 | INPR | 2020-06-23 | COMP | Rule 16 | 84 | 37 | 4 | 1 |  |  | 205
17074 | 2019-08-29 | 2020-01-29 | 2020-03-06 | 2020-03-06 | COMP | 2020-05-15 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-06-24 | COMP | Rule 16 | 103 | 27 | 51 | 7 | 1 | 22 | 206
17110 | 2019-08-29 | 2020-01-30 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-01 | COMP | 2020-07-07 | COMP | 2020-07-20 | COMP | 2020-09-24 | COMP | Rule 16 | 104 | 61 | 6 | 47 | 10 | 48 | 271
17242 | 2019-08-29 | 2020-02-05 | 2020-04-05 | 2020-04-05 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-08-27 | COMP | 2020-09-16 | COMP | Rule 16 | 108 | 42 | 8 | 1 | 96 | 14 | 265
17530 | 2019-08-29 | 2020-02-19 | 2020-05-07 | 2020-06-01 | COMP | 2020-06-01 | NOTN | 2020-06-17 | COMP | 2020-06-22 | COMP | 2020-07-29 | COMP | Rule 16 | 117 | 57 |  | 13 | 4 | 28 | 231
17651 | 2019-08-29 | 2020-02-24 | 2020-05-05 | 2020-05-05 | COMP | 2020-08-10 | COMP | 2020-11-25 | COMP | 2020-11-30 | COMP | 2020-12-19 | COMP | Rule 16 | 120 | 52 | 69 | 76 | 2 | 15 | 329
17828 | 2019-08-29 | 2020-02-28 | 2020-05-03 | 2021-02-12 | COMP | 2021-03-29 | COMP | 2021-04-14 | COMP | 2021-07-09 | COMP | 2021-08-11 | COMP | Rule 15/16 | 124 | 46 | 31 | 13 | 61 | 24 | 491
18199 | 2019-08-29 | 2020-03-16 | 2020-11-05 | 2020-11-05 | COMP | 2020-11-24 | COMP | 2021-01-25 | COMP | 2021-02-10 | COMP | 2021-02-17 | COMP | Rule 16 | 135 | 167 | 13 | 40 | 13 | 5 | 368
18638 | 2019-08-29 | 2020-04-01 | 2020-10-01 | 2020-10-01 | COMP | 2020-10-15 | COMP | 2021-02-08 | COMP | 2021-02-10 | COMP | 2021-03-03 | COMP | Rule 15/16 | 147 | 130 | 11 | 77 | 3 | 15 | 378
20433 | 2019-08-29 | 2020-06-19 | 2020-10-10 | 2020-11-07 | COMP | 2020-12-07 | COMP | 2021-03-15 | COMP | 2021-03-06 | COMP | 2021-03-18 | COMP | Rule 15/16 | 203 | 80 | 18 | 67 | 0 | 4 | 389
4234 | 2019-08-30 | 2019-09-23 | 2019-10-21 | 2019-10-21 | COMP | 2020-01-07 | COMP | 2020-01-17 | COMP | 2020-01-07 | COMP | 2020-02-09 | COMP | Rule 16 | 16 | 21 | 52 | 9 | 0 | 15 | 109
14748 | 2019-08-30 | 2019-09-25 | 2020-02-20 | 2020-02-20 | COMP | 2020-02-21 | NOTN | 2020-02-24 | COMP | 2020-02-21 | COMP | 2020-06-22 | COMP | Other | 18 | 100 |  | 3 | 0 | 85 | 203
14802 | 2019-08-30 | 2019-09-27 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-25 | COMP | 2020-03-10 | COMP | 2023-04-30 | INPR | 2020-08-05 | COMP | Rule 16 | 20 | 94 | 8 | 11 |  |  | 235
14813 | 2019-08-30 | 2019-09-28 | 2020-05-08 | 2020-05-08 | COMP | 2020-11-09 | COMP | 2020-11-12 | COMP |  | INPR | 2021-01-13 | COMP | Rule 15/16 | 20 | 153 | 130 | 3 |  |  | 344
14859 | 2019-08-30 | 2019-10-01 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-23 | COMP | 2020-06-09 | COMP | 2020-08-25 | COMP | 2020-11-13 | COMP | Rule 16 | 22 | 110 | 9 | 56 | 56 | 57 | 305
14894 | 2019-08-30 | 2019-10-03 | 2019-10-22 | 2019-10-22 | COMP | 2019-10-25 | COMP | 2019-10-25 | COMP | 2019-11-05 | COMP | 2019-11-08 | COMP | Rule 16 | 24 | 14 | 4 | 1 | 8 | 4 | 50
14951 | 2019-08-30 | 2019-10-06 | 2020-07-23 | 2020-07-23 | COMP | 2020-10-01 | COMP | 2021-02-12 | COMP | 2021-06-07 | COMP | 2021-06-11 | COMP | Rule 16 | 25 | 201 | 50 | 91 | 80 | 5 | 448
15487 | 2019-08-30 | 2019-11-04 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-09 | COMP | 2019-12-26 | COMP | 2020-01-13 | COMP | 2020-01-27 | COMP | Rule 16 | 46 | 20 | 4 | 13 | 12 | 10 | 100
16534 | 2019-08-30 | 2020-01-06 | 2020-04-23 | 2020-04-24 | COMP | 2021-01-22 | COMP | 2021-01-25 | COMP | 2021-02-23 | COMP | 2021-03-15 | COMP | Rule 15/16 | 86 | 77 | 188 | 2 | 21 | 15 | 385
16725 | 2019-08-30 | 2020-01-14 | 2020-09-15 | 2020-09-15 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2021-06-11 | COMP | 2021-10-31 | COMP | Rule 15/16 | 92 | 172 | 49 | 1 | 138 | 99 | 546
16726 | 2019-08-30 | 2020-01-14 | 2020-08-20 | 2021-09-01 | COMP | 2021-09-16 | COMP | 2021-09-16 | COMP | 2021-11-02 | COMP | 2021-11-03 | COMP | Rule 15/16 | 92 | 155 | 11 | 1 | 34 | 2 | 549
16727 | 2019-08-30 | 2020-01-14 | 2020-08-20 | 2020-08-20 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2021-11-23 | COMP | 2022-01-31 | COMP | Rule 15/16 | 92 | 155 | 56 | 1 | 262 | 47 | 608
16728 | 2019-08-30 | 2020-01-14 | 2020-07-31 | 2021-01-07 | COMP | 2021-02-12 | COMP | 2021-07-16 | COMP | 2021-10-11 | COMP | 2021-11-03 | COMP | Rule 15/16 | 92 | 141 | 26 | 108 | 61 | 18 | 549
17978 | 2019-08-30 | 2020-03-06 | 2020-06-11 | 2020-06-11 | COMP | 2020-10-23 | NOTN | 2020-10-23 | COMP | 2020-11-30 | COMP | 2021-01-08 | COMP | Other | 128 | 69 |  | 96 | 24 | 28 | 341
19463 | 2019-08-30 | 2020-05-07 | 2020-09-29 | 2020-09-29 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2021-03-15 | COMP | 2021-04-08 | COMP | Rule 16 | 172 | 102 | 18 | 1 | 96 | 19 | 403
20984 | 2019-08-30 | 2020-07-16 | 2020-08-07 | 2020-08-07 | COMP | 2021-01-12 | COMP | 2021-01-18 | COMP | 2021-04-27 | COMP | 2021-05-11 | COMP | Rule 15/16 | 221 | 17 | 107 | 4 | 70 | 11 | 426
22378 | 2019-08-30 | 2020-09-22 | 2020-12-08 | 2020-12-08 | COMP | 2021-07-20 | COMP | 2021-08-09 | COMP | 2022-05-25 | COMP | 2022-06-11 | COMP | Rule 16 | 268 | 53 | 155 | 15 | 202 | 12 | 700
14495 | 2019-08-31 | 2019-09-13 | 2020-01-30 | 2020-01-30 | COMP | 2020-03-30 | COMP | 2020-12-30 | COMP | 2021-03-09 | COMP | 2021-03-16 | COMP | Rule 15/16 | 9 | 94 | 42 | 192 | 47 | 6 | 385
14586 | 2019-08-31 | 2019-09-17 | 2019-10-07 | 2020-01-13 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2019-12-30 | COMP | 2020-02-13 | COMP | Rule 16 | 11 | 15 | 12 | 1 | 0 | 12 | 112
14304 | 2019-09-01 | 2019-09-05 | 2019-11-05 | 2019-11-05 | COMP | 2019-12-16 | COMP | 2020-06-05 | COMP | 2019-12-27 | COMP | 2020-08-28 | COMP | Rule 16 | 3 | 44 | 27 | 120 | 0 | 61 | 251
15078 | 2019-09-01 | 2019-10-11 | 2019-12-11 | 2019-12-11 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-05-27 | COMP | 2020-05-28 | COMP | Rule 16 | 29 | 41 | 101 | 1 | 16 | 2 | 185
15050 | 2019-09-02 | 2019-10-10 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-26 | COMP | 2019-12-26 | COMP | 2020-01-08 | COMP | 2020-01-29 | COMP | Rule 16 | 28 | 43 | 10 | 1 | 9 | 15 | 101
15052 | 2019-09-02 | 2019-10-10 | 2020-01-27 | 2020-01-27 | COMP | 2020-02-10 | COMP | 2020-03-18 | COMP | 2020-02-26 | COMP | 2020-03-27 | COMP | Rule 15/16 | 28 | 72 | 11 | 27 | 0 | 8 | 142
16126 | 2019-09-02 | 2019-12-11 | 2020-04-21 | 2020-04-21 | COMP | 2020-05-20 | COMP | 2020-05-21 | COMP | 2020-12-15 | COMP | 2021-02-05 | COMP | Rule 16 | 69 | 91 | 22 | 2 | 144 | 36 | 359
18451 | 2019-09-02 | 2020-03-24 | 2020-07-24 | 2020-07-24 | COMP | 2020-09-01 | COMP | 2020-11-17 | COMP | 2020-12-01 | COMP | 2020-12-16 | COMP | Rule 16 | 139 | 88 | 28 | 54 | 9 | 12 | 325
19130 | 2019-09-02 | 2020-04-21 | 2021-01-08 | 2021-02-03 | COMP | 2021-02-11 | COMP | 2021-02-16 | COMP | 2021-02-16 | COMP | 2021-03-13 | COMP | Rule 16 | 159 | 182 | 7 | 3 | 1 | 19 | 383
14315 | 2019-09-03 | 2019-09-04 | 2020-02-15 | 2020-02-15 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2021-07-23 | COMP | 2022-01-18 | COMP | Rule 16 | 2 | 112 | 33 | 1 | 331 | 123 | 598
14364 | 2019-09-03 | 2019-09-06 | 2019-12-18 | 2019-12-18 | COMP | 2019-12-31 | COMP | 2020-01-14 | COMP | 2020-05-13 | COMP | 2020-06-16 | COMP | Rule 16 | 4 | 71 | 9 | 10 | 85 | 24 | 198
14541 | 2019-09-03 | 2019-09-16 | 2020-02-07 | 2020-02-07 | COMP | 2020-02-07 | NOTN | 2020-02-08 | COMP | 2020-02-25 | COMP | 2020-08-06 | COMP | Other | 10 | 99 |  | 1 | 11 | 117 | 235
14595 | 2019-09-03 | 2019-09-18 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-19 | COMP | 2021-07-02 | COMP | 2021-09-08 | COMP | 2022-01-29 | COMP | Rule 15/16 | 12 | 172 | 19 | 262 | 47 | 99 | 606
14606 | 2019-09-03 | 2019-09-18 | 2019-12-06 | 2019-12-06 | COMP | 2020-01-07 | COMP | 2020-01-14 | COMP | 2020-03-05 | COMP | 2020-03-26 | COMP | Rule 16 | 12 | 55 | 21 | 6 | 36 | 16 | 141
14769 | 2019-09-03 | 2019-09-26 | 2020-04-15 | 2020-04-15 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-14 | COMP | Rule 15/16 | 18 | 138 | 59 | 1 | 1 | 29 | 241
14788 | 2019-09-03 | 2019-09-27 | 2021-08-21 | 2021-10-05 | COMP | 2021-11-22 | COMP | 2021-12-03 | COMP | 2022-07-27 | COMP | 2022-09-28 | COMP | Rule 15/16 | 19 | 478 | 34 | 8 | 164 | 45 | 774
14791 | 2019-09-03 | 2019-09-27 | 2021-10-29 | 2021-11-02 | COMP | 2021-11-08 | COMP | 2021-11-17 | COMP | 2022-02-15 | COMP | 2022-03-28 | COMP | Rule 15/16 | 19 | 527 | 5 | 7 | 62 | 29 | 646
14792 | 2019-09-03 | 2019-09-27 | 2019-12-30 | 2019-12-30 | COMP | 2020-01-17 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-06-15 | COMP | Rule 16 | 19 | 63 | 14 | 17 | 1 | 88 | 197
14870 | 2019-09-03 | 2019-10-01 | 2019-10-17 | 2019-10-17 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2020-01-28 | COMP | 2020-01-31 | COMP | Rule 16 | 21 | 13 | 6 | 1 | 63 | 4 | 103
15007 | 2019-09-03 | 2019-10-08 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-04-28 | COMP | 2020-06-02 | COMP | Rule 16 | 26 | 78 | 18 | 1 | 44 | 25 | 188
15202 | 2019-09-03 | 2019-10-19 | 2020-01-16 | 2020-03-04 | COMP | 2020-07-22 | COMP | 2020-08-12 | COMP | 2020-08-27 | COMP | 2020-11-17 | COMP | Rule 16 | 34 | 59 | 100 | 16 | 12 | 57 | 306
15251 | 2019-09-03 | 2019-10-24 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-20 | COMP | 2020-03-03 | COMP | 2020-02-24 | COMP | 2020-05-18 | COMP | Rule 16 | 38 | 66 | 13 | 9 | 0 | 55 | 178
15268 | 2019-09-03 | 2019-10-23 | 2020-06-23 | 2022-02-23 | COMP | 2022-03-29 | COMP | 2020-09-22 | COMP | 2023-05-19 | COMP | 2023-06-18 | COMP | Rule 16 | 37 | 167 | 25 |  | 668 | 20 | 953
15328 | 2019-09-03 | 2019-10-28 | 2019-12-04 | 2019-12-04 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-04-07 | COMP | 2020-04-14 | COMP | Rule 16 | 40 | 25 | 32 | 1 | 55 | 6 | 154
15468 | 2019-09-03 | 2019-11-04 | 2019-12-18 | 2019-12-18 | COMP | 2020-01-07 | COMP | 2020-02-04 | COMP | 2020-02-19 | COMP | 2020-02-27 | COMP | Rule 16 | 45 | 30 | 13 | 20 | 11 | 7 | 121
15566 | 2019-09-03 | 2019-11-07 | 2019-12-12 | 2019-12-16 | COMP | 2019-12-31 | COMP | 2020-01-01 | COMP | 2020-03-18 | COMP | 2020-06-04 | COMP | Rule 16 | 48 | 23 | 11 | 1 | 53 | 56 | 190
15901 | 2019-09-03 | 2019-11-26 | 2020-01-16 | 2020-01-16 | COMP | 2020-03-17 | COMP | 2020-03-24 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | Rule 16 | 60 | 34 | 42 | 6 | 53 | 1 | 191
15916 | 2019-09-03 | 2019-12-02 | 2020-08-27 | 2020-08-27 | COMP | 2021-01-05 | COMP | 2021-03-09 | COMP | 2022-04-06 | COMP | 2022-05-13 | COMP | Rule 16 | 62 | 189 | 88 | 44 | 274 | 28 | 680
16016 | 2019-09-03 | 2019-12-05 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-20 | COMP | 2020-03-23 | COMP | 2020-04-13 | COMP | 2020-05-22 | COMP | Rule 16 | 65 | 58 | 16 | 2 | 16 | 30 | 182
16122 | 2019-09-03 | 2019-12-10 | 2020-01-22 | 2020-01-22 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-05-15 | COMP | 2020-07-06 | COMP | Rule 16 | 68 | 29 | 49 | 1 | 34 | 36 | 212
16218 | 2019-09-03 | 2019-12-16 | 2020-03-16 | 2022-05-05 | COMP | 2023-03-17 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP | 2023-11-01 | COMP | Rule 16 | 72 | 62 | 216 | 101 | 1 | 60 | 1048
16733 | 2019-09-03 | 2020-01-13 | 2020-02-05 | 2020-02-05 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2022-03-31 | COMP | 2022-04-08 | COMP | Rule 15/16 | 90 | 17 | 131 | 1 | 414 | 7 | 655
16743 | 2019-09-03 | 2020-01-14 | 2020-04-09 | 2020-04-20 | COMP | 2020-04-23 | COMP | 2020-07-08 | INPR | 2020-05-06 | COMP | 2020-07-06 | COMP | Rule 16 | 91 | 61 | 4 |  |  |  | 212
16858 | 2019-09-03 | 2020-01-21 | 2020-03-07 | 2020-03-07 | COMP | 2020-03-13 | COMP | 2020-03-25 | COMP | 2020-06-08 | COMP | 2020-06-09 | COMP | Rule 16 | 95 | 33 | 5 | 9 | 53 | 2 | 193
16869 | 2019-09-03 | 2020-01-21 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-05-11 | COMP | 2020-06-01 | COMP | Rule 15/16 | 95 | 50 | 12 | 1 | 19 | 15 | 187
17252 | 2019-09-03 | 2020-02-06 | 2020-03-15 | 2020-03-15 | COMP | 2020-04-22 | COMP | 2020-09-09 | COMP | 2020-10-29 | COMP | 2020-12-22 | COMP | Rule 16 | 107 | 26 | 28 | 99 | 37 | 36 | 329
17400 | 2019-09-03 | 2020-02-13 | 2020-03-06 | 2020-03-06 | COMP | 2020-03-23 | COMP | 2020-03-26 | COMP | 2020-05-26 | NOTN | 2020-06-15 | COMP | Rule 16 | 112 | 16 | 12 | 4 |  |  | 197
17527 | 2019-09-03 | 2020-02-19 | 2020-03-10 | 2020-03-10 | COMP | 2020-03-19 | COMP | 2020-04-01 | COMP | 2020-04-15 | COMP | 2020-04-21 | COMP | Rule 16 | 115 | 15 | 8 | 10 | 11 | 5 | 159
19128 | 2019-09-03 | 2020-04-22 | 2020-07-16 | 2020-07-16 | COMP | 2020-09-08 | COMP | 2020-09-11 | COMP | 2020-09-14 | COMP | 2020-10-20 | COMP | Rule 16 | 160 | 61 | 38 | 4 | 2 | 27 | 287
21036 | 2019-09-03 | 2020-07-20 | 2020-09-20 | 2022-08-19 | COMP | 2022-11-22 | COMP | 2023-03-31 | COMP | 2023-09-26 | COMP | 2023-10-30 | COMP | Rule 16 | 222 | 44 | 66 | 88 | 124 | 25 | 1046
22523 | 2019-09-03 | 2020-09-28 | 2020-12-02 | 2020-12-02 | COMP | 2021-02-08 | COMP | 2021-03-04 | COMP | 2021-05-12 | COMP | 2021-06-22 | COMP | Rule 15/16 | 271 | 45 | 46 | 18 | 50 | 29 | 454
14342 | 2019-09-04 | 2019-09-05 | 2019-09-21 | 2019-12-12 | COMP | 2020-03-21 | REQD | 2020-03-21 | REQD | 2020-03-21 | INPR | 2019-12-09 | COMP | Rule 16 | 2 | 12 |  |  |  |  | 66
14396 | 2019-09-04 | 2019-09-08 | 2020-04-16 | 2020-04-16 | COMP | 2020-04-21 | COMP | 2020-11-25 | COMP | 2021-06-29 | COMP | 2021-07-23 | COMP | Rule 15/16 | 3 | 152 | 4 | 154 | 148 | 18 | 475
14397 | 2019-09-04 | 2019-09-08 | 2020-05-14 | 2020-12-09 | COMP | 2020-12-11 | COMP | 2020-12-08 | COMP | 2020-12-29 | COMP | 2021-03-26 | COMP | Rule 16 | 3 | 172 | 3 |  | 15 | 61 | 392
14513 | 2019-09-04 | 2019-09-13 | 2019-11-09 | 2019-11-09 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2021-03-27 | INPR | 2020-03-04 | COMP | Rule 15/16 | 8 | 41 | 11 | 1 |  |  | 124
14610 | 2019-09-04 | 2019-09-18 | 2019-11-12 | 2019-11-12 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2019-12-04 | COMP | 2020-01-30 | COMP | Rule 16 | 11 | 39 | 17 | 1 | 0 | 37 | 101
14627 | 2019-09-04 | 2019-09-20 | 2020-01-02 | 2020-01-02 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-04-15 | COMP | 2020-04-13 | COMP | Rule 16 | 13 | 70 | 33 | 1 | 41 |  | 152
14682 | 2019-09-04 | 2019-09-23 | 2020-01-17 | 2020-01-17 | COMP | 2020-01-23 | NOTN | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-02-25 | COMP | Other | 14 | 80 |  | 4 | 1 | 23 | 118
14774 | 2019-09-04 | 2019-09-26 | 2019-10-17 | 2019-10-17 | COMP | 2020-02-03 | COMP | 2020-02-03 | INPR | 2020-03-03 | COMP | 2020-06-23 | COMP | Rule 16 | 17 | 16 | 72 |  |  |  | 202
14833 | 2019-09-04 | 2019-09-30 | 2019-12-16 | 2019-12-16 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2021-01-06 | COMP | 2021-01-26 | COMP | Rule 16 | 19 | 53 | 153 | 1 | 115 | 14 | 350
14843 | 2019-09-04 | 2019-09-30 | 2019-12-16 | 2019-12-16 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-03-28 | COMP | Rule 16 | 19 | 53 | 62 | 1 | 1 | 10 | 141
15109 | 2019-09-04 | 2019-10-14 | 2019-12-15 | 2019-12-15 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-09-08 | COMP | 2020-11-10 | COMP | Rule 16 | 29 | 42 | 28 | 1 | 159 | 46 | 301
15187 | 2019-09-04 | 2019-10-17 | 2020-01-27 | 2020-12-11 | COMP | 2021-01-07 | COMP | 2020-02-20 | COMP | 2021-01-08 | COMP | 2021-02-19 | COMP | Rule 16 | 32 | 67 | 18 |  | 225 | 29 | 367
15188 | 2019-09-04 | 2019-10-17 | 2020-02-01 | 2020-02-01 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-11-23 | COMP | 2020-12-23 | COMP | Rule 16 | 32 | 71 | 23 | 1 | 185 | 21 | 329
15227 | 2019-09-04 | 2019-10-21 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-08 | COMP | 2020-10-01 | COMP | 2020-11-12 | COMP | 2020-11-20 | COMP | Rule 16 | 34 | 145 | 14 | 83 | 30 | 7 | 308
15232 | 2019-09-04 | 2019-10-22 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-05-05 | COMP | Rule 15/16 | 35 | 70 | 17 | 1 | 1 | 49 | 168
15262 | 2019-09-04 | 2019-10-23 | 2021-04-15 | 2021-05-14 | COMP | 2022-10-21 | COMP | 2022-10-21 | COMP | 2022-11-01 | COMP | 2023-01-27 | COMP | Rule 15/16 | 36 | 371 | 364 | 1 | 8 | 58 | 854
15710 | 2019-09-04 | 2019-11-18 | 2020-03-20 | 2020-03-20 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-08-31 | COMP | 2020-09-01 | COMP | Rule 16 | 53 | 84 | 22 | 1 | 95 | 2 | 252
15976 | 2019-09-04 | 2019-12-04 | 2020-03-16 | 2020-04-17 | COMP | 2020-04-20 | NOTN | 2020-04-20 | COMP | 2020-03-27 | COMP | 2020-05-01 | COMP | Other | 63 | 70 |  | 2 | 0 | 10 | 166
16006 | 2019-09-04 | 2019-12-05 | 2020-01-21 | 2020-01-21 | COMP | 2020-10-30 | COMP | 2020-10-30 | COMP | 2020-11-19 | COMP | 2020-11-25 | COMP | Rule 16 | 64 | 31 | 201 | 1 | 14 | 5 | 311
16032 | 2019-09-04 | 2019-12-06 | 2020-04-09 | 2020-04-09 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-05-08 | COMP | 2020-06-19 | COMP | Rule 16 | 65 | 86 | 19 | 1 | 4 | 30 | 200
16189 | 2019-09-04 | 2019-12-14 | 2020-05-21 | 2020-05-21 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-09-08 | COMP | 2021-10-07 | COMP | Rule 15/16 | 70 | 110 | 68 | 1 | 261 | 22 | 528
16531 | 2019-09-04 | 2020-01-07 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-05-11 | COMP | 2020-07-07 | COMP | Rule 16 | 85 | 55 | 22 | 1 | 13 | 41 | 212
16700 | 2019-09-04 | 2020-01-13 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-05-18 | COMP | 2020-06-15 | COMP | Rule 16 | 89 | 52 | 21 | 1 | 18 | 20 | 196
16751 | 2019-09-04 | 2020-01-15 | 2020-11-20 | 2020-11-20 | COMP | 2021-01-11 | COMP | 2021-10-12 | COMP | 2021-10-13 | COMP | 2021-12-04 | COMP | Rule 15/16 | 91 | 218 | 33 | 192 | 2 | 35 | 566
16931 | 2019-09-04 | 2020-01-25 | 2020-07-09 | 2020-11-25 | COMP | 2020-12-08 | COMP | 2021-07-06 | COMP | 2021-06-02 | COMP | 2021-07-29 | COMP | Rule 16 | 97 | 117 | 8 | 145 | 0 | 18 | 479
16956 | 2019-09-04 | 2020-01-25 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-07-06 | COMP | 2020-06-19 | COMP | 2020-09-29 | COMP | Rule 16 | 97 | 70 | 6 | 40 | 0 | 61 | 271
17263 | 2019-09-04 | 2020-02-06 | 2020-10-05 | 2020-10-05 | COMP | 2020-11-12 | COMP | 2020-11-20 | COMP | 2020-12-15 | COMP | 2021-04-05 | COMP | Rule 16 | 106 | 170 | 28 | 7 | 16 | 76 | 398
17268 | 2019-09-04 | 2020-02-06 | 2020-05-21 | 2020-06-15 | COMP | 2020-06-18 | COMP | 2020-07-01 | COMP | 2020-07-21 | COMP | 2020-07-28 | COMP | Rule 15/16 | 106 | 75 | 4 | 10 | 15 | 6 | 227
17367 | 2019-09-04 | 2020-02-11 | 2020-02-21 | 2020-02-21 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-08-04 | COMP | 2020-09-17 | COMP | Rule 16 | 109 | 8 | 47 | 1 | 71 | 32 | 263
17783 | 2019-09-04 | 2020-02-28 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-22 | COMP | 2020-05-18 | COMP | 2020-12-08 | COMP | 2020-12-23 | COMP | Rule 16 | 121 | 27 | 13 | 19 | 142 | 12 | 329
18236 | 2019-09-04 | 2020-03-16 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-10 | COMP | 2020-08-10 | COMP | 2020-10-11 | COMP | 2020-11-09 | COMP | Rule 16 | 132 | 101 | 5 | 1 | 44 | 21 | 300
18566 | 2019-09-04 | 2020-03-30 | 2020-08-14 | 2021-01-07 | COMP | 2021-02-18 | COMP | 2021-04-05 | COMP | 2021-03-18 | COMP | 2021-04-29 | COMP | Rule 15/16 | 142 | 99 | 29 | 33 | 0 | 19 | 416
18938 | 2019-09-04 | 2020-04-13 | 2021-05-18 | 2021-05-18 | COMP | 2021-06-08 | COMP | 2023-06-09 | COMP | 2023-06-16 | COMP | 2023-09-20 | COMP | Rule 15/16 | 152 | 278 | 15 | 505 | 6 | 66 | 1017
18992 | 2019-09-04 | 2020-04-16 | 2020-08-31 | 2020-08-31 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2022-06-03 | COMP | 2022-07-18 | COMP | Rule 16 | 155 | 97 | 29 | 1 | 415 | 30 | 722
22224 | 2019-09-04 | 2020-09-15 | 2020-12-09 | 2020-12-09 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2022-05-28 | INPR | 2021-05-04 | COMP | Rule 16 | 261 | 59 | 10 | 1 |  |  | 419
14852 | 2019-09-05 | 2019-09-30 | 2019-11-05 | 2019-11-05 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-05 | COMP | 2019-12-12 | COMP | Rule 16 | 18 | 27 | 15 | 1 | 6 | 6 | 68
14861 | 2019-09-05 | 2019-10-01 | 2020-02-20 | 2020-02-20 | COMP | 2020-11-02 | COMP | 2021-08-12 | COMP | 2022-02-10 | COMP | 2022-04-01 | COMP | Rule 16 | 19 | 96 | 181 | 195 | 126 | 36 | 648
14875 | 2019-09-05 | 2019-10-02 | 2020-02-24 | 2020-02-24 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-05-13 | COMP | 2020-06-22 | COMP | Rule 16 | 20 | 97 | 47 | 1 | 12 | 28 | 200
14925 | 2019-09-05 | 2019-10-04 | 2019-10-25 | 2019-10-25 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-05 | COMP | Rule 16 | 22 | 16 | 22 | 1 | 1 | 6 | 63
15010 | 2019-09-05 | 2019-10-09 | 2019-12-22 | 2019-12-22 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-01-24 | COMP | 2020-06-03 | COMP | Rule 16 | 25 | 50 | 26 | 1 | 0 | 88 | 187
15031 | 2019-09-05 | 2019-10-10 | 2019-11-26 | 2019-11-26 | COMP | 2019-12-06 | COMP | 2019-12-10 | COMP | 2019-11-13 | COMP | 2020-01-13 | COMP | Rule 16 | 26 | 33 | 7 | 3 | 0 | 23 | 88
15087 | 2019-09-05 | 2019-10-11 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-25 | COMP | 2020-04-23 | COMP | 2020-04-28 | COMP | 2020-06-17 | COMP | Rule 16 | 27 | 94 | 19 | 22 | 4 | 36 | 197
15163 | 2019-09-05 | 2019-10-18 | 2019-12-20 | 2019-12-20 | COMP | 2020-02-18 | COMP | 2020-03-05 | COMP | 2020-02-22 | COMP | 2020-03-27 | COMP | Rule 16 | 32 | 43 | 39 | 13 | 0 | 17 | 140
15172 | 2019-09-05 | 2019-10-16 | 2020-02-25 | 2020-02-25 | COMP | 2020-06-01 | COMP | 2021-07-06 | COMP | 2023-02-25 | INPR | 2021-07-21 | COMP | Rule 16 | 30 | 88 | 69 | 277 |  |  | 472
15185 | 2019-09-05 | 2019-10-17 | 2020-01-21 | 2020-01-21 | COMP | 2020-01-21 | NOTN | 2020-01-21 | COMP | 2020-01-13 | COMP | 2020-02-21 | COMP | Rule 16 | 31 | 63 |  | 1 | 0 | 23 | 115
15848 | 2019-09-05 | 2019-11-25 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-06 | COMP | 2020-04-08 | COMP | 2021-04-24 | INPR | 2020-04-14 | COMP | Rule 16 | 57 | 64 | 6 | 24 |  |  | 152
15882 | 2019-09-05 | 2019-11-25 | 2020-01-12 | 2020-01-12 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-03-04 | COMP | 2020-06-23 | COMP | Rule 16 | 57 | 31 | 12 | 1 | 25 | 79 | 201
15948 | 2019-09-05 | 2019-12-03 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-20 | COMP | 2020-10-09 | COMP | 2020-10-16 | COMP | 2020-12-06 | COMP | Rule 15/16 | 61 | 89 | 8 | 123 | 6 | 33 | 315
16091 | 2019-09-05 | 2019-12-09 | 2020-03-18 | 2020-03-18 | COMP | 2020-06-12 | COMP | 2020-09-16 | COMP | 2023-12-03 | INPR | 2020-11-04 | COMP | Rule 16 | 65 | 69 | 62 | 68 |  |  | 296
16110 | 2019-09-05 | 2019-12-11 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-12 | COMP | 2020-04-17 | COMP | Rule 16 | 67 | 37 | 5 | 1 | 3 | 47 | 155
16149 | 2019-09-05 | 2019-12-12 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-07-28 | COMP | 2020-08-14 | COMP | Rule 15/16 | 68 | 104 | 30 | 1 | 27 | 14 | 239
16368 | 2019-09-05 | 2019-12-23 | 2020-04-07 | 2020-04-07 | COMP | 2020-04-13 | COMP | 2020-04-23 | COMP | 2020-06-09 | COMP | 2020-11-12 | COMP | Rule 16 | 75 | 73 | 5 | 9 | 33 | 111 | 301
16474 | 2019-09-05 | 2020-01-02 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-24 | COMP | 2020-04-22 | COMP | 2020-06-16 | COMP | 2020-06-22 | COMP | Rule 16 | 81 | 39 | 19 | 22 | 39 | 5 | 200
16774 | 2019-09-05 | 2020-01-17 | 2020-02-20 | 2020-02-20 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2022-01-30 | INPR | 2020-04-15 | COMP | Rule 16 | 92 | 23 | 43 | 1 |  |  | 153
17038 | 2019-09-05 | 2020-01-28 | 2020-10-16 | 2020-10-16 | COMP | 2020-12-08 | NOTN | 2020-12-17 | COMP | 2021-01-04 | COMP | 2021-02-09 | COMP | Other | 98 | 186 |  | 42 | 11 | 26 | 359
17403 | 2019-09-05 | 2020-02-12 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2021-04-27 | COMP | 2021-05-13 | COMP | Rule 16 | 109 | 53 | 13 | 1 | 241 | 13 | 425
17803 | 2019-09-05 | 2020-02-27 | 2020-03-16 | 2020-03-16 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-05-30 | COMP | 2021-04-19 | COMP | Rule 16 | 119 | 13 | 49 | 1 | 6 | 223 | 407
17977 | 2019-09-05 | 2020-03-06 | 2020-12-10 | 2020-12-10 | COMP | 2020-12-21 | COMP | 2021-02-19 | COMP | 2023-11-13 | INPR | 2021-03-02 | COMP | Rule 16 | 125 | 195 | 8 | 41 |  |  | 373
18146 | 2019-09-05 | 2020-03-12 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-20 | COMP | 2020-08-12 | COMP | 2021-12-07 | COMP | 2022-01-14 | COMP | Rule 16 | 129 | 65 | 28 | 18 | 331 | 29 | 595
18216 | 2019-09-05 | 2020-03-16 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-08-18 | COMP | 2020-09-24 | COMP | Rule 16 | 131 | 71 | 17 | 1 | 25 | 27 | 267
19078 | 2019-09-05 | 2020-04-20 | 2020-05-13 | 2020-05-13 | COMP | 2020-07-31 | COMP | 2020-08-17 | COMP | 2020-08-24 | COMP | 2020-09-24 | COMP | Rule 16 | 156 | 18 | 57 | 12 | 6 | 23 | 267
19134 | 2019-09-05 | 2020-04-22 | 2020-07-20 | 2020-07-20 | COMP | 2020-09-24 | COMP | 2021-02-25 | COMP | 2021-12-01 | COMP | 2022-10-21 | COMP | Rule 15/16 | 158 | 63 | 48 | 104 | 194 | 227 | 789
19244 | 2019-09-05 | 2020-04-27 | 2020-05-22 | 2020-05-22 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2022-01-30 | INPR | 2020-08-11 | COMP | Rule 16 | 161 | 20 | 47 | 1 |  |  | 236
19467 | 2019-09-05 | 2020-05-08 | 2020-11-09 | 2021-04-09 | COMP | 2021-05-07 | COMP | 2021-08-30 | COMP | 2021-11-10 | COMP | 2021-11-24 | COMP | Rule 16 | 170 | 130 | 21 | 80 | 52 | 10 | 560
19627 | 2019-09-05 | 2020-05-15 | 2020-06-19 | 2020-06-19 | COMP | 2020-09-25 | COMP | 2020-12-16 | COMP | 2021-02-24 | COMP | 2021-04-29 | COMP | Rule 16 | 175 | 25 | 70 | 56 | 47 | 47 | 415
14505 | 2019-09-06 | 2019-09-13 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2020-01-07 | COMP | 2020-01-09 | COMP | Rule 16 | 6 | 40 | 13 | 1 | 27 | 3 | 85
14542 | 2019-09-06 | 2019-09-16 | 2019-12-03 | 2020-05-20 | COMP | 2021-04-28 | COMP | 2021-07-29 | COMP | 2021-12-03 | COMP | 2021-12-22 | COMP | Rule 16 | 7 | 54 | 237 | 65 | 88 | 14 | 577
14583 | 2019-09-06 | 2019-09-17 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-25 | COMP | 2020-03-17 | COMP | Rule 16 | 8 | 72 | 5 | 1 | 34 | 16 | 131
14652 | 2019-09-06 | 2019-09-20 | 2020-01-13 | 2020-03-25 | COMP | 2020-04-01 | COMP | 2020-04-03 | COMP | 2020-06-29 | COMP | 2020-07-14 | COMP | Rule 16 | 11 | 77 | 6 | 3 | 61 | 12 | 215
14667 | 2019-09-06 | 2019-09-23 | 2019-11-14 | 2019-12-16 | COMP | 2020-01-28 | COMP | 2020-01-28 | COMP | 2020-06-22 | COMP | 2020-07-25 | COMP | Rule 16 | 12 | 38 | 29 | 1 | 103 | 25 | 223
14668 | 2019-09-06 | 2019-09-23 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-31 | COMP | 2020-02-29 | COMP | 2020-07-10 | COMP | 2020-08-28 | COMP | Rule 16 | 12 | 39 | 30 | 41 | 94 | 36 | 248
14708 | 2019-09-06 | 2019-09-24 | 2020-01-22 | 2020-01-22 | COMP | 2021-05-11 | COMP | 2021-08-02 | COMP | 2021-12-03 | COMP | 2021-12-22 | COMP | Rule 16 | 13 | 81 | 330 | 58 | 86 | 14 | 577
14761 | 2019-09-06 | 2019-09-26 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-01-23 | COMP | 2020-01-27 | COMP | Rule 16 | 15 | 46 | 11 | 1 | 25 | 3 | 96
14772 | 2019-09-06 | 2019-09-26 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2021-03-27 | INPR | 2020-03-14 | COMP | Rule 16 | 15 | 63 | 15 | 1 |  |  | 129
14794 | 2019-09-06 | 2019-09-27 | 2020-01-30 | 2020-10-13 | COMP | 2020-10-28 | COMP | 2020-02-28 | COMP | 2020-11-24 | COMP | 2021-02-04 | COMP | Rule 16 | 16 | 84 | 12 |  | 190 | 48 | 355
15124 | 2019-09-06 | 2019-10-14 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-04 | COMP | 2020-04-09 | COMP | 2020-06-25 | COMP | 2020-08-10 | COMP | Rule 16 | 27 | 67 | 10 | 47 | 55 | 33 | 234
15169 | 2019-09-06 | 2019-10-16 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-01 | COMP | 2020-10-29 | COMP | 2020-06-01 | COMP | 2020-12-07 | COMP | Rule 16 | 29 | 153 | 4 | 108 | 0 | 25 | 315
15189 | 2019-09-06 | 2019-10-17 | 2020-01-07 | 2020-01-07 | COMP | 2020-03-17 | COMP | 2020-06-11 | COMP | 2020-06-01 | COMP | 2020-07-23 | COMP | Rule 16 | 30 | 54 | 49 | 62 | 0 | 31 | 222
15246 | 2019-09-06 | 2019-10-22 | 2019-12-03 | 2019-12-03 | COMP | 2020-06-02 | COMP | 2020-03-17 | COMP | 2021-02-22 | COMP | 2021-03-15 | COMP | Rule 16 | 33 | 28 | 126 |  | 236 | 16 | 381
15266 | 2019-09-06 | 2019-10-23 | 2020-03-11 | 2020-03-11 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-05-04 | COMP | 2020-06-11 | COMP | Rule 16 | 34 | 94 | 24 | 1 | 16 | 28 | 192
15304 | 2019-09-06 | 2019-10-25 | 2020-03-22 | 2020-03-22 | COMP | 2020-10-28 | COMP | 2020-11-13 | COMP | 2022-04-19 | COMP | 2022-05-17 | COMP | Rule 16 | 36 | 99 | 156 | 12 | 359 | 21 | 679
15370 | 2019-09-06 | 2019-10-31 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-08-12 | COMP | 2020-10-07 | COMP | Rule 16 | 40 | 86 | 50 | 1 | 63 | 40 | 275
15447 | 2019-09-06 | 2019-11-02 | 2020-04-07 | 2020-04-07 | COMP | 2021-02-19 | COMP | 2021-02-19 | COMP | 2021-05-13 | COMP | 2021-07-15 | COMP | Rule 16 | 41 | 105 | 220 | 1 | 60 | 44 | 467
15512 | 2019-09-06 | 2019-11-05 | 2020-03-23 | 2020-03-23 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | 2020-06-05 | COMP | Rule 16 | 43 | 93 | 7 | 1 | 2 | 47 | 188
15571 | 2019-09-06 | 2019-11-07 | 2019-12-14 | 2019-12-14 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | Rule 16 | 45 | 24 | 9 | 1 | 24 | 1 | 100
15575 | 2019-09-06 | 2019-11-07 | 2020-01-31 | 2020-01-31 | COMP | 2020-03-12 | COMP | 2020-03-26 | COMP | 2020-04-13 | COMP | 2020-06-11 | COMP | Rule 16 | 45 | 56 | 29 | 11 | 13 | 43 | 192
15881 | 2019-09-06 | 2019-11-25 | 2020-03-06 | 2020-03-06 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2021-02-17 | COMP | 2021-03-25 | COMP | Rule 16 | 56 | 69 | 66 | 1 | 175 | 27 | 389
16083 | 2019-09-06 | 2019-12-09 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-29 | COMP | 2020-02-06 | COMP | 2020-02-04 | COMP | 2020-02-22 | COMP | Rule 16 | 64 | 25 | 11 | 7 | 0 | 11 | 114
16450 | 2019-09-06 | 2019-12-31 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-07 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-03-05 | COMP | Rule 15/16 | 79 | 22 | 6 | 15 | 1 | 5 | 123
16579 | 2019-09-06 | 2020-01-08 | 2020-04-23 | 2020-05-05 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-01 | COMP | 2020-07-08 | COMP | Rule 16 | 84 | 75 | 16 | 1 | 4 | 28 | 211
17095 | 2019-09-06 | 2020-02-01 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-07-28 | COMP | 2020-09-22 | COMP | Rule 15/16 | 100 | 66 | 25 | 1 | 36 | 40 | 264
17154 | 2019-09-06 | 2020-02-03 | 2020-03-27 | 2020-03-27 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2021-01-14 | COMP | 2021-01-29 | COMP | Rule 16 | 101 | 39 | 188 | 1 | 16 | 11 | 351
17205 | 2019-09-06 | 2020-02-04 | 2020-03-04 | 2020-03-04 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2020-04-20 | COMP | 2020-07-01 | COMP | Rule 15/16 | 102 | 21 | 7 | 1 | 28 | 52 | 206
17344 | 2019-09-06 | 2020-02-11 | 2020-02-19 | 2020-02-19 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | Rule 16 | 107 | 6 | 8 | 1 | 1 | 1 | 119
17405 | 2019-09-06 | 2020-02-12 | 2020-05-19 | 2020-05-19 | COMP | 2020-12-30 | COMP | 2020-12-30 | COMP | 2022-07-16 | INPR | 2021-02-16 | COMP | Rule 16 | 108 | 69 | 156 | 1 |  |  | 362
17772 | 2019-09-06 | 2020-02-26 | 2020-03-30 | 2020-03-30 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-10-30 | COMP | Rule 16 | 117 | 24 | 57 | 1 | 1 | 97 | 292
17773 | 2019-09-06 | 2020-02-26 | 2020-07-20 | 2020-09-22 | COMP | 2020-10-06 | COMP | 2020-10-06 | COMP | 2020-10-08 | COMP | 2020-12-30 | COMP | Rule 16 | 117 | 103 | 11 | 1 | 3 | 56 | 331
17868 | 2019-09-06 | 2020-03-03 | 2020-03-11 | 2020-03-11 | COMP | 2020-06-16 | COMP | 2020-06-17 | COMP | 2022-06-03 | COMP | 2022-09-16 | COMP | Rule 15/16 | 121 | 7 | 69 | 2 | 496 | 73 | 763
18486 | 2019-09-06 | 2020-03-26 | 2020-05-21 | 2020-05-21 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2020-11-04 | COMP | 2020-12-05 | COMP | Rule 16 | 138 | 41 | 108 | 1 | 11 | 20 | 314
19280 | 2019-09-06 | 2020-04-29 | 2020-05-07 | 2020-05-07 | COMP | 2020-05-15 | COMP | 2020-06-18 | COMP | 2020-05-18 | COMP | 2020-07-21 | COMP | Rule 16 | 162 | 7 | 7 | 24 | 0 | 24 | 220
15123 | 2019-09-07 | 2019-10-14 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-22 | COMP | 2020-10-07 | COMP | 2020-09-08 | COMP | 2020-12-10 | COMP | Rule 16 | 26 | 112 | 42 | 97 | 0 | 44 | 317
15866 | 2019-09-07 | 2019-11-26 | 2020-02-04 | 2020-02-04 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-03-24 | COMP | 2020-04-09 | COMP | Rule 16 | 56 | 46 | 21 | 1 | 15 | 13 | 147
18961 | 2019-09-07 | 2020-04-14 | 2020-05-01 | 2020-05-01 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2021-01-06 | COMP | 2021-03-24 | COMP | Rule 16 | 150 | 14 | 57 | 1 | 116 | 54 | 387
14382 | 2019-09-09 | 2019-09-09 | 2019-12-27 | 2019-12-27 | COMP | 2019-12-27 | NOTN | 2020-03-18 | COMP | 2023-12-03 | INPR | 2020-06-17 | COMP | Other | 1 | 76 |  | 56 |  |  | 195
14539 | 2019-09-09 | 2019-09-16 | 2020-02-13 | 2021-06-16 | COMP | 2021-02-24 | COMP | 2021-07-14 | COMP | 2021-08-19 | COMP | 2021-10-11 | COMP | Rule 15/16 | 6 | 103 |  | 99 | 27 | 37 | 527
14609 | 2019-09-09 | 2019-09-18 | 2020-01-04 | 2020-01-04 | COMP | 2020-04-27 | COMP | 2021-06-01 | COMP | 2022-07-23 | INPR | 2021-06-29 | COMP | Rule 16 | 8 | 73 | 79 | 277 |  |  | 455
15171 | 2019-09-09 | 2019-10-16 | 2020-02-25 | 2020-02-25 | COMP | 2020-05-20 | COMP | 2020-05-20 | INPR | 2020-05-20 | COMP | 2020-06-03 | COMP | Rule 16 | 28 | 88 | 62 |  |  |  | 185
15376 | 2019-09-09 | 2019-10-29 | 2020-02-13 | 2021-08-11 | COMP | 2021-09-02 | COMP | 2021-10-27 | COMP | 2021-09-10 | COMP | 2021-12-02 | COMP | Rule 15/16 | 37 | 72 | 17 | 39 | 0 | 24 | 562
15499 | 2019-09-09 | 2019-11-05 | 2019-12-24 | 2019-12-24 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | Rule 16 | 42 | 33 | 18 | 1 | 1 | 1 | 91
15515 | 2019-09-09 | 2019-11-05 | 2019-12-02 | 2019-12-02 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-08-14 | COMP | 2020-09-10 | COMP | Rule 16 | 42 | 17 | 41 | 1 | 140 | 19 | 255
15540 | 2019-09-09 | 2019-11-06 | 2020-01-09 | 2020-01-09 | COMP | 2019-11-08 | NOTN | 2020-01-09 | COMP | 2020-01-10 | NOTN | 2020-02-24 | COMP | Other | 43 | 42 |  | 1 |  |  | 114
15559 | 2019-09-09 | 2019-11-06 | 2020-04-01 | 2020-04-01 | COMP | 2020-11-20 | COMP | 2021-01-22 | COMP | 2021-01-15 | COMP | 2021-03-08 | COMP | Rule 15/16 | 43 | 99 | 165 | 41 | 0 | 31 | 375
15600 | 2019-09-09 | 2019-11-08 | 2020-01-27 | 2020-01-27 | COMP | 2020-02-21 | COMP | 2020-04-14 | COMP | 2020-04-30 | COMP | 2020-12-07 | COMP | Rule 16 | 45 | 51 | 19 | 38 | 13 | 153 | 314
15894 | 2019-09-09 | 2019-11-27 | 2020-04-15 | 2020-07-03 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-08-10 | COMP | 2020-08-21 | COMP | Rule 15/16 | 57 | 95 | 5 | 1 | 23 | 10 | 242
15927 | 2019-09-09 | 2019-12-02 | 2020-03-20 | 2020-03-20 | COMP | 2021-04-06 | COMP | 2021-04-06 | COMP | 2021-04-27 | COMP | 2021-05-14 | COMP | Rule 15/16 | 58 | 76 | 264 | 1 | 16 | 14 | 424
16036 | 2019-09-09 | 2019-12-06 | 2020-04-29 | 2020-04-29 | COMP | 2020-11-24 | COMP | 2020-11-24 | COMP | 2021-08-24 | COMP | 2021-10-08 | COMP | Rule 15/16 | 62 | 100 | 147 | 1 | 188 | 33 | 526
16089 | 2019-09-09 | 2019-12-09 | 2020-01-19 | 2020-09-10 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2022-07-16 | INPR | 2021-01-05 | COMP | Rule 16 | 63 | 28 | 36 | 1 |  |  | 333
16166 | 2019-09-09 | 2019-12-12 | 2020-02-03 | 2020-02-03 | COMP | 2020-04-03 | COMP | 2020-04-03 | COMP | 2020-05-03 | COMP | 2020-06-10 | COMP | Rule 16 | 66 | 35 | 44 | 1 | 21 | 27 | 190
16231 | 2019-09-09 | 2019-12-16 | 2020-04-08 | 2020-04-08 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-10-08 | COMP | 2020-11-16 | COMP | Rule 16 | 68 | 79 | 131 | 1 | 0 | 26 | 301
16522 | 2019-09-09 | 2020-01-06 | 2020-02-10 | 2020-02-10 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-04-27 | COMP | 2020-05-09 | COMP | Rule 16 | 81 | 25 | 6 | 1 | 50 | 10 | 168
17571 | 2019-09-09 | 2020-02-20 | 2020-04-13 | 2020-04-13 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2020-10-14 | COMP | 2020-12-04 | COMP | Rule 15/16 | 112 | 38 | 126 | 1 | 6 | 35 | 313
17805 | 2019-09-09 | 2020-02-28 | 2020-05-22 | 2020-09-28 | COMP | 2020-10-02 | COMP | 2021-07-15 | COMP | 2021-07-13 | COMP | 2021-11-29 | COMP | Rule 16 | 118 | 61 | 5 | 196 | 0 | 94 | 559
18729 | 2019-09-09 | 2020-04-06 | 2020-09-11 | 2022-03-21 | COMP | 2022-03-24 | COMP | 2022-05-10 | COMP | 2022-04-28 | COMP | 2022-05-17 | COMP | Rule 16 | 144 | 113 | 4 | 34 | 0 | 6 | 678
19584 | 2019-09-09 | 2020-05-14 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-11 | COMP | 2020-06-15 | COMP | 2020-06-11 | COMP | 2021-01-21 | COMP | Rule 16 | 172 | 16 | 5 | 3 | 0 | 152 | 344
19754 | 2019-09-09 | 2020-05-20 | 2020-08-23 | 2020-08-23 | COMP | 2020-12-29 | COMP | 2021-01-04 | COMP | 2021-08-06 | COMP | 2021-09-14 | COMP | Rule 16 | 176 | 67 | 87 | 4 | 151 | 27 | 508
20230 | 2019-09-09 | 2020-06-11 | 2020-08-14 | 2020-08-14 | COMP | 2020-10-05 | COMP | 2020-10-05 | COMP | 2021-03-15 | COMP | 2021-04-15 | COMP | Rule 16 | 191 | 47 | 36 | 1 | 109 | 24 | 403
4278 | 2019-09-10 | 2020-03-09 | 2021-03-05 | 2021-03-05 | COMP | 2021-06-29 | COMP |  | REQD | 2022-11-29 | COMP | 2022-12-21 | COMP | Rule 15/16 | 123 | 251 | 82 |  |  |  | 826
14656 | 2019-09-10 | 2019-09-21 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-16 | COMP | 2019-10-17 | INPR | 2020-03-29 | REQD | 2019-12-03 | COMP | Rule 16 | 9 | 11 | 8 |  |  |  | 58
14954 | 2019-09-10 | 2019-10-07 | 2019-12-12 | 2019-12-12 | COMP | 2020-01-06 | COMP | 2020-05-12 | COMP | 2020-06-09 | COMP | 2020-06-16 | COMP | Rule 16 | 20 | 46 | 16 | 90 | 20 | 6 | 193
14991 | 2019-09-10 | 2019-10-08 | 2019-12-26 | 2019-12-26 | COMP | 2020-01-08 | COMP | 2020-01-17 | COMP | 2023-04-30 | INPR | 2020-06-10 | COMP | Rule 16 | 21 | 54 | 9 | 8 |  |  | 189
15070 | 2019-09-10 | 2019-10-10 | 2020-03-01 | 2020-03-01 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2022-06-14 | COMP | 2022-09-27 | COMP | Rule 15/16 | 23 | 95 | 82 | 1 | 498 | 73 | 768
15079 | 2019-09-10 | 2019-10-11 | 2019-12-10 | 2019-12-10 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-02-10 | COMP | 2020-03-05 | COMP | Rule 15/16 | 24 | 40 | 15 | 1 | 28 | 18 | 121
15093 | 2019-09-10 | 2019-10-11 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-03-05 | COMP | 2020-04-01 | COMP | Rule 16 | 24 | 63 | 18 | 1 | 19 | 20 | 140
15101 | 2019-09-10 | 2019-10-11 | 2020-01-27 | 2020-09-22 | COMP | 2020-10-20 | COMP | 2020-04-16 | COMP | 2020-11-23 | COMP | 2021-03-03 | COMP | Rule 15/16 | 24 | 71 | 21 |  | 155 | 67 | 371
15129 | 2019-09-10 | 2019-10-14 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-02-06 | COMP | 2020-03-09 | COMP | Rule 16 | 25 | 60 | 14 | 1 | 6 | 22 | 123
15208 | 2019-09-10 | 2019-10-21 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-14 | COMP | 2020-03-27 | COMP | 2020-07-09 | COMP | 2020-09-21 | COMP | Rule 16 | 30 | 66 | 14 | 30 | 74 | 52 | 261
15243 | 2019-09-10 | 2019-10-22 | 2020-03-01 | 2020-03-01 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2020-07-28 | COMP | 2020-08-15 | COMP | Rule 16 | 31 | 87 | 17 | 1 | 90 | 14 | 236
15696 | 2019-09-10 | 2019-11-15 | 2020-03-05 | 2020-03-25 | COMP | 2020-06-02 | COMP | 2020-10-08 | COMP | 2021-01-04 | COMP | 2021-02-23 | COMP | Rule 16 | 48 | 74 | 49 | 92 | 58 | 35 | 365
15849 | 2019-09-10 | 2019-11-25 | 2020-05-28 | 2020-05-28 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2022-01-30 | INPR | 2020-06-23 | COMP | Rule 16 | 54 | 127 | 3 | 1 |  |  | 198
15868 | 2019-09-10 | 2019-11-26 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-06-11 | COMP | 2021-06-29 | COMP | Rule 16 | 55 | 45 | 6 | 1 | 87 | 265 | 454
16101 | 2019-09-10 | 2019-12-09 | 2020-04-29 | 2020-08-03 | COMP | 2020-08-06 | COMP | 2020-06-02 | COMP | 2020-12-30 | COMP | 2021-02-05 | COMP | Rule 16 | 62 | 99 | 4 |  | 147 | 26 | 354
16113 | 2019-09-10 | 2019-12-11 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-30 | COMP | 2020-02-13 | INPR | 2023-04-30 | CANC | 2020-02-11 | COMP | Rule 16 | 64 | 21 | 14 |  |  |  | 105
16401 | 2019-09-10 | 2019-12-27 | 2020-03-14 | 2020-03-22 | COMP | 2020-04-01 | COMP | 2020-09-11 | COMP | 2022-04-08 | COMP | 2022-06-06 | COMP | Rule 15/16 | 75 | 53 | 8 | 116 | 396 | 41 | 690
16447 | 2019-09-10 | 2020-01-02 | 2020-11-21 | 2021-04-07 | COMP | 2021-05-06 | COMP | 2021-05-06 | COMP | 2021-10-03 | COMP | 2022-01-15 | COMP | Rule 15/16 | 78 | 227 | 22 | 1 | 104 | 72 | 592
16477 | 2019-09-10 | 2020-01-03 | 2020-03-07 | 2020-03-07 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-21 | COMP | 2020-05-01 | COMP | Rule 16 | 79 | 44 | 17 | 1 | 16 | 9 | 162
16484 | 2019-09-10 | 2020-01-02 | 2020-02-06 | 2020-02-06 | COMP | 2020-03-12 | COMP | 2020-04-01 | COMP | 2020-04-27 | COMP | 2020-06-05 | COMP | Rule 16 | 78 | 25 | 25 | 15 | 19 | 29 | 186
16550 | 2019-09-10 | 2020-01-08 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-28 | COMP | 2020-05-28 | COMP | 2020-07-24 | COMP | 2020-09-04 | COMP | Rule 15/16 | 82 | 79 | 21 | 1 | 42 | 31 | 251
16586 | 2019-09-10 | 2020-01-08 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-12 | COMP | 2020-03-23 | COMP | 2020-06-24 | COMP | 2020-09-21 | COMP | Rule 16 | 82 | 29 | 17 | 8 | 67 | 63 | 261
16758 | 2019-09-10 | 2020-01-15 | 2020-03-25 | 2020-04-23 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2023-04-30 | INPR | 2020-06-02 | COMP | Rule 16 | 87 | 49 | 9 | 1 |  |  | 183
16892 | 2019-09-10 | 2020-01-22 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-27 | COMP | 2020-05-29 | COMP | 2020-06-23 | COMP | 2020-07-23 | COMP | Rule 16 | 91 | 74 | 16 | 3 | 18 | 23 | 220
16934 | 2019-09-10 | 2020-01-25 | 2020-02-26 | 2020-02-26 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-05-20 | COMP | 2020-06-02 | COMP | Rule 16 | 93 | 22 | 47 | 1 | 15 | 9 | 183
17153 | 2019-09-10 | 2020-02-03 | 2020-05-29 | 2021-04-15 | COMP | 2021-04-28 | COMP | 2020-12-07 | COMP | 2021-05-11 | COMP | 2021-06-24 | COMP | Rule 16 | 99 | 83 | 10 |  | 108 | 32 | 451
17162 | 2019-09-10 | 2020-02-03 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-06-02 | COMP | 2020-07-01 | COMP | Rule 16 | 99 | 20 | 8 | 1 | 59 | 22 | 204
17608 | 2019-09-10 | 2020-02-21 | 2020-06-02 | 2020-06-02 | COMP | 2020-07-28 | NOTN | 2020-07-27 | COMP | 2020-06-26 | COMP | 2020-12-10 | COMP | Other | 112 | 72 |  | 40 | 0 | 95 | 316
17649 | 2019-09-10 | 2020-02-24 | 2020-05-21 | 2020-06-04 | COMP | 2020-06-29 | COMP | 2021-04-27 | COMP |  | INPR | 2021-06-09 | COMP | Rule 15/16 | 113 | 64 | 18 | 209 |  |  | 440
17748 | 2019-09-10 | 2020-02-26 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-24 | COMP | 2020-05-14 | NOTN | 2020-05-14 | COMP | 2020-05-22 | COMP | Rule 16 | 115 | 17 | 27 |  |  |  | 177
18886 | 2019-09-10 | 2020-04-11 | 2020-05-22 | 2020-05-22 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2021-03-29 | COMP | 2021-04-28 | COMP | Rule 16 | 147 | 30 | 54 | 1 | 160 | 23 | 411
18914 | 2019-09-10 | 2020-04-12 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-09-14 | COMP | 2020-12-02 | COMP | Rule 15/16 | 147 | 51 | 13 | 1 | 47 | 55 | 310
20124 | 2019-09-10 | 2020-06-06 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-03 | COMP | 2020-08-27 | COMP | 2020-08-13 | COMP | 2020-09-22 | COMP | Rule 15/16 | 186 | 11 | 10 | 40 | 0 | 18 | 262
21410 | 2019-09-10 | 2020-08-05 | 2020-09-19 | 2020-09-19 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | 2021-02-23 | COMP | 2021-03-29 | COMP | Rule 16 | 229 | 32 | 48 | 1 | 58 | 25 | 389
14475 | 2019-09-11 | 2019-09-11 | 2019-09-15 | 2019-09-21 | COMP | 2019-10-24 | COMP | 2019-10-24 | COMP | 2019-12-04 | COMP | 2019-12-17 | COMP | Rule 16 | 1 | 3 | 24 | 1 | 27 | 10 | 67
14573 | 2019-09-11 | 2019-09-17 | 2019-11-16 | 2019-11-16 | COMP | 2019-11-27 | COMP | 2019-12-23 | COMP | 2020-02-04 | COMP | 2020-06-11 | COMP | Rule 15/16 | 5 | 43 | 8 | 17 | 29 | 91 | 189
14723 | 2019-09-11 | 2019-09-25 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-09 | COMP | 2019-12-31 | COMP | 2019-12-10 | COMP | 2020-02-03 | COMP | Rule 16 | 11 | 37 | 14 | 16 | 0 | 23 | 98
14781 | 2019-09-11 | 2019-09-27 | 2019-11-12 | 2019-11-12 | COMP | 2020-01-17 | COMP | 2020-01-17 | COMP | 2021-04-24 | INPR | 2020-04-08 | COMP | Rule 16 | 13 | 32 | 45 | 1 |  |  | 144
15012 | 2019-09-11 | 2019-10-09 | 2020-01-12 | 2020-01-12 | COMP | 2020-01-21 | COMP | 2020-03-06 | COMP | 2019-12-30 | COMP | 2020-03-11 | COMP | Rule 16 | 21 | 63 | 6 | 33 | 0 | 4 | 124
15111 | 2019-09-11 | 2019-10-15 | 2021-01-29 | 2021-03-18 | COMP | 2021-06-10 | COMP | 2021-07-22 | COMP | 2021-07-07 | COMP | 2022-02-15 | COMP | Rule 15/16 | 25 | 324 | 60 | 30 | 0 | 144 | 612
15118 | 2019-09-11 | 2019-10-15 | 2019-11-05 | 2019-11-05 | COMP | 2019-11-20 | COMP | 2019-11-13 | COMP | 2020-01-30 | COMP | 2020-02-27 | COMP | Rule 16 | 25 | 16 | 11 |  | 52 | 20 | 115
15281 | 2019-09-11 | 2019-10-24 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-10 | COMP | 2020-02-19 | COMP | 2020-02-14 | COMP | 2020-02-26 | COMP | Rule 16 | 32 | 66 | 7 | 7 | 0 | 6 | 114
15325 | 2019-09-11 | 2019-10-25 | 2020-03-06 | 2020-04-20 | COMP | 2020-06-05 | COMP | 2020-08-31 | COMP | 2020-09-08 | COMP | 2020-10-10 | COMP | Rule 16 | 33 | 89 | 34 | 62 | 6 | 24 | 274
15374 | 2019-09-11 | 2019-10-29 | 2020-02-13 | 2020-03-26 | COMP | 2020-04-07 | COMP | 2020-03-20 | COMP | 2020-06-08 | COMP | 2020-07-07 | COMP | Rule 15/16 | 35 | 72 | 9 |  | 56 | 22 | 207
15452 | 2019-09-11 | 2019-11-02 | 2020-01-06 | 2020-04-07 | COMP | 2020-04-15 | COMP | 2020-04-27 | COMP | 2020-12-15 | COMP | 2021-02-01 | COMP | Rule 15/16 | 38 | 41 | 7 | 9 | 162 | 32 | 349
15459 | 2019-09-11 | 2019-11-02 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-06 | COMP | 2020-09-14 | COMP | 2022-01-30 | INPR | 2020-11-16 | COMP | Rule 16 | 38 | 174 | 18 | 27 |  |  | 299
15509 | 2019-09-11 | 2019-11-05 | 2020-01-09 | 2020-01-09 | COMP | 2021-02-01 | COMP | 2021-02-25 | COMP | 2021-07-22 | COMP | 2021-09-07 | COMP | Rule 16 | 40 | 43 | 268 | 18 | 104 | 33 | 501
15757 | 2019-09-11 | 2019-11-20 | 2020-03-20 | 2020-03-20 | COMP | 2020-05-04 | COMP | 2020-07-09 | COMP | 2020-07-17 | COMP | 2020-08-14 | COMP | Rule 16 | 50 | 82 | 32 | 48 | 7 | 21 | 235
16108 | 2019-09-11 | 2019-12-10 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-14 | COMP | 2020-03-25 | COMP | 2020-06-01 | COMP | 2020-07-08 | COMP | Rule 16 | 62 | 33 | 14 | 28 | 48 | 28 | 208
16370 | 2019-09-11 | 2019-12-23 | 2020-12-29 | 2020-12-29 | COMP | 2021-01-13 | COMP | 2021-01-25 | COMP | 2021-01-19 | COMP | 2021-02-26 | COMP | Rule 16 | 71 | 257 | 11 | 8 | 0 | 24 | 367
16471 | 2019-09-11 | 2020-01-02 | 2020-03-25 | 2020-03-25 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-06-30 | COMP | 2020-07-13 | COMP | Rule 16 | 77 | 58 | 42 | 1 | 28 | 10 | 211
16811 | 2019-09-11 | 2020-01-16 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-07 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-05-06 | COMP | Rule 16 | 87 | 11 | 6 | 27 | 1 | 37 | 164
17562 | 2019-09-11 | 2020-02-20 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-27 | COMP | 2020-05-28 | COMP | 2023-04-30 | INPR | 2020-10-06 | COMP | Rule 16 | 110 | 46 | 3 | 23 |  |  | 271
17678 | 2019-09-11 | 2020-02-24 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-20 | COMP | 2020-06-01 | COMP | 2020-04-09 | COMP | 2020-06-30 | COMP | Rule 16 | 112 | 13 | 8 | 51 | 0 | 22 | 202
18618 | 2019-09-11 | 2020-03-31 | 2020-05-05 | 2020-05-05 | COMP | 2020-11-13 | COMP | 2020-11-13 | COMP | 2020-12-24 | COMP | 2021-06-16 | COMP | Rule 16 | 138 | 26 | 136 | 1 | 28 | 120 | 444
18680 | 2019-09-11 | 2020-04-03 | 2020-06-02 | 2020-06-19 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-07-20 | COMP | 2020-07-27 | COMP | Rule 15/16 | 141 | 42 | 6 | 1 | 17 | 6 | 221
23260 | 2019-09-11 | 2020-10-29 | 2021-02-23 | 2021-02-23 | COMP | 2021-03-11 | COMP | 2021-04-13 | COMP | 2023-12-04 | INPR | 2021-04-18 | COMP | Rule 16 | 288 | 77 | 13 | 24 |  |  | 402
4274 | 2019-09-12 | 2020-02-19 | 2020-07-24 | 2020-07-24 | COMP | 2020-10-21 | COMP | 2021-04-20 | COMP |  | INPR | 2021-07-07 | COMP | Rule 15/16 | 108 | 112 | 63 | 123 |  |  | 457
14487 | 2019-09-12 | 2019-09-12 | 2019-11-15 | 2019-11-15 | COMP | 2019-11-15 | NOTN | 2019-11-15 | COMP | 2020-01-21 | NOTN | 2020-02-07 | COMP | Other | 1 | 46 |  | 1 |  |  | 101
14516 | 2019-09-12 | 2019-09-13 | 2019-11-20 | 2019-11-20 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-16 | COMP | 2019-12-19 | COMP | Rule 16 | 2 | 48 | 5 | 1 | 13 | 4 | 68
14657 | 2019-09-12 | 2019-09-21 | 2019-10-07 | 2019-10-07 | COMP | 2019-10-18 | COMP | 2019-11-12 | COMP | 2019-11-08 | COMP | 2019-12-16 | COMP | Rule 16 | 7 | 11 | 10 | 17 | 0 | 23 | 65
14671 | 2019-09-12 | 2019-09-23 | 2019-09-26 | 2019-09-26 | COMP | 2019-10-07 | COMP | 2019-10-07 | COMP | 2020-03-13 | COMP | 2020-03-22 | COMP | Rule 16 | 8 | 4 | 8 | 1 | 108 | 6 | 130
14693 | 2019-09-12 | 2019-09-23 | 2020-07-06 | 2020-07-06 | COMP | 2020-12-21 | COMP | 2020-08-17 | COMP | 2021-11-08 | COMP | 2023-05-10 | COMP | Rule 15/16 | 8 | 198 | 117 |  | 310 | 377 | 920
14733 | 2019-09-12 | 2019-09-24 | 2019-10-22 | 2021-03-22 | COMP | 2021-05-05 | COMP | 2019-10-28 | COMP | 2022-06-18 | INPR | 2021-05-21 | COMP | Rule 16 | 9 | 21 | 33 |  |  |  | 426
14747 | 2019-09-12 | 2019-09-25 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-06 | COMP | 2020-05-11 | COMP | 2020-02-06 | COMP | 2020-08-20 | COMP | Rule 16 | 10 | 76 | 16 | 67 | 0 | 73 | 238
14770 | 2019-09-12 | 2019-09-26 | 2020-02-09 | 2020-02-09 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-03-30 | COMP | 2020-05-05 | COMP | Rule 16 | 11 | 91 | 6 | 1 | 30 | 27 | 162
14831 | 2019-09-12 | 2019-09-30 | 2019-11-15 | 2019-11-15 | COMP | 2020-01-29 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-04-01 | COMP | Rule 16 | 13 | 34 | 49 | 13 | 1 | 33 | 138
14880 | 2019-09-12 | 2019-10-02 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-05-22 | COMP | 2020-06-17 | COMP | Rule 16 | 15 | 42 | 19 | 1 | 102 | 18 | 192
14937 | 2019-09-12 | 2019-10-04 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2020-06-11 | COMP | 2020-07-22 | COMP | Rule 15/16 | 17 | 77 | 13 | 1 | 84 | 30 | 217
15204 | 2019-09-12 | 2019-10-19 | 2020-04-23 | 2020-04-23 | COMP | 2021-04-26 | COMP | 2021-08-04 | COMP | 2022-11-30 | COMP | 2023-01-27 | COMP | Rule 16 | 27 | 127 | 254 | 71 | 333 | 40 | 848
15438 | 2019-09-12 | 2019-11-01 | 2019-12-19 | 2019-12-19 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-02-24 | COMP | 2020-02-27 | COMP | Rule 16 | 37 | 32 | 37 | 1 | 8 | 4 | 114
15567 | 2019-09-12 | 2019-11-07 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-01-24 | COMP | 2020-02-21 | COMP | Rule 16 | 41 | 23 | 12 | 1 | 18 | 20 | 110
15680 | 2019-09-12 | 2019-11-14 | 2019-12-30 | 2020-01-03 | COMP | 2020-02-10 | COMP | 2020-03-02 | COMP | 2020-06-24 | COMP | 2020-07-21 | COMP | Rule 16 | 45 | 30 | 26 | 15 | 82 | 20 | 216
15788 | 2019-09-12 | 2019-11-21 | 2020-04-29 | 2021-05-06 | COMP | 2021-06-14 | COMP | 2020-10-09 | COMP | 2021-05-12 | COMP | 2021-07-14 | COMP | Rule 16 | 50 | 109 | 27 |  | 147 | 44 | 462
16013 | 2019-09-12 | 2019-12-04 | 2020-02-12 | 2020-03-22 | COMP | 2020-09-22 | COMP | 2020-10-21 | COMP | 2020-10-01 | COMP | 2020-11-17 | COMP | Rule 16 | 57 | 48 | 130 | 22 | 0 | 19 | 299
16201 | 2019-09-12 | 2019-12-13 | 2021-01-12 | 2021-01-12 | COMP | 2021-02-18 | COMP | 2021-04-28 | COMP | 2021-11-15 | COMP | 2021-12-12 | COMP | Rule 16 | 64 | 272 | 26 | 50 | 140 | 18 | 565
16626 | 2019-09-12 | 2020-01-09 | 2020-04-10 | 2020-04-10 | COMP | 2020-12-04 | COMP | 2020-12-16 | COMP | 2020-12-07 | COMP | 2021-01-07 | COMP | Rule 16 | 81 | 65 | 166 | 9 | 0 | 15 | 332
16729 | 2019-09-12 | 2020-01-14 | 2020-06-24 | 2020-06-24 | COMP | 2020-08-11 | COMP | 2020-10-05 | COMP | 2020-08-11 | COMP | 2020-12-09 | COMP | Rule 16 | 84 | 114 | 35 | 39 | 0 | 45 | 313
16860 | 2019-09-12 | 2020-01-21 | 2020-02-26 | 2020-02-26 | COMP | 2020-04-01 | COMP | 2020-10-03 | COMP | 2020-10-09 | COMP | 2020-12-02 | COMP | Rule 16 | 88 | 26 | 26 | 131 | 5 | 36 | 308
16877 | 2019-09-12 | 2020-01-21 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-07-27 | COMP | 2020-08-26 | COMP | Rule 16 | 88 | 58 | 15 | 1 | 62 | 23 | 242
16911 | 2019-09-12 | 2020-01-23 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-23 | COMP | 2020-04-13 | COMP | 2020-05-18 | COMP | 2020-06-12 | COMP | Rule 16 | 90 | 25 | 18 | 16 | 26 | 19 | 189
17104 | 2019-09-12 | 2020-01-30 | 2020-07-28 | 2020-08-03 | COMP | 2021-02-01 | COMP | 2022-03-17 | COMP | 2022-03-18 | COMP | 2023-04-17 | COMP | Rule 15/16 | 95 | 127 | 124 | 285 | 2 | 271 | 903
17466 | 2019-09-12 | 2020-02-14 | 2020-11-05 | 2020-11-05 | COMP | 2020-11-18 | COMP | 2022-08-10 | COMP | 2022-07-13 | COMP | 2022-08-15 | COMP | Rule 16 | 106 | 187 | 9 | 434 | 0 | 4 | 736
17798 | 2019-09-12 | 2020-02-27 | 2020-04-19 | 2020-04-19 | COMP | 2020-05-19 | COMP | 2020-05-27 | COMP | 2020-05-19 | COMP | 2020-07-31 | COMP | Rule 16 | 114 | 37 | 22 | 6 | 0 | 48 | 224
18028 | 2019-09-12 | 2020-03-09 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-23 | COMP | 2020-08-05 | COMP | 2020-07-30 | COMP | 2020-09-16 | COMP | Rule 16 | 121 | 74 | 25 | 10 | 0 | 30 | 256
18156 | 2019-09-12 | 2020-03-12 | 2020-10-09 | 2020-10-09 | COMP | 2020-10-16 | COMP | 2023-11-13 | CANC | 2020-12-02 | COMP | 2020-12-04 | COMP | Rule 16 | 124 | 150 | 6 |  |  |  | 310
18353 | 2019-09-12 | 2020-03-20 | 2020-05-06 | 2020-05-06 | COMP | 2021-01-26 | COMP | 2021-01-26 | COMP | 2021-05-11 | COMP | 2021-06-23 | COMP | Rule 16 | 130 | 34 | 182 | 1 | 75 | 31 | 448
21556 | 2019-09-12 | 2020-08-13 | 2020-12-31 | 2022-05-09 | COMP | 2022-06-17 | COMP | 2022-11-09 | COMP | 2023-01-05 | COMP | 2023-02-02 | COMP | Rule 16 | 233 | 96 | 29 | 101 | 37 | 20 | 852
14680 | 2019-09-13 | 2019-09-23 | 2020-03-19 | 2020-03-19 | COMP | 2020-05-05 | COMP | 2020-08-14 | COMP | 2020-08-07 | COMP | 2020-11-12 | COMP | Rule 16 | 7 | 122 | 34 | 73 | 0 | 63 | 295
14705 | 2019-09-13 | 2019-09-23 | 2020-03-22 | 2020-03-22 | COMP | 2020-12-23 | COMP | 2020-12-23 | COMP | 2020-12-29 | COMP | 2021-01-09 | COMP | Rule 16 | 7 | 123 | 193 | 1 | 4 | 8 | 332
14819 | 2019-09-13 | 2019-09-29 | 2020-07-16 | 2020-07-16 | COMP | 2020-07-30 | COMP | 2020-08-07 | COMP | 2020-09-02 | COMP | 2020-10-02 | COMP | Rule 15/16 | 11 | 201 | 11 | 7 | 19 | 22 | 267
15029 | 2019-09-13 | 2019-10-09 | 2020-01-07 | 2020-01-22 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-07-10 | COMP | Other | 19 | 60 | 19 | 1 | 1 | 103 | 208
15110 | 2019-09-13 | 2019-10-14 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-19 | COMP | 2020-06-10 | COMP | 2021-01-21 | COMP | 2021-03-03 | COMP | Rule 15/16 | 22 | 131 | 20 | 16 | 155 | 29 | 368
15166 | 2019-09-13 | 2019-10-18 | 2020-01-09 | 2020-01-09 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-07-28 | COMP | 2020-09-14 | COMP | Rule 16 | 26 | 55 | 136 | 1 | 6 | 34 | 253
15511 | 2019-09-13 | 2019-11-05 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-27 | COMP | 2020-04-09 | COMP | 2020-05-04 | COMP | 2020-06-25 | COMP | Rule 16 | 38 | 88 | 10 | 10 | 18 | 38 | 197
15676 | 2019-09-13 | 2019-11-14 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-04 | COMP | 2020-02-04 | COMP | 2020-06-15 | COMP | 2020-07-05 | COMP | Rule 16 | 44 | 41 | 14 | 1 | 93 | 15 | 203
16012 | 2019-09-13 | 2019-12-04 | 2021-01-05 | 2021-01-05 | COMP | 2021-04-22 | COMP | 2021-04-22 | COMP | 2021-01-05 | COMP | 2021-06-22 | COMP | Rule 16 | 56 | 274 | 76 | 1 | 0 | 43 | 446
16320 | 2019-09-13 | 2019-12-19 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-07-01 | COMP | 2020-08-05 | COMP | Rule 16 | 67 | 88 | 25 | 1 | 24 | 26 | 226
16388 | 2019-09-13 | 2019-12-24 | 2020-03-03 | 2020-03-03 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-04-21 | COMP | 2020-07-20 | COMP | Rule 16 | 70 | 47 | 22 | 1 | 15 | 64 | 214
16497 | 2019-09-13 | 2020-01-04 | 2020-04-15 | 2020-04-15 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-06-12 | COMP | 2020-08-03 | COMP | Rule 16 | 76 | 71 | 9 | 1 | 34 | 37 | 224
16532 | 2019-09-13 | 2020-01-07 | 2020-04-01 | 2020-04-01 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2021-05-27 | COMP | 2021-07-06 | COMP | Rule 16 | 78 | 60 | 33 | 1 | 261 | 27 | 455
16578 | 2019-09-13 | 2020-01-08 | 2020-02-28 | 2020-12-28 | COMP | 2021-03-24 | COMP | 2020-03-12 | COMP | 2020-06-15 | COMP | 2020-11-09 | COMP | Rule 16 | 79 | 36 | 60 |  | 67 | 105 | 293
16886 | 2019-09-13 | 2020-01-22 | 2020-03-05 | 2020-03-05 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-11 | COMP | 2020-04-13 | COMP | Rule 16 | 88 | 31 | 2 | 1 | 4 | 24 | 145
16987 | 2019-09-13 | 2020-01-29 | 2021-04-05 | 2021-10-11 | COMP | 2021-10-13 | COMP | 2021-10-14 | COMP | 2021-06-10 | COMP | 2021-11-11 | COMP | Rule 15/16 | 93 | 299 | 3 | 2 | 0 | 20 | 545
17488 | 2019-09-13 | 2020-02-18 | 2020-04-07 | 2020-04-07 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-08-26 | COMP | Rule 15/16 | 106 | 36 | 20 | 1 | 1 | 82 | 241
18003 | 2019-09-13 | 2020-03-06 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-29 | COMP | 2020-11-19 | COMP | 2020-11-18 | COMP | 2021-01-18 | COMP | Rule 16 | 119 | 53 | 8 | 123 | 0 | 38 | 337
19528 | 2019-09-13 | 2020-05-11 | 2020-07-22 | 2020-07-22 | COMP | 2020-10-05 | COMP | 2020-10-05 | COMP | 2021-04-26 | COMP | 2021-06-25 | COMP | Rule 16 | 165 | 52 | 53 | 1 | 139 | 44 | 449
14545 | 2019-09-14 | 2019-09-16 | 2020-01-06 | 2020-01-06 | COMP | 2020-01-06 | NOTN | 2020-07-08 | COMP | 2020-01-06 | COMP | 2020-08-24 | COMP | Other | 1 | 76 |  | 130 | 0 | 34 | 238
15176 | 2019-09-14 | 2019-10-17 | 2019-11-16 | 2019-11-16 | COMP | 2020-01-15 | COMP | 2020-03-31 | COMP | 2020-07-23 | COMP | 2020-08-19 | COMP | Rule 16 | 24 | 21 | 39 | 53 | 82 | 20 | 235
18093 | 2019-09-14 | 2020-03-10 | 2020-07-08 | 2020-07-08 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2020-12-04 | COMP | 2020-12-31 | COMP | Rule 16 | 120 | 86 | 14 | 1 | 91 | 19 | 326
15057 | 2019-09-15 | 2019-10-10 | 2019-12-12 | 2019-12-12 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-06-08 | COMP | 2020-06-22 | COMP | Rule 16 | 19 | 43 | 84 | 1 | 40 | 11 | 193
15319 | 2019-09-15 | 2019-10-26 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-18 | COMP | 2020-03-25 | COMP | 2021-05-30 | INPR | 2020-04-06 | COMP | Rule 16 | 30 | 59 | 17 | 27 |  |  | 139
16427 | 2019-09-15 | 2019-12-30 | 2020-03-03 | 2020-03-06 | COMP | 2020-03-20 | COMP | 2020-03-24 | COMP | 2020-03-20 | COMP | 2020-06-19 | COMP | Rule 16 | 72 | 44 | 11 | 3 | 0 | 63 | 192
17190 | 2019-09-15 | 2020-02-04 | 2020-09-28 | 2020-09-28 | COMP | 2020-10-02 | COMP | 2021-03-17 | COMP | 2021-04-15 | COMP | 2021-05-03 | COMP | Rule 16 | 96 | 167 | 5 | 112 | 22 | 13 | 410
4247 | 2019-09-16 | 2019-10-25 | [7 empty] | 2019-10-25 | COMP | 2020-02-11 | COMP | Other | 30 | [5 empty] | 101
14661 | 2019-09-16 | 2019-09-21 | 2020-03-04 | 2020-03-04 | COMP | 2020-03-11 | COMP | 2020-09-24 | COMP | 2020-09-01 | COMP | 2020-12-02 | COMP | Rule 16 | 5 | 111 | 6 | 140 | 0 | 47 | 306
14756 | 2019-09-16 | 2019-09-25 | 2019-12-03 | 2019-12-03 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2020-11-30 | COMP | 2021-02-05 | COMP | Rule 15/16 | 8 | 47 | 165 | 1 | 87 | 47 | 350
14956 | 2019-09-16 | 2019-10-07 | 2019-11-20 | 2019-11-20 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-05-05 | COMP | Rule 16 | 16 | 32 | 9 | 1 | 1 | 106 | 160
14995 | 2019-09-16 | 2019-10-09 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-04 | COMP | 2020-04-16 | COMP | 2020-02-20 | COMP | 2020-06-17 | COMP | Rule 16 | 18 | 72 | 8 | 52 | 0 | 44 | 190
15056 | 2019-09-16 | 2019-10-10 | 2019-12-18 | 2020-01-16 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-07-09 | COMP | 2020-08-24 | COMP | Rule 16 | 19 | 47 | 122 | 1 | 2 | 33 | 238
15113 | 2019-09-16 | 2019-10-14 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-09 | COMP | 2020-01-09 | COMP | 2020-01-11 | COMP | 2020-03-12 | COMP | Rule 16 | 21 | 51 | 8 | 1 | 2 | 42 | 122
15314 | 2019-09-16 | 2019-10-25 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-04 | COMP | 2020-05-01 | COMP | 2020-05-15 | COMP | 2020-08-05 | COMP | Rule 16 | 30 | 62 | 6 | 63 | 11 | 58 | 225
15321 | 2019-09-16 | 2019-10-26 | 2020-03-08 | 2020-03-08 | COMP | 2020-03-23 | COMP | 2020-04-08 | COMP | 2020-06-02 | COMP | 2020-08-03 | COMP | Rule 16 | 30 | 88 | 11 | 13 | 39 | 45 | 223
15478 | 2019-09-16 | 2019-11-04 | 2019-12-30 | 2019-12-30 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-08-04 | COMP | 2020-08-24 | COMP | Rule 16 | 36 | 37 | 30 | 1 | 124 | 15 | 238
15490 | 2019-09-16 | 2019-11-04 | 2020-03-08 | 2020-03-08 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2021-01-20 | COMP | 2021-02-06 | COMP | Rule 16 | 36 | 83 | 115 | 1 | 106 | 13 | 350
15612 | 2019-09-16 | 2019-11-12 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-04-27 | COMP | 2020-06-08 | COMP | Rule 16 | 41 | 69 | 7 | 1 | 40 | 30 | 183
15814 | 2019-09-16 | 2019-11-21 | 2020-01-30 | 2020-01-30 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-04-23 | COMP | Rule 16 | 48 | 46 | 55 | 1 | 1 | 6 | 152
15857 | 2019-09-16 | 2019-11-25 | 2020-02-10 | 2020-02-10 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-03-02 | COMP | 2020-09-16 | COMP | Rule 16 | 50 | 51 | 13 | 1 | 3 | 141 | 254
15884 | 2019-09-16 | 2019-11-25 | 2020-02-27 | 2020-02-27 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-07-10 | COMP | 2020-07-21 | COMP | Rule 16 | 50 | 63 | 26 | 1 | 71 | 8 | 214
16245 | 2019-09-16 | 2019-12-17 | 2020-04-07 | 2020-04-07 | COMP | 2021-05-11 | COMP | 2021-05-11 | COMP | 2021-05-11 | COMP | 2021-06-23 | COMP | Rule 15/16 | 64 | 77 | 277 | 1 | 1 | 31 | 446
16272 | 2019-09-16 | 2019-12-18 | 2020-06-29 | 2021-02-04 | COMP | 2021-02-25 | COMP | 2021-08-23 | COMP | 2021-08-11 | COMP | 2021-09-10 | COMP | Rule 16 | 65 | 134 | 15 | 126 | 0 | 14 | 501
16646 | 2019-09-16 | 2020-01-09 | 2020-04-09 | 2020-04-09 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-06-15 | COMP | 2020-07-24 | COMP | Rule 16 | 79 | 64 | 27 | 1 | 21 | 30 | 217
16805 | 2019-09-16 | 2020-01-17 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-03 | COMP | 2020-03-10 | COMP | 2020-03-10 | COMP | 2020-03-26 | COMP | Rule 16 | 85 | 28 | 4 | 6 | 1 | 13 | 132
17413 | 2019-09-16 | 2020-02-12 | 2020-02-29 | 2020-02-29 | COMP | 2020-03-06 | COMP | 2020-03-06 | INPR | 2020-03-31 | COMP | 2020-04-14 | COMP | Rule 16 | 102 | 12 | 5 |  |  |  | 145
17710 | 2019-09-16 | 2020-02-26 | 2020-06-01 | 2020-06-01 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2021-09-16 | COMP | 2021-10-18 | COMP | Rule 16 | 111 | 68 | 24 | 1 | 305 | 23 | 527
18122 | 2019-09-16 | 2020-03-11 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-06-19 | COMP | 2020-07-23 | COMP | Rule 16 | 121 | 41 | 14 | 1 | 19 | 25 | 216
18154 | 2019-09-16 | 2020-03-12 | 2020-09-18 | 2021-04-20 | COMP | 2021-05-24 | COMP | 2021-05-24 | COMP | 2021-07-21 | COMP | 2021-08-10 | COMP | Rule 16 | 122 | 135 | 25 | 1 | 41 | 15 | 479
14804 | 2019-09-17 | 2019-09-27 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-13 | COMP | 2020-02-03 | COMP | Rule 16 | 9 | 58 | 10 | 1 | 6 | 15 | 94
14961 | 2019-09-17 | 2019-10-07 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-02-21 | COMP | 2020-05-06 | COMP | Rule 16 | 15 | 62 | 34 | 1 | 0 | 52 | 160
15412 | 2019-09-17 | 2019-11-01 | 2020-02-25 | 2020-08-06 | COMP | 2020-08-04 | NOTN | 2020-08-06 | COMP | 2020-08-05 | COMP | 2020-09-21 | COMP | Other | 34 | 76 |  | 1 | 0 | 32 | 256
15463 | 2019-09-17 | 2019-11-04 | 2020-01-10 | 2020-02-13 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-07-13 | COMP | 2020-07-10 | COMP | Rule 16 | 35 | 45 | 102 | 1 | 5 |  | 206
15607 | 2019-09-17 | 2019-11-09 | 2020-01-14 | 2020-01-14 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-08-13 | COMP | 2020-10-01 | COMP | Rule 16 | 39 | 42 | 126 | 1 | 25 | 35 | 264
15667 | 2019-09-17 | 2019-11-14 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-02-11 | COMP | Rule 16 | 42 | 38 | 8 | 1 | 1 | 15 | 100
15856 | 2019-09-17 | 2019-11-25 | 2020-04-06 | 2020-04-06 | COMP | 2020-06-03 | COMP | 2020-07-23 | COMP | 2020-09-09 | COMP | 2020-11-20 | COMP | Rule 15/16 | 49 | 90 | 42 | 37 | 34 | 52 | 299
16081 | 2019-09-17 | 2019-12-09 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-04-21 | COMP | 2020-05-04 | COMP | Rule 16 | 57 | 56 | 5 | 1 | 34 | 10 | 158
16109 | 2019-09-17 | 2019-12-10 | 2020-01-25 | 2020-01-25 | COMP | 2020-02-13 | COMP | 2020-02-13 | COMP | 2020-03-31 | COMP | 2020-05-15 | COMP | Rule 16 | 58 | 31 | 14 | 1 | 33 | 34 | 167
16215 | 2019-09-17 | 2019-12-16 | 2020-03-06 | 2020-03-06 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-05-29 | COMP | 2020-06-23 | COMP | Rule 15/16 | 62 | 56 | 56 | 1 | 5 | 18 | 193
16322 | 2019-09-17 | 2019-12-20 | 2020-05-18 | 2020-05-18 | COMP | 2020-12-16 | COMP | 2021-04-07 | COMP | 2021-03-31 | COMP | 2021-04-26 | COMP | Rule 16 | 66 | 103 | 148 | 77 | 0 | 14 | 404
16788 | 2019-09-17 | 2020-01-16 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-12-26 | COMP | 2021-02-04 | COMP | Rule 16 | 83 | 41 | 31 | 1 | 169 | 27 | 348
16893 | 2019-09-17 | 2020-01-22 | 2020-02-24 | 2020-02-24 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2022-04-16 | INPR | 2021-03-31 | COMP | Rule 16 | 86 | 23 | 29 | 1 |  |  | 386
16933 | 2019-09-17 | 2020-01-25 | 2020-04-27 | 2020-04-27 | COMP | 2020-07-21 | COMP | 2021-04-26 | COMP | 2021-04-28 | COMP | 2021-06-04 | COMP | Rule 16 | 88 | 65 | 61 | 192 | 3 | 27 | 432
17357 | 2019-09-17 | 2020-02-11 | 2020-03-31 | 2020-10-19 | COMP | 2020-11-03 | COMP | 2020-11-03 | COMP | 2020-12-02 | COMP | 2020-12-12 | COMP | Rule 15/16 | 100 | 35 | 12 | 1 | 19 | 8 | 312
17419 | 2019-09-17 | 2020-02-13 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-07-20 | COMP | 2020-09-07 | COMP | Rule 16 | 102 | 36 | 4 | 1 | 73 | 35 | 246
17599 | 2019-09-17 | 2020-02-20 | 2020-03-06 | 2020-03-06 | COMP | 2020-09-17 | COMP | 2020-05-15 | COMP | 2020-12-29 | COMP | 2021-03-03 | COMP | Rule 16 | 106 | 12 | 138 |  | 157 | 44 | 366
18025 | 2019-09-17 | 2020-03-09 | 2020-06-24 | 2020-06-24 | COMP | 2020-08-27 | COMP | 2020-08-27 | COMP | 2020-10-27 | COMP | 2020-11-17 | COMP | Rule 15/16 | 118 | 77 | 47 | 1 | 43 | 15 | 296
19290 | 2019-09-17 | 2020-04-28 | 2020-07-10 | 2021-04-06 | COMP | 2021-04-15 | COMP | 2021-04-27 | COMP | 2021-05-07 | COMP | 2021-06-03 | COMP | Rule 16 | 154 | 53 | 8 | 9 | 9 | 19 | 431
22983 | 2019-09-17 | 2020-10-19 | 2020-10-29 | 2020-10-29 | COMP | 2020-11-25 | COMP | 2020-11-28 | COMP | 2021-01-12 | COMP | 2021-02-26 | COMP | Rule 16 | 276 | 9 | 19 | 1 | 30 | 32 | 363
24392 | 2019-09-17 | 2020-12-22 | 2021-03-16 | 2021-03-16 | COMP | 2021-04-26 | COMP | 2021-04-28 | COMP | 2021-05-03 | COMP | 2021-05-05 | COMP | Rule 16 | 319 | 57 | 30 | 3 | 4 | 3 | 411
25126 | 2019-09-17 | 2021-01-29 | 2021-03-15 | 2021-03-15 | COMP | 2021-04-27 | COMP | 2021-04-27 | COMP | 2021-05-03 | COMP | 2021-05-05 | COMP | Rule 16 | 344 | 31 | 32 | 1 | 5 | 3 | 411
25541 | 2019-09-17 | 2021-02-15 | 2021-04-06 | 2021-04-06 | COMP | 2021-05-05 | COMP | 2021-05-05 | COMP | 2021-05-07 | COMP | 2021-06-01 | COMP | Rule 16 | 354 | 36 | 22 | 1 | 3 | 17 | 429
14784 | 2019-09-18 | 2019-09-27 | 2019-11-03 | 2019-11-03 | COMP | 2020-01-03 | COMP | 2020-01-06 | COMP | 2020-01-07 | COMP | 2020-01-28 | COMP | Rule 16 | 8 | 26 | 40 | 2 | 2 | 15 | 89
14897 | 2019-09-18 | 2019-10-03 | 2019-12-17 | 2019-12-17 | COMP | 2019-12-30 | COMP | 2020-01-17 | COMP | 2020-01-13 | COMP | 2020-02-21 | COMP | Rule 16 | 12 | 51 | 9 | 14 | 0 | 24 | 106
15004 | 2019-09-18 | 2019-10-09 | 2019-11-16 | 2019-11-16 | COMP | 2019-12-02 | COMP | 2019-12-09 | COMP | 2020-06-03 | COMP | 2020-06-24 | COMP | Rule 16 | 16 | 27 | 9 | 6 | 123 | 16 | 193
15130 | 2019-09-18 | 2019-10-16 | 2019-12-28 | 2019-12-28 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-08-08 | COMP | 2020-09-17 | COMP | Rule 16 | 21 | 49 | 154 | 1 | 3 | 28 | 253
15131 | 2019-09-18 | 2019-10-16 | 2019-12-16 | 2019-12-16 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2020-09-19 | COMP | 2020-11-10 | COMP | Rule 16 | 21 | 41 | 190 | 1 | 5 | 37 | 291
15132 | 2019-09-18 | 2019-10-16 | 2020-02-08 | 2020-02-08 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2021-03-02 | COMP | Rule 16 | 21 | 77 | 153 | 1 | 1 | 115 | 364
15143 | 2019-09-18 | 2019-10-15 | 2019-11-03 | 2019-11-03 | COMP | 2019-11-26 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-06-26 | COMP | Rule 16 | 20 | 14 | 16 | 133 | 1 | 15 | 195
15409 | 2019-09-18 | 2019-10-30 | 2020-07-03 | 2021-04-22 | COMP | 2021-05-14 | COMP | 2021-05-20 | COMP | 2021-07-27 | COMP | 2021-07-31 | COMP | Rule 16 | 31 | 170 | 17 | 5 | 47 | 4 | 470
15636 | 2019-09-18 | 2019-11-13 | 2020-04-15 | 2020-06-09 | COMP | 2020-07-29 | COMP | 2020-08-24 | COMP | 2020-09-15 | COMP | 2020-12-12 | COMP | Rule 15/16 | 40 | 105 | 37 | 19 | 16 | 61 | 311
15652 | 2019-09-18 | 2019-11-14 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-07 | COMP | 2020-02-12 | COMP | 2023-04-30 | INPR | 2020-06-16 | COMP | Rule 16 | 41 | 42 | 16 | 4 |  |  | 187
15657 | 2019-09-18 | 2019-11-13 | 2020-02-12 | 2020-02-12 | COMP | 2020-06-17 | COMP | 2020-06-25 | COMP | 2020-12-15 | COMP | 2021-01-09 | COMP | Rule 15/16 | 40 | 61 | 89 | 7 | 120 | 17 | 329
15723 | 2019-09-18 | 2019-11-19 | 2020-01-06 | 2020-01-06 | COMP | 2020-03-20 | COMP | 2020-04-20 | COMP | 2021-04-26 | COMP | 2021-05-19 | COMP | Rule 15/16 | 44 | 31 | 53 | 22 | 257 | 18 | 420
15810 | 2019-09-18 | 2019-11-21 | 2020-01-06 | 2020-11-23 | COMP | 2020-12-23 | COMP | 2020-12-23 | COMP | 2021-04-16 | COMP | 2021-04-29 | COMP | Rule 15/16 | 46 | 29 | 21 | 1 | 79 | 10 | 406
16488 | 2019-09-18 | 2020-01-03 | 2020-03-23 | 2020-03-30 | COMP | 2020-04-10 | COMP | 2020-06-01 | COMP | 2020-05-20 | COMP | 2020-06-29 | COMP | Rule 15/16 | 73 | 55 | 10 | 36 | 0 | 21 | 196
16716 | 2019-09-18 | 2020-01-13 | 2020-06-09 | 2022-02-19 | COMP | 2022-03-11 | COMP | 2022-03-11 | COMP | 2023-10-16 | COMP | 2023-11-24 | COMP | Rule 16 | 79 | 104 | 14 | 1 | 402 | 27 | 1051
16730 | 2019-09-18 | 2020-01-13 | 2020-04-11 | 2020-04-13 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-06-03 | COMP | 2020-06-30 | COMP | Rule 16 | 79 | 63 | 12 | 1 | 26 | 20 | 197
16833 | 2019-09-18 | 2020-01-18 | 2020-05-11 | 2020-05-22 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-07-28 | COMP | 2020-10-07 | COMP | Rule 16 | 83 | 79 | 42 | 1 | 6 | 51 | 267
16861 | 2019-09-18 | 2020-01-21 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2020-06-11 | COMP | 2020-07-08 | COMP | Rule 16 | 84 | 19 | 27 | 1 | 57 | 20 | 203
17057 | 2019-09-18 | 2020-01-29 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-11 | COMP | 2020-07-13 | COMP | 2020-10-05 | COMP | 2020-10-23 | COMP | Rule 16 | 90 | 77 | 19 | 23 | 60 | 15 | 279
17332 | 2019-09-18 | 2020-02-10 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-15 | COMP | 2020-09-02 | COMP | Rule 16 | 98 | 62 | 27 | 1 | 24 | 36 | 243
18043 | 2019-09-18 | 2020-03-10 | 2020-06-02 | 2020-06-02 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-12-04 | COMP | 2021-03-20 | COMP | Rule 15/16 | 118 | 60 | 41 | 1 | 90 | 72 | 377
18725 | 2019-09-18 | 2020-04-04 | 2020-09-03 | 2020-09-03 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2021-04-29 | COMP | 2021-06-04 | COMP | Rule 15/16 | 136 | 108 | 66 | 1 | 98 | 26 | 431
20811 | 2019-09-18 | 2020-07-07 | 2020-08-04 | 2020-08-04 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2020-12-01 | COMP | 2020-12-02 | COMP | Rule 16 | 202 | 21 | 57 | 1 | 26 | 2 | 304
25297 | 2019-09-18 | 2021-02-04 | 2021-03-11 | 2021-03-11 | COMP | 2021-03-18 | COMP | 2021-03-18 | COMP | 2021-03-18 | COMP | 2021-04-13 | COMP | Rule 15/16 | 347 | 25 | 6 | 1 | 1 | 19 | 394
14642 | 2019-09-19 | 2019-09-21 | 2020-04-21 | 2020-04-21 | COMP | 2020-04-28 | COMP | 2020-07-02 | COMP | 2020-09-08 | COMP | 2021-03-29 | COMP | Rule 16 | 2 | 145 | 6 | 47 | 48 | 138 | 382
14867 | 2019-09-19 | 2019-10-01 | 2020-02-05 | 2020-09-23 | COMP | 2020-10-20 | COMP | 2021-04-19 | COMP | 2021-05-07 | COMP | 2021-06-02 | COMP | Rule 16 | 9 | 86 | 20 | 123 | 15 | 18 | 428
15240 | 2019-09-19 | 2019-10-22 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-20 | COMP | 2020-03-22 | COMP | 2020-06-30 | COMP | 2020-07-23 | COMP | Rule 16 | 24 | 85 | 18 | 1 | 71 | 18 | 213
15299 | 2019-09-19 | 2019-10-25 | 2019-12-04 | 2019-12-04 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-07 | COMP | 2020-04-15 | COMP | Rule 16 | 27 | 26 | 60 | 1 | 5 | 28 | 143
15315 | 2019-09-19 | 2019-10-25 | 2020-04-07 | 2022-03-02 | COMP | 2022-03-09 | COMP | 2022-03-16 | COMP | 2022-01-18 | COMP | 2022-04-29 | COMP | Rule 15/16 | 27 | 111 | 6 | 6 | 0 | 33 | 658
15377 | 2019-09-19 | 2019-10-29 | 2020-03-23 | 2020-03-23 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2020-08-21 | COMP | Rule 16 | 29 | 98 | 88 | 1 | 1 | 22 | 234
15473 | 2019-09-19 | 2019-11-04 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-09-16 | COMP | 2020-11-30 | COMP | Rule 15/16 | 33 | 124 | 40 | 1 | 57 | 51 | 301
15544 | 2019-09-19 | 2019-11-06 | 2020-01-09 | 2020-01-09 | COMP | 2020-12-17 | COMP | 2021-01-28 | COMP | 2021-02-11 | NOTN | 2021-02-26 | COMP | Rule 15/16 | 35 | 42 | 239 | 28 |  |  | 361
15664 | 2019-09-19 | 2019-11-14 | 2019-12-17 | 2019-12-17 | COMP | 2020-04-30 | COMP | 2020-05-28 | COMP | 2020-05-28 | COMP | 2020-06-23 | COMP | Rule 16 | 40 | 22 | 94 | 20 | 1 | 19 | 191
15715 | 2019-09-19 | 2019-11-18 | 2020-03-25 | 2020-03-25 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-06-12 | COMP | 2020-08-10 | COMP | Rule 16 | 42 | 87 | 69 | 1 | 0 | 30 | 225
15720 | 2019-09-19 | 2019-11-19 | 2020-08-02 | 2020-08-02 | COMP | 2021-04-02 | COMP | 2021-08-19 | COMP | 2021-09-01 | COMP | 2021-10-08 | COMP | Rule 15/16 | 43 | 177 | 167 | 98 | 10 | 27 | 518
15829 | 2019-09-19 | 2019-11-22 | 2020-01-24 | 2020-03-31 | COMP | 2021-10-05 | COMP | 2020-02-12 | COMP |  | INPR | 2020-04-10 | COMP | Rule 15/16 | 46 | 41 | 384 |  |  |  | 140
15830 | 2019-09-19 | 2019-11-22 | 2020-02-05 | 2021-09-23 | COMP | 2021-11-16 | COMP | 2022-02-11 | COMP | 2023-11-13 | INPR | 2022-07-23 | COMP | Rule 16 | 46 | 49 | 38 | 61 |  |  | 715
15988 | 2019-09-19 | 2019-12-04 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2019-12-20 | COMP | 2019-12-31 | COMP | Rule 16 | 52 | 8 | 6 | 1 | 1 | 7 | 70
16266 | 2019-09-19 | 2019-12-18 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2022-01-30 | INPR | 2020-12-22 | COMP | Rule 16 | 62 | 32 | 7 | 1 |  |  | 317
16323 | 2019-09-19 | 2019-12-20 | 2020-03-27 | 2020-03-27 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-05-06 | COMP | 2020-08-04 | COMP | Rule 16 | 64 | 67 | 47 | 1 | 0 | 46 | 221
16563 | 2019-09-19 | 2020-01-08 | 2020-04-28 | 2020-04-28 | COMP | 2020-04-28 | NOTN | 2020-05-07 | COMP | 2020-12-16 | COMP | 2021-01-29 | COMP | Other | 75 | 78 |  | 8 | 155 | 30 | 342
16665 | 2019-09-19 | 2020-01-10 | 2020-04-22 | 2020-04-22 | COMP | 2020-07-13 | COMP | 2020-06-24 | COMP | 2020-06-30 | COMP | 2020-07-21 | COMP | Rule 16 | 77 | 72 | 58 |  | 5 | 16 | 211
16684 | 2019-09-19 | 2020-01-13 | 2020-05-07 | 2020-05-07 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2021-06-02 | COMP | 2021-07-15 | COMP | Rule 16 | 78 | 82 | 9 | 1 | 262 | 31 | 458
16785 | 2019-09-19 | 2020-01-16 | 2020-03-24 | 2020-08-10 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2021-08-23 | COMP | 2021-11-18 | COMP | Rule 16 | 81 | 47 | 46 | 1 | 216 | 62 | 546
16793 | 2019-09-19 | 2020-01-15 | 2020-03-08 | 2020-03-08 | COMP | 2021-02-10 | COMP | 2021-02-10 | INPR | 2022-04-16 | REQD | 2021-03-22 | COMP | Rule 16 | 80 | 36 | 235 |  |  |  | 377
17027 | 2019-09-19 | 2020-01-28 | 2020-03-30 | 2020-03-30 | COMP | 2020-03-30 | NOTN | 2020-05-20 | COMP | 2020-05-06 | COMP | 2020-06-16 | COMP | Other | 88 | 44 |  | 38 | 0 | 19 | 186
17460 | 2019-09-19 | 2020-02-14 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-04 | COMP | 2020-08-26 | COMP | 2020-10-01 | COMP | 2020-11-05 | COMP | Rule 16 | 101 | 57 | 22 | 60 | 26 | 26 | 287
17532 | 2019-09-19 | 2020-02-19 | 2020-07-06 | 2020-07-06 | COMP | 2021-08-13 | COMP | 2022-05-27 | COMP | 2022-05-31 | COMP | 2022-08-08 | COMP | Rule 16 | 103 | 98 | 280 | 200 | 2 | 48 | 726
17533 | 2019-09-19 | 2020-02-19 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-03-18 | COMP | 2020-04-10 | COMP | Rule 16 | 103 | 3 | 18 | 1 | 2 | 18 | 140
17806 | 2019-09-19 | 2020-02-27 | 2020-06-13 | 2020-06-13 | COMP | 2021-07-26 | COMP | 2021-07-26 | COMP | 2022-02-03 | COMP | 2022-02-15 | COMP | Rule 16 | 109 | 76 | 281 | 1 | 134 | 9 | 606
18420 | 2019-09-19 | 2020-03-23 | 2020-11-03 | 2020-11-03 | COMP | 2021-04-13 | COMP | 2021-06-01 | COMP | 2021-07-16 | COMP | 2021-07-23 | COMP | Rule 16 | 126 | 160 | 109 | 35 | 33 | 6 | 464
18905 | 2019-09-19 | 2020-04-13 | 2021-01-26 | 2022-08-05 | COMP | 2022-08-19 | COMP | 2022-09-07 | COMP | 2022-08-12 | COMP | 2022-10-14 | COMP | Rule 15/16 | 141 | 199 | 11 | 13 | 0 | 28 | 774
19069 | 2019-09-19 | 2020-04-20 | 2021-03-30 | 2021-03-30 | COMP | 2021-12-30 | COMP | 2021-06-11 | COMP | 2022-02-03 | COMP | 2022-04-05 | COMP | Rule 15/16 | 146 | 238 | 192 |  | 164 | 43 | 640
14666 | 2019-09-20 | 2019-09-23 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-07 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | 2020-02-12 | COMP | Rule 16 | 2 | 92 | 3 | 4 | 1 | 1 | 98
14974 | 2019-09-20 | 2019-10-08 | 2019-11-21 | 2019-11-21 | COMP | 2019-12-13 | COMP | 2019-12-13 | COMP | 2020-01-02 | COMP | 2019-12-31 | COMP | Rule 16 | 13 | 32 | 15 | 1 | 13 |  | 69
15085 | 2019-09-20 | 2019-10-11 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-08 | COMP | 2020-03-23 | COMP | Rule 16 | 16 | 87 | 13 | 1 | 1 | 11 | 125
15126 | 2019-09-20 | 2019-10-14 | 2019-11-20 | 2019-11-20 | COMP | 2019-11-27 | COMP | 2019-12-10 | COMP | 2019-11-15 | COMP | 2020-02-05 | COMP | Rule 16 | 17 | 27 | 6 | 8 | 0 | 39 | 93
15283 | 2019-09-20 | 2019-10-24 | 2019-12-02 | 2019-12-02 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-01-30 | COMP | 2020-02-01 | COMP | Rule 16 | 25 | 25 | 22 | 1 | 20 | 2 | 90
15619 | 2019-09-20 | 2019-11-13 | 2020-01-13 | 2020-01-13 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-18 | COMP | 2020-03-11 | COMP | Rule 16 | 38 | 40 | 20 | 1 | 6 | 17 | 117
15886 | 2019-09-20 | 2019-11-25 | 2020-03-08 | 2020-03-08 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2021-05-25 | COMP | 2021-06-16 | COMP | Rule 16 | 46 | 69 | 29 | 1 | 280 | 16 | 437
15938 | 2019-09-20 | 2019-12-02 | 2020-03-20 | 2021-03-11 | COMP | 2021-04-02 | COMP | 2021-07-14 | COMP | 2021-07-26 | COMP | 2021-08-23 | COMP | Rule 16 | 49 | 76 | 17 | 72 | 9 | 21 | 484
16060 | 2019-09-20 | 2019-12-06 | 2020-02-13 | 2020-02-13 | COMP | 2020-03-30 | COMP | 2020-05-12 | COMP | 2021-04-13 | COMP | 2021-05-14 | COMP | Rule 16 | 53 | 47 | 32 | 32 | 232 | 24 | 415
16146 | 2019-09-20 | 2019-12-12 | 2020-01-11 | 2020-01-14 | COMP | 2020-03-26 | COMP | 2020-04-14 | COMP | 2020-03-26 | COMP | 2020-05-11 | COMP | Rule 16 | 57 | 20 | 51 | 14 | 0 | 20 | 160
16249 | 2019-09-20 | 2019-12-17 | 2020-02-22 | 2020-02-22 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-04-28 | COMP | 2020-05-28 | COMP | Rule 16 | 60 | 45 | 24 | 1 | 24 | 22 | 172
16612 | 2019-09-20 | 2020-01-10 | 2020-03-03 | 2020-03-03 | COMP | 2021-10-11 | COMP | 2021-10-11 | INPR | 2022-04-01 | COMP | 2022-05-31 | COMP | Rule 16 | 76 | 36 | 408 |  |  |  | 678
16620 | 2019-09-20 | 2020-01-10 | 2020-03-28 | 2020-03-28 | COMP | 2020-07-29 | COMP | 2020-07-30 | COMP | 2020-08-17 | COMP | 2020-09-22 | COMP | Rule 16 | 76 | 54 | 87 | 2 | 13 | 26 | 254
16769 | 2019-09-20 | 2020-01-15 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-05-15 | COMP | Rule 16 | 79 | 31 | 42 | 1 | 1 | 15 | 164
17002 | 2019-09-20 | 2020-01-27 | 2020-05-14 | 2020-05-14 | COMP | 2020-07-07 | COMP | 2020-09-11 | INPR | 2021-02-23 | COMP | 2021-02-22 | COMP | Rule 15/16 | 86 | 78 | 38 |  |  |  | 356
17308 | 2019-09-20 | 2020-02-08 | 2020-03-02 | 2020-11-16 | COMP | 2020-11-19 | COMP | 2020-09-21 | COMP | 2020-09-28 | COMP | 2020-11-20 | COMP | Rule 16 | 95 | 15 | 4 |  | 6 | 39 | 296
18108 | 2019-09-20 | 2020-03-11 | 2021-02-03 | 2021-02-03 | COMP | 2021-03-30 | COMP | 2023-03-08 | COMP | 2023-04-07 | COMP | 2023-07-27 | COMP | Rule 15/16 | 117 | 228 | 39 | 488 | 23 | 77 | 967
18690 | 2019-09-20 | 2020-04-03 | 2020-09-25 | 2020-09-25 | COMP | 2020-10-02 | COMP | 2020-10-26 | COMP | 2021-01-07 | COMP | 2021-02-03 | COMP | Rule 16 | 134 | 124 | 6 | 17 | 49 | 19 | 344
19964 | 2019-09-20 | 2020-05-30 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-08-03 | COMP | 2020-09-25 | COMP | Rule 16 | 173 | 21 | 15 | 1 | 12 | 39 | 257
20597 | 2019-09-20 | 2020-06-29 | 2020-10-06 | 2020-10-06 | COMP | 2021-01-07 | COMP | 2021-02-12 | COMP | 2021-02-16 | COMP | 2021-03-24 | COMP | Rule 16 | 194 | 71 | 63 | 26 | 2 | 27 | 378
20598 | 2019-09-20 | 2020-06-29 | 2020-10-06 | 2020-12-22 | COMP | 2021-01-27 | COMP | 2021-03-12 | COMP | 2021-02-16 | COMP | 2021-03-24 | COMP | Rule 15/16 | 194 | 71 | 24 | 32 | 0 | 9 | 378
22422 | 2019-09-20 | 2020-09-23 | 2020-10-06 | 2020-10-06 | COMP | 2021-01-22 | COMP | 2021-04-05 | COMP | 2021-04-13 | COMP | 2021-05-26 | COMP | Rule 15/16 | 255 | 10 | 73 | 51 | 7 | 32 | 423
15023 | 2019-09-21 | 2019-10-09 | 2020-01-24 | 2020-04-23 | COMP | 2020-06-04 | COMP | 2020-02-10 | COMP | 2020-08-18 | COMP | 2020-09-17 | COMP | Rule 16 | 13 | 72 | 30 |  | 135 | 22 | 250
15660 | 2019-09-21 | 2019-11-14 | 2020-04-22 | 2020-06-22 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-07-10 | COMP | 2020-07-11 | COMP | Rule 15/16 | 38 | 109 | 7 | 1 | 9 | 1 | 202
16037 | 2019-09-21 | 2019-12-06 | 2020-03-27 | 2020-03-27 | COMP | 2020-05-07 | COMP | 2020-08-31 | COMP | 2020-07-16 | COMP | 2020-10-20 | COMP | Rule 16 | 52 | 77 | 30 | 82 | 0 | 36 | 273
17682 | 2019-09-21 | 2020-02-24 | 2020-08-26 | 2020-08-26 | COMP | 2020-09-24 | COMP | 2020-10-12 | COMP |  | INPR | 2023-07-10 | COMP | Rule 16 | 104 | 132 | 21 | 13 |  |  | 953
19440 | 2019-09-21 | 2020-05-06 | 2020-08-27 | 2020-10-08 | COMP | 2021-10-21 | COMP | 2021-10-21 | COMP | 2021-10-22 | COMP | 2022-01-08 | COMP | Rule 16 | 156 | 81 | 261 | 1 | 2 | 53 | 578
15042 | 2019-09-22 | 2019-10-10 | 2020-03-12 | 2020-03-25 | COMP | 2020-04-09 | COMP | 2020-05-28 | COMP | 2023-04-30 | INPR | 2020-06-19 | COMP | Rule 16 | 14 | 104 | 12 | 35 |  |  | 187
4238 | 2019-09-23 | 2019-09-30 | [7 empty] | 2019-10-17 | COMP | 2019-11-08 | COMP | Other | 6 | [5 empty] | 35
14694 | 2019-09-23 | 2019-09-24 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-10 | COMP | 2020-04-22 | COMP | 2020-04-13 | COMP | 2020-05-18 | COMP | Rule 16 | 2 | 100 | 15 | 32 | 0 | 19 | 164
14878 | 2019-09-23 | 2019-10-02 | 2020-04-26 | 2020-04-26 | COMP | 2020-05-08 | COMP | 2020-12-02 | COMP | 2020-11-30 | COMP | 2020-12-19 | COMP | Rule 16 | 8 | 141 | 10 | 144 | 0 | 13 | 313
14881 | 2019-09-23 | 2019-10-02 | 2019-12-12 | 2019-12-12 | COMP | 2020-01-03 | COMP | 2020-01-03 | COMP | 2020-02-19 | COMP | 2020-04-14 | COMP | Rule 15/16 | 8 | 49 | 15 | 1 | 32 | 40 | 140
14960 | 2019-09-23 | 2019-10-07 | 2019-11-29 | 2019-12-02 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-23 | COMP | 2020-05-27 | COMP | Rule 16 | 11 | 37 | 65 | 1 | 13 | 47 | 170
15005 | 2019-09-23 | 2019-10-09 | 2019-12-17 | 2019-12-17 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2020-02-19 | COMP | 2020-06-02 | COMP | Rule 16 | 13 | 47 | 8 | 1 | 36 | 74 | 174
15076 | 2019-09-23 | 2019-10-11 | 2019-12-18 | 2019-12-18 | COMP | 2020-01-16 | COMP | 2020-01-17 | COMP | 2020-04-02 | COMP | 2020-05-20 | COMP | Rule 16 | 15 | 46 | 20 | 2 | 53 | 35 | 166
15077 | 2019-09-23 | 2019-10-11 | 2019-12-12 | 2019-12-12 | COMP | 2020-03-09 | COMP | 2020-03-11 | COMP | 2020-05-19 | COMP | 2020-06-07 | COMP | Rule 16 | 15 | 42 | 59 | 3 | 50 | 13 | 177
15165 | 2019-09-23 | 2019-10-18 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-18 | COMP | 2020-02-18 | COMP | 2020-02-22 | COMP | 2020-05-29 | COMP | Rule 16 | 20 | 70 | 11 | 1 | 4 | 69 | 172
15431 | 2019-09-23 | 2019-11-01 | 2020-02-05 | 2020-02-05 | COMP | 2020-03-12 | COMP | 2020-07-09 | COMP | 2021-03-02 | COMP | 2021-03-30 | COMP | Rule 16 | 30 | 63 | 26 | 85 | 161 | 21 | 381
15465 | 2019-09-23 | 2019-11-04 | 2019-12-04 | 2019-12-04 | COMP | 2019-12-31 | COMP | 2019-12-31 | COMP | 2020-06-13 | COMP | 2020-06-16 | COMP | Rule 16 | 31 | 20 | 19 | 1 | 115 | 2 | 184
15635 | 2019-09-23 | 2019-11-13 | 2019-12-24 | 2019-12-24 | COMP | 2020-01-22 | COMP | 2020-01-22 | COMP | 2020-01-31 | COMP | 2020-02-24 | COMP | Rule 16 | 37 | 28 | 19 | 1 | 8 | 16 | 104
15658 | 2019-09-23 | 2019-11-14 | 2020-03-07 | 2020-06-04 | COMP | 2020-06-06 | NOTN | 2020-06-09 | COMP | 2020-06-06 | COMP | 2020-08-12 | COMP | Other | 38 | 76 |  | 4 | 0 | 47 | 225
15718 | 2019-09-23 | 2019-11-18 | 2020-01-11 | 2020-01-11 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-24 | COMP | 2020-07-28 | COMP | Rule 16 | 40 | 36 | 98 | 1 | 18 | 25 | 214
15855 | 2019-09-23 | 2019-11-26 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-17 | COMP | 2020-05-05 | COMP | 2020-03-13 | COMP | 2020-06-13 | COMP | Rule 16 | 46 | 28 | 8 | 76 | 0 | 28 | 182
16052 | 2019-09-23 | 2019-12-07 | 2020-01-23 | 2020-01-23 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-01-30 | COMP | 2020-02-14 | COMP | Rule 16 | 52 | 31 | 6 | 1 | 1 | 12 | 99
16258 | 2019-09-23 | 2019-12-18 | 2020-03-30 | 2020-03-30 | COMP | 2020-07-20 | COMP | 2020-09-25 | COMP | 2022-02-26 | INPR | 2021-01-16 | COMP | Rule 16 | 60 | 70 | 80 | 49 |  |  | 331
16310 | 2019-09-23 | 2019-12-19 | 2020-05-15 | 2020-05-15 | COMP | 2021-04-27 | COMP | 2021-08-23 | COMP | 2021-11-12 | COMP | 2021-12-06 | COMP | Rule 16 | 61 | 103 | 239 | 83 | 58 | 15 | 554
16382 | 2019-09-23 | 2019-12-23 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-28 | COMP | 2020-03-10 | COMP | 2020-03-30 | COMP | 2020-07-17 | COMP | Rule 15/16 | 63 | 13 | 12 | 30 | 15 | 79 | 207
16457 | 2019-09-23 | 2020-01-02 | 2020-06-16 | 2020-06-16 | COMP | 2020-06-30 | COMP | 2021-01-13 | COMP | 2021-06-01 | COMP | 2021-06-30 | COMP | Rule 15/16 | 69 | 116 | 11 | 136 | 97 | 22 | 446
16499 | 2019-09-23 | 2020-01-03 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-20 | COMP | 2020-03-12 | NOTN | 2020-03-11 | COMP | 2020-03-23 | COMP | Rule 15/16 | 70 | 20 | 14 |  |  |  | 124
16523 | 2019-09-23 | 2020-01-06 | 2020-03-07 | 2020-03-07 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-06-01 | COMP | 2020-06-19 | COMP | Rule 15/16 | 71 | 43 | 15 | 1 | 46 | 15 | 187
16602 | 2019-09-23 | 2020-01-09 | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | NOTN | 2020-09-17 | COMP | 2020-09-17 | COMP | 2021-02-27 | COMP | Other | 74 | 97 |  | 81 | 1 | 110 | 359
16673 | 2019-09-23 | 2020-01-10 | 2020-03-18 | 2020-03-18 | COMP | 2021-08-23 | COMP | 2021-09-13 | COMP | 2022-04-04 | COMP | 2022-04-20 | COMP | Rule 16 | 75 | 47 | 363 | 15 | 141 | 13 | 649
16717 | 2019-09-23 | 2020-01-14 | 2020-01-29 | 2020-02-20 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-04-30 | COMP | 2020-05-06 | COMP | Rule 16 | 77 | 11 | 31 | 1 | 21 | 5 | 156
17556 | 2019-09-23 | 2020-02-22 | 2020-05-23 | 2020-05-23 | COMP | 2020-08-20 | COMP | 2020-10-15 | COMP | 2020-11-23 | COMP | 2020-12-15 | COMP | Rule 15/16 | 103 | 65 | 63 | 40 | 27 | 15 | 310
17647 | 2019-09-23 | 2020-02-24 | 2020-04-17 | 2020-04-17 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-12-14 | COMP | 2021-08-19 | COMP | Rule 16 | 104 | 40 | 96 | 1 | 72 | 173 | 481
17691 | 2019-09-23 | 2020-02-24 | 2020-06-10 | 2020-06-10 | COMP | 2021-04-08 | COMP | 2021-04-08 | COMP | 2023-09-19 | COMP | 2023-10-02 | COMP | Rule 15/16 | 104 | 77 | 209 | 1 | 616 | 10 | 1012
17771 | 2019-09-23 | 2020-02-26 | 2020-05-28 | 2020-05-28 | COMP | 2020-02-26 | NOTN | 2020-05-28 | COMP | 2020-06-02 | COMP | 2020-08-09 | COMP | Other | 106 | 66 |  | 1 | 4 | 49 | 222
18237 | 2019-09-23 | 2020-03-16 | 2020-06-28 | 2020-06-28 | COMP | 2020-09-30 | COMP | 2020-10-21 | COMP | 2020-10-30 | COMP | 2020-11-30 | COMP | Rule 16 | 119 | 74 | 67 | 16 | 8 | 19 | 299
18377 | 2019-09-23 | 2020-03-21 | 2020-12-19 | 2020-12-19 | COMP | 2021-06-29 | COMP | 2021-06-29 | COMP | 2021-08-15 | COMP | 2022-03-15 | COMP | Rule 16 | 123 | 190 | 132 | 1 | 33 | 146 | 623
19028 | 2019-09-23 | 2020-04-17 | 2020-06-08 | 2020-06-08 | COMP | 2020-09-16 | COMP | 2020-10-20 | COMP | 2020-12-17 | COMP | 2021-01-31 | COMP | Rule 16 | 143 | 36 | 72 | 25 | 40 | 29 | 340
14816 | 2019-09-24 | 2019-09-30 | 2020-02-09 | 2020-02-09 | COMP | 2019-09-30 | NOTN | 2020-02-09 | COMP | 2020-02-24 | COMP | 2020-03-20 | COMP | Other | 5 | 89 |  | 0 | 10 | 20 | 122
14820 | 2019-09-24 | 2019-09-29 | 2020-05-01 | 2020-05-01 | COMP | 2021-03-03 | COMP | 2021-06-25 | COMP | 2021-06-29 | COMP | 2021-08-31 | COMP | Rule 15/16 | 4 | 148 | 210 | 82 | 3 | 45 | 488
15039 | 2019-09-24 | 2019-10-10 | 2020-02-19 | 2020-02-19 | COMP | 2020-05-06 | COMP | 2020-06-03 | COMP | 2020-04-14 | COMP | 2020-10-28 | COMP | Rule 16 | 13 | 88 | 56 | 20 | 0 | 105 | 278
15309 | 2019-09-24 | 2019-10-25 | 2020-01-23 | 2021-07-16 | COMP | 2021-07-22 | COMP | 2020-04-01 | COMP | 2021-05-28 | COMP | 2021-08-28 | COMP | Rule 16 | 24 | 59 | 5 |  | 294 | 64 | 486
15340 | 2019-09-24 | 2019-10-28 | 2020-02-24 | 2020-03-31 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-08-18 | COMP | 2020-09-16 | COMP | Rule 16 | 25 | 79 | 91 | 1 | 10 | 21 | 248
15457 | 2019-09-24 | 2019-11-02 | 2019-12-22 | 2019-12-22 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-02-11 | COMP | 2020-04-29 | COMP | Rule 16 | 29 | 32 | 9 | 1 | 26 | 56 | 150
15474 | 2019-09-24 | 2019-11-05 | 2020-09-19 | 2020-09-19 | COMP | 2021-02-01 | COMP | 2021-09-09 | COMP | 2022-09-14 | COMP | 2022-11-11 | COMP | Rule 15/16 | 31 | 220 | 90 | 155 | 256 | 42 | 790
15702 | 2019-09-24 | 2019-11-18 | 2020-01-25 | 2020-01-28 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-07-22 | COMP | 2020-09-01 | COMP | Rule 15 | 39 | 45 | 42 | 1 | 84 | 30 | 238
15767 | 2019-09-24 | 2019-11-20 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-08-17 | COMP | Rule 16 | 41 | 144 | 31 | 1 | 1 | 14 | 227
15807 | 2019-09-24 | 2019-11-20 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-12 | COMP | 2020-04-13 | COMP | 2020-04-28 | COMP | 2020-07-13 | COMP | Rule 16 | 41 | 68 | 9 | 23 | 12 | 54 | 202
15889 | 2019-09-24 | 2019-11-25 | 2020-01-13 | 2020-01-13 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-08-07 | COMP | 2020-08-18 | COMP | Rule 15/16 | 44 | 32 | 15 | 1 | 133 | 8 | 228
15906 | 2019-09-24 | 2019-11-26 | 2020-01-14 | 2020-01-14 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-05-29 | COMP | 2020-08-12 | COMP | Rule 16 | 45 | 32 | 19 | 1 | 78 | 54 | 224
15985 | 2019-09-24 | 2019-12-04 | 2019-12-22 | 2019-12-22 | COMP | 2020-01-15 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-03-11 | COMP | Rule 16 | 49 | 13 | 16 | 26 | 1 | 14 | 115
16187 | 2019-09-24 | 2019-12-13 | 2020-03-23 | 2020-03-23 | COMP | 2020-03-31 | COMP | 2020-05-14 | COMP | 2020-04-23 | COMP | 2020-05-26 | COMP | Rule 16 | 56 | 68 | 7 | 33 | 0 | 8 | 168
16200 | 2019-09-24 | 2019-12-15 | 2020-05-25 | 2020-05-25 | COMP | 2020-08-13 | COMP | 2020-09-10 | COMP | 2020-08-18 | COMP | 2020-10-12 | COMP | Rule 15/16 | 56 | 111 | 58 | 20 | 0 | 23 | 266
16224 | 2019-09-24 | 2019-12-17 | 2020-04-21 | 2020-04-21 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-05-26 | COMP | 2020-07-08 | COMP | Rule 16 | 58 | 87 | 14 | 1 | 12 | 32 | 199
16274 | 2019-09-24 | 2019-12-18 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-01 | COMP | 2020-08-07 | COMP | 2023-05-27 | INPR | 2020-11-20 | COMP | Rule 16 | 59 | 110 | 5 | 50 |  |  | 294
17551 | 2019-09-24 | 2020-02-20 | 2020-07-31 | 2020-07-31 | COMP | 2020-10-14 | COMP | 2021-01-19 | COMP | 2021-01-20 | COMP | 2021-03-02 | COMP | Rule 16 | 101 | 116 | 53 | 64 | 2 | 29 | 360
18019 | 2019-09-24 | 2020-03-09 | 2020-05-20 | 2021-11-12 | COMP | 2022-03-04 | COMP | 2021-07-21 | COMP | 2022-04-05 | COMP | 2022-04-29 | COMP | Rule 16 | 113 | 53 | 77 |  | 179 | 19 | 655
18068 | 2019-09-24 | 2020-03-11 | 2020-04-24 | 2020-09-27 | COMP | 2020-10-02 | COMP | 2020-11-19 | COMP | 2023-11-13 | INPR | 2021-02-17 | COMP | Rule 16 | 115 | 33 | 5 | 34 |  |  | 351
18958 | 2019-09-24 | 2020-04-15 | 2020-07-20 | 2020-07-20 | COMP | 2020-12-10 | COMP | 2020-12-10 | COMP | 2021-07-27 | COMP | 2021-08-25 | COMP | Other | 140 | 68 | 100 | 1 | 158 | 22 | 484
19676 | 2019-09-24 | 2020-05-17 | 2020-07-16 | 2020-07-16 | COMP | 2020-08-03 | NOTN | 2020-08-03 | COMP | 2020-08-18 | COMP | 2020-12-18 | COMP | Other | 162 | 43 |  | 13 | 12 | 85 | 312
24591 | 2019-09-24 | 2020-12-31 | 2021-03-05 | 2021-03-05 | COMP | 2021-05-04 | COMP | 2021-05-04 | COMP | 2021-05-25 | COMP | 2021-06-28 | COMP | Rule 16 | 320 | 44 | 43 | 1 | 16 | 24 | 443
4236 | 2019-09-25 | 2019-09-25 | 2019-09-26 | 2019-09-26 | COMP | 2019-09-30 | NOTN | 2019-09-30 | COMP | 2019-09-30 | COMP | 2019-11-25 | COMP | Rule 15/16 | 1 | 2 |  | 3 | 1 | 40 | 43
14760 | 2019-09-25 | 2019-09-26 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-30 | COMP | 2020-01-24 | COMP | 2020-01-09 | COMP | 2020-02-12 | COMP | Rule 16 | 2 | 46 | 19 | 18 | 0 | 14 | 95
14845 | 2019-09-25 | 2019-10-01 | 2020-01-28 | 2020-01-28 | COMP | 2022-02-23 | COMP | 2022-02-23 | COMP | 2022-02-23 | COMP | 2022-07-15 | COMP | Rule 16 | 5 | 80 | 524 | 1 | 1 | 100 | 706
15030 | 2019-09-25 | 2019-10-10 | 2020-01-30 | 2020-01-30 | COMP | 2020-06-10 | COMP | 2020-07-06 | COMP | 2020-10-02 | COMP | 2020-10-20 | COMP | Rule 16 | 12 | 75 | 93 | 19 | 64 | 13 | 271
15310 | 2019-09-25 | 2019-10-25 | 2020-03-27 | 2020-03-27 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-12-22 | COMP | 2021-01-26 | COMP | Rule 16 | 23 | 104 | 20 | 1 | 169 | 23 | 335
15329 | 2019-09-25 | 2019-10-28 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-03-13 | COMP | 2020-05-01 | COMP | Rule 15/16 | 24 | 63 | 8 | 1 | 24 | 36 | 151
15368 | 2019-09-25 | 2019-10-28 | 2020-02-21 | 2020-03-14 | COMP | 2020-05-01 | COMP | 2020-05-01 | COMP | 2020-07-21 | COMP | 2020-09-05 | COMP | Rule 15/16 | 24 | 78 | 35 | 1 | 57 | 34 | 240
15705 | 2019-09-25 | 2019-11-19 | 2020-02-09 | 2020-02-09 | COMP | 2020-06-03 | COMP | 2020-02-28 | COMP | 2020-07-24 | COMP | 2020-07-28 | COMP | Rule 16 | 39 | 54 | 81 |  | 105 | 3 | 212
15746 | 2019-09-25 | 2019-11-19 | 2020-05-12 | 2020-10-28 | COMP | 2020-05-12 | NOTN | 2022-08-17 | COMP | 2020-06-12 | COMP | 2022-08-30 | COMP | Other | 39 | 120 |  | 453 | 0 | 10 | 738
15853 | 2019-09-25 | 2019-11-26 | 2020-02-25 | 2020-02-25 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-03-25 | COMP | 2020-04-16 | COMP | Rule 16 | 44 | 60 | 4 | 1 | 19 | 17 | 140
15854 | 2019-09-25 | 2019-11-26 | 2020-01-08 | 2020-01-14 | COMP | 2020-01-14 | NOTN | 2020-01-14 | COMP | 2020-02-18 | COMP | 2020-02-24 | COMP | Other | 44 | 28 |  | 1 | 24 | 5 | 102
16130 | 2019-09-25 | 2019-12-10 | 2020-06-08 | 2020-10-09 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2020-10-30 | COMP | 2020-12-11 | COMP | Rule 16 | 52 | 125 | 10 | 1 | 7 | 28 | 306
16131 | 2019-09-25 | 2019-12-10 | 2020-01-17 | 2020-05-12 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-07-06 | COMP | 2020-07-09 | COMP | Rule 16 | 52 | 27 | 14 | 1 | 26 | 4 | 199
16203 | 2019-09-25 | 2019-12-13 | 2020-06-11 | 2020-08-09 | COMP | 2020-09-04 | COMP | 2020-10-28 | INPR | 2020-08-13 | COMP | 2020-10-09 | COMP | Rule 16 | 55 | 125 | 20 |  |  |  | 264
16279 | 2019-09-25 | 2019-12-18 | 2020-03-17 | 2020-03-17 | COMP | 2020-03-27 | COMP | 2020-04-08 | COMP | 2020-07-31 | COMP | 2020-08-13 | COMP | Rule 16 | 58 | 61 | 9 | 9 | 82 | 10 | 224
16490 | 2019-09-25 | 2020-01-04 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-07-29 | COMP | 2020-09-18 | COMP | Rule 16 | 68 | 17 | 26 | 1 | 104 | 37 | 249
16809 | 2019-09-25 | 2020-01-16 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-20 | COMP | 2020-05-08 | COMP | 2020-05-11 | COMP | 2021-02-15 | COMP | Rule 16 | 77 | 44 | 23 | 15 | 2 | 192 | 348
17161 | 2019-09-25 | 2020-02-04 | 2020-03-24 | 2020-03-24 | COMP | 2020-06-02 | COMP | 2020-06-03 | COMP | 2020-07-22 | COMP | 2020-09-10 | COMP | Rule 16 | 89 | 35 | 50 | 2 | 36 | 36 | 243
17444 | 2019-09-25 | 2020-02-13 | 2020-06-05 | 2020-06-05 | COMP | 2020-08-21 | COMP | 2020-09-16 | COMP | 2020-11-01 | COMP | 2020-11-03 | COMP | Rule 16 | 96 | 80 | 56 | 18 | 33 | 2 | 281
17453 | 2019-09-25 | 2020-02-13 | 2020-09-02 | 2020-09-02 | COMP | 2021-02-08 | COMP | 2021-04-06 | COMP | 2021-06-07 | COMP | 2021-06-29 | COMP | Rule 16 | 96 | 143 | 107 | 41 | 44 | 17 | 443
17625 | 2019-09-25 | 2020-02-22 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2021-05-30 | INPR | 2020-05-14 | COMP | Rule 16 | 101 | 36 | 7 | 1 |  |  | 160
18112 | 2019-09-25 | 2020-03-11 | 2020-04-19 | 2020-04-19 | COMP | 2020-05-01 | COMP | 2020-06-13 | COMP | 2020-06-08 | COMP | 2020-06-25 | COMP | Rule 16 | 114 | 28 | 10 | 30 | 0 | 9 | 189
18281 | 2019-09-25 | 2020-03-19 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-08-10 | COMP | 2020-09-15 | COMP | Rule 16 | 120 | 34 | 7 | 1 | 63 | 26 | 246
19116 | 2019-09-25 | 2020-04-22 | 2020-09-01 | 2020-09-01 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2020-09-03 | COMP | 2020-10-12 | COMP | Rule 15/16 | 144 | 94 | 7 | 1 | 0 | 23 | 265
19905 | 2019-09-25 | 2020-05-27 | 2020-06-08 | 2020-06-08 | COMP | 2020-07-13 | COMP | 2020-08-28 | COMP | 2022-04-26 | COMP | 2022-06-15 | COMP | Rule 16 | 168 | 9 | 26 | 35 | 417 | 36 | 686
14891 | 2019-09-26 | 2019-10-02 | 2019-12-20 | 2019-12-20 | COMP | 2020-09-02 | COMP | 2020-09-02 | COMP | 2020-09-23 | COMP | 2020-09-28 | COMP | Rule 16 | 5 | 55 | 179 | 1 | 15 | 4 | 254
14965 | 2019-09-26 | 2019-10-08 | 2019-10-29 | 2019-10-29 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2019-11-06 | COMP | 2019-11-07 | COMP | Rule 16 | 9 | 16 | 7 | 1 | 1 | 2 | 31
15049 | 2019-09-26 | 2019-10-10 | 2020-01-16 | 2020-01-16 | COMP | 2020-06-25 | COMP | 2020-09-04 | COMP | 2020-09-04 | COMP | 2020-10-03 | COMP | Rule 15/16 | 11 | 66 | 113 | 52 | 1 | 20 | 258
15256 | 2019-09-26 | 2019-10-23 | 2020-01-23 | 2020-01-23 | COMP | 2020-03-02 | COMP | 2020-03-17 | COMP | 2021-03-02 | COMP | 2021-04-06 | COMP | Rule 15/16 | 20 | 61 | 27 | 12 | 242 | 26 | 383
15414 | 2019-09-26 | 2019-11-01 | 2020-03-24 | 2020-03-24 | COMP | 2020-03-23 | NOTN | 2020-03-24 | COMP | 2020-05-05 | COMP | 2020-09-22 | COMP | Other | 27 | 96 |  | 1 | 31 | 99 | 250
15538 | 2019-09-26 | 2019-11-06 | 2019-12-24 | 2019-12-24 | COMP | 2020-02-27 | COMP | 2020-02-28 | COMP | 2020-05-26 | COMP | 2020-06-15 | COMP | Rule 16 | 30 | 32 | 44 | 2 | 62 | 15 | 180
15701 | 2019-09-26 | 2019-11-18 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-03 | COMP | 2020-03-26 | COMP | Rule 16 | 37 | 62 | 9 | 1 | 2 | 18 | 124
16145 | 2019-09-26 | 2019-12-12 | 2020-03-23 | 2020-03-23 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-24 | COMP | 2020-09-12 | COMP | Rule 16 | 53 | 69 | 80 | 1 | 10 | 35 | 243
16184 | 2019-09-26 | 2019-12-13 | 2020-11-19 | 2020-11-19 | COMP | 2021-01-26 | COMP | 2021-01-26 | COMP | 2021-10-19 | COMP | 2021-11-29 | COMP | Rule 16 | 54 | 238 | 44 | 1 | 187 | 27 | 546
16206 | 2019-09-26 | 2019-12-16 | 2020-04-30 | 2020-04-30 | COMP | 2020-07-06 | COMP | 2021-02-03 | COMP | 2023-11-13 | INPR | 2021-03-18 | COMP | Rule 16 | 55 | 95 | 47 | 146 |  |  | 370
16836 | 2019-09-26 | 2020-01-17 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-19 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-08-19 | COMP | Rule 16 | 77 | 79 | 8 | 32 | 1 | 35 | 227
17010 | 2019-09-26 | 2020-01-27 | 2020-07-31 | 2020-07-31 | COMP | 2020-10-09 | COMP | 2020-11-04 | COMP | 2020-12-15 | COMP | 2021-04-22 | COMP | Rule 16 | 82 | 133 | 50 | 19 | 27 | 89 | 395
17060 | 2019-09-26 | 2020-01-29 | 2020-03-16 | 2020-03-16 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-06-16 | COMP | 2020-07-29 | COMP | Rule 16 | 84 | 33 | 42 | 1 | 25 | 32 | 212
17061 | 2019-09-26 | 2020-01-29 | 2020-04-07 | 2020-04-07 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-06-16 | COMP | 2020-07-28 | COMP | Rule 16 | 84 | 49 | 30 | 1 | 21 | 31 | 211
17062 | 2019-09-26 | 2020-01-29 | 2020-04-14 | 2020-04-14 | COMP | 2020-05-12 | COMP | 2020-07-27 | COMP | 2020-07-10 | COMP | 2020-09-08 | COMP | Rule 16 | 84 | 54 | 21 | 54 | 0 | 31 | 240
17196 | 2019-09-26 | 2020-02-04 | 2020-03-17 | 2020-03-17 | COMP | 2020-03-27 | COMP | 2020-04-10 | COMP | 2020-03-27 | COMP | 2020-06-11 | COMP | Rule 16 | 88 | 30 | 9 | 11 | 0 | 44 | 178
17272 | 2019-09-26 | 2020-02-07 | 2021-02-23 | 2021-02-23 | COMP | 2021-06-07 | COMP | 2021-08-03 | COMP | 2022-12-01 | COMP | 2021-09-24 | COMP | Rule 15/16 | 91 | 263 | 74 | 41 | 335 |  | 503
17389 | 2019-09-26 | 2020-02-12 | 2020-03-04 | 2020-03-04 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-05-14 | COMP | 2020-05-29 | COMP | Rule 16 | 94 | 15 | 13 | 1 | 40 | 11 | 169
17550 | 2019-09-26 | 2020-02-20 | 2020-08-31 | 2020-09-30 | COMP | 2020-11-20 | COMP | 2020-11-23 | COMP | 2021-03-18 | COMP | 2021-05-19 | COMP | Rule 16 | 99 | 137 | 37 | 2 | 78 | 45 | 414
17552 | 2019-09-26 | 2020-02-20 | 2020-08-31 | 2020-09-30 | COMP | 2020-10-16 | COMP | 2022-02-09 | COMP | 2023-12-03 | INPR | 2022-03-12 | COMP | Rule 16 | 99 | 137 | 13 | 330 |  |  | 618
18067 | 2019-09-26 | 2020-03-10 | 2020-04-10 | 2020-04-30 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-07-17 | COMP | 2020-08-06 | COMP | Rule 16 | 112 | 24 | 13 | 1 | 44 | 15 | 218
18873 | 2019-09-26 | 2020-04-09 | 2020-06-17 | 2020-12-24 | COMP | 2021-03-04 | COMP | 2021-03-16 | COMP | 2021-02-16 | COMP | 2021-03-30 | COMP | Rule 16 | 134 | 49 | 47 | 9 | 0 | 11 | 378
18883 | 2019-09-26 | 2020-04-10 | 2020-05-12 | 2020-05-12 | COMP | 2020-07-17 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-27 | COMP | Rule 16 | 135 | 23 | 48 | 6 | 1 | 25 | 233
19823 | 2019-09-26 | 2020-05-22 | 2021-06-24 | 2021-06-24 | COMP | 2021-07-15 | COMP | 2022-05-31 | COMP | 2022-05-03 | COMP | 2022-10-07 | COMP | Rule 15/16 | 165 | 275 | 15 | 222 | 0 | 91 | 764
4282 | 2019-09-27 | 2020-03-19 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-08 | COMP | 2020-06-30 | COMP | 2020-08-14 | COMP | 2020-09-17 | COMP | Rule 16 | 118 | 6 | 32 | 37 | 34 | 24 | 246
14917 | 2019-09-27 | 2019-10-03 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-18 | COMP | 2019-12-18 | COMP | 2020-02-25 | COMP | 2020-03-02 | COMP | Rule 16 | 5 | 48 | 5 | 1 | 46 | 5 | 105
15018 | 2019-09-27 | 2019-10-09 | 2020-03-11 | 2020-03-11 | COMP | 2020-04-09 | COMP | 2020-11-02 | COMP | 2020-12-08 | COMP | 2020-12-09 | COMP | Rule 15/16 | 9 | 104 | 22 | 146 | 24 | 2 | 302
15059 | 2019-09-27 | 2019-10-10 | 2019-12-22 | 2019-12-22 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-04-15 | COMP | 2020-05-13 | COMP | Rule 16 | 10 | 49 | 9 | 1 | 71 | 21 | 157
15112 | 2019-09-27 | 2019-10-17 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-10 | COMP | 2020-04-28 | COMP | Rule 16 | 15 | 79 | 34 | 1 | 9 | 13 | 146
15195 | 2019-09-27 | 2019-10-18 | 2019-11-06 | 2020-02-19 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-03-18 | COMP | 2020-06-25 | COMP | Rule 16 | 16 | 14 | 3 | 1 | 19 | 71 | 187
15230 | 2019-09-27 | 2019-10-21 | 2020-03-08 | 2020-03-18 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-04-07 | COMP | 2020-05-19 | COMP | Rule 16 | 17 | 93 | 12 | 1 | 4 | 31 | 161
15269 | 2019-09-27 | 2019-10-23 | 2020-03-09 | 2020-04-14 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-12-21 | COMP | 2021-02-04 | COMP | Other | 19 | 92 | 75 | 1 | 101 | 31 | 340
15295 | 2019-09-27 | 2019-10-24 | 2019-12-12 | 2019-12-12 | COMP | 2019-12-12 | NOTN | 2019-12-12 | COMP | 2019-12-12 | NOTN | 2020-01-22 | COMP | Other | 20 | 33 |  | 1 |  |  | 78
15437 | 2019-09-27 | 2019-10-31 | 2020-03-13 | 2020-03-13 | COMP | 2020-04-13 | COMP | 2020-07-06 | COMP | 2020-07-13 | COMP | 2020-07-29 | COMP | Rule 15/16 | 25 | 90 | 22 | 60 | 6 | 13 | 211
15996 | 2019-09-27 | 2019-12-04 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-03-25 | COMP | 2020-04-07 | COMP | Rule 16 | 46 | 30 | 17 | 1 | 32 | 10 | 131
16169 | 2019-09-27 | 2019-12-13 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-13 | COMP | 2020-04-17 | COMP | 2020-06-18 | COMP | 2020-07-22 | COMP | Rule 16 | 53 | 63 | 21 | 5 | 44 | 25 | 206
16186 | 2019-09-27 | 2019-12-13 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2021-06-24 | COMP | 2021-07-27 | COMP | Rule 16 | 53 | 63 | 13 | 1 | 312 | 23 | 460
16232 | 2019-09-27 | 2019-12-16 | 2020-04-13 | 2021-02-12 | COMP | 2021-03-25 | COMP | 2020-05-04 | COMP | 2022-06-18 | INPR | 2021-06-09 | COMP | Rule 16 | 54 | 82 | 29 |  |  |  | 427
16329 | 2019-09-27 | 2019-12-20 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2021-04-03 | COMP | 2021-04-19 | COMP | Rule 16 | 58 | 87 | 18 | 1 | 220 | 11 | 391
16411 | 2019-09-27 | 2019-12-27 | 2020-03-10 | 2020-03-10 | COMP | 2020-04-03 | COMP | 2020-04-03 | COMP | 2020-06-15 | COMP | 2020-06-29 | COMP | Rule 16 | 62 | 50 | 19 | 1 | 51 | 11 | 189
16672 | 2019-09-27 | 2020-01-10 | 2020-05-12 | 2020-05-12 | COMP | 2021-01-08 | COMP | 2021-07-06 | COMP | 2021-06-21 | COMP | 2021-09-02 | COMP | Rule 16 | 71 | 86 | 167 | 124 | 0 | 43 | 487
16921 | 2019-09-27 | 2020-01-23 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-07 | COMP | 2020-11-05 | COMP | 2020-12-07 | COMP | 2020-12-14 | COMP | Rule 16 | 79 | 47 | 29 | 129 | 20 | 6 | 305
17120 | 2019-09-27 | 2020-01-31 | 2020-04-07 | 2020-04-07 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2021-03-25 | COMP | 2021-05-20 | COMP | Rule 16 | 85 | 47 | 80 | 1 | 165 | 41 | 414
17715 | 2019-09-27 | 2020-02-24 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-12-03 | COMP | 2020-12-31 | COMP | Rule 16 | 100 | 88 | 36 | 1 | 77 | 20 | 317
18196 | 2019-09-27 | 2020-03-16 | 2020-07-03 | 2020-07-03 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | 2021-03-16 | COMP | 2021-03-30 | COMP | Rule 16 | 115 | 79 | 103 | 1 | 73 | 11 | 377
18224 | 2019-09-27 | 2020-03-16 | 2020-06-11 | 2020-06-11 | COMP | 2022-10-03 | COMP | 2022-11-02 | COMP | 2022-11-02 | COMP | 2023-02-01 | COMP | Rule 15/16 | 115 | 63 | 583 | 23 | 1 | 60 | 840
18500 | 2019-09-27 | 2020-03-26 | 2020-06-30 | 2020-07-30 | COMP | 2020-08-04 | COMP | 2020-08-05 | COMP | 2020-08-11 | COMP | 2020-08-25 | COMP | Rule 15/16 | 123 | 68 | 4 | 2 | 5 | 11 | 230
15028 | 2019-09-28 | 2019-10-09 | 2020-05-21 | 2020-11-24 | COMP | 2020-12-07 | COMP | 2021-04-02 | COMP | 2021-07-26 | COMP | 2021-09-03 | COMP | Rule 15/16 | 8 | 155 | 8 | 81 | 80 | 30 | 487
16687 | 2019-09-28 | 2020-01-12 | 2021-01-05 | 2021-01-05 | COMP | 2021-01-06 | NOTN | 2021-05-03 | COMP | 2021-05-06 | COMP | 2021-06-30 | COMP | Other | 70 | 248 |  | 83 | 4 | 39 | 441
15455 | 2019-09-29 | 2019-11-01 | 2019-12-25 | 2019-12-25 | COMP | 2020-01-06 | COMP | 2020-01-09 | COMP | 2020-04-22 | COMP | 2020-07-09 | COMP | Rule 16 | 25 | 35 | 7 | 4 | 73 | 56 | 196
16410 | 2019-09-29 | 2019-12-27 | 2020-03-30 | 2020-03-30 | COMP | 2020-10-01 | COMP | 2020-11-18 | COMP | 2020-10-30 | COMP | 2020-12-28 | COMP | Rule 16 | 61 | 64 | 132 | 34 | 0 | 26 | 313
16421 | 2019-09-29 | 2019-12-30 | 2020-03-16 | 2020-03-16 | COMP | 2020-10-01 | COMP | 2020-10-01 | COMP | 2020-10-01 | COMP | 2020-11-04 | COMP | Rule 16 | 62 | 53 | 142 | 1 | 1 | 25 | 279
18985 | 2019-09-29 | 2020-04-16 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2021-02-17 | COMP | 2021-03-05 | COMP | Rule 16 | 137 | 22 | 7 | 1 | 184 | 13 | 359
14825 | 2019-09-30 | 2019-10-01 | 2020-01-27 | 2020-01-27 | COMP | 2020-04-28 | COMP | 2020-07-01 | COMP | 2020-06-29 | COMP | 2020-08-11 | COMP | Rule 15/16 | 2 | 79 | 66 | 46 | 0 | 30 | 219
14935 | 2019-09-30 | 2019-10-04 | 2020-03-03 | 2020-03-03 | COMP | 2020-05-12 | COMP | 2020-12-17 | COMP | 2020-10-21 | COMP | 2021-03-19 | COMP | Rule 15/16 | 5 | 101 | 51 | 153 | 0 | 63 | 369
15267 | 2019-09-30 | 2019-10-23 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-16 | COMP | 2020-04-23 | COMP | 2020-03-23 | COMP | 2020-07-29 | COMP | Rule 16 | 18 | 82 | 16 | 29 | 0 | 69 | 210
15284 | 2019-09-30 | 2019-10-24 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-03-13 | COMP | 2020-03-24 | COMP | Rule 16 | 19 | 55 | 28 | 1 | 14 | 8 | 120
15285 | 2019-09-30 | 2019-10-24 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-11 | COMP | 2020-07-31 | COMP | 2020-10-13 | COMP | 2020-10-29 | COMP | Rule 16 | 19 | 146 | 13 | 37 | 52 | 13 | 275
15298 | 2019-09-30 | 2019-10-24 | 2019-11-19 | 2019-11-19 | COMP | 2019-12-02 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-01-30 | COMP | Rule 16 | 19 | 18 | 8 | 32 | 1 | 10 | 83
15413 | 2019-09-30 | 2019-11-01 | 2020-04-02 | 2020-04-02 | COMP | 2020-05-18 | COMP | 2021-06-29 | COMP | 2021-08-11 | COMP | 2022-02-23 | COMP | Rule 16 | 25 | 103 | 33 | 282 | 31 | 135 | 604
15513 | 2019-09-30 | 2019-11-05 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-02-20 | COMP | 2020-04-16 | COMP | Rule 16 | 27 | 71 | 13 | 1 | 0 | 29 | 137
15590 | 2019-09-30 | 2019-11-08 | 2019-12-27 | 2020-01-09 | COMP | 2020-01-15 | COMP | 2020-01-16 | COMP | 2020-01-06 | COMP | 2020-01-30 | COMP | Rule 16 | 30 | 32 | 5 | 2 | 0 | 10 | 83
15592 | 2019-09-30 | 2019-11-08 | 2019-12-09 | 2019-12-09 | COMP | 2019-12-20 | COMP | 2020-01-06 | COMP | 2020-01-06 | COMP | 2020-01-30 | COMP | Rule 16 | 30 | 19 | 10 | 10 | 1 | 18 | 83
16057 | 2019-09-30 | 2019-12-07 | 2020-04-09 | 2020-04-17 | COMP | 2020-08-10 | COMP | 2020-08-25 | COMP | 2022-01-30 | INPR | 2020-11-30 | COMP | Rule 16 | 47 | 85 | 81 | 12 |  |  | 294
16234 | 2019-09-30 | 2019-12-17 | 2020-08-10 | 2020-09-18 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2022-08-30 | COMP | 2023-02-09 | COMP | Rule 16 | 54 | 165 | 22 | 1 | 469 | 111 | 845
16633 | 2019-09-30 | 2020-01-10 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-25 | COMP | 2020-05-27 | COMP | 2020-08-04 | COMP | 2020-09-21 | COMP | Rule 16 | 70 | 18 | 14 | 66 | 50 | 34 | 247
17182 | 2019-09-30 | 2020-02-03 | 2020-05-19 | 2020-11-19 | COMP | 2020-11-25 | COMP | 2020-12-02 | COMP | 2020-12-01 | COMP | 2021-01-19 | COMP | Rule 16 | 85 | 76 | 5 | 4 | 0 | 32 | 327
17195 | 2019-09-30 | 2020-02-04 | 2020-06-19 |  | REQD | 2020-10-08 | NOTN | 2020-08-10 | COMP | 2020-08-31 | COMP | 2020-09-17 | COMP | Unknown | 86 |  |  |  | 16 | 13 | 245
17543 | 2019-09-30 | 2020-02-20 | 2020-05-29 | 2020-05-29 | COMP | 2020-08-14 | COMP | 2020-12-11 | COMP | 2020-12-21 | COMP | 2021-01-25 | COMP | Rule 16 | 97 | 71 | 56 | 82 | 7 | 23 | 331
17561 | 2019-09-30 | 2020-02-20 | 2020-03-04 | 2020-03-13 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-05-15 | COMP | 2020-06-10 | COMP | Rule 16 | 97 | 10 | 31 | 1 | 16 | 18 | 175
17588 | 2019-09-30 | 2020-02-20 | 2020-06-02 | 2020-06-02 | COMP | 2020-08-06 | COMP | 2020-08-06 | INPR | 2020-08-04 | COMP | 2020-08-27 | COMP | Rule 16 | 97 | 73 | 48 |  |  |  | 231
17743 | 2019-09-30 | 2020-02-25 | 2020-04-10 | 2020-04-10 | COMP | 2021-02-08 | COMP | 2021-02-08 | NOTN | 2021-11-10 | COMP | 2021-11-23 | COMP | Rule 16 | 100 | 34 | 209 |  |  |  | 542
17888 | 2019-09-30 | 2020-03-03 | 2020-03-11 | 2020-03-22 | COMP | 2020-07-14 | COMP | 2020-07-16 | COMP |  |  | 2020-08-01 | COMP | Rule 16 | 105 | 7 | 81 | 3 |  |  | 212
18830 | 2019-09-30 | 2020-04-08 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-26 | COMP | 2020-08-05 | COMP | 2020-08-07 | COMP | 2020-09-11 | COMP | Rule 16 | 131 | 21 | 14 | 52 | 3 | 25 | 241
19334 | 2019-09-30 | 2020-04-30 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-07-03 | COMP | 2020-08-05 | COMP | Rule 16 | 147 | 26 | 13 | 1 | 9 | 24 | 215
4244 | 2019-10-01 | 2019-10-18 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-27 | COMP | 2020-03-31 | COMP | 2020-03-30 | COMP | 2020-04-27 | COMP | Rule 16 | 14 | 56 | 11 | 46 | 0 | 20 | 143
14869 | 2019-10-01 | 2019-10-01 | 2019-12-06 | 2019-12-06 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-09-10 | COMP | 2020-11-24 | COMP | Rule 16 | 1 | 46 | 158 | 1 | 37 | 53 | 291
15019 | 2019-10-01 | 2019-10-09 | 2019-11-21 | 2019-11-21 | COMP | 2019-11-25 | COMP | 2019-12-12 | COMP | 2020-01-10 | COMP | 2020-01-13 | COMP | Rule 16 | 7 | 31 | 3 | 12 | 20 | 2 | 70
15053 | 2019-10-01 | 2019-10-10 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-02 | COMP | 2019-12-02 | COMP | 2020-01-07 | COMP | 2020-01-13 | COMP | Rule 16 | 8 | 26 | 10 | 1 | 25 | 5 | 70
15083 | 2019-10-01 | 2019-10-11 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-04-03 | COMP | Rule 16 | 9 | 90 | 6 | 1 | 1 | 25 | 127
15156 | 2019-10-01 | 2019-10-16 | 2020-01-07 | 2020-01-07 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2021-10-23 | INPR | 2020-06-13 | COMP | Rule 16 | 12 | 55 | 89 | 1 |  |  | 176
15157 | 2019-10-01 | 2019-10-16 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2020-05-23 | COMP | 2020-06-04 | COMP | Rule 16 | 12 | 70 | 39 | 1 | 44 | 8 | 170
15241 | 2019-10-01 | 2019-10-22 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-12 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-06-24 | COMP | Rule 16 | 16 | 88 | 9 | 4 | 1 | 71 | 184
15349 | 2019-10-01 | 2019-10-28 | 2020-01-18 | 2020-01-18 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-06-22 | COMP | 2020-07-17 | COMP | Rule 16 | 20 | 55 | 27 | 1 | 82 | 20 | 201
15418 | 2019-10-01 | 2019-10-31 | 2020-01-24 | 2020-01-24 | COMP | 2020-03-06 | COMP | 2020-03-06 | COMP | 2020-03-07 | COMP | 2020-06-08 | COMP | Rule 16 | 23 | 56 | 30 | 1 | 1 | 65 | 172
15632 | 2019-10-01 | 2019-11-13 | 2020-01-18 | 2020-01-18 | COMP | 2020-02-05 | COMP | 2020-03-09 | COMP | 2020-02-18 | COMP | 2020-03-31 | COMP | Rule 16 | 31 | 44 | 12 | 23 | 0 | 17 | 124
15686 | 2019-10-01 | 2019-11-15 | 2020-03-05 | 2020-03-05 | COMP | 2020-03-11 | COMP | 2020-03-12 | COMP | 2020-11-20 | COMP | 2020-12-17 | COMP | Rule 16 | 33 | 74 | 5 | 2 | 179 | 18 | 306
15688 | 2019-10-01 | 2019-11-15 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-08 | COMP | 2020-01-24 | COMP | 2020-01-15 | COMP | 2020-02-18 | COMP | Rule 15/16 | 33 | 28 | 7 | 12 | 0 | 17 | 94
15734 | 2019-10-01 | 2019-11-20 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-08-05 | COMP | 2020-08-10 | COMP | Rule 16 | 36 | 36 | 13 | 1 | 132 | 4 | 217
15908 | 2019-10-01 | 2019-11-26 | 2020-02-29 | 2020-02-29 | COMP | 2020-04-13 | COMP | 2020-10-16 | COMP | 2020-09-24 | COMP | 2020-10-17 | COMP | Rule 16 | 40 | 63 | 31 | 133 | 0 | 1 | 265
16790 | 2019-10-01 | 2020-01-15 | 2020-07-21 | 2020-07-21 | COMP | 2020-07-24 | COMP | 2020-09-04 | COMP | 2020-09-30 | COMP | 2020-11-09 | COMP | Rule 16 | 72 | 132 | 4 | 31 | 18 | 29 | 281
16927 | 2019-10-01 | 2020-01-24 | 2020-10-27 | 2020-12-18 | COMP | 2021-03-11 | COMP | 2021-06-21 | COMP | 2021-07-27 | COMP | 2021-08-06 | COMP | Rule 15/16 | 78 | 195 | 56 | 72 | 26 | 9 | 466
17111 | 2019-10-01 | 2020-01-30 | 2020-04-23 | 2020-04-23 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2022-07-16 | INPR | 2020-07-23 | COMP | Rule 16 | 82 | 60 | 44 | 1 |  |  | 205
17328 | 2019-10-01 | 2020-02-10 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2021-07-20 | COMP | 2021-08-31 | COMP | Rule 16 | 89 | 98 | 11 | 1 | 257 | 31 | 483
18719 | 2019-10-01 | 2020-04-04 | 2020-06-02 | 2020-06-12 | COMP | 2020-06-18 | COMP | 2020-07-09 | COMP | 2020-07-22 | COMP | 2020-08-18 | COMP | Rule 16 | 127 | 41 | 5 | 16 | 10 | 20 | 223
19024 | 2019-10-01 | 2020-04-17 | 2021-03-26 | 2021-04-22 | COMP | 2021-07-15 | COMP | 2021-07-15 | COMP | 2021-07-16 | COMP | 2021-09-09 | COMP | Rule 15/16 | 137 | 237 | 59 | 1 | 2 | 39 | 489
14984 | 2019-10-02 | 2019-10-08 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-06 | COMP | 2019-12-06 | COMP | 2019-11-29 | COMP | 2019-12-20 | COMP | Rule 15/16 | 5 | 33 | 9 | 1 | 0 | 11 | 55
15054 | 2019-10-02 | 2019-10-10 | 2019-11-07 | 2019-11-07 | COMP | 2019-11-19 | COMP | 2019-11-19 | COMP | 2020-01-07 | COMP | 2020-01-14 | COMP | Rule 16 | 7 | 21 | 8 | 1 | 32 | 6 | 70
15061 | 2019-10-02 | 2019-10-10 | 2019-12-14 | 2019-12-14 | COMP | 2020-01-15 | COMP | 2020-01-15 | COMP | 2020-02-18 | COMP | 2020-02-28 | COMP | Rule 16 | 7 | 44 | 21 | 1 | 23 | 9 | 101
15149 | 2019-10-02 | 2019-10-16 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-27 | COMP | 2019-12-27 | COMP | 2021-03-27 | INPR | 2020-03-02 | COMP | Rule 16 | 11 | 40 | 10 | 1 |  |  | 102
15282 | 2019-10-02 | 2019-10-24 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-09 | COMP | 2020-04-09 | COMP | 2020-07-06 | COMP | 2020-09-21 | COMP | Rule 16 | 17 | 107 | 8 | 1 | 62 | 55 | 245
15334 | 2019-10-02 | 2019-10-26 | 2019-11-19 | 2019-11-19 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-11-27 | COMP | 2020-01-02 | COMP | Rule 16 | 18 | 16 | 6 | 1 | 2 | 23 | 62
15400 | 2019-10-02 | 2019-10-30 | 2020-01-11 | 2020-01-11 | COMP | 2020-02-19 | COMP | 2020-04-15 | COMP | 2020-05-05 | COMP | 2020-05-11 | COMP | Rule 16 | 21 | 48 | 26 | 41 | 15 | 5 | 152
15416 | 2019-10-02 | 2019-11-01 | 2020-01-08 | 2020-01-08 | COMP | 2020-02-11 | COMP | 2020-02-11 | INPR | 2022-01-30 | REQD | 2020-07-28 | COMP | Rule 16 | 23 | 44 | 24 |  |  |  | 207
15521 | 2019-10-02 | 2019-11-05 | 2020-10-22 | 2020-10-22 | COMP | 2020-11-17 | COMP | 2021-04-15 | COMP | 2021-06-18 | COMP | 2021-07-30 | COMP | Rule 15/16 | 25 | 244 | 18 | 102 | 46 | 30 | 460
15700 | 2019-10-02 | 2019-11-18 | 2019-12-20 | 2019-12-20 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-02-04 | COMP | 2020-02-18 | COMP | Rule 16 | 33 | 23 | 29 | 1 | 2 | 10 | 93
15725 | 2019-10-02 | 2019-11-19 | 2020-01-13 | 2020-01-13 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-06-09 | COMP | 2020-07-08 | COMP | Rule 16 | 34 | 36 | 21 | 1 | 84 | 22 | 193
15729 | 2019-10-02 | 2019-11-19 | 2020-03-20 | 2020-03-20 | COMP | 2020-07-02 | COMP | 2020-07-20 | COMP | 2022-01-30 | INPR | 2020-12-02 | COMP | Rule 16 | 34 | 83 | 74 | 13 |  |  | 294
15737 | 2019-10-02 | 2019-11-20 | 2020-03-10 | 2020-03-10 | COMP | 2020-12-15 | COMP | 2021-01-27 | COMP | 2021-06-29 | COMP | 2021-08-03 | COMP | Rule 16 | 35 | 74 | 196 | 29 | 108 | 25 | 462
15979 | 2019-10-02 | 2019-12-03 | 2020-03-08 | 2020-03-08 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-05-26 | COMP | 2020-08-11 | COMP | Rule 16 | 42 | 65 | 17 | 1 | 40 | 56 | 217
16073 | 2019-10-02 | 2019-12-08 | 2020-03-11 | 2020-03-11 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-09-09 | COMP | Rule 16 | 45 | 64 | 95 | 1 | 1 | 35 | 237
16088 | 2019-10-02 | 2019-12-09 | 2020-04-06 | 2020-04-06 | COMP | 2020-03-31 | NOTN | 2020-04-06 | COMP | 2020-04-07 | COMP | 2020-08-07 | COMP | Other | 46 | 82 |  | 1 | 2 | 88 | 215
16155 | 2019-10-02 | 2019-12-16 | 2020-10-15 | 2020-10-15 | COMP | 2020-10-30 | COMP | 2020-11-03 | COMP | 2021-06-30 | COMP | 2021-09-07 | COMP | Rule 15/16 | 51 | 213 | 12 | 3 | 164 | 48 | 486
16297 | 2019-10-02 | 2019-12-19 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-10 | COMP | 2020-03-26 | COMP | 2020-09-25 | COMP | 2020-10-22 | COMP | Rule 16 | 54 | 32 | 4 | 33 | 130 | 20 | 268
16475 | 2019-10-02 | 2020-01-03 | 2020-04-03 | 2020-04-03 | COMP | 2021-03-04 | COMP | 2021-03-04 | COMP | 2021-03-23 | COMP | 2021-04-09 | COMP | Rule 16 | 63 | 64 | 231 | 1 | 14 | 14 | 382
16737 | 2019-10-02 | 2020-01-14 | 2020-02-11 | 2020-02-14 | COMP | 2020-02-20 | COMP | 2020-04-01 | COMP | 2020-04-28 | COMP | 2020-05-22 | COMP | Rule 16 | 70 | 20 | 4 | 30 | 20 | 19 | 161
16843 | 2019-10-02 | 2020-01-22 | 2020-04-06 | 2020-06-17 | COMP | 2020-10-07 | COMP | 2021-04-11 | COMP | 2021-05-04 | COMP | 2021-07-02 | COMP | Rule 15/16 | 75 | 53 | 80 | 126 | 17 | 43 | 441
17481 | 2019-10-02 | 2020-02-18 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-29 | COMP | 2020-06-19 | COMP | 2020-07-21 | COMP | 2020-07-25 | COMP | Rule 16 | 93 | 57 | 17 | 16 | 23 | 4 | 205
18249 | 2019-10-02 | 2020-03-17 | 2020-06-28 | 2020-06-28 | COMP | 2020-08-20 | COMP | 2020-09-10 | COMP | 2020-08-20 | COMP | 2020-09-14 | COMP | Rule 16 | 113 | 73 | 39 | 15 | 0 | 3 | 240
18347 | 2019-10-02 | 2020-03-20 | 2020-05-15 | 2020-08-06 | COMP | 2020-09-09 | COMP | 2020-09-10 | COMP | 2020-10-20 | COMP | 2020-11-06 | COMP | Rule 16 | 116 | 41 | 24 | 2 | 29 | 14 | 279
18751 | 2019-10-02 | 2020-04-06 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-06 | COMP | 2020-09-17 | COMP | 2020-09-22 | COMP | 2020-10-22 | COMP | Rule 16 | 127 | 62 | 4 | 53 | 4 | 23 | 268
21576 | 2019-10-02 | 2020-08-13 | 2020-09-09 | 2020-09-09 | COMP | 2020-08-31 | NOTN | 2020-10-06 | COMP | 2020-10-20 | COMP | 2020-11-16 | COMP | Other | 219 | 19 |  | 20 | 11 | 19 | 284
41116 | 2019-10-02 | 2023-02-24 | 2023-05-23 | 2023-05-23 | COMP | 2023-05-23 | NOTN | 2023-07-11 | COMP | 2023-12-11 | COMP | 2023-10-19 | COMP | Other | 853 | 63 |  | 33 | 106 |  | 1018
14909 | 2019-10-03 | 2019-10-03 | 2019-10-05 | 2019-10-05 | COMP | 2019-10-29 | COMP | 2019-10-09 | COMP | 2020-03-01 | INPR | 2019-11-01 | COMP | Rule 16 | 1 | 2 | 17 |  |  |  | 22
15275 | 2019-10-03 | 2019-10-24 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-12 | COMP | 2020-07-06 | COMP | 2020-09-03 | COMP | 2020-11-20 | COMP | Rule 16 | 16 | 126 | 12 | 39 | 44 | 55 | 287
15348 | 2019-10-03 | 2019-10-28 | 2019-12-14 | 2019-12-14 | COMP | 2020-01-16 | COMP | 2020-01-17 | COMP | 2020-01-31 | COMP | 2020-02-05 | COMP | Rule 16 | 18 | 32 | 22 | 2 | 10 | 4 | 84
15358 | 2019-10-03 | 2019-10-29 | 2019-12-30 | 2019-12-30 | COMP | 2020-05-27 | COMP | 2020-08-12 | COMP | 2020-08-20 | COMP | 2020-09-18 | COMP | Rule 16 | 19 | 41 | 104 | 56 | 7 | 21 | 243
15425 | 2019-10-03 | 2019-10-31 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-21 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-03-31 | COMP | Rule 16 | 21 | 29 | 25 | 27 | 1 | 24 | 122
15551 | 2019-10-03 | 2019-11-06 | 2020-03-26 | 2020-03-26 | COMP | 2020-06-25 | COMP | 2020-06-25 | COMP | 2021-11-05 | COMP | 2021-12-08 | COMP | Rule 16 | 25 | 95 | 65 | 1 | 346 | 21 | 548
15749 | 2019-10-03 | 2019-11-19 | 2020-03-24 | 2020-03-24 | COMP | 2020-04-13 | COMP | 2020-05-18 | COMP |  | INPR | 2021-01-04 | COMP | Rule 15/16 | 33 | 85 | 15 | 26 |  |  | 314
15750 | 2019-10-03 | 2019-11-19 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-10 | COMP | 2020-08-25 | COMP | 2022-07-16 | INPR | 2021-01-04 | COMP | Rule 16 | 33 | 81 | 18 | 97 |  |  | 314
15791 | 2019-10-03 | 2019-11-20 | 2020-03-24 | 2022-03-03 | COMP | 2022-03-08 | COMP | 2020-10-08 | COMP | 2022-07-29 | COMP | 2023-04-12 | COMP | Rule 16 | 34 | 84 | 4 |  | 454 | 176 | 885
15820 | 2019-10-03 | 2019-11-23 | 2020-03-16 | 2020-03-16 | COMP | 2020-05-04 | COMP | 2020-06-30 | COMP | 2020-05-29 | COMP | 2020-08-07 | COMP | Rule 16 | 36 | 75 | 36 | 41 | 0 | 29 | 214
15832 | 2019-10-03 | 2019-11-22 | 2020-02-10 | 2020-02-10 | COMP | 2020-02-14 | COMP | 2020-04-14 | COMP | 2020-02-18 | COMP | 2020-07-29 | COMP | Rule 16 | 36 | 52 | 5 | 42 | 0 | 76 | 207
16132 | 2019-10-03 | 2019-12-10 | 2020-05-05 | 2020-05-05 | COMP | 2020-09-30 | COMP | 2020-09-30 | COMP |  | INPR | 2021-06-23 | COMP | Rule 15/16 | 46 | 102 | 105 | 1 |  |  | 433
16373 | 2019-10-03 | 2019-12-23 | 2020-05-13 | 2020-05-13 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2021-01-19 | COMP | 2021-02-10 | COMP | Rule 16 | 55 | 99 | 49 | 1 | 124 | 17 | 340
16731 | 2019-10-03 | 2020-01-13 | 2020-04-11 | 2021-06-02 | COMP | 2021-07-14 | COMP | 2021-07-14 | COMP | 2021-09-07 | COMP | 2021-11-11 | COMP | Rule 16 | 68 | 63 | 30 | 1 | 39 | 47 | 531
16873 | 2019-10-03 | 2020-01-21 | 2020-05-04 | 2020-05-04 | COMP | 2020-10-09 | COMP | 2021-05-17 | COMP | 2021-07-13 | COMP | 2021-07-24 | COMP | Rule 16 | 73 | 74 | 113 | 150 | 40 | 9 | 454
16920 | 2019-10-03 | 2020-01-23 | 2020-02-18 | 2020-02-18 | COMP | 2020-03-20 | COMP | 2020-07-07 | COMP | 2020-03-23 | COMP | 2020-09-24 | COMP | Rule 15/16 | 75 | 18 | 24 | 77 | 0 | 57 | 247
16998 | 2019-10-03 | 2020-01-27 | 2020-04-20 | 2020-12-15 | COMP | 2020-12-31 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2021-01-10 | COMP | Rule 15/16 | 77 | 60 | 12 |  | 1 | 83 | 318
18623 | 2019-10-03 | 2020-03-31 | 2020-05-07 | 2020-05-07 | COMP | 2020-09-16 | COMP | 2020-10-10 | COMP | 2022-11-30 | COMP | 2020-12-13 | COMP | Rule 16 | 122 | 28 | 93 | 18 | 536 |  | 300
19036 | 2019-10-03 | 2020-04-17 | 2020-06-13 | 2020-06-13 | COMP | 2020-07-08 | COMP | 2020-07-28 | COMP | 2021-05-03 | COMP | 2021-09-02 | COMP | Rule 16 | 135 | 40 | 18 | 15 | 192 | 87 | 483
21248 | 2019-10-03 | 2020-07-29 | 2020-11-10 | 2020-11-10 | COMP | 2021-04-07 | COMP | 2021-04-10 | COMP | 2021-05-10 | COMP | 2021-05-21 | COMP | Rule 16 | 207 | 74 | 100 | 3 | 21 | 10 | 411
14903 | 2019-10-04 | 2019-10-04 | 2020-01-27 | 2020-01-27 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2022-01-19 | COMP | 2022-02-03 | COMP | Rule 16 | 1 | 76 | 115 | 1 | 387 | 12 | 587
15135 | 2019-10-04 | 2019-10-15 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-04 | COMP | 2019-12-04 | COMP | 2020-01-06 | COMP | 2020-02-21 | COMP | Rule 16 | 8 | 23 | 12 | 1 | 22 | 33 | 94
15417 | 2019-10-04 | 2019-11-01 | 2020-08-07 | 2020-08-07 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2022-01-05 | COMP | 2021-07-29 | COMP | Rule 16 | 21 | 193 | 85 | 1 | 271 |  | 457
15614 | 2019-10-04 | 2019-11-12 | 2020-03-18 | 2020-03-18 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2020-10-12 | COMP | 2020-11-19 | COMP | Rule 15/16 | 27 | 86 | 63 | 1 | 85 | 28 | 285
15808 | 2019-10-04 | 2019-11-20 | 2020-03-30 | 2020-03-30 | COMP | 2020-09-24 | COMP | 2020-10-01 | COMP | 2023-02-14 | COMP | 2023-04-20 | COMP | Rule 16 | 33 | 88 | 127 | 6 | 594 | 47 | 890
16054 | 2019-10-04 | 2019-12-07 | 2020-04-28 | 2020-04-28 | COMP | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-10-22 | COMP | 2020-12-06 | COMP | Rule 16 | 43 | 98 | 5 | 6 | 117 | 29 | 294
16062 | 2019-10-04 | 2019-12-07 | 2020-04-10 | 2020-04-10 | COMP | 2020-12-30 | COMP | 2020-12-30 | COMP | 2021-02-09 | COMP | 2021-02-12 | COMP | Rule 16 | 43 | 86 | 183 | 1 | 28 | 4 | 341
16713 | 2019-10-04 | 2020-01-14 | 2020-02-10 | 2020-02-10 | COMP | 2020-02-25 | COMP | 2020-03-12 | COMP | 2020-03-11 | COMP | 2020-05-13 | COMP | Rule 15/16 | 68 | 19 | 11 | 13 | 0 | 45 | 152
16837 | 2019-10-04 | 2020-01-18 | 2020-07-13 | 2020-07-13 | COMP | 2021-05-10 | COMP | 2021-06-14 | COMP | 2023-12-06 | COMP | 2023-05-19 | COMP | Rule 15/16 | 71 | 123 | 208 | 25 | 623 |  | 911
17055 | 2019-10-04 | 2020-01-29 | 2020-09-18 | 2020-09-18 | COMP | 2020-10-09 | COMP | 2021-03-01 | COMP | 2021-01-21 | COMP | 2021-03-25 | COMP | Rule 15/16 | 78 | 165 | 16 | 95 | 0 | 19 | 369
17420 | 2019-10-04 | 2020-02-12 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-07-27 | COMP | 2020-09-03 | COMP | Rule 16 | 88 | 60 | 20 | 1 | 39 | 29 | 232
17607 | 2019-10-04 | 2020-02-21 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-09 | COMP | 2020-06-17 | COMP | 2020-08-03 | COMP | 2020-08-27 | COMP | Rule 16 | 94 | 73 | 5 | 7 | 34 | 19 | 227
17930 | 2019-10-04 | 2020-03-04 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-04 | COMP | 2020-06-22 | COMP | 2020-06-15 | COMP | 2020-07-15 | COMP | Rule 16 | 102 | 37 | 8 | 35 | 0 | 18 | 196
18004 | 2019-10-04 | 2020-03-06 | 2020-10-22 | 2020-11-25 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2021-03-25 | COMP | 2021-04-26 | COMP | Rule 16 | 104 | 163 | 28 | 1 | 54 | 23 | 391
18189 | 2019-10-04 | 2020-03-13 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2021-03-02 | COMP | 2021-03-29 | COMP | Rule 16 | 109 | 82 | 19 | 1 | 145 | 20 | 371
18264 | 2019-10-04 | 2020-03-17 | 2020-06-03 | 2020-06-03 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2021-03-01 | COMP | 2021-03-12 | COMP | Rule 16 | 111 | 56 | 54 | 1 | 133 | 10 | 360
18360 | 2019-10-04 | 2020-03-21 | 2021-01-26 | 2022-08-15 | COMP | 2022-12-21 | COMP | 2022-12-21 | COMP |  | INPR | 2023-03-03 | COMP | Rule 16 | 114 | 214 | 89 | 1 |  |  | 856
18396 | 2019-10-04 | 2020-03-23 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-31 | COMP | 2020-08-12 | COMP | 2020-08-03 | COMP | 2020-09-23 | COMP | Rule 16 | 115 | 65 | 30 | 9 | 0 | 30 | 245
18398 | 2019-10-04 | 2020-03-23 | 2020-05-18 | 2020-05-18 | COMP | 2020-07-31 | COMP | 2020-08-14 | COMP | 2020-08-03 | COMP | 2020-09-27 | COMP | Rule 16 | 115 | 41 | 54 | 11 | 0 | 30 | 247
19055 | 2019-10-04 | 2020-04-20 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-03 | COMP | 2020-09-28 | COMP | 2021-01-25 | COMP | 2021-02-17 | COMP | Rule 16 | 135 | 60 | 16 | 40 | 80 | 17 | 343
19749 | 2019-10-04 | 2020-05-20 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-07-03 | COMP | 2020-08-04 | COMP | Rule 16 | 157 | 27 | 4 | 1 | 2 | 23 | 210
19904 | 2019-10-04 | 2020-05-28 | 2020-10-09 | 2020-10-09 | COMP | 2020-10-19 | COMP | 2020-12-14 | COMP | 2021-01-25 | COMP | 2021-02-08 | COMP | Rule 16 | 162 | 96 | 7 | 38 | 28 | 11 | 337
14976 | 2019-10-05 | 2019-10-07 | 2019-11-03 | 2020-06-11 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-10-05 | COMP | Rule 16 | 1 | 20 | 48 | 1 | 1 | 35 | 252
15277 | 2019-10-05 | 2019-10-25 | 2020-05-08 | 2020-05-08 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2021-01-11 | COMP | 2021-02-17 | COMP | Rule 16 | 15 | 134 | 125 | 1 | 46 | 26 | 342
15709 | 2019-10-05 | 2019-11-18 | 2020-04-17 | 2020-04-17 | COMP | 2020-04-17 | NOTN | 2020-06-07 | COMP | 2020-04-14 | COMP | 2021-01-12 | COMP | Other | 30 | 104 |  | 35 | 0 | 151 | 318
15142 | 2019-10-06 | 2019-10-15 | 2019-12-28 | 2019-12-28 | COMP | 2020-02-06 | COMP | 2020-02-26 | COMP | 2020-03-07 | COMP | 2020-06-01 | COMP | Rule 16 | 7 | 50 | 27 | 14 | 8 | 60 | 163
15225 | 2019-10-06 | 2019-10-21 | 2020-04-28 | 2020-04-28 | COMP | 2020-04-29 | NOTN | 2020-08-05 | COMP | 2020-09-01 | NOTN | 2020-10-28 | COMP | Other | 11 | 130 |  | 71 |  |  | 269
16412 | 2019-10-06 | 2019-12-27 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-27 | COMP | 2020-04-06 | COMP | 2021-07-12 | COMP | 2021-07-21 | COMP | Rule 16 | 56 | 37 | 27 | 7 | 320 | 8 | 450
15081 | 2019-10-07 | 2019-10-10 | 2019-11-13 | 2019-11-13 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-11-18 | COMP | 2019-12-16 | COMP | Rule 16 | 4 | 24 | 4 | 1 | 1 | 19 | 48
15162 | 2019-10-07 | 2019-10-16 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-03-04 | COMP | Rule 16 | 8 | 75 | 8 | 1 | 1 | 13 | 101
15244 | 2019-10-07 | 2019-10-22 | 2020-03-13 | 2020-12-24 | COMP | 2021-02-04 | COMP | 2021-03-02 | COMP | 2022-04-16 | INPR | 2021-03-26 | COMP | Rule 16 | 12 | 97 | 28 | 18 |  |  | 369
15302 | 2019-10-07 | 2019-10-25 | 2019-12-04 | 2019-12-16 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2020-06-02 | COMP | 2020-07-07 | COMP | Rule 16 | 15 | 26 | 12 | 1 | 106 | 26 | 189
15443 | 2019-10-07 | 2019-11-01 | 2020-04-02 | 2020-04-02 | COMP | 2020-05-04 | COMP | 2020-05-13 | COMP | 2020-05-18 | COMP | 2020-07-08 | COMP | Rule 16 | 20 | 103 | 23 | 8 | 4 | 37 | 190
15537 | 2019-10-07 | 2019-11-06 | 2020-03-09 | 2021-05-28 | COMP | 2021-06-25 | COMP | 2021-06-25 | COMP | 2023-02-13 | COMP | 2023-04-13 | COMP | Rule 15/16 | 23 | 82 | 20 | 1 | 410 | 43 | 884
15682 | 2019-10-07 | 2019-11-15 | 2020-01-15 | 2020-01-15 | COMP | 2020-02-25 | COMP | 2020-03-10 | COMP | 2020-02-12 | COMP | 2020-06-24 | COMP | Rule 16 | 29 | 40 | 28 | 11 | 0 | 76 | 180
15825 | 2019-10-07 | 2019-11-22 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-04-13 | COMP | 2020-05-06 | COMP | Rule 16 | 34 | 39 | 24 | 1 | 35 | 18 | 146
15887 | 2019-10-07 | 2019-11-25 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-22 | COMP | 2020-02-24 | COMP | 2020-04-02 | COMP | 2020-06-03 | COMP | Rule 16 | 35 | 30 | 9 | 23 | 29 | 44 | 165
16074 | 2019-10-07 | 2019-12-08 | 2020-02-28 | 2020-04-01 | COMP | 2020-04-07 | COMP | 2020-05-05 | COMP | 2020-08-18 | COMP | 2020-09-14 | COMP | Rule 16 | 42 | 56 | 5 | 21 | 75 | 19 | 237
16287 | 2019-10-07 | 2019-12-19 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-27 | COMP | 2020-07-16 | COMP | 2020-06-01 | COMP | 2020-07-29 | COMP | Rule 15/16 | 51 | 98 | 13 | 37 | 0 | 10 | 205
16292 | 2019-10-07 | 2019-12-19 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-13 | COMP | 2020-06-09 | COMP | 2020-08-13 | COMP | 2020-08-25 | COMP | Rule 16 | 51 | 73 | 7 | 41 | 48 | 9 | 224
16356 | 2019-10-07 | 2019-12-24 | 2020-02-11 | 2020-02-11 | COMP | 2020-03-02 | COMP | 2020-03-09 | COMP | 2020-06-15 | COMP | 2020-07-17 | COMP | Rule 16 | 54 | 33 | 14 | 6 | 70 | 25 | 197
16480 | 2019-10-07 | 2020-01-03 | 2020-02-24 | 2020-02-24 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-06-15 | COMP | 2020-06-22 | COMP | Rule 16 | 60 | 35 | 41 | 1 | 40 | 6 | 178
16825 | 2019-10-07 | 2020-01-17 | 2020-05-19 | 2020-05-19 | COMP | 2020-09-24 | COMP | 2020-09-24 | COMP | 2021-10-12 | COMP | 2022-02-07 | COMP | Rule 16 | 70 | 86 | 91 | 1 | 264 | 81 | 588
17213 | 2019-10-07 | 2020-02-04 | 2020-09-21 | 2020-09-21 | COMP | 2020-12-03 | COMP | 2021-06-18 | COMP | 2021-06-08 | COMP | 2021-09-13 | COMP | Rule 16 | 81 | 162 | 51 | 137 | 0 | 60 | 487
17225 | 2019-10-07 | 2020-02-05 | 2020-03-20 | 2020-03-20 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-13 | COMP | 2020-05-04 | COMP | Rule 16 | 82 | 32 | 8 | 1 | 10 | 16 | 144
17406 | 2019-10-07 | 2020-02-12 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-19 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-06-24 | COMP | Rule 16 | 87 | 13 | 14 | 66 | 1 | 4 | 180
17474 | 2019-10-07 | 2020-02-15 | 2020-05-15 | 2020-05-15 | COMP | 2021-04-22 | COMP | 2021-04-22 | COMP | 2023-07-12 | COMP | 2023-09-01 | COMP | Rule 16 | 89 | 64 | 236 | 1 | 558 | 38 | 982
18150 | 2019-10-07 | 2020-03-12 | 2020-07-28 | 2020-11-23 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2020-08-28 | COMP | 2021-01-23 | COMP | Rule 16 | 107 | 98 | 3 | 1 | 0 | 38 | 325
18960 | 2019-10-07 | 2020-04-14 | 2020-06-04 | 2020-06-04 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP |  | INPR | 2020-09-30 | COMP | Rule 16 | 130 | 37 | 3 | 1 |  |  | 249
19237 | 2019-10-07 | 2020-04-27 | 2020-06-26 | 2020-11-01 | COMP | 2020-11-16 | COMP | 2020-11-23 | COMP | 2020-11-16 | COMP | 2021-02-19 | COMP | Rule 16 | 139 | 44 | 10 | 6 | 0 | 59 | 344
21326 | 2019-10-07 | 2020-07-31 | 2020-10-02 | 2020-11-19 | COMP | 2020-12-04 | COMP | 2020-12-04 | COMP | 2020-12-11 | COMP | 2021-01-12 | COMP | Rule 15/16 | 207 | 45 | 10 | 1 | 6 | 21 | 318
15133 | 2019-10-08 | 2019-10-15 | 2019-12-19 | 2019-12-19 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-02-18 | COMP | 2020-03-05 | COMP | Rule 16 | 6 | 45 | 25 | 1 | 16 | 13 | 101
15193 | 2019-10-08 | 2019-10-18 | 2019-12-22 | 2019-12-23 | COMP | 2020-01-16 | COMP | 2020-01-16 | COMP | 2020-03-11 | COMP | 2020-03-20 | COMP | Rule 16 | 9 | 43 | 17 | 1 | 38 | 8 | 112
15426 | 2019-10-08 | 2019-10-31 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-02-14 | COMP | Rule 16 | 18 | 29 | 16 | 1 | 1 | 28 | 88
15586 | 2019-10-08 | 2019-11-07 | 2020-03-24 | 2020-03-24 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-05-01 | COMP | 2020-06-11 | COMP | Rule 15/16 | 23 | 92 | 31 | 1 | 0 | 27 | 170
15628 | 2019-10-08 | 2019-11-12 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-03 | NOTN | 2019-12-31 | COMP | 2020-02-03 | COMP | 2020-02-04 | COMP | Other | 25 | 13 |  | 21 | 23 | 2 | 80
15736 | 2019-10-08 | 2019-11-19 | 2019-12-14 | 2019-12-14 | COMP | 2020-03-25 | COMP | 2020-04-23 | COMP | 2020-04-02 | COMP | 2020-05-21 | COMP | Rule 16 | 30 | 17 | 69 | 22 | 0 | 21 | 156
16465 | 2019-10-08 | 2020-01-03 | 2020-02-07 | 2020-02-07 | COMP | 2020-02-07 | NOTN | 2020-03-27 | COMP | 2020-03-17 | COMP | 2020-05-15 | COMP | Other | 59 | 25 |  | 35 | 0 | 36 | 152
16747 | 2019-10-08 | 2020-01-14 | 2020-04-01 | 2020-04-01 | COMP | 2021-03-22 | COMP | 2021-04-22 | COMP | 2021-04-16 | COMP | 2021-05-15 | COMP | Rule 16 | 66 | 55 | 245 | 24 | 0 | 17 | 403
16848 | 2019-10-08 | 2020-01-22 | 2020-04-23 | 2020-04-23 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-08-11 | COMP | Rule 15/16 | 71 | 66 | 46 | 1 | 1 | 33 | 213
17396 | 2019-10-08 | 2020-02-12 | 2020-05-19 | 2020-05-19 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2022-01-30 | INPR | 2020-09-09 | COMP | Rule 16 | 86 | 69 | 37 | 1 |  |  | 233
19822 | 2019-10-08 | 2020-05-23 | 2021-01-28 | 2021-01-28 | COMP | 2021-02-22 | COMP | 2021-05-27 | COMP | 2021-07-30 | COMP | 2021-11-30 | COMP | Rule 16 | 157 | 171 | 17 | 69 | 45 | 84 | 539
15009 | 2019-10-09 | 2019-10-09 | 2019-10-16 | 2019-10-16 | COMP | 2019-10-29 | COMP | 2019-12-24 | COMP | 2020-01-06 | COMP | 2020-01-08 | COMP | Rule 16 | 1 | 6 | 10 | 38 | 8 | 3 | 61
15026 | 2019-10-09 | 2019-10-09 | 2020-05-19 | 2020-05-19 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-10-07 | COMP | 2020-11-10 | COMP | Rule 16 | 1 | 153 | 89 | 1 | 12 | 25 | 276
15027 | 2019-10-09 | 2019-10-09 | 2020-05-19 | 2020-05-19 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-10-07 | COMP | 2020-11-09 | COMP | Rule 16 | 1 | 153 | 89 | 1 | 12 | 24 | 275
15144 | 2019-10-09 | 2019-10-16 | 2020-02-11 | 2020-04-16 | COMP | 2020-06-29 | COMP | 2020-09-28 | COMP | 2020-08-21 | COMP | 2020-10-04 | COMP | Rule 15/16 | 6 | 79 | 52 | 65 | 0 | 5 | 249
15221 | 2019-10-09 | 2019-10-21 | 2020-02-07 | 2020-02-07 | COMP | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-09-30 | COMP | 2021-09-09 | COMP | Rule 15/16 | 9 | 74 | 134 | 1 | 33 | 237 | 483
15259 | 2019-10-09 | 2019-10-23 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-18 | COMP | 2020-02-24 | COMP | 2020-04-20 | COMP | 2020-05-15 | COMP | Rule 16 | 11 | 50 | 29 | 5 | 41 | 20 | 151
15498 | 2019-10-09 | 2019-11-05 | 2020-03-23 | 2020-03-23 | COMP | 2020-05-11 | COMP | 2020-05-20 | COMP | 2020-05-26 | COMP | 2020-06-27 | COMP | Rule 16 | 20 | 93 | 36 | 8 | 4 | 24 | 180
15822 | 2019-10-09 | 2019-11-21 | 2020-03-25 | 2020-03-25 | COMP | 2020-05-21 | COMP | 2020-09-21 | COMP | 2020-07-31 | COMP | 2020-10-30 | COMP | Rule 16 | 31 | 84 | 42 | 86 | 0 | 30 | 269
15913 | 2019-10-09 | 2019-11-27 | 2020-01-02 | 2020-01-02 | COMP | 2020-01-08 | COMP | 2020-01-13 | COMP | 2020-01-21 | COMP | 2020-02-07 | COMP | Rule 16 | 35 | 23 | 5 | 4 | 6 | 14 | 82
18597 | 2019-10-09 | 2020-03-30 | 2020-04-17 | 2022-03-24 | COMP | 2020-04-30 | NOTN | 2022-05-24 | COMP | 2020-06-23 | COMP | 2023-06-28 | COMP | Other | 117 | 15 |  | 44 | 0 | 274 | 934
19383 | 2019-10-09 | 2020-05-04 | 2020-08-10 | 2020-08-10 | COMP | 2020-10-13 | COMP | 2021-08-13 | COMP | 2021-08-13 | COMP | 2021-08-24 | COMP | Rule 16 | 142 | 70 | 46 | 210 | 1 | 8 | 472
19646 | 2019-10-09 | 2020-05-15 | 2020-09-21 | 2020-10-23 | COMP | 2020-11-23 | COMP | 2021-02-19 | COMP | 2021-03-09 | COMP | 2021-03-23 | COMP | Rule 15/16 | 151 | 90 | 21 | 59 | 13 | 11 | 364
15436 | 2019-10-10 | 2019-10-31 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-10 | COMP | 2020-05-21 | COMP | 2020-05-12 | COMP | 2020-06-03 | COMP | Rule 16 | 16 | 82 | 6 | 53 | 0 | 9 | 162
15679 | 2019-10-10 | 2019-11-14 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-30 | COMP | 2020-07-20 | COMP | Rule 16 | 25 | 107 | 20 | 1 | 10 | 36 | 195
15852 | 2019-10-10 | 2019-11-26 | 2020-03-01 | 2020-06-13 | COMP | 2020-06-30 | COMP | 2020-04-29 | COMP | 2020-07-10 | COMP | 2020-08-04 | COMP | Rule 16 | 33 | 63 | 12 |  | 52 | 18 | 206
15961 | 2019-10-10 | 2019-12-03 | 2020-02-20 | 2020-02-20 | COMP | 2020-08-28 | COMP | 2020-08-31 | COMP | 2020-09-22 | COMP | 2020-10-08 | COMP | Rule 15/16 | 36 | 54 | 136 | 2 | 16 | 13 | 252
15970 | 2019-10-10 | 2019-12-03 | 2020-01-11 | 2020-01-11 | COMP | 2020-01-17 | COMP | 2020-03-18 | COMP | 2020-02-05 | COMP | 2020-05-03 | COMP | Rule 16 | 36 | 27 | 5 | 42 | 0 | 33 | 140
15973 | 2019-10-10 | 2019-12-04 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2020-02-06 | COMP | 2020-03-09 | COMP | Rule 16 | 37 | 25 | 16 | 1 | 5 | 22 | 101
16047 | 2019-10-10 | 2019-12-06 | 2020-03-26 | 2020-03-27 | COMP | 2020-05-14 | COMP | 2020-07-30 | COMP | 2020-07-29 | COMP | 2020-09-21 | COMP | Rule 16 | 39 | 76 | 35 | 55 | 0 | 37 | 239
16105 | 2019-10-10 | 2019-12-10 | 2020-02-06 | 2020-02-06 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2021-03-22 | COMP | 2021-03-29 | COMP | Rule 16 | 41 | 40 | 140 | 1 | 144 | 6 | 367
16164 | 2019-10-10 | 2019-12-12 | 2020-03-20 | 2020-03-28 | COMP | 2020-04-30 | COMP | 2020-06-26 | COMP | 2020-06-30 | COMP | 2020-07-21 | COMP | Rule 15/16 | 43 | 68 | 24 | 41 | 3 | 16 | 196
16209 | 2019-10-10 | 2019-12-16 | 2020-03-04 | 2020-03-04 | COMP | 2020-07-13 | COMP | 2020-08-10 | COMP | 2020-09-22 | COMP | 2020-12-22 | COMP | Rule 15/16 | 45 | 54 | 93 | 21 | 31 | 63 | 302
16293 | 2019-10-10 | 2019-12-19 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-05 | COMP | 2020-03-25 | COMP | 2022-07-30 | INPR | 2020-05-14 | COMP | Rule 16 | 48 | 50 | 3 | 15 |  |  | 149
16540 | 2019-10-10 | 2020-01-09 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-12 | COMP | 2020-07-07 | COMP | 2020-07-10 | COMP | 2020-08-26 | COMP | Rule 15/16 | 61 | 74 | 14 | 40 | 4 | 34 | 222
16554 | 2019-10-10 | 2020-01-07 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-12 | COMP | 2020-03-13 | COMP | 2020-03-12 | COMP | 2020-06-03 | COMP | Rule 16 | 59 | 43 | 4 | 2 | 0 | 58 | 162
17212 | 2019-10-10 | 2020-02-05 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-06 | COMP | 2020-11-04 | COMP | 2020-12-29 | COMP | 2021-02-02 | COMP | Rule 15/16 | 79 | 91 | 17 | 87 | 36 | 24 | 329
18050 | 2019-10-10 | 2020-03-10 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-05-27 | COMP | 2020-11-09 | COMP | Rule 16 | 102 | 25 | 11 | 1 | 22 | 118 | 274
18397 | 2019-10-10 | 2020-03-23 | 2020-05-17 | 2020-05-17 | COMP | 2020-05-26 | COMP | 2020-06-29 | COMP | 2020-07-10 | COMP | 2020-08-10 | COMP | Rule 15/16 | 111 | 40 | 6 | 25 | 10 | 22 | 210
18564 | 2019-10-10 | 2020-03-30 | 2020-09-22 | 2020-09-22 | COMP |  | INPR | 2021-02-18 | COMP | 2020-11-10 | COMP | 2021-04-17 | COMP | Rule 15/16 | 116 | 125 |  | 101 | 0 | 42 | 381
18894 | 2019-10-10 | 2020-04-10 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-06-15 | COMP | 2020-08-06 | COMP | Rule 16 | 125 | 35 | 15 | 1 | 0 | 36 | 208
18944 | 2019-10-10 | 2020-04-13 | 2020-05-31 | 2021-01-28 | COMP | 2021-03-29 | COMP | 2021-03-29 | COMP | 2021-04-21 | COMP | 2021-04-22 | COMP | Rule 16 | 126 | 34 | 42 | 1 | 18 | 2 | 385
18979 | 2019-10-10 | 2020-04-16 | 2020-07-16 | 2020-07-16 | COMP | 2020-11-04 | COMP | 2021-01-26 | COMP | 2021-01-25 | COMP | 2021-02-26 | COMP | Rule 16 | 129 | 65 | 79 | 54 | 0 | 23 | 346
22290 | 2019-10-10 | 2020-09-17 | 2020-10-16 | 2020-10-16 | COMP | 2020-12-03 | COMP | 2021-04-21 | COMP | 2022-03-15 | COMP | 2022-07-14 | COMP | Rule 15/16 | 237 | 22 | 32 | 96 | 227 | 85 | 694
23295 | 2019-10-10 | 2020-10-30 | 2021-01-23 | 2021-01-23 | COMP | 2021-03-05 | COMP | 2021-03-05 | COMP | 2021-04-13 | COMP | 2021-04-29 | COMP | Rule 15/16 | 268 | 55 | 29 | 1 | 28 | 13 | 390
15150 | 2019-10-11 | 2019-10-16 | 2019-12-10 | 2020-01-30 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2023-04-30 | INPR | 2020-05-20 | COMP | Rule 16 | 4 | 37 | 3 | 1 |  |  | 152
15175 | 2019-10-11 | 2019-10-17 | 2020-03-19 | 2020-03-19 | COMP | 2020-03-19 | NOTN | 2020-05-11 | COMP | 2019-12-24 | COMP | 2020-10-16 | COMP | Other | 5 | 104 |  | 38 | 0 | 113 | 257
15270 | 2019-10-11 | 2019-10-23 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | 2020-05-11 | COMP | Rule 16 | 9 | 79 | 30 | 1 | 2 | 29 | 145
15346 | 2019-10-11 | 2019-10-29 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-09 | COMP | 2020-06-18 | COMP | 2020-07-06 | COMP | 2020-07-28 | COMP | Rule 16 | 13 | 134 | 20 | 8 | 13 | 17 | 200
15360 | 2019-10-11 | 2019-10-29 | 2020-03-06 | 2020-03-06 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-09-01 | COMP | 2020-09-21 | COMP | Rule 16 | 13 | 87 | 23 | 1 | 105 | 14 | 238
15379 | 2019-10-11 | 2019-10-29 | 2020-02-28 | 2020-02-28 | COMP | 2020-11-18 | COMP | 2020-11-18 | COMP | 2020-11-18 | COMP | 2020-12-17 | COMP | Rule 16 | 13 | 82 | 186 | 1 | 1 | 20 | 298
15423 | 2019-10-11 | 2019-10-31 | 2019-12-09 | 2019-12-09 | COMP | 2020-01-03 | COMP | 2020-01-10 | COMP | 2020-01-17 | COMP | 2020-02-19 | COMP | Rule 15/16 | 15 | 25 | 18 | 6 | 6 | 22 | 87
15539 | 2019-10-11 | 2019-11-06 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-07 | COMP | 2020-04-01 | COMP | 2020-04-02 | COMP | 2020-06-04 | COMP | Rule 16 | 19 | 57 | 5 | 38 | 2 | 45 | 162
15755 | 2019-10-11 | 2019-11-20 | 2020-01-31 | 2020-02-13 | COMP | 2020-02-24 | COMP | 2020-02-12 | COMP | 2020-02-04 | COMP | 2020-07-10 | COMP | Rule 16 | 28 | 48 | 7 |  | 0 | 106 | 188
15939 | 2019-10-11 | 2019-12-02 | 2020-07-02 | 2020-07-02 | COMP | 2020-06-08 | NOTN | 2020-09-14 | COMP | 2022-02-08 | COMP | 2022-05-26 | COMP | Other | 34 | 149 |  | 52 | 353 | 77 | 661
16118 | 2019-10-11 | 2019-12-10 | 2020-04-08 | 2020-04-08 | COMP | 2020-06-10 | COMP | 2020-05-29 | COMP | 2020-06-15 | COMP | 2020-07-24 | COMP | Rule 16 | 40 | 83 | 45 |  | 12 | 30 | 198
16502 | 2019-10-11 | 2020-01-07 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-17 | COMP | 2020-04-30 | COMP | 2020-05-04 | COMP | 2020-09-17 | COMP | Rule 16 | 58 | 38 | 12 | 33 | 3 | 97 | 236
16628 | 2019-10-11 | 2020-01-09 | 2020-02-24 | 2020-03-31 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-05-11 | COMP | 2020-06-08 | COMP | Rule 16 | 60 | 31 | 26 | 1 | 5 | 20 | 164
16854 | 2019-10-11 | 2020-01-21 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-31 | COMP | 2020-04-21 | COMP | 2020-05-05 | COMP | 2020-06-17 | COMP | Rule 16 | 67 | 39 | 12 | 16 | 11 | 31 | 171
16964 | 2019-10-11 | 2020-01-27 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-06-29 | COMP | 2020-08-17 | COMP | Rule 16 | 71 | 50 | 18 | 1 | 43 | 36 | 214
17540 | 2019-10-11 | 2020-02-19 | 2020-05-19 | 2021-01-13 | COMP | 2022-01-26 | COMP | 2022-01-26 | COMP | 2022-10-18 | COMP | 2023-01-20 | COMP | Rule 15/16 | 87 | 65 | 262 | 1 | 185 | 63 | 822
17765 | 2019-10-11 | 2020-02-26 | 2020-06-03 | 2020-06-03 | COMP | 2020-09-04 | COMP | 2020-10-13 | COMP | 2020-10-09 | COMP | 2020-11-05 | COMP | Other | 92 | 70 | 68 | 27 | 0 | 18 | 271
17883 | 2019-10-11 | 2020-03-02 | 2020-03-12 | 2020-03-12 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-03-24 | COMP | 2020-04-15 | COMP | Rule 16 | 95 | 9 | 7 | 1 | 3 | 17 | 127
18105 | 2019-10-11 | 2020-03-11 | 2020-07-28 | 2021-09-27 | COMP | 2021-09-29 | COMP | 2021-10-08 | COMP | 2021-06-21 | COMP | 2021-10-15 | COMP | Rule 16 | 102 | 99 | 3 | 8 | 0 | 6 | 507
18508 | 2019-10-11 | 2020-03-27 | 2020-11-10 | 2020-11-10 | COMP | 2021-01-13 | COMP | 2021-01-13 | COMP | 2021-04-05 | COMP | 2021-05-18 | COMP | Rule 16 | 114 | 161 | 42 | 1 | 57 | 32 | 402
18521 | 2019-10-11 | 2020-03-27 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-09 | COMP | 2020-09-08 | COMP | 2020-09-09 | COMP | 2020-10-13 | COMP | Rule 15/16 | 114 | 46 | 7 | 65 | 2 | 25 | 254
19259 | 2019-10-11 | 2020-04-28 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-10-21 | COMP | 2020-11-24 | COMP | Rule 16 | 136 | 37 | 11 | 1 | 79 | 24 | 283
15136 | 2019-10-12 | 2019-10-15 | 2019-11-26 | 2020-02-03 | COMP | 2020-08-20 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-03-05 | COMP | Rule 16 | 2 | 30 | 142 |  | 1 | 18 | 97
15572 | 2019-10-12 | 2019-11-07 | 2020-03-18 | 2020-03-18 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-05-11 | COMP | 2020-06-29 | COMP | Rule 16 | 19 | 88 | 36 | 1 | 4 | 35 | 178
15792 | 2019-10-12 | 2019-11-20 | 2020-03-23 | 2020-04-15 | COMP | 2020-04-27 | COMP | 2020-06-08 | COMP | 2020-08-31 | COMP | 2020-10-09 | COMP | Rule 16 | 27 | 83 | 9 | 30 | 61 | 29 | 251
18716 | 2019-10-12 | 2020-04-03 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-06-08 | COMP | Rule 16 | 118 | 24 | 4 | 1 | 1 | 20 | 163
15923 | 2019-10-13 | 2019-12-02 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-13 | NOTN | 2020-04-13 | COMP | 2020-04-15 | COMP | 2020-07-21 | COMP | Other | 33 | 92 |  | 1 | 3 | 69 | 194
15928 | 2019-10-13 | 2019-12-02 | 2020-04-21 | 2020-04-21 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-11-02 | COMP | 2020-11-12 | COMP | Rule 15/16 | 33 | 98 | 75 | 1 | 64 | 8 | 274
15192 | 2019-10-14 | 2019-10-17 | 2020-03-26 | 2020-03-27 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-05-15 | COMP | 2020-06-04 | COMP | Rule 16 | 4 | 109 | 9 | 1 | 28 | 14 | 161
15372 | 2019-10-14 | 2019-10-30 | 2019-12-20 | 2019-12-20 | COMP | 2020-01-21 | COMP | 2020-04-08 | COMP | 2020-08-10 | COMP | 2020-08-24 | COMP | Rule 15/16 | 13 | 35 | 20 | 56 | 88 | 11 | 218
15419 | 2019-10-14 | 2019-10-31 | 2020-02-24 | 2020-02-24 | COMP | 2020-02-27 | COMP | 2020-04-01 | COMP | 2020-04-17 | COMP | 2020-05-18 | COMP | Rule 16 | 14 | 76 | 4 | 25 | 13 | 22 | 149
15424 | 2019-10-14 | 2019-10-31 | 2020-01-21 | 2020-01-21 | COMP | 2021-02-25 | COMP | 2021-02-25 | COMP | 2021-07-13 | COMP | 2021-09-17 | COMP | Rule 16 | 14 | 53 | 278 | 1 | 97 | 48 | 486
15442 | 2019-10-14 | 2019-11-01 | 2020-03-06 | 2020-03-06 | COMP | 2020-06-10 | COMP | 2020-08-19 | COMP | 2020-08-24 | COMP | 2020-10-07 | COMP | Rule 16 | 15 | 84 | 68 | 51 | 4 | 32 | 249
15496 | 2019-10-14 | 2019-11-05 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-13 | COMP | 2020-08-10 | COMP | 2020-09-10 | COMP | 2020-10-22 | COMP | Rule 15/16 | 17 | 121 | 31 | 41 | 23 | 31 | 260
15523 | 2019-10-14 | 2019-11-05 | 2020-01-11 | 2020-01-11 | COMP | 2020-01-17 | COMP | 2020-03-10 | COMP | 2020-03-12 | COMP | 2020-05-07 | COMP | Rule 16 | 17 | 44 | 5 | 36 | 3 | 41 | 142
15533 | 2019-10-14 | 2019-11-06 | 2020-02-13 | 2020-07-13 | COMP | 2020-03-24 | COMP | 2020-08-20 | COMP | 2020-08-06 | COMP | 2020-10-18 | COMP | Rule 15/16 | 18 | 66 |  | 107 | 0 | 41 | 256
15610 | 2019-10-14 | 2019-11-10 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-25 | COMP | 2020-04-08 | COMP | 2020-08-25 | COMP | 2020-11-10 | COMP | Rule 16 | 20 | 63 | 8 | 32 | 99 | 55 | 273
15672 | 2019-10-14 | 2019-11-14 | 2020-02-13 | 2020-02-13 | COMP | 2020-05-18 | COMP | 2020-06-16 | COMP | 2020-06-09 | COMP | 2020-08-06 | COMP | Rule 16 | 23 | 61 | 67 | 21 | 0 | 38 | 206
15782 | 2019-10-14 | 2019-11-21 | 2020-03-17 | 2020-08-17 | COMP | 2020-09-08 | COMP | 2020-03-30 | COMP | 2021-06-02 | COMP | 2021-07-21 | COMP | Rule 16 | 28 | 78 | 16 |  | 298 | 35 | 445
16230 | 2019-10-14 | 2019-12-16 | 2020-04-21 | 2021-11-23 | COMP | 2022-04-18 | COMP | 2022-04-18 | COMP | 2022-08-08 | COMP | 2022-07-15 | COMP | Rule 16 | 43 | 88 | 101 | 1 | 78 |  | 693
16300 | 2019-10-14 | 2019-12-20 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-06 | COMP | 2020-03-16 | COMP | Rule 16 | 47 | 27 | 14 | 1 | 13 | 7 | 104
16702 | 2019-10-14 | 2020-01-13 | 2020-06-16 | 2020-06-16 | COMP | 2020-11-04 | COMP | 2021-08-23 | COMP | 2023-11-15 | COMP | 2023-12-05 | COMP | Rule 16 | 61 | 109 | 101 | 200 | 561 | 13 | 1040
16762 | 2019-10-14 | 2020-01-14 | 2020-05-01 | 2020-05-01 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-08-12 | COMP | 2020-08-26 | COMP | Rule 16 | 62 | 77 | 70 | 1 | 4 | 11 | 220
16913 | 2019-10-14 | 2020-01-23 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-13 | COMP | 2020-03-23 | COMP | 2020-07-07 | COMP | 2020-07-12 | COMP | Rule 16 | 68 | 32 | 5 | 7 | 76 | 4 | 187
17173 | 2019-10-14 | 2020-02-03 | 2021-02-19 | 2021-02-19 | COMP | 2021-10-05 | COMP | 2022-12-08 | COMP | 2023-03-17 | COMP | 2023-04-26 | COMP | Rule 15/16 | 75 | 265 | 160 | 296 | 68 | 29 | 888
17230 | 2019-10-14 | 2020-02-05 | 2020-03-04 | 2020-03-04 | COMP | 2020-05-07 | COMP | 2020-05-19 | COMP | 2020-06-01 | COMP | 2020-07-09 | COMP | Rule 16 | 77 | 20 | 47 | 9 | 9 | 29 | 186
17590 | 2019-10-14 | 2020-02-20 | 2020-06-24 | 2020-09-04 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2020-10-27 | COMP | 2020-12-03 | COMP | Rule 15/16 | 87 | 89 | 36 | 1 | 2 | 25 | 287
17618 | 2019-10-14 | 2020-02-21 | 2020-12-22 | 2020-12-22 | COMP | 2021-01-26 | COMP | 2022-03-08 | COMP | 2022-03-02 | COMP | 2022-04-15 | COMP | Rule 16 | 88 | 213 | 23 | 282 | 0 | 29 | 631
17627 | 2019-10-14 | 2020-02-24 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-04 | COMP | 2020-06-04 | COMP | 2020-05-07 | COMP | 2020-07-06 | COMP | Rule 16 | 89 | 53 | 21 | 1 | 0 | 23 | 183
17731 | 2019-10-14 | 2020-02-26 | 2020-04-20 | 2021-02-11 | COMP | 2021-03-04 | COMP | 2022-12-19 | COMP | 2023-01-26 | COMP | 2023-04-25 | COMP | Rule 16 | 91 | 39 | 15 | 453 | 26 | 63 | 887
17789 | 2019-10-14 | 2020-02-28 | 2020-05-26 | 2020-05-26 | COMP | 2020-07-22 | COMP | 2020-07-23 | COMP | 2020-09-28 | COMP | 2020-10-07 | COMP | Rule 16 | 93 | 62 | 42 | 2 | 47 | 8 | 249
18425 | 2019-10-14 | 2020-03-24 | 2020-04-24 | 2020-04-24 | COMP | 2020-08-07 | COMP | 2020-08-11 | COMP | 2020-10-09 | COMP | 2020-11-05 | COMP | Rule 16 | 110 | 24 | 75 | 3 | 43 | 20 | 270
18740 | 2019-10-14 | 2020-04-06 | 2020-07-03 | 2020-07-03 | COMP | 2021-01-26 | COMP | 2021-08-02 | COMP | 2021-07-29 | COMP | 2022-02-12 | COMP | Rule 16 | 119 | 64 | 141 | 132 | 0 | 135 | 587
18762 | 2019-10-14 | 2020-04-06 | 2020-05-19 | 2020-05-26 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2021-03-11 | COMP | 2021-03-23 | COMP | Rule 16 | 119 | 32 | 5 | 1 | 196 | 9 | 361
18940 | 2019-10-14 | 2020-04-13 | 2020-10-09 | 2020-10-09 | COMP | 2021-04-09 | COMP | 2021-05-18 | COMP | 2021-04-14 | COMP | 2021-06-17 | COMP | Rule 16 | 124 | 128 | 124 | 28 | 0 | 22 | 422
19556 | 2019-10-14 | 2020-05-12 | 2020-08-08 | 2020-08-08 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2020-10-06 | COMP | 2020-10-10 | COMP | Rule 16 | 145 | 63 | 35 | 1 | 7 | 4 | 251
20331 | 2019-10-14 | 2020-06-16 | 2020-10-26 | 2020-10-26 | COMP | 2020-11-12 | COMP | 2020-12-18 | COMP | 2020-12-29 | COMP | 2020-12-30 | COMP | Rule 16 | 169 | 94 | 13 | 25 | 7 | 2 | 305
26414 | 2019-10-14 | 2021-03-19 | 2021-07-29 | 2021-12-30 | COMP | 2022-01-03 | COMP | 2021-10-15 | COMP | 2022-11-08 | COMP | 2023-01-31 | COMP | Rule 16 | 359 | 93 | 3 |  | 269 | 55 | 828
4251 | 2019-10-15 | 2019-11-14 | [8 empty] | INPR | 2020-05-13 | COMP | Other | 22 | [5 empty] | 145
15120 | 2019-10-15 | 2019-10-15 | 2019-12-21 | 2019-12-21 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-01-22 | COMP | 2020-06-15 | COMP | Rule 16 | 1 | 46 | 10 | 1 | 11 | 102 | 167
15191 | 2019-10-15 | 2019-10-18 | 2020-06-11 | 2022-01-11 | COMP | 2022-02-17 | COMP | 2022-03-31 | COMP | 2022-05-24 | COMP | 2022-08-06 | COMP | Rule 15/16 | 4 | 162 | 27 | 30 | 39 | 51 | 707
15220 | 2019-10-15 | 2019-10-21 | 2020-01-21 | 2020-02-26 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP |  | INPR | 2020-11-12 | COMP | Other | 5 | 61 | 139 | 1 |  |  | 273
15307 | 2019-10-15 | 2019-10-25 | 2020-02-15 | 2020-02-15 | COMP | 2020-03-18 | COMP | 2020-04-13 | COMP | 2021-03-03 | COMP | 2021-03-21 | COMP | Rule 16 | 9 | 75 | 22 | 19 | 224 | 13 | 358
15357 | 2019-10-15 | 2019-10-29 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-04-02 | COMP | 2020-05-20 | COMP | Rule 16 | 11 | 82 | 17 | 1 | 9 | 35 | 150
15522 | 2019-10-15 | 2019-11-05 | 2019-12-02 | 2019-12-02 | COMP | 2019-12-10 | COMP | 2019-12-11 | COMP | 2020-03-11 | COMP | 2020-03-25 | COMP | Rule 16 | 16 | 17 | 7 | 2 | 62 | 11 | 110
15546 | 2019-10-15 | 2019-11-06 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-10-30 | COMP | 2020-11-25 | COMP | Rule 16 | 17 | 76 | 42 | 1 | 133 | 18 | 282
15553 | 2019-10-15 | 2019-11-06 | 2020-09-16 | 2020-09-16 | COMP | 2021-07-26 | COMP | 2022-03-07 | COMP | 2022-02-23 | COMP | 2022-04-28 | COMP | Rule 15/16 | 17 | 217 | 215 | 155 | 0 | 39 | 639
15555 | 2019-10-15 | 2019-11-06 | 2021-04-07 | 2023-06-22 | COMP | 2023-06-27 | COMP | 2023-07-13 | COMP | 2023-06-28 | COMP | 2023-09-30 | COMP | Rule 15/16 | 17 | 355 | 4 | 12 | 0 | 56 | 995
15578 | 2019-10-15 | 2019-11-08 | 2019-12-24 | 2019-12-24 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-06-16 | COMP | 2020-08-04 | COMP | Rule 15/16 | 19 | 30 | 114 | 1 | 8 | 36 | 203
15622 | 2019-10-15 | 2019-11-12 | 2020-03-22 | 2020-08-05 | COMP | 2020-11-13 | COMP | 2021-02-10 | COMP | 2021-02-10 | COMP | 2021-02-16 | COMP | Rule 16 | 20 | 88 | 71 | 59 | 1 | 4 | 335
15639 | 2019-10-15 | 2019-11-13 | 2020-03-07 | 2020-03-07 | COMP | 2021-01-19 | COMP | 2021-03-11 | INPR | 2021-04-06 | COMP | 2021-04-28 | COMP | Rule 16 | 21 | 77 | 219 |  |  |  | 386
15674 | 2019-10-15 | 2019-11-14 | 2020-09-04 | 2022-10-27 | COMP | 2022-12-05 | COMP |  | REQD |  | REQD | 2023-07-14 | COMP | Rule 15/16 | 22 | 205 | 25 |  |  |  | 941
15784 | 2019-10-15 | 2019-11-21 | 2020-01-26 | 2020-01-26 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-03-23 | COMP | 2020-06-08 | COMP | Rule 16 | 27 | 42 | 22 | 1 | 19 | 55 | 162
16087 | 2019-10-15 | 2019-12-09 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-21 | COMP | 2020-06-10 | COMP | 2023-04-30 | INPR | 2020-07-28 | COMP | Rule 16 | 37 | 95 | 21 | 14 |  |  | 198
16111 | 2019-10-15 | 2019-12-11 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-26 | COMP | 2020-04-29 | COMP | 2020-04-06 | COMP | 2020-06-12 | COMP | Rule 15/16 | 39 | 60 | 14 | 25 | 0 | 32 | 166
16161 | 2019-10-15 | 2019-12-12 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-31 | COMP | 2020-01-31 | COMP | 2022-01-30 | INPR | 2020-07-08 | COMP | Rule 16 | 40 | 20 | 15 | 1 |  |  | 184
16366 | 2019-10-15 | 2019-12-23 | 2020-07-14 | 2020-07-14 | COMP | 2020-10-20 | COMP | 2021-02-04 | COMP | 2021-02-07 | COMP | 2021-04-08 | COMP | Rule 15/16 | 47 | 142 | 70 | 72 | 2 | 43 | 372
16942 | 2019-10-15 | 2020-01-24 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-07-08 | COMP | Rule 16 | 68 | 26 | 4 | 1 | 1 | 89 | 184
17125 | 2019-10-15 | 2020-01-31 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-29 | COMP | 2021-01-14 | COMP | 2021-01-15 | COMP | 2021-02-17 | COMP | Rule 16 | 73 | 31 | 33 | 180 | 2 | 22 | 336
17246 | 2019-10-15 | 2020-02-05 | 2020-05-14 | 2020-05-14 | COMP | 2021-04-29 | COMP | 2021-05-25 | COMP | 2022-06-18 | INPR | 2021-05-27 | COMP | Rule 16 | 76 | 71 | 242 | 19 |  |  | 407
17665 | 2019-10-15 | 2020-02-25 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-08 | COMP | Rule 16 | 89 | 38 | 13 | 1 | 1 | 5 | 142
17927 | 2019-10-15 | 2020-03-04 | 2020-07-03 | 2020-07-03 | COMP | 2020-08-03 | COMP | 2020-07-22 | COMP | 2020-09-06 | COMP | 2020-08-31 | COMP | Rule 16 | 95 | 87 | 22 |  | 33 |  | 222
18686 | 2019-10-15 | 2020-04-02 | 2021-01-06 | 2021-01-06 | COMP | 2021-01-12 | COMP | 2021-02-12 | COMP | 2022-07-16 | INPR | 2021-06-16 | COMP | Rule 16 | 116 | 193 | 5 | 23 |  |  | 420
15352 | 2019-10-16 | 2019-10-28 | 2020-01-11 | 2020-01-22 | COMP | 2020-02-05 | COMP | 2020-03-19 | COMP | 2022-01-30 | INPR | 2020-06-08 | COMP | Rule 16 | 9 | 50 | 11 | 31 |  |  | 161
15532 | 2019-10-16 | 2019-11-06 | 2020-07-09 | 2020-07-14 | COMP | 2020-10-21 | COMP | 2022-06-09 | COMP | 2022-02-16 | COMP | 2023-04-13 | COMP | Rule 16 | 16 | 169 | 71 | 411 | 0 | 211 | 877
15536 | 2019-10-16 | 2019-11-06 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-21 | COMP | 2020-02-28 | COMP | 2020-03-02 | COMP | 2020-03-13 | COMP | Rule 16 | 16 | 42 | 8 | 28 | 2 | 10 | 101
15549 | 2019-10-16 | 2019-11-06 | 2020-03-08 | 2020-03-08 | COMP | 2020-04-01 | COMP | 2020-04-01 | COMP | 2020-12-15 | COMP | 2021-01-11 | COMP | Rule 16 | 16 | 81 | 18 | 1 | 180 | 18 | 310
15564 | 2019-10-16 | 2019-11-07 | 2020-02-19 | 2020-02-19 | COMP | 2020-05-19 | COMP | 2020-05-26 | COMP | 2020-05-19 | COMP | 2020-06-29 | COMP | Rule 16 | 17 | 68 | 65 | 5 | 0 | 25 | 176
15574 | 2019-10-16 | 2019-11-07 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-07 | NOTN | 2020-04-28 | COMP | 2020-02-18 | COMP | 2020-06-19 | COMP | Other | 17 | 75 |  | 43 | 0 | 38 | 170
15615 | 2019-10-16 | 2019-11-12 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-22 | COMP | 2020-08-19 | COMP | 2020-08-06 | COMP | 2020-10-02 | COMP | Rule 16 | 19 | 79 | 33 | 85 | 0 | 32 | 244
15774 | 2019-10-16 | 2019-11-20 | 2020-03-18 | 2020-03-18 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-06-24 | COMP | Rule 16 | 25 | 80 | 39 | 1 | 1 | 32 | 173
15875 | 2019-10-16 | 2019-11-25 | 2020-02-03 | 2020-02-03 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2022-06-28 | COMP | 2022-08-12 | COMP | Rule 16 | 28 | 46 | 40 | 1 | 568 | 33 | 711
15897 | 2019-10-16 | 2019-11-27 | 2020-02-08 | 2021-01-26 | COMP | 2021-03-15 | COMP | 2020-08-05 | COMP | 2021-03-30 | COMP | 2021-04-29 | COMP | Rule 16 | 30 | 48 | 34 |  | 162 | 23 | 386
16046 | 2019-10-16 | 2019-12-06 | 2020-02-21 | 2020-02-21 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-09-08 | COMP | 2020-10-21 | COMP | Rule 16 | 35 | 52 | 80 | 1 | 62 | 32 | 257
16525 | 2019-10-16 | 2020-01-06 | 2020-04-27 | 2021-06-03 | COMP | 2021-07-26 | COMP | 2021-10-07 | COMP | 2021-01-25 | COMP | 2022-02-11 | COMP | Rule 16 | 54 | 79 | 37 | 53 | 0 | 88 | 585
16569 | 2019-10-16 | 2020-01-08 | 2020-02-10 | 2020-02-10 | COMP | 2020-02-18 | COMP | 2020-03-12 | COMP | 2022-07-30 | INPR | 2020-03-30 | COMP | Rule 16 | 56 | 23 | 6 | 18 |  |  | 112
16696 | 2019-10-16 | 2020-01-13 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-06 | COMP | 2020-07-24 | COMP | 2020-09-22 | COMP | 2020-10-01 | COMP | Rule 16 | 59 | 74 | 8 | 57 | 42 | 8 | 243
16760 | 2019-10-16 | 2020-01-15 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-12-28 | COMP | 2021-01-08 | COMP | Rule 16 | 61 | 82 | 23 | 1 | 138 | 9 | 309
16967 | 2019-10-16 | 2020-01-27 | 2020-03-21 | 2020-03-21 | COMP | 2020-03-26 | COMP | 2021-04-21 | COMP | 2021-04-19 | COMP | 2021-05-26 | COMP | Rule 16 | 68 | 39 | 4 | 271 | 0 | 26 | 405
16979 | 2019-10-16 | 2020-01-28 | 2020-02-12 | 2020-02-12 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-05-05 | COMP | 2020-05-27 | COMP | Rule 15/16 | 69 | 12 | 36 | 1 | 24 | 16 | 153
17259 | 2019-10-16 | 2020-02-06 | 2020-02-17 | 2020-02-17 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-12-10 | COMP | 2020-12-23 | COMP | Rule 16 | 76 | 7 | 37 | 1 | 172 | 10 | 299
17292 | 2019-10-16 | 2020-02-07 | 2020-11-02 | 2020-11-02 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2022-02-26 | INPR | 2021-01-29 | COMP | Rule 16 | 77 | 189 | 17 | 1 |  |  | 323
17449 | 2019-10-16 | 2020-02-13 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2022-01-30 | INPR | 2020-05-28 | COMP | Rule 16 | 81 | 58 | 11 | 1 |  |  | 154
17462 | 2019-10-16 | 2020-02-14 | 2020-03-26 | 2020-07-20 | COMP | 2020-08-13 | COMP | 2020-09-01 | COMP | 2022-01-30 | INPR | 2020-09-17 | COMP | Rule 16 | 82 | 29 | 19 | 14 |  |  | 233
17503 | 2019-10-16 | 2020-02-19 | 2020-07-20 | 2020-10-09 | COMP | 2020-11-25 | COMP | 2021-11-10 | COMP | 2023-05-16 | COMP | 2023-06-23 | COMP | Rule 16 | 84 | 108 | 33 | 242 | 379 | 27 | 926
18115 | 2019-10-16 | 2020-03-11 | 2020-11-03 | 2020-11-03 | COMP | 2021-10-28 | COMP | 2021-12-06 | COMP | 2022-08-24 | COMP | 2022-10-14 | COMP | Rule 16 | 99 | 168 | 248 | 25 | 183 | 37 | 755
18503 | 2019-10-16 | 2020-03-26 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2022-01-26 | COMP | 2022-05-04 | COMP | Rule 16 | 110 | 63 | 27 | 1 | 376 | 70 | 642
18546 | 2019-10-16 | 2020-03-30 | 2020-04-26 | 2020-04-26 | COMP | 2020-06-12 | COMP | 2020-07-17 | COMP | 2020-09-22 | COMP | 2020-10-21 | COMP | Rule 16 | 112 | 20 | 34 | 26 | 47 | 22 | 257
19717 | 2019-10-16 | 2020-05-19 | 2020-09-04 | 2020-09-22 | COMP | 2020-10-07 | COMP | 2020-10-22 | COMP | 2021-02-02 | COMP | 2021-02-05 | COMP | Rule 16 | 148 | 78 | 12 | 12 | 68 | 4 | 328
15276 | 2019-10-17 | 2019-10-25 | 2020-01-24 | 2020-01-24 | COMP | 2020-04-13 | COMP | 2020-04-14 | COMP | 2020-04-29 | COMP | 2020-07-11 | COMP | Rule 15/16 | 7 | 60 | 56 | 2 | 12 | 52 | 184
15366 | 2019-10-17 | 2019-10-29 | 2019-11-22 | 2019-11-22 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-06 | COMP | 2020-01-10 | COMP | Rule 16 | 9 | 18 | 3 | 1 | 7 | 24 | 57
15373 | 2019-10-17 | 2019-10-29 | 2019-11-22 | 2019-11-22 | COMP | 2019-11-26 | COMP | 2019-11-26 | COMP | 2019-12-05 | COMP | 2020-01-10 | COMP | Rule 16 | 9 | 18 | 3 | 1 | 6 | 25 | 57
15434 | 2019-10-17 | 2019-10-31 | 2020-09-18 | 2020-09-18 | COMP | 2020-12-04 | COMP | 2020-12-04 | COMP | 2021-05-19 | COMP | 2021-06-07 | COMP | Rule 15/16 | 11 | 223 | 53 | 1 | 115 | 13 | 411
15456 | 2019-10-17 | 2019-11-01 | 2020-04-21 | 2020-04-21 | COMP | 2020-08-04 | COMP | 2021-04-21 | COMP | 2021-04-12 | COMP | 2021-05-06 | COMP | Rule 15/16 | 12 | 116 | 75 | 179 | 0 | 12 | 390
15561 | 2019-10-17 | 2019-11-06 | 2020-02-08 | 2020-02-08 | COMP | 2020-03-03 | COMP | 2020-05-07 | COMP | 2020-05-27 | COMP | 2020-06-11 | COMP | Rule 16 | 15 | 62 | 16 | 48 | 14 | 12 | 163
15599 | 2019-10-17 | 2019-11-08 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-06-19 | COMP | 2020-08-10 | COMP | Rule 16 | 17 | 48 | 21 | 1 | 86 | 37 | 205
15685 | 2019-10-17 | 2019-11-15 | 2020-07-10 | 2020-07-10 | COMP | 2020-07-13 | NOTN | 2020-07-27 | COMP | 2020-07-13 | COMP | 2020-09-16 | COMP | Other | 21 | 164 |  | 12 | 0 | 37 | 231
15777 | 2019-10-17 | 2019-11-21 | 2020-03-23 | 2020-03-23 | COMP | 2021-03-02 | COMP | 2021-03-02 | COMP | 2021-04-28 | COMP | 2021-05-18 | COMP | Rule 16 | 25 | 82 | 238 | 1 | 42 | 15 | 398
15877 | 2019-10-17 | 2019-11-25 | 2020-01-28 | 2020-01-28 | COMP | 2020-04-17 | COMP | 2020-04-20 | COMP | 2020-04-27 | COMP | 2020-07-09 | COMP | Rule 16 | 27 | 42 | 58 | 2 | 6 | 53 | 183
15879 | 2019-10-17 | 2019-11-25 | 2020-01-23 | 2020-01-28 | COMP | 2020-01-28 | NOTN | 2020-03-18 | COMP | 2020-04-07 | COMP | 2020-06-23 | COMP | Other | 27 | 39 |  | 36 | 15 | 55 | 171
15914 | 2019-10-17 | 2019-11-27 | 2020-03-12 | 2020-03-12 | COMP | 2020-03-17 | NOTN | 2020-05-05 | COMP | 2020-05-13 | COMP | 2020-06-30 | COMP | Rule 16 | 29 | 71 |  | 39 | 7 | 34 | 176
15926 | 2019-10-17 | 2019-12-02 | 2020-08-20 | 2020-08-20 | COMP | 2020-09-28 | COMP | 2020-10-22 | COMP | 2020-09-29 | COMP | 2021-01-15 | COMP | Rule 15/16 | 30 | 184 | 27 | 19 | 0 | 57 | 313
15951 | 2019-10-17 | 2019-12-03 | 2020-03-13 | 2020-03-13 | COMP | 2020-06-18 | COMP | 2021-01-27 | COMP | 2021-12-13 | COMP | 2022-01-29 | COMP | Rule 16 | 31 | 70 | 69 | 153 | 222 | 34 | 574
16137 | 2019-10-17 | 2019-12-11 | 2020-08-09 | 2021-03-03 | COMP | 2021-12-15 | COMP | 2022-06-27 | COMP | 2022-07-19 | COMP | 2022-09-01 | COMP | Rule 15/16 | 37 | 168 | 200 | 135 | 16 | 33 | 724
16156 | 2019-10-17 | 2019-12-16 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-02-21 | COMP | 2020-03-26 | COMP | Rule 15/16 | 40 | 33 | 10 | 1 | 5 | 25 | 109
16314 | 2019-10-17 | 2019-12-20 | 2020-01-29 | 2020-01-29 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-02-21 | COMP | 2020-03-09 | COMP | Rule 16 | 44 | 26 | 9 | 1 | 9 | 12 | 96
16557 | 2019-10-17 | 2020-01-07 | 2020-06-06 | 2020-06-06 | COMP | 2020-07-07 | COMP | 2020-09-08 | COMP | 2022-01-30 | INPR | 2020-09-25 | COMP | Rule 16 | 54 | 106 | 22 | 45 |  |  | 238
16573 | 2019-10-17 | 2020-01-08 | 2020-01-22 | 2020-03-08 | COMP | 2020-04-02 | COMP | 2020-03-03 | COMP | 2020-04-06 | COMP | 2020-06-18 | COMP | Rule 16 | 55 | 10 | 19 |  | 25 | 53 | 168
16619 | 2019-10-17 | 2020-01-10 | 2020-06-19 | 2020-06-19 | COMP | 2020-09-18 | COMP | 2020-12-30 | COMP | 2021-04-05 | COMP | 2021-04-27 | COMP | Rule 16 | 57 | 113 | 65 | 70 | 66 | 17 | 383
16761 | 2019-10-17 | 2020-01-14 | 2020-03-22 | 2020-03-22 | COMP | 2020-04-01 | COMP | 2020-05-28 | NOTN | 2020-05-31 | COMP | 2020-07-10 | COMP | Rule 15/16 | 59 | 47 | 8 |  |  |  | 184
17529 | 2019-10-17 | 2020-02-19 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-26 | COMP | 2020-06-24 | COMP | 2020-08-24 | COMP | 2020-09-14 | COMP | Rule 16 | 83 | 54 | 16 | 22 | 44 | 15 | 229
17553 | 2019-10-17 | 2020-02-20 | 2020-10-25 | 2020-10-25 | COMP | 2020-11-12 | COMP | 2020-12-23 | COMP | 2021-03-16 | COMP | 2021-05-07 | COMP | Rule 15/16 | 84 | 175 | 13 | 28 | 56 | 39 | 391
17631 | 2019-10-17 | 2020-02-24 | 2020-04-21 | 2020-04-21 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2021-04-28 | COMP | 2021-05-08 | COMP | Rule 16 | 86 | 42 | 160 | 1 | 99 | 8 | 391
17693 | 2019-10-17 | 2020-02-24 | 2020-12-04 | 2020-12-04 | COMP | 2020-02-24 | NOTN | 2021-04-14 | COMP | 2021-08-09 | COMP | 2021-11-17 | COMP | Other | 86 | 200 |  | 90 | 82 | 71 | 525
17913 | 2019-10-17 | 2020-03-03 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-24 | COMP | 2020-06-09 | COMP | 2020-04-24 | COMP | 2020-08-11 | COMP | Rule 16 | 92 | 22 | 18 | 32 | 0 | 46 | 206
18009 | 2019-10-17 | 2020-03-09 | 2020-04-29 | 2020-10-01 | COMP | 2020-10-30 | COMP | 2020-12-31 | COMP | 2020-11-09 | COMP | 2021-02-05 | COMP | Rule 16 | 96 | 38 | 22 | 41 | 0 | 25 | 327
18210 | 2019-10-17 | 2020-03-16 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-08 | COMP | 2020-07-09 | COMP | 2020-07-21 | COMP | 2020-08-10 | COMP | Rule 16 | 101 | 45 | 16 | 24 | 9 | 15 | 205
18485 | 2019-10-17 | 2020-03-26 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-17 | COMP | 2020-10-19 | COMP | 2020-12-07 | COMP | 2020-12-10 | COMP | Rule 16 | 109 | 56 | 26 | 66 | 33 | 4 | 289
18562 | 2019-10-17 | 2020-03-29 | 2020-12-22 | 2020-12-22 | COMP | 2021-01-19 | COMP | 2021-05-10 | COMP | 2021-06-08 | COMP | 2021-08-11 | COMP | Rule 15/16 | 110 | 187 | 18 | 79 | 21 | 46 | 457
18859 | 2019-10-17 | 2020-04-09 | 2020-10-01 | 2020-10-01 | COMP | 2021-01-20 | COMP | 2021-02-02 | COMP | 2021-02-08 | COMP | 2021-02-17 | COMP | Rule 16 | 119 | 124 | 74 | 10 | 5 | 7 | 334
18962 | 2019-10-17 | 2020-04-14 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2021-04-01 | COMP | 2022-03-14 | COMP | Rule 16 | 122 | 34 | 14 | 1 | 198 | 240 | 604
19942 | 2019-10-17 | 2020-05-28 | 2020-08-03 | 2020-11-19 | COMP | 2021-02-01 | COMP | 2021-02-01 | COMP | 2021-03-23 | COMP | 2021-05-11 | COMP | Rule 16 | 153 | 48 | 48 | 1 | 36 | 36 | 393
15326 | 2019-10-18 | 2019-10-25 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-13 | COMP | 2020-01-23 | COMP | 2020-02-07 | COMP | 2020-02-24 | COMP | Rule 16 | 6 | 33 | 20 | 8 | 12 | 11 | 85
15333 | 2019-10-18 | 2019-10-28 | 2019-12-27 | 2019-12-27 | COMP | 2019-12-29 | NOTN | 2019-12-29 | COMP | 2019-12-29 | COMP | 2020-02-07 | COMP | Other | 7 | 41 |  | 1 | 0 | 28 | 75
15351 | 2019-10-18 | 2019-10-28 | 2019-12-05 | 2019-12-05 | COMP | 2020-01-02 | COMP | 2020-01-02 | COMP | 2021-03-28 | INPR | 2020-03-14 | COMP | Rule 16 | 7 | 26 | 19 | 1 |  |  | 99
15396 | 2019-10-18 | 2019-10-30 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-07 | COMP | 2020-04-10 | COMP | 2020-07-08 | COMP | 2020-08-12 | COMP | Rule 16 | 9 | 106 | 3 | 4 | 63 | 26 | 206
15717 | 2019-10-18 | 2019-11-18 | 2020-02-11 | 2020-02-11 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2021-01-26 | COMP | 2021-02-23 | COMP | Rule 16 | 21 | 57 | 203 | 1 | 40 | 20 | 337
16044 | 2019-10-18 | 2019-12-06 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-30 | COMP | 2020-12-21 | COMP | 2021-06-06 | COMP | 2021-07-27 | COMP | Rule 16 | 33 | 108 | 36 | 121 | 115 | 36 | 445
16335 | 2019-10-18 | 2019-12-20 | 2020-03-09 | 2020-07-22 | COMP | 2020-08-26 | COMP | 2020-11-17 | COMP | 2020-11-30 | COMP | 2020-12-18 | COMP | Rule 15/16 | 43 | 53 | 26 | 58 | 8 | 15 | 294
16402 | 2019-10-18 | 2019-12-27 | 2020-02-07 | 2020-02-21 | COMP | 2020-03-02 | COMP | 2020-03-09 | COMP |  |  | 2020-03-23 | COMP | Rule 16 | 47 | 29 | 7 | 6 |  |  | 105
16414 | 2019-10-18 | 2019-12-27 | 2020-05-28 | 2021-07-31 | COMP | 2021-08-03 | COMP | 2021-08-03 | COMP | 2020-06-19 | COMP | 2021-11-15 | COMP | Rule 16 | 47 | 106 | 2 | 1 | 0 | 73 | 522
16723 | 2019-10-18 | 2020-01-13 | 2020-02-07 | 2020-02-07 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-11-16 | COMP | 2020-12-07 | COMP | Rule 16 | 57 | 19 | 94 | 1 | 105 | 14 | 285
16766 | 2019-10-18 | 2020-01-14 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-03-10 | COMP | 2020-05-28 | COMP | Rule 16 | 58 | 32 | 12 | 1 | 0 | 53 | 152
16796 | 2019-10-18 | 2020-01-16 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-17 | COMP | 2020-07-06 | COMP | 2020-06-26 | COMP | 2020-11-06 | COMP | Rule 16 | 60 | 77 | 31 | 14 | 0 | 89 | 267
16815 | 2019-10-18 | 2020-01-16 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-28 | COMP | 2020-07-08 | COMP | 2020-07-01 | COMP | 2020-08-04 | COMP | Rule 15/16 | 60 | 87 | 7 | 30 | 0 | 20 | 200
16849 | 2019-10-18 | 2020-01-22 | 2020-06-17 | 2020-06-17 | COMP | 2020-10-01 | COMP | 2020-11-06 | COMP | 2021-04-26 | COMP | 2021-05-25 | COMP | Rule 15/16 | 63 | 104 | 76 | 27 | 115 | 22 | 402
16955 | 2019-10-18 | 2020-01-25 | 2020-05-19 | 2020-06-26 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-12-09 | COMP | 2021-02-10 | COMP | Rule 16 | 65 | 81 | 48 | 1 | 68 | 43 | 329
16995 | 2019-10-18 | 2020-01-27 | 2020-07-20 | 2020-07-20 | COMP | 2020-08-21 | COMP | 2020-11-25 | COMP | 2022-04-04 | COMP | 2022-05-16 | COMP | Rule 16 | 66 | 124 | 25 | 67 | 340 | 31 | 648
17009 | 2019-10-18 | 2020-01-28 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-20 | COMP | 2020-06-19 | COMP | 2021-04-26 | COMP | 2021-06-25 | COMP | Rule 16 | 67 | 47 | 13 | 44 | 214 | 44 | 424
17136 | 2019-10-18 | 2020-01-31 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-08-27 | COMP | Rule 16 | 70 | 89 | 8 | 1 | 1 | 53 | 217
17440 | 2019-10-18 | 2020-02-13 | 2020-08-07 | 2020-08-07 | COMP | 2020-10-02 | COMP | 2021-03-26 | COMP | 2021-04-13 | COMP | 2021-05-29 | COMP | Rule 15/16 | 79 | 125 | 40 | 119 | 13 | 34 | 405
17574 | 2019-10-18 | 2020-02-20 | 2020-03-31 | 2020-03-31 | COMP | 2020-03-31 | NOTN | 2020-03-31 | COMP | 2021-09-10 | COMP | 2021-11-04 | COMP | Other | 83 | 29 |  | 1 | 367 | 40 | 516
17755 | 2019-10-18 | 2020-02-25 | 2020-07-30 | 2020-07-30 | COMP | 2020-09-14 | COMP | 2021-02-24 | COMP | 2021-04-01 | COMP | 2021-04-15 | COMP | Rule 15/16 | 86 | 112 | 32 | 111 | 27 | 11 | 374
36451 | 2019-10-18 | 2022-05-18 | 2022-10-21 | 2022-10-21 | COMP | 2022-11-09 | COMP | 2022-11-09 | COMP | 2023-01-04 | COMP | 2023-01-20 | COMP | Rule 16 | 650 | 109 | 14 | 1 | 36 | 12 | 817
15744 | 2019-10-19 | 2019-11-20 | 2020-03-20 | 2020-06-05 | COMP | 2020-08-04 | COMP | 2020-08-07 | COMP | 2020-11-30 | COMP | 2020-12-08 | COMP | Rule 15/16 | 22 | 82 | 43 | 4 | 78 | 7 | 285
16409 | 2019-10-19 | 2019-12-27 | 2020-02-05 | 2020-02-05 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-04-25 | COMP | 2020-06-04 | COMP | Rule 16 | 46 | 27 | 57 | 1 | 1 | 28 | 156
16436 | 2019-10-19 | 2019-12-31 | 2020-03-16 | 2020-03-16 | COMP | 2020-06-01 | COMP | 2020-06-10 | INPR | 2020-06-02 | COMP | 2020-06-30 | COMP | Rule 16 | 48 | 52 | 55 |  |  |  | 174
16487 | 2019-10-19 | 2020-01-03 | 2020-04-02 | 2020-04-02 | COMP | 2020-06-03 | COMP | 2021-09-16 | COMP | 2022-03-29 | COMP | 2022-04-22 | COMP | Rule 16 | 50 | 63 | 44 | 326 | 134 | 19 | 631
16510 | 2019-10-19 | 2020-01-06 | 2020-05-07 | 2020-05-07 | COMP | 2020-07-01 | COMP | 2020-10-15 | COMP | 2020-12-18 | COMP | 2021-01-25 | COMP | Rule 15/16 | 51 | 87 | 39 | 76 | 44 | 24 | 316
16516 | 2019-10-19 | 2020-01-06 | 2020-03-24 | 2020-03-24 | COMP | 2020-06-03 | COMP | 2022-02-28 | COMP | 2022-03-09 | COMP | 2022-04-28 | COMP | Rule 16 | 51 | 55 | 51 | 438 | 8 | 37 | 635
16519 | 2019-10-19 | 2020-01-06 | 2020-03-30 | 2022-08-06 | COMP | 2020-09-15 | COMP | 2023-06-21 | COMP | 2023-06-23 | COMP | 2023-08-29 | COMP | Rule 16 | 51 | 59 |  | 694 | 3 | 47 | 969
16520 | 2019-10-19 | 2020-01-06 | 2020-03-24 | 2020-03-24 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-02 | COMP | 2020-06-29 | COMP | Rule 16 | 51 | 55 | 49 | 1 | 2 | 20 | 173
16629 | 2019-10-19 | 2020-01-09 | 2020-04-02 | 2020-04-02 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-02 | COMP | 2020-06-29 | COMP | Rule 16 | 54 | 59 | 42 | 1 | 2 | 20 | 173
16671 | 2019-10-19 | 2020-01-10 | 2020-04-14 | 2020-04-20 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-09-08 | COMP | 2020-10-05 | COMP | Rule 16 | 55 | 66 | 32 | 1 | 69 | 20 | 242
16755 | 2019-10-19 | 2020-01-14 | 2020-04-20 | 2020-04-20 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-09-21 | COMP | 2020-10-06 | COMP | Rule 16 | 57 | 68 | 105 | 1 | 5 | 12 | 243
15265 | 2019-10-21 | 2019-10-24 | 2019-12-03 | 2019-12-03 | COMP | 2019-12-16 | COMP | 2020-02-04 | COMP | 2020-01-31 | COMP | 2020-12-14 | COMP | Rule 16 | 4 | 26 | 10 | 34 | 0 | 219 | 289
15380 | 2019-10-21 | 2019-10-29 | 2020-01-08 | 2021-02-27 | REQD | 2021-02-27 | REQD | 2020-01-23 | COMP | 2020-02-18 | COMP | 2020-02-17 | COMP | Unknown | 7 |  |  |  | 18 |  | 79
15381 | 2019-10-21 | 2019-10-29 | 2020-01-11 | 2020-01-11 | COMP | 2020-01-23 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-03-01 | COMP | Rule 16 | 7 | 49 | 8 | 23 | 1 | 4 | 88
15383 | 2019-10-21 | 2019-10-29 | 2019-12-16 | 2019-12-16 | COMP | 2019-12-30 | COMP | 2019-12-30 | COMP | 2020-02-20 | COMP | 2020-02-23 | COMP | Rule 16 | 7 | 32 | 10 | 1 | 36 | 2 | 83
15384 | 2019-10-21 | 2019-10-29 | 2019-11-26 | 2019-11-26 | COMP | 2019-12-16 | COMP | 2019-12-16 | COMP | 2020-02-20 | COMP | 2020-02-23 | COMP | Rule 16 | 7 | 20 | 13 | 1 | 45 | 2 | 83
15385 | 2019-10-21 | 2019-10-29 | 2019-12-13 | 2019-12-13 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-03-03 | COMP | 2020-03-01 | COMP | Rule 16 | 7 | 31 | 16 | 1 | 39 |  | 88
15998 | 2019-10-21 | 2019-12-04 | 2020-01-16 | 2020-01-16 | COMP | 2020-04-06 | COMP | 2020-07-07 | COMP | 2020-09-21 | COMP | 2020-10-22 | COMP | Rule 16 | 30 | 30 | 56 | 66 | 54 | 24 | 255
16115 | 2019-10-21 | 2019-12-10 | 2021-01-29 | 2021-01-29 | COMP | 2021-02-26 | COMP | 2021-12-01 | COMP | 2021-12-23 | COMP | 2022-03-03 | COMP | Rule 15/16 | 34 | 287 | 20 | 193 | 17 | 49 | 595
16225 | 2019-10-21 | 2019-12-17 | 2020-03-24 | 2020-04-13 | COMP | 2020-06-24 | COMP | 2020-09-09 | COMP | 2022-01-30 | INPR | 2020-10-28 | COMP | Rule 16 | 39 | 67 | 52 | 55 |  |  | 259
16364 | 2019-10-21 | 2019-12-26 | 2020-06-17 | 2020-06-17 | COMP | 2020-08-24 | COMP | 2020-10-21 | COMP | 2021-05-25 | COMP | 2021-06-25 | COMP | Rule 15/16 | 45 | 121 | 49 | 42 | 148 | 23 | 423
16397 | 2019-10-21 | 2019-12-27 | 2020-01-28 | 2020-01-28 | COMP | 2020-02-20 | COMP | 2020-02-20 | COMP | 2020-03-31 | COMP | 2020-06-02 | COMP | Rule 16 | 46 | 21 | 17 | 1 | 29 | 45 | 154
16415 | 2019-10-21 | 2019-12-27 | 2020-07-13 | 2020-07-13 | COMP | 2020-11-12 | COMP | 2021-02-22 | COMP | 2022-01-04 | COMP | 2022-01-26 | COMP | Rule 15/16 | 46 | 138 | 87 | 67 | 221 | 16 | 570
16582 | 2019-10-21 | 2020-01-08 | 2020-05-27 | 2020-05-27 | COMP | 2020-11-18 | COMP | 2021-06-11 | COMP | 2021-07-06 | COMP | 2021-07-24 | COMP | Rule 15/16 | 53 | 98 | 124 | 141 | 17 | 14 | 442
16686 | 2019-10-21 | 2020-01-12 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-07 | COMP | 2020-06-05 | COMP | 2023-04-30 | INPR | 2020-06-26 | COMP | Rule 16 | 55 | 57 | 4 | 43 |  |  | 172
16770 | 2019-10-21 | 2020-01-15 | 2020-04-22 | 2020-04-22 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-11-24 | COMP | 2020-12-07 | COMP | Rule 16 | 58 | 69 | 94 | 1 | 59 | 8 | 284
16776 | 2019-10-21 | 2020-01-15 | 2020-02-17 | 2020-02-17 | COMP | 2020-04-04 | NOTN | 2020-04-04 | COMP | 2020-05-18 | COMP | 2020-05-20 | COMP | Rule 16 | 58 | 22 |  | 34 | 31 | 3 | 146
16925 | 2019-10-21 | 2020-01-23 | 2020-04-19 | 2020-09-23 | COMP | 2020-10-12 | COMP | 2020-12-21 | COMP | 2023-11-13 | INPR | 2021-01-05 | COMP | Rule 16 | 63 | 61 | 14 | 48 |  |  | 303
16993 | 2019-10-21 | 2020-01-27 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-18 | COMP | 2020-05-22 | COMP | 2020-05-11 | COMP | 2020-06-29 | COMP | Rule 16 | 65 | 70 | 11 | 5 | 0 | 26 | 173
17121 | 2019-10-21 | 2020-01-31 | 2020-04-11 | 2020-04-11 | COMP | 2020-07-17 | COMP | 2020-09-15 | COMP | 2021-03-29 | COMP | 2021-05-03 | COMP | Rule 16 | 69 | 50 | 69 | 42 | 133 | 26 | 385
17254 | 2019-10-21 | 2020-02-06 | 2020-03-03 | 2020-03-03 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-05-18 | COMP | 2020-05-26 | COMP | Rule 16 | 73 | 18 | 35 | 1 | 21 | 6 | 149
17623 | 2019-10-21 | 2020-02-21 | 2020-06-01 | 2020-06-09 | COMP | 2020-07-03 | COMP | 2020-08-19 | COMP | 2020-10-02 | COMP | 2020-12-07 | COMP | Rule 16 | 83 | 71 | 19 | 34 | 32 | 44 | 284
17708 | 2019-10-21 | 2020-02-24 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-09-28 | COMP | 2020-11-20 | COMP | Rule 16 | 84 | 21 | 18 | 1 | 117 | 39 | 275
17793 | 2019-10-21 | 2020-02-27 | 2020-07-10 | 2023-05-17 | COMP | 2023-05-25 | COMP | 2023-05-25 | COMP | 2023-05-30 | COMP | 2023-07-31 | COMP | Rule 15/16 | 87 | 96 | 7 | 1 | 3 | 43 | 948
17841 | 2019-10-21 | 2020-03-02 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-07-02 | COMP | 2020-07-06 | COMP | Other | 89 | 46 | 37 | 1 | 7 | 3 | 178
17850 | 2019-10-21 | 2020-03-02 | 2020-07-08 | 2020-07-08 | COMP | 2020-09-11 | COMP | 2020-11-23 | COMP | 2021-01-11 | COMP | 2021-01-12 | COMP | Rule 16 | 89 | 92 | 47 | 51 | 32 | 2 | 308
17953 | 2019-10-21 | 2020-03-05 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-30 | COMP | 2020-10-28 | COMP | 2020-11-23 | COMP | 2020-12-07 | COMP | Rule 16 | 92 | 52 | 32 | 86 | 18 | 9 | 284
17963 | 2019-10-21 | 2020-03-05 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-03-31 | COMP | 2020-04-08 | COMP | Rule 16 | 92 | 8 | 11 | 1 | 2 | 7 | 116
18179 | 2019-10-21 | 2020-03-13 | 2020-08-04 | 2020-08-04 | COMP | 2020-07-22 | NOTN | 2020-08-04 | COMP | 2022-05-31 | COMP | 2022-07-13 | COMP | Other | 98 | 102 |  | 1 | 459 | 30 | 686
18702 | 2019-10-21 | 2020-04-03 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-21 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-09-04 | COMP | Rule 16 | 113 | 59 | 19 | 18 | 1 | 17 | 222
18790 | 2019-10-21 | 2020-04-07 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-03 | COMP | 2020-07-08 | COMP | 2020-08-26 | COMP | 2020-10-08 | COMP | Rule 16 | 115 | 54 | 10 | 4 | 36 | 31 | 245
19469 | 2019-10-21 | 2020-05-07 | 2020-05-13 | 2020-07-20 | COMP | 2020-07-31 | COMP | 2020-06-18 | COMP | 2020-09-21 | COMP | 2021-05-03 | COMP | Rule 15/16 | 137 | 5 | 10 |  | 67 | 154 | 385
20303 | 2019-10-21 | 2020-06-16 | 2020-08-05 | 2020-08-05 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2020-08-20 | COMP | 2020-10-30 | COMP | Rule 16 | 164 | 37 | 11 | 1 | 2 | 51 | 261
20413 | 2019-10-21 | 2020-06-19 | 2020-09-17 | 2020-09-17 | COMP | 2020-10-28 | COMP | 2020-11-17 | COMP | 2022-04-17 | INPR | 2021-03-27 | COMP | Rule 16 | 167 | 64 | 30 | 14 |  |  | 359
15481 | 2019-10-22 | 2019-11-04 | 2020-02-24 | 2020-06-03 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-07-03 | COMP | Rule 16 | 10 | 74 | 6 | 1 | 1 | 18 | 176
15602 | 2019-10-22 | 2019-11-08 | 2019-12-30 | 2020-06-08 | COMP | 2020-06-16 | COMP | 2021-03-28 | COMP | 2021-03-23 | COMP | 2021-04-10 | COMP | Rule 16 | 14 | 33 | 7 | 196 | 0 | 10 | 368
15805 | 2019-10-22 | 2019-11-21 | 2020-03-31 | 2020-04-20 | COMP | 2020-05-12 | COMP | 2020-07-28 | COMP | 2020-09-25 | COMP | 2020-11-13 | COMP | Rule 16 | 22 | 88 | 17 | 55 | 43 | 35 | 269
15809 | 2019-10-22 | 2019-11-21 | 2019-12-10 | 2019-12-10 | COMP | 2019-12-23 | COMP | 2020-01-13 | COMP | 2020-01-22 | COMP | 2020-02-13 | COMP | Rule 16 | 22 | 12 | 10 | 14 | 7 | 17 | 77
15850 | 2019-10-22 | 2019-11-25 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-10 | COMP | 2020-11-09 | COMP | 2020-12-01 | COMP | 2020-12-03 | COMP | Rule 16 | 24 | 47 | 5 | 193 | 14 | 3 | 281
15919 | 2019-10-22 | 2019-12-02 | 2020-01-13 | 2020-01-13 | COMP | 2021-06-07 | COMP | 2021-06-07 | COMP | 2023-07-29 | INPR | 2021-07-22 | COMP | Rule 16 | 27 | 29 | 354 | 1 |  |  | 440
16023 | 2019-10-22 | 2019-12-06 | 2020-02-05 | 2020-03-02 | COMP | 2020-03-03 | NOTN | 2020-03-03 | COMP | 2021-04-24 | INPR | 2020-04-21 | COMP | Other | 31 | 41 |  | 2 |  |  | 124
16066 | 2019-10-22 | 2019-12-07 | 2020-03-11 | 2020-03-11 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-08-06 | COMP | Rule 16 | 31 | 64 | 85 | 1 | 1 | 22 | 200
16119 | 2019-10-22 | 2019-12-10 | 2020-01-29 | 2020-01-29 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-06-09 | COMP | 2020-07-17 | COMP | Rule 16 | 33 | 34 | 92 | 1 | 2 | 29 | 186
16235 | 2019-10-22 | 2019-12-17 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-19 | NOTN | 2020-06-18 | COMP | 2020-06-30 | COMP | 2020-07-22 | COMP | Other | 38 | 107 |  | 22 | 9 | 17 | 189
16263 | 2019-10-22 | 2019-12-18 | 2020-02-11 | 2020-02-12 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2020-08-04 | COMP | 2020-10-01 | COMP | Rule 16 | 39 | 37 | 36 | 1 | 88 | 42 | 239
16379 | 2019-10-22 | 2019-12-23 | 2020-06-13 | 2020-12-04 | COMP | 2020-12-14 | COMP | 2021-01-22 | COMP | 2021-01-25 | COMP | 2021-02-23 | COMP | Rule 16 | 42 | 120 | 7 | 27 | 2 | 21 | 335
16678 | 2019-10-22 | 2020-01-11 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-05 | COMP | 2020-08-17 | COMP | 2020-10-06 | COMP | 2021-01-14 | COMP | Rule 16 | 54 | 98 | 5 | 52 | 36 | 68 | 309
16681 | 2019-10-22 | 2020-01-10 | 2020-07-01 | 2020-07-01 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-10-01 | COMP | 2021-02-15 | COMP | Rule 16 | 54 | 121 | 57 | 1 | 10 | 91 | 329
16772 | 2019-10-22 | 2020-01-15 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-09 | COMP | 2020-05-21 | COMP | 2020-06-15 | COMP | 2020-08-07 | COMP | Rule 16 | 57 | 50 | 11 | 31 | 17 | 40 | 201
17373 | 2019-10-22 | 2020-02-12 | 2020-07-17 | 2020-07-17 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2020-10-30 | COMP | 2020-12-07 | COMP | Rule 16 | 76 | 111 | 58 | 1 | 18 | 24 | 283
17570 | 2019-10-22 | 2020-02-20 | 2020-02-22 | 2020-02-22 | COMP | 2020-02-21 | NOTN | 2020-02-22 | COMP | 2020-03-27 | NOTN | 2020-04-30 | COMP | Rule 16 | 81 | 2 |  | 0 |  |  | 131
18538 | 2019-10-22 | 2020-03-28 | 2020-05-23 | 2020-05-23 | COMP | 2020-07-10 | COMP | 2020-09-03 | COMP | 2020-08-11 | COMP | 2020-10-28 | COMP | Rule 16 | 107 | 40 | 34 | 40 | 0 | 39 | 258
18866 | 2019-10-22 | 2020-04-09 | 2020-08-13 | 2020-08-13 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-09-15 | COMP | 2020-10-22 | COMP | Rule 16 | 116 | 90 | 28 | 1 | 0 | 23 | 254
19145 | 2019-10-22 | 2020-04-22 | 2020-05-11 | 2020-05-11 | COMP | 2020-08-26 | COMP | 2020-09-22 | COMP | 2021-05-10 | COMP | 2021-06-21 | COMP | Rule 16 | 125 | 14 | 77 | 19 | 158 | 30 | 418
19423 | 2019-10-22 | 2020-05-06 | 2020-06-17 | 2020-06-17 | COMP | 2020-11-12 | COMP | 2021-03-23 | COMP | 2022-08-19 | COMP | 2022-11-16 | COMP | Rule 16 | 135 | 30 | 105 | 88 | 358 | 62 | 773
19779 | 2019-10-22 | 2020-05-22 | 2020-07-07 | 2022-05-17 | COMP | 2022-05-18 | NOTN | 2022-07-15 | COMP | 2022-07-18 | COMP | 2023-04-20 | COMP | Other | 147 | 32 |  | 41 | 2 | 191 | 878
19929 | 2019-10-22 | 2020-05-28 | 2020-07-30 | 2020-07-30 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2021-03-23 | COMP | 2021-05-04 | COMP | Rule 16 | 150 | 46 | 71 | 1 | 91 | 31 | 385
15505 | 2019-10-23 | 2019-11-05 | 2019-12-17 | 2019-12-17 | COMP | 2019-12-18 | NOTN | 2019-12-18 | COMP | 2019-12-19 | COMP | 2020-01-22 | COMP | Other | 10 | 28 |  | 2 | 2 | 22 | 60
15524 | 2019-10-23 | 2019-11-05 | 2020-04-21 | 2020-04-21 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-22 | COMP | 2020-08-05 | COMP | Rule 16 | 10 | 114 | 37 | 1 | 8 | 33 | 198
15531 | 2019-10-23 | 2019-11-08 | 2020-03-05 | 2020-03-05 | COMP | 2019-11-08 | NOTN | 2020-03-05 | COMP | 2022-01-30 | INPR | 2020-06-05 | COMP | Other | 13 | 78 |  | 1 |  |  | 155
15570 | 2019-10-23 | 2019-11-07 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-08 | COMP | 2020-12-31 | COMP | 2021-01-05 | COMP | 2021-02-05 | COMP | Rule 15/16 | 12 | 103 | 23 | 164 | 3 | 23 | 323
15623 | 2019-10-23 | 2019-11-12 | 2020-03-22 | 2020-03-22 | COMP | 2021-03-22 | COMP | 2023-01-04 | COMP | 2022-12-22 | COMP | 2023-03-28 | COMP | Rule 15/16 | 14 | 88 | 252 | 451 | 0 | 58 | 860
15693 | 2019-10-23 | 2019-11-15 | 2019-12-26 | 2019-12-26 | COMP | 2020-01-08 | COMP | 2020-01-22 | COMP | 2021-06-04 | COMP | 2021-08-13 | COMP | Rule 16 | 17 | 27 | 9 | 10 | 347 | 50 | 455
15742 | 2019-10-23 | 2019-11-20 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-03 | COMP | 2020-07-24 | COMP | 2020-07-07 | COMP | 2020-11-10 | COMP | Rule 16 | 20 | 89 | 4 | 80 | 0 | 77 | 266
15813 | 2019-10-23 | 2019-11-21 | 2020-01-28 | 2020-01-28 | COMP | 2020-06-29 | COMP | 2020-08-21 | COMP | 2020-09-03 | COMP | 2020-11-09 | COMP | Rule 16 | 21 | 44 | 108 | 40 | 10 | 47 | 265
15912 | 2019-10-23 | 2019-11-27 | 2020-12-08 | 2021-09-08 | COMP | 2021-09-23 | COMP | 2021-10-05 | COMP | 2021-07-28 | COMP | 2021-12-02 | COMP | Rule 15/16 | 25 | 259 | 12 | 9 | 0 | 40 | 530
15953 | 2019-10-23 | 2019-12-02 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-10 | COMP | 2020-06-11 | COMP | 2021-08-17 | COMP | 2021-11-10 | COMP | Rule 15/16 | 26 | 105 | 29 | 2 | 299 | 61 | 517
16193 | 2019-10-23 | 2019-12-13 | 2020-04-02 | 2020-04-02 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-08-21 | COMP | 2020-09-15 | COMP | Rule 16 | 35 | 76 | 78 | 1 | 24 | 17 | 226
16251 | 2019-10-23 | 2019-12-17 | 2020-12-21 | 2020-12-21 | COMP | 2021-01-05 | COMP | 2021-01-13 | COMP | 2021-02-02 | COMP | 2021-02-20 | COMP | Rule 16 | 37 | 256 | 10 | 7 | 14 | 13 | 332
16252 | 2019-10-23 | 2019-12-17 | 2021-03-05 | 2021-03-05 | COMP | 2021-03-12 | COMP | 2021-05-13 | COMP | 2021-05-14 | COMP | 2021-05-18 | COMP | Rule 16 | 37 | 306 | 6 | 45 | 2 | 3 | 394
16265 | 2019-10-23 | 2019-12-18 | 2020-02-26 | 2020-02-26 | COMP | 2020-06-11 | COMP | 2020-07-28 | COMP | 2021-06-08 | COMP | 2021-08-11 | COMP | Rule 16 | 38 | 47 | 76 | 34 | 217 | 46 | 453
16284 | 2019-10-23 | 2019-12-19 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-11 | COMP | 2020-03-02 | COMP | 2020-05-11 | COMP | 2020-06-15 | COMP | Rule 16 | 39 | 29 | 7 | 14 | 51 | 25 | 161
16291 | 2019-10-23 | 2019-12-19 | 2020-01-22 | 2020-01-22 | COMP | 2020-01-23 | NOTN | 2020-01-23 | COMP | 2021-02-27 | INPR | 2020-02-04 | COMP | Rule 16 | 39 | 22 |  | 2 |  |  | 69
16344 | 2019-10-23 | 2019-12-23 | 2020-03-17 | 2020-03-17 | COMP | 2020-03-18 | NOTN | 2020-04-17 | COMP | 2020-04-27 | NOTN | 2020-06-10 | COMP | Other | 41 | 58 |  | 24 |  |  | 158
16460 | 2019-10-23 | 2019-12-31 | 2020-06-17 | 2020-06-17 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2021-05-18 | COMP | 2021-06-17 | COMP | Rule 15/16 | 46 | 118 | 89 | 1 | 144 | 22 | 415
16515 | 2019-10-23 | 2020-01-07 | 2020-04-07 | 2020-04-07 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-12-11 | COMP | 2021-02-16 | COMP | Rule 16 | 50 | 64 | 104 | 1 | 71 | 44 | 329
16965 | 2019-10-23 | 2020-01-27 | 2020-03-23 | 2020-03-23 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-05-08 | COMP | 2020-06-24 | COMP | Rule 16 | 63 | 40 | 4 | 1 | 32 | 33 | 168
17123 | 2019-10-23 | 2020-01-31 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-01 | COMP | 2020-06-01 | COMP | 2020-05-01 | COMP | 2020-06-19 | COMP | Rule 16 | 67 | 56 | 10 | 21 | 0 | 15 | 165
17163 | 2019-10-23 | 2020-02-03 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-11 | COMP | 2020-07-16 | COMP | 2020-07-15 | COMP | 2023-06-03 | COMP | Rule 16 | 68 | 40 | 31 | 48 | 0 | 724 | 907
17441 | 2019-10-23 | 2020-02-13 | 2020-05-29 | 2020-05-29 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2020-12-01 | COMP | 2021-03-04 | COMP | Rule 16 | 76 | 75 | 103 | 1 | 27 | 64 | 341
17511 | 2019-10-23 | 2020-02-19 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-06-16 | COMP | 2020-06-26 | COMP | Rule 16 | 79 | 40 | 12 | 1 | 34 | 9 | 170
18130 | 2019-10-23 | 2020-03-11 | 2020-05-12 | 2020-07-21 | COMP | 2020-08-06 | COMP | 2020-06-19 | COMP | 2020-08-06 | COMP | 2020-09-19 | COMP | Rule 16 | 94 | 45 | 13 |  | 35 | 31 | 229
18429 | 2019-10-23 | 2020-03-24 | 2020-10-01 | 2021-11-18 | COMP | 2021-12-08 | COMP | 2021-12-15 | COMP | 2022-01-04 | COMP | 2022-02-24 | COMP | Rule 15/16 | 103 | 136 | 13 | 6 | 15 | 36 | 588
18895 | 2019-10-23 | 2020-04-10 | 2020-11-07 | 2020-11-07 | COMP | 2021-08-03 | COMP | 2021-08-30 | COMP | 2022-02-16 | COMP | 2022-03-16 | COMP | Rule 16 | 116 | 149 | 183 | 20 | 118 | 20 | 602
18966 | 2019-10-23 | 2020-04-14 | 2020-06-18 | 2020-06-18 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2020-10-05 | COMP | 2020-11-18 | COMP | Other | 118 | 47 | 65 | 1 | 13 | 32 | 271
19033 | 2019-10-23 | 2020-04-17 | 2022-04-27 | 2022-04-27 | COMP | 2022-06-09 | COMP | 2022-09-22 | COMP |  | INPR | 2023-08-05 | COMP | Rule 15/16 | 121 | 512 | 31 | 73 |  |  | 950
19968 | 2019-10-23 | 2020-05-29 | 2021-02-25 | 2021-02-25 | COMP | 2021-03-19 | COMP | 2021-06-21 | COMP | 2021-06-22 | COMP | 2021-08-25 | COMP | Rule 16 | 150 | 187 | 17 | 66 | 2 | 46 | 463
20490 | 2019-10-23 | 2020-06-23 | 2021-05-20 | 2022-03-03 | COMP | 2022-03-10 | COMP | 2022-03-31 | COMP | 2022-04-12 | COMP | 2022-04-26 | COMP | Rule 15/16 | 167 | 230 | 6 | 16 | 9 | 11 | 631
15306 | 2019-10-24 | 2019-10-25 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-18 | COMP | 2020-03-17 | COMP | 2020-06-18 | COMP | 2020-07-21 | COMP | Rule 16 | 2 | 60 | 17 | 21 | 67 | 24 | 186
15394 | 2019-10-24 | 2019-10-30 | 2019-12-22 | 2019-12-22 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2020-04-15 | COMP | 2020-04-27 | COMP | Rule 16 | 5 | 35 | 58 | 1 | 22 | 9 | 126
15529 | 2019-10-24 | 2019-11-05 | 2020-03-19 | 2020-03-19 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | 2020-05-13 | COMP | Rule 16 | 9 | 91 | 9 | 1 | 2 | 31 | 138
15541 | 2019-10-24 | 2019-11-06 | 2020-02-26 | 2020-04-29 | COMP | 2020-03-19 | NOTN | 2020-04-29 | COMP | 2020-04-29 | COMP | 2020-06-08 | COMP | Other | 10 | 74 |  | 1 | 1 | 28 | 155
15558 | 2019-10-24 | 2019-11-06 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-22 | COMP | 2020-09-16 | COMP | Rule 16 | 10 | 135 | 12 | 1 | 33 | 40 | 226
15618 | 2019-10-24 | 2019-11-13 | 2020-01-02 | 2020-01-02 | COMP | 2020-01-29 | COMP | 2020-03-12 | COMP | 2020-03-02 | COMP | 2020-03-11 | COMP | Rule 16 | 14 | 33 | 19 | 31 | 0 |  | 93
15697 | 2019-10-24 | 2019-11-16 | 2020-04-07 | 2020-04-07 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-04-29 | COMP | 2020-06-23 | COMP | Rule 16 | 16 | 96 | 6 | 1 | 12 | 39 | 166
15763 | 2019-10-24 | 2019-11-20 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-28 | COMP | 2020-03-31 | COMP | 2020-03-23 | COMP | 2020-04-24 | COMP | Rule 16 | 19 | 51 | 17 | 23 | 0 | 19 | 125
15766 | 2019-10-24 | 2019-11-20 | 2020-01-22 | 2020-01-22 | COMP | 2020-04-27 | COMP | 2020-02-04 | COMP | 2020-06-09 | COMP | 2020-06-13 | COMP | Rule 16 | 19 | 41 | 68 |  | 89 | 4 | 159
15780 | 2019-10-24 | 2019-11-21 | 2020-01-15 | 2020-01-15 | COMP | 2020-03-09 | COMP | 2020-06-03 | COMP | 2020-05-27 | COMP | 2020-07-13 | COMP | Rule 16 | 20 | 36 | 37 | 62 | 0 | 29 | 180
15787 | 2019-10-24 | 2019-11-21 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-05-04 | COMP | 2020-07-07 | COMP | Rule 16 | 20 | 68 | 7 | 1 | 39 | 46 | 176
15806 | 2019-10-24 | 2019-11-20 | 2019-12-13 | 2019-12-13 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2019-12-19 | COMP | 2020-01-25 | COMP | Rule 16 | 19 | 16 | 5 | 1 | 1 | 24 | 61
15999 | 2019-10-24 | 2019-12-05 | 2020-03-27 | 2020-03-27 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2021-04-30 | COMP | 2021-08-06 | COMP | Rule 16 | 28 | 78 | 137 | 1 | 141 | 69 | 449
16018 | 2019-10-24 | 2019-12-05 | 2020-05-04 | 2020-05-04 | COMP | 2021-04-08 | COMP | 2021-04-23 | COMP | 2021-05-15 | COMP | 2021-07-23 | COMP | Other | 28 | 104 | 235 | 12 | 16 | 48 | 439
16019 | 2019-10-24 | 2019-12-05 | 2020-05-03 | 2020-05-03 | COMP | 2021-01-20 | COMP | 2021-05-22 | COMP | 2021-05-03 | COMP | 2021-07-27 | COMP | Other | 28 | 103 | 180 | 87 | 0 | 45 | 441
16123 | 2019-10-24 | 2019-12-10 | 2020-08-02 | 2020-08-02 | COMP | 2020-10-21 | COMP | 2020-11-12 | COMP | 2021-02-23 | COMP | 2021-04-23 | COMP | Rule 15/16 | 31 | 164 | 57 | 16 | 68 | 44 | 376
16162 | 2019-10-24 | 2019-12-12 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-03-02 | COMP | 2020-03-13 | COMP | Rule 16 | 33 | 29 | 11 | 1 | 16 | 10 | 95
16196 | 2019-10-24 | 2019-12-13 | 2020-03-25 | 2020-09-28 | COMP | 2020-11-24 | COMP | 2020-11-24 | COMP | 2021-01-14 | COMP | 2021-02-27 | COMP | Rule 16 | 34 | 70 | 41 | 1 | 34 | 30 | 336
16331 | 2019-10-24 | 2019-12-20 | 2020-05-20 | 2020-05-20 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2020-08-03 | COMP | 2020-08-20 | COMP | Rule 16 | 39 | 105 | 51 | 1 | 3 | 14 | 208
16365 | 2019-10-24 | 2019-12-23 | 2020-06-17 | 2020-06-17 | COMP | 2020-10-19 | COMP | 2022-03-31 | COMP | 2022-03-29 | COMP | 2022-06-11 | COMP | Rule 15/16 | 40 | 123 | 88 | 364 | 0 | 51 | 662
16638 | 2019-10-24 | 2020-01-09 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2021-10-23 | INPR | 2020-08-06 | COMP | Rule 16 | 51 | 65 | 11 | 1 |  |  | 198
16670 | 2019-10-24 | 2020-01-10 | 2020-05-07 | 2020-05-07 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-08-18 | COMP | 2020-09-30 | COMP | Rule 16 | 52 | 83 | 38 | 1 | 36 | 31 | 236
17072 | 2019-10-24 | 2020-01-29 | 2020-03-06 | 2020-03-06 | COMP | 2020-03-18 | COMP | 2020-03-20 | COMP | 2020-04-13 | COMP | 2020-04-21 | COMP | Rule 16 | 64 | 27 | 9 | 3 | 17 | 7 | 122
17211 | 2019-10-24 | 2020-02-04 | 2020-07-15 | 2020-07-15 | COMP | 2020-07-21 | COMP | 2020-07-30 | COMP | 2020-09-16 | COMP | 2020-09-30 | COMP | Rule 16 | 68 | 115 | 5 | 8 | 34 | 11 | 236
17601 | 2019-10-24 | 2020-02-21 | 2020-07-08 | 2020-07-08 | COMP | 2020-12-04 | COMP | 2021-03-05 | COMP | 2020-12-31 | COMP | 2021-03-31 | COMP | Rule 15/16 | 80 | 98 | 104 | 62 | 0 | 19 | 359
17671 | 2019-10-24 | 2020-02-24 | 2020-10-12 | 2020-10-12 | COMP | 2020-10-27 | COMP | 2020-12-15 | COMP | 2021-01-25 | COMP | 2021-02-04 | COMP | Rule 16 | 81 | 164 | 12 | 33 | 27 | 9 | 321
18177 | 2019-10-24 | 2020-03-13 | 2020-06-22 | 2020-08-28 | COMP | 2020-09-30 | COMP | 2020-10-03 | COMP | 2020-11-24 | COMP | 2021-01-25 | COMP | Rule 16 | 95 | 71 | 23 | 3 | 36 | 40 | 313
22472 | 2019-10-24 | 2020-09-25 | 2021-01-11 | 2021-01-11 | COMP | 2021-02-10 | COMP | 2021-04-06 | COMP | 2021-04-20 | COMP | 2021-05-19 | COMP | Rule 15/16 | 233 | 72 | 22 | 39 | 11 | 22 | 394
15327 | 2019-10-25 | 2019-10-25 | 2019-11-15 | 2019-11-15 | COMP | 2019-12-17 | COMP | 2019-12-17 | COMP | 2020-08-17 | COMP | 2020-09-29 | COMP | Rule 16 | 1 | 15 | 21 | 1 | 170 | 31 | 234
15337 | 2019-10-25 | 2019-10-26 | 2020-04-22 | 2020-04-22 | COMP |  | INPR |  | REQD |  | REQD | 2021-07-12 | COMP | Rule 16 | 1 | 121 |  |  |  |  | 429
15753 | 2019-10-25 | 2019-11-20 | 2020-03-01 | 2020-03-02 | COMP | 2020-04-03 | COMP | 2020-04-03 | COMP | 2020-04-04 | COMP | 2020-04-15 | COMP | Rule 16 | 18 | 67 | 25 | 1 | 1 | 8 | 117
15786 | 2019-10-25 | 2019-11-21 | 2020-01-21 | 2020-01-21 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-03-03 | COMP | 2020-07-23 | COMP | Rule 16 | 19 | 39 | 15 | 1 | 16 | 102 | 187
15869 | 2019-10-25 | 2019-11-26 | 2020-03-23 | 2022-12-26 | COMP | 2024-02-13 | COMP | 2020-09-24 | COMP | 2022-12-16 | COMP | 2023-03-28 | COMP | Rule 16 | 22 | 79 | 283 |  | 560 | 69 | 858
15885 | 2019-10-25 | 2019-11-25 | 2020-09-06 | 2020-09-06 | COMP | 2020-09-07 | NOTN | 2020-10-02 | COMP | 2020-10-06 | COMP | 2020-11-17 | COMP | Other | 21 | 198 |  | 19 | 3 | 30 | 268
16007 | 2019-10-25 | 2019-12-06 | 2020-04-05 | 2020-04-05 | COMP | 2020-05-04 | COMP | 2020-05-05 | COMP | 2020-05-23 | COMP | 2020-06-19 | COMP | Rule 16 | 28 | 82 | 21 | 2 | 14 | 19 | 163
16404 | 2019-10-25 | 2019-12-27 | 2020-09-22 | 2022-02-22 | COMP | 2022-03-21 | COMP | 2022-04-04 | COMP | 2022-03-28 | COMP | 2022-06-11 | COMP | Rule 15/16 | 42 | 188 | 20 | 11 | 0 | 49 | 661
16405 | 2019-10-25 | 2019-12-27 | 2020-09-22 | 2022-02-22 | COMP | 2022-03-01 | COMP | 2023-05-16 | COMP | 2023-05-12 | COMP | 2023-06-20 | COMP | Rule 16 | 42 | 188 | 6 | 305 | 0 | 24 | 916
16406 | 2019-10-25 | 2019-12-27 | 2020-09-22 | 2022-02-22 | COMP | 2022-03-01 | COMP | 2023-06-07 | COMP | 2023-06-13 | COMP | 2023-06-20 | COMP | Rule 16 | 42 | 188 | 6 | 320 | 5 | 5 | 916
16407 | 2019-10-25 | 2019-12-27 | 2020-09-22 | 2022-02-22 | COMP | 2022-03-03 | COMP | 2023-08-22 | COMP | 2023-09-05 | COMP | 2023-10-11 | COMP | Rule 16 | 42 | 188 | 8 | 370 | 10 | 27 | 995
16408 | 2019-10-25 | 2019-12-27 | 2020-09-22 | 2022-02-22 | COMP | 2022-03-01 | COMP | 2023-04-04 | COMP | 2023-11-01 | COMP | 2023-12-01 | COMP | Rule 16 | 42 | 188 | 6 | 275 | 148 | 20 | 1029
17093 | 2019-10-25 | 2020-01-30 | 2020-03-30 | 2020-03-30 | COMP | 2020-04-13 | COMP | 2020-07-29 | COMP | 2020-10-12 | COMP | 2020-12-09 | COMP | Rule 16 | 64 | 42 | 11 | 77 | 53 | 40 | 282
17958 | 2019-10-25 | 2020-03-05 | 2020-05-27 | 2020-05-27 | COMP | 2020-10-20 | COMP | 2021-08-19 | COMP | 2020-06-19 | COMP | 2022-02-23 | COMP | Rule 16 | 88 | 59 | 104 | 209 | 0 | 129 | 585
18035 | 2019-10-25 | 2020-03-09 | 2020-04-20 | 2020-04-20 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-10-06 | COMP | 2020-11-04 | COMP | Rule 16 | 90 | 31 | 32 | 1 | 89 | 22 | 260
19603 | 2019-10-25 | 2020-05-14 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-09 | COMP | 2020-06-16 | NOTN | 2020-06-06 | COMP | 2020-06-18 | COMP | Rule 16 | 138 | 13 | 6 |  |  |  | 162
32870 | 2019-10-25 | 2021-12-06 | 2021-12-17 | 2021-12-17 | COMP | 2022-01-25 | COMP | 2022-01-25 | COMP | 2023-11-01 | COMP | 2023-12-01 | COMP | Rule 16 | 530 | 10 | 27 | 1 | 446 | 20 | 1029
32871 | 2019-10-25 | 2021-12-06 | 2021-12-17 | 2021-12-17 | COMP | 2022-08-26 | COMP | 2022-08-26 | COMP | 2023-11-07 | COMP | 2023-12-01 | COMP | Rule 16 | 530 | 10 | 176 | 1 | 301 | 16 | 1029
32872 | 2019-10-25 | 2021-12-06 | 2021-12-17 | 2021-12-17 | COMP | 2022-08-26 | COMP | 2022-08-26 | COMP | 2023-11-04 | COMP | 2023-02-01 | COMP | Rule 16 | 530 | 10 | 176 | 1 | 299 |  | 820
32873 | 2019-10-25 | 2021-12-06 | 2021-12-17 | 2021-12-17 | COMP | 2022-08-26 | COMP | 2022-08-26 | COMP | 2023-11-04 | COMP | 2023-02-01 | COMP | Rule 16 | 530 | 10 | 176 | 1 | 299 |  | 820
32874 | 2019-10-25 | 2021-12-06 | 2021-12-17 | 2021-12-17 | COMP | 2022-08-26 | COMP | 2022-08-26 | COMP | 2022-08-26 | COMP | 2022-09-11 | COMP | Rule 16 | 530 | 10 | 176 | 1 | 1 | 10 | 723
32875 | 2019-10-25 | 2021-12-06 | 2021-12-17 | 2021-12-17 | COMP | 2022-08-26 | COMP | 2022-08-26 | COMP | 2022-08-26 | COMP | 2022-09-11 | COMP | Rule 16 | 530 | 10 | 176 | 1 | 1 | 10 | 723
32876 | 2019-10-25 | 2021-12-06 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2022-12-13 | COMP | 2023-02-14 | COMP | Rule 16 | 530 | 55 | 23 | 1 | 182 | 43 | 829
32880 | 2019-10-25 | 2021-12-06 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2024-03-04 | INPR | 2023-02-14 | COMP | Rule 16 | 530 | 55 | 23 | 1 |  |  | 829
32881 | 2019-10-25 | 2021-12-06 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-21 | COMP | 2022-03-21 | COMP | 2024-03-04 | INPR | 2023-02-14 | COMP | Rule 16 | 530 | 55 | 20 | 1 |  |  | 829
32894 | 2019-10-25 | 2021-12-06 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-21 | COMP | 2022-03-21 | COMP | 2023-11-01 | COMP | 2023-11-30 | COMP | Rule 16 | 530 | 55 | 20 | 1 | 408 | 19 | 1028
32895 | 2019-10-25 | 2021-12-06 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-21 | COMP | 2022-03-21 | COMP | 2023-11-01 | COMP | 2023-11-30 | COMP | Rule 16 | 530 | 55 | 20 | 1 | 408 | 19 | 1028
32896 | 2019-10-25 | 2021-12-06 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2023-12-08 | COMP | 2023-02-01 | COMP | Rule 16 | 530 | 55 | 23 | 1 | 429 |  | 820
32897 | 2019-10-25 | 2021-12-06 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2022-11-29 | COMP | 2022-12-05 | COMP | Rule 16 | 530 | 55 | 23 | 1 | 172 | 5 | 781
32922 | 2019-10-25 | 2021-12-07 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-21 | COMP | 2022-03-21 | COMP | 2022-11-29 | COMP | 2022-12-05 | COMP | Rule 16 | 531 | 54 | 20 | 1 | 175 | 5 | 781
32923 | 2019-10-25 | 2021-12-07 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-21 | COMP | 2022-03-21 | COMP | 2022-11-29 | COMP | 2022-12-05 | COMP | Rule 16 | 531 | 54 | 20 | 1 | 175 | 5 | 781
32924 | 2019-10-25 | 2021-12-07 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2022-05-24 | COMP | 2022-07-05 | COMP | Rule 16 | 531 | 54 | 23 | 1 | 44 | 28 | 676
32926 | 2019-10-25 | 2021-12-07 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2022-10-14 | COMP | 2022-12-05 | COMP | Rule 16 | 531 | 54 | 23 | 1 | 143 | 34 | 781
32927 | 2019-10-25 | 2021-12-07 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2023-08-31 | COMP | 2023-10-11 | COMP | Rule 16 | 531 | 54 | 23 | 1 | 362 | 29 | 995
32928 | 2019-10-25 | 2021-12-07 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2023-09-16 | COMP | 2023-10-11 | COMP | Rule 16 | 531 | 54 | 23 | 1 | 372 | 18 | 995
32929 | 2019-10-25 | 2021-12-07 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2024-01-30 | COMP | 2023-02-01 | COMP | Rule 16 | 531 | 54 | 23 | 1 | 463 |  | 820
33519 | 2019-10-25 | 2022-01-03 | 2022-02-22 | 2022-02-22 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP | 2023-06-14 | COMP | 2023-08-04 | COMP | Rule 16 | 550 | 35 | 23 | 1 | 308 | 36 | 948
33520 | 2019-10-25 | 2022-01-03 | 2022-02-23 | 2022-02-23 | COMP | 2022-03-24 | COMP | 2022-03-24 | COMP |  | INPR | 2022-08-16 | COMP | Rule 16 | 550 | 36 | 22 | 1 |  |  | 706
33521 | 2019-10-25 | 2022-01-03 | 2022-02-23 | 2022-02-23 | COMP | 2022-03-24 | COMP | 2022-03-24 | INPR |  | REQD | 2022-08-16 | COMP | Rule 16 | 550 | 36 | 22 |  |  |  | 706
15359 | 2019-10-26 | 2019-10-29 | 2020-02-12 | 2020-02-12 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2021-09-21 | COMP | 2021-12-03 | COMP | Rule 16 | 2 | 71 | 101 | 1 | 307 | 51 | 528
17619 | 2019-10-26 | 2020-02-21 | 2020-11-12 | 2021-02-22 | COMP | 2021-04-22 | COMP | 2021-05-23 | COMP | 2023-12-03 | INPR | 2021-05-26 | COMP | Rule 16 | 78 | 187 | 44 | 22 |  |  | 397
18734 | 2019-10-26 | 2020-04-07 | 2020-09-23 | 2020-09-23 | COMP | 2020-10-05 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2020-12-07 | COMP | Rule 16 | 110 | 120 | 9 | 14 | 1 | 30 | 279
18735 | 2019-10-26 | 2020-04-07 | 2020-09-13 | 2020-09-28 | COMP | 2020-10-02 | COMP | 2020-11-23 | COMP | 2022-01-30 | INPR | 2020-12-22 | COMP | Rule 16 | 110 | 112 | 5 | 36 |  |  | 290
15548 | 2019-10-27 | 2019-11-06 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-10 | COMP | 2020-04-20 | COMP | 2020-04-17 | COMP | 2020-04-29 | COMP | Rule 16 | 8 | 75 | 9 | 30 | 0 | 8 | 126
15931 | 2019-10-27 | 2019-12-02 | 2020-03-27 | 2020-03-27 | COMP | 2020-04-01 | COMP | 2021-04-21 | COMP | 2021-04-30 | COMP | 2021-06-09 | COMP | Rule 16 | 23 | 81 | 4 | 267 | 8 | 28 | 406
16660 | 2019-10-27 | 2020-01-10 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-21 | COMP | 2020-04-30 | COMP | 2020-03-02 | COMP | 2020-05-09 | COMP | Rule 15/16 | 50 | 24 | 6 | 50 | 0 | 7 | 133
17260 | 2019-10-27 | 2020-02-06 | 2020-05-19 | 2020-08-05 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2021-04-01 | COMP | 2021-05-21 | COMP | Rule 16 | 68 | 73 | 13 | 1 | 152 | 37 | 394
15648 | 2019-10-28 | 2019-11-13 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-14 | COMP | 2020-03-10 | COMP | 2020-10-19 | COMP | 2020-11-03 | COMP | Rule 15/16 | 12 | 43 | 21 | 17 | 158 | 12 | 258
15722 | 2019-10-28 | 2019-11-19 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-21 | COMP | 2020-01-21 | COMP | 2020-03-19 | COMP | 2020-03-30 | COMP | Rule 16 | 16 | 33 | 9 | 1 | 42 | 8 | 104
15764 | 2019-10-28 | 2019-11-20 | 2020-03-07 | 2020-03-07 | COMP | 2020-04-13 | COMP | 2020-05-11 | COMP | 2021-01-07 | COMP | 2021-02-10 | COMP | Rule 16 | 17 | 72 | 26 | 21 | 167 | 24 | 323
15870 | 2019-10-28 | 2019-11-26 | 2020-03-23 | 2020-04-14 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-07-22 | COMP | 2020-09-01 | COMP | Rule 16 | 21 | 79 | 68 | 1 | 4 | 30 | 214
15898 | 2019-10-28 | 2019-11-27 | 2020-03-28 | 2021-02-01 | COMP | 2021-02-16 | COMP | 2021-04-23 | COMP | 2021-04-28 | COMP | 2021-05-25 | COMP | Rule 16 | 22 | 82 | 11 | 49 | 4 | 20 | 396
16223 | 2019-10-28 | 2019-12-17 | 2020-04-08 | 2020-04-08 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-07-08 | COMP | 2020-07-28 | COMP | Rule 16 | 34 | 78 | 59 | 1 | 7 | 15 | 189
16358 | 2019-10-28 | 2019-12-23 | 2020-04-17 | 2020-04-17 | COMP | 2020-05-28 | COMP | 2020-09-08 | COMP | 2020-09-11 | COMP | 2021-02-16 | COMP | Rule 16 | 38 | 81 | 29 | 73 | 4 | 106 | 326
16396 | 2019-10-28 | 2019-12-26 | 2020-04-09 | 2020-04-09 | COMP | 2020-06-17 | COMP | 2022-05-24 | COMP | 2022-05-23 | COMP | 2022-07-22 | COMP | Rule 16 | 40 | 73 | 49 | 489 | 0 | 41 | 688
16463 | 2019-10-28 | 2020-01-02 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-07-15 | COMP | 2020-08-25 | COMP | Rule 16 | 44 | 11 | 12 | 1 | 116 | 30 | 209
16697 | 2019-10-28 | 2020-01-13 | 2020-04-30 | 2020-04-30 | COMP | 2022-06-02 | COMP | 2022-06-02 | COMP | 2022-08-05 | COMP | 2022-09-02 | COMP | Rule 16 | 51 | 77 | 528 | 1 | 45 | 21 | 718
16732 | 2019-10-28 | 2020-01-13 | 2020-03-17 | 2020-03-17 | COMP | 2020-04-09 | COMP | 2020-04-10 | COMP | 2020-04-23 | COMP | 2020-06-04 | COMP | Rule 16 | 51 | 45 | 18 | 2 | 10 | 30 | 151
16899 | 2019-10-28 | 2020-01-22 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-23 | COMP | 2020-07-13 | COMP | Rule 16 | 57 | 87 | 7 | 1 | 15 | 15 | 178
17573 | 2019-10-28 | 2020-02-20 | 2020-03-15 | 2020-03-15 | COMP | 2020-03-13 | NOTN | 2020-04-24 | COMP | 2020-06-09 | COMP | 2020-07-07 | COMP | Rule 16 | 77 | 17 |  | 30 | 32 | 21 | 174
17675 | 2019-10-28 | 2020-02-25 | 2020-04-01 | 2020-04-01 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2021-08-10 | COMP | 2021-09-16 | COMP | Rule 16 | 80 | 27 | 102 | 1 | 243 | 27 | 475
17914 | 2019-10-28 | 2020-03-03 | 2020-04-26 | 2020-04-26 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-11-05 | COMP | 2020-12-01 | COMP | Rule 16 | 85 | 39 | 37 | 1 | 101 | 16 | 275
18720 | 2019-10-28 | 2020-04-04 | 2020-09-21 | 2020-09-21 | COMP | 2021-03-19 | COMP | 2021-03-19 | COMP | 2021-10-05 | COMP | 2021-10-04 | COMP | Rule 16 | 108 | 119 | 123 | 1 | 140 |  | 487
19468 | 2019-10-28 | 2020-05-09 | 2020-08-13 | 2020-08-13 | COMP | 2020-09-08 | COMP | 2020-09-24 | INPR |  | REQD | 2020-11-18 | COMP | Rule 15/16 | 133 | 68 | 18 |  |  |  | 268
19699 | 2019-10-28 | 2020-05-18 | 2020-07-22 | 2020-07-22 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-29 | COMP | 2020-09-09 | COMP | Rule 16 | 139 | 47 | 8 | 1 | 21 | 7 | 219
25890 | 2019-10-28 | 2021-03-01 | 2021-09-08 | 2021-09-08 | COMP | 2021-09-28 | COMP | 2021-09-29 | COMP | 2021-09-29 | COMP | 2021-11-16 | COMP | Rule 15/16 | 335 | 135 | 15 | 2 | 1 | 34 | 517
4248 | 2019-10-29 | 2019-10-31 | [7 empty] | 2019-11-14 | COMP | 2020-07-13 | COMP | Other | 3 | [5 empty] | 177
15514 | 2019-10-29 | 2019-11-05 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-06-22 | COMP | 2020-07-13 | COMP | Rule 16 | 6 | 96 | 32 | 1 | 31 | 16 | 177
15595 | 2019-10-29 | 2019-11-08 | 2020-03-03 | 2020-03-03 | COMP | 2020-04-22 | COMP | 2020-10-12 | COMP | 2020-11-06 | COMP | 2021-01-07 | COMP | Rule 15/16 | 9 | 76 | 37 | 122 | 20 | 40 | 299
15677 | 2019-10-29 | 2019-11-14 | 2020-02-08 | 2020-02-08 | COMP | 2020-02-26 | COMP | 2020-02-26 | COMP | 2020-04-28 | COMP | 2020-06-02 | COMP | Rule 16 | 12 | 57 | 12 | 1 | 45 | 25 | 148
15776 | 2019-10-29 | 2019-11-20 | 2020-04-13 | 2020-04-13 | COMP | 2020-11-13 | COMP | 2020-11-13 | COMP | 2021-02-16 | COMP | 2021-03-24 | COMP | Rule 16 | 16 | 98 | 152 | 1 | 62 | 27 | 351
15949 | 2019-10-29 | 2019-12-03 | 2020-04-08 | 2020-04-08 | COMP | 2020-06-03 | COMP | 2020-08-12 | COMP | 2022-07-16 | INPR | 2021-03-02 | COMP | Rule 15/16 | 23 | 88 | 40 | 51 |  |  | 335
15974 | 2019-10-29 | 2019-12-04 | 2019-12-28 | 2019-12-28 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2020-02-10 | COMP | 2020-03-02 | COMP | Rule 15/16 | 24 | 17 | 27 | 1 | 3 | 15 | 83
16022 | 2019-10-29 | 2019-12-05 | 2020-01-14 | 2020-01-14 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-10-17 | COMP | 2020-10-30 | COMP | Rule 16 | 25 | 27 | 148 | 1 | 48 | 10 | 255
16030 | 2019-10-29 | 2019-12-06 | 2020-01-15 | 2020-01-15 | COMP | 2021-08-23 | COMP | 2021-08-23 | COMP | 2021-09-14 | COMP | 2021-09-23 | COMP | Rule 16 | 26 | 27 | 406 | 1 | 16 | 8 | 479
16167 | 2019-10-29 | 2019-12-13 | 2020-06-22 | 2020-06-29 | COMP | 2020-08-11 | COMP | 2021-03-03 | COMP | 2021-03-23 | COMP | 2021-04-24 | COMP | Rule 15/16 | 31 | 132 | 32 | 139 | 15 | 24 | 373
16211 | 2019-10-29 | 2019-12-16 | 2020-03-30 | 2020-04-02 | COMP | 2020-05-19 | COMP | 2020-06-24 | COMP | 2020-08-10 | COMP | 2020-08-10 | COMP | Rule 15/16 | 32 | 72 | 34 | 26 | 34 | 1 | 197
16603 | 2019-10-29 | 2020-01-09 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-07 | COMP | 2020-05-15 | COMP | 2020-07-09 | COMP | 2020-08-07 | COMP | Rule 16 | 48 | 69 | 16 | 7 | 39 | 22 | 196
16950 | 2019-10-29 | 2020-01-24 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-06-02 | COMP | 2020-06-11 | COMP | Rule 16 | 58 | 43 | 9 | 1 | 41 | 8 | 155
17235 | 2019-10-29 | 2020-02-05 | 2020-07-08 | 2020-07-08 | COMP | 2020-07-16 | COMP | 2020-11-03 | COMP | 2021-07-07 | COMP | 2021-08-17 | COMP | Rule 16 | 66 | 109 | 7 | 78 | 168 | 30 | 453
17340 | 2019-10-29 | 2020-02-10 | 2020-05-05 | 2021-05-19 | COMP | 2021-05-24 | COMP | 2021-01-05 | COMP | 2021-04-12 | COMP | 2022-07-27 | COMP | Rule 15/16 | 69 | 61 | 4 |  | 68 | 327 | 690
17606 | 2019-10-29 | 2020-02-21 | 2020-05-21 | 2020-05-21 | COMP | 2020-05-26 | NOTN | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-07-20 | COMP | Other | 77 | 65 |  | 3 | 1 | 40 | 182
17821 | 2019-10-29 | 2020-02-28 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-10 | COMP | 2020-06-30 | COMP | Rule 16 | 82 | 39 | 9 | 1 | 27 | 15 | 168
17989 | 2019-10-29 | 2020-03-06 | 2020-05-15 | 2020-05-15 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2021-10-05 | COMP | 2021-10-20 | COMP | Other | 87 | 51 | 71 | 1 | 281 | 12 | 498
18225 | 2019-10-29 | 2020-03-16 | 2020-06-04 | 2020-06-04 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-10-20 | COMP | 2020-11-02 | COMP | Rule 15/16 | 93 | 58 | 59 | 1 | 40 | 10 | 256
19190 | 2019-10-29 | 2020-04-24 | 2020-10-08 | 2020-10-08 | COMP | 2020-10-20 | COMP | 2020-10-21 | COMP | 2021-01-11 | COMP | 2021-01-21 | COMP | Rule 16 | 122 | 118 | 9 | 2 | 54 | 8 | 308
23358 | 2019-10-29 | 2020-11-03 | 2021-02-26 | 2021-02-26 | COMP | 2021-03-08 | COMP | 2021-03-08 | COMP | 2021-04-27 | COMP | 2021-06-16 | COMP | Rule 16 | 257 | 77 | 7 | 1 | 37 | 36 | 410
15497 | 2019-10-30 | 2019-11-05 | 2020-03-23 | 2020-03-26 | COMP | 2020-04-29 | COMP | 2020-07-16 | COMP | 2020-07-17 | COMP | 2020-08-27 | COMP | Rule 15/16 | 5 | 93 | 25 | 56 | 2 | 30 | 209
15542 | 2019-10-30 | 2019-11-06 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-06 | COMP | 2020-07-17 | COMP | 2020-05-22 | COMP | 2020-07-29 | COMP | Rule 16 | 6 | 94 | 9 | 74 | 0 | 9 | 188
15552 | 2019-10-30 | 2019-11-06 | 2021-04-24 | 2021-04-24 | COMP | 2021-09-23 | COMP | 2021-09-23 | COMP | 2021-10-04 | COMP | 2021-12-04 | COMP | Rule 15/16 | 6 | 367 | 106 | 1 | 8 | 42 | 526
15785 | 2019-10-30 | 2019-11-21 | 2020-01-14 | 2020-01-14 | COMP | 2020-03-10 | COMP | 2020-03-10 | INPR |  | REQD | 2020-06-02 | COMP | Other | 16 | 35 | 39 |  |  |  | 147
16185 | 2019-10-30 | 2019-12-16 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-05-12 | COMP | 2020-06-15 | COMP | Rule 16 | 31 | 73 | 9 | 1 | 23 | 24 | 156
16424 | 2019-10-30 | 2019-12-30 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-08-25 | COMP | 2020-10-08 | COMP | Rule 15/16 | 40 | 100 | 10 | 1 | 60 | 32 | 238
16459 | 2019-10-30 | 2020-01-03 | 2020-06-03 | 2021-03-30 | COMP | 2021-04-14 | COMP | 2021-04-14 | COMP | 2021-05-03 | COMP | 2021-06-07 | COMP | Rule 16 | 43 | 106 | 12 | 1 | 14 | 25 | 402
16527 | 2019-10-30 | 2020-01-06 | 2020-05-14 | 2020-05-14 | COMP | 2020-06-17 | COMP | 2020-09-22 | COMP | 2020-10-06 | COMP | 2020-12-13 | COMP | Rule 15/16 | 44 | 92 | 24 | 69 | 11 | 46 | 281
16618 | 2019-10-30 | 2020-01-10 | 2020-08-17 | 2020-08-17 | COMP | 2020-11-13 | COMP | 2020-12-22 | COMP | 2020-12-23 | COMP | 2021-02-01 | COMP | Rule 15/16 | 48 | 154 | 63 | 26 | 2 | 26 | 314
16786 | 2019-10-30 | 2020-01-16 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-05-08 | COMP | 2020-06-23 | COMP | Rule 16 | 52 | 69 | 4 | 1 | 9 | 32 | 162
17250 | 2019-10-30 | 2020-02-06 | 2020-02-21 | 2020-02-26 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-04-10 | COMP | 2020-04-13 | COMP | Rule 16 | 66 | 11 | 6 | 1 | 28 | 2 | 112
17251 | 2019-10-30 | 2020-02-06 | 2020-02-13 | 2020-02-26 | COMP | 2020-03-04 | COMP | 2020-03-04 | COMP | 2020-04-10 | COMP | 2020-04-13 | COMP | Rule 16 | 66 | 6 | 6 | 1 | 28 | 2 | 112
17477 | 2019-10-30 | 2020-02-15 | 2020-12-11 | 2020-12-11 | COMP | 2021-07-28 | COMP | 2022-05-19 | COMP | 2022-04-26 | COMP | 2022-06-09 | COMP | Rule 15/16 | 72 | 209 | 158 | 206 | 0 | 15 | 657
17727 | 2019-10-30 | 2020-02-25 | 2020-03-26 | 2020-03-26 | COMP | 2020-06-13 | COMP | 2020-07-01 | COMP |  | INPR | 2020-08-20 | COMP | Other | 78 | 23 | 56 | 13 |  |  | 204
17752 | 2019-10-30 | 2020-02-26 | 2020-08-06 | 2020-08-06 | COMP | 2021-04-06 | COMP | 2021-04-06 | COMP | 2021-04-06 | COMP | 2021-05-10 | COMP | Rule 16 | 79 | 116 | 166 | 1 | 1 | 25 | 383
18290 | 2019-10-30 | 2020-03-18 | 2020-04-26 | 2020-04-26 | COMP | 2020-06-09 | COMP | 2020-07-08 | COMP | 2020-06-18 | COMP | 2020-07-24 | COMP | Rule 15/16 | 94 | 28 | 31 | 22 | 0 | 13 | 185
18369 | 2019-10-30 | 2020-03-20 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2021-12-21 | COMP | 2022-02-08 | COMP | Rule 16 | 96 | 65 | 21 | 1 | 359 | 35 | 572
19083 | 2019-10-30 | 2020-04-20 | 2020-08-26 | 2020-08-26 | COMP | 2021-04-21 | COMP | 2021-04-21 | COMP | 2023-01-06 | COMP | 2023-04-17 | COMP | Rule 16 | 117 | 92 | 163 | 1 | 431 | 70 | 869
19268 | 2019-10-30 | 2020-04-28 | 2020-08-18 | 2020-08-18 | COMP | 2020-09-02 | COMP | 2020-09-02 | COMP | 2022-01-31 | INPR | 2020-10-28 | COMP | Rule 16 | 123 | 80 | 12 | 1 |  |  | 252
19671 | 2019-10-30 | 2020-05-18 | 2020-06-30 | 2020-06-30 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2020-10-22 | COMP | 2020-11-13 | COMP | Rule 16 | 137 | 31 | 50 | 1 | 33 | 16 | 263
15587 | 2019-10-31 | 2019-11-08 | 2020-02-15 | 2020-02-15 | COMP | 2020-03-09 | COMP | 2020-03-10 | INPR | 2020-04-06 | COMP | 2020-04-09 | COMP | Rule 16 | 7 | 65 | 15 |  |  |  | 109
15762 | 2019-10-31 | 2019-11-20 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | 2020-04-06 | COMP | 2020-05-22 | COMP | Rule 16 | 14 | 41 | 14 | 1 | 40 | 35 | 140
15775 | 2019-10-31 | 2019-11-20 | 2020-03-22 | 2020-03-26 | COMP | 2020-03-27 | NOTN | 2020-03-27 | COMP | 2020-03-29 | COMP | 2020-06-16 | COMP | Other | 14 | 82 |  | 2 | 1 | 56 | 156
15811 | 2019-10-31 | 2019-11-21 | 2020-01-10 | 2020-01-10 | COMP | 2020-01-22 | COMP | 2020-02-24 | COMP | 2020-01-28 | COMP | 2020-03-05 | COMP | Rule 16 | 15 | 33 | 8 | 23 | 0 | 9 | 84
15817 | 2019-10-31 | 2019-11-21 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-07 | COMP | 2020-01-07 | COMP | 2020-01-08 | COMP | 2020-02-11 | COMP | Rule 16 | 15 | 26 | 5 | 1 | 2 | 24 | 68
15899 | 2019-10-31 | 2019-11-26 | 2020-02-01 | 2020-02-01 | COMP | 2020-03-13 | COMP | 2020-03-23 | COMP | 2021-10-23 | INPR | 2020-04-07 | COMP | Rule 16 | 18 | 44 | 29 | 7 |  |  | 107
16029 | 2019-10-31 | 2019-12-06 | 2020-08-25 | 2020-09-05 | COMP | 2020-09-18 | COMP | 2020-10-13 | COMP | 2020-11-17 | COMP | 2021-02-24 | COMP | Rule 16 | 24 | 183 | 9 | 18 | 25 | 66 | 329
16138 | 2019-10-31 | 2019-12-11 | 2020-05-12 | 2020-10-08 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2020-10-26 | COMP | 2021-02-22 | COMP | Rule 15/16 | 27 | 106 | 11 | 1 | 3 | 79 | 327
16374 | 2019-10-31 | 2019-12-23 | 2020-02-25 | 2020-02-25 | COMP | 2020-03-25 | COMP | 2020-04-13 | COMP | 2023-11-13 | INPR | 2021-04-05 | COMP | Rule 16 | 35 | 43 | 22 | 14 |  |  | 357
16395 | 2019-10-31 | 2019-12-26 | 2020-03-19 | 2020-07-02 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-08-17 | COMP | Rule 16 | 37 | 58 | 20 | 1 | 1 | 14 | 200
16781 | 2019-10-31 | 2020-01-15 | 2020-01-29 | 2020-01-29 | COMP | 2021-01-14 | COMP | 2021-01-14 | COMP | 2021-03-03 | COMP | 2021-03-05 | COMP | Rule 16 | 50 | 10 | 244 | 1 | 33 | 3 | 336
16962 | 2019-10-31 | 2020-01-25 | 2020-07-27 | 2020-07-27 | COMP | 2020-12-14 | COMP | 2021-05-12 | COMP | 2021-05-18 | COMP | 2022-04-08 | COMP | Rule 16 | 56 | 129 | 97 | 104 | 5 | 226 | 613
17008 | 2019-10-31 | 2020-01-27 | 2020-04-17 | 2020-04-17 | COMP | 2020-05-13 | COMP | 2020-08-21 | COMP | 2022-08-20 | COMP | 2022-10-04 | COMP | Rule 16 | 57 | 59 | 19 | 72 | 502 | 31 | 736
17445 | 2019-10-31 | 2020-02-14 | 2020-03-04 | 2020-04-13 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-05-19 | COMP | 2020-05-23 | COMP | Rule 16 | 71 | 13 | 9 | 1 | 19 | 4 | 140
17688 | 2019-10-31 | 2020-02-24 | 2020-03-19 | 2020-03-19 | COMP | 2020-08-21 | COMP | 2022-03-03 | COMP | 2022-01-26 | COMP | 2022-03-22 | COMP | Rule 16 | 76 | 19 | 111 | 384 | 0 | 14 | 600
17750 | 2019-10-31 | 2020-02-25 | 2020-03-28 | 2020-03-28 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2020-05-19 | COMP | 2020-06-18 | COMP | Rule 16 | 77 | 24 | 34 | 1 | 4 | 22 | 158
17762 | 2019-10-31 | 2020-02-26 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2021-06-09 | COMP | 2021-06-24 | COMP | Rule 16 | 78 | 26 | 19 | 1 | 283 | 12 | 414
17865 | 2019-10-31 | 2020-03-03 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-30 | COMP | 2020-09-15 | COMP | Rule 16 | 82 | 43 | 27 | 1 | 39 | 33 | 220
18333 | 2019-10-31 | 2020-03-20 | 2020-09-19 | 2020-09-19 | COMP | 2020-12-29 | COMP | 2021-03-19 | COMP | 2021-03-22 | COMP | 2021-04-06 | COMP | Rule 16 | 95 | 129 | 68 | 56 | 2 | 12 | 358
18550 | 2019-10-31 | 2020-03-30 | 2020-06-30 | 2020-06-30 | COMP | 2020-09-10 | COMP | 2021-01-26 | COMP | 2021-09-28 | COMP | 2021-11-08 | COMP | Rule 16 | 101 | 66 | 52 | 93 | 172 | 30 | 509
19172 | 2019-10-31 | 2020-04-22 | 2020-05-08 | 2020-05-08 | COMP | 2021-03-04 | COMP | 2021-03-04 | COMP | 2021-10-10 | COMP | 2021-10-22 | COMP | Rule 16 | 118 | 13 | 206 | 1 | 154 | 10 | 498
19254 | 2019-10-31 | 2020-04-28 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2022-06-18 | INPR | 2021-06-15 | COMP | Rule 16 | 122 | 18 | 8 | 1 |  |  | 407
24630 | 2019-10-31 | 2021-01-05 | 2023-04-17 | 2023-04-17 | COMP | 2023-04-19 | NOTN | 2023-04-20 | COMP | 2023-04-20 | COMP | 2023-11-06 | COMP | Other | 295 | 574 |  | 4 | 1 | 139 | 1009
15731 | 2019-11-01 | 2019-11-19 | 2020-01-25 | 2020-01-25 | COMP | 2020-01-27 | NOTN | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-03-12 | COMP | Other | 12 | 44 |  | 1 | 1 | 33 | 88
15759 | 2019-11-01 | 2019-11-20 | 2020-05-27 | 2020-05-27 | COMP | 2021-02-24 | COMP | 2022-05-05 | COMP | 2022-07-12 | COMP | 2022-09-12 | COMP | Rule 15/16 | 13 | 129 | 188 | 304 | 46 | 44 | 719
15804 | 2019-11-01 | 2019-11-20 | 2019-12-20 | 2019-12-20 | COMP | 2020-03-27 | COMP | 2020-02-21 | COMP | 2020-06-29 | COMP | 2020-07-29 | COMP | Rule 16 | 13 | 21 | 67 |  | 91 | 23 | 186
16086 | 2019-11-01 | 2019-12-09 | 2020-04-16 | 2020-04-16 | COMP | 2020-04-21 | COMP | 2021-01-07 | COMP | 2021-08-27 | COMP | 2021-10-04 | COMP | Rule 16 | 24 | 90 | 4 | 181 | 163 | 26 | 483
16651 | 2019-11-01 | 2020-01-09 | 2020-02-14 | 2020-02-14 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-02-24 | COMP | 2020-03-07 | COMP | Rule 16 | 45 | 26 | 7 | 1 | 0 | 9 | 84
16652 | 2019-11-01 | 2020-01-09 | 2020-04-23 | 2020-04-23 | COMP | 2021-01-13 | COMP | 2021-09-16 | COMP | 2021-01-13 | COMP | 2021-10-20 | COMP | Rule 15/16 | 45 | 74 | 183 | 172 | 0 | 25 | 495
16675 | 2019-11-01 | 2020-01-11 | 2020-05-01 | 2020-05-01 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-09-29 | COMP | 2020-10-20 | COMP | Rule 16 | 46 | 78 | 65 | 1 | 42 | 16 | 244
16745 | 2019-11-01 | 2020-01-14 | 2020-07-06 | 2021-01-29 | COMP | 2021-02-25 | COMP | 2021-02-25 | COMP | 2021-02-26 | COMP | 2021-04-09 | COMP | Rule 16 | 48 | 122 | 19 | 1 | 2 | 31 | 360
16827 | 2019-11-01 | 2020-01-17 | 2021-04-24 | 2021-04-24 | COMP | 2021-07-02 | COMP | 2022-04-18 | COMP | 2022-04-26 | COMP | 2022-05-13 | COMP | Rule 15/16 | 51 | 320 | 49 | 200 | 7 | 14 | 637
16857 | 2019-11-01 | 2020-01-22 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-25 | COMP | 2020-03-26 | COMP | Rule 16 | 53 | 22 | 10 | 1 | 15 | 2 | 98
17084 | 2019-11-01 | 2020-01-30 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-08-03 | COMP | 2020-08-18 | COMP | Rule 16 | 59 | 23 | 12 | 1 | 98 | 12 | 200
17288 | 2019-11-01 | 2020-02-07 | 2020-09-05 | 2020-09-05 | COMP | 2020-10-07 | NOTN | 2020-10-12 | COMP | 2020-10-26 | COMP | 2020-12-22 | COMP | Other | 65 | 149 |  | 25 | 11 | 39 | 286
17450 | 2019-11-01 | 2020-02-13 | 2020-06-30 | 2020-07-16 | COMP | 2020-07-27 | COMP | 2020-07-07 | COMP | 2020-08-06 | COMP | 2020-08-31 | COMP | Rule 16 | 69 | 97 | 8 |  | 23 | 18 | 209
17834 | 2019-11-01 | 2020-02-29 | 2020-05-08 | 2020-05-08 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-07-10 | COMP | Rule 16 | 79 | 50 | 28 | 1 | 1 | 18 | 173
18172 | 2019-11-01 | 2020-03-13 | 2020-04-23 | 2020-04-23 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-07-27 | COMP | 2020-08-06 | COMP | Rule 16 | 89 | 30 | 63 | 1 | 5 | 9 | 192
18575 | 2019-11-01 | 2020-03-28 | 2020-04-28 | 2020-04-28 | COMP | 2020-09-08 | COMP | 2021-01-04 | COMP | 2021-06-18 | COMP | 2021-06-23 | COMP | Rule 16 | 99 | 22 | 94 | 80 | 117 | 4 | 412
18600 | 2019-11-01 | 2020-04-02 | 2020-06-30 | 2021-07-20 | COMP | 2021-08-16 | COMP | 2021-08-20 | COMP | 2021-10-14 | COMP | 2021-12-04 | COMP | Rule 16 | 103 | 63 | 20 | 5 | 39 | 34 | 524
18607 | 2019-11-01 | 2020-03-31 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-26 | COMP | 2020-06-22 | COMP | 2020-06-16 | COMP | 2020-06-26 | COMP | Rule 16 | 101 | 26 | 15 | 20 | 0 | 5 | 163
19746 | 2019-11-01 | 2020-05-20 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-18 | COMP | 2020-08-19 | COMP | 2020-10-30 | COMP | 2020-09-26 | COMP | Rule 16 | 137 | 48 | 17 | 2 | 52 |  | 227
32283 | 2019-11-01 | 2021-11-09 | 2022-05-09 | 2022-05-09 | COMP | 2022-07-27 | COMP | 2022-07-27 | COMP | 2022-08-12 | COMP | 2022-11-23 | COMP | Rule 16 | 509 | 125 | 55 | 1 | 13 | 72 | 770
15576 | 2019-11-02 | 2019-11-07 | 2020-02-05 | 2020-02-07 | COMP | 2020-04-01 | COMP | 2020-06-08 | COMP | 2021-03-10 | COMP | 2021-05-07 | COMP | Rule 16 | 4 | 59 | 38 | 48 | 190 | 43 | 379
18337 | 2019-11-03 | 2020-03-20 | 2020-09-25 | 2020-09-25 | COMP | 2020-10-09 | COMP | 2021-03-03 | COMP | 2021-04-19 | COMP | 2021-06-03 | COMP | Rule 16 | 93 | 134 | 11 | 97 | 34 | 33 | 397
19395 | 2019-11-03 | 2020-05-05 | 2020-05-18 | 2020-05-18 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-07-09 | COMP | 2020-07-27 | COMP | Rule 16 | 125 | 10 | 9 | 1 | 30 | 13 | 183
21071 | 2019-11-03 | 2020-07-20 | 2020-08-19 | 2020-08-19 | COMP | 2020-10-09 | COMP | 2020-11-20 | COMP | 2021-09-09 | COMP | 2021-10-12 | COMP | Rule 16 | 178 | 23 | 37 | 30 | 201 | 24 | 488
15730 | 2019-11-04 | 2019-11-19 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2021-05-30 | INPR | 2020-05-07 | COMP | Rule 16 | 11 | 74 | 6 | 1 |  |  | 127
15752 | 2019-11-04 | 2019-11-19 | 2020-05-22 | 2020-05-22 | COMP | 2020-03-31 | NOTN | 2020-11-19 | COMP | 2021-01-20 | COMP | 2021-02-23 | COMP | Other | 11 | 128 |  | 127 | 40 | 24 | 326
15795 | 2019-11-04 | 2019-11-20 | 2019-11-22 | 2019-11-22 | COMP | 2019-12-06 | COMP | 2019-12-06 | INPR | 2019-12-20 | COMP | 2020-01-10 | COMP | Rule 16 | 12 | 3 | 9 |  |  |  | 45
15890 | 2019-11-04 | 2019-11-25 | 2020-01-08 | 2020-01-08 | COMP | 2020-01-22 | COMP | 2020-01-24 | COMP | 2020-02-12 | COMP | 2020-02-13 | COMP | Rule 16 | 15 | 29 | 10 | 3 | 14 | 2 | 68
16053 | 2019-11-04 | 2019-12-07 | 2020-03-18 | 2020-03-18 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-07-27 | COMP | 2020-08-12 | COMP | Other | 22 | 69 | 66 | 1 | 28 | 13 | 195
16055 | 2019-11-04 | 2019-12-07 | 2020-04-15 | 2020-04-15 | COMP | 2020-09-16 | COMP | 2020-11-09 | COMP | 2020-11-10 | COMP | 2021-02-24 | COMP | Rule 15/16 | 22 | 89 | 109 | 39 | 2 | 70 | 327
16207 | 2019-11-04 | 2019-12-16 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-11 | COMP | 2020-06-08 | COMP | 2023-03-21 | COMP | 2023-04-17 | COMP | Rule 16 | 28 | 84 | 19 | 20 | 700 | 20 | 866
16351 | 2019-11-04 | 2019-12-23 | 2020-02-21 | 2020-02-21 | COMP | 2020-03-18 | COMP | 2020-04-06 | COMP | 2020-05-18 | COMP | 2020-06-09 | COMP | Rule 16 | 33 | 41 | 19 | 14 | 31 | 16 | 149
16360 | 2019-11-04 | 2019-12-23 | 2020-04-21 | 2020-04-21 | COMP | 2020-06-03 | COMP | 2020-07-01 | COMP | 2020-06-23 | COMP | 2020-09-04 | COMP | Rule 15/16 | 33 | 83 | 31 | 21 | 0 | 48 | 212
16430 | 2019-11-04 | 2019-12-30 | 2020-03-13 | 2020-03-13 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-11-23 | COMP | 2021-01-11 | COMP | Rule 16 | 37 | 52 | 56 | 1 | 124 | 32 | 297
16536 | 2019-11-04 | 2020-01-07 | 2020-01-15 | 2020-01-15 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2021-03-28 | INPR | 2020-03-14 | COMP | Rule 16 | 42 | 7 | 8 | 1 |  |  | 88
16627 | 2019-11-04 | 2020-01-09 | 2020-04-26 | 2020-04-26 | COMP | 2020-05-20 | COMP | 2021-03-08 | COMP | 2021-02-05 | COMP | 2021-04-08 | COMP | Rule 15/16 | 44 | 75 | 18 | 200 | 0 | 24 | 358
16668 | 2019-11-04 | 2020-01-10 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2021-02-05 | COMP | 2021-03-17 | COMP | Rule 16 | 45 | 70 | 16 | 1 | 187 | 28 | 342
16698 | 2019-11-04 | 2020-01-13 | 2020-04-14 | 2020-04-14 | COMP | 2020-05-11 | COMP | 2020-07-29 | COMP | 2020-07-10 | COMP | 2020-08-19 | COMP | Rule 16 | 46 | 65 | 20 | 57 | 0 | 16 | 200
16708 | 2019-11-04 | 2020-01-14 | 2020-05-12 | 2020-05-12 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2021-12-21 | COMP | 2022-06-17 | COMP | Rule 15/16 | 47 | 84 | 66 | 1 | 341 | 126 | 660
16714 | 2019-11-04 | 2020-01-14 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-24 | COMP | 2020-06-20 | COMP | 2020-09-30 | COMP | 2020-11-20 | COMP | Rule 16 | 47 | 57 | 16 | 40 | 72 | 37 | 265
16806 | 2019-11-04 | 2020-01-16 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-03-03 | COMP | 2020-03-18 | COMP | Rule 16 | 49 | 26 | 7 | 1 | 1 | 12 | 91
16943 | 2019-11-04 | 2020-01-24 | 2020-10-05 | 2022-01-22 | COMP | 2022-02-11 | COMP | 2021-05-05 | COMP | 2022-04-26 | COMP | 2022-05-11 | COMP | Rule 16 | 54 | 179 | 15 |  | 247 | 12 | 634
17214 | 2019-11-04 | 2020-02-04 | 2020-04-14 | 2020-04-14 | COMP | 2020-05-04 | COMP | 2020-05-19 | INPR | 2020-05-12 | COMP | 2020-06-08 | COMP | Rule 16 | 61 | 50 | 15 |  |  |  | 148
17437 | 2019-11-04 | 2020-02-14 | 2020-05-17 | 2020-05-17 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-06-22 | COMP | 2020-07-31 | COMP | Rule 16 | 69 | 65 | 27 | 1 | 0 | 28 | 187
17592 | 2019-11-04 | 2020-02-20 | 2020-03-22 | 2020-03-22 | COMP | 2020-03-31 | COMP | 2020-12-18 | NOTN | 2020-12-18 | COMP | 2021-01-05 | COMP | Rule 16 | 72 | 22 | 7 |  |  |  | 293
17622 | 2019-11-04 | 2020-02-22 | 2020-03-13 | 2020-03-13 | COMP | 2020-03-16 | NOTN | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-11-13 | COMP | Other | 73 | 15 |  | 2 | 1 | 172 | 260
17976 | 2019-11-04 | 2020-03-06 | 2020-11-20 | 2021-01-04 | COMP | 2021-01-08 | COMP | 2021-02-09 | COMP | 2022-07-16 | INPR | 2021-04-05 | COMP | Rule 16 | 83 | 183 | 5 | 22 |  |  | 355
18301 | 2019-11-04 | 2020-03-18 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-13 | COMP | 2021-03-23 | COMP | 2023-12-03 | INPR | 2021-08-27 | COMP | Rule 16 | 91 | 72 | 12 | 174 |  |  | 457
18332 | 2019-11-04 | 2020-03-20 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-30 | COMP | 2020-05-20 | COMP | 2020-05-26 | COMP | 2020-07-01 | COMP | Rule 16 | 93 | 25 | 6 | 15 | 4 | 27 | 165
18407 | 2019-11-04 | 2020-03-23 | 2020-07-25 | 2020-07-25 | COMP | 2020-09-08 | COMP | 2020-09-16 | COMP | 2020-11-23 | COMP | 2020-12-16 | COMP | Other | 94 | 89 | 31 | 7 | 48 | 16 | 281
18773 | 2019-11-04 | 2020-04-06 | 2020-05-20 | 2020-05-20 | COMP | 2021-08-23 | COMP | 2023-01-30 | COMP | 2022-06-06 | COMP | 2023-08-16 | COMP | Rule 16 | 104 | 33 | 318 | 360 | 0 | 139 | 950
18929 | 2019-11-04 | 2020-04-13 | 2020-05-31 | 2020-08-31 | COMP | 2020-09-30 | COMP | 2020-09-30 | COMP | 2020-12-31 | COMP | 2021-01-05 | COMP | Rule 16 | 109 | 34 | 22 | 1 | 63 | 3 | 293
19277 | 2019-11-04 | 2020-04-29 | 2020-06-11 | 2020-06-11 | COMP | 2020-10-02 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2020-12-10 | COMP | Rule 15/16 | 121 | 31 | 81 | 20 | 1 | 28 | 277
19418 | 2019-11-04 | 2020-05-06 | 2020-07-23 | 2020-07-23 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2020-12-08 | COMP | 2021-02-09 | COMP | Rule 16 | 126 | 56 | 46 | 1 | 50 | 43 | 317
21059 | 2019-11-04 | 2020-07-19 | 2020-09-08 | 2021-11-02 | COMP | 2021-11-17 | COMP | 2021-03-10 | COMP | 2021-11-22 | COMP | 2022-05-04 | COMP | Rule 16 | 177 | 36 | 11 |  | 180 | 114 | 629
4263 | 2019-11-05 | 2020-01-07 | 2020-07-19 | 2020-07-19 | COMP | 2020-09-14 | COMP | 2021-03-08 | COMP | 2021-04-20 | COMP | 2021-06-02 | COMP | Rule 15/16 | 41 | 136 | 40 | 119 | 32 | 31 | 395
15568 | 2019-11-05 | 2019-11-07 | 2020-03-18 | 2020-03-18 | COMP | 2020-08-26 | COMP | 2020-12-18 | COMP | 2021-07-06 | COMP | 2021-08-14 | COMP | Rule 15/16 | 3 | 88 | 115 | 79 | 137 | 29 | 446
15694 | 2019-11-05 | 2019-11-16 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-11-12 | COMP | 2020-12-14 | COMP | Rule 16 | 8 | 136 | 15 | 1 | 101 | 21 | 278
15779 | 2019-11-05 | 2019-11-21 | 2020-05-08 | 2020-05-08 | COMP | 2020-10-05 | COMP | 2020-12-08 | COMP |  | INPR | 2020-12-10 | COMP | Rule 15/16 | 12 | 116 | 105 | 44 |  |  | 276
15794 | 2019-11-05 | 2019-11-20 | 2020-01-11 | 2020-01-11 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-06-10 | COMP | 2020-07-31 | COMP | Rule 16 | 11 | 34 | 84 | 1 | 22 | 38 | 186
15818 | 2019-11-05 | 2019-11-21 | 2020-01-09 | 2020-01-09 | COMP | 2020-02-05 | COMP | 2020-03-17 | COMP | 2020-03-25 | COMP | 2020-05-13 | COMP | Rule 16 | 12 | 32 | 19 | 29 | 7 | 36 | 130
15920 | 2019-11-05 | 2019-12-02 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-22 | COMP | 2020-02-12 | COMP | 2020-08-28 | COMP | 2020-08-29 | COMP | Rule 16 | 17 | 30 | 6 | 16 | 141 | 1 | 206
16041 | 2019-11-05 | 2019-12-06 | 2020-03-30 | 2020-03-30 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-06-26 | COMP | 2020-08-03 | COMP | Rule 16 | 21 | 78 | 46 | 1 | 19 | 27 | 187
16045 | 2019-11-05 | 2019-12-06 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-20 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2020-05-27 | COMP | Rule 16 | 21 | 40 | 12 | 39 | 1 | 31 | 139
16099 | 2019-11-05 | 2019-12-09 | 2020-04-27 | 2020-04-27 | COMP | 2020-04-27 | NOTN | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-05-12 | COMP | Other | 22 | 97 |  | 1 | 1 | 12 | 129
16116 | 2019-11-05 | 2019-12-10 | 2020-03-06 | 2020-08-26 | COMP | 2020-09-04 | COMP | 2021-06-11 | COMP | 2021-06-29 | COMP | 2021-08-21 | COMP | Rule 16 | 23 | 60 | 8 | 192 | 13 | 38 | 451
16277 | 2019-11-05 | 2019-12-18 | 2020-04-14 | 2020-04-20 | COMP | 2020-05-08 | COMP | 2020-07-23 | COMP | 2020-09-08 | COMP | 2020-09-25 | COMP | Rule 15/16 | 29 | 81 | 15 | 54 | 33 | 14 | 225
16353 | 2019-11-05 | 2019-12-23 | 2020-04-27 | 2020-06-09 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2021-02-24 | COMP | 2021-04-01 | COMP | Rule 16 | 32 | 87 | 8 | 1 | 172 | 27 | 352
16390 | 2019-11-05 | 2019-12-24 | 2020-04-08 | 2020-04-08 | COMP | 2020-07-20 | COMP | 2020-10-15 | COMP | 2020-09-11 | COMP | 2020-11-10 | COMP | Rule 16 | 33 | 73 | 73 | 63 | 0 | 19 | 257
16500 | 2019-11-05 | 2020-01-03 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-04-29 | COMP | Rule 16 | 39 | 45 | 13 | 1 | 1 | 26 | 120
16546 | 2019-11-05 | 2020-01-07 | 2020-03-10 | 2020-03-10 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-05-12 | COMP | 2020-05-13 | COMP | Rule 16 | 41 | 44 | 24 | 1 | 23 | 2 | 130
16939 | 2019-11-05 | 2020-01-25 | 2020-12-23 | 2021-08-13 | COMP | 2021-09-07 | COMP | 2021-09-13 | COMP | 2021-10-27 | COMP | 2021-12-08 | COMP | Rule 16 | 53 | 232 | 17 | 5 | 33 | 28 | 525
17105 | 2019-11-05 | 2020-01-30 | 2020-04-28 | 2020-10-01 | COMP | 2020-07-14 | COMP | 2020-07-14 | COMP | 2020-10-01 | COMP | 2020-10-23 | COMP | Rule 16 | 57 | 63 |  | 1 | 57 | 17 | 245
17238 | 2019-11-05 | 2020-02-05 | 2020-02-29 | 2020-02-29 | COMP | 2020-03-31 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-06-23 | COMP | Rule 16 | 61 | 17 | 22 | 35 | 1 | 26 | 158
17378 | 2019-11-05 | 2020-02-12 | 2020-04-01 | 2020-04-01 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-01 | COMP | 2020-06-04 | COMP | Rule 16 | 66 | 35 | 24 | 1 | 20 | 4 | 145
17500 | 2019-11-05 | 2020-02-19 | 2020-03-15 | 2020-03-15 | COMP | 2020-04-14 | COMP | 2020-04-15 | COMP | 2020-05-28 | COMP | 2020-06-03 | COMP | Rule 16 | 70 | 18 | 22 | 2 | 31 | 5 | 144
17547 | 2019-11-05 | 2020-02-20 | 2020-05-19 | 2020-05-19 | COMP | 2021-08-09 | COMP | 2021-08-09 | COMP | 2022-05-24 | COMP | 2022-06-13 | COMP | Rule 16 | 71 | 64 | 309 | 1 | 201 | 14 | 655
18158 | 2019-11-05 | 2020-03-12 | 2020-07-08 | 2020-07-08 | COMP | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-10-26 | COMP | 2021-02-09 | COMP | Rule 16 | 86 | 84 | 28 | 1 | 51 | 71 | 316
18257 | 2019-11-05 | 2020-03-17 | 2022-04-05 | 2023-02-15 | COMP | 2023-03-08 | COMP | 2023-08-09 | COMP | 2023-05-05 | COMP | 2023-08-31 | COMP | Rule 15/16 | 89 | 519 | 15 | 108 | 0 | 17 | 960
18442 | 2019-11-05 | 2020-03-24 | 2021-02-18 | 2022-04-14 | COMP | 2022-04-15 | NOTN | 2022-05-20 | COMP | 2022-04-15 | COMP | 2022-05-27 | COMP | Other | 94 | 229 |  | 27 | 0 | 6 | 645
18606 | 2019-11-05 | 2020-03-31 | 2020-06-16 | 2020-06-16 | COMP | 2021-07-30 | COMP | 2023-06-28 | COMP | 2023-07-03 | COMP | 2023-07-11 | COMP | Rule 16 | 99 | 55 | 284 | 480 | 4 | 6 | 923
18831 | 2019-11-05 | 2020-04-08 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-10 | COMP | 2020-10-13 | COMP | 2020-09-24 | COMP | 2020-11-04 | COMP | Rule 16 | 105 | 56 | 33 | 46 | 0 | 17 | 253
18945 | 2019-11-05 | 2020-04-14 | 2020-05-15 | 2020-08-21 | COMP | 2020-09-11 | COMP | 2020-09-11 | COMP | 2020-09-08 | COMP | 2020-10-06 | COMP | Rule 16 | 109 | 24 | 15 | 1 | 0 | 18 | 232
19222 | 2019-11-05 | 2020-04-25 | 2020-12-03 | 2020-12-03 | COMP | 2020-12-03 | NOTN | 2021-03-10 | COMP | 2021-01-12 | COMP | 2022-09-12 | COMP | Other | 117 | 154 |  | 66 | 0 | 382 | 717
19687 | 2019-11-05 | 2020-05-17 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-02 | COMP | 2020-07-22 | COMP | 2020-09-29 | COMP | 2020-12-10 | COMP | Rule 16 | 132 | 22 | 12 | 15 | 49 | 50 | 276
23007 | 2019-11-05 | 2020-10-20 | 2021-04-30 | 2021-04-30 | COMP | 2021-07-29 | COMP | 2021-08-11 | COMP | 2021-09-22 | COMP | 2021-09-29 | COMP | Rule 16 | 242 | 132 | 63 | 10 | 30 | 6 | 478
4268 | 2019-11-06 | 2020-01-21 | 2020-03-13 | 2020-03-13 | COMP | 2020-10-21 | NOTN | 2020-10-21 | COMP | 2020-11-16 | COMP | 2020-12-29 | COMP | Other | 49 | 38 |  | 157 | 18 | 29 | 287
15588 | 2019-11-06 | 2019-11-08 | 2020-01-06 | 2020-01-06 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2021-03-28 | INPR | 2020-03-20 | COMP | Rule 16 | 3 | 37 | 20 | 1 |  |  | 91
15589 | 2019-11-06 | 2019-11-08 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2021-03-28 | INPR | 2020-03-20 | COMP | Rule 16 | 3 | 38 | 19 | 1 |  |  | 91
15617 | 2019-11-06 | 2019-11-12 | 2019-12-23 | 2019-12-23 | COMP | 2020-01-28 | NOTN | 2020-02-03 | COMP | 2020-02-24 | COMP | 2020-06-30 | COMP | Other | 4 | 28 |  | 28 | 15 | 91 | 162
15673 | 2019-11-06 | 2019-11-14 | 2021-07-22 | 2021-07-22 | COMP | 2021-08-31 | COMP | 2021-11-01 | COMP | 2021-11-09 | COMP | 2021-12-21 | COMP | Rule 15/16 | 6 | 424 | 29 | 44 | 7 | 28 | 533
15721 | 2019-11-06 | 2019-11-18 | 2019-12-14 | 2020-06-17 | COMP | 2020-07-02 | COMP | 2020-05-04 | COMP | 2020-06-23 | COMP | 2020-08-10 | COMP | Rule 16 | 8 | 18 | 12 |  | 36 | 35 | 191
15765 | 2019-11-06 | 2019-11-20 | 2020-03-06 | 2020-03-06 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-12-08 | COMP | 2021-01-26 | COMP | Rule 16 | 10 | 72 | 31 | 1 | 163 | 33 | 305
15917 | 2019-11-06 | 2019-12-02 | 2020-02-11 | 2020-02-11 | COMP | 2020-05-07 | COMP | 2020-05-18 | COMP | 2020-05-07 | COMP | 2020-06-26 | COMP | Rule 16 | 16 | 49 | 62 | 8 | 0 | 29 | 160
15918 | 2019-11-06 | 2019-12-02 | 2020-01-09 | 2020-01-09 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2021-03-09 | COMP | Rule 16 | 16 | 27 | 84 | 1 | 1 | 210 | 334
16008 | 2019-11-06 | 2019-12-06 | 2020-03-18 | 2020-03-18 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-09-14 | COMP | 2021-07-21 | COMP | Rule 16 | 20 | 70 | 114 | 1 | 14 | 214 | 428
16059 | 2019-11-06 | 2019-12-06 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-05-26 | COMP | 2020-06-27 | COMP | Rule 16 | 20 | 90 | 16 | 1 | 14 | 24 | 160
16079 | 2019-11-06 | 2019-12-09 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-04-22 | COMP | 2020-06-08 | COMP | Rule 16 | 21 | 72 | 18 | 1 | 6 | 33 | 146
16096 | 2019-11-06 | 2019-12-09 | 2020-02-18 | 2020-02-18 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-10-22 | COMP | 2020-12-08 | COMP | Rule 16 | 21 | 48 | 28 | 1 | 149 | 31 | 273
16106 | 2019-11-06 | 2019-12-10 | 2020-01-21 | 2020-01-21 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-02-27 | COMP | 2020-03-13 | COMP | Rule 16 | 22 | 28 | 7 | 1 | 21 | 12 | 86
16264 | 2019-11-06 | 2019-12-18 | 2020-02-21 | 2020-02-21 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-08-11 | COMP | 2020-12-03 | COMP | Rule 16 | 28 | 44 | 100 | 1 | 23 | 79 | 270
16376 | 2019-11-06 | 2019-12-23 | 2020-03-09 | 2020-06-02 | COMP | 2021-03-02 | COMP | 2021-03-02 | COMP | 2021-05-19 | COMP | 2021-07-13 | COMP | Rule 16 | 31 | 52 | 188 | 1 | 57 | 38 | 422
16616 | 2019-11-06 | 2020-01-10 | 2020-02-18 | 2020-04-10 | COMP | 2020-05-01 | COMP | 2021-02-17 | COMP |  |  | 2021-03-04 | COMP | Rule 16 | 43 | 26 | 16 | 200 |  |  | 331
16617 | 2019-11-06 | 2020-01-10 | 2020-03-26 | 2020-03-26 | COMP | 2020-07-28 | COMP | 2020-08-19 | COMP | 2023-11-17 | COMP | 2023-12-18 | COMP | Rule 16 | 43 | 53 | 88 | 17 | 816 | 20 | 1032
16635 | 2019-11-06 | 2020-01-09 | 2020-02-10 | 2020-03-06 | COMP | 2020-05-18 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-31 | COMP | Rule 16 | 42 | 22 | 52 | 15 | 1 | 40 | 185
16859 | 2019-11-06 | 2020-01-21 | 2020-02-27 | 2020-02-27 | COMP | 2020-02-28 | NOTN | 2020-03-03 | COMP | 2020-04-16 | NOTN | 2020-06-05 | COMP | Other | 49 | 27 |  | 4 |  |  | 145
16868 | 2019-11-06 | 2020-01-22 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-10-28 | COMP | 2020-12-19 | COMP | Rule 15/16 | 50 | 77 | 42 | 1 | 81 | 35 | 281
17089 | 2019-11-06 | 2020-01-30 | 2020-04-17 | 2020-05-15 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-08-05 | COMP | 2021-09-20 | COMP | Rule 16 | 56 | 56 | 5 | 1 | 54 | 283 | 470
17144 | 2019-11-06 | 2020-02-01 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-07-10 | COMP | 2020-08-25 | COMP | Rule 16 | 57 | 59 | 21 | 1 | 35 | 33 | 202
17307 | 2019-11-06 | 2020-02-08 | 2020-04-23 | 2020-04-23 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2022-08-21 | INPR | 2021-08-11 | COMP | Rule 16 | 62 | 53 | 52 | 1 |  |  | 443
17935 | 2019-11-06 | 2020-03-04 | 2020-04-26 | 2020-04-26 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-10-09 | COMP | 2020-11-05 | COMP | Rule 16 | 79 | 38 | 33 | 1 | 86 | 20 | 253
18467 | 2019-11-06 | 2020-03-25 | 2020-07-07 | 2020-07-22 | COMP | 2021-05-17 | COMP | 2022-03-29 | COMP | 2022-03-28 | COMP | 2022-05-10 | COMP | Rule 16 | 94 | 74 | 206 | 219 | 0 | 31 | 631
19325 | 2019-11-06 | 2020-04-30 | 2020-06-08 | 2020-06-08 | COMP | 2020-08-17 | COMP | 2020-10-26 | COMP | 2020-11-12 | COMP | 2020-12-09 | COMP | Rule 16 | 120 | 27 | 51 | 50 | 13 | 18 | 274
19618 | 2019-11-06 | 2020-05-15 | 2020-08-11 | 2020-08-11 | COMP | 2020-08-26 | COMP | 2020-12-01 | COMP | 2020-12-29 | COMP | 2021-01-07 | COMP | Rule 16 | 131 | 62 | 12 | 66 | 20 | 7 | 293
19898 | 2019-11-06 | 2020-05-27 | 2020-09-04 | 2020-09-04 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2021-02-22 | COMP | 2021-02-26 | COMP | Rule 16 | 138 | 73 | 32 | 1 | 83 | 5 | 327
15616 | 2019-11-07 | 2019-11-12 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-05-11 | COMP | 2020-06-15 | COMP | Rule 16 | 3 | 84 | 26 | 1 | 16 | 25 | 150
15903 | 2019-11-07 | 2019-11-26 | 2020-09-16 | 2020-09-16 | COMP | 2020-09-29 | COMP | 2021-02-08 | COMP | 2023-12-03 | INPR | 2022-02-02 | COMP | Rule 16 | 13 | 204 | 10 | 89 |  |  | 562
15932 | 2019-11-07 | 2019-12-02 | 2020-03-10 | 2020-03-10 | COMP | 2020-06-24 | COMP | 2021-03-31 | COMP | 2021-08-03 | COMP | 2021-09-16 | COMP | Rule 15/16 | 15 | 68 | 76 | 193 | 88 | 32 | 467
16065 | 2019-11-07 | 2019-12-07 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2021-03-30 | COMP | 2021-03-31 | COMP | Rule 16 | 19 | 125 | 8 | 1 | 198 | 2 | 349
16084 | 2019-11-07 | 2019-12-09 | 2020-01-11 | 2020-01-11 | COMP | 2020-01-17 | COMP | 2020-01-17 | INPR | 2020-01-21 | COMP | 2020-01-28 | COMP | Rule 16 | 20 | 23 | 5 |  |  |  | 53
16219 | 2019-11-07 | 2019-12-17 | 2020-01-26 | 2020-01-26 | COMP | 2020-02-07 | COMP | 2020-02-07 | COMP | 2020-04-08 | COMP | 2020-05-11 | COMP | Rule 16 | 26 | 26 | 10 | 1 | 43 | 24 | 126
16220 | 2019-11-07 | 2019-12-17 | 2020-04-15 | 2020-04-15 | COMP | 2020-07-10 | COMP | 2020-07-31 | COMP | 2020-08-11 | COMP | 2020-10-09 | COMP | Rule 16 | 26 | 83 | 62 | 16 | 8 | 43 | 233
16238 | 2019-11-07 | 2019-12-17 | 2020-03-18 | 2020-03-18 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2021-08-03 | COMP | 2021-09-29 | COMP | Rule 16 | 26 | 63 | 69 | 1 | 281 | 41 | 476
16239 | 2019-11-07 | 2019-12-17 | 2020-03-10 | 2020-03-10 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2021-08-03 | COMP | 2021-09-29 | COMP | Rule 16 | 26 | 57 | 75 | 1 | 281 | 41 | 476
16240 | 2019-11-07 | 2019-12-17 | 2020-03-23 | 2020-03-23 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2021-08-03 | COMP | 2021-09-29 | COMP | Rule 15/16 | 26 | 66 | 66 | 1 | 281 | 41 | 476
16384 | 2019-11-07 | 2019-12-23 | 2020-01-09 | 2020-01-09 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-02-10 | COMP | 2020-02-10 | COMP | Rule 16 | 30 | 12 | 12 | 1 | 11 | 1 | 62
16846 | 2019-11-07 | 2020-01-21 | 2020-04-20 | 2020-08-05 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-09-21 | COMP | 2020-11-12 | COMP | Rule 16 | 48 | 64 | 7 | 1 | 27 | 38 | 256
17000 | 2019-11-07 | 2020-01-27 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-29 | COMP | 2020-06-12 | COMP | 2020-06-01 | COMP | 2020-07-08 | COMP | Rule 16 | 52 | 63 | 5 | 32 | 0 | 19 | 167
17492 | 2019-11-07 | 2020-02-18 | 2020-07-13 | 2020-07-13 | COMP | 2021-06-11 | COMP | 2021-07-03 | COMP | 2021-08-26 | COMP | 2021-09-14 | COMP | Rule 15/16 | 67 | 104 | 231 | 16 | 38 | 13 | 465
17633 | 2019-11-07 | 2020-02-24 | 2020-05-03 | 2020-05-03 | COMP | 2020-07-03 | COMP | 2020-08-20 | COMP | 2020-09-22 | COMP | 2020-12-02 | COMP | Rule 15/16 | 71 | 50 | 44 | 35 | 23 | 49 | 268
17716 | 2019-11-07 | 2020-02-25 | 2020-04-07 | 2020-05-21 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-16 | COMP | 2020-07-03 | COMP | Rule 16 | 72 | 31 | 7 | 1 | 12 | 14 | 164
17746 | 2019-11-07 | 2020-02-25 | 2020-06-15 | 2020-06-15 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2021-01-21 | COMP | 2021-02-05 | COMP | Rule 16 | 72 | 79 | 31 | 1 | 122 | 12 | 312
18129 | 2019-11-07 | 2020-03-11 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-11-02 | COMP | 2020-12-08 | COMP | Rule 16 | 83 | 70 | 28 | 1 | 71 | 24 | 272
18241 | 2019-11-07 | 2020-03-16 | 2020-08-12 | 2020-08-12 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2021-04-15 | COMP | 2021-06-07 | COMP | Rule 16 | 86 | 107 | 23 | 1 | 147 | 37 | 396
18269 | 2019-11-07 | 2020-03-17 | 2020-07-20 | 2020-07-20 | COMP | 2020-11-04 | COMP | 2020-11-13 | COMP | 2021-06-10 | COMP | 2021-06-22 | COMP | Rule 16 | 87 | 89 | 77 | 7 | 143 | 9 | 407
18443 | 2019-11-07 | 2020-03-26 | 2020-07-26 | 2020-07-26 | COMP | 2020-08-19 | COMP | 2020-09-20 | COMP | 2020-09-21 | COMP | 2020-10-20 | COMP | Rule 16 | 94 | 86 | 18 | 22 | 1 | 22 | 240
18617 | 2019-11-07 | 2020-03-31 | 2020-04-23 | 2022-04-05 | COMP | 2022-04-27 | COMP | 2020-07-31 | COMP | 2023-10-16 | COMP | 2023-12-11 | COMP | Rule 16 | 97 | 18 | 17 |  | 806 | 38 | 1026
18663 | 2019-11-07 | 2020-04-01 | 2020-07-17 | 2020-07-17 | COMP | 2020-08-31 | COMP | 2020-09-22 | COMP | 2022-02-10 | COMP | 2022-02-28 | COMP | Other | 98 | 77 | 32 | 16 | 349 | 12 | 579
19271 | 2019-11-07 | 2020-04-29 | 2020-07-27 | 2020-07-27 | COMP | 2022-03-25 | COMP | 2022-03-25 | COMP | 2022-04-05 | COMP | 2022-06-15 | COMP | Rule 16 | 118 | 63 | 419 | 1 | 8 | 51 | 655
19821 | 2019-11-07 | 2020-05-23 | 2020-09-10 | 2020-09-10 | COMP | 2020-10-15 | COMP | 2020-10-20 | COMP | 2020-11-16 | COMP | 2020-12-15 | COMP | Rule 16 | 135 | 77 | 26 | 4 | 19 | 20 | 277
15624 | 2019-11-08 | 2019-11-12 | 2020-03-25 | 2020-05-27 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-09-12 | COMP | Rule 16 | 2 | 91 | 31 | 1 | 1 | 47 | 212
15732 | 2019-11-08 | 2019-11-19 | 2020-01-06 | 2020-01-06 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-03-09 | COMP | 2020-03-23 | COMP | Rule 16 | 7 | 31 | 26 | 1 | 19 | 11 | 90
15733 | 2019-11-08 | 2019-11-19 | 2020-01-07 | 2020-01-07 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-03-09 | COMP | 2020-03-25 | COMP | Rule 16 | 7 | 32 | 25 | 1 | 19 | 13 | 92
15860 | 2019-11-08 | 2019-11-25 | 2020-02-24 | 2020-02-28 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-06-23 | COMP | 2020-07-02 | COMP | Rule 16 | 11 | 60 | 16 | 1 | 67 | 8 | 162
15873 | 2019-11-08 | 2019-11-26 | 2020-01-02 | 2020-01-02 | COMP | 2020-02-11 | COMP | 2020-02-11 | COMP | 2020-03-04 | COMP | 2020-04-08 | COMP | Rule 16 | 12 | 24 | 28 | 1 | 16 | 26 | 102
15874 | 2019-11-08 | 2019-11-25 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-10 | COMP | 2020-03-20 | COMP | 2023-11-13 | INPR | 2020-05-11 | COMP | Rule 15/16 | 11 | 55 | 17 | 9 |  |  | 125
16014 | 2019-11-08 | 2019-12-04 | 2019-12-21 | 2019-12-21 | COMP | 2020-03-12 | COMP | 2020-03-12 | INPR | 2020-03-23 | COMP | 2020-01-22 | COMP | Rule 16 | 16 | 13 | 55 |  |  |  | 48
16085 | 2019-11-08 | 2019-12-09 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-21 | COMP | 2020-06-09 | COMP | 2020-08-07 | COMP | 2020-09-01 | COMP | Rule 16 | 19 | 85 | 9 | 35 | 44 | 18 | 205
16543 | 2019-11-08 | 2020-01-07 | 2020-03-12 | 2020-03-12 | COMP | 2021-01-20 | COMP | 2021-01-23 | COMP | 2021-05-25 | COMP | 2021-08-01 | COMP | Rule 16 | 38 | 46 | 217 | 3 | 86 | 47 | 433
16644 | 2019-11-08 | 2020-01-09 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2021-10-23 | INPR | 2020-04-29 | COMP | Rule 16 | 40 | 49 | 25 | 1 |  |  | 117
16653 | 2019-11-08 | 2020-01-09 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-06-08 | COMP | 2020-07-08 | COMP | Rule 16 | 40 | 75 | 12 | 1 | 20 | 23 | 166
16749 | 2019-11-08 | 2020-01-15 | 2020-03-06 | 2020-03-06 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-12 | COMP | 2020-06-16 | COMP | Rule 16 | 44 | 36 | 63 | 1 | 8 | 3 | 150
16753 | 2019-11-08 | 2020-01-14 | 2020-07-21 | 2020-07-21 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2020-12-15 | COMP | 2021-02-08 | COMP | Rule 16 | 43 | 133 | 78 | 1 | 25 | 37 | 312
16754 | 2019-11-08 | 2020-01-14 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-26 | COMP | 2020-06-02 | COMP | 2020-06-23 | COMP | 2020-07-22 | COMP | Rule 16 | 43 | 60 | 34 | 6 | 16 | 22 | 176
16765 | 2019-11-08 | 2020-01-14 | 2020-02-20 | 2020-02-28 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | Rule 16 | 43 | 26 | 16 | 1 | 97 | 1 | 185
16773 | 2019-11-08 | 2020-01-15 | 2020-05-30 | 2020-05-30 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-08-17 | COMP | 2020-10-08 | COMP | Rule 16 | 44 | 95 | 29 | 1 | 28 | 38 | 231
16777 | 2019-11-08 | 2020-01-15 | 2020-02-22 | 2020-02-22 | COMP | 2020-04-01 | COMP | 2020-05-05 | COMP | 2021-06-28 | COMP | 2021-07-06 | COMP | Rule 16 | 44 | 26 | 28 | 25 | 290 | 6 | 415
16822 | 2019-11-08 | 2020-01-17 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-07-07 | COMP | 2020-07-28 | COMP | Rule 16 | 46 | 91 | 8 | 1 | 23 | 16 | 180
16851 | 2019-11-08 | 2020-01-21 | 2020-02-17 | 2020-02-17 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-06-24 | COMP | 2020-06-12 | COMP | Rule 16 | 47 | 19 | 29 | 1 | 63 |  | 148
16940 | 2019-11-08 | 2020-01-24 | 2020-03-22 | 2021-04-30 | COMP | 2021-08-06 | COMP | 2023-04-23 | COMP | 2023-04-19 | COMP | 2023-07-11 | COMP | Rule 15/16 | 50 | 40 | 69 | 429 | 0 | 54 | 920
16944 | 2019-11-08 | 2020-01-24 | 2020-04-20 | 2020-04-20 | COMP | 2020-04-24 | NOTN | 2020-04-24 | COMP | 2020-06-09 | COMP | 2020-07-01 | COMP | Other | 50 | 61 |  | 5 | 32 | 17 | 161
16968 | 2019-11-08 | 2020-01-27 | 2020-04-29 | 2020-04-29 | COMP | 2020-07-16 | COMP | 2020-08-10 | COMP | 2020-07-17 | COMP | 2020-08-31 | COMP | Rule 16 | 51 | 67 | 56 | 18 | 0 | 16 | 204
17001 | 2019-11-08 | 2020-01-27 | 2020-04-22 | 2020-04-22 | COMP | 2020-04-24 | COMP | 2020-05-08 | COMP | 2020-05-11 | COMP | 2020-06-12 | COMP | Rule 16 | 51 | 62 | 3 | 11 | 2 | 24 | 148
17081 | 2019-11-08 | 2020-01-29 | 2020-02-26 | 2020-02-26 | COMP | 2020-06-01 | COMP | 2020-09-04 | COMP | 2020-11-10 | COMP | 2021-01-06 | COMP | Rule 15/16 | 53 | 20 | 68 | 70 | 47 | 37 | 290
17840 | 2019-11-08 | 2020-03-02 | 2020-10-10 | 2020-10-12 | COMP | 2020-10-27 | COMP | 2020-11-03 | COMP | 2020-10-26 | COMP | 2020-12-17 | COMP | Rule 16 | 75 | 158 | 12 | 6 | 0 | 30 | 278
17908 | 2019-11-08 | 2020-03-04 | 2020-08-04 | 2020-08-04 | COMP | 2021-01-20 | COMP | 2020-11-20 | COMP | 2020-12-16 | COMP | 2021-02-18 | COMP | Rule 15/16 | 77 | 109 | 115 |  | 17 | 43 | 319
18159 | 2019-11-08 | 2020-03-13 | 2020-09-21 | 2020-09-21 | COMP | 2020-10-02 | COMP | 2021-03-05 | COMP | 2021-02-03 | COMP | 2021-04-02 | COMP | Rule 15/16 | 84 | 135 | 10 | 104 | 0 | 21 | 350
18671 | 2019-11-08 | 2020-04-02 | 2020-12-28 | 2020-12-28 | COMP | 2021-01-20 | COMP | 2021-07-21 | INPR | 2023-01-28 | REQD | 2021-08-05 | COMP | Rule 16 | 98 | 187 | 16 |  |  |  | 437
18682 | 2019-11-08 | 2020-04-03 | 2020-04-26 | 2020-04-26 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-07-30 | COMP | 2020-09-18 | COMP | Rule 16 | 99 | 16 | 53 | 1 | 16 | 36 | 217
18996 | 2019-11-08 | 2020-04-16 | 2020-12-02 | 2020-12-02 | COMP | 2021-02-08 | COMP | 2022-02-10 | COMP | 2022-02-03 | COMP | 2022-03-04 | COMP | Rule 16 | 108 | 160 | 46 | 256 | 0 | 16 | 582
19053 | 2019-11-08 | 2020-04-20 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-12 | COMP | 2020-06-16 | COMP |  | INPR | 2020-06-26 | COMP | Rule 16 | 110 | 20 | 20 | 3 |  |  | 158
19429 | 2019-11-08 | 2020-05-06 | 2020-10-04 | 2020-10-04 | COMP | 2020-10-29 | COMP | 2020-12-08 | COMP | 2020-12-28 | COMP | 2021-01-12 | COMP | Rule 16 | 122 | 106 | 19 | 26 | 14 | 11 | 294
17090 | 2019-11-09 | 2020-01-30 | 2021-02-18 | 2021-02-18 | COMP | 2021-05-14 | COMP | 2021-10-12 | COMP | 2021-05-06 | COMP | 2022-01-20 | COMP | Rule 15/16 | 53 | 266 | 62 | 105 | 0 | 69 | 551
16312 | 2019-11-10 | 2019-12-20 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-24 | COMP | 2020-02-24 | COMP | 2021-02-17 | COMP | 2021-02-21 | COMP | Rule 16 | 27 | 29 | 15 | 1 | 249 | 3 | 319
16712 | 2019-11-10 | 2020-01-14 | 2020-04-21 | 2020-04-21 | COMP | 2020-05-06 | COMP | 2020-05-23 | COMP | 2020-06-02 | COMP | 2020-06-05 | COMP | Rule 16 | 42 | 69 | 12 | 13 | 6 | 4 | 142
18160 | 2019-11-10 | 2020-03-13 | 2020-07-24 | 2021-12-06 | COMP | 2022-08-05 | COMP | 2022-09-12 | COMP | 2023-03-11 | COMP | 2023-07-31 | COMP | Rule 15/16 | 83 | 95 | 170 | 26 | 123 | 98 | 933
15711 | 2019-11-11 | 2019-11-18 | 2020-09-18 | 2020-09-18 | COMP | 2020-12-21 | COMP | 2021-04-09 | COMP | 2021-04-05 | COMP | 2021-05-25 | COMP | Rule 15/16 | 5 | 212 | 64 | 76 | 0 | 33 | 386
15735 | 2019-11-11 | 2019-11-19 | 2020-01-11 | 2020-01-14 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-03-12 | COMP | 2020-03-23 | COMP | Rule 16 | 6 | 35 | 9 | 1 | 33 | 8 | 89
15815 | 2019-11-11 | 2019-11-22 | 2020-04-08 | 2020-04-08 | COMP | 2020-11-03 | COMP | 2020-11-03 | COMP | 2021-01-08 | COMP | 2021-02-25 | COMP | Rule 16 | 9 | 93 | 148 | 1 | 44 | 33 | 323
15936 | 2019-11-11 | 2019-12-02 | 2020-02-03 | 2020-03-08 | COMP | 2020-03-31 | COMP | 2020-04-06 | COMP | 2020-11-30 | COMP | 2021-01-13 | COMP | Rule 16 | 13 | 43 | 17 | 5 | 166 | 31 | 294
16124 | 2019-11-11 | 2019-12-10 | 2020-10-16 | 2020-10-16 | COMP | 2021-06-17 | COMP | 2021-07-03 | COMP | 2022-02-15 | COMP | 2022-09-28 | COMP | Rule 15/16 | 19 | 218 | 167 | 12 | 156 | 157 | 725
16645 | 2019-11-11 | 2020-01-09 | 2020-05-26 | 2020-05-26 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2021-03-02 | COMP | 2021-04-20 | COMP | Rule 16 | 39 | 96 | 53 | 1 | 141 | 36 | 361
17004 | 2019-11-11 | 2020-01-27 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-19 | COMP | 2020-10-15 | COMP | 2021-03-12 | COMP | 2021-05-07 | COMP | Rule 15/16 | 50 | 63 | 19 | 106 | 100 | 41 | 374
17635 | 2019-11-11 | 2020-02-25 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-25 | COMP | 2020-06-25 | COMP | 2020-08-06 | COMP | 2020-08-10 | COMP | Rule 16 | 70 | 51 | 37 | 1 | 31 | 3 | 188
18045 | 2019-11-11 | 2020-03-10 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-12-01 | COMP | 2020-12-18 | COMP | Rule 16 | 80 | 47 | 7 | 1 | 134 | 14 | 278
18601 | 2019-11-11 | 2020-03-30 | 2020-11-20 | 2020-11-20 | COMP | 2021-02-10 | COMP | 2021-02-10 | COMP | 2022-04-17 | INPR | 2021-04-02 | COMP | Rule 16 | 94 | 167 | 54 | 1 |  |  | 349
18833 | 2019-11-11 | 2020-04-09 | 2020-06-02 | 2020-09-26 | COMP | 2020-10-05 | COMP | 2020-10-05 | COMP | 2020-10-26 | COMP | 2020-11-06 | COMP | Rule 16 | 102 | 38 | 6 | 1 | 16 | 10 | 251
18855 | 2019-11-11 | 2020-04-09 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-28 | COMP | 2020-05-19 | COMP | 2020-05-22 | COMP | 2020-05-26 | COMP | Rule 16 | 102 | 3 | 12 | 16 | 4 | 2 | 134
18903 | 2019-11-11 | 2020-04-10 | 2020-05-13 | 2020-05-13 | COMP | 2021-03-12 | COMP | 2021-05-04 | COMP | 2021-03-14 | COMP | 2021-06-02 | COMP | Rule 15/16 | 103 | 24 | 209 | 38 | 0 | 21 | 391
19292 | 2019-11-11 | 2020-04-28 | 2021-03-13 | 2021-03-17 | COMP | 2021-04-02 | COMP | 2021-09-13 | COMP | 2021-10-06 | COMP | 2021-11-05 | COMP | Rule 16 | 115 | 220 | 13 | 114 | 18 | 23 | 501
19928 | 2019-11-11 | 2020-05-28 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-12 | COMP | 2020-08-18 | COMP | 2020-09-29 | COMP | 2021-01-13 | COMP | Rule 16 | 136 | 49 | 7 | 5 | 30 | 72 | 294
22713 | 2019-11-11 | 2020-10-07 | 2021-06-09 | 2021-08-06 | COMP | 2021-10-22 | COMP | 2022-09-02 | COMP | 2022-10-05 | COMP | 2022-12-21 | COMP | Rule 15/16 | 229 | 168 | 55 | 218 | 23 | 53 | 782
23294 | 2019-11-11 | 2020-10-30 | 2020-11-05 | 2020-11-05 | COMP | 2020-12-11 | NOTN | 2020-12-11 | COMP | 2020-12-29 | COMP | 2021-01-13 | COMP | Other | 246 | 5 |  | 24 | 12 | 11 | 294
4252 | 2019-11-12 | 2019-11-19 | [7 empty] | 2019-11-19 | COMP | 2020-02-06 | COMP | Other | 6 | [5 empty] | 58
15649 | 2019-11-12 | 2019-11-13 | 2019-12-09 | 2019-12-09 | COMP | 2019-12-16 | COMP | 2020-01-22 | INPR | 2020-05-31 | REQD | 2020-02-10 | COMP | Rule 16 | 2 | 17 | 6 |  |  |  | 60
15650 | 2019-11-12 | 2019-11-13 | 2019-12-09 | 2019-12-19 | COMP | 2019-12-23 | COMP | 2020-01-22 | INPR | 2020-05-31 | REQD | 2020-02-10 | COMP | Rule 16 | 2 | 17 | 3 |  |  |  | 60
16000 | 2019-11-12 | 2019-12-05 | 2020-03-18 | 2020-03-18 | COMP | 2020-08-11 | COMP | 2020-08-13 | COMP | 2020-08-14 | COMP | 2020-09-11 | COMP | Rule 16 | 16 | 71 | 104 | 3 | 2 | 20 | 211
16093 | 2019-11-12 | 2019-12-09 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-04-16 | COMP | 2020-07-10 | COMP | Rule 16 | 18 | 69 | 21 | 1 | 2 | 61 | 167
16212 | 2019-11-12 | 2019-12-15 | 2020-01-24 | 2020-01-24 | COMP | 2020-02-07 | COMP | 2020-02-26 | COMP | 2023-04-30 | INPR | 2020-08-10 | COMP | Rule 16 | 22 | 27 | 11 | 13 |  |  | 188
16435 | 2019-11-12 | 2019-12-31 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-10 | COMP | 2020-04-16 | COMP | 2020-05-19 | COMP | 2020-06-26 | COMP | Rule 16 | 33 | 64 | 8 | 5 | 24 | 28 | 157
16591 | 2019-11-12 | 2020-01-09 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-13 | NOTN | 2020-05-21 | COMP | 2020-06-09 | COMP | 2020-07-16 | COMP | Other | 39 | 71 |  | 24 | 13 | 28 | 171
16756 | 2019-11-12 | 2020-01-14 | 2020-08-03 | 2021-12-12 | COMP | 2021-12-20 | COMP | 2022-02-19 | COMP | 2022-02-08 | COMP | 2022-02-24 | COMP | Rule 16 | 42 | 142 | 6 | 44 | 0 | 3 | 575
16792 | 2019-11-12 | 2020-01-15 | 2020-06-13 | 2020-06-13 | COMP | 2020-07-21 | COMP | 2020-12-28 | COMP | 2021-01-21 | COMP | 2021-02-18 | COMP | Rule 16 | 43 | 105 | 27 | 110 | 17 | 20 | 318
17224 | 2019-11-12 | 2020-02-05 | 2020-03-15 | 2020-03-19 | COMP | 2020-04-01 | COMP | 2020-04-06 | COMP | 2020-04-20 | COMP | 2020-05-27 | COMP | Rule 16 | 57 | 27 | 10 | 4 | 11 | 27 | 135
17318 | 2019-11-12 | 2020-02-10 | 2020-03-20 | 2020-03-20 | COMP | 2020-04-03 | COMP | 2020-07-20 | COMP | 2020-05-28 | COMP | 2020-08-26 | COMP | Rule 16 | 60 | 29 | 11 | 76 | 0 | 28 | 200
17484 | 2019-11-12 | 2020-02-18 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-24 | NOTN | 2020-06-12 | COMP | 2020-03-24 | COMP | 2020-06-30 | COMP | Other | 65 | 20 |  | 64 | 0 | 13 | 159
17642 | 2019-11-12 | 2020-02-24 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-14 | COMP | 2020-07-17 | COMP | 2020-10-05 | COMP | 2020-12-11 | COMP | Rule 16 | 69 | 44 | 16 | 46 | 56 | 47 | 273
17794 | 2019-11-12 | 2020-02-28 | 2020-07-30 | 2020-07-30 | COMP | 2020-09-21 | COMP | 2020-11-02 | COMP | 2020-11-16 | NOTN | 2021-01-14 | COMP | Rule 16 | 73 | 109 | 37 | 31 |  |  | 295
17879 | 2019-11-12 | 2020-03-02 | 2020-03-17 | 2020-03-17 | COMP | 2020-03-25 | COMP | 2020-03-25 | COMP | 2021-10-23 | INPR | 2020-04-30 | COMP | Rule 16 | 74 | 12 | 7 | 1 |  |  | 117
18205 | 2019-11-12 | 2020-03-16 | 2020-07-22 | 2020-07-22 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-09-29 | COMP | 2020-11-13 | COMP | Rule 16 | 84 | 92 | 6 | 1 | 44 | 33 | 255
18695 | 2019-11-12 | 2020-04-03 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-08-13 | COMP | 2020-09-29 | COMP | Rule 16 | 98 | 67 | 7 | 1 | 22 | 33 | 223
18804 | 2019-11-12 | 2020-04-07 | 2020-10-05 | 2020-10-05 | COMP | 2021-01-19 | COMP | 2021-01-20 | COMP | 2022-11-07 | COMP | 2022-12-21 | COMP | Rule 16 | 100 | 128 | 71 | 2 | 456 | 30 | 782
19176 | 2019-11-12 | 2020-04-23 | 2020-07-10 | 2020-07-10 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | 2021-06-04 | COMP | 2021-06-24 | COMP | Rule 16 | 112 | 56 | 131 | 1 | 97 | 15 | 407
20717 | 2019-11-12 | 2020-07-02 | 2020-09-30 | 2021-10-20 | COMP | 2022-01-25 | COMP | 2021-01-11 | COMP | 2022-04-19 | COMP | 2022-05-31 | COMP | Rule 16 | 161 | 64 | 66 |  | 322 | 30 | 642
15675 | 2019-11-13 | 2019-11-14 | 2020-02-28 | 2020-02-28 | COMP | 2020-04-29 | COMP | 2020-04-30 | COMP | 2020-08-24 | COMP | 2020-09-28 | COMP | Rule 16 | 2 | 71 | 44 | 2 | 82 | 25 | 221
15921 | 2019-11-13 | 2019-12-02 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-06-08 | COMP | Rule 15/16 | 12 | 52 | 16 | 1 | 1 | 65 | 142
15940 | 2019-11-13 | 2019-12-02 | 2020-06-25 | 2020-11-10 | COMP | 2021-02-26 | COMP | 2021-02-26 | COMP | 2021-03-16 | COMP | 2021-04-02 | COMP | Rule 16 | 12 | 144 | 72 | 1 | 13 | 14 | 348
15978 | 2019-11-13 | 2019-12-03 | 2020-04-17 | 2020-04-17 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-08-11 | COMP | 2020-10-23 | COMP | Rule 16 | 13 | 95 | 38 | 1 | 45 | 53 | 240
16076 | 2019-11-13 | 2019-12-09 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-05-18 | COMP | 2020-06-02 | COMP | Rule 16 | 17 | 52 | 6 | 1 | 56 | 11 | 138
16150 | 2019-11-13 | 2019-12-12 | 2020-11-21 | 2020-11-21 | COMP | 2021-06-24 | COMP | 2023-03-13 | COMP |  | INPR | 2023-04-19 | COMP | Rule 16 | 20 | 240 | 147 | 430 |  |  | 862
16163 | 2019-11-13 | 2019-12-12 | 2020-05-07 | 2020-05-07 | COMP | 2020-06-19 | COMP | 2020-07-13 | COMP | 2020-06-30 | COMP | 2020-07-30 | COMP | Rule 16 | 20 | 102 | 31 | 17 | 0 | 14 | 180
16302 | 2019-11-13 | 2019-12-19 | 2020-03-20 | 2020-03-20 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-11-17 | COMP | Rule 16 | 25 | 63 | 117 | 1 | 1 | 54 | 256
16378 | 2019-11-13 | 2019-12-23 | 2020-04-29 | 2020-09-21 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2021-06-21 | COMP | 2021-08-06 | COMP | Rule 16 | 27 | 89 |  | 1 | 234 | 34 | 436
16413 | 2019-11-13 | 2019-12-27 | 2020-01-09 | 2020-01-09 | COMP | 2020-08-11 | COMP | 2020-08-11 | INPR | 2022-08-21 | REQD | 2021-08-17 | COMP | Rule 16 | 30 | 9 | 151 |  |  |  | 443
16441 | 2019-11-13 | 2019-12-31 | 2020-01-11 | 2020-01-11 | COMP | 2020-01-29 | COMP | 2020-02-10 | COMP | 2020-02-14 | COMP | 2020-03-13 | COMP | Rule 16 | 32 | 8 | 12 | 9 | 5 | 20 | 82
16560 | 2019-11-13 | 2020-01-08 | 2020-02-11 | 2020-02-11 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-03-24 | COMP | 2020-04-01 | COMP | Rule 16 | 37 | 24 | 12 | 1 | 19 | 7 | 95
16584 | 2019-11-13 | 2020-01-08 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-07 | COMP | 2020-05-11 | COMP | 2020-04-30 | COMP | 2020-06-12 | COMP | Rule 16 | 37 | 49 | 15 | 25 | 0 | 24 | 146
16630 | 2019-11-13 | 2020-01-09 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-05-18 | COMP | 2020-06-01 | COMP | Rule 16 | 38 | 41 | 22 | 1 | 30 | 10 | 137
16819 | 2019-11-13 | 2020-01-17 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-05-23 | COMP | 2020-09-15 | COMP | Rule 16 | 44 | 62 | 20 | 1 | 9 | 80 | 212
17045 | 2019-11-13 | 2020-01-29 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2022-01-30 | INPR | 2021-01-05 | COMP | Rule 16 | 51 | 81 | 7 | 1 |  |  | 287
17059 | 2019-11-13 | 2020-01-29 | 2020-04-11 | 2020-04-13 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-07-31 | COMP | 2020-08-21 | COMP | Rule 16 | 51 | 52 | 10 | 1 | 70 | 16 | 196
17094 | 2019-11-13 | 2020-02-01 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-11-22 | COMP | 2020-12-04 | COMP | Rule 16 | 53 | 81 | 4 | 1 | 123 | 8 | 267
17206 | 2019-11-13 | 2020-02-04 | 2020-07-28 | 2020-07-28 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-02-22 | COMP | 2021-03-23 | COMP | Rule 16 | 55 | 124 | 45 | 1 | 98 | 22 | 340
17273 | 2019-11-13 | 2020-02-07 | 2020-06-29 | 2021-04-29 | COMP | 2021-05-24 | COMP | 2022-07-05 | COMP | 2022-06-17 | COMP | 2022-08-08 | COMP | Rule 15/16 | 58 | 100 | 18 | 281 | 0 | 25 | 688
17276 | 2019-11-13 | 2020-02-06 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-15 | COMP | 2020-05-27 | COMP | 2020-06-23 | COMP | 2020-09-04 | COMP | Rule 16 | 57 | 32 | 18 | 30 | 20 | 54 | 206
17427 | 2019-11-13 | 2020-02-13 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-22 | COMP | 2020-10-21 | COMP | 2020-11-10 | COMP | 2020-12-03 | COMP | Rule 15/16 | 62 | 77 | 15 | 87 | 15 | 15 | 266
17480 | 2019-11-13 | 2020-02-18 | 2020-02-25 | 2020-03-16 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-05-04 | COMP | 2020-05-15 | COMP | Rule 16 | 64 | 6 | 24 | 1 | 13 | 10 | 127
17525 | 2019-11-13 | 2020-02-19 | 2020-07-27 | 2020-07-27 | COMP | 2021-04-26 | COMP | 2021-04-26 | COMP | 2023-03-23 | COMP | 2023-05-01 | COMP | Rule 15/16 | 65 | 113 | 188 | 1 | 480 | 28 | 870
17832 | 2019-11-13 | 2020-02-28 | 2020-04-20 | 2020-04-20 | COMP | 2020-07-21 | COMP | 2020-08-04 | COMP | 2020-07-22 | COMP | 2020-09-03 | COMP | Rule 16 | 72 | 37 | 66 | 11 | 0 | 23 | 205
17837 | 2019-11-13 | 2020-02-29 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-09 | COMP | 2020-07-23 | COMP | Rule 16 | 72 | 48 | 15 | 1 | 10 | 33 | 175
17956 | 2019-11-13 | 2020-03-05 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-05-14 | COMP | 2021-09-08 | COMP | Rule 16 | 76 | 50 | 29 | 1 | 0 | 306 | 458
18023 | 2019-11-13 | 2020-03-09 | 2020-03-27 | 2020-03-27 | COMP | 2020-04-09 | COMP | 2020-04-09 | NOTN | 2020-05-23 | COMP | 2020-07-22 | COMP | Rule 16 | 78 | 15 | 10 |  |  |  | 174
18328 | 2019-11-13 | 2020-03-19 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-12 | NOTN | 2020-06-12 | COMP | 2020-08-24 | COMP | 2020-10-13 | COMP | Other | 86 | 61 |  | 1 | 52 | 36 | 232
18586 | 2019-11-13 | 2020-03-30 | 2020-05-04 | 2020-07-22 | COMP | 2020-07-31 | COMP | 2020-07-28 | COMP | 2022-07-16 | INPR | 2020-07-29 | COMP | Rule 16 | 93 | 26 | 8 |  |  |  | 179
18978 | 2019-11-13 | 2020-04-15 | 2020-07-30 | 2022-01-11 | COMP | 2022-01-18 | COMP | 2023-11-13 | CANC | 2021-11-10 | COMP | 2022-02-25 | COMP | Rule 15/16 | 105 | 76 | 5 |  |  |  | 575
19199 | 2019-11-13 | 2020-04-23 | 2020-05-20 | 2020-05-20 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2022-03-29 | COMP | 2022-05-16 | COMP | Rule 16 | 111 | 20 | 114 | 1 | 355 | 35 | 631
19232 | 2019-11-13 | 2020-04-28 | 2020-06-03 | 2020-07-09 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-31 | COMP | 2020-09-11 | COMP | Rule 16 | 114 | 26 | 17 | 1 | 22 | 9 | 210
19362 | 2019-11-13 | 2020-05-04 | 2020-05-23 | 2020-05-23 | COMP | 2020-09-18 | COMP | 2021-02-17 | COMP | 2021-05-25 | COMP | 2021-07-06 | COMP | Rule 16 | 118 | 15 | 83 | 102 | 70 | 29 | 413
19519 | 2019-11-13 | 2020-05-11 | 2020-09-12 | 2020-09-12 | COMP | 2021-05-11 | COMP | 2021-09-01 | COMP | 2022-02-22 | COMP | 2022-03-27 | COMP | Rule 15/16 | 123 | 88 | 165 | 80 | 119 | 24 | 595
15837 | 2019-11-14 | 2019-11-23 | 2020-01-14 | 2020-01-14 | COMP | 2020-01-30 | COMP | 2020-05-01 | COMP | 2020-04-20 | COMP | 2020-06-29 | COMP | Rule 16 | 7 | 33 | 12 | 66 | 0 | 41 | 156
15872 | 2019-11-14 | 2019-11-26 | 2020-01-22 | 2020-01-22 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-16 | COMP | 2020-08-10 | COMP | Rule 16 | 9 | 37 | 89 | 1 | 15 | 40 | 186
16151 | 2019-11-14 | 2019-12-12 | 2020-02-07 | 2020-02-07 | COMP | 2020-03-04 | COMP | 2020-05-04 | COMP | 2020-07-03 | COMP | 2020-08-10 | COMP | Rule 15/16 | 19 | 39 | 18 | 44 | 44 | 27 | 186
16593 | 2019-11-14 | 2020-01-08 | 2020-02-19 | 2020-02-19 | COMP | 2020-02-21 | COMP | 2020-02-21 | INPR | 2020-02-25 | COMP | 2021-05-10 | COMP | Rule 16 | 36 | 29 | 3 |  |  |  | 373
16594 | 2019-11-14 | 2020-01-08 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-06 | NOTN | 2020-06-25 | COMP | 2020-04-06 | COMP | 2020-10-13 | COMP | Other | 36 | 62 |  | 58 | 0 | 78 | 231
17054 | 2019-11-14 | 2020-01-29 | 2020-06-02 | 2020-07-22 | COMP | 2020-07-27 | COMP | 2020-06-08 | COMP | 2020-08-04 | COMP | 2020-09-16 | COMP | Rule 16 | 50 | 88 | 4 |  | 42 | 31 | 212
17068 | 2019-11-14 | 2020-01-29 | 2020-12-08 | 2020-12-08 | COMP | 2021-01-13 | COMP | 2021-02-17 | COMP | 2021-01-15 | COMP | 2021-03-03 | COMP | Rule 16 | 50 | 219 | 25 | 24 | 0 | 11 | 325
17177 | 2019-11-14 | 2020-02-04 | 2020-07-21 | 2020-10-26 | COMP | 2020-12-30 | COMP | 2021-11-19 | COMP | 2021-11-16 | COMP | 2021-10-22 | COMP | Rule 15/16 | 54 | 119 | 44 | 226 | 0 |  | 489
17178 | 2019-11-14 | 2020-02-04 | 2020-07-21 | 2020-10-26 | COMP | 2021-02-18 | COMP | 2021-08-12 | COMP | 2021-11-16 | COMP | 2021-10-22 | COMP | Rule 15/16 | 54 | 119 | 77 | 124 | 67 |  | 489
17188 | 2019-11-14 | 2020-02-04 | 2020-05-30 | 2020-05-30 | COMP | 2020-06-13 | COMP | 2020-07-07 | COMP | 2020-07-16 | COMP | 2020-10-01 | COMP | Rule 16 | 54 | 82 | 10 | 17 | 8 | 55 | 223
17342 | 2019-11-14 | 2020-02-10 | 2020-04-01 | 2020-08-14 | COMP | 2021-01-13 | COMP | 2021-01-13 | COMP | 2021-05-12 | COMP | 2021-06-23 | COMP | Rule 15/16 | 58 | 37 | 103 | 1 | 84 | 30 | 404
17476 | 2019-11-14 | 2020-02-15 | 2020-06-12 | 2021-01-06 | COMP | 2021-01-28 | COMP | 2021-01-28 | COMP | 2022-04-06 | NOTN | 2022-04-26 | COMP | Rule 15/16 | 62 | 83 | 16 | 1 |  |  | 616
17539 | 2019-11-14 | 2020-02-19 | 2020-09-23 | 2020-09-23 | COMP | 2022-01-13 | COMP | 2023-02-07 | COMP | 2023-03-24 | COMP | 2023-06-23 | COMP | Rule 15/16 | 64 | 154 | 329 | 267 | 33 | 64 | 906
17645 | 2019-11-14 | 2020-02-24 | 2020-06-18 | 2020-06-18 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2020-12-11 | COMP | Rule 16 | 67 | 83 | 92 | 1 | 1 | 32 | 271
17740 | 2019-11-14 | 2020-02-25 | 2020-05-07 | 2020-05-07 | COMP | 2020-11-12 | COMP | 2020-11-12 | COMP | 2021-08-19 | COMP | 2021-09-28 | COMP | Rule 16 | 68 | 53 | 133 | 1 | 193 | 28 | 471
17874 | 2019-11-14 | 2020-03-02 | 2020-04-01 | 2020-04-01 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2021-06-16 | COMP | 2021-07-06 | COMP | Rule 15/16 | 72 | 23 | 94 | 1 | 213 | 14 | 412
17875 | 2019-11-14 | 2020-03-02 | 2020-04-03 | 2020-04-03 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2021-06-14 | COMP | 2021-07-06 | COMP | Rule 16 | 72 | 25 | 111 | 1 | 192 | 16 | 412
18060 | 2019-11-14 | 2020-03-10 | 2020-07-14 | 2021-05-24 | COMP | 2021-07-07 | COMP | 2021-11-04 | COMP | 2021-10-01 | COMP | 2022-01-28 | COMP | Other | 78 | 90 | 31 | 86 | 0 | 58 | 555
18515 | 2019-11-14 | 2020-03-26 | 2020-05-28 | 2020-07-20 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-09-18 | COMP | 2020-11-21 | COMP | Rule 16 | 90 | 45 | 59 | 1 | 0 | 30 | 258
18821 | 2019-11-14 | 2020-04-08 | 2020-06-23 | 2020-11-07 | COMP | 2020-11-16 | COMP | 2021-09-08 | COMP | 2021-08-31 | COMP | 2021-10-06 | COMP | Rule 16 | 99 | 54 | 5 | 204 | 0 | 21 | 477
19357 | 2019-11-14 | 2020-05-02 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-12 | COMP | 2020-11-20 | NOTN | 2020-11-20 | COMP | 2020-12-03 | COMP | Rule 16 | 116 | 10 | 20 |  |  |  | 265
19414 | 2019-11-14 | 2020-05-05 | 2020-06-01 | 2020-08-07 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-11-05 | COMP | 2020-11-19 | COMP | Rule 15/16 | 118 | 19 | 16 | 1 | 49 | 10 | 257
21314 | 2019-11-14 | 2020-07-31 | 2020-10-04 | 2020-10-04 | COMP | 2020-11-03 | COMP | 2020-11-03 | COMP | 2021-01-20 | COMP | 2021-02-13 | COMP | Rule 15/16 | 180 | 45 | 22 | 1 | 51 | 18 | 313
15689 | 2019-11-15 | 2019-11-15 | 2019-11-26 | 2019-11-26 | COMP | 2019-12-06 | COMP | 2019-12-11 | COMP | 2019-12-04 | COMP | 2020-01-06 | COMP | Rule 16 | 1 | 8 | 7 | 4 | 0 | 17 | 33
16067 | 2019-11-15 | 2019-12-09 | 2020-02-11 | 2020-02-11 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-03-13 | COMP | 2020-03-23 | COMP | Rule 16 | 15 | 44 | 13 | 1 | 11 | 7 | 86
16355 | 2019-11-15 | 2019-12-23 | 2020-03-24 | 2020-03-24 | COMP | 2021-03-25 | COMP | 2020-07-06 | COMP | 2021-06-14 | COMP | 2021-09-26 | COMP | Rule 15/16 | 25 | 63 | 254 |  | 237 | 73 | 468
16453 | 2019-11-15 | 2019-12-31 | 2020-10-31 | 2020-10-31 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP |  | INPR | 2021-01-14 | COMP | Rule 16 | 30 | 214 | 17 | 1 |  |  | 292
16738 | 2019-11-15 | 2020-01-15 | 2020-08-13 | 2020-08-31 | COMP | 2020-09-02 | COMP | 2021-01-06 | COMP | 2022-04-16 | INPR | 2021-01-10 | COMP | Rule 15/16 | 40 | 149 | 3 | 85 |  |  | 288
16980 | 2019-11-15 | 2020-01-28 | 2020-03-10 | 2020-03-10 | COMP | 2020-04-29 | COMP | 2020-05-06 | COMP | 2020-05-19 | COMP | 2020-07-06 | COMP | Rule 16 | 48 | 30 | 37 | 6 | 10 | 34 | 160
16982 | 2019-11-15 | 2020-01-28 | 2020-04-28 | 2020-04-28 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-06-03 | COMP | 2020-07-13 | COMP | Rule 16 | 48 | 65 | 23 | 1 | 4 | 29 | 165
16983 | 2019-11-15 | 2020-01-28 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-05-04 | COMP | 2020-08-05 | COMP | Rule 15/16 | 48 | 29 | 25 | 1 | 17 | 67 | 182
17115 | 2019-11-15 | 2020-01-31 | 2020-04-23 | 2020-04-23 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-08-08 | COMP | 2020-10-09 | COMP | Rule 16 | 51 | 59 | 73 | 1 | 4 | 44 | 228
17116 | 2019-11-15 | 2020-01-31 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-04 | COMP | 2020-08-17 | COMP | 2020-08-08 | COMP | 2020-09-22 | COMP | Rule 16 | 51 | 70 | 62 | 10 | 0 | 26 | 215
17118 | 2019-11-15 | 2020-01-31 | 2020-05-14 | 2020-05-14 | COMP | 2020-08-05 | COMP | 2020-09-04 | COMP | 2020-08-08 | COMP | 2020-12-07 | COMP | Rule 16 | 51 | 74 | 59 | 23 | 0 | 63 | 266
17425 | 2019-11-15 | 2020-02-13 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-15 | COMP | 2020-09-08 | COMP | 2020-09-04 | COMP | 2020-10-28 | COMP | Rule 16 | 60 | 73 | 14 | 61 | 0 | 37 | 241
17491 | 2019-11-15 | 2020-02-18 | 2020-06-05 | 2020-06-05 | COMP | 2020-07-06 | COMP | 2020-07-29 | COMP | 2020-10-27 | COMP | 2020-12-05 | COMP | Rule 15/16 | 62 | 78 | 22 | 18 | 64 | 26 | 265
18238 | 2019-11-15 | 2020-03-17 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-12 | COMP | 2020-07-30 | COMP | 2022-01-30 | INPR | 2020-12-17 | COMP | Rule 16 | 82 | 58 | 6 | 35 |  |  | 274
18422 | 2019-11-15 | 2020-03-23 | 2020-06-30 | 2020-06-30 | COMP | 2021-03-16 | NOTN | 2021-03-17 | COMP | 2021-03-16 | COMP | 2021-07-27 | COMP | Other | 86 | 71 |  | 179 | 0 | 93 | 426
29249 | 2019-11-15 | 2021-07-14 | 2021-12-02 | 2021-12-24 | COMP | 2022-01-19 | COMP | 2022-01-19 | COMP | 2022-03-01 | COMP | 2022-03-22 | COMP | Other | 417 | 98 | 18 | 1 | 29 | 16 | 590
15896 | 2019-11-16 | 2019-11-30 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-29 | COMP | 2020-06-11 | COMP | 2022-02-26 | INPR | 2020-10-23 | COMP | Rule 16 | 8 | 67 | 38 | 31 |  |  | 237
16191 | 2019-11-16 | 2019-12-14 | 2020-02-14 | 2020-02-14 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-03-31 | COMP | 2020-04-03 | COMP | Rule 16 | 18 | 42 | 18 | 1 | 15 | 4 | 94
16485 | 2019-11-16 | 2020-01-02 | 2020-07-10 |  | REQD |  | REQD | 2020-09-28 | COMP | 2020-10-06 | COMP | 2020-11-12 | COMP | Unknown | 30 |  |  |  | 7 | 27 | 250
16916 | 2019-11-16 | 2020-01-23 | 2020-02-19 | 2020-02-19 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2022-01-30 | INPR | 2020-06-17 | COMP | Rule 16 | 44 | 19 | 16 | 1 |  |  | 146
17147 | 2019-11-16 | 2020-02-01 | 2020-12-11 | 2020-12-11 | COMP | 2021-05-05 | COMP | 2021-12-06 | COMP | 2022-02-04 | COMP | 2022-03-22 | COMP | Rule 15/16 | 50 | 219 | 100 | 148 | 44 | 32 | 589
18180 | 2019-11-16 | 2020-03-13 | 2020-08-20 | 2020-08-20 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP | 2022-09-13 | COMP | 2022-09-19 | COMP | Rule 16 | 79 | 114 | 115 | 1 | 405 | 5 | 714
19204 | 2019-11-16 | 2020-04-23 | 2020-07-30 | 2020-07-30 | COMP | 2020-08-28 | COMP | 2020-11-23 | COMP | 2020-08-07 | COMP | 2020-12-18 | COMP | Rule 16 | 108 | 70 | 22 | 60 | 0 | 18 | 274
19359 | 2019-11-16 | 2020-05-02 | 2020-08-14 | 2020-08-14 | COMP | 2020-09-11 | COMP | 2020-09-11 | COMP | 2020-11-12 | COMP | 2021-02-03 | COMP | Rule 16 | 114 | 74 | 20 | 1 | 44 | 55 | 304
15712 | 2019-11-17 | 2019-11-18 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-21 | COMP | 2020-12-07 | COMP | 2021-05-03 | COMP | 2021-06-01 | COMP | Rule 15/16 | 1 | 153 | 18 | 96 | 102 | 21 | 386
15911 | 2019-11-18 | 2019-11-27 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-02 | COMP | 2020-08-26 | COMP | 2022-02-26 | INPR | 2020-09-25 | COMP | Rule 16 | 8 | 141 | 10 | 40 |  |  | 217
16100 | 2019-11-18 | 2019-12-09 | 2020-04-30 | 2021-12-21 | COMP | 2022-01-20 | COMP | 2021-03-28 | COMP | 2021-06-16 | COMP | 2022-02-18 | COMP | Rule 16 | 14 | 100 | 22 |  | 57 | 172 | 568
16103 | 2019-11-18 | 2019-12-09 | 2020-05-14 | 2020-05-14 | COMP | 2020-05-21 | NOTN | 2020-05-21 | COMP | 2020-05-26 | COMP | 2020-09-21 | COMP | Other | 14 | 110 |  | 6 | 3 | 84 | 213
16128 | 2019-11-18 | 2019-12-11 | 2019-12-18 | 2019-12-18 | COMP | 2019-12-27 | COMP | 2019-12-30 | COMP | 2019-12-27 | COMP | 2020-02-19 | COMP | Rule 16 | 16 | 6 | 7 | 2 | 0 | 35 | 62
16153 | 2019-11-18 | 2019-12-12 | 2020-03-18 | 2020-03-18 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-09-14 | COMP | Rule 16 | 17 | 66 | 81 | 1 | 1 | 47 | 208
16217 | 2019-11-18 | 2019-12-16 | 2020-03-27 | 2020-03-27 | COMP | 2020-05-29 | COMP | 2020-06-04 | COMP | 2020-06-03 | COMP | 2020-07-08 | COMP | Rule 16 | 19 | 71 | 45 | 5 | 0 | 25 | 161
16330 | 2019-11-18 | 2019-12-20 | 2020-04-13 | 2020-04-13 | COMP | 2020-11-13 | COMP | 2021-02-19 | COMP | 2021-01-22 | COMP | 2021-02-24 | COMP | Rule 16 | 23 | 78 | 152 | 65 | 0 | 4 | 318
16338 | 2019-11-18 | 2019-12-20 | 2020-04-24 | 2020-05-07 | COMP | 2020-08-04 | COMP | 2023-11-14 | COMP | 2023-09-25 | COMP | 2023-11-30 | COMP | Rule 16 | 23 | 87 | 63 | 824 | 0 | 11 | 1013
16742 | 2019-11-18 | 2020-01-14 | 2020-04-03 | 2020-04-03 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-11-04 | COMP | 2020-12-10 | COMP | Rule 16 | 38 | 57 | 28 | 1 | 125 | 24 | 268
16744 | 2019-11-18 | 2020-01-14 | 2020-03-28 | 2020-03-28 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-06-10 | COMP | 2020-07-17 | COMP | Rule 16 | 38 | 52 | 22 | 1 | 31 | 28 | 168
16768 | 2019-11-18 | 2020-01-15 | 2020-03-18 | 2020-03-18 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-09-08 | COMP | 2020-11-06 | COMP | Rule 16 | 39 | 44 | 80 | 1 | 44 | 44 | 247
16799 | 2019-11-18 | 2020-01-16 | 2020-02-10 | 2020-02-10 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-06-09 | COMP | 2020-07-03 | COMP | Rule 15/16 | 40 | 17 | 69 | 1 | 17 | 19 | 158
16814 | 2019-11-18 | 2020-01-16 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-06 | COMP | 2020-03-06 | NOTN | 2020-03-16 | COMP | 2020-03-23 | COMP | Rule 16 | 40 | 26 | 10 |  |  |  | 85
17222 | 2019-11-18 | 2020-02-05 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-04 | COMP | 2020-06-15 | COMP | 2020-06-08 | COMP | 2020-08-26 | COMP | Rule 16 | 53 | 81 | 5 | 8 | 0 | 53 | 196
17248 | 2019-11-18 | 2020-02-06 | 2020-06-15 | 2020-06-15 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2021-01-12 | COMP | 2021-02-17 | COMP | Rule 15/16 | 54 | 91 | 61 | 1 | 86 | 25 | 313
17329 | 2019-11-18 | 2020-02-10 | 2020-04-17 | 2020-04-17 | COMP | 2020-04-29 | COMP | 2020-08-21 | COMP | 2020-11-23 | COMP | 2020-11-04 | COMP | Rule 15/16 | 56 | 49 | 9 | 82 | 65 |  | 245
17416 | 2019-11-18 | 2020-02-13 | 2020-04-24 | 2020-04-24 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-06-23 | COMP | 2020-07-13 | COMP | Rule 16 | 59 | 51 | 32 | 1 | 11 | 15 | 164
17519 | 2019-11-18 | 2020-02-19 | 2020-04-14 | 2020-04-14 | COMP | 2020-05-05 | COMP | 2020-04-24 | COMP | 2020-07-17 | COMP | 2020-08-12 | COMP | Rule 15/16 | 62 | 40 | 16 |  | 60 | 19 | 186
17564 | 2019-11-18 | 2020-02-20 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-06-17 | COMP | 2020-07-26 | COMP | Rule 16 | 63 | 35 | 23 | 1 | 28 | 28 | 173
17903 | 2019-11-18 | 2020-03-03 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-22 | COMP | 2020-08-12 | COMP | 2020-08-25 | COMP | 2020-12-08 | COMP | Rule 16 | 71 | 79 | 23 | 16 | 10 | 72 | 266
18233 | 2019-11-18 | 2020-03-16 | 2020-05-28 | 2020-05-28 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-14 | COMP | Rule 16 | 80 | 53 | 33 | 1 | 1 | 2 | 165
18274 | 2019-11-18 | 2020-03-18 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-12 | COMP | 2020-07-31 | COMP | 2020-08-24 | COMP | 2020-09-10 | COMP | Rule 16 | 82 | 48 | 15 | 36 | 17 | 13 | 206
18354 | 2019-11-18 | 2020-03-20 | 2020-08-14 | 2020-08-14 | COMP | 2020-09-24 | COMP | 2021-01-05 | COMP | 2021-09-29 | COMP | 2021-12-04 | COMP | Rule 15/16 | 84 | 105 | 29 | 69 | 187 | 45 | 514
18459 | 2019-11-18 | 2020-03-25 | 2021-02-26 | 2021-02-26 | COMP | 2021-04-06 | COMP | 2021-07-08 | COMP | 2021-08-15 | COMP | 2021-09-18 | COMP | Rule 15/16 | 87 | 234 | 28 | 66 | 27 | 24 | 462
18697 | 2019-11-18 | 2020-04-03 | 2020-05-31 | 2020-09-04 | COMP | 2020-10-01 | COMP | 2020-10-07 | COMP | 2020-10-06 | COMP | 2020-11-04 | COMP | Rule 16 | 94 | 40 | 19 | 5 | 0 | 21 | 245
18869 | 2019-11-18 | 2020-04-09 | 2020-10-23 | 2020-10-23 | COMP | 2020-11-09 | COMP | 2021-03-26 | COMP | 2021-06-16 | COMP | 2021-04-07 | COMP | Rule 15/16 | 98 | 140 | 12 | 93 | 58 |  | 348
19263 | 2019-11-18 | 2020-04-28 | 2020-05-15 | 2020-05-15 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-07-27 | COMP | 2020-08-06 | COMP | Rule 15/16 | 111 | 14 | 39 | 1 | 13 | 9 | 182
19922 | 2019-11-18 | 2020-05-28 | 2020-08-03 | 2020-08-03 | COMP | 2020-08-07 | COMP | 2020-12-03 | COMP | 2021-02-23 | COMP | 2021-02-17 | COMP | Rule 16 | 132 | 48 | 5 | 81 | 55 |  | 313
19930 | 2019-11-18 | 2020-05-28 | 2020-08-13 | 2020-08-13 | COMP | 2020-10-12 | COMP | 2021-03-01 | COMP | 2021-05-25 | COMP | 2021-06-08 | COMP | Rule 16 | 132 | 56 | 42 | 94 | 62 | 10 | 391
21283 | 2019-11-18 | 2020-07-30 | 2020-09-18 | 2020-09-18 | COMP | 2021-05-04 | COMP | 2021-05-04 | COMP | 2021-06-15 | COMP | 2021-08-16 | COMP | Rule 16 | 177 | 36 | 156 | 1 | 30 | 44 | 439
15954 | 2019-11-19 | 2019-12-02 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-04-22 | COMP | 2020-06-11 | COMP | Rule 16 | 8 | 93 | 6 | 1 | 2 | 36 | 141
16075 | 2019-11-19 | 2019-12-09 | 2020-07-20 | 2021-02-11 | COMP | 2021-04-16 | COMP | 2021-06-23 | COMP | 2021-12-02 | COMP | 2022-02-07 | COMP | Rule 15/16 | 13 | 156 | 46 | 48 | 112 | 47 | 558
16228 | 2019-11-19 | 2019-12-16 | 2020-06-22 | 2020-06-22 | COMP | 2020-08-31 | COMP | 2020-09-21 | COMP | 2020-10-05 | COMP | 2020-12-15 | COMP | Rule 15/16 | 18 | 131 | 51 | 15 | 11 | 49 | 270
16254 | 2019-11-19 | 2019-12-18 | 2020-05-12 | 2020-05-29 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-06-16 | COMP | 2020-07-28 | COMP | Rule 16 | 20 | 101 | 8 | 1 | 6 | 31 | 174
16518 | 2019-11-19 | 2020-01-06 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-11-10 | COMP | 2020-12-04 | COMP | Rule 16 | 31 | 81 | 9 | 1 | 130 | 16 | 263
16767 | 2019-11-19 | 2020-01-15 | 2020-01-29 | 2020-01-29 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-04 | COMP | 2020-03-12 | COMP | Rule 16 | 38 | 10 | 23 | 1 | 3 | 7 | 77
16923 | 2019-11-19 | 2020-01-23 | 2020-03-14 | 2020-03-14 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-04-28 | COMP | 2020-05-11 | COMP | Rule 16 | 43 | 36 | 23 | 1 | 10 | 10 | 119
17023 | 2019-11-19 | 2020-01-28 | 2020-05-12 | 2020-05-12 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-09-01 | COMP | Rule 16 | 46 | 75 | 43 | 1 | 1 | 38 | 199
17065 | 2019-11-19 | 2020-01-29 | 2020-03-05 | 2020-03-05 | COMP | 2020-03-31 | COMP | 2020-04-14 | COMP | 2020-04-13 | COMP | 2020-04-24 | COMP | Rule 15/16 | 47 | 26 | 19 | 11 | 0 | 9 | 108
17077 | 2019-11-19 | 2020-01-29 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-20 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-05-20 | COMP | Rule 16 | 47 | 35 | 24 | 2 | 1 | 22 | 126
17142 | 2019-11-19 | 2020-02-01 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-03-19 | COMP | 2020-04-13 | COMP | Rule 16 | 49 | 21 | 10 | 1 | 4 | 18 | 99
17352 | 2019-11-19 | 2020-02-10 | 2020-03-04 | 2020-03-04 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-05-27 | COMP | 2020-06-04 | COMP | Rule 16 | 55 | 17 | 32 | 1 | 29 | 7 | 136
17384 | 2019-11-19 | 2020-02-12 | 2020-03-08 | 2020-03-09 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2021-10-23 | INPR | 2020-07-07 | COMP | Rule 16 | 57 | 17 | 29 | 1 |  |  | 159
17422 | 2019-11-19 | 2020-02-12 | 2020-10-29 | 2020-10-29 | COMP | 2020-12-18 | COMP | 2021-08-25 | COMP | 2021-10-19 | COMP | 2021-10-28 | COMP | Rule 15/16 | 57 | 184 | 34 | 173 | 39 | 8 | 490
17452 | 2019-11-19 | 2020-02-13 | 2020-06-15 | 2020-06-15 | COMP | 2021-04-28 | COMP | 2021-12-15 | COMP | 2022-01-06 | COMP | 2022-02-15 | COMP | Rule 15/16 | 58 | 86 | 220 | 160 | 17 | 28 | 564
17659 | 2019-11-19 | 2020-02-24 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-10 | COMP | 2020-05-28 | COMP | 2020-09-03 | COMP | 2020-11-21 | COMP | Rule 15/16 | 64 | 23 | 13 | 34 | 71 | 55 | 255
17721 | 2019-11-19 | 2020-02-25 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-21 | COMP | 2020-06-22 | COMP | 2020-08-27 | COMP | 2020-10-13 | COMP | Rule 16 | 65 | 51 | 13 | 22 | 49 | 33 | 228
18200 | 2019-11-19 | 2020-03-16 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-09 | COMP | 2020-10-09 | COMP | 2020-09-21 | COMP | 2020-11-10 | COMP | Rule 16 | 79 | 51 | 11 | 88 | 0 | 23 | 248
18220 | 2019-11-19 | 2020-03-16 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-22 | COMP | 2020-06-15 | COMP | 2020-08-14 | COMP | 2020-09-25 | COMP | Rule 16 | 79 | 38 | 13 | 16 | 45 | 30 | 216
18255 | 2019-11-19 | 2020-03-17 | 2020-06-19 | 2020-06-19 | COMP | 2020-09-17 | COMP | 2020-10-22 | COMP | 2022-01-30 | INPR | 2020-11-23 | COMP | Rule 16 | 80 | 68 | 64 | 26 |  |  | 256
18273 | 2019-11-19 | 2020-03-17 | 2020-06-29 | 2020-06-29 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2020-12-18 | COMP | 2021-02-17 | COMP | Rule 15/16 | 80 | 74 | 114 | 1 | 8 | 40 | 312
18334 | 2019-11-19 | 2020-03-20 | 2020-09-10 | 2021-02-03 | COMP | 2021-02-11 | COMP | 2021-02-11 | COMP | 2022-04-17 | INPR | 2021-03-02 | COMP | Rule 16 | 83 | 123 | 7 | 1 |  |  | 321
18504 | 2019-11-19 | 2020-03-26 | 2020-08-26 | 2020-11-21 | COMP | 2021-01-05 | COMP | 2021-03-25 | COMP | 2021-04-13 | COMP | 2021-06-01 | COMP | Rule 16 | 87 | 109 | 28 | 56 | 14 | 35 | 385
18842 | 2019-11-19 | 2020-04-09 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP |  | INPR | 2020-08-06 | COMP | Rule 15/16 | 97 | 24 | 26 | 1 |  |  | 181
15760 | 2019-11-20 | 2019-11-20 | 2019-12-31 | 2019-12-31 | COMP | 2020-04-16 | COMP | 2020-02-05 | COMP | 2020-04-15 | COMP | 2020-10-20 | COMP | Rule 16 | 1 | 27 | 75 |  | 50 | 133 | 232
15761 | 2019-11-20 | 2019-11-20 | 2019-12-31 | 2019-12-31 | COMP | 2020-01-23 | COMP | 2020-01-23 | COMP | 2020-05-15 | COMP | 2020-07-07 | COMP | Rule 16 | 1 | 27 | 16 | 1 | 81 | 37 | 158
15838 | 2019-11-20 | 2019-11-23 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-03 | COMP | 2020-02-03 | COMP | 2020-04-21 | COMP | 2020-05-04 | COMP | Rule 16 | 3 | 35 | 12 | 1 | 56 | 10 | 113
16154 | 2019-11-20 | 2019-12-12 | 2020-01-15 | 2020-01-15 | COMP | 2020-01-29 | COMP | 2020-01-29 | COMP | 2020-02-06 | COMP | 2020-02-26 | COMP | Rule 16 | 15 | 23 | 10 | 1 | 7 | 14 | 65
16367 | 2019-11-20 | 2019-12-23 | 2020-04-08 | 2020-04-08 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2020-09-21 | COMP | Rule 16 | 22 | 74 | 94 | 1 | 1 | 24 | 211
16380 | 2019-11-20 | 2019-12-23 | 2020-01-30 | 2020-03-15 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-03-24 | COMP | 2020-04-30 | COMP | Rule 16 | 22 | 26 | 5 | 1 | 3 | 28 | 111
16528 | 2019-11-20 | 2020-01-06 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-11 | COMP | 2020-11-09 | COMP | 2021-02-04 | COMP | 2021-03-11 | COMP | Rule 16 | 30 | 86 | 26 | 107 | 58 | 25 | 327
16599 | 2019-11-20 | 2020-01-09 | 2020-02-27 | 2020-05-07 | COMP | 2020-10-30 | COMP | 2020-03-06 | COMP | 2020-11-03 | COMP | 2020-11-24 | COMP | Rule 16 | 33 | 34 | 125 |  | 171 | 15 | 256
16963 | 2019-11-20 | 2020-01-25 | 2020-04-15 | 2021-08-24 | COMP | 2021-08-27 | COMP | 2020-11-23 | COMP | 2021-09-07 | COMP | 2021-09-21 | COMP | Rule 16 | 43 | 57 | 4 |  | 198 | 11 | 462
16994 | 2019-11-20 | 2020-01-27 | 2020-05-19 | 2020-05-19 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-07-03 | COMP | 2020-08-31 | COMP | Rule 16 | 44 | 81 | 41 | 1 | 0 | 34 | 197
17013 | 2019-11-20 | 2020-01-28 | 2020-05-12 | 2020-05-12 | COMP | 2020-09-02 | COMP | 2020-09-02 | COMP | 2022-05-21 | COMP | 2022-08-06 | COMP | Rule 16 | 45 | 75 | 81 | 1 | 432 | 52 | 682
17037 | 2019-11-20 | 2020-01-29 | 2020-03-14 | 2020-03-14 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-06-12 | COMP | 2020-07-09 | COMP | Rule 16 | 46 | 32 | 23 | 1 | 42 | 20 | 160
17051 | 2019-11-20 | 2020-01-30 | 2020-05-07 | 2020-05-07 | COMP | 2020-09-08 | COMP | 2020-11-04 | COMP | 2020-11-05 | COMP | 2021-01-14 | COMP | Rule 15/16 | 47 | 70 | 87 | 42 | 2 | 46 | 289
17697 | 2019-11-20 | 2020-02-24 | 2020-03-31 | 2020-03-31 | COMP | 2020-05-28 | COMP | 2020-06-29 | COMP | 2020-07-27 | COMP | 2020-09-24 | COMP | Rule 15/16 | 63 | 27 | 42 | 23 | 21 | 43 | 214
18005 | 2019-11-20 | 2020-03-06 | 2020-07-20 | 2020-07-20 | COMP | 2020-08-07 | COMP | 2020-09-10 | COMP | 2020-08-03 | COMP | 2021-02-03 | COMP | Rule 16 | 72 | 96 | 15 | 24 | 0 | 99 | 302
18488 | 2019-11-20 | 2020-03-26 | 2020-05-22 | 2020-05-22 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2020-12-15 | COMP | 2021-01-12 | COMP | Rule 16 | 86 | 42 | 85 | 1 | 59 | 19 | 287
18835 | 2019-11-20 | 2020-04-08 | 2020-05-08 | 2020-05-08 | COMP | 2020-06-15 | COMP | 2020-09-09 | COMP | 2023-12-03 | INPR | 2020-09-30 | COMP | Rule 16 | 95 | 23 | 26 | 62 |  |  | 218
19020 | 2019-11-20 | 2020-04-17 | 2020-05-12 | 2020-05-12 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-07-31 | COMP | 2020-08-11 | COMP | Rule 16 | 102 | 18 | 5 | 1 | 54 | 8 | 183
19309 | 2019-11-20 | 2020-04-30 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-07-03 | COMP | Rule 15/16 | 111 | 22 | 9 | 1 | 1 | 17 | 156
19619 | 2019-11-20 | 2020-05-15 | 2020-07-25 | 2020-07-25 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-09-12 | COMP | 2020-10-19 | COMP | Rule 16 | 122 | 50 | 27 | 1 | 8 | 26 | 231
20103 | 2019-11-20 | 2020-06-04 | 2020-06-23 | 2020-06-23 | COMP | 2021-10-27 | COMP | 2021-10-27 | COMP | 2022-03-11 | COMP | 2022-05-03 | COMP | Rule 16 | 135 | 14 | 341 | 1 | 93 | 38 | 617
26682 | 2019-11-20 | 2021-03-30 | 2022-02-11 | 2022-03-03 | COMP | 2022-03-22 | COMP | 2022-03-22 | COMP | 2022-04-04 | COMP | 2022-05-02 | COMP | Rule 15/16 | 340 | 222 | 14 | 1 | 10 | 21 | 616
16010 | 2019-11-21 | 2019-12-06 | 2019-12-28 | 2019-12-28 | COMP | 2020-01-22 | NOTN | 2020-01-22 | COMP | 2020-01-07 | COMP | 2020-02-10 | COMP | Rule 16 | 10 | 15 |  | 16 | 0 | 14 | 53
16017 | 2019-11-21 | 2019-12-04 | 2020-04-05 | 2020-04-05 | COMP | 2020-05-01 | COMP | 2020-11-06 | COMP | 2023-11-13 | INPR | 2021-08-09 | COMP | Rule 15/16 | 8 | 84 | 20 | 134 |  |  | 431
16142 | 2019-11-21 | 2019-12-11 | 2020-05-08 | 2020-05-08 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2020-10-17 | COMP | 2020-12-18 | COMP | Rule 15/16 | 13 | 104 | 112 | 1 | 3 | 42 | 271
16188 | 2019-11-21 | 2019-12-13 | 2020-04-11 | 2020-04-11 | COMP | 2020-11-04 | COMP | 2020-11-04 | COMP | 2021-03-18 | COMP | 2021-04-19 | COMP | Rule 16 | 15 | 82 | 146 | 1 | 90 | 23 | 353
16229 | 2019-11-21 | 2019-12-16 | 2021-04-16 | 2021-04-16 | COMP | 2021-05-04 | COMP | 2021-05-04 | COMP | 2021-05-04 | COMP | 2021-06-13 | COMP | Rule 15/16 | 16 | 337 | 13 | 1 | 1 | 28 | 391
16598 | 2019-11-21 | 2020-01-09 | 2020-03-24 | 2020-03-24 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-05-08 | COMP | 2020-05-16 | COMP | Rule 16 | 32 | 52 | 12 | 1 | 23 | 6 | 121
16734 | 2019-11-21 | 2020-01-14 | 2020-02-15 | 2020-02-15 | COMP | 2020-07-24 | COMP | 2021-03-28 | COMP | 2021-03-29 | COMP | 2021-04-20 | COMP | Rule 16 | 35 | 23 | 113 | 168 | 1 | 17 | 354
17005 | 2019-11-21 | 2020-01-27 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-05-11 | COMP | Rule 16 | 43 | 54 | 6 | 1 | 1 | 17 | 117
17148 | 2019-11-21 | 2020-01-31 | 2020-04-28 | 2020-04-28 | COMP | 2020-06-02 | COMP | 2020-06-07 | COMP | 2020-06-30 | COMP | 2020-07-27 | COMP | Rule 16 | 47 | 62 | 25 | 4 | 17 | 20 | 171
17202 | 2019-11-21 | 2020-02-04 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-03-26 | COMP | 2020-03-27 | COMP | Rule 16 | 49 | 24 | 14 | 1 | 1 | 2 | 86
17330 | 2019-11-21 | 2020-02-10 | 2020-05-12 | 2020-05-28 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-27 | COMP | 2020-10-06 | COMP | Rule 16 | 53 | 66 | 42 | 1 | 25 | 28 | 221
17402 | 2019-11-21 | 2020-02-12 | 2020-05-21 | 2020-08-12 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-11-24 | COMP | 2021-01-08 | COMP | Rule 16 | 55 | 71 | 10 | 1 | 64 | 30 | 284
17424 | 2019-11-21 | 2020-02-13 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2020-09-14 | COMP | 2020-10-20 | COMP | Rule 16 | 56 | 95 | 20 | 1 | 37 | 27 | 231
17800 | 2019-11-21 | 2020-02-27 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-26 | COMP | 2020-10-14 | COMP | 2021-09-21 | COMP | 2021-09-27 | COMP | Other | 65 | 23 | 41 | 101 | 235 | 5 | 465
17804 | 2019-11-21 | 2020-02-28 | 2020-03-25 | 2021-04-06 | COMP | 2021-04-13 | COMP | 2021-04-13 | COMP | 2021-10-18 | COMP | 2021-12-22 | COMP | Rule 16 | 66 | 19 | 6 | 1 | 132 | 45 | 524
17938 | 2019-11-21 | 2020-03-04 | 2020-04-07 | 2020-04-07 | COMP | 2020-07-08 | COMP | 2020-07-08 | COMP | 2020-07-21 | COMP | 2020-08-11 | COMP | Rule 16 | 69 | 25 | 66 | 1 | 10 | 16 | 182
18644 | 2019-11-21 | 2020-04-01 | 2020-10-23 | 2020-10-23 | COMP | 2020-12-08 | COMP | 2020-12-08 | COMP | 2020-12-01 | COMP | 2021-01-07 | COMP | Rule 16 | 89 | 146 | 30 | 1 | 0 | 21 | 283
18897 | 2019-11-21 | 2020-04-10 | 2020-10-09 | 2020-10-09 | COMP | 2020-12-01 | COMP | 2021-03-09 | COMP | 2021-04-19 | COMP | 2021-04-22 | COMP | Rule 16 | 96 | 129 | 35 | 67 | 30 | 4 | 356
18927 | 2019-11-21 | 2020-04-13 | 2020-10-01 | 2020-10-01 | COMP | 2020-10-30 | COMP | 2020-11-03 | COMP | 2021-05-13 | COMP | 2021-06-30 | COMP | Rule 15/16 | 97 | 122 | 22 | 3 | 131 | 34 | 404
19094 | 2019-11-21 | 2020-04-21 | 2020-08-06 | 2020-08-06 | COMP | 2020-08-06 | NOTN | 2020-09-21 | COMP | 2020-08-06 | COMP | 2020-10-21 | COMP | Other | 103 | 77 |  | 32 | 0 | 23 | 232
19908 | 2019-11-21 | 2020-05-27 | 2020-07-11 | 2020-07-11 | COMP | 2021-03-01 | COMP | 2021-03-03 | COMP | 2023-02-14 | COMP | 2023-04-03 | COMP | Rule 16 | 128 | 33 | 158 | 3 | 492 | 34 | 844
20097 | 2019-11-21 | 2020-06-04 | 2020-08-25 | 2020-10-02 | COMP | 2020-10-08 | COMP | 2020-11-18 | COMP | 2020-12-11 | COMP | 2021-02-12 | COMP | Rule 16 | 134 | 59 | 5 | 29 | 16 | 43 | 308
20111 | 2019-11-21 | 2020-06-04 | 2020-08-08 | 2020-08-08 | COMP | 2021-01-28 | COMP | 2021-01-28 | COMP | 2021-01-19 | COMP | 2021-02-19 | COMP | Rule 16 | 134 | 47 | 117 | 1 | 0 | 16 | 312
20166 | 2019-11-21 | 2020-06-08 | 2020-10-20 | 2020-10-20 | COMP | 2021-01-26 | COMP | 2021-04-07 | COMP | 2021-09-13 | COMP | 2021-10-16 | COMP | Rule 15/16 | 136 | 96 | 65 | 51 | 111 | 25 | 479
20253 | 2019-11-21 | 2020-06-12 | 2020-07-17 | 2020-07-17 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2020-12-01 | COMP | 2020-12-31 | COMP | Rule 16 | 140 | 26 | 90 | 1 | 5 | 22 | 279
23416 | 2019-11-21 | 2020-11-05 | 2021-03-15 | 2021-03-15 | COMP | 2021-04-21 | COMP | 2021-04-30 | COMP | 2021-06-30 | COMP | 2021-07-21 | COMP | Rule 16 | 243 | 86 | 28 | 8 | 43 | 15 | 418
4272 | 2019-11-22 | 2020-02-10 | 2020-03-24 | 2020-03-24 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-09-26 | COMP | 2020-11-03 | COMP | Rule 16 | 52 | 31 | 44 | 1 | 89 | 27 | 240
4309 | 2019-11-22 | 2020-07-20 | 2020-11-05 | 2021-03-17 | COMP | 2022-08-15 | COMP | 2022-08-17 | INPR | 2022-08-03 | COMP | 2022-11-03 | COMP | Rule 15/16 | 165 | 78 | 358 |  |  |  | 743
15981 | 2019-11-22 | 2019-12-04 | 2020-03-24 | 2020-03-24 | COMP | 2020-12-01 | COMP | 2021-01-11 | COMP | 2021-05-07 | COMP | 2021-06-25 | COMP | Rule 16 | 7 | 76 | 176 | 28 | 83 | 35 | 400
16246 | 2019-11-22 | 2019-12-17 | 2020-05-01 | 2020-05-01 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-05-28 | COMP | 2020-07-22 | COMP | Rule 16 | 16 | 95 | 17 | 1 | 3 | 40 | 167
16337 | 2019-11-22 | 2019-12-20 | 2020-04-07 | 2020-04-07 | COMP | 2020-06-10 | COMP | 2020-07-13 | COMP | 2020-06-06 | COMP | 2020-08-24 | COMP | Rule 16 | 19 | 74 | 46 | 24 | 0 | 31 | 190
16369 | 2019-11-22 | 2019-12-23 | 2020-04-07 | 2020-04-07 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-05-23 | COMP | 2020-06-23 | COMP | Rule 16 | 20 | 73 | 33 | 1 | 2 | 21 | 146
16476 | 2019-11-22 | 2020-01-03 | 2020-03-05 | 2020-03-05 | COMP | 2020-04-06 | COMP | 2020-04-21 | COMP | 2020-04-07 | COMP | 2020-05-11 | COMP | Rule 15/16 | 27 | 43 | 23 | 12 | 0 | 15 | 116
16507 | 2019-11-22 | 2020-01-06 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2021-02-01 | COMP | 2021-02-04 | COMP | Rule 16 | 28 | 77 | 19 | 1 | 177 | 4 | 301
16545 | 2019-11-22 | 2020-01-07 | 2020-01-31 | 2020-01-31 | COMP | 2020-02-27 | COMP | 2020-12-09 | COMP | 2021-01-14 | COMP | 2021-01-31 | COMP | Rule 16 | 29 | 18 | 19 | 200 | 25 | 11 | 297
16552 | 2019-11-22 | 2020-01-07 | 2020-03-05 | 2020-11-20 | COMP | 2020-12-01 | COMP | 2020-03-26 | COMP | 2020-12-02 | COMP | 2021-01-08 | COMP | Rule 16 | 29 | 41 | 6 |  | 175 | 26 | 283
16656 | 2019-11-22 | 2020-01-10 | 2020-03-25 | 2020-03-25 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2020-09-08 | COMP | 2020-10-21 | COMP | Rule 15/16 | 32 | 52 | 70 | 1 | 49 | 32 | 231
16659 | 2019-11-22 | 2020-01-10 | 2020-02-08 | 2020-02-08 | COMP | 2020-03-04 | COMP | 2020-03-04 | INPR | 2022-01-30 | REQD | 2020-06-16 | COMP | Rule 16 | 32 | 20 | 17 |  |  |  | 141
16959 | 2019-11-22 | 2020-01-25 | 2020-07-06 | 2020-07-06 | COMP | 2020-08-05 | COMP | 2020-08-28 | COMP | 2021-02-04 | COMP | 2021-03-04 | COMP | Rule 16 | 41 | 114 | 23 | 18 | 108 | 20 | 320
17080 | 2019-11-22 | 2020-01-29 | 2020-10-16 | 2020-10-16 | COMP | 2021-05-24 | COMP | 2022-08-25 | COMP | 2022-08-19 | COMP | 2023-04-06 | COMP | Rule 15/16 | 44 | 185 | 150 | 318 | 0 | 153 | 846
17160 | 2019-11-22 | 2020-02-04 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-07-20 | COMP | 2020-07-24 | COMP | Rule 16 | 48 | 51 | 20 | 1 | 49 | 5 | 169
17277 | 2019-11-22 | 2020-02-06 | 2020-07-01 | 2020-07-01 | COMP | 2020-08-31 | COMP | 2020-10-13 | COMP | 2020-11-17 | COMP | 2021-03-09 | COMP | Rule 16 | 50 | 103 | 44 | 31 | 25 | 75 | 323
17669 | 2019-11-22 | 2020-02-24 | 2020-04-28 | 2020-04-28 | COMP | 2020-05-08 | COMP | 2020-06-23 | COMP | 2020-06-25 | COMP | 2020-08-07 | COMP | Rule 16 | 61 | 47 | 9 | 32 | 3 | 32 | 179
17722 | 2019-11-22 | 2020-02-25 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-06 | COMP | 2020-12-07 | COMP | 2023-12-03 | INPR | 2021-08-27 | COMP | Rule 16 | 62 | 23 | 30 | 149 |  |  | 444
18051 | 2019-11-22 | 2020-03-10 | 2020-05-26 | 2020-06-01 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-09-18 | COMP | 2020-10-29 | COMP | Rule 16 | 72 | 55 | 56 | 1 | 24 | 30 | 237
18253 | 2019-11-22 | 2020-03-17 | 2020-04-03 | 2020-04-03 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2022-04-16 | INPR | 2021-03-25 | COMP | Rule 16 | 77 | 14 | 73 | 1 |  |  | 335
18502 | 2019-11-22 | 2020-03-26 | 2020-05-23 | 2020-05-23 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2022-01-30 | INPR | 2020-08-13 | COMP | Rule 16 | 84 | 42 | 43 | 1 |  |  | 183
18984 | 2019-11-22 | 2020-04-16 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-17 | COMP | 2020-07-15 | COMP | Rule 16 | 99 | 24 | 9 | 1 | 13 | 21 | 162
15944 | 2019-11-23 | 2019-12-02 | 2020-01-08 | 2020-01-10 | COMP | 2020-03-09 | COMP | 2020-03-09 | COMP | 2020-12-28 | COMP | 2021-02-10 | COMP | Rule 16 | 4 | 26 | 40 | 1 | 205 | 31 | 304
18242 | 2019-11-23 | 2020-03-16 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-12 | COMP | 2020-08-27 | COMP | 2020-10-06 | COMP | 2020-11-05 | COMP | Rule 16 | 75 | 45 | 20 | 55 | 28 | 23 | 241
16559 | 2019-11-24 | 2020-01-08 | 2020-04-20 | 2020-04-20 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-08-13 | COMP | 2020-09-02 | COMP | Rule 16 | 29 | 72 | 44 | 1 | 40 | 15 | 196
16797 | 2019-11-24 | 2020-01-16 | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | NOTN | 2020-06-12 | COMP | 2020-06-15 | COMP | 2020-08-13 | COMP | Other | 35 | 92 |  | 13 | 2 | 44 | 182
4275 | 2019-11-25 | 2020-02-21 | [7 empty] | 2020-02-24 | COMP | 2020-03-26 | COMP | Other | 59 | [5 empty] | 83
15983 | 2019-11-25 | 2019-12-04 | 2020-04-05 | 2020-04-05 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-17 | COMP | 2020-09-02 | COMP | Rule 16 | 6 | 84 | 84 | 1 | 12 | 13 | 196
16102 | 2019-11-25 | 2019-12-09 | 2020-03-11 | 2020-03-11 | COMP | 2020-05-12 | COMP | 2020-05-19 | COMP | 2020-07-31 | COMP | 2020-08-28 | COMP | Rule 16 | 9 | 64 | 45 | 6 | 53 | 21 | 193
16107 | 2019-11-25 | 2019-12-10 | 2020-02-19 | 2020-02-19 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | Rule 16 | 10 | 48 | 57 | 1 | 32 | 1 | 144
16216 | 2019-11-25 | 2019-12-16 | 2020-03-01 | 2020-03-01 | COMP | 2020-03-11 | COMP | 2020-03-16 | COMP | 2020-04-13 | COMP | 2020-06-15 | COMP | Rule 16 | 14 | 51 | 8 | 4 | 21 | 45 | 139
16280 | 2019-11-25 | 2019-12-18 | 2020-05-05 | 2020-05-05 | COMP | 2020-07-29 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP | 2021-02-11 | COMP | Rule 15/16 | 16 | 96 | 61 | 87 | 1 | 49 | 305
16462 | 2019-11-25 | 2020-01-02 | 2020-01-15 | 2020-01-15 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-11-17 | COMP | 2020-12-22 | COMP | Rule 16 | 25 | 10 | 42 | 1 | 174 | 24 | 271
16494 | 2019-11-25 | 2020-01-03 | 2020-05-21 | 2020-06-17 | COMP | 2020-08-21 | COMP | 2020-10-20 | COMP | 2020-11-05 | COMP | 2020-12-08 | COMP | Rule 16 | 26 | 98 | 48 | 42 | 13 | 21 | 261
16621 | 2019-11-25 | 2020-01-10 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-21 | COMP | 2020-08-13 | COMP | 2020-10-01 | COMP | 2020-10-30 | COMP | Rule 16 | 31 | 85 | 9 | 60 | 35 | 22 | 237
16690 | 2019-11-25 | 2020-01-13 | 2020-03-26 | 2022-08-11 | COMP | 2022-09-06 | COMP | 2020-06-08 | COMP | 2023-04-06 | COMP | 2023-05-16 | COMP | Rule 16 | 32 | 52 | 18 |  | 712 | 29 | 873
17126 | 2019-11-25 | 2020-01-31 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-12 | COMP | 2020-06-20 | COMP | 2020-06-04 | COMP | 2020-07-08 | COMP | Rule 16 | 45 | 56 | 17 | 28 | 0 | 13 | 156
17141 | 2019-11-25 | 2020-02-01 | 2020-04-16 | 2020-04-16 | COMP | 2020-04-22 | COMP | 2020-07-02 | COMP | 2020-07-13 | COMP | 2020-08-09 | COMP | Rule 15/16 | 45 | 53 | 5 | 51 | 8 | 20 | 178
17285 | 2019-11-25 | 2020-02-07 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-08 | COMP | 2020-12-03 | COMP | 2020-12-02 | COMP | 2021-01-15 | COMP | Rule 16 | 50 | 72 | 14 | 125 | 0 | 30 | 287
17774 | 2019-11-25 | 2020-02-26 | 2020-05-26 | 2020-05-26 | COMP | 2020-10-12 | COMP | 2021-02-16 | COMP | 2021-02-12 | COMP | 2021-03-19 | COMP | Rule 16 | 62 | 64 | 99 | 85 | 0 | 24 | 330
17955 | 2019-11-25 | 2020-03-05 | 2020-08-25 | 2020-09-30 | COMP | 2020-11-17 | COMP | 2022-02-28 | COMP | 2022-03-03 | COMP | 2022-04-05 | COMP | Rule 16 | 68 | 123 | 34 | 321 | 4 | 24 | 594
17957 | 2019-11-25 | 2020-03-05 | 2020-08-19 | 2020-11-20 | COMP | 2021-01-08 | COMP | 2021-05-22 | COMP | 2020-11-23 | COMP | 2021-07-02 | COMP | Rule 16 | 68 | 119 | 32 | 94 | 0 | 29 | 404
18932 | 2019-11-25 | 2020-04-13 | 2020-07-07 | 2020-07-07 | COMP | 2021-01-13 | COMP | 2021-01-13 | COMP | 2021-08-03 | COMP | 2021-09-16 | COMP | Rule 16 | 95 | 61 | 131 | 1 | 141 | 32 | 456
19018 | 2019-11-25 | 2020-04-17 | 2020-07-10 | 2020-07-10 | COMP | 2020-07-17 | COMP | 2020-09-08 | COMP | 2020-09-16 | COMP | 2020-10-21 | COMP | Rule 16 | 99 | 60 | 6 | 37 | 7 | 26 | 230
19189 | 2019-11-25 | 2020-04-24 | 2020-09-16 | 2020-09-16 | COMP | 2021-02-07 | NOTN | 2021-02-07 | COMP | 2023-11-22 | COMP | 2023-11-03 | COMP | Other | 104 | 102 |  | 97 | 703 |  | 992
19567 | 2019-11-25 | 2020-05-12 | 2020-05-26 | 2021-01-11 | COMP | 2021-01-29 | COMP | 2021-01-29 | COMP | 2021-02-03 | COMP | 2021-03-05 | COMP | Rule 16 | 116 | 10 | 14 | 1 | 4 | 22 | 320
20401 | 2019-11-25 | 2020-06-18 | 2020-07-22 | 2020-07-22 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2020-10-30 | COMP | 2020-12-08 | COMP | Rule 16 | 142 | 25 | 68 | 1 | 5 | 25 | 261
15910 | 2019-11-26 | 2019-11-27 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-30 | COMP | 2020-09-16 | COMP | 2020-11-09 | COMP | 2020-12-11 | COMP | Rule 16 | 2 | 135 | 14 | 56 | 39 | 22 | 263
16350 | 2019-11-26 | 2019-12-23 | 2020-02-04 | 2020-03-13 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-04-08 | COMP | Rule 16 | 18 | 29 | 5 | 1 | 1 | 15 | 91
16558 | 2019-11-26 | 2020-01-07 | 2020-11-09 | 2020-11-09 | COMP | 2020-11-13 | COMP | 2020-12-10 | COMP | 2020-11-10 | COMP | 2021-01-29 | COMP | Rule 16 | 27 | 216 | 4 | 18 | 0 | 34 | 295
16639 | 2019-11-26 | 2020-01-09 | 2020-03-17 | 2020-03-17 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-04-12 | COMP | 2020-06-10 | COMP | Rule 16 | 29 | 47 | 15 | 1 | 5 | 42 | 135
16852 | 2019-11-26 | 2020-01-21 | 2020-05-07 | 2020-05-07 | COMP | 2021-10-01 | COMP | 2021-10-01 | COMP | 2021-10-01 | COMP | 2021-10-29 | COMP | Rule 16 | 36 | 77 | 355 | 1 | 1 | 21 | 486
16856 | 2019-11-26 | 2020-01-21 | 2020-05-14 | 2020-05-14 | COMP | 2023-05-11 | COMP | 2023-05-11 | COMP | 2023-05-12 | COMP | 2023-06-16 | COMP | Rule 16 | 36 | 82 | 753 | 1 | 2 | 25 | 894
16871 | 2019-11-26 | 2020-01-21 | 2020-04-03 | 2020-04-03 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-30 | COMP | 2020-09-22 | COMP | Rule 16 | 36 | 53 | 71 | 1 | 14 | 38 | 208
16898 | 2019-11-26 | 2020-01-23 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-01 | COMP | 2020-06-02 | COMP | 2020-09-15 | COMP | 2020-11-10 | COMP | Rule 16 | 38 | 86 | 6 | 2 | 75 | 41 | 243
16997 | 2019-11-26 | 2020-01-27 | 2020-04-01 | 2020-04-01 | COMP | 2020-04-22 | COMP | 2020-07-09 | COMP | 2020-06-17 | COMP | 2020-08-06 | COMP | Rule 16 | 40 | 47 | 16 | 56 | 0 | 21 | 176
17030 | 2019-11-26 | 2020-01-28 | 2020-02-15 | 2020-02-15 | COMP | 2020-04-15 | COMP | 2020-04-16 | INPR | 2020-06-19 | COMP | 2020-07-08 | COMP | Rule 16 | 41 | 14 | 42 |  |  |  | 155
17067 | 2019-11-26 | 2020-01-29 | 2020-03-24 | 2020-03-24 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-12-17 | COMP | 2020-12-28 | COMP | Rule 16 | 42 | 39 | 149 | 1 | 40 | 7 | 273
17069 | 2019-11-26 | 2020-01-29 | 2020-04-23 | 2021-08-13 | COMP | 2021-10-20 | COMP | 2020-10-20 | COMP | 2023-07-01 | INPR | 2022-04-20 | COMP | Rule 16 | 42 | 61 | 48 |  |  |  | 604
17070 | 2019-11-26 | 2020-01-29 | 2020-04-19 | 2020-04-19 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-11-02 | COMP | 2020-11-24 | COMP | Rule 16 | 42 | 57 | 130 | 1 | 10 | 16 | 252
17071 | 2019-11-26 | 2020-01-29 | 2020-03-24 | 2020-03-24 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-11-02 | COMP | 2020-11-25 | COMP | Rule 16 | 42 | 39 | 149 | 1 | 10 | 17 | 253
17073 | 2019-11-26 | 2020-01-29 | 2020-04-23 | 2020-04-23 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2021-03-08 | COMP | 2021-04-02 | COMP | Rule 16 | 42 | 61 | 133 | 1 | 87 | 20 | 339
17082 | 2019-11-26 | 2020-01-30 | 2020-04-28 | 2020-04-28 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-10-15 | COMP | 2020-11-09 | COMP | Rule 16 | 43 | 63 | 71 | 1 | 51 | 18 | 242
17197 | 2019-11-26 | 2020-02-04 | 2020-03-20 | 2020-03-20 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-05-27 | COMP | Rule 16 | 46 | 33 | 6 | 1 | 1 | 43 | 125
17736 | 2019-11-26 | 2020-02-26 | 2020-04-20 | 2020-04-20 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-07-10 | COMP | 2020-08-07 | COMP | Rule 16 | 61 | 39 | 9 | 1 | 51 | 21 | 177
18497 | 2019-11-26 | 2020-03-26 | 2020-09-24 | 2023-03-23 | COMP | 2023-04-17 | COMP | 2023-05-01 | COMP |  | INPR | 2023-08-29 | COMP | Rule 16 | 82 | 129 | 18 | 11 |  |  | 944
19068 | 2019-11-26 | 2020-04-20 | 2020-05-26 | 2020-05-26 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2020-12-15 | COMP | 2021-01-13 | COMP | Rule 16 | 99 | 26 | 76 | 1 | 67 | 20 | 284
19146 | 2019-11-26 | 2020-04-22 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-06-30 | COMP | 2020-07-30 | COMP | Rule 16 | 101 | 18 | 15 | 1 | 18 | 23 | 171
19860 | 2019-11-26 | 2020-05-26 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2022-07-16 | INPR | 2020-07-24 | COMP | Rule 16 | 124 | 20 | 14 | 1 |  |  | 167
16363 | 2019-11-27 | 2019-12-26 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-07 | COMP | 2020-08-08 | COMP | 2021-06-01 | COMP | 2021-07-19 | COMP | Rule 16 | 19 | 122 | 14 | 24 | 203 | 34 | 412
16391 | 2019-11-27 | 2019-12-24 | 2020-03-07 | 2020-03-07 | COMP | 2020-03-17 | COMP | 2020-03-30 | COMP | 2020-04-22 | COMP | 2020-05-14 | COMP | Rule 16 | 18 | 50 | 7 | 10 | 18 | 17 | 116
16590 | 2019-11-27 | 2020-01-08 | 2020-02-11 | 2020-02-11 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-08-21 | COMP | 2020-08-11 | COMP | Rule 16 | 27 | 24 | 90 | 1 | 48 |  | 178
16624 | 2019-11-27 | 2020-01-10 | 2020-03-07 | 2020-03-07 | COMP | 2020-05-13 | COMP | 2020-06-16 | COMP | 2023-04-30 | INPR | 2020-07-01 | COMP | Rule 16 | 29 | 39 | 48 | 24 |  |  | 149
16907 | 2019-11-27 | 2020-01-23 | 2020-02-13 | 2020-02-13 | COMP | 2020-02-19 | COMP | 2020-02-19 | COMP | 2020-03-02 | COMP | 2020-03-04 | COMP | Rule 16 | 37 | 16 | 4 | 1 | 9 | 3 | 65
17240 | 2019-11-27 | 2020-02-06 | 2020-06-11 | 2020-06-25 | COMP | 2020-07-09 | COMP | 2020-07-10 | COMP | 2023-12-30 | INPR | 2020-11-05 | COMP | Rule 16 | 47 | 89 | 11 | 2 |  |  | 239
17513 | 2019-11-27 | 2020-02-19 | 2020-05-02 | 2020-05-02 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2022-08-30 | COMP | 2022-10-03 | COMP | Rule 16 | 55 | 53 | 60 | 1 | 528 | 24 | 717
18030 | 2019-11-27 | 2020-03-09 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2020-09-21 | COMP | 2020-10-12 | COMP | Rule 16 | 68 | 74 | 9 | 1 | 58 | 16 | 221
18044 | 2019-11-27 | 2020-03-10 | 2020-05-12 | 2020-05-12 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2020-11-30 | COMP | 2020-12-14 | COMP | Rule 16 | 69 | 46 | 118 | 1 | 23 | 11 | 263
18307 | 2019-11-27 | 2020-03-20 | 2020-07-10 | 2020-07-10 | COMP | 2021-11-12 | COMP | 2021-11-12 | COMP | 2021-12-04 | COMP | 2021-12-20 | COMP | Rule 16 | 77 | 80 | 339 | 1 | 14 | 11 | 518
18321 | 2019-11-27 | 2020-03-20 | 2020-05-14 | 2020-05-14 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP |  | INPR | 2020-07-15 | COMP | Rule 15/16 | 77 | 40 | 21 | 1 |  |  | 159
18415 | 2019-11-27 | 2020-03-23 | 2020-07-02 | 2020-07-02 | COMP | 2020-07-10 | COMP | 2020-07-22 | COMP | 2020-07-14 | COMP | 2020-08-06 | COMP | Rule 16 | 78 | 73 | 7 | 9 | 0 | 12 | 175
18539 | 2019-11-27 | 2020-03-28 | 2020-08-13 | 2020-08-13 | COMP | 2020-10-08 | COMP | 2020-11-10 | COMP | 2021-04-16 | COMP | 2021-05-06 | COMP | Rule 15/16 | 82 | 98 | 40 | 24 | 107 | 15 | 362
18639 | 2019-11-27 | 2020-04-01 | 2020-11-10 | 2020-11-10 | COMP | 2020-12-31 | COMP | 2021-02-24 | COMP | 2021-02-26 | COMP | 2021-05-04 | COMP | Rule 15/16 | 85 | 158 | 34 | 37 | 3 | 48 | 360
18642 | 2019-11-27 | 2020-04-01 | 2020-10-16 | 2020-10-16 | COMP | 2020-11-06 | COMP | 2021-01-26 | COMP | 2021-02-10 | COMP | 2021-06-16 | COMP | Rule 16 | 85 | 141 | 16 | 52 | 12 | 89 | 390
19075 | 2019-11-27 | 2020-04-20 | 2021-04-16 | 2021-04-16 | COMP | 2021-06-28 | COMP | 2021-07-01 | COMP | 2022-01-18 | COMP | 2022-02-15 | COMP | Rule 15/16 | 98 | 251 | 51 | 4 | 138 | 21 | 558
19623 | 2019-11-27 | 2020-05-15 | 2020-07-12 | 2020-07-12 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-07-20 | COMP | 2020-08-01 | COMP | Rule 16 | 117 | 40 | 5 | 1 | 2 | 10 | 171
20655 | 2019-11-27 | 2020-06-30 | 2020-12-18 | 2021-04-28 | COMP | 2021-05-07 | COMP | 2021-05-17 | COMP | 2021-05-24 | COMP | 2021-05-29 | COMP | Rule 15/16 | 148 | 120 | 8 | 7 | 6 | 5 | 378
16580 | 2019-11-29 | 2020-01-08 | 2020-04-17 | 2020-04-17 | COMP | 2021-02-24 | COMP | 2021-02-24 | COMP | 2021-03-08 | COMP | 2021-04-13 | COMP | Rule 16 | 26 | 71 | 215 | 1 | 9 | 27 | 344
18624 | 2019-11-29 | 2020-03-31 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-20 | COMP | 2020-05-22 | COMP | 2020-07-07 | COMP | 2020-06-24 | COMP | Rule 16 | 83 | 34 | 4 | 3 | 32 |  | 143
15924 | 2019-11-30 | 2019-12-02 | 2020-03-24 | 2020-03-24 | COMP | 2020-03-25 | NOTN | 2020-03-25 | COMP | 2020-03-25 | COMP | 2020-08-25 | COMP | Other | 1 | 78 |  | 2 | 1 | 109 | 187
17140 | 2019-11-30 | 2020-01-31 | 2020-03-14 | 2020-03-14 | COMP | 2020-03-30 | COMP | 2020-05-06 | COMP | 2022-01-11 | COMP | 2022-01-21 | COMP | Rule 16 | 42 | 30 | 11 | 28 | 425 | 8 | 540
17735 | 2019-11-30 | 2020-02-25 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-08-25 | COMP | 2020-10-30 | COMP | Rule 16 | 58 | 78 | 7 | 1 | 47 | 48 | 234
17763 | 2019-11-30 | 2020-02-26 | 2020-05-04 | 2020-05-04 | COMP | 2020-07-27 | NOTN | 2020-07-28 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | Other | 59 | 49 |  | 61 | 52 | 1 | 218
15925 | 2019-12-01 | 2019-12-02 | 2020-08-02 | 2020-08-02 | COMP | 2020-09-03 | COMP | 2021-02-18 | COMP | 2021-02-19 | COMP | 2021-03-13 | COMP | Rule 15/16 | 1 | 170 | 24 | 113 | 2 | 16 | 322
15982 | 2019-12-02 | 2019-12-04 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-15 | COMP | 2020-07-07 | COMP | Rule 16 | 3 | 95 | 27 | 1 | 14 | 17 | 152
16181 | 2019-12-02 | 2019-12-13 | 2020-01-30 | 2020-01-30 | COMP | 2020-04-30 | COMP | 2020-03-11 | COMP | 2020-06-25 | COMP | 2020-07-15 | COMP | Rule 16 | 10 | 32 | 65 |  | 76 | 15 | 158
16182 | 2019-12-02 | 2019-12-13 | 2020-02-04 | 2020-02-04 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-04-27 | COMP | 2020-05-02 | COMP | Rule 16 | 10 | 35 | 57 | 1 | 3 | 5 | 106
16261 | 2019-12-02 | 2019-12-19 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-19 | COMP | 2020-03-25 | COMP | 2020-02-19 | COMP | 2020-04-18 | COMP | Rule 15/16 | 14 | 28 | 14 | 26 | 0 | 18 | 96
16286 | 2019-12-02 | 2019-12-19 | 2020-04-11 | 2020-04-11 | COMP | 2020-05-28 | COMP | 2020-08-18 | COMP | 2020-08-13 | COMP | 2020-11-17 | COMP | Rule 16 | 14 | 78 | 33 | 59 | 0 | 64 | 245
16313 | 2019-12-02 | 2019-12-20 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-02 | NOTN | 2020-06-13 | COMP | 2020-04-02 | COMP | 2020-11-03 | COMP | Other | 15 | 71 |  | 51 | 0 | 101 | 236
16377 | 2019-12-02 | 2019-12-23 | 2020-01-28 | 2020-01-28 | COMP | 2020-12-29 | COMP | 2020-12-29 | COMP | 2021-01-20 | COMP | 2021-02-04 | COMP | Rule 16 | 16 | 24 | 234 | 1 | 15 | 12 | 297
16438 | 2019-12-02 | 2019-12-31 | 2020-06-04 | 2020-06-04 | COMP | 2020-06-18 | COMP | 2020-07-21 | COMP | 2020-07-22 | COMP | 2020-08-13 | COMP | Rule 16 | 21 | 109 | 11 | 24 | 2 | 17 | 179
16564 | 2019-12-02 | 2020-01-08 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-05-31 | INPR | 2020-02-11 | COMP | Rule 16 | 26 | 16 | 5 | 1 |  |  | 49
16595 | 2019-12-02 | 2020-01-09 | 2020-02-27 | 2020-03-13 | COMP | 2020-03-17 | COMP | 2020-03-19 | COMP | 2020-05-29 | COMP | 2020-06-10 | COMP | Rule 16 | 27 | 34 | 3 | 3 | 51 | 9 | 133
16764 | 2019-12-02 | 2020-01-14 | 2020-02-06 | 2020-02-06 | COMP | 2020-02-20 | COMP | 2020-02-21 | COMP | 2020-06-12 | COMP | 2020-07-02 | COMP | Rule 16 | 30 | 17 | 10 | 2 | 80 | 15 | 149
16872 | 2019-12-02 | 2020-01-21 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-02 | COMP | 2020-08-27 | COMP | 2020-11-01 | COMP | 2021-01-12 | COMP | Rule 16 | 34 | 107 | 10 | 41 | 46 | 47 | 281
16989 | 2019-12-02 | 2020-01-27 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2021-04-08 | COMP | 2021-04-20 | COMP | Rule 16 | 38 | 23 | 17 | 1 | 266 | 9 | 349
17102 | 2019-12-02 | 2020-01-30 | 2020-05-15 | 2020-05-15 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-09-22 | COMP | 2020-09-24 | COMP | Rule 16 | 41 | 76 | 62 | 1 | 30 | 3 | 208
17175 | 2019-12-02 | 2020-02-03 | 2020-10-05 | 2020-10-05 | COMP | 2021-01-08 | COMP | 2021-09-06 | COMP | 2021-09-08 | COMP | 2021-09-30 | COMP | Rule 16 | 43 | 173 | 65 | 167 | 2 | 17 | 463
17284 | 2019-12-02 | 2020-02-07 | 2020-06-15 | 2020-06-15 | COMP | 2020-09-04 | COMP | 2020-09-04 | COMP | 2020-09-04 | COMP | 2021-02-25 | COMP | Rule 16 | 47 | 90 | 60 | 1 | 1 | 117 | 311
17363 | 2019-12-02 | 2020-02-11 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-19 | COMP | 2020-08-12 | COMP | 2020-08-10 | COMP | 2020-09-15 | COMP | Rule 15/16 | 49 | 54 | 17 | 61 | 0 | 24 | 201
17429 | 2019-12-02 | 2020-02-13 | 2020-07-27 | 2020-07-27 | COMP | 2020-10-02 | COMP | 2020-11-16 | COMP | 2021-03-22 | COMP | 2021-04-14 | COMP | Rule 15/16 | 51 | 116 | 49 | 31 | 85 | 18 | 345
17786 | 2019-12-02 | 2020-02-28 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-22 | COMP | 2020-06-25 | COMP | 2020-06-16 | COMP | 2020-07-05 | COMP | Rule 16 | 61 | 44 | 18 | 24 | 0 | 7 | 150
17962 | 2019-12-02 | 2020-03-05 | 2020-06-11 | 2020-06-11 | COMP | 2021-08-16 | COMP | 2021-08-19 | COMP | 2022-04-14 | COMP | 2022-05-13 | COMP | Rule 16 | 65 | 70 | 298 | 4 | 165 | 22 | 619
18052 | 2019-12-02 | 2020-03-10 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-05-12 | COMP | 2020-05-28 | COMP | Rule 16 | 68 | 40 | 6 | 1 | 2 | 12 | 124
18235 | 2019-12-02 | 2020-03-16 | 2020-06-03 | 2020-10-01 | COMP | 2021-04-08 | COMP | 2021-05-06 | COMP | 2021-04-26 | COMP | 2021-06-22 | COMP | Rule 16 | 72 | 57 | 129 | 21 | 0 | 33 | 393
18289 | 2019-12-02 | 2020-03-18 | 2020-09-01 | 2020-09-01 | COMP | 2020-11-12 | COMP | 2021-05-05 | COMP | 2021-04-20 | COMP | 2021-05-27 | COMP | Rule 15/16 | 74 | 119 | 51 | 119 | 0 | 17 | 376
18318 | 2019-12-02 | 2020-03-19 | 2020-08-27 | 2020-08-27 | COMP | 2021-10-04 | COMP | 2021-11-10 | COMP | 2021-11-30 | COMP | 2022-01-25 | COMP | Rule 15/16 | 75 | 115 | 277 | 28 | 12 | 40 | 542
18351 | 2019-12-02 | 2020-03-21 | 2020-05-14 | 2020-05-14 | COMP | 2020-05-20 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-09-14 | COMP | Rule 16 | 76 | 39 | 5 | 16 | 1 | 67 | 200
18604 | 2019-12-02 | 2020-03-31 | 2020-10-15 | 2020-10-15 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2020-12-29 | COMP | 2021-02-26 | COMP | Rule 16 | 83 | 141 | 10 | 1 | 41 | 41 | 312
18700 | 2019-12-02 | 2020-04-02 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-11 | NOTN | 2020-06-11 | COMP | 2020-06-12 | COMP | 2020-08-28 | COMP | Other | 85 | 48 |  | 3 | 2 | 56 | 190
19391 | 2019-12-02 | 2020-05-06 | 2020-09-24 | 2020-09-24 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | 2021-02-24 | COMP | 2021-04-01 | COMP | Rule 16 | 109 | 100 | 78 | 1 | 26 | 27 | 336
19637 | 2019-12-02 | 2020-05-15 | 2020-08-13 | 2020-08-13 | COMP | 2020-08-24 | COMP | 2020-09-20 | COMP | 2020-09-21 | COMP | 2020-10-22 | COMP | Rule 16 | 116 | 64 | 8 | 19 | 1 | 24 | 228
19915 | 2019-12-02 | 2020-05-27 | 2020-08-04 | 2020-08-04 | COMP | 2020-09-24 | COMP | 2022-03-08 | COMP | 2021-12-08 | COMP | 2022-04-18 | COMP | Rule 16 | 123 | 50 | 37 | 364 | 0 | 30 | 600
4257 | 2019-12-03 | 2019-12-05 | [7 empty] | 2020-07-02 | COMP | 2020-07-22 | COMP | Other | 3 | [5 empty] | 162
15963 | 2019-12-03 | 2019-12-03 | 2020-03-23 | 2020-03-23 | COMP | 2020-11-04 | COMP | 2021-01-07 | COMP | 2021-03-29 | COMP | 2023-01-28 | COMP | Rule 16 | 1 | 76 | 161 | 42 | 56 | 462 | 793
16168 | 2019-12-03 | 2019-12-13 | 2020-06-16 | 2020-06-16 | COMP | 2020-10-14 | COMP | 2021-06-14 | COMP | 2021-06-29 | COMP | 2021-07-20 | COMP | Rule 15/16 | 9 | 128 | 86 | 166 | 12 | 15 | 411
16195 | 2019-12-03 | 2019-12-13 | 2020-06-02 | 2020-06-12 | COMP | 2020-08-12 | COMP | 2020-12-29 | COMP | 2021-01-26 | COMP | 2021-02-04 | COMP | Rule 16 | 9 | 118 | 44 | 95 | 19 | 8 | 296
16247 | 2019-12-03 | 2019-12-17 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-27 | COMP | 2020-05-26 | COMP | 2020-06-12 | COMP | 2020-08-05 | COMP | Rule 16 | 11 | 81 | 11 | 21 | 14 | 39 | 172
16492 | 2019-12-03 | 2020-01-03 | 2020-02-11 | 2020-02-11 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP |  | INPR | 2020-11-11 | COMP | Rule 15/16 | 22 | 27 | 117 | 1 |  |  | 240
16823 | 2019-12-03 | 2020-01-17 | 2020-05-07 | 2020-05-07 | COMP | 2020-08-05 | COMP | 2020-07-16 | COMP | 2022-06-28 | COMP | 2022-08-23 | COMP | Rule 16 | 32 | 78 | 64 |  | 491 | 40 | 687
16884 | 2019-12-03 | 2020-01-22 | 2020-03-09 | 2020-03-09 | COMP | 2020-05-20 | COMP | 2020-05-21 | COMP | 2022-11-30 | COMP | 2020-08-28 | COMP | Rule 16 | 34 | 33 | 53 | 2 | 636 |  | 189
16889 | 2019-12-03 | 2020-01-22 | 2020-02-06 | 2020-02-06 | COMP | 2020-02-27 | COMP | 2020-02-29 | COMP | 2020-03-20 | COMP | 2020-06-02 | COMP | Rule 16 | 34 | 12 | 15 | 2 | 15 | 52 | 126
16935 | 2019-12-03 | 2020-01-25 | 2020-05-08 | 2021-04-07 | COMP | 2021-04-28 | COMP | 2021-04-30 | COMP | 2021-05-05 | COMP | 2021-05-21 | COMP | Rule 16 | 36 | 74 | 16 | 3 | 4 | 13 | 371
17063 | 2019-12-03 | 2020-01-29 | 2020-03-06 | 2020-03-06 | COMP | 2020-03-20 | COMP | 2020-03-20 | COMP | 2020-03-30 | COMP | 2020-04-01 | COMP | Rule 16 | 39 | 27 | 11 | 1 | 7 | 3 | 83
17113 | 2019-12-03 | 2020-01-31 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-17 | COMP | 2020-04-21 | COMP | 2021-01-19 | COMP | 2021-02-12 | COMP | Rule 16 | 41 | 26 | 7 | 26 | 188 | 19 | 302
17150 | 2019-12-03 | 2020-02-01 | 2020-05-08 | 2020-05-08 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2021-05-29 | COMP | 2021-07-08 | COMP | Rule 15/16 | 41 | 69 | 116 | 1 | 152 | 27 | 403
17497 | 2019-12-03 | 2020-02-18 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-07-02 | COMP | 2020-07-15 | COMP | Rule 16 | 52 | 49 | 7 | 1 | 43 | 10 | 157
17809 | 2019-12-03 | 2020-02-27 | 2020-06-28 | 2020-06-28 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2020-11-25 | COMP | 2020-12-28 | COMP | Rule 16 | 59 | 86 | 83 | 1 | 24 | 21 | 270
17923 | 2019-12-03 | 2020-03-04 | 2020-05-22 | 2020-05-22 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-10-16 | COMP | 2020-12-15 | COMP | Rule 16 | 63 | 58 | 61 | 1 | 44 | 40 | 262
18124 | 2019-12-03 | 2020-03-12 | 2020-09-19 | 2020-09-19 | COMP | 2020-11-17 | NOTN | 2020-12-07 | COMP | 2021-01-28 | COMP | 2021-04-27 | COMP | Other | 69 | 135 |  | 53 | 36 | 63 | 353
18490 | 2019-12-03 | 2020-03-26 | 2020-07-21 | 2020-07-21 | COMP | 2021-05-04 | COMP | 2021-05-04 | COMP | 2022-12-22 | COMP | 2022-08-05 | COMP | Rule 16 | 79 | 83 | 198 | 1 | 413 |  | 675
18660 | 2019-12-03 | 2020-04-02 | 2020-07-03 | 2020-07-03 | COMP | 2020-10-05 | COMP | 2021-04-09 | COMP | 2021-11-09 | COMP | 2021-11-17 | COMP | Rule 16 | 84 | 66 | 66 | 128 | 150 | 6 | 495
18674 | 2019-12-03 | 2020-04-02 | 2020-04-05 | 2020-04-05 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-04-29 | COMP | 2020-05-19 | COMP | Rule 16 | 84 | 2 | 12 | 1 | 7 | 15 | 117
19647 | 2019-12-03 | 2020-05-15 | 2020-11-03 | 2020-11-03 | COMP | 2020-12-18 | COMP | 2021-05-28 | COMP | 2021-06-02 | COMP | 2021-06-30 | COMP | Rule 16 | 115 | 121 | 31 | 112 | 3 | 21 | 398
20064 | 2019-12-03 | 2020-06-03 | 2020-08-20 | 2020-08-20 | COMP | 2020-10-13 | COMP | 2021-03-03 | COMP | 2023-11-07 | INPR | 2021-05-21 | COMP | Rule 15/16 | 127 | 57 | 38 | 95 |  |  | 371
16301 | 2019-12-04 | 2019-12-20 | 2020-03-04 | 2020-03-04 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2020-05-12 | COMP | 2020-06-15 | COMP | Rule 16 | 13 | 50 | 12 | 1 | 39 | 24 | 134
16317 | 2019-12-04 | 2019-12-19 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-31 | COMP | 2020-03-31 | COMP | 2021-01-29 | COMP | 2021-02-16 | COMP | Rule 16 | 12 | 42 | 29 | 1 | 211 | 12 | 302
16348 | 2019-12-04 | 2019-12-23 | 2020-02-03 | 2020-07-13 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-08-18 | COMP | Rule 16 | 14 | 28 | 24 | 1 | 1 | 4 | 180
16429 | 2019-12-04 | 2019-12-30 | 2020-05-01 | 2020-05-01 | COMP | 2020-06-11 | NOTN | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-08-15 | COMP | Other | 18 | 87 |  | 29 | 1 | 47 | 178
16542 | 2019-12-04 | 2020-01-07 | 2020-05-08 | 2020-05-08 | COMP | 2021-08-13 | COMP | 2021-09-09 | COMP | 2021-09-28 | COMP | 2021-10-16 | COMP | Rule 16 | 23 | 87 | 320 | 19 | 14 | 14 | 472
16549 | 2019-12-04 | 2020-01-07 | 2020-10-22 | 2020-10-22 | COMP | 2020-11-24 | COMP | 2021-03-10 | COMP |  | INPR | 2021-06-14 | COMP | Rule 16 | 23 | 204 | 23 | 71 |  |  | 385
16667 | 2019-12-04 | 2020-01-10 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-08 | COMP | 2020-09-18 | COMP | 2021-01-27 | COMP | 2021-03-05 | COMP | Rule 15/16 | 26 | 65 | 20 | 94 | 88 | 27 | 315
16685 | 2019-12-04 | 2020-01-12 | 2020-05-18 | 2020-06-08 | COMP | 2020-07-15 | COMP | 2020-07-22 | COMP | 2020-09-09 | COMP | 2020-10-09 | COMP | Rule 16 | 26 | 89 | 28 | 6 | 35 | 23 | 217
16701 | 2019-12-04 | 2020-01-13 | 2020-03-24 | 2020-03-24 | COMP | 2020-03-24 | NOTN | 2020-06-26 | COMP | 2020-06-20 | COMP | 2020-08-06 | COMP | Other | 27 | 50 |  | 68 | 0 | 30 | 172
16719 | 2019-12-04 | 2020-01-14 | 2020-04-07 | 2020-04-07 | COMP | 2020-04-13 | COMP | 2020-07-07 | COMP | 2020-09-29 | COMP | 2020-10-30 | COMP | Rule 16 | 28 | 59 | 5 | 61 | 60 | 24 | 232
16752 | 2019-12-04 | 2020-01-15 | 2020-01-16 | 2020-01-16 | COMP | 2020-01-27 | COMP | 2020-01-27 | COMP | 2020-08-10 | COMP | 2020-10-02 | COMP | Rule 16 | 29 | 2 | 7 | 1 | 139 | 39 | 212
16802 | 2019-12-04 | 2020-01-16 | 2020-02-10 | 2020-02-10 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-04-14 | COMP | 2020-04-17 | COMP | Rule 16 | 30 | 17 | 44 | 1 | 3 | 4 | 94
16808 | 2019-12-04 | 2020-01-16 | 2020-05-19 | 2020-05-19 | COMP | 2020-08-14 | COMP | 2022-02-17 | COMP | 2022-03-01 | COMP | 2022-04-19 | COMP | Rule 15/16 | 30 | 87 | 63 | 380 | 8 | 36 | 599
17124 | 2019-12-04 | 2020-01-31 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-13 | COMP | 2020-05-27 | COMP | 2020-05-05 | COMP | 2020-06-09 | COMP | Rule 15/16 | 40 | 36 | 16 | 32 | 0 | 10 | 130
17256 | 2019-12-04 | 2020-02-06 | 2020-03-29 | 2020-03-29 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-05-04 | COMP | 2020-06-15 | COMP | Rule 16 | 44 | 36 | 15 | 1 | 12 | 30 | 134
17472 | 2019-12-04 | 2020-02-15 | 2020-04-24 | 2020-04-24 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2022-06-18 | INPR | 2021-05-28 | COMP | Rule 16 | 50 | 49 | 90 | 1 |  |  | 375
17473 | 2019-12-04 | 2020-02-15 | 2020-04-24 | 2020-04-24 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2022-06-18 | INPR | 2021-05-28 | COMP | Rule 16 | 50 | 49 | 63 | 1 |  |  | 375
17496 | 2019-12-04 | 2020-02-18 | 2020-04-07 | 2020-04-07 | COMP | 2020-04-10 | COMP | 2020-04-29 | COMP | 2020-04-15 | COMP | 2020-04-30 | COMP | Rule 16 | 51 | 36 | 4 | 14 | 0 | 2 | 103
17581 | 2019-12-04 | 2020-02-20 | 2020-04-21 | 2020-04-21 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-06-10 | COMP | Rule 16 | 53 | 44 | 11 | 1 | 1 | 26 | 131
17855 | 2019-12-04 | 2020-03-02 | 2020-05-04 | 2020-05-04 | COMP | 2020-08-26 | COMP | 2020-12-19 | COMP | 2020-12-19 | COMP | 2021-02-05 | COMP | Rule 16 | 60 | 46 | 82 | 79 | 0 | 32 | 296
17992 | 2019-12-04 | 2020-03-06 | 2020-08-07 | 2020-08-07 | COMP | 2020-11-16 | COMP | 2020-11-16 | COMP | 2021-05-05 | COMP | 2021-05-13 | COMP | Rule 16 | 64 | 110 | 70 | 1 | 117 | 7 | 364
18040 | 2019-12-04 | 2020-03-09 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-04 | COMP | 2020-05-26 | COMP | 2022-01-30 | INPR | 2020-07-09 | COMP | Rule 16 | 65 | 28 | 14 | 16 |  |  | 152
18153 | 2019-12-04 | 2020-03-12 | 2020-11-24 | 2020-11-24 | COMP | 2020-12-17 | COMP | 2021-02-18 | COMP | 2023-11-13 | INPR | 2021-03-01 | COMP | Rule 16 | 68 | 181 | 16 | 42 |  |  | 311
18447 | 2019-12-04 | 2020-03-24 | 2020-05-20 | 2021-06-03 | COMP | 2021-06-14 | COMP | 2021-06-14 | COMP | 2022-02-10 | COMP | 2022-03-16 | COMP | Rule 16 | 76 | 42 | 8 | 1 | 168 | 24 | 575
18598 | 2019-12-04 | 2020-03-31 | 2021-02-18 | 2021-02-18 | COMP | 2021-08-05 | COMP | 2021-11-17 | COMP | 2021-12-14 | COMP | 2022-05-31 | COMP | Rule 15/16 | 81 | 224 | 119 | 73 | 18 | 118 | 628
18599 | 2019-12-04 | 2020-03-31 | 2021-02-18 | 2021-02-18 | COMP | 2021-08-05 | COMP | 2021-11-16 | COMP | 2022-03-16 | COMP | 2022-05-31 | COMP | Rule 15/16 | 81 | 224 | 119 | 72 | 83 | 54 | 628
18640 | 2019-12-04 | 2020-04-01 | 2020-10-19 | 2021-05-25 | COMP | 2021-06-10 | COMP | 2021-09-16 | COMP | 2021-08-17 | COMP | 2021-10-07 | COMP | Rule 16 | 82 | 142 | 12 | 69 | 0 | 16 | 466
18766 | 2019-12-04 | 2020-04-06 | 2020-06-15 | 2020-06-15 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-08-22 | COMP | 2020-09-21 | COMP | Rule 16 | 85 | 50 | 8 | 1 | 43 | 20 | 203
19788 | 2019-12-04 | 2020-05-22 | 2020-08-20 | 2020-08-20 | COMP | 2020-08-25 | NOTN | 2020-08-25 | COMP | 2020-09-15 | NOTN | 2021-03-27 | COMP | Other | 119 | 64 |  | 4 |  |  | 330
20164 | 2019-12-04 | 2020-06-09 | 2020-07-03 | 2020-12-09 | COMP | 2020-12-30 | COMP | 2020-12-30 | COMP | 2021-01-19 | COMP | 2021-03-20 | COMP | Rule 15/16 | 130 | 19 | 15 | 1 | 13 | 43 | 325
20355 | 2019-12-04 | 2020-06-17 | 2020-07-14 | 2020-07-14 | COMP | 2021-01-15 | COMP | 2021-01-15 | COMP | 2021-12-15 | COMP | 2022-02-24 | COMP | Rule 16 | 136 | 20 | 128 | 1 | 231 | 50 | 561
16208 | 2019-12-05 | 2019-12-16 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-04-23 | COMP | 2020-08-05 | COMP | Rule 16 | 8 | 80 | 10 | 1 | 2 | 74 | 170
16332 | 2019-12-05 | 2019-12-20 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-28 | COMP | 2020-05-29 | COMP | 2023-12-09 | INPR | 2020-06-11 | COMP | Rule 16 | 12 | 60 | 30 | 23 |  |  | 131
16449 | 2019-12-05 | 2020-01-02 | 2020-01-30 | 2020-01-30 | COMP | 2020-02-24 | COMP | 2020-07-08 | COMP | 2023-12-03 | INPR | 2021-10-29 | COMP | Rule 16 | 19 | 20 | 17 | 97 |  |  | 481
16481 | 2019-12-05 | 2020-01-03 | 2020-04-21 | 2020-04-21 | COMP | 2020-09-10 | COMP | 2020-09-11 | COMP | 2021-04-27 | COMP | 2021-07-13 | COMP | Rule 15/16 | 20 | 76 | 101 | 2 | 156 | 54 | 404
16495 | 2019-12-05 | 2020-01-04 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2021-01-14 | COMP | 2021-03-04 | COMP | Rule 15/16 | 20 | 85 | 7 | 1 | 170 | 34 | 313
16503 | 2019-12-05 | 2020-01-07 | 2020-04-02 | 2020-08-02 | COMP | 2020-12-01 | COMP | 2020-12-01 | COMP | 2020-12-30 | COMP | 2021-02-09 | COMP | Rule 15/16 | 22 | 61 | 83 | 1 | 21 | 28 | 297
16632 | 2019-12-05 | 2020-01-10 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2020-04-29 | COMP | Rule 16 | 25 | 33 | 11 | 1 | 1 | 35 | 101
16682 | 2019-12-05 | 2020-01-13 | 2020-06-12 | 2020-06-12 | COMP | 2021-01-20 | COMP | 2021-09-23 | COMP | 2021-09-08 | COMP | 2021-09-22 | COMP | Rule 15/16 | 26 | 107 | 152 | 173 | 0 |  | 454
16683 | 2019-12-05 | 2020-01-13 | 2020-08-27 | 2020-09-03 | COMP | 2020-10-28 | COMP | 2020-12-01 | COMP | 2021-07-28 | COMP | 2021-03-25 | COMP | Rule 15/16 | 26 | 161 | 39 | 22 | 166 |  | 328
16807 | 2019-12-05 | 2020-01-16 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-23 | NOTN | 2020-04-23 | COMP | 2020-08-24 | COMP | 2020-11-12 | COMP | Other | 29 | 69 |  | 1 | 87 | 57 | 239
16820 | 2019-12-05 | 2020-01-17 | 2020-04-22 | 2020-04-22 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-07-17 | COMP | 2020-09-09 | COMP | Rule 16 | 30 | 67 | 61 | 1 | 2 | 38 | 194
16838 | 2019-12-05 | 2020-01-17 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-11 | COMP | 2020-03-11 | COMP | 2020-03-24 | COMP | 2020-04-16 | COMP | Rule 16 | 30 | 18 | 20 | 1 | 10 | 18 | 92
17024 | 2019-12-05 | 2020-01-28 | 2020-05-06 | 2020-05-06 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-03 | COMP | 2020-09-16 | COMP | Rule 16 | 36 | 71 | 62 | 1 | 2 | 32 | 199
17172 | 2019-12-05 | 2020-02-03 | 2020-03-19 | 2020-03-19 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-18 | COMP | 2020-07-09 | COMP | Rule 16 | 40 | 33 | 42 | 1 | 2 | 38 | 151
17417 | 2019-12-05 | 2020-02-13 | 2020-04-30 | 2022-04-07 | COMP | 2022-08-10 | COMP | 2020-07-22 | COMP | 2023-10-05 | COMP | 2023-12-05 | COMP | Rule 15/16 | 48 | 55 | 87 |  | 806 | 41 | 1005
17478 | 2019-12-05 | 2020-02-16 | 2020-10-26 | 2020-10-26 | COMP | 2021-10-04 | COMP | 2021-06-01 | COMP | 2021-08-27 | COMP | 2021-10-05 | COMP | Rule 15/16 | 49 | 178 | 236 |  | 63 | 27 | 463
17676 | 2019-12-05 | 2020-02-25 | 2020-10-19 | 2020-10-19 | COMP | 2022-03-23 | COMP | 2022-04-13 | COMP | 2022-03-23 | COMP | 2022-07-31 | COMP | Rule 15/16 | 55 | 168 | 358 | 16 | 0 | 75 | 668
17720 | 2019-12-05 | 2020-02-25 | 2020-07-01 | 2021-08-04 | COMP | 2022-03-10 | COMP | 2022-09-13 | COMP | 2022-09-20 | COMP | 2022-10-07 | COMP | Rule 16 | 55 | 91 | 151 | 130 | 6 | 14 | 717
17912 | 2019-12-05 | 2020-03-04 | 2020-06-01 | 2020-06-01 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-11-12 | COMP | 2020-12-30 | COMP | Rule 16 | 61 | 63 | 27 | 1 | 91 | 32 | 270
17934 | 2019-12-05 | 2020-03-04 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-01 | COMP | 2020-05-21 | COMP | 2020-06-03 | COMP | 2020-06-18 | COMP | Rule 15/16 | 61 | 9 | 13 | 37 | 9 | 12 | 136
18477 | 2019-12-05 | 2020-03-26 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-25 | COMP | 2020-05-29 | COMP | 2020-06-08 | COMP | 2020-07-27 | COMP | Rule 16 | 77 | 42 | 24 |  | 7 | 36 | 163
18621 | 2019-12-05 | 2020-03-31 | 2020-04-30 | 2020-05-05 | COMP | 2020-05-22 | COMP | 2020-05-28 | COMP | 2020-06-24 | COMP | 2020-07-15 | COMP | Rule 15/16 | 80 | 23 | 14 | 4 | 20 | 16 | 155
19037 | 2019-12-05 | 2020-04-17 | 2020-11-13 | 2020-11-13 | COMP | 2021-01-26 | COMP | 2021-04-21 | COMP | 2021-05-03 | COMP | 2021-09-02 | COMP | Rule 16 | 93 | 148 | 48 | 61 | 9 | 87 | 441
19092 | 2019-12-05 | 2020-04-21 | 2020-09-17 | 2020-09-17 | COMP | 2020-09-30 | COMP | 2020-09-30 | COMP | 2020-10-05 | COMP | 2020-12-18 | COMP | Rule 16 | 95 | 106 | 10 | 1 | 4 | 52 | 263
19122 | 2019-12-05 | 2020-04-21 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-12-14 | COMP | 2020-12-19 | COMP | Rule 16 | 95 | 19 | 12 | 1 | 136 | 5 | 263
19147 | 2019-12-05 | 2020-04-22 | 2020-10-15 | 2020-10-15 | COMP | 2020-11-30 | COMP | 2021-03-16 | COMP | 2022-01-12 | COMP | 2022-01-29 | COMP | Rule 15/16 | 96 | 125 | 30 | 73 | 211 | 12 | 542
19365 | 2019-12-05 | 2020-05-04 | 2020-06-02 | 2020-06-02 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-11-10 | COMP | 2020-12-15 | COMP | Rule 16 | 104 | 21 | 36 | 1 | 80 | 23 | 260
19471 | 2019-12-05 | 2020-05-08 | 2020-08-31 | 2021-06-16 | COMP | 2021-09-01 | COMP | 2021-09-01 | COMP | 2022-01-29 | COMP | 2022-03-09 | COMP | Rule 15/16 | 108 | 81 | 55 | 1 | 103 | 27 | 569
19543 | 2019-12-05 | 2020-05-11 | 2021-01-11 | 2021-01-11 | COMP | 2021-01-15 | COMP | 2021-04-08 | COMP | 2023-12-04 | INPR | 2021-04-26 | COMP | Rule 16 | 109 | 169 | 5 | 58 |  |  | 350
19657 | 2019-12-05 | 2020-05-16 | 2020-09-11 | 2020-09-11 | COMP | 2021-03-15 | COMP | 2021-03-15 | COMP | 2021-08-02 | COMP | 2021-08-24 | COMP | Rule 15/16 | 113 | 83 | 125 | 1 | 99 | 17 | 434
19886 | 2019-12-05 | 2020-05-28 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-11-10 | COMP | 2020-12-15 | COMP | Rule 16 | 121 | 19 | 21 | 1 | 80 | 23 | 260
24046 | 2019-12-05 | 2020-12-08 | 2021-02-16 | 2021-02-16 | COMP | 2021-07-07 | COMP | 2021-07-07 | COMP | 2022-05-12 | COMP | 2022-06-16 | COMP | Rule 16 | 255 | 47 | 100 | 1 | 216 | 25 | 639
16144 | 2019-12-06 | 2019-12-13 | 2020-01-27 | 2020-03-13 | COMP | 2020-03-20 | COMP | 2020-03-25 | COMP | 2020-01-27 | COMP | 2020-06-01 | COMP | Rule 16 | 6 | 29 | 6 | 4 | 0 | 48 | 122
16275 | 2019-12-06 | 2019-12-19 | 2020-02-04 | 2020-02-04 | COMP | 2020-02-12 | COMP | 2020-04-02 | COMP | 2020-04-13 | COMP | 2020-06-08 | COMP | Rule 16 | 10 | 31 | 7 | 36 | 8 | 40 | 127
16466 | 2019-12-06 | 2020-01-03 | 2020-04-23 | 2020-04-29 | COMP | 2020-04-27 | NOTN | 2020-05-18 | COMP | 2020-04-27 | COMP | 2020-06-04 | COMP | Other | 19 | 78 |  | 14 | 0 | 13 | 125
16467 | 2019-12-06 | 2020-01-03 | 2020-04-23 | 2020-04-29 | COMP | 2020-04-27 | NOTN | 2020-06-02 | COMP | 2020-04-27 | COMP | 2020-07-16 | COMP | Other | 19 | 78 |  | 24 | 0 | 33 | 155
16468 | 2019-12-06 | 2020-01-03 | 2020-04-14 | 2020-04-29 | COMP | 2020-04-27 | NOTN | 2020-05-15 | COMP | 2020-04-27 | COMP | 2020-06-04 | COMP | Other | 19 | 71 |  | 13 | 0 | 14 | 125
16469 | 2019-12-06 | 2020-01-03 | 2020-04-23 | 2020-04-29 | COMP | 2020-04-27 | NOTN | 2020-05-15 | COMP | 2020-04-27 | COMP | 2020-06-04 | COMP | Other | 19 | 78 |  | 13 | 0 | 14 | 125
16470 | 2019-12-06 | 2020-01-03 | 2020-04-23 | 2020-04-29 | COMP | 2020-04-27 | NOTN | 2020-04-29 | COMP | 2020-04-27 | COMP | 2020-06-09 | COMP | Other | 19 | 78 |  | 1 | 0 | 29 | 128
16498 | 2019-12-06 | 2020-01-03 | 2020-04-23 | 2020-04-29 | COMP | 2020-04-27 | NOTN | 2020-06-06 | COMP | 2020-04-27 | COMP | 2020-06-13 | COMP | Other | 19 | 78 |  | 27 | 0 | 5 | 131
16506 | 2019-12-06 | 2020-01-06 | 2021-04-28 | 2021-08-27 | COMP | 2022-03-10 | COMP | 2022-06-28 | COMP | 2022-08-01 | COMP | 2023-02-22 | COMP | Rule 15/16 | 20 | 332 | 134 | 77 | 24 | 140 | 807
16508 | 2019-12-06 | 2020-01-06 | 2020-03-14 | 2020-03-14 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-06-11 | COMP | Rule 15/16 | 20 | 48 | 48 | 1 | 1 | 16 | 130
16544 | 2019-12-06 | 2020-01-07 | 2020-03-12 | 2020-03-12 | COMP | 2020-03-27 | COMP | 2020-05-19 | COMP | 2021-06-23 | COMP | 2021-09-22 | COMP | Rule 15/16 | 21 | 46 | 12 | 38 | 277 | 64 | 453
16664 | 2019-12-06 | 2020-01-10 | 2020-08-08 | 2020-08-08 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-08-18 | COMP | 2020-09-22 | COMP | Rule 15/16 | 24 | 148 | 2 | 1 | 6 | 25 | 202
16763 | 2019-12-06 | 2020-01-14 | 2020-03-22 | 2020-03-22 | COMP | 2020-03-31 | COMP | 2020-05-28 | NOTN | 2020-05-11 | COMP | 2020-06-10 | COMP | Rule 16 | 26 | 47 | 7 |  |  |  | 129
16928 | 2019-12-06 | 2020-01-24 | 2020-07-13 | 2020-07-13 | COMP | 2020-10-27 | COMP | 2021-02-23 | COMP | 2021-07-27 | COMP | 2021-08-24 | COMP | Rule 15/16 | 33 | 120 | 76 | 79 | 109 | 21 | 433
16961 | 2019-12-06 | 2020-01-25 | 2020-04-17 | 2020-04-17 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-10-30 | COMP | 2020-11-05 | COMP | Rule 16 | 33 | 59 | 21 | 1 | 119 | 5 | 234
17304 | 2019-12-06 | 2020-02-07 | 2020-04-22 | 2020-04-22 | COMP | 2020-04-28 | COMP | 2020-05-07 | COMP | 2022-01-30 | INPR | 2020-07-01 | COMP | Rule 16 | 43 | 53 | 5 | 8 |  |  | 144
17331 | 2019-12-06 | 2020-02-10 | 2020-08-05 | 2020-12-11 | COMP | 2021-10-05 | COMP | 2023-04-25 | COMP | 2023-03-01 | COMP | 2023-06-13 | COMP | Rule 15/16 | 44 | 126 | 206 | 390 | 0 | 35 | 885
17348 | 2019-12-06 | 2020-02-10 | 2020-02-26 | 2020-11-15 | COMP | 2020-11-30 | COMP | 2020-11-30 | INPR | 2020-11-30 | COMP | 2020-12-01 | COMP | Rule 16 | 44 | 12 | 9 |  |  |  | 249
17382 | 2019-12-06 | 2020-02-12 | 2020-03-29 | 2020-03-29 | COMP | 2020-05-06 | COMP | 2020-05-29 | COMP | 2023-11-13 | INPR | 2020-06-13 | COMP | Rule 16 | 46 | 32 | 28 | 17 |  |  | 131
17613 | 2019-12-06 | 2020-02-21 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-11-16 | COMP | 2020-12-01 | COMP | Rule 15/16 | 52 | 44 | 12 | 1 | 135 | 10 | 249
17699 | 2019-12-06 | 2020-02-25 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-11-23 | COMP | 2021-01-19 | COMP | Rule 16 | 54 | 70 | 15 | 1 | 109 | 37 | 281
18483 | 2019-12-06 | 2020-03-26 | 2020-08-26 | 2020-08-26 | COMP | 2021-05-28 | COMP | 2021-08-25 | COMP | 2022-11-07 | COMP | 2023-02-02 | COMP | Rule 16 | 76 | 109 | 190 | 62 | 304 | 58 | 794
21158 | 2019-12-06 | 2020-07-23 | 2020-08-13 | 2020-08-13 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | 2021-01-28 | COMP | 2021-03-16 | COMP | Rule 16 | 160 | 16 | 10 | 1 | 105 | 33 | 320
28020 | 2019-12-06 | 2021-05-18 | 2021-06-18 | 2021-06-18 | COMP | 2021-06-21 | NOTN | 2021-06-30 | COMP | 2021-06-29 | COMP | 2021-08-24 | COMP | Other | 365 | 23 |  | 9 | 0 | 39 | 433
17264 | 2019-12-07 | 2020-02-06 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-06-01 | COMP | 2020-07-21 | COMP | Rule 15/16 | 41 | 66 | 15 | 1 | 2 | 37 | 157
17341 | 2019-12-07 | 2020-02-10 | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | NOTN | 2020-08-14 | COMP | 2020-06-25 | COMP | 2020-10-01 | COMP | Other | 43 | 91 |  | 43 | 0 | 34 | 208
18267 | 2019-12-07 | 2020-03-18 | 2020-04-26 | 2020-06-02 | COMP | 2020-08-27 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2020-09-14 | COMP | Rule 16 | 69 | 28 | 63 | 8 | 1 | 5 | 195
16257 | 2019-12-08 | 2019-12-18 | 2020-01-16 | 2020-01-16 | COMP | 2020-02-06 | COMP | 2020-02-06 | COMP | 2022-01-30 | INPR | 2020-06-03 | COMP | Rule 16 | 8 | 20 | 15 | 1 |  |  | 123
16319 | 2019-12-08 | 2019-12-20 | 2020-04-23 | 2020-05-04 | COMP | 2020-06-03 | COMP | 2020-06-22 | COMP | 2020-06-15 | COMP | 2020-08-13 | COMP | Rule 16 | 10 | 86 | 22 | 14 | 0 | 39 | 174
16757 | 2019-12-08 | 2020-01-14 | 2020-05-26 | 2020-05-26 | COMP | 2020-07-27 | NOTN | 2020-07-29 | COMP | 2020-09-16 | NOTN | 2021-01-12 | COMP | Other | 25 | 93 |  | 47 |  |  | 276
20086 | 2019-12-08 | 2020-06-04 | 2020-08-05 | 2021-02-19 | COMP | 2022-04-15 | COMP | 2022-03-01 | COMP | 2022-03-22 | COMP | 2022-04-29 | COMP | Rule 16 | 124 | 45 | 293 |  | 16 | 29 | 604
4258 | 2019-12-09 | 2019-12-12 | 2020-07-29 | 2019-12-13 | COMP |  |  |  |  | 2019-12-12 | COMP | 2020-01-10 | COMP | Other | 4 | 160 |  |  |  |  | 23
16244 | 2019-12-09 | 2019-12-17 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-02 | COMP | 2020-03-31 | COMP | Rule 16 | 7 | 50 | 2 | 1 | 1 | 22 | 78
16288 | 2019-12-09 | 2019-12-19 | 2020-02-07 | 2020-02-07 | COMP | 2020-02-11 | NOTN | 2020-02-25 | COMP | 2020-02-11 | COMP | 2020-03-11 | COMP | Rule 16 | 9 | 34 |  | 12 | 0 | 12 | 64
16425 | 2019-12-09 | 2019-12-30 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-08 | COMP | 2020-08-10 | COMP | 2020-08-12 | COMP | 2020-10-14 | COMP | Rule 15/16 | 15 | 56 | 15 | 88 | 3 | 45 | 217
16643 | 2019-12-09 | 2020-01-09 | 2020-04-09 | 2020-05-04 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-11 | COMP | 2020-09-02 | COMP | Rule 16 | 22 | 64 | 64 | 1 | 8 | 17 | 188
16735 | 2019-12-09 | 2020-01-14 | 2020-02-18 | 2020-02-18 | COMP | 2020-02-26 | NOTN | 2020-02-26 | COMP | 2022-11-30 | COMP | 2020-04-06 | COMP | Other | 25 | 24 |  | 7 | 697 |  | 82
16864 | 2019-12-09 | 2020-01-21 | 2020-03-06 | 2020-03-06 | COMP | 2020-03-31 | COMP | 2020-04-24 | COMP | 2020-05-04 | COMP | 2020-05-13 | COMP | Rule 16 | 29 | 33 | 18 | 19 | 7 | 8 | 109
16932 | 2019-12-09 | 2020-01-25 | 2020-05-06 | 2020-05-06 | COMP | 2021-04-09 | COMP | 2021-04-09 | COMP | 2021-07-01 | COMP | 2021-09-10 | COMP | Rule 16 | 32 | 72 | 234 | 1 | 59 | 50 | 444
17108 | 2019-12-09 | 2020-01-30 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-23 | COMP | 2020-07-31 | COMP | 2020-07-17 | COMP | 2020-08-25 | COMP | Rule 16 | 36 | 79 | 24 | 29 | 0 | 18 | 182
17337 | 2019-12-09 | 2020-02-10 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-12-07 | COMP | 2020-12-18 | COMP | Rule 16 | 43 | 36 | 13 | 1 | 163 | 10 | 261
17455 | 2019-12-09 | 2020-02-13 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-04-21 | COMP | 2020-06-05 | COMP | Rule 16 | 46 | 22 | 20 | 1 | 8 | 33 | 125
17569 | 2019-12-09 | 2020-02-20 | 2020-03-24 | 2020-03-24 | COMP | 2020-03-26 | NOTN | 2020-05-19 | COMP | 2020-04-13 | NOTN | 2020-07-15 | COMP | Rule 16 | 50 | 24 |  | 41 |  |  | 153
17603 | 2019-12-09 | 2020-02-21 | 2020-06-13 | 2020-06-13 | COMP | 2020-07-02 | COMP | 2020-07-06 | COMP | 2020-08-24 | COMP | 2020-09-01 | COMP | Rule 16 | 51 | 80 | 14 | 3 | 36 | 7 | 187
17653 | 2019-12-09 | 2020-02-24 | 2021-01-26 | 2021-01-26 | COMP | 2021-03-12 | COMP | 2021-05-05 | COMP | 2021-04-30 | COMP | 2021-06-05 | COMP | Rule 15/16 | 52 | 234 | 33 | 39 | 0 | 22 | 376
17733 | 2019-12-09 | 2020-02-25 | 2021-07-22 | 2021-07-22 | COMP | 2021-08-18 | COMP | 2021-09-15 | COMP | 2021-08-22 | COMP | 2021-10-15 | COMP | Rule 15/16 | 53 | 357 | 20 | 20 | 0 | 23 | 469
17776 | 2019-12-09 | 2020-02-26 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-26 | COMP | 2020-08-21 | COMP | 2020-09-15 | COMP | 2020-11-12 | COMP | Rule 16 | 54 | 60 | 5 | 64 | 17 | 42 | 237
17904 | 2019-12-09 | 2020-03-03 | 2020-03-23 | 2020-06-05 | COMP | 2020-06-09 | COMP | 2020-06-23 | COMP | 2020-06-24 | COMP | 2020-08-07 | COMP | Rule 16 | 58 | 15 | 3 | 11 | 2 | 33 | 170
18221 | 2019-12-09 | 2020-03-16 | 2020-06-17 | 2020-10-08 | COMP | 2020-11-30 | COMP | 2021-08-25 | COMP | 2021-09-20 | COMP | 2021-10-04 | COMP | Rule 16 | 67 | 67 | 35 | 187 | 18 | 11 | 460
18426 | 2019-12-09 | 2020-03-24 | 2020-05-20 | 2020-05-20 | COMP | 2023-11-03 | COMP | 2020-06-18 | COMP | 2024-02-29 | COMP | 2021-12-07 | COMP | Rule 16 | 73 | 42 | 871 |  | 928 |  | 503
18616 | 2019-12-09 | 2020-03-31 | 2020-07-24 | 2020-07-24 | COMP | 2021-02-26 | COMP | 2021-06-23 | COMP | 2021-08-25 | COMP | 2022-04-22 | COMP | Rule 15/16 | 78 | 83 | 148 | 83 | 45 | 167 | 599
18881 | 2019-12-09 | 2020-04-09 | 2020-08-24 | 2020-08-24 | COMP | 2020-09-17 | COMP | 2020-12-22 | COMP | 2021-04-20 | COMP | 2021-05-05 | COMP | Rule 15/16 | 85 | 97 | 18 | 66 | 82 | 12 | 355
18963 | 2019-12-09 | 2020-04-14 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-03 | COMP | 2020-07-20 | COMP | 2020-10-13 | COMP | 2020-11-06 | COMP | Rule 16 | 88 | 33 | 4 | 34 | 61 | 19 | 234
19320 | 2019-12-09 | 2020-04-30 | 2021-03-16 | 2021-03-16 | COMP | 2021-03-23 | COMP | 2021-05-22 | COMP | 2022-06-18 | INPR | 2021-06-07 | COMP | Rule 16 | 100 | 220 | 6 | 44 |  |  | 377
19507 | 2019-12-09 | 2020-05-09 | 2020-08-11 | 2020-08-11 | COMP | 2020-09-08 | COMP | 2020-11-23 | COMP | 2020-10-16 | COMP | 2020-12-22 | COMP | Rule 16 | 106 | 66 | 20 | 54 | 0 | 20 | 263
20290 | 2019-12-09 | 2020-06-15 | 2020-07-14 | 2020-07-14 | COMP | 2020-11-02 | COMP | 2021-09-08 | COMP | 2021-10-12 | COMP | 2021-11-22 | COMP | Rule 16 | 131 | 22 | 79 | 213 | 25 | 29 | 494
20854 | 2019-12-09 | 2020-07-09 | 2020-08-03 | 2020-10-27 | COMP | 2020-12-02 | COMP | 2020-12-17 | COMP | 2020-12-17 | COMP | 2021-01-11 | COMP | Rule 16 | 149 | 18 | 24 | 12 | 1 | 16 | 275
16305 | 2019-12-10 | 2019-12-19 | 2020-01-22 | 2020-01-22 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-02-25 | COMP | 2020-04-02 | COMP | Rule 16 | 8 | 22 | 24 | 1 | 1 | 28 | 79
16454 | 2019-12-10 | 2019-12-31 | 2020-03-03 | 2020-03-03 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2020-04-12 | COMP | 2020-04-20 | COMP | Rule 16 | 15 | 43 | 25 | 1 | 5 | 6 | 91
16496 | 2019-12-10 | 2020-01-04 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-06-29 | COMP | 2020-08-12 | COMP | Rule 16 | 17 | 67 | 7 | 1 | 51 | 33 | 172
16710 | 2019-12-10 | 2020-01-14 | 2020-05-08 | 2020-10-01 | COMP | 2021-03-31 | COMP | 2021-05-12 | COMP | 2021-02-25 | COMP | 2021-06-10 | COMP | Other | 24 | 82 | 123 | 31 | 0 | 21 | 379
16855 | 2019-12-10 | 2020-01-21 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-23 | COMP | 2020-10-30 | COMP | 2020-11-10 | COMP | 2020-12-16 | COMP | Rule 16 | 28 | 78 | 54 | 71 | 8 | 24 | 258
17129 | 2019-12-10 | 2020-01-31 | 2020-04-07 | 2020-04-07 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-11-17 | COMP | 2020-12-16 | COMP | Rule 16 | 36 | 47 | 85 | 1 | 74 | 20 | 258
17338 | 2019-12-10 | 2020-02-10 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-09-17 | COMP | 2021-06-05 | COMP | Rule 16 | 42 | 33 | 12 | 1 | 113 | 179 | 375
17351 | 2019-12-10 | 2020-02-10 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-13 | COMP | 2020-05-18 | COMP | 2020-06-09 | COMP | 2020-06-23 | COMP | Rule 16 | 42 | 48 | 20 | 4 | 16 | 11 | 136
17459 | 2019-12-10 | 2020-02-14 | 2020-05-14 | 2020-05-14 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2021-03-29 | COMP | 2021-04-13 | COMP | Rule 16 | 46 | 64 | 18 | 1 | 202 | 12 | 338
17732 | 2019-12-10 | 2020-02-25 | 2020-04-25 | 2020-04-25 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2022-07-23 | INPR | 2021-06-29 | COMP | Rule 16 | 52 | 44 | 63 | 1 |  |  | 392
18688 | 2019-12-10 | 2020-04-02 | 2020-04-20 | 2020-04-20 | COMP | 2020-09-18 | COMP | 2020-12-18 | COMP | 2020-11-30 | COMP | 2021-01-24 | COMP | Rule 16 | 79 | 13 | 108 | 63 | 0 | 23 | 282
18799 | 2019-12-10 | 2020-04-07 | 2020-04-23 | 2020-04-29 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-05-14 | COMP | 2020-08-05 | COMP | Rule 16 | 82 | 13 | 6 | 1 | 7 | 59 | 167
18800 | 2019-12-10 | 2020-04-07 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-23 | NOTN | 2020-07-23 | COMP | 2020-07-23 | COMP | 2021-02-26 | COMP | Other | 82 | 53 |  | 25 | 1 | 149 | 306
19944 | 2019-12-10 | 2020-05-28 | 2020-08-14 | 2020-08-14 | COMP | 2021-01-27 | COMP | 2021-01-27 | COMP | 2021-02-09 | COMP | 2021-03-10 | COMP | Rule 16 | 118 | 57 | 112 | 1 | 10 | 21 | 314
21521 | 2019-12-10 | 2020-08-11 | 2020-09-28 | 2020-09-28 | COMP | 2021-02-16 | COMP | 2021-02-19 | COMP | 2022-09-19 | COMP | 2022-12-16 | COMP | Rule 16 | 171 | 34 | 95 | 4 | 400 | 62 | 761
30685 | 2019-12-10 | 2021-09-08 | 2021-10-02 | 2021-10-02 | COMP | 2021-10-25 | COMP | 2022-03-29 | COMP | 2022-03-11 | COMP | 2022-05-10 | COMP | Rule 15/16 | 441 | 18 | 16 | 107 | 0 | 31 | 610
16143 | 2019-12-11 | 2019-12-12 | 2020-04-02 | 2020-04-29 | COMP | 2020-04-30 | NOTN | 2020-06-07 | COMP | 2020-06-23 | NOTN | 2020-08-18 | COMP | Rule 16 | 2 | 77 |  | 27 |  |  | 175
16511 | 2019-12-11 | 2020-01-06 | 2020-04-15 | 2020-12-18 | COMP | 2021-01-22 | COMP | 2021-03-01 | COMP | 2021-03-01 | COMP | 2021-04-07 | COMP | Rule 16 | 17 | 71 | 23 | 26 | 1 | 28 | 333
16641 | 2019-12-11 | 2020-01-09 | 2020-03-24 | 2020-03-24 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-04-12 | COMP | 2020-08-06 | COMP | Rule 16 | 20 | 52 | 12 | 1 | 3 | 83 | 167
16946 | 2019-12-11 | 2020-01-24 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-22 | COMP | 2020-06-23 | COMP | 2020-07-06 | COMP | 2020-08-26 | COMP | Rule 16 | 30 | 80 | 6 | 22 | 10 | 38 | 181
16948 | 2019-12-11 | 2020-01-24 | 2020-05-07 | 2020-05-07 | COMP | 2020-06-03 | COMP | 2020-08-28 | COMP | 2020-09-03 | COMP | 2020-09-29 | COMP | Rule 16 | 30 | 74 | 19 | 63 | 5 | 18 | 204
16966 | 2019-12-11 | 2020-01-27 | 2020-05-08 | 2020-05-11 | COMP | 2020-05-15 | COMP | 2020-07-21 | COMP | 2020-06-04 | COMP | 2020-08-03 | COMP | Rule 16 | 31 | 74 | 5 | 47 | 0 | 10 | 164
16969 | 2019-12-11 | 2020-01-27 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2020-11-30 | COMP | 2020-12-12 | COMP | Rule 16 | 31 | 58 | 14 | 1 | 145 | 10 | 254
17020 | 2019-12-11 | 2020-01-28 | 2020-10-15 | 2020-10-15 | COMP | 2021-03-05 | COMP | 2021-04-13 | COMP | 2022-06-27 | COMP | 2022-07-19 | COMP | Rule 16 | 32 | 185 | 95 | 28 | 305 | 16 | 656
17053 | 2019-12-11 | 2020-01-29 | 2020-05-01 | 2020-05-07 | COMP | 2021-04-06 | COMP | 2023-04-13 | COMP |  | INPR | 2023-04-28 | COMP | Rule 16 | 33 | 67 | 230 | 509 |  |  | 851
17302 | 2019-12-11 | 2020-02-08 | 2020-08-19 | 2020-08-19 | COMP | 2020-08-26 | COMP | 2020-09-02 | COMP | 2020-09-09 | COMP | 2020-10-14 | COMP | Rule 15/16 | 40 | 136 | 6 | 6 | 5 | 26 | 215
17636 | 2019-12-11 | 2020-02-24 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2022-01-30 | INPR | 2020-07-03 | COMP | Rule 16 | 50 | 11 | 7 | 1 |  |  | 143
17790 | 2019-12-11 | 2020-02-26 | 2020-04-23 | 2020-08-19 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2020-11-23 | COMP | 2021-01-04 | COMP | Rule 16 | 52 | 42 | 53 | 1 | 15 | 27 | 268
17884 | 2019-12-11 | 2020-03-03 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-15 | COMP | 2020-07-11 | COMP | 2020-07-12 | COMP | 2020-08-26 | COMP | Rule 16 | 56 | 49 | 6 | 40 | 0 | 33 | 181
18064 | 2019-12-11 | 2020-03-10 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-28 | COMP | 2020-09-21 | COMP | 2020-08-04 | COMP | 2020-10-12 | COMP | Rule 16 | 61 | 37 | 21 | 82 | 0 | 16 | 213
18086 | 2019-12-11 | 2020-03-10 | 2020-06-17 | 2020-06-17 | COMP | 2020-06-16 | NOTN | 2020-09-03 | COMP | 2020-11-30 | COMP | 2021-01-23 | COMP | Other | 61 | 71 |  | 57 | 59 | 37 | 281
18247 | 2019-12-11 | 2020-03-17 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-13 | COMP | 2020-06-13 | COMP | 2020-10-30 | COMP | 2020-11-10 | COMP | Rule 16 | 66 | 40 | 24 | 0 | 99 | 8 | 234
18676 | 2019-12-11 | 2020-04-02 | 2020-08-07 | 2020-08-07 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2020-12-07 | COMP | 2021-01-08 | COMP | Rule 16 | 78 | 91 | 75 | 1 | 9 | 23 | 272
19267 | 2019-12-11 | 2020-04-28 | 2020-08-18 | 2020-08-18 | COMP | 2021-01-28 | COMP | 2021-01-28 | COMP | 2021-02-18 | COMP | 2021-03-02 | COMP | Rule 16 | 96 | 80 | 111 | 1 | 15 | 9 | 307
19808 | 2019-12-11 | 2020-05-22 | 2020-08-06 | 2020-08-06 | COMP | 2020-08-10 | COMP | 2021-01-14 | COMP | 2021-01-13 | COMP | 2021-02-10 | COMP | Rule 16 | 114 | 54 | 3 | 108 | 0 | 19 | 294
19984 | 2019-12-11 | 2020-06-01 | 2020-07-27 | 2020-11-16 | COMP | 2021-01-15 | COMP | 2021-01-15 | COMP | 2021-02-08 | COMP | 2021-02-17 | COMP | Rule 15/16 | 119 | 41 | 41 | 1 | 16 | 7 | 298
20622 | 2019-12-11 | 2020-06-30 | 2020-09-21 | 2020-09-21 | COMP | 2020-09-25 | COMP | 2021-02-23 | COMP | 2021-02-12 | COMP | 2021-04-01 | COMP | Rule 15/16 | 140 | 59 | 5 | 101 | 0 | 28 | 329
20677 | 2019-12-11 | 2020-07-01 | 2020-11-09 | 2021-09-13 | COMP | 2022-01-10 | COMP | 2021-09-29 | COMP |  | INPR | 2022-02-09 | COMP | Rule 16 | 141 | 93 | 83 |  |  |  | 546
25612 | 2019-12-11 | 2021-02-18 | 2021-04-02 | 2021-04-02 | COMP | 2021-06-07 | COMP | 2021-07-16 | COMP | 2021-10-05 | COMP | 2021-10-06 | COMP | Rule 16 | 299 | 32 | 46 | 29 | 57 | 2 | 460
16455 | 2019-12-12 | 2020-01-02 | 2020-09-18 | 2020-09-18 | COMP | 2021-02-02 | COMP | 2022-03-15 | COMP | 2022-03-16 | COMP | 2022-04-09 | COMP | Rule 15/16 | 14 | 183 | 92 | 282 | 2 | 18 | 586
16512 | 2019-12-12 | 2020-01-06 | 2020-02-26 | 2020-02-26 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-04-02 | COMP | Rule 16 | 16 | 36 | 3 | 1 | 1 | 25 | 77
16658 | 2019-12-12 | 2020-01-10 | 2020-02-12 | 2020-02-12 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-11-04 | COMP | 2020-12-08 | COMP | Rule 16 | 20 | 23 | 28 | 1 | 161 | 22 | 250
17106 | 2019-12-12 | 2020-01-30 | 2020-05-11 | 2020-05-11 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-08-17 | COMP | 2020-09-24 | COMP | Rule 16 | 33 | 72 | 38 | 1 | 33 | 28 | 200
17216 | 2019-12-12 | 2020-02-04 | 2020-05-02 | 2020-05-02 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-07-01 | COMP | Rule 16 | 36 | 63 | 19 | 1 | 1 | 24 | 140
17313 | 2019-12-12 | 2020-02-10 | 2020-03-02 | 2020-03-02 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-06-04 | COMP | Rule 16 | 40 | 15 | 40 | 1 | 1 | 29 | 121
17512 | 2019-12-12 | 2020-02-19 | 2020-03-16 | 2021-11-09 | COMP | 2021-11-09 | NOTN | 2021-01-08 | COMP | 2021-08-11 | COMP | 2021-11-26 | COMP | Other | 46 | 19 |  |  | 150 | 74 | 493
17878 | 2019-12-12 | 2020-03-02 | 2020-04-13 | 2020-04-13 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-15 | COMP | 2020-07-29 | COMP | Rule 16 | 54 | 31 | 43 | 1 | 3 | 33 | 160
17931 | 2019-12-12 | 2020-03-04 | 2020-11-21 | 2020-11-21 | COMP | 2021-01-26 | COMP | 2021-10-04 | COMP | 2021-10-04 | COMP | 2021-12-07 | COMP | Rule 15/16 | 56 | 185 | 42 | 176 | 1 | 44 | 500
17932 | 2019-12-12 | 2020-03-04 | 2021-01-19 | 2021-01-19 | COMP | 2021-02-02 | COMP | 2021-07-07 | COMP | 2021-07-09 | COMP | 2021-12-21 | COMP | Rule 15/16 | 56 | 222 | 11 | 109 | 3 | 114 | 510
19367 | 2019-12-12 | 2020-05-04 | 2020-06-02 | 2020-06-02 | COMP | 2020-07-28 | COMP | 2020-08-03 | COMP | 2021-03-30 | COMP | 2021-04-30 | COMP | Rule 16 | 99 | 21 | 41 | 5 | 164 | 24 | 349
19601 | 2019-12-12 | 2020-05-14 | 2020-09-11 | 2020-09-11 | COMP | 2020-09-24 | COMP | 2020-10-15 | COMP | 2021-04-06 | COMP | 2021-04-28 | COMP | Rule 15/16 | 107 | 85 | 10 | 16 | 117 | 17 | 347
21056 | 2019-12-12 | 2020-07-19 | 2020-11-19 | 2021-07-15 | COMP | 2021-07-29 | COMP | 2021-08-12 | COMP | 2021-07-01 | COMP | 2021-09-30 | COMP | Rule 16 | 152 | 87 | 11 | 11 | 0 | 35 | 455
23837 | 2019-12-12 | 2020-11-25 | 2021-04-07 | 2021-04-07 | COMP | 2021-06-09 | COMP | 2022-01-05 | COMP | 2021-12-15 | COMP | 2022-02-16 | COMP | Rule 16 | 243 | 90 | 45 | 146 | 0 | 30 | 550
16256 | 2019-12-13 | 2019-12-17 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-27 | COMP | 2020-05-07 | COMP | 2021-02-23 | COMP | 2021-03-24 | COMP | Rule 16 | 3 | 48 | 23 | 30 | 200 | 22 | 321
16451 | 2019-12-13 | 2019-12-31 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-26 | COMP | 2020-06-10 | COMP | 2020-07-15 | COMP | 2020-08-28 | COMP | Rule 16 | 12 | 94 | 9 | 12 | 26 | 33 | 181
16504 | 2019-12-13 | 2020-01-07 | 2020-02-22 | 2020-02-22 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-09-03 | COMP | 2020-09-17 | COMP | Rule 16 | 16 | 32 | 115 | 1 | 24 | 10 | 194
16541 | 2019-12-13 | 2020-01-07 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-22 | COMP | 2020-05-12 | COMP | 2020-06-23 | COMP | 2020-07-02 | COMP | Rule 16 | 16 | 55 | 21 | 15 | 30 | 8 | 140
16556 | 2019-12-13 | 2020-01-07 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-06-17 | COMP | Rule 16 | 16 | 73 | 11 | 1 | 6 | 27 | 129
16607 | 2019-12-13 | 2020-01-09 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-21 | COMP | 2020-10-21 | COMP | 2021-08-12 | COMP | 2021-08-26 | COMP | Rule 16 | 18 | 16 | 14 | 172 | 203 | 11 | 430
17031 | 2019-12-13 | 2020-01-28 | 2020-03-23 | 2020-03-23 | COMP | 2020-04-08 | COMP | 2020-05-21 | COMP | 2020-06-25 | COMP | 2020-06-24 | COMP | Rule 16 | 30 | 39 | 13 | 32 | 25 |  | 134
17117 | 2019-12-13 | 2020-01-31 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-30 | COMP | 2020-04-23 | COMP | 2020-04-21 | COMP | 2020-05-06 | COMP | Rule 16 | 33 | 22 | 20 | 19 | 0 | 10 | 100
17143 | 2019-12-13 | 2020-02-01 | 2020-03-22 | 2020-05-29 | COMP | 2020-06-05 | COMP | 2020-08-06 | NOTN | 2020-08-04 | COMP | 2020-08-27 | COMP | Rule 16 | 33 | 34 | 6 |  |  |  | 180
17204 | 2019-12-13 | 2020-02-04 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-06-16 | COMP | 2020-07-21 | COMP | Rule 16 | 35 | 50 | 9 | 1 | 37 | 26 | 153
17364 | 2019-12-13 | 2020-02-11 | 2020-06-18 | 2020-06-18 | COMP | 2020-06-30 | COMP | 2020-10-06 | COMP | 2020-09-25 | COMP | 2020-12-03 | COMP | Rule 16 | 40 | 91 | 9 | 70 | 0 | 40 | 246
17541 | 2019-12-13 | 2020-02-20 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-05 | COMP | 2020-06-05 | NOTN | 2020-12-07 | COMP | 2020-12-16 | COMP | Rule 16 | 46 | 71 | 6 |  |  |  | 255
17658 | 2019-12-13 | 2020-02-24 | 2020-11-15 | 2020-11-15 | COMP | 2020-11-23 | COMP | 2021-05-24 | COMP | 2023-12-03 | INPR | 2021-12-14 | COMP | Rule 16 | 48 | 187 | 6 | 125 |  |  | 504
18304 | 2019-12-13 | 2020-03-19 | 2020-09-24 | 2020-09-24 | COMP | 2020-10-05 | COMP | 2020-10-02 | COMP | 2023-11-13 | INPR | 2021-02-12 | COMP | Rule 16 | 66 | 134 | 8 |  |  |  | 294
18409 | 2019-12-13 | 2020-03-23 | 2021-01-15 | 2021-01-15 | COMP | 2021-02-22 | COMP | 2021-02-26 | COMP | 2021-05-06 | COMP | 2021-06-03 | COMP | Rule 15/16 | 68 | 208 | 25 | 5 | 50 | 20 | 371
19570 | 2019-12-13 | 2020-05-12 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-07-27 | COMP | 2020-08-13 | COMP | Rule 16 | 104 | 45 | 5 | 1 | 6 | 14 | 170
18431 | 2019-12-14 | 2020-03-24 | 2020-11-16 | 2020-11-16 | COMP | 2021-02-23 | COMP | 2021-03-11 | COMP | 2021-03-02 | COMP | 2021-05-12 | COMP | Rule 15/16 | 68 | 167 | 66 | 13 | 0 | 45 | 355
17591 | 2019-12-15 | 2020-02-20 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-07-01 | COMP | 2020-08-22 | COMP | Rule 16 | 45 | 78 | 16 | 1 | 2 | 38 | 175
4260 | 2019-12-16 | 2019-12-18 | [7 empty] | 2020-05-29 | COMP | 2020-06-22 | COMP | Other | 3 | [5 empty] | 131
16581 | 2019-12-16 | 2020-01-08 | 2020-02-01 | 2020-02-01 | COMP | 2020-06-12 | COMP | 2020-06-12 | NOTN | 2020-06-12 | COMP | 2020-06-26 | COMP | Rule 16 | 16 | 17 | 93 |  |  |  | 135
16640 | 2019-12-16 | 2020-01-09 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-04-21 | COMP | 2020-05-18 | COMP | Rule 16 | 17 | 49 | 22 | 1 | 3 | 20 | 107
16704 | 2019-12-16 | 2020-01-14 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-08-07 | COMP | 2020-09-18 | COMP | Rule 16 | 20 | 82 | 46 | 1 | 20 | 30 | 194
16974 | 2019-12-16 | 2020-01-27 | 2020-10-25 | 2020-10-25 | COMP | 2020-12-21 | COMP | 2021-04-27 | COMP | 2021-05-04 | COMP | 2021-06-10 | COMP | Rule 15/16 | 28 | 192 | 38 | 88 | 6 | 27 | 375
17269 | 2019-12-16 | 2020-02-06 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-01 | NOTN | 2020-05-29 | COMP | 2020-05-01 | COMP | 2020-08-05 | COMP | Other | 36 | 60 |  | 21 | 0 | 49 | 163
17334 | 2019-12-16 | 2020-02-10 | 2020-03-25 | 2020-03-25 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-07-10 | COMP | 2020-08-27 | COMP | Rule 16 | 38 | 32 | 31 | 1 | 47 | 35 | 179
17359 | 2019-12-16 | 2020-02-11 | 2020-04-30 | 2020-04-30 | COMP | 2020-04-30 | NOTN | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-06-23 | COMP | Other | 39 | 57 |  | 1 | 1 | 38 | 132
17468 | 2019-12-16 | 2020-02-14 | 2020-12-04 | 2020-12-04 | COMP | 2021-02-01 | COMP | 2021-02-27 | COMP | 2022-03-20 | INPR | 2021-03-08 | COMP | Rule 16 | 42 | 205 | 39 | 19 |  |  | 308
17660 | 2019-12-16 | 2020-02-24 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-06-03 | COMP | 2020-06-09 | COMP | Rule 16 | 47 | 27 | 10 | 1 | 37 | 5 | 122
18089 | 2019-12-16 | 2020-03-10 | 2020-06-17 | 2020-06-17 | COMP | 2020-11-04 | NOTN | 2020-11-04 | COMP | 2022-06-13 | COMP | 2022-10-03 | COMP | Other | 58 | 71 |  | 100 | 403 | 78 | 706
18111 | 2019-12-16 | 2020-03-11 | 2020-04-01 | 2020-04-28 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-06-29 | COMP | 2020-08-07 | COMP | Rule 16 | 59 | 16 | 7 | 1 | 38 | 30 | 165
18197 | 2019-12-16 | 2020-03-16 | 2020-09-25 | 2021-05-01 | COMP | 2021-05-07 | COMP | 2020-12-22 | COMP | 2021-06-01 | COMP | 2021-07-29 | COMP | Rule 16 | 62 | 138 | 5 |  | 111 | 42 | 409
18278 | 2019-12-16 | 2020-03-19 | 2020-06-22 | 2020-06-22 | COMP | 2020-06-25 | COMP | 2020-07-29 | COMP | 2020-07-28 | COMP | 2020-09-16 | COMP | Rule 15/16 | 65 | 67 | 4 | 25 | 0 | 35 | 192
18484 | 2019-12-16 | 2020-03-26 | 2020-05-15 | 2020-05-15 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-27 | COMP | 2020-08-10 | COMP | Rule 16 | 70 | 37 | 41 | 1 | 11 | 11 | 166
18487 | 2019-12-16 | 2020-03-26 | 2020-05-18 | 2020-05-18 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-20 | COMP | 2020-08-10 | COMP | Rule 15/16 | 70 | 38 | 40 | 1 | 6 | 16 | 166
18547 | 2019-12-16 | 2020-03-30 | 2020-10-05 | 2020-10-05 | COMP | 2020-11-04 | COMP | 2020-11-04 | COMP | 2021-02-04 | COMP | 2021-03-22 | COMP | Rule 16 | 72 | 134 | 23 | 1 | 61 | 32 | 318
18699 | 2019-12-16 | 2020-04-03 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-21 | COMP | 2020-07-22 | COMP | 2020-10-12 | COMP | 2020-11-10 | COMP | Rule 16 | 76 | 59 | 19 | 2 | 58 | 22 | 231
18814 | 2019-12-16 | 2020-04-08 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-11-03 | COMP | 2020-11-07 | COMP | Rule 16 | 79 | 57 | 17 | 1 | 76 | 4 | 229
18822 | 2019-12-16 | 2020-04-08 | 2020-09-09 | 2020-09-09 | COMP | 2020-09-29 | COMP | 2020-10-26 | COMP | 2021-01-12 | COMP | 2021-01-23 | COMP | Rule 15/16 | 79 | 109 | 15 | 20 | 52 | 8 | 278
18868 | 2019-12-16 | 2020-04-09 | 2020-08-31 | 2020-08-31 | COMP | 2020-10-09 | COMP | 2021-05-06 | COMP |  |  | 2021-06-24 | COMP | Rule 15/16 | 80 | 102 | 29 | 143 |  |  | 385
19090 | 2019-12-16 | 2020-04-21 | 2020-06-04 | 2021-09-09 | COMP | 2021-10-01 | COMP | 2021-10-04 | COMP | 2021-05-28 | COMP | 2021-11-04 | COMP | Rule 16 | 88 | 32 | 17 | 2 | 0 | 24 | 478
19136 | 2019-12-16 | 2020-04-21 | 2020-08-12 | 2020-08-12 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2021-10-29 | COMP | 2021-12-02 | COMP | Rule 16 | 88 | 81 | 30 | 1 | 278 | 22 | 495
19270 | 2019-12-16 | 2020-04-28 | 2020-07-29 | 2020-07-29 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP |  |  | 2021-06-22 | COMP | Rule 16 | 93 | 66 | 52 | 1 |  |  | 383
19558 | 2019-12-16 | 2020-05-12 | 2020-06-11 | 2020-06-11 | COMP | 2020-09-24 | COMP | 2020-09-10 | COMP | 2020-10-14 | COMP | 2020-11-25 | COMP | Rule 16 | 103 | 22 | 75 |  | 25 | 30 | 241
19606 | 2019-12-16 | 2020-05-14 | 2021-01-25 | 2021-01-25 | COMP | 2021-02-04 | COMP | 2021-03-09 | COMP | 2023-12-04 | INPR | 2021-06-02 | COMP | Rule 16 | 105 | 175 | 9 | 23 |  |  | 369
19655 | 2019-12-16 | 2020-05-16 | 2020-09-30 | 2020-09-30 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2021-09-20 | COMP | 2021-09-03 | COMP | Rule 16 | 106 | 96 | 57 | 1 | 188 |  | 435
19691 | 2019-12-16 | 2020-05-18 | 2020-06-04 | 2020-06-04 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2020-12-01 | COMP | 2020-12-16 | COMP | Rule 16 | 107 | 13 | 82 | 1 | 44 | 12 | 254
21641 | 2019-12-16 | 2020-08-18 | 2020-10-31 | 2020-10-31 | COMP | 2020-11-24 | COMP | 2020-12-03 | COMP | 2020-12-01 | COMP | 2020-12-23 | COMP | Rule 15/16 | 172 | 53 | 16 | 6 | 0 | 15 | 259
21642 | 2019-12-16 | 2020-08-18 | 2020-10-31 | 2020-10-31 | COMP | 2020-11-17 | COMP | 2020-11-20 | COMP | 2020-12-01 | COMP | 2020-12-14 | COMP | Rule 16 | 172 | 53 | 11 | 4 | 6 | 10 | 252
21743 | 2019-12-16 | 2020-08-24 | 2020-12-01 | 2020-12-01 | COMP | 2020-12-16 | COMP | 2020-12-16 | COMP | 2021-01-26 | COMP | 2021-02-27 | COMP | Rule 16 | 176 | 68 | 12 | 1 | 27 | 23 | 302
21826 | 2019-12-16 | 2020-08-30 | 2020-12-01 | 2020-12-01 | COMP | 2020-12-16 | COMP | 2020-12-16 | COMP | 2021-01-28 | COMP | 2021-02-28 | COMP | Rule 16 | 180 | 63 | 12 | 1 | 29 | 21 | 302
16260 | 2019-12-17 | 2019-12-18 | 2020-02-10 | 2020-02-10 | COMP | 2020-03-10 | COMP | 2020-06-29 | COMP | 2020-05-12 | COMP | 2020-07-22 | COMP | Rule 15/16 | 2 | 36 | 21 | 79 | 0 | 18 | 152
16354 | 2019-12-17 | 2019-12-23 | 2020-02-07 | 2020-02-07 | COMP | 2020-02-21 | COMP | 2020-02-25 | COMP | 2020-02-24 | COMP | 2020-06-16 | COMP | Rule 16 | 5 | 32 | 10 | 3 | 0 | 80 | 126
16456 | 2019-12-17 | 2020-01-02 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-19 | COMP | 2020-06-12 | COMP | 2021-01-23 | COMP | 2021-02-03 | COMP | Rule 16 | 11 | 76 | 22 | 18 | 154 | 8 | 285
16613 | 2019-12-17 | 2020-01-10 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-03 | COMP | 2020-06-19 | COMP | 2021-09-14 | COMP | 2021-10-13 | COMP | Rule 15/16 | 17 | 47 | 13 | 55 | 312 | 22 | 461
17130 | 2019-12-17 | 2020-01-31 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-10-02 | COMP | 2020-11-03 | COMP | Rule 16 | 31 | 38 | 10 | 1 | 127 | 23 | 225
17227 | 2019-12-17 | 2020-02-04 | 2021-10-26 | 2021-10-26 | COMP | 2021-11-01 | COMP | 2021-12-15 | COMP | 2021-11-15 | COMP | 2022-03-29 | COMP | Rule 15/16 | 33 | 438 | 5 | 30 | 0 | 73 | 575
17439 | 2019-12-17 | 2020-02-13 | 2020-04-10 | 2020-04-10 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-12 | COMP | 2020-07-27 | COMP | Rule 16 | 40 | 41 | 17 | 1 | 7 | 54 | 155
17499 | 2019-12-17 | 2020-02-18 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2020-07-27 | COMP | 2020-09-02 | COMP | Rule 16 | 42 | 94 | 3 | 1 | 19 | 28 | 182
17595 | 2019-12-17 | 2020-02-20 | 2020-05-11 | 2021-03-25 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2021-08-31 | COMP | 2021-09-08 | COMP | Rule 16 | 44 | 58 | 42 | 1 | 71 | 6 | 436
17637 | 2019-12-17 | 2020-02-24 | 2020-07-16 | 2020-07-16 | COMP | 2020-09-25 | COMP | 2020-09-28 | COMP | 2020-10-08 | COMP | 2020-11-03 | COMP | Rule 16 | 46 | 103 | 51 | 2 | 9 | 19 | 225
17698 | 2019-12-17 | 2020-02-25 | 2020-06-24 | 2020-06-24 | COMP | 2020-08-06 | COMP | 2020-08-06 | NOTN | 2020-08-06 | COMP | 2020-08-12 | COMP | Rule 16 | 47 | 86 | 32 |  |  |  | 167
17854 | 2019-12-17 | 2020-03-02 | 2020-03-26 | 2020-03-26 | COMP | 2020-03-27 | NOTN | 2020-03-27 | COMP | 2020-03-27 | COMP | 2020-04-22 | COMP | Other | 51 | 19 |  | 2 | 1 | 19 | 88
17871 | 2019-12-17 | 2020-03-02 | 2020-04-26 | 2020-04-26 | COMP | 2020-05-05 | COMP | 2020-06-02 | COMP | 2020-06-04 | COMP | 2020-07-01 | COMP | Rule 16 | 51 | 40 | 7 | 20 | 3 | 20 | 137
17872 | 2019-12-17 | 2020-03-02 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-12 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-12-28 | COMP | Rule 16 | 51 | 55 | 20 | 34 | 1 | 104 | 260
18258 | 2019-12-17 | 2020-03-17 | 2020-05-27 | 2021-03-12 | COMP | 2021-03-16 | COMP | 2021-03-19 | COMP | 2021-03-02 | COMP | 2021-04-02 | COMP | Rule 16 | 62 | 51 | 3 | 4 | 0 | 11 | 326
18365 | 2019-12-17 | 2020-03-20 | 2020-06-17 | 2021-04-16 | COMP | 2021-05-14 | COMP | 2021-05-18 | COMP | 2021-07-26 | COMP | 2021-08-20 | COMP | Rule 16 | 65 | 63 | 21 | 3 | 48 | 20 | 424
18464 | 2019-12-17 | 2020-03-25 | 2020-05-28 | 2020-05-28 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2022-07-16 | INPR | 2020-12-18 | COMP | Rule 16 | 68 | 46 | 63 | 1 |  |  | 255
18528 | 2019-12-17 | 2020-03-27 | 2020-08-14 | 2020-08-14 | COMP | 2020-09-02 | COMP | 2021-04-26 | COMP | 2021-06-23 | COMP | 2022-04-02 | COMP | Rule 15/16 | 70 | 100 | 14 | 161 | 42 | 196 | 578
19464 | 2019-12-17 | 2020-05-07 | 2020-10-07 | 2020-10-07 | COMP | 2020-10-21 | COMP | 2020-10-29 | COMP | 2021-03-31 | COMP | 2021-04-30 | COMP | Rule 16 | 99 | 108 | 11 | 7 | 103 | 23 | 346
19820 | 2019-12-17 | 2020-05-23 | 2020-08-13 | 2021-05-06 | COMP | 2021-07-06 | COMP | 2021-10-04 | COMP | 2021-12-13 | COMP | 2022-03-01 | COMP | Rule 16 | 110 | 58 | 42 | 64 | 48 | 55 | 555
20160 | 2019-12-17 | 2020-06-08 | 2020-06-22 | 2020-08-10 | COMP | 2020-08-18 | COMP | 2020-07-10 | COMP | 2020-10-12 | COMP | 2020-11-12 | COMP | Rule 16 | 120 | 11 | 7 |  | 66 | 23 | 231
21639 | 2019-12-17 | 2020-08-18 | 2020-11-10 | 2020-11-10 | COMP | 2020-11-23 | COMP | 2020-12-03 | COMP | 2020-12-01 | COMP | 2020-12-22 | COMP | Rule 16 | 171 | 60 | 9 | 7 | 0 | 14 | 257
4264 | 2019-12-18 | 2020-01-07 | 2020-03-27 | 2020-03-27 | COMP | 2020-08-10 | COMP | 2020-09-21 | COMP |  |  | 2021-09-23 | COMP | Rule 16 | 13 | 57 | 96 | 30 |  |  | 446
16271 | 2019-12-18 | 2019-12-18 | 2020-09-03 | 2020-09-03 | COMP | 2020-07-22 | NOTN | 2020-09-16 | COMP | 2021-09-28 | COMP | 2021-11-10 | COMP | Other | 1 | 182 |  | 9 | 260 | 32 | 480
16482 | 2019-12-18 | 2020-01-03 | 2020-09-04 | 2020-09-04 | COMP | 2020-10-02 | COMP | 2021-02-10 | COMP | 2021-02-02 | COMP | 2021-03-14 | COMP | Rule 15/16 | 11 | 173 | 20 | 88 | 0 | 22 | 310
16585 | 2019-12-18 | 2020-01-08 | 2020-02-14 | 2020-02-14 | COMP | 2020-02-20 | COMP | 2020-02-21 | COMP | 2020-02-21 | COMP | 2020-05-14 | COMP | Rule 16 | 14 | 27 | 4 | 2 | 1 | 60 | 103
17078 | 2019-12-18 | 2020-01-30 | 2020-07-10 | 2020-07-19 | COMP | 2021-06-21 | COMP | 2021-07-20 | COMP | 2021-06-25 | COMP | 2021-11-16 | COMP | Rule 15/16 | 29 | 115 | 232 | 21 | 0 | 84 | 483
17131 | 2019-12-18 | 2020-01-31 | 2020-04-29 | 2020-04-29 | COMP | 2020-07-01 | COMP | 2020-09-24 | COMP | 2020-11-04 | COMP | 2021-12-18 | COMP | Rule 16 | 30 | 63 | 45 | 61 | 30 | 280 | 504
17184 | 2019-12-18 | 2020-02-03 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-18 | COMP | 2020-03-18 | COMP | 2020-04-30 | COMP | 2020-08-06 | COMP | Rule 16 | 31 | 15 | 18 | 1 | 32 | 70 | 162
17281 | 2019-12-18 | 2020-02-07 | 2020-08-11 | 2020-08-30 | COMP | 2020-09-23 | COMP | 2021-02-24 | COMP |  | INPR | 2021-04-08 | COMP | Rule 15/16 | 35 | 131 | 17 | 104 |  |  | 329
17283 | 2019-12-18 | 2020-02-07 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-21 | COMP | 2020-06-18 | COMP | 2020-09-29 | COMP | 2020-10-05 | COMP | Rule 16 | 35 | 44 | 9 | 42 | 73 | 5 | 203
17418 | 2019-12-18 | 2020-02-12 | 2020-04-12 | 2020-04-12 | COMP | 2020-11-16 | COMP | 2020-11-16 | COMP | 2022-03-28 | COMP | 2022-04-08 | COMP | Rule 16 | 38 | 42 | 153 | 1 | 342 | 10 | 582
17548 | 2019-12-18 | 2020-02-20 | 2020-08-02 | 2020-08-02 | COMP | 2020-09-15 | COMP | 2022-02-04 | COMP | 2022-01-09 | COMP | 2022-04-04 | COMP | Rule 15/16 | 43 | 116 | 31 | 350 | 0 | 41 | 578
17634 | 2019-12-18 | 2020-02-24 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-12 | COMP |  | REQD |  | REQD | 2020-05-26 | COMP | Rule 16 | 45 | 49 | 9 |  |  |  | 110
17936 | 2019-12-18 | 2020-03-04 | 2020-04-26 | 2020-04-30 | COMP | 2020-05-01 | NOTN | 2020-05-01 | COMP | 2020-05-14 | COMP | 2020-07-09 | COMP | Other | 52 | 38 |  | 2 | 10 | 40 | 142
18454 | 2019-12-18 | 2020-03-24 | 2020-08-03 | 2021-05-27 | COMP | 2021-06-01 | COMP | 2021-06-01 | COMP | 2021-04-29 | COMP | 2021-06-24 | COMP | Rule 16 | 66 | 94 | 3 | 1 | 0 | 18 | 383
18845 | 2019-12-18 | 2020-04-09 | 2020-07-13 | 2020-07-13 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-11-05 | COMP | 2020-12-11 | COMP | Rule 16 | 78 | 67 | 46 | 1 | 38 | 24 | 249
19336 | 2019-12-18 | 2020-05-01 | 2020-09-16 | 2020-09-16 | COMP | 2020-10-02 | COMP | 2020-12-01 | COMP | 2021-02-09 | COMP | 2021-04-14 | COMP | Rule 15/16 | 94 | 97 | 13 | 40 | 48 | 46 | 333
19438 | 2019-12-18 | 2020-05-07 | 2020-10-31 | 2020-10-31 | COMP | 2021-07-19 | COMP | 2021-08-20 | COMP | 2022-08-31 | COMP | 2022-11-17 | COMP | Rule 15/16 | 98 | 125 | 177 | 25 | 260 | 55 | 736
19447 | 2019-12-18 | 2020-05-06 | 2020-09-23 | 2020-09-23 | COMP | 2021-03-11 | COMP | 2021-03-13 | COMP | 2023-07-29 | INPR | 2021-11-05 | COMP | Rule 16 | 97 | 99 | 115 | 2 |  |  | 477
20369 | 2019-12-18 | 2020-06-17 | 2020-07-16 | 2020-07-16 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-09-14 | COMP | 2020-09-24 | COMP | Rule 16 | 126 | 22 | 12 | 1 | 31 | 9 | 196
20398 | 2019-12-18 | 2020-06-18 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2020-09-08 | COMP | 2021-02-09 | COMP | Rule 16 | 127 | 19 | 27 | 1 | 14 | 105 | 288
20847 | 2019-12-18 | 2020-07-09 | 2020-10-26 | 2020-10-26 | COMP | 2021-03-23 | COMP | 2021-04-20 | COMP | 2021-04-20 | COMP | 2021-05-28 | COMP | Rule 16 | 142 | 77 | 100 | 21 | 1 | 29 | 365
21381 | 2019-12-18 | 2020-08-04 | 2020-10-20 | 2020-10-20 | COMP | 2021-07-19 | NOTN | 2022-07-07 | COMP |  |  | 2023-05-12 | COMP | Other | 160 | 55 |  | 430 |  |  | 856
4270 | 2019-12-19 | 2020-02-01 | 2020-03-28 | 2020-03-28 | COMP | 2020-04-28 | COMP | 2020-09-24 | COMP | 2020-09-17 | COMP | 2020-12-07 | COMP | Rule 15/16 | 29 | 39 | 22 | 106 | 0 | 50 | 244
4273 | 2019-12-19 | 2020-02-13 | [7 empty] | 2020-02-14 | COMP | 2020-05-20 | COMP | Other | 38 | [5 empty] | 106
16285 | 2019-12-19 | 2019-12-19 | 2023-02-14 | 2023-02-14 | COMP | 2023-02-16 | NOTN |  | REQD |  | REQD | 2023-06-23 | COMP | Other | 1 | 793 |  |  |  |  | 883
16372 | 2019-12-19 | 2019-12-23 | 2020-05-14 | 2020-05-14 | COMP | 2020-06-24 | COMP | 2020-09-16 | COMP | 2020-11-10 | COMP | 2021-01-07 | COMP | Rule 16 | 3 | 100 | 29 | 60 | 40 | 38 | 265
16387 | 2019-12-19 | 2019-12-23 | 2020-02-22 | 2020-02-22 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2020-07-18 | COMP | 2020-08-04 | COMP | Rule 16 | 3 | 41 | 14 | 1 | 91 | 12 | 159
16446 | 2019-12-19 | 2019-12-31 | 2020-04-03 | 2020-04-03 | COMP | 2020-06-13 | COMP | 2021-01-20 | COMP | 2020-12-03 | COMP | 2021-04-02 | COMP | Rule 16 | 8 | 66 | 50 | 151 | 0 | 52 | 324
16839 | 2019-12-19 | 2020-01-17 | 2020-02-10 | 2020-02-10 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-11-13 | COMP | 2020-11-22 | COMP | Rule 16 | 20 | 16 | 179 | 1 | 18 | 6 | 235
16909 | 2019-12-19 | 2020-01-23 | 2020-03-10 | 2020-11-20 | COMP | 2021-03-25 | COMP | 2021-04-15 | COMP | 2021-08-31 | COMP | 2021-06-02 | COMP | Rule 16 | 23 | 33 | 84 | 16 | 97 |  | 366
17050 | 2019-12-19 | 2020-01-30 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-08-21 | COMP | 2020-09-30 | COMP | Rule 16 | 28 | 85 | 10 | 1 | 52 | 28 | 199
17157 | 2019-12-19 | 2020-02-04 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-05-13 | COMP | 2020-06-05 | COMP | Rule 16 | 31 | 14 | 21 | 1 | 38 | 17 | 117
17265 | 2019-12-19 | 2020-02-06 | 2020-05-20 | 2020-09-11 | COMP | 2021-01-20 | COMP | 2021-05-28 | COMP | 2021-05-26 | COMP | 2021-07-01 | COMP | Rule 16 | 33 | 74 | 88 | 92 | 0 | 24 | 387
17300 | 2019-12-19 | 2020-02-07 | 2020-09-28 | 2020-09-28 | COMP | 2020-10-06 | COMP | 2020-10-21 | COMP | 2021-01-19 | COMP | 2021-01-27 | COMP | Rule 16 | 34 | 164 | 7 | 12 | 59 | 7 | 278
17442 | 2019-12-19 | 2020-02-13 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-15 | COMP | 2020-06-04 | COMP | 2020-06-16 | COMP | 2020-08-11 | COMP | Rule 16 | 38 | 62 | 5 | 14 | 9 | 41 | 164
17443 | 2019-12-19 | 2020-02-13 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2021-07-09 | COMP | 2021-07-30 | COMP | Rule 15/16 | 38 | 71 | 26 | 1 | 260 | 16 | 407
17578 | 2019-12-19 | 2020-02-20 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-25 | COMP | 2021-05-17 | COMP | 2021-06-18 | COMP | 2021-06-25 | COMP | Rule 16 | 42 | 72 | 19 | 225 | 24 | 6 | 383
17749 | 2019-12-19 | 2020-02-27 | 2020-05-15 | 2020-05-16 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-08-11 | COMP | 2020-08-13 | COMP | Rule 16 | 47 | 57 | 16 | 1 | 46 | 3 | 166
18116 | 2019-12-19 | 2020-03-11 | 2020-04-30 | 2020-04-30 | COMP | 2020-07-27 | COMP | 2020-12-01 | COMP | 2020-11-17 | COMP | 2021-01-06 | COMP | Rule 16 | 56 | 37 | 62 | 88 | 0 | 25 | 264
18349 | 2019-12-19 | 2020-03-20 | 2020-08-15 | 2020-08-15 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2022-01-30 | INPR | 2020-12-08 | COMP | Rule 16 | 63 | 105 | 18 | 1 |  |  | 245
18463 | 2019-12-19 | 2020-03-25 | 2020-04-30 | 2020-06-22 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-12-31 | COMP | 2023-06-03 | COMP | Rule 16 | 66 | 27 | 18 | 1 | 117 | 609 | 869
18689 | 2019-12-19 | 2020-04-03 | 2020-12-03 | 2021-03-22 | COMP | 2021-04-09 | COMP | 2021-04-12 | COMP | 2021-08-13 | COMP | 2021-09-20 | COMP | Rule 15/16 | 73 | 170 | 15 | 2 | 88 | 26 | 442
19260 | 2019-12-19 | 2020-04-29 | 2020-06-05 | 2020-07-02 | COMP | 2020-07-27 | COMP | 2020-06-11 | COMP | 2020-08-21 | COMP | 2020-10-04 | COMP | Rule 16 | 91 | 27 | 18 |  | 52 | 30 | 201
19407 | 2019-12-19 | 2020-05-06 | 2020-10-25 | 2020-10-25 | COMP | 2020-11-06 | COMP | 2021-03-30 | COMP |  | INPR | 2021-04-24 | COMP | Rule 15/16 | 96 | 121 | 10 | 96 |  |  | 339
19421 | 2019-12-19 | 2020-05-05 | 2020-10-27 | 2020-11-25 | COMP | 2021-03-16 | COMP | 2021-03-16 | COMP | 2021-03-04 | COMP | 2021-05-18 | COMP | Rule 16 | 95 | 124 | 74 | 1 | 0 | 46 | 356
19563 | 2019-12-19 | 2020-05-12 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-29 | COMP | 2020-07-16 | COMP | 2020-12-28 | COMP | 2021-02-02 | COMP | Rule 16 | 100 | 16 | 19 | 14 | 113 | 25 | 282
20960 | 2019-12-19 | 2020-07-14 | 2022-03-13 | 2022-12-02 | COMP | 2023-02-06 | COMP | 2023-12-11 | COMP | 2024-03-01 | COMP | 2023-12-02 | COMP | Rule 15/16 | 144 | 418 | 44 | 213 | 56 |  | 993
21286 | 2019-12-19 | 2020-07-30 | 2020-10-12 | 2020-10-12 | COMP | 2020-11-02 | COMP | 2020-12-08 | COMP | 2020-11-24 | COMP | 2021-01-15 | COMP | Other | 156 | 52 | 16 | 24 | 0 | 27 | 271
27418 | 2019-12-19 | 2021-04-27 | 2021-05-04 | 2021-05-04 | COMP | 2021-05-04 | NOTN | 2021-05-14 | COMP | 2021-05-14 | COMP | 2021-06-02 | COMP | Other | 341 | 6 |  | 9 | 1 | 13 | 366
16801 | 2019-12-20 | 2020-01-16 | 2020-02-20 | 2020-02-20 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP |  | INPR | 2020-04-29 | COMP | Rule 15/16 | 18 | 24 | 18 | 1 |  |  | 90
16862 | 2019-12-20 | 2020-01-21 | 2020-02-28 | 2020-06-26 | COMP | 2020-07-14 | COMP | 2020-07-24 | COMP | 2020-08-11 | COMP | 2020-08-27 | COMP | Rule 16 | 20 | 28 | 13 | 9 | 13 | 13 | 175
17041 | 2019-12-20 | 2020-01-28 | 2020-05-28 | 2020-05-28 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2023-04-12 | COMP | 2023-06-01 | COMP | Rule 16 | 25 | 86 | 74 | 1 | 650 | 36 | 867
17137 | 2019-12-20 | 2020-01-31 | 2020-03-10 | 2020-05-01 | COMP | 2020-05-21 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-06-01 | COMP | Rule 16 | 28 | 27 | 15 | 2 | 1 | 6 | 112
17179 | 2019-12-20 | 2020-02-04 | 2020-09-16 | 2021-09-26 | COMP | 2021-10-05 | COMP | 2021-04-20 | COMP | 2021-04-23 | COMP | 2021-05-05 | COMP | Rule 15/16 | 30 | 159 | 7 |  | 4 | 9 | 346
17670 | 2019-12-20 | 2020-02-24 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2021-10-23 | INPR | 2020-07-14 | COMP | Rule 15/16 | 43 | 78 | 6 | 1 |  |  | 143
17719 | 2019-12-20 | 2020-02-26 | 2020-08-27 | 2020-08-27 | COMP | 2020-09-28 | COMP | 2020-11-03 | COMP | 2020-09-29 | COMP | 2020-11-10 | COMP | Rule 15/16 | 45 | 131 | 22 | 27 | 0 | 6 | 227
17920 | 2019-12-20 | 2020-03-03 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-13 | COMP | 2020-08-07 | COMP | 2020-07-17 | COMP | 2020-09-04 | COMP | Rule 16 | 49 | 73 | 22 | 20 | 0 | 21 | 181
17941 | 2019-12-20 | 2020-03-05 | 2020-06-01 | 2020-06-29 | COMP | 2020-08-11 | COMP | 2020-09-03 | COMP | 2020-08-11 | COMP | 2020-11-23 | COMP | Rule 16 | 51 | 62 | 32 | 18 | 0 | 56 | 235
17942 | 2019-12-20 | 2020-03-05 | 2020-06-01 | 2020-07-02 | COMP | 2020-08-11 | COMP | 2020-11-20 | COMP | 2020-08-11 | COMP | 2021-01-07 | COMP | Rule 16 | 51 | 62 | 29 | 72 | 0 | 31 | 264
17946 | 2019-12-20 | 2020-03-05 | 2020-06-10 | 2020-06-10 | COMP | 2020-06-22 | COMP | 2020-08-05 | COMP | 2020-10-07 | COMP | 2020-10-20 | COMP | Rule 16 | 51 | 69 | 9 | 33 | 45 | 10 | 212
18168 | 2019-12-20 | 2020-03-13 | 2020-11-10 | 2021-04-01 | COMP | 2021-04-14 | COMP | 2021-04-21 | COMP | 2021-04-17 | COMP | 2021-07-03 | COMP | Rule 15/16 | 57 | 171 | 10 | 6 | 0 | 52 | 387
18259 | 2019-12-20 | 2020-03-17 | 2021-04-24 | 2021-04-24 | COMP | 2021-06-07 | COMP | 2021-11-10 | COMP | 2022-03-01 | COMP | 2022-04-01 | COMP | Rule 15/16 | 59 | 280 | 30 | 111 | 75 | 24 | 575
18535 | 2019-12-20 | 2020-03-27 | 2020-06-02 | 2022-08-02 | COMP | 2023-03-31 | COMP | 2023-07-01 | COMP | 2023-05-23 | COMP | 2023-08-24 | COMP | Rule 16 | 67 | 47 | 166 | 64 | 0 | 38 | 925
19200 | 2019-12-20 | 2020-04-23 | 2020-10-07 | 2020-10-07 | COMP | 2020-10-20 | COMP | 2020-12-03 | COMP | 2020-12-09 | COMP | 2020-12-14 | COMP | Rule 16 | 86 | 118 | 10 | 30 | 5 | 4 | 248
20315 | 2019-12-20 | 2020-06-15 | 2020-08-22 | 2020-08-22 | COMP | 2021-08-20 | COMP | 2022-08-04 | COMP | 2022-08-29 | COMP | 2022-09-30 | COMP | Rule 16 | 122 | 50 | 250 | 241 | 18 | 24 | 701
17666 | 2019-12-22 | 2020-02-25 | 2020-04-23 | 2020-04-23 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-12-14 | COMP | 2021-01-14 | COMP | Rule 16 | 43 | 43 | 79 | 1 | 85 | 22 | 268
16568 | 2019-12-23 | 2020-01-08 | 2020-03-28 | 2020-03-28 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-12 | COMP | 2020-06-16 | COMP | Rule 16 | 11 | 56 | 53 | 1 | 2 | 3 | 122
16657 | 2019-12-23 | 2020-01-10 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-12 | COMP | 2020-03-12 | COMP | 2020-03-13 | COMP | 2020-04-14 | COMP | Rule 16 | 13 | 36 | 8 | 1 | 2 | 23 | 78
16666 | 2019-12-23 | 2020-01-10 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-25 | COMP | 2020-03-31 | COMP | 2020-04-01 | COMP | 2020-04-23 | COMP | Rule 16 | 13 | 34 | 19 | 5 | 2 | 17 | 85
16949 | 2019-12-23 | 2020-01-24 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-24 | COMP | 2020-05-26 | COMP | 2020-10-08 | COMP | 2020-12-10 | COMP | Rule 16 | 22 | 54 | 12 | 22 | 97 | 43 | 245
16986 | 2019-12-23 | 2020-01-29 | 2020-03-20 | 2020-09-22 | COMP | 2020-10-15 | COMP | 2020-12-04 | COMP | 2020-05-18 | COMP | 2020-12-21 | COMP | Rule 16 | 25 | 37 | 18 | 34 | 0 | 12 | 252
17012 | 2019-12-23 | 2020-01-27 | 2020-11-23 | 2020-11-23 | COMP | 2021-02-18 | COMP | 2021-02-18 | COMP | 2021-02-18 | COMP | 2021-03-06 | COMP | Rule 16 | 23 | 212 | 58 | 1 | 1 | 12 | 302
17156 | 2019-12-23 | 2020-02-04 | 2020-03-20 | 2020-03-20 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-08 | COMP | 2020-08-13 | COMP | Rule 16 | 29 | 33 | 60 | 1 | 19 | 27 | 164
17289 | 2019-12-23 | 2020-02-07 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-22 | COMP | 2020-05-06 | COMP | 2021-01-25 | COMP | 2021-03-01 | COMP | Rule 16 | 32 | 33 | 21 | 11 | 181 | 25 | 298
17430 | 2019-12-23 | 2020-02-13 | 2020-03-26 | 2020-03-26 | COMP | 2020-05-01 | COMP | 2020-05-01 | COMP | 2020-07-16 | COMP | 2020-09-02 | COMP | Rule 16 | 36 | 30 | 27 | 1 | 54 | 35 | 178
17610 | 2019-12-23 | 2020-02-20 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-08-10 | COMP | Rule 16 | 40 | 72 | 3 | 1 | 1 | 49 | 161
17827 | 2019-12-23 | 2020-02-28 | 2020-06-09 | 2020-06-09 | COMP | 2020-09-21 | COMP | 2021-02-23 | COMP | 2021-02-23 | COMP | 2021-04-05 | COMP | Rule 16 | 46 | 72 | 74 | 105 | 1 | 30 | 323
17925 | 2019-12-23 | 2020-03-04 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-06-03 | COMP | 2020-12-15 | COMP | Rule 16 | 49 | 62 | 7 | 1 | 0 | 133 | 248
18031 | 2019-12-23 | 2020-03-09 | 2020-04-29 | 2020-04-29 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-12 | COMP | 2020-07-07 | COMP | Rule 15/16 | 52 | 38 | 25 | 1 | 8 | 18 | 137
18276 | 2019-12-23 | 2020-03-18 | 2020-07-06 | 2020-07-06 | COMP | 2020-07-23 | COMP | 2021-02-18 | COMP | 2021-04-20 | COMP | 2021-05-17 | COMP | Rule 16 | 59 | 78 | 14 | 143 | 44 | 20 | 353
18936 | 2019-12-23 | 2020-04-14 | 2020-06-08 | 2020-06-08 | COMP | 2020-09-21 | COMP | 2020-10-02 | COMP | 2020-10-06 | COMP | 2020-11-05 | COMP | Rule 16 | 78 | 39 | 75 | 10 | 3 | 23 | 223
21591 | 2019-12-23 | 2020-08-14 | 2020-12-28 | 2021-02-24 | COMP | 2021-11-02 | COMP | 2022-03-10 | COMP | 2022-10-14 | COMP | 2023-05-10 | COMP | Rule 16 | 165 | 92 | 177 | 88 | 153 | 142 | 851
16437 | 2019-12-24 | 2019-12-30 | 2020-06-08 | 2020-06-08 | COMP | 2020-07-01 | NOTN | 2020-08-31 | INPR | 2023-11-13 | CANC | 2020-08-19 | COMP | Other | 4 | 112 |  |  |  |  | 167
16538 | 2019-12-24 | 2020-01-07 | 2020-03-03 | 2020-03-03 | COMP | 2020-03-05 | COMP | 2020-03-05 | COMP | 2020-03-10 | COMP | 2020-05-04 | COMP | Rule 16 | 9 | 39 | 3 | 1 | 4 | 40 | 91
17159 | 2019-12-24 | 2020-02-04 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-19 | COMP | 2020-05-07 | COMP | 2020-06-02 | COMP | 2020-07-02 | COMP | Rule 16 | 28 | 26 | 7 | 36 | 18 | 23 | 133
17447 | 2019-12-24 | 2020-02-13 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-07 | COMP | 2020-07-08 | COMP | 2020-12-22 | COMP | 2021-02-22 | COMP | Rule 15/16 | 35 | 70 | 33 | 2 | 116 | 41 | 292
17709 | 2019-12-24 | 2020-02-24 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-09 | COMP | 2020-11-16 | COMP | 2020-07-03 | COMP | 2021-04-20 | COMP | Rule 16 | 41 | 89 | 9 | 91 | 0 | 106 | 333
18070 | 2019-12-24 | 2020-03-10 | 2020-09-08 | 2020-09-08 | COMP | 2021-04-02 | COMP | 2021-04-02 | COMP | 2021-04-05 | COMP | 2021-04-29 | COMP | Rule 16 | 52 | 129 | 142 | 1 | 2 | 19 | 340
18110 | 2019-12-24 | 2020-03-11 | 2020-07-14 | 2020-10-19 | COMP | 2020-12-16 | COMP | 2020-12-22 | COMP | 2020-12-16 | COMP | 2021-12-10 | COMP | Rule 16 | 53 | 89 | 40 | 5 | 0 | 244 | 495
18231 | 2019-12-24 | 2020-03-16 | 2020-05-23 | 2020-05-23 | COMP | 2021-04-02 | COMP | 2021-04-02 | COMP | 2021-04-05 | COMP | 2021-04-29 | COMP | Rule 16 | 56 | 50 | 216 | 1 | 2 | 19 | 340
19339 | 2019-12-24 | 2020-05-01 | 2020-07-07 | 2020-07-07 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2020-08-28 | COMP | 2020-10-08 | COMP | Rule 16 | 90 | 47 | 35 | 1 | 5 | 29 | 202
19415 | 2019-12-24 | 2020-05-05 | 2020-10-15 | 2020-10-15 | COMP | 2020-11-30 | COMP | 2022-03-08 | COMP | 2023-01-11 | COMP | 2023-02-11 | COMP | Rule 15/16 | 92 | 116 | 30 | 320 | 213 | 22 | 788
20108 | 2019-12-24 | 2020-06-05 | 2020-07-22 | 2020-07-22 | COMP | 2020-07-31 | COMP | 2020-09-22 | COMP | 2020-10-30 | COMP | 2020-12-01 | COMP | Rule 16 | 114 | 34 | 8 | 37 | 29 | 20 | 237
18090 | 2019-12-25 | 2020-03-10 | 2020-05-12 | 2020-05-12 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-10-16 | COMP | 2020-11-30 | COMP | Rule 15/16 | 51 | 46 | 48 | 1 | 65 | 29 | 235
18626 | 2019-12-25 | 2020-03-31 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-29 | COMP | 2020-10-06 | COMP | 2020-10-27 | COMP | 2020-10-29 | COMP | Rule 16 | 66 | 58 | 7 | 71 | 16 | 3 | 216
16597 | 2019-12-26 | 2020-01-09 | 2020-05-21 | 2020-07-01 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-12 | COMP | 2020-09-28 | COMP | Rule 16 | 10 | 94 | 18 | 1 | 14 | 33 | 193
16699 | 2019-12-26 | 2020-01-13 | 2020-03-21 | 2020-03-21 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-07-06 | COMP | 2020-07-15 | COMP | Rule 15/16 | 12 | 48 | 18 | 1 | 58 | 8 | 141
16709 | 2019-12-26 | 2020-01-14 | 2020-04-29 | 2020-04-29 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-12-15 | COMP | 2021-01-14 | COMP | Rule 16 | 13 | 75 | 69 | 1 | 92 | 21 | 266
16810 | 2019-12-26 | 2020-01-16 | 2020-02-28 | 2020-05-13 | COMP | 2020-02-24 | NOTN | 2020-05-19 | COMP | 2020-05-11 | COMP | 2020-07-21 | COMP | Other | 15 | 30 |  | 5 | 0 | 45 | 145
16951 | 2019-12-26 | 2020-01-24 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-16 | COMP | 2020-06-08 | COMP | 2021-10-23 | INPR | 2020-07-31 | COMP | Rule 16 | 20 | 90 | 12 |  |  |  | 153
17589 | 2019-12-26 | 2020-02-20 | 2020-06-01 | 2020-06-01 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-09-29 | COMP | 2020-10-31 | COMP | Rule 15/16 | 38 | 72 | 81 | 1 | 6 | 24 | 217
17745 | 2019-12-26 | 2020-02-25 | 2020-09-11 | 2020-09-11 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-11-09 | COMP | 2020-12-04 | COMP | Rule 16 | 41 | 142 | 6 | 1 | 37 | 17 | 239
17778 | 2019-12-26 | 2020-02-26 | 2020-04-26 | 2021-02-09 | COMP | 2021-05-21 | COMP | 2021-05-21 | COMP | 2022-02-27 | COMP | 2022-04-14 | COMP | Rule 16 | 42 | 43 | 73 | 1 | 193 | 34 | 581
17797 | 2019-12-26 | 2020-02-27 | 2020-03-18 | 2020-03-18 | COMP | 2020-03-26 | COMP | 2020-07-19 | NOTN | 2020-05-18 | COMP | 2020-07-25 | COMP | Rule 16 | 43 | 15 | 7 |  |  |  | 148
18916 | 2019-12-26 | 2020-04-12 | 2020-07-30 | 2020-11-04 | COMP | 2020-12-21 | COMP | 2021-01-27 | COMP | 2021-04-20 | COMP | 2021-05-07 | COMP | Rule 16 | 74 | 78 | 31 | 25 | 59 | 14 | 345
19931 | 2019-12-26 | 2020-05-28 | 2020-08-12 | 2020-08-12 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2021-04-06 | COMP | 2021-05-25 | COMP | Rule 16 | 107 | 55 | 58 | 1 | 105 | 36 | 357
16501 | 2019-12-27 | 2020-01-07 | 2020-03-02 | 2020-03-02 | COMP | 2020-03-17 | COMP | 2020-04-30 | COMP | 2020-05-04 | COMP | 2020-08-24 | COMP | Rule 16 | 7 | 38 | 12 | 33 | 3 | 80 | 168
17164 | 2019-12-27 | 2020-02-03 | 2020-04-14 | 2020-04-16 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-08 | COMP | 2020-06-22 | COMP | Rule 16 | 25 | 51 | 34 | 1 | 4 | 11 | 123
17295 | 2019-12-27 | 2020-02-08 | 2020-04-08 | 2020-04-08 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-05-27 | COMP | 2020-07-14 | COMP | Rule 16 | 29 | 42 | 52 | 1 | 0 | 18 | 139
17369 | 2019-12-27 | 2020-02-11 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-08-25 | COMP | 2020-09-14 | COMP | Rule 16 | 31 | 41 | 21 | 1 | 79 | 14 | 182
17461 | 2019-12-27 | 2020-02-14 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-25 | COMP | 2020-08-14 | COMP | 2020-07-06 | COMP | 2020-08-31 | COMP | Rule 16 | 34 | 84 | 10 | 37 | 0 | 12 | 173
18099 | 2019-12-27 | 2020-03-10 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-06-22 | COMP | 2020-07-30 | COMP | Rule 16 | 50 | 38 | 29 | 1 | 9 | 29 | 151
18134 | 2019-12-27 | 2020-03-12 | 2020-07-16 | 2020-09-22 | COMP | 2020-12-18 | COMP | 2021-03-16 | COMP | 2021-03-29 | COMP | 2021-04-24 | COMP | Rule 15/16 | 52 | 90 | 61 | 59 | 10 | 20 | 334
18532 | 2019-12-27 | 2020-03-27 | 2020-06-02 | 2020-06-08 | COMP | 2020-07-06 | COMP | 2021-02-22 | COMP | 2023-05-31 | COMP | 2023-08-11 | COMP | Rule 16 | 63 | 47 | 21 | 158 | 573 | 51 | 912
18549 | 2019-12-27 | 2020-03-28 | 2020-05-30 | 2020-05-30 | COMP | 2020-06-12 | COMP | 2020-07-24 | COMP | 2020-07-28 | COMP | 2020-09-01 | COMP | Rule 16 | 63 | 44 | 10 | 31 | 3 | 26 | 174
18816 | 2019-12-27 | 2020-04-08 | 2020-06-22 | 2020-06-22 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-07-06 | COMP | 2020-08-11 | COMP | Rule 16 | 71 | 53 | 6 | 1 | 6 | 27 | 159
16417 | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2019-12-30 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-08-18 | COMP | 2021-01-13 | COMP | Rule 16 | 0 | 1 | 154 | 1 | 10 | 101 | 263
18573 | 2019-12-28 | 2020-03-28 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-10-22 | COMP | 2020-11-30 | COMP | Rule 16 | 62 | 49 | 10 | 1 | 90 | 25 | 233
16509 | 2019-12-29 | 2020-01-06 | 2020-05-12 | 2020-05-12 | COMP | 2020-08-10 | COMP | 2021-03-04 | COMP | 2021-03-09 | COMP | 2021-03-16 | COMP | Rule 16 | 5 | 90 | 64 | 141 | 4 | 6 | 305
18872 | 2019-12-29 | 2020-04-09 | 2020-05-20 | 2020-05-20 | COMP | 2020-09-08 | COMP | 2021-02-16 | COMP | 2021-01-28 | COMP | 2021-03-27 | COMP | Rule 15/16 | 71 | 30 | 78 | 109 | 0 | 29 | 313
18888 | 2019-12-29 | 2020-04-10 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-07-29 | COMP | 2021-01-11 | COMP | Rule 15/16 | 72 | 23 | 31 | 1 | 26 | 113 | 261
19432 | 2019-12-29 | 2020-05-06 | 2020-09-21 | 2020-09-21 | COMP | 2020-10-30 | COMP | 2021-04-10 | COMP | 2021-04-20 | COMP | 2021-05-17 | COMP | Rule 16 | 90 | 97 | 30 | 109 | 7 | 20 | 349
16432 | 2019-12-30 | 2019-12-30 | 2020-05-27 | 2020-07-27 | COMP | 2020-06-01 | NOTN | 2021-04-26 | COMP | 2020-06-01 | COMP | 2021-05-11 | COMP | Other | 1 | 104 |  | 188 | 0 | 12 | 345
16434 | 2019-12-30 | 2019-12-30 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-09 | NOTN | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-11-16 | COMP | Other | 1 | 113 |  | 1 | 1 | 113 | 225
16491 | 2019-12-30 | 2020-01-03 | 2020-02-11 | 2020-02-11 | COMP | 2020-04-02 | COMP | 2020-09-25 | INPR | 2020-09-25 | COMP | 2020-09-28 | COMP | Rule 16 | 4 | 27 | 37 |  |  |  | 191
16677 | 2019-12-30 | 2020-01-11 | 2020-05-12 | 2020-05-12 | COMP | 2020-05-12 | NOTN | 2020-07-31 | COMP | 2020-05-12 | COMP | 2020-10-01 | COMP | Other | 9 | 85 |  | 58 | 0 | 44 | 194
16787 | 2019-12-30 | 2020-01-16 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-08 | COMP | 2020-06-01 | COMP | 2020-06-03 | COMP | 2020-06-19 | COMP | Rule 16 | 13 | 51 | 30 | 16 | 3 | 13 | 121
16903 | 2019-12-30 | 2020-01-23 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-04-21 | COMP | 2020-05-04 | COMP | Rule 16 | 17 | 24 | 14 | 1 | 27 | 10 | 88
16904 | 2019-12-30 | 2020-01-23 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-04-21 | COMP | 2020-05-04 | COMP | Rule 16 | 17 | 24 | 14 | 1 | 27 | 10 | 88
16905 | 2019-12-30 | 2020-01-23 | 2020-03-04 | 2020-03-04 | COMP | 2020-03-25 | COMP | 2020-03-26 | COMP | 2020-04-28 | COMP | 2020-05-05 | COMP | Rule 15/16 | 17 | 29 | 16 | 2 | 24 | 6 | 89
17032 | 2019-12-30 | 2020-01-28 | 2020-02-14 | 2020-02-14 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-12-29 | COMP | 2021-03-30 | COMP | Rule 16 | 20 | 14 | 122 | 1 | 100 | 63 | 315
17134 | 2019-12-30 | 2020-02-01 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-26 | COMP | 2020-08-11 | COMP | 2021-06-02 | COMP | 2021-07-16 | COMP | Rule 16 | 23 | 80 | 24 | 33 | 203 | 32 | 391
17158 | 2019-12-30 | 2020-02-04 | 2020-03-03 | 2020-03-03 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-10-13 | COMP | 2020-11-10 | COMP | Rule 16 | 25 | 20 | 111 | 1 | 49 | 21 | 222
17558 | 2019-12-30 | 2020-02-22 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-07-28 | COMP | 2020-08-27 | COMP | Rule 16 | 37 | 55 | 51 | 1 | 7 | 23 | 170
17609 | 2019-12-30 | 2020-02-21 | 2020-06-03 | 2020-06-03 | COMP | 2020-07-22 | COMP | 2020-08-05 | COMP | 2023-11-13 | INPR | 2021-04-13 | COMP | Rule 16 | 37 | 73 | 36 | 11 |  |  | 325
17795 | 2019-12-30 | 2020-02-28 | 2020-06-10 | 2020-06-10 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2021-10-29 | COMP | 2021-12-07 | COMP | Rule 16 | 42 | 73 | 66 | 1 | 287 | 25 | 489
18465 | 2019-12-30 | 2020-03-25 | 2020-07-03 | 2020-07-03 | COMP | 2020-07-07 | COMP | 2020-10-02 | COMP | 2021-02-01 | COMP | 2021-03-29 | COMP | Rule 16 | 60 | 72 | 3 | 63 | 81 | 40 | 314
18534 | 2019-12-30 | 2020-03-27 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-10-29 | COMP | 2020-11-20 | COMP | Rule 16 | 62 | 31 | 53 | 1 | 71 | 16 | 229
19323 | 2019-12-30 | 2020-04-30 | 2020-06-26 | 2020-06-29 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-10-08 | COMP | 2020-11-20 | COMP | Rule 16 | 86 | 41 | 45 | 1 | 29 | 31 | 229
16891 | 2019-12-31 | 2020-01-22 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-01 | COMP | 2020-05-01 | COMP | 2020-05-11 | COMP | 2020-05-18 | COMP | Rule 16 | 15 | 68 | 5 | 1 | 7 | 6 | 97
16958 | 2019-12-31 | 2020-01-25 | 2020-03-23 | 2020-03-23 | COMP | 2020-03-31 | NOTN | 2020-03-31 | COMP | 2020-04-28 | COMP | 2020-06-08 | COMP | Other | 17 | 40 |  | 7 | 21 | 29 | 111
17228 | 2019-12-31 | 2020-02-04 | 2020-08-08 | 2020-08-08 | COMP | 2020-08-17 | COMP | 2021-02-25 | COMP | 2021-04-30 | COMP | 2021-07-16 | COMP | Rule 16 | 24 | 132 | 6 | 131 | 47 | 54 | 390
17371 | 2019-12-31 | 2020-02-11 | 2020-05-30 | 2020-05-30 | COMP | 2020-11-23 | COMP | 2020-12-16 | COMP | 2021-01-04 | COMP | 2021-02-12 | COMP | Rule 16 | 29 | 77 | 124 | 16 | 12 | 29 | 283
17867 | 2019-12-31 | 2020-03-03 | 2020-05-20 | 2020-08-19 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2022-06-28 | COMP | 2022-07-28 | COMP | Rule 15/16 | 43 | 57 | 25 | 1 | 443 | 22 | 650
18846 | 2019-12-31 | 2020-04-09 | 2020-06-18 | 2020-06-18 | COMP | 2020-11-18 | COMP | 2021-01-25 | COMP | 2021-07-06 | COMP | 2021-07-27 | COMP | Rule 16 | 70 | 50 | 108 | 44 | 114 | 16 | 397
18857 | 2019-12-31 | 2020-04-09 | 2020-12-14 | 2020-12-14 | COMP | 2021-01-28 | COMP | 2021-01-29 | COMP | 2022-07-16 | INPR | 2021-06-14 | COMP | Rule 16 | 70 | 173 | 31 | 2 |  |  | 367
18994 | 2019-12-31 | 2020-04-16 | 2020-10-10 | 2020-10-10 | COMP | 2020-11-06 | COMP | 2020-12-21 | COMP | 2020-12-02 | COMP | 2021-03-22 | COMP | Rule 16 | 75 | 125 | 20 | 29 | 0 | 62 | 308
23364 | 2019-12-31 | 2020-11-03 | 2021-01-20 | 2021-01-20 | COMP | 2021-02-02 | COMP | 2021-02-02 | COMP | 2021-07-29 | COMP | 2021-08-12 | COMP | Rule 16 | 216 | 51 | 10 | 1 | 125 | 11 | 409
17261 | 2020-01-01 | 2020-02-06 | 2020-03-30 | 2020-03-30 | COMP | 2020-04-07 | COMP | 2020-04-11 | COMP | 2021-04-27 | COMP | 2021-05-26 | COMP | Rule 16 | 25 | 37 | 7 | 4 | 263 | 22 | 354
18378 | 2020-01-01 | 2020-03-22 | 2020-07-16 | 2020-09-15 | COMP | 2020-10-23 | COMP | 2021-09-23 | COMP | 2021-11-30 | COMP | 2022-01-13 | COMP | Rule 16 | 55 | 83 | 29 | 230 | 46 | 33 | 514
18645 | 2020-01-01 | 2020-03-31 | 2020-05-01 | 2020-05-01 | COMP | 2020-05-29 | COMP | 2020-06-01 | COMP | 2020-05-29 | COMP | 2020-06-23 | COMP | Rule 16 | 62 | 24 | 20 | 2 | 0 | 17 | 121
19252 | 2020-01-01 | 2020-04-28 | 2020-07-22 | 2020-07-22 | COMP | 2020-08-27 | COMP | 2020-08-27 | COMP | 2020-09-02 | COMP | 2020-11-02 | COMP | Rule 16 | 82 | 61 | 27 | 1 | 5 | 43 | 214
19706 | 2020-01-01 | 2020-05-18 | 2020-09-01 | 2020-09-01 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2020-10-27 | COMP | 2020-12-11 | COMP | Rule 16 | 96 | 76 | 19 | 1 | 22 | 31 | 240
16537 | 2020-01-02 | 2020-01-07 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-05 | COMP | 2020-04-24 | COMP | 2020-04-15 | COMP | 2020-06-06 | COMP | Rule 16 | 4 | 35 | 7 | 37 | 0 | 30 | 109
16637 | 2020-01-02 | 2020-01-09 | 2020-02-06 | 2020-02-06 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-06-02 | COMP | 2020-06-07 | COMP | Rule 16 | 6 | 20 | 44 | 1 | 39 | 4 | 109
16707 | 2020-01-02 | 2020-01-14 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-12 | COMP | 2020-07-20 | COMP | Rule 16 | 9 | 76 | 30 | 1 | 2 | 27 | 140
16711 | 2020-01-02 | 2020-01-14 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-26 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-08-09 | COMP | Rule 16 | 9 | 83 | 11 | 11 | 1 | 44 | 154
16906 | 2020-01-02 | 2020-01-23 | 2020-03-05 | 2020-03-05 | COMP | 2020-04-02 | COMP | 2020-04-03 | COMP | 2020-04-02 | COMP | 2020-04-22 | COMP | Rule 16 | 15 | 30 | 21 | 2 | 0 | 14 | 78
16976 | 2020-01-02 | 2020-01-27 | 2020-04-30 | 2020-04-30 | COMP | 2020-09-21 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2020-11-09 | COMP | Other | 17 | 68 | 101 | 6 | 1 | 31 | 219
17457 | 2020-01-02 | 2020-02-13 | 2020-04-25 | 2020-04-25 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-17 | COMP | 2020-07-07 | COMP | Rule 16 | 30 | 51 | 6 | 1 | 32 | 15 | 131
17471 | 2020-01-02 | 2020-02-15 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-07 | COMP | 2020-06-19 | COMP | 2020-07-14 | COMP | 2020-08-28 | COMP | Rule 16 | 31 | 49 | 10 | 31 | 18 | 34 | 169
17498 | 2020-01-02 | 2020-02-18 | 2020-04-13 | 2020-04-13 | COMP | 2020-06-11 | COMP | 2020-06-16 | COMP | 2022-08-17 | COMP | 2023-04-14 | COMP | Rule 16 | 32 | 40 | 43 | 4 | 548 | 165 | 827
17960 | 2020-01-02 | 2020-03-05 | 2020-05-22 | 2020-05-22 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-07-01 | COMP | 2020-08-04 | COMP | Rule 16 | 44 | 57 | 27 | 1 | 2 | 25 | 151
18032 | 2020-01-02 | 2020-03-09 | 2020-05-06 | 2020-06-10 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-07-10 | COMP | 2020-07-23 | COMP | Rule 15/16 | 46 | 43 | 9 | 1 | 15 | 10 | 143
18114 | 2020-01-02 | 2020-03-11 | 2020-06-18 | 2020-06-18 | COMP | 2020-06-23 | COMP | 2020-06-25 | COMP | 2021-06-29 | COMP | 2021-08-26 | COMP | Rule 16 | 48 | 71 | 4 | 3 | 255 | 42 | 418
18591 | 2020-01-02 | 2020-03-30 | 2020-12-16 | 2020-12-16 | COMP | 2021-03-05 | COMP | 2021-03-19 | COMP | 2021-03-08 | COMP | 2021-04-21 | COMP | Rule 15 | 61 | 183 | 54 | 11 | 0 | 24 | 329
18627 | 2020-01-02 | 2020-03-31 | 2020-06-12 | 2020-11-05 | COMP | 2023-12-03 | CANC | 2020-07-31 | COMP | 2020-09-28 | COMP | 2020-11-13 | COMP | Rule 16 | 62 | 53 |  |  | 41 | 34 | 222
18643 | 2020-01-02 | 2020-04-01 | 2020-05-21 | 2020-05-21 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-08-24 | COMP | 2020-09-29 | COMP | Rule 16 | 63 | 37 | 58 | 1 | 10 | 26 | 190
18760 | 2020-01-02 | 2020-04-06 | 2020-06-08 | 2020-06-08 | COMP | 2020-07-29 | COMP | 2020-08-07 | COMP | 2020-08-24 | COMP | 2020-09-24 | COMP | Rule 16 | 66 | 45 | 38 | 8 | 12 | 23 | 187
18794 | 2020-01-02 | 2020-04-07 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-18 | COMP | 2020-05-20 | COMP | 2020-11-16 | COMP | 2020-11-19 | COMP | Rule 16 | 67 | 15 | 16 | 3 | 126 | 4 | 226
18891 | 2020-01-02 | 2020-04-10 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-06-19 | COMP | 2020-07-29 | COMP | Rule 16 | 70 | 37 | 5 | 1 | 10 | 29 | 147
18952 | 2020-01-02 | 2020-04-14 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2021-05-13 | COMP | 2021-07-08 | COMP | Rule 16 | 72 | 80 | 14 | 1 | 182 | 39 | 383
18953 | 2020-01-02 | 2020-04-14 | 2020-07-28 | 2020-07-28 | COMP | 2020-09-09 | COMP | 2020-09-14 | COMP | 2021-06-10 | COMP | 2020-12-15 | COMP | Rule 16 | 72 | 75 | 31 | 4 | 186 |  | 242
19638 | 2020-01-02 | 2020-05-15 | 2020-11-21 | 2020-11-21 | COMP | 2021-04-23 | COMP | 2022-03-29 | COMP | 2024-02-03 | INPR | 2021-05-07 | COMP | Rule 16 | 95 | 133 | 104 | 235 |  |  | 341
19639 | 2020-01-02 | 2020-05-15 | 2020-12-11 | 2021-01-12 | COMP | 2021-02-17 | COMP | 2021-03-23 | COMP | 2021-04-13 | COMP | 2021-05-06 | COMP | Rule 16 | 95 | 146 | 25 | 25 | 16 | 18 | 340
19666 | 2020-01-02 | 2020-05-17 | 2020-08-12 | 2020-08-12 | COMP | 2020-08-18 | COMP | 2020-10-01 | COMP | 2020-09-14 | COMP | 2020-11-25 | COMP | Rule 16 | 95 | 62 | 5 | 32 | 0 | 39 | 230
20254 | 2020-01-02 | 2020-06-12 | 2020-09-21 | 2020-09-21 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2022-01-31 | INPR | 2020-11-16 | COMP | Rule 16 | 114 | 71 | 17 | 1 |  |  | 223
20402 | 2020-01-02 | 2020-06-19 | 2020-08-22 | 2020-08-22 | COMP | 2020-12-31 | COMP | 2020-12-31 | COMP | 2021-06-25 | COMP | 2021-07-09 | COMP | Rule 16 | 119 | 46 | 89 | 1 | 123 | 10 | 384
21312 | 2020-01-02 | 2020-07-31 | 2021-11-05 | 2021-11-05 | COMP | 2021-11-10 | COMP | 2023-01-28 | REQD | 2023-01-28 | REQD | 2021-12-05 | COMP | Rule 15/16 | 149 | 320 | 4 |  |  |  | 485
22322 | 2020-01-02 | 2020-09-20 | 2020-12-08 | 2022-12-20 | COMP | 2022-12-28 | COMP | 2023-05-05 | COMP | 2023-01-03 | COMP | 2023-08-21 | COMP | Rule 15/16 | 183 | 54 | 6 | 90 | 0 | 74 | 915
22532 | 2020-01-02 | 2020-09-28 | 2020-12-16 | 2020-12-16 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | 2021-03-17 | COMP | 2021-04-17 | COMP | Rule 16 | 189 | 55 | 17 | 1 | 46 | 23 | 326
26046 | 2020-01-02 | 2021-03-05 | 2021-05-27 | 2021-05-27 | COMP | 2022-05-11 | COMP | 2022-05-31 | COMP | 2022-06-13 | COMP | 2022-07-12 | COMP | Rule 16 | 296 | 60 | 242 | 14 | 10 | 20 | 637
16566 | 2020-01-03 | 2020-01-08 | 2020-03-12 | 2020-03-12 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-06-22 | COMP | 2020-07-27 | COMP | Rule 16 | 4 | 45 | 29 | 1 | 44 | 26 | 144
16804 | 2020-01-03 | 2020-01-17 | 2020-02-12 | 2020-03-18 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-04-02 | COMP | 2020-05-15 | COMP | Rule 16 | 11 | 18 | 4 | 1 | 9 | 32 | 94
17145 | 2020-01-03 | 2020-02-01 | 2020-05-21 | 2020-05-21 | COMP | 2020-05-21 | NOTN | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-07-14 | COMP | Other | 20 | 78 |  | 1 | 1 | 38 | 135
17146 | 2020-01-03 | 2020-01-31 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-07 | COMP | 2020-06-01 | COMP | 2020-07-17 | COMP | 2020-09-16 | COMP | Rule 16 | 20 | 45 | 3 | 39 | 35 | 43 | 180
17379 | 2020-01-03 | 2020-02-12 | 2020-03-20 | 2020-03-20 | COMP | 2020-06-10 | COMP | 2020-06-10 | INPR | 2022-01-30 | REQD | 2020-06-11 | COMP | Rule 16 | 28 | 27 | 58 |  |  |  | 112
17386 | 2020-01-03 | 2020-02-12 | 2020-03-03 | 2020-03-03 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | Rule 16 | 28 | 14 | 29 | 1 | 3 | 1 | 71
17397 | 2020-01-03 | 2020-02-12 | 2021-11-12 | 2023-11-09 | COMP | 2023-11-16 | COMP | 2023-11-17 | COMP | 2023-12-04 | COMP | 2023-12-19 | COMP | Rule 15/16 | 28 | 444 | 5 | 2 | 10 | 12 | 996
17725 | 2020-01-03 | 2020-02-25 | 2020-10-22 | 2020-10-22 | COMP | 2020-11-02 | COMP | 2020-11-09 | COMP | 2021-03-08 | COMP | 2021-07-20 | COMP | Rule 16 | 36 | 171 | 8 | 6 | 79 | 95 | 390
17851 | 2020-01-03 | 2020-03-02 | 2020-04-14 | 2020-04-14 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-12-02 | COMP | 2020-12-06 | COMP | Rule 16 | 40 | 32 | 134 | 1 | 29 | 3 | 234
17990 | 2020-01-03 | 2020-03-06 | 2020-06-20 | 2020-06-20 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2020-12-08 | COMP | 2021-01-15 | COMP | Rule 16 | 44 | 75 | 24 | 1 | 95 | 27 | 262
18352 | 2020-01-03 | 2020-03-20 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-29 | COMP | 2020-07-27 | COMP | Rule 16 | 54 | 45 | 16 | 1 | 12 | 21 | 144
18405 | 2020-01-03 | 2020-03-23 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-03 | COMP | 2021-02-16 | COMP | 2021-03-11 | COMP | 2021-04-26 | COMP | Rule 16 | 55 | 69 | 5 | 155 | 18 | 33 | 331
18473 | 2020-01-03 | 2020-03-26 | 2020-05-22 | 2020-05-22 | COMP | 2020-09-09 | COMP | 2021-02-17 | COMP | 2022-04-20 | COMP | 2022-05-17 | COMP | Other | 58 | 42 | 77 | 109 | 298 | 20 | 599
18587 | 2020-01-03 | 2020-03-30 | 2020-06-29 | 2021-03-16 | COMP | 2021-06-01 | COMP | 2021-07-15 | COMP |  | INPR | 2021-10-06 | COMP | Rule 15/16 | 60 | 65 | 55 | 32 |  |  | 445
18840 | 2020-01-03 | 2020-04-08 | 2020-05-23 | 2020-05-23 | COMP | 2021-01-11 | COMP | 2021-02-23 | COMP | 2020-12-12 | COMP | 2021-03-03 | COMP | Rule 16 | 67 | 33 | 159 | 30 | 0 | 7 | 293
18908 | 2020-01-03 | 2020-04-13 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-24 | COMP | 2020-09-30 | COMP | 2020-10-20 | COMP | 2020-11-06 | COMP | Rule 16 | 70 | 57 | 18 | 48 | 15 | 14 | 217
18982 | 2020-01-03 | 2020-04-15 | 2020-09-11 | 2020-09-11 | COMP | 2021-02-22 | COMP | 2021-04-20 | COMP |  | INPR | 2021-06-01 | COMP | Rule 15/16 | 72 | 106 | 110 | 42 |  |  | 356
19054 | 2020-01-03 | 2020-04-19 | 2020-05-27 | 2020-05-27 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2021-02-20 | COMP | 2021-03-25 | COMP | Rule 15/16 | 74 | 27 | 103 | 1 | 83 | 24 | 309
19121 | 2020-01-03 | 2020-04-22 | 2020-10-06 | 2020-10-06 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP | 2021-01-19 | COMP | 2021-02-04 | COMP | Rule 16 | 77 | 118 | 39 | 1 | 32 | 13 | 275
19427 | 2020-01-03 | 2020-05-06 | 2020-08-20 | 2020-08-20 | COMP | 2020-09-22 | COMP | 2020-10-09 | COMP | 2021-02-03 | COMP | 2021-02-24 | COMP | Rule 16 | 87 | 76 | 23 | 14 | 78 | 15 | 288
19433 | 2020-01-03 | 2020-05-06 | 2020-10-30 | 2020-10-30 | COMP | 2020-11-16 | COMP | 2021-01-29 | COMP | 2021-02-24 | COMP | 2021-03-05 | COMP | Rule 15/16 | 87 | 126 | 11 | 50 | 18 | 8 | 295
19441 | 2020-01-03 | 2020-05-06 | 2020-10-04 | 2020-10-04 | COMP | 2020-10-26 | COMP | 2020-10-27 | COMP | 2020-12-07 | COMP | 2021-01-21 | COMP | Rule 16 | 87 | 106 | 16 | 2 | 27 | 31 | 265
19551 | 2020-01-03 | 2020-05-12 | 2020-07-20 | 2020-07-20 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-10-14 | COMP | Rule 16 | 91 | 49 | 32 | 1 | 1 | 31 | 200
19641 | 2020-01-03 | 2020-05-15 | 2020-09-15 | 2020-09-15 | COMP | 2021-01-06 | COMP | 2021-01-06 | COMP | 2022-10-13 | COMP | 2022-07-19 | COMP | Rule 16 | 94 | 86 | 77 | 1 | 448 |  | 641
20445 | 2020-01-03 | 2020-06-20 | 2020-08-20 | 2020-08-20 | COMP | 2020-12-09 | COMP | 2021-04-02 | COMP | 2021-03-17 | COMP | 2021-05-25 | COMP | Rule 16 | 118 | 44 | 76 | 79 | 0 | 38 | 352
20870 | 2020-01-03 | 2020-07-10 | 2020-08-21 | 2020-08-21 | COMP | 2023-02-25 | INPR | 2023-02-25 | REQD | 2020-09-17 | COMP | 2020-12-23 | COMP | Rule 16 | 133 | 31 |  |  |  |  | 247
20880 | 2020-01-03 | 2020-07-10 | 2020-11-22 | 2020-11-22 | COMP | 2021-02-23 | COMP | 2021-02-23 | COMP | 2021-03-15 | COMP | 2021-04-20 | COMP | Rule 16 | 133 | 94 | 61 | 1 | 15 | 27 | 327
21640 | 2020-01-03 | 2020-08-18 | 2020-10-31 | 2020-10-31 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2020-12-01 | COMP | 2020-12-22 | COMP | Rule 15/16 | 160 | 53 | 11 | 1 | 9 | 16 | 246
21643 | 2020-01-03 | 2020-08-18 | 2020-11-13 | 2020-11-24 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP |  |  | 2020-12-21 | COMP | Rule 15/16 | 160 | 62 | 8 | 1 |  |  | 245
22574 | 2020-01-03 | 2020-09-30 | 2020-10-01 | 2020-10-01 | COMP | 2020-10-27 | NOTN | 2020-11-20 | COMP | 2020-11-30 | NOTN | 2021-02-17 | COMP | Other | 190 | 2 |  | 36 |  |  | 283
17174 | 2020-01-04 | 2020-02-03 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-15 | COMP | 2020-06-24 | COMP | 2023-04-30 | INPR | 2020-07-13 | COMP | Rule 16 | 20 | 88 | 7 | 8 |  |  | 133
17816 | 2020-01-04 | 2020-02-28 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-07-02 | COMP | Rule 15/16 | 38 | 22 | 36 | 1 | 1 | 33 | 126
18805 | 2020-01-04 | 2020-04-08 | 2020-09-18 | 2020-09-18 | COMP | 2020-09-22 | COMP | 2020-11-09 | COMP | 2021-08-10 | COMP | 2021-08-17 | COMP | Rule 16 | 66 | 116 | 3 | 35 | 188 | 6 | 409
19284 | 2020-01-04 | 2020-04-29 | 2020-06-09 | 2020-06-09 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2020-10-20 | COMP | 2020-11-10 | COMP | Rule 16 | 81 | 29 | 83 | 1 | 13 | 16 | 218
19797 | 2020-01-04 | 2020-05-21 | 2020-07-29 | 2020-07-29 | COMP | 2020-09-11 | COMP | 2021-01-22 | COMP | 2021-01-04 | COMP | 2021-02-16 | COMP | Rule 16 | 97 | 49 | 32 | 90 | 0 | 17 | 281
16865 | 2020-01-05 | 2020-01-21 | 2020-02-24 | 2020-02-24 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-04-29 | COMP | 2020-05-13 | COMP | Rule 16 | 11 | 24 | 26 | 1 | 23 | 11 | 91
16631 | 2020-01-06 | 2020-01-10 | 2020-01-30 | 2020-02-03 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-05-07 | COMP | 2020-05-20 | COMP | Rule 16 | 5 | 14 | 56 | 1 | 13 | 10 | 96
16691 | 2020-01-06 | 2020-01-13 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-07-20 | COMP | 2020-09-17 | COMP | Rule 16 | 6 | 54 | 30 | 1 | 51 | 43 | 180
17076 | 2020-01-06 | 2020-01-29 | 2020-03-05 | 2020-03-05 | COMP | 2021-04-24 | REQD | 2020-03-30 | COMP | 2021-04-24 | INPR | 2020-03-31 | COMP | Rule 16 | 17 | 26 |  | 18 |  |  | 60
17107 | 2020-01-06 | 2020-01-30 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-10-29 | COMP | 2021-01-13 | COMP | Rule 16 | 18 | 67 | 13 | 1 | 115 | 50 | 259
17122 | 2020-01-06 | 2020-01-31 | 2020-03-30 | 2020-03-30 | COMP | 2020-04-17 | COMP | 2020-07-07 | COMP | 2020-04-24 | COMP | 2020-07-22 | COMP | Rule 16 | 19 | 41 | 15 | 57 | 0 | 12 | 140
17198 | 2020-01-06 | 2020-02-04 | 2020-02-19 | 2020-02-19 | COMP | 2020-02-28 | COMP | 2020-02-28 | COMP | 2020-03-16 | COMP | 2020-04-08 | COMP | Rule 16 | 21 | 11 | 8 | 1 | 12 | 18 | 66
17215 | 2020-01-06 | 2020-02-04 | 2020-04-14 | 2020-04-28 | COMP | 2020-07-31 | COMP | 2020-08-10 | COMP | 2020-08-26 | COMP | 2020-11-24 | COMP | Rule 15/16 | 21 | 50 | 68 | 7 | 13 | 63 | 227
17485 | 2020-01-06 | 2020-02-18 | 2020-03-30 | 2020-03-30 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-22 | COMP | 2020-07-29 | COMP | Rule 16 | 30 | 30 | 54 | 1 | 7 | 28 | 145
17528 | 2020-01-06 | 2020-02-19 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-08 | COMP | 2020-06-11 | COMP | 2020-12-17 | COMP | 2021-01-14 | COMP | Rule 16 | 31 | 63 | 16 | 4 | 132 | 19 | 260
17549 | 2020-01-06 | 2020-02-20 | 2020-08-17 | 2020-08-17 | COMP | 2020-10-16 | COMP | 2021-01-19 | COMP | 2023-02-25 | INPR | 2021-09-09 | COMP | Rule 16 | 32 | 127 | 44 | 62 |  |  | 425
17997 | 2020-01-06 | 2020-03-06 | 2020-07-18 | 2020-07-18 | COMP | 2020-08-25 | COMP | 2020-08-27 | COMP | 2022-07-16 | INPR | 2020-11-09 | COMP | Rule 16 | 43 | 95 | 27 | 3 |  |  | 217
17999 | 2020-01-06 | 2020-03-06 | 2020-05-09 | 2020-05-09 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2020-11-04 | COMP | 2020-11-20 | COMP | Rule 16 | 43 | 46 | 121 | 1 | 6 | 12 | 225
18135 | 2020-01-06 | 2020-03-12 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | Rule 16 | 47 | 58 | 17 | 1 | 110 | 1 | 229
18634 | 2020-01-06 | 2020-04-01 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | Rule 16 | 61 | 28 | 62 | 1 | 6 | 1 | 154
18890 | 2020-01-06 | 2020-04-10 | 2020-09-30 | 2020-09-30 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2021-02-08 | COMP | 2021-04-12 | COMP | Rule 16 | 68 | 122 | 67 | 1 | 22 | 45 | 320
18910 | 2020-01-06 | 2020-04-13 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-18 | COMP | 2020-07-02 | COMP | 2020-08-19 | COMP | 2020-08-22 | COMP | Rule 16 | 69 | 20 | 72 |  | 35 | 3 | 162
18911 | 2020-01-06 | 2020-04-13 | 2020-05-15 | 2020-05-15 | COMP | 2020-08-18 | COMP | 2020-07-02 | COMP | 2020-08-19 | COMP | 2020-07-22 | COMP | Rule 16 | 69 | 25 | 67 |  | 35 |  | 140
19112 | 2020-01-06 | 2020-04-21 | 2020-10-15 | 2020-10-15 | COMP | 2021-02-04 | COMP | 2021-02-26 | COMP | 2021-04-15 | COMP | 2021-05-05 | COMP | Rule 15/16 | 75 | 126 | 75 | 16 | 35 | 15 | 337
20478 | 2020-01-06 | 2020-06-22 | 2020-08-03 | 2020-08-03 | COMP | 2020-08-21 | COMP | 2020-11-02 | COMP | 2020-11-30 | COMP | 2021-01-07 | COMP | Rule 16 | 118 | 31 | 15 | 51 | 18 | 27 | 255
21901 | 2020-01-06 | 2020-09-02 | 2020-11-07 | 2020-11-07 | COMP | 2020-11-13 | COMP | 2021-03-30 | COMP | 2021-04-05 | COMP | 2021-05-07 | COMP | Rule 16 | 170 | 47 | 4 | 92 | 5 | 25 | 339
21903 | 2020-01-06 | 2020-09-02 | 2020-11-01 | 2020-11-01 | COMP | 2020-11-04 | COMP | 2020-12-12 | COMP | 2020-12-28 | COMP | 2021-02-24 | COMP | Rule 16 | 170 | 42 | 3 | 25 | 10 | 40 | 287
16636 | 2020-01-07 | 2020-01-09 | 2020-02-05 | 2020-02-05 | COMP | 2020-02-25 | COMP | 2020-03-17 | INPR | 2020-03-05 | COMP | 2020-03-23 | COMP | Rule 15/16 | 3 | 19 | 14 |  |  |  | 53
16970 | 2020-01-07 | 2020-01-27 | 2020-03-18 | 2020-03-24 | COMP | 2020-03-30 | COMP | 2020-05-05 | COMP | 2020-03-30 | COMP | 2020-05-20 | COMP | Rule 16 | 14 | 37 | 5 | 27 | 0 | 12 | 95
16972 | 2020-01-07 | 2020-01-27 | 2020-02-25 | 2020-02-25 | COMP | 2020-04-03 | COMP | 2020-04-03 | NOTN | 2020-04-27 | COMP | 2020-05-06 | COMP | Rule 16 | 14 | 21 | 29 |  |  |  | 85
17006 | 2020-01-07 | 2020-01-27 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-05 | COMP | 2020-07-08 | COMP | 2020-06-05 | COMP | 2020-09-20 | COMP | Rule 16 | 14 | 90 | 4 | 24 | 0 | 52 | 180
17021 | 2020-01-07 | 2020-01-28 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-22 | COMP | 2020-04-23 | COMP | 2020-04-24 | COMP | 2020-06-17 | COMP | Rule 16 | 15 | 53 | 9 | 2 | 2 | 38 | 114
17058 | 2020-01-07 | 2020-01-29 | 2020-04-26 | 2020-04-26 | COMP | 2020-06-11 | COMP | 2020-06-27 | COMP | 2020-06-12 | COMP | 2020-07-07 | COMP | Other | 16 | 62 | 33 | 12 | 0 | 7 | 128
17132 | 2020-01-07 | 2020-01-31 | 2020-03-25 | 2020-03-25 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-11-02 | COMP | 2020-10-30 | COMP | Rule 16 | 18 | 38 | 87 | 1 | 71 |  | 210
17249 | 2020-01-07 | 2020-02-06 | 2020-05-07 | 2020-05-07 | COMP | 2020-07-08 | COMP | 2020-08-12 | COMP | 2023-12-03 | INPR | 2021-05-26 | COMP | Other | 22 | 65 | 44 | 26 |  |  | 351
17270 | 2020-01-07 | 2020-02-06 | 2020-04-11 | 2020-04-13 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-05-18 | COMP | 2020-07-15 | COMP | Rule 16 | 22 | 46 | 23 | 1 | 4 | 42 | 134
17278 | 2020-01-07 | 2020-02-06 | 2020-07-21 | 2020-07-21 | COMP | 2020-10-16 | COMP | 2020-11-18 | COMP | 2020-12-01 | COMP | 2021-02-02 | COMP | Rule 15/16 | 22 | 117 | 63 | 23 | 8 | 43 | 271
17383 | 2020-01-07 | 2020-02-12 | 2020-03-08 | 2020-03-08 | COMP | 2020-04-02 | COMP | 2020-04-02 | COMP | 2021-10-23 | INPR | 2020-05-12 | COMP | Rule 16 | 26 | 17 | 19 | 1 |  |  | 89
17656 | 2020-01-07 | 2020-02-24 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-05-05 | COMP | 2020-05-27 | COMP | Rule 16 | 33 | 29 | 19 | 1 | 6 | 16 | 99
17860 | 2020-01-07 | 2020-03-02 | 2020-05-28 | 2020-05-28 | COMP | 2020-06-30 | COMP | 2021-01-23 | COMP |  | INPR | 2021-03-05 | COMP | Rule 15/16 | 38 | 63 | 24 | 142 |  |  | 293
17944 | 2020-01-07 | 2020-03-05 | 2020-03-27 | 2020-03-27 | COMP | 2020-09-01 | COMP | 2020-09-14 | NOTN | 2020-10-14 | COMP | 2020-11-20 | COMP | Rule 16 | 41 | 17 | 112 |  |  |  | 224
17973 | 2020-01-07 | 2020-03-06 | 2020-05-20 | 2021-12-08 | COMP | 2022-01-11 | NOTN | 2021-02-22 | COMP | 2023-04-30 | INPR | 2022-02-05 | COMP | Other | 42 | 54 |  |  |  |  | 526
18002 | 2020-01-07 | 2020-03-06 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-09 | COMP | 2020-08-28 | COMP | 2022-02-26 | INPR | 2020-11-05 | COMP | Rule 16 | 42 | 81 | 9 | 37 |  |  | 214
18320 | 2020-01-07 | 2020-03-19 | 2020-04-13 | 2020-04-13 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-09-16 | COMP | 2020-11-04 | COMP | Rule 16 | 51 | 18 | 7 | 1 | 105 | 36 | 213
18785 | 2020-01-07 | 2020-04-06 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-13 | COMP | 2020-08-04 | COMP | 2020-10-05 | COMP | 2020-12-08 | COMP | Rule 15/16 | 63 | 48 | 23 | 17 | 44 | 44 | 234
19108 | 2020-01-07 | 2020-04-21 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-11 | COMP | 2020-09-23 | COMP | 2020-10-28 | COMP | 2020-12-15 | COMP | Rule 15/16 | 74 | 59 | 22 | 31 | 26 | 32 | 239
19178 | 2020-01-07 | 2020-04-23 | 2020-05-30 | 2020-05-30 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-03 | COMP | 2020-08-10 | COMP | Rule 16 | 76 | 26 | 45 | 1 | 2 | 6 | 152
19216 | 2020-01-07 | 2020-04-24 | 2020-06-17 | 2020-06-17 | COMP | 2020-09-09 | COMP | 2020-10-12 | COMP | 2020-08-13 | COMP | 2020-11-13 | COMP | Rule 15/16 | 77 | 38 | 60 | 24 | 0 | 24 | 219
19324 | 2020-01-07 | 2020-04-30 | 2020-06-08 | 2020-06-08 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-09-01 | COMP | 2020-10-22 | COMP | Rule 16 | 81 | 27 | 41 | 1 | 22 | 37 | 204
19403 | 2020-01-07 | 2020-05-05 | 2020-06-16 | 2020-06-16 | COMP | 2020-10-07 | COMP | 2020-11-16 | COMP | 2020-11-05 | COMP | 2020-12-17 | COMP | Other | 84 | 30 | 81 | 28 | 0 | 22 | 241
19461 | 2020-01-07 | 2020-05-07 | 2020-08-25 | 2021-03-09 | COMP | 2021-04-26 | COMP | 2021-04-26 | COMP | 2021-04-26 | COMP | 2021-05-26 | COMP | Rule 15/16 | 86 | 78 | 35 | 1 | 1 | 23 | 351
19462 | 2020-01-07 | 2020-05-07 | 2020-08-25 | 2021-04-28 | COMP | 2021-06-07 | COMP | 2021-06-09 | COMP | 2021-06-08 | COMP | 2021-07-16 | COMP | Rule 16 | 86 | 78 | 28 | 3 | 0 | 27 | 386
21096 | 2020-01-07 | 2020-07-22 | 2020-10-13 | 2021-08-05 | COMP | 2021-09-09 | COMP | 2021-10-04 | COMP | 2022-08-12 | COMP | 2022-10-14 | COMP | Rule 15/16 | 139 | 59 | 25 | 18 | 217 | 45 | 701
21533 | 2020-01-07 | 2020-08-11 | 2021-01-28 | 2021-05-27 | COMP | 2021-07-21 | COMP | 2021-09-01 | COMP | 2022-03-04 | COMP | 2022-04-06 | COMP | Rule 15/16 | 153 | 116 | 38 | 31 | 127 | 24 | 568
4266 | 2020-01-08 | 2020-01-16 | [7 empty] | 2020-01-17 | COMP | 2020-03-03 | COMP | Other | 7 | [5 empty] | 38
4271 | 2020-01-08 | 2020-02-05 | [7 empty] | 2020-02-05 | COMP | 2020-06-09 | COMP | Other | 20 | [5 empty] | 107
16840 | 2020-01-08 | 2020-01-18 | 2020-05-14 | 2020-05-14 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2022-01-30 | INPR | 2020-08-11 | COMP | Rule 16 | 8 | 82 | 4 | 1 |  |  | 152
16999 | 2020-01-08 | 2020-01-27 | 2020-04-01 | 2020-04-01 | COMP | 2020-05-27 | COMP | 2020-06-16 | COMP | 2020-05-28 | COMP | 2020-06-24 | COMP | Rule 16 | 13 | 47 | 40 | 15 | 0 | 7 | 118
17083 | 2020-01-08 | 2020-01-30 | 2020-03-08 | 2020-03-08 | COMP | 2020-05-08 | NOTN | 2020-05-08 | COMP | 2022-01-30 | INPR | 2020-12-21 | COMP | Rule 16 | 16 | 26 |  | 45 |  |  | 242
17092 | 2020-01-08 | 2020-01-30 | 2020-03-05 | 2020-03-05 | COMP | 2022-04-11 | COMP | 2022-04-11 | COMP | 2023-05-04 | COMP | 2023-05-09 | COMP | Other | 16 | 25 | 531 | 1 | 268 | 4 | 840
17096 | 2020-01-08 | 2020-02-01 | 2020-06-19 | 2020-11-04 | COMP | 2021-02-25 | COMP | 2021-02-25 | COMP | 2020-10-23 | COMP | 2021-04-19 | COMP | Rule 16 | 17 | 98 | 75 | 1 | 0 | 38 | 323
17185 | 2020-01-08 | 2020-02-03 | 2020-04-02 | 2020-04-02 | COMP | 2020-05-05 | COMP | 2020-06-04 | COMP | 2020-07-07 | COMP | 2020-07-22 | COMP | Rule 16 | 18 | 43 | 24 | 22 | 24 | 12 | 138
17279 | 2020-01-08 | 2020-02-07 | 2020-04-18 | 2020-04-18 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-09-22 | COMP | 2020-10-12 | COMP | Rule 16 | 22 | 50 | 36 | 1 | 75 | 15 | 195
17372 | 2020-01-08 | 2020-02-12 | 2020-04-05 | 2020-04-05 | COMP | 2020-09-17 | COMP | 2020-09-21 | COMP | 2020-11-10 | COMP | 2021-01-13 | COMP | Rule 16 | 25 | 37 | 117 | 3 | 37 | 42 | 257
17600 | 2020-01-08 | 2020-02-21 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-18 | COMP | 2020-06-01 | COMP | 2020-06-30 | COMP | 2020-09-14 | COMP | Rule 16 | 31 | 56 | 7 | 10 | 22 | 54 | 175
17810 | 2020-01-08 | 2020-02-27 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-13 | COMP | 2020-10-02 | COMP | 2020-12-08 | COMP | 2021-01-18 | COMP | Rule 16 | 35 | 81 | 17 | 59 | 45 | 27 | 259
17873 | 2020-01-08 | 2020-03-02 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-09-02 | COMP | 2020-10-01 | COMP | Rule 16 | 37 | 46 | 36 | 1 | 52 | 21 | 188
18102 | 2020-01-08 | 2020-03-10 | 2020-06-17 | 2020-06-17 | COMP | 2020-08-07 | COMP | 2020-08-25 | COMP | 2020-10-09 | COMP | 2020-12-14 | COMP | Rule 15/16 | 43 | 71 | 38 | 13 | 33 | 44 | 237
18198 | 2020-01-08 | 2020-03-15 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2020-09-08 | COMP | 2020-10-02 | COMP | Rule 16 | 46 | 60 | 6 | 1 | 61 | 19 | 189
18226 | 2020-01-08 | 2020-03-17 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-06-01 | COMP | 2020-07-09 | COMP | Rule 16 | 48 | 42 | 6 | 1 | 8 | 29 | 129
18665 | 2020-01-08 | 2020-04-01 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-06-16 | COMP | Rule 16 | 59 | 37 | 8 | 1 | 1 | 11 | 112
18694 | 2020-01-08 | 2020-04-03 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-07 | COMP | 2020-08-29 | COMP | 2021-05-13 | COMP | 2021-06-18 | COMP | Rule 16 | 61 | 35 | 33 | 39 | 176 | 26 | 366
18851 | 2020-01-08 | 2020-04-10 | 2020-10-30 | 2020-10-30 | COMP | 2021-01-12 | COMP | 2021-02-22 | COMP | 2021-05-17 | COMP | 2021-06-08 | COMP | Rule 16 | 66 | 144 | 48 | 28 | 61 | 16 | 358
18898 | 2020-01-08 | 2020-04-10 | 2021-01-12 | 2021-10-13 | COMP | 2021-11-01 | COMP | 2022-04-13 | COMP | 2022-02-09 | COMP | 2022-06-24 | COMP | Rule 15/16 | 66 | 191 | 14 | 113 | 0 | 51 | 622
19027 | 2020-01-08 | 2020-04-17 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-23 | COMP | 2020-08-05 | COMP | 2020-07-22 | COMP | 2020-09-17 | COMP | Rule 16 | 71 | 40 | 8 | 32 | 0 | 31 | 178
19088 | 2020-01-08 | 2020-04-20 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-17 | COMP | 2020-08-25 | COMP | 2020-08-24 | COMP | 2020-09-17 | COMP | Rule 16 | 72 | 79 | 7 | 7 | 0 | 17 | 178
19191 | 2020-01-08 | 2020-04-24 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-21 | COMP | 2020-07-31 | COMP | 2020-07-29 | COMP | 2020-08-29 | COMP | Rule 16 | 76 | 39 | 24 | 9 | 0 | 21 | 165
19377 | 2020-01-08 | 2020-05-04 | 2020-07-10 | 2021-02-08 | COMP | 2021-04-05 | COMP | 2021-04-05 | COMP | 2021-06-02 | COMP | 2021-06-29 | COMP | Rule 16 | 82 | 49 | 40 | 1 | 42 | 20 | 373
19444 | 2020-01-08 | 2020-05-06 | 2020-07-22 | 2020-07-22 | COMP | 2020-10-26 | COMP | 2020-11-06 | COMP | 2020-12-07 | COMP | 2020-12-18 | COMP | Rule 16 | 84 | 55 | 68 | 10 | 19 | 10 | 241
19483 | 2020-01-08 | 2020-05-09 | 2020-06-12 | 2020-06-12 | COMP | 2020-09-02 | COMP | 2021-02-03 | COMP | 2021-09-16 | COMP | 2021-10-18 | COMP | Rule 16 | 86 | 24 | 59 | 104 | 158 | 23 | 450
19533 | 2020-01-08 | 2020-05-11 | 2020-08-19 | 2020-08-31 | COMP | 2020-10-12 | COMP | 2020-11-12 | COMP |  | INPR | 2022-04-02 | COMP | Rule 15/16 | 87 | 72 | 30 | 23 |  |  | 564
19615 | 2020-01-08 | 2020-05-15 | 2020-08-05 | 2020-08-05 | COMP | 2020-09-02 | COMP | 2020-12-29 | COMP | 2021-01-06 | COMP | 2021-02-24 | COMP | Rule 16 | 91 | 58 | 21 | 80 | 6 | 34 | 285
19633 | 2020-01-08 | 2020-05-15 | 2020-08-13 | 2020-08-13 | COMP | 2020-11-03 | COMP | 2020-12-10 | COMP |  |  | 2021-01-25 | COMP | Rule 16 | 91 | 64 | 58 | 25 |  |  | 264
19941 | 2020-01-08 | 2020-05-29 | 2020-09-21 | 2020-09-21 | COMP | 2020-10-12 | COMP | 2021-06-10 | COMP | 2021-07-27 | COMP | 2021-08-04 | COMP | Rule 16 | 100 | 81 | 16 | 166 | 33 | 7 | 398
21131 | 2020-01-08 | 2020-07-22 | 2020-11-07 | 2020-11-07 | COMP | 2021-01-13 | COMP | 2021-01-13 | COMP | 2021-05-25 | COMP | 2021-06-04 | COMP | Rule 16 | 138 | 77 | 43 | 1 | 93 | 8 | 356
21229 | 2020-01-08 | 2020-07-29 | 2020-09-03 | 2020-09-03 | COMP | 2021-04-06 | COMP | 2021-04-06 | COMP | 2021-11-30 | COMP | 2021-12-23 | COMP | Rule 16 | 143 | 27 | 146 | 1 | 165 | 18 | 495
22004 | 2020-01-08 | 2020-09-08 | 2021-01-12 | 2021-04-07 | COMP | 2022-02-16 | COMP | 2022-03-16 | COMP | 2022-04-15 | COMP | 2022-05-27 | COMP | Rule 16 | 171 | 86 | 219 | 20 | 23 | 31 | 604
22005 | 2020-01-08 | 2020-09-08 | 2021-01-12 | 2021-04-07 | COMP | 2022-02-17 | COMP | 2022-02-17 | COMP | 2022-04-15 | COMP | 2022-05-27 | COMP | Rule 16 | 171 | 86 | 220 | 1 | 41 | 31 | 604
23387 | 2020-01-08 | 2020-11-04 | 2021-04-24 | 2021-04-24 | COMP | 2021-05-14 | COMP | 2021-06-22 | COMP | 2021-07-08 | COMP | 2021-10-06 | COMP | Rule 16 | 212 | 116 | 15 | 27 | 12 | 64 | 442
16947 | 2020-01-09 | 2020-01-24 | 2020-03-01 | 2020-03-01 | COMP | 2020-03-27 | COMP | 2020-03-30 | COMP | 2020-03-30 | COMP | 2020-06-18 | COMP | Rule 16 | 11 | 25 | 20 | 2 | 1 | 58 | 113
16981 | 2020-01-09 | 2020-01-28 | 2020-02-27 | 2020-02-27 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-06-15 | COMP | Rule 16 | 13 | 22 | 46 | 1 | 1 | 32 | 110
17138 | 2020-01-09 | 2020-01-31 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-27 | COMP | 2020-07-09 | COMP | 2023-06-06 | COMP | 2023-07-21 | COMP | Rule 16 | 16 | 75 | 8 | 32 | 731 | 32 | 889
17180 | 2020-01-09 | 2020-02-04 | 2020-04-02 | 2020-04-02 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2021-01-11 | COMP | 2021-01-14 | COMP | Rule 16 | 18 | 42 | 182 | 1 | 15 | 4 | 257
17189 | 2020-01-09 | 2020-02-04 | 2020-05-01 | 2020-05-01 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-05-26 | COMP | 2020-06-15 | COMP | Rule 16 | 18 | 63 | 16 | 1 | 2 | 15 | 110
17192 | 2020-01-09 | 2020-02-04 | 2020-10-12 | 2020-10-12 | COMP | 2020-11-10 | COMP | 2020-11-10 | COMP | 2021-01-07 | COMP | 2021-01-14 | COMP | Rule 15/16 | 18 | 177 | 22 | 1 | 38 | 6 | 257
17275 | 2020-01-09 | 2020-02-06 | 2020-10-22 | 2020-10-22 | COMP | 2020-11-20 | COMP | 2020-11-20 | COMP | 2021-11-18 | COMP | 2022-03-26 | COMP | Rule 15/16 | 20 | 183 | 21 | 1 | 250 | 88 | 558
17291 | 2020-01-09 | 2020-02-07 | 2020-04-20 | 2022-04-15 | COMP | 2022-05-04 | COMP | 2022-05-11 | COMP | 2022-05-04 | COMP | 2022-08-04 | COMP | Rule 15/16 | 21 | 51 | 14 | 6 | 0 | 59 | 649
17317 | 2020-01-09 | 2020-02-10 | 2020-03-27 | 2020-03-27 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | Rule 16 | 22 | 34 | 47 | 1 | 99 | 1 | 199
17343 | 2020-01-09 | 2020-02-11 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-05-26 | COMP | 2020-06-30 | COMP | Rule 16 | 23 | 44 | 27 | 1 | 5 | 26 | 121
17370 | 2020-01-09 | 2020-02-11 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-05-26 | COMP | 2020-07-22 | COMP | Rule 16 | 23 | 32 | 12 | 1 | 32 | 42 | 137
17387 | 2020-01-09 | 2020-02-12 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-04-27 | COMP | 2020-05-01 | COMP | Rule 16 | 24 | 36 | 11 | 1 | 8 | 5 | 80
17388 | 2020-01-09 | 2020-02-12 | 2020-04-02 | 2020-04-02 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-04-27 | COMP | 2020-05-01 | COMP | Rule 16 | 24 | 36 | 13 | 1 | 6 | 5 | 80
17421 | 2020-01-09 | 2020-02-12 | 2020-04-15 | 2020-04-15 | COMP | 2020-04-29 | COMP | 2020-05-11 | COMP | 2020-06-15 | COMP | 2020-07-24 | COMP | Rule 16 | 24 | 45 | 11 | 9 | 25 | 30 | 139
17446 | 2020-01-09 | 2020-02-13 | 2020-04-21 | 2020-04-21 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-06-02 | COMP | 2020-06-23 | COMP | Rule 16 | 25 | 48 | 25 | 1 | 6 | 16 | 116
17493 | 2020-01-09 | 2020-02-18 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-06-09 | COMP | 2020-07-21 | COMP | Rule 16 | 27 | 40 | 31 | 1 | 11 | 31 | 136
17598 | 2020-01-09 | 2020-02-20 | 2020-03-13 | 2020-03-13 | COMP | 2020-08-17 | COMP | 2020-08-19 | NOTN | 2020-11-17 | COMP | 2020-11-28 | COMP | Rule 16 | 29 | 17 | 111 |  |  |  | 225
17611 | 2020-01-09 | 2020-02-20 | 2020-06-04 | 2020-06-04 | COMP | 2020-06-23 | COMP | 2020-07-08 | COMP | 2020-06-24 | COMP | 2020-09-04 | COMP | Rule 16 | 29 | 75 | 14 | 12 | 0 | 43 | 169
17632 | 2020-01-09 | 2020-02-24 | 2020-05-01 | 2020-07-02 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2020-08-03 | COMP | 2020-08-04 | COMP | Rule 16 | 31 | 50 | 18 | 1 | 6 | 2 | 146
17648 | 2020-01-09 | 2020-02-24 | 2020-05-19 | 2020-09-21 | COMP | 2020-09-24 | COMP | 2020-09-24 | COMP | 2020-09-24 | COMP | 2020-10-23 | COMP | Rule 16 | 31 | 62 | 4 | 1 | 1 | 22 | 203
17707 | 2020-01-09 | 2020-02-24 | 2020-08-05 | 2020-08-05 | COMP | 2020-10-23 | COMP | 2020-10-24 | COMP | 2021-07-21 | COMP | 2021-07-30 | COMP | Rule 16 | 31 | 117 | 57 | 1 | 184 | 8 | 394
17767 | 2020-01-09 | 2020-02-26 | 2020-05-28 | 2020-05-28 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-25 | COMP | Rule 16 | 33 | 66 | 12 | 1 | 1 | 31 | 139
17866 | 2020-01-09 | 2020-03-03 | 2020-11-19 | 2020-11-19 | COMP | 2021-01-20 | COMP | 2021-02-05 | COMP | 2021-06-08 | COMP | 2021-07-13 | COMP | Rule 16 | 37 | 185 | 40 | 13 | 86 | 25 | 381
17896 | 2020-01-09 | 2020-03-03 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-07 | NOTN | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-10-22 | COMP | Other | 37 | 47 |  | 11 | 1 | 110 | 202
17922 | 2020-01-09 | 2020-03-04 | 2020-05-17 | 2020-05-17 | COMP | 2020-06-30 | COMP | 2020-07-16 | COMP | 2021-04-12 | COMP | 2021-05-12 | COMP | Rule 16 | 38 | 53 | 31 | 13 | 185 | 23 | 339
17937 | 2020-01-09 | 2020-03-04 | 2020-04-26 | 2020-04-26 | COMP | 2020-05-27 | COMP | 2020-07-29 | COMP | 2020-09-22 | COMP | 2020-11-02 | COMP | Rule 16 | 38 | 38 | 22 | 46 | 39 | 30 | 209
18041 | 2020-01-09 | 2020-03-09 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-15 | COMP | 2020-08-11 | COMP | 2020-10-01 | COMP | 2020-10-21 | COMP | Rule 16 | 41 | 42 | 29 | 42 | 37 | 15 | 201
18106 | 2020-01-09 | 2020-03-11 | 2020-03-30 | 2020-03-30 | COMP | 2020-05-04 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-09-30 | COMP | Rule 16 | 43 | 14 | 26 | 95 | 1 | 12 | 186
18174 | 2020-01-09 | 2020-03-14 | 2020-06-10 | 2020-06-10 | COMP | 2020-06-12 | COMP | 2020-08-04 | COMP | 2020-09-22 | COMP | 2020-12-09 | COMP | Rule 16 | 45 | 62 | 3 | 38 | 35 | 54 | 233
18280 | 2020-01-09 | 2020-03-19 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-15 | COMP | 2020-06-15 | COMP | 2020-09-16 | COMP | 2020-10-12 | COMP | Rule 15/16 | 49 | 42 | 21 | 1 | 67 | 19 | 194
18361 | 2020-01-09 | 2020-03-21 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-11-25 | COMP | 2020-12-19 | COMP | Rule 16 | 50 | 76 | 19 | 1 | 82 | 16 | 240
18455 | 2020-01-09 | 2020-03-25 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-23 | COMP | 2020-05-07 | COMP | 2020-10-19 | COMP | 2020-11-04 | COMP | Rule 16 | 53 | 12 | 11 | 11 | 116 | 13 | 211
18520 | 2020-01-09 | 2020-03-27 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-06 | COMP | 2020-05-12 | COMP | 2020-05-18 | COMP | 2020-06-04 | COMP | Rule 16 | 55 | 25 | 5 | 5 | 5 | 13 | 103
18693 | 2020-01-09 | 2020-04-03 | 2020-08-10 | 2021-04-03 | COMP | 2021-04-23 | COMP | 2021-05-10 | COMP | 2021-08-06 | COMP | 2021-11-15 | COMP | Rule 16 | 60 | 91 | 15 | 12 | 63 | 70 | 468
19034 | 2020-01-09 | 2020-04-17 | 2020-06-23 | 2020-06-23 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2020-10-01 | COMP | 2020-12-14 | COMP | Rule 16 | 70 | 47 | 41 | 1 | 32 | 50 | 236
19238 | 2020-01-09 | 2020-04-27 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-07-06 | COMP | 2020-07-23 | COMP | Rule 16 | 76 | 25 | 15 | 1 | 12 | 14 | 138
19239 | 2020-01-09 | 2020-04-27 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-07-06 | COMP | 2020-07-24 | COMP | Rule 16 | 76 | 25 | 7 | 1 | 20 | 15 | 139
19406 | 2020-01-09 | 2020-05-06 | 2021-05-07 | 2021-10-04 | COMP | 2021-10-28 | COMP | 2022-06-29 | COMP | 2022-08-10 | COMP | 2023-08-22 | COMP | Rule 15/16 | 83 | 254 | 19 | 168 | 30 | 259 | 911
19492 | 2020-01-09 | 2020-05-09 | 2020-08-05 | 2020-08-05 | COMP | 2020-08-05 | NOTN | 2020-09-28 | COMP | 2020-08-05 | COMP | 2020-11-02 | COMP | Other | 85 | 62 |  | 38 | 0 | 26 | 209
19514 | 2020-01-09 | 2020-05-11 | 2020-12-16 | 2020-12-16 | COMP | 2021-02-25 | COMP | 2021-05-29 | COMP | 2021-01-14 | COMP | 2021-11-19 | COMP | Rule 15/16 | 86 | 153 | 48 | 67 | 0 | 121 | 472
19586 | 2020-01-09 | 2020-05-13 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-10 | COMP | 2020-06-19 | COMP | 2020-06-16 | COMP | 2020-07-28 | COMP | Rule 16 | 88 | 15 | 6 | 8 | 0 | 28 | 141
19652 | 2020-01-09 | 2020-05-15 | 2020-08-13 | 2020-08-13 | COMP | 2020-10-13 | COMP | 2020-10-21 | COMP | 2020-11-15 | COMP | 2020-12-16 | COMP | Rule 16 | 90 | 64 | 43 | 7 | 17 | 21 | 238
19842 | 2020-01-09 | 2020-05-26 | 2020-10-15 | 2020-10-15 | COMP | 2021-02-09 | COMP | 2021-02-09 | COMP | 2021-09-14 | COMP | 2021-09-28 | COMP | Rule 16 | 96 | 102 | 78 | 1 | 152 | 11 | 435
20095 | 2020-01-09 | 2020-06-04 | 2020-07-13 | 2020-07-13 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2021-01-15 | COMP | 2021-03-27 | COMP | Rule 16 | 103 | 28 | 42 | 1 | 88 | 49 | 306
21205 | 2020-01-09 | 2020-07-27 | 2020-10-12 | 2020-10-12 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2022-03-20 | INPR | 2021-03-16 | COMP | Rule 16 | 140 | 55 | 7 | 1 |  |  | 298
16750 | 2020-01-10 | 2020-01-15 | 2020-01-30 | 2020-01-30 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-29 | COMP | 2020-07-06 | COMP | Rule 16 | 4 | 11 | 76 | 1 | 10 | 27 | 124
16771 | 2020-01-10 | 2020-01-15 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-21 | COMP | 2020-03-31 | COMP | 2020-05-18 | COMP | 2020-06-13 | COMP | Rule 16 | 4 | 12 | 14 | 28 | 35 | 19 | 108
16798 | 2020-01-10 | 2020-01-16 | 2020-05-27 | 2021-01-15 | COMP | 2020-05-19 | NOTN | 2021-04-27 | COMP | 2020-05-27 | COMP | 2021-06-01 | COMP | Other | 5 | 92 |  | 71 | 0 | 25 | 351
16975 | 2020-01-10 | 2020-01-27 | 2020-05-18 | 2020-05-18 | COMP | 2020-07-31 | COMP | 2020-12-17 | NOTN | 2020-12-17 | COMP | 2020-12-23 | COMP | Rule 16 | 11 | 80 | 54 |  |  |  | 242
17046 | 2020-01-10 | 2020-01-29 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-02 | NOTN | 2020-05-04 | COMP | 2020-05-02 | COMP | 2020-06-12 | COMP | Other | 13 | 68 |  | 1 | 0 | 29 | 108
17282 | 2020-01-10 | 2020-02-07 | 2020-03-25 | 2020-03-25 | COMP | 2020-04-17 | COMP | 2020-04-17 | COMP | 2020-04-30 | COMP | 2020-05-02 | COMP | Rule 16 | 20 | 33 | 18 | 1 | 10 | 2 | 79
17310 | 2020-01-10 | 2020-02-08 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-07-05 | COMP | 2020-08-25 | COMP | Rule 16 | 20 | 73 | 31 | 1 | 1 | 37 | 160
17356 | 2020-01-10 | 2020-02-11 | 2021-04-01 | 2021-10-22 | COMP | 2021-12-14 | COMP | 2021-12-14 | COMP | 2022-11-15 | COMP | 2023-06-22 | COMP | Rule 15/16 | 22 | 288 | 35 | 1 | 234 | 150 | 868
17516 | 2020-01-10 | 2020-02-18 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-05-17 | COMP | 2020-07-06 | COMP | Rule 16 | 26 | 43 | 25 | 1 | 0 | 33 | 124
17576 | 2020-01-10 | 2020-02-20 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-27 | COMP | 2020-05-15 | COMP | 2020-04-27 | COMP | 2020-07-03 | COMP | Rule 16 | 28 | 37 | 12 | 15 | 0 | 35 | 123
17680 | 2020-01-10 | 2020-02-24 | 2020-08-27 | 2020-08-27 | COMP | 2020-09-11 | COMP | 2020-09-15 | COMP | 2020-11-17 | COMP | 2020-12-06 | COMP | Rule 16 | 30 | 133 | 11 | 3 | 45 | 12 | 229
17701 | 2020-01-10 | 2020-02-25 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-01-27 | COMP | 2021-03-02 | COMP | Rule 16 | 31 | 54 | 77 | 1 | 105 | 24 | 287
17784 | 2020-01-10 | 2020-02-28 | 2020-04-27 | 2020-04-27 | COMP | 2020-06-02 | COMP | 2020-08-11 | COMP | 2023-03-09 | COMP | 2023-01-25 | COMP | Rule 16 | 34 | 42 | 26 | 51 | 646 |  | 765
17905 | 2020-01-10 | 2020-03-03 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-08-21 | COMP | 2020-11-10 | COMP | Rule 16 | 36 | 94 | 35 | 1 | 0 | 52 | 214
18021 | 2020-01-10 | 2020-03-09 | 2020-09-25 | 2020-09-25 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2021-04-07 | COMP | 2021-06-19 | COMP | Rule 16 | 40 | 143 | 24 | 1 | 109 | 52 | 364
18436 | 2020-01-10 | 2020-03-25 | 2020-04-23 | 2020-04-23 | COMP | 2020-06-11 | COMP | 2020-06-23 | COMP | 2020-10-12 | COMP | 2020-11-20 | COMP | Rule 16 | 52 | 22 | 35 | 9 | 79 | 29 | 221
18437 | 2020-01-10 | 2020-03-26 | 2020-09-22 | 2023-02-13 | COMP | 2023-04-12 | COMP | 2023-08-09 | COMP | 2023-07-27 | COMP | 2023-10-26 | COMP | Rule 15/16 | 53 | 127 | 42 | 83 | 0 | 56 | 956
18448 | 2020-01-10 | 2020-03-24 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-21 | COMP | 2020-12-14 | COMP | 2021-02-26 | COMP | 2021-03-23 | COMP | Rule 16 | 51 | 103 | 6 | 78 | 51 | 18 | 302
18912 | 2020-01-10 | 2020-04-13 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-27 | COMP | 2020-07-20 | COMP | 2020-06-18 | COMP | 2020-08-13 | COMP | Rule 16 | 65 | 9 | 3 | 60 | 0 | 19 | 152
18925 | 2020-01-10 | 2020-04-13 | 2020-07-30 | 2020-07-30 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2021-06-02 | COMP | 2021-06-11 | COMP | Rule 15/16 | 65 | 78 | 18 | 1 | 194 | 8 | 359
18970 | 2020-01-10 | 2020-04-15 | 2020-12-20 | 2020-12-20 | COMP | 2021-04-08 | COMP | 2021-04-08 | COMP | 2023-04-28 | COMP | 2023-06-01 | COMP | Rule 15/16 | 67 | 173 | 75 | 1 | 518 | 24 | 854
19449 | 2020-01-10 | 2020-05-07 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-18 | COMP | 2020-08-07 | COMP | 2020-07-21 | COMP | 2020-09-03 | COMP | Rule 16 | 83 | 26 | 5 | 37 | 0 | 20 | 167
20278 | 2020-01-10 | 2020-06-12 | 2020-07-09 | 2020-07-09 | COMP | 2020-07-13 | COMP | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-09-22 | COMP | Rule 16 | 108 | 20 | 3 | 25 | 1 | 27 | 179
17149 | 2020-01-11 | 2020-01-31 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-01 | COMP | 2020-08-31 | COMP | 2020-08-28 | COMP | 2020-09-24 | COMP | Rule 16 | 14 | 66 | 20 | 66 | 0 | 18 | 180
17229 | 2020-01-11 | 2020-02-04 | 2020-04-14 | 2020-04-14 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-11-24 | COMP | 2021-02-22 | COMP | Rule 16 | 16 | 50 | 19 | 1 | 140 | 59 | 280
16693 | 2020-01-12 | 2020-01-13 | 2020-05-19 | 2020-05-19 | COMP | 2020-07-29 | NOTN | 2020-08-11 | COMP | 2020-07-29 | COMP | 2020-10-09 | COMP | Other | 1 | 90 |  | 60 | 0 | 43 | 191
4317 | 2020-01-13 | 2020-09-02 | 2020-10-02 | 2020-10-02 | COMP | 2020-10-20 | COMP | 2021-01-07 | COMP | 2020-12-23 | COMP | 2021-01-14 | COMP | Rule 16 | 165 | 22 | 13 | 53 | 0 | 6 | 255
16689 | 2020-01-13 | 2020-01-13 | 2020-05-28 | 2022-03-11 | COMP | 2022-04-05 | COMP | 2022-04-12 | COMP | 2022-04-28 | COMP | 2022-06-30 | COMP | Rule 16 | 1 | 96 | 18 | 6 | 13 | 44 | 623
16800 | 2020-01-13 | 2020-01-16 | 2020-03-08 | 2020-03-08 | COMP | 2020-03-16 | COMP | 2020-03-17 | COMP | 2020-04-15 | COMP | 2020-04-14 | COMP | Rule 16 | 4 | 35 | 6 | 2 | 22 |  | 65
16917 | 2020-01-13 | 2020-01-23 | 2020-04-03 | 2020-04-14 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-05-11 | COMP | 2020-05-22 | COMP | Rule 16 | 8 | 51 | 10 | 1 | 11 | 10 | 93
16973 | 2020-01-13 | 2020-01-27 | 2020-03-13 | 2020-03-13 | COMP | 2020-03-24 | COMP | 2020-03-24 | COMP | 2020-03-19 | COMP | 2020-04-09 | COMP | Rule 15/16 | 10 | 34 | 8 | 1 | 0 | 13 | 62
17112 | 2020-01-13 | 2020-01-31 | 2020-04-05 | 2020-04-05 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-10-01 | COMP | 2020-10-16 | COMP | Rule 16 | 14 | 45 | 8 | 1 | 120 | 12 | 196
17114 | 2020-01-13 | 2020-01-31 | 2020-06-03 | 2020-06-03 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-08-06 | COMP | 2020-08-20 | COMP | Rule 16 | 14 | 87 | 45 | 1 | 3 | 11 | 156
17183 | 2020-01-13 | 2020-02-03 | 2020-02-27 | 2020-02-27 | COMP | 2020-03-19 | COMP | 2020-04-02 | COMP | 2020-07-28 | COMP | 2020-09-01 | COMP | Rule 16 | 15 | 18 | 16 | 11 | 83 | 26 | 164
17247 | 2020-01-13 | 2020-02-06 | 2020-03-02 | 2020-03-02 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-08-21 | COMP | 2020-09-22 | COMP | Rule 16 | 18 | 17 | 100 | 1 | 25 | 22 | 178
17365 | 2020-01-13 | 2020-02-11 | 2020-03-27 | 2020-03-27 | COMP | 2020-04-20 | COMP | 2020-04-20 | COMP | 2020-06-08 | COMP | 2020-06-29 | COMP | Rule 16 | 21 | 33 | 17 | 1 | 35 | 16 | 118
17368 | 2020-01-13 | 2020-02-11 | 2020-05-20 | 2020-05-20 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2021-01-08 | COMP | 2021-03-02 | COMP | Rule 16 | 21 | 71 | 160 | 1 | 2 | 36 | 286
17486 | 2020-01-13 | 2020-02-18 | 2020-06-05 | 2020-06-05 | COMP | 2021-07-23 | COMP | 2021-07-23 | COMP | 2021-08-24 | COMP | 2021-10-15 | COMP | Rule 16 | 25 | 78 | 286 | 1 | 23 | 38 | 446
17933 | 2020-01-13 | 2020-03-04 | 2020-05-18 | 2020-05-18 | COMP | 2020-08-03 | COMP | 2020-09-11 | COMP | 2020-10-07 | COMP | 2020-11-24 | COMP | Rule 15/16 | 36 | 54 | 55 | 29 | 19 | 34 | 222
17939 | 2020-01-13 | 2020-03-04 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-21 | COMP | 2020-09-25 | COMP | Rule 16 | 36 | 75 | 28 | 1 | 21 | 25 | 181
18185 | 2020-01-13 | 2020-03-13 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-23 | COMP | 2020-07-30 | COMP | 2020-07-22 | COMP | 2020-08-20 | COMP | Rule 16 | 43 | 43 | 30 | 28 | 0 | 16 | 156
18300 | 2020-01-13 | 2020-03-18 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-24 | NOTN | 2020-04-24 | COMP | 2020-07-14 | COMP | 2020-06-08 | COMP | Other | 46 | 27 |  | 2 | 57 |  | 103
18865 | 2020-01-13 | 2020-04-09 | 2020-10-06 | 2020-10-06 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2020-12-21 | COMP | 2021-02-12 | COMP | Rule 15/16 | 62 | 127 | 51 | 1 | 2 | 37 | 275
19328 | 2020-01-13 | 2020-05-02 | 2020-08-14 | 2020-10-12 | COMP | 2020-12-10 | COMP | 2020-12-10 | COMP | 2020-12-22 | COMP | 2021-03-08 | COMP | Rule 16 | 78 | 74 | 41 | 1 | 9 | 51 | 290
19379 | 2020-01-13 | 2020-05-04 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-07-23 | COMP | 2020-09-01 | COMP | Rule 16 | 79 | 16 | 19 | 1 | 25 | 29 | 164
19544 | 2020-01-13 | 2020-05-11 | 2020-06-02 | 2020-06-02 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-11-04 | COMP | 2020-12-11 | COMP | Rule 16 | 84 | 16 | 78 | 1 | 34 | 25 | 233
19549 | 2020-01-13 | 2020-05-12 | 2020-06-25 | 2020-10-21 | COMP | 2021-02-01 | COMP | 2021-06-09 | INPR | 2021-04-22 | COMP | 2021-06-05 | COMP | Rule 16 | 85 | 32 | 68 |  |  |  | 353
20263 | 2020-01-13 | 2020-06-13 | 2020-08-11 | 2020-08-11 | COMP | 2021-01-19 | COMP | 2021-01-20 | COMP | 2021-06-22 | COMP | 2021-07-02 | COMP | Rule 15/16 | 107 | 42 | 109 | 2 | 108 | 9 | 373
4269 | 2020-01-14 | 2020-02-01 | 2020-12-07 | 2020-12-07 | COMP |  |  |  |  | 2020-02-24 | COMP | 2020-05-14 | COMP | Other | 13 | 215 |  |  |  |  | 86
16824 | 2020-01-14 | 2020-01-17 | 2020-02-01 | 2020-02-01 | COMP | 2020-02-14 | COMP | 2020-02-14 | COMP | 2020-06-16 | COMP | 2020-08-15 | COMP | Rule 16 | 4 | 10 | 10 | 1 | 86 | 44 | 151
16984 | 2020-01-14 | 2020-01-28 | 2020-03-09 | 2020-03-09 | COMP | 2020-03-20 | COMP | 2020-06-15 | COMP | 2020-06-13 | COMP | 2020-07-08 | COMP | Rule 16 | 10 | 29 | 10 | 61 | 0 | 18 | 124
17186 | 2020-01-14 | 2020-02-03 | 2020-03-05 | 2020-03-05 | COMP | 2020-03-18 | NOTN | 2020-03-18 | COMP | 2021-04-24 | INPR | 2020-03-31 | COMP | Rule 16 | 14 | 23 |  | 10 |  |  | 54
17199 | 2020-01-14 | 2020-02-04 | 2020-02-25 | 2020-02-25 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | Rule 16 | 15 | 15 | 15 | 1 | 24 | 1 | 66
17226 | 2020-01-14 | 2020-02-04 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-07-07 | COMP | 2020-07-27 | COMP | Rule 16 | 15 | 65 | 23 | 1 | 23 | 15 | 137
17280 | 2020-01-14 | 2020-02-07 | 2020-04-10 | 2020-04-10 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-06-10 | COMP | 2020-07-22 | COMP | Rule 16 | 18 | 45 | 42 | 1 | 2 | 31 | 134
17451 | 2020-01-14 | 2020-02-13 | 2020-07-01 | 2020-07-01 | COMP | 2021-01-08 | COMP | 2021-11-24 | COMP | 2021-10-18 | COMP | 2022-01-19 | COMP | Rule 15/16 | 22 | 98 | 132 | 223 | 0 | 38 | 509
17454 | 2020-01-14 | 2020-02-13 | 2020-04-17 | 2020-05-06 | COMP | 2020-05-11 | COMP | 2020-06-19 | COMP | 2020-06-22 | COMP | 2020-07-22 | COMP | Rule 16 | 22 | 46 | 4 | 29 | 2 | 23 | 134
17554 | 2020-01-14 | 2020-02-20 | 2020-06-19 | 2020-06-19 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2020-12-15 | COMP | 2022-02-08 | COMP | Other | 26 | 86 | 118 | 1 | 7 | 290 | 523
17575 | 2020-01-14 | 2020-02-20 | 2020-04-01 | 2020-04-09 | COMP | 2020-12-08 | COMP | 2020-07-30 | COMP | 2022-12-03 | INPR | 2021-03-25 | COMP | Rule 16 | 26 | 30 | 169 |  |  |  | 302
17641 | 2020-01-14 | 2020-02-24 | 2020-05-05 | 2020-05-05 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2020-06-05 | COMP | 2020-08-24 | COMP | Rule 16 | 28 | 52 | 44 | 1 | 0 | 36 | 157
17754 | 2020-01-14 | 2020-02-26 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-01 | COMP | 2021-01-06 | COMP | 2021-02-11 | COMP | 2021-03-17 | COMP | Rule 16 | 30 | 58 | 11 | 152 | 26 | 24 | 296
17764 | 2020-01-14 | 2020-02-26 | 2020-02-28 | 2020-02-28 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-03-31 | COMP | 2020-04-03 | COMP | Rule 16 | 30 | 3 | 17 | 1 | 7 | 4 | 57
17915 | 2020-01-14 | 2020-03-03 | 2020-05-15 | 2020-05-15 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-27 | COMP | 2020-09-30 | COMP | Rule 16 | 34 | 54 | 37 | 1 | 38 | 24 | 183
18020 | 2020-01-14 | 2020-03-09 | 2020-06-09 | 2020-10-01 | COMP | 2020-10-08 | COMP | 2020-12-07 | COMP | 2021-02-02 | COMP | 2021-03-09 | COMP | Rule 16 | 38 | 66 | 6 | 40 | 39 | 25 | 290
18037 | 2020-01-14 | 2020-03-09 | 2020-06-29 | 2021-11-11 | COMP | 2022-07-21 | COMP | 2023-01-18 | COMP | 2023-02-14 | COMP | 2023-04-16 | COMP | Rule 16 | 38 | 80 | 173 | 123 | 20 | 43 | 819
18117 | 2020-01-14 | 2020-03-11 | 2020-05-02 | 2021-07-20 | COMP | 2020-10-23 | NOTN | 2023-03-14 | COMP | 2023-01-06 | COMP | 2023-05-16 | COMP | Other | 40 | 38 |  | 414 | 0 | 46 | 841
18145 | 2020-01-14 | 2020-03-12 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-19 | COMP | 2020-07-17 | COMP | 2020-07-15 | COMP | 2020-07-27 | COMP | Rule 16 | 41 | 32 | 18 | 43 | 0 | 7 | 137
18217 | 2020-01-14 | 2020-03-16 | 2020-03-24 | 2020-03-24 | COMP | 2020-08-31 | COMP | 2020-10-09 | COMP | 2020-10-08 | COMP | 2020-09-02 | COMP | Rule 16 | 43 | 7 | 114 | 29 | 0 |  | 164
18222 | 2020-01-14 | 2020-03-16 | 2020-06-09 | 2020-09-24 | COMP | 2020-09-30 | COMP | 2020-09-30 | COMP | 2020-09-10 | COMP | 2020-11-10 | COMP | Rule 16 | 43 | 61 | 5 | 1 | 0 | 30 | 212
18305 | 2020-01-14 | 2020-03-19 | 2021-02-12 | 2021-03-05 | COMP | 2021-03-11 | COMP | 2021-05-06 | COMP | 2023-12-03 | INPR | 2021-05-19 | COMP | Rule 16 | 46 | 229 | 5 | 41 |  |  | 341
18372 | 2020-01-14 | 2020-03-21 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-01 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-11-19 | COMP | Rule 16 | 47 | 43 | 8 | 56 | 1 | 67 | 218
18596 | 2020-01-14 | 2020-03-31 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-08-18 | COMP | 2020-08-28 | COMP | Rule 16 | 54 | 30 | 30 | 1 | 42 | 9 | 161
19062 | 2020-01-14 | 2020-04-20 | 2020-10-29 | 2020-10-29 | COMP | 2020-11-16 | COMP | 2020-11-16 | COMP | 2022-03-20 | INPR | 2021-02-26 | COMP | Rule 16 | 68 | 137 | 12 | 1 |  |  | 283
19177 | 2020-01-14 | 2020-04-23 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-27 | COMP | 2020-07-24 | COMP | 2021-04-02 | COMP | 2021-05-04 | COMP | Rule 16 | 71 | 17 | 8 | 43 | 173 | 23 | 330
19183 | 2020-01-14 | 2020-04-23 | 2020-10-01 | 2020-10-01 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2021-11-16 | COMP | 2021-12-10 | COMP | Rule 16 | 71 | 114 | 27 | 1 | 257 | 17 | 482
19218 | 2020-01-14 | 2020-04-24 | 2020-10-06 | 2020-10-06 | COMP | 2021-03-01 | COMP | 2021-05-12 | COMP | 2021-05-12 | COMP | 2021-09-01 | COMP | Rule 16 | 72 | 116 | 98 | 53 | 1 | 79 | 414
19261 | 2020-01-14 | 2020-04-29 | 2020-08-13 | 2020-08-13 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2021-02-08 | COMP | 2021-02-23 | COMP | Rule 16 | 75 | 76 | 27 | 1 | 95 | 11 | 280
19430 | 2020-01-14 | 2020-05-06 | 2020-08-10 | 2020-08-10 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2021-12-23 | COMP | 2022-02-01 | COMP | Rule 16 | 80 | 68 | 44 | 1 | 302 | 28 | 518
19574 | 2020-01-14 | 2020-05-13 | 2020-08-16 | 2020-08-16 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2020-12-08 | COMP | 2021-01-25 | COMP | Rule 16 | 85 | 67 | 20 | 1 | 59 | 32 | 260
19651 | 2020-01-14 | 2020-05-16 | 2020-10-02 | 2020-10-02 | COMP | 2020-10-27 | COMP | 2021-02-27 | COMP | 2021-02-24 | COMP | 2021-04-08 | COMP | Rule 16 | 87 | 98 | 18 | 82 | 0 | 29 | 312
19856 | 2020-01-14 | 2020-05-26 | 2020-08-30 | 2020-08-30 | COMP | 2020-09-30 | COMP | 2020-10-26 | COMP | 2021-04-30 | COMP | 2021-06-29 | COMP | Rule 16 | 93 | 69 | 22 | 19 | 128 | 42 | 369
19965 | 2020-01-14 | 2020-05-29 | 2020-07-02 | 2020-08-10 | COMP | 2020-10-05 | COMP | 2020-10-05 | COMP | 2020-10-06 | COMP | 2020-11-24 | COMP | Rule 15/16 | 96 | 25 | 40 | 1 | 2 | 35 | 221
21426 | 2020-01-14 | 2020-08-06 | 2020-09-11 | 2020-09-11 | COMP | 2020-09-18 | COMP | 2021-07-19 | COMP | 2021-09-29 | COMP | 2021-11-03 | COMP | Rule 16 | 145 | 26 | 6 | 208 | 52 | 26 | 458
16791 | 2020-01-15 | 2020-01-15 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-19 | NOTN | 2021-03-11 | COMP | 2021-03-23 | COMP | 2021-04-15 | COMP | Other | 1 | 110 |  | 182 | 9 | 18 | 316
16874 | 2020-01-15 | 2020-01-22 | 2020-02-03 | 2020-02-03 | COMP | 2020-02-07 | COMP | 2020-02-26 | COMP | 2020-02-28 | COMP | 2020-03-10 | COMP | Rule 16 | 5 | 9 | 5 | 13 | 3 | 8 | 38
16954 | 2020-01-15 | 2020-01-24 | 2020-05-12 | 2020-05-12 | COMP | 2020-05-13 | NOTN | 2020-06-29 | COMP | 2020-07-28 | COMP | 2020-12-15 | COMP | Other | 7 | 77 |  | 34 | 22 | 97 | 233
17028 | 2020-01-15 | 2020-01-28 | 2020-05-27 | 2020-05-27 | COMP | 2020-05-20 | NOTN | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-11-19 | COMP | Other | 9 | 85 |  | 1 | 1 | 125 | 217
17075 | 2020-01-15 | 2020-01-29 | 2020-02-14 | 2020-03-06 | COMP | 2020-03-13 | COMP | 2020-03-13 | COMP | 2020-04-15 | COMP | 2020-05-06 | COMP | Rule 16 | 10 | 13 | 6 | 1 | 24 | 16 | 79
17103 | 2020-01-15 | 2020-01-30 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-07-22 | COMP | 2020-07-24 | COMP | Rule 16 | 11 | 71 | 15 | 1 | 39 | 3 | 135
17165 | 2020-01-15 | 2020-02-03 | 2020-03-12 | 2020-03-12 | COMP | 2020-03-24 | COMP | 2020-05-06 | COMP | 2020-08-26 | COMP | 2020-09-01 | COMP | Rule 16 | 13 | 28 | 9 | 32 | 80 | 5 | 162
17166 | 2020-01-15 | 2020-02-03 | 2020-03-12 | 2020-03-12 | COMP | 2020-03-24 | COMP | 2020-05-05 | COMP | 2020-08-26 | COMP | 2020-09-01 | COMP | Rule 16 | 13 | 28 | 9 | 31 | 81 | 5 | 162
17167 | 2020-01-15 | 2020-02-03 | 2020-03-10 | 2020-03-10 | COMP | 2020-03-24 | COMP | 2020-05-05 | COMP | 2020-08-26 | COMP | 2020-08-31 | COMP | Rule 16 | 13 | 26 | 11 | 31 | 81 | 4 | 161
17168 | 2020-01-15 | 2020-02-03 | 2020-03-10 | 2020-03-10 | COMP | 2020-04-07 | COMP | 2020-04-07 | COMP | 2020-08-26 | COMP | 2020-08-31 | COMP | Rule 16 | 13 | 26 | 21 | 1 | 101 | 4 | 161
17171 | 2020-01-15 | 2020-02-03 | 2020-04-10 | 2020-04-17 | COMP | 2020-04-22 | COMP | 2020-04-22 | COMP | 2020-08-26 | COMP | 2020-08-31 | COMP | Rule 16 | 13 | 49 | 4 | 1 | 90 | 4 | 161
17391 | 2020-01-15 | 2020-02-12 | 2020-03-26 | 2020-03-26 | COMP | 2020-04-29 | COMP | 2020-06-25 | COMP | 2020-06-25 | COMP | 2020-08-06 | COMP | Rule 16 | 20 | 31 | 25 | 41 | 1 | 31 | 144
17404 | 2020-01-15 | 2020-02-12 | 2020-05-04 | 2020-05-04 | COMP | 2021-02-26 | COMP | 2021-02-26 | COMP | 2021-08-03 | COMP | 2021-08-11 | COMP | Rule 16 | 20 | 58 | 206 | 1 | 111 | 7 | 398
17572 | 2020-01-15 | 2020-02-20 | 2020-04-15 | 2020-04-15 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2021-10-23 | INPR | 2020-10-01 | COMP | Rule 16 | 25 | 40 | 55 | 1 |  |  | 183
17728 | 2020-01-15 | 2020-02-25 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-08 | COMP | 2020-07-06 | COMP | 2023-12-03 | INPR | 2021-11-08 | COMP | Rule 16 | 28 | 38 | 17 | 41 |  |  | 460
17775 | 2020-01-15 | 2020-02-26 | 2020-05-19 | 2020-08-31 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2020-09-29 | COMP | 2020-12-15 | COMP | Rule 16 | 29 | 60 | 13 | 1 | 9 | 53 | 233
17895 | 2020-01-15 | 2020-03-03 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-10-26 | COMP | 2020-11-16 | COMP | Rule 16 | 33 | 76 | 33 | 1 | 61 | 15 | 214
17900 | 2020-01-15 | 2020-03-03 | 2020-04-23 | 2020-12-03 | COMP | 2020-12-18 | COMP | 2021-03-09 | COMP | 2021-01-12 | COMP | 2021-03-25 | COMP | Rule 16 | 33 | 38 | 12 | 54 | 0 | 13 | 301
17987 | 2020-01-15 | 2020-03-06 | 2020-06-08 | 2021-03-05 | COMP | 2021-04-02 | COMP | 2021-04-09 | COMP | 2020-10-28 | COMP | 2021-04-17 | COMP | Rule 15 | 36 | 66 | 21 | 6 | 0 | 6 | 317
18001 | 2020-01-15 | 2020-03-06 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-20 | COMP | 2020-09-10 | COMP | 2020-09-14 | COMP | 2020-10-08 | COMP | Rule 15/16 | 36 | 69 | 28 | 38 | 3 | 19 | 188
18056 | 2020-01-15 | 2020-03-10 | 2020-04-17 | 2020-04-27 | COMP | 2020-05-12 | COMP | 2020-06-08 | COMP | 2020-06-17 | COMP | 2020-07-13 | COMP | Rule 15/16 | 38 | 29 | 12 | 19 | 8 | 19 | 126
18165 | 2020-01-15 | 2020-03-13 | 2020-05-03 | 2020-05-03 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-09-15 | COMP | 2020-08-22 | COMP | Rule 16 | 41 | 36 | 8 | 1 | 88 |  | 155
18244 | 2020-01-15 | 2020-03-17 | 2020-12-23 | 2021-02-19 | COMP | 2021-03-10 | COMP | 2021-04-26 | COMP | 2022-07-16 | INPR | 2021-06-10 | COMP | Rule 16 | 43 | 197 | 14 | 34 |  |  | 355
18551 | 2020-01-15 | 2020-03-30 | 2020-05-12 | 2020-05-12 | COMP | 2020-05-19 | COMP | 2020-05-19 | COMP | 2020-06-02 | COMP | 2020-07-14 | COMP | Rule 16 | 52 | 32 | 6 | 1 | 10 | 31 | 127
18662 | 2020-01-15 | 2020-04-01 | 2020-11-08 | 2020-11-08 | COMP | 2020-11-12 | COMP | 2020-12-29 | COMP | 2021-01-05 | COMP | 2021-01-26 | COMP | Rule 16 | 54 | 156 | 3 | 31 | 5 | 15 | 260
18782 | 2020-01-15 | 2020-04-07 | 2020-04-15 | 2020-04-15 | COMP | 2020-04-30 | COMP | 2020-04-30 | COMP | 2020-10-13 | COMP | 2020-11-01 | COMP | Rule 16 | 58 | 7 | 12 | 1 | 117 | 14 | 204
19298 | 2020-01-15 | 2020-04-28 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-18 | COMP | 2020-07-28 | COMP | 2020-07-23 | COMP | 2020-08-13 | COMP | Rule 16 | 73 | 29 | 9 | 29 | 0 | 13 | 149
19593 | 2020-01-15 | 2020-05-13 | 2020-10-23 | 2020-10-23 | COMP | 2020-11-17 | NOTN | 2021-01-20 | COMP | 2023-12-04 | INPR | 2021-06-29 | COMP | Rule 16 | 84 | 116 |  | 58 |  |  | 368
19629 | 2020-01-15 | 2020-05-15 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-09-28 | COMP | 2020-10-08 | COMP | Rule 16 | 86 | 3 | 20 | 1 | 74 | 9 | 188
19959 | 2020-01-15 | 2020-05-29 | 2020-07-10 | 2020-07-10 | COMP | 2020-10-27 | COMP | 2020-12-14 | COMP | 2020-11-09 | COMP | 2021-02-23 | COMP | Rule 16 | 95 | 31 | 77 | 32 | 0 | 48 | 279
19996 | 2020-01-15 | 2020-06-01 | 2020-08-08 | 2020-08-08 | COMP | 2021-08-31 | COMP | 2021-08-31 | COMP | 2021-09-23 | COMP | 2021-11-03 | COMP | Rule 16 | 96 | 50 | 267 | 1 | 17 | 30 | 457
20183 | 2020-01-15 | 2020-06-10 | 2020-07-30 | 2020-07-30 | COMP | 2021-02-26 | COMP | 2021-05-05 | COMP | 2021-05-10 | COMP | 2021-06-10 | COMP | Rule 16 | 103 | 37 | 144 | 49 | 4 | 23 | 355
21816 | 2020-01-15 | 2020-08-27 | 2020-12-22 | 2020-12-22 | COMP | 2021-03-25 | COMP | 2021-06-30 | COMP | 2022-01-10 | COMP | 2022-01-20 | COMP | Rule 15/16 | 159 | 80 | 64 | 69 | 134 | 8 | 509
16834 | 2020-01-16 | 2020-01-18 | 2020-05-27 | 2020-05-27 | COMP | 2020-11-17 | NOTN | 2020-11-18 | COMP | 2021-06-09 | COMP | 2021-07-13 | COMP | Other | 2 | 90 |  | 124 | 139 | 24 | 376
16953 | 2020-01-16 | 2020-01-24 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | NOTN | 2020-05-20 | COMP | 2020-06-09 | COMP | 2020-08-10 | COMP | Other | 6 | 76 |  | 8 | 14 | 45 | 145
17015 | 2020-01-16 | 2020-01-28 | 2020-03-24 | 2020-03-24 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2020-08-07 | COMP | 2022-06-22 | COMP | Rule 16 | 8 | 40 | 97 | 1 | 2 | 471 | 614
17064 | 2020-01-16 | 2020-01-29 | 2020-07-13 | 2020-07-13 | COMP | 2020-09-22 | COMP | 2020-12-21 | COMP | 2020-12-23 | COMP | 2021-02-01 | COMP | Rule 15/16 | 9 | 117 | 51 | 62 | 3 | 26 | 263
17170 | 2020-01-16 | 2020-02-03 | 2020-03-25 | 2020-03-25 | COMP | 2020-05-11 | COMP | 2020-05-14 | COMP | 2020-08-18 | COMP | 2020-10-02 | COMP | Rule 15/16 | 12 | 37 | 34 | 4 | 68 | 33 | 183
17266 | 2020-01-16 | 2020-02-06 | 2020-04-07 | 2020-04-26 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-29 | COMP | 2020-07-27 | COMP | Rule 16 | 15 | 43 | 33 | 1 | 13 | 21 | 135
17509 | 2020-01-16 | 2020-02-19 | 2020-07-28 | 2021-08-05 | COMP | 2021-08-27 | COMP | 2021-08-27 | COMP | 2023-03-21 | COMP | 2023-04-27 | COMP | Rule 15/16 | 23 | 114 | 17 | 1 | 391 | 28 | 826
17683 | 2020-01-16 | 2020-02-24 | 2020-06-19 | 2020-06-19 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2021-01-13 | COMP | 2021-01-29 | COMP | Rule 16 | 26 | 84 | 47 | 1 | 97 | 12 | 262
17705 | 2020-01-16 | 2020-02-24 | 2020-07-13 | 2020-08-24 | COMP | 2020-08-26 | COMP | 2020-11-17 | COMP | 2020-10-12 | COMP | 2020-12-16 | COMP | Rule 16 | 26 | 100 | 3 | 58 | 0 | 20 | 233
17926 | 2020-01-16 | 2020-03-05 | 2020-04-26 | 2020-10-20 | COMP | 2020-11-24 | COMP | 2021-11-02 | COMP | 2020-04-27 | COMP | 2021-10-20 | COMP | Rule 16 | 34 | 37 | 25 | 237 | 0 |  | 446
18128 | 2020-01-16 | 2020-03-11 | 2020-03-24 | 2020-03-24 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2022-07-16 | INPR | 2021-04-01 | COMP | Rule 16 | 38 | 10 | 43 | 1 |  |  | 305
18248 | 2020-01-16 | 2020-03-17 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-06-09 | COMP | 2020-06-12 | COMP | Rule 16 | 42 | 33 | 12 | 1 | 17 | 4 | 104
18571 | 2020-01-16 | 2020-03-28 | 2020-10-05 | 2020-10-05 | COMP | 2021-02-02 | COMP | 2021-02-12 | COMP | 2022-02-01 | COMP | 2022-03-07 | COMP | Rule 15/16 | 50 | 134 | 81 | 9 | 245 | 24 | 539
18709 | 2020-01-16 | 2020-04-03 | 2020-07-09 | 2020-07-09 | COMP | 2020-07-13 | COMP | 2020-09-15 | COMP | 2020-09-21 | COMP | 2020-10-14 | COMP | Rule 16 | 55 | 69 | 3 | 46 | 5 | 18 | 191
19012 | 2020-01-16 | 2020-04-17 | 2020-10-28 | 2020-10-28 | COMP | 2022-03-10 | COMP | 2022-03-14 | COMP | 2022-12-20 | COMP | 2023-04-11 | COMP | Rule 16 | 65 | 137 | 342 | 3 | 195 | 77 | 814
19283 | 2020-01-16 | 2020-04-29 | 2020-08-06 | 2020-08-06 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP | 2021-02-26 | COMP | 2021-03-23 | COMP | Rule 16 | 73 | 71 | 125 | 1 | 15 | 18 | 298
19321 | 2020-01-16 | 2020-04-30 | 2020-05-15 | 2020-05-15 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2020-10-27 | COMP | 2020-12-03 | COMP | Rule 16 | 74 | 12 | 69 | 1 | 48 | 25 | 224
19473 | 2020-01-16 | 2020-05-08 | 2020-10-30 | 2020-11-21 | COMP | 2021-09-02 | COMP | 2021-12-07 | COMP | 2021-12-07 | COMP | 2022-10-05 | COMP | Rule 15/16 | 80 | 124 | 196 | 65 | 1 | 211 | 687
19566 | 2020-01-16 | 2020-05-12 | 2020-06-30 | 2020-10-14 | COMP | 2020-12-21 | COMP | 2020-12-21 | COMP | 2021-03-31 | COMP | 2021-05-03 | COMP | Rule 16 | 82 | 35 | 46 | 1 | 69 | 24 | 327
20545 | 2020-01-16 | 2020-06-25 | 2020-08-26 | 2020-08-26 | COMP | 2020-11-09 | COMP | 2020-12-10 | COMP | 2020-12-10 | COMP | 2021-01-21 | COMP | Rule 16 | 113 | 45 | 53 | 21 | 1 | 28 | 256
20756 | 2020-01-16 | 2020-07-03 | 2020-09-11 | 2020-09-11 | COMP | 2020-11-09 | COMP | 2021-04-16 | COMP | 2021-08-17 | COMP | 2021-09-20 | COMP | Rule 15 | 119 | 50 | 42 | 108 | 86 | 24 | 424
21138 | 2020-01-16 | 2020-07-23 | 2021-08-20 | 2021-10-26 | COMP | 2021-11-12 | COMP | 2022-02-17 | COMP | 2021-12-15 | COMP | 2022-04-25 | COMP | Rule 15/16 | 133 | 272 | 13 | 67 | 0 | 47 | 574
17018 | 2020-01-17 | 2020-01-27 | 2020-05-19 | 2020-05-19 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2020-10-14 | COMP | 2020-10-28 | COMP | Rule 16 | 6 | 81 | 31 | 1 | 75 | 11 | 200
17025 | 2020-01-17 | 2020-01-29 | 2020-05-30 | 2020-05-30 | COMP | 2020-08-13 | COMP | 2022-04-28 | COMP | 2022-04-12 | COMP | 2022-06-08 | COMP | Rule 16 | 8 | 86 | 54 | 430 | 0 | 29 | 604
17044 | 2020-01-17 | 2020-01-28 | 2020-05-14 | 2020-05-14 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-06-06 | COMP | 2020-08-01 | COMP | Rule 16 | 7 | 77 | 17 | 1 | 0 | 40 | 138
17047 | 2020-01-17 | 2020-01-29 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-23 | NOTN | 2020-05-23 | COMP | 2020-05-23 | COMP | 2020-08-01 | COMP | Other | 8 | 79 |  | 4 | 0 | 49 | 138
17237 | 2020-01-17 | 2020-02-05 | 2020-04-11 | 2020-04-11 | COMP | 2020-04-20 | COMP | 2020-05-19 | COMP | 2020-04-21 | COMP | 2020-06-08 | COMP | Rule 16 | 13 | 47 | 6 | 22 | 0 | 14 | 99
17305 | 2020-01-17 | 2020-02-07 | 2020-11-15 | 2020-11-15 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2023-05-10 | COMP | 2023-05-09 | COMP | Rule 16 | 15 | 197 | 6 | 1 | 618 |  | 833
17538 | 2020-01-17 | 2020-02-19 | 2020-06-18 | 2020-11-04 | COMP | 2021-01-05 | COMP | 2021-03-11 | COMP | 2021-06-25 | COMP | 2022-10-07 | COMP | Rule 15/16 | 22 | 86 | 40 | 46 | 76 | 325 | 688
17577 | 2020-01-17 | 2020-02-20 | 2020-04-20 | 2020-04-20 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-05-07 | COMP | 2020-06-05 | COMP | Rule 16 | 23 | 43 | 5 | 1 | 10 | 21 | 98
17849 | 2020-01-17 | 2020-03-02 | 2020-04-22 | 2020-04-22 | COMP | 2020-06-19 | COMP | 2020-06-19 | COMP | 2020-06-22 | COMP | 2020-08-03 | COMP | Rule 15/16 | 30 | 38 | 42 | 1 | 2 | 31 | 139
17887 | 2020-01-17 | 2020-03-02 | 2020-11-25 | 2021-09-03 | COMP | 2022-09-29 | COMP | 2022-03-09 | COMP | 2022-03-24 | COMP | 2022-05-12 | COMP | Rule 15 | 30 | 190 | 270 |  | 12 | 36 | 586
18010 | 2020-01-17 | 2020-03-09 | 2020-06-04 | 2020-06-04 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2021-01-25 | COMP | 2021-03-04 | COMP | Rule 16 | 35 | 63 | 73 | 1 | 89 | 28 | 284
18046 | 2020-01-17 | 2020-03-09 | 2020-06-24 | 2020-09-28 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-11-01 | COMP | 2020-11-30 | COMP | Rule 16 | 35 | 77 | 12 | 1 | 14 | 18 | 220
18576 | 2020-01-17 | 2020-03-30 | 2020-12-08 | 2020-12-08 | COMP | 2021-03-19 | COMP | 2021-07-14 | COMP | 2021-07-19 | COMP | 2021-10-19 | COMP | Rule 15/16 | 50 | 177 | 70 | 82 | 4 | 66 | 444
18585 | 2020-01-17 | 2020-03-30 | 2020-04-28 | 2020-04-28 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2021-01-05 | COMP | 2021-01-06 | COMP | Rule 16 | 50 | 22 | 44 | 1 | 131 | 2 | 245
18703 | 2020-01-17 | 2020-04-03 | 2020-06-30 | 2020-06-30 | COMP | 2020-08-12 | COMP | 2020-10-28 | COMP | 2020-11-02 | COMP | 2020-11-23 | COMP | Rule 15/16 | 54 | 62 | 32 | 55 | 4 | 15 | 217
18711 | 2020-01-17 | 2020-04-03 | 2020-08-19 | 2021-07-14 | COMP | 2021-07-23 | COMP | 2021-07-23 | COMP | 2023-02-25 | INPR | 2021-08-23 | COMP | Rule 16 | 54 | 98 | 8 | 1 |  |  | 404
18901 | 2020-01-17 | 2020-04-10 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-19 | COMP | 2020-06-22 | COMP | 2020-06-23 | COMP | 2020-08-07 | COMP | Rule 16 | 59 | 45 | 6 | 2 | 2 | 34 | 143
19041 | 2020-01-17 | 2020-04-20 | 2020-09-11 | 2020-09-11 | COMP | 2020-09-18 | COMP | 2020-10-22 | COMP | 2020-09-04 | COMP | 2020-11-06 | COMP | Rule 16 | 65 | 103 | 6 | 25 | 0 | 12 | 207
19058 | 2020-01-17 | 2020-04-20 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-14 | COMP | 2021-01-22 | COMP | 2021-01-27 | COMP | 2021-03-01 | COMP | Rule 16 | 65 | 48 | 37 | 109 | 4 | 23 | 281
19286 | 2020-01-17 | 2020-04-28 | 2020-06-09 | 2020-07-13 | COMP | 2020-07-31 | COMP | 2020-08-03 | COMP | 2020-09-21 | COMP | 2021-01-14 | COMP | Rule 15/16 | 71 | 30 | 15 | 2 | 35 | 79 | 251
19848 | 2020-01-17 | 2020-05-26 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-08-24 | COMP | 2020-10-01 | COMP | Rule 16 | 90 | 36 | 21 | 1 | 10 | 28 | 181
21505 | 2020-01-17 | 2020-08-10 | 2020-10-14 | 2020-10-14 | COMP | 2020-10-19 | COMP | 2021-02-22 | COMP | 2021-07-21 | COMP | 2021-09-17 | COMP | Rule 16 | 144 | 47 | 4 | 84 | 106 | 42 | 422
22018 | 2020-01-17 | 2020-09-08 | 2020-10-13 | 2020-10-13 | COMP | 2021-11-08 | COMP | 2022-06-17 | COMP | 2022-12-30 | COMP | 2023-02-09 | COMP | Rule 16 | 164 | 26 | 270 | 154 | 134 | 28 | 771
25659 | 2020-01-17 | 2021-02-19 | 2021-04-05 | 2021-04-05 | COMP | 2021-05-04 | COMP | 2021-07-06 | COMP | 2021-07-15 | COMP | 2021-09-10 | COMP | Rule 16 | 275 | 32 | 22 | 44 | 8 | 41 | 417
17982 | 2020-01-18 | 2020-03-06 | 2020-06-23 | 2020-06-23 | COMP | 2020-06-23 | NOTN | 2020-08-04 | COMP | 2020-07-03 | NOTN | 2020-10-14 | COMP | Other | 33 | 77 |  | 31 |  |  | 189
18291 | 2020-01-18 | 2020-03-18 | 2020-06-19 | 2020-06-30 | COMP | 2020-07-06 | COMP | 2020-08-13 | COMP | 2020-08-05 | COMP | 2020-10-21 | COMP | Rule 16 | 41 | 67 | 5 | 29 | 0 | 49 | 194
19431 | 2020-01-18 | 2020-05-06 | 2020-07-15 | 2020-07-15 | COMP | 2020-08-28 | COMP | 2020-09-21 | COMP | 2021-10-05 | COMP | 2021-11-04 | COMP | Rule 16 | 76 | 50 | 33 | 16 | 262 | 23 | 455
17559 | 2020-01-20 | 2020-02-20 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-07 | COMP | 2020-08-18 | COMP | 2020-10-22 | COMP | 2020-11-23 | COMP | Rule 16 | 22 | 101 | 21 | 8 | 47 | 22 | 216
17681 | 2020-01-20 | 2020-02-24 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-09 | COMP | 2020-12-22 | NOTN | 2020-12-16 | COMP | 2021-01-05 | COMP | Rule 16 | 24 | 62 | 15 |  |  |  | 243
18066 | 2020-01-20 | 2020-03-10 | 2020-04-23 | 2020-04-23 | COMP | 2020-05-04 | COMP | 2020-07-20 | COMP | 2020-09-21 | COMP | 2020-10-06 | COMP | Rule 16 | 35 | 33 | 8 | 55 | 45 | 12 | 183
18411 | 2020-01-20 | 2020-03-23 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2024-03-02 | INPR | 2020-08-04 | COMP | Rule 16 | 44 | 47 | 4 | 1 |  |  | 139
18741 | 2020-01-20 | 2020-04-06 | 2020-08-18 | 2020-08-18 | COMP | 2020-08-26 | COMP | 2020-09-25 | COMP | 2020-11-04 | COMP | 2020-11-06 | COMP | Rule 16 | 54 | 96 | 7 | 22 | 29 | 3 | 206
19213 | 2020-01-20 | 2020-04-23 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-24 | COMP | 2021-05-07 | COMP | 2021-09-13 | COMP | 2021-11-12 | COMP | Rule 15/16 | 67 | 39 | 28 | 198 | 89 | 44 | 460
19387 | 2020-01-20 | 2020-05-04 | 2020-09-15 | 2021-07-01 | COMP | 2021-06-18 | NOTN | 2020-10-22 | COMP | 2023-11-13 | INPR | 2021-08-13 | COMP | Rule 16 | 74 | 95 |  |  |  |  | 397
19552 | 2020-01-20 | 2020-05-12 | 2020-06-19 | 2020-06-19 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-08-11 | COMP | 2020-09-14 | COMP | Rule 15/16 | 80 | 28 | 32 | 1 | 7 | 24 | 167
19680 | 2020-01-20 | 2020-05-18 | 2020-07-07 | 2020-07-07 | COMP | 2020-08-31 | COMP | 2021-03-11 | COMP | 2021-07-06 | COMP | 2021-06-30 | COMP | Rule 16 | 84 | 36 | 40 | 131 | 82 |  | 366
19758 | 2020-01-20 | 2020-05-20 | 2020-10-09 | 2020-10-09 | COMP | 2021-03-25 | COMP | 2021-12-30 | COMP | 2021-12-30 | COMP | 2022-01-15 | COMP | Rule 15/16 | 86 | 101 | 113 | 195 | 1 | 12 | 503
16902 | 2020-01-21 | 2020-01-23 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-16 | COMP | 2020-03-16 | COMP | 2020-04-21 | COMP | 2020-11-23 | COMP | Rule 16 | 3 | 24 | 14 | 1 | 27 | 152 | 216
16915 | 2020-01-21 | 2020-01-24 | 2020-03-15 | 2020-03-15 | COMP | 2020-04-01 | COMP | 2020-05-01 | COMP | 2020-06-02 | COMP | 2020-06-16 | COMP | Rule 16 | 4 | 35 | 13 | 23 | 22 | 11 | 104
16937 | 2020-01-21 | 2020-01-25 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-01 | NOTN | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-09-29 | COMP | Other | 4 | 86 |  | 4 | 1 | 86 | 178
17036 | 2020-01-21 | 2020-01-28 | 2020-02-14 | 2020-02-14 | COMP | 2020-02-25 | COMP | 2020-02-25 | INPR | 2022-01-30 | REQD | 2020-09-18 | COMP | Rule 16 | 6 | 14 | 7 |  |  |  | 171
17040 | 2020-01-21 | 2020-01-28 | 2020-05-08 | 2020-05-21 | COMP | 2020-05-22 | NOTN | 2020-07-14 | COMP | 2020-07-28 | COMP | 2020-08-19 | COMP | Other | 6 | 73 |  | 38 | 11 | 17 | 150
17301 | 2020-01-21 | 2020-02-08 | 2020-08-25 | 2020-08-25 | COMP | 2023-12-30 | INPR | 2020-09-09 | COMP | 2020-11-10 | COMP | 2020-12-10 | COMP | Rule 15/16 | 14 | 140 |  | 11 | 45 | 20 | 227
17314 | 2020-01-21 | 2020-02-10 | 2020-04-15 | 2020-04-15 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-07-28 | COMP | 2020-09-15 | COMP | Rule 16 | 15 | 47 | 45 | 1 | 30 | 35 | 168
17414 | 2020-01-21 | 2020-02-13 | 2020-05-22 | 2020-05-22 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2022-03-04 | COMP | 2022-05-19 | COMP | Rule 15/16 | 18 | 71 | 102 | 1 | 348 | 55 | 590
17563 | 2020-01-21 | 2020-02-20 | 2020-04-20 | 2020-04-20 | COMP | 2020-04-30 | COMP | 2020-05-27 | COMP | 2022-07-30 | INPR | 2020-07-02 | COMP | Rule 16 | 22 | 43 | 9 | 19 |  |  | 116
17706 | 2020-01-21 | 2020-02-24 | 2020-04-16 | 2020-04-16 | COMP | 2020-04-28 | COMP | 2020-05-08 | COMP | 2020-04-28 | COMP | 2020-06-01 | COMP | Rule 16 | 24 | 39 | 9 | 9 | 0 | 16 | 93
17782 | 2020-01-21 | 2020-02-26 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-17 | COMP | 2020-03-17 | COMP | 2021-04-24 | INPR | 2020-04-15 | COMP | Rule 16 | 26 | 11 | 5 | 1 |  |  | 61
17842 | 2020-01-21 | 2020-03-02 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-11-25 | COMP | 2020-12-05 | COMP | Rule 16 | 29 | 74 | 21 | 1 | 97 | 6 | 223
17929 | 2020-01-21 | 2020-03-04 | 2020-07-26 | 2020-07-26 | COMP | 2020-07-31 | COMP | 2020-08-25 | COMP | 2020-10-02 | COMP | 2020-10-05 | COMP | Rule 16 | 31 | 102 | 5 | 18 | 28 | 2 | 182
17981 | 2020-01-21 | 2020-03-06 | 2020-05-08 | 2020-05-08 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP | 2020-12-18 | COMP | 2021-01-26 | COMP | Rule 16 | 33 | 46 | 28 | 1 | 129 | 25 | 257
18034 | 2020-01-21 | 2020-03-09 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2021-02-08 | COMP | 2021-03-05 | COMP | Rule 16 | 34 | 39 | 24 | 1 | 172 | 19 | 284
18065 | 2020-01-21 | 2020-03-10 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-20 | COMP | 2020-08-23 | COMP | 2020-10-29 | COMP | 2020-12-10 | COMP | Rule 16 | 35 | 70 | 25 | 25 | 48 | 28 | 227
18370 | 2020-01-21 | 2020-03-21 | 2020-05-21 | 2020-05-21 | COMP | 2020-08-06 | COMP | 2021-02-12 | COMP | 2021-02-12 | COMP | 2021-03-17 | COMP | Rule 16 | 43 | 44 | 55 | 130 | 1 | 23 | 292
18416 | 2020-01-21 | 2020-03-23 | 2020-07-02 | 2020-07-02 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2021-02-17 | COMP | 2021-03-17 | COMP | Rule 16 | 44 | 73 | 43 | 1 | 115 | 21 | 292
18568 | 2020-01-21 | 2020-03-28 | 2020-08-13 | 2020-08-13 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-01-11 | COMP | 2021-02-11 | COMP | Rule 16 | 48 | 98 | 33 | 1 | 70 | 23 | 269
18620 | 2020-01-21 | 2020-03-31 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-02 | COMP | 2020-08-05 | COMP | 2020-07-29 | COMP | 2020-09-02 | COMP | Rule 16 | 50 | 38 | 30 | 25 | 0 | 21 | 160
18810 | 2020-01-21 | 2020-04-07 | 2020-11-23 | 2020-11-23 | COMP | 2021-04-22 | COMP | 2021-06-07 | COMP | 2022-07-16 | INPR | 2021-06-14 | COMP | Rule 16 | 55 | 162 | 103 | 32 |  |  | 354
18829 | 2020-01-21 | 2020-04-08 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2020-06-29 | COMP | 2020-08-05 | COMP | Rule 16 | 56 | 21 | 7 | 1 | 32 | 28 | 140
19219 | 2020-01-21 | 2020-04-24 | 2020-09-16 | 2020-09-16 | COMP | 2020-12-29 | COMP | 2020-12-29 | COMP | 2021-09-14 | COMP | 2021-10-30 | COMP | Rule 16 | 68 | 102 | 71 | 1 | 180 | 34 | 451
19262 | 2020-01-21 | 2020-04-29 | 2020-09-25 | 2020-09-25 | COMP | 2020-10-01 | COMP | 2020-10-07 | COMP | 2022-01-31 | INPR | 2020-12-02 | COMP | Rule 16 | 71 | 106 | 5 | 5 |  |  | 221
19642 | 2020-01-21 | 2020-05-15 | 2020-08-14 | 2020-08-14 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2020-10-23 | COMP | 2020-12-31 | COMP | Rule 16 | 83 | 65 | 48 | 1 | 3 | 46 | 241
19643 | 2020-01-21 | 2020-05-15 | 2020-11-05 | 2020-11-05 | COMP | 2020-12-22 | COMP | 2021-02-18 | COMP | 2021-03-15 | COMP | 2021-04-19 | COMP | Rule 16 | 83 | 123 | 31 | 39 | 18 | 26 | 315
19686 | 2020-01-21 | 2020-05-18 | 2020-08-12 | 2020-08-12 | COMP | 2021-03-08 | NOTN | 2021-03-08 | COMP | 2021-03-08 | NOTN | 2021-04-15 | COMP | Rule 16 | 84 | 62 |  | 141 |  |  | 313
20050 | 2020-01-21 | 2020-06-02 | 2020-07-26 | 2020-07-26 | COMP | 2020-09-03 | COMP | 2020-09-25 | COMP | 2020-10-09 | COMP | 2020-11-05 | COMP | Rule 16 | 94 | 39 | 29 | 16 | 11 | 20 | 205
20276 | 2020-01-21 | 2020-06-12 | 2020-07-14 | 2020-07-14 | COMP | 2020-11-02 | COMP | 2020-11-03 | COMP | 2020-11-16 | COMP | 2020-12-22 | COMP | Rule 16 | 102 | 23 | 79 | 2 | 9 | 25 | 235
20345 | 2020-01-21 | 2020-06-16 | 2020-09-19 | 2021-01-25 | COMP | 2021-04-01 | COMP | 2020-12-09 | COMP | 2020-12-16 | COMP | 2021-04-14 | COMP | Rule 16 | 104 | 68 | 48 |  | 6 | 82 | 312
20580 | 2020-01-21 | 2020-06-27 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2022-07-16 | INPR | 2021-03-03 | COMP | Rule 16 | 112 | 10 | 30 | 1 |  |  | 282
20800 | 2020-01-21 | 2020-07-07 | 2020-09-15 | 2020-10-09 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2020-11-18 | COMP | 2020-12-18 | COMP | Rule 16 | 119 | 50 | 7 | 1 | 22 | 21 | 233
20827 | 2020-01-21 | 2020-07-09 | 2020-09-15 | 2020-09-15 | COMP | 2020-10-05 | COMP | 2021-05-19 | COMP | 2021-06-08 | COMP | 2021-07-12 | COMP | Rule 16 | 121 | 48 | 15 | 156 | 14 | 24 | 373
16910 | 2020-01-22 | 2020-01-22 | 2020-01-24 | 2020-01-28 | COMP | 2020-02-05 | COMP | 2020-02-05 | COMP | 2020-02-25 | COMP | 2020-03-03 | COMP | Rule 16 | 1 | 3 | 7 | 1 | 14 | 6 | 29
17035 | 2020-01-22 | 2020-01-28 | 2020-02-26 | 2020-02-26 | COMP | 2020-03-04 | COMP | 2020-04-20 | COMP |  | INPR | 2020-04-30 | COMP | Rule 16 | 5 | 21 | 6 | 34 |  |  | 71
17052 | 2020-01-22 | 2020-01-29 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-05-27 | COMP | 2020-06-26 | COMP | Rule 16 | 6 | 55 | 18 | 1 | 13 | 23 | 111
17433 | 2020-01-22 | 2020-02-13 | 2020-09-01 | 2020-09-23 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2020-10-26 | COMP | 2021-01-07 | COMP | Rule 15/16 | 17 | 142 | 4 | 1 | 21 | 49 | 244
17508 | 2020-01-22 | 2020-02-19 | 2020-06-16 | 2020-06-16 | COMP | 2020-08-24 | COMP | 2020-09-02 | COMP | 2020-08-24 | COMP | 2020-12-12 | COMP | Rule 15/16 | 20 | 84 | 50 | 8 | 0 | 69 | 227
17523 | 2020-01-22 | 2020-02-19 | 2020-04-10 | 2020-09-23 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-10-19 | COMP | 2020-11-10 | COMP | Rule 15/16 | 20 | 38 | 15 | 1 | 5 | 17 | 207
17537 | 2020-01-22 | 2020-02-19 | 2021-02-10 | 2021-02-10 | COMP | 2021-05-03 | COMP | 2021-05-29 | COMP | 2021-05-25 | COMP | 2021-08-07 | COMP | Rule 15/16 | 20 | 248 | 58 | 20 | 0 | 48 | 391
17594 | 2020-01-22 | 2020-02-20 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-16 | COMP | 2020-07-07 | COMP | 2020-07-21 | COMP | 2020-08-27 | COMP | Rule 16 | 21 | 78 | 6 | 16 | 11 | 28 | 155
17690 | 2020-01-22 | 2020-02-24 | 2020-06-17 | 2020-06-17 | COMP | 2020-12-08 | COMP | 2020-12-08 | COMP | 2023-11-13 | INPR | 2021-01-05 | COMP | Rule 16 | 23 | 82 | 121 | 1 |  |  | 242
17910 | 2020-01-22 | 2020-03-04 | 2020-04-28 | 2020-04-28 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-05-08 | COMP | 2020-06-08 | COMP | Rule 16 | 30 | 40 | 7 | 1 | 3 | 21 | 97
18047 | 2020-01-22 | 2020-03-09 | 2020-06-02 | 2020-06-10 | COMP | 2020-06-18 | COMP | 2020-10-13 | COMP | 2020-10-27 | COMP | 2020-11-13 | COMP | Rule 15/16 | 33 | 61 | 7 | 83 | 11 | 13 | 209
18053 | 2020-01-22 | 2020-03-09 | 2020-05-07 | 2020-05-07 | COMP | 2020-07-14 | COMP | 2020-07-24 | COMP | 2022-01-04 | COMP | 2022-03-28 | COMP | Rule 16 | 33 | 44 | 48 | 9 | 364 | 58 | 551
18327 | 2020-01-22 | 2020-03-19 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-05 | COMP | 2020-07-10 | COMP | 2020-08-07 | COMP | 2020-08-18 | COMP | Rule 16 | 41 | 49 | 8 | 26 | 21 | 8 | 148
18506 | 2020-01-22 | 2020-03-26 | 2020-05-31 | 2020-06-23 | COMP | 2020-10-19 | COMP | 2021-11-03 | COMP | 2020-06-29 | COMP | 2021-11-19 | COMP | Rule 16 | 46 | 46 | 84 | 263 | 0 | 12 | 464
18692 | 2020-01-22 | 2020-04-03 | 2020-05-14 | 2020-05-14 | COMP | 2021-03-19 | COMP | 2021-03-25 | COMP | 2021-05-04 | COMP | 2021-05-04 | COMP | Rule 16 | 52 | 30 | 213 | 5 | 29 | 1 | 325
18728 | 2020-01-22 | 2020-04-06 | 2020-10-05 | 2020-10-05 | COMP | 2020-12-09 | COMP | 2021-01-06 | COMP | 2021-05-03 | COMP | 2021-06-15 | COMP | Rule 16 | 53 | 129 | 45 | 19 | 82 | 31 | 354
18745 | 2020-01-22 | 2020-04-05 | 2020-06-11 | 2020-06-11 | COMP | 2021-02-23 | COMP | 2021-03-18 | COMP | 2022-01-26 | COMP | 2022-03-22 | COMP | Rule 16 | 52 | 48 | 176 | 18 | 218 | 39 | 547
18847 | 2020-01-22 | 2020-04-09 | 2020-08-16 | 2020-08-16 | COMP | 2020-09-21 | COMP | 2020-11-12 | COMP | 2020-12-04 | COMP | 2020-12-16 | COMP | Rule 15/16 | 56 | 91 | 25 | 38 | 15 | 9 | 230
19091 | 2020-01-22 | 2020-04-21 | 2020-09-17 | 2020-09-17 | COMP | 2020-11-05 | COMP | 2021-04-12 | COMP | 2021-04-06 | COMP | 2021-04-26 | COMP | Rule 16 | 64 | 106 | 36 | 106 | 0 | 11 | 319
19179 | 2020-01-22 | 2020-04-23 | 2020-05-12 | 2020-05-21 | COMP | 2020-05-27 | COMP | 2020-11-11 | COMP | 2023-04-02 | INPR | 2022-03-14 | COMP | Rule 16 | 66 | 14 | 4 | 119 |  |  | 541
19227 | 2020-01-22 | 2020-04-27 | 2020-09-04 | 2020-09-04 | COMP | 2020-10-22 | COMP | 2021-02-08 | COMP | 2021-01-07 | COMP | 2021-03-06 | COMP | Rule 16 | 68 | 94 | 34 | 72 | 0 | 19 | 283
19921 | 2020-01-22 | 2020-05-27 | 2020-07-03 | 2020-07-03 | COMP | 2020-07-15 | COMP | 2020-08-10 | NOTN | 2021-06-03 | COMP | 2021-06-11 | COMP | Rule 16 | 89 | 28 | 9 |  |  |  | 352
20138 | 2020-01-22 | 2020-06-08 | 2020-06-23 | 2020-06-23 | COMP | 2020-08-21 | COMP | 2020-09-10 | COMP | 2020-08-21 | COMP | 2020-10-02 | COMP | Rule 16 | 97 | 12 | 44 | 14 | 0 | 17 | 180
20307 | 2020-01-22 | 2020-06-15 | 2020-08-08 | 2020-08-08 | COMP | 2021-03-03 | COMP | 2021-03-03 | COMP | 2021-03-10 | COMP | 2021-03-26 | COMP | Rule 16 | 102 | 40 | 140 | 1 | 6 | 13 | 298
20483 | 2020-01-22 | 2020-06-23 | 2020-09-16 | 2020-09-16 | COMP | 2021-05-10 | COMP | 2021-05-13 | COMP | 2021-04-30 | COMP | 2021-07-21 | COMP | Rule 15/16 | 108 | 61 | 162 | 4 | 0 | 48 | 379
20554 | 2020-01-22 | 2020-06-25 | 2020-08-14 | 2020-08-14 | COMP | 2020-09-04 | COMP | 2021-06-03 | COMP | 2021-06-14 | COMP | 2021-06-24 | COMP | Rule 16 | 110 | 37 | 16 | 186 | 8 | 9 | 361
20656 | 2020-01-22 | 2020-06-30 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2020-09-03 | COMP | 2020-09-11 | COMP | Rule 16 | 113 | 30 | 11 | 1 | 9 | 6 | 165
4311 | 2020-01-23 | 2020-07-22 | 2020-07-29 | 2020-07-29 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-07-29 | COMP | 2020-09-11 | COMP | Rule 16 | 128 | 6 | 6 | 1 | 0 | 27 | 164
16919 | 2020-01-23 | 2020-01-23 | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | NOTN | 2020-05-27 | COMP | 2020-07-14 | NOTN | 2020-09-11 | COMP | Other | 1 | 88 |  | 1 |  |  | 164
16929 | 2020-01-23 | 2020-01-23 | 2020-05-21 | 2020-08-04 | COMP | 2020-05-21 | NOTN | 2020-08-04 | COMP | 2020-08-15 | COMP | 2020-10-21 | COMP | Other | 1 | 85 |  | 1 | 9 | 47 | 192
17042 | 2020-01-23 | 2020-01-28 | 2020-05-29 | 2022-04-18 | COMP | 2021-02-26 | NOTN | 2021-03-03 | COMP | 2023-12-03 | INPR | 2022-07-27 | COMP | Other | 4 | 87 |  |  |  |  | 634
17066 | 2020-01-23 | 2020-01-29 | 2020-07-21 | 2020-07-21 | COMP | 2020-07-29 | COMP | 2020-09-18 | COMP | 2020-09-19 | COMP | 2020-11-06 | COMP | Rule 15/16 | 5 | 123 | 7 | 37 | 1 | 35 | 204
17360 | 2020-01-23 | 2020-02-11 | 2020-08-19 | 2020-08-25 | COMP | 2021-02-09 | COMP | 2021-08-24 | COMP | 2021-08-30 | COMP | 2021-09-22 | COMP | Rule 15/16 | 14 | 135 | 114 | 138 | 5 | 17 | 422
17435 | 2020-01-23 | 2020-02-13 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2021-07-23 | COMP | 2021-09-29 | COMP | Rule 16 | 16 | 88 | 11 | 1 | 268 | 48 | 427
17456 | 2020-01-23 | 2020-02-13 | 2020-06-02 | 2020-06-02 | COMP | 2020-07-10 | COMP | 2020-08-04 | COMP | 2020-09-14 | COMP | 2020-11-12 | COMP | Rule 16 | 16 | 77 | 29 | 18 | 29 | 43 | 207
17770 | 2020-01-23 | 2020-02-26 | 2020-08-04 | 2020-08-04 | COMP | 2020-09-17 | COMP | 2020-11-09 | COMP | 2020-12-23 | COMP | 2021-02-10 | COMP | Rule 16 | 24 | 114 | 32 | 38 | 30 | 33 | 266
17906 | 2020-01-23 | 2020-03-03 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-30 | COMP | 2020-06-24 | COMP | 2020-08-07 | COMP | 2020-09-01 | COMP | Rule 16 | 28 | 25 | 19 | 39 | 33 | 18 | 157
18083 | 2020-01-23 | 2020-03-10 | 2020-05-07 | 2020-05-07 | COMP | 2020-08-10 | COMP | 2020-08-10 | COMP | 2021-01-05 | COMP | 2021-03-12 | COMP | Rule 16 | 33 | 43 | 67 | 1 | 101 | 47 | 287
18166 | 2020-01-23 | 2020-03-13 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-07 | COMP | 2020-08-04 | COMP | 2021-07-09 | COMP | 2021-09-29 | COMP | Rule 16 | 36 | 64 | 19 | 21 | 234 | 58 | 427
18173 | 2020-01-23 | 2020-03-13 | 2020-10-15 | 2020-12-28 | COMP | 2021-01-12 | COMP | 2021-06-14 | COMP | 2021-07-16 | COMP | 2021-11-03 | COMP | Rule 15/16 | 36 | 153 | 11 | 107 | 24 | 78 | 452
18635 | 2020-01-23 | 2020-04-01 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2020-06-02 | COMP | 2020-07-03 | COMP | Rule 16 | 49 | 28 | 5 | 1 | 13 | 24 | 115
18818 | 2020-01-23 | 2020-04-08 | 2020-05-27 | 2020-09-10 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2021-02-01 | COMP | 2021-04-01 | COMP | Rule 16 | 54 | 35 | 4 | 1 | 94 | 43 | 301
18820 | 2020-01-23 | 2020-04-08 | 2020-10-06 | 2020-10-06 | COMP | 2020-11-12 | COMP | 2020-11-30 | COMP | 2021-01-12 | COMP | 2021-01-26 | COMP | Rule 15/16 | 54 | 128 | 27 | 11 | 30 | 10 | 255
19143 | 2020-01-23 | 2020-04-22 | 2020-07-09 | 2020-07-09 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2020-09-01 | COMP | 2020-11-10 | COMP | Rule 16 | 64 | 56 | 80 | 1 | 0 | 9 | 206
19361 | 2020-01-23 | 2020-05-04 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-10 | NOTN | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-07-06 | COMP | Other | 72 | 17 |  | 11 | 1 | 19 | 116
19405 | 2020-01-23 | 2020-05-05 | 2020-07-06 | 2020-07-06 | COMP | 2020-09-11 | COMP | 2020-09-19 | COMP | 2020-12-15 | COMP | 2021-02-11 | COMP | Rule 15/16 | 73 | 44 | 49 | 6 | 59 | 40 | 267
19411 | 2020-01-23 | 2020-05-05 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-01 | COMP | 2020-08-21 | COMP | 2020-08-10 | COMP | 2020-09-30 | COMP | Rule 15/16 | 73 | 37 | 5 | 38 | 0 | 28 | 177
19508 | 2020-01-23 | 2020-05-11 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-10 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-04 | COMP | Rule 15/16 | 77 | 14 | 9 | 38 | 1 | 3 | 137
19525 | 2020-01-23 | 2020-05-11 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-23 | COMP | 2020-08-07 | COMP | 2020-09-22 | COMP | 2020-10-02 | COMP | Rule 16 | 77 | 19 | 13 | 34 | 32 | 9 | 179
19541 | 2020-01-23 | 2020-05-11 | 2020-06-05 | 2020-06-05 | COMP | 2020-07-07 | COMP | 2020-07-15 | COMP | 2020-08-10 | COMP | 2020-10-01 | COMP | Rule 16 | 77 | 19 | 23 | 7 | 19 | 38 | 178
20198 | 2020-01-23 | 2020-06-09 | 2020-07-20 | 2021-05-21 | COMP | 2021-10-21 | COMP | 2021-10-21 | NOTN | 2022-06-27 | COMP | 2022-07-19 | COMP | Rule 16 | 97 | 30 | 107 |  |  |  | 628
22184 | 2020-01-23 | 2020-09-14 | 2020-10-03 | 2020-10-03 | COMP | 2020-10-16 | COMP | 2020-10-27 | COMP | 2022-01-26 | COMP | 2022-02-23 | COMP | Rule 16 | 165 | 15 | 10 | 8 | 313 | 20 | 527
17293 | 2020-01-24 | 2020-02-07 | 2020-04-20 | 2020-07-17 | COMP | 2020-08-24 | COMP | 2020-10-01 | COMP | 2020-10-05 | COMP | 2020-10-27 | COMP | Rule 16 | 11 | 51 | 27 | 28 | 3 | 17 | 195
17303 | 2020-01-24 | 2020-02-08 | 2021-05-14 | 2021-05-14 | COMP | 2021-05-26 | COMP | 2021-11-03 | COMP | 2021-09-14 | COMP | 2021-12-23 | COMP | Rule 15/16 | 11 | 320 | 9 | 113 | 0 | 34 | 484
17483 | 2020-01-24 | 2020-02-18 | 2020-07-17 | 2020-07-17 | COMP | 2020-02-19 | NOTN | 2020-11-17 | COMP | 2020-02-19 | COMP | 2021-03-16 | COMP | Other | 17 | 108 |  | 86 | 0 | 80 | 288
17542 | 2020-01-24 | 2020-02-20 | 2020-05-27 | 2020-08-31 | COMP | 2020-09-16 | COMP | 2020-12-30 | COMP | 2020-12-30 | COMP | 2021-02-09 | COMP | Rule 15/16 | 19 | 69 | 12 | 72 | 1 | 28 | 264
17667 | 2020-01-24 | 2020-02-25 | 2020-05-07 | 2020-05-07 | COMP | 2020-02-25 | NOTN | 2020-05-07 | COMP | 2020-05-08 | COMP | 2020-06-17 | COMP | Other | 22 | 53 |  | 1 | 2 | 28 | 102
17738 | 2020-01-24 | 2020-02-26 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-10-20 | COMP | 2020-10-22 | COMP | Rule 16 | 23 | 61 | 16 | 1 | 93 | 3 | 192
17751 | 2020-01-24 | 2020-02-25 | 2020-06-10 | 2020-06-10 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2020-09-02 | COMP | 2020-10-10 | COMP | Rule 16 | 22 | 76 | 52 | 1 | 10 | 27 | 183
17844 | 2020-01-24 | 2020-03-02 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2021-04-13 | COMP | 2021-05-25 | COMP | Rule 16 | 26 | 65 | 5 | 1 | 215 | 31 | 338
17880 | 2020-01-24 | 2020-03-02 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-18 | COMP | 2020-07-14 | COMP | 2020-08-18 | COMP | 2020-09-24 | COMP | Rule 16 | 26 | 73 | 6 | 19 | 26 | 27 | 172
17917 | 2020-01-24 | 2020-03-03 | 2020-04-26 | 2020-04-26 | COMP | 2020-08-21 | COMP | 2020-09-18 | COMP | 2021-01-14 | COMP | 2021-02-10 | COMP | Rule 16 | 27 | 39 | 84 | 20 | 80 | 19 | 265
18104 | 2020-01-24 | 2020-03-11 | 2020-07-31 | 2020-07-31 | COMP | 2020-11-18 | COMP | 2020-11-19 | COMP | 2021-11-02 | COMP | 2021-11-02 | COMP | Other | 33 | 102 | 77 | 2 | 240 | 1 | 450
18192 | 2020-01-24 | 2020-03-14 | 2020-11-09 | 2020-11-09 | COMP | 2020-12-11 | COMP | 2020-12-11 | COMP | 2022-03-28 | COMP | 2022-03-28 | COMP | Rule 16 | 35 | 169 | 22 | 1 | 325 | 1 | 549
18480 | 2020-01-24 | 2020-03-27 | 2020-05-17 | 2020-05-17 | COMP | 2020-06-09 | NOTN | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-06-24 | COMP | Rule 16 | 45 | 36 |  | 16 | 1 | 12 | 107
19148 | 2020-01-24 | 2020-04-22 | 2020-05-27 | 2020-05-27 | COMP | 2020-12-21 | COMP | 2021-01-11 | COMP | 2021-04-27 | COMP | 2021-06-01 | COMP | Rule 16 | 63 | 25 | 145 | 14 | 75 | 25 | 342
19939 | 2020-01-24 | 2020-05-29 | 2020-10-09 | 2020-10-09 | COMP | 2020-10-21 | COMP | 2020-11-12 | COMP | 2021-02-08 | COMP | 2021-03-03 | COMP | Rule 16 | 89 | 95 | 9 | 16 | 58 | 17 | 279
24807 | 2020-01-24 | 2021-01-13 | 2021-03-13 | 2021-03-13 | COMP | 2021-03-30 | COMP | 2021-04-09 | COMP | 2021-05-11 | COMP | 2021-05-24 | COMP | Rule 16 | 246 | 41 | 12 | 9 | 23 | 10 | 337
26372 | 2020-01-24 | 2021-03-18 | 2021-06-17 | 2021-08-21 | COMP | 2021-09-30 | COMP | 2021-11-09 | COMP | 2021-11-10 | COMP | 2022-02-08 | COMP | Rule 15/16 | 290 | 65 | 28 | 29 | 2 | 61 | 516
16971 | 2020-01-25 | 2020-01-27 | 2020-06-17 | 2020-06-17 | COMP | 2020-06-18 | NOTN | 2020-06-24 | COMP | 2020-06-18 | COMP | 2020-09-16 | COMP | Other | 1 | 101 |  | 6 | 0 | 60 | 165
17022 | 2020-01-25 | 2020-01-28 | 2020-02-11 | 2020-02-19 | COMP | 2020-03-04 | COMP | 2020-03-10 | COMP | 2020-03-31 | COMP | 2020-03-30 | COMP | Rule 16 | 2 | 11 | 11 | 5 | 16 |  | 45
17218 | 2020-01-25 | 2020-02-05 | 2020-07-27 | 2020-07-27 | COMP | 2020-07-28 | NOTN | 2020-07-28 | COMP | 2020-08-04 | COMP | 2020-10-20 | COMP | Other | 8 | 122 |  | 2 | 6 | 55 | 189
17294 | 2020-01-25 | 2020-02-07 | 2020-05-14 | 2020-05-14 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2022-01-30 | INPR | 2020-06-25 | COMP | Rule 16 | 10 | 69 | 7 | 1 |  |  | 107
17505 | 2020-01-25 | 2020-02-19 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-15 | COMP | 2020-06-22 | COMP | 2020-11-17 | COMP | 2021-02-08 | COMP | Rule 15/16 | 17 | 79 | 5 | 6 | 105 | 55 | 262
19838 | 2020-01-25 | 2020-05-26 | 2020-09-23 | 2020-09-23 | COMP | 2020-10-13 | COMP | 2020-11-07 | COMP | 2021-01-13 | COMP | 2021-03-22 | COMP | Rule 16 | 85 | 86 | 15 | 19 | 43 | 47 | 291
17712 | 2020-01-26 | 2020-02-26 | 2020-07-08 | 2020-07-08 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2021-01-19 | COMP | 2021-03-17 | COMP | Rule 16 | 22 | 95 | 83 | 1 | 51 | 41 | 288
17737 | 2020-01-26 | 2020-02-26 | 2020-05-15 | 2020-12-16 | COMP | 2021-02-01 | COMP | 2021-05-11 | COMP | 2021-06-28 | COMP | 2021-08-31 | COMP | Rule 16 | 22 | 58 | 31 | 71 | 34 | 46 | 405
18072 | 2020-01-26 | 2020-03-10 | 2020-06-04 | 2020-06-30 | COMP | 2020-11-10 | COMP | 2020-08-10 | COMP | 2020-10-09 | COMP | 2020-09-18 | COMP | Rule 16 | 31 | 62 | 95 |  | 44 |  | 167
20242 | 2020-01-26 | 2020-06-11 | 2020-11-24 | 2020-11-24 | COMP | 2021-02-03 | COMP | 2021-02-03 | COMP | 2021-03-31 | COMP | 2021-04-29 | COMP | Rule 16 | 97 | 117 | 47 | 1 | 40 | 22 | 319
17011 | 2020-01-27 | 2020-01-27 | 2020-07-13 | 2020-07-23 | COMP | 2020-12-14 | COMP | 2021-09-09 | COMP | 2021-09-10 | COMP | 2021-09-30 | COMP | Rule 15/16 | 1 | 119 | 99 | 187 | 2 | 15 | 426
17017 | 2020-01-27 | 2020-01-27 | 2021-02-19 | 2021-02-19 | COMP | 2021-03-05 | NOTN | 2021-04-15 | COMP | 2021-08-04 | COMP | 2021-09-15 | COMP | Other | 1 | 270 |  | 40 | 78 | 30 | 415
17628 | 2020-01-27 | 2020-02-24 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-17 | COMP | 2020-09-17 | COMP | 2020-12-22 | COMP | 2021-02-24 | COMP | Rule 16 | 20 | 89 | 16 | 44 | 66 | 43 | 273
17724 | 2020-01-27 | 2020-02-25 | 2020-06-17 | 2020-06-17 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-08-10 | COMP | 2021-01-27 | COMP | Rule 16 | 21 | 81 | 53 | 1 | 0 | 102 | 254
18011 | 2020-01-27 | 2020-03-09 | 2020-07-02 | 2020-07-16 | COMP | 2020-07-24 | COMP | 2020-08-12 | COMP | 2020-08-10 | COMP | 2020-09-15 | COMP | Rule 16 | 30 | 83 | 7 | 14 | 0 | 24 | 164
18033 | 2020-01-27 | 2020-03-09 | 2020-03-24 | 2020-03-24 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-07-08 | COMP | 2020-07-07 | COMP | Rule 16 | 30 | 12 | 25 | 1 | 52 |  | 115
18079 | 2020-01-27 | 2020-03-10 | 2020-05-04 | 2020-09-10 | COMP | 2020-09-21 | COMP | 2020-06-25 | COMP | 2020-08-15 | COMP | 2020-10-29 | COMP | Rule 16 | 31 | 40 | 8 |  | 37 | 53 | 196
18136 | 2020-01-27 | 2020-03-12 | 2020-07-08 | 2020-08-25 | COMP | 2021-08-10 | COMP | 2022-03-07 | COMP | 2022-03-22 | COMP | 2022-04-14 | COMP | Rule 15/16 | 33 | 84 | 241 | 144 | 12 | 18 | 561
18137 | 2020-01-27 | 2020-03-12 | 2020-08-07 | 2021-05-28 | COMP | 2021-08-24 | COMP | 2022-06-08 | COMP | 2022-06-07 | COMP | 2022-08-22 | COMP | Rule 15/16 | 33 | 106 | 61 | 200 | 0 | 52 | 650
18557 | 2020-01-27 | 2020-03-28 | 2020-07-20 | 2020-07-20 | COMP | 2020-07-30 | COMP | 2020-08-17 | COMP | 2021-04-13 | COMP | 2021-05-25 | COMP | Rule 16 | 44 | 80 | 9 | 13 | 164 | 31 | 337
18727 | 2020-01-27 | 2020-04-05 | 2020-08-05 | 2020-08-05 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2021-02-18 | COMP | 2021-05-06 | COMP | Rule 16 | 49 | 87 | 45 | 1 | 90 | 56 | 324
18732 | 2020-01-27 | 2020-04-07 | 2021-01-06 | 2022-11-03 | COMP | 2022-11-07 | COMP | 2023-02-21 | COMP | 2023-02-14 | COMP | 2023-03-08 | COMP | Rule 15/16 | 51 | 190 | 3 | 70 | 0 | 12 | 784
18775 | 2020-01-27 | 2020-04-06 | 2020-07-07 | 2020-07-07 | COMP | 2020-08-31 | COMP | 2020-09-17 | COMP | 2021-01-26 | COMP | 2021-03-01 | COMP | Rule 16 | 50 | 66 | 40 | 13 | 88 | 24 | 276
18874 | 2020-01-27 | 2020-04-10 | 2020-07-20 | 2020-07-20 | COMP | 2020-08-17 | COMP | 2020-10-07 | COMP | 2020-12-02 | COMP | 2020-12-09 | COMP | Rule 16 | 54 | 71 | 21 | 37 | 38 | 6 | 222
19141 | 2020-01-27 | 2020-04-21 | 2020-05-22 | 2020-05-22 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-07-22 | COMP | 2020-08-28 | COMP | Rule 16 | 61 | 24 | 58 | 1 | 0 | 13 | 153
19167 | 2020-01-27 | 2020-04-23 | 2020-07-24 | 2020-07-24 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2020-10-05 | COMP | 2020-10-12 | COMP | Rule 16 | 63 | 66 | 20 | 1 | 32 | 6 | 183
19245 | 2020-01-27 | 2020-04-27 | 2020-08-02 | 2020-08-02 | COMP | 2020-08-18 | COMP | 2020-10-15 | COMP | 2020-12-08 | COMP | 2021-01-11 | COMP | Rule 16 | 65 | 69 | 12 | 42 | 36 | 23 | 243
19266 | 2020-01-27 | 2020-04-28 | 2020-07-23 | 2020-07-23 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-09-28 | COMP | 2020-10-19 | COMP | Rule 16 | 66 | 62 | 12 | 1 | 36 | 16 | 188
19485 | 2020-01-27 | 2020-05-08 | 2020-10-02 | 2020-10-02 | COMP | 2021-05-14 | COMP | 2021-05-14 | COMP | 2021-10-29 | COMP | 2021-11-17 | COMP | Rule 16 | 74 | 104 | 154 | 1 | 118 | 13 | 459
19532 | 2020-01-27 | 2020-05-11 | 2020-08-06 | 2020-09-03 | COMP | 2020-09-28 | COMP | 2020-10-09 | COMP | 2020-10-19 | COMP | 2020-12-18 | COMP | Rule 15/16 | 75 | 63 | 17 | 10 | 7 | 42 | 229
19648 | 2020-01-27 | 2020-05-16 | 2020-06-29 | 2020-07-14 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2020-11-25 | COMP | 2020-12-30 | COMP | Rule 16 | 79 | 30 | 93 | 1 | 3 | 23 | 236
19669 | 2020-01-27 | 2020-05-17 | 2020-08-12 | 2020-08-12 | COMP | 2020-11-16 | COMP | 2020-12-02 | COMP | 2020-11-09 | COMP | 2021-01-14 | COMP | Rule 16 | 79 | 62 | 67 | 11 | 0 | 30 | 246
20275 | 2020-01-27 | 2020-06-12 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-21 | COMP | 2020-09-10 | COMP | 2020-09-01 | COMP | 2020-09-28 | COMP | Rule 16 | 98 | 38 | 14 | 14 | 0 | 13 | 173
20326 | 2020-01-27 | 2020-06-16 | 2020-07-09 | 2020-07-09 | COMP | 2020-07-13 | COMP | 2020-08-06 | COMP | 2020-10-13 | COMP | 2020-11-19 | COMP | Rule 16 | 100 | 18 | 3 | 19 | 48 | 27 | 210
20356 | 2020-01-27 | 2020-06-17 | 2020-07-14 | 2020-07-14 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2022-05-10 | COMP | 2022-06-24 | COMP | Rule 16 | 101 | 20 | 53 | 1 | 408 | 32 | 610
20552 | 2020-01-27 | 2020-06-25 | 2020-11-04 | 2022-06-21 | COMP | 2022-09-19 | COMP | 2022-11-22 | COMP | 2022-12-05 | COMP | 2023-09-30 | COMP | Other | 107 | 94 | 63 | 46 | 8 | 207 | 927
20553 | 2020-01-27 | 2020-06-25 | 2020-10-21 | 2020-11-04 | COMP | 2022-03-23 | COMP | 2023-01-04 | COMP |  | INPR | 2023-07-25 | COMP | Other | 107 | 84 | 346 | 197 |  |  | 880
20882 | 2020-01-27 | 2020-07-10 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2022-01-31 | INPR | 2021-01-14 | COMP | Rule 16 | 118 | 22 | 12 | 1 |  |  | 246
21371 | 2020-01-27 | 2020-08-04 | 2020-11-10 | 2020-11-10 | COMP | 2020-11-20 | COMP | 2022-05-19 | COMP | 2023-08-07 | COMP | 2023-10-20 | COMP | Rule 16 | 135 | 70 | 8 | 376 | 304 | 54 | 942
22495 | 2020-01-27 | 2020-09-26 | 2020-11-04 | 2020-11-04 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2022-03-20 | INPR | 2021-03-08 | COMP | Rule 16 | 172 | 28 | 13 | 1 |  |  | 281
24062 | 2020-01-27 | 2020-12-08 | 2020-12-16 | 2020-12-16 | COMP | 2020-12-18 | NOTN | 2020-12-21 | COMP | 2020-12-18 | COMP | 2020-12-30 | COMP | Other | 221 | 7 |  | 4 | 0 | 7 | 236
17203 | 2020-01-28 | 2020-02-04 | 2020-05-28 | 2020-05-28 | COMP | 2020-05-28 | NOTN | 2020-06-02 | COMP | 2020-08-10 | COMP | 2021-03-31 | COMP | Other | 6 | 81 |  | 4 | 50 | 160 | 297
17267 | 2020-01-28 | 2020-02-06 | 2020-04-11 | 2020-12-23 | COMP | 2021-06-04 | COMP | 2021-06-07 | COMP | 2021-06-07 | COMP | 2021-07-19 | COMP | Rule 16 | 8 | 46 | 113 | 2 | 1 | 30 | 373
17346 | 2020-01-28 | 2020-02-10 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-01 | COMP | 2020-04-02 | COMP | 2020-06-11 | COMP | 2020-07-04 | COMP | Rule 16 | 10 | 25 | 13 | 2 | 50 | 17 | 112
17587 | 2020-01-28 | 2020-02-21 | 2020-07-02 | 2020-07-02 | COMP | 2020-07-07 | COMP | 2020-09-25 | COMP | 2020-10-28 | COMP | 2020-12-02 | COMP | Rule 16 | 18 | 94 | 4 | 58 | 24 | 23 | 216
17612 | 2020-01-28 | 2020-02-20 | 2020-05-26 | 2020-05-26 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2021-01-22 | COMP | 2021-02-13 | COMP | Rule 16 | 17 | 68 | 49 | 1 | 119 | 16 | 265
17639 | 2020-01-28 | 2020-02-24 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-29 | COMP | 2020-05-29 | COMP | 2020-05-28 | COMP | 2020-07-08 | COMP | Rule 16 | 19 | 51 | 19 | 1 | 0 | 29 | 115
17711 | 2020-01-28 | 2020-02-26 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-31 | COMP | 2020-04-06 | NOTN | 2020-10-14 | COMP | 2020-10-31 | COMP | Rule 16 | 21 | 14 | 12 |  |  |  | 196
17768 | 2020-01-28 | 2020-02-26 | 2020-04-08 | 2020-04-08 | COMP | 2020-04-17 | COMP | 2020-04-22 | COMP | 2020-07-06 | COMP | 2020-09-24 | COMP | Rule 16 | 21 | 31 | 8 | 4 | 53 | 58 | 170
18081 | 2020-01-28 | 2020-03-10 | 2020-06-26 | 2020-06-26 | COMP | 2020-06-26 | NOTN | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-08-28 | COMP | Other | 30 | 78 |  | 1 | 1 | 46 | 152
18324 | 2020-01-28 | 2020-03-19 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-25 | COMP | 2021-05-06 | COMP | 2021-05-12 | COMP | 2021-07-02 | COMP | Rule 16 | 37 | 37 | 77 | 175 | 5 | 37 | 363
18492 | 2020-01-28 | 2020-03-26 | 2020-10-09 | 2020-10-09 | COMP | 2020-11-09 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2020-12-23 | COMP | Rule 16 | 42 | 140 | 22 | 6 | 1 | 25 | 231
18589 | 2020-01-28 | 2020-03-30 | 2020-04-24 | 2020-04-24 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-08-12 | COMP | 2020-08-13 | COMP | Rule 16 | 44 | 20 | 68 | 1 | 11 | 2 | 141
18636 | 2020-01-28 | 2020-04-01 | 2020-07-03 | 2020-07-03 | COMP | 2020-08-20 | COMP | 2020-10-29 | COMP | 2020-11-24 | COMP | 2020-12-01 | COMP | Rule 16 | 46 | 67 | 35 | 50 | 18 | 4 | 215
18981 | 2020-01-28 | 2020-04-16 | 2020-11-13 | 2020-11-13 | COMP | 2021-04-02 | COMP | 2021-04-02 | COMP | 2021-08-23 | COMP | 2021-10-14 | COMP | Rule 16 | 57 | 149 | 95 | 1 | 100 | 38 | 435
19509 | 2020-01-28 | 2020-05-11 | 2020-06-10 | 2020-06-10 | COMP | 2020-06-24 | COMP | 2020-09-29 | COMP | 2021-05-24 | COMP | 2021-07-09 | COMP | Rule 16 | 74 | 22 | 11 | 69 | 163 | 33 | 367
19672 | 2020-01-28 | 2020-05-17 | 2020-06-04 | 2020-06-04 | COMP | 2020-06-29 | COMP | 2020-07-01 | COMP | 2020-07-26 | COMP | 2020-09-28 | COMP | Rule 16 | 78 | 13 | 18 | 3 | 18 | 45 | 172
19828 | 2020-01-28 | 2020-05-26 | 2020-08-19 | 2020-09-05 | COMP | 2020-09-10 | COMP | 2020-10-19 | COMP | 2020-10-20 | COMP | 2020-11-10 | COMP | Rule 16 | 84 | 62 | 3 | 28 | 2 | 16 | 203
19936 | 2020-01-28 | 2020-05-28 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-12 | COMP | 2020-07-13 | COMP | Rule 16 | 86 | 7 | 5 | 1 | 2 | 22 | 118
20158 | 2020-01-28 | 2020-06-08 | 2020-07-28 | 2020-07-28 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2021-03-02 | COMP | 2021-03-15 | COMP | Rule 16 | 93 | 37 | 52 | 1 | 97 | 10 | 285
20551 | 2020-01-28 | 2020-06-25 | 2020-10-21 | 2020-11-04 | COMP | 2021-09-15 | COMP | 2022-10-18 | COMP | 2022-09-23 | COMP | 2023-02-10 | COMP | Other | 106 | 84 | 216 | 276 | 0 | 78 | 766
20608 | 2020-01-28 | 2020-06-29 | 2020-09-11 | 2020-09-11 | COMP | 2021-03-10 | COMP | 2021-03-25 | COMP | 2021-05-12 | COMP | 2021-06-10 | COMP | Rule 16 | 108 | 54 | 122 | 12 | 35 | 21 | 347
21027 | 2020-01-28 | 2020-07-17 | 2020-08-17 | 2020-08-17 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2021-04-08 | COMP | 2021-05-19 | COMP | Rule 16 | 122 | 22 | 12 | 1 | 150 | 30 | 332
21297 | 2020-01-28 | 2020-08-01 | 2020-09-29 | 2020-09-29 | COMP | 2021-02-05 | COMP | 2021-02-18 | COMP | 2021-02-17 | COMP | 2021-05-07 | COMP | Rule 16 | 132 | 41 | 88 | 9 | 0 | 57 | 324
17169 | 2020-01-29 | 2020-02-03 | 2020-02-24 | 2020-02-26 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-02-27 | COMP | 2020-03-17 | COMP | Rule 16 | 4 | 15 | 2 | 1 | 1 | 14 | 34
17217 | 2020-01-29 | 2020-02-05 | 2020-08-20 | 2020-08-20 | COMP | 2021-01-14 | COMP | 2021-02-26 | COMP | 2021-02-25 | COMP | 2021-09-14 | COMP | Rule 15/16 | 6 | 140 | 100 | 30 | 0 | 140 | 412
17312 | 2020-01-29 | 2020-02-09 | 2020-04-24 | 2020-04-24 | COMP | 2020-04-24 | NOTN | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-06-30 | COMP | Other | 8 | 54 |  | 1 | 1 | 47 | 108
17354 | 2020-01-29 | 2020-02-10 | 2020-12-08 | 2020-12-08 | COMP | 2021-01-19 | COMP | 2021-03-11 | COMP | 2021-03-11 | COMP | 2021-03-22 | COMP | Rule 16 | 9 | 211 | 28 | 37 | 1 | 8 | 289
17885 | 2020-01-29 | 2020-03-03 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-05 | COMP | 2020-07-07 | COMP | 2020-08-19 | COMP | 2020-10-28 | COMP | Rule 16 | 24 | 57 | 12 | 23 | 32 | 50 | 193
17961 | 2020-01-29 | 2020-03-05 | 2020-05-07 | 2020-07-16 | COMP | 2020-08-06 | COMP | 2020-08-14 | COMP | 2021-11-29 | COMP | 2022-01-14 | COMP | Rule 15/16 | 26 | 46 | 16 | 7 | 323 | 35 | 497
18006 | 2020-01-29 | 2020-03-09 | 2020-04-02 | 2020-04-02 | COMP | 2020-03-18 | NOTN | 2020-04-02 | COMP | 2022-01-30 | INPR | 2020-11-02 | COMP | Rule 16 | 28 | 19 |  | 1 |  |  | 196
18054 | 2020-01-29 | 2020-03-09 | 2020-07-08 | 2020-07-08 | COMP | 2020-07-17 | COMP | 2020-09-03 | COMP | 2022-01-30 | INPR | 2020-11-30 | COMP | Rule 16 | 28 | 87 | 8 | 35 |  |  | 213
18410 | 2020-01-29 | 2020-03-23 | 2021-03-03 | 2021-07-30 | COMP | 2021-07-09 | NOTN | 2021-09-08 | COMP | 2021-03-16 | COMP | 2021-09-13 | COMP | Other | 38 | 239 |  | 28 | 0 | 4 | 411
18561 | 2020-01-29 | 2020-03-28 | 2020-07-20 | 2020-07-20 | COMP | 2022-01-06 | NOTN | 2022-09-07 | COMP | 2022-09-06 | COMP | 2023-05-12 | COMP | Other | 42 | 80 |  | 538 | 0 | 171 | 829
18713 | 2020-01-29 | 2020-04-03 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-29 | COMP | 2021-04-28 | COMP | 2021-04-12 | COMP | 2021-05-14 | COMP | Rule 16 | 47 | 55 | 7 | 210 | 0 | 13 | 328
19015 | 2020-01-29 | 2020-04-17 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-09-21 | COMP | 2020-09-29 | COMP | Rule 16 | 57 | 49 | 24 | 1 | 39 | 7 | 172
19343 | 2020-01-29 | 2020-05-01 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-25 | COMP | 2020-09-29 | COMP | 2020-07-27 | COMP | 2020-11-30 | COMP | Rule 16 | 67 | 61 | 22 | 25 | 0 | 42 | 213
19720 | 2020-01-29 | 2020-05-19 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-07-23 | COMP | 2020-09-29 | COMP | Rule 16 | 79 | 35 | 14 | 1 | 0 | 47 | 172
19734 | 2020-01-29 | 2020-05-20 | 2020-06-13 | 2020-06-13 | COMP | 2020-06-19 | COMP | 2020-07-17 | COMP | 2020-12-24 | COMP | 2021-02-02 | COMP | Rule 16 | 80 | 17 | 5 | 21 | 111 | 26 | 256
19764 | 2020-01-29 | 2020-05-20 | 2021-01-15 | 2021-01-15 | COMP | 2021-02-23 | COMP | 2021-02-23 | COMP | 2021-04-02 | COMP | 2021-05-12 | COMP | Rule 16 | 80 | 166 | 26 | 1 | 29 | 29 | 326
20146 | 2020-01-29 | 2020-06-08 | 2020-07-02 | 2020-07-16 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-13 | COMP | Rule 16 | 92 | 19 | 12 | 1 | 1 | 10 | 140
20311 | 2020-01-29 | 2020-06-15 | 2020-07-27 | 2020-07-27 | COMP | 2020-10-13 | COMP | 2021-04-20 | COMP | 2021-04-08 | COMP | 2021-05-07 | COMP | Rule 16 | 97 | 31 | 56 | 129 | 0 | 14 | 323
20332 | 2020-01-29 | 2020-06-16 | 2020-08-06 | 2020-08-06 | COMP | 2020-11-03 | COMP | 2020-10-16 | COMP | 2020-10-21 | COMP | 2021-04-11 | COMP | Rule 16 | 98 | 38 | 63 |  | 4 | 116 | 303
21009 | 2020-01-29 | 2020-07-18 | 2020-09-13 | 2020-09-13 | COMP | 2020-12-18 | COMP | 2021-01-15 | COMP | 2021-05-03 | COMP | 2021-05-10 | COMP | Rule 16 | 121 | 39 | 67 | 19 | 75 | 6 | 324
21613 | 2020-01-29 | 2020-08-15 | 2020-10-19 | 2020-10-19 | COMP | 2021-01-13 | COMP | 2021-02-17 | COMP | 2021-10-04 | COMP | 2021-10-15 | COMP | Other | 141 | 45 | 58 | 24 | 161 | 10 | 435
23165 | 2020-01-29 | 2020-10-27 | 2021-01-22 | 2021-01-22 | COMP | 2021-02-09 | COMP | 2021-07-16 | COMP | 2021-07-19 | COMP | 2021-08-17 | COMP | Rule 16 | 192 | 58 | 13 | 111 | 2 | 22 | 393
17236 | 2020-01-30 | 2020-02-05 | 2020-07-13 | 2020-07-13 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2021-03-16 | COMP | 2021-04-22 | COMP | Rule 16 | 5 | 112 | 54 | 1 | 116 | 28 | 311
17287 | 2020-01-30 | 2020-02-06 | 2020-03-11 | 2020-03-11 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-06-19 | COMP | 2020-09-01 | COMP | Rule 16 | 6 | 24 | 46 | 1 | 27 | 53 | 152
17296 | 2020-01-30 | 2020-02-07 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-13 | COMP | 2020-04-13 | COMP | 2020-04-22 | COMP | 2020-04-30 | COMP | Rule 16 | 7 | 44 | 3 | 1 | 8 | 7 | 65
17401 | 2020-01-30 | 2020-02-13 | 2020-05-11 | 2020-05-11 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-09-15 | COMP | 2020-09-30 | COMP | Rule 16 | 11 | 62 | 68 | 1 | 23 | 12 | 172
17629 | 2020-01-30 | 2020-02-24 | 2020-12-15 |  | INPR | 2021-04-12 | COMP | 2022-07-13 | COMP | 2022-12-07 | COMP | 2023-01-20 | COMP | Rule 15/16 | 17 |  |  |  | 102 | 30 | 749
17677 | 2020-01-30 | 2020-02-24 | 2020-04-17 | 2020-04-17 | COMP | 2020-04-23 | COMP | 2020-04-28 | COMP | 2020-05-15 | COMP | 2020-05-20 | COMP | Rule 15/16 | 17 | 40 | 5 | 4 | 14 | 4 | 79
17753 | 2020-01-30 | 2020-02-26 | 2020-05-15 | 2020-07-03 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2020-08-29 | COMP | 2020-10-21 | COMP | Rule 16 | 19 | 58 | 47 | 1 | 0 | 32 | 187
17831 | 2020-01-30 | 2020-02-28 | 2020-08-25 | 2020-08-25 | COMP | 2020-09-14 | COMP | 2020-09-23 | COMP | 2020-10-23 | COMP | 2020-11-09 | COMP | Rule 15/16 | 21 | 127 | 14 | 8 | 23 | 12 | 200
18087 | 2020-01-30 | 2020-03-10 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-08 | NOTN | 2020-12-09 | COMP | 2020-12-10 | COMP | 2021-02-11 | COMP | Other | 28 | 64 |  | 129 | 2 | 43 | 262
18182 | 2020-01-30 | 2020-03-13 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2021-06-16 | COMP | 2021-08-31 | COMP | Other | 31 | 77 | 21 | 1 | 223 | 54 | 402
18183 | 2020-01-30 | 2020-03-13 | 2020-12-10 | 2020-12-10 | COMP | 2020-12-18 | COMP | 2021-02-02 | COMP | 2021-02-05 | COMP | 2021-04-17 | COMP | Rule 16 | 31 | 190 | 7 | 30 | 4 | 50 | 307
18438 | 2020-01-30 | 2020-03-24 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-09 | COMP | 2021-01-07 | COMP | 2020-08-20 | COMP | 2021-03-16 | COMP | Rule 16 | 38 | 68 | 9 | 125 | 0 | 47 | 284
18519 | 2020-01-30 | 2020-03-27 | 2020-07-20 | 2020-07-20 | COMP | 2022-01-24 | COMP | 2022-01-24 | COMP | 2022-01-24 | COMP | 2022-03-04 | COMP | Rule 16 | 41 | 81 | 381 | 1 | 1 | 29 | 529
19331 | 2020-01-30 | 2020-04-30 | 2020-08-07 | 2020-08-07 | COMP | 2020-12-17 | COMP | 2020-12-17 | COMP | 2021-01-07 | COMP | 2021-03-03 | COMP | Rule 15/16 | 65 | 71 | 91 | 1 | 14 | 38 | 275
19332 | 2020-01-30 | 2020-04-30 | 2020-09-22 | 2020-09-22 | COMP | 2020-12-17 | COMP | 2021-01-06 | COMP | 2021-01-19 | COMP | 2021-03-13 | COMP | Rule 15/16 | 65 | 102 | 60 | 13 | 9 | 38 | 282
19338 | 2020-01-30 | 2020-05-01 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2022-05-28 | INPR | 2020-09-21 | COMP | Rule 16 | 66 | 21 | 20 | 1 |  |  | 165
19422 | 2020-01-30 | 2020-05-06 | 2020-08-16 | 2020-08-16 | COMP | 2020-09-30 | COMP | 2021-02-23 | COMP | 2021-06-09 | COMP | 2021-06-11 | COMP | Rule 16 | 69 | 72 | 32 | 98 | 76 | 3 | 346
19527 | 2020-01-30 | 2020-05-11 | 2020-07-27 | 2020-08-06 | COMP | 2020-09-23 | COMP | 2020-10-02 | COMP | 2021-04-27 | COMP | 2021-10-19 | COMP | Rule 16 | 72 | 55 | 34 | 8 | 141 | 123 | 436
19902 | 2020-01-30 | 2020-05-27 | 2020-06-23 | 2020-06-23 | COMP | 2020-06-29 | NOTN | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-07-28 | COMP | Other | 83 | 20 |  | 6 | 1 | 21 | 127
20701 | 2020-01-30 | 2020-07-02 | 2020-07-19 | 2020-07-19 | COMP | 2020-10-09 | NOTN | 2020-10-09 | INPR | 2020-08-29 | COMP | 2020-11-02 | COMP | Rule 16 | 109 | 12 |  |  |  |  | 195
20815 | 2020-01-30 | 2020-07-07 | 2021-03-04 | 2021-03-04 | COMP | 2022-01-25 | COMP | 2023-06-12 | COMP | 2023-08-28 | COMP | 2023-08-24 | COMP | Rule 15/16 | 112 | 165 | 227 | 347 | 54 |  | 899
21391 | 2020-01-30 | 2020-08-04 | 2020-11-05 | 2021-06-11 | COMP | 2021-08-13 | COMP | 2021-09-28 | COMP | 2021-11-02 | COMP | 2021-11-30 | COMP | Rule 15/16 | 132 | 67 | 45 | 32 | 26 | 18 | 463
21756 | 2020-01-30 | 2020-08-24 | 2020-10-30 | 2020-10-30 | COMP | 2020-11-05 | COMP | 2020-11-17 | COMP | 2021-02-11 | COMP | 2021-03-01 | COMP | Rule 16 | 146 | 49 | 5 | 8 | 58 | 12 | 273
17358 | 2020-01-31 | 2020-02-11 | 2020-04-14 | 2020-04-14 | COMP | 2020-07-31 | COMP | 2020-11-02 | COMP | 2021-02-01 | COMP | 2021-02-19 | COMP | Rule 16 | 8 | 45 | 78 | 66 | 60 | 14 | 266
17361 | 2020-01-31 | 2020-02-11 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-23 | COMP | 2020-03-23 | COMP | 2020-04-10 | COMP | 2020-04-29 | COMP | Rule 16 | 8 | 21 | 9 | 1 | 15 | 14 | 63
17395 | 2020-01-31 | 2020-02-12 | 2020-06-10 | 2020-06-10 | COMP | 2020-06-17 | COMP | 2021-01-21 | COMP | 2020-06-12 | COMP | 2021-02-19 | COMP | Rule 16 | 9 | 84 | 6 | 150 | 0 | 21 | 266
17657 | 2020-01-31 | 2020-02-24 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2020-07-07 | COMP | 2020-07-31 | COMP | Other | 16 | 82 | 14 | 1 | 2 | 19 | 129
17692 | 2020-01-31 | 2020-02-24 | 2020-10-01 | 2020-10-01 | COMP | 2020-11-12 | COMP | 2022-11-28 | COMP |  | INPR | 2023-07-26 | COMP | Rule 16 | 16 | 157 | 30 | 512 |  |  | 877
17702 | 2020-01-31 | 2020-02-25 | 2020-07-21 | 2020-07-21 | COMP | 2021-04-09 | COMP | 2021-06-11 | COMP | 2021-06-29 | COMP | 2021-08-26 | COMP | Rule 15/16 | 17 | 105 | 181 | 45 | 13 | 42 | 398
17974 | 2020-01-31 | 2020-03-06 | 2020-11-03 | 2020-11-03 | COMP | 2021-05-21 | COMP | 2021-11-02 | COMP | 2023-01-04 | COMP | 2023-06-22 | COMP | Rule 15/16 | 25 | 171 | 137 | 115 | 293 | 118 | 854
18036 | 2020-01-31 | 2020-03-09 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-11 | COMP | 2020-09-24 | COMP | 2020-11-25 | COMP | 2020-12-23 | COMP | Rule 15/16 | 26 | 39 | 30 | 75 | 44 | 19 | 228
18171 | 2020-01-31 | 2020-03-13 | 2020-05-14 | 2020-05-14 | COMP | 2020-07-28 | COMP | 2020-07-29 | COMP | 2020-07-28 | COMP | 2020-09-28 | COMP | Rule 16 | 30 | 45 | 53 | 2 | 0 | 43 | 169
18213 | 2020-01-31 | 2020-03-16 | 2020-12-22 | 2020-12-22 | COMP | 2022-07-12 | COMP | 2022-08-12 | COMP | 2022-08-16 | COMP | 2022-09-23 | COMP | Rule 16 | 31 | 197 | 391 | 24 | 3 | 28 | 669
18302 | 2020-01-31 | 2020-03-18 | 2020-06-22 | 2020-06-22 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-11-13 | COMP | 2021-03-18 | COMP | Rule 16 | 33 | 68 | 51 | 1 | 53 | 84 | 285
18476 | 2020-01-31 | 2020-03-25 | 2020-08-20 | 2020-08-20 | COMP | 2020-10-23 | NOTN | 2020-10-23 | COMP | 2020-11-30 | COMP | 2021-01-12 | COMP | Other | 38 | 106 |  | 46 | 24 | 30 | 240
18537 | 2020-01-31 | 2020-03-28 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-07-02 | COMP | Rule 16 | 40 | 40 | 7 | 1 | 1 | 22 | 108
18673 | 2020-01-31 | 2020-04-02 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-01 | NOTN | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-11-06 | COMP | Other | 44 | 56 |  | 62 | 1 | 39 | 198
18967 | 2020-01-31 | 2020-04-14 | 2020-06-08 | 2020-06-08 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-07-16 | COMP | 2020-08-06 | COMP | Rule 16 | 52 | 39 | 22 | 1 | 8 | 16 | 133
19067 | 2020-01-31 | 2020-04-20 | 2020-05-08 | 2020-05-08 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-08-06 | COMP | 2020-08-10 | COMP | Rule 16 | 56 | 15 | 50 | 1 | 15 | 3 | 135
19101 | 2020-01-31 | 2020-04-21 | 2020-09-10 | 2020-09-10 | COMP | 2020-09-14 | COMP | 2021-02-26 | COMP | 2021-03-02 | COMP | 2021-04-06 | COMP | Rule 16 | 57 | 101 | 3 | 113 | 3 | 26 | 298
19437 | 2020-01-31 | 2020-05-07 | 2020-07-20 | 2020-07-20 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2022-01-31 | INPR | 2020-10-08 | COMP | Rule 16 | 69 | 52 | 17 | 1 |  |  | 177
19522 | 2020-01-31 | 2020-05-11 | 2020-06-18 | 2020-06-18 | COMP | 2020-06-30 | COMP | 2020-07-10 | COMP | 2020-08-29 | COMP | 2021-01-05 | COMP | Rule 16 | 71 | 28 | 9 | 9 | 36 | 86 | 235
19534 | 2020-01-31 | 2020-05-11 | 2020-06-12 | 2020-06-12 | COMP | 2020-08-11 | COMP | 2020-08-14 | COMP | 2020-08-31 | COMP | 2020-10-13 | COMP | Rule 16 | 71 | 24 | 43 | 4 | 12 | 31 | 180
19644 | 2020-01-31 | 2020-05-15 | 2020-08-18 | 2020-08-18 | COMP | 2020-10-06 | COMP | 2020-10-06 | COMP | 2021-06-23 | COMP | 2021-07-12 | COMP | Rule 16 | 75 | 67 | 35 | 1 | 179 | 13 | 365
20642 | 2020-01-31 | 2020-06-29 | 2020-07-23 | 2020-07-23 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2020-08-21 | COMP | 2020-09-19 | COMP | Rule 16 | 105 | 19 | 21 | 1 | 2 | 20 | 163
22065 | 2020-01-31 | 2020-09-09 | 2020-09-29 | 2020-09-29 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-11-03 | COMP | 2020-11-29 | COMP | Rule 16 | 156 | 15 | 11 | 1 | 16 | 16 | 210
24817 | 2020-01-31 | 2021-01-13 | 2021-03-26 | 2021-03-26 | COMP | 2021-04-20 | COMP | 2021-12-29 | COMP | 2021-11-01 | COMP | 2022-02-16 | COMP | Rule 16 | 241 | 51 | 18 | 176 | 0 | 35 | 517
17221 | 2020-02-01 | 2020-02-05 | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | NOTN | 2020-05-27 | COMP | 2020-06-23 | COMP | 2020-11-02 | COMP | Other | 3 | 79 |  | 1 | 20 | 94 | 193
17220 | 2020-02-03 | 2020-02-05 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-09-25 | COMP | 2020-11-14 | COMP | Rule 16 | 3 | 74 | 3 | 1 | 90 | 35 | 201
17231 | 2020-02-03 | 2020-02-05 | 2020-02-26 | 2020-02-26 | COMP | 2020-04-09 | COMP | 2020-04-23 | COMP | 2020-06-09 | COMP | 2020-08-06 | COMP | Rule 16 | 3 | 15 | 32 | 11 | 33 | 43 | 132
17274 | 2020-02-03 | 2020-02-07 | 2020-03-02 | 2020-03-02 | COMP | 2020-04-06 | COMP | 2020-04-06 | COMP | 2022-07-16 | INPR | 2020-08-27 | COMP | Rule 16 | 5 | 16 | 26 | 1 |  |  | 147
17349 | 2020-02-03 | 2020-02-10 | 2020-03-15 | 2020-03-15 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-07-13 | COMP | 2020-08-07 | COMP | Rule 16 | 6 | 24 | 41 | 1 | 45 | 20 | 133
17643 | 2020-02-03 | 2020-02-24 | 2020-06-08 | 2021-01-20 | COMP | 2020-06-08 | NOTN | 2020-06-08 | COMP | 2020-10-28 | COMP | 2022-06-15 | COMP | Other | 15 | 75 |  |  | 102 | 410 | 599
17664 | 2020-02-03 | 2020-02-25 | 2020-05-04 | 2020-05-04 | COMP | 2020-08-17 | COMP | 2021-04-05 | COMP | 2021-08-04 | COMP | 2021-09-13 | COMP | Rule 15/16 | 16 | 50 | 75 | 158 | 86 | 28 | 408
17714 | 2020-02-03 | 2020-02-24 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2021-03-15 | COMP | 2021-04-05 | COMP | Rule 16 | 15 | 70 | 14 | 1 | 185 | 16 | 296
17848 | 2020-02-03 | 2020-03-02 | 2020-04-16 | 2020-04-16 | COMP | 2020-05-29 | COMP | 2020-06-16 | COMP | 2021-04-26 | COMP | 2021-05-15 | COMP | Rule 16 | 20 | 34 | 31 | 13 | 217 | 15 | 325
17877 | 2020-02-03 | 2020-03-02 | 2020-04-03 | 2020-04-03 | COMP | 2020-03-02 | NOTN | 2020-04-03 | COMP | 2020-05-05 | COMP | 2020-05-04 | COMP | Other | 20 | 25 |  | 1 | 23 |  | 65
17897 | 2020-02-03 | 2020-03-03 | 2020-12-01 | 2020-12-01 | COMP | 2020-12-07 | COMP | 2021-03-29 | COMP | 2021-03-17 | COMP | 2021-04-12 | COMP | Rule 15/16 | 21 | 191 | 5 | 77 | 0 | 11 | 301
17924 | 2020-02-03 | 2020-03-04 | 2020-04-13 | 2022-05-06 | COMP | 2022-05-10 | COMP | 2020-04-24 | COMP | 2022-06-27 | COMP | 2022-08-04 | COMP | Rule 16 | 22 | 29 | 3 |  | 548 | 28 | 633
17967 | 2020-02-03 | 2020-03-05 | 2020-03-15 | 2020-03-16 | COMP | 2020-03-19 | COMP | 2020-03-19 | COMP | 2021-10-23 | INPR | 2020-04-15 | COMP | Rule 16 | 23 | 7 | 4 | 1 |  |  | 52
18169 | 2020-02-03 | 2020-03-13 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2020-06-02 | COMP | 2020-06-17 | COMP | Rule 16 | 29 | 41 | 9 | 1 | 9 | 12 | 96
18284 | 2020-02-03 | 2020-03-19 | 2020-04-26 | 2020-04-26 | COMP | 2020-05-13 | COMP | 2020-05-01 | COMP | 2020-05-14 | COMP | 2020-05-19 | COMP | Rule 15/16 | 33 | 27 | 13 |  | 10 | 4 | 76
18368 | 2020-02-03 | 2020-03-20 | 2020-04-09 | 2020-04-09 | COMP | 2020-08-11 | COMP | 2020-08-13 | NOTN | 2020-08-12 | COMP | 2020-08-19 | COMP | Rule 16 | 34 | 15 | 88 |  |  |  | 141
18412 | 2020-02-03 | 2020-03-23 | 2020-06-18 | 2020-12-19 | COMP | 2020-12-28 | COMP | 2020-07-09 | COMP | 2021-02-25 | COMP | 2021-03-25 | COMP | Rule 16 | 35 | 63 | 5 |  | 158 | 21 | 289
18446 | 2020-02-03 | 2020-03-24 | 2020-10-12 | 2020-10-12 | COMP | 2020-10-21 | COMP | 2020-12-08 | COMP | 2021-01-25 | COMP | 2021-03-20 | COMP | Rule 15/16 | 36 | 143 | 8 | 32 | 32 | 39 | 285
18793 | 2020-02-03 | 2020-04-07 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-02 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-08-05 | COMP | Rule 16 | 46 | 33 | 30 | 10 | 1 | 16 | 131
18803 | 2020-02-03 | 2020-04-07 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-09-01 | COMP | 2020-09-24 | COMP | Rule 16 | 46 | 40 | 4 | 1 | 63 | 17 | 166
18918 | 2020-02-03 | 2020-04-12 | 2020-07-09 | 2020-09-10 | COMP | 2020-09-24 | COMP | 2020-10-05 | COMP | 2021-01-13 | COMP | 2021-03-18 | COMP | Rule 16 | 49 | 63 | 11 | 8 | 68 | 45 | 284
18923 | 2020-02-03 | 2020-04-13 | 2020-07-08 | 2020-07-08 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | 2020-09-28 | COMP | 2020-10-06 | COMP | Rule 16 | 50 | 62 | 36 | 1 | 23 | 7 | 174
19014 | 2020-02-03 | 2020-04-17 | 2021-03-29 | 2021-03-29 | COMP | 2021-06-07 | COMP | 2022-01-24 | COMP | 2022-02-23 | COMP | 2022-08-26 | COMP | Rule 15/16 | 54 | 238 | 50 | 160 | 22 | 130 | 649
19052 | 2020-02-03 | 2020-04-19 | 2021-03-10 | 2021-03-10 | COMP | 2021-04-02 | COMP | 2021-06-18 | COMP | 2022-06-28 | COMP | 2022-07-23 | COMP | Rule 15/16 | 54 | 224 | 18 | 55 | 259 | 18 | 624
19076 | 2020-02-03 | 2020-04-20 | 2020-05-01 | 2020-05-01 | COMP | 2020-05-19 | COMP | 2020-08-14 | NOTN | 2020-08-12 | COMP | 2020-08-19 | COMP | Rule 16 | 55 | 10 | 13 |  |  |  | 141
19155 | 2020-02-03 | 2020-04-23 | 2020-07-27 | 2020-09-11 | COMP | 2020-11-10 | COMP | 2020-11-10 | COMP | 2020-11-12 | COMP | 2021-01-07 | COMP | Rule 16 | 58 | 67 | 43 | 1 | 2 | 37 | 236
19420 | 2020-02-03 | 2020-05-06 | 2020-07-13 | 2020-07-13 | COMP | 2020-07-28 | COMP | 2020-08-14 | COMP | 2020-07-28 | COMP | 2020-11-05 | COMP | Rule 16 | 67 | 48 | 12 | 14 | 0 | 59 | 196
19560 | 2020-02-03 | 2020-05-12 | 2020-07-24 | 2020-07-24 | COMP | 2020-07-29 | COMP | 2020-08-17 | COMP | 2020-10-14 | COMP | 2021-01-07 | COMP | Rule 16 | 71 | 53 | 4 | 14 | 42 | 57 | 236
19697 | 2020-02-03 | 2020-05-18 | 2020-08-17 | 2021-06-09 | COMP | 2021-09-09 | COMP | 2022-03-25 | COMP |  |  | 2022-04-11 | COMP | Rule 16 | 75 | 65 | 65 | 137 |  |  | 553
19938 | 2020-02-03 | 2020-05-29 | 2020-10-28 | 2020-10-28 | COMP | 2020-10-28 | NOTN | 2020-12-13 | COMP | 2020-12-23 | COMP | 2021-04-14 | COMP | Other | 83 | 108 |  | 30 | 8 | 77 | 303
20272 | 2020-02-03 | 2020-06-12 | 2020-12-18 | 2020-12-18 | COMP | 2021-04-15 | COMP | 2021-04-15 | COMP | 2021-06-03 | COMP | 2021-06-07 | COMP | Rule 16 | 93 | 132 | 81 | 1 | 35 | 3 | 340
20491 | 2020-02-03 | 2020-06-23 | 2020-08-27 | 2020-08-27 | COMP | 2020-09-02 | COMP | 2020-09-02 | COMP | 2021-12-15 | COMP | 2021-12-27 | COMP | Rule 16 | 100 | 48 | 5 | 1 | 322 | 9 | 480
21098 | 2020-02-03 | 2020-07-21 | 2020-11-05 | 2020-11-21 | COMP | 2020-12-09 | COMP | 2021-02-25 | COMP | 2021-04-07 | COMP | 2021-04-16 | COMP | Rule 16 | 120 | 77 | 11 | 53 | 30 | 8 | 305
21460 | 2020-02-03 | 2020-08-08 | 2020-11-10 | 2021-03-16 | COMP | 2021-03-31 | COMP | 2021-03-31 | COMP | 2021-04-01 | COMP | 2021-04-26 | COMP | Rule 15/16 | 133 | 66 | 12 | 1 | 2 | 18 | 311
23511 | 2020-02-03 | 2020-11-09 | 2021-02-02 | 2021-02-02 | COMP | 2021-02-09 | COMP | 2021-03-24 | COMP | 2021-04-09 | COMP | 2021-05-11 | COMP | Rule 16 | 198 | 56 | 6 | 31 | 13 | 23 | 322
17336 | 2020-02-04 | 2020-02-10 | 2020-03-16 | 2020-03-16 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-06-06 | COMP | 2020-06-17 | COMP | Rule 16 | 5 | 25 | 18 | 1 | 42 | 8 | 95
17409 | 2020-02-04 | 2020-02-12 | 2020-04-17 | 2020-06-25 | COMP | 2020-04-17 | NOTN | 2020-07-20 | COMP | 2020-04-22 | COMP | 2020-10-03 | COMP | Other | 7 | 47 |  | 18 | 0 | 54 | 171
17489 | 2020-02-04 | 2020-02-18 | 2020-06-26 | 2021-03-12 | COMP | 2021-03-12 | NOTN | 2021-03-12 | COMP | 2021-05-14 | COMP | 2021-06-18 | COMP | Rule 15/16 | 10 | 93 |  | 1 | 46 | 25 | 348
17490 | 2020-02-04 | 2020-02-18 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-17 | COMP | 2020-09-30 | COMP | 2020-11-13 | COMP | 2020-12-09 | COMP | Rule 16 | 10 | 100 | 9 | 53 | 32 | 17 | 216
17568 | 2020-02-04 | 2020-02-20 | 2020-03-25 | 2020-03-25 | COMP | 2020-03-26 | NOTN | 2020-05-28 | COMP | 2022-01-30 | INPR | 2020-12-03 | COMP | Other | 12 | 25 |  | 46 |  |  | 212
17616 | 2020-02-04 | 2020-02-21 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2023-04-30 | INPR | 2021-10-08 | COMP | Rule 16 | 13 | 59 | 22 | 1 |  |  | 426
17662 | 2020-02-04 | 2020-02-24 | 2020-05-30 | 2020-05-30 | COMP | 2020-06-09 | COMP | 2020-08-03 | COMP | 2020-07-28 | COMP | 2020-09-14 | COMP | Rule 16 | 14 | 69 | 7 | 40 | 0 | 30 | 157
17757 | 2020-02-04 | 2020-02-26 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-19 | NOTN | 2020-09-04 | COMP | 2020-06-18 | COMP | 2020-10-21 | COMP | Other | 16 | 82 |  | 56 | 0 | 33 | 184
17861 | 2020-02-04 | 2020-03-02 | 2020-03-09 | 2020-03-09 | COMP | 2020-04-03 | COMP | 2020-04-06 | COMP | 2020-04-23 | COMP | 2020-05-20 | COMP | Rule 16 | 19 | 6 | 20 | 2 | 14 | 20 | 76
18088 | 2020-02-04 | 2020-03-10 | 2020-07-16 | 2020-07-16 | COMP | 2020-08-06 | COMP | 2020-08-17 | COMP | 2020-09-15 | COMP | 2020-12-12 | COMP | Rule 15/16 | 25 | 92 | 16 | 8 | 21 | 61 | 218
18193 | 2020-02-04 | 2020-03-14 | 2020-12-28 | 2020-12-28 | COMP | 2021-01-19 | COMP | 2021-11-10 | COMP | 2023-12-03 | INPR | 2021-12-09 | COMP | Rule 16 | 28 | 200 | 15 | 208 |  |  | 467
18209 | 2020-02-04 | 2020-03-16 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-09 | COMP | 2020-09-02 | COMP | 2020-10-01 | COMP | 2020-11-02 | COMP | Rule 16 | 29 | 71 | 13 | 40 | 21 | 23 | 192
18271 | 2020-02-04 | 2020-03-18 | 2020-04-09 | 2020-04-09 | COMP | 2021-02-03 | COMP | 2021-02-04 | COMP | 2021-02-04 | COMP | 2021-02-22 | COMP | Rule 16 | 31 | 17 | 207 | 2 | 1 | 12 | 265
18691 | 2020-02-04 | 2020-04-04 | 2020-08-25 | 2020-08-25 | COMP | 2020-08-31 | COMP | 2021-04-08 | COMP | 2021-03-29 | COMP | 2021-04-15 | COMP | Rule 16 | 43 | 101 | 5 | 151 | 0 | 6 | 303
18752 | 2020-02-04 | 2020-04-06 | 2020-12-11 | 2020-12-11 | COMP | 2021-01-04 | COMP | 2021-04-20 | COMP | 2021-12-06 | COMP | 2022-01-31 | COMP | Rule 15/16 | 44 | 175 | 15 | 75 | 159 | 40 | 503
18756 | 2020-02-04 | 2020-04-06 | 2020-12-11 | 2020-12-16 | COMP | 2021-05-14 | COMP | 2021-10-20 | COMP | 2021-09-30 | COMP | 2022-01-31 | COMP | Rule 15/16 | 44 | 175 | 104 | 111 | 0 | 70 | 503
18771 | 2020-02-04 | 2020-04-06 | 2020-05-08 | 2020-05-08 | COMP | 2020-08-21 | COMP | 2020-09-15 | COMP | 2020-08-21 | COMP | 2020-10-11 | COMP | Rule 16 | 44 | 25 | 75 | 17 | 0 | 19 | 176
18772 | 2020-02-04 | 2020-04-06 | 2020-12-11 | 2020-12-11 | COMP | 2021-01-15 | COMP | 2021-09-03 | COMP | 2021-09-07 | COMP | 2022-01-31 | COMP | Rule 15/16 | 44 | 175 | 24 | 162 | 2 | 101 | 503
18854 | 2020-02-04 | 2020-04-09 | 2020-06-12 | 2020-06-12 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2021-05-27 | COMP | 2021-11-17 | COMP | Rule 16 | 47 | 46 | 39 | 1 | 204 | 121 | 453
18926 | 2020-02-04 | 2020-04-13 | 2020-06-23 | 2020-06-23 | COMP | 2020-08-24 | COMP | 2020-11-30 | COMP | 2020-12-01 | COMP | 2021-01-12 | COMP | Rule 16 | 49 | 51 | 45 | 67 | 2 | 29 | 238
18980 | 2020-02-04 | 2020-04-16 | 2020-05-13 | 2020-05-13 | COMP | 2020-07-15 | COMP | 2020-07-29 | COMP | 2020-07-22 | COMP | 2020-09-01 | COMP | Rule 16 | 52 | 20 | 45 | 11 | 0 | 25 | 149
18990 | 2020-02-04 | 2020-04-16 | 2020-08-17 | 2020-08-17 | COMP | 2021-04-28 | COMP | 2021-07-13 | COMP | 2020-08-20 | COMP | 2021-08-31 | COMP | Rule 16 | 52 | 87 | 175 | 53 | 0 | 36 | 399
19081 | 2020-02-04 | 2020-04-20 | 2022-07-06 | 2022-07-06 | COMP | 2022-07-14 | COMP | 2022-09-15 | COMP |  | INPR | 2023-02-10 | COMP | Rule 15/16 | 54 | 558 | 7 | 45 |  |  | 761
19132 | 2020-02-04 | 2020-04-21 | 2020-08-14 | 2020-08-14 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2021-06-28 | COMP | 2021-07-08 | COMP | Rule 16 | 55 | 83 | 72 | 1 | 147 | 8 | 361
19154 | 2020-02-04 | 2020-04-22 | 2020-05-27 | 2020-05-27 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-09-08 | COMP | 2020-10-06 | COMP | Rule 16 | 56 | 25 | 68 | 1 | 7 | 21 | 173
19459 | 2020-02-04 | 2020-05-07 | 2020-08-11 | 2020-08-11 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2020-10-29 | COMP | 2021-01-08 | COMP | Rule 16 | 67 | 68 | 22 | 1 | 36 | 47 | 236
19520 | 2020-02-04 | 2020-05-11 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-14 | COMP | 2020-10-15 | COMP | 2021-09-14 | COMP | 2021-10-14 | COMP | Rule 16 | 69 | 80 | 10 | 24 | 229 | 23 | 430
19524 | 2020-02-04 | 2020-05-11 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-08-04 | COMP | 2020-11-05 | COMP | Rule 16 | 69 | 19 | 14 | 1 | 30 | 67 | 195
19622 | 2020-02-04 | 2020-05-15 | 2020-10-26 | 2020-10-26 | COMP | 2021-03-02 | COMP | 2021-03-02 | COMP | 2022-08-19 | COMP | 2022-11-17 | COMP | Rule 15/16 | 73 | 115 | 85 | 1 | 373 | 63 | 705
19654 | 2020-02-04 | 2020-05-16 | 2020-10-19 | 2020-10-19 | COMP | 2020-10-30 | COMP | 2020-11-17 | COMP | 2020-12-03 | COMP | 2021-02-24 | COMP | Rule 16 | 73 | 109 | 10 | 12 | 11 | 56 | 267
19812 | 2020-02-04 | 2020-05-22 | 2020-09-25 | 2020-09-25 | COMP | 2020-11-03 | COMP | 2021-01-07 | COMP | 2021-01-20 | COMP | 2021-01-21 | COMP | Rule 16 | 78 | 89 | 28 | 43 | 9 | 2 | 244
19813 | 2020-02-04 | 2020-05-22 | 2020-09-23 | 2020-09-23 | COMP | 2020-11-03 | COMP | 2020-11-03 | INPR | 2021-01-08 | COMP | 2021-01-21 | COMP | Rule 16 | 78 | 87 | 30 |  |  |  | 244
19851 | 2020-02-04 | 2020-05-26 | 2020-07-24 | 2021-03-23 | COMP | 2021-04-19 | COMP | 2021-06-14 | COMP | 2021-03-30 | COMP | 2022-01-25 | COMP | Rule 15/16 | 79 | 44 | 20 | 40 | 0 | 156 | 499
19852 | 2020-02-04 | 2020-05-26 | 2020-07-11 | 2021-03-30 | COMP | 2021-05-03 | COMP | 2021-06-23 | COMP | 2021-03-30 | COMP | 2021-10-14 | COMP | Rule 16 | 79 | 34 | 25 | 37 | 0 | 80 | 430
19853 | 2020-02-04 | 2020-05-26 | 2020-09-25 | 2021-03-21 | COMP | 2021-04-16 | COMP | 2021-08-12 | COMP | 2021-03-24 | COMP | 2022-04-29 | COMP | Rule 16 | 79 | 88 | 20 | 83 | 0 | 181 | 566
19933 | 2020-02-04 | 2020-05-28 | 2020-07-03 | 2020-07-03 | COMP | 2020-08-06 | COMP | 2021-03-09 | COMP | 2021-03-23 | COMP | 2021-06-11 | COMP | Rule 16 | 81 | 27 | 25 | 146 | 11 | 58 | 343
19995 | 2020-02-04 | 2020-06-01 | 2020-08-25 | 2020-08-25 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2020-12-15 | COMP | 2021-03-21 | COMP | Other | 83 | 62 | 59 | 1 | 19 | 65 | 284
20033 | 2020-02-04 | 2020-06-01 | 2020-08-06 | 2020-08-06 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2023-01-27 | COMP | 2023-03-02 | COMP | Rule 16 | 83 | 49 | 33 | 1 | 589 | 24 | 774
20437 | 2020-02-04 | 2020-06-20 | 2020-08-02 | 2020-08-02 | COMP | 2021-03-12 | COMP | 2021-04-05 | COMP | 2021-05-10 | COMP | 2021-05-21 | COMP | Rule 16 | 97 | 30 | 152 | 17 | 26 | 10 | 329
21625 | 2020-02-04 | 2020-08-17 | 2020-09-16 | 2020-09-16 | COMP | 2020-09-22 | COMP | 2020-11-17 | COMP | 2020-12-22 | COMP | 2021-01-08 | COMP | Rule 16 | 138 | 22 | 5 | 40 | 24 | 12 | 236
21874 | 2020-02-04 | 2020-08-31 | 2020-11-06 | 2020-11-06 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP | 2021-02-22 | COMP | 2021-03-19 | COMP | Rule 16 | 148 | 49 | 60 | 1 | 11 | 20 | 284
22585 | 2020-02-04 | 2020-10-01 | 2020-12-14 | 2020-12-14 | COMP | 2021-06-25 | COMP | 2021-07-19 | COMP | 2022-08-09 | COMP | 2022-08-25 | COMP | Rule 16 | 170 | 50 | 135 | 16 | 268 | 13 | 647
22912 | 2020-02-04 | 2020-10-16 | 2021-02-11 | 2021-02-11 | COMP | 2021-03-08 | COMP | 2021-03-11 | COMP | 2021-02-25 | COMP | 2021-04-07 | COMP | Rule 16 | 181 | 79 | 17 | 4 | 0 | 20 | 297
23985 | 2020-02-04 | 2020-12-04 | 2021-02-03 | 2021-02-03 | COMP | 2022-04-04 | COMP | 2022-04-04 | COMP | 2022-04-26 | COMP | 2022-06-12 | COMP | Other | 213 | 41 | 295 | 1 | 17 | 33 | 595
17290 | 2020-02-05 | 2020-02-07 | 2020-04-16 | 2020-04-16 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-07-05 | COMP | 2020-07-16 | COMP | Rule 16 | 3 | 49 | 56 | 1 | 1 | 9 | 115
17463 | 2020-02-05 | 2020-02-14 | 2020-04-20 | 2020-04-20 | COMP | 2020-04-23 | COMP | 2020-04-23 | COMP | 2020-05-11 | COMP | 2020-06-01 | COMP | Rule 16 | 8 | 46 | 4 | 1 | 13 | 15 | 82
17605 | 2020-02-05 | 2020-02-21 | 2020-03-17 | 2020-03-31 | COMP | 2020-03-17 | NOTN | 2020-03-31 | COMP | 2020-03-17 | COMP | 2020-05-08 | COMP | Other | 12 | 18 |  | 1 | 0 | 29 | 67
17614 | 2020-02-05 | 2020-02-21 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-24 | COMP | 2020-05-08 | COMP | 2020-06-09 | COMP | 2020-07-23 | COMP | Rule 16 | 12 | 20 | 27 | 11 | 22 | 33 | 120
17679 | 2020-02-05 | 2020-02-24 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-22 | COMP | 2021-01-08 | COMP | 2021-01-08 | COMP | 2021-02-26 | COMP | Rule 16 | 13 | 76 | 10 | 139 | 1 | 34 | 268
17717 | 2020-02-05 | 2020-02-25 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2020-04-09 | COMP | 2020-05-03 | COMP | Rule 16 | 14 | 34 | 5 | 1 | 0 | 12 | 62
17723 | 2020-02-05 | 2020-02-25 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-24 | COMP | 2020-09-11 | COMP | 2021-10-23 | INPR | 2020-10-12 | COMP | Rule 16 | 14 | 75 | 12 | 57 |  |  | 176
17862 | 2020-02-05 | 2020-03-02 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-02 | COMP | 2020-07-17 | COMP | 2021-06-08 | COMP | 2021-07-09 | COMP | Rule 16 | 18 | 59 | 30 | 12 | 224 | 23 | 361
17919 | 2020-02-05 | 2020-03-04 | 2020-11-02 | 2020-11-02 | COMP | 2021-01-19 | COMP | 2021-10-07 | COMP | 2021-09-11 | COMP | 2022-02-04 | COMP | Rule 15/16 | 20 | 172 | 51 | 184 | 0 | 83 | 506
18012 | 2020-02-05 | 2020-03-09 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-18 | COMP | 2020-05-20 | COMP | 2020-06-02 | COMP | 2020-06-17 | COMP | Rule 16 | 23 | 39 | 13 | 3 | 9 | 12 | 94
18059 | 2020-02-05 | 2020-03-10 | 2020-05-31 | 2020-05-31 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-07-27 | COMP | 2020-08-28 | COMP | Rule 16 | 24 | 58 | 42 | 1 | 0 | 24 | 146
18138 | 2020-02-05 | 2020-03-12 | 2020-08-07 | 2022-05-12 | COMP | 2022-05-23 | COMP | 2022-06-07 | COMP | 2022-06-07 | COMP | 2022-08-22 | COMP | Rule 15/16 | 26 | 106 | 8 | 11 | 1 | 53 | 643
18203 | 2020-02-05 | 2020-03-16 | 2020-07-28 | 2020-07-28 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2023-05-02 | COMP | 2023-05-22 | COMP | Rule 16 | 28 | 96 | 93 | 1 | 602 | 15 | 830
18433 | 2020-02-05 | 2020-03-24 | 2020-04-15 | 2020-04-15 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-06-03 | COMP | 2020-07-06 | COMP | Rule 16 | 34 | 17 | 18 | 1 | 18 | 24 | 107
18650 | 2020-02-05 | 2020-04-01 | 2021-04-08 | 2021-04-08 | COMP | 2021-07-06 | COMP | 2021-07-06 | COMP | 2021-07-14 | COMP | 2021-09-25 | COMP | Rule 15/16 | 40 | 258 | 62 | 1 | 7 | 52 | 415
18781 | 2020-02-05 | 2020-04-07 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-28 | COMP | 2020-08-20 | COMP | 2021-03-26 | COMP | 2021-05-27 | COMP | Rule 16 | 44 | 48 | 33 | 18 | 149 | 45 | 332
18860 | 2020-02-05 | 2020-04-09 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-25 | COMP | 2020-06-29 | COMP | 2020-07-09 | COMP | 2020-09-21 | COMP | Rule 16 | 46 | 51 | 5 | 3 | 9 | 52 | 161
19000 | 2020-02-05 | 2020-04-16 | 2020-06-04 | 2020-08-03 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2020-08-26 | COMP | 2020-11-30 | COMP | Rule 16 | 51 | 35 | 41 | 1 | 0 | 42 | 208
19009 | 2020-02-05 | 2020-04-17 | 2020-06-10 | 2020-06-10 | COMP | 2020-08-07 | COMP | 2020-08-15 | COMP | 2020-12-08 | COMP | 2021-01-07 | COMP | Rule 16 | 52 | 38 | 43 | 6 | 78 | 21 | 234
19211 | 2020-02-05 | 2020-04-24 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-10-05 | COMP | 2020-12-07 | COMP | Rule 16 | 57 | 46 | 9 | 1 | 62 | 43 | 213
19281 | 2020-02-05 | 2020-04-29 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-05 | COMP | 2020-06-05 | COMP | 2020-08-11 | COMP | 2020-08-28 | COMP | Rule 16 | 60 | 19 | 9 | 1 | 48 | 14 | 146
19360 | 2020-02-05 | 2020-05-02 | 2020-07-28 | 2020-07-28 | COMP | 2020-11-10 | COMP | 2020-11-10 | COMP | 2020-11-06 | COMP | 2020-12-08 | COMP | Rule 16 | 62 | 61 | 75 | 1 | 0 | 18 | 214
19705 | 2020-02-05 | 2020-05-19 | 2020-09-10 | 2020-09-10 | COMP | 2021-03-08 | NOTN | 2021-03-08 | COMP | 2021-03-08 | NOTN | 2021-04-17 | COMP | Other | 74 | 81 |  | 121 |  |  | 303
20349 | 2020-02-05 | 2020-06-17 | 2020-07-10 | 2020-07-10 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-09-16 | COMP | 2020-11-10 | COMP | Rule 16 | 94 | 18 | 11 | 1 | 38 | 40 | 197
21852 | 2020-02-05 | 2020-08-31 | 2020-10-28 | 2020-10-28 | COMP | 2020-11-12 | NOTN | 2021-10-15 | COMP | 2021-10-15 | COMP | 2022-02-04 | COMP | Other | 147 | 42 |  | 243 | 1 | 77 | 506
17704 | 2020-02-06 | 2020-02-25 | 2020-07-08 | 2020-07-08 | COMP | 2020-08-13 | COMP | 2020-10-15 | COMP | 2021-03-02 | COMP | 2021-04-02 | COMP | Rule 16 | 13 | 96 | 27 | 45 | 92 | 24 | 292
17742 | 2020-02-06 | 2020-02-25 | 2020-06-17 | 2020-06-30 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2021-05-03 | COMP | 2021-06-30 | COMP | Rule 16 | 13 | 81 | 59 | 1 | 154 | 42 | 354
17744 | 2020-02-06 | 2020-02-25 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-08-11 | COMP | 2020-08-27 | COMP | Rule 15/16 | 13 | 88 | 11 | 1 | 23 | 13 | 144
17761 | 2020-02-06 | 2020-02-26 | 2020-03-14 | 2020-03-14 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-07-09 | COMP | 2020-08-03 | COMP | Rule 16 | 14 | 13 | 30 | 1 | 54 | 18 | 126
18069 | 2020-02-06 | 2020-03-11 | 2020-05-17 | 2020-05-17 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-06-30 | COMP | 2020-08-14 | COMP | Rule 16 | 24 | 48 | 33 | 1 | 0 | 32 | 135
18201 | 2020-02-06 | 2020-03-16 | 2020-07-23 | 2020-07-23 | COMP | 2020-08-10 | COMP | 2020-09-04 | COMP | 2020-09-23 | COMP | 2020-10-22 | COMP | Rule 15/16 | 27 | 93 | 13 | 20 | 13 | 22 | 183
18413 | 2020-02-06 | 2020-03-23 | 2020-06-15 | 2020-08-11 | COMP | 2020-09-22 | COMP | 2020-09-28 | COMP | 2020-10-14 | COMP | 2020-12-02 | COMP | Rule 16 | 32 | 60 | 30 | 5 | 13 | 33 | 209
18456 | 2020-02-06 | 2020-03-25 | 2020-06-16 | 2020-10-20 | COMP | 2020-11-18 | COMP | 2021-01-15 | COMP | 2020-11-19 | COMP | 2021-04-06 | COMP | Rule 16 | 34 | 59 | 21 | 39 | 0 | 56 | 294
18524 | 2020-02-06 | 2020-03-27 | 2020-09-03 | 2020-09-03 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-09-22 | COMP | 2020-10-14 | COMP | Rule 16 | 36 | 114 | 8 | 1 | 6 | 17 | 177
18530 | 2020-02-06 | 2020-03-27 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-12 | COMP | 2020-05-12 | COMP | 2020-12-15 | COMP | 2021-01-01 | COMP | Rule 16 | 36 | 19 | 15 | 1 | 151 | 12 | 229
18559 | 2020-02-06 | 2020-03-28 | 2020-07-17 | 2020-07-17 | COMP | 2020-09-30 | NOTN | 2020-09-30 | COMP | 2020-10-13 | COMP | 2021-02-03 | COMP | Other | 36 | 79 |  | 53 | 10 | 76 | 251
18743 | 2020-02-06 | 2020-04-07 | 2020-07-17 | 2020-07-17 | COMP | 2020-07-27 | COMP | 2020-09-24 | COMP | 2020-11-20 | COMP | 2021-02-20 | COMP | Rule 16 | 43 | 73 | 7 | 43 | 41 | 60 | 262
18801 | 2020-02-06 | 2020-04-07 | 2020-05-26 | 2020-05-26 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2020-11-10 | COMP | 2020-12-16 | COMP | Rule 16 | 43 | 35 | 90 | 1 | 31 | 24 | 219
19048 | 2020-02-06 | 2020-04-19 | 2020-07-23 | 2020-07-23 | COMP | 2020-08-13 | COMP | 2021-03-20 | COMP | 2022-11-02 | COMP | 2022-12-13 | COMP | Other | 51 | 68 | 16 | 149 | 411 | 27 | 719
19114 | 2020-02-06 | 2020-04-21 | 2020-06-28 | 2020-06-28 | COMP | 2020-07-06 | COMP | 2020-07-06 | NOTN | 2020-07-06 | COMP | 2020-07-31 | COMP | Rule 16 | 53 | 48 | 6 |  |  |  | 125
19272 | 2020-02-06 | 2020-04-29 | 2020-06-23 | 2020-06-23 | COMP | 2020-06-26 | COMP | 2020-06-26 | COMP | 2020-09-04 | COMP | 2020-10-13 | COMP | Rule 15/16 | 59 | 39 | 4 | 1 | 51 | 27 | 176
19774 | 2020-02-06 | 2020-05-21 | 2020-06-12 | 2020-06-12 | COMP | 2020-12-17 | COMP | 2020-12-17 | COMP | 2021-08-24 | COMP | 2021-09-20 | COMP | Rule 16 | 75 | 16 | 131 | 1 | 173 | 19 | 410
19949 | 2020-02-06 | 2020-05-29 | 2020-10-29 | 2020-10-29 | COMP | 2021-01-20 | COMP | 2021-01-25 | COMP | 2021-01-21 | COMP | 2021-02-19 | COMP | Rule 16 | 80 | 109 | 54 | 4 | 0 | 19 | 262
20236 | 2020-02-06 | 2020-06-11 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-09-25 | COMP | Rule 16 | 89 | 24 | 21 | 1 | 1 | 33 | 164
20292 | 2020-02-06 | 2020-06-15 | 2020-08-18 | 2020-08-18 | COMP | 2020-09-03 | COMP | 2020-10-27 | COMP | 2020-12-01 | COMP | 2020-12-22 | COMP | Rule 16 | 91 | 47 | 13 | 38 | 23 | 16 | 223
20358 | 2020-02-06 | 2020-06-17 | 2020-07-13 | 2020-07-13 | COMP | 2020-07-24 | COMP | 2020-07-27 | COMP | 2020-07-24 | COMP | 2020-08-11 | COMP | Other | 93 | 19 | 10 | 2 | 0 | 12 | 132
20359 | 2020-02-06 | 2020-06-17 | 2020-07-13 | 2020-07-13 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-26 | COMP | Other | 93 | 19 | 10 | 1 | 1 | 24 | 143
20393 | 2020-02-06 | 2020-06-17 | 2020-08-19 | 2021-04-07 | COMP | 2021-04-22 | COMP | 2021-04-22 | COMP | 2021-06-01 | COMP | 2021-06-28 | COMP | Rule 16 | 93 | 46 | 12 | 1 | 28 | 20 | 352
20697 | 2020-02-06 | 2020-07-01 | 2020-09-04 | 2020-09-04 | COMP | 2020-10-05 | COMP | 2020-11-02 | COMP | 2020-12-18 | COMP | 2021-01-05 | COMP | Rule 16 | 103 | 48 | 21 | 21 | 32 | 11 | 231
20703 | 2020-02-06 | 2020-07-02 | 2020-08-20 | 2020-08-20 | COMP | 2021-04-07 | COMP | 2021-04-07 | COMP | 2021-08-26 | COMP | 2021-09-23 | COMP | Rule 16 | 104 | 36 | 157 | 1 | 100 | 20 | 413
20867 | 2020-02-06 | 2020-07-10 | 2020-08-24 | 2020-08-24 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2022-09-14 | COMP | 2022-09-26 | COMP | Rule 16 | 110 | 32 | 22 | 1 | 497 | 9 | 666
21220 | 2020-02-06 | 2020-07-29 | 2020-10-19 | 2020-10-19 | COMP | 2020-10-27 | COMP | 2020-10-27 | COMP | 2020-11-10 | COMP | 2020-12-03 | COMP | Rule 16 | 123 | 58 | 7 | 1 | 11 | 15 | 210
21332 | 2020-02-06 | 2020-08-02 | 2020-12-08 | 2020-12-08 | COMP | 2021-01-26 | COMP | 2021-05-05 | COMP | 2021-06-08 | COMP | 2021-06-14 | COMP | Rule 16 | 125 | 88 | 33 | 71 | 24 | 5 | 342
21702 | 2020-02-06 | 2020-08-20 | 2021-02-24 | 2021-02-24 | COMP | 2021-03-10 | COMP | 2021-05-18 | COMP | 2021-06-23 | COMP | 2021-08-26 | COMP | Rule 15/16 | 139 | 127 | 11 | 50 | 26 | 46 | 394
23389 | 2020-02-06 | 2020-11-04 | 2021-03-05 | 2021-03-05 | COMP | 2021-03-16 | COMP | 2021-03-19 | COMP | 2021-07-27 | COMP | 2021-09-01 | COMP | Rule 16 | 192 | 81 | 8 | 4 | 91 | 27 | 398
24350 | 2020-02-06 | 2020-12-21 | 2021-03-01 | 2021-03-01 | COMP | 2021-03-08 | COMP | 2021-06-28 | COMP | 2021-06-23 | COMP | 2021-08-26 | COMP | Other | 222 | 47 | 6 | 80 | 0 | 43 | 394
24641 | 2020-02-06 | 2021-01-05 | 2021-02-25 | 2021-02-25 | COMP | 2021-03-09 | COMP | 2021-03-09 | COMP | 2021-04-08 | COMP | 2021-05-17 | COMP | Rule 16 | 231 | 36 | 9 | 1 | 23 | 28 | 323
17381 | 2020-02-07 | 2020-02-12 | 2020-03-11 | 2020-03-11 | COMP | 2020-03-26 | COMP | 2020-05-12 | COMP | 2020-05-18 | COMP | 2020-06-18 | COMP | Rule 16 | 4 | 20 | 12 | 34 | 5 | 23 | 93
17482 | 2020-02-07 | 2020-02-18 | 2020-10-05 | 2020-12-03 | COMP | 2020-12-23 | COMP | 2021-03-17 | COMP | 2021-07-22 | COMP | 2021-08-13 | COMP | Rule 16 | 7 | 163 | 15 | 57 | 90 | 17 | 384
17663 | 2020-02-07 | 2020-02-24 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2020-04-17 | COMP | 2020-04-21 | COMP | Rule 16 | 11 | 31 | 5 | 1 | 6 | 3 | 52
17739 | 2020-02-07 | 2020-02-25 | 2020-06-15 | 2020-06-15 | COMP | 2020-08-27 | COMP | 2020-10-09 | COMP | 2020-10-07 | COMP | 2020-11-06 | COMP | Other | 12 | 79 | 54 | 31 | 0 | 21 | 193
17759 | 2020-02-07 | 2020-02-26 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-06-18 | COMP | 2020-08-27 | COMP | Rule 16 | 13 | 64 | 11 | 1 | 8 | 51 | 143
17898 | 2020-02-07 | 2020-03-03 | 2020-06-21 | 2020-06-21 | COMP | 2020-07-13 | COMP | 2020-09-03 | COMP | 2020-10-06 | COMP | 2020-12-03 | COMP | Rule 16 | 17 | 78 | 16 | 39 | 23 | 40 | 209
17928 | 2020-02-07 | 2020-03-04 | 2020-09-23 | 2020-09-23 | COMP | 2020-10-28 | COMP | 2021-01-27 | COMP | 2021-04-20 | COMP | 2021-06-02 | COMP | Rule 15/16 | 18 | 144 | 26 | 60 | 59 | 31 | 333
17983 | 2020-02-07 | 2020-03-06 | 2020-09-08 | 2020-10-07 | COMP | 2020-12-21 | COMP | 2020-12-22 | COMP | 2021-10-11 | COMP | 2021-12-01 | COMP | Rule 15/16 | 20 | 131 | 51 | 2 | 203 | 35 | 458
17986 | 2020-02-07 | 2020-03-05 | 2021-02-25 | 2021-02-25 | COMP | 2021-03-22 | COMP | 2021-03-22 | COMP | 2021-06-02 | COMP | 2021-07-08 | COMP | Rule 16 | 19 | 247 | 18 | 1 | 52 | 26 | 358
18007 | 2020-02-07 | 2020-03-09 | 2020-05-19 | 2020-06-02 | COMP | 2020-08-20 | COMP | 2020-08-20 | COMP | 2021-01-12 | COMP | 2021-02-02 | COMP | Rule 16 | 21 | 52 | 58 | 1 | 98 | 15 | 249
18017 | 2020-02-07 | 2020-03-09 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-05-15 | COMP | 2020-05-26 | COMP | 2020-07-06 | COMP | Rule 16 | 21 | 41 | 6 | 5 | 7 | 30 | 105
18096 | 2020-02-07 | 2020-03-11 | 2020-05-18 | 2020-05-18 | COMP | 2020-08-26 | NOTN | 2020-08-26 | COMP | 2020-10-20 | COMP | 2020-10-14 | COMP | Other | 23 | 49 |  | 72 | 39 |  | 176
18228 | 2020-02-07 | 2020-03-16 | 2020-04-27 | 2020-07-09 | COMP | 2020-10-15 | COMP | 2020-10-15 | COMP | 2022-07-16 | INPR | 2020-11-18 | COMP | Rule 16 | 26 | 31 | 70 | 1 |  |  | 200
18323 | 2020-02-07 | 2020-03-20 | 2020-05-08 | 2020-06-11 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-09-02 | COMP | 2020-11-02 | COMP | Rule 16 | 30 | 36 | 13 | 1 | 48 | 43 | 189
18331 | 2020-02-07 | 2020-03-21 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-17 | COMP | 2021-04-15 | COMP | 2021-09-02 | COMP | 2021-09-30 | COMP | Other | 30 | 70 | 15 | 187 | 99 | 20 | 417
18404 | 2020-02-07 | 2020-03-23 | 2020-09-18 | 2020-09-18 | COMP | 2020-09-30 | COMP | 2020-11-18 | COMP | 2021-03-16 | COMP | 2021-04-16 | COMP | Rule 16 | 31 | 128 | 9 | 35 | 79 | 24 | 301
18523 | 2020-02-07 | 2020-03-27 | 2020-09-25 | 2020-09-25 | COMP | 2020-10-20 | COMP | 2020-12-03 | COMP | 2021-10-05 | COMP | 2021-11-18 | COMP | Rule 16 | 35 | 129 | 18 | 30 | 212 | 32 | 451
18545 | 2020-02-07 | 2020-03-29 | 2020-10-07 | 2020-10-07 | COMP | 2020-10-15 | COMP | 2020-11-07 | COMP | 2020-11-18 | COMP | 2021-02-10 | COMP | Rule 15/16 | 35 | 136 | 7 | 17 | 7 | 56 | 255
18574 | 2020-02-07 | 2020-03-28 | 2020-07-08 | 2020-10-25 | COMP | 2020-11-03 | COMP | 2021-03-01 | COMP | 2021-02-24 | COMP | 2021-03-22 | COMP | Rule 15/16 | 35 | 72 | 7 | 78 | 0 | 16 | 282
18726 | 2020-02-07 | 2020-04-05 | 2020-07-27 | 2020-07-27 | COMP | 2020-12-29 | COMP | 2020-12-29 | INPR | 2020-12-28 | COMP | 2021-01-06 | COMP | Rule 16 | 40 | 80 | 107 |  |  |  | 231
19302 | 2020-02-07 | 2020-04-29 | 2021-01-15 | 2021-01-15 | COMP | 2021-07-27 | COMP | 2023-03-22 | COMP | 2023-09-18 | COMP | 2023-07-17 | COMP | Rule 15/16 | 58 | 181 | 134 | 415 | 125 |  | 865
19337 | 2020-02-07 | 2020-04-30 | 2020-10-12 | 2020-10-12 | COMP | 2020-10-14 | NOTN | 2020-11-20 | COMP | 2020-10-14 | COMP | 2021-01-11 | COMP | Other | 59 | 116 |  | 29 | 0 | 33 | 234
19372 | 2020-02-07 | 2020-05-04 | 2020-10-14 | 2020-10-14 | COMP | 2020-11-12 | COMP | 2021-05-21 | COMP | 2021-05-26 | COMP | 2021-06-29 | COMP | Rule 15/16 | 61 | 116 | 21 | 131 | 4 | 24 | 352
19521 | 2020-02-07 | 2020-05-11 | 2020-08-06 | 2020-08-06 | COMP | 2020-08-13 | COMP | 2020-09-28 | COMP | 2021-01-12 | COMP | 2021-03-02 | COMP | Rule 16 | 66 | 63 | 6 | 32 | 72 | 34 | 268
19645 | 2020-02-07 | 2020-05-15 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-17 | COMP | 2021-09-16 | COMP | 2021-10-05 | COMP | 2022-01-24 | COMP | Other | 70 | 24 | 22 | 294 | 14 | 76 | 495
19854 | 2020-02-07 | 2020-05-26 | 2020-08-26 | 2021-04-05 | COMP | 2021-04-16 | COMP | 2021-06-14 | COMP | 2021-09-08 | COMP | 2021-10-16 | COMP | Rule 16 | 76 | 67 | 10 | 41 | 61 | 28 | 428
19878 | 2020-02-07 | 2020-05-26 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-30 | COMP | 2021-06-23 | COMP | 2022-07-27 | COMP | 2022-09-23 | COMP | Rule 16 | 76 | 31 | 18 | 226 | 276 | 42 | 664
19894 | 2020-02-07 | 2020-05-27 | 2020-08-25 | 2020-08-25 | COMP | 2020-12-31 | NOTN | 2020-12-31 | COMP | 2021-05-21 | COMP | 2021-06-15 | COMP | Other | 77 | 65 |  | 88 | 99 | 17 | 342
20312 | 2020-02-07 | 2020-06-15 | 2020-07-17 | 2020-07-27 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2021-01-05 | COMP | 2021-02-12 | COMP | Rule 16 | 90 | 25 | 54 | 1 | 58 | 28 | 257
20555 | 2020-02-07 | 2020-06-25 | 2020-07-29 | 2020-07-29 | COMP | 2020-08-10 | COMP | 2021-01-27 | COMP | 2021-01-26 | COMP | 2021-03-16 | COMP | Rule 16 | 98 | 25 | 9 | 116 | 0 | 34 | 278
23407 | 2020-02-07 | 2020-11-05 | 2021-05-05 | 2021-05-05 | COMP | 2021-06-25 | COMP | 2021-11-04 | COMP | 2022-02-08 | COMP | 2022-07-12 | COMP | Rule 16 | 192 | 123 | 37 | 93 | 65 | 107 | 612
4296 | 2020-02-08 | 2020-05-01 | 2020-09-04 | 2020-09-04 | COMP | 2020-11-18 | COMP | 2021-06-08 | COMP | 2021-06-22 | COMP | 2021-07-20 | COMP | Rule 16 | 59 | 90 | 52 | 138 | 11 | 20 | 365
17323 | 2020-02-08 | 2020-02-10 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-06 | NOTN | 2020-06-08 | COMP | 2020-12-10 | COMP | 2021-02-10 | COMP | Other | 1 | 84 |  | 1 | 130 | 42 | 254
17324 | 2020-02-08 | 2020-02-10 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-09 | NOTN | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-07-27 | COMP | Other | 1 | 85 |  | 1 | 1 | 35 | 119
17327 | 2020-02-08 | 2020-02-10 | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | NOTN | 2020-09-03 | COMP | 2020-09-08 | COMP | 2020-11-17 | COMP | Other | 1 | 130 |  | 18 | 3 | 50 | 198
17350 | 2020-02-08 | 2020-02-10 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-12 | NOTN | 2020-09-08 | COMP | 2020-08-18 | COMP | 2020-11-16 | COMP | Other | 1 | 88 |  | 62 | 0 | 49 | 197
18786 | 2020-02-08 | 2020-04-06 | 2020-06-04 | 2020-06-04 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-11-13 | COMP | 2020-12-28 | COMP | Rule 16 | 40 | 43 | 22 | 1 | 94 | 29 | 224
20002 | 2020-02-08 | 2020-06-01 | 2020-12-05 | 2020-12-05 | COMP | 2021-01-19 | COMP | 2021-03-29 | COMP | 2021-03-18 | COMP | 2021-05-20 | COMP | Rule 15/16 | 79 | 131 | 29 | 49 | 0 | 39 | 324
17555 | 2020-02-09 | 2020-02-20 | 2020-09-11 | 2020-09-11 | COMP | 2020-09-14 | NOTN | 2021-03-17 | COMP | 2021-03-30 | COMP | 2021-04-16 | COMP | Other | 8 | 145 |  | 127 | 10 | 14 | 300
17947 | 2020-02-09 | 2020-03-05 | 2020-08-27 | 2020-08-27 | COMP | 2021-03-10 | COMP | 2021-03-10 | COMP | 2021-05-28 | COMP | 2021-07-20 | COMP | Rule 15/16 | 18 | 125 | 132 | 1 | 58 | 36 | 365
18536 | 2020-02-09 | 2020-03-28 | 2020-07-17 | 2020-07-17 | COMP | 2020-09-30 | NOTN | 2021-03-26 | COMP | 2022-05-26 | COMP | 2022-09-29 | COMP | Rule 16 | 34 | 79 |  | 173 | 297 | 87 | 667
18723 | 2020-02-09 | 2020-04-03 | 2020-05-30 | 2020-05-30 | COMP | 2020-06-12 | COMP | 2020-07-11 | COMP | 2020-12-21 | COMP | 2021-01-05 | COMP | Rule 16 | 39 | 40 | 10 | 21 | 112 | 10 | 229
19425 | 2020-02-09 | 2020-05-05 | 2020-12-22 | 2020-12-22 | COMP | 2021-04-02 | COMP | 2021-08-06 | COMP | 2022-12-03 | INPR | 2021-08-17 | COMP | Rule 16 | 61 | 161 | 70 | 89 |  |  | 385
17380 | 2020-02-10 | 2020-02-12 | 2020-02-25 | 2020-02-25 | COMP | 2020-05-06 | COMP | 2020-03-03 | COMP | 2020-05-29 | COMP | 2020-06-11 | COMP | Rule 16 | 3 | 9 | 52 |  | 63 | 10 | 87
17470 | 2020-02-10 | 2020-02-14 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2022-07-16 | INPR | 2020-11-19 | COMP | Rule 16 | 5 | 129 | 6 | 1 |  |  | 200
17517 | 2020-02-10 | 2020-02-18 | 2020-04-17 | 2020-04-17 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-12-01 | COMP | 2020-12-23 | COMP | Rule 16 | 6 | 44 | 48 | 1 | 111 | 17 | 222
17624 | 2020-02-10 | 2020-02-21 | 2020-04-22 | 2020-04-22 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2022-01-30 | INPR | 2020-12-11 | COMP | Rule 16 | 9 | 44 | 127 | 1 |  |  | 214
17668 | 2020-02-10 | 2020-02-25 | 2020-11-21 | 2020-11-21 | COMP | 2021-02-02 | COMP | 2021-02-02 | COMP | 2021-10-12 | COMP | 2021-11-15 | COMP | Rule 16 | 11 | 191 | 47 | 1 | 177 | 24 | 447
17686 | 2020-02-10 | 2020-02-24 | 2020-04-30 | 2020-04-30 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2022-05-21 | COMP | 2022-07-15 | COMP | Rule 16 | 10 | 49 | 174 | 1 | 347 | 37 | 614
17696 | 2020-02-10 | 2020-02-24 | 2020-07-13 | 2020-07-13 | COMP | 2020-09-04 | COMP | 2020-09-04 | COMP | 2020-10-13 | COMP | 2020-10-22 | COMP | Rule 16 | 10 | 100 | 40 | 1 | 27 | 8 | 181
17747 | 2020-02-10 | 2020-02-26 | 2020-03-18 | 2020-03-18 | COMP | 2020-04-29 | COMP | 2020-05-11 | NOTN | 2020-05-11 | COMP | 2020-06-05 | COMP | Rule 16 | 12 | 16 | 31 |  |  |  | 83
17833 | 2020-02-10 | 2020-02-28 | 2020-06-03 | 2021-02-17 | COMP | 2021-02-24 | COMP | 2021-04-22 | COMP | 2021-05-03 | COMP | 2021-06-14 | COMP | Rule 16 | 14 | 68 | 6 | 42 | 8 | 30 | 340
17969 | 2020-02-10 | 2020-03-05 | 2020-04-08 | 2020-04-08 | COMP | 2020-04-17 | COMP | 2020-05-11 | NOTN | 2020-05-11 | COMP | 2020-05-20 | COMP | Rule 16 | 18 | 25 | 8 |  |  |  | 72
18132 | 2020-02-10 | 2020-03-12 | 2020-07-16 | 2021-03-17 | COMP | 2021-03-29 | COMP | 2021-03-29 | COMP |  | INPR | 2021-06-08 | COMP | Rule 15/16 | 23 | 90 | 9 | 1 |  |  | 336
18188 | 2020-02-10 | 2020-03-13 | 2020-06-24 | 2020-09-10 | COMP | 2020-09-29 | COMP | 2020-10-01 | COMP | 2020-10-13 | COMP | 2020-10-30 | COMP | Rule 16 | 24 | 73 | 14 | 3 | 9 | 14 | 187
18202 | 2020-02-10 | 2020-03-16 | 2020-06-24 | 2020-06-24 | COMP | 2020-06-25 | NOTN | 2020-08-13 | COMP | 2020-07-17 | COMP | 2020-10-20 | COMP | Other | 25 | 72 |  | 37 | 0 | 48 | 179
18270 | 2020-02-10 | 2020-03-18 | 2020-04-05 | 2020-04-05 | COMP | 2020-04-27 | COMP | 2020-04-27 | COMP | 2020-10-30 | COMP | 2020-12-16 | COMP | Rule 15/16 | 27 | 13 | 16 | 1 | 133 | 31 | 217
18356 | 2020-02-10 | 2020-03-20 | 2020-07-08 | 2021-03-05 | COMP | 2021-03-09 | COMP | 2020-11-25 | COMP | 2021-02-24 | COMP | 2021-03-22 | COMP | Rule 16 | 29 | 78 | 3 |  | 60 | 19 | 281
18423 | 2020-02-10 | 2020-03-24 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-06-29 | COMP | 2020-08-10 | COMP | Rule 16 | 31 | 53 | 12 | 1 | 6 | 31 | 129
18704 | 2020-02-10 | 2020-04-03 | 2021-05-13 | 2021-05-13 | COMP | 2021-06-29 | COMP | 2021-09-21 | COMP | 2021-09-07 | COMP | 2021-11-17 | COMP | Rule 15/16 | 39 | 281 | 33 | 59 | 0 | 41 | 449
18755 | 2020-02-10 | 2020-04-06 | 2020-06-09 | 2020-06-09 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2022-09-19 | COMP | 2022-10-13 | COMP | Rule 16 | 40 | 46 | 135 | 1 | 441 | 19 | 677
18784 | 2020-02-10 | 2020-04-06 | 2020-05-05 | 2020-05-05 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-09-29 | COMP | 2022-07-19 | COMP | Rule 15/16 | 40 | 22 | 70 | 1 | 35 | 453 | 616
18824 | 2020-02-10 | 2020-04-08 | 2020-10-01 | 2020-10-01 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2023-11-07 | INPR | 2022-09-13 | COMP | Rule 16 | 42 | 125 | 6 | 1 |  |  | 655
18986 | 2020-02-10 | 2020-04-16 | 2020-06-01 | 2020-06-01 | COMP | 2020-08-06 | COMP | 2020-11-03 | COMP | 2021-01-04 | COMP | 2021-01-05 | COMP | Rule 16 | 48 | 32 | 49 | 63 | 40 | 2 | 229
19005 | 2020-02-10 | 2020-04-16 | 2020-06-08 | 2020-06-08 | COMP | 2021-01-15 | COMP | 2021-01-15 | COMP | 2021-05-04 | COMP | 2021-05-20 | COMP | Rule 16 | 48 | 37 | 154 | 1 | 76 | 13 | 324
19057 | 2020-02-10 | 2020-04-20 | 2020-08-18 | 2020-08-18 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2021-05-14 | COMP | 2021-06-21 | COMP | Rule 16 | 50 | 86 | 70 | 1 | 117 | 26 | 345
19127 | 2020-02-10 | 2020-04-22 | 2020-08-14 | 2023-08-08 | COMP | 2020-08-14 | NOTN | 2020-08-14 | COMP | 2023-01-31 | COMP | 2023-11-09 | COMP | Other | 52 | 82 |  |  | 617 | 198 | 946
19161 | 2020-02-10 | 2020-04-23 | 2020-10-29 | 2020-10-29 | COMP | 2021-03-03 | COMP | 2021-03-03 | COMP | 2021-04-17 | COMP | 2021-05-07 | COMP | Rule 16 | 53 | 134 | 83 | 1 | 33 | 15 | 315
19546 | 2020-02-10 | 2020-05-11 | 2020-06-02 | 2020-06-02 | COMP | 2020-08-07 | COMP | 2020-08-19 | COMP | 2020-09-08 | COMP | 2020-10-06 | COMP | Rule 16 | 65 | 16 | 49 | 9 | 14 | 21 | 169
19837 | 2020-02-10 | 2020-05-26 | 2020-10-03 | 2020-10-03 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP | 2020-12-31 | COMP | 2020-12-28 | COMP | Rule 16 | 75 | 93 | 40 | 1 | 21 |  | 224
20162 | 2020-02-10 | 2020-06-09 | 2020-07-09 | 2020-07-09 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-09-14 | COMP | 2020-10-21 | COMP | Rule 16 | 85 | 23 | 10 | 1 | 38 | 28 | 180
20686 | 2020-02-10 | 2020-07-01 | 2020-11-19 | 2020-11-19 | COMP | 2021-03-25 | COMP | 2021-03-25 | COMP | 2021-03-29 | COMP | 2021-04-28 | COMP | Rule 16 | 101 | 100 | 85 | 1 | 3 | 23 | 308
20876 | 2020-02-10 | 2020-07-10 | 2020-09-25 | 2020-09-25 | COMP | 2021-06-16 | COMP | 2021-07-26 | COMP | 2021-08-03 | COMP | 2021-08-05 | COMP | Rule 16 | 108 | 55 | 181 | 28 | 7 | 3 | 377
21271 | 2020-02-10 | 2020-07-30 | 2020-09-04 | 2020-09-04 | COMP | 2020-12-09 | COMP | 2021-04-14 | COMP | 2021-04-27 | COMP | 2021-05-27 | COMP | Rule 16 | 122 | 27 | 65 | 87 | 10 | 23 | 329
17518 | 2020-02-11 | 2020-02-18 | 2020-07-16 | 2020-07-16 | COMP | 2020-07-22 | COMP | 2020-07-22 | INPR | 2022-07-23 | REQD | 2020-08-17 | COMP | Rule 16 | 5 | 107 | 5 |  |  |  | 133
17565 | 2020-02-11 | 2020-02-20 | 2020-05-06 | 2020-07-17 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2022-01-30 | INPR | 2021-01-25 | COMP | Rule 16 | 7 | 55 | 5 | 1 |  |  | 241
17726 | 2020-02-11 | 2020-02-25 | 2020-06-10 | 2020-06-10 | COMP | 2020-10-19 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2020-12-29 | COMP | Rule 16 | 10 | 76 | 93 | 21 | 1 | 28 | 224
17886 | 2020-02-11 | 2020-03-03 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-07 | NOTN | 2020-05-27 | COMP | 2020-05-28 | COMP | 2023-06-28 | COMP | Rule 16 | 15 | 25 |  | 37 | 2 | 776 | 851
17959 | 2020-02-11 | 2020-03-05 | 2020-05-20 | 2020-05-20 | COMP | 2020-07-07 | COMP | 2020-07-30 | COMP | 2020-07-13 | COMP | 2020-08-26 | COMP | Rule 16 | 17 | 55 | 34 | 18 | 0 | 20 | 140
17996 | 2020-02-11 | 2020-03-06 | 2020-06-09 | 2020-06-09 | COMP | 2020-11-19 | COMP | 2020-11-24 | COMP | 2021-04-08 | COMP | 2021-04-10 | COMP | Rule 16 | 18 | 67 | 116 | 4 | 92 | 2 | 294
18013 | 2020-02-11 | 2020-03-09 | 2020-04-16 | 2020-04-16 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-07-08 | COMP | 2020-07-11 | COMP | Rule 16 | 19 | 29 | 43 | 1 | 17 | 3 | 107
18098 | 2020-02-11 | 2020-03-10 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-07-23 | COMP | Rule 16 | 20 | 67 | 4 | 1 | 1 | 28 | 116
18178 | 2020-02-11 | 2020-03-13 | 2020-06-19 | 2020-06-19 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-12-21 | COMP | 2021-01-12 | COMP | Rule 16 | 23 | 70 | 39 | 1 | 90 | 15 | 233
18317 | 2020-02-11 | 2020-03-19 | 2020-07-30 | 2020-07-30 | COMP | 2020-09-17 | COMP | 2021-03-02 | COMP | 2021-02-09 | COMP | 2021-04-01 | COMP | Rule 15/16 | 27 | 95 | 35 | 112 | 0 | 23 | 288
18452 | 2020-02-11 | 2020-03-24 | 2020-10-29 | 2020-10-29 | COMP | 2021-02-17 | COMP | 2022-05-24 | COMP | 2023-01-24 | COMP | 2023-03-03 | COMP | Rule 15/16 | 30 | 156 | 73 | 322 | 166 | 28 | 770
18622 | 2020-02-11 | 2020-03-31 | 2020-05-05 | 2020-05-05 | COMP | 2020-07-31 | COMP | 2020-08-08 | COMP | 2020-09-02 | COMP | 2020-10-06 | COMP | Rule 16 | 35 | 26 | 63 | 6 | 18 | 24 | 168
18667 | 2020-02-11 | 2020-04-01 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-30 | COMP | 2020-07-03 | COMP | 2021-10-23 | INPR | 2020-08-24 | COMP | Rule 16 | 36 | 48 | 17 | 4 |  |  | 138
18783 | 2020-02-11 | 2020-04-06 | 2020-06-16 | 2020-06-16 | COMP | 2020-06-08 | NOTN | 2020-06-16 | COMP | 2020-08-17 | COMP | 2020-09-29 | COMP | Other | 39 | 51 |  | 1 | 45 | 31 | 163
18817 | 2020-02-11 | 2020-04-08 | 2020-07-06 | 2020-07-06 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-07-29 | COMP | 2020-08-31 | COMP | Rule 16 | 41 | 63 | 12 | 1 | 7 | 24 | 143
18838 | 2020-02-11 | 2020-04-09 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-09 | COMP | 2020-07-16 | COMP | Rule 16 | 42 | 32 | 10 | 1 | 24 | 6 | 111
19111 | 2020-02-11 | 2020-04-21 | 2020-07-15 | 2020-07-15 | COMP | 2020-07-29 | COMP | 2020-11-04 | COMP | 2021-01-12 | COMP | 2021-02-10 | COMP | Rule 16 | 50 | 61 | 11 | 70 | 45 | 21 | 253
19209 | 2020-02-11 | 2020-04-23 | 2020-12-08 | 2020-12-08 | COMP | 2020-12-28 | COMP | 2021-01-20 | COMP | 2022-02-26 | INPR | 2021-01-28 | COMP | Rule 16 | 52 | 159 | 14 | 16 |  |  | 244
19347 | 2020-02-11 | 2020-05-02 | 2020-06-10 | 2020-07-29 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2020-09-17 | COMP | 2020-09-16 | COMP | Rule 16 | 58 | 27 | 7 | 1 | 30 |  | 154
20012 | 2020-02-11 | 2020-06-02 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-17 | COMP | 2020-08-18 | COMP | Rule 16 | 79 | 11 | 29 | 1 | 17 | 2 | 134
20769 | 2020-02-11 | 2020-07-07 | 2020-07-23 | 2020-07-23 | COMP | 2020-11-03 | COMP | 2020-11-03 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | Rule 16 | 104 | 13 | 73 | 1 | 50 | 1 | 237
20872 | 2020-02-11 | 2020-07-09 | 2020-07-27 | 2020-07-27 | COMP | 2020-12-09 | COMP | 2020-12-10 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | Rule 16 | 106 | 13 | 94 | 2 | 26 | 1 | 237
23798 | 2020-02-11 | 2020-11-23 | 2021-02-19 | 2021-02-19 | COMP | 2021-04-08 | COMP | 2021-04-08 | COMP | 2021-06-11 | COMP | 2021-07-12 | COMP | Rule 15/16 | 201 | 59 | 35 | 1 | 46 | 21 | 358
25198 | 2020-02-11 | 2021-02-01 | 2021-03-22 | 2021-03-22 | COMP | 2021-06-14 | COMP | 2021-06-14 | COMP | 2022-01-04 | COMP | 2022-03-17 | COMP | Rule 15/16 | 246 | 35 | 60 | 1 | 142 | 51 | 530
25707 | 2020-02-11 | 2021-02-22 | 2021-04-09 | 2021-04-09 | COMP | 2021-04-19 | COMP | 2021-04-19 | COMP | 2021-08-16 | COMP | 2021-11-05 | COMP | Rule 16 | 260 | 35 | 7 | 1 | 84 | 59 | 441
17510 | 2020-02-12 | 2020-02-19 | 2020-03-16 | 2020-03-16 | COMP | 2020-03-20 | COMP | 2020-03-25 | INPR | 2020-07-14 | COMP | 2020-05-22 | COMP | Rule 16 | 5 | 19 | 5 |  |  |  | 72
17535 | 2020-02-12 | 2020-02-19 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-09 | NOTN | 2020-10-01 | COMP | 2020-10-06 | COMP | 2020-12-17 | COMP | Other | 5 | 81 |  | 80 | 4 | 50 | 216
17580 | 2020-02-12 | 2020-02-20 | 2020-04-17 | 2020-04-17 | COMP | 2020-06-08 | COMP | 2020-07-13 | COMP | 2020-11-30 | COMP | 2021-01-05 | COMP | Rule 16 | 6 | 42 | 36 | 26 | 97 | 25 | 227
17687 | 2020-02-12 | 2020-02-24 | 2020-06-09 | 2020-06-09 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-10-20 | COMP | 2020-11-03 | COMP | Rule 16 | 8 | 76 | 25 | 1 | 71 | 11 | 187
17843 | 2020-02-12 | 2020-03-02 | 2020-04-07 | 2020-04-07 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2022-01-30 | INPR | 2020-09-02 | COMP | Rule 16 | 13 | 27 | 7 | 1 |  |  | 144
17859 | 2020-02-12 | 2020-03-02 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-10 | NOTN | 2020-08-10 | COMP | 2020-08-10 | COMP | 2020-09-30 | COMP | Other | 13 | 115 |  | 1 | 1 | 37 | 163
18061 | 2020-02-12 | 2020-03-10 | 2020-07-26 | 2020-07-26 | COMP | 2020-08-18 | COMP | 2020-08-18 | COMP | 2020-11-09 | COMP | 2021-02-10 | COMP | Rule 16 | 19 | 98 | 17 | 1 | 59 | 62 | 252
18063 | 2020-02-12 | 2020-03-10 | 2020-08-05 | 2020-09-09 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2020-11-09 | COMP | 2020-12-10 | COMP | Rule 16 | 19 | 106 | 4 | 1 | 41 | 21 | 211
18103 | 2020-02-12 | 2020-03-11 | 2020-10-20 | 2020-10-29 | COMP | 2020-12-03 | COMP | 2021-01-27 | COMP | 2022-05-02 | COMP | 2022-05-23 | COMP | Rule 16 | 20 | 158 | 23 | 37 | 320 | 16 | 576
18109 | 2020-02-12 | 2020-03-11 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2021-06-14 | COMP | 2021-09-09 | COMP | Rule 16 | 20 | 37 | 37 | 1 | 247 | 62 | 399
18164 | 2020-02-12 | 2020-03-12 | 2020-05-13 | 2020-05-13 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2021-03-10 | COMP | 2021-05-06 | COMP | Rule 16 | 21 | 45 | 53 | 1 | 155 | 42 | 312
18167 | 2020-02-12 | 2020-03-13 | 2020-04-30 | 2020-04-30 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-03-03 | COMP | 2021-04-13 | COMP | Rule 16 | 22 | 35 | 107 | 1 | 105 | 30 | 295
18184 | 2020-02-12 | 2020-03-13 | 2020-05-14 | 2020-07-08 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-09-27 | COMP | 2020-10-30 | COMP | Rule 16 | 22 | 45 | 9 | 1 | 49 | 25 | 185
18239 | 2020-02-12 | 2020-03-16 | 2020-05-27 | 2020-05-27 | COMP | 2021-02-24 | COMP | 2021-12-10 | COMP | 2022-04-05 | COMP | 2022-06-03 | COMP | Rule 16 | 23 | 52 | 188 | 202 | 81 | 43 | 584
18263 | 2020-02-12 | 2020-03-17 | 2020-05-08 | 2020-05-08 | COMP | 2020-09-28 | COMP | 2021-04-20 | COMP | 2021-03-30 | COMP | 2021-05-04 | COMP | Rule 16 | 24 | 39 | 100 | 140 | 0 | 11 | 310
18344 | 2020-02-12 | 2020-03-20 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-12 | COMP | 2020-08-13 | COMP | 2021-04-13 | COMP | 2021-05-27 | COMP | Rule 16 | 27 | 82 | 22 | 2 | 166 | 33 | 327
18563 | 2020-02-12 | 2020-03-30 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-03 | COMP | 2020-08-04 | COMP | 2021-07-15 | COMP | 2021-09-10 | COMP | Rule 16 | 33 | 74 | 17 | 2 | 238 | 41 | 400
18608 | 2020-02-12 | 2020-03-31 | 2020-05-28 | 2021-11-03 | COMP | 2021-11-23 | COMP | 2021-11-23 | COMP | 2022-06-06 | COMP | 2022-06-20 | COMP | Rule 16 | 34 | 42 | 14 | 1 | 135 | 10 | 594
18675 | 2020-02-12 | 2020-04-02 | 2020-07-23 | 2020-07-27 | COMP | 2020-09-01 | COMP | 2021-02-26 | COMP | 2021-02-19 | COMP | 2021-06-02 | COMP | Other | 36 | 80 | 27 | 121 | 0 | 68 | 330
18710 | 2020-02-12 | 2020-04-03 | 2020-10-04 | 2020-10-04 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-10-12 | COMP | 2020-10-15 | COMP | Rule 16 | 37 | 129 | 5 | 1 | 2 | 4 | 174
18989 | 2020-02-12 | 2020-04-15 | 2020-05-20 | 2020-11-09 | COMP | 2021-05-04 | COMP | 2021-09-13 | COMP | 2022-05-31 | COMP | 2022-07-06 | COMP | Rule 16 | 45 | 26 | 120 | 92 | 181 | 25 | 605
19354 | 2020-02-12 | 2020-05-02 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-08-21 | COMP | 2020-09-12 | COMP | Rule 16 | 57 | 51 | 3 | 1 | 27 | 15 | 150
19424 | 2020-02-12 | 2020-05-06 | 2020-06-04 | 2020-06-04 | COMP | 2021-02-19 | COMP | 2021-03-05 | COMP | 2021-05-06 | COMP | 2021-06-04 | COMP | Rule 16 | 60 | 21 | 179 | 11 | 45 | 21 | 332
19460 | 2020-02-12 | 2020-05-07 | 2020-06-16 | 2020-10-16 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2021-03-24 | COMP | 2021-04-14 | COMP | Rule 16 | 61 | 28 | 7 | 1 | 101 | 16 | 296
19630 | 2020-02-12 | 2020-05-15 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-08-13 | COMP | 2020-11-05 | COMP | Rule 16 | 67 | 30 | 24 | 1 | 12 | 60 | 189
19831 | 2020-02-12 | 2020-05-24 | 2020-07-22 | 2020-07-22 | COMP | 2020-11-03 | COMP | 2021-07-12 | COMP |  |  | 2021-10-12 | COMP | Rule 15/16 | 72 | 42 | 74 | 171 |  |  | 422
19961 | 2020-02-12 | 2020-05-29 | 2020-06-19 | 2020-06-19 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | 2020-10-13 | COMP | 2020-11-17 | COMP | Rule 16 | 76 | 16 | 49 | 1 | 34 | 25 | 196
20048 | 2020-02-12 | 2020-06-02 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-09-08 | COMP | 2020-11-12 | COMP | Rule 16 | 78 | 31 | 11 | 1 | 30 | 47 | 193
20143 | 2020-02-12 | 2020-06-08 | 2020-07-22 | 2020-07-22 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-11-06 | COMP | 2020-12-02 | COMP | Rule 16 | 82 | 33 | 29 | 1 | 49 | 16 | 205
20464 | 2020-02-12 | 2020-06-22 | 2020-08-12 | 2020-08-12 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2020-10-13 | COMP | 2020-12-15 | COMP | Rule 16 | 92 | 38 | 9 | 1 | 36 | 43 | 214
17604 | 2020-02-13 | 2020-02-21 | 2020-04-09 | 2020-04-09 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-06-05 | COMP | 2020-06-30 | COMP | Rule 16 | 6 | 35 | 18 | 1 | 24 | 18 | 97
17630 | 2020-02-13 | 2020-02-25 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-07-20 | COMP | 2020-08-13 | COMP | Rule 15/16 | 8 | 63 | 41 | 1 | 2 | 19 | 129
17853 | 2020-02-13 | 2020-03-02 | 2020-05-07 | 2020-05-07 | COMP | 2020-05-20 | COMP | 2020-05-20 | COMP | 2021-01-26 | COMP | 2021-02-15 | COMP | Rule 16 | 12 | 49 | 10 | 1 | 172 | 14 | 253
17890 | 2020-02-13 | 2020-03-03 | 2020-07-13 | 2020-07-13 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-09-02 | COMP | 2020-12-01 | COMP | Rule 16 | 13 | 94 | 10 | 1 | 29 | 61 | 203
17964 | 2020-02-13 | 2020-03-05 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-10-20 | COMP | 2020-12-15 | COMP | Rule 16 | 15 | 52 | 11 | 1 | 101 | 38 | 213
18055 | 2020-02-13 | 2020-03-10 | 2020-04-05 | 2020-04-05 | COMP | 2020-04-15 | COMP | 2020-06-25 | COMP | 2020-06-23 | COMP | 2020-07-07 | COMP | Rule 15/16 | 18 | 19 | 8 | 51 | 0 | 9 | 102
18075 | 2020-02-13 | 2020-03-10 | 2020-03-24 | 2020-03-24 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-28 | COMP | 2020-06-16 | COMP | Rule 16 | 18 | 11 | 39 | 1 | 9 | 14 | 87
18511 | 2020-02-13 | 2020-03-27 | 2020-06-23 | 2020-07-13 | COMP | 2020-06-23 | NOTN | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-11-14 | COMP | Other | 31 | 62 |  |  | 1 | 102 | 193
18844 | 2020-02-13 | 2020-04-09 | 2020-08-15 | 2020-08-15 | COMP | 2020-09-21 | COMP | 2021-11-08 | COMP | 2023-03-02 | COMP | 2023-04-21 | COMP | Rule 15/16 | 40 | 91 | 25 | 286 | 328 | 37 | 803
18902 | 2020-02-13 | 2020-04-10 | 2020-09-16 | 2020-09-16 | COMP | 2020-10-16 | COMP | 2020-12-08 | COMP | 2021-04-20 | COMP | 2021-05-07 | COMP | Rule 16 | 41 | 112 | 23 | 35 | 92 | 14 | 312
19049 | 2020-02-13 | 2020-04-19 | 2020-09-27 | 2020-09-27 | COMP | 2020-10-05 | COMP | 2020-11-18 | COMP | 2020-12-29 | COMP | 2021-02-08 | COMP | Rule 15/16 | 46 | 113 | 6 | 32 | 27 | 28 | 249
19299 | 2020-02-13 | 2020-04-28 | 2020-07-31 | 2020-10-14 | COMP | 2020-10-20 | COMP | 2020-11-24 | COMP | 2021-02-26 | COMP | 2021-06-02 | COMP | Rule 15/16 | 53 | 68 | 5 | 25 | 63 | 68 | 329
19446 | 2020-02-13 | 2020-05-06 | 2020-08-23 | 2020-08-23 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2020-10-09 | COMP | 2020-11-09 | COMP | Rule 16 | 59 | 77 | 11 | 1 | 24 | 22 | 190
19634 | 2020-02-13 | 2020-05-15 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-07-06 | COMP | 2020-07-09 | COMP | Rule 16 | 66 | 19 | 13 | 1 | 6 | 4 | 104
20497 | 2020-02-13 | 2020-06-23 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | Unknown | 92 | 35 | 2 | 1 | 26 | 1 | 152
20947 | 2020-02-13 | 2020-07-15 | 2020-11-21 | 2020-11-21 | COMP | 2021-06-01 | COMP | 2021-06-24 | COMP | 2022-02-14 | COMP | 2022-03-15 | COMP | Rule 16 | 108 | 91 | 130 | 18 | 162 | 21 | 526
21536 | 2020-02-13 | 2020-08-12 | 2020-11-30 | 2020-11-30 | COMP | 2020-12-22 | COMP | 2021-05-12 | COMP | 2021-04-30 | COMP | 2021-06-09 | COMP | Rule 15/16 | 128 | 75 | 17 | 98 | 0 | 20 | 334
17796 | 2020-02-14 | 2020-02-27 | 2020-07-31 | 2020-07-31 | COMP | 2020-09-15 | COMP | 2020-09-19 | COMP | 2021-03-05 | COMP | 2021-04-22 | COMP | Rule 16 | 9 | 111 | 32 | 4 | 113 | 35 | 300
17847 | 2020-02-14 | 2020-03-02 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-05-12 | COMP | 2020-06-08 | COMP | Rule 16 | 11 | 46 | 6 | 1 | 2 | 19 | 80
17881 | 2020-02-14 | 2020-03-02 | 2020-05-05 | 2020-05-05 | COMP | 2020-09-10 | COMP | 2020-09-30 | COMP | 2020-10-05 | COMP | 2020-11-16 | COMP | Rule 16 | 11 | 47 | 91 | 15 | 4 | 30 | 193
18038 | 2020-02-14 | 2020-03-09 | 2020-04-21 | 2020-05-15 | COMP | 2020-06-17 | COMP | 2020-06-22 | COMP | 2020-09-10 | COMP | 2020-10-23 | COMP | Rule 16 | 16 | 32 | 23 | 4 | 58 | 32 | 178
18176 | 2020-02-14 | 2020-03-13 | 2020-09-25 | 2020-09-25 | COMP | 2021-05-04 | COMP | 2021-05-04 | COMP | 2021-05-25 | COMP | 2021-06-15 | COMP | Rule 16 | 20 | 139 | 151 | 1 | 16 | 15 | 337
18190 | 2020-02-14 | 2020-03-13 | 2020-06-15 | 2020-06-15 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2020-08-17 | COMP | 2020-09-29 | COMP | Rule 16 | 20 | 66 | 31 | 1 | 16 | 31 | 160
18215 | 2020-02-14 | 2020-03-16 | 2020-09-11 | 2020-09-11 | COMP | 2020-10-16 | COMP | 2020-12-22 | COMP | 2021-03-07 | COMP | 2021-03-27 | COMP | Rule 16 | 21 | 128 | 26 | 45 | 50 | 15 | 281
18399 | 2020-02-14 | 2020-03-23 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-27 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-07-23 | COMP | Rule 16 | 26 | 26 | 22 | 33 | 1 | 10 | 113
18552 | 2020-02-14 | 2020-03-28 | 2020-07-10 | 2021-02-05 | COMP | 2021-04-15 | COMP | 2021-09-22 | COMP | 2021-04-15 | COMP | 2021-10-18 | COMP | Rule 16 | 30 | 74 | 49 | 112 | 0 | 19 | 424
18651 | 2020-02-14 | 2020-04-01 | 2020-05-28 | 2020-05-28 | COMP | 2020-05-28 | NOTN | 2020-05-29 | COMP | 2020-05-28 | COMP | 2020-07-10 | COMP | Other | 33 | 41 |  | 2 | 0 | 31 | 104
18657 | 2020-02-14 | 2020-04-02 | 2020-08-05 | 2020-08-05 | COMP | 2020-12-24 | COMP | 2021-01-13 | COMP | 2020-08-07 | COMP | 2021-05-05 | COMP | Rule 16 | 34 | 89 | 98 | 13 | 0 | 79 | 309
18779 | 2020-02-14 | 2020-04-09 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-16 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-07-09 | COMP | Rule 16 | 39 | 45 | 4 | 6 | 1 | 13 | 103
18850 | 2020-02-14 | 2020-04-09 | 2020-09-21 | 2020-09-21 | COMP | 2020-09-28 | COMP | 2020-12-15 | COMP | 2020-12-28 | COMP | 2021-04-05 | COMP | Rule 16 | 39 | 116 | 6 | 54 | 9 | 68 | 287
19035 | 2020-02-14 | 2020-04-17 | 2020-10-16 | 2020-10-16 | COMP | 2021-03-03 | COMP | 2022-07-12 | COMP | 2022-06-28 | COMP | 2022-08-12 | COMP | Rule 16 | 45 | 129 | 92 | 344 | 0 | 24 | 630
19315 | 2020-02-14 | 2020-04-29 | 2020-05-18 | 2020-05-18 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-05-28 | COMP | 2020-06-11 | COMP | Rule 16 | 53 | 14 | 6 | 1 | 3 | 11 | 83
19809 | 2020-02-14 | 2020-05-22 | 2020-12-21 | 2021-03-02 | COMP | 2021-03-16 | COMP | 2021-04-13 | INPR | 2023-12-04 | CANC | 2021-06-28 | COMP | Rule 16 | 70 | 147 | 11 |  |  |  | 346
19951 | 2020-02-14 | 2020-05-30 | 2020-07-30 | 2020-07-30 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-08-14 | COMP | 2020-09-22 | COMP | Rule 16 | 74 | 44 | 11 | 1 | 2 | 27 | 155
20163 | 2020-02-14 | 2020-06-09 | 2020-08-27 | 2020-08-27 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2020-09-14 | COMP | 2020-11-30 | COMP | Rule 16 | 81 | 58 | 51 | 1 | 0 | 14 | 201
20202 | 2020-02-14 | 2020-06-10 | 2020-08-23 | 2020-08-23 | COMP | 2021-01-25 | COMP | 2021-02-22 | COMP | 2021-02-19 | COMP | 2021-03-30 | COMP | Rule 15/16 | 82 | 53 | 104 | 20 | 0 | 27 | 283
20322 | 2020-02-14 | 2020-06-15 | 2020-07-28 | 2020-07-28 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2020-08-17 | COMP | 2020-08-13 | COMP | Rule 16 | 85 | 32 | 8 | 1 | 8 |  | 128
20693 | 2020-02-14 | 2020-07-01 | 2020-07-29 | 2020-07-29 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-02-22 | COMP | 2021-02-22 | COMP | Rule 16 | 97 | 21 | 44 | 1 | 98 | 1 | 257
20724 | 2020-02-14 | 2020-07-03 | 2020-09-23 | 2020-09-23 | COMP | 2020-10-02 | COMP | 2020-10-13 | COMP | 2023-12-30 | INPR | 2020-11-02 | COMP | Rule 16 | 99 | 58 | 8 | 8 |  |  | 184
21208 | 2020-02-14 | 2020-07-27 | 2020-10-21 | 2020-12-07 | COMP | 2021-03-04 | NOTN | 2021-05-27 | COMP | 2020-12-14 | COMP | 2023-04-14 | COMP | Other | 115 | 62 |  | 120 | 0 | 473 | 797
21508 | 2020-02-14 | 2020-08-10 | 2020-10-06 | 2020-10-06 | COMP | 2021-04-20 | COMP | 2022-04-22 | COMP | 2022-02-23 | COMP | 2022-06-13 | COMP | Rule 16 | 125 | 41 | 134 | 256 | 0 | 36 | 588
21555 | 2020-02-14 | 2020-08-12 | 2020-10-14 | 2020-10-14 | COMP | 2021-04-20 | COMP | 2021-04-20 | COMP | 2022-02-04 | COMP | 2022-05-20 | COMP | Rule 16 | 127 | 45 | 128 | 1 | 202 | 75 | 573
17475 | 2020-02-15 | 2020-02-15 | 2020-05-28 | 2020-05-28 | COMP | 2020-11-17 | NOTN | 2021-03-17 | COMP | 2021-03-23 | COMP | 2021-06-03 | COMP | Other | 0 | 72 |  | 202 | 5 | 52 | 328
18531 | 2020-02-15 | 2020-03-27 | 2020-04-28 | 2020-04-28 | COMP | 2020-05-01 | NOTN | 2020-05-01 | COMP | 2020-05-26 | COMP | 2020-06-08 | COMP | Rule 16 | 29 | 23 |  | 4 | 17 | 10 | 79
19531 | 2020-02-15 | 2020-05-11 | 2020-07-23 | 2020-07-23 | COMP | 2020-10-01 | COMP | 2021-01-13 | COMP | 2021-06-19 | COMP | 2021-07-14 | COMP | Rule 16 | 60 | 53 | 50 | 70 | 110 | 17 | 356
20455 | 2020-02-15 | 2020-06-20 | 2020-08-10 | 2020-08-10 | COMP | 2021-09-08 | COMP | 2021-09-28 | COMP | 2021-09-09 | COMP | 2021-11-09 | COMP | Rule 16 | 88 | 36 | 272 | 15 | 0 | 31 | 439
21020 | 2020-02-15 | 2020-07-18 | 2020-09-18 | 2020-09-18 | COMP | 2021-04-21 | COMP | 2021-05-04 | COMP | 2021-07-23 | COMP | 2021-09-02 | COMP | Rule 16 | 108 | 44 | 147 | 10 | 57 | 30 | 392
17689 | 2020-02-16 | 2020-02-24 | 2020-06-18 | 2020-06-18 | COMP | 2020-06-18 | NOTN | 2020-06-18 | COMP | 2020-06-18 | COMP | 2021-06-29 | COMP | Other | 5 | 83 |  | 1 | 1 | 260 | 346
18039 | 2020-02-16 | 2020-03-09 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2022-01-30 | INPR | 2020-06-27 | COMP | Rule 16 | 15 | 43 | 33 | 1 |  |  | 93
19072 | 2020-02-16 | 2020-04-20 | 2020-07-17 | 2020-07-17 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | 2020-10-14 | COMP | Rule 16 | 45 | 64 | 43 | 1 | 1 | 21 | 170
17501 | 2020-02-17 | 2020-02-19 | 2020-03-10 | 2020-03-10 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2022-03-28 | COMP | 2022-03-31 | COMP | Rule 16 | 2 | 15 | 24 | 1 | 495 | 4 | 536
17506 | 2020-02-17 | 2020-02-19 | 2020-03-17 | 2020-03-17 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2022-05-28 | INPR | 2021-05-04 | COMP | Rule 16 | 2 | 20 | 19 | 1 |  |  | 307
17507 | 2020-02-17 | 2020-02-19 | 2020-03-19 | 2020-03-19 | COMP | 2020-04-10 | COMP | 2020-04-10 | COMP | 2022-11-30 | COMP | 2021-05-04 | COMP | Rule 16 | 2 | 22 | 17 | 1 | 665 |  | 307
17756 | 2020-02-17 | 2020-02-26 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-08 | NOTN | 2020-08-12 | COMP | 2020-06-09 | COMP | 2020-10-08 | COMP | Other | 7 | 73 |  | 48 | 0 | 41 | 166
18148 | 2020-02-17 | 2020-03-12 | 2020-04-21 | 2020-07-07 | COMP | 2020-09-17 | COMP | 2021-05-12 | COMP | 2022-01-19 | COMP | 2022-02-19 | COMP | Rule 16 | 18 | 29 | 52 | 163 | 174 | 23 | 508
18395 | 2020-02-17 | 2020-03-23 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-10 | NOTN | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-06-24 | COMP | Rule 16 | 25 | 33 |  | 25 | 1 | 11 | 91
18856 | 2020-02-17 | 2020-04-09 | 2020-10-13 | 2020-10-13 | COMP | 2020-11-24 | COMP | 2020-11-24 | COMP | 2023-02-14 | COMP | 2023-02-15 | COMP | Rule 16 | 38 | 132 | 30 | 1 | 557 | 2 | 755
19152 | 2020-02-17 | 2020-04-22 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-13 | COMP | 2020-05-13 | INPR | 2020-05-22 | COMP | 2020-05-25 | COMP | Rule 16 | 47 | 10 | 7 |  |  |  | 69
19374 | 2020-02-17 | 2020-05-04 | 2020-09-26 | 2020-09-26 | COMP | 2020-10-13 | COMP | 2021-02-03 | COMP | 2021-03-02 | COMP | 2021-03-24 | COMP | Rule 16 | 55 | 103 | 12 | 76 | 19 | 17 | 278
19476 | 2020-02-17 | 2020-05-08 | 2020-06-15 | 2020-06-15 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-09-08 | COMP | 2020-09-11 | COMP | Rule 16 | 59 | 26 | 11 | 1 | 51 | 4 | 147
19540 | 2020-02-17 | 2020-05-11 | 2020-12-31 | 2020-12-31 | COMP | 2021-02-18 | COMP | 2021-02-18 | COMP | 2022-05-28 | INPR | 2021-04-28 | COMP | Rule 16 | 60 | 163 | 33 | 1 |  |  | 303
19596 | 2020-02-17 | 2020-05-14 | 2020-06-12 | 2020-06-12 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-10-22 | COMP | Rule 16 | 63 | 21 | 43 | 1 | 1 | 52 | 176
19849 | 2020-02-17 | 2020-05-26 | 2020-06-30 | 2020-06-30 | COMP | 2020-08-10 | COMP | 2020-08-10 | COMP | 2021-03-25 | COMP | 2021-04-27 | COMP | Rule 16 | 70 | 26 | 30 | 1 | 156 | 24 | 302
20814 | 2020-02-17 | 2020-07-07 | 2020-09-04 | 2020-09-04 | COMP | 2020-09-15 | COMP | 2020-09-15 | COMP | 2020-12-22 | COMP | 2021-02-10 | COMP | Rule 16 | 100 | 44 | 7 | 1 | 68 | 34 | 249
23551 | 2020-02-17 | 2020-11-12 | 2020-12-08 | 2020-12-08 | COMP | 2020-12-17 | COMP | 2021-03-23 | COMP | 2021-10-01 | COMP | 2022-05-13 | COMP | Rule 16 | 190 | 17 | 8 | 65 | 136 | 156 | 567
17520 | 2020-02-18 | 2020-02-19 | 2020-06-02 | 2020-06-02 | COMP | 2020-09-01 | NOTN | 2020-12-04 | COMP | 2020-12-08 | COMP | 2021-01-15 | COMP | Other | 2 | 74 |  | 130 | 3 | 27 | 232
17545 | 2020-02-18 | 2020-02-20 | 2020-03-17 | 2020-03-17 | COMP | 2020-04-17 | COMP | 2020-04-17 | INPR | 2022-01-30 | REQD | 2020-06-15 | COMP | Rule 16 | 3 | 19 | 24 |  |  |  | 84
17674 | 2020-02-18 | 2020-02-25 | 2020-05-18 | 2020-05-18 | COMP | 2020-11-09 | COMP | 2022-02-09 | COMP | 2022-02-24 | COMP | 2022-03-24 | COMP | Rule 16 | 6 | 60 | 124 | 314 | 11 | 21 | 531
17824 | 2020-02-18 | 2020-02-28 | 2020-04-16 | 2020-04-16 | COMP | 2020-06-24 | COMP | 2021-02-18 | COMP | 2021-10-12 | COMP | 2023-06-14 | COMP | Rule 15/16 | 9 | 35 | 49 | 164 | 166 | 420 | 838
17856 | 2020-02-18 | 2020-03-02 | 2020-05-07 | 2020-05-07 | COMP | 2020-06-04 | COMP | 2020-06-04 | COMP | 2020-07-01 | COMP | 2020-07-16 | COMP | Rule 15/16 | 10 | 49 | 20 | 1 | 20 | 12 | 107
17911 | 2020-02-18 | 2020-03-04 | 2020-05-12 | 2020-05-12 | COMP | 2020-05-28 | COMP | 2020-06-04 | COMP | 2020-06-23 | COMP | 2020-07-14 | COMP | Rule 16 | 12 | 50 | 12 | 6 | 14 | 16 | 105
17948 | 2020-02-18 | 2020-03-05 | 2020-12-14 | 2021-07-15 | COMP | 2021-09-03 | COMP | 2022-03-14 | COMP | 2023-08-28 | COMP | 2023-09-14 | COMP | Rule 15/16 | 13 | 198 | 37 | 131 | 367 | 13 | 901
18024 | 2020-02-18 | 2020-03-09 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-06-25 | COMP | 2020-08-05 | COMP | Rule 16 | 15 | 56 | 16 | 1 | 8 | 30 | 121
18057 | 2020-02-18 | 2020-03-10 | 2020-06-24 | 2020-06-24 | COMP | 2020-11-05 | COMP | 2021-03-05 | COMP | 2021-06-16 | COMP | 2021-08-13 | COMP | Rule 15/16 | 16 | 76 | 96 | 80 | 73 | 42 | 378
18094 | 2020-02-18 | 2020-03-10 | 2020-06-19 | 2020-09-04 | COMP | 2020-10-05 | COMP | 2020-10-05 | COMP |  | INPR | 2021-02-27 | COMP | Rule 16 | 16 | 73 | 21 | 1 |  |  | 260
18101 | 2020-02-18 | 2020-03-10 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2020-07-29 | COMP | 2020-08-03 | COMP | Rule 16 | 16 | 42 | 12 | 1 | 49 | 4 | 119
18141 | 2020-02-18 | 2020-03-12 | 2020-06-05 | 2020-06-05 | COMP | 2020-07-29 | COMP | 2020-08-10 | COMP | 2020-11-05 | COMP | 2020-12-04 | COMP | Rule 16 | 18 | 61 | 39 | 9 | 63 | 19 | 204
18187 | 2020-02-18 | 2020-03-13 | 2020-12-02 | 2020-12-02 | COMP | 2021-01-29 | COMP | 2021-03-24 | COMP | 2022-05-28 | INPR | 2021-04-20 | COMP | Rule 16 | 19 | 184 | 40 | 38 |  |  | 297
18191 | 2020-02-18 | 2020-03-14 | 2020-05-13 | 2020-05-13 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2021-05-19 | COMP | 2021-05-27 | COMP | Rule 16 | 19 | 43 | 112 | 1 | 146 | 7 | 324
18218 | 2020-02-18 | 2020-03-16 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-14 | COMP | 2020-04-14 | COMP | 2022-01-30 | INPR | 2020-06-22 | COMP | Rule 16 | 20 | 15 | 8 | 1 |  |  | 89
18227 | 2020-02-18 | 2020-03-16 | 2020-12-04 | 2020-12-04 | COMP | 2021-04-20 | COMP | 2021-04-20 | COMP | 2021-04-20 | COMP | 2022-09-26 | COMP | Rule 15/16 | 20 | 185 | 94 | 1 | 1 | 363 | 659
18260 | 2020-02-18 | 2020-03-17 | 2020-05-18 | 2020-05-18 | COMP | 2020-05-29 | COMP | 2020-05-29 | INPR | 2020-08-24 | COMP | 2020-09-12 | COMP | Rule 16 | 21 | 45 | 9 |  |  |  | 147
18262 | 2020-02-18 | 2020-03-17 | 2020-05-27 | 2020-05-27 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-03-03 | COMP | 2021-04-12 | COMP | Rule 16 | 21 | 51 | 89 | 1 | 105 | 29 | 291
18379 | 2020-02-18 | 2020-03-22 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-11 | COMP | 2020-09-04 | COMP | 2020-07-17 | COMP | 2020-11-03 | COMP | Rule 16 | 24 | 54 | 5 | 62 | 0 | 42 | 184
18408 | 2020-02-18 | 2020-03-23 | 2021-01-14 | 2021-01-14 | COMP | 2021-03-02 | COMP | 2022-04-26 | COMP | 2022-05-03 | COMP | 2022-05-06 | COMP | Rule 15/16 | 25 | 207 | 32 | 293 | 6 | 4 | 562
18512 | 2020-02-18 | 2020-03-28 | 2020-05-14 | 2020-05-15 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-08-24 | COMP | 2020-10-06 | COMP | Rule 16 | 29 | 34 | 40 | 1 | 32 | 31 | 164
18579 | 2020-02-18 | 2020-03-30 | 2020-06-25 | 2020-06-26 | COMP | 2020-07-24 | COMP | 2020-08-08 | COMP | 2020-08-24 | COMP | 2020-10-28 | COMP | Rule 15/16 | 30 | 63 | 21 | 11 | 11 | 47 | 180
18625 | 2020-02-18 | 2020-03-31 | 2021-01-20 | 2021-01-20 | COMP | 2021-01-27 | COMP | 2021-04-27 | COMP | 2021-08-19 | COMP | 2021-12-21 | COMP | Rule 16 | 31 | 204 | 6 | 64 | 81 | 85 | 466
18628 | 2020-02-18 | 2020-03-31 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-13 | COMP | 2020-06-19 | COMP | 2020-06-04 | COMP | 2020-07-01 | COMP | Rule 16 | 31 | 29 | 4 | 27 | 0 | 9 | 96
18677 | 2020-02-18 | 2020-04-02 | 2020-08-12 | 2020-08-12 | COMP | 2020-10-23 | COMP | 2020-11-19 | COMP | 2021-01-19 | COMP | 2021-02-11 | COMP | Rule 15/16 | 33 | 94 | 52 | 19 | 39 | 18 | 250
18763 | 2020-02-18 | 2020-04-06 | 2020-05-31 | 2020-05-31 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-12-19 | COMP | 2021-01-19 | COMP | Rule 16 | 35 | 39 | 21 | 1 | 121 | 19 | 233
18841 | 2020-02-18 | 2020-04-08 | 2020-06-08 | 2020-06-08 | COMP | 2020-09-03 | COMP | 2021-01-14 | COMP | 2021-04-28 | COMP | 2021-06-03 | COMP | Rule 15/16 | 37 | 43 | 64 | 90 | 73 | 26 | 328
18972 | 2020-02-18 | 2020-04-15 | 2020-08-15 | 2020-08-15 | COMP | 2020-11-02 | COMP | 2023-06-08 | COMP | 2023-06-02 | COMP | 2023-07-03 | COMP | Rule 16 | 42 | 87 | 55 | 652 | 0 | 17 | 850
19046 | 2020-02-18 | 2020-04-19 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-13 | COMP | Rule 16 | 44 | 20 | 20 | 1 | 1 | 22 | 104
19490 | 2020-02-18 | 2020-05-08 | 2021-03-02 | 2021-03-02 | COMP | 2021-04-05 | COMP | 2021-04-21 | COMP | 2022-01-13 | COMP | 2022-01-13 | COMP | Rule 16 | 59 | 204 | 25 | 13 | 186 | 1 | 483
19547 | 2020-02-18 | 2020-05-12 | 2021-01-21 | 2021-01-21 | COMP | 2021-03-30 | COMP | 2023-05-03 | COMP | 2023-05-02 | COMP | 2023-06-07 | COMP | Rule 16 | 61 | 175 | 48 | 528 | 0 | 25 | 833
19988 | 2020-02-18 | 2020-06-01 | 2020-09-08 | 2020-09-08 | COMP | 2021-01-28 | COMP | 2021-02-27 | COMP | 2021-03-16 | COMP | 2021-08-10 | COMP | Other | 74 | 71 | 97 | 21 | 12 | 104 | 375
21002 | 2020-02-18 | 2020-07-17 | 2020-08-04 | 2020-08-04 | COMP | 2020-12-02 | COMP | 2020-12-02 | NOTN | 2020-12-04 | COMP | 2020-12-10 | COMP | Rule 16 | 108 | 13 | 83 |  |  |  | 208
21313 | 2020-02-18 | 2020-07-31 | 2021-08-21 | 2021-08-21 | COMP | 2021-09-16 | COMP | 2021-09-16 | COMP | 2021-11-10 | COMP | 2021-11-17 | COMP | Rule 16 | 118 | 266 | 18 | 1 | 40 | 5 | 444
24764 | 2020-02-18 | 2021-01-11 | 2021-03-19 | 2021-03-19 | COMP | 2021-09-15 | COMP | 2021-09-15 | COMP | 2021-09-21 | COMP | 2021-11-16 | COMP | Rule 16 | 228 | 48 | 126 | 1 | 5 | 40 | 443
33056 | 2020-02-18 | 2021-12-13 | 2022-03-11 | 2022-03-11 | COMP | 2022-03-08 | NOTN | 2022-04-01 | INPR | 2022-04-05 | COMP | 2022-04-07 | COMP | Other | 460 | 63 |  |  |  |  | 541
4326 | 2020-02-19 | 2021-01-05 | 2021-10-14 | 2021-03-18 | COMP |  |  |  |  | 2022-11-30 | COMP | 2022-07-08 | COMP | Other | 223 | 198 |  |  |  |  | 603
17524 | 2020-02-19 | 2020-02-19 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-13 | COMP | 2020-07-06 | COMP | 2020-08-04 | NOTN | 2020-08-06 | COMP | Rule 15/16 | 1 | 55 | 7 | 38 |  |  | 121
17638 | 2020-02-19 | 2020-02-24 | 2020-07-29 | 2020-07-29 | COMP | 2021-01-19 | NOTN | 2021-01-27 | COMP | 2021-02-03 | COMP | 2021-02-17 | COMP | Other | 4 | 112 |  | 124 | 6 | 10 | 252
17825 | 2020-02-19 | 2020-02-28 | 2020-04-22 | 2020-04-22 | COMP | 2020-06-01 | COMP | 2020-09-23 | COMP | 2020-11-13 | COMP | 2021-01-14 | COMP | Rule 16 | 8 | 39 | 28 | 82 | 37 | 41 | 230
17870 | 2020-02-19 | 2020-03-03 | 2020-08-26 | 2020-08-26 | COMP | 2020-09-25 | COMP | 2020-10-23 | COMP | 2021-02-12 | COMP | 2021-04-08 | COMP | Rule 16 | 10 | 126 | 22 | 21 | 75 | 39 | 288
18029 | 2020-02-19 | 2020-03-09 | 2020-03-30 | 2020-03-30 | COMP | 2020-04-02 | COMP | 2020-07-22 | NOTN | 2020-07-22 | COMP | 2020-08-12 | COMP | Rule 16 | 14 | 16 | 4 |  |  |  | 125
18139 | 2020-02-19 | 2020-03-12 | 2020-12-14 | 2020-12-14 | COMP | 2021-03-16 | COMP | 2021-05-25 | COMP | 2021-04-26 | COMP | 2021-08-31 | COMP | Rule 15/16 | 17 | 193 | 63 | 51 | 0 | 69 | 389
18162 | 2020-02-19 | 2020-03-12 | 2020-05-08 | 2020-05-13 | COMP | 2020-05-22 | COMP | 2020-06-01 | COMP | 2020-05-21 | COMP | 2020-06-19 | COMP | Rule 16 | 17 | 42 | 8 | 6 | 0 | 15 | 87
18268 | 2020-02-19 | 2020-03-18 | 2020-05-22 | 2020-05-22 | COMP | 2020-07-16 | COMP | 2020-07-16 | COMP | 2020-07-17 | COMP | 2020-07-22 | COMP | Rule 16 | 21 | 48 | 39 | 1 | 2 | 4 | 110
18444 | 2020-02-19 | 2020-03-30 | 2020-10-26 | 2020-10-26 | COMP | 2020-11-13 | COMP | 2021-01-06 | COMP | 2022-07-16 | INPR | 2021-02-20 | COMP | Rule 16 | 29 | 149 | 14 | 35 |  |  | 254
18457 | 2020-02-19 | 2020-03-25 | 2020-06-11 | 2020-10-28 | COMP | 2020-11-20 | COMP | 2020-08-14 | COMP | 2020-08-26 | COMP | 2021-02-22 | COMP | Rule 16 | 26 | 56 | 17 |  | 9 | 121 | 255
18495 | 2020-02-19 | 2020-03-26 | 2020-04-26 | 2020-04-26 | COMP | 2020-04-28 | NOTN | 2020-05-18 | COMP | 2020-04-28 | COMP | 2020-06-10 | COMP | Other | 27 | 22 |  | 16 | 0 | 17 | 80
18594 | 2020-02-19 | 2020-03-30 | 2020-10-23 | 2020-10-23 | COMP | 2020-12-15 | COMP | 2021-01-13 | COMP | 2021-01-05 | COMP | 2021-01-21 | COMP | Rule 16 | 29 | 148 | 35 | 20 | 0 | 6 | 234
18612 | 2020-02-19 | 2020-03-31 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-19 | COMP | 2021-06-28 | COMP | 2021-05-25 | COMP | 2021-08-06 | COMP | Other | 30 | 34 | 25 | 258 | 0 | 29 | 372
18738 | 2020-02-19 | 2020-04-06 | 2020-08-27 | 2020-08-27 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2020-11-06 | COMP | 2020-11-13 | COMP | Rule 16 | 34 | 103 | 15 | 1 | 37 | 5 | 190
18778 | 2020-02-19 | 2020-04-07 | 2020-06-02 | 2020-06-02 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-09-11 | COMP | 2020-09-22 | COMP | Rule 16 | 35 | 40 | 29 | 1 | 45 | 8 | 153
18807 | 2020-02-19 | 2020-04-08 | 2020-10-15 | 2020-10-15 | COMP | 2021-09-21 | COMP | 2021-11-04 | COMP | 2022-01-25 | COMP | 2022-02-09 | COMP | Rule 16 | 36 | 135 | 234 | 33 | 55 | 12 | 500
18811 | 2020-02-19 | 2020-04-07 | 2020-11-04 | 2020-11-20 | COMP | 2021-01-08 | COMP | 2021-01-08 | COMP | 2021-02-16 | COMP | 2021-02-22 | COMP | Rule 15/16 | 35 | 150 | 32 | 1 | 26 | 5 | 255
18946 | 2020-02-19 | 2020-04-14 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-07-08 | COMP | 2020-07-24 | COMP | Rule 16 | 40 | 31 | 20 | 1 | 12 | 13 | 112
19040 | 2020-02-19 | 2020-04-20 | 2020-08-03 | 2020-08-03 | COMP | 2021-01-04 | COMP | 2021-01-04 | COMP | 2021-03-11 | COMP | 2021-03-31 | COMP | Rule 16 | 44 | 75 | 105 | 1 | 47 | 15 | 282
19207 | 2020-02-19 | 2020-04-24 | 2020-10-23 | 2020-10-23 | COMP | 2020-11-05 | COMP | 2021-01-22 | COMP | 2020-12-30 | COMP | 2021-02-18 | COMP | Rule 16 | 48 | 129 | 10 | 51 | 0 | 19 | 253
19605 | 2020-02-19 | 2020-05-14 | 2020-12-28 | 2020-12-28 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | 2021-06-22 | COMP | 2021-06-25 | COMP | Rule 16 | 62 | 157 | 15 | 1 | 109 | 4 | 343
20505 | 2020-02-19 | 2020-06-23 | 2020-11-13 | 2020-11-13 | COMP | 2021-04-27 | COMP | 2022-02-03 | COMP | 2022-05-10 | COMP | 2022-06-21 | COMP | Rule 15/16 | 89 | 102 | 112 | 196 | 68 | 29 | 591
20845 | 2020-02-19 | 2020-07-08 | 2020-08-18 | 2020-08-18 | COMP | 2021-05-26 | COMP | 2021-05-26 | COMP | 2021-05-22 | COMP | 2021-06-21 | COMP | Rule 16 | 100 | 30 | 194 | 1 | 0 | 18 | 339
20917 | 2020-02-19 | 2020-07-13 | 2020-09-23 | 2020-09-23 | COMP | 2020-09-28 | COMP | 2020-09-28 | COMP | 2020-10-20 | COMP | 2020-11-17 | COMP | Rule 16 | 103 | 52 | 4 | 1 | 17 | 20 | 192
21173 | 2020-02-19 | 2020-07-24 | 2020-10-12 | 2020-10-12 | COMP | 2020-10-16 | COMP |  | REQD | 2020-11-10 | COMP | 2020-11-14 | COMP | Rule 15/16 | 112 | 56 | 5 |  |  |  | 190
23733 | 2020-02-19 | 2020-11-20 | 2021-01-21 | 2021-02-24 | COMP | 2021-06-21 | COMP | 2021-06-21 | COMP | 2021-11-19 | COMP | 2022-01-13 | COMP | Rule 16 | 195 | 40 | 83 | 1 | 107 | 38 | 482
4277 | 2020-02-20 | 2020-03-04 | 2020-10-14 | 2020-10-14 | COMP | 2020-11-12 | COMP | 2021-01-20 | COMP | 2021-01-29 | COMP | 2021-04-13 | COMP | Rule 15/16 | 10 | 159 | 21 | 45 | 8 | 52 | 290
17644 | 2020-02-20 | 2020-02-24 | 2020-07-10 | 2020-07-24 | COMP | 2020-07-10 | NOTN | 2020-08-04 | COMP | 2020-07-10 | COMP | 2020-09-25 | COMP | Other | 3 | 99 |  | 8 | 0 | 38 | 155
17899 | 2020-02-20 | 2020-03-03 | 2020-05-01 | 2020-09-26 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2021-01-19 | COMP | 2021-11-04 | COMP | Rule 16 | 9 | 44 | 36 | 1 | 41 | 204 | 434
18125 | 2020-02-20 | 2020-03-12 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-02 | COMP | 2020-10-28 | COMP | 2020-12-16 | COMP | 2021-01-13 | COMP | Rule 16 | 16 | 38 | 21 | 106 | 33 | 19 | 228
18133 | 2020-02-20 | 2020-03-12 | 2020-06-24 | 2020-12-08 | COMP | 2021-04-28 | COMP | 2021-04-28 | COMP | 2021-10-04 | COMP | 2021-11-16 | COMP | Rule 15/16 | 16 | 74 | 98 | 1 | 111 | 31 | 441
18293 | 2020-02-20 | 2020-03-19 | 2020-06-17 | 2020-06-17 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-08-13 | COMP | Rule 16 | 21 | 64 | 10 | 1 | 1 | 33 | 125
18380 | 2020-02-20 | 2020-03-22 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-29 | COMP | 2020-08-04 | COMP | 2021-05-26 | COMP | 2021-06-15 | COMP | Rule 16 | 22 | 45 | 25 | 27 | 204 | 14 | 334
18414 | 2020-02-20 | 2020-03-23 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2021-03-30 | COMP | 2021-04-12 | COMP | Rule 16 | 23 | 69 | 25 | 1 | 166 | 10 | 289
18482 | 2020-02-20 | 2020-03-25 | 2020-09-19 | 2020-09-19 | COMP | 2020-11-03 | NOTN | 2020-11-16 | COMP | 2020-11-23 | COMP | 2021-02-10 | COMP | Other | 25 | 126 |  | 40 | 6 | 53 | 247
18496 | 2020-02-20 | 2020-03-26 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-06 | COMP | 2020-06-24 | COMP | 2020-07-06 | COMP | 2020-09-14 | COMP | Rule 16 | 26 | 26 | 5 | 35 | 9 | 50 | 146
18533 | 2020-02-20 | 2020-03-27 | 2020-05-30 | 2020-06-02 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-06-30 | COMP | 2020-08-03 | COMP | Rule 16 | 27 | 45 | 15 | 1 | 7 | 25 | 117
18631 | 2020-02-20 | 2020-04-01 | 2020-07-24 | 2020-07-24 | COMP | 2020-07-31 | COMP | 2020-09-11 | COMP | 2020-10-05 | COMP | 2020-10-23 | COMP | Rule 16 | 30 | 82 | 6 | 30 | 17 | 15 | 175
18871 | 2020-02-20 | 2020-04-09 | 2020-08-05 | 2020-08-05 | COMP | 2020-08-12 | COMP | 2020-10-28 | COMP | 2020-09-08 | COMP | 2020-10-29 | COMP | Rule 16 | 36 | 84 | 6 | 55 | 0 | 2 | 179
18904 | 2020-02-20 | 2020-04-10 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-08-10 | COMP | 2020-09-18 | COMP | Rule 16 | 37 | 55 | 5 | 1 | 28 | 29 | 150
18948 | 2020-02-20 | 2020-04-14 | 2020-10-24 | 2020-10-24 | COMP | 2020-11-23 | COMP | 2021-04-20 | COMP | 2021-04-02 | COMP | 2021-10-28 | COMP | Rule 15/16 | 39 | 137 | 20 | 101 | 0 | 135 | 429
19150 | 2020-02-20 | 2020-04-22 | 2020-06-09 | 2020-06-09 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-11-09 | COMP | 2021-03-01 | COMP | Rule 16 | 45 | 34 | 21 | 1 | 89 | 74 | 259
19202 | 2020-02-20 | 2020-04-23 | 2020-08-28 | 2020-08-28 | COMP | 2020-09-01 | COMP | 2020-09-21 | COMP | 2020-12-07 | COMP | 2021-02-20 | COMP | Rule 16 | 46 | 91 | 3 | 14 | 53 | 51 | 253
19434 | 2020-02-20 | 2020-05-07 | 2020-09-11 | 2020-09-11 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2021-03-13 | COMP | 2021-05-04 | COMP | Rule 16 | 56 | 90 | 51 | 1 | 74 | 37 | 305
19457 | 2020-02-20 | 2020-05-07 | 2020-06-01 | 2020-06-01 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2020-08-12 | COMP | 2020-08-26 | COMP | Rule 16 | 56 | 17 | 60 | 1 | 0 | 4 | 134
19573 | 2020-02-20 | 2020-05-13 | 2020-08-13 | 2020-08-13 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-10-15 | COMP | 2020-11-09 | COMP | Rule 16 | 60 | 66 | 43 | 1 | 3 | 18 | 186
19650 | 2020-02-20 | 2020-05-15 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-13 | COMP | 2020-09-23 | COMP | 2023-05-27 | INPR | 2020-11-10 | COMP | Rule 16 | 62 | 26 | 16 | 52 |  |  | 187
19673 | 2020-02-20 | 2020-05-17 | 2020-06-18 | 2021-03-23 | COMP | 2021-03-25 | COMP | 2020-12-15 | COMP | 2021-02-17 | COMP | 2021-04-14 | COMP | Rule 16 | 62 | 23 | 3 |  | 43 | 41 | 291
19688 | 2020-02-20 | 2020-05-17 | 2020-07-10 | 2020-07-10 | COMP | 2020-09-08 | COMP | 2020-10-27 | COMP | 2020-12-15 | COMP | 2021-01-06 | COMP | Rule 16 | 62 | 39 | 42 | 36 | 33 | 15 | 223
19689 | 2020-02-20 | 2020-05-17 | 2020-07-02 | 2020-07-02 | COMP | 2021-01-26 | COMP | 2021-05-17 | COMP | 2021-06-25 | COMP | 2021-07-29 | COMP | Rule 16 | 62 | 33 | 142 | 79 | 29 | 24 | 365
19741 | 2020-02-20 | 2020-05-20 | 2020-09-02 | 2020-09-02 | COMP | 2020-11-09 | COMP | 2020-11-09 | COMP | 2021-01-12 | COMP | 2021-01-13 | COMP | Rule 15/16 | 65 | 75 | 48 | 1 | 42 | 2 | 228
19798 | 2020-02-20 | 2020-05-21 | 2020-08-25 | 2020-08-25 | COMP | 2020-12-02 | COMP | 2020-12-02 | COMP | 2021-02-16 | COMP | 2021-03-23 | COMP | Rule 16 | 66 | 68 | 68 | 1 | 51 | 26 | 275
19927 | 2020-02-20 | 2020-05-28 | 2021-06-08 | 2021-06-08 | COMP | 2021-06-14 | COMP | 2021-07-16 | COMP | 2022-07-26 | COMP | 2022-07-26 | COMP | Rule 16 | 70 | 260 | 5 | 24 | 259 | 1 | 614
19966 | 2020-02-20 | 2020-05-29 | 2020-06-29 | 2020-06-29 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-10-06 | COMP | 2020-10-19 | COMP | Rule 16 | 71 | 22 | 45 | 1 | 27 | 10 | 171
20058 | 2020-02-20 | 2020-06-02 | 2020-10-05 | 2020-10-05 | COMP | 2020-12-10 | COMP | 2021-03-30 | COMP | 2021-03-30 | COMP | 2021-06-17 | COMP | Rule 15/16 | 73 | 89 | 46 | 75 | 1 | 57 | 336
20274 | 2020-02-20 | 2020-06-12 | 2020-07-29 | 2020-07-29 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-12-29 | COMP | 2021-06-15 | COMP | Rule 16 | 81 | 34 | 20 | 1 | 86 | 117 | 334
20391 | 2020-02-20 | 2020-06-17 | 2020-07-17 | 2020-07-17 | COMP | 2021-08-17 | COMP | 2022-10-14 | COMP | 2022-10-05 | COMP | 2023-01-24 | COMP | Rule 16 | 84 | 23 | 273 | 294 | 0 | 67 | 737
20392 | 2020-02-20 | 2020-06-17 | 2020-07-31 | 2020-07-31 | COMP | 2021-03-17 | COMP | 2022-11-08 | COMP | 2022-10-05 | COMP | 2023-02-02 | COMP | Rule 16 | 84 | 33 | 156 | 418 | 0 | 57 | 744
20488 | 2020-02-20 | 2020-06-22 | 2020-08-20 | 2020-08-20 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2021-02-11 | COMP | 2021-06-07 | COMP | Rule 16 | 87 | 44 | 23 | 1 | 97 | 81 | 328
20661 | 2020-02-20 | 2020-07-01 | 2020-09-08 | 2020-09-08 | COMP | 2020-12-14 | COMP | 2020-12-30 | COMP | 2021-07-06 | COMP | 2021-07-26 | COMP | Rule 16 | 94 | 49 | 67 | 12 | 130 | 15 | 362
20802 | 2020-02-20 | 2020-07-06 | 2020-08-19 | 2020-08-19 | COMP | 2020-10-01 | COMP | 2020-10-01 | COMP | 2020-11-02 | COMP | 2020-11-17 | COMP | Rule 16 | 97 | 33 | 31 | 1 | 23 | 11 | 191
21430 | 2020-02-20 | 2020-08-06 | 2020-10-23 | 2020-10-23 | COMP | 2020-11-03 | COMP | 2021-04-09 | COMP | 2021-05-25 | COMP | 2021-06-15 | COMP | Rule 16 | 120 | 56 | 8 | 107 | 33 | 15 | 334
22098 | 2020-02-20 | 2020-09-10 | 2020-10-29 | 2020-10-29 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2021-02-08 | COMP | 2021-02-16 | COMP | Rule 16 | 144 | 36 | 13 | 1 | 55 | 6 | 250
17823 | 2020-02-21 | 2020-02-28 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-11 | COMP | 2020-07-07 | COMP | 2020-07-17 | COMP | 2020-08-05 | COMP | Rule 16 | 6 | 68 | 7 | 19 | 9 | 14 | 118
17991 | 2020-02-21 | 2020-03-06 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2021-02-26 | COMP | 2021-04-09 | COMP | Rule 16 | 11 | 72 | 31 | 1 | 146 | 31 | 287
18082 | 2020-02-21 | 2020-03-10 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | 2020-04-24 | COMP | Rule 16 | 13 | 24 | 11 | 1 | 1 | 1 | 46
18140 | 2020-02-21 | 2020-03-12 | 2021-02-09 | 2021-02-09 | COMP | 2021-03-31 | COMP | 2021-05-05 | COMP | 2021-06-14 | COMP | 2021-06-11 | COMP | Rule 15/16 | 15 | 231 | 36 | 26 | 28 |  | 331
18206 | 2020-02-21 | 2020-03-16 | 2021-01-03 | 2021-01-03 | COMP | 2021-05-28 | COMP | 2021-05-28 | COMP | 2021-06-30 | COMP | 2021-10-23 | COMP | Rule 15/16 | 17 | 203 | 103 | 1 | 23 | 81 | 424
18277 | 2020-02-21 | 2020-03-18 | 2020-07-22 | 2020-07-22 | COMP | 2020-07-30 | COMP | 2020-10-29 | COMP | 2021-01-20 | COMP | 2021-02-12 | COMP | Rule 16 | 19 | 90 | 7 | 65 | 54 | 18 | 248
18339 | 2020-02-21 | 2020-03-19 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-04 | COMP | 2020-05-05 | COMP | 2020-05-04 | COMP | 2020-06-09 | COMP | Rule 15/16 | 20 | 28 | 6 | 2 | 0 | 25 | 77
18373 | 2020-02-21 | 2020-03-21 | 2020-07-01 | 2021-05-25 | COMP | 2021-06-21 | COMP | 2021-10-28 | COMP | 2021-10-28 | COMP | 2022-01-13 | COMP | Rule 16 | 21 | 72 | 19 | 92 | 1 | 53 | 480
18491 | 2020-02-21 | 2020-03-26 | 2020-07-28 | 2020-07-28 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2020-12-07 | COMP | 2020-12-31 | COMP | Rule 15/16 | 25 | 88 | 67 | 1 | 25 | 18 | 219
18647 | 2020-02-21 | 2020-04-01 | 2020-07-05 | 2020-07-05 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-09-02 | COMP | 2020-09-25 | COMP | Rule 16 | 29 | 67 | 17 | 1 | 27 | 17 | 154
18892 | 2020-02-21 | 2020-04-10 | 2020-09-15 | 2020-09-15 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2020-10-12 | COMP | 2020-12-11 | COMP | Rule 16 | 36 | 111 | 18 | 1 | 3 | 42 | 206
19085 | 2020-02-21 | 2020-04-20 | 2020-10-23 | 2020-10-23 | COMP | 2021-02-02 | COMP | 2021-02-02 | COMP | 2021-03-19 | COMP | 2021-04-07 | COMP | Rule 16 | 42 | 133 | 67 | 1 | 33 | 14 | 285
19138 | 2020-02-21 | 2020-04-21 | 2020-08-20 | 2020-08-20 | COMP | 2020-08-20 | NOTN | 2021-10-28 | COMP | 2023-07-30 | COMP | 2023-12-14 | COMP | Other | 43 | 87 |  | 300 | 438 | 95 | 960
19224 | 2020-02-21 | 2020-04-27 | 2020-10-22 | 2020-10-22 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2023-12-03 | INPR | 2021-05-06 | COMP | Rule 16 | 47 | 127 | 39 | 1 |  |  | 306
19253 | 2020-02-21 | 2020-04-28 | 2020-07-13 | 2020-09-02 | COMP | 2020-10-30 | COMP | 2020-07-16 | COMP | 2020-10-06 | COMP | 2020-12-15 | COMP | Rule 16 | 48 | 54 | 42 |  | 58 | 48 | 208
19436 | 2020-02-21 | 2020-05-07 | 2020-08-17 | 2020-08-17 | COMP | 2020-08-28 | COMP | 2020-09-14 | COMP | 2020-08-31 | COMP | 2020-12-10 | COMP | Rule 16 | 55 | 72 | 10 | 11 | 0 | 61 | 205
19640 | 2020-02-21 | 2020-05-15 | 2020-08-12 | 2020-09-11 | COMP | 2020-09-29 | COMP | 2020-11-29 | COMP | 2020-12-02 | COMP | 2021-01-12 | COMP | Rule 16 | 61 | 63 | 13 | 41 | 3 | 28 | 226
19712 | 2020-02-21 | 2020-05-19 | 2020-10-30 | 2021-03-17 | COMP | 2021-12-10 | COMP | 2021-12-16 | COMP | 2022-02-15 | COMP | 2022-11-15 | COMP | Rule 16 | 63 | 117 | 187 | 5 | 43 | 190 | 691
19728 | 2020-02-21 | 2020-05-19 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-01 | COMP | 2020-07-23 | COMP | 2020-07-20 | COMP | 2020-09-07 | COMP | Rule 16 | 63 | 21 | 11 | 17 | 0 | 32 | 140
19765 | 2020-02-21 | 2020-05-20 | 2020-11-14 | 2020-12-09 | COMP | 2020-12-29 | COMP | 2021-03-11 | COMP | 2021-05-18 | COMP | 2021-06-08 | COMP | Rule 15/16 | 64 | 125 | 14 | 50 | 49 | 15 | 328
19884 | 2020-02-21 | 2020-05-27 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2020-09-03 | COMP | 2020-10-09 | COMP | Rule 16 | 68 | 35 | 13 | 1 | 26 | 26 | 164
19900 | 2020-02-21 | 2020-05-27 | 2020-07-17 | 2020-07-17 | COMP | 2020-07-21 | COMP | 2020-08-13 | COMP | 2022-01-31 | INPR | 2020-08-19 | COMP | Rule 16 | 68 | 38 | 3 | 18 |  |  | 128
20009 | 2020-02-21 | 2020-06-01 | 2020-09-09 | 2020-09-09 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-12-29 | COMP | 2021-01-11 | COMP | Rule 16 | 71 | 72 | 30 | 1 | 47 | 9 | 225
20078 | 2020-02-21 | 2020-06-03 | 2020-06-12 | 2020-06-12 | COMP | 2021-05-13 | COMP | 2022-03-11 | COMP | 2022-03-22 | COMP | 2022-04-23 | COMP | Rule 16 | 73 | 8 | 232 | 209 | 8 | 24 | 549
20456 | 2020-02-21 | 2020-06-20 | 2021-02-19 | 2021-02-19 | COMP | 2021-03-25 | COMP | 2021-08-05 | COMP | 2021-12-16 | COMP | 2022-01-14 | COMP | Rule 16 | 85 | 167 | 25 | 94 | 92 | 22 | 481
20518 | 2020-02-21 | 2020-06-24 | 2020-10-28 | 2021-10-05 | COMP | 2022-01-05 | COMP | 2021-03-01 | COMP | 2022-01-05 | COMP | 2022-05-14 | COMP | Rule 16 | 88 | 90 | 64 |  | 217 | 91 | 564
20634 | 2020-02-21 | 2020-06-30 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2021-01-26 | COMP | 2021-02-06 | COMP | Rule 16 | 92 | 26 | 19 | 1 | 101 | 9 | 243
21030 | 2020-02-21 | 2020-07-18 | 2021-07-20 | 2021-07-20 | COMP | 2021-09-14 | COMP | 2022-04-22 | COMP | 2023-12-06 | COMP | 2023-04-11 | COMP | Rule 15/16 | 105 | 252 | 40 | 154 | 406 |  | 790
22463 | 2020-02-21 | 2020-09-25 | 2020-10-15 | 2020-10-15 | COMP | 2021-02-01 | COMP | 2021-02-01 | COMP | 2021-02-17 | COMP | 2021-02-23 | COMP | Rule 16 | 154 | 15 | 72 | 1 | 12 | 5 | 254
28064 | 2020-02-21 | 2021-05-18 | 2021-09-24 | 2021-09-24 | COMP | 2021-11-10 | COMP | 2022-04-05 | COMP | 2022-04-12 | COMP | 2022-06-29 | COMP | Rule 16 | 314 | 91 | 34 | 100 | 6 | 55 | 595
18078 | 2020-02-22 | 2020-03-10 | 2020-06-28 | 2020-08-19 | COMP | 2020-09-09 | COMP | 2020-10-22 | COMP | 2020-11-16 | COMP | 2020-12-08 | COMP | Rule 16 | 12 | 78 | 15 | 32 | 17 | 15 | 202
18381 | 2020-02-22 | 2020-03-22 | 2020-07-06 | 2020-07-06 | COMP | 2020-08-31 | COMP | 2020-11-09 | COMP | 2021-03-10 | COMP | 2021-03-11 | COMP | Rule 16 | 20 | 75 | 41 | 50 | 81 | 2 | 265
18384 | 2020-02-22 | 2020-03-22 | 2020-07-28 | 2020-07-28 | COMP | 2021-06-29 | COMP | 2021-11-01 | COMP | 2021-11-12 | COMP | 2021-11-29 | COMP | Rule 15/16 | 20 | 91 | 232 | 88 | 9 | 10 | 446
18920 | 2020-02-22 | 2020-04-12 | 2020-07-09 | 2020-07-09 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-08-26 | COMP | Rule 16 | 35 | 63 | 2 | 1 | 1 | 34 | 132
19428 | 2020-02-22 | 2020-05-06 | 2020-09-18 | 2020-09-18 | COMP | 2020-11-24 | COMP | 2021-02-22 | COMP | 2021-03-01 | COMP | 2021-03-30 | COMP | Rule 15/16 | 53 | 96 | 47 | 59 | 6 | 22 | 278
19435 | 2020-02-22 | 2020-05-07 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-05 | COMP | 2020-10-02 | COMP | 2020-11-17 | COMP | 2020-12-08 | COMP | Rule 16 | 54 | 46 | 19 | 42 | 32 | 14 | 202
20233 | 2020-02-22 | 2020-06-11 | 2020-08-04 | 2021-04-12 | COMP | 2021-07-06 | COMP | 2021-07-08 | COMP | 2022-02-15 | COMP | 2022-03-29 | COMP | Rule 16 | 78 | 39 | 60 | 3 | 154 | 30 | 530
20440 | 2020-02-22 | 2020-06-20 | 2020-08-18 | 2020-08-18 | COMP | 2020-09-10 | COMP | 2020-12-16 | COMP | 2020-12-16 | COMP | 2021-02-05 | COMP | Rule 16 | 84 | 42 | 17 | 67 | 1 | 35 | 242
22855 | 2020-02-22 | 2020-10-14 | 2020-12-15 | 2020-12-15 | COMP | 2021-01-05 | COMP | 2021-06-03 | COMP | 2021-06-08 | COMP | 2021-07-01 | COMP | Rule 16 | 166 | 42 | 14 | 105 | 4 | 18 | 344
4284 | 2020-02-23 | 2020-03-23 | 2020-09-18 | 2020-09-18 | COMP | 2020-11-09 | COMP | 2022-01-06 | COMP | 2022-03-08 | COMP | 2022-04-30 | COMP | Rule 15/16 | 21 | 128 | 37 | 291 | 42 | 39 | 553
19056 | 2020-02-23 | 2020-04-19 | 2020-07-25 | 2020-08-31 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | 2021-03-04 | COMP | 2021-04-15 | COMP | Rule 16 | 40 | 69 | 12 | 1 | 115 | 31 | 290
19291 | 2020-02-23 | 2020-04-28 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-10-30 | COMP | 2020-11-06 | COMP | Rule 16 | 47 | 6 | 26 | 1 | 102 | 6 | 183
21270 | 2020-02-23 | 2020-07-30 | 2020-09-03 | 2020-09-03 | COMP | 2020-09-14 | COMP | 2020-10-27 | COMP | 2021-03-22 | COMP | 2021-06-11 | COMP | Rule 16 | 113 | 26 | 7 | 32 | 98 | 59 | 330
17785 | 2020-02-24 | 2020-02-28 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-16 | COMP | 2020-04-16 | COMP | 2022-01-30 | INPR | 2020-06-18 | COMP | Rule 16 | 5 | 27 | 9 | 1 |  |  | 83
17811 | 2020-02-24 | 2020-02-28 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-28 | COMP | 2020-04-28 | COMP | 2020-09-02 | COMP | 2020-09-16 | COMP | Rule 16 | 5 | 33 | 11 | 1 | 91 | 10 | 146
17813 | 2020-02-24 | 2020-02-28 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-10-17 | COMP | 2020-11-17 | COMP | Rule 16 | 5 | 52 | 11 | 1 | 103 | 21 | 189
17829 | 2020-02-24 | 2020-02-28 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-26 | COMP | 2020-06-04 | COMP | 2021-01-04 | COMP | 2021-01-09 | COMP | Rule 16 | 5 | 54 | 9 | 8 | 147 | 5 | 223
17968 | 2020-02-24 | 2020-03-05 | 2020-03-24 | 2020-03-24 | COMP | 2020-04-15 | COMP | 2020-04-17 | COMP | 2020-04-15 | COMP | 2020-04-29 | COMP | Rule 16 | 9 | 14 | 17 | 3 | 0 | 9 | 48
18048 | 2020-02-24 | 2020-03-09 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-29 | COMP | 2020-07-29 | COMP | 2020-09-24 | COMP | 2020-10-15 | COMP | Rule 16 | 11 | 75 | 28 | 1 | 41 | 16 | 167
18223 | 2020-02-24 | 2020-03-17 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-21 | COMP | 2020-05-21 | COMP | 2022-07-30 | INPR | 2020-07-03 | COMP | Rule 16 | 17 | 33 | 16 | 1 |  |  | 94
18314 | 2020-02-24 | 2020-03-19 | 2020-03-30 | 2020-03-30 | COMP | 2020-03-31 | NOTN | 2020-03-31 | COMP | 2020-04-14 | COMP | 2020-05-16 | COMP | Other | 19 | 8 |  | 2 | 11 | 24 | 60
18363 | 2020-02-24 | 2020-03-21 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-17 | COMP | 2021-10-21 | COMP | 2022-01-26 | COMP | 2022-03-06 | COMP | Rule 16 | 20 | 51 | 12 | 341 | 66 | 27 | 513
18401 | 2020-02-24 | 2020-03-23 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-25 | COMP | 2020-06-25 | COMP | 2020-07-06 | COMP | 2020-08-16 | COMP | Rule 16 | 21 | 58 | 11 | 1 | 8 | 30 | 124
18402 | 2020-02-24 | 2020-03-23 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-11 | COMP | 2020-05-11 | COMP | 2020-12-14 | COMP | 2020-12-18 | COMP | Rule 16 | 21 | 23 | 14 | 1 | 151 | 5 | 210
18406 | 2020-02-24 | 2020-03-23 | 2020-04-21 | 2020-04-21 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-09-23 | COMP | 2020-10-03 | COMP | Rule 16 | 21 | 22 | 10 | 1 | 101 | 8 | 158
18517 | 2020-02-24 | 2020-03-27 | 2020-04-24 | 2020-04-24 | COMP | 2020-05-08 | COMP | 2020-05-08 | COMP | 2020-06-01 | COMP | 2020-06-05 | COMP | Rule 16 | 25 | 21 | 11 | 1 | 16 | 5 | 74
18580 | 2020-02-24 | 2020-03-30 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-01 | COMP | Rule 15/16 | 26 | 42 | 13 | 1 | 1 | 14 | 92
18646 | 2020-02-24 | 2020-04-01 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-08-12 | COMP | 2020-09-02 | COMP | Rule 16 | 28 | 37 | 28 | 1 | 32 | 16 | 137
18679 | 2020-02-24 | 2020-04-03 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-09-22 | COMP | 2020-09-30 | COMP | Rule 16 | 30 | 62 | 16 | 1 | 45 | 7 | 156
18853 | 2020-02-24 | 2020-04-09 | 2020-07-31 | 2020-07-31 | COMP | 2020-08-06 | COMP | 2020-09-14 | COMP | 2020-08-10 | COMP | 2020-09-29 | COMP | Rule 16 | 34 | 81 | 5 | 27 | 0 | 12 | 155
18861 | 2020-02-24 | 2020-04-09 | 2020-09-20 | 2020-09-20 | COMP | 2020-09-26 | NOTN | 2020-09-26 | COMP | 2020-10-23 | COMP | 2020-11-23 | COMP | Other | 34 | 115 |  | 5 | 20 | 21 | 193
18896 | 2020-02-24 | 2020-04-10 | 2020-08-09 | 2020-08-21 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-10-19 | COMP | 2020-11-12 | COMP | Rule 16 | 35 | 85 | 37 | 1 | 5 | 18 | 186
19039 | 2020-02-24 | 2020-04-20 | 2020-07-29 | 2020-07-29 | COMP | 2020-08-07 | COMP | 2020-10-08 | COMP | 2020-09-21 | COMP | 2020-12-15 | COMP | Rule 16 | 41 | 72 | 8 | 44 | 0 | 46 | 207
19051 | 2020-02-24 | 2020-04-19 | 2020-10-10 | 2020-10-10 | COMP | 2020-10-19 | COMP | 2021-05-17 | COMP | 2021-05-06 | COMP | 2021-06-03 | COMP | Rule 16 | 40 | 123 | 6 | 144 | 0 | 13 | 324
19168 | 2020-02-24 | 2020-04-23 | 2020-10-23 | 2020-10-23 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2021-06-07 | COMP | 2021-07-06 | COMP | Rule 15/16 | 44 | 130 | 38 | 1 | 117 | 21 | 346
19203 | 2020-02-24 | 2020-04-23 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-06-29 | COMP | 2020-07-21 | COMP | Rule 16 | 44 | 19 | 6 | 1 | 24 | 17 | 106
19208 | 2020-02-24 | 2020-04-24 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-09 | COMP | 2020-09-30 | COMP | 2020-11-03 | COMP | 2020-12-07 | COMP | Rule 16 | 45 | 91 | 7 | 16 | 25 | 22 | 201
19482 | 2020-02-24 | 2020-05-09 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-30 | COMP | 2020-07-21 | COMP | 2020-07-01 | COMP | 2020-08-24 | COMP | Rule 16 | 55 | 29 | 8 | 16 | 0 | 25 | 130
19495 | 2020-02-24 | 2020-05-09 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-10-22 | COMP | 2020-11-13 | COMP | Rule 16 | 55 | 29 | 16 | 1 | 74 | 16 | 187
19513 | 2020-02-24 | 2020-05-11 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-09-01 | COMP | 2021-01-13 | COMP | Rule 16 | 56 | 24 | 9 | 1 | 50 | 91 | 226
19597 | 2020-02-24 | 2020-05-14 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2021-01-26 | COMP | 2021-03-23 | COMP | Rule 16 | 59 | 17 | 2 | 1 | 159 | 40 | 273
19608 | 2020-02-24 | 2020-05-14 | 2021-01-22 | 2021-01-22 | COMP | 2021-02-11 | COMP | 2022-03-04 | COMP | 2022-03-21 | COMP | 2022-06-15 | COMP | Rule 15/16 | 59 | 174 | 15 | 268 | 12 | 62 | 585
19731 | 2020-02-24 | 2020-05-20 | 2020-09-30 | 2020-09-30 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-10-16 | COMP | 2020-11-03 | COMP | Rule 16 | 63 | 94 | 10 | 1 | 4 | 13 | 180
19839 | 2020-02-24 | 2020-05-26 | 2020-10-19 | 2020-10-19 | COMP | 2020-10-26 | COMP | 2021-02-11 | COMP | 2020-11-13 | COMP | 2021-04-26 | COMP | Rule 16 | 66 | 104 | 6 | 73 | 0 | 52 | 297
20029 | 2020-02-24 | 2020-06-02 | 2021-01-22 | 2021-01-22 | COMP | 2021-03-11 | COMP | 2021-09-23 | COMP | 2021-11-29 | COMP | 2022-01-14 | COMP | Rule 15/16 | 71 | 162 | 34 | 138 | 45 | 35 | 480
20140 | 2020-02-24 | 2020-06-07 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-14 | NOTN | 2020-07-29 | COMP | 2020-09-24 | COMP | 2020-11-18 | COMP | Other | 74 | 27 |  | 12 | 41 | 39 | 190
20378 | 2020-02-24 | 2020-06-17 | 2020-09-15 | 2020-10-29 | COMP | 2021-04-27 | COMP | 2021-04-27 | COMP | 2021-06-01 | COMP | 2021-06-21 | COMP | Rule 15/16 | 82 | 64 | 122 | 1 | 25 | 15 | 336
20481 | 2020-02-24 | 2020-06-22 | 2020-07-10 | 2020-07-17 | COMP | 2020-12-07 | COMP | 2021-01-12 | COMP | 2020-12-28 | COMP | 2021-03-01 | COMP | Rule 15/16 | 85 | 15 | 98 | 25 | 0 | 33 | 257
20687 | 2020-02-24 | 2020-07-02 | 2020-07-09 | 2020-07-09 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2020-11-09 | COMP | Rule 16 | 93 | 6 | 33 | 1 | 1 | 55 | 184
21645 | 2020-02-24 | 2020-08-18 | 2020-10-20 | 2020-10-20 | COMP | 2020-11-02 | COMP | 2020-11-06 | COMP | 2021-02-02 | COMP | 2021-02-12 | COMP | Rule 16 | 126 | 45 | 10 | 5 | 57 | 9 | 247
23852 | 2020-02-24 | 2020-11-25 | 2021-10-24 | 2021-10-24 | COMP | 2021-11-09 | COMP | 2022-01-24 | COMP | 2022-01-11 | COMP | 2022-01-27 | COMP | Rule 15/16 | 195 | 229 | 12 | 51 | 0 | 4 | 488
17718 | 2020-02-25 | 2020-02-25 | 2020-04-24 | 2020-04-24 | COMP | 2020-04-28 | COMP | 2020-05-27 | COMP | 2020-06-02 | COMP | 2020-06-26 | COMP | Rule 16 | 1 | 44 | 3 | 21 | 5 | 19 | 88
17826 | 2020-02-25 | 2020-02-28 | 2020-07-29 | 2020-07-29 | COMP | 2020-11-13 | COMP | 2020-12-07 | COMP | 2021-02-26 | COMP | 2021-03-10 | COMP | Rule 16 | 4 | 108 | 76 | 15 | 56 | 9 | 263
17846 | 2020-02-25 | 2020-03-02 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-11-18 | COMP | 2021-06-15 | COMP | Rule 15/16 | 5 | 46 | 21 | 1 | 120 | 143 | 331
17852 | 2020-02-25 | 2020-03-02 | 2020-04-07 | 2020-04-08 | COMP | 2020-04-08 | NOTN | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-04-17 | COMP | Other | 5 | 27 |  | 1 | 1 | 8 | 39
17869 | 2020-02-25 | 2020-03-03 | 2020-03-06 | 2020-03-06 | COMP | 2021-03-28 | REQD | 2021-03-28 | REQD | 2021-03-28 | REQD | 2020-03-03 | COMP | Other | 6 | 4 |  |  |  |  | 6
17918 | 2020-02-25 | 2020-03-03 | 2020-11-20 | 2020-11-20 | COMP | 2021-01-20 | COMP | 2021-03-26 | COMP | 2021-04-29 | COMP | 2021-09-14 | COMP | Rule 15/16 | 6 | 186 | 39 | 47 | 25 | 96 | 394
18097 | 2020-02-25 | 2020-03-11 | 2020-05-11 | 2020-05-11 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-11-02 | COMP | 2020-11-11 | COMP | Rule 16 | 12 | 44 | 61 | 1 | 64 | 7 | 184
18161 | 2020-02-25 | 2020-03-12 | 2020-05-20 | 2020-05-20 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-12-21 | COMP | 2021-02-17 | COMP | Rule 16 | 13 | 50 | 34 | 1 | 116 | 39 | 248
18286 | 2020-02-25 | 2020-03-18 | 2020-06-09 | 2020-06-09 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2020-10-15 | COMP | Rule 16 | 17 | 59 | 66 | 1 | 1 | 27 | 166
18430 | 2020-02-25 | 2020-03-24 | 2020-10-20 | 2020-10-20 | COMP | 2021-06-24 | COMP | 2021-06-24 | COMP | 2021-07-06 | COMP | 2021-09-16 | COMP | Rule 16 | 21 | 149 | 170 | 1 | 8 | 52 | 396
18543 | 2020-02-25 | 2020-03-28 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2022-01-30 | INPR | 2020-07-15 | COMP | Rule 16 | 24 | 50 | 13 | 1 |  |  | 101
18584 | 2020-02-25 | 2020-03-30 | 2020-10-06 | 2020-10-06 | COMP | 2020-10-28 | COMP | 2021-01-12 | COMP | 2021-01-23 | COMP | 2021-03-05 | COMP | Rule 15/16 | 25 | 135 | 17 | 50 | 8 | 29 | 260
18717 | 2020-02-25 | 2020-04-04 | 2020-07-20 | 2020-07-20 | COMP | 2021-03-17 | COMP | 2022-03-07 | COMP | 2022-03-05 | COMP | 2022-05-05 | COMP | Rule 15/16 | 29 | 75 | 165 | 246 | 0 | 44 | 556
18777 | 2020-02-25 | 2020-04-07 | 2020-05-30 | 2020-05-30 | COMP | 2020-06-02 | COMP | 2020-06-02 | COMP | 2020-06-08 | COMP | 2020-06-17 | COMP | Rule 16 | 31 | 38 | 2 | 1 | 5 | 8 | 81
18889 | 2020-02-25 | 2020-04-10 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-20 | COMP | 2020-05-28 | COMP | 2020-06-22 | COMP | 2020-07-31 | COMP | Rule 16 | 34 | 14 | 16 | 6 | 18 | 30 | 113
18933 | 2020-02-25 | 2020-04-13 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-06-19 | COMP | 2020-08-12 | COMP | Rule 15/16 | 35 | 40 | 7 | 1 | 4 | 39 | 121
19001 | 2020-02-25 | 2020-04-16 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-29 | COMP | 2020-06-11 | COMP | 2020-06-15 | COMP | 2020-07-22 | COMP | Rule 16 | 38 | 24 | 8 | 10 | 3 | 28 | 106
19096 | 2020-02-25 | 2020-04-21 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-16 | COMP | 2020-10-14 | COMP | 2020-12-02 | COMP | 2021-04-14 | COMP | Rule 16 | 41 | 55 | 8 | 64 | 33 | 92 | 288
19192 | 2020-02-25 | 2020-04-24 | 2021-04-02 | 2021-04-02 | COMP | 2021-06-22 | COMP | 2022-04-11 | COMP | 2022-03-10 | COMP | 2022-04-25 | COMP | Rule 15/16 | 44 | 237 | 57 | 203 | 0 | 11 | 548
19276 | 2020-02-25 | 2020-04-28 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-07-29 | COMP | 2020-09-03 | COMP | Rule 16 | 46 | 12 | 21 | 1 | 35 | 27 | 137
19402 | 2020-02-25 | 2020-05-05 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-08-06 | COMP | 2020-08-20 | COMP | Rule 16 | 51 | 33 | 23 | 1 | 13 | 11 | 127
19679 | 2020-02-25 | 2020-05-18 | 2020-10-08 | 2020-10-08 | COMP | 2020-10-15 | COMP | 2020-10-15 | COMP | 2020-11-17 | COMP | 2020-12-02 | COMP | Rule 16 | 60 | 102 | 6 | 1 | 23 | 10 | 197
20054 | 2020-02-25 | 2020-06-02 | 2020-07-02 | 2020-07-02 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-07-27 | COMP | 2020-09-10 | COMP | Rule 16 | 70 | 23 | 14 | 1 | 5 | 33 | 141
20317 | 2020-02-25 | 2020-06-16 | 2020-08-17 | 2021-04-13 | COMP | 2021-05-10 | COMP | 2021-06-29 | COMP | 2021-07-06 | COMP | 2021-07-22 | COMP | Rule 16 | 80 | 45 | 20 | 36 | 5 | 13 | 357
20743 | 2020-02-25 | 2020-07-03 | 2021-01-14 | 2022-08-12 | COMP | 2022-08-29 | COMP | 2023-04-27 | COMP | 2023-04-24 | COMP | 2023-06-01 | COMP | Rule 15/16 | 93 | 134 | 12 | 166 | 0 | 25 | 824
20798 | 2020-02-25 | 2020-07-06 | 2020-09-09 | 2020-09-09 | COMP | 2020-10-19 | COMP | 2020-12-11 | COMP |  | INPR | 2021-02-17 | COMP | Rule 16 | 94 | 47 | 29 | 37 |  |  | 248
21444 | 2020-02-25 | 2020-08-06 | 2021-02-05 | 2021-02-05 | COMP | 2021-03-23 | COMP | 2021-12-17 | COMP | 2021-12-10 | COMP | 2022-02-04 | COMP | Rule 15/16 | 117 | 125 | 32 | 188 | 0 | 35 | 493
22263 | 2020-02-25 | 2020-09-17 | 2021-03-16 | 2021-03-16 | COMP | 2021-04-01 | NOTN | 2021-10-14 | COMP | 2022-01-25 | COMP | 2022-02-12 | COMP | Other | 146 | 122 |  | 150 | 70 | 14 | 498
22395 | 2020-02-25 | 2020-09-23 | 2021-02-10 | 2021-02-10 | COMP | 2021-02-17 | COMP | 2021-09-16 | COMP | 2021-10-26 | COMP | 2022-03-03 | COMP | Rule 16 | 150 | 95 | 5 | 149 | 29 | 88 | 511
23135 | 2020-02-25 | 2020-10-26 | 2020-12-13 | 2020-12-13 | COMP | 2021-03-19 | COMP | 2021-03-22 | COMP | 2022-05-30 | COMP | 2022-07-18 | COMP | Rule 15/16 | 173 | 32 | 66 | 2 | 302 | 33 | 605
26786 | 2020-02-25 | 2021-04-02 | 2021-06-29 | 2021-06-29 | COMP | 2021-06-30 | COMP | 2021-07-15 | COMP | 2021-07-27 | COMP | 2021-08-05 | COMP | Rule 16 | 280 | 62 | 2 | 11 | 9 | 8 | 367
17788 | 2020-02-26 | 2020-02-28 | 2020-04-10 | 2020-04-10 | COMP | 2022-01-04 | COMP | 2022-01-04 | COMP | 2022-01-10 | COMP | 2022-02-17 | COMP | Rule 16 | 3 | 31 | 438 | 1 | 5 | 28 | 501
17836 | 2020-02-26 | 2020-02-29 | 2020-05-06 | 2020-05-06 | COMP | 2020-08-06 | COMP | 2020-11-03 | COMP | 2020-09-08 | COMP | 2020-11-24 | COMP | Rule 16 | 3 | 48 | 66 | 63 | 0 | 15 | 192
17838 | 2020-02-26 | 2020-02-29 | 2020-03-31 | 2020-03-31 | COMP | 2020-04-21 | COMP | 2020-04-23 | COMP | 2020-04-28 | COMP | 2020-06-04 | COMP | Other | 3 | 22 | 16 | 3 | 4 | 27 | 71
17894 | 2020-02-26 | 2020-03-03 | 2020-05-18 | 2020-05-18 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-11-18 | COMP | 2020-11-22 | COMP | Rule 16 | 5 | 55 | 19 | 1 | 112 | 3 | 190
17916 | 2020-02-26 | 2020-03-03 | 2020-07-08 | 2020-07-08 | COMP | 2020-10-12 | COMP | 2020-11-19 | COMP | 2021-01-25 | COMP | 2021-02-28 | COMP | Rule 15/16 | 5 | 91 | 68 | 28 | 43 | 24 | 254
18246 | 2020-02-26 | 2020-03-17 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-06-29 | COMP | 2020-08-03 | COMP | Rule 16 | 15 | 54 | 17 | 1 | 5 | 26 | 113
18390 | 2020-02-26 | 2020-03-23 | 2020-06-08 | 2020-06-08 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2022-11-29 | COMP | 2023-02-08 | COMP | Rule 16 | 19 | 55 | 47 | 1 | 578 | 49 | 744
18470 | 2020-02-26 | 2020-03-26 | 2020-04-29 | 2020-04-29 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-08-13 | COMP | Rule 16 | 22 | 25 | 47 | 1 | 1 | 30 | 121
18540 | 2020-02-26 | 2020-03-28 | 2020-07-20 | 2020-07-20 | COMP | 2020-07-30 | COMP | 2020-09-21 | COMP | 2023-12-03 | CANC | 2020-10-21 | COMP | Rule 16 | 23 | 80 | 9 | 37 |  |  | 169
18565 | 2020-02-26 | 2020-03-30 | 2020-06-04 | 2020-06-04 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-08-29 | COMP | 2020-10-12 | COMP | Rule 15/16 | 24 | 48 | 62 | 1 | 1 | 30 | 162
18744 | 2020-02-26 | 2020-04-05 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-27 | COMP | 2020-06-08 | COMP | 2020-04-28 | COMP | 2020-08-13 | COMP | Rule 16 | 28 | 14 | 3 | 30 | 0 | 49 | 121
18757 | 2020-02-26 | 2020-04-06 | 2020-08-20 | 2020-08-20 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-12-21 | COMP | 2021-02-10 | COMP | Rule 16 | 29 | 98 | 43 | 1 | 42 | 35 | 243
18788 | 2020-02-26 | 2020-04-06 | 2020-08-05 | 2020-09-17 | COMP | 2020-10-06 | COMP | 2020-12-01 | COMP | 2020-12-01 | COMP | 2021-02-12 | COMP | Rule 16 | 29 | 87 | 14 | 38 | 1 | 51 | 245
19013 | 2020-02-26 | 2020-04-17 | 2020-10-06 | 2020-12-15 | COMP | 2021-03-05 | COMP | 2021-05-18 | COMP | 2021-06-29 | COMP | 2021-07-21 | COMP | Rule 15/16 | 38 | 121 | 55 | 53 | 30 | 16 | 355
19142 | 2020-02-26 | 2020-04-22 | 2020-11-13 | 2020-11-13 | COMP | 2020-12-01 | COMP | 2020-12-01 | COMP | 2021-02-11 | COMP | 2021-03-03 | COMP | Rule 16 | 41 | 145 | 11 | 1 | 50 | 14 | 257
19297 | 2020-02-26 | 2020-04-28 | 2020-07-14 | 2020-07-14 | COMP | 2020-10-27 | COMP | 2020-10-27 | COMP | 2021-03-24 | COMP | 2021-05-17 | COMP | Rule 16 | 45 | 55 | 75 | 1 | 100 | 39 | 310
19305 | 2020-02-26 | 2020-04-29 | 2020-10-27 | 2020-10-27 | COMP | 2020-11-16 | COMP | 2020-11-16 | COMP | 2021-01-19 | COMP | 2021-03-01 | COMP | Rule 16 | 46 | 128 | 14 | 1 | 42 | 29 | 255
19316 | 2020-02-26 | 2020-04-29 | 2020-07-22 | 2020-07-22 | COMP | 2020-08-25 | COMP | 2020-09-09 | COMP | 2020-09-15 | COMP | 2020-10-12 | COMP | Rule 16 | 46 | 60 | 25 | 11 | 5 | 20 | 162
19548 | 2020-02-26 | 2020-05-12 | 2020-06-11 | 2020-06-19 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2021-02-26 | COMP | 2021-03-05 | COMP | Rule 15/16 | 55 | 22 | 13 | 1 | 161 | 6 | 259
19803 | 2020-02-26 | 2020-05-21 | 2020-10-29 | 2020-10-29 | COMP | 2020-12-11 | NOTN | 2020-12-16 | COMP | 2021-03-01 | COMP | 2021-04-05 | COMP | Other | 62 | 114 |  | 32 | 50 | 26 | 280
19877 | 2020-02-26 | 2020-05-26 | 2020-09-02 | 2020-09-02 | COMP | 2020-09-29 | COMP | 2021-11-10 | COMP | 2021-11-18 | COMP | 2021-12-11 | COMP | Rule 16 | 64 | 72 | 19 | 282 | 6 | 15 | 453
19948 | 2020-02-26 | 2020-05-29 | 2020-10-29 | 2020-10-29 | COMP | 2021-02-16 | COMP | 2021-02-16 | COMP | 2023-08-14 | COMP | 2023-09-18 | COMP | Rule 15/16 | 67 | 109 | 72 | 1 | 628 | 25 | 897
20318 | 2020-02-26 | 2020-06-16 | 2020-07-31 | 2021-04-13 | COMP | 2021-05-10 | COMP | 2021-07-13 | COMP | 2021-07-09 | COMP | 2021-09-08 | COMP | Rule 15/16 | 79 | 34 | 20 | 45 | 0 | 41 | 389
20319 | 2020-02-26 | 2020-06-16 | 2020-08-18 | 2020-08-18 | COMP | 2021-02-03 | COMP | 2021-03-24 | COMP | 2021-05-18 | COMP | 2021-07-20 | COMP | Rule 15/16 | 79 | 46 | 115 | 35 | 40 | 44 | 354
20320 | 2020-02-26 | 2020-06-16 | 2020-09-30 | 2020-09-30 | COMP | 2021-02-02 | COMP | 2021-06-23 | COMP | 2021-06-17 | COMP | 2021-07-29 | COMP | Rule 15/16 | 79 | 76 | 84 | 100 | 0 | 26 | 361
20321 | 2020-02-26 | 2020-06-16 | 2020-08-18 | 2021-05-24 | COMP | 2021-07-01 | COMP | 2021-07-08 | COMP | 2021-06-22 | COMP | 2021-07-27 | COMP | Rule 15/16 | 79 | 46 | 28 | 5 | 0 | 14 | 359
20428 | 2020-02-26 | 2020-06-19 | 2020-08-10 | 2020-08-10 | COMP | 2020-11-03 | COMP | 2020-11-03 | COMP | 2021-02-10 | COMP | 2021-03-03 | COMP | Rule 16 | 82 | 37 | 61 | 1 | 66 | 15 | 257
20900 | 2020-02-26 | 2020-07-13 | 2020-09-11 | 2020-09-11 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2021-06-24 | COMP | 2021-07-31 | COMP | Rule 16 | 98 | 44 | 19 | 1 | 179 | 26 | 362
17863 | 2020-02-27 | 2020-03-02 | 2020-04-21 | 2020-04-21 | COMP | 2021-02-02 | COMP | 2021-02-02 | COMP | 2021-02-09 | COMP | 2021-03-15 | COMP | Rule 16 | 3 | 37 | 198 | 1 | 6 | 24 | 264
18014 | 2020-02-27 | 2020-03-09 | 2020-04-15 | 2020-04-15 | COMP | 2020-04-27 | COMP | 2020-05-02 | COMP | 2020-04-30 | COMP | 2020-05-20 | COMP | Rule 16 | 8 | 28 | 9 | 5 | 0 | 13 | 60
18058 | 2020-02-27 | 2020-03-10 | 2020-06-02 | 2020-06-02 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2020-12-21 | COMP | 2021-01-11 | COMP | Rule 16 | 9 | 60 | 131 | 1 | 11 | 14 | 221
18080 | 2020-02-27 | 2020-03-10 | 2020-06-11 | 2020-06-11 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2022-01-30 | INPR | 2020-11-25 | COMP | Rule 16 | 9 | 67 | 63 | 1 |  |  | 192
18149 | 2020-02-27 | 2020-03-12 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-07-24 | COMP | 2020-07-31 | COMP | Rule 16 | 11 | 43 | 20 | 1 | 35 | 6 | 111
18250 | 2020-02-27 | 2020-03-17 | 2020-06-01 | 2020-06-01 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2023-05-27 | INPR | 2023-05-27 | COMP | Rule 16 | 14 | 54 | 73 | 1 |  |  | 819
18366 | 2020-02-27 | 2020-03-21 | 2020-04-03 | 2020-04-03 | COMP | 2020-05-27 | COMP | 2020-06-03 | COMP | 2020-07-06 | COMP | 2020-08-06 | COMP | Rule 16 | 17 | 10 | 38 | 6 | 24 | 24 | 115
18498 | 2020-02-27 | 2020-03-26 | 2020-04-17 | 2020-06-05 | COMP | 2020-07-28 | COMP | 2020-08-24 | COMP | 2020-08-26 | COMP | 2020-10-07 | COMP | Rule 15/16 | 21 | 17 | 38 | 20 | 3 | 30 | 158
18649 | 2020-02-27 | 2020-04-01 | 2020-04-30 | 2020-04-30 | COMP | 2020-05-26 | COMP | 2020-06-11 | COMP | 2020-07-24 | COMP | 2020-07-27 | COMP | Rule 16 | 25 | 22 | 18 | 13 | 32 | 2 | 107
18683 | 2020-02-27 | 2020-04-02 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-15 | COMP | 2020-06-05 | COMP | 2020-06-19 | COMP | 2020-06-29 | COMP | Rule 16 | 26 | 25 | 8 | 15 | 11 | 7 | 87
18737 | 2020-02-27 | 2020-04-05 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-11 | COMP | 2020-07-20 | COMP | 2020-07-27 | COMP | 2020-09-05 | COMP | Rule 16 | 27 | 32 | 17 | 28 | 6 | 30 | 136
18827 | 2020-02-27 | 2020-04-08 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-08-10 | COMP | 2020-08-12 | COMP | Rule 16 | 30 | 30 | 9 | 1 | 51 | 3 | 119
18864 | 2020-02-27 | 2020-04-09 | 2020-09-24 | 2020-09-24 | COMP | 2020-10-09 | COMP | 2020-11-14 | COMP | 2020-11-02 | COMP | 2020-12-16 | COMP | Rule 15/16 | 31 | 119 | 12 | 25 | 0 | 21 | 205
18924 | 2020-02-27 | 2020-04-13 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-01 | COMP | 2020-07-12 | COMP | 2020-07-09 | COMP | 2020-08-27 | COMP | Rule 16 | 33 | 43 | 15 | 8 | 0 | 34 | 130
18935 | 2020-02-27 | 2020-04-14 | 2020-07-02 | 2020-07-02 | COMP | 2020-08-07 | COMP | 2021-04-13 | COMP | 2022-05-28 | INPR | 2021-05-16 | COMP | Rule 16 | 34 | 57 | 27 | 170 |  |  | 308
19087 | 2020-02-27 | 2020-04-20 | 2020-10-06 | 2020-10-06 | COMP | 2020-10-13 | COMP | 2020-12-05 | COMP | 2020-12-07 | COMP | 2021-02-18 | COMP | Rule 16 | 38 | 120 | 6 | 36 | 1 | 50 | 247
19156 | 2020-02-27 | 2020-04-23 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-23 | COMP | 2020-07-23 | COMP | 2022-07-16 | INPR | 2020-08-22 | COMP | Rule 16 | 41 | 49 | 17 | 1 |  |  | 126
19273 | 2020-02-27 | 2020-04-29 | 2020-06-17 | 2020-06-17 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2021-02-23 | COMP | 2021-03-09 | COMP | Rule 16 | 45 | 35 | 69 | 1 | 104 | 11 | 260
19287 | 2020-02-27 | 2020-04-29 | 2020-12-10 | 2021-08-11 | COMP | 2021-09-27 | COMP | 2021-09-27 | COMP | 2021-09-27 | COMP | 2021-11-11 | COMP | Rule 16 | 45 | 157 | 33 | 1 | 1 | 33 | 433
19393 | 2020-02-27 | 2020-05-05 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-09 | COMP | 2020-07-21 | COMP | 2020-08-18 | COMP | 2020-10-09 | COMP | Rule 15/16 | 49 | 38 | 10 | 9 | 21 | 38 | 160
19404 | 2020-02-27 | 2020-05-05 | 2020-07-03 | 2020-07-03 | COMP | 2020-07-28 | COMP | 2021-02-09 | COMP | 2021-02-05 | COMP | 2021-03-12 | COMP | Rule 16 | 49 | 43 | 18 | 134 | 0 | 23 | 263
19667 | 2020-02-27 | 2020-05-17 | 2020-09-10 | 2020-09-10 | COMP | 2020-12-10 | COMP | 2021-03-16 | COMP | 2022-08-08 | COMP | 2022-09-27 | COMP | Rule 15/16 | 57 | 82 | 63 | 65 | 354 | 36 | 653
19806 | 2020-02-27 | 2020-05-21 | 2020-10-23 | 2021-03-16 | COMP | 2021-08-04 | COMP | 2021-09-08 | COMP | 2023-12-04 | INPR | 2022-03-23 | COMP | Rule 16 | 61 | 110 | 100 | 25 |  |  | 523
20114 | 2020-02-27 | 2020-06-06 | 2020-09-15 | 2020-09-15 | COMP | 2020-11-03 | COMP | 2020-11-03 | COMP | 2021-07-12 | COMP | 2021-08-16 | COMP | Rule 15/16 | 71 | 71 | 36 | 1 | 171 | 26 | 372
20357 | 2020-02-27 | 2020-06-17 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-08-10 | COMP | 2020-10-15 | COMP | Rule 16 | 79 | 20 | 6 | 1 | 15 | 48 | 164
20631 | 2020-02-27 | 2020-06-29 | 2020-08-11 | 2020-08-11 | COMP | 2021-04-07 | COMP | 2021-04-07 | COMP | 2021-06-02 | COMP | 2021-07-07 | COMP | Rule 16 | 87 | 32 | 164 | 1 | 40 | 25 | 344
20664 | 2020-02-27 | 2020-07-01 | 2021-03-11 | 2021-03-11 | COMP | 2021-04-09 | COMP | 2022-06-08 | COMP | 2023-08-16 | COMP | 2023-11-30 | COMP | Rule 16 | 89 | 174 | 22 | 295 | 298 | 73 | 946
23541 | 2020-02-27 | 2020-11-10 | 2021-01-31 | 2021-01-31 | COMP | 2021-02-10 | COMP | 2021-02-15 | COMP | 2021-04-16 | COMP | 2021-05-28 | COMP | Rule 16 | 182 | 53 | 8 | 3 | 44 | 31 | 318
24650 | 2020-02-27 | 2021-01-06 | 2021-03-26 | 2021-03-26 | COMP | 2021-04-05 | COMP | 2021-06-07 | COMP | 2021-05-03 | COMP | 2021-07-27 | COMP | Rule 15/16 | 218 | 56 | 7 | 45 | 0 | 36 | 358
18042 | 2020-02-28 | 2020-03-09 | 2020-10-14 | 2020-10-14 | COMP | 2020-10-19 | COMP | 2021-01-27 | COMP | 2022-01-30 | INPR | 2021-01-12 | COMP | Rule 16 | 7 | 156 | 4 | 67 |  |  | 221
18107 | 2020-02-28 | 2020-03-11 | 2020-04-06 | 2020-04-06 | COMP | 2020-04-15 | COMP | 2020-04-15 | COMP | 2020-10-26 | COMP | 2020-12-15 | COMP | Rule 15/16 | 9 | 19 | 8 | 1 | 137 | 34 | 203
18163 | 2020-02-28 | 2020-03-12 | 2020-05-08 | 2020-05-08 | COMP | 2020-06-05 | COMP | 2020-08-28 | COMP | 2020-09-01 | COMP | 2020-09-30 | COMP | Rule 16 | 10 | 42 | 20 | 61 | 3 | 21 | 152
18204 | 2020-02-28 | 2020-03-16 | 2020-08-19 | 2020-08-19 | COMP | 2020-08-19 | NOTN | 2020-08-19 | COMP | 2020-09-04 | COMP | 2020-09-28 | COMP | Other | 12 | 112 |  | 1 | 13 | 16 | 150
18266 | 2020-02-28 | 2020-03-17 | 2020-04-09 | 2020-04-09 | COMP | 2020-04-21 | COMP | 2020-04-21 | COMP | 2020-08-31 | COMP | 2020-09-16 | COMP | Rule 16 | 13 | 18 | 9 | 1 | 94 | 12 | 142
18288 | 2020-02-28 | 2020-03-18 | 2020-05-11 | 2020-05-11 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-07-14 | COMP | 2020-08-28 | COMP | Rule 16 | 14 | 39 | 23 | 1 | 24 | 34 | 130
18367 | 2020-02-28 | 2020-03-20 | 2020-06-24 | 2020-06-24 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-07-13 | COMP | 2020-08-22 | COMP | Rule 16 | 16 | 68 | 14 | 1 | 1 | 30 | 125
18460 | 2020-02-28 | 2020-03-25 | 2020-05-19 | 2020-05-19 | COMP | 2020-07-10 | COMP | 2020-06-24 | COMP | 2020-06-25 | COMP | 2020-08-04 | COMP | Rule 16 | 19 | 40 | 38 |  | 2 | 29 | 112
18479 | 2020-02-28 | 2020-03-27 | 2020-05-17 | 2020-05-17 | COMP | 2020-05-29 | NOTN | 2020-05-29 | COMP | 2020-06-09 | COMP | 2020-06-24 | COMP | Rule 16 | 21 | 36 |  | 9 | 8 | 12 | 83
18499 | 2020-02-28 | 2020-03-26 | 2020-05-13 | 2020-05-13 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP |  |  | 2020-09-18 | COMP | Rule 16 | 20 | 35 | 60 | 1 |  |  | 144
18583 | 2020-02-28 | 2020-03-30 | 2020-05-20 | 2020-06-05 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-09-01 | COMP | 2020-09-21 | COMP | Rule 16 | 22 | 38 | 14 | 1 | 50 | 14 | 145
18796 | 2020-02-28 | 2020-04-07 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-06-29 | COMP | 2020-07-22 | COMP | Rule 16 | 28 | 36 | 21 | 1 | 4 | 18 | 103
19003 | 2020-02-28 | 2020-04-16 | 2020-05-21 | 2020-05-21 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2022-01-30 | INPR | 2020-09-01 | COMP | Rule 16 | 35 | 26 | 32 | 1 |  |  | 132
19084 | 2020-02-28 | 2020-04-20 | 2020-11-05 | 2020-12-10 | COMP | 2021-02-03 | COMP | 2021-06-28 | COMP | 2021-06-15 | COMP | 2021-07-23 | COMP | Rule 15/16 | 37 | 142 | 37 | 102 | 0 | 19 | 355
19098 | 2020-02-28 | 2020-04-21 | 2020-06-05 | 2020-07-20 | COMP | 2020-07-24 | COMP | 2020-07-28 | COMP | 2020-08-16 | COMP | 2021-02-17 | COMP | Rule 16 | 38 | 33 | 5 | 3 | 14 | 125 | 245
19124 | 2020-02-28 | 2020-04-21 | 2020-05-07 | 2020-05-07 | COMP | 2020-05-15 | COMP | 2020-06-19 | COMP | 2020-06-29 | COMP | 2020-07-10 | COMP | Rule 16 | 38 | 13 | 7 | 25 | 7 | 10 | 95
19170 | 2020-02-28 | 2020-04-22 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2021-02-23 | COMP | 2021-03-24 | COMP | Rule 16 | 39 | 43 | 15 | 1 | 155 | 22 | 270
19348 | 2020-02-28 | 2020-05-02 | 2020-08-03 | 2020-08-03 | COMP | 2020-08-14 | COMP | 2020-09-30 | COMP | 2020-09-28 | COMP | 2020-11-04 | COMP | Rule 16 | 46 | 65 | 10 | 33 | 0 | 26 | 177
19458 | 2020-02-28 | 2020-05-07 | 2020-08-11 | 2020-08-11 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2020-11-11 | COMP | Rule 16 | 50 | 68 | 31 | 1 | 1 | 35 | 181
19466 | 2020-02-28 | 2020-05-07 | 2020-07-15 | 2020-07-15 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-08-11 | COMP | 2020-08-26 | COMP | Rule 16 | 50 | 49 | 4 | 1 | 17 | 12 | 128
19653 | 2020-02-28 | 2020-05-15 | 2020-08-20 | 2020-08-20 | COMP | 2020-09-22 | COMP | 2020-10-01 | COMP | 2020-11-02 | COMP | 2021-01-20 | COMP | Rule 16 | 56 | 69 | 23 | 8 | 23 | 52 | 226
19708 | 2020-02-28 | 2020-05-19 | 2020-08-20 | 2020-08-20 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-11-23 | COMP | 2020-11-30 | COMP | Rule 16 | 58 | 67 | 38 | 1 | 29 | 4 | 192
19759 | 2020-02-28 | 2020-05-20 | 2021-03-25 | 2021-03-25 | COMP | 2021-04-20 | COMP | 2022-07-28 | COMP | 2022-08-12 | COMP | 2022-08-29 | COMP | Rule 15/16 | 59 | 213 | 19 | 322 | 12 | 12 | 632
19832 | 2020-02-28 | 2020-05-26 | 2020-06-15 | 2020-06-15 | COMP | 2021-04-07 | COMP | 2021-04-07 | COMP | 2021-03-30 | COMP | 2021-04-20 | COMP | Rule 16 | 62 | 15 | 205 | 1 | 0 | 10 | 289
20252 | 2020-02-28 | 2020-06-12 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-24 | COMP | 2020-10-04 | COMP | 2020-09-22 | COMP | 2020-11-02 | COMP | Rule 16 | 75 | 32 | 21 | 29 | 0 | 21 | 175
20380 | 2020-02-28 | 2020-06-18 | 2020-09-02 | 2020-10-31 | COMP | 2021-03-17 | COMP | 2021-03-17 | COMP | 2023-09-02 | INPR | 2021-05-26 | COMP | Rule 16 | 79 | 55 | 91 | 1 |  |  | 315
20389 | 2020-02-28 | 2020-06-18 | 2020-08-14 | 2020-08-14 | COMP | 2020-09-22 | COMP | 2020-12-08 | COMP | 2020-09-03 | COMP | 2021-01-04 | COMP | Rule 16 | 79 | 42 | 27 | 53 | 0 | 18 | 215
20561 | 2020-02-28 | 2020-06-26 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-14 | NOTN | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-10-19 | COMP | Other | 85 | 36 |  | 1 | 1 | 46 | 165
20617 | 2020-02-28 | 2020-06-29 | 2020-08-14 | 2020-08-14 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2020-09-21 | COMP | 2020-10-22 | COMP | Rule 16 | 86 | 35 | 19 | 1 | 8 | 24 | 168
22297 | 2020-02-28 | 2020-09-18 | 2020-12-31 | 2021-03-25 | COMP | 2021-03-31 | COMP | 2021-04-09 | COMP | 2021-04-06 | COMP | 2021-05-21 | COMP | Rule 16 | 144 | 71 | 5 | 8 | 0 | 31 | 312
26989 | 2020-02-28 | 2021-04-09 | 2021-06-11 | 2021-06-11 | COMP | 2021-09-17 | COMP | 2021-09-28 | COMP | 2021-09-17 | COMP | 2022-01-27 | COMP | Rule 15/16 | 282 | 45 | 69 | 8 | 0 | 84 | 484
17994 | 2020-02-29 | 2020-03-06 | 2020-04-07 | 2020-04-07 | COMP | 2021-06-23 | COMP | 2021-06-23 | COMP | 2023-07-29 | INPR | 2021-09-13 | COMP | Rule 16 | 5 | 23 | 307 | 1 |  |  | 389
17995 | 2020-02-29 | 2020-03-06 | 2020-05-29 | 2020-05-29 | COMP | 2021-06-23 | COMP | 2021-09-03 | COMP | 2021-08-23 | COMP | 2021-10-28 | COMP | Rule 15/16 | 5 | 60 | 270 | 52 | 0 | 39 | 422
18265 | 2020-02-29 | 2020-03-17 | 2020-07-15 | 2020-07-15 | COMP | 2020-07-20 | COMP | 2020-10-01 | COMP | 2020-10-02 | COMP | 2020-11-02 | COMP | Rule 16 | 12 | 86 | 4 | 53 | 2 | 22 | 174
19139 | 2020-02-29 | 2020-04-22 | 2020-08-05 | 2020-08-05 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2020-10-02 | COMP | 2020-10-10 | COMP | Rule 16 | 38 | 75 | 25 | 1 | 18 | 6 | 158
19682 | 2020-02-29 | 2020-05-17 | 2020-09-25 | 2020-09-25 | COMP | 2020-10-13 | COMP | 2020-11-19 | COMP | 2021-01-12 | COMP | 2021-01-25 | COMP | Rule 16 | 55 | 93 | 13 | 27 | 35 | 9 | 228
21411 | 2020-02-29 | 2020-08-05 | 2020-10-29 | 2020-12-02 | COMP | 2021-01-22 | COMP | 2021-02-09 | COMP | 2023-11-13 | INPR | 2021-02-23 | COMP | Rule 16 | 112 | 61 | 35 | 13 |  |  | 248
22142 | 2020-02-29 | 2020-09-12 | 2020-12-13 | 2020-12-16 | COMP | 2020-12-23 | COMP | 2020-12-23 | COMP | 2021-03-29 | COMP | 2021-05-04 | COMP | Rule 16 | 138 | 62 | 6 | 1 | 65 | 27 | 298
18311 | 2020-03-01 | 2020-03-19 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-17 | COMP | 2021-01-29 | COMP | 2021-01-29 | COMP | 2021-03-25 | COMP | Rule 16 | 14 | 35 | 30 | 156 | 1 | 39 | 270
19063 | 2020-03-01 | 2020-04-20 | 2020-10-29 | 2020-10-29 | COMP | 2020-11-17 | COMP | 2021-01-13 | COMP | 2022-04-17 | INPR | 2021-02-26 | COMP | Rule 15/16 | 36 | 137 | 13 | 38 |  |  | 251
20959 | 2020-03-01 | 2020-07-14 | 2020-08-31 | 2020-08-31 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP | 2020-10-22 | COMP | 2020-11-09 | COMP | Rule 16 | 96 | 35 | 28 | 1 | 11 | 13 | 179
17876 | 2020-03-02 | 2020-03-02 | 2020-04-14 | 2020-04-14 | COMP | 2020-04-15 | NOTN | 2020-04-15 | COMP |  |  | 2020-06-15 | COMP | Rule 16 | 1 | 32 |  | 2 |  |  | 75
17901 | 2020-03-02 | 2020-03-04 | 2021-04-05 | 2022-07-22 | COMP | 2022-08-16 | NOTN | 2023-02-10 | COMP | 2023-02-13 | COMP | 2023-04-10 | COMP | Rule 16 | 3 | 275 |  | 139 | 2 | 40 | 783
17985 | 2020-03-02 | 2020-03-06 | 2020-04-24 | 2020-04-24 | COMP | 2020-04-27 | COMP | 2020-05-04 | COMP | 2020-10-05 | COMP | 2020-12-03 | COMP | Rule 16 | 5 | 36 | 2 | 6 | 109 | 41 | 194
18147 | 2020-03-02 | 2020-03-12 | 2020-04-28 | 2020-04-28 | COMP | 2021-12-06 | COMP | 2021-12-06 | COMP | 2022-01-04 | COMP | 2022-04-29 | COMP | Rule 16 | 9 | 34 | 405 | 1 | 22 | 82 | 548
18272 | 2020-03-02 | 2020-03-17 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-06-25 | COMP | 2020-08-06 | COMP | Rule 16 | 12 | 55 | 15 | 1 | 4 | 31 | 113
18358 | 2020-03-02 | 2020-03-21 | 2020-08-24 | 2020-08-24 | COMP | 2020-10-07 | COMP | 2020-10-07 | COMP | 2021-02-22 | COMP | 2021-03-31 | COMP | Rule 16 | 15 | 110 | 32 | 1 | 92 | 28 | 274
18403 | 2020-03-02 | 2020-03-23 | 2020-08-23 | 2020-08-23 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2021-05-11 | COMP | 2021-06-21 | COMP | Rule 15/16 | 16 | 109 | 24 | 1 | 156 | 29 | 331
18474 | 2020-03-02 | 2020-03-26 | 2020-05-08 | 2020-05-08 | COMP | 2020-05-08 | NOTN | 2020-05-08 | COMP | 2020-09-15 | COMP | 2020-10-28 | COMP | Other | 19 | 32 |  | 1 | 91 | 32 | 171
18501 | 2020-03-02 | 2020-03-26 | 2020-04-20 | 2020-04-20 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2022-09-08 | COMP | 2022-10-17 | COMP | Rule 16 | 19 | 18 | 20 | 1 | 584 | 28 | 665
18768 | 2020-03-02 | 2020-04-06 | 2020-04-26 | 2020-04-26 | COMP | 2020-07-01 | COMP | 2020-08-04 | COMP | 2020-10-07 | COMP | 2020-11-09 | COMP | Rule 16 | 26 | 15 | 47 | 25 | 46 | 24 | 179
18909 | 2020-03-02 | 2020-04-13 | 2020-06-17 | 2020-06-17 | COMP | 2020-06-22 | COMP | 2020-07-07 | COMP | 2020-07-16 | COMP | 2020-07-31 | COMP | Rule 16 | 31 | 47 | 4 | 12 | 8 | 12 | 109
18913 | 2020-03-02 | 2020-04-12 | 2020-09-02 | 2020-09-02 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2020-09-22 | COMP | 2020-12-02 | COMP | Rule 16 | 30 | 102 | 13 | 1 | 2 | 49 | 193
18919 | 2020-03-02 | 2020-04-12 | 2020-05-29 | 2020-05-29 | COMP | 2020-09-04 | COMP | 2020-07-30 | COMP | 2020-08-03 | COMP | 2021-01-25 | COMP | Rule 16 | 30 | 34 | 71 |  | 3 | 119 | 228
18997 | 2020-03-02 | 2020-04-16 | 2020-07-22 | 2020-07-22 | COMP | 2020-08-06 | NOTN | 2020-09-15 | COMP | 2020-09-29 | COMP | 2020-10-19 | COMP | Other | 34 | 69 |  | 39 | 11 | 15 | 164
19065 | 2020-03-02 | 2020-04-20 | 2020-05-27 | 2020-05-27 | COMP | 2020-09-08 | COMP | 2020-10-05 | COMP | 2020-09-08 | COMP | 2020-10-27 | COMP | Other | 36 | 27 | 74 | 20 | 0 | 17 | 170
19126 | 2020-03-02 | 2020-04-22 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-01 | COMP | 2020-07-01 | COMP | 2022-01-30 | INPR | 2020-07-06 | COMP | Rule 16 | 38 | 44 | 7 | 1 |  |  | 90
19144 | 2020-03-02 | 2020-04-22 | 2020-06-20 | 2020-06-20 | COMP | 2020-07-17 | COMP | 2020-07-18 | COMP | 2020-08-04 | COMP | 2020-08-19 | COMP | Rule 16 | 38 | 42 | 20 | 1 | 12 | 12 | 122
19188 | 2020-03-02 | 2020-04-24 | 2020-07-03 | 2020-07-03 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2020-08-25 | COMP | 2020-08-28 | COMP | Rule 16 | 40 | 50 | 6 | 1 | 33 | 4 | 129
19246 | 2020-03-02 | 2020-04-27 | 2020-11-18 | 2020-11-18 | COMP | 2020-12-08 | COMP | 2021-02-12 | COMP | 2021-03-01 | COMP | 2021-03-16 | COMP | Rule 16 | 41 | 145 | 13 | 46 | 11 | 12 | 263
19317 | 2020-03-02 | 2020-04-29 | 2020-06-05 | 2020-06-05 | COMP | 2020-06-09 | COMP | 2020-06-12 | COMP | 2020-06-22 | COMP | 2020-07-13 | COMP | Rule 16 | 43 | 27 | 3 | 4 | 7 | 16 | 95
19598 | 2020-03-02 | 2020-05-15 | 2020-11-20 | 2021-05-03 | COMP | 2021-09-17 | COMP | 2022-03-10 | COMP | 2022-05-29 | COMP | 2022-03-24 | COMP | Other | 55 | 133 | 97 | 120 | 57 |  | 522
19664 | 2020-03-02 | 2020-05-17 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-18 | COMP | 2020-10-16 | COMP | 2020-11-12 | COMP | 2021-01-06 | COMP | Rule 16 | 55 | 59 | 8 | 43 | 19 | 36 | 216
19722 | 2020-03-02 | 2020-05-19 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-09-30 | COMP | 2020-11-12 | COMP | Rule 15/16 | 57 | 49 | 6 | 1 | 42 | 31 | 181
19768 | 2020-03-02 | 2020-05-20 | 2020-07-29 | 2020-08-03 | COMP | 2020-08-11 | COMP | 2020-11-20 | COMP | 2020-10-28 | COMP | 2020-12-16 | COMP | Rule 16 | 58 | 50 | 7 | 72 | 0 | 17 | 203
19778 | 2020-03-02 | 2020-05-22 | 2020-11-09 | 2020-11-09 | COMP | 2021-02-19 | COMP | 2021-02-19 | COMP | 2021-03-22 | COMP | 2021-04-16 | COMP | Rule 16 | 60 | 120 | 68 | 1 | 22 | 20 | 286
20014 | 2020-03-02 | 2020-06-01 | 2020-12-09 | 2020-12-09 | COMP | 2021-01-12 | COMP | 2021-02-09 | COMP |  | INPR | 2022-02-07 | COMP | Rule 16 | 65 | 134 | 23 | 20 |  |  | 490
20089 | 2020-03-02 | 2020-06-03 | 2020-07-14 | 2020-09-05 | COMP | 2020-09-21 | NOTN | 2020-09-21 | COMP | 2020-10-12 | COMP | 2020-10-28 | COMP | Other | 67 | 30 |  | 10 | 16 | 13 | 171
20181 | 2020-03-02 | 2020-06-09 | 2020-10-08 | 2020-10-08 | COMP | 2020-11-17 | NOTN | 2020-11-20 | COMP | 2021-03-04 | COMP | 2021-05-17 | COMP | Other | 71 | 87 |  | 31 | 69 | 53 | 307
20288 | 2020-03-02 | 2020-06-15 | 2020-07-17 | 2021-11-09 | COMP | 2021-12-02 | COMP | 2021-12-02 | COMP | 2022-09-09 | COMP | 2022-09-26 | COMP | Rule 16 | 75 | 25 | 15 | 1 | 196 | 12 | 650
20422 | 2020-03-02 | 2020-06-19 | 2020-07-13 | 2020-07-13 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2021-04-02 | COMP | 2021-04-17 | COMP | Rule 16 | 79 | 17 | 67 | 1 | 116 | 11 | 286
20530 | 2020-03-02 | 2020-06-25 | 2020-09-21 | 2020-09-21 | COMP | 2023-03-03 | COMP | 2023-03-03 | COMP | 2023-08-08 | COMP | 2023-08-24 | COMP | Rule 16 | 83 | 62 | 614 | 1 | 110 | 13 | 878
20690 | 2020-03-02 | 2020-07-01 | 2020-07-14 | 2021-03-25 | COMP | 2021-03-30 | COMP | 2021-04-27 | COMP | 2021-12-07 | COMP | 2022-01-25 | COMP | Rule 16 | 87 | 10 | 4 | 21 | 155 | 35 | 481
20977 | 2020-03-02 | 2020-07-17 | 2020-08-24 | 2020-08-24 | COMP | 2022-12-16 | COMP | 2022-12-16 | COMP | 2023-11-28 | COMP | 2023-12-26 | COMP | Rule 16 | 99 | 27 | 582 | 1 | 237 | 20 | 961
22038 | 2020-03-02 | 2020-09-09 | 2020-11-03 | 2023-03-08 | COMP | 2023-04-12 | COMP | 2021-02-08 | COMP | 2023-03-27 | COMP | 2023-06-07 | COMP | Rule 16 | 136 | 40 | 26 |  | 536 | 52 | 824
17950 | 2020-03-03 | 2020-03-05 | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | NOTN | 2021-01-25 | COMP | 2020-09-25 | COMP | 2021-03-05 | COMP | Other | 3 | 145 |  | 81 | 0 | 29 | 255
18212 | 2020-03-03 | 2020-03-16 | 2020-12-16 | 2020-12-16 | COMP | 2021-01-04 | COMP | 2021-09-14 | INPR | 2023-12-03 | CANC | 2022-01-17 | COMP | Rule 16 | 10 | 193 | 12 |  |  |  | 474
18229 | 2020-03-03 | 2020-03-16 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-22 | COMP | 2021-01-06 | COMP | 2021-06-24 | COMP | 2021-07-30 | COMP | Rule 16 | 10 | 66 | 27 | 115 | 119 | 26 | 358
18232 | 2020-03-03 | 2020-03-16 | 2020-05-07 | 2020-05-07 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-07-28 | COMP | Rule 16 | 10 | 39 | 17 | 1 | 1 | 42 | 105
18292 | 2020-03-03 | 2020-03-19 | 2020-05-21 | 2020-12-29 | COMP | 2021-01-05 | COMP | 2020-05-29 | COMP | 2020-12-22 | COMP | 2021-01-21 | COMP | Rule 16 | 13 | 46 | 5 |  | 144 | 20 | 225
18303 | 2020-03-03 | 2020-03-19 | 2020-07-14 | 2020-07-22 | COMP | 2020-08-04 | COMP | 2021-08-05 | INPR |  | REQD | 2021-08-13 | COMP | Rule 15/16 | 13 | 83 | 10 |  |  |  | 368
18309 | 2020-03-03 | 2020-03-19 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-06-26 | COMP | 2020-07-15 | COMP | Rule 16 | 13 | 53 | 16 | 1 | 4 | 14 | 96
18319 | 2020-03-03 | 2020-03-19 | 2021-04-07 | 2021-04-07 | COMP | 2021-04-26 | COMP | 2021-04-26 | COMP | 2021-04-26 | COMP | 2021-08-31 | COMP | Rule 15/16 | 13 | 266 | 14 | 1 | 1 | 90 | 380
18362 | 2020-03-03 | 2020-03-21 | 2020-06-24 | 2020-06-24 | COMP | 2021-10-04 | COMP | 2021-09-27 | COMP | 2021-09-28 | COMP | 2021-11-10 | COMP | Rule 16 | 14 | 67 | 323 |  | 2 | 32 | 430
18388 | 2020-03-03 | 2020-03-23 | 2020-06-03 | 2020-06-03 | COMP | 2020-09-11 | COMP | 2020-09-11 | COMP | 2020-09-14 | COMP | 2020-11-03 | COMP | Rule 16 | 15 | 52 | 72 | 1 | 2 | 37 | 174
18389 | 2020-03-03 | 2020-03-23 | 2020-06-04 | 2020-06-04 | COMP | 2020-09-11 | COMP | 2020-09-11 | COMP | 2020-09-14 | COMP | 2020-10-25 | COMP | Rule 16 | 15 | 53 | 71 | 1 | 2 | 30 | 167
18435 | 2020-03-03 | 2020-03-25 | 2020-05-06 | 2020-05-11 | COMP | 2020-06-17 | COMP | 2020-06-17 | COMP |  | INPR | 2020-09-18 | COMP | Rule 15/16 | 17 | 31 | 27 | 1 |  |  | 142
18514 | 2020-03-03 | 2020-03-28 | 2020-05-20 | 2020-05-20 | COMP | 2021-10-28 | COMP | 2021-10-28 | COMP |  | INPR | 2023-04-06 | COMP | Rule 16 | 19 | 38 | 365 | 1 |  |  | 780
18637 | 2020-03-03 | 2020-04-01 | 2020-10-31 | 2020-10-31 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2021-03-03 | COMP | 2021-03-17 | COMP | Rule 16 | 22 | 151 | 32 | 1 | 50 | 11 | 263
18698 | 2020-03-03 | 2020-04-03 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-28 | COMP | 2020-09-02 | COMP | 2020-09-03 | COMP | 2020-09-18 | COMP | Other | 24 | 59 | 47 | 4 | 2 | 11 | 142
19082 | 2020-03-03 | 2020-04-20 | 2020-09-19 | 2020-11-18 | COMP | 2021-03-09 | COMP | 2021-03-10 | COMP |  | INPR | 2021-04-13 | COMP | Rule 16 | 35 | 108 | 74 | 2 |  |  | 282
19118 | 2020-03-03 | 2020-04-22 | 2020-05-12 | 2020-05-12 | COMP | 2020-05-22 | COMP | 2020-09-28 | COMP | 2020-10-19 | COMP | 2020-11-13 | COMP | Rule 16 | 37 | 15 | 9 | 90 | 16 | 19 | 181
19180 | 2020-03-03 | 2020-04-23 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-02 | COMP | 2020-07-31 | COMP | 2020-07-03 | COMP | 2020-10-20 | COMP | Rule 16 | 38 | 46 | 5 | 22 | 0 | 57 | 164
19234 | 2020-03-03 | 2020-04-27 | 2020-12-15 | 2022-06-14 | COMP | 2022-07-15 | COMP | 2022-07-27 | COMP | 2022-07-18 | COMP | 2022-10-13 | COMP | Rule 15/16 | 40 | 162 | 22 | 9 | 0 | 56 | 662
19388 | 2020-03-03 | 2020-05-05 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-07-13 | COMP | 2020-08-03 | COMP | Rule 16 | 46 | 30 | 16 | 1 | 5 | 16 | 109
19452 | 2020-03-03 | 2020-05-07 | 2020-10-07 | 2020-10-07 | COMP | 2021-06-07 | COMP | 2021-07-28 | COMP | 2021-11-30 | COMP | 2022-02-21 | COMP | Rule 15/16 | 48 | 108 | 166 | 37 | 86 | 58 | 498
19491 | 2020-03-03 | 2020-05-08 | 2020-09-05 | 2020-09-05 | COMP | 2020-10-16 | COMP | 2020-10-16 | COMP | 2022-01-31 | INPR | 2020-12-02 | COMP | Rule 16 | 49 | 85 | 29 | 1 |  |  | 192
19536 | 2020-03-03 | 2020-05-11 | 2020-06-09 | 2020-06-09 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-06-25 | COMP | 2020-07-29 | COMP | Rule 16 | 50 | 21 | 6 | 1 | 8 | 25 | 106
19595 | 2020-03-03 | 2020-05-14 | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | NOTN | 2020-07-21 | COMP | 2020-07-28 | COMP | 2020-08-28 | COMP | Other | 53 | 24 |  | 25 | 6 | 24 | 128
19610 | 2020-03-03 | 2020-05-14 | 2020-06-03 | 2020-06-04 | COMP | 2020-10-22 | COMP | 2020-10-22 | COMP | 2021-02-25 | COMP | 2021-02-25 | COMP | Rule 16 | 53 | 14 | 100 | 1 | 84 | 1 | 249
19617 | 2020-03-03 | 2020-05-15 | 2020-09-28 | 2020-11-03 | COMP | 2020-11-06 | COMP | 2020-12-29 | COMP | 2021-03-03 | COMP | 2021-06-08 | COMP | Rule 16 | 54 | 95 | 4 | 34 | 44 | 69 | 321
19632 | 2020-03-03 | 2020-05-15 | 2020-06-17 | 2020-06-17 | COMP | 2020-09-03 | COMP | 2020-09-03 | COMP | 2021-01-13 | COMP | 2021-02-17 | COMP | Rule 16 | 54 | 23 | 57 | 1 | 89 | 24 | 243
19668 | 2020-03-03 | 2020-05-17 | 2020-08-23 | 2020-11-05 | COMP | 2021-01-12 | COMP | 2021-02-11 | COMP | 2021-02-10 | COMP | 2021-04-23 | COMP | Rule 16 | 54 | 69 | 44 | 22 | 0 | 51 | 290
19675 | 2020-03-03 | 2020-05-17 | 2020-11-19 | 2021-02-25 | COMP | 2020-12-02 | NOTN | 2020-12-11 | COMP | 2020-12-11 | COMP | 2021-04-28 | COMP | Other | 54 | 131 |  |  | 1 | 95 | 293
19916 | 2020-03-03 | 2020-05-27 | 2020-12-10 | 2020-12-10 | COMP | 2021-06-25 | COMP | 2021-10-25 | COMP | 2021-11-12 | COMP | 2022-02-21 | COMP | Rule 15/16 | 61 | 138 | 137 | 85 | 14 | 68 | 498
19980 | 2020-03-03 | 2020-06-02 | 2020-07-02 | 2020-07-02 | COMP | 2021-01-13 | COMP | 2021-01-13 | COMP | 2021-12-07 | COMP | 2022-01-03 | COMP | Rule 16 | 65 | 23 | 134 | 1 | 227 | 20 | 465
21005 | 2020-03-03 | 2020-07-17 | 2020-07-31 | 2020-07-31 | COMP | 2021-12-07 | COMP | 2021-12-07 | NOTN | 2022-01-31 | COMP | 2022-02-12 | COMP | Rule 16 | 98 | 11 | 339 |  |  |  | 493
21284 | 2020-03-03 | 2020-07-30 | 2020-09-18 | 2021-01-20 | COMP | 2021-01-27 | COMP | 2020-12-31 | COMP | 2021-01-28 | COMP | 2022-06-17 | COMP | Rule 16 | 107 | 36 | 6 |  | 19 | 352 | 581
22393 | 2020-03-03 | 2020-09-22 | 2021-02-03 | 2021-05-04 | COMP | 2021-05-14 | COMP | 2021-07-14 | COMP | 2021-08-31 | COMP | 2021-11-24 | COMP | Rule 15/16 | 144 | 91 | 9 | 42 | 35 | 60 | 439
25484 | 2020-03-03 | 2021-02-10 | 2021-04-30 | 2021-04-30 | COMP | 2021-07-02 | COMP | 2021-07-06 | COMP | 2021-10-30 | COMP | 2021-12-06 | COMP | Rule 16 | 239 | 57 | 45 | 2 | 83 | 23 | 445
32103 | 2020-03-03 | 2021-11-03 | 2022-04-21 | 2022-04-21 | COMP | 2022-09-13 | COMP | 2022-10-27 | COMP | 2022-09-12 | COMP | 2022-11-15 | COMP | Rule 15/16 | 425 | 117 | 100 | 33 | 0 | 13 | 684
4281 | 2020-03-04 | 2020-03-17 | 2020-08-04 | 2020-08-04 | COMP | 2021-01-13 | COMP | 2021-02-01 | COMP | 2021-01-28 | COMP | 2021-03-12 | COMP | Rule 16 | 10 | 100 | 111 | 13 | 0 | 29 | 259
4300 | 2020-03-04 | 2020-05-14 | 2020-08-07 | 2020-08-07 | COMP | 2020-11-02 | COMP | 2021-02-04 | COMP | 2021-02-23 | COMP | 2021-04-08 | COMP | Rule 16 | 52 | 61 | 61 | 63 | 13 | 33 | 278
17943 | 2020-03-04 | 2020-03-05 | 2020-06-24 | 2020-06-24 | COMP | 2020-06-03 | NOTN | 2020-08-24 | COMP | 2020-06-25 | COMP | 2020-09-16 | COMP | Other | 2 | 79 |  | 44 | 0 | 17 | 139
17972 | 2020-03-04 | 2020-03-06 | 2020-04-10 | 2020-04-10 | COMP | 2020-04-23 | NOTN | 2020-04-23 | INPR | 2020-04-23 | COMP | 2020-07-01 | COMP | Other | 3 | 26 |  |  |  |  | 85
18000 | 2020-03-04 | 2020-03-06 | 2020-07-07 | 2020-09-04 | COMP | 2020-10-09 | COMP | 2021-05-25 | COMP | 2022-06-18 | INPR | 2021-05-27 | COMP | Rule 15/16 | 3 | 87 | 25 | 156 |  |  | 313
18126 | 2020-03-04 | 2020-03-12 | 2020-08-21 | 2020-08-21 | COMP | 2020-12-08 | COMP | 2021-01-05 | COMP | 2021-01-06 | COMP | 2021-03-02 | COMP | Rule 15/16 | 7 | 116 | 74 | 19 | 2 | 38 | 251
18194 | 2020-03-04 | 2020-03-14 | 2020-12-21 | 2020-12-21 | COMP | 2021-01-06 | COMP | 2021-01-20 | COMP | 2022-01-30 | INPR | 2021-01-21 | COMP | Rule 16 | 8 | 196 | 11 | 10 |  |  | 224
18376 | 2020-03-04 | 2020-03-21 | 2020-05-21 | 2020-05-21 | COMP | 2020-05-28 | COMP | 2020-06-09 | COMP | 2020-08-04 | COMP | 2020-10-17 | COMP | Rule 16 | 13 | 44 | 5 | 9 | 41 | 53 | 161
18419 | 2020-03-04 | 2020-03-23 | 2020-04-30 | 2020-04-30 | COMP | 2020-06-15 | COMP | 2021-01-25 | NOTN | 2021-01-25 | COMP | 2021-02-16 | COMP | Rule 16 | 14 | 29 | 32 |  |  |  | 241
18478 | 2020-03-04 | 2020-03-27 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-03 | COMP | 2020-10-14 | COMP | Rule 16 | 18 | 54 | 19 | 1 | 20 | 52 | 159
18548 | 2020-03-04 | 2020-03-28 | 2020-06-13 | 2020-06-13 | COMP | 2020-06-29 | COMP | 2020-08-17 | COMP | 2020-09-21 | COMP | 2020-09-29 | COMP | Rule 16 | 18 | 54 | 11 | 36 | 25 | 7 | 148
18761 | 2020-03-04 | 2020-04-06 | 2020-05-08 | 2020-05-08 | COMP | 2020-06-30 | COMP | 2020-06-30 | COMP | 2020-09-10 | COMP | 2020-10-29 | COMP | Rule 16 | 24 | 25 | 37 | 1 | 52 | 36 | 170
18767 | 2020-03-04 | 2020-04-06 | 2020-04-30 | 2020-04-30 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | 2020-09-01 | COMP | 2020-10-15 | COMP | Rule 16 | 24 | 19 | 87 | 1 | 2 | 32 | 160
19061 | 2020-03-04 | 2020-04-20 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-27 | COMP | 2021-05-18 | COMP | 2022-06-18 | INPR | 2021-05-21 | COMP | Rule 16 | 34 | 20 | 8 | 247 |  |  | 309
19235 | 2020-03-04 | 2020-04-27 | 2020-11-10 | 2020-11-10 | COMP | 2020-12-14 | COMP | 2021-03-16 | COMP |  | INPR | 2021-05-11 | COMP | Rule 15/16 | 39 | 140 | 22 | 63 |  |  | 301
19300 | 2020-03-04 | 2020-04-28 | 2020-11-02 | 2020-11-02 | COMP | 2021-03-11 | NOTN | 2021-06-19 | COMP | 2021-08-25 | COMP | 2021-09-21 | COMP | Rule 16 | 40 | 133 |  | 157 | 47 | 19 | 393
19301 | 2020-03-04 | 2020-04-29 | 2020-08-10 | 2020-08-10 | COMP | 2020-09-10 | COMP | 2021-05-12 | COMP | 2021-05-12 | COMP | 2021-07-12 | COMP | Rule 16 | 41 | 73 | 23 | 168 | 1 | 42 | 343
19313 | 2020-03-04 | 2020-04-30 | 2021-02-10 | 2021-02-10 | COMP | 2021-04-14 | COMP | 2021-04-14 | COMP | 2021-04-21 | COMP | 2022-04-18 | COMP | Rule 16 | 42 | 197 | 45 | 1 | 6 | 251 | 537
19318 | 2020-03-04 | 2020-04-29 | 2020-08-13 | 2020-08-13 | COMP | 2020-09-16 | COMP | 2020-09-23 | COMP | 2020-09-24 | COMP | 2020-11-07 | COMP | Rule 16 | 41 | 76 | 24 | 6 | 2 | 32 | 176
19390 | 2020-03-04 | 2020-05-05 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-16 | COMP | 2020-06-16 | COMP | 2020-07-09 | COMP | 2020-07-16 | COMP | Rule 16 | 45 | 16 | 15 | 1 | 18 | 6 | 96
19454 | 2020-03-04 | 2020-05-07 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-12 | COMP | 2020-09-02 | COMP | Rule 16 | 47 | 38 | 24 | 1 | 9 | 16 | 130
19501 | 2020-03-04 | 2020-05-09 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-16 | COMP | 2020-09-15 | COMP | 2020-09-04 | COMP | 2020-10-20 | COMP | Rule 16 | 48 | 24 | 3 | 65 | 0 | 26 | 163
19670 | 2020-03-04 | 2020-05-17 | 2020-08-18 | 2020-08-18 | COMP | 2020-08-26 | COMP | 2020-10-19 | COMP | 2020-09-22 | COMP | 2020-11-30 | COMP | Rule 16 | 53 | 66 | 7 | 38 | 0 | 28 | 189
19748 | 2020-03-04 | 2020-05-20 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-06 | COMP | 2020-09-10 | COMP | 2021-08-03 | COMP | 2021-09-02 | COMP | Rule 16 | 56 | 37 | 20 | 25 | 225 | 23 | 381
19775 | 2020-03-04 | 2020-05-20 | 2020-08-10 | 2020-08-10 | COMP | 2020-09-02 | COMP | 2022-01-27 | COMP | 2022-01-26 | COMP | 2022-02-15 | COMP | Rule 16 | 56 | 58 | 18 | 352 | 0 | 14 | 494
19799 | 2020-03-04 | 2020-05-21 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-07 | NOTN | 2020-09-29 | COMP | 2020-09-30 | COMP | 2020-12-03 | COMP | Rule 16 | 57 | 56 |  | 37 | 2 | 44 | 192
19850 | 2020-03-04 | 2020-05-26 | 2020-08-31 | 2020-08-31 | COMP | 2020-10-27 | COMP | 2021-06-25 | COMP |  |  | 2022-06-11 | COMP | Rule 16 | 59 | 70 | 41 | 166 |  |  | 575
19873 | 2020-03-04 | 2020-05-28 | 2020-09-16 | 2020-09-16 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2021-06-03 | COMP | 2021-07-10 | COMP | Rule 16 | 61 | 79 | 58 | 1 | 122 | 26 | 342
19893 | 2020-03-04 | 2020-05-28 | 2021-05-20 | 2021-05-20 | COMP | 2021-10-28 | COMP | 2022-05-11 | COMP | 2023-01-18 | COMP | 2023-04-27 | COMP | Rule 15/16 | 61 | 248 | 113 | 135 | 171 | 71 | 794
19975 | 2020-03-04 | 2020-05-30 | 2020-10-15 | 2020-10-15 | COMP | 2020-11-24 | COMP | 2021-10-20 | COMP |  |  | 2021-12-10 | COMP | Rule 15/16 | 62 | 98 | 28 | 228 |  |  | 448
20106 | 2020-03-04 | 2020-06-05 | 2020-09-28 | 2021-08-10 | COMP | 2021-08-13 | COMP | 2020-11-18 | COMP | 2021-05-05 | COMP | 2021-11-09 | COMP | Rule 16 | 67 | 81 | 4 |  | 115 | 132 | 428
20116 | 2020-03-04 | 2020-06-06 | 2020-07-14 | 2020-07-14 | COMP | 2020-11-04 | COMP | 2020-11-04 | COMP | 2020-11-05 | COMP | 2020-12-03 | COMP | Rule 16 | 67 | 27 | 81 | 1 | 2 | 18 | 192
20559 | 2020-03-04 | 2020-06-25 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-26 | COMP | 2020-08-26 | COMP | 2020-09-15 | COMP | 2020-10-19 | COMP | Rule 15/16 | 81 | 37 | 9 | 1 | 14 | 25 | 162
23207 | 2020-03-04 | 2020-10-28 | 2021-01-22 | 2021-01-22 | COMP | 2021-02-18 | COMP | 2021-04-26 | COMP |  |  | 2021-06-01 | COMP | Rule 15/16 | 169 | 57 | 19 | 48 |  |  | 315
17998 | 2020-03-05 | 2020-03-06 | 2020-05-29 | 2021-02-16 | COMP | 2021-03-09 | COMP | 2021-03-09 | COMP | 2021-03-09 | COMP | 2021-05-15 | COMP | Rule 16 | 2 | 60 | 16 | 1 | 1 | 49 | 303
18261 | 2020-03-05 | 2020-03-17 | 2020-07-17 | 2020-07-17 | COMP | 2020-10-28 | COMP | 2020-10-29 | COMP | 2021-06-15 | COMP | 2021-06-28 | COMP | Rule 16 | 9 | 88 | 73 | 2 | 156 | 10 | 333
18343 | 2020-03-05 | 2020-03-20 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-04 | COMP | 2020-05-04 | COMP | 2020-05-05 | COMP | 2020-07-07 | COMP | Rule 16 | 12 | 17 | 16 | 1 | 2 | 45 | 88
18609 | 2020-03-05 | 2020-03-31 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-06-25 | COMP | 2020-08-11 | COMP | Rule 16 | 19 | 27 | 35 | 1 | 2 | 34 | 113
18789 | 2020-03-05 | 2020-04-06 | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | NOTN | 2020-07-16 | COMP | 2021-07-01 | COMP | 2021-09-13 | COMP | Other | 23 | 37 |  | 37 | 242 | 51 | 386
18877 | 2020-03-05 | 2020-04-10 | 2020-10-29 | 2020-10-29 | COMP | 2020-11-03 | NOTN | 2020-11-16 | COMP | 2021-04-15 | NOTN | 2022-01-11 | COMP | Other | 27 | 143 |  | 12 |  |  | 469
18950 | 2020-03-05 | 2020-04-14 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-08 | COMP | 2020-11-13 | COMP | 2021-04-06 | COMP | 2021-04-16 | COMP | Rule 16 | 29 | 99 | 6 | 48 | 97 | 9 | 283
19205 | 2020-03-05 | 2020-04-23 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-08-14 | COMP | 2020-09-14 | COMP | Rule 16 | 36 | 73 | 9 | 1 | 1 | 21 | 136
19413 | 2020-03-05 | 2020-05-05 | 2020-06-17 | 2020-06-17 | COMP | 2020-08-27 | COMP | 2020-09-23 | COMP | 2020-10-12 | COMP | 2021-01-05 | COMP | Rule 16 | 44 | 31 | 52 | 19 | 14 | 57 | 212
19564 | 2020-03-05 | 2020-05-12 | 2020-07-20 | 2020-08-05 | COMP | 2020-09-11 | COMP | 2020-09-20 | COMP | 2020-09-16 | COMP | 2020-10-15 | COMP | Rule 16 | 49 | 49 | 27 | 6 | 0 | 19 | 159
19658 | 2020-03-05 | 2020-05-16 | 2020-08-26 | 2020-08-26 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2020-11-30 | COMP | 2020-12-09 | COMP | Rule 16 | 52 | 72 | 52 | 1 | 14 | 8 | 195
19701 | 2020-03-05 | 2020-05-18 | 2020-10-02 | 2020-10-02 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2022-06-18 | INPR | 2021-05-27 | COMP | Rule 16 | 53 | 98 | 9 | 1 |  |  | 312
19745 | 2020-03-05 | 2020-05-20 | 2020-12-15 | 2020-12-15 | COMP | 2021-02-24 | COMP | 2021-05-21 | COMP |  | INPR | 2021-05-18 | COMP | Rule 15/16 | 55 | 145 | 48 | 63 |  |  | 305
19954 | 2020-03-05 | 2020-05-29 | 2020-09-18 | 2020-09-18 | COMP | 2021-03-08 | COMP | 2021-03-11 | COMP | 2021-11-10 | COMP | 2022-01-19 | COMP | Rule 16 | 61 | 80 | 115 | 4 | 172 | 47 | 474
20772 | 2020-03-05 | 2020-07-06 | 2020-09-25 | 2020-09-25 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2021-05-20 | COMP | 2021-06-24 | COMP | Rule 16 | 87 | 59 | 70 | 1 | 94 | 25 | 331
20883 | 2020-03-05 | 2020-07-10 | 2020-08-21 | 2020-08-21 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-10-12 | COMP | 2020-10-02 | COMP | Rule 16 | 91 | 31 | 8 | 1 | 29 |  | 150
20924 | 2020-03-05 | 2020-07-14 | 2020-09-04 | 2020-09-04 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-11-19 | COMP | 2021-01-11 | COMP | Rule 16 | 93 | 39 | 12 | 1 | 42 | 34 | 216
21276 | 2020-03-05 | 2020-07-30 | 2020-09-01 | 2020-09-01 | COMP | 2020-12-23 | COMP | 2020-12-23 | COMP | 2022-09-20 | COMP | 2022-10-24 | COMP | Other | 105 | 24 | 78 | 1 | 439 | 25 | 667
21277 | 2020-03-05 | 2020-07-30 | 2020-09-01 | 2020-09-01 | COMP | 2021-05-14 | COMP | 2021-10-26 | COMP | 2022-09-14 | COMP | 2022-11-23 | COMP | Other | 105 | 24 | 176 | 115 | 223 | 50 | 688
21353 | 2020-03-05 | 2020-08-03 | 2020-08-14 | 2020-08-14 | COMP | 2021-03-30 | COMP | 2021-03-30 | COMP | 2021-04-08 | COMP | 2021-05-11 | COMP | Rule 16 | 107 | 10 | 155 | 1 | 8 | 24 | 300
21610 | 2020-03-05 | 2020-08-15 | 2020-12-17 | 2020-12-17 | COMP | 2021-02-19 | COMP | 2021-12-09 | COMP | 2021-12-14 | COMP | 2022-02-08 | COMP | Rule 16 | 116 | 85 | 43 | 204 | 4 | 40 | 488
21723 | 2020-03-05 | 2020-08-21 | 2021-01-26 | 2021-01-26 | COMP | 2021-10-14 | COMP | 2021-06-23 | COMP | 2021-09-29 | COMP | 2021-10-08 | COMP | Rule 15/16 | 121 | 106 | 184 |  | 69 | 8 | 405
21840 | 2020-03-05 | 2020-08-30 | 2020-11-05 | 2020-11-05 | COMP | 2020-11-19 | COMP | 2020-12-30 | COMP | 2020-12-04 | COMP | 2021-02-03 | COMP | Rule 16 | 126 | 48 | 10 | 27 | 0 | 24 | 232
22191 | 2020-03-05 | 2020-09-14 | 2020-12-18 | 2020-12-18 | COMP | 2021-01-04 | COMP | 2021-03-03 | COMP | 2021-03-26 | COMP | 2021-04-09 | COMP | Rule 16 | 136 | 67 | 10 | 41 | 18 | 11 | 278
23803 | 2020-03-05 | 2020-11-23 | 2021-01-11 | 2021-01-11 | COMP | 2021-03-09 | COMP | 2021-03-09 | COMP | 2021-05-04 | COMP | 2021-06-16 | COMP | Rule 16 | 185 | 32 | 40 | 1 | 41 | 31 | 325
18049 | 2020-03-06 | 2020-03-10 | 2020-06-05 | 2020-06-05 | COMP | 2020-07-17 | COMP | 2020-08-13 | COMP | 2020-12-24 | COMP | 2021-02-01 | COMP | Rule 15/16 | 3 | 63 | 31 | 20 | 92 | 25 | 229
18095 | 2020-03-06 | 2020-03-10 | 2020-04-18 | 2020-04-18 | COMP | 2020-05-26 | COMP | 2020-05-26 | COMP | 2020-07-17 | COMP | 2020-08-25 | COMP | Rule 16 | 3 | 29 | 26 | 1 | 39 | 28 | 122
18131 | 2020-03-06 | 2020-03-12 | 2020-06-25 | 2020-07-28 | COMP | 2020-09-04 | COMP | 2020-09-11 | COMP | 2020-10-13 | COMP | 2021-03-12 | COMP | Rule 16 | 5 | 75 | 29 | 5 | 23 | 102 | 257
18157 | 2020-03-06 | 2020-03-12 | 2020-08-20 | 2020-08-20 | COMP | 2021-01-26 | COMP | 2022-04-13 | COMP | 2022-04-28 | COMP | 2022-05-27 | COMP | Rule 15/16 | 5 | 115 | 107 | 308 | 12 | 22 | 564
18450 | 2020-03-06 | 2020-03-24 | 2020-07-27 | 2020-07-27 | COMP | 2020-07-30 | COMP | 2020-09-11 | COMP | 2020-09-19 | COMP | 2020-11-13 | COMP | Rule 16 | 13 | 89 | 4 | 31 | 6 | 39 | 178
18529 | 2020-03-06 | 2020-03-27 | 2020-10-05 | 2020-10-05 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2020-10-19 | COMP | 2020-11-06 | COMP | Rule 15/16 | 16 | 135 | 11 | 1 | 1 | 15 | 174
18544 | 2020-03-06 | 2020-03-28 | 2020-08-18 | 2020-08-18 | COMP | 2020-08-21 | COMP | 2020-11-09 | COMP | 2020-12-15 | COMP | 2020-01-06 | COMP | Rule 16 | 16 | 101 | 4 | 56 | 24
18581 | 2020-03-06 | 2020-03-30 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-14 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-08-14 | COMP | Rule 16 | 17 | 27 | 8 | 12 | 1 | 55 | 115
18687 | 2020-03-06 | 2020-04-02 | 2020-06-03 | 2020-06-03 | COMP | 2020-06-24 | COMP | 2020-06-24 | COMP | 2020-07-08 | COMP | 2020-07-28 | COMP | Rule 16 | 20 | 44 | 16 | 1 | 11 | 15 | 102
18759 | 2020-03-06 | 2020-04-06 | 2020-06-25 | 2020-07-03 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2020-10-29 | COMP | 2020-12-18 | COMP | Rule 16 | 22 | 58 | 83 | 1 | 2 | 34 | 201
18764 | 2020-03-06 | 2020-04-06 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-29 | COMP | 2020-07-02 | COMP | 2020-06-08 | COMP | 2020-07-21 | COMP | Rule 16 | 22 | 26 | 14 | 25 | 0 | 14 | 97
18769 | 2020-03-06 | 2020-04-06 | 2020-05-15 | 2020-05-28 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-07-06 | COMP | 2020-07-31 | COMP | Rule 16 | 22 | 30 | 19 | 1 | 10 | 20 | 105
18922 | 2020-03-06 | 2020-04-13 | 2020-06-24 | 2020-06-24 | COMP | 2020-09-02 | COMP | 2020-09-02 | COMP | 2020-12-01 | COMP | 2021-01-07 | COMP | Rule 16 | 27 | 52 | 51 | 1 | 61 | 26 | 213
18999 | 2020-03-06 | 2020-04-17 | 2020-05-06 | 2020-05-06 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-09-29 | COMP | Rule 16 | 31 | 14 | 64 | 1 | 1 | 40 | 146
19019 | 2020-03-06 | 2020-04-17 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-07 | COMP | 2020-07-30 | COMP | 2020-08-04 | COMP | 2020-09-01 | COMP | Rule 16 | 31 | 53 | 5 | 18 | 4 | 21 | 127
19242 | 2020-03-06 | 2020-04-28 | 2020-11-03 | 2020-11-03 | COMP | 2020-12-02 | COMP | 2021-07-14 | COMP | 2021-07-16 | COMP | 2021-07-27 | COMP | Rule 16 | 38 | 134 | 19 | 155 | 3 | 8 | 352
19312 | 2020-03-06 | 2020-04-29 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2022-01-31 | INPR | 2020-06-16 | COMP | Rule 16 | 39 | 5 | 8 | 1 |  |  | 72
19384 | 2020-03-06 | 2020-05-04 | 2020-10-29 | 2020-10-29 | COMP | 2020-11-06 | COMP | 2021-03-31 | COMP | 2023-09-30 | INPR | 2021-11-19 | COMP | Rule 16 | 42 | 127 | 7 | 97 |  |  | 433
19412 | 2020-03-06 | 2020-05-05 | 2020-08-13 | 2020-08-13 | COMP | 2022-01-27 | COMP | 2022-09-02 | COMP | 2022-06-13 | COMP | 2022-10-25 | COMP | Rule 16 | 43 | 72 | 366 | 153 | 0 | 37 | 667
19773 | 2020-03-06 | 2020-05-21 | 2021-06-08 | 2021-06-08 | COMP | 2021-10-19 | COMP | 2022-06-16 | COMP | 2022-06-21 | COMP | 2023-04-13 | COMP | Rule 15/16 | 55 | 264 | 94 | 167 | 3 | 204 | 782
19976 | 2020-03-06 | 2020-05-30 | 2020-12-16 | 2020-12-16 | COMP | 2021-01-19 | COMP | 2021-04-01 | COMP | 2021-07-02 | COMP | 2021-07-09 | COMP | Rule 16 | 60 | 139 | 22 | 52 | 66 | 5 | 340
20122 | 2020-03-06 | 2020-06-05 | 2020-08-05 | 2022-07-18 | COMP | 2022-08-05 | COMP | 2021-06-30 | COMP | 2020-10-22 | COMP | 2023-06-27 | COMP | Rule 16 | 65 | 44 | 15 |  | 0 | 500 | 833
20439 | 2020-03-06 | 2020-06-20 | 2020-09-06 | 2020-09-06 | COMP | 2020-10-16 | COMP | 2020-12-24 | INPR | 2023-12-04 | CANC | 2020-11-20 | COMP | Rule 15/16 | 75 | 55 | 29 |  |  |  | 183
24360 | 2020-03-06 | 2020-12-21 | 2021-01-28 | 2021-01-28 | COMP | 2021-02-02 | COMP | 2021-02-04 | COMP | 2021-02-22 | COMP | 2021-02-19 | COMP | Rule 16 | 202 | 26 | 4 | 3 | 12 |  | 242
18074 | 2020-03-07 | 2020-03-10 | 2020-06-11 | 2020-06-11 | COMP | 2020-08-07 | COMP | 2021-03-06 | COMP | 2021-02-23 | COMP | 2021-04-06 | COMP | Rule 16 | 2 | 67 | 42 | 143 | 0 | 22 | 273
18085 | 2020-03-07 | 2020-03-10 | 2020-07-14 | 2021-02-06 | COMP | 2021-03-05 | COMP | 2021-03-30 | COMP | 2021-03-09 | COMP | 2021-04-30 | COMP | Rule 15/16 | 2 | 90 | 19 | 18 | 0 | 24 | 291
18092 | 2020-03-07 | 2020-03-10 | 2020-05-04 | 2020-05-04 | COMP | 2020-05-18 | COMP | 2020-05-18 | COMP | 2020-10-08 | COMP | 2020-11-12 | COMP | Rule 15/16 | 2 | 40 | 11 | 1 | 102 | 25 | 176
18214 | 2020-03-07 | 2020-03-16 | 2020-05-30 | 2020-07-17 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-06-30 | COMP | 2020-09-15 | COMP | Rule 16 | 6 | 54 | 16 | 1 | 0 | 27 | 135
21050 | 2020-03-07 | 2020-07-20 | 2021-03-08 | 2021-03-08 | COMP | 2021-03-16 | COMP | 2021-07-15 | COMP | 2022-06-02 | COMP | 2022-07-14 | COMP | Rule 16 | 95 | 158 | 7 | 86 | 224 | 29 | 594
21263 | 2020-03-07 | 2020-07-29 | 2020-12-16 | 2020-12-16 | COMP | 2020-12-28 | COMP | 2020-12-28 | COMP | 2022-01-31 | INPR | 2021-01-12 | COMP | Rule 16 | 102 | 97 | 8 | 1 |  |  | 215
19814 | 2020-03-08 | 2020-05-23 | 2020-09-06 | 2020-09-06 | COMP | 2020-10-19 | COMP | 2020-10-27 | COMP | 2022-01-31 | INPR | 2020-12-02 | COMP | Rule 16 | 55 | 74 | 30 | 7 |  |  | 188
4280 | 2020-03-09 | 2020-03-14 | 2020-09-04 | 2020-09-04 | COMP |  |  |  |  | 2020-10-28 | COMP | 2022-09-13 | COMP | Other | 5 | 124 |  |  |  |  | 636
18022 | 2020-03-09 | 2020-03-09 | 2020-04-04 | 2020-04-04 | COMP | 2020-05-04 | COMP | 2020-06-26 | COMP | 2020-06-30 | COMP | 2020-07-21 | COMP | Rule 16 | 1 | 20 | 21 | 39 | 3 | 16 | 96
18027 | 2020-03-09 | 2020-03-09 | 2020-03-17 | 2020-03-17 | COMP | 2020-04-01 | COMP | 2020-05-04 | COMP | 2020-06-02 | COMP | 2020-06-16 | COMP | Rule 15/16 | 1 | 7 | 12 | 24 | 21 | 11 | 71
18151 | 2020-03-09 | 2020-03-12 | 2020-04-02 | 2020-04-02 | COMP | 2020-05-08 | COMP | 2020-06-17 | COMP | 2020-06-18 | COMP | 2020-07-30 | COMP | Rule 16 | 4 | 16 | 27 | 28 | 2 | 31 | 103
18152 | 2020-03-09 | 2020-03-12 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-06-15 | COMP | 2020-07-08 | COMP | Rule 16 | 4 | 30 | 11 | 1 | 28 | 18 | 87
18348 | 2020-03-09 | 2020-03-20 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-09-15 | COMP | 2020-10-02 | COMP | Rule 16 | 10 | 51 | 8 | 1 | 69 | 14 | 148
18393 | 2020-03-09 | 2020-03-23 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-31 | COMP | 2020-08-18 | COMP | 2020-11-10 | COMP | 2020-12-10 | COMP | Rule 16 | 11 | 63 | 32 | 13 | 60 | 20 | 194
18424 | 2020-03-09 | 2020-03-23 | 2020-11-30 | 2020-11-30 | COMP | 2020-12-10 | COMP | 2021-01-27 | COMP | 2023-11-13 | INPR | 2021-02-22 | COMP | Rule 16 | 11 | 176 | 9 | 32 |  |  | 242
18542 | 2020-03-09 | 2020-03-28 | 2020-05-19 | 2020-05-19 | COMP | 2020-09-10 | COMP | 2020-09-10 | INPR | 2020-09-25 | COMP | 2020-10-24 | COMP | Other | 15 | 37 | 81 |  |  |  | 163
18610 | 2020-03-09 | 2020-03-31 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-08-03 | COMP | 2020-09-02 | COMP | Rule 15/16 | 17 | 36 | 24 | 1 | 31 | 23 | 127
18648 | 2020-03-09 | 2020-04-01 | 2020-06-04 | 2020-06-04 | COMP | 2020-06-24 | COMP | 2020-06-25 | COMP | 2020-07-27 | COMP | 2020-08-31 | COMP | Rule 15/16 | 18 | 46 | 15 | 2 | 23 | 26 | 125
18976 | 2020-03-09 | 2020-04-15 | 2020-11-10 | 2020-11-10 | COMP | 2020-11-16 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2020-12-21 | COMP | Rule 16 | 28 | 148 | 4 | 16 | 1 | 9 | 201
19066 | 2020-03-09 | 2020-04-20 | 2020-08-11 | 2020-08-11 | COMP | 2020-08-19 | COMP | 2020-10-05 | COMP | 2020-10-06 | COMP | 2020-11-12 | COMP | Rule 15/16 | 31 | 81 | 7 | 33 | 2 | 27 | 176
19293 | 2020-03-09 | 2020-04-28 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-10-26 | COMP | 2020-12-08 | COMP | Rule 16 | 37 | 18 | 7 | 1 | 105 | 29 | 192
19611 | 2020-03-09 | 2020-05-14 | 2021-11-09 | 2021-11-09 | COMP | 2021-12-23 | COMP | 2022-05-13 | COMP | 2022-04-26 | COMP | 2022-06-18 | COMP | Rule 15/16 | 49 | 377 | 30 | 100 | 0 | 25 | 577
19661 | 2020-03-09 | 2020-05-17 | 2020-07-17 | 2020-07-17 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-13 | COMP | 2020-09-30 | COMP | Rule 15/16 | 50 | 44 | 6 | 1 | 15 | 34 | 146
19685 | 2020-03-09 | 2020-05-18 | 2020-07-24 | 2020-07-24 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-18 | COMP | 2020-09-18 | COMP | Rule 15/16 | 51 | 49 | 6 | 1 | 13 | 23 | 138
19794 | 2020-03-09 | 2020-05-21 | 2020-11-06 | 2020-11-06 | COMP | 2021-01-05 | COMP | 2021-01-05 | COMP | 2021-11-22 | COMP | 2021-12-14 | COMP | Rule 16 | 54 | 120 | 38 | 1 | 224 | 15 | 447
19955 | 2020-03-09 | 2020-05-28 | 2020-08-19 | 2020-08-19 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2020-11-02 | COMP | 2021-01-07 | COMP | Rule 16 | 58 | 60 | 23 | 1 | 31 | 44 | 212
20006 | 2020-03-09 | 2020-06-01 | 2020-07-22 | 2020-07-22 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2022-08-21 | REQD | 2020-11-19 | COMP | Rule 16 | 60 | 38 | 12 | 1 |  |  | 181
20399 | 2020-03-09 | 2020-06-18 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-08-25 | COMP | 2020-10-22 | COMP | Rule 16 | 73 | 19 | 17 | 1 | 15 | 42 | 162
21064 | 2020-03-09 | 2020-07-20 | 2020-12-30 | 2020-12-30 | COMP | 2021-01-21 | COMP | 2022-04-07 | COMP | 2022-04-28 | COMP | 2022-10-11 | COMP | Rule 16 | 95 | 113 | 15 | 307 | 16 | 115 | 656
22145 | 2020-03-09 | 2020-09-11 | 2020-12-08 | 2020-12-08 | COMP | 2020-12-16 | COMP | 2020-12-16 | COMP | 2020-12-18 | COMP | 2021-02-08 | COMP | Rule 16 | 133 | 60 | 7 | 1 | 3 | 34 | 233
18195 | 2020-03-10 | 2020-03-14 | 2021-01-18 | 2021-01-18 | COMP | 2021-03-02 | COMP | 2021-11-18 | COMP | 2021-09-15 | COMP | 2021-11-23 | COMP | Rule 16 | 4 | 213 | 30 | 184 | 0 | 4 | 433
18282 | 2020-03-10 | 2020-03-18 | 2020-05-26 | 2020-05-26 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-07-29 | COMP | Rule 16 | 7 | 49 | 14 | 1 | 1 | 34 | 101
18310 | 2020-03-10 | 2020-03-19 | 2020-04-22 | 2020-04-22 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2021-04-23 | COMP | 2021-05-26 | COMP | Rule 16 | 8 | 25 | 17 | 1 | 238 | 24 | 308
18468 | 2020-03-10 | 2020-03-25 | 2021-04-07 | 2021-04-07 | COMP | 2021-10-20 | COMP | 2021-11-22 | COMP | 2022-01-20 | COMP | 2022-02-15 | COMP | Rule 15/16 | 12 | 262 | 138 | 23 | 41 | 19 | 490
18469 | 2020-03-10 | 2020-03-26 | 2020-04-13 | 2020-04-13 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2022-11-30 | COMP | 2022-03-26 | COMP | Rule 16 | 13 | 13 | 71 | 1 | 594 |  | 517
18541 | 2020-03-10 | 2020-03-27 | 2020-04-03 | 2020-04-03 | COMP | 2020-04-08 | COMP | 2020-04-08 | COMP | 2020-06-03 | COMP | 2020-06-06 | COMP | Rule 16 | 14 | 6 | 4 | 1 | 40 | 3 | 63
18558 | 2020-03-10 | 2020-03-30 | 2020-10-06 | 2021-03-08 | COMP | 2021-04-07 | COMP | 2021-04-22 | COMP | 2021-08-12 | COMP | 2021-09-13 | COMP | Rule 16 | 15 | 135 | 23 | 12 | 79 | 22 | 383
18812 | 2020-03-10 | 2020-04-07 | 2020-10-06 | 2020-12-02 | COMP | 2020-12-07 | COMP | 2020-12-30 | COMP | 2020-12-21 | COMP | 2021-01-22 | COMP | Rule 15/16 | 21 | 129 | 4 | 17 | 0 | 16 | 221
18836 | 2020-03-10 | 2020-04-08 | 2020-10-03 | 2020-10-03 | COMP | 2020-11-23 | COMP | 2021-01-14 | COMP | 2020-12-04 | COMP | 2021-03-13 | COMP | Rule 16 | 22 | 126 | 35 | 35 | 0 | 40 | 255
18937 | 2020-03-10 | 2020-04-13 | 2020-10-23 | 2020-11-18 | COMP | 2020-12-03 | COMP | 2020-12-03 | COMP | 2020-12-03 | COMP | 2021-04-06 | COMP | Rule 16 | 25 | 138 | 10 | 1 | 1 | 85 | 272
19073 | 2020-03-10 | 2020-04-20 | 2020-09-15 | 2020-09-15 | COMP | 2021-09-20 | COMP | 2021-10-20 | COMP | 2021-10-06 | COMP | 2021-12-02 | COMP | Rule 16 | 30 | 105 | 255 | 23 | 0 | 29 | 438
19109 | 2020-03-10 | 2020-04-21 | 2020-08-04 | 2020-08-04 | COMP | 2020-08-11 | COMP | 2020-09-25 | COMP | 2020-09-21 | COMP | 2020-10-07 | COMP | Rule 16 | 31 | 75 | 6 | 33 | 0 | 9 | 150
19236 | 2020-03-10 | 2020-04-27 | 2020-05-06 | 2020-05-06 | COMP | 2020-05-07 | NOTN | 2020-05-07 | COMP | 2020-05-07 | COMP | 2020-07-08 | COMP | Other | 35 | 8 |  | 2 | 1 | 44 | 86
19255 | 2020-03-10 | 2020-04-28 | 2020-05-22 | 2020-07-03 | COMP | 2020-07-10 | COMP | 2020-07-10 | COMP | 2022-01-30 | INPR | 2020-12-04 | COMP | Rule 16 | 36 | 19 | 6 | 1 |  |  | 189
19327 | 2020-03-10 | 2020-05-01 | 2020-06-09 | 2020-06-09 | COMP | 2020-09-29 | COMP | 2021-02-10 | COMP | 2021-01-25 | COMP | 2021-03-30 | COMP | Rule 16 | 39 | 27 | 80 | 91 | 0 | 34 | 267
19335 | 2020-03-10 | 2020-05-01 | 2020-12-28 | 2020-12-28 | COMP |  | INPR | 2021-02-11 | COMP | 2021-06-17 | COMP | 2021-09-08 | COMP | Rule 15/16 | 39 | 166 |  | 32 | 89 | 58 | 380
19400 | 2020-03-10 | 2020-05-04 | 2020-05-21 | 2020-05-21 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2020-11-27 | COMP | 2020-12-03 | COMP | Rule 16 | 40 | 14 | 16 | 1 | 117 | 4 | 188
19867 | 2020-03-10 | 2020-05-26 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-07-14 | COMP | 2020-07-14 | COMP | Rule 16 | 55 | 23 | 11 | 1 | 4 | 1 | 90
19887 | 2020-03-10 | 2020-05-27 | 2020-09-10 | 2020-09-11 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2020-12-15 | COMP | 2021-01-12 | COMP | Rule 16 | 56 | 76 | 16 | 1 | 50 | 19 | 214
19956 | 2020-03-10 | 2020-05-29 | 2020-08-13 | 2020-08-13 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP |  | INPR | 2020-10-22 | COMP | Rule 16 | 58 | 55 | 41 | 1 |  |  | 161
20066 | 2020-03-10 | 2020-06-03 | 2020-11-10 | 2021-02-01 | COMP | 2021-02-11 | COMP | 2021-03-16 | COMP | 2021-04-06 | COMP | 2021-04-16 | COMP | Rule 16 | 61 | 114 | 9 | 23 | 16 | 9 | 280
20105 | 2020-03-10 | 2020-06-05 | 2020-08-10 | 2021-04-30 | COMP | 2021-05-11 | COMP | 2021-08-20 | COMP | 2021-08-02 | COMP | 2021-09-10 | COMP | Rule 15/16 | 63 | 47 | 8 | 72 | 0 | 15 | 382
20184 | 2020-03-10 | 2020-06-09 | 2020-07-02 | 2020-07-02 | COMP | 2020-08-11 | COMP | 2020-08-20 | COMP | 2022-07-01 | COMP | 2022-12-12 | COMP | Rule 16 | 65 | 18 | 29 | 8 | 469 | 112 | 696
20185 | 2020-03-10 | 2020-06-09 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-06 | COMP | 2020-08-06 | COMP | 2022-07-01 | COMP | 2022-08-02 | COMP | Rule 16 | 65 | 13 | 31 | 1 | 479 | 22 | 606
20190 | 2020-03-10 | 2020-06-10 | 2020-08-05 | 2020-09-28 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2023-11-13 | INPR | 2020-11-12 | COMP | Rule 16 | 66 | 41 | 13 | 1 |  |  | 175
20191 | 2020-03-10 | 2020-06-10 | 2020-08-05 | 2020-08-05 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2020-11-30 | COMP | 2020-12-28 | COMP | Rule 16 | 66 | 41 | 28 | 1 | 53 | 20 | 204
20216 | 2020-03-10 | 2020-06-11 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-11 | COMP | 2020-10-02 | COMP | 2022-07-01 | COMP | 2022-12-13 | COMP | Rule 16 | 67 | 24 | 21 | 38 | 439 | 113 | 697
20410 | 2020-03-10 | 2020-06-18 | 2020-12-23 | 2020-12-23 | COMP | 2021-02-04 | COMP | 2021-09-07 | COMP | 2021-09-08 | COMP | 2021-09-24 | COMP | Rule 16 | 72 | 131 | 29 | 150 | 2 | 13 | 392
20506 | 2020-03-10 | 2020-06-23 | 2020-11-09 | 2020-11-09 | COMP | 2020-11-25 | COMP | 2021-01-27 | COMP | 2021-07-23 | COMP | 2021-08-23 | COMP | Rule 16 | 75 | 99 | 12 | 41 | 125 | 22 | 369
20672 | 2020-03-10 | 2020-07-01 | 2020-08-26 | 2020-08-26 | COMP | 2020-11-16 | COMP | 2020-11-23 | COMP | 2020-12-21 | COMP | 2021-01-07 | COMP | Rule 16 | 81 | 41 | 57 | 6 | 19 | 12 | 211
20738 | 2020-03-10 | 2020-07-03 | 2020-08-19 | 2020-08-19 | COMP | 2020-09-04 | COMP | 2020-09-16 | COMP | 2020-10-05 | COMP | 2020-11-05 | COMP | Rule 16 | 83 | 34 | 13 | 8 | 14 | 24 | 171
21040 | 2020-03-10 | 2020-07-20 | 2020-09-11 | 2020-09-11 | COMP | 2020-10-13 | COMP | 2020-11-16 | COMP | 2020-12-04 | COMP | 2020-12-08 | COMP | Rule 16 | 94 | 39 | 23 | 24 | 13 | 3 | 191
21315 | 2020-03-10 | 2020-07-31 | 2020-09-28 | 2020-09-28 | COMP | 2020-10-15 | COMP | 2020-10-15 | COMP | 2023-01-28 | INPR | 2021-11-29 | COMP | Rule 16 | 103 | 41 | 14 | 1 |  |  | 435
21892 | 2020-03-10 | 2020-09-03 | 2020-09-04 | 2020-09-04 | COMP | 2020-09-10 | COMP | 2020-09-10 | COMP | 2020-09-29 | COMP | 2020-11-30 | COMP | Rule 16 | 127 | 2 | 4 | 1 | 14 | 42 | 185
18287 | 2020-03-11 | 2020-03-18 | 2020-05-19 | 2020-05-19 | COMP | 2020-05-19 | NOTN | 2020-05-19 | COMP | 2020-05-23 | COMP | 2020-07-13 | COMP | Other | 6 | 45 |  | 1 | 4 | 35 | 88
18294 | 2020-03-11 | 2020-03-19 | 2020-07-15 | 2020-07-15 | COMP | 2020-09-28 | COMP | 2022-02-03 | COMP | 2022-02-15 | COMP | 2022-03-31 | COMP | Rule 15/16 | 7 | 84 | 53 | 340 | 9 | 32 | 520
18641 | 2020-03-11 | 2020-04-01 | 2020-10-22 | 2020-10-22 | COMP | 2021-05-14 | COMP | 2021-06-01 | COMP | 2021-06-25 | COMP | 2021-07-28 | COMP | Rule 16 | 16 | 145 | 140 | 12 | 19 | 23 | 350
18826 | 2020-03-11 | 2020-04-08 | 2020-09-03 | 2020-09-03 | COMP | 2020-09-30 | COMP | 2020-09-30 | COMP | 2020-11-19 | COMP | 2020-11-23 | COMP | Rule 15/16 | 21 | 106 | 19 | 1 | 36 | 3 | 181
18832 | 2020-03-11 | 2020-04-09 | 2020-05-04 | 2020-05-04 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2020-07-08 | COMP | 2020-07-10 | COMP | Rule 16 | 22 | 18 | 33 | 1 | 15 | 3 | 87
18839 | 2020-03-11 | 2020-04-09 | 2020-06-02 | 2020-06-02 | COMP | 2020-08-04 | COMP | 2020-08-18 | COMP | 2020-08-13 | COMP | 2020-09-28 | COMP | Rule 16 | 22 | 38 | 46 | 11 | 0 | 29 | 142
18907 | 2020-03-11 | 2020-04-13 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-22 | COMP | 2020-06-22 | COMP | 2020-08-04 | COMP | 2020-08-28 | COMP | Rule 16 | 24 | 43 | 8 | 1 | 32 | 19 | 122
18957 | 2020-03-11 | 2020-04-15 | 2020-06-12 | 2020-06-12 | COMP | 2020-12-29 | COMP | 2020-12-29 | COMP | 2020-12-29 | COMP | 2021-02-19 | COMP | Rule 16 | 26 | 42 | 138 | 1 | 1 | 36 | 239
19010 | 2020-03-11 | 2020-04-17 | 2020-07-08 | 2020-10-15 | COMP | 2020-11-17 | COMP | 2020-12-17 | COMP | 2020-12-15 | COMP | 2021-02-23 | COMP | Rule 16 | 28 | 58 | 23 | 21 | 0 | 45 | 241
19110 | 2020-03-11 | 2020-04-21 | 2020-06-11 | 2020-06-11 | COMP | 2020-07-06 | COMP | 2021-04-08 | COMP | 2021-04-06 | COMP | 2021-06-28 | COMP | Rule 16 | 30 | 37 | 18 | 191 | 0 | 57 | 329
19289 | 2020-03-11 | 2020-04-28 | 2020-06-22 | 2020-06-22 | COMP | 2020-06-29 | COMP | 2020-06-29 | COMP | 2020-07-08 | COMP | 2020-07-20 | COMP | Rule 16 | 35 | 39 | 6 | 1 | 8 | 9 | 93
19326 | 2020-03-11 | 2020-05-01 | 2020-08-04 | 2020-08-04 | COMP | 2020-09-29 | COMP | 2020-09-29 | COMP | 2021-03-16 | COMP | 2021-03-26 | COMP | Rule 16 | 38 | 67 | 40 | 1 | 114 | 9 | 264
19342 | 2020-03-11 | 2020-05-01 | 2020-08-28 | 2020-08-28 | COMP | 2020-09-04 | COMP | 2020-09-17 | COMP | 2020-09-04 | COMP | 2021-02-03 | COMP | Rule 16 | 38 | 85 | 6 | 9 | 0 | 94 | 228
19715 | 2020-03-11 | 2020-05-19 | 2020-10-10 | 2021-02-04 | COMP | 2021-03-10 | COMP | 2021-03-12 | COMP | 2021-03-24 | COMP | 2021-04-20 | COMP | Rule 16 | 50 | 102 | 24 | 3 | 9 | 20 | 281
19835 | 2020-03-11 | 2020-05-26 | 2020-07-24 | 2022-01-13 | COMP | 2022-08-08 | COMP | 2022-09-13 | COMP | 2022-09-14 | COMP | 2022-11-11 | COMP | Rule 16 | 54 | 44 | 143 | 26 | 2 | 42 | 676
19890 | 2020-03-11 | 2020-05-27 | 2020-09-10 | 2020-09-10 | COMP | 2020-10-20 | COMP | 2021-03-11 | COMP | 2021-04-16 | COMP | 2021-04-20 | COMP | Rule 16 | 55 | 76 | 29 | 96 | 27 | 3 | 281
20107 | 2020-03-11 | 2020-06-05 | 2020-07-10 | 2020-07-10 | COMP | 2020-10-05 | COMP | 2020-10-14 | COMP | 2021-04-07 | COMP | 2021-09-29 | COMP | Rule 15/16 | 62 | 26 | 61 | 8 | 119 | 123 | 394
20139 | 2020-03-11 | 2020-06-08 | 2020-07-09 | 2020-07-28 | COMP | 2020-08-14 | COMP | 2020-12-10 | COMP | 2020-10-23 | COMP | 2021-01-06 | COMP | Rule 16 | 63 | 24 | 14 | 81 | 0 | 18 | 209
20194 | 2020-03-11 | 2020-06-10 | 2020-07-29 | 2020-07-29 | COMP | 2020-08-03 | COMP | 2020-10-06 | COMP | 2022-01-31 | INPR | 2020-12-03 | COMP | Rule 16 | 65 | 36 | 4 | 46 |  |  | 187
20241 | 2020-03-11 | 2020-06-12 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2020-10-05 | COMP | 2020-11-20 | COMP | Rule 16 | 67 | 46 | 7 | 1 | 30 | 34 | 180
21316 | 2020-03-11 | 2020-07-31 | 2020-08-21 | 2020-08-21 | COMP | 2020-09-01 | COMP | 2020-09-01 | COMP | 2020-09-16 | COMP | 2020-11-18 | COMP | Rule 16 | 102 | 16 | 8 | 1 | 11 | 45 | 178
21501 | 2020-03-11 | 2020-08-10 | 2021-06-10 | 2021-06-17 | COMP | 2021-07-02 | COMP | 2021-07-02 | COMP | 2021-12-13 | COMP | 2022-02-20 | COMP | Rule 15/16 | 108 | 210 | 12 | 1 | 112 | 49 | 492
21631 | 2020-03-11 | 2020-08-17 | 2020-12-08 | 2020-12-08 | COMP | 2021-01-07 | COMP | 2021-01-28 | COMP | 2022-03-20 | INPR | 2021-03-16 | COMP | Rule 16 | 113 | 78 | 21 | 15 |  |  | 256
21986 | 2020-03-11 | 2020-09-07 | 2020-10-03 | 2021-04-27 | COMP | 2021-05-07 | COMP | 2021-05-07 | COMP | 2021-10-26 | COMP | 2021-11-09 | COMP | Rule 16 | 127 | 19 | 9 | 1 | 120 | 11 | 423
24333 | 2020-03-11 | 2020-12-20 | 2021-03-08 | 2021-03-08 | COMP | 2021-03-29 | COMP | 2021-03-29 | COMP | 2022-07-25 | COMP | 2022-09-26 | COMP | Rule 16 | 198 | 52 | 16 | 1 | 335 | 45 | 643
41148 | 2020-03-11 | 2023-02-27 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-09 | NOTN | 2023-09-01 | COMP | 2023-12-07 | COMP | 2023-09-14 | COMP | Other | 746 | 62 |  | 71 | 66 |  | 885
41164 | 2020-03-11 | 2023-02-27 | 2023-06-02 | 2023-06-02 | COMP | 2023-06-02 | NOTN | 2023-08-07 | COMP | 2023-06-20 | COMP | 2023-08-14 | COMP | Other | 746 | 69 |  | 45 | 0 | 6 | 863
4306 | 2020-03-12 | 2020-06-19 | 2021-03-08 | 2022-07-27 | COMP | 2021-06-15 | COMP | 2022-07-27 | COMP | 2022-08-02 | COMP | 2022-08-12 | COMP | Rule 15/16 | 71 | 179 |  | 282 | 5 | 9 | 612
18245 | 2020-03-12 | 2020-03-17 | 2020-10-21 | 2021-10-29 | COMP | 2021-12-22 | COMP | 2021-07-22 | COMP | 2021-10-01 | COMP | 2021-10-07 | COMP | Rule 15/16 | 4 | 155 | 36 |  | 51 | 5 | 399
18392 | 2020-03-12 | 2020-03-23 | 2020-04-28 | 2020-04-28 | COMP | 2020-05-06 | COMP | 2020-05-06 | COMP | 2020-06-29 | COMP | 2020-07-27 | COMP | Rule 16 | 8 | 27 | 7 | 1 | 38 | 21 | 97
18582 | 2020-03-12 | 2020-03-30 | 2020-10-27 | 2020-11-16 | COMP | 2020-12-18 | COMP | 2021-02-05 | COMP | 2021-02-02 | COMP | 2021-03-09 | COMP | Rule 15/16 | 13 | 150 | 23 | 33 | 0 | 22 | 250
18603 | 2020-03-12 | 2020-03-31 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-13 | COMP | 2020-12-01 | COMP | 2020-10-19 | COMP | 2020-12-22 | COMP | Rule 16 | 14 | 59 | 16 | 98 | 0 | 16 | 199
18614 | 2020-03-12 | 2020-03-31 | 2020-09-02 | 2020-09-02 | COMP | 2020-09-02 | NOTN | 2020-10-28 | COMP | 2021-02-17 | COMP | 2021-02-20 | COMP | Other | 14 | 111 |  | 40 | 74 | 3 | 238
18705 | 2020-03-12 | 2020-04-02 | 2020-05-29 | 2020-05-29 | COMP | 2020-06-25 | COMP | 2020-06-25 | COMP | 2020-08-28 | COMP | 2020-10-06 | COMP | Rule 16 | 16 | 41 | 20 | 1 | 47 | 27 | 147
18774 | 2020-03-12 | 2020-04-06 | 2020-05-20 | 2020-05-20 | COMP | 2020-06-10 | COMP | 2020-07-06 | COMP | 2020-06-22 | COMP | 2020-08-07 | COMP | Rule 16 | 18 | 33 | 15 | 19 | 0 | 25 | 106
18885 | 2020-03-12 | 2020-04-11 | 2020-06-22 | 2020-06-22 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2020-09-02 | COMP | 2020-09-02 | COMP | Rule 16 | 22 | 50 | 29 | 1 | 25 | 1 | 124
19149 | 2020-03-12 | 2020-04-22 | 2020-09-09 | 2020-09-09 | COMP | 2020-09-17 | COMP | 2020-09-17 | COMP | 2021-03-15 | COMP | 2021-04-05 | COMP | Rule 16 | 30 | 99 | 7 | 1 | 121 | 16 | 269
19248 | 2020-03-12 | 2020-04-28 | 2020-07-15 | 2020-07-15 | COMP | 2023-03-08 | COMP | 2023-05-08 | COMP | 2023-06-27 | COMP | 2023-08-01 | COMP | Rule 16 | 34 | 56 | 664 | 44 | 35 | 25 | 853
19311 | 2020-03-12 | 2020-04-29 | 2020-10-21 | 2021-02-08 | COMP | 2021-02-18 | COMP | 2020-12-10 | COMP | 2021-04-06 | COMP | 2021-04-09 | COMP | Rule 15/16 | 35 | 124 | 8 |  | 80 | 4 | 273
19443 | 2020-03-12 | 2020-05-06 | 2020-08-21 | 2020-08-21 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-10-02 | COMP | 2020-12-30 | COMP | Rule 16 | 40 | 77 | 22 | 1 | 9 | 60 | 204
19553 | 2020-03-12 | 2020-05-12 | 2020-08-14 | 2020-08-14 | COMP | 2020-10-05 | COMP | 2020-10-05 | COMP | 2020-12-01 | COMP | 2020-12-11 | COMP | Rule 16 | 44 | 68 | 36 | 1 | 39 | 9 | 192
19604 | 2020-03-12 | 2020-05-14 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-23 | COMP | 2020-07-15 | COMP | 2020-07-28 | COMP | 2020-10-02 | COMP | Rule 16 | 46 | 26 | 3 | 17 | 10 | 48 | 145
19755 | 2020-03-12 | 2020-05-20 | 2020-08-27 | 2020-08-27 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2021-01-20 | COMP | 2021-03-03 | COMP | Rule 16 | 50 | 71 | 19 | 1 | 80 | 30 | 246
19943 | 2020-03-12 | 2020-05-28 | 2020-07-28 | 2020-07-28 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2021-01-04 | COMP | 2021-02-02 | COMP | Rule 16 | 55 | 44 | 21 | 1 | 89 | 21 | 226
19970 | 2020-03-12 | 2020-05-30 | 2020-07-02 | 2020-10-21 | COMP | 2020-11-04 | COMP | 2020-11-06 | COMP | 2020-11-14 | COMP | 2020-12-04 | COMP | Rule 16 | 56 | 24 | 11 | 3 | 5 | 13 | 187
19991 | 2020-03-12 | 2020-06-01 | 2020-06-15 | 2020-06-15 | COMP | 2020-06-29 | COMP | 2020-07-27 | COMP | 2020-07-13 | COMP | 2020-08-11 | COMP | Rule 16 | 57 | 11 | 11 | 21 | 0 | 12 | 108
20096 | 2020-03-12 | 2020-06-04 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-24 | COMP | 2020-08-03 | COMP | 2020-08-31 | COMP | 2020-08-31 | COMP | Rule 16 | 60 | 19 | 19 | 7 | 21 | 1 | 122
20436 | 2020-03-12 | 2020-06-20 | 2020-08-05 | 2020-08-05 | COMP | 2020-11-06 | COMP | 2020-11-06 | COMP | 2021-03-22 | COMP | 2021-04-22 | COMP | Rule 16 | 71 | 33 | 67 | 1 | 90 | 24 | 282
20517 | 2020-03-12 | 2020-06-24 | 2020-08-11 | 2021-08-18 | COMP | 2021-08-31 | COMP | 2020-11-03 | COMP | 2023-04-30 | INPR | 2021-11-29 | COMP | Rule 16 | 74 | 35 | 10 |  |  |  | 433
20529 | 2020-03-12 | 2020-06-24 | 2020-08-07 | 2020-09-14 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2021-04-06 | COMP | 2021-05-05 | COMP | Rule 16 | 74 | 33 | 60 | 1 | 81 | 22 | 291
20774 | 2020-03-12 | 2020-07-06 | 2020-09-09 | 2020-09-09 | COMP | 2021-03-09 | COMP | 2021-03-10 | COMP | 2021-05-24 | COMP | 2021-06-07 | COMP | Rule 16 | 82 | 47 | 123 | 2 | 54 | 10 | 313
21019 | 2020-03-12 | 2020-07-17 | 2021-03-12 | 2021-04-01 | COMP | 2021-07-02 | COMP | 2021-08-05 | COMP | 2022-01-04 | COMP | 2022-04-28 | COMP | Rule 15/16 | 91 | 163 | 66 | 24 | 105 | 81 | 539
21073 | 2020-03-12 | 2020-07-20 | 2020-08-12 | 2020-08-12 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2021-01-12 | COMP | 2021-02-07 | COMP | Rule 16 | 92 | 18 | 28 | 1 | 77 | 18 | 229
21499 | 2020-03-12 | 2020-08-10 | 2021-05-19 | 2021-05-19 | COMP | 2021-08-20 | COMP | 2022-01-05 | COMP |  | INPR | 2022-01-28 | COMP | Rule 16 | 107 | 195 | 66 | 95 |  |  | 476
22222 | 2020-03-12 | 2020-09-16 | 2020-12-14 | 2020-12-14 | COMP | 2022-03-15 | COMP | 2022-03-15 | COMP | 2022-03-16 | COMP | 2022-04-12 | COMP | Rule 16 | 133 | 61 | 315 | 1 | 2 | 20 | 527
39132 | 2020-03-12 | 2022-10-03 | 2022-10-11 | 2022-10-11 | COMP | 2022-10-21 | COMP | 2023-05-16 | COMP | 2023-05-15 | COMP | 2023-06-26 | COMP | Rule 16 | 647 | 7 | 9 | 141 | 0 | 28 | 828
18299 | 2020-03-13 | 2020-03-18 | 2020-06-10 | 2020-06-10 | COMP | 2020-07-09 | COMP | 2020-07-15 | COMP | 2020-07-03 | COMP | 2020-07-24 | COMP | Rule 16 | 4 | 60 | 22 | 5 | 0 | 8 | 95
18364 | 2020-03-13 | 2020-03-21 | 2020-06-24 | 2020-06-24 | COMP | 2021-09-27 | COMP | 2021-09-27 | COMP | 2021-09-27 | COMP | 2021-10-02 | COMP | Rule 16 | 6 | 67 | 318 | 1 | 1 | 5 | 394
18494 | 2020-03-13 | 2020-03-26 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-16 | NOTN | 2021-03-28 | COMP | 2021-03-30 | COMP | 2021-04-30 | COMP | Other | 10 | 97 |  | 157 | 2 | 24 | 287
18570 | 2020-03-13 | 2020-03-30 | 2020-07-17 | 2020-07-17 | COMP | 2021-03-10 | COMP | 2021-03-10 | COMP | 2021-03-15 | COMP | 2021-04-21 | COMP | Rule 15/16 | 12 | 79 | 161 | 1 | 4 | 28 | 280
18724 | 2020-03-13 | 2020-04-04 | 2020-11-03 | 2020-11-03 | COMP | 2021-01-19 | COMP | 2021-03-02 | COMP | 2021-01-19 | COMP | 2021-05-13 | COMP | Rule 16 | 16 | 150 | 50 | 30 | 0 | 53 | 296
18736 | 2020-03-13 | 2020-04-07 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-31 | COMP | 2020-11-09 | COMP | 2020-10-15 | COMP | 2021-02-03 | COMP | Rule 16 | 18 | 93 | 12 | 50 | 0 | 57 | 226
18899 | 2020-03-13 | 2020-04-11 | 2020-06-05 | 2020-06-05 | COMP | 2020-08-13 | COMP | 2020-08-13 | COMP | 2020-10-27 | COMP | 2020-11-13 | COMP | Rule 16 | 21 | 39 | 50 | 1 | 53 | 13 | 173
19174 | 2020-03-13 | 2020-04-22 | 2020-08-24 | 2020-08-24 | COMP | 2020-09-02 | COMP | 2020-10-06 | COMP | 2020-10-28 | COMP | 2020-12-30 | COMP | Rule 15/16 | 29 | 88 | 8 | 24 | 17 | 42 | 203
19241 | 2020-03-13 | 2020-04-27 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2021-05-03 | COMP | 2021-05-10 | COMP | Rule 16 | 32 | 55 | 18 | 1 | 186 | 6 | 293
19279 | 2020-03-13 | 2020-04-29 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-09 | COMP | 2020-07-09 | COMP | 2020-07-18 | COMP | 2020-07-22 | COMP | Rule 16 | 34 | 45 | 7 | 1 | 7 | 3 | 93
19353 | 2020-03-13 | 2020-05-02 | 2020-05-18 | 2020-05-18 | COMP | 2020-06-02 | COMP | 2020-06-02 | NOTN | 2020-09-30 | COMP | 2020-10-21 | COMP | Rule 16 | 36 | 11 | 11 |  |  |  | 157
19355 | 2020-03-13 | 2020-05-02 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-12 | COMP | 2020-08-11 | NOTN | 2020-08-18 | COMP | 2020-09-10 | COMP | Rule 16 | 36 | 20 | 10 |  |  |  | 128
19456 | 2020-03-13 | 2020-05-07 | 2020-12-18 | 2021-02-22 | COMP | 2021-03-30 | COMP | 2021-03-30 | COMP | 2021-05-27 | COMP | 2021-05-28 | COMP | Rule 16 | 40 | 157 | 27 | 1 | 43 | 2 | 307
19479 | 2020-03-13 | 2020-05-08 | 2020-07-15 | 2020-07-15 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2021-06-01 | COMP | 2021-08-13 | COMP | Rule 16 | 41 | 48 | 69 | 1 | 153 | 53 | 360
19535 | 2020-03-13 | 2020-05-11 | 2020-06-29 | 2021-04-13 | COMP | 2021-05-06 | COMP | 2021-07-19 | COMP | 2021-05-12 | COMP | 2021-11-09 | COMP | Rule 16 | 42 | 35 | 18 | 51 | 0 | 81 | 421
19561 | 2020-03-13 | 2020-05-12 | 2020-06-12 | 2020-06-12 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2021-11-04 | COMP | 2022-02-28 | COMP | Rule 16 | 43 | 23 | 115 | 1 | 240 | 78 | 495
19756 | 2020-03-13 | 2020-05-20 | 2020-06-23 | 2020-06-23 | COMP | 2020-08-31 | COMP | 2020-09-03 | COMP | 2021-03-18 | COMP | 2021-04-30 | COMP | Rule 16 | 49 | 24 | 50 | 4 | 133 | 32 | 287
19889 | 2020-03-13 | 2020-05-27 | 2020-07-08 | 2020-11-05 | COMP | 2020-12-18 | COMP | 2020-12-18 | COMP | 2020-12-22 | COMP | 2021-01-09 | COMP | Rule 16 | 53 | 31 | 29 | 1 | 3 | 12 | 209
20113 | 2020-03-13 | 2020-06-04 | 2020-07-31 | 2020-07-31 | COMP | 2020-08-06 | COMP | 2020-08-27 | COMP | 2020-08-10 | COMP | 2020-09-16 | COMP | Rule 15/16 | 59 | 42 | 5 | 16 | 0 | 14 | 132
20126 | 2020-03-13 | 2020-06-06 | 2020-07-09 | 2020-09-25 | COMP | 2020-11-25 | COMP | 2020-11-30 | COMP | 2021-12-06 | COMP | 2022-03-25 | COMP | Rule 15/16 | 60 | 24 | 43 | 2 | 256 | 78 | 514
20465 | 2020-03-13 | 2020-06-22 | 2020-09-15 | 2020-09-15 | COMP | 2020-12-15 | COMP | 2021-03-25 | COMP | 2021-04-27 | COMP | 2021-06-10 | COMP | Rule 16 | 71 | 61 | 63 | 69 | 24 | 32 | 315
20721 | 2020-03-13 | 2020-07-02 | 2020-09-26 | 2020-09-26 | COMP | 2020-09-23 | NOTN | 2021-03-26 | COMP | 2021-03-30 | COMP | 2021-04-24 | COMP | Other | 79 | 61 |  | 123 | 3 | 19 | 282
21003 | 2020-03-13 | 2020-07-17 | 2020-09-11 | 2020-09-11 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2020-12-09 | COMP | 2021-01-24 | COMP | Rule 16 | 90 | 40 | 7 | 1 | 55 | 30 | 218
21008 | 2020-03-13 | 2020-07-17 | 2020-09-18 | 2020-09-18 | COMP | 2020-07-17 | NOTN | 2020-09-18 | COMP | 2020-09-21 | COMP | 2020-10-23 | COMP | Other | 90 | 45 |  | 1 | 2 | 25 | 159
21565 | 2020-03-13 | 2020-08-13 | 2020-09-08 | 2020-09-08 | COMP | 2020-12-14 | COMP | 2020-12-14 | COMP | 2021-01-27 | COMP | 2021-02-01 | COMP | Rule 16 | 109 | 18 | 67 | 1 | 30 | 4 | 224
21839 | 2020-03-13 | 2020-08-30 | 2020-11-05 | 2020-11-05 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | 2022-01-05 | COMP | 2022-02-19 | COMP | Rule 16 | 120 | 48 | 43 | 1 | 250 | 32 | 490
21877 | 2020-03-13 | 2020-08-31 | 2020-11-13 | 2020-11-13 | COMP | 2021-02-23 | COMP | 2021-02-25 | COMP | 2021-04-26 | COMP | 2021-05-04 | COMP | Rule 16 | 121 | 53 | 67 | 3 | 43 | 7 | 289
22089 | 2020-03-13 | 2020-09-10 | 2020-11-10 | 2021-08-25 | COMP | 2021-09-14 | COMP | 2022-01-31 | COMP | 2022-02-18 | COMP | 2022-02-26 | COMP | Rule 16 | 128 | 44 | 14 | 96 | 15 | 5 | 494
22856 | 2020-03-13 | 2020-10-14 | 2020-12-22 | 2020-12-22 | COMP | 2022-03-02 | COMP | 2022-03-02 | COMP | 2022-03-02 | COMP | 2022-04-25 | COMP | Rule 16 | 152 | 47 | 300 | 1 | 1 | 39 | 535
23013 | 2020-03-13 | 2020-10-20 | 2020-10-31 | 2020-10-31 | COMP | 2020-11-13 | COMP | 2020-11-25 | COMP | 2021-01-20 | COMP | 2021-01-05 | COMP | Rule 16 | 156 | 9 | 9 | 9 | 36 |  | 206
18518 | 2020-03-14 | 2020-03-27 | 2020-06-29 | 2020-06-29 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP | 2020-09-15 | COMP | 2020-09-30 | COMP | Rule 16 | 10 | 66 | 42 | 1 | 15 | 12 | 141
19250 | 2020-03-14 | 2020-04-28 | 2020-07-29 | 2020-07-29 | COMP | 2021-02-17 | COMP | 2021-02-17 | COMP | 2022-01-12 | COMP | 2022-02-26 | COMP | Rule 16 | 32 | 66 | 138 | 1 | 230 | 31 | 493
19981 | 2020-03-14 | 2020-06-02 | 2020-08-12 | 2020-08-12 | COMP | 2020-09-21 | COMP | 2020-10-15 | COMP | 2020-10-26 | COMP | 2020-11-24 | COMP | Rule 16 | 56 | 52 | 28 | 19 | 8 | 21 | 179
22947 | 2020-03-14 | 2020-10-16 | 2020-12-10 | 2020-12-10 | COMP | 2020-12-14 | COMP | 2021-01-12 | COMP | 2021-02-09 | COMP | 2021-03-03 | COMP | Rule 16 | 153 | 37 | 3 | 20 | 20 | 16 | 244
19329 | 2020-03-15 | 2020-05-02 | 2020-08-20 | 2020-08-20 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-12-21 | COMP | 2021-01-13 | COMP | Rule 16 | 35 | 78 | 21 | 1 | 64 | 16 | 211
18350 | 2020-03-16 | 2020-03-21 | 2020-07-13 | 2020-07-13 | COMP | 2020-12-11 | NOTN | 2020-12-11 | COMP | 2020-12-28 | COMP | 2021-04-07 | COMP | Other | 5 | 80 |  | 106 | 11 | 70 | 269
18590 | 2020-03-16 | 2020-03-30 | 2020-07-27 | 2020-07-27 | COMP | 2020-09-08 | COMP | 2020-12-09 | COMP | 2021-03-16 | COMP | 2021-05-06 | COMP | Rule 16 | 11 | 85 | 31 | 64 | 66 | 38 | 290
18721 | 2020-03-16 | 2020-04-03 | 2020-10-21 | 2020-10-21 | COMP | 2020-10-27 | COMP | 2020-12-09 | COMP | 2020-12-04 | COMP | 2021-02-09 | COMP | Rule 16 | 15 | 142 | 5 | 29 | 0 | 42 | 229
18739 | 2020-03-16 | 2020-04-06 | 2020-07-22 | 2020-07-22 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2021-03-09 | COMP | Rule 15/16 | 16 | 77 | 87 | 1 | 1 | 71 | 248
18753 | 2020-03-16 | 2020-04-07 | 2020-07-10 | 2020-07-10 | COMP | 2020-07-13 | NOTN | 2020-07-13 | COMP | 2022-08-16 | COMP | 2022-12-07 | COMP | Other | 17 | 68 |  | 2 | 528 | 78 | 689
18930 | 2020-03-16 | 2020-04-13 | 2020-09-03 | 2020-09-03 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2020-11-02 | COMP | 2020-12-04 | COMP | Rule 15/16 | 21 | 103 | 16 | 1 | 27 | 22 | 185
18943 | 2020-03-16 | 2020-04-13 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-14 | COMP | 2020-05-14 | COMP | 2020-08-19 | COMP | 2020-08-21 | COMP | Rule 16 | 21 | 21 | 4 | 1 | 69 | 3 | 114
18974 | 2020-03-16 | 2020-04-15 | 2020-09-21 | 2020-09-21 | COMP | 2020-10-12 | COMP | 2020-10-21 | COMP | 2022-01-30 | INPR | 2020-12-10 | COMP | Rule 16 | 23 | 112 | 16 | 8 |  |  | 189
19032 | 2020-03-16 | 2020-04-17 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-03 | COMP | 2020-08-29 | COMP | 2020-08-25 | COMP | 2020-09-25 | COMP | Rule 16 | 25 | 62 | 15 | 20 | 0 | 19 | 138
19102 | 2020-03-16 | 2020-04-21 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-10-19 | COMP | 2020-12-10 | COMP | Rule 16 | 27 | 59 | 20 | 1 | 51 | 36 | 189
19103 | 2020-03-16 | 2020-04-21 | 2020-10-19 | 2020-10-19 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2021-02-24 | COMP | 2021-04-05 | COMP | Rule 15/16 | 27 | 128 | 11 | 1 | 76 | 29 | 267
19137 | 2020-03-16 | 2020-04-21 | 2020-07-16 | 2020-09-11 | COMP | 2021-03-25 | COMP | 2021-04-07 | COMP | 2021-03-25 | COMP | 2021-05-06 | COMP | Rule 16 | 27 | 62 | 133 | 10 | 0 | 22 | 290
19164 | 2020-03-16 | 2020-04-22 | 2020-05-21 | 2020-05-21 | COMP | 2020-12-22 | COMP | 2021-03-22 | COMP | 2021-04-19 | COMP | 2022-02-27 | COMP | Rule 16 | 28 | 22 | 149 | 61 | 21 | 217 | 493
19465 | 2020-03-16 | 2020-05-07 | 2020-08-11 | 2020-08-12 | COMP | 2020-08-18 | COMP | 2020-08-27 | INPR | 2020-09-04 | COMP | 2020-09-14 | COMP | Rule 16 | 39 | 68 | 5 |  |  |  | 129
19506 | 2020-03-16 | 2020-05-09 | 2020-06-05 | 2020-12-23 | COMP | 2021-01-14 | COMP | 2020-07-10 | COMP | 2021-02-12 | COMP | 2021-03-31 | COMP | Rule 15/16 | 40 | 19 | 15 |  | 149 | 33 | 264
19752 | 2020-03-16 | 2020-05-20 | 2020-10-09 | 2021-05-13 | COMP | 2021-05-27 | COMP | 2021-06-10 | COMP | 2021-07-19 | COMP | 2021-09-01 | COMP | Rule 16 | 48 | 101 | 11 | 10 | 27 | 33 | 372
19780 | 2020-03-16 | 2020-05-22 | 2020-07-15 | 2020-07-15 | COMP | 2020-09-17 | COMP | 2020-10-08 | COMP | 2021-01-20 | COMP | 2021-03-04 | COMP | Rule 16 | 50 | 38 | 46 | 16 | 69 | 31 | 245
19834 | 2020-03-16 | 2020-05-26 | 2020-06-23 | 2020-06-23 | COMP | 2020-08-17 | COMP | 2021-01-06 | COMP | 2020-12-08 | COMP | 2021-02-08 | COMP | Rule 16 | 51 | 21 | 40 | 97 | 0 | 23 | 228
19865 | 2020-03-16 | 2020-05-26 | 2020-07-14 | 2021-04-23 | COMP | 2021-05-19 | COMP | 2021-06-24 | COMP | 2021-06-24 | COMP | 2022-02-16 | COMP | Rule 16 | 51 | 36 | 19 | 26 | 1 | 164 | 487
20262 | 2020-03-16 | 2020-06-11 | 2020-07-31 | 2020-07-31 | COMP | 2021-05-04 | COMP | 2021-07-24 | COMP | 2021-07-20 | COMP | 2021-08-23 | COMP | Rule 15/16 | 63 | 37 | 190 | 57 | 0 | 21 | 365
20562 | 2020-03-16 | 2020-06-26 | 2020-07-31 | 2020-07-31 | COMP | 2020-09-29 | COMP | 2020-11-19 | COMP | 2020-11-19 | COMP | 2021-03-19 | COMP | Rule 16 | 74 | 26 | 42 | 37 | 1 | 81 | 256
20674 | 2020-03-16 | 2020-06-30 | 2020-09-25 | 2020-09-25 | COMP | 2020-12-18 | COMP | 2021-04-28 | COMP | 2021-05-25 | COMP | 2021-07-20 | COMP | Rule 16 | 76 | 63 | 58 | 90 | 20 | 39 | 341
20689 | 2020-03-16 | 2020-07-01 | 2020-08-10 | 2020-08-10 | COMP | 2020-11-17 | COMP | 2020-11-17 | COMP | 2020-11-19 | COMP | 2021-01-02 | COMP | Rule 16 | 77 | 29 | 70 | 1 | 3 | 28 | 203
20731 | 2020-03-16 | 2020-07-03 | 2020-09-14 | 2020-09-14 | COMP | 2020-09-23 | COMP | 2020-12-16 | COMP | 2021-01-12 | COMP | 2021-02-16 | COMP | Rule 16 | 79 | 51 | 8 | 58 | 18 | 24 | 233
20808 | 2020-03-16 | 2020-07-07 | 2021-01-26 | 2021-01-26 | COMP | 2021-02-12 | COMP | 2021-05-03 | COMP | 2021-03-01 | COMP | 2021-06-04 | COMP | Rule 16 | 81 | 139 | 14 | 56 | 0 | 24 | 310
20957 | 2020-03-16 | 2020-07-14 | 2020-09-08 | 2020-10-06 | COMP | 2020-10-29 | COMP | 2020-11-05 | COMP | 2020-11-10 | COMP | 2020-12-16 | COMP | Rule 16 | 86 | 40 | 18 | 6 | 4 | 24 | 193
20972 | 2020-03-16 | 2020-07-16 | 2020-10-07 | 2020-10-07 | COMP | 2020-10-15 | COMP | 2020-12-29 | COMP | 2021-03-22 | COMP | 2021-05-11 | COMP | Rule 16 | 88 | 59 | 7 | 50 | 57 | 37 | 293
21148 | 2020-03-16 | 2020-07-23 | 2021-01-22 | 2021-01-23 | COMP | 2021-02-09 | COMP | 2021-02-09 | COMP | 2021-08-19 | COMP | 2021-09-16 | COMP | Rule 16 | 93 | 125 | 12 | 1 | 135 | 20 | 382
21370 | 2020-03-16 | 2020-08-04 | 2020-11-13 | 2020-11-13 | COMP | 2021-01-04 | NOTN | 2021-03-17 | COMP | 2021-03-19 | NOTN | 2021-05-10 | COMP | Other | 101 | 72 |  | 83 |  |  | 292
22304 | 2020-03-16 | 2020-09-18 | 2020-10-26 | 2021-01-28 | COMP | 2021-03-24 | COMP | 2021-10-05 | COMP | 2021-10-12 | COMP | 2021-11-30 | COMP | Rule 15/16 | 133 | 27 | 39 | 137 | 6 | 33 | 432
23403 | 2020-03-16 | 2020-11-05 | 2021-02-22 | 2021-02-22 | COMP | 2021-04-21 | COMP | 2021-04-21 | COMP | 2023-04-30 | INPR | 2022-01-21 | COMP | Rule 16 | 167 | 71 | 43 | 1 |  |  | 469
18254 | 2020-03-17 | 2020-03-17 | 2020-04-08 | 2020-04-08 | COMP | 2020-05-29 | COMP | 2020-05-28 | COMP | 2023-12-09 | INPR | 2020-06-04 | COMP | Rule 16 | 1 | 17 | 37 |  |  |  | 57
18329 | 2020-03-17 | 2020-03-20 | 2020-06-09 | 2020-08-21 | COMP | 2020-11-05 | COMP | 2020-11-24 | COMP | 2020-11-24 | COMP | 2020-12-30 | COMP | Rule 15/16 | 4 | 57 | 54 | 13 | 1 | 24 | 201
18336 | 2020-03-17 | 2020-03-20 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-05 | COMP | 2020-05-05 | COMP | 2022-01-30 | INPR | 2020-07-17 | COMP | Rule 16 | 4 | 17 | 17 | 1 |  |  | 88
18359 | 2020-03-17 | 2020-03-21 | 2020-04-13 | 2020-04-13 | COMP | 2020-05-11 | COMP | 2020-10-01 | NOTN | 2021-10-25 | COMP | 2021-10-28 | COMP | Rule 16 | 4 | 16 | 21 |  |  |  | 411
18394 | 2020-03-17 | 2020-03-23 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-10-31 | COMP | 2020-12-08 | COMP | Rule 16 | 5 | 79 | 24 | 1 | 57 | 24 | 186
18417 | 2020-03-17 | 2020-03-23 | 2020-07-16 | 2020-07-16 | COMP | 2020-08-11 | COMP | 2020-08-11 | COMP | 2020-09-10 | COMP | 2020-10-27 | COMP | Rule 15/16 | 5 | 83 | 19 | 1 | 22 | 34 | 159
18428 | 2020-03-17 | 2020-03-24 | 2020-07-15 | 2020-08-31 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2022-06-18 | INPR | 2021-06-16 | COMP | Rule 16 | 6 | 81 | 31 | 1 |  |  | 317
18516 | 2020-03-17 | 2020-03-27 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-07 | COMP | 2020-08-26 | COMP | 2020-08-25 | COMP | 2020-09-25 | COMP | Rule 15/16 | 9 | 64 | 32 | 14 | 0 | 22 | 137
18652 | 2020-03-17 | 2020-04-01 | 2020-06-26 | 2020-06-26 | COMP | 2020-06-29 | NOTN | 2020-06-29 | COMP | 2020-07-21 | COMP | 2020-08-13 | COMP | Other | 12 | 62 |  | 2 | 17 | 18 | 107
19031 | 2020-03-17 | 2020-04-17 | 2020-05-25 | 2020-05-25 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2021-02-03 | COMP | 2021-03-22 | COMP | Rule 16 | 24 | 26 | 157 | 1 | 19 | 33 | 256
19100 | 2020-03-17 | 2020-04-21 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-03 | COMP | 2020-06-08 | COMP | Rule 16 | 26 | 19 | 13 | 1 | 1 | 4 | 59
19153 | 2020-03-17 | 2020-04-22 | 2020-07-07 | 2020-07-07 | COMP | 2020-07-03 | NOTN | 2020-08-14 | COMP | 2020-07-03 | COMP | 2021-02-11 | COMP | Other | 27 | 54 |  | 29 | 0 | 123 | 230
19285 | 2020-03-17 | 2020-04-28 | 2020-06-05 | 2020-07-02 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2020-08-25 | COMP | 2020-10-01 | COMP | Rule 16 | 31 | 28 | 35 | 1 | 5 | 27 | 141
19392 | 2020-03-17 | 2020-05-04 | 2021-03-17 | 2021-03-17 | COMP | 2021-05-21 | COMP | 2023-01-18 | COMP | 2023-03-16 | COMP | 2023-03-24 | COMP | Rule 16 | 35 | 219 | 48 | 416 | 41 | 7 | 761
19660 | 2020-03-17 | 2020-05-17 | 2020-08-07 | 2020-08-07 | COMP | 2020-08-20 | COMP | 2020-09-24 | COMP | 2020-08-20 | COMP | 2020-11-06 | COMP | Rule 16 | 44 | 59 | 10 | 25 | 0 | 32 | 167
19736 | 2020-03-17 | 2020-05-19 | 2020-07-24 | 2020-09-25 | COMP | 2020-10-02 | COMP | 2020-08-17 | COMP | 2020-08-03 | COMP | 2020-11-23 | COMP | Rule 16 | 46 | 48 | 6 |  | 0 | 69 | 177
19917 | 2020-03-17 | 2020-05-27 | 2020-12-23 | 2020-12-23 | COMP | 2021-02-18 | COMP | 2021-02-23 | COMP | 2021-05-04 | COMP | 2021-10-01 | COMP | Rule 15/16 | 51 | 147 | 38 | 4 | 51 | 106 | 392
19940 | 2020-03-17 | 2020-05-29 | 2021-01-28 | 2021-06-17 | COMP | 2021-09-29 | COMP | 2021-10-28 | COMP | 2021-10-13 | NOTN | 2021-11-16 | COMP | Rule 16 | 53 | 168 | 73 | 22 |  |  | 423
19983 | 2020-03-17 | 2020-05-31 | 2020-07-10 | 2020-07-10 | COMP | 2020-07-27 | COMP | 2020-11-10 | INPR | 2020-09-28 | COMP | 2021-01-13 | COMP | Rule 16 | 53 | 30 | 12 |  |  |  | 210
20112 | 2020-03-17 | 2020-06-04 | 2020-08-23 | 2020-08-23 | COMP | 2020-09-15 | COMP | 2020-10-23 | COMP | 2020-09-23 | COMP | 2020-11-05 | COMP | Rule 16 | 57 | 57 | 16 | 29 | 0 | 10 | 166
20260 | 2020-03-17 | 2020-06-12 | 2020-11-15 | 2020-11-15 | COMP | 2021-01-06 | COMP | 2021-05-27 | COMP | 2022-02-16 | COMP | 2022-09-23 | COMP | Rule 16 | 63 | 109 | 34 | 100 | 183 | 153 | 638
20394 | 2020-03-17 | 2020-06-17 | 2020-07-14 | 2020-07-14 | COMP | 2020-09-01 | COMP | 2020-10-01 | COMP | 2020-09-14 | COMP | 2020-10-28 | COMP | Rule 15/16 | 66 | 20 | 36 | 22 | 0 | 20 | 160
20414 | 2020-03-17 | 2020-06-20 | 2020-08-06 | 2020-08-06 | COMP | 2020-12-07 | COMP | 2021-03-24 | COMP | 2021-03-22 | COMP | 2021-04-26 | COMP | Rule 16 | 68 | 34 | 84 | 74 | 0 | 24 | 281
20424 | 2020-03-17 | 2020-06-19 | 2020-07-28 | 2020-07-28 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-09-08 | COMP | 2020-09-16 | COMP | Rule 16 | 68 | 28 | 12 | 1 | 19 | 7 | 130
20643 | 2020-03-17 | 2020-06-30 | 2021-02-10 | 2022-01-19 | COMP | 2022-02-11 | COMP | 2022-06-02 | COMP | 2022-06-01 | COMP | 2022-07-19 | COMP | Rule 16 | 75 | 155 | 18 | 78 | 0 | 32 | 591
20766 | 2020-03-17 | 2020-07-04 | 2020-08-13 | 2020-08-13 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | 2021-01-25 | COMP | 2021-02-22 | COMP | Rule 16 | 78 | 29 | 107 | 1 | 5 | 20 | 236
20859 | 2020-03-17 | 2020-07-09 | 2020-08-24 | 2020-08-24 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2020-11-09 | COMP | 2021-01-15 | COMP | Other | 82 | 33 | 36 | 1 | 20 | 45 | 212
21335 | 2020-03-17 | 2020-08-04 | 2020-10-14 | 2020-10-14 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2022-01-25 | COMP | 2022-02-23 | COMP | Rule 16 | 100 | 51 | 5 | 1 | 317 | 21 | 490
22265 | 2020-03-17 | 2020-09-16 | 2020-12-23 | 2020-12-23 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP | 2021-03-17 | COMP | 2021-04-28 | COMP | Rule 16 | 130 | 68 | 10 | 1 | 48 | 31 | 283
4283 | 2020-03-18 | 2020-03-18 | 2020-04-29 | 2020-04-29 | COMP | 2020-05-29 | COMP | 2020-09-18 | COMP | 2020-09-21 | COMP | 2020-10-21 | COMP | Rule 16 | 1 | 31 | 22 | 80 | 2 | 23 | 154
18312 | 2020-03-18 | 2020-03-19 | 2020-05-12 | 2020-05-12 | COMP | 2020-06-10 | COMP | 2020-06-10 | COMP | 2020-06-11 | COMP | 2020-07-22 | COMP | Rule 16 | 2 | 39 | 21 | 1 | 2 | 30 | 90
18385 | 2020-03-18 | 2020-03-22 | 2020-05-20 | 2020-08-28 | COMP | 2020-09-08 | COMP | 2020-09-17 | INPR | 2022-05-28 | REQD | 2020-12-04 | COMP | Rule 16 | 3 | 43 | 7 |  |  |  | 183
18656 | 2020-03-18 | 2020-04-02 | 2020-08-24 | 2020-09-21 | COMP | 2020-10-08 | COMP | 2020-10-08 | COMP |  |  | 2023-06-21 | COMP | Rule 16 | 12 | 102 | 14 | 1 |  |  | 821
18798 | 2020-03-18 | 2020-04-07 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-08 | COMP | 2020-06-08 | COMP | 2020-08-18 | COMP | 2020-10-06 | COMP | Rule 16 | 15 | 36 | 9 | 1 | 52 | 35 | 143
18956 | 2020-03-18 | 2020-04-14 | 2020-07-10 | 2020-09-11 | COMP | 2020-09-22 | COMP | 2021-03-15 | COMP | 2021-06-30 | COMP | 2021-07-23 | COMP | Rule 16 | 20 | 63 | 8 | 118 | 77 | 17 | 342
18968 | 2020-03-18 | 2020-04-15 | 2020-08-31 | 2020-08-31 | COMP | 2020-09-16 | COMP | 2020-10-27 | COMP | 2021-01-12 | COMP | 2021-02-16 | COMP | Rule 16 | 21 | 98 | 12 | 30 | 51 | 24 | 231
19210 | 2020-03-18 | 2020-04-24 | 2020-10-15 | 2022-02-23 | COMP | 2022-04-18 | COMP | 2022-04-26 | INPR | 2022-04-25 | COMP | 2022-06-15 | COMP | Rule 15/16 | 28 | 123 | 39 |  |  |  | 568
19587 | 2020-03-18 | 2020-05-14 | 2020-08-17 | 2020-08-17 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2022-01-11 | COMP | 2022-02-10 | COMP | Rule 16 | 42 | 67 | 25 | 1 | 329 | 22 | 481
19864 | 2020-03-18 | 2020-05-26 | 2020-07-07 | 2020-07-07 | COMP | 2020-09-25 | COMP | 2021-07-13 | COMP | 2021-07-13 | COMP | 2021-09-13 | COMP | Rule 16 | 49 | 31 | 58 | 199 | 1 | 44 | 377
20144 | 2020-03-18 | 2020-06-08 | 2020-07-03 | 2020-07-03 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2021-10-19 | COMP | 2021-11-17 | COMP | Rule 15/16 | 58 | 20 | 11 | 1 | 317 | 21 | 423
20195 | 2020-03-18 | 2020-06-10 | 2020-07-08 | 2020-07-08 | COMP | 2020-08-24 | COMP | 2020-08-24 | COMP | 2022-01-31 | INPR | 2020-09-09 | COMP | Rule 16 | 60 | 21 | 34 | 1 |  |  | 124
20209 | 2020-03-18 | 2020-06-11 | 2020-08-24 | 2020-08-24 | COMP | 2021-04-14 | COMP | 2021-04-14 | COMP | 2022-06-22 | COMP | 2022-08-27 | COMP | Rule 15/16 | 61 | 53 | 160 | 1 | 301 | 47 | 618
20248 | 2020-03-18 | 2020-06-11 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-06 | COMP | 2020-08-06 | NOTN | 2020-08-12 | COMP | 2020-08-19 | COMP | Rule 16 | 61 | 22 | 20 |  |  |  | 110
20405 | 2020-03-18 | 2020-06-19 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-21 | COMP | 2020-10-22 | COMP | 2020-10-12 | COMP | 2020-12-01 | COMP | Rule 16 | 67 | 41 | 6 | 44 | 0 | 26 | 180
20524 | 2020-03-18 | 2020-06-24 | 2020-08-19 | 2020-08-19 | COMP | 2020-10-06 | COMP | 2020-10-30 | COMP | 2020-11-03 | COMP | 2020-12-02 | COMP | Rule 15/16 | 70 | 41 | 34 | 19 | 3 | 19 | 181
20790 | 2020-03-18 | 2020-07-07 | 2020-08-06 | 2020-08-06 | COMP | 2021-03-01 | COMP | 2021-03-01 | COMP | 2022-04-17 | INPR | 2021-03-18 | COMP | Rule 16 | 79 | 23 | 140 | 1 |  |  | 253
21115 | 2020-03-18 | 2020-07-22 | 2020-08-31 | 2020-08-31 | COMP | 2020-11-13 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2021-02-03 | COMP | Rule 16 | 90 | 29 | 53 | 15 | 1 | 40 | 223
21365 | 2020-03-18 | 2020-08-04 | 2020-09-15 | 2020-09-15 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2020-11-30 | COMP | 2021-01-02 | COMP | Rule 16 | 99 | 30 | 32 | 1 | 21 | 23 | 201
23212 | 2020-03-18 | 2020-10-28 | 2020-12-23 | 2021-01-14 | COMP | 2021-02-03 | COMP | 2021-02-18 | COMP | 2021-02-09 | COMP | 2021-05-06 | COMP | Rule 16 | 159 | 38 | 14 | 11 | 0 | 56 | 288
29858 | 2020-03-18 | 2021-08-03 | 2022-06-28 | 2023-04-04 | COMP | 2022-07-02 | NOTN | 2022-08-01 | COMP | 2023-05-19 | COMP | 2023-10-03 | COMP | Other | 349 | 228 |  |  | 202 | 94 | 893
40708 | 2020-03-18 | 2023-01-25 | 2023-06-05 | 2023-06-05 | COMP | 2023-06-05 | NOTN | 2023-08-07 | COMP |  | INPR | 2023-11-15 | COMP | Other | 719 | 92 |  | 44 |  |  | 923
4289 | 2020-03-19 | 2020-04-08 | 2020-07-09 | 2020-07-09 | COMP | 2022-04-16 | REQD | 2020-07-29 | COMP | 2021-01-20 | COMP | 2021-03-26 | COMP | Rule 16 | 15 | 66 |  | 15 | 119 | 47 | 258
18375 | 2020-03-19 | 2020-03-21 | 2020-05-21 | 2020-05-21 | COMP | 2020-12-11 | NOTN | 2021-03-12 | COMP | 2022-03-21 | COMP | 2022-04-11 | COMP | Other | 2 | 44 |  | 203 | 259 | 16 | 521
18653 | 2020-03-19 | 2020-04-01 | 2020-07-16 | 2021-04-22 | COMP | 2021-05-06 | COMP | 2021-05-06 | COMP | 2021-05-25 | COMP | 2021-05-27 | COMP | Rule 16 | 10 | 76 | 11 | 1 | 14 | 3 | 302
18714 | 2020-03-19 | 2020-04-03 | 2021-03-30 | 2021-03-30 | COMP | 2021-04-27 | COMP | 2022-07-07 | COMP | 2023-09-02 | INPR | 2022-08-03 | COMP | Rule 16 | 12 | 249 | 21 | 302 |  |  | 600
18802 | 2020-03-19 | 2020-04-07 | 2021-05-03 | 2021-05-03 | COMP | 2021-05-26 | COMP | 2022-06-10 | COMP |  | INPR | 2022-07-30 | COMP | Rule 15/16 | 14 | 271 | 18 | 264 |  |  | 597
18849 | 2020-03-19 | 2020-04-09 | 2020-06-04 | 2020-06-04 | COMP | 2020-07-15 | COMP | 2020-07-15 | COMP | 2020-07-16 | COMP | 2020-08-12 | COMP | Rule 16 | 16 | 40 | 30 | 1 | 2 | 20 | 104
18867 | 2020-03-19 | 2020-04-09 | 2020-07-24 | 2020-07-24 | COMP | 2020-09-17 | COMP | 2021-01-21 | COMP |  |  | 2021-07-02 | COMP | Rule 16 | 16 | 76 | 39 | 85 |  |  | 327
19070 | 2020-03-19 | 2020-04-21 | 2020-07-15 | 2020-07-15 | COMP | 2021-03-23 | COMP | 2021-04-21 | COMP | 2021-04-13 | COMP | 2021-07-01 | COMP | Rule 15/16 | 24 | 61 | 172 | 22 | 0 | 51 | 326
19131 | 2020-03-19 | 2020-04-21 | 2020-06-26 | 2020-12-28 | COMP | 2021-01-25 | COMP | 2021-03-03 | COMP | 2021-02-23 | COMP | 2021-04-06 | COMP | Rule 16 | 24 | 48 | 19 | 27 | 0 | 25 | 265
19307 | 2020-03-19 | 2020-04-29 | 2020-07-08 | 2020-07-08 | COMP | 2020-07-21 | COMP | 2020-07-30 | COMP | 2020-08-04 | COMP | 2020-10-01 | COMP | Rule 16 | 30 | 50 | 10 | 8 | 4 | 42 | 139
19512 | 2020-03-19 | 2020-05-11 | 2020-10-20 | 2020-10-20 | COMP | 2020-10-20 | NOTN | 2020-10-20 | COMP | 2020-11-02 | NOTN | 2020-12-09 | COMP | Other | 38 | 115 |  | 1 |  |  | 185
19568 | 2020-03-19 | 2020-05-12 | 2020-06-24 | 2020-06-24 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2021-01-04 | COMP | 2021-03-03 | COMP | Rule 16 | 39 | 31 | 54 | 1 | 80 | 41 | 241
19649 | 2020-03-19 | 2020-05-16 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-21 | COMP | 2020-07-21 | COMP | 2020-09-09 | COMP | 2020-10-12 | COMP | Rule 16 | 42 | 30 | 17 | 1 | 36 | 24 | 146
19665 | 2020-03-19 | 2020-05-17 | 2020-07-20 | 2020-07-20 | COMP | 2020-07-24 | COMP | 2020-10-02 | COMP | 2020-09-14 | COMP | 2020-11-09 | COMP | Rule 16 | 42 | 45 | 5 | 50 | 0 | 27 | 166
19827 | 2020-03-19 | 2020-05-26 | 2020-08-08 | 2020-08-13 | COMP | 2020-08-26 | COMP | 2020-09-15 | COMP | 2020-09-21 | COMP | 2020-09-29 | COMP | Rule 16 | 48 | 54 | 10 | 14 | 5 | 7 | 137
19868 | 2020-03-19 | 2020-05-26 | 2020-07-03 | 2020-07-03 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-10-02 | COMP | Rule 16 | 48 | 29 | 16 | 1 | 1 | 50 | 140
19896 | 2020-03-19 | 2020-05-27 | 2020-08-11 | 2021-04-01 | COMP | 2021-04-22 | COMP | 2021-05-17 | COMP | 2021-06-07 | COMP | 2021-06-22 | COMP | Rule 15/16 | 49 | 55 | 16 | 18 | 15 | 12 | 319
20569 | 2020-03-19 | 2020-06-26 | 2020-08-10 | 2020-08-10 | COMP | 2020-09-01 | COMP | 2020-09-04 | COMP | 2020-08-21 | COMP | 2020-10-29 | COMP | Rule 16 | 71 | 32 | 17 | 4 | 0 | 39 | 159
20994 | 2020-03-19 | 2020-07-17 | 2021-01-14 | 2021-01-14 | COMP | 2021-03-12 | COMP | 2021-10-21 | COMP | 2022-01-28 | COMP | 2023-03-31 | COMP | Rule 15/16 | 86 | 124 | 40 | 157 | 68 | 294 | 764
21132 | 2020-03-19 | 2020-07-22 | 2020-12-31 | 2021-08-28 | COMP | 2021-10-21 | COMP | 2022-04-14 | COMP | 2022-03-16 | COMP | 2022-05-15 | COMP | Rule 16 | 89 | 112 | 38 | 121 | 0 | 22 | 545
21227 | 2020-03-19 | 2020-07-28 | 2020-10-15 | 2021-03-23 | COMP | 2021-05-05 | COMP | 2021-03-11 | COMP | 2021-05-06 | COMP | 2021-07-15 | COMP | Rule 16 | 93 | 57 | 32 |  | 41 | 49 | 335
22099 | 2020-03-19 | 2020-09-10 | 2020-11-05 | 2020-11-05 | COMP | 2020-12-09 | COMP | 2020-12-09 | COMP | 2021-03-16 | COMP | 2021-04-22 | COMP | Rule 15/16 | 124 | 41 | 22 | 1 | 66 | 28 | 277
23252 | 2020-03-19 | 2020-10-29 | 2021-01-14 | 2021-10-26 | COMP | 2022-02-28 | COMP | 2022-10-12 | COMP | 2022-10-13 | COMP | 2023-02-10 | COMP | Rule 15/16 | 159 | 51 | 85 | 159 | 2 | 81 | 730
23408 | 2020-03-19 | 2020-11-05 | 2021-05-05 | 2021-05-05 | COMP | 2021-06-03 | COMP | 2021-06-03 | COMP | 2021-11-05 | COMP | 2021-12-01 | COMP | Rule 16 | 164 | 123 | 21 | 1 | 110 | 16 | 430
25104 | 2020-03-19 | 2021-01-28 | 2021-04-27 | 2021-04-27 | COMP | 2021-06-10 | COMP | 2021-09-29 | COMP | 2022-04-11 | COMP | 2022-08-10 | COMP | Rule 15/16 | 218 | 63 | 32 | 78 | 134 | 85 | 605
27077 | 2020-03-19 | 2021-04-15 | 2021-06-25 | 2021-06-25 | COMP | 2021-08-10 | COMP | 2021-08-13 | COMP | 2022-06-06 | COMP | 2022-06-22 | COMP | Rule 16 | 272 | 51 | 32 | 4 | 205 | 12 | 571
29028 | 2020-03-19 | 2021-07-02 | 2021-08-05 | 2021-12-06 | COMP | 2021-12-16 | COMP | 2021-09-03 | COMP | 2022-01-18 | COMP | 2022-01-27 | COMP | Rule 16 | 327 | 24 | 9 |  | 93 | 8 | 470
18445 | 2020-03-20 | 2020-03-24 | 2020-07-28 | 2020-07-28 | COMP | 2020-11-03 | NOTN | 2020-11-03 | COMP | 2020-11-04 | COMP | 2021-01-14 | COMP | Other | 3 | 90 |  | 70 | 2 | 47 | 208
18555 | 2020-03-20 | 2020-03-28 | 2020-06-29 | 2020-06-29 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-10-01 | COMP | 2020-11-02 | COMP | Rule 15/16 | 6 | 65 | 26 | 1 | 43 | 23 | 160
18787 | 2020-03-20 | 2020-04-06 | 2020-06-12 | 2020-06-12 | COMP | 2020-06-19 | NOTN | 2020-08-13 | COMP | 2020-07-08 | COMP | 2020-10-01 | COMP | Rule 16 | 12 | 49 |  | 45 | 0 | 35 | 138
18792 | 2020-03-20 | 2020-04-07 | 2020-05-29 | 2020-05-29 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2021-10-23 | INPR | 2020-08-26 | COMP | Rule 16 | 13 | 38 | 37 | 1 |  |  | 113
18998 | 2020-03-20 | 2020-04-16 | 2020-09-18 | 2020-09-18 | COMP | 2020-11-25 | COMP | 2020-12-15 | COMP | 2021-03-22 | COMP | 2021-05-07 | COMP | Rule 15/16 | 20 | 110 | 48 | 13 | 66 | 35 | 287
19074 | 2020-03-20 | 2020-04-21 | 2020-06-04 | 2020-06-04 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | Rule 16 | 23 | 32 | 76 | 1 | 4 | 1 | 132
19140 | 2020-03-20 | 2020-04-22 | 2020-08-14 | 2020-12-10 | COMP | 2020-12-17 | COMP | 2020-10-27 | COMP | 2021-02-17 | COMP | 2021-03-25 | COMP | Rule 16 | 24 | 82 | 6 |  | 75 | 27 | 256
19197 | 2020-03-20 | 2020-04-23 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-20 | COMP | 2020-07-13 | COMP | 2022-04-17 | INPR | 2020-09-09 | COMP | Rule 16 | 25 | 9 | 12 | 38 |  |  | 122
19278 | 2020-03-20 | 2020-04-29 | 2020-07-03 | 2020-07-22 | COMP | 2020-07-23 | NOTN | 2020-07-23 | COMP | 2020-07-21 | COMP | 2020-08-26 | COMP | Other | 29 | 47 |  | 2 | 0 | 25 | 113
21390 | 2020-03-20 | 2020-08-05 | 2020-10-26 | 2020-10-26 | COMP | 2020-11-12 | COMP | 2021-06-23 | COMP | 2023-12-04 | INPR | 2021-08-06 | COMP | Rule 15/16 | 98 | 58 | 13 | 153 |  |  | 350
21538 | 2020-03-20 | 2020-08-12 | 2020-10-22 | 2020-10-22 | COMP | 2021-01-27 | COMP | 2021-01-27 | COMP | 2023-12-04 | INPR | 2021-08-06 | COMP | Rule 16 | 103 | 51 | 64 | 1 |  |  | 350
21952 | 2020-03-20 | 2020-09-04 | 2020-11-04 | 2020-11-04 | COMP | 2021-09-16 | COMP | 2021-10-01 | COMP | 2022-01-24 | COMP | 2022-01-24 | COMP | Rule 15/16 | 120 | 43 | 217 | 12 | 78 | 1 | 466
34995 | 2020-03-20 | 2022-03-11 | 2022-10-07 | 2022-10-07 | COMP | 2022-10-19 | COMP | 2023-08-23 | COMP | 2023-09-06 | COMP | 2023-11-15 | COMP | Rule 16 | 499 | 147 | 9 | 211 | 10 | 50 | 921
18434 | 2020-03-21 | 2020-03-25 | 2020-06-25 | 2020-06-25 | COMP | 2020-03-26 | NOTN | 2020-07-13 | COMP | 2020-06-29 | COMP | 2020-09-16 | COMP | Other | 3 | 66 |  | 13 | 0 | 47 | 126
18819 | 2020-03-21 | 2020-04-08 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-04 | COMP | 2020-08-04 | COMP | 2020-08-31 | COMP | 2020-10-06 | COMP | Rule 16 | 13 | 68 | 17 | 1 | 20 | 26 | 140
20978 | 2020-03-21 | 2020-07-16 | 2020-11-16 | 2020-11-16 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2020-12-07 | COMP | 2020-12-16 | COMP | Rule 15/16 | 83 | 86 | 8 | 1 | 7 | 8 | 188
19086 | 2020-03-22 | 2020-04-20 | 2020-10-16 | 2021-06-15 | COMP | 2021-07-22 | COMP | 2021-07-22 | COMP | 2021-08-10 | COMP | 2021-09-09 | COMP | Rule 16 | 21 | 128 | 27 | 1 | 14 | 22 | 372
19580 | 2020-03-22 | 2020-05-13 | 2020-06-15 | 2020-06-15 | COMP | 2020-07-10 | COMP | 2020-08-23 | COMP | 2021-01-27 | COMP | 2021-03-03 | COMP | Rule 16 | 38 | 23 | 20 | 31 | 106 | 25 | 239
20458 | 2020-03-22 | 2020-06-22 | 2020-09-18 | 2021-02-18 | COMP | 2021-03-30 | COMP | 2021-03-30 | COMP | 2022-04-20 | COMP | 2022-05-07 | COMP | Rule 16 | 65 | 64 | 29 | 1 | 269 | 13 | 538
21104 | 2020-03-22 | 2020-07-22 | 2020-09-27 | 2020-09-27 | COMP | 2020-10-27 | COMP | 2020-10-27 | COMP | 2020-12-07 | COMP | 2021-01-05 | COMP | Rule 16 | 87 | 47 | 22 | 1 | 27 | 20 | 200
18439 | 2020-03-23 | 2020-03-24 | 2020-05-27 | 2020-05-27 | COMP | 2020-06-26 | COMP | 2020-08-14 | COMP | 2020-09-05 | COMP | 2020-11-10 | COMP | Rule 16 | 2 | 46 | 23 | 36 | 16 | 46 | 165
18471 | 2020-03-23 | 2020-03-27 | 2020-11-09 | 2020-11-09 | COMP | 2021-01-20 | COMP | 2021-02-19 | INPR | 2021-04-14 | COMP | 2021-04-26 | COMP | Rule 16 | 5 | 160 | 47 |  |  |  | 277
18712 | 2020-03-23 | 2020-04-03 | 2020-11-17 | 2020-12-29 | COMP | 2021-01-07 | COMP | 2021-03-03 | COMP | 2021-01-07 | COMP | 2021-03-15 | COMP | Rule 16 | 10 | 160 | 7 | 38 | 0 | 9 | 247
18746 | 2020-03-23 | 2020-04-05 | 2020-07-10 | 2020-07-10 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2021-02-22 | COMP | 2021-04-03 | COMP | Rule 16 | 10 | 69 | 51 | 1 | 104 | 30 | 261
18939 | 2020-03-23 | 2020-04-13 | 2020-07-27 | 2020-07-27 | COMP | 2022-02-18 | NOTN | 2022-10-05 | COMP | 2022-08-24 | COMP | 2022-12-18 | COMP | Other | 16 | 75 |  | 553 | 0 | 50 | 691
19077 | 2020-03-23 | 2020-04-20 | 2020-05-13 | 2020-05-13 | COMP | 2020-06-03 | COMP | 2020-07-27 | COMP | 2020-08-26 | COMP | 2020-09-30 | COMP | Rule 16 | 21 | 18 | 15 | 39 | 23 | 25 | 136
19079 | 2020-03-23 | 2020-04-20 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-23 | COMP | 2020-07-16 | COMP | Rule 15/16 | 21 | 25 | 5 | 1 | 17 | 18 | 83
19095 | 2020-03-23 | 2020-04-21 | 2020-07-09 | 2020-07-09 | COMP | 2020-09-28 | NOTN | 2020-09-28 | COMP | 2021-12-21 | COMP | 2022-01-27 | COMP | Other | 22 | 57 |  | 57 | 309 | 27 | 468
19133 | 2020-03-23 | 2020-04-22 | 2020-06-08 | 2020-06-08 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2021-05-05 | COMP | 2021-07-02 | COMP | Rule 16 | 23 | 33 | 12 | 1 | 219 | 42 | 325
19380 | 2020-03-23 | 2020-05-04 | 2020-07-23 | 2020-07-23 | COMP | 2020-10-21 | COMP | 2021-07-07 | COMP | 2021-08-03 | COMP | 2021-08-03 | COMP | Rule 16 | 31 | 58 | 64 | 177 | 20 | 1 | 346
19620 | 2020-03-23 | 2020-05-15 | 2020-09-10 | 2020-09-10 | COMP | 2021-04-14 | COMP | 2021-04-14 | COMP | 2021-05-11 | COMP | 2021-06-10 | COMP | Rule 16 | 40 | 83 | 148 | 1 | 20 | 22 | 309
19635 | 2020-03-23 | 2020-05-15 | 2020-08-14 | 2020-08-14 | COMP | 2020-10-15 | COMP | 2020-10-15 | COMP | 2022-01-31 | INPR | 2020-10-25 | COMP | Rule 16 | 40 | 65 | 44 | 1 |  |  | 153
19678 | 2020-03-23 | 2020-05-17 | 2020-06-25 | 2022-02-15 | COMP | 2020-12-10 | NOTN | 2022-08-11 | COMP | 2022-07-27 | COMP | 2022-09-16 | COMP | Rule 16 | 40 | 28 |  | 124 | 0 | 26 | 629
19772 | 2020-03-23 | 2020-05-21 | 2020-08-18 | 2020-08-18 | COMP | 2020-11-30 | COMP | 2021-01-05 | COMP | 2021-01-04 | COMP | 2022-04-18 | COMP | Rule 15/16 | 44 | 63 | 71 | 25 | 0 | 325 | 524
20148 | 2020-03-23 | 2020-06-08 | 2020-07-23 | 2020-07-23 | COMP | 2020-10-22 | COMP | 2020-10-28 | COMP | 2020-10-15 | COMP | 2020-11-25 | COMP | Rule 16 | 55 | 34 | 65 | 5 | 0 | 20 | 175
20500 | 2020-03-23 | 2020-06-23 | 2020-10-13 | 2020-10-13 | COMP | 2020-10-27 | COMP | 2021-12-17 | COMP | 2021-11-29 | COMP | 2022-01-12 | COMP | Rule 16 | 66 | 80 | 11 | 286 | 0 | 19 | 458
20585 | 2020-03-23 | 2020-06-27 | 2020-11-05 | 2020-11-05 | COMP | 2020-11-18 | COMP | 2021-05-13 | COMP | 2021-07-09 | COMP | 2021-07-12 | COMP | Rule 16 | 69 | 93 | 9 | 121 | 40 | 2 | 330
20635 | 2020-03-23 | 2020-06-30 | 2020-08-14 | 2020-08-14 | COMP | 2021-01-04 | COMP | 2021-01-04 | COMP | 2021-01-15 | COMP | 2021-03-08 | COMP | Rule 16 | 71 | 34 | 96 | 1 | 10 | 35 | 242
20751 | 2020-03-23 | 2020-07-03 | 2020-10-05 | 2021-02-04 | COMP | 2021-02-08 | COMP | 2021-02-09 | COMP | 2021-02-09 | COMP | 2021-02-18 | COMP | Rule 16 | 74 | 66 | 3 | 2 | 1 | 7 | 230
20933 | 2020-03-23 | 2020-07-13 | 2020-09-01 | 2020-09-01 | COMP | 2020-12-16 | COMP | 2021-03-18 | COMP | 2021-03-30 | COMP | 2021-04-12 | COMP | Rule 16 | 80 | 37 | 73 | 63 | 9 | 10 | 267
21181 | 2020-03-23 | 2020-07-24 | 2020-10-30 | 2020-10-30 | COMP | 2021-10-14 | COMP | 2021-10-14 | COMP | 2022-02-23 | COMP | 2022-03-22 | COMP | Rule 16 | 89 | 70 | 240 | 1 | 90 | 20 | 505
21622 | 2020-03-23 | 2020-08-17 | 2020-12-08 | 2020-12-08 | COMP | 2021-01-20 | COMP | 2021-06-14 | COMP | 2021-06-09 | COMP | 2021-07-09 | COMP | Rule 16 | 105 | 78 | 29 | 102 | 0 | 19 | 329
21911 | 2020-03-23 | 2020-09-01 | 2020-10-28 | 2020-11-06 | COMP | 2020-12-21 | COMP | 2020-12-21 | COMP | 2022-02-26 | INPR | 2021-02-17 | COMP | Rule 16 | 116 | 41 | 29 | 1 |  |  | 229
27706 | 2020-03-23 | 2021-05-06 | 2021-06-23 | 2021-06-23 | COMP | 2021-11-03 | COMP | 2021-11-23 | COMP | 2021-10-16 | COMP | 2021-12-15 | COMP | Rule 16 | 285 | 34 | 94 | 14 | 0 | 15 | 438
4290 | 2020-03-24 | 2020-04-07 | 2020-05-20 | 2020-05-20 | COMP | 2020-05-20 | NOTN | 2020-05-20 | COMP | 2020-05-21 | COMP | 2020-08-13 | COMP | Other | 11 | 32 |  | 1 | 2 | 60 | 102
18432 | 2020-03-24 | 2020-03-24 | 2020-03-26 | 2020-03-26 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-08-12 | COMP | 2020-09-22 | COMP | Rule 15/16 | 1 | 3 | 55 | 1 | 45 | 29 | 129
18472 | 2020-03-24 | 2020-03-25 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-03 | COMP | 2021-01-08 | COMP | 2020-12-14 | COMP | 2021-09-14 | COMP | Rule 16 | 2 | 57 | 16 | 130 | 0 | 173 | 374
18481 | 2020-03-24 | 2020-03-25 | 2020-07-31 | 2020-12-29 | COMP | 2020-11-03 | NOTN | 2021-04-15 | COMP | 2020-11-04 | COMP | 2021-05-24 | COMP | Other | 2 | 92 |  | 75 | 0 | 28 | 296
18509 | 2020-03-24 | 2020-03-28 | 2021-02-11 | 2021-02-11 | COMP | 2021-04-23 | COMP | 2021-04-23 | COMP | 2021-10-22 | COMP | 2021-10-30 | COMP | Rule 16 | 4 | 221 | 51 | 1 | 128 | 6 | 407
18527 | 2020-03-24 | 2020-03-28 | 2021-03-02 | 2022-04-19 | COMP | 2022-07-29 | COMP | 2022-10-07 | COMP | 2022-10-06 | COMP | 2022-12-07 | COMP | Rule 16 | 4 | 233 | 71 | 50 | 0 | 41 | 683
18553 | 2020-03-24 | 2020-03-28 | 2020-04-14 | 2020-04-14 | COMP | 2020-05-01 | COMP | 2020-08-05 | COMP | 2020-08-14 | COMP | 2020-09-21 | COMP | Rule 15/16 | 4 | 12 | 14 | 68 | 8 | 26 | 128
18554 | 2020-03-24 | 2020-03-28 | 2021-08-26 | 2021-08-26 | COMP | 2022-03-07 | COMP | 2022-06-15 | COMP | 2022-06-17 | COMP | 2022-07-28 | COMP | Rule 15/16 | 4 | 358 | 132 | 72 | 3 | 28 | 593
18556 | 2020-03-24 | 2020-03-28 | 2021-04-13 | 2021-04-13 | COMP | 2022-05-09 | COMP | 2022-05-09 | COMP | 2022-07-19 | COMP | 2022-07-29 | COMP | Rule 15/16 | 4 | 263 | 272 | 1 | 49 | 9 | 594
18578 | 2020-03-24 | 2020-03-30 | 2020-11-24 | 2020-11-24 | COMP | 2021-02-09 | COMP | 2021-02-16 | COMP |  | INPR | 2021-03-02 | COMP | Other | 5 | 169 | 51 | 5 |  |  | 237
18588 | 2020-03-24 | 2020-03-30 | 2020-10-01 | 2020-10-01 | COMP | 2020-11-09 | COMP | 2020-11-09 | COMP | 2022-02-15 | COMP | 2022-03-16 | COMP | Rule 15/16 | 5 | 132 | 28 | 1 | 318 | 21 | 500
18613 | 2020-03-24 | 2020-03-31 | 2020-05-07 | 2020-05-07 | COMP | 2020-05-28 | COMP | 2020-06-08 | COMP | 2020-06-27 | COMP | 2020-08-18 | COMP | Rule 16 | 6 | 28 | 15 | 8 | 15 | 37 | 105
18670 | 2020-03-24 | 2020-04-03 | 2020-07-18 | 2020-07-18 | COMP | 2020-07-24 | COMP | 2020-08-04 | COMP | 2020-09-29 | COMP | 2020-10-28 | COMP | Rule 16 | 9 | 75 | 5 | 8 | 40 | 22 | 155
18684 | 2020-03-24 | 2020-04-02 | 2020-05-21 | 2020-05-21 | COMP | 2020-12-29 | COMP | 2021-02-24 | COMP |  | INPR | 2021-02-24 | COMP | Other | 8 | 36 | 153 | 39 |  |  | 233
18685 | 2020-03-24 | 2020-04-02 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-10 | COMP | 2023-04-27 | COMP | 2023-02-07 | COMP | 2023-05-11 | COMP | Rule 16 | 8 | 82 | 11 | 682 | 0 | 11 | 790
18880 | 2020-03-24 | 2020-04-10 | 2020-05-26 | 2020-08-26 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-08-31 | COMP | 2020-09-30 | COMP | Rule 16 | 14 | 32 | 3 | 1 | 2 | 22 | 135
18921 | 2020-03-24 | 2020-04-13 | 2020-05-23 | 2020-10-06 | COMP | 2020-10-07 | NOTN | 2020-10-07 | COMP | 2021-05-24 | COMP | 2021-07-22 | COMP | Rule 15/16 | 15 | 30 |  | 2 | 157 | 42 | 337
18969 | 2020-03-24 | 2020-04-15 | 2021-02-02 | 2021-02-02 | COMP | 2021-08-03 | COMP | 2021-08-03 | COMP | 2021-10-26 | COMP | 2021-10-27 | COMP | Other | 17 | 202 | 128 | 1 | 60 | 2 | 405
19047 | 2020-03-24 | 2020-04-19 | 2020-07-28 | 2020-07-28 | COMP | 2020-08-20 | COMP | 2020-08-18 | COMP | 2020-10-01 | COMP | 2020-10-29 | COMP | Rule 16 | 19 | 71 | 18 |  | 32 | 21 | 156
19050 | 2020-03-24 | 2020-04-19 | 2020-08-17 | 2020-08-17 | COMP | 2021-10-25 | COMP | 2021-08-23 | INPR | 2021-08-23 | COMP | 2021-08-25 | COMP | Rule 16 | 19 | 85 | 300 |  |  |  | 361
19625 | 2020-03-24 | 2020-05-15 | 2020-09-23 | 2020-09-23 | COMP | 2020-10-14 | COMP | 2020-11-03 | COMP | 2021-05-24 | COMP | 2021-07-02 | COMP | Rule 16 | 39 | 92 | 16 | 15 | 138 | 29 | 324
19662 | 2020-03-24 | 2020-05-17 | 2020-07-02 | 2020-07-02 | COMP | 2021-06-16 | COMP | 2021-06-16 | COMP | 2021-12-10 | COMP | 2022-01-03 | COMP | Rule 16 | 39 | 33 | 241 | 1 | 123 | 17 | 450
19793 | 2020-03-24 | 2020-05-21 | 2020-08-07 | 2021-02-02 | COMP | 2021-02-10 | COMP | 2021-08-25 | COMP | 2021-08-19 | COMP | 2021-09-02 | COMP | Rule 16 | 43 | 56 | 7 | 138 | 0 | 7 | 367
19810 | 2020-03-24 | 2020-05-22 | 2021-09-13 | 2021-09-13 | COMP | 2021-11-24 | COMP | 2023-12-04 | CANC | 2023-12-04 | CANC | 2022-07-26 | COMP | Other | 44 | 330 | 52 |  |  |  | 591
19818 | 2020-03-24 | 2020-05-23 | 2020-06-20 | 2020-06-20 | COMP | 2020-07-30 | COMP | 2020-07-30 | COMP | 2020-09-08 | COMP | 2020-10-06 | COMP | Rule 16 | 44 | 19 | 29 | 1 | 28 | 21 | 139
19833 | 2020-03-24 | 2020-05-26 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2021-05-04 | COMP | 2021-05-10 | COMP | Rule 16 | 45 | 35 | 18 | 1 | 187 | 5 | 286
19883 | 2020-03-24 | 2020-05-27 | 2020-07-07 | 2020-07-07 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-07-21 | COMP | 2020-09-04 | COMP | Rule 16 | 46 | 30 | 20 | 1 | 0 | 25 | 118
19924 | 2020-03-24 | 2020-05-28 | 2020-06-19 | 2020-06-19 | COMP | 2020-06-24 | COMP | 2020-07-17 | COMP | 2020-07-17 | COMP | 2020-07-27 | COMP | Rule 16 | 47 | 17 | 4 | 18 | 1 | 7 | 89
20032 | 2020-03-24 | 2020-06-01 | 2020-09-18 | 2020-09-18 | COMP | 2020-11-03 | COMP | 2021-06-14 | COMP | 2021-05-26 | COMP | 2021-06-14 | COMP | Rule 16 | 49 | 79 | 33 | 152 | 0 | 1 | 310
20067 | 2020-03-24 | 2020-06-03 | 2020-07-17 | 2020-07-17 | COMP | 2020-08-31 | COMP | 2020-09-14 | COMP | 2020-09-01 | COMP | 2020-10-09 | COMP | Rule 16 | 51 | 33 | 32 | 10 | 0 | 20 | 142
20249 | 2020-03-24 | 2020-06-13 | 2020-07-16 | 2020-07-16 | COMP | 2020-11-19 | COMP | 2020-09-25 | COMP | 2022-01-31 | INPR | 2020-11-09 | COMP | Rule 16 | 58 | 24 | 89 |  |  |  | 163
20749 | 2020-03-24 | 2020-07-03 | 2020-09-17 | 2020-09-17 | COMP | 2020-10-12 | COMP | 2020-11-04 | COMP | 2020-12-09 | COMP | 2020-12-11 | COMP | Rule 16 | 73 | 54 | 18 | 18 | 23 | 3 | 184
21160 | 2020-03-24 | 2020-07-23 | 2021-03-19 | 2021-03-19 | COMP | 2021-03-26 | COMP | 2021-12-23 | COMP | 2021-12-23 | COMP | 2021-12-30 | COMP | Rule 16 | 87 | 164 | 6 | 189 | 1 | 6 | 448
21292 | 2020-03-24 | 2020-07-30 | 2020-11-12 | 2020-11-12 | COMP | 2021-02-18 | COMP | 2021-02-18 | COMP | 2021-08-03 | COMP | 2021-10-21 | COMP | Other | 92 | 74 | 65 | 1 | 117 | 57 | 401
21541 | 2020-03-24 | 2020-08-12 | 2020-10-22 | 2020-10-22 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2021-02-11 | COMP | 2021-03-19 | COMP | Rule 16 | 101 | 51 | 3 | 1 | 73 | 26 | 250
21623 | 2020-03-24 | 2020-08-17 | 2020-11-05 | 2020-11-05 | COMP | 2020-11-30 | COMP | 2020-12-30 | COMP | 2020-12-23 | COMP | 2021-02-26 | COMP | Rule 15/16 | 104 | 58 | 15 | 22 | 0 | 40 | 235
30565 | 2020-03-24 | 2021-09-03 | 2021-10-05 | 2021-10-05 | COMP | 2021-11-01 | COMP | 2021-11-04 | COMP | 2021-10-29 | COMP | 2021-12-06 | COMP | Rule 16 | 368 | 22 | 20 | 4 | 0 | 20 | 430
18475 | 2020-03-25 | 2020-03-25 | 2020-06-29 | 2020-06-29 | COMP | 2020-12-29 | NOTN | 2020-12-29 | COMP | 2022-06-13 | COMP | 2022-10-07 | COMP | Other | 1 | 68 |  | 127 | 368 | 82 | 642
18510 | 2020-03-25 | 2020-03-27 | 2020-04-15 | 2020-04-15 | COMP | 2020-04-20 | COMP | 2020-04-29 | COMP | 2022-07-30 | INPR | 2020-05-12 | COMP | Rule 16 | 3 | 14 | 4 | 8 |  |  | 35
18572 | 2020-03-25 | 2020-03-28 | 2020-06-03 | 2020-06-03 | COMP | 2020-12-11 | COMP | 2020-12-11 | COMP | 2021-08-04 | COMP | 2021-10-11 | COMP | Rule 16 | 3 | 47 | 134 | 1 | 163 | 48 | 392
18605 | 2020-03-25 | 2020-03-31 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-27 | COMP | 2020-05-27 | COMP | 2020-10-08 | COMP | 2020-11-02 | COMP | Rule 16 | 5 | 34 | 8 | 1 | 96 | 18 | 157
18615 | 2020-03-25 | 2020-03-31 | 2021-01-25 | 2021-02-24 | COMP | 2021-04-06 | COMP | 2021-04-06 | COMP | 2023-01-09 | COMP | 2023-04-12 | COMP | Rule 15/16 | 5 | 207 | 30 | 1 | 443 | 66 | 768
18619 | 2020-03-25 | 2020-03-31 | 2020-10-13 | 2020-10-13 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2021-02-12 | COMP | 2021-02-24 | COMP | Rule 16 | 5 | 139 | 13 | 1 | 71 | 8 | 232
18706 | 2020-03-25 | 2020-04-03 | 2021-01-07 | 2022-02-17 | COMP | 2022-03-02 | COMP | 2021-03-09 | COMP | 2022-06-28 | COMP | 2022-10-14 | COMP | Rule 16 | 8 | 193 | 9 |  | 331 | 77 | 647
18748 | 2020-03-25 | 2020-04-07 | 2021-03-30 | 2021-03-30 | COMP | 2021-04-12 | COMP | 2021-08-31 | COMP | 2021-09-02 | COMP | 2021-10-11 | COMP | Rule 15/16 | 10 | 247 | 10 | 100 | 3 | 27 | 392
18809 | 2020-03-25 | 2020-04-07 | 2020-05-06 | 2020-05-06 | COMP | 2020-06-12 | COMP | 2020-06-12 | COMP | 2022-01-30 | INPR | 2020-08-31 | COMP | Rule 16 | 10 | 22 | 27 | 1 |  |  | 113
18893 | 2020-03-25 | 2020-04-10 | 2020-10-04 | 2020-10-04 | COMP | 2020-10-13 | COMP | 2020-12-11 | COMP | 2020-11-24 | COMP | 2021-01-12 | COMP | Rule 15/16 | 13 | 124 | 7 | 41 | 0 | 21 | 203
18915 | 2020-03-25 | 2020-04-12 | 2020-07-20 | 2021-02-25 | COMP | 2021-03-12 | COMP | 2020-10-19 | COMP | 2020-11-24 | COMP | 2020-12-29 | COMP | Rule 16 | 13 | 70 | 12 |  | 26 | 23 | 194
18959 | 2020-03-25 | 2020-04-15 | 2020-05-02 | 2020-05-02 | COMP | 2021-02-17 | COMP | 2021-02-23 | COMP | 2021-02-23 | COMP | 2021-02-22 | COMP | Rule 16 | 16 | 13 | 199 | 5 | 1 |  | 230
18983 | 2020-03-25 | 2020-04-16 | 2021-06-28 | 2021-06-28 | COMP | 2021-10-11 | COMP | 2022-02-14 | COMP | 2022-04-26 | COMP | 2022-03-25 | COMP | Rule 16 | 17 | 303 | 74 | 87 | 51 |  | 506
19175 | 2020-03-25 | 2020-04-23 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-10-12 | COMP | 2020-11-16 | COMP | Rule 16 | 22 | 39 | 13 | 1 | 71 | 25 | 166
19215 | 2020-03-25 | 2020-04-24 | 2020-07-29 | 2020-07-29 | COMP | 2021-03-10 | COMP | 2021-03-10 | COMP | 2021-03-10 | COMP | 2021-11-03 | COMP | Other | 23 | 68 | 153 | 1 | 1 | 168 | 409
19344 | 2020-03-25 | 2020-05-01 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-03 | COMP | 2020-07-03 | COMP | 2020-10-06 | COMP | 2020-12-16 | COMP | Rule 16 | 28 | 30 | 16 | 1 | 67 | 49 | 186
19448 | 2020-03-25 | 2020-05-07 | 2020-07-17 | 2020-07-27 | COMP | 2020-08-25 | COMP | 2021-06-28 | COMP | 2021-06-21 | COMP | 2022-01-21 | COMP | Rule 15/16 | 32 | 51 | 22 | 211 | 0 | 144 | 462
19475 | 2020-03-25 | 2020-05-08 | 2020-06-15 | 2020-06-15 | COMP | 2020-07-13 | COMP | 2020-08-25 | COMP | 2020-08-28 | COMP | 2020-10-16 | COMP | Rule 16 | 33 | 26 | 21 | 32 | 4 | 35 | 146
19554 | 2020-03-25 | 2020-05-12 | 2020-10-15 | 2020-10-15 | COMP | 2021-07-29 | COMP | 2021-07-29 | COMP | 2021-08-05 | COMP | 2021-12-02 | COMP | Rule 16 | 35 | 111 | 197 | 1 | 6 | 82 | 427
19577 | 2020-03-25 | 2020-05-13 | 2020-06-12 | 2020-06-12 | COMP | 2020-07-15 | COMP | 2020-08-10 | COMP | 2021-11-10 | COMP | 2021-11-30 | COMP | Rule 16 | 36 | 22 | 24 | 19 | 317 | 12 | 425
19656 | 2020-03-25 | 2020-05-16 | 2020-10-03 | 2020-12-07 | COMP | 2020-12-22 | COMP | 2020-12-31 | COMP | 2020-12-28 | COMP | 2021-02-05 | COMP | Rule 16 | 38 | 98 | 12 | 7 | 0 | 25 | 220
20197 | 2020-03-25 | 2020-06-09 | 2020-07-10 | 2020-07-10 | COMP | 2020-08-05 | COMP | 2020-08-05 | COMP | 2020-08-11 | COMP | 2020-08-23 | COMP | Rule 16 | 54 | 24 | 19 | 1 | 5 | 9 | 107
20536 | 2020-03-25 | 2020-06-25 | 2020-12-04 | 2020-12-04 | COMP | 2021-12-13 | COMP | 2021-12-13 | COMP | 2022-07-01 | COMP | 2022-07-31 | COMP | Rule 16 | 66 | 113 | 257 | 1 | 141 | 20 | 593
20660 | 2020-03-25 | 2020-07-01 | 2020-08-21 | 2020-08-21 | COMP | 2020-11-20 | COMP | 2020-11-20 | COMP | 2020-12-07 | COMP | 2020-12-23 | COMP | Rule 16 | 70 | 38 | 64 | 1 | 10 | 13 | 191
20662 | 2020-03-25 | 2020-07-01 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-13 | COMP | 2020-09-03 | COMP | 2022-01-31 | INPR | 2020-10-19 | COMP | Rule 16 | 70 | 29 | 4 | 16 |  |  | 147
20710 | 2020-03-25 | 2020-07-02 | 2020-08-25 | 2020-08-25 | COMP | 2020-09-08 | COMP | 2020-09-08 | COMP | 2020-09-09 | COMP | 2020-09-30 | COMP | Rule 16 | 71 | 39 | 10 | 1 | 2 | 16 | 134
20801 | 2020-03-25 | 2020-07-07 | 2020-09-29 | 2020-09-29 | COMP | 2020-11-04 | COMP | 2020-11-04 | COMP | 2020-12-01 | COMP | 2021-01-12 | COMP | Other | 74 | 60 | 27 | 1 | 17 | 29 | 203
21183 | 2020-03-25 | 2020-07-25 | 2020-10-21 | 2020-10-21 | COMP | 2020-12-29 | COMP | 2020-12-10 | COMP | 2021-05-25 | COMP | 2021-06-04 | COMP | Rule 16 | 87 | 62 | 46 |  | 115 | 8 | 303
21869 | 2020-03-25 | 2020-09-01 | 2020-12-01 | 2020-12-01 | COMP | 2021-01-13 | COMP | 2021-01-19 | COMP | 2021-07-06 | COMP | 2021-08-28 | COMP | Rule 15/16 | 114 | 62 | 30 | 4 | 118 | 39 | 362
22387 | 2020-03-25 | 2020-09-22 | 2021-02-23 | 2021-02-23 | COMP | 2021-06-09 | COMP | 2022-05-13 | COMP |  | INPR | 2023-04-18 | COMP | Rule 16 | 128 | 104 | 76 | 236 |  |  | 772
22979 | 2020-03-25 | 2020-10-19 | 2021-01-06 | 2021-01-06 | COMP | 2021-02-03 | COMP | 2021-12-27 | COMP | 2022-04-12 | COMP | 2023-07-13 | COMP | Rule 16 | 147 | 53 | 20 | 227 | 75 | 314 | 831
23253 | 2020-03-25 | 2020-10-29 | 2021-01-22 | 2021-01-22 | COMP | 2021-04-12 | COMP | 2021-04-12 | COMP | 2021-06-02 | COMP | 2021-07-15 | COMP | Rule 16 | 155 | 56 | 56 | 1 | 37 | 31 | 331
18567 | 2020-03-26 | 2020-03-28 | 2021-04-23 | 2022-01-11 | COMP | 2022-01-21 | COMP | 2022-10-17 | COMP | 2022-10-31 | COMP | 2023-06-29 | COMP | Rule 16 | 2 | 271 | 8 | 187 | 11 | 165 | 821
18577 | 2020-03-26 | 2020-03-30 | 2020-06-24 | 2020-06-24 | COMP | 2020-10-30 | COMP | 2020-10-30 | COMP |  | INPR | 2023-06-12 | COMP | Rule 16 | 3 | 62 | 92 | 1 |  |  | 809
18678 | 2020-03-26 | 2020-04-03 | 2020-04-27 | 2020-04-27 | COMP | 2020-05-15 | COMP | 2020-05-15 | COMP | 2020-05-18 | COMP | 2020-06-13 | COMP | Rule 16 | 7 | 17 | 15 | 1 | 2 | 19 | 56
18770 | 2020-03-26 | 2020-04-06 | 2020-05-08 | 2020-05-08 | COMP | 2020-04-06 | NOTN | 2020-07-09 | COMP | 2021-11-04 | COMP | 2022-02-26 | COMP | Rule 16 | 8 | 25 |  | 44 | 335 | 77 | 485
18862 | 2020-03-26 | 2020-04-09 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-22 | COMP | 2020-07-16 | COMP | 2021-10-11 | COMP | 2021-11-22 | COMP | Rule 16 | 11 | 27 | 6 | 39 | 312 | 30 | 420
19011 | 2020-03-26 | 2020-04-16 | 2020-06-04 | 2020-07-21 | COMP | 2020-07-24 | COMP | 2020-08-11 | COMP | 2020-07-23 | COMP | 2020-09-22 | COMP | Rule 16 | 16 | 35 | 4 | 13 | 0 | 30 | 127
19173 | 2020-03-26 | 2020-04-22 | 2020-07-13 | 2020-10-01 | COMP | 2020-11-02 | COMP | 2020-11-02 | COMP | 2021-02-24 | COMP | 2021-04-05 | COMP | Rule 16 | 20 | 58 | 23 | 1 | 76 | 29 | 259
19214 | 2020-03-26 | 2020-04-24 | 2020-08-05 | 2020-08-05 | COMP | 2020-08-31 | COMP | 2020-10-21 | COMP | 2020-09-03 | COMP | 2021-01-05 | COMP | Rule 16 | 22 | 73 | 19 | 37 | 0 | 50 | 197
19257 | 2020-03-26 | 2020-04-28 | 2020-09-21 | 2020-09-21 | COMP | 2021-06-10 | COMP | 2021-06-11 | COMP | 2021-10-26 | COMP | 2021-11-15 | COMP | Rule 15/16 | 24 | 103 | 181 | 2 | 96 | 14 | 415
19258 | 2020-03-26 | 2020-04-28 | 2020-09-10 | 2020-09-11 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2021-10-26 | COMP | 2021-11-11 | COMP | Rule 16 | 24 | 96 | 9 | 1 | 275 | 12 | 413
19310 | 2020-03-26 | 2020-04-30 | 2020-08-04 | 2020-10-08 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2020-10-23 | COMP | 2020-11-16 | COMP | Rule 15/16 | 26 | 68 | 9 | 1 | 4 | 16 | 165
19319 | 2020-03-26 | 2020-04-30 | 2020-07-07 | 2020-07-07 | COMP | 2020-08-06 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-09-23 | COMP | Rule 15/16 | 26 | 48 | 23 |  | 1 | 41 | 128
19364 | 2020-03-26 | 2020-05-04 | 2021-02-24 | 2021-02-24 | COMP | 2021-04-05 | COMP | 2021-07-28 | COMP | 2021-07-30 | COMP | 2021-11-04 | COMP | Rule 15/16 | 28 | 204 | 29 | 81 | 3 | 69 | 409
19417 | 2020-03-26 | 2020-05-06 | 2020-09-04 | 2020-09-04 | COMP | 2020-09-23 | COMP | 2020-09-28 | COMP | 2020-09-01 | COMP | 2020-11-06 | COMP | Rule 16 | 30 | 87 | 13 | 4 | 0 | 30 | 160
19453 | 2020-03-26 | 2020-05-07 | 2020-06-11 | 2020-06-11 | COMP | 2020-06-10 | NOTN | 2020-06-11 | COMP | 2021-01-19 | COMP | 2021-03-13 | COMP | Rule 16 | 31 | 25 |  | 1 | 152 | 38 | 243
19589 | 2020-03-26 | 2020-05-14 | 2020-09-21 | 2021-08-30 | COMP | 2021-09-22 | COMP | 2021-04-08 | COMP | 2021-11-15 | COMP | 2022-02-08 | COMP | Rule 15/16 | 36 | 91 | 17 |  | 154 | 59 | 473
19677 | 2020-03-26 | 2020-05-17 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-09 | COMP | 2020-08-04 | COMP | 2020-08-21 | COMP | 2020-09-11 | COMP | Rule 16 | 37 | 32 | 7 | 19 | 14 | 15 | 120
19830 | 2020-03-26 | 2020-05-26 | 2020-09-03 | 2020-09-03 | COMP | 2020-10-05 | COMP | 2020-10-05 | COMP | 2020-10-12 | COMP | 2020-12-11 | COMP | Rule 16 | 43 | 73 | 22 | 1 | 6 | 42 | 182
19977 | 2020-03-26 | 2020-06-01 | 2020-07-12 | 2020-07-12 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2021-10-23 | INPR | 2020-09-18 | COMP | Rule 16 | 47 | 30 | 10 | 1 |  |  | 125
20302 | 2020-03-26 | 2020-06-15 | 2020-08-07 | 2020-08-07 | COMP | 2020-09-24 | COMP | 2020-10-12 | COMP | 2020-09-28 | COMP | 2020-10-20 | COMP | Rule 16 | 57 | 40 | 34 | 13 | 0 | 7 | 147
20452 | 2020-03-26 | 2020-06-20 | 2020-09-09 | 2021-02-19 | COMP | 2021-03-22 | COMP | 2021-04-28 | COMP | 2021-05-04 | COMP | 2021-06-04 | COMP | Rule 16 | 61 | 57 | 22 | 28 | 5 | 23 | 302
20599 | 2020-03-26 | 2020-06-29 | 2020-07-09 | 2020-07-09 | COMP | 2020-07-14 | COMP | 2020-07-14 | COMP | 2020-08-14 | COMP | 2020-09-15 | COMP | Rule 16 | 67 | 9 | 4 | 1 | 24 | 22 | 122
20671 | 2020-03-26 | 2020-07-01 | 2020-08-18 | 2020-08-26 | COMP | 2020-09-04 | COMP | 2020-10-01 | COMP | 2020-10-15 | COMP | 2021-02-24 | COMP | Rule 16 | 69 | 35 | 8 | 19 | 11 | 88 | 231
20832 | 2020-03-26 | 2020-07-08 | 2020-09-28 | 2020-09-28 | COMP | 2020-10-05 | COMP | 2020-12-17 | COMP | 2021-03-30 | COMP | 2021-04-30 | COMP | Rule 16 | 74 | 58 | 6 | 51 | 70 | 24 | 278
20989 | 2020-03-26 | 2020-07-16 | 2021-05-13 | 2021-05-13 | COMP | 2021-05-18 | COMP | 2023-12-04 | CANC | 2022-04-07 | COMP | 2022-04-06 | COMP | Rule 16 | 80 | 208 | 4 |  |  |  | 513
21124 | 2020-03-26 | 2020-07-23 | 2020-08-24 | 2020-08-24 | COMP | 2021-04-08 | COMP | 2021-04-08 | COMP | 2021-05-28 | COMP | 2021-07-12 | COMP | Rule 16 | 85 | 23 | 156 | 1 | 37 | 30 | 327
21933 | 2020-03-26 | 2020-09-02 | 2020-11-23 | 2020-11-23 | COMP | 2020-12-16 | COMP | 2021-03-29 | COMP | 2021-09-27 | COMP | 2021-10-16 | COMP | Rule 16 | 114 | 57 | 16 | 70 | 128 | 15 | 395
22524 | 2020-03-26 | 2020-09-28 | 2020-12-14 | 2020-12-14 | COMP | 2020-12-30 | COMP | 2020-12-31 | COMP | 2021-03-22 | COMP | 2021-04-24 | COMP | Rule 16 | 131 | 53 | 12 | 2 | 55 | 25 | 273
22586 | 2020-03-26 | 2020-10-01 | 2021-01-30 | 2021-01-30 | COMP | 2021-09-10 | COMP | 2022-06-21 | COMP | 2022-12-22 | COMP | 2023-05-04 | COMP | Rule 16 | 134 | 81 | 156 | 196 | 128 | 92 | 783
24857 | 2020-03-26 | 2021-01-14 | 2021-03-08 | 2021-03-08 | COMP | 2021-06-23 | COMP | 2022-04-05 | COMP | 2022-04-12 | COMP | 2022-05-20 | COMP | Rule 15/16 | 204 | 36 | 77 | 198 | 6 | 29 | 545
26136 | 2020-03-26 | 2021-03-10 | 2021-09-24 | 2021-09-24 | COMP | 2021-10-13 | COMP | 2022-04-18 | COMP | 2022-03-31 | COMP | 2022-05-05 | COMP | Rule 15/16 | 241 | 140 | 14 | 129 | 0 | 14 | 534
18569 | 2020-03-27 | 2020-03-30 | 2020-04-29 | 2020-04-29 | COMP | 2020-10-14 | COMP | 2020-10-14 | COMP | 2021-03-29 | COMP | 2021-05-18 | COMP | Rule 15/16 | 2 | 23 | 119 | 1 | 112 | 37 | 289
18668 | 2020-03-27 | 2020-04-02 | 2020-11-05 | 2020-11-05 | COMP | 2021-01-08 | COMP | 2022-03-24 | COMP | 2022-03-08 | COMP | 2022-05-12 | COMP | Rule 16 | 5 | 154 | 42 | 305 | 0 | 36 | 538
19017 | 2020-03-27 | 2020-04-17 | 2020-12-16 | 2020-12-16 | COMP | 2021-02-10 | COMP | 2021-02-10 | COMP | 2021-03-02 | COMP | 2021-05-21 | COMP | Rule 16 | 16 | 169 | 38 | 1 | 14 | 59 | 292
19080 | 2020-03-27 | 2020-04-20 | 2020-08-15 | 2020-08-15 | COMP | 2020-09-17 | COMP | 2021-05-26 | COMP | 2021-05-17 | COMP | 2021-07-29 | COMP | Rule 16 | 17 | 84 | 23 | 173 | 0 | 45 | 339
19264 | 2020-03-27 | 2020-04-28 | 2020-10-13 | 2020-10-13 | COMP | 2020-10-20 | COMP | 2020-11-03 | COMP | 2020-11-02 | COMP | 2021-01-12 | COMP | Rule 16 | 23 | 119 | 6 | 11 | 0 | 46 | 201
19451 | 2020-03-27 | 2020-05-08 | 2020-08-17 | 2020-08-17 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2021-01-14 | COMP | 2021-03-17 | COMP | Rule 16 | 31 | 71 | 27 | 1 | 77 | 43 | 245
19517 | 2020-03-27 | 2020-05-11 | 2020-07-17 | 2020-07-17 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2020-09-23 | COMP | Rule 16 | 32 | 49 | 12 | 1 | 1 | 37 | 127
19763 | 2020-03-27 | 2020-05-21 | 2020-07-02 | 2020-07-02 | COMP | 2020-07-16 | COMP | 2020-08-10 | COMP | 2020-07-16 | COMP | 2020-09-03 | COMP | Rule 16 | 40 | 30 | 11 | 18 | 0 | 19 | 114
20018 | 2020-03-27 | 2020-06-02 | 2020-07-28 | 2021-09-16 | COMP | 2022-01-10 | COMP | 2022-06-30 | COMP | 2022-06-29 | COMP | 2022-08-28 | COMP | Rule 16 | 47 | 41 | 80 | 120 | 0 | 41 | 611
20026 | 2020-03-27 | 2020-06-01 | 2020-06-19 | 2020-07-27 | COMP | 2020-08-05 | COMP | 2020-09-10 | COMP | 2020-09-15 | COMP | 2020-09-28 | COMP | Rule 16 | 46 | 15 | 8 | 26 | 4 | 10 | 130
20519 | 2020-03-27 | 2020-06-24 | 2020-08-14 | 2020-08-14 | COMP | 2020-10-15 | COMP | 2020-12-03 | COMP |  | INPR | 2021-01-12 | COMP | Rule 16 | 63 | 38 | 44 | 33 |  |  | 201
20520 | 2020-03-27 | 2020-06-24 | 2020-08-14 | 2020-08-26 | COMP | 2020-10-13 | COMP | 2020-10-28 | COMP | 2023-05-27 | INPR | 2021-10-08 | COMP | Rule 16 | 63 | 38 | 34 | 12 |  |  | 389
20893 | 2020-03-27 | 2020-07-13 | 2021-01-26 | 2021-07-06 | COMP | 2021-08-27 | COMP | 2022-03-28 | COMP | 2023-01-26 | COMP | 2023-04-06 | COMP | Rule 15/16 | 76 | 135 | 39 | 146 | 209 | 50 | 762
21093 | 2020-03-27 | 2020-07-22 | 2020-09-28 | 2020-10-20 | COMP | 2020-11-04 | COMP | 2020-11-10 | COMP | 2022-02-26 | INPR | 2021-02-09 | COMP | Rule 16 | 83 | 48 | 12 | 5 |  |  | 220
21146 | 2020-03-27 | 2020-07-23 | 2020-11-05 | 2020-12-01 | COMP | 2021-02-04 | COMP | 2021-03-22 | COMP | 2021-04-21 | COMP | 2021-05-10 | COMP | Rule 16 | 84 | 75 | 45 | 32 | 23 | 14 | 283
21364 | 2020-03-27 | 2020-08-04 | 2020-11-03 | 2020-11-03 | COMP | 2021-01-07 | COMP | 2021-01-07 | COMP |  |  | 2021-06-11 | COMP | Rule 16 | 92 | 65 | 43 | 1 |  |  | 306
21787 | 2020-03-27 | 2020-08-26 | 2020-12-11 | 2021-12-15 | COMP | 2022-01-03 | COMP | 2022-01-25 | COMP | 2022-03-07 | COMP | 2022-04-07 | COMP | Rule 16 | 108 | 74 | 14 | 16 | 29 | 24 | 513
22396 | 2020-03-27 | 2020-09-23 | 2020-12-30 | 2020-12-30 | COMP | 2021-03-09 | COMP | 2021-03-12 | COMP | 2021-05-25 | COMP | 2021-06-28 | COMP | Rule 15/16 | 127 | 67 | 47 | 4 | 53 | 24 | 317
18659 | 2020-03-29 | 2020-04-02 | 2020-04-23 | 2020-04-23 | COMP | 2020-04-29 | COMP | 2020-06-11 | NOTN | 2020-06-11 | COMP | 2020-06-26 | COMP | Rule 16 | 4 | 16 | 5 |  |  |  | 64
18828 | 2020-03-29 | 2020-04-08 | 2020-08-06 | 2020-08-06 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2023-11-13 | INPR | 2021-03-26 | COMP | Rule 16 | 8 | 86 | 59 | 1 |  |  | 251
20344 | 2020-03-29 | 2020-06-16 | 2020-07-27 | 2020-08-21 | COMP | 2020-08-26 | COMP | 2020-09-21 | COMP | 2023-11-13 | INPR | 2020-10-14 | COMP | Rule 16 | 56 | 30 | 4 | 18 |  |  | 141
18795 | 2020-03-30 | 2020-04-07 | 2020-05-05 | 2020-05-05 | COMP | 2020-06-09 | COMP | 2020-06-09 | COMP | 2020-07-30 | COMP | 2020-09-01 | COMP | Rule 16 | 7 | 21 | 25 | 1 | 38 | 24 | 111
18808 | 2020-03-30 | 2020-04-08 | 2020-07-03 | 2020-07-03 | COMP | 2020-07-03 | NOTN | 2020-09-17 | COMP | 2020-08-18 | COMP | 2020-12-03 | COMP | Other | 8 | 62 |  | 54 | 0 | 53 | 174
18928 | 2020-03-30 | 2020-04-13 | 2020-08-07 | 2020-08-07 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | 2021-05-13 | COMP | 2021-06-23 | COMP | Rule 15/16 | 11 | 84 | 111 | 1 | 82 | 29 | 313
19044 | 2020-03-30 | 2020-04-19 | 2020-11-17 | 2020-11-17 | COMP | 2020-12-07 | COMP | 2021-04-07 | COMP | 2021-06-12 | COMP | 2021-07-22 | COMP | Rule 16 | 15 | 149 | 13 | 84 | 47 | 28 | 333
19182 | 2020-03-30 | 2020-04-23 | 2020-05-15 | 2020-05-15 | COMP | 2020-05-22 | COMP | 2020-05-22 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | Rule 16 | 19 | 17 | 6 | 1 | 82 | 1 | 121
19294 | 2020-03-30 | 2020-04-28 | 2020-05-29 | 2020-05-29 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-09-15 | COMP | 2020-09-22 | COMP | Rule 16 | 22 | 23 | 54 | 1 | 24 | 6 | 125
19341 | 2020-03-30 | 2020-05-01 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-23 | COMP | 2020-06-23 | COMP | 2020-07-14 | COMP | 2020-08-04 | COMP | Rule 16 | 25 | 22 | 16 | 1 | 16 | 16 | 91
19811 | 2020-03-30 | 2020-05-22 | 2020-10-07 | 2020-10-07 | COMP | 2020-10-20 | COMP | 2021-06-16 | COMP | 2021-05-11 | COMP | 2021-06-18 | COMP | Rule 16 | 40 | 97 | 10 | 164 | 0 | 3 | 310
19990 | 2020-03-30 | 2020-06-01 | 2020-07-28 | 2020-07-28 | COMP | 2021-01-22 | COMP | 2021-01-22 | COMP | 2021-02-08 | COMP | 2021-03-25 | COMP | Rule 16 | 45 | 42 | 122 | 1 | 12 | 33 | 250
20053 | 2020-03-30 | 2020-06-02 | 2020-06-29 | 2020-06-29 | COMP | 2022-01-25 | COMP | 2022-01-26 | COMP | 2022-01-26 | COMP | 2022-02-09 | COMP | Rule 16 | 46 | 20 | 397 | 2 | 1 | 11 | 472
20396 | 2020-03-30 | 2020-06-17 | 2020-10-22 | 2020-10-22 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP | 2020-12-28 | COMP | 2021-01-14 | COMP | Rule 16 | 57 | 91 | 22 | 1 | 23 | 13 | 202
20602 | 2020-03-30 | 2020-06-29 | 2020-11-18 | 2020-11-18 | COMP | 2021-04-01 | COMP | 2021-11-18 | COMP | 2021-11-15 | COMP | 2023-10-11 | COMP | Rule 16 | 65 | 101 | 91 | 162 | 0 | 476 | 891
20855 | 2020-03-30 | 2020-07-09 | 2020-10-21 | 2020-10-21 | COMP | 2020-11-02 | COMP | 2020-11-05 | COMP | 2020-11-17 | COMP | 2020-12-12 | COMP | Rule 16 | 73 | 74 | 9 | 4 | 8 | 17 | 180
4291 | 2020-03-31 | 2020-04-08 | 2020-05-13 | 2020-05-13 | COMP | 2020-05-29 | NOTN | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-22 | COMP | Other | 7 | 26 |  | 13 | 1 | 16 | 59
4308 | 2020-03-31 | 2020-07-18 | 2020-10-09 | 2020-10-09 | COMP | 2020-10-14 | NOTN | 2020-10-28 | COMP | 2023-07-29 | INPR | 2021-07-31 | COMP | Other | 78 | 59 |  | 14 |  |  | 338
18632 | 2020-03-31 | 2020-04-01 | 2020-06-02 | 2020-06-02 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2020-11-16 | COMP | 2021-01-12 | COMP | Rule 16 | 2 | 44 | 59 | 1 | 60 | 38 | 199
18661 | 2020-03-31 | 2020-04-01 | 2020-05-23 | 2020-05-23 | COMP | 2020-06-17 | COMP | 2020-10-30 | COMP | 2020-11-18 | COMP | 2020-11-19 | COMP | Rule 16 | 2 | 38 | 17 | 97 | 13 | 2 | 165
18791 | 2020-03-31 | 2020-04-07 | 2020-05-06 | 2020-05-06 | COMP | 2020-07-27 | COMP | 2020-08-18 | COMP | 2020-11-05 | COMP | 2020-12-03 | COMP | Rule 16 | 6 | 22 | 58 | 17 | 57 | 18 | 173
18852 | 2020-03-31 | 2020-04-10 | 2020-10-26 | 2020-10-26 | COMP | 2021-01-19 | COMP | 2021-01-19 | COMP | 2021-02-16 | COMP | 2021-04-13 | COMP | Rule 16 | 9 | 140 | 56 | 1 | 20 | 41 | 262
18941 | 2020-03-31 | 2020-04-14 | 2020-12-22 | 2021-02-18 | COMP | 2021-03-11 | COMP | 2021-03-11 | COMP |  | INPR | 2021-05-23 | COMP | Rule 15/16 | 11 | 176 | 16 | 1 |  |  | 290
19226 | 2020-03-31 | 2020-04-27 | 2022-02-17 | 2023-01-09 | COMP | 2023-05-10 | COMP | 2023-05-12 | COMP | 2023-01-11 | COMP | 2023-06-23 | COMP | Rule 16 | 20 | 458 | 86 | 3 | 0 | 29 | 814
19247 | 2020-03-31 | 2020-04-28 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-06 | COMP | 2020-07-06 | COMP | 2020-10-06 | COMP | 2020-11-03 | COMP | Rule 16 | 21 | 44 | 6 | 1 | 66 | 21 | 154
19349 | 2020-03-31 | 2020-05-02 | 2020-09-15 | 2021-02-23 | COMP | 2021-03-19 | COMP | 2021-03-22 | COMP | 2021-03-27 | COMP | 2021-05-19 | COMP | Rule 16 | 24 | 95 | 19 | 2 | 5 | 38 | 288
19565 | 2020-03-31 | 2020-05-12 | 2020-08-05 | 2020-08-05 | COMP | 2020-10-02 | COMP | 2020-10-02 | COMP | 2020-10-05 | COMP | 2020-10-28 | COMP | Rule 16 | 31 | 61 | 42 | 1 | 2 | 18 | 150
19582 | 2020-03-31 | 2020-05-13 | 2021-03-18 | 2021-04-05 | COMP | 2021-05-26 | COMP | 2021-09-17 | COMP | 2021-09-28 | COMP | 2021-11-24 | COMP | Rule 15/16 | 32 | 213 | 38 | 80 | 8 | 41 | 419
19859 | 2020-03-31 | 2020-05-26 | 2020-08-03 | 2020-08-03 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2020-11-18 | COMP | 2020-12-16 | COMP | Rule 16 | 40 | 50 | 11 | 1 | 66 | 19 | 182
20045 | 2020-03-31 | 2020-06-03 | 2020-07-23 | 2021-07-29 | COMP | 2022-06-30 | COMP | 2022-07-26 | COMP | 2022-07-27 | COMP | 2022-08-18 | COMP | Rule 15/16 | 46 | 37 | 233 | 18 | 2 | 17 | 603
20953 | 2020-03-31 | 2020-07-15 | 2020-09-16 | 2020-09-16 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2021-05-11 | COMP | 2021-03-04 | COMP | Rule 16 | 76 | 45 | 32 | 1 | 132 |  | 234
21140 | 2020-03-31 | 2020-07-23 | 2020-09-11 | 2020-09-11 | COMP | 2020-11-12 | COMP | 2020-11-12 | COMP | 2021-01-04 | COMP | 2021-02-18 | COMP | Rule 16 | 82 | 36 | 44 | 1 | 34 | 32 | 224
21506 | 2020-03-31 | 2020-08-10 | 2020-10-15 | 2020-10-15 | COMP | 2021-01-06 | COMP | 2021-12-29 | COMP | 2021-09-14 | COMP | 2022-03-02 | COMP | Rule 15/16 | 94 | 48 | 55 | 248 | 0 | 44 | 485
22857 | 2020-03-31 | 2020-10-14 | 2020-12-28 | 2020-12-28 | COMP | 2021-01-14 | COMP | 2021-06-03 | COMP | 2021-01-14 | COMP | 2021-07-07 | COMP | Rule 16 | 140 | 50 | 13 | 98 | 0 | 24 | 321
23093 | 2020-03-31 | 2020-10-23 | 2021-12-29 | 2022-01-20 | COMP | 2022-02-24 | COMP | 2023-03-21 | COMP | 2023-02-24 | COMP | 2023-04-22 | COMP | Rule 15/16 | 147 | 296 | 25 | 268 | 0 | 24 | 771
23604 | 2020-03-31 | 2020-11-14 | 2021-04-09 | 2021-04-30 | COMP | 2021-05-20 | COMP | 2021-05-21 | COMP | 2022-09-13 | COMP | 2022-10-18 | COMP | Rule 15/16 | 161 | 99 | 15 | 2 | 331 | 26 | 645
4298 | 2020-04-01 | 2020-05-11 | 2020-07-29 | 2020-06-05 | COMP |  |  |  |  | 2020-05-11 | COMP | 2020-06-19 | COMP | Other | 29 | 57 |  |  |  |  | 57
4301 | 2020-04-01 | 2020-05-18 | 2020-06-11 | 2020-06-11 | COMP | 2020-09-22 | COMP | 2020-11-30 | COMP | 2020-11-25 | COMP | 2021-01-06 | COMP | Rule 16 | 34 | 18 | 73 | 47 | 0 | 26 | 194
18664 | 2020-04-01 | 2020-04-01 | 2020-07-20 | 2020-07-20 | COMP | 2020-08-06 | COMP | 2020-10-22 | COMP | 2020-10-21 | COMP | 2020-11-09 | COMP | Rule 16 | 1 | 78 | 14 | 55 | 0 | 13 | 157
18780 | 2020-04-01 | 2020-04-09 | 2020-06-04 | 2020-06-04 | COMP | 2020-07-22 | COMP | 2020-07-22 | COMP | 2020-08-27 | COMP | 2020-08-27 | COMP | Rule 16 | 7 | 40 | 35 | 1 | 27 | 1 | 106
18858 | 2020-04-01 | 2020-04-09 | 2020-10-23 | 2020-10-23 | COMP | 2020-10-26 | NOTN | 2020-12-02 | COMP | 2020-11-30 | COMP | 2021-01-11 | COMP | Other | 7 | 140 |  | 26 | 0 | 27 | 197
19113 | 2020-04-01 | 2020-04-21 | 2020-09-24 | 2020-09-24 | COMP | 2020-10-13 | COMP | 2020-10-15 | COMP | 2020-12-02 | COMP | 2020-12-21 | COMP | Rule 16 | 15 | 111 | 14 | 3 | 32 | 14 | 184
19123 | 2020-04-01 | 2020-04-21 | 2020-05-08 | 2020-05-08 | COMP | 2021-01-07 | COMP | 2021-01-20 | COMP | 2023-12-30 | INPR | 2021-07-15 | COMP | Rule 16 | 15 | 14 | 168 | 9 |  |  | 326
19157 | 2020-04-01 | 2020-04-23 | 2020-07-15 | 2020-07-15 | COMP | 2020-07-23 | COMP | 2020-08-18 | COMP | 2020-08-21 | COMP | 2020-09-15 | COMP | Rule 16 | 17 | 59 | 7 | 19 | 4 | 17 | 118
19158 | 2020-04-01 | 2020-04-23 | 2020-07-25 | 2020-07-25 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2020-08-11 | COMP | 2020-10-15 | COMP | Rule 16 | 17 | 66 | 5 | 1 | 8 | 47 | 140
19243 | 2020-04-01 | 2020-04-28 | 2020-05-08 | 2020-05-08 | COMP | 2020-06-18 | COMP | 2020-06-18 | COMP | 2022-07-16 | INPR | 2020-09-30 | COMP | Rule 16 | 20 | 9 | 29 | 1 |  |  | 129
19373 | 2020-04-01 | 2020-05-04 | 2020-09-09 | 2020-09-09 | COMP | 2020-10-15 | COMP | 2020-10-15 | COMP | 2020-10-19 | COMP | 2020-11-19 | COMP | Rule 16 | 24 | 91 | 27 | 1 | 3 | 23 | 164
19578 | 2020-04-01 | 2020-05-13 | 2020-10-27 | 2020-10-27 | COMP | 2021-03-03 | COMP | 2021-03-03 | COMP | 2021-08-26 | COMP | 2021-09-29 | COMP | Rule 16 | 31 | 118 | 85 | 1 | 125 | 24 | 379
19753 | 2020-04-01 | 2020-05-20 | 2021-01-28 | 2021-01-28 | COMP | 2021-02-02 | COMP | 2021-03-24 | COMP | 2023-12-04 | INPR | 2021-04-14 | COMP | Rule 16 | 36 | 174 | 4 | 36 |  |  | 262
19880 | 2020-04-01 | 2020-05-27 | 2020-09-09 | 2021-05-10 | COMP | 2021-06-24 | COMP | 2021-06-30 | COMP | 2021-07-15 | COMP | 2021-11-23 | COMP | Rule 16 | 40 | 75 | 33 | 5 | 11 | 92 | 417
19962 | 2020-04-01 | 2020-05-29 | 2021-01-26 | 2021-01-26 | COMP | 2021-06-25 | COMP | 2021-07-27 | COMP | 2022-02-04 | COMP | 2022-04-12 | COMP | Rule 15/16 | 42 | 166 | 107 | 22 | 134 | 47 | 513
20003 | 2020-04-01 | 2020-06-01 | 2020-09-01 | 2021-08-06 | COMP | 2022-01-03 | COMP | 2022-08-02 | COMP | 2022-08-03 | COMP | 2022-09-14 | COMP | Rule 15/16 | 43 | 67 | 103 | 147 | 2 | 30 | 620
20047 | 2020-04-01 | 2020-06-02 | 2020-09-05 | 2020-09-05 | COMP | 2020-10-06 | COMP | 2020-10-27 | COMP | 2020-10-23 | COMP | 2021-01-26 | COMP | Rule 16 | 44 | 69 | 21 | 16 | 0 | 60 | 207
20298 | 2020-04-01 | 2020-06-15 | 2020-08-24 | 2020-08-24 | COMP | 2020-09-17 | COMP | 2020-10-19 | COMP | 2020-11-03 | COMP | 2021-02-19 | COMP | Rule 15/16 | 53 | 51 | 18 | 23 | 12 | 72 | 224
21325 | 2020-04-01 | 2020-07-31 | 2020-12-03 | 2020-12-03 | COMP | 2020-12-11 | COMP | 2020-12-11 | COMP | 2021-04-26 | COMP | 2021-05-26 | COMP | Rule 16 | 87 | 86 | 7 | 1 | 93 | 23 | 292
21379 | 2020-04-01 | 2020-08-04 | 2020-10-21 | 2020-10-21 | COMP | 2020-12-04 | COMP | 2021-03-30 | COMP | 2021-03-04 | COMP | 2021-05-01 | COMP | Rule 16 | 89 | 56 | 30 | 79 | 0 | 24 | 274
21528 | 2020-04-01 | 2020-08-11 | 2020-09-01 | 2021-08-06 | COMP | 2021-01-27 | NOTN | 2021-08-06 | COMP | 2021-09-07 | COMP | 2022-08-24 | COMP | Other | 94 | 16 |  | 1 | 22 | 244 | 606
21573 | 2020-04-01 | 2020-08-13 | 2020-10-08 | 2020-10-08 | COMP | 2020-11-17 | COMP | 2020-12-08 | COMP | 2021-01-20 | COMP | 2021-01-28 | COMP | Rule 16 | 96 | 40 | 28 | 14 | 29 | 7 | 209
22162 | 2020-04-01 | 2020-09-12 | 2020-10-08 | 2020-10-08 | COMP | 2020-11-20 | COMP | 2020-11-20 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | Rule 16 | 116 | 19 | 31 | 1 | 33 | 1 | 197
18742 | 2020-04-02 | 2020-04-07 | 2020-05-11 | 2021-06-08 | COMP | 2021-08-06 | COMP | 2021-08-12 | COMP | 2021-03-23 | COMP | 2021-10-03 | COMP | Rule 15/16 | 4 | 25 | 43 | 5 | 0 | 36 | 380
18758 | 2020-04-02 | 2020-04-06 | 2021-01-22 | 2021-01-25 | COMP | 2021-02-08 | COMP | 2021-07-09 | COMP | 2022-07-06 | COMP | 2022-07-21 | COMP | Rule 15/16 | 3 | 202 | 11 | 107 | 250 | 12 | 581
18834 | 2020-04-02 | 2020-04-09 | 2020-06-01 | 2020-06-24 | COMP | 2020-12-14 | COMP | 2020-12-14 | COMP | 2023-10-10 | COMP | 2023-12-01 | COMP | Other | 6 | 37 | 120 | 1 | 710 | 36 | 922
18906 | 2020-04-02 | 2020-04-13 | 2021-02-11 | 2021-02-11 | COMP | 2021-05-05 | COMP | 2021-06-02 | COMP | 2021-09-08 | COMP | 2021-11-13 | COMP | Rule 15/16 | 8 | 211 | 59 | 20 | 69 | 47 | 409
19064 | 2020-04-02 | 2020-04-20 | 2020-07-28 | 2020-11-13 | COMP | 2021-01-11 | COMP | 2021-01-11 | COMP | 2021-03-09 | COMP | 2021-04-02 | COMP | Rule 16 | 13 | 71 | 38 | 1 | 40 | 19 | 253
19220 | 2020-04-02 | 2020-04-24 | 2020-09-02 | 2020-09-02 | COMP | 2020-09-21 | COMP | 2020-09-21 | COMP | 2021-01-14 | COMP | 2021-02-10 | COMP | Rule 16 | 17 | 93 | 13 | 1 | 79 | 19 | 217
19221 | 2020-04-02 | 2020-04-25 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-13 | COMP | 2020-08-16 | COMP | 2020-07-27 | COMP | 2020-09-15 | COMP | Rule 16 | 17 | 37 | 19 | 25 | 0 | 21 | 117
19228 | 2020-04-02 | 2020-04-27 | 2020-06-12 | 2020-06-12 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2021-01-05 | COMP | 2021-02-01 | COMP | Rule 16 | 18 | 34 | 44 | 1 | 99 | 19 | 210
19690 | 2020-04-02 | 2020-05-18 | 2020-09-04 | 2022-03-17 | COMP | 2022-05-24 | COMP | 2023-10-04 | COMP | 2023-10-04 | COMP | 2023-12-29 | COMP | Rule 16 | 33 | 79 | 49 | 342 | 1 | 59 | 941
19742 | 2020-04-02 | 2020-05-20 | 2020-08-03 | 2020-11-18 | COMP | 2020-11-23 | COMP | 2020-11-23 | COMP |  | INPR | 2020-12-23 | COMP | Rule 15/16 | 35 | 53 | 4 | 1 |  |  | 185
20412 | 2020-04-02 | 2020-06-19 | 2020-09-11 | 2020-09-11 | COMP | 2020-10-05 | COMP | 2020-10-15 | COMP | 2020-12-08 | COMP | 2021-01-26 | COMP | Rule 15/16 | 56 | 60 | 17 | 9 | 36 | 33 | 206
20593 | 2020-04-02 | 2020-06-29 | 2020-08-14 | 2020-08-24 | COMP | 2020-08-25 | COMP | 2020-10-04 | COMP | 2020-10-07 | COMP | 2020-10-23 | COMP | Rule 15/16 | 62 | 35 | 2 | 28 | 3 | 13 | 145
20901 | 2020-04-02 | 2020-07-13 | 2020-09-08 | 2020-09-08 | COMP | 2021-06-22 | COMP | 2021-09-03 | COMP | 2021-06-25 | COMP | 2021-10-05 | COMP | Rule 16 | 72 | 41 | 198 | 53 | 0 | 22 | 382
21265 | 2020-04-02 | 2020-07-30 | 2020-10-05 | 2020-10-05 | COMP | 2020-10-15 | COMP | 2020-10-21 | COMP | 2020-12-16 | COMP | 2021-01-05 | COMP | Rule 16 | 85 | 47 | 9 | 5 | 38 | 13 | 192
22250 | 2020-04-02 | 2020-09-16 | 2020-12-23 | 2020-12-23 | COMP | 2021-02-17 | COMP | 2021-02-17 | COMP | 2021-03-16 | COMP | 2021-04-27 | COMP | Rule 16 | 118 | 68 | 37 | 1 | 20 | 31 | 270
23145 | 2020-04-02 | 2020-10-26 | 2021-02-13 | 2021-02-13 | COMP | 2021-03-09 | COMP | 2021-03-26 | COMP | 2021-03-29 | COMP | 2021-04-29 | COMP | Rule 16 | 146 | 74 | 16 | 14 | 2 | 24 | 272
27736 | 2020-04-02 | 2021-05-06 | 2021-08-07 | 2023-02-28 | COMP | 2023-03-03 | COMP | 2023-03-06 | COMP | 2023-04-14 | COMP | 2023-12-12 | COMP | Rule 16 | 277 | 65 | 4 | 2 | 30 | 166 | 929
18681 | 2020-04-03 | 2020-04-03 | 2020-08-13 | 2020-08-13 | COMP | 2020-08-13 | NOTN | 2020-08-14 | COMP | 2020-08-13 | COMP | 2020-11-04 | COMP | Other | 1 | 94 |  | 2 | 0 | 58 | 152
18765 | 2020-04-03 | 2020-04-06 | 2021-03-16 | 2021-03-16 | COMP | 2021-07-13 | COMP | 2021-07-13 | COMP | 2022-08-10 | COMP | 2022-10-18 | COMP | Rule 16 | 2 | 238 | 84 | 1 | 273 | 49 | 642
18931 | 2020-04-03 | 2020-04-13 | 2020-07-24 | 2020-07-24 | COMP | 2020-08-07 | COMP | 2020-09-03 | COMP | 2020-08-11 | COMP | 2020-10-05 | COMP | Rule 16 | 7 | 74 | 11 | 20 | 0 | 22 | 130
19006 | 2020-04-03 | 2020-04-16 | 2020-06-24 | 2022-09-26 | COMP | 2022-12-12 | COMP | 2022-12-14 | COMP | 2023-02-07 | COMP | 2023-04-07 | COMP | Rule 29 | 10 | 49 | 53 | 3 | 37 | 43 | 758
19025 | 2020-04-03 | 2020-04-17 | 2020-07-31 | 2020-07-31 | COMP | 2020-09-01 | COMP | 2020-09-22 | COMP | 2021-09-20 | COMP | 2022-04-22 | COMP | Rule 15/16 | 11 | 75 | 23 | 15 | 250 | 150 | 519
19233 | 2020-04-03 | 2020-04-27 | 2020-05-19 | 2020-05-19 | COMP | 2020-06-01 | COMP | 2020-06-01 | COMP | 2020-06-11 | COMP | 2020-06-17 | COMP | Rule 16 | 17 | 17 | 9 | 1 | 9 | 5 | 53
20099 | 2020-04-03 | 2020-06-04 | 2020-07-09 | 2020-07-09 | COMP | 2020-08-26 | COMP | 2020-09-28 | COMP | 2020-12-24 | COMP | 2021-01-12 | COMP | Rule 16 | 44 | 26 | 35 | 23 | 61 | 12 | 196
20175 | 2020-04-03 | 2020-06-09 | 2020-07-16 | 2020-07-16 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2022-01-31 | INPR | 2020-08-26 | COMP | Rule 16 | 47 | 28 | 17 | 1 |  |  | 103
20499 | 2020-04-03 | 2020-06-23 | 2020-07-14 | 2020-07-14 | COMP | 2020-07-21 | COMP | 2020-07-29 | COMP | 2020-10-02 | COMP | 2020-12-14 | COMP | Rule 16 | 57 | 16 | 6 | 7 | 47 | 49 | 177
20650 | 2020-04-03 | 2020-06-30 | 2020-08-31 | 2021-09-28 | COMP | 2022-02-18 | COMP | 2022-04-22 | COMP |  |  | 2023-07-03 | COMP | Rule 15/16 | 62 | 45 | 100 | 45 |  |  | 817
20652 | 2020-04-03 | 2020-06-30 | 2020-08-31 | 2020-09-18 | COMP | 2020-10-05 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2021-02-17 | COMP | Rule 16 | 62 | 45 | 12 | 54 | 1 | 38 | 220
20932 | 2020-04-03 | 2020-07-13 | 2020-09-23 | 2020-09-23 | COMP | 2020-11-17 | COMP | 2021-02-09 | COMP | 2021-02-22 | COMP | 2021-03-22 | COMP | Rule 16 | 71 | 52 | 39 | 56 | 9 | 21 | 243
21482 | 2020-04-03 | 2020-08-10 | 2020-11-13 | 2020-11-13 | COMP | 2020-11-30 | COMP | 2021-04-05 | COMP | 2021-04-26 | COMP | 2021-07-13 | COMP | Rule 16 | 91 | 68 | 10 | 87 | 16 | 55 | 322
21572 | 2020-04-03 | 2020-08-13 | 2020-11-24 | 2020-11-24 | COMP | 2021-03-03 | COMP | 2021-03-03 | COMP | 2022-08-30 | COMP | 2022-10-03 | COMP | Rule 16 | 94 | 72 | 66 | 1 | 379 | 24 | 631
22816 | 2020-04-03 | 2020-10-13 | 2020-10-25 | 2020-10-25 | COMP | 2021-03-15 | COMP | 2021-04-08 | COMP | 2021-06-07 | COMP | 2021-06-22 | COMP | Rule 16 | 136 | 9 | 94 | 19 | 42 | 12 | 308
19304 | 2020-04-04 | 2020-04-29 | 2020-12-16 | 2021-01-15 | COMP | 2021-04-15 | COMP | 2021-04-15 | COMP | 2021-07-28 | COMP | 2021-08-23 | COMP | Rule 15/16 | 18 | 161 | 63 | 1 | 73 | 19 | 350
19375 | 2020-04-04 | 2020-05-04 | 2020-06-30 | 2020-06-30 | COMP | 2020-07-01 | NOTN | 2020-07-01 | COMP | 2020-07-01 | COMP | 2020-08-05 | COMP | Other | 21 | 41 |  | 2 | 1 | 26 | 87
21824 | 2020-04-04 | 2020-08-28 | 2020-10-09 | 2020-10-09 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2021-01-13 | COMP | 2021-01-22 | COMP | Rule 16 | 104 | 30 | 39 | 1 | 26 | 7 | 202
22421 | 2020-04-04 | 2020-09-24 | 2020-12-15 | 2020-12-15 | COMP | 2020-12-23 | COMP | 2021-02-26 | COMP | 2021-03-03 | COMP | 2021-06-15 | COMP | Rule 16 | 122 | 56 | 7 | 44 | 4 | 74 | 302
24115 | 2020-04-04 | 2020-12-10 | 2021-04-08 | 2021-08-18 | COMP | 2021-10-22 | COMP | 2022-03-28 | COMP |  | INPR | 2023-08-04 | COMP | Rule 15/16 | 174 | 82 | 47 | 107 |  |  | 839
18837 | 2020-04-05 | 2020-04-09 | 2020-11-23 | 2020-11-23 | COMP | 2020-11-30 | COMP | 2020-11-30 | COMP | 2021-09-15 | COMP | 2021-08-23 | COMP | Rule 16 | 4 | 160 | 4 | 1 | 201 |  | 350
18884 | 2020-04-06 | 2020-04-11 | 2020-07-27 | 2020-07-27 | COMP | 2021-12-20 | COMP | 2021-12-20 | COMP | 2021-12-20 | COMP | 2022-02-09 | COMP | Rule 16 | 5 | 75 | 352 | 1 | 1 | 37 | 467
18995 | 2020-04-06 | 2020-04-16 | 2020-10-14 | 2020-10-14 | COMP | 2020-10-29 | COMP | 2020-11-03 | COMP | 2020-10-29 | COMP | 2021-02-11 | COMP | Rule 16 | 9 | 128 | 12 | 4 | 0 | 67 | 216
19171 | 2020-04-06 | 2020-04-22 | 2020-07-13 | 2020-07-13 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-08-28 | COMP | 2020-10-12 | COMP | Rule 16 | 13 | 58 | 35 | 1 | 1 | 31 | 134
19256 | 2020-04-06 | 2020-04-28 | 2020-06-02 | 2020-06-02 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-11 | COMP | 2020-06-12 | COMP | Rule 16 | 17 | 25 | 8 | 1 | 1 | 2 | 49
19488 | 2020-04-06 | 2020-05-09 | 2020-06-09 | 2020-06-09 | COMP | 2021-02-25 | COMP | 2021-08-18 | COMP | 2021-12-28 | COMP | 2022-01-19 | COMP | Rule 16 | 25 | 21 | 180 | 123 | 91 | 16 | 452
19545 | 2020-04-06 | 2020-05-11 | 2020-11-21 | 2020-11-21 | COMP | 2021-01-07 | COMP | 2021-06-09 | COMP | 2021-06-02 | COMP | 2021-08-31 | COMP | Rule 16 | 26 | 137 | 30 | 107 | 0 | 59 | 356
19872 | 2020-04-06 | 2020-05-27 | 2020-07-03 | 2020-07-29 | COMP | 2020-08-28 | COMP | 2020-09-03 | COMP | 2020-09-14 | COMP | 2020-10-06 | COMP | Rule 16 | 37 | 28 | 23 | 5 | 7 | 17 | 130
19876 | 2020-04-06 | 2020-05-26 | 2020-06-22 | 2020-06-22 | COMP | 2020-08-24 | COMP | 2020-08-24 | NOTN | 2021-09-02 | COMP | 2021-09-14 | COMP | Rule 16 | 36 | 20 | 46 |  |  |  | 365
20075 | 2020-04-06 | 2020-06-03 | 2020-09-19 | 2021-03-26 | COMP | 2021-05-10 | COMP | 2021-07-06 | COMP | 2021-07-14 | COMP | 2021-08-12 | COMP | Rule 15/16 | 42 | 77 | 32 | 40 | 7 | 22 | 343
20277 | 2020-04-06 | 2020-06-12 | 2020-07-27 | 2022-10-17 | COMP | 2023-02-08 | COMP | 2023-02-08 | COMP | 2022-09-12 | COMP | 2023-04-21 | COMP | Rule 16 | 49 | 32 | 77 | 1 | 0 | 52 | 767
20450 | 2020-04-06 | 2020-06-20 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-07 | COMP | 2021-07-08 | COMP | 2022-06-17 | COMP | 2022-08-12 | COMP | Rule 16 | 54 | 26 | 10 | 230 | 240 | 39 | 595
20828 | 2020-04-06 | 2020-07-08 | 2021-01-20 | 2021-01-20 | COMP | 2021-03-05 | COMP | 2021-03-23 | COMP | 2021-04-19 | COMP | 2021-05-27 | COMP | Unknown | 67 | 134 | 32 | 13 | 20 | 29 | 290
20829 | 2020-04-06 | 2020-07-08 | 2020-11-13 | 2020-11-13 | COMP | 2021-03-02 | COMP | 2021-03-02 | COMP | 2023-07-01 | INPR | 2021-05-06 | COMP | Rule 16 | 67 | 91 | 72 | 1 |  |  | 275
21075 | 2020-04-06 | 2020-07-21 | 2020-09-28 | 2020-09-28 | COMP | 2021-02-03 | COMP | 2021-02-03 | COMP | 2021-07-30 | COMP | 2021-09-15 | COMP | Rule 16 | 76 | 49 | 87 | 1 | 125 | 33 | 366
22380 | 2020-04-06 | 2020-09-22 | 2021-01-20 | 2021-01-20 | COMP | 2021-03-01 | COMP | 2021-03-22 | COMP | 2021-05-03 | COMP | 2021-06-09 | COMP | Rule 16 | 120 | 81 | 28 | 16 | 31 | 27 | 298
18813 | 2020-04-07 | 2020-04-08 | 2020-10-16 | 2020-10-16 | COMP | 2020-10-16 | NOTN | 2020-11-13 | COMP | 2020-11-16 | NOTN | 2021-01-14 | COMP | Other | 2 | 136 |  | 20 |  |  | 196
18975 | 2020-04-07 | 2020-04-15 | 2020-12-03 | 2020-12-03 | COMP | 2021-02-08 | NOTN | 2021-05-26 | COMP | 2021-05-12 | COMP | 2021-06-03 | COMP | Other | 7 | 162 |  | 121 | 0 | 6 | 293
18987 | 2020-04-07 | 2020-04-15 | 2021-01-27 | 2021-01-28 | COMP | 2021-02-03 | COMP | 2021-02-03 | COMP | 2022-05-28 | INPR | 2021-05-04 | COMP | Rule 16 | 7 | 198 | 5 | 1 |  |  | 272
19330 | 2020-04-07 | 2020-05-02 | 2020-08-04 | 2020-08-04 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2022-01-31 | INPR | 2021-01-14 | COMP | Rule 16 | 19 | 66 | 56 | 1 |  |  | 196
19351 | 2020-04-07 | 2020-05-02 | 2020-07-20 | 2020-07-20 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2021-01-21 | COMP | 2021-02-17 | COMP | Rule 16 | 19 | 55 | 73 | 1 | 55 | 19 | 218
19378 | 2020-04-07 | 2020-05-04 | 2020-09-01 | 2020-09-01 | COMP | 2020-09-18 | COMP | 2020-09-18 | COMP | 2020-09-24 | COMP | 2020-10-30 | COMP | Rule 16 | 20 | 86 | 13 | 1 | 5 | 27 | 147
19863 | 2020-04-07 | 2020-05-26 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-03 | COMP | 2020-08-03 | COMP | 2022-01-31 | INPR | 2020-10-29 | COMP | Rule 16 | 35 | 23 | 28 | 1 |  |  | 146
20182 | 2020-04-07 | 2020-06-09 | 2020-08-27 | 2020-08-27 | COMP | 2021-01-28 | COMP | 2021-01-28 | COMP | 2022-01-24 | COMP | 2022-03-08 | COMP | Rule 16 | 45 | 58 | 104 | 1 | 250 | 31 | 484
20213 | 2020-04-07 | 2020-06-10 | 2020-11-17 | 2020-11-17 | COMP | 2021-01-20 | COMP | 2021-01-23 | COMP |  | INPR | 2021-04-30 | COMP | Rule 16 | 46 | 113 | 42 | 3 |  |  | 270
20255 | 2020-04-07 | 2020-06-12 | 2020-08-06 | 2020-08-06 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2020-08-20 | COMP | 2020-09-25 | COMP | Rule 16 | 48 | 40 | 10 | 1 | 2 | 26 | 122
20323 | 2020-04-07 | 2020-06-15 | 2020-07-14 | 2020-07-14 | COMP | 2020-08-04 | COMP | 2021-01-13 | COMP | 2021-01-13 | COMP | 2021-02-24 | COMP | Rule 16 | 49 | 22 | 16 | 111 | 1 | 29 | 223
20404 | 2020-04-07 | 2020-06-19 | 2020-10-08 | 2021-01-24 | COMP | 2021-03-23 | COMP | 2021-04-12 | COMP | 2021-04-19 | COMP | 2021-04-16 | COMP | Rule 16 | 53 | 79 | 41 | 15 | 6 |  | 260
21076 | 2020-04-07 | 2020-07-21 | 2020-09-11 | 2020-11-17 | COMP | 2021-02-05 | COMP | 2021-02-05 | COMP | 2021-03-09 | COMP | 2021-04-21 | COMP | Rule 16 | 75 | 38 | 54 | 1 | 22 | 32 | 263
21125 | 2020-04-07 | 2020-07-23 | 2020-08-04 | 2020-08-04 | COMP | 2020-11-04 | COMP | 2020-11-04 | COMP | 2021-09-07 | COMP | 2021-09-27 | COMP | Rule 16 | 77 | 9 | 66 | 1 | 210 | 15 | 373
21165 | 2020-04-07 | 2020-07-24 | 2020-10-06 | 2020-10-06 | COMP | 2020-11-23 | COMP | 2020-11-25 | COMP | 2021-01-11 | COMP | 2020-12-17 | COMP | Rule 15/16 | 78 | 52 | 34 | 3 | 30 |  | 178
22106 | 2020-04-07 | 2020-09-10 | 2020-11-25 | 2020-11-25 | COMP | 2021-01-19 | COMP | 2021-01-26 | COMP |  | INPR | 2023-11-15 | COMP | Rule 16 | 111 | 54 | 35 | 6 |  |  | 909
23328 | 2020-04-07 | 2020-11-02 | 2021-01-27 | 2021-01-27 | COMP | 2021-08-16 | COMP | 2021-08-16 | COMP | 2021-05-06 | COMP | 2021-09-02 | COMP | Rule 16 | 148 | 57 | 141 | 1 | 0 | 14 | 357
23419 | 2020-04-07 | 2020-11-05 | 2020-12-11 | 2020-12-11 | COMP | 2021-01-27 | COMP | 2021-03-25 | COMP | 2021-05-03 | COMP | 2021-04-30 | COMP | Rule 16 | 151 | 24 | 31 | 41 | 28 |  | 270
18843 | 2020-04-08 | 2020-04-08 | 2020-07-16 | 2020-07-16 | COMP | 2020-07-16 | NOTN | 2020-07-20 | COMP | 2020-07-16 | COMP | 2020-08-27 | COMP | Other | 1 | 71 |  | 3 | 0 | 29 | 101
18879 | 2020-04-08 | 2020-04-10 | 2020-09-23 | 2020-09-23 | COMP | 2020-12-30 | COMP | 2021-04-27 | COMP | 2021-04-27 | COMP | 2021-06-09 | COMP | Rule 16 | 3 | 117 | 67 | 82 | 1 | 31 | 296
18942 | 2020-04-08 | 2020-04-14 | 2020-05-05 | 2020-05-05 | COMP | 2020-05-13 | COMP | 2020-05-13 | COMP | 2020-07-13 | COMP | 2020-08-03 | COMP | Rule 16 | 5 | 16 | 7 | 1 | 43 | 16 | 83
19023 | 2020-04-08 | 2020-04-17 | 2020-07-09 | 2020-07-09 | COMP | 2020-07-09 | NOTN | 2020-08-28 | COMP | 2020-07-09 | COMP | 2020-11-11 | COMP | Other | 8 | 59 |  | 37 | 0 | 52 | 153
19105 | 2020-04-08 | 2020-04-21 | 2020-05-31 | 2020-05-31 | COMP | 2020-08-04 | COMP | 2020-09-08 | COMP | 2020-09-14 | COMP | 2020-10-07 | COMP | Rule 16 | 10 | 28 | 47 | 25 | 5 | 18 | 129
19129 | 2020-04-08 | 2020-04-22 | 2020-07-01 | 2020-07-01 | COMP | 2020-07-13 | COMP | 2020-11-16 | COMP | 2020-12-12 | COMP | 2021-01-07 | COMP | Rule 16 | 11 | 50 | 9 | 89 | 18 | 17 | 190
19198 | 2020-04-08 | 2020-04-23 | 2020-08-03 | 2020-08-03 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2021-08-31 | COMP | 2021-09-29 | COMP | Rule 16 | 12 | 72 | 57 | 1 | 216 | 21 | 374
19352 | 2020-04-08 | 2020-05-02 | 2020-07-15 | 2020-07-15 | COMP | 2020-07-31 | COMP | 2020-07-31 | COMP | 2022-08-16 | COMP | 2022-09-11 | COMP | Rule 16 | 18 | 52 | 13 | 1 | 514 | 18 | 612
19389 | 2020-04-08 | 2020-05-05 | 2020-08-18 | 2020-08-18 | COMP | 2020-08-31 | COMP | 2020-10-19 | COMP | 2021-04-27 | COMP | 2021-06-15 | COMP | Rule 16 | 20 | 75 | 10 | 35 | 130 | 35 | 300
19526 | 2020-04-08 | 2020-05-11 | 2020-06-19 | 2020-06-19 | COMP | 2020-07-20 | COMP | 2020-07-20 | COMP | 2020-07-28 | COMP | 2020-10-02 | COMP | Rule 16 | 24 | 29 | 22 | 1 | 7 | 48 | 126
19569 | 2020-04-08 | 2020-05-12 | 2020-06-23 | 2020-06-23 | COMP | 2020-07-29 | COMP | 2020-10-08 | COMP | 2020-10-16 | COMP | 2020-12-15 | COMP | Rule 16 | 25 | 30 | 27 | 51 | 7 | 40 | 175
19602 | 2020-04-08 | 2020-05-14 | 2020-06-16 | 2020-06-16 | COMP | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-07-25 | COMP | 2020-10-02 | COMP | Rule 15/16 | 27 | 23 | 13 | 1 | 17 | 49 | 126
19692 | 2020-04-08 | 2020-05-18 | 2020-10-19 | 2020-10-19 | COMP | 2020-11-06 | COMP | 2020-12-07 | COMP | 2020-11-10 | COMP | 2020-12-30 | COMP | Rule 15/16 | 29 | 109 | 15 | 19 | 0 | 17 | 185
19760 | 2020-04-08 | 2020-05-20 | 2020-06-25 | 2020-06-25 | COMP | 2020-07-28 | COMP | 2020-07-28 | COMP | 2020-09-09 | COMP | 2020-10-19 | COMP | Rule 16 | 31 | 26 | 24 | 1 | 31 | 29 | 137
19817 | 2020-04-08 | 2020-05-23 | 2020-08-02 | 2020-08-02 | COMP | 2020-11-12 | COMP | 2020-11-12 | COMP | 2020-11-23 | COMP | 2021-01-07 | COMP | Rule 16 | 33 | 49 | 72 | 1 | 8 | 30 | 190
20017 | 2020-04-08 | 2020-06-02 | 2020-08-04 | 2020-08-04 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2021-03-01 | COMP | 2021-03-24 | COMP | Rule 16 | 39 | 46 | 50 | 1 | 93 | 18 | 242
20060 | 2020-04-08 | 2020-06-03 | 2020-07-22 | 2020-10-21 | COMP | 2020-11-17 | COMP | 2021-01-29 | COMP | 2021-01-29 | COMP | 2021-02-04 | COMP | Rule 16 | 40 | 36 | 19 | 49 | 1 | 5 | 209
20382 | 2020-04-08 | 2020-06-18 | 2020-09-11 | 2020-09-11 | COMP | 2021-03-03 | COMP | 2021-03-16 | COMP | 2021-08-17 | COMP | 2021-08-24 | COMP | Rule 16 | 51 | 61 | 117 | 10 | 109 | 6 | 349
20408 | 2020-04-08 | 2020-06-19 | 2020-10-15 | 2020-10-15 | COMP | 2021-02-08 | COMP | 2021-04-13 | COMP | 2021-11-17 | COMP | 2021-12-06 | COMP | Rule 15/16 | 52 | 84 | 77 | 46 | 153 | 12 | 419
20621 | 2020-04-08 | 2020-06-30 | 2020-08-12 | 2020-08-28 | COMP | 2021-09-10 | COMP | 2021-09-24 | COMP | 2021-09-13 | COMP | 2021-10-18 | COMP | Rule 16 | 59 | 32 | 260 | 11 | 0 | 17 | 387
20754 | 2020-04-08 | 2020-07-03 | 2020-11-19 | 2020-11-19 | COMP | 2020-12-08 | COMP | 2021-02-09 | COMP |  | INPR | 2022-04-23 | COMP | Rule 16 | 62 | 98 | 12 | 43 |  |  | 516
20935 | 2020-04-08 | 2020-07-13 | 2020-10-21 | 2021-06-03 | COMP | 2021-12-09 | COMP | 2022-01-05 | COMP | 2023-12-04 | INPR | 2022-04-20 | COMP | Rule 15/16 | 68 | 72 | 131 | 20 |  |  | 514
21085 | 2020-04-08 | 2020-07-21 | 2020-08-08 | 2020-08-08 | COMP | 2020-11-25 | COMP | 2020-11-25 | COMP | 2021-05-03 | COMP | 2021-01-21 | COMP | Rule 16 | 74 | 14 | 76 | 1 | 108 |  | 199
21168 | 2020-04-08 | 2020-07-24 | 2020-10-07 | 2020-10-07 | COMP | 2020-11-05 | COMP | 2020-11-05 | COMP | 2020-11-09 | COMP | 2021-01-11 | COMP | Rule 16 | 77 | 53 | 22 | 1 | 3 | 41 | 192
21190 | 2020-04-08 | 2020-07-27 | 2021-02-12 | 2021-02-12 | COMP | 2021-03-04 | COMP | 2021-08-19 | COMP | 2021-10-06 | COMP | 2021-11-03 | COMP | Rule 16 | 78 | 138 | 14 | 119 | 34 | 21 | 399
18882 | 2020-04-09 | 2020-04-10 | 2020-10-12 | 2020-10-12 | COMP | 2020-10-28 | COMP | 2021-01-06 | COMP | 2020-12-18 | COMP | 2021-02-24 | COMP | Rule 16 | 2 | 130 | 13 | 46 | 0 | 34 | 221
18917 | 2020-04-09 | 2020-04-12 | 2020-07-02 | 2020-07-02 | COMP | 2020-08-07 | COMP | 2020-08-07 | COMP | 2020-09-09 | COMP | 2021-01-08 | COMP | Rule 16 | 2 | 58 | 27 | 1 | 23 | 83 | 190
19195 | 2020-04-09 | 2020-04-23 | 2020-05-11 | 2020-05-11 | COMP | 2020-05-28 | COMP | 2020-05-28 | COMP | 2020-06-15 | COMP | 2020-11-19 | COMP | Rule 16 | 11 | 13 | 13 | 1 | 13 | 112 | 158
19196 | 2020-04-09 | 2020-04-23 | 2020-07-16 | 2020-07-17 | COMP | 2020-07-27 | COMP | 2020-07-27 | COMP | 2020-08-10 | COMP | 2020-09-03 | COMP | Rule 16 | 11 | 60 | 7 | 1 | 11 | 19 | 105
19487 | 2020-04-09 | 2020-05-09 | 2020-10-29 | 2020-10-29 | COMP | 2020-12-09 | COMP | 2021-01-04 | COMP | 2020-11-20 | COMP | 2021-02-01 | COMP | Rule 16 | 22 | 122 | 27 | 17 | 0 | 20 | 205
19592 | 2020-04-09 | 2020-05-14 | 2020-07-08 | 2020-07-08 | COMP | 2020-10-13 | COMP | 2020-10-15 | COMP | 2020-11-09 | COMP | 2020-12-05 | COMP | Rule 16 | 26 | 39 | 69 | 3 | 18 | 17 | 167
20232 | 2020-04-09 | 2020-06-11 | 2020-07-23 | 2020-07-23 | COMP | 2020-08-03 | COMP | 2020-11-20 | COMP | 2020-11-20 | COMP | 2020-12-29 | COMP | Rule 16 | 45 | 31 | 8 | 78 | 1 | 25 | 183
20273 | 2020-04-09 | 2020-06-12 | 2020-07-24 | 2020-07-26 | COMP | 2020-08-17 | COMP | 2020-08-17 | COMP | 2021-02-01 | COMP | 2021-02-19 | COMP | Rule 16 | 46 | 31 | 16 | 1 | 114 | 14 | 218
20534 | 2020-04-09 | 2020-06-25 | 2020-08-08 | 2020-08-08 | COMP | 2020-10-23 | COMP | 2020-10-23 | COMP | 2020-10-23 | COMP | 2020-12-02 | COMP | Rule 16 | 55 | 32 | 54 | 1 | 1 | 26 | 165
20752 | 2020-04-09 | 2020-07-03 | 2020-08-27 | 2020-12-24 | COMP | 2021-01-06 | COMP | 2021-01-06 | COMP | 2021-04-28 | COMP | 2021-05-13 | COMP | Rule 16 | 61 | 40 | 8 | 1 | 79 | 12 | 277
20837 | 2020-04-09 | 2020-07-08 | 2020-08-10 | 2020-08-10 | COMP | 2020-09-03 | COMP | 2021-10-06 | COMP | 2021-11-02 | COMP | 2021-11-08 | COMP | Rule 16 | 64 | 24 | 19 | 274 | 20 | 5 | 401
20936 | 2020-04-09 | 2020-07-14 | 2020-09-08 | 2020-09-08 | COMP | 2020-09-25 | COMP | 2020-09-25 | COMP | 2020-10-07 | COMP | 2021-01-08 | COMP | Rule 16 | 68 | 40 | 14 | 1 | 9 | 63 | 190
21163 | 2020-04-09 | 2020-07-24 | 2020-09-20 | 2021-05-12 | COMP | 2021-10-15 | COMP | 2021-10-15 | INPR | 2021-10-18 | COMP | 2021-12-03 | COMP | Rule 15/16 | 76 | 40 | 110 |  |  |  | 417
21305 | 2020-04-09 | 2020-07-31 | 2020-09-27 | 2020-09-27 | COMP | 2020-12-18 | COMP | 2021-02-23 | COMP | 2021-11-22 | COMP | 2021-12-28 | COMP | Rule 15/16 | 81 | 40 | 57 | 44 | 191 | 25 | 434
22593 | 2020-04-09 | 2020-10-01 | 2020-10-23 | 2020-10-23 | COMP | 2020-11-16 | COMP | 2020-11-24 | COMP | 2020-11-20 | COMP | 2020-12-21 | COMP | Rule 16 | 124 | 17 | 16 | 7 | 0 | 18 | 178
23722 | 2020-04-09 | 2020-11-20 | 2021-02-25 | 2021-02-25 | COMP | 2021-03-22 | COMP | 2021-03-25 | COMP | 2023-11-07 | INPR | 2022-10-20 | COMP | Rule 16 | 159 | 64 | 18 | 4 |  |  | 640
26283 | 2020-04-09 | 2021-03-15 | 2021-04-30 | 2021-04-30 | COMP | 2021-10-04 | COMP | 2022-10-06 | COMP | 2022-09-27 | COMP | 2022-11-22 | COMP | Rule 16 | 234 | 35 | 109 | 255 | 0 | 33 | 662
18947 | 2020-04-10 | 2020-04-14 | 2020-06-08 | 2020-06-08 | COMP | 2020-08-25 | COMP | 2020-08-25 | COMP |  | INPR | 2020-10-02 | COMP | Rule 15/16 | 3 | 39 | 57 | 1 |  |  | 124
18955 | 2020-04-10 | 2020-04-14 | 2020-05-12 | 2020-05-12 | COMP | 2021-10-08 | COMP | 2021-10-08 | COMP | 2021-10-11 | COMP | 2021-11-02 | COMP | Rule 16 | 3 | 21 | 357 | 1 | 2 | 17 | 396
18991 | 2020-04-10 | 2020-04-16 | 2020-07-15 | 2021-01-22 | COMP | 2021-02-03 | COMP | 2021-03-11 | COMP | 2021-05-04 | COMP | 2021-05-06 | COMP | Rule 16 | 5 | 64 | 9 | 26 | 39 | 3 | 271
19165 | 2020-04-10 | 2020-04-22 | 2020-11-17 | 2020-11-17 | COMP | 2023-10-20 | COMP | 2023-12-05 | COMP | 2023-11-03 | COMP | 2023-12-19 | COMP | Other | 9 | 147 | 735 | 30 | 0 | 11 | 928
19169 | 2020-04-10 | 2020-04-23 | 2020-10-05 | 2020-10-05 | COMP | 2020-10-09 | COMP | 2020-10-09 | COMP | 2020-10-30 | COMP | 2020-11-30 | COMP | Rule 16 | 10 | 116 | 5 | 1 | 16 | 19 | 162
19296 | 2020-04-10 | 2020-04-28 | 2021-03-16 | 2021-03-16 | COMP | 2021-05-06 | COMP | 2023-07-19 | COMP |  | INPR | 2023-10-06 | COMP | Rule 16 | 13 | 222 | 38 | 553 |  |  | 879
19363 | 2020-04-10 | 2020-05-04 | 2020-10-05 | 2020-10-05 | COMP | 2020-10-22 | COMP | 2020-12-01 | COMP | 2020-11-24 | COMP | 2020-12-17 | COMP | Rule 15/16 | 17 | 109 | 14 | 26 | 0 | 13 | 175
19499 | 2020-04-10 | 2020-05-09 | 2020-06-18 | 2020-06-18 | COMP | 2020-07-07 | COMP | 2020-07-07 | COMP | 2020-08-21 | COMP | 2020-10-06 | COMP | Rule 16 | 21 | 28 | 14 | 1 | 34 | 32 | 126
19594 | 2020-04-10 | 2020-05-14 | 2020-06-12 | 2020-06-12 | COMP | 2020-08-12 | COMP | 2020-09-14 | COMP | 2020-12-29 | COMP | 2021-01-14 | COMP | Rule 16 | 25 | 21 | 44 | 23 | 73 | 12 | 193
19795 | 2020-04-10 | 2020-05-21 | 2020-09-02 | 2020-09-02 | COMP | 2020-12-10 | COMP | 2020-12-10 | COMP | 2020-12-21 | COMP | 2021-01-14 | COMP | Rule 16 | 30 | 74 | 68 | 1 | 8 | 17 | 193
19857 | 2020-04-10 | 2020-05-26 | 2020-08-30 | 2020-08-30 | COMP | 2020-09-14 | COMP | 2020-09-14 | COMP | 2021-01-15 | COMP | 2021-01-23 | COMP | Rule 16 | 32 | 69 | 10 | 1 | 85 | 5 | 198
19888 | 2020-04-10 | 2020-05-27 | 2020-10-09 | 2020-10-09 | COMP | 2021-02-19 | COMP | 2021-07-27 | COMP | 2021-07-22 | COMP | 2021-09-24 | COMP | Rule 15/16 | 33 | 97 | 89 | 111 | 0 | 43 | 369
19907 | 2020-04-10 | 2020-05-27 | 2020-08-26 | 2020-08-26 | COMP | 2020-09-23 | COMP | 2020-09-23 | COMP | 2020-09-28 | COMP | 2020-11-18 | COMP | Rule 16 | 33 | 66 | 20 | 1 | 4 | 37 | 156
19914 | 2020-04-10 | 2020-05-27 | 2020-09-11 | 2020-09-11 | COMP | 2020-09-23 | COMP | 2020-10-26 | COMP | 2020-10-26 | COMP | 2020-11-17 | COMP | Rule 16 | 33 | 77 | 9 | 24 | 1 | 16 | 155
20072 | 2020-04-10 | 2020-06-03 | 2020-07-24 | 2020-07-24 | COMP | 2020-09-22 | COMP | 2020-09-22 | COMP | 2020-09-25 | COMP | 2020-10-20 | COMP | Rule 16 | 38 | 38 | 42 | 1 | 4 | 18 | 136
20074 | 2020-04-10 | 2020-06-03 | 2020-07-31 | 2020-07-31 | COMP | 2020-08-05 | NOTN | 2020-09-04 | COMP | 2020-09-28 | COMP | 2020-10-05 | COMP | Other | 38 | 43 |  | 26 | 16 | 6 | 125
20076 | 2020-04-10 | 2020-06-03 | 2020-08-23 | 2020-08-23 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2020-11-23 | COMP | 2020-11-25 | COMP | Rule 16 | 38 | 58 | 47 | 1 | 18 | 3 | 161
20102 | 2020-04-10 | 2020-06-04 | 2020-07-31 | 2020-07-31 | COMP | 2020-10-23 | COMP | 2021-05-11 | COMP | 2020-11-03 | COMP | 2021-05-26 | COMP | Rule 16 | 39 | 42 | 60 | 136 | 0 | 12 | 285
20444 | 2020-04-10 | 2020-06-20 | 2020-08-26 | 2020-08-26 | COMP | 2020-10-28 | COMP | 2020-12-14 | COMP | 2021-02-18 | COMP | 2021-02-19 | COMP | Rule 16 | 50 | 48 | 45 | 31 | 45 | 2 | 217
20446 | 2020-04-10 | 2020-06-20 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-28 | COMP | 2020-12-14 | COMP | 2021-02-18 | COMP | 2021-02-19 | COMP | Rule 15/16 | 50 | 40 | 11 | 73 | 45 | 2 | 217
20558 | 2020-04-10 | 2020-06-25 | 2020-08-11 | 2020-08-11 | COMP | 2020-08-28 | COMP | 2020-11-11 | COMP | 2020-11-13 | COMP | 2020-12-28 | COMP | Rule 16 | 54 | 34 | 14 | 52 | 2 | 29 | 181
20683 | 2020-04-10 | 2020-07-01 | 2020-09-22 | 2020-09-29 | COMP | 2021-09-20 | COMP | 2021-09-21 | COMP | 2021-05-13 | COMP | 2022-01-21 | COMP | Rule 16 | 58 | 59 | 245 | 2 | 0 | 85 | 450
20794 | 2020-04-10 | 2020-07-06 | 2020-08-11 | 2020-08-11 | COMP | 2020-10-28 | COMP | 2020-10-28 | COMP | 2020-12-16 | COMP | 2020-11-18 | COMP | Rule 16 | 61 | 27 | 56 | 1 | 33 |  | 156
21067 | 2020-04-10 | 2020-07-21 | 2020-09-23 | 2022-11-08 | COMP | 2023-09-29 | COMP | 2023-09-29 | COMP | 2023-10-17 | COMP | 2023-12-05 | COMP | Rule 16 | 72 | 46 | 223 | 1 | 13 | 33 | 918
21161 | 2020-04-10 | 2020-07-23 | 2021-02-10 | 2021-02-12 | COMP | 2021-03-01 | COMP | 2021-05-04 | COMP | 2023-12-04 | INPR | 2021-06-24 | COMP | Rule 16 | 74 | 138 | 11 | 47 |  |  | 305
22325 | 2020-04-10 | 2020-09-20 | 2020-11-30 | 2020-11-30 | COMP | 2021-01-12 | COMP | 2021-04-20 | COMP | 2021-04-19 | COMP | 2021-05-17 | COMP | Rule 16 | 114 | 48 | 30 | 69 | 0 | 20 | 278
19575 | 2020-04-11 | 2020-05-13 | 2020-07-20 | 2020-07-20 | COMP | 2020-08-19 | COMP | 2020-08-19 | COMP | 2021-07-03 | COMP | 2021-08-24 | COMP | Rule 16 | 23 | 48 | 23 | 1 | 219 | 36 | 346
21404 | 2020-04-11 | 2020-08-04 | 2020-09-23 | 2020-09-23 | COMP | 2020-11-30 | COMP | 2021-01-08 | COMP | 2021-06-11 | COMP | 2021-07-15 | COMP | Rule 16 | 81 | 36 | 46 | 28 | 108 | 24 | 318
22409 | 2020-04-11 | 2020-09-23 | 2020-11-25 | 2020-11-25 | COMP | 2020-12-11 | COMP | 2020-12-07 | COMP | 2021-03-08 | COMP | 2021-04-12 | COMP | Rule 16 | 116 | 45 | 11 |  | 62 | 26 | 252
19539 | 2020-04-12 | 2020-05-11 | 2020-07-27 | 2020-07-27 | COMP | 2020-08-12 | COMP | 2020-08-12 | COMP | 2020-12-12 | COMP | 2021-01-12 | COMP | Rule 15/16 | 21 | 55 | 13 | 1 | 84 | 20 | 190
20400 | 2020-04-12 | 2020-06-18 | 2020-08-05 | 2020-08-05 | COMP | 2020-09-16 | COMP | 2020-10-03 | COMP | 2020-10-14 | COMP | 2020-11-12 | COMP | Rule 15/16 | 48 | 35 | 30 | 13 | 8 | 21 | 151
21468 | 2020-04-12 | 2020-08-07 | 2020-12-28 | 2020-12-28 | COMP | 2021-02-16 | COMP | 2021-03-03 | COMP | 2021-05-11 | COMP | 2021-09-01 | COMP | Rule 16 | 84 | 97 | 34 | 12 | 50 | 80 | 352
21797 | 2020-04-12 | 2020-08-26 | 2020-10-08 | 2020-10-08 | COMP | 2020-11-17 | COMP | 2021-01-19 | COMP | 2021-02-02 | COMP | 2021-03-30 | COMP | Rule 16 | 97 | 31 | 28 | 41 | 11 | 40 | 243
22418 | 2020-04-12 | 2020-09-23 | 2021-02-03 | 2021-02-03 | COMP | 2021-02-12 | COMP | 2021-03-29 | COMP | 2021-06-29 | COMP | 2021-08-30 | COMP | Rule 16 | 116 | 90 | 8 | 31 | 66 | 44 | 350
18934 | 2020-04-13 | 2020-04-13 | 2020-07-24 | 2020-07-24 | COMP | 2021-04-16 | COMP | 2021-12-08 | COMP | 2023-01-20 | COMP | 2023-04-24 | COMP | Rule 16 | 1 | 74 | 183 | 163 | 281 | 66 | 763
19099 | 2020-04-13 | 2020-04-21 | 2020-08-14 | 2020-08-14 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2020-08-25 | COMP | 2020-10-28 | COMP | Rule 16 | 7 | 83 | 6 | 1 | 3 | 46 | 141
19249 | 2020-04-13 | 2020-04-28 | 2020-09-29 | 2020-09-29 | COMP | 2021-02-01 | COMP | 2021-02-01 | COMP | 2023-11-13 | INPR | 2021-02-24 | COMP | Rule 15/16 | 12 | 109 | 84 | 1 |  |  | 219
19636 | 2020-04-13 | 2020-05-15 | 2020-08-27 | 2020-08-27 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2021-08-10 | COMP | 2021-09-07 | COMP | Rule 16 | 25 | 74 | 45 | 1 | 195 | 20 | 355
19836 | 2020-04-13 | 2020-05-26 | 2020-07-31 | 2020-07-31 | COMP | 2020-12-08 | COMP | 2020-12-08 | COMP | 2020-12-08 | COMP | 2021-01-01 | COMP | Rule 16 | 31 | 49 | 89 | 1 | 1 | 17 | 183
19926 | 2020-04-13 | 2020-05-28 | 2020-08-07 | 2020-08-07 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2020-12-22 | COMP | 2021-03-12 | COMP | Rule 15/16 | 33 | 52 | 94 | 1 | 1 | 55 | 231
20118 | 2020-04-13 | 2020-06-06 | 2020-07-07 | 2020-07-07 | COMP | 2020-08-04 | COMP | 2020-08-14 | COMP | 2021-10-23 | INPR | 2020-09-12 | COMP | Rule 16 | 39 | 22 | 21 | 9 |  |  | 108
20123 | 2020-04-13 | 2020-06-05 | 2020-07-25 | 2020-07-25 | COMP | 2020-07-30 | COMP | 2020-10-05 | COMP | 2021-02-02 | COMP | 2021-04-08 | COMP | Rule 16 | 39 | 36 | 4 | 47 | 81 | 47 | 250
20151 | 2020-04-13 | 2020-06-08 | 2020-06-26 | 2020-06-26 | COMP | 2020-07-24 | COMP | 2020-07-24 | COMP | 2020-08-24 | COMP | 2020-09-03 | COMP | Rule 16 | 40 | 15 | 21 | 1 | 22 | 9 | 103
20153 | 2020-04-13 | 2020-06-08 | 2020-08-04 | 2020-08-20 | COMP | 2020-11-13 | COMP | 2020-11-13 | COMP | 2021-11-19 | COMP | 2022-01-18 | COMP | Rule 15/16 | 40 | 42 | 60 | 1 | 256 | 40 | 446
20212 | 2020-04-13 | 2020-06-11 | 2020-09-03 | 2021-02-12 | COMP | 2021-03-05 | COMP | 2021-05-17 | COMP | 2021-05-10 | COMP | 2021-06-10 | COMP | Rule 16 | 43 | 61 | 15 | 52 | 0 | 18 | 294
20466 | 2020-04-13 | 2020-06-22 | 2020-08-11 | 2020-08-11 | COMP | 2020-10-06 | COMP | 2020-10-06 | COMP | 2021-10-27 | COMP | 2021-10-29 | COMP | Rule 16 | 50 | 37 | 40 | 1 | 267 | 3 | 393
20537 | 2020-04-13 | 2020-06-25 | 2020-08-13 | 2020-08-13 | COMP | 2020-10-15 | COMP | 2020-10-15 | COMP | 2020-11-13 | COMP | 2020-12-11 | COMP | Rule 16 | 53 | 36 | 45 | 1 | 21 | 19 | 170
20574 | 2020-04-13 | 2020-06-26 | 2021-11-09 | 2022-09-08 | COMP | 2022-09-21 | COMP | 2022-05-23 | COMP | 2023-07-21 | COMP | 2023-08-18 | COMP | Rule 15/16 | 54 | 347 | 10 |  | 291 | 21 | 844
20575 | 2020-04-13 | 2020-06-26 | 2021-10-13 | 2023-02-07 | COMP | 2023-03-07 | COMP | 2022-03-22 | COMP | 2023-07-21 | COMP | 2023-08-18 | COMP | Rule 16 | 54 | 328 | 20 |  | 335 | 21 | 844
20685 | 2020-04-13 | 2020-07-01 | 2020-08-04 | 2020-08-04 | COMP | 2020-11-19 | COMP | 2020-11-19 | COMP | 2020-11-16 | COMP | 2020-12-18 | COMP | Rule 16 | 57 | 25 | 76 | 1 | 0 | 20 | 175
21033 | 2020-04-13 | 2020-07-20 | 2020-10-02 | 2020-10-02 | COMP | 2020-10-13 | COMP | 2020-10-13 | COMP | 2021-02-02 | COMP | 2021-03-04 | COMP | Rule 16 | 70 | 54 | 8 | 1 | 75 | 22 | 225
21317 | 2020-04-13 | 2020-07-31 | 2020-09-10 | 2020-09-10 | COMP | 2020-12-07 | COMP | 2020-12-07 | COMP | 2021-10-18 | COMP | 2021-10-27 | COMP | Rule 16 | 79 | 29 | 60 | 1 | 219 | 8 | 391
21739 | 2020-04-13 | 2020-08-23 | 2020-11-02 | 2022-03-23 | COMP | 2022-08-19 | COMP | 2022-11-22 | COMP | 2022-10-17 | COMP | 2023-02-07 | COMP | Rule 16 | 94 | 50 | 105 | 66 | 0 | 51 | 710
19007 | 2020-04-14 | 2020-04-16 | 2020-06-16 | 2020-06-16 | COMP | 2020-06-16 | NOTN | 2020-06-16 | COMP | 2022-02-26 | INPR | 2021-02-06 | COMP | Other | 3 | 43 |  | 1 |  |  | 206
19008 | 2020-04-14 | 2020-04-16 | 2020-06-11 | 2020-06-20 | COMP | 2020-07-03 | NOTN | 2020-07-03 | COMP | 2020-09-29 | COMP | 2020-10-14 | COMP | Other | 3 | 40 |  | 10 | 62 | 12 | 130
19016 | 2020-04-14 | 2020-04-17 | 2020-07-31 | 2020-07-31 | COMP | 2020-10-23 | COMP | 2021-01-20 | COMP | 2021-01-26 | COMP | 2021-03-10 | COMP | Rule 16 | 4 | 75 | 60 | 58 | 5 | 31 | 228
19022 | 2020-04-14 | 2020-04-17 | 2020-05-15 | 2020-05-15 | COMP | 2020-06-03 | COMP | 2020-07-20 | COMP | 2020-08-21 | COMP | 2020-10-20 | COMP | Rule 16 | 4 | 21 | 13 | 34 | 25 | 42 | 134
19097 | 2020-04-14 | 2020-04-21 | 2020-08-13 | 2020-08-13 | COMP | 2021-04-16 | COMP | 2021-04-20 | COMP | 2022-02-25 | COMP | 2022-04-25 | COMP | Rule 16 | 6 | 82 | 169 | 3 | 216 | 42 | 513
19115 | 2020-04-14 | 2020-04-21 | 2020-07-27 | 2020-07-27 | COMP | 2020-10-21 | COMP | 2020-10-21 | COMP | 2021-04-20 | COMP | 2021-06-01 | COMP | Rule 16 | 6 | 69 | 62 | 1 | 123 | 30 | 286
19160 | 2020-04-14 | 2020-04-23 | 2020-06-01 | 2020-06-01 | COMP | 2020-06-04 | COMP | 2020-06-04 | COMP | 2020-12-15 | COMP | 2020-12-30 | COMP | Rule 16 | 8 | 27 | 4 | 1 | 135 | 11 | 181
19229 | 2020-04-14 | 2020-04-27 | 2020-09-04 | 2020-09-04 | COMP | 2021-01-25 | COMP | 2021-01-26 | COMP | 2021-01-26 | COMP | 2021-03-17 | COMP | Rule 15/16 | 10 | 94 | 95 | 2 | 1 | 36 | 233
19340 | 2020-04-14 | 2020-05-01 | 2020-09-09 | 2020-09-18 | COMP | 2020-10-16 | COMP | 2020-12-01 | COMP | 2021-02-10 | COMP | 2021-03-24 | COMP | Rule 16 | 14 | 92 | 21 | 30 | 49 | 30 | 238
19442 | 2020-04-14 | 2020-05-06 | 2020-11-04 | 2020-11-04 | COMP | 2020-11-12 | COMP | 2020-12-29 | COMP | 2020-12-08 | COMP | 2021-02-09 | COMP | Rule 16 | 17 | 129 | 6 | 31 | 0 | 29 | 208
19616 | 2020-04-14 | 2020-05-15 | 2020-07-02 | 2021-04-29 | COMP | 2021-05-05 | COMP | 2021-07-12 | COMP | 2021-05-05 | COMP | 2021-08-16 | COMP | Rule 16 | 24 | 34 | 5 | 47 | 0 | 26 | 339
19987 | 2020-04-14 | 2020-06-02 | 2020-06-25 | 2020-07-28 | COMP | 2022-01-31 | REQD | 2020-09-09 | COMP | 2022-01-31 | INPR | 2020-09-23 | COMP | Rule 16 | 35 | 18 |  | 31 |  |  | 115
20087 | 2020-04-14 | 2020-06-04 | 2020-08-23 | 2020-08-23 | COMP | 2020-09-01 | COMP | 2020-10-06 | COMP | 2020-12-02 | COMP | 2021-01-07 | COMP | Rule 16 | 37 | 57 | 7 | 25 | 39 | 25 | 186
20226 | 2020-04-14 | 2020-06-10 | 2020-10-08 | 2020-10-08 | COMP | 2021-02-16 | COMP | 2021-02-16 | COMP | 2021-02-23 | COMP | 2021-03-24 | COMP | Rule 15/16 | 41 | 86 | 87 | 1 | 6 | 22 | 238
20305 | 2020-04-14 | 2020-06-18 | 2021-01-03 | 2021-01-03 | COMP | 2021-01-26 | COMP | 2021-01-26 | COMP | 2021-03-02 | COMP | 2021-04-06 | COMP | Rule 15/16 | 47 | 136 | 16 | 1 | 25 | 26 | 247
20335 | 2020-04-14 | 2020-06-16 | 2020-07-24 | 2020-10-21 | COMP | 2021-01-04 | COMP | 2021-01-05 | COMP | 2020-09-25 | COMP | 2021-02-17 | COMP | Rule 16 | 45 | 29 | 49 | 2 | 0 | 30 | 213
20383 | 2020-04-14 | 2020-06-18 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-29 | NOTN | 2020-08-29 | COMP | 2022-01-31 | INPR | 2020-11-02 | COMP | Rule 16 | 47 | 6 |  | 47 |  |  | 143
20384 | 2020-04-14 | 2020-06-18 | 2020-06-29 | 2020-06-29 | COMP | 2020-06-30 | NOTN | 2020-06-30 | COMP | 2023-04-30 | INPR | 2021-12-02 | COMP | Rule 16 | 47 | 8 |  | 2 |  |  | 413
20406 | 2020-04-14 | 2020-06-18 | 2020-06-25 | 2020-06-25 | COMP | 2020-08-29 | NOTN | 2020-08-29 | COMP | 2022-01-31 | INPR | 2020-11-02 | COMP | Rule 16 | 47 | 6 |  | 47 |  |  | 143
20407 | 2020-04-14 | 2020-06-18 | 2020-07-19 | 2020-07-19 | COMP | 2022-03-29 | COMP | 2022-03-28 | COMP | 2022-06-27 | COMP | 2022-07-18 | COMP | Rule 16 | 47 | 22 | 426 |  | 64 | 15 | 570
20771 | 2020-04-14 | 2020-07-07 | 2020-10-19 | 2020-10-19 | COMP | 2020-10-21 | COMP | 2020-10-22 | COMP | 2020-12-21 | COMP | 2021-01-07 | COMP | Rule 16 | 60 | 74 | 3 | 2 | 40 | 12 | 186
20910 | 2020-04-14 | 2020-07-14 | 2020-08-24 | 2020-09-23 | COMP | 2020-10-06 | COMP | 2021-04-22 | COMP | 2020-11-19 | COMP | 2021-05-27 | COMP | Rule 16 | 65 | 30 | 10 | 136 | 0 | 26 | 284
21078 | 2020-04-14 | 2020-07-21 | 2020-10-12 | 2020-10-12 | COMP | 2020-11-18 | COMP | 2020-11-30 | COMP | 2023-05-09 | COMP | 2023-05-19 | COMP | Rule 15/16 | 70 | 59 | 27 | 7 | 614 | 9 | 781
21395 | 2020-04-14 | 2020-08-04 | 2020-12-08 | 2020-12-08 | COMP | 2021-05-25 | COMP | 2021-05-25 | COMP | 2022-01-10 | COMP | 2022-02-23 | COMP | Rule 15/16 | 80 | 87 | 117 | 1 | 159 | 31 | 470
22006 | 2020-04-14 | 2020-09-08 | 2020-10-23 | 2020-10-23 | COMP | 2021-04-21 | NOTN | 2021-04-21 | COMP | 2021-05-11 | COMP | 2021-08-02 | COMP | Other | 104 | 34 |  | 122 | 15 | 58 | 329
18965 | 2020-04-15 | 2020-04-15 | 2020-06-25 | 2020-06-25 | COMP | 2020-11-03 | COMP | 2021-01-20 | COMP | 2020-11-30 | COMP | 2021-03-11 | COMP | Rule 15/16 | 1 | 51 | 93 | 51 | 0 | 36 | 228
18993 | 2020-04-15 | 2020-04-16 | 2020-10-29 | 2021-04-09 | COMP | 2020-11-16 | NOTN | 2021-07-02 | COMP | 2021-07-02 | COMP | 2021-09-16 | COMP | Other | 2 | 139 |  | 60 | 1 | 53 | 360
19106 | 2020-04-15 | 2020-04-21 | 2020-05-14 | 2020-06-01 | COMP | 2020-08-21 | COMP | 2020-08-21 | COMP | 2020-08-31 | COMP | 2020-10-08 | COMP | Rule 16 | 5 | 18 | 60 | 1 | 7 | 28 | 125
19117 | 2020-04-15 | 2020-04-22 | 2020-07-24 | 2020-07-24 | COMP | 2020-08-06 | COMP | 2020-08-24 | COMP | 2020-09-18 | COMP | 2020-11-05 | COMP | Rule 16 | 6 | 67 | 10 | 13 | 19 | 35 | 145
19333 | 2020-04-15 | 2020-04-30 | 2020-10-07 | 2020-12-09 | COMP | 2021-01-06 | COMP | 2021-01-06 | COMP | 2021-01-20 | COMP | 2021-03-16 | COMP | Rule 16 | 12 | 113 | 19 | 1 | 10 | 39 | 231
19385 | 2020-04-15 | 2020-05-05 | 2020-08-07 | 2020-08-07 | COMP | 2020-09-01 | COMP | 2020-09-02 | COMP | 2020-11-13 | COMP | 2020-11-20 | COMP | Rule 16 | 15 | 68 | 18 | 2 | 51 | 6 | 155
19484 | 2020-04-15 | 2020-05-08 | 2020-08-10 | 2020-08-10 | COMP | 2020-08-17 | COMP | 2020-09-29 | COMP | 2020-10-02 | COMP | 2020-11-03 | COMP | Rule 16 | 18 | 66 | 6 | 31 | 4 | 23 | 143
19696 | 2020-04-15 | 2020-05-18 | 2021-01-15 | 2021-01-15 | COMP | 2021-01-25 | COMP | 2021-02-23 | COMP | 2023-12-04 | INPR | 2021-03-26 | COMP | Rule 16 | 24 | 168 | 6 | 21 |  |  | 239
19801 | 2020-04-15 | 2020-05-21 | 2020-10-10 | 2020-10-10 | COMP | 2020-10-30 | COMP | 2020-11-19 | COMP | 2020-12-02 | COMP | 2020-12-24 | COMP | Rule 16 | 27 | 100 | 15 | 14 | 8 | 17 | 177
19807 | 2020-04-15 | 2020-05-22 | 2020-06-17 | 2020-06-17 | COMP | 2020-07-03 | COMP | 2020-07-14 | COMP | 2020-07-03 | COMP | 2020-09-04 | COMP | Rule 15/16 | 28 | 18 | 13 | 8 | 0 | 39 | 102
20007 | 2020-04-15 | 2020-06-01 | 2020-07-07 | 2020-07-07 | COMP | 2020-09-11 | COMP | 2020-09-11 | COMP | 2020-10-22 | COMP | 2021-01-22 | COMP | Rule 16 | 33 | 27 | 48 | 1 | 30 | 61 | 195
20088 | 2020-04-15 | 2020-06-03 | 2020-08-03 | 2020-08-03 | COMP | 2020-09-16 | COMP | 2020-09-16 | COMP | 2020-12-28 | COMP | 2021-01-15 | COMP | Rule 16 | 35 | 44 | 32 | 1 | 70 | 14 | 191
20110 | 2020-04-15 | 2020-06-04 | 2020-07-09 | 2020-08-04 | COMP | 2020-09-09 | COMP | 2020-09-09 | COMP | 2020-09-15 | COMP | 2020-09-28 | COMP | Rule 16 | 36 | 26 | 26 | 1 | 5 | 10 | 117
20159 | 2020-04-15 | 2020-06-08 | 2020-06-29 | 2020-06-29 | COMP | 2020-07-01 | NOTN | 2020-07-02 | COMP | 2020-07-02 | COMP | 2020-07-30 | COMP | Other | 38 | 16 |  | 4 | 1 | 21 | 76
20200 | 2020-04-15 | 2020-06-09 | 2020-08-13 | 2020-08-13 | COMP | 2020-09-23 | COMP | 2021-01-22 | COMP | 2020-12-18 | COMP | 2021-02-19 | COMP | Rule 16 | 39 | 48 | 29 | 82 | 0 | 20 | 214
20526 | 2020-04-15 | 2020-06-24 | 2020-07-15 | 2020-07-15 | COMP | 2020-08-06 | COMP | 2020-08-31 | COMP | 2021-08-02 | COMP | 2021-08-30 | COMP | Rule 16 | 50 | 16 | 17 | 18 | 231 | 21 | 348
20637 | 2020-04-15 | 2020-06-30 | 2020-09-03 | 2021-03-03 | COMP | 2021-03-12 | COMP | 2021-08-20 | COMP | 2021-08-11 | COMP | 2021-09-21 | COMP | Rule 15/16 | 54 | 48 | 8 | 114 | 0 | 22 | 363
20835 | 2020-04-15 | 2020-07-08 | 2020-08-29 | 2020-08-31 | COMP | 2020-10-29 | COMP | 2020-10-29 | COMP | 2021-05-24 | COMP | 2021-06-08 | COMP | Rule 16 | 60 | 38 | 43 | 1 | 141 | 11 | 290
20856 | 2020-04-15 | 2020-07-09 | 2020-08-19 | 2020-08-19 | COMP | 2021-05-06 | COMP | 2021-05-06 | COMP | 2021-05-20 | COMP | 2021-07-08 | COMP | Rule 16 | 61 | 30 | 179 | 1 | 11 | 34 | 311