41715 | 2023-01-17 | 2023-04-21 | 2023-06-11 | 2023-06-11 | COMP | 2023-08-03 | COMP | 2023-08-03 | COMP | 2023-08-28 | COMP | 2023-10-02 | COMP | Rule 16 | 68 | 35 | 37 | 1 | 18 | 25 | 180
42078 | 2023-01-17 | 2023-06-07 | 2023-09-14 | 2023-09-14 | COMP | 2023-10-12 | COMP | 2023-10-12 | COMP | 2023-10-12 | COMP | 2023-12-12 | COMP | Rule 16 | 100 | 69 | 21 | 1 | 1 | 41 | 228
42201 | 2023-01-17 | 2023-06-30 | 2023-07-21 | 2023-07-21 | COMP | 2023-08-30 | NOTN | 2023-08-30 | COMP | 2023-08-30 | COMP | 2023-10-11 | COMP | Other | 116 | 15 |  | 29 | 1 | 30 | 187
40789 | 2023-01-18 | 2023-01-31 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-18 | COMP | 2023-06-16 | COMP | 2023-09-09 | COMP | 2023-10-02 | COMP | Rule 15/16 | 10 | 62 | 16 | 21 | 58 | 16 | 179
40873 | 2023-01-18 | 2023-02-06 | 2023-04-14 | 2023-09-22 | COMP | 2023-10-04 | COMP | 2023-10-04 | COMP | 2023-10-03 | COMP | 2023-12-14 | COMP | Rule 16 | 14 | 49 | 9 | 1 | 0 | 49 | 229
40914 | 2023-01-18 | 2023-02-07 | 2023-07-26 | 2023-07-26 | COMP | 2023-08-09 | COMP | 2023-08-28 | COMP | 2023-10-05 | COMP | 2023-10-04 | COMP | Rule 15/16 | 15 | 118 | 11 | 14 | 28 |  | 181
41024 | 2023-01-18 | 2023-02-16 | 2023-05-08 | 2023-05-08 | COMP | 2023-05-09 | NOTN | 2023-06-23 | COMP | 2023-07-11 | COMP | 2023-08-16 | COMP | Other | 22 | 57 |  | 33 | 12 | 27 | 147
41074 | 2023-01-18 | 2023-02-22 | 2023-06-09 | 2023-06-09 | COMP | 2023-06-15 | COMP | 2023-08-23 | COMP | 2023-08-28 | COMP | 2023-11-30 | COMP | Rule 16 | 25 | 77 | 5 | 48 | 4 | 65 | 219
41122 | 2023-01-18 | 2023-02-24 | 2023-05-18 | 2023-06-21 | COMP | 2023-06-27 | COMP | 2023-07-06 | COMP | 2023-08-31 | COMP | 2023-10-18 | COMP | Rule 16 | 27 | 60 | 5 | 7 | 41 | 34 | 191
41124 | 2023-01-18 | 2023-02-24 | 2023-05-10 | 2023-05-10 | COMP | 2023-06-01 | COMP | 2023-06-01 | COMP | 2023-08-22 | COMP | 2023-10-09 | COMP | Rule 16 | 27 | 54 | 16 | 1 | 57 | 34 | 184
41132 | 2023-01-18 | 2023-02-25 | 2023-05-04 | 2023-05-04 | COMP | 2023-06-16 | COMP | 2023-06-22 | COMP | 2023-06-30 | COMP | 2023-12-01 | COMP | Rule 16 | 27 | 49 | 31 | 4 | 7 | 106 | 220
41195 | 2023-01-18 | 2023-03-01 | 2023-04-19 | 2023-05-26 | COMP | 2023-06-16 | COMP | 2023-06-16 | COMP | 2023-07-17 | COMP | 2023-08-07 | COMP | Rule 16 | 30 | 36 | 15 | 1 | 20 | 16 | 140
41206 | 2023-01-18 | 2023-03-02 | 2023-04-18 | 2023-04-18 | COMP | 2023-05-30 | COMP | 2023-09-07 | COMP | 2023-09-23 | COMP | 2023-11-02 | COMP | Rule 16 | 31 | 34 | 30 | 70 | 12 | 29 | 202
41260 | 2023-01-18 | 2023-03-08 | 2023-04-20 | 2023-04-24 | COMP | 2023-07-14 | COMP | 2023-07-14 | COMP | 2023-07-14 | COMP | 2023-08-25 | COMP | Rule 16 | 35 | 32 | 57 | 1 | 1 | 31 | 154
41311 | 2023-01-18 | 2023-03-13 | 2023-06-14 | 2023-06-14 | COMP | 2023-06-26 | COMP | 2023-06-26 | COMP | 2023-06-26 | COMP | 2023-08-11 | COMP | Rule 16 | 38 | 67 | 8 | 1 | 1 | 34 | 144
41324 | 2023-01-18 | 2023-03-14 | 2023-05-17 | 2023-05-17 | COMP | 2023-07-19 | COMP | 2023-08-01 | COMP | 2023-12-04 | COMP | 2023-09-29 | COMP | Rule 16 | 39 | 47 | 43 | 10 | 86 |  | 178
41420 | 2023-01-18 | 2023-03-23 | 2023-06-21 | 2023-06-21 | COMP | 2023-06-28 | COMP | 2023-08-23 | COMP | 2023-09-15 | COMP | 2023-09-19 | COMP | Rule 16 | 46 | 63 | 6 | 40 | 17 | 3 | 170
40878 | 2023-01-19 | 2023-02-06 | 2023-05-08 | 2023-05-08 | COMP | 2023-05-30 | COMP | 2023-05-30 | COMP | 2023-07-03 | COMP | 2023-07-31 | COMP | Rule 15/16 | 13 | 65 | 16 | 1 | 24 | 20 | 134
40918 | 2023-01-19 | 2023-02-08 | 2023-03-09 | 2023-03-09 | COMP | 2023-03-14 | COMP | 2023-03-14 | COMP | 2023-05-18 | COMP | 2023-06-02 | COMP | Rule 16 | 15 | 21 | 4 | 1 | 48 | 11 | 95
40973 | 2023-01-19 | 2023-02-13 | 2023-04-24 | 2023-04-24 | COMP | 2023-04-24 | NOTN | 2023-05-01 | COMP | 2023-04-24 | COMP | 2023-08-24 | COMP | Other | 18 | 50 |  | 6 | 0 | 81 | 152
41018 | 2023-01-19 | 2023-02-16 | 2023-04-17 | 2023-04-17 | COMP | 2023-05-02 | COMP | 2023-05-17 | COMP | 2023-07-09 | COMP | 2023-08-15 | COMP | Rule 16 | 21 | 42 | 12 | 12 | 35 | 27 | 145
41020 | 2023-01-19 | 2023-02-16 | 2023-05-12 | 2023-05-12 | COMP | 2023-05-26 | COMP | 2023-06-07 | COMP | 2023-06-06 | COMP | 2023-07-05 | COMP | Rule 16 | 21 | 61 | 11 | 8 | 0 | 19 | 116
41083 | 2023-01-19 | 2023-02-22 | 2023-03-27 | 2023-03-27 | COMP | 2023-07-05 | COMP | 2023-07-13 | COMP | 2023-07-12 | COMP | 2023-08-11 | COMP | Rule 16 | 24 | 24 | 70 | 7 | 0 | 22 | 143
41108 | 2023-01-19 | 2023-02-23 | 2023-06-02 | 2023-06-02 | COMP | 2023-06-16 | COMP | 2023-08-23 | COMP | 2023-08-24 | COMP | 2023-11-22 | COMP | Rule 16 | 25 | 71 | 11 | 47 | 2 | 63 | 214
41176 | 2023-01-19 | 2023-02-28 | 2023-03-23 | 2023-03-23 | COMP | 2023-06-22 | COMP | 2023-08-14 | COMP | 2023-09-05 | COMP | 2023-09-22 | COMP | Rule 16 | 28 | 18 | 64 | 37 | 16 | 14 | 172
41201 | 2023-01-19 | 2023-03-02 | 2023-05-12 | 2023-05-12 | COMP | 2023-05-31 | COMP | 2023-09-06 | COMP | 2023-11-27 | COMP | 2023-12-09 | COMP | Rule 16 | 30 | 52 | 13 | 68 | 56 | 10 | 224
41278 | 2023-01-19 | 2023-03-09 | 2023-06-10 | 2023-06-10 | COMP | 2023-08-02 | COMP | 2023-08-30 | COMP | 2023-08-28 | COMP | 2023-11-29 | COMP | Rule 16 | 35 | 66 | 36 | 21 | 0 | 62 | 217
41331 | 2023-01-19 | 2023-03-14 | 2023-04-17 | 2023-04-17 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-08-22 | COMP | Rule 16 | 38 | 25 | 77 | 1 | 1 | 13 | 150
41381 | 2023-01-19 | 2023-03-20 | 2023-06-14 | 2023-06-14 | COMP | 2023-06-20 | COMP | 2023-07-31 | COMP | 2023-08-23 | COMP | 2023-12-12 | COMP | Rule 16 | 42 | 62 | 4 | 29 | 18 | 76 | 226
41459 | 2023-01-19 | 2023-03-27 | 2023-05-10 | 2023-05-10 | COMP | 2023-05-30 | COMP | 2023-07-21 | COMP | 2023-10-20 | COMP | 2023-12-06 | COMP | Rule 16 | 47 | 33 | 14 | 37 | 65 | 31 | 222
41553 | 2023-01-19 | 2023-04-04 | 2023-06-20 | 2023-06-20 | COMP | 2023-07-18 | COMP | 2023-07-18 | COMP | 2023-12-26 | COMP | 2023-10-30 | COMP | Rule 16 | 53 | 54 | 20 | 1 | 111 |  | 198
41883 | 2023-01-19 | 2023-05-11 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-09 | COMP | 2023-06-09 | COMP |  | INPR | 2023-08-16 | COMP | Rule 16 | 80 | 9 | 13 | 1 |  |  | 146
40678 | 2023-01-20 | 2023-01-23 | 2023-04-07 | 2023-04-07 | COMP | 2023-05-09 | COMP | 2023-08-30 | COMP | 2023-11-03 | COMP | 2023-11-14 | COMP | Rule 16 | 2 | 54 | 23 | 79 | 47 | 7 | 207
40719 | 2023-01-20 | 2023-01-25 | 2023-01-27 | 2023-01-27 | COMP | 2023-02-01 | COMP | 2023-02-01 | COMP | 2024-03-04 | INPR | 2023-02-13 | COMP | Rule 16 | 4 | 3 | 4 | 1 |  |  | 17
40736 | 2023-01-20 | 2023-01-25 | 2023-04-14 | 2023-04-14 | COMP | 2023-04-17 | NOTN | 2023-08-07 | COMP | 2023-07-26 | COMP | 2023-09-12 | COMP | Other | 4 | 57 |  | 79 | 0 | 26 | 163
40920 | 2023-01-20 | 2023-02-08 | 2023-03-26 | 2023-03-26 | COMP | 2023-05-26 | COMP | 2023-05-26 | COMP | 2023-06-20 | COMP | 2023-07-07 | COMP | Rule 16 | 14 | 32 | 45 | 1 | 16 | 13 | 117
41036 | 2023-01-20 | 2023-02-16 | 2023-04-20 | 2023-04-20 | COMP | 2023-04-21 | NOTN | 2023-06-06 | COMP | 2023-09-27 | COMP | 2023-12-13 | COMP | Other | 20 | 45 |  | 33 | 79 | 53 | 226
41285 | 2023-01-20 | 2023-03-10 | 2023-04-26 | 2023-04-26 | COMP | 2023-05-19 | COMP | 2023-06-07 | COMP | 2023-06-29 | COMP | 2023-11-02 | COMP | Rule 16 | 35 | 34 | 18 | 13 | 16 | 89 | 200
41338 | 2023-01-20 | 2023-03-16 | 2023-05-06 | 2023-05-06 | COMP | 2023-05-17 | COMP | 2023-05-17 | COMP | 2023-06-01 | COMP | 2023-06-13 | COMP | Rule 16 | 39 | 37 | 8 | 1 | 11 | 9 | 101
41433 | 2023-01-20 | 2023-03-24 | 2023-05-10 | 2023-05-10 | COMP | 2023-07-25 | NOTN | 2023-07-28 | COMP | 2023-08-01 | COMP | 2023-09-12 | COMP | Other | 45 | 34 |  | 55 | 3 | 30 | 163
41531 | 2023-01-20 | 2023-03-31 | 2023-05-24 | 2023-05-24 | COMP | 2023-06-09 | COMP | 2023-06-09 | COMP | 2023-07-17 | COMP | 2023-09-19 | COMP | Rule 16 | 50 | 39 | 12 | 1 | 25 | 46 | 168
41540 | 2023-01-20 | 2023-04-03 | 2023-05-04 | 2023-05-04 | COMP | 2023-05-23 | COMP | 2023-06-26 | COMP | 2023-06-29 | COMP | 2023-09-11 | COMP | Rule 16 | 51 | 24 | 14 | 23 | 4 | 51 | 162
41544 | 2023-01-20 | 2023-04-03 | 2023-05-15 | 2023-05-15 | COMP | 2023-06-27 | COMP | 2023-06-27 | COMP | 2023-07-20 | COMP | 2023-09-13 | COMP | Rule 16 | 51 | 31 | 30 | 1 | 17 | 39 | 164
41840 | 2023-01-20 | 2023-05-05 | 2023-07-21 | 2023-07-21 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-08-22 | COMP | 2023-10-03 | COMP | Rule 16 | 75 | 53 | 11 | 1 | 13 | 30 | 178
41954 | 2023-01-20 | 2023-05-23 | 2023-07-14 | 2023-07-14 | COMP | 2023-08-11 | COMP | 2023-08-11 | COMP | 2023-09-25 | COMP | 2023-10-31 | COMP | Rule 16 | 87 | 36 | 21 | 1 | 31 | 27 | 198
41022 | 2023-01-21 | 2023-02-16 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-08 | COMP | 2023-05-18 | COMP | 2023-10-02 | COMP | 2023-11-03 | COMP | Rule 16 | 19 | 50 | 8 | 9 | 94 | 25 | 200
41776 | 2023-01-22 | 2023-04-27 | 2023-06-01 | 2023-06-01 | COMP | 2023-06-16 | COMP | 2023-06-17 | COMP | 2023-07-25 | COMP | 2023-10-26 | COMP | Rule 16 | 68 | 25 | 12 | 1 | 25 | 67 | 194
40823 | 2023-01-23 | 2023-02-01 | 2023-07-21 | 2023-07-21 | COMP | 2023-08-31 | COMP | 2023-09-14 | COMP | 2023-10-09 | COMP | 2023-11-30 | COMP | Rule 15 | 8 | 119 | 30 | 10 | 18 | 36 | 216
40889 | 2023-01-23 | 2023-02-07 | 2023-02-16 | 2023-03-24 | COMP | 2023-05-01 | COMP | 2023-05-10 | COMP | 2023-03-15 | COMP | 2023-08-11 | COMP | Rule 16 | 12 | 8 | 27 | 8 | 0 | 65 | 141
40994 | 2023-01-23 | 2023-02-14 | 2023-04-09 | 2023-04-09 | COMP | 2023-08-25 | COMP | 2023-08-25 | COMP | 2023-09-20 | COMP | 2023-10-13 | COMP | Rule 16 | 17 | 38 | 97 | 1 | 18 | 18 | 185
41026 | 2023-01-23 | 2023-02-16 | 2023-04-17 | 2023-04-17 | COMP | 2023-04-27 | COMP | 2023-06-26 | COMP | 2023-06-27 | COMP | 2023-10-02 | COMP | Rule 16 | 19 | 42 | 9 | 41 | 2 | 68 | 176
41120 | 2023-01-23 | 2023-02-24 | 2023-05-07 | 2023-05-07 | COMP | 2023-05-17 | COMP | 2023-05-17 | COMP | 2023-05-22 | COMP | 2023-06-19 | COMP | Rule 16 | 24 | 51 | 8 | 1 | 4 | 19 | 103
41144 | 2023-01-23 | 2023-02-26 | 2023-04-19 | 2023-04-19 | COMP | 2023-05-30 | COMP | 2023-06-26 | COMP | 2023-07-31 | COMP | 2023-11-14 | COMP | Rule 16 | 24 | 38 | 29 | 19 | 25 | 75 | 206
41244 | 2023-01-23 | 2023-03-07 | 2023-05-21 | 2023-05-21 | COMP | 2023-06-21 | COMP | 2023-06-21 | COMP | 2023-06-30 | COMP | 2023-08-09 | COMP | Rule 15/16 | 31 | 54 | 21 | 1 | 8 | 28 | 139
41276 | 2023-01-23 | 2023-03-11 | 2023-03-25 | 2023-03-25 | COMP | 2023-08-25 | COMP | 2023-08-25 | COMP | 2023-09-20 | COMP | 2023-10-13 | COMP | Rule 16 | 34 | 10 | 107 | 1 | 18 | 18 | 185
41291 | 2023-01-23 | 2023-03-10 | 2023-04-04 | 2023-04-04 | COMP | 2023-06-08 | COMP | 2023-08-10 | COMP | 2023-08-01 | COMP | 2023-09-12 | COMP | Rule 16 | 34 | 18 | 47 | 44 | 0 | 23 | 162
41353 | 2023-01-23 | 2023-03-16 | 2023-06-21 | 2023-06-21 | COMP | 2023-06-30 | COMP | 2023-08-23 | COMP | 2023-06-22 | COMP | 2023-09-18 | COMP | Rule 16 | 38 | 68 | 8 | 38 | 0 | 18 | 166
41439 | 2023-01-23 | 2023-03-24 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-09 | COMP | 2023-06-09 | COMP | 2023-06-10 | COMP | 2023-08-11 | COMP | Rule 16 | 44 | 45 | 11 | 1 | 1 | 43 | 141
41464 | 2023-01-23 | 2023-03-27 | 2023-05-26 | 2023-05-26 | COMP | 2023-07-13 | COMP | 2023-07-13 | COMP | 2023-08-30 | COMP | 2023-09-15 | COMP | Rule 16 | 45 | 45 | 32 | 1 | 35 | 12 | 165
41530 | 2023-01-23 | 2023-03-31 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-24 | COMP | 2023-05-24 | COMP | 2023-10-30 | COMP | 2023-12-27 | COMP | Rule 16 | 49 | 23 | 17 | 1 | 110 | 39 | 234
41599 | 2023-01-23 | 2023-04-11 | 2023-05-09 | 2023-05-09 | COMP | 2023-06-05 | COMP | 2023-06-05 | COMP | 2023-06-06 | COMP | 2023-07-07 | COMP | Rule 16 | 56 | 21 | 19 | 1 | 2 | 22 | 116
41733 | 2023-01-23 | 2023-04-24 | 2023-06-27 | 2023-06-27 | COMP | 2023-07-13 | COMP | 2023-08-11 | COMP | 2023-08-15 | COMP | 2023-08-25 | COMP | Rule 16 | 65 | 45 | 12 | 22 | 3 | 9 | 151
41739 | 2023-01-23 | 2023-04-24 | 2023-07-04 | 2023-07-04 | COMP | 2023-09-01 | COMP | 2023-09-08 | INPR | 2023-10-24 | COMP | 2023-09-26 | COMP | Rule 16 | 65 | 49 | 43 |  |  |  | 172
41860 | 2023-01-23 | 2023-05-09 | 2023-06-11 | 2023-06-11 | COMP | 2023-06-12 | NOTN | 2023-08-31 | COMP | 2023-09-18 | COMP | 2023-10-10 | COMP | Other | 76 | 23 |  | 57 | 12 | 17 | 182
42162 | 2023-01-23 | 2023-06-21 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-25 | COMP | 2023-08-25 | COMP | 2023-09-29 | COMP | 2023-11-20 | COMP | Rule 16 | 105 | 28 | 20 | 1 | 25 | 36 | 210
42163 | 2023-01-23 | 2023-06-21 | 2023-07-30 | 2023-07-30 | COMP | 2023-09-14 | COMP | 2023-10-03 | COMP | 2023-09-29 | COMP | 2023-11-20 | COMP | Rule 16 | 105 | 27 | 33 | 14 | 0 | 34 | 210
42260 | 2023-01-23 | 2023-07-12 | 2023-08-04 | 2023-08-04 | COMP | 2023-09-11 | COMP | 2023-10-02 | COMP | 2023-10-06 | COMP | 2023-12-05 | COMP | Rule 16 | 119 | 18 | 26 | 16 | 5 | 40 | 219
40730 | 2023-01-24 | 2023-01-25 | 2023-04-26 | 2023-04-26 | COMP | 2023-05-15 | COMP | 2023-05-17 | COMP | 2023-05-23 | COMP | 2023-07-03 | COMP | Rule 16 | 2 | 65 | 14 | 3 | 5 | 28 | 112
40840 | 2023-01-24 | 2023-02-02 | 2023-02-08 | 2023-02-08 | COMP | 2023-02-08 | NOTN | 2023-02-08 | COMP | 2023-02-21 | COMP | 2023-04-07 | COMP | Other | 8 | 5 |  | 1 | 9 | 34 | 53
40944 | 2023-01-24 | 2023-02-09 | 2023-04-13 | 2023-08-24 | COMP | 2023-09-11 | COMP | 2023-09-11 | COMP | 2023-09-12 | COMP | 2023-11-07 | COMP | Rule 16 | 13 | 45 | 12 | 1 | 2 | 41 | 201
41093 | 2023-01-24 | 2023-02-22 | 2023-04-28 | 2023-04-28 | COMP | 2023-05-03 | COMP | 2023-05-19 | COMP | 2023-08-07 | COMP | 2023-09-07 | COMP | Rule 16 | 21 | 48 | 4 | 13 | 54 | 23 | 158
41167 | 2023-01-24 | 2023-02-28 | 2023-05-08 | 2023-05-08 | COMP | 2023-05-18 | COMP | 2023-06-29 | COMP | 2023-06-23 | COMP | 2023-07-21 | COMP | Rule 16 | 25 | 50 | 9 | 29 | 0 | 16 | 125
41225 | 2023-01-24 | 2023-03-06 | 2023-05-09 | 2023-05-09 | COMP | 2023-05-09 | NOTN | 2023-06-29 | COMP | 2023-05-30 | COMP | 2023-08-10 | COMP | Other | 29 | 47 |  | 36 | 0 | 30 | 139
41267 | 2023-01-24 | 2023-03-08 | 2023-05-02 | 2023-05-02 | COMP | 2023-10-06 | COMP | 2023-10-06 | COMP | 2023-09-11 | COMP | 2023-11-20 | COMP | Rule 16 | 31 | 40 | 110 | 1 | 0 | 31 | 209
41283 | 2023-01-24 | 2023-03-09 | 2023-05-24 | 2023-05-24 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-08-09 | COMP | 2023-10-12 | COMP | Rule 16 | 32 | 55 | 52 | 1 | 2 | 46 | 183
41404 | 2023-01-24 | 2023-03-22 | 2023-06-21 | 2023-06-21 | COMP | 2023-06-29 | COMP | 2023-07-25 | COMP | 2023-09-08 | COMP | 2023-10-11 | COMP | Rule 16 | 41 | 64 | 7 | 18 | 33 | 24 | 182
41521 | 2023-01-24 | 2023-03-31 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-15 | COMP | 2023-06-20 | COMP | 2023-05-15 | COMP | 2023-09-09 | COMP | Rule 16 | 48 | 23 | 10 | 25 | 0 | 57 | 159
41527 | 2023-01-24 | 2023-03-31 | 2023-05-03 | 2023-05-03 | COMP | 2023-05-19 | COMP | 2023-07-21 | COMP | 2023-07-09 | COMP | 2023-08-24 | COMP | Rule 16 | 48 | 24 | 13 | 43 | 0 | 25 | 149
41554 | 2023-01-24 | 2023-04-04 | 2023-05-03 | 2023-05-03 | COMP | 2023-07-12 | COMP | 2023-08-08 | COMP | 2023-08-23 | COMP | 2023-12-20 | COMP | Rule 16 | 50 | 22 | 48 | 20 | 12 | 82 | 229
41721 | 2023-01-24 | 2023-04-21 | 2023-07-24 | 2023-07-24 | COMP | 2023-08-07 | COMP | 2023-10-10 | COMP |  | INPR | 2023-11-08 | COMP | Rule 16 | 63 | 64 | 11 | 46 |  |  | 202
41757 | 2023-01-24 | 2023-04-26 | 2023-06-26 | 2023-06-26 | COMP | 2023-07-03 | COMP | 2023-10-17 | COMP | 2023-10-19 | COMP | 2023-11-03 | COMP | Rule 16 | 66 | 42 | 6 | 75 | 3 | 12 | 199
41837 | 2023-01-24 | 2023-05-05 | 2023-05-18 | 2023-05-18 | COMP | 2023-06-16 | COMP | 2023-06-16 | COMP | 2023-08-07 | COMP | 2023-09-07 | COMP | Rule 15/16 | 73 | 10 | 21 | 1 | 35 | 23 | 158
42070 | 2023-01-24 | 2023-06-06 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-12 | COMP | 2023-08-15 | COMP | 2023-11-01 | COMP | 2023-12-22 | COMP | Rule 16 | 94 | 23 | 3 | 25 | 56 | 35 | 231
42074 | 2023-01-24 | 2023-06-06 | 2023-07-18 | 2023-07-18 | COMP | 2023-07-24 | COMP | 2023-08-01 | COMP | 2023-10-24 | COMP | 2023-10-27 | COMP | Rule 16 | 94 | 29 | 5 | 7 | 60 | 4 | 194
42112 | 2023-01-24 | 2023-06-12 | 2023-07-12 | 2023-08-31 | COMP | 2023-09-11 | COMP | 2023-10-14 | COMP | 2023-11-01 | COMP | 2023-12-26 | COMP | Rule 16 | 98 | 21 | 7 | 25 | 13 | 36 | 232
42207 | 2023-01-24 | 2023-07-03 | 2023-08-09 | 2023-08-09 | COMP | 2023-08-14 | NOTN | 2023-09-27 | COMP | 2023-11-22 | COMP | 2023-10-18 | COMP | Other | 112 | 27 |  | 35 | 40 |  | 187
40824 | 2023-01-25 | 2023-02-01 | 2023-05-08 | 2023-05-08 | COMP | 2023-06-02 | COMP | 2023-08-29 | COMP | 2023-07-12 | COMP | 2023-12-27 | COMP | Rule 16 | 6 | 68 | 19 | 61 | 0 | 82 | 232
40943 | 2023-01-25 | 2023-02-09 | 2023-04-19 | 2023-04-19 | COMP | 2023-05-02 | COMP | 2023-09-08 | COMP | 2023-06-15 | COMP | 2023-10-24 | COMP | Rule 15/16 | 12 | 49 | 10 | 90 | 0 | 33 | 190
41021 | 2023-01-25 | 2023-02-16 | 2023-05-02 | 2023-05-02 | COMP | 2023-09-07 | COMP | 2023-09-07 | COMP | 2023-09-26 | COMP | 2023-10-12 | COMP | Rule 16 | 17 | 53 | 89 | 1 | 14 | 13 | 182
41114 | 2023-01-25 | 2023-02-23 | 2023-04-02 | 2023-04-02 | COMP | 2023-04-12 | COMP | 2023-04-12 | COMP | 2023-07-17 | COMP | 2023-08-29 | COMP | Rule 16 | 21 | 27 | 8 | 1 | 66 | 32 | 151
41118 | 2023-01-25 | 2023-02-24 | 2023-06-24 | 2023-06-24 | COMP | 2023-07-03 | COMP | 2023-08-07 | COMP | 2023-08-17 | COMP | 2023-09-18 | COMP | Rule 16 | 22 | 84 | 6 | 25 | 9 | 22 | 164
41161 | 2023-01-25 | 2023-02-27 |  |  | REQD |  | REQD |  | REQD |  | REQD | 2023-03-23 | COMP | Unknown | 23 | [5 empty] | 41
41169 | 2023-01-25 | 2023-02-28 | 2023-05-08 |  | REQD | 2023-05-09 | NOTN | 2023-05-16 | COMP | 2023-09-02 | COMP | 2023-11-03 | COMP | Unknown | 24 |  |  |  | 76 | 44 | 198
41348 | 2023-01-25 | 2023-03-16 | 2023-05-06 | 2023-05-06 | COMP | 2023-05-25 | COMP | 2023-06-07 | COMP | 2023-08-02 | COMP | 2023-08-02 | COMP | Rule 16 | 36 | 37 | 14 | 9 | 39 | 1 | 132
41407 | 2023-01-25 | 2023-03-23 | 2023-05-16 | 2023-05-16 | COMP | 2023-05-24 | COMP | 2023-06-16 | COMP | 2023-06-20 | COMP | 2023-08-22 | COMP | Rule 16 | 41 | 39 | 7 | 17 | 2 | 45 | 146
41494 | 2023-01-25 | 2023-03-29 | 2023-04-18 | 2023-04-18 | COMP | 2023-04-28 | COMP | 2023-06-09 | COMP | 2023-05-02 | COMP | 2023-08-01 | COMP | Rule 16 | 45 | 15 | 9 | 30 | 0 | 36 | 131
41512 | 2023-01-25 | 2023-03-30 | 2023-04-13 | 2023-04-13 | COMP | 2023-06-02 | COMP | 2023-06-13 | COMP | 2023-06-13 | COMP | 2023-07-01 | COMP | Rule 16 | 46 | 11 | 36 | 8 | 1 | 13 | 110
41593 | 2023-01-25 | 2023-04-08 | 2023-06-28 | 2023-06-28 | COMP | 2023-07-12 | COMP | 2023-07-12 | COMP | 2023-09-27 | COMP | 2023-10-25 | COMP | Rule 16 | 52 | 56 | 10 | 1 | 55 | 21 | 191
41695 | 2023-01-25 | 2023-04-19 | 2023-06-08 | 2023-06-08 | COMP | 2023-06-21 | COMP | 2023-07-25 | COMP | 2023-08-09 | COMP | 2023-09-28 | COMP | Rule 16 | 60 | 36 | 9 | 24 | 12 | 36 | 172
41963 | 2023-01-25 | 2023-05-23 | 2023-07-03 | 2023-07-03 | COMP | 2023-08-01 | COMP | 2023-08-07 | COMP | 2023-09-05 | COMP | 2023-11-03 | COMP | Rule 16 | 84 | 28 | 21 | 5 | 21 | 44 | 198
42133 | 2023-01-25 | 2023-06-14 | 2023-08-07 | 2023-08-07 | COMP | 2023-10-09 | COMP | 2023-10-09 | COMP | 2023-10-11 | COMP | 2023-11-28 | COMP | Rule 16 | 99 | 37 | 45 | 1 | 3 | 32 | 212
40842 | 2023-01-26 | 2023-02-02 | 2023-03-31 | 2023-03-31 | COMP | 2023-04-28 | COMP | 2023-05-30 | COMP | 2023-08-17 | COMP | 2023-09-22 | COMP | Rule 16 | 6 | 41 | 21 | 22 | 56 | 26 | 167
41029 | 2023-01-26 | 2023-02-16 | 2023-04-27 | 2023-06-13 | COMP | 2023-06-29 | COMP | 2023-06-29 | COMP | 2023-08-04 | COMP | 2023-11-10 | COMP | Rule 16 | 16 | 50 | 12 | 1 | 26 | 69 | 201
41050 | 2023-01-26 | 2023-02-17 | 2023-05-09 | 2023-05-09 | COMP | 2023-09-20 | COMP | 2023-09-20 | COMP | 2023-10-03 | COMP | 2023-11-13 | COMP | Rule 16 | 17 | 57 | 93 | 1 | 10 | 29 | 202
41159 | 2023-01-26 | 2023-02-27 | 2023-05-19 | 2023-05-24 | COMP | 2023-06-02 | COMP | 2023-06-02 | COMP | 2023-10-12 | COMP | 2023-10-14 | COMP | Rule 16 | 22 | 60 | 7 | 1 | 92 | 2 | 182
41248 | 2023-01-26 | 2023-03-07 | 2023-04-28 | 2023-04-28 | COMP | 2023-05-19 | COMP | 2023-05-19 | COMP | 2023-08-16 | COMP | 2023-09-25 | COMP | Rule 16 | 28 | 39 | 16 | 1 | 61 | 28 | 168
41255 | 2023-01-26 | 2023-03-07 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-23 | COMP | 2023-08-07 | COMP | 2023-06-29 | COMP | 2023-10-26 | COMP | Rule 16 | 28 | 74 | 4 | 31 | 0 | 58 | 191
41322 | 2023-01-26 | 2023-03-13 | 2023-04-28 | 2023-04-28 | COMP | 2023-05-11 | COMP | 2023-05-11 | COMP | 2023-11-22 | COMP | 2023-07-26 | COMP | Rule 16 | 32 | 35 | 10 | 1 | 135 |  | 126
41372 | 2023-01-26 | 2023-03-17 | 2023-05-26 | 2023-05-26 | COMP | 2023-10-17 | COMP | 2023-10-17 | COMP | 2024-02-29 | COMP | 2023-12-13 | COMP | Rule 16 | 36 | 51 | 99 | 1 | 91 |  | 222
41472 | 2023-01-26 | 2023-03-27 | 2023-06-29 | 2023-07-19 | COMP | 2023-07-27 | COMP | 2023-10-05 | COMP | 2023-10-10 | COMP | 2023-12-01 | COMP | Rule 16 | 42 | 67 | 7 | 50 | 4 | 36 | 214
41473 | 2023-01-26 | 2023-03-28 | 2023-04-15 | 2023-04-15 | COMP | 2023-04-18 | NOTN | 2023-04-18 | COMP |  | INPR | 2023-07-06 | COMP | Rule 16 | 43 | 14 |  | 2 |  |  | 112
41489 | 2023-01-26 | 2023-03-29 | 2023-06-10 | 2023-06-10 | COMP | 2023-07-10 | COMP | 2023-08-21 | COMP | 2023-07-31 | COMP | 2023-10-02 | COMP | Rule 16 | 44 | 52 | 19 | 31 | 0 | 30 | 173
41566 | 2023-01-26 | 2023-04-05 | 2023-06-07 | 2023-06-14 | COMP | 2023-06-26 | COMP | 2023-07-25 | COMP | 2023-09-19 | COMP | 2023-11-08 | COMP | Rule 16 | 49 | 45 | 8 | 21 | 40 | 37 | 200
41707 | 2023-01-26 | 2023-04-20 | 2023-05-18 | 2023-05-18 | COMP | 2023-06-01 | COMP | 2023-06-28 | COMP | 2023-07-19 | COMP | 2023-08-29 | COMP | Rule 16 | 60 | 21 | 10 | 19 | 15 | 30 | 150
40891 | 2023-01-27 | 2023-02-07 | 2023-02-16 | 2023-02-16 | COMP | 2023-02-16 | NOTN | 2023-05-08 | COMP | 2023-05-31 | COMP | 2023-06-13 | COMP | Other | 8 | 8 |  | 57 | 17 | 10 | 96
40892 | 2023-01-27 | 2023-02-07 | 2023-02-16 | 2023-02-16 | COMP | 2023-02-22 | COMP | 2023-05-02 | COMP | 2023-02-24 | COMP | 2023-06-12 | COMP | Rule 16 | 8 | 8 | 4 | 50 | 0 | 29 | 95
40967 | 2023-01-27 | 2023-02-13 | 2023-03-17 | 2023-03-17 | COMP | 2023-08-22 | COMP | 2023-08-22 | COMP | 2023-10-25 | COMP | 2023-11-28 | COMP | Rule 16 | 12 | 24 | 110 | 1 | 46 | 22 | 210
41139 | 2023-01-27 | 2023-02-27 | 2023-04-25 | 2023-04-25 | COMP | 2023-06-12 | COMP | 2023-06-14 | COMP | 2023-07-31 | COMP | 2023-09-25 | COMP | Rule 16 | 21 | 42 | 34 | 3 | 32 | 40 | 167
41230 | 2023-01-27 | 2023-03-06 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-05 | NOTN | 2023-06-20 | COMP | 2023-08-07 | COMP | 2023-09-05 | COMP | Other | 26 | 42 |  | 34 | 34 | 21 | 153
41387 | 2023-01-27 | 2023-03-20 | 2023-06-05 | 2023-06-05 | COMP | 2023-07-13 | COMP | 2023-07-25 | COMP | 2023-09-21 | COMP | 2023-12-06 | COMP | Rule 16 | 36 | 55 | 27 | 9 | 42 | 52 | 216
41432 | 2023-01-27 | 2023-03-24 | 2023-06-14 | 2023-06-14 | COMP | 2023-09-08 | COMP | 2023-09-08 | COMP | 2023-10-04 | COMP | 2023-11-13 | COMP | Rule 16 | 40 | 58 | 60 | 1 | 19 | 28 | 201
41577 | 2023-01-27 | 2023-04-06 | 2023-05-31 | 2023-05-31 | COMP | 2023-07-20 | COMP | 2023-07-20 | COMP | 2023-07-26 | COMP | 2023-09-06 | COMP | Rule 16 | 49 | 39 | 35 | 1 | 5 | 30 | 154
41632 | 2023-01-27 | 2023-04-13 | 2023-07-17 | 2023-11-22 | COMP | 2023-12-08 | COMP | 2023-08-23 | COMP | 2023-12-13 | COMP | 2023-12-16 | COMP | Rule 16 | 54 | 65 | 11 |  | 77 | 3 | 223
41651 | 2023-01-27 | 2023-04-14 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-06 | NOTN | 2023-07-06 | COMP | 2023-08-21 | COMP | 2023-09-14 | COMP | Other | 55 | 56 |  | 2 | 33 | 18 | 160
41694 | 2023-01-27 | 2023-04-19 | 2023-07-03 | 2023-07-03 | COMP | 2023-07-11 | COMP | 2023-07-19 | COMP | 2023-07-01 | COMP | 2023-10-27 | COMP | Rule 16 | 58 | 52 | 6 | 7 | 0 | 72 | 191
41737 | 2023-01-27 | 2023-04-24 | 2023-06-02 | 2023-06-02 | COMP | 2023-06-08 | COMP | 2023-06-08 | COMP | 2023-07-28 | COMP | 2023-09-08 | COMP | Rule 16 | 61 | 29 | 5 | 1 | 35 | 30 | 156
41104 | 2023-01-28 | 2023-02-23 | 2023-04-19 | 2023-04-19 | COMP | 2023-05-10 | COMP | 2023-06-16 | COMP | 2023-05-17 | COMP | 2023-08-26 | COMP | Rule 16 | 18 | 40 | 16 | 27 | 0 | 49 | 146
41333 | 2023-01-28 | 2023-03-15 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-06 | COMP | 2023-06-06 | COMP | 2023-11-07 | COMP | 2023-11-16 | COMP | Rule 16 | 32 | 50 | 10 | 1 | 108 | 7 | 203
41232 | 2023-01-29 | 2023-03-06 | 2023-06-01 | 2023-06-01 | COMP | 2023-06-26 | COMP | 2023-08-02 | COMP | 2023-08-14 | COMP | 2023-10-10 | COMP | Rule 16 | 25 | 63 | 17 | 27 | 9 | 41 | 177
41450 | 2023-01-29 | 2023-03-27 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-07 | COMP | 2023-06-07 | COMP | 2023-08-04 | COMP | 2023-08-23 | COMP | Rule 16 | 40 | 44 | 9 | 1 | 41 | 14 | 144
41480 | 2023-01-29 | 2023-03-28 | 2023-06-19 | 2023-06-19 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP |  | INPR | 2023-10-21 | COMP | Rule 16 | 41 | 58 | 40 | 1 |  |  | 185
41545 | 2023-01-29 | 2023-04-03 | 2023-05-04 | 2023-05-04 | COMP | 2023-05-12 | COMP | 2023-09-22 | COMP | 2023-09-25 | COMP | 2023-11-30 | COMP | Rule 16 | 45 | 24 | 7 | 92 | 2 | 46 | 211
40814 | 2023-01-30 | 2023-02-01 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-03 | NOTN | 2023-07-12 | COMP | 2023-07-12 | NOTN | 2023-09-20 | COMP | Other | 3 | 61 |  | 52 |  |  | 163
40816 | 2023-01-30 | 2023-02-01 | 2023-02-17 | 2023-02-17 | COMP | 2023-05-17 | COMP | 2023-04-27 | COMP | 2023-07-19 | COMP | 2023-08-10 | COMP | Rule 16 | 3 | 13 | 63 |  | 57 | 17 | 135
40850 | 2023-01-30 | 2023-02-03 | 2023-02-09 | 2023-02-09 | COMP | 2023-02-15 | COMP | 2023-02-15 | COMP | 2023-02-16 | COMP | 2023-04-05 | COMP | Rule 16 | 5 | 5 | 5 | 1 | 2 | 34 | 47
40870 | 2023-01-30 | 2023-02-06 | 2023-05-04 | 2023-05-04 | COMP | 2023-06-07 | COMP | 2023-10-17 | COMP | 2023-10-06 | COMP | 2023-11-27 | COMP | Rule 16 | 6 | 63 | 24 | 92 | 0 | 27 | 208
40953 | 2023-01-30 | 2023-02-10 | 2023-03-04 | 2023-03-04 | COMP | 2023-04-07 | COMP | 2023-04-07 | COMP | 2023-10-24 | COMP | 2023-11-27 | COMP | Other | 10 | 15 | 25 | 1 | 139 | 22 | 208
41041 | 2023-01-30 | 2023-02-17 | 2023-04-07 | 2023-04-07 | COMP | 2023-04-12 | COMP | 2023-07-18 | COMP | 2023-06-14 | COMP | 2023-07-25 | COMP | Rule 16 | 15 | 35 | 4 | 67 | 0 | 6 | 123
41190 | 2023-01-30 | 2023-03-01 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-23 | COMP | 2023-07-10 | COMP | 2023-06-27 | COMP | 2023-10-18 | COMP | Rule 16 | 22 | 62 | 20 | 11 | 0 | 72 | 183
41194 | 2023-01-30 | 2023-03-02 | 2023-05-10 | 2023-05-10 | COMP | 2023-08-18 | COMP | 2023-08-18 | COMP | 2023-08-22 | COMP | 2023-11-01 | COMP | Rule 16 | 23 | 50 | 70 | 1 | 3 | 51 | 193
41214 | 2023-01-30 | 2023-03-04 | 2023-05-15 | 2023-05-15 | COMP | 2023-05-30 | COMP | 2023-07-12 | COMP | 2023-10-17 | COMP | 2023-12-07 | COMP | Rule 16 | 24 | 51 | 11 | 30 | 69 | 35 | 216
41215 | 2023-01-30 | 2023-03-05 | 2023-04-06 | 2023-04-06 | COMP | 2023-08-25 | COMP | 2023-08-25 | COMP | 2023-08-24 | COMP | 2023-10-09 | COMP | Rule 16 | 24 | 24 | 99 | 1 | 0 | 31 | 176
41526 | 2023-01-30 | 2023-03-31 | 2023-04-26 | 2023-04-26 | COMP | 2023-06-01 | COMP | 2023-06-12 | COMP | 2023-06-20 | COMP | 2023-09-22 | COMP | Rule 15/16 | 44 | 19 | 26 | 8 | 6 | 67 | 165
41563 | 2023-01-30 | 2023-04-05 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-07 | COMP | 2023-08-11 | COMP | 2023-08-15 | COMP | 2023-09-08 | COMP | Rule 15/16 | 47 | 55 | 11 | 26 | 3 | 18 | 155
40916 | 2023-01-31 | 2023-02-08 | 2023-04-05 | 2023-04-05 | COMP | 2023-04-11 | COMP | 2023-05-24 | COMP | 2023-06-27 | COMP | 2023-08-15 | COMP | Rule 16 | 7 | 40 | 5 | 32 | 23 | 35 | 137
40939 | 2023-01-31 | 2023-02-09 | 2023-04-24 | 2023-04-24 | COMP | 2023-05-04 | COMP | 2023-07-11 | COMP | 2023-07-11 | COMP | 2023-08-30 | COMP | Rule 16 | 8 | 52 | 9 | 46 | 1 | 37 | 148
40972 | 2023-01-31 | 2023-02-13 | 2023-04-15 | 2023-04-15 | COMP | 2023-05-11 | COMP | 2023-05-12 | COMP | 2023-09-18 | COMP | 2023-09-25 | COMP | Rule 16 | 10 | 44 | 19 | 2 | 88 | 6 | 165
40984 | 2023-01-31 | 2023-02-14 | 2023-04-18 | 2023-04-18 | COMP | 2023-05-08 | COMP | 2023-05-16 | COMP | 2023-11-22 | COMP | 2023-08-07 | COMP | Rule 16 | 11 | 45 | 15 | 7 | 132 |  | 131
41001 | 2023-01-31 | 2023-02-15 | 2023-05-03 | 2023-05-03 | COMP | 2023-05-23 | COMP | 2023-06-05 | COMP | 2023-06-05 | COMP | 2023-07-10 | COMP | Rule 16 | 12 | 55 | 15 | 9 | 1 | 24 | 111
41117 | 2023-01-31 | 2023-02-24 | 2023-05-20 | 2023-05-20 | COMP | 2023-08-14 | COMP | 2023-08-14 | COMP | 2023-08-25 | COMP | 2023-10-10 | COMP | Rule 16 | 18 | 61 | 58 | 1 | 10 | 32 | 176
41231 | 2023-01-31 | 2023-03-06 | 2023-05-09 | 2023-05-09 | COMP | 2023-10-10 | COMP | 2023-10-10 | COMP | 2023-12-04 | COMP | 2023-12-14 | COMP | Rule 16 | 24 | 47 | 107 | 1 | 37 | 9 | 220
41274 | 2023-01-31 | 2023-03-09 | 2023-04-24 | 2023-04-24 | COMP | 2023-06-26 | COMP | 2023-09-12 | COMP | 2023-08-28 | COMP | 2023-11-09 | COMP | Rule 16 | 27 | 33 | 44 | 55 | 0 | 43 | 198
41402 | 2023-01-31 | 2023-03-23 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-07 | COMP | 2023-06-16 | COMP | 2023-06-08 | COMP | 2023-07-14 | COMP | Rule 16 | 37 | 46 | 9 | 8 | 0 | 19 | 115
41426 | 2023-01-31 | 2023-03-24 | 2023-04-25 | 2023-04-25 | COMP | 2023-05-30 | COMP | 2023-05-30 | COMP | 2023-07-18 | COMP | 2023-08-02 | COMP | Rule 16 | 38 | 23 | 25 | 1 | 34 | 12 | 128
41483 | 2023-01-31 | 2023-03-29 | 2023-05-30 | 2023-05-30 | COMP | 2023-06-05 | COMP | 2023-06-05 | INPR |  | REQD | 2023-07-07 | COMP | Rule 16 | 41 | 44 | 5 |  |  |  | 110
41594 | 2023-01-31 | 2023-04-07 | 2023-07-03 | 2023-07-03 | COMP | 2023-09-06 | COMP | 2023-09-29 | COMP | 2023-09-27 | COMP | 2023-11-07 | COMP | Rule 16 | 48 | 60 | 46 | 18 | 0 | 28 | 196
41622 | 2023-01-31 | 2023-04-12 | 2023-05-17 | 2023-05-17 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP |  | INPR | 2023-10-27 | COMP | Rule 16 | 51 | 26 | 56 | 1 |  |  | 189
41681 | 2023-01-31 | 2023-04-18 | 2023-07-04 | 2023-07-04 | COMP | 2023-07-17 | COMP | 2023-08-21 | COMP | 2023-07-10 | COMP | 2023-12-04 | COMP | Rule 16 | 55 | 53 | 9 | 26 | 0 | 72 | 212
41848 | 2023-01-31 | 2023-05-08 | 2023-06-30 | 2023-06-30 | COMP | 2023-08-23 | COMP | 2023-09-08 | COMP | 2023-08-23 | COMP | 2023-10-25 | COMP | Rule 16 | 69 | 38 | 38 | 12 | 0 | 34 | 187
40848 | 2023-02-01 | 2023-02-02 | 2023-03-19 | 2023-03-19 | COMP | 2023-03-24 | NOTN | 2023-05-11 | COMP | 2023-03-24 | COMP | 2023-06-29 | COMP | Other | 2 | 31 |  | 39 | 0 | 34 | 104
40859 | 2023-02-01 | 2023-02-04 | 2023-04-28 | 2023-04-28 | COMP | 2023-10-20 | COMP | 2023-11-02 | COMP | 2023-11-16 | COMP | 2023-12-26 | COMP | Other | 3 | 59 | 122 | 10 | 10 | 26 | 226
41054 | 2023-02-01 | 2023-02-20 | 2023-02-24 | 2023-02-24 | COMP | 2023-04-21 | COMP | 2023-04-21 | COMP | 2023-08-05 | COMP | 2023-05-26 | COMP | Rule 16 | 13 | 4 | 41 | 1 | 73 |  | 82
41178 | 2023-02-01 | 2023-03-01 | 2023-05-20 | 2023-05-20 | COMP | 2023-06-20 | NOTN | 2023-08-25 | COMP | 2023-10-04 | COMP | 2023-10-30 | COMP | Rule 16 | 20 | 58 |  | 67 | 28 | 19 | 189
41208 | 2023-02-01 | 2023-03-03 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-24 | NOTN | 2023-10-16 | COMP | 2023-11-02 | COMP | 2023-11-29 | COMP | Other | 22 | 76 |  | 83 | 14 | 17 | 208
41235 | 2023-02-01 | 2023-03-06 | 2023-04-24 | 2023-04-24 | COMP | 2023-05-18 | COMP | 2023-06-12 | COMP | 2023-06-13 | COMP | 2023-07-25 | COMP | Rule 16 | 23 | 36 | 19 | 17 | 2 | 29 | 121
41252 | 2023-02-01 | 2023-03-07 | 2023-04-26 | 2023-04-26 | COMP | 2023-04-28 | NOTN | 2023-06-14 | COMP | 2023-07-05 | COMP | 2023-08-27 | COMP | Other | 24 | 37 |  | 35 | 14 | 38 | 144
41284 | 2023-02-01 | 2023-03-10 | 2023-05-19 | 2023-05-19 | COMP | 2023-05-20 | NOTN | 2023-07-14 | COMP | 2023-05-20 | COMP | 2023-08-28 | COMP | Other | 27 | 51 |  | 38 | 0 | 32 | 145
41378 | 2023-02-01 | 2023-03-20 | 2023-04-25 | 2023-04-25 | COMP | 2023-05-01 | COMP | 2023-05-01 | COMP | 2023-08-23 | COMP | 2023-09-26 | COMP | Rule 16 | 33 | 27 | 5 | 1 | 80 | 24 | 165
41447 | 2023-02-01 | 2023-03-26 | 2023-05-04 | 2023-05-04 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP | 2023-10-13 | COMP | Rule 15/16 | 37 | 29 | 67 | 1 | 1 | 47 | 178
41638 | 2023-02-01 | 2023-04-13 | 2023-05-21 | 2023-05-21 | COMP | 2023-06-20 | COMP | 2023-06-20 | COMP | 2023-11-15 | COMP | 2023-11-30 | COMP | Rule 16 | 51 | 27 | 20 | 1 | 104 | 10 | 209
41666 | 2023-02-01 | 2023-04-17 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-20 | COMP | 2023-09-08 | COMP | 2023-07-25 | COMP | 2023-10-17 | COMP | Rule 16 | 53 | 55 | 12 | 36 | 0 | 28 | 180
41842 | 2023-02-01 | 2023-05-05 | 2023-06-12 | 2023-06-12 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-09-05 | COMP | 2023-10-17 | COMP | Rule 16 | 67 | 26 | 40 | 1 | 20 | 31 | 180
41962 | 2023-02-01 | 2023-05-23 | 2023-06-08 | 2023-06-08 | COMP | 2023-06-22 | COMP | 2023-07-28 | COMP | 2023-07-27 | COMP | 2023-08-11 | COMP | Rule 16 | 79 | 12 | 10 | 26 | 0 | 11 | 134
42108 | 2023-02-01 | 2023-06-12 | 2023-07-15 | 2023-07-15 | COMP | 2023-08-30 | COMP | 2023-09-21 | COMP |  | INPR | 2023-12-06 | COMP | Rule 16 | 92 | 23 | 33 | 16 |  |  | 213
41016 | 2023-02-02 | 2023-02-16 | 2023-03-24 | 2023-03-24 | COMP | 2023-03-30 | COMP | 2023-05-10 | COMP | 2023-05-11 | COMP | 2023-06-13 | COMP | Rule 16 | 11 | 26 | 5 | 30 | 2 | 23 | 92
41138 | 2023-02-02 | 2023-02-27 | 2023-03-20 | 2023-03-20 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP |  | INPR | 2023-09-28 | COMP | Rule 16 | 17 | 16 | 97 | 1 |  |  | 166
41253 | 2023-02-02 | 2023-03-07 | 2023-04-04 | 2023-04-04 | COMP | 2023-04-12 | COMP | 2023-08-07 | COMP | 2023-09-25 | COMP | 2023-10-21 | COMP | Rule 16 | 23 | 21 | 7 | 81 | 35 | 20 | 182
41363 | 2023-02-02 | 2023-03-16 | 2023-04-08 | 2023-04-08 | COMP | 2023-04-19 | COMP | 2023-05-05 | COMP | 2023-04-19 | COMP | 2023-07-10 | COMP | Rule 16 | 30 | 17 | 8 | 13 | 0 | 44 | 109
41451 | 2023-02-02 | 2023-03-27 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-07 | COMP | 2023-07-24 | COMP | 2023-08-08 | COMP | 2023-08-31 | COMP | Rule 15/16 | 37 | 62 | 11 | 12 | 12 | 18 | 147
41522 | 2023-02-02 | 2023-03-31 | 2023-05-12 | 2023-05-12 | COMP | 2023-05-19 | COMP | 2023-07-10 | COMP | 2023-05-30 | COMP | 2023-07-26 | COMP | Rule 16 | 41 | 31 | 6 | 34 | 0 | 13 | 121
41795 | 2023-02-02 | 2023-04-30 | 2023-06-27 | 2023-06-27 | COMP | 2023-08-03 | COMP | 2023-08-14 | COMP | 2023-09-12 | COMP | 2023-10-03 | COMP | Rule 16 | 61 | 40 | 27 | 8 | 21 | 16 | 169
40886 | 2023-02-03 | 2023-02-07 | 2023-03-31 | 2023-03-31 | COMP | 2023-04-04 | NOTN | 2023-05-25 | COMP | 2023-04-04 | COMP | 2023-06-08 | COMP | Other | 3 | 38 |  | 40 | 0 | 10 | 88
41134 | 2023-02-03 | 2023-02-25 | 2023-05-21 | 2023-05-21 | COMP | 2023-05-31 | COMP | 2023-05-31 | COMP | 2023-11-03 | COMP | 2023-12-08 | COMP | Rule 16 | 15 | 60 | 7 | 1 | 110 | 23 | 213
41170 | 2023-02-03 | 2023-02-28 | 2023-05-12 | 2023-05-31 | COMP | 2023-06-02 | COMP | 2023-06-02 | COMP | 2023-12-06 | COMP | 2023-06-27 | COMP | Rule 16 | 17 | 54 | 3 | 1 | 128 |  | 100
41224 | 2023-02-03 | 2023-03-05 | 2023-06-12 | 2023-06-12 | COMP | 2023-06-21 | COMP | 2023-06-21 | COMP | 2023-06-29 | COMP | 2023-09-06 | COMP | Rule 16 | 20 | 70 | 7 | 1 | 7 | 48 | 149
41295 | 2023-02-03 | 2023-03-10 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-02 | COMP | 2023-05-02 | COMP | 2023-05-16 | COMP | 2023-06-20 | COMP | Rule 16 | 25 | 35 | 4 | 1 | 11 | 24 | 95
41335 | 2023-02-03 | 2023-03-14 | 2023-05-23 | 2023-05-23 | COMP | 2023-05-30 | COMP | 2023-07-28 | COMP | 2023-09-27 | COMP | 2023-11-14 | COMP | Rule 16 | 27 | 51 | 5 | 42 | 43 | 34 | 197
41377 | 2023-02-03 | 2023-03-17 | 2023-05-10 | 2023-05-10 | COMP | 2023-06-26 | COMP | 2023-06-26 | COMP | 2023-06-26 | COMP | 2023-07-11 | COMP | Rule 16 | 30 | 39 | 32 | 1 | 1 | 11 | 109
41385 | 2023-02-03 | 2023-03-20 | 2023-06-28 | 2023-06-28 | COMP | 2023-06-28 | NOTN | 2023-08-14 | COMP | 2023-09-14 | COMP | 2023-11-29 | COMP | Other | 31 | 71 |  | 33 | 23 | 52 | 206
41422 | 2023-02-03 | 2023-03-24 | 2023-05-10 | 2023-05-10 | COMP | 2023-05-17 | COMP | 2023-08-01 | COMP | 2023-08-11 | COMP | 2023-11-14 | COMP | Rule 16 | 35 | 34 | 6 | 52 | 9 | 66 | 197
41427 | 2023-02-03 | 2023-03-24 | 2023-05-06 | 2023-05-06 | COMP | 2023-06-23 | COMP | 2023-06-23 | COMP | 2023-09-11 | COMP | 2023-11-02 | COMP | Rule 16 | 35 | 31 | 33 | 1 | 55 | 39 | 190
41431 | 2023-02-03 | 2023-03-24 | 2023-05-27 | 2023-05-27 | COMP | 2023-06-28 | COMP | 2023-09-25 | COMP | 2023-12-01 | COMP | 2023-12-12 | COMP | Rule 16 | 35 | 46 | 21 | 62 | 47 | 8 | 215
41461 | 2023-02-03 | 2023-03-28 | 2023-06-08 | 2023-06-08 | COMP | 2023-08-21 | COMP | 2023-08-21 | COMP | 2023-10-06 | COMP | 2023-12-19 | COMP | Rule 16 | 37 | 52 | 51 | 1 | 34 | 50 | 220
41555 | 2023-02-03 | 2023-04-04 | 2023-05-04 | 2023-05-04 | COMP | 2023-07-03 | COMP | 2023-07-11 | COMP | 2023-07-05 | COMP | 2023-09-09 | COMP | Rule 16 | 42 | 23 | 41 | 6 | 0 | 43 | 151
41648 | 2023-02-03 | 2023-04-14 | 2023-05-05 | 2023-05-05 | COMP | 2023-05-22 | COMP | 2023-05-22 | COMP | 2023-07-18 | COMP | 2023-08-14 | COMP | Rule 16 | 50 | 16 | 12 | 1 | 39 | 20 | 133
41713 | 2023-02-03 | 2023-04-21 | 2023-06-27 | 2023-06-27 | COMP | 2023-07-25 | COMP | 2023-07-25 | COMP |  | INPR | 2023-08-01 | COMP | Rule 16 | 55 | 46 | 20 | 1 |  |  | 124
41960 | 2023-02-03 | 2023-05-23 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-11 | COMP | 2023-07-11 | COMP | 2023-11-29 | COMP | 2023-12-07 | COMP | Rule 16 | 77 | 29 | 5 | 1 | 98 | 7 | 212
42088 | 2023-02-03 | 2023-06-08 | 2023-07-20 | 2023-07-20 | COMP | 2023-07-27 | COMP | 2023-07-27 | COMP | 2023-08-14 | COMP | 2023-11-08 | COMP | Rule 16 | 88 | 29 | 6 | 1 | 13 | 62 | 194
41263 | 2023-02-04 | 2023-03-08 | 2023-06-24 | 2023-06-24 | COMP | 2023-08-03 | COMP | 2023-08-14 | COMP | 2023-11-03 | COMP | 2023-11-17 | COMP | Rule 16 | 22 | 76 | 28 | 8 | 59 | 10 | 199
41826 | 2023-02-04 | 2023-05-04 | 2023-06-01 | 2023-06-01 | COMP | 2023-08-23 | COMP | 2023-08-24 | COMP | 2023-08-25 | COMP | 2023-10-16 | COMP | Rule 16 | 63 | 20 | 58 | 2 | 2 | 36 | 176
41894 | 2023-02-04 | 2023-05-15 | 2023-06-30 | 2023-06-30 | COMP | 2023-07-11 | COMP | 2023-07-11 | COMP | 2023-07-12 | COMP | 2023-08-07 | COMP | Rule 16 | 70 | 33 | 7 | 1 | 2 | 19 | 127
41588 | 2023-02-05 | 2023-04-07 | 2023-05-21 | 2023-05-21 | COMP | 2023-05-26 | COMP | 2023-05-26 | COMP | 2023-06-26 | COMP | 2023-07-10 | COMP | Rule 16 | 44 | 31 | 5 | 1 | 20 | 10 | 107
41797 | 2023-02-05 | 2023-05-01 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-10 | NOTN | 2023-07-10 | COMP | 2023-08-08 | COMP | 2023-08-15 | COMP | Other | 60 | 48 |  | 1 | 22 | 6 | 133
40897 | 2023-02-06 | 2023-02-07 | 2023-06-23 | 2023-06-23 | COMP | 2023-02-07 | NOTN | 2023-08-09 | COMP |  | INPR | 2023-10-13 | COMP | Other | 2 | 96 |  | 33 |  |  | 175
41226 | 2023-02-06 | 2023-03-06 | 2023-05-21 | 2023-05-21 | COMP | 2023-06-01 | COMP | 2023-06-01 | COMP | 2023-06-01 | COMP | 2023-07-21 | COMP | Rule 16 | 20 | 55 | 8 | 1 | 1 | 35 | 116
41269 | 2023-02-06 | 2023-03-08 | 2023-04-12 | 2023-04-12 | COMP | 2023-04-24 | COMP | 2023-06-20 | COMP | 2023-06-09 | COMP | 2023-09-29 | COMP | Rule 16 | 22 | 26 | 9 | 40 | 0 | 72 | 165
41375 | 2023-02-06 | 2023-03-17 | 2023-06-09 | 2023-06-09 | COMP | 2023-06-15 | COMP | 2023-10-31 | COMP | 2023-06-09 | COMP | 2023-12-13 | COMP | Rule 16 | 29 | 60 | 5 | 96 | 0 | 29 | 215
41443 | 2023-02-06 | 2023-03-25 | 2023-07-17 | 2023-07-17 | COMP | 2023-08-10 | COMP | 2023-08-11 | COMP | 2023-08-10 | COMP | 2023-09-28 | COMP | Rule 16 | 34 | 78 | 19 | 2 | 0 | 34 | 164
41474 | 2023-02-06 | 2023-03-28 | 2023-06-19 | 2023-06-19 | COMP | 2023-07-10 | COMP | 2023-07-10 | COMP | 2023-08-28 | COMP | 2023-09-07 | COMP | Rule 16 | 36 | 58 | 14 | 1 | 36 | 8 | 149
41506 | 2023-02-06 | 2023-03-30 | 2023-07-27 | 2023-07-27 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP | 2023-10-16 | COMP | 2023-11-03 | COMP | Rule 16 | 38 | 83 | 10 | 1 | 48 | 15 | 190
41524 | 2023-02-06 | 2023-03-31 | 2023-04-21 | 2023-04-21 | COMP | 2023-05-23 | COMP | 2023-06-15 | COMP | 2023-08-16 | COMP | 2023-10-23 | COMP | Rule 16 | 39 | 16 | 23 | 17 | 43 | 48 | 181
41576 | 2023-02-06 | 2023-04-06 | 2023-05-02 | 2023-05-02 | COMP | 2023-10-16 | COMP | 2023-10-16 | COMP | 2023-10-17 | COMP | 2023-11-07 | COMP | Rule 16 | 43 | 19 | 116 | 1 | 2 | 16 | 192
41582 | 2023-02-06 | 2023-04-07 | 2023-05-31 | 2023-09-12 | COMP | 2023-09-18 | COMP | 2023-09-18 | COMP | 2023-09-19 | COMP | 2023-10-17 | COMP | Rule 16 | 44 | 38 | 5 | 1 | 2 | 21 | 177
41640 | 2023-02-06 | 2023-04-14 | 2023-05-17 | 2023-05-17 | COMP | 2023-05-31 | COMP | 2023-06-09 | COMP | 2023-05-31 | COMP | 2023-07-25 | COMP | Rule 16 | 49 | 24 | 10 | 8 | 0 | 31 | 118
41656 | 2023-02-06 | 2023-04-14 | 2023-05-10 | 2023-05-10 | COMP | 2023-05-19 | NOTN | 2023-05-23 | COMP | 2023-05-23 | COMP | 2023-08-11 | COMP | Other | 49 | 19 |  | 10 | 1 | 56 | 131
41736 | 2023-02-06 | 2023-04-24 | 2023-06-12 | 2023-06-12 | COMP | 2023-06-15 | COMP | 2023-06-15 | COMP | 2023-11-13 | COMP | 2023-12-28 | COMP | Rule 16 | 55 | 35 | 4 | 1 | 104 | 31 | 225
41949 | 2023-02-06 | 2023-05-22 | 2023-08-08 | 2023-08-08 | COMP | 2023-08-17 | COMP | 2023-09-26 | COMP | 2023-08-11 | COMP | 2023-11-08 | COMP | Rule 16 | 75 | 54 | 8 | 28 | 0 | 32 | 193
41013 | 2023-02-07 | 2023-02-16 | 2023-05-05 | 2023-05-05 | COMP | 2023-05-16 | COMP | 2023-05-16 | COMP |  | INPR | 2023-06-08 | COMP | Rule 16 | 8 | 56 | 8 | 1 |  |  | 86
41042 | 2023-02-07 | 2023-02-17 | 2023-04-19 | 2023-04-19 | COMP | 2023-04-25 | COMP | 2023-05-04 | COMP | 2023-05-22 | COMP | 2023-06-22 | COMP | Rule 16 | 9 | 43 | 5 | 8 | 13 | 22 | 95
41094 | 2023-02-07 | 2023-02-22 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-05 | COMP | 2023-06-20 | COMP | 2023-08-07 | COMP | 2023-08-16 | COMP | Rule 16 | 11 | 50 | 4 | 31 | 34 | 8 | 133
41175 | 2023-02-07 | 2023-02-28 | 2023-04-16 | 2023-04-16 | COMP | 2023-09-08 | COMP | 2023-10-13 | COMP | 2023-10-16 | COMP | 2023-12-14 | COMP | Rule 16 | 15 | 34 | 101 | 26 | 2 | 41 | 215
41189 | 2023-02-07 | 2023-03-01 | 2023-04-11 | 2023-04-11 | COMP | 2023-04-17 | COMP | 2023-04-26 | COMP | 2023-05-22 | COMP | 2023-07-29 | COMP | Rule 16 | 16 | 30 | 5 | 8 | 19 | 47 | 120
41205 | 2023-02-07 | 2023-03-03 | 2023-05-06 | 2023-05-06 | COMP | 2023-07-05 | COMP | 2023-07-05 | COMP | 2023-09-01 | COMP | 2023-11-28 | COMP | Rule 16 | 18 | 46 | 40 | 1 | 43 | 59 | 203
41242 | 2023-02-07 | 2023-03-06 | 2023-04-22 | 2023-04-22 | COMP | 2023-05-17 | COMP | 2023-05-17 | COMP | 2023-07-11 | COMP | 2023-09-02 | COMP | Rule 16 | 19 | 35 | 18 | 1 | 37 | 39 | 145
41425 | 2023-02-07 | 2023-03-24 | 2023-05-23 | 2023-08-14 | COMP | 2023-08-14 | NOTN | 2023-09-08 | COMP | 2023-06-06 | COMP | 2023-11-10 | COMP | Other | 33 | 43 |  | 19 | 0 | 45 | 193
41470 | 2023-02-07 | 2023-03-28 | 2023-05-22 | 2023-05-22 | COMP | 2023-05-31 | COMP | 2023-06-21 | COMP | 2023-08-16 | COMP | 2023-09-21 | COMP | Rule 16 | 35 | 40 | 7 | 15 | 40 | 26 | 158
41507 | 2023-02-07 | 2023-03-30 | 2023-06-29 | 2023-08-21 | COMP | 2023-10-19 | COMP | 2023-10-19 | COMP |  | INPR | 2023-12-17 | COMP | Rule 16 | 37 | 64 | 43 | 1 |  |  | 216
41514 | 2023-02-07 | 2023-03-30 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-06 | COMP | 2023-10-06 | COMP | 2023-08-29 | COMP | 2023-11-01 | COMP | Rule 16 | 37 | 59 | 10 | 66 | 0 | 19 | 187
41679 | 2023-02-07 | 2023-04-18 | 2023-05-12 | 2023-05-12 | COMP | 2023-06-06 | COMP | 2023-06-28 | COMP | 2023-06-06 | COMP | 2023-08-03 | COMP | Rule 16 | 50 | 19 | 17 | 16 | 0 | 26 | 124
41740 | 2023-02-07 | 2023-04-24 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-28 | COMP | 2023-08-02 | COMP | 2023-06-28 | COMP | 2023-10-10 | COMP | Rule 16 | 54 | 32 | 15 | 25 | 0 | 49 | 171
40962 | 2023-02-08 | 2023-02-13 | 2023-04-29 | 2023-04-29 | COMP | 2023-05-09 | COMP | 2023-06-24 | COMP | 2023-11-10 | COMP | 2023-12-14 | COMP | Rule 16 | 4 | 54 | 7 | 32 | 97 | 22 | 214
41088 | 2023-02-08 | 2023-02-22 | 2023-04-20 | 2023-04-20 | COMP | 2023-04-20 | NOTN | 2023-04-20 | COMP | 2023-04-25 | COMP | 2023-06-14 | COMP | Other | 10 | 42 |  | 1 | 4 | 36 | 89
41130 | 2023-02-08 | 2023-02-24 | 2023-04-21 | 2023-04-21 | COMP | 2023-04-27 | COMP | 2023-12-19 | COMP | 2023-05-03 | COMP | 2023-11-16 | COMP | Rule 16 | 12 | 41 | 5 | 162 | 0 |  | 196
41262 | 2023-02-08 | 2023-03-08 | 2023-05-12 | 2023-05-12 | COMP | 2023-05-12 | NOTN | 2023-07-03 | COMP |  | INPR | 2023-09-22 | COMP | Other | 20 | 48 |  | 35 |  |  | 158
41476 | 2023-02-08 | 2023-03-28 | 2023-05-12 | 2023-05-12 | COMP | 2023-06-21 | COMP | 2023-08-16 | COMP | 2023-06-30 | COMP | 2023-10-20 | COMP | Rule 16 | 34 | 34 | 27 | 40 | 0 | 47 | 178
41509 | 2023-02-08 | 2023-03-30 | 2023-05-15 | 2023-05-25 | COMP | 2023-06-08 | COMP | 2023-06-14 | COMP | 2023-08-21 | COMP | 2023-12-01 | COMP | Rule 16 | 36 | 33 | 10 | 5 | 47 | 71 | 205
41562 | 2023-02-08 | 2023-04-04 | 2023-05-10 | 2023-05-10 | COMP | 2023-06-08 | COMP | 2023-06-22 | COMP | 2023-05-12 | COMP | 2023-07-31 | COMP | Rule 16 | 39 | 27 | 21 | 10 | 0 | 27 | 120
41600 | 2023-02-08 | 2023-04-11 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-10 | NOTN | 2023-07-10 | COMP | 2023-07-13 | COMP | 2023-08-10 | COMP | Other | 44 | 62 |  | 1 | 4 | 21 | 128
41631 | 2023-02-08 | 2023-04-12 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-07 | COMP | 2023-07-17 | COMP | 2023-08-28 | COMP | 2023-11-17 | COMP | Rule 16 | 45 | 32 | 9 | 27 | 31 | 58 | 197
41704 | 2023-02-08 | 2023-04-20 | 2023-06-14 | 2023-06-14 | COMP | 2023-07-10 | COMP | 2023-07-31 | COMP | 2023-07-10 | COMP | 2023-10-03 | COMP | Rule 16 | 51 | 39 | 17 | 16 | 0 | 46 | 165
41747 | 2023-02-08 | 2023-04-25 | 2023-06-29 | 2023-06-29 | COMP | 2023-07-05 | COMP | 2023-07-05 | COMP | 2023-08-01 | COMP | 2023-08-28 | COMP | Rule 16 | 54 | 46 | 4 | 1 | 20 | 20 | 140
40940 | 2023-02-09 | 2023-02-09 | 2023-04-07 | 2023-04-07 | COMP | 2023-04-27 | NOTN | 2023-06-07 | COMP |  | INPR | 2023-09-15 | COMP | Other | 1 | 41 |  | 43 |  |  | 152
41239 | 2023-02-09 | 2023-03-08 | 2023-06-21 | 2023-06-21 | COMP | 2023-07-20 | COMP | 2023-08-08 | COMP | 2023-08-28 | COMP | 2023-10-02 | COMP | Rule 16 | 19 | 74 | 21 | 14 | 15 | 25 | 163
41408 | 2023-02-09 | 2023-03-23 | 2023-03-31 | 2023-03-31 | COMP | 2023-05-04 | COMP | 2023-05-04 | COMP | 2023-05-01 | COMP | 2023-07-06 | COMP | Rule 16 | 30 | 7 | 25 | 1 | 0 | 43 | 102
41477 | 2023-02-09 | 2023-03-28 | 2023-04-17 | 2023-04-19 | COMP | 2023-07-14 | COMP | 2023-07-14 | COMP | 2023-07-26 | COMP | 2023-08-18 | COMP | Rule 16 | 33 | 15 | 60 | 1 | 9 | 18 | 133
41515 | 2023-02-09 | 2023-03-30 | 2023-06-06 | 2023-06-15 | COMP |  | INPR | 2023-07-10 | COMP | 2023-07-10 | COMP | 2023-07-08 | COMP | Rule 16 | 35 | 48 |  | 16 | 1 |  | 103
41516 | 2023-02-09 | 2023-03-30 | 2023-05-14 | 2023-05-14 | COMP | 2023-05-23 | COMP | 2023-05-24 | COMP | 2023-08-08 | COMP | 2023-08-15 | COMP | Rule 16 | 35 | 32 | 7 | 2 | 52 | 6 | 130
41537 | 2023-02-09 | 2023-04-03 | 2023-05-12 | 2023-05-12 | COMP | 2023-05-17 | COMP | 2023-05-17 | COMP | 2023-08-02 | COMP | 2023-08-03 | COMP | Rule 16 | 37 | 30 | 4 | 1 | 53 | 2 | 122
41559 | 2023-02-09 | 2023-04-04 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-08 | COMP | 2023-06-14 | COMP | 2023-10-10 | COMP | 2023-11-13 | COMP | Rule 16 | 38 | 38 | 10 | 5 | 82 | 24 | 192
41624 | 2023-02-09 | 2023-04-12 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-22 | COMP | 2023-05-22 | COMP | 2023-05-23 | COMP | 2023-06-19 | COMP | Rule 16 | 44 | 15 | 15 | 1 | 2 | 18 | 90
41732 | 2023-02-09 | 2023-04-24 | 2023-09-06 | 2023-09-06 | COMP | 2023-09-28 | COMP | 2023-10-12 | COMP | 2023-10-13 | COMP | 2023-10-22 | COMP | Rule 16 | 52 | 94 | 17 | 11 | 2 | 6 | 177
41800 | 2023-02-09 | 2023-05-01 | 2023-06-16 | 2023-06-16 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-09-11 | COMP | 2023-10-09 | COMP | Rule 16 | 57 | 34 | 34 | 1 | 26 | 21 | 168
41839 | 2023-02-09 | 2023-05-05 | 2023-06-07 | 2023-06-07 | COMP | 2023-08-11 | COMP | 2023-11-21 | COMP | 2023-11-14 | COMP | 2023-11-24 | COMP | Rule 16 | 61 | 23 | 46 | 71 | 0 | 2 | 199
41849 | 2023-02-09 | 2023-05-08 | 2023-06-07 | 2023-06-07 | COMP | 2023-08-14 | COMP | 2023-11-21 | COMP | 2023-11-14 | COMP | 2023-11-24 | COMP | Rule 16 | 62 | 22 | 47 | 70 | 0 | 2 | 199
41863 | 2023-02-09 | 2023-05-09 | 2023-07-17 | 2023-07-17 | COMP | 2023-07-17 | NOTN | 2023-09-05 | COMP | 2023-11-15 | COMP | 2023-11-03 | COMP | Other | 63 | 47 |  | 36 | 51 |  | 187
41877 | 2023-02-09 | 2023-05-10 | 2023-07-02 | 2023-07-02 | COMP | 2023-07-12 | COMP | 2023-08-02 | COMP | 2023-08-08 | COMP | 2023-09-20 | COMP | Rule 16 | 64 | 36 | 7 | 16 | 5 | 31 | 155
41919 | 2023-02-09 | 2023-05-17 | 2023-07-04 | 2023-07-04 | COMP | 2023-07-10 | COMP | 2023-08-21 | COMP | 2023-09-20 | COMP | 2023-09-29 | COMP | Rule 16 | 69 | 32 | 4 | 31 | 22 | 8 | 162
40954 | 2023-02-10 | 2023-02-10 | 2023-07-27 | 2023-07-27 | COMP | 2023-07-27 | NOTN | 2023-08-19 | COMP | 2023-08-07 | COMP | 2023-10-24 | COMP | Other | 1 | 116 |  | 17 | 0 | 46 | 178
41229 | 2023-02-10 | 2023-03-06 | 2023-04-12 | 2023-04-18 | COMP | 2023-05-19 | COMP | 2023-05-19 | COMP | 2023-06-21 | COMP | 2023-08-24 | COMP | Rule 16 | 16 | 28 | 24 | 1 | 22 | 46 | 136
41365 | 2023-02-10 | 2023-03-16 | 2023-05-06 | 2023-05-06 | COMP | 2023-05-09 | NOTN | 2023-06-08 | COMP | 2023-08-07 | COMP | 2023-09-19 | COMP | Other | 24 | 37 |  | 23 | 41 | 31 | 153
41418 | 2023-02-10 | 2023-03-23 | 2023-04-27 | 2023-04-27 | COMP | 2023-06-15 | COMP |  | REQD | 2023-07-19 | COMP | 2023-10-17 | COMP | Rule 16 | 29 | 26 | 35 |  |  |  | 173
41419 | 2023-02-10 | 2023-03-23 | 2023-05-08 | 2023-05-08 | COMP | 2023-05-19 | COMP | 2023-05-19 | COMP | 2023-05-22 | COMP | 2023-10-17 | COMP | Rule 16 | 29 | 33 | 10 | 1 | 2 | 103 | 173
41646 | 2023-02-10 | 2023-04-14 | 2023-06-26 | 2023-06-28 | COMP | 2023-10-25 | COMP | 2023-10-25 | COMP | 2023-10-11 | COMP | 2023-11-29 | COMP | Rule 16 | 45 | 50 | 84 | 1 | 0 | 23 | 201
41653 | 2023-02-10 | 2023-04-14 | 2023-07-27 | 2023-07-27 | COMP | 2023-07-28 | NOTN | 2023-08-17 | COMP | 2023-08-22 | COMP | 2023-10-16 | COMP | Other | 45 | 72 |  | 16 | 4 | 39 | 172
41712 | 2023-02-10 | 2023-04-21 | 2023-05-22 | 2023-05-22 | COMP | 2023-06-08 | COMP | 2023-06-08 | INPR | 2023-09-13 | COMP | 2023-09-19 | COMP | Rule 16 | 50 | 22 | 13 |  |  |  | 153
41941 | 2023-02-10 | 2023-05-20 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-09 | COMP | 2023-09-18 | COMP | 2023-08-09 | COMP | 2023-12-08 | COMP | Rule 16 | 70 | 48 | 8 | 28 | 0 | 57 | 208
41952 | 2023-02-10 | 2023-05-23 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-09 | NOTN | 2023-07-13 | COMP | 2023-07-26 | COMP | 2023-09-07 | COMP | Other | 72 | 31 |  | 5 | 10 | 31 | 145
41440 | 2023-02-11 | 2023-03-25 | 2023-05-18 | 2023-05-18 | COMP | 2023-05-30 | COMP | 2023-09-27 | COMP | 2023-08-22 | COMP | 2023-10-21 | COMP | Rule 16 | 29 | 39 | 8 | 84 | 0 | 18 | 175
40963 | 2023-02-12 | 2023-02-13 | 2023-05-04 | 2023-05-04 | COMP | 2023-05-18 | NOTN | 2023-07-12 | COMP | 2023-05-19 | NOTN | 2023-10-10 | COMP | Other | 1 | 58 |  | 47 |  |  | 167
41025 | 2023-02-13 | 2023-02-16 | 2023-03-28 | 2023-03-28 | COMP | 2023-04-19 | COMP | 2023-04-19 | COMP | 2023-06-06 | COMP | 2023-09-13 | COMP | Rule 16 | 4 | 28 | 17 | 1 | 34 | 69 | 148
41048 | 2023-02-13 | 2023-02-17 | 2023-06-26 | 2023-06-26 | COMP | 2023-07-18 | COMP | 2023-11-22 | COMP | 2023-11-02 | COMP | 2023-12-15 | COMP | Rule 29 | 5 | 89 | 16 | 90 | 0 | 16 | 212
41049 | 2023-02-13 | 2023-02-17 | 2023-07-13 | 2023-08-29 | COMP | 2023-09-07 | COMP | 2023-11-02 | COMP | 2023-11-30 | COMP | 2023-12-05 | COMP | Rule 16 | 5 | 101 | 7 | 41 | 18 | 4 | 204
41209 | 2023-02-13 | 2023-03-03 | 2023-03-10 | 2023-03-10 | COMP | 2023-03-16 | COMP | 2023-05-25 | COMP | 2023-05-09 | COMP | 2023-06-28 | COMP | Rule 16 | 14 | 6 | 5 | 51 | 0 | 23 | 95
41223 | 2023-02-13 | 2023-03-05 | 2023-07-16 | 2023-07-16 | COMP | 2023-07-21 | COMP | 2023-09-01 | COMP | 2023-08-23 | COMP | 2023-12-08 | COMP | Rule 16 | 14 | 92 | 5 | 31 | 0 | 67 | 207
41287 | 2023-02-13 | 2023-03-10 | 2023-03-28 | 2023-03-28 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP | 2023-12-06 | COMP | 2023-12-26 | COMP | Rule 16 | 19 | 13 | 94 | 1 | 82 | 14 | 218
41313 | 2023-02-13 | 2023-03-14 | 2023-03-29 | 2023-03-29 | COMP | 2023-03-30 | COMP | 2023-04-20 | COMP | 2023-04-25 | COMP | 2023-05-26 | COMP | Rule 16 | 21 | 12 | 2 | 16 | 4 | 24 | 74
41347 | 2023-02-13 | 2023-03-17 | 2023-06-19 | 2023-06-19 | COMP | 2023-07-10 | COMP | 2023-09-05 | COMP | 2023-09-18 | COMP | 2023-11-08 | COMP | Rule 16 | 24 | 65 | 14 | 41 | 10 | 38 | 188
41359 | 2023-02-13 | 2023-03-16 | 2023-06-20 | 2023-06-20 | COMP | 2023-07-26 | COMP | 2023-10-24 | COMP | 2023-10-03 | COMP | 2023-11-14 | COMP | Rule 16 | 23 | 67 | 26 | 64 | 0 | 15 | 191
41508 | 2023-02-13 | 2023-03-30 | 2023-05-19 | 2023-05-19 | COMP | 2023-07-12 | COMP | 2023-09-10 | COMP | 2023-11-14 | COMP | 2023-12-28 | COMP | Rule 16 | 33 | 37 | 36 | 42 | 46 | 30 | 220
41629 | 2023-02-13 | 2023-04-12 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-20 | COMP | 2023-07-06 | COMP | 2023-08-29 | COMP | 2023-10-02 | COMP | Rule 16 | 42 | 40 | 9 | 12 | 39 | 24 | 161
41700 | 2023-02-13 | 2023-04-20 | 2023-06-01 | 2023-06-01 | COMP | 2023-07-21 | COMP | 2023-07-27 | COMP | 2023-09-29 | COMP | 2023-11-27 | COMP | Rule 16 | 48 | 30 | 35 | 5 | 46 | 39 | 198
41702 | 2023-02-13 | 2023-04-20 | 2023-05-30 | 2023-05-30 | COMP | 2023-06-13 | COMP | 2023-06-13 | COMP | 2023-08-18 | COMP | 2023-09-21 | COMP | Rule 16 | 48 | 28 | 11 | 1 | 47 | 24 | 154
41817 | 2023-02-13 | 2023-05-03 | 2023-07-15 | 2023-07-15 | COMP | 2023-07-18 | NOTN | 2023-10-05 | COMP |  | INPR | 2023-12-16 | COMP | Other | 57 | 50 |  | 58 |  |  | 212
41892 | 2023-02-13 | 2023-05-14 | 2023-09-02 | 2023-09-02 | COMP | 2023-09-29 | COMP | 2023-10-11 | COMP | 2023-10-31 | COMP | 2023-12-27 | COMP | Rule 16 | 64 | 77 | 19 | 9 | 15 | 38 | 219
41911 | 2023-02-13 | 2023-05-17 | 2023-08-01 | 2023-08-01 | COMP | 2023-08-04 | COMP | 2023-09-26 | COMP | 2023-09-19 | COMP | 2023-10-27 | COMP | Rule 16 | 67 | 52 | 4 | 37 | 0 | 24 | 180
41951 | 2023-02-13 | 2023-05-23 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-09 | NOTN | 2023-07-13 | COMP | 2023-07-26 | COMP | 2023-09-07 | COMP | Other | 71 | 31 |  | 5 | 10 | 31 | 144
42371 | 2023-02-13 | 2023-08-14 | 2023-09-07 | 2023-09-07 | COMP | 2023-09-12 | COMP | 2023-11-07 | COMP | 2023-10-24 | COMP | 2023-12-14 | COMP | Rule 16 | 127 | 18 | 4 | 41 | 0 | 25 | 211
41045 | 2023-02-14 | 2023-02-17 | 2023-05-05 | 2023-05-05 | COMP | 2023-05-23 | COMP | 2023-05-23 | COMP | 2023-09-13 | COMP | 2023-12-01 | COMP | Rule 15/16 | 4 | 55 | 13 | 1 | 78 | 55 | 201
41067 | 2023-02-14 | 2023-02-21 | 2023-04-11 | 2023-04-11 | COMP | 2023-04-17 | COMP | 2023-04-17 | COMP | 2023-04-17 | COMP | 2023-05-03 | COMP | Rule 16 | 5 | 36 | 5 | 1 | 1 | 13 | 56
41185 | 2023-02-14 | 2023-03-01 | 2023-04-26 | 2023-04-26 | COMP | 2023-05-09 | COMP | 2023-05-09 | COMP | 2023-06-26 | COMP | 2023-09-07 | COMP | Rule 16 | 11 | 41 | 10 | 1 | 33 | 52 | 143
41228 | 2023-02-14 | 2023-03-06 | 2023-04-05 | 2023-04-05 | COMP | 2023-04-20 | COMP | 2023-04-20 | COMP | 2023-04-28 | COMP | 2023-07-31 | COMP | Rule 16 | 14 | 23 | 12 | 1 | 7 | 64 | 116
41289 | 2023-02-14 | 2023-03-10 | 2023-05-11 | 2023-05-11 | COMP | 2023-05-19 | COMP | 2023-05-19 | COMP | 2023-06-07 | COMP | 2023-06-27 | COMP | Rule 16 | 18 | 45 | 7 | 1 | 13 | 14 | 93
41368 | 2023-02-14 | 2023-03-17 | 2023-06-07 | 2023-06-07 | COMP | 2023-08-01 | COMP | 2023-08-18 | COMP | 2023-09-29 | COMP | 2023-10-20 | COMP | Rule 16 | 23 | 58 | 38 | 14 | 30 | 16 | 174
41376 | 2023-02-14 | 2023-03-17 | 2023-04-08 | 2023-04-08 | COMP | 2023-04-10 | NOTN | 2023-05-23 | COMP | 2023-07-11 | COMP | 2023-09-29 | COMP | Other | 23 | 16 |  | 32 | 33 | 58 | 159
41406 | 2023-02-14 | 2023-03-23 | 2023-04-13 | 2023-04-13 | COMP | 2023-05-02 | COMP | 2023-05-02 | COMP | 2023-05-08 | COMP | 2023-09-19 | COMP | Rule 16 | 27 | 16 | 14 | 1 | 5 | 93 | 151
41428 | 2023-02-14 | 2023-03-24 | 2023-05-15 | 2023-05-15 | COMP | 2023-06-22 | COMP | 2023-06-22 | COMP | 2023-08-04 | COMP | 2023-09-26 | COMP | Rule 16 | 28 | 37 | 27 | 1 | 31 | 37 | 156
41486 | 2023-02-14 | 2023-03-30 | 2023-06-13 | 2023-06-13 | COMP | 2023-06-13 | NOTN | 2023-06-14 | COMP | 2023-06-13 | COMP | 2023-08-18 | COMP | Other | 32 | 53 |  | 2 | 0 | 46 | 130
41487 | 2023-02-14 | 2023-03-29 | 2023-07-17 | 2023-07-17 | COMP | 2023-08-21 | COMP | 2023-08-22 | COMP | 2023-11-20 | COMP | 2023-12-19 | COMP | Rule 16 | 31 | 76 | 26 | 2 | 63 | 20 | 213
41541 | 2023-02-14 | 2023-04-03 | 2023-04-25 | 2023-04-25 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP | 2023-09-12 | COMP | 2023-09-22 | COMP | Other | 34 | 17 | 72 | 1 | 26 | 9 | 154
41667 | 2023-02-14 | 2023-04-17 | 2023-05-21 | 2023-05-21 | COMP | 2023-06-12 | COMP | 2023-07-06 | COMP | 2023-07-10 | COMP | 2023-08-14 | COMP | Rule 16 | 44 | 25 | 15 | 17 | 3 | 26 | 126
41682 | 2023-02-14 | 2023-04-18 | 2023-05-21 | 2023-05-21 | COMP | 2023-05-22 | NOTN | 2023-07-03 | COMP | 2023-10-29 | COMP | 2023-11-17 | COMP | Other | 45 | 24 |  | 29 | 83 | 14 | 193
41706 | 2023-02-14 | 2023-04-20 | 2023-05-31 | 2023-05-31 | COMP | 2023-07-19 | COMP | 2023-09-07 | COMP | 2023-08-10 | COMP | 2023-10-24 | COMP | Rule 16 | 47 | 29 | 34 | 36 | 0 | 34 | 176
41915 | 2023-02-14 | 2023-05-17 | 2023-06-09 | 2023-06-09 | COMP | 2023-07-06 | COMP | 2023-08-07 | COMP | 2023-09-18 | COMP | 2023-09-19 | COMP | Rule 16 | 66 | 17 | 18 | 23 | 30 | 2 | 151
42011 | 2023-02-14 | 2023-05-31 | 2023-07-18 | 2023-07-18 | COMP | 2023-07-25 | COMP | 2023-08-08 | COMP | 2023-10-17 | COMP | 2023-12-20 | COMP | Rule 16 | 75 | 33 | 6 | 11 | 50 | 44 | 214
42196 | 2023-02-14 | 2023-06-29 | 2023-08-29 | 2023-08-29 | COMP | 2023-09-11 | COMP | 2023-11-10 | COMP | 2023-11-09 | COMP | 2023-12-14 | COMP | Rule 16 | 95 | 43 | 9 | 44 | 0 | 22 | 210
41111 | 2023-02-15 | 2023-02-23 | 2023-04-01 | 2023-04-01 | COMP | 2023-04-10 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-09-20 | COMP | Rule 16 | 6 | 27 | 6 | 82 | 1 | 33 | 151
41192 | 2023-02-15 | 2023-03-02 | 2023-05-03 | 2023-05-03 | COMP | 2023-05-08 | COMP | 2023-05-25 | COMP | 2023-05-25 | COMP | 2023-07-27 | COMP | Rule 16 | 11 | 45 | 4 | 14 | 1 | 43 | 113
41290 | 2023-02-15 | 2023-03-10 | 2023-05-23 | 2023-05-23 | COMP | 2023-05-24 | NOTN | 2023-06-21 | COMP |  | INPR | 2023-07-02 | COMP | Other | 17 | 53 |  | 20 |  |  | 95
41417 | 2023-02-15 | 2023-03-23 | 2023-07-12 | 2023-08-16 | COMP | 2023-08-24 | COMP | 2023-09-01 | COMP | 2023-09-27 | COMP | 2023-11-30 | COMP | Rule 16 | 26 | 77 | 7 | 7 | 18 | 44 | 199
41434 | 2023-02-15 | 2023-03-24 | 2023-05-06 | 2023-05-06 | COMP | 2023-05-19 | NOTN | 2023-08-07 | COMP | 2023-09-27 | COMP | 2023-10-06 | COMP | Other | 27 | 31 |  | 63 | 37 | 8 | 163
41436 | 2023-02-15 | 2023-03-24 | 2023-06-14 | 2023-06-14 | COMP | 2023-06-22 | NOTN | 2023-08-16 | COMP | 2023-06-22 | COMP | 2023-08-18 | COMP | Other | 27 | 58 |  | 44 | 0 | 3 | 129
41513 | 2023-02-15 | 2023-03-30 | 2023-06-28 | 2023-06-28 | COMP | 2023-07-06 | COMP | 2023-07-06 | COMP | 2023-07-12 | COMP | 2023-08-27 | COMP | Rule 16 | 31 | 63 | 6 | 1 | 5 | 33 | 134
41579 | 2023-02-15 | 2023-04-05 | 2023-06-26 | 2023-06-26 | COMP | 2023-06-26 | NOTN | 2023-08-09 | COMP | 2023-08-22 | COMP | 2023-09-25 | COMP | Other | 35 | 57 |  | 32 | 10 | 24 | 154
41727 | 2023-02-15 | 2023-04-24 | 2023-06-08 | 2023-06-08 | COMP | 2023-06-14 | COMP | 2023-06-15 | COMP | 2023-09-29 | COMP | 2023-12-21 | COMP | Rule 16 | 48 | 33 | 5 | 2 | 74 | 57 | 214
41749 | 2023-02-15 | 2023-04-25 | 2023-07-29 | 2023-07-29 | COMP | 2023-08-07 | COMP | 2023-09-15 | COMP | 2023-08-04 | COMP | 2023-11-30 | COMP | Rule 16 | 49 | 66 | 6 | 29 | 0 | 52 | 199
41750 | 2023-02-15 | 2023-04-25 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-24 | COMP | 2023-09-19 | COMP | 2023-10-17 | COMP | 2023-11-14 | COMP | Rule 16 | 49 | 51 | 12 | 41 | 21 | 20 | 189
41798 | 2023-02-15 | 2023-05-01 | 2023-06-16 | 2023-06-16 | COMP | 2023-07-17 | COMP | 2023-07-17 | COMP | 2023-07-18 | COMP | 2023-08-16 | COMP | Rule 16 | 53 | 34 | 20 | 1 | 2 | 22 | 127
41844 | 2023-02-15 | 2023-05-06 | 2023-06-05 | 2023-07-06 | COMP | 2023-08-14 | COMP | 2023-08-28 | COMP |  | INPR | 2023-10-12 | COMP | Rule 16 | 57 | 20 | 28 | 11 |  |  | 167
41871 | 2023-02-15 | 2023-05-10 | 2023-07-25 | 2023-07-25 | COMP | 2023-08-03 | COMP | 2023-08-03 | COMP | 2023-07-25 | COMP | 2023-08-05 | COMP | Rule 16 | 60 | 52 | 8 | 1 | 0 | 2 | 119
41008 | 2023-02-16 | 2023-02-16 | 2023-02-27 | 2023-02-27 | COMP | 2023-02-28 | NOTN | 2023-03-22 | COMP | 2023-02-28 | COMP | 2023-05-23 | COMP | Other | 1 | 7 |  | 18 | 0 | 45 | 68
41105 | 2023-02-16 | 2023-02-23 | 2023-05-05 | 2023-06-30 | COMP | 2023-07-05 | COMP | 2023-05-17 | COMP | 2023-07-31 | COMP | 2023-08-29 | COMP | Rule 16 | 5 | 52 | 3 |  | 51 | 22 | 135
41380 | 2023-02-16 | 2023-03-20 | 2023-05-04 | 2023-05-04 | COMP | 2023-05-15 | COMP | 2023-06-23 | COMP | 2023-07-06 | COMP | 2023-10-25 | COMP | Rule 16 | 22 | 34 | 8 | 28 | 9 | 79 | 175
41394 | 2023-02-16 | 2023-03-22 | 2023-04-25 | 2023-04-25 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP |  | INPR | 2023-11-06 | COMP | Rule 16 | 24 | 25 | 73 | 1 |  |  | 183
41529 | 2023-02-16 | 2023-03-31 | 2023-05-10 | 2023-08-26 | COMP | 2023-09-05 | COMP | 2023-09-05 | COMP | 2023-09-26 | COMP | 2023-10-26 | COMP | Rule 16 | 31 | 29 | 6 | 1 | 16 | 23 | 176
41628 | 2023-02-16 | 2023-04-12 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-26 | COMP | 2023-08-09 | COMP | 2023-10-03 | COMP | 2023-10-25 | COMP | Rule 16 | 39 | 48 | 5 | 32 | 39 | 17 | 175
41634 | 2023-02-16 | 2023-04-13 | 2023-05-22 | 2023-05-22 | COMP | 2023-07-10 | COMP | 2023-07-10 | COMP | 2023-08-21 | COMP | 2023-09-19 | COMP | Rule 16 | 40 | 28 | 33 | 1 | 31 | 21 | 149
41664 | 2023-02-16 | 2023-04-17 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-29 | COMP |  | REQD | 2023-10-26 | COMP | 2023-12-16 | COMP | Rule 16 | 42 | 76 | 19 |  |  |  | 209
41792 | 2023-02-16 | 2023-04-28 | 2023-06-12 | 2023-06-12 | COMP | 2023-06-26 | COMP | 2023-07-20 | COMP | 2023-07-13 | COMP | 2023-10-02 | COMP | Rule 16 | 51 | 31 | 10 | 18 | 0 | 52 | 158
41891 | 2023-02-16 | 2023-05-13 | 2023-06-01 | 2023-06-01 | COMP | 2023-06-21 | COMP | 2023-09-25 | COMP | 2023-11-06 | COMP | 2023-12-01 | COMP | Rule 16 | 61 | 13 | 14 | 67 | 31 | 17 | 199
41943 | 2023-02-16 | 2023-05-20 | 2023-05-29 | 2023-05-29 | COMP | 2023-06-02 | NOTN | 2023-06-02 | COMP | 2023-06-09 | COMP | 2023-07-24 | COMP | Other | 66 | 5 |  | 4 | 6 | 30 | 109
41978 | 2023-02-16 | 2023-05-25 | 2023-07-17 | 2023-07-17 | COMP | 2023-07-20 | COMP | 2023-08-08 | COMP | 2023-08-31 | COMP | 2023-09-25 | COMP | Rule 16 | 70 | 35 | 4 | 14 | 18 | 17 | 153
41060 | 2023-02-17 | 2023-02-21 | 2023-03-23 | 2023-03-23 | COMP | 2023-03-23 | NOTN | 2023-03-23 | INPR | 2023-03-23 | COMP | 2023-05-24 | COMP | Other | 2 | 23 |  |  |  |  | 68
41076 | 2023-02-17 | 2023-02-22 | 2023-05-12 | 2023-05-12 | COMP | 2023-06-02 | COMP | 2023-07-27 | COMP |  | INPR | 2023-12-06 | COMP | Rule 16 | 3 | 58 | 15 | 38 |  |  | 201
41339 | 2023-02-17 | 2023-03-15 | 2023-05-14 | 2023-05-14 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-09-12 | COMP | 2023-09-13 | COMP | Rule 16 | 18 | 43 | 59 | 1 | 25 | 2 | 144
41533 | 2023-02-17 | 2023-04-01 | 2023-06-14 | 2023-06-14 | COMP | 2023-07-10 | COMP | 2023-08-14 | COMP | 2023-08-03 | COMP | 2023-09-20 | COMP | Rule 16 | 30 | 52 | 17 | 26 | 0 | 27 | 149
41578 | 2023-02-17 | 2023-04-05 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-05 | NOTN | 2023-07-14 | COMP | 2023-08-19 | COMP | 2023-02-02 | COMP | Other | 33 | 63 |  | 8 | 26
41610 | 2023-02-17 | 2023-04-12 | 2023-05-31 | 2023-05-31 | COMP | 2023-06-22 | COMP | 2023-06-22 | COMP | 2023-09-29 | COMP | 2023-10-17 | COMP | Rule 16 | 38 | 35 | 16 | 1 | 70 | 13 | 168
41657 | 2023-02-17 | 2023-04-14 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-05 | COMP | 2023-07-17 | COMP | 2023-09-08 | COMP | 2023-10-05 | COMP | Rule 16 | 40 | 30 | 7 | 29 | 39 | 20 | 160
41672 | 2023-02-17 | 2023-04-17 | 2023-05-10 | 2023-05-10 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP | 2023-08-21 | COMP | 2023-10-30 | COMP | Rule 16 | 41 | 18 | 63 | 1 | 9 | 50 | 177
41723 | 2023-02-17 | 2023-04-22 | 2023-06-15 | 2023-06-15 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-08-21 | COMP | 2023-10-06 | COMP | Rule 16 | 45 | 38 | 37 | 1 | 10 | 34 | 161
41753 | 2023-02-17 | 2023-04-25 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-23 | COMP | 2023-07-25 | COMP | 2023-07-28 | COMP | 2023-09-07 | COMP | Rule 16 | 47 | 31 | 12 | 22 | 4 | 29 | 140
41780 | 2023-02-17 | 2023-04-27 | 2023-06-02 | 2023-06-02 | COMP | 2023-06-27 | COMP | 2023-06-27 | COMP | 2023-06-02 | COMP | 2023-09-08 | COMP | Rule 16 | 49 | 26 | 17 | 1 | 0 | 52 | 141
41805 | 2023-02-17 | 2023-05-02 | 2023-05-15 | 2023-05-15 | COMP | 2023-05-22 | COMP | 2023-08-02 | COMP | 2023-05-24 | COMP | 2023-09-06 | COMP | Rule 16 | 52 | 10 | 6 | 50 | 0 | 25 | 139
41825 | 2023-02-17 | 2023-05-04 | 2023-08-08 | 2023-08-08 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | 2023-09-05 | COMP | 2023-09-12 | COMP | Rule 16 | 54 | 66 | 15 | 1 | 6 | 6 | 143
41615 | 2023-02-18 | 2023-04-12 | 2023-05-18 | 2023-05-18 | COMP | 2023-05-23 | COMP | 2023-05-23 | COMP | 2023-08-22 | COMP | 2023-09-07 | COMP | Rule 16 | 37 | 27 | 4 | 1 | 63 | 12 | 139
41644 | 2023-02-18 | 2023-04-14 | 2023-05-10 | 2023-05-10 | COMP | 2023-05-22 | COMP | 2023-10-06 | COMP | 2023-10-19 | COMP | 2023-12-02 | COMP | Rule 16 | 39 | 19 | 9 | 96 | 10 | 29 | 197
41717 | 2023-02-18 | 2023-04-21 | 2023-06-08 | 2023-06-08 | COMP | 2023-06-30 | COMP | 2023-06-30 | COMP | 2023-06-15 | COMP | 2023-09-12 | COMP | Rule 16 | 44 | 34 | 16 | 1 | 0 | 51 | 142
41238 | 2023-02-20 | 2023-03-07 | 2023-06-06 | 2023-06-06 | COMP | 2023-06-13 | COMP | 2023-07-06 | COMP | 2023-07-14 | COMP | 2023-10-03 | COMP | Rule 16 | 11 | 65 | 6 | 16 | 7 | 57 | 157
41575 | 2023-02-20 | 2023-04-06 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-06 | NOTN | 2023-08-23 | COMP | 2023-11-03 | COMP | 2023-11-30 | COMP | Other | 33 | 62 |  | 36 | 52 | 17 | 196
41950 | 2023-02-20 | 2023-05-22 | 2023-07-28 | 2023-07-28 | COMP | 2023-08-09 | NOTN | 2023-09-18 | COMP | 2023-12-19 | COMP | 2023-11-30 | COMP | Other | 65 | 47 |  | 36 | 64 |  | 196
42211 | 2023-02-20 | 2023-07-03 | 2023-08-12 | 2023-08-12 | COMP | 2023-08-22 | COMP | 2023-08-23 | COMP | 2023-11-20 | COMP | 2023-11-29 | COMP | Rule 16 | 93 | 29 | 7 | 2 | 62 | 6 | 195
42401 | 2023-02-20 | 2023-08-22 | 2023-08-29 | 2023-08-29 | COMP | 2023-09-01 | NOTN | 2023-09-14 | COMP | 2023-12-26 | COMP | 2023-10-03 | COMP | Other | 128 | 6 |  | 12 | 70 |  | 157
41171 | 2023-02-21 | 2023-02-28 | 2023-07-01 | 2023-07-01 | COMP | 2023-09-15 | COMP | 2023-10-16 | COMP | 2023-10-10 | COMP | 2023-10-27 | COMP | Rule 15/16 | 6 | 87 | 53 | 22 | 0 | 10 | 175
41270 | 2023-02-21 | 2023-03-09 | 2023-04-17 | 2023-04-17 | COMP | 2023-04-24 | COMP | 2023-11-03 | COMP | 2023-10-23 | COMP | 2023-12-13 | COMP | Rule 16 | 13 | 28 | 6 | 136 | 0 | 26 | 205
41344 | 2023-02-21 | 2023-03-15 | 2023-04-02 | 2023-04-02 | COMP | 2023-04-06 | COMP | 2023-05-22 | COMP | 2023-05-25 | COMP | 2023-08-10 | COMP | Rule 16 | 17 | 13 | 4 | 33 | 4 | 53 | 120
41370 | 2023-02-21 | 2023-03-17 | 2023-04-27 | 2023-06-23 | COMP | 2023-07-07 | COMP | 2023-07-07 | COMP | 2023-06-14 | COMP | 2023-09-28 | COMP | Rule 16 | 19 | 30 | 10 | 1 | 0 | 59 | 154
41409 | 2023-02-21 | 2023-03-22 | 2023-06-16 | 2023-06-16 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-09-28 | COMP | 2023-12-07 | COMP | Rule 16 | 22 | 62 | 65 | 1 | 8 | 48 | 201
41503 | 2023-02-21 | 2023-03-29 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-10 | COMP | 2023-08-07 | COMP |  | INPR | 2023-11-29 | COMP | Rule 16 | 27 | 60 | 12 | 21 |  |  | 195
41618 | 2023-02-21 | 2023-04-12 | 2023-05-17 | 2023-05-17 | COMP | 2023-08-18 | COMP | 2023-08-18 | COMP | 2023-08-23 | COMP | 2023-09-13 | COMP | Rule 16 | 37 | 26 | 65 | 1 | 4 | 15 | 143
41625 | 2023-02-21 | 2023-04-12 | 2023-05-19 | 2023-05-19 | COMP | 2023-06-12 | COMP | 2023-06-14 | COMP | 2023-06-12 | COMP | 2023-08-04 | COMP | Rule 16 | 37 | 28 | 16 | 3 | 0 | 36 | 116
41652 | 2023-02-21 | 2023-04-14 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-01 | COMP | 2023-06-13 | COMP | 2023-08-23 | COMP | 2023-09-18 | COMP | Rule 16 | 39 | 30 | 5 | 9 | 50 | 18 | 146
41663 | 2023-02-21 | 2023-04-18 | 2023-05-21 | 2023-05-21 | COMP | 2023-06-21 | COMP | 2023-10-19 | COMP | 2023-10-13 | COMP | 2023-10-30 | COMP | Other | 41 | 24 | 21 | 85 | 0 | 8 | 176
41709 | 2023-02-21 | 2023-04-20 | 2023-06-12 | 2023-06-12 | COMP | 2023-06-23 | COMP | 2023-07-26 | COMP | 2023-08-14 | COMP | 2023-08-24 | COMP | Rule 16 | 43 | 37 | 9 | 23 | 14 | 9 | 130
41771 | 2023-02-21 | 2023-04-26 | 2023-05-31 | 2023-05-31 | COMP | 2023-06-07 | COMP | 2023-08-03 | COMP | 2023-08-04 | COMP | 2023-11-30 | COMP | Rule 16 | 47 | 25 | 6 | 40 | 2 | 81 | 196
41835 | 2023-02-21 | 2023-05-05 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-05 | NOTN | 2023-07-10 | COMP | 2023-07-05 | COMP | 2023-10-23 | COMP | Other | 54 | 41 |  | 4 | 0 | 75 | 171
41910 | 2023-02-21 | 2023-05-16 | 2023-06-26 | 2023-06-26 | COMP | 2023-08-16 | COMP | 2023-08-22 | COMP | 2023-08-16 | COMP | 2023-11-09 | COMP | Rule 16 | 61 | 28 | 37 | 5 | 0 | 57 | 184
41917 | 2023-02-21 | 2023-05-17 | 2023-08-05 | 2023-08-05 | COMP | 2023-08-07 | NOTN | 2023-08-11 | COMP |  | INPR | 2023-10-24 | COMP | Other | 62 | 55 |  | 5 |  |  | 172
41965 | 2023-02-21 | 2023-05-24 | 2023-07-25 | 2023-07-25 | COMP | 2023-08-24 | COMP | 2023-09-27 | COMP | 2023-09-18 | COMP | 2023-11-14 | COMP | Rule 16 | 67 | 42 | 23 | 24 | 0 | 34 | 186
42075 | 2023-02-21 | 2023-06-06 | 2023-06-26 | 2023-06-26 | COMP | 2023-07-25 | COMP | 2023-08-04 | COMP | 2023-08-21 | COMP | 2023-09-06 | COMP | Rule 15/16 | 75 | 14 | 21 | 9 | 12 | 12 | 138
42125 | 2023-02-21 | 2023-06-14 | 2023-08-18 | 2023-08-18 | COMP | 2023-08-28 | COMP | 2023-08-28 | NOTN | 2023-11-03 | COMP | 2023-11-29 | COMP | Rule 16 | 81 | 46 | 7 |  |  |  | 195
41089 | 2023-02-22 | 2023-02-23 | 2023-04-17 | 2023-04-17 | COMP | 2023-05-02 | COMP | 2023-05-02 | COMP | 2023-07-10 | COMP | 2023-07-17 | COMP | Rule 16 | 2 | 38 | 12 | 1 | 47 | 6 | 101
41090 | 2023-02-22 | 2023-02-23 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-02 | COMP | 2023-08-14 | COMP | 2023-06-20 | NOTN | 2023-09-11 | COMP | Rule 16 | 2 | 46 | 4 | 72 |  |  | 140
41095 | 2023-02-22 | 2023-02-23 | 2023-03-15 | 2023-03-15 | COMP | 2023-03-15 | NOTN | 2023-05-04 | COMP | 2023-05-16 | COMP | 2023-05-25 | COMP | Other | 2 | 15 |  | 37 | 9 | 8 | 67
41099 | 2023-02-22 | 2023-02-23 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-02 | NOTN | 2023-07-10 | COMP | 2023-07-26 | COMP | 2023-08-15 | COMP | Other | 2 | 49 |  | 47 | 13 | 15 | 122
41140 | 2023-02-22 | 2023-02-27 | 2023-05-15 | 2023-05-15 | COMP | 2023-05-17 | COMP | 2023-06-05 | COMP | 2023-06-12 | COMP | 2023-07-06 | COMP | Rule 16 | 4 | 56 | 3 | 13 | 6 | 17 | 94
41186 | 2023-02-22 | 2023-03-02 | 2023-04-04 | 2023-04-04 | COMP | 2023-04-07 | NOTN | 2023-06-02 | COMP | 2023-08-22 | COMP | 2023-12-08 | COMP | Other | 7 | 24 |  | 43 | 56 | 75 | 201
41383 | 2023-02-22 | 2023-03-20 | 2023-05-12 | 2023-05-12 | COMP | 2023-05-22 | COMP | 2023-07-21 | COMP | 2023-07-24 | COMP | 2023-09-01 | COMP | Rule 16 | 19 | 40 | 7 | 42 | 2 | 30 | 135
41386 | 2023-02-22 | 2023-03-20 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-26 | COMP | 2023-08-31 | COMP |  | INPR | 2023-12-02 | COMP | Rule 16 | 19 | 57 | 13 | 48 |  |  | 196
41391 | 2023-02-22 | 2023-03-21 | 2023-04-19 | 2023-04-19 | COMP | 2023-05-17 | COMP | 2023-09-08 | COMP | 2023-08-06 | COMP | 2023-10-18 | COMP | Rule 16 | 20 | 22 | 21 | 79 | 0 | 29 | 167
41455 | 2023-02-22 | 2023-03-27 | 2023-06-06 | 2023-06-06 | COMP | 2023-08-21 | COMP | 2023-09-13 | COMP | 2023-10-17 | COMP | 2023-11-21 | COMP | Rule 16 | 24 | 51 | 53 | 17 | 25 | 25 | 190
41546 | 2023-02-22 | 2023-04-03 | 2023-05-01 | 2023-05-01 | COMP | 2023-05-16 | COMP | 2023-05-16 | COMP | 2023-12-06 | COMP | 2023-12-11 | COMP | Rule 16 | 29 | 21 | 12 | 1 | 140 | 4 | 202
41758 | 2023-02-22 | 2023-04-25 | 2023-05-25 | 2023-05-26 | COMP | 2023-06-06 | COMP | 2023-07-10 | COMP | 2023-09-07 | COMP | 2023-11-30 | COMP | Rule 16 | 45 | 23 | 7 | 23 | 43 | 58 | 195
41866 | 2023-02-22 | 2023-05-10 | 2023-07-26 | 2023-07-26 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP | 2023-09-27 | COMP | Rule 16 | 56 | 53 | 15 | 1 | 1 | 31 | 152
41932 | 2023-02-22 | 2023-05-19 | 2023-08-17 | 2023-08-17 | COMP | 2023-09-26 | COMP |  | REQD | 2023-10-10 | COMP | 2023-12-13 | COMP | Other | 63 | 62 | 28 |  |  |  | 204
42019 | 2023-02-22 | 2023-05-31 | 2023-06-28 | 2023-08-18 | COMP | 2023-09-01 | COMP | 2023-09-01 | COMP | 2023-10-30 | COMP | 2023-11-21 | COMP | Rule 16 | 70 | 20 | 11 | 1 | 41 | 16 | 190
42155 | 2023-02-22 | 2023-06-21 | 2023-07-21 | 2023-07-21 | COMP | 2023-08-11 | COMP | 2023-09-19 | COMP | 2023-09-11 | COMP | 2023-11-07 | COMP | Rule 16 | 84 | 22 | 16 | 27 | 0 | 36 | 181
41204 | 2023-02-23 | 2023-03-03 | 2023-03-16 | 2023-03-16 | COMP | 2023-06-22 | COMP | 2023-06-22 | COMP |  | INPR | 2023-07-19 | COMP | Rule 16 | 7 | 10 | 69 | 1 |  |  | 102
41371 | 2023-02-23 | 2023-03-17 | 2023-05-20 | 2023-05-20 | COMP | 2023-06-12 | COMP | 2023-06-12 | COMP | 2023-06-27 | COMP | 2023-07-14 | COMP | Rule 16 | 17 | 46 | 15 | 1 | 11 | 13 | 99
41466 | 2023-02-23 | 2023-03-27 | 2023-06-19 | 2023-06-19 | COMP | 2023-08-22 | COMP | 2023-09-18 | COMP | 2023-08-29 | COMP | 2023-11-02 | COMP | Rule 16 | 23 | 59 | 45 | 19 | 0 | 34 | 177
41543 | 2023-02-23 | 2023-04-03 | 2023-06-16 | 2023-06-16 | COMP | 2023-06-20 | NOTN | 2023-06-20 | COMP | 2023-07-25 | COMP | 2023-09-15 | COMP | Other | 28 | 54 |  | 2 | 25 | 38 | 143
41572 | 2023-02-23 | 2023-04-05 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-04 | NOTN | 2023-08-04 | COMP | 2023-08-17 | COMP | 2023-09-21 | COMP | Other | 30 | 84 |  | 2 | 10 | 25 | 147
41614 | 2023-02-23 | 2023-04-12 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-28 | COMP | 2023-08-07 | COMP | 2023-07-03 | COMP | 2023-09-13 | COMP | Rule 16 | 35 | 48 | 7 | 28 | 0 | 27 | 141
41630 | 2023-02-23 | 2023-04-13 | 2023-05-04 | 2023-05-04 | COMP | 2023-07-10 | COMP | 2023-07-10 | COMP | 2023-08-28 | COMP | 2023-09-18 | COMP | Rule 16 | 36 | 16 | 45 | 1 | 36 | 15 | 144
41773 | 2023-02-23 | 2023-04-27 | 2023-08-23 | 2023-08-23 | COMP | 2023-09-01 | COMP | 2023-09-01 | COMP | 2023-09-01 | COMP | 2023-09-06 | COMP | Rule 16 | 46 | 82 | 8 | 1 | 1 | 3 | 136
41873 | 2023-02-23 | 2023-05-10 | 2023-06-24 | 2023-06-24 | COMP | 2023-07-06 | NOTN | 2023-07-06 | COMP | 2023-07-11 | COMP | 2023-12-04 | COMP | Other | 55 | 31 |  | 8 | 4 | 101 | 196
41918 | 2023-02-23 | 2023-05-17 | 2023-06-15 | 2023-06-15 | COMP | 2023-06-20 | COMP | 2023-07-07 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | Rule 16 | 60 | 21 | 3 | 13 | 37 | 1 | 130
41959 | 2023-02-23 | 2023-05-23 | 2023-06-23 | 2023-06-23 | COMP | 2023-06-24 | NOTN | 2023-07-24 | COMP | 2023-08-09 | NOTN | 2023-10-04 | COMP | Other | 64 | 22 |  | 21 |  |  | 156
41968 | 2023-02-23 | 2023-05-24 | 2023-06-30 | 2023-06-30 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-10-25 | COMP | 2023-10-31 | COMP | Rule 16 | 65 | 26 | 27 | 1 | 56 | 5 | 175
41135 | 2023-02-24 | 2023-02-27 | 2023-04-25 | 2023-04-25 | COMP | 2023-05-02 | COMP | 2023-06-13 | COMP | 2023-06-20 | COMP | 2023-09-02 | COMP | Rule 16 | 2 | 42 | 6 | 30 | 5 | 53 | 133
41257 | 2023-02-24 | 2023-03-08 | 2023-05-18 | 2023-05-18 | COMP | 2023-06-14 | COMP | 2023-06-14 | COMP | 2023-06-29 | COMP | 2023-08-23 | COMP | Rule 16 | 9 | 52 | 19 | 1 | 11 | 39 | 126
41389 | 2023-02-24 | 2023-03-21 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-24 | COMP | 2023-05-24 | COMP | 2023-06-05 | COMP | 2023-06-14 | COMP | Rule 16 | 18 | 31 | 17 | 1 | 8 | 8 | 78
41448 | 2023-02-24 | 2023-03-27 | 2023-04-15 | 2023-04-15 | COMP | 2023-05-18 | COMP | 2023-05-18 | COMP | 2023-08-03 | COMP | 2023-08-14 | COMP | Rule 16 | 22 | 15 | 24 | 1 | 53 | 8 | 119
41449 | 2023-02-24 | 2023-03-27 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-07 | NOTN | 2023-07-25 | COMP | 2023-06-09 | COMP | 2023-08-24 | COMP | Other | 22 | 52 |  | 33 | 0 | 23 | 127
41462 | 2023-02-24 | 2023-03-27 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-01 | COMP | 2023-06-01 | COMP | 2023-08-05 | COMP | 2023-07-19 | COMP | Rule 16 | 22 | 42 | 7 | 1 | 45 |  | 101
41475 | 2023-02-24 | 2023-03-28 | 2023-05-18 | 2023-05-18 | COMP | 2023-05-26 | COMP | 2023-07-06 | COMP | 2023-08-22 | COMP | 2023-09-19 | COMP | Rule 16 | 23 | 38 | 7 | 27 | 34 | 20 | 144
41479 | 2023-02-24 | 2023-03-28 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-01 | NOTN | 2023-05-01 | COMP | 2023-05-02 | COMP | 2023-05-28 | COMP | Other | 23 | 23 |  | 3 | 2 | 19 | 66
41542 | 2023-02-24 | 2023-04-04 | 2023-05-05 | 2023-05-05 | COMP | 2023-05-24 | NOTN | 2023-05-24 | COMP | 2023-05-24 | COMP | 2023-08-29 | COMP | Other | 28 | 24 |  | 14 | 1 | 67 | 130
41592 | 2023-02-24 | 2023-04-08 | 2023-06-13 | 2023-06-13 | COMP | 2023-10-17 | COMP | 2023-10-19 | COMP | 2023-10-25 | COMP | 2023-11-10 | COMP | Rule 16 | 31 | 46 | 88 | 3 | 5 | 12 | 181
41608 | 2023-02-24 | 2023-04-12 | 2023-05-30 | 2023-05-30 | COMP | 2023-06-09 | COMP | 2023-07-17 | COMP | 2023-10-05 | COMP | 2023-08-31 | COMP | Rule 16 | 34 | 34 | 9 | 25 | 58 |  | 132
41711 | 2023-02-24 | 2023-04-20 | 2023-06-14 | 2023-06-14 | COMP | 2023-06-21 | COMP | 2023-07-07 | COMP | 2023-08-29 | COMP | 2023-10-17 | COMP | Rule 16 | 40 | 39 | 5 | 12 | 38 | 35 | 164
41718 | 2023-02-24 | 2023-04-21 | 2023-06-08 | 2023-06-08 | COMP | 2023-07-11 | COMP | 2023-07-14 | COMP | 2023-08-15 | COMP | 2023-08-29 | COMP | Rule 16 | 41 | 34 | 22 | 4 | 23 | 11 | 130
41738 | 2023-02-24 | 2023-04-25 | 2023-06-16 | 2023-06-16 | COMP | 2023-07-27 | COMP | 2023-07-27 | COMP | 2023-08-03 | COMP | 2023-08-23 | COMP | Rule 16 | 43 | 38 | 28 | 1 | 6 | 15 | 126
41820 | 2023-02-24 | 2023-05-04 | 2023-06-30 | 2023-06-30 | COMP | 2023-07-14 | NOTN | 2023-08-14 | COMP | 2023-07-27 | COMP | 2023-09-29 | COMP | Other | 50 | 40 |  | 31 | 0 | 34 | 152
41889 | 2023-02-24 | 2023-05-12 | 2023-06-15 | 2023-06-15 | COMP | 2023-06-28 | COMP | 2023-08-07 | COMP | 2023-07-17 | COMP | 2023-09-19 | COMP | Rule 16 | 56 | 24 | 9 | 28 | 0 | 31 | 144
41997 | 2023-02-24 | 2023-05-30 | 2023-06-23 | 2023-06-23 | COMP | 2023-07-14 | COMP | 2023-08-02 | COMP | 2023-09-06 | COMP | 2023-09-25 | COMP | Rule 16 | 67 | 18 | 15 | 14 | 25 | 14 | 148
42042 | 2023-02-24 | 2023-06-02 | 2023-06-22 | 2023-07-27 | COMP | 2023-09-01 | COMP | 2023-09-11 | COMP | 2023-06-26 | COMP | 2023-12-21 | COMP | Rule 16 | 70 | 14 | 27 | 6 | 0 | 71 | 208
42081 | 2023-02-24 | 2023-06-07 | 2023-06-22 | 2023-06-22 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP |  | INPR | 2023-11-16 | COMP | Rule 16 | 73 | 11 | 47 | 1 |  |  | 185
41759 | 2023-02-26 | 2023-04-26 | 2023-05-31 | 2023-05-31 | COMP | 2023-06-07 | COMP | 2023-07-21 | COMP | 2023-07-21 | COMP | 2023-08-16 | COMP | Rule 16 | 43 | 25 | 6 | 31 | 1 | 19 | 120
41781 | 2023-02-26 | 2023-04-27 | 2023-05-21 | 2023-08-29 | COMP | 2023-09-05 | COMP | 2023-09-21 | COMP | 2023-09-06 | COMP | 2023-10-27 | COMP | Rule 16 | 44 | 17 | 5 | 13 | 0 | 27 | 171
42374 | 2023-02-26 | 2023-08-14 | 2023-09-09 | 2023-09-09 | COMP | 2023-09-14 | COMP | 2023-10-10 | COMP | 2023-10-24 | COMP | 2023-11-02 | COMP | Rule 16 | 118 | 19 | 4 | 19 | 11 | 8 | 175
41236 | 2023-02-27 | 2023-03-07 | 2023-05-17 | 2023-05-17 | COMP | 2023-07-31 | NOTN | 2023-08-30 | COMP |  | INPR | 2023-12-04 | COMP | Other | 7 | 52 |  | 73 |  |  | 194
41237 | 2023-02-27 | 2023-03-07 | 2023-05-04 | 2023-05-04 | COMP | 2023-05-08 | NOTN | 2023-08-29 | COMP | 2023-05-08 | COMP | 2023-11-14 | COMP | Other | 7 | 43 |  | 81 | 0 | 54 | 182
41265 | 2023-02-27 | 2023-03-08 | 2023-06-05 | 2023-06-05 | COMP | 2023-06-23 | COMP | 2023-06-23 | COMP | 2023-08-29 | COMP | 2023-09-26 | COMP | Rule 16 | 8 | 63 | 14 | 1 | 47 | 20 | 148
41288 | 2023-02-27 | 2023-03-10 | 2023-03-28 | 2023-03-28 | COMP | 2023-06-13 | COMP | 2023-06-13 | COMP | 2023-11-16 | COMP | 2023-11-26 | COMP | Rule 16 | 10 | 13 | 55 | 1 | 109 | 5 | 188
41351 | 2023-02-27 | 2023-03-16 | 2023-05-17 | 2023-05-17 | COMP | 2023-08-01 | COMP | 2023-08-01 | COMP | 2023-11-02 | COMP | 2023-11-21 | COMP | Rule 16 | 14 | 45 | 52 | 1 | 67 | 13 | 187
41401 | 2023-02-27 | 2023-03-22 | 2023-05-31 | 2023-05-31 | COMP | 2023-06-05 | COMP | 2023-07-13 | COMP | 2023-06-12 | COMP | 2023-09-15 | COMP | Rule 16 | 18 | 50 | 4 | 27 | 0 | 46 | 141
41492 | 2023-02-27 | 2023-03-29 | 2023-07-06 | 2023-07-06 | COMP | 2023-10-02 | COMP | 2023-10-02 | COMP | 2023-11-01 | COMP | 2023-12-05 | COMP | Rule 16 | 23 | 69 | 62 | 1 | 23 | 22 | 195
41536 | 2023-02-27 | 2023-04-03 | 2023-06-02 | 2023-06-13 | COMP | 2023-07-14 | COMP | 2023-08-28 | COMP | 2023-08-25 | COMP | 2023-10-11 | COMP | Rule 16 | 26 | 44 | 22 | 32 | 0 | 32 | 159
41586 | 2023-02-27 | 2023-04-07 | 2023-05-11 | 2023-05-11 | COMP | 2023-05-15 | COMP | 2023-07-25 | COMP | 2023-08-09 | COMP | 2023-08-28 | COMP | Rule 16 | 30 | 25 | 3 | 49 | 12 | 14 | 128
41603 | 2023-02-27 | 2023-04-11 | 2023-06-30 | 2023-06-30 | COMP | 2023-07-12 | COMP | 2023-10-09 | COMP | 2023-10-09 | COMP | 2023-11-29 | COMP | Rule 16 | 32 | 57 | 8 | 63 | 1 | 35 | 191
41633 | 2023-02-27 | 2023-04-13 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-09 | COMP | 2023-07-05 | COMP | 2023-08-01 | COMP | 2023-10-09 | COMP | Rule 16 | 34 | 29 | 13 | 17 | 20 | 49 | 157
41660 | 2023-02-27 | 2023-04-17 | 2023-05-01 | 2023-05-01 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP |  | INPR | 2023-12-01 | COMP | Rule 16 | 36 | 11 | 69 | 1 |  |  | 193
41754 | 2023-02-27 | 2023-04-25 | 2023-05-19 | 2023-05-19 | COMP | 2023-07-12 | COMP | 2023-11-21 | COMP | 2023-11-21 | COMP | 2023-12-08 | COMP | Rule 16 | 42 | 19 | 36 | 93 | 1 | 12 | 198
41782 | 2023-02-27 | 2023-04-27 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-06 | COMP | 2023-07-06 | COMP | 2023-07-17 | COMP | 2023-11-07 | COMP | Rule 16 | 44 | 39 | 10 | 1 | 8 | 81 | 178
41790 | 2023-02-27 | 2023-04-28 | 2023-07-13 | 2023-07-13 | COMP | 2023-08-23 | COMP | 2023-09-08 | COMP | 2023-08-24 | COMP | 2023-10-20 | COMP | Rule 16 | 45 | 52 | 30 | 12 | 0 | 31 | 166
41881 | 2023-02-27 | 2023-05-12 | 2023-08-22 | 2023-08-22 | COMP | 2023-10-03 | COMP | 2023-10-03 | COMP | 2023-10-03 | COMP | 2023-10-25 | COMP | Rule 16 | 55 | 70 | 30 | 1 | 1 | 17 | 169
41961 | 2023-02-27 | 2023-05-23 | 2023-06-30 | 2023-06-30 | COMP | 2023-07-12 | COMP | 2023-07-14 | COMP | 2023-07-26 | COMP | 2023-08-21 | COMP | Rule 15/16 | 62 | 27 | 8 | 3 | 9 | 19 | 123
42116 | 2023-02-27 | 2023-06-12 | 2023-07-25 | 2023-07-25 | COMP | 2023-09-25 | COMP | 2023-10-17 | COMP | 2023-09-25 | COMP | 2023-12-20 | COMP | Rule 16 | 75 | 30 | 44 | 17 | 0 | 44 | 206
42179 | 2023-02-27 | 2023-06-27 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-23 | COMP | 2023-08-23 | COMP | 2023-09-12 | COMP | 2023-10-18 | COMP | Rule 16 | 85 | 27 | 15 | 1 | 14 | 27 | 164
41184 | 2023-02-28 | 2023-02-28 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-07 | NOTN | 2023-07-24 | COMP | 2023-07-07 | COMP | 2023-10-13 | COMP | Other | 1 | 91 |  | 12 | 0 | 59 | 160
41301 | 2023-02-28 | 2023-03-11 | 2023-08-14 | 2023-08-14 | COMP | 2023-08-25 | COMP | 2023-10-26 | COMP |  | INPR | 2023-12-15 | COMP | Rule 16 | 9 | 108 | 10 | 44 |  |  | 202
41454 | 2023-02-28 | 2023-03-27 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-29 | COMP | 2023-06-29 | COMP | 2023-07-13 | COMP | 2023-11-16 | COMP | Rule 16 | 20 | 60 | 8 | 1 | 10 | 89 | 183
41478 | 2023-02-28 | 2023-03-28 | 2023-04-25 | 2023-04-25 | COMP | 2023-05-12 | NOTN | 2023-05-12 | COMP | 2023-05-15 | COMP | 2023-07-21 | COMP | Other | 21 | 21 |  | 14 | 2 | 47 | 101
41493 | 2023-02-28 | 2023-03-29 | 2023-06-04 | 2023-06-04 | COMP | 2023-06-12 | COMP | 2023-06-12 | COMP | 2023-06-14 | COMP | 2023-07-28 | COMP | Rule 15/16 | 22 | 47 | 6 | 1 | 3 | 31 | 106
41606 | 2023-02-28 | 2023-04-12 | 2023-06-08 | 2023-06-08 | COMP | 2023-06-30 | COMP | 2023-06-30 | COMP | 2023-08-01 | COMP | 2023-10-12 | COMP | Rule 15/16 | 32 | 41 | 16 | 1 | 22 | 52 | 159
41642 | 2023-02-28 | 2023-04-14 | 2023-05-12 | 2023-05-12 | COMP | 2023-05-17 | COMP | 2023-05-23 | COMP | 2023-06-08 | COMP | 2023-07-07 | COMP | Rule 16 | 34 | 21 | 4 | 5 | 12 | 20 | 91
41649 | 2023-02-28 | 2023-04-14 | 2023-05-24 | 2023-06-06 | COMP | 2023-06-12 | COMP | 2023-06-14 | COMP | 2023-10-04 | COMP | 2023-11-08 | COMP | Rule 16 | 34 | 29 | 5 | 3 | 78 | 26 | 178
41719 | 2023-02-28 | 2023-04-21 | 2023-06-26 | 2023-06-26 | COMP | 2023-07-14 | COMP | 2023-08-14 | COMP |  | INPR | 2023-11-03 | COMP | Rule 16 | 39 | 45 | 14 | 22 |  |  | 175
41755 | 2023-02-28 | 2023-04-25 | 2023-08-30 | 2023-08-30 | COMP | 2023-09-05 | COMP | 2023-10-25 | COMP | 2023-10-24 | COMP | 2023-12-30 | COMP | Rule 16 | 41 | 89 | 4 | 37 | 0 | 44 | 211
42050 | 2023-02-28 | 2023-06-05 | 2023-08-03 | 2023-08-03 | COMP | 2023-09-22 | COMP | 2023-12-05 | COMP |  | INPR | 2023-12-29 | COMP | Rule 16 | 69 | 42 | 36 | 50 |  |  | 211
42073 | 2023-02-28 | 2023-06-06 | 2023-07-14 | 2023-07-14 | COMP | 2023-08-30 | COMP | 2023-09-01 | COMP | 2023-08-31 | COMP | 2023-10-25 | COMP | Rule 16 | 70 | 27 | 34 | 3 | 0 | 38 | 168
42141 | 2023-02-28 | 2023-06-20 | 2023-07-06 | 2023-07-06 | COMP | 2023-09-07 | COMP | 2023-09-07 | COMP |  | INPR | 2023-11-03 | COMP | Rule 16 | 79 | 12 | 45 | 1 |  |  | 175
42340 | 2023-02-28 | 2023-08-03 | 2023-09-06 | 2023-09-06 | COMP | 2023-09-18 | COMP |  | REQD | 2023-12-13 | COMP | 2023-12-28 | COMP | Rule 16 | 110 | 24 | 9 |  |  |  | 210
41358 | 2023-03-01 | 2023-03-16 | 2023-06-22 | 2023-06-22 | COMP | 2023-06-26 | COMP | 2023-08-24 | COMP | 2023-08-18 | COMP | 2023-12-15 | COMP | Rule 16 | 12 | 69 | 3 | 43 | 0 | 78 | 201
41388 | 2023-03-01 | 2023-03-20 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-08 | COMP | 2023-06-13 | COMP | 2023-06-12 | COMP | 2023-06-19 | COMP | Rule 15/16 | 14 | 47 | 12 | 4 | 0 | 4 | 77
41453 | 2023-03-01 | 2023-03-27 | 2023-06-10 | 2023-06-10 | COMP | 2023-06-26 | COMP | 2023-07-31 | COMP | 2023-07-28 | COMP | 2023-10-24 | COMP | Rule 16 | 19 | 54 | 10 | 25 | 0 | 61 | 166
41548 | 2023-03-01 | 2023-04-04 | 2023-06-20 | 2023-06-20 | COMP | 2023-06-26 | COMP | 2023-12-04 | COMP | 2023-07-10 | COMP | 2023-12-26 | COMP | Rule 16 | 25 | 54 | 5 | 111 | 0 | 16 | 207
41620 | 2023-03-01 | 2023-04-13 | 2023-05-16 | 2023-05-16 | COMP | 2023-05-24 | NOTN | 2023-05-24 | COMP | 2023-05-24 | COMP | 2023-10-09 | COMP | Other | 32 | 24 |  | 7 | 1 | 95 | 155
41691 | 2023-03-01 | 2023-04-19 | 2023-05-17 | 2023-05-17 | COMP | 2023-05-24 | COMP | 2023-06-30 | COMP | 2023-05-24 | COMP | 2023-07-26 | COMP | Rule 16 | 36 | 21 | 6 | 26 | 0 | 18 | 103
41802 | 2023-03-01 | 2023-05-02 | 2023-06-21 | 2023-06-21 | COMP | 2023-09-06 | COMP | 2023-09-06 | COMP | 2023-09-06 | COMP | 2023-10-18 | COMP | Rule 16 | 45 | 35 | 54 | 1 | 1 | 31 | 162
41986 | 2023-03-01 | 2023-05-25 | 2023-07-29 | 2023-07-29 | COMP | 2023-10-03 | COMP | 2023-10-03 | COMP | 2023-10-03 | COMP | 2023-11-14 | COMP | Rule 16 | 62 | 44 | 46 | 1 | 1 | 30 | 180
41993 | 2023-03-01 | 2023-05-26 | 2023-06-30 | 2023-06-30 | COMP | 2023-07-10 | NOTN | 2023-07-10 | COMP | 2023-07-10 | COMP | 2023-09-05 | COMP | Other | 63 | 24 |  | 6 | 1 | 41 | 131
41994 | 2023-03-01 | 2023-05-26 | 2023-07-14 | 2023-07-14 | COMP | 2023-07-20 | COMP | 2023-08-24 | COMP | 2023-11-28 | COMP | 2023-12-15 | COMP | Rule 16 | 63 | 33 | 5 | 26 | 65 | 14 | 201
42220 | 2023-03-01 | 2023-07-05 | 2023-09-13 | 2023-09-13 | COMP | 2023-09-20 | COMP | 2023-10-13 | COMP | 2023-10-16 | COMP | 2023-11-08 | COMP | Rule 16 | 88 | 50 | 6 | 18 | 2 | 18 | 177
41411 | 2023-03-02 | 2023-03-23 | 2023-06-02 | 2023-06-02 | COMP | 2023-06-08 | COMP | 2023-09-05 | COMP | 2023-08-22 | COMP | 2023-09-26 | COMP | Rule 16 | 16 | 51 | 5 | 61 | 0 | 16 | 145
41556 | 2023-03-02 | 2023-04-04 | 2023-06-09 | 2023-06-09 | COMP | 2023-06-30 | COMP | 2023-08-24 | COMP | 2023-06-30 | COMP | 2023-09-14 | COMP | Rule 16 | 24 | 48 | 15 | 39 | 0 | 15 | 137
41612 | 2023-03-02 | 2023-04-12 | 2023-06-01 | 2023-06-01 | COMP | 2023-06-08 | COMP | 2023-07-20 | COMP | 2023-09-17 | COMP | 2023-10-23 | COMP | Rule 16 | 30 | 36 | 6 | 29 | 41 | 26 | 164
41641 | 2023-03-02 | 2023-04-14 | 2023-05-11 | 2023-05-26 | COMP | 2023-06-01 | COMP | 2023-07-05 | COMP | 2023-07-17 | COMP | 2023-09-22 | COMP | Rule 16 | 32 | 20 | 4 | 23 | 9 | 49 | 143
41665 | 2023-03-02 | 2023-04-17 | 2023-06-13 | 2023-06-13 | COMP | 2023-06-30 | COMP | 2023-06-30 | COMP | 2023-06-30 | COMP | 2023-09-18 | COMP | Rule 16 | 33 | 41 | 13 | 1 | 1 | 55 | 139
41680 | 2023-03-02 | 2023-04-18 | 2023-05-08 | 2023-05-08 | COMP | 2023-05-22 | NOTN | 2023-08-02 | COMP | 2023-09-19 | COMP | 2023-11-06 | COMP | Other | 34 | 15 |  | 60 | 34 | 35 | 174
41768 | 2023-03-02 | 2023-04-26 | 2023-06-27 | 2023-06-27 | COMP | 2023-07-11 | COMP | 2023-07-27 | COMP | 2023-07-11 | COMP | 2023-08-14 | COMP | Rule 16 | 40 | 43 | 10 | 13 | 0 | 13 | 115
41898 | 2023-03-02 | 2023-05-15 | 2023-08-22 | 2023-08-22 | COMP | 2023-08-28 | COMP | 2023-09-15 | COMP | 2023-10-09 | COMP | 2023-10-24 | COMP | Rule 16 | 53 | 69 | 5 | 14 | 17 | 12 | 165
42245 | 2023-03-02 | 2023-07-11 | 2023-08-11 | 2023-08-11 | COMP | 2023-08-22 | COMP | 2023-08-22 | COMP | 2023-10-19 | COMP | 2023-10-20 | COMP | Rule 16 | 91 | 24 | 8 | 1 | 42 | 2 | 163
42251 | 2023-03-02 | 2023-07-11 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-14 | COMP | 2023-08-14 | COMP | 2023-10-02 | COMP | 2023-11-09 | COMP | Rule 16 | 91 | 15 | 11 | 1 | 35 | 29 | 177
41254 | 2023-03-03 | 2023-03-07 | 2023-03-15 | 2023-03-15 | COMP | 2023-04-12 | COMP | 2023-06-07 | COMP | 2023-07-20 | COMP | 2023-08-07 | COMP | Rule 16 | 3 | 7 | 21 | 40 | 30 | 13 | 109
41282 | 2023-03-03 | 2023-03-09 | 2023-05-01 | 2023-05-01 | COMP | 2023-05-04 | COMP | 2023-07-25 | COMP | 2023-07-28 | COMP | 2023-08-25 | COMP | Rule 16 | 5 | 38 | 4 | 56 | 4 | 21 | 123
41410 | 2023-03-03 | 2023-03-23 | 2023-05-16 | 2023-05-16 | COMP | 2023-06-08 | COMP | 2023-06-08 | COMP | 2023-08-21 | COMP | 2023-09-11 | COMP | Rule 16 | 15 | 39 | 17 | 1 | 51 | 15 | 133
41423 | 2023-03-03 | 2023-03-23 | 2023-05-24 | 2023-05-24 | COMP | 2023-07-17 | COMP | 2023-08-30 | COMP | 2023-07-17 | COMP | 2023-10-12 | COMP | Rule 16 | 15 | 45 | 36 | 33 | 0 | 31 | 156
41645 | 2023-03-03 | 2023-04-14 | 2023-06-16 | 2023-06-16 | COMP | 2023-06-27 | COMP |  | REQD | 2023-10-26 | COMP | 2023-12-02 | COMP | Rule 16 | 31 | 45 | 7 |  |  |  | 189
41655 | 2023-03-03 | 2023-04-14 | 2023-05-28 | 2023-05-28 | COMP | 2023-08-03 | COMP | 2023-08-03 | COMP | 2023-08-29 | COMP | 2023-10-09 | COMP | Rule 16 | 31 | 31 | 46 | 1 | 19 | 29 | 153
41766 | 2023-03-03 | 2023-04-26 | 2023-07-14 | 2023-07-14 | COMP | 2023-07-26 | COMP | 2023-07-26 | COMP | 2023-08-23 | COMP | 2023-10-04 | COMP | Rule 15/16 | 39 | 55 | 9 | 1 | 21 | 30 | 150
41811 | 2023-03-03 | 2023-05-03 | 2023-06-24 | 2023-06-24 | COMP | 2023-10-04 | COMP | 2023-10-04 | COMP | 2023-10-09 | COMP | 2023-11-08 | COMP | Rule 16 | 44 | 36 | 71 | 1 | 4 | 23 | 175
42025 | 2023-03-03 | 2023-06-01 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-20 | COMP | 2023-07-27 | COMP | 2023-08-24 | COMP | 2023-12-07 | COMP | Rule 16 | 64 | 26 | 9 | 6 | 21 | 72 | 193
41678 | 2023-03-04 | 2023-04-18 | 2023-06-08 | 2023-06-08 | COMP | 2023-06-13 | COMP | 2023-08-08 | COMP | 2023-08-22 | COMP | 2023-11-06 | COMP | Rule 16 | 32 | 37 | 4 | 39 | 11 | 54 | 172
42106 | 2023-03-05 | 2023-06-12 | 2023-07-19 | 2023-07-19 | COMP | 2023-07-21 | COMP | 2023-08-08 | COMP | 2023-10-03 | COMP | 2023-10-11 | COMP | Rule 16 | 70 | 26 | 3 | 13 | 40 | 7 | 154
41264 | 2023-03-06 | 2023-03-08 | 2023-06-14 | 2023-06-14 | COMP | 2023-06-20 | COMP | 2023-06-28 | COMP | 2023-07-11 | COMP | 2023-08-14 | COMP | Rule 16 | 3 | 70 | 4 | 7 | 9 | 25 | 113
41488 | 2023-03-06 | 2023-03-29 | 2023-08-29 | 2023-09-18 | COMP | 2023-08-29 | NOTN | 2023-10-03 | COMP | 2023-08-29 | COMP | 2023-12-15 | COMP | Other | 18 | 107 |  | 12 | 0 | 51 | 198
41571 | 2023-03-06 | 2023-04-05 | 2023-06-16 | 2023-06-16 | COMP | 2023-07-24 | COMP | 2023-07-24 | COMP | 2023-08-22 | COMP | 2023-09-25 | COMP | Rule 16 | 23 | 52 | 25 | 1 | 22 | 24 | 142
41601 | 2023-03-06 | 2023-04-11 | 2023-05-10 | 2023-05-15 | COMP | 2023-08-22 | COMP | 2023-08-22 | COMP | 2023-08-17 | COMP | 2023-09-10 | COMP | Rule 16 | 27 | 22 | 69 | 1 | 0 | 13 | 131
41698 | 2023-03-06 | 2023-04-20 | 2023-08-17 | 2023-08-17 | COMP | 2023-09-29 | COMP | 2023-09-29 | COMP | 2023-11-15 | COMP | 2023-11-30 | COMP | Rule 16 | 34 | 83 | 31 | 1 | 33 | 10 | 187
41722 | 2023-03-06 | 2023-04-21 | 2023-07-14 | 2023-07-14 | COMP | 2023-07-20 | COMP | 2023-07-31 | COMP | 2023-08-28 | COMP | 2023-11-08 | COMP | Rule 16 | 35 | 58 | 5 | 8 | 21 | 52 | 174
41764 | 2023-03-06 | 2023-04-27 | 2023-06-08 | 2023-06-08 | COMP | 2023-08-01 | COMP | 2023-08-01 | COMP |  | INPR | 2023-12-05 | COMP | Rule 16 | 39 | 30 | 37 | 1 |  |  | 190
41794 | 2023-03-06 | 2023-05-01 | 2023-06-14 | 2023-06-14 | COMP | 2023-06-21 | COMP | 2023-08-01 | COMP | 2023-08-29 | COMP | 2023-10-03 | COMP | Rule 15/16 | 41 | 32 | 5 | 29 | 21 | 25 | 148
41804 | 2023-03-06 | 2023-05-02 | 2023-06-19 | 2023-06-19 | COMP | 2023-06-30 | COMP | 2023-07-11 | COMP | 2023-08-07 | COMP | 2023-09-13 | COMP | Rule 15/16 | 42 | 33 | 9 | 7 | 20 | 27 | 134
41824 | 2023-03-06 | 2023-05-04 | 2023-06-16 | 2023-06-16 | COMP | 2023-07-10 | COMP | 2023-07-10 | COMP | 2023-07-26 | COMP | 2023-09-21 | COMP | Rule 16 | 44 | 31 | 15 | 1 | 13 | 41 | 140
41832 | 2023-03-06 | 2023-05-04 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-04 | NOTN | 2023-10-10 | COMP | 2023-10-24 | COMP | 2023-12-12 | COMP | Other | 44 | 64 |  | 47 | 11 | 33 | 195
41833 | 2023-03-06 | 2023-05-04 | 2023-06-05 | 2023-06-05 | COMP |  | REQD |  | REQD |  | REQD | 2023-05-09 | COMP | Rule 16 | 44 | 22 |  |  |  |  | 47
41974 | 2023-03-06 | 2023-05-24 | 2023-08-07 | 2023-08-07 | COMP | 2023-08-11 | COMP | 2023-08-11 | COMP | 2023-10-18 | COMP | 2023-11-03 | COMP | Rule 16 | 58 | 51 | 5 | 1 | 48 | 13 | 171
42002 | 2023-03-06 | 2023-05-30 | 2023-08-23 | 2023-08-23 | COMP | 2023-09-07 | COMP | 2023-10-10 | COMP | 2023-11-07 | COMP | 2023-12-12 | COMP | Rule 16 | 61 | 60 | 11 | 24 | 21 | 23 | 195
42043 | 2023-03-06 | 2023-06-02 | 2023-07-28 | 2023-07-28 | COMP | 2023-08-03 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-11-30 | COMP | Rule 16 | 64 | 39 | 5 | 4 | 1 | 79 | 187
42130 | 2023-03-06 | 2023-06-14 | 2023-07-31 | 2023-08-21 | COMP | 2023-09-07 | COMP | 2023-10-11 | COMP | 2023-09-11 | COMP | 2023-12-01 | COMP | Rule 16 | 72 | 32 | 13 | 25 | 0 | 35 | 188
41296 | 2023-03-07 | 2023-03-10 | 2023-04-06 | 2023-04-06 | COMP | 2023-04-07 | NOTN | 2023-04-07 | COMP | 2023-04-07 | COMP | 2023-09-13 | COMP | Other | 4 | 20 |  | 2 | 1 | 110 | 133
41716 | 2023-03-07 | 2023-04-21 | 2023-05-21 | 2023-05-21 | COMP | 2023-05-24 | COMP | 2023-07-10 | COMP |  | INPR | 2023-09-07 | COMP | Rule 16 | 34 | 21 | 3 | 31 |  |  | 129
41783 | 2023-03-07 | 2023-04-28 | 2023-07-14 | 2023-07-14 | COMP | 2023-08-29 | COMP | 2023-10-18 | COMP | 2023-10-19 | COMP | 2023-12-20 | COMP | Rule 16 | 39 | 53 | 33 | 36 | 2 | 42 | 200
41858 | 2023-03-07 | 2023-05-08 | 2023-06-14 | 2023-06-30 | COMP | 2023-07-10 | COMP | 2023-08-09 | COMP | 2023-07-15 | COMP | 2023-10-23 | COMP | Rule 16 | 45 | 27 | 6 | 23 | 0 | 53 | 161
41929 | 2023-03-07 | 2023-05-19 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-28 | COMP | 2023-09-07 | COMP | 2023-10-09 | COMP | 2023-11-20 | COMP | Rule 16 | 54 | 49 | 21 | 8 | 23 | 30 | 180
41973 | 2023-03-07 | 2023-05-24 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-11 | COMP | 2023-09-08 | COMP | 2023-07-11 | COMP | 2023-10-17 | COMP | Rule 16 | 57 | 30 | 3 | 43 | 0 | 28 | 157
41987 | 2023-03-07 | 2023-05-25 | 2023-08-24 | 2023-08-24 | COMP | 2023-10-10 | COMP | 2023-10-26 | COMP | 2023-10-22 | COMP | 2023-11-27 | COMP | Rule 15/16 | 58 | 63 | 33 | 13 | 0 | 20 | 183
42123 | 2023-03-07 | 2023-06-12 | 2023-07-13 | 2023-07-13 | COMP | 2023-07-27 | COMP | 2023-09-01 | COMP | 2023-09-19 | COMP | 2023-10-30 | COMP | Rule 16 | 69 | 22 | 11 | 27 | 12 | 30 | 166
41327 | 2023-03-08 | 2023-03-14 | 2023-05-16 | 2023-05-16 | COMP | 2023-06-08 | COMP | 2023-09-07 | COMP |  | INPR | 2023-11-20 | COMP | Rule 16 | 5 | 46 | 17 | 63 |  |  | 179
41398 | 2023-03-08 | 2023-03-22 | 2023-05-18 | 2023-10-17 | COMP | 2023-10-23 | COMP | 2023-10-24 | COMP | 2023-08-18 | COMP | 2023-11-13 | COMP | Rule 15/16 | 11 | 42 | 5 | 2 | 0 | 14 | 174
41535 | 2023-03-08 | 2023-04-03 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-19 | COMP | 2023-05-19 | COMP | 2023-05-19 | COMP | 2023-06-14 | COMP | Rule 16 | 19 | 22 | 14 | 1 | 1 | 18 | 70
41551 | 2023-03-08 | 2023-04-04 | 2023-05-16 | 2023-05-16 | COMP | 2023-05-26 | COMP | 2023-07-25 | INPR | 2023-07-18 | COMP | 2023-07-29 | COMP | Rule 16 | 20 | 31 | 9 |  |  |  | 100
41565 | 2023-03-08 | 2023-04-05 | 2023-05-24 | 2023-05-24 | COMP | 2023-06-16 | COMP | 2023-06-16 | COMP | 2023-07-03 | COMP | 2023-08-04 | COMP | Rule 15/16 | 21 | 36 | 17 | 1 | 11 | 24 | 105
41661 | 2023-03-08 | 2023-04-17 | 2023-06-21 | 2023-06-21 | COMP | 2023-06-26 | COMP | 2023-06-30 | COMP | 2023-07-12 | COMP | 2023-09-14 | COMP | Rule 16 | 29 | 46 | 4 | 5 | 8 | 46 | 133
41742 | 2023-03-08 | 2023-04-25 | 2023-06-29 | 2023-06-29 | COMP | 2023-08-21 | COMP | 2023-08-31 | INPR |  | INPR | 2023-09-14 | COMP | Rule 16 | 35 | 46 | 37 |  |  |  | 133
41762 | 2023-03-08 | 2023-04-26 | 2023-07-06 | 2023-07-06 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-10-20 | COMP | 2023-11-30 | COMP | Rule 16 | 36 | 49 | 53 | 1 | 24 | 27 | 185
41830 | 2023-03-08 | 2023-05-05 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-03 | COMP | 2023-07-03 | COMP | 2023-10-02 | COMP | 2023-11-06 | COMP | Rule 16 | 43 | 33 | 8 | 1 | 64 | 26 | 170
41875 | 2023-03-08 | 2023-05-10 | 2023-08-29 | 2023-08-29 | COMP | 2023-09-26 | NOTN | 2023-10-19 | COMP | 2023-09-12 | COMP | 2023-11-07 | COMP | Other | 46 | 77 |  | 37 | 0 | 14 | 171
41933 | 2023-03-08 | 2023-05-19 | 2023-06-28 | 2023-06-28 | COMP | 2023-07-31 | COMP | 2023-07-31 | COMP | 2023-08-29 | COMP | 2023-09-18 | COMP | Rule 16 | 53 | 27 | 23 | 1 | 22 | 14 | 135
41934 | 2023-03-08 | 2023-05-19 | 2023-06-28 | 2023-06-28 | COMP | 2023-07-13 | COMP | 2023-07-13 | COMP | 2023-08-29 | COMP | 2023-09-18 | COMP | Rule 16 | 53 | 27 | 11 | 1 | 34 | 14 | 135
41940 | 2023-03-08 | 2023-05-20 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-11 | COMP | 2023-07-18 | COMP | 2023-07-19 | COMP | 2023-12-19 | COMP | Rule 16 | 53 | 22 | 13 | 6 | 2 | 106 | 198
42037 | 2023-03-08 | 2023-06-02 | 2023-06-24 | 2023-06-24 | COMP | 2023-07-31 | COMP | 2023-07-31 | COMP | 2023-11-22 | COMP | 2023-11-14 | COMP | Rule 16 | 62 | 15 | 25 | 1 | 81 |  | 175
42084 | 2023-03-08 | 2023-06-08 | 2023-07-20 | 2023-07-20 | COMP | 2023-10-30 | COMP | 2023-10-30 | COMP | 2023-11-01 | COMP | 2023-11-30 | COMP | Rule 16 | 66 | 29 | 72 | 1 | 3 | 19 | 185
42194 | 2023-03-08 | 2023-06-29 | 2023-08-12 | 2023-08-12 | COMP | 2023-08-24 | COMP | 2023-08-24 | COMP | 2023-08-31 | COMP | 2023-10-25 | COMP | Rule 16 | 80 | 31 | 9 | 1 | 6 | 39 | 162
42238 | 2023-03-08 | 2023-07-10 | 2023-07-25 | 2023-07-25 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP | 2023-10-10 | COMP | 2023-10-30 | COMP | Rule 16 | 86 | 12 | 10 | 1 | 46 | 15 | 165
42289 | 2023-03-08 | 2023-07-21 | 2023-08-30 | 2023-08-30 | COMP | 2023-09-07 | COMP | 2023-09-15 | COMP | 2023-11-03 | COMP | 2023-11-10 | COMP | Rule 16 | 95 | 29 | 6 | 7 | 36 | 5 | 173
42305 | 2023-03-08 | 2023-07-26 | 2023-08-08 | 2023-08-08 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP | 2023-08-21 | COMP | Rule 16 | 98 | 10 | 6 | 1 | 1 | 5 | 116
41557 | 2023-03-09 | 2023-04-04 | 2023-04-28 | 2023-04-28 | COMP | 2023-05-17 | COMP | 2023-07-10 | COMP |  | INPR | 2023-10-27 | COMP | Rule 16 | 19 | 19 | 14 | 36 |  |  | 163
41598 | 2023-03-09 | 2023-04-11 | 2023-05-18 | 2023-05-18 | COMP | 2023-06-16 | COMP | 2023-06-21 | COMP | 2023-07-07 | COMP | 2023-08-15 | COMP | Rule 16 | 24 | 28 | 21 | 3 | 12 | 28 | 111
41650 | 2023-03-09 | 2023-04-14 | 2023-09-25 | 2023-09-25 | COMP | 2023-10-02 | COMP | 2023-10-10 | COMP | 2023-10-06 | COMP | 2023-11-20 | COMP | Rule 16 | 27 | 113 | 6 | 7 | 0 | 29 | 178
41690 | 2023-03-09 | 2023-04-19 | 2023-06-14 | 2023-06-14 | COMP | 2023-06-20 | COMP | 2023-06-20 | COMP | 2023-06-20 | COMP | 2023-08-18 | COMP | Rule 16 | 30 | 40 | 4 | 1 | 1 | 43 | 114
41859 | 2023-03-09 | 2023-05-09 | 2023-06-23 | 2023-06-23 | COMP | 2023-07-13 | COMP | 2023-08-08 | COMP | 2023-06-29 | COMP | 2023-09-12 | COMP | Rule 16 | 44 | 32 | 14 | 19 | 0 | 25 | 130
41942 | 2023-03-09 | 2023-05-20 | 2023-06-15 | 2023-06-15 | COMP | 2023-06-22 | COMP | 2023-06-26 | COMP | 2023-07-31 | COMP | 2023-07-31 | COMP | Rule 16 | 52 | 18 | 5 | 3 | 25 | 1 | 100
42109 | 2023-03-09 | 2023-06-12 | 2023-07-14 | 2023-07-14 | COMP | 2023-08-23 | COMP | 2023-08-23 | COMP | 2023-09-19 | COMP | 2023-11-30 | COMP | Rule 16 | 67 | 23 | 29 | 1 | 19 | 50 | 184
42151 | 2023-03-09 | 2023-06-21 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-26 | COMP | 2023-09-07 | COMP | 2023-10-03 | COMP | 2023-11-29 | COMP | Rule 16 | 73 | 13 | 13 | 31 | 19 | 39 | 183
42336 | 2023-03-09 | 2023-08-02 | 2023-09-05 | 2023-09-05 | COMP | 2023-09-15 | COMP | 2023-09-15 | INPR | 2023-10-31 | COMP | 2023-11-30 | COMP | Rule 16 | 102 | 24 | 9 |  |  |  | 184
41495 | 2023-03-10 | 2023-03-29 | 2023-04-18 | 2023-04-18 | COMP | 2023-04-27 | COMP | 2023-07-18 | COMP | 2023-04-27 | COMP | 2023-08-01 | COMP | Rule 16 | 14 | 15 | 8 | 56 | 0 | 11 | 100
41587 | 2023-03-10 | 2023-04-07 | 2023-06-13 | 2023-06-13 | COMP | 2023-06-14 | NOTN | 2023-06-22 | COMP | 2023-10-10 | COMP | 2023-10-10 | COMP | Other | 21 | 47 |  | 7 | 77 | 1 | 149
41611 | 2023-03-10 | 2023-04-12 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-20 | COMP | 2023-07-18 | COMP | 2023-08-26 | COMP | 2023-11-30 | COMP | Rule 16 | 24 | 30 | 19 | 20 | 29 | 65 | 183
41770 | 2023-03-10 | 2023-04-27 | 2023-07-03 | 2023-07-03 | COMP | 2023-07-25 | COMP | 2023-07-25 | COMP | 2023-07-25 | COMP | 2023-10-05 | COMP | Rule 16 | 35 | 46 | 16 | 1 | 1 | 52 | 146
41777 | 2023-03-10 | 2023-04-27 | 2023-07-13 | 2023-07-13 | COMP | 2023-07-15 | NOTN | 2023-08-28 | COMP | 2023-08-30 | COMP | 2023-10-24 | COMP | Other | 35 | 53 |  | 33 | 3 | 39 | 159
41884 | 2023-03-10 | 2023-05-11 | 2023-06-07 | 2023-06-07 | COMP | 2023-09-22 | COMP | 2023-09-22 | INPR | 2023-10-12 | COMP | 2023-11-10 | COMP | Rule 16 | 45 | 19 | 75 |  |  |  | 171
41906 | 2023-03-10 | 2023-05-16 | 2023-06-23 | 2023-06-23 | COMP | 2023-07-03 | COMP | 2023-08-15 | COMP | 2023-09-14 | COMP | 2023-11-06 | COMP | Rule 15/16 | 48 | 27 | 7 | 31 | 22 | 38 | 168
41909 | 2023-03-10 | 2023-05-16 | 2023-08-15 | 2023-08-15 | COMP | 2023-08-18 | COMP | 2023-10-02 | COMP |  | INPR | 2023-12-07 | COMP | Rule 16 | 48 | 63 | 4 | 31 |  |  | 188
41926 | 2023-03-10 | 2023-05-18 | 2023-06-21 | 2023-07-07 | COMP | 2023-06-22 | NOTN | 2023-07-11 | COMP | 2023-06-22 | COMP | 2023-08-05 | COMP | Other | 50 | 23 |  | 3 | 0 | 19 | 103
41971 | 2023-03-10 | 2023-05-24 | 2023-08-18 | 2023-08-18 | COMP | 2023-08-25 | COMP | 2023-10-21 | COMP | 2023-10-03 | COMP | 2023-12-04 | COMP | Rule 16 | 54 | 60 | 6 | 40 | 0 | 28 | 185
42132 | 2023-03-10 | 2023-06-14 | 2023-10-03 | 2023-10-03 | COMP | 2023-10-05 | COMP |  | REQD | 2023-11-22 | COMP | 2023-12-04 | COMP | Rule 16 | 68 | 77 | 3 |  |  |  | 185
42274 | 2023-03-10 | 2023-07-18 | 2023-08-07 | 2023-08-07 | COMP | 2023-09-25 | COMP | 2023-10-17 | COMP | 2023-10-03 | COMP | 2023-11-30 | COMP | Rule 16 | 90 | 15 | 35 | 17 | 0 | 30 | 183
41616 | 2023-03-11 | 2023-04-12 | 2023-07-03 | 2023-07-03 | COMP | 2023-07-17 | COMP | 2023-07-17 | COMP | 2023-09-20 | COMP | 2023-10-07 | COMP | Rule 16 | 23 | 57 | 10 | 1 | 47 | 13 | 146
42055 | 2023-03-11 | 2023-06-05 | 2023-08-23 | 2023-08-23 | COMP | 2023-09-11 | COMP | 2023-10-14 | COMP | 2023-11-13 | COMP | 2023-12-27 | COMP | Rule 16 | 60 | 56 | 13 | 25 | 20 | 30 | 200
41756 | 2023-03-12 | 2023-04-26 | 2023-05-12 | 2023-05-12 | COMP | 2023-10-09 | COMP | 2023-10-09 | COMP | 2023-11-14 | COMP | 2023-11-28 | COMP | Rule 16 | 33 | 13 | 103 | 1 | 26 | 9 | 180
41362 | 2023-03-13 | 2023-03-16 | 2023-06-02 | 2023-06-02 | COMP | 2023-08-07 | COMP | 2023-07-25 | COMP | 2023-06-28 | COMP | 2023-10-10 | COMP | Rule 16 | 4 | 56 | 45 |  | 0 | 55 | 148
41617 | 2023-03-13 | 2023-04-12 | 2023-04-25 | 2023-04-25 | COMP | 2023-09-25 | COMP | 2023-09-25 | COMP | 2023-10-27 | COMP | 2023-10-27 | COMP | Rule 16 | 23 | 10 | 106 | 1 | 25 | 1 | 161
41714 | 2023-03-13 | 2023-04-21 | 2023-05-06 | 2023-05-06 | COMP | 2023-05-18 | COMP | 2023-05-18 | COMP | 2023-11-15 | COMP | 2023-11-27 | COMP | Rule 16 | 30 | 11 | 9 | 1 | 125 | 7 | 179
41741 | 2023-03-13 | 2023-04-24 | 2023-08-16 | 2023-08-16 | COMP | 2023-08-16 | NOTN | 2023-08-28 | COMP | 2023-08-16 | COMP | 2023-10-20 | COMP | Other | 31 | 80 |  | 9 | 0 | 39 | 156
41851 | 2023-03-13 | 2023-05-08 | 2023-07-21 | 2023-07-26 | COMP | 2023-10-05 | COMP | 2023-10-05 | COMP | 2023-10-16 | COMP | 2023-11-20 | COMP | Rule 16 | 41 | 52 | 51 | 1 | 8 | 25 | 176
41861 | 2023-03-13 | 2023-05-09 | 2023-06-28 | 2023-06-28 | COMP | 2023-06-29 | NOTN | 2023-06-30 | COMP | 2023-07-05 | COMP | 2023-08-28 | COMP | Other | 42 | 35 |  | 3 | 3 | 39 | 118
41868 | 2023-03-13 | 2023-05-10 | 2023-06-03 | 2023-06-08 | COMP | 2023-06-30 | COMP | 2023-07-25 | COMP | 2023-08-21 | COMP | 2023-09-25 | COMP | Rule 16 | 43 | 17 | 16 | 17 | 20 | 25 | 137
41896 | 2023-03-13 | 2023-05-15 | 2023-07-12 | 2023-07-12 | COMP | 2023-08-23 | COMP | 2023-08-23 | COMP | 2023-12-18 | COMP | 2023-12-22 | COMP | Rule 16 | 46 | 40 | 31 | 1 | 80 | 5 | 198
41964 | 2023-03-13 | 2023-05-24 | 2023-06-27 | 2023-06-27 | COMP | 2023-07-06 | NOTN | 2023-08-14 | COMP | 2023-07-06 | COMP | 2023-11-20 | COMP | Other | 53 | 23 |  | 34 | 0 | 69 | 176
42250 | 2023-03-13 | 2023-07-12 | 2023-08-09 | 2023-09-01 | COMP | 2023-09-27 | COMP |  | REQD | 2023-10-23 | COMP | 2023-11-21 | COMP | Rule 16 | 85 | 21 | 18 |  |  |  | 177
41500 | 2023-03-14 | 2023-03-29 | 2023-06-17 | 2023-06-17 | COMP | 2023-06-27 | COMP | 2023-08-07 | COMP | 2023-07-31 | COMP | 2023-10-29 | COMP | Rule 16 | 12 | 57 | 6 | 29 | 0 | 59 | 160
41584 | 2023-03-14 | 2023-04-06 | 2023-04-19 | 2023-04-19 | COMP | 2023-04-19 | NOTN | 2023-04-19 | COMP | 2023-06-12 | COMP | 2023-06-20 | COMP | Other | 18 | 10 |  | 1 | 38 | 6 | 69
41591 | 2023-03-14 | 2023-04-07 | 2023-06-08 | 2023-08-09 | COMP | 2023-08-14 | COMP | 2023-09-06 | COMP |  | INPR | 2023-10-01 | COMP | Rule 16 | 19 | 44 | 4 | 17 |  |  | 140
41621 | 2023-03-14 | 2023-04-13 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-18 | NOTN | 2023-08-08 | COMP | 2023-07-18 | COMP | 2023-10-03 | COMP | Other | 23 | 60 |  | 22 | 0 | 40 | 142
41662 | 2023-03-14 | 2023-04-18 | 2023-06-02 | 2023-06-02 | COMP | 2023-06-16 | COMP | 2023-06-16 | COMP | 2023-10-31 | COMP | 2023-11-09 | COMP | Rule 16 | 26 | 33 | 11 | 1 | 95 | 8 | 169
41668 | 2023-03-14 | 2023-04-17 | 2023-06-28 | 2023-06-28 | COMP | 2023-07-10 | COMP | 2023-07-13 | COMP | 2023-08-08 | COMP | 2023-08-15 | COMP | Rule 16 | 25 | 51 | 8 | 4 | 19 | 6 | 108
41765 | 2023-03-14 | 2023-04-27 | 2023-06-29 | 2023-06-29 | COMP | 2023-07-13 | COMP | 2023-08-11 | COMP | 2023-11-02 | COMP | 2023-12-22 | COMP | Rule 16 | 33 | 44 | 10 | 22 | 59 | 34 | 197
41821 | 2023-03-14 | 2023-05-04 | 2023-05-23 | 2023-05-23 | COMP | 2023-05-26 | NOTN | 2023-06-13 | COMP | 2023-06-13 | COMP | 2023-09-08 | COMP | Rule 16 | 38 | 14 |  | 15 | 1 | 61 | 125
41855 | 2023-03-14 | 2023-05-08 | 2023-06-26 | 2023-06-26 | COMP | 2023-06-28 | COMP | 2023-08-19 | COMP | 2023-06-30 | COMP | 2023-09-28 | COMP | Rule 16 | 40 | 34 | 3 | 37 | 0 | 28 | 139
41874 | 2023-03-14 | 2023-05-10 | 2023-08-11 | 2023-08-11 | COMP | 2023-08-14 | NOTN |  | REQD |  | REQD | 2023-12-13 | COMP | Other | 42 | 65 |  |  |  |  | 190
41969 | 2023-03-14 | 2023-05-24 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-03 | COMP | 2023-07-03 | COMP | 2023-09-26 | COMP | 2023-11-13 | COMP | Rule 16 | 52 | 20 | 8 | 1 | 60 | 34 | 170
41981 | 2023-03-14 | 2023-05-25 | 2023-07-14 | 2023-07-14 | COMP | 2023-07-28 | COMP | 2023-07-28 | COMP | 2023-08-01 | COMP | 2023-10-24 | COMP | Rule 16 | 53 | 34 | 11 | 1 | 3 | 60 | 157
42117 | 2023-03-14 | 2023-06-13 | 2023-07-27 | 2023-07-27 | COMP | 2023-07-27 | NOTN | 2023-07-27 | COMP | 2023-07-28 | COMP | 2023-08-10 | COMP | Other | 65 | 31 |  | 1 | 2 | 10 | 105
42128 | 2023-03-14 | 2023-06-14 | 2023-07-28 | 2023-08-04 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-07-31 | COMP | 2023-09-27 | COMP | Rule 16 | 66 | 31 | 3 | 1 | 0 | 36 | 138
41367 | 2023-03-15 | 2023-03-17 | 2023-04-22 | 2023-04-22 | COMP | 2023-04-28 | NOTN | 2023-04-28 | COMP | 2023-05-02 | COMP | 2023-06-26 | COMP | Other | 3 | 26 |  | 5 | 3 | 38 | 72
41635 | 2023-03-15 | 2023-04-13 | 2023-05-30 | 2023-05-30 | COMP | 2023-06-09 | COMP | 2023-08-24 | COMP | 2023-08-17 | COMP | 2023-09-22 | COMP | Rule 16 | 22 | 33 | 9 | 53 | 0 | 21 | 134
41677 | 2023-03-15 | 2023-04-18 | 2023-06-21 | 2023-06-21 | COMP | 2023-06-26 | COMP | 2023-08-15 | COMP | 2023-11-22 | COMP | 2023-10-19 | COMP | Rule 16 | 25 | 45 | 4 | 36 | 70 |  | 153
41775 | 2023-03-15 | 2023-04-27 | 2023-06-23 | 2023-06-23 | COMP | 2023-06-30 | COMP | 2023-08-25 | COMP | 2023-08-10 | COMP | 2023-10-10 | COMP | Rule 16 | 32 | 40 | 6 | 40 | 0 | 32 | 146
41854 | 2023-03-15 | 2023-05-08 | 2023-06-24 | 2023-06-24 | COMP | 2023-07-28 | COMP | 2023-10-13 | COMP | 2023-11-10 | COMP | 2023-12-18 | COMP | Rule 16 | 39 | 33 | 24 | 55 | 20 | 24 | 192
41903 | 2023-03-15 | 2023-05-15 | 2023-07-20 | 2023-07-20 | COMP | 2023-08-02 | COMP | 2023-08-02 | COMP | 2023-11-06 | COMP | 2023-11-15 | COMP | Rule 16 | 44 | 46 | 10 | 1 | 68 | 7 | 171
41924 | 2023-03-15 | 2023-05-18 | 2023-05-26 | 2023-05-26 | COMP | 2023-06-29 | COMP | 2023-06-29 | COMP |  | INPR | 2023-07-29 | COMP | Rule 16 | 47 | 7 | 23 | 1 |  |  | 95
41937 | 2023-03-15 | 2023-05-19 | 2023-06-24 | 2023-06-24 | COMP | 2023-07-14 | COMP | 2023-07-14 | COMP | 2023-12-07 | COMP | 2023-12-21 | COMP | Rule 16 | 48 | 24 | 14 | 1 | 101 | 11 | 195
42061 | 2023-03-15 | 2023-06-05 | 2023-07-04 | 2023-07-04 | COMP | 2023-07-13 | COMP | 2023-08-23 | COMP | 2023-05-10 | COMP | 2023-10-31 | COMP | Rule 16 | 58 | 20 | 7 | 30 | 0 | 49 | 161
41787 | 2023-03-16 | 2023-04-28 | 2023-06-19 | 2023-06-19 | COMP | 2023-06-26 | COMP | 2023-06-26 | COMP | 2023-09-01 | COMP | 2023-11-07 | COMP | Rule 16 | 32 | 35 | 5 | 1 | 49 | 47 | 165
41841 | 2023-03-16 | 2023-05-05 | 2023-07-11 | 2023-07-11 | COMP | 2023-07-31 | COMP | 2023-07-31 | COMP | 2023-08-14 | COMP | 2023-09-22 | COMP | Rule 15/16 | 37 | 45 | 15 | 1 | 11 | 29 | 133
41852 | 2023-03-16 | 2023-05-08 | 2023-06-29 | 2023-06-29 | COMP | 2023-07-25 | COMP | 2023-07-31 | COMP | 2023-07-25 | COMP | 2023-09-26 | COMP | Rule 16 | 38 | 37 | 18 | 5 | 0 | 41 | 135
42024 | 2023-03-16 | 2023-06-01 | 2023-07-03 | 2023-07-21 | COMP | 2023-08-01 | COMP | 2023-11-16 | COMP | 2023-11-16 | COMP | 2023-12-13 | COMP | Rule 16 | 55 | 22 | 8 | 76 | 1 | 18 | 188
42057 | 2023-03-16 | 2023-06-05 | 2023-06-09 | 2023-06-09 | COMP | 2023-07-20 | COMP | 2023-10-24 | COMP | 2023-10-17 | COMP | 2023-11-02 | COMP | Rule 16 | 57 | 5 | 28 | 68 | 0 | 8 | 162
41525 | 2023-03-17 | 2023-03-31 | 2023-04-06 | 2023-04-06 | COMP | 2023-04-13 | NOTN | 2023-05-21 | COMP | 2023-04-13 | COMP | 2023-08-03 | COMP | Other | 11 | 5 |  | 32 | 0 | 51 | 97
41539 | 2023-03-17 | 2023-04-03 | 2023-06-27 | 2023-06-27 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP | 2023-09-19 | COMP | 2023-10-10 | COMP | Rule 16 | 12 | 60 | 29 | 1 | 31 | 16 | 144
41581 | 2023-03-17 | 2023-04-06 | 2023-05-26 | 2023-05-26 | COMP | 2023-06-07 | COMP | 2023-06-15 | COMP | 2023-08-16 | COMP | 2023-09-26 | COMP | Rule 15/16 | 15 | 37 | 8 | 7 | 43 | 29 | 134
41675 | 2023-03-17 | 2023-04-18 | 2023-05-23 | 2023-07-26 | COMP | 2023-08-24 | COMP | 2023-08-24 | COMP | 2023-10-05 | COMP | 2023-11-23 | COMP | Rule 16 | 23 | 26 | 22 | 1 | 30 | 34 | 174
41676 | 2023-03-17 | 2023-04-18 | 2023-06-15 | 2023-06-15 | COMP | 2023-07-07 | COMP | 2023-07-31 | COMP | 2023-08-15 | COMP | 2023-09-19 | COMP | Rule 16 | 23 | 42 | 15 | 17 | 12 | 25 | 129
41685 | 2023-03-17 | 2023-04-19 | 2023-06-05 | 2023-06-05 | COMP | 2023-06-12 | COMP | 2023-07-12 | COMP | 2023-07-06 | COMP | 2023-08-25 | COMP | Rule 16 | 24 | 33 | 6 | 21 | 0 | 33 | 113
41786 | 2023-03-17 | 2023-04-28 | 2023-06-21 | 2023-06-21 | COMP | 2023-06-23 | COMP | 2023-06-23 | COMP | 2023-10-23 | COMP | 2023-10-19 | COMP | Rule 16 | 31 | 37 | 3 | 1 | 85 |  | 151
41796 | 2023-03-17 | 2023-04-30 | 2023-07-19 | 2023-07-19 | COMP | 2023-07-25 | NOTN | 2023-07-28 | COMP |  | INPR | 2023-09-26 | COMP | Other | 31 | 55 |  | 8 |  |  | 134
41876 | 2023-03-17 | 2023-05-11 | 2023-05-24 | 2023-05-24 | COMP | 2023-06-13 | COMP | 2023-06-13 | COMP | 2023-07-17 | COMP | 2023-07-18 | COMP | Rule 16 | 40 | 10 | 14 | 1 | 23 | 2 | 85
42083 | 2023-03-17 | 2023-06-07 | 2023-09-22 | 2023-09-22 | COMP | 2023-10-18 | COMP | 2023-11-29 | COMP | 2023-10-25 | COMP | 2023-12-04 | COMP | Rule 16 | 58 | 75 | 19 | 28 | 0 | 4 | 180
42183 | 2023-03-17 | 2023-06-28 | 2023-08-15 | 2023-08-15 | COMP | 2023-08-15 | NOTN | 2023-09-11 | COMP | 2023-09-11 | COMP | 2023-10-18 | COMP | Other | 72 | 34 |  | 19 | 1 | 28 | 150
42197 | 2023-03-17 | 2023-06-29 | 2023-08-01 | 2023-08-01 | COMP | 2023-08-10 | COMP | 2023-08-10 | COMP | 2023-09-27 | COMP | 2023-12-06 | COMP | Rule 16 | 73 | 23 | 8 | 1 | 34 | 48 | 182
41818 | 2023-03-19 | 2023-05-04 | 2023-06-06 | 2023-06-06 | COMP | 2023-07-27 | COMP | 2023-08-14 | INPR | 2023-09-22 | COMP | 2023-10-11 | COMP | Rule 16 | 34 | 23 | 36 |  |  |  | 144
42453 | 2023-03-19 | 2023-09-21 | 2023-10-04 | 2023-10-04 | COMP | 2023-10-10 | COMP | 2023-10-18 | COMP | 2023-10-18 | COMP | 2023-10-28 | COMP | Rule 15/16 | 130 | 10 | 5 | 7 | 1 | 8 | 156
41403 | 2023-03-20 | 2023-03-23 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-30 | COMP | 2023-12-04 | COMP | 2023-06-07 | COMP | 2023-12-06 | COMP | Rule 16 | 4 | 54 | 17 | 107 | 0 | 3 | 181
41511 | 2023-03-20 | 2023-03-30 | 2023-05-11 | 2023-05-11 | COMP | 2023-06-28 | COMP | 2023-06-28 | COMP | 2023-07-19 | COMP | 2023-08-23 | COMP | Rule 15/16 | 9 | 31 | 33 | 1 | 15 | 26 | 110
41519 | 2023-03-20 | 2023-03-30 | 2023-05-24 | 2023-05-24 | COMP | 2023-09-11 | COMP | 2023-09-11 | COMP | 2023-10-31 | COMP | 2023-11-14 | COMP | Rule 16 | 9 | 40 | 75 | 1 | 37 | 10 | 167
41769 | 2023-03-20 | 2023-04-27 | 2023-06-15 | 2023-06-15 | COMP | 2023-06-16 | NOTN | 2023-08-23 | COMP | 2023-08-16 | COMP | 2023-09-18 | COMP | Other | 29 | 35 |  | 48 | 0 | 18 | 127
41791 | 2023-03-20 | 2023-04-28 | 2023-06-01 | 2023-06-01 | COMP | 2023-06-12 | COMP | 2023-09-07 | COMP | 2023-08-25 | COMP | 2023-12-15 | COMP | Rule 16 | 30 | 24 | 8 | 61 | 0 | 69 | 188
41913 | 2023-03-20 | 2023-05-17 | 2023-06-29 | 2023-06-29 | COMP | 2023-06-29 | NOTN | 2023-07-05 | COMP | 2023-07-25 | COMP | 2023-10-16 | COMP | Other | 43 | 30 |  | 4 | 15 | 59 | 147
41972 | 2023-03-20 | 2023-05-24 | 2023-07-13 | 2023-07-13 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-10-13 | COMP | Rule 16 | 48 | 34 | 19 | 1 | 1 | 48 | 146
42033 | 2023-03-20 | 2023-06-02 | 2023-07-12 | 2023-07-12 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP | 2023-09-05 | COMP | 2023-10-09 | COMP | Rule 16 | 54 | 27 | 19 | 1 | 21 | 25 | 142
42046 | 2023-03-20 | 2023-06-02 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-28 | COMP | 2023-09-01 | COMP | 2023-09-18 | COMP | 2023-10-04 | COMP | Rule 16 | 54 | 25 | 15 | 26 | 11 | 13 | 139
42098 | 2023-03-20 | 2023-06-09 | 2023-07-21 | 2023-07-21 | COMP | 2023-07-23 | NOTN | 2023-09-04 | COMP | 2023-08-21 | COMP | 2023-10-03 | COMP | Other | 59 | 29 |  | 31 | 0 | 21 | 138
41772 | 2023-03-21 | 2023-04-26 | 2023-07-29 | 2023-07-29 | COMP | 2023-08-02 | COMP | 2023-08-04 | COMP | 2023-07-31 | COMP | 2023-08-18 | COMP | Rule 16 | 27 | 65 | 3 | 3 | 0 | 11 | 106
41838 | 2023-03-21 | 2023-05-05 | 2023-08-21 | 2023-08-21 | COMP | 2023-08-23 | NOTN | 2023-09-07 | COMP | 2023-08-18 | COMP | 2023-11-11 | COMP | Other | 34 | 74 |  | 13 | 0 | 46 | 164
41935 | 2023-03-21 | 2023-05-19 | 2023-07-29 | 2023-07-29 | COMP | 2023-08-16 | COMP | 2023-09-18 | COMP |  | INPR | 2023-11-06 | COMP | Rule 16 | 44 | 48 | 13 | 23 |  |  | 161
42003 | 2023-03-21 | 2023-05-30 | 2023-06-23 | 2023-06-23 | COMP | 2023-06-28 | COMP | 2023-07-31 | COMP | 2023-08-07 | COMP | 2023-08-24 | COMP | Rule 16 | 50 | 18 | 4 | 23 | 6 | 14 | 110
42170 | 2023-03-21 | 2023-06-23 | 2023-08-11 | 2023-08-11 | COMP | 2023-09-05 | COMP | 2023-10-02 | COMP | 2023-09-12 | COMP | 2023-10-23 | COMP | Rule 16 | 67 | 35 | 17 | 20 | 0 | 16 | 151
42236 | 2023-03-21 | 2023-07-10 | 2023-09-21 | 2023-09-21 | COMP | 2023-09-28 | NOTN | 2023-10-06 | COMP |  | INPR | 2023-12-14 | COMP | Other | 77 | 53 |  | 12 |  |  | 186
42395 | 2023-03-21 | 2023-08-21 | 2023-10-19 | 2023-10-19 | COMP | 2023-10-24 | COMP | 2023-10-24 | COMP | 2023-11-22 | COMP | 2023-11-13 | COMP | Rule 16 | 107 | 43 | 4 | 1 | 21 |  | 165
42400 | 2023-03-21 | 2023-08-22 | 2023-09-15 | 2023-09-15 | COMP | 2023-09-26 | NOTN | 2023-09-26 | COMP | 2023-09-26 | COMP | 2023-11-20 | COMP | Other | 108 | 18 |  | 8 | 1 | 39 | 170
42457 | 2023-03-21 | 2023-09-22 | 2023-10-03 | 2023-10-03 | COMP | 2023-10-11 | COMP | 2023-10-11 | COMP | 2023-10-13 | COMP | 2023-12-16 | COMP | Rule 16 | 130 | 8 | 7 | 1 | 3 | 43 | 187
41627 | 2023-03-22 | 2023-04-12 | 2023-06-06 | 2023-06-06 | COMP | 2023-06-12 | COMP |  | REQD | 2023-07-17 | COMP | 2023-08-01 | COMP | Rule 16 | 16 | 39 | 5 |  |  |  | 92
41658 | 2023-03-22 | 2023-04-17 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-14 | COMP | 2023-08-22 | COMP | 2023-08-22 | COMP | 2023-10-16 | COMP | Rule 16 | 19 | 37 | 6 | 48 | 1 | 39 | 145
41701 | 2023-03-22 | 2023-04-20 | 2023-07-01 | 2023-07-01 | COMP | 2023-07-13 | COMP | 2023-10-25 | COMP | 2023-10-25 | COMP | 2023-12-12 | COMP | Rule 16 | 22 | 50 | 8 | 74 | 1 | 32 | 183
41827 | 2023-03-22 | 2023-05-04 | 2023-05-17 | 2023-05-17 | COMP | 2023-05-18 | NOTN | 2023-06-06 | COMP | 2023-06-30 | NOTN | 2023-07-24 | COMP | Other | 32 | 10 |  | 14 |  |  | 86
41887 | 2023-03-22 | 2023-05-11 | 2023-07-01 | 2023-07-01 | COMP | 2023-07-13 | COMP | 2023-07-24 | COMP | 2023-08-07 | COMP | 2023-08-25 | COMP | Rule 16 | 37 | 35 | 8 | 8 | 11 | 15 | 110
41930 | 2023-03-22 | 2023-05-19 | 2023-06-23 | 2023-07-10 | COMP | 2023-08-03 | COMP | 2023-08-14 | COMP | 2023-11-21 | COMP | 2023-11-30 | COMP | Rule 16 | 43 | 24 | 19 | 8 | 70 | 6 | 175
42007 | 2023-03-22 | 2023-05-30 | 2023-06-30 | 2023-06-30 | COMP | 2023-07-06 | COMP | 2023-08-28 | COMP | 2023-08-23 | COMP | 2023-10-17 | COMP | Rule 16 | 49 | 23 | 4 | 38 | 0 | 36 | 146
42071 | 2023-03-22 | 2023-06-06 | 2023-08-05 | 2023-11-02 | COMP | 2023-11-10 | COMP | 2023-11-10 | COMP | 2023-11-09 | COMP | 2023-11-13 | COMP | Rule 16 | 54 | 42 | 6 | 0 | 0 | 1 | 164
42096 | 2023-03-22 | 2023-06-09 | 2023-07-14 | 2023-07-14 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP | 2023-11-14 | COMP | 2023-11-17 | COMP | Rule 16 | 57 | 24 | 17 | 1 | 70 | 4 | 168
42135 | 2023-03-22 | 2023-06-15 | 2023-07-11 | 2023-07-11 | COMP | 2023-07-20 | COMP | 2023-10-13 | COMP | 2023-11-27 | COMP | 2023-12-26 | COMP | Rule 16 | 61 | 17 | 8 | 61 | 29 | 21 | 192
41597 | 2023-03-23 | 2023-04-10 | 2023-06-07 | 2023-06-07 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-11-02 | COMP | 2023-11-15 | COMP | Rule 16 | 13 | 42 | 43 | 1 | 62 | 9 | 165
41763 | 2023-03-23 | 2023-04-27 | 2023-06-09 | 2023-06-09 | COMP | 2023-07-05 | COMP | 2023-07-17 | COMP | 2023-08-03 | COMP | 2023-10-03 | COMP | Rule 16 | 26 | 31 | 17 | 9 | 14 | 43 | 135
41828 | 2023-03-23 | 2023-05-04 | 2023-06-02 | 2023-06-02 | COMP | 2023-08-29 | COMP | 2023-08-29 | COMP | 2023-08-29 | COMP | 2023-11-07 | COMP | Rule 16 | 31 | 21 | 61 | 1 | 1 | 50 | 160
41856 | 2023-03-23 | 2023-05-08 | 2023-06-13 | 2023-06-13 | COMP | 2023-06-20 | COMP | 2023-06-20 | COMP |  | INPR | 2023-07-01 | COMP | Rule 16 | 33 | 26 | 5 | 1 |  |  | 70
41878 | 2023-03-23 | 2023-05-10 | 2023-08-10 | 2023-08-10 | COMP | 2023-09-11 | COMP | 2023-09-11 | COMP | 2023-10-09 | COMP | 2023-10-18 | COMP | Rule 16 | 35 | 64 | 22 | 1 | 21 | 8 | 146
41982 | 2023-03-23 | 2023-05-25 | 2023-08-07 | 2023-08-07 | COMP | 2023-08-11 | COMP | 2023-08-11 | COMP | 2023-10-31 | COMP | 2023-11-13 | COMP | Rule 16 | 46 | 50 | 5 | 1 | 57 | 9 | 163
42107 | 2023-03-23 | 2023-06-11 | 2023-07-14 | 2023-07-14 | COMP | 2023-08-14 | COMP | 2023-08-24 | COMP | 2023-08-28 | COMP | 2023-12-08 | COMP | Rule 16 | 56 | 23 | 22 | 9 | 3 | 71 | 180
41673 | 2023-03-24 | 2023-04-17 | 2023-07-04 | 2023-07-04 | COMP | 2023-07-18 | COMP | 2023-08-21 | COMP | 2023-08-16 | COMP | 2023-10-18 | COMP | Rule 16 | 17 | 54 | 10 | 25 | 0 | 42 | 145
41748 | 2023-03-24 | 2023-04-25 | 2023-06-06 | 2023-06-06 | COMP | 2023-07-10 | COMP | 2023-07-18 | COMP | 2023-08-03 | COMP | 2023-11-28 | COMP | Rule 16 | 23 | 30 | 23 | 7 | 13 | 80 | 171
41885 | 2023-03-24 | 2023-05-11 | 2023-06-05 | 2023-06-05 | COMP | 2023-08-16 | COMP | 2023-08-16 | COMP | 2023-09-20 | COMP | 2023-11-01 | COMP | Rule 16 | 35 | 17 | 51 | 1 | 25 | 31 | 155
42054 | 2023-03-24 | 2023-06-05 | 2023-07-24 | 2023-07-24 | COMP | 2023-08-30 | COMP | 2023-12-06 | COMP |  | INPR | 2023-12-15 | COMP | Rule 16 | 51 | 34 | 28 | 67 |  |  | 184
42095 | 2023-03-24 | 2023-06-08 | 2023-08-13 | 2023-08-13 | COMP | 2023-08-21 | COMP | 2023-08-24 | COMP | 2023-08-23 | COMP | 2023-09-27 | COMP | Rule 16 | 54 | 45 | 6 | 4 | 0 | 24 | 130
41931 | 2023-03-26 | 2023-05-19 | 2023-06-12 | 2023-06-12 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | 2023-10-03 | COMP | Rule 16 | 40 | 16 | 54 | 1 | 1 | 26 | 133
41504 | 2023-03-27 | 2023-03-29 | 2023-05-16 | 2023-05-16 | COMP | 2023-06-21 | COMP | 2023-10-16 | COMP | 2023-10-26 | COMP | 2023-12-08 | COMP | Rule 29 | 3 | 35 | 25 | 82 | 9 | 29 | 178
41589 | 2023-03-27 | 2023-04-07 | 2023-05-17 | 2023-05-17 | COMP | 2023-06-13 | COMP | 2023-06-15 | COMP | 2023-06-27 | COMP | 2023-08-30 | COMP | Rule 16 | 10 | 29 | 19 | 3 | 8 | 46 | 110
41725 | 2023-03-27 | 2023-04-24 | 2023-07-17 | 2023-07-17 | COMP | 2023-08-02 | COMP | 2023-09-05 | COMP | 2023-09-06 | COMP | 2023-11-19 | COMP | Rule 16 | 21 | 58 | 13 | 24 | 2 | 52 | 165
41946 | 2023-03-27 | 2023-05-22 | 2023-06-28 | 2023-06-28 | COMP | 2023-07-24 | COMP | 2023-08-04 | COMP | 2023-07-25 | COMP | 2023-09-14 | COMP | Rule 16 | 41 | 26 | 18 | 10 | 0 | 29 | 120
41948 | 2023-03-27 | 2023-05-22 | 2023-06-30 | 2023-06-30 | COMP | 2023-07-13 | COMP | 2023-09-01 | COMP | 2023-09-07 | COMP | 2023-10-25 | COMP | Rule 16 | 41 | 28 | 9 | 37 | 4 | 35 | 149
42056 | 2023-03-27 | 2023-06-05 | 2023-06-28 | 2023-06-28 | COMP | 2023-08-15 | COMP | 2023-09-26 | COMP | 2023-10-05 | COMP | 2023-12-02 | COMP | Rule 16 | 50 | 17 | 34 | 30 | 8 | 39 | 173
42319 | 2023-03-27 | 2023-07-29 | 2023-09-11 | 2023-10-02 | COMP | 2023-10-16 | COMP | 2023-10-26 | COMP | 2023-10-17 | COMP | 2023-12-15 | COMP | Rule 16 | 87 | 30 | 11 | 9 | 0 | 34 | 183
41498 | 2023-03-28 | 2023-03-29 | 2023-04-28 | 2023-04-28 | COMP | 2023-05-12 | COMP | 2023-05-12 | COMP | 2023-08-10 | COMP | 2023-08-22 | COMP | Rule 15/16 | 2 | 23 | 11 | 1 | 62 | 9 | 103
41850 | 2023-03-28 | 2023-05-08 | 2023-06-21 | 2023-07-03 | COMP | 2023-07-07 | COMP | 2023-09-06 | COMP | 2023-08-25 | COMP | 2023-10-17 | COMP | Rule 16 | 30 | 31 | 4 | 43 | 0 | 30 | 142
41905 | 2023-03-28 | 2023-05-16 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-28 | COMP | 2023-08-09 | COMP | 2023-09-12 | COMP | 2023-10-17 | COMP | Rule 16 | 36 | 37 | 15 | 9 | 24 | 26 | 142
41998 | 2023-03-28 | 2023-05-28 | 2023-06-22 | 2023-06-22 | COMP | 2023-06-28 | COMP | 2023-06-28 | COMP | 2023-08-24 | COMP | 2023-08-29 | COMP | Rule 16 | 44 | 17 | 5 | 1 | 41 | 4 | 108
42015 | 2023-03-28 | 2023-05-31 | 2023-08-08 | 2023-08-08 | COMP | 2023-08-15 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | 2023-09-29 | COMP | Rule 16 | 46 | 48 | 6 | 10 | 1 | 24 | 130
42182 | 2023-03-28 | 2023-06-28 | 2023-08-24 | 2023-08-24 | COMP | 2023-08-30 | COMP | 2023-11-07 | COMP | 2023-11-14 | COMP | 2023-11-21 | COMP | Rule 16 | 65 | 41 | 5 | 49 | 5 | 6 | 166
42221 | 2023-03-28 | 2023-07-05 | 2023-08-21 | 2023-08-21 | COMP | 2023-09-22 | COMP | 2023-10-05 | COMP | 2023-10-30 | COMP | 2023-11-03 | COMP | Rule 16 | 69 | 34 | 24 | 10 | 18 | 5 | 155
42419 | 2023-03-28 | 2023-08-30 | 2023-09-18 | 2023-09-18 | COMP | 2023-12-05 | COMP | 2023-12-05 | COMP | 2023-12-05 | COMP | 2023-12-21 | COMP | Rule 16 | 109 | 13 | 54 | 1 | 1 | 13 | 186
41484 | 2023-03-29 | 2023-03-29 | 2023-05-21 | 2023-05-21 | COMP | 2023-05-24 | NOTN | 2023-06-23 | COMP | 2023-09-27 | COMP | 2023-10-26 | COMP | Other | 1 | 38 |  | 23 | 67 | 22 | 148
41605 | 2023-03-29 | 2023-04-12 | 2023-06-21 | 2023-06-21 | COMP | 2023-06-27 | COMP | 2023-08-25 | COMP | 2023-08-16 | COMP | 2023-10-02 | COMP | Rule 16 | 11 | 49 | 5 | 43 | 0 | 26 | 130
41639 | 2023-03-29 | 2023-04-13 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-05 | NOTN | 2023-08-07 | COMP | 2023-09-27 | COMP | 2023-11-20 | COMP | Other | 12 | 57 |  | 24 | 37 | 38 | 164
41647 | 2023-03-29 | 2023-04-14 | 2023-06-28 | 2023-06-28 | COMP | 2023-07-12 | COMP | 2023-07-12 | COMP | 2023-08-23 | COMP | 2023-10-10 | COMP | Rule 15/16 | 13 | 52 | 10 | 1 | 31 | 34 | 136
41836 | 2023-03-29 | 2023-05-06 | 2023-07-03 | 2023-07-03 | COMP | 2023-07-10 | COMP | 2023-10-17 | COMP | 2023-09-12 | COMP | 2023-11-06 | COMP | Rule 15/16 | 28 | 39 | 5 | 71 | 0 | 15 | 155
41908 | 2023-03-29 | 2023-05-16 | 2023-06-10 | 2023-06-10 | COMP | 2023-07-11 | COMP | 2023-07-11 | COMP | 2023-07-31 | COMP | 2023-08-18 | COMP | Rule 16 | 35 | 18 | 20 | 1 | 15 | 15 | 100
41996 | 2023-03-29 | 2023-05-27 | 2023-07-25 | 2023-07-25 | COMP | 2023-07-27 | COMP | 2023-10-05 | COMP | 2023-09-15 | COMP | 2023-10-16 | COMP | Rule 16 | 43 | 39 | 3 | 50 | 0 | 8 | 140
42001 | 2023-03-29 | 2023-05-30 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-28 | COMP | 2023-07-28 | COMP | 2023-09-13 | COMP | 2023-10-10 | COMP | Rule 16 | 44 | 25 | 18 | 1 | 33 | 20 | 136
42040 | 2023-03-29 | 2023-06-02 | 2023-07-27 | 2023-07-27 | COMP | 2023-08-02 | COMP | 2023-09-11 | COMP | 2023-10-19 | COMP | 2023-11-01 | COMP | Rule 16 | 47 | 38 | 5 | 28 | 29 | 10 | 152
41688 | 2023-03-30 | 2023-04-19 | 2023-06-16 | 2023-06-16 | COMP | 2023-06-26 | COMP | 2023-07-27 | COMP | 2023-06-21 | COMP | 2023-09-11 | COMP | Rule 16 | 15 | 42 | 6 | 23 | 0 | 32 | 114
41819 | 2023-03-30 | 2023-05-04 | 2023-05-31 | 2023-07-19 | COMP | 2023-07-20 | COMP | 2023-07-20 | COMP | 2023-09-13 | COMP | 2023-12-20 | COMP | Rule 16 | 26 | 19 | 2 | 1 | 39 | 68 | 183
41893 | 2023-03-30 | 2023-05-15 | 2023-06-06 | 2023-06-06 | COMP | 2023-06-12 | COMP | 2023-08-02 | COMP | 2023-08-10 | COMP | 2023-10-17 | COMP | Rule 16 | 33 | 16 | 5 | 36 | 7 | 48 | 140
42129 | 2023-03-30 | 2023-06-14 | 2023-08-16 | 2023-08-16 | COMP | 2023-08-24 | COMP | 2023-08-24 | COMP | 2023-09-18 | COMP | 2023-11-07 | COMP | Rule 16 | 54 | 44 | 7 | 1 | 17 | 37 | 155
42143 | 2023-03-30 | 2023-06-19 | 2023-08-31 | 2023-08-31 | COMP | 2023-09-19 | COMP | 2023-10-17 | COMP | 2023-12-15 | COMP | 2023-12-05 | COMP | Rule 16 | 56 | 52 | 13 | 21 | 41 |  | 172
41564 | 2023-03-31 | 2023-04-04 | 2023-06-07 | 2023-06-07 | COMP | 2023-06-07 | NOTN | 2023-07-14 | COMP | 2023-09-27 | COMP | 2023-10-03 | COMP | Other | 3 | 46 |  | 26 | 53 | 5 | 129
41831 | 2023-03-31 | 2023-05-05 | 2023-06-10 | 2023-07-12 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-10-03 | COMP | 2023-11-06 | COMP | Other | 26 | 25 | 49 | 1 | 11 | 25 | 153
41872 | 2023-03-31 | 2023-05-10 | 2023-07-11 | 2023-07-11 | COMP | 2023-08-01 | COMP | 2023-08-29 | COMP | 2023-09-19 | COMP | 2023-10-11 | COMP | Rule 16 | 29 | 42 | 16 | 21 | 15 | 17 | 135
41912 | 2023-03-31 | 2023-05-16 | 2023-07-06 | 2023-07-06 | COMP | 2023-07-11 | COMP | 2023-09-02 | COMP | 2023-08-31 | COMP | 2023-11-30 | COMP | Rule 16 | 33 | 35 | 4 | 39 | 0 | 60 | 168
41980 | 2023-03-31 | 2023-05-25 | 2023-07-11 | 2023-07-11 | COMP | 2023-07-13 | COMP | 2023-08-28 | COMP | 2023-07-11 | COMP | 2023-09-27 | COMP | Rule 16 | 40 | 31 | 3 | 33 | 0 | 22 | 125
42026 | 2023-03-31 | 2023-06-02 | 2023-06-10 | 2023-06-10 | COMP | 2023-07-21 | COMP | 2023-07-21 | COMP | 2023-07-21 | COMP | 2023-08-12 | COMP | Rule 16 | 45 | 6 | 28 | 1 | 1 | 16 | 93
42195 | 2023-03-31 | 2023-06-29 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-17 | NOTN | 2023-09-29 | COMP | 2023-08-23 | COMP | 2023-12-02 | COMP | Other | 63 | 30 |  | 36 | 0 | 43 | 169
42226 | 2023-03-31 | 2023-07-07 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-21 | COMP | 2023-08-21 | COMP | 2023-08-22 | COMP | 2023-12-07 | COMP | Rule 16 | 68 | 25 | 8 | 1 | 2 | 74 | 173
42231 | 2023-03-31 | 2023-07-07 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-03 | COMP | 2023-08-10 | COMP | 2023-08-10 | COMP | 2023-12-04 | COMP | Rule 16 | 68 | 17 | 4 | 6 | 1 | 79 | 170
42242 | 2023-03-31 | 2023-07-11 | 2023-08-18 | 2023-09-01 | COMP | 2023-10-11 | COMP | 2023-10-11 | COMP | 2023-10-11 | COMP | 2023-12-07 | COMP | Rule 16 | 70 | 29 | 28 | 1 | 1 | 39 | 173
42254 | 2023-03-31 | 2023-07-12 | 2023-08-19 | 2023-08-19 | COMP | 2023-10-12 | COMP | 2023-10-12 | COMP |  | INPR | 2023-12-14 | COMP | Rule 16 | 71 | 28 | 38 | 1 |  |  | 178
42273 | 2023-03-31 | 2023-07-17 | 2023-09-15 | 2023-09-15 | COMP | 2023-09-21 | COMP | 2023-09-21 | COMP | 2023-10-30 | COMP | 2023-11-13 | COMP | Rule 16 | 74 | 44 | 5 | 1 | 28 | 10 | 157
41939 | 2023-04-01 | 2023-05-20 | 2023-06-22 | 2023-06-22 | COMP | 2023-06-28 | COMP | 2023-08-08 | COMP | 2023-06-22 | COMP | 2023-12-09 | COMP | Rule 16 | 35 | 22 | 5 | 29 | 0 | 85 | 173
41945 | 2023-04-02 | 2023-05-22 | 2023-06-27 | 2023-06-27 | COMP | 2023-07-14 | COMP | 2023-07-14 | COMP | 2023-10-27 | COMP | 2023-11-16 | COMP | Rule 16 | 36 | 25 | 13 | 1 | 75 | 14 | 159
42184 | 2023-04-02 | 2023-06-28 | 2023-08-18 | 2023-08-18 | COMP | 2023-08-21 | NOTN | 2023-10-09 | COMP | 2023-10-09 | COMP | 2023-12-09 | COMP | Other | 61 | 37 |  | 36 | 1 | 42 | 173
4357 | 2023-04-03 | 2023-05-03 | [7 empty] | 2023-08-03 | COMP | 2023-09-15 | COMP | Other | 23 | [5 empty] | 116
41670 | 2023-04-03 | 2023-04-17 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-14 | NOTN | 2023-08-14 | COMP | 2023-08-29 | COMP | 2023-12-08 | COMP | Other | 11 | 75 |  | 9 | 12 | 70 | 173
41703 | 2023-04-03 | 2023-04-20 | 2023-07-25 | 2023-07-25 | COMP | 2023-08-07 | COMP | 2023-09-11 | COMP | 2023-10-17 | COMP | 2023-11-29 | COMP | Rule 16 | 14 | 66 | 10 | 25 | 27 | 29 | 166
41784 | 2023-04-03 | 2023-04-28 | 2023-08-08 | 2023-08-08 | COMP | 2023-08-18 | COMP | 2023-10-04 | COMP | 2023-09-22 | COMP | 2023-11-15 | COMP | Rule 16 | 20 | 70 | 9 | 33 | 0 | 30 | 158
41927 | 2023-04-03 | 2023-05-18 | 2023-07-11 | 2023-07-11 | COMP | 2023-07-28 | COMP | 2023-09-06 | COMP | 2023-08-23 | COMP | 2023-10-17 | COMP | Rule 16 | 34 | 36 | 14 | 28 | 0 | 30 | 138
42005 | 2023-04-03 | 2023-05-30 | 2023-07-11 | 2023-07-11 | COMP | 2023-07-24 | COMP | 2023-07-24 | COMP | 2023-09-14 | COMP | 2023-11-02 | COMP | Rule 16 | 41 | 29 | 10 | 1 | 38 | 36 | 150
42076 | 2023-04-03 | 2023-06-06 | 2023-07-21 | 2023-07-21 | COMP | 2023-07-25 | COMP | 2023-10-17 | COMP | 2023-09-28 | COMP | 2023-10-31 | COMP | Rule 16 | 46 | 32 | 3 | 60 | 0 | 11 | 148
42086 | 2023-04-03 | 2023-06-08 | 2023-08-14 | 2023-08-14 | COMP | 2023-10-11 | COMP | 2023-10-11 | COMP | 2023-10-30 | COMP | 2023-11-28 | COMP | Rule 16 | 48 | 46 | 42 | 1 | 14 | 19 | 165
42188 | 2023-04-03 | 2023-06-28 | 2023-07-22 | 2023-08-04 | COMP | 2023-08-30 | COMP | 2023-08-30 | COMP | 2023-09-18 | COMP | 2023-10-24 | COMP | Rule 16 | 61 | 17 | 19 | 1 | 13 | 27 | 143
42189 | 2023-04-03 | 2023-06-28 | 2023-07-22 | 2023-07-22 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP | 2023-08-28 | COMP | 2023-10-26 | COMP | Rule 16 | 61 | 17 | 17 | 1 | 10 | 43 | 145
42234 | 2023-04-03 | 2023-07-10 | 2023-08-21 | 2023-08-21 | COMP | 2023-09-06 | COMP | 2023-09-06 | COMP | 2023-09-11 | COMP | 2023-11-30 | COMP | Rule 16 | 68 | 31 | 12 | 1 | 4 | 56 | 167
42312 | 2023-04-03 | 2023-07-27 | 2023-08-21 | 2023-08-21 | COMP | 2023-10-06 | COMP | 2023-10-06 | COMP | 2023-11-06 | COMP | 2023-11-29 | COMP | Rule 16 | 81 | 18 | 34 | 1 | 22 | 15 | 166
41699 | 2023-04-04 | 2023-04-20 | 2023-05-30 | 2023-05-30 | COMP | 2023-06-02 | COMP | 2023-06-02 | COMP | 2023-08-08 | COMP | 2023-09-30 | COMP | Rule 16 | 13 | 28 | 4 | 1 | 46 | 38 | 125
41793 | 2023-04-04 | 2023-05-01 | 2023-06-20 | 2023-06-20 | COMP | 2023-07-07 | COMP | 2023-07-07 | COMP |  | INPR | 2023-11-15 | COMP | Rule 16 | 20 | 35 | 13 | 1 |  |  | 157
41843 | 2023-04-04 | 2023-05-06 | 2023-05-23 | 2023-05-23 | COMP | 2023-06-06 | COMP | 2023-06-09 | COMP | 2023-07-25 | COMP | 2023-08-21 | COMP | Rule 15/16 | 24 | 12 | 10 | 4 | 31 | 20 | 97
41923 | 2023-04-04 | 2023-05-18 | 2023-06-07 | 2023-06-07 | COMP | 2023-07-06 | COMP | 2023-07-07 | COMP | 2023-07-13 | COMP | 2023-08-31 | COMP | Rule 16 | 33 | 14 | 20 | 2 | 5 | 36 | 105
42021 | 2023-04-04 | 2023-06-01 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-04 | NOTN | 2023-10-10 | COMP | 2023-08-04 | COMP | 2023-11-22 | COMP | Other | 42 | 45 |  | 47 | 0 | 31 | 162
42022 | 2023-04-04 | 2023-06-01 | 2023-07-24 | 2023-07-24 | COMP | 2023-08-21 | COMP | 2023-09-11 | COMP | 2023-09-25 | COMP | 2023-10-16 | COMP | Rule 16 | 42 | 36 | 21 | 15 | 11 | 16 | 136
42168 | 2023-04-04 | 2023-06-23 | 2023-09-02 | 2023-09-02 | COMP | 2023-09-05 | NOTN | 2023-09-06 | COMP |  | INPR | 2023-10-24 | COMP | Other | 57 | 50 |  | 2 |  |  | 142
42187 | 2023-04-04 | 2023-06-28 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-10 | COMP | 2023-08-18 | COMP | 2023-11-06 | COMP | 2023-11-15 | COMP | Rule 16 | 60 | 23 | 9 | 7 | 56 | 7 | 157
42200 | 2023-04-04 | 2023-06-30 | 2023-08-23 | 2023-08-23 | COMP | 2023-10-17 | COMP | 2023-10-17 | COMP | 2023-11-07 | COMP | 2023-12-16 | COMP | Rule 16 | 62 | 38 | 39 | 1 | 16 | 26 | 177
41731 | 2023-04-05 | 2023-04-24 | 2023-09-09 | 2023-09-09 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-11-04 | COMP | 2023-12-27 | COMP | Rule 16 | 14 | 96 | 7 | 1 | 34 | 34 | 183
41801 | 2023-04-05 | 2023-05-01 | 2023-06-09 | 2023-06-09 | COMP | 2023-07-21 | COMP | 2023-10-25 | COMP | 2023-10-05 | COMP | 2023-10-31 | COMP | Rule 16 | 19 | 29 | 29 | 68 | 0 | 5 | 146
41936 | 2023-04-05 | 2023-05-19 | 2023-06-05 | 2023-06-05 | COMP | 2023-06-12 | COMP | 2023-06-12 | COMP |  | INPR | 2023-10-17 | COMP | Rule 16 | 33 | 11 | 6 | 1 |  |  | 136
42079 | 2023-04-05 | 2023-06-07 | 2023-09-09 | 2023-09-09 | COMP | 2023-09-19 | COMP | 2023-10-09 | COMP | 2023-10-17 | COMP | 2023-11-30 | COMP | Rule 16 | 45 | 65 | 7 | 15 | 7 | 30 | 165
42150 | 2023-04-05 | 2023-06-20 | 2023-08-01 | 2023-08-01 | COMP | 2023-08-11 | COMP | 2023-08-11 | COMP | 2023-10-24 | COMP | 2023-11-27 | COMP | Rule 16 | 53 | 30 | 9 | 1 | 52 | 22 | 162
42237 | 2023-04-05 | 2023-07-10 | 2023-08-31 | 2023-08-31 | COMP | 2023-09-27 | COMP | 2023-09-27 | COMP | 2023-10-03 | COMP | 2023-11-28 | COMP | Rule 16 | 66 | 39 | 19 | 1 | 5 | 38 | 163
41671 | 2023-04-06 | 2023-04-18 | 2023-05-05 | 2023-05-05 | COMP | 2023-05-23 | COMP | 2023-05-23 | COMP | 2023-07-18 | COMP | 2023-08-31 | COMP | Rule 16 | 9 | 14 | 13 | 1 | 38 | 33 | 103
41720 | 2023-04-06 | 2023-04-21 | 2023-05-02 | 2023-05-02 | COMP | 2023-05-09 | NOTN | 2023-05-09 | COMP | 2023-05-16 | COMP | 2023-07-17 | COMP | Rule 16 | 12 | 8 |  | 6 | 6 | 42 | 70
41810 | 2023-04-06 | 2023-05-02 | 2023-06-15 | 2023-06-15 | COMP | 2023-07-07 | COMP | 2023-10-23 | COMP | 2023-10-20 | COMP | 2023-11-17 | COMP | Rule 16 | 19 | 32 | 15 | 76 | 0 | 19 | 157
41812 | 2023-04-06 | 2023-05-03 | 2023-06-28 | 2023-06-28 | COMP | 2023-08-08 | COMP | 2023-08-17 | COMP | 2023-09-22 | COMP | 2023-10-10 | COMP | Unknown | 20 | 39 | 29 | 8 | 26 | 13 | 130
41984 | 2023-04-06 | 2023-05-25 | 2023-08-23 | 2023-08-23 | COMP | 2023-08-28 | COMP | 2023-08-29 | COMP | 2023-10-04 | COMP | 2023-10-26 | COMP | Rule 16 | 36 | 62 | 4 | 2 | 26 | 17 | 142
42041 | 2023-04-06 | 2023-06-02 | 2023-07-01 | 2023-07-01 | COMP | 2023-07-07 | COMP | 2023-07-28 | COMP |  | INPR | 2023-08-29 | COMP | Rule 16 | 41 | 20 | 4 | 16 |  |  | 101
42047 | 2023-04-06 | 2023-06-02 | 2023-07-12 | 2023-07-12 | COMP | 2023-09-13 | COMP | 2023-10-20 | COMP | 2023-10-10 | COMP | 2023-12-12 | COMP | Rule 15/16 | 41 | 27 | 45 | 28 | 0 | 35 | 172
42049 | 2023-04-06 | 2023-06-03 | 2023-07-17 | 2023-07-17 | COMP | 2023-08-03 | COMP | 2023-09-08 | COMP | 2023-09-22 | COMP | 2023-11-01 | COMP | Rule 16 | 41 | 29 | 14 | 26 | 11 | 29 | 146
42058 | 2023-04-06 | 2023-06-05 | 2023-08-15 | 2023-08-15 | COMP | 2023-08-24 | COMP | 2023-10-02 | COMP | 2023-10-17 | COMP | 2023-10-31 | COMP | Rule 16 | 42 | 50 | 8 | 27 | 12 | 11 | 145
42165 | 2023-04-06 | 2023-06-22 | 2023-08-12 | 2023-08-12 | COMP | 2023-08-24 | COMP | 2023-10-02 | COMP | 2023-10-09 | COMP | 2023-10-26 | COMP | Rule 16 | 54 | 36 | 9 | 27 | 6 | 14 | 142
41669 | 2023-04-07 | 2023-04-17 | 2023-05-19 | 2023-05-19 | COMP | 2023-05-31 | COMP | 2023-05-31 | COMP |  | INPR | 2023-12-01 | COMP | Rule 16 | 7 | 25 | 8 | 1 |  |  | 164
41904 | 2023-04-07 | 2023-05-15 | 2023-07-12 | 2023-07-12 | COMP | 2023-09-21 | COMP | 2023-10-06 | COMP |  | INPR | 2023-12-07 | COMP | Rule 16 | 27 | 40 | 51 | 12 |  |  | 168
41916 | 2023-04-07 | 2023-05-17 | 2023-06-21 | 2023-06-21 | COMP | 2023-07-21 | COMP | 2023-08-08 | COMP | 2023-08-10 | COMP | 2023-10-11 | COMP | Rule 16 | 29 | 24 | 22 | 13 | 3 | 44 | 130
42020 | 2023-04-07 | 2023-06-01 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-14 | COMP | 2023-08-21 | COMP | 2023-10-10 | COMP | 2023-11-01 | COMP | Rule 16 | 39 | 25 | 6 | 27 | 36 | 17 | 145
42027 | 2023-04-07 | 2023-06-01 | 2023-06-30 | 2023-06-30 | COMP | 2023-11-02 | COMP | 2023-11-02 | COMP | 2023-11-07 | COMP | 2023-11-14 | COMP | Unknown | 39 | 21 | 88 | 1 | 4 | 5 | 153
42227 | 2023-04-07 | 2023-07-06 | 2023-08-04 | 2023-08-04 | COMP | 2023-09-21 | COMP | 2023-09-25 | COMP | 2023-11-14 | COMP | 2023-12-01 | COMP | Rule 16 | 62 | 22 | 34 | 3 | 36 | 12 | 164
42252 | 2023-04-07 | 2023-07-11 | 2023-07-27 | 2023-07-27 | COMP | 2023-07-31 | COMP | 2023-08-17 | COMP |  | INPR | 2023-09-29 | COMP | Rule 16 | 65 | 13 | 3 | 14 |  |  | 122
42082 | 2023-04-08 | 2023-06-07 | 2023-07-11 | 2023-07-11 | COMP | 2023-08-09 | COMP | 2023-08-28 | COMP | 2023-08-29 | COMP | 2023-11-10 | COMP | Rule 16 | 42 | 23 | 22 | 14 | 2 | 52 | 150
41761 | 2023-04-10 | 2023-04-26 | 2023-06-21 | 2023-06-21 | COMP | 2023-07-12 | COMP | 2023-08-21 | COMP | 2023-09-07 | COMP | 2023-09-19 | COMP | Rule 16 | 13 | 39 | 15 | 29 | 13 | 9 | 113
41867 | 2023-04-10 | 2023-05-10 | 2023-05-24 | 2023-05-24 | COMP | 2023-05-31 | COMP | 2023-07-11 | COMP | 2023-08-16 | COMP | 2023-10-07 | COMP | Rule 16 | 23 | 11 | 5 | 28 | 27 | 37 | 126
41983 | 2023-04-10 | 2023-05-26 | 2023-07-26 | 2023-07-26 | COMP | 2023-07-31 | COMP | 2023-07-31 | COMP | 2023-07-25 | COMP | 2023-09-08 | COMP | Rule 16 | 35 | 41 | 4 | 1 | 0 | 29 | 106
41989 | 2023-04-10 | 2023-05-25 | 2023-06-28 | 2023-06-28 | COMP | 2023-06-29 | COMP | 2023-08-14 | COMP | 2023-08-21 | COMP | 2023-10-16 | COMP | Rule 16 | 34 | 23 | 2 | 32 | 6 | 40 | 132
42006 | 2023-04-10 | 2023-05-31 | 2023-07-25 | 2023-07-25 | COMP | 2023-07-28 | COMP | 2023-08-23 | COMP | 2023-09-29 | COMP | 2023-12-04 | COMP | Rule 16 | 37 | 38 | 4 | 19 | 27 | 44 | 164
42121 | 2023-04-10 | 2023-06-13 | 2023-07-06 | 2023-07-06 | COMP | 2023-07-27 | COMP | 2023-08-31 | COMP | 2023-11-14 | COMP | 2023-12-07 | COMP | Rule 16 | 46 | 16 | 16 | 26 | 52 | 16 | 167
42178 | 2023-04-10 | 2023-06-26 | 2023-07-25 | 2023-07-25 | COMP | 2023-07-27 | COMP | 2023-07-27 | COMP | 2023-08-03 | COMP | 2023-08-12 | COMP | Rule 16 | 54 | 21 | 3 | 1 | 6 | 7 | 87
42243 | 2023-04-10 | 2023-07-11 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-23 | COMP | 2023-09-20 | COMP | 2023-09-19 | COMP | 2023-12-05 | COMP | Rule 16 | 64 | 18 | 15 | 20 | 0 | 52 | 165
41976 | 2023-04-11 | 2023-05-25 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-17 | COMP | 2023-08-08 | COMP | 2023-09-08 | COMP | 2023-10-10 | COMP | Rule 16 | 33 | 27 | 9 | 17 | 23 | 23 | 127
42202 | 2023-04-11 | 2023-06-30 | 2023-08-08 | 2023-08-08 | COMP | 2023-08-22 | COMP | 2023-09-25 | COMP | 2023-08-22 | COMP | 2023-12-01 | COMP | Rule 16 | 57 | 27 | 11 | 24 | 0 | 47 | 162
41683 | 2023-04-12 | 2023-04-18 | 2023-07-15 | 2023-07-15 | COMP | 2023-07-25 | COMP | 2023-09-05 | COMP | 2023-11-13 | COMP | 2023-12-12 | COMP | Rule 16 | 5 | 61 | 7 | 30 | 49 | 20 | 168
41735 | 2023-04-12 | 2023-04-24 | 2023-05-03 | 2023-05-03 | COMP | 2023-05-17 | COMP | 2023-05-17 | COMP | 2023-05-17 | COMP | 2023-07-31 | COMP | Rule 16 | 9 | 8 | 11 | 1 | 1 | 51 | 76
41953 | 2023-04-12 | 2023-05-22 | 2023-06-28 | 2023-09-07 | COMP | 2023-09-11 | COMP | 2023-11-06 | COMP |  | INPR | 2023-12-15 | COMP | Rule 16 | 29 | 26 | 3 | 41 |  |  | 171
42126 | 2023-04-12 | 2023-06-13 | 2023-09-07 | 2023-09-07 | COMP | 2023-09-21 | COMP | 2023-11-07 | COMP | 2023-08-05 | COMP | 2023-11-28 | COMP | Rule 16 | 44 | 60 | 11 | 34 | 0 | 13 | 158
42225 | 2023-04-12 | 2023-07-06 | 2023-08-28 | 2023-08-28 | COMP | 2023-09-05 | COMP | 2023-09-05 | COMP | 2023-10-16 | COMP | 2023-12-15 | COMP | Rule 16 | 59 | 38 | 6 | 1 | 30 | 42 | 171
42266 | 2023-04-12 | 2023-07-14 | 2023-08-18 | 2023-08-18 | COMP | 2023-09-18 | COMP | 2023-09-18 | COMP | 2023-09-18 | COMP | 2023-11-17 | COMP | Rule 16 | 65 | 26 | 21 | 1 | 1 | 44 | 153
42267 | 2023-04-12 | 2023-07-14 | 2023-10-09 | 2023-10-09 | COMP | 2023-10-30 | COMP | 2023-11-29 | COMP | 2023-10-31 | COMP | 2023-12-20 | COMP | Rule 16 | 65 | 61 | 16 | 20 | 0 | 16 | 174
42333 | 2023-04-12 | 2023-08-02 | 2023-10-12 | 2023-10-12 | COMP | 2023-10-23 | COMP | 2023-12-08 | COMP | 2023-11-13 | COMP | 2023-12-10 | COMP | Rule 16 | 78 | 51 | 8 | 32 | 0 | 1 | 166
42348 | 2023-04-12 | 2023-08-07 | 2023-08-17 | 2023-08-17 | COMP | 2023-09-20 | COMP | 2023-09-20 | COMP | 2023-10-10 | COMP | 2023-11-21 | COMP | Rule 16 | 81 | 9 | 24 | 1 | 15 | 30 | 155
42389 | 2023-04-12 | 2023-08-18 | 2023-10-31 | 2023-10-31 | COMP | 2023-11-03 | COMP | 2023-11-28 | COMP | 2023-12-01 | COMP | 2023-12-26 | COMP | Rule 16 | 90 | 52 | 4 | 15 | 4 | 17 | 177
42460 | 2023-04-12 | 2023-09-27 | 2023-11-01 | 2023-11-01 | COMP | 2023-12-06 | COMP | 2023-12-06 | COMP | 2023-12-01 | COMP | 2023-12-27 | COMP | Rule 16 | 117 | 26 | 23 | 1 | 0 | 15 | 178
41882 | 2023-04-13 | 2023-05-11 | 2023-07-29 | 2023-07-29 | COMP | 2023-10-06 | COMP | 2023-10-06 | COMP | 2023-10-20 | COMP | 2023-11-28 | COMP | Rule 16 | 21 | 54 | 49 | 1 | 11 | 25 | 157
41958 | 2023-04-13 | 2023-05-23 | 2023-06-01 | 2023-06-01 | COMP | 2023-06-30 | COMP | 2023-06-30 | COMP | 2023-10-23 | COMP | 2023-11-11 | COMP | Rule 16 | 29 | 7 | 21 | 1 | 80 | 14 | 147
41979 | 2023-04-13 | 2023-05-25 | 2023-07-25 | 2023-07-25 | COMP | 2023-07-26 | NOTN | 2023-08-24 | COMP | 2023-08-07 | COMP | 2023-09-28 | COMP | Other | 31 | 41 |  | 23 | 0 | 25 | 117
42018 | 2023-04-13 | 2023-05-31 | 2023-07-05 | 2023-07-05 | COMP | 2023-08-01 | COMP | 2023-09-29 | COMP | 2023-09-25 | COMP | 2023-10-06 | COMP | Rule 15/16 | 34 | 24 | 20 | 43 | 0 | 6 | 123
42060 | 2023-04-13 | 2023-06-05 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-10 | COMP | 2023-09-21 | COMP | 2023-08-10 | COMP | 2023-11-06 | COMP | Rule 16 | 37 | 39 | 9 | 30 | 0 | 33 | 144
42124 | 2023-04-13 | 2023-06-13 | 2023-07-19 | 2023-07-19 | COMP | 2023-08-02 | COMP | 2023-08-21 | COMP | 2023-09-18 | COMP | 2023-11-02 | COMP | Rule 16 | 43 | 25 | 11 | 14 | 20 | 34 | 142
42177 | 2023-04-13 | 2023-06-27 | 2023-07-31 | 2023-07-31 | COMP | 2023-07-31 | NOTN | 2023-10-03 | COMP | 2023-08-15 | COMP | 2023-11-13 | COMP | Other | 52 | 24 |  | 46 | 0 | 29 | 148
42198 | 2023-04-13 | 2023-06-29 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-16 | COMP | 2023-08-16 | COMP | 2023-11-01 | COMP | 2023-12-11 | COMP | Rule 16 | 54 | 26 | 9 | 1 | 55 | 26 | 166
42302 | 2023-04-13 | 2023-07-26 | 2023-09-05 | 2023-09-05 | COMP | 2023-09-06 | COMP | 2023-10-20 | COMP | 2023-11-08 | COMP | 2023-11-14 | COMP | Rule 16 | 72 | 29 | 2 | 33 | 14 | 4 | 149
41988 | 2023-04-14 | 2023-05-25 | 2023-07-11 | 2023-07-11 | COMP | 2023-07-13 | COMP | 2023-08-02 | COMP | 2023-09-27 | COMP | 2023-10-09 | COMP | Rule 16 | 30 | 31 | 3 | 15 | 40 | 9 | 123
42028 | 2023-04-14 | 2023-06-01 | 2023-08-12 | 2023-08-12 | COMP | 2023-08-14 | NOTN | 2023-08-25 | COMP | 2023-08-30 | COMP | 2023-10-20 | COMP | Other | 34 | 50 |  | 10 | 4 | 37 | 132
42029 | 2023-04-14 | 2023-06-01 | 2023-09-04 | 2023-09-04 | COMP | 2023-09-15 | COMP | 2023-09-15 | COMP | 2023-09-19 | COMP | 2023-10-30 | COMP | Rule 16 | 34 | 65 | 9 | 1 | 3 | 30 | 138
42032 | 2023-04-14 | 2023-06-01 | 2023-06-15 | 2023-06-15 | COMP | 2023-06-16 | NOTN | 2023-06-20 | COMP | 2023-06-29 | COMP | 2023-12-07 | COMP | Other | 34 | 11 |  | 3 | 8 | 111 | 163
42051 | 2023-04-14 | 2023-06-05 | 2023-07-03 | 2023-07-03 | COMP | 2023-07-12 | COMP | 2023-08-30 | COMP | 2023-09-12 | COMP | 2023-09-25 | COMP | Rule 16 | 36 | 20 | 7 | 36 | 9 | 10 | 113
42146 | 2023-04-14 | 2023-06-20 | 2023-07-16 | 2023-07-16 | COMP | 2023-08-18 | COMP | 2023-08-28 | COMP | 2023-11-02 | COMP | 2023-11-27 | COMP | Rule 16 | 46 | 18 | 25 | 7 | 48 | 15 | 155
42191 | 2023-04-14 | 2023-06-29 | 2023-07-17 | 2023-07-17 | COMP | 2023-08-03 | COMP | 2023-12-11 | COMP | 2023-11-02 | COMP | 2023-12-15 | COMP | Rule 16 | 53 | 12 | 14 | 89 | 0 | 5 | 169
42239 | 2023-04-14 | 2023-07-10 | 2023-07-28 | 2023-07-28 | COMP | 2023-08-02 | COMP | 2023-08-09 | COMP | 2023-10-17 | COMP | 2023-12-05 | COMP | Rule 16 | 59 | 15 | 4 | 6 | 49 | 33 | 161
42256 | 2023-04-14 | 2023-07-13 | 2023-08-17 | 2023-08-17 | COMP | 2023-08-21 | COMP | 2023-10-03 | COMP | 2023-12-27 | COMP | 2023-11-06 | COMP | Rule 16 | 62 | 26 | 3 | 31 | 58 |  | 143
42303 | 2023-04-14 | 2023-07-26 | 2023-08-14 | 2023-08-14 | COMP | 2023-10-12 | COMP | 2023-10-12 | COMP | 2023-11-06 | COMP | 2023-12-12 | COMP | Rule 16 | 71 | 14 | 43 | 1 | 18 | 24 | 166
42326 | 2023-04-14 | 2023-08-01 | 2023-09-04 | 2023-09-04 | COMP | 2023-09-08 | COMP | 2023-09-29 | COMP | 2023-10-10 | COMP | 2023-11-28 | COMP | Rule 16 | 75 | 24 | 4 | 16 | 8 | 33 | 156
41693 | 2023-04-15 | 2023-04-20 | 2023-06-26 | 2023-06-26 | COMP | 2023-06-27 | NOTN | 2023-07-03 | COMP | 2023-12-26 | COMP | 2023-10-25 | COMP | Other | 4 | 46 |  | 6 | 121 |  | 134
41864 | 2023-04-15 | 2023-05-10 | 2023-06-22 | 2023-06-22 | COMP | 2023-06-24 | NOTN | 2023-07-10 | COMP | 2023-06-24 | COMP | 2023-10-11 | COMP | Other | 18 | 30 |  | 12 | 0 | 67 | 124
41966 | 2023-04-17 | 2023-05-24 | 2023-06-05 | 2023-06-05 | COMP | 2023-08-29 | COMP | 2023-08-29 | COMP | 2023-11-15 | COMP | 2023-12-17 | COMP | Rule 16 | 28 | 8 | 60 | 1 | 55 | 21 | 168
41970 | 2023-04-17 | 2023-05-24 | 2023-07-04 | 2023-07-04 | COMP | 2023-07-20 | COMP | 2023-07-20 | COMP | 2023-07-26 | COMP | 2023-09-11 | COMP | Rule 15/16 | 28 | 27 | 12 | 1 | 5 | 33 | 102
42017 | 2023-04-17 | 2023-05-31 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-28 | COMP |  | REQD | 2023-11-08 | COMP | 2023-11-11 | COMP | Rule 16 | 32 | 26 | 16 |  |  |  | 145
42034 | 2023-04-17 | 2023-06-02 | 2023-07-03 | 2023-09-12 | COMP | 2023-09-18 | COMP | 2023-10-20 | COMP | 2023-06-29 | COMP | 2023-11-28 | COMP | Rule 16 | 34 | 21 | 5 | 25 | 0 | 25 | 155
42101 | 2023-04-17 | 2023-06-09 | 2023-07-26 | 2023-07-26 | COMP | 2023-08-15 | COMP | 2023-09-27 | COMP | 2023-08-15 | COMP | 2023-10-18 | COMP | Rule 16 | 39 | 32 | 15 | 31 | 0 | 16 | 129
42122 | 2023-04-17 | 2023-06-12 | 2023-06-21 | 2023-07-10 | COMP | 2023-07-13 | COMP | 2023-07-18 | COMP | 2023-07-28 | COMP | 2023-09-20 | COMP | Rule 16 | 40 | 7 | 4 | 4 | 9 | 38 | 109
42203 | 2023-04-17 | 2023-06-30 | 2023-09-01 | 2023-09-01 | COMP | 2023-09-01 | NOTN | 2023-09-26 | COMP | 2023-09-01 | COMP | 2023-11-01 | COMP | Other | 53 | 45 |  | 17 | 0 | 27 | 139
42283 | 2023-04-17 | 2023-07-20 | 2023-08-24 | 2023-08-24 | COMP | 2023-08-28 | COMP |  | REQD | 2024-01-16 | COMP | 2023-12-19 | COMP | Rule 16 | 66 | 26 | 3 |  |  |  | 170
42448 | 2023-04-17 | 2023-09-19 | 2023-10-04 | 2023-10-04 | COMP | 2023-10-09 | NOTN | 2023-10-09 | COMP | 2023-10-10 | COMP | 2023-10-25 | COMP | Other | 108 | 12 |  | 4 | 2 | 12 | 134
42014 | 2023-04-18 | 2023-05-31 | 2023-07-21 | 2023-07-21 | COMP | 2023-09-06 | COMP | 2023-09-06 | INPR | 2023-08-09 | COMP | 2023-10-25 | COMP | Rule 16 | 31 | 36 | 33 |  |  |  | 133
42016 | 2023-04-18 | 2023-05-31 | 2023-07-17 | 2023-07-17 | COMP | 2023-08-03 | COMP | 2023-10-11 | COMP | 2023-07-18 | COMP | 2023-11-13 | COMP | Rule 16 | 31 | 32 | 14 | 49 | 0 | 23 | 145
42156 | 2023-04-18 | 2023-06-21 | 2023-07-17 | 2023-07-17 | COMP | 2023-07-27 | COMP | 2023-07-27 | COMP | 2023-08-14 | COMP | 2023-09-04 | COMP | Rule 16 | 45 | 18 | 9 | 1 | 13 | 15 | 96
42437 | 2023-04-18 | 2023-09-08 | 2023-09-15 | 2023-09-20 | COMP | 2023-09-25 | COMP | 2023-09-26 | COMP | 2023-09-28 | COMP | 2023-10-25 | COMP | Rule 16 | 100 | 6 | 4 | 2 | 3 | 20 | 133
41724 | 2023-04-19 | 2023-04-23 | 2023-07-19 | 2023-07-19 | COMP | 2023-07-20 | NOTN | 2023-09-05 | COMP | 2023-07-20 | COMP | 2023-12-14 | COMP | Other | 3 | 60 |  | 34 | 0 | 70 | 165
41726 | 2023-04-19 | 2023-04-23 | 2023-07-18 | 2023-07-18 | COMP | 2023-07-19 | NOTN | 2023-09-05 | COMP | 2023-07-19 | COMP | 2023-12-06 | COMP | Other | 3 | 59 |  | 35 | 0 | 64 | 159
42008 | 2023-04-19 | 2023-05-30 | 2023-06-14 | 2023-06-14 | COMP | 2023-10-31 | COMP | 2023-11-07 | COMP |  | INPR | 2023-12-12 | COMP | Rule 16 | 29 | 12 | 97 | 6 |  |  | 163
42045 | 2023-04-19 | 2023-06-02 | 2023-06-19 | 2023-06-19 | COMP | 2023-07-11 | COMP | 2023-10-02 | COMP | 2023-09-29 | COMP | 2023-10-12 | COMP | Rule 16 | 32 | 11 | 15 | 59 | 0 | 9 | 123
42127 | 2023-04-19 | 2023-06-13 | 2023-07-01 | 2023-07-21 | COMP | 2023-08-01 | COMP | 2023-08-31 | COMP |  | INPR | 2023-09-14 | COMP | Rule 16 | 39 | 13 | 8 | 23 |  |  | 103
42142 | 2023-04-19 | 2023-06-20 | 2023-07-17 | 2023-07-17 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP | 2023-08-15 | COMP | 2023-10-10 | COMP | Rule 16 | 43 | 19 | 18 | 1 | 5 | 40 | 121
42190 | 2023-04-19 | 2023-06-29 | 2023-08-21 | 2023-08-21 | COMP | 2023-08-25 | COMP | 2023-10-09 | COMP |  | INPR | 2023-11-14 | COMP | Rule 16 | 50 | 37 | 5 | 31 |  |  | 145
42248 | 2023-04-19 | 2023-07-11 | 2023-08-23 | 2023-08-23 | COMP | 2023-08-25 | NOTN | 2023-10-10 | COMP | 2023-09-13 | COMP | 2023-10-25 | COMP | Other | 57 | 32 |  | 34 | 0 | 12 | 132
42362 | 2023-04-19 | 2023-08-10 | 2023-09-18 | 2023-09-18 | COMP | 2023-09-28 | COMP | 2023-11-13 | COMP | 2023-09-28 | COMP | 2023-12-20 | COMP | Rule 16 | 79 | 27 | 9 | 32 | 0 | 26 | 169
41710 | 2023-04-20 | 2023-04-21 | 2023-07-03 | 2023-07-03 | COMP | 2023-07-06 | NOTN | 2023-09-11 | COMP | 2023-08-23 | COMP | 2023-09-25 | COMP | Other | 2 | 50 |  | 49 | 0 | 11 | 109
41921 | 2023-04-20 | 2023-05-18 | 2023-09-15 | 2023-09-15 | COMP | 2023-09-15 | NOTN |  | REQD | 2023-10-26 | COMP | 2023-12-06 | COMP | Other | 21 | 83 |  |  |  |  | 158
42039 | 2023-04-20 | 2023-06-02 | 2023-07-28 | 2023-07-28 | COMP | 2023-09-06 | COMP | 2023-09-06 | COMP | 2023-10-20 | COMP | 2023-11-10 | COMP | Rule 16 | 31 | 39 | 28 | 1 | 33 | 15 | 142
42048 | 2023-04-20 | 2023-06-03 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-10 | COMP | 2023-10-31 | COMP | 2023-08-30 | COMP | 2023-11-03 | COMP | Rule 16 | 31 | 41 | 7 | 58 | 0 | 4 | 138
42066 | 2023-04-20 | 2023-06-06 | 2023-07-05 | 2023-07-31 | COMP | 2023-08-02 | COMP | 2023-09-07 | COMP | 2023-09-27 | COMP | 2023-10-25 | COMP | Rule 16 | 33 | 20 | 3 | 26 | 15 | 21 | 131
42154 | 2023-04-20 | 2023-06-21 | 2023-08-12 | 2023-08-12 | COMP | 2023-08-17 | COMP | 2023-09-29 | COMP | 2023-10-16 | COMP | 2023-11-20 | COMP | Rule 16 | 43 | 37 | 4 | 31 | 12 | 25 | 148
42166 | 2023-04-20 | 2023-06-23 | 2023-08-07 | 2023-08-07 | COMP | 2023-08-21 | COMP | 2023-08-21 | COMP | 2023-11-06 | COMP | 2023-11-28 | COMP | Rule 15/16 | 45 | 31 | 11 | 1 | 55 | 14 | 152
42210 | 2023-04-20 | 2023-07-03 | 2023-08-23 | 2023-08-23 | COMP | 2023-08-25 | COMP | 2023-08-28 | COMP | 2023-08-25 | COMP | 2023-10-11 | COMP | Rule 16 | 51 | 37 | 3 | 2 | 0 | 32 | 121
42229 | 2023-04-20 | 2023-07-07 | 2023-07-26 | 2023-07-26 | COMP | 2023-08-16 | COMP | 2023-09-11 | COMP | 2023-11-28 | COMP | 2023-12-13 | COMP | Rule 16 | 54 | 14 | 16 | 18 | 54 | 12 | 163
42439 | 2023-04-20 | 2023-09-12 | 2023-10-18 | 2023-10-18 | COMP | 2023-11-10 | COMP | 2023-11-10 | COMP | 2023-11-08 | COMP | 2023-12-05 | COMP | Rule 16 | 100 | 27 | 17 | 0 | 0 | 15 | 157
41734 | 2023-04-21 | 2023-04-24 | 2023-07-14 | 2023-07-14 | COMP | 2023-07-18 | NOTN | 2023-09-05 | COMP | 2023-09-14 | COMP | 2023-12-13 | COMP | Other | 2 | 57 |  | 37 | 8 | 62 | 162
41778 | 2023-04-21 | 2023-04-27 | 2023-06-03 | 2023-06-03 | COMP | 2023-06-30 | COMP | 2023-06-30 | COMP | 2023-12-15 | COMP | 2023-12-28 | COMP | Rule 16 | 5 | 26 | 19 | 1 | 116 | 9 | 172
42120 | 2023-04-21 | 2023-06-12 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-12 | COMP | 2023-09-18 | COMP | 2023-09-28 | COMP | 2023-12-13 | COMP | Rule 16 | 36 | 16 | 6 | 48 | 9 | 52 | 162
42288 | 2023-04-21 | 2023-07-20 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-10 | COMP | 2023-09-20 | COMP | 2023-09-15 | COMP | 2023-11-03 | COMP | Rule 16 | 62 | 10 | 7 | 29 | 0 | 33 | 137
42323 | 2023-04-21 | 2023-07-31 | 2023-08-28 | 2023-08-28 | COMP | 2023-09-06 | COMP | 2023-09-06 | COMP | 2023-11-03 | COMP | 2023-11-27 | COMP | Rule 15/16 | 69 | 21 | 7 | 1 | 43 | 14 | 150
41752 | 2023-04-22 | 2023-04-25 | 2023-06-26 | 2023-06-26 | COMP | 2023-07-07 | COMP | 2023-07-07 | COMP | 2023-07-17 | COMP | 2023-08-07 | COMP | Rule 16 | 2 | 43 | 9 | 1 | 7 | 16 | 73
42180 | 2023-04-22 | 2023-06-27 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-11 | COMP | 2023-08-11 | COMP | 2023-08-16 | COMP | 2023-09-20 | COMP | Rule 16 | 45 | 28 | 6 | 1 | 4 | 25 | 104
42277 | 2023-04-22 | 2023-07-19 | 2023-09-09 | 2023-09-09 | COMP | 2023-10-25 | COMP | 2023-10-27 | COMP | 2023-10-25 | COMP | 2023-12-11 | COMP | Rule 16 | 60 | 37 | 33 | 3 | 0 | 29 | 159
42175 | 2023-04-23 | 2023-06-26 | 2023-07-14 | 2023-07-14 | COMP | 2023-08-03 | COMP | 2023-08-24 | COMP | 2023-09-19 | COMP | 2023-10-26 | COMP | Rule 16 | 44 | 14 | 15 | 16 | 18 | 28 | 130
41743 | 2023-04-24 | 2023-04-25 | 2023-09-15 | 2023-09-15 | COMP | 2023-09-25 | COMP | 2023-09-25 | COMP | 2023-10-10 | COMP | 2023-11-30 | COMP | Rule 16 | 2 | 100 | 7 | 1 | 12 | 35 | 152
41977 | 2023-04-24 | 2023-05-25 | 2023-07-12 | 2023-07-12 | COMP | 2023-07-17 | COMP | 2023-07-20 | COMP | 2023-08-08 | COMP | 2023-08-28 | COMP | Rule 16 | 24 | 32 | 4 | 4 | 14 | 15 | 88
41985 | 2023-04-24 | 2023-05-25 | 2023-06-16 | 2023-06-16 | COMP | 2023-06-29 | COMP | 2023-07-31 | COMP | 2023-07-11 | COMP | 2023-10-04 | COMP | Rule 16 | 24 | 16 | 9 | 22 | 0 | 47 | 114
42010 | 2023-04-24 | 2023-05-31 | 2023-08-16 | 2023-08-16 | COMP | 2023-11-20 | COMP | 2023-10-02 | COMP | 2023-09-29 | COMP | 2023-11-28 | COMP | Rule 16 | 27 | 54 | 67 |  | 0 | 39 | 150
42115 | 2023-04-24 | 2023-06-12 | 2023-09-05 | 2023-09-05 | COMP | 2023-09-15 | COMP | 2023-09-15 | COMP | 2023-10-03 | COMP | 2023-10-20 | COMP | Rule 16 | 35 | 59 | 9 | 1 | 13 | 14 | 126
42136 | 2023-04-24 | 2023-06-15 | 2023-06-30 | 2023-06-30 | COMP | 2023-08-07 | COMP | 2023-08-22 | COMP | 2023-08-23 | COMP | 2023-10-17 | COMP | Rule 16 | 38 | 11 | 26 | 12 | 2 | 39 | 123
42300 | 2023-04-24 | 2023-07-25 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-20 | NOTN | 2023-09-18 | COMP | 2023-08-29 | COMP | 2023-11-10 | COMP | Rule 16 | 64 | 7 |  | 33 | 0 | 39 | 140
42463 | 2023-04-24 | 2023-10-02 | 2023-10-27 | 2023-10-27 | COMP | 2023-11-02 | COMP | 2023-11-09 | COMP | 2023-11-16 | COMP | 2023-12-22 | COMP | Rule 16 | 112 | 20 | 5 | 6 | 5 | 25 | 168
41938 | 2023-04-25 | 2023-05-19 | 2023-07-27 | 2023-07-27 | COMP | 2023-08-16 | COMP | 2023-09-11 | COMP | 2023-10-02 | COMP | 2023-10-23 | COMP | Rule 15/16 | 19 | 47 | 15 | 18 | 16 | 16 | 126
41957 | 2023-04-25 | 2023-05-23 | 2023-06-05 | 2023-06-05 | COMP | 2023-09-08 | COMP | 2023-09-08 | COMP | 2023-09-09 | COMP | 2023-10-11 | COMP | Rule 16 | 21 | 9 | 67 | 1 | 1 | 23 | 118
42031 | 2023-04-25 | 2023-06-01 | 2023-06-10 | 2023-06-10 | COMP | 2023-06-21 | COMP | 2023-06-21 | COMP | 2023-08-11 | COMP | 2023-10-09 | COMP | Rule 16 | 27 | 7 | 7 | 1 | 37 | 41 | 116
42038 | 2023-04-25 | 2023-06-02 | 2023-08-09 | 2023-08-09 | COMP | 2023-08-25 | COMP | 2023-08-25 | COMP | 2023-11-09 | COMP | 2023-12-13 | COMP | Rule 16 | 28 | 47 | 13 | 1 | 54 | 22 | 160
42103 | 2023-04-25 | 2023-06-10 | 2023-07-27 | 2023-07-27 | COMP | 2023-08-16 | COMP | 2023-08-16 | COMP | 2023-09-20 | COMP | 2023-10-12 | COMP | Rule 16 | 33 | 32 | 15 | 1 | 25 | 17 | 119
42370 | 2023-04-25 | 2023-08-14 | 2023-09-11 | 2023-09-11 | COMP | 2023-09-26 | COMP | 2023-09-26 | COMP | 2023-10-20 | COMP | 2023-11-30 | COMP | Rule 16 | 77 | 20 | 12 | 1 | 19 | 27 | 151
42397 | 2023-04-25 | 2023-08-22 | 2023-09-06 | 2023-09-06 | COMP | 2023-09-15 | COMP | 2023-10-20 | COMP | 2023-11-06 | COMP | 2023-11-14 | COMP | Rule 16 | 83 | 11 | 8 | 26 | 12 | 6 | 141
42077 | 2023-04-26 | 2023-06-07 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-07 | NOTN | 2023-08-22 | COMP | 2023-09-07 | COMP | 2023-10-24 | COMP | Other | 30 | 21 |  | 33 | 12 | 34 | 126
42091 | 2023-04-26 | 2023-06-09 | 2023-06-26 | 2023-06-26 | COMP | 2023-07-06 | COMP | 2023-07-06 | COMP | 2023-10-10 | COMP | 2023-10-20 | COMP | Rule 16 | 32 | 11 | 8 | 1 | 68 | 9 | 124
42199 | 2023-04-26 | 2023-06-30 | 2023-09-18 | 2023-09-18 | COMP | 2023-10-12 | COMP | 2023-10-18 | COMP | 2023-10-18 | COMP | 2023-12-09 | COMP | Rule 16 | 46 | 55 | 19 | 5 | 1 | 35 | 156
42204 | 2023-04-26 | 2023-06-30 | 2023-08-23 | 2023-08-23 | COMP | 2023-08-30 | NOTN | 2023-10-16 | COMP |  | INPR | 2023-11-15 | COMP | Other | 46 | 38 |  | 38 |  |  | 141
42216 | 2023-04-26 | 2023-07-05 | 2023-08-11 | 2023-08-11 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP | 2023-09-08 | COMP | 2023-09-28 | COMP | Rule 16 | 48 | 28 | 3 | 1 | 18 | 15 | 108
41799 | 2023-04-27 | 2023-05-01 | 2023-05-24 | 2023-05-24 | COMP | 2023-05-25 | NOTN | 2023-05-25 | COMP | 2023-05-25 | COMP | 2023-06-28 | COMP | Other | 3 | 18 |  | 2 | 1 | 23 | 43
42013 | 2023-04-27 | 2023-05-31 | 2023-06-13 | 2023-06-13 | COMP | 2023-11-07 | COMP | 2023-11-07 | COMP | 2023-11-27 | COMP | 2023-11-29 | COMP | Rule 16 | 24 | 10 | 103 | 1 | 12 | 3 | 148
42160 | 2023-04-27 | 2023-06-21 | 2023-08-12 | 2023-08-12 | COMP | 2023-08-16 | COMP | 2023-08-16 | COMP | 2023-09-22 | COMP | 2023-10-11 | COMP | Rule 16 | 38 | 37 | 3 | 1 | 27 | 14 | 116
42299 | 2023-04-27 | 2023-07-25 | 2023-08-04 | 2023-08-04 | COMP | 2023-10-20 | COMP | 2023-10-27 | COMP | 2023-10-26 | COMP | 2023-12-04 | COMP | Rule 16 | 61 | 9 | 55 | 6 | 0 | 24 | 151
42346 | 2023-04-27 | 2023-08-06 | 2023-09-13 | 2023-09-13 | COMP | 2023-10-05 | COMP | 2023-12-05 | COMP | 2023-11-15 | COMP | 2023-12-01 | COMP | Rule 16 | 69 | 27 | 17 | 41 | 0 |  | 150
41857 | 2023-04-28 | 2023-05-08 | 2023-05-30 | 2023-05-30 | COMP | 2023-06-06 | COMP | 2023-08-09 | COMP | 2023-08-03 | COMP | 2023-08-28 | COMP | Rule 16 | 7 | 16 | 6 | 45 | 0 | 14 | 84
42264 | 2023-04-28 | 2023-07-13 | 2023-08-22 | 2023-08-22 | COMP | 2023-08-24 | COMP | 2023-11-07 | COMP | 2023-11-14 | COMP | 2023-12-29 | COMP | Rule 16 | 52 | 29 | 3 | 53 | 5 | 31 | 168
42090 | 2023-04-29 | 2023-06-09 | 2023-07-15 | 2023-07-15 | COMP | 2023-07-25 | COMP | 2023-08-04 | COMP | 2023-09-13 | COMP | 2023-12-22 | COMP | Rule 16 | 29 | 24 | 7 | 9 | 28 | 70 | 163
42255 | 2023-04-30 | 2023-07-12 | 2023-08-28 | 2023-08-28 | COMP | 2023-09-29 | COMP | 2023-10-16 | COMP | 2023-10-17 | COMP | 2023-12-27 | COMP | Rule 15/16 | 50 | 34 | 24 | 12 | 2 | 48 | 165
42063 | 2023-05-01 | 2023-06-05 | 2023-06-19 | 2023-06-19 | COMP | 2023-06-29 | COMP | 2023-06-29 | COMP |  | INPR | 2023-12-06 | COMP | Rule 16 | 25 | 10 | 8 | 1 |  |  | 151
42100 | 2023-05-01 | 2023-06-09 | 2023-07-12 | 2023-07-12 | COMP | 2023-08-11 | COMP | 2023-08-11 | COMP | 2023-09-28 | COMP | 2023-10-07 | COMP | Rule 15/16 | 29 | 22 | 23 | 1 | 34 | 7 | 111
42110 | 2023-05-01 | 2023-06-12 | 2023-07-07 | 2023-07-28 | COMP | 2023-08-09 | COMP | 2023-08-02 | COMP | 2023-08-21 | COMP | 2023-10-05 | COMP | Rule 16 | 30 | 18 | 9 |  | 14 | 33 | 110
42159 | 2023-05-01 | 2023-06-21 | 2023-07-20 | 2023-07-20 | COMP | 2023-08-07 | COMP | 2023-09-07 | COMP | 2023-08-11 | COMP | 2023-10-09 | COMP | Rule 16 | 36 | 21 | 13 | 23 | 0 | 23 | 112
42310 | 2023-05-01 | 2023-07-26 | 2023-08-31 | 2023-08-31 | COMP | 2023-09-12 | COMP | 2023-09-12 | COMP |  | INPR | 2023-10-12 | COMP | Rule 16 | 60 | 27 | 8 | 1 |  |  | 115
41815 | 2023-05-02 | 2023-05-03 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-12 | NOTN | 2023-10-09 | COMP | 2023-10-19 | COMP | 2023-12-11 | COMP | Other | 2 | 35 |  | 76 | 9 | 35 | 153
42000 | 2023-05-02 | 2023-05-30 | 2023-06-27 | 2023-06-27 | COMP | 2023-07-26 | COMP | 2023-08-14 | COMP | 2023-08-21 | COMP | 2023-10-09 | COMP | Rule 16 | 20 | 20 | 21 | 14 | 6 | 35 | 111
42105 | 2023-05-02 | 2023-06-12 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-11-13 | COMP | 2023-11-27 | COMP | Rule 16 | 29 | 36 | 3 | 1 | 70 | 9 | 143
42209 | 2023-05-02 | 2023-07-03 | 2023-08-23 | 2023-08-23 | COMP | 2023-08-31 | COMP | 2023-10-26 | COMP | 2023-09-01 | COMP | 2023-12-18 | COMP | Rule 16 | 43 | 37 | 7 | 40 | 0 | 35 | 158
42219 | 2023-05-02 | 2023-07-05 | 2023-07-16 | 2023-07-16 | COMP | 2023-08-16 | COMP | 2023-09-01 | COMP | 2023-09-07 | COMP | 2023-10-09 | COMP | Rule 16 | 44 | 8 | 23 | 13 | 4 | 23 | 111
42293 | 2023-05-02 | 2023-07-24 | 2023-08-04 | 2023-08-04 | COMP | 2023-09-01 | COMP | 2023-09-01 | INPR | 2023-09-08 | COMP | 2023-09-20 | COMP | Rule 16 | 57 | 10 | 21 |  |  |  | 98
42410 | 2023-05-02 | 2023-08-25 | 2023-10-23 | 2023-10-23 | COMP | 2023-11-06 | COMP | 2023-11-06 | NOTN | 2023-11-10 | COMP | 2023-11-21 | COMP | Rule 16 | 81 | 41 | 11 |  |  |  | 141
41834 | 2023-05-03 | 2023-05-05 | 2023-06-07 | 2023-06-07 | COMP | 2023-08-09 | COMP | 2023-08-18 | COMP | 2023-08-10 | COMP | 2023-10-16 | COMP | Rule 16 | 3 | 23 | 44 | 8 | 0 | 41 | 115
42161 | 2023-05-03 | 2023-06-21 | 2023-09-02 | 2023-09-02 | COMP | 2023-09-07 | COMP | 2023-09-15 | COMP | 2023-12-11 | COMP | 2023-12-11 | COMP | Rule 16 | 34 | 52 | 3 | 7 | 59 | 1 | 152
42228 | 2023-05-03 | 2023-07-06 | 2023-08-17 | 2023-08-17 | COMP | 2023-09-05 | COMP | 2023-09-15 | COMP | 2023-09-29 | COMP | 2023-01-05 | COMP | Rule 16 | 44 | 31 | 13 | 9 | 11
42249 | 2023-05-03 | 2023-07-11 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-21 | COMP | 2023-10-04 | COMP | 2023-10-21 | COMP | 2023-12-07 | COMP | Rule 16 | 47 | 23 | 8 | 32 | 13 | 31 | 150
42268 | 2023-05-03 | 2023-07-15 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-07 | NOTN | 2023-09-01 | COMP | 2023-09-01 | COMP | 2023-11-04 | COMP | Other | 50 | 14 |  | 22 | 1 | 45 | 129
42316 | 2023-05-03 | 2023-07-27 | 2023-08-28 | 2023-08-28 | COMP | 2023-08-31 | COMP | 2023-10-20 | COMP | 2023-09-11 | COMP | 2023-11-16 | COMP | Rule 16 | 59 | 23 | 4 | 36 | 0 | 19 | 137
42325 | 2023-05-03 | 2023-07-31 | 2023-08-22 | 2023-08-22 | COMP | 2023-08-23 | NOTN | 2023-08-23 | COMP | 2023-08-24 | COMP | 2023-09-28 | COMP | Other | 61 | 17 |  | 2 | 2 | 25 | 103
42328 | 2023-05-03 | 2023-08-01 | 2023-08-15 | 2023-08-15 | COMP | 2023-09-28 | COMP | 2023-09-28 | COMP | 2023-10-30 | COMP | 2023-12-06 | COMP | Rule 16 | 62 | 11 | 32 | 1 | 23 | 25 | 149
42331 | 2023-05-03 | 2023-08-01 | 2023-09-08 | 2023-09-08 | COMP | 2023-09-10 | NOTN | 2023-09-18 | COMP | 2023-10-09 | COMP | 2023-12-08 | COMP | Other | 62 | 28 |  | 7 | 16 | 42 | 151
42337 | 2023-05-03 | 2023-08-02 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-23 | COMP | 2023-09-06 | COMP | 2023-08-31 | COMP | 2023-10-05 | COMP | Rule 16 | 63 | 7 | 10 | 10 | 0 | 22 | 108
42342 | 2023-05-03 | 2023-08-04 | 2023-09-15 | 2023-09-15 | COMP | 2023-09-20 | COMP | 2023-10-30 | COMP | 2023-10-02 | COMP | 2023-11-15 | COMP | Rule 16 | 65 | 30 | 4 | 29 | 0 | 12 | 136
42369 | 2023-05-03 | 2023-08-13 | 2023-08-18 | 2023-08-18 | COMP | 2023-08-30 | COMP | 2023-09-06 | COMP | 2023-08-30 | COMP | 2023-10-03 | COMP | Rule 16 | 70 | 5 | 9 | 5 | 0 | 20 | 106
42053 | 2023-05-04 | 2023-06-05 | 2023-06-15 | 2023-06-15 | COMP | 2023-06-21 | COMP | 2023-06-21 | COMP | 2023-10-05 | COMP | 2023-11-01 | COMP | Rule 16 | 22 | 9 | 4 | 1 | 75 | 20 | 126
42269 | 2023-05-04 | 2023-07-15 | 2023-09-11 | 2023-09-11 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-10-02 | COMP | 2023-12-05 | COMP | Rule 16 | 49 | 40 | 7 | 1 | 10 | 44 | 147
42304 | 2023-05-04 | 2023-07-26 | 2023-08-11 | 2023-08-11 | COMP | 2023-10-05 | COMP | 2023-10-05 | COMP | 2023-10-06 | COMP | 2023-11-29 | COMP | Rule 16 | 57 | 13 | 39 | 1 | 2 | 36 | 143
41870 | 2023-05-05 | 2023-05-10 | 2023-06-06 | 2023-06-06 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-09-29 | COMP | 2023-11-03 | COMP | Rule 16 | 4 | 19 | 42 | 1 | 40 | 26 | 127
41956 | 2023-05-05 | 2023-05-23 | 2023-08-21 | 2023-09-11 | COMP | 2023-11-30 | COMP | 2023-11-30 | COMP | 2023-11-30 | COMP | 2023-12-04 | COMP | Rule 16 | 13 | 62 | 56 | 1 | 1 | 3 | 145
41990 | 2023-05-05 | 2023-05-26 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-08 | COMP | 2023-11-16 | COMP | 2023-09-20 | COMP | 2023-12-26 | COMP | Rule 16 | 16 | 46 | 5 | 71 | 0 | 26 | 160
42072 | 2023-05-05 | 2023-06-06 | 2023-06-27 | 2023-06-27 | COMP | 2023-08-08 | COMP | 2023-08-15 | COMP | 2023-09-26 | COMP | 2023-11-01 | COMP | Rule 16 | 22 | 15 | 30 | 6 | 30 | 27 | 125
42235 | 2023-05-05 | 2023-07-10 | 2023-08-19 | 2023-08-19 | COMP | 2023-11-08 | COMP | 2023-11-14 | COMP | 2023-11-10 | COMP | 2023-11-16 | COMP | Rule 16 | 44 | 30 | 57 | 4 | 0 | 3 | 135
42240 | 2023-05-05 | 2023-07-10 | 2023-07-18 | 2023-08-25 | COMP | 2023-08-30 | COMP | 2023-08-01 | COMP |  | INPR | 2023-09-27 | COMP | Rule 16 | 44 | 7 | 4 |  |  |  | 100
42261 | 2023-05-05 | 2023-07-13 | 2023-09-25 | 2023-09-25 | COMP | 2023-10-03 | COMP | 2023-10-03 | COMP | 2023-11-03 | COMP | 2023-11-28 | COMP | Rule 16 | 47 | 52 | 7 | 1 | 24 | 15 | 141
42067 | 2023-05-06 | 2023-06-05 | 2023-08-16 | 2023-08-16 | COMP | 2023-09-05 | COMP |  | REQD |  | REQD | 2023-11-21 | COMP | Rule 16 | 20 | 51 | 14 |  |  |  | 137
42144 | 2023-05-06 | 2023-06-19 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-14 | COMP | 2023-10-13 | COMP | 2023-10-13 | COMP | 2023-11-21 | COMP | Rule 16 | 29 | 13 | 6 | 65 | 1 | 27 | 137
41914 | 2023-05-07 | 2023-05-17 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-21 | COMP | 2023-10-11 | COMP | 2023-10-19 | COMP | 2023-11-27 | COMP | Rule 16 | 8 | 55 | 12 | 37 | 7 | 25 | 139
41999 | 2023-05-08 | 2023-05-30 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-11 | NOTN | 2023-08-14 | COMP | 2023-08-11 | COMP | 2023-10-05 | COMP | Other | 16 | 51 |  | 3 | 0 | 38 | 105
42093 | 2023-05-08 | 2023-06-09 | 2023-08-13 | 2023-08-13 | COMP | 2023-08-22 | COMP | 2023-11-21 | COMP | 2023-12-05 | COMP | 2023-12-26 | COMP | Rule 15/16 | 24 | 44 | 7 | 64 | 9 | 15 | 159
42309 | 2023-05-08 | 2023-07-27 | 2023-10-12 | 2023-10-12 | COMP | 2023-10-20 | COMP | 2023-12-04 | COMP | 2023-11-28 | COMP | 2023-12-27 | COMP | Rule 16 | 56 | 55 | 7 | 29 | 0 | 17 | 160
42104 | 2023-05-09 | 2023-06-12 | 2023-07-17 | 2023-07-17 | COMP | 2023-07-21 | COMP | 2023-07-21 | COMP | 2023-08-01 | COMP | 2023-08-04 | COMP | Rule 16 | 24 | 24 | 5 | 1 | 8 | 4 | 61
42364 | 2023-05-09 | 2023-08-10 | 2023-09-21 | 2023-09-21 | COMP | 2023-09-26 | COMP | 2023-10-25 | COMP | 2023-09-27 | COMP | 2023-12-05 | COMP | Rule 16 | 65 | 30 | 4 | 22 | 0 | 27 | 144
42394 | 2023-05-09 | 2023-08-21 | 2023-09-28 | 2023-09-28 | COMP | 2023-10-05 | COMP | 2023-10-05 | COMP | 2023-10-16 | COMP | 2023-11-06 | COMP | Rule 16 | 72 | 28 | 6 | 1 | 8 | 16 | 126
41895 | 2023-05-10 | 2023-05-15 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-18 | COMP | 2023-08-18 | COMP | 2023-09-09 | COMP | 2023-09-27 | COMP | Rule 16 | 4 | 61 | 7 | 1 | 15 | 13 | 97
42068 | 2023-05-10 | 2023-06-06 | 2023-07-05 | 2023-07-05 | COMP | 2023-07-10 | COMP | 2023-08-10 | COMP | 2023-08-02 | COMP | 2023-09-18 | COMP | Rule 16 | 19 | 20 | 4 | 24 | 0 | 27 | 90
42102 | 2023-05-10 | 2023-06-09 | 2023-09-27 | 2023-09-27 | COMP | 2023-10-05 | COMP | 2023-11-08 | COMP | 2023-10-05 | COMP | 2023-11-28 | COMP | Rule 16 | 22 | 76 | 7 | 25 | 0 | 12 | 138
42139 | 2023-05-10 | 2023-06-16 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-15 | COMP | 2023-08-15 | COMP | 2023-09-05 | COMP | 2023-10-09 | COMP | Rule 16 | 27 | 30 | 12 | 1 | 15 | 25 | 105
42366 | 2023-05-10 | 2023-08-11 | 2023-09-04 | 2023-09-04 | COMP | 2023-09-12 | COMP | 2023-09-13 | COMP | 2023-09-12 | COMP | 2023-10-30 | COMP | Rule 16 | 65 | 16 | 6 | 2 | 0 | 34 | 120
42375 | 2023-05-10 | 2023-08-15 | 2023-08-24 | 2023-08-24 | COMP | 2023-08-31 | COMP | 2023-08-31 | COMP | 2023-09-07 | COMP | 2023-10-11 | COMP | Rule 16 | 67 | 8 | 6 | 1 | 5 | 25 | 107
41975 | 2023-05-11 | 2023-05-25 | 2023-07-05 | 2023-10-13 | COMP | 2023-10-20 | COMP | 2023-10-20 | COMP | 2023-12-12 | COMP | 2023-12-27 | COMP | Rule 16 | 11 | 27 | 6 | 1 | 35 | 11 | 157
42338 | 2023-05-11 | 2023-08-03 | 2023-09-10 | 2023-09-10 | COMP | 2023-09-26 | COMP | 2023-09-26 | COMP | 2023-11-28 | COMP | 2023-12-15 | COMP | Rule 16 | 58 | 26 | 12 | 1 | 43 | 14 | 150
42036 | 2023-05-12 | 2023-06-02 | 2023-06-13 | 2023-06-13 | COMP | 2023-07-13 | COMP | 2023-07-13 | COMP | 2023-11-01 | COMP | 2023-11-07 | COMP | Rule 16 | 15 | 8 | 21 | 1 | 79 | 5 | 124
42134 | 2023-05-12 | 2023-06-15 | 2023-07-23 | 2023-07-23 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-08-09 | COMP | 2023-09-13 | COMP | Rule 16 | 24 | 25 | 10 | 1 | 4 | 25 | 85
42192 | 2023-05-12 | 2023-06-29 | 2023-08-22 | 2023-08-22 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-10-23 | COMP | 2023-11-02 | COMP | Rule 15/16 | 33 | 38 | 20 | 1 | 25 | 9 | 121
42381 | 2023-05-12 | 2023-08-15 | 2023-08-24 | 2023-08-24 | COMP | 2023-10-18 | COMP | 2023-10-18 | COMP | 2023-10-24 | COMP | 2023-12-13 | COMP | Rule 16 | 65 | 8 | 39 | 1 | 5 | 34 | 147
41897 | 2023-05-13 | 2023-05-15 | 2023-07-25 | 2023-07-25 | COMP | 2023-07-25 | NOTN | 2023-09-28 | COMP | 2023-07-31 | COMP | 2023-11-09 | COMP | Other | 1 | 49 |  | 47 | 0 | 31 | 125
41899 | 2023-05-13 | 2023-05-15 | 2023-07-19 | 2023-07-19 | COMP | 2023-07-19 | NOTN | 2023-09-05 | COMP | 2023-07-20 | COMP | 2023-12-14 | COMP | Other | 1 | 45 |  | 34 | 0 | 70 | 147
41900 | 2023-05-13 | 2023-05-15 | 2023-08-01 | 2023-08-01 | COMP | 2023-08-03 | NOTN | 2023-09-18 | COMP | 2023-08-03 | COMP | 2023-12-13 | COMP | Other | 1 | 54 |  | 34 | 0 | 60 | 146
41901 | 2023-05-13 | 2023-05-15 | 2023-08-01 | 2023-08-01 | COMP | 2023-08-03 | NOTN | 2023-08-09 | COMP | 2023-08-03 | COMP | 2023-09-19 | COMP | Other | 1 | 54 |  | 7 | 0 | 29 | 88
42023 | 2023-05-15 | 2023-06-01 | 2023-07-26 | 2023-07-26 | COMP | 2023-07-26 | NOTN | 2023-08-16 | COMP | 2023-07-26 | COMP | 2023-09-19 | COMP | Other | 13 | 38 |  | 16 | 0 | 24 | 88
42044 | 2023-05-15 | 2023-06-02 | 2023-06-16 | 2023-06-16 | COMP | 2023-10-18 | COMP | 2023-10-18 | COMP | 2023-10-20 | COMP | 2023-12-06 | COMP | Rule 16 | 14 | 11 | 86 | 1 | 3 | 31 | 141
42065 | 2023-05-15 | 2023-06-05 | 2023-06-29 | 2023-06-29 | COMP | 2023-07-10 | COMP | 2023-09-06 | COMP |  | INPR | 2023-11-01 | COMP | Rule 16 | 15 | 18 | 7 | 42 |  |  | 119
42069 | 2023-05-15 | 2023-06-06 | 2023-07-03 | 2023-07-03 | COMP | 2023-07-31 | COMP | 2023-07-31 | COMP | 2023-08-15 | COMP | 2023-10-10 | COMP | Rule 16 | 16 | 19 | 20 | 1 | 12 | 40 | 103
42206 | 2023-05-15 | 2023-07-01 | 2023-07-30 | 2023-07-30 | COMP | 2023-08-07 | COMP | 2023-10-26 | COMP | 2023-11-01 | COMP | 2023-11-13 | COMP | Rule 16 | 33 | 19 | 6 | 58 | 5 | 8 | 126
42276 | 2023-05-15 | 2023-07-18 | 2023-08-21 | 2023-08-21 | COMP | 2023-09-14 | COMP | 2023-09-14 | COMP | 2023-09-21 | COMP | 2023-10-17 | COMP | Rule 15/16 | 44 | 25 | 18 | 1 | 6 | 19 | 108
42317 | 2023-05-15 | 2023-07-27 | 2023-08-19 | 2023-08-19 | COMP | 2023-08-29 | NOTN | 2023-09-06 | COMP | 2023-08-30 | COMP | 2023-10-16 | COMP | Rule 16 | 51 | 17 |  | 12 | 0 | 29 | 107
42379 | 2023-05-15 | 2023-08-15 | 2023-09-07 | 2023-09-07 | COMP | 2023-09-14 | COMP | 2023-10-20 | COMP | 2023-10-31 | COMP | 2023-11-28 | COMP | Rule 16 | 64 | 17 | 6 | 27 | 8 | 18 | 135
42385 | 2023-05-15 | 2023-08-17 | 2023-09-01 | 2023-09-01 | COMP | 2023-12-20 | COMP | 2023-12-20 | COMP | 2023-12-21 | COMP | 2023-12-28 | COMP | Rule 15/16 | 66 | 12 | 75 | 1 | 2 | 5 | 156
42452 | 2023-05-15 | 2023-09-21 | 2023-10-16 | 2023-10-16 | COMP | 2023-10-26 | COMP | 2023-10-26 | COMP | 2023-10-26 | COMP | 2023-12-04 | COMP | Rule 16 | 90 | 18 | 9 | 1 | 1 | 25 | 139
42147 | 2023-05-16 | 2023-06-20 | 2023-07-25 | 2023-07-25 | COMP | 2023-08-04 | COMP | 2023-11-16 | COMP | 2023-11-07 | COMP | 2023-12-22 | COMP | Rule 16 | 24 | 25 | 9 | 73 | 0 | 25 | 152
41928 | 2023-05-17 | 2023-05-18 | 2023-07-20 | 2023-07-20 | COMP | 2023-07-20 | NOTN | 2023-07-28 | COMP | 2023-08-11 | NOTN | 2023-10-18 | COMP | Other | 2 | 43 |  | 7 |  |  | 107
42224 | 2023-05-17 | 2023-07-06 | 2023-08-28 | 2023-09-08 | COMP | 2023-09-21 | COMP | 2023-09-21 | COMP | 2023-10-03 | COMP | 2023-11-15 | COMP | Rule 15/16 | 34 | 38 | 10 | 1 | 9 | 31 | 126
42384 | 2023-05-17 | 2023-08-18 | 2023-08-29 | 2023-08-29 | COMP | 2023-09-22 | COMP | 2023-09-22 | COMP | 2023-11-22 | COMP | 2023-12-29 | COMP | Rule 16 | 65 | 8 | 18 | 1 | 43 | 25 | 155
42458 | 2023-05-17 | 2023-09-25 | 2023-10-25 | 2023-10-25 | COMP | 2023-11-02 | COMP | 2023-11-02 | COMP | 2023-11-02 | COMP | 2023-11-30 | COMP | Rule 16 | 90 | 23 | 7 | 1 | 1 | 18 | 135
42145 | 2023-05-18 | 2023-06-19 | 2023-08-28 | 2023-08-28 | COMP | 2023-11-17 | COMP | 2023-11-17 | COMP | 2023-11-17 | COMP | 2023-12-06 | COMP | Rule 16 | 21 | 49 | 58 | 1 | 1 | 12 | 138
42314 | 2023-05-18 | 2023-07-27 | 2023-09-27 | 2023-09-27 | COMP | 2023-10-24 | COMP | 2023-10-24 | COMP | 2023-11-14 | COMP | 2023-12-08 | COMP | Rule 16 | 48 | 44 | 20 | 1 | 15 | 17 | 140
42387 | 2023-05-18 | 2023-08-17 | 2023-09-20 | 2023-09-20 | COMP | 2023-09-21 | NOTN | 2023-09-21 | COMP | 2023-09-21 | COMP | 2023-11-15 | COMP | Other | 63 | 24 |  | 2 | 1 | 39 | 125
42428 | 2023-05-18 | 2023-09-06 | 2023-09-24 | 2023-09-24 | COMP | 2023-10-06 | NOTN | 2023-11-17 | COMP | 2023-12-12 | COMP | 2023-12-27 | COMP | Other | 76 | 13 |  | 39 | 16 | 11 | 152
41992 | 2023-05-19 | 2023-05-26 | 2023-07-18 | 2023-07-18 | COMP | 2023-08-28 | COMP | 2023-10-17 | COMP | 2023-09-21 | COMP | 2023-11-06 | COMP | Other | 6 | 35 | 30 | 36 | 0 | 15 | 118
42111 | 2023-05-19 | 2023-06-12 | 2023-07-17 | 2023-07-17 | COMP | 2023-07-27 | COMP | 2023-09-21 | COMP | 2023-10-09 | COMP | 2023-10-24 | COMP | Rule 16 | 16 | 24 | 9 | 40 | 13 | 12 | 109
42167 | 2023-05-19 | 2023-06-22 | 2023-09-18 | 2023-09-18 | COMP | 2023-09-28 | COMP | 2023-09-28 | COMP | 2023-11-13 | COMP | 2023-12-11 | COMP | Rule 16 | 23 | 61 | 9 | 1 | 32 | 19 | 140
42186 | 2023-05-19 | 2023-06-28 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-24 | COMP | 2023-08-24 | COMP | 2023-09-14 | COMP | 2023-12-26 | COMP | Rule 16 | 27 | 31 | 11 | 1 | 15 | 70 | 150
42291 | 2023-05-19 | 2023-07-24 | 2023-08-24 | 2023-10-20 | COMP | 2023-10-31 | COMP | 2023-10-31 | COMP | 2023-11-15 | COMP | 2023-12-12 | COMP | Rule 16 | 44 | 24 | 8 | 1 | 11 | 18 | 141
42377 | 2023-05-20 | 2023-08-15 | 2023-09-04 | 2023-09-04 | COMP | 2023-09-05 | NOTN | 2023-09-05 | COMP | 2023-10-30 | COMP | 2023-10-30 | COMP | Other | 59 | 14 |  | 1 | 40 | 1 | 112
42158 | 2023-05-22 | 2023-06-21 | 2023-07-07 | 2023-07-19 | COMP | 2023-09-05 | COMP | 2023-09-05 | COMP | 2023-10-24 | COMP | 2023-11-30 | COMP | Rule 15/16 | 21 | 12 | 34 | 1 | 36 | 25 | 132
42214 | 2023-05-22 | 2023-07-05 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-10 | COMP | 2023-08-10 | COMP | 2023-08-15 | COMP | 2023-09-18 | COMP | Rule 16 | 30 | 23 | 5 | 1 | 4 | 24 | 82
42233 | 2023-05-22 | 2023-07-10 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-25 | COMP | 2023-09-18 | COMP | 2023-08-26 | COMP | 2023-11-08 | COMP | Rule 16 | 33 | 18 | 18 | 16 | 0 | 38 | 119
42246 | 2023-05-22 | 2023-07-11 | 2023-09-04 | 2023-09-04 | COMP | 2023-09-13 | COMP | 2023-10-16 | COMP | 2023-09-15 | COMP | 2023-11-29 | COMP | Rule 15/16 | 34 | 39 | 7 | 24 | 0 | 30 | 131
42262 | 2023-05-22 | 2023-07-13 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-11 | COMP | 2023-08-21 | COMP | 2023-09-11 | COMP | 2023-10-13 | COMP | Rule 16 | 36 | 16 | 7 | 7 | 15 | 25 | 101
42272 | 2023-05-22 | 2023-07-18 | 2023-08-31 | 2023-08-31 | COMP | 2023-09-21 | COMP | 2023-09-21 | COMP | 2023-09-22 | COMP | 2023-10-12 | COMP | Rule 16 | 39 | 33 | 15 | 1 | 2 | 15 | 100
42301 | 2023-05-22 | 2023-07-25 | 2023-09-28 | 2023-09-28 | COMP | 2023-10-12 | COMP | 2023-10-12 | COMP | 2023-11-07 | COMP | 2023-12-11 | COMP | Rule 16 | 44 | 47 | 11 | 1 | 19 | 22 | 139
42329 | 2023-05-22 | 2023-08-01 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-21 | COMP | 2023-08-21 | INPR | 2023-08-21 | COMP | 2023-09-08 | COMP | Unknown | 49 | 4 | 12 |  |  |  | 76
42344 | 2023-05-22 | 2023-08-04 | 2023-08-31 | 2023-08-31 | COMP | 2023-09-14 | COMP | 2023-09-14 | COMP | 2023-10-17 | COMP | 2023-10-27 | COMP | Rule 16 | 52 | 20 | 10 | 1 | 24 | 9 | 111
42464 | 2023-05-22 | 2023-10-03 | 2023-10-23 | 2023-10-23 | COMP | 2023-10-25 | COMP | 2023-10-25 | COMP | 2023-12-13 | COMP | 2023-12-23 | COMP | Rule 16 | 93 | 15 | 3 | 1 | 33 | 8 | 148
42232 | 2023-05-23 | 2023-07-08 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-04 | COMP | 2023-08-04 | COMP | 2023-09-28 | COMP | 2023-10-30 | COMP | Rule 16 | 31 | 18 | 3 | 1 | 39 | 23 | 111
42271 | 2023-05-23 | 2023-07-17 | 2023-09-08 | 2023-09-08 | COMP | 2023-09-08 | NOTN | 2023-09-08 | COMP | 2023-09-08 | COMP | 2023-11-02 | COMP | Other | 37 | 39 |  | 1 | 1 | 40 | 114
42281 | 2023-05-23 | 2023-07-19 | 2023-09-27 | 2023-09-27 | COMP | 2023-09-28 | NOTN | 2023-09-28 | COMP | 2023-09-28 | COMP | 2023-10-27 | COMP | Other | 39 | 50 |  | 2 | 1 | 22 | 110
42318 | 2023-05-23 | 2023-07-29 | 2023-09-01 | 2023-09-01 | COMP | 2023-09-12 | COMP | 2023-09-12 | COMP | 2023-10-03 | COMP | 2023-11-06 | COMP | Rule 16 | 46 | 25 | 7 | 1 | 16 | 25 | 116
42113 | 2023-05-24 | 2023-06-12 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-31 | COMP | 2023-09-18 | COMP | 2023-10-03 | COMP | 2023-10-23 | COMP | Rule 16 | 13 | 38 | 20 | 12 | 12 | 15 | 105
42138 | 2023-05-24 | 2023-06-16 | 2023-07-12 | 2023-07-12 | COMP | 2023-08-01 | COMP | 2023-08-01 | COMP | 2023-08-17 | COMP | 2023-09-25 | COMP | Rule 16 | 17 | 17 | 15 | 1 | 13 | 27 | 85
42258 | 2023-05-24 | 2023-07-12 | 2023-08-05 | 2023-08-05 | COMP | 2023-08-28 | COMP | 2023-09-05 | COMP | 2023-11-09 | COMP | 2023-11-17 | COMP | Rule 16 | 33 | 18 | 16 | 6 | 48 | 6 | 123
42324 | 2023-05-24 | 2023-07-31 | 2023-09-04 | 2023-09-04 | COMP | 2023-09-07 | COMP | 2023-10-19 | COMP | 2024-03-18 | COMP | 2023-12-13 | COMP | Rule 16 | 46 | 25 | 3 | 31 | 101 |  | 139
42358 | 2023-05-24 | 2023-08-10 | 2023-09-08 | 2023-09-08 | COMP | 2023-09-08 | NOTN | 2023-10-20 | COMP | 2023-09-21 | COMP | 2023-12-06 | COMP | Other | 54 | 21 |  | 31 | 0 | 31 | 134
42035 | 2023-05-25 | 2023-06-02 | 2023-06-26 | 2023-06-26 | COMP | 2023-06-29 | COMP | 2023-12-07 | COMP | 2023-12-04 | COMP | 2023-12-12 | COMP | Rule 16 | 6 | 16 | 4 | 111 | 0 | 4 | 137
42217 | 2023-05-25 | 2023-07-07 | 2023-07-11 | 2023-07-11 | COMP | 2023-08-29 | COMP | 2023-08-29 | COMP | 2023-08-18 | COMP | 2023-09-06 | COMP | Rule 16 | 29 | 3 | 36 | 1 | 0 | 6 | 71
42306 | 2023-05-25 | 2023-07-26 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-23 | COMP | 2023-09-20 | COMP | 2023-10-30 | COMP | 2023-11-01 | COMP | Rule 16 | 42 | 12 | 10 | 20 | 29 | 3 | 111
42409 | 2023-05-25 | 2023-08-24 | 2023-10-11 | 2023-10-11 | COMP | 2023-10-18 | COMP | 2023-10-24 | COMP | 2023-11-16 | COMP | 2023-11-29 | COMP | Rule 16 | 63 | 34 | 6 | 5 | 17 | 8 | 128
42351 | 2023-05-26 | 2023-08-09 | 2023-09-18 | 2023-09-18 | COMP | 2023-09-20 | NOTN | 2023-09-20 | COMP | 2023-10-02 | COMP | 2023-12-15 | COMP | Other | 51 | 28 |  | 3 | 9 | 52 | 139
42420 | 2023-05-29 | 2023-08-30 | 2023-09-14 | 2023-09-14 | COMP | 2023-10-30 | COMP | 2023-10-30 | COMP |  | INPR | 2023-11-08 | COMP | Rule 16 | 65 | 11 | 33 | 1 |  |  | 114
42099 | 2023-05-30 | 2023-06-09 | 2023-07-17 | 2023-07-17 | COMP | 2023-09-07 | COMP | 2023-09-25 | COMP | 2023-10-23 | COMP | 2023-11-28 | COMP | Rule 16 | 9 | 25 | 38 | 13 | 21 | 24 | 125
42153 | 2023-05-30 | 2023-06-20 | 2023-07-14 | 2023-07-14 | COMP | 2023-07-19 | COMP | 2023-10-06 | COMP | 2023-11-10 | COMP | 2023-12-13 | COMP | Rule 16 | 15 | 18 | 4 | 57 | 25 | 21 | 136
42215 | 2023-05-30 | 2023-07-05 | 2023-08-08 | 2023-08-08 | COMP | 2023-10-02 | COMP | 2023-10-02 | COMP | 2023-10-04 | COMP | 2023-10-16 | COMP | Rule 16 | 25 | 25 | 39 | 1 | 3 | 9 | 97
42279 | 2023-05-30 | 2023-07-19 | 2023-08-25 | 2023-08-25 | COMP | 2023-09-05 | COMP | 2023-10-10 | COMP | 2023-10-17 | COMP | 2023-11-17 | COMP | Rule 16 | 35 | 28 | 7 | 26 | 6 | 23 | 120
42280 | 2023-05-30 | 2023-07-19 | 2023-08-16 | 2023-08-16 | COMP | 2023-08-29 | COMP | 2023-11-01 | COMP | 2023-11-02 | COMP | 2023-12-07 | COMP | Other | 35 | 21 | 10 | 46 | 2 | 23 | 132
42296 | 2023-05-30 | 2023-07-24 | 2023-08-07 | 2023-08-07 | COMP | 2023-08-10 | COMP | 2023-08-10 | COMP | 2023-09-12 | COMP | 2023-11-02 | COMP | Rule 16 | 38 | 11 | 4 | 1 | 23 | 38 | 110
42307 | 2023-05-30 | 2023-07-26 | 2023-08-03 | 2023-08-03 | COMP | 2023-10-30 | COMP | 2023-10-30 | COMP | 2023-10-30 | COMP | 2023-11-04 | COMP | Rule 16 | 40 | 7 | 62 | 1 | 1 | 5 | 111
42012 | 2023-05-31 | 2023-05-31 | 2023-07-29 | 2023-07-29 | COMP | 2023-07-31 | NOTN | 2023-08-04 | COMP | 2023-07-31 | COMP | 2023-10-06 | COMP | Other | 1 | 41 |  | 5 | 0 | 45 | 90
42320 | 2023-05-31 | 2023-07-31 | 2023-08-31 | 2023-08-31 | COMP | 2023-09-26 | COMP | 2023-10-13 | COMP |  | INPR | 2023-12-04 | COMP | Rule 16 | 42 | 24 | 18 | 14 |  |  | 128
42327 | 2023-05-31 | 2023-08-01 | 2023-08-15 | 2023-08-29 | COMP | 2023-09-11 | COMP | 2023-10-12 | COMP | 2023-10-09 | COMP | 2023-10-10 | COMP | Rule 16 | 43 | 11 | 9 | 24 | 0 |  | 92
42330 | 2023-05-31 | 2023-08-01 | 2023-08-21 | 2023-08-21 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | 2023-11-14 | COMP | 2023-12-11 | COMP | Rule 15/16 | 43 | 15 | 6 | 1 | 55 | 18 | 133
42345 | 2023-05-31 | 2023-08-05 | 2023-09-21 | 2023-09-26 | COMP | 2023-10-02 | COMP | 2023-10-02 | COMP | 2023-10-20 | COMP | 2023-12-12 | COMP | Rule 16 | 46 | 33 | 5 | 1 | 15 | 35 | 134
42398 | 2023-05-31 | 2023-08-22 | 2023-09-08 | 2023-09-08 | COMP | 2023-09-23 | NOTN | 2023-09-23 | COMP | 2023-11-02 | COMP | 2023-12-11 | COMP | Other | 58 | 13 |  | 11 | 29 | 25 | 133
42030 | 2023-06-01 | 2023-06-01 | 2023-08-11 | 2023-08-11 | COMP | 2023-08-14 | NOTN | 2023-09-29 | COMP |  | INPR | 2023-12-12 | COMP | Other | 1 | 50 |  | 35 |  |  | 133
42131 | 2023-06-01 | 2023-06-14 | 2023-06-23 | 2023-06-23 | COMP | 2023-07-06 | COMP | 2023-07-07 | COMP | 2023-07-06 | COMP | 2023-07-17 | COMP | Rule 16 | 10 | 7 | 9 | 2 | 0 | 7 | 31
42270 | 2023-06-01 | 2023-07-17 | 2023-10-17 | 2023-10-17 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-11-30 | COMP | Rule 15/16 | 31 | 66 | 5 | 1 | 1 | 26 | 125
42282 | 2023-06-01 | 2023-07-20 | 2023-07-31 | 2023-08-03 | COMP | 2023-09-05 | COMP | 2023-09-18 | COMP | 2023-10-05 | COMP | 2023-10-27 | COMP | Rule 16 | 34 | 8 | 23 | 10 | 14 | 17 | 104
42388 | 2023-06-01 | 2023-08-17 | 2023-08-21 | 2023-08-21 | COMP | 2023-08-23 | COMP | 2023-08-24 | COMP | 2023-09-07 | COMP | 2023-09-20 | COMP | Rule 16 | 54 | 3 | 3 | 2 | 10 | 10 | 77
42052 | 2023-06-02 | 2023-06-05 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-03 | NOTN | 2023-09-20 | COMP | 2023-12-26 | COMP | 2023-11-13 | COMP | Other | 2 | 41 |  | 35 | 66 |  | 113
42212 | 2023-06-02 | 2023-07-03 | 2023-07-22 | 2023-07-22 | COMP | 2023-10-30 | COMP | 2023-10-30 | COMP | 2023-10-30 | COMP | 2023-11-14 | COMP | Rule 16 | 21 | 14 | 70 | 1 | 1 | 11 | 114
42411 | 2023-06-02 | 2023-08-26 | 2023-10-22 | 2023-10-22 | COMP | 2023-11-30 | COMP | 2023-11-30 | COMP |  | INPR | 2023-11-29 | COMP | Rule 16 | 59 | 39 | 26 | 1 |  |  | 123
42171 | 2023-06-05 | 2023-06-23 | 2023-07-24 | 2023-07-24 | COMP | 2023-08-15 | COMP | 2023-10-17 | COMP | 2023-09-22 | COMP | 2023-11-04 | COMP | Rule 16 | 14 | 21 | 17 | 45 | 0 | 14 | 107
42392 | 2023-06-05 | 2023-08-20 | 2023-09-13 | 2023-09-13 | COMP | 2023-09-28 | COMP | 2023-09-28 | COMP | 2023-09-25 | COMP | 2023-10-26 | COMP | Rule 16 | 53 | 17 | 12 | 1 | 0 | 21 | 101
42085 | 2023-06-06 | 2023-06-07 | 2023-07-18 | 2023-07-18 | COMP | 2023-07-24 | NOTN | 2023-07-24 | COMP | 2023-08-07 | COMP | 2023-11-17 | COMP | Other | 2 | 28 |  | 5 | 11 | 73 | 115
42181 | 2023-06-06 | 2023-06-27 | 2023-07-19 | 2023-07-19 | COMP | 2023-07-24 | COMP | 2023-09-18 | COMP | 2023-09-08 | COMP | 2023-10-20 | COMP | Rule 16 | 15 | 16 | 4 | 40 | 0 | 25 | 96
42292 | 2023-06-06 | 2023-07-24 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP | 2023-10-12 | COMP | 2023-10-18 | COMP | Rule 16 | 33 | 6 | 6 | 1 | 48 | 5 | 94
42334 | 2023-06-06 | 2023-08-02 | 2023-08-10 | 2023-08-10 | COMP | 2023-08-24 | COMP | 2023-08-24 | COMP | 2023-08-18 | COMP | 2023-10-04 | COMP | Rule 16 | 40 | 7 | 11 | 1 | 0 | 29 | 84
42247 | 2023-06-07 | 2023-07-11 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-25 | COMP | 2023-08-25 | COMP | 2023-09-29 | COMP | 2023-10-04 | COMP | Rule 16 | 23 | 18 | 17 | 1 | 25 | 4 | 83
42253 | 2023-06-07 | 2023-07-12 | 2023-10-21 | 2023-10-21 | COMP | 2023-10-25 | COMP | 2023-10-25 | COMP | 2023-12-06 | COMP | 2023-12-26 | COMP | Rule 16 | 24 | 72 | 3 | 1 | 28 | 14 | 138
42259 | 2023-06-07 | 2023-07-12 | 2023-08-08 | 2023-08-08 | COMP | 2023-08-16 | COMP | 2023-10-20 | COMP | 2023-10-17 | COMP | 2023-11-30 | COMP | Rule 16 | 24 | 20 | 7 | 47 | 0 | 27 | 121
42470 | 2023-06-07 | 2023-10-10 | 2023-10-20 | 2023-10-20 | COMP | 2023-11-14 | COMP | 2023-11-14 | COMP |  | INPR | 2023-12-14 | COMP | Rule 16 | 87 | 9 | 17 | 1 |  |  | 131
42148 | 2023-06-08 | 2023-06-20 | 2023-08-14 | 2023-08-14 | COMP | 2023-08-23 | NOTN | 2023-08-23 | COMP | 2023-08-23 | COMP | 2023-10-13 | COMP | Other | 8 | 39 |  | 8 | 1 | 37 | 89
42152 | 2023-06-08 | 2023-06-21 | 2023-07-22 | 2023-07-22 | COMP | 2023-08-14 | COMP | 2023-09-25 | COMP | 2023-11-06 | COMP | 2023-12-06 | COMP | Rule 16 | 9 | 22 | 16 | 30 | 31 | 20 | 124
42339 | 2023-06-08 | 2023-08-03 | 2023-08-15 | 2023-10-22 | COMP | 2023-12-04 | COMP | 2023-12-04 | COMP | 2023-12-06 | COMP | 2023-12-13 | COMP | Rule 16 | 39 | 9 | 28 | 1 | 3 | 6 | 129
42275 | 2023-06-09 | 2023-07-18 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-22 | COMP | 2023-08-22 | COMP | 2023-10-09 | COMP | 2023-10-18 | COMP | Rule 16 | 26 | 10 | 17 | 1 | 34 | 8 | 91
42393 | 2023-06-09 | 2023-08-21 | 2023-09-14 | 2023-09-14 | COMP | 2023-09-21 | COMP | 2023-09-21 | COMP | 2023-10-23 | COMP | 2023-12-05 | COMP | Rule 16 | 50 | 18 | 6 | 1 | 23 | 29 | 122
42438 | 2023-06-11 | 2023-09-11 | 2023-10-08 | 2023-10-08 | COMP | 2023-10-13 | COMP | 2023-10-13 | COMP | 2023-10-25 | COMP | 2023-11-30 | COMP | Rule 16 | 63 | 20 | 5 | 1 | 9 | 24 | 118
42222 | 2023-06-12 | 2023-07-06 | 2023-08-03 | 2023-08-03 | COMP | 2023-08-24 | COMP | 2023-09-20 | COMP | 2023-08-25 | COMP | 2023-11-17 | COMP | Rule 16 | 17 | 21 | 16 | 19 | 0 | 42 | 111
42241 | 2023-06-12 | 2023-07-11 | 2023-08-04 | 2023-09-20 | COMP | 2023-09-27 | COMP | 2023-09-29 | COMP | 2023-10-10 | COMP | 2023-11-14 | COMP | Rule 16 | 20 | 19 | 6 | 3 | 8 | 25 | 108
42367 | 2023-06-12 | 2023-08-11 | 2023-09-01 | 2023-09-01 | COMP | 2023-11-08 | COMP | 2023-11-08 | COMP | 2023-11-14 | COMP | 2023-12-27 | COMP | Rule 15/16 | 43 | 16 | 48 | 1 | 4 | 29 | 136
42424 | 2023-06-12 | 2023-08-31 | 2023-09-12 | 2023-09-12 | COMP | 2023-09-25 | COMP | 2023-09-25 | COMP | 2023-10-20 | COMP | 2023-12-05 | COMP | Rule 16 | 57 | 8 | 10 | 1 | 20 | 30 | 121
42223 | 2023-06-13 | 2023-07-05 | 2023-09-01 | 2023-09-01 | COMP | 2023-09-14 | COMP | 2023-09-16 | COMP | 2023-09-22 | COMP | 2023-11-01 | COMP | Rule 15/16 | 15 | 43 | 9 | 2 | 5 | 29 | 99
42408 | 2023-06-13 | 2023-08-24 | 2023-10-18 | 2023-10-18 | COMP | 2023-11-06 | COMP | 2023-11-06 | COMP | 2023-11-08 | COMP | 2023-12-14 | COMP | Rule 15/16 | 51 | 39 | 14 | 1 | 3 | 24 | 127
42193 | 2023-06-14 | 2023-06-29 | 2023-07-25 | 2023-07-25 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-10-26 | COMP | 2023-12-11 | COMP | Rule 16 | 11 | 18 | 64 | 1 | 4 | 30 | 123
42213 | 2023-06-14 | 2023-07-05 | 2023-08-22 | 2023-08-22 | COMP | 2023-10-24 | COMP | 2023-10-24 | COMP | 2023-09-20 | COMP | 2023-12-29 | COMP | Rule 16 | 14 | 35 | 45 | 1 | 0 | 45 | 136
42372 | 2023-06-14 | 2023-08-14 | 2023-08-29 | 2023-08-29 | COMP | 2023-09-06 | COMP | 2023-09-06 | COMP | 2023-10-25 | COMP | 2023-12-07 | COMP | Rule 16 | 42 | 12 | 6 | 1 | 36 | 29 | 121
42382 | 2023-06-14 | 2023-08-17 | 2023-09-05 | 2023-09-05 | COMP | 2023-09-20 | COMP | 2023-09-20 | COMP |  | INPR | 2023-10-04 | COMP | Rule 16 | 45 | 13 | 12 | 1 |  |  | 78
42137 | 2023-06-15 | 2023-06-15 | 2023-06-27 | 2023-06-27 | COMP | 2023-06-30 | COMP | 2023-08-18 | COMP | 2023-08-21 | COMP | 2023-09-13 | COMP | Rule 16 | 1 | 8 | 4 | 35 | 2 | 17 | 62
42140 | 2023-06-15 | 2023-06-20 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-03 | NOTN | 2023-09-15 | COMP | 2023-08-03 | COMP | 2023-10-26 | COMP | Other | 3 | 31 |  | 32 | 0 | 30 | 93
42149 | 2023-06-15 | 2023-06-20 | 2023-07-12 | 2023-09-01 | COMP | 2023-10-18 | COMP | 2023-12-08 | COMP | 2023-12-21 | COMP | 2023-12-15 | COMP | Rule 15/16 | 3 | 16 | 33 | 35 | 10 |  | 126
42176 | 2023-06-15 | 2023-06-26 | 2023-07-29 | 2023-07-29 | COMP | 2023-08-11 | COMP | 2023-08-11 | COMP | 2023-11-01 | COMP | 2023-12-11 | COMP | Rule 16 | 7 | 24 | 10 | 1 | 58 | 26 | 122
42383 | 2023-06-15 | 2023-08-17 | 2023-09-13 | 2023-09-13 | COMP | 2023-09-20 | COMP | 2023-10-03 | COMP | 2023-10-05 | COMP | 2023-11-02 | COMP | Rule 16 | 44 | 19 | 6 | 10 | 3 | 21 | 98
42295 | 2023-06-16 | 2023-07-24 | 2023-08-15 | 2023-08-15 | COMP | 2023-09-18 | COMP | 2023-09-18 | COMP | 2023-10-23 | COMP | 2023-11-30 | COMP | Rule 16 | 25 | 17 | 24 | 1 | 26 | 26 | 114
42308 | 2023-06-16 | 2023-07-26 | 2023-10-25 | 2023-10-25 | COMP | 2023-11-27 | COMP | 2023-12-14 | COMP | 2023-12-13 | COMP | 2023-12-27 | COMP | Rule 16 | 27 | 65 | 21 | 14 | 0 | 9 | 132
42461 | 2023-06-16 | 2023-10-02 | 2023-11-01 | 2023-11-01 | COMP | 2023-11-01 | NOTN | 2023-11-01 | COMP | 2023-11-01 | COMP | 2023-11-28 | COMP | Other | 74 | 23 |  | 1 | 1 | 17 | 112
42205 | 2023-06-19 | 2023-06-30 | 2023-09-26 | 2023-09-26 | COMP | 2023-10-17 | COMP | 2023-12-05 | COMP | 2023-11-10 | COMP | 2023-12-06 | COMP | Rule 16 | 9 | 61 | 16 | 33 | 0 | 2 | 117
42321 | 2023-06-19 | 2023-07-31 | 2023-08-02 | 2023-08-02 | COMP | 2023-08-16 | COMP | 2023-09-20 | COMP | 2023-10-02 | COMP | 2023-11-07 | COMP | Rule 16 | 29 | 3 | 11 | 25 | 9 | 27 | 99
42332 | 2023-06-19 | 2023-08-02 | 2023-08-22 | 2023-08-22 | COMP | 2023-09-20 | COMP | 2023-10-04 | COMP | 2023-09-20 | COMP | 2023-11-13 | COMP | Rule 16 | 31 | 15 | 21 | 11 | 0 | 28 | 102
42349 | 2023-06-19 | 2023-08-07 | 2023-10-24 | 2023-10-24 | COMP | 2023-10-30 | COMP | 2023-11-01 | COMP | 2023-11-28 | COMP | 2023-11-04 | COMP | Rule 16 | 34 | 56 | 5 | 3 | 17 |  | 97
42406 | 2023-06-19 | 2023-08-24 | 2023-09-07 | 2023-09-07 | COMP | 2023-09-13 | COMP | 2023-10-27 | COMP | 2023-10-11 | COMP | 2023-12-05 | COMP | Rule 16 | 47 | 10 | 5 | 33 | 0 | 25 | 116
42157 | 2023-06-20 | 2023-06-21 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-06 | NOTN | 2023-08-24 | COMP |  | INPR | 2023-12-01 | COMP | Other | 2 | 32 |  | 15 |  |  | 114
42297 | 2023-06-20 | 2023-07-24 | 2023-08-24 | 2023-08-24 | COMP | 2023-09-06 | COMP | 2023-10-02 | COMP | 2023-09-08 | COMP | 2023-11-17 | COMP | Rule 16 | 24 | 24 | 9 | 19 | 0 | 34 | 106
42311 | 2023-06-20 | 2023-07-27 | 2023-08-17 | 2023-08-17 | COMP | 2023-08-21 | COMP | 2023-10-03 | COMP |  | INPR | 2023-11-28 | COMP | Rule 16 | 27 | 16 | 3 | 31 |  |  | 111
42315 | 2023-06-20 | 2023-07-28 | 2023-08-04 | 2023-08-04 | COMP | 2023-08-15 | COMP | 2023-11-27 | COMP | 2023-11-27 | COMP | 2023-12-06 | COMP | Rule 16 | 28 | 6 | 8 | 71 | 1 | 8 | 117
42335 | 2023-06-20 | 2023-08-02 | 2023-08-22 | 2023-08-22 | COMP | 2023-09-15 | COMP | 2023-09-16 | COMP | 2023-09-25 | COMP | 2023-12-06 | COMP | Rule 16 | 31 | 15 | 18 | 1 | 6 | 50 | 117
42449 | 2023-06-20 | 2023-09-19 | 2023-10-18 | 2023-10-18 | COMP | 2023-10-31 | COMP | 2023-12-01 | COMP | 2023-12-12 | COMP | 2023-12-22 | COMP | Rule 16 | 64 | 22 | 10 | 21 | 8 | 9 | 129
42169 | 2023-06-21 | 2023-06-23 | 2023-08-02 | 2023-08-02 | COMP | 2023-09-05 | COMP | 2023-09-05 | COMP |  | INPR | 2023-11-17 | COMP | Rule 16 | 3 | 28 | 24 | 1 |  |  | 105
42230 | 2023-06-21 | 2023-07-08 | 2023-08-01 | 2023-08-01 | COMP | 2023-11-07 | COMP | 2023-11-07 | COMP | 2023-11-07 | COMP | 2023-11-27 | COMP | Rule 16 | 12 | 17 | 70 | 1 | 1 | 12 | 109
42416 | 2023-06-21 | 2023-08-28 | 2023-09-11 | 2023-09-11 | COMP | 2023-09-15 | COMP | 2023-10-18 | COMP | 2023-10-02 | COMP | 2023-10-30 | COMP | Rule 16 | 48 | 10 | 5 | 24 | 0 | 9 | 92
42417 | 2023-06-21 | 2023-08-29 | 2023-10-05 | 2023-10-05 | COMP | 2023-10-09 | COMP | 2023-10-17 | COMP | 2023-10-10 | COMP | 2023-10-26 | COMP | Rule 16 | 49 | 27 | 3 | 7 | 0 | 8 | 90
42373 | 2023-06-22 | 2023-08-14 | 2023-08-28 | 2023-08-28 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-10-26 | COMP | Rule 16 | 37 | 11 | 40 | 1 | 1 | 4 | 89
42172 | 2023-06-23 | 2023-06-23 | 2023-08-17 | 2023-08-17 | COMP | 2023-08-23 | COMP | 2023-09-08 | COMP | 2023-09-08 | COMP | 2023-09-10 | COMP | Rule 16 | 1 | 39 | 5 | 12 | 1 | 1 | 54
42263 | 2023-06-23 | 2023-07-13 | 2023-07-26 | 2023-08-04 | COMP | 2023-08-08 | COMP | 2023-08-08 | COMP | 2023-08-10 | COMP | 2023-11-09 | COMP | Rule 16 | 14 | 10 | 3 | 1 | 3 | 65 | 98
42173 | 2023-06-24 | 2023-06-26 | 2023-08-09 | 2023-08-09 | COMP | 2023-08-11 | NOTN | 2023-09-25 | COMP | 2023-08-11 | COMP | 2023-11-08 | COMP | Other | 1 | 32 |  | 33 | 0 | 33 | 96
42174 | 2023-06-25 | 2023-06-26 | 2023-07-15 | 2023-07-15 | COMP | 2023-08-11 | NOTN | 2023-09-21 | COMP | 2023-08-11 | NOTN | 2023-11-07 | COMP | Other | 1 | 14 |  | 48 |  |  | 95
42244 | 2023-06-27 | 2023-07-11 | 2023-09-13 | 2023-09-13 | COMP | 2023-09-25 | COMP | 2023-10-23 | COMP | 2023-11-07 | COMP | 2023-12-11 | COMP | Rule 16 | 10 | 46 | 9 | 21 | 12 | 22 | 115
42363 | 2023-06-27 | 2023-08-10 | 2023-09-15 | 2023-09-15 | COMP | 2023-09-19 | COMP | 2023-09-27 | COMP | 2023-09-21 | COMP | 2023-11-10 | COMP | Rule 16 | 32 | 26 | 3 | 7 | 0 | 32 | 96
42476 | 2023-06-27 | 2023-10-23 | 2023-10-30 | 2023-10-30 | COMP | 2023-11-02 | COMP | 2023-11-07 | COMP | 2023-11-08 | COMP | 2023-12-21 | COMP | Rule 16 | 83 | 6 | 4 | 4 | 2 | 29 | 123
42278 | 2023-06-28 | 2023-07-19 | 2023-08-22 | 2023-08-22 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | 2023-08-28 | COMP | 2023-08-29 | COMP | Rule 16 | 15 | 25 | 5 | 1 | 1 | 2 | 44
42399 | 2023-06-28 | 2023-08-22 | 2023-09-16 | 2023-09-16 | COMP | 2023-09-29 | COMP | 2023-09-29 | COMP | 2023-10-30 | COMP | 2023-11-06 | COMP | Rule 16 | 39 | 18 | 10 | 1 | 22 | 6 | 92
42403 | 2023-06-28 | 2023-08-22 | 2023-09-01 | 2023-09-01 | COMP | 2023-10-05 | COMP | 2023-10-16 | COMP | 2023-10-05 | COMP | 2023-10-21 | COMP | Rule 15/16 | 39 | 9 | 24 | 8 | 0 | 5 | 81
42343 | 2023-06-30 | 2023-08-04 | 2023-08-22 | 2023-08-22 | COMP | 2023-09-18 | COMP | 2023-09-18 | COMP | 2023-11-08 | COMP | 2023-12-09 | COMP | Rule 16 | 25 | 13 | 19 | 1 | 38 | 20 | 111
42444 | 2023-06-30 | 2023-09-15 | 2023-10-09 | 2023-10-09 | COMP | 2023-10-11 | COMP | 2023-10-11 | COMP | 2023-12-02 | COMP | 2023-12-15 | COMP | Rule 16 | 54 | 17 | 3 | 1 | 35 | 10 | 116
42425 | 2023-07-01 | 2023-09-01 | 2023-09-18 | 2023-09-18 | COMP | 2023-10-12 | COMP | 2023-10-12 | COMP |  | INPR | 2023-12-06 | COMP | Rule 16 | 44 | 11 | 19 | 1 |  |  | 108
42431 | 2023-07-03 | 2023-09-07 | 2023-11-03 | 2023-11-03 | COMP | 2023-11-22 | COMP | 2023-12-04 | COMP | 2023-12-07 | COMP | 2023-12-15 | COMP | Rule 16 | 47 | 42 | 13 | 7 | 4 | 7 | 115
42432 | 2023-07-05 | 2023-09-07 | 2023-10-11 | 2023-10-11 | COMP | 2023-10-18 | COMP | 2023-11-27 | COMP |  | INPR | 2023-12-22 | COMP | Rule 16 | 46 | 25 | 6 | 26 |  |  | 119
42354 | 2023-07-06 | 2023-08-09 | 2023-09-04 | 2023-09-04 | COMP | 2023-09-12 | COMP | 2023-10-16 | COMP | 2023-09-12 | COMP | 2023-11-28 | COMP | Rule 16 | 25 | 18 | 6 | 25 | 0 | 29 | 100
42421 | 2023-07-06 | 2023-08-31 | 2023-10-13 | 2023-10-13 | COMP | 2023-10-31 | COMP | 2023-11-15 | COMP | 2023-10-24 | COMP | 2023-12-02 | COMP | Rule 16 | 41 | 31 | 13 | 11 | 0 | 11 | 103
42426 | 2023-07-06 | 2023-09-05 | 2023-09-30 | 2023-09-30 | COMP | 2023-10-16 | COMP | 2023-10-16 | COMP | 2023-12-13 | COMP | 2023-12-20 | COMP | Rule 16 | 43 | 19 | 11 | 1 | 40 | 6 | 116
41814 | 2023-07-07 | 2023-05-03 | 2023-06-29 | 2023-07-10 | COMP | 2023-08-07 | COMP | 2023-10-23 | COMP | 2023-10-30 | COMP | 2023-11-30 | COMP | Rule 16 |  | 40 | 21 | 55 | 6 | 21 | 101
42413 | 2023-07-07 | 2023-08-28 | 2023-09-06 | 2023-09-06 | COMP | 2023-09-11 | COMP | 2023-10-09 | COMP | 2023-10-06 | COMP | 2023-11-28 | COMP | Rule 16 | 37 | 7 | 4 | 21 | 0 | 34 | 99
42414 | 2023-07-08 | 2023-08-28 | 2023-10-05 | 2023-10-05 | COMP | 2023-10-10 | COMP | 2023-10-25 | COMP | 2023-10-31 | COMP | 2023-12-01 | COMP | Rule 16 | 36 | 28 | 4 | 12 | 5 | 21 | 101
42287 | 2023-07-10 | 2023-07-20 | 2023-09-01 | 2023-09-01 | COMP | 2023-10-06 | COMP | 2023-10-06 | COMP | 2023-12-05 | COMP | 2023-12-17 | COMP | Rule 16 | 9 | 32 | 25 | 1 | 40 | 9 | 111
42447 | 2023-07-10 | 2023-09-19 | 2023-09-28 | 2023-09-28 | COMP | 2023-10-27 | COMP | 2023-12-04 | COMP | 2023-12-11 | COMP | 2023-12-10 | COMP | Rule 16 | 51 | 8 | 22 | 24 | 6 |  | 106
42434 | 2023-07-11 | 2023-09-08 | 2023-10-12 | 2023-10-12 | COMP | 2023-10-16 | COMP | 2023-10-16 | COMP |  | INPR | 2023-12-13 | COMP | Rule 16 | 43 | 25 | 3 | 1 |  |  | 108
42391 | 2023-07-12 | 2023-08-20 | 2023-09-14 | 2023-09-14 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-11-14 | COMP | 2023-11-29 | COMP | Rule 16 | 28 | 18 | 4 | 1 | 40 | 10 | 97
42405 | 2023-07-12 | 2023-08-24 | 2023-09-15 | 2023-09-15 | COMP | 2023-10-13 | COMP | 2023-10-13 | COMP | 2023-11-07 | COMP | 2023-12-08 | COMP | Rule 16 | 32 | 16 | 21 | 1 | 18 | 21 | 104
42433 | 2023-07-12 | 2023-09-08 | 2023-09-25 | 2023-09-25 | COMP | 2023-11-28 | COMP | 2023-11-28 | COMP | 2023-11-28 | COMP | 2023-12-27 | COMP | Rule 16 | 42 | 12 | 44 | 1 | 1 | 21 | 116
42360 | 2023-07-13 | 2023-08-10 | 2023-08-29 | 2023-08-29 | COMP | 2023-09-05 | COMP | 2023-09-05 | COMP | 2023-09-29 | COMP | 2023-11-06 | COMP | Rule 16 | 21 | 14 | 5 | 1 | 19 | 27 | 82
42361 | 2023-07-15 | 2023-08-10 | 2023-09-08 | 2023-09-08 | COMP | 2023-09-15 | COMP | 2023-09-15 | COMP | 2023-10-11 | COMP | 2023-11-08 | COMP | Rule 16 | 19 | 21 | 6 | 1 | 19 | 21 | 82
42418 | 2023-07-16 | 2023-08-30 | 2023-09-08 | 2023-09-08 | COMP | 2023-09-19 | COMP | 2023-09-19 | COMP | 2023-10-20 | COMP | 2023-10-26 | COMP | Rule 16 | 33 | 7 | 8 | 1 | 24 | 5 | 73
42466 | 2023-07-16 | 2023-10-03 | 2023-10-17 | 2023-10-17 | COMP | 2023-10-27 | COMP | 2023-10-27 | COMP | 2023-12-01 | COMP | 2023-12-14 | COMP | Rule 16 | 56 | 11 | 9 | 1 | 23 | 10 | 105
42347 | 2023-07-17 | 2023-08-06 | 2023-09-09 | 2023-09-09 | COMP | 2023-09-13 | COMP | 2023-09-13 | INPR | 2023-09-13 | COMP | 2023-09-26 | COMP | Rule 16 | 15 | 24 | 3 |  |  |  | 51
42412 | 2023-07-17 | 2023-08-28 | 2023-10-24 | 2023-10-24 | COMP | 2023-11-07 | COMP | 2023-11-07 | COMP | 2023-11-07 | COMP | 2023-12-11 | COMP | Rule 16 | 31 | 41 | 11 | 1 | 1 | 22 | 102
42436 | 2023-07-17 | 2023-09-08 | 2023-10-06 | 2023-10-06 | COMP | 2023-10-06 | NOTN | 2023-10-23 | COMP | 2023-11-06 | COMP | 2023-11-18 | COMP | Other | 39 | 21 |  | 12 | 11 | 9 | 88
42468 | 2023-07-17 | 2023-10-09 | 2023-10-17 | 2023-10-17 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-11-01 | COMP | Rule 16 | 60 | 7 | 5 | 1 | 1 | 8 | 77
42294 | 2023-07-18 | 2023-07-24 | 2023-08-15 | 2023-08-15 | COMP | 2023-08-21 | COMP | 2023-09-13 | COMP | 2023-09-26 | COMP | 2023-10-05 | COMP | Rule 16 | 5 | 17 | 5 | 17 | 10 | 8 | 57
42350 | 2023-07-18 | 2023-08-07 | 2023-09-21 | 2023-09-21 | COMP | 2023-10-13 | COMP | 2023-10-24 | COMP | 2023-10-25 | COMP | 2023-12-20 | COMP | Rule 15/16 | 15 | 33 | 17 | 8 | 2 | 38 | 108
42423 | 2023-07-18 | 2023-08-31 | 2023-10-05 | 2023-10-05 | COMP | 2023-10-27 | COMP | 2023-11-29 | COMP | 2023-11-21 | COMP | 2023-12-28 | COMP | Rule 16 | 33 | 25 | 17 | 21 | 0 | 21 | 113
42474 | 2023-07-18 | 2023-10-19 | 2023-12-12 | 2023-12-12 | COMP | 2023-12-15 | COMP | 2023-12-15 | COMP | 2023-12-15 | COMP | 2023-12-28 | COMP | Rule 16 | 67 | 36 | 4 | 1 | 1 | 9 | 113
42481 | 2023-07-18 | 2023-11-04 | 2023-12-03 | 2023-12-03 | COMP | 2023-12-08 | COMP | 2023-12-13 | COMP | 2023-12-08 | COMP | 2023-12-29 | COMP | Rule 16 | 78 | 17 | 5 | 4 | 0 | 12 | 114
42429 | 2023-07-19 | 2023-09-06 | 2023-09-15 | 2023-09-15 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP | 2023-11-15 | COMP | 2023-11-17 | COMP | Rule 16 | 35 | 8 | 27 | 1 | 17 | 3 | 86
42386 | 2023-07-24 | 2023-08-17 | 2023-09-01 | 2023-09-01 | COMP | 2023-09-08 | NOTN | 2023-09-08 | COMP | 2023-09-19 | COMP | 2023-10-05 | COMP | Other | 19 | 12 |  | 5 | 8 | 13 | 53
42365 | 2023-07-26 | 2023-08-11 | 2023-08-28 | 2023-08-28 | COMP | 2023-09-11 | COMP | 2023-09-11 | COMP | 2023-10-09 | COMP | 2023-10-18 | COMP | Rule 16 | 13 | 12 | 10 | 1 | 21 | 8 | 60
42443 | 2023-07-26 | 2023-09-15 | 2023-10-18 | 2023-10-18 | COMP | 2023-10-23 | COMP | 2023-10-23 | COMP |  | INPR | 2023-11-02 | COMP | Rule 16 | 37 | 24 | 4 | 1 |  |  | 71
42478 | 2023-07-27 | 2023-10-30 | 2023-11-09 | 2023-11-09 | COMP | 2023-11-13 | COMP | 2023-11-13 | COMP | 2023-11-27 | COMP | 2023-12-13 | COMP | Rule 16 | 67 | 9 | 2 | 1 | 9 | 13 | 96
42407 | 2023-07-29 | 2023-08-24 | 2023-09-20 | 2023-09-20 | COMP | 2023-09-20 | NOTN | 2023-09-28 | COMP | 2023-09-22 | COMP | 2023-11-14 | COMP | Other | 19 | 19 |  | 7 | 0 | 33 | 75
42359 | 2023-07-31 | 2023-08-10 | 2023-09-11 | 2023-09-11 | COMP | 2023-09-19 | COMP | 2023-10-27 | COMP | 2023-10-11 | COMP | 2023-12-06 | COMP | Rule 15/16 | 9 | 22 | 7 | 29 | 0 | 26 | 89
42378 | 2023-08-01 | 2023-08-15 | 2023-09-11 | 2023-09-11 | COMP | 2023-10-16 | COMP | 2023-11-08 | COMP |  | INPR | 2023-12-21 | COMP | Rule 16 | 11 | 19 | 26 | 18 |  |  | 99
42415 | 2023-08-01 | 2023-08-28 | 2023-10-23 | 2023-10-23 | COMP | 2023-10-30 | COMP | 2023-11-27 | COMP | 2023-12-08 | COMP | 2023-03-12 | COMP | Rule 16 | 20 | 40 | 6 | 18 | 10
42450 | 2023-08-04 | 2023-09-20 | 2023-09-27 | 2023-09-27 | COMP | 2023-09-29 | COMP | 2023-09-29 | COMP | 2023-09-27 | COMP | 2023-10-26 | COMP | Rule 16 | 33 | 6 | 3 | 1 | 0 | 20 | 59
42390 | 2023-08-08 | 2023-08-19 | 2023-09-07 | 2023-09-07 | COMP | 2023-09-15 | NOTN | 2023-09-15 | COMP | 2023-09-15 | COMP | 2023-10-30 | COMP | Other | 9 | 13 |  | 7 | 1 | 32 | 59
42404 | 2023-08-08 | 2023-08-22 | 2023-09-08 | 2023-09-08 | COMP | 2023-09-13 | COMP | 2023-10-28 | COMP | 2023-08-22 | COMP | 2023-12-13 | COMP | Rule 16 | 11 | 13 | 4 | 33 | 0 | 30 | 88
42446 | 2023-08-08 | 2023-09-19 | 2023-10-04 | 2023-10-04 | COMP | 2023-11-20 | COMP | 2023-11-20 | COMP | 2023-11-20 | COMP | 2023-12-05 | COMP | Rule 16 | 30 | 12 | 33 | 1 | 1 | 10 | 82
42355 | 2023-08-09 | 2023-08-10 | 2023-09-01 | 2023-09-01 | COMP | 2023-09-05 | NOTN | 2023-11-15 | COMP | 2023-09-05 | COMP | 2023-12-11 | COMP | Other | 2 | 17 |  | 52 | 0 | 17 | 85
42356 | 2023-08-09 | 2023-08-10 | 2023-08-22 | 2023-11-01 | COMP | 2023-11-09 | COMP | 2023-12-06 | COMP | 2023-09-14 | COMP | 2023-12-16 | COMP | Rule 16 | 2 | 9 | 7 | 17 | 0 | 8 | 89
42357 | 2023-08-10 | 2023-08-10 | 2023-08-29 | 2023-08-29 | COMP | 2023-10-24 | NOTN | 2023-10-24 | COMP | 2023-10-24 | COMP | 2023-12-31 | COMP | Other | 1 | 14 |  | 40 | 1 | 45 | 97
42477 | 2023-08-10 | 2023-10-24 | 2023-11-02 | 2023-11-02 | COMP | 2023-11-09 | COMP | 2023-12-04 | COMP | 2023-11-08 | COMP | 2023-12-14 | COMP | Unknown | 53 | 8 | 6 | 15 | 0 | 9 | 87
42440 | 2023-08-11 | 2023-09-13 | 2023-10-06 | 2023-10-06 | COMP | 2023-10-19 | COMP | 2023-10-19 | COMP | 2023-12-12 | COMP | 2023-12-26 | COMP | Rule 16 | 23 | 18 | 10 | 1 | 36 | 10 | 93
42402 | 2023-08-14 | 2023-08-22 | 2023-10-04 | 2023-10-04 | COMP | 2023-10-13 | COMP | 2023-11-17 | COMP | 2023-11-20 | COMP | 2023-12-01 | COMP | Rule 16 | 7 | 31 | 8 | 25 | 2 | 8 | 76
42376 | 2023-08-15 | 2023-08-15 | 2023-09-06 | 2023-09-18 | COMP | 2023-09-21 | COMP | 2023-10-16 | COMP | 2023-09-18 | COMP | 2023-11-04 | COMP | Rule 16 | 1 | 16 | 4 | 18 | 0 | 15 | 58
42430 | 2023-08-15 | 2023-09-06 | 2023-10-04 | 2023-10-04 | COMP | 2023-10-10 | COMP | 2023-10-10 | COMP | 2023-10-12 | COMP | 2023-11-27 | COMP | Rule 16 | 16 | 21 | 5 | 1 | 3 | 30 | 71
42435 | 2023-08-15 | 2023-09-08 | 2023-09-26 | 2023-09-26 | COMP | 2023-10-05 | COMP | 2023-10-05 | COMP | 2023-10-26 | COMP | 2023-11-30 | COMP | Rule 16 | 18 | 13 | 8 | 1 | 16 | 23 | 74
42445 | 2023-08-16 | 2023-09-18 | 2023-10-17 | 2023-10-17 | COMP | 2023-11-10 | COMP | 2023-11-10 | COMP | 2023-11-10 | COMP | 2023-12-13 | COMP | Rule 15/16 | 23 | 22 | 18 | 0 | 0 | 21 | 82
42396 | 2023-08-18 | 2023-08-21 | 2023-09-09 | 2023-09-09 | COMP | 2023-09-18 | COMP | 2023-10-10 | COMP | 2023-09-18 | COMP | 2023-12-02 | COMP | Rule 16 | 2 | 14 | 6 | 17 | 0 | 36 | 72
42427 | 2023-08-21 | 2023-09-06 | 2023-09-18 | 2023-09-18 | COMP | 2023-10-02 | COMP | 2023-12-04 | COMP | 2023-11-28 | COMP | 2023-12-09 | COMP | Rule 16 | 12 | 9 | 11 | 43 | 0 | 5 | 76
42465 | 2023-08-22 | 2023-10-03 | 2023-10-19 | 2023-10-19 | COMP | 2023-10-31 | COMP | 2023-10-31 | COMP | 2023-11-02 | COMP | 2023-12-13 | COMP | Rule 16 | 30 | 13 | 9 | 1 | 3 | 27 | 78
42472 | 2023-08-22 | 2023-10-11 | 2023-11-20 | 2023-11-20 | COMP | 2023-11-20 | NOTN | 2023-11-20 | COMP | 2023-11-20 | COMP | 2023-12-06 | COMP | Rule 16 | 36 | 28 |  | 1 | 1 | 11 | 73
42462 | 2023-08-23 | 2023-10-02 | 2023-10-28 | 2023-10-28 | COMP | 2023-11-15 | COMP | 2023-11-15 | COMP | 2023-11-15 | COMP | 2023-12-28 | COMP | Rule 16 | 28 | 20 | 12 | 1 | 1 | 29 | 87
42441 | 2023-08-24 | 2023-09-14 | 2023-10-04 | 2023-10-04 | COMP | 2023-10-05 | NOTN | 2023-10-05 | COMP | 2023-10-05 | COMP | 2023-12-01 | COMP | Other | 15 | 15 |  | 2 | 1 | 39 | 68
42442 | 2023-08-29 | 2023-09-15 | 2023-10-02 | 2023-10-02 | COMP | 2023-10-10 | COMP | 2023-10-31 | COMP | 2023-10-06 | COMP | 2023-12-07 | COMP | Rule 16 | 13 | 12 | 7 | 16 | 0 | 25 | 69
42454 | 2023-08-31 | 2023-09-21 | 2023-10-27 | 2023-10-27 | COMP | 2023-11-06 | COMP | 2023-11-07 | COMP | 2023-11-28 | COMP | 2023-12-09 | COMP | Rule 16 | 15 | 27 | 7 | 2 | 13 | 9 | 68
42459 | 2023-08-31 | 2023-09-27 | 2023-10-04 | 2023-10-04 | COMP | 2023-10-11 | COMP | 2023-10-30 | COMP | 2023-11-02 | COMP | 2023-12-04 | COMP | Rule 16 | 19 | 6 | 6 | 14 | 4 | 20 | 64
42473 | 2023-08-31 | 2023-10-12 | 2023-11-08 | 2023-11-08 | COMP | 2023-11-15 | COMP | 2023-11-15 | COMP | 2023-11-17 | COMP | 2023-12-19 | COMP | Rule 16 | 30 | 20 | 5 | 1 | 3 | 21 | 75
42479 | 2023-09-05 | 2023-10-30 | 2023-11-12 | 2023-11-12 | COMP | 2023-11-20 | COMP | 2023-11-20 | COMP | 2023-11-27 | COMP | 2023-12-28 | COMP | Rule 16 | 40 | 9 | 6 | 1 | 4 | 23 | 79
42482 | 2023-09-13 | 2023-11-15 | 2023-11-30 | 2023-11-30 | COMP | 2023-12-05 | COMP | 2023-12-05 | COMP | 2023-12-14 | COMP | 2023-12-27 | COMP | Rule 16 | 45 | 10 | 4 | 1 | 8 | 9 | 72
42456 | 2023-09-14 | 2023-09-22 | 2023-10-02 | 2023-10-02 | COMP | 2023-10-12 | COMP | 2023-10-12 | COMP | 2023-11-28 | COMP | 2023-12-09 | COMP | Rule 16 | 7 | 7 | 9 | 1 | 31 | 9 | 59
42471 | 2023-09-19 | 2023-10-11 | 2023-10-27 | 2023-10-27 | COMP | 2023-10-30 | COMP | 2023-11-08 | COMP | 2023-11-01 | COMP | 2023-11-22 | COMP | Rule 16 | 17 | 13 | 2 | 8 | 0 | 10 | 46
42467 | 2023-09-20 | 2023-10-04 | 2023-11-17 | 2023-11-17 | COMP | 2023-11-27 | COMP | 2023-11-27 | COMP | 2023-11-30 | COMP | 2023-12-20 | COMP | Rule 16 | 11 | 32 | 5 | 1 | 4 | 15 | 63
42469 | 2023-09-21 | 2023-10-10 | 2023-10-25 | 2023-10-25 | COMP | 2023-10-30 | COMP | 2023-12-11 | COMP | 2023-12-05 | COMP | 2023-12-21 | COMP | Rule 16 | 14 | 12 | 4 | 28 | 0 | 9 | 63
42480 | 2023-10-17 | 2023-11-01 | 2023-11-10 | 2023-11-10 | COMP | 2023-11-17 | COMP | 2023-12-07 | COMP | 2023-12-08 | COMP | 2023-12-27 | COMP | Rule 16 | 12 | 7 | 5 | 13 | 2 | 13 | 48
1 | 2002-01-15 | 2003-11-10 | [7 empty] | 2009-01-31 | COMP | 2020-05-21 | COMP | Other | 460 | [5 empty] | 4610
2 | 2005-11-09 | 2005-12-23 | 2009-05-12 | 2009-05-12 | COMP | 2009-05-12 | COMP |  | REQD |  | REQD | 2020-06-24 | COMP | Other | 30 | 851 | 1 |  |  |  | 3672
5882 | 2018-04-26 | 2018-07-09 | 2018-11-10 | 2020-09-05 | COMP | 2020-10-20 | COMP | 2020-10-20 | COMP | 2021-06-24 | COMP | 2021-07-23 | COMP | Rule 16 | 51 | 89 | 31 | 1 | 170 | 21 | 816
7693 | 2018-06-18 | 2018-10-27 | 2018-12-26 | 2018-12-26 | COMP | 2019-02-11 | COMP | 2019-02-11 | COMP | 2019-02-12 | COMP | 2019-02-21 | COMP | Rule 16 | 93 | 39 | 32 | 1 | 2 | 7 | 170
13985 | 2022-03-23 | 2019-08-20 | 2020-09-04 | 2020-09-04 | COMP | 2022-03-16 | COMP | 2022-03-23 | COMP | 2022-09-22 | COMP | 2022-10-18 | COMP | Rule 16 |  | 265 | 383 | 6 | 128 | 19 | 146
22456 | 2020-12-09 | 2020-09-25 | 2020-10-27 | 2020-10-27 | COMP | 2020-11-02 | COMP | 2020-12-09 | COMP | 2021-03-26 | COMP | 2021-05-19 | COMP | Rule 16 |  | 23 | 5 | 25 | 74 | 39 | 112
36179 | 2022-05-03 | 2022-05-05 | 2022-06-13 | 2022-06-13 | COMP | 2022-07-26 | COMP | 2022-08-12 | COMP | 2022-09-07 | COMP | 2022-10-19 | COMP | Rule 16 | 3 | 27 | 30 | 14 | 18 | 31 | 118
36199 | 2022-04-15 | 2022-05-06 | 2022-06-09 | 2022-06-09 | COMP | 2022-08-02 | COMP | 2022-08-02 | COMP | 2022-10-04 | COMP | 2022-11-01 | COMP | Rule 16 | 16 | 24 | 37 | 1 | 45 | 21 | 139
36239 | 2022-04-16 | 2022-05-09 | 2022-11-16 | 2022-11-16 | COMP | 2022-12-28 | COMP | 2022-12-28 | COMP | 2023-03-01 | COMP | 2023-08-01 | COMP | Rule 16 | 16 | 133 | 28 | 1 | 43 | 107 | 323
36346 | 2022-04-15 | 2022-05-13 | 2022-06-17 | 2022-06-17 | COMP | 2022-06-01 | NOTN | 2022-06-17 | COMP | 2022-06-17 | COMP | 2022-08-03 | COMP | Other | 21 | 25 |  | 1 | 1 | 32 | 76
36354 | 2022-04-15 | 2022-05-12 | 2022-09-07 | 2022-10-24 | COMP | 2022-11-02 | COMP | 2023-02-08 | COMP | 2023-01-27 | COMP | 2023-07-25 | COMP | Rule 16 | 20 | 81 | 8 | 65 | 0 | 116 | 319
36381 | 2022-04-21 | 2022-05-13 | 2022-08-18 | 2022-08-18 | COMP | 2022-08-26 | COMP | 2023-03-27 | COMP | 2023-01-24 | COMP | 2023-04-03 | COMP | Rule 16 | 17 | 67 | 7 | 144 | 0 | 6 | 237
36423 | 2022-04-11 | 2022-05-16 | 2022-09-22 | 2022-09-22 | COMP | 2022-09-28 | COMP | 2022-11-22 | COMP | 2022-12-12 | COMP | 2023-10-26 | COMP | Rule 16 | 26 | 90 | 5 | 39 | 13 | 221 | 389
36552 | 2022-05-01 | 2022-05-22 | 2022-10-31 | 2022-10-31 | COMP | 2022-11-07 | COMP | 2022-11-07 | COMP | 2023-08-09 | COMP | 2023-08-30 | COMP | Rule 16 | 15 | 112 | 6 | 1 | 188 | 16 | 334
36683 | 2022-05-20 | 2022-05-28 | 2022-07-07 | 2022-07-07 | COMP | 2022-07-11 | COMP | 2022-08-01 | COMP | 2022-10-11 | COMP | 2023-01-31 | COMP | Rule 16 | 6 | 26 | 3 | 16 | 51 | 75 | 173
36813 | 2022-04-03 | 2022-06-04 | 2023-01-10 | 2023-01-10 | COMP | 2023-01-27 | COMP | 2023-01-27 | COMP | 2023-05-06 | COMP | 2023-05-11 | COMP | Rule 16 | 44 | 149 | 13 | 1 | 70 | 4 | 278
36897 | 2022-04-01 | 2022-06-08 | 2022-12-09 | 2022-12-09 | COMP | 2022-12-14 | COMP | 2023-01-25 | COMP | 2023-03-13 | COMP | 2023-05-27 | COMP | Rule 16 | 48 | 127 | 4 | 28 | 33 | 55 | 290
36933 | 2022-04-22 | 2022-06-09 | 2022-06-20 | 2022-06-20 | COMP | 2022-06-24 | COMP | 2022-08-11 | COMP | 2022-06-27 | COMP | 2022-10-04 | COMP | Rule 16 | 34 | 7 | 4 | 34 | 0 | 38 | 114
37004 | 2022-04-25 | 2022-06-13 | 2022-07-18 | 2022-07-18 | COMP | 2022-07-18 | NOTN | 2022-07-18 | COMP | 2022-07-18 | COMP | 2022-08-25 | COMP | Other | 35 | 24 |  | 1 | 1 | 29 | 86
37040 | 2022-05-10 | 2022-06-15 | 2022-07-02 | 2022-07-02 | COMP | 2023-01-12 | COMP | 2023-06-14 | COMP | 2023-07-14 | COMP | 2023-08-04 | COMP | Rule 16 | 26 | 12 | 132 | 107 | 21 | 16 | 310
37051 | 2022-04-18 | 2022-06-14 | 2022-08-09 | 2022-08-09 | COMP | 2022-08-12 | COMP | 2022-08-17 | COMP |  | INPR | 2023-07-24 | COMP | Rule 16 | 41 | 39 | 4 | 4 |  |  | 317
37076 | 2022-06-02 | 2022-06-16 | 2022-10-19 | 2022-10-19 | COMP | 2022-10-26 | COMP | 2022-12-05 | COMP | 2022-12-13 | COMP | 2023-04-20 | COMP | Rule 16 | 11 | 87 | 6 | 26 | 7 | 89 | 221
37086 | 2022-03-31 | 2022-06-16 | 2022-10-04 | 2022-10-04 | COMP | 2023-01-13 | COMP | 2023-05-09 | COMP | 2023-09-09 | COMP | 2023-10-13 | COMP | Rule 16 | 55 | 76 | 69 | 81 | 85 | 25 | 387
37112 | 2022-04-25 | 2022-06-17 | 2022-12-12 | 2022-12-12 | COMP | 2022-12-16 | COMP | 2022-12-22 | COMP | 2023-01-19 | COMP | 2023-03-27 | COMP | Rule 16 | 39 | 121 | 5 | 5 | 18 | 47 | 230
37190 | 2022-05-18 | 2022-06-22 | 2022-08-19 | 2022-08-19 | COMP | 2022-09-09 | COMP | 2022-09-14 | COMP | 2022-09-27 | COMP | 2022-09-27 | COMP | Rule 16 | 24 | 42 | 15 | 4 | 10 | 1 | 91
37291 | 2022-05-18 | 2022-06-28 | 2022-08-08 | 2022-08-08 | COMP | 2022-09-07 | COMP | 2022-11-14 | COMP | 2023-06-06 | COMP | 2023-06-21 | COMP | Rule 16 | 28 | 29 | 22 | 48 | 140 | 11 | 273
37320 | 2022-04-13 | 2022-06-29 | 2022-12-02 | 2022-12-02 | COMP | 2023-01-13 | COMP | 2023-01-13 | COMP | 2023-11-22 | COMP | 2023-05-01 | COMP | Rule 16 | 54 | 108 | 29 | 1 | 217 |  | 263
37349 | 2022-06-03 | 2022-06-30 | 2022-10-19 | 2022-10-19 | COMP | 2022-12-15 | COMP | 2022-12-22 | COMP | 2022-12-21 | COMP | 2023-05-15 | COMP | Rule 16 | 19 | 78 | 39 | 6 | 0 | 99 | 237
37386 | 2022-06-06 | 2022-07-01 | 2022-10-12 | 2022-10-12 | COMP | 2022-11-14 | COMP | 2022-11-14 | COMP | 2022-12-19 | COMP | 2023-07-21 | COMP | Rule 16 | 19 | 72 | 23 | 1 | 24 | 148 | 282
37397 | 2022-05-09 | 2022-07-01 | 2022-11-20 | 2022-11-20 | COMP | 2022-11-23 | COMP | 2022-12-01 | COMP | 2023-03-16 | COMP | 2023-04-18 | COMP | Rule 16 | 38 | 98 | 3 | 5 | 72 | 24 | 236
37491 | 2022-06-06 | 2022-07-08 | 2022-11-09 | 2022-11-09 | COMP | 2022-11-09 | NOTN | 2023-02-06 | COMP | 2023-02-15 | COMP | 2023-04-28 | COMP | Other | 23 | 88 |  | 58 | 8 | 52 | 225
37741 | 2022-05-08 | 2022-07-21 | 2023-02-04 | 2023-02-04 | COMP | 2023-02-13 | COMP | 2023-05-02 | COMP | 2023-06-26 | COMP | 2023-06-26 | COMP | Rule 16 | 51 | 135 | 6 | 56 | 38 | 1 | 283
37803 | 2022-05-27 | 2022-07-25 | 2022-11-28 | 2022-11-28 | COMP | 2022-11-29 | NOTN | 2023-02-15 | COMP | 2023-03-03 | COMP | 2023-10-25 | COMP | Other | 39 | 87 |  | 55 | 12 | 165 | 354
37935 | 2022-05-27 | 2022-08-02 | 2022-09-14 | 2022-09-14 | COMP | 2022-09-21 | COMP | 2023-04-11 | COMP | 2023-02-24 | COMP | 2023-04-17 | COMP | Rule 16 | 45 | 31 | 6 | 138 | 0 | 5 | 221
37994 | 2022-06-29 | 2022-08-05 | 2022-09-04 | 2022-11-11 | COMP | 2022-11-21 | NOTN | 2022-11-21 | COMP | 2024-03-04 | INPR | 2023-02-01 | COMP | Other | 27 | 21 |  | 6 |  |  | 148
38032 | 2022-04-19 | 2022-08-06 | 2022-12-13 | 2022-12-13 | COMP | 2022-12-20 | COMP | 2023-02-21 | COMP |  | INPR | 2023-05-11 | COMP | Rule 16 | 76 | 88 | 6 | 42 |  |  | 267
38062 | 2022-06-30 | 2022-08-09 | 2022-10-11 | 2022-10-11 | COMP | 2022-10-21 | COMP | 2022-11-29 | COMP | 2022-11-30 | COMP | 2023-05-16 | COMP | Rule 16 | 28 | 45 | 9 | 25 | 2 | 116 | 220
38127 | 2022-06-09 | 2022-08-11 | 2022-08-28 | 2022-08-28 | COMP | 2022-10-24 | COMP | 2022-10-24 | COMP | 2022-10-24 | COMP | 2022-09-22 | COMP | Rule 16 | 44 | 12 | 40 | 1 | 1 |  | 73
38156 | 2022-06-10 | 2022-08-12 | 2022-12-06 | 2022-12-06 | COMP | 2022-12-08 | COMP | 2023-02-03 | COMP | 2023-03-23 | COMP | 2023-04-21 | COMP | Rule 16 | 44 | 79 | 3 | 39 | 34 | 22 | 216
38205 | 2022-04-27 | 2022-08-16 | 2023-02-06 | 2023-10-17 | COMP | 2023-10-23 | COMP | 2023-11-29 | COMP | 2023-09-11 | COMP | 2023-12-15 | COMP | Rule 16 | 77 | 118 | 5 | 25 | 0 | 13 | 410
38246 | 2022-07-18 | 2022-08-17 | 2023-02-09 | 2023-02-28 | COMP | 2023-03-06 | COMP | 2023-03-28 | COMP | 2023-05-04 | COMP | 2023-10-27 | COMP | Rule 16 | 23 | 120 | 5 | 17 | 28 | 123 | 323
38292 | 2022-07-21 | 2022-08-19 | 2022-11-18 | 2022-11-18 | COMP | 2022-11-29 | COMP | 2023-02-09 | COMP | 2023-02-23 | COMP | 2023-06-20 | COMP | Rule 16 | 22 | 64 | 6 | 50 | 10 | 82 | 229
38318 | 2022-04-18 | 2022-08-22 | 2022-10-17 | 2022-10-17 | COMP | 2022-10-28 | COMP | 2023-04-18 | COMP | 2023-04-12 | COMP | 2023-05-08 | COMP | Rule 16 | 88 | 40 | 10 | 116 | 0 | 15 | 265
38393 | 2022-06-28 | 2022-08-24 | 2023-01-17 | 2023-01-17 | COMP | 2023-01-26 | COMP | 2023-07-13 | COMP | 2023-05-08 | COMP | 2023-10-09 | COMP | Rule 16 | 41 | 98 | 8 | 117 | 0 | 62 | 322
38394 | 2022-08-04 | 2022-08-24 | 2023-03-07 | 2023-03-07 | COMP | 2023-03-16 | COMP |  | REQD | 2023-04-28 | COMP | 2023-06-13 | COMP | Rule 16 | 15 | 132 | 8 |  |  |  | 215
38456 | 2022-08-08 | 2022-08-29 | 2023-02-02 | 2023-02-02 | COMP | 2023-02-27 | COMP | 2023-02-27 | COMP | 2023-05-11 | COMP | 2023-05-19 | COMP | Rule 16 | 16 | 107 | 17 | 1 | 54 | 7 | 197
38488 | 2022-07-22 | 2022-08-30 | 2022-10-02 | 2022-10-02 | COMP | 2023-03-29 | COMP | 2023-03-29 | COMP | 2023-07-08 | COMP | 2023-08-17 | COMP | Rule 16 | 28 | 23 | 121 | 1 | 70 | 29 | 269
38501 | 2022-07-19 | 2022-08-30 | 2022-12-15 | 2022-12-15 | COMP | 2023-01-20 | COMP | 2023-01-20 | COMP | 2023-06-05 | COMP | 2023-07-05 | COMP | Rule 16 | 31 | 74 | 24 | 1 | 95 | 21 | 241
38543 | 2022-07-08 | 2022-09-02 | 2023-01-24 | 2023-01-24 | COMP | 2023-01-24 | NOTN | 2023-06-23 | COMP | 2023-04-27 | COMP | 2023-07-27 | COMP | Other | 41 | 96 |  | 106 | 0 | 24 | 264
38560 | 2022-07-08 | 2022-09-01 | 2023-06-05 | 2023-06-05 | COMP | 2023-06-23 | COMP | 2023-12-06 | COMP | 2023-07-13 | COMP | 2023-12-14 | COMP | Rule 16 | 40 | 189 | 14 | 114 | 0 | 7 | 360
38574 | 2022-07-18 | 2022-09-02 | 2022-11-30 | 2022-11-30 | COMP | 2023-01-31 | COMP | 2023-01-31 | COMP | 2023-09-01 | COMP | 2023-10-04 | COMP | Rule 16 | 35 | 60 | 42 | 1 | 150 | 23 | 306
38577 | 2022-08-15 | 2022-09-02 | 2023-01-18 | 2023-01-18 | COMP | 2023-01-18 | NOTN | 2023-05-01 | COMP | 2023-05-01 | COMP | 2023-05-17 | COMP | Other | 15 | 92 |  | 73 | 1 | 13 | 190
38618 | 2022-06-15 | 2022-09-06 | 2023-01-11 | 2023-01-11 | COMP | 2023-01-12 | NOTN | 2023-02-10 | COMP | 2023-02-10 | COMP | 2023-05-01 | COMP | Other | 57 | 87 |  | 22 | 1 | 56 | 219
38620 | 2022-07-27 | 2022-09-06 | 2022-12-14 | 2022-12-14 | COMP | 2022-12-21 | COMP | 2023-02-13 | COMP | 2023-04-11 | COMP | 2023-07-28 | COMP | Rule 16 | 29 | 69 | 6 | 36 | 41 | 76 | 252
38685 | 2022-08-09 | 2022-09-08 | 2022-10-19 | 2022-10-19 | COMP | 2022-10-26 | COMP | 2022-11-04 | COMP | 2023-03-07 | COMP | 2023-01-26 | COMP | Rule 16 | 22 | 30 | 6 | 8 | 81 |  | 116
38702 | 2022-08-06 | 2022-09-12 | 2023-02-02 | 2023-02-02 | COMP | 2023-02-17 | COMP | 2023-08-15 | COMP |  | INPR | 2023-10-27 | COMP | Rule 16 | 25 | 98 | 12 | 124 |  |  | 308
38776 | 2022-08-09 | 2022-09-14 | 2022-12-28 | 2022-12-28 | COMP | 2022-12-28 | NOTN | 2023-05-02 | COMP | 2023-11-22 | COMP | 2023-06-26 | COMP | Other | 26 | 72 |  | 87 | 142 |  | 220
38788 | 2022-08-10 | 2022-09-15 | 2022-12-16 | 2022-12-16 | COMP | 2022-12-19 | NOTN | 2023-01-30 | COMP | 2023-05-03 | COMP | 2023-10-11 | COMP | Other | 26 | 64 |  | 29 | 67 | 112 | 294
38889 | 2022-08-24 | 2022-09-21 | 2023-03-31 | 2023-03-31 | COMP | 2023-04-10 | COMP | 2023-07-05 | COMP | 2023-08-23 | COMP | 2023-11-27 | COMP | Rule 16 | 20 | 131 | 7 | 60 | 36 | 65 | 314
38954 | 2022-08-12 | 2022-09-23 | 2023-03-28 | 2023-03-28 | COMP | 2023-06-12 | COMP | 2023-07-06 | COMP | 2023-09-05 | COMP | 2023-10-03 | COMP | Rule 16 | 30 | 126 | 54 | 17 | 43 | 21 | 286
38985 | 2022-08-26 | 2022-09-26 | 2023-04-08 | 2023-04-08 | COMP | 2023-05-15 | COMP | 2023-06-20 | COMP | 2023-06-22 | COMP | 2023-08-23 | COMP | Rule 16 | 21 | 133 | 26 | 25 | 3 | 44 | 248
39031 | 2022-08-16 | 2022-09-28 | 2022-11-10 | 2022-11-10 | COMP | 2022-11-30 | COMP | 2022-11-30 | COMP | 2023-03-22 | COMP | 2023-03-31 | COMP | Rule 16 | 31 | 32 | 12 | 1 | 77 | 8 | 156
39113 | 2022-09-04 | 2022-10-03 | 2023-01-29 | 2023-01-29 | COMP | 2023-01-29 | NOTN | 2023-03-21 | COMP | 2023-04-11 | COMP | 2023-05-17 | COMP | Other | 20 | 79 |  | 36 | 16 | 27 | 175
39126 | 2022-08-30 | 2022-10-04 | 2023-04-26 | 2023-04-26 | COMP | 2023-05-18 | COMP | 2023-06-15 | COMP | 2023-06-21 | COMP | 2023-10-07 | COMP | Rule 16 | 25 | 140 | 17 | 20 | 4 | 76 | 277
39172 | 2022-08-17 | 2022-10-05 | 2023-02-23 | 2023-02-23 | COMP | 2023-03-21 | COMP | 2023-04-04 | COMP | 2023-04-11 | COMP | 2023-05-23 | COMP | Rule 16 | 35 | 95 | 19 | 11 | 6 | 31 | 192
39239 | 2022-08-23 | 2022-10-07 | 2023-02-01 | 2023-02-01 | COMP | 2023-02-06 | COMP | 2023-06-27 | COMP | 2023-06-27 | COMP | 2023-10-10 | COMP | Rule 16 | 33 | 78 | 4 | 99 | 1 | 74 | 284
39269 | 2022-07-07 | 2022-10-10 | 2023-05-15 | 2023-05-15 | COMP | 2023-05-26 | COMP | 2023-07-31 | COMP | 2023-09-07 | COMP | 2023-12-04 | COMP | Rule 16 | 67 | 149 | 10 | 44 | 28 | 60 | 353
39285 | 2022-08-31 | 2022-10-11 | 2023-01-30 | 2023-01-30 | COMP | 2023-02-07 | COMP | 2023-02-10 | COMP | 2023-04-26 | COMP | 2023-07-14 | COMP | Rule 16 | 29 | 74 | 7 | 4 | 53 | 55 | 217
39308 | 2022-08-23 | 2022-10-12 | 2023-02-28 | 2023-02-28 | COMP | 2023-03-03 | COMP | 2023-04-17 | COMP | 2023-05-22 | COMP | 2023-09-07 | COMP | Rule 16 | 36 | 93 | 4 | 32 | 26 | 75 | 261
39399 | 2022-09-10 | 2022-10-18 | 2023-03-17 | 2023-03-17 | COMP | 2023-03-17 | NOTN | 2023-05-10 | COMP | 2023-03-20 | COMP | 2023-06-27 | COMP | Other | 27 | 102 |  | 39 | 0 | 33 | 198
39434 | 2022-07-15 | 2022-10-20 | 2022-11-18 | 2022-11-18 | COMP | 2022-12-28 | COMP | 2022-12-28 | COMP | 2023-03-06 | COMP | 2023-03-30 | COMP | Rule 16 | 69 | 21 | 26 | 1 | 46 | 19 | 177
39449 | 2022-08-22 | 2022-10-20 | 2022-11-17 | 2022-11-17 | COMP | 2022-12-12 | COMP | 2022-12-12 | COMP | 2023-03-29 | COMP | 2023-05-05 | COMP | Rule 16 | 43 | 20 | 16 | 1 | 74 | 28 | 177
39468 | 2022-09-14 | 2022-10-21 | 2023-03-10 | 2023-03-10 | COMP | 2023-05-11 | COMP | 2023-08-08 | COMP | 2023-09-18 | COMP | 2023-10-09 | COMP | Rule 16 | 28 | 94 | 45 | 61 | 29 | 16 | 268
39576 | 2022-09-20 | 2022-10-27 | 2023-03-01 | 2023-03-01 | COMP | 2023-03-01 | NOTN | 2023-04-18 | COMP | 2023-03-01 | COMP | 2023-06-16 | COMP | Other | 28 | 83 |  | 35 | 0 | 43 | 186
39589 | 2022-06-18 | 2022-10-27 | 2023-01-14 | 2023-01-14 | COMP | 2023-02-17 | COMP | 2023-02-18 | COMP | 2023-04-07 | COMP | 2023-04-19 | COMP | Rule 16 | 91 | 52 | 24 | 1 | 34 | 9 | 208
39684 | 2022-09-22 | 2022-11-03 | 2023-04-28 | 2023-04-28 | COMP | 2023-05-12 | COMP | 2023-07-05 | COMP | 2023-07-05 | COMP | 2023-10-11 | COMP | Rule 16 | 31 | 120 | 11 | 36 | 1 | 70 | 264
39705 | 2022-08-03 | 2022-11-04 | 2023-01-03 | 2023-01-15 | COMP | 2023-01-23 | COMP | 2023-04-12 | COMP | 2023-05-30 | COMP | 2023-07-05 | COMP | Rule 16 | 67 | 38 | 5 | 57 | 34 | 25 | 230
39736 | 2022-10-12 | 2022-11-06 | 2023-02-03 | 2023-02-03 | COMP | 2023-02-14 | COMP | 2023-02-14 | INPR | 2023-06-21 | COMP | 2023-07-11 | COMP | Rule 16 | 18 | 59 | 8 |  |  |  | 185
39768 | 2022-09-22 | 2022-11-07 | 2022-12-09 | 2022-12-09 | COMP | 2022-12-13 | NOTN | 2022-12-13 | COMP | 2023-05-22 | COMP | 2023-07-12 | COMP | Rule 16 | 33 | 22 |  | 3 | 111 | 35 | 200
39824 | 2022-08-12 | 2022-11-11 | 2023-06-18 | 2023-06-18 | COMP | 2023-06-22 | COMP | 2023-07-25 | COMP | 2023-07-25 | COMP | 2023-10-11 | COMP | Rule 16 | 64 | 148 | 3 | 23 | 1 | 56 | 292
39827 | 2022-09-15 | 2022-11-11 | 2023-02-23 | 2023-02-23 | COMP | 2023-03-02 | COMP | 2023-04-07 | COMP | 2023-05-17 | COMP | 2023-06-13 | COMP | Rule 16 | 41 | 68 | 6 | 27 | 29 | 19 | 186
39862 | 2022-08-01 | 2022-11-14 | 2022-12-18 | 2022-12-18 | COMP | 2022-12-27 | COMP | 2023-05-22 | COMP | 2023-06-26 | COMP | 2023-08-14 | COMP | Rule 16 | 74 | 23 | 6 | 102 | 24 | 35 | 260
39947 | 2022-09-23 | 2022-11-21 | 2022-12-20 | 2022-12-20 | COMP | 2023-01-03 | COMP | 2023-04-12 | COMP | 2023-04-18 | COMP | 2023-06-05 | COMP | Rule 16 | 41 | 20 | 9 | 70 | 5 | 34 | 174
39948 | 2022-09-23 | 2022-11-21 | 2023-01-05 | 2023-01-05 | COMP | 2023-01-05 | NOTN | 2023-04-17 | COMP | 2023-04-18 | COMP | 2023-06-05 | COMP | Other | 41 | 30 |  | 71 | 2 | 34 | 174
40037 | 2022-11-07 | 2022-11-30 | 2023-03-04 | 2023-03-04 | COMP | 2023-03-10 | COMP | 2023-03-10 | COMP | 2023-07-30 | COMP | 2023-10-02 | COMP | Rule 16 | 15 | 64 | 5 | 1 | 98 | 45 | 225
40044 | 2022-06-03 | 2022-12-01 | 2023-05-20 | 2023-05-20 | COMP | 2023-06-14 | COMP | 2023-06-14 | COMP | 2023-09-05 | COMP | 2023-12-08 | COMP | Rule 15/16 | 124 | 118 | 17 | 1 | 57 | 66 | 379
40046 | 2022-10-06 | 2022-12-01 | 2023-03-28 | 2023-03-28 | COMP | 2023-03-28 | NOTN | 2023-04-03 | COMP | 2023-06-01 | COMP | 2023-08-07 | COMP | Other | 38 | 80 |  | 5 | 43 | 46 | 208
40048 | 2022-09-29 | 2022-12-01 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-30 | COMP | 2023-07-10 | COMP | 2023-05-05 | COMP | 2023-10-04 | COMP | Rule 16 | 43 | 102 | 23 | 28 | 0 | 62 | 254
40079 | 2022-09-27 | 2022-12-02 | 2023-07-16 | 2023-07-16 | COMP | 2023-07-24 | COMP | 2023-07-31 | COMP | 2023-12-07 | COMP | 2023-12-20 | COMP | Rule 16 | 46 | 154 | 6 | 6 | 90 | 10 | 308
40084 | 2022-08-24 | 2022-12-02 | 2023-04-24 | 2023-04-24 | COMP | 2023-05-08 | COMP | 2023-05-08 | COMP | 2023-09-05 | COMP | 2023-09-22 | COMP | Rule 16 | 69 | 98 | 11 | 1 | 83 | 14 | 271
40091 | 2022-09-26 | 2022-12-03 | 2023-04-04 | 2023-04-04 | COMP | 2023-04-13 | NOTN |  | REQD | 2023-11-01 | COMP | 2023-11-09 | COMP | Other | 47 | 83 |  |  |  |  | 283
40099 | 2022-09-14 | 2022-12-05 | 2023-04-27 | 2023-04-27 | COMP | 2023-05-22 | COMP | 2023-06-22 | COMP | 2023-09-05 | COMP | 2023-10-20 | COMP | Rule 16 | 56 | 100 | 18 | 22 | 52 | 34 | 277
40106 | 2022-11-07 | 2022-12-05 | 2023-03-23 | 2023-03-23 | COMP | 2023-04-03 | COMP | 2023-05-24 | COMP | 2023-07-20 | COMP | 2023-08-18 | COMP | Rule 16 | 18 | 75 | 8 | 38 | 39 | 22 | 195
40160 | 2022-10-09 | 2022-12-08 | 2023-03-15 | 2023-03-15 | COMP | 2023-04-03 | COMP | 2023-04-03 | COMP | 2023-05-11 | COMP | 2023-07-14 | COMP | Rule 16 | 41 | 66 | 14 | 1 | 29 | 44 | 190
40197 | 2022-11-20 | 2022-12-12 | 2023-04-27 | 2023-04-27 | COMP | 2023-04-27 | NOTN | 2023-06-13 | COMP | 2023-07-24 | COMP | 2023-08-04 | COMP | Other | 14 | 95 |  | 33 | 28 | 10 | 176
40263 | 2022-08-07 | 2022-12-15 | 2023-03-15 | 2023-03-15 | COMP | 2023-03-15 | NOTN | 2023-05-04 | COMP |  | INPR | 2023-06-06 | COMP | Other | 90 | 61 |  | 37 |  |  | 208
40265 | 2022-10-26 | 2022-12-15 | 2023-02-22 | 2023-02-22 | COMP | 2023-03-16 | COMP | 2023-03-23 | COMP |  | INPR | 2023-05-26 | COMP | Rule 16 | 34 | 46 | 17 | 6 |  |  | 146
40297 | 2022-10-31 | 2022-12-19 | 2023-02-07 | 2023-02-07 | COMP | 2023-02-17 | COMP | 2023-05-25 | COMP | 2023-05-18 | COMP | 2023-06-19 | COMP | Rule 16 | 33 | 34 | 9 | 69 | 0 | 16 | 157
40406 | 2022-11-21 | 2022-12-29 | 2023-03-10 | 2023-03-23 | COMP | 2023-04-26 | COMP | 2023-05-26 | COMP | 2023-07-18 | COMP | 2023-09-26 | COMP | Rule 16 | 26 | 49 | 25 | 23 | 35 | 50 | 212
40414 | 2022-10-19 | 2022-12-30 | 2023-02-14 | 2023-02-14 | COMP | 2023-02-16 | COMP | 2023-04-06 | COMP | 2023-03-14 | COMP | 2023-07-20 | COMP | Rule 16 | 49 | 31 | 3 | 35 | 0 | 73 | 187
40431 | 2022-10-31 | 2022-12-31 | 2023-02-16 | 2023-02-16 | COMP | 2023-02-21 | COMP | 2023-06-05 | COMP | 2023-05-10 | COMP | 2023-07-26 | COMP | Rule 16 | 41 | 32 | 3 | 74 | 0 | 36 | 183
40448 | 2022-10-13 | 2023-01-03 | 2023-03-17 | 2023-03-17 | COMP | 2023-04-07 | COMP | 2023-05-18 | COMP | 2023-06-22 | COMP | 2023-10-31 | COMP | Rule 16 | 54 | 52 | 16 | 30 | 24 | 92 | 263
40482 | 2022-11-04 | 2023-01-06 | 2023-02-06 | 2023-02-06 | COMP | 2023-02-28 | COMP | 2023-06-05 | COMP | 2023-07-11 | COMP | 2023-09-06 | COMP | Rule 16 | 41 | 21 | 16 | 69 | 25 | 41 | 208
40522 | 2022-11-03 | 2023-01-10 | 2023-03-01 | 2023-03-01 | COMP | 2023-03-08 | COMP | 2023-03-08 | COMP | 2023-09-26 | COMP | 2023-09-26 | COMP | Rule 16 | 44 | 35 | 6 | 1 | 141 | 1 | 223
40556 | 2022-12-14 | 2023-01-11 | 2023-02-06 | 2023-02-12 | COMP | 2023-02-24 | COMP | 2023-03-21 | COMP | 2023-04-26 | COMP | 2023-10-16 | COMP | Rule 16 | 19 | 18 | 9 | 18 | 27 | 120 | 211
40565 | 2022-11-01 | 2023-01-12 | 2023-06-20 | 2023-06-20 | COMP | 2023-07-20 | COMP | 2023-07-20 | COMP | 2023-07-27 | COMP | 2023-08-21 | COMP | Rule 16 | 48 | 110 | 22 | 1 | 6 | 18 | 200
40578 | 2022-11-01 | 2023-01-12 | 2023-01-23 | 2023-01-23 | COMP | 2023-02-09 | COMP | 2023-02-09 | COMP | 2023-06-06 | COMP | 2023-07-10 | COMP | Rule 16 | 48 | 7 | 14 | 1 | 82 | 23 | 170
40606 | 2022-10-31 | 2023-01-14 | 2023-02-26 | 2023-02-26 | COMP | 2023-03-07 | COMP | 2023-03-07 | COMP |  | INPR | 2023-11-30 | COMP | Rule 16 | 50 | 28 | 7 | 1 |  |  | 270
40685 | 2022-11-24 | 2023-01-23 | 2023-04-18 | 2023-04-18 | COMP | 2023-06-13 | COMP | 2023-06-13 | COMP | 2023-10-20 | COMP | 2023-12-26 | COMP | Rule 16 | 38 | 61 | 40 | 1 | 91 | 44 | 270
40711 | 2022-11-23 | 2023-01-24 | 2023-05-07 | 2023-05-07 | COMP | 2023-06-29 | COMP | 2023-06-29 | COMP | 2023-08-28 | COMP | 2023-12-06 | COMP | Rule 16 | 40 | 73 | 37 | 1 | 42 | 69 | 258
40715 | 2022-09-17 | 2023-01-25 | 2023-03-30 | 2023-03-30 | COMP | 2023-06-20 | COMP | 2023-07-28 | COMP | 2023-09-26 | COMP | 2023-10-13 | COMP | Rule 16 | 87 | 46 | 57 | 28 | 42 | 14 | 269
40723 | 2022-12-15 | 2023-01-25 | 2023-04-28 | 2023-04-28 | COMP | 2023-06-09 | COMP | 2023-06-20 | COMP | 2023-10-02 | COMP | 2023-09-07 | COMP | Rule 16 | 27 | 67 | 30 | 7 | 73 |  | 183
40763 | 2022-12-22 | 2023-01-26 | 2023-03-30 | 2023-03-30 | COMP | 2023-04-05 | COMP | 2023-08-31 | COMP | 2023-08-22 | COMP | 2023-10-05 | COMP | Rule 16 | 23 | 45 | 5 | 104 | 0 | 25 | 198
40822 | 2022-11-01 | 2023-02-01 | 2023-05-31 | 2023-05-31 | COMP | 2023-06-01 | NOTN | 2023-06-01 | COMP | 2023-10-02 | COMP | 2023-12-06 | COMP | Other | 61 | 84 |  | 2 | 85 | 45 | 273
40828 | 2022-12-15 | 2023-02-01 | 2023-06-12 | 2023-06-12 | COMP | 2023-06-29 | COMP | 2023-09-20 | COMP | 2023-06-30 | COMP | 2023-10-06 | COMP | Rule 16 | 32 | 92 | 13 | 58 | 0 | 13 | 204
40830 | 2023-01-13 | 2023-02-02 | 2023-05-10 | 2023-05-10 | COMP | 2023-05-10 | NOTN | 2023-06-30 | COMP | 2023-06-05 | COMP | 2023-09-30 | COMP | Other | 14 | 69 |  | 36 | 0 | 64 | 180
41023 | 2022-09-21 | 2023-02-16 | 2023-05-15 | 2023-05-15 | COMP | 2023-05-22 | NOTN | 2023-07-22 | COMP | 2023-08-22 | COMP | 2023-11-04 | COMP | Other | 101 | 62 |  | 47 | 22 | 53 | 282
41119 | 2023-02-14 | 2023-02-24 | 2023-05-21 | 2023-05-21 | COMP | 2023-05-22 | NOTN | 2023-07-05 | COMP | 2023-10-11 | COMP | 2023-10-11 | COMP | Other | 8 | 61 |  | 30 | 70 | 1 | 167
41125 | 2022-10-24 | 2023-02-24 | 2023-04-25 | 2023-04-25 | COMP | 2023-08-29 | COMP | 2023-09-01 | COMP | 2023-09-01 | COMP | 2023-11-01 | COMP | Rule 16 | 83 | 43 | 88 | 4 | 1 | 43 | 257
41293 | 2023-02-04 | 2023-03-10 | 2023-05-20 | 2023-05-20 | COMP | 2023-05-31 | COMP | 2023-06-14 | COMP | 2023-06-09 | COMP | 2023-09-12 | COMP | Rule 16 | 24 | 51 | 7 | 11 | 0 | 62 | 152
41318 | 2023-02-10 | 2023-03-14 | 2023-04-21 | 2023-04-21 | COMP | 2023-05-03 | COMP | 2023-06-06 | COMP | 2023-06-13 | COMP | 2023-08-17 | COMP | Rule 16 | 22 | 29 | 9 | 24 | 6 | 46 | 131
41326 | 2022-11-17 | 2023-03-14 | 2023-04-20 | 2023-06-06 | COMP | 2023-07-24 | COMP | 2023-07-24 | COMP | 2023-09-20 | COMP | 2023-12-15 | COMP | Rule 16 | 78 | 28 | 33 | 1 | 42 | 60 | 269
41329 | 2022-12-01 | 2023-03-14 | 2023-04-18 | 2023-04-18 | COMP | 2023-05-03 | COMP | 2023-09-27 | COMP | 2023-09-26 | COMP | 2023-11-30 | COMP | Rule 16 | 70 | 26 | 12 | 102 | 0 | 44 | 250
41340 | 2022-11-10 | 2023-03-15 | 2023-06-03 | 2023-06-03 | COMP | 2023-06-06 | NOTN | 2023-07-17 | COMP | 2023-08-07 | COMP | 2023-10-16 | COMP | Other | 83 | 57 |  | 29 | 16 | 50 | 232
41395 | 2023-01-10 | 2023-03-22 | 2023-04-27 | 2023-04-27 | COMP | 2023-08-07 | COMP | 2023-08-07 | COMP | 2023-10-31 | COMP | 2023-12-29 | COMP | Rule 16 | 50 | 27 | 70 | 1 | 61 | 40 | 244
41413 | 2023-01-18 | 2023-03-23 | 2023-06-25 | 2023-06-25 | COMP | 2023-07-06 | COMP | 2023-07-06 | COMP | 2023-08-22 | COMP | 2023-09-18 | COMP | Rule 16 | 46 | 65 | 8 | 1 | 34 | 19 | 169
41429 | 2023-01-31 | 2023-03-24 | 2023-06-22 | 2023-06-22 | COMP | 2023-07-07 | COMP | 2023-07-31 | COMP | 2023-09-13 | COMP | 2023-10-26 | COMP | Rule 16 | 38 | 63 | 11 | 17 | 32 | 32 | 188
41538 | 2023-02-06 | 2023-04-03 | 2023-06-26 | 2023-06-26 | COMP | 2023-06-30 | NOTN |  | REQD | 2023-12-06 | COMP | 2023-12-12 | COMP | Other | 40 | 59 |  |  |  |  | 214
41567 | 2023-01-31 | 2023-04-05 | 2023-06-16 | 2023-06-21 | COMP | 2023-08-31 | COMP | 2023-08-31 | COMP | 2023-09-20 | COMP | 2023-10-31 | COMP | Rule 16 | 46 | 52 | 51 | 1 | 14 | 30 | 191
41580 | 2023-01-18 | 2023-04-06 | 2023-05-09 | 2023-05-09 | COMP | 2023-05-17 | COMP | 2023-06-30 | COMP | 2023-05-17 | COMP | 2023-09-13 | COMP | Rule 16 | 56 | 24 | 7 | 31 | 0 | 52 | 166
41604 | 2023-01-13 | 2023-04-11 | 2023-05-17 | 2023-05-17 | COMP | 2023-05-18 | NOTN | 2023-07-18 | COMP | 2023-07-11 | COMP | 2023-10-24 | COMP | Other | 61 | 27 |  | 42 | 0 | 70 | 197
41613 | 2023-03-08 | 2023-04-12 | 2023-05-25 | 2023-05-25 | COMP | 2023-06-09 | COMP | 2023-08-24 | COMP | 2023-09-25 | COMP | 2023-12-15 | COMP | Rule 16 | 26 | 32 | 11 | 53 | 22 | 57 | 196
41659 | 2023-03-07 | 2023-04-17 | 2023-05-31 | 2023-05-31 | COMP | 2023-07-14 | COMP | 2023-07-14 | COMP | 2023-09-18 | COMP | 2023-10-24 | COMP | Rule 16 | 30 | 32 | 31 | 1 | 46 | 27 | 162
41779 | 2023-02-06 | 2023-04-28 | 2023-07-10 | 2023-07-10 | COMP | 2023-07-17 | COMP | 2023-10-06 | INPR | 2023-08-21 | COMP | 2023-10-26 | COMP | Rule 16 | 59 | 49 | 6 |  |  |  | 184
41785 | 2023-02-07 | 2023-04-28 | 2023-07-31 | 2023-07-31 | COMP | 2023-08-09 | COMP | 2023-08-09 | COMP |  | INPR | 2023-10-30 | COMP | Rule 16 | 58 | 64 | 8 | 1 |  |  | 185
41813 | 2023-03-09 | 2023-05-03 | 2023-07-26 | 2023-07-26 | COMP | 2023-08-08 | COMP | 2023-10-24 | COMP | 2023-12-11 | COMP | 2023-12-11 | COMP | Rule 16 | 40 | 58 | 10 | 55 | 32 | 1 | 191
41816 | 2023-03-10 | 2023-05-03 | 2023-07-28 | 2023-07-28 | COMP | 2023-08-14 | COMP | 2023-09-15 | INPR | 2023-08-31 | COMP | 2023-09-27 | COMP | Rule 16 | 39 | 60 | 12 |  |  |  | 140
41869 | 2023-03-07 | 2023-05-10 | 2023-06-29 | 2023-06-29 | COMP | 2023-07-07 | COMP | 2023-09-13 | COMP | 2023-11-27 | COMP | 2023-11-02 | COMP | Rule 16 | 47 | 35 | 6 | 48 | 51 |  | 169
41890 | 2023-03-15 | 2023-05-12 | 2023-06-27 | 2023-06-27 | COMP | 2023-07-14 | COMP | 2023-07-14 | COMP | 2023-09-07 | COMP | 2023-11-02 | COMP | Rule 16 | 43 | 31 | 13 | 1 | 39 | 41 | 163
41925 | 2023-02-28 | 2023-05-18 | 2023-07-12 | 2023-07-12 | COMP | 2023-09-07 | COMP | 2023-09-07 | COMP | 2023-10-03 | COMP | 2023-11-10 | COMP | Rule 16 | 58 | 37 | 41 | 1 | 19 | 28 | 179
41947 | 2023-04-19 | 2023-05-22 | 2023-06-29 | 2023-06-29 | COMP | 2023-07-31 | COMP | 2023-08-11 | COMP | 2023-09-05 | COMP | 2023-09-08 | COMP | Rule 16 | 24 | 27 | 22 | 10 | 17 | 4 | 99
41955 | 2023-01-31 | 2023-05-23 | 2023-06-28 | 2023-06-28 | COMP | 2023-08-08 | COMP | 2023-08-11 | COMP | 2023-08-15 | COMP | 2023-11-17 | COMP | Rule 16 | 80 | 25 | 29 | 4 | 3 | 67 | 203
41967 | 2023-03-24 | 2023-05-24 | 2023-07-07 | 2023-07-07 | COMP | 2023-07-25 | NOTN | 2023-11-03 | COMP | 2023-09-20 | COMP | 2023-11-18 | COMP | Other | 44 | 30 |  | 85 | 0 | 10 | 166
41991 | 2023-02-23 | 2023-05-26 | 2023-07-12 | 2023-07-12 | COMP | 2023-07-26 | COMP | 2023-10-17 | COMP | 2023-12-14 | COMP | 2023-12-29 | COMP | Rule 16 | 67 | 31 | 11 | 59 | 40 | 11 | 214
42009 | 2023-05-17 | 2023-05-30 | 2023-07-25 | 2023-07-25 | COMP | 2023-07-27 | COMP | 2023-07-31 | COMP | 2023-07-26 | COMP | 2023-09-27 | COMP | Rule 16 | 9 | 39 | 3 | 3 | 0 | 42 | 92
42208 | 2023-04-24 | 2023-07-03 | 2023-07-26 | 2023-07-26 | COMP | 2023-08-01 | NOTN | 2023-08-01 | COMP | 2023-10-17 | COMP | 2023-12-15 | COMP | Other | 49 | 17 |  | 5 | 55 | 41 | 163
42265 | 2023-03-24 | 2023-07-14 | 2023-08-12 | 2023-08-12 | COMP | 2023-09-12 | COMP | 2023-09-12 | COMP | 2023-11-13 | COMP | 2023-12-11 | COMP | Rule 16 | 78 | 21 | 21 | 1 | 44 | 19 | 180
42298 | 2023-03-30 | 2023-07-25 | 2023-09-25 | 2023-09-25 | COMP | 2023-10-10 | COMP | 2023-10-10 | COMP | 2023-07-17 | COMP | 2023-12-07 | COMP | Rule 16 | 81 | 44 | 12 | 1 | 0 | 40 | 174
42313 | 2023-06-20 | 2023-07-27 | 2023-09-19 | 2023-09-19 | COMP | 2023-09-27 | COMP | 2023-09-27 | COMP | 2023-10-16 | COMP | 2023-11-27 | COMP | Rule 16 | 27 | 38 | 7 | 1 | 14 | 28 | 110
42322 | 2023-05-02 | 2023-07-31 | 2023-08-08 | 2023-08-08 | COMP | 2023-10-04 | COMP | 2023-10-04 | COMP |  | INPR | 2023-12-04 | COMP | Rule 16 | 62 | 7 | 41 | 1 |  |  | 148
42341 | 2023-07-10 | 2023-08-04 | 2023-08-24 | 2023-08-25 | COMP | 2023-11-02 | COMP | 2023-11-02 | COMP | 2023-11-09 | COMP | 2023-11-24 | COMP | Rule 16 | 20 | 15 | 49 | 1 | 6 | 9 | 96
42352 | 2023-04-04 | 2023-08-09 | 2023-09-02 | 2023-09-02 | COMP | 2023-09-12 | COMP | 2023-10-20 | COMP | 2023-11-27 | COMP | 2023-12-15 | COMP | Rule 16 | 89 | 18 | 6 | 29 | 24 | 15 | 177
42368 | 2023-06-30 | 2023-08-13 | 2023-09-12 | 2023-09-12 | COMP | 2023-10-05 | COMP | 2023-10-16 | COMP | 2023-12-04 | COMP | 2023-12-29 | COMP | Rule 16 | 30 | 21 | 18 | 8 | 33 | 19 | 125
42380 | 2023-03-16 | 2023-08-15 | 2023-08-24 | 2023-08-24 | COMP | 2023-08-31 | COMP | 2023-08-31 | COMP | 2023-09-14 | COMP | 2023-10-11 | COMP | Rule 16 | 106 | 8 | 6 | 1 | 10 | 20 | 146
42422 | 2023-04-07 | 2023-08-31 | 2023-10-05 | 2023-10-05 | COMP | 2023-10-12 | COMP | 2023-10-18 | COMP | 2023-10-20 | COMP | 2023-11-20 | COMP | Rule 16 | 102 | 25 | 6 | 5 | 3 | 21 | 157
42451 | 2023-06-19 | 2023-09-20 | 2023-10-17 | 2023-10-17 | COMP | 2023-10-20 | COMP | 2023-10-20 | COMP | 2023-10-25 | COMP | 2023-11-27 | COMP | Rule 16 | 65 | 20 | 4 | 1 | 4 | 21 | 110
42455 | 2023-05-30 | 2023-09-21 | 2023-10-11 | 2023-10-11 | COMP | 2023-10-17 | COMP | 2023-10-17 | COMP | 2023-12-06 | COMP | 2023-12-20 | COMP | Rule 16 | 80 | 15 | 5 | 1 | 34 | 11 | 141
42475 | 2023-06-06 | 2023-10-23 | 2023-11-20 | 2023-11-20 | COMP | 2023-11-29 | COMP | 2023-11-29 | COMP | 2023-12-07 | COMP | 2023-12-19 | COMP | Rule 16 | 97 | 20 | 6 | 1 | 7 | 9 | 135

## Response to Question 3
Table A1 Energization Timelines by Upstream Distribution Capacity Upgrade Type (Calendar Days) |  |  |  |  | Table B1 Energization Timelines by Upstream Distribution Capacity Upgrade Type (Business Days)
Upstream Distribution Capacity Upgrade Type | Average (day) | Median (day) | Standard Deviation (day) | Percentage of Instances Upgrade Type is Triggered by an Energization request | Upstream Distribution Capacity Upgrade Type | Average (day) | Median (day) | Standard Deviation (day)
Substation Updates | 1020.6667 | 759 | 600.8696 | 28.57% | Substation Updates | 785 | 562 | 488.3124
Line/Circuit Updates | 683.8108 | 646 | 542.352 | 53.12% | Line/Circuit Updates | 489.4054 | 463 | 387.4012
New Substations | N/A | N/A | N/A | N/A | New Substations | N/A | N/A | N/A
Table A2 Pre Funding Durations- incl 2024 data (Calendar Days) |  |  |  |  | Table B2 Pre Funding Durations -incl 2024 data (Business Days)
Upstream Distribution Capacity Upgrade Type | Average (day) | Median (day) | STDEV ADD |  | Upstream Distribution Capacity Upgrade Type | Average (day) | Median (day) | STDEV ADD
Substation Updates*(2024) | 469.05 | 473.5 | 372.047 |  | Substation Updates*(2024) | 336.05 | 339.5 | 265.9366
Line/Circuit Updates | 317.5135 | 85 | 394.3938 |  | Line/Circuit Updates | 227.7568 | 62 | 281.6501