## Assumptions
PYD Extension Project Assumptions
1. | Sites consist of approximately 10 ports each, total program consists of 2,000 ports; plus 1 testing/training site
2. | For cost estimate purposes, workplace sites consist of 78% Lots, 22% Structures (PYD Pilot Data)
3. | For cost estimate purposes, MUD sites consist of 66% Lots, 34% Structures (PYD Pilot Data)
4. | Sites consist of 75% Workplaces, 25% MUDs (Assumption)
5. | SDG&E ownership of EVSEs at all multi-unit dwelling sites (MUDs), assumes 50 sites / 500 ports
6. | Customer ownership at workplace sites, assumes 150 sites / 1,500 ports
7. | Direct Costs used per site: $140K Lot, $160K Structure (utility-owned), and $104K Lot, $124K Structure (customer-owned) - PYD Pilot Data
8. | Assumes EVSE per port costs to be $3K
9. | $2K/site for high side connection
10. | $2K/site for standby costs
11. PYD Pilot actual site costs used as the basis for PYD Extension construction site estimates | $5K per site of construction change order funding is included in estimates

## Summary Table
| Capital |  |  |  | Capital | O&M |  |  |  | O&M | Total |  |  |  | Combined
| 2021 | 2022 | 2023 | 2024 | Total | 2021 | 2022 | 2023 | 2024 | Total | 2021 | 2022 | 2023 | 2024 | Total | Comments
Program Implementation
Engineering Design & Construction | 3141733.4773 | 16558928.4165 | 5586330.7821 | 0 | 25286992.676 | 97727.2727 | 268181.8182 | 134090.9091 | 0 | 500000 | 3239460.7501 | 16827110.2347 | 5720421.6912 | 0 | 25786992.676 | Includes engineering design, construction, and SDG&E field employee labor
EV Charging Equipment & Other Program Materials | 487231.4349 | 2932299.6536 | 471476.2354 | 0 | 3891007.324 | 0 | 0 | 0 | 0 | 0 | 487231.4349 | 2932299.6536 | 471476.2354 | 0 | 3891007.324 | Includes transformers, freight, meter pedestals, EVSEs, misc. materials
Program Management | 509571.4286 | 857142.8571 | 476785.7143 | 0 | 1843500 | 0 | 0 | 0 | 0 | 0 | 509571.4286 | 857142.8571 | 476785.7143 | 0 | 1843500 | Includes 3rd Party P6 Scheduler and internal SDG&E Project Management Labor
EVSE Rebates & Rebate Administration | 0 | 0 | 0 | 0 | 0 | 12600 | 2278112.1212 | 2449287.8788 | 0 | 4740000 | 12600 | 2278112.1212 | 2449287.8788 | 0 | 4740000 | ($3K x 100% Workplace @ 1,500 ports) = $4,500,000
Data Collection, Analysis & Reporting | 0 | 0 | 0 | 0 | 0 | 42000 | 72000 | 36000 | 0 | 150000 | 42000 | 72000 | 36000 | 0 | 150000
Marketing, Education & Outreach (ME&O) | 0 | 0 | 0 | 0 | 0 | 130000 | 136000 | 18000 | 0 | 284000 | 130000 | 136000 | 18000 | 0 | 284000
Contingency on Unescalated Direct Costs | 0 | 0 | 3669550 | 0 | 3669550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3669550 | 0 | 3669550 | Contingency was calculated based on 10% of unescalated total directs plus indirects (Cap. & O&M); entire amount was allocated to capital for calculations of escalation, AFUDC, capitalized property taxes, & Rev. Req.
Unescalated Direct Costs Subtotal | 4138536.3409 | 20348370.9273 | 10204142.7318 | 0 | 34691050 | 282327.2727 | 2754293.9394 | 2637378.7879 | 0 | 5674000 | 4420863.6136 | 23102664.8667 | 12841521.5197 | 0 | 40365050
Overhead Costs | 1109274.6379 | 2864805.9161 | 1255069.1853 | 0 | 5229149.7392 | 106179.7488 | 351761.3452 | 265492.328 | 0 | 723433.422 | 1215454.3867 | 3216567.2613 | 1520561.5132 | 0 | 5952583.1612
Contingency on Unescalated Overhead Costs |  |  | 595258.3161 |  | 595258.3161 |  |  |  |  | 0 | 0 | 0 | 595258.3161 | 0 | 595258.3161 | Contingency was calculated based on 10% of unescalated total directs plus indirects (Cap. & O&M); entire amount was allocated to capital for calculations of escalation, AFUDC, capitalized property taxes, & Rev. Req.
Unescalated Overhead Costs Subtotal | 1109274.6379 | 2864805.9161 | 1850327.5014 | 0 | 5824408.0553 | 106179.7488 | 351761.3452 | 265492.328 | 0 | 723433.422 | 1215454.3867 | 3216567.2613 | 2115819.8293 | 0 | 6547841.4773
Total Unescalated Direct & Overhead Costs | 5247810.9788 | 23213176.8434 | 12054470.2332 | 0 | 40515458.0553 | 388507.0215 | 3106055.2846 | 2902871.1158 | 0 | 6397433.422 | 5636318.0003 | 26319232.128 | 14957341.3491 | 0 | 46912891.4773
Escalation | 376714.324 | 2385992.5569 | 1621390.7383 | 0 | 4384097.6192 | 50708.9607 | 359606.464 | 238289.9684 | 0 | 648605.393 | 427423.2847 | 2745599.0209 | 1859680.7067 | 0 | 5032703.0122
Property Taxes | 17116.4813 | 46885.9269 | 12018.2122 | 0 | 76020.6205 | 0 | 0 | 0 | 0 | 0 | 17116.4813 | 46885.9269 | 12018.2122 | 0 | 76020.6205
AFUDC | 122445.5639 | 292770.7762 | 71001.2036 | 0 | 486217.5437 | 0 | 0 | 0 | 0 | 0 | 122445.5639 | 292770.7762 | 71001.2036 | 0 | 486217.5437
Total Program Implementation | 5764087.348 | 25938826.1033 | 13758880.3874 | 0 | 45461793.8387 | 439215.9822 | 3465661.7486 | 3141161.0842 | 0 | 7046038.815 | 6203303.3302 | 29404487.852 | 16900041.4716 | 0 | 52507832.6537
Ongoing O&M (39 month total) | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Direct Costs | 0 | 0 | 0 | 0 | 0 | 265842.9757 | 811231.9028 | 908381.4818 | 874014.6397 | 2859471 | 265842.9757 | 811231.9028 | 908381.4818 | 874014.6397 | 2859471
Contingency on Directs |  |  |  |  | 0 | 26584.2976 | 81123.1903 | 90838.1482 | 87401.464 | 285947.1 | 26584.2976 | 81123.1903 | 90838.1482 | 87401.464 | 285947.1
Unescalated Direct Costs Subtotal | 0 | 0 | 0 | 0 | 0 | 292427.2733 | 892355.0931 | 999219.63 | 961416.1036 | 3145418.1 | 292427.2733 | 892355.0931 | 999219.63 | 961416.1036 | 3145418.1
Overhead Costs | 0 | 0 | 0 | 0 | 0 | 186886.1583 | 670352.2987 | 635240.3174 | 609706.8233 | 2102185.5977 | 186886.1583 | 670352.2987 | 635240.3174 | 609706.8233 | 2102185.5977
Contingency on Unescalated Overhead Costs |  |  |  |  | 0 | 18688.6158 | 67035.2299 | 63524.0317 | 60970.6823 | 210218.5598 | 18688.6158 | 67035.2299 | 63524.0317 | 60970.6823 | 210218.5598
Unescalated Overhead Costs Subtotal | 0 | 0 | 0 | 0 | 0 | 205574.7742 | 737387.5285 | 698764.3491 | 670677.5056 | 2312404.1574 | 205574.7742 | 737387.5285 | 698764.3491 | 670677.5056 | 2312404.1574
Total Unescalated Direct & Overhead Costs | 0 | 0 | 0 | 0 | 0 | 498002.0475 | 1629742.6217 | 1697983.9791 | 1632093.6093 | 5457822.2574 | 498002.0475 | 1629742.6217 | 1697983.9791 | 1632093.6093 | 5457822.2574
Escalation |  |  |  |  | 0 | 0 | 0 | 223563 | 243273 | 466836 | 0 | 0 | 223563 | 243273 | 466836
Total Ongoing O&M | 0 | 0 | 0 | 0 | 0 | 498002.0475 | 1629742.6217 | 1921546.9791 | 1875366.6093 | 5924658.2574 | 498002.0475 | 1629742.6217 | 1921546.9791 | 1875366.6093 | 5924658.2574
Total Requested | 5764087.348 | 25938826.1033 | 13758880.3874 | 0 | 45461793.8387 | 937218.0296 | 5095404.3703 | 5062708.0633 | 1875366.6093 | 12970697.0724 | 6701305.3776 | 31034230.4736 | 18821588.4507 | 1875366.6093 | 58432490.9112
Implementation Capital and O&M
Unescalated, no contingency | [14 empty] | 43210321.3254
Per Port | [14 empty] | 21605.1607
Unescalated, with contingency | [14 empty] | 47475129.6415
Per Port | [14 empty] | 23737.5648
Escalated, with contingency | [14 empty] | 52507832.6537
Per Port | [14 empty] | 26253.9163

## Cost Estimate By Month
|  | Capital |  |  |  |  | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | Capital | O&M |  |  |  |  | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M | O&M
Program Phase |  | EAC | 2021 | 2022 | 2023 | 2024 | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | EAC | 2021 | 2022 | 2023 | 2024 | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024
Cost to Implement | Direct Costs | 31021500 | 4138536.3409 | 20348370.9273 | 6534592.7318 | 0 | 126666.6667 | 126666.6667 | 181666.6667 | 181666.6667 | 181666.6667 | 181666.6667 | 255261.9048 | 255261.9048 | 290919.7995 | 328364.2439 | 712364.2439 | 1316364.2439 | 1432364.2439 | 1420364.2439 | 1336364.2439 | 1531564.2439 | 1779564.2439 | 1695564.2439 | 1744097.5773 | 1881697.5773 | 1902497.5773 | 1944097.5773 | 1798497.5773 | 1881697.5773 | 1902497.5773 | 1902497.5773 | 1440897.5773 | 713800 | 319400 | 137000 | 39500 | 39500 | 39500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5674000 | 282327.2727 | 2754293.9394 | 2637378.7879 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 9000 | 29833.3333 | 29833.3333 | 48015.1515 | 52215.1515 | 52215.1515 | 52215.1515 | 57770.7071 | 57770.7071 | 57770.7071 | 250627.8499 | 250627.8499 | 250627.8499 | 233961.1833 | 238670.2742 | 238670.2742 | 238670.2742 | 439563.1313 | 439563.1313 | 439563.1313 | 439563.1313 | 439563.1313 | 439563.1313 | 439563.1313 | 439563.1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Direct Labor | 3031500 | 890571.4286 | 1349142.8571 | 791785.7143 | 0 | 0 | 0 | 55000 | 55000 | 55000 | 55000 | 103595.2381 | 103595.2381 | 126095.2381 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112428.5714 | 112000 | 112000 | 112000 | 39500 | 39500 | 39500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474000 | 109600 | 231945.4545 | 132454.5455 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 9000 | 13166.6667 | 13166.6667 | 13166.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 17366.6667 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 22075.7576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Back Office Support Ext Implementation - E-920.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 25000 | 50000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | EVSE Rebates - E-986.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 12600 | 73945.4545 | 53454.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 8909.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Data Collection, Analysis, & Reporting Ext Implementation - E-598.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 42000 | 72000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Eng Design and Construction Ext Implementation - E-398.20 | 1738000 | 481000 | 792000 | 465000 | 0 | 0 | 0 | 32500 | 32500 | 32500 | 32500 | 43500 | 43500 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 66000 | 23000 | 23000 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | IT Vendor Acceptance Ext Implementation - E-398.20 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | ME&O Execution Ext Implementation - E-908.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84000 | 30000 | 36000 | 18000 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Program Management Ext Implementation - E-398.20 | 1243500 | 359571.4286 | 557142.8571 | 326785.7143 | 0 | 0 | 0 | 22500 | 22500 | 22500 | 22500 | 43428.5714 | 43428.5714 | 43428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46428.5714 | 46000 | 46000 | 46000 | 16500 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Non-Labor | 27990000 | 3247964.9123 | 18999228.0702 | 5742807.0175 | 0 | 126666.6667 | 126666.6667 | 126666.6667 | 126666.6667 | 126666.6667 | 126666.6667 | 151666.6667 | 151666.6667 | 164824.5614 | 215935.6725 | 599935.6725 | 1203935.6725 | 1319935.6725 | 1307935.6725 | 1223935.6725 | 1419135.6725 | 1667135.6725 | 1583135.6725 | 1631669.0058 | 1769269.0058 | 1790069.0058 | 1831669.0058 | 1686069.0058 | 1769269.0058 | 1790069.0058 | 1790069.0058 | 1328469.0058 | 601800 | 207400 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 172727.2727 | 2522348.4848 | 2504924.2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 34848.4848 | 34848.4848 | 34848.4848 | 34848.4848 | 40404.0404 | 40404.0404 | 40404.0404 | 233261.1833 | 233261.1833 | 233261.1833 | 216594.5166 | 216594.5166 | 216594.5166 | 216594.5166 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Services | 24098992.676 | 2760733.4773 | 16066928.4165 | 5271330.7821 | 0 | 126666.6667 | 126666.6667 | 126666.6667 | 126666.6667 | 126666.6667 | 126666.6667 | 151666.6667 | 151666.6667 | 151666.6667 | 186377.7818 | 463777.8138 | 895577.8818 | 978777.8938 | 974977.8738 | 915577.8618 | 1070777.8394 | 1331977.6234 | 1216977.3314 | 1472310.4575 | 1621110.3071 | 1640110.2959 | 1678110.2735 | 1545110.3519 | 1621110.3071 | 1640110.2959 | 1640110.2959 | 1218110.5399 | 554999.7304 | 192999.92 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200000 | 172727.2727 | 2522348.4848 | 2504924.2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 34848.4848 | 34848.4848 | 34848.4848 | 34848.4848 | 40404.0404 | 40404.0404 | 40404.0404 | 233261.1833 | 233261.1833 | 233261.1833 | 216594.5166 | 216594.5166 | 216594.5166 | 216594.5166 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 417487.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6220600 - SRV-CONSULTING-OTHER | 600000 | 150000 | 300000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 66666.6667 | 33333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 5555.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6220006 - SRV-CONSTRUCTION SERVICES DEPT ONLY | 804003.312 | 42399.568 | 569602.0784 | 192001.6656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1599.988 | 11999.892 | 28799.688 | 31999.652 | 31199.712 | 28799.748 | 35199.7152 | 46399.8632 | 42400.2392 | 53600.3888 | 60000.552 | 60800.5616 | 62400.5808 | 56800.5136 | 60000.552 | 60800.5616 | 60800.5616 | 43200.3616 | 20800.1488 | 6400.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6220480 - SRV-ENGINEERING | 3000000 | 1333333.3333 | 1333333.3333 | 333333.3333 | 0 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 111111.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6221000 - SRV-CONSTRUCTION-ELECTRIC | 19494989.364 | 1075000.576 | 13823993.0048 | 4595995.7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000.016 | 309000.144 | 724000.416 | 804000.464 | 801000.384 | 744000.336 | 892800.3464 | 1142799.9824 | 1031799.3144 | 1282598.9576 | 1424998.644 | 1443198.6232 | 1479598.5816 | 1352198.7272 | 1424998.644 | 1443198.6232 | 1443198.6232 | 1038799.0672 | 509199.5816 | 161599.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6220050 - SRV-ADVERTISING AND MARKETING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 16666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6220052 - REBATES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 2137500 | 2362500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192857.1429 | 192857.1429 | 192857.1429 | 192857.1429 | 192857.1429 | 192857.1429 | 192857.1429 | 393750 | 393750 | 393750 | 393750 | 393750 | 393750 | 393750 | 393750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6220570 - SRV-DESIGN | 200000 | 160000 | 40000 | 0 | 0 | 15555.5556 | 15555.5556 | 15555.5556 | 15555.5556 | 15555.5556 | 15555.5556 | 15555.5556 | 15555.5556 | 15555.5556 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 6666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6231022 - SERVICES-ENVIROMENTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 72727.2727 | 218181.8182 | 109090.9091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 18181.8182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Materials | 3891007.324 | 487231.4349 | 2932299.6536 | 471476.2354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13157.8947 | 29557.8907 | 136157.8587 | 308357.7907 | 341157.7787 | 332957.7987 | 308357.8107 | 348357.8331 | 335158.0491 | 366158.3411 | 159358.5483 | 148158.6987 | 149958.7099 | 153558.7323 | 140958.6539 | 148158.6987 | 149958.7099 | 149958.7099 | 110358.4659 | 46800.2696 | 14400.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6215070 - MATL ISSUANCES-KEARNY WAREHOUSE | 1005001.292 | 52999.712 | 712000.6944 | 240000.8856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1999.992 | 14999.928 | 35999.792 | 39999.768 | 38999.808 | 35999.832 | 43999.8072 | 57999.8912 | 53000.1272 | 67000.2008 | 75000.252 | 76000.2536 | 78000.2568 | 71000.2456 | 75000.252 | 76000.2536 | 76000.2536 | 54000.2096 | 26000.1208 | 8000.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6213090 - MATL-FREIGHT | 102001.36 | 21200.288 | 80801.072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800.008 | 6000.072 | 14400.208 | 16000.232 | 15600.192 | 14400.168 | 16000.208 | 13600.2 | 3600.04 | 1600.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6213222 - MATL-UNDERGROUND TRANSFORMERS | 250000 | 52631.5789 | 157894.7368 | 39473.6842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 13157.8947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6213225 - MATL-ELECTRICAL EQUIPMENT | 1530001.36 | 318000.288 | 1212001.072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000.008 | 90000.072 | 216000.208 | 240000.232 | 234000.192 | 216000.168 | 240000.208 | 204000.2 | 54000.04 | 24000.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | 6213385 - MATL-ELEC MATERIAL MISCELLANEOUS | 1004003.312 | 42399.568 | 769602.0784 | 192001.6656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1599.988 | 11999.892 | 28799.688 | 31999.652 | 31199.712 | 28799.748 | 35199.7152 | 46399.8632 | 242400.2392 | 53600.3888 | 60000.552 | 60800.5616 | 62400.5808 | 56800.5136 | 60000.552 | 60800.5616 | 60800.5616 | 43200.3616 | 20800.1488 | 6400.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Non Direct Costs | 5791387.9034 | 1248836.6831 | 3204462.6191 | 1338088.6011 | 0 | 7627.2346 | 8672.619 | 65420.7331 | 67341.1807 | 69274.0344 | 71220.9098 | 123898.3457 | 126841.2403 | 153380.9969 | 146795.153 | 179060.8797 | 229303.3558 | 241302.2661 | 240899.8072 | 234517.8659 | 249659.2601 | 272160.7282 | 300519.1713 | 272933.2502 | 283394.0452 | 283103.9811 | 283931.8989 | 268987.3291 | 273053.0159 | 273371.424 | 272946.4276 | 233461.5361 | 172715.46 | 135751.2863 | 118161.984 | 43863.5401 | 43894.0957 | 43922.8473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723433.422 | 106179.7488 | 351761.3452 | 265492.328 | 0 | 0 | 0 | 2863.65 | 2863.65 | 2863.65 | 8590.95 | 12656.4237 | 12656.4237 | 12752.6222 | 16977.4598 | 16977.4598 | 16977.4598 | 17292.2076 | 17292.2076 | 17292.2076 | 28218.4558 | 28218.4558 | 28218.4558 | 28130.2738 | 32867.2128 | 32867.2128 | 32867.2128 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | All Indirects | 5229149.7392 | 1109274.6379 | 2864805.9161 | 1255069.1853 | 0 | 7176.2519 | 7176.2519 | 62501.5054 | 62501.5054 | 62501.5054 | 62501.5054 | 112800.4866 | 112800.4866 | 136179.0004 | 126437.5515 | 155410.2413 | 201288.3463 | 210080.9913 | 208845.9859 | 202421.4709 | 217921.8911 | 239744.8619 | 268210.1614 | 242732.4217 | 254969.6264 | 256703.2285 | 260170.4326 | 248035.2181 | 254969.6264 | 256703.2285 | 256703.2285 | 218337.3662 | 161191.9051 | 128853.9837 | 114078.6999 | 39733.5912 | 39733.5912 | 39733.5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 723433.422 | 106179.7488 | 351761.3452 | 265492.328 | 0 | 0 | 0 | 2863.65 | 2863.65 | 2863.65 | 8590.95 | 12656.4237 | 12656.4237 | 12752.6222 | 16977.4598 | 16977.4598 | 16977.4598 | 17292.2076 | 17292.2076 | 17292.2076 | 28218.4558 | 28218.4558 | 28218.4558 | 28130.2738 | 32867.2128 | 32867.2128 | 32867.2128 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 44248.7213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | All Property Tax | 76020.6205 | 17116.4813 | 46885.9269 | 12018.2122 | 0 | 0 | 141.1137 | 283.2526 | 542.7407 | 804.112 | 1067.3788 | 1332.5547 | 1730.2782 | 2130.8875 | 2596.6453 | 2975.3734 | 3512.1445 | 4177.6908 | 4312.2002 | 4399.3505 | 4298.8048 | 4318.5921 | 4503.847 | 4226.0895 | 3928.5851 | 3759.1371 | 3346.3373 | 3060.8488 | 2554.4438 | 2319.5082 | 2182.4206 | 2228.0752 | 1817.9641 | 1230.1053 | 552.5764 | 558.3422 | 562.6097 | 566.6107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Non Direct Costs AFUDC | 486217.5437 | 122445.5639 | 292770.7762 | 71001.2036 | 0 | 450.9828 | 1355.2534 | 2635.9751 | 4296.9347 | 5968.417 | 7652.0257 | 9765.3044 | 12310.4755 | 15071.109 | 17760.9563 | 20675.265 | 24502.8651 | 27043.584 | 27741.6211 | 27697.0445 | 27438.5642 | 28097.2743 | 27805.1629 | 25974.739 | 24495.8337 | 22641.6156 | 20415.129 | 17891.2622 | 15528.9457 | 14348.6873 | 14060.7786 | 12896.0948 | 9705.5908 | 5667.1973 | 3530.7076 | 3571.6068 | 3597.8949 | 3622.6455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | All Cost Elements wo Contingency - Unescalated | 36812887.9034 | 5387373.024 | 23552833.5464 | 7872681.333 | 0 | 134293.9013 | 135339.2857 | 247087.3997 | 249007.8474 | 250940.7011 | 252887.5765 | 379160.2504 | 382103.1451 | 444300.7964 | 475159.397 | 891425.1236 | 1545667.5998 | 1673666.51 | 1661264.0511 | 1570882.1099 | 1781223.504 | 2051724.9722 | 1996083.4152 | 2017030.8274 | 2165091.6225 | 2185601.5584 | 2228029.4762 | 2067484.9064 | 2154750.5931 | 2175869.0012 | 2175444.0049 | 1674359.1134 | 886515.46 | 455151.2863 | 255161.984 | 83363.5401 | 83394.0957 | 83422.8473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397433.422 | 388507.0215 | 3106055.2846 | 2902871.1158 | 0 | 0 | 0 | 5863.65 | 5863.65 | 5863.65 | 17590.95 | 42489.757 | 42489.757 | 60767.7737 | 69192.6113 | 69192.6113 | 69192.6113 | 75062.9147 | 75062.9147 | 75062.9147 | 278846.3057 | 278846.3057 | 278846.3057 | 262091.457 | 271537.487 | 271537.487 | 271537.487 | 483811.8526 | 483811.8526 | 483811.8526 | 483811.8526 | 483811.8526 | 483811.8526 | 483811.8526 | 483811.8526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Contingency | 4264808.3161 | 0 | 0 | 4264808.3161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4264808.3161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | Escalation | 4384097.6192 | 376714.324 | 2385992.5569 | 1621390.7383 | 0 | 9607.9193 | 9607.9193 | 17527.6221 | 17527.6221 | 17527.6221 | 17527.6221 | 26421.3737 | 26421.3737 | 30659.3047 | 32647.9653 | 62293.2266 | 108944.7528 | 168820.5855 | 167460.2106 | 158165.8248 | 179822.9051 | 207556.9634 | 201848.7666 | 204218.5618 | 219619.7478 | 221935.8895 | 226568.1729 | 210355.181 | 219619.7478 | 290424.0601 | 290424.0601 | 223175.9768 | 117691.0924 | 60292.559 | 33771.4284 | 10657.3419 | 10657.3419 | 10657.3419 | 573639.5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648605.393 | 50708.9607 | 359606.464 | 238289.9684 | 0 | 0 | 0 | 387.6439 | 387.6439 | 387.6439 | 1162.9318 | 2358.7028 | 2358.7028 | 7942.0577 | 11122.3786 | 11122.3786 | 13478.8766 | 17476.5063 | 17476.5063 | 17476.5063 | 30102.4783 | 30102.4783 | 30102.4783 | 29079.7071 | 29987.2517 | 29987.2517 | 29987.2517 | 43139.3058 | 54688.7425 | 58885.9318 | 58885.9318 | 58885.9318 | 58885.9318 | 2746.2411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost to Implement | All Implementation Costs - Escalated | 45461793.8387 | 5764087.348 | 25938826.1033 | 13758880.3874 | 0 | 143901.8206 | 144947.205 | 264615.0219 | 266535.4695 | 268468.3232 | 270415.1986 | 405581.6241 | 408524.5188 | 474960.1011 | 507807.3623 | 953718.3502 | 1654612.3525 | 1842487.0956 | 1828724.2617 | 1729047.9347 | 1961046.4091 | 2259281.9356 | 2197932.1818 | 2221249.3892 | 2384711.3703 | 2407537.4479 | 2454597.6491 | 2277840.0875 | 2374370.341 | 2466293.0613 | 2465868.065 | 1897535.0902 | 1004206.5524 | 515443.8452 | 288933.4124 | 94020.882 | 94051.4376 | 94080.1892 | 4838447.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7046038.815 | 439215.9822 | 3465661.7486 | 3141161.0842 | 0 | 0 | 0 | 6251.2939 | 6251.2939 | 6251.2939 | 18753.8818 | 44848.4598 | 44848.4598 | 68709.8314 | 80314.9899 | 80314.9899 | 82671.4878 | 92539.421 | 92539.421 | 92539.421 | 308948.784 | 308948.784 | 308948.784 | 291171.1641 | 301524.7387 | 301524.7387 | 301524.7387 | 526951.1584 | 538500.5951 | 542697.7844 | 542697.7844 | 542697.7844 | 542697.7844 | 486558.0938 | 483811.8526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extension Maintenance | Direct Costs | Not Applicable to Capital, See O&M Section | [52 empty] | 2859471 | 265842.9757 | 811231.9028 | 908381.4818 | 874014.6397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100535 | 55102.6586 | 55102.6586 | 55102.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 71769.3252 | 71769.3252 | 71769.3252 | 71769.3252 | 82295.641 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533
Extension Maintenance | Back Office Support Ext - E-920.00 | [53 empty] | 479941 | 36918.5385 | 147674.1538 | 147674.1538 | 147674.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795
Extension Maintenance | Equipment, Facilities, & Testing Ext - E-588.00 | [53 empty] | 100535 | 100535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extension Maintenance | Field, Shop, & Logistics Labor Ext - E-588.00 | [53 empty] | 713364 | 54874.1538 | 219496.6154 | 219496.6154 | 219496.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846
Extension Maintenance | Meter Technical/Eng Support Ext - E-920.00 | [53 empty] | 349131 | 34594.2308 | 138376.9231 | 101315.9757 | 74843.8704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892
Extension Maintenance | Billing & Rebates Ext - E-908.00 | [53 empty] | 253500 | 19500 | 78000 | 78000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500
Extension Maintenance | Call Center (Customer Care) Ext - E-908.00 | [53 empty] | 253500 | 19500 | 78000 | 78000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500
Extension Maintenance | Cust Ops Support Ext - E-908.00 | [53 empty] | 253500 | 19500 | 78000 | 78000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500
Extension Maintenance | ME&O (utilitzation) - E-908.00 | [53 empty] | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extension Maintenance | Participation Payments - E-986.00 | [53 empty] | -200000 | -31578.9474 | -126315.7895 | -42105.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Extension Maintenance | Data Maintenance Fees - E-920.00 | [53 empty] | 450000 | 0 | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500
Extension Maintenance | IT Maint Support - E-920.00 | [53 empty] | 156000 | 12000 | 48000 | 48000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Extension Maintenance | Indirect Costs | Not Applicable to Capital, See O&M Section | [52 empty] | 2102185.5977 | 186886.1583 | 670352.2987 | 635240.3174 | 609706.8233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19496.4932 | 55796.5551 | 55796.5551 | 55796.5551 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55884.7371 | 55884.7371 | 55884.7371 | 55884.7371 | 55884.7371 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019
Extension Maintenance | All Cost Elements wo Contingency - Unescalated | [53 empty] | 4961656.5977 | 452729.134 | 1481584.2015 | 1543621.7991 | 1483721.463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120031.4932 | 110899.2136 | 110899.2136 | 110899.2136 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 127654.0623 | 127654.0623 | 127654.0623 | 127654.0623 | 138180.3781 | 127832.1674 | 127832.1674 | 127832.1674 | 127832.1674 | 127832.1674 | 127832.1674 | 127832.1674 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552 | 123643.4552
Extension Maintenance | Contingency | [53 empty] | 496165.6598 | 45272.9134 | 148158.4202 | 154362.1799 | 148372.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45272.9134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148158.4202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154362.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148372.1463
Extension Maintenance | Escalation | [53 empty] | 466836 | 0 | 0 | 223563 | 243273 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 57026 | 58458 | 15320 | 15320 | 15320 | 15320 | 15320 | 31479 | 18644 | 18644 | 18644 | 18644 | 18644 | 18644 | 18644 | 18644 | 18644 | 18644 | 18644 | 38189
Extension Maintenance | All Maintenance Costs - Escalated | [53 empty] | 5924658.2574 | 498002.0475 | 1629742.6217 | 1921546.9791 | 1875366.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120031.4932 | 110899.2136 | 110899.2136 | 156172.127 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 123465.3501 | 271623.7703 | 127654.0623 | 127654.0623 | 127654.0623 | 127654.0623 | 195206.3781 | 186290.1674 | 143152.1674 | 143152.1674 | 143152.1674 | 143152.1674 | 143152.1674 | 313673.3473 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 310204.6015
Total Program Costs | Fully Loaded and Escalated Program Costs, Including Contingency | 45461793.8387 | 5764087.348 | 25938826.1033 | 13758880.3874 | 0 | 143901.8206 | 144947.205 | 264615.0219 | 266535.4695 | 268468.3232 | 270415.1986 | 405581.6241 | 408524.5188 | 474960.1011 | 507807.3623 | 953718.3502 | 1654612.3525 | 1842487.0956 | 1828724.2617 | 1729047.9347 | 1961046.4091 | 2259281.9356 | 2197932.1818 | 2221249.3892 | 2384711.3703 | 2407537.4479 | 2454597.6491 | 2277840.0875 | 2374370.341 | 2466293.0613 | 2465868.065 | 1897535.0902 | 1004206.5524 | 515443.8452 | 288933.4124 | 94020.882 | 94051.4376 | 94080.1892 | 4838447.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12970697.0724 | 937218.0296 | 5095404.3703 | 5062708.0633 | 1875366.6093 | 0 | 0 | 6251.2939 | 6251.2939 | 6251.2939 | 18753.8818 | 44848.4598 | 44848.4598 | 188741.3246 | 191214.2035 | 191214.2035 | 238843.6149 | 216004.7711 | 216004.7711 | 216004.7711 | 432414.1341 | 432414.1341 | 432414.1341 | 414636.5142 | 424990.0888 | 424990.0888 | 424990.0888 | 650416.5086 | 810124.3654 | 670351.8467 | 670351.8467 | 670351.8467 | 670351.8467 | 681764.4719 | 670102.0201 | 143152.1674 | 143152.1674 | 143152.1674 | 143152.1674 | 143152.1674 | 313673.3473 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 142287.4552 | 310204.6015
Note on C53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For modeling the revenue requirement, O&M escalation was applied to all implementation O&M and maintenance O&M costs together and split using a weighted average. For purposes of this file, O&M escalation was time-phased by applying escalation to the implementation O&M first, then to ongoing maintenance.

## Const. Site Cost Summary
Weighted Construction Site Direct Cost Estimates
Used to calculate values in Table 3-2
|  |  | Cost | Total
| Quantity |  | Each | Cost
Workplace Sites - Customer Owned (75% Total) | 150 | Sites
Lots: | 117 |  | 104000 | 12168000
Structures: | 33 |  | 124000 | 4092000
MUD Sites - Utility Owned (25% Total) | 50 | Sites
Lots: | 33 |  | 140000 | 4620000
Structures: | 17 |  | 160000 | 2720000
Total: | 200 | Sites |  | 23600000
Lots: | 150 |  |  | 16788000
Structures: | 50 |  |  | 6812000
Average Site Cost: |  |  |  | 118000
Testing & Training Site | 1 | Site | 140000 | 140000
Total: | 201 | Sites |  | 23740000
Overall Average Cost Per Site: |  |  |  | 118109.4527

## Const. Cost Breakdown-Site Type
Cost Element Breakdown by Site Type (rounded to nearest $100)
Customer Owned
10 Nozzle Lot Site | $
6220006 - SRV-CONSTRUCTION SERVICES DEPT ONLY | 4000
6221000 - SRV-CONSTRUCTION-ELECTRIC | 91000
6215070 - MATL ISSUANCES-KEARNY WAREHOUSE | 5000
6213385 - MATL-ELEC MATERIAL MISCELLANEOUS | 4000
Total Direct Costs | 104000
10 Nozzle Structure Site | $
6220006 - SRV-CONSTRUCTION SERVICES DEPT ONLY | 4000
6221000 - SRV-CONSTRUCTION-ELECTRIC | 111000
6215070 - MATL ISSUANCES-KEARNY WAREHOUSE | 5000
6213385 - MATL-ELEC MATERIAL MISCELLANEOUS | 4000
Total Direct Costs | 124000
Utility-Owned
10 Nozzle Lot Site | $
6220006 - SRV-CONSTRUCTION SERVICES DEPT ONLY | 4000
6221000 - SRV-CONSTRUCTION-ELECTRIC | 95000
6215070 - MATL ISSUANCES-KEARNY WAREHOUSE | 5000
6213090 - MATL-FREIGHT | 2000
6213225 - MATL-ELECTRICAL EQUIPMENT | 30000
6213385 - MATL-ELEC MATERIAL MISCELLANEOUS | 4000
Total Direct Costs | 140000
10 Nozzle Structure Site | $
6220006 - SRV-CONSTRUCTION SERVICES DEPT ONLY | 4000
6221000 - SRV-CONSTRUCTION-ELECTRIC | 115000
6215070 - MATL ISSUANCES-KEARNY WAREHOUSE | 5000
6213090 - MATL-FREIGHT | 2000
6213225 - MATL-ELECTRICAL EQUIPMENT | 30000
6213385 - MATL-ELEC MATERIAL MISCELLANEOUS | 4000
Total Direct Costs | 160000

## Monthly Site Construction
Site Description | Total Sites | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023
Utility-Owned: 10 Nozzle Parking Lot Site | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 6 | 5 | 4 | 5 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Utility-Owned: 10 Nozzle Structure Site | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer-Owned: 10 Nozzle Parking Lot Site | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 9 | 12 | 12 | 13 | 11 | 12 | 12 | 13 | 9 | 4 | 1
Customer Owned: 10 Nozzle Structure Site | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1
Total - All Site Types | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 8 | 8 | 7 | 8 | 12 | 10 | 13 | 15 | 15 | 16 | 14 | 15 | 15 | 16 | 12 | 6 | 2
Site Percent Complete |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.995% | 3.483% | 3.98% | 3.98% | 3.483% | 3.98% | 5.97% | 4.975% | 6.468% | 7.463% | 7.463% | 7.96% | 6.965% | 7.463% | 7.463% | 7.96% | 5.97% | 2.985% | 0.995%
Cumulative Percent Complete |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.995% | 4.478% | 8.458% | 12.44% | 15.92% | 19.9% | 25.87% | 30.85% | 37.31% | 44.78% | 52.24% | 60.2% | 67.16% | 74.63% | 82.09% | 90.05% | 96.02% | 99% | 100%

## Maintenance by Month
| O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M | O & M
Direct | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024
Extension Maintenance - Directs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100535 | 55102.6586 | 55102.6586 | 55102.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 67602.6586 | 71769.3252 | 71769.3252 | 71769.3252 | 71769.3252 | 82295.641 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 77001.22 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533 | 72834.5533
Cust Field Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100535 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 42128.9744 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533 | 36834.5533
Back Office Support Ext - E-920.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795 | 12306.1795
Equipment, Facilities, & Testing Ext - E-588.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Field, Shop, & Logistics Labor Ext - E-588.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846 | 18291.3846
Meter Technical/Eng Support Ext - E-920.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 11531.4103 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892 | 6236.9892
Customer Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 8973.6842 | 13140.3509 | 13140.3509 | 13140.3509 | 13140.3509 | 23666.6667 | 23666.6667 | 23666.6667 | 23666.6667 | 23666.6667 | 23666.6667 | 23666.6667 | 23666.6667 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500 | 19500
Billing & Rebates Ext - E-908.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500
Call Center (Customer Care) Ext - E-908.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500
Cust Ops Support Ext - E-908.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500 | 6500
ME&O (utilitzation) - E-908.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participation Payments - E-986.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | -10526.3158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT Data and Maintenance Support - E-920.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500
Data Maintenance Fees - E-920.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500
IT Maint Support - E-920.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Extension Maintenance - Indirects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19496.4932 | 55796.5551 | 55796.5551 | 55796.5551 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55862.6916 | 55884.7371 | 55884.7371 | 55884.7371 | 55884.7371 | 55884.7371 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50830.9474 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019 | 50808.9019

## Testimony Table 3-1
Table 3-1: PYD Extension Program Overall Site Construction Direct Cost Estimates
(In 2019$ )
Site Types | Cost Est.
Customer-Owned: 10 Nozzle Parking Lot Site | 104000
Customer Owned: 10 Nozzle Structure Site | 124000
Utility-Owned: 10 Nozzle Parking Lot Site | 140000
Utility-Owned: 10 Nozzle Structure Site | 160000

## Testimony Table 3-2
Table 3-2: PYD Extension Program Weighted Site Construction Direct Cost Estimate
(In 2019$ )
| Quantity | Cost Est. Each | Total Cost Est.
Workplace Sites Customer Owned (75%) | 150
Lots (78%) | 117 | 104000 | 12168000
Structures (22%) | 33 | 124000 | 4092000
`
MUD Sites Utility Owned (25%) | 50
Lots (66%) | 33 | 140000 | 4620000
Structures (34%) | 17 | 160000 | 2720000
Site Construction Subtotal: | 200 |  | 23600000
Testing and Training Site Construction: | 1 | 140000 | 140000
Site Construction Total: | 201 |  | 23740000
Average Cost Per Site: |  |  | 118109.4527

## Testimony Table 3-3
Table 3-3: PYD Extension Program Engineering, Design, Construction and EV Charging Equipment / Materials Cost Estimate
(In Millions, 2019$ )
| Capital | O&M | Total
Site Construction | 23.74
Engineering | 3.2
~ 10 FTE* Construction Internal Labor | 1.79
Transformers | 0.25 |  |  | `
Spares | 0.2
Misc. O&M |  | 0.5
Totals: | 29.18 | 0.5 | 29.68
* Full Time Equivalent

## Testimony Table 3-4
Table 3-4: PYD Extension Program Direct Cost Estimates by Category
(In Millions, 2019$ )
| Capital | O&M | Total
Engineering Design & Construction | 25.287 | 0.5 | 25.787
EV Charging Equip. & Pgm Matls | 3.891 | 0 | 3.891
Program Management | 1.8435 | 0 | 1.8435
EVSE Rebates & Administration | 0 | 4.74 | 4.74 | `
Data Collection, Analysis & Reporting | 0 | 0.15 | 0.15
Marketing, Education & Outreach | 0 | 0.284 | 0.284
Ongoing O&M | 0 | 2.8595 | 2.8595
Direct Costs Subtotal: | 31.0215 | 8.5335 | 39.555
Contingency: | 3.6696 | 0.28595 | 3.9555
Direct Cost Total: | 34.691 | 8.8194 | 43.5105

## Testimony Table 3-5, 5-1
Tables 3-5 & 5-1: Direct Cost Estimate By Year
(In Millions, 2019$)
| 2021 | 2022 | 2023 | 2024 | Total
Capital | 4.1385 | 20.3484 | 10.2041 | 0 | 34.6911
O&M | 0.28233 | 2.7543 | 2.6374 | 0 | 5.674
Total Implementation | 4.4209 | 23.1027 | 12.8415 | 0 | 40.365
Ongoing O&M | 0.29243 | 0.89236 | 0.99922 | 0.96142 | 3.1454
Total Request | 4.7133 | 23.995 | 13.8407 | 0.96142 | 43.5105

## Testimony Table 3-6, 5-2
Tables 3-6 & 5-2: Total Capital and O&M
(In Millions, includes escalation, overheads, AFUDC, and capitalized property tax)
| 2021 | 2022 | 2023 | 2024 | Total
Capital | 5.7641 | 25.9388 | 13.7589 | 0 | 45.4618
O&M | 0.43922 | 3.4657 | 3.1412 | 0 | 7.046
Total Implementation | 6.2033 | 29.4045 | 16.9 | 0 | 52.5078
Ongoing O&M | 0.498 | 1.6297 | 1.9215 | 1.8754 | 5.9247
Total Request | 6.7013 | 31.0342 | 18.8216 | 1.8754 | 58.4325

## Job Type Cost-Const. ED Loader (hidden)
100
Lot 10 Lvl2s | Direct % | Direct Cost | TM1 Input
6220006 - SRV-CONSTRUCTION SERVICES DEPT ONLY | 2.963% | 4000 | 2.963
6221000 - SRV-CONSTRUCTION-ELECTRIC | 66.67% | 90000 | 66.6666
6215070 - MATL ISSUANCES-KEARNY WAREHOUSE | 3.704% | 5000 | 3.7037
6213090 - MATL-FREIGHT | 1.481% | 2000 | 1.4815
6213225 - MATL-ELECTRICAL EQUIPMENT | 22.22% | 30000 | 22.2222
6213385 - MATL-ELEC MATERIAL MISCELLANEOUS | 2.963% | 4000 | 2.963
| 100% | 135000 | 100
Structure 10 Lvl2s | Direct % | Direct Cost
6220006 - SRV-CONSTRUCTION SERVICES DEPT ONLY | 2.581% | 4000 | 2.5806
6221000 - SRV-CONSTRUCTION-ELECTRIC | 70.97% | 110000 | 70.9679
6215070 - MATL ISSUANCES-KEARNY WAREHOUSE | 3.226% | 5000 | 3.2258
6213090 - MATL-FREIGHT | 1.29% | 2000 | 1.2903
6213225 - MATL-ELECTRICAL EQUIPMENT | 19.35% | 30000 | 19.3548
6213385 - MATL-ELEC MATERIAL MISCELLANEOUS | 2.581% | 4000 | 2.5806
| 100% | 155000 | 100