## Sheet1 (2)
Design Phase Steps | 1. Base Mapping | 2. 10% Design | 3. 30% Design | 4. Constructability Fielding | 5. 60% Design (T&C) | 6. 60% Design (C&C, CP, SCADA, OH RFS) | 7. 90% Design | 8. 100% Design
Design Phase Documents
| The Mapping Blank | The Preliminary Environmental Submittal The Project Master Schedule | The 30% Design Document The 30% Environmental Review Request |  | The 60% Design Document The 60% Environmental Review Request | The 60% Design Documents | The 90% Design Document The 90% Environmental Review Request | The 100% Design Documents
Permitting / Land Rights Phase Steps |  |  | 3. Initial Research |  | 5. Long-Lead Applications |  | 7. Ministerial Applications
Permitting Phase Documents |  |  | Permit Requirements Review Record Land Rights Requirements Review Record Tribal Lands Review Record |  | Agency Permitting Application(s) Land Rights Request Letter(s) |  | Agency Permitting Application(s) Regulatory Agency Notification(s)
Construction Phase Steps | 9. IFC | 10. Award Civil | 11. Civil Construction | 12. Award Electric | 13. Electric Construction | 14. Operations Construction | 15. Operational Asset
Construction Phase Documents | The Approved Construction Plans Approved Agency Permits Aquired Land Rights (Summary Document) Environmental Release (Compliance Instructions Document) | Construction Contract | Civil Construction As-Builts Contractor Invoicing | Electric Construction Contract System Operation Pre-Digitization (Confirmation Document) | Construction As-Builts Approved Switching Orders System Operation Confirmation Contractor Invoicing | Construction As-Builts Approved Switching Orders System Operation Confirmation
Post-Construction Phase Steps | 16. As-Built Reconciliation and Post Construction Field Inspections | 17. Financial Closeout | 18. Final Closeout
Post Construction Phase Documents | Final Digitization of New Assets (Confirmation Document) Post-Construction Inspection Reports (Where Applicable) Correction Reports (Where Applicable) | SAP Closeout (Charges prevented in the accounting systems) | Project Record Documents in Archive System (OpenText).