## Summary Tables
SDG&E and SoCalGas 2024 Risk Spending Accountability Report
SDG&E Summary Tables
[9 empty] | Actual Cost 2024 | Imputed Authorized Cost 2024 | $ Variance | % Variance
| Capital |  |  |  | 0 | 0 |  | SDG&E Direct Capital | 1615035381.3545 | 1442927990.76 | 172107390.5945 | 11.93%
| O&M |  |  |  | 0 | 4.2915e-06 |  | SDG&E Direct O&M | 1389913635.7523 | 1343895999.8616 | 46017635.8907 | 3.424%
[8 empty] | SDG&E Direct Total | 3004949017.1068 | 2786823990.6216 | 218125026.4852 | 7.827%
Summary Tables by Line of Business
[7 empty] | Utility | GRC General Line of Business | Actual Cost 2024 | Imputed Authorized Cost 2024 | $ Variance | % Variance
[7 empty] | O&M | Electric | 383563728.4117 | 383623999.9536 | -60271.5419 | -0.01571%
[8 empty] | Gas | 81896276.8672 | 54508999.9764 | 27387276.8908 | 50.24%
[8 empty] | Other | 924453630.4734 | 905762999.9316 | 18690630.5418 | 2.064%
[8 empty] | SDG&E TOTAL O&M | 1389913635.7523 | 1343895999.8616 | 46017635.8907 | 3.424%
Summary Tables by GRC Witness Area
Sheet names | Hana Type | LOB | Hana Witness Area | Balanced? | Check to Hana Actuals (s/b zero) | Check to Hana Imputed (s/b zero) | Utility | GRC Witness Areas | Actual Cost 2024 | Imputed Authorized Cost 2024 | $ Variance | % Variance
EOED | O&M | Electric | ELECTRIC DISTRIBUTION | NO | 0 | 0 | SDG&E Non-Balanced O&M | Electric Distribution | 135168103.1016 | 128983999.9836 | 6184103.118 | 4.794%
EOEG | O&M | Electric | ELECTRIC GENERATION | NO | 0 | 0 |  | Electric Generation | 40194579.3236 | 43022999.9976 | -2828420.674 | -6.574%
EODD | O&M | Electric | CLEAN ENERGY INNOVATIONS | NO | 0 | 0 |  | Clean Energy Innovations | 3664738.5544 | 3278999.9988 | 385738.5556 | 11.76%
EOCT | O&M | Electric | CLEAN TRANSPORTATION | NO | 0 | 0 |  | Clean Transportation | 4271808.5298 | 4921999.9992 | -650191.4694 | -13.21%
EOEP | O&M | Electric | SDG&E ENERGY PROCUREMENT | NO | 0 | 0 |  | Energy Procurement | 9346987.0548 | 10601999.9988 | -1255012.944 | -11.84%
[8 empty] | Sub-Total Electric | 192646216.5642 | 190809999.978 | 1836216.5862 | 0.9623%
GOGD | O&M | Gas | GAS DISTRIBUTION | NO | 0 | 0 |  | Gas Distribution | 43708794.0826 | 37006999.9872 | 6701794.0954 | 18.11%
GOTD | O&M | Gas | GAS INTEGRITY PROGRAMS | NO | 0 | 0 |  | Gas Integrity Management Programs | 0 | 145999.9992 | -145999.9992 | -100%
GOGT | O&M | Gas | GAS TRANSMISSION | NO | 0 | 0 |  | Gas Transmission Operations and Construction | 5385056.3469 | 6191999.9952 | -806943.6483 | -13.03%
GOSI | O&M | Gas | GAS SYSTEM STAFF & TECHNOLOGY | NO | 0 | 0 |  | Gas System Staff & Technology | 580813.2831 | 480999.9948 | 99813.2883 | 20.75%
[8 empty] | Sub-Total Gas | 49674663.7126 | 43825999.9764 | 5848663.7362 | 13.35%
CSFC | O&M | Other | CS - FIELD OPERATIONS | NO | 0 | 0 |  | Customer Services - Field Operations | 40552178.9034 | 35898999.9972 | 4653178.9062 | 12.96%
CSIN | O&M | Other | CS - INFORMATION | NO | 0 | 0 |  | Customer Services - Information | 17607458.0481 | 25708999.9968 | -8101541.9487 | -31.51%
CSOO | O&M | Other | CS - OFFICE OPERATIONS | NO | 0 | 0 |  | Customer Services - Office Operations | 39436219.2781 | 36935999.9976 | 2500219.2805 | 6.769%
ESEV | O&M | Other | SDG&E ENVIRONMENTAL SERVICES AND SONGS | NO | 0 | 0 |  | Environmental Services and San Onofre Nuclear Generating Station ("SONGS") | 7132422.738 | 7969999.9992 | -837577.2612 | -10.51%
SMFS | O&M | Other | FLEET SERVICES | NO | 0 | 0 |  | Fleet Services | 46245781.6073 | 48493999.998 | -2248218.3907 | -4.636%
ESRE | O&M | Other | REAL ESTATE, LAND SERVICES & FACILITIES | NO | 0 | 0 |  | Real Estate, Land Services & Facility Operations | 40913911.2229 | 40356999.9948 | 556911.2281 | 1.38%
SMSS | O&M | Other | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | NO | 0 | 0 |  | Supply Management, Logistics, & Supplier Diversity | 33966411.6428 | 23325999.996 | 10640411.6468 | 45.62%
ITCS | O&M | Other | CYBERSECURITY | NO | 0 | 0 |  | Cybersecurity | 13795797.6568 | 18165999.9996 | -4370202.3428 | -24.06%
ITIT | O&M | Other | INFORMATION TECHNOLOGY | NO | 0 | 0 |  | Information Technology | 92590404.661 | 111804999.9948 | -19214595.3338 | -17.19%
AGHR | O&M | Other | PEOPLE AND CULTURE DEPARTMENT | NO | 0 | 0 |  | People and Culture Department | 19183354.6831 | 19036999.9944 | 146354.6887 | 0.7688%
AGAG | O&M | Other | ADMINISTRATIVE & GENERAL | NO | 0 | 0 |  | Administrative and General | 43165933.6107 | 47064999.99 | -3899066.3793 | -8.284%
SEAG | O&M | Other | CORPORATE CENTER - GENERAL ADMINISTRATION | NO | 0 | 0 |  | Corporate Center - General Administration | 64506504.8292 | 58059999.9984 | 6446504.8308 | 11%
SEIN | O&M | Other | CORPORATE CENTER - INSURANCE | NO | 0 | 0 |  | Corporate Center - Insurance | 12621352.3884 | 16980999.9984 | -4359647.61 | -25.67%
AGCP | O&M | Other | CORPORATE CENTER - COMPENSATION & BENEFITS | NO | 0 | 0 |  | Corporate Center - Compensation & Benefits | 202423678.1066 | 127056999.9924 | 75366678.1142 | 59.32%
GOSM | O&M | Other | SAFETY MANAGEMENT SYSTEMS | NO | 0 | 0 |  | Safety, Risk & Asset Management Systems | 13318489.5223 | 16752999.9888 | -3434510.4665 | -20.5%
[8 empty] | Sub-Total Other | 687459898.8986 | 633614999.9364 | 53844898.9622 | 8.498%
[8 empty] | Sub-Total Non-Balanced O&M | 929780779.1754 | 868250999.8908 | 61529779.2846 | 7.087%
EOWM-B | O&M | Electric | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | YES | 0 | 0 | SDG&E Balanced O&M | Wildfire Mitigation and Vegetation Management | 190917511.8475 | 192813999.9756 | -1896488.1281 | -0.9836%
ESEV-B | O&M | Other | SDG&E ENVIRONMENTAL SERVICES AND SONGS | YES | 0 | 0 |  | Environmental Services and San Onofre Nuclear Generating Station ("SONGS") | 5240631.3565 | 3157999.998 | 2082631.3585 | 65.95%
GOTD-B | O&M | Gas | GAS INTEGRITY PROGRAMS | YES | 0 | 0 |  | Gas Integrity Management Programs | 32221613.1546 | 10683000 | 21538613.1546 | 201.6%
SEIN-B | O&M | Other | CORPORATE CENTER - INSURANCE | YES | 0 | 0 |  | Corporate Center - Insurance | 196605335.5284 | 233714999.9988 | -37109664.4704 | -15.88%
AGPN-B | O&M | Other | CORPORATE CENTER - PENSION & PBOP | YES | 0 | 0 |  | Corporate Center - Pension and Postretirement Benefits Other than Pension | 35147764.69 | 35274999.9984 | -127235.3084 | -0.3607%
[8 empty] | Sub-Total Balanced O&M | 460132856.577 | 475644999.9708 | -15512143.3938 | -3.261%
[8 empty] | TOTAL SDG&E O&M | 1389913635.7523 | 1343895999.8616 | 46017635.8907 | 3.424%
Summary Tables by Line of Business
[7 empty] | Utility | GRC General Line of Business | Actual Cost 2024 | Imputed Authorized Cost 2024 | $ Variance | % Variance
[7 empty] | Capital | Electric | 1068797589.217 | 1030713995.04 | 38083594.177 | 3.695%
[8 empty] | Gas | 331816439.3472 | 170697998.16 | 161118441.1872 | 94.39%
[8 empty] | Other | 214421352.7903 | 241515997.56 | -27094644.7697 | -11.22%
[8 empty] | SDG&E TOTAL Capital | 1615035381.3545 | 1442927990.76 | 172107390.5945 | 11.93%
Summary Tables by GRC Witness Area
[7 empty] | Utility | GRC Witness Areas | Actual Cost 2024 | Imputed Authorized Cost 2024 | $ Variance | % Variance
EOED-C | Capital | Electric | ELECTRIC DISTRIBUTION | NO | 0 | 0 | SDG&E Non-Balanced Capital | Electric Distribution | 337972025.7353 | 431287997.16 | -93315971.4247 | -21.64%
EOEG-C | Capital | Electric | ELECTRIC GENERATION | NO | 0 | 0 |  | Electric Generation | 10544131.5693 | 13374999.72 | -2830868.1507 | -21.17%
EODD-C | Capital | Electric | CLEAN ENERGY INNOVATIONS | NO | 0 | 0 |  | Clean Energy Innovations | 1932643.798 | 2769999.84 | -837356.042 | -30.23%
[8 empty] | Sub-Total Electric | 350448801.1027 | 447432996.72 | -96984195.6173 | -21.68%
GOGD-C | Capital | Gas | GAS DISTRIBUTION | NO | 0 | 0 |  | Gas Distribution | 135562979.4126 | 104073998.88 | 31488980.5326 | 30.26%
GOGT-C | Capital | Gas | GAS TRANSMISSION | NO | 0 | 0 |  | Gas Transmission Operations and Construction | 67661434.2114 | 11663999.52 | 55997434.6914 | 480.1%
GOEN-C | Capital | Gas | GAS ENGINEERING | NO | 0 | 0 |  | Gas Engineering | 367273.0114 | 294000 | 73273.0114 | 24.92%
GOTD-C | Capital | Gas | GAS INTEGRITY PROGRAMS | NO | 0 | 0 |  | Gas Integrity | 11423376.1176 | 27060999.84 | -15637623.7224 | -57.79%
[8 empty] | Sub-Total Gas | 215015062.753 | 143092998.24 | 71922064.513 | 50.26%
ESRE-C | Capital | Other | FACILITIES/OTHER | NO | 0 | 0 |  | Facilites/Other | 40810787.7779 | 51424999.68 | -10614211.9021 | -20.64%
ITCS-C | Capital | Other | CYBERSECURITY | NO | 0 | 0 |  | Cybersecurity | 4013006.0544 | 11408999.64 | -7395993.5856 | -64.83%
ITIT-C | Capital | Other | INFORMATION TECHNOLOGY | NO | 0 | 0 |  | Information Technology | 167288329.4841 | 175708998.36 | -8420668.8759 | -4.792%
GOSM-C | Capital | Other | SAFETY MANAGEMENT SYSTEMS | NO | 0 | 0 |  | Safety, Risk & Asset Management Systems | 2309229.4739 | 2972999.88 | -663770.4061 | -22.33%
[8 empty] | Sub-Total Other | 214421352.7903 | 241515997.56 | -27094644.7697 | -11.22%
[8 empty] | Sub-Total Non-Balanced Capital | 779885216.6459 | 832041992.52 | -52156775.874 | -6.269%
EOWM-C-B | Capital | Electric | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | YES | 0 | 0 | SDG&E Balanced Capital | Wildfire Mitigation and Vegetation Management | 485403550.8731 | 395990998.56 | 89412552.3131 | 22.58%
EOED-C-B | Capital | Electric | ELECTRIC DISTRIBUTION | YES | 0 | 0 |  | Electric Distribution | 232945237.2412 | 187289999.76 | 45655237.4812 | 24.38%
GOTD-C-B | Capital | Gas | GAS INTEGRITY PROGRAMS | YES | 0 | 0 |  | Gas Integrity Management Programs | 114313332.5144 | 25279999.92 | 89033332.5944 | 352.2%
GOGD-C-B | Capital | Gas | GAS DISTRIBUTION | YES | 0 | 0 |  | Gas Distribution | 2488044.0798 | 2325000 | 163044.0798 | 7.013%
[8 empty] | Sub-Total Balanced Capital | 835150164.7086 | 610885998.24 | 224264166.4685 | 36.71%
[8 empty] | TOTAL SDG&E Capital | 1615035381.3545 | 1442927990.76 | 172107390.5945 | 11.93%

## LOB Details =>
ATTACHMENT A - SDG&E'S 2024 RISK SPENDING ACCOUNTABILITY REPORT

## EOED
SDG&E ELECTRIC DISTRIBUTION O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | ELECTRIC DISTRIBUTION | ELECTRIC DISTRIBUTION |  |  |  | Yes |  |  | 135168103.1016 | 0 | 0 | 0 | 135168103.1016 | 128983999.9836 | 132853999.986 | 136837999.9848 | 140942999.9856 | 128983999.9836 | 6184103.118 | -132853999.986 | -136837999.9848 | -140942999.9856 | 6184103.118 | 4.794% | -100% | -100% | -100% | 4.794%
O&M | ELECTRIC DISTRIBUTION | COMPLIANCE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3343523.979 | 0 | 0 | 0 | 3343523.979 | 5487000 | 5652000 | 5821999.9992 | 5997000 | 5487000 | -2143476.021 | -5652000 | -5821999.9992 | -5997000 | -2143476.021 | -39.06% | -100% | -100% | -100% | -39.06% | This activity area consists of a variety of work streams that utilize internal and external labor and resources to manage including: (1) Oversight and governance of SDG&E’s distribution electric Corrective Maintenance Program (2) Performance of graffiti abatement mandated by local ordinance for all of SDG&E’s facilities (3) Performance of quality control and quality assurance audits of our distribution electric inspections (4) Responsibility for all joint asset management processes related to third-party use of SDG&E’s overhead and underground facilities (5) Facilitate and support for CPUC, Safety Enforcement Division (SED) incident investigations and complaints (6) Facilitate and support CPUC, SED audits for electric distribution, transmission and substation (7) Execution of wood pole intrusive inspections and QA/QC audit of the wood pole intrusive inspection work (8) Management of SDG&E’s Line Inspection program with responsibility to perform overhead and underground patrol inspections and overhead detailed inspections The variety and variability of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal COMPLIANCE MANAGEMENT |  |  |  | Yes |  |  | 3343523.979 | 0 | 0 | 0 | 3343523.979 | 5487000 | 5652000 | 5821999.9992 | 5997000 | 5487000 | -2143476.021 | -5652000 | -5821999.9992 | -5997000 | -2143476.021 | -39.06% | -100% | -100% | -100% | -39.06% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | CONSTRUCTION MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2620816.884 | 0 | 0 | 0 | 2620816.884 | 4593000 | 4731000 | 4872999.9996 | 5019999.9996 | 4593000 | -1972183.116 | -4731000 | -4872999.9996 | -5019999.9996 | -1972183.116 | -42.94% | -100% | -100% | -100% | -42.94% | This activity provides oversight of all construction performed by Contractors on the electric distribution system. This oversight promotes all work being built to SDG&E engineering, design, and safety standards and in accordance with GO 95 and GO 128 rules for construction. The O&M portion of construction work conducted by Construction Management includes O&M activities associated with completing construction of capital projects, installation and removal of transformers, and repairs and management of street lighting. The Construction Management group is responsible for administrative activities associated with capital construction work and also supports the Corrective Maintenance Program by monitoring and tracking those jobs which are constructed by contractors. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | CONSTRUCTION MANAGEMENT | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | N/A | No | On-going | Annual | 5109.7759 | 0 | 0 | 0 | 5109.7759 | 9000 | 9000 | 9000 | 9000 | 9000 | -3890.2241 | -9000 | -9000 | -9000 | -3890.2241 | -43.22% | -100% | -100% | -100% | -43.22% | FTE | 2 |  |  |  | 2 | 1.9 |  |  |  | 1.9 | 0.1 | 0 | 0 | 0 | 0.1 | 5.263% | 0% | 0% | 0% | 5.263% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | CONSTRUCTION MANAGEMENT | Incident Involving an Employee | Personal Protective Equipment | N/A | No | On-going | Annual | 5109.7759 | 0 | 0 | 0 | 5109.7759 | 9000 | 9000 | 9000 | 9000 | 9000 | -3890.2241 | -9000 | -9000 | -9000 | -3890.2241 | -43.22% | -100% | -100% | -100% | -43.22% | FTE | 2 |  |  |  | 2 | 1.9 |  |  |  | 1.9 | 0.1 | 0 | 0 | 0 | 0.1 | 5.263% | 0% | 0% | 0% | 5.263% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal CONSTRUCTION MANAGEMENT |  |  |  | Yes |  |  | 2631036.4359 | 0 | 0 | 0 | 2631036.4359 | 4611000 | 4749000 | 4890999.9996 | 5037999.9996 | 4611000 | -1979963.5641 | -4749000 | -4890999.9996 | -5037999.9996 | -1979963.5641 | -42.94% | -100% | -100% | -100% | -42.94% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | DISTRIBUTION DESIGN AND PROJECT MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1127552.1984 | 0 | 0 | 0 | 1127552.1984 | 1485999.9996 | 1530999.9996 | 1576999.9992 | 1623999.9996 | 1485999.9996 | -358447.8012 | -1530999.9996 | -1576999.9992 | -1623999.9996 | -358447.8012 | -24.12% | -100% | -100% | -100% | -24.12% | FTE | 3.5 |  |  |  | 3.5 | 3.3 |  |  |  | 3.3 | 0.2 | 0 | 0 | 0 | 0.2 | 6.061% | 0% | 0% | 0% | 6.061% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal DISTRIBUTION DESIGN AND PROJECT MANAGEMENT |  |  |  | Yes |  |  | 1127552.1984 | 0 | 0 | 0 | 1127552.1984 | 1485999.9996 | 1530999.9996 | 1576999.9992 | 1623999.9996 | 1485999.9996 | -358447.8012 | -1530999.9996 | -1576999.9992 | -1623999.9996 | -358447.8012 | -24.12% | -100% | -100% | -100% | -24.12% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2009789.3506 | 0 | 0 | 0 | 2009789.3506 | 2388999.9996 | 2460999.9996 | 2535000 | 2610999.9996 | 2388999.9996 | -379210.649 | -2460999.9996 | -2535000 | -2610999.9996 | -379210.649 | -15.87% | -100% | -100% | -100% | -15.87% | FTE | 4.1 |  |  |  | 4.1 | 8.2 |  |  |  | 8.2 | -4.1 | 0 | 0 | 0 | -4.1 | -50% | 0% | 0% | 0% | -50% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. SDG&E continues to recruit qualified candidates. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Electric Distribution and Engineering group is responsible for developing and maintaining overhead and underground equipment specifications, risk analysis and mitigation, and construction standards to enable safe and reliable customer service throughout the 4kV and 12kV electric distribution system. The group also develops and maintains electric standard practices to establish uniform and safe work methods, procedures and inspection requirements and enable regulatory compliance with all governing agencies. Construction standards and standard practices are used by company and contractor construction forces throughout the SDG&E electric distribution system. This group also provides real-time support for operations and construction teams. A single work unit is not possible to identify due to multiple activities in this workpaper such as FTE allocated to developing and maintaining construction standards, performing equipment failure and risk analysis, and costs that scale with capital programs. | SDG&E-12-R-E TS-57 to TS-62 WP 1ED012.000
O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING | Asset Management | AIM (Gov, Strat, AIP) | N/A | No | On-going | Annual | 16671.2662 | 0 | 0 | 0 | 16671.2662 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | 11671.267 | -4999.9992 | -4999.9992 | -4999.9992 | 11671.267 | 233.4% | -100% | -100% | -100% | 233.4% | This activity area consists of work to further develop and implement asset data aggregation, integration, and asset health models for an expanded scope of assets within Gas, Smart Meter, Facilities, Information Technology, and emerging lines of business. The development of these data repositories supports the overall objectives of the broader Asset Integrity Management (AIM) program. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING | Incident Involving an Employee | Personal Protective Equipment | N/A | No | On-going | Annual | 4998.7834 | 0 | 0 | 0 | 4998.7834 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 22999.9992 | -18001.2158 | -24000 | -24999.9996 | -25999.9992 | -18001.2158 | -78.27% | -100% | -100% | -100% | -78.27% | FTE | 4.1 |  |  |  | 4.1 | 8.2 |  |  |  | 8.2 | -4.1 | 0 | 0 | 0 | -4.1 | -50% | 0% | 0% | 0% | -50% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. SDG&E continues to recruit qualified candidates. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Electric Distribution and Engineering group is responsible for developing and maintaining overhead and underground equipment specifications, risk analysis and mitigation, and construction standards to enable safe and reliable customer service throughout the 4kV and 12kV electric distribution system. The group also develops and maintains electric standard practices to establish uniform and safe work methods, procedures and inspection requirements and enable regulatory compliance with all governing agencies. Construction standards and standard practices are used by company and contractor construction forces throughout the SDG&E electric distribution system. This group also provides real-time support for operations and construction teams. A single work unit is not possible to identify due to multiple activities in this workpaper such as FTE allocated to developing and maintaining construction standards, performing equipment failure and risk analysis, and costs that scale with capital programs. | SDG&E-12-R-E TS-57 to TS-62 WP 1ED012.000
O&M | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC ENGINEERING |  |  |  | Yes |  |  | 2031459.4002 | 0 | 0 | 0 | 2031459.4002 | 2416999.998 | 2489999.9988 | 2564999.9988 | 2641999.998 | 2416999.998 | -385540.5978 | -2489999.9988 | -2564999.9988 | -2641999.998 | -385540.5978 | -15.95% | -100% | -100% | -100% | -15.95% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING (TNG) | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 26437.1685 | 0 | 0 | 0 | 26437.1685 | 75999.9996 | 78000 | 79999.9992 | 81999.9996 | 75999.9996 | -49562.8311 | -78000 | -79999.9992 | -81999.9996 | -49562.8311 | -65.21% | -100% | -100% | -100% | -65.21% | This activity includes O&M costs related to the Associate Engineer’s Program. The labor for these Associate Engineer’s is primarily charged to Engineering Pools and the non-labor is for O&M related expenses. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC ENGINEERING (TNG) |  |  |  | Yes |  |  | 26437.1685 | 0 | 0 | 0 | 26437.1685 | 75999.9996 | 78000 | 79999.9992 | 81999.9996 | 75999.9996 | -49562.8311 | -78000 | -79999.9992 | -81999.9996 | -49562.8311 | -65.21% | -100% | -100% | -100% | -65.21% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 35125453.746 | 0 | 0 | 0 | 35125453.746 | 40531999.9992 | 41748000 | 42999999.9996 | 44289999.9996 | 40531999.9992 | -5406546.2532 | -41748000 | -42999999.9996 | -44289999.9996 | -5406546.2532 | -13.34% | -100% | -100% | -100% | -13.34% | FTE | 124.6 |  |  |  | 124.6 | 167.8 |  |  |  | 167.8 | -43.2 | 0 | 0 | 0 | -43.2 | -25.74% | 0% | 0% | 0% | -25.74% | YES | YES | YES | SDG&E continues to recruit linemen, during an industry wide shortage, but was unable to fill all the positions. Candidate attrition also contributed to the variance. | The variance is driven by lower than forecasted staffing levels. SDG&E continues to recruit linemen, during an industry wide shortage, but was unable to fill all the positions. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Electric Regional Operations organization consists of the electric distribution crews within six districts, two satellite districts and other operating centers. These crews provide coverage for all of SDG&E's electric distribution system throughout its service territory. The ERO group consists of electric linemen, apprentices, line assistants, schedulers, office support personnel, and management supervision. Their primary job functions are to maintain reliability of the electric distribution system, construct new electric infrastructure, schedule and forecast to drive efficient work practices, restore service due to outages, and fix service problems and other customer issues. A single work unit is not possible to identify due to multiple activities in this workpaper such as facilities inspected, jobs completed, and employees' hours in safety meetings. | SDG&E-12-R-E TS-47 to TS-51 WP 1ED008.000
O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Incident Involving an Employee | Employee Accidental Behavior Program | None | No | On-going | Annual | 62339.4212 | 0 | 0 | 0 | 62339.4212 | 79999.9992 | 81999.9996 | 84000 | 87000 | 79999.9992 | -17660.578 | -81999.9996 | -84000 | -87000 | -17660.578 | -22.08% | -100% | -100% | -100% | -22.08% | FTE | 0.39 |  |  |  | 0.39 | 0.51 |  |  |  | 0.51 | -0.12 | 0 | 0 | 0 | -0.12 | -23.53% | 0% | 0% | 0% | -23.53% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. SDG&E continues to recruit qualified candidates. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Electric Regional Operations organization consists of the electric distribution crews within six districts, two satellite districts and other operating centers. These crews provide coverage for all of SDG&E's electric distribution system throughout its service territory. The ERO group consists of electric linemen, apprentices, line assistants, schedulers, office support personnel, and management supervision. Their primary job functions are to maintain reliability of the electric distribution system, construct new electric infrastructure, schedule and forecast to drive efficient work practices, restore service due to outages, and fix service problems and other customer issues. A single work unit is not possible to identify due to multiple activities in this workpaper such as facilities inspected, jobs completed, and employees' hours in safety meetings. | SDG&E-12-R-E TS-47 to TS-51 WP 1ED008.000
O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | None | No | On-going | Annual | 144886.8493 | 0 | 0 | 0 | 144886.8493 | 186999.9996 | 192999.9996 | 198999.9996 | 204999.9996 | 186999.9996 | -42113.1503 | -192999.9996 | -198999.9996 | -204999.9996 | -42113.1503 | -22.52% | -100% | -100% | -100% | -22.52% | Training classes | 56 |  |  |  | 56 | 39 |  |  |  | 39 | 17 | 0 | 0 | 0 | 17 | 43.59% | 0% | 0% | 0% | 43.59% | YES | NO | YES | N/A | The variance is due to an increased number of safety classes required compared to the base year. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Electric Regional Operations organization consists of the electric distribution crews within six districts, two satellite districts and other operating centers. These crews provide coverage for all of SDG&E's electric distribution system throughout its service territory. The ERO group consists of electric linemen, apprentices, line assistants, schedulers, office support personnel, and management supervision. Their primary job functions are to maintain reliability of the electric distribution system, construct new electric infrastructure, schedule and forecast to drive efficient work practices, restore service due to outages, and fix service problems and other customer issues. A single work unit is not possible to identify due to multiple activities in this workpaper such as facilities inspected, jobs completed, and employees' hours in safety meetings. | SDG&E-12-R-E TS-47 to TS-51 WP 1ED008.000
O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Incident Involving an Employee | Personal Protective Equipment | None | No | On-going | Annual | 467174.0998 | 0 | 0 | 0 | 467174.0998 | 601999.9992 | 619999.9992 | 639000 | 657999.9996 | 601999.9992 | -134825.8994 | -619999.9992 | -639000 | -657999.9996 | -134825.8994 | -22.4% | -100% | -100% | -100% | -22.4% | FTE | 124.6 |  |  |  | 124.6 | 167.8 |  |  |  | 167.8 | -43.2 | 0 | 0 | 0 | -43.2 | -25.74% | 0% | 0% | 0% | -25.74% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. SDG&E continues to recruit qualified candidates. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Electric Regional Operations organization consists of the electric distribution crews within six districts, two satellite districts and other operating centers. These crews provide coverage for all of SDG&E's electric distribution system throughout its service territory. The ERO group consists of electric linemen, apprentices, line assistants, schedulers, office support personnel, and management supervision. Their primary job functions are to maintain reliability of the electric distribution system, construct new electric infrastructure, schedule and forecast to drive efficient work practices, restore service due to outages, and fix service problems and other customer issues. A single work unit is not possible to identify due to multiple activities in this workpaper such as facilities inspected, jobs completed, and employees' hours in safety meetings. | SDG&E-12-R-E TS-47 to TS-51 WP 1ED008.000
O&M | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC REGIONAL OPERATIONS |  |  |  | Yes |  |  | 35799854.1163 | 0 | 0 | 0 | 35799854.1163 | 41400999.9972 | 42642999.9984 | 43921999.9992 | 45239999.9988 | 41400999.9972 | -5601145.8809 | -42642999.9984 | -43921999.9992 | -45239999.9988 | -5601145.8809 | -13.53% | -100% | -100% | -100% | -13.53% | [21 empty] | YES | YES | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ELECTRIC SYSTEM OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 41361768.9958 | 0 | 0 | 0 | 41361768.9958 | 34092000 | 35115000 | 36168000 | 37252999.9992 | 34092000 | 7269768.9958 | -35115000 | -36168000 | -37252999.9992 | 7269768.9958 | 21.32% | -100% | -100% | -100% | 21.32% | Electric System Operations provides oversight of all activities on the electric system and is required to ensure the safety of both the public and field workers making enhancements and repairs to the electric system. The activities involve planned and unplanned outages, along with managing emergency events related to wildfire safety and system stresses. Being the source provider on situational awareness and workflow management technology to key stakeholders, the Mission Control Center houses several workgroups within Electric Grid Operations and Electric Distribution Operations. One of the essential workgroups for both departments are the operators who are responsible for monitoring and maintaining the reliability of SDG&E’s service territory on a 24/7/365 basis. This workpaper also includes support for electric operations, such as operator training, maintenance of SCADA and Advanced Distribution Management systems, Distributed Energy resource enablement and storeroom material and logistics support for construction activities. The data systems that support SDG&E’s daily operational workforce are continuously advancing to sustain the integrity of the electric system that is growing through technology and new energy resources. The Supervisory Control and Data Acquisition (SCADA) technology is continuing to grow in use for wildfire mitigations, visibility into the electric system, and customer energy electrification and the use of distributed energy resources. Training on the new features of technologies and tools is also needed. A single work unit is not possible to identify due to disparate activities in this workpaper such as switching volumes, costs that scale with capital, and costs related to managing technology. | [20 empty] | YES | YES | NO | Higher than forecasted spend is attributable to increased exempt materials $3.258M and freight expenses $3.963M. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Electric System Operations provides oversight of all activities on the electric system and is required to ensure the safety of both the public and field workers making enhancements and repairs to the electric system. The activities involve planned and unplanned outages, along with managing emergency events related to wildfire safety and system stresses. Being the source provider on situational awareness and workflow management technology to key stakeholders, the Mission Control Center houses several workgroups within Electric Grid Operations and Electric Distribution Operations. One of the essential workgroups for both departments are the operators who are responsible to monitor and maintain the reliability of SDG&E’s service territory on a 24/7/365 basis. This workpaper also includes upward pressures that support electric operations, such as operator training, maintenance of SCADA and Advanced Distribution Management systems, Distributed Energy resource enablement and storeroom material and logistics support for construction activities. The data systems that support SDG& E’s daily operational workforce are continuously advancing to sustain the integrity of the electric system that is growing through technology and new energy resources. The upsurge trend of Supervisory Control and Data Acquisition (SCADA) technology is continuing to grow in use for wildfire mitigations, visibility into the electric system, and customer energy electrification and the use of distributed energy resources. Training on the new features of technologies and tools is also needed. These cost drivers are detailed in this workpaper. A single work unit was not possible to identify due to disparate activities in this workpaper such as switching volumes, costs that scale with capital, and costs related to managing technology. | SDG&E-12-R-E TS-25 to TS-30 WP 1ED003.000
O&M | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC SYSTEM OPERATIONS |  |  |  | Yes |  |  | 41361768.9958 | 0 | 0 | 0 | 41361768.9958 | 34092000 | 35115000 | 36168000 | 37252999.9992 | 34092000 | 7269768.9958 | -35115000 | -36168000 | -37252999.9992 | 7269768.9958 | 21.32% | -100% | -100% | -100% | 21.32% | [21 empty] | YES | YES | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ELECTRIC SYSTEM OPERATIONS (TNG - GISS) | Records Management | GIS Jobs Processed | N/A | No | On-going | Annual | 2186867.1926 | 0 | 0 | 0 | 2186867.1926 | 1039999.9992 | 1071000 | 1102999.9992 | 1135999.9992 | 1039999.9992 | 1146867.1934 | -1071000 | -1102999.9992 | -1135999.9992 | 1146867.1934 | 110.3% | -100% | -100% | -100% | 110.3% | FTE | 20.6 |  |  |  | 20.6 | 12.9 |  |  |  | 12.9 | 7.7 | 0 | 0 | 0 | 7.7 | 59.69% | 0% | 0% | 0% | 59.69% | YES | NO | YES | N/A | Actual FTEs for 2024 reflect that training classes have returned to pre-COVID levels as compared to the 2021 base year forecast. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Enterprise GIS Services (EGISS) is the section of Electric Distribution Operations that creates and maintains all electric distribution, transmission, telecommunications, and substation data in SDG&E’s enterprise GIS system. EGISS digitizes the data in a preliminary state, energizes the data in real-time, reconciles and converts design work orders into construction order as-builts, scans them to a central repository, records details in the GIS system, and identifies these assets for tax and franchise fee calculations and reports. SDG&E’s enterprise GIS is a direct input of information into many operational and planning tools used by engineering and operations. Accurate and timely data stored in the GIS database is essential for the safety and reliability of electric operations throughout the Company. If the information was not captured precisely, it could impact work activities for employees and public safety. All costs for this workpaper are RAMP related. Please see RAMP costs for appropriate work units. | SDG&E-12-R-E TS-32 to TS-33 WP 1ED003.001
O&M | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC SYSTEM OPERATIONS (TNG - GISS) |  |  |  | Yes |  |  | 2186867.1926 | 0 | 0 | 0 | 2186867.1926 | 1039999.9992 | 1071000 | 1102999.9992 | 1135999.9992 | 1039999.9992 | 1146867.1934 | -1071000 | -1102999.9992 | -1135999.9992 | 1146867.1934 | 110.3% | -100% | -100% | -100% | 110.3% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ET&D: OPERATIONS SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2430129.1151 | 0 | 0 | 0 | 2430129.1151 | 1558999.9992 | 1605999.9996 | 1654999.9992 | 1704999.9996 | 1558999.9992 | 871129.1159 | -1605999.9996 | -1654999.9992 | -1704999.9996 | 871129.1159 | 55.88% | -100% | -100% | -100% | 55.88% | Tests, inspections, and repairs of rubber goods, tools, and equipment | 41052 |  |  |  | 41052 | 33455 |  |  |  | 33455 | 7597 | 0 | 0 | 0 | 7597 | 22.71% | 0% | 0% | 0% | 22.71% | YES | NO | YES | N/A | Units were higher than forecasted due to increases in the population of rubber goods, tools, and equipment that this group is responsible for inspecting, testing, and repairing. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Electric Transmission and Distribution: Operations Services (ET&D: Operations Services) performs a variety of support functions centered around Safety and Service. The group is responsible for the maintenance, repair, fabrication, and acquisition of new tooling to support various other groups performing work on the electric distribution system. ET&D Operations Services conducts salvage work on line equipment removed from service, and also operates a high voltage test station to perform tests and confirm the condition of electric distribution equipment and tools. The group inventories, inspects, and tests rubber goods and live line tools used for worker protection by multiple other groups working on the electric distribution system. Work units for this workpaper are the number of tests, inspections, and repairs of rubber goods, tools, and equipment. | SDG&E-12-R-E TS-33 to TS-37 WP 1ED005.000
O&M | ELECTRIC DISTRIBUTION | ET&D: OPERATIONS SERVICES | Incident Involving an Employee | OSHA Voluntary Protection Program | N/A | No | On-going | Annual | 621366.0763 | 0 | 0 | 0 | 621366.0763 | 78000 | 79999.9992 | 81999.9996 | 84000 | 78000 | 543366.0763 | -79999.9992 | -81999.9996 | -84000 | 543366.0763 | 696.6% | -100% | -100% | -100% | 696.6% | Voluntary Protection Plan (VPP) locations | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | ET&D: OPERATIONS SERVICES | Incident Involving an Employee | Personal Protective Equipment | None | No | On-going | Annual | 1286021.3022 | 0 | 0 | 0 | 1286021.3022 | 823999.9992 | 849000 | 873999.9996 | 900000 | 823999.9992 | 462021.303 | -849000 | -873999.9996 | -900000 | 462021.303 | 56.07% | -100% | -100% | -100% | 56.07% | FTE | 19 |  |  |  | 19 | 15.5 |  |  |  | 15.5 | 3.5 | 0 | 0 | 0 | 3.5 | 22.58% | 0% | 0% | 0% | 22.58% | YES | NO | YES | N/A | FTEs were higher than forecasted due to the growing workload associated with the expanding inventory of rubber goods, tools, and equipment that this group is responsible for inspecting, testing, and repairing. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Electric Transmission and Distribution: Operations Services (ET&D: Operations Services) performs a variety of support functions centered around Safety and Service. The group is responsible for the maintenance, repair, fabrication, and acquisition of new tooling to support various other groups performing work on the electric distribution system. ET&D Operations Services conducts salvage work on line equipment removed from service, and also operates a high voltage test station to perform tests and confirm the condition of electric distribution equipment and tools. The group inventories, inspects, and tests rubber goods and live line tools used for worker protection by multiple other groups working on the electric distribution system. Work units for this workpaper are the number of tests, inspections, and repairs of rubber goods, tools, and equipment. | SDG&E-12-R-E TS-33 to TS-37 WP 1ED005.000
O&M | ELECTRIC DISTRIBUTION | SubTotal ET&D: OPERATIONS SERVICES |  |  |  | Yes |  |  | 4337516.4935 | 0 | 0 | 0 | 4337516.4935 | 2460999.9984 | 2534999.9988 | 2610999.9984 | 2688999.9996 | 2460999.9984 | 1876516.4951 | -2534999.9988 | -2610999.9984 | -2688999.9996 | 1876516.4951 | 76.25% | -100% | -100% | -100% | 76.25% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 8417864.8556 | 0 | 0 | 0 | 8417864.8556 | 4903999.9992 | 5049999.9996 | 5202000 | 5358000 | 4903999.9992 | 3513864.8564 | -5049999.9996 | -5202000 | -5358000 | 3513864.8564 | 71.65% | -100% | -100% | -100% | 71.65% | Preventative maintenance orders | 2424 |  |  |  | 2424 | 1727 |  |  |  | 1727 | 697 | 0 | 0 | 0 | 697 | 40.36% | 0% | 0% | 0% | 40.36% | YES | YES | YES | Increased preventative maintenance work. The amount of maintenance required on substation equipment varies year-to-year depending on timing of cyclical preventative maintenance and identification of additional necessary corrective maintenance. In addition, $1.7M in non-labor expenses were recategorized from FERC transmission to electric distribution; these costs were not originally forecast in the 2024 GRC. | Increased preventative maintenance work. The amount of maintenance required on substation equipment varies year-to-year depending on timing of cyclical preventative maintenance and identification of additional necessary corrective maintenance. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Electric Transmission & Distribution: Substation Construction and Operations (ET&D: Substation C&O) and associated support organizations are responsible for the installation, inspection, and maintenance of approximately 135 distribution substations on the SDG&E system. Substation equipment maintained includes approximately 298 distribution power transformers and their associated load tap changers or voltage regulators, and approximately 1550 circuit breakers including oil, air, and vacuum classifications, and their associated line and bus disconnect switches. It also includes inspection and maintenance for all substation equipment including batteries, buses, support structures, capacitor banks, reactors, grounding systems, fire suppression systems, and perimeter fences and gates. The substation inspection and resulting corrective maintenance program managed by this group is established in compliance with GO 174, CAISO maintenance requirements, and SDG&E's maintenance standards. This program is critical to the safe operation and reliability of all electric distribution substation facilities. Work units for this workpaper are the number of maintenance orders. | SDG&E-12-R-E TS-37 to TS-41 WP 1ED006.000
O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Electric Infrastructure Integrity | Substation Inspections & Repairs GO-174 | Inspections & Repairs | No | On-going | Annual | 1843039.1867 | 0 | 0 | 0 | 1843039.1867 | 1350999.9996 | 1392000 | 1432999.9992 | 1476000 | 1350999.9996 | 492039.1871 | -1392000 | -1432999.9992 | -1476000 | 492039.1871 | 36.42% | -100% | -100% | -100% | 36.42% | Inspections and corrective maintenance orders | 2211 |  |  |  | 2211 | 2156 |  |  |  | 2156 | 55 | 0 | 0 | 0 | 55 | 2.551% | 0% | 0% | 0% | 2.551% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Incident Involving an Employee | OSHA Voluntary Protection Program | N/A | No | On-going | Annual | 24900.1998 | 0 | 0 | 0 | 24900.1998 | 163999.9992 | 168999.9996 | 174000 | 178999.9992 | 163999.9992 | -139099.7994 | -168999.9996 | -174000 | -178999.9992 | -139099.7994 | -84.82% | -100% | -100% | -100% | -84.82% | VPP locations | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Incident Involving an Employee | Personal Protective Equipment | None | No | On-going | Annual | 256316.2272 | 0 | 0 | 0 | 256316.2272 | 162000 | 166999.9992 | 171999.9996 | 177000 | 162000 | 94316.2272 | -166999.9992 | -171999.9996 | -177000 | 94316.2272 | 58.22% | -100% | -100% | -100% | 58.22% | FTE | 35.6 |  |  |  | 35.6 | 27.5 |  |  |  | 27.5 | 8.1 | 0 | 0 | 0 | 8.1 | 29.45% | 0% | 0% | 0% | 29.45% | YES | NO | YES | N/A | Increased preventative maintenance work. The amount of maintenance required on substation equipment varies year-to-year depending on timing of cyclical preventative maintenance and identification of additional necessary corrective maintenance. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Electric Transmission & Distribution: Substation Construction and Operations (ET&D: Substation C&O) and associated support organizations are responsible for the installation, inspection, and maintenance of approximately 135 distribution substations on the SDG&E system. Substation equipment maintained includes approximately 298 distribution power transformers and their associated load tap changers or voltage regulators, and approximately 1550 circuit breakers including oil, air, and vacuum classifications, and their associated line and bus disconnect switches. It also includes inspection and maintenance for all substation equipment including batteries, buses, support structures, capacitor banks, reactors, grounding systems, fire suppression systems, and perimeter fences and gates. The substation inspection and resulting corrective maintenance program managed by this group is established in compliance with GO 174, CAISO maintenance requirements, and SDG&E's maintenance standards. This program is critical to the safe operation and reliability of all electric distribution substation facilities. Work units for this workpaper are the number of maintenance orders. | SDG&E-12-R-E TS-37 to TS-41 WP 1ED006.000
O&M | ELECTRIC DISTRIBUTION | SubTotal ET&D: SUBSTATION C&O |  |  |  | Yes |  |  | 10542120.4693 | 0 | 0 | 0 | 10542120.4693 | 6580999.998 | 6777999.9984 | 6980999.9988 | 7189999.9992 | 6580999.998 | 3961120.4713 | -6777999.9984 | -6980999.9988 | -7189999.9992 | 3961120.4713 | 60.19% | -100% | -100% | -100% | 60.19% | [21 empty] | YES | YES | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O (RELAY & SCADA) | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3874932.692 | 0 | 0 | 0 | 3874932.692 | 4161000 | 4285999.9992 | 4414999.9992 | 4546999.9992 | 4161000 | -286067.308 | -4285999.9992 | -4414999.9992 | -4546999.9992 | -286067.308 | -6.875% | -100% | -100% | -100% | -6.875% | Preventative and corrective maintenance orders completed by SPM | 1210 |  |  |  | 1210 | 1522 |  |  |  | 1522 | -312 | 0 | 0 | 0 | -312 | -20.5% | 0% | 0% | 0% | -20.5% | YES | NO | YES | N/A | Less work performed than forecasted. The amount of maintenance required on protection and control equipment varies year-to-year depending on timing of cyclical preventative maintenance and identification of additional necessary corrective maintenance. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Distribution System Control & Protection group, within the Substation Construction and Operations group, performs maintenance of protective relays and control systems installed in both substations and electric distribution field devices. The organization performs routine preventive maintenance at fixed time-based intervals to maintain reliable operation of protective relays and relay controls. They also perform timely corrective maintenance, which is troubleshooting and repairing systems that alarm or fail to function properly, to enable 24/7 operation of these devices. Lastly, the group downloads events captured during system outages and system emergencies to better investigate the cause of failures. This sometimes requires around the clock staffing during major events , as well as during system emergencies, for example, unscheduled load shedding and earthquakes. As SDG&E’s SCADA system has expanded, the scope and scale of maintenance and installation required has also expanded. It now includes distribution voltage regulators, capacitors, distribution reclosers, weather stations, other distribution SCADA controlled equipment and switchgear, and aircraft warning lights. Work units for this workpaper are the number of maintenance orders. | SDG&E-12-R-E TS-41 to TS-43 WP 1ED006.002
O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O (RELAY & SCADA) | Incident Involving an Employee | Personal Protective Equipment | None | No | On-going | Annual | 41066.3051 | 0 | 0 | 0 | 41066.3051 | 30999.9996 | 31999.9992 | 33000 | 33999.9996 | 30999.9996 | 10066.3055 | -31999.9992 | -33000 | -33999.9996 | 10066.3055 | 32.47% | -100% | -100% | -100% | 32.47% | FTE | 16.9 |  |  |  | 16.9 | 22.1 |  |  |  | 22.1 | -5.2 | 0 | 0 | 0 | -5.2 | -23.53% | 0% | 0% | 0% | -23.53% | YES | NO | YES | N/A | Less O&M work was performed in 2024 than forecasted in the GRC. The amount of maintenance required on protection and control equipment varies year-to-year depending on timing of cyclical preventative maintenance and identification of additional necessary corrective maintenance. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Distribution System Control & Protection group, within the Substation Construction and Operations group, performs maintenance of protective relays and control systems installed in both substations and electric distribution field devices. The organization performs routine preventive maintenance at fixed time-based intervals to maintain reliable operation of protective relays and relay controls. They also perform timely corrective maintenance, which is troubleshooting and repairing systems that alarm or fail to function properly, to enable 24/7 operation of these devices. Lastly, the group downloads events captured during system outages and system emergencies to better investigate the cause of failures. This sometimes requires around the clock staffing during major events , as well as during system emergencies, for example, unscheduled load shedding and earthquakes. As SDG&E’s SCADA system has expanded, the scope and scale of maintenance and installation required has also expanded. It now includes distribution voltage regulators, capacitors, distribution reclosers, weather stations, other distribution SCADA controlled equipment and switchgear, and aircraft warning lights. Work units for this workpaper are the number of maintenance orders. | SDG&E-12-R-E TS-41 to TS-43 WP 1ED006.002
O&M | ELECTRIC DISTRIBUTION | SubTotal ET&D: SUBSTATION C&O (RELAY & SCADA) |  |  |  | Yes |  |  | 3915998.9971 | 0 | 0 | 0 | 3915998.9971 | 4191999.9996 | 4317999.9984 | 4447999.9992 | 4580999.9988 | 4191999.9996 | -276001.0025 | -4317999.9984 | -4447999.9992 | -4580999.9988 | -276001.0025 | -6.584% | -100% | -100% | -100% | -6.584% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | SubTotal |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | [22 empty] | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | TROUBLESHOOTING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 12854531.1184 | 0 | 0 | 0 | 12854531.1184 | 10807999.9992 | 11131999.9992 | 11466000 | 11809999.9992 | 10807999.9992 | 2046531.1192 | -11131999.9992 | -11466000 | -11809999.9992 | 2046531.1192 | 18.94% | -100% | -100% | -100% | 18.94% | FTE | 49.8 |  |  |  | 49.8 | 48.4 |  |  |  | 48.4 | 1.4 | 0 | 0 | 0 | 1.4 | 2.893% | 0% | 0% | 0% | 2.893% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | TROUBLESHOOTING | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | None | No | On-going | Annual | 36252.2885 | 0 | 0 | 0 | 36252.2885 | 30000 | 30999.9996 | 31999.9992 | 33000 | 30000 | 6252.2885 | -30999.9996 | -31999.9992 | -33000 | 6252.2885 | 20.84% | -100% | -100% | -100% | 20.84% | Number of trainings classes | 56 |  |  |  | 56 | 39 |  |  |  | 39 | 17 | 0 | 0 | 0 | 17 | 43.59% | 0% | 0% | 0% | 43.59% | YES | NO | YES | N/A | The variance is due to an increased number of safety classes required compared to the base year. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Troubleshooting organization is responsible for ensuring safe and reliable electric service to SDG&E's customers. The group covers six districts and two satellite locations within the service territory. The six operational districts have electric troubleshooters, engineers, technical assistants, and management supervision. The troubleshooters are the primary contact with customers who are experiencing service problems, and work closely with emergency response agencies to protect the public and SDG&E employees from potentially hazardous conditions. The units that best represent troubleshooting are the number of orders dispatched. | SDG&E-12-R-E TS-62 to TS-64 WP 1ED013.000
O&M | ELECTRIC DISTRIBUTION | TROUBLESHOOTING | Incident Involving an Employee | Personal Protective Equipment | None | No | On-going | Annual | 44308.6033 | 0 | 0 | 0 | 44308.6033 | 36999.9996 | 37999.9992 | 39000 | 39999.9996 | 36999.9996 | 7308.6036 | -37999.9992 | -39000 | -39999.9996 | 7308.6036 | 19.75% | -100% | -100% | -100% | 19.75% | FTE | 49.8 |  |  |  | 49.8 | 48.4 |  |  |  | 48.4 | 1.4 | 0 | 0 | 0 | 1.4 | 2.893% | 0% | 0% | 0% | 2.893% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal TROUBLESHOOTING |  |  |  | Yes |  |  | 12935092.0101 | 0 | 0 | 0 | 12935092.0101 | 10874999.9988 | 11200999.998 | 11536999.9992 | 11882999.9988 | 10874999.9988 | 2060092.0113 | -11200999.998 | -11536999.9992 | -11882999.9988 | 2060092.0113 | 18.94% | -100% | -100% | -100% | 18.94% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | OFFICER | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 987280.686 | 0 | 0 | 0 | 987280.686 | 1450999.9992 | 1494999.9996 | 1539999.9996 | 1585999.9992 | 1450999.9992 | -463719.3132 | -1494999.9996 | -1539999.9996 | -1585999.9992 | -463719.3132 | -31.96% | -100% | -100% | -100% | -31.96% | FTE | 3.1 |  |  |  | 3.1 | 5.5 |  |  |  | 5.5 | -2.4 | 0 | 0 | 0 | -2.4 | -43.64% | 0% | 0% | 0% | -43.64% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workgroup includes the costs for officers and administrative assistants in support of electric distribution. The total salaries are a direct labor charge and crossover amounts allocated to electric transmission are excluded from this account as an indirect charge and not included in the requested expenses. Typical activities included in this account include officer activities in support of electric distribution. | SDG&E-12-R-E TS-70 to TS-71 WP 1ED016.000
O&M | ELECTRIC DISTRIBUTION | SubTotal OFFICER |  |  |  | Yes |  |  | 987280.686 | 0 | 0 | 0 | 987280.686 | 1450999.9992 | 1494999.9996 | 1539999.9996 | 1585999.9992 | 1450999.9992 | -463719.3132 | -1494999.9996 | -1539999.9996 | -1585999.9992 | -463719.3132 | -31.96% | -100% | -100% | -100% | -31.96% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | PORTFOLIO & PROJECT MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 455992.4673 | 0 | 0 | 0 | 455992.4673 | 582000 | 598999.9992 | 616999.9992 | 636000 | 582000 | -126007.5327 | -598999.9992 | -616999.9992 | -636000 | -126007.5327 | -21.65% | -100% | -100% | -100% | -21.65% | Portfolio & Project Management is responsible for project management, document control management, project scheduling, quality assurance, and quality control for transmission, distribution, substation, energy storage, system hardening, and system interconnection projects. This group manages projects from preliminary design through energization, ensuring consistent project management responsibility throughout the life of the project. QA/QC support is provided to ensure that all work is built to SDG&E Design and Safety Standards and is in accordance with GO 95 and GO 128 design and construction specifications. Document control and project scheduling helps maintain project timelines and meet schedule goals while ensuring that all documents for projects are labeled and safely stored for the required document retention timeline. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal PORTFOLIO & PROJECT MANAGEMENT |  |  |  | Yes |  |  | 455992.4673 | 0 | 0 | 0 | 455992.4673 | 582000 | 598999.9992 | 616999.9992 | 636000 | 582000 | -126007.5327 | -598999.9992 | -616999.9992 | -636000 | -126007.5327 | -21.65% | -100% | -100% | -100% | -21.65% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | REGIONAL PUBLIC AFFAIRS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1639241.65 | 0 | 0 | 0 | 1639241.65 | 1566000 | 1612999.9992 | 1660999.9992 | 1710999.9996 | 1566000 | 73241.65 | -1612999.9992 | -1660999.9992 | -1710999.9996 | 73241.65 | 4.677% | -100% | -100% | -100% | 4.677% | FTE | 11 |  |  |  | 11 | 11 |  |  |  | 11 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal REGIONAL PUBLIC AFFAIRS |  |  |  | Yes |  |  | 1639241.65 | 0 | 0 | 0 | 1639241.65 | 1566000 | 1612999.9992 | 1660999.9992 | 1710999.9996 | 1566000 | 73241.65 | -1612999.9992 | -1660999.9992 | -1710999.9996 | 73241.65 | 4.677% | -100% | -100% | -100% | 4.677% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | RELIABILITY AND CAPACITY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2281598.8853 | 0 | 0 | 0 | 2281598.8853 | 2785999.9992 | 2869999.9992 | 2955999.9996 | 3045000 | 2785999.9992 | -504401.1139 | -2869999.9992 | -2955999.9996 | -3045000 | -504401.1139 | -18.1% | -100% | -100% | -100% | -18.1% | FTE | 13.3 |  |  |  | 13.3 | 16.5 |  |  |  | 16.5 | -3.2 | 0 | 0 | 0 | -3.2 | -19.39% | 0% | 0% | 0% | -19.39% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal RELIABILITY AND CAPACITY |  |  |  | Yes |  |  | 2281598.8853 | 0 | 0 | 0 | 2281598.8853 | 2785999.9992 | 2869999.9992 | 2955999.9996 | 3045000 | 2785999.9992 | -504401.1139 | -2869999.9992 | -2955999.9996 | -3045000 | -504401.1139 | -18.1% | -100% | -100% | -100% | -18.1% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | SERVICE ORDER TEAM (SOT) | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 7936206.3582 | 0 | 0 | 0 | 7936206.3582 | 4635000 | 4773999.9996 | 4917000 | 5064999.9996 | 4635000 | 3301206.3582 | -4773999.9996 | -4917000 | -5064999.9996 | 3301206.3582 | 71.22% | -100% | -100% | -100% | 71.22% | Service Orders Completed | 11324 |  |  |  | 11324 | 13462 |  |  |  | 13462 | -2138 | 0 | 0 | 0 | -2138 | -15.88% | 0% | 0% | 0% | -15.88% | YES | YES | NO | Decision D.24.09.020, issued September 2024, set compliance timelines for timely energization of certain customer work. In order to meet timelines, extra Service Crews were onboarded. Of note, projects cross multiple years, often submitting applications in one year and completing the related projects 3-9 months after, therefore spanning multiple years. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | The Service Order Team (SOT) is responsible for planning, overseeing and managing new additions and modifications to the electric and gas distribution systems, primarily related to services, acting in the capacity of the SDG&E customer representative for these projects. The O&M costs associated with this team are for its employee training, support of disconnect/reconnect work associated with residential solar, support of utility upgrades related to home remodeling, construction operations for storm recovery, coordinating Communication Infrastructure Providers (CIP) 5G network attachments to utility infrastructure, and support of other replacement of non-capital electrical equipment. The unit that best describes the activities in this workpaper are service orders completed. | SDG&E-12-R-E TS-56 to TS-57 WP 1ED010.000
O&M | ELECTRIC DISTRIBUTION | SubTotal SERVICE ORDER TEAM (SOT) |  |  |  | Yes |  |  | 7936206.3582 | 0 | 0 | 0 | 7936206.3582 | 4635000 | 4773999.9996 | 4917000 | 5064999.9996 | 4635000 | 3301206.3582 | -4773999.9996 | -4917000 | -5064999.9996 | 3301206.3582 | 71.22% | -100% | -100% | -100% | 71.22% | [21 empty] | YES | YES | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1103495.7801 | 0 | 0 | 0 | 1103495.7801 | 1693999.9992 | 1743999.9996 | 1795999.9992 | 1849999.9992 | 1693999.9992 | -590504.2191 | -1743999.9996 | -1795999.9992 | -1849999.9992 | -590504.2191 | -34.86% | -100% | -100% | -100% | -34.86% | FTE | 2.9 |  |  |  | 2.9 | 3.9 |  |  |  | 3.9 | -1 | 0 | 0 | 0 | -1 | -25.64% | 0% | 0% | 0% | -25.64% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Skills Training is responsible for the development and training of the Electric Regional Operations (ERO) workforce, which consists of electric field personnel, non-electrical support personnel, and supervisory staff. The core training provided by this organization consists of the following: electric linemen development using a three-year apprenticeship program; compliance training to meet federal, state, local, safety, and environmental regulations; equipment operations and commercial drivers' training; and providing training support for other business units. Within skills & compliance training, is the Electric Safety Center, which is a group designed to improve the readiness of Company field personnel through enhanced oversight of operations, focused communication, field-based training, data analysis and field safety inspections. The work unit that best describe the activities in this workpaper are FTE and number of classes. | SDG&E-12-R-E TS-51 to TS-56 WP 1ED009.000
O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING | Incident Involving an Employee | Industrial Athletic Trainer | N/A | No | On-going | Annual | 153319.5 | 0 | 0 | 0 | 153319.5 | 27000 | 27999.9996 | 28999.9992 | 30000 | 27000 | 126319.5 | -27999.9996 | -28999.9992 | -30000 | 126319.5 | 467.8% | -100% | -100% | -100% | 467.8% | FTE | 1.7 |  |  |  | 1.7 | 0.3 |  |  |  | 0.3 | 1.4 | 0 | 0 | 0 | 1.4 | 466.7% | 0% | 0% | 0% | 466.7% | YES | NO | YES | N/A | SDG&E hired the Athletic Trainers before the GRC Decision was issued and did not authorize all forecasted positions. | Over (O) | On Target (T) | Over (O) | Expanded | NO | 1.5 Industrial Athletic Trainers in 2024 actuals compared to 0.3 authorized. | Skills Training is responsible for the development and training of the Electric Regional Operations (ERO) workforce, which consists of electric field personnel, non-electrical support personnel, and supervisory staff. The core training provided by this organization consists of the following: electric linemen development using a three-year apprenticeship program; compliance training to meet federal, state, local, safety, and environmental regulations; equipment operations and commercial drivers' training; and providing training support for other business units. Within skills & compliance training, is the Electric Safety Center, which is a group designed to improve the readiness of our field personnel through enhanced oversight of operations, focused communication, field-based training, data analysis and field safety inspections. The work unit that best describe the activities in this workpaper are FTE and number of classes. | SDG&E-12-R-E TS-51 to TS-56 WP 1ED009.000
O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING | Incident Involving an Employee | Personal Protective Equipment | N/A | No | On-going | Annual | 52367.3033 | 0 | 0 | 0 | 52367.3033 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 127999.9992 | -75632.6959 | -132000 | -135999.9996 | -139999.9992 | -75632.6959 | -59.09% | -100% | -100% | -100% | -59.09% | FTE | 4.6 |  |  |  | 4.6 | 4.2 |  |  |  | 4.2 | 0.4 | 0 | 0 | 0 | 0.4 | 9.524% | 0% | 0% | 0% | 9.524% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC DISTRIBUTION | SubTotal SKILLS & COMPLIANCE TRAINING |  |  |  | Yes |  |  | 1309182.5834 | 0 | 0 | 0 | 1309182.5834 | 1848999.9984 | 1903999.9992 | 1960999.998 | 2019999.9984 | 1848999.9984 | -539817.415 | -1903999.9992 | -1960999.998 | -2019999.9984 | -539817.415 | -29.2% | -100% | -100% | -100% | -29.2% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING (TNG) | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 284241.9829 | 0 | 0 | 0 | 284241.9829 | 1273999.9992 | 1311999.9996 | 1350999.9996 | 1390999.9992 | 1273999.9992 | -989758.0163 | -1311999.9996 | -1350999.9996 | -1390999.9992 | -989758.0163 | -77.69% | -100% | -100% | -100% | -77.69% | FTE | 0.8 |  |  |  | 0.8 | 1.9 |  |  |  | 1.9 | -1.1 | 0 | 0 | 0 | -1.1 | -57.89% | 0% | 0% | 0% | -57.89% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | Skills Training is responsible for the development and training of the Electric Regional Operations (ERO) workforce, which consists of electric field personnel, non-electrical support personnel, and supervisory staff. The core training provided by this organization consists of the following: electric linemen development using a three-year apprenticeship program; compliance training to meet federal, state, local, safety, and environmental regulations; equipment operations and commercial drivers' training; and providing training support for other business units. Within skills & compliance training, is the Electric Safety Center, which is a group designed to improve the readiness of our field personnel through enhanced oversight of operations, focused communication, field-based training, data analysis and field safety inspections. The work unit that best describe the activities in this workpaper are FTE and number of classes. | SDG&E-12-R-E TS-51 to TS-56 WP 1ED009.001
O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING (TNG) | Incident Involving an Employee | Personal Protective Equipment | None | No | On-going | Annual | 35131.0315 | 0 | 0 | 0 | 35131.0315 | 121999.9992 | 126000 | 129999.9996 | 133999.9992 | 121999.9992 | -86868.9677 | -126000 | -129999.9996 | -133999.9992 | -86868.9677 | -71.2% | -100% | -100% | -100% | -71.2% | FTE | 0.8 |  |  |  | 0.8 | 1.9 |  |  |  | 1.9 | -1.1 | 0 | 0 | 0 | -1.1 | -57.89% | 0% | 0% | 0% | -57.89% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | Skills Training is responsible for the development and training of the Electric Regional Operations (ERO) workforce, which consists of electric field personnel, non-electrical support personnel, and supervisory staff. The core training provided by this organization consists of the following: electric linemen development using a three-year apprenticeship program; compliance training to meet federal, state, local, safety, and environmental regulations; equipment operations and commercial drivers' training; and providing training support for other business units. Within skills & compliance training, is the Electric Safety Center, which is a group designed to improve the readiness of our field personnel through enhanced oversight of operations, focused communication, field-based training, data analysis and field safety inspections. The work unit that best describe the activities in this workpaper are FTE and number of classes. | SDG&E-12-R-E TS-51 to TS-56 WP 1ED009.001
O&M | ELECTRIC DISTRIBUTION | SubTotal SKILLS & COMPLIANCE TRAINING (TNG) |  |  |  | Yes |  |  | 319373.0145 | 0 | 0 | 0 | 319373.0145 | 1395999.9984 | 1437999.9996 | 1480999.9992 | 1524999.9984 | 1395999.9984 | -1076626.984 | -1437999.9996 | -1480999.9992 | -1524999.9984 | -1076626.984 | -77.12% | -100% | -100% | -100% | -77.12% | [21 empty] | YES | NO | [7 empty] | NO

## EOEG
SDG&E ELECTRIC GENERATION O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | ELECTRIC GENERATION | ELECTRIC GENERATION |  |  |  | Yes |  |  | 40194579.3236 | 0 | 0 | 0 | 40194579.3236 | 43022999.9976 | 44312999.9964 | 45641999.9976 | 47010999.9972 | 43022999.9976 | -2828420.674 | -44312999.9964 | -45641999.9976 | -47010999.9972 | -2828420.674 | -6.574% | -100% | -100% | -100% | -6.574%
O&M | ELECTRIC GENERATION | GENERATION - PLANT - ADMIN | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 296993.7081 | 0 | 0 | 0 | 296993.7081 | 292999.9992 | 301999.9992 | 310999.9992 | 319999.9992 | 292999.9992 | 3993.7089 | -301999.9992 | -310999.9992 | -319999.9992 | 3993.7089 | 1.363% | -100% | -100% | -100% | 1.363% | FTE | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC GENERATION | SubTotal GENERATION - PLANT - ADMIN |  |  |  | Yes |  |  | 296993.7081 | 0 | 0 | 0 | 296993.7081 | 292999.9992 | 301999.9992 | 310999.9992 | 319999.9992 | 292999.9992 | 3993.7089 | -301999.9992 | -310999.9992 | -319999.9992 | 3993.7089 | 1.363% | -100% | -100% | -100% | 1.363% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC GENERATION | GENERATION DISTRIBUTED ENERGY FACILITIES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1433003.0709 | 0 | 0 | 0 | 1433003.0709 | 1569000 | 1615999.9992 | 1663999.9992 | 1713999.9996 | 1569000 | -135996.9291 | -1615999.9992 | -1663999.9992 | -1713999.9996 | -135996.9291 | -8.668% | -100% | -100% | -100% | -8.668% | MWh Discharge | 292096 |  |  |  | 292096 | 317808 |  |  |  | 317808 | -25712 | 0 | 0 | 0 | -25712 | -8.09% | 0% | 0% | 0% | -8.09% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC GENERATION | SubTotal GENERATION DISTRIBUTED ENERGY FACILITIES |  |  |  | Yes |  |  | 1433003.0709 | 0 | 0 | 0 | 1433003.0709 | 1569000 | 1615999.9992 | 1663999.9992 | 1713999.9996 | 1569000 | -135996.9291 | -1615999.9992 | -1663999.9992 | -1713999.9996 | -135996.9291 | -8.668% | -100% | -100% | -100% | -8.668% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC GENERATION | GENERATION PLANT CUYAMACA PEAK | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1321663.5596 | 0 | 0 | 0 | 1321663.5596 | 1077999.9996 | 1110000 | 1143000 | 1176999.9996 | 1077999.9996 | 243663.56 | -1110000 | -1143000 | -1176999.9996 | 243663.56 | 22.6% | -100% | -100% | -100% | 22.6% | Plant Equivalent Operating Hours | 3314 |  |  |  | 3314 | 11565 |  |  |  | 11565 | -8251 | 0 | 0 | 0 | -8251 | -71.34% | 0% | 0% | 0% | -71.34% | YES | NO | YES | N/A | Underrun in plant equivalent operating hours is due to Cuyamaca Plant dispatched less in 2024 causing lower number of starts and service hours. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Generation Plant Cuyamaca Peak encompasses the operation and maintenance of the peaking plant at the Cuyamaca Peak Energy Plant (CPEP). The labor component includes salaries for supervision, support staff and maintenance and operations personnel. The non-labor component includes, but is not limited to, industrial gases, chemicals, water, outside services, spare parts, miscellaneous consumables and maintenance activities. Maintenance activities are performed while the plant is operating and during planned maintenance outages. | SDG&E-14-E DSB-12 WP 1EG007.000
O&M | Electric Generation | SubTotal GENERATION PLANT CUYAMACA PEAK |  |  |  | Yes |  |  | 1321663.5596 | 0 | 0 | 0 | 1321663.5596 | 1077999.9996 | 1110000 | 1143000 | 1176999.9996 | 1077999.9996 | 243663.56 | -1110000 | -1143000 | -1176999.9996 | 243663.56 | 22.6% | -100% | -100% | -100% | 22.6% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC GENERATION | GENERATION PLANT DESERT STAR | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 15597905.01 | 0 | 0 | 0 | 15597905.01 | 15979999.9992 | 16458999.9996 | 16953000 | 17461999.9992 | 15979999.9992 | -382094.9892 | -16458999.9996 | -16953000 | -17461999.9992 | -382094.9892 | -2.391% | -100% | -100% | -100% | -2.391% | Plant Equivalent Operating Hours | 18160 |  |  |  | 18160 | 17985 |  |  |  | 17985 | 175 | 0 | 0 | 0 | 175 | 0.973% | 0% | 0% | 0% | 0.973% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ELECTRIC GENERATION | SubTotal GENERATION PLANT DESERT STAR |  |  |  | Yes |  |  | 15597905.01 | 0 | 0 | 0 | 15597905.01 | 15979999.9992 | 16458999.9996 | 16953000 | 17461999.9992 | 15979999.9992 | -382094.9892 | -16458999.9996 | -16953000 | -17461999.9992 | -382094.9892 | -2.391% | -100% | -100% | -100% | -2.391% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC GENERATION | GENERATION PLANT MIRAMAR | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1416401.2311 | 0 | 0 | 0 | 1416401.2311 | 2175000 | 2239999.9992 | 2307000 | 2376000 | 2175000 | -758598.7689 | -2239999.9992 | -2307000 | -2376000 | -758598.7689 | -34.88% | -100% | -100% | -100% | -34.88% | Plant Equivalent Operating Hours | 2636 |  |  |  | 2636 | 24863 |  |  |  | 24863 | -22227 | 0 | 0 | 0 | -22227 | -89.4% | 0% | 0% | 0% | -89.4% | YES | NO | YES | N/A | Underrun in plant equivalent operating hours is due to Miramar Plant dispatched less in 2024 causing lower number of starts and service hours. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Generation Plant Miramar encompasses the operation and maintenance of 2 peaking plants at the Miramar Energy Facility (MEF). Labor costs includes salaries for supervision, support staff and maintenance and operations personnel. Non-labor costs include, but is not limited to, industrial gases, chemicals, water, outside services, spare parts, miscellaneous consumables and maintenance activities. Maintenance activities are performed while the plant is operating and during planned maintenance outages. | SDG&E-14-E DSB-11 to DSB-12 WP 1EG002.000
O&M | ELECTRIC GENERATION | SubTotal GENERATION PLANT MIRAMAR |  |  |  | Yes |  |  | 1416401.2311 | 0 | 0 | 0 | 1416401.2311 | 2175000 | 2239999.9992 | 2307000 | 2376000 | 2175000 | -758598.7689 | -2239999.9992 | -2307000 | -2376000 | -758598.7689 | -34.88% | -100% | -100% | -100% | -34.88% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ELECTRIC GENERATION | GENERATION PLANT PALOMAR | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 20128612.7439 | 0 | 0 | 0 | 20128612.7439 | 21927999.9996 | 22585999.9992 | 23263999.9992 | 23961999.9996 | 21927999.9996 | -1799387.2557 | -22585999.9992 | -23263999.9992 | -23961999.9996 | -1799387.2557 | -8.206% | -100% | -100% | -100% | -8.206% | Plant Equivalent Operating Hours | 13428 |  |  |  | 13428 | 25427 |  |  |  | 25427 | -11999 | 0 | 0 | 0 | -11999 | -47.19% | 0% | 0% | 0% | -47.19% | YES | NO | YES | N/A | Underrun in plant equivalent operating hours is primarily due to Palomar Energy Center operations being restricted by a regional gas curtailment (4/09/2024 - 6/11/2024). The curtailment caused the plant to have lower starts and service hours. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Generation Plant Palomar encompasses the operation and maintenance of the Combined Cycle Generating Plant at Palomar Energy Center. Labor costs include salaries for supervision, support staff and maintenance and operations personnel. Non-labor costs include, but is not limited to, industrial gases, chemicals, water, outside services, spare parts, miscellaneous consumables and maintenance activities. Maintenance activities are performed while the plant is operating and during planned maintenance outages. | SDG&E-14-E DSB-10 WP 1EG003.000
O&M | ELECTRIC GENERATION | SubTotal GENERATION PLANT PALOMAR |  |  |  | Yes |  |  | 20128612.7439 | 0 | 0 | 0 | 20128612.7439 | 21927999.9996 | 22585999.9992 | 23263999.9992 | 23961999.9996 | 21927999.9996 | -1799387.2557 | -22585999.9992 | -23263999.9992 | -23961999.9996 | -1799387.2557 | -8.206% | -100% | -100% | -100% | -8.206% | [21 empty] | YES | NO | [7 empty] | NO

## EODD
SDG&E CLEAN ENERGY INNOVATIONS O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CLEAN ENERGY INNOVATIONS | CLEAN ENERGY INNOVATIONS |  |  |  | Yes |  |  | 3664738.5544 | 0 | 0 | 0 | 3664738.5544 | 3278999.9988 | 3376999.9992 | 3478999.9992 | 3582999.9984 | 3278999.9988 | 385738.5556 | -3376999.9992 | -3478999.9992 | -3582999.9984 | 385738.5556 | 11.76% | -100% | -100% | -100% | 11.76%
O&M | CLEAN ENERGY INNOVATIONS | ADVANCED CLEAN TECHNOLOGY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1817365.1882 | 0 | 0 | 0 | 1817365.1882 | 1377999.9996 | 1419000 | 1461999.9996 | 1506000 | 1377999.9996 | 439365.1886 | -1419000 | -1461999.9996 | -1506000 | 439365.1886 | 31.88% | -100% | -100% | -100% | 31.88% | FTE | 7.7 |  |  |  | 7.7 | 7 |  |  |  | 7 | 0.7 | 0 | 0 | 0 | 0.7 | 10% | 0% | 0% | 0% | 10% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CLEAN ENERGY INNOVATIONS | SubTotal ADVANCED CLEAN TECHNOLOGY |  |  |  | Yes |  |  | 1817365.1882 | 0 | 0 | 0 | 1817365.1882 | 1377999.9996 | 1419000 | 1461999.9996 | 1506000 | 1377999.9996 | 439365.1886 | -1419000 | -1461999.9996 | -1506000 | 439365.1886 | 31.88% | -100% | -100% | -100% | 31.88% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CLEAN ENERGY INNOVATIONS | DISTRIBUTED ENERGY RESOURCE ENGINEERING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 877497.0223 | 0 | 0 | 0 | 877497.0223 | 1204999.9992 | 1240999.9992 | 1278000 | 1315999.9992 | 1204999.9992 | -327502.9769 | -1240999.9992 | -1278000 | -1315999.9992 | -327502.9769 | -27.18% | -100% | -100% | -100% | -27.18% | This activity consists of support for the Borrego Microgrid, Carmel Valley, Ortega Highway, and all the testing equipment and licenses at the Integrated Test Facility. The non-labor supports battery/inverter/HVAC maintenance, parts, services, fire suppression bi-annual testing, generator source testing and fuel. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CLEAN ENERGY INNOVATIONS | SubTotal DISTRIBUTED ENERGY RESOURCE ENGINEERING |  |  |  | Yes |  |  | 877497.0223 | 0 | 0 | 0 | 877497.0223 | 1204999.9992 | 1240999.9992 | 1278000 | 1315999.9992 | 1204999.9992 | -327502.9769 | -1240999.9992 | -1278000 | -1315999.9992 | -327502.9769 | -27.18% | -100% | -100% | -100% | -27.18% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CLEAN ENERGY INNOVATIONS | HYDROGEN STRATEGY AND IMPLEMENTATION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 652459.3439 | 0 | 0 | 0 | 652459.3439 | 696000 | 717000 | 738999.9996 | 760999.9992 | 696000 | -43540.6561 | -717000 | -738999.9996 | -760999.9992 | -43540.6561 | -6.256% | -100% | -100% | -100% | -6.256% | FTE | 3.18 |  |  |  | 3.18 | 4 |  |  |  | 4 | -0.82 | 0 | 0 | 0 | -0.82 | -20.5% | 0% | 0% | 0% | -20.5% | YES | NO | YES | N/A | In 2024, the Hydrogen Strategy & Implementation Department had lower than forecasted staffing levels due to an employee retiring. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Hydrogen Strategy and Implementation department is responsible for understanding, developing, incorporating, and leading clean hydrogen projects into the company's electric, gas, and internal operations as part of SDG&E's sustainability strategy and supporting customer adoption of hydrogen technologies. As this is a newly created department, additional staff are required to support the state's goals of decarbonization and utilizing hydrogen technologies as one of the many solutions. Request for non-labor funding to support additional modeling and surveys performed to improve knowledge base on various aspects of hydrogen technologies and adoption. | SDG&E-15-R-E FV-5 to FV-8 WP 1DD001
O&M | CLEAN ENERGY INNOVATIONS | SubTotal HYDROGEN STRATEGY AND IMPLEMENTATION |  |  |  | Yes |  |  | 652459.3439 | 0 | 0 | 0 | 652459.3439 | 696000 | 717000 | 738999.9996 | 760999.9992 | 696000 | -43540.6561 | -717000 | -738999.9996 | -760999.9992 | -43540.6561 | -6.256% | -100% | -100% | -100% | -6.256% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CLEAN ENERGY INNOVATIONS | SUSTAINABLE COMMUNITIES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 317417 | 0 | 0 | 0 | 317417 | 0 | 0 | 0 | 0 | 0 | 317417 | 0 | 0 | 0 | 317417 | 100% | 0% | 0% | 0% | 100% | Leases | 21 |  |  |  | 21 | 0 |  |  |  | 0 | 21 | 0 | 0 | 0 | 21 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Lease payments are from lease obligations that were entered into prior to this GRC. No lease extensions have been signed. | Over (O) | Over (O) | Over (O) | Other | NO | Lease payments and service maintenance agreements are from obligations that were entered into prior to this GRC. No lease extensions have been signed. | The Sustainable Community Program (SCP) has been open since 2004 as authorized by D.04-12-015. While the program now is closed to enrollment, lease payments and operations and maintenance expenses associated with maintaining the assets are required as part of SDG&E's obligations under the exisitng lease agreements with the community members. | SDG&E-15-R-E FV-14 to FV-15 WP 1DD004
O&M | CLEAN ENERGY INNOVATIONS | SubTotal SUSTAINABLE COMMUNITIES |  |  |  | Yes |  |  | 317417 | 0 | 0 | 0 | 317417 | 0 | 0 | 0 | 0 | 0 | 317417 | 0 | 0 | 0 | 317417 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO

## EOCT
SDG&E CLEAN TRANSPORTATION O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CLEAN TRANSPORTATION | CLEAN TRANSPORTATION |  |  |  | Yes |  |  | 4271808.5298 | 0 | 0 | 0 | 4271808.5298 | 4921999.9992 | 5070000 | 5221999.9992 | 5379000 | 4921999.9992 | -650191.4694 | -5070000 | -5221999.9992 | -5379000 | -650191.4694 | -13.21% | -100% | -100% | -100% | -13.21%
O&M | CLEAN TRANSPORTATION | CLEAN TRANSPORTATION - NSS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 4271808.5298 | 0 | 0 | 0 | 4271808.5298 | 4921999.9992 | 5070000 | 5221999.9992 | 5379000 | 4921999.9992 | -650191.4694 | -5070000 | -5221999.9992 | -5379000 | -650191.4694 | -13.21% | -100% | -100% | -100% | -13.21% | FTE | 13.89 |  |  |  | 13.89 | 14.7 |  |  |  | 14.7 | -0.81 | 0 | 0 | 0 | -0.81 | -5.51% | 0% | 0% | 0% | -5.51% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CLEAN TRANSPORTATION | SubTotal CLEAN TRANSPORTATION - NSS |  |  |  | Yes |  |  | 4271808.5298 | 0 | 0 | 0 | 4271808.5298 | 4921999.9992 | 5070000 | 5221999.9992 | 5379000 | 4921999.9992 | -650191.4694 | -5070000 | -5221999.9992 | -5379000 | -650191.4694 | -13.21% | -100% | -100% | -100% | -13.21% | [21 empty] | YES | NO | [7 empty] | NO

## EOEP
SDG&E ENERGY PROCUREMENT O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | ENERGY PROCUREMENT | ENERGY PROCUREMENT |  |  |  | Yes |  |  | 9346987.0548 | 0 | 0 | 0 | 9346987.0548 | 10601999.9988 | 10919999.9988 | 11246999.9976 | 11583999.9984 | 10601999.9988 | -1255012.944 | -10919999.9988 | -11246999.9976 | -11583999.9984 | -1255012.944 | -11.84% | -100% | -100% | -100% | -11.84%
O&M | SDG&E ENERGY PROCUREMENT | BACK OFFICE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 4606002.58 | 0 | 0 | 0 | 4606002.58 | 4008999.9996 | 4128999.9996 | 4252999.9992 | 4380999.9996 | 4008999.9996 | 597002.5804 | -4128999.9996 | -4252999.9992 | -4380999.9996 | 597002.5804 | 14.89% | -100% | -100% | -100% | 14.89% | FTE | 18.4 |  |  |  | 18.4 | 17.1 |  |  |  | 17.1 | 1.3 | 0 | 0 | 0 | 1.3 | 7.602% | 0% | 0% | 0% | 7.602% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SDG&E ENERGY PROCUREMENT | SubTotal BACK OFFICE |  |  |  | Yes |  |  | 4606002.58 | 0 | 0 | 0 | 4606002.58 | 4008999.9996 | 4128999.9996 | 4252999.9992 | 4380999.9996 | 4008999.9996 | 597002.5804 | -4128999.9996 | -4252999.9992 | -4380999.9996 | 597002.5804 | 14.89% | -100% | -100% | -100% | 14.89% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SDG&E ENERGY PROCUREMENT | ENERGY SUPPLY & DISPATCH | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2205089.4608 | 0 | 0 | 0 | 2205089.4608 | 2434999.9992 | 2508000 | 2583000 | 2659999.9992 | 2434999.9992 | -229910.5384 | -2508000 | -2583000 | -2659999.9992 | -229910.5384 | -9.442% | -100% | -100% | -100% | -9.442% | FTE | 14.8 |  |  |  | 14.8 | 15.8 |  |  |  | 15.8 | -1 | 0 | 0 | 0 | -1 | -6.329% | 0% | 0% | 0% | -6.329% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SDG&E ENERGY PROCUREMENT | SubTotal ENERGY SUPPLY & DISPATCH |  |  |  | Yes |  |  | 2205089.4608 | 0 | 0 | 0 | 2205089.4608 | 2434999.9992 | 2508000 | 2583000 | 2659999.9992 | 2434999.9992 | -229910.5384 | -2508000 | -2583000 | -2659999.9992 | -229910.5384 | -9.442% | -100% | -100% | -100% | -9.442% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SDG&E ENERGY PROCUREMENT | ORIGINATION & PORTFOLIO DESIGN | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1755781.9505 | 0 | 0 | 0 | 1755781.9505 | 2799000 | 2883000 | 2968999.9992 | 3057999.9996 | 2799000 | -1043218.0495 | -2883000 | -2968999.9992 | -3057999.9996 | -1043218.0495 | -37.27% | -100% | -100% | -100% | -37.27% | FTE | 8.9 |  |  |  | 8.9 | 15.4 |  |  |  | 15.4 | -6.5 | 0 | 0 | 0 | -6.5 | -42.21% | 0% | 0% | 0% | -42.21% | YES | NO | YES | N/A | The variance in FTEs is primarily driven by lower than forecasted staffing levels due to employee attrition and workforce turnover within Origination and Portfolio Design. This includes the impact of organizational changes involving the Origination and Portfolio Design and Resource Planning groups. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Origination & Portfolio Design (O&PD) functions include the Vice President of Energy Procurement and Sustainability, and the O&PD department. The Vice President is responsible for providing strategic direction consistent with and complementary to SDG&E’s wider mission, developing policies to strengthen and enhance energy supply functions and performance, and ensuring that all energy procurement is conducted consistent with internal requirements, Commission rules and decisions, and CAISO tariffs. Competitive solicitations are conducted by issuing a Request for Offers (RFO) to potential counterparties, developing a valuation model and methodology, evaluating bids submitted, and selecting the most cost-effective resources to meet the RFO objectives. Following the solicitation activities, O&PD then negotiates with independent suppliers who have winning bidders to execute final contracts. Bid evaluation, bid selection, and contract negotiation practices and principles for RFOs are similar to those for bilateral negotiations. Once contracts have been executed, O&PD is also responsible for preparing, and filing and litigating the application or advice letter requesting CPUC approval of the contract(s). Market & Policy group is responsible for policy and implementation issues including CAISO interface, policy and strategic decisions regarding CAISO market policy and initiatives and various CPUC initiatives. The group works with policy experts to develop and execute long-term strategic plans, monitors changes to CPUC regulations and requirements governing least-cost dispatch of SDG&E’s generation portfolio and manages CPUC related issues and decision that impact Energy Supply & Dispatch and in that capacity work with Regulatory on development of policy and filings in the various CPUC proceedings. | SDG&E-10 CAS-6 to CAS-14 WP 1EP001.000
O&M | SDG&E ENERGY PROCUREMENT | SubTotal ORIGINATION & PORTFOLIO DESIGN |  |  |  | Yes |  |  | 1755781.9505 | 0 | 0 | 0 | 1755781.9505 | 2799000 | 2883000 | 2968999.9992 | 3057999.9996 | 2799000 | -1043218.0495 | -2883000 | -2968999.9992 | -3057999.9996 | -1043218.0495 | -37.27% | -100% | -100% | -100% | -37.27% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SDG&E ENERGY PROCUREMENT | RESOURCE PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 780113.0635 | 0 | 0 | 0 | 780113.0635 | 1359000 | 1399999.9992 | 1441999.9992 | 1485000 | 1359000 | -578886.9365 | -1399999.9992 | -1441999.9992 | -1485000 | -578886.9365 | -42.6% | -100% | -100% | -100% | -42.6% | FTE | 5.9 |  |  |  | 5.9 | 6.9 |  |  |  | 6.9 | -1 | 0 | 0 | 0 | -1 | -14.49% | 0% | 0% | 0% | -14.49% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SDG&E ENERGY PROCUREMENT | SubTotal RESOURCE PLANNING |  |  |  | Yes |  |  | 780113.0635 | 0 | 0 | 0 | 780113.0635 | 1359000 | 1399999.9992 | 1441999.9992 | 1485000 | 1359000 | -578886.9365 | -1399999.9992 | -1441999.9992 | -1485000 | -578886.9365 | -42.6% | -100% | -100% | -100% | -42.6% | [21 empty] | YES | NO | [7 empty] | NO

## GOGD
SDG&E GAS DISTRIBUTION O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | GAS DISTRIBUTION | GAS DISTRIBUTION |  |  |  | Yes |  |  | 43708794.0826 | 0 | 0 | 0 | 43708794.0826 | 37006999.9872 | 38116999.9884 | 39259999.986 | 40436999.988 | 37006999.9872 | 6701794.0954 | -38116999.9884 | -39259999.986 | -40436999.988 | 6701794.0954 | 18.11% | -100% | -100% | -100% | 18.11%
O&M | GAS DISTRIBUTION | ASSET MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 459604.1338 | 0 | 0 | 0 | 459604.1338 | 693000 | 712999.9992 | 733999.9992 | 756000 | 693000 | -233395.8662 | -712999.9992 | -733999.9992 | -756000 | -233395.8662 | -33.68% | -100% | -100% | -100% | -33.68% | These activities include time spent by personnel to support the technical office associated with identifying construction design requirements. Examples of work include evaluating pressure specifications, providing project drawings, and identifying material selection. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | ASSET MANAGEMENT | Asset Management | AIM (Gov, Strat, AIP) | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 123999.9996 | 127999.9992 | 132000 | 135999.9996 | 123999.9996 | -123999.9996 | -127999.9992 | -132000 | -135999.9996 | -123999.9996 | -100% | -100% | -100% | -100% | -100% | FTE | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Variance is due to the timing of hiring one Asset Strategy Advisor. | On Target (T) | Under (U) | Under (U) | Deferred | NO | N/A | This workgroup records the labor and non-labor costs for services provided by SDG&E’s Gas Design, Project Management, Engineering, and Geographic Information Systems groups. These groups provide many of the technical and administrative services needed for the successful and timely completion of the O&M activities in Gas Distribution. Activities performed by this office include items such as identifying construction design requirements, evaluating pressure specifications, conducting pipeline planning, providing project drawings, identifying material selection, preparing work order estimates, acquiring third-party contract services, developing and maintaining pipeline and pipeline component mapped records in the GIS system, processing as-built drawings from the field to create a final record of pipeline system additions and changes, and obtaining permits for construction from city, county, state, and federal agencies. | SDGE-04-R-E LPK-54 to LPK-59 WP 1GD009.000
O&M | GAS DISTRIBUTION | ASSET MANAGEMENT | Records Management | Gas Geographic Information System | N/A | No | On-going | Annual | 686928.9856 | 0 | 0 | 0 | 686928.9856 | 730999.9992 | 752999.9988 | 775999.9992 | 798999.9984 | 730999.9992 | -44071.0136 | -752999.9988 | -775999.9992 | -798999.9984 | -44071.0136 | -6.029% | -100% | -100% | -100% | -6.029% | Reconciled work orders | 3366 |  |  |  | 3366 | 2957 |  |  |  | 2957 | 409 | 0 | 0 | 0 | 409 | 13.83% | 0% | 0% | 0% | 13.83% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | SubTotal ASSET MANAGEMENT |  |  |  | Yes |  |  | 1146533.1194 | 0 | 0 | 0 | 1146533.1194 | 1547999.9988 | 1593999.9972 | 1641999.9984 | 1690999.998 | 1547999.9988 | -401466.8794 | -1593999.9972 | -1641999.9984 | -1690999.998 | -401466.8794 | -25.93% | -100% | -100% | -100% | -25.93% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection - O&M | HP Supply Line | No | On-going | Annual | 393161.6642 | 0 | 0 | 0 | 393161.6642 | 111999.9996 | 114999.9996 | 117999.9996 | 121999.9992 | 111999.9996 | 281161.6646 | -114999.9996 | -117999.9996 | -121999.9992 | 281161.6646 | 251% | -100% | -100% | -100% | 251% | High pressure reads | 1262 |  |  |  | 1262 | 1182 |  |  |  | 1182 | 80 | 0 | 0 | 0 | 80 | 6.768% | 0% | 0% | 0% | 6.768% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection - O&M | MP Main Steel | No | On-going | Annual | 1914354.3729 | 0 | 0 | 0 | 1914354.3729 | 1954999.9992 | 2013999.9996 | 2074999.9992 | 2136999.9996 | 1954999.9992 | -40645.6263 | -2013999.9996 | -2074999.9992 | -2136999.9996 | -40645.6263 | -2.079% | -100% | -100% | -100% | -2.079% | Medium pressure reads | 22114 |  |  |  | 22114 | 20706 |  |  |  | 20706 | 1408 | 0 | 0 | 0 | 1408 | 6.8% | 0% | 0% | 0% | 6.8% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | SubTotal CATHODIC PROTECTION |  |  |  | Yes |  |  | 2307516.037 | 0 | 0 | 0 | 2307516.037 | 2066999.9988 | 2128999.9992 | 2192999.9988 | 2258999.9988 | 2066999.9988 | 240516.0382 | -2128999.9992 | -2192999.9988 | -2258999.9988 | 240516.0382 | 11.64% | -100% | -100% | -100% | 11.64% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | ELECTRIC SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 755969.7413 | 0 | 0 | 0 | 755969.7413 | 559999.9992 | 576999.9996 | 594000 | 612000 | 559999.9992 | 195969.7421 | -576999.9996 | -594000 | -612000 | 195969.7421 | 34.99% | -100% | -100% | -100% | 34.99% | The variety and scope of work for electric support (Gas Crew and Street Repair support primarily their Corrective Maintenance Program, the Quality Control Repairs and Inspection Program, the restoration of outage, and transformer change outs) makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | SubTotal ELECTRIC SUPPORT |  |  |  | Yes |  |  | 755969.7413 | 0 | 0 | 0 | 755969.7413 | 559999.9992 | 576999.9996 | 594000 | 612000 | 559999.9992 | 195969.7421 | -576999.9996 | -594000 | -612000 | 195969.7421 | 34.99% | -100% | -100% | -100% | 34.99% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | LEAK SURVEY | Incident Related to the Medium Pressure System (Excluding Dig-in) | Pipeline Monitoring (Leak Mitigation, Bridge & Span, Unstable Earth, and Pipeline Patrol | HP Transmission | No | On-going | Annual | 56144.508 | 0 | 0 | 0 | 56144.508 | 27000 | 27999.9996 | 28999.9992 | 30000 | 27000 | 29144.508 | -27999.9996 | -28999.9992 | -30000 | 29144.508 | 107.9% | -100% | -100% | -100% | 107.9% | Miles surveyed | 354 |  |  |  | 354 | 360 |  |  |  | 360 | -6 | 0 | 0 | 0 | -6 | -1.667% | 0% | 0% | 0% | -1.667% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | LEAK SURVEY | Incident Related to the Medium Pressure System (Excluding Dig-in) | Pipeline Monitoring (Leak Mitigation, Bridge & Span, Unstable Earth, and Pipeline Patrol | MP Overall | No | On-going | Annual | 2700732.1707 | 0 | 0 | 0 | 2700732.1707 | 2304000 | 2373000 | 2443999.9992 | 2517000 | 2304000 | 396732.1707 | -2373000 | -2443999.9992 | -2517000 | 396732.1707 | 17.22% | -100% | -100% | -100% | 17.22% | Inspections & surveys | 972 |  |  |  | 972 | 940 |  |  |  | 940 | 32 | 0 | 0 | 0 | 32 | 3.404% | 0% | 0% | 0% | 3.404% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | SubTotal LEAK SURVEY |  |  |  | Yes |  |  | 2756876.6787 | 0 | 0 | 0 | 2756876.6787 | 2331000 | 2400999.9996 | 2472999.9984 | 2547000 | 2331000 | 425876.6787 | -2400999.9996 | -2472999.9984 | -2547000 | 425876.6787 | 18.27% | -100% | -100% | -100% | 18.27% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2164837.1412 | 0 | 0 | 0 | 2164837.1412 | 2977999.9992 | 3066999.9996 | 3159000 | 3253999.9992 | 2977999.9992 | -813162.858 | -3066999.9996 | -3159000 | -3253999.9992 | -813162.858 | -27.31% | -100% | -100% | -100% | -27.31% | The variety and scope of work for main maintenance (moving, lowering, raising gas mains, vaults, valves, and related structures) makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The costs associated with Non-RAMP main maintenance was shifted to address Abnormal Operating Conditions (AOC) associated with service maintenance, which can be seen with the increase in cost in Non-RAMP service maintenance. | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | Main maintenance work is generally corrective in nature and is required to keep the natural gas system operating safely and reliably. The work in this workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F, pipeline safety regulations and to extend the life of distribution main pipelines and related infrastructure. Main maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution mains as well as moving, lowering, and raising short sections of gas distribution mains, vaults, valves, and related structures. This group includes the Main Maintenance portion of RAMP (SDG&E-Risk-9, C06): Leak Repair, and (SDG&E-Risk-9, C11): Gas Distribution Emergency Department. | SDGE-04-R-E LPK-35 to LPK-38 WP 1GD003.000
O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Gas Distribution Emergency Department - Main Portion | MP Main Steel & Plastic | No | On-going | Annual | 1299794.2833 | 0 | 0 | 0 | 1299794.2833 | 1296999.9996 | 1335999.9996 | 1375999.9992 | 1416999.9996 | 1296999.9996 | 2794.2837 | -1335999.9996 | -1375999.9992 | -1416999.9996 | 2794.2837 | 0.2154% | -100% | -100% | -100% | 0.2154% | Responses | 402 |  |  |  | 402 | 619 |  |  |  | 619 | -217 | 0 | 0 | 0 | -217 | -35.06% | 0% | 0% | 0% | -35.06% | YES | NO | YES | N/A | This activity covers the response of the Gas Distribution Emergency Department (GED) to leaks and Dig-In’s on the gas system mains. The variety and frequency of these responses are based on factors outside of SDG&E control (i.e., third party leaks) and vary year to year. The number of responses forecasted did not materialize in 2024. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Main maintenance work is generally corrective in nature and is required to keep the natural gas system operating safely and reliably. The work in this workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F, pipeline safety regulations and to extend the life of distribution main pipelines and related infrastructure. Main maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution mains as well as moving, lowering, and raising short sections of gas distribution mains, vaults, valves, and related structures. This group includes the Main Maintenance portion of RAMP (SDG&E-Risk-9, C06): Leak Repair, and (SDG&E-Risk-9, C11): Gas Distribution Emergency Department. | SDGE-04-R-E LPK-35 to LPK-38 WP 1GD003.000
O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Main Portion | MP Main Plastic | No | On-going | Annual | 479824.3946 | 0 | 0 | 0 | 479824.3946 | 369999.9996 | 381000 | 391999.9992 | 403999.9992 | 369999.9996 | 109824.395 | -381000 | -391999.9992 | -403999.9992 | 109824.395 | 29.68% | -100% | -100% | -100% | 29.68% | Projects | 65 |  |  |  | 65 | 90 |  |  |  | 90 | -25 | 0 | 0 | 0 | -25 | -27.78% | 0% | 0% | 0% | -27.78% | YES | NO | YES | N/A | This activity covers the repair of leaks on plastic mains. The frequency of these leaks are based on factors outside of SDG&E control (i.e., third party leaks) and vary year to year. The number of leaks forecasted for repaired on plastic mains did not materialize in 2024. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Main maintenance work is generally corrective in nature and is required to keep the natural gas system operating safely and reliably. The work in this workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F, pipeline safety regulations and to extend the life of distribution main pipelines and related infrastructure. Main maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution mains as well as moving, lowering, and raising short sections of gas distribution mains, vaults, valves, and related structures. This group includes the Main Maintenance portion of RAMP (SDG&E-Risk-9, C06): Leak Repair, and (SDG&E-Risk-9, C11): Gas Distribution Emergency Department. | SDGE-04-R-E LPK-35 to LPK-38 WP 1GD003.000
O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Main Portion | MP Main Steel | No | On-going | Annual | 719736.592 | 0 | 0 | 0 | 719736.592 | 637999.9992 | 657000 | 676999.9992 | 696999.9996 | 637999.9992 | 81736.5928 | -657000 | -676999.9992 | -696999.9996 | 81736.5928 | 12.81% | -100% | -100% | -100% | 12.81% | Projects | 111 |  |  |  | 111 | 156 |  |  |  | 156 | -45 | 0 | 0 | 0 | -45 | -28.85% | 0% | 0% | 0% | -28.85% | YES | NO | YES | N/A | This activity covers the repair of repair of leaks on steel mains. The frequency of these leaks are based on factors outside of SDG&E control (i.e., third party leaks) and vary year to year. The number of leaks forecasted for repaired on steel mains did not materialize in 2024. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Main maintenance work is generally corrective in nature and is required to keep the natural gas system operating safely and reliably. The work in this workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F, pipeline safety regulations and to extend the life of distribution main pipelines and related infrastructure. Main maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution mains as well as moving, lowering, and raising short sections of gas distribution mains, vaults, valves, and related structures. This group includes the Main Maintenance portion of RAMP (SDG&E-Risk-9, C06): Leak Repair, and (SDG&E-Risk-9, C11): Gas Distribution Emergency Department. | SDGE-04-R-E LPK-35 to LPK-38 WP 1GD003.000
O&M | GAS DISTRIBUTION | SubTotal MAIN MAINTENANCE |  |  |  | Yes |  |  | 4664192.4111 | 0 | 0 | 0 | 4664192.4111 | 5282999.9976 | 5440999.9992 | 5603999.9976 | 5771999.9976 | 5282999.9976 | -618807.5865 | -5440999.9992 | -5603999.9976 | -5771999.9976 | -618807.5865 | -11.71% | -100% | -100% | -100% | -11.71% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1570073.5924 | 0 | 0 | 0 | 1570073.5924 | 772999.9992 | 795999.9996 | 819999.9996 | 844999.9992 | 772999.9992 | 797073.5932 | -795999.9996 | -819999.9996 | -844999.9992 | 797073.5932 | 103.1% | -100% | -100% | -100% | 103.1% | The variety and scope of work for Measurement and Regulations (Liquified Natural Gas facility maintenance and inspections, Compressed Natural Gas facility maintenance and inspection, planned large meter change outs, odor checks, and regulator station repairs) makes it infeasible to identify a signle unit of measurement. | [20 empty] | YES | YES | NO | This variance is attributed to shift in dollars away from Control Center Modernization to address Abnormal Operating Conditions (AOC). on the gas system which were identified during mapping reviews and during pipeline patrols. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This group includes the cost of labor, materials used, and expenses incurred in inspecting and maintaining large gas meters and their Meter Set Assemblies (MSAs), gas instruments, company Compressed Natural Gas (CNG) facilities, inspection and maintenance of gas regulator stations and other equipment used in measuring and regulating gas within gas distribution system operations other than the measurement of gas deliveries to customers. This group includes RAMP SDG&E-Risk-9, C04: Regulator Station, Valve, and Large Meter Set Inspection and SDG&E-Risk-09, C17: Control Center Modernization | SDGE-04-R-E LPK-46 to LPK-50 WP 1GD007.000
O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Control Center Modernization - Incremental add of personnel | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 540000 | 555999.9996 | 573000 | 589999.9992 | 540000 | -540000 | -555999.9996 | -573000 | -589999.9992 | -540000 | -100% | -100% | -100% | -100% | -100% | Supervisory Control and Data Acquisition (SCADA) Enhanced Sites | 0 |  |  |  | 0 | 3 |  |  |  | 3 | -3 | 0 | 0 | 0 | -3 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | This workpaper was intended for the O&M of SCADA sites on regulator stations in the SDG&E service territory. The design and construction of these types of activities can take several years. The capital construction of these sites is ongoing, but as of the end of 2024 zero sites had come online to send data, be monitored, or controlled and subsequently zero O&M costs. The plan is for these sites to come on-line in 2025. | This workpaper was intended for the O&M of SCADA sites on regulator stations in the SDG&E service territory. The design and construction of these types of activities can take several years. The capital construction of these sites is ongoing, but as of the end of 2024 zero sites had come online to send data, be monitored, or controlled and subsequently zero O&M costs. The plan is for these sites to come on-line in 2025. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This group includes the cost of labor, materials used, and expenses incurred in inspecting and maintaining large gas meters and their Meter Set Assemblies (MSAs), gas instruments, company Compressed Natural Gas (CNG) facilities, inspection and maintenance of gas regulator stations and other equipment used in measuring and regulating gas within gas distribution system operations other than the measurement of gas deliveries to customers. This group includes RAMP SDG&E-Risk-9, C04: Regulator Station, Valve, and Large Meter Set Inspection and SDG&E-Risk-09, C17: Control Center Modernization | SDGE-04-R-E LPK-46 to LPK-50 WP 1GD007.000
O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Regulator Station, Valve, and Large Meter Set Inspection | HP Supply Line | No | On-going | Annual | 130097.4689 | 0 | 0 | 0 | 130097.4689 | 90000 | 93000 | 96000 | 99000 | 90000 | 40097.4689 | -93000 | -96000 | -99000 | 40097.4689 | 44.55% | -100% | -100% | -100% | 44.55% | Inspections | 68 |  |  |  | 68 | 17 |  |  |  | 17 | 51 | 0 | 0 | 0 | 51 | 300% | 0% | 0% | 0% | 300% | YES | NO | YES | N/A | This variance is attributed to incorrectly forecasting the number of regulator stations, valves and large meter inspections. Currently there are over 600 large meter, over 2,200 valve, and over 450 regulator station inspections performed annually per regulations. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This group includes the cost of labor, materials used, and expenses incurred in inspecting and maintaining large gas meters and their Meter Set Assemblies (MSAs), gas instruments, company Compressed Natural Gas (CNG) facilities, inspection and maintenance of gas regulator stations and other equipment used in measuring and regulating gas within gas distribution system operations other than the measurement of gas deliveries to customers. This group includes RAMP SDG&E-Risk-9, C04: Regulator Station, Valve, and Large Meter Set Inspection and SDG&E-Risk-09, C17: Control Center Modernization | SDGE-04-R-E LPK-46 to LPK-50 WP 1GD007.000
O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Regulator Station, Valve, and Large Meter Set Inspection | MP Overall | No | On-going | Annual | 4599236.8802 | 0 | 0 | 0 | 4599236.8802 | 4398999.9996 | 4530999.9996 | 4665999.9996 | 4806000 | 4398999.9996 | 200236.8806 | -4530999.9996 | -4665999.9996 | -4806000 | 200236.8806 | 4.552% | -100% | -100% | -100% | 4.552% | Inspections | 3334 |  |  |  | 3334 | 842 |  |  |  | 842 | 2492 | 0 | 0 | 0 | 2492 | 296% | 0% | 0% | 0% | 296% | YES | NO | YES | N/A | This variance is attributed to incorrectly forecasting the number of regulator stations, valves and large meters inspections. Currently there are over 600 large meter, over 2,200 valve, and over 450 regulator station inspections performed annually per regulations. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This group includes the cost of labor, materials used, and expenses incurred in inspecting and maintaining large gas meters and their Meter Set Assemblies (MSAs), gas instruments, company Compressed Natural Gas (CNG) facilities, inspection and maintenance of gas regulator stations and other equipment used in measuring and regulating gas within gas distribution system operations other than the measurement of gas deliveries to customers. This group includes RAMP SDG&E-Risk-9, C04: Regulator Station, Valve, and Large Meter Set Inspection and SDG&E-Risk-09, C17: Control Center Modernization | SDGE-04-R-E LPK-46 to LPK-50 WP 1GD007.000
O&M | GAS DISTRIBUTION | SubTotal MEASUREMENT & REGULATION |  |  |  | Yes |  |  | 6299407.9415 | 0 | 0 | 0 | 6299407.9415 | 5801999.9988 | 5975999.9988 | 6154999.9992 | 6339999.9984 | 5801999.9988 | 497407.9428 | -5975999.9988 | -6154999.9992 | -6339999.9984 | 497407.9428 | 8.573% | -100% | -100% | -100% | 8.573% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 6010873.2065 | 0 | 0 | 0 | 6010873.2065 | 7236999.9996 | 7455000 | 7678999.9992 | 7908000 | 7236999.9996 | -1226126.7931 | -7455000 | -7678999.9992 | -7908000 | -1226126.7931 | -16.94% | -100% | -100% | -100% | -16.94% | The activities in this item include the supervision and management in the operating districts, training expenses of the employees in the districts, supplies, telephone expenses, mileage expenses, employee uniforms, etc. This includes expenses for leadership-based training of personnel in the Gas Technical Services, Gas Operations, and Gas Distribution groups. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Excavation Damage (Dig-In) on the Gas System | L&M Training Groupings | MP | No | On-going | Annual | 299570.3628 | 0 | 0 | 0 | 299570.3628 | 840999.9996 | 865999.9992 | 891999.9996 | 918999.9996 | 840999.9996 | -541429.6368 | -865999.9992 | -891999.9996 | -918999.9996 | -541429.6368 | -64.38% | -100% | -100% | -100% | -64.38% | Locate & Mark training hours | 682 |  |  |  | 682 | 1374 |  |  |  | 1374 | -692 | 0 | 0 | 0 | -692 | -50.36% | 0% | 0% | 0% | -50.36% | YES | YES | YES | The variance of cost and units is attributed to lower drop out rate in 2024 as compared to years past. Employees who bid for the locator position who struggle with the Operator Qualifications (OpQuals) of the position require additional hours of training to give them additional opportunity to pass the requirements. | The variance of cost and units is attributed to lower drop out rate in 2024 as compared to years past. Employees who bid for the locator position who struggle with the Operator Qualifications (OpQuals) of the position require additional hours of training to give them additional opportunity to pass the requirements. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Work completed within this group includes Gas Distribution leadership; developing and maintaining gas distribution construction and operating standards; evaluating new field technologies; development of field training materials and providing the skills training both in classroom and simulation format; providing code required welder testing, training and welding inspection; and managing the Operator Qualification (OQ) program for SDG&E gas employees and contractors. This workpaper includes RAMP: SDG&E-Risk-9, C14: Human Factors Mitigations - Ops Qual Training, SDG&E-Risk-9, C15: Human Factors Mitigation - QA/QC Program, and SDG&E-Risk-7, C01: L&M Training Groupings. | SDGE-04-R-E LPK-59 to LPK-66 WP 1GD010.000
O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factors Mitigation - QA/QC Program | N/A | No | On-going | Annual | 293997.9829 | 0 | 0 | 0 | 293997.9829 | 337999.9992 | 348000 | 357999.9996 | 369000 | 337999.9992 | -44002.0163 | -348000 | -357999.9996 | -369000 | -44002.0163 | -13.02% | -100% | -100% | -100% | -13.02% | Quality assurance/quality control field audits | 832 |  |  |  | 832 | 239 |  |  |  | 239 | 593 | 0 | 0 | 0 | 593 | 248.1% | 0% | 0% | 0% | 248.1% | YES | NO | YES | N/A | The unit variance is attributed to the Quality Assurance (QA) group being able to perform more QA field audits than originally forecast. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Work completed within this group includes Gas Distribution leadership; developing and maintaining gas distribution construction and operating standards; evaluating new field technologies; development of field training materials and providing the skills training both in classroom and simulation format; providing code required welder testing, training and welding inspection; and managing the Operator Qualification (OQ) program for SDG&E gas employees and contractors. This workpaper includes RAMP: SDG&E-Risk-9, C14: Human Factors Mitigations - Ops Qual Training, SDG&E-Risk-9, C15: Human Factors Mitigation - QA/QC Program, and SDG&E-Risk-7, C01: L&M Training Groupings. | SDGE-04-R-E LPK-59 to LPK-66 WP 1GD010.000
O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factors Mitigations - Ops Qual Training | N/A | No | On-going | Annual | 1940112.377 | 0 | 0 | 0 | 1940112.377 | 1872000 | 1927999.9992 | 1986000 | 2046000 | 1872000 | 68112.377 | -1927999.9992 | -1986000 | -2046000 | 68112.377 | 3.638% | -100% | -100% | -100% | 3.638% | Employees/Contractors trained | 899 |  |  |  | 899 | 749 |  |  |  | 749 | 150 | 0 | 0 | 0 | 150 | 20.03% | 0% | 0% | 0% | 20.03% | YES | NO | YES | N/A | The variance on units associated with the Operator Qualifications (OpQuals) performed is attributed to an increase of OpQuals required by both internal gas workers and external gas contractors. The number of OpQuals is determined by OpQual frequency and by number of new internal gas workers and new contractors who perform work on the SDG&E gas pipelines system. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Work completed within this group includes Gas Distribution leadership; developing and maintaining gas distribution construction and operating standards; evaluating new field technologies; development of field training materials and providing the skills training both in classroom and simulation format; providing code required welder testing, training and welding inspection; and managing the Operator Qualification (OQ) program for SDG&E gas employees and contractors. This workpaper includes RAMP: SDG&E-Risk-9, C14: Human Factors Mitigations - Ops Qual Training, SDG&E-Risk-9, C15: Human Factors Mitigation - QA/QC Program, and SDG&E-Risk-7, C01: L&M Training Groupings. | SDGE-04-R-E LPK-59 to LPK-66 WP 1GD010.000
O&M | GAS DISTRIBUTION | SubTotal OPERATIONS MANAGEMENT, SUPERVISION & TRAINING |  |  |  | Yes |  |  | 8544553.9292 | 0 | 0 | 0 | 8544553.9292 | 10287999.9984 | 10596999.9984 | 10914999.9984 | 11241999.9996 | 10287999.9984 | -1743446.0692 | -10596999.9984 | -10914999.9984 | -11241999.9996 | -1743446.0692 | -16.95% | -100% | -100% | -100% | -16.95% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | OTHER SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 207891.5248 | 0 | 0 | 0 | 207891.5248 | 0 | 0 | 0 | 0 | 0 | 207891.5248 | 0 | 0 | 0 | 207891.5248 | 100% | 0% | 0% | 0% | 100% | This consists of miscellaneous expenses associated with Gas Distribution field operations that are not captured in other workgroups. Activities include inspecting and repairing customer meters, house regulators and house lines, and providing patrolling and other support to Transmission facilities and pipelines. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | SubTotal OTHER SERVICES |  |  |  | Yes |  |  | 207891.5248 | 0 | 0 | 0 | 207891.5248 | 0 | 0 | 0 | 0 | 0 | 207891.5248 | 0 | 0 | 0 | 207891.5248 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2118010.7585 | 0 | 0 | 0 | 2118010.7585 | 865999.9992 | 891999.9996 | 918999.9996 | 946999.9992 | 865999.9992 | 1252010.7593 | -891999.9996 | -918999.9996 | -946999.9992 | 1252010.7593 | 144.6% | -100% | -100% | -100% | 144.6% | The variety, scope, and duration of work for service maintenance (moving, lowering, raising gas services, changing service valves, checking & repairing riser wrap and coating on MSAs) makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The costs associated with Non-RAMP main maintenance were shifted to address abnormal operating condition associated with service maintenance, which can be seen with the increase in cost in Non-RAMP service maintenance. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Service maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution services, changing service valves, checking the condition of coating at the MSA, testing service pipe for leaks, inspecting and testing service pipe after repairs have been made, and installing, maintaining and removing temporary feeds. Also included in this subgroup are expenses for moving, lowering, and raising sections of distribution services. Workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F pipeline safety regulations and to extend the life of distribution service pipelines and related infrastructure. | SDGE-04-R-E LPK-38 to LPK-42 WP 1GD004.000
O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Gas Distribution Emergency Department - Service Portion | MP Service Steel & Plastic | No | On-going | Annual | 1166845.3686 | 0 | 0 | 0 | 1166845.3686 | 777000 | 799999.9992 | 823999.9992 | 849000 | 777000 | 389845.3686 | -799999.9992 | -823999.9992 | -849000 | 389845.3686 | 50.17% | -100% | -100% | -100% | 50.17% | Responses | 1205 |  |  |  | 1205 | 345 |  |  |  | 345 | 860 | 0 | 0 | 0 | 860 | 249.3% | 0% | 0% | 0% | 249.3% | YES | NO | YES | N/A | This activity covers the response of the GED to leaks and Dig-In’s on the gas system services. The variety and frequency of these responses are based on factors outside of SDG&E control (i.e., leaks by third party excavators) and the number of responses forecasted was exceeded. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Service maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution services, changing service valves, checking the condition of coating at the MSA, testing service pipe for leaks, inspecting and testing service pipe after repairs have been made, and installing, maintaining and removing temporary feeds. Also included in this subgroup are expenses for moving, lowering, and raising sections of distribution services. Workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F pipeline safety regulations and to extend the life of distribution service pipelines and related infrastructure. | SDGE-04-R-E LPK-38 to LPK-42 WP 1GD004.000
O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Service Portion | MP Service Plastic | No | On-going | Annual | 682950.9807 | 0 | 0 | 0 | 682950.9807 | 588000 | 606000 | 624000 | 642999.9996 | 588000 | 94950.9807 | -606000 | -624000 | -642999.9996 | 94950.9807 | 16.15% | -100% | -100% | -100% | 16.15% | Projects | 274 |  |  |  | 274 | 88 |  |  |  | 88 | 186 | 0 | 0 | 0 | 186 | 211.4% | 0% | 0% | 0% | 211.4% | YES | NO | YES | N/A | This activity covers the repair of repair of leaks on plastic services. The frequency of these leaks are based on factors outside of SDG&E control (i.e., third party leaks) and the number of leaks forecasted for repaired on plastic services was exceeded. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Service maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution services, changing service valves, checking the condition of coating at the MSA, testing service pipe for leaks, inspecting and testing service pipe after repairs have been made, and installing, maintaining and removing temporary feeds. Also included in this subgroup are expenses for moving, lowering, and raising sections of distribution services. Workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F pipeline safety regulations and to extend the life of distribution service pipelines and related infrastructure. | SDGE-04-R-E LPK-38 to LPK-42 WP 1GD004.000
O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Service Portion | MP Service Steel | No | On-going | Annual | 1024424.0511 | 0 | 0 | 0 | 1024424.0511 | 891999.9996 | 918999.9996 | 946999.9992 | 973999.9992 | 891999.9996 | 132424.0515 | -918999.9996 | -946999.9992 | -973999.9992 | 132424.0515 | 14.85% | -100% | -100% | -100% | 14.85% | Projects | 410 |  |  |  | 410 | 133 |  |  |  | 133 | 277 | 0 | 0 | 0 | 277 | 208.3% | 0% | 0% | 0% | 208.3% | YES | NO | YES | N/A | This activity covers the repair of repair of leaks on steel services. The frequency of these leaks are based on factors outside of SDG&E control (i.e., third party leaks) and the number of leaks forecasted for repaired on steel services was exceeded. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Service maintenance work is primarily comprised of labor and non-labor expenses associated with investigating and repairing leaks in distribution services, changing service valves, checking the condition of coating at the MSA, testing service pipe for leaks, inspecting and testing service pipe after repairs have been made, and installing, maintaining and removing temporary feeds. Also included in this subgroup are expenses for moving, lowering, and raising sections of distribution services. Workgroup is designed to meet federal, i.e., 49 C.F.R. §192, and state, i.e., CPUC General Order 112-F pipeline safety regulations and to extend the life of distribution service pipelines and related infrastructure. | SDGE-04-R-E LPK-38 to LPK-42 WP 1GD004.000
O&M | GAS DISTRIBUTION | SubTotal SERVICE MAINTENANCE |  |  |  | Yes |  |  | 4992231.1588 | 0 | 0 | 0 | 4992231.1588 | 3122999.9988 | 3216999.9984 | 3313999.998 | 3412999.998 | 3122999.9988 | 1869231.16 | -3216999.9984 | -3313999.998 | -3412999.998 | 1869231.16 | 59.85% | -100% | -100% | -100% | 59.85% | [21 empty] | YES | YES | [7 empty] | NO
O&M | GAS DISTRIBUTION | TOOLS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1662610.5419 | 0 | 0 | 0 | 1662610.5419 | 1390999.9992 | 1432999.9992 | 1476000 | 1519999.9992 | 1390999.9992 | 271610.5427 | -1432999.9992 | -1476000 | -1519999.9992 | 271610.5427 | 19.53% | -100% | -100% | -100% | 19.53% | Included in this category are materials used and expenses necessary for Personal Protective Equipment (PPE) used during construction and maintenance activities and those held in inventory as vehicle truck stock. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | TOOLS | Incident Involving an Employee | Personal Protective Equipment | N/A | No | On-going | Annual | 357798.93 | 0 | 0 | 0 | 357798.93 | 499999.9992 | 514999.9992 | 529999.9992 | 546000 | 499999.9992 | -142201.0692 | -514999.9992 | -529999.9992 | -546000 | -142201.0692 | -28.44% | -100% | -100% | -100% | -28.44% | Employees | 577 |  |  |  | 577 | 576 |  |  |  | 576 | 1 | 0 | 0 | 0 | 1 | 0.1736% | 0% | 0% | 0% | 0.1736% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | SubTotal TOOLS |  |  |  | Yes |  |  | 2020409.4719 | 0 | 0 | 0 | 2020409.4719 | 1890999.9984 | 1947999.9984 | 2005999.9992 | 2065999.9992 | 1890999.9984 | 129409.4735 | -1947999.9984 | -2005999.9992 | -2065999.9992 | 129409.4735 | 6.843% | -100% | -100% | -100% | 6.843% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS DISTRIBUTION | R-LOCATE & MARK | Excavation Damage (Dig-In) on the Gas System | Locate & Mark Activities (HP) | HP | No | On-going | Annual | 501445.0084 | 0 | 0 | 0 | 501445.0084 | 108999.9996 | 111999.9996 | 114999.9996 | 117999.9996 | 108999.9996 | 392445.0088 | -111999.9996 | -114999.9996 | -117999.9996 | 392445.0088 | 360% | -100% | -100% | -100% | 360% | Tickets | 19117 |  |  |  | 19117 | 7452 |  |  |  | 7452 | 11665 | 0 | 0 | 0 | 11665 | 156.5% | 0% | 0% | 0% | 156.5% | YES | NO | YES | N/A | The number of tickets submitted to DigAlert is outside of SDG&E's control as the tickets are submitted by any 3rd party who is excavating. The number of High Pressure Gas tickets was higher than forecasted and authorized. | Over (O) | On Target (T) | Over (O) | Expanded | NO | N/A | This all RAMP workpaper (SDG&E-Risk-7, C03, C04, & C09) group includes labor and non-labor expenses to locate and mark out multiple underground facilities which include distribution and transmission gas facilities, secondary and primary electric underground, electric transmission, fiber optics, and standby activities of excavators near high pressure distribution facilities. The activities under this cost workgroup are preventative in nature, contribute to sustainability, and are required to avert damages caused by third-party excavators working near gas and electric underground substructures. | SDG&E-04-R-E LPK-31 to LPK-35 WP 1GD002.000
O&M | GAS DISTRIBUTION | R-LOCATE & MARK | Excavation Damage (Dig-In) on the Gas System | Locate & Mark Activities (MP) | MP | No | On-going | Annual | 9217769.0774 | 0 | 0 | 0 | 9217769.0774 | 3844999.9992 | 3960000 | 4078999.9992 | 4201999.9992 | 3844999.9992 | 5372769.0782 | -3960000 | -4078999.9992 | -4201999.9992 | 5372769.0782 | 139.7% | -100% | -100% | -100% | 139.7% | Tickets transmitted | 193436 |  |  |  | 193436 | 164706 |  |  |  | 164706 | 28730 | 0 | 0 | 0 | 28730 | 17.44% | 0% | 0% | 0% | 17.44% | YES | YES | NO | The variance is attributed to activities and associated expense for electric underground and fiber optic mark out which make up the difference between what was authorized (only the gas markout) and what was spent. | N/A | Over (O) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | This all RAMP workpaper (SDG&E-Risk-7, C03, C04, & C09) group includes labor and non-labor expenses to locate and mark out multiple underground facilities which include distribution and transmission gas facilities, secondary and primary electric underground, electric transmission, fiber optics, and standby activities of excavators near high pressure distribution facilities. The activities under this cost workgroup are preventative in nature, contribute to sustainability, and are required to avert damages caused by third-party excavators working near gas and electric underground substructures. | SDG&E-04-R-E LPK-31 to LPK-35 WP 1GD002.000
O&M | GAS DISTRIBUTION | R-LOCATE & MARK | Excavation Damage (Dig-In) on the Gas System | Locate & Mark Quality Assurance | MP | No | On-going | Annual | 293997.9829 | 0 | 0 | 0 | 293997.9829 | 159999.9996 | 165000 | 169999.9992 | 174999.9996 | 159999.9996 | 133997.9833 | -165000 | -169999.9992 | -174999.9996 | 133997.9833 | 83.75% | -100% | -100% | -100% | 83.75% | FTE | 2 |  |  |  | 2 | 2 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS DISTRIBUTION | SubTotal R-LOCATE & MARK |  |  |  | Yes |  |  | 10013212.0687 | 0 | 0 | 0 | 10013212.0687 | 4113999.9984 | 4236999.9996 | 4363999.998 | 4494999.9984 | 4113999.9984 | 5899212.0703 | -4236999.9996 | -4363999.998 | -4494999.9984 | 5899212.0703 | 143.4% | -100% | -100% | -100% | 143.4% | [21 empty] | YES | YES | [7 empty] | NO

## GOTD
SDG&E GAS INTEGRITY MANAGEMENT PROGRAMS O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | GAS INTEGRITY MANAGEMENT PROGRAMS | GAS INTEGRITY MANAGEMENT PROGRAMS |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 145999.9992 | 149999.9988 | 154999.9968 | 159999.9996 | 145999.9992 | -145999.9992 | -149999.9988 | -154999.9968 | -159999.9996 | -145999.9992 | -100% | -100% | -100% | -100% | -100%
O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - HCA | No | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 76999.9992 | 78000 | 79999.9992 | 81999.9996 | 76999.9992 | -76999.9992 | -78000 | -79999.9992 | -81999.9996 | -76999.9992 | -100% | -100% | -100% | -100% | -100% | This activity and the work completed in 2024 consist of program management activities (e.g., training, data management, and reporting). The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Other | YES | The GTSR Part 1 program remains active and to maximize efficiencies, SDG&E was able to leverage SoCalGas resources to conduct general GTSR Part 1 management activities, so costs were allocated to the shared services workpaper (2200-7003). | Implementation of new gas safety rules and regulations activities as follows: MAOP Reconfirmation as required by PHMSA's Gas Transmission Safety Rule (GTSR) Part 1 (49 CFR 192.624); GTSR Part 2, which includes corrosion management and remediation measures; and the Valve Installation and Minimum Rupture Standards Rule (Valve Rule). | SDGE-09-R AK-TS-36 to AK-TS-46 WP 1TD005.000
O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - Non-HCA | No | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 24000 | 24999.9996 | 25999.9992 | 27000 | 24000 | -24000 | -24999.9996 | -25999.9992 | -27000 | -24000 | -100% | -100% | -100% | -100% | -100% | This activity and the work completed in 2024 consist of program management activities (e.g., training, data management, and reporting). The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Other | YES | The GTSR Part 1 program remains active and to maximize efficiencies, SDG&E was able to leverage SoCalGas resources to conduct general GTSR Part 1 management activities, so costs were allocated to the shared services workpaper (2200-7003). | Implementation of new gas safety rules and regulations activities as follows: MAOP Reconfirmation as required by PHMSA's Gas Transmission Safety Rule (GTSR) Part 1 (49 CFR 192.624); GTSR Part 2, which includes corrosion management and remediation measures; and the Valve Installation and Minimum Rupture Standards Rule (Valve Rule). | SDGE-09-R AK-TS-36 to AK-TS-46 WP 1TD005.000
O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Gas Transmission Safety Rule (GTSR) Part 2 | Transmission - HCA & non-HCA | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 18000 | 18999.9996 | 19999.9992 | 21000 | 18000 | -18000 | -18999.9996 | -19999.9992 | -21000 | -18000 | -100% | -100% | -100% | -100% | -100% | A unit of measure is not feasible for the wide range of activities that are required to comply with GTSR Part 2 (e.g., training, data management and analysis, corrosion control surveys). | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Other | YES | The primary driver for GTSR Part 1 costs are corrosion control activities as required by 49 CFR 192.465 and 192.473. In 2024, SDG&E did not encounter conditions requiring GTSR Part 2 compliance activities as previously expected. However, the scope of work remains necessary and SDG&E continues to monitor and manage its pipelines in accordance with GTSR Part 2 requirements and anticipates. Additionally, to maximize efficiencies, SDG&E was able to leverage SoCalGas resources to conduct general management activities, so costs were allocated to the shared services workpaper (2200-7003). | Implementation of new gas safety rules and regulations activities as follows: MAOP Reconfirmation as required by PHMSA's Gas Transmission Safety Rule (GTSR) Part 1 (49 CFR 192.624); GTSR Part 2, which includes corrosion management and remediation measures; and the Valve Installation and Minimum Rupture Standards Rule (Valve Rule). | SDGE-09-R AK-TS-36 to AK-TS-46 WP 1TD005.000
O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Valve Rule | Transmission - HCA & non-HCA | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 27000 | 27999.9996 | 28999.9992 | 30000 | 27000 | -27000 | -27999.9996 | -28999.9992 | -30000 | -27000 | -100% | -100% | -100% | -100% | -100% | Since O&M costs are incurred due to a variety of activities (e.g., data management, reporting, training) necessary to support capital work, units are presented in the capital section. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Other | YES | Valve Rule compliance remains active and to maximize efficiencies, SDG&E was able to leverage SoCalGas resources to conduct general management activities, so costs were allocated to the shared services workpaper (2200-7003). | Implementation of new gas safety rules and regulations activities as follows: MAOP Reconfirmation as required by PHMSA's Gas Transmission Safety Rule (GTSR) Part 1 (49 CFR 192.624); GTSR Part 2, which includes corrosion management and remediation measures; and the Valve Installation and Minimum Rupture Standards Rule (Valve Rule). | SDGE-09-R AK-TS-36 to AK-TS-46 WP 1TD005.000
O&M | GAS INTEGRITY PROGRAMS | SubTotal GAS SAFETY ENHANCEMENT PROGRAMS |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 145999.9992 | 149999.9988 | 154999.9968 | 159999.9996 | 145999.9992 | -145999.9992 | -149999.9988 | -154999.9968 | -159999.9996 | -145999.9992 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES

## GOGT
SDG&E GAS TRANSMISSION OPERATIONS AND CONSTRUCTION O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | GAS TRANSMISSION OPERATIONS AND CONSTRUCTION | GAS TRANSMISSION OPERATIONS AND CONSTRUCTION |  |  |  | Yes |  |  | 5385056.3469 | 0 | 0 | 0 | 5385056.3469 | 6191999.9952 | 6377999.994 | 6569999.9952 | 6767999.994 | 6191999.9952 | -806943.6483 | -6377999.994 | -6569999.9952 | -6767999.994 | -806943.6483 | -13.03% | -100% | -100% | -100% | -13.03%
O&M | GAS TRANSMISSION | COMPRESSOR STATION OPERATIONS - MORENO | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 256999.9992 | 264999.9996 | 273000 | 280999.9992 | 256999.9992 | -256999.9992 | -264999.9996 | -273000 | -280999.9992 | -256999.9992 | -100% | -100% | -100% | -100% | -100% | The activities in this workpaper include Compressor Station Operation activities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Other | YES | All costs associated with Moreno Compressor Station in 2024 were determined to be RAMP. Work at the compressor station is expected to proceed as planned.
O&M | GAS TRANSMISSION | COMPRESSOR STATION OPERATIONS - MORENO | Incident Related to the High Pressure System (Excluding Dig-in) | Compressor Station | Transmission - Facilities | No | On-going | Annual | 3463730.9239 | 0 | 0 | 0 | 3463730.9239 | 3502999.9992 | 3607999.9992 | 3715999.9992 | 3828000 | 3502999.9992 | -39269.0753 | -3607999.9992 | -3715999.9992 | -3828000 | -39269.0753 | -1.121% | -100% | -100% | -100% | -1.121% | The activities in this workpaper include Compressor Station Operation activities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | COMPRESSOR STATION OPERATIONS - MORENO | Incident Related to the High Pressure System (Excluding Dig-in) | Engineering, Oversight Compliance Review | N/A | No | On-going | Annual | 6496 | 0 | 0 | 0 | 6496 | 93000 | 96000 | 99000 | 102000 | 93000 | -86504 | -96000 | -99000 | -102000 | -86504 | -93.02% | -100% | -100% | -100% | -93.02% | The activities in this workpaper include Compressor Station Operation activities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | SubTotal COMPRESSOR STATION OPERATIONS - MORENO |  |  |  | Yes |  |  | 3470226.9239 | 0 | 0 | 0 | 3470226.9239 | 3852999.9984 | 3968999.9988 | 4087999.9992 | 4210999.9992 | 3852999.9984 | -382773.0745 | -3968999.9988 | -4087999.9992 | -4210999.9992 | -382773.0745 | -9.934% | -100% | -100% | -100% | -9.934% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | -0.1574 | 0 | 0 | 0 | -0.1574 | 1008000 | 1038000 | 1069999.9992 | 1102999.9992 | 1008000 | -1008000.1574 | -1038000 | -1069999.9992 | -1102999.9992 | -1008000.1574 | -100% | -100% | -100% | -100% | -100% | This workpaper is unable to identify a single unit of measure due to the variety of Pipeline and Instrumentation non-RAMP activities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | All Pipeline and Instrumentation Operations costs in 2024 were determined to be RAMP. The costs originally estimated in this non-RAMP category have been a accounted for in the appropriate RAMP line items. | N/A | On Target (T) | On Target (T) | Under (U) | Other | YES | All Pipeline and Instrumentation Operations costs in 2024 were determined to be RAMP. The costs originally estimated for in this non-RAMP category have been a accounted for in the appropriate RAMP line items. Future costs may be incurred in this cost category. | The Gas Transmission Pipeline & Instrumentation Operations includes operation and maintenance of equipment at pipeline receipt points, valve control stations, major customer delivery custody-transfer points, and all associated monitoring, metering, and control facilities, odorization equipment, and real-time operating data telemetry communications between gas facilities and SoCalGas’s Gas Control department. | SDG&E-06-E RC/SH-13 to RC/SH-17 WP 1GT000.000
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection (HCA & Non-HCA) | Transmission - HCA | No | On-going | Annual | 110379.7648 | 0 | 0 | 0 | 110379.7648 | 70999.9992 | 72999.9996 | 75000 | 76999.9992 | 70999.9992 | 39379.7656 | -72999.9996 | -75000 | -76999.9992 | 39379.7656 | 55.46% | -100% | -100% | -100% | 55.46% | This workpaper is unable to identify a single unit of measure because there are many Cathodic Protection Maintenance activities which consist of annual electrolysis test station (ETS) reads, bi-monthly current source inspections and annual rectifier maintenance on transmission pipelines. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection (HCA & Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 24229.7932 | 0 | 0 | 0 | 24229.7932 | 15999.9996 | 15999.9996 | 15999.9996 | 15999.9996 | 15999.9996 | 8229.7936 | -15999.9996 | -15999.9996 | -15999.9996 | 8229.7936 | 51.44% | -100% | -100% | -100% | 51.44% | This workpaper is unable to identify a single unit of measure because there are many Cathodic Protection Maintenance activities which consist of annual electrolysis test station (ETS) reads, bi-monthly current source inspections and annual rectifier maintenance on transmission pipelines. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Engineering, Oversight Compliance Review | N/A | No | On-going | Annual | 22154.28 | 0 | 0 | 0 | 22154.28 | 93000 | 96000 | 99000 | 102000 | 93000 | -70845.72 | -96000 | -99000 | -102000 | -70845.72 | -76.18% | -100% | -100% | -100% | -76.18% | This workpaper is unable to identify a single unit of measure due to the variety of Engineering, Oversight, Compliance Review activities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation Station Maintenance (HCA & Non-HCA) | Transmission - HCA | No | On-going | Annual | 298617.2605 | 0 | 0 | 0 | 298617.2605 | 324999.9996 | 334999.9992 | 345000 | 355999.9992 | 324999.9996 | -26382.7391 | -334999.9992 | -345000 | -355999.9992 | -26382.7391 | -8.118% | -100% | -100% | -100% | -8.118% | The activities tracked within this category are associated with the maintenance of meter set assemblies and pressure limiting stations. The scope of work is project-specific and varies significantly from project to project (e.g., station piping, valves, regulators, control and communications equipment, shelters, enclosure, etc.). The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation Station Maintenance (HCA & Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 65549.9108 | 0 | 0 | 0 | 65549.9108 | 72000 | 73999.9992 | 75999.9996 | 78000 | 72000 | -6450.0892 | -73999.9992 | -75999.9996 | -78000 | -6450.0892 | -8.958% | -100% | -100% | -100% | -8.958% | The activities tracked within this category are associated with the maintenance of meter set assemblies and pressure limiting stations. The scope of work varies significantly from project to project (e.g., station piping, valves, regulators, control and communications equipment, shelters, enclosure, etc.). The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Odorization | Transmission Facilities | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 9999.9996 | 9999.9996 | 9999.9996 | 9999.9996 | 9999.9996 | -9999.9996 | -9999.9996 | -9999.9996 | -9999.9996 | -9999.9996 | -100% | -100% | -100% | -100% | -100% | The odorization of the natural gas is required by 49CFR § 192.625. Odorant is added to natural gas as a safety precaution reducing risk that leaks will go undetected and gas will accumulate to hazardous levels. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | YES | Odorization of the natural gas supply is an ongoing activity. There were no purchases of odorant in 2024 so this category is underspent. Future costs are anticipated in this cost category.
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline Maintenance (HCA & Non-HCA) | Transmission - HCA | No | On-going | Annual | 1077570.9758 | 0 | 0 | 0 | 1077570.9758 | 564000 | 580999.9992 | 598999.9992 | 616999.9992 | 564000 | 513570.9758 | -580999.9992 | -598999.9992 | -616999.9992 | 513570.9758 | 91.06% | -100% | -100% | -100% | 91.06% | This workpaper is unable to identify a single unit of measure because there are many Pipeline Maintenance activities which consist of leak surveys, pipeline patrol, valve inspections, meter inspections, vault inspections and bridge & span inspections on transmission pipelines. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | Higher than estimated costs in this category are due to more RAMP Pipeline Maintenance work occuring in 2024. The increased cost for Pipeline Maintenance was forecast in the non-RAMP Pipeline and Instrumentation Operations cost category. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | The Gas Transmission Pipeline & Instrumentation Operations includes operation and maintenance of equipment at pipeline receipt points, valve control stations, major customer delivery custody-transfer points, and all associated monitoring, metering, and control facilities, odorization equipment, and real-time operating data telemetry communications between gas facilities and SoCalGas’s Gas Control department. | SDG&E-06-E RC/SH-13 to RC/SH-17 WP 1GT000.000
O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline Maintenance (HCA & Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 236539.6504 | 0 | 0 | 0 | 236539.6504 | 123999.9996 | 127999.9992 | 132000 | 135999.9996 | 123999.9996 | 112539.6508 | -127999.9992 | -132000 | -135999.9996 | 112539.6508 | 90.76% | -100% | -100% | -100% | 90.76% | This workpaper is unable to identify a single unit of measure because there are many Pipeline Maintenance activities which consist of leak surveys, pipeline patrol, valve inspections, meter inspections, vault inspections and bridge & span inspections on transmission pipelines. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | SubTotal PIPELINE & INSTRUMENTATION OPERATIONS |  |  |  | Yes |  |  | 1835041.478 | 0 | 0 | 0 | 1835041.478 | 2282999.9976 | 2350999.9956 | 2421999.9972 | 2494999.9956 | 2282999.9976 | -447958.5196 | -2350999.9956 | -2421999.9972 | -2494999.9956 | -447958.5196 | -19.62% | -100% | -100% | -100% | -19.62% | [21 empty] | YES | NO | [7 empty] | NO
O&M | GAS TRANSMISSION | TECHNICAL SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 6999.9996 | 6999.9996 | 6999.9996 | 6999.9996 | 6999.9996 | -6999.9996 | -6999.9996 | -6999.9996 | -6999.9996 | -6999.9996 | -100% | -100% | -100% | -100% | -100% | This workpaper activities include the support of the day-to-day operations and maintenance of the gas transmission system include design and engineering, instrumentation, control, project support, and environmental services. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | All Technical Services costs in 2024 were determined to be RAMP. The costs originally estimated for in this non-RAMP category have been a accounted for in the engineering, oversight, and compliance review RAMP line item. Future costs may be incurred in this cost category.
O&M | GAS TRANSMISSION | TECHNICAL SERVICES | Incident Related to the High Pressure System (Excluding Dig-in) | Engineering, Oversight Compliance Review | N/A | No | On-going | Annual | 79787.945 | 0 | 0 | 0 | 79787.945 | 48999.9996 | 51000 | 52999.9992 | 54999.9996 | 48999.9996 | 30787.9454 | -51000 | -52999.9992 | -54999.9996 | 30787.9454 | 62.83% | -100% | -100% | -100% | 62.83% | This workpaper activities include the support of the day-to-day operations and maintenance of the gas transmission system include design and engineering, instrumentation, control, project support, and environmental services. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
O&M | GAS TRANSMISSION | SubTotal TECHNICAL SERVICES |  |  |  | Yes |  |  | 79787.945 | 0 | 0 | 0 | 79787.945 | 55999.9992 | 57999.9996 | 59999.9988 | 61999.9992 | 55999.9992 | 23787.9458 | -57999.9996 | -59999.9988 | -61999.9992 | 23787.9458 | 42.48% | -100% | -100% | -100% | 42.48% | [21 empty] | YES | NO | [7 empty] | NO

## GOSI
SDG&E GAS SYSTEM STAFF & TECHNOLOGY O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | GAS SYSTEM STAFF & TECHNOLOGY | GAS SYSTEM STAFF & TECHNOLOGY |  |  |  | Yes |  |  | 580813.2831 | 0 | 0 | 0 | 580813.2831 | 480999.9948 | 494999.9964 | 509999.9964 | 524999.9952 | 480999.9948 | 99813.2883 | -494999.9964 | -509999.9964 | -524999.9952 | 99813.2883 | 20.75% | -100% | -100% | -100% | 20.75%
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 359228.7951 | 0 | 0 | 0 | 359228.7951 | 274999.9992 | 281999.9988 | 289999.9992 | 297999.9996 | 274999.9992 | 84228.7959 | -281999.9988 | -289999.9992 | -297999.9996 | 84228.7959 | 30.63% | -100% | -100% | -100% | 30.63% | USA tickets | 212553 |  |  |  | 212553 | 185612 |  |  |  | 185612 | 26941 | 0 | 0 | 0 | 26941 | 14.51% | 0% | 0% | 0% | 14.51% | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Outreach for Latent 3rd Party Damages (HP) | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 999.9996 | 999.9996 | 999.9996 | 999.9996 | 999.9996 | -999.9996 | -999.9996 | -999.9996 | -999.9996 | -999.9996 | -100% | -100% | -100% | -100% | -100% | This workpaper covers a range of activities such as one-call notifications, identifying potential hazards from accidental gas pipeline releases, recognizing physical signs of such releases, implementing safety measures, and reporting procedures. These activities collectively play a crucial role in maintaining the system integrity of SDG&E gas pipelines. Consequently, it is impractical to establish a single unit of measure for this workpaper. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | In 2024, there were no third-party damages to high-pressure (HP) pipelines. As a result, no outreach efforts were necessary.
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Outreach for Latent 3rd Party Damages (MP) | N/A | No | On-going | Annual | 869.102 | 0 | 0 | 0 | 869.102 | 3000 | 3000 | 3000 | 3000 | 3000 | -2130.898 | -3000 | -3000 | -3000 | -2130.898 | -71.03% | -100% | -100% | -100% | -71.03% | This workpaper covers a range of activities such as one-call notifications, identifying potential hazards from accidental gas pipeline releases, recognizing physical signs of such releases, implementing safety measures, and reporting procedures. These activities collectively play a crucial role in maintaining the system integrity of SDG&E gas pipelines. Consequently, it is impractical to establish a single unit of measure for this workpaper. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | Excavators (HP) | No | On-going | Annual | 869.102 | 0 | 0 | 0 | 869.102 | 6000 | 6000 | 6000 | 6000 | 6000 | -5130.898 | -6000 | -6000 | -6000 | -5130.898 | -85.51% | -100% | -100% | -100% | -85.51% | Communications sent | 9506 |  |  |  | 9506 | 10648 |  |  |  | 10648 | -1142 | 0 | 0 | 0 | -1142 | -10.73% | 0% | 0% | 0% | -10.73% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | Local Public Officials (MP) | No | On-going | Annual | 3476.408 | 0 | 0 | 0 | 3476.408 | 18999.9996 | 19999.9992 | 21000 | 21999.9996 | 18999.9996 | -15523.5916 | -19999.9992 | -21000 | -21999.9996 | -15523.5916 | -81.7% | -100% | -100% | -100% | -81.7% | Communications sent | 414 |  |  |  | 414 | 384 |  |  |  | 384 | 30 | 0 | 0 | 0 | 30 | 7.812% | 0% | 0% | 0% | 7.812% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | Emergency Officials (HP) | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 999.9996 | 999.9996 | 999.9996 | 999.9996 | 999.9996 | -999.9996 | -999.9996 | -999.9996 | -999.9996 | -999.9996 | -100% | -100% | -100% | -100% | -100% | Communications sent | 248 |  |  |  | 248 | 100 |  |  |  | 100 | 148 | 0 | 0 | 0 | 148 | 148% | 0% | 0% | 0% | 148% | YES | NO | YES | N/A | The number of communications sent to emergency officials fluctuates annually, depending on the necessary notifications. These alerts are vital for keeping emergency officials informed about potential risks or incidents related to SDG&E’s infrastructure. They encompass information about excavation activities, safety protocols, and any immediate threats to the pipelines. The frequency of communications varies among officials, influenced by their awareness and understanding of the different programs within the damage prevention initiatives. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | The frequency of communications varies among officials, depending on their awareness and understanding of the different programs within the damage prevention initiatives. All notifications and alerts were sent to emergency officials as required or requested. | SDG&E has developed and implemented a federally mandated Public Awareness program, as prescribed in 49 CFR 192.616. The Public Awareness program contributes to enhanced public safety by providing certain risk mitigation measures. In adopting these Public Awareness program requirements, the Pipeline and Hazardous Materials Safety Administration (PHMSA) determined that “effective public awareness programs are vital to continued safe pipeline Operations” and that “such programs are an important factor in establishing communications with affected stakeholders, providing information necessary to enhance public awareness of pipelines, and communicating stakeholder roles relative to pipeline safety. ” The federal regulations directing the implementation of this program specifically require that the program include activities to educate the public, appropriate government organizations, and persons engaged in excavation-related activities regarding: (1) Use of the one-call notification system prior to excavation and other damage prevention activities; (2) possible hazards associated with unintended releases from a gas pipeline facility; (3) Physical indications that such a release may have occurred; (4) steps that should be taken for public safety in the event of a gas pipeline release; and (5) procedures for reporting such an event. | SDG&E-05 WR-9 to WR-20 WP 1SI001.000
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | Local Public Officials (HP) | No | On-going | Annual | 869.102 | 0 | 0 | 0 | 869.102 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | -4130.8972 | -4999.9992 | -4999.9992 | -4999.9992 | -4130.8972 | -82.62% | -100% | -100% | -100% | -82.62% | Communications sent | 95 |  |  |  | 95 | 88 |  |  |  | 88 | 7 | 0 | 0 | 0 | 7 | 7.955% | 0% | 0% | 0% | 7.955% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | The Affected Public (HP) | No | On-going | Annual | 36112.51 | 0 | 0 | 0 | 36112.51 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 22999.9992 | 13112.5108 | -24000 | -24999.9996 | -25999.9992 | 13112.5108 | 57.01% | -100% | -100% | -100% | 57.01% | Communications sent | 388816 |  |  |  | 388816 | 362443 |  |  |  | 362443 | 26373 | 0 | 0 | 0 | 26373 | 7.276% | 0% | 0% | 0% | 7.276% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | Emergency Officials (MP) | No | On-going | Annual | 869.102 | 0 | 0 | 0 | 869.102 | 3000 | 3000 | 3000 | 3000 | 3000 | -2130.898 | -3000 | -3000 | -3000 | -2130.898 | -71.03% | -100% | -100% | -100% | -71.03% | Communications sent | 238 |  |  |  | 238 | 440 |  |  |  | 440 | -202 | 0 | 0 | 0 | -202 | -45.91% | 0% | 0% | 0% | -45.91% | YES | NO | YES | N/A | The number of communications sent to emergency officials fluctuates annually, depending on the necessary notifications. These alerts are vital for keeping emergency officials informed about potential risks or incidents related to SDG&E’s infrastructure. They encompass information about excavation activities, safety protocols, and any immediate threats to the pipelines. The frequency of communications varies among officials, influenced by their awareness and understanding of the different programs within the damage prevention initiatives. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | SDG&E has developed and implemented a federally mandated Public Awareness program , as prescribed in 49 CFR 192.616. The Public Awareness program contributes to enhanced public safety by providing certain risk mitigation measures. In adopting these Public Awareness program requirements, the Pipeline and Hazardous Materials Safety Administration (PHMSA) determined that “effective public awareness programs are vital to continued safe pipeline Operations” and that “such programs are an important factor in establishing communications with affected stakeholders, providing information necessary to enhance public awareness of pipelines, and communicating stakeholder roles relative to pipeline safety. ” The federal regulations directing the implementation of this program specifically require that the program include activities to educate the public, appropriate government organizations, and persons engaged in excavation-related activities regarding: (1) Use of the one-call notification system prior to excavation and other damage prevention activities; (2) possible hazards associated with unintended releases from a gas pipeline facility; (3) Physical indications that such a release may have occurred; (4) steps that should be taken for public safety in the event of a gas pipeline release; and (5) procedures for reporting such an event. | SDG&E-05 WR-9 to WR-20 WP 1SI001.000
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | Excavators (MP) | No | On-going | Annual | 4345.51 | 0 | 0 | 0 | 4345.51 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 22999.9992 | -18654.4892 | -24000 | -24999.9996 | -25999.9992 | -18654.4892 | -81.11% | -100% | -100% | -100% | -81.11% | Communications sent | 41330 |  |  |  | 41330 | 46720 |  |  |  | 46720 | -5390 | 0 | 0 | 0 | -5390 | -11.54% | 0% | 0% | 0% | -11.54% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | The Affected Public (MP) | No | On-going | Annual | 174173.652 | 0 | 0 | 0 | 174173.652 | 121999.9992 | 126000 | 129999.9996 | 133999.9992 | 121999.9992 | 52173.6528 | -126000 | -129999.9996 | -133999.9992 | 52173.6528 | 42.77% | -100% | -100% | -100% | 42.77% | Communications sent | 1690503 |  |  |  | 1690503 | 1590214 |  |  |  | 1590214 | 100289 | 0 | 0 | 0 | 100289 | 6.307% | 0% | 0% | 0% | 6.307% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | GAS SYSTEM STAFF & TECHNOLOGY | SubTotal DAMAGE PREVENTION |  |  |  | Yes |  |  | 580813.2831 | 0 | 0 | 0 | 580813.2831 | 480999.9948 | 494999.9964 | 509999.9964 | 524999.9952 | 480999.9948 | 99813.2883 | -494999.9964 | -509999.9964 | -524999.9952 | 99813.2883 | 20.75% | -100% | -100% | -100% | 20.75% | [21 empty] | YES | NO | [7 empty] | NO

## CSFC
SDG&E CUSTOMER SERVICES - FIELD OPERATIONS O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CUSTOMER SERVICES - FIELD OPERATIONS | CUSTOMER SERVICES - FIELD OPERATIONS |  |  |  | Yes |  |  | 40552178.9034 | 0 | 0 | 0 | 40552178.9034 | 35898999.9972 | 36975999.996 | 38084999.9952 | 39227999.9976 | 35898999.9972 | 4653178.9062 | -36975999.996 | -38084999.9952 | -39227999.9976 | 4653178.9062 | 12.96% | -100% | -100% | -100% | 12.96%
O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 7183053.7207 | 0 | 0 | 0 | 7183053.7207 | 5590999.9992 | 5758999.9992 | 5931999.9996 | 6109999.9992 | 5590999.9992 | 1592053.7215 | -5758999.9992 | -5931999.9996 | -6109999.9992 | 1592053.7215 | 28.48% | -100% | -100% | -100% | 28.48% | Non-RAMP Orders | 122022 |  |  |  | 122022 | 107469 |  |  |  | 107469 | 14553 | 0 | 0 | 0 | 14553 | 13.54% | 0% | 0% | 0% | 13.54% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Incident Involving an Employee | Employee Behavioral Accident Prevention Process Program | Overall | No | On-going | Annual | 327305.1498 | 0 | 0 | 0 | 327305.1498 | 264999.9996 | 273000 | 280999.9992 | 288999.9996 | 264999.9996 | 62305.1503 | -273000 | -280999.9992 | -288999.9996 | 62305.1503 | 23.51% | -100% | -100% | -100% | 23.51% | Job Observations | 1973 |  |  |  | 1973 | 1041 |  |  |  | 1041 | 932 | 0 | 0 | 0 | 932 | 89.53% | 0% | 0% | 0% | 89.53% | YES | NO | YES | N/A | Higher than authorized 6-year average (2017-2022) job observations were realized as part of SDG&E's continued efforts to enhance safety engagement with field employees primarily through the following actions: (1) consistent scheduling to ensure observations are performed; (2) continually improving the contact rate with each employee by having regularly occurring peer to peer observations in all districts; and (3) performing full-scale observations of both vehicle parking/driving skills and technical field activities. | Over (O) | Over (O) | On Target (T) | Proceeding as Planned | NO | N/A | The Customer Field Operations cost category consists of labor and non-labor costs for field technicians to provide service at customer premises, including both customer and company generated work orders. Examples of customer-generated work orders include requests to establish/remove gas and electric service, light gas pilots, check gas appliances, shut off and restore gas service for fumigation, investigate the potential causes of high bills, respond to emergency incidents, investigate potential gas leaks, and other services. Examples of company generated work include meter and regulator changes, and other meter work necessary to maintain company assets, and collecting customer payments for delinquent bills. | SDG&E-17-R DHT-13 to DHT-20 WP 1FC001.000
O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Incident Involving an Employee | Personal Protective Equipment | N/A | No | On-going | Annual | 93983.98 | 0 | 0 | 0 | 93983.98 | 99000 | 102000 | 105000 | 108000 | 99000 | -5016.02 | -102000 | -105000 | -108000 | -5016.02 | -5.067% | -100% | -100% | -100% | -5.067% | Technician FTE | 148.8 |  |  |  | 148.8 | 140.2 |  |  |  | 140.2 | 8.6 | 0 | 0 | 0 | 8.6 | 6.134% | 0% | 0% | 0% | 6.134% | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Incident Related to the Medium Pressure System (Excluding Dig-in) | Field and Public Safety | Meter and Beyond the Meter | No | On-going | Annual | 12230603.6949 | 0 | 0 | 0 | 12230603.6949 | 11971999.9992 | 12330999.9996 | 12700999.9992 | 13083000 | 11971999.9992 | 258603.6957 | -12330999.9996 | -12700999.9992 | -13083000 | 258603.6957 | 2.16% | -100% | -100% | -100% | 2.16% | RAMP Orders | 107160 |  |  |  | 107160 | 136025 |  |  |  | 136025 | -28865 | 0 | 0 | 0 | -28865 | -21.22% | 0% | 0% | 0% | -21.22% | YES | NO | YES | N/A | Lower than authorized 6-year average (2017-2022) RAMP orders due to less customer generated service orders and fewer emergencies. Hazardous orders were reclassified as non-hazardous such as when customer smells gas when appliance is off. There were also fewer seasonal light-up orders due to cancellation of multiple pilot lighting programs. In addition, workforce capacity shifted to non-RAMP activities such as increased gas module replacements and meter reads to address gas module non-communication. | Under (U) | Under (U) | On Target (T) | Proceeding as Planned | NO | N/A | The Customer Field Operations cost category consists of labor and non-labor costs for field technicians to provide service at customer premises, including both customer and company generated work orders. Examples of customer-generated work orders include requests to establish/remove gas and electric service, light gas pilots, check gas appliances, shut off and restore gas service for fumigation, investigate the potential causes of high bills, respond to emergency incidents, investigate potential gas leaks, and other services. Examples of company generated work include meter and regulator changes, and other meter work necessary to maintain company assets, and collecting customer payments for delinquent bills. | SDG&E-17-R DHT-13 to DHT-20 WP 1FC001.000
O&M | CS - FIELD OPERATIONS | SubTotal CUSTOMER FIELD OPERATIONS |  |  |  | Yes |  |  | 19834946.5455 | 0 | 0 | 0 | 19834946.5455 | 17926999.998 | 18464999.9988 | 19018999.998 | 19589999.9988 | 17926999.998 | 1907946.5475 | -18464999.9988 | -19018999.998 | -19589999.9988 | 1907946.5475 | 10.64% | -100% | -100% | -100% | 10.64% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS SUPERVISION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1530164.7035 | 0 | 0 | 0 | 1530164.7035 | 1335000 | 1374999.9996 | 1416000 | 1458000 | 1335000 | 195164.7035 | -1374999.9996 | -1416000 | -1458000 | 195164.7035 | 14.62% | -100% | -100% | -100% | 14.62% | Supervisor FTE | 11.4 |  |  |  | 11.4 | 10.1 |  |  |  | 10.1 | 1.3 | 0 | 0 | 0 | 1.3 | 12.87% | 0% | 0% | 0% | 12.87% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - FIELD OPERATIONS | SubTotal CUSTOMER FIELD OPERATIONS SUPERVISION |  |  |  | Yes |  |  | 1530164.7035 | 0 | 0 | 0 | 1530164.7035 | 1335000 | 1374999.9996 | 1416000 | 1458000 | 1335000 | 195164.7035 | -1374999.9996 | -1416000 | -1458000 | 195164.7035 | 14.62% | -100% | -100% | -100% | 14.62% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 4298386.1918 | 0 | 0 | 0 | 4298386.1918 | 3231000 | 3327999.9996 | 3427999.9992 | 3531000 | 3231000 | 1067386.1918 | -3327999.9996 | -3427999.9992 | -3531000 | 1067386.1918 | 33.04% | -100% | -100% | -100% | 33.04% | Support FTE | 28.7 |  |  |  | 28.7 | 25.9 |  |  |  | 25.9 | 2.8 | 0 | 0 | 0 | 2.8 | 10.81% | 0% | 0% | 0% | 10.81% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS SUPPORT | Incident Related to the Medium Pressure System (Excluding Dig-in) | CSF Quality Assurance (QA) Program | Meter and Beyond the Meter | No | On-going | Annual | 287065.4952 | 0 | 0 | 0 | 287065.4952 | 282999.9996 | 291000 | 300000 | 309000 | 282999.9996 | 4065.4956 | -291000 | -300000 | -309000 | 4065.4956 | 1.437% | -100% | -100% | -100% | 1.437% | QA Inspections | 1856 |  |  |  | 1856 | 1001 |  |  |  | 1001 | 855 | 0 | 0 | 0 | 855 | 85.41% | 0% | 0% | 0% | 85.41% | YES | NO | YES | N/A | Higher than authorized 6-year average (2017-2022) QA inspections due to resumption of regular work after the pandemic. During the period of 2020-2022, the QA process was completely halted and only resumed in a minimal capacity with meter-only inspections. This significantly affected the overall inspection count and average for those years. | Over (O) | Over (O) | On Target (T) | Proceeding as Planned | NO | N/A | The Customer Field Operations Support cost category consists of labor and non-labor costs for centralized training including classroom and field instructors and training manager; quality assurance (QA) inspectors and QA supervisor who inspect the work of technicians; operations clerks at each field operating district responsible for supporting the field operations; Area Managers who oversee the day-to-day activities of each field operating district; a Meter Access group that manages any difficulty field technicians experience gaining safe access to meters at customers' premises; a Safety, Compliance and Regulatory group who oversee critical safety and compliance endeavors; Field Operations Strategy and Analytics group responsible for operations reporting and analytics leveraging business intelligence; Customer Service Technical Advisors to provide internal and external technical support and guidance to ensure compliance with SDG&E Service Standards; and Director and Vice President of Customer Operations. Also included is Field Service Delivery, an initiative to modernize delivery of customer services in the field while enhancing safety and employee engagement. | SDG&E-17-R DHT-25 to DHT-29 WP 1FC004.000
O&M | CS - FIELD OPERATIONS | SubTotal CUSTOMER FIELD OPERATIONS SUPPORT |  |  |  | Yes |  |  | 4585451.687 | 0 | 0 | 0 | 4585451.687 | 3513999.9996 | 3618999.9996 | 3727999.9992 | 3840000 | 3513999.9996 | 1071451.6874 | -3618999.9996 | -3727999.9992 | -3840000 | 1071451.6874 | 30.49% | -100% | -100% | -100% | 30.49% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CS - FIELD OPERATIONS | SMART METER OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 10980440.4517 | 0 | 0 | 0 | 10980440.4517 | 9258000 | 9535999.9992 | 9822000 | 10116999.9996 | 9258000 | 1722440.4517 | -9535999.9992 | -9822000 | -10116999.9996 | 1722440.4517 | 18.6% | -100% | -100% | -100% | 18.6% | Orders | 59733 |  |  |  | 59733 | 47737 |  |  |  | 47737 | 11996 | 0 | 0 | 0 | 11996 | 25.13% | 0% | 0% | 0% | 25.13% | YES | NO | YES | N/A | Higher than authorized 6-year average (2017-2022) orders completed primarily driven by more electric meter changeouts due to non-communicating meters. | Over (O) | Over (O) | On Target (T) | Proceeding as Planned | NO | N/A | The Smart Meter Operations cost category consists of labor and non-labor costs for Electric Metering Operations, Quality Assurance & Training, Network Operations, Electric Metering Engineering, Smart Meter Field Services and the Smart Meter Capital Program Team responsible for on-premise advanced metering customer service, customer inquiry investigations, customer metering problem remediation, and end-to-end management of the smart metering system, which includes field networking infrastructure, the metering head-end system, and integrations with the meter data management system. Collectively, the organizations are critical to enable accurate and timely bills for all of SDG&E’s metered customers, covering San Diego County and South Orange County and also responsible for meter data acquisition utilized by the operations and engineering organizations to enhance safety and reliability. | SDG&E-17-R DHT-30 to DHT-40 WP 1FC005.000
O&M | CS - FIELD OPERATIONS | SMART METER OPERATIONS | Incident Involving an Employee | Employee Behavioral Accident Prevention Process Program | Overall | No | On-going | Annual | 161657.0452 | 0 | 0 | 0 | 161657.0452 | 126000 | 129999.9996 | 133999.9992 | 138000 | 126000 | 35657.0452 | -129999.9996 | -133999.9992 | -138000 | 35657.0452 | 28.3% | -100% | -100% | -100% | 28.3% | Job Observations | 613 |  |  |  | 613 | 612 |  |  |  | 612 | 1 | 0 | 0 | 0 | 1 | 0.1634% | 0% | 0% | 0% | 0.1634% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - FIELD OPERATIONS | SMART METER OPERATIONS | Incident Involving an Employee | Personal Protective Equipment | N/A | No | On-going | Annual | 47912.7 | 0 | 0 | 0 | 47912.7 | 39000 | 39999.9996 | 40999.9992 | 42000 | 39000 | 8912.7 | -39999.9996 | -40999.9992 | -42000 | 8912.7 | 22.85% | -100% | -100% | -100% | 22.85% | Technician FTE | 55.9 |  |  |  | 55.9 | 42.2 |  |  |  | 42.2 | 13.7 | 0 | 0 | 0 | 13.7 | 32.46% | 0% | 0% | 0% | 32.46% | YES | NO | YES | N/A | Additional personal protective equipment needed to equip more field technicians than 6-year average (2017-2022) authorized due to increased workload caused by non-communicating meters. | Over (O) | Over (O) | On Target (T) | Proceeding as Planned | NO | N/A | The Smart Meter Operations cost category consists of labor and non-labor costs for Electric Metering Operations, Quality Assurance & Training, Network Operations, Electric Metering Engineering, Smart Meter Field Services and the Smart Meter Capital Program Team responsible for on-premise advanced metering customer service, customer inquiry investigations, customer metering problem remediation, and end-to-end management of the smart metering system, which includes field networking infrastructure, the metering head-end system, and integrations with the meter data management system. Collectively, the organizations are critical to enable accurate and timely bills for all of SDG&E’s metered customers, covering San Diego County and South Orange County and also responsible for meter data acquisition utilized by the operations and engineering organizations to enhance safety and reliability. | SDG&E-17-R DHT-30 to DHT-40 WP 1FC005.000
O&M | CS - FIELD OPERATIONS | SubTotal SMART METER OPERATIONS |  |  |  | Yes |  |  | 11190010.1969 | 0 | 0 | 0 | 11190010.1969 | 9423000 | 9705999.9984 | 9996999.9984 | 10296999.9996 | 9423000 | 1767010.1969 | -9705999.9984 | -9996999.9984 | -10296999.9996 | 1767010.1969 | 18.75% | -100% | -100% | -100% | 18.75% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CS - FIELD OPERATIONS | WORK MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3411605.7705 | 0 | 0 | 0 | 3411605.7705 | 3699999.9996 | 3810999.9996 | 3924999.9996 | 4042999.9992 | 3699999.9996 | -288394.2291 | -3810999.9996 | -3924999.9996 | -4042999.9992 | -288394.2291 | -7.794% | -100% | -100% | -100% | -7.794% | Work Management FTE | 25 |  |  |  | 25 | 29 |  |  |  | 29 | -4 | 0 | 0 | 0 | -4 | -13.79% | 0% | 0% | 0% | -13.79% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - FIELD OPERATIONS | SubTotal WORK MANAGEMENT |  |  |  | Yes |  |  | 3411605.7705 | 0 | 0 | 0 | 3411605.7705 | 3699999.9996 | 3810999.9996 | 3924999.9996 | 4042999.9992 | 3699999.9996 | -288394.2291 | -3810999.9996 | -3924999.9996 | -4042999.9992 | -288394.2291 | -7.794% | -100% | -100% | -100% | -7.794% | [21 empty] | YES | NO | [7 empty] | NO

## CSIN
SDG&E CUSTOMER SERVICES - INFORMATION O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CUSTOMER SERVICES - INFORMATION | CUSTOMER SERVICES - INFORMATION |  |  |  | Yes |  |  | 17607458.0481 | 0 | 0 | 0 | 17607458.0481 | 25708999.9968 | 26479999.9968 | 27273999.9984 | 28092999.9972 | 25708999.9968 | -8101541.9487 | -26479999.9968 | -27273999.9984 | -28092999.9972 | -8101541.9487 | -31.51% | -100% | -100% | -100% | -31.51%
O&M | CS - INFORMATION | CUSTOMER PRICING, LOAD RESEARCH, ANALYSIS, AND FORECASTING | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 4899086.6714 | 0 | 0 | 0 | 4899086.6714 | 4572999.9996 | 4710000 | 4851000 | 4996999.9992 | 4572999.9996 | 326086.6718 | -4710000 | -4851000 | -4996999.9992 | 326086.6718 | 7.131% | -100% | -100% | -100% | 7.131% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - INFORMATION | SubTotal CUSTOMER PRICING, LOAD RESEARCH, ANALYSIS, AND FORECASTING |  |  |  | Yes |  |  | 4899086.6714 | 0 | 0 | 0 | 4899086.6714 | 4572999.9996 | 4710000 | 4851000 | 4996999.9992 | 4572999.9996 | 326086.6718 | -4710000 | -4851000 | -4996999.9992 | 326086.6718 | 7.131% | -100% | -100% | -100% | 7.131% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - INFORMATION | CUSTOMER PROGRAMS AND BUSINESS SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 4817828.634 | 0 | 0 | 0 | 4817828.634 | 6504999.9996 | 6699999.9996 | 6900999.9996 | 7107999.9996 | 6504999.9996 | -1687171.3656 | -6699999.9996 | -6900999.9996 | -7107999.9996 | -1687171.3656 | -25.94% | -100% | -100% | -100% | -25.94% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - INFORMATION | SubTotal CUSTOMER PROGRAMS AND BUSINESS SERVICES |  |  |  | Yes |  |  | 4817828.634 | 0 | 0 | 0 | 4817828.634 | 6504999.9996 | 6699999.9996 | 6900999.9996 | 7107999.9996 | 6504999.9996 | -1687171.3656 | -6699999.9996 | -6900999.9996 | -7107999.9996 | -1687171.3656 | -25.94% | -100% | -100% | -100% | -25.94% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - INFORMATION | MARKETING, COMMUNICATIONS, RESEARCH AND ANALYTICS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 6769413.5111 | 0 | 0 | 0 | 6769413.5111 | 9358999.9992 | 9639999.9996 | 9928999.9992 | 10227000 | 9358999.9992 | -2589586.4881 | -9639999.9996 | -9928999.9992 | -10227000 | -2589586.4881 | -27.67% | -100% | -100% | -100% | -27.67% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - INFORMATION | SubTotal MARKETING, COMMUNICATIONS, RESEARCH AND ANALYTICS |  |  |  | Yes |  |  | 6769413.5111 | 0 | 0 | 0 | 6769413.5111 | 9358999.9992 | 9639999.9996 | 9928999.9992 | 10227000 | 9358999.9992 | -2589586.4881 | -9639999.9996 | -9928999.9992 | -10227000 | -2589586.4881 | -27.67% | -100% | -100% | -100% | -27.67% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - INFORMATION | RAMP - NATURAL GAS APPLIANCE TESTING (NGAT) | Incident Related to the Medium Pressure System (Excluding Dig-in) | RAMP Natural Gas Appliance Testing (NGAT) | Meter and Beyond the Meter | No | On-going | Annual | 301324.32 | 0 | 0 | 0 | 301324.32 | 712999.9992 | 733999.9992 | 756000 | 778999.9992 | 712999.9992 | -411675.6792 | -733999.9992 | -756000 | -778999.9992 | -411675.6792 | -57.74% | -100% | -100% | -100% | -57.74% | NGAT's (tests) Completed | 3754 |  |  |  | 3754 | 9190 |  |  |  | 9190 | -5436 | 0 | 0 | 0 | -5436 | -59.15% | 0% | 0% | 0% | -59.15% | YES | NO | YES | N/A | In 2024, the Energy Savings Assistance (ESA) Main Program anticipated completing 5,015 Natural Gas Appliance Testing (NGAT) jobs but only completed 2,795. Similarly, the Multifamily Whole Building (MFWB) Program anticipated completing 7,200 NGAT jobs but only completed 959. Both programs experienced a slower than anticipated start in 2024, which impacted the overall number of NGAT jobs completed. This slow start was due to various operational challenges and delays in project initiation. The MFWB Program was still in the process of ramping up during 2024. This included finalizing program policy and procedures and working through system challenges. Additionally, there were necessary revisions to the contract to address pricing concerns raised by our Implementer and subcontractors. These revisions were crucial to ensure the program's long-term success but contributed to the lower-than-expected NGAT job completion. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Natural Gas Appliance Testing (NGAT) or CO testing is a safety-related program for Customer Assistance's Energy Savings Assistance (ESA) Program participants. SDG&E conducts Carbon Monoxide (CO) testing on homes weatherized through the ESA Program in accordance with Statewide ESA Program Installation Standards and the Statewide ESA Program Policy and Procedures Manual. CPUC directives require SDG&E to charge the costs for the NGAT program to base rates rather than to the public purpose funds. | SDG&E-19-E SFB-27, SFB-34 to SFB-35 WP 1IN002.001
O&M | CS - INFORMATION | SubTotal RAMP - NATURAL GAS APPLIANCE TESTING (NGAT) |  |  |  | Yes |  |  | 301324.32 | 0 | 0 | 0 | 301324.32 | 712999.9992 | 733999.9992 | 756000 | 778999.9992 | 712999.9992 | -411675.6792 | -733999.9992 | -756000 | -778999.9992 | -411675.6792 | -57.74% | -100% | -100% | -100% | -57.74% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CS - INFORMATION | RAMP - SAFETY COMMUNICATIONS | Customer and Public Safety – Contact with Electric Equipment | RAMP General Safety Communications | Overall | No | On-going | Annual | 395440.9558 | 0 | 0 | 0 | 395440.9558 | 1767000 | 1819999.9992 | 1875000 | 1930999.9992 | 1767000 | -1371559.0442 | -1819999.9992 | -1875000 | -1930999.9992 | -1371559.0442 | -77.62% | -100% | -100% | -100% | -77.62% | Campaigns | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - INFORMATION | RAMP - SAFETY COMMUNICATIONS | Incident Related to the Medium Pressure System (Excluding Dig-in) | RAMP Gas Public Safety Communications | Overall | No | On-going | Annual | 424363.9558 | 0 | 0 | 0 | 424363.9558 | 2791999.9992 | 2875999.9992 | 2961999.9996 | 3051000 | 2791999.9992 | -2367636.0434 | -2875999.9992 | -2961999.9996 | -3051000 | -2367636.0434 | -84.8% | -100% | -100% | -100% | -84.8% | Campaigns | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CS - INFORMATION | SubTotal RAMP - SAFETY COMMUNICATIONS |  |  |  | Yes |  |  | 819804.9116 | 0 | 0 | 0 | 819804.9116 | 4558999.9992 | 4695999.9984 | 4836999.9996 | 4981999.9992 | 4558999.9992 | -3739195.0876 | -4695999.9984 | -4836999.9996 | -4981999.9992 | -3739195.0876 | -82.02% | -100% | -100% | -100% | -82.02% | [21 empty] | YES | YES |  | Lower than forecasted safety communications expenses due to forecasted O&M resources that were shifted to emergent reliability and compliance work. Safety communications were still achieved by executing more cost-effective tactics such as community outreach, email and social media. | [5 empty] | NO |  | SDG&E educates its customers and the public about the dangers and risks associated with working and being near electricity and electrical equipment, how to safely dig on their property or how to detect possible gas and electric safety issues within and around their home. Communications include bill inserts and onserts, television, web, social media, print, public service announcements, email, radio and other paid digital media. Messages include, but are not limited to carbon monoxide safety, fumigation, furnace safety, digging, how to detect gas leaks, and how to prevent electrical fire hazards | SDG&E-19-E SFB-17 to SFB-18 WP 1IN001.001

## CSOO
SDG&E CUSTOMER SERVICES - OFFICE OPERATIONS O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CUSTOMER SERVICES - OFFICE OPERATIONS | CUSTOMER SERVICES - OFFICE OPERATIONS |  |  |  | Yes |  |  | 39436219.2781 | 0 | 0 | 0 | 39436219.2781 | 36935999.9976 | 38043999.9972 | 39184999.9968 | 40360999.9956 | 36935999.9976 | 2500219.2805 | -38043999.9972 | -39184999.9968 | -40360999.9956 | 2500219.2805 | 6.769% | -100% | -100% | -100% | 6.769%
O&M | CS - OFFICE OPERATIONS | BILLING | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 7405916.5407 | 0 | 0 | 0 | 7405916.5407 | 7455999.9996 | 7680000 | 7909999.9992 | 8146999.9992 | 7455999.9996 | -50083.4589 | -7680000 | -7909999.9992 | -8146999.9992 | -50083.4589 | -0.6717% | -100% | -100% | -100% | -0.6717% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - OFFICE OPERATIONS | SubTotal BILLING |  |  |  | Yes |  |  | 7405916.5407 | 0 | 0 | 0 | 7405916.5407 | 7455999.9996 | 7680000 | 7909999.9992 | 8146999.9992 | 7455999.9996 | -50083.4589 | -7680000 | -7909999.9992 | -8146999.9992 | -50083.4589 | -0.6717% | -100% | -100% | -100% | -0.6717% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | BRANCH OFFICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1130284.6724 | 0 | 0 | 0 | 1130284.6724 | 0 | 0 | 0 | 0 | 0 | 1130284.6724 | 0 | 0 | 0 | 1130284.6724 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - OFFICE OPERATIONS | SubTotal BRANCH OFFICES |  |  |  | Yes |  |  | 1130284.6724 | 0 | 0 | 0 | 1130284.6724 | 0 | 0 | 0 | 0 | 0 | 1130284.6724 | 0 | 0 | 0 | 1130284.6724 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | CCC OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 14622324.538 | 0 | 0 | 0 | 14622324.538 | 12336000 | 12705999.9996 | 13086999.9996 | 13479999.9996 | 12336000 | 2286324.538 | -12705999.9996 | -13086999.9996 | -13479999.9996 | 2286324.538 | 18.53% | -100% | -100% | -100% | 18.53% | ESS Calls | 1254447 |  |  |  | 1254447 | 1501297 |  |  |  | 1501297 | -246850 | 0 | 0 | 0 | -246850 | -16.44% | 0% | 0% | 0% | -16.44% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Customer Contact Center (CCC) expenses include costs for a variety of customer interactions, including: answering telephone calls; responding to incoming email; responding to customer inquiries through on-line chat features; answering written customer correspondence regarding customer account activity; following up on all CPUC telephone referrals and informal and formal customer complaints; and, responding to other customer account-related inquiries. | SDG&E-18-E SFB-21 to SFB-26 WP1OO004.000
O&M | CS - OFFICE OPERATIONS | SubTotal |  |  |  | Yes |  |  | 14622324.538 | 0 | 0 | 0 | 14622324.538 | 12336000 | 12705999.9996 | 13086999.9996 | 13479999.9996 | 12336000 | 2286324.538 | -12705999.9996 | -13086999.9996 | -13479999.9996 | 2286324.538 | 18.53% | -100% | -100% | -100% | 18.53% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | CCC SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 4111885.2245 | 0 | 0 | 0 | 4111885.2245 | 4554999.9996 | 4692000 | 4833000 | 4977999.9996 | 4554999.9996 | -443114.7751 | -4692000 | -4833000 | -4977999.9996 | -443114.7751 | -9.728% | -100% | -100% | -100% | -9.728% | ESS Calls | 1254447 |  |  |  | 1254447 | 1501297 |  |  |  | 1501297 | -246850 | 0 | 0 | 0 | -246850 | -16.44% | 0% | 0% | 0% | -16.44% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Customer Contact Center (CCC) Support work group activities include resource planning and scheduling; technology support (including software licensing, maintenance and support service); training; quality assurance; policy and procedures support; planning and analysis functions; complaint resolution and clerical support. | SDG&E-18-E SFB-26 to SFB-28 WP1OO005.000
O&M | CS - OFFICE OPERATIONS | SubTotal |  |  |  | Yes |  |  | 4111885.2245 | 0 | 0 | 0 | 4111885.2245 | 4554999.9996 | 4692000 | 4833000 | 4977999.9996 | 4554999.9996 | -443114.7751 | -4692000 | -4833000 | -4977999.9996 | -443114.7751 | -9.728% | -100% | -100% | -100% | -9.728% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | CREDIT & COLLECTIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2087809.8532 | 0 | 0 | 0 | 2087809.8532 | 2367999.9996 | 2439000 | 2511999.9996 | 2586999.9996 | 2367999.9996 | -280190.1464 | -2439000 | -2511999.9996 | -2586999.9996 | -280190.1464 | -11.83% | -100% | -100% | -100% | -11.83% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - OFFICE OPERATIONS | SubTotal CREDIT & COLLECTIONS |  |  |  | Yes |  |  | 2087809.8532 | 0 | 0 | 0 | 2087809.8532 | 2367999.9996 | 2439000 | 2511999.9996 | 2586999.9996 | 2367999.9996 | -280190.1464 | -2439000 | -2511999.9996 | -2586999.9996 | -280190.1464 | -11.83% | -100% | -100% | -100% | -11.83% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | CUSTOMER OPERATIONS COMPLIANCE AND STRATEGY | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2962597.1221 | 0 | 0 | 0 | 2962597.1221 | 5244000 | 5400999.9996 | 5562999.9996 | 5730000 | 5244000 | -2281402.8779 | -5400999.9996 | -5562999.9996 | -5730000 | -2281402.8779 | -43.51% | -100% | -100% | -100% | -43.51% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - OFFICE OPERATIONS | SubTotal CUSTOMER OPERATIONS COMPLIANCE AND STRATEGY |  |  |  | Yes |  |  | 2962597.1221 | 0 | 0 | 0 | 2962597.1221 | 5244000 | 5400999.9996 | 5562999.9996 | 5730000 | 5244000 | -2281402.8779 | -5400999.9996 | -5562999.9996 | -5730000 | -2281402.8779 | -43.51% | -100% | -100% | -100% | -43.51% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | POSTAGE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 5480067.02 | 0 | 0 | 0 | 5480067.02 | 3825999.9996 | 3940999.9992 | 4059000 | 4180999.9992 | 3825999.9996 | 1654067.0204 | -3940999.9992 | -4059000 | -4180999.9992 | 1654067.0204 | 43.23% | -100% | -100% | -100% | 43.23% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - OFFICE OPERATIONS | SubTotal POSTAGE |  |  |  | Yes |  |  | 5480067.02 | 0 | 0 | 0 | 5480067.02 | 3825999.9996 | 3940999.9992 | 4059000 | 4180999.9992 | 3825999.9996 | 1654067.0204 | -3940999.9992 | -4059000 | -4180999.9992 | 1654067.0204 | 43.23% | -100% | -100% | -100% | 43.23% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | REMITTANCE PROCESSING | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1299134.5213 | 0 | 0 | 0 | 1299134.5213 | 769999.9992 | 792999.9996 | 816999.9996 | 841999.9992 | 769999.9992 | 529134.5221 | -792999.9996 | -816999.9996 | -841999.9992 | 529134.5221 | 68.72% | -100% | -100% | -100% | 68.72% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CS - OFFICE OPERATIONS | SubTotal REMITTANCE PROCESSING |  |  |  | Yes |  |  | 1299134.5213 | 0 | 0 | 0 | 1299134.5213 | 769999.9992 | 792999.9996 | 816999.9996 | 841999.9992 | 769999.9992 | 529134.5221 | -792999.9996 | -816999.9996 | -841999.9992 | 529134.5221 | 68.72% | -100% | -100% | -100% | 68.72% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CS - OFFICE OPERATIONS | SAFETY - METER REVENUE PROTECTION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 336199.7859 | 0 | 0 | 0 | 336199.7859 | 381000 | 391999.9992 | 403999.9992 | 415999.9992 | 381000 | -44800.2141 | -391999.9992 | -403999.9992 | -415999.9992 | -44800.2141 | -11.76% | -100% | -100% | -100% | -11.76% | Investigations/ Leads | 2160 |  |  |  | 2160 | 1659 |  |  |  | 1659 | 501 | 0 | 0 | 0 | 501 | 30.2% | 0% | 0% | 0% | 30.2% | YES | NO | YES | N/A | Higher than forecasted investigations as compared to base year 2021 forecast due to ramp-up of activities that were originally placed on hold for emergency customer protections. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Meter Revenue Protection investigates unauthorized attachments (also referred to as a “bypass”) that create unsafe conditions for our crews as well as public safety officers and first responders. Unauthorized attachments are not standard and violate electric code and local building ordinances. These connections present the potential for fire, electrical shock and a risk of electrocution to SDG&E service technicians, law enforcement, firefighters, city or county officials, occupants of the residence and/or community.. | SDG&E-18-E SFB-13 WP 1OO001.001
O&M | CS - OFFICE OPERATIONS | SubTotal SAFETY - METER REVENUE PROTECTION |  |  |  | Yes |  |  | 336199.7859 | 0 | 0 | 0 | 336199.7859 | 381000 | 391999.9992 | 403999.9992 | 415999.9992 | 381000 | -44800.2141 | -391999.9992 | -403999.9992 | -415999.9992 | -44800.2141 | -11.76% | -100% | -100% | -100% | -11.76% | [21 empty] | YES | NO | [7 empty] | NO

## ESEV
SDG&E ENVIRONMENTAL SERVICES AND SAN ONOFRE NUCLEAR GENERATING STATION ("SONGS') O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | ENVIRONMENTAL SERVICES AND SAN ONOFRE NUCLEAR GENERATING STATION ("SONGS') | ENVIRONMENTAL SERVICES AND SAN ONOFRE NUCLEAR GENERATING STATION ("SONGS') |  |  |  | Yes |  |  | 7132422.738 | 0 | 0 | 0 | 7132422.738 | 7969999.9992 | 8208999.9996 | 8454999.9996 | 8709000 | 7969999.9992 | -837577.2612 | -8208999.9996 | -8454999.9996 | -8709000 | -837577.2612 | -10.51% | -100% | -100% | -100% | -10.51%
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | ENVIRONMENTAL SDGE NSS COST CENTER | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 7132422.738 | 0 | 0 | 0 | 7132422.738 | 7969999.9992 | 8208999.9996 | 8454999.9996 | 8709000 | 7969999.9992 | -837577.2612 | -8208999.9996 | -8454999.9996 | -8709000 | -837577.2612 | -10.51% | -100% | -100% | -100% | -10.51% | FTE | 40.84 |  |  |  | 40.84 | 40.1 |  |  |  | 40.1 | 0.74 | 0 | 0 | 0 | 0.74 | 1.845% | 0% | 0% | 0% | 1.845% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal ENVIRONMENTAL SDGE NSS COST CENTER |  |  |  | Yes |  |  | 7132422.738 | 0 | 0 | 0 | 7132422.738 | 7969999.9992 | 8208999.9996 | 8454999.9996 | 8709000 | 7969999.9992 | -837577.2612 | -8208999.9996 | -8454999.9996 | -8709000 | -837577.2612 | -10.51% | -100% | -100% | -100% | -10.51% | [21 empty] | YES | NO | [7 empty] | NO

## SMFS
SDG&E FLEET SERVICES O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | FLEET SERVICES | FLEET SERVICES |  |  |  | Yes |  |  | 46245781.6073 | 0 | 0 | 0 | 46245781.6073 | 48493999.998 | 49948999.998 | 51447999.9972 | 52990999.9968 | 48493999.998 | -2248218.3907 | -49948999.998 | -51447999.9972 | -52990999.9968 | -2248218.3907 | -4.636% | -100% | -100% | -100% | -4.636%
O&M | FLEET SERVICES | ASSET MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1273400.7236 | 0 | 0 | 0 | 1273400.7236 | 1548000 | 1593999.9996 | 1641999.9996 | 1690999.9992 | 1548000 | -274599.2764 | -1593999.9996 | -1641999.9996 | -1690999.9992 | -274599.2764 | -17.74% | -100% | -100% | -100% | -17.74% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | FLEET SERVICES | SubTotal ASSET MANAGEMENT |  |  |  | Yes |  |  | 1273400.7236 | 0 | 0 | 0 | 1273400.7236 | 1548000 | 1593999.9996 | 1641999.9996 | 1690999.9992 | 1548000 | -274599.2764 | -1593999.9996 | -1641999.9996 | -1690999.9992 | -274599.2764 | -17.74% | -100% | -100% | -100% | -17.74% | [21 empty] | NO | NO | [7 empty] | NO
O&M | FLEET SERVICES | AUTOMOTIVE FUELS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 7276166.81 | 0 | 0 | 0 | 7276166.81 | 7569999.9996 | 7797000 | 8031000 | 8271999.9996 | 7569999.9996 | -293833.1896 | -7797000 | -8031000 | -8271999.9996 | -293833.1896 | -3.882% | -100% | -100% | -100% | -3.882% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | FLEET SERVICES | SubTotal AUTOMOTIVE FUELS |  |  |  | Yes |  |  | 7276166.81 | 0 | 0 | 0 | 7276166.81 | 7569999.9996 | 7797000 | 8031000 | 8271999.9996 | 7569999.9996 | -293833.1896 | -7797000 | -8031000 | -8271999.9996 | -293833.1896 | -3.882% | -100% | -100% | -100% | -3.882% | [21 empty] | NO | NO | [7 empty] | NO
O&M | FLEET SERVICES | COMMUTATION FEE CREDITS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | -287002.94 | 0 | 0 | 0 | -287002.94 | -271999.9992 | -279999.9996 | -288000 | -297000 | -271999.9992 | -15002.9408 | 279999.9996 | 288000 | 297000 | -15002.9408 | 5.516% | -100% | -100% | -100% | 5.516% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | FLEET SERVICES | SubTotal COMMUTATION FEE CREDITS |  |  |  | Yes |  |  | -287002.94 | 0 | 0 | 0 | -287002.94 | -271999.9992 | -279999.9996 | -288000 | -297000 | -271999.9992 | -15002.9408 | 279999.9996 | 288000 | 297000 | -15002.9408 | 5.516% | -100% | -100% | -100% | 5.516% | [21 empty] | NO | NO | [7 empty] | NO
O&M | FLEET SERVICES | EXISTING LEASES & FEES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 15228120.91 | 0 | 0 | 0 | 15228120.91 | 18027999.9996 | 18568999.9992 | 19125999.9996 | 19699999.9992 | 18027999.9996 | -2799879.0896 | -18568999.9992 | -19125999.9996 | -19699999.9992 | -2799879.0896 | -15.53% | -100% | -100% | -100% | -15.53% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | FLEET SERVICES | SubTotal EXISTING LEASES & FEES |  |  |  | Yes |  |  | 15228120.91 | 0 | 0 | 0 | 15228120.91 | 18027999.9996 | 18568999.9992 | 19125999.9996 | 19699999.9992 | 18027999.9996 | -2799879.0896 | -18568999.9992 | -19125999.9996 | -19699999.9992 | -2799879.0896 | -15.53% | -100% | -100% | -100% | -15.53% | [21 empty] | NO | NO | [7 empty] | NO
O&M | FLEET SERVICES | FINANCIAL & SYSTEMS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1815829.59 | 0 | 0 | 0 | 1815829.59 | 1293000 | 1332000 | 1371999.9996 | 1413000 | 1293000 | 522829.59 | -1332000 | -1371999.9996 | -1413000 | 522829.59 | 40.44% | -100% | -100% | -100% | 40.44% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | FLEET SERVICES | SubTotal FINANCIAL & SYSTEMS |  |  |  | Yes |  |  | 1815829.59 | 0 | 0 | 0 | 1815829.59 | 1293000 | 1332000 | 1371999.9996 | 1413000 | 1293000 | 522829.59 | -1332000 | -1371999.9996 | -1413000 | 522829.59 | 40.44% | -100% | -100% | -100% | 40.44% | [21 empty] | NO | NO | [7 empty] | NO
O&M | FLEET SERVICES | HYDROGEN FUEL-CELL VEHICLES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 9479 | 0 | 0 | 0 | 9479 | 30000 | 30999.9996 | 31999.9992 | 33000 | 30000 | -20521 | -30999.9996 | -31999.9992 | -33000 | -20521 | -68.4% | -100% | -100% | -100% | -68.4% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | FLEET SERVICES | SubTotal HYDROGEN FUEL-CELL VEHICLES |  |  |  | Yes |  |  | 9479 | 0 | 0 | 0 | 9479 | 30000 | 30999.9996 | 31999.9992 | 33000 | 30000 | -20521 | -30999.9996 | -31999.9992 | -33000 | -20521 | -68.4% | -100% | -100% | -100% | -68.4% | [21 empty] | NO | NO | [7 empty] | NO
O&M | FLEET SERVICES | MAINTENANCE GARAGE OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 16821456.1529 | 0 | 0 | 0 | 16821456.1529 | 14433000 | 14865999.9996 | 15312000 | 15771000 | 14433000 | 2388456.1529 | -14865999.9996 | -15312000 | -15771000 | 2388456.1529 | 16.55% | -100% | -100% | -100% | 16.55% | Vehicles and Equipment | 2262 |  |  |  | 2262 | 2122 |  |  |  | 2122 | 140 | 0 | 0 | 0 | 140 | 6.598% | 0% | 0% | 0% | 6.598% | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A
O&M | FLEET SERVICES | SubTotal MAINTENANCE GARAGE OPERATIONS |  |  |  | Yes |  |  | 16821456.1529 | 0 | 0 | 0 | 16821456.1529 | 14433000 | 14865999.9996 | 15312000 | 15771000 | 14433000 | 2388456.1529 | -14865999.9996 | -15312000 | -15771000 | 2388456.1529 | 16.55% | -100% | -100% | -100% | 16.55% | [21 empty] | YES | NO | [7 empty] | NO
O&M | FLEET SERVICES | MAINTENANCE OPERATIONS MANAGEMENT & SUPERVISION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 819669.3607 | 0 | 0 | 0 | 819669.3607 | 742999.9992 | 765000 | 787999.9992 | 811999.9992 | 742999.9992 | 76669.3615 | -765000 | -787999.9992 | -811999.9992 | 76669.3615 | 10.32% | -100% | -100% | -100% | 10.32% | FTE | 6 |  |  |  | 6 | 6 |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | FLEET SERVICES | SubTotal MAINTENANCE OPERATIONS MANAGEMENT & SUPERVISION |  |  |  | Yes |  |  | 819669.3607 | 0 | 0 | 0 | 819669.3607 | 742999.9992 | 765000 | 787999.9992 | 811999.9992 | 742999.9992 | 76669.3615 | -765000 | -787999.9992 | -811999.9992 | 76669.3615 | 10.32% | -100% | -100% | -100% | 10.32% | [21 empty] | YES | NO | [7 empty] | NO
O&M | FLEET SERVICES | REPLACEMENT PLAN AND SALVAGE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2885128 | 0 | 0 | 0 | 2885128 | 4156999.9992 | 4281999.9996 | 4410000 | 4542000 | 4156999.9992 | -1271871.9992 | -4281999.9996 | -4410000 | -4542000 | -1271871.9992 | -30.6% | -100% | -100% | -100% | -30.6% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | FLEET SERVICES | SubTotal REPLACEMENT PLAN AND SALVAGE |  |  |  | Yes |  |  | 2885128 | 0 | 0 | 0 | 2885128 | 4156999.9992 | 4281999.9996 | 4410000 | 4542000 | 4156999.9992 | -1271871.9992 | -4281999.9996 | -4410000 | -4542000 | -1271871.9992 | -30.6% | -100% | -100% | -100% | -30.6% | [21 empty] | NO | NO | [7 empty] | NO
O&M | FLEET SERVICES | TELEMATICS SERVICE FEES | Incident Involving an Employee | Enhanced Employee Safe DrivingTraining | Vehicle Incident | No | On-going | Annual | 403534 | 0 | 0 | 0 | 403534 | 963999.9996 | 993000 | 1023000 | 1053999.9996 | 963999.9996 | -560465.9996 | -993000 | -1023000 | -1053999.9996 | -560465.9996 | -58.14% | -100% | -100% | -100% | -58.14% | Vehicles and Equipment | 2262 |  |  |  | 2262 | 2122 |  |  |  | 2122 | 140 | 0 | 0 | 0 | 140 | 6.598% | 0% | 0% | 0% | 6.598% | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Proceeding as Planned | NO | N/A
O&M | FLEET SERVICES | SubTotal TELEMATICS SERVICE FEES |  |  |  | Yes |  |  | 403534 | 0 | 0 | 0 | 403534 | 963999.9996 | 993000 | 1023000 | 1053999.9996 | 963999.9996 | -560465.9996 | -993000 | -1023000 | -1053999.9996 | -560465.9996 | -58.14% | -100% | -100% | -100% | -58.14% | [21 empty] | YES | NO | [7 empty] | NO

## ESRE
SDG&E REAL ESTATE, LAND SERVICES & FACILITY OPERATIONS O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | REAL ESTATE, LAND SERVICES & FACILITY OPERATIONS | REAL ESTATE, LAND SERVICES & FACILITY OPERATIONS |  |  |  | Yes |  |  | 40913911.2229 | 0 | 0 | 0 | 40913911.2229 | 40356999.9948 | 41569999.9944 | 42815999.9964 | 44099999.9964 | 40356999.9948 | 556911.2281 | -41569999.9944 | -42815999.9964 | -44099999.9964 | 556911.2281 | 1.38% | -100% | -100% | -100% | 1.38%
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | CORPORATE REAL ESTATE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 769602.5676 | 0 | 0 | 0 | 769602.5676 | 666999.9996 | 687000 | 708000 | 729000 | 666999.9996 | 102602.568 | -687000 | -708000 | -729000 | 102602.568 | 15.38% | -100% | -100% | -100% | 15.38% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal CORPORATE REAL ESTATE |  |  |  | Yes |  |  | 769602.5676 | 0 | 0 | 0 | 769602.5676 | 666999.9996 | 687000 | 708000 | 729000 | 666999.9996 | 102602.568 | -687000 | -708000 | -729000 | 102602.568 | 15.38% | -100% | -100% | -100% | 15.38% | [21 empty] | NO | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | FACILITES OPS - SHARED SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 4256012.9692 | 0 | 0 | 0 | 4256012.9692 | 4351999.9992 | 4482999.9996 | 4617000 | 4755999.9996 | 4351999.9992 | -95987.03 | -4482999.9996 | -4617000 | -4755999.9996 | -95987.03 | -2.206% | -100% | -100% | -100% | -2.206% | Units are not available for this workpaper due to highly diverse activities and the absence of like units that would be comparable year over year. Facilities Operations' expenses consist of labor and non-labor costs necessary to maintain the Century Park Complex, Rancho Bernardo Data Center, and the Sempra Headquarters buildings. Some activities such as facility engineering and janitorial services are outsourced due to the size and complexity of the buildings. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal FACILITES OPS - SHARED SERVICES |  |  |  | Yes |  |  | 4256012.9692 | 0 | 0 | 0 | 4256012.9692 | 4351999.9992 | 4482999.9996 | 4617000 | 4755999.9996 | 4351999.9992 | -95987.03 | -4482999.9996 | -4617000 | -4755999.9996 | -95987.03 | -2.206% | -100% | -100% | -100% | -2.206% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | FACILITIES CAPITAL PROGRAMS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 78037.2805 | 0 | 0 | 0 | 78037.2805 | 165000 | 169999.9992 | 174999.9996 | 180000 | 165000 | -86962.7195 | -169999.9992 | -174999.9996 | -180000 | -86962.7195 | -52.7% | -100% | -100% | -100% | -52.7% | FTE | 0.4 |  |  |  | 0.4 | 1 |  |  |  | 1 | -0.6 | 0 | 0 | 0 | -0.6 | -60% | 0% | 0% | 0% | -60% | YES | NO | YES | N/A | The underrun in the unit variance for this workpaper is due to shifting FTEs to support the Century Park Building 4 tenant improvement as well as the Kearny Master Plan capital projects. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This cost center contains the costs for the facilities capital programs manager and support staff . This group is responsible for overall planning, budgeting, scheduling, tracking, and the implementation of authorized capital construction projects internal to our facilities, which support SDG&E and affiliates. | SDG&E-23 DT-24 to DT-25 WP 2100-3025.000
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal FACILITIES CAPITAL PROGRAMS |  |  |  | Yes |  |  | 78037.2805 | 0 | 0 | 0 | 78037.2805 | 165000 | 169999.9992 | 174999.9996 | 180000 | 165000 | -86962.7195 | -169999.9992 | -174999.9996 | -180000 | -86962.7195 | -52.7% | -100% | -100% | -100% | -52.7% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | HQ FACILITIES MAINTENANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1507901.0958 | 0 | 0 | 0 | 1507901.0958 | 1395000 | 1437000 | 1479999.9996 | 1524000 | 1395000 | 112901.0958 | -1437000 | -1479999.9996 | -1524000 | 112901.0958 | 8.093% | -100% | -100% | -100% | 8.093% | Square footage | 535140 |  |  |  | 535140 | 495072 |  |  |  | 495072 | 40068 | 0 | 0 | 0 | 40068 | 8.093% | 0% | 0% | 0% | 8.093% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal HQ FACILITIES MAINTENANCE |  |  |  | Yes |  |  | 1507901.0958 | 0 | 0 | 0 | 1507901.0958 | 1395000 | 1437000 | 1479999.9996 | 1524000 | 1395000 | 112901.0958 | -1437000 | -1479999.9996 | -1524000 | 112901.0958 | 8.093% | -100% | -100% | -100% | 8.093% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | REAL ESTATE PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1165192.923 | 0 | 0 | 0 | 1165192.923 | 1449999.9996 | 1494000 | 1539000 | 1584999.9996 | 1449999.9996 | -284807.0766 | -1494000 | -1539000 | -1584999.9996 | -284807.0766 | -19.64% | -100% | -100% | -100% | -19.64% | FTE | 3.7 |  |  |  | 3.7 | 6.9 |  |  |  | 6.9 | -3.2 | 0 | 0 | 0 | -3.2 | -46.38% | 0% | 0% | 0% | -46.38% | YES | NO | YES | N/A | The underrun in the unit variance for this workpaper is due to shifting FTEs to support the Century Park Building 4 tenant improvement as well as the Kearny Master Plan capital projects. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Real Estate Planning group provides space and site planning services to SDG&E, some affiliates and Corporate Center. This group also coordinates with our Moves, Adds, and Changes (MAC) team for employee moves involving furniture and equipment. | SDG&E-23 DT-25 to DT-26 WP 2100-0706.000
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal REAL ESTATE PLANNING |  |  |  | Yes |  |  | 1165192.923 | 0 | 0 | 0 | 1165192.923 | 1449999.9996 | 1494000 | 1539000 | 1584999.9996 | 1449999.9996 | -284807.0766 | -1494000 | -1539000 | -1584999.9996 | -284807.0766 | -19.64% | -100% | -100% | -100% | -19.64% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E FACILITIES OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-Going | Annual | 4925637.5612 | 0 | 0 | 0 | 4925637.5612 | 5904999.9996 | 6081999.9996 | 6264000 | 6451999.9992 | 5904999.9996 | -979362.4384 | -6081999.9996 | -6264000 | -6451999.9992 | -979362.4384 | -16.59% | -100% | -100% | -100% | -16.59% | Units are not available for this workpaper due to highly diverse activities and the absence of like units that would be comparable year over year. Facilities Operations' expenses consist of labor and non-labor costs necessary to maintain the construction and operations centers, telecommunication sites, warehouse and branch/bill payment offices. Some activities such as facility engineering and janitorial services are outsourced due to the size and complexity of the buildings. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal SDG&E FACILITIES OPERATIONS |  |  |  | Yes |  |  | 4925637.5612 | 0 | 0 | 0 | 4925637.5612 | 5904999.9996 | 6081999.9996 | 6264000 | 6451999.9992 | 5904999.9996 | -979362.4384 | -6081999.9996 | -6264000 | -6451999.9992 | -979362.4384 | -16.59% | -100% | -100% | -100% | -16.59% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E RENTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 6108159.43 | 0 | 0 | 0 | 6108159.43 | 5451000 | 5614999.9992 | 5782999.9992 | 5955999.9996 | 5451000 | 657159.43 | -5614999.9992 | -5782999.9992 | -5955999.9996 | 657159.43 | 12.06% | -100% | -100% | -100% | 12.06% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal SDG&E RENTS |  |  |  | Yes |  |  | 6108159.43 | 0 | 0 | 0 | 6108159.43 | 5451000 | 5614999.9992 | 5782999.9992 | 5955999.9996 | 5451000 | 657159.43 | -5614999.9992 | -5782999.9992 | -5955999.9996 | 657159.43 | 12.06% | -100% | -100% | -100% | 12.06% | [21 empty] | NO | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E SECURITY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-Going | Annual | 1858090.4599 | 0 | 0 | 0 | 1858090.4599 | 2044999.9992 | 2106999.9996 | 2169999.9996 | 2235000 | 2044999.9992 | -186909.5393 | -2106999.9996 | -2169999.9996 | -2235000 | -186909.5393 | -9.14% | -100% | -100% | -100% | -9.14% | Security guards | 36 |  |  |  | 36 | 36 |  |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E SECURITY | Physical Security | Contract Security | N/A | No | On-Going | Annual | 1858090.4599 | 0 | 0 | 0 | 1858090.4599 | 2044999.9992 | 2106000 | 2169000 | 2233999.9992 | 2044999.9992 | -186909.5393 | -2106000 | -2169000 | -2233999.9992 | -186909.5393 | -9.14% | -100% | -100% | -100% | -9.14% | Secuirty guards | 36 |  |  |  | 36 | 36 |  |  |  | 36 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal SDG&E SECURITY |  |  |  | Yes |  |  | 3716180.9198 | 0 | 0 | 0 | 3716180.9198 | 4089999.9984 | 4212999.9996 | 4338999.9996 | 4468999.9992 | 4089999.9984 | -373819.0786 | -4212999.9996 | -4338999.9996 | -4468999.9992 | -373819.0786 | -9.14% | -100% | -100% | -100% | -9.14% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SHARED SERVICES OPEX MAINT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-Going | Annual | 3392903.6378 | 0 | 0 | 0 | 3392903.6378 | 3261000 | 3358999.9992 | 3459999.9996 | 3564000 | 3261000 | 131903.6378 | -3358999.9992 | -3459999.9996 | -3564000 | 131903.6378 | 4.045% | -100% | -100% | -100% | 4.045% | Square footage | 450455 |  |  |  | 450455 | 432943 |  |  |  | 432943 | 17512 | 0 | 0 | 0 | 17512 | 4.045% | 0% | 0% | 0% | 4.045% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal SHARED SERVICES OPEX MAINT |  |  |  | Yes |  |  | 3392903.6378 | 0 | 0 | 0 | 3392903.6378 | 3261000 | 3358999.9992 | 3459999.9996 | 3564000 | 3261000 | 131903.6378 | -3358999.9992 | -3459999.9996 | -3564000 | 131903.6378 | 4.045% | -100% | -100% | -100% | 4.045% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SHARED SERVICES RENTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 13055332.7 | 0 | 0 | 0 | 13055332.7 | 12192999.9996 | 12558999.9996 | 12936000 | 13323999.9996 | 12192999.9996 | 862332.7004 | -12558999.9996 | -12936000 | -13323999.9996 | 862332.7004 | 7.072% | -100% | -100% | -100% | 7.072% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal SHARED SERVICES RENTS |  |  |  | Yes |  |  | 13055332.7 | 0 | 0 | 0 | 13055332.7 | 12192999.9996 | 12558999.9996 | 12936000 | 13323999.9996 | 12192999.9996 | 862332.7004 | -12558999.9996 | -12936000 | -13323999.9996 | 862332.7004 | 7.072% | -100% | -100% | -100% | 7.072% | [21 empty] | NO | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | TRIBAL RELATIONS & LAND SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-Going | Annual | 1476463.38 | 0 | 0 | 0 | 1476463.38 | 1029999.9996 | 1060999.9992 | 1092999.9996 | 1125999.9996 | 1029999.9996 | 446463.3804 | -1060999.9992 | -1092999.9996 | -1125999.9996 | 446463.3804 | 43.35% | -100% | -100% | -100% | 43.35% | FTE | 1.2 |  |  |  | 1.2 | 2.1 |  |  |  | 2.1 | -0.9 | 0 | 0 | 0 | -0.9 | -42.86% | 0% | 0% | 0% | -42.86% | YES | NO | YES | N/A | The underrun in the unit variance for this workpaper is due to shifting FTEs to support land easements for critical distribution and transmission capital projects. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Tribal Relations and Land Services provides land management, right of way and surveying services for protection and enforcement of land rights, securing easements, and right of ways, as well as the managment of survey contractors. Land Management responds to infractions (e.g., vehicle removal, gate/lock installation, or relocation of propane tanks under lines) of CPUC General Order operating standards and utility-developed standards related to land rights. Right of Way is responsible for the negotiation and acquisition of land rights in the form of easements, rights of way, licenses, and leases. Land Survey support is responsible for the management, service delivery, and quality assurance oversight of survey contractors. | SDG&E-23 DT-10 to DT-13 WP 1RE002.000
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal TRIBAL RELATIONS & LAND SERVICES |  |  |  | Yes |  |  | 1476463.38 | 0 | 0 | 0 | 1476463.38 | 1029999.9996 | 1060999.9992 | 1092999.9996 | 1125999.9996 | 1029999.9996 | 446463.3804 | -1060999.9992 | -1092999.9996 | -1125999.9996 | 446463.3804 | 43.35% | -100% | -100% | -100% | 43.35% | [21 empty] | YES | NO | [7 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | VP OPERATIONS SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 462486.7581 | 0 | 0 | 0 | 462486.7581 | 397999.9992 | 409999.9992 | 421999.9992 | 435000 | 397999.9992 | 64486.7589 | -409999.9992 | -421999.9992 | -435000 | 64486.7589 | 16.2% | -100% | -100% | -100% | 16.2% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SubTotal VP OPERATIONS SUPPORT |  |  |  | Yes |  |  | 462486.7581 | 0 | 0 | 0 | 462486.7581 | 397999.9992 | 409999.9992 | 421999.9992 | 435000 | 397999.9992 | 64486.7589 | -409999.9992 | -421999.9992 | -435000 | 64486.7589 | 16.2% | -100% | -100% | -100% | 16.2% | [21 empty] | NO | NO | [7 empty] | NO

## SMSS
SDG&E SUPPLY MANAGEMENT, LOGISTICS, & SUPPLIER DIVERSITY O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | SUPPLY MANAGEMENT, LOGISTICS, & SUPPLIER DIVERSITY | SUPPLY MANAGEMENT, LOGISTICS, & SUPPLIER DIVERSITY |  |  |  | Yes |  |  | 33966411.6428 | 0 | 0 | 0 | 33966411.6428 | 23325999.996 | 24026999.9964 | 24748999.9944 | 25490999.9952 | 23325999.996 | 10640411.6468 | -24026999.9964 | -24748999.9944 | -25490999.9952 | 10640411.6468 | 45.62% | -100% | -100% | -100% | 45.62%
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | CUSTOMER PROGRAMS & SUPPORT SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2608587.1099 | 0 | 0 | 0 | 2608587.1099 | 1311999.9996 | 1350999.9996 | 1392000 | 1434000 | 1311999.9996 | 1296587.1103 | -1350999.9996 | -1392000 | -1434000 | 1296587.1103 | 98.83% | -100% | -100% | -100% | 98.83% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal CUSTOMER PROGRAMS & SUPPORT SERVICES |  |  |  | Yes |  |  | 2608587.1099 | 0 | 0 | 0 | 2608587.1099 | 1311999.9996 | 1350999.9996 | 1392000 | 1434000 | 1311999.9996 | 1296587.1103 | -1350999.9996 | -1392000 | -1434000 | 1296587.1103 | 98.83% | -100% | -100% | -100% | 98.83% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | ELECTRIC PORTFOLIO | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3224865.0809 | 0 | 0 | 0 | 3224865.0809 | 2221999.9992 | 2289000 | 2358000 | 2428999.9992 | 2221999.9992 | 1002865.0817 | -2289000 | -2358000 | -2428999.9992 | 1002865.0817 | 45.13% | -100% | -100% | -100% | 45.13% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal ELECTRIC PORTFOLIO |  |  |  | Yes |  |  | 3224865.0809 | 0 | 0 | 0 | 3224865.0809 | 2221999.9992 | 2289000 | 2358000 | 2428999.9992 | 2221999.9992 | 1002865.0817 | -2289000 | -2358000 | -2428999.9992 | 1002865.0817 | 45.13% | -100% | -100% | -100% | 45.13% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | IT & TELECOM PORTFOLIO - SDG&E | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3749466.1833 | 0 | 0 | 0 | 3749466.1833 | 2151000 | 2215999.9992 | 2281999.9992 | 2349999.9996 | 2151000 | 1598466.1833 | -2215999.9992 | -2281999.9992 | -2349999.9996 | 1598466.1833 | 74.31% | -100% | -100% | -100% | 74.31% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal IT & TELECOM PORTFOLIO - SDG&E |  |  |  | Yes |  |  | 3749466.1833 | 0 | 0 | 0 | 3749466.1833 | 2151000 | 2215999.9992 | 2281999.9992 | 2349999.9996 | 2151000 | 1598466.1833 | -2215999.9992 | -2281999.9992 | -2349999.9996 | 1598466.1833 | 74.31% | -100% | -100% | -100% | 74.31% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | LOGISTICS SHOPS SOUTH - PURCHASING POOL | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 4280021.8157 | 0 | 0 | 0 | 4280021.8157 | 1290999.9996 | 1329999.9996 | 1369999.9992 | 1410999.9996 | 1290999.9996 | 2989021.8161 | -1329999.9996 | -1369999.9992 | -1410999.9996 | 2989021.8161 | 231.5% | -100% | -100% | -100% | 231.5% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal LOGISTICS SHOPS SOUTH - PURCHASING POOL |  |  |  | Yes |  |  | 4280021.8157 | 0 | 0 | 0 | 4280021.8157 | 1290999.9996 | 1329999.9996 | 1369999.9992 | 1410999.9996 | 1290999.9996 | 2989021.8161 | -1329999.9996 | -1369999.9992 | -1410999.9996 | 2989021.8161 | 231.5% | -100% | -100% | -100% | 231.5% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | LOGISTICS SHOPS SOUTH - WAREHOUSE POOL | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 9005204.0371 | 0 | 0 | 0 | 9005204.0371 | 7624999.9992 | 7854000 | 8089999.9992 | 8332999.9992 | 7624999.9992 | 1380204.0379 | -7854000 | -8089999.9992 | -8332999.9992 | 1380204.0379 | 18.1% | -100% | -100% | -100% | 18.1% | FTE | 44.6 |  |  |  | 44.6 | 50.8 | 50.8 | 50.8 | 50.8 | 50.8 | -6.2 | -50.8 | -50.8 | -50.8 | -6.2 | -12.2% | -100% | -100% | -100% | -12.2% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal LOGISTICS SHOPS SOUTH - WAREHOUSE POOL |  |  |  | Yes |  |  | 9005204.0371 | 0 | 0 | 0 | 9005204.0371 | 7624999.9992 | 7854000 | 8089999.9992 | 8332999.9992 | 7624999.9992 | 1380204.0379 | -7854000 | -8089999.9992 | -8332999.9992 | 1380204.0379 | 18.1% | -100% | -100% | -100% | 18.1% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | OFFICE SERVICES - NON-SHARED SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3471548.6 | 0 | 0 | 0 | 3471548.6 | 3363000 | 3463999.9992 | 3567999.9996 | 3675000 | 3363000 | 108548.6 | -3463999.9992 | -3567999.9996 | -3675000 | 108548.6 | 3.228% | -100% | -100% | -100% | 3.228% | This workpaper manages the third party service contractors that provide services to the copy centers, mail rooms, onsite food services, employee travel reservations and bookings, along with document archives and records management services. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal OFFICE SERVICES - NON-SHARED SERVICES |  |  |  | Yes |  |  | 3471548.6 | 0 | 0 | 0 | 3471548.6 | 3363000 | 3463999.9992 | 3567999.9996 | 3675000 | 3363000 | 108548.6 | -3463999.9992 | -3567999.9996 | -3675000 | 108548.6 | 3.228% | -100% | -100% | -100% | 3.228% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | OFFICE SERVICES - SHARED SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 487969.7775 | 0 | 0 | 0 | 487969.7775 | 564999.9996 | 582000 | 598999.9992 | 616999.9992 | 564999.9996 | -77030.2221 | -582000 | -598999.9992 | -616999.9992 | -77030.2221 | -13.63% | -100% | -100% | -100% | -13.63% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal OFFICE SERVICES - SHARED SERVICES |  |  |  | Yes |  |  | 487969.7775 | 0 | 0 | 0 | 487969.7775 | 564999.9996 | 582000 | 598999.9992 | 616999.9992 | 564999.9996 | -77030.2221 | -582000 | -598999.9992 | -616999.9992 | -77030.2221 | -13.63% | -100% | -100% | -100% | -13.63% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | STRATEGY & SUPPLY CHAIN SUSTAINABILITY | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2485307.8941 | 0 | 0 | 0 | 2485307.8941 | 858000 | 883999.9992 | 910999.9992 | 937999.9992 | 858000 | 1627307.8941 | -883999.9992 | -910999.9992 | -937999.9992 | 1627307.8941 | 189.7% | -100% | -100% | -100% | 189.7% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal STRATEGY & SUPPLY CHAIN SUSTAINABILITY |  |  |  | Yes |  |  | 2485307.8941 | 0 | 0 | 0 | 2485307.8941 | 858000 | 883999.9992 | 910999.9992 | 937999.9992 | 858000 | 1627307.8941 | -883999.9992 | -910999.9992 | -937999.9992 | 1627307.8941 | 189.7% | -100% | -100% | -100% | 189.7% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SUPPLIER DIVERSITY | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 939748.7624 | 0 | 0 | 0 | 939748.7624 | 940999.9992 | 969000 | 997999.9992 | 1027999.9992 | 940999.9992 | -1251.2368 | -969000 | -997999.9992 | -1027999.9992 | -1251.2368 | -0.133% | -100% | -100% | -100% | -0.133% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal SUPPLIER DIVERSITY |  |  |  | Yes |  |  | 939748.7624 | 0 | 0 | 0 | 939748.7624 | 940999.9992 | 969000 | 997999.9992 | 1027999.9992 | 940999.9992 | -1251.2368 | -969000 | -997999.9992 | -1027999.9992 | -1251.2368 | -0.133% | -100% | -100% | -100% | -0.133% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SUPPLY OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 611476.8424 | 0 | 0 | 0 | 611476.8424 | 1476999.9996 | 1521000 | 1566999.9996 | 1614000 | 1476999.9996 | -865523.1572 | -1521000 | -1566999.9996 | -1614000 | -865523.1572 | -58.6% | -100% | -100% | -100% | -58.6% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal SUPPLY OPERATIONS |  |  |  | Yes |  |  | 611476.8424 | 0 | 0 | 0 | 611476.8424 | 1476999.9996 | 1521000 | 1566999.9996 | 1614000 | 1476999.9996 | -865523.1572 | -1521000 | -1566999.9996 | -1614000 | -865523.1572 | -58.6% | -100% | -100% | -100% | -58.6% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | TECHNOLOGY, INTELLIGENCE, POLICY & SOLUTIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2385703.2272 | 0 | 0 | 0 | 2385703.2272 | 1521000 | 1566999.9996 | 1614000 | 1662000 | 1521000 | 864703.2272 | -1566999.9996 | -1614000 | -1662000 | 864703.2272 | 56.85% | -100% | -100% | -100% | 56.85% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal TECHNOLOGY, INTELLIGENCE, POLICY & SOLUTIONS |  |  |  | Yes |  |  | 2385703.2272 | 0 | 0 | 0 | 2385703.2272 | 1521000 | 1566999.9996 | 1614000 | 1662000 | 1521000 | 864703.2272 | -1566999.9996 | -1614000 | -1662000 | 864703.2272 | 56.85% | -100% | -100% | -100% | 56.85% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | GAS PORTFOLIO | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 716512.3124 | 0 | 0 | 0 | 716512.3124 | 0 | 0 | 0 | 0 | 0 | 716512.3124 | 0 | 0 | 0 | 716512.3124 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SubTotal GAS PORTFOLIO |  |  |  | Yes |  |  | 716512.3124 | 0 | 0 | 0 | 716512.3124 | 0 | 0 | 0 | 0 | 0 | 716512.3124 | 0 | 0 | 0 | 716512.3124 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO

## ITCS
SDG&E CYBERSECURITY O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CYBERSECURITY | CYBERSECURITY |  |  |  | Yes |  |  | 13795797.6568 | 0 | 0 | 0 | 13795797.6568 | 18165999.9996 | 18710999.9988 | 19272999.9996 | 19850999.9988 | 18165999.9996 | -4370202.3428 | -18710999.9988 | -19272999.9996 | -19850999.9988 | -4370202.3428 | -24.06% | -100% | -100% | -100% | -24.06%
O&M | CYBERSECURITY | NON-SHARED CYBERSECURITY | Cybersecurity | All Mitigations | Overall | No | On-going | Annual | 11922.27 | 0 | 0 | 0 | 11922.27 | 21999.9996 | 22999.9992 | 24000 | 24999.9996 | 21999.9996 | -10077.7296 | -22999.9992 | -24000 | -24999.9996 | -10077.7296 | -45.81% | -100% | -100% | -100% | -45.81% | The types of functions in this area include compliance with North American Electric Reliability Corporation (NERC) Critical Infrastructure Protection (CIP) regulatory requirements which consist of maintaining asset list inventory of our critical cyber assets, ensuring cybersecurity awareness, background checks, designating an electronic and physical security perimeter, providing security controls, incident reporting, vulnerability change management, protecting our Bulk Electric System (BES) cybersecurity information locations, and ensuring we have CIP sign-off on compliance requirements. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | CYBERSECURITY | SubTotal NON-SHARED CYBERSECURITY |  |  |  | Yes |  |  | 11922.27 | 0 | 0 | 0 | 11922.27 | 21999.9996 | 22999.9992 | 24000 | 24999.9996 | 21999.9996 | -10077.7296 | -22999.9992 | -24000 | -24999.9996 | -10077.7296 | -45.81% | -100% | -100% | -100% | -45.81% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CYBERSECURITY | SHARED CYBERSECURITY | Cybersecurity | All Mitigations | Overall | No | On-going | Annual | 13783875.3869 | 0 | 0 | 0 | 13783875.3869 | 18144000 | 18687999.9996 | 19248999.9996 | 19825999.9992 | 18144000 | -4360124.6131 | -18687999.9996 | -19248999.9996 | -19825999.9992 | -4360124.6131 | -24.03% | -100% | -100% | -100% | -24.03% | FTE | 46.1 |  |  |  | 46.1 | 67.1 |  |  |  | 67.1 | -21 | 0 | 0 | 0 | -21 | -31.3% | 0% | 0% | 0% | -31.3% | YES | YES | YES | Cybersecurity initiatives focused on infrastructure upgrades, perimeter defense improvements, and replacing outdated technology. Staffing levels were lower than authorized due to the delayed GRC decision. | Cybersecurity initiatives focused on infrastructure upgrades, perimeter defense improvements, and replacing outdated technology. Staffing levels were lower than authorized due to the delayed GRC decision. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The shared SDG&E cybersecurity costs represent labor and non-labor for the cybersecurity area where costs are shared between multiple business units and support the objectives of operating and maintaining the company infrastructure systems safely and reliably. Cybersecurity supports the necessary resources and systems maintenance needs of the following functional cybersecurity areas: threat Intelligence; monitoring, alerting and detection; systems operations; incident response; insider threat; vulnerability management; assessments; compliance; risk management; program office; consulting and engineering. | SDG&E-26-R LRM-14 to LRM-19 WP 2100-3101.000
O&M | CYBERSECURITY | SubTotal SHARED CYBERSECURITY |  |  |  | Yes |  |  | 13783875.3869 | 0 | 0 | 0 | 13783875.3869 | 18144000 | 18687999.9996 | 19248999.9996 | 19825999.9992 | 18144000 | -4360124.6131 | -18687999.9996 | -19248999.9996 | -19825999.9992 | -4360124.6131 | -24.03% | -100% | -100% | -100% | -24.03% | [21 empty] | YES | YES | [7 empty] | NO

## ITIT
SDG&E INFORMATION TECHNOLOGY O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | INFORMATION TECHNOLOGY | INFORMATION TECHNOLOGY |  |  |  | Yes |  |  | 92590404.661 | 0 | 0 | 0 | 92590404.661 | 111804999.9948 | 115159999.9932 | 118613999.9964 | 122172999.9936 | 111804999.9948 | -19214595.3338 | -115159999.9932 | -118613999.9964 | -122172999.9936 | -19214595.3338 | -17.19% | -100% | -100% | -100% | -17.19%
O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 12141666.3427 | 0 | 0 | 0 | 12141666.3427 | 12342999.9996 | 12712999.9992 | 13095000 | 13488000 | 12342999.9996 | -201333.6569 | -12712999.9992 | -13095000 | -13488000 | -201333.6569 | -1.631% | -100% | -100% | -100% | -1.631% | FTE | 14.3 |  |  |  | 14.3 | 40 |  |  |  | 40 | -25.7 | 0 | 0 | 0 | -25.7 | -64.25% | 0% | 0% | 0% | -64.25% | YES | NO | YES | N/A | Internal resources charged more labor to customer service capital projects undertaken to enhance customer self service and experience. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The non-shared SDG&E IT costs represent labor and non-labor for technology systems where 100% of the activities directly support the objectives of operating and maintaining SDG&E infrastructure systems safely and reliably. The types of functions supported in this area include customer billing and revenue management, smart grid and electric operations, meter data services, smart grid and electric operations portfolio management office, applications and utility operations maintenance agreements, and customer information systems (CIS) operations. Customer information systems includes ongoing costs related to the CIS replacement | SDG&E-25 TLB-12 to TLB-14 WP 1IT002.000
O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL APPLICATIONS | Foundational Technology Systems | All Mitigations | N/A | No | On-going | Annual | 1789947.4574 | 0 | 0 | 0 | 1789947.4574 | 1818999.9996 | 1873999.9992 | 1929999.9996 | 1987999.9992 | 1818999.9996 | -29052.5422 | -1873999.9992 | -1929999.9996 | -1987999.9992 | -29052.5422 | -1.597% | -100% | -100% | -100% | -1.597% | FTE | 2.1 |  |  |  | 2.1 | 5.9 |  |  |  | 5.9 | -3.8 | 0 | 0 | 0 | -3.8 | -64.41% | 0% | 0% | 0% | -64.41% | YES | NO | YES | N/A | Internal resources charged more labor to customer service capital projects undertaken to enhance customer self service and experience. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The non-shared SDG&E IT costs represent labor and non-labor for technology systems where 100% of the activities directly support the objectives of operating and maintaining SDG&E infrastructure systems safely and reliably. The types of functions supported in this area include customer billing and revenue management, smart grid and electric operations, meter data services, smart grid and electric operations portfolio management office, applications and utility operations maintenance agreements, and customer information systems (CIS) operations. Customer information systems includes ongoing costs related to the CIS replacement | SDG&E-25 TLB-12 to TLB-14 WP 1IT002.000
O&M | INFORMATION TECHNOLOGY | SubTotal NON-SHARED OPERATIONAL APPLICATIONS |  |  |  | Yes |  |  | 13931613.8001 | 0 | 0 | 0 | 13931613.8001 | 14161999.9992 | 14586999.9984 | 15024999.9996 | 15475999.9992 | 14161999.9992 | -230386.1991 | -14586999.9984 | -15024999.9996 | -15475999.9992 | -230386.1991 | -1.627% | -100% | -100% | -100% | -1.627% | [21 empty] | YES | NO | [7 empty] | NO
O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 5084677.2732 | 0 | 0 | 0 | 5084677.2732 | 4801999.9992 | 4945999.9992 | 5094999.9996 | 5247999.9996 | 4801999.9992 | 282677.274 | -4945999.9992 | -5094999.9996 | -5247999.9996 | 282677.274 | 5.887% | -100% | -100% | -100% | 5.887% | This area encompasses IT operations, including outsourced services and hardware/software maintenance, which support SDG&E infrastructure. Key tasks involve OT network monitoring, troubleshooting, and IT support (servers, storage, disaster recovery, communication, databases, security, and user assistance) to ensure infrastructure reliability. Microsoft licenses and subscriptions, like M365, GitHub Enterprise, Power BI, and more, are essential for smooth operations and meeting diverse organizational needs. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL INFRASTRUCTURE | Foundational Technology Systems | All Mitigations | N/A | No | On-going | Annual | 3022588.0367 | 0 | 0 | 0 | 3022588.0367 | 2853000 | 2938999.9992 | 3027000 | 3117999.9996 | 2853000 | 169588.0367 | -2938999.9992 | -3027000 | -3117999.9996 | 169588.0367 | 5.944% | -100% | -100% | -100% | 5.944% | This area encompasses IT operations, including outsourced services and hardware/software maintenance, which support SDG&E infrastructure. Key tasks involve OT network monitoring, troubleshooting, and IT support (servers, storage, disaster recovery, communication, databases, security, and user assistance) to ensure infrastructure reliability. Microsoft licenses and subscriptions, like M365, GitHub Enterprise, Power BI, and more, are essential for smooth operations and meeting diverse organizational needs. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | INFORMATION TECHNOLOGY | SubTotal NON-SHARED OPERATIONAL INFRASTRUCTURE |  |  |  | Yes |  |  | 8107265.31 | 0 | 0 | 0 | 8107265.31 | 7654999.9992 | 7884999.9984 | 8121999.9996 | 8365999.9992 | 7654999.9992 | 452265.3108 | -7884999.9984 | -8121999.9996 | -8365999.9992 | 452265.3108 | 5.908% | -100% | -100% | -100% | 5.908% | [21 empty] | YES | NO | [7 empty] | NO
O&M | INFORMATION TECHNOLOGY | SHARED APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 15845031.7502 | 0 | 0 | 0 | 15845031.7502 | 21342999.9996 | 21982999.9992 | 22641999.9996 | 23320999.9992 | 21342999.9996 | -5497968.2494 | -21982999.9992 | -22641999.9996 | -23320999.9992 | -5497968.2494 | -25.76% | -100% | -100% | -100% | -25.76% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | INFORMATION TECHNOLOGY | SubTotal SHARED APPLICATIONS |  |  |  | Yes |  |  | 15845031.7502 | 0 | 0 | 0 | 15845031.7502 | 21342999.9996 | 21982999.9992 | 22641999.9996 | 23320999.9992 | 21342999.9996 | -5497968.2494 | -21982999.9992 | -22641999.9996 | -23320999.9992 | -5497968.2494 | -25.76% | -100% | -100% | -100% | -25.76% | [21 empty] | NO | NO | [7 empty] | NO
O&M | INFORMATION TECHNOLOGY | SHARED INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3369453.7716 | 0 | 0 | 0 | 3369453.7716 | 4398999.9996 | 4530999.9996 | 4666999.9992 | 4806999.9996 | 4398999.9996 | -1029546.228 | -4530999.9996 | -4666999.9992 | -4806999.9996 | -1029546.228 | -23.4% | -100% | -100% | -100% | -23.4% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | INFORMATION TECHNOLOGY | SubTotal SHARED INFRASTRUCTURE |  |  |  | Yes |  |  | 3369453.7716 | 0 | 0 | 0 | 3369453.7716 | 4398999.9996 | 4530999.9996 | 4666999.9992 | 4806999.9996 | 4398999.9996 | -1029546.228 | -4530999.9996 | -4666999.9992 | -4806999.9996 | -1029546.228 | -23.4% | -100% | -100% | -100% | -23.4% | [21 empty] | NO | NO | [7 empty] | NO
O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 10681894.9695 | 0 | 0 | 0 | 10681894.9695 | 14163999.9996 | 14589000 | 15027000 | 15477999.9996 | 14163999.9996 | -3482105.0301 | -14589000 | -15027000 | -15477999.9996 | -3482105.0301 | -24.58% | -100% | -100% | -100% | -24.58% | FTE | 24 |  |  |  | 24 | 48.7 |  |  |  | 48.7 | -24.7 | 0 | 0 | 0 | -24.7 | -50.72% | 0% | 0% | 0% | -50.72% | YES | YES | YES | Underrun in spend is driven by a shift from internal labor to external resources. This shift was due to internal resources shift to customer service capital projects. | Underrun in FTEs is driven by a shift from internal labor to external resources. This shift was due internal resources shift to customer service capital-related work. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The shared SDG&E IT costs represent labor and non-labor for technology systems where costs are shared between multiple business units and support the objectives of operating and maintaining the company infrastructure systems safely and reliably. The types of systems supported in this area include utility operations, work management, business intelligence, analytics and reporting, and emergency operations. The types of functions supported in this area include systems engineering, systems architecture and integration, portfolio management services, applications outsourced services, and software maintenance agreements. | SDG&E-25 TLB-15 to TLB-18 WP 2100-3073.000
O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL APPLICATIONS | Foundational Technology Systems | All Mitigations | N/A | No | On-going | Annual | 2155097.524 | 0 | 0 | 0 | 2155097.524 | 2856999.9996 | 2943000 | 3030999.9996 | 3121999.9992 | 2856999.9996 | -701902.4756 | -2943000 | -3030999.9996 | -3121999.9992 | -701902.4756 | -24.57% | -100% | -100% | -100% | -24.57% | FTE | 4.9 |  |  |  | 4.9 | 9.8 |  |  |  | 9.8 | -4.9 | 0 | 0 | 0 | -4.9 | -50% | 0% | 0% | 0% | -50% | YES | NO | YES | N/A | Underrun in FTEs is driven by a shift from internal labor to external resources. This shift was due to internal resources shift to customer service capital-related work. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The shared SDG&E IT applications costs represent labor and non-labor for technology systems where costs are shared between multiple business units and support the objectives of operating and maintaining the company infrastructure systems safely and reliably. The types of systems supported in this area include utility operations, work management, business intelligence, analytics and reporting, and emergency operations. The types of functions supported in this area include systems engineering, systems architecture and integration, portfolio management services, applications outsourced services, and software maintenance agreements. | SDG&E-25 TLB-15 to TLB-18 WP 2100-3073.000
O&M | INFORMATION TECHNOLOGY | SubTotal SHARED OPERATIONAL APPLICATIONS |  |  |  | Yes |  |  | 12836992.4936 | 0 | 0 | 0 | 12836992.4936 | 17020999.9992 | 17532000 | 18057999.9996 | 18599999.9988 | 17020999.9992 | -4184007.5056 | -17532000 | -18057999.9996 | -18599999.9988 | -4184007.5056 | -24.58% | -100% | -100% | -100% | -24.58% | [21 empty] | YES | YES | [7 empty] | NO
O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 10853553.5205 | 0 | 0 | 0 | 10853553.5205 | 13188999.9996 | 13584999.9996 | 13992999.9996 | 14412999.9996 | 13188999.9996 | -2335446.4791 | -13584999.9996 | -13992999.9996 | -14412999.9996 | -2335446.4791 | -17.71% | -100% | -100% | -100% | -17.71% | FTE | 14.2 |  |  |  | 14.2 | 14.8 |  |  |  | 14.8 | -0.6 | 0 | 0 | 0 | -0.6 | -4.054% | 0% | 0% | 0% | -4.054% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL INFRASTRUCTURE | Foundational Technology Systems | All Mitigations | N/A | No | On-going | Annual | 19875209.7255 | 0 | 0 | 0 | 19875209.7255 | 21741000 | 22392999.9996 | 23064000 | 23755999.9992 | 21741000 | -1865790.2745 | -22392999.9996 | -23064000 | -23755999.9992 | -1865790.2745 | -8.582% | -100% | -100% | -100% | -8.582% | FTE | 26.1 |  |  |  | 26.1 | 27 |  |  |  | 27 | -0.9 | 0 | 0 | 0 | -0.9 | -3.333% | 0% | 0% | 0% | -3.333% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | INFORMATION TECHNOLOGY | SubTotal SHARED OPERATIONAL INFRASTRUCTURE |  |  |  | Yes |  |  | 30728763.2461 | 0 | 0 | 0 | 30728763.2461 | 34929999.9996 | 35977999.9992 | 37056999.9996 | 38168999.9988 | 34929999.9996 | -4201236.7535 | -35977999.9992 | -37056999.9996 | -38168999.9988 | -4201236.7535 | -12.03% | -100% | -100% | -100% | -12.03% | [21 empty] | YES | NO | [7 empty] | NO
O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2226148.4151 | 0 | 0 | 0 | 2226148.4151 | 4015999.9992 | 4135999.9992 | 4260000 | 4387999.9992 | 4015999.9992 | -1789851.5841 | -4135999.9992 | -4260000 | -4387999.9992 | -1789851.5841 | -44.57% | -100% | -100% | -100% | -44.57% | FTE | 6.7 |  |  |  | 6.7 | 17.8 |  |  |  | 17.8 | -11.1 | 0 | 0 | 0 | -11.1 | -62.36% | 0% | 0% | 0% | -62.36% | YES | NO | YES | N/A | The reduction in FTEs is due to shifting from internal labor to external resources, allowing internal staff to focus on Capital-related tasks | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The shared SDG&E IT support costs represent labor and non-labor for technology systems where costs are shared between multiple business units and support the objectives of operating and maintaining the company infrastructure systems safely and reliably. The types of services supported in this area include quality assurance, release and environment management, enterprise monitoring, and solutions architecture. | SDG&E-25 TLB-19 to TLB-20 WP 2100-0460.000
O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL SUPPORT | Foundational Technology Systems | All Mitigations | N/A | No | On-going | Annual | 508952.8831 | 0 | 0 | 0 | 508952.8831 | 918000 | 945999.9996 | 973999.9992 | 1002999.9996 | 918000 | -409047.1169 | -945999.9996 | -973999.9992 | -1002999.9996 | -409047.1169 | -44.56% | -100% | -100% | -100% | -44.56% | FTE | 1.5 |  |  |  | 1.5 | 4.1 |  |  |  | 4.1 | -2.6 | 0 | 0 | 0 | -2.6 | -63.41% | 0% | 0% | 0% | -63.41% | YES | NO | YES | N/A | The reduction in FTEs is due to shifting from internal labor to external resources, allowing internal staff to focus on Capital-related tasks | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The shared SDG&E IT support costs represent labor and non-labor for technology systems where costs are shared between multiple business units and support the objectives of operating and maintaining the company infrastructure systems safely and reliably. The types of services supported in this area include quality assurance, release and environment management, enterprise monitoring, and solutions architecture. | SDG&E-25 TLB-19 to TLB-20 WP 2100-0460.000
O&M | INFORMATION TECHNOLOGY | SubTotal SHARED OPERATIONAL SUPPORT |  |  |  | Yes |  |  | 2735101.2982 | 0 | 0 | 0 | 2735101.2982 | 4933999.9992 | 5081999.9988 | 5233999.9992 | 5390999.9988 | 4933999.9992 | -2198898.701 | -5081999.9988 | -5233999.9992 | -5390999.9988 | -2198898.701 | -44.57% | -100% | -100% | -100% | -44.57% | [21 empty] | YES | NO | [7 empty] | NO
O&M | INFORMATION TECHNOLOGY | SHARED SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 5036182.9912 | 0 | 0 | 0 | 5036182.9912 | 7360999.9992 | 7581999.9996 | 7809000 | 8043000 | 7360999.9992 | -2324817.008 | -7581999.9996 | -7809000 | -8043000 | -2324817.008 | -31.58% | -100% | -100% | -100% | -31.58% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | INFORMATION TECHNOLOGY | SubTotal SHARED SUPPORT |  |  |  | Yes |  |  | 5036182.9912 | 0 | 0 | 0 | 5036182.9912 | 7360999.9992 | 7581999.9996 | 7809000 | 8043000 | 7360999.9992 | -2324817.008 | -7581999.9996 | -7809000 | -8043000 | -2324817.008 | -31.58% | -100% | -100% | -100% | -31.58% | [21 empty] | NO | NO | [7 empty] | NO

## AGHR
SDG&E PEOPLE AND CULTURE DEPARTMENT O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | PEOPLE AND CULTURE DEPARTMENT | PEOPLE AND CULTURE DEPARTMENT |  |  |  | Yes |  |  | 19183354.6831 | 0 | 0 | 0 | 19183354.6831 | 19036999.9944 | 19609999.9956 | 20196999.9948 | 20801999.9928 | 19036999.9944 | 146354.6887 | -19609999.9956 | -20196999.9948 | -20801999.9928 | 146354.6887 | 0.7688% | -100% | -100% | -100% | 0.7688%
O&M | PEOPLE AND CULTURE DEPARTMENT | BUSINESS IMPROVEMENT AND PROCESS OPTIMIZATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 347180.6295 | 0 | 0 | 0 | 347180.6295 | 294999.9996 | 303999.9996 | 312999.9996 | 321999.9996 | 294999.9996 | 52180.6299 | -303999.9996 | -312999.9996 | -321999.9996 | 52180.6299 | 17.69% | -100% | -100% | -100% | 17.69% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal BUSINESS IMPROVEMENT AND PROCESS OPTIMIZATION |  |  |  | Yes |  |  | 347180.6295 | 0 | 0 | 0 | 347180.6295 | 294999.9996 | 303999.9996 | 312999.9996 | 321999.9996 | 294999.9996 | 52180.6299 | -303999.9996 | -312999.9996 | -321999.9996 | 52180.6299 | 17.69% | -100% | -100% | -100% | 17.69% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | BUSINESS OPTIMIZATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 0 | 0 | 0 | 0 | 0 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 127999.9992 | -127999.9992 | -132000 | -135999.9996 | -139999.9992 | -127999.9992 | -100% | -100% | -100% | -100% | -100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | YES
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal BUSINESS OPTIMIZATION |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 127999.9992 | -127999.9992 | -132000 | -135999.9996 | -139999.9992 | -127999.9992 | -100% | -100% | -100% | -100% | -100% | [21 empty] | NO | NO | [7 empty] | YES
O&M | PEOPLE AND CULTURE DEPARTMENT | DIVERSITY AND INCLUSION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 518570.876 | 0 | 0 | 0 | 518570.876 | 625999.9992 | 645000 | 663999.9996 | 684000 | 625999.9992 | -107429.1232 | -645000 | -663999.9996 | -684000 | -107429.1232 | -17.16% | -100% | -100% | -100% | -17.16% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal DIVERSITY AND INCLUSION |  |  |  | Yes |  |  | 518570.876 | 0 | 0 | 0 | 518570.876 | 625999.9992 | 645000 | 663999.9996 | 684000 | 625999.9992 | -107429.1232 | -645000 | -663999.9996 | -684000 | -107429.1232 | -17.16% | -100% | -100% | -100% | -17.16% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | DIVERSITY AND WORKFORCE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2453930.9968 | 0 | 0 | 0 | 2453930.9968 | 3259999.9992 | 3357999.9996 | 3459000 | 3562999.9992 | 3259999.9992 | -806069.0024 | -3357999.9996 | -3459000 | -3562999.9992 | -806069.0024 | -24.73% | -100% | -100% | -100% | -24.73% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal DIVERSITY AND WORKFORCE MANAGEMENT |  |  |  | Yes |  |  | 2453930.9968 | 0 | 0 | 0 | 2453930.9968 | 3259999.9992 | 3357999.9996 | 3459000 | 3562999.9992 | 3259999.9992 | -806069.0024 | -3357999.9996 | -3459000 | -3562999.9992 | -806069.0024 | -24.73% | -100% | -100% | -100% | -24.73% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | DRUG AND ALCOHOL TESTING PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 194100.0029 | 0 | 0 | 0 | 194100.0029 | 105000 | 108000 | 111000 | 114999.9996 | 105000 | 89100.0029 | -108000 | -111000 | -114999.9996 | 89100.0029 | 84.86% | -100% | -100% | -100% | 84.86% | FTE | 2 |  |  |  | 2 | 1.8 |  |  |  | 1.8 | 0.2 | 0 | 0 | 0 | 0.2 | 0.11111 | 0 | 0 | 0 | 0.11111 | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | PEOPLE AND CULTURE DEPARTMENT | DRUG AND ALCOHOL TESTING PROGRAM | Incident Involving an Employee | Drug & Alcohol Testing Program | N/A | No | On-going | Annual | 166215.85 | 0 | 0 | 0 | 166215.85 | 138999.9996 | 142999.9992 | 147999.9996 | 151999.9992 | 138999.9996 | 27215.8504 | -142999.9992 | -147999.9996 | -151999.9992 | 27215.8504 | 19.58% | -100% | -100% | -100% | 19.58% | Drug tests administered | 1073 |  |  |  | 1073 | 1680 |  |  |  | 1680 | -607 | 0 | 0 | 0 | -607 | -0.36131 | 0 | 0 | 0 | -0.36131 | YES | NO | YES | N/A | DOT Random testing percentages change from year to year, based on national positivity rates. Random follow-up testing rates change from year to year. As a company SDG&E has had less employees participate in its follow-up program compared to authorized numbers in 2024. Less positive drug tests mean less follow-up drug and alcohol testing. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The administration of this testing program includes management and oversight of all pre-employment, random, and other required drug and alcohol testing of employees in safety-sensitive positions under the Department of Transportation (DOT) regulations. | SDG&E-32-2E AGT-37 to AGT-38 WP 2100-3414.000
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal DRUG AND ALCOHOL TESTING PROGRAM |  |  |  | Yes |  |  | 360315.8529 | 0 | 0 | 0 | 360315.8529 | 243999.9996 | 250999.9992 | 258999.9996 | 266999.9988 | 243999.9996 | 116315.8533 | -250999.9992 | -258999.9996 | -266999.9988 | 116315.8533 | 47.67% | -100% | -100% | -100% | 47.67% | [21 empty] | YES | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | EMPLOYEE CARE SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1149043.5141 | 0 | 0 | 0 | 1149043.5141 | 1533000 | 1578999.9996 | 1626000 | 1674999.9996 | 1533000 | -383956.4859 | -1578999.9996 | -1626000 | -1674999.9996 | -383956.4859 | -25.05% | -100% | -100% | -100% | -25.05% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal EMPLOYEE CARE SERVICES |  |  |  | Yes |  |  | 1149043.5141 | 0 | 0 | 0 | 1149043.5141 | 1533000 | 1578999.9996 | 1626000 | 1674999.9996 | 1533000 | -383956.4859 | -1578999.9996 | -1626000 | -1674999.9996 | -383956.4859 | -25.05% | -100% | -100% | -100% | -25.05% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | EXECUTIVE OFFICES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 591082.765 | 0 | 0 | 0 | 591082.765 | 1203999.9996 | 1239999.9996 | 1276999.9992 | 1314999.9996 | 1203999.9996 | -612917.2346 | -1239999.9996 | -1276999.9992 | -1314999.9996 | -612917.2346 | -50.91% | -100% | -100% | -100% | -50.91% | This workpaper is for Executive Offices and officer salaries are excluded and the expense are other related expenses for these Officer organizations with no one single unit of measure. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | PEOPLE AND CULTURE DEPARTMENT | EXECUTIVE OFFICES | Incident Involving an Employee | Utilizing OSHA and Industry Best Practices and Industry Benchmarking | N/A | No | On-going | Annual | 1050689 | 0 | 0 | 0 | 1050689 | 0 | 0 | 0 | 0 | 0 | 1050689 | 0 | 0 | 0 | 1050689 | 100% | 0% | 0% | 0% | 100% | Memberships | 2 |  |  |  | 2 | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | YES | NO | YES | N/A | Membership dues for Edison Electric Institute (EEI) and American Gas Association (AGA) are included in 2024 actuals even though the costs were denied in the final 2024 GRC decision. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | The Chief Executive Officer (CEO) and President & CFO provide executive leadership guidance, and strategic direction of the Company’s mission, vision, and values. The CEO and President & CFO are responsible and accountable for SDG&E’s overall performance. The Executive Offices executes the direction utility employees follow in providing safe and reliable service to customers. The CEO is the highest-ranking officer at SDG&E. Reporting directly to the CEO are the President & CFO, SVP & General Counsel, SVP of Customer Service & External Affairs, VP of People & Culture, VP of Electric Operations. The President & CFO directs the activities of the organization in accordance with policies, goals, and objectives established by the CEO. Reporting directly to the President & CFO are the SVP, CIO & Chief Digital Officer, SVP – State Government Affairs & CRO, VP – Operations Support, VP – Energy Innovation, VP – Controller & Chief Accounting Officer, VP – Energy Procurement & Sustainability. | SDG&E-32-2E AGT-31 to AGT-34 WP 1HR008.000
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal EXECUTIVE OFFICES |  |  |  | Yes |  |  | 1641771.765 | 0 | 0 | 0 | 1641771.765 | 1203999.9996 | 1239999.9996 | 1276999.9992 | 1314999.9996 | 1203999.9996 | 437771.7654 | -1239999.9996 | -1276999.9992 | -1314999.9996 | 437771.7654 | 36.36% | -100% | -100% | -100% | 36.36% | [21 empty] | YES | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | HUMAN RESOURCES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2730243.4355 | 0 | 0 | 0 | 2730243.4355 | 2829999.9996 | 2914999.9992 | 3001999.9992 | 3091999.9992 | 2829999.9996 | -99756.5641 | -2914999.9992 | -3001999.9992 | -3091999.9992 | -99756.5641 | -3.525% | -100% | -100% | -100% | -3.525% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal HUMAN RESOURCES |  |  |  | Yes |  |  | 2730243.4355 | 0 | 0 | 0 | 2730243.4355 | 2829999.9996 | 2914999.9992 | 3001999.9992 | 3091999.9992 | 2829999.9996 | -99756.5641 | -2914999.9992 | -3001999.9992 | -3091999.9992 | -99756.5641 | -3.525% | -100% | -100% | -100% | -3.525% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | LONG-TERM DISABILITY (LTD) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3895334.0001 | 0 | 0 | 0 | 3895334.0001 | 2490999.9996 | 2565999.9996 | 2643000 | 2721999.9996 | 2490999.9996 | 1404334.0005 | -2565999.9996 | -2643000 | -2721999.9996 | 1404334.0005 | 56.38% | -100% | -100% | -100% | 56.38% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal LONG-TERM DISABILITY (LTD) |  |  |  | Yes |  |  | 3895334.0001 | 0 | 0 | 0 | 3895334.0001 | 2490999.9996 | 2565999.9996 | 2643000 | 2721999.9996 | 2490999.9996 | 1404334.0005 | -2565999.9996 | -2643000 | -2721999.9996 | 1404334.0005 | 56.38% | -100% | -100% | -100% | 56.38% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | ORGANIZATIONAL EFFECTIVENESS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1759980.5616 | 0 | 0 | 0 | 1759980.5616 | 2052999.9996 | 2115000 | 2178000 | 2242999.9992 | 2052999.9996 | -293019.438 | -2115000 | -2178000 | -2242999.9992 | -293019.438 | -14.27% | -100% | -100% | -100% | -14.27% | FTE | 11.3 |  |  |  | 11.3 | 12.75 |  |  |  | 12.75 | -1.45 | 0 | 0 | 0 | -1.45 | -0.11373 | 0 | 0 | 0 | -0.11373 | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal ORGANIZATIONAL EFFECTIVENESS |  |  |  | Yes |  |  | 1759980.5616 | 0 | 0 | 0 | 1759980.5616 | 2052999.9996 | 2115000 | 2178000 | 2242999.9992 | 2052999.9996 | -293019.438 | -2115000 | -2178000 | -2242999.9992 | -293019.438 | -14.27% | -100% | -100% | -100% | -14.27% | [21 empty] | YES | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | PEOPLE RESEARCH | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 193952.0974 | 0 | 0 | 0 | 193952.0974 | 0 | 0 | 0 | 0 | 0 | 193952.0974 | 0 | 0 | 0 | 193952.0974 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal PEOPLE RESEARCH |  |  |  | Yes |  |  | 193952.0974 | 0 | 0 | 0 | 193952.0974 | 0 | 0 | 0 | 0 | 0 | 193952.0974 | 0 | 0 | 0 | 193952.0974 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | TOTAL DISABILITY | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 286948.45 | 0 | 0 | 0 | 286948.45 | 325999.9992 | 336000 | 345999.9996 | 355999.9992 | 325999.9992 | -39051.5492 | -336000 | -345999.9996 | -355999.9992 | -39051.5492 | -11.98% | -100% | -100% | -100% | -11.98% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal TOTAL DISABILITY |  |  |  | Yes |  |  | 286948.45 | 0 | 0 | 0 | 286948.45 | 325999.9992 | 336000 | 345999.9996 | 355999.9992 | 325999.9992 | -39051.5492 | -336000 | -345999.9996 | -355999.9992 | -39051.5492 | -11.98% | -100% | -100% | -100% | -11.98% | [21 empty] | NO | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | VP - PEOPLE AND CULTURE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 351576.2059 | 0 | 0 | 0 | 351576.2059 | 0 | 0 | 0 | 0 | 0 | 351576.2059 | 0 | 0 | 0 | 351576.2059 | 100% | 0% | 0% | 0% | 100% | The VP of People & Culture's officer salary is excluded and the other expenses are related to expenses for the People & Culture organizaion. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | Workpaper 1HR000 was denied in the final GRC Decision; however an Advice Letter 4628-E-A / 3410-G-A (Cost Recovery Supplemental) has been filed to seek recovery. | The VP – People and Culture provides leadership and strategic direction to an organization of approximately 70 employees, as well as ensures employees have the qualifications, experience, and skillset to perform their work. The VP - People and Culture is also responsible for implementing policies, programs, and activities aimed at attracting and retaining a qualified skilled workforce that is invested in the Company's goals and serving the community. | SDG&E-32-2E AGT-11 to AGT-12 WP 1HR000.000
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal VP - PEOPLE AND CULTURE |  |  |  | Yes |  |  | 351576.2059 | 0 | 0 | 0 | 351576.2059 | 0 | 0 | 0 | 0 | 0 | 351576.2059 | 0 | 0 | 0 | 351576.2059 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | WELLNESS PROGRAMS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3.5257 | 0 | 0 | 0 | 3.5257 | 24000 | 24999.9996 | 25999.9992 | 27000 | 24000 | -23996.4743 | -24999.9996 | -25999.9992 | -27000 | -23996.4743 | -99.99% | -100% | -100% | -100% | -99.99% | This activity includes costs related to miscellaneous Wellness Programs expenses. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | SDG&E understands that this component of the Wellness Programs Framework should have been coupled with the broader Wellness Programs Framework below. SDG&E does not anticipate having a non-RAMP component of its Wellenss Programs Framework in this General Rate Case cycle. | Wellness Programs is responsible for managing and administering the Company 's Employee Assistance Program (EAP), as well as assisting with sensitive HR-related issues associated with possible substance abuse or threats of workplace violence. | SDG&E-32-2E AGT-38 to AGT-40 WP 2100-3506.000
O&M | PEOPLE AND CULTURE DEPARTMENT | WELLNESS PROGRAMS | Incident Involving an Employee | Employee Wellness Programs | Overall | No | On-going | Annual | 128249.1025 | 0 | 0 | 0 | 128249.1025 | 195000 | 201000 | 207000 | 213000 | 195000 | -66750.8975 | -201000 | -207000 | -213000 | -66750.8975 | -34.23% | -100% | -100% | -100% | -34.23% | FTE | 1 |  |  |  | 1 | 2.1 |  |  |  | 2.1 | -1.1 | 0 | 0 | 0 | -1.1 | -0.52381 | 0 | 0 | 0 | -0.52381 | YES | NO | YES | N/A | The incremental Wellness Programs Coordinator was not hired in 2024. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Wellness Programs is responsible for managing and administering the Company 's Employee Assistance Program (EAP), as well as assisting with sensitive HR-related issues associated with possible substance abuse or threats of workplace violence. | SDG&E-32-2E AGT-38 to AGT-40 WP 2100-3506.000
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal WELLNESS PROGRAMS |  |  |  | Yes |  |  | 128252.6282 | 0 | 0 | 0 | 128252.6282 | 219000 | 225999.9996 | 232999.9992 | 240000 | 219000 | -90747.3718 | -225999.9996 | -232999.9992 | -240000 | -90747.3718 | -41.44% | -100% | -100% | -100% | -41.44% | [21 empty] | YES | NO | [7 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | WORKERS' COMPENSATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3366253.67 | 0 | 0 | 0 | 3366253.67 | 3828000 | 3942999.9996 | 4060999.9992 | 4182999.9996 | 3828000 | -461746.33 | -3942999.9996 | -4060999.9992 | -4182999.9996 | -461746.33 | -12.06% | -100% | -100% | -100% | -12.06% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | NO | NO | [6 empty] | NO
O&M | PEOPLE AND CULTURE DEPARTMENT | SubTotal WORKERS' COMPENSATION |  |  |  | Yes |  |  | 3366253.67 | 0 | 0 | 0 | 3366253.67 | 3828000 | 3942999.9996 | 4060999.9992 | 4182999.9996 | 3828000 | -461746.33 | -3942999.9996 | -4060999.9992 | -4182999.9996 | -461746.33 | -12.06% | -100% | -100% | -100% | -12.06% | [21 empty] | NO | NO | [7 empty] | NO

## AGAG
SDG&E ADMINISTRATIVE & GENERAL O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | ADMINISTRATIVE & GENERAL | ADMINISTRATIVE & GENERAL |  |  |  | Yes |  |  | 43165933.6107 | 0 | 0 | 0 | 43165933.6107 | 47064999.99 | 48478999.9896 | 49933999.9896 | 51430999.9896 | 47064999.99 | -3899066.3793 | -48478999.9896 | -49933999.9896 | -51430999.9896 | -3899066.3793 | -8.284% | -100% | -100% | -100% | -8.284%
O&M | ADMINISTRATIVE & GENERAL | ACCOUNTING RESEARCH & BUSINESS CONTROLS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 389792.3998 | 0 | 0 | 0 | 389792.3998 | 454999.9992 | 468999.9996 | 483000 | 496999.9992 | 454999.9992 | -65207.5994 | -468999.9996 | -483000 | -496999.9992 | -65207.5994 | -14.33% | -100% | -100% | -100% | -14.33% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal ACCOUNTING RESEARCH & BUSINESS CONTROLS |  |  |  | Yes |  |  | 389792.3998 | 0 | 0 | 0 | 389792.3998 | 454999.9992 | 468999.9996 | 483000 | 496999.9992 | 454999.9992 | -65207.5994 | -468999.9996 | -483000 | -496999.9992 | -65207.5994 | -14.33% | -100% | -100% | -100% | -14.33% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | ACCOUNTS PAYABLE (AP) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1102762.3931 | 0 | 0 | 0 | 1102762.3931 | 1119999.9996 | 1153999.9992 | 1188999.9996 | 1224999.9996 | 1119999.9996 | -17237.6065 | -1153999.9992 | -1188999.9996 | -1224999.9996 | -17237.6065 | -1.539% | -100% | -100% | -100% | -1.539% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal ACCOUNTS PAYABLE (AP) |  |  |  | Yes |  |  | 1102762.3931 | 0 | 0 | 0 | 1102762.3931 | 1119999.9996 | 1153999.9992 | 1188999.9996 | 1224999.9996 | 1119999.9996 | -17237.6065 | -1153999.9992 | -1188999.9996 | -1224999.9996 | -17237.6065 | -1.539% | -100% | -100% | -100% | -1.539% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | AFFILIATE BILLING & COSTING (ABC) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 383337.3989 | 0 | 0 | 0 | 383337.3989 | 444000 | 456999.9996 | 471000 | 484999.9992 | 444000 | -60662.6011 | -456999.9996 | -471000 | -484999.9992 | -60662.6011 | -13.66% | -100% | -100% | -100% | -13.66% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal AFFILIATE BILLING & COSTING (ABC) |  |  |  | Yes |  |  | 383337.3989 | 0 | 0 | 0 | 383337.3989 | 444000 | 456999.9996 | 471000 | 484999.9992 | 444000 | -60662.6011 | -456999.9996 | -471000 | -484999.9992 | -60662.6011 | -13.66% | -100% | -100% | -100% | -13.66% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | ASSET & PROJECT ACCOUNTING (A&PA) - PLANT ACCOUNTING AND FINANCIAL & RATEBASE SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2664743.8427 | 0 | 0 | 0 | 2664743.8427 | 2766999.9996 | 2850000 | 2935999.9992 | 3024000 | 2766999.9996 | -102256.1569 | -2850000 | -2935999.9992 | -3024000 | -102256.1569 | -3.696% | -100% | -100% | -100% | -3.696% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal ASSET & PROJECT ACCOUNTING (A&PA) - PLANT ACCOUNTING AND FINANCIAL & RATEBASE SERVICES |  |  |  | Yes |  |  | 2664743.8427 | 0 | 0 | 0 | 2664743.8427 | 2766999.9996 | 2850000 | 2935999.9992 | 3024000 | 2766999.9996 | -102256.1569 | -2850000 | -2935999.9992 | -3024000 | -102256.1569 | -3.696% | -100% | -100% | -100% | -3.696% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | ASSISTANT CONTROLLER | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 347529.9759 | 0 | 0 | 0 | 347529.9759 | 357999.9996 | 369000 | 379999.9992 | 390999.9996 | 357999.9996 | -10470.0237 | -369000 | -379999.9992 | -390999.9996 | -10470.0237 | -2.925% | -100% | -100% | -100% | -2.925% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal ASSISTANT CONTROLLER |  |  |  | Yes |  |  | 347529.9759 | 0 | 0 | 0 | 347529.9759 | 357999.9996 | 369000 | 379999.9992 | 390999.9996 | 357999.9996 | -10470.0237 | -369000 | -379999.9992 | -390999.9996 | -10470.0237 | -2.925% | -100% | -100% | -100% | -2.925% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | BILLABLE PROJECT ACCOUNTING & SUNDRY SERVICES (BPA & SS) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 792830.5769 | 0 | 0 | 0 | 792830.5769 | 969000 | 997999.9992 | 1027999.9992 | 1059000 | 969000 | -176169.4231 | -997999.9992 | -1027999.9992 | -1059000 | -176169.4231 | -18.18% | -100% | -100% | -100% | -18.18% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal BILLABLE PROJECT ACCOUNTING & SUNDRY SERVICES (BPA & SS) |  |  |  | Yes |  |  | 792830.5769 | 0 | 0 | 0 | 792830.5769 | 969000 | 997999.9992 | 1027999.9992 | 1059000 | 969000 | -176169.4231 | -997999.9992 | -1027999.9992 | -1059000 | -176169.4231 | -18.18% | -100% | -100% | -100% | -18.18% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | BUSINESS INNOVATIONS AND FINANCIAL SYSTEMS CLIENT SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 903664.2258 | 0 | 0 | 0 | 903664.2258 | 816000 | 840000 | 864999.9996 | 891000 | 816000 | 87664.2258 | -840000 | -864999.9996 | -891000 | 87664.2258 | 10.74% | -100% | -100% | -100% | 10.74% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal BUSINESS INNOVATIONS AND FINANCIAL SYSTEMS CLIENT SUPPORT |  |  |  | Yes |  |  | 903664.2258 | 0 | 0 | 0 | 903664.2258 | 816000 | 840000 | 864999.9996 | 891000 | 816000 | 87664.2258 | -840000 | -864999.9996 | -891000 | 87664.2258 | 10.74% | -100% | -100% | -100% | 10.74% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | CLAIMS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1479845.1032 | 0 | 0 | 0 | 1479845.1032 | 1419999.9996 | 1462999.9992 | 1506999.9996 | 1551999.9996 | 1419999.9996 | 59845.1036 | -1462999.9992 | -1506999.9996 | -1551999.9996 | 59845.1036 | 4.214% | -100% | -100% | -100% | 4.214% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal CLAIMS |  |  |  | Yes |  |  | 1479845.1032 | 0 | 0 | 0 | 1479845.1032 | 1419999.9996 | 1462999.9992 | 1506999.9996 | 1551999.9996 | 1419999.9996 | 59845.1036 | -1462999.9992 | -1506999.9996 | -1551999.9996 | 59845.1036 | 4.214% | -100% | -100% | -100% | 4.214% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | CLAIMS PAYMENTS AND RECOVERY COSTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3148834.0001 | 0 | 0 | 0 | 3148834.0001 | 4221999.9996 | 4348999.9992 | 4479000 | 4612999.9992 | 4221999.9996 | -1073165.9995 | -4348999.9992 | -4479000 | -4612999.9992 | -1073165.9995 | -25.42% | -100% | -100% | -100% | -25.42% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal CLAIMS PAYMENTS AND RECOVERY COSTS |  |  |  | Yes |  |  | 3148834.0001 | 0 | 0 | 0 | 3148834.0001 | 4221999.9996 | 4348999.9992 | 4479000 | 4612999.9992 | 4221999.9996 | -1073165.9995 | -4348999.9992 | -4479000 | -4612999.9992 | -1073165.9995 | -25.42% | -100% | -100% | -100% | -25.42% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | COMMUNITY RELATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1137814.0428 | 0 | 0 | 0 | 1137814.0428 | 1255999.9992 | 1293999.9996 | 1332999.9996 | 1372999.9992 | 1255999.9992 | -118185.9564 | -1293999.9996 | -1332999.9996 | -1372999.9992 | -118185.9564 | -9.41% | -100% | -100% | -100% | -9.41% | FTE | 8.33 |  |  |  | 8.33 | 9.4 |  |  |  | 9.4 | -1.07 | 0 | 0 | 0 | -1.07 | -11.38% | 0% | 0% | 0% | -11.38% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ADMINISTRATIVE & GENERAL | SubTotal COMMUNITY RELATIONS |  |  |  | Yes |  |  | 1137814.0428 | 0 | 0 | 0 | 1137814.0428 | 1255999.9992 | 1293999.9996 | 1332999.9996 | 1372999.9992 | 1255999.9992 | -118185.9564 | -1293999.9996 | -1332999.9996 | -1372999.9992 | -118185.9564 | -9.41% | -100% | -100% | -100% | -9.41% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | FINANCIAL & BUSINESS PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 6431010.1368 | 0 | 0 | 0 | 6431010.1368 | 7185999.9996 | 7401999.9996 | 7623999.9996 | 7852999.9992 | 7185999.9996 | -754989.8628 | -7401999.9996 | -7623999.9996 | -7852999.9992 | -754989.8628 | -10.51% | -100% | -100% | -100% | -10.51% | FTE | 48.63 |  |  |  | 48.63 | 55 |  |  |  | 55 | -6.37 | 0 | 0 | 0 | -6.37 | -11.58% | 0% | 0% | 0% | -11.58% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | ADMINISTRATIVE & GENERAL | SubTotal FINANCIAL & BUSINESS PLANNING |  |  |  | Yes |  |  | 6431010.1368 | 0 | 0 | 0 | 6431010.1368 | 7185999.9996 | 7401999.9996 | 7623999.9996 | 7852999.9992 | 7185999.9996 | -754989.8628 | -7401999.9996 | -7623999.9996 | -7852999.9992 | -754989.8628 | -10.51% | -100% | -100% | -100% | -10.51% | [21 empty] | YES | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | FINANCIAL ACCOUNTING | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1098011.1644 | 0 | 0 | 0 | 1098011.1644 | 1074999.9996 | 1107000 | 1140000 | 1173999.9996 | 1074999.9996 | 23011.1648 | -1107000 | -1140000 | -1173999.9996 | 23011.1648 | 2.141% | -100% | -100% | -100% | 2.141% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal FINANCIAL ACCOUNTING |  |  |  | Yes |  |  | 1098011.1644 | 0 | 0 | 0 | 1098011.1644 | 1074999.9996 | 1107000 | 1140000 | 1173999.9996 | 1074999.9996 | 23011.1648 | -1107000 | -1140000 | -1173999.9996 | 23011.1648 | 2.141% | -100% | -100% | -100% | 2.141% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | FINANCIAL PLANNING SYSTEMS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 934715.9485 | 0 | 0 | 0 | 934715.9485 | 883999.9992 | 910999.9992 | 937999.9992 | 966000 | 883999.9992 | 50715.9493 | -910999.9992 | -937999.9992 | -966000 | 50715.9493 | 5.737% | -100% | -100% | -100% | 5.737% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal FINANCIAL PLANNING SYSTEMS |  |  |  | Yes |  |  | 934715.9485 | 0 | 0 | 0 | 934715.9485 | 883999.9992 | 910999.9992 | 937999.9992 | 966000 | 883999.9992 | 50715.9493 | -910999.9992 | -937999.9992 | -966000 | 50715.9493 | 5.737% | -100% | -100% | -100% | 5.737% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | GENERAL COUNSEL | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 11824991.4905 | 0 | 0 | 0 | 11824991.4905 | 11889000 | 12246000 | 12612999.9996 | 12990999.9996 | 11889000 | -64008.5095 | -12246000 | -12612999.9996 | -12990999.9996 | -64008.5095 | -0.5384% | -100% | -100% | -100% | -0.5384% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal GENERAL COUNSEL |  |  |  | Yes |  |  | 11824991.4905 | 0 | 0 | 0 | 11824991.4905 | 11889000 | 12246000 | 12612999.9996 | 12990999.9996 | 11889000 | -64008.5095 | -12246000 | -12612999.9996 | -12990999.9996 | -64008.5095 | -0.5384% | -100% | -100% | -100% | -0.5384% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | GRC & REVENUE REQUIREMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 589103.3048 | 0 | 0 | 0 | 589103.3048 | 819999.9996 | 844999.9992 | 870000 | 895999.9992 | 819999.9996 | -230896.6948 | -844999.9992 | -870000 | -895999.9992 | -230896.6948 | -28.16% | -100% | -100% | -100% | -28.16% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal GRC & REVENUE REQUIREMENTS |  |  |  | Yes |  |  | 589103.3048 | 0 | 0 | 0 | 589103.3048 | 819999.9996 | 844999.9992 | 870000 | 895999.9992 | 819999.9996 | -230896.6948 | -844999.9992 | -870000 | -895999.9992 | -230896.6948 | -28.16% | -100% | -100% | -100% | -28.16% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | GRC & REVENUE REQUIREMENTS - GRC ACCOUNTABILITY REPORTING | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 504896.2402 | 0 | 0 | 0 | 504896.2402 | 315000 | 324000 | 333999.9996 | 343999.9992 | 315000 | 189896.2402 | -324000 | -333999.9996 | -343999.9992 | 189896.2402 | 60.28% | -100% | -100% | -100% | 60.28% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal GRC & REVENUE REQUIREMENTS - GRC ACCOUNTABILITY REPORTING |  |  |  | Yes |  |  | 504896.2402 | 0 | 0 | 0 | 504896.2402 | 315000 | 324000 | 333999.9996 | 343999.9992 | 315000 | 189896.2402 | -324000 | -333999.9996 | -343999.9992 | 189896.2402 | 60.28% | -100% | -100% | -100% | 60.28% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | GRC & REVENUE REQUIREMENTS - GRC CASE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 760635.8849 | 0 | 0 | 0 | 760635.8849 | 829999.9992 | 855000 | 880999.9992 | 906999.9996 | 829999.9992 | -69364.1142 | -855000 | -880999.9992 | -906999.9996 | -69364.1142 | -8.357% | -100% | -100% | -100% | -8.357% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal GRC & REVENUE REQUIREMENTS - GRC CASE MANAGEMENT |  |  |  | Yes |  |  | 760635.8849 | 0 | 0 | 0 | 760635.8849 | 829999.9992 | 855000 | 880999.9992 | 906999.9996 | 829999.9992 | -69364.1142 | -855000 | -880999.9992 | -906999.9996 | -69364.1142 | -8.357% | -100% | -100% | -100% | -8.357% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | POLICY & PROCEEDINGS - CASE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3118164.6895 | 0 | 0 | 0 | 3118164.6895 | 3756000 | 3868999.9992 | 3984999.9996 | 4104999.9996 | 3756000 | -637835.3105 | -3868999.9992 | -3984999.9996 | -4104999.9996 | -637835.3105 | -16.98% | -100% | -100% | -100% | -16.98% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal POLICY & PROCEEDINGS - CASE MANAGEMENT |  |  |  | Yes |  |  | 3118164.6895 | 0 | 0 | 0 | 3118164.6895 | 3756000 | 3868999.9992 | 3984999.9996 | 4104999.9996 | 3756000 | -637835.3105 | -3868999.9992 | -3984999.9996 | -4104999.9996 | -637835.3105 | -16.98% | -100% | -100% | -100% | -16.98% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | POLICY & PROCEEDINGS - TARIFFS AND COMPLIANCE AND STRATEGIC PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1269932.2462 | 0 | 0 | 0 | 1269932.2462 | 2155999.9992 | 2220999.9996 | 2287999.9992 | 2356999.9992 | 2155999.9992 | -886067.753 | -2220999.9996 | -2287999.9992 | -2356999.9992 | -886067.753 | -41.1% | -100% | -100% | -100% | -41.1% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal POLICY & PROCEEDINGS - TARIFFS AND COMPLIANCE AND STRATEGIC PLANNING |  |  |  | Yes |  |  | 1269932.2462 | 0 | 0 | 0 | 1269932.2462 | 2155999.9992 | 2220999.9996 | 2287999.9992 | 2356999.9992 | 2155999.9992 | -886067.753 | -2220999.9996 | -2287999.9992 | -2356999.9992 | -886067.753 | -41.1% | -100% | -100% | -100% | -41.1% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | REGULATORY POLICY & LEGISLATIVE ANALYSIS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 108419.6304 | 0 | 0 | 0 | 108419.6304 | 261000 | 268999.9992 | 276999.9996 | 285000 | 261000 | -152580.3697 | -268999.9992 | -276999.9996 | -285000 | -152580.3697 | -58.46% | -100% | -100% | -100% | -58.46% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal REGULATORY POLICY & LEGISLATIVE ANALYSIS |  |  |  | Yes |  |  | 108419.6304 | 0 | 0 | 0 | 108419.6304 | 261000 | 268999.9992 | 276999.9996 | 285000 | 261000 | -152580.3697 | -268999.9992 | -276999.9996 | -285000 | -152580.3697 | -58.46% | -100% | -100% | -100% | -58.46% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | REGULATORY REPORTING AND REGULATORY ACCOUNTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1352787.1185 | 0 | 0 | 0 | 1352787.1185 | 1773999.9996 | 1827000 | 1881999.9996 | 1938000 | 1773999.9996 | -421212.8811 | -1827000 | -1881999.9996 | -1938000 | -421212.8811 | -23.74% | -100% | -100% | -100% | -23.74% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal REGULATORY REPORTING AND REGULATORY ACCOUNTS |  |  |  | Yes |  |  | 1352787.1185 | 0 | 0 | 0 | 1352787.1185 | 1773999.9996 | 1827000 | 1881999.9996 | 1938000 | 1773999.9996 | -421212.8811 | -1827000 | -1881999.9996 | -1938000 | -421212.8811 | -23.74% | -100% | -100% | -100% | -23.74% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SAN FRANCISCO OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 830514.9733 | 0 | 0 | 0 | 830514.9733 | 898999.9992 | 925999.9992 | 954000 | 982999.9992 | 898999.9992 | -68485.0259 | -925999.9992 | -954000 | -982999.9992 | -68485.0259 | -7.618% | -100% | -100% | -100% | -7.618% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal SAN FRANCISCO OPERATIONS |  |  |  | Yes |  |  | 830514.9733 | 0 | 0 | 0 | 830514.9733 | 898999.9992 | 925999.9992 | 954000 | 982999.9992 | 898999.9992 | -68485.0259 | -925999.9992 | -954000 | -982999.9992 | -68485.0259 | -7.618% | -100% | -100% | -100% | -7.618% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SVP - STATE GOVERNMENT AFFAIRS & CRO | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 927486.9277 | 0 | 0 | 0 | 927486.9277 | 582000 | 598999.9992 | 616999.9992 | 636000 | 582000 | 345486.9277 | -598999.9992 | -616999.9992 | -636000 | 345486.9277 | 59.36% | -100% | -100% | -100% | 59.36% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal SVP - STATE GOVERNMENT AFFAIRS & CRO |  |  |  | Yes |  |  | 927486.9277 | 0 | 0 | 0 | 927486.9277 | 582000 | 598999.9992 | 616999.9992 | 636000 | 582000 | 345486.9277 | -598999.9992 | -616999.9992 | -636000 | 345486.9277 | 59.36% | -100% | -100% | -100% | 59.36% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | VP - CONTROLLER & CAO | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1063431.2957 | 0 | 0 | 0 | 1063431.2957 | 475999.9992 | 489999.9996 | 504999.9996 | 519999.9996 | 475999.9992 | 587431.2965 | -489999.9996 | -504999.9996 | -519999.9996 | 587431.2965 | 123.4% | -100% | -100% | -100% | 123.4% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | SubTotal VP - CONTROLLER & CAO |  |  |  | Yes |  |  | 1063431.2957 | 0 | 0 | 0 | 1063431.2957 | 475999.9992 | 489999.9996 | 504999.9996 | 519999.9996 | 475999.9992 | 587431.2965 | -489999.9996 | -504999.9996 | -519999.9996 | 587431.2965 | 123.4% | -100% | -100% | -100% | 123.4% | [21 empty] | NO | NO | [7 empty] | NO
O&M | ADMINISTRATIVE & GENERAL | COMMUNITY RELATIONS NSS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 678.6 | 0 | 0 | 0 | 678.6 | 334999.9992 | 345000 | 354999.9996 | 366000 | 334999.9992 | -334321.3992 | -345000 | -354999.9996 | -366000 | -334321.3992 | -99.8% | -100% | -100% | -100% | -99.8% | FTE | 0 |  |  |  | 0 | 0.6 |  |  |  | 0.6 | -0.6 | 0 | 0 | 0 | -0.6 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Variance is due to internal reorganization that redesigned roles and responsibilities and created different VP roles, FTE position and all costs were spread across the redesigned organizations. | Under (U) | Under (U) | Under (U) | Other | YES | Variance is due to internal reorganization that redesigned roles and responsibilities and created different VP roles, FTE (Full-Time Equivalent) position and all costs were spread across the redesigned organizations. | The Community Relations department is the primary liaison between SDG&E and nonprofit community-based organizations (CBOs), and local communities. The Community Relations department develops relationships with these groups to facilitate the promotion of SDG&E’s customer programs and services. The Community Relations department engages these organizations in Company programs, providing charitable support, and linking them with energy efficiency products and programs to save energy and money. In preparation of this testimony, the Company has removed costs for political, civic, and related activities, and other nonallowable expenses. | SDG&E-33-R-E RA-47 to RA-50 WP 1AG012.000
O&M | ADMINISTRATIVE & GENERAL | SubTotal COMMUNITY RELATIONS NSS |  |  |  | Yes |  |  | 678.6 | 0 | 0 | 0 | 678.6 | 334999.9992 | 345000 | 354999.9996 | 366000 | 334999.9992 | -334321.3992 | -345000 | -354999.9996 | -366000 | -334321.3992 | -99.8% | -100% | -100% | -100% | -99.8% | [21 empty] | YES | NO | [7 empty] | YES

## SEAG
SDG&E CORPORATE CENTER - GENERAL ADMINISTRATION O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | CORPORATE CENTER - GENERAL ADMINISTRATION |  |  |  | Yes |  |  | 64506504.8292 | 0 | 0 | 0 | 64506504.8292 | 58059999.9984 | 59801999.9988 | 61595999.9988 | 63444000 | 58059999.9984 | 6446504.8308 | -59801999.9988 | -61595999.9988 | -63444000 | 6446504.8308 | 11.1% | -100% | -100% | -100% | 11.1%
O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SECC DERPRECIATION ROR - F923.4 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2148189.9 | 0 | 0 | 0 | 2148189.9 | 1767999.9996 | 1821000 | 1875999.9996 | 1932000 | 1767999.9996 | 380189.9004 | -1821000 | -1875999.9996 | -1932000 | 380189.9004 | 21.5% | -100% | -100% | -100% | 21.5% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SubTotal SECC DERPRECIATION ROR - F923.4 |  |  |  | Yes |  |  | 2148189.9 | 0 | 0 | 0 | 2148189.9 | 1767999.9996 | 1821000 | 1875999.9996 | 1932000 | 1767999.9996 | 380189.9004 | -1821000 | -1875999.9996 | -1932000 | 380189.9004 | 21.5% | -100% | -100% | -100% | 21.5% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SECC OUTSIDE SERVICES EMPLOYED - F923.1 | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 61691295.5292 | 0 | 0 | 0 | 61691295.5292 | 55797999.9996 | 57471999.9996 | 59196000 | 60972000 | 55797999.9996 | 5893295.5296 | -57471999.9996 | -59196000 | -60972000 | 5893295.5296 | 10.56% | -100% | -100% | -100% | 10.56% | The costs include allocations from the following Sempra Energy Corporate Center (SECC) functions: finance including cash/bank fees, human resources, legal and outside legal counsel, external affairs, facilities, and employee benefits. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The variance in 2024 actuals is due to spending more than authorized costs allocated to SDG&E by Corporate Center for deparment costs, outside services, and incentive compensation. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Corporate Center allocated costs include supporting services such as accounting, treasury, audit services, human resources, and legal affairs that Corporate Center has provided to SDG&E. Without Corporate Center provided services and allocated costs, additional staffing and operations and maintenance expenses would be required at SDG&E. | SDG&E-27-R-E DRC-5 to DRC-74 WP 1SE000.001
O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SECC OUTSIDE SERVICES EMPLOYED - F923.1 | Physical Security | Planning, Awareness, Risk Management, and Incident Management | Planning, Awareness, Risk Management, and Incident Management | No | On-going | Annual | 667019.4 | 0 | 0 | 0 | 667019.4 | 493999.9992 | 508999.9992 | 523999.9992 | 540000 | 493999.9992 | 173019.4008 | -508999.9992 | -523999.9992 | -540000 | 173019.4008 | 35.02% | -100% | -100% | -100% | 35.02% | The costs include allocations related to security systems, use of applications, and training to enhance the safety of employees, contractors, vendors, SDG&E facilities and infrastructure, and the public. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Corporate Center allocated costs include computer hardware/software and employee training to support SDG&E in maintaining its strong physical security program and responding to security incidents. Without Corporate Center provided services and allocated costs, additional staffing and operations and maintenance expenses would be required at SDG&E. | SDG&E-27-R-E DRC-3 to DRC-5 WP 1SE000.001
O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SubTotal SECC OUTSIDE SERVICES EMPLOYED - F923.1 |  |  |  | Yes |  |  | 62358314.9292 | 0 | 0 | 0 | 62358314.9292 | 56291999.9988 | 57980999.9988 | 59719999.9992 | 61512000 | 56291999.9988 | 6066314.9304 | -57980999.9988 | -59719999.9992 | -61512000 | 6066314.9304 | 10.78% | -100% | -100% | -100% | 10.78% | [21 empty] | YES | YES | [7 empty] | NO

## SEIN
SDG&E CORPORATE CENTER - INSURANCE O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CORPORATE CENTER - INSURANCE | CORPORATE CENTER - INSURANCE |  |  |  | Yes |  |  | 12621352.3884 | 0 | 0 | 0 | 12621352.3884 | 16980999.9984 | 17489999.9976 | 18013999.998 | 18553999.998 | 16980999.9984 | -4359647.61 | -17489999.9976 | -18013999.998 | -18553999.998 | -4359647.61 | -25.67% | -100% | -100% | -100% | -25.67%
O&M | CORPORATE CENTER - INSURANCE | SECC PROPERTY INSURANCE NON-NUCLEAR - 924.0 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 12525836.3892 | 0 | 0 | 0 | 12525836.3892 | 16860000 | 17365999.9992 | 17886999.9996 | 18423999.9996 | 16860000 | -4334163.6108 | -17365999.9992 | -17886999.9996 | -18423999.9996 | -4334163.6108 | -25.71% | -100% | -100% | -100% | -25.71% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | SubTotal SECC PROPERTY INSURANCE NON-NUCLEAR - 924.0 |  |  |  | Yes |  |  | 12525836.3892 | 0 | 0 | 0 | 12525836.3892 | 16860000 | 17365999.9992 | 17886999.9996 | 18423999.9996 | 16860000 | -4334163.6108 | -17365999.9992 | -17886999.9996 | -18423999.9996 | -4334163.6108 | -25.71% | -100% | -100% | -100% | -25.71% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | SECC PROPERTY INSURANCE NUCLEAR - 924.1 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 0 | 0 | 0 | 0 | 0 | 13999.9992 | 13999.9992 | 13999.9992 | 13999.9992 | 13999.9992 | -13999.9992 | -13999.9992 | -13999.9992 | -13999.9992 | -13999.9992 | -100% | -100% | -100% | -100% | -100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
O&M | CORPORATE CENTER - INSURANCE | SubTotal SECC PROPERTY INSURANCE NUCLEAR - 924.1 |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 13999.9992 | 13999.9992 | 13999.9992 | 13999.9992 | 13999.9992 | -13999.9992 | -13999.9992 | -13999.9992 | -13999.9992 | -13999.9992 | -100% | -100% | -100% | -100% | -100% | [21 empty] | NO | NO | [7 empty] | YES
O&M | CORPORATE CENTER - INSURANCE | SECC SURETY BONDS - F925.6 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 95515.9992 | 0 | 0 | 0 | 95515.9992 | 106999.9992 | 109999.9992 | 112999.9992 | 115999.9992 | 106999.9992 | -11484 | -109999.9992 | -112999.9992 | -115999.9992 | -11484 | -10.73% | -100% | -100% | -100% | -10.73% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | SubTotal SECC SURETY BONDS - F925.6 |  |  |  | Yes |  |  | 95515.9992 | 0 | 0 | 0 | 95515.9992 | 106999.9992 | 109999.9992 | 112999.9992 | 115999.9992 | 106999.9992 | -11484 | -109999.9992 | -112999.9992 | -115999.9992 | -11484 | -10.73% | -100% | -100% | -100% | -10.73% | [21 empty] | NO | NO | [7 empty] | NO

## AGCP
SDG&E CORPORATE CENTER - COMPENSATION & BENEFITS O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | CORPORATE CENTER - COMPENSATION & BENEFITS |  |  |  | Yes |  |  | 202423678.1066 | 0 | 0 | 0 | 202423678.1066 | 127056999.9924 | 130869999.9936 | 134797999.9932 | 138842999.9916 | 127056999.9924 | 75366678.1142 | -130869999.9936 | -134797999.9932 | -138842999.9916 | 75366678.1142 | 59.32% | -100% | -100% | -100% | 59.32%
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | COMPENSATION - SPOT CASH (GRC USE ONLY) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1675912.4202 | 0 | 0 | 0 | 1675912.4202 | 1705999.9992 | 1756999.9992 | 1809999.9996 | 1863999.9996 | 1705999.9992 | -30087.579 | -1756999.9992 | -1809999.9996 | -1863999.9996 | -30087.579 | -1.764% | -100% | -100% | -100% | -1.764% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal COMPENSATION - SPOT CASH (GRC USE ONLY) |  |  |  | Yes |  |  | 1675912.4202 | 0 | 0 | 0 | 1675912.4202 | 1705999.9992 | 1756999.9992 | 1809999.9996 | 1863999.9996 | 1705999.9992 | -30087.579 | -1756999.9992 | -1809999.9996 | -1863999.9996 | -30087.579 | -1.764% | -100% | -100% | -100% | -1.764% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | COMPENSATION - VARIABLE PAY (GRC USE ONLY) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 105030440.807 | 0 | 0 | 0 | 105030440.807 | 34701000 | 35742000 | 36813999.9996 | 37917999.9996 | 34701000 | 70329440.807 | -35742000 | -36813999.9996 | -37917999.9996 | 70329440.807 | 202.7% | -100% | -100% | -100% | 202.7% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal COMPENSATION - VARIABLE PAY (GRC USE ONLY) |  |  |  | Yes |  |  | 105030440.807 | 0 | 0 | 0 | 105030440.807 | 34701000 | 35742000 | 36813999.9996 | 37917999.9996 | 34701000 | 70329440.807 | -35742000 | -36813999.9996 | -37917999.9996 | 70329440.807 | 202.7% | -100% | -100% | -100% | 202.7% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | COMPENSATION-SPECIAL RECOGNITION AWARDS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 505477.94 | 0 | 0 | 0 | 505477.94 | 393999.9996 | 405999.9996 | 417999.9996 | 430999.9992 | 393999.9996 | 111477.9404 | -405999.9996 | -417999.9996 | -430999.9992 | 111477.9404 | 28.29% | -100% | -100% | -100% | 28.29% | [5 empty] | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal COMPENSATION-SPECIAL RECOGNITION AWARDS |  |  |  | Yes |  |  | 505477.94 | 0 | 0 | 0 | 505477.94 | 393999.9996 | 405999.9996 | 417999.9996 | 430999.9992 | 393999.9996 | 111477.9404 | -405999.9996 | -417999.9996 | -430999.9992 | 111477.9404 | 28.29% | -100% | -100% | -100% | 28.29% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS - EMP ASSISTANCE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 732755.35 | 0 | 0 | 0 | 732755.35 | 510000 | 525000 | 540999.9996 | 556999.9992 | 510000 | 222755.35 | -525000 | -540999.9996 | -556999.9992 | 222755.35 | 43.68% | -100% | -100% | -100% | 43.68% | Headcount | 4808 |  |  |  | 4808 | 5388 |  |  |  | 5388 | -580 | 0 | 0 | 0 | -580 | -10.76% | 0% | 0% | 0% | -10.76% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal HEALTH BENEFITS - EMP ASSISTANCE PROGRAM |  |  |  | Yes |  |  | 732755.35 | 0 | 0 | 0 | 732755.35 | 510000 | 525000 | 540999.9996 | 556999.9992 | 510000 | 222755.35 | -525000 | -540999.9996 | -556999.9992 | 222755.35 | 43.68% | -100% | -100% | -100% | 43.68% | [21 empty] | YES | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS - VISION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 264403.58 | 0 | 0 | 0 | 264403.58 | 277999.9992 | 285999.9996 | 294999.9996 | 303999.9996 | 277999.9992 | -13596.4192 | -285999.9996 | -294999.9996 | -303999.9996 | -13596.4192 | -4.891% | -100% | -100% | -100% | -4.891% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal HEALTH BENEFITS - VISION |  |  |  | Yes |  |  | 264403.58 | 0 | 0 | 0 | 264403.58 | 277999.9992 | 285999.9996 | 294999.9996 | 303999.9996 | 277999.9992 | -13596.4192 | -285999.9996 | -294999.9996 | -303999.9996 | -13596.4192 | -4.891% | -100% | -100% | -100% | -4.891% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS-DENTAL | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3360092.85 | 0 | 0 | 0 | 3360092.85 | 3486999.9996 | 3591999.9996 | 3699999.9996 | 3810999.9996 | 3486999.9996 | -126907.1496 | -3591999.9996 | -3699999.9996 | -3810999.9996 | -126907.1496 | -3.639% | -100% | -100% | -100% | -3.639% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal HEALTH BENEFITS-DENTAL |  |  |  | Yes |  |  | 3360092.85 | 0 | 0 | 0 | 3360092.85 | 3486999.9996 | 3591999.9996 | 3699999.9996 | 3810999.9996 | 3486999.9996 | -126907.1496 | -3591999.9996 | -3699999.9996 | -3810999.9996 | -126907.1496 | -3.639% | -100% | -100% | -100% | -3.639% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS-MEDICAL | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 62528018.4795 | 0 | 0 | 0 | 62528018.4795 | 57592999.9992 | 59320999.9992 | 61101000 | 62934000 | 57592999.9992 | 4935018.4803 | -59320999.9992 | -61101000 | -62934000 | 4935018.4803 | 8.569% | -100% | -100% | -100% | 8.569% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal HEALTH BENEFITS-MEDICAL |  |  |  | Yes |  |  | 62528018.4795 | 0 | 0 | 0 | 62528018.4795 | 57592999.9992 | 59320999.9992 | 61101000 | 62934000 | 57592999.9992 | 4935018.4803 | -59320999.9992 | -61101000 | -62934000 | 4935018.4803 | 8.569% | -100% | -100% | -100% | 8.569% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS-WELLNESS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 777612.06 | 0 | 0 | 0 | 777612.06 | 1221000 | 1257999.9996 | 1296000 | 1335000 | 1221000 | -443387.94 | -1257999.9996 | -1296000 | -1335000 | -443387.94 | -36.31% | -100% | -100% | -100% | -36.31% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal HEALTH BENEFITS-WELLNESS |  |  |  | Yes |  |  | 777612.06 | 0 | 0 | 0 | 777612.06 | 1221000 | 1257999.9996 | 1296000 | 1335000 | 1221000 | -443387.94 | -1257999.9996 | -1296000 | -1335000 | -443387.94 | -36.31% | -100% | -100% | -100% | -36.31% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - BENEFIT ADMIN FEES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1038376.2 | 0 | 0 | 0 | 1038376.2 | 1056000 | 1087999.9992 | 1120999.9992 | 1155000 | 1056000 | -17623.8 | -1087999.9992 | -1120999.9992 | -1155000 | -17623.8 | -1.669% | -100% | -100% | -100% | -1.669% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal OTHER BENEFITS - BENEFIT ADMIN FEES |  |  |  | Yes |  |  | 1038376.2 | 0 | 0 | 0 | 1038376.2 | 1056000 | 1087999.9992 | 1120999.9992 | 1155000 | 1056000 | -17623.8 | -1087999.9992 | -1120999.9992 | -1155000 | -17623.8 | -1.669% | -100% | -100% | -100% | -1.669% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - EDUCATIONAL ASSISTANCE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 664381.45 | 0 | 0 | 0 | 664381.45 | 771999.9996 | 795000 | 819000 | 843999.9996 | 771999.9996 | -107618.5496 | -795000 | -819000 | -843999.9996 | -107618.5496 | -13.94% | -100% | -100% | -100% | -13.94% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal OTHER BENEFITS - EDUCATIONAL ASSISTANCE |  |  |  | Yes |  |  | 664381.45 | 0 | 0 | 0 | 664381.45 | 771999.9996 | 795000 | 819000 | 843999.9996 | 771999.9996 | -107618.5496 | -795000 | -819000 | -843999.9996 | -107618.5496 | -13.94% | -100% | -100% | -100% | -13.94% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - EMERGENCY CARE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 154573 | 0 | 0 | 0 | 154573 | 207999.9996 | 213999.9996 | 219999.9996 | 226999.9992 | 207999.9996 | -53426.9996 | -213999.9996 | -219999.9996 | -226999.9992 | -53426.9996 | -25.69% | -100% | -100% | -100% | -25.69% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal OTHER BENEFITS - EMERGENCY CARE |  |  |  | Yes |  |  | 154573 | 0 | 0 | 0 | 154573 | 207999.9996 | 213999.9996 | 219999.9996 | 226999.9992 | 207999.9996 | -53426.9996 | -213999.9996 | -219999.9996 | -226999.9992 | -53426.9996 | -25.69% | -100% | -100% | -100% | -25.69% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - MASS TRANSIT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 24775 | 0 | 0 | 0 | 24775 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 127999.9992 | -103224.9992 | -132000 | -135999.9996 | -139999.9992 | -103224.9992 | -80.64% | -100% | -100% | -100% | -80.64% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal OTHER BENEFITS - MASS TRANSIT |  |  |  | Yes |  |  | 24775 | 0 | 0 | 0 | 24775 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 127999.9992 | -103224.9992 | -132000 | -135999.9996 | -139999.9992 | -103224.9992 | -80.64% | -100% | -100% | -100% | -80.64% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - RETIREMENT ACTIVITIES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 49238.79 | 0 | 0 | 0 | 49238.79 | 87000 | 90000 | 93000 | 96000 | 87000 | -37761.21 | -90000 | -93000 | -96000 | -37761.21 | -43.4% | -100% | -100% | -100% | -43.4% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal OTHER BENEFITS - RETIREMENT ACTIVITIES |  |  |  | Yes |  |  | 49238.79 | 0 | 0 | 0 | 49238.79 | 87000 | 90000 | 93000 | 96000 | 87000 | -37761.21 | -90000 | -93000 | -96000 | -37761.21 | -43.4% | -100% | -100% | -100% | -43.4% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - SERVICE RECOGNITION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 114004.47 | 0 | 0 | 0 | 114004.47 | 133999.9992 | 138000 | 141999.9996 | 145999.9992 | 133999.9992 | -19995.5292 | -138000 | -141999.9996 | -145999.9992 | -19995.5292 | -14.92% | -100% | -100% | -100% | -14.92% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal OTHER BENEFITS - SERVICE RECOGNITION |  |  |  | Yes |  |  | 114004.47 | 0 | 0 | 0 | 114004.47 | 133999.9992 | 138000 | 141999.9996 | 145999.9992 | 133999.9992 | -19995.5292 | -138000 | -141999.9996 | -145999.9992 | -19995.5292 | -14.92% | -100% | -100% | -100% | -14.92% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | RETIREMENT BENEFITS - RETIREMENT SAVINGS PLAN | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 21577904.29 | 0 | 0 | 0 | 21577904.29 | 22953999.9996 | 23643000 | 24351999.9996 | 25083000 | 22953999.9996 | -1376095.7096 | -23643000 | -24351999.9996 | -25083000 | -1376095.7096 | -5.995% | -100% | -100% | -100% | -5.995% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal RETIREMENT BENEFITS - RETIREMENT SAVINGS PLAN |  |  |  | Yes |  |  | 21577904.29 | 0 | 0 | 0 | 21577904.29 | 22953999.9996 | 23643000 | 24351999.9996 | 25083000 | 22953999.9996 | -1376095.7096 | -23643000 | -24351999.9996 | -25083000 | -1376095.7096 | -5.995% | -100% | -100% | -100% | -5.995% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | RETIREMENT BENEFITS - SUPPLEMENTAL PENSION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2964924 | 0 | 0 | 0 | 2964924 | 972999.9996 | 1002000 | 1032000 | 1062999.9996 | 972999.9996 | 1991924.0004 | -1002000 | -1032000 | -1062999.9996 | 1991924.0004 | 204.7% | -100% | -100% | -100% | 204.7% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal RETIREMENT BENEFITS - SUPPLEMENTAL PENSION |  |  |  | Yes |  |  | 2964924 | 0 | 0 | 0 | 2964924 | 972999.9996 | 1002000 | 1032000 | 1062999.9996 | 972999.9996 | 1991924.0004 | -1002000 | -1032000 | -1062999.9996 | 1991924.0004 | 204.7% | -100% | -100% | -100% | 204.7% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | RETIREMENT BENEFITS-NQ SAVINGS PLAN | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 251084 | 0 | 0 | 0 | 251084 | 124999.9992 | 129000 | 132999.9996 | 136999.9992 | 124999.9992 | 126084.0008 | -129000 | -132999.9996 | -136999.9992 | 126084.0008 | 100.9% | -100% | -100% | -100% | 100.9% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal RETIREMENT BENEFITS-NQ SAVINGS PLAN |  |  |  | Yes |  |  | 251084 | 0 | 0 | 0 | 251084 | 124999.9992 | 129000 | 132999.9996 | 136999.9992 | 124999.9992 | 126084.0008 | -129000 | -132999.9996 | -136999.9992 | 126084.0008 | 100.9% | -100% | -100% | -100% | 100.9% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | WELFARE BENEFITS - BUSINESS TRAVEL INS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 47712.99 | 0 | 0 | 0 | 47712.99 | 27000 | 27999.9996 | 28999.9992 | 30000 | 27000 | 20712.99 | -27999.9996 | -28999.9992 | -30000 | 20712.99 | 76.71% | -100% | -100% | -100% | 76.71% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal WELFARE BENEFITS - BUSINESS TRAVEL INS |  |  |  | Yes |  |  | 47712.99 | 0 | 0 | 0 | 47712.99 | 27000 | 27999.9996 | 28999.9992 | 30000 | 27000 | 20712.99 | -27999.9996 | -28999.9992 | -30000 | 20712.99 | 76.71% | -100% | -100% | -100% | 76.71% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | WELFARE BENEFITS-AD&D INSURANCE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 127028.02 | 0 | 0 | 0 | 127028.02 | 135999.9996 | 139999.9992 | 144000 | 147999.9996 | 135999.9996 | -8971.9796 | -139999.9992 | -144000 | -147999.9996 | -8971.9796 | -6.597% | -100% | -100% | -100% | -6.597% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal WELFARE BENEFITS-AD&D INSURANCE |  |  |  | Yes |  |  | 127028.02 | 0 | 0 | 0 | 127028.02 | 135999.9996 | 139999.9992 | 144000 | 147999.9996 | 135999.9996 | -8971.9796 | -139999.9992 | -144000 | -147999.9996 | -8971.9796 | -6.597% | -100% | -100% | -100% | -6.597% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | WELFARE BENEFITS-LIFE INSURANCE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 534962.41 | 0 | 0 | 0 | 534962.41 | 567000 | 583999.9992 | 601999.9992 | 619999.9992 | 567000 | -32037.59 | -583999.9992 | -601999.9992 | -619999.9992 | -32037.59 | -5.65% | -100% | -100% | -100% | -5.65% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | SubTotal WELFARE BENEFITS-LIFE INSURANCE |  |  |  | Yes |  |  | 534962.41 | 0 | 0 | 0 | 534962.41 | 567000 | 583999.9992 | 601999.9992 | 619999.9992 | 567000 | -32037.59 | -583999.9992 | -601999.9992 | -619999.9992 | -32037.59 | -5.65% | -100% | -100% | -100% | -5.65% | [21 empty] | NO | NO | [7 empty] | NO

## GOSM
SDG&E SAFETY, RISK & ASSET MANAGEMENT SYSTEMS O&M
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | SAFETY, RISK & ASSET MANAGEMENT SYSTEMS | SAFETY, RISK & ASSET MANAGEMENT SYSTEMS |  |  |  | Yes |  |  | 13318489.5223 | 0 | 0 | 0 | 13318489.5223 | 16752999.9888 | 17254999.986 | 17773999.9872 | 18306999.9876 | 16752999.9888 | -3434510.4665 | -17254999.986 | -17773999.9872 | -18306999.9876 | -3434510.4665 | -20.5% | -100% | -100% | -100% | -20.5%
O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 0.07799 | 0 | 0 | 0 | 0.07799 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 22999.9992 | -22999.9212 | -24000 | -24999.9996 | -25999.9992 | -22999.9212 | -100% | -100% | -100% | -100% | -100% | This activity area consists of work to further develop and implement asset data aggregation, integration, and asset health models for an expanded scope of assets within Gas, Smart Meter, Facilities, Information Technology, and emerging lines of business. The development of these data repositories supports the overall objectives of the broader Asset Integrity Management (AIM) program. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | SDG&E believes that this component of the Asset Management Framework should have been coupled with the broader Asset Management activities below. SDGE does not anticipate having a "non-RAMP" component of Asset Management in this General Rate Case cycle.
O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Asset Management | AIM (Gov, Strat, AIP) | N/A | No | On-going | Annual | 421606.1896 | 0 | 0 | 0 | 421606.1896 | 720000 | 741000 | 762999.9996 | 786000 | 720000 | -298393.8104 | -741000 | -762999.9996 | -786000 | -298393.8104 | -41.44% | -100% | -100% | -100% | -41.44% | This activity area consists of work to further develop and implement asset data aggregation, integration, and asset health models for an expanded scope of assets within Gas, Smart Meter, Facilities, Information Technology, and emerging lines of business. The development of these data repositories supports the overall objectives of the broader Asset Integrity Management (AIM) program. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Asset Management | Asset Data Syst & Rec Mgt (Data Integration) | N/A | No | On-going | Annual | 194032.9362 | 0 | 0 | 0 | 194032.9362 | 168999.9996 | 174000 | 178999.9992 | 183999.9996 | 168999.9996 | 25032.9366 | -174000 | -178999.9992 | -183999.9996 | 25032.9366 | 14.81% | -100% | -100% | -100% | 14.81% | This activity area consists of objectives to continue alignment and integration of asset information across various functional areas to enable data-driven, risk-informed initiatives, supporting capital investment priorities, and advance asset data intelligence, integration, and analytics. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Asset Management | Asset Data Syst & Rec Mgt (Gov, Quality, Rec Mgt) | N/A | No | On-going | Annual | 62564.1104 | 0 | 0 | 0 | 62564.1104 | 0 | 0 | 0 | 0 | 0 | 62564.1104 | 0 | 0 | 0 | 62564.1104 | 100% | 0% | 0% | 0% | 100% | This activity area consists of cloud computing costs and it is infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal ASSET MANAGEMENT |  |  |  | Yes |  |  | 678203.3142 | 0 | 0 | 0 | 678203.3142 | 911999.9988 | 939000 | 966999.9984 | 995999.9988 | 911999.9988 | -233796.6846 | -939000 | -966999.9984 | -995999.9988 | -233796.6846 | -25.64% | -100% | -100% | -100% | -25.64% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | BUSINESS TECHNOLOGY SOLUTIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2217214.949 | 0 | 0 | 0 | 2217214.949 | 2704999.9992 | 2785999.9992 | 2869999.9992 | 2955999.9996 | 2704999.9992 | -487785.0502 | -2785999.9992 | -2869999.9992 | -2955999.9996 | -487785.0502 | -18.03% | -100% | -100% | -100% | -18.03% | FTE | 8.1 |  |  |  | 8.1 | 10.9 |  |  |  | 10.9 | -2.8 | 0 | 0 | 0 | -2.8 | -25.69% | 0% | 0% | 0% | -25.69% | YES | NO | YES | N/A | The variance in FTEs is primarly driven by lower than forecasted staffing levels. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The Business Technology Services group provides support for: Construction Planning and Design, Telecommunications Asset Management (TAMS), Pole Loading, Document Management, Vender Billing, GIS Mobile/Desktop/Web/Portal Application Design and Support, Project Coordination/Support, Project Management, and Computer Hardware and Software Support. This includes providing functional support for systems, requirements development, change management planning, facilitation of business domain testing, application and data development and design, coordination of software or application release testing, post implementation/storm support, training, advancements in overall IT innovation, optimization of hardware and software utilization, and stakeholder and business unit engagement. | SDG&E-31-R-E KJD-59 to KJD-73 1SM004.000
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal BUSINESS TECHNOLOGY SOLUTIONS |  |  |  | Yes |  |  | 2217214.949 | 0 | 0 | 0 | 2217214.949 | 2704999.9992 | 2785999.9992 | 2869999.9992 | 2955999.9996 | 2704999.9992 | -487785.0502 | -2785999.9992 | -2869999.9992 | -2955999.9996 | -487785.0502 | -18.03% | -100% | -100% | -100% | -18.03% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | ENERGY RISK MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1730808.9495 | 0 | 0 | 0 | 1730808.9495 | 1668000 | 1717999.9992 | 1770000 | 1822999.9992 | 1668000 | 62808.9495 | -1717999.9992 | -1770000 | -1822999.9992 | 62808.9495 | 3.766% | -100% | -100% | -100% | 3.766% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal ENERGY RISK MANAGEMENT |  |  |  | Yes |  |  | 1730808.9495 | 0 | 0 | 0 | 1730808.9495 | 1668000 | 1717999.9992 | 1770000 | 1822999.9992 | 1668000 | 62808.9495 | -1717999.9992 | -1770000 | -1822999.9992 | 62808.9495 | 3.766% | -100% | -100% | -100% | 3.766% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | ENTERPRISE RISK MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3264699.9446 | 0 | 0 | 0 | 3264699.9446 | 4569999.9996 | 4707000 | 4848999.9996 | 4993999.9992 | 4569999.9996 | -1305300.055 | -4707000 | -4848999.9996 | -4993999.9992 | -1305300.055 | -28.56% | -100% | -100% | -100% | -28.56% | FTE | 25 |  |  |  | 25 | 26 |  |  |  | 26 | -1 | 0 | 0 | 0 | -1 | -3.846% | 0% | 0% | 0% | -3.846% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | ENTERPRISE RISK MANAGEMENT | Asset Management | AIMDAT (Data Analytics) | N/A | No | On-going | Annual | 159033.6566 | 0 | 0 | 0 | 159033.6566 | 207000 | 213000 | 219000 | 225999.9996 | 207000 | -47966.3434 | -213000 | -219000 | -225999.9996 | -47966.3434 | -23.17% | -100% | -100% | -100% | -23.17% | This activity area consists of predictive machine learning models and asset health. Risk scores will continue to be developed for additional electric system assets and will be used to prioritize maintenance and replacement activities to stay informed on situations that might lead to potential outages or failures. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal ENTERPRISE RISK MANAGEMENT |  |  |  | Yes |  |  | 3423733.6013 | 0 | 0 | 0 | 3423733.6013 | 4776999.9996 | 4920000 | 5067999.9996 | 5219999.9988 | 4776999.9996 | -1353266.3983 | -4920000 | -5067999.9996 | -5219999.9988 | -1353266.3983 | -28.33% | -100% | -100% | -100% | -28.33% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 706334.5899 | 0 | 0 | 0 | 706334.5899 | 1196999.9976 | 1233999.9984 | 1271999.9988 | 1310999.9988 | 1196999.9976 | -490665.4077 | -1233999.9984 | -1271999.9988 | -1310999.9988 | -490665.4077 | -40.99% | -100% | -100% | -100% | -40.99% | FTE | 2.7 |  |  |  | 2.7 | 2.7 |  |  |  | 2.7 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving a Contractor | Contractor Oversight Program | Overall | No | On-going | Annual | 1044451.2853 | 0 | 0 | 0 | 1044451.2853 | 1206000 | 1242000 | 1278999.9996 | 1317000 | 1206000 | -161548.7147 | -1242000 | -1278999.9996 | -1317000 | -161548.7147 | -13.4% | -100% | -100% | -100% | -13.4% | FTE | 6.3 |  |  |  | 6.3 | 9.4 |  |  |  | 9.4 | -3.1 | 0 | 0 | 0 | -3.1 | -32.98% | 0% | 0% | 0% | -32.98% | YES | NO | YES | N/A | The variance in FTEs is primarly driven by lower than forecasted staffing levels. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Safety Compliance is primarily responsibile for compliance with safety regulations and establishing and managing programs, policies and guidelines to promote the safety of SDG&E employees. | SDG&E-31-R-E KJD-36 to KJD-42 1SM002.001
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Break/rest trailers with filtered air systems | Non-Vehicle incident | No | On-going | Annual | -0.58655 | 0 | 0 | 0 | -0.58655 | 169999.9992 | 174999.9996 | 180000 | 184999.9992 | 169999.9992 | -170000.5857 | -174999.9996 | -180000 | -184999.9992 | -170000.5857 | -100% | -100% | -100% | -100% | -100% | Staging area trailers | 0 |  |  |  | 0 | 15 |  |  |  | 15 | -15 | 0 | 0 | 0 | -15 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Break rest trailers were not needed as air quality thresholds were not exceeded during wildfire support operations in SDG&E’s service territory in 2024. | Under (U) | Under (U) | Under (U) | Other | YES | Break rest trailers were not needed as no wildfire occurred in SDG&E’s service territory in 2024. | Safety Compliance is primarily responsibile for compliance with safety regulations and establishing and managing programs, policies and guidelines to promote the safety of SDG&E employees. | SDG&E-31-R-E KJD-36 to KJD-42 1SM002.001
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Designer support to update & convert safety training | N/A | No | On-going | Annual | -0.03905 | 0 | 0 | 0 | -0.03905 | 31999.9992 | 33000 | 33999.9996 | 34999.9992 | 31999.9992 | -32000.0382 | -33000 | -33999.9996 | -34999.9992 | -32000.0382 | -100% | -100% | -100% | -100% | -100% | Contractor FTE | 0 |  |  |  | 0 | 0.5 |  |  |  | 0.5 | -0.5 | 0 | 0 | 0 | -0.5 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Designer cross-functional support leveraged. Safety training conversion was performed, but no cost included within this cost center. | Under (U) | Under (U) | Under (U) | Other | YES | Designer cross-functional support leveraged. Safety training conversion was performed, but no cost included within this cost center. | Safety Compliance is primarily responsibile for compliance with safety regulations and establishing and managing programs, policies and guidelines to promote the safety of SDG&E employees. | SDG&E-31-R-E KJD-36 to KJD-42 1SM002.001
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Employee Wildfire Smoke Protection Cal/OSHA emergency regulation | N/A | No | On-going | Annual | 21444.8069 | 0 | 0 | 0 | 21444.8069 | 18000 | 18999.9996 | 19999.9992 | 21000 | 18000 | 3444.8069 | -18999.9996 | -19999.9992 | -21000 | 3444.8069 | 19.14% | -100% | -100% | -100% | 19.14% | Employees requiring medical evaluation | 600 |  |  |  | 600 | 650 |  |  |  | 650 | -50 | 0 | 0 | 0 | -50 | -7.692% | 0% | 0% | 0% | -7.692% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Enhanced Mandatory Employee Training (OSHA): Certified Occupational Safety Specialist, Certified Utility Safety Professional; Certified Safety Professional | Overall | No | On-going | Annual | 8041.0288 | 0 | 0 | 0 | 8041.0288 | 6999.9996 | 6999.9996 | 6999.9996 | 6999.9996 | 6999.9996 | 1041.0292 | -6999.9996 | -6999.9996 | -6999.9996 | 1041.0292 | 14.87% | -100% | -100% | -100% | 14.87% | Employees trained | 25 |  |  |  | 25 | 30 |  |  |  | 30 | -5 | 0 | 0 | 0 | -5 | -16.67% | 0% | 0% | 0% | -16.67% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | Overall | No | On-going | Annual | 743842.1573 | 0 | 0 | 0 | 743842.1573 | 627999.9996 | 645999.9996 | 664999.9992 | 684999.9996 | 627999.9996 | 115842.1577 | -645999.9996 | -664999.9992 | -684999.9996 | 115842.1577 | 18.45% | -100% | -100% | -100% | 18.45% | FTE | 3.7 |  |  |  | 3.7 | 3.9 |  |  |  | 3.9 | -0.2 | 0 | 0 | 0 | -0.2 | -5.128% | 0% | 0% | 0% | -5.128% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Respiratory protection for wildfire smoke particulates | Overall | No |  |  | 0 | 0 | 0 | 0 | 0 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -100% | -100% | -100% | -100% | -100% | Replacement filters purchased | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | This cost was absorbed by individual business units as employees obtain replacement filters directly from the storeroom and costs are billed to their cost centers. | Safety Compliance is primarily responsibile for compliance with safety regulations and establishing and managing programs, policies and guidelines to promote the safety of SDG&E employees. | SDG&E-31-R-E KJD-36 to KJD-42 1SM002.001
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal SAFETY |  |  |  | Yes |  |  | 2524113.2426 | 0 | 0 | 0 | 2524113.2426 | 3259999.9944 | 3357999.996 | 3458999.9952 | 3562999.9956 | 3259999.9944 | -735886.7518 | -3357999.996 | -3458999.9952 | -3562999.9956 | -735886.7518 | -22.57% | -100% | -100% | -100% | -22.57% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 131645.3701 | 0 | 0 | 0 | 131645.3701 | 165000 | 169999.9992 | 174999.9996 | 178999.9992 | 165000 | -33354.6299 | -169999.9992 | -174999.9996 | -178999.9992 | -33354.6299 | -20.21% | -100% | -100% | -100% | -20.21% | FTE | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Development and Implementation of a Strong Management of Change Platform | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 84999.9996 | 87999.9996 | 90999.9996 | 93999.9996 | 84999.9996 | -84999.9996 | -87999.9996 | -90999.9996 | -93999.9996 | -84999.9996 | -100% | -100% | -100% | -100% | -100% | This activity consists of a standardized Management of Change (MOC) process to reduce the possibility of introducing additional risk, or inadvertently increasing the risk, to public or employee health and safety, the environment, or the community as the result of a change. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | During 2024, SDG&E assessed internal development of a single safety application to include a Management of Change platform in lieu of a separate, standalone application. Assessments are ongoing. In the interim, SDG&E is leveraging SoCalGas’ Management of Change platform to capture and track identified changes.
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Development and Implementation of an Enterprise-Wide SMS | N/A | No | On-going | Annual | 604691.6724 | 0 | 0 | 0 | 604691.6724 | 925999.9992 | 952999.9992 | 981999.9996 | 1011000 | 925999.9992 | -321308.3268 | -952999.9992 | -981999.9996 | -1011000 | -321308.3268 | -34.7% | -100% | -100% | -100% | -34.7% | FTE | 3 |  |  |  | 3 | 3.9 |  |  |  | 3.9 | -0.9 | 0 | 0 | 0 | -0.9 | -23.08% | 0% | 0% | 0% | -23.08% | YES | NO | YES | N/A | The variance is primarily due to lower than forecasted staffing levels. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | SDG&E has developed and is operating within a Safety Management System (SMS) framework to improve its safety performance and culture with a structured, systematic, aligned approach to risk and safety. The SMS takes a process-based approach to build risk, safety, and asset management into all programs, projects and activities. SDG&E is currently implementing its developed SMS processes and will continue to measure and evaluate program effectiveness for continuous safety improvement . | SDG&E-31-R-E KJD-23 to KJD-32 1SM001.000
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Enhanced Documentation and Recordkeeping Practices | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 27999.9996 | 28999.9992 | 30000 | 30999.9996 | 27999.9996 | -27999.9996 | -28999.9992 | -30000 | -30999.9996 | -27999.9996 | -100% | -100% | -100% | -100% | -100% | This activity area consists of technology software upgrades to aid in enhanced documentation and recordkeeping practices to align document and recordkeeping processes to coordinate cross-functional access to support the SMS. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | Within its Safety Management System, SDG&E applies enhanced documentation and recordkeeping practices. SDG&E’s SMS documentation was developed in 2020 – 2022. Per SDG&E’s policy review cycle, SDG&E’s SMS documentation will undergo review and update starting in 2025.
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Enhanced Employee and Stakeholder Engagement, including SMS Competence, Awareness, Survey and Training | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 27999.9996 | 28999.9992 | 30000 | 30999.9996 | 27999.9996 | -27999.9996 | -28999.9992 | -30000 | -30999.9996 | -27999.9996 | -100% | -100% | -100% | -100% | -100% | This activity area consists of plans to develop and deliver SMS-specific training and create ways to measure and track such competencies. The creation of an employee engagement and training program is necessary to achieve full understanding and cultural adoption of SMS with its broader safety focus on all safety pillars: People Safety, Risk Identification & Management, Asset Safety, Gas & Electric Operations, and Emergency Preparedness/Incident Response. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | Within its Safety Management System, SDG&E seeks enhanced internal and external stakeholder feedback, survey and training. In 2024, these efforts did not incur costs that were separately tracked. As SDG&E seeks to further implement and mature its SMS, we will apply additional focus on survey, benchmarking, measurement and review.
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Enhanced Stakeholder Feedback and Key Performance Indicator Monitoring, Tracking, and Reporting | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 57000 | 58999.9992 | 60999.9996 | 63000 | 57000 | -57000 | -58999.9992 | -60999.9996 | -63000 | -57000 | -100% | -100% | -100% | -100% | -100% | This activity area consists of processes for considering qualitative (e.g., subject matter expert feedback) and quantitative (e.g., KPIs and quality control results) to perform data analysis for trends and emergent issues to identify and mitigate new risks and to improve the SMS. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | Within its Safety Management System, SDG&E seeks enhanced internal and external stakeholder feedback. In 2024, these efforts did not incur costs that were separately tracked. As SDG&E seeks to further implement and mature its SMS, we will apply additional focus on key performance indicators, benchmarking, measurement and review.
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Integration of New Technology and Enhanced Data and Analytics Capabilities for Continuous Safety Improvement | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 240000 | 246999.9996 | 252999.9996 | 261000 | 240000 | -240000 | -246999.9996 | -252999.9996 | -261000 | -240000 | -100% | -100% | -100% | -100% | -100% | This activity area consists of integrating new technology to enhance worker and/or system safety (e.g., data and analytic tools and communication tools) to measure the effectiveness of the SMS. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | In 2024, SDG&E leveraged existing technology and resources to perform data collection and analytics. This is a manual process that can be improved and matured with enhanced technology and resources. SDG&E is assessing options for a single safety application for the most effective and optimal solution.
O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | SMS Program Benchmarking, Measurement, and Maturity Assessment for Continuous Improvement | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 57000 | 58999.9992 | 60999.9996 | 63000 | 57000 | -57000 | -58999.9992 | -60999.9996 | -63000 | -57000 | -100% | -100% | -100% | -100% | -100% | This activity area consists of applying multiple layers of safety assurances to improve performance and effective risk management. These safety assurances, coupled with regular review, assessment, and audit, help evaluate quality and completeness of programs and confirm that risk management processes are systematic and disciplined. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | Within its Safety Management System, SDG&E seeks enhanced internal and external stakeholder feedback, survey, benchmarking and review. In 2024, SDG&E informally collaborated and benchmarked with industry partners but these efforts did not incur costs that were separately tracked. As SDG&E seeks to further implement and mature its SMS, we will apply additional focus on survey, benchmarking, measurement and review.
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal SAFETY MANAGEMENT SYSTEM |  |  |  | Yes |  |  | 736337.0425 | 0 | 0 | 0 | 736337.0425 | 1585999.998 | 1633999.9944 | 1682999.9976 | 1732999.998 | 1585999.998 | -849662.9555 | -1633999.9944 | -1682999.9976 | -1732999.998 | -849662.9555 | -53.57% | -100% | -100% | -100% | -53.57% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | SDG&E FIELD SAFETY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1087915.4014 | 0 | 0 | 0 | 1087915.4014 | 1020999.9996 | 1050999.9996 | 1081999.9992 | 1114999.9992 | 1020999.9996 | 66915.4018 | -1050999.9996 | -1081999.9992 | -1114999.9992 | 66915.4018 | 6.554% | -100% | -100% | -100% | 6.554% | FTE | 7.1 |  |  |  | 7.1 | 7.4 |  |  |  | 7.4 | -0.3 | 0 | 0 | 0 | -0.3 | -4.054% | 0% | 0% | 0% | -4.054% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SDG&E FIELD SAFETY | Incident Involving an Employee | Safe Driving Programs | Vehicle Incident | No | On-going | Annual | 24253.34 | 0 | 0 | 0 | 24253.34 | 100999.9992 | 103999.9992 | 106999.9992 | 109999.9992 | 100999.9992 | -76746.6592 | -103999.9992 | -106999.9992 | -109999.9992 | -76746.6592 | -75.99% | -100% | -100% | -100% | -75.99% | Employees in safe driving programs | 2200 |  |  |  | 2200 | 2200 |  |  |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SDG&E FIELD SAFETY | Incident Involving an Employee | Strong Safety Culture | N/A | No | On-going | Annual | 368550 | 0 | 0 | 0 | 368550 | 252000 | 259999.9992 | 267999.9996 | 276000 | 252000 | 116550 | -259999.9992 | -267999.9996 | -276000 | 116550 | 46.25% | -100% | -100% | -100% | 46.25% | Safety Events | 2 |  |  |  | 2 | 2 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal SDG&E FIELD SAFETY |  |  |  | Yes |  |  | 1480718.7414 | 0 | 0 | 0 | 1480718.7414 | 1373999.9988 | 1414999.998 | 1456999.998 | 1500999.9984 | 1373999.9988 | 106718.7426 | -1414999.998 | -1456999.998 | -1500999.9984 | 106718.7426 | 7.767% | -100% | -100% | -100% | 7.767% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SAFETY MANAGEMENT SYSTEMS | VP- RISK MGMT & CHF COMPL OFCR | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 527359.6817 | 0 | 0 | 0 | 527359.6817 | 471000 | 484999.9992 | 499999.9992 | 514999.9992 | 471000 | 56359.6817 | -484999.9992 | -499999.9992 | -514999.9992 | 56359.6817 | 11.97% | -100% | -100% | -100% | 11.97% | FTE | 1.6 |  |  |  | 1.6 | 1.6 |  |  |  | 1.6 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SAFETY MANAGEMENT SYSTEMS | SubTotal VP- RISK MGMT & CHF COMPL OFCR |  |  |  | Yes |  |  | 527359.6817 | 0 | 0 | 0 | 527359.6817 | 471000 | 484999.9992 | 499999.9992 | 514999.9992 | 471000 | 56359.6817 | -484999.9992 | -499999.9992 | -514999.9992 | 56359.6817 | 11.97% | -100% | -100% | -100% | 11.97% | [21 empty] | YES | NO | [7 empty] | NO

## EOWM-B
SDG&E WILDFIRE MITIGATION & VEGETATION MANAGEMENT O&M
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WILDFIRE MITIGATION & VEGETATION MANAGEMENT |  |  |  | Yes |  |  | 190917511.8475 | 0 | 0 | 0 | 190917511.8475 | 192813999.9756 | 198595999.9812 | 204552999.9732 | 210687999.978 | 192813999.9756 | -1896488.1281 | -198595999.9812 | -204552999.9732 | -210687999.978 | -1896488.1281 | -0.9836% | -100% | -100% | -100% | -0.9836%
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist Syst InspectCMP 5 Yr Detail Inspect | Tier 2 | No | On-going | Annual | 201991.1097 | 0 | 0 | 0 | 201991.1097 | 132000 | 135999.9996 | 139999.9992 | 144000 | 132000 | 69991.1097 | -135999.9996 | -139999.9992 | -144000 | 69991.1097 | 53.02% | -100% | -100% | -100% | 53.02% | HFTD Inspections | 6190 |  |  |  | 6190 | 6070 |  |  |  | 6070 | 120 | 0 | 0 | 0 | 120 | 1.977% | 0% | 0% | 0% | 1.977% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.478 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist Syst InspectCMP 5 Yr Detail Inspect | Tier 3 | No | On-going | Annual | 336532.9768 | 0 | 0 | 0 | 336532.9768 | 225000 | 231999.9996 | 238999.9992 | 246000 | 225000 | 111532.9768 | -231999.9996 | -238999.9992 | -246000 | 111532.9768 | 49.57% | -100% | -100% | -100% | 49.57% | HFTD Inspections | 10313 |  |  |  | 10313 | 10320 |  |  |  | 10320 | -7 | 0 | 0 | 0 | -7 | -0.06783% | 0% | 0% | 0% | -0.06783% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.478 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspect CMP Annual Patrol | Tier 2 | No | On-going | Annual | 154243.739 | 0 | 0 | 0 | 154243.739 | 171999.9996 | 177000 | 181999.9992 | 186999.9996 | 171999.9996 | -17756.2606 | -177000 | -181999.9992 | -186999.9996 | -17756.2606 | -10.32% | -100% | -100% | -100% | -10.32% | HFTD Patrols | 46793 |  |  |  | 46793 | 46751 |  |  |  | 46751 | 42 | 0 | 0 | 0 | 42 | 0.08984% | 0% | 0% | 0% | 0.08984% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.488 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspect CMP Annual Patrol | Tier 3 | No | On-going | Annual | 129698.9491 | 0 | 0 | 0 | 129698.9491 | 144999.9996 | 148999.9992 | 153000 | 157999.9992 | 144999.9996 | -15301.0505 | -148999.9992 | -153000 | -157999.9992 | -15301.0505 | -10.55% | -100% | -100% | -100% | -10.55% | HFTD Patrols | 39347 |  |  |  | 39347 | 39371 |  |  |  | 39371 | -24 | 0 | 0 | 0 | -24 | -0.06096% | 0% | 0% | 0% | -0.06096% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.488 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspection Drone Inspections | Tier 3 | No | On-going | Annual | 32869592.8412 | 0 | 0 | 0 | 32869592.8412 | 14443999.9992 | 14877999.9996 | 15324000 | 15783999.9996 | 14443999.9992 | 18425592.842 | -14877999.9996 | -15324000 | -15783999.9996 | 18425592.842 | 127.6% | -100% | -100% | -100% | 127.6% | The number of inspections and repairs varies each year based on evolving methodologies and the specific issues identified, making direct comparisons difficult. Additionally, the range of work activities within this program is too diverse to be captured by a single, consistent unit of measurement year over year. | [20 empty] | YES | YES | NO | The 2024 spend was over authorized primarily due to ongoing repair work associated with Tier 2 HFTD drone inspections performed in 2021 and 2022. It was originally anticipated that repair work for Tier 2 drone inspections would be completed by the end of 2023 and both inspections and repairs were expected to be significantly reduced in 2024 and going forward. However, 2022 and 2023 repair work associated with Tier 2 HFTD drone inspections was shifted into 2024 and later due to identifying significantly more scope than anticipated, engineering delays, resource constraints and material shortages. In addition, repair work identified during the ongoing drone inspections performed in 2023 and 2024 was higher than forecasted. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.483 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspection HFTD Tier 3 Inspections | Tier 3 | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 373999.9992 | 384999.9996 | 396999.9996 | 408999.9996 | 373999.9992 | -373999.9992 | -384999.9996 | -396999.9996 | -408999.9996 | -373999.9992 | -100% | -100% | -100% | -100% | -100% | HFTD Inspections | 0 |  |  |  | 0 | 11596 |  |  |  | 11596 | -11596 | 0 | 0 | 0 | -11596 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | HFTD Tier 3 inspections were discontinued in 2022 and replaced in 2023 with risk-informed drone inspections (RIDI). RIDI work is tracked under Dist System Inspection – Drone Inspections. | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.483 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspection IR/Corona | Tier 2 | No | On-going | Annual | 138733.9999 | 0 | 0 | 0 | 138733.9999 | 199999.9992 | 205999.9992 | 211999.9992 | 217999.9992 | 199999.9992 | -61265.9993 | -205999.9992 | -211999.9992 | -217999.9992 | -61265.9993 | -30.63% | -100% | -100% | -100% | -30.63% | HFTD Inspections | 6398 |  |  |  | 6398 | 18000 |  |  |  | 18000 | -11602 | 0 | 0 | 0 | -11602 | -64.46% | 0% | 0% | 0% | -64.46% | YES | NO | YES | N/A | In 2024, SDG&E transitioned this program to a risk-informed approach in an effort to find efficiencies and optimize outcomes. In prior years, structures selected for this program were based on previously inspected structures to ensure no repeat inspections were performed in consecutive years and on subject matter experts’ (SME) recommendations. SDG&E has found that this inspection program yielded only a 0.2% find rate. To optimize this program and make it more effective in 2024, the program targeted specific areas during peak load season and the structures were selected using a risk-informed strategy comprised of SDG&E’s Asset 360 models, risk analytics models, and Intelligent Image Processing (IIP). This program will continue with the risk-informed approach in 2025, and inspections will be performed on 300 structures, as approved in its 2025 Wildfire Mitigation Plan (WMP) Update. SDG&E does not anticipate these changes will impact desired risk reduction. | Under (U) | Under (U) | Under (U) | Other | NO | In 2024, SDG&E transitioned this program to a risk-informed approach to improve efficiency and outcomes. Previously, structures were selected based on past inspections and SME recommendations, but the program's 0.2% find rate highlighted its limited effectiveness. To enhance impact, SDG&E now targets specific areas during peak load seasons using Asset 360 models, risk analytics, and Intelligent Image Processing (IIP). The program is set to continue with this approach in 2025, focusing on 300 structures as outlined in the 2025 WMP Update. However, due to its historically low find rate, there is a possibility the program may be discontinued in the future if risk reduction goals are better met through alternative strategies. | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.483 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Intrusive Poles | Tier 2 | No | On-going | Annual | 59555.2116 | 0 | 0 | 0 | 59555.2116 | 48999.9996 | 49999.9992 | 51999.9996 | 54000 | 48999.9996 | 10555.212 | -49999.9992 | -51999.9996 | -54000 | 10555.212 | 21.54% | -100% | -100% | -100% | 21.54% | HFTD Inspections | 1818 |  |  |  | 1818 | 679 |  |  |  | 679 | 1139 | 0 | 0 | 0 | 1139 | 167.7% | 0% | 0% | 0% | 167.7% | YES | NO | YES | N/A | The inspection targets for each year is based on a snapshot in time in SDG&E’s work management system. Generally, SDG&E generates the target for this program by running a report in the work management system to identify wood poles that are due for inspection in the upcoming calendar year. However, that report inevitably changes almost daily with changes to the electric system. Poles can fall in and out of the inspection cycle for various reasons, including but not limited to the following: 1. Pole retired – removed from service 2. Pole replaced (e.g. due to third party damage, conversion to steel or other reason) 3. Pole received a special off-cycle inspection to support a Pole loading Calculation as required by GO 95, Rule 44.2 | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.483 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Intrusive Poles | Tier 3 | No | On-going | Annual | 13332.9285 | 0 | 0 | 0 | 13332.9285 | 94999.9992 | 97999.9992 | 100999.9992 | 103999.9992 | 94999.9992 | -81667.0707 | -97999.9992 | -100999.9992 | -103999.9992 | -81667.0707 | -85.97% | -100% | -100% | -100% | -85.97% | HFTD Inspections | 407 |  |  |  | 407 | 1321 |  |  |  | 1321 | -914 | 0 | 0 | 0 | -914 | -69.19% | 0% | 0% | 0% | -69.19% | YES | NO | YES | N/A | The inspection targets for each year is based on a snapshot in time in SDG&E’s work management system. Generally, SDG&E generates the target for this program by running a report in the work management system to identify wood poles that are due for inspection in the upcoming calendar year. However, that report inevitably changes almost daily with changes to the electric system. Poles can fall in and out of the inspection cycle for various reasons, including but not limited to the following: 1. Pole retired – removed from service 2. Pole replaced (e.g. due to third party damage, conversion to steel or other reason) 3. Pole received a special off-cycle inspection to support a Pole loading Calculation as required by GO 95, Rule 44.2 | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.483 in the 2023 WMP filing. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | LiDAR Flights | N/A | No | On-going | Annual | 31361 | 0 | 0 | 0 | 31361 | 1711999.9992 | 1762999.9992 | 1815999.9996 | 1869999.9996 | 1711999.9992 | -1680638.9992 | -1762999.9992 | -1815999.9996 | -1869999.9996 | -1680638.9992 | -98.17% | -100% | -100% | -100% | -98.17% | This workpaper includes light detection and ranging (LiDAR) inspections which is a new and evolving initiative that uses LiDAR surveys. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This cost category consists of SDG&E’s asset management and inspection programs. The purpose of these programs is to promote safety for the general public, SDG&E personnel, and contractors by providing a safe operating and construction environment while maintaining system reliability. SDG& E’s established inspection and maintenance programs enable SDG&E to identify and repair conditions and components to reduce the potential of equipment failure on SDG&E’s electric system to minimize hazards and maintain system reliability. To accomplish this, SDG&E meets or exceeds the requirements of the inspections mandated by Public Resource Code Sections 4292 and 4293 as well as G.O. 95, G.O. 128, G.O. 165, and G.O. 174. The asset inspection programs contained within this workpaper are the HFTD inspections associated with drone inspections, detailed inspections, HFTD Tier 3 inspections, patrol inspections, intrusive wood pole inspections, LiDAR inspections, and infrared inspections. | SDG&E-13-2R-E JTW-54 to JTW-60 WP 1WM004.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal ASSET MANAGEMENT & INSPECTIONS |  |  |  | Yes |  |  | 33935042.7558 | 0 | 0 | 0 | 33935042.7558 | 17547999.9948 | 18073999.9944 | 18615999.9948 | 19173999.996 | 17547999.9948 | 16387042.761 | -18073999.9944 | -18615999.9948 | -19173999.996 | 16387042.761 | 93.38% | -100% | -100% | -100% | 93.38% | [21 empty] | YES | YES | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | DATA GOVERNANCE | Wildfire Involving SDG&E Equipment | Data Governance | N/A | No | On-going | Annual | 1322326.8922 | 0 | 0 | 0 | 1322326.8922 | 1873999.9992 | 1929999.9996 | 1987999.9992 | 2047999.9992 | 1873999.9992 | -551673.107 | -1929999.9996 | -1987999.9992 | -2047999.9992 | -551673.107 | -29.44% | -100% | -100% | -100% | -29.44% | Activities include a centralized data lake for WMP data and metrics that enables consistent, reliable, and automated reporting of the spatial and non-spatial Quarterly Data Report (QDR) mandated by Energy Safety's Data guidelines, along with comprehensive documentation to ensure transparency and accountability. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Data Governance GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.519 in the 2023 WMP filing. Data Governance includes costs for centralization of data, WMP metrics, data repository, and documentation of models. Initially, SDG&E almost exclusively collected data metrics and measures manually. To enhance data quality and improve the efficiency of the data gathering process, SDG&E began developing a WMP Data Governance Framework (DGF) and an automated Central Data Repository (CDR) for wildfire-related data, which can be used by multiple internal and external stakeholders in the future. These changes will improve data collection by moving away from manual collection to a more uniform, electronic format that will provide data metrics in a searchable format, similar to a GIS data structure. The DGF will define a set of repeatable standards, policies, processes and controls for wildfire- related data. Similar to the Wildfire Safety Division’s GIS Data Standards, the vision of SDG&E’s DGF is to make its wildfire-related data actionable, accessible, aligned, and auditable. In 2020, SDG&E began centralizing its measures and metrics put forth in Wildfire Mitigation Plans in a central repository to gain insights and assess progress on programs and initiatives. | SDG&E-13-2R-E JTW-84 to JTW-85 WP 1WM007.002
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal DATA GOVERNANCE |  |  |  | Yes |  |  | 1322326.8922 | 0 | 0 | 0 | 1322326.8922 | 1873999.9992 | 1929999.9996 | 1987999.9992 | 2047999.9992 | 1873999.9992 | -551673.107 | -1929999.9996 | -1987999.9992 | -2047999.9992 | -551673.107 | -29.44% | -100% | -100% | -100% | -29.44% | [21 empty] | YES | NO | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | EMERGENCY PLANNING & PREPAREDNESS | Wildfire Involving SDG&E Equipment | Emergency Management Operations | N/A | No | On-going | Annual | 17536855.2396 | 0 | 0 | 0 | 17536855.2396 | 18471999.9996 | 19026000 | 19596999.9996 | 20184999.9996 | 18471999.9996 | -935144.76 | -19026000 | -19596999.9996 | -20184999.9996 | -935144.76 | -5.062% | -100% | -100% | -100% | -5.062% | Emergency Management Operations focus on preparedness and response to unpredictable hazards, particularly wildfires. Unlike programs with consistent metrics, these efforts involve varied activities—planning, training, exercises, and direct response—that change in scope and complexity each year. Because emergencies demand adaptive strategies, a single, comparable unit of measurement is not feasible. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Emergency Planning and Preparedness GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1008 in the 2023 WMP filing. The mission of the SDG&E Emergency Management department is to coordinate safe and effective emergency preparedness for the Company, the public, and emergency response personnel. That mission extends to safely and efficiently preparing for, responding to, and recovering from all threats and hazards through strategic planning, training and exercising, and a sustained Quality Assurance and Improvement process. The Emergency Planning & Preparedness cost category comprises of five divisions: (1) Emergency Services Division, (2) Operational Field and Emergency Readiness, (3) Aviation Services, (4) Training and Exercise, and (5) Emergency Management Technology Solutions. | SDG&E-13-2R-E JTW-30 to JTW-43 WP 1WM001.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal EMERGENCY PLANNING & PREPAREDNESS |  |  |  | Yes |  |  | 17536855.2396 | 0 | 0 | 0 | 17536855.2396 | 18471999.9996 | 19026000 | 19596999.9996 | 20184999.9996 | 18471999.9996 | -935144.76 | -19026000 | -19596999.9996 | -20184999.9996 | -935144.76 | -5.062% | -100% | -100% | -100% | -5.062% | [21 empty] | YES | NO | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Advanced Protection | Tier 3 | No | On-going | Annual | 145415.1656 | 0 | 0 | 0 | 145415.1656 | 0 | 0 | 0 | 0 | 0 | 145415.1656 | 0 | 0 | 0 | 145415.1656 | 100% | 0% | 0% | 0% | 100% | Circuits | 5 |  |  |  | 5 | 0 |  |  |  | 0 | 5 | 0 | 0 | 0 | 5 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | O&M costs are typically forecasted based on historical expenditures. However, during the 2024 GRC application, no historical data was available for this project. While forecasted and authorized capital expenditures exist, the associated O&M costs were not initially projected, as no O&M spending was anticipated at the time of the 2024 GRC application. These costs are directly linked to the units worked on through capital charges, which ultimately drove the need for O&M activities. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The O&M activities support the capital workpaper included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.463 and WMP.1195 in the 2023 WMP filing. The purpose of this project is to replace aging circuit breakers and/or obsolete electromechanical relays and to create a more comprehensive protection system with installation of Distribution Supervisory Control and Data Acquisition (SCADA). Substation improvements include the following: • Reconfiguration of 12kV circuit breakers and relays to meet reliability and safety standards. • Installation of Distribution SCADA. • Installation of new transformer bank relays. • Installation of new 12kV Bus Differential relays. • Installation of microprocessor feeder relays. Advanced Protection devices to enhance feeder protection, reduce fire risk, and enable opportunities include: • Falling conductor logic • Downed conductor detection (DCD) • Arc sensing technology (AST) • Advanced SGF (spike counting/adaptive set-point) • Remote event retrieval • Remote setting changes | SDG&E-13-2R-E JTW-119 to JTW-121 CWP 152590
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Avian Protection Program | OH Distribution | No | On-going | Annual | 30391.6984 | 0 | 0 | 0 | 30391.6984 | 0 | 0 | 0 | 0 | 0 | 30391.6984 | 0 | 0 | 0 | 30391.6984 | 100% | 0% | 0% | 0% | 100% | Poles protected | 774 |  |  |  | 774 | 0 |  |  |  | 0 | 774 | 0 | 0 | 0 | 774 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | O&M costs are typically forecasted based on historical expenditures. However, during the 2024 GRC application, no historical data was available for this project. While forecasted and authorized capital expenditures exist, the associated O&M costs were not initially projected, as no O&M spending was anticipated at the time of the 2024 GRC application. These costs are directly linked to the units worked on through capital charges, which ultimately drove the need for O&M activities. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The O&M activities support the capital workpaper included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.972 in the 2023 WMP filing. Lightning arrestors are installed on the distribution system throughout the service territory to protect electric power equipment from exceeding thermal insulation ratings in the event of surge voltages due to lightning strikes or other faults. The lightning arrestor enables a surge in the current to be diverted through the arrestor to a ground terminal and protect the insulation and conductors on the distribution system. The lightning arrestor replacement program utilizes new technology to reduce the risk of equipment-related failures and ignitions. Through this process, a new lightning arrestor standard product was introduced that received CAL FIRE approval. The purpose of this project is to replace outdated lightning arrestors with the CAL FIRE-approved lightning arrestors. Embedded within this budget code is also work related to avian protection. SDG&E will bundle these types of jobs together to avoid revisiting the same pole and causing multiple planned outages for customers. The avian protection program seeks to install avian protection equipment or otherwise rearrange distribution poles to prevent avian contact with energized conductor. This is in compliance with the Migratory Bird Treaty Act, Bald and Golden Eagle Protection Act, and codes defined by the California Department of Fish and Game. This will harden the system, reducing the risk of ignition associated with avian contact, improve reliability, and align with Avian Power Line Interaction Committee (APLIC) Guidelines. | SDG&E-13-2R-E JTW-122 to JTW-124 CWP 202820
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | BLM Land Management | New01 | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | -4999.9992 | -4999.9992 | -4999.9992 | -4999.9992 | -4999.9992 | -100% | -100% | -100% | -100% | -100% | Plans | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The Bureau of Land Management (BLM) O&M Plan has been temporarily paused at the request of BLM staff, pending the completion of the O&M plans for Southern California Edison and Pacific Gas and Electric Company. | On Target (T) | On Target (T) | On Target (T) | Other | YES | The Bureau of Land Management (BLM) O&M Plan has been temporarily paused at the request of BLM staff, pending the completion of the O&M plans for Southern California Edison and Pacific Gas and Electric Company. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | CNF Access Roads | None | No | On-going | Annual | 231729.6576 | 0 | 0 | 0 | 231729.6576 | 0 | 0 | 0 | 0 | 0 | 231729.6576 | 0 | 0 | 0 | 231729.6576 | 100% | 0% | 0% | 0% | 100% | Miles of road decommissioned | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | The costs associated with this program are trailing expenses and are not anticipated to recur in future years. The program was originally planned for completion before 2024. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1017 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | CNF Land Management | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 153000 | 157999.9992 | 162999.9996 | 168000 | 153000 | -153000 | -157999.9992 | -162999.9996 | -168000 | -153000 | -100% | -100% | -100% | -100% | -100% | Cleveland National Forest (CNF) Master Special Use Permit | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The issuance of the CNF Master Special Use Permit has been postponed and is scheduled to be processed in 2025. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | The issuance of the CNF Master Special Use Permit has been postponed and is scheduled to be processed in 2025. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | EARLY FAULT DETECTION | None | No | On-going | Annual | 125187.6834 | 0 | 0 | 0 | 125187.6834 | 0 | 0 | 0 | 0 | 0 | 125187.6834 | 0 | 0 | 0 | 125187.6834 | 100% | 0% | 0% | 0% | 100% | Nodes | 62 |  |  |  | 62 | 0 |  |  |  | 0 | 62 | 0 | 0 | 0 | 62 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | O&M costs are typically forecasted based on historical expenditures. However, during the 2024 GRC application, no historical data was available for this project. While forecasted and authorized capital expenditures exist, the associated O&M costs were not initially projected, as no O&M spending was anticipated at the time of the 2024 GRC application. These costs are directly linked to the units worked on through capital charges, which ultimately drove the need for O&M activities. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | This mitigation can be mapped to Tracking ID WMP.1195 in the 2023 WMP filing. The O&M activities support the Early Fault Detection capital project, which will deploy Power Quality Meters and advanced Radio Frequency (RF) Sensors in SDG&E electric substations and electric distribution circuits within the High Fire Threat District, to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. | SDG&E-13-2R-E JTW-119 to JTW-121 CWP 152590
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 2 | No | On-going | Annual | 89649.8318 | 0 | 0 | 0 | 89649.8318 | 207999.9996 | 213999.9996 | 219999.9996 | 226999.9992 | 207999.9996 | -118350.1678 | -213999.9996 | -219999.9996 | -226999.9992 | -118350.1678 | -56.9% | -100% | -100% | -100% | -56.9% | Hotline clamps replaced | 17 |  |  |  | 17 | 106 |  |  |  | 106 | -89 | 0 | 0 | 0 | -89 | -83.96% | 0% | 0% | 0% | -83.96% | YES | NO | YES | N/A | The reduction in units is attributable to the company's decision to deviate from performing standalone hotline clamp jobs due to their higher cost. Instead, the company has opted to bundle asset replacement work at a single pole, which includes hotline clamp work. This bundled approach is classified as a capital expense. Capital costs are presented in WP 242420. | Under (U) | Under (U) | Under (U) | Other | NO | The company has shifted away from standalone hotline clamp jobs due to their higher cost. Instead, the company has opted to bundle asset replacement work at a single pole, which includes hotline clamp work. This bundled approach is classified as a capital expense. Capital costs are presented in emergent CWP 242420. The work is classified as O&M if the hotline clamp is the only High-Volume asset being replaced on that structure. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.464 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 3 | No | On-going | Annual | 16114.1136 | 0 | 0 | 0 | 16114.1136 | 207999.9996 | 213999.9996 | 219999.9996 | 226999.9992 | 207999.9996 | -191885.886 | -213999.9996 | -219999.9996 | -226999.9992 | -191885.886 | -92.25% | -100% | -100% | -100% | -92.25% | Hotline clamps replaced | 3 |  |  |  | 3 | 106 |  |  |  | 106 | -103 | 0 | 0 | 0 | -103 | -97.17% | 0% | 0% | 0% | -97.17% | YES | NO | YES | N/A | The reduction in units is attributable to the company's decision to deviate from performing standalone hotline clamp jobs due to their higher cost. Instead, the company has opted to bundle asset replacement work at a single pole, which includes hotline clamp work. This bundled approach is classified as a capital expense. Capital costs are presented in WP 242420. | Under (U) | Under (U) | Under (U) | Other | NO | The company has shifted away from standalone hotline clamp jobs due to their higher cost. Instead, the company has opted to bundle asset replacement work at a single pole, which includes hotline clamp work. This bundled approach is classified as a capital expense. Capital costs are presented in emergent CWP 242420. The work is classified as O&M if the hotline clamp is the only High-Volume asset being replaced on that structure. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.464 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | LTE Communication Network | None | No | On-going | Annual | 843342.8695 | 0 | 0 | 0 | 843342.8695 | 0 | 0 | 0 | 0 | 0 | 843342.8695 | 0 | 0 | 0 | 843342.8695 | 100% | 0% | 0% | 0% | 100% | LTE communication network | 1 |  |  |  | 1 | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | O&M costs are typically forecasted based on historical expenditures. However, during the 2024 GRC application, no historical data was available for this project. While forecasted and authorized capital expenditures exist, the associated O&M costs were not initially projected, as no O&M spending was anticipated at the time of the 2024 GRC application. These costs are directly linked to the units worked on through capital charges, which ultimately drove the need for O&M activities. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The O&M activities support the capital workpaper included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.549 in the 2023 WMP filing. Existing wireless communications infrastructure is increasingly inadequate to meet the demand for greater volumes of data at high speed. Expanding the existing systems can provide coverage over a larger area but cannot meet the demand for high volume low latency data and control. To address this, SDG&E is implementing a private broadband wireless digital communications network. SDG&E is deploying a privately-owned LTE network using licensed radio frequency (RF) spectrum by means of the Distribution Communications Reliability Improvements (DCRI) program. This will enhance the overall reliability of SDG&E's communication network, which is critical for enabling fire prevention and public safety programs. SDG&E's communication network is foundational to many initiatives that demand reliable communication. The ability to reliably enable and disable sensitive settings, enable or disable reclosing, or even remotely operating a switch during a high-risk weather event demands reliable communication that the LTE network will provide. SDG&E's Falling Conductor Protection in particular relies on a robust communications network to operate successfully and falling conductor circuits will continue to be enabled as SDG&E's communication network comes online. | SDG&E-13-2R-E JTW-112 to JTW-114 CWP 198730
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Microgrids | Tier 2 | No | On-going | Annual | 1018926.3194 | 0 | 0 | 0 | 1018926.3194 | 1834999.9992 | 1890000 | 1947000 | 2004000 | 1834999.9992 | -816073.6798 | -1890000 | -1947000 | -2004000 | -816073.6798 | -44.47% | -100% | -100% | -100% | -44.47% | Megawatts reserved through generator rentals | 3.1 |  |  |  | 3.1 | 5.9 |  |  |  | 5.9 | -2.8 | 0 | 0 | 0 | -2.8 | -47.46% | 0% | 0% | 0% | -47.46% | YES | NO | YES | N/A | The generator rental fleet has been reduced following the energization and commissioning of the Ramona Air Attack Base Microgrid, as well as the completion of strategic undergrounding initiatives to support Downtown Julian. Additionally, operational efficiencies have been identified in generator sizing, enabling more effective support for most ad hoc generator requests during a Public Safety Power Shutoff (PSPS). | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.462 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Non-HFTD | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -100% | -100% | -100% | -100% | -100% | Miles hardened (Capital) | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.475 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 2 | No | On-going | Annual | 226925.6525 | 0 | 0 | 0 | 226925.6525 | 30000 | 30999.9996 | 31999.9992 | 33000 | 30000 | 196925.6525 | -30999.9996 | -31999.9992 | -33000 | 196925.6525 | 656.4% | -100% | -100% | -100% | 656.4% | Miles hardened (Capital) | 0.05 |  |  |  | 0.05 | 0 |  |  |  | 0 | 0.05 | 0 | 0 | 0 | 0.05 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Reevaluated miles and shifted to Covered Conductor scope which has higher risk reduction to phase out Traditional Hardening (Bare Conductor). | Over (O) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.475 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 3 | No | On-going | Annual | 2338483.1927 | 0 | 0 | 0 | 2338483.1927 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 22999.9992 | 2315483.1935 | -24000 | -24999.9996 | -25999.9992 | 2315483.1935 | 10067% | -100% | -100% | -100% | 10067% | Miles hardened (Capital) | 0.49 |  |  |  | 0.49 | 5 |  |  |  | 5 | -4.51 | 0 | 0 | 0 | -4.51 | -90.2% | 0% | 0% | 0% | -90.2% | YES | NO | YES | N/A | Reevaluated miles and shifted to Covered Conductor scope which has higher risk reduction to phase out Traditional Hardening (Bare Conductor). | Over (O) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.475 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Cond | Tier 2 | No | On-going | Annual | 1404008.0475 | 0 | 0 | 0 | 1404008.0475 | 121999.9992 | 126000 | 129999.9996 | 133999.9992 | 121999.9992 | 1282008.0483 | -126000 | -129999.9996 | -133999.9992 | 1282008.0483 | 1051% | -100% | -100% | -100% | 1051% | Miles hardened (Capital) | 20.85 |  |  |  | 20.85 | 18 |  |  |  | 18 | 2.85 | 0 | 0 | 0 | 2.85 | 15.83% | 0% | 0% | 0% | 15.83% | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Over (O) | Deferred | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.455 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Cond | Tier 3 | No | On-going | Annual | 1014161.5327 | 0 | 0 | 0 | 1014161.5327 | 552999.9996 | 570000 | 586999.9992 | 604999.9992 | 552999.9996 | 461161.5331 | -570000 | -586999.9992 | -604999.9992 | 461161.5331 | 83.39% | -100% | -100% | -100% | 83.39% | Miles hardened (Capital) | 15.06 |  |  |  | 15.06 | 82 |  |  |  | 82 | -66.94 | 0 | 0 | 0 | -66.94 | -81.63% | 0% | 0% | 0% | -81.63% | YES | NO | YES | N/A | Less work was designed and issued to construction in Tier 3 than authorized in the 2024-2027 General Rate Case (GRC). The draft GRC decision was issued in late October and the final decision in late December of 2024, which was too late in the year to ramp-up Covered Conductor hardening work in Tier 3 due to challenges finalizing designs, acquiring land rights, permits, and materials. | Under (U) | Under (U) | Over (O) | Deferred | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.455 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Trans Fire Hardening Dist Underbuild | Tier 2 | No | On-going | Annual | 623 | 0 | 0 | 0 | 623 | 0 | 0 | 0 | 0 | 0 | 623 | 0 | 0 | 0 | 623 | 100% | 0% | 0% | 0% | 100% | Miles hardened (Capital) | 7 |  |  |  | 7 | 0 |  |  |  | 0 | 7 | 0 | 0 | 0 | 7 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | O&M costs are typically forecasted based on historical expenditures. However, during the 2024 GRC application, no historical data was available for this project. While forecasted and authorized capital expenditures exist, the associated O&M costs were not initially projected, as no O&M spending was anticipated at the time of the 2024 GRC application. These costs are directly linked to the units worked on through capital charges, which ultimately drove the need for O&M activities. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The O&M activities support the capital workpaper included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.545 in the 2023 WMP filing. Overhead Transmission Fire Hardening is replacing select existing wood poles with new steel poles and replacing aging conductor with new high-strength conductor to fire harden the electric transmission system. These pole and conductor replacements are part of an overall effort to help improve the reliability and integrity of the electric transmission system and to mitigate future potential fire risk. This project will improve the electric transmission system performance during extreme weather conditions such as Santa Ana wind events. When these transmission poles are replaced, the distribution facilities on the pole will need to be replaced or relocated onto the new pole. | SDG&E-13-2R-E JTW-127 to JTW-128 CWP 141400
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Assistance Programs | Tier 2 | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 1252999.9992 | 1290999.9996 | 1329999.9996 | 1369999.9992 | 1252999.9992 | -1252999.9992 | -1290999.9996 | -1329999.9996 | -1369999.9992 | -1252999.9992 | -100% | -100% | -100% | -100% | -100% | Rebates | 0 |  |  |  | 0 | 750 |  |  |  | 750 | -750 | 0 | 0 | 0 | -750 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The Resiliency Assistance Program is administered as a single, unified initiative that encompasses all customers residing within High Fire Threat Districts (HFTD), including both Tier 2 and Tier 3 areas. As part of its operational framework, the program does not currently distinguish participation based on tier classifications. Instead, all eligible customers within the designated HFTD regions are collectively included, and tracking or reporting between individual tiers is not performed. | Under (U) | Under (U) | Under (U) | Other | YES | The Resiliency Assistance Program is administered as a single, unified initiative that encompasses all customers residing within High Fire Threat Districts (HFTD), including both Tier 2 and Tier 3 areas. As part of its operational framework, the program does not currently distinguish participation based on tier classifications. Instead, all eligible customers within the designated HFTD regions are collectively included, and tracking or reporting between individual tiers is not performed. All costs and units are reported in Tier 3 tranche. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.467 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Assistance Programs | Tier 3 | No | On-going | Annual | 489447.7061 | 0 | 0 | 0 | 489447.7061 | 835999.9992 | 861000 | 886999.9992 | 913999.9992 | 835999.9992 | -346552.2931 | -861000 | -886999.9992 | -913999.9992 | -346552.2931 | -41.45% | -100% | -100% | -100% | -41.45% | Rebates | 232 |  |  |  | 232 | 500 |  |  |  | 500 | -268 | 0 | 0 | 0 | -268 | -53.6% | 0% | 0% | 0% | -53.6% | YES | NO | YES | N/A | This program has been designed and operated with the intent of providing backup power solutions to customers in high fire threat districts that have been historically identified as high risk for PSPS to mitigate the burden of electric outages. Initial projections based on historical PSPS data in 2021 allowed the program the opportunity to offer and provide backup power options to a large volume of customers in need. These projections were extended to annual forecasts though 2024 to estimate program costs based on the known trend at that time. In the following years, this program achieved significant adoption rates of customers participating in the program and achieving the anticipated result of making the SDG&E community more prepared. In addition to program success, the lower number of called PSPS events caused the amount of eligible customers to remain the same between 2021 and 2024, where it was originally estimated that the number of impacted customers would continue to grow. The program continues to evaluate customers in need to offer them the most effective backup power solution. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.467 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Grant Programs | Tier 2 | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 5586999.9996 | 5754000 | 5926999.9992 | 6105000 | 5586999.9996 | -5586999.9996 | -5754000 | -5926999.9992 | -6105000 | -5586999.9996 | -100% | -100% | -100% | -100% | -100% | Generators | 0 |  |  |  | 0 | 2000 |  |  |  | 2000 | -2000 | 0 | 0 | 0 | -2000 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | This program has been designed and operated with the intent of providing backup power solutions to customers in high fire threat districts that have been historically identified as high risk for PSPS to mitigate the burden of electric outages. Initial projections based on historical PSPS data in 2021 allowed the program the opportunity to offer and provide backup power options to a large volume of customers in need. These projections were extended to annual forecasts through 2024 to estimate program costs based on the known trend at that time. In the following years, this program achieved significant adoption rates of customers participating in the program and achieving the anticipated result of making the SDG&E community more prepared. In addition to program success, the lower number of called PSPS events caused the amount of eligible customers to remain the same between 2021 and 2024, where it was originally estimated that the number of impacted customers would continue to grow. The program continues to evaluate customers in need to offer them the most effective backup power solution. | The Resiliency Grant Program is administered as a single, unified initiative that encompasses all customers residing within High Fire Threat Districts (HFTD), including both Tier 2 and Tier 3 areas. As part of its operational framework, the program does not currently distinguish participation based on tier classifications. Instead, all eligible customers within the designated HFTD regions are collectively included, and tracking or reporting between individual tiers is not performed. | Under (U) | Under (U) | Under (U) | Other | YES | The Resiliency Grant Program is administered as a single, unified initiative that encompasses all customers residing within High Fire Threat Districts (HFTD), including both Tier 2 and Tier 3 areas. As part of its operational framework, the program does not currently distinguish participation based on tier classifications. Instead, all eligible customers within the designated HFTD regions are collectively included, and tracking or reporting between individual tiers is not performed. All costs and units are reported in Tier 3 tranche. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.466 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Grant Programs | Tier 3 | No | On-going | Annual | 979765.7838 | 0 | 0 | 0 | 979765.7838 | 3036000 | 3126999.9996 | 3219999.9996 | 3316999.9992 | 3036000 | -2056234.2162 | -3126999.9996 | -3219999.9996 | -3316999.9992 | -2056234.2162 | -67.73% | -100% | -100% | -100% | -67.73% | Generators | 158 |  |  |  | 158 | 1000 |  |  |  | 1000 | -842 | 0 | 0 | 0 | -842 | -84.2% | 0% | 0% | 0% | -84.2% | YES | NO | YES | N/A | This program has been designed and operated with the intent of providing backup power solutions to customers in high fire threat districts that have been historically identified as high risk for PSPS to mitigate the burden of electric outages. Initial projections based on historical PSPS data in 2021 allowed the program the opportunity to offer and provide backup power options to a large volume of customers in need. These projections were extended to annual forecasts through 2024 to estimate program costs based on the known trend at that time. In the following years, this program achieved significant adoption rates of customers participating in the program and achieving the anticipated result of making the SDG&E community more prepared. In addition to program success, the lower number of called PSPS events caused the amount of eligible customers to remain the same between 2021 and 2024, where it was originally estimated that the number of impacted customers would continue to grow. The program continues to evaluate customers in need to offer them the most effective backup power solution. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.466 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Standby Power Programs | Tier 3 | No | On-going | Annual | 5206457.297 | 0 | 0 | 0 | 5206457.297 | 11820000 | 12174000 | 12538999.9992 | 12915000 | 11820000 | -6613542.703 | -12174000 | -12538999.9992 | -12915000 | -6613542.703 | -55.95% | -100% | -100% | -100% | -55.95% | Generators | 54 |  |  |  | 54 | 412 |  |  |  | 412 | -358 | 0 | 0 | 0 | -358 | -86.89% | 0% | 0% | 0% | -86.89% | YES | YES | YES | This program has been designed and operated with the intent of providing backup power solutions to customers in high fire threat districts that have been historically identified as high risk for PSPS to mitigate the burden of electric outages. Initial projections based on historical PSPS data in 2021 allowed the program the opportunity to offer and provide backup power options to a large volume of customers in need. These projections were extended to annual forecasts through 2024 to estimate program costs based on the known trend at that time. In the following years, this program achieved significant adoption rates of customers participating in the program and achieving the anticipated result of making the SDG&E community more prepared. In addition to program success, the lower number of called PSPS events caused the amount of eligible customers to remain the same between 2021 and 2024, where it was originally estimated that the number of impacted customers would continue to grow. The program continues to evaluate customers in need to offer them the most effective backup power solution. | This program has been designed and operated with the intent of providing backup power solutions to customers in high fire threat districts that have been historically identified as high risk for PSPS to mitigate the burden of electric outages. Initial projections based on historical PSPS data in 2021 allowed the program the opportunity to offer and provide backup power options to a large volume of customers in need. These projections were extended to annual forecasts through 2024 to estimate program costs based on the known trend at that time. In the following years, this program achieved significant adoption rates of customers participating in the program and achieving the anticipated result of making the SDG&E community more prepared. In addition to program success, the lower number of called PSPS events caused the amount of eligible customers to remain the same between 2021 and 2024, where it was originally estimated that the number of impacted customers would continue to grow. The program continues to evaluate customers in need to offer them the most effective backup power solution. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.468 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Strategic Pole Replacement Program (HFTD) | HFTD Tiers 2 & 3 | No | On-going | Annual | 151220.8685 | 0 | 0 | 0 | 151220.8685 | 0 | 0 | 0 | 0 | 0 | 151220.8685 | 0 | 0 | 0 | 151220.8685 | 100% | 0% | 0% | 0% | 100% | Poles | 40 |  |  |  | 40 | 0 |  |  |  | 0 | 40 | 0 | 0 | 0 | 40 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | O&M costs are typically forecasted based on historical expenditures. However, during the 2024 GRC application, no historical data was available for this project. While forecasted and authorized capital expenditures exist, the associated O&M costs were not initially projected, as no O&M spending was anticipated at the time of the 2024 GRC application. These costs are directly linked to the units worked on through capital charges, which ultimately drove the need for O&M activities. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The O&M activities support the capital workpaper included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1189 in the 2023 WMP filing. The purpose of this project is to target high risk poles located throughout SDG&E service territory for replacement. This will continue SDG&E's efforts in hardening the system within the HFTD. Examples of poles this program will focus on will include but not be limited to, gas-treated poles (may be known as Cellon treatment), steel reinforced and poles that are set in concrete. These identified poles are also nearing the end of their useful life and are known to have a higher failure potential than average. | SDG&E-13-2R-E JTW-135 to JTW-137 CWP 222420
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 2 | No | On-going | Annual | 347769.5822 | 0 | 0 | 0 | 347769.5822 | 1234999.9992 | 1272000 | 1309999.9992 | 1348999.9992 | 1234999.9992 | -887230.417 | -1272000 | -1309999.9992 | -1348999.9992 | -887230.417 | -71.84% | -100% | -100% | -100% | -71.84% | Miles undergrounded (Capital) | 26.32 |  |  |  | 26.32 | 13 |  |  |  | 13 | 13.32 | 0 | 0 | 0 | 13.32 | 102.5% | 0% | 0% | 0% | 102.5% | YES | NO | YES | N/A | Number of completed units were based on target of 125 miles for the year. The draft GRC decision was issued in late October and the final decision in late December, which was too late in the year to adjust the workplan. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.473 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 3 | No | On-going | Annual | 1134151.1881 | 0 | 0 | 0 | 1134151.1881 | 2100999.9996 | 2163999.9996 | 2229000 | 2295000 | 2100999.9996 | -966848.8115 | -2163999.9996 | -2229000 | -2295000 | -966848.8115 | -46.02% | -100% | -100% | -100% | -46.02% | Miles undergrounded (Capital) | 85.68 |  |  |  | 85.68 | 22 |  |  |  | 22 | 63.68 | 0 | 0 | 0 | 63.68 | 289.5% | 0% | 0% | 0% | 289.5% | YES | NO | YES | N/A | Number of completed units were based on target of 125 miles for the year. The draft GRC decision was issued in late October and the final decision in late December, which was too late in the year to adjust the workplan. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.473 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Transmission System Inspection | None | No | On-going | Annual | 5645 | 0 | 0 | 0 | 5645 | 0 | 0 | 0 | 0 | 0 | 5645 | 0 | 0 | 0 | 5645 | 100% | 0% | 0% | 0% | 100% | Inspections | 2940 |  |  |  | 2940 | 0 |  |  |  | 0 | 2940 | 0 | 0 | 0 | 2940 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | O&M costs are typically forecasted based on historical expenditures. However, during the 2024 GRC application, no historical data was available for this project. While forecasted and authorized capital expenditures exist, the associated O&M costs were not initially projected, as no O&M spending was anticipated at the time of the 2024 GRC application. These costs are directly linked to the units worked on through capital charges, which ultimately drove the need for O&M activities. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The O&M activities support the capital workpaper included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.479 in the 2023 WMP filing. To meet SDG&E's obligation to serve by providing funding for the Corrective Maintenance Program (CMP) in areas designated as HFTD. To meet SDGE’s obligation to serve and the safety requirements promulgated by CPUC G .O 95, A.B. 1890, A.B. 1017, etc., this project provides funds for several purposes, such as: 1. To maintain and restore transmission facilities. 2. To repair the system in the vent of disaster such as storm or fire 3. To provide funding for a pole restoration program for in-service transmission wood poles. 4. To provide funding for annual NERC and Tie Lines Assessments (TLA). | SDG&E-13-2R-E JTW-140 to JTW-141 CWP 201270
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal GRID DESIGN & SYSTEM HARDENING |  |  |  | Yes |  |  | 15799416.1904 | 0 | 0 | 0 | 15799416.1904 | 29006999.9916 | 29876999.9952 | 30772999.9908 | 31695999.9912 | 29006999.9916 | -13207583.8012 | -29876999.9952 | -30772999.9908 | -31695999.9912 | -13207583.8012 | -45.53% | -100% | -100% | -100% | -45.53% | [21 empty] | YES | YES | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Non-HFTD | No | On-going | Annual | 0.49266 | 0 | 0 | 0 | 0.49266 | 342000 | 351999.9996 | 363000 | 373999.9992 | 342000 | -341999.5073 | -351999.9996 | -363000 | -373999.9992 | -341999.5073 | -100% | -100% | -100% | -100% | -100% | Leased helicopters | 0 |  |  |  | 0 | 2 |  |  |  | 2 | -2 | 0 | 0 | 0 | -2 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The Aviation Firefighting Program operates as a comprehensive, territory-wide initiative that primarily focuses on High Fire Threat District (HFTD) areas while remaining adaptable to provide aerial firefighting support wherever necessary within the service territory. Rather than being allocated to specific regions or tracked separately, the program deploys resources based on situational needs and fire response priorities. Its costs and associated units are not separately monitored across different tranches, as the program serves the entire service territory holistically, ensuring effective and timely aerial firefighting support wherever required. All units are reported within the Tier 3 tranche. | Under (U) | Under (U) | Under (U) | Other | YES | The Aviation Firefighting Program operates as a comprehensive, territory-wide initiative that primarily focuses on High Fire Threat District (HFTD) areas while remaining adaptable to provide aerial firefighting support wherever necessary within the service territory. Rather than being allocated to specific regions or tracked separately, the program deploys resources based on situational needs and fire response priorities. Its costs and associated units are not separately monitored across different tranches, as the program serves the entire service territory holistically, ensuring effective and timely aerial firefighting support wherever required. All costs and units are reported within the Tier 3 tranche. | This workpaper was included in the Grid Operations and Protocols GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.557 in the 2023 WMP filing. SDG&E Grid Operations & Protocols O&M costs account for the aviation firefighting program and wildfire infrastructure protection teams. SDG&E’s grid operations and protocols activities consist of mitigations that reduce risk through changing the way SDG&E operates during periods of elevated and extreme wildfire risk. This includes the disabling of reclosing in the HFTD, the enabling of fast recloser settings, restricting work in the HFTD during extreme fire potential and Red Flag Warnings, and sending contract fire resources into the field during elevated days in the HFTD. These operational decisions strive to reduce ignitions on the electric system . Also included within SDG&E’s grid operations and protocols is the aviation firefighting program . Specifically, Firehawk and Bell 412 helicopters are available to be used by CalFire to respond to active fires. Operations and maintenance on new helicopters will begin in 2022. Additional costs to support the aviation firefighting program include leases for an aviation hanger and training facility for the helicopters. Annual hangar lease expected to begin in October 2021 with 10 months lease in 2022 . Annual facility maintenance costs are also accounted for within this workpaper. SDG&E's wildfire infrastructure protection teams include contracting teams of qualified firefighters that join electric crews to assist in prevention and mitigation of ignitions. | SDG&E-13-2R-E JTW-73 to JTW-76 WP 1WM006.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 2 | No | On-going | Annual | -0.08764 | 0 | 0 | 0 | -0.08764 | 4746999.9996 | 4888999.9992 | 5035999.9992 | 5187000 | 4746999.9996 | -4747000.0872 | -4888999.9992 | -5035999.9992 | -5187000 | -4747000.0872 | -100% | -100% | -100% | -100% | -100% | Leased helicopters | 0 |  |  |  | 0 | 2 |  |  |  | 2 | -2 | 0 | 0 | 0 | -2 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | The aviation firefighting program's costs are not separately monitored across different tranches, as the program serves the entire service territory holistically, ensuring effective and timely aerial firefighting support wherever required. All costs are reported within the Tier 3 tranche. While the 2021 base year costs were correctly allocated at 63% to the Wildfire Mitigation Plan (WMP), the 2024 forecast adjustments reflect an incorrect allocation of 85% to WMP. Additionally, although the number of firefighting missions increased, fewer extended engagements led to a reduction in total flight hours and associated costs. | The Aviation Firefighting Program operates as a comprehensive, territory-wide initiative that primarily focuses on High Fire Threat District (HFTD) areas while remaining adaptable to provide aerial firefighting support wherever necessary within the service territory. Rather than being allocated to specific regions or tracked separately, the program deploys resources based on situational needs and fire response priorities. Its costs and associated units are not separately monitored across different tranches, as the program serves the entire service territory holistically, ensuring effective and timely aerial firefighting support wherever required. All units are reported within the Tier 3 tranche. | Under (U) | Under (U) | Under (U) | Other | YES | The Aviation Firefighting Program operates as a comprehensive, territory-wide initiative that primarily focuses on High Fire Threat District (HFTD) areas while remaining adaptable to provide aerial firefighting support wherever necessary within the service territory. Rather than being allocated to specific regions or tracked separately, the program deploys resources based on situational needs and fire response priorities. Its costs and associated units are not separately monitored across different tranches, as the program serves the entire service territory holistically, ensuring effective and timely aerial firefighting support wherever required. All costs and units are reported within the Tier 3 tranche. | This workpaper was included in the Grid Operations and Protocols GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.557 in the 2023 WMP filing. SDG&E Grid Operations & Protocols O&M costs account for the aviation firefighting program and wildfire infrastructure protection teams. SDG&E’s grid operations and protocols activities consist of mitigations that reduce risk through changing the way SDG&E operates during periods of elevated and extreme wildfire risk. This includes the disabling of reclosing in the HFTD, the enabling of fast recloser settings, restricting work in the HFTD during extreme fire potential and Red Flag Warnings, and sending contract fire resources into the field during elevated days in the HFTD. These operational decisions strive to reduce ignitions on the electric system . Also included within SDG&E’s grid operations and protocols is the aviation firefighting program . Specifically, Firehawk and Bell 412 helicopters are available to be used by CalFire to respond to active fires. Operations and maintenance on new helicopters will begin in 2022. Additional costs to support the aviation firefighting program include leases for an aviation hanger and training facility for the helicopters. Annual hangar lease expected to begin in October 2021 with 10 months lease in 2022 . Annual facility maintenance costs are also accounted for within this workpaper. SDG&E's wildfire infrastructure protection teams include contracting teams of qualified firefighters that join electric crews to assist in prevention and mitigation of ignitions. | SDG&E-13-2R-E JTW-73 to JTW-76 WP 1WM006.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 3 | No | On-going | Annual | 7665013.6849 | 0 | 0 | 0 | 7665013.6849 | 8049999.9996 | 8292000 | 8539999.9992 | 8796000 | 8049999.9996 | -384986.3147 | -8292000 | -8539999.9992 | -8796000 | -384986.3147 | -4.782% | -100% | -100% | -100% | -4.782% | Leased helicopters | 2 |  |  |  | 2 | 2 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Operations and Protocols GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.557 in the 2023 WMP filing. SDG&E Grid Operations & Protocols O&M costs account for the aviation firefighting program and wildfire infrastructure protection teams. SDG&E’s grid operations and protocols activities consist of mitigations that reduce risk through changing the way SDG&E operates during periods of elevated and extreme wildfire risk. This includes the disabling of reclosing in the HFTD, the enabling of fast recloser settings, restricting work in the HFTD during extreme fire potential and Red Flag Warnings, and sending contract fire resources into the field during elevated days in the HFTD. These operational decisions strive to reduce ignitions on the electric system . Also included within SDG&E’s grid operations and protocols is the aviation firefighting program . Specifically, Firehawk and Bell 412 helicopters are available to be used by CalFire to respond to active fires. Operations and maintenance on new helicopters will begin in 2022. Additional costs to support the aviation firefighting program include leases for an aviation hanger and training facility for the helicopters. Annual hangar lease expected to begin in October 2021 with 10 months lease in 2022 . Annual facility maintenance costs are also accounted for within this workpaper. SDG&E's wildfire infrastructure protection teams include contracting teams of qualified firefighters that join electric crews to assist in prevention and mitigation of ignitions. | SDG&E-13-2R-E JTW-73 to JTW-76 WP 1WM006.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Wildfire Infrastructure Protection Teams | Tier 2 | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 1095999.9996 | 1128999.9996 | 1162999.9992 | 1197999.9996 | 1095999.9996 | -1095999.9996 | -1128999.9996 | -1162999.9992 | -1197999.9996 | -1095999.9996 | -100% | -100% | -100% | -100% | -100% | Qualified firefighters collaborate with electric crews to support prevention and ignition mitigation efforts. Due to the diverse range of activities within this category, establishing a single unit of measurement is not feasible. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | As these resources provide mitigation support under fire coordination and respond dynamically to evolving threats, their deployment is based on real-time crew support needs rather than predetermined geographic allocations. Consequently, program costs are not tracked separately by tier, as the initiative operates holistically across the entire High Fire Threat Districts (HFTD) to ensure effective and timely wildfire mitigation wherever necessary. All costs are reported within the Tier 3 tranche. | This workpaper was included in the Grid Operations and Protocols GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.514 in the 2023 WMP filing. SDG&E Grid Operations & Protocols O&M costs account for the aviation firefighting program and wildfire infrastructure protection teams. SDG&E’s grid operations and protocols activities consist of mitigations that reduce risk through changing the way SDG&E operates during periods of elevated and extreme wildfire risk. This includes the disabling of reclosing in the HFTD, the enabling of fast recloser settings, restricting work in the HFTD during extreme fire potential and Red Flag Warnings, and sending contract fire resources into the field during elevated days in the HFTD. These operational decisions strive to reduce ignitions on the electric system . Also included within SDG&E’s grid operations and protocols is the aviation firefighting program . Specifically, Firehawk and Bell 412 helicopters are available to be used by CalFire to respond to active fires. Operations and maintenance on new helicopters will begin in 2022. Additional costs to support the aviation firefighting program include leases for an aviation hanger and training facility for the helicopters. Annual hangar lease expected to begin in October 2021 with 10 months lease in 2022 . Annual facility maintenance costs are also accounted for within this workpaper. SDG&E's wildfire infrastructure protection teams include contracting teams of qualified firefighters that join electric crews to assist in prevention and mitigation of ignitions. | SDG&E-13-2R-E JTW-73 to JTW-76 WP 1WM006.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Wildfire Infrastructure Protection Teams | Tier 3 | No | On-going | Annual | 4822242 | 0 | 0 | 0 | 4822242 | 2580999.9996 | 2658000 | 2737999.9992 | 2820000 | 2580999.9996 | 2241242.0004 | -2658000 | -2737999.9992 | -2820000 | 2241242.0004 | 86.84% | -100% | -100% | -100% | 86.84% | Qualified firefighters collaborate with electric crews to support prevention and ignition mitigation efforts. Due to the diverse range of activities within this category, establishing a single unit of measurement is not feasible. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Operations and Protocols GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.514 in the 2023 WMP filing. SDG&E Grid Operations & Protocols O&M costs account for the aviation firefighting program and wildfire infrastructure protection teams. SDG&E’s grid operations and protocols activities consist of mitigations that reduce risk through changing the way SDG&E operates during periods of elevated and extreme wildfire risk. This includes the disabling of reclosing in the HFTD, the enabling of fast recloser settings, restricting work in the HFTD during extreme fire potential and Red Flag Warnings, and sending contract fire resources into the field during elevated days in the HFTD. These operational decisions strive to reduce ignitions on the electric system . Also included within SDG&E’s grid operations and protocols is the aviation firefighting program . Specifically, Firehawk and Bell 412 helicopters are available to be used by CalFire to respond to active fires. Operations and maintenance on new helicopters will begin in 2022. Additional costs to support the aviation firefighting program include leases for an aviation hanger and training facility for the helicopters. Annual hangar lease expected to begin in October 2021 with 10 months lease in 2022 . Annual facility maintenance costs are also accounted for within this workpaper. SDG&E's wildfire infrastructure protection teams include contracting teams of qualified firefighters that join electric crews to assist in prevention and mitigation of ignitions. | SDG&E-13-2R-E JTW-73 to JTW-76 WP 1WM006.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal GRID OPERATIONS & OPERATING PROTOCOLS |  |  |  | Yes |  |  | 12487256.0899 | 0 | 0 | 0 | 12487256.0899 | 16815999.9984 | 17319999.9984 | 17839999.9968 | 18374999.9988 | 16815999.9984 | -4328743.9085 | -17319999.9984 | -17839999.9968 | -18374999.9988 | -4328743.9085 | -25.74% | -100% | -100% | -100% | -25.74% | [21 empty] | YES | YES | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | RESOURCE ALLOCATION METHODOLOGY | Wildfire Involving SDG&E Equipment | Wildfire Mitigation Personnel | None | No | On-going | Annual | 2710499.6979 | 0 | 0 | 0 | 2710499.6979 | 8781999.9996 | 9045000 | 9315999.9996 | 9594999.9996 | 8781999.9996 | -6071500.3017 | -9045000 | -9315999.9996 | -9594999.9996 | -6071500.3017 | -69.14% | -100% | -100% | -100% | -69.14% | Activities include the development of the Wildfire Mitigation Plan, support regulatory and legislative activities related to wildfire mitigation. It also includes tracking and monitoring of Wildfire Mitigation program progress and metrics, leading the the utility wildfire mitigation maturity model, spearheads vision projects, promotes new methods to enhance fire safety, and explores advancements to drive further improvement and change. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The underspend is primarily due to the PSPS Department not being established, leading to approximately 10 fewer full-time equivalent employees (FTEs). Additionally, analytics-related costs were reassigned to the Risk Assessment & Mapping mitigation, which has incurred $1.9 million in costs exceeding the authorized amount. Lastly, the independent PSPS study that was planned did not occur. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Resource Allocation Methodology category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.523 in the 2023 WMP filing. 1WM007 Resource Allocation Methodology includes costs for WMP Mitigations: Asset Management O&M; Wildfire Mitigation Personnel and PSPS Mitigation Engineering Team. This WMP mitigation includes costs for the Wildfire Mitigation department (Cost Centers 2100-4089; 2100-4097). Resource Allocation includes costs for development of tools and models utilized for allocating funding for WMP programs (e.g., WINGS) to promote efficient and cost-effective wildfire mitigation efforts. SDG&E's Wildfire Mitigation department is also included in this workpaper. This department, which was formed in 2019, contains three departments. First, the Wildfire Mitigation Programs group which is involved with the various regulatory proceedings that address wildfire and de-energization as well as legislative and media inquiries. Second, the Wildfire Mitigation Plan Strategic group develops metrics, leads vision projects, promotes new ways to enhance fire safety, and explores advancements to further drive improvement and change including risk modeling capabilities. Third, the Wildfire Mitigation Plan Accountability group is responsible for monitoring fire-related metrics, tracking WMP activities, complying with reporting requirements, provide for governance specifications and procedures, and act in a lead capacity on audits of the WMP programs. | SDG&E-13-2R-E JTW-77 to JTW-80 WP 1WM007.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | RESOURCE ALLOCATION METHODOLOGY | Wildfire Involving SDG&E Equipment | Asset Management | None | No | On-going | Annual | 103507.3686 | 0 | 0 | 0 | 103507.3686 | 0 | 0 | 0 | 0 | 0 | 103507.3686 | 0 | 0 | 0 | 103507.3686 | 100% | 0% | 0% | 0% | 100% | Initiative that develops proactive asset replacement, inspection, and repair programs based on risk. Because there are multiple different types of units of measure in this program, it would not be accurate or consistent to identify one unit of measure. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Other | NO | The costs associated with this program are trailing expenses and are not anticipated to recur in future years. The program was originally planned for completion before 2024. | This workpaper was included in the Resource Allocation Methodology category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.523 in the 2023 WMP filing. 1WM007 Resource Allocation Methodology includes costs for WMP Mitigations: Asset Management O&M; Wildfire Mitigation Personnel and PSPS Mitigation Engineering Team. This WMP mitigation includes costs for the Wildfire Mitigation department (Cost Centers 2100-4089; 2100-4097). Resource Allocation includes costs for development of tools and models utilized for allocating funding for WMP programs (e.g., WINGS) to promote efficient and cost-effective wildfire mitigation efforts. SDG&E's Wildfire Mitigation department is also included in this workpaper. This department, which was formed in 2019, contains three departments. First, the Wildfire Mitigation Programs group which is involved with the various regulatory proceedings that address wildfire and de-energization as well as legislative and media inquiries. Second, the Wildfire Mitigation Plan Strategic group develops metrics, leads vision projects, promotes new ways to enhance fire safety, and explores advancements to further drive improvement and change including risk modeling capabilities. Third, the Wildfire Mitigation Plan Accountability group is responsible for monitoring fire-related metrics, tracking WMP activities, complying with reporting requirements, provide for governance specifications and procedures, and act in a lead capacity on audits of the WMP programs. | SDG&E-13-2R-E JTW-77 to JTW-80 WP 1WM007.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal RESOURCE ALLOCATION METHODOLOGY |  |  |  | Yes |  |  | 2814007.0665 | 0 | 0 | 0 | 2814007.0665 | 8781999.9996 | 9045000 | 9315999.9996 | 9594999.9996 | 8781999.9996 | -5967992.9331 | -9045000 | -9315999.9996 | -9594999.9996 | -5967992.9331 | -67.96% | -100% | -100% | -100% | -67.96% | [21 empty] | YES | YES | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | RISK ASSESSMENT & MAPPING | Wildfire Involving SDG&E Equipment | Risk Assessment & Mapping | N/A | No | On-going | Annual | 4684549.6967 | 0 | 0 | 0 | 4684549.6967 | 2754999.9996 | 2838000 | 2922999.9996 | 3010999.9992 | 2754999.9996 | 1929549.6971 | -2838000 | -2922999.9996 | -3010999.9992 | 1929549.6971 | 70.04% | -100% | -100% | -100% | 70.04% | Activities include the development of WiNGS Planning, which enables risk assessment and prioritization of distribution grid hardening based on both an assessment of SDG&E’s overall system risk and the risk of specific circuit segments and WiNGS Ops model to assess wildfire and PSPS risk and support operational decision making. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Risk Assessment & Mapping category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.442 in the 2023 WMP filing. Risk Assessment & Mapping includes costs for specific risk modeling tools . SDG&E has utilitized its Wildfire Risk Reduction Model (WRRM) and WRRM-Operational System (WRRM-Ops) which continue to help SDG&E understand the wildfire risk from electric grid assets and fire propagation. While WRRM and WRRM-Ops continue to play a critical role in understanding the fire risk, SDG&E recognized a need for a model with the capability to analyze circuit segments for risk of wildfire and PSPS impacts, as well as calculate Risk Spend Efficiency scores for mitigation initiatives . To meet that need, SDG&E developed a new model in 2020 named Wildfire Next Generation System (WiNGS). While it is in the first year of use, WiNGS is expected to help prioritize SDG&E’s grid hardening mitigations in the coming years. SDG&E has remained committed to the ongoing development and implementation of its wildfire risk modeling through joint collaboration with Energy Safety, other IOUs, and contractors and continues to refine a primarily automated risk assessment and mapping methodology. | SDG&E-13-2R-E JTW-80 to JTW-83 WP 1WM007.001
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal RISK ASSESSMENT & MAPPING |  |  |  | Yes |  |  | 4684549.6967 | 0 | 0 | 0 | 4684549.6967 | 2754999.9996 | 2838000 | 2922999.9996 | 3010999.9992 | 2754999.9996 | 1929549.6971 | -2838000 | -2922999.9996 | -3010999.9992 | 1929549.6971 | 70.04% | -100% | -100% | -100% | 70.04% | [21 empty] | YES | NO | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SITUATIONAL AWARENESS AND FORECASTING | Incident Involving an Employee | Wildfire Smoke Particulates | N/A | No | On-going | Annual | 44991 | 0 | 0 | 0 | 44991 | 114000 | 117000 | 120999.9996 | 124999.9992 | 114000 | -69009 | -117000 | -120999.9996 | -124999.9992 | -69009 | -60.53% | -100% | -100% | -100% | -60.53% | Particulate smoke sensors maintained | 16 |  |  |  | 16 | 40 |  |  |  | 40 | -24 | 0 | 0 | 0 | -24 | -60% | 0% | 0% | 0% | -60% | YES | NO | YES | N/A | The estimated number of smoke sensors maintained, as submitted in the GRC application, was erroneously overstated at 40 sensors. Maintaining 16 sensors per month, totaling 192 sensor maintenance actions annually (16 sensors × 12 months), aligns with the figures reported in SDG&E's WMP. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Situational Awareness & Forecasting category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1431 in the 2023 WMP filing. Weather has a significant impact on utility operations. SDG&E develops and implements utility-specific meteorological technology to anticipate, prepare for, respond to, and recover from severe weather and wildfire events. Situational awareness tools are used to inform system planning, emergency operations, and the safe implementation of PSPS. Situational Awareness and Forecasting includes costs for SDG&E Fire Coordination, Meteorology, and Wildfire Resilience. | SDG&E-13-2R-E JTW-44 to JTW-48 WP 1WM002.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SITUATIONAL AWARENESS AND FORECASTING | Wildfire Involving SDG&E Equipment | Fire Science and Climate Adaptation Department | N/A | No | On-going | Annual | 5486441.7474 | 0 | 0 | 0 | 5486441.7474 | 4296000 | 4425000 | 4557000 | 4692999.9996 | 4296000 | 1190441.7474 | -4425000 | -4557000 | -4692999.9996 | 1190441.7474 | 27.71% | -100% | -100% | -100% | 27.71% | Due to the diverse and evolving nature of the Fire Science & Climate Adaptation Department’s work, establishing a single, comparable unit of measurement is not feasible. The department’s initiatives span a range of activities, including weather monitoring, fire forecasting, and PSPS situational awareness tools. These efforts vary significantly based on wildfire risk levels, operational demands, and environmental conditions, making it impractical to quantify them under a standardized metric. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Situational Awareness & Forecasting category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.450 in the 2023 WMP filing. Weather has a significant impact on utility operations. SDG&E develops and implements utility-specific meteorological technology to anticipate, prepare for, respond to, and recover from severe weather and wildfire events. Situational awareness tools are used to inform system planning, emergency operations, and the safe implementation of PSPS. Situational Awareness and Forecasting includes costs for SDG&E Fire Coordination, Meteorology, and Wildfire Resilience. | SDG&E-13-2R-E JTW-44 to JTW-48 WP 1WM002.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal SITUATIONAL AWARENESS AND FORECASTING |  |  |  | Yes |  |  | 5531432.7474 | 0 | 0 | 0 | 5531432.7474 | 4410000 | 4542000 | 4677999.9996 | 4817999.9988 | 4410000 | 1121432.7474 | -4542000 | -4677999.9996 | -4817999.9988 | 1121432.7474 | 25.43% | -100% | -100% | -100% | 25.43% | [21 empty] | YES | NO | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | Mylar Balloon Alternative | N/A | No | On-going | Annual | 1728 | 0 | 0 | 0 | 1728 | 97999.9992 | 100999.9992 | 103999.9992 | 106999.9992 | 97999.9992 | -96271.9992 | -100999.9992 | -103999.9992 | -106999.9992 | -96271.9992 | -98.24% | -100% | -100% | -100% | -98.24% | Program to develop a non-conductive balloon that will not cause an electrical fault when it comes in contact with overhead distribution power lines. One unit of measure would not accurately represent the program. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | This workpaper was included in the Stakeholder Cooperation & Community Engagement category within the Wildfire Mitigation and Vegetation Management witness area. Engagement and cooperation among all wildfire stakeholders, including the public, are extremely important to SDG&E. SDG&E partners with utility customers, elected officials, nonprofit support organizations, first responders and all other public safety and community partners. Each stakeholder group plays a unique and important role in achieving wildfire prevention and mitigation in SDG&E’s service territory. SDG&E provides an essential service, and it takes its role within the communities it serves very seriously. This is especially true during times of PSPS events, when communities depend on complete, accurate, and timely information for their well-being. | SDG&E-13-2R-E JTW-86 to JTW-93 WP 1WM008.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | PSPS Communication Practices | N/A | No | On-going | Annual | 7369719.7738 | 0 | 0 | 0 | 7369719.7738 | 11257999.9992 | 11595999.9996 | 11943999.9996 | 12303000 | 11257999.9992 | -3888280.2254 | -11595999.9996 | -11943999.9996 | -12303000 | -3888280.2254 | -34.54% | -100% | -100% | -100% | -34.54% | The diverse communication efforts in Wildfire and PSPS Marketing/Communications use varied tactics, each requiring different performance metrics. Because methods, variables, and reporting approaches differ across activities, no single unit of measurement can consistently quantify performance. | [20 empty] | YES | YES | NO | Program costs have decreased as we now have an established library of advertising campaign assets (creative), reducing the need for additional spending in this area. Additionally, our media buy—including advertising time and space across broadcast and print media—has declined over the past few years, further contributing to cost reductions. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Stakeholder Cooperation & Community Engagement category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.563 in the 2023 WMP filing. Engagement and cooperation among all wildfire stakeholders, including the public, are extremely important to SDG&E. SDG&E partners with utility customers, elected officials, nonprofit support organizations, first responders and all other public safety and community partners. Each stakeholder group plays a unique and important role in achieving wildfire prevention and mitigation in SDG&E’s service territory. SDG&E provides an essential service, and it takes its role within the communities it serves very seriously. This is especially true during times of PSPS events, when communities depend on complete, accurate, and timely information for their well-being. | SDG&E-13-2R-E JTW-86 to JTW-93 WP 1WM008.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | WMP AFN Customer Support | N/A | No | On-going | Annual | 1495517.8571 | 0 | 0 | 0 | 1495517.8571 | 1582999.9992 | 1629999.9996 | 1678999.9992 | 1728999.9996 | 1582999.9992 | -87482.1421 | -1629999.9996 | -1678999.9992 | -1728999.9996 | -87482.1421 | -5.526% | -100% | -100% | -100% | -5.526% | This workpaper includes several initiatives aimed at reducing impacts, improving coordination and Medical Baseline and Access and Functional Needs (AFN) customer awareness during fires or PSPS events. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Stakeholder Cooperation & Community Engagement category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.532 in the 2023 WMP filing. Engagement and cooperation among all wildfire stakeholders, including the public, are extremely important to SDG&E. SDG&E partners with utility customers, elected officials, nonprofit support organizations, first responders and all other public safety and community partners. Each stakeholder group plays a unique and important role in achieving wildfire prevention and mitigation in SDG&E’s service territory. SDG&E provides an essential service, and it takes its role within the communities it serves very seriously. This is especially true during times of PSPS events, when communities depend on complete, accurate, and timely information for their well-being. | SDG&E-13-2R-E JTW-86 to JTW-93 WP 1WM008.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | WMP Tribal Customer Support | N/A | No | On-going | Annual | 156488.3783 | 0 | 0 | 0 | 156488.3783 | 228000 | 234999.9996 | 241999.9992 | 249000 | 228000 | -71511.6217 | -234999.9996 | -241999.9992 | -249000 | -71511.6217 | -31.36% | -100% | -100% | -100% | -31.36% | This workpaper includes several initiatives aimed at reducing impacts, improving coordination and Tribal customer awareness during fires or PSPS events. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Stakeholder Cooperation & Community Engagement category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.527 in the 2023 WMP filing. Engagement and cooperation among all wildfire stakeholders, including the public, are extremely important to SDG&E. SDG&E partners with utility customers, elected officials, nonprofit support organizations, first responders and all other public safety and community partners. Each stakeholder group plays a unique and important role in achieving wildfire prevention and mitigation in SDG&E’s service territory. SDG&E provides an essential service, and it takes its role within the communities it serves very seriously. This is especially true during times of PSPS events, when communities depend on complete, accurate, and timely information for their well-being. | SDG&E-13-2R-E JTW-86 to JTW-93 WP 1WM008.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT |  |  |  | Yes |  |  | 9023454.0092 | 0 | 0 | 0 | 9023454.0092 | 13166999.9976 | 13561999.998 | 13968999.9972 | 14387999.9988 | 13166999.9976 | -4143545.9884 | -13561999.998 | -13968999.9972 | -14387999.9988 | -4143545.9884 | -31.47% | -100% | -100% | -100% | -31.47% | [21 empty] | YES | YES | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Fuels Management Program | Tier 2 | No | On-going | Annual | 623092.5703 | 0 | 0 | 0 | 623092.5703 | 1125000 | 1158999.9996 | 1194000 | 1230000 | 1125000 | -501907.4297 | -1158999.9996 | -1194000 | -1230000 | -501907.4297 | -44.61% | -100% | -100% | -100% | -44.61% | Structures cleared | 26 |  |  |  | 26 | 110 |  |  |  | 110 | -84 | 0 | 0 | 0 | -84 | -76.36% | 0% | 0% | 0% | -76.36% | YES | NO | YES | N/A | In 2024, as SDG&E awaited final decision in its GRC, it evaluated non-mandated, supple-mental WMP initiatives to find cost efficiencies and consider affordability measures, which included Fuels Management. SDG&E made the decision to pause this program in part know-ing that the remaining poles in the fuels management initiative would be addressed by other risk-reducing vegetation management measures such as pole brushing. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.497 in the 2023 WMP filing. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree clearances are mandated by CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety and mitigate ignition risk, especially in the HFTD. SDG&E’s vegetation management initiatives captured in this workpaper are: fuels management, pole brushing, and sustainability initiatives such as vegetation restoration efforts. | SDG&E-13-2R-E JTW-61 to JTW-68 WP 1WM005.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Fuels Management Program | Tier 3 | No | On-going | Annual | 2899776.7824 | 0 | 0 | 0 | 2899776.7824 | 4494000 | 4629000 | 4767999.9996 | 4911000 | 4494000 | -1594223.2176 | -4629000 | -4767999.9996 | -4911000 | -1594223.2176 | -35.47% | -100% | -100% | -100% | -35.47% | Structures cleared | 121 |  |  |  | 121 | 440 |  |  |  | 440 | -319 | 0 | 0 | 0 | -319 | -72.5% | 0% | 0% | 0% | -72.5% | YES | NO | YES | N/A | In 2024, as SDG&E awaited final decision in its GRC, it evaluated non-mandated, supple-mental WMP initiatives to find cost efficiencies and consider affordability measures, which included Fuels Management. SDG&E made the decision to pause this program in part know-ing that the remaining poles in the fuels management initiative would be addressed by other risk-reducing vegetation management measures such as pole brushing. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.497 in the 2023 WMP filing. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree clearances are mandated by CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety and mitigate ignition risk, especially in the HFTD. SDG&E’s vegetation management initiatives captured in this workpaper are: fuels management, pole brushing, and sustainability initiatives such as vegetation restoration efforts. | SDG&E-13-2R-E JTW-61 to JTW-68 WP 1WM005.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Pole Brushing | Non-HFTD | No | On-going | Annual | 804917.6987 | 0 | 0 | 0 | 804917.6987 | 679999.9992 | 699999.9996 | 720999.9996 | 742999.9992 | 679999.9992 | 124917.6995 | -699999.9996 | -720999.9996 | -742999.9992 | 124917.6995 | 18.37% | -100% | -100% | -100% | 18.37% | Poles brushed | 4126 |  |  |  | 4126 | 3460 |  |  |  | 3460 | 666 | 0 | 0 | 0 | 666 | 19.25% | 0% | 0% | 0% | 19.25% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.512 in the 2023 WMP filing. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree clearances are mandated by CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety and mitigate ignition risk, especially in the HFTD. SDG&E’s vegetation management initiatives captured in this workpaper are: fuels management, pole brushing, and sustainability initiatives such as vegetation restoration efforts. | SDG&E-13-2R-E JTW-61 to JTW-68 WP 1WM005.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Pole Brushing | Tier 2 | No | On-going | Annual | 3258492.2486 | 0 | 0 | 0 | 3258492.2486 | 3100999.9992 | 3193999.9992 | 3289999.9992 | 3387999.9996 | 3100999.9992 | 157492.2494 | -3193999.9992 | -3289999.9992 | -3387999.9996 | 157492.2494 | 5.079% | -100% | -100% | -100% | 5.079% | Poles brushed | 16703 |  |  |  | 16703 | 15788 |  |  |  | 15788 | 915 | 0 | 0 | 0 | 915 | 5.796% | 0% | 0% | 0% | 5.796% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.512 in the 2023 WMP filing. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree clearances are mandated by CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety and mitigate ignition risk, especially in the HFTD. SDG&E’s vegetation management initiatives captured in this workpaper are: fuels management, pole brushing, and sustainability initiatives such as vegetation restoration efforts. | SDG&E-13-2R-E JTW-61 to JTW-68 WP 1WM005.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Pole Brushing | Tier 3 | No | On-going | Annual | 3057166.7686 | 0 | 0 | 0 | 3057166.7686 | 2896999.9992 | 2983999.9992 | 3072999.9996 | 3165000 | 2896999.9992 | 160166.7694 | -2983999.9992 | -3072999.9996 | -3165000 | 160166.7694 | 5.529% | -100% | -100% | -100% | 5.529% | Poles brushed | 15671 |  |  |  | 15671 | 14752 |  |  |  | 14752 | 919 | 0 | 0 | 0 | 919 | 6.23% | 0% | 0% | 0% | 6.23% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.512 in the 2023 WMP filing. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree clearances are mandated by CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety and mitigate ignition risk, especially in the HFTD. SDG&E’s vegetation management initiatives captured in this workpaper are: fuels management, pole brushing, and sustainability initiatives such as vegetation restoration efforts. | SDG&E-13-2R-E JTW-61 to JTW-68 WP 1WM005.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Vegetation Restoration Initiative | N/A | No | On-going | Annual | 926075.5103 | 0 | 0 | 0 | 926075.5103 | 1071000 | 1102999.9992 | 1135999.9992 | 1170000 | 1071000 | -144924.4897 | -1102999.9992 | -1135999.9992 | -1170000 | -144924.4897 | -13.53% | -100% | -100% | -100% | -13.53% | Trees planted | 9401 |  |  |  | 9401 | 10000 |  |  |  | 10000 | -599 | 0 | 0 | 0 | -599 | -5.99% | 0% | 0% | 0% | -5.99% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Other | NO | The Vegetation Restoration Initiative addresses lower risks compared to other WMP programs, making it a potential area for funding reductions to prioritize higher-risk programs. This assessment is conducted annually based on the needs of the entire WMP portfolio. However, the company remains committed to its goal of planting 100,000 trees over a 10-year period, ensuring that the program is not entirely canceled. | This workpaper was included in the Vegetation Management & Inspections category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1325 in the 2023 WMP filing. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree clearances are mandated by CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety and mitigate ignition risk, especially in the HFTD. SDG&E’s vegetation management initiatives captured in this workpaper are: fuels management, pole brushing, and sustainability initiatives such as vegetation restoration efforts. | SDG&E-13-2R-E JTW-61 to JTW-68 WP 1WM005.000
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal VEGETATION MGMT & INSP |  |  |  | Yes |  |  | 11569521.5789 | 0 | 0 | 0 | 11569521.5789 | 13367999.9976 | 13768999.9968 | 14181999.9972 | 14606999.9988 | 13367999.9976 | -1798478.4187 | -13768999.9968 | -14181999.9972 | -14606999.9988 | -1798478.4187 | -13.45% | -100% | -100% | -100% | -13.45% | [21 empty] | YES | NO | [7 empty] | NO
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Electric Infrastructure Integrity | Tree Trimming (non-HFTD) | N/A | No | On-going | Annual | 35382139.6622 | 0 | 0 | 0 | 35382139.6622 | 19516999.9992 | 20103000 | 20706000 | 21327000 | 19516999.9992 | 15865139.663 | -20103000 | -20706000 | -21327000 | 15865139.663 | 81.29% | -100% | -100% | -100% | 81.29% | Trees Trimmed and Removed | 89060 |  |  |  | 89060 | 88702 |  |  |  | 88702 | 358 | 0 | 0 | 0 | 358 | 0.4036% | 0% | 0% | 0% | 0.4036% | YES | YES | NO | O&M expenditures recorded for this initiative include detailed inspections, off-cycle patrols, QA/QC of vegetation management, routine tree pruning and removal activities. The increase in O&M expenditures can be attributed to negotiated fixed-cost rates resulting from new service agreements between SDG&E and its contractors. Additionally, higher costs were attributed to an increase in the volume of work performed at the more expensive time and equipment (hourly) rate. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections - Tree Trimming Only category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.494 in the 2023 WMP filing. SDG&E's Vegetation Management Program is responsible for annually inspecting and maintaining an inventory of approximately 460,000 trees that have the potential to encroach within the minimum required compliance distance between vegetation and overhead powerlines. This includes pruning healthy trees growing into overhead powerlines as well as the pruning or removal of dead, dying, diseased or structurally unsound trees with the potential to fall into overhead lines. In the High Fire Threat District, SDG&E conducts a second patrol that follows approximately 6 months after the scheduled annual inspection to ensure trees remain compliant and additional tree hazards are observed. SDG&E increased its post prune clearance up to 25 feet on targeted species in the HFTD that have been identified to cause the majority of its tree related outages due to very fast growth, strike potential, and failure characteristics. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree trimming is a mandated activity pursuant to CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety, especially in the HFTD. SDG&E’s vegetation management initiatives included in this workpaper are: tracking and maintaining a database of inventory trees and poles, routine and enhanced patrolling, pruning and removing hazardous trees, and replacing unsafe trees with more situationally compatible species. | SDG&E-13-2R-E JTW-68 to JTW-73 WP 1WM005.001
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Enhanced Vegetation Management | Tier 2 | No | On-going | Annual | 2725052.1536 | 0 | 0 | 0 | 2725052.1536 | 7444999.9992 | 7668000 | 7897999.9992 | 8134999.9992 | 7444999.9992 | -4719947.8456 | -7668000 | -7897999.9992 | -8134999.9992 | -4719947.8456 | -63.4% | -100% | -100% | -100% | -63.4% | Trees trimmed | 8079 |  |  |  | 8079 | 7298 |  |  |  | 7298 | 781 | 0 | 0 | 0 | 781 | 10.7% | 0% | 0% | 0% | 10.7% | YES | YES | NO | The underspend was a result of reduced work volume for tree trimming and tree removal within the HFTD. Continued QA/QC activities following trimming and removal activities including a 100% audit of all completed work associated with the off-cycle HFTD patrols ensured no additional risk associated with reduction of work volume. | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections - Tree Trimming Only category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.501 in the 2023 WMP filing. SDG&E's Vegetation Management Program is responsible for annually inspecting and maintaining an inventory of approximately 460,000 trees that have the potential to encroach within the minimum required compliance distance between vegetation and overhead powerlines. This includes pruning healthy trees growing into overhead powerlines as well as the pruning or removal of dead, dying, diseased or structurally unsound trees with the potential to fall into overhead lines. In the High Fire Threat District, SDG&E conducts a second patrol that follows approximately 6 months after the scheduled annual inspection to ensure trees remain compliant and additional tree hazards are observed. SDG&E increased its post prune clearance up to 25 feet on targeted species in the HFTD that have been identified to cause the majority of its tree related outages due to very fast growth, strike potential, and failure characteristics. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree trimming is a mandated activity pursuant to CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety, especially in the HFTD. SDG&E’s vegetation management initiatives included in this workpaper are: tracking and maintaining a database of inventory trees and poles, routine and enhanced patrolling, pruning and removing hazardous trees, and replacing unsafe trees with more situationally compatible species. | SDG&E-13-2R-E JTW-68 to JTW-73 WP 1WM005.001
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Enhanced Vegetation Management | Tier 3 | No | On-going | Annual | 1261516.5768 | 0 | 0 | 0 | 1261516.5768 | 5637000 | 5805999.9996 | 5979999.9996 | 6159000 | 5637000 | -4375483.4232 | -5805999.9996 | -5979999.9996 | -6159000 | -4375483.4232 | -77.62% | -100% | -100% | -100% | -77.62% | Trees trimmed | 3709 |  |  |  | 3709 | 5526 |  |  |  | 5526 | -1817 | 0 | 0 | 0 | -1817 | -32.88% | 0% | 0% | 0% | -32.88% | YES | YES | YES | The underspend was a result of reduced work volume for tree trimming and tree removal within the HFTD. Continued QA/QC activities following trimming and removal activities including a 100% audit of all completed work associated with the off-cycle HFTD patrols ensured no additional risk associated with reduction of work volume. | The reduction in work units required for tree trimming and tree removal within the HFTD was the result of the reduced population of trees that required enhanced clearance. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections - Tree Trimming Only category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.501 in the 2023 WMP filing. SDG&E's Vegetation Management Program is responsible for annually inspecting and maintaining an inventory of approximately 460,000 trees that have the potential to encroach within the minimum required compliance distance between vegetation and overhead powerlines. This includes pruning healthy trees growing into overhead powerlines as well as the pruning or removal of dead, dying, diseased or structurally unsound trees with the potential to fall into overhead lines. In the High Fire Threat District, SDG&E conducts a second patrol that follows approximately 6 months after the scheduled annual inspection to ensure trees remain compliant and additional tree hazards are observed. SDG&E increased its post prune clearance up to 25 feet on targeted species in the HFTD that have been identified to cause the majority of its tree related outages due to very fast growth, strike potential, and failure characteristics. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree trimming is a mandated activity pursuant to CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety, especially in the HFTD. SDG&E’s vegetation management initiatives included in this workpaper are: tracking and maintaining a database of inventory trees and poles, routine and enhanced patrolling, pruning and removing hazardous trees, and replacing unsafe trees with more situationally compatible species. | SDG&E-13-2R-E JTW-68 to JTW-73 WP 1WM005.001
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Tree Trimming | Tier 2 | No | On-going | Annual | 21555057.2919 | 0 | 0 | 0 | 21555057.2919 | 18594000 | 19150999.9992 | 19725000 | 20316999.9996 | 18594000 | 2961057.2919 | -19150999.9992 | -19725000 | -20316999.9996 | 2961057.2919 | 15.92% | -100% | -100% | -100% | 15.92% | Trees Trimmed and Removed | 54256 |  |  |  | 54256 | 56857 |  |  |  | 56857 | -2601 | 0 | 0 | 0 | -2601 | -4.575% | 0% | 0% | 0% | -4.575% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections - Tree Trimming Only category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.494 in the 2023 WMP filing. SDG&E's Vegetation Management Program is responsible for annually inspecting and maintaining an inventory of approximately 460,000 trees that have the potential to encroach within the minimum required compliance distance between vegetation and overhead powerlines. This includes pruning healthy trees growing into overhead powerlines as well as the pruning or removal of dead, dying, diseased or structurally unsound trees with the potential to fall into overhead lines. In the High Fire Threat District, SDG&E conducts a second patrol that follows approximately 6 months after the scheduled annual inspection to ensure trees remain compliant and additional tree hazards are observed. SDG&E increased its post prune clearance up to 25 feet on targeted species in the HFTD that have been identified to cause the majority of its tree related outages due to very fast growth, strike potential, and failure characteristics. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree trimming is a mandated activity pursuant to CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety, especially in the HFTD. SDG&E’s vegetation management initiatives included in this workpaper are: tracking and maintaining a database of inventory trees and poles, routine and enhanced patrolling, pruning and removing hazardous trees, and replacing unsafe trees with more situationally compatible species. | SDG&E-13-2R-E JTW-68 to JTW-73 WP 1WM005.001
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Tree Trimming | Tier 3 | No | On-going | Annual | 15289883.8964 | 0 | 0 | 0 | 15289883.8964 | 15421999.9992 | 15885000 | 16362000 | 16852999.9992 | 15421999.9992 | -132116.1028 | -15885000 | -16362000 | -16852999.9992 | -132116.1028 | -0.8567% | -100% | -100% | -100% | -0.8567% | Trees Trimmed and Removed | 38486 |  |  |  | 38486 | 38985 |  |  |  | 38985 | -499 | 0 | 0 | 0 | -499 | -1.28% | 0% | 0% | 0% | -1.28% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Vegetation Management & Inspections - Tree Trimming Only category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.494 in the 2023 WMP filing. SDG&E's Vegetation Management Program is responsible for annually inspecting and maintaining an inventory of approximately 460,000 trees that have the potential to encroach within the minimum required compliance distance between vegetation and overhead powerlines. This includes pruning healthy trees growing into overhead powerlines as well as the pruning or removal of dead, dying, diseased or structurally unsound trees with the potential to fall into overhead lines. In the High Fire Threat District, SDG&E conducts a second patrol that follows approximately 6 months after the scheduled annual inspection to ensure trees remain compliant and additional tree hazards are observed. SDG&E increased its post prune clearance up to 25 feet on targeted species in the HFTD that have been identified to cause the majority of its tree related outages due to very fast growth, strike potential, and failure characteristics. Vegetation around electric distribution lines and equipment poses potential risks for safety, wildfire, compliance, and reliability. To address these risks, SDG&E developed and executes a robust and detailed schedule and scope for its vegetation inspection activities. While tree trimming is a mandated activity pursuant to CPUC G.O. 95, Rule 35, Public Resources Code 4293, and NERC FAC003-4, SDG&E’s program goes beyond these minimum requirements to further enhance safety, especially in the HFTD. SDG&E’s vegetation management initiatives included in this workpaper are: tracking and maintaining a database of inventory trees and poles, routine and enhanced patrolling, pruning and removing hazardous trees, and replacing unsafe trees with more situationally compatible species. | SDG&E-13-2R-E JTW-68 to JTW-73 WP 1WM005.001
O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal VEGETATION MGMT & INSP. - TREE TRIMMING ONLY |  |  |  | Yes |  |  | 76213649.5808 | 0 | 0 | 0 | 76213649.5808 | 66614999.9976 | 68612999.9988 | 70670999.9988 | 72790999.998 | 66614999.9976 | 9598649.5832 | -68612999.9988 | -70670999.9988 | -72790999.998 | 9598649.5832 | 14.41% | -100% | -100% | -100% | 14.41% | [21 empty] | YES | YES | [7 empty] | NO

## ESEV-B
SDG&E ENVIRONMENTAL SERVICES AND SAN ONOFRE NUCLEAR GENERATING STATION ("SONGS') O&M
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | ENVIRONMENTAL SERVICES AND SAN ONOFRE NUCLEAR GENERATING STATION ("SONGS') | ENVIRONMENTAL SERVICES AND SAN ONOFRE NUCLEAR GENERATING STATION ("SONGS') |  |  |  | Yes |  |  | 5240631.3565 | 0 | 0 | 0 | 5240631.3565 | 3157999.998 | 3204999.9984 | 3253999.998 | 3303999.9984 | 3157999.998 | 2082631.3585 | -3204999.9984 | -3253999.998 | -3303999.9984 | 2082631.3585 | 65.95% | -100% | -100% | -100% | 65.95%
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | EG -SONGS WKP_GRP_1 | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1142922.89 | 0 | 0 | 0 | 1142922.89 | 1575000 | 1575000 | 1575000 | 1575000 | 1575000 | -432077.11 | -1575000 | -1575000 | -1575000 | -432077.11 | -27.43% | -100% | -100% | -100% | -27.43% | This workpaper represents SDG&E's 20% share of SONGs marine mitigation workmans compensation costs. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal EG -SONGS WKP_GRP_1 |  |  |  | Yes |  |  | 1142922.89 | 0 | 0 | 0 | 1142922.89 | 1575000 | 1575000 | 1575000 | 1575000 | 1575000 | -432077.11 | -1575000 | -1575000 | -1575000 | -432077.11 | -27.43% | -100% | -100% | -100% | -27.43% | [21 empty] | YES | NO | [7 empty] | NO
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-AB32 FEES-ELECTRIC | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 652150 | 0 | 0 | 0 | 652150 | 472999.9992 | 486999.9996 | 501999.9996 | 516999.9996 | 472999.9992 | 179150.0008 | -486999.9996 | -501999.9996 | -516999.9996 | 179150.0008 | 37.88% | -100% | -100% | -100% | 37.88% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal RNERBA-AB32 FEES-ELECTRIC |  |  |  | Yes |  |  | 652150 | 0 | 0 | 0 | 652150 | 472999.9992 | 486999.9996 | 501999.9996 | 516999.9996 | 472999.9992 | 179150.0008 | -486999.9996 | -501999.9996 | -516999.9996 | 179150.0008 | 37.88% | -100% | -100% | -100% | 37.88% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-AB32 FEES-GAS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1367841 | 0 | 0 | 0 | 1367841 | 1029000 | 1059999.9996 | 1092000 | 1125000 | 1029000 | 338841 | -1059999.9996 | -1092000 | -1125000 | 338841 | 32.93% | -100% | -100% | -100% | 32.93% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal RNERBA-AB32 FEES-GAS |  |  |  | Yes |  |  | 1367841 | 0 | 0 | 0 | 1367841 | 1029000 | 1059999.9996 | 1092000 | 1125000 | 1029000 | 338841 | -1059999.9996 | -1092000 | -1125000 | 338841 | 32.93% | -100% | -100% | -100% | 32.93% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-LDAR | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2077717.4665 | 0 | 0 | 0 | 2077717.4665 | 66999.9996 | 69000 | 70999.9992 | 72999.9996 | 66999.9996 | 2010717.4669 | -69000 | -70999.9992 | -72999.9996 | 2010717.4669 | 3001% | -100% | -100% | -100% | 3001% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal RNERBA-LDAR |  |  |  | Yes |  |  | 2077717.4665 | 0 | 0 | 0 | 2077717.4665 | 66999.9996 | 69000 | 70999.9992 | 72999.9996 | 66999.9996 | 2010717.4669 | -69000 | -70999.9992 | -72999.9996 | 2010717.4669 | 3001% | -100% | -100% | -100% | 3001% | [21 empty] | NO | NO | [7 empty] | NO
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-MS4-ELECTRIC | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -100% | -100% | -100% | -100% | -100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal RNERBA-MS4-ELECTRIC |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -100% | -100% | -100% | -100% | -100% | [21 empty] | NO | NO | [7 empty] | YES
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-MS4-GAS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -100% | -100% | -100% | -100% | -100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal RNERBA-MS4-GAS |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -100% | -100% | -100% | -100% | -100% | [21 empty] | NO | NO | [7 empty] | YES
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-SUBPART W | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 0 | 0 | 0 | 0 | 0 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -100% | -100% | -100% | -100% | -100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | SubTotal RNERBA-SUBPART W |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -100% | -100% | -100% | -100% | -100% | [21 empty] | NO | NO | [7 empty] | YES

## GOTD-B
SDG&E GAS INTEGRITY MANAGEMENT PROGRAMS O&M
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | GAS INTEGRITY MANAGEMENT PROGRAMS | GAS INTEGRITY MANAGEMENT PROGRAMS |  |  |  | Yes |  |  | 32221613.1546 | 0 | 0 | 0 | 32221613.1546 | 10683000 | 11002999.9992 | 11332999.9992 | 11672999.9988 | 10683000 | 21538613.1546 | -11002999.9992 | -11332999.9992 | -11672999.9988 | 21538613.1546 | 201.6% | -100% | -100% | -100% | 201.6%
O&M | GAS INTEGRITY PROGRAMS | DIMP | Incident Related to the Medium Pressure System (Excluding Dig-in) | Distribution Integrity Management Program (DIMP) | Plastic - Main (VIPP) | No | On-going | Annual | 660744.1471 | 0 | 0 | 0 | 660744.1471 | 0 | 0 | 0 | 0 | 0 | 660744.1471 | 0 | 0 | 0 | 660744.1471 | 100% | 0% | 0% | 0% | 100% | Workpaper activity includes managing and developing programs/projects and activities to address risk (PAARs), risk analysis, data collection and management, database maintenance, and reporting. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | DIMP complies with 49 CFR 192, Subpart P - Gas Distribution Pipeline Integrity Management and includes threat identification, risk assessment, and various programs to minimize threats and integrity concerns to reduce risk of pipeline incidents. The 2024 VIPP cost variance is driven by expenditures incurred to manage this program. While the TY 2024 GRC Decision (D.24-12-074) authorized SDG&E to execute VIPP replacements, it did not fund the necessary O&M activities to complete this work. SDG&E uses its Quantitative Risk Assessment (QRA) results to inform the prioritization of DREAMS VIPP replacements and costs were necessarily incurred for 2024 VIPP replacement activities. Actual O&M costs will continue to be incurred at a level necessary to conduct the safe operation and oversight of the VIPP. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | DIMP activities and projects such as DREAMS, GIPP, SLIP, DRIP and other various activities in compliance with 49 CFR Part 192, Subpart P. | SDGE-09-R AK-TS-26 to AK-TS-32 WP 1TD002.000
O&M | GAS INTEGRITY PROGRAMS | SubTotal DIMP |  |  |  | Yes |  |  | 660744.1471 | 0 | 0 | 0 | 660744.1471 | 0 | 0 | 0 | 0 | 0 | 660744.1471 | 0 | 0 | 0 | 660744.1471 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | YES | [7 empty] | NO
O&M | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - HCA | No | On-going | Annual | 30929651.1047 | 0 | 0 | 0 | 30929651.1047 | 10149000 | 10452999.9996 | 10767000 | 11089999.9992 | 10149000 | 20780651.1047 | -10452999.9996 | -10767000 | -11089999.9992 | 20780651.1047 | 204.8% | -100% | -100% | -100% | 204.8% | Miles assessed | 10.56 |  |  |  | 10.56 | 7.6 |  |  |  | 7.6 | 2.96 | 0 | 0 | 0 | 2.96 | 38.95% | 0% | 0% | 0% | 38.95% | YES | YES | YES | TIMP complies with 49 CFR §192, Subpart O—Gas Transmission Pipeline Integrity Management, and includes activities such as threat identification and risk assessment, pipeline assessments, remediation, and other actions that minimize threats and integrity concerns to reduce risk of pipeline failure. The number of assessment projects vary year to year primarily based on the timing and intervals of prior assessments and compliance dates. TIMP assessments may span both HCA and non-HCA segments and these tranches should be viewed in aggregate. Non-HCA pipeline segments include those in Class 3 and 4 locations, as well as Moderate Consequence Areas (MCAs), which are required under expanded PHMSA requirements per 49 CFR § 192.710. The allocation between the tranches is calculated based on the number of the actual 2024 completed assessment mileage. Furthermore, integrity assessments remain variable based on external factors (e.g., risks and threats) and individual project costs will differ. The 2024 variance in expenditures is primarily due to the expansion of the ILI program, as necessitated by the changes resulting from GTSR Part 1 (84 FR 52180). In order to assess manufacturing threats newly classified as active under 49 CFR § 192.917(e), SDG&E inspected previously unpiggable pipelines through the application of ILI technology. | TIMP complies with 49 CFR §192, Subpart O—Gas Transmission Pipeline Integrity Management, and includes activities such as threat identification and risk assessment, pipeline assessments, remediation, and other actions that minimize threats and integrity concerns to reduce risk of pipeline failure. Assessments vary year to year based on prescribed compliance-driven assessment cycles. TIMP assessments may span both HCA and non-HCA segments and these tranches should be viewed in aggregate. The allocation between the tranches is calculated based on the number of the actual 2024 completed assessment mileage. Due to regulatory changes in 49 CFR § 192.917(e) that resulted from the publication of the GTSR Part 1 (84 FR 52180), newly active manufacturing threats necessitated ILI assessments not forecasted at the time of the TY 2024 GRC application. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | TIMP assessments, remediation, preventative & mitigative measures, and other activities in compliance with 49 CFR Part 192, Subpart O, as well as new requirements of 49 CFR § 192.710. | SDGE-09-R AK-TS-19 to AK-TS-26 WP 1TD001.000
O&M | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 631217.9028 | 0 | 0 | 0 | 631217.9028 | 534000 | 549999.9996 | 565999.9992 | 582999.9996 | 534000 | 97217.9028 | -549999.9996 | -565999.9992 | -582999.9996 | 97217.9028 | 18.21% | -100% | -100% | -100% | 18.21% | Miles assessed | 0.16 |  |  |  | 0.16 | 0.4 |  |  |  | 0.4 | -0.24 | 0 | 0 | 0 | -0.24 | -60% | 0% | 0% | 0% | -60% | YES | NO | YES | N/A | TIMP complies with 49 CFR §192, Subpart O—Gas Transmission Pipeline Integrity Management, and includes activities such as threat identification and risk assessment, pipeline assessments, remediation, and other actions that minimize threats and integrity concerns to reduce risk of pipeline failure. Assessments vary year to year based on prescribed compliance-driven assessment cycles. TIMP assessments may span both HCA and non-HCA segments and these tranches should be viewed in aggregate. Non-HCA pipeline segments include those in Class 3 and 4 locations, as well as Moderate Consequence Areas (MCAs), which are required under expanded PHMSA requirements per 49 CFR § 192.710. The allocation between the tranches is calculated based on the number of the actual 2024 completed assessment mileage. In 2024, most TIMP assessment activities during the year focused on High Consequence Area (HCA) pipeline segments. Based on risk evaluation and reassessment cycles, some of the non-HCA miles were deferred to future periods. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | TIMP assessments, remediation, preventative & mitigative measures, and other activities in compliance with 49 CFR Part 192, Subpart O, as well as new requirements of 49 CFR § 192.710. | SDGE-09-R AK-TS-19 to AK-TS-26 WP 1TD001.000
O&M | GAS INTEGRITY PROGRAMS | SubTotal TIMP |  |  |  | Yes |  |  | 31560869.0075 | 0 | 0 | 0 | 31560869.0075 | 10683000 | 11002999.9992 | 11332999.9992 | 11672999.9988 | 10683000 | 20877869.0075 | -11002999.9992 | -11332999.9992 | -11672999.9988 | 20877869.0075 | 195.4% | -100% | -100% | -100% | 195.4% | [21 empty] | YES | YES | [7 empty] | NO

## SEIN-B
SDG&E CORPORATE CENTER - INSURANCE O&M
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CORPORATE CENTER - INSURANCE | CORPORATE CENTER - INSURANCE |  |  |  | Yes |  |  | 196605335.5284 | 0 | 0 | 0 | 196605335.5284 | 233714999.9988 | 240726999.9984 | 247948999.998 | 255387999.9984 | 233714999.9988 | -37109664.4704 | -240726999.9984 | -247948999.998 | -255387999.9984 | -37109664.4704 | -15.88% | -100% | -100% | -100% | -15.88%
O&M | CORPORATE CENTER - INSURANCE | EXCESS WORKERS COMPENSATION INSURANCE - F925.1 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2903547.78 | 0 | 0 | 0 | 2903547.78 | 3756999.9996 | 3870000 | 3985999.9992 | 4105999.9992 | 3756999.9996 | -853452.2196 | -3870000 | -3985999.9992 | -4105999.9992 | -853452.2196 | -22.72% | -100% | -100% | -100% | -22.72% | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | SubTotal EXCESS WORKERS COMPENSATION INSURANCE - F925.1 |  |  |  | Yes |  |  | 2903547.78 | 0 | 0 | 0 | 2903547.78 | 3756999.9996 | 3870000 | 3985999.9992 | 4105999.9992 | 3756999.9996 | -853452.2196 | -3870000 | -3985999.9992 | -4105999.9992 | -853452.2196 | -22.72% | -100% | -100% | -100% | -22.72% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | RSECC EXCESS LIABILITY INSURANCE PLPD - F925.0 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 44457522.1392 | 0 | 0 | 0 | 44457522.1392 | 54132000 | 55755999.9996 | 57429000 | 59151999.9996 | 54132000 | -9674477.8608 | -55755999.9996 | -57429000 | -59151999.9996 | -9674477.8608 | -17.87% | -100% | -100% | -100% | -17.87% | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | SubTotal RSECC EXCESS LIABILITY INSURANCE PLPD - F925.0 |  |  |  | Yes |  |  | 44457522.1392 | 0 | 0 | 0 | 44457522.1392 | 54132000 | 55755999.9996 | 57429000 | 59151999.9996 | 54132000 | -9674477.8608 | -55755999.9996 | -57429000 | -59151999.9996 | -9674477.8608 | -17.87% | -100% | -100% | -100% | -17.87% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | RSECC EXCESS LIABILITY INSURANCE PLPD - F925.5 WILDFIRE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 146668408.2192 | 0 | 0 | 0 | 146668408.2192 | 172696999.9992 | 177877999.9992 | 183213999.9996 | 188709999.9996 | 172696999.9992 | -26028591.78 | -177877999.9992 | -183213999.9996 | -188709999.9996 | -26028591.78 | -15.07% | -100% | -100% | -100% | -15.07% | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | SubTotal RSECC EXCESS LIABILITY INSURANCE PLPD - F925.5 WILDFIRE |  |  |  | Yes |  |  | 146668408.2192 | 0 | 0 | 0 | 146668408.2192 | 172696999.9992 | 177877999.9992 | 183213999.9996 | 188709999.9996 | 172696999.9992 | -26028591.78 | -177877999.9992 | -183213999.9996 | -188709999.9996 | -26028591.78 | -15.07% | -100% | -100% | -100% | -15.07% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | RSECC OTHER LIABILITY INSURANCE NON-NUCLEAR - F925.3 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2575857.39 | 0 | 0 | 0 | 2575857.39 | 3129000 | 3222999.9996 | 3319999.9992 | 3420000 | 3129000 | -553142.61 | -3222999.9996 | -3319999.9992 | -3420000 | -553142.61 | -17.68% | -100% | -100% | -100% | -17.68% | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - INSURANCE | SubTotal RSECC OTHER LIABILITY INSURANCE NON-NUCLEAR - F925.3 |  |  |  | Yes |  |  | 2575857.39 | 0 | 0 | 0 | 2575857.39 | 3129000 | 3222999.9996 | 3319999.9992 | 3420000 | 3129000 | -553142.61 | -3222999.9996 | -3319999.9992 | -3420000 | -553142.61 | -17.68% | -100% | -100% | -100% | -17.68% | [21 empty] | NO | NO | [7 empty] | NO

## AGPN-B
SDG&E CORPORATE CENTER - PENSION AND POSTRETIREMENT BENEFITS OTHER THAN PENSION O&M
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
O&M | CORPORATE CENTER - PENSION AND POSTRETIREMENT BENEFITS OTHER THAN PENSION | CORPORATE CENTER - PENSION AND POSTRETIREMENT BENEFITS OTHER THAN PENSION |  |  |  | Yes |  |  | 35147764.69 | 0 | 0 | 0 | 35147764.69 | 35274999.9984 | 36333000 | 37422999.9984 | 38545999.9992 | 35274999.9984 | -127235.3084 | -36333000 | -37422999.9984 | -38545999.9992 | -127235.3084 | -0.3607% | -100% | -100% | -100% | -0.3607%
O&M | CORPORATE CENTER - PENSION & PBOP | EMPLOYEE PBOP | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 220462 | 0 | 0 | 0 | 220462 | 346999.9992 | 357000 | 367999.9992 | 378999.9996 | 346999.9992 | -126537.9992 | -357000 | -367999.9992 | -378999.9996 | -126537.9992 | -36.47% | -100% | -100% | -100% | -36.47% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - PENSION & PBOP | SubTotal EMPLOYEE PBOP |  |  |  | Yes |  |  | 220462 | 0 | 0 | 0 | 220462 | 346999.9992 | 357000 | 367999.9992 | 378999.9996 | 346999.9992 | -126537.9992 | -357000 | -367999.9992 | -378999.9996 | -126537.9992 | -36.47% | -100% | -100% | -100% | -36.47% | [21 empty] | NO | NO | [7 empty] | NO
O&M | CORPORATE CENTER - PENSION & PBOP | EMPLOYEE PENSION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 34927302.69 | 0 | 0 | 0 | 34927302.69 | 34927999.9992 | 35976000 | 37054999.9992 | 38166999.9996 | 34927999.9992 | -697.3092 | -35976000 | -37054999.9992 | -38166999.9996 | -697.3092 | -0.001996% | -100% | -100% | -100% | -0.001996% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
O&M | CORPORATE CENTER - PENSION & PBOP | SubTotal EMPLOYEE PENSION |  |  |  | Yes |  |  | 34927302.69 | 0 | 0 | 0 | 34927302.69 | 34927999.9992 | 35976000 | 37054999.9992 | 38166999.9996 | 34927999.9992 | -697.3092 | -35976000 | -37054999.9992 | -38166999.9996 | -697.3092 | -0.001996% | -100% | -100% | -100% | -0.001996% | [21 empty] | NO | NO | [7 empty] | NO

## EOED-C
SDG&E ELECTRIC DISTRIBUTION Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | ELECTRIC DISTRIBUTION | ELECTRIC DISTRIBUTION |  |  |  | Yes |  |  | 337972025.7353 | 0 | 0 | 0 | 337972025.7353 | 431287997.16 | 444225996.96 | 457553997 | 471279996.72 | 431287997.16 | -93315971.4247 | -444225996.96 | -457553997 | -471279996.72 | -93315971.4247 | -21.64% | -100% | -100% | -100% | -21.64%
Capital | ELECTRIC DISTRIBUTION | 3 ROOTS TL6906,TL677,TL668 CUST RELO | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 140940.6567 | 0 | 0 | 0 | 140940.6567 | 999.96 | 999.96 | 999.96 | 999.96 | 999.96 | 139940.6967 | -999.96 | -999.96 | -999.96 | 139940.6967 | 13995% | -100% | -100% | -100% | 13995% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal 3 ROOTS TL6906,TL677,TL668 CUST RELO |  |  |  | Yes |  |  | 140940.6567 | 0 | 0 | 0 | 140940.6567 | 999.96 | 999.96 | 999.96 | 999.96 | 999.96 | 139940.6967 | -999.96 | -999.96 | -999.96 | 139940.6967 | 13995% | -100% | -100% | -100% | 13995% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CITY OF SAN DIEGO SURCHARGE PROG (20SD) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 7003586.7122 | 0 | 0 | 0 | 7003586.7122 | 23847999.96 | 24562999.92 | 25299999.96 | 26058999.96 | 23847999.96 | -16844413.2478 | -24562999.92 | -25299999.96 | -26058999.96 | -16844413.2478 | -70.63% | -100% | -100% | -100% | -70.63% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal CITY OF SAN DIEGO SURCHARGE PROG (20SD) |  |  |  | Yes |  |  | 7003586.7122 | 0 | 0 | 0 | 7003586.7122 | 23847999.96 | 24562999.92 | 25299999.96 | 26058999.96 | 23847999.96 | -16844413.2478 | -24562999.92 | -25299999.96 | -26058999.96 | -16844413.2478 | -70.63% | -100% | -100% | -100% | -70.63% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CONVERSION FROM OH TO UG RULE 20A | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3194267.6442 | 0 | 0 | 0 | 3194267.6442 | 19476999.96 | 20061000 | 20662999.92 | 21282999.96 | 19476999.96 | -16282732.3158 | -20061000 | -20662999.92 | -21282999.96 | -16282732.3158 | -83.6% | -100% | -100% | -100% | -83.6% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal CONVERSION FROM OH TO UG RULE 20A |  |  |  | Yes |  |  | 3194267.6442 | 0 | 0 | 0 | 3194267.6442 | 19476999.96 | 20061000 | 20662999.92 | 21282999.96 | 19476999.96 | -16282732.3158 | -20061000 | -20662999.92 | -21282999.96 | -16282732.3158 | -83.6% | -100% | -100% | -100% | -83.6% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CONVERSION FROM OH-UG RULE 20B NEW BUSIN | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 895502.6902 | 0 | 0 | 0 | 895502.6902 | 2139999.96 | 2203999.92 | 2269999.92 | 2337999.96 | 2139999.96 | -1244497.2698 | -2203999.92 | -2269999.92 | -2337999.96 | -1244497.2698 | -58.15% | -100% | -100% | -100% | -58.15% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal CONVERSION FROM OH-UG RULE 20B NEW BUSIN |  |  |  | Yes |  |  | 895502.6902 | 0 | 0 | 0 | 895502.6902 | 2139999.96 | 2203999.92 | 2269999.92 | 2337999.96 | 2139999.96 | -1244497.2698 | -2203999.92 | -2269999.92 | -2337999.96 | -1244497.2698 | -58.15% | -100% | -100% | -100% | -58.15% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CONVERSION FROM OH-UG RULE 20C | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2300166.5792 | 0 | 0 | 0 | 2300166.5792 | 2553999.96 | 2629999.92 | 2709000 | 2790000 | 2553999.96 | -253833.3808 | -2629999.92 | -2709000 | -2790000 | -253833.3808 | -9.939% | -100% | -100% | -100% | -9.939% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal CONVERSION FROM OH-UG RULE 20C |  |  |  | Yes |  |  | 2300166.5792 | 0 | 0 | 0 | 2300166.5792 | 2553999.96 | 2629999.92 | 2709000 | 2790000 | 2553999.96 | -253833.3808 | -2629999.92 | -2709000 | -2790000 | -253833.3808 | -9.939% | -100% | -100% | -100% | -9.939% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CORONADO 69/12KV TRANSFORMER REPLACEMENT | Electric Infrastructure Integrity | Substation Reliability for Distribution Components - Coronado 69/12kV Transformer Replacements | Substation | No | 4 | 4 | 1280676.1549 | 0 | 0 | 0 | 1280676.1549 | 870999.96 | 897000 | 924000 | 951999.96 | 870999.96 | 409676.1949 | -897000 | -924000 | -951999.96 | 409676.1949 | 47.04% | -100% | -100% | -100% | 47.04% | Transformers replaced | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal CORONADO 69/12KV TRANSFORMER REPLACEMENT |  |  |  | Yes |  |  | 1280676.1549 | 0 | 0 | 0 | 1280676.1549 | 870999.96 | 897000 | 924000 | 951999.96 | 870999.96 | 409676.1949 | -897000 | -924000 | -951999.96 | 409676.1949 | 47.04% | -100% | -100% | -100% | 47.04% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CUSTOMER REQUESTED UPGRADES AND SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 21449329.7167 | 0 | 0 | 0 | 21449329.7167 | 16834999.92 | 17340000 | 17859999.96 | 18396000 | 16834999.92 | 4614329.7967 | -17340000 | -17859999.96 | -18396000 | 4614329.7967 | 27.41% | -100% | -100% | -100% | 27.41% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal CUSTOMER REQUESTED UPGRADES AND SERVICES |  |  |  | Yes |  |  | 21449329.7167 | 0 | 0 | 0 | 21449329.7167 | 16834999.92 | 17340000 | 17859999.96 | 18396000 | 16834999.92 | 4614329.7967 | -17340000 | -17859999.96 | -18396000 | 4614329.7967 | 27.41% | -100% | -100% | -100% | 27.41% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | DISTRIBUTED GENERATION INTERCONNECT. PRO | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 770591.6031 | 0 | 0 | 0 | 770591.6031 | 2217999.96 | 2284999.92 | 2353999.92 | 2424999.96 | 2217999.96 | -1447408.3569 | -2284999.92 | -2353999.92 | -2424999.96 | -1447408.3569 | -65.26% | -100% | -100% | -100% | -65.26% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal DISTRIBUTED GENERATION INTERCONNECT. PRO |  |  |  | Yes |  |  | 770591.6031 | 0 | 0 | 0 | 770591.6031 | 2217999.96 | 2284999.92 | 2353999.92 | 2424999.96 | 2217999.96 | -1447408.3569 | -2284999.92 | -2353999.92 | -2424999.96 | -1447408.3569 | -65.26% | -100% | -100% | -100% | -65.26% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | DISTRIBUTION SYSTEM CAPACITY IMPROVEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 75036.9488 | 0 | 0 | 0 | 75036.9488 | 3997999.92 | 4117999.92 | 4242000 | 4368999.96 | 3997999.92 | -3922962.9712 | -4117999.92 | -4242000 | -4368999.96 | -3922962.9712 | -98.12% | -100% | -100% | -100% | -98.12% | This program is for minor modification types of projects. Work may include feeder and branch reconductoring, installation of appropriate switching, and other equipment as necessary, to increase the capacity of the distribution system for reliability and operating concerns. This program also installs infrastructure for future circuit projects in conjunction with road improvements, transmission system upgrades or other upgrade activities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | Several planned project schedules were shifted from 2024 to 2025 due to permitting delays and new business dependencies, resulting in lower than forecasted 2024 construction activity and spend.
Capital | ELECTRIC DISTRIBUTION | SubTotal DISTRIBUTION SYSTEM CAPACITY IMPROVEMENT |  |  |  | Yes |  |  | 75036.9488 | 0 | 0 | 0 | 75036.9488 | 3997999.92 | 4117999.92 | 4242000 | 4368999.96 | 3997999.92 | -3922962.9712 | -4117999.92 | -4242000 | -4368999.96 | -3922962.9712 | -98.12% | -100% | -100% | -100% | -98.12% | [21 empty] | YES | NO | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | ELCT TRANS SMALL REALIBLTY JOBS- NON WMP | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 178887.6812 | 0 | 0 | 0 | 178887.6812 | 1033999.92 | 1065000 | 1096999.92 | 1129999.92 | 1033999.92 | -855112.2388 | -1065000 | -1096999.92 | -1129999.92 | -855112.2388 | -82.7% | -100% | -100% | -100% | -82.7% | Poles replaced | 44 |  |  |  | 44 | 40 |  |  |  | 40 | 4 | 0 | 0 | 0 | 4 | 10% | 0% | 0% | 0% | 10% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal ELCT TRANS SMALL REALIBLTY JOBS- NON WMP |  |  |  | Yes |  |  | 178887.6812 | 0 | 0 | 0 | 178887.6812 | 1033999.92 | 1065000 | 1096999.92 | 1129999.92 | 1033999.92 | -855112.2388 | -1065000 | -1096999.92 | -1129999.92 | -855112.2388 | -82.7% | -100% | -100% | -100% | -82.7% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ELECTRIC - CONVERSION FROM OH TO UG RULE 20B | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 177929.5083 | 0 | 0 | 0 | 177929.5083 | 59670999.96 | 61461000 | 63304999.92 | 65203999.92 | 59670999.96 | -59493070.4517 | -61461000 | -63304999.92 | -65203999.92 | -59493070.4517 | -99.7% | -100% | -100% | -100% | -99.7% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
Capital | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC - CONVERSION FROM OH TO UG RULE 20B |  |  |  | Yes |  |  | 177929.5083 | 0 | 0 | 0 | 177929.5083 | 59670999.96 | 61461000 | 63304999.92 | 65203999.92 | 59670999.96 | -59493070.4517 | -61461000 | -63304999.92 | -65203999.92 | -59493070.4517 | -99.7% | -100% | -100% | -100% | -99.7% | [21 empty] | NO | NO | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | ELECTRIC DIST. STREET/HWY RELOCATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3076220.5406 | 0 | 0 | 0 | 3076220.5406 | 7971000 | 8209999.92 | 8455999.92 | 8709999.96 | 7971000 | -4894779.4594 | -8209999.92 | -8455999.92 | -8709999.96 | -4894779.4594 | -61.41% | -100% | -100% | -100% | -61.41% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC DIST. STREET/HWY RELOCATIONS |  |  |  | Yes |  |  | 3076220.5406 | 0 | 0 | 0 | 3076220.5406 | 7971000 | 8209999.92 | 8455999.92 | 8709999.96 | 7971000 | -4894779.4594 | -8209999.92 | -8455999.92 | -8709999.96 | -4894779.4594 | -61.41% | -100% | -100% | -100% | -61.41% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ELECTRIC DISTRIBUTION EASEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3879125.8948 | 0 | 0 | 0 | 3879125.8948 | 2836999.92 | 2922000 | 3009999.96 | 3099999.96 | 2836999.92 | 1042125.9748 | -2922000 | -3009999.96 | -3099999.96 | 1042125.9748 | 36.73% | -100% | -100% | -100% | 36.73% | This capital workpaper is required to obtain new electric distribution easements necessary to provide service to new customers, accommodate street and highway relocations, underground conversions, and other capital improvement projects to improve electrical service. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC DISTRIBUTION EASEMENTS |  |  |  | Yes |  |  | 3879125.8948 | 0 | 0 | 0 | 3879125.8948 | 2836999.92 | 2922000 | 3009999.96 | 3099999.96 | 2836999.92 | 1042125.9748 | -2922000 | -3009999.96 | -3099999.96 | 1042125.9748 | 36.73% | -100% | -100% | -100% | 36.73% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ELECTRIC DISTRIBUTION TOOLS/EQUIPMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 864683.21 | 0 | 0 | 0 | 864683.21 | 2631999.96 | 2710999.92 | 2791999.92 | 2875999.92 | 2631999.96 | -1767316.75 | -2710999.92 | -2791999.92 | -2875999.92 | -1767316.75 | -67.15% | -100% | -100% | -100% | -67.15% | Various types of new tools and equipment are purchased through this program to support Electric Distribution work. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC DISTRIBUTION TOOLS/EQUIPMENT |  |  |  | Yes |  |  | 864683.21 | 0 | 0 | 0 | 864683.21 | 2631999.96 | 2710999.92 | 2791999.92 | 2875999.92 | 2631999.96 | -1767316.75 | -2710999.92 | -2791999.92 | -2875999.92 | -1767316.75 | -67.15% | -100% | -100% | -100% | -67.15% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ELECTRIC METERS & REGULATORS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 9745351.75 | 0 | 0 | 0 | 9745351.75 | 6636999.96 | 6835999.92 | 7041000 | 7251999.96 | 6636999.96 | 3108351.79 | -6835999.92 | -7041000 | -7251999.96 | 3108351.79 | 46.83% | -100% | -100% | -100% | 46.83% | Meters purchased | 62211 |  |  |  | 62211 | 9515 |  |  |  | 9515 | 52696 | 0 | 0 | 0 | 52696 | 553.8% | 0% | 0% | 0% | 553.8% | YES | NO | YES | N/A | The actual unit variance compared to authorized is driven by higher-than-expected equipment failure and replacement rate of field electric smart meters. This program is responsive in nature and the demand for meters is ongoing as replacement meters are necessary to service electric distribution customers. | Over (O) | On Target (T) | On Target (T) | Expanded | NO | N/A | This budget code is for an ongoing project to purchase new meters and regulators used to measure service to electric distribution customers. The funds are used to maintain inventory levels at each of the electric distribution service centers. | SDG&E-11-R OR-64 to OR-65 CWP 002020
Capital | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC METERS & REGULATORS |  |  |  | Yes |  |  | 9745351.75 | 0 | 0 | 0 | 9745351.75 | 6636999.96 | 6835999.92 | 7041000 | 7251999.96 | 6636999.96 | 3108351.79 | -6835999.92 | -7041000 | -7251999.96 | 3108351.79 | 46.83% | -100% | -100% | -100% | 46.83% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ELECTRIC TRANSMISSION TOOLS & EQUIPMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 369985.33 | 0 | 0 | 0 | 369985.33 | 555000 | 571999.92 | 588999.96 | 606999.96 | 555000 | -185014.67 | -571999.92 | -588999.96 | -606999.96 | -185014.67 | -33.34% | -100% | -100% | -100% | -33.34% | This program supports new types or additional tool purchases for ongoing construction and maintenance activities on the Substation and Transmission System. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal ELECTRIC TRANSMISSION TOOLS & EQUIPMENT |  |  |  | Yes |  |  | 369985.33 | 0 | 0 | 0 | 369985.33 | 555000 | 571999.92 | 588999.96 | 606999.96 | 555000 | -185014.67 | -571999.92 | -588999.96 | -606999.96 | -185014.67 | -33.34% | -100% | -100% | -100% | -33.34% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | FIBER OPTIC FOR RELAY PROTECT & TELECOM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3903417.9015 | 0 | 0 | 0 | 3903417.9015 | 8928999.96 | 9196999.92 | 9472999.92 | 9756999.96 | 8928999.96 | -5025582.0585 | -9196999.92 | -9472999.92 | -9756999.96 | -5025582.0585 | -56.28% | -100% | -100% | -100% | -56.28% | All-Dielectric Self-Supporting (ADSS) Miles | 0 |  |  |  | 0 | 24 |  |  |  | 24 | -24 | 0 | 0 | 0 | -24 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | Lower actual costs due to delayed design stage and shifting of construction to later years in the cycle and lower CPUC communications spend as a result of the FERC 898 Decision. | The 2024 scope was not completed due to delayed design stage and shifting of construction to later years in the cycle. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Projects completed will provide a diverse company-owned and maintained communications network to support electric operations. | SDG&E-11-R OR-169 to OR-170 CWP 071440
Capital | ELECTRIC DISTRIBUTION | SubTotal FIBER OPTIC FOR RELAY PROTECT & TELECOM |  |  |  | Yes |  |  | 3903417.9015 | 0 | 0 | 0 | 3903417.9015 | 8928999.96 | 9196999.92 | 9472999.92 | 9756999.96 | 8928999.96 | -5025582.0585 | -9196999.92 | -9472999.92 | -9756999.96 | -5025582.0585 | -56.28% | -100% | -100% | -100% | -56.28% | [21 empty] | YES | YES | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | FIELD SHUNT CAPACITORS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 86332.6685 | 0 | 0 | 0 | 86332.6685 | 870999.96 | 897000 | 924000 | 951999.96 | 870999.96 | -784667.2915 | -897000 | -924000 | -951999.96 | -784667.2915 | -90.09% | -100% | -100% | -100% | -90.09% | Capacitor banks energized | 2 |  |  |  | 2 | 8 |  |  |  | 8 | -6 | 0 | 0 | 0 | -6 | -75% | 0% | 0% | 0% | -75% | YES | NO | YES | N/A | Capacitors are installed to efficiently supply the reactive power with the increasing load in the distribution system. In 2024, there was less need to install capacitors than forecasted in the 2024 GRC. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This program provides installation of overhead and underground shunt capacitors on 4kV and 12kV distribution circuits. | SDG&E-11-R OR-28 to OR-29 CWP 002090
Capital | ELECTRIC DISTRIBUTION | SubTotal FIELD SHUNT CAPACITORS |  |  |  | Yes |  |  | 86332.6685 | 0 | 0 | 0 | 86332.6685 | 870999.96 | 897000 | 924000 | 951999.96 | 870999.96 | -784667.2915 | -897000 | -924000 | -951999.96 | -784667.2915 | -90.09% | -100% | -100% | -100% | -90.09% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | FUTURE CAPACITY PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 13021818.6357 | 0 | 0 | 0 | 13021818.6357 | 9651999.96 | 9942000 | 10239999.96 | 10546999.92 | 9651999.96 | 3369818.6757 | -9942000 | -10239999.96 | -10546999.92 | 3369818.6757 | 34.91% | -100% | -100% | -100% | 34.91% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal FUTURE CAPACITY PROJECTS |  |  |  | Yes |  |  | 13021818.6357 | 0 | 0 | 0 | 13021818.6357 | 9651999.96 | 9942000 | 10239999.96 | 10546999.92 | 9651999.96 | 3369818.6757 | -9942000 | -10239999.96 | -10546999.92 | 3369818.6757 | 34.91% | -100% | -100% | -100% | 34.91% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | GRANITE SUBSTATION 69KV LOOP-IN | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 2 | 297527.0352 | 0 | 0 | 0 | 297527.0352 | 177000 | 181999.92 | 186999.96 | 192999.96 | 177000 | 120527.0352 | -181999.92 | -186999.96 | -192999.96 | 120527.0352 | 68.09% | -100% | -100% | -100% | 68.09% | Telecom materials | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal GRANITE SUBSTATION 69KV LOOP-IN |  |  |  | Yes |  |  | 297527.0352 | 0 | 0 | 0 | 297527.0352 | 177000 | 181999.92 | 186999.96 | 192999.96 | 177000 | 120527.0352 | -181999.92 | -186999.96 | -192999.96 | 120527.0352 | 68.09% | -100% | -100% | -100% | 68.09% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | LA JOLLA 69/12KV TRANSFORMER REPLACEMENT | Electric Infrastructure Integrity | La Jolla 69/12kV Transformer Replacement | Substation | No | 4 | Canceled | 116680.62 | 0 | 0 | 0 | 116680.62 | 135000 | 138999.96 | 142999.92 | 147000 | 135000 | -18319.38 | -138999.96 | -142999.92 | -147000 | -18319.38 | -13.57% | -100% | -100% | -100% | -13.57% | This project was canceled because it has been reassessed, and no significant maintenance concerns have been evaluated. Due to affordability and other more critical projects, the project has been canceled. 2024 activities included preliminary engineering. The intended purpose of this project was to remove and replace transformer(s), disconnect(s), and capacitor banks due to aging infrastructure, operational limitations, environmental concerns, in addition to meeting current reliability standards. The variety of work activities in this category makes it infeasible to identify a single unit of measure. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Over (O) | Under (U) | Canceled | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal LA JOLLA 69/12KV TRANSFORMER REPLACEMENT |  |  |  | Yes |  |  | 116680.62 | 0 | 0 | 0 | 116680.62 | 135000 | 138999.96 | 142999.92 | 147000 | 135000 | -18319.38 | -138999.96 | -142999.92 | -147000 | -18319.38 | -13.57% | -100% | -100% | -100% | -13.57% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | MISSION DCC REMODEL PROJECT | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 3 | 308798.777 | 0 | 0 | 0 | 308798.777 | 10347999.96 | 10657999.92 | 10977999.96 | 11307000 | 10347999.96 | -10039201.183 | -10657999.92 | -10977999.96 | -11307000 | -10039201.183 | -97.02% | -100% | -100% | -100% | -97.02% | Activities in this workpaper represent planning, design, permitting, and construction of a 22,000 square feet 2-story addition to Mission Control Building A and renovation of the existing distribution control center (DCC) and related areas. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | Project was taken through permitting, then placed on hold due to an increase in responsive and new business projects in 2024. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | Project on hold driven by an increase in responsive and new business projects in 2024. | The project involves the planning, design, permitting, and construction of a 12,000 s.f. 2-story addition to Mission Control Building A, as well as renovation of the existing DCC and related areas. The new addition will include a new DCC with new operator consoles, workstations, conference rooms, and offices, raised flooring, high ceilings, good fenestration allowing natural lighting, new building systems such as HVAC, energy management, furniture, audio- visual, video wall, and new finishes brought up to the current Company standards. City of San Diego Planning Department and Building Department approval is required. Certification through USGBC's LEED program (silver level) and Zero Net Energy are also objectives. | SDG&E-11-R OR-163 to OR-165 CWP 212670
Capital | ELECTRIC DISTRIBUTION | SubTotal MISSION DCC REMODEL PROJECT |  |  |  | Yes |  |  | 308798.777 | 0 | 0 | 0 | 308798.777 | 10347999.96 | 10657999.92 | 10977999.96 | 11307000 | 10347999.96 | -10039201.183 | -10657999.92 | -10977999.96 | -11307000 | -10039201.183 | -97.02% | -100% | -100% | -100% | -97.02% | [21 empty] | YES | YES | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | NEW BUSINESS INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 4121060.1942 | 0 | 0 | 0 | 4121060.1942 | 6465000 | 6658999.92 | 6858999.96 | 7063999.92 | 6465000 | -2343939.8058 | -6658999.92 | -6858999.96 | -7063999.92 | -2343939.8058 | -36.26% | -100% | -100% | -100% | -36.26% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal NEW BUSINESS INFRASTRUCTURE |  |  |  | Yes |  |  | 4121060.1942 | 0 | 0 | 0 | 4121060.1942 | 6465000 | 6658999.92 | 6858999.96 | 7063999.92 | 6465000 | -2343939.8058 | -6658999.92 | -6858999.96 | -7063999.92 | -2343939.8058 | -36.26% | -100% | -100% | -100% | -36.26% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | NEW SERVICE INSTALLATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 10468002.3041 | 0 | 0 | 0 | 10468002.3041 | 8718000 | 8979999.96 | 9249999.96 | 9526999.92 | 8718000 | 1750002.3041 | -8979999.96 | -9249999.96 | -9526999.92 | 1750002.3041 | 20.07% | -100% | -100% | -100% | 20.07% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal NEW SERVICE INSTALLATIONS |  |  |  | Yes |  |  | 10468002.3041 | 0 | 0 | 0 | 10468002.3041 | 8718000 | 8979999.96 | 9249999.96 | 9526999.92 | 8718000 | 1750002.3041 | -8979999.96 | -9249999.96 | -9526999.92 | 1750002.3041 | 20.07% | -100% | -100% | -100% | 20.07% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | OH NON-RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1352279.3242 | 0 | 0 | 0 | 1352279.3242 | 1278999.96 | 1317999.96 | 1357999.92 | 1398999.96 | 1278999.96 | 73279.3642 | -1317999.96 | -1357999.92 | -1398999.96 | 73279.3642 | 5.729% | -100% | -100% | -100% | 5.729% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal OH NON-RESIDENTIAL NB |  |  |  | Yes |  |  | 1352279.3242 | 0 | 0 | 0 | 1352279.3242 | 1278999.96 | 1317999.96 | 1357999.92 | 1398999.96 | 1278999.96 | 73279.3642 | -1317999.96 | -1357999.92 | -1398999.96 | 73279.3642 | 5.729% | -100% | -100% | -100% | 5.729% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | OH RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1898155.3411 | 0 | 0 | 0 | 1898155.3411 | 1050000 | 1080999.96 | 1113000 | 1146000 | 1050000 | 848155.3411 | -1080999.96 | -1113000 | -1146000 | 848155.3411 | 80.78% | -100% | -100% | -100% | 80.78% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal OH RESIDENTIAL NB |  |  |  | Yes |  |  | 1898155.3411 | 0 | 0 | 0 | 1898155.3411 | 1050000 | 1080999.96 | 1113000 | 1146000 | 1050000 | 848155.3411 | -1080999.96 | -1113000 | -1146000 | 848155.3411 | 80.78% | -100% | -100% | -100% | 80.78% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | PLANNED INVESTMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 1929205.8878 | 0 | 0 | 0 | 1929205.8878 | 4432999.92 | 4566000 | 4702999.92 | 4843999.92 | 4432999.92 | -2503794.0322 | -4566000 | -4702999.92 | -4843999.92 | -2503794.0322 | -56.48% | -100% | -100% | -100% | -56.48% | This blanket program provides for the reconstruction and extension of overhead and underground distribution facilities to replace overloaded conductors, to correct primary voltage problems, and to transfer load to balance circuits and substations. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal PLANNED INVESTMENTS |  |  |  | Yes |  |  | 1929205.8878 | 0 | 0 | 0 | 1929205.8878 | 4432999.92 | 4566000 | 4702999.92 | 4843999.92 | 4432999.92 | -2503794.0322 | -4566000 | -4702999.92 | -4843999.92 | -2503794.0322 | -56.48% | -100% | -100% | -100% | -56.48% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP - CORRECTIVE MAINTENANCE PROGRAM (CMP) | Electric Infrastructure Integrity | GO165 Corrective Maintenance Program Underground | UG Distribution | No | On-going | Annual | 22351427.1534 | 0 | 0 | 0 | 22351427.1534 | 14073000 | 14494999.92 | 14929999.92 | 15378000 | 14073000 | 8278427.1534 | -14494999.92 | -14929999.92 | -15378000 | 8278427.1534 | 58.82% | -100% | -100% | -100% | 58.82% | Jobs completed | 1420 |  |  |  | 1420 | 1695 |  |  |  | 1695 | -275 | 0 | 0 | 0 | -275 | -16.22% | 0% | 0% | 0% | -16.22% | YES | YES | NO | Higher than historical average costs for 4.5% of jobs with larger scope or higher cost materials/ equipment contributed to cost variance. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Repair of overhead and underground electric distribution facilities to correct conditions found during inspection. This program is mandated under CPUC General Orders 165, 95, and 128 to ensure safe, high quality electrical service and compliance with SDG&E and CPUC construction standards. Inspections are performed on a cyclical basis and conditions found during inspections are repaired in a timely manner. This program has been ongoing since January 1998. | SDG&E-11-R OR-56 to OR-57 CWP 002290
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP - CORRECTIVE MAINTENANCE PROGRAM (CMP) |  |  |  | Yes |  |  | 22351427.1534 | 0 | 0 | 0 | 22351427.1534 | 14073000 | 14494999.92 | 14929999.92 | 15378000 | 14073000 | 8278427.1534 | -14494999.92 | -14929999.92 | -15378000 | 8278427.1534 | 58.82% | -100% | -100% | -100% | 58.82% | [21 empty] | YES | YES | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP - INSTALL SCADA ON LINE CAPACITORS | Electric Infrastructure Integrity | SCADA Capacitors | OH Distribution | No | On-going | Annual | 157783.5561 | 0 | 0 | 0 | 157783.5561 | 864000 | 889999.92 | 916999.92 | 943999.92 | 864000 | -706216.4439 | -889999.92 | -916999.92 | -943999.92 | -706216.4439 | -81.74% | -100% | -100% | -100% | -81.74% | Overhead (OH) SCADA capacitors installed | 1 |  |  |  | 1 | 11 |  |  |  | 11 | -10 | 0 | 0 | 0 | -10 | -90.91% | 0% | 0% | 0% | -90.91% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project will improve system efficiency and operability by converting existing distribution line capacitors to SCADA controlled line capacitors that will enable remote VAR control and download circuit loading information to a web portal . The data/information provided by the SCADA capacitors will help improve capacitor reliability, minimize duration of outages, and enable expedited repair work. | SDG&E-11-R OR-106 to OR-108 CWP 112490
Capital | ELECTRIC DISTRIBUTION | RAMP - INSTALL SCADA ON LINE CAPACITORS | Electric Infrastructure Integrity | SCADA Capacitors | UG Distribution | No | On-going | Annual | 67621.5305 | 0 | 0 | 0 | 67621.5305 | 369999.96 | 381000 | 391999.92 | 403999.92 | 369999.96 | -302378.4295 | -381000 | -391999.92 | -403999.92 | -302378.4295 | -81.72% | -100% | -100% | -100% | -81.72% | Underground (UG) SCADA capacitors installed | 0 |  |  |  | 0 | 4 |  |  |  | 4 | -4 | 0 | 0 | 0 | -4 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project will improve system efficiency and operability by converting existing distribution line capacitors to SCADA controlled line capacitors that will enable remote VAR control and download circuit loading information to a web portal . The data/information provided by the SCADA capacitors will help improve capacitor reliability, minimize duration of outages, and enable expedited repair work. | SDG&E-11-R OR-106 to OR-108 CWP 112490
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP - INSTALL SCADA ON LINE CAPACITORS |  |  |  | Yes |  |  | 225405.0866 | 0 | 0 | 0 | 225405.0866 | 1233999.96 | 1270999.92 | 1308999.84 | 1347999.84 | 1233999.96 | -1008594.8734 | -1270999.92 | -1308999.84 | -1347999.84 | -1008594.8734 | -81.73% | -100% | -100% | -100% | -81.73% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP - MANHOLE, HANDHOLE, AND VAULT RESTORATION | Electric Infrastructure Integrity | GO 165 Manhole, Vault Restoration Program | Manhole/Handhole | No | On-going | Annual | 4109581.5124 | 0 | 0 | 0 | 4109581.5124 | 5404999.92 | 5566999.92 | 5733999.96 | 5905999.92 | 5404999.92 | -1295418.4076 | -5566999.92 | -5733999.96 | -5905999.92 | -1295418.4076 | -23.97% | -100% | -100% | -100% | -23.97% | Manhole restorations | 622 |  |  |  | 622 | 771 |  |  |  | 771 | -149 | 0 | 0 | 0 | -149 | -19.33% | 0% | 0% | 0% | -19.33% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP - MANHOLE, HANDHOLE, AND VAULT RESTORATION |  |  |  | Yes |  |  | 4109581.5124 | 0 | 0 | 0 | 4109581.5124 | 5404999.92 | 5566999.92 | 5733999.96 | 5905999.92 | 5404999.92 | -1295418.4076 | -5566999.92 | -5733999.96 | -5905999.92 | -1295418.4076 | -23.97% | -100% | -100% | -100% | -23.97% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP - POLE REPLACEMENT AND REINFORCEMENT | Electric Infrastructure Integrity | GO165 Pole Replacement Reinforcement | N/A | No | On-going | Annual | 19509318.2107 | 0 | 0 | 0 | 19509318.2107 | 15933000 | 16410999.96 | 16902999.96 | 17409999.96 | 15933000 | 3576318.2107 | -16410999.96 | -16902999.96 | -17409999.96 | 3576318.2107 | 22.45% | -100% | -100% | -100% | 22.45% | Poles replaced | 747 |  |  |  | 747 | 600 |  |  |  | 600 | 147 | 0 | 0 | 0 | 147 | 24.5% | 0% | 0% | 0% | 24.5% | YES | NO | YES | N/A | Higher than anticipated pole replacements due to the responsive nature of this workpaper and aging infrastructure. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This program provides funding to continue the pole restoration, replacement and removal program for electric distribution poles identified through the CMP program. | SDG&E-11-R OR-62 to OR-63 CWP 872320
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP - POLE REPLACEMENT AND REINFORCEMENT |  |  |  | Yes |  |  | 19509318.2107 | 0 | 0 | 0 | 19509318.2107 | 15933000 | 16410999.96 | 16902999.96 | 17409999.96 | 15933000 | 3576318.2107 | -16410999.96 | -16902999.96 | -17409999.96 | 3576318.2107 | 22.45% | -100% | -100% | -100% | 22.45% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP - REPLACE OBSOLETE SUBSTATION EQUIPMENT | Electric Infrastructure Integrity | Distribution Substation Obsolete Equipment | Substation | No | On-going | Annual | 1730617.5885 | 0 | 0 | 0 | 1730617.5885 | 2641999.92 | 2721000 | 2802999.96 | 2886999.96 | 2641999.92 | -911382.3315 | -2721000 | -2802999.96 | -2886999.96 | -911382.3315 | -34.5% | -100% | -100% | -100% | -34.5% | Major substation equipment installed | 7 |  |  |  | 7 | 3 |  |  |  | 3 | 4 | 0 | 0 | 0 | 4 | 133.3% | 0% | 0% | 0% | 133.3% | YES | NO | YES | N/A | Preparation for and associated costs were incurred in prior calendar years in order to support the installations of 7 pieces of equipment in 2024 compared to the estimated 3 authorized. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project will improve safety and reliability related to the replacement of obsolete and problematic substation equipment. This project will focus primarily on distribution substation bank transformers and circuit breaker replacements. The Substation Equipment Assessment Team will develop alternatives to replace or remove obsolete and problematic equipment. A condition assessment process and evaluation criteria have been created using probability and risk analysis, financial impacts and present value analysis to justify projects. Equipment that is truly obsolete such as equipment that cannot be maintained (no spare parts available), or that which poses a safety risk will be replaced. | SDG&E-11-R OR-147 to OR-148 CWP 992820
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP - REPLACE OBSOLETE SUBSTATION EQUIPMENT |  |  |  | Yes |  |  | 1730617.5885 | 0 | 0 | 0 | 1730617.5885 | 2641999.92 | 2721000 | 2802999.96 | 2886999.96 | 2641999.92 | -911382.3315 | -2721000 | -2802999.96 | -2886999.96 | -911382.3315 | -34.5% | -100% | -100% | -100% | -34.5% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP - STUART 12KV TRANSFORMER REPLACEMENT | Electric Infrastructure Integrity | Stuart 12kV Transformer Replacement | Substation | No | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 1090999.92 | 1123999.92 | 1158000 | 1192999.92 | 1090999.92 | -1090999.92 | -1123999.92 | -1158000 | -1192999.92 | -1090999.92 | -100% | -100% | -100% | -100% | -100% | Transformer replaced | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Project was put on hold pending further internal analysis. | On Target (T) | Over (O) | On Target (T) | Other | YES | Project was placed on hold pending further analysis but is expected to resume later in the 2024 GRC cycle. | This project addresses safety, reliability and environmental concerns associated with aging infrastructure, equipment with operational limits and/or does not meet current standards, and unsafe site conditions. | SDG&E-11-R OR-135 to OR-136 CWP 20270A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP - STUART 12KV TRANSFORMER REPLACEMENT |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 1090999.92 | 1123999.92 | 1158000 | 1192999.92 | 1090999.92 | -1090999.92 | -1123999.92 | -1158000 | -1192999.92 | -1090999.92 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | RAMP- 4KV MODERNIZATION | Electric Infrastructure Integrity | 4kV Modernization Program Distribution | OH Distribution | No | On-going | Annual | 223228.3275 | 0 | 0 | 0 | 223228.3275 | 8202000 | 8448000 | 8700999.96 | 8961999.96 | 8202000 | -7978771.6725 | -8448000 | -8700999.96 | -8961999.96 | -7978771.6725 | -97.28% | -100% | -100% | -100% | -97.28% | Miles of conductor replaced | 0 |  |  |  | 0 | 6 |  |  |  | 6 | -6 | 0 | 0 | 0 | -6 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | Lower actual costs driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | Lower actual costs and units driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | The purpose of this project is to increase reliability by targeting the replacement of poles, wires, equipment, hardware, degraded UG structures, transformers, switches, and other distribution equipment as necessary to accommodate conversion of 4 kV facilities to modern 12 kV distribution. At the culmination of the distribution cutover, the associated 4kV substation infrastructure will be removed as applicable. | SDG&E-11-R OR-121 to OR-123 CWP 172690
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- 4KV MODERNIZATION |  |  |  | Yes |  |  | 223228.3275 | 0 | 0 | 0 | 223228.3275 | 8202000 | 8448000 | 8700999.96 | 8961999.96 | 8202000 | -7978771.6725 | -8448000 | -8700999.96 | -8961999.96 | -7978771.6725 | -97.28% | -100% | -100% | -100% | -97.28% | [21 empty] | YES | YES | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | RAMP- AVIAN PROTECTION | Electric Infrastructure Integrity | Avian Protection Program | OH Distribution | No | On-going | Annual | 14459.5354 | 0 | 0 | 0 | 14459.5354 | 234000 | 240999.96 | 247999.92 | 255000 | 234000 | -219540.4646 | -240999.96 | -247999.92 | -255000 | -219540.4646 | -93.82% | -100% | -100% | -100% | -93.82% | Poles protected | 0 |  |  |  | 0 | 50 |  |  |  | 50 | -50 | 0 | 0 | 0 | -50 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Lower actual unit count was driven by higher Avian Protection Wildfire Mitigation Plan (WMP) workpaper 22247 using resources assumed Non-HFTD in 2024. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Systematically inspect all distribution lines and poles in the overhead distribution system that either 1) lie within the Avian Protection Zone, or 2) have associated known bird contacts, in which case potential avian risks are identified and resolved. | SDG&E-11-R OR-58 to OR-60 CWP 102650
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- AVIAN PROTECTION |  |  |  | Yes |  |  | 14459.5354 | 0 | 0 | 0 | 14459.5354 | 234000 | 240999.96 | 247999.92 | 255000 | 234000 | -219540.4646 | -240999.96 | -247999.92 | -255000 | -219540.4646 | -93.82% | -100% | -100% | -100% | -93.82% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- BERNARDO 12 KV BREAKERS AND TRANSFORMER | Electric Infrastructure Integrity | Substation Reliability for Distribution Components Bernardo 12kV Breakers Replacements | Substation | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1161999.96 | 1197000 | 1233000 | 1269999.96 | 1161999.96 | -1161999.96 | -1197000 | -1233000 | -1269999.96 | -1161999.96 | -100% | -100% | -100% | -100% | -100% | Breakers replaced | 0 |  |  |  | 0 | 15 |  |  |  | 15 | -15 | 0 | 0 | 0 | -15 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Project was put on hold due to re-prioritization of more critical replacements. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This program will proactively address safety and reliability issues associated with equipment that has reached its useful life. The equipment to be replaced is that which is determined to have reached the end of its useful life and poses both a safety and reliability threat if not replaced. | SDG&E-11-R OR-130 to OR-132 CWP 20263A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- BERNARDO 12 KV BREAKERS AND TRANSFORMER |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 1161999.96 | 1197000 | 1233000 | 1269999.96 | 1161999.96 | -1161999.96 | -1197000 | -1233000 | -1269999.96 | -1161999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | RAMP- CAPITAL RESTORATION OF SERVICE | Electric Infrastructure Integrity | Restoration of Service | N/A | No | On-going | Annual | 10933651.1225 | 0 | 0 | 0 | 10933651.1225 | 11937999.96 | 12295999.92 | 12664999.92 | 13044999.96 | 11937999.96 | -1004348.8375 | -12295999.92 | -12664999.92 | -13044999.96 | -1004348.8375 | -8.413% | -100% | -100% | -100% | -8.413% | Non-transformer forced outages requiring crew repair or in-kind replacement | 776 |  |  |  | 776 | 590 |  |  |  | 590 | 186 | 0 | 0 | 0 | 186 | 31.53% | 0% | 0% | 0% | 31.53% | YES | NO | YES | N/A | 2024 had a higher average number of outages compared to the three-year average authorized in the 2024 GRC, primarily driven by January and February storm events and September heat event. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The purpose of this program is to fund reactionary repairs to SDG&E distribution facilities as necessary to restore electric service to customers in a timely manner and in compliance with the CPUC General Orders. | SDG&E-11-R OR-100 to OR-102 CWP 002360
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- CAPITAL RESTORATION OF SERVICE |  |  |  | Yes |  |  | 10933651.1225 | 0 | 0 | 0 | 10933651.1225 | 11937999.96 | 12295999.92 | 12664999.92 | 13044999.96 | 11937999.96 | -1004348.8375 | -12295999.92 | -12664999.92 | -13044999.96 | -1004348.8375 | -8.413% | -100% | -100% | -100% | -8.413% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- DISTRIBUTION CIRCUIT RELIABILITY CONSTRUCTION | Electric Infrastructure Integrity | Distribution Circuit Reliability | OH Distribution | No | On-going | Annual | 691728.9509 | 0 | 0 | 0 | 691728.9509 | 2067999.96 | 2130999.96 | 2193999.96 | 2260999.92 | 2067999.96 | -1376271.0091 | -2130999.96 | -2193999.96 | -2260999.92 | -1376271.0091 | -66.55% | -100% | -100% | -100% | -66.55% | OH Switches Replaced | 1 |  |  |  | 1 | 5 |  |  |  | 5 | -4 | 0 | 0 | 0 | -4 | -80% | 0% | 0% | 0% | -80% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The electric service reliability will deteriorate in the absence of comprehensive remedial solutions offered by these projects, also, electric reliability performance is negatively impacted by system deficiencies and an aging infrastructure. The 93240 budget funds projects that mitigate existing electric system deficiencies, projects for system performance improvements as follows General Reliability, Scada Initiatives and the Community Fire Safety Program. | SDG&E-11-R OR-143 to OR-144 CWP 932400
Capital | ELECTRIC DISTRIBUTION | RAMP- DISTRIBUTION CIRCUIT RELIABILITY CONSTRUCTION | Electric Infrastructure Integrity | Distribution Circuit Reliability | UG Distribution | No | On-going | Annual | 1037593.4313 | 0 | 0 | 0 | 1037593.4313 | 3102000 | 3193999.92 | 3291000 | 3388999.92 | 3102000 | -2064406.5687 | -3193999.92 | -3291000 | -3388999.92 | -2064406.5687 | -66.55% | -100% | -100% | -100% | -66.55% | UG Switches Replaced | 2 |  |  |  | 2 | 9 |  |  |  | 9 | -7 | 0 | 0 | 0 | -7 | -77.78% | 0% | 0% | 0% | -77.78% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The electric service reliability will deteriorate in the absence of comprehensive remedial solutions offered by these projects, also, electric reliability performance is negatively impacted by system deficiencies and an aging infrastructure. The 93240 budget funds projects that mitigate existing electric system deficiencies, projects for system performance improvements as follows General Reliability, Scada Initiatives and the Community Fire Safety Program. | SDG&E-11-R OR-143 to OR-144 CWP 932400
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- DISTRIBUTION CIRCUIT RELIABILITY CONSTRUCTION |  |  |  | Yes |  |  | 1729322.3822 | 0 | 0 | 0 | 1729322.3822 | 5169999.96 | 5324999.88 | 5484999.96 | 5649999.84 | 5169999.96 | -3440677.5778 | -5324999.88 | -5484999.96 | -5649999.84 | -3440677.5778 | -66.55% | -100% | -100% | -100% | -66.55% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- DISTRIBUTION SUBSTATION RELIABILITY | Electric Infrastructure Integrity | Minor Distribution Substation Reliability Projects | N/A | No | On-going | Annual | 1572500.7445 | 0 | 0 | 0 | 1572500.7445 | 1725000 | 1776999.96 | 1830000 | 1884999.96 | 1725000 | -152499.2555 | -1776999.96 | -1830000 | -1884999.96 | -152499.2555 | -8.841% | -100% | -100% | -100% | -8.841% | Major substation equipment installed | 3 |  |  |  | 3 | 3 |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- DISTRIBUTION SUBSTATION RELIABILITY |  |  |  | Yes |  |  | 1572500.7445 | 0 | 0 | 0 | 1572500.7445 | 1725000 | 1776999.96 | 1830000 | 1884999.96 | 1725000 | -152499.2555 | -1776999.96 | -1830000 | -1884999.96 | -152499.2555 | -8.841% | -100% | -100% | -100% | -8.841% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- DOE SWITCH REPLACEMENT | Electric Infrastructure Integrity | DOE Switch Replacement Underground | UG Distribution | No | On-going | Annual | 2325336.0586 | 0 | 0 | 0 | 2325336.0586 | 7248999.96 | 7465999.92 | 7689999.96 | 7920999.96 | 7248999.96 | -4923663.9014 | -7465999.92 | -7689999.96 | -7920999.96 | -4923663.9014 | -67.92% | -100% | -100% | -100% | -67.92% | Do not Operate Energized (DOE) Switches Replaced | 16 |  |  |  | 16 | 28 |  |  |  | 28 | -12 | 0 | 0 | 0 | -12 | -42.86% | 0% | 0% | 0% | -42.86% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project removes or replaces defective overhead switches and underground oil, gas and air-insulated manual and SCADA switches that SDG&E has classified as Do not Operate Energized (DOE). Good engineering practices and CPUC general orders dictate that removal, replacement, or repairs of these switches be completed to ensure employee, contractor and public safety. | SDG&E-11-R OR-103 to OR-105 CWP 002900
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- DOE SWITCH REPLACEMENT |  |  |  | Yes |  |  | 2325336.0586 | 0 | 0 | 0 | 2325336.0586 | 7248999.96 | 7465999.92 | 7689999.96 | 7920999.96 | 7248999.96 | -4923663.9014 | -7465999.92 | -7689999.96 | -7920999.96 | -4923663.9014 | -67.92% | -100% | -100% | -100% | -67.92% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- EL CAJON 12KV BREAKER REPLACEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | 4 | Completed | 2112103.2225 | 0 | 0 | 0 | 2112103.2225 | 0 | 0 | 0 | 0 | 0 | 2112103.2225 | 0 | 0 | 0 | 2112103.2225 | 100% | 0% | 0% | 0% | 100% | Breakers replaced | 14 |  |  |  | 14 | 0 |  |  |  | 0 | 14 | 0 | 0 | 0 | 14 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Units were originally anticipated to be installed in 2022 and 2023; however, were deferred to 2024 due to re-prioritization of funding allocation to responsive projects. | Over (O) | Over (O) | Over (O) | Completed | NO | Project was anticipated to be completed during the 2019 GRC cycle but was completed in 2024. | This program removes and replaces existing circuit breakers at El Cajon Substation with new 12kV breakers to address aging infrastructure, operation limitations, environmental concerns, and to bring the substation up to current reliability standards. The breakers are approaching their end of life expectancy. This replacement will add 12kV system reliability as well as environmental benefits by replacing the oil-filled breakers with a vacuum switch model. | SDG&E-11-R OR-127 to OR-129 CWP 202450
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- EL CAJON 12KV BREAKER REPLACEMENTS |  |  |  | Yes |  |  | 2112103.2225 | 0 | 0 | 0 | 2112103.2225 | 0 | 0 | 0 | 0 | 0 | 2112103.2225 | 0 | 0 | 0 | 2112103.2225 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- EMERGENCY TRANSFORMER & SWITCHGEAR | Electric Infrastructure Integrity | Emergency Transformer and Switchgear | N/A | No | On-going | Annual | 960873.6458 | 0 | 0 | 0 | 960873.6458 | 418999.92 | 432000 | 444999.96 | 457999.92 | 418999.92 | 541873.7258 | -432000 | -444999.96 | -457999.92 | 541873.7258 | 129.3% | -100% | -100% | -100% | 129.3% | Substation equipment purchased | 25 |  |  |  | 25 | 77 |  |  |  | 77 | -52 | 0 | 0 | 0 | -52 | -67.53% | 0% | 0% | 0% | -67.53% | YES | NO | YES | N/A | Increased unit pricing for equipment and milestone payments resulted in lower actual units purchased than authorized. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Purchase and install a 69/12 kV transformer on a concrete pad at Bay Blvd Substation, purchase and install a 69/12 kV transformer on a concrete pad at Vine Substation, refurbish and replace equipment on an existing trailer mounted 12/4kV transformer, purchase three mobile 12kV circuit breakers, and purchase spare bushings, insulators, disconnects, capacitor cans, arresters, and circuit breakers for the 12kV system. | SDG&E-11-R OR-105 to OR-106 CWP 062540
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- EMERGENCY TRANSFORMER & SWITCHGEAR |  |  |  | Yes |  |  | 960873.6458 | 0 | 0 | 0 | 960873.6458 | 418999.92 | 432000 | 444999.96 | 457999.92 | 418999.92 | 541873.7258 | -432000 | -444999.96 | -457999.92 | 541873.7258 | 129.3% | -100% | -100% | -100% | 129.3% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- HIGH RISK SWITCH REPLACEMENT PROJECT | Electric Infrastructure Integrity | Distribution Overhead Switch Replacement Program | OH Distribution | No | On-going | Annual | 352453.3514 | 0 | 0 | 0 | 352453.3514 | 1042999.92 | 1074000 | 1105999.92 | 1138999.92 | 1042999.92 | -690546.5686 | -1074000 | -1105999.92 | -1138999.92 | -690546.5686 | -66.21% | -100% | -100% | -100% | -66.21% | Switches Replaced | 4 |  |  |  | 4 | 20 |  |  |  | 20 | -16 | 0 | 0 | 0 | -16 | -80% | 0% | 0% | 0% | -80% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Replace high-risk OH switches, in-line switches, and cutouts from environmental contamination and corrosions with new and improved designs and/or dynamic protective devices. | SDG&E-11-R OR-118 to OR-120 CWP 172610
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- HIGH RISK SWITCH REPLACEMENT PROJECT |  |  |  | Yes |  |  | 352453.3514 | 0 | 0 | 0 | 352453.3514 | 1042999.92 | 1074000 | 1105999.92 | 1138999.92 | 1042999.92 | -690546.5686 | -1074000 | -1105999.92 | -1138999.92 | -690546.5686 | -66.21% | -100% | -100% | -100% | -66.21% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- ENERGIZED TEST YARD | Non-RAMP | Non-RAMP | Non-RAMP | No | 6 | 8 | 52414.856 | 0 | 0 | 0 | 52414.856 | 0 | 0 | 0 | 0 | 0 | 52414.856 | 0 | 0 | 0 | 52414.856 | 100% | 0% | 0% | 0% | 100% | This project was previously completed in 2023 which included installation of padmount transformers. Costs shown in 2024 include minor closeout trailing costs. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | Project was anticipated to be completed during the 2019 GRC cycle but had minor trailing costs in 2024.
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- ENERGIZED TEST YARD |  |  |  | Yes |  |  | 52414.856 | 0 | 0 | 0 | 52414.856 | 0 | 0 | 0 | 0 | 0 | 52414.856 | 0 | 0 | 0 | 52414.856 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- MANAGEMENT OF OH DIST. SERVICE | Electric Infrastructure Integrity | Management of Overhead Distribution Service (Non-CMP) | N/A | No | On-going | Annual | 10643741.7925 | 0 | 0 | 0 | 10643741.7925 | 10176000 | 10480999.92 | 10794999.96 | 11118999.96 | 10176000 | 467741.7925 | -10480999.92 | -10794999.96 | -11118999.96 | 467741.7925 | 4.597% | -100% | -100% | -100% | 4.597% | Overhead transformer forced outages requiring crew in-kind replacements | 101 |  |  |  | 101 | 160 |  |  |  | 160 | -59 | 0 | 0 | 0 | -59 | -36.88% | 0% | 0% | 0% | -36.88% | YES | NO | YES | N/A | Transformer in-kind replacements were lower than authorized in 2024, however cost per job was increased due to the need for upgraded transformer sizes and additional overhead electrical equipment needed to complete jobs. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project is required to reinforce the electric overhead distribution system infrastructure by responsive action to system damages, deterioration and unsafe conditions outside normal restoration of service. The overall objective is to maintain continuity of safe and reliable customer service. | SDG&E-11-R OR-95 to OR-97 CWP 002260
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- MANAGEMENT OF OH DIST. SERVICE |  |  |  | Yes |  |  | 10643741.7925 | 0 | 0 | 0 | 10643741.7925 | 10176000 | 10480999.92 | 10794999.96 | 11118999.96 | 10176000 | 467741.7925 | -10480999.92 | -10794999.96 | -11118999.96 | 467741.7925 | 4.597% | -100% | -100% | -100% | 4.597% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- MANAGEMENT OF UG DIST. SERVICE | Electric Infrastructure Integrity | Management of Underground Distribution Service | N/A | No | On-going | Annual | 6217438.171 | 0 | 0 | 0 | 6217438.171 | 4203999.96 | 4329999.96 | 4459999.92 | 4593999.96 | 4203999.96 | 2013438.211 | -4329999.96 | -4459999.92 | -4593999.96 | 2013438.211 | 47.89% | -100% | -100% | -100% | 47.89% | Underground transformer forced outages requiring crew in-kind replacement | 265 |  |  |  | 265 | 260 |  |  |  | 260 | 5 | 0 | 0 | 0 | 5 | 1.923% | 0% | 0% | 0% | 1.923% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- MANAGEMENT OF UG DIST. SERVICE |  |  |  | Yes |  |  | 6217438.171 | 0 | 0 | 0 | 6217438.171 | 4203999.96 | 4329999.96 | 4459999.92 | 4593999.96 | 4203999.96 | 2013438.211 | -4329999.96 | -4459999.92 | -4593999.96 | 2013438.211 | 47.89% | -100% | -100% | -100% | 47.89% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- MIRAMAR 12KV REPLACEMENTS | Electric Infrastructure Integrity | Substation Reliability for Distribution Components Miramar 12kV Replacements | Substation | No | 3 | 3 | 39854.6104 | 0 | 0 | 0 | 39854.6104 | 123999.96 | 127999.92 | 132000 | 135999.96 | 123999.96 | -84145.3496 | -127999.92 | -132000 | -135999.96 | -84145.3496 | -67.86% | -100% | -100% | -100% | -67.86% | The purpose of this project is to replace the existing 12kV breakers. 2024 costs and activities include procurement of 16 12kV breakers. Breaker installation and energization is expected in 2025. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | Over (O) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- MIRAMAR 12KV REPLACEMENTS |  |  |  | Yes |  |  | 39854.6104 | 0 | 0 | 0 | 39854.6104 | 123999.96 | 127999.92 | 132000 | 135999.96 | 123999.96 | -84145.3496 | -127999.92 | -132000 | -135999.96 | -84145.3496 | -67.86% | -100% | -100% | -100% | -67.86% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- MISSION 12KV REPLACEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | 4 | 5 | 1372390.4749 | 0 | 0 | 0 | 1372390.4749 | 0 | 0 | 0 | 0 | 0 | 1372390.4749 | 0 | 0 | 0 | 1372390.4749 | 100% | 0% | 0% | 0% | 100% | Breakers replaced | 12 |  |  |  | 12 | 3 |  |  |  | 3 | 9 | 0 | 0 | 0 | 9 | 300% | 0% | 0% | 0% | 300% | YES | NO | YES | N/A | Units were originally anticipated to be installed in prior years, but were deferred to 2024 due to higher number of reactive jobs in 2023. | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle. | This project removes and replaces circuit breaker(s) and relay(s) due to aging infrastructure, operational limitations, environmental concerns, and to meet current reliability standards. | SDG&E-11-R OR-134 to OR-135 CWP 202680
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- MISSION 12KV REPLACEMENTS |  |  |  | Yes |  |  | 1372390.4749 | 0 | 0 | 0 | 1372390.4749 | 0 | 0 | 0 | 0 | 0 | 1372390.4749 | 0 | 0 | 0 | 1372390.4749 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- NORTH HARBOR | Electric Infrastructure Integrity | Underground Cable Replacement Program Proactive North Harbor Project | UG Distribution | No | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 9729999.96 | 10021999.92 | 10323000 | 10632999.96 | 9729999.96 | -9729999.96 | -10021999.92 | -10323000 | -10632999.96 | -9729999.96 | -100% | -100% | -100% | -100% | -100% | Cable installed (ft) | 0 |  |  |  | 0 | 20205 |  |  |  | 20205 | -20205 | 0 | 0 | 0 | -20205 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | No actual cost driven by an increase in responsive and new business projects in 2024. | No actual units driven by an increase in responsive and new business projects in 2024. | On Target (T) | Over (O) | On Target (T) | Proceeding as Planned | YES | Project is delayed due to an increase in responsive and new business projects in 2024. | This project addresses identified safety and service reliability issues associated with the electrical distribution circuit providing service to the San Diego International Airport. The removal, replacement, and expansion of components of this underground cable addresses safety concerns regarding potential asbestos exposure in the area and the potential for long duration outage events and associated regulatory scrutiny and penalties associated with a cable failure. | SDG&E-11-R OR-120 to OR-121 CWP 17264A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- NORTH HARBOR |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 9729999.96 | 10021999.92 | 10323000 | 10632999.96 | 9729999.96 | -9729999.96 | -10021999.92 | -10323000 | -10632999.96 | -9729999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | YES | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | RAMP- OH PUBLIC SAFETY (OPS) | Electric Infrastructure Integrity | Overhead Public Safety (OPS) Program | OH Distribution | No | On-going | Annual | 290606.7644 | 0 | 0 | 0 | 290606.7644 | 8464999.92 | 8718999.96 | 8980999.92 | 9249999.96 | 8464999.92 | -8174393.1556 | -8718999.96 | -8980999.92 | -9249999.96 | -8174393.1556 | -96.57% | -100% | -100% | -100% | -96.57% | Miles of conductor replaced | 0 |  |  |  | 0 | 8 |  |  |  | 8 | -8 | 0 | 0 | 0 | -8 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | Lower actual costs driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | Lower actual costs and units driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | This program involves proactively replacing high-risk overhead (OH) conductors prone to wire down events measured as tracked by failure rates, historic wire down events, Corrective maintenance program records and lack of protection (fuse or advanced) that are in proximity to the public (schools, freeways, high profile areas) that could put the public at risk of energized contact. | SDG&E-11-R OR-160 to OR-161 CWP 202410
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- OH PUBLIC SAFETY (OPS) |  |  |  | Yes |  |  | 290606.7644 | 0 | 0 | 0 | 290606.7644 | 8464999.92 | 8718999.96 | 8980999.92 | 9249999.96 | 8464999.92 | -8174393.1556 | -8718999.96 | -8980999.92 | -9249999.96 | -8174393.1556 | -96.57% | -100% | -100% | -100% | -96.57% | [21 empty] | YES | YES | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | RAMP- PLANNED CABLE REPLACEMENTS | Electric Infrastructure Integrity | Underground Cable Replacement Program Proactive | UG Distribution | No | On-going | Annual | 3307576.6794 | 0 | 0 | 0 | 3307576.6794 | 4300999.92 | 4429999.92 | 4563000 | 4699999.92 | 4300999.92 | -993423.2406 | -4429999.92 | -4563000 | -4699999.92 | -993423.2406 | -23.1% | -100% | -100% | -100% | -23.1% | Miles of Conductor Replaced | 19.2 |  |  |  | 19.2 | 38 |  |  |  | 38 | -18.8 | 0 | 0 | 0 | -18.8 | -49.47% | 0% | 0% | 0% | -49.47% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This program facilitates the replacement of underground cable that was identified to have a high probability of failure based on electric reliability circuit analysis and cable failure data. | SDG&E-11-R OR-102 to OR-103 CWP 002380
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- PLANNED CABLE REPLACEMENTS |  |  |  | Yes |  |  | 3307576.6794 | 0 | 0 | 0 | 3307576.6794 | 4300999.92 | 4429999.92 | 4563000 | 4699999.92 | 4300999.92 | -993423.2406 | -4429999.92 | -4563000 | -4699999.92 | -993423.2406 | -23.1% | -100% | -100% | -100% | -23.1% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- POWER QUALITY PROGRAM | Electric Infrastructure Integrity | Power Quality Monitor Deployment and Replacement | N/A | No | On-going | Annual | 284694.2794 | 0 | 0 | 0 | 284694.2794 | 2883999.96 | 2970000 | 3058999.92 | 3150999.96 | 2883999.96 | -2599305.6806 | -2970000 | -3058999.92 | -3150999.96 | -2599305.6806 | -90.13% | -100% | -100% | -100% | -90.13% | Meters replaced | 7 |  |  |  | 7 | 5 |  |  |  | 5 | 2 | 0 | 0 | 0 | 2 | 40% | 0% | 0% | 0% | 40% | YES | NO | YES | N/A | Project team was able to exceed forecast due to delayed jobs from 2023 into 2024. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This program provides funding for the expansion of the substation power quality monitoring system (PQ Nodes) and associated communication system. This system improvement will allow an increase of data to be collected, which will result in a more effective grid reliability assessment. | SDG&E-11-R OR-145 to OR-146 CWP 942410
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- POWER QUALITY PROGRAM |  |  |  | Yes |  |  | 284694.2794 | 0 | 0 | 0 | 284694.2794 | 2883999.96 | 2970000 | 3058999.92 | 3150999.96 | 2883999.96 | -2599305.6806 | -2970000 | -3058999.92 | -3150999.96 | -2599305.6806 | -90.13% | -100% | -100% | -100% | -90.13% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- PROACTIVE DEAD FRONT TERMINATOR DEPLOY | Electric Infrastructure Integrity | Replacement of Live Front Equipment - Proactive | UG Distribution | No | On-going | Annual | 62710.6761 | 0 | 0 | 0 | 62710.6761 | 885000 | 912000 | 939000 | 966999.96 | 885000 | -822289.3239 | -912000 | -939000 | -966999.96 | -822289.3239 | -92.91% | -100% | -100% | -100% | -92.91% | Terminators Replaced | 0 |  |  |  | 0 | 15 |  |  |  | 15 | -15 | 0 | 0 | 0 | -15 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The new dead front terminators (UG 3517, 3518) will be deployed in strategic areas to improve distribution circuit reliability, such as where large customer segments can be further sectionalized in small padmount applications. Funding for this program assumes a target of 15 locations each year where live front terminators currently exist. Limited cable replacements will be included in this work as directly related to making up new cable terminations. | SDG&E-11-R OR-158 to OR-160 CWP 192410
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- PROACTIVE DEAD FRONT TERMINATOR DEPLOY |  |  |  | Yes |  |  | 62710.6761 | 0 | 0 | 0 | 62710.6761 | 885000 | 912000 | 939000 | 966999.96 | 885000 | -822289.3239 | -912000 | -939000 | -966999.96 | -822289.3239 | -92.91% | -100% | -100% | -100% | -92.91% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- REPLACEMENT OF LIVE FRONT EQUIPMENT | Electric Infrastructure Integrity | Replacement of Live Front Equipment - Reactive | N/A | No | On-going | Annual | 1461.7981 | 0 | 0 | 0 | 1461.7981 | 457999.92 | 471999.96 | 486000 | 501000 | 457999.92 | -456538.1219 | -471999.96 | -486000 | -501000 | -456538.1219 | -99.68% | -100% | -100% | -100% | -99.68% | Terminators Replaced | 0 |  |  |  | 0 | 6 |  |  |  | 6 | -6 | 0 | 0 | 0 | -6 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | Lower actual costs and units driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | The purpose of this project is to replace live front (energized) padmounted distribution equipment with dead front (de-energized) padmounted distribution equipment when it is encountered during normal SDG&E work. | SDG&E-11-R OR-149 to OR-150 CWP 062470
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- REPLACEMENT OF LIVE FRONT EQUIPMENT |  |  |  | Yes |  |  | 1461.7981 | 0 | 0 | 0 | 1461.7981 | 457999.92 | 471999.96 | 486000 | 501000 | 457999.92 | -456538.1219 | -471999.96 | -486000 | -501000 | -456538.1219 | -99.68% | -100% | -100% | -100% | -99.68% | [21 empty] | YES | NO | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | RAMP- REPLACEMENT OF UNDERGROUND CABLES | Electric Infrastructure Integrity | Underground Cable Replacement Program Reactive | N/A | No | On-going | Annual | 6595683.4153 | 0 | 0 | 0 | 6595683.4153 | 7269999.96 | 7488000 | 7713000 | 7944000 | 7269999.96 | -674316.5447 | -7488000 | -7713000 | -7944000 | -674316.5447 | -9.275% | -100% | -100% | -100% | -9.275% | Distribution UG cable outages requiring crew replacement | 533 |  |  |  | 533 | 350 |  |  |  | 350 | 183 | 0 | 0 | 0 | 183 | 52.29% | 0% | 0% | 0% | 52.29% | YES | NO | YES | N/A | 2024 had a higher average number of outages compared to recent prior years primarily driven by a September heat event. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The project facilitates the responsive replacement of underground cable that has failed or has operated outside of its intended threshold of rated operation. | SDG&E-11-R OR-99 to OR-100 CWP 002300
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- REPLACEMENT OF UNDERGROUND CABLES |  |  |  | Yes |  |  | 6595683.4153 | 0 | 0 | 0 | 6595683.4153 | 7269999.96 | 7488000 | 7713000 | 7944000 | 7269999.96 | -674316.5447 | -7488000 | -7713000 | -7944000 | -674316.5447 | -9.275% | -100% | -100% | -100% | -9.275% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- RTU MODERNIZATION | Electric Infrastructure Integrity | Field SCADA RTU Replacement | UG Distribution | No | On-going | Annual | 771162.5481 | 0 | 0 | 0 | 771162.5481 | 792000 | 816000 | 840000 | 864999.96 | 792000 | -20837.4519 | -816000 | -840000 | -864999.96 | -20837.4519 | -2.631% | -100% | -100% | -100% | -2.631% | Remote Terminal Units (RTU) replaced | 10 |  |  |  | 10 | 15 |  |  |  | 15 | -5 | 0 | 0 | 0 | -5 | -33.33% | 0% | 0% | 0% | -33.33% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project helps ensure safe operation of the distribution system by replacing legacy and end-of-life RMS900 Remote Terminal Units (RTU) in existing pad mounted transformers. Replacing these devices is vital for Electric Distribution Operations and SDG&E's grid reliability. This RTU modernization project will allow SDG&E to accomplish reliability goals, control costs, and better serve customers. | SDG&E-11-R OR-153 to OR-155 CWP 162770
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- RTU MODERNIZATION |  |  |  | Yes |  |  | 771162.5481 | 0 | 0 | 0 | 771162.5481 | 792000 | 816000 | 840000 | 864999.96 | 792000 | -20837.4519 | -816000 | -840000 | -864999.96 | -20837.4519 | -2.631% | -100% | -100% | -100% | -2.631% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- SAN MARCOS SUB REBUILD 69KV & 12KV | Electric Infrastructure Integrity | San Marcos Substation 69kV Rebuild & 12kV Switchgear | Substation | No | 8 | Canceled | -408022.45 | 0 | 0 | 0 | -408022.45 | 126999.96 | 130999.92 | 135000 | 138999.96 | 126999.96 | -535022.41 | -130999.92 | -135000 | -138999.96 | -535022.41 | -421.3% | -100% | -100% | -100% | -421.3% | Breakers installed | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Project is canceled due to internal evaluation showing equipment does not need to be replaced at this time. | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | Upgrade the 69kV bus, replace all 69kV insulators, disconnects, potential transformers, protection and controls. Replace existing control shelter with a new block shelter. Replace Bk 32’s 12kV switchgear with new switchgear (sized to fit on existing foundation) and cutover existing 12kV circuits to new switchgear. Replace and relocate existing 12kV capacitors. | SDG&E-11-R OR-115 to OR-116 CWP 171600
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- SAN MARCOS SUB REBUILD 69KV & 12KV |  |  |  | Yes |  |  | -408022.45 | 0 | 0 | 0 | -408022.45 | 126999.96 | 130999.92 | 135000 | 138999.96 | 126999.96 | -535022.41 | -130999.92 | -135000 | -138999.96 | -535022.41 | -421.3% | -100% | -100% | -100% | -421.3% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- SUBSTATION SCADA EXPANSION-DISTRIBUTION | Electric Infrastructure Integrity | Distribution Substation SCADA Expansion | N/A | No | On-going | Annual | 413311.0112 | 0 | 0 | 0 | 413311.0112 | 2226999.96 | 2293999.92 | 2362999.92 | 2433999.96 | 2226999.96 | -1813688.9488 | -2293999.92 | -2362999.92 | -2433999.96 | -1813688.9488 | -81.44% | -100% | -100% | -100% | -81.44% | Relays installed | 0 |  |  |  | 0 | 20 |  |  |  | 20 | -20 | 0 | 0 | 0 | -20 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project provides funding for the installation, upgrades, and expansion of the Supervisory Control and Data Acquisition (SCADA) system at substations for the distribution portion in substations. | SDG&E-11-R OR-113 to OR-114 CWP 152430
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- SUBSTATION SCADA EXPANSION-DISTRIBUTION |  |  |  | Yes |  |  | 413311.0112 | 0 | 0 | 0 | 413311.0112 | 2226999.96 | 2293999.92 | 2362999.92 | 2433999.96 | 2226999.96 | -1813688.9488 | -2293999.92 | -2362999.92 | -2433999.96 | -1813688.9488 | -81.44% | -100% | -100% | -100% | -81.44% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- SUBSTATION MOD TO SUPPORT FLISR | Non-RAMP | Non-RAMP | Non-RAMP | No | 6 | Completed | 34174.1568 | 0 | 0 | 0 | 34174.1568 | 0 | 0 | 0 | 0 | 0 | 34174.1568 | 0 | 0 | 0 | 34174.1568 | 100% | 0% | 0% | 0% | 100% | This project was previously completed in 2022. Actual costs in 2024 represent close out spend. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- SUBSTATION MOD TO SUPPORT FLISR |  |  |  | Yes |  |  | 34174.1568 | 0 | 0 | 0 | 34174.1568 | 0 | 0 | 0 | 0 | 0 | 34174.1568 | 0 | 0 | 0 | 34174.1568 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- TEE MODERNIZATION PROGRAM | Electric Infrastructure Integrity | Tee Modernization Program | UG Distribution | No | On-going | Annual | 4922184.7913 | 0 | 0 | 0 | 4922184.7913 | 4431999.96 | 4564999.92 | 4701999.96 | 4842999.96 | 4431999.96 | 490184.8313 | -4564999.92 | -4701999.96 | -4842999.96 | 490184.8313 | 11.06% | -100% | -100% | -100% | 11.06% | Tees replaced | 253 |  |  |  | 253 | 130 |  |  |  | 130 | 123 | 0 | 0 | 0 | 123 | 94.62% | 0% | 0% | 0% | 94.62% | YES | NO | YES | N/A | The variance is due to additional tees replaced as a result of lower negotiated unit pricing. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The primary objective of this project is to improve reliability. Tee connector failures have become one of the largest contributors to system SAIDI and SAIFI over the last few years. One of the most frequently failed components of Tees are the double-ended plug. This component is not used with the modern replacement for the tee; the Cleer connector. This new design will improve reliability by removing the known common point of failure and also provide additional sectionalizing capabilities for overall circuit operation. | SDG&E-11-R OR-155 to OR-156 CWP 172550
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- TEE MODERNIZATION PROGRAM |  |  |  | Yes |  |  | 4922184.7913 | 0 | 0 | 0 | 4922184.7913 | 4431999.96 | 4564999.92 | 4701999.96 | 4842999.96 | 4431999.96 | 490184.8313 | -4564999.92 | -4701999.96 | -4842999.96 | 490184.8313 | 11.06% | -100% | -100% | -100% | 11.06% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- TORREY PINES 12KV BREAKER REPLACEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 5 | 858683.4809 | 0 | 0 | 0 | 858683.4809 | 0 | 0 | 0 | 0 | 0 | 858683.4809 | 0 | 0 | 0 | 858683.4809 | 100% | 0% | 0% | 0% | 100% | The purpose of this project is to replace the existing 12kV breakers. 2024 costs and activities include initial constuction and replacement costs with energization of the breakers replaced beginning in 2025. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- TORREY PINES 12KV BREAKER REPLACEMENT |  |  |  | Yes |  |  | 858683.4809 | 0 | 0 | 0 | 858683.4809 | 0 | 0 | 0 | 0 | 0 | 858683.4809 | 0 | 0 | 0 | 858683.4809 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP- URBAN SUBSTATION REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | No | 4 | 5 | 463710.5787 | 0 | 0 | 0 | 463710.5787 | 0 | 0 | 0 | 0 | 0 | 463710.5787 | 0 | 0 | 0 | 463710.5787 | 100% | 0% | 0% | 0% | 100% | The purpose of this project is to replace the existing 12kV switchgear which currently has temporary repairs to the roof. In order to accomplish this, a new concrete masonry unit (CMU) wall will need to be constructed extending the current wall to the property line allowing us to reliably serve the fourteen (14) existing 12kV circuits while building the new 12kV switchgear. 2024 costs and activities include phase 1 wall construction and related support services. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP- URBAN SUBSTATION REBUILD |  |  |  | Yes |  |  | 463710.5787 | 0 | 0 | 0 | 463710.5787 | 0 | 0 | 0 | 0 | 0 | 463710.5787 | 0 | 0 | 0 | 463710.5787 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RAMP-NON-HFTD WIRELESS FAULT INDICATORS | Electric Infrastructure Integrity | Non-HFTD Wireless Fault Indicator | OH Distribution | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 1557999.96 | 1605000 | 1653000 | 1702999.92 | 1557999.96 | -1557999.96 | -1605000 | -1653000 | -1702999.92 | -1557999.96 | -100% | -100% | -100% | -100% | -100% | Wireless Fault Indicators (WFIs) | 0 |  |  |  | 0 | 800 |  |  |  | 800 | -800 | 0 | 0 | 0 | -800 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Project deferred as a result of an increase in high priority work including responsive and new business projects. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This project provides a way to rapidly identify and locate faults on distribution circuits via wireless fault indicators (WFI). The scope is to install wireless fault indicators (WFIs) on conductors. This will reduce outage and repair times, improving reliability. | SDG&E-11-R OR-140 to OR-142 CWP 202880
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP-NON-HFTD WIRELESS FAULT INDICATORS |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 1557999.96 | 1605000 | 1653000 | 1702999.92 | 1557999.96 | -1557999.96 | -1605000 | -1653000 | -1702999.92 | -1557999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | RAMP-STRATEGIC POLE REPLACEMENT PROGRAM (NON-HFTD) | Electric Infrastructure Integrity | Strategic Pole Replacement Program (Non-HFTD) | OH Distribution | No | On-going | Annual | 12772.2659 | 0 | 0 | 0 | 12772.2659 | 7512999.96 | 7737999.96 | 7969999.92 | 8208999.96 | 7512999.96 | -7500227.6941 | -7737999.96 | -7969999.92 | -8208999.96 | -7500227.6941 | -99.83% | -100% | -100% | -100% | -99.83% | Poles replaced | 0 |  |  |  | 0 | 225 |  |  |  | 225 | -225 | 0 | 0 | 0 | -225 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | Lower actual cost was driven by shift from this non-high fire threat district (non-HFTD) workpaper to Strategic Pole Replacement (SPRP) - (WMP) workpaper 22242.0 in the HFTD. | Lower actual unit count was driven by shift from this non-high fire threat district (non-HFTD) workpaper to Strategic Pole Replacement (SPRP) - (WMP) workpaper 22242.0 in the HFTD. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This program will have multiple categories of risk. We are prioritizing gas-treated wood poles in combination with steel reinforced and encased in concrete. Based on research, it has been determined that the gas-treated poles are considered high priority based on the poles interaction with the moisture in the soil. In combination with identified rot and inspection limitations of the pole being in concrete, SDG&E believes these are the highest risk group of poles to target. As SDG&E investigates further, there may be other contributing factors that presents risks that need to be mitigated and/or priortized. | SDG&E-11-R OR-165 to OR-167 CWP 222410
Capital | ELECTRIC DISTRIBUTION | SubTotal RAMP-STRATEGIC POLE REPLACEMENT PROGRAM (NON-HFTD) |  |  |  | Yes |  |  | 12772.2659 | 0 | 0 | 0 | 12772.2659 | 7512999.96 | 7737999.96 | 7969999.92 | 8208999.96 | 7512999.96 | -7500227.6941 | -7737999.96 | -7969999.92 | -8208999.96 | -7500227.6941 | -99.83% | -100% | -100% | -100% | -99.83% | [21 empty] | YES | YES | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | REACTIVE SMALL CAPITAL PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3110031.1479 | 0 | 0 | 0 | 3110031.1479 | 1576999.92 | 1623999.96 | 1672999.92 | 1722999.96 | 1576999.92 | 1533031.2279 | -1623999.96 | -1672999.92 | -1722999.96 | 1533031.2279 | 97.21% | -100% | -100% | -100% | 97.21% | This responsive blanket program addresses primary distribution system overload and voltage-related issues with individual capital jobs identified on the forecast process. It provides for the reconstruction and extension of overhead and underground distribution facilities to replace overloaded conductors, to correct primary voltage problems, and to transfer load to balance circuits and substations. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal REACTIVE SMALL CAPITAL PROJECTS |  |  |  | Yes |  |  | 3110031.1479 | 0 | 0 | 0 | 3110031.1479 | 1576999.92 | 1623999.96 | 1672999.92 | 1722999.96 | 1576999.92 | 1533031.2279 | -1623999.96 | -1672999.92 | -1722999.96 | 1533031.2279 | 97.21% | -100% | -100% | -100% | 97.21% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SF6 SWITCH REPLACEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 67464.3065 | 0 | 0 | 0 | 67464.3065 | 7875999.96 | 8112000 | 8355000 | 8605999.92 | 7875999.96 | -7808535.6535 | -8112000 | -8355000 | -8605999.92 | -7808535.6535 | -99.14% | -100% | -100% | -100% | -99.14% | SF6 switches replaced | 0 |  |  |  | 0 | 28 |  |  |  | 28 | -28 | 0 | 0 | 0 | -28 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | Lower actual costs driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | Lower actual costs and units driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | The primary objective of this initiative is to reduce environmental risks associated with the potential for SF6 emissions. | SDG&E-11-R OR-150 to OR-152 CWP 142490
Capital | ELECTRIC DISTRIBUTION | SubTotal SF6 SWITCH REPLACEMENT |  |  |  | Yes |  |  | 67464.3065 | 0 | 0 | 0 | 67464.3065 | 7875999.96 | 8112000 | 8355000 | 8605999.92 | 7875999.96 | -7808535.6535 | -8112000 | -8355000 | -8605999.92 | -7808535.6535 | -99.14% | -100% | -100% | -100% | -99.14% | [21 empty] | YES | YES | [7 empty] | YES
Capital | ELECTRIC DISTRIBUTION | SOUTH ORANGE COUNTY RELIABILITY ENHANCEMENT (SOCRE) | Non-RAMP | Non-RAMP | Non-RAMP | No | 8 | 8 | 268144.1598 | 0 | 0 | 0 | 268144.1598 | 112999.92 | 117000 | 120999.96 | 124999.92 | 112999.92 | 155144.2398 | -117000 | -120999.96 | -124999.92 | 155144.2398 | 137.3% | -100% | -100% | -100% | 137.3% | The scope of this project includes rebuilding the existing Capistrano Substation, from a 138/12kV distribution substation to a 230/138kV, removing transmission line TL13835 between Talega Substation and Capistrano Substation, opening transmission line TL23007 at Talega Substation, and looping in two new 230kV transmission lines into Capistrano Substation. 2024 costs and activities include distribution substation work at San Juan Capistrano substation. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal SOUTH ORANGE COUNTY RELIABILITY ENHANCEMENT (SOCRE) |  |  |  | Yes |  |  | 268144.1598 | 0 | 0 | 0 | 268144.1598 | 112999.92 | 117000 | 120999.96 | 124999.92 | 112999.92 | 155144.2398 | -117000 | -120999.96 | -124999.92 | 155144.2398 | 137.3% | -100% | -100% | -100% | 137.3% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | STREAMVIEW 69/12KV SUB REBUILD-PRE ENG | Non-RAMP | Non-RAMP | Non-RAMP | No | 8 | 8 | 3023980.8658 | 0 | 0 | 0 | 3023980.8658 | 198999.96 | 204999.96 | 210999.96 | 216999.96 | 198999.96 | 2824980.9058 | -204999.96 | -210999.96 | -216999.96 | 2824980.9058 | 1420% | -100% | -100% | -100% | 1420% | This is a full substation rebuild major project that is currently in construction but was delayed several years due to land acquisition and permitting challenges. The project scope includes a variety of different types of activities both inside and outside the substation perimeter, which makes it infeasible to identify and track a single unit of measure. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | Over (O) | Over (O) | Other | NO | Project was delayed from the 2019 GRC cycle and scheduled to be completed within the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal STREAMVIEW 69/12KV SUB REBUILD-PRE ENG |  |  |  | Yes |  |  | 3023980.8658 | 0 | 0 | 0 | 3023980.8658 | 198999.96 | 204999.96 | 210999.96 | 216999.96 | 198999.96 | 2824980.9058 | -204999.96 | -210999.96 | -216999.96 | 2824980.9058 | 1420% | -100% | -100% | -100% | 1420% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | STREET LIGHT MODERNIZATION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 857964.8723 | 0 | 0 | 0 | 857964.8723 | 4462999.92 | 4596999.96 | 4734999.96 | 4876999.92 | 4462999.92 | -3605035.0477 | -4596999.96 | -4734999.96 | -4876999.92 | -3605035.0477 | -80.78% | -100% | -100% | -100% | -80.78% | LED Lights | 1383 |  |  |  | 1383 | 2000 |  |  |  | 2000 | -617 | 0 | 0 | 0 | -617 | -30.85% | 0% | 0% | 0% | -30.85% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project targets modernizing street lighting system owned by SDG&E to LEDs. In addition, based on location and current condition of poles, pole replacement might be required with street light modernization. The current scope will cover every operational district utilyzing a block per block approach rather than a failure replacement approach. | SDG&E-11-R OR-61 to OR-62 CWP 172620
Capital | ELECTRIC DISTRIBUTION | SubTotal STREET LIGHT MODERNIZATION |  |  |  | Yes |  |  | 857964.8723 | 0 | 0 | 0 | 857964.8723 | 4462999.92 | 4596999.96 | 4734999.96 | 4876999.92 | 4462999.92 | -3605035.0477 | -4596999.96 | -4734999.96 | -4876999.92 | -3605035.0477 | -80.78% | -100% | -100% | -100% | -80.78% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SUBSTATION 12KV CAPACITOR UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 703010.5072 | 0 | 0 | 0 | 703010.5072 | 1611000 | 1659000 | 1708999.92 | 1759999.92 | 1611000 | -907989.4928 | -1659000 | -1708999.92 | -1759999.92 | -907989.4928 | -56.36% | -100% | -100% | -100% | -56.36% | Capacitor banks energized | 1 |  |  |  | 1 | 2 |  |  |  | 2 | -1 | 0 | 0 | 0 | -1 | -50% | 0% | 0% | 0% | -50% | YES | NO | YES | N/A | Lower actual unit count driven by an increase in responsive and New Business projects in 2024, which utilized resources from proactive reliability projects during the period. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Replace existing single-step capacitor banks at selected substations with banks of increased capacity and multiple steps. Add capacitor banks where the power factor is below minimum requirements. Add capacitor and reactor banks where the power factor is below minimum requirements. | SDG&E-11-R OR-32 to OR-33 CWP 082530
Capital | ELECTRIC DISTRIBUTION | SubTotal SUBSTATION 12KV CAPACITOR UPGRADES |  |  |  | Yes |  |  | 703010.5072 | 0 | 0 | 0 | 703010.5072 | 1611000 | 1659000 | 1708999.92 | 1759999.92 | 1611000 | -907989.4928 | -1659000 | -1708999.92 | -1759999.92 | -907989.4928 | -56.36% | -100% | -100% | -100% | -56.36% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TRANSFORMER & METER INSTALLATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 9477792.2103 | 0 | 0 | 0 | 9477792.2103 | 11716999.92 | 12069000 | 12430999.92 | 12804000 | 11716999.92 | -2239207.7097 | -12069000 | -12430999.92 | -12804000 | -2239207.7097 | -19.11% | -100% | -100% | -100% | -19.11% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal TRANSFORMER & METER INSTALLATIONS |  |  |  | Yes |  |  | 9477792.2103 | 0 | 0 | 0 | 9477792.2103 | 11716999.92 | 12069000 | 12430999.92 | 12804000 | 11716999.92 | -2239207.7097 | -12069000 | -12430999.92 | -12804000 | -2239207.7097 | -19.11% | -100% | -100% | -100% | -19.11% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TRANSFORMERS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 83157014.94 | 0 | 0 | 0 | 83157014.94 | 33174000 | 34168999.92 | 35193999.96 | 36249999.96 | 33174000 | 49983014.94 | -34168999.92 | -35193999.96 | -36249999.96 | 49983014.94 | 150.7% | -100% | -100% | -100% | 150.7% | Transformers purchased | 7302 |  |  |  | 7302 | 6999 |  |  |  | 6999 | 303 | 0 | 0 | 0 | 303 | 4.329% | 0% | 0% | 0% | 4.329% | YES | YES | NO | The funding for this ongoing program supports purchasing new distribution transformers that will provide service to SDG&E's electric distribution customers. These purchases are required to maintain inventory levels at SDG&E's electric distribution service centers. The cost variance is due to a significant increase in the average cost per unit caused by both price increases and a change in the mix of transformer demand to larger electrical rated units to meet current and future demand for customer electrification. Long lead-times caused by data center demand, shortages in domestic supply leading to purchasing from foreign suppliers, and high raw material prices are driving up unit-costs. | N/A | Over (O) | On Target (T) | Over (O) | Expanded | NO | N/A | This blanket budget provides the funds to purchase new line transformers. Materials are required to support the electric distribution system. The funds for this blanket budget are required to purchase new line transformers to be used to service the electric distribution system's customers. It is required to maintain inventory levels at each of the electric distribution service centers. | SDG&E-11-R OR-65 CWP 002140
Capital | ELECTRIC DISTRIBUTION | SubTotal TRANSFORMERS |  |  |  | Yes |  |  | 83157014.94 | 0 | 0 | 0 | 83157014.94 | 33174000 | 34168999.92 | 35193999.96 | 36249999.96 | 33174000 | 49983014.94 | -34168999.92 | -35193999.96 | -36249999.96 | 49983014.94 | 150.7% | -100% | -100% | -100% | 150.7% | [21 empty] | YES | YES | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TRANSMISSION CORRECTIVE MAINTENANCE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2473620.6697 | 0 | 0 | 0 | 2473620.6697 | 3769999.92 | 3882999.96 | 3999000 | 4119000 | 3769999.92 | -1296379.2503 | -3882999.96 | -3999000 | -4119000 | -1296379.2503 | -34.39% | -100% | -100% | -100% | -34.39% | Poles replaced | 105 |  |  |  | 105 | 80 |  |  |  | 80 | 25 | 0 | 0 | 0 | 25 | 31.25% | 0% | 0% | 0% | 31.25% | YES | NO | YES | N/A | The number of poles replaced increased due to the responsive nature of findings determined in routine annual inspection. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This program supports SDG&E's obligation to serve and meet safety requirements promulgated by various legislative and Commission requirements, e.g., CPUC General Order 95, Assembly Bill 1890, and Assembly Bill 1017. This program annually replaces approximately 80 wooden poles in non- High Fire Threat Districts with steel poles. Distribution costs represent about 10% of costs associated with installing transmission poles with distribution underbuild. | SDG&E-11-R OR-174 CWP 201260
Capital | ELECTRIC DISTRIBUTION | SubTotal TRANSMISSION CORRECTIVE MAINTENANCE PROGRAM |  |  |  | Yes |  |  | 2473620.6697 | 0 | 0 | 0 | 2473620.6697 | 3769999.92 | 3882999.96 | 3999000 | 4119000 | 3769999.92 | -1296379.2503 | -3882999.96 | -3999000 | -4119000 | -1296379.2503 | -34.39% | -100% | -100% | -100% | -34.39% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | UG NON-RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 12609107.6087 | 0 | 0 | 0 | 12609107.6087 | 9693999.96 | 9984999.96 | 10284999.96 | 10593999.96 | 9693999.96 | 2915107.6487 | -9984999.96 | -10284999.96 | -10593999.96 | 2915107.6487 | 30.07% | -100% | -100% | -100% | 30.07% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal UG NON-RESIDENTIAL NB |  |  |  | Yes |  |  | 12609107.6087 | 0 | 0 | 0 | 12609107.6087 | 9693999.96 | 9984999.96 | 10284999.96 | 10593999.96 | 9693999.96 | 2915107.6487 | -9984999.96 | -10284999.96 | -10593999.96 | 2915107.6487 | 30.07% | -100% | -100% | -100% | 30.07% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | UG RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 13356102.1343 | 0 | 0 | 0 | 13356102.1343 | 9091999.92 | 9364999.92 | 9645999.96 | 9934999.92 | 9091999.92 | 4264102.2143 | -9364999.92 | -9645999.96 | -9934999.92 | 4264102.2143 | 46.9% | -100% | -100% | -100% | 46.9% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal UG RESIDENTIAL NB |  |  |  | Yes |  |  | 13356102.1343 | 0 | 0 | 0 | 13356102.1343 | 9091999.92 | 9364999.92 | 9645999.96 | 9934999.92 | 9091999.92 | 4264102.2143 | -9364999.92 | -9645999.96 | -9934999.92 | 4264102.2143 | 46.9% | -100% | -100% | -100% | 46.9% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ARTESIAN 230KV EXPANSION | Non-RAMP | Non-RAMP | Non-RAMP | No | 5 | 7 | 13220.84 | 0 | 0 | 0 | 13220.84 | 0 | 0 | 0 | 0 | 0 | 13220.84 | 0 | 0 | 0 | 13220.84 | 100% | 0% | 0% | 0% | 100% | This is a FERC-driven major project. Phase 1 included building a brand new 69/12kV substation, adjacent to the existing one, was energized in 2022 with close-out costs carrying over into 2024. Being a brand new substation, the scope of the project included a multitude of both substation and line-side distribution and transmission work. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal ARTESIAN 230KV EXPANSION |  |  |  | Yes |  |  | 13220.84 | 0 | 0 | 0 | 13220.84 | 0 | 0 | 0 | 0 | 0 | 13220.84 | 0 | 0 | 0 | 13220.84 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | BORREGO SPRINGS MICROGRID GENERATOR REPL | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 1 | 3487280.0703 | 0 | 0 | 0 | 3487280.0703 | 0 | 0 | 0 | 0 | 0 | 3487280.0703 | 0 | 0 | 0 | 3487280.0703 | 100% | 0% | 0% | 0% | 100% | This emergent project will replace the 2-1.8 MW Borrego Microgrid generators, with 2-2.50 MW generators. These generators are required to support the resiliency of the Borrego community during emergencies and extended planned outages to accommodate compliance substation and transmission system maintenance. 2024 activities included below grade construction for generator pads, transformer pads, material purchases (generator downpayment, cables), trenching/conduit install, services (environmental permitting, civil testing/mark outs) and labor (union/ non-union labor). The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal BORREGO SPRINGS MICROGRID GENERATOR REPL |  |  |  | Yes |  |  | 3487280.0703 | 0 | 0 | 0 | 3487280.0703 | 0 | 0 | 0 | 0 | 0 | 3487280.0703 | 0 | 0 | 0 | 3487280.0703 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | C1162, BD: NEW C1162 | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 3 | 23906.4778 | 0 | 0 | 0 | 23906.4778 | 0 | 0 | 0 | 0 | 0 | 23906.4778 | 0 | 0 | 0 | 23906.4778 | 100% | 0% | 0% | 0% | 100% | The purpose of this project is to install a new 12kV circuit (C1162) at Border substation to relieve overloading on circuit C536 associated with forecasted new load in the area. The project reconductored 5,700 feet of wire, trenched and installed 450 feet of conduit, and install one switch. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal C1162, BD: NEW C1162 |  |  |  | Yes |  |  | 23906.4778 | 0 | 0 | 0 | 23906.4778 | 0 | 0 | 0 | 0 | 0 | 23906.4778 | 0 | 0 | 0 | 23906.4778 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | C369, S: NEW 12KV TWIN CIRCUIT | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 3 | 68978.0767 | 0 | 0 | 0 | 68978.0767 | 0 | 0 | 0 | 0 | 0 | 68978.0767 | 0 | 0 | 0 | 68978.0767 | 100% | 0% | 0% | 0% | 100% | The purpose of this project is to install a new 12kV twin circuit C369 at Sampson substation to relieve overloading on an existing circuit associated with forecasted new load in the area. The project reconductors 2,500 feet of cable, trenches and installs 100 feet of conduit, installs one switch, and installs one capacitor. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal C369, S: NEW 12KV TWIN CIRCUIT |  |  |  | Yes |  |  | 68978.0767 | 0 | 0 | 0 | 68978.0767 | 0 | 0 | 0 | 0 | 0 | 68978.0767 | 0 | 0 | 0 | 68978.0767 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TRANSMISSION SUBSTATION RELIABILITY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 56460.7043 | 0 | 0 | 0 | 56460.7043 | 0 | 0 | 0 | 0 | 0 | 56460.7043 | 0 | 0 | 0 | 56460.7043 | 100% | 0% | 0% | 0% | 100% | This is an emergent project. The activities under this blanket workpaper includes minimal costs for distribution and communication component of the replacement of obsolete or failed substation equipment. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal TRANSMISSION SUBSTATION RELIABILITY |  |  |  | Yes |  |  | 56460.7043 | 0 | 0 | 0 | 56460.7043 | 0 | 0 | 0 | 0 | 0 | 56460.7043 | 0 | 0 | 0 | 56460.7043 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | C50, PTL: RECO AND CAPACITOR | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 4 | 20830.2521 | 0 | 0 | 0 | 20830.2521 | 0 | 0 | 0 | 0 | 0 | 20830.2521 | 0 | 0 | 0 | 20830.2521 | 100% | 0% | 0% | 0% | 100% | The purpose of this project is to reconductor existing 12kV circuit C50 at Point Loma substation to relieve overloading associated with forecasted new load in the area. The project will replace 1,800 feet of cable and install one capacitor bank. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal C50, PTL: RECO AND CAPACITOR |  |  |  | Yes |  |  | 20830.2521 | 0 | 0 | 0 | 20830.2521 | 0 | 0 | 0 | 0 | 0 | 20830.2521 | 0 | 0 | 0 | 20830.2521 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CBM - 4.2 FIRMWARE UPGRADE FOR TRANSFORM | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 4 | 14541.7556 | 0 | 0 | 0 | 14541.7556 | 0 | 0 | 0 | 0 | 0 | 14541.7556 | 0 | 0 | 0 | 14541.7556 | 100% | 0% | 0% | 0% | 100% | The project replaced/upgraded equipment and existing hardware/software at various substations that is used to monitor and provide numerous data points pertaining to the status of the transformers and ancilliary equipment data on the gases forming inside transformers. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Other | NO | Project was anticipated to be completed during the 2019 GRC cycle but had minor trailing costs in 2024.
Capital | ELECTRIC DISTRIBUTION | SubTotal CBM - 4.2 FIRMWARE UPGRADE FOR TRANSFORM |  |  |  | Yes |  |  | 14541.7556 | 0 | 0 | 0 | 14541.7556 | 0 | 0 | 0 | 0 | 0 | 14541.7556 | 0 | 0 | 0 | 14541.7556 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | COLLECTIBLE - CAMP PENDLETON - STUART MESA HOUSING | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 36627.4557 | 0 | 0 | 0 | 36627.4557 | 0 | 0 | 0 | 0 | 0 | 36627.4557 | 0 | 0 | 0 | 36627.4557 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal COLLECTIBLE - CAMP PENDLETON - STUART MESA HOUSING |  |  |  | Yes |  |  | 36627.4557 | 0 | 0 | 0 | 36627.4557 | 0 | 0 | 0 | 0 | 0 | 36627.4557 | 0 | 0 | 0 | 36627.4557 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TRANSMISSION SYSTEM AUTOMATION | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 80603.3316 | 0 | 0 | 0 | 80603.3316 | 0 | 0 | 0 | 0 | 0 | 80603.3316 | 0 | 0 | 0 | 80603.3316 | 100% | 0% | 0% | 0% | 100% | This is an on-going project. The activities under this blanket budget include a variety of different types of system protection engineering projects and initiatives related to transmission SCADA system upgrades and control and monitoring in support of Grid Operations. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal TRANSMISSION SYSTEM AUTOMATION |  |  |  | Yes |  |  | 80603.3316 | 0 | 0 | 0 | 80603.3316 | 0 | 0 | 0 | 0 | 0 | 80603.3316 | 0 | 0 | 0 | 80603.3316 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | VALENCIA POINTE RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | -3625.82 | 0 | 0 | 0 | -3625.82 | 0 | 0 | 0 | 0 | 0 | -3625.82 | 0 | 0 | 0 | -3625.82 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal VALENCIA POINTE RELOCATION |  |  |  | Yes |  |  | -3625.82 | 0 | 0 | 0 | -3625.82 | 0 | 0 | 0 | 0 | 0 | -3625.82 | 0 | 0 | 0 | -3625.82 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | CRITICAL ASSET SECURITY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | -25814.3379 | 0 | 0 | 0 | -25814.3379 | 0 | 0 | 0 | 0 | 0 | -25814.3379 | 0 | 0 | 0 | -25814.3379 | 100% | 0% | 0% | 0% | 100% | This program is focused on major transmission substation security upgrade projects. This includes different types of physical and electronic security technologies. The spend is primarily the CPUC portion of communication equipment installs and upgrades. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal CRITICAL ASSET SECURITY |  |  |  | Yes |  |  | -25814.3379 | 0 | 0 | 0 | -25814.3379 | 0 | 0 | 0 | 0 | 0 | -25814.3379 | 0 | 0 | 0 | -25814.3379 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | DPM DIGITAL LAYER | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1174256.9464 | 0 | 0 | 0 | 1174256.9464 | 0 | 0 | 0 | 0 | 0 | 1174256.9464 | 0 | 0 | 0 | 1174256.9464 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal DPM DIGITAL LAYER |  |  |  | Yes |  |  | 1174256.9464 | 0 | 0 | 0 | 1174256.9464 | 0 | 0 | 0 | 0 | 0 | 1174256.9464 | 0 | 0 | 0 | 1174256.9464 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ELEC TRANS LINE RELOCATION PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 5112.3412 | 0 | 0 | 0 | 5112.3412 | 0 | 0 | 0 | 0 | 0 | 5112.3412 | 0 | 0 | 0 | 5112.3412 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal ELEC TRANS LINE RELOCATION PROJECTS |  |  |  | Yes |  |  | 5112.3412 | 0 | 0 | 0 | 5112.3412 | 0 | 0 | 0 | 0 | 0 | 5112.3412 | 0 | 0 | 0 | 5112.3412 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ELECTRIFICATION SUBSTATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 1 | 8899.0974 | 0 | 0 | 0 | 8899.0974 | 0 | 0 | 0 | 0 | 0 | 8899.0974 | 0 | 0 | 0 | 8899.0974 | 100% | 0% | 0% | 0% | 100% | This is an emergent workpaper focused on addressing forecasted impacts of electrification at 8 load pockets identified by the Distribution Planning group within SDG&E's service territory on the 69kV system. The finalized scopes could include building out existing substations and/or constructing new substations. The work will also include upgrading, extending and/or building new transmission and distribution circuits. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. Work activities in 2024 includes only feasibility analysis and preliminary scoping. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal ELECTRIFICATION SUBSTATIONS |  |  |  | Yes |  |  | 8899.0974 | 0 | 0 | 0 | 8899.0974 | 0 | 0 | 0 | 0 | 0 | 8899.0974 | 0 | 0 | 0 | 8899.0974 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | ENCINA DECOMMISSION-REMOVAL 138KV SUBSTA | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Completed | 2371.9382 | 0 | 0 | 0 | 2371.9382 | 0 | 0 | 0 | 0 | 0 | 2371.9382 | 0 | 0 | 0 | 2371.9382 | 100% | 0% | 0% | 0% | 100% | This project was previously completed in 2022 with minor trailing charges in 2024. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal ENCINA DECOMMISSION-REMOVAL 138KV SUBSTA |  |  |  | Yes |  |  | 2371.9382 | 0 | 0 | 0 | 2371.9382 | 0 | 0 | 0 | 0 | 0 | 2371.9382 | 0 | 0 | 0 | 2371.9382 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | GENERATION INTERCONNECTION PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 471875.8859 | 0 | 0 | 0 | 471875.8859 | 0 | 0 | 0 | 0 | 0 | 471875.8859 | 0 | 0 | 0 | 471875.8859 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal GENERATION INTERCONNECTION PROJECTS |  |  |  | Yes |  |  | 471875.8859 | 0 | 0 | 0 | 471875.8859 | 0 | 0 | 0 | 0 | 0 | 471875.8859 | 0 | 0 | 0 | 471875.8859 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | GRANITE 12KV BREAKER AND SWITCHGEAR REPL | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 5 | 1102556.8906 | 0 | 0 | 0 | 1102556.8906 | 0 | 0 | 0 | 0 | 0 | 1102556.8906 | 0 | 0 | 0 | 1102556.8906 | 100% | 0% | 0% | 0% | 100% | This emergent project comprises activities that include replacing of 12kV circuit breakers, capacitor banks, 69kV bus work, 69kV SF6 replacements, and both above- and below-grade construction services. Activities completed in 2024 include 12 breakers and 4 capacitor banks as the major pieces of equipment. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal GRANITE 12KV BREAKER AND SWITCHGEAR REPL |  |  |  | Yes |  |  | 1102556.8906 | 0 | 0 | 0 | 1102556.8906 | 0 | 0 | 0 | 0 | 0 | 1102556.8906 | 0 | 0 | 0 | 1102556.8906 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | NORTH VALLEY 69/12KV SUBSTATION REBUILD | Electric Infrastructure Integrity | North Valley (Morro Hill) Substation Rebuild | Substation | No | Emergent | 1 | 244548.5979 | 0 | 0 | 0 | 244548.5979 | 0 | 0 | 0 | 0 | 0 | 244548.5979 | 0 | 0 | 0 | 244548.5979 | 100% | 0% | 0% | 0% | 100% | This is an emergent project that split off from the WMP balanced capital workpaper 152590. This scope of work includes a major substation rebuild encompassing construction of a new 69/12kV substation to be named “North Valley” on existing SDG&E property adjacent to the current Morro Hill substation, migration of all circuits, and Remove from Service of Morro Hills once completed. 2024 actuals represent only pre-construction for engineering and design. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal NORTH VALLEY 69/12KV SUBSTATION REBUILD |  |  |  | Yes |  |  | 244548.5979 | 0 | 0 | 0 | 244548.5979 | 0 | 0 | 0 | 0 | 0 | 244548.5979 | 0 | 0 | 0 | 244548.5979 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | WORKLOAD MANAGEMENT APPLICATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1217992.1897 | 0 | 0 | 0 | 1217992.1897 | 0 | 0 | 0 | 0 | 0 | 1217992.1897 | 0 | 0 | 0 | 1217992.1897 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal WORKLOAD MANAGEMENT APPLICATION |  |  |  | Yes |  |  | 1217992.1897 | 0 | 0 | 0 | 1217992.1897 | 0 | 0 | 0 | 0 | 0 | 1217992.1897 | 0 | 0 | 0 | 1217992.1897 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | KETTNER REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | No | 4 | 5 | 614435.2899 | 0 | 0 | 0 | 614435.2899 | 0 | 0 | 0 | 0 | 0 | 614435.2899 | 0 | 0 | 0 | 614435.2899 | 100% | 0% | 0% | 0% | 100% | The scope of this workpaper includes adding/replacing 69kV oil circuit breakers with vacuum circuit breakers, add 12kV Capacitor Bank with step-wise switching, and construct new control shelter. The project scope included a variety of different types of activities inside/outside the substation perimeter as noted above, which made it infeasible to identify and track a single unit of measure. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal KETTNER REBUILD |  |  |  | Yes |  |  | 614435.2899 | 0 | 0 | 0 | 614435.2899 | 0 | 0 | 0 | 0 | 0 | 614435.2899 | 0 | 0 | 0 | 614435.2899 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | INCIDENT RESPONSE- NON-INCREMENTAL | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 79773.8394 | 0 | 0 | 0 | 79773.8394 | 0 | 0 | 0 | 0 | 0 | 79773.8394 | 0 | 0 | 0 | 79773.8394 | 100% | 0% | 0% | 0% | 100% | The purpose of this workpaper is to capture non-incremental costs related to any and all activities necessary to restore service; repair, replace, or restore damaged facilities; and comply with governmental orders in connection with events declared disasters by competent state or federal authorities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal INCIDENT RESPONSE- NON-INCREMENTAL |  |  |  | Yes |  |  | 79773.8394 | 0 | 0 | 0 | 79773.8394 | 0 | 0 | 0 | 0 | 0 | 79773.8394 | 0 | 0 | 0 | 79773.8394 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | MID-COAST TROLLEY EXTENSION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1106.3117 | 0 | 0 | 0 | 1106.3117 | 0 | 0 | 0 | 0 | 0 | 1106.3117 | 0 | 0 | 0 | 1106.3117 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal MID-COAST TROLLEY EXTENSION |  |  |  | Yes |  |  | 1106.3117 | 0 | 0 | 0 | 1106.3117 | 0 | 0 | 0 | 0 | 0 | 1106.3117 | 0 | 0 | 0 | 1106.3117 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | MISSION 138KV & 69KV SUB REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 4 | 347546.8917 | 0 | 0 | 0 | 347546.8917 | 0 | 0 | 0 | 0 | 0 | 347546.8917 | 0 | 0 | 0 | 347546.8917 | 100% | 0% | 0% | 0% | 100% | This is an emergent substation rebuild project. The project scope included a variety of different types of activities on substation property, 2024 activities included purchasing of communication equipment. The variety of work activities makes it infeasible to identify and track a single unit of measure. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal MISSION 138KV & 69KV SUB REBUILD |  |  |  | Yes |  |  | 347546.8917 | 0 | 0 | 0 | 347546.8917 | 0 | 0 | 0 | 0 | 0 | 347546.8917 | 0 | 0 | 0 | 347546.8917 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | NARROWS REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 2 | 1807.6072 | 0 | 0 | 0 | 1807.6072 | 0 | 0 | 0 | 0 | 0 | 1807.6072 | 0 | 0 | 0 | 1807.6072 | 100% | 0% | 0% | 0% | 100% | This emergent project is the rebuild of Narrows substation which is a critical asset that supports the remote communities of Borrego and Warners in the northeastern part of SDG&E’s service territory. Narrows also provides an interconnection with Imperial Irrigation District (IID). 2024 activities include allocation of a split account due to the communications associated to the project. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal NARROWS REBUILD |  |  |  | Yes |  |  | 1807.6072 | 0 | 0 | 0 | 1807.6072 | 0 | 0 | 0 | 0 | 0 | 1807.6072 | 0 | 0 | 0 | 1807.6072 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | NEW DOWNTOWN 69/12KV SUBSTATION | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 1 | 26993.0993 | 0 | 0 | 0 | 26993.0993 | 0 | 0 | 0 | 0 | 0 | 26993.0993 | 0 | 0 | 0 | 26993.0993 | 100% | 0% | 0% | 0% | 100% | This is an emergent project for a new downtown San Diego 69/12kV substation. 2024 activities include preliminary feasibility studies. The variety of work activities in this category make it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal NEW DOWNTOWN 69/12KV SUBSTATION |  |  |  | Yes |  |  | 26993.0993 | 0 | 0 | 0 | 26993.0993 | 0 | 0 | 0 | 0 | 0 | 26993.0993 | 0 | 0 | 0 | 26993.0993 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | POLE LOADING REMEDIATION (NON-WMP) | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 384915.2603 | 0 | 0 | 0 | 384915.2603 | 0 | 0 | 0 | 0 | 0 | 384915.2603 | 0 | 0 | 0 | 384915.2603 | 100% | 0% | 0% | 0% | 100% | Poles replaced | 2 |  |  |  | 2 | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 | 2 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Emergent project created to address pole loading improvements. Pole loading documents, tracks, and timely closes non-compliant pole issues identified by the pole loading calculation program. If the pole loading calculation fails, it requires a pole replacement and therefore this project helps extend the lifespan of the overhead distribution system, minimizes customer safety risks and mitigates the need for extensive capital replacements. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | This program supports the performance of work for The Pole Loading Remediation Program (non-WMP). The PLR Program documents, tracks, and timely closes non-compliant pole issues identified by the pole loading calculation program. | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal POLE LOADING REMEDIATION (NON-WMP) |  |  |  | Yes |  |  | 384915.2603 | 0 | 0 | 0 | 384915.2603 | 0 | 0 | 0 | 0 | 0 | 384915.2603 | 0 | 0 | 0 | 384915.2603 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | PURE WATER ELECTRIC | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | -55764.5079 | 0 | 0 | 0 | -55764.5079 | 0 | 0 | 0 | 0 | 0 | -55764.5079 | 0 | 0 | 0 | -55764.5079 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal PURE WATER ELECTRIC |  |  |  | Yes |  |  | -55764.5079 | 0 | 0 | 0 | -55764.5079 | 0 | 0 | 0 | 0 | 0 | -55764.5079 | 0 | 0 | 0 | -55764.5079 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | REBUILDING OF SKILLS TRAINING YARD | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 4 | 1269688.7209 | 0 | 0 | 0 | 1269688.7209 | 0 | 0 | 0 | 0 | 0 | 1269688.7209 | 0 | 0 | 0 | 1269688.7209 | 100% | 0% | 0% | 0% | 100% | Activities in this workpaper represent equipment and labor related to expanding and rebuilding areas of overhead and underground training yards with equipment that is currently being used in the field and in line with current standards. This includes expanding the Fault Finding Specialist training yard to better support fault location, isolation and restoration for unplanned outages. 2024 activities included reroute the Fault Finding training circuit, and the feeder for the overhead training yards. In addition, the adding of OH SCADA switches and house meter simulator for the Electric Troubleshooter field practicum. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal REBUILDING OF SKILLS TRAINING YARD |  |  |  | Yes |  |  | 1269688.7209 | 0 | 0 | 0 | 1269688.7209 | 0 | 0 | 0 | 0 | 0 | 1269688.7209 | 0 | 0 | 0 | 1269688.7209 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | RFS JAPANESE MESA SUBSTATION | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 4 | 108089.0073 | 0 | 0 | 0 | 108089.0073 | 0 | 0 | 0 | 0 | 0 | 108089.0073 | 0 | 0 | 0 | 108089.0073 | 100% | 0% | 0% | 0% | 100% | This is an emergent project for a substation bypass. The project includes new conductors, new poles and new lines being in serviced, as well as the decommissioning and removal of Japanese Mesa Substation. 2024 activities included the construction of distribution poles and the decommisioning of the substation. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal RFS JAPANESE MESA SUBSTATION |  |  |  | Yes |  |  | 108089.0073 | 0 | 0 | 0 | 108089.0073 | 0 | 0 | 0 | 0 | 0 | 108089.0073 | 0 | 0 | 0 | 108089.0073 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SCADA EXPANSION-TRANSMISSION | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 5425.9915 | 0 | 0 | 0 | 5425.9915 | 0 | 0 | 0 | 0 | 0 | 5425.9915 | 0 | 0 | 0 | 5425.9915 | 100% | 0% | 0% | 0% | 100% | The variety of work activities in this category makes it infeasible to identify a single unit of measurement. 2024 activities included installation/upgrade of transmission relays and terminal units, engineering, consulting, project management, procurement and other capital expenditures in support thereof. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal SCADA EXPANSION-TRANSMISSION |  |  |  | Yes |  |  | 5425.9915 | 0 | 0 | 0 | 5425.9915 | 0 | 0 | 0 | 0 | 0 | 5425.9915 | 0 | 0 | 0 | 5425.9915 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SCADA HEAD-END REPLACEMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | 6 | 8 | 21995.217 | 0 | 0 | 0 | 21995.217 | 0 | 0 | 0 | 0 | 0 | 21995.217 | 0 | 0 | 0 | 21995.217 | 100% | 0% | 0% | 0% | 100% | The purpose of the SCADA Head-End Replacement project was to fix issues with the old system and improved reliability and security. The project included duplicating the system at the backup control center, adding simulation for testing and training, preparing for system growth, upgrading communication protocols, and supporting grid modernization efforts. The project was completed in 2023 and 2024 spend was related to close-out costs. The variety of work activities in this category makes it infeasible to identify a single unit of measurement | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | On Target (T) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal SCADA HEAD-END REPLACEMENT |  |  |  | Yes |  |  | 21995.217 | 0 | 0 | 0 | 21995.217 | 0 | 0 | 0 | 0 | 0 | 21995.217 | 0 | 0 | 0 | 21995.217 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SUB EXTERNALLY ROUTABLE CONNECTIV (SERC) | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 52651.8246 | 0 | 0 | 0 | 52651.8246 | 0 | 0 | 0 | 0 | 0 | 52651.8246 | 0 | 0 | 0 | 52651.8246 | 100% | 0% | 0% | 0% | 100% | The variety of work activities in this category makes it infeasible to identify a single unit of measurement. 2024 work activities for this emergent project include installation of devices such as real time automation controllers (RTACs), Secure Access Management Solutions (SAMS), and engineering, consulting, project management, procurement and other capital expenditures in support thereof. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal SUB EXTERNALLY ROUTABLE CONNECTIV (SERC) |  |  |  | Yes |  |  | 52651.8246 | 0 | 0 | 0 | 52651.8246 | 0 | 0 | 0 | 0 | 0 | 52651.8246 | 0 | 0 | 0 | 52651.8246 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SUBSTATION DC RELIABILITY UPGRADE PROJ | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 4981.3512 | 0 | 0 | 0 | 4981.3512 | 0 | 0 | 0 | 0 | 0 | 4981.3512 | 0 | 0 | 0 | 4981.3512 | 100% | 0% | 0% | 0% | 100% | The variety of work activities in this category makes it infeasible to identify a single unit of measurement. 2024 activities include installation/upgrade of dedicated inverters, AC breaker panels, HVAC equipment, station batteries, DC-DC converters, DC breaker panels, DC fuse panels, and fuse/terminal plates, engineering, consulting, project management, procurement and other capital expenditures in support thereof. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal SUBSTATION DC RELIABILITY UPGRADE PROJ |  |  |  | Yes |  |  | 4981.3512 | 0 | 0 | 0 | 4981.3512 | 0 | 0 | 0 | 0 | 0 | 4981.3512 | 0 | 0 | 0 | 4981.3512 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SUBSTATION SECURITY PROJ UNDER $500K | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 327895.7277 | 0 | 0 | 0 | 327895.7277 | 0 | 0 | 0 | 0 | 0 | 327895.7277 | 0 | 0 | 0 | 327895.7277 | 100% | 0% | 0% | 0% | 100% | This program is focused on upgrading physical and electronic security systems within and around SDG&E’s substation assets. 2024 activities included the physical security hardening of the Adams substation through the installation of a new SDGE substation standard perimeter fence. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal SUBSTATION SECURITY PROJ UNDER $500K |  |  |  | Yes |  |  | 327895.7277 | 0 | 0 | 0 | 327895.7277 | 0 | 0 | 0 | 0 | 0 | 327895.7277 | 0 | 0 | 0 | 327895.7277 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SYNCHRONIZED PHASOR MEASUREMENT SYSTEM | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | -360730.8052 | 0 | 0 | 0 | -360730.8052 | 0 | 0 | 0 | 0 | 0 | -360730.8052 | 0 | 0 | 0 | -360730.8052 | 100% | 0% | 0% | 0% | 100% | The variety of work activities in this category makes it infeasible to identify a single unit of measurement. 2024 work activities include installation of devices such as Phasor Measurement Units (PMU), real time automation controllers (RTACs), internal software development of deployment of the Wide Area Situational Awareness (WASA) system, engineering, consulting, project management, procurement and other capital expenditures in support thereof. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal SYNCHRONIZED PHASOR MEASUREMENT SYSTEM |  |  |  | Yes |  |  | -360730.8052 | 0 | 0 | 0 | -360730.8052 | 0 | 0 | 0 | 0 | 0 | -360730.8052 | 0 | 0 | 0 | -360730.8052 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL23001 TL23004 INSULATOR AND HARDWARE R | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Completed | 5681.95 | 0 | 0 | 0 | 5681.95 | 0 | 0 | 0 | 0 | 0 | 5681.95 | 0 | 0 | 0 | 5681.95 | 100% | 0% | 0% | 0% | 100% | This emergent project was previously completed in 2022 which included the replacement of ceramic insulators and all associated insulator assembly hardware. Costs shown in 2024 include minor closeout trailing costs. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal TL23001 TL23004 INSULATOR AND HARDWARE R |  |  |  | Yes |  |  | 5681.95 | 0 | 0 | 0 | 5681.95 | 0 | 0 | 0 | 0 | 0 | 5681.95 | 0 | 0 | 0 | 5681.95 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL600 - RELIABILITY POLE REPLACEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | 6 | Completed | 93182.1803 | 0 | 0 | 0 | 93182.1803 | 0 | 0 | 0 | 0 | 0 | 93182.1803 | 0 | 0 | 0 | 93182.1803 | 100% | 0% | 0% | 0% | 100% | This project was previously completed in 2022 which included distribution pole replacements and restringing over highway. Costs shown in 2024 include minor closeout trailing costs. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal TL600 - RELIABILITY POLE REPLACEMENTS |  |  |  | Yes |  |  | 93182.1803 | 0 | 0 | 0 | 93182.1803 | 0 | 0 | 0 | 0 | 0 | 93182.1803 | 0 | 0 | 0 | 93182.1803 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL603B SWEETWATER TAP REMOVAL | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 8 | 1492.151 | 0 | 0 | 0 | 1492.151 | 0 | 0 | 0 | 0 | 0 | 1492.151 | 0 | 0 | 0 | 1492.151 | 100% | 0% | 0% | 0% | 100% | This is an emergent project. This is primarily a transmission driven project with a small portion for distribution. The minor scope of distribution work consisted of ancillary information technology and communications upgrades inside the substation with minimal trailing costs in 2024. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal TL603B SWEETWATER TAP REMOVAL |  |  |  | Yes |  |  | 1492.151 | 0 | 0 | 0 | 1492.151 | 0 | 0 | 0 | 0 | 0 | 1492.151 | 0 | 0 | 0 | 1492.151 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL605 RECONDUCTOR: SILVERGATE - URBAN | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | 9 | 211078.2505 | 0 | 0 | 0 | 211078.2505 | 0 | 0 | 0 | 0 | 0 | 211078.2505 | 0 | 0 | 0 | 211078.2505 | 100% | 0% | 0% | 0% | 100% | This emergent project will involve the rebuild of an approximately 2-mile line between Silvergate Substation and Urban Substation. This new fully underground alignment from Silvergate Substation to Urban Substation concrete-encased duct package will then be utilized to install new 3000kCMIL copper cables to achieve the ampacity rating to mitigate potential overload approved by the California Independent System Operator (CAISO). The scope of this transmission driven project includes underground trench and conduit civil work, cable installation, and related communications equipment as well as the removal of overhead transmission line that will then be de-energized upon completion of the underground cable system. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal TL605 RECONDUCTOR: SILVERGATE - URBAN |  |  |  | Yes |  |  | 211078.2505 | 0 | 0 | 0 | 211078.2505 | 0 | 0 | 0 | 0 | 0 | 211078.2505 | 0 | 0 | 0 | 211078.2505 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL634 JUNIPER STREET CUSTOMER RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 157856.5227 | 0 | 0 | 0 | 157856.5227 | 0 | 0 | 0 | 0 | 0 | 157856.5227 | 0 | 0 | 0 | 157856.5227 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal TL634 JUNIPER STREET CUSTOMER RELOCATION |  |  |  | Yes |  |  | 157856.5227 | 0 | 0 | 0 | 157856.5227 | 0 | 0 | 0 | 0 | 0 | 157856.5227 | 0 | 0 | 0 | 157856.5227 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TRANSMISSION EMS/SCADA RELIANCE UPGRADE | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Completed | 373883.8247 | 0 | 0 | 0 | 373883.8247 | 0 | 0 | 0 | 0 | 0 | 373883.8247 | 0 | 0 | 0 | 373883.8247 | 100% | 0% | 0% | 0% | 100% | This is an emergent project and includes new hardware, software, network device, as well as a disaster recovery system. The variety of work activities in this program makes it infeasible to identify a single unit of measurement. 2024 activities include testing, parallel operations, and system commissioning. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal TRANSMISSION EMS/SCADA RELIANCE UPGRADE |  |  |  | Yes |  |  | 373883.8247 | 0 | 0 | 0 | 373883.8247 | 0 | 0 | 0 | 0 | 0 | 373883.8247 | 0 | 0 | 0 | 373883.8247 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL667 SAN DIEGUITO RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 9537.6326 | 0 | 0 | 0 | 9537.6326 | 0 | 0 | 0 | 0 | 0 | 9537.6326 | 0 | 0 | 0 | 9537.6326 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal TL667 SAN DIEGUITO RELOCATION |  |  |  | Yes |  |  | 9537.6326 | 0 | 0 | 0 | 9537.6326 | 0 | 0 | 0 | 0 | 0 | 9537.6326 | 0 | 0 | 0 | 9537.6326 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL673 RN-LJ DB CABLE REPLACE | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Completed | 953.153 | 0 | 0 | 0 | 953.153 | 0 | 0 | 0 | 0 | 0 | 953.153 | 0 | 0 | 0 | 953.153 | 100% | 0% | 0% | 0% | 100% | This is an emergent project that was completed in 2023. This is primarily a transmission driven project with a small portion for distribution. The minor scope of distribution work consisted of ancillary information technology and communications upgrades inside the substation. Minimal costs in 2024 for trailing charges. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal TL673 RN-LJ DB CABLE REPLACE |  |  |  | Yes |  |  | 953.153 | 0 | 0 | 0 | 953.153 | 0 | 0 | 0 | 0 | 0 | 953.153 | 0 | 0 | 0 | 953.153 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL674A DEL MAR RECONFIGURE/TL666D RFS | Non-RAMP | Non-RAMP | Non-RAMP | No | 7 | Completed | 158885.4882 | 0 | 0 | 0 | 158885.4882 | 0 | 0 | 0 | 0 | 0 | 158885.4882 | 0 | 0 | 0 | 158885.4882 | 100% | 0% | 0% | 0% | 100% | The purpose of this project was to remove TL666D from service at the Del Mar sub, remove the tap on TL674 from service at Via De La Valle, build two circuits: Del Mar - North City West and Encinitas - Rancho Santa Fe, and terminate the new Del Mar - North City West circuit and the old TL666D. The cost incurred in 2024 were related to closeout activities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal TL674A DEL MAR RECONFIGURE/TL666D RFS |  |  |  | Yes |  |  | 158885.4882 | 0 | 0 | 0 | 158885.4882 | 0 | 0 | 0 | 0 | 0 | 158885.4882 | 0 | 0 | 0 | 158885.4882 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TRANSMISSION INFRASTRUCTURE IMPROVEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Annual | 28032.7485 | 0 | 0 | 0 | 28032.7485 | 0 | 0 | 0 | 0 | 0 | 28032.7485 | 0 | 0 | 0 | 28032.7485 | 100% | 0% | 0% | 0% | 100% | This is an emergent project. The activities under this blanket workpaper involves the replacement of obsolete substation equipment including transformers, circuit breakers, disconnects, transmission line relaying and site improvements. 2024 activities includes minimal costs for distribution and communication component of the replacement of obsolete substation equipment. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal TRANSMISSION INFRASTRUCTURE IMPROVEMENTS |  |  |  | Yes |  |  | 28032.7485 | 0 | 0 | 0 | 28032.7485 | 0 | 0 | 0 | 0 | 0 | 28032.7485 | 0 | 0 | 0 | 28032.7485 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL6975 ESCONDIDO - SAN MARCOS | Non-RAMP | Non-RAMP | Non-RAMP | No | Emergent | Completed | 26484.8934 | 0 | 0 | 0 | 26484.8934 | 0 | 0 | 0 | 0 | 0 | 26484.8934 | 0 | 0 | 0 | 26484.8934 | 100% | 0% | 0% | 0% | 100% | This is an emergent project that was completed in 2023. The project scope included a variety of different types of activities which make it infeasible to identify and track a single unit of measure. 2024 activities were related to repatriation and closeout punch list items for San Marcos to include wood pole removals after communications attachments were transferred. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | This project was forecasted to be completed prior to 2024 and was delayed. Project will now be completed during the 2024 GRC cycle.
Capital | ELECTRIC DISTRIBUTION | SubTotal TL6975 ESCONDIDO - SAN MARCOS |  |  |  | Yes |  |  | 26484.8934 | 0 | 0 | 0 | 26484.8934 | 0 | 0 | 0 | 0 | 0 | 26484.8934 | 0 | 0 | 0 | 26484.8934 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | TL698 MEADOWOOD RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | -23099.1551 | 0 | 0 | 0 | -23099.1551 | 0 | 0 | 0 | 0 | 0 | -23099.1551 | 0 | 0 | 0 | -23099.1551 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | ELECTRIC DISTRIBUTION | SubTotal TL698 MEADOWOOD RELOCATION |  |  |  | Yes |  |  | -23099.1551 | 0 | 0 | 0 | -23099.1551 | 0 | 0 | 0 | 0 | 0 | -23099.1551 | 0 | 0 | 0 | -23099.1551 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO

## EOEG-C
SDG&E ELECTRIC GENERATION Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | ELECTRIC GENERATION | ELECTRIC GENERATION |  |  |  | Yes |  |  | 10544131.5693 | 0 | 0 | 0 | 10544131.5693 | 13374999.72 | 13776999.72 | 14189999.76 | 14615999.64 | 13374999.72 | -2830868.1507 | -13776999.72 | -14189999.76 | -14615999.64 | -2830868.1507 | -21.17% | -100% | -100% | -100% | -21.17%
Capital | ELECTRIC GENERATION | CUYAMACA PEAK ENERGY PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 218157.42 | 0 | 0 | 0 | 218157.42 | 651000 | 670999.92 | 690999.96 | 711999.96 | 651000 | -432842.58 | -670999.92 | -690999.96 | -711999.96 | -432842.58 | -66.49% | -100% | -100% | -100% | -66.49% | 2024 Actual project spend that increased the overall reliability, operability and safety of the Cuyamaca Plant include inlet filter replacement, and various electrical, mechanical and instrumentation improvement projects. The projects completed in 2024 are comparable to the type of projects reflected in the imputed authorized amounts. Due to the variety of work activities in this category, it is infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal CUYAMACA PEAK ENERGY PLANT OPER ENHANCE |  |  |  | Yes |  |  | 218157.42 | 0 | 0 | 0 | 218157.42 | 651000 | 670999.92 | 690999.96 | 711999.96 | 651000 | -432842.58 | -670999.92 | -690999.96 | -711999.96 | -432842.58 | -66.49% | -100% | -100% | -100% | -66.49% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | DESERT STAR ENERGY CTR OPER. ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 4350452.2325 | 0 | 0 | 0 | 4350452.2325 | 5509999.92 | 5674999.92 | 5844999.96 | 6019999.92 | 5509999.92 | -1159547.6875 | -5674999.92 | -5844999.96 | -6019999.92 | -1159547.6875 | -21.04% | -100% | -100% | -100% | -21.04% | 2024 Actual project spend that increased the overall reliability, operability and safety of the Desert Star Plant include physical security improvements, valve replacement, platform installation, Auxiliary Transformer upgrade, station battery replacment, control system upgrade, blade replacment, and various mechanical improvement projects. The projects completed in 2024 are comparable to the type of projects reflected in the imputed authorized amounts. Due to the variety of work activities in this category, it is infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal DESERT STAR ENERGY CTR OPER. ENHANCE |  |  |  | Yes |  |  | 4350452.2325 | 0 | 0 | 0 | 4350452.2325 | 5509999.92 | 5674999.92 | 5844999.96 | 6019999.92 | 5509999.92 | -1159547.6875 | -5674999.92 | -5844999.96 | -6019999.92 | -1159547.6875 | -21.04% | -100% | -100% | -100% | -21.04% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | GENERATION CAPITAL TOOLS & TEST EQPT. | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 76764.01 | 0 | 0 | 0 | 76764.01 | 91999.92 | 94999.92 | 97999.92 | 100999.92 | 91999.92 | -15235.91 | -94999.92 | -97999.92 | -100999.92 | -15235.91 | -16.56% | -100% | -100% | -100% | -16.56% | This workpaper consists of a variety of activities, including acquisition of mechanical tools, plant test and analysis equipment (such as meters, cameras, volt detectors, videoscopes, other equipment). The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal GENERATION CAPITAL TOOLS & TEST EQPT. |  |  |  | Yes |  |  | 76764.01 | 0 | 0 | 0 | 76764.01 | 91999.92 | 94999.92 | 97999.92 | 100999.92 | 91999.92 | -15235.91 | -94999.92 | -97999.92 | -100999.92 | -15235.91 | -16.56% | -100% | -100% | -100% | -16.56% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | MIRAMAR PLANT OPERATIONAL ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 143704.097 | 0 | 0 | 0 | 143704.097 | 975999.96 | 1005000 | 1035000 | 1065999.96 | 975999.96 | -832295.863 | -1005000 | -1035000 | -1065999.96 | -832295.863 | -85.28% | -100% | -100% | -100% | -85.28% | 2024 Actual project spend that increased the overall reliability, operability and safety of the Miramar Plant include waste heat recovery upgrade, and various mechanical and instrumentation improvement projects. The projects completed in 2024 are comparable to the type of projects reflected in the imputed authorized amounts. Due to the variety of work activities in this category, it is infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal MIRAMAR PLANT OPERATIONAL ENHANCEMENTS |  |  |  | Yes |  |  | 143704.097 | 0 | 0 | 0 | 143704.097 | 975999.96 | 1005000 | 1035000 | 1065999.96 | 975999.96 | -832295.863 | -1005000 | -1035000 | -1065999.96 | -832295.863 | -85.28% | -100% | -100% | -100% | -85.28% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | PALOMAR PLANT OPERATIONAL ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 4815094.0436 | 0 | 0 | 0 | 4815094.0436 | 6093000 | 6276000 | 6463999.92 | 6657999.96 | 6093000 | -1277905.9564 | -6276000 | -6463999.92 | -6657999.96 | -1277905.9564 | -20.97% | -100% | -100% | -100% | -20.97% | 2024 Actual project spend that increased the overall reliability, operability and safety of the Palomar Plant include upgrades to HVAC system, valve replacements, piping and insulation upgrades, relay upgrades, and various safety, electrical, mechanical and instrument improvement projects. The projects completed in 2024 are comparable to the type of projects reflected in the imputed authorized amounts. Due to the variety of work activities in this category, it is infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal PALOMAR PLANT OPERATIONAL ENHANCEMENTS |  |  |  | Yes |  |  | 4815094.0436 | 0 | 0 | 0 | 4815094.0436 | 6093000 | 6276000 | 6463999.92 | 6657999.96 | 6093000 | -1277905.9564 | -6276000 | -6463999.92 | -6657999.96 | -1277905.9564 | -20.97% | -100% | -100% | -100% | -20.97% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | RAMONA SOLAR PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 5031.73 | 0 | 0 | 0 | 5031.73 | 52999.92 | 54999.96 | 57000 | 58999.92 | 52999.92 | -47968.19 | -54999.96 | -57000 | -58999.92 | -47968.19 | -90.51% | -100% | -100% | -100% | -90.51% | 2024 Actual project spend that increased the overall reliability, operability and safety of the Ramona Solar Plant include mechanical improvement projects. The projects completed in 2024 are comparable to the type of projects reflected in the imputed authorized amounts. Due to the variety of work activities in this category, it is infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal RAMONA SOLAR PLANT OPER ENHANCE |  |  |  | Yes |  |  | 5031.73 | 0 | 0 | 0 | 5031.73 | 52999.92 | 54999.96 | 57000 | 58999.92 | 52999.92 | -47968.19 | -54999.96 | -57000 | -58999.92 | -47968.19 | -90.51% | -100% | -100% | -100% | -90.51% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | ESCONDIDO BESS PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 660 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 660 | 100% | 0% | 0% | 0% | 100% | Project was completed over the 2019 GRC cycle. 2024 activity is related to project close-out costs. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Other | NO | Project was anticipated to be completed prior to the TY 2024 GRC cycle.
Capital | ELECTRIC GENERATION | SubTotal ESCONDIDO BESS PLANT OPER ENHANCE |  |  |  | Yes |  |  | 660 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 660 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | MIGUEL VRF- BATTERY FACILITIES ENHANCEME | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 219562.5521 | 0 | 0 | 0 | 219562.5521 | 0 | 0 | 0 | 0 | 0 | 219562.5521 | 0 | 0 | 0 | 219562.5521 | 100% | 0% | 0% | 0% | 100% | 2024 actual project spend that increased the overall reliability, operability and safety of the Miguel VRF-Battery site include a network upgrade project. The project completed in 2024 is comparable to the type of projects reflected in the imputed authorized amounts. Due to the variety of work activities in this category, it is infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal MIGUEL VRF- BATTERY FACILITIES ENHANCEME |  |  |  | Yes |  |  | 219562.5521 | 0 | 0 | 0 | 219562.5521 | 0 | 0 | 0 | 0 | 0 | 219562.5521 | 0 | 0 | 0 | 219562.5521 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | PALOMAR HYDROGEN SYSTEMS | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 4 | 715283.4042 | 0 | 0 | 0 | 715283.4042 | 0 | 0 | 0 | 0 | 0 | 715283.4042 | 0 | 0 | 0 | 715283.4042 | 100% | 0% | 0% | 0% | 100% | Capital project focused on demonstrating multiple use cases of electrolytically produced hydrogen to support decarbonizing natural gas-powered plant operations. This pilot project focuses on increased understanding of hydrogen’s behavior and impact on SDG&E’s turbines; the impact on various emissions; how to design, operate, and maintain hydrogen equipment; and how to reduce the unit cost of hydrogen. The variety of work activities associated with this project makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal PALOMAR HYDROGEN SYSTEMS |  |  |  | Yes |  |  | 715283.4042 | 0 | 0 | 0 | 715283.4042 | 0 | 0 | 0 | 0 | 0 | 715283.4042 | 0 | 0 | 0 | 715283.4042 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | ELECTRIC GENERATION | EL CAJON BESS PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | -577.92 | 0 | 0 | 0 | -577.92 | 0 | 0 | 0 | 0 | 0 | -577.92 | 0 | 0 | 0 | -577.92 | 100% | 0% | 0% | 0% | 100% | Project was canceled. 2024 activity is related to an accounting adjustment. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Canceled | NO | N/A
Capital | ELECTRIC GENERATION | SubTotal EL CAJON BESS PLANT OPER ENHANCE |  |  |  | Yes |  |  | -577.92 | 0 | 0 | 0 | -577.92 | 0 | 0 | 0 | 0 | 0 | -577.92 | 0 | 0 | 0 | -577.92 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO

## EODD-C
SDG&E CLEAN ENERGY INNOVATIONS Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | CLEAN ENERGY INNOVATIONS | CLEAN ENERGY INNOVATIONS |  |  |  | Yes |  |  | 1932643.798 | 0 | 0 | 0 | 1932643.798 | 2769999.84 | 2852999.88 | 2937999.96 | 3025999.92 | 2769999.84 | -837356.042 | -2852999.88 | -2937999.96 | -3025999.92 | -837356.042 | -30.23% | -100% | -100% | -100% | -30.23%
Capital | CLEAN ENERGY INNOVATIONS | ADVANCED ENERGY STORAGE | Non-RAMP | Non-RAMP | Non-RAMP | No | 6 | 6 | 3716228.3809 | 0 | 0 | 0 | 3716228.3809 | 0 | 0 | 0 | 0 | 0 | 3716228.3809 | 0 | 0 | 0 | 3716228.3809 | 100% | 0% | 0% | 0% | 100% | This project installs a new 7.3MW/14.6MWh energy storage system at the Borrego Microgrid, to support grid reliability and resiliency for the Borrego Springs community. This includes installing new foundations, switchgear, control shelter, step-up transformers, a grounding transformer, a new energy storage system and implementation of the Local Area Distribution Controller (LADC) for microgrid operations. This new battery will participate in the CAISO marketplace during normal, non-emergency conditions, and it will have the capability to act as the new island master during microgrid operations. The variety of work activities in the category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Completed | NO | N/A
Capital | CLEAN ENERGY INNOVATIONS | SubTotal ADVANCED ENERGY STORAGE |  |  |  | Yes |  |  | 3716228.3809 | 0 | 0 | 0 | 3716228.3809 | 0 | 0 | 0 | 0 | 0 | 3716228.3809 | 0 | 0 | 0 | 3716228.3809 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | CLEAN ENERGY INNOVATIONS | BORREGO MICROGRID 3.0 | Non-RAMP | Non-RAMP | Non-RAMP | No | 6 | 6 | -2008434.0928 | 0 | 0 | 0 | -2008434.0928 | 0 | 0 | 0 | 0 | 0 | -2008434.0928 | 0 | 0 | 0 | -2008434.0928 | 100% | 0% | 0% | 0% | 100% | This project modifies the existing Borrego Springs Microgrid to enable increased load capacity and fully renewable energy operation, reducing the reliance on diesel generators.This includes building a new circuit, new bay position, and developing the land adjacent to the microgrid to accommodate additional distributed energy resources.The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Under (U) | Expanded | NO | N/A
Capital | CLEAN ENERGY INNOVATIONS | SubTotal BORREGO MICROGRID 3.0 |  |  |  | Yes |  |  | -2008434.0928 | 0 | 0 | 0 | -2008434.0928 | 0 | 0 | 0 | 0 | 0 | -2008434.0928 | 0 | 0 | 0 | -2008434.0928 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | CLEAN ENERGY INNOVATIONS | SUSTAINABLE COMMUNITIES REMOVAL | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 224849.51 | 0 | 0 | 0 | 224849.51 | 166999.92 | 171999.96 | 177000 | 181999.92 | 166999.92 | 57849.59 | -171999.96 | -177000 | -181999.92 | 57849.59 | 34.64% | -100% | -100% | -100% | 34.64% | Customer Sites Decommissioned | 3 |  |  |  | 3 | 1 |  |  |  | 1 | 2 | 0 | 0 | 0 | 2 | 200% | 0% | 0% | 0% | 200% | YES | NO | YES | N/A | Del Lago Academy was forecasted to decommission in 2024 at the time of the GRC filing, but ended up renewing their lease. 3 other sites were decommissioned instead in 2024, including High Tech High, Ladera Ranch and Agua Hedionda. The selection for which sites to decommission is generally driven by risk assessment and customer requirements. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Pursuant to D.04-12-015, SDG&E opened the Sustainable Community Program to engineer, design, procure, install and maintain community-based energy strategies, state-of-the-art generation and storage technologies, and advanced control devices. As part of the program, SDG&E owns the assets and leases the land from the community. Upon the expiration of a land lease, community members have the option to either extend the lease with SDG&E or choose to have SDG&E remove the asset. | SDG&E-15-R-E FV-25 to FV-26 CWP 20281A
Capital | CLEAN ENERGY INNOVATIONS | SubTotal SUSTAINABLE COMMUNITIES REMOVAL |  |  |  | Yes |  |  | 224849.51 | 0 | 0 | 0 | 224849.51 | 166999.92 | 171999.96 | 177000 | 181999.92 | 166999.92 | 57849.59 | -171999.96 | -177000 | -181999.92 | 57849.59 | 34.64% | -100% | -100% | -100% | 34.64% | [21 empty] | YES | NO | [7 empty] | NO
Capital | CLEAN ENERGY INNOVATIONS | MOBILE BATTERY ENERGY STORAGE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 2602999.92 | 2680999.92 | 2760999.96 | 2844000 | 2602999.92 | -2602999.92 | -2680999.92 | -2760999.96 | -2844000 | -2602999.92 | -100% | -100% | -100% | -100% | -100% | Mobile Battery Storage Units | 0 |  |  |  | 0 | 3 |  |  |  | 3 | -3 | 0 | 0 | 0 | -3 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | This program was on hold in 2024 pending GRC funding decision. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | Strategic deployment of mobile energy storage systems to support the Company's goal of increasing resiliency and operational flexibility. These mobile energy storage systems will be designed, built and deployed to provide back-up and microgriding capabilities without being limited by its physical location. The technology, along with its use case and benefits, were demonstrated in EPIC 3, Project 7. | SDG&E-15-R-E FV-26 to FV-27 CWP 212610
Capital | CLEAN ENERGY INNOVATIONS | SubTotal MOBILE BATTERY ENERGY STORAGE PROGRAM |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 2602999.92 | 2680999.92 | 2760999.96 | 2844000 | 2602999.92 | -2602999.92 | -2680999.92 | -2760999.96 | -2844000 | -2602999.92 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES

## GOGD-C
SDG&E GAS DISTRIBUTION Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | GAS DISTRIBUTION | GAS DISTRIBUTION |  |  |  | Yes |  |  | 135562979.4126 | 0 | 0 | 0 | 135562979.4126 | 104073998.88 | 107195998.8 | 110412998.76 | 113722998.72 | 104073998.88 | 31488980.5326 | -107195998.8 | -110412998.76 | -113722998.72 | 31488980.5326 | 30.26% | -100% | -100% | -100% | 30.26%
Capital | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection Program - Capital | HP Supply Line | No | On-going | Annual | 274004.1641 | 0 | 0 | 0 | 274004.1641 | 237000 | 243999.96 | 250999.92 | 258999.96 | 237000 | 37004.1641 | -243999.96 | -250999.92 | -258999.96 | 37004.1641 | 15.61% | -100% | -100% | -100% | 15.61% | Deep well anode beds | 3 |  |  |  | 3 | 3 |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection Program - Capital | MP Main Steel | No | On-going | Annual | 5206079.1177 | 0 | 0 | 0 | 5206079.1177 | 4156999.92 | 4281999.96 | 4410999.96 | 4542999.96 | 4156999.92 | 1049079.1977 | -4281999.96 | -4410999.96 | -4542999.96 | 1049079.1977 | 25.24% | -100% | -100% | -100% | 25.24% | Deep well anode beds | 20 |  |  |  | 20 | 42 |  |  |  | 42 | -22 | 0 | 0 | 0 | -22 | -52.38% | 0% | 0% | 0% | -52.38% | YES | YES | YES | The cost and unit variance associated with this workpaper were attributed to several key factors. The vendor performing this activity ceased to operate in the beginning of 2024. New vendor options were extremely limited and significantly more expensive than what was forecasted in 2022 for the 2024 GRC. Several deep well anode jobs had increased costs due to hard soil, which added additional days to the drilling operation. | The cost and unit variance associated with this workpaper were attributed to several key factors. The vendor performing this activity ceased to operate in the beginning of 2024. New vendor options were extremely limited and significantly more expensive than what was forecasted in 2022 for the 2024 GRC. Several deep well anode jobs had increased costs due to hard soil, which added additional days to the drilling operation. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | CP equipment additions are required so that SDG&E meets code mandated corrosion control requirements for the steel portion of the gas distribution system. By placing steel pipelines under cathodic protection, corrosion is minimized, resulting in a safer and more reliable gas system as well as extending the life of the steel pipeline system. | SDG&E-04-R-E LPK-94 to LPK-97 CWP 00509
Capital | GAS DISTRIBUTION | SubTotal CATHODIC PROTECTION |  |  |  | Yes |  |  | 5480083.2818 | 0 | 0 | 0 | 5480083.2818 | 4393999.92 | 4525999.92 | 4661999.88 | 4801999.92 | 4393999.92 | 1086083.3618 | -4525999.92 | -4661999.88 | -4801999.92 | 1086083.3618 | 24.72% | -100% | -100% | -100% | 24.72% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | CATHODIC PROTECTION SYSTEM ENHANCEMENT | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection System Enhancements | HP Supply Line | No | On-going | Annual | 90630.9776 | 0 | 0 | 0 | 90630.9776 | 0 | 0 | 0 | 0 | 0 | 90630.9776 | 0 | 0 | 0 | 90630.9776 | 100% | 0% | 0% | 0% | 100% | Projects | 1 |  |  |  | 1 | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | The variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A | The Cathodic Protection System Enhancement budget code tracks projects specifically associated with creating dedicated high pressure and medium distribution pressure pipeline CP systems and remediating non-state-of-the-art cathodic protection on steel pipe segments, risers and valves as determined through advances in GIS mapping capabilities. | SDG&E-04-R-E LPK-97 to LPK-100 CWP 12551
Capital | GAS DISTRIBUTION | CATHODIC PROTECTION SYSTEM ENHANCEMENT | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection System Enhancements | MP Main Steel | No | On-going | Annual | 1721988.5745 | 0 | 0 | 0 | 1721988.5745 | 0 | 0 | 0 | 0 | 0 | 1721988.5745 | 0 | 0 | 0 | 1721988.5745 | 100% | 0% | 0% | 0% | 100% | Projects | 49 |  |  |  | 49 | 0 |  |  |  | 0 | 49 | 0 | 0 | 0 | 49 | 100% | 0% | 0% | 0% | 100% | YES | YES | YES | The variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | The variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A | The Cathodic Protection System Enhancement budget code tracks projects specifically associated with creating dedicated high pressure and medium distribution pressure pipeline CP systems and remediating non-state-of-the-art cathodic protection on steel pipe segments, risers and valves as determined through advances in GIS mapping capabilities. | SDG&E-04-R-E LPK-97 to LPK-100 CWP 12551
Capital | GAS DISTRIBUTION | SubTotal CATHODIC PROTECTION SYSTEM ENHANCEMENT |  |  |  | Yes |  |  | 1812619.5521 | 0 | 0 | 0 | 1812619.5521 | 0 | 0 | 0 | 0 | 0 | 1812619.5521 | 0 | 0 | 0 | 1812619.5521 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | CNG STATION UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 453688.6359 | 0 | 0 | 0 | 453688.6359 | 0 | 0 | 0 | 0 | 0 | 453688.6359 | 0 | 0 | 0 | 453688.6359 | 100% | 0% | 0% | 0% | 100% | Compressed Natural Gas Stations | 2 |  |  |  | 2 | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 | 2 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | The variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A | Provides for labor, services and materials to upgrades needed to maintain a compressed natural gas (CNG) alternative fueling station infrastructure for use by company fleet vehicles and the public. | SDG&E-04-R-E LPK-121 to LPK-122 CWP 145530
Capital | GAS DISTRIBUTION | SubTotal CNG STATION UPGRADES |  |  |  | Yes |  |  | 453688.6359 | 0 | 0 | 0 | 453688.6359 | 0 | 0 | 0 | 0 | 0 | 453688.6359 | 0 | 0 | 0 | 453688.6359 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | CODE COMPLIANCE | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 423999.96 | 436999.92 | 450000 | 463999.92 | 423999.96 | -423999.96 | -436999.92 | -450000 | -463999.92 | -423999.96 | -100% | -100% | -100% | -100% | -100% | Projects | 0 |  |  |  | 0 | 100 |  |  |  | 100 | -100 | 0 | 0 | 0 | -100 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The variance is due to this non-RAMP activity being completed in 2023. | On Target (T) | On Target (T) | On Target (T) | Completed | YES | N/A | Capital expenditures in budget code 507 are used to keep SDG&E's gas distribution system in compliance with State and Federal regulations for natural gas pipelines. | SDG&E-04-R-E LPK-88 to LPK-92 CWP 005070
Capital | GAS DISTRIBUTION | CODE COMPLIANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Code Compliance Mitigation | Meter & Beyond the Meter | No | On-going | Annual | 5466727.7013 | 0 | 0 | 0 | 5466727.7013 | 2652999.96 | 2733000 | 2814999.96 | 2898999.96 | 2652999.96 | 2813727.7413 | -2733000 | -2814999.96 | -2898999.96 | 2813727.7413 | 106.1% | -100% | -100% | -100% | 106.1% | Projects | 4530 |  |  |  | 4530 | 1481 |  |  |  | 1481 | 3049 | 0 | 0 | 0 | 3049 | 205.9% | 0% | 0% | 0% | 205.9% | YES | YES | YES | The variance is attributed to reprioritizing money towards the installation of barrier posts around meter set assemblies that are vulnerable to vehicular contact. SDG&E is prioritizing these installations to reduce the risk to the gas system as economic growth and building (like remodels) has increased the exposure of meters to vehicular contact. | The variance is attributed to reprioritizing money towards the installation of barrier posts around meter set assemblies that are vulnerable to vehicular contact. SDG&E is prioritizing these installations to reduce the risk to the gas system as economic growth and building (like remodels) has increased the exposure of meters to vehicular contact. | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | Capital expenditures in budget code 507 are used to keep SDG&E's gas distribution system in compliance with State and Federal regulations for natural gas pipelines. | SDG&E-04-R-E LPK-88 to LPK-92 CWP 005070
Capital | GAS DISTRIBUTION | SubTotal CODE COMPLIANCE |  |  |  | Yes |  |  | 5466727.7013 | 0 | 0 | 0 | 5466727.7013 | 3076999.92 | 3169999.92 | 3264999.96 | 3362999.88 | 3076999.92 | 2389727.7813 | -3169999.92 | -3264999.96 | -3362999.88 | 2389727.7813 | 77.66% | -100% | -100% | -100% | 77.66% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | CONTRACT ADMIN – GAS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 5683921.363 | 0 | 0 | 0 | 5683921.363 | 6561000 | 6757999.92 | 6960999.96 | 7168999.92 | 6561000 | -877078.637 | -6757999.92 | -6960999.96 | -7168999.92 | -877078.637 | -13.37% | -100% | -100% | -100% | -13.37% | This activity included in this non-RAMP Contract Administration (CA) pool consists of those expenses necessary for the administration of projects that are performed by contractors for SDG&E. The expenses to this pool consist of labor for Contract Administrators and support personnel, as well as the associated non-labor support costs such as office and field supplies. This pool includes the costs that will be allocated to contracted work. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | GAS DISTRIBUTION | SubTotal CONTRACT ADMIN – GAS |  |  |  | Yes |  |  | 5683921.363 | 0 | 0 | 0 | 5683921.363 | 6561000 | 6757999.92 | 6960999.96 | 7168999.92 | 6561000 | -877078.637 | -6757999.92 | -6960999.96 | -7168999.92 | -877078.637 | -13.37% | -100% | -100% | -100% | -13.37% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | CURB VALVE REPLACEMENTS | Incident Related to the Medium Pressure System (Excluding Dig-in) | Replace Curb Valves with EFVs | MP Main & Service Plastic | No | On-going | Annual | 1323853.9442 | 0 | 0 | 0 | 1323853.9442 | 996999.96 | 1026999.96 | 1057999.92 | 1089999.96 | 996999.96 | 326853.9842 | -1026999.96 | -1057999.92 | -1089999.96 | 326853.9842 | 32.78% | -100% | -100% | -100% | 32.78% | Projects | 17 |  |  |  | 17 | 67 |  |  |  | 67 | -50 | 0 | 0 | 0 | -50 | -74.63% | 0% | 0% | 0% | -74.63% | YES | NO | YES | N/A | This variance is attributed to higher than forecasted costs per unit. The higher cost per unit is associated with increases in costs for supplies and materials and additional restoration requirements by the municipalities. | On Target (T) | Under (U) | Over (O) | Proceeding as Planned | NO | N/A | The Curb Valve Replacement project will survey the gas system for installed curb valves, prioritize their replacement based on inaccessibility issues and schedule the replacement of these valves with excess flow valve (EFVs). | SDG&E-04-R-E LPK-119 to LPK-121 CWP 215750
Capital | GAS DISTRIBUTION | SubTotal CURB VALVE REPLACEMENTS |  |  |  | Yes |  |  | 1323853.9442 | 0 | 0 | 0 | 1323853.9442 | 996999.96 | 1026999.96 | 1057999.92 | 1089999.96 | 996999.96 | 326853.9842 | -1026999.96 | -1057999.92 | -1089999.96 | 326853.9842 | 32.78% | -100% | -100% | -100% | 32.78% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | DEPARTMENT OVERHEAD POOL - GAS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 14627188.8513 | 0 | 0 | 0 | 14627188.8513 | 5871999.96 | 6048000 | 6228999.96 | 6414999.96 | 5871999.96 | 8755188.8913 | -6048000 | -6228999.96 | -6414999.96 | 8755188.8913 | 149.1% | -100% | -100% | -100% | 149.1% | The activities included in this non-RAMP Department Overhead pool consists of expenses for supervision and administration of gas crews in the SDG&E Construction and Operation (C&O) districts. Department Overhead is charged for expenses that are not attributable to one particular project, but benefit many projects, or the Construction and Operation (C&O) districts as a whole. Certain costs are incurred by capital projects that originate from central activities, which are subsequently distributed to those capital projects. These central activity costs are also called ‘pooled’ or ‘overhead’ costs. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | This variance is attributed to an increase in capital work being performed by internal gas construction crews versus completed by contract crews. This can be seen by the decrease in the Contractor Administration Pool workpaper in 2024 as well as the decrease in O&M compared to what was forecasted for both areas in 2024. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Department Overhead is charged for expenses that are not attributable to one particular project, but benefit many projects, or the Construction and Operation (C&O) districts as a whole. Certain costs are incurred by capital projects that originate from central activities which are subsequently distributed to those capital projects. These central activity costs are also called 'pooled' or 'indirect' costs. | SDG&E-04-R-E LPK-129 to LPK-131 CWP G09050
Capital | GAS DISTRIBUTION | SubTotal DEPARTMENT OVERHEAD POOL - GAS |  |  |  | Yes |  |  | 14627188.8513 | 0 | 0 | 0 | 14627188.8513 | 5871999.96 | 6048000 | 6228999.96 | 6414999.96 | 5871999.96 | 8755188.8913 | -6048000 | -6228999.96 | -6414999.96 | 8755188.8913 | 149.1% | -100% | -100% | -100% | 149.1% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | DISTRIBUTION EASEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 7192.2 | 0 | 0 | 0 | 7192.2 | 0 | 0 | 0 | 0 | 0 | 7192.2 | 0 | 0 | 0 | 7192.2 | 100% | 0% | 0% | 0% | 100% | This activity involves work required to perform necessary surveys and mapping functions, document research, document preparation, and negotiations for the acquisition of easements to allow the installation of gas distribution facilities on private property or public lands. The variety of work activities in this category makes it infeasible to identify a single unit of measure. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | GAS DISTRIBUTION | SubTotal DISTRIBUTION EASEMENTS |  |  |  | Yes |  |  | 7192.2 | 0 | 0 | 0 | 7192.2 | 0 | 0 | 0 | 0 | 0 | 7192.2 | 0 | 0 | 0 | 7192.2 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | EARLY VINTAGE PROGRAM - DRESSER MECHANICAL COUPLING REMOVAL | Incident Related to the Medium Pressure System (Excluding Dig-in) | Early Vintage Program- Dresser Mech Coupling Removal | Main Steel | No | On-going | Annual | 1575713.0348 | 0 | 0 | 0 | 1575713.0348 | 498000 | 513000 | 528000 | 543999.96 | 498000 | 1077713.0348 | -513000 | -528000 | -543999.96 | 1077713.0348 | 216.4% | -100% | -100% | -100% | 216.4% | Projects | 4 |  |  |  | 4 | 4 |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | YES | NO | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Budget code 19566 provides funds for evaluating locations where Dresser mechanical couplings exist, excavating, removing the Dresser mechanical couplings, and reconnecting the pipeline back together. Removing these couplings mitigates the risk of an incident caused by the leakage of gas from these couplings. | SDG&E-04-R-E LPK-109 to LPK-110 CWP 195660
Capital | GAS DISTRIBUTION | SubTotal EARLY VINTAGE PROGRAM - DRESSER MECHANICAL COUPLING REMOVAL |  |  |  | Yes |  |  | 1575713.0348 | 0 | 0 | 0 | 1575713.0348 | 498000 | 513000 | 528000 | 543999.96 | 498000 | 1077713.0348 | -513000 | -528000 | -543999.96 | 1077713.0348 | 216.4% | -100% | -100% | -100% | 216.4% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | EARLY VINTAGE PROGRAM - OIL DRIP PIPING REMOVAL | Incident Related to the Medium Pressure System (Excluding Dig-in) | Early Vintage Program- Oil Drip Piping Removal | Main Steel | No | On-going | Annual | 1006040.9074 | 0 | 0 | 0 | 1006040.9074 | 1494999.96 | 1539999.96 | 1585999.92 | 1633999.92 | 1494999.96 | -488959.0526 | -1539999.96 | -1585999.92 | -1633999.92 | -488959.0526 | -32.71% | -100% | -100% | -100% | -32.71% | Projects | 3 |  |  |  | 3 | 12 |  |  |  | 12 | -9 | 0 | 0 | 0 | -9 | -75% | 0% | 0% | 0% | -75% | YES | NO | YES | N/A | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Budget code 19567 provides the funding to analyze gas system mapping to determine oil drip piping locations and prioritize their removal. In addition, funding is provided to remove this piping at selected locations. | SDG&E-04-R-E LPK-110 to LPK-112 CWP 195670
Capital | GAS DISTRIBUTION | SubTotal EARLY VINTAGE PROGRAM - OIL DRIP PIPING REMOVAL |  |  |  | Yes |  |  | 1006040.9074 | 0 | 0 | 0 | 1006040.9074 | 1494999.96 | 1539999.96 | 1585999.92 | 1633999.92 | 1494999.96 | -488959.0526 | -1539999.96 | -1585999.92 | -1633999.92 | -488959.0526 | -32.71% | -100% | -100% | -100% | -32.71% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | EARLY VINTAGE PROGRAM - REMOVAL OF CLOSED VALVES BETWEEN HP/MP ZONES | Incident Related to the Medium Pressure System (Excluding Dig-in) | Early Vintage Program-Remove Closed Valves b/w HP/MP | Main Steel | No | On-going | Annual | 633357.1228 | 0 | 0 | 0 | 633357.1228 | 889999.92 | 916999.92 | 945000 | 972999.96 | 889999.92 | -256642.7972 | -916999.92 | -945000 | -972999.96 | -256642.7972 | -28.84% | -100% | -100% | -100% | -28.84% | Projects | 1 |  |  |  | 1 | 6 |  |  |  | 6 | -5 | 0 | 0 | 0 | -5 | -83.33% | 0% | 0% | 0% | -83.33% | YES | NO | YES | N/A | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project provides funds to select and remove system block valves that separate high pressure and medium pressure zones. This would mitigate the risk should the valve be operated in error, operated in an act of sabotage, or the valve leak pressure downstream to the lower Maximum Allowable Operating Pressure (MAOP) system potentially causing an overpressure condition of the downstream system. | SDG&E-04-R-E LPK-113 to LPK-114 CWP 195690
Capital | GAS DISTRIBUTION | SubTotal EARLY VINTAGE PROGRAM - REMOVAL OF CLOSED VALVES BETWEEN HP/MP ZONES |  |  |  | Yes |  |  | 633357.1228 | 0 | 0 | 0 | 633357.1228 | 889999.92 | 916999.92 | 945000 | 972999.96 | 889999.92 | -256642.7972 | -916999.92 | -945000 | -972999.96 | -256642.7972 | -28.84% | -100% | -100% | -100% | -28.84% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | GAS OPS CONTROL CENTER PROJ DISTR REG STATION & OTHER | Incident Related to the Medium Pressure System (Excluding Dig-in) | CCM Distribution Field Asset Real Time Monitoring | N/A | No | On-going | Annual | 1935413.7516 | 0 | 0 | 0 | 1935413.7516 | 3765000 | 3877999.92 | 3993999.96 | 4113999.96 | 3765000 | -1829586.2484 | -3877999.92 | -3993999.96 | -4113999.96 | -1829586.2484 | -48.59% | -100% | -100% | -100% | -48.59% | Supervisory control and data acquisition monitored sites | 0 |  |  |  | 0 | 3 |  |  |  | 3 | -3 | 0 | 0 | 0 | -3 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | This workpaper was intended for the capital construction of SCADA sites on regulator stations in the SDG&E service territory. The design and construction of these types of activities can take several years. The capital construction of these sites is ongoing, but as of end of 2024 zero sites had come online to send data, be monitored, or controlled. The plan is for these sites to come on-line in 2025. | This workpaper was intended for the capital construction of SCADA sites on regulator stations in the SDG&E service territory. The design and construction of these types of activities can take several years. The capital construction of these sites is ongoing, but as of end of 2024 zero sites had come online to send data, be monitored, or controlled. The plan is for these sites to come on-line in 2025. | On Target (T) | Under (U) | On Target (T) | Proceeding as Planned | NO | N/A | The purpose of the Control Center Modernization (CCM) project is to construct a new modernized Gas Control facility that will include advanced technology and be sized to accommodate the expanding workforce needed to monitor, maintain, and respond to data transmitted by the over 9,800 new and existing field assets and incidents on a continuous 24/7 basis. The costs detailed in this section are related to the field assets that will be deployed on the SDG&E distribution system. | SDG&E-04-R-E LPK-117 to LPK-119 CWP 215740
Capital | GAS DISTRIBUTION | SubTotal GAS OPS CONTROL CENTER PROJ DISTR REG STATION & OTHER |  |  |  | Yes |  |  | 1935413.7516 | 0 | 0 | 0 | 1935413.7516 | 3765000 | 3877999.92 | 3993999.96 | 4113999.96 | 3765000 | -1829586.2484 | -3877999.92 | -3993999.96 | -4113999.96 | -1829586.2484 | -48.59% | -100% | -100% | -100% | -48.59% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | LEAK REPAIR | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair (Capital) | MP Main Plastic | No | On-going | Annual | 6586365.6424 | 0 | 0 | 0 | 6586365.6424 | 3907999.92 | 4024999.92 | 4146000 | 4270999.92 | 3907999.92 | 2678365.7224 | -4024999.92 | -4146000 | -4270999.92 | 2678365.7224 | 68.54% | -100% | -100% | -100% | 68.54% | Projects MP Plastic | 184 |  |  |  | 184 | 238 |  |  |  | 238 | -54 | 0 | 0 | 0 | -54 | -22.69% | 0% | 0% | 0% | -22.69% | YES | YES | YES | This activity covers the repair of leaking plastic mains. This variance is attributed to higher than forecasted costs per unit. The higher cost per unit is associated with increases in costs associated with supplies and materials and additional restoration requirements by the municipalities. | This activity covers the repair of leaking plastic mains. The scope of projects is based on factors outside of SDG&E’s control. However, with the inception of increased leak survey funded by SB 1371, the number of capital and O&M leaks has seen a linear increase in cost and units. SB 1371 did not authorize SDGE to repair those leaks identified through increased leak survey with SB 1371 funds and as such SDG&E has seen a linear increase in costs and units for leak repair. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Expenditures in budget code 508 support SDG&E's continued safe and reliable delivery of natural gas in compliance with State and Federal code requirements for replacement of gas distribution system piping due to poor condition or location. | SDG&E-04-R-E LPK-92 to LPK-94 CWP 005080
Capital | GAS DISTRIBUTION | LEAK REPAIR | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair (Capital) | MP Main Steel | No | On-going | Annual | 9879548.4636 | 0 | 0 | 0 | 9879548.4636 | 6138999.96 | 6322999.92 | 6511999.92 | 6706999.92 | 6138999.96 | 3740548.5036 | -6322999.92 | -6511999.92 | -6706999.92 | 3740548.5036 | 60.93% | -100% | -100% | -100% | 60.93% | Projects MP Steel | 289 |  |  |  | 289 | 374 |  |  |  | 374 | -85 | 0 | 0 | 0 | -85 | -22.73% | 0% | 0% | 0% | -22.73% | YES | YES | YES | This activity covers the repair of leaking steel mains. This variance is attributed to higher than forecasted costs per unit. The higher cost per unit is associated with increases in costs associated with supplies and materials and additional restoration requirements by the municipalities. | This activity covers the repair of leaking plastic mains. The scope of projects is based on factors outside of SDG&E’s control. However, with the inception of increased leak survey funded by SB 1371, the number of capital and O&M leaks has seen a linear increase in cost and units. SB 1371 did not authorize SDGE to repair those leaks identified through increased leak survey with SB 1371 funds and as such SDG&E has seen a linear increase in costs and units for leak repair. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Expenditures in budget code 508 support SDG&E's continued safe and reliable delivery of natural gas in compliance with State and Federal code requirements for replacement of gas distribution system piping due to poor condition or location. | SDG&E-04-R-E LPK-92 to LPK-94 CWP 005080
Capital | GAS DISTRIBUTION | SubTotal LEAK REPAIR |  |  |  | Yes |  |  | 16465914.106 | 0 | 0 | 0 | 16465914.106 | 10046999.88 | 10347999.84 | 10657999.92 | 10977999.84 | 10046999.88 | 6418914.226 | -10347999.84 | -10657999.92 | -10977999.84 | 6418914.226 | 63.89% | -100% | -100% | -100% | 63.89% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 22386882.555 | 0 | 0 | 0 | 22386882.555 | 22357999.92 | 23026999.92 | 23718000 | 24429000 | 22357999.92 | 28882.635 | -23026999.92 | -23718000 | -24429000 | 28882.635 | 0.1292% | -100% | -100% | -100% | 0.1292% | This activity includes non-RAMP related work performed by both company employees and contracted personnel based on availability and skill sets required of each project’s scope of work. The type of work includes project management, engineering, design, and drafting cost for both internal and external resources to support capital investment. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO
Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factors Mitigations - Gas Handling Plans | N/A | No | On-going | Annual | 240130.308 | 0 | 0 | 0 | 240130.308 | 288000 | 297000 | 306000 | 315000 | 288000 | -47869.692 | -297000 | -306000 | -315000 | -47869.692 | -16.62% | -100% | -100% | -100% | -16.62% | Gas handling plans | 262 |  |  |  | 262 | 499 |  |  |  | 499 | -237 | 0 | 0 | 0 | -237 | -47.49% | 0% | 0% | 0% | -47.49% | YES | NO | YES | N/A | The variance is due to a shift in capital work to jobs that do not require a Gas Handling Plan (GHP) such as cathodic protection replacements and barrier post placements. Additionally, there was a shift towards HP jobs which produced fewer GHP units compared to the dollars allocated. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This budget code represents the forecasted costs associated with the Gas Distribution Local Engineering (LE) Pool. Certain costs are incurred by capital projects that originate from central activities which are subsequently distributed to those capital projects. These central activity costs are also called 'pooled' or 'indirect' costs | SDG&E-04-R-E LPK-122 to LPK-129 CWP G09020
Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Records Management | GGIS Growth | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 126000 | 129999.96 | 133999.92 | 138000 | 126000 | -126000 | -129999.96 | -133999.92 | -138000 | -126000 | -100% | -100% | -100% | -100% | -100% | FTE | 0 |  |  |  | 0 | 2 |  |  |  | 2 | -2 | 0 | 0 | 0 | -2 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Variance is due to the timing of hiring two Gas Geographic Information specialists. | On Target (T) | Under (U) | Under (U) | Deferred | NO | N/A | This budget code represents the forecasted costs associated with the Gas Distribution Local Engineering (LE) Pool. Certain costs are incurred by capital projects that originate from central activities which are subsequently distributed to those capital projects. These central activity costs are also called 'pooled' or 'indirect' costs. | SDG&E-04-R-E LPK-122 to LPK-129 CWP G09020
Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Records Management | RAMP: SDG&E-CFF-6, New: Gas Geographic Information System Group | N/A | No | On-going | Annual | 2430710.6976 | 0 | 0 | 0 | 2430710.6976 | 909000 | 936000 | 963999.96 | 993000 | 909000 | 1521710.6976 | -936000 | -963999.96 | -993000 | 1521710.6976 | 167.4% | -100% | -100% | -100% | 167.4% | Reconciled work orders | 3366 |  |  |  | 3366 | 2901 |  |  |  | 2901 | 465 | 0 | 0 | 0 | 465 | 16.03% | 0% | 0% | 0% | 16.03% | YES | YES | NO | The variance is associated with an increase in the work needed to reconcile GIS maps based on capital work. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This budget code represents the forecasted costs associated with the Gas Distribution Local Engineering (LE) Pool. Certain costs are incurred by capital projects that originate from central activities which are subsequently distributed to those capital projects. These central activity costs are also called 'pooled' or 'indirect' costs. | SDG&E-04-R-E LPK-122 to LPK-129 CWP G09020
Capital | GAS DISTRIBUTION | SubTotal LOCAL ENGINEERING POOL - GAS |  |  |  | Yes |  |  | 25057723.5606 | 0 | 0 | 0 | 25057723.5606 | 23680999.92 | 24389999.88 | 25121999.88 | 25875000 | 23680999.92 | 1376723.6406 | -24389999.88 | -25121999.88 | -25875000 | 1376723.6406 | 5.814% | -100% | -100% | -100% | 5.814% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | METER AND REGULATOR MATERIALS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 10134979.73 | 0 | 0 | 0 | 10134979.73 | 8344999.92 | 8595000 | 8853000 | 9118999.92 | 8344999.92 | 1789979.81 | -8595000 | -8853000 | -9118999.92 | 1789979.81 | 21.45% | -100% | -100% | -100% | 21.45% | Meters and regulators | 79658 |  |  |  | 79658 | 104688 |  |  |  | 104688 | -25030 | 0 | 0 | 0 | -25030 | -23.91% | 0% | 0% | 0% | -23.91% | YES | YES | YES | The variance is attributed to an increase in cost per unit (higher material, labor and longer lead times) that was not forecasted in the 2024 GRC. Additionally, the variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | The variance is attributed to an increase in cost per unit (higher material, labor and longer lead times) that was not forecasted in the 2024 GRC. Additionally, the variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Budget code 502 provides funding for the purchase of new domestic, commercial and industrial gas meters and regulators used in establishing service to new customers, and also for replacement of meters and regulators that have reached the end of their useful life or are removed as part of the Gas Meter Performance Control Program. | SDG&E-04-R-E LPK-77 to LPK-79 CWP 005020
Capital | GAS DISTRIBUTION | SubTotal METER AND REGULATOR MATERIALS |  |  |  | Yes |  |  | 10134979.73 | 0 | 0 | 0 | 10134979.73 | 8344999.92 | 8595000 | 8853000 | 9118999.92 | 8344999.92 | 1789979.81 | -8595000 | -8853000 | -9118999.92 | 1789979.81 | 21.45% | -100% | -100% | -100% | 21.45% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | NEW BUSINESS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 7694613.4761 | 0 | 0 | 0 | 7694613.4761 | 4753999.92 | 4896999.96 | 5043999.96 | 5194999.92 | 4753999.92 | 2940613.5561 | -4896999.96 | -5043999.96 | -5194999.92 | 2940613.5561 | 61.86% | -100% | -100% | -100% | 61.86% | The variety and scope of work for each new business (customer-driven gas service) project makes it infeasible to identify a single imputed authorized unit of measure. The number and timing of new pipeline projects is based on factors outside the control of SDG&E. The variety of work activities in this category makes it infeasible to identify a single unit of measure. | [20 empty] | YES | YES | NO | This activity involves installing new pipeline associated with providing gas service to new business. The number and timing of new pipeline projects is based on factors outside the control of SDG&E. This variance is attributed to a several large customer paid jobs over original forecasted activity. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Expenditures within budget code 500 provide for changes and additions to the existing gas distribution system for the purpose of serving new gas customers. | SDG&E-04-R-E LPK-70 to LPK-74 CWP 005000
Capital | GAS DISTRIBUTION | SubTotal NEW BUSINESS |  |  |  | Yes |  |  | 7694613.4761 | 0 | 0 | 0 | 7694613.4761 | 4753999.92 | 4896999.96 | 5043999.96 | 5194999.92 | 4753999.92 | 2940613.5561 | -4896999.96 | -5043999.96 | -5194999.92 | 2940613.5561 | 61.86% | -100% | -100% | -100% | 61.86% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | PIPE RELOCATIONS - FRANCHISE AND FREEWAY | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 9239246.8259 | 0 | 0 | 0 | 9239246.8259 | 5755999.92 | 5928999.96 | 6106999.92 | 6289999.92 | 5755999.92 | 3483246.9059 | -5928999.96 | -6106999.92 | -6289999.92 | 3483246.9059 | 60.52% | -100% | -100% | -100% | 60.52% | Projects | 25 |  |  |  | 25 | 48 |  |  |  | 48 | -23 | 0 | 0 | 0 | -23 | -47.92% | 0% | 0% | 0% | -47.92% | YES | YES | YES | This activity covers the relocation of existing gas distribution facilities when necessitated by public improvements, as required by the company’s franchise agreements to clear municipal or other improvements. The scope of projects is based on factors outside of SDG&E’s control, and the number of projects anticipated was beyond forecasted expectations. | This activity covers the relocation of existing gas distribution facilities when necessitated by public improvements, as required by the company’s franchise agreements to clear municipal or other improvements. The scope of projects is based on factors outside of SDG&E’s control, and the number of projects anticipated was beyond forecasted expectations. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Budget code 505 provides funding for the required relocation of existing gas facilities when necessitated by conflict with the installation of public improvements | SDG&E-04-R-E LPK-82 to LPK-84 CWP 005050
Capital | GAS DISTRIBUTION | SubTotal PIPE RELOCATIONS - FRANCHISE AND FREEWAY |  |  |  | Yes |  |  | 9239246.8259 | 0 | 0 | 0 | 9239246.8259 | 5755999.92 | 5928999.96 | 6106999.92 | 6289999.92 | 5755999.92 | 3483246.9059 | -5928999.96 | -6106999.92 | -6289999.92 | 3483246.9059 | 60.52% | -100% | -100% | -100% | 60.52% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | PIPING IN VAUTS REPLACEMENT PROGRAM | Incident Related to the Medium Pressure System (Excluding Dig-in) | Piping in Vaults Replacement Program | MP Main Steel | No | On-going | Annual | 328078.8664 | 0 | 0 | 0 | 328078.8664 | 1494999.96 | 1539999.96 | 1585999.92 | 1633999.92 | 1494999.96 | -1166921.0936 | -1539999.96 | -1585999.92 | -1633999.92 | -1166921.0936 | -78.05% | -100% | -100% | -100% | -78.05% | Projects | 1 |  |  |  | 1 | 8 |  |  |  | 8 | -7 | 0 | 0 | 0 | -7 | -87.5% | 0% | 0% | 0% | -87.5% | YES | YES | YES | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project provides funds for the selection and replacement of piping located in underground vaults. Pipe segments, fittings, or valves exposed within a below grade vault is at risk for accelerated atmospheric corrosion due to the potential for water accumulation or pipe coating failure. | SDG&E-04-R-E LPK-115 to LPK-116 CWP 195680
Capital | GAS DISTRIBUTION | SubTotal |  |  |  | Yes |  |  | 328078.8664 | 0 | 0 | 0 | 328078.8664 | 1494999.96 | 1539999.96 | 1585999.92 | 1633999.92 | 1494999.96 | -1166921.0936 | -1539999.96 | -1585999.92 | -1633999.92 | -1166921.0936 | -78.05% | -100% | -100% | -100% | -78.05% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | PRESSURE BETTERMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 495474.3913 | 0 | 0 | 0 | 495474.3913 | 0 | 0 | 0 | 0 | 0 | 495474.3913 | 0 | 0 | 0 | 495474.3913 | 100% | 0% | 0% | 0% | 100% | Projects | 1 |  |  |  | 1 | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | The variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Expenditures within budget code 503 provide for gas distribution system reinforcement projects required to maintain gas service to core customers. This work category addresses critical areas of the distribution pipeline network that are most susceptible to pressure drops to alleviate the potential risk of loss of service to customers. | SDG&E-04-R-E LPK-80 to LPK-82 CWP 005030
Capital | GAS DISTRIBUTION | SubTotal PRESSURE BETTERMENT |  |  |  | Yes |  |  | 495474.3913 | 0 | 0 | 0 | 495474.3913 | 0 | 0 | 0 | 0 | 0 | 495474.3913 | 0 | 0 | 0 | 495474.3913 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | REGULATOR STATION IMPROVEMENTS AND OTHER | Incident Related to the Medium Pressure System (Excluding Dig-in) | Reg Station Replacement Program | HP Supply Line | No | On-going | Annual | 1041238.1435 | 0 | 0 | 0 | 1041238.1435 | 213999.96 | 220999.92 | 226999.92 | 234000 | 213999.96 | 827238.1835 | -220999.92 | -226999.92 | -234000 | 827238.1835 | 386.6% | -100% | -100% | -100% | 386.6% | Projects | 1 |  |  |  | 1 | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | The variance is associated with two primary reasons: Large project work managed in alignment with TY 2019 GRC was delayed due to easements and permits with CalTrans & City of San Diego from 2023. Project work was managed in alignment with 2024 forecasts submitted in SDG&E's TY 2024 GRC application. GRC final decision not issued until December 2024. SDG&E continued projects as planned while waiting for the final TY 2024 GRC Decision. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Budget code 510 provides funding for small capital projects or upgrades (not captured under the other budget codes) that improve safety, provide required code compliance, and improve gas system performance or reliability through the replacement of aging gas operating equipment | SDG&E-04-R-E LPK-100 to LPK-102 CWP 005100
Capital | GAS DISTRIBUTION | REGULATOR STATION IMPROVEMENTS AND OTHER | Incident Related to the Medium Pressure System (Excluding Dig-in) | Reg Station Replacement Program | HP-MP Main Steel & Plastic | No | On-going | Annual | 2114028.958 | 0 | 0 | 0 | 2114028.958 | 429000 | 441000 | 454999.92 | 468000 | 429000 | 1685028.958 | -441000 | -454999.92 | -468000 | 1685028.958 | 392.8% | -100% | -100% | -100% | 392.8% | Projects | 2 |  |  |  | 2 | 1 |  |  |  | 1 | 1 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 100% | YES | YES | YES | The variance is associated with easement and permitting delays from 2023. Additionally, the variance is due to project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | The variance is associated with easement and permitting delays from 2023. Additionally, the variance is due to project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Budget code 510 provides funding for small capital projects or upgrades (not captured under the other budget codes) that improve safety, provide required code compliance, and improve gas system performance or reliability through the replacement of aging gas operating equipment | SDG&E-04-R-E LPK-100 to LPK-102 CWP 005100
Capital | GAS DISTRIBUTION | SubTotal REGULATOR STATION IMPROVEMENTS AND OTHER |  |  |  | Yes |  |  | 3155267.1014 | 0 | 0 | 0 | 3155267.1014 | 642999.96 | 661999.92 | 681999.84 | 702000 | 642999.96 | 2512267.1414 | -661999.92 | -681999.84 | -702000 | 2512267.1414 | 390.7% | -100% | -100% | -100% | 390.7% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | SYSTEMS MINOR ADDITIONS, RELOCATIONS AND RETIREMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 7213219.6766 | 0 | 0 | 0 | 7213219.6766 | 5202000 | 5358000 | 5518999.92 | 5683999.92 | 5202000 | 2011219.6766 | -5358000 | -5518999.92 | -5683999.92 | 2011219.6766 | 38.66% | -100% | -100% | -100% | 38.66% | Projects | 46 |  |  |  | 46 | The variety and scope of work for each system addition, relocation, or retirement (customer-driven) project makes it infeasible to identify a single imputed authorized unit. The number and timing of addition, relocation, or retirements are based on factors outside the control of SDG&E. |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 100% | YES | YES | NO | This activity covers the relocation of existing gas distribution facilities when necessitated by customer initiated improvements. The scope of projects is based on factors outside of SDG&E’s control. Most come from customer requests or expenses involved in customer encroachments and the number of projects was greater than forecasted. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Expenses in budget code 501 provide for minor gas distribution main and service additions, retirements and relocations. These expenditures are required to maintain the continued integrity of SDG&E's gas distribution system | SDG&E-04-R-E LPK-74 to LPK-77 CWP 005010
Capital | GAS DISTRIBUTION | SubTotal SYSTEMS MINOR ADDITIONS, RELOCATIONS AND RETIREMENTS |  |  |  | Yes |  |  | 7213219.6766 | 0 | 0 | 0 | 7213219.6766 | 5202000 | 5358000 | 5518999.92 | 5683999.92 | 5202000 | 2011219.6766 | -5358000 | -5518999.92 | -5683999.92 | 2011219.6766 | 38.66% | -100% | -100% | -100% | 38.66% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | TOOLS AND EQUIPMENT | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 897178.17 | 0 | 0 | 0 | 897178.17 | 3024999.96 | 3115999.92 | 3210000 | 3306000 | 3024999.96 | -2127821.79 | -3115999.92 | -3210000 | -3306000 | -2127821.79 | -70.34% | -100% | -100% | -100% | -70.34% | Tools ordered | 12 |  |  |  | 12 | The need for tools and equipment is influenced by the age and condition of the tools, technology, ergonomics, and changes in company gas standards and procedures, which make it infeasible to identify a single imputed authorized unit. |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% | 100% | YES | YES | NO | The funds associated with this workpaper are used to acquire tools and equipment for use by gas crews. The costs associated with this workpaper were shifted to other workpapers in Gas Distribution (like Leak Repair and Cathodic Protection) to help address higher risk activities. To address this some new or replacement tool purchases were deferred to 2025. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Budget code 506 provides funds for new tools and equipment required by field personnel in order to safely and efficiently install, operate and maintain the gas distribution system as well as maintenance of the inventory of training equipment at the "Skills City" training facility at SDG&E where gas operations activities are simulated. | SDG&E-04-R-E LPK-84 to LPK-88 CWP 005060
Capital | GAS DISTRIBUTION | TOOLS AND EQUIPMENT | Excavation Damage (Dig-In) on the Gas System | Locating Equipment | MP | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 210000 | 216000 | 222999.96 | 229999.92 | 210000 | -210000 | -216000 | -222999.96 | -229999.92 | -210000 | -100% | -100% | -100% | -100% | -100% | Mobile docking terminals | 0 |  |  |  | 0 | 43 |  |  |  | 43 | -43 | 0 | 0 | 0 | -43 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The funds associated with this workpaper are used to acquire tools and equipment for use by gas crews. The costs associated with this workpaper were shifted to other workpapers in Gas Distribution (like Leak Repair and Cathodic Protection) to help address higher risk activities. To address this some new or replacement tool purchases were deferred to 2025. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | Budget code 506 provides funds for new tools and equipment required by field personnel in order to safely and efficiently install, operate and maintain the gas distribution system as well as maintenance of the inventory of training equipment at the "Skills City" training facility at SDG&E where gas operations activities are simulated. | SDG&E-04-R-E LPK-84 to LPK-88 CWP 005060
Capital | GAS DISTRIBUTION | TOOLS AND EQUIPMENT | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factor Mitigations - OpQual Training & Cert | N/A | No | On-going | Annual | 151000 | 0 | 0 | 0 | 151000 | 411000 | 423000 | 435999.96 | 448999.92 | 411000 | -260000 | -423000 | -435999.96 | -448999.92 | -260000 | -63.26% | -100% | -100% | -100% | -63.26% | Employee/contractors trained on an operator qualified task | 899 |  |  |  | 899 | 696 |  |  |  | 696 | 203 | 0 | 0 | 0 | 203 | 29.17% | 0% | 0% | 0% | 29.17% | YES | NO | YES | N/A | This unit variance is attributed to higher than forecast numbers of employees and contractors having to obtain Operator Qualifications to work on the SDG&E Gas system. This number can fluctuate depending on employee and contractor turnover. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Budget code 506 provides funds for new tools and equipment required by field personnel in order to safely and efficiently install, operate and maintain the gas distribution system as well as maintenance of the inventory of training equipment at the "Skills City" training facility at SDG&E where gas operations activities are simulated. | SDG&E-04-R-E LPK-84 to LPK-88 CWP 005060
Capital | GAS DISTRIBUTION | SubTotal TOOLS AND EQUIPMENT |  |  |  | Yes |  |  | 1048178.17 | 0 | 0 | 0 | 1048178.17 | 3645999.96 | 3754999.92 | 3868999.92 | 3984999.84 | 3645999.96 | -2597821.79 | -3754999.92 | -3868999.92 | -3984999.84 | -2597821.79 | -71.25% | -100% | -100% | -100% | -71.25% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | UNDERPERFORMING STEEL REPLACEMENT PROGRAM - OTHER (POST 1965 VINTAGE) | Incident Related to the Medium Pressure System (Excluding Dig-in) | Underperforming Steel Replacement Program - Other Steel (Post-1965 Vintage) | MP Main Steel | No | On-going | Annual | 1532684.5051 | 0 | 0 | 0 | 1532684.5051 | 2989999.92 | 3079999.92 | 3171999.96 | 3267000 | 2989999.92 | -1457315.4149 | -3079999.92 | -3171999.96 | -3267000 | -1457315.4149 | -48.74% | -100% | -100% | -100% | -48.74% | Feet | 6653 |  |  |  | 6653 | 18750 |  |  |  | 18750 | -12097 | 0 | 0 | 0 | -12097 | -64.52% | 0% | 0% | 0% | -64.52% | YES | YES | YES | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Expenditures within budget code 514 provide for the planned replacement of pipelines based on replacement decision elements with strong emphasis on a recurring leak history. | SDG&E-04-R-E LPK-107 to LPK-108 CWP 005140
Capital | GAS DISTRIBUTION | SubTotal UNDERPERFORMING STEEL REPLACEMENT PROGRAM - OTHER (POST 1965 VINTAGE) |  |  |  | Yes |  |  | 1532684.5051 | 0 | 0 | 0 | 1532684.5051 | 2989999.92 | 3079999.92 | 3171999.96 | 3267000 | 2989999.92 | -1457315.4149 | -3079999.92 | -3171999.96 | -3267000 | -1457315.4149 | -48.74% | -100% | -100% | -100% | -48.74% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS DISTRIBUTION | UNDERPERFORMING STEEL REPLACEMENT PROGRAM - THREADED MAIN (PRE-1934 VINTAGE) | Incident Related to the Medium Pressure System (Excluding Dig-in) | Underperforming Steel Replacement Program (Pre-1934 vintage) | MP Main Steel | No | On-going | Annual | 8009702.5429 | 0 | 0 | 0 | 8009702.5429 | 6975999.96 | 7185000 | 7401000 | 7623000 | 6975999.96 | 1033702.5829 | -7185000 | -7401000 | -7623000 | 1033702.5829 | 14.82% | -100% | -100% | -100% | 14.82% | Feet | 28618 |  |  |  | 28618 | 21875 |  |  |  | 21875 | 6743 | 0 | 0 | 0 | 6743 | 30.83% | 0% | 0% | 0% | 30.83% | YES | NO | YES | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Budget code 19565 provides funding specifically for the removal of early vintage (pre-1934) steel pipelines that were threaded together rather than welded. This practice was later abandoned in favor of welding the pipe. The threaded pipe is prone to higher rate of leakage due to susceptibility to corrosion near the threaded joint and offers less corrosion allowance than the standard welded pipe due to the thread cuts. | SDG&E-04-R-E LPK-103 to LPK-105 CWP 195650
Capital | GAS DISTRIBUTION | SubTotal UNDERPERFORMING STEEL REPLACEMENT PROGRAM - THREADED MAIN (PRE-1934 VINTAGE) |  |  |  | Yes |  |  | 8009702.5429 | 0 | 0 | 0 | 8009702.5429 | 6975999.96 | 7185000 | 7401000 | 7623000 | 6975999.96 | 1033702.5829 | -7185000 | -7401000 | -7623000 | 1033702.5829 | 14.82% | -100% | -100% | -100% | 14.82% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS DISTRIBUTION | UNDERPERFORMING STEEL REPLACEMENT PROGRAM (1934-1965 VINTAGE) | Incident Related to the Medium Pressure System (Excluding Dig-in) | Underperforming Steel Replacement Program - 1934-1965 Vintage (19564) | MP Main Steel | No | On-going | Annual | 5182096.114 | 0 | 0 | 0 | 5182096.114 | 2989999.92 | 3079999.92 | 3171999.96 | 3267000 | 2989999.92 | 2192096.194 | -3079999.92 | -3171999.96 | -3267000 | 2192096.194 | 73.31% | -100% | -100% | -100% | 73.31% | Feet | 20222 |  |  |  | 20222 | 11111 |  |  |  | 11111 | 9111 | 0 | 0 | 0 | 9111 | 82% | 0% | 0% | 0% | 82% | YES | YES | YES | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | In 2024, SDG&E started to manage the three steel replacement programs, and 4 component programs (dresser coupling removal, oil drip removal, piping in vaults removal and HP/MP block valve removal component) holistically as a single program to address the highest risks across the system first and to gain efficiencies when addressing risk. The decision to combine these workpapers together allows SDG&E to pinpoint and remove gas facilities based on total overall risk to the system. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | Expenditures within budget code 19564 provide for the removal and replacement of early vintage steel pipelines (installed in the gas distribution system from 1934 to 1965) that due to pipe wrap disbonding lose their cathodic protection leading to increased leakage. | SDG&E-04-R LPK-105 to LPK-106 CWP 195640
Capital | GAS DISTRIBUTION | SubTotal UNDERPERFORMING STEEL REPLACEMENT PROGRAM (1934-1965 VINTAGE) |  |  |  | Yes |  |  | 5182096.114 | 0 | 0 | 0 | 5182096.114 | 2989999.92 | 3079999.92 | 3171999.96 | 3267000 | 2989999.92 | 2192096.194 | -3079999.92 | -3171999.96 | -3267000 | 2192096.194 | 73.31% | -100% | -100% | -100% | 73.31% | [21 empty] | YES | YES | [7 empty] | NO

## GOGT-C
SDG&E GAS TRANSMISSION OPERATIONS AND CONSTRUCTION Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | GAS TRANSMISSION OPERATIONS AND CONSTRUCTION | GAS TRANSMISSION OPERATIONS AND CONSTRUCTION |  |  |  | Yes |  |  | 67661434.2114 | 0 | 0 | 0 | 67661434.2114 | 11663999.52 | 12012999.24 | 12372999.48 | 12743999.4 | 11663999.52 | 55997434.6914 | -12012999.24 | -12372999.48 | -12743999.4 | 55997434.6914 | 480.1% | -100% | -100% | -100% | 480.1%
Capital | GAS TRANSMISSION | GT AUXILIARY EQUIPMENT& INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 172999.92 | 177999.96 | 183000 | 187999.92 | 172999.92 | -172999.92 | -177999.96 | -183000 | -187999.92 | -172999.92 | -100% | -100% | -100% | -100% | -100% | The activities tracked within this category are for projects associated with the installation of equipment to support transmission system operations that are not assigned to any other Budget Code. The scope of work is project-specific and varies significantly from project to project (i.e., installation of telemetric and recording equipment, auxiliary water, electrical, paving, moisture analyzer, pipe supports, methane sensing, etc.) Accordingly, project costs vary significantly from project to project as well. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | All costs in this category in 2024 were determined to be RAMP. | The Auxiliary Equipment & Infrastructure capital request captures the cost of equipment used to support the natural gas transmission system operations that cannot appropriately be assigned to a specific project. This category includes, among other items, RAMP-related costs associated with physical security upgrades to energy infrastructure and equipment to assist SDG&E with real-time monitoring of land movement. Security and auxiliary equipment expenses consist of the planning, installation, construction, and closeout of security cameras, lighting, gates, locks, and equipment upgrades such as pipe supports and analyzers at gas transmission facilities. | SDG&E-06-E RC/SH-34 to RC/SH-36 CWP 004190
Capital | GAS TRANSMISSION | GT AUXILIARY EQUIPMENT& INFRASTRUCTURE | Incident Related to the High Pressure System (Excluding Dig-in) | Security and Auxuliary Equipment | Overall | No | On-going | Annual | 1433954.6576 | 0 | 0 | 0 | 1433954.6576 | 228999.96 | 235999.92 | 243000 | 249999.96 | 228999.96 | 1204954.6976 | -235999.92 | -243000 | -249999.96 | 1204954.6976 | 526.2% | -100% | -100% | -100% | 526.2% | The activities tracked within this category are for projects associated with the installation of equipment to support transmission system operations that are not assigned to any other Budget Code. The scope of work is project-specific and varies significantly from project to project (i.e., installation of telemetric and recording equipment, auxiliary water, electrical, paving, moisture analyzer, pipe supports, methane sensing, etc.) Accordingly, project costs vary significantly from project to project as well. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The variance in the Security and Auxiliary RAMP category was associated with one security gate upgrade project. All 2024 Security and Auxiliary Equipment costs were determined to be RAMP. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | The Auxiliary Equipment & Infrastructure capital request captures the cost of equipment used to support the natural gas transmission system operations that cannot appropriately be assigned to a specific project. This category includes, among other items, RAMP-related costs associated with physical security upgrades to energy infrastructure and equipment to assist SDG&E with real-time monitoring of land movement. Security and auxiliary equipment expenses consist of the planning, installation, construction, and closeout of security cameras, lighting, gates, locks, and equipment upgrades such as pipe supports and analyzers at gas transmission facilities. | SDG&E-06-E RC/SH-34 to RC/SH-36 CWP 004190
Capital | GAS TRANSMISSION | SubTotal GT AUXILIARY EQUIPMENT& INFRASTRUCTURE |  |  |  | Yes |  |  | 1433954.6576 | 0 | 0 | 0 | 1433954.6576 | 401999.88 | 413999.88 | 426000 | 437999.88 | 401999.88 | 1031954.7776 | -413999.88 | -426000 | -437999.88 | 1031954.7776 | 256.7% | -100% | -100% | -100% | 256.7% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS TRANSMISSION | GT CAPITAL TOOLS | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 172149.3651 | 0 | 0 | 0 | 172149.3651 | 147000 | 150999.96 | 156000 | 160999.92 | 147000 | 25149.3651 | -150999.96 | -156000 | -160999.92 | 25149.3651 | 17.11% | -100% | -100% | -100% | 17.11% | The activities tracked within this category are for projects associated with the replacement and purchase of required capital tools. Costs associated with this category vary significantly from item to item and from year to year. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | SubTotal GT CAPITAL TOOLS |  |  |  | Yes |  |  | 172149.3651 | 0 | 0 | 0 | 172149.3651 | 147000 | 150999.96 | 156000 | 160999.92 | 147000 | 25149.3651 | -150999.96 | -156000 | -160999.92 | 25149.3651 | 17.11% | -100% | -100% | -100% | 17.11% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS TRANSMISSION | GT CATHODIC PROTECTION | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection - Capital (HCA & Non-HCA) | Transmission - HCA | No | On-going | Annual | 47775.7133 | 0 | 0 | 0 | 47775.7133 | 783999.96 | 807000 | 831999.96 | 855999.96 | 783999.96 | -736224.2467 | -807000 | -831999.96 | -855999.96 | -736224.2467 | -93.91% | -100% | -100% | -100% | -93.91% | The activities tracked within this category are for projects associated with the installation of cathodic protection equipment used to preserve transmission pipelines, such as surface anodes, rectifiers, and cathodic protection stations. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | GT CATHODIC PROTECTION | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection - Capital (HCA & Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 10487.3517 | 0 | 0 | 0 | 10487.3517 | 171999.96 | 177999.96 | 183000 | 189000 | 171999.96 | -161512.6083 | -177999.96 | -183000 | -189000 | -161512.6083 | -93.9% | -100% | -100% | -100% | -93.9% | The activities tracked within this category are for projects associated with the installation of cathodic protection equipment used to preserve transmission pipelines, such as surface anodes, rectifiers, and cathodic protection stations. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | SubTotal GT CATHODIC PROTECTION |  |  |  | Yes |  |  | 58263.065 | 0 | 0 | 0 | 58263.065 | 955999.92 | 984999.96 | 1014999.96 | 1044999.96 | 955999.92 | -897736.855 | -984999.96 | -1014999.96 | -1044999.96 | -897736.855 | -93.91% | -100% | -100% | -100% | -93.91% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS TRANSMISSION | GT COMPRESSOR STATIONS ADDITIONS/REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Compressor Stations - Capital | Transmission - Facilities | No | On-going | Annual | 4814882.129 | 0 | 0 | 0 | 4814882.129 | 6540999.96 | 6736999.92 | 6939000 | 7146999.96 | 6540999.96 | -1726117.831 | -6736999.92 | -6939000 | -7146999.96 | -1726117.831 | -26.39% | -100% | -100% | -100% | -26.39% | The activities tracked within this category are for projects associated with the replacement of compression station equipment. The scope of work is project-specific and varies significantly from project to project (i.e., automated data gathering systems, replacing outdated technology, emissions monitoring, catalyst, and combustion technologies, etc.) Accordingly, project costs vary significantly from project to project as well. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The variance is due to lower 2024 spending than the historical 5-year average authorized due to on-going modernization work resulting in fewer capital improvements needed. | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This category includes costs associated with the installation and replacement of compressor station equipment used in operating the transmission system. The environmental and regulations associated with the operation of compressor stations requires consistent maintenance and replacement of key engine components and controls equipment to maintain acceptable emissions levels. New air quality regulations require emissions monitoring and reporting equipment along with new catalyst and combustion technology to meet lower emission levels. | SDG&E-06-E RC/SH-28 to RC/SH-29 CWP 004150
Capital | GAS TRANSMISSION | SubTotal GT COMPRESSOR STATIONS ADDITIONS/REPLACEMENTS |  |  |  | Yes |  |  | 4814882.129 | 0 | 0 | 0 | 4814882.129 | 6540999.96 | 6736999.92 | 6939000 | 7146999.96 | 6540999.96 | -1726117.831 | -6736999.92 | -6939000 | -7146999.96 | -1726117.831 | -26.39% | -100% | -100% | -100% | -26.39% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS TRANSMISSION | GT M&R STATIONS ADDITIONS/REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation - Capital (HCA & Non-HCA) | Transmission - HCA | No | On-going | Annual | 2202633.7869 | 0 | 0 | 0 | 2202633.7869 | 1335999.96 | 1374000 | 1416000 | 1458000 | 1335999.96 | 866633.8269 | -1374000 | -1416000 | -1458000 | 866633.8269 | 64.87% | -100% | -100% | -100% | 64.87% | The activities tracked within this category are for projects associated with installing and rebuilding meter set assemblies and pressure limiting stations. The scope of work is project-specific and varies significantly from project to project (e.g., station piping, valves, regulators, control and communications equipment, shelters, enclosure, etc.). Accordingly, project costs vary significantly from project to project as well. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | GT M&R STATIONS ADDITIONS/REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation - Capital (HCA & Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 483504.9776 | 0 | 0 | 0 | 483504.9776 | 294999.96 | 304999.92 | 312999.96 | 322999.92 | 294999.96 | 188505.0176 | -304999.92 | -312999.96 | -322999.92 | 188505.0176 | 63.9% | -100% | -100% | -100% | 63.9% | The activities tracked within this category are for projects associated with installing and rebuilding meter set assemblies and pressure limiting stations. The scope of work is project-specific and varies significantly from project to project (e.g., station piping, valves, regulators, control and communications equipment, shelters, enclosure, etc.). Accordingly, project costs vary significantly from project to project as well. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | SubTotal GT M&R STATIONS ADDITIONS/REPLACEMENTS |  |  |  | Yes |  |  | 2686138.7645 | 0 | 0 | 0 | 2686138.7645 | 1630999.92 | 1678999.92 | 1728999.96 | 1780999.92 | 1630999.92 | 1055138.8445 | -1678999.92 | -1728999.96 | -1780999.92 | 1055138.8445 | 64.69% | -100% | -100% | -100% | 64.69% | [21 empty] | YES | YES |  | The cost variance in this category is due to higher than the 5-year average cost forecasted in the TY 2024 GRC for aging infrastructure, equipment replacement, major maintenance and overhauls that were required to support capacity and reliability across several pipeline pressure limiting stations. | [5 empty] | NO |  | This Budget Code includes costs of installing and rebuilding large meter set assemblies (MSAs) for transmission-served customers and pressure limiting stations residing on the gas transmission system. These assets require replacement for three principal reasons: aging, change in use patterns and/or population encroachment, and enhancement of the transmission system to contend with gas quality and capacity issues. The capital work sustains reliable operation of critical transmission assets to the extent that they are not compromised by equipment deployed past its useful life. This includes periodic replacement of local field measurement and control equipment directly linking with Gas Operations SCADA system via remote communications. | SDG&E-06-E RC/SH-32 to RC/SH-34 CWP 004080
Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Leak Repair (HCA & Non- HCA) | Tranmsission - HCA | No | On-going | Annual | -0.52767 | 0 | 0 | 0 | -0.52767 | 816000 | 840000 | 865999.92 | 891999.96 | 816000 | -816000.5277 | -840000 | -865999.92 | -891999.96 | -816000.5277 | -100% | -100% | -100% | -100% | -100% | The activities tracked within this category are for projects associated with the replacement of pipelines to address identified leaks. The scope of work is project-specific and varies significantly from project to project (i.e., pipe size, location, installation method, etc.). Accordingly, project costs vary significantly from project to project as well. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | YES | No leaks projects were identified in 2024. When projects are identified leaks must be remediated in accordance to General Order 112-F. | Leak repair activities consist of the planning, installation, construction, and closeout of projects initiated due to leaks on transmission pipelines or appurtenances. Classification of leaks is based on relative degree of hazard and must be remediated in accordance with the timelines set out by General Order 112-F. Leak repair activities are necessary to uphold public safety, maintain system reliability, and meet regulatory requirements. No leaks projects were identified in 2024. | SDG&E-06-E RC/SH-25 to RC/SH-28 CWP 004120.001
Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Leak Repair (HCA & Non- HCA) | Transmission - Non-HCA | No | On-going | Annual | -0.03477 | 0 | 0 | 0 | -0.03477 | 178999.92 | 184999.92 | 189999.96 | 195999.96 | 178999.92 | -178999.9548 | -184999.92 | -189999.96 | -195999.96 | -178999.9548 | -100% | -100% | -100% | -100% | -100% | The activities tracked within this category are for projects associated with the replacement of pipelines to address identified leaks. The scope of work is project-specific and varies significantly from project to project (i.e., pipe size, location, installation method, etc.). Accordingly, project costs vary significantly from project to project as well. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | YES | No leaks projects were identified in 2024. When projects are identified leaks must be remediated in accordance to General Order 112-F. | Leak repair activities consist of the planning, installation, construction, and closeout of projects initiated due to leaks on transmission pipelines or appurtenances. Classification of leaks is based on relative degree of hazard and must be remediated in accordance with the timelines set out by General Order 112-F. Leak repair activities are necessary to uphold public safety, maintain system reliability, and meet regulatory requirements. | SDG&E-06-E RC/SH-25 to RC/SH-28 CWP 004120.001
Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline relocation and replacement (HCA & Non-HCA) | Transmission - HCA | No | On-going | Annual | 210080.2593 | 0 | 0 | 0 | 210080.2593 | 405999.96 | 418999.92 | 430999.92 | 444000 | 405999.96 | -195919.7007 | -418999.92 | -430999.92 | -444000 | -195919.7007 | -48.26% | -100% | -100% | -100% | -48.26% | This activity is associated with the replacement of pipelines due to the condition or hazardous conditions affecting the pipeline such as poor coating and changes to the class location of the pipeline. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline relocation and replacement (HCA & Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 43865.4984 | 0 | 0 | 0 | 43865.4984 | 90000 | 91999.92 | 94999.92 | 97999.92 | 90000 | -46134.5016 | -91999.92 | -94999.92 | -97999.92 | -46134.5016 | -51.26% | -100% | -100% | -100% | -51.26% | This activity is associated with the replacement of pipelines due to the condition or hazardous conditions affecting the pipeline such as poor coating and changes to the class location of the pipeline. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Shallow Exposure (HCA & Non-HCA) | Transmission - HCA | No | On-going | Annual | 1892169.0727 | 0 | 0 | 0 | 1892169.0727 | 405999.96 | 418999.92 | 430999.92 | 444000 | 405999.96 | 1486169.1127 | -418999.92 | -430999.92 | -444000 | 1486169.1127 | 366.1% | -100% | -100% | -100% | 366.1% | This activity is associated with the replacement of pipelines due to the condition or hazardous conditions affecting the pipeline such as erosion and exposure of the pipeline. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | Higher than anticipated spending was due to an increase in shallow pipeline mitigation projects. These unanticipated projects were needed to address safety concerns related to exposed pipelines caused by washouts from heavy rains. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Shallow or exposed pipe activities consist of the planning, installation, construction, and closeout of projects to add additional cover or protection to transmission pipelines. Exposed pipelines are inspected for signs of corrosion, metallurgical flaws, construction flaws, and mechanical damage. Concrete revetment mats (technology designed to help prevent shoreline erosion) and/or additional earth coverage are installed to prevent damage to exposed/shallow pipe caused by corrosion, third party damage, erosion, or other external forces. | SDG&E-06-E RC/SH-25 to RC/SH-28 CWP 004120.004
Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Shallow Exposure (HCA & Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 385495.5033 | 0 | 0 | 0 | 385495.5033 | 90000 | 91999.92 | 94999.92 | 97999.92 | 90000 | 295495.5033 | -91999.92 | -94999.92 | -97999.92 | 295495.5033 | 328.3% | -100% | -100% | -100% | 328.3% | This activity is associated with the replacement of pipelines due to the condition or hazardous conditions affecting the pipeline such as erosion and exposure of the pipeline. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
Capital | GAS TRANSMISSION | SubTotal GT PIPELINE REPLACEMENTS |  |  |  | Yes |  |  | 2531609.7712 | 0 | 0 | 0 | 2531609.7712 | 1986999.84 | 2046999.6 | 2107999.56 | 2171999.76 | 1986999.84 | 544609.9312 | -2046999.6 | -2107999.56 | -2171999.76 | 544609.9312 | 27.41% | -100% | -100% | -100% | 27.41% | [21 empty] | YES | NO | [7 empty] | NO
Capital | GAS TRANSMISSION | MORENO COMPRESSOR STATION MODERNIZATION | Incident Related to the High Pressure System (Excluding Dig-in) | Compressor Stations - Capital | Transmission - Facilities | No | 9 | 5 | 55964436.4589 | 0 | 0 | 0 | 55964436.4589 | 0 | 0 | 0 | 0 | 0 | 55964436.4589 | 0 | 0 | 0 | 55964436.4589 | 100% | 0% | 0% | 0% | 100% | The Moreno Compressor Station Modernization (MCM) project consists of a variety of activities including installation of two new electric driven compressors (EDCs), two new compressor gas turbines, two new natural gas‐fueled emergency generators, one new building for CGTs, one new building for EDCs, and associated compression support and emission control equipment. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The primary purpose of the MCM Project is to comply with the sunset of the South Coast AQMD’s Regional Clean Air Incentives Market (RECLAIM) program for NOx requirements. This project is exempt from GO 177 because the associated Permit to Construct application to the AQMD was submitted prior to the effective date of the General Order. In D.24-12-074, the Commission recognized that “the MCM project is important for safety and reliability and for mitigating the risk of impacting future customer costs and non-compliance with SCAQMD regulations for various reasons.”; however, the decision did not authorize costs to be placed into rates and instead ordered SDG&E to file for cost recovery via a Tier II Advice Letter upon completing and placing the project into service. The costs incurred in 2024 are associated with execution of Phase 1 Detailed Engineering and Procurement activities, associated company labor and support services, continued environmental evaluation and applications for biological permits, and Southern California Edison (SCE) Method of Service study; all of which support the modernization of the existing station and associated safety and reliability benefits . | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | The Moreno Compressor Station Modernization (MCM) project consists of a variety of activities including installation of two new electric driven compressors (EDCs), two new compressor gas turbines, two new natural gas‐fueled emergency generators, one new building for CGTs, one new building for EDCs, and associated compression support and emission control equipment. | SDG&E-06-E RC/SH-37 to RC/SH-40 CWP Appendix B
Capital | GAS TRANSMISSION | SubTotal MORENO COMPRESSOR STATION MODERNIZATION |  |  |  | Yes |  |  | 55964436.4589 | 0 | 0 | 0 | 55964436.4589 | 0 | 0 | 0 | 0 | 0 | 55964436.4589 | 0 | 0 | 0 | 55964436.4589 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | YES | [7 empty] | NO

## GOEN-C
SDG&E GAS ENGINEERING Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | GAS ENGINEERING | GAS ENGINEERING |  |  |  | Yes |  |  | 367273.0114 | 0 | 0 | 0 | 367273.0114 | 294000 | 303000 | 312000 | 321000 | 294000 | 73273.0114 | -303000 | -312000 | -321000 | 73273.0114 | 24.92% | -100% | -100% | -100% | 24.92%
Capital | GAS ENGINEERING | Local GT Supervision and Engineering Pool | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 367273.0114 | 0 | 0 | 0 | 367273.0114 | 294000 | 303000 | 312000 | 321000 | 294000 | 73273.0114 | -303000 | -312000 | -321000 | 73273.0114 | 24.92% | -100% | -100% | -100% | 24.92% | Local Gas Transmission Supervision & Engineering Overhead Pool captures expenditures that include labor costs for planning, and engineering of capital gas infrastructure projects. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | GAS ENGINEERING | SubTotal Local GT Supervision and Engineering Pool |  |  |  | Yes |  |  | 367273.0114 | 0 | 0 | 0 | 367273.0114 | 294000 | 303000 | 312000 | 321000 | 294000 | 73273.0114 | -303000 | -312000 | -321000 | 73273.0114 | 24.92% | -100% | -100% | -100% | 24.92% | [21 empty] | YES | NO | [7 empty] | NO

## GOTD-C
SDG&E GAS INTEGRITY MANAGEMENT PROGRAMS Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | GAS INTEGRITY MANAGEMENT PROGRAMS | GAS INTEGRITY MANAGEMENT PROGRAMS |  |  |  | Yes |  |  | 11423376.1176 | 0 | 0 | 0 | 11423376.1176 | 27060999.84 | 27873000 | 28708999.8 | 29570999.88 | 27060999.84 | -15637623.7224 | -27873000 | -28708999.8 | -29570999.88 | -15637623.7224 | -57.79% | -100% | -100% | -100% | -57.79%
Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - HCA | No | 14 | 4 | 9824103.5438 | 0 | 0 | 0 | 9824103.5438 | 24693999.96 | 25434000 | 26197999.92 | 26982999.96 | 24693999.96 | -14869896.4162 | -25434000 | -26197999.92 | -26982999.96 | -14869896.4162 | -60.22% | -100% | -100% | -100% | -60.22% | Miles reconfirmed | 0 |  |  |  | 0 | 1.79 |  |  |  | 1.79 | -1.79 | 0 | 0 | 0 | -1.79 | -100% | 0% | 0% | 0% | -100% | YES | YES | YES | Pursuant to 49 CFR § 192.624, SDG&E is required to reconfirm by July 2035 the maximum allowable operating pressure (MAOP) of transmission lines that either: 1) do not have traceable, verifiable, or complete pressure test records to establish MAOP in accordance with 49 C.F.R § 192.619(a) and are located in high consequence areas (HCAs) or Class 3 or 4 locations, or 2) have an MAOP established in accordance with 49 CFR § 192.619(c), have an MAOP greater than 30% SMYS, and are located in HCAs, Class 3 or 4 locations, or – where the segment can accommodate an in-line inspection (ILI) tool – moderate consequence areas (MCAs). Since MAOP reconfirmation projects can span both HCA and non-HCA segments and these tranches should be viewed in aggregate. The costs incurred in 2024 are attributed to the planning and execution of MAOP reconfirmation projects utilizing the pressure testing and replacement methods of reconfirmation. The variance is primarily due to a reduction in the incremental scope subject to the Gas Transmission Safety Rule (GTSR) Part 1, as a result of SDG&E scope validation and management efforts since the TY 2024 GRC application was filed. SDG&E was able to leverage efficiencies attained through the execution of Pipeline Safety Enhancement Plan (PSEP) projects that contained overlapping scope subject to the requirements of GTSR Part 1. SDG&E balanced its portfolio and incremental MAOP reconfirmation projects were deferred to future years within the GRC cycle. | Pursuant to 49 CFR § 192.624, SDG&E is required to reconfirm by July 2035 the maximum allowable operating pressure (MAOP) of transmission lines that either: 1) do not have traceable, verifiable, or complete pressure test records to establish MAOP in accordance with 49 C.F.R § 192.619(a) and are located in high consequence areas (HCAs) or Class 3 or 4 locations, or 2) have an MAOP established in accordance with 49 CFR § 192.619(c), have an MAOP greater than 30% SMYS, and are located in HCAs, Class 3 or 4 locations, or – where the segment can accommodate an in-line inspection (ILI) tool – moderate consequence areas (MCAs). Since MAOP reconfirmation projects can span both HCA and non-HCA segments and these tranches should be viewed in aggregate. In 2024, progress towards the interim compliance deadline was achieved through the execution of PSEP projects that contained overlapping scope subject to the requirements of GTSR Part 1. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | GTSR capital activities in budget code 214770 include reconfirming the maximum allowable operating pressure (MAOP) in accordance with 49 CFR § 192.624 and PUC § 958 on the DOT-defined transmission pipelines. For these transmission lines, costs include reconfirmation using the following methods: pressure testing and replacement. | SDGE-09-R AK-TS-54 to AK-TS-59 CWP 214770.001
Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - Non-HCA | No | 14 | 4 | 1599272.5738 | 0 | 0 | 0 | 1599272.5738 | 1575000 | 1623000 | 1671000 | 1722000 | 1575000 | 24272.5738 | -1623000 | -1671000 | -1722000 | 24272.5738 | 1.541% | -100% | -100% | -100% | 1.541% | Miles reconfirmed | 0 |  |  |  | 0 | 0.11 |  |  |  | 0.11 | -0.11 | 0 | 0 | 0 | -0.11 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Pursuant to 49 CFR § 192.624, SoCalGas is required to reconfirm by July 2035 the MAOP of transmission lines that either: 1) do not have traceable, verifiable, or complete pressure test records to establish MAOP in accordance with 49 C.F.R § 192.619(a) and are located in HCAs or Class 3 or 4 locations, or 2) have an MAOP established in accordance with 49 CFR § 192.619(c), have an MAOP greater than 30% SMYS, and are located in HCAs, Class 3 or 4 locations, or – where the segment can accommodate an in-line inspection (ILI) tool – MCAs. Since MAOP reconfirmation projects can span both HCA and non-HCA segments and these tranches should be viewed in aggregate. In 2024, progress towards the interim compliance deadline was achieved through the execution of PSEP projects that contained overlapping scope subject to the requirements of GTSR Part 1. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | GTSR capital activities in budget code 214770 include reconfirming the maximum allowable operating pressure (MAOP) in accordance with 49 CFR § 192.624 and PUC § 958 on the DOT-defined transmission pipelines. For these transmission lines, costs include reconfirmation using the following methods: pressure testing and replacement. | SDGE-09-R AK-TS-54 to AK-TS-59 CWP 214770.001
Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Gas Transmission Safety Rule (GTSR) Part 2 | Transmission - HCA & non-HCA | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 331999.92 | 342000 | 351999.96 | 363000 | 331999.92 | -331999.92 | -342000 | -351999.96 | -363000 | -331999.92 | -100% | -100% | -100% | -100% | -100% | Capital activities are driven by O&M activities, for which SDG&E identified units. Additionally, a unit of measure is not feasible for the variety of capital activities that could result from O&M activities to comply with GTSR Part 2. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | YES | The primary driver for GTSR Part 2 costs are corrosion control activities as required by 49 CFR 192.465 and 192.473. In 2024, SDG&E did not encounter conditions requiring GTSR Part 2 compliance activities as previously expected. However, the scope of work remains necessary and SDG&E continues to monitor and manage its pipelines in accordance with GTSR Part 2 requirements and anticipates. | Capital activities in budget code 214770 address the requirements of the GTSR Parts 1 and 2, as well as the Valve Rule. These costs are forecasted for the implementation of the Valve Rule requirements , which include the installation of rupture mitigation valves for new or replacement transmission pipelines of at least 2 contiguous miles based on HCA and class location. Costs are inclusive of materials, communications equipment, and installation. Activities will be driven by compliance with 85 FR 7162. | SDGE-09-R AK-TS-54 to AK-TS-59 CWP 214770.003
Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Valve Rule | Transmission - HCA & non-HCA | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 459999.96 | 474000 | 487999.92 | 502999.92 | 459999.96 | -459999.96 | -474000 | -487999.92 | -502999.92 | -459999.96 | -100% | -100% | -100% | -100% | -100% | Assets installed - valves | 0 |  |  |  | 0 | 0.14 |  |  |  | 0.14 | -0.14 | 0 | 0 | 0 | -0.14 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Valve Rule projects comprise the installation of rupture mitigation valves (RMVs) on transmission pipeline segments as required by the Valve Rule (87 FR 20940). Due to planning and operational considerations, work has been deferred to future years within the GRC cycle. | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | YES | At the time the TY 2024 GRC application was filed, the Valve Rule installations were expected to begin in 2024; however, updated planning and resource prioritization shifted execution into future years. The scope of work remains necessary, and the projects are currently in the early stages of planning and scheduling. Expenditures are expected in future years of this GRC cycle. | Capital activities in budget code 214770 address the requirements of the GTSR Parts 1 and 2, as well as the Valve Rule. These costs are forecasted for the implementation of the Valve Rule requirements , which include the installation of rupture mitigation valves for new or replacement transmission pipelines of at least 2 contiguous miles based on HCA and class location. Costs are inclusive of materials, communications equipment, and installation. Activities will be driven by compliance with 85 FR 7162. | SDGE-09-R AK-TS-54 to AK-TS-59 CWP 214770.005
Capital | GAS INTEGRITY PROGRAMS | SubTotal GAS SAFETY ENHANCEMENT PROGRAMS |  |  |  | Yes |  |  | 11423376.1176 | 0 | 0 | 0 | 11423376.1176 | 27060999.84 | 27873000 | 28708999.8 | 29570999.88 | 27060999.84 | -15637623.7224 | -27873000 | -28708999.8 | -29570999.88 | -15637623.7224 | -57.79% | -100% | -100% | -100% | -57.79% | [21 empty] | YES | YES | [7 empty] | NO

## ESRE-C
SDG&E FACILITIES/OTHER Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | FACILITIES/OTHER | FACILITIES/OTHER |  |  |  | Yes |  |  | 40810787.7779 | 0 | 0 | 0 | 40810787.7779 | 51424999.68 | 52965999.72 | 54555999.6 | 56193999.72 | 51424999.68 | -10614211.9021 | -52965999.72 | -54555999.6 | -56193999.72 | -10614211.9021 | -20.64% | -100% | -100% | -100% | -20.64%
Capital | FACILITIES/OTHER | CHULA VISTA YARD SECURITY IMPROVEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | Canceled | 0 | 0 | 0 | 0 | 0 | 5175999.96 | 5331000 | 5490999.96 | 5655999.96 | 5175999.96 | -5175999.96 | -5331000 | -5490999.96 | -5655999.96 | -5175999.96 | -100% | -100% | -100% | -100% | -100% | Units are not available for these workpapers due to highly diverse project scope and the absence of like units that would be comparable over a multi-year period. Due to the number of significantly different property types such as fencing, motorized gates, surveillance systems, lighting, racking, paving and an office trailer, the deveopment of a meaningful unit of measure was not feasible. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | Project canceled. SDG&E has determined that the location of the Chula Vista Yard was not a logistically practical option due to its location in relation to SDG&E's Construction and Operations centers and hence, has chosen not to proceed with the project. | N/A | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | The project scope will include the design, permitting and construction of a new wrought iron security fence, concrete entry driveway aprons, controlled motorized gate access, surveillance equipment, site lighting, office trailer on concrete pad, and site grading with gravel overlay. | SDG&E-23 DT-39 to DT-40 CWP 00710A
Capital | FACILITIES/OTHER | SubTotal CHULA VISTA YARD SECURITY IMPROVEMENTS |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 5175999.96 | 5331000 | 5490999.96 | 5655999.96 | 5175999.96 | -5175999.96 | -5331000 | -5490999.96 | -5655999.96 | -5175999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | YES | [7 empty] | YES
Capital | FACILITIES/OTHER | CLEAN TRANSPORTATION INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1470544.0735 | 0 | 0 | 0 | 1470544.0735 | 14443999.92 | 14877000 | 15322999.92 | 15783000 | 14443999.92 | -12973455.8465 | -14877000 | -15322999.92 | -15783000 | -12973455.8465 | -89.82% | -100% | -100% | -100% | -89.82% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | FACILITIES/OTHER | SubTotal CLEAN TRANSPORTATION INFRASTRUCTURE |  |  |  | Yes |  |  | 1470544.0735 | 0 | 0 | 0 | 1470544.0735 | 14443999.92 | 14877000 | 15322999.92 | 15783000 | 14443999.92 | -12973455.8465 | -14877000 | -15322999.92 | -15783000 | -12973455.8465 | -89.82% | -100% | -100% | -100% | -89.82% | [21 empty] | NO | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | COMM. PLANT BLKT-BUSINESS UNIT EXPANSION | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 216563.3616 | 0 | 0 | 0 | 216563.3616 | 0 | 0 | 0 | 0 | 0 | 216563.3616 | 0 | 0 | 0 | 216563.3616 | 100% | 0% | 0% | 0% | 100% | Units are not available for these workpapers due to highly diverse project scope and the absence of like units that would be comparable over a multi-year period. The purpose of this blanket project is to fund building and facility expansions and improvements that are necessary to adequately support growing corporate business objectives and initiatives. The projects under this blanket include master planning, expansion, relocation, building construction and facility consolidation projects at various company buildings and facilities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal COMM. PLANT BLKT-BUSINESS UNIT EXPANSION |  |  |  | Yes |  |  | 216563.3616 | 0 | 0 | 0 | 216563.3616 | 0 | 0 | 0 | 0 | 0 | 216563.3616 | 0 | 0 | 0 | 216563.3616 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | COMM. PLANT BLKT-INFRASTRUCTURE & RELIAB | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 7277604.7958 | 0 | 0 | 0 | 7277604.7958 | 6717999.96 | 6919999.92 | 7128000 | 7341999.96 | 6717999.96 | 559604.8358 | -6919999.92 | -7128000 | -7341999.96 | 559604.8358 | 8.33% | -100% | -100% | -100% | 8.33% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. This capital blanket project funds the purchase and installation of items such as chillers, boilers, air handlers, heating, ventilation and air conditioning (HVAC) replacements, generators, UPS (Uninterruptible Power Supply) and building management system (BMS) systems, electrical distribution systems and computer room infrastructure. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal COMM. PLANT BLKT-INFRASTRUCTURE & RELIAB |  |  |  | Yes |  |  | 7277604.7958 | 0 | 0 | 0 | 7277604.7958 | 6717999.96 | 6919999.92 | 7128000 | 7341999.96 | 6717999.96 | 559604.8358 | -6919999.92 | -7128000 | -7341999.96 | 559604.8358 | 8.33% | -100% | -100% | -100% | 8.33% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | COMM. PLANT BLKT-REMODEL/RELOC/RECONFIG | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 15837540.0757 | 0 | 0 | 0 | 15837540.0757 | 2946000 | 3033999.96 | 3124999.92 | 3219000 | 2946000 | 12891540.0757 | -3033999.96 | -3124999.92 | -3219000 | 12891540.0757 | 437.6% | -100% | -100% | -100% | 437.6% | Units are not available for these workpapers due to highly diverse project scope and the absence of like units that would be comparable over a multi-year period. The remodel, reconfigure, and relocation blanket budget funds tenant improvement construction, spatial remodels and associated workstation moves, and changes needed to provide adequate and efficient office space and work environments for employees. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The overrun was driven by the completion of the CP4 tenant improvement project which was previously approved in the 2019 GRC (SDG&E-22-CWP - DTattersall, CP4 Refresh CWP 00709A.003, pg. 52). | N/A | Over (O) | On Target (T) | Over (O) | Expanded | NO | N/A | This budget funds tenant improvement construction, spatial remodels and associated work station moves and changes needed to provide adequate and efficient office space and work environments for employees . Requirements are based on business needs and functionality needed to meet business and resource objectives. Space standards and guidelines are used to manage space allocations and modifications effectively in reconfigurations . Ergonomics are considered in the upgrades to provide improved working conditions for employees. | SDG&E-23 DT-38 to DT-39 CWP 00709
Capital | FACILITIES/OTHER | SubTotal COMM. PLANT BLKT-REMODEL/RELOC/RECONFIG |  |  |  | Yes |  |  | 15837540.0757 | 0 | 0 | 0 | 15837540.0757 | 2946000 | 3033999.96 | 3124999.92 | 3219000 | 2946000 | 12891540.0757 | -3033999.96 | -3124999.92 | -3219000 | 12891540.0757 | 437.6% | -100% | -100% | -100% | 437.6% | [21 empty] | YES | YES | [7 empty] | NO
Capital | FACILITIES/OTHER | SECURITY SYSTEMS BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 414756.4275 | 0 | 0 | 0 | 414756.4275 | 3204999.96 | 3300999.96 | 3399999.96 | 3501999.96 | 3204999.96 | -2790243.5325 | -3300999.96 | -3399999.96 | -3501999.96 | -2790243.5325 | -87.06% | -100% | -100% | -100% | -87.06% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. This capital blanket funds projects that address the security of the company employees, operations, and assets. Common project types covered in this budget code are card readers, cameras, video recorders, physical barriers, and controlled automated gates and turnstiles. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal SECURITY SYSTEMS BLANKET |  |  |  | Yes |  |  | 414756.4275 | 0 | 0 | 0 | 414756.4275 | 3204999.96 | 3300999.96 | 3399999.96 | 3501999.96 | 3204999.96 | -2790243.5325 | -3300999.96 | -3399999.96 | -3501999.96 | -2790243.5325 | -87.06% | -100% | -100% | -100% | -87.06% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | STRUCTURES & IMPROVEMENTS BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2492518.7765 | 0 | 0 | 0 | 2492518.7765 | 6312000 | 6501000 | 6696000 | 6897000 | 6312000 | -3819481.2235 | -6501000 | -6696000 | -6897000 | -3819481.2235 | -60.51% | -100% | -100% | -100% | -60.51% | Units are not available for these workpapers due to highly diverse project scope and the absence of like units that would be comparable over a multi-year period. This capital blanket funds building shell modifications, site improvements and other facility upgrades of a structural, civil or weatherproofing nature. These projects vary year to year based on need, but address the capital replacement or addition of basic, individual interior and exterior facilities construction components, including site lighting, fencing, gates, paving, roofing, canopies, training areas, windows and storage racking or sheds. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal STRUCTURES & IMPROVEMENTS BLANKET |  |  |  | Yes |  |  | 2492518.7765 | 0 | 0 | 0 | 2492518.7765 | 6312000 | 6501000 | 6696000 | 6897000 | 6312000 | -3819481.2235 | -6501000 | -6696000 | -6897000 | -3819481.2235 | -60.51% | -100% | -100% | -100% | -60.51% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | KEARNY MASTER PLAN PHASE 2 | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 3 | 10380840.0016 | 0 | 0 | 0 | 10380840.0016 | 0 | 0 | 0 | 0 | 0 | 10380840.0016 | 0 | 0 | 0 | 10380840.0016 | 100% | 0% | 0% | 0% | 100% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. The unique scope of this project includes grading, the removal of contaminated soils, installation of fencing, security systems and the construction of vehicle canopies. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The Kearny Master Plan was denied without prejudice in the GRC Decision (D.24-12-074, pg 631) with the guidance of filing a Tier 3 Advice Letter or seeking recovery for the projects in the next GRC cycle. SDG&E has since completed Phase 1 of the Kearny Master Plan and will include the project in the TY 2028 GRC cycle. | N/A | On Target (T) | Under (U) | Over (O) | Proceeding as Planned | NO | N/A | SDG&E's relocation and expansion of its existing substation on its Kearny Construction & Operations property, coupled with the decommissioning of an onsite peaker plant, creates an opportunity to optimize existing operations on the site, accommodate future growth, consolidate employees from other locations and improve traffic circulation . | SDG&E-23 DT-39 to DT-40 CWP 00710 B&C
Capital | FACILITIES/OTHER | SubTotal KEARNY MASTER PLAN PHASE 2 |  |  |  | Yes |  |  | 10380840.0016 | 0 | 0 | 0 | 10380840.0016 | 0 | 0 | 0 | 0 | 0 | 10380840.0016 | 0 | 0 | 0 | 10380840.0016 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | YES | [7 empty] | NO
Capital | FACILITIES/OTHER | FURNITURE & OFFICE EQUIPMENT BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 231660.7011 | 0 | 0 | 0 | 231660.7011 | 0 | 0 | 0 | 0 | 0 | 231660.7011 | 0 | 0 | 0 | 231660.7011 | 100% | 0% | 0% | 0% | 100% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. This blanket budget funds the purchase of miscellaneous furniture and other office equipment greater than $5,000. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A
Capital | FACILITIES/OTHER | SubTotal FURNITURE & OFFICE EQUIPMENT BLANKET |  |  |  | Yes |  |  | 231660.7011 | 0 | 0 | 0 | 231660.7011 | 0 | 0 | 0 | 0 | 0 | 231660.7011 | 0 | 0 | 0 | 231660.7011 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | LAND BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 87000 | 90000 | 93000 | 96000 | 87000 | -87000 | -90000 | -93000 | -96000 | -87000 | -100% | -100% | -100% | -100% | -100% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. This capital blanket includes funding for the installation of new landscaping or renovation of existing landscape and irrigation systems and other improvements on existing Company property and various Company property works (i.e., Substations, transmission line right-of-way) including but not limited to fencing, masonry screening or retaining walls, access gates, signs, grading, paving, drainage improvements, landscaping and landscape irrigation. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | The Land blanket supports both CPUC and FERC related projects with the project mix varying year-over-year. In 2024, all projects implemented by the Land blanket were related to transmission substations (FERC). There were no CPUC related projects implemented in 2024.
Capital | FACILITIES/OTHER | SubTotal LAND BLANKET |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 87000 | 90000 | 93000 | 96000 | 87000 | -87000 | -90000 | -93000 | -96000 | -87000 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | FACILITIES/OTHER | LAND SERVICES ARCHIBUS SYSTEM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 840049.4416 | 0 | 0 | 0 | 840049.4416 | 1771999.92 | 1824999.96 | 1879999.92 | 1935999.96 | 1771999.92 | -931950.4784 | -1824999.96 | -1879999.92 | -1935999.96 | -931950.4784 | -52.59% | -100% | -100% | -100% | -52.59% | Units are not available for this workpaper due to highly diverse nature of the system development that takes place over a multi-year period. Archibus is an integrated work management system used by Real Estate & Facilities employees to capture support requests and manage preventative maintenance for real estate assets and facilities. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal LAND SERVICES ARCHIBUS SYSTEM |  |  |  | Yes |  |  | 840049.4416 | 0 | 0 | 0 | 840049.4416 | 1771999.92 | 1824999.96 | 1879999.92 | 1935999.96 | 1771999.92 | -931950.4784 | -1824999.96 | -1879999.92 | -1935999.96 | -931950.4784 | -52.59% | -100% | -100% | -100% | -52.59% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | MISC EQUIPMENT BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 918536.6958 | 0 | 0 | 0 | 918536.6958 | 2007999.96 | 2067999.96 | 2130000 | 2193999.96 | 2007999.96 | -1089463.2642 | -2067999.96 | -2130000 | -2193999.96 | -1089463.2642 | -54.26% | -100% | -100% | -100% | -54.26% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. This capital blanket funds the purchase and installation of miscellaneous equipment that does not fall under the scope of any other capital project. Types of equipment included in this budget code are replacements of small equipment such as kitchen, audio-visual, specialized mechanical equipment used in the fleet garages. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal MISC EQUIPMENT BLANKET |  |  |  | Yes |  |  | 918536.6958 | 0 | 0 | 0 | 918536.6958 | 2007999.96 | 2067999.96 | 2130000 | 2193999.96 | 2007999.96 | -1089463.2642 | -2067999.96 | -2130000 | -2193999.96 | -1089463.2642 | -54.26% | -100% | -100% | -100% | -54.26% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | SDG&E SITE SECURITY UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | -6849.16 | 0 | 0 | 0 | -6849.16 | 0 | 0 | 0 | 0 | 0 | -6849.16 | 0 | 0 | 0 | -6849.16 | 100% | 0% | 0% | 0% | 100% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. The security scope at various company locations differs to such an extent the assignment of a comparible unit of measure is not feasible. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal SDG&E SITE SECURITY UPGRADES |  |  |  | Yes |  |  | -6849.16 | 0 | 0 | 0 | -6849.16 | 0 | 0 | 0 | 0 | 0 | -6849.16 | 0 | 0 | 0 | -6849.16 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | SAFETY/ENVIRONMENTAL | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 618076.0583 | 0 | 0 | 0 | 618076.0583 | 2313000 | 2382000 | 2452999.92 | 2526999.96 | 2313000 | -1694923.9417 | -2382000 | -2452999.92 | -2526999.96 | -1694923.9417 | -73.28% | -100% | -100% | -100% | -73.28% | Units are not available for this workpaper due to highly diverse project scope and the absence of like units that would be comparable year over year. This capital blanket funds the installation of concrete pads, hazardous waste storage and other requirements to mitigate environmental risks. Safety projects vary in nature but can include communication systems, fall protection, on-campus traffic improvements, canopies, or any other improvements to reduce employee risk. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | FACILITIES/OTHER | SubTotal SAFETY/ENVIRONMENTAL |  |  |  | Yes |  |  | 618076.0583 | 0 | 0 | 0 | 618076.0583 | 2313000 | 2382000 | 2452999.92 | 2526999.96 | 2313000 | -1694923.9417 | -2382000 | -2452999.92 | -2526999.96 | -1694923.9417 | -73.28% | -100% | -100% | -100% | -73.28% | [21 empty] | YES | NO | [7 empty] | NO
Capital | FACILITIES/OTHER | SDG&E SUSTAINABILITY PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 118946.5289 | 0 | 0 | 0 | 118946.5289 | 6444000 | 6636999.96 | 6837000 | 7041999.96 | 6444000 | -6325053.4711 | -6636999.96 | -6837000 | -7041999.96 | -6325053.4711 | -98.15% | -100% | -100% | -100% | -98.15% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
Capital | FACILITIES/OTHER | SubTotal SDG&E SUSTAINABILITY PROGRAM |  |  |  | Yes |  |  | 118946.5289 | 0 | 0 | 0 | 118946.5289 | 6444000 | 6636999.96 | 6837000 | 7041999.96 | 6444000 | -6325053.4711 | -6636999.96 | -6837000 | -7041999.96 | -6325053.4711 | -98.15% | -100% | -100% | -100% | -98.15% | [21 empty] | NO | NO | [7 empty] | YES

## ITCS-C
SDG&E CYBERSECURITY Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | CYBERSECURITY | CYBERSECURITY |  |  |  | Yes |  |  | 4013006.0544 | 0 | 0 | 0 | 4013006.0544 | 11408999.64 | 11752999.68 | 12105999.72 | 12470999.88 | 11408999.64 | -7395993.5856 | -11752999.68 | -12105999.72 | -12470999.88 | -7395993.5856 | -64.83% | -100% | -100% | -100% | -64.83%
Capital | CYBERSECURITY | RAMP - CYBER - SDGE - INTERNAL DEFENSES | Cybersecurity | Internal Defenses | Overall | No | On-going | Annual | 115922.8202 | 0 | 0 | 0 | 115922.8202 | 1357999.92 | 1398999.96 | 1440999.96 | 1485000 | 1357999.92 | -1242077.0998 | -1398999.96 | -1440999.96 | -1485000 | -1242077.0998 | -91.46% | -100% | -100% | -100% | -91.46% | Users protected | 25000 |  |  |  | 25000 | 25000 |  |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | CYBERSECURITY | SubTotal RAMP - CYBER - SDGE - INTERNAL DEFENSES |  |  |  | Yes |  |  | 115922.8202 | 0 | 0 | 0 | 115922.8202 | 1357999.92 | 1398999.96 | 1440999.96 | 1485000 | 1357999.92 | -1242077.0998 | -1398999.96 | -1440999.96 | -1485000 | -1242077.0998 | -91.46% | -100% | -100% | -100% | -91.46% | [21 empty] | YES | NO | [7 empty] | NO
Capital | CYBERSECURITY | RAMP - CYBER - SDGE - OBSOLETE IT INFRASTRUCTURE AND APPLICATION REPLACEMENT | Cybersecurity | Obsolete Information Technology (IT) Infrastructure and Application Replacement | Overall | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 1357999.92 | 1398999.96 | 1440999.96 | 1485000 | 1357999.92 | -1357999.92 | -1398999.96 | -1440999.96 | -1485000 | -1357999.92 | -100% | -100% | -100% | -100% | -100% | Users protected | 0 |  |  |  | 0 | 25000 |  |  |  | 25000 | -25000 | 0 | 0 | 0 | -25000 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | A priority of the cybersecurity organization in 2024 was replacing and reconfiguring firewalls and related technology assets. There were no obsolete projects identified during 2024. SDG&E intends to manage this program over the entire GRC cycle. | Under (U) | Under (U) | Under (U) | Proceeding as Planned | YES | There were no obsolete projects identified during 2024. | The types of Obsolete IT Infrastructure and Application Replacement activities include technology refreshes and /or replacements of obsolete infrastructure, operating systems, middleware and applications. Additionally, there is the need to provide ongoing system maintenance activity to confirm continued secure configurations, patching, and upgrading, among others. Lastly, the need to utilize effective architecture and other mechanisms to confirm high availability and service continuity for critical systems | SDG&E-26-R LRM-19 to LRM-27 CWP 00906J
Capital | CYBERSECURITY | SubTotal RAMP - CYBER - SDGE - OBSOLETE IT INFRASTRUCTURE AND APPLICATION REPLACEMENT |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 1357999.92 | 1398999.96 | 1440999.96 | 1485000 | 1357999.92 | -1357999.92 | -1398999.96 | -1440999.96 | -1485000 | -1357999.92 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | CYBERSECURITY | RAMP - CYBER - SDGE - OPERATIONAL TECHNOLOGY (OT) CYBERSECURITY | Cybersecurity | Operational Technology (OT) Cybersecurity | Overall | No | On-going | Annual | 3897083.2342 | 0 | 0 | 0 | 3897083.2342 | 4075999.92 | 4198999.92 | 4324999.92 | 4455000 | 4075999.92 | -178916.6858 | -4198999.92 | -4324999.92 | -4455000 | -178916.6858 | -4.39% | -100% | -100% | -100% | -4.39% | Users protected | 25000 |  |  |  | 25000 | 25000 |  |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | CYBERSECURITY | SubTotal RAMP - CYBER - SDGE - OPERATIONAL TECHNOLOGY (OT) CYBERSECURITY |  |  |  | Yes |  |  | 3897083.2342 | 0 | 0 | 0 | 3897083.2342 | 4075999.92 | 4198999.92 | 4324999.92 | 4455000 | 4075999.92 | -178916.6858 | -4198999.92 | -4324999.92 | -4455000 | -178916.6858 | -4.39% | -100% | -100% | -100% | -4.39% | [21 empty] | YES | NO | [7 empty] | NO
Capital | CYBERSECURITY | RAMP - CYBER - SDGE - PERIMETER DEFENSES | Cybersecurity | Perimeter Defenses | Overall | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 2715999.96 | 2797999.92 | 2881999.92 | 2968999.92 | 2715999.96 | -2715999.96 | -2797999.92 | -2881999.92 | -2968999.92 | -2715999.96 | -100% | -100% | -100% | -100% | -100% | Users protected | 0 |  |  |  | 0 | 25000 |  |  |  | 25000 | -25000 | 0 | 0 | 0 | -25000 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The expenditures incurred for enhancements to perimeter defenses in 2024 were covered by the North American Electric Reliability Corporation Critical Infrastructure Protection plan (NERC-CIP), and therefore fell outside of the scope of the CPUC GRC funded perimeter defenses category. SDG&E intends to manage this program over the entire GRC cycle. | Under (U) | Under (U) | Under (U) | Proceeding as Planned | YES | The expenditures incurred for enhancements to perimeter defenses in 2024 were covered by the North American Electric Reliability Corporation Critical Infrastructure Protection plan (NERC-CIP), and therefore fell outside of the scope of the CPUC GRC funded perimeter defenses category. | The types of perimeter defense activities include efforts such as firewall upgrades and process automation, web application firewall protections, distributed denial of service (DDoS) protection and the implementation of other perimeter defensive and threat mitigation mechanisms. | SDG&E-26-R LRM-19 to LRM-27 CWP 00906G
Capital | CYBERSECURITY | SubTotal RAMP - CYBER - SDGE - PERIMETER DEFENSES |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 2715999.96 | 2797999.92 | 2881999.92 | 2968999.92 | 2715999.96 | -2715999.96 | -2797999.92 | -2881999.92 | -2968999.92 | -2715999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | CYBERSECURITY | RAMP - CYBER - SDGE - SENSITIVE DATA PROTECTION | Cybersecurity | Sensitive Data Protection | Overall | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 1900999.92 | 1957999.92 | 2016999.96 | 2076999.96 | 1900999.92 | -1900999.92 | -1957999.92 | -2016999.96 | -2076999.96 | -1900999.92 | -100% | -100% | -100% | -100% | -100% | Users protected | 0 |  |  |  | 0 | 25000 |  |  |  | 25000 | -25000 | 0 | 0 | 0 | -25000 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | No SDG&E only investments were required in 2024 for Sensitive Data Protection. SDG&E intends to manage this program over the entire GRC cycle. | Under (U) | Under (U) | Under (U) | Proceeding as Planned | YES | No SDG&E only investments were required in 2024 for Sensitive Data Protection. | The types of sensitive data activities include efforts such as identity access management (IAM) enhancements, data loss prevention (DLP), data crawler technology to identify sensitive data in the environment and mobile device security. | SDG&E-26-R LRM-19 to LRM-27 CWP 00906K
Capital | CYBERSECURITY | SubTotal RAMP - CYBER - SDGE - SENSITIVE DATA PROTECTION |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 1900999.92 | 1957999.92 | 2016999.96 | 2076999.96 | 1900999.92 | -1900999.92 | -1957999.92 | -2016999.96 | -2076999.96 | -1900999.92 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES

## ITIT-C
SDG&E INFORMATION TECHNOLOGY Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | INFORMATION TECHNOLOGY | INFORMATION TECHNOLOGY |  |  |  | Yes |  |  | 167288329.4841 | 0 | 0 | 0 | 167288329.4841 | 175708998.36 | 180977998.08 | 186411998.28 | 192005998.44 | 175708998.36 | -8420668.8759 | -180977998.08 | -186411998.28 | -192005998.44 | -8420668.8759 | -4.792% | -100% | -100% | -100% | -4.792%
Capital | INFORMATION TECHNOLOGY | APP MODERNIZATION & VULNERABILITY REDUCTION - PHASE 2 | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 4 | -16586 | 0 | 0 | 0 | -16586 | 4725000 | 4866999.96 | 5013000 | 5163000 | 4725000 | -4741586 | -4866999.96 | -5013000 | -5163000 | -4741586 | -100.4% | -100% | -100% | -100% | -100.4% | Applications | 23 |  |  |  | 23 | 25 |  |  |  | 25 | -2 | 0 | 0 | 0 | -2 | -8% | 0% | 0% | 0% | -8% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | YES | Project completed in 2023
Capital | INFORMATION TECHNOLOGY | SubTotal APP MODERNIZATION & VULNERABILITY REDUCTION - PHASE 2 |  |  |  | Yes |  |  | -16586 | 0 | 0 | 0 | -16586 | 4725000 | 4866999.96 | 5013000 | 5163000 | 4725000 | -4741586 | -4866999.96 | -5013000 | -5163000 | -4741586 | -100.4% | -100% | -100% | -100% | -100.4% | [21 empty] | YES | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | BUSINESS ADAPTATION TECHNOLOGIES & DIGITALIZATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1588960.6456 | 0 | 0 | 0 | 1588960.6456 | 1405999.92 | 1447999.92 | 1491000 | 1536000 | 1405999.92 | 182960.7256 | -1447999.92 | -1491000 | -1536000 | 182960.7256 | 13.01% | -100% | -100% | -100% | 13.01% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal BUSINESS ADAPTATION TECHNOLOGIES & DIGITALIZATION |  |  |  | Yes |  |  | 1588960.6456 | 0 | 0 | 0 | 1588960.6456 | 1405999.92 | 1447999.92 | 1491000 | 1536000 | 1405999.92 | 182960.7256 | -1447999.92 | -1491000 | -1536000 | 182960.7256 | 13.01% | -100% | -100% | -100% | 13.01% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | CAISO MANDATES 2023 | Non-RAMP | Non-RAMP | Non-RAMP | No | 1 | 2 | 1993000.2445 | 0 | 0 | 0 | 1993000.2445 | 444999.96 | 457999.92 | 471999.96 | 486000 | 444999.96 | 1548000.2845 | -457999.92 | -471999.96 | -486000 | 1548000.2845 | 347.9% | -100% | -100% | -100% | 347.9% | Applications | 4 |  |  |  | 4 | 4 |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal CAISO MANDATES 2023 |  |  |  | Yes |  |  | 1993000.2445 | 0 | 0 | 0 | 1993000.2445 | 444999.96 | 457999.92 | 471999.96 | 486000 | 444999.96 | 1548000.2845 | -457999.92 | -471999.96 | -486000 | 1548000.2845 | 347.9% | -100% | -100% | -100% | 347.9% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | CAISO MANDATES 2024 | Non-RAMP | Non-RAMP | Non-RAMP | No | 1 | 1 | 332524.417 | 0 | 0 | 0 | 332524.417 | 1825999.92 | 1879999.92 | 1935999.96 | 1993999.92 | 1825999.92 | -1493475.503 | -1879999.92 | -1935999.96 | -1993999.92 | -1493475.503 | -81.79% | -100% | -100% | -100% | -81.79% | Applications | 4 |  |  |  | 4 | 4 |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal CAISO MANDATES 2024 |  |  |  | Yes |  |  | 332524.417 | 0 | 0 | 0 | 332524.417 | 1825999.92 | 1879999.92 | 1935999.96 | 1993999.92 | 1825999.92 | -1493475.503 | -1879999.92 | -1935999.96 | -1993999.92 | -1493475.503 | -81.79% | -100% | -100% | -100% | -81.79% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | CIS REGULATORY & ENHANCEMENTS 2024 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 24428788.4651 | 0 | 0 | 0 | 24428788.4651 | 28077000 | 28918999.92 | 29787000 | 30681000 | 28077000 | -3648211.5349 | -28918999.92 | -29787000 | -30681000 | -3648211.5349 | -12.99% | -100% | -100% | -100% | -12.99% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal CIS REGULATORY & ENHANCEMENTS 2024 |  |  |  | Yes |  |  | 24428788.4651 | 0 | 0 | 0 | 24428788.4651 | 28077000 | 28918999.92 | 29787000 | 30681000 | 28077000 | -3648211.5349 | -28918999.92 | -29787000 | -30681000 | -3648211.5349 | -12.99% | -100% | -100% | -100% | -12.99% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | CLEAN TRANSPORTATION PRODUCT TEAM 2023-2024 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1731874.0965 | 0 | 0 | 0 | 1731874.0965 | 2020999.92 | 2082000 | 2143999.92 | 2208999.96 | 2020999.92 | -289125.8235 | -2082000 | -2143999.92 | -2208999.96 | -289125.8235 | -14.31% | -100% | -100% | -100% | -14.31% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal CLEAN TRANSPORTATION PRODUCT TEAM 2023-2024 |  |  |  | Yes |  |  | 1731874.0965 | 0 | 0 | 0 | 1731874.0965 | 2020999.92 | 2082000 | 2143999.92 | 2208999.96 | 2020999.92 | -289125.8235 | -2082000 | -2143999.92 | -2208999.96 | -289125.8235 | -14.31% | -100% | -100% | -100% | -14.31% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | CLOUD DATA LAKE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 0 | 0 | 0 | 0 | 0 | 2952999.96 | 3042000 | 3132999.96 | 3226999.92 | 2952999.96 | -2952999.96 | -3042000 | -3132999.96 | -3226999.92 | -2952999.96 | -100% | -100% | -100% | -100% | -100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
Capital | INFORMATION TECHNOLOGY | SubTotal CLOUD DATA LAKE |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 2952999.96 | 3042000 | 3132999.96 | 3226999.92 | 2952999.96 | -2952999.96 | -3042000 | -3132999.96 | -3226999.92 | -2952999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | NO | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | CONSTRUCTION, PLANNING AND DESIGN (CPD) ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No | 2 | 2 | 1626278.53 | 0 | 0 | 0 | 1626278.53 | 2328000 | 2397999.96 | 2469999.96 | 2544000 | 2328000 | -701721.47 | -2397999.96 | -2469999.96 | -2544000 | -701721.47 | -30.14% | -100% | -100% | -100% | -30.14% | Applications | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal CONSTRUCTION, PLANNING AND DESIGN (CPD) ENHANCEMENTS |  |  |  | Yes |  |  | 1626278.53 | 0 | 0 | 0 | 1626278.53 | 2328000 | 2397999.96 | 2469999.96 | 2544000 | 2328000 | -701721.47 | -2397999.96 | -2469999.96 | -2544000 | -701721.47 | -30.14% | -100% | -100% | -100% | -30.14% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | CONTACT CENTER OF THE FUTURE (CCOTF) | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 9240199.175 | 0 | 0 | 0 | 9240199.175 | 11563999.92 | 11910999.96 | 12268999.92 | 12636999.96 | 11563999.92 | -2323800.745 | -11910999.96 | -12268999.92 | -12636999.96 | -2323800.745 | -20.1% | -100% | -100% | -100% | -20.1% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal CONTACT CENTER OF THE FUTURE (CCOTF) |  |  |  | Yes |  |  | 9240199.175 | 0 | 0 | 0 | 9240199.175 | 11563999.92 | 11910999.96 | 12268999.92 | 12636999.96 | 11563999.92 | -2323800.745 | -11910999.96 | -12268999.92 | -12636999.96 | -2323800.745 | -20.1% | -100% | -100% | -100% | -20.1% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | CROSS-FUNCTIONAL WORK MANAGEMENT ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 0 | 0 | 0 | 0 | 0 | 261999.96 | 270000 | 277999.92 | 285999.96 | 261999.96 | -261999.96 | -270000 | -277999.92 | -285999.96 | -261999.96 | -100% | -100% | -100% | -100% | -100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
Capital | INFORMATION TECHNOLOGY | SubTotal CROSS-FUNCTIONAL WORK MANAGEMENT ENHANCEMENTS |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 261999.96 | 270000 | 277999.92 | 285999.96 | 261999.96 | -261999.96 | -270000 | -277999.92 | -285999.96 | -261999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | NO | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | IT NON-RAMP APPLICATIONS-SRM | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 3300474.0042 | 0 | 0 | 0 | 3300474.0042 | 0 | 0 | 0 | 0 | 0 | 3300474.0042 | 0 | 0 | 0 | 3300474.0042 | 100% | 0% | 0% | 0% | 100% | This workpaper for the Application portfolio contains various projects within the following categories: (1) Geospatial Field Improvements; (2) Emerging Tech - Virtual Reality Expansion; (3) Builder Customer portal modernization. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal IT NON-RAMP APPLICATIONS-SRM |  |  |  | Yes |  |  | 3300474.0042 | 0 | 0 | 0 | 3300474.0042 | 0 | 0 | 0 | 0 | 0 | 3300474.0042 | 0 | 0 | 0 | 3300474.0042 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | DATA GOVERNANCE TOOLS & FRAMEWORK | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 4987428.5982 | 0 | 0 | 0 | 4987428.5982 | 2658000 | 2737999.92 | 2820000 | 2904999.96 | 2658000 | 2329428.5982 | -2737999.92 | -2820000 | -2904999.96 | 2329428.5982 | 87.64% | -100% | -100% | -100% | 87.64% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal DATA GOVERNANCE TOOLS & FRAMEWORK |  |  |  | Yes |  |  | 4987428.5982 | 0 | 0 | 0 | 4987428.5982 | 2658000 | 2737999.92 | 2820000 | 2904999.96 | 2658000 | 2329428.5982 | -2737999.92 | -2820000 | -2904999.96 | 2329428.5982 | 87.64% | -100% | -100% | -100% | 87.64% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | DIGITAL SERVICE INTEGRATION PLATFORM | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 3303209.5243 | 0 | 0 | 0 | 3303209.5243 | 1830999.96 | 1885999.92 | 1942999.92 | 2001000 | 1830999.96 | 1472209.5643 | -1885999.92 | -1942999.92 | -2001000 | 1472209.5643 | 80.4% | -100% | -100% | -100% | 80.4% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal DIGITAL SERVICE INTEGRATION PLATFORM |  |  |  | Yes |  |  | 3303209.5243 | 0 | 0 | 0 | 3303209.5243 | 1830999.96 | 1885999.92 | 1942999.92 | 2001000 | 1830999.96 | 1472209.5643 | -1885999.92 | -1942999.92 | -2001000 | 1472209.5643 | 80.4% | -100% | -100% | -100% | 80.4% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | DISTRIBUTION INTERCONNECTION INFO. SYSTEM - RULE 21 AND NET ENERGY METERING ENHANCEMENTS - PHASE 2 | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 3 | 1493677.2188 | 0 | 0 | 0 | 1493677.2188 | 1765999.92 | 1818999.96 | 1873999.92 | 1929999.96 | 1765999.92 | -272322.7012 | -1818999.96 | -1873999.92 | -1929999.96 | -272322.7012 | -15.42% | -100% | -100% | -100% | -15.42% | Applications | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal DISTRIBUTION INTERCONNECTION INFO. SYSTEM - RULE 21 AND NET ENERGY METERING ENHANCEMENTS - PHASE 2 |  |  |  | Yes |  |  | 1493677.2188 | 0 | 0 | 0 | 1493677.2188 | 1765999.92 | 1818999.96 | 1873999.92 | 1929999.96 | 1765999.92 | -272322.7012 | -1818999.96 | -1873999.92 | -1929999.96 | -272322.7012 | -15.42% | -100% | -100% | -100% | -15.42% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | ELECTRIC GRID OPS SMALL CAPITAL 2024 | Non-RAMP | Non-RAMP | Non-RAMP | No | 1 | 1 | 211408.7648 | 0 | 0 | 0 | 211408.7648 | 519000 | 534999.96 | 550999.92 | 567000 | 519000 | -307591.2353 | -534999.96 | -550999.92 | -567000 | -307591.2353 | -59.27% | -100% | -100% | -100% | -59.27% | Hardware | 2 |  |  |  | 2 | 2 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal ELECTRIC GRID OPS SMALL CAPITAL 2024 |  |  |  | Yes |  |  | 211408.7648 | 0 | 0 | 0 | 211408.7648 | 519000 | 534999.96 | 550999.92 | 567000 | 519000 | -307591.2353 | -534999.96 | -550999.92 | -567000 | -307591.2353 | -59.27% | -100% | -100% | -100% | -59.27% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | ENGINEERING & CONSTRUCTION DOCUMENT CENTRALIZATION AND COMPLIANCE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | -13413.272 | 0 | 0 | 0 | -13413.272 | 762000 | 784999.92 | 808999.92 | 832999.92 | 762000 | -775413.272 | -784999.92 | -808999.92 | -832999.92 | -775413.272 | -101.8% | -100% | -100% | -100% | -101.8% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | YES
Capital | INFORMATION TECHNOLOGY | SubTotal ENGINEERING & CONSTRUCTION DOCUMENT CENTRALIZATION AND COMPLIANCE |  |  |  | Yes |  |  | -13413.272 | 0 | 0 | 0 | -13413.272 | 762000 | 784999.92 | 808999.92 | 832999.92 | 762000 | -775413.272 | -784999.92 | -808999.92 | -832999.92 | -775413.272 | -101.8% | -100% | -100% | -100% | -101.8% | [21 empty] | NO | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | ENTERPRISE DISTRIBUTED ENERGY RESOURCE MANAGEMENT SYSTEM (DERMS) | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3933999.96 | 4051999.92 | 4173999.96 | 4299000 | 3933999.96 | -3933999.96 | -4051999.92 | -4173999.96 | -4299000 | -3933999.96 | -100% | -100% | -100% | -100% | -100% | Applications | 0 |  |  |  | 0 | 3 |  |  |  | 3 | -3 | 0 | 0 | 0 | -3 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The enterprise Distributed Energy Resource Management System (DERMS) project has been delayed due to extensive research of commercially available market solutions to meet functional requirements. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | The enterprise Distributed Energy Resource Management System (DERMS) project has been delayed due to extensive research of commercially available market solutions to meet functional requirements. | This project implements an Enterprise Distributed Energy Resource Management System (DERMS). This project will include software and hardware needed to monitor and control SDG&E Distributed Energy Resources (DER). This will set the foundation for SDG&E's future efforts to accomplish various strategic goals. | SDG&E-12-R TS-30 to TS-31 CWP 00920BA
Capital | INFORMATION TECHNOLOGY | SubTotal ENTERPRISE DISTRIBUTED ENERGY RESOURCE MANAGEMENT SYSTEM (DERMS) |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 3933999.96 | 4051999.92 | 4173999.96 | 4299000 | 3933999.96 | -3933999.96 | -4051999.92 | -4173999.96 | -4299000 | -3933999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | FOUNDATIONAL ANALYTICS FOR SAFETY, COMPLIANCE AND EFFICIENCY | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 3 | 1022067.5685 | 0 | 0 | 0 | 1022067.5685 | 6930999.96 | 7138999.92 | 7353000 | 7573999.92 | 6930999.96 | -5908932.3915 | -7138999.92 | -7353000 | -7573999.92 | -5908932.3915 | -85.25% | -100% | -100% | -100% | -85.25% | Applications | 7 |  |  |  | 7 | 50 |  |  |  | 50 | -43 | 0 | 0 | 0 | -43 | -86% | 0% | 0% | 0% | -86% | YES | YES | YES | Scope reduced in order to reallocate team capacity to higher-priority targeted data platform infrastructure hardening work. | Scope reduced in order to reallocate team capacity to higher-priority targeted data platform infrastructure hardening work. | Under (U) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This project provides business insights that drive business operational decisions. The project also designs and develops new and enhanced data views, data integrations, data cataloging, data visualizations and reports to allow the business to drive operational decisions. | SDG&E-25 WJE-52 CWP 00920BD
Capital | INFORMATION TECHNOLOGY | SubTotal FOUNDATIONAL ANALYTICS FOR SAFETY, COMPLIANCE AND EFFICIENCY |  |  |  | Yes |  |  | 1022067.5685 | 0 | 0 | 0 | 1022067.5685 | 6930999.96 | 7138999.92 | 7353000 | 7573999.92 | 6930999.96 | -5908932.3915 | -7138999.92 | -7353000 | -7573999.92 | -5908932.3915 | -85.25% | -100% | -100% | -100% | -85.25% | [21 empty] | YES | YES | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | GRC & REGULATORY MANAGEMENT SYSTEM - PHASE 3 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1687748.1941 | 0 | 0 | 0 | 1687748.1941 | 1494000 | 1539000 | 1584999.96 | 1632999.96 | 1494000 | 193748.1941 | -1539000 | -1584999.96 | -1632999.96 | 193748.1941 | 12.97% | -100% | -100% | -100% | 12.97% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal GRC & REGULATORY MANAGEMENT SYSTEM - PHASE 3 |  |  |  | Yes |  |  | 1687748.1941 | 0 | 0 | 0 | 1687748.1941 | 1494000 | 1539000 | 1584999.96 | 1632999.96 | 1494000 | 193748.1941 | -1539000 | -1584999.96 | -1632999.96 | 193748.1941 | 12.97% | -100% | -100% | -100% | 12.97% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | INVESTMENT PRIORITIZATION | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 3 | 2874463.6965 | 0 | 0 | 0 | 2874463.6965 | 10935000 | 11262999.96 | 11601000 | 11949000 | 10935000 | -8060536.3035 | -11262999.96 | -11601000 | -11949000 | -8060536.3035 | -73.71% | -100% | -100% | -100% | -73.71% | Applications | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | YES | NO | The underspend in 2024 is due to a schedule acceleration in 2023, resulting in increased spending during that year. The total project expenditure remains consistent with the forecast during the GRC cycle. | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The current asset investment planning tool has reached end of support and is limited in capabilities required for the new regulatory requirements. Regulatory agencies are requesting more transparency and accountability in capital spending. Using a data-driven and consistent value-based decision model approach, and in alignment with the Company's strategic plan, the Software as a Service (SaaS) solution - Asset Investment Planning and Management (AIPM) utilizes a consistent enterprise-level value framework to prioritize the capital investments. This project expands the implementation of the SaaS solution to other departments such as Gas Distribution, Information Technology, Fleet and Facilities, while continuing the business adoption with Electric Transmission, Substation, System Protection and Distribution group. | SDG&E-31-R-E KJD-86 to KJD-88 CWP 00920E
Capital | INFORMATION TECHNOLOGY | SubTotal INVESTMENT PRIORITIZATION |  |  |  | Yes |  |  | 2874463.6965 | 0 | 0 | 0 | 2874463.6965 | 10935000 | 11262999.96 | 11601000 | 11949000 | 10935000 | -8060536.3035 | -11262999.96 | -11601000 | -11949000 | -8060536.3035 | -73.71% | -100% | -100% | -100% | -73.71% | [21 empty] | YES | YES | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | IT QUALITY AND CONTINUOUS TESTING PLATFORMS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 747611.8847 | 0 | 0 | 0 | 747611.8847 | 1174999.92 | 1209999.96 | 1245999.96 | 1282999.92 | 1174999.92 | -427388.0353 | -1209999.96 | -1245999.96 | -1282999.92 | -427388.0353 | -36.37% | -100% | -100% | -100% | -36.37% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal IT QUALITY AND CONTINUOUS TESTING PLATFORMS |  |  |  | Yes |  |  | 747611.8847 | 0 | 0 | 0 | 747611.8847 | 1174999.92 | 1209999.96 | 1245999.96 | 1282999.92 | 1174999.92 | -427388.0353 | -1209999.96 | -1245999.96 | -1282999.92 | -427388.0353 | -36.37% | -100% | -100% | -100% | -36.37% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | LOCAL AREA DISTRIBUTION CONTROLLER (LADC) 2023-2024 | Non-RAMP | Non-RAMP | Non-RAMP | No | 0 | 2 | 913319.0524 | 0 | 0 | 0 | 913319.0524 | 0 | 0 | 0 | 0 | 0 | 913319.0524 | 0 | 0 | 0 | 913319.0524 | 100% | 0% | 0% | 0% | 100% | Sites | 1 |  |  |  | 1 | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | The variance is associated with project work completed before the GRC Decision was issued in December 2024 and the Decision ultimately did not authorize all forecasted projects. | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A | LADC is a software and hardware solution that enables the distribution grid operator to monitor, manage and control the component resources of a microgrid. The LADC is a key component of the successful deployments of microgrids operated by SDG&E. This distributed microgrid controller is necessary to augment and interoperate with SDG&E’s existing Advanced Distribution Management System (ADMS) and Supervisory Control and Data Acquisition (SCADA) system. The LADC will coordinate the control of Distributed Energy Resources (DERs) and conventional grid management devices (e.g., capacitors, switches) to ensure reliable operation during both island and grid-connected scenarios. | SDG&E-15-R-E FV-35 CWP 00920L
Capital | INFORMATION TECHNOLOGY | SubTotal LOCAL AREA DISTRIBUTION CONTROLLER (LADC) 2023-2024 |  |  |  | Yes |  |  | 913319.0524 | 0 | 0 | 0 | 913319.0524 | 0 | 0 | 0 | 0 | 0 | 913319.0524 | 0 | 0 | 0 | 913319.0524 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - ADVANCED DATA AND DECISION MODELING | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 3 | 1 | 643603.255 | 0 | 0 | 0 | 643603.255 | 4677999.96 | 4818000 | 4962999.96 | 5112000 | 4677999.96 | -4034396.705 | -4818000 | -4962999.96 | -5112000 | -4034396.705 | -86.24% | -100% | -100% | -100% | -86.24% | Applications | 1 |  |  |  | 1 | 5 |  |  |  | 5 | -4 | 0 | 0 | 0 | -4 | -80% | 0% | 0% | 0% | -80% | YES | NO | YES | N/A | Scope reduced in order to reallocate team capacity to higher-priority targeted data platform infrastructure hardening work. | Under (U) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | This project started in 2021. This project focuses on advanced machine learning and statistical or decision science use cases that drive wildfire mitigation, safety, electric reliability, energy transition and the ability to leverage on the elasticity of Cloud resources. It also focuses on the development and implementation of data science workbench and machine learning operations to support the enterprise. | SDG&E-25 WJE-52 to WJE-53 CWP 00920BE
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - ADVANCED DATA AND DECISION MODELING |  |  |  | Yes |  |  | 643603.255 | 0 | 0 | 0 | 643603.255 | 4677999.96 | 4818000 | 4962999.96 | 5112000 | 4677999.96 | -4034396.705 | -4818000 | -4962999.96 | -5112000 | -4034396.705 | -86.24% | -100% | -100% | -100% | -86.24% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - CLOUD FOUNDATIONS | Foundational Technology Systems | Cloud Resiliency Services | N/A | No | 5 | 5 | 5413520.6227 | 0 | 0 | 0 | 5413520.6227 | 6274999.92 | 6462999.96 | 6657000 | 6856999.92 | 6274999.92 | -861479.2973 | -6462999.96 | -6657000 | -6856999.92 | -861479.2973 | -13.73% | -100% | -100% | -100% | -13.73% | Cloud Environments | 3 |  |  |  | 3 | 3 |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - CLOUD FOUNDATIONS |  |  |  | Yes |  |  | 5413520.6227 | 0 | 0 | 0 | 5413520.6227 | 6274999.92 | 6462999.96 | 6657000 | 6856999.92 | 6274999.92 | -861479.2973 | -6462999.96 | -6657000 | -6856999.92 | -861479.2973 | -13.73% | -100% | -100% | -100% | -13.73% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - DECISION ANALYTICS & SITUATIONAL AWARENESS | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 3 | 1 | 525487.6271 | 0 | 0 | 0 | 525487.6271 | 1813999.92 | 1867999.92 | 1923999.96 | 1981999.92 | 1813999.92 | -1288512.2929 | -1867999.92 | -1923999.96 | -1981999.92 | -1288512.2929 | -71.03% | -100% | -100% | -100% | -71.03% | Applications | 1 |  |  |  | 1 | 5 |  |  |  | 5 | -4 | 0 | 0 | 0 | -4 | -80% | 0% | 0% | 0% | -80% | YES | NO | YES | N/A | Scope reduced in order to reallocate team capacity to higher-priority targeted data platform infrastructure hardening work. | Under (U) | Under (U) | Under (U) | Completed | NO | N/A | This project provides reporting and data analytics services that will drive business operational decisions. The project designs and develops new and enhanced data views, data integrations, data cataloging, data visualizations and reports to allow the business to make operational decisions. | SDG&E-25 WJE-53 to WJE-54 CWP 00920BF
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - DECISION ANALYTICS & SITUATIONAL AWARENESS |  |  |  | Yes |  |  | 525487.6271 | 0 | 0 | 0 | 525487.6271 | 1813999.92 | 1867999.92 | 1923999.96 | 1981999.92 | 1813999.92 | -1288512.2929 | -1867999.92 | -1923999.96 | -1981999.92 | -1288512.2929 | -71.03% | -100% | -100% | -100% | -71.03% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL ASSET AND DAMAGES DETECTION PLATFORM | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 3 | 3 | 2529952.3196 | 0 | 0 | 0 | 2529952.3196 | 4347000 | 4476999.96 | 4611000 | 4749000 | 4347000 | -1817047.6804 | -4476999.96 | -4611000 | -4749000 | -1817047.6804 | -41.8% | -100% | -100% | -100% | -41.8% | Applications | 8 |  |  |  | 8 | 15 |  |  |  | 15 | -7 | 0 | 0 | 0 | -7 | -46.67% | 0% | 0% | 0% | -46.67% | YES | NO | YES | N/A | Scope reduced in order to reallocate team capacity to higher-priority Climate Prediction Digital Twin work. | Under (U) | On Target (T) | On Target (T) | Completed | NO | N/A | This project addresses the increasing backlog of opportunities to utilize Intelligent Image Processing (IIP) and machine learning to automatically identify gas and electric assets, third party equipment and asset damages. | SDG&E-25 WJE-57 CWP 00920P
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - DIGITAL ASSET AND DAMAGES DETECTION PLATFORM |  |  |  | Yes |  |  | 2529952.3196 | 0 | 0 | 0 | 2529952.3196 | 4347000 | 4476999.96 | 4611000 | 4749000 | 4347000 | -1817047.6804 | -4476999.96 | -4611000 | -4749000 | -1817047.6804 | -41.8% | -100% | -100% | -100% | -41.8% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL PROCESS AUTOMATION | Non-RAMP | Non-RAMP | Non-RAMP | No | 3 | 3 | 3516182.219 | 0 | 0 | 0 | 3516182.219 | 3837999.96 | 3952999.92 | 4071000 | 4192999.92 | 3837999.96 | -321817.741 | -3952999.92 | -4071000 | -4192999.92 | -321817.741 | -8.385% | -100% | -100% | -100% | -8.385% | Applications | 28 |  |  |  | 28 | 25 |  |  |  | 25 | 3 | 0 | 0 | 0 | 3 | 12% | 0% | 0% | 0% | 12% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL PROCESS AUTOMATION | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 3 | 3 | 1758092.6095 | 0 | 0 | 0 | 1758092.6095 | 1893999.96 | 1950999.96 | 2008999.92 | 2070000 | 1893999.96 | -135907.3505 | -1950999.96 | -2008999.92 | -2070000 | -135907.3505 | -7.176% | -100% | -100% | -100% | -7.176% | Applications | 15 |  |  |  | 15 | 15 |  |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal |  |  |  | Yes |  |  | 5274274.8285 | 0 | 0 | 0 | 5274274.8285 | 5731999.92 | 5903999.88 | 6079999.92 | 6262999.92 | 5731999.92 | -457725.0915 | -5903999.88 | -6079999.92 | -6262999.92 | -457725.0915 | -7.985% | -100% | -100% | -100% | -7.985% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - ELECTIRC DISTRIBUTION ASSET INVESTMENT | Asset Management | Asset Management | N/A | No | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 4677999.96 | 4818000 | 4962999.96 | 5112000 | 4677999.96 | -4677999.96 | -4818000 | -4962999.96 | -5112000 | -4677999.96 | -100% | -100% | -100% | -100% | -100% | Applications | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Project was completed prior to 2024 | Under (U) | Under (U) | Under (U) | Completed | YES | Project completed prior to 2024 | This is a continuation of a project that began in 2021. The current Asset Investment Planning tool has reached the end of support and is lacking in capabilities required for upcoming regulatory requirements (RAMP/S-MAP). Regulatory bodies are requesting more transparency and accountability in capital spending. Using a consistent value-based decision model approach, and in alignment with the Company's strategic plan, the project will implement a new Asset Investment Planning and Management (AIPM) tool, which will utilize the enterprise-level value framework to optimize the capital project portfolio for Electric Distribution. | SDG&E-31-R-E KJD-86 to KJD-88 CWP 00920BL
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - ELECTIRC DISTRIBUTION ASSET INVESTMENT |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 4677999.96 | 4818000 | 4962999.96 | 5112000 | 4677999.96 | -4677999.96 | -4818000 | -4962999.96 | -5112000 | -4677999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | RAMP - ENERGY TRANSITION DIGITAL TWIN | Foundational Technology Systems | Monitoring Systems and Services | N/A | No | 3 | 3 | 2517037.4197 | 0 | 0 | 0 | 2517037.4197 | 2346000 | 2415999.96 | 2487999.96 | 2562999.96 | 2346000 | 171037.4197 | -2415999.96 | -2487999.96 | -2562999.96 | 171037.4197 | 7.291% | -100% | -100% | -100% | 7.291% | Use Cases | 3 |  |  |  | 3 | 3 |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - ENERGY TRANSITION DIGITAL TWIN |  |  |  | Yes |  |  | 2517037.4197 | 0 | 0 | 0 | 2517037.4197 | 2346000 | 2415999.96 | 2487999.96 | 2562999.96 | 2346000 | 171037.4197 | -2415999.96 | -2487999.96 | -2562999.96 | 171037.4197 | 7.291% | -100% | -100% | -100% | 7.291% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - FIELD MOBILE HARDWARE REPLACEMENT | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 2 | 2 | 2554000.5769 | 0 | 0 | 0 | 2554000.5769 | 4186999.92 | 4312999.92 | 4443000 | 4575999.96 | 4186999.92 | -1632999.3431 | -4312999.92 | -4443000 | -4575999.96 | -1632999.3431 | -39% | -100% | -100% | -100% | -39% | Devices | 800 |  |  |  | 800 | 800 |  |  |  | 800 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - FIELD MOBILE HARDWARE REPLACEMENT |  |  |  | Yes |  |  | 2554000.5769 | 0 | 0 | 0 | 2554000.5769 | 4186999.92 | 4312999.92 | 4443000 | 4575999.96 | 4186999.92 | -1632999.3431 | -4312999.92 | -4443000 | -4575999.96 | -1632999.3431 | -39% | -100% | -100% | -100% | -39% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - FIELD SERVICE DELIVERY (FSD) - DATA & ANALYTICS PLATFORM | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency; Gas Operations Systems Resiliency | N/A | No | 2 | 1 | 3194318.7468 | 0 | 0 | 0 | 3194318.7468 | 5754999.96 | 5928000 | 6105999.96 | 6288999.96 | 5754999.96 | -2560681.2132 | -5928000 | -6105999.96 | -6288999.96 | -2560681.2132 | -44.49% | -100% | -100% | -100% | -44.49% | Applications | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - FIELD SERVICE DELIVERY (FSD) - DATA & ANALYTICS PLATFORM |  |  |  | Yes |  |  | 3194318.7468 | 0 | 0 | 0 | 3194318.7468 | 5754999.96 | 5928000 | 6105999.96 | 6288999.96 | 5754999.96 | -2560681.2132 | -5928000 | -6105999.96 | -6288999.96 | -2560681.2132 | -44.49% | -100% | -100% | -100% | -44.49% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - FIELD SERVICE DELIVERY (FSD) - SCHEDULING & DISPATCH PHASE | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency; Gas Operations Systems Resiliency | N/A | No | 4 | 2 | 17630759.3042 | 0 | 0 | 0 | 17630759.3042 | 12480000 | 12853999.92 | 13239999.96 | 13636999.92 | 12480000 | 5150759.3042 | -12853999.92 | -13239999.96 | -13636999.92 | 5150759.3042 | 41.27% | -100% | -100% | -100% | 41.27% | Applications | 2 |  |  |  | 2 | 2 |  |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | YES | NO | Scope refinement based detailed analysis of requirements, and updated deployment approach to ensure optimum outcomes, increased timeline and level of effort from original plan. | N/A | Over (O) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | The Company's current scheduling and dispatch functions have three critical issues: the current scheduling system is highly customized, the users have adopted manual process workarounds, and the work management systems are not fully integrated. The current version of ClickSoftware is out of support. The current Click mobile solutions (Classic and Touch) are integrated with the current software version and must be upgraded or replaced.This project will leverage this opportunity to transform the scheduling and dispatching functions by implementing leading technology and processes. | SDG&E-17-R DHT-44 to DHT-45 CWP 00920AI
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - FIELD SERVICE DELIVERY (FSD) - SCHEDULING & DISPATCH PHASE |  |  |  | Yes |  |  | 17630759.3042 | 0 | 0 | 0 | 17630759.3042 | 12480000 | 12853999.92 | 13239999.96 | 13636999.92 | 12480000 | 5150759.3042 | -12853999.92 | -13239999.96 | -13636999.92 | 5150759.3042 | 41.27% | -100% | -100% | -100% | 41.27% | [21 empty] | YES | YES | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - GIS MODERNIZATION | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 3 | 3 | 2403155.7766 | 0 | 0 | 0 | 2403155.7766 | 405999.96 | 417999.96 | 430999.92 | 444000 | 405999.96 | 1997155.8166 | -417999.96 | -430999.92 | -444000 | 1997155.8166 | 491.9% | -100% | -100% | -100% | 491.9% | Applications | 4 |  |  |  | 4 | 4 |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - GIS MODERNIZATION |  |  |  | Yes |  |  | 2403155.7766 | 0 | 0 | 0 | 2403155.7766 | 405999.96 | 417999.96 | 430999.92 | 444000 | 405999.96 | 1997155.8166 | -417999.96 | -430999.92 | -444000 | 1997155.8166 | 491.9% | -100% | -100% | -100% | 491.9% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - INFRASTRUCTURE AS A SERVICE (IAAS) IMPLEMENTATION | Foundational Technology Systems | Cloud Resiliency Services | N/A | No | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2362999.92 | 2433999.96 | 2506999.92 | 2581999.92 | 2362999.92 | -2362999.92 | -2433999.96 | -2506999.92 | -2581999.92 | -2362999.92 | -100% | -100% | -100% | -100% | -100% | Contracts | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The project has been deferred due to the incomplete status of the prerequisite foundational work. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This project provides prepaid infrastructure in Amazon Web Services (AWS) for critical applications to migrate to the Cloud. Additionally, this project enables faster delivery of this infrastructure through a standard consumption and pricing model. | SDG&E-25 WJE-44 to WJE-45 CWP 00908W
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - INFRASTRUCTURE AS A SERVICE (IAAS) IMPLEMENTATION |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 2362999.92 | 2433999.96 | 2506999.92 | 2581999.92 | 2362999.92 | -2362999.92 | -2433999.96 | -2506999.92 | -2581999.92 | -2362999.92 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | RAMP - JUNIPER 2022 EQUIPMENT REPLACEMENT AGREEMENT | Foundational Technology Systems | Network & Voice System Resiliency | N/A | No | On-going | Annual | 1370514 | 0 | 0 | 0 | 1370514 | 1408999.92 | 1450999.92 | 1494999.96 | 1539999.96 | 1408999.92 | -38485.92 | -1450999.92 | -1494999.96 | -1539999.96 | -38485.92 | -2.731% | -100% | -100% | -100% | -2.731% | Contracts | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - JUNIPER 2022 EQUIPMENT REPLACEMENT AGREEMENT |  |  |  | Yes |  |  | 1370514 | 0 | 0 | 0 | 1370514 | 1408999.92 | 1450999.92 | 1494999.96 | 1539999.96 | 1408999.92 | -38485.92 | -1450999.92 | -1494999.96 | -1539999.96 | -38485.92 | -2.731% | -100% | -100% | -100% | -2.731% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - LOCAL AREA NETWORK (LAN) REFRESH 2022 | Foundational Technology Systems | Network & Voice System Resiliency | N/A | No | 4 | 4 | 1337599.3942 | 0 | 0 | 0 | 1337599.3942 | 5841000 | 6015999.96 | 6196999.92 | 6382999.92 | 5841000 | -4503400.6058 | -6015999.96 | -6196999.92 | -6382999.92 | -4503400.6058 | -77.1% | -100% | -100% | -100% | -77.1% | Sites | 10 |  |  |  | 10 | 10 |  |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - LOCAL AREA NETWORK (LAN) REFRESH 2022 |  |  |  | Yes |  |  | 1337599.3942 | 0 | 0 | 0 | 1337599.3942 | 5841000 | 6015999.96 | 6196999.92 | 6382999.92 | 5841000 | -4503400.6058 | -6015999.96 | -6196999.92 | -6382999.92 | -4503400.6058 | -77.1% | -100% | -100% | -100% | -77.1% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - TELECOM SITE IMPROVEMENTS | Foundational Technology Systems | Network & Voice System Resiliency | N/A | No | 4 | 4 | 2213183.806 | 0 | 0 | 0 | 2213183.806 | 4395999.96 | 4527999.96 | 4663999.92 | 4803999.96 | 4395999.96 | -2182816.154 | -4527999.96 | -4663999.92 | -4803999.96 | -2182816.154 | -49.65% | -100% | -100% | -100% | -49.65% | Sites | 14 |  |  |  | 14 | 14 |  |  |  | 14 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - TELECOM SITE IMPROVEMENTS |  |  |  | Yes |  |  | 2213183.806 | 0 | 0 | 0 | 2213183.806 | 4395999.96 | 4527999.96 | 4663999.92 | 4803999.96 | 4395999.96 | -2182816.154 | -4527999.96 | -4663999.92 | -4803999.96 | -2182816.154 | -49.65% | -100% | -100% | -100% | -49.65% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - TRANSMISSION COMMUNICATIONS RELIABILITY IMPROVEMENT (TCRI) 2024 | Foundational Technology Systems | Network & Voice System Resiliency | N/A | No | On-going | Annual | 3096972.5737 | 0 | 0 | 0 | 3096972.5737 | 5532000 | 5697999.96 | 5869999.92 | 6045999.96 | 5532000 | -2435027.4263 | -5697999.96 | -5869999.92 | -6045999.96 | -2435027.4263 | -44.02% | -100% | -100% | -100% | -44.02% | Sites | 5 |  |  |  | 5 | 5 |  |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - TRANSMISSION COMMUNICATIONS RELIABILITY IMPROVEMENT (TCRI) 2024 |  |  |  | Yes |  |  | 3096972.5737 | 0 | 0 | 0 | 3096972.5737 | 5532000 | 5697999.96 | 5869999.92 | 6045999.96 | 5532000 | -2435027.4263 | -5697999.96 | -5869999.92 | -6045999.96 | -2435027.4263 | -44.02% | -100% | -100% | -100% | -44.02% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - VEGETATION MANAGEMENT - WORK MANAGEMENT | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2103999.96 | 2166999.96 | 2232000 | 2298999.96 | 2103999.96 | -2103999.96 | -2166999.96 | -2232000 | -2298999.96 | -2103999.96 | -100% | -100% | -100% | -100% | -100% | Applications | 0 |  |  |  | 0 | 2 |  |  |  | 2 | -2 | 0 | 0 | 0 | -2 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The project was delayed in 2024 in order to reallocate team capacity to higher-priority Field Service Delivery (FSD) - Scheduling & Dispatch Phase. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | The project was delayed in 2024 in order to reallocate team capacity to higher-priority FSD - Scheduling & Dispatch Phase. | This project will replace the Vegetation Management Powerworkz/EPOCH and VETS system with an SAP Work Management solution. This project would leverage existing SAP ECC and ESRI Geographic Information System (GIS) as well as incorporate the following: 1) SAP Geographical Enablement Framework (GEF) which will allow us to visualize assets, work in a geographical view linked to GIS, and manage (create/edit/view) directly from a geo-view in SAP 2) SAP Analytics Cloud which will allow us to explore data to achieve better compliance and work efficiency (forecast, comparison, progress tracking, capacity analysis). | SDG&E-13-2R-E JTW-168 to JTW-169 CWP 00920R
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - VEGETATION MANAGEMENT - WORK MANAGEMENT |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 2103999.96 | 2166999.96 | 2232000 | 2298999.96 | 2103999.96 | -2103999.96 | -2166999.96 | -2232000 | -2298999.96 | -2103999.96 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | RAMP - VEHICLE TELEMATICS - PHASE 2 | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 402000 | 414000 | 426000 | 390000 | -390000 | -402000 | -414000 | -426000 | -390000 | -100% | -100% | -100% | -100% | -100% | Applications | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Variance is due to the project being delayed in 2024 to resolve implementation issues around privacy concerns. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This project will implement additional functionality for SDG&E Fleet Vehicle Telematics to improve usability and increase accuracy by implementing Active Directory Integration, Outage Map Integration, and a Companywide Electronic Driver Vehicle Inspection Reporting (eDVIR) Program. | SDG&E-22-R-E AA-35 to AA-39 CWP 00920BI
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - VEHICLE TELEMATICS - PHASE 2 |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 390000 | 402000 | 414000 | 426000 | 390000 | -390000 | -402000 | -414000 | -426000 | -390000 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | INFORMATION TECHNOLOGY | RAMP - VIRTUAL DESKTOP EXPANSION (VDI) - PHASE 2 | Foundational Technology Systems | End User Access and Supporting Services | N/A | No | 2 | 3 | 128304.5585 | 0 | 0 | 0 | 128304.5585 | 1830999.96 | 1884999.96 | 1941999.96 | 2001000 | 1830999.96 | -1702695.4015 | -1884999.96 | -1941999.96 | -2001000 | -1702695.4015 | -92.99% | -100% | -100% | -100% | -92.99% | Virtual desktop instances | 0 |  |  |  | 0 | 2500 |  |  |  | 2500 | -2500 | 0 | 0 | 0 | -2500 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Project was delayed in order to reallocate team capacity to higher priority compliance-related process automation work (workpaper Data Governance Tools & Framework). | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This project expands the enterprise Virtual Desktop Infrastructure (VDI) Platform, making Citrix the single VDI Platform for the Company. | SDG&E-25 WJE-35 CWP 00908C
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - VIRTUAL DESKTOP EXPANSION (VDI) - PHASE 2 |  |  |  | Yes |  |  | 128304.5585 | 0 | 0 | 0 | 128304.5585 | 1830999.96 | 1884999.96 | 1941999.96 | 2001000 | 1830999.96 | -1702695.4015 | -1884999.96 | -1941999.96 | -2001000 | -1702695.4015 | -92.99% | -100% | -100% | -100% | -92.99% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - WIDE AREA NETWORK (WAN) REFRESH | Foundational Technology Systems | Network & Voice System Resiliency | N/A | No | 4 | 4 | 424810.5481 | 0 | 0 | 0 | 424810.5481 | 3582000 | 3690000 | 3801000 | 3915000 | 3582000 | -3157189.4518 | -3690000 | -3801000 | -3915000 | -3157189.4518 | -88.14% | -100% | -100% | -100% | -88.14% | Sites | 100 |  |  |  | 100 | 100 |  |  |  | 100 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - WIDE AREA NETWORK (WAN) REFRESH |  |  |  | Yes |  |  | 424810.5481 | 0 | 0 | 0 | 424810.5481 | 3582000 | 3690000 | 3801000 | 3915000 | 3582000 | -3157189.4518 | -3690000 | -3801000 | -3915000 | -3157189.4518 | -88.14% | -100% | -100% | -100% | -88.14% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP- ASSET 360 - ASSET DATA FOUNDATION | Asset Management | Asset Management | N/A | No | 3 | 3 | 2271951.7344 | 0 | 0 | 0 | 2271951.7344 | 2941999.92 | 3030000 | 3120999.96 | 3214999.92 | 2941999.92 | -670048.1856 | -3030000 | -3120999.96 | -3214999.92 | -670048.1856 | -22.78% | -100% | -100% | -100% | -22.78% | Models for Dashboard | 14 |  |  |  | 14 | 30 |  |  |  | 30 | -16 | 0 | 0 | 0 | -16 | -53.33% | 0% | 0% | 0% | -53.33% | YES | NO | YES | N/A | Scope is constantly being refined and re-priorized. Fewer number of data models were developed than originally forecasted. | Under (U) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The third Phase of the Asset 360 Project incorporates disparate electric asset data into a consolidated Data Foundation in SAP Hana. It will also advance and enhance consolidated data views, asset health and risk models for electric assets. | SDG&E-31-R-E KJD-84 to KJD-85 CWP 00920BM
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP- ASSET 360 - ASSET DATA FOUNDATION |  |  |  | Yes |  |  | 2271951.7344 | 0 | 0 | 0 | 2271951.7344 | 2941999.92 | 3030000 | 3120999.96 | 3214999.92 | 2941999.92 | -670048.1856 | -3030000 | -3120999.96 | -3214999.92 | -670048.1856 | -22.78% | -100% | -100% | -100% | -22.78% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | SMART GRID OPERATIONS 2024 | Non-RAMP | Non-RAMP | Non-RAMP | No | 1 | 1 | 3434767.5366 | 0 | 0 | 0 | 3434767.5366 | 2970000 | 3058999.92 | 3150999.96 | 3246000 | 2970000 | 464767.5366 | -3058999.92 | -3150999.96 | -3246000 | 464767.5366 | 15.65% | -100% | -100% | -100% | 15.65% | Applications | 4 |  |  |  | 4 | 4 |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal SMART GRID OPERATIONS 2024 |  |  |  | Yes |  |  | 3434767.5366 | 0 | 0 | 0 | 3434767.5366 | 2970000 | 3058999.92 | 3150999.96 | 3246000 | 2970000 | 464767.5366 | -3058999.92 | -3150999.96 | -3246000 | 464767.5366 | 15.65% | -100% | -100% | -100% | 15.65% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | SMART METER (PRODUCT) 2022-2024 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1820233.5037 | 0 | 0 | 0 | 1820233.5037 | 0 | 0 | 0 | 0 | 0 | 1820233.5037 | 0 | 0 | 0 | 1820233.5037 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal SMART METER (PRODUCT) 2022-2024 |  |  |  | Yes |  |  | 1820233.5037 | 0 | 0 | 0 | 1820233.5037 | 0 | 0 | 0 | 0 | 0 | 1820233.5037 | 0 | 0 | 0 | 1820233.5037 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | SMART METER 2.0 | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 13348505.1075 | 0 | 0 | 0 | 13348505.1075 | 0 | 0 | 0 | 0 | 0 | 13348505.1075 | 0 | 0 | 0 | 13348505.1075 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal SMART METER 2.0 |  |  |  | Yes |  |  | 13348505.1075 | 0 | 0 | 0 | 13348505.1075 | 0 | 0 | 0 | 0 | 0 | 13348505.1075 | 0 | 0 | 0 | 13348505.1075 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | TEST ACCELERATION ENABLEMENT (TAE) WITH DEVSECOPS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1454125.8917 | 0 | 0 | 0 | 1454125.8917 | 2038999.92 | 2100000 | 2163000 | 2227999.92 | 2038999.92 | -584874.0283 | -2100000 | -2163000 | -2227999.92 | -584874.0283 | -28.68% | -100% | -100% | -100% | -28.68% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal TEST ACCELERATION ENABLEMENT (TAE) WITH DEVSECOPS |  |  |  | Yes |  |  | 1454125.8917 | 0 | 0 | 0 | 1454125.8917 | 2038999.92 | 2100000 | 2163000 | 2227999.92 | 2038999.92 | -584874.0283 | -2100000 | -2163000 | -2227999.92 | -584874.0283 | -28.68% | -100% | -100% | -100% | -28.68% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | IT ELECTRIC OPERATIONS SYSTEMS | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | No | On-going | Annual | 581513.7495 | 0 | 0 | 0 | 581513.7495 | 0 | 0 | 0 | 0 | 0 | 581513.7495 | 0 | 0 | 0 | 581513.7495 | 100% | 0% | 0% | 0% | 100% | This workpaper for Application - RAMP portfolio contains various projects within the following categories: (1) Field Hardware Mobile Data Terminals (MDT) Replacement; (2) Situational Awareness Dashboards. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal IT ELECTRIC OPERATIONS SYSTEMS |  |  |  | Yes |  |  | 581513.7495 | 0 | 0 | 0 | 581513.7495 | 0 | 0 | 0 | 0 | 0 | 581513.7495 | 0 | 0 | 0 | 581513.7495 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | IT NON-RAMP CUSTOMER SERVICE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1819729.8379 | 0 | 0 | 0 | 1819729.8379 | 0 | 0 | 0 | 0 | 0 | 1819729.8379 | 0 | 0 | 0 | 1819729.8379 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal IT NON-RAMP CUSTOMER SERVICE |  |  |  | Yes |  |  | 1819729.8379 | 0 | 0 | 0 | 1819729.8379 | 0 | 0 | 0 | 0 | 0 | 1819729.8379 | 0 | 0 | 0 | 1819729.8379 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | NETWORK SYSTEMS | Foundational Technology Systems | Network & Voice System Resiliency | N/A | No | On-going | Annual | 2217071.6865 | 0 | 0 | 0 | 2217071.6865 | 0 | 0 | 0 | 0 | 0 | 2217071.6865 | 0 | 0 | 0 | 2217071.6865 | 100% | 0% | 0% | 0% | 100% | This workpaper for the Network - RAMP portfolio contains various projects within the following categories: (1) Software Defined Wide Area Network (SD-WAN) Implementation; (2) Data Center Network (DCN) Core Refresh; (3) Network Time Protocol (NTP) Clock Refresh and (4) - Field Area Network (FAN) Voice & Dispatch - Phase 2. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal NETWORK SYSTEMS |  |  |  | Yes |  |  | 2217071.6865 | 0 | 0 | 0 | 2217071.6865 | 0 | 0 | 0 | 0 | 0 | 2217071.6865 | 0 | 0 | 0 | 2217071.6865 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | NON-RAMP APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 7211006.9065 | 0 | 0 | 0 | 7211006.9065 | 0 | 0 | 0 | 0 | 0 | 7211006.9065 | 0 | 0 | 0 | 7211006.9065 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal NON-RAMP APPLICATIONS |  |  |  | Yes |  |  | 7211006.9065 | 0 | 0 | 0 | 7211006.9065 | 0 | 0 | 0 | 0 | 0 | 7211006.9065 | 0 | 0 | 0 | 7211006.9065 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - DIGI REMOTE MANAGER 2023 | Foundational Technology Systems | Monitoring Systems and Services | N/A | No | 1 | 2 | 6865.9018 | 0 | 0 | 0 | 6865.9018 | 0 | 0 | 0 | 0 | 0 | 6865.9018 | 0 | 0 | 0 | 6865.9018 | 100% | 0% | 0% | 0% | 100% | Projected was completed prior to 2024. 2024 activity is related to trailing charges. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - DIGI REMOTE MANAGER 2023 |  |  |  | Yes |  |  | 6865.9018 | 0 | 0 | 0 | 6865.9018 | 0 | 0 | 0 | 0 | 0 | 6865.9018 | 0 | 0 | 0 | 6865.9018 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL WORKSPACE | Foundational Technology Systems | End User Access and Supporting Services | N/A | No | 3 | 4 | 68240.8059 | 0 | 0 | 0 | 68240.8059 | 0 | 0 | 0 | 0 | 0 | 68240.8059 | 0 | 0 | 0 | 68240.8059 | 100% | 0% | 0% | 0% | 100% | Project was completed prior to 2024. 2024 activity is related to trailing charges. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - DIGITAL WORKSPACE |  |  |  | Yes |  |  | 68240.8059 | 0 | 0 | 0 | 68240.8059 | 0 | 0 | 0 | 0 | 0 | 68240.8059 | 0 | 0 | 0 | 68240.8059 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | ENTERPRISE PRODUCTIVITY & COLLAB SDGE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1033667.114 | 0 | 0 | 0 | 1033667.114 | 0 | 0 | 0 | 0 | 0 | 1033667.114 | 0 | 0 | 0 | 1033667.114 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal ENTERPRISE PRODUCTIVITY & COLLAB SDGE |  |  |  | Yes |  |  | 1033667.114 | 0 | 0 | 0 | 1033667.114 | 0 | 0 | 0 | 0 | 0 | 1033667.114 | 0 | 0 | 0 | 1033667.114 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | IOS EPOCH MOBILITY APPS 2024 | Non-RAMP | Non-RAMP | Non-RAMP | No | 0 | 1 | 1084406.9816 | 0 | 0 | 0 | 1084406.9816 | 0 | 0 | 0 | 0 | 0 | 1084406.9816 | 0 | 0 | 0 | 1084406.9816 | 100% | 0% | 0% | 0% | 100% | Applications | 2 |  |  |  | 2 | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 | 2 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Emergent need to upgrade applications that are solely Windows based application and upgrading them to be able to run on iOS devices. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | This program focuses on upgrading applications that are solely Windows based application and upgrading them to be able to run on iOS devices. | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal IOS EPOCH MOBILITY APPS 2024 |  |  |  | Yes |  |  | 1084406.9816 | 0 | 0 | 0 | 1084406.9816 | 0 | 0 | 0 | 0 | 0 | 1084406.9816 | 0 | 0 | 0 | 1084406.9816 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | NETBRAIN ENHANCEMENTS (P) | Non-RAMP | Non-RAMP | Non-RAMP | No | 0 | 1 | 465720.4716 | 0 | 0 | 0 | 465720.4716 | 0 | 0 | 0 | 0 | 0 | 465720.4716 | 0 | 0 | 0 | 465720.4716 | 100% | 0% | 0% | 0% | 100% | Devices | 5000 |  |  |  | 5000 | 0 |  |  |  | 0 | 5000 | 0 | 0 | 0 | 5000 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | To ensure network reliability, and allow for better insights into our network infrastructure, this emergent project was to extend network coverage and add additional telecom devices. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | To ensure network reliability, and allow for better insights into our network infrastructure, this emergent project was to extend network coverage and add additional telecom devices. | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal NETBRAIN ENHANCEMENTS (P) |  |  |  | Yes |  |  | 465720.4716 | 0 | 0 | 0 | 465720.4716 | 0 | 0 | 0 | 0 | 0 | 465720.4716 | 0 | 0 | 0 | 465720.4716 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | POWERWORKZ AGILE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | No | 0 | 2 | 1027539.4194 | 0 | 0 | 0 | 1027539.4194 | 0 | 0 | 0 | 0 | 0 | 1027539.4194 | 0 | 0 | 0 | 1027539.4194 | 100% | 0% | 0% | 0% | 100% | Applications | 2 |  |  |  | 2 | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 | 2 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Emergent need to upgrade the PowerWorkz suite of applications in support of Vegetation Management. This included scope for application upgrades, support scripts and reporting supporting vegetation management operations and reporting requirements. | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | This program supports the PowerWorkz suite of applications in support of Vegetation Management. This included scope for application upgrades, support scripts and reporting supporting vegetation management operations and reporting requirements. | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal POWERWORKZ AGILE PROGRAM |  |  |  | Yes |  |  | 1027539.4194 | 0 | 0 | 0 | 1027539.4194 | 0 | 0 | 0 | 0 | 0 | 1027539.4194 | 0 | 0 | 0 | 1027539.4194 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | PROJECT ECHELON SDGE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 2007405.413 | 0 | 0 | 0 | 2007405.413 | 0 | 0 | 0 | 0 | 0 | 2007405.413 | 0 | 0 | 0 | 2007405.413 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal PROJECT ECHELON SDGE |  |  |  | Yes |  |  | 2007405.413 | 0 | 0 | 0 | 2007405.413 | 0 | 0 | 0 | 0 | 0 | 2007405.413 | 0 | 0 | 0 | 2007405.413 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RCM UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | No | 0 | 3 | 236700 | 0 | 0 | 0 | 236700 | 0 | 0 | 0 | 0 | 0 | 236700 | 0 | 0 | 0 | 236700 | 100% | 0% | 0% | 0% | 100% | Server Host Upgrades | 2 |  |  |  | 2 | 0 |  |  |  | 0 | 2 | 0 | 0 | 0 | 2 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Project scope was to perform software enhancements and provide platform security features with newer code versions to ensure compliance with vendor hardware compatibility, component integration, security compliance monitoring, inoperability validation reducing the risk of outages induced by untested or incompatible firmware of code releases or defects, through functionality and regression testing. This is done at each data center, and upgrades all firmware and software for VC Infrastructure. | Over (O) | Over (O) | Over (O) | Emergent | NO |  | Project scope was to perform software enhancements and provide platform security features with newer code versions to ensure compliance with vendor hardware compatibility, component integration, security compliance monitoring, inoperability validation reducing the risk of outages induced by untested or incompatible firmware of code releases or defects, through functionality and regression testing. This is done at each data center, and upgrades all firmware and software for VC Infrastructure. Completed 2 units in 2022, 2 units in 2023, and 2 units in 2024. | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal RCM UPGRADES |  |  |  | Yes |  |  | 236700 | 0 | 0 | 0 | 236700 | 0 | 0 | 0 | 0 | 0 | 236700 | 0 | 0 | 0 | 236700 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | SMART METER NETWORK DEVICES | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 356425.1646 | 0 | 0 | 0 | 356425.1646 | 0 | 0 | 0 | 0 | 0 | 356425.1646 | 0 | 0 | 0 | 356425.1646 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal SMART METER NETWORK DEVICES |  |  |  | Yes |  |  | 356425.1646 | 0 | 0 | 0 | 356425.1646 | 0 | 0 | 0 | 0 | 0 | 356425.1646 | 0 | 0 | 0 | 356425.1646 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | SORT UPGRADE- ENTERPRISE | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 1304731.636 | 0 | 0 | 0 | 1304731.636 | 0 | 0 | 0 | 0 | 0 | 1304731.636 | 0 | 0 | 0 | 1304731.636 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal SORT UPGRADE- ENTERPRISE |  |  |  | Yes |  |  | 1304731.636 | 0 | 0 | 0 | 1304731.636 | 0 | 0 | 0 | 0 | 0 | 1304731.636 | 0 | 0 | 0 | 1304731.636 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | TEMS 2024 (P) | Non-RAMP | Non-RAMP | Non-RAMP | No | 0 | 1 | 551463 | 0 | 0 | 0 | 551463 | 0 | 0 | 0 | 0 | 0 | 551463 | 0 | 0 | 0 | 551463 | 100% | 0% | 0% | 0% | 100% | Applications | 1 |  |  |  | 1 | 0 |  |  |  | 0 | 1 | 0 | 0 | 0 | 1 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Emergent need to implement the Calero Telecom Expense Management System (TEMS) solution to replace the out-of-support Tangoe TEMS solution. | Over (O) | Over (O) | Over (O) | Emergent | NO |  | The project is to implement a modern cloud based telecom expense management solution to replace the legacy on-premises system, ensuring seamless integration, ongoing support, and optimization. | N/A
Capital | INFORMATION TECHNOLOGY | SubTotal TEMS 2024 (P) |  |  |  | Yes |  |  | 551463 | 0 | 0 | 0 | 551463 | 0 | 0 | 0 | 0 | 0 | 551463 | 0 | 0 | 0 | 551463 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | TM1 ENHANCEMENTS- O&M PROCESS MODERNIZATION | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 123167.4316 | 0 | 0 | 0 | 123167.4316 | 0 | 0 | 0 | 0 | 0 | 123167.4316 | 0 | 0 | 0 | 123167.4316 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal TM1 ENHANCEMENTS- O&M PROCESS MODERNIZATION |  |  |  | Yes |  |  | 123167.4316 | 0 | 0 | 0 | 123167.4316 | 0 | 0 | 0 | 0 | 0 | 123167.4316 | 0 | 0 | 0 | 123167.4316 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | MY ENERGY CENTER | Non-RAMP | Non-RAMP | Non-RAMP | No |  |  | 12152003.5315 | 0 | 0 | 0 | 12152003.5315 | 0 | 0 | 0 | 0 | 0 | 12152003.5315 | 0 | 0 | 0 | 12152003.5315 | 100% | 0% | 0% | 0% | 100% | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | NO | NO | NO | [6 empty] | NO
Capital | INFORMATION TECHNOLOGY | SubTotal MY ENERGY CENTER |  |  |  | Yes |  |  | 12152003.5315 | 0 | 0 | 0 | 12152003.5315 | 0 | 0 | 0 | 0 | 0 | 12152003.5315 | 0 | 0 | 0 | 12152003.5315 | 100% | 0% | 0% | 0% | 100% | [21 empty] | NO | NO | [7 empty] | NO
Capital | INFORMATION TECHNOLOGY | RAMP - EMERGENCY COMMUNICATIONS ENHANCEMENTS | Foundational Technology Systems | Emergency Operations Center (EOC) Technology Resiliency | N/A | No | 1 | 3 | 556.4929 | 0 | 0 | 0 | 556.4929 | 0 | 0 | 0 | 0 | 0 | 556.4929 | 0 | 0 | 0 | 556.4929 | 100% | 0% | 0% | 0% | 100% | Project was completed prior to 2024. 2024 activity is related to trailing charges. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Completed | NO
Capital | INFORMATION TECHNOLOGY | SubTotal RAMP - EMERGENCY COMMUNICATIONS ENHANCEMENTS |  |  |  | Yes |  |  | 556.4929 | 0 | 0 | 0 | 556.4929 | 0 | 0 | 0 | 0 | 0 | 556.4929 | 0 | 0 | 0 | 556.4929 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO

## GOSM-C
SDG&E SAFETY, RISK, & ASSET MANAGEMENT SYSTEMS Capital
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | SAFETY, RISK, & ASSET MANAGEMENT SYSTEMS | SAFETY, RISK, & ASSET MANAGEMENT SYSTEMS |  |  |  | Yes |  |  | 2309229.4739 | 0 | 0 | 0 | 2309229.4739 | 2972999.88 | 3061999.92 | 3152999.88 | 3247999.8 | 2972999.88 | -663770.4061 | -3061999.92 | -3152999.88 | -3247999.8 | -663770.4061 | -22.33% | -100% | -100% | -100% | -22.33%
Capital | SAFETY MANAGEMENT SYSTEMS | CONTRACTOR FIELD SAFETY MANAGEMENT POOL | Incident Involving a Contractor | Enhanced Verification of Class 1 | Overall | No | On-going | Annual | 97280.6725 | 0 | 0 | 0 | 97280.6725 | 144000 | 147999.96 | 151999.92 | 156999.96 | 144000 | -46719.3275 | -147999.96 | -151999.92 | -156999.96 | -46719.3275 | -32.44% | -100% | -100% | -100% | -32.44% | Contractor hours | 181246 |  |  |  | 181246 | 378991 |  |  |  | 378991 | -197745 | 0 | 0 | 0 | -197745 | -52.18% | 0% | 0% | 0% | -52.18% | YES | NO | YES | N/A | The variance is primarily driven by lower than forecasted staffing levels. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | The new OH pool will collect the costs of managing all Class 1 contractors across the company except for those costs associated with major projects. Those costs will be directly charged to the major projects they support. | SDG&E-31-R-E KJD-81 to KJD-82 CWP S09060
Capital | SAFETY MANAGEMENT SYSTEMS | CONTRACTOR FIELD SAFETY MANAGEMENT POOL | Incident Involving a Contractor | Enterprise-Wide Contractor Incident and | N/A | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 70999.92 | 72999.96 | 75000 | 76999.92 | 70999.92 | -70999.92 | -72999.96 | -75000 | -76999.92 | -70999.92 | -100% | -100% | -100% | -100% | -100% | Contractor hours | 0 |  |  |  | 0 | 188946 |  |  |  | 188946 | -188946 | 0 | 0 | 0 | -188946 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Implementation of this mitigation is currently deferred while enhancements are being developed and coordinated. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | The new OH pool will collect the costs of managing all Class 1 contractors across the company except for those costs associated with major projects. Those costs will be directly charged to the major projects they support. | SDG&E-31-R-E KJD-81 to KJD-82 CWP S09060
Capital | SAFETY MANAGEMENT SYSTEMS | CONTRACTOR FIELD SAFETY MANAGEMENT POOL | Incident Involving a Contractor | Field Safety Oversight | Overall | No | On-going | Annual | 2211948.8014 | 0 | 0 | 0 | 2211948.8014 | 2757999.96 | 2841000 | 2925999.96 | 3013999.92 | 2757999.96 | -546051.1586 | -2841000 | -2925999.96 | -3013999.92 | -546051.1586 | -19.8% | -100% | -100% | -100% | -19.8% | Contractor hours | 7068593 |  |  |  | 7068593 | 6920703 |  |  |  | 6920703 | 147890 | 0 | 0 | 0 | 147890 | 2.137% | 0% | 0% | 0% | 2.137% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | SAFETY MANAGEMENT SYSTEMS | SubTotal CONTRACTOR FIELD SAFETY MANAGEMENT POOL |  |  |  | Yes |  |  | 2309229.4739 | 0 | 0 | 0 | 2309229.4739 | 2972999.88 | 3061999.92 | 3152999.88 | 3247999.8 | 2972999.88 | -663770.4061 | -3061999.92 | -3152999.88 | -3247999.8 | -663770.4061 | -22.33% | -100% | -100% | -100% | -22.33% | [21 empty] | YES | NO | [7 empty] | NO

## EOWM-C-B
SDG&E WILDFIRE MITIGATION & VEGETATION MANAGEMENT Capital
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WILDFIRE MITIGATION & VEGETATION MANAGEMENT |  |  |  | Yes |  |  | 485403550.8731 | 0 | 0 | 0 | 485403550.8731 | 395990998.56 | 417102998.64 | 424479998.64 | 432423998.28 | 395990998.56 | 89412552.3131 | -417102998.64 | -424479998.64 | -432423998.28 | 89412552.3131 | 22.58% | -100% | -100% | -100% | 22.58%
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ADVANCED PROTECTION | Wildfire Involving SDG&E Equipment | Advanced Protection | Tier 3 | No | On-going | Annual | 14811763.9553 | 0 | 0 | 0 | 14811763.9553 | 6945999.96 | 7153999.92 | 7368000 | 7588999.92 | 6945999.96 | 7865763.9953 | -7153999.92 | -7368000 | -7588999.92 | 7865763.9953 | 113.2% | -100% | -100% | -100% | 113.2% | Circuits enabled | 5 |  |  |  | 5 | 8 |  |  |  | 8 | -3 | 0 | 0 | 0 | -3 | -37.5% | 0% | 0% | 0% | -37.5% | YES | YES | YES | Variance is driven by increased scope for Advanced Protection substation capital projects which incurred a much higher unit cost. Scope was also expanded to include Early Fault Detection project, which will deploy Power Quality Meters and advanced Radio Frequency (RF) Sensors in SDG&E electric substations and electric distribution circuits within the High Fire Threat District to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. | Resource constraints at the end of 2024 caused reprioritization of construction to other projects and prevented completion of three projects in 2024. | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.463 and WMP.1195 in the 2023 WMP filing. The purpose of this project is to replace aging circuit breakers and/or obsolete electromechanical relays and to create a more comprehensive protection system with installation of Distribution Supervisory Control and Data Acquisition (SCADA). Substation improvements include the following: • Reconfiguration of 12kV circuit breakers and relays to meet reliability and safety standards. • Installation of Distribution SCADA. • Installation of new transformer bank relays. • Installation of new 12kV Bus Differential relays. • Installation of microprocessor feeder relays. Advanced Protection devices to enhance feeder protection, reduce fire risk, and enable opportunities include: • Falling conductor logic • Downed conductor detection (DCD) • Arc sensing technology (AST) • Advanced SGF (spike counting/adaptive set-point) • Remote event retrieval • Remote setting changes | SDG&E-13-2R-E JTW-119 to JTW-121 CWP 152590
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal ADVANCED PROTECTION |  |  |  | Yes |  |  | 14811763.9553 | 0 | 0 | 0 | 14811763.9553 | 6945999.96 | 7153999.92 | 7368000 | 7588999.92 | 6945999.96 | 7865763.9953 | -7153999.92 | -7368000 | -7588999.92 | 7865763.9953 | 113.2% | -100% | -100% | -100% | 113.2% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ADVANCED WEATHER STATION INTEGRATION AND FORECAST | Wildfire Involving SDG&E Equipment | Advanced Weather Station Integration | N/A | No | On-going | Annual | 116008.5098 | 0 | 0 | 0 | 116008.5098 | 475999.92 | 489999.96 | 504999.96 | 519999.96 | 475999.92 | -359991.4102 | -489999.96 | -504999.96 | -519999.96 | -359991.4102 | -75.63% | -100% | -100% | -100% | -75.63% | Weather sensors | 1 |  |  |  | 1 | 20 |  |  |  | 20 | -19 | 0 | 0 | 0 | -19 | -95% | 0% | 0% | 0% | -95% | YES | NO | YES | N/A | Project includes multi-spectral cameras, fuel moisture sensors and additional software upgrades and modifications. The unit variance is primarily driven by the limited Santa Ana events and lack of data that helps identify gaps in coverage which facilitates the install schedule and helps predict and monitor weather during extreme weather events. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Situational Awareness and Forecasting GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1430 in the 2023 WMP filing. The SDG&E Weather Station Network was originally developed and deployed in 2009 and weather stations are reaching end of life. The purpose of this project is to strategically enhance the Weather Network ensuring continuing operations of critical fire weather infrastructure. This project will continuously enhance the Weather Network to ensure a reliable flow of operationally critical fire weather information. This information will be fed into fire weather tools such as the Fire Potential Index (FPI) and the Santa Anna Wildfire Threat Index (SAWTI). This data is used for decision-making during emergency situations to mitigate fire and weather-related risks. The Weather Network will be upgraded by installing new weather stations capable of more frequent weather reads. Additionally, multi-spectral cameras, fuel moisture sensors, and additional capabilities will be integrated to help predict and monitor weather during extreme weather events. | SDG&E-13-2R-E JTW-98 to JTW-100 CWP 192470
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal ADVANCED WEATHER STATION INTEGRATION AND FORECAST |  |  |  | Yes |  |  | 116008.5098 | 0 | 0 | 0 | 116008.5098 | 475999.92 | 489999.96 | 504999.96 | 519999.96 | 475999.92 | -359991.4102 | -489999.96 | -504999.96 | -519999.96 | -359991.4102 | -75.63% | -100% | -100% | -100% | -75.63% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP PRIVATE LTE | Wildfire Involving SDG&E Equipment | LTE Communication Network | N/A | No | On-going | Annual | 12745554.7968 | 0 | 0 | 0 | 12745554.7968 | 82902000 | 85389000 | 87951000 | 90589999.92 | 82902000 | -70156445.2032 | -85389000 | -87951000 | -90589999.92 | -70156445.2032 | -84.63% | -100% | -100% | -100% | -84.63% | Base stations | 3 |  |  |  | 3 | 72 |  |  |  | 72 | -69 | 0 | 0 | 0 | -69 | -95.83% | 0% | 0% | 0% | -95.83% | YES | YES | YES | To further align WMP programs with funding totals authorized by SDG&E’s GRC, SDG&E completed less base stations in an effort to realize cost efficiencies aligned with its GRC decision. This program has no direct impact to risk reduction and therefore will not change SDG&E’s risk profile. | To further align WMP programs with funding totals authorized by SDG&E’s GRC, SDG&E completed less base stations in an effort to realize cost efficiencies aligned with its GRC decision. This program has no direct impact to risk reduction and therefore will not change SDG&E’s risk profile. | Under (U) | Under (U) | Under (U) | Other | NO | SDG&E is now forecasting to complete fewer stations over the GRC cycle than originally projected. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.549 in the 2023 WMP filing. Existing wireless communications infrastructure is increasingly inadequate to meet the demand for greater volumes of data at high speed. Expanding the existing systems can provide coverage over a larger area but cannot meet the demand for high volume low latency data and control. To address this, SDG&E is implementing a private broadband wireless digital communications network. SDG&E is deploying a privately-owned LTE network using licensed radio frequency (RF) spectrum by means of the Distribution Communications Reliability Improvements (DCRI) program. This will enhance the overall reliability of SDG&E's communication network, which is critical for enabling fire prevention and public safety programs. SDG&E's communication network is foundational to many initiatives that demand reliable communication. The ability to reliably enable and disable sensitive settings, enable or disable reclosing, or even remotely operating a switch during a high-risk weather event demands reliable communication that the LTE network will provide. SDG&E's Falling Conductor Protection in particular relies on a robust communications network to operate successfully and falling conductor circuits will continue to be enabled as SDG&E's communication network comes online. | SDG&E-13-2R-E JTW-112 to JTW-114 CWP 198730
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP PRIVATE LTE |  |  |  | Yes |  |  | 12745554.7968 | 0 | 0 | 0 | 12745554.7968 | 82902000 | 85389000 | 87951000 | 90589999.92 | 82902000 | -70156445.2032 | -85389000 | -87951000 | -90589999.92 | -70156445.2032 | -84.63% | -100% | -100% | -100% | -84.63% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | AVIATION FIREFIGHTING PROGRAM | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 3 | No | 8 | 5 | 2241358.8401 | 0 | 0 | 0 | 2241358.8401 | 9567999.96 | 9855999.96 | 10152000 | 10456999.92 | 9567999.96 | -7326641.12 | -9855999.96 | -10152000 | -10456999.92 | -7326641.12 | -76.57% | -100% | -100% | -100% | -76.57% | The workpaper contains activities that serve as a wildfire suppression resource to ensure aerial firefighting resources remain available in the region including initial purchase of the helicopter and modification costs and costs for purchases related to UAS. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | Under forecasted spend due to deferral of Airbus helicopter purchase. 2024 spend includes spare parts and the Total Assurance Program (TAP) agreement with Sikorsky for the Firehawk helicopter and UAS purchases. | N/A | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This workpaper was included in the Grid Operations and Protocols GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.557 in the 2023 WMP filing. Under certain conditions, a wildfire that is not suppressed may grow rapidly and uncontrollably and endanger public safety. Additionally, in the event of an simultaneous wildfire events fire agencies could divert aerial resources to fight wildfires outside of SDG&E’s service territory. To mitigate this risk, the aviation firefighting program serves as a wildfire suppression resource to ensure aerial firefighting resources remain available in the region. To enhance SDG&E’s aviation firefighting program, this budget code includes the purchase of a new Sikorsky S-70M Firehawk and the development of an aviation training area. The purpose of purchasing and equipping of a new Sikorsky S-70M Firehawk is to complete firefighting and heavy construction needs for SDG&E. The purpose of the “On the Rocks” Aviation Training Area is to train helicopter and UAS pilots. | SDG&E-13-2R-E JTW-145 to JTW-149 CWP 202770
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal AVIATION FIREFIGHTING PROGRAM |  |  |  | Yes |  |  | 2241358.8401 | 0 | 0 | 0 | 2241358.8401 | 9567999.96 | 9855999.96 | 10152000 | 10456999.92 | 9567999.96 | -7326641.12 | -9855999.96 | -10152000 | -10456999.92 | -7326641.12 | -76.57% | -100% | -100% | -100% | -76.57% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | CNF FIRE HARDENING | Wildfire Involving SDG&E Equipment | Cleveland National Forest Fire Hardening T1-T2 | Tier 3 | No | On-going | Annual | 1035885.1086 | 0 | 0 | 0 | 1035885.1086 | 1512000 | 1557000 | 1603999.92 | 1651999.92 | 1512000 | -476114.8914 | -1557000 | -1603999.92 | -1651999.92 | -476114.8914 | -31.49% | -100% | -100% | -100% | -31.49% | The workpaper contains activities related to post-construction habitat restoration that is required by project permits for temporarily impacted mitigatable vegetation communities. This includes restoration implementation (weed control and seeding), supplemental seeding, monitoring and maintenance, reporting, and agency meetings/site visits. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1017 in the 2023 WMP filing. The Cleveland National Forest (CNF) Fire Hardening program hardened distribution electric infrastructure within CNF boundaries through replacing wood poles with steel poles, replacing aged conductor with new high-strength conductor, and associated upgrades. The CNF hardening projects were all completed in 2021 but environmental restoration costs will continue. | SDG&E-13-2R-E JTW-130 to JTW-132 CWP 81650
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal CNF FIRE HARDENING |  |  |  | Yes |  |  | 1035885.1086 | 0 | 0 | 0 | 1035885.1086 | 1512000 | 1557000 | 1603999.92 | 1651999.92 | 1512000 | -476114.8914 | -1557000 | -1603999.92 | -1651999.92 | -476114.8914 | -31.49% | -100% | -100% | -100% | -31.49% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | CORRECTIVE MAINTENANCE PROGRAM TIER 2&3 | Wildfire Involving SDG&E Equipment | Transmission System Inspection | N/A | No | On-going | Annual | 1042850.7261 | 0 | 0 | 0 | 1042850.7261 | 726999.96 | 748999.92 | 771000 | 793999.92 | 726999.96 | 315850.7661 | -748999.92 | -771000 | -793999.92 | 315850.7661 | 43.45% | -100% | -100% | -100% | 43.45% | Poles replaced | 27 |  |  |  | 27 | 19 |  |  |  | 19 | 8 | 0 | 0 | 0 | 8 | 42.11% | 0% | 0% | 0% | 42.11% | YES | NO | YES | N/A | Variance is attributed to the fact that Transmission CMP programs are compliance driven and forecast was based on historical needs rather than specifically planned projects. They are dynamic reactive programs remediating GO95 infractions discovered during routine mandated inspections. In addition, the Transmission reliability programs are proactive/risk mitigation driven and forecasted based on annual historical performance data, so a planned number of projects on any given year may fluctuate +/- a percentage based on a number of factors such as engineering performance, permitting durations, material lead times, construction crews availability, and canceled/delayed outage requests. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.479 in the 2023 WMP filing. To meet SDG&E's obligation to serve by providing funding for the Corrective Maintenance Program (CMP) in areas designated as HFTD. To meet SDGE’s obligation to serve and the safety requirements promulgated by CPUC G .O 95, A.B. 1890, A.B. 1017, etc., this project provides funds for several purposes, such as: 1. To maintain and restore transmission facilities. 2. To repair the system in the vent of disaster such as storm or fire 3. To provide funding for a pole restoration program for in-service transmission wood poles. 4. To provide funding for annual NERC and Tie Lines Assessments (TLA). | SDG&E-13-2R-E JTW-140 to JTW-141 CWP 201270
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal CORRECTIVE MAINTENANCE PROGRAM TIER 2&3 |  |  |  | Yes |  |  | 1042850.7261 | 0 | 0 | 0 | 1042850.7261 | 726999.96 | 748999.92 | 771000 | 793999.92 | 726999.96 | 315850.7661 | -748999.92 | -771000 | -793999.92 | 315850.7661 | 43.45% | -100% | -100% | -100% | 43.45% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | DIGITAL FORTRESS | Foundational Technology Systems | Emergency Management Operations | N/A | No | On-going | Annual | 3153510.0469 | 0 | 0 | 0 | 3153510.0469 | 0 | 0 | 0 | 0 | 0 | 3153510.0469 | 0 | 0 | 0 | 3153510.0469 | 100% | 0% | 0% | 0% | 100% | The workpaper contains activities to continue enhancements on the Emergency Operations Center Applications including Public Saftey Power Shutoff Dashboard, Outage Dashboard, Notification Dashboard, Emergency Response Team Roster, Air Quality Index, and Heat Index, fire season support, Gen Artifical Intelligence component built on Amazon Web Services Bedrock to accelerate governmental reporting process, application security enhancements, User Interface alerts when there are data issues, implementation of roll-back procedures for Emergency Operations Center applications, and First Responder Application blueprint that includes high-level functionality, low-level User Interface mockups, and system architecture. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Emergency Planning and Preparedness GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1008 in the 2023 WMP filing. The purpose of this project is to migrate Tier 1 EOC Applications and Dashboards to a cloud-based environment. EOC operations provide risk mitigation of wildfires, PSPS, and other weather-related events. Currently, applications used to make de-energization decisions are housed on-premise and are subject to network outages, leading to lost availability and performance issues. This project will establish DevOps processes and tools to reduce cycle time, improve quality, and reduce manual processes. The application code will be modernized to utilize the cloud environment so more efficiency can be gained. Reporting and analytics data will be decoupled with transactional data through a dedicated EOC data platform. | SDG&E-13-2R-E JTW-159 to JTW-161 CWP 218820
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal DIGITAL FORTRESS |  |  |  | Yes |  |  | 3153510.0469 | 0 | 0 | 0 | 3153510.0469 | 0 | 0 | 0 | 0 | 0 | 3153510.0469 | 0 | 0 | 0 | 3153510.0469 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | DRONE INVESTIGATION ASSESMENT AND REPAIR | Wildfire Involving SDG&E Equipment | Distribution System Inspection Drone Inspections | Tier 2 | No | On-going | Annual | 73078532.4154 | 0 | 0 | 0 | 73078532.4154 | 8665999.92 | 8925999.96 | 9193999.92 | 9469999.92 | 8665999.92 | 64412532.4954 | -8925999.96 | -9193999.92 | -9469999.92 | 64412532.4954 | 743.3% | -100% | -100% | -100% | 743.3% | Pole replacements | 1992 |  |  |  | 1992 | 159 |  |  |  | 159 | 1833 | 0 | 0 | 0 | 1833 | 1153% | 0% | 0% | 0% | 1153% | YES | YES | YES | Repair work based on 2021 and 2022 inspections in the Tier 2 HFTD was anticipated to be completed by end of 2023 and ongoing inspections and repairs were expected to be significantly reduced in 2024 going forward. However, 2022 and 2023 work to repair defects identified during the 2021-2022 inspections were shifted into 2024 and later due to identifying significantly more scope than anticipated, engineering delays, resource constraints and material shortages. In addition, repair work associated with the ongoing inspections performed in 2023 and 2024 was higher than forecasted. | Repair work based on 2021 and 2022 inspections in the Tier 2 HFTD was anticipated to be completed by end of 2023 and ongoing inspections and repairs were expected to be significantly reduced in 2024 going forward. However, 2022 and 2023 work to repair defects identified during the 2021-2022 inspections were shifted into 2024 and later due to identifying significantly more scope than anticipated, engineering delays, resource constraints and material shortages. In addition, repair work associated with the ongoing inspections performed in 2023 and 2024 was higher than forecasted. | Over (O) | Over (O) | Over (O) | Other | NO | Repair work based on 2021 and 2022 inspections in the Tier 2 HFTD was anticipated to be completed by end of 2023 and ongoing inspections and repairs were expected to be significantly reduced in 2024 going forward. However, 2022 and 2023 work to repair defects identified during the 2021-2022 inspections were shifted into 2024 and later due to identifying significantly more scope than anticipated, engineering delays, resource constraints and material shortages. In addition, repair work associated with the ongoing inspections performed in 2023 and 2024 was higher than forecasted. | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.552 in the 2023 WMP filing. SDG&E's Drone Investigation Assessment and Repair (DIAR) program performs drone inspections of SDG&E's overhead distribution infrastructure in the HFTD. These drone inspections provide high definition images of distribution infrastructure from vantage points that are not obtainable using traditional ground inspections. These images are processed through machine learning and reviewed by qualified electrical workers to find infractions. This budget code represents the repairs associated with correcting the infractions found during these inspections. These repairs include pole replacements and associated work that help ensure reliability and safety of the electric distribution system. | SDG&E-13-2R-E JTW-141 to JTW-145 CWP 202480
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal DRONE INVESTIGATION ASSESMENT AND REPAIR |  |  |  | Yes |  |  | 73078532.4154 | 0 | 0 | 0 | 73078532.4154 | 8665999.92 | 8925999.96 | 9193999.92 | 9469999.92 | 8665999.92 | 64412532.4954 | -8925999.96 | -9193999.92 | -9469999.92 | 64412532.4954 | 743.3% | -100% | -100% | -100% | 743.3% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD HOT LINE CLAMPS | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 2 | No | On-going | Annual | 578970.6886 | 0 | 0 | 0 | 578970.6886 | 0 | 0 | 0 | 0 | 0 | 578970.6886 | 0 | 0 | 0 | 578970.6886 | 100% | 0% | 0% | 0% | 100% | Hot line clamps | 575 |  |  |  | 575 | 0 |  |  |  | 0 | 575 | 0 | 0 | 0 | 575 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Hotline clamp replacements are identified concurrently with lightning arrestor replacements and are required to support lightning arrestors, which is the driver for the volume of capital work performed in this program. The forecast had assumed performance of standalone hotline clamp jobs instead of the current process to bundle asset replacement work at a single pole, which includes hotline clamp work. This bundled approach is classified as a capital expense. | Over (O) | Over (O) | Over (O) | Other | NO | Only O&M-related work was scoped for the 2024 GRC. Capital-related work is also being performed in this program as hotline clamp replacements are identified concurrently with lightning arrestor replacements and are required to support lightning arrestors. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.464 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD HOT LINE CLAMPS | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 3 | No | On-going | Annual | 102171.298 | 0 | 0 | 0 | 102171.298 | 0 | 0 | 0 | 0 | 0 | 102171.298 | 0 | 0 | 0 | 102171.298 | 100% | 0% | 0% | 0% | 100% | Hot line clamps | 103 |  |  |  | 103 | 0 |  |  |  | 0 | 103 | 0 | 0 | 0 | 103 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Hotline clamp replacements are identified concurrently with lightning arrestor replacements and are required to support lightning arrestors, which is the driver for the volume of capital work performed in this program. The forecast had assumed performance of standalone hotline clamp jobs instead of the current process to bundle asset replacement work at a single pole, which includes hotline clamp work. This bundled approach is classified as a capital expense. | Over (O) | Over (O) | Over (O) | Other | NO | Only O&M-related work was scoped for the 2024 GRC. Capital-related work is also being performed in this program as hotline clamp replacements are identified concurrently with lightning arrestor replacements and are required to support lightning arrestors. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.464 in the 2023 WMP filing. SDG&E’s grid hardening programs are a set of initiatives that address the goal of reducing wildfires caused by utility equipment and minimizing the impacts to customers from mitigations such as PSPS. SDG&E has a number of initiatives including covered conductor and strategic undergrounding that reduce risk events on utility equipment, reducing the opportunities for ignition. SDG&E has a number of protection and equipment programs such as advanced protection, the expulsion fuse replacement program, and the lightning arrestor program. These programs reduce the chance that a risk event results in an ignition by utilizing protection settings and/or equipment that address a specific failure mode known to lead to ignition. Finally, SDG&E has a number of programs with the purpose of reducing PSPS impacts to customers including the PSPS sectionalizing program, microgrid and generator programs, as well as strategic undergrounding. The impacts of these programs are measured in the number of customers who will have reduced impacts from PSPS events assuming weather conditions similar to previous events. The costs represented are the O&M costs associated with the capital grid hardening programs, and the costs associated with the fully O&M programs such as the generator programs. | SDG&E-13-2R-E JTW-48 to JTW-54 WP 1WM003.000
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal HFTD HOT LINE CLAMPS |  |  |  | Yes |  |  | 681141.9866 | 0 | 0 | 0 | 681141.9866 | 0 | 0 | 0 | 0 | 0 | 681141.9866 | 0 | 0 | 0 | 681141.9866 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP PSPS MOBILE AND ENS ENHANCEMENTS | Wildfire Involving SDG&E Equipment | Communication Practices | N/A | No | 9 | 5 | 6719063.47 | 0 | 0 | 0 | 6719063.47 | 3699000 | 3810000 | 3924000 | 4041999.96 | 3699000 | 3020063.47 | -3810000 | -3924000 | -4041999.96 | 3020063.47 | 81.65% | -100% | -100% | -100% | 81.65% | The workpaper contains activities to enhance the existing SDG&E Emergency Notification System (ENS) by implementing automations and mandatory CPUC reporting requirements. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Stakeholder Cooperation and Community Engagement GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.563 in the 2023 WMP filing. The purpose of the Enterprise Notification System (ENS) project is to enhance and update the functionality of the Emergency Notification System (ENS), a critical Tier 1 business operations application used in notifying customers of both planned and unplanned outages across the service territory. Updates to the ENS application are required to meet regulatory requirements by sending appropriate customer communications during PSPS events and supporting both internal and external reporting requirements. | SDG&E-13-2R-E JTW-163 to JTW-166 CWP 208900
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP PSPS MOBILE AND ENS ENHANCEMENTS |  |  |  | Yes |  |  | 6719063.47 | 0 | 0 | 0 | 6719063.47 | 3699000 | 3810000 | 3924000 | 4041999.96 | 3699000 | 3020063.47 | -3810000 | -3924000 | -4041999.96 | 3020063.47 | 81.65% | -100% | -100% | -100% | 81.65% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | EMERGENCY MANAGEMENT OPERATIONS | Foundational Technology Systems | Emergency Management Operations | N/A | No | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 2949000 | 3036999.96 | 3127999.92 | 3222000 | 2949000 | -2949000 | -3036999.96 | -3127999.92 | -3222000 | -2949000 | -100% | -100% | -100% | -100% | -100% | The workpaper contains activities to expand the capabilities of the Noggin 2.0 system with additional digitization of incident forms, workflow configuration, SMS/email notifications of events, and additional compliance and situational awareness reports to migrate about existing 500 end users from WebEOC to Noggin. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Completed | YES | This workpaper was completed and fully implemented in 2023. | WebEOC supports mission-critical functions in the Emergency Operations Centers (EOCs) of SoCal Gas, SDG&E and Gas Operations for tracking, managing and reporting incidents. Implemented more than eight years ago, WebEOC has fallen behind current information technology advancements and cannot be integrated with other mission critical systems such as GIS, HR, and Microsoft Active Directory, and is limited in its ability to expand and adapt to changing business, regulatory, and technical requirements. The Noggin core 2.0 system was implemented in 2020 to replace WebEOC for the Emergency Management group with the digitization of incident report forms, situational awareness dashboard, SMS/email notifications, and compliance reporting. | SDG&E-13-2R-E JTW-157 to JTW-159 CWP 218790
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal EMERGENCY MANAGEMENT OPERATIONS |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 2949000 | 3036999.96 | 3127999.92 | 3222000 | 2949000 | -2949000 | -3036999.96 | -3127999.92 | -3222000 | -2949000 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | FIRE SCIENCE ENHANCEMENT (WRRM-OPS) | Wildfire Involving SDG&E Equipment | WRRM - OPS | N/A | No | On-going | Annual | 0.45004 | 0 | 0 | 0 | 0.45004 | 3144999.96 | 3238999.92 | 3336000 | 3435999.96 | 3144999.96 | -3144999.51 | -3238999.92 | -3336000 | -3435999.96 | -3144999.51 | -100% | -100% | -100% | -100% | -100% | The workpaper contains activities to modernize and expand the capabilities of existing tools such as the Fire Potential Index to asses the risk and the impacts of wildfire and reduce the number of required patrols following outages. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | 2024-2027 work scope will only consist of O&M costs associated with visualization and storage of various models. O&M costs are presented in WP 1WM002.000. | This workpaper was included in the Risk Assessment and Mapping GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.450 and WMP .521 in the 2023 WMP filing. The purpose of this project is to develop new fire science technologies to increase the effectiveness of existing tools such as the Fire Potential Index (FPI) The modernization of existing tools is critical to daily operations and enhances efficiencies and increases reliability by reducing the number of required patrols following outages . This project, also called FireSafe 3.0, embodies a massive collaboration between SDG&E, academia, and private industry enabling efficient management and significant cutting-edge output from terabytes of data. | SDG&E-13-2R-E JTW-94 to JTW-97 CWP 192480
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal FIRE SCIENCE ENHANCEMENT (WRRM-OPS) |  |  |  | Yes |  |  | 0.45004 | 0 | 0 | 0 | 0.45004 | 3144999.96 | 3238999.92 | 3336000 | 3435999.96 | 3144999.96 | -3144999.51 | -3238999.92 | -3336000 | -3435999.96 | -3144999.51 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD EXPULSION FUSE REPLACEMENT | Wildfire Involving SDG&E Equipment | HFTD Expulsion Fuse Replacements | Tier 2 | No | On-going | Annual | 99058.3415 | 0 | 0 | 0 | 99058.3415 | 0 | 0 | 0 | 0 | 0 | 99058.3415 | 0 | 0 | 0 | 99058.3415 | 100% | 0% | 0% | 0% | 100% | Fuses replaced | 90 |  |  |  | 90 | 0 |  |  |  | 0 | 90 | 0 | 0 | 0 | 90 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Expulsion Fuse Replacements are identified concurrently with lightning arrestor replacements and are required to support lightning arrestors, which is the driver for the volume of work performed in this program. Additional work was carried over from 2023 due to a mid-2023 fuse shortage. | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.459 in the 2023 WMP filing. This project will proactively replace at risk electric distribution cutout bodies and fuses in HFTD Tier 2 and Tier 3 with Cal Fire approved devices in order to reduce the risk of wildfire ignition. Infrastructure upgrades as required to facilitate these fuse changeouts may also be implemented. This work is pursuant to Wildfire Mitigation Plan (WMP) scoping. | SDG&E-13-2R-E JTW-118 to JTW-119 CWP 192420
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD EXPULSION FUSE REPLACEMENT | Wildfire Involving SDG&E Equipment | HFTD Expulsion Fuse Replacements | Tier 3 | No | On-going | Annual | 107313.2033 | 0 | 0 | 0 | 107313.2033 | 0 | 0 | 0 | 0 | 0 | 107313.2033 | 0 | 0 | 0 | 107313.2033 | 100% | 0% | 0% | 0% | 100% | Fuses replaced | 98 |  |  |  | 98 | 0 |  |  |  | 0 | 98 | 0 | 0 | 0 | 98 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Expulsion Fuse Replacements are identified concurrently with lightning arrestor replacements and are required to support lightning arrestors, which is the driver for the volume of work performed in this program. Additional work was carried over from 2023 due to a mid-2023 fuse shortage. | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.459 in the 2023 WMP filing. This project will proactively replace at risk electric distribution cutout bodies and fuses in HFTD Tier 2 and Tier 3 with Cal Fire approved devices in order to reduce the risk of wildfire ignition. Infrastructure upgrades as required to facilitate these fuse changeouts may also be implemented. This work is pursuant to Wildfire Mitigation Plan (WMP) scoping. | SDG&E-13-2R-E JTW-118 to JTW-119 CWP 192420
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal HFTD EXPULSION FUSE REPLACEMENT |  |  |  | Yes |  |  | 206371.5448 | 0 | 0 | 0 | 206371.5448 | 0 | 0 | 0 | 0 | 0 | 206371.5448 | 0 | 0 | 0 | 206371.5448 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP VEGETATION MANAGEMENT SERVICE POWERW | Wildfire Involving SDG&E Equipment | WMP VEGETATION MANAGEMENT SERVICE POWERW | N/A | No | Emergent | 2 | 622158.424 | 0 | 0 | 0 | 622158.424 | 0 | 0 | 0 | 0 | 0 | 622158.424 | 0 | 0 | 0 | 622158.424 | 100% | 0% | 0% | 0% | 100% | The workpaper contains activities to upgrade Vegetation Management Services (VMS) to deliver an automated environmental data update for Wood Pole Intrusive inspections and develop VMS Patrols and TCM workflows, and regulatory reporting mandates. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The workpaper contains activities to upgrade Vegetation Management Services (VMS) to deliver an automated environmental data update for Wood Pole Intrusive inspections and develop VMS Patrols and TCM workflows, and regulatory reporting mandates. | N/A
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP VEGETATION MANAGEMENT SERVICE POWERW |  |  |  | Yes |  |  | 622158.424 | 0 | 0 | 0 | 622158.424 | 0 | 0 | 0 | 0 | 0 | 622158.424 | 0 | 0 | 0 | 622158.424 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD SCADA CAPACITOR REPLACEMENT | Wildfire Involving SDG&E Equipment | SCADA Capacitors (HFTD Tier 2) | Tier 2 | No | On-going | Annual | 189384.0625 | 0 | 0 | 0 | 189384.0625 | 1788999.96 | 1842999.96 | 1897999.92 | 1954999.92 | 1788999.96 | -1599615.8975 | -1842999.96 | -1897999.92 | -1954999.92 | -1599615.8975 | -89.41% | -100% | -100% | -100% | -89.41% | Capacitors replaced | 1 |  |  |  | 1 | 24 |  |  |  | 24 | -23 | 0 | 0 | 0 | -23 | -95.83% | 0% | 0% | 0% | -95.83% | YES | NO | YES | N/A | Majority of the project was completed in 2023 with the last project completed in 2024 due to environmental constraints. All risk reduction was met in 2024 with completion of this program. | Under (U) | Under (U) | Under (U) | Completed | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.453 in the 2023 WMP filing. The purpose of this project is to replace existing non-SCADA capacitors with a more modern SCADA switchable capacitor or to remove non-SCADA capacitors if not required for voltage or reactive support . These modernized capacitors have a monitoring system to check for imbalances and isolate internal faults before they become catastrophic. In addition, SCADA capacitors have the capacity for remote isolation and monitoring of the system which provides additional situational awareness during extreme weather conditions. While this program will not reduce capacitor faults, the advanced protection equipment is designed to detect and isolate issues before a capacitor rupture occurs, reducing the failure mode most likely to lead to an ignition. SCADA line capacitors will send capacitor failures and fuse operation alerts to the electric control center. This will increase capacitor reliability, minimize downtime, and expedite repair work. | SDG&E-13-2R-E JTW-107 to JTW-108 CWP 202580
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal HFTD SCADA CAPACITOR REPLACEMENT |  |  |  | Yes |  |  | 189384.0625 | 0 | 0 | 0 | 189384.0625 | 1788999.96 | 1842999.96 | 1897999.92 | 1954999.92 | 1788999.96 | -1599615.8975 | -1842999.96 | -1897999.92 | -1954999.92 | -1599615.8975 | -89.41% | -100% | -100% | -100% | -89.41% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD TRANSM. FIBER OPTICS | Wildfire Involving SDG&E Equipment | LTE Communication Network | N/A | No | On-going | Annual | 13676161.8256 | 0 | 0 | 0 | 13676161.8256 | 9652999.92 | 9942999.96 | 10240999.92 | 10548000 | 9652999.92 | 4023161.9056 | -9942999.96 | -10240999.92 | -10548000 | 4023161.9056 | 41.68% | -100% | -100% | -100% | 41.68% | Miles of cable | 6 |  |  |  | 6 | 26 |  |  |  | 26 | -20 | 0 | 0 | 0 | -20 | -76.92% | 0% | 0% | 0% | -76.92% | YES | NO | YES | N/A | Completed less miles than anticipated due to outage constraints and contractor resources, expecting to complete remaining miles in 2025. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.549 in the 2023 WMP filing. This project provides funds for the installation, upgrade, and expansion of SDG&E’s Fiber Optic communication system for Control & Protection of Transmission and Distribution lines, and automation in areas of High Fire Threat Districts (HFTD). Secure fiber optic communications is required for transporting large amount of high speed data throughput for Condition Based Maintenance (CBM), Wide Area Measurement and Control (Synchrophasors/Phasor Measurement), Video Security and Surveillance, Smart Grid technologies and IT network communications. | SDG&E-13-2R-E JTW-114 to JTW-115 CWP 191340
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal HFTD TRANSM. FIBER OPTICS |  |  |  | Yes |  |  | 13676161.8256 | 0 | 0 | 0 | 13676161.8256 | 9652999.92 | 9942999.96 | 10240999.92 | 10548000 | 9652999.92 | 4023161.9056 | -9942999.96 | -10240999.92 | -10548000 | 4023161.9056 | 41.68% | -100% | -100% | -100% | 41.68% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HIGH RISK POLE REPLACEMENT PROGRAM HFTD | Wildfire Involving SDG&E Equipment | Strategic Pole Replacement Program (HFTD) | HFTD Tiers 2 & 3 | No | On-going | Annual | 2444670.0972 | 0 | 0 | 0 | 2444670.0972 | 7957999.92 | 8196999.96 | 8442999.96 | 8695999.92 | 7957999.92 | -5513329.8228 | -8196999.96 | -8442999.96 | -8695999.92 | -5513329.8228 | -69.28% | -100% | -100% | -100% | -69.28% | Poles | 40 |  |  |  | 40 | 200 |  |  |  | 200 | -160 | 0 | 0 | 0 | -160 | -80% | 0% | 0% | 0% | -80% | YES | YES | YES | Fewer projects were issued to construction than authorized due to delayed engineering and design. | Fewer projects were issued to construction than authorized due to late start with engineering and design. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1189 in the 2023 WMP filing. The purpose of this project is to target high risk poles located throughout SDG&E service territory for replacement. This will continue SDG&E's efforts in hardening the system within the HFTD. Examples of poles this program will focus on will include but not be limited to, gas-treated poles (may be known as Cellon treatment), steel reinforced and poles that are set in concrete. These identified poles are also nearing the end of their useful life and are known to have a higher failure potential than average. | SDG&E-13-2R-E JTW-135 to JTW-137 CWP 222420
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal HIGH RISK POLE REPLACEMENT PROGRAM HFTD |  |  |  | Yes |  |  | 2444670.0972 | 0 | 0 | 0 | 2444670.0972 | 7957999.92 | 8196999.96 | 8442999.96 | 8695999.92 | 7957999.92 | -5513329.8228 | -8196999.96 | -8442999.96 | -8695999.92 | -5513329.8228 | -69.28% | -100% | -100% | -100% | -69.28% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | LIGHTNING ARRESTOR REPLACEMENT PROGRAM | Electric Infrastructure Integrity | Avian Protection Program | OH Distribution | No | On-going | Annual | 1065808.6687 | 0 | 0 | 0 | 1065808.6687 | 1719000 | 1770999.96 | 1824000 | 1878999.96 | 1719000 | -653191.3313 | -1770999.96 | -1824000 | -1878999.96 | -653191.3313 | -38% | -100% | -100% | -100% | -38% | Poles protected | 774 |  |  |  | 774 | 570 |  |  |  | 570 | 204 | 0 | 0 | 0 | 204 | 35.79% | 0% | 0% | 0% | 35.79% | YES | NO | YES | N/A | Avian Protection units are installed alongside lightning arrestor replacements, driving the program's volume of capital work. In 2024, authorized units were exceeded due to additional scope from configuration of poles identified during the lightning arrestor replacement program and necessary upgrades to bring poles up to standard. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.972 in the 2023 WMP filing. Lightning arrestors are installed on the distribution system throughout the service territory to protect electric power equipment from exceeding thermal insulation ratings in the event of surge voltages due to lightning strikes or other faults. The lightning arrestor enables a surge in the current to be diverted through the arrestor to a ground terminal and protect the insulation and conductors on the distribution system. The lightning arrestor replacement program utilizes new technology to reduce the risk of equipment-related failures and ignitions. Through this process, a new lightning arrestor standard product was introduced that received CAL FIRE approval. The purpose of this project is to replace outdated lightning arrestors with the CAL FIRE-approved lightning arrestors. Embedded within this budget code is also work related to avian protection. SDG&E will bundle these types of jobs together to avoid revisiting the same pole and causing multiple planned outages for customers. The avian protection program seeks to install avian protection equipment or otherwise rearrange distribution poles to prevent avian contact with energized conductor. This is in compliance with the Migratory Bird Treaty Act, Bald and Golden Eagle Protection Act, and codes defined by the California Department of Fish and Game. This will harden the system, reducing the risk of ignition associated with avian contact, improve reliability, and align with Avian Power Line Interaction Committee (APLIC) Guidelines. | SDG&E-13-2R-E JTW-122 to JTW-124 CWP 202820
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | LIGHTNING ARRESTOR REPLACEMENT PROGRAM | Wildfire Involving SDG&E Equipment | Lightning Arrestor Removal/Replacement Program | Tier 2 | No | On-going | Annual | 1238736.1041 | 0 | 0 | 0 | 1238736.1041 | 232999.92 | 240000 | 246999.96 | 253999.92 | 232999.92 | 1005736.1841 | -240000 | -246999.96 | -253999.92 | 1005736.1841 | 431.6% | -100% | -100% | -100% | 431.6% | Lightning arrestors | 763 |  |  |  | 763 | 188 |  |  |  | 188 | 575 | 0 | 0 | 0 | 575 | 305.9% | 0% | 0% | 0% | 305.9% | YES | NO | YES | N/A | Authorized forecasts assumed installation of 1,848 lightning arrestors (924 structures with 2 lightning arrestors installed on each) with 90% in Tier 3 and 10% in Tier 2. Actual replacements were completed for only 705 structures with more work performed in Tier 2 versus Tier 3 based on operational workplan. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.550 in the 2023 WMP filing. Lightning arrestors are installed on the distribution system throughout the service territory to protect electric power equipment from exceeding thermal insulation ratings in the event of surge voltages due to lightning strikes or other faults. The lightning arrestor enables a surge in the current to be diverted through the arrestor to a ground terminal and protect the insulation and conductors on the distribution system. The lightning arrestor replacement program utilizes new technology to reduce the risk of equipment-related failures and ignitions. Through this process, a new lightning arrestor standard product was introduced that received CAL FIRE approval. The purpose of this project is to replace outdated lightning arrestors with the CAL FIRE-approved lightning arrestors. Embedded within this budget code is also work related to avian protection. SDG&E will bundle these types of jobs together to avoid revisiting the same pole and causing multiple planned outages for customers. The avian protection program seeks to install avian protection equipment or otherwise rearrange distribution poles to prevent avian contact with energized conductor. This is in compliance with the Migratory Bird Treaty Act, Bald and Golden Eagle Protection Act, and codes defined by the California Department of Fish and Game. This will harden the system, reducing the risk of ignition associated with avian contact, improve reliability, and align with Avian Power Line Interaction Committee (APLIC) Guidelines. | SDG&E-13-2R-E JTW-122 to JTW-124 CWP 202820
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | LIGHTNING ARRESTOR REPLACEMENT PROGRAM | Wildfire Involving SDG&E Equipment | Lightning Arrestor Removal/Replacement Program | Tier 3 | No | On-going | Annual | 1454168.47 | 0 | 0 | 0 | 1454168.47 | 2059999.92 | 2121999.96 | 2185999.92 | 2251999.92 | 2059999.92 | -605831.45 | -2121999.96 | -2185999.92 | -2251999.92 | -605831.45 | -29.41% | -100% | -100% | -100% | -29.41% | Lightning arrestors | 891 |  |  |  | 891 | 1660 |  |  |  | 1660 | -769 | 0 | 0 | 0 | -769 | -46.33% | 0% | 0% | 0% | -46.33% | YES | NO | YES | N/A | Authorized forecasts assumed installation of 1,848 lightning arrestors (924 structures with 2 lightning arrestors installed on each) with 90% in Tier 3 and 10% in Tier 2. Actual replacements were completed for only 705 structures with more work performed in Tier 2 versus Tier 3 based on operational workplan. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.550 in the 2023 WMP filing. Lightning arrestors are installed on the distribution system throughout the service territory to protect electric power equipment from exceeding thermal insulation ratings in the event of surge voltages due to lightning strikes or other faults. The lightning arrestor enables a surge in the current to be diverted through the arrestor to a ground terminal and protect the insulation and conductors on the distribution system. The lightning arrestor replacement program utilizes new technology to reduce the risk of equipment-related failures and ignitions. Through this process, a new lightning arrestor standard product was introduced that received CAL FIRE approval. The purpose of this project is to replace outdated lightning arrestors with the CAL FIRE-approved lightning arrestors. Embedded within this budget code is also work related to avian protection. SDG&E will bundle these types of jobs together to avoid revisiting the same pole and causing multiple planned outages for customers. The avian protection program seeks to install avian protection equipment or otherwise rearrange distribution poles to prevent avian contact with energized conductor. This is in compliance with the Migratory Bird Treaty Act, Bald and Golden Eagle Protection Act, and codes defined by the California Department of Fish and Game. This will harden the system, reducing the risk of ignition associated with avian contact, improve reliability, and align with Avian Power Line Interaction Committee (APLIC) Guidelines. | SDG&E-13-2R-E JTW-122 to JTW-124 CWP 202820
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal LIGHTNING ARRESTOR REPLACEMENT PROGRAM |  |  |  | Yes |  |  | 3758713.2429 | 0 | 0 | 0 | 3758713.2429 | 4011999.84 | 4132999.92 | 4256999.88 | 4384999.8 | 4011999.84 | -253286.5971 | -4132999.92 | -4256999.88 | -4384999.8 | -253286.5971 | -6.313% | -100% | -100% | -100% | -6.313% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM COVERED CONDUCTOR | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Conductor | Tier 2 | No | On-going | Annual | 43446468.6545 | 0 | 0 | 0 | 43446468.6545 | 16224999.96 | 16224999.96 | 16224999.96 | 16224999.96 | 16224999.96 | 27221468.6945 | -16224999.96 | -16224999.96 | -16224999.96 | 27221468.6945 | 167.8% | -100% | -100% | -100% | 167.8% | Miles hardened | 21 |  |  |  | 21 | 18 |  |  |  | 18 | 3 | 0 | 0 | 0 | 3 | 16.67% | 0% | 0% | 0% | 16.67% | YES | YES | NO | More work was designed and issued to construction in Tier 2 than authorized in the 2024-2027 General Rate Case (GRC). The final GRC decision was issued in late December, which was too late in the year to adjust the workplan. | N/A | Under (U) | Under (U) | Under (U) | Other | NO | SDG&E is now forecasting to complete less miles over the GRC cycle than originally projected. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.455 in the 2023 WMP filing. The Electric System Hardening (ESH) Overhead (OH) Covered Conductor program is focused on hardening SDG&E's overhead distribution facilities within the High Fire Threat District (HFTD) Tier 3, Tier 2, and the Wildland Urban Interface (WUI) by implementing long-term solutions focused on significant reduction of both the fire risk and impact to the public due to Public Safety Power Shutoff (PSPS) events. The primary objective of this program encompasses the rebuilding of the distribution system in fire prone areas with covered primary conductors. The priority and scope of the projects will be dictated by full circuit analysis using the Wildfire Next Generation System (WiNGS) model, and input gathered from operational teams. | SDG&E-13-2R-E JTW-109 to JTW-111 CWP 202850
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM COVERED CONDUCTOR | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Conductor | Tier 3 | No | On-going | Annual | 31515426.5974 | 0 | 0 | 0 | 31515426.5974 | 73915999.92 | 73915999.92 | 73915999.92 | 73915999.92 | 73915999.92 | -42400573.3226 | -73915999.92 | -73915999.92 | -73915999.92 | -42400573.3226 | -57.36% | -100% | -100% | -100% | -57.36% | Miles hardened | 15 |  |  |  | 15 | 82 |  |  |  | 82 | -67 | 0 | 0 | 0 | -67 | -81.71% | 0% | 0% | 0% | -81.71% | YES | YES | YES | Less work was designed and issued to construction in Tier 3 than authorized in the 2024-2027 General Rate Case (GRC). The final GRC decision was issued in late December of 2024, which was too late in the year to ramp-up Covered Conductor hardening work in Tier 3 due to challenges finalizing designs, acquiring land rights, permits, and materials. | Less work was designed and issued to construction in Tier 3 than authorized in the 2024-2027 General Rate Case (GRC). The finalGRC decision was issued in late December of 2024, which was too late in the year to ramp-up Covered Conductor hardening work in Tier 3 due to challenges finalizing designs, acquiring land rights, permits, and materials. | Under (U) | Under (U) | Under (U) | Deferred | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.455 in the 2023 WMP filing. The Electric System Hardening (ESH) Overhead (OH) Covered Conductor program is focused on hardening SDG&E's overhead distribution facilities within the High Fire Threat District (HFTD) Tier 3, Tier 2, and the Wildland Urban Interface (WUI) by implementing long-term solutions focused on significant reduction of both the fire risk and impact to the public due to Public Safety Power Shutoff (PSPS) events. The primary objective of this program encompasses the rebuilding of the distribution system in fire prone areas with covered primary conductors. The priority and scope of the projects will be dictated by full circuit analysis using the Wildfire Next Generation System (WiNGS) model, and input gathered from operational teams. | SDG&E-13-2R-E JTW-109 to JTW-111 CWP 202850
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal OH SYSTEM COVERED CONDUCTOR |  |  |  | Yes |  |  | 74961895.2519 | 0 | 0 | 0 | 74961895.2519 | 90140999.88 | 90140999.88 | 90140999.88 | 90140999.88 | 90140999.88 | -15179104.6281 | -90140999.88 | -90140999.88 | -90140999.88 | -15179104.6281 | -16.84% | -100% | -100% | -100% | -16.84% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM TRADITIONAL HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 3 | No | On-going | Annual | 3254239.347 | 0 | 0 | 0 | 3254239.347 | 6868999.92 | 7074999.96 | 7287000 | 7506000 | 6868999.92 | -3614760.573 | -7074999.96 | -7287000 | -7506000 | -3614760.573 | -52.62% | -100% | -100% | -100% | -52.62% | Miles hardened | 0.5 |  |  |  | 0.5 | 5 |  |  |  | 5 | -4.5 | 0 | 0 | 0 | -4.5 | -90% | 0% | 0% | 0% | -90% | YES | NO | YES | N/A | SDG&E has reevaluated the number of miles planned and has shifted to Covered Conductor scope which has higher risk reduction to phase out Traditional Hardening (Bare Conductor). | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.475 in the 2023 WMP filing. The Electric System Hardening (ESH) Overhead (OH) Traditional Hardening program is focused on hardening SDG&E's overhead distribution facilities within the HFTD Tier 3, Tier 2, and the WUI by implementing long-term solutions focused on significant reduction of both the fire risk and impact to the public due to PSPS events. The primary objective of this program encompasses the rebuilding of the distribution system in fire prone areas with new, stronger bare primary conductors. The priority and scope of the projects will be dictated by full circuit analysis using the WiNGS model, and input gathered from operational teams. | SDG&E-13-2R-E JTW-115 to JTW-117 CWP 202840
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM TRADITIONAL HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 2 | No | On-going | Annual | 321847.8481 | 0 | 0 | 0 | 321847.8481 | 0 | 0 | 0 | 0 | 0 | 321847.8481 | 0 | 0 | 0 | 321847.8481 | 100% | 0% | 0% | 0% | 100% | Miles hardened | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.475 in the 2023 WMP filing. The Electric System Hardening (ESH) Overhead (OH) Traditional Hardening program is focused on hardening SDG&E's overhead distribution facilities within the HFTD Tier 3, Tier 2, and the WUI by implementing long-term solutions focused on significant reduction of both the fire risk and impact to the public due to PSPS events. The primary objective of this program encompasses the rebuilding of the distribution system in fire prone areas with new, stronger bare primary conductors. The priority and scope of the projects will be dictated by full circuit analysis using the WiNGS \ model, and input gathered from operational teams. | SDG&E-13-2R-E JTW-115 to JTW-117 CWP 202840
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal OH SYSTEM TRADITIONAL HARDENING |  |  |  | Yes |  |  | 3576087.1951 | 0 | 0 | 0 | 3576087.1951 | 6868999.92 | 7074999.96 | 7287000 | 7506000 | 6868999.92 | -3292912.7249 | -7074999.96 | -7287000 | -7506000 | -3292912.7249 | -47.94% | -100% | -100% | -100% | -47.94% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OVERHEAD TRANSMISSION FIRE HARDENING (DISTRIBUTION UNDERBUILD) | Wildfire Involving SDG&E Equipment | OH Trans Fire Hardening Dist Underbuild | Tier 2 | No | 11 | 8 | 12448112.2909 | 0 | 0 | 0 | 12448112.2909 | 16791999.96 | 17295000 | 17814000 | 18346999.92 | 16791999.96 | -4343887.6691 | -17295000 | -17814000 | -18346999.92 | -4343887.6691 | -25.87% | -100% | -100% | -100% | -25.87% | Miles hardened | 7 |  |  |  | 7 | 13.8 |  |  |  | 13.8 | -6.8 | 0 | 0 | 0 | -6.8 | -49.28% | 0% | 0% | 0% | -49.28% | YES | NO | YES | N/A | Variance driven by delays in design due to permitting for TL627, multiple re-designs due to overlapping distribution jobs and longer than anticipated design reviews for TL6910, material and permitting constraints for TL694, scope delays with TL691 still in planning and design stages. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.545 in the 2023 WMP filing. Overhead Transmission Fire Hardening is replacing select existing wood poles with new steel poles and replacing aging conductor with new high-strength conductor to fire harden the electric transmission system. These pole and conductor replacements are part of an overall effort to help improve the reliability and integrity of the electric transmission system and to mitigate future potential fire risk. This project will improve the electric transmission system performance during extreme weather conditions such as Santa Ana wind events. When these transmission poles are replaced, the distribution facilities on the pole will need to be replaced or relocated onto the new pole. | SDG&E-13-2R-E JTW-127 to JTW-128 CWP 141400
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OVERHEAD TRANSMISSION FIRE HARDENING (DISTRIBUTION UNDERBUILD) | Wildfire Involving SDG&E Equipment | OH Trans Fire Hardening Dist Underbuild | Tier 3 | No | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 1341000 | 1381999.92 | 1422999.96 | 1465999.92 | 1341000 | -1341000 | -1381999.92 | -1422999.96 | -1465999.92 | -1341000 | -100% | -100% | -100% | -100% | -100% | Miles hardened | 0 |  |  |  | 0 | 1 |  |  |  | 1 | -1 | 0 | 0 | 0 | -1 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | The forecasted units by tranche were allocated based on a high level percentage based on work anticipated in Tier 2 versus Tier 3. The variance is due to the target being determined prior to actual project scope and no actual work was completed in Tier 3 in 2024. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | YES | The authorized scope of work by tranche was allocated based on a high level percentage of work anticipated in Tier 2 versus Tier 3. The actual work completed in 2024 only consisted of Tier 2 scope. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.545 in the 2023 WMP filing. Overhead Transmission Fire Hardening is replacing select existing wood poles with new steel poles and replacing aging conductor with new high-strength conductor to fire harden the electric transmission system. These pole and conductor replacements are part of an overall effort to help improve the reliability and integrity of the electric transmission system and to mitigate future potential fire risk. This project will improve the electric transmission system performance during extreme weather conditions such as Santa Ana wind events. When these transmission poles are replaced, the distribution facilities on the pole will need to be replaced or relocated onto the new pole. | SDG&E-13-2R-E JTW-127 to JTW-128 CWP 141400
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal OVERHEAD TRANSMISSION FIRE HARDENING (DISTRIBUTION UNDERBUILD) |  |  |  | Yes |  |  | 12448112.2909 | 0 | 0 | 0 | 12448112.2909 | 18132999.96 | 18676999.92 | 19236999.96 | 19812999.84 | 18132999.96 | -5684887.6691 | -18676999.92 | -19236999.96 | -19812999.84 | -5684887.6691 | -31.35% | -100% | -100% | -100% | -31.35% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP 10 Year Intrusive T2 | Tier 2 | No | On-going | Annual | 208177.9167 | 0 | 0 | 0 | 208177.9167 | 1482999.96 | 1527000 | 1572999.96 | 1620000 | 1482999.96 | -1274822.0433 | -1527000 | -1572999.96 | -1620000 | -1274822.0433 | -85.96% | -100% | -100% | -100% | -85.96% | Poles replaced | 9 |  |  |  | 9 | 76 |  |  |  | 76 | -67 | 0 | 0 | 0 | -67 | -88.16% | 0% | 0% | 0% | -88.16% | YES | NO | YES | N/A | Pole replacement forecasts are typically developed using an average, of sorts, for historical poles replaced resulting from any given inspection type. The repair work needed resulting from inspections is highly variable and there are often inconsistencies in the number of inspection findings year to year. In 2024, there were fewer pole replacements resulting from intrusive inspections than anticipated. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.483 in the 2023 WMP filing. Short and long term deterioration of equipment can increase the likelihood of asset failure and cause potential risk, including injury, to the public, contractors, and employees. This program is mandated per GO 165 and non-compliance poses risk of regulatory action, including fines. All electric distribution facilities are visually patrolled on an annual basis in urban and rural areas, and inspected in detail every three, five, or ten years depending on equipment type. Conditions found during these inspections may require repair or replacement of equipment that is no longer serviceable. The costs included within this workpaper are the capital pole replacements/reinforcements completed as a result of the various asset inspection programs discussed in 1WM004. | SDG&E-13-2R-E JTW-138 to JTW-139 CWP 02390
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP 5 Year Detailed Inspections T1-T2 | Tier 2 | No | On-going | Annual | 3747202.6698 | 0 | 0 | 0 | 3747202.6698 | 4257000 | 4384999.92 | 4516999.92 | 4651999.92 | 4257000 | -509797.3302 | -4384999.92 | -4516999.92 | -4651999.92 | -509797.3302 | -11.98% | -100% | -100% | -100% | -11.98% | Poles replaced | 153 |  |  |  | 153 | 217 |  |  |  | 217 | -64 | 0 | 0 | 0 | -64 | -29.49% | 0% | 0% | 0% | -29.49% | YES | NO | YES | N/A | Pole replacement forecasts are typically developed using an average, of sorts, for historical poles replaced resulting from any given inspection type. The repair work needed resulting from inspections is highly variable and there are often inconsistencies in the number of inspection findings year to year. In 2024, there were fewer pole replacements resulting from detailed inspections than anticipated. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.478 in the 2023 WMP filing. Short and long term deterioration of equipment can increase the likelihood of asset failure and cause potential risk, including injury, to the public, contractors, and employees. This program is mandated per GO 165 and non-compliance poses risk of regulatory action, including fines. All electric distribution facilities are visually patrolled on an annual basis in urban and rural areas, and inspected in detail every three, five, or ten years depending on equipment type. Conditions found during these inspections may require repair or replacement of equipment that is no longer serviceable. The costs included within this workpaper are the capital pole replacements/reinforcements completed as a result of the various asset inspection programs discussed in 1WM004. | SDG&E-13-2R-E JTW-138 to JTW-139 CWP 02390
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP 5 Year Detailed Inspections T1-T2 | Tier 3 | No | On-going | Annual | 4059469.5606 | 0 | 0 | 0 | 4059469.5606 | 3285000 | 3382999.92 | 3483999.96 | 3588999.96 | 3285000 | 774469.5606 | -3382999.92 | -3483999.96 | -3588999.96 | 774469.5606 | 23.58% | -100% | -100% | -100% | 23.58% | Poles replaced | 165 |  |  |  | 165 | 168 |  |  |  | 168 | -3 | 0 | 0 | 0 | -3 | -1.786% | 0% | 0% | 0% | -1.786% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.478 in the 2023 WMP filing. Short and long term deterioration of equipment can increase the likelihood of asset failure and cause potential risk, including injury, to the public, contractors, and employees. This program is mandated per GO 165 and non-compliance poses risk of regulatory action, including fines. All electric distribution facilities are visually patrolled on an annual basis in urban and rural areas, and inspected in detail every three, five, or ten years depending on equipment type. Conditions found during these inspections may require repair or replacement of equipment that is no longer serviceable. The costs included within this workpaper are the capital pole replacements/reinforcements completed as a result of the various asset inspection programs discussed in 1WM004. | SDG&E-13-2R-E JTW-138 to JTW-139 CWP 02390
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP Annual Patrol T1-T2 | Tier 2 | No | On-going | Annual | 1873601.3242 | 0 | 0 | 0 | 1873601.3242 | 469999.92 | 483999.96 | 498999.96 | 513999.96 | 469999.92 | 1403601.4042 | -483999.96 | -498999.96 | -513999.96 | 1403601.4042 | 298.6% | -100% | -100% | -100% | 298.6% | Poles replaced | 75 |  |  |  | 75 | 24 |  |  |  | 24 | 51 | 0 | 0 | 0 | 51 | 212.5% | 0% | 0% | 0% | 212.5% | YES | NO | YES | N/A | Pole replacement forecasts are typically developed using an average, of sorts, for historical poles replaced resulting from any given inspection type. The repair work needed resulting from inspections is highly variable and there are often inconsistencies in the number of inspection findings year to year. In 2024, there were more pole replacements resulting from patrol inspections than anticipated. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.488 in the 2023 WMP filing. Short and long term deterioration of equipment can increase the likelihood of asset failure and cause potential risk, including injury, to the public, contractors, and employees. This program is mandated per GO 165 and non-compliance poses risk of regulatory action, including fines. All electric distribution facilities are visually patrolled on an annual basis in urban and rural areas, and inspected in detail every three, five, or ten years depending on equipment type. Conditions found during these inspections may require repair or replacement of equipment that is no longer serviceable. The costs included within this workpaper are the capital pole replacements/reinforcements completed as a result of the various asset inspection programs discussed in 1WM004. | SDG&E-13-2R-E JTW-138 to JTW-139 CWP 02390
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP Annual Patrol T1-T2 | Tier 3 | No | On-going | Annual | 520444.8074 | 0 | 0 | 0 | 520444.8074 | 396000 | 408000 | 420000 | 432999.96 | 396000 | 124444.8074 | -408000 | -420000 | -432999.96 | 124444.8074 | 31.43% | -100% | -100% | -100% | 31.43% | Poles replaced | 20 |  |  |  | 20 | 20 |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.488 in the 2023 WMP filing. Short and long term deterioration of equipment can increase the likelihood of asset failure and cause potential risk, including injury, to the public, contractors, and employees. This program is mandated per GO 165 and non-compliance poses risk of regulatory action, including fines. All electric distribution facilities are visually patrolled on an annual basis in urban and rural areas, and inspected in detail every three, five, or ten years depending on equipment type. Conditions found during these inspections may require repair or replacement of equipment that is no longer serviceable. The costs included within this workpaper are the capital pole replacements/reinforcements completed as a result of the various asset inspection programs discussed in 1WM004. | SDG&E-13-2R-E JTW-138 to JTW-139 CWP 02390
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection HFTD Tier 3 Inspections T1-T2 | Tier 3 | No | On-going | Annual | 0 | 0 | 0 | 0 | 0 | 2472000 | 2545999.92 | 2622000 | 2700999.96 | 2472000 | -2472000 | -2545999.92 | -2622000 | -2700999.96 | -2472000 | -100% | -100% | -100% | -100% | -100% | Poles replaced | 0 |  |  |  | 0 | 126 |  |  |  | 126 | -126 | 0 | 0 | 0 | -126 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Additional HFTD Tier 3 distribution pole inspections were conducted from 2010 through 2016 as a result of a settlement agreement adopted in D.10‐04‐047. In 2017, SDG&E decided to proactively continue the HFTD Tier 3 Quality Assessment/Quality Control (QA/QC) inspections as part of its regular inspection program. However, in an effort to implement risk-informed inspections, SDG&E discontinued the HFTD Tier 3 QA/QC inspections in its current form and is instead performing risk-informed drone inspections. | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | This workpaper was included in the Asset Management and Inspections GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.551 in the 2023 WMP filing. Short and long term deterioration of equipment can increase the likelihood of asset failure and cause potential risk, including injury, to the public, contractors, and employees. This program is mandated per GO 165 and non-compliance poses risk of regulatory action, including fines. All electric distribution facilities are visually patrolled on an annual basis in urban and rural areas, and inspected in detail every three, five, or ten years depending on equipment type. Conditions found during these inspections may require repair or replacement of equipment that is no longer serviceable. The costs included within this workpaper are the capital pole replacements/reinforcements completed as a result of the various asset inspection programs discussed in 1WM004. | SDG&E-13-2R-E JTW-138 to JTW-139 CWP 02390
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal POLE REPLACEMENT AND REINFORCEMENT IN HFTD |  |  |  | Yes |  |  | 10408896.2787 | 0 | 0 | 0 | 10408896.2787 | 12362999.88 | 12732999.72 | 13114999.8 | 13508999.76 | 12362999.88 | -1954103.6013 | -12732999.72 | -13114999.8 | -13508999.76 | -1954103.6013 | -15.81% | -100% | -100% | -100% | -15.81% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | PSPP ALL HAZARDS & K2 | Wildfire Involving SDG&E Equipment | PSPP ALL HAZARDS & K2 | N/A | No | Emergent | 2 | 9801017.3364 | 0 | 0 | 0 | 9801017.3364 | 0 | 0 | 0 | 0 | 0 | 9801017.3364 | 0 | 0 | 0 | 9801017.3364 | 100% | 0% | 0% | 0% | 100% | The workpaper contains activities to implement and evolve the Public Safety Partner Portal and mobile app into a one-stop-shop solution for Partners to access All-hazard related information to implement All-hazard solutions. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | Variance due to emergent need to implement the Public Safety Partner Portal and mobile app into a one-stop-shop solution for Partners to access All-hazard related information to implement All-hazard solutions, to automate notifications to Partners and facilitate reporting customization. | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The workpaper contains activities to implement and evolve the Public Safety Partner Portal and mobile app into a one-stop-shop solution for Partners to access All-hazard related information to implement All-hazard solutions. | N/A
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal PSPP ALL HAZARDS & K2 |  |  |  | Yes |  |  | 9801017.3364 | 0 | 0 | 0 | 9801017.3364 | 0 | 0 | 0 | 0 | 0 | 9801017.3364 | 0 | 0 | 0 | 9801017.3364 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | PUBLIC SAFETY POWER SHUTOFF (PSPS) ENGINEERING ENHANCEMENTS | Wildfire Involving SDG&E Equipment | PSPS Sectionalizing | Tier 2 | No | On-going | Annual | 1087264.1267 | 0 | 0 | 0 | 1087264.1267 | 1965000 | 2023999.92 | 2085000 | 2148000 | 1965000 | -877735.8733 | -2023999.92 | -2085000 | -2148000 | -877735.8733 | -44.67% | -100% | -100% | -100% | -44.67% | Switches installed | 9 |  |  |  | 9 | 10 |  |  |  | 10 | -1 | 0 | 0 | 0 | -1 | -10% | 0% | 0% | 0% | -10% | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.461 in the 2023 WMP filing The purpose of this project is to add distribution sectionalizing devices in the HFTD to minimize customer impacts during PSPS events. Additional sectionalizing devices allow for the use of PSPS to be targeted to only the areas with extreme weather conditions, minimizing the number of customers impacted by PSPS. Communication infrastructure includes site-specific designs and procurement of engineered steel poles and material, siting surveys, land rights, environmental analysis, community outreach, and community planning. This project will allow for the implementation of a private LTE network that can be expanded in stages , as needed, to provide communications capability in traditionally difficult to reach locations. | SDG&E-13-2R-E JTW-129 to JTW-130 CWP 192450
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | PUBLIC SAFETY POWER SHUTOFF (PSPS) ENGINEERING ENHANCEMENTS | Wildfire Involving SDG&E Equipment | PSPS Sectionalizing | Tier 3 | No | On-going | Annual | 1087264.1267 | 0 | 0 | 0 | 1087264.1267 | 0 | 0 | 0 | 0 | 0 | 1087264.1267 | 0 | 0 | 0 | 1087264.1267 | 100% | 0% | 0% | 0% | 100% | Switches installed | 9 |  |  |  | 9 | 0 |  |  |  | 0 | 9 | 0 | 0 | 0 | 9 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | Variance driven by completion of additional service restorer disconnect replacements, which were less costly than a typical PSPS switch installation. By replacing them, the SCADA team was able to test SCADA functionality of the service restorers which would be used during a PSPS event. | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.461 in the 2023 WMP filing. The purpose of this project is to add distribution sectionalizing devices in the HFTD to minimize customer impacts during PSPS events. Additional sectionalizing devices allow for the use of PSPS to be targeted to only the areas with extreme weather conditions, minimizing the number of customers impacted by PSPS. | SDG&E-13-2R-E JTW-129 to JTW-130 CWP 192450
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal PUBLIC SAFETY POWER SHUTOFF (PSPS) ENGINEERING ENHANCEMENTS |  |  |  | Yes |  |  | 2174528.2534 | 0 | 0 | 0 | 2174528.2534 | 1965000 | 2023999.92 | 2085000 | 2148000 | 1965000 | 209528.2534 | -2023999.92 | -2085000 | -2148000 | 209528.2534 | 10.66% | -100% | -100% | -100% | 10.66% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | [22 empty] | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STRATEGIC UNDERGROUNDING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 2 | No | On-going | Annual | 49184147.1968 | 0 | 0 | 0 | 49184147.1968 | 38314999.92 | 43881999.96 | 44298999.96 | 44856000 | 38314999.92 | 10869147.2768 | -43881999.96 | -44298999.96 | -44856000 | 10869147.2768 | 28.37% | -100% | -100% | -100% | 28.37% | Miles UG | 26 |  |  |  | 26 | 13 |  |  |  | 13 | 13 | 0 | 0 | 0 | 13 | 100% | 0% | 0% | 0% | 100% | YES | YES | YES | Spend and number of completed units were based on target of 125 miles for the year. The the final GRC decision was issued in late December 2024, which was too late in the year to adjust the workplan. | Spend and number of completed units were based on target of 125 miles for the year. The the final GRC decision was issued in late December 2024, which was too late in the year to adjust the workplan. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.473 in the 2023 WMP filing. Reduce the risk of wildfire, PSPS, and overhead distribution infrastructure failures caused by foreign object contact, wind, extreme weather conditions, and other external triggers by converting overhead infrastructure to underground. The project will install new underground electric distribution facilities, and remove from service existing overhead electric facilities. | SDG&E-13-2R-E JTW-132 to JTW-135 CWP 192460
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STRATEGIC UNDERGROUNDING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 3 | No | On-going | Annual | 164659972.5495 | 0 | 0 | 0 | 164659972.5495 | 65241000 | 74718000 | 75429000 | 76377000 | 65241000 | 99418972.5495 | -74718000 | -75429000 | -76377000 | 99418972.5495 | 152.4% | -100% | -100% | -100% | 152.4% | Miles UG | 86 |  |  |  | 86 | 22 |  |  |  | 22 | 64 | 0 | 0 | 0 | 64 | 290.9% | 0% | 0% | 0% | 290.9% | YES | YES | YES | Spend and number of completed units were based on target of 125 miles for the year. The the final GRC decision was issued in late December 2024, which was too late in the year to adjust the workplan. | Spend and number of completed units were based on target of 125 miles for the year. The the final GRC decision was issued in late December 2024, which was too late in the year to adjust the workplan. | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.473 in the 2023 WMP filing. Reduce the risk of wildfire, PSPS, and overhead distribution infrastructure failures caused by foreign object contact, wind, extreme weather conditions, and other external triggers by converting overhead infrastructure to underground. The project will install new underground electric distribution facilities, and remove from service existing overhead electric facilities. | SDG&E-13-2R-E JTW-132 to JTW-135 CWP 192460
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal STRATEGIC UNDERGROUNDING |  |  |  | Yes |  |  | 213844119.7463 | 0 | 0 | 0 | 213844119.7463 | 103555999.92 | 118599999.96 | 119727999.96 | 121233000 | 103555999.92 | 110288119.8263 | -118599999.96 | -119727999.96 | -121233000 | 110288119.8263 | 106.5% | -100% | -100% | -100% | 106.5% | [21 empty] | YES | YES | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | TWIN ENGINE MEDIUM LIFT HELICOPTER | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 3 | No | 2 | 4 | 767439.27 | 0 | 0 | 0 | 767439.27 | 0 | 0 | 0 | 0 | 0 | 767439.27 | 0 | 0 | 0 | 767439.27 | 100% | 0% | 0% | 0% | 100% | The workpaper contains activities related to firefighting modifications for the helicopter. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Grid Operations and Protocols GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.557 in the 2023 WMP filing. The Bell 412 helicopter is a twin-engine medium lift helicopter that provides an increase in lifting capability for construction-related loads. The Bell 412 will be outfitted with equipment necessary for firefighting capabilities. | SDG&E-13-2R-E JTW-150 to JTW-152 CWP 212560
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal TWIN ENGINE MEDIUM LIFT HELICOPTER |  |  |  | Yes |  |  | 767439.27 | 0 | 0 | 0 | 767439.27 | 0 | 0 | 0 | 0 | 0 | 767439.27 | 0 | 0 | 0 | 767439.27 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WILDFIRE AND CLIMATE RESILIENCE CENTER | Wildfire Involving SDG&E Equipment | Emergency Management Operations | N/A | No | 5 | 6 | 784335.3742 | 0 | 0 | 0 | 784335.3742 | 0 | 0 | 0 | 0 | 0 | 784335.3742 | 0 | 0 | 0 | 784335.3742 | 100% | 0% | 0% | 0% | 100% | The workpaper contains activities related to the design, construction, logistics, and project management for the buildout of the Wildfire & Climate Resilience Center (WCRC). The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Expanded | NO | N/A | This workpaper was included in the Emergency Planning and Preparedness GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.1008 in the 2023 WMP filing. Rapidly changing climate conditions are changing the way we maintain and operate the electric system, and the WCRC will be a physical space that is committed to the climate resilience of our organization and the communities we serve. This includes housing the Wildfire Science and Innovation Lab which collaborates with academia to advance climate science, and this will also be a resilience center focused on fostering community partnerships and educating stakeholders in the wildfire and climate community. This facility will also serve as a great venue to train SDG&E employees on the importance of wildfire safety, emergency preparedness, sustainability and climate resilience. Importantly, this space will also house the primary EOC for the organization and will be the central response hub for the organization when emergencies occur. Lastly, this will serve as a centralized workspace for all employees working in Wildfire Mitigation, Emergency Management, Fire Science and Climate Adaptation, increasing employee collaboration and innovation in this space. | SDG&E-13-2R-E JTW-161 to JTW-163 CWP 197800
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WILDFIRE AND CLIMATE RESILIENCE CENTER |  |  |  | Yes |  |  | 784335.3742 | 0 | 0 | 0 | 784335.3742 | 0 | 0 | 0 | 0 | 0 | 784335.3742 | 0 | 0 | 0 | 784335.3742 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WIRELESS FAULT INDICATORS | Wildfire Involving SDG&E Equipment | Wireless Fault Indicators | Tier 2 | No | On-going | Annual | 1448.6828 | 0 | 0 | 0 | 1448.6828 | 666999.96 | 687000 | 706999.92 | 729000 | 666999.96 | -665551.2772 | -687000 | -706999.92 | -729000 | -665551.2772 | -99.78% | -100% | -100% | -100% | -99.78% | Wireless fault indicators installed | 0 |  |  |  | 0 | 400 |  |  |  | 400 | -400 | 0 | 0 | 0 | -400 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | SDG&E discontinued this program due to manufacturer upgrades to the currently used fault indicators. The upgraded equipment requires additional communication requirements not currently employed. SDG&E utilizes SCADA devices and existing fault indicators to provide situational awareness and guide first responders to the likely location of a fault. | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | This workpaper was included in the Situational Awareness and Forecasting GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.449 in the 2023 WMP filing. The purpose of this program is to install Wireless Fault Indicators (WFIs) which will be used to monitor overhead and underground lines and locate faults more efficiently and accurately . WFIs, typically mounted on conductors or in underground vaults, cause a state change on a mechanical target flag, LED, or remote indication device that indicates a fault on the system. When coupled with the On-Ramp Wireless system, the WFI will communicate information to distribution system operators. This allows the operators to dispatch electric troubleshooters closer to the exact fault location to more quickly identify and isolate the fault and begin service restorations. This program helps to improve reliability and find faults on the system more quickly, minimizing the consequence of a fire should it occur. Deploying new network devices throughout the HFTD will strengthen and modernize Low Power Communication Network (LPCN) coverage and reliability. | SDG&E-13-2R-E JTW-100 to JTW-102 CWP 112530
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WIRELESS FAULT INDICATORS | Wildfire Involving SDG&E Equipment | Wireless Fault Indicators | Tier 3 | No | On-going | Annual | 1448.6828 | 0 | 0 | 0 | 1448.6828 | 666999.96 | 687000 | 708000 | 727999.92 | 666999.96 | -665551.2772 | -687000 | -708000 | -727999.92 | -665551.2772 | -99.78% | -100% | -100% | -100% | -99.78% | Wireless fault indicators installed | 0 |  |  |  | 0 | 400 |  |  |  | 400 | -400 | 0 | 0 | 0 | -400 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | SDG&E discontinued this program due to manufacturer upgrades to the currently used fault indicators. The upgraded equipment requires additional communication requirements not currently employed. SDG&E utilizes SCADA devices and existing fault indicators to provide situational awareness and guide first responders to the likely location of a fault. | Under (U) | Under (U) | Under (U) | Canceled | NO | N/A | This workpaper was included in the Situational Awareness and Forecasting GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.449 in the 2023 WMP filing. The purpose of this program is to install Wireless Fault Indicators (WFIs) which will be used to monitor overhead and underground lines and locate faults more efficiently and accurately . WFIs, typically mounted on conductors or in underground vaults, cause a state change on a mechanical target flag, LED, or remote indication device that indicates a fault on the system. When coupled with the On-Ramp Wireless system, the WFI will communicate information to distribution system operators. This allows the operators to dispatch electric troubleshooters closer to the exact fault location to more quickly identify and isolate the fault and begin service restorations. This program helps to improve reliability and find faults on the system more quickly, minimizing the consequence of a fire should it occur. Deploying new network devices throughout the HFTD will strengthen and modernize Low Power Communication Network (LPCN) coverage and reliability. | SDG&E-13-2R-E JTW-100 to JTW-102 CWP 112530
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WIRELESS FAULT INDICATORS |  |  |  | Yes |  |  | 2897.3656 | 0 | 0 | 0 | 2897.3656 | 1333999.92 | 1374000 | 1414999.92 | 1456999.92 | 1333999.92 | -1331102.5544 | -1374000 | -1414999.92 | -1456999.92 | -1331102.5544 | -99.78% | -100% | -100% | -100% | -99.78% | [21 empty] | YES | NO | [7 empty] | YES
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP ADVANCED ANALYTICS | Wildfire Involving SDG&E Equipment | Centralized Repository for Data | N/A | No | On-going | Annual | 4744997.1444 | 0 | 0 | 0 | 4744997.1444 | 5007000 | 5157000 | 5311999.92 | 5470999.92 | 5007000 | -262002.8556 | -5157000 | -5311999.92 | -5470999.92 | -262002.8556 | -5.233% | -100% | -100% | -100% | -5.233% | The workpaper contains activities to build out machine learning models and pipelines and develop advanced analytics/predictive use cases to proactively identify, reduce and manage wildfire-related risk. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Data Governance GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.519 in the 2023 WMP filing. The purpose of the WMP Advanced Analytics project is to increase the capacity and skills to enable and develop advanced analytics and predictive use cases to support ongoing WMP and Risk Management initiatives. This project includes the build out of a data lake and machine learning pipeline to leverage readily-available cloud machine learning and artificial intelligence capabilities. | SDG&E-13-2R-E JTW-154 to JTW-155 CWP 218840
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP ADVANCED ANALYTICS |  |  |  | Yes |  |  | 4744997.1444 | 0 | 0 | 0 | 4744997.1444 | 5007000 | 5157000 | 5311999.92 | 5470999.92 | 5007000 | -262002.8556 | -5157000 | -5311999.92 | -5470999.92 | -262002.8556 | -5.233% | -100% | -100% | -100% | -5.233% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP ASSET AND WORK MANAGEMENT ANALYTICS | Wildfire Involving SDG&E Equipment | WMP ASSET AND WORK MANAGEMENT ANALYTICS | N/A | No | Emergent | 1 | 1139326.7816 | 0 | 0 | 0 | 1139326.7816 | 0 | 0 | 0 | 0 | 0 | 1139326.7816 | 0 | 0 | 0 | 1139326.7816 | 100% | 0% | 0% | 0% | 100% | The workpaper contains activities to integrate asset, risk event, outage, and maintenance and inspection data including build consolidated views, data catalogues, data cleansing and data governance for asset data. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The workpaper contains activities to integrate asset, risk event, outage, and maintenance and inspection data including build consolidated views, data catalogues, data cleansing and data governance for asset data. | N/A
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP ASSET AND WORK MANAGEMENT ANALYTICS |  |  |  | Yes |  |  | 1139326.7816 | 0 | 0 | 0 | 1139326.7816 | 0 | 0 | 0 | 0 | 0 | 1139326.7816 | 0 | 0 | 0 | 1139326.7816 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP ASSET INVESTMENT PRIORITIZATION | Asset Management | Asset Management | N/A | No | 5 | 5 | 677983.1677 | 0 | 0 | 0 | 677983.1677 | 2371999.92 | 2442999.96 | 2515999.92 | 2590999.92 | 2371999.92 | -1694016.7523 | -2442999.96 | -2515999.92 | -2590999.92 | -1694016.7523 | -71.42% | -100% | -100% | -100% | -71.42% | The workpaper contains activities to replace existing application to use a new value-based decision model approach for capital investment decisions and/or prioritization. The variety of work activities in this category makes it infeasible to identify a single unit of measurement | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Completed | NO | N/A | This workpaper was included in the Data Governance GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.523 in the 2023 WMP filing. The current Asset Investment Planning tool (REVEAL) has reached the end of its useful life therefore this project is to replace REVEAL and implement a consistent value-based decision model approach, and in alignment with the Company's strategic plan using Copperleaf's Asset Investment Planning and Management (AIPM) tool, which will utilize the enterprise-level value framework to optimize the capital project portfolio for Electric Transmission , Substations, and Distribution. | SDG&E-13-2R-E JTW-155 to JTW-157 CWP 218770
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP ASSET INVESTMENT PRIORITIZATION |  |  |  | Yes |  |  | 677983.1677 | 0 | 0 | 0 | 677983.1677 | 2371999.92 | 2442999.96 | 2515999.92 | 2590999.92 | 2371999.92 | -1694016.7523 | -2442999.96 | -2515999.92 | -2590999.92 | -1694016.7523 | -71.42% | -100% | -100% | -100% | -71.42% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP CENTRALIZED REPOSITORY FOR DATA | Wildfire Involving SDG&E Equipment | Centralized Repository for Data | N/A | No | 8 | 5 | 6086216.0367 | 0 | 0 | 0 | 6086216.0367 | 6712999.92 | 6913999.92 | 7120999.92 | 7335000 | 6712999.92 | -626783.8833 | -6913999.92 | -7120999.92 | -7335000 | -626783.8833 | -9.337% | -100% | -100% | -100% | -9.337% | The workpaper contains activities to build out central data repository, reporting and analytics solutions across variety of WMP related initiatives. Project includes ingestion of raw data into central repository from multiple source systems, development of logical views, visualizations and advanced analytics models to provide actionable insights. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A | This workpaper was included in the Data Governance GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.519 and .523 in the 2023 WMP filing. This budget code contains projects related to the centralization of Wildfire Mitigation Plan (WMP) data and utilizing that data to advance asset management capabilities, develop advanced analytics, and automate WMP-related reporting. The Centralized Repository for Data will centralize data from 10+ business units into the central repository, with a primary focus of automating aggregated summary metrics required for the WMP Performance Metrics (Tables 1-12). Business units include: GIS, Electric Distribution, Electric Transmission, Fire Science and Climate Adaptation, Reliability, Safety, and Vegetation Management. Raw data will be gathered and centralized from multiple sources. The project will work in close collaboration with WMP Data Governance for data auditability and initial WMP data catalog development . Utilizing this combined data, asset management capabilities will be enhanced to develop a centralized repository for Electric Asset data, asset health and risk models for critical distribution and transmission assets, and visualization for end users to interact with the data. The Office of Energy Infrastructure Safety (OEIS) requires submission of a Quarterly Data Report (QDR) utilizing a defined data taxonomy and schema for many feature classes to use for future WMP data analysis . This project will provide an automated solution to gather the required data, convert the data to geospatial format, and create the QDR for submission to OEIS. | SDG&E-13-2R-E JTW-152 to JTW-154 CWP 208910
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP CENTRALIZED REPOSITORY FOR DATA |  |  |  | Yes |  |  | 6086216.0367 | 0 | 0 | 0 | 6086216.0367 | 6712999.92 | 6913999.92 | 7120999.92 | 7335000 | 6712999.92 | -626783.8833 | -6913999.92 | -7120999.92 | -7335000 | -626783.8833 | -9.337% | -100% | -100% | -100% | -9.337% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP CIRCUIT RISK INDEX | Wildfire Involving SDG&E Equipment | Fire Science and Climate Adaptation Department | N/A | No | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 526999.92 | 543000 | 558999.96 | 576000 | 526999.92 | -526999.92 | -543000 | -558999.96 | -576000 | -526999.92 | -100% | -100% | -100% | -100% | -100% | The workpaper contains multiple components of creation of a Circuit Risk Index (CRI) that would allow quick consolidation of multiple data points into a single index that could be quickly interpreted. Data points that could be incorporated to create this Circuit Risk Index include but are not limited to circuit spans subject to temporary construction/configuration that have mechanically de-rated facilities, inspection infractions, asset condition, age, or fire hardening structures, overloaded structures, outage history, network assets, electric system conditions and characteristics, and at risk parameters. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Under (U) | Under (U) | Under (U) | Other | YES | SDG&E’s Circuit Risk Index (CRI) model evolved into the WiNGS cloud-based risk models, WiNGS-Planning and WiNGS-Ops Visualization Platforms and advanced analytics to advance WMP reporting. These costs will be incurred in the GRC workpapers CWP 218840 and CWP 208910. | The purpose of this project is to develop new machine learning models to predict failures and ignitions for different asset types and drivers of ignitions. The models developed in this project will be used to inform both operational and long-term decision making. The purpose of this project is to develop new machine learning models to predict failures and ignitions for different asset types and drivers of ignitions. The models developed in this project will be used to inform both operational and long-term decision making. Several models will be developed for different asset types (poles, conductors, transformers, etc.) as well as other ignition drivers (vegetation, vehicle, balloon contact, etc.). These models will then be aggregated up to a single model such as WiNGS and/or WiNGS-Ops as an enhancement to those tools. In addition to model development, there will be an effort to run these models in the cloud to enable more dynamic updates to these models. | SDG&E-13-2R-E JTW-102 to JTW-103 CWP 208770
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP CIRCUIT RISK INDEX |  |  |  | Yes |  |  | 0 | 0 | 0 | 0 | 0 | 526999.92 | 543000 | 558999.96 | 576000 | 526999.92 | -526999.92 | -543000 | -558999.96 | -576000 | -526999.92 | -100% | -100% | -100% | -100% | -100% | [21 empty] | YES | NO | [7 empty] | YES
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP MICROGRIDS | Wildfire Involving SDG&E Equipment | Microgrids | Tier 2 | No | 6 | 6 | 1276576.7271 | 0 | 0 | 0 | 1276576.7271 | 3009000 | 3099000 | 3192000 | 3288000 | 3009000 | -1732423.2729 | -3099000 | -3192000 | -3288000 | -1732423.2729 | -57.57% | -100% | -100% | -100% | -57.57% | Microgrids | 0 |  |  |  | 0 | 8 |  |  |  | 8 | -8 | 0 | 0 | 0 | -8 | -100% | 0% | 0% | 0% | -100% | YES | NO | YES | N/A | Work on Drones, CWP 202480, was prioritized in 2024 to complete higher than anticipated scope of pole repairs and replacements associated with infractions identified during drone inspections. Off-grid power solutions work is now expected to resume in 2028. | Under (U) | Under (U) | Under (U) | Other | NO | SDG&E is now forecasting to complete fewer microgrid projects over the GRC cycle than originally projected. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.462 in the 2023 WMP filing. The purpose of this project is to increase renewable back-up power infrastructure by building microgrids that can keep customers energized during PSPS events. Microgrids are constructed using solar generation and battery storage to enable the local critical infrastructure to stay energized during PSPS events. | SDG&E-13-2R-E JTW-124 to JTW-127 CWP 192490
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP MICROGRIDS | Wildfire Involving SDG&E Equipment | Microgrids | Tier 3 | No | 6 | 6 | 5819198.1507 | 0 | 0 | 0 | 5819198.1507 | 0 | 0 | 0 | 0 | 0 | 5819198.1507 | 0 | 0 | 0 | 5819198.1507 | 100% | 0% | 0% | 0% | 100% | Microgrids | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | YES | YES | NO | Cameron Corners and Shelter Valley were originally forecasted to be completed and placed into service in 2022 and 2023, respectively. Due to scope delays, the in service dates for both projects were shifted beyond 2023. Costs reflect the removal and replacement of battery energy storage equipment and its associated below grade and above grade infrastructure and network technology for Cameron Corners, plus engineering, designing and construction of civil and site development grading work for Shelter Valley. | N/A | Over (O) | Over (O) | Over (O) | Other | NO | Cameron Corners and Shelter Valley were originally forecasted to be completed and placed into service in 2022 and 2023, respectively. Due to scope delays, the in service dates for both projects were shifted beyond 2023. | This workpaper was included in the Grid Design and System Hardening GRC category within the Wildfire Mitigation and Vegetation Management witness area. This workpaper can also be mapped to Tracking ID WMP.462 in the 2023 WMP filing. The purpose of this project is to increase renewable back-up power infrastructure by building microgrids that can keep customers energized during PSPS events. Microgrids are constructed using solar generation and battery storage to enable the local critical infrastructure to stay energized during PSPS events. | SDG&E-13-2R-E JTW-124 to JTW-127 CWP 192490
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP MICROGRIDS |  |  |  | Yes |  |  | 7095774.8778 | 0 | 0 | 0 | 7095774.8778 | 3009000 | 3099000 | 3192000 | 3288000 | 3009000 | 4086774.8778 | -3099000 | -3192000 | -3288000 | 4086774.8778 | 135.8% | -100% | -100% | -100% | 135.8% | [21 empty] | YES | NO | [7 empty] | NO
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP OPERATION MEGAPHONE | Wildfire Involving SDG&E Equipment | WMP OPERATION MEGAPHONE | N/A | No | Emergent | 2 | 366795 | 0 | 0 | 0 | 366795 | 0 | 0 | 0 | 0 | 0 | 366795 | 0 | 0 | 0 | 366795 | 100% | 0% | 0% | 0% | 100% | The workpaper contains activities to enhance customer notification and increase capacity for customer notifications voice calling and text messaging to full-service territory. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | Over (O) | Over (O) | Over (O) | Emergent | NO | N/A | The workpaper contains activities to enhance customer notification and increase capacity for customer notifications voice calling and text messaging to full-service territory. | N/A
Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SubTotal WMP OPERATION MEGAPHONE |  |  |  | Yes |  |  | 366795 | 0 | 0 | 0 | 366795 | 0 | 0 | 0 | 0 | 0 | 366795 | 0 | 0 | 0 | 366795 | 100% | 0% | 0% | 0% | 100% | [21 empty] | YES | NO | [7 empty] | NO

## EOED-C-B
SDG&E ELECTRIC DISTRIBUTION Capital - Balanced
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | ELECTRIC DISTRIBUTION | ELECTRIC DISTRIBUTION |  |  |  | Yes |  |  | 232945237.2412 | 0 | 0 | 0 | 232945237.2412 | 187289999.76 | 192908999.64 | 198696999.72 | 204656999.76 | 187289999.76 | 45655237.4812 | -192908999.64 | -198696999.72 | -204656999.76 | 45655237.4812 | 24.38% | -100% | -100% | -100% | 24.38%
Capital | ELECTRIC DISTRIBUTION | CONTRACT ADMINISTRATION POOL - ELEC | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 9965353.5348 | 0 | 0 | 0 | 9965353.5348 | 54904999.92 | 56551999.92 | 58248999.96 | 59995999.92 | 54904999.92 | -44939646.3852 | -56551999.92 | -58248999.96 | -59995999.92 | -44939646.3852 | -81.85% | -100% | -100% | -100% | -81.85% | The Contract Administration (CA) pool consists of those expenses necessary for the administration of projects that are performed by contractors for SDG&E. The expenses to this pool consist of labor for Contract Administrators and support personnel, as well as the associated non-labor support costs such as office and field supplies. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The variance is due to less contractor hours in 2024 than forecasted. | N/A | On Target (T) | On Target (T) | Under (U) | Proceeding as Planned | NO | N/A | The CA Pool consists of those expenses necessary for the administration of projects that are performed by contractors for SDG&E. Due to the volume of capital work that takes place on the electric distribution system, the most effective and efficient way to allocate the contract administration costs is through the use of the CA Pool . It is not feasible to charge directly for each electric distribution job due to the large volume of work orders. Typical activities included in this account are: Working with Contractors to develop fixed price bid for construction projects; Overseeing the Contractor work to remove obstacles and verify work is completed and complies with company standards; Approving Contractor Invoices for completed work; and Developing and Administering Contract Units for unit priced contracts. | SDG&E-11-R OR-91 to OR-92 CWP E09060
Capital | ELECTRIC DISTRIBUTION | SubTotal CONTRACT ADMINISTRATION POOL - ELEC |  |  |  | Yes |  |  | 9965353.5348 | 0 | 0 | 0 | 9965353.5348 | 54904999.92 | 56551999.92 | 58248999.96 | 59995999.92 | 54904999.92 | -44939646.3852 | -56551999.92 | -58248999.96 | -59995999.92 | -44939646.3852 | -81.85% | -100% | -100% | -100% | -81.85% | [21 empty] | YES | YES | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | DEPARTMENT OVERHEAD POOL - ELEC | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 48644457.9246 | 0 | 0 | 0 | 48644457.9246 | 26401999.92 | 27193999.92 | 28009999.92 | 28849999.92 | 26401999.92 | 22242458.0046 | -27193999.92 | -28009999.92 | -28849999.92 | 22242458.0046 | 84.25% | -100% | -100% | -100% | 84.25% | Department Overheads are those costs for supervision and administration of crews in the SDG&E Construction and Operation (C&O) districts. Department Overhead is charged for expenses that are not attributable to one particular project but benefit many projects, or the Construction and Operation (C&O) districts as a whole. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | The timing of project construction is dynamic and the variance is due to individual project schedule movements. Please see ED capital and WMP RSAR schedule submissions to review individual workpapers that impact the overhead pools. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Department Overheads are those costs for supervision and administration of crews in the SDG&E Construction and Operation (C&O) districts. Department Overhead is charged for expenses that are not attributable to one particular project, but benefit many projects, or the Construction and Operation (C&O) districts as a whole. Due to the volume of capital work that takes place on the distribution system, the most effective and efficient way to allocate the expenditures for the management of capital distribution operations activities throughout the service territory is through the use of this pool. It is not feasible to direct charge for each electric distribution job due to the large volume of work orders and field memos. | SDG&E-11-R OR-90 to OR-91 CWP E09050
Capital | ELECTRIC DISTRIBUTION | SubTotal DEPARTMENT OVERHEAD POOL - ELEC |  |  |  | Yes |  |  | 48644457.9246 | 0 | 0 | 0 | 48644457.9246 | 26401999.92 | 27193999.92 | 28009999.92 | 28849999.92 | 26401999.92 | 22242458.0046 | -27193999.92 | -28009999.92 | -28849999.92 | 22242458.0046 | 84.25% | -100% | -100% | -100% | 84.25% | [21 empty] | YES | YES | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | LOCAL ENGINEERING POOL - ED POOL | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 168928568.4009 | 0 | 0 | 0 | 168928568.4009 | 102528000 | 105603999.96 | 108771999.96 | 112035000 | 102528000 | 66400568.4009 | -105603999.96 | -108771999.96 | -112035000 | 66400568.4009 | 64.76% | -100% | -100% | -100% | 64.76% | The Local Engineering – ED Pool consists of the pool of Planners, Designers and Engineers, and support personnel who research, analyze, and design the facilities needed to serve customers. These persons address the engineering needs for new services, facilities relocations, overhead-to-underground conversions, capacity, and reliability projects. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | Engineering work is charged to the pool at the beginning of the project. Timing of projects is dynamic and the variance is due to individual project schedule movements. Please see ED capital and WMP RSAR schedule submissions to review individual workpapers that impact the overhead pools. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | Local Engineering activities are required to see a project from inception to completion. Due to the volume of capital work that takes place on the distribution system, the most effective and efficient way to allocate the planning and engineering activities is through the use of the overhead pools. It is not feasible to charge directly for each electric distribution job due to the large amount of work orders. The Local Engineering - ED Pool consists of the pool of Planners, Designers and Engineers, and support personnel who research, analyze, and design the facilities needed to serve customers. These persons address the engineering needs for new services, facilities relocations, overhead-to-underground conversions, capacity, and reliability projects. These persons also address the interaction with internal and external customers in preparing a work order package for construction. This pool includes the costs that will be allocated to electric distribution capital activities. | SDG&E-11-R OR-87 to OR-88 CWP E09010
Capital | ELECTRIC DISTRIBUTION | LOCAL ENGINEERING POOL - ED POOL | Asset Management | AIMDAT (Data Analytics) | N/A | No | On-going | Annual | 136881.3777 | 0 | 0 | 0 | 136881.3777 | 165000 | 169999.92 | 174999.96 | 180000 | 165000 | -28118.6223 | -169999.92 | -174999.96 | -180000 | -28118.6223 | -17.04% | -100% | -100% | -100% | -17.04% | The Local Engineering – ED Pool consists of the pool of Planners, Designers and Engineers, and support personnel who research, analyze, and design the facilities needed to serve customers. These persons address the engineering needs for new services, facilities relocations, overhead-to-underground conversions, capacity, and reliability projects. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal LOCAL ENGINEERING POOL - ED POOL |  |  |  | Yes |  |  | 169065449.7786 | 0 | 0 | 0 | 169065449.7786 | 102693000 | 105773999.88 | 108946999.92 | 112215000 | 102693000 | 66372449.7786 | -105773999.88 | -108946999.92 | -112215000 | 66372449.7786 | 64.63% | -100% | -100% | -100% | 64.63% | [21 empty] | YES | YES | [7 empty] | NO
Capital | ELECTRIC DISTRIBUTION | LOCAL ENGINEERING POOL - SUBSTATION POOL ELEC | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 5269976.0031 | 0 | 0 | 0 | 5269976.0031 | 3289999.92 | 3388999.92 | 3490999.92 | 3595999.92 | 3289999.92 | 1979976.0831 | -3388999.92 | -3490999.92 | -3595999.92 | 1979976.0831 | 60.18% | -100% | -100% | -100% | 60.18% | The Local Engineering – Substation Pool consists of activities supporting substation capital project design, engineering and construction that cannot easily be associated with single job orders and therefore are not fit for direct-charging. Examples of these types of activities include management and administrative labor and meetings and functions covering a wide range of substation engineering-related capital projects and topics. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A
Capital | ELECTRIC DISTRIBUTION | SubTotal LOCAL ENGINEERING POOL - SUBSTATION POOL ELEC |  |  |  | Yes |  |  | 5269976.0031 | 0 | 0 | 0 | 5269976.0031 | 3289999.92 | 3388999.92 | 3490999.92 | 3595999.92 | 3289999.92 | 1979976.0831 | -3388999.92 | -3490999.92 | -3595999.92 | 1979976.0831 | 60.18% | -100% | -100% | -100% | 60.18% | [21 empty] | YES | NO | [7 empty] | NO

## GOTD-C-B
SDG&E GAS INTEGRITY MANAGEMENT PROGRAMS Capital - Balanced
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | GAS INTEGRITY MANAGEMENT PROGRAMS | GAS INTEGRITY MANAGEMENT PROGRAMS |  |  |  | Yes |  |  | 114313332.5144 | 0 | 0 | 0 | 83013618.4733 | 25279999.92 | 26038999.8 | 26819999.88 | 27624999.84 | 25279999.92 | 89033332.5944 | -26038999.8 | -26819999.88 | -27624999.84 | 89033332.5944 | 352.2% | -100% | -100% | -100% | 352.2%
Capital | GAS INTEGRITY PROGRAMS | DIMP | Incident Related to the Medium Pressure System (Excluding Dig-in) | Distribution Integrity Management Program (DIMP) | Plastic - Main (VIPP) | No | On-going | Annual | 82374849.1508 | 0 | 0 | 0 | 82374849.1508 | 16023000 | 16503999.96 | 16998999.96 | 17508999.96 | 16023000 | 66351849.1508 | -16503999.96 | -16998999.96 | -17508999.96 | 66351849.1508 | 414.1% | -100% | -100% | -100% | 414.1% | Miles replaced | 58.19 |  |  |  | 58.19 | 14 |  |  |  | 14 | 44.19 | 0 | 0 | 0 | 44.19 | 315.6% | 0% | 0% | 0% | 315.6% | YES | YES | YES | DIMP complies with 49 CFR 192, Subpart P - Gas Distribution Pipeline Integrity Management and includes threat identification, risk assessment, and various projects to minimize threats and integrity concerns to reduce risk of pipeline incidents. The 2024 variance is driven by a difference between SDG&E’s plan as presented in the TY 2024 GRC application and the level of activity funded in the final TY 2024 GRC decision, which was issued in December of 2024. SDG&E’s VIPP activity level followed the strategy that was approved in the 2019 GRC due to the delay in receiving a final 2024 GRC decision, which funded a lower level of activity but also authorized a memorandum account for additional replacements when pipe in areas of risk are identified. While SDG&E has completed more miles than authorized within the DIMP balancing account, the level of activity is consistent with that for which SDG&E is authorized to seek recovery. Replacements were planned and completed in alignment with SDG&E’s transition to its Quantitative Risk Assessment (QRA) results, which inform the prioritization of DREAMS replacements to address pipeline segments that exceed SDG&E’s risk threshold. | DIMP complies with 49 CFR 192, Subpart P - Gas Distribution Pipeline Integrity Management and includes threat identification, risk assessment, and various projects to minimize threats and integrity concerns to reduce risk of pipeline incidents. The 2024 variance is driven by a difference between SDG&E’s plan as presented in the TY 2024 GRC application and the level of activity funded in the final TY 2024 GRC decision, which was issued in December of 2024. SDG&E’s VIPP activity level followed the strategy that was approved in the 2019 GRC due to the delay in receiving a final 2024 GRC decision, which funded a lower level of activity but also authorized a memorandum account for additional replacements when pipe in areas of risk are identified. While SDG&E has completed more miles than authorized within the DIMP balancing account, the level of activity is consistent with that for which SDG&E is authorized to seek recovery. Replacements were planned and completed in alignment with SDG&E’s transition to its Quantitative Risk Assessment (QRA) results, which inform the prioritization of DREAMS replacements to address pipeline segments that exceed SDG&E’s risk threshold. | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | DIMP Capital activities in budget code 9546 include installations, replacements, and other risk mitigation or remediation activities driven by DIMP Projects and Activities to Address Risk (PAARs). These costs reflect expected activity levels under the VIPP, which consists of replacement of non-state-of-the-art Aldyl-A pipe. | SDGE-09-R AK-TS-51 to AK-TS-52 CWP 095460
Capital | GAS INTEGRITY PROGRAMS | SubTotal DIMP |  |  |  | Yes |  |  | 82374849.1508 | 0 | 0 | 0 | 82374849.1508 | 16023000 | 16503999.96 | 16998999.96 | 17508999.96 | 16023000 | 66351849.1508 | -16503999.96 | -16998999.96 | -17508999.96 | 66351849.1508 | 414.1% | -100% | -100% | -100% | 414.1% | [21 empty] | YES | YES | [7 empty] | NO
Capital | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - HCA | No | On-going | Annual | 31299714.0411 | 0 | 0 | 0 | 31299714.0411 | 8794999.92 | 9058999.92 | 9330000 | 9610999.92 | 8794999.92 | 22504714.1211 | -9058999.92 | -9330000 | -9610999.92 | 22504714.1211 | 255.9% | -100% | -100% | -100% | 255.9% | This activity and the work completed in 2024 consist of retrofitting pipelines for in-line inspection capability, replacements, and other capital remediation. The number and types of remediation are driven by each assessment. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | YES | NO | TIMP complies with 49 CFR 192, Subpart O - Gas Transmission Pipeline Integrity Management and includes threat identification, risk analysis, pipeline assessments, remediation, and other actions that minimize threats and integrity concerns to reduce risk of pipeline failure. In general, the TIMP activity level is driven by assessment requirements and pipeline safety considerations, as well as the resulting remediation and repair needs. TIMP remediation activities are informed by assessment findings and may vary from pipeline to pipeline and year to year, and in some cases, remediation activities are a result of the previous year's assessment findings. TIMP assessments may span both HCA and non-HCA segments and these tranches should be viewed in aggregate. Non-HCA pipeline segments include those in Class 3 and 4 locations, as well as Moderate Consequence Areas (MCAs), which are required under expanded PHMSA requirements per 49 CFR § 192.710. The allocation between the tranches is calculated based on the number of the actual 2024 completed assessment mileage. The 2024 variance in expenditures is primarily due to the expansion of the ILI program, as necessitated by the changes resulting from GTSR Part 1 (84 FR 52180). In order to assess manufacturing threats newly classified as active under 49 CFR § 192.917(e), SDG&E retrofitted previously unpiggable piping to enable the use of ILI tools. | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | TIMP Capital activities in budget code 03468 include retrofitting pipelines for in-line inspection capability, replacements, and other capital remediation as a result of assessment findings on the DOT-defined transmission pipelines. | SDGE-09-R AK-TS-47 to AK-TS-51 CWP 034680
Capital | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - Non-HCA | No | On-going | Annual | 638769.3225 | 0 | 0 | 0 | 638769.3225 | 462000 | 475999.92 | 490999.92 | 504999.96 | 462000 | 176769.3225 | -475999.92 | -490999.92 | -504999.96 | 176769.3225 | 38.26% | -100% | -100% | -100% | 38.26% | This activity and the work completed in 2024 consist of retrofitting pipelines for in-line inspection capability, replacements, and other capital remediation. The number and types of remediation are driven by each assessment. The variety of work activities in this category makes it infeasible to identify a single unit of measurement. | [20 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | Over (O) | Proceeding as Planned | NO | N/A | TIMP Capital activities in budget code 03468 include retrofitting pipelines for in-line inspection capability, replacements, and other capital remediation as a result of assessment findings on the DOT-defined transmission pipelines. | SDGE-09-R AK-TS-47 to AK-TS-51 CWP 034680
Capital | GAS INTEGRITY PROGRAMS | SubTotal TIMP |  |  |  | Yes |  |  | 31938483.3636 | 0 | 0 | 0 | 638769.3225 | 9256999.92 | 9534999.84 | 9820999.92 | 10115999.88 | 9256999.92 | 22681483.4436 | -9534999.84 | -9820999.92 | -10115999.88 | 22681483.4436 | 2.9414 | -100% | -100% | -100% | 245% | [21 empty] | YES | YES | [7 empty] | NO

## GOGD-C-B
SDG&E GAS DISTRIBUTION Capital - Balanced
Balanced
Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Roll-up | Project Life (Years) | Project Year | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Unit of Measure (Unit Type) | Actual Units 2024 | Actual Units 2025 | Actual Units 2026 | Actual Units 2027 | Actual Units to Date | Imputed Authorized Units 2024 | Imputed Authorized Units 2025 | Imputed Authorized Units 2026 | Imputed Authorized Units 2027 | Imputed Authorized Units to Date | Annual Units Difference 2024 | Annual Units Difference 2025 | Annual Units Difference 2026 | Annual Units Difference 2027 | Units to Date Difference | Annual Units Percent Variance 2024 | Annual Units Percent Variance 2025 | Annual Units Percent Variance 2026 | Annual Units Percent Variance 2027 | Units to Date Percent Variance | Safety, Reliability, or Maintenance? | Spending Variance Explanation Required? | Unit Variance Explanation Required? | Cost Variance Explanation | Unit Variance Explanation | Forecast Scope Status | Forecast Schedule Status | Forecast Spending Status | Status | Status Variance Explanation Required? | Status Variance Explanation | WP Activity Description | 2024 GRC Testimony Location
Capital | GAS DISTRIBUTION | GAS DISTRIBUTION |  |  |  | Yes |  |  | 2488044.0798 | 0 | 0 | 0 | 2488044.0798 | 2325000 | 2394999.96 | 2466999.96 | 2541000 | 2325000 | 163044.0798 | -2394999.96 | -2466999.96 | -2541000 | 163044.0798 | 7.013% | -100% | -100% | -100% | 7.013%
Capital | GAS DISTRIBUTION | NEW BUSINESS- BALANCED | Non-RAMP | Non-RAMP | Non-RAMP | No | On-going | Annual | 2263763.7724 | 0 | 0 | 0 | 2263763.7724 | 2325000 | 2394999.96 | 2466999.96 | 2541000 | 2325000 | -61236.2276 | -2394999.96 | -2466999.96 | -2541000 | -61236.2276 | -2.634% | -100% | -100% | -100% | -2.634% | Non-collectible new customers | 358 |  |  |  | 358 | The 2024 GRC final decision adopted a forecast that was lower in scope and dollars than originally requested. The variety and scope of work for each new business (customer-driven gas service) project makes it infeasible to identify a single imputed authorized unit of measure. | [14 empty] | YES | NO | NO | N/A | N/A | On Target (T) | On Target (T) | On Target (T) | Proceeding as Planned | NO | N/A
Capital | GAS DISTRIBUTION | NEW BUSINESS- BALANCED | Incident Related to the Medium Pressure System (Excluding Dig-in) | Field and Public Safety | Meter & Beyond the Meter | No | On-going | Annual | 224280.3074 | 0 | 0 | 0 | 224280.3074 | 0 | 0 | 0 | 0 | 0 | 224280.3074 | 0 | 0 | 0 | 224280.3074 | 100% | 0% | 0% | 0% | 100% | Purge orders | 170 |  |  |  | 170 | 0 |  |  |  | 0 | 170 | 0 | 0 | 0 | 170 | 100% | 0% | 0% | 0% | 100% | YES | NO | YES | N/A | This activity involves installing new pipeline associated with providing gas service to new business. The number and timing of new pipeline purging projects is based on new business requests which are outside the control of SDG&E. | Over (O) | Over (O) | Over (O) | Proceeding as Planned | NO | N/A | Expenditures within budget code 500 provide for changes and additions to the existing gas distribution system for the purpose of serving new gas customers. | SDG&E-04-R-E LPK-70 to LPK-74 CWP 005000
Capital | GAS DISTRIBUTION | SubTotal NEW BUSINESS- BALANCED |  |  |  | Yes |  |  | 2488044.0798 | 0 | 0 | 0 | 2488044.0798 | 2325000 | 2394999.96 | 2466999.96 | 2541000 | 2325000 | 163044.0798 | -2394999.96 | -2466999.96 | -2541000 | 163044.0798 | 7.013% | -100% | -100% | -100% | 7.013% | [21 empty] | YES | NO | [7 empty] | NO

## Var Criteria (hidden)
Variance Thresholds Requiring Variance Explanations as of 1/1/2020
SDG&E | O&M |  |  | Capital
| Criteria 1 | Criteria 2 |  | Criteria 1 | Criteria 2
| Anything Over | Greater than 20% AND min $ |  | Anything Over | Greater than 20% AND min $
[7 empty] | Status Variance Explanation | 2019 GRC Testimony Location | 2024 GRC Testimony Location
Elect | 5000000 | 2500000 | 20% | 10000000 | 5000000 | 20%
Gas | 2500000 | 500000 | 20% | 5000000 | 1000000 | 20%
Other | 5000000 | 2500000 | 20% | 10000000 | 5000000 | 20%
SoCal Gas | O&M |  |  | Capital
| Criteria 1 | Criteria 2 |  | Criteria 1 | Criteria 2
| Anything Over | Greater than 20% AND min $ |  | Anything Over | Greater than 20% AND min $
Gas | 5000000 | 1000000 | 20% | 10000000 | 2000000 | 20%
Other | 5000000 | 1000000 | 20% | 10000000 | 2000000 | 20%
Unit Criteria (SCG & SDG&E)
20%

## Toggle (hidden)
RSAR Year: | 2024
| TY | PTY-1 | PTY-2 | PTY-3
GRC Cycle | 2024 | 2025 | 2026 | 2027

## DataValParameters (hidden)
Status | Forecast Status
Proceeding as Planned | Under (U)
Deferred | On Target (T)
Canceled | Over (O)
Emergent
Expanded
Completed
Other

## Linking Data (hidden)
Link | Type | Witness Area (Line of Business) | WP Activity Description (Spending Category) | RAMP Risk Chapter | RAMP Mitigation Activity | RAMP Tranche | Actual Cost 2024 | Actual Cost 2025 | Actual Cost 2026 | Actual Cost 2027 | Actual Cost to Date ($) | Imputed Authorized Cost 2024 | Imputed Authorized Cost 2025 | Imputed Authorized Cost 2026 | Imputed Authorized Cost 2027 | Imputed Authorized Cost to Date ($) | Annual Cost Difference 2024 | Annual Cost Difference 2025 | Annual Cost Difference 2026 | Annual Cost Difference 2027 | Cost to Date Difference ($) | Annual Cost Percent Variance 2024 | Annual Cost Percent Variance 2025 | Annual Cost Percent Variance 2026 | Annual Cost Percent Variance 2027 | Cost to Date Percent Variance | Safety, Reliability, or Maintenance? | Workpaper Key | Balanced | RAMP Risk Chapter Key
CapitalCLEAN ENERGY INNOVATIONSADVANCED ENERGY STORAGENon-RAMPNon-RAMPNon-RAMP | Capital | CLEAN ENERGY INNOVATIONS | ADVANCED ENERGY STORAGE | Non-RAMP | Non-RAMP | Non-RAMP | 3716228.3809 | 0 | 0 | 0 | 3716228.3809 | 0 | 0 | 0 | 0 | 0 | 3716228.3809 | 0 | 0 | 0 | 3716228.3809 | 100% | 100% | 100% | 100% | 100% | YES | 202780 | NO | NR
CapitalCLEAN ENERGY INNOVATIONSBORREGO MICROGRID 3.0Non-RAMPNon-RAMPNon-RAMP | Capital | CLEAN ENERGY INNOVATIONS | BORREGO MICROGRID 3.0 | Non-RAMP | Non-RAMP | Non-RAMP | -2008434.0928 | 0 | 0 | 0 | -2008434.0928 | 0 | 0 | 0 | 0 | 0 | -2008434.0928 | 0 | 0 | 0 | -2008434.0928 | 100% | 100% | 100% | 100% | 100% | YES | 172460 | NO | NR
CapitalCLEAN ENERGY INNOVATIONSMOBILE BATTERY ENERGY STORAGE PROGRAMNon-RAMPNon-RAMPNon-RAMP | Capital | CLEAN ENERGY INNOVATIONS | MOBILE BATTERY ENERGY STORAGE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 2602999.92 | 2680999.92 | 2760999.96 | 2844000 | 10888999.8 | -2602999.92 | -2680999.92 | -2760999.96 | -2844000 | -10888999.8 | -100% | -100% | -100% | -100% | -100% | YES | 212610 | NO | NR
CapitalCLEAN ENERGY INNOVATIONSSUSTAINABLE COMMUNITIES REMOVALNon-RAMPNon-RAMPNon-RAMP | Capital | CLEAN ENERGY INNOVATIONS | SUSTAINABLE COMMUNITIES REMOVAL | Non-RAMP | Non-RAMP | Non-RAMP | 224849.51 | 0 | 0 | 0 | 224849.51 | 166999.92 | 171999.96 | 177000 | 181999.92 | 697999.8 | 57849.59 | -171999.96 | -177000 | -181999.92 | -473150.29 | 34.64% | -100% | -100% | -100% | -67.79% | YES | 20281A | NO | NR
CapitalCYBERSECURITYRAMP - CYBER - SDGE - INTERNAL DEFENSESCybersecurityInternal DefensesOverall | Capital | CYBERSECURITY | RAMP - CYBER - SDGE - INTERNAL DEFENSES | Cybersecurity | Internal Defenses | Overall | 115922.8202 | 0 | 0 | 0 | 115922.8202 | 1357999.92 | 1398999.96 | 1440999.96 | 1485000 | 5682999.84 | -1242077.0998 | -1398999.96 | -1440999.96 | -1485000 | -5567077.0198 | -91.46% | -100% | -100% | -100% | -97.96% | YES | 00906H | NO | SDG&E-Risk-6
CapitalCYBERSECURITYRAMP - CYBER - SDGE - OBSOLETE IT INFRASTRUCTURE AND APPLICATION REPLACEMENTCybersecurityObsolete Information Technology (IT) Infrastructure and Application ReplacementOverall | Capital | CYBERSECURITY | RAMP - CYBER - SDGE - OBSOLETE IT INFRASTRUCTURE AND APPLICATION REPLACEMENT | Cybersecurity | Obsolete Information Technology (IT) Infrastructure and Application Replacement | Overall | 0 | 0 | 0 | 0 | 0 | 1357999.92 | 1398999.96 | 1440999.96 | 1485000 | 5682999.84 | -1357999.92 | -1398999.96 | -1440999.96 | -1485000 | -5682999.84 | -100% | -100% | -100% | -100% | -100% | YES | 00906J | NO | SDG&E-Risk-6
CapitalCYBERSECURITYRAMP - CYBER - SDGE - OPERATIONAL TECHNOLOGY (OT) CYBERSECURITYCybersecurityOperational Technology (OT) CybersecurityOverall | Capital | CYBERSECURITY | RAMP - CYBER - SDGE - OPERATIONAL TECHNOLOGY (OT) CYBERSECURITY | Cybersecurity | Operational Technology (OT) Cybersecurity | Overall | 3897083.2342 | 0 | 0 | 0 | 3897083.2342 | 4075999.92 | 4198999.92 | 4324999.92 | 4455000 | 17054999.76 | -178916.6858 | -4198999.92 | -4324999.92 | -4455000 | -13157916.5258 | -4.39% | -100% | -100% | -100% | -77.15% | YES | 00906I | NO | SDG&E-Risk-6
CapitalCYBERSECURITYRAMP - CYBER - SDGE - PERIMETER DEFENSESCybersecurityPerimeter DefensesOverall | Capital | CYBERSECURITY | RAMP - CYBER - SDGE - PERIMETER DEFENSES | Cybersecurity | Perimeter Defenses | Overall | 0 | 0 | 0 | 0 | 0 | 2715999.96 | 2797999.92 | 2881999.92 | 2968999.92 | 11364999.72 | -2715999.96 | -2797999.92 | -2881999.92 | -2968999.92 | -11364999.72 | -100% | -100% | -100% | -100% | -100% | YES | 00906G | NO | SDG&E-Risk-6
CapitalCYBERSECURITYRAMP - CYBER - SDGE - SENSITIVE DATA PROTECTIONCybersecuritySensitive Data ProtectionOverall | Capital | CYBERSECURITY | RAMP - CYBER - SDGE - SENSITIVE DATA PROTECTION | Cybersecurity | Sensitive Data Protection | Overall | 0 | 0 | 0 | 0 | 0 | 1900999.92 | 1957999.92 | 2016999.96 | 2076999.96 | 7952999.76 | -1900999.92 | -1957999.92 | -2016999.96 | -2076999.96 | -7952999.76 | -100% | -100% | -100% | -100% | -100% | YES | 00906K | NO | SDG&E-Risk-6
CapitalELECTRIC DISTRIBUTION3 ROOTS TL6906,TL677,TL668 CUST RELONon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | 3 ROOTS TL6906,TL677,TL668 CUST RELO | Non-RAMP | Non-RAMP | Non-RAMP | 140940.6567 | 0 | 0 | 0 | 140940.6567 | 999.96 | 999.96 | 999.96 | 999.96 | 3999.84 | 139940.6967 | -999.96 | -999.96 | -999.96 | 136940.8167 | 13995% | -100% | -100% | -100% | 3424% | NO | 181430 | NO | NR
CapitalELECTRIC DISTRIBUTIONARTESIAN 230KV EXPANSIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ARTESIAN 230KV EXPANSION | Non-RAMP | Non-RAMP | Non-RAMP | 13220.84 | 0 | 0 | 0 | 13220.84 | 0 | 0 | 0 | 0 | 0 | 13220.84 | 0 | 0 | 0 | 13220.84 | 100% | 100% | 100% | 100% | 100% | YES | 141280 | NO | NR
CapitalELECTRIC DISTRIBUTIONBORREGO SPRINGS MICROGRID GENERATOR REPLNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | BORREGO SPRINGS MICROGRID GENERATOR REPL | Non-RAMP | Non-RAMP | Non-RAMP | 3487280.0703 | 0 | 0 | 0 | 3487280.0703 | 0 | 0 | 0 | 0 | 0 | 3487280.0703 | 0 | 0 | 0 | 3487280.0703 | 100% | 100% | 100% | 100% | 100% | YES | 23250 | NO | NR
CapitalELECTRIC DISTRIBUTIONC1162, BD: NEW C1162Non-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | C1162, BD: NEW C1162 | Non-RAMP | Non-RAMP | Non-RAMP | 23906.4778 | 0 | 0 | 0 | 23906.4778 | 0 | 0 | 0 | 0 | 0 | 23906.4778 | 0 | 0 | 0 | 23906.4778 | 100% | 100% | 100% | 100% | 100% | YES | 21251A | NO | NR
CapitalELECTRIC DISTRIBUTIONC369, S: NEW 12KV TWIN CIRCUITNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | C369, S: NEW 12KV TWIN CIRCUIT | Non-RAMP | Non-RAMP | Non-RAMP | 68978.0767 | 0 | 0 | 0 | 68978.0767 | 0 | 0 | 0 | 0 | 0 | 68978.0767 | 0 | 0 | 0 | 68978.0767 | 100% | 100% | 100% | 100% | 100% | YES | 212580 | NO | NR
CapitalELECTRIC DISTRIBUTIONC50, PTL: RECO AND CAPACITORNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | C50, PTL: RECO AND CAPACITOR | Non-RAMP | Non-RAMP | Non-RAMP | 20830.2521 | 0 | 0 | 0 | 32713.7421 | 0 | 0 | 0 | 0 | 0 | 20830.2521 | 0 | 0 | 0 | 32713.7421 | 100% | 100% | 100% | 100% | 100% | YES | 212470 | NO | NR
CapitalELECTRIC DISTRIBUTIONCBM - 4.2 FIRMWARE UPGRADE FOR TRANSFORMNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CBM - 4.2 FIRMWARE UPGRADE FOR TRANSFORM | Non-RAMP | Non-RAMP | Non-RAMP | 14541.7556 | 0 | 0 | 0 | 14541.7556 | 0 | 0 | 0 | 0 | 0 | 14541.7556 | 0 | 0 | 0 | 14541.7556 | 100% | 100% | 100% | 100% | 100% | YES | 202830 | NO | NR
CapitalELECTRIC DISTRIBUTIONCITY OF SAN DIEGO SURCHARGE PROG (20SD)Non-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CITY OF SAN DIEGO SURCHARGE PROG (20SD) | Non-RAMP | Non-RAMP | Non-RAMP | 7003586.7122 | 0 | 0 | 0 | 7003586.7122 | 23847999.96 | 24562999.92 | 25299999.96 | 26058999.96 | 99769999.8 | -16844413.2478 | -24562999.92 | -25299999.96 | -26058999.96 | -92766413.0878 | -70.63% | -100% | -100% | -100% | -92.98% | NO | 2130 | NO | NR
CapitalELECTRIC DISTRIBUTIONCOLLECTIBLE - CAMP PENDLETON - STUART MESA HOUSINGNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | COLLECTIBLE - CAMP PENDLETON - STUART MESA HOUSING | Non-RAMP | Non-RAMP | Non-RAMP | 36627.4557 | 0 | 0 | 0 | 94014.8157 | 0 | 0 | 0 | 0 | 0 | 36627.4557 | 0 | 0 | 0 | 94014.8157 | 100% | 100% | 100% | 100% | 100% | NO | 202560 | NO | NR
CapitalELECTRIC DISTRIBUTIONCONTRACT ADMINISTRATION POOL - ELECNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CONTRACT ADMINISTRATION POOL - ELEC | Non-RAMP | Non-RAMP | Non-RAMP | 9965353.5348 | 0 | 0 | 0 | 9965353.5348 | 54904999.92 | 56551999.92 | 58248999.96 | 59995999.92 | 229701999.72 | -44939646.3852 | -56551999.92 | -58248999.96 | -59995999.92 | -219736646.1852 | -81.85% | -100% | -100% | -100% | -95.66% | YES | E09060 | YES | NR
CapitalELECTRIC DISTRIBUTIONCONVERSION FROM OH TO UG RULE 20ANon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CONVERSION FROM OH TO UG RULE 20A | Non-RAMP | Non-RAMP | Non-RAMP | 3194267.6442 | 0 | 0 | 0 | 3194267.6442 | 19476999.96 | 20061000 | 20662999.92 | 21282999.96 | 81483999.84 | -16282732.3158 | -20061000 | -20662999.92 | -21282999.96 | -78289732.1958 | -83.6% | -100% | -100% | -100% | -96.08% | NO | 2100 | NO | NR
CapitalELECTRIC DISTRIBUTIONCONVERSION FROM OH-UG RULE 20B NEW BUSINNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CONVERSION FROM OH-UG RULE 20B NEW BUSIN | Non-RAMP | Non-RAMP | Non-RAMP | 895502.6902 | 0 | 0 | 0 | 895502.6902 | 2139999.96 | 2203999.92 | 2269999.92 | 2337999.96 | 8951999.76 | -1244497.2698 | -2203999.92 | -2269999.92 | -2337999.96 | -8056497.0698 | -58.15% | -100% | -100% | -100% | -90% | NO | 212520 | NO | NR
CapitalELECTRIC DISTRIBUTIONCONVERSION FROM OH-UG RULE 20CNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CONVERSION FROM OH-UG RULE 20C | Non-RAMP | Non-RAMP | Non-RAMP | 2300166.5792 | 0 | 0 | 0 | 2300166.5792 | 2553999.96 | 2629999.92 | 2709000 | 2790000 | 10682999.88 | -253833.3808 | -2629999.92 | -2709000 | -2790000 | -8382833.3008 | -9.939% | -100% | -100% | -100% | -78.47% | NO | 212530 | NO | NR
CapitalELECTRIC DISTRIBUTIONCORONADO 69/12KV TRANSFORMER REPLACEMENTElectric Infrastructure IntegritySubstation Reliability for Distribution Components - Coronado 69/12kV Transformer ReplacementsSubstation | Capital | ELECTRIC DISTRIBUTION | CORONADO 69/12KV TRANSFORMER REPLACEMENT | Electric Infrastructure Integrity | Substation Reliability for Distribution Components - Coronado 69/12kV Transformer Replacements | Substation | 1280676.1549 | 0 | 0 | 0 | 1280676.1549 | 870999.96 | 897000 | 924000 | 951999.96 | 3643999.92 | 409676.1949 | -897000 | -924000 | -951999.96 | -2363323.7651 | 47.04% | -100% | -100% | -100% | -64.86% | YES | 202740 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONCRITICAL ASSET SECURITYNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CRITICAL ASSET SECURITY | Non-RAMP | Non-RAMP | Non-RAMP | -25814.3379 | 0 | 0 | 0 | -25814.3379 | 0 | 0 | 0 | 0 | 0 | -25814.3379 | 0 | 0 | 0 | -25814.3379 | 100% | 100% | 100% | 100% | 100% | YES | 151250 | NO | NR
CapitalELECTRIC DISTRIBUTIONCUSTOMER REQUESTED UPGRADES AND SERVICESNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | CUSTOMER REQUESTED UPGRADES AND SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 21449329.7167 | 0 | 0 | 0 | 21449329.7167 | 16834999.92 | 17340000 | 17859999.96 | 18396000 | 70430999.88 | 4614329.7967 | -17340000 | -17859999.96 | -18396000 | -48981670.1633 | 27.41% | -100% | -100% | -100% | -69.55% | NO | 2250 | NO | NR
CapitalELECTRIC DISTRIBUTIONDEPARTMENT OVERHEAD POOL - ELECNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | DEPARTMENT OVERHEAD POOL - ELEC | Non-RAMP | Non-RAMP | Non-RAMP | 48644457.9246 | 0 | 0 | 0 | 48644457.9246 | 26401999.92 | 27193999.92 | 28009999.92 | 28849999.92 | 110455999.68 | 22242458.0046 | -27193999.92 | -28009999.92 | -28849999.92 | -61811541.7554 | 84.25% | -100% | -100% | -100% | -55.96% | YES | E09050 | YES | NR
CapitalELECTRIC DISTRIBUTIONDISTRIBUTED GENERATION INTERCONNECT. PRONon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | DISTRIBUTED GENERATION INTERCONNECT. PRO | Non-RAMP | Non-RAMP | Non-RAMP | 770591.6031 | 0 | 0 | 0 | 770591.6031 | 2217999.96 | 2284999.92 | 2353999.92 | 2424999.96 | 9281999.76 | -1447408.3569 | -2284999.92 | -2353999.92 | -2424999.96 | -8511408.1569 | -65.26% | -100% | -100% | -100% | -91.7% | NO | 132640 | NO | NR
CapitalELECTRIC DISTRIBUTIONDISTRIBUTION SYSTEM CAPACITY IMPROVEMENTNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | DISTRIBUTION SYSTEM CAPACITY IMPROVEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 75036.9488 | 0 | 0 | 0 | 75036.9488 | 3997999.92 | 4117999.92 | 4242000 | 4368999.96 | 16726999.8 | -3922962.9712 | -4117999.92 | -4242000 | -4368999.96 | -16651962.8512 | -98.12% | -100% | -100% | -100% | -99.55% | YES | 972480 | NO | NR
CapitalELECTRIC DISTRIBUTIONDPM DIGITAL LAYERNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | DPM DIGITAL LAYER | Non-RAMP | Non-RAMP | Non-RAMP | 1174256.9464 | 0 | 0 | 0 | 1174256.9464 | 0 | 0 | 0 | 0 | 0 | 1174256.9464 | 0 | 0 | 0 | 1174256.9464 | 100% | 100% | 100% | 100% | 100% | NO | 242430 | NO | NR
CapitalELECTRIC DISTRIBUTIONELCT TRANS SMALL REALIBLTY JOBS- NON WMPNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELCT TRANS SMALL REALIBLTY JOBS- NON WMP | Non-RAMP | Non-RAMP | Non-RAMP | 178887.6812 | 0 | 0 | 0 | 178887.6812 | 1033999.92 | 1065000 | 1096999.92 | 1129999.92 | 4325999.76 | -855112.2388 | -1065000 | -1096999.92 | -1129999.92 | -4147112.0788 | -82.7% | -100% | -100% | -100% | -95.86% | YES | 211350 | NO | NR
CapitalELECTRIC DISTRIBUTIONELEC TRANS LINE RELOCATION PROJECTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELEC TRANS LINE RELOCATION PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | 5112.3412 | 0 | 0 | 0 | 5112.3412 | 0 | 0 | 0 | 0 | 0 | 5112.3412 | 0 | 0 | 0 | 5112.3412 | 100% | 100% | 100% | 100% | 100% | NO | 1020 | NO | NR
CapitalELECTRIC DISTRIBUTIONELECTRIC - CONVERSION FROM OH TO UG RULE 20BNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELECTRIC - CONVERSION FROM OH TO UG RULE 20B | Non-RAMP | Non-RAMP | Non-RAMP | 177929.5083 | 0 | 0 | 0 | 177929.5083 | 59670999.96 | 61461000 | 63304999.92 | 65203999.92 | 249640999.8 | -59493070.4517 | -61461000 | -63304999.92 | -65203999.92 | -249463070.2917 | -99.7% | -100% | -100% | -100% | -99.93% | NO | 202570 | NO | NR
CapitalELECTRIC DISTRIBUTIONELECTRIC DIST. STREET/HWY RELOCATIONSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELECTRIC DIST. STREET/HWY RELOCATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 3076220.5406 | 0 | 0 | 0 | 3076220.5406 | 7971000 | 8209999.92 | 8455999.92 | 8709999.96 | 33346999.8 | -4894779.4594 | -8209999.92 | -8455999.92 | -8709999.96 | -30270779.2594 | -61.41% | -100% | -100% | -100% | -90.78% | NO | 2050 | NO | NR
CapitalELECTRIC DISTRIBUTIONELECTRIC DISTRIBUTION EASEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELECTRIC DISTRIBUTION EASEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 3879125.8948 | 0 | 0 | 0 | 3879125.8948 | 2836999.92 | 2922000 | 3009999.96 | 3099999.96 | 11868999.84 | 1042125.9748 | -2922000 | -3009999.96 | -3099999.96 | -7989873.9452 | 36.73% | -100% | -100% | -100% | -67.32% | YES | 2040 | NO | NR
CapitalELECTRIC DISTRIBUTIONELECTRIC DISTRIBUTION TOOLS/EQUIPMENTNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELECTRIC DISTRIBUTION TOOLS/EQUIPMENT | Non-RAMP | Non-RAMP | Non-RAMP | 864683.21 | 0 | 0 | 0 | 1029205.13 | 2631999.96 | 2710999.92 | 2791999.92 | 2875999.92 | 11010999.72 | -1767316.75 | -2710999.92 | -2791999.92 | -2875999.92 | -9981794.59 | -67.15% | -100% | -100% | -100% | -90.65% | YES | 2060 | NO | NR
CapitalELECTRIC DISTRIBUTIONELECTRIC METERS & REGULATORSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELECTRIC METERS & REGULATORS | Non-RAMP | Non-RAMP | Non-RAMP | 9745351.75 | 0 | 0 | 0 | 13354932.46 | 6636999.96 | 6835999.92 | 7041000 | 7251999.96 | 27765999.84 | 3108351.79 | -6835999.92 | -7041000 | -7251999.96 | -14411067.38 | 46.83% | -100% | -100% | -100% | -51.9% | YES | 2020 | NO | NR
CapitalELECTRIC DISTRIBUTIONELECTRIC TRANSMISSION TOOLS & EQUIPMENTNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELECTRIC TRANSMISSION TOOLS & EQUIPMENT | Non-RAMP | Non-RAMP | Non-RAMP | 369985.33 | 0 | 0 | 0 | 369985.33 | 555000 | 571999.92 | 588999.96 | 606999.96 | 2322999.84 | -185014.67 | -571999.92 | -588999.96 | -606999.96 | -1953014.51 | -33.34% | -100% | -100% | -100% | -84.07% | YES | 1060 | NO | NR
CapitalELECTRIC DISTRIBUTIONELECTRIFICATION SUBSTATIONSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ELECTRIFICATION SUBSTATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 8899.0974 | 0 | 0 | 0 | 8899.0974 | 0 | 0 | 0 | 0 | 0 | 8899.0974 | 0 | 0 | 0 | 8899.0974 | 100% | 100% | 100% | 100% | 100% | YES | 241320 | NO | NR
CapitalELECTRIC DISTRIBUTIONENCINA DECOMMISSION-REMOVAL 138KV SUBSTANon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | ENCINA DECOMMISSION-REMOVAL 138KV SUBSTA | Non-RAMP | Non-RAMP | Non-RAMP | 2371.9382 | 0 | 0 | 0 | 2486.0582 | 0 | 0 | 0 | 0 | 0 | 2371.9382 | 0 | 0 | 0 | 2486.0582 | 100% | 100% | 100% | 100% | 100% | YES | 211450 | NO | NR
CapitalELECTRIC DISTRIBUTIONFIBER OPTIC FOR RELAY PROTECT & TELECOMNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | FIBER OPTIC FOR RELAY PROTECT & TELECOM | Non-RAMP | Non-RAMP | Non-RAMP | 3903417.9015 | 0 | 0 | 0 | 3903417.9015 | 8928999.96 | 9196999.92 | 9472999.92 | 9756999.96 | 37355999.76 | -5025582.0585 | -9196999.92 | -9472999.92 | -9756999.96 | -33452581.8585 | -56.28% | -100% | -100% | -100% | -89.55% | YES | 71440 | NO | NR
CapitalELECTRIC DISTRIBUTIONFIELD SHUNT CAPACITORSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | FIELD SHUNT CAPACITORS | Non-RAMP | Non-RAMP | Non-RAMP | 86332.6685 | 0 | 0 | 0 | 86332.6685 | 870999.96 | 897000 | 924000 | 951999.96 | 3643999.92 | -784667.2915 | -897000 | -924000 | -951999.96 | -3557667.2515 | -90.09% | -100% | -100% | -100% | -97.63% | YES | 2090 | NO | NR
CapitalELECTRIC DISTRIBUTIONFUTURE CAPACITY PROJECTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | FUTURE CAPACITY PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | 13021818.6357 | 0 | 0 | 0 | 13021818.6357 | 9651999.96 | 9942000 | 10239999.96 | 10546999.92 | 40380999.84 | 3369818.6757 | -9942000 | -10239999.96 | -10546999.92 | -27359181.2043 | 34.91% | -100% | -100% | -100% | -67.75% | NO | 212760 | NO | NR
CapitalELECTRIC DISTRIBUTIONGENERATION INTERCONNECTION PROJECTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | GENERATION INTERCONNECTION PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | 471875.8859 | 0 | 0 | 0 | 471875.8859 | 0 | 0 | 0 | 0 | 0 | 471875.8859 | 0 | 0 | 0 | 471875.8859 | 100% | 100% | 100% | 100% | 100% | NO | 211560 | NO | NR
CapitalELECTRIC DISTRIBUTIONGRANITE 12KV BREAKER AND SWITCHGEAR REPLNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | GRANITE 12KV BREAKER AND SWITCHGEAR REPL | Non-RAMP | Non-RAMP | Non-RAMP | 1102556.8906 | 0 | 0 | 0 | 1102556.8906 | 0 | 0 | 0 | 0 | 0 | 1102556.8906 | 0 | 0 | 0 | 1102556.8906 | 100% | 100% | 100% | 100% | 100% | YES | 202440 | NO | NR
CapitalELECTRIC DISTRIBUTIONGRANITE SUBSTATION 69KV LOOP-INNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | GRANITE SUBSTATION 69KV LOOP-IN | Non-RAMP | Non-RAMP | Non-RAMP | 297527.0352 | 0 | 0 | 0 | 297527.0352 | 177000 | 181999.92 | 186999.96 | 192999.96 | 738999.84 | 120527.0352 | -181999.92 | -186999.96 | -192999.96 | -441472.8048 | 68.09% | -100% | -100% | -100% | -59.74% | YES | 171250 | NO | NR
CapitalELECTRIC DISTRIBUTIONINCIDENT RESPONSE- NON-INCREMENTALNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | INCIDENT RESPONSE- NON-INCREMENTAL | Non-RAMP | Non-RAMP | Non-RAMP | 79773.8394 | 0 | 0 | 0 | 79773.8394 | 0 | 0 | 0 | 0 | 0 | 79773.8394 | 0 | 0 | 0 | 79773.8394 | 100% | 100% | 100% | 100% | 100% | YES | 93002 | NO | NR
CapitalELECTRIC DISTRIBUTIONKETTNER REBUILDNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | KETTNER REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | 614435.2899 | 0 | 0 | 0 | 614435.2899 | 0 | 0 | 0 | 0 | 0 | 614435.2899 | 0 | 0 | 0 | 614435.2899 | 100% | 100% | 100% | 100% | 100% | YES | 202510 | NO | NR
CapitalELECTRIC DISTRIBUTIONLA JOLLA 69/12KV TRANSFORMER REPLACEMENTElectric Infrastructure IntegrityLa Jolla 69/12kV Transformer ReplacementSubstation | Capital | ELECTRIC DISTRIBUTION | LA JOLLA 69/12KV TRANSFORMER REPLACEMENT | Electric Infrastructure Integrity | La Jolla 69/12kV Transformer Replacement | Substation | 116680.62 | 0 | 0 | 0 | 116680.62 | 135000 | 138999.96 | 142999.92 | 147000 | 563999.88 | -18319.38 | -138999.96 | -142999.92 | -147000 | -447319.26 | -13.57% | -100% | -100% | -100% | -79.31% | YES | 202750 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONLOCAL ENGINEERING POOL - ED POOLAsset ManagementAIMDAT (Data Analytics)N/A | Capital | ELECTRIC DISTRIBUTION | LOCAL ENGINEERING POOL - ED POOL | Asset Management | AIMDAT (Data Analytics) | N/A | 136881.3777 | 0 | 0 | 0 | 136881.3777 | 165000 | 169999.92 | 174999.96 | 180000 | 689999.88 | -28118.6223 | -169999.92 | -174999.96 | -180000 | -553118.5023 | -17.04% | -100% | -100% | -100% | -80.16% | YES | E09010 | YES | SDG&E-CFF-1
CapitalELECTRIC DISTRIBUTIONLOCAL ENGINEERING POOL - ED POOLNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | LOCAL ENGINEERING POOL - ED POOL | Non-RAMP | Non-RAMP | Non-RAMP | 168928568.4009 | 0 | 0 | 0 | 168928568.4009 | 102528000 | 105603999.96 | 108771999.96 | 112035000 | 428938999.92 | 66400568.4009 | -105603999.96 | -108771999.96 | -112035000 | -260010431.5191 | 64.76% | -100% | -100% | -100% | -60.62% | YES | E09010 | YES | NR
CapitalELECTRIC DISTRIBUTIONLOCAL ENGINEERING POOL - SUBSTATION POOL ELECNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | LOCAL ENGINEERING POOL - SUBSTATION POOL ELEC | Non-RAMP | Non-RAMP | Non-RAMP | 5269976.0031 | 0 | 0 | 0 | 5269976.0031 | 3289999.92 | 3388999.92 | 3490999.92 | 3595999.92 | 13765999.68 | 1979976.0831 | -3388999.92 | -3490999.92 | -3595999.92 | -8496023.6769 | 60.18% | -100% | -100% | -100% | -61.72% | YES | E09040 | YES | NR
CapitalELECTRIC DISTRIBUTIONMID-COAST TROLLEY EXTENSIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | MID-COAST TROLLEY EXTENSION | Non-RAMP | Non-RAMP | Non-RAMP | 1106.3117 | 0 | 0 | 0 | 1106.3117 | 0 | 0 | 0 | 0 | 0 | 1106.3117 | 0 | 0 | 0 | 1106.3117 | 100% | 100% | 100% | 100% | 100% | NO | 152580 | NO | NR
CapitalELECTRIC DISTRIBUTIONMISSION 138KV & 69KV SUB REBUILDNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | MISSION 138KV & 69KV SUB REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | 347546.8917 | 0 | 0 | 0 | 347546.8917 | 0 | 0 | 0 | 0 | 0 | 347546.8917 | 0 | 0 | 0 | 347546.8917 | 100% | 100% | 100% | 100% | 100% | YES | 181280 | NO | NR
CapitalELECTRIC DISTRIBUTIONMISSION DCC REMODEL PROJECTNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | MISSION DCC REMODEL PROJECT | Non-RAMP | Non-RAMP | Non-RAMP | 308798.777 | 0 | 0 | 0 | 308798.777 | 10347999.96 | 10657999.92 | 10977999.96 | 11307000 | 43290999.84 | -10039201.183 | -10657999.92 | -10977999.96 | -11307000 | -42982201.063 | -97.02% | -100% | -100% | -100% | -99.29% | YES | 212670 | NO | NR
CapitalELECTRIC DISTRIBUTIONNARROWS REBUILDNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | NARROWS REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | 1807.6072 | 0 | 0 | 0 | 1831.3972 | 0 | 0 | 0 | 0 | 0 | 1807.6072 | 0 | 0 | 0 | 1831.3972 | 100% | 100% | 100% | 100% | 100% | YES | 231260 | NO | NR
CapitalELECTRIC DISTRIBUTIONNEW BUSINESS INFRASTRUCTURENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | NEW BUSINESS INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | 4121060.1942 | 0 | 0 | 0 | 4121060.1942 | 6465000 | 6658999.92 | 6858999.96 | 7063999.92 | 27046999.8 | -2343939.8058 | -6658999.92 | -6858999.96 | -7063999.92 | -22925939.6058 | -36.26% | -100% | -100% | -100% | -84.76% | NO | 2190 | NO | NR
CapitalELECTRIC DISTRIBUTIONNEW DOWNTOWN 69/12KV SUBSTATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | NEW DOWNTOWN 69/12KV SUBSTATION | Non-RAMP | Non-RAMP | Non-RAMP | 26993.0993 | 0 | 0 | 0 | 26993.0993 | 0 | 0 | 0 | 0 | 0 | 26993.0993 | 0 | 0 | 0 | 26993.0993 | 100% | 100% | 100% | 100% | 100% | YES | 182510 | NO | NR
CapitalELECTRIC DISTRIBUTIONNEW SERVICE INSTALLATIONSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | NEW SERVICE INSTALLATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 10468002.3041 | 0 | 0 | 0 | 10468002.3041 | 8718000 | 8979999.96 | 9249999.96 | 9526999.92 | 36474999.84 | 1750002.3041 | -8979999.96 | -9249999.96 | -9526999.92 | -26006997.5359 | 20.07% | -100% | -100% | -100% | -71.3% | NO | 2240 | NO | NR
CapitalELECTRIC DISTRIBUTIONNORTH VALLEY 69/12KV SUBSTATION REBUILDElectric Infrastructure IntegrityNorth Valley (Morro Hill) Substation RebuildSubstation | Capital | ELECTRIC DISTRIBUTION | NORTH VALLEY 69/12KV SUBSTATION REBUILD | Electric Infrastructure Integrity | North Valley (Morro Hill) Substation Rebuild | Substation | 244548.5979 | 0 | 0 | 0 | 244548.5979 | 0 | 0 | 0 | 0 | 0 | 244548.5979 | 0 | 0 | 0 | 244548.5979 | 100% | 100% | 100% | 100% | 100% | YES | 242520 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONOH NON-RESIDENTIAL NBNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | OH NON-RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | 1352279.3242 | 0 | 0 | 0 | 1352279.3242 | 1278999.96 | 1317999.96 | 1357999.92 | 1398999.96 | 5353999.8 | 73279.3642 | -1317999.96 | -1357999.92 | -1398999.96 | -4001720.4758 | 5.729% | -100% | -100% | -100% | -74.74% | NO | 2160 | NO | NR
CapitalELECTRIC DISTRIBUTIONOH RESIDENTIAL NBNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | OH RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | 1898155.3411 | 0 | 0 | 0 | 1898155.3411 | 1050000 | 1080999.96 | 1113000 | 1146000 | 4389999.96 | 848155.3411 | -1080999.96 | -1113000 | -1146000 | -2491844.6189 | 80.78% | -100% | -100% | -100% | -56.76% | NO | 2150 | NO | NR
CapitalELECTRIC DISTRIBUTIONPLANNED INVESTMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | PLANNED INVESTMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 1929205.8878 | 0 | 0 | 0 | 1929205.8878 | 4432999.92 | 4566000 | 4702999.92 | 4843999.92 | 18545999.76 | -2503794.0322 | -4566000 | -4702999.92 | -4843999.92 | -16616793.8722 | -56.48% | -100% | -100% | -100% | -89.6% | YES | 202470 | NO | NR
CapitalELECTRIC DISTRIBUTIONPOLE LOADING REMEDIATION (NON-WMP)Non-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | POLE LOADING REMEDIATION (NON-WMP) | Non-RAMP | Non-RAMP | Non-RAMP | 384915.2603 | 0 | 0 | 0 | 384915.2603 | 0 | 0 | 0 | 0 | 0 | 384915.2603 | 0 | 0 | 0 | 384915.2603 | 100% | 100% | 100% | 100% | 100% | YES | 232480 | NO | NR
CapitalELECTRIC DISTRIBUTIONPURE WATER ELECTRICNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | PURE WATER ELECTRIC | Non-RAMP | Non-RAMP | Non-RAMP | -55764.5079 | 0 | 0 | 0 | -55764.5079 | 0 | 0 | 0 | 0 | 0 | -55764.5079 | 0 | 0 | 0 | -55764.5079 | 100% | 100% | 100% | 100% | 100% | NO | 182420 | NO | NR
CapitalELECTRIC DISTRIBUTIONRAMP - CORRECTIVE MAINTENANCE PROGRAM (CMP)Electric Infrastructure IntegrityGO165 Corrective Maintenance Program UndergroundUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP - CORRECTIVE MAINTENANCE PROGRAM (CMP) | Electric Infrastructure Integrity | GO165 Corrective Maintenance Program Underground | UG Distribution | 22351427.1534 | 0 | 0 | 0 | 22351427.1534 | 14073000 | 14494999.92 | 14929999.92 | 15378000 | 58875999.84 | 8278427.1534 | -14494999.92 | -14929999.92 | -15378000 | -36524572.6866 | 58.82% | -100% | -100% | -100% | -62.04% | YES | 2290 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP - INSTALL SCADA ON LINE CAPACITORSElectric Infrastructure IntegritySCADA CapacitorsOH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP - INSTALL SCADA ON LINE CAPACITORS | Electric Infrastructure Integrity | SCADA Capacitors | OH Distribution | 157783.5561 | 0 | 0 | 0 | 157783.5561 | 864000 | 889999.92 | 916999.92 | 943999.92 | 3614999.76 | -706216.4439 | -889999.92 | -916999.92 | -943999.92 | -3457216.2039 | -81.74% | -100% | -100% | -100% | -95.64% | YES | 112490 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP - INSTALL SCADA ON LINE CAPACITORSElectric Infrastructure IntegritySCADA CapacitorsUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP - INSTALL SCADA ON LINE CAPACITORS | Electric Infrastructure Integrity | SCADA Capacitors | UG Distribution | 67621.5305 | 0 | 0 | 0 | 67621.5305 | 369999.96 | 381000 | 391999.92 | 403999.92 | 1546999.8 | -302378.4295 | -381000 | -391999.92 | -403999.92 | -1479378.2695 | -81.72% | -100% | -100% | -100% | -95.63% | YES | 112490 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP - MANHOLE, HANDHOLE, AND VAULT RESTORATIONElectric Infrastructure IntegrityGO 165 Manhole, Vault Restoration ProgramManhole/Handhole | Capital | ELECTRIC DISTRIBUTION | RAMP - MANHOLE, HANDHOLE, AND VAULT RESTORATION | Electric Infrastructure Integrity | GO 165 Manhole, Vault Restoration Program | Manhole/Handhole | 4109581.5124 | 0 | 0 | 0 | 4109581.5124 | 5404999.92 | 5566999.92 | 5733999.96 | 5905999.92 | 22611999.72 | -1295418.4076 | -5566999.92 | -5733999.96 | -5905999.92 | -18502418.2076 | -23.97% | -100% | -100% | -100% | -81.83% | YES | 2890 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP - POLE REPLACEMENT AND REINFORCEMENTElectric Infrastructure IntegrityGO165 Pole Replacement ReinforcementN/A | Capital | ELECTRIC DISTRIBUTION | RAMP - POLE REPLACEMENT AND REINFORCEMENT | Electric Infrastructure Integrity | GO165 Pole Replacement Reinforcement | N/A | 19509318.2107 | 0 | 0 | 0 | 19509318.2107 | 15933000 | 16410999.96 | 16902999.96 | 17409999.96 | 66656999.88 | 3576318.2108 | -16410999.96 | -16902999.96 | -17409999.96 | -47147681.6692 | 22.45% | -100% | -100% | -100% | -70.73% | YES | 872320 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP - REPLACE OBSOLETE SUBSTATION EQUIPMENTElectric Infrastructure IntegrityDistribution Substation Obsolete EquipmentSubstation | Capital | ELECTRIC DISTRIBUTION | RAMP - REPLACE OBSOLETE SUBSTATION EQUIPMENT | Electric Infrastructure Integrity | Distribution Substation Obsolete Equipment | Substation | 1730617.5885 | 0 | 0 | 0 | 1730617.5885 | 2641999.92 | 2721000 | 2802999.96 | 2886999.96 | 11052999.84 | -911382.3315 | -2721000 | -2802999.96 | -2886999.96 | -9322382.2515 | -34.5% | -100% | -100% | -100% | -84.34% | YES | 992820 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP - STUART 12KV TRANSFORMER REPLACEMENTElectric Infrastructure IntegrityStuart 12kV Transformer ReplacementSubstation | Capital | ELECTRIC DISTRIBUTION | RAMP - STUART 12KV TRANSFORMER REPLACEMENT | Electric Infrastructure Integrity | Stuart 12kV Transformer Replacement | Substation | 0 | 0 | 0 | 0 | 0 | 1090999.92 | 1123999.92 | 1158000 | 1192999.92 | 4565999.76 | -1090999.92 | -1123999.92 | -1158000 | -1192999.92 | -4565999.76 | -100% | -100% | -100% | -100% | -100% | YES | 20270A | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- 4KV MODERNIZATIONElectric Infrastructure Integrity4kV Modernization Program DistributionOH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- 4KV MODERNIZATION | Electric Infrastructure Integrity | 4kV Modernization Program Distribution | OH Distribution | 223228.3275 | 0 | 0 | 0 | 226047.5675 | 8202000 | 8448000 | 8700999.96 | 8961999.96 | 34312999.92 | -7978771.6725 | -8448000 | -8700999.96 | -8961999.96 | -34086952.3525 | -97.28% | -100% | -100% | -100% | -99.34% | YES | 172690 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- AVIAN PROTECTIONElectric Infrastructure IntegrityAvian Protection ProgramOH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- AVIAN PROTECTION | Electric Infrastructure Integrity | Avian Protection Program | OH Distribution | 14459.5354 | 0 | 0 | 0 | 14459.5354 | 234000 | 240999.96 | 247999.92 | 255000 | 977999.88 | -219540.4646 | -240999.96 | -247999.92 | -255000 | -963540.3446 | -93.82% | -100% | -100% | -100% | -98.52% | YES | 102650 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- BERNARDO 12 KV BREAKERS AND TRANSFORMERElectric Infrastructure IntegritySubstation Reliability for Distribution Components Bernardo 12kV Breakers ReplacementsSubstation | Capital | ELECTRIC DISTRIBUTION | RAMP- BERNARDO 12 KV BREAKERS AND TRANSFORMER | Electric Infrastructure Integrity | Substation Reliability for Distribution Components Bernardo 12kV Breakers Replacements | Substation | 0 | 0 | 0 | 0 | 0 | 1161999.96 | 1197000 | 1233000 | 1269999.96 | 4861999.92 | -1161999.96 | -1197000 | -1233000 | -1269999.96 | -4861999.92 | -100% | -100% | -100% | -100% | -100% | YES | 20263A | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- CAPITAL RESTORATION OF SERVICEElectric Infrastructure IntegrityRestoration of ServiceN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- CAPITAL RESTORATION OF SERVICE | Electric Infrastructure Integrity | Restoration of Service | N/A | 10933651.1225 | 0 | 0 | 0 | 10933651.1225 | 11937999.96 | 12295999.92 | 12664999.92 | 13044999.96 | 49943999.76 | -1004348.8375 | -12295999.92 | -12664999.92 | -13044999.96 | -39010348.6375 | -8.413% | -100% | -100% | -100% | -78.11% | YES | 2360 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- DISTRIBUTION CIRCUIT RELIABILITY CONSTRUCTIONElectric Infrastructure IntegrityDistribution Circuit ReliabilityOH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- DISTRIBUTION CIRCUIT RELIABILITY CONSTRUCTION | Electric Infrastructure Integrity | Distribution Circuit Reliability | OH Distribution | 691728.9509 | 0 | 0 | 0 | 691728.9509 | 2067999.96 | 2130999.96 | 2193999.96 | 2260999.92 | 8653999.8 | -1376271.0091 | -2130999.96 | -2193999.96 | -2260999.92 | -7962270.8491 | -66.55% | -100% | -100% | -100% | -92.01% | YES | 932400 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- DISTRIBUTION CIRCUIT RELIABILITY CONSTRUCTIONElectric Infrastructure IntegrityDistribution Circuit ReliabilityUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- DISTRIBUTION CIRCUIT RELIABILITY CONSTRUCTION | Electric Infrastructure Integrity | Distribution Circuit Reliability | UG Distribution | 1037593.4313 | 0 | 0 | 0 | 1037593.4313 | 3102000 | 3193999.92 | 3291000 | 3388999.92 | 12975999.84 | -2064406.5687 | -3193999.92 | -3291000 | -3388999.92 | -11938406.4087 | -66.55% | -100% | -100% | -100% | -92% | YES | 932400 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- DISTRIBUTION SUBSTATION RELIABILITYElectric Infrastructure IntegrityMinor Distribution Substation Reliability ProjectsN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- DISTRIBUTION SUBSTATION RELIABILITY | Electric Infrastructure Integrity | Minor Distribution Substation Reliability Projects | N/A | 1572500.7445 | 0 | 0 | 0 | 1572500.7445 | 1725000 | 1776999.96 | 1830000 | 1884999.96 | 7216999.92 | -152499.2555 | -1776999.96 | -1830000 | -1884999.96 | -5644499.1755 | -8.841% | -100% | -100% | -100% | -78.21% | YES | 2030 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- DOE SWITCH REPLACEMENTElectric Infrastructure IntegrityDOE Switch Replacement UndergroundUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- DOE SWITCH REPLACEMENT | Electric Infrastructure Integrity | DOE Switch Replacement Underground | UG Distribution | 2325336.0586 | 0 | 0 | 0 | 2325336.0586 | 7248999.96 | 7465999.92 | 7689999.96 | 7920999.96 | 30325999.8 | -4923663.9014 | -7465999.92 | -7689999.96 | -7920999.96 | -28000663.7414 | -67.92% | -100% | -100% | -100% | -92.33% | YES | 2900 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- EL CAJON 12KV BREAKER REPLACEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | RAMP- EL CAJON 12KV BREAKER REPLACEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 2112103.2225 | 0 | 0 | 0 | 2112103.2225 | 0 | 0 | 0 | 0 | 0 | 2112103.2225 | 0 | 0 | 0 | 2112103.2225 | 100% | 100% | 100% | 100% | 100% | YES | 202450 | NO | NR
CapitalELECTRIC DISTRIBUTIONRAMP- EMERGENCY TRANSFORMER & SWITCHGEARElectric Infrastructure IntegrityEmergency Transformer and SwitchgearN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- EMERGENCY TRANSFORMER & SWITCHGEAR | Electric Infrastructure Integrity | Emergency Transformer and Switchgear | N/A | 960873.6458 | 0 | 0 | 0 | 960873.6458 | 418999.92 | 432000 | 444999.96 | 457999.92 | 1753999.8 | 541873.7258 | -432000 | -444999.96 | -457999.92 | -793126.1542 | 129.3% | -100% | -100% | -100% | -45.22% | YES | 62540 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- ENERGIZED TEST YARDNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | RAMP- ENERGIZED TEST YARD | Non-RAMP | Non-RAMP | Non-RAMP | 52414.856 | 0 | 0 | 0 | 52414.856 | 0 | 0 | 0 | 0 | 0 | 52414.856 | 0 | 0 | 0 | 52414.856 | 100% | 100% | 100% | 100% | 100% | YES | 172590 | NO | NR
CapitalELECTRIC DISTRIBUTIONRAMP- HIGH RISK SWITCH REPLACEMENT PROJECTElectric Infrastructure IntegrityDistribution Overhead Switch Replacement ProgramOH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- HIGH RISK SWITCH REPLACEMENT PROJECT | Electric Infrastructure Integrity | Distribution Overhead Switch Replacement Program | OH Distribution | 352453.3514 | 0 | 0 | 0 | 352453.3514 | 1042999.92 | 1074000 | 1105999.92 | 1138999.92 | 4361999.76 | -690546.5686 | -1074000 | -1105999.92 | -1138999.92 | -4009546.4086 | -66.21% | -100% | -100% | -100% | -91.92% | YES | 172610 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- MANAGEMENT OF OH DIST. SERVICEElectric Infrastructure IntegrityManagement of Overhead Distribution Service (Non-CMP)N/A | Capital | ELECTRIC DISTRIBUTION | RAMP- MANAGEMENT OF OH DIST. SERVICE | Electric Infrastructure Integrity | Management of Overhead Distribution Service (Non-CMP) | N/A | 10643741.7925 | 0 | 0 | 0 | 10643741.7925 | 10176000 | 10480999.92 | 10794999.96 | 11118999.96 | 42570999.84 | 467741.7925 | -10480999.92 | -10794999.96 | -11118999.96 | -31927258.0475 | 4.597% | -100% | -100% | -100% | -75% | YES | 2260 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- MANAGEMENT OF UG DIST. SERVICEElectric Infrastructure IntegrityManagement of Underground Distribution ServiceN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- MANAGEMENT OF UG DIST. SERVICE | Electric Infrastructure Integrity | Management of Underground Distribution Service | N/A | 6217438.171 | 0 | 0 | 0 | 6217438.171 | 4203999.96 | 4329999.96 | 4459999.92 | 4593999.96 | 17587999.8 | 2013438.211 | -4329999.96 | -4459999.92 | -4593999.96 | -11370561.629 | 47.89% | -100% | -100% | -100% | -64.65% | YES | 2270 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- MIRAMAR 12KV REPLACEMENTSElectric Infrastructure IntegritySubstation Reliability for Distribution Components Miramar 12kV ReplacementsSubstation | Capital | ELECTRIC DISTRIBUTION | RAMP- MIRAMAR 12KV REPLACEMENTS | Electric Infrastructure Integrity | Substation Reliability for Distribution Components Miramar 12kV Replacements | Substation | 39854.6104 | 0 | 0 | 0 | 960683.6304 | 123999.96 | 127999.92 | 132000 | 135999.96 | 519999.84 | -84145.3496 | -127999.92 | -132000 | -135999.96 | 440683.7904 | -67.86% | -100% | -100% | -100% | 84.75% | YES | 20267A | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- MISSION 12KV REPLACEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | RAMP- MISSION 12KV REPLACEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 1372390.4749 | 0 | 0 | 0 | 1372390.4749 | 0 | 0 | 0 | 0 | 0 | 1372390.4749 | 0 | 0 | 0 | 1372390.4749 | 100% | 100% | 100% | 100% | 100% | YES | 202680 | NO | NR
CapitalELECTRIC DISTRIBUTIONRAMP- NORTH HARBORElectric Infrastructure IntegrityUnderground Cable Replacement Program Proactive North Harbor ProjectUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- NORTH HARBOR | Electric Infrastructure Integrity | Underground Cable Replacement Program Proactive North Harbor Project | UG Distribution | 0 | 0 | 0 | 0 | 0 | 9729999.96 | 10021999.92 | 10323000 | 10632999.96 | 40707999.84 | -9729999.96 | -10021999.92 | -10323000 | -10632999.96 | -40707999.84 | -100% | -100% | -100% | -100% | -100% | YES | 17264A | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- OH PUBLIC SAFETY (OPS)Electric Infrastructure IntegrityOverhead Public Safety (OPS) ProgramOH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- OH PUBLIC SAFETY (OPS) | Electric Infrastructure Integrity | Overhead Public Safety (OPS) Program | OH Distribution | 290606.7644 | 0 | 0 | 0 | 290606.7644 | 8464999.92 | 8718999.96 | 8980999.92 | 9249999.96 | 35414999.76 | -8174393.1556 | -8718999.96 | -8980999.92 | -9249999.96 | -35124392.9956 | -96.57% | -100% | -100% | -100% | -99.18% | YES | 202410 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- PLANNED CABLE REPLACEMENTSElectric Infrastructure IntegrityUnderground Cable Replacement Program ProactiveUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- PLANNED CABLE REPLACEMENTS | Electric Infrastructure Integrity | Underground Cable Replacement Program Proactive | UG Distribution | 3307576.6794 | 0 | 0 | 0 | 3307576.6794 | 4300999.92 | 4429999.92 | 4563000 | 4699999.92 | 17993999.76 | -993423.2406 | -4429999.92 | -4563000 | -4699999.92 | -14686423.0806 | -23.1% | -100% | -100% | -100% | -81.62% | YES | 2380 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- POWER QUALITY PROGRAMElectric Infrastructure IntegrityPower Quality Monitor Deployment and ReplacementN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- POWER QUALITY PROGRAM | Electric Infrastructure Integrity | Power Quality Monitor Deployment and Replacement | N/A | 284694.2794 | 0 | 0 | 0 | 284694.2794 | 2883999.96 | 2970000 | 3058999.92 | 3150999.96 | 12063999.84 | -2599305.6806 | -2970000 | -3058999.92 | -3150999.96 | -11779305.5606 | -90.13% | -100% | -100% | -100% | -97.64% | YES | 942410 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- PROACTIVE DEAD FRONT TERMINATOR DEPLOYElectric Infrastructure IntegrityReplacement of Live Front Equipment - ProactiveUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- PROACTIVE DEAD FRONT TERMINATOR DEPLOY | Electric Infrastructure Integrity | Replacement of Live Front Equipment - Proactive | UG Distribution | 62710.6761 | 0 | 0 | 0 | 62710.6761 | 885000 | 912000 | 939000 | 966999.96 | 3702999.96 | -822289.3239 | -912000 | -939000 | -966999.96 | -3640289.2839 | -92.91% | -100% | -100% | -100% | -98.31% | YES | 192410 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- REPLACEMENT OF LIVE FRONT EQUIPMENTElectric Infrastructure IntegrityReplacement of Live Front Equipment - ReactiveN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- REPLACEMENT OF LIVE FRONT EQUIPMENT | Electric Infrastructure Integrity | Replacement of Live Front Equipment - Reactive | N/A | 1461.7981 | 0 | 0 | 0 | 1461.7981 | 457999.92 | 471999.96 | 486000 | 501000 | 1916999.88 | -456538.1219 | -471999.96 | -486000 | -501000 | -1915538.0819 | -99.68% | -100% | -100% | -100% | -99.92% | YES | 62470 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- REPLACEMENT OF UNDERGROUND CABLESElectric Infrastructure IntegrityUnderground Cable Replacement Program ReactiveN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- REPLACEMENT OF UNDERGROUND CABLES | Electric Infrastructure Integrity | Underground Cable Replacement Program Reactive | N/A | 6595683.4153 | 0 | 0 | 0 | 6595683.4153 | 7269999.96 | 7488000 | 7713000 | 7944000 | 30414999.96 | -674316.5447 | -7488000 | -7713000 | -7944000 | -23819316.5447 | -9.275% | -100% | -100% | -100% | -78.31% | YES | 2300 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- RTU MODERNIZATIONElectric Infrastructure IntegrityField SCADA RTU ReplacementUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- RTU MODERNIZATION | Electric Infrastructure Integrity | Field SCADA RTU Replacement | UG Distribution | 771162.5481 | 0 | 0 | 0 | 771162.5481 | 792000 | 816000 | 840000 | 864999.96 | 3312999.96 | -20837.4519 | -816000 | -840000 | -864999.96 | -2541837.4119 | -2.631% | -100% | -100% | -100% | -76.72% | YES | 162770 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- SAN MARCOS SUB REBUILD 69KV & 12KVElectric Infrastructure IntegritySan Marcos Substation 69kV Rebuild & 12kV SwitchgearSubstation | Capital | ELECTRIC DISTRIBUTION | RAMP- SAN MARCOS SUB REBUILD 69KV & 12KV | Electric Infrastructure Integrity | San Marcos Substation 69kV Rebuild & 12kV Switchgear | Substation | -408022.45 | 0 | 0 | 0 | -408022.45 | 126999.96 | 130999.92 | 135000 | 138999.96 | 531999.84 | -535022.41 | -130999.92 | -135000 | -138999.96 | -940022.29 | -421.3% | -100% | -100% | -100% | -176.7% | YES | 171600 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- SUBSTATION MOD TO SUPPORT FLISRNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | RAMP- SUBSTATION MOD TO SUPPORT FLISR | Non-RAMP | Non-RAMP | Non-RAMP | 34174.1568 | 0 | 0 | 0 | 34174.1568 | 0 | 0 | 0 | 0 | 0 | 34174.1568 | 0 | 0 | 0 | 34174.1568 | 100% | 100% | 100% | 100% | 100% | YES | 172430 | NO | NR
CapitalELECTRIC DISTRIBUTIONRAMP- SUBSTATION SCADA EXPANSION-DISTRIBUTIONElectric Infrastructure IntegrityDistribution Substation SCADA ExpansionN/A | Capital | ELECTRIC DISTRIBUTION | RAMP- SUBSTATION SCADA EXPANSION-DISTRIBUTION | Electric Infrastructure Integrity | Distribution Substation SCADA Expansion | N/A | 413311.0112 | 0 | 0 | 0 | 413311.0112 | 2226999.96 | 2293999.92 | 2362999.92 | 2433999.96 | 9317999.76 | -1813688.9488 | -2293999.92 | -2362999.92 | -2433999.96 | -8904688.7488 | -81.44% | -100% | -100% | -100% | -95.56% | YES | 152430 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- TEE MODERNIZATION PROGRAMElectric Infrastructure IntegrityTee Modernization ProgramUG Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP- TEE MODERNIZATION PROGRAM | Electric Infrastructure Integrity | Tee Modernization Program | UG Distribution | 4922184.7913 | 0 | 0 | 0 | 4904813.8813 | 4431999.96 | 4564999.92 | 4701999.96 | 4842999.96 | 18541999.8 | 490184.8313 | -4564999.92 | -4701999.96 | -4842999.96 | -13637185.9187 | 11.06% | -100% | -100% | -100% | -73.55% | YES | 172550 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP- TORREY PINES 12KV BREAKER REPLACEMENTNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | RAMP- TORREY PINES 12KV BREAKER REPLACEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 858683.4809 | 0 | 0 | 0 | 858683.4809 | 0 | 0 | 0 | 0 | 0 | 858683.4809 | 0 | 0 | 0 | 858683.4809 | 100% | 100% | 100% | 100% | 100% | YES | 202420 | NO | NR
CapitalELECTRIC DISTRIBUTIONRAMP- URBAN SUBSTATION REBUILDNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | RAMP- URBAN SUBSTATION REBUILD | Non-RAMP | Non-RAMP | Non-RAMP | 463710.5787 | 0 | 0 | 0 | 463710.5787 | 0 | 0 | 0 | 0 | 0 | 463710.5787 | 0 | 0 | 0 | 463710.5787 | 100% | 100% | 100% | 100% | 100% | YES | 192520 | NO | NR
CapitalELECTRIC DISTRIBUTIONRAMP-NON-HFTD WIRELESS FAULT INDICATORSElectric Infrastructure IntegrityNon-HFTD Wireless Fault IndicatorOH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP-NON-HFTD WIRELESS FAULT INDICATORS | Electric Infrastructure Integrity | Non-HFTD Wireless Fault Indicator | OH Distribution | 0 | 0 | 0 | 0 | 0 | 1557999.96 | 1605000 | 1653000 | 1702999.92 | 6518999.88 | -1557999.96 | -1605000 | -1653000 | -1702999.92 | -6518999.88 | -100% | -100% | -100% | -100% | -100% | YES | 202880 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONRAMP-STRATEGIC POLE REPLACEMENT PROGRAM (NON-HFTD)Electric Infrastructure IntegrityStrategic Pole Replacement Program (Non-HFTD)OH Distribution | Capital | ELECTRIC DISTRIBUTION | RAMP-STRATEGIC POLE REPLACEMENT PROGRAM (NON-HFTD) | Electric Infrastructure Integrity | Strategic Pole Replacement Program (Non-HFTD) | OH Distribution | 12772.2659 | 0 | 0 | 0 | 12772.2659 | 7512999.96 | 7737999.96 | 7969999.92 | 8208999.96 | 31429999.8 | -7500227.6941 | -7737999.96 | -7969999.92 | -8208999.96 | -31417227.5341 | -99.83% | -100% | -100% | -100% | -99.96% | YES | 222410 | NO | SDG&E-Risk-2
CapitalELECTRIC DISTRIBUTIONREACTIVE SMALL CAPITAL PROJECTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | REACTIVE SMALL CAPITAL PROJECTS | Non-RAMP | Non-RAMP | Non-RAMP | 3110031.1479 | 0 | 0 | 0 | 3110031.1479 | 1576999.92 | 1623999.96 | 1672999.92 | 1722999.96 | 6596999.76 | 1533031.2279 | -1623999.96 | -1672999.92 | -1722999.96 | -3486968.6121 | 97.21% | -100% | -100% | -100% | -52.86% | YES | 2280 | NO | NR
CapitalELECTRIC DISTRIBUTIONREBUILDING OF SKILLS TRAINING YARDNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | REBUILDING OF SKILLS TRAINING YARD | Non-RAMP | Non-RAMP | Non-RAMP | 1269688.7209 | 0 | 0 | 0 | 1269688.7209 | 0 | 0 | 0 | 0 | 0 | 1269688.7209 | 0 | 0 | 0 | 1269688.7209 | 100% | 100% | 100% | 100% | 100% | YES | 202870 | NO | NR
CapitalELECTRIC DISTRIBUTIONRFS JAPANESE MESA SUBSTATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | RFS JAPANESE MESA SUBSTATION | Non-RAMP | Non-RAMP | Non-RAMP | 108089.0073 | 0 | 0 | 0 | 108089.0073 | 0 | 0 | 0 | 0 | 0 | 108089.0073 | 0 | 0 | 0 | 108089.0073 | 100% | 100% | 100% | 100% | 100% | YES | 211530 | NO | NR
CapitalELECTRIC DISTRIBUTIONSCADA EXPANSION-TRANSMISSIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SCADA EXPANSION-TRANSMISSION | Non-RAMP | Non-RAMP | Non-RAMP | 5425.9915 | 0 | 0 | 0 | 5425.9915 | 0 | 0 | 0 | 0 | 0 | 5425.9915 | 0 | 0 | 0 | 5425.9915 | 100% | 100% | 100% | 100% | 100% | YES | 121320 | NO | NR
CapitalELECTRIC DISTRIBUTIONSCADA HEAD-END REPLACEMENTNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SCADA HEAD-END REPLACEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 21995.217 | 0 | 0 | 0 | 21995.217 | 0 | 0 | 0 | 0 | 0 | 21995.217 | 0 | 0 | 0 | 21995.217 | 100% | 100% | 100% | 100% | 100% | YES | 162760 | NO | NR
CapitalELECTRIC DISTRIBUTIONSF6 SWITCH REPLACEMENTNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SF6 SWITCH REPLACEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 67464.3065 | 0 | 0 | 0 | 67464.3065 | 7875999.96 | 8112000 | 8355000 | 8605999.92 | 32948999.88 | -7808535.6535 | -8112000 | -8355000 | -8605999.92 | -32881535.5735 | -99.14% | -100% | -100% | -100% | -99.8% | YES | 142490 | NO | NR
CapitalELECTRIC DISTRIBUTIONSOUTH ORANGE COUNTY RELIABILITY ENHANCEMENT (SOCRE)Non-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SOUTH ORANGE COUNTY RELIABILITY ENHANCEMENT (SOCRE) | Non-RAMP | Non-RAMP | Non-RAMP | 268144.1598 | 0 | 0 | 0 | 268144.1598 | 112999.92 | 117000 | 120999.96 | 124999.92 | 475999.8 | 155144.2398 | -117000 | -120999.96 | -124999.92 | -207855.6402 | 137.3% | -100% | -100% | -100% | -43.67% | YES | 61290 | NO | NR
CapitalELECTRIC DISTRIBUTIONSTREAMVIEW 69/12KV SUB REBUILD-PRE ENGNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | STREAMVIEW 69/12KV SUB REBUILD-PRE ENG | Non-RAMP | Non-RAMP | Non-RAMP | 3023980.8658 | 0 | 0 | 0 | 3023980.8658 | 198999.96 | 204999.96 | 210999.96 | 216999.96 | 831999.84 | 2824980.9058 | -204999.96 | -210999.96 | -216999.96 | 2191981.0258 | 1420% | -100% | -100% | -100% | 263.5% | YES | 132440 | NO | NR
CapitalELECTRIC DISTRIBUTIONSTREET LIGHT MODERNIZATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | STREET LIGHT MODERNIZATION | Non-RAMP | Non-RAMP | Non-RAMP | 857964.8723 | 0 | 0 | 0 | 1075034.5223 | 4462999.92 | 4596999.96 | 4734999.96 | 4876999.92 | 18671999.76 | -3605035.0477 | -4596999.96 | -4734999.96 | -4876999.92 | -17596965.2376 | -80.78% | -100% | -100% | -100% | -94.24% | YES | 172620 | NO | NR
CapitalELECTRIC DISTRIBUTIONSUB EXTERNALLY ROUTABLE CONNECTIV (SERC)Non-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SUB EXTERNALLY ROUTABLE CONNECTIV (SERC) | Non-RAMP | Non-RAMP | Non-RAMP | 52651.8246 | 0 | 0 | 0 | 52651.8246 | 0 | 0 | 0 | 0 | 0 | 52651.8246 | 0 | 0 | 0 | 52651.8246 | 100% | 100% | 100% | 100% | 100% | YES | 231290 | NO | NR
CapitalELECTRIC DISTRIBUTIONSUBSTATION 12KV CAPACITOR UPGRADESNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SUBSTATION 12KV CAPACITOR UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | 703010.5072 | 0 | 0 | 0 | 703010.5072 | 1611000 | 1659000 | 1708999.92 | 1759999.92 | 6738999.84 | -907989.4928 | -1659000 | -1708999.92 | -1759999.92 | -6035989.3328 | -56.36% | -100% | -100% | -100% | -89.57% | YES | 82530 | NO | NR
CapitalELECTRIC DISTRIBUTIONSUBSTATION DC RELIABILITY UPGRADE PROJNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SUBSTATION DC RELIABILITY UPGRADE PROJ | Non-RAMP | Non-RAMP | Non-RAMP | 4981.3512 | 0 | 0 | 0 | 4981.3512 | 0 | 0 | 0 | 0 | 0 | 4981.3512 | 0 | 0 | 0 | 4981.3512 | 100% | 100% | 100% | 100% | 100% | YES | 161380 | NO | NR
CapitalELECTRIC DISTRIBUTIONSUBSTATION SECURITY PROJ UNDER $500KNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SUBSTATION SECURITY PROJ UNDER $500K | Non-RAMP | Non-RAMP | Non-RAMP | 327895.7277 | 0 | 0 | 0 | 327895.7277 | 0 | 0 | 0 | 0 | 0 | 327895.7277 | 0 | 0 | 0 | 327895.7277 | 100% | 100% | 100% | 100% | 100% | YES | 161260 | NO | NR
CapitalELECTRIC DISTRIBUTIONSYNCHRONIZED PHASOR MEASUREMENT SYSTEMNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | SYNCHRONIZED PHASOR MEASUREMENT SYSTEM | Non-RAMP | Non-RAMP | Non-RAMP | -360730.8052 | 0 | 0 | 0 | -353689.7752 | 0 | 0 | 0 | 0 | 0 | -360730.8052 | 0 | 0 | 0 | -353689.7752 | 100% | 100% | 100% | 100% | 100% | YES | 101380 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL23001 TL23004 INSULATOR AND HARDWARE RNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL23001 TL23004 INSULATOR AND HARDWARE R | Non-RAMP | Non-RAMP | Non-RAMP | 5681.95 | 0 | 0 | 0 | 5687.27 | 0 | 0 | 0 | 0 | 0 | 5681.95 | 0 | 0 | 0 | 5687.27 | 100% | 100% | 100% | 100% | 100% | YES | 201380 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL600 - RELIABILITY POLE REPLACEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL600 - RELIABILITY POLE REPLACEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 93182.1803 | 0 | 0 | 0 | 93182.1803 | 0 | 0 | 0 | 0 | 0 | 93182.1803 | 0 | 0 | 0 | 93182.1803 | 100% | 100% | 100% | 100% | 100% | YES | 121560 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL603B SWEETWATER TAP REMOVALNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL603B SWEETWATER TAP REMOVAL | Non-RAMP | Non-RAMP | Non-RAMP | 1492.151 | 0 | 0 | 0 | 1492.151 | 0 | 0 | 0 | 0 | 0 | 1492.151 | 0 | 0 | 0 | 1492.151 | 100% | 100% | 100% | 100% | 100% | YES | 171290 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL605 RECONDUCTOR: SILVERGATE - URBANNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL605 RECONDUCTOR: SILVERGATE - URBAN | Non-RAMP | Non-RAMP | Non-RAMP | 211078.2505 | 0 | 0 | 0 | 211078.2505 | 0 | 0 | 0 | 0 | 0 | 211078.2505 | 0 | 0 | 0 | 211078.2505 | 100% | 100% | 100% | 100% | 100% | YES | 161580 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL634 JUNIPER STREET CUSTOMER RELOCATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL634 JUNIPER STREET CUSTOMER RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | 157856.5227 | 0 | 0 | 0 | 157856.5227 | 0 | 0 | 0 | 0 | 0 | 157856.5227 | 0 | 0 | 0 | 157856.5227 | 100% | 100% | 100% | 100% | 100% | NO | 21139A | NO | NR
CapitalELECTRIC DISTRIBUTIONTL667 SAN DIEGUITO RELOCATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL667 SAN DIEGUITO RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | 9537.6326 | 0 | 0 | 0 | 9559.3926 | 0 | 0 | 0 | 0 | 0 | 9537.6326 | 0 | 0 | 0 | 9559.3926 | 100% | 100% | 100% | 100% | 100% | NO | 191280 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL673 RN-LJ DB CABLE REPLACENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL673 RN-LJ DB CABLE REPLACE | Non-RAMP | Non-RAMP | Non-RAMP | 953.153 | 0 | 0 | 0 | 953.153 | 0 | 0 | 0 | 0 | 0 | 953.153 | 0 | 0 | 0 | 953.153 | 100% | 100% | 100% | 100% | 100% | YES | 171520 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL674A DEL MAR RECONFIGURE/TL666D RFSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL674A DEL MAR RECONFIGURE/TL666D RFS | Non-RAMP | Non-RAMP | Non-RAMP | 158885.4882 | 0 | 0 | 0 | -131931.9918 | 0 | 0 | 0 | 0 | 0 | 158885.4882 | 0 | 0 | 0 | -131931.9918 | 100% | 100% | 100% | 100% | 100% | YES | 131300 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL6975 ESCONDIDO - SAN MARCOSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL6975 ESCONDIDO - SAN MARCOS | Non-RAMP | Non-RAMP | Non-RAMP | 26484.8934 | 0 | 0 | 0 | 26484.8934 | 0 | 0 | 0 | 0 | 0 | 26484.8934 | 0 | 0 | 0 | 26484.8934 | 100% | 100% | 100% | 100% | 100% | YES | 141370 | NO | NR
CapitalELECTRIC DISTRIBUTIONTL698 MEADOWOOD RELOCATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TL698 MEADOWOOD RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | -23099.1551 | 0 | 0 | 0 | -23099.1551 | 0 | 0 | 0 | 0 | 0 | -23099.1551 | 0 | 0 | 0 | -23099.1551 | 100% | 100% | 100% | 100% | 100% | NO | 191350 | NO | NR
CapitalELECTRIC DISTRIBUTIONTRANSFORMER & METER INSTALLATIONSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TRANSFORMER & METER INSTALLATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 9477792.2103 | 0 | 0 | 0 | 9477792.2103 | 11716999.92 | 12069000 | 12430999.92 | 12804000 | 49020999.84 | -2239207.7097 | -12069000 | -12430999.92 | -12804000 | -39543207.6297 | -19.11% | -100% | -100% | -100% | -80.67% | NO | 2350 | NO | NR
CapitalELECTRIC DISTRIBUTIONTRANSFORMERSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TRANSFORMERS | Non-RAMP | Non-RAMP | Non-RAMP | 83157014.94 | 0 | 0 | 0 | 103024703.99 | 33174000 | 34168999.92 | 35193999.96 | 36249999.96 | 138786999.84 | 49983014.94 | -34168999.92 | -35193999.96 | -36249999.96 | -35762295.85 | 150.7% | -100% | -100% | -100% | -25.77% | YES | 2140 | NO | NR
CapitalELECTRIC DISTRIBUTIONTRANSMISSION CORRECTIVE MAINTENANCE PROGRAMNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TRANSMISSION CORRECTIVE MAINTENANCE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | 2473620.6697 | 0 | 0 | 0 | 2473620.6697 | 3769999.92 | 3882999.96 | 3999000 | 4119000 | 15770999.88 | -1296379.2504 | -3882999.96 | -3999000 | -4119000 | -13297379.2103 | -34.39% | -100% | -100% | -100% | -84.32% | YES | 201260 | NO | NR
CapitalELECTRIC DISTRIBUTIONTRANSMISSION EMS/SCADA RELIANCE UPGRADENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TRANSMISSION EMS/SCADA RELIANCE UPGRADE | Non-RAMP | Non-RAMP | Non-RAMP | 373883.8247 | 0 | 0 | 0 | 373883.8247 | 0 | 0 | 0 | 0 | 0 | 373883.8247 | 0 | 0 | 0 | 373883.8247 | 100% | 100% | 100% | 100% | 100% | YES | 211550 | NO | NR
CapitalELECTRIC DISTRIBUTIONTRANSMISSION INFRASTRUCTURE IMPROVEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TRANSMISSION INFRASTRUCTURE IMPROVEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 28032.7485 | 0 | 0 | 0 | 28032.7485 | 0 | 0 | 0 | 0 | 0 | 28032.7485 | 0 | 0 | 0 | 28032.7485 | 100% | 100% | 100% | 100% | 100% | YES | 11450 | NO | NR
CapitalELECTRIC DISTRIBUTIONTRANSMISSION SUBSTATION RELIABILITYNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TRANSMISSION SUBSTATION RELIABILITY | Non-RAMP | Non-RAMP | Non-RAMP | 56460.7043 | 0 | 0 | 0 | 56460.7043 | 0 | 0 | 0 | 0 | 0 | 56460.7043 | 0 | 0 | 0 | 56460.7043 | 100% | 100% | 100% | 100% | 100% | YES | 1030 | NO | NR
CapitalELECTRIC DISTRIBUTIONTRANSMISSION SYSTEM AUTOMATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | TRANSMISSION SYSTEM AUTOMATION | Non-RAMP | Non-RAMP | Non-RAMP | 80603.3316 | 0 | 0 | 0 | 80603.3316 | 0 | 0 | 0 | 0 | 0 | 80603.3316 | 0 | 0 | 0 | 80603.3316 | 100% | 100% | 100% | 100% | 100% | YES | 31710 | NO | NR
CapitalELECTRIC DISTRIBUTIONUG NON-RESIDENTIAL NBNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | UG NON-RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | 12609107.6087 | 0 | 0 | 0 | 12609107.6087 | 9693999.96 | 9984999.96 | 10284999.96 | 10593999.96 | 40557999.84 | 2915107.6487 | -9984999.96 | -10284999.96 | -10593999.96 | -27948892.2313 | 30.07% | -100% | -100% | -100% | -68.91% | NO | 2180 | NO | NR
CapitalELECTRIC DISTRIBUTIONUG RESIDENTIAL NBNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | UG RESIDENTIAL NB | Non-RAMP | Non-RAMP | Non-RAMP | 13356102.1343 | 0 | 0 | 0 | 13356102.1343 | 9091999.92 | 9364999.92 | 9645999.96 | 9934999.92 | 38037999.72 | 4264102.2143 | -9364999.92 | -9645999.96 | -9934999.92 | -24681897.5857 | 46.9% | -100% | -100% | -100% | -64.89% | NO | 2170 | NO | NR
CapitalELECTRIC DISTRIBUTIONVALENCIA POINTE RELOCATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | VALENCIA POINTE RELOCATION | Non-RAMP | Non-RAMP | Non-RAMP | -3625.82 | 0 | 0 | 0 | -3625.82 | 0 | 0 | 0 | 0 | 0 | -3625.82 | 0 | 0 | 0 | -3625.82 | 100% | 100% | 100% | 100% | 100% | NO | 201320 | NO | NR
CapitalELECTRIC DISTRIBUTIONWORKLOAD MANAGEMENT APPLICATIONNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC DISTRIBUTION | WORKLOAD MANAGEMENT APPLICATION | Non-RAMP | Non-RAMP | Non-RAMP | 1217992.1897 | 0 | 0 | 0 | 1217992.1897 | 0 | 0 | 0 | 0 | 0 | 1217992.1897 | 0 | 0 | 0 | 1217992.1897 | 100% | 100% | 100% | 100% | 100% | NO | 232570 | NO | NR
CapitalELECTRIC GENERATIONCUYAMACA PEAK ENERGY PLANT OPER ENHANCENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | CUYAMACA PEAK ENERGY PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | 218157.42 | 0 | 0 | 0 | 218157.42 | 651000 | 670999.92 | 690999.96 | 711999.96 | 2724999.84 | -432842.58 | -670999.92 | -690999.96 | -711999.96 | -2506842.42 | -66.49% | -100% | -100% | -100% | -91.99% | YES | 110 | NO | NR
CapitalELECTRIC GENERATIONDESERT STAR ENERGY CTR OPER. ENHANCENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | DESERT STAR ENERGY CTR OPER. ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | 4350452.2325 | 0 | 0 | 0 | 5018296.9425 | 5509999.92 | 5674999.92 | 5844999.96 | 6019999.92 | 23049999.72 | -1159547.6875 | -5674999.92 | -5844999.96 | -6019999.92 | -18031702.7775 | -21.04% | -100% | -100% | -100% | -78.23% | YES | 100 | NO | NR
CapitalELECTRIC GENERATIONEL CAJON BESS PLANT OPER ENHANCENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | EL CAJON BESS PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | -577.92 | 0 | 0 | 0 | -577.92 | 0 | 0 | 0 | 0 | 0 | -577.92 | 0 | 0 | 0 | -577.92 | 100% | 100% | 100% | 100% | 100% | YES | 130 | NO | NR
CapitalELECTRIC GENERATIONESCONDIDO BESS PLANT OPER ENHANCENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | ESCONDIDO BESS PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | 660 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 660 | 100% | 100% | 100% | 100% | 100% | YES | 120 | NO | NR
CapitalELECTRIC GENERATIONGENERATION CAPITAL TOOLS & TEST EQPT.Non-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | GENERATION CAPITAL TOOLS & TEST EQPT. | Non-RAMP | Non-RAMP | Non-RAMP | 76764.01 | 0 | 0 | 0 | 98088.82 | 91999.92 | 94999.92 | 97999.92 | 100999.92 | 385999.68 | -15235.91 | -94999.92 | -97999.92 | -100999.92 | -287910.86 | -16.56% | -100% | -100% | -100% | -74.59% | YES | 60 | NO | NR
CapitalELECTRIC GENERATIONMIGUEL VRF- BATTERY FACILITIES ENHANCEMENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | MIGUEL VRF- BATTERY FACILITIES ENHANCEME | Non-RAMP | Non-RAMP | Non-RAMP | 219562.5521 | 0 | 0 | 0 | 219562.5521 | 0 | 0 | 0 | 0 | 0 | 219562.5521 | 0 | 0 | 0 | 219562.5521 | 100% | 100% | 100% | 100% | 100% | YES | 210470 | NO | NR
CapitalELECTRIC GENERATIONMIRAMAR PLANT OPERATIONAL ENHANCEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | MIRAMAR PLANT OPERATIONAL ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 143704.097 | 0 | 0 | 0 | 217608.117 | 975999.96 | 1005000 | 1035000 | 1065999.96 | 4081999.92 | -832295.863 | -1005000 | -1035000 | -1065999.96 | -3864391.803 | -85.28% | -100% | -100% | -100% | -94.67% | YES | 80 | NO | NR
CapitalELECTRIC GENERATIONPALOMAR HYDROGEN SYSTEMSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | PALOMAR HYDROGEN SYSTEMS | Non-RAMP | Non-RAMP | Non-RAMP | 715283.4042 | 0 | 0 | 0 | 715283.4042 | 0 | 0 | 0 | 0 | 0 | 715283.4042 | 0 | 0 | 0 | 715283.4042 | 100% | 100% | 100% | 100% | 100% | YES | 210390 | NO | NR
CapitalELECTRIC GENERATIONPALOMAR PLANT OPERATIONAL ENHANCEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | PALOMAR PLANT OPERATIONAL ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 4815094.0436 | 0 | 0 | 0 | 4815094.0436 | 6093000 | 6276000 | 6463999.92 | 6657999.96 | 25490999.88 | -1277905.9564 | -6276000 | -6463999.92 | -6657999.96 | -20675905.8364 | -20.97% | -100% | -100% | -100% | -81.11% | YES | 90 | NO | NR
CapitalELECTRIC GENERATIONRAMONA SOLAR PLANT OPER ENHANCENon-RAMPNon-RAMPNon-RAMP | Capital | ELECTRIC GENERATION | RAMONA SOLAR PLANT OPER ENHANCE | Non-RAMP | Non-RAMP | Non-RAMP | 5031.73 | 0 | 0 | 0 | 5031.73 | 52999.92 | 54999.96 | 57000 | 58999.92 | 223999.8 | -47968.19 | -54999.96 | -57000 | -58999.92 | -218968.07 | -90.51% | -100% | -100% | -100% | -97.75% | YES | 140 | NO | NR
CapitalFACILITIES/OTHERCHULA VISTA YARD SECURITY IMPROVEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | CHULA VISTA YARD SECURITY IMPROVEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 5175999.96 | 5331000 | 5490999.96 | 5655999.96 | 21653999.88 | -5175999.96 | -5331000 | -5490999.96 | -5655999.96 | -21653999.88 | -100% | -100% | -100% | -100% | -100% | YES | 00710A | NO | NR
CapitalFACILITIES/OTHERCLEAN TRANSPORTATION INFRASTRUCTURENon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | CLEAN TRANSPORTATION INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | 1470544.0735 | 0 | 0 | 0 | 1470544.0735 | 14443999.92 | 14877000 | 15322999.92 | 15783000 | 60426999.84 | -12973455.8466 | -14877000 | -15322999.92 | -15783000 | -58956455.7665 | -89.82% | -100% | -100% | -100% | -97.57% | NO | 87290 | NO | NR
CapitalFACILITIES/OTHERCOMM. PLANT BLKT-BUSINESS UNIT EXPANSIONNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | COMM. PLANT BLKT-BUSINESS UNIT EXPANSION | Non-RAMP | Non-RAMP | Non-RAMP | 216563.3616 | 0 | 0 | 0 | 216563.3616 | 0 | 0 | 0 | 0 | 0 | 216563.3616 | 0 | 0 | 0 | 216563.3616 | 100% | 100% | 100% | 100% | 100% | YES | 7100 | NO | NR
CapitalFACILITIES/OTHERCOMM. PLANT BLKT-INFRASTRUCTURE & RELIABNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | COMM. PLANT BLKT-INFRASTRUCTURE & RELIAB | Non-RAMP | Non-RAMP | Non-RAMP | 7277604.7958 | 0 | 0 | 0 | 7277604.7958 | 6717999.96 | 6919999.92 | 7128000 | 7341999.96 | 28107999.84 | 559604.8358 | -6919999.92 | -7128000 | -7341999.96 | -20830395.0442 | 8.33% | -100% | -100% | -100% | -74.11% | YES | 7080 | NO | NR
CapitalFACILITIES/OTHERCOMM. PLANT BLKT-REMODEL/RELOC/RECONFIGNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | COMM. PLANT BLKT-REMODEL/RELOC/RECONFIG | Non-RAMP | Non-RAMP | Non-RAMP | 15837540.0757 | 0 | 0 | 0 | 15837540.0757 | 2946000 | 3033999.96 | 3124999.92 | 3219000 | 12323999.88 | 12891540.0757 | -3033999.96 | -3124999.92 | -3219000 | 3513540.1957 | 437.6% | -100% | -100% | -100% | 28.51% | YES | 7090 | NO | NR
CapitalFACILITIES/OTHERFURNITURE & OFFICE EQUIPMENT BLANKETNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | FURNITURE & OFFICE EQUIPMENT BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | 231660.7011 | 0 | 0 | 0 | 231660.7011 | 0 | 0 | 0 | 0 | 0 | 231660.7011 | 0 | 0 | 0 | 231660.7011 | 100% | 100% | 100% | 100% | 100% | YES | 7020 | NO | NR
CapitalFACILITIES/OTHERKEARNY MASTER PLAN PHASE 2Non-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | KEARNY MASTER PLAN PHASE 2 | Non-RAMP | Non-RAMP | Non-RAMP | 10380840.0016 | 0 | 0 | 0 | 10380840.0016 | 0 | 0 | 0 | 0 | 0 | 10380840.0016 | 0 | 0 | 0 | 10380840.0016 | 100% | 100% | 100% | 100% | 100% | YES | 00710C | NO | NR
CapitalFACILITIES/OTHERLAND BLANKETNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | LAND BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 29730 | 87000 | 90000 | 93000 | 96000 | 366000 | -87000 | -90000 | -93000 | -96000 | -336270 | -100% | -100% | -100% | -100% | -91.88% | YES | 7000 | NO | NR
CapitalFACILITIES/OTHERLAND SERVICES ARCHIBUS SYSTEMNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | LAND SERVICES ARCHIBUS SYSTEM | Non-RAMP | Non-RAMP | Non-RAMP | 840049.4416 | 0 | 0 | 0 | 840049.4416 | 1771999.92 | 1824999.96 | 1879999.92 | 1935999.96 | 7412999.76 | -931950.4784 | -1824999.96 | -1879999.92 | -1935999.96 | -6572950.3184 | -52.59% | -100% | -100% | -100% | -88.67% | YES | 137460 | NO | NR
CapitalFACILITIES/OTHERMISC EQUIPMENT BLANKETNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | MISC EQUIPMENT BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | 918536.6958 | 0 | 0 | 0 | 918536.6958 | 2007999.96 | 2067999.96 | 2130000 | 2193999.96 | 8399999.88 | -1089463.2642 | -2067999.96 | -2130000 | -2193999.96 | -7481463.1842 | -54.26% | -100% | -100% | -100% | -89.07% | YES | 7050 | NO | NR
CapitalFACILITIES/OTHERSAFETY/ENVIRONMENTALNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | SAFETY/ENVIRONMENTAL | Non-RAMP | Non-RAMP | Non-RAMP | 618076.0583 | 0 | 0 | 0 | 618076.0583 | 2313000 | 2382000 | 2452999.92 | 2526999.96 | 9674999.88 | -1694923.9417 | -2382000 | -2452999.92 | -2526999.96 | -9056923.8217 | -73.28% | -100% | -100% | -100% | -93.61% | YES | 7030 | NO | NR
CapitalFACILITIES/OTHERSDG&E SITE SECURITY UPGRADESNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | SDG&E SITE SECURITY UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | -6849.16 | 0 | 0 | 0 | 70890.73 | 0 | 0 | 0 | 0 | 0 | -6849.16 | 0 | 0 | 0 | 70890.73 | 100% | 100% | 100% | 100% | 100% | YES | 00707B | NO | NR
CapitalFACILITIES/OTHERSDG&E SUSTAINABILITY PROGRAMNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | SDG&E SUSTAINABILITY PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | 118946.5289 | 0 | 0 | 0 | 118946.5289 | 6444000 | 6636999.96 | 6837000 | 7041999.96 | 26959999.92 | -6325053.4711 | -6636999.96 | -6837000 | -7041999.96 | -26841053.3911 | -98.15% | -100% | -100% | -100% | -99.56% | NO | 21757B | NO | NR
CapitalFACILITIES/OTHERSECURITY SYSTEMS BLANKETNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | SECURITY SYSTEMS BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | 414756.4275 | 0 | 0 | 0 | 414756.4275 | 3204999.96 | 3300999.96 | 3399999.96 | 3501999.96 | 13407999.84 | -2790243.5325 | -3300999.96 | -3399999.96 | -3501999.96 | -12993243.4125 | -87.06% | -100% | -100% | -100% | -96.91% | YES | 7070 | NO | NR
CapitalFACILITIES/OTHERSTRUCTURES & IMPROVEMENTS BLANKETNon-RAMPNon-RAMPNon-RAMP | Capital | FACILITIES/OTHER | STRUCTURES & IMPROVEMENTS BLANKET | Non-RAMP | Non-RAMP | Non-RAMP | 2492518.7765 | 0 | 0 | 0 | 2492518.7765 | 6312000 | 6501000 | 6696000 | 6897000 | 26406000 | -3819481.2235 | -6501000 | -6696000 | -6897000 | -23913481.2235 | -60.51% | -100% | -100% | -100% | -90.56% | YES | 7010 | NO | NR
CapitalGAS DISTRIBUTIONCATHODIC PROTECTION SYSTEM ENHANCEMENTIncident Related to the Medium Pressure System (Excluding Dig-in)Cathodic Protection System EnhancementsHP Supply Line | Capital | GAS DISTRIBUTION | CATHODIC PROTECTION SYSTEM ENHANCEMENT | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection System Enhancements | HP Supply Line | 90630.9776 | 0 | 0 | 0 | 90630.9776 | 0 | 0 | 0 | 0 | 0 | 90630.9776 | 0 | 0 | 0 | 90630.9776 | 100% | 100% | 100% | 100% | 100% | YES | 125510 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONCATHODIC PROTECTION SYSTEM ENHANCEMENTIncident Related to the Medium Pressure System (Excluding Dig-in)Cathodic Protection System EnhancementsMP Main Steel | Capital | GAS DISTRIBUTION | CATHODIC PROTECTION SYSTEM ENHANCEMENT | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection System Enhancements | MP Main Steel | 1721988.5745 | 0 | 0 | 0 | 1721988.5745 | 0 | 0 | 0 | 0 | 0 | 1721988.5745 | 0 | 0 | 0 | 1721988.5745 | 100% | 100% | 100% | 100% | 100% | YES | 125510 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONCATHODIC PROTECTIONIncident Related to the Medium Pressure System (Excluding Dig-in)Cathodic Protection Program - CapitalHP Supply Line | Capital | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection Program - Capital | HP Supply Line | 274004.1641 | 0 | 0 | 0 | 274004.1641 | 237000 | 243999.96 | 250999.92 | 258999.96 | 990999.84 | 37004.1641 | -243999.96 | -250999.92 | -258999.96 | -716995.6759 | 15.61% | -100% | -100% | -100% | -72.35% | YES | 5090 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONCATHODIC PROTECTIONIncident Related to the Medium Pressure System (Excluding Dig-in)Cathodic Protection Program - CapitalMP Main Steel | Capital | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection Program - Capital | MP Main Steel | 5206079.1177 | 0 | 0 | 0 | 5206079.1177 | 4156999.92 | 4281999.96 | 4410999.96 | 4542999.96 | 17392999.8 | 1049079.1977 | -4281999.96 | -4410999.96 | -4542999.96 | -12186920.6823 | 25.24% | -100% | -100% | -100% | -70.07% | YES | 5090 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONCNG STATION UPGRADESNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | CNG STATION UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | 453688.6359 | 0 | 0 | 0 | 453688.6359 | 0 | 0 | 0 | 0 | 0 | 453688.6359 | 0 | 0 | 0 | 453688.6359 | 100% | 100% | 100% | 100% | 100% | YES | 145530 | NO | NR
CapitalGAS DISTRIBUTIONCODE COMPLIANCEIncident Related to the Medium Pressure System (Excluding Dig-in)Code Compliance MitigationMeter & Beyond the Meter | Capital | GAS DISTRIBUTION | CODE COMPLIANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Code Compliance Mitigation | Meter & Beyond the Meter | 5466727.7013 | 0 | 0 | 0 | 5466727.7013 | 2652999.96 | 2733000 | 2814999.96 | 2898999.96 | 11099999.88 | 2813727.7413 | -2733000 | -2814999.96 | -2898999.96 | -5633272.1787 | 106.1% | -100% | -100% | -100% | -50.75% | YES | 5070 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONCODE COMPLIANCENon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | CODE COMPLIANCE | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 423999.96 | 436999.92 | 450000 | 463999.92 | 1774999.8 | -423999.96 | -436999.92 | -450000 | -463999.92 | -1774999.8 | -100% | -100% | -100% | -100% | -100% | YES | 5070 | NO | NR
CapitalGAS DISTRIBUTIONCONTRACT ADMIN – GASNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | CONTRACT ADMIN – GAS | Non-RAMP | Non-RAMP | Non-RAMP | 5683921.363 | 0 | 0 | 0 | 5683921.363 | 6561000 | 6757999.92 | 6960999.96 | 7168999.92 | 27448999.8 | -877078.637 | -6757999.92 | -6960999.96 | -7168999.92 | -21765078.437 | -13.37% | -100% | -100% | -100% | -79.29% | YES | G09060 | NO | NR
CapitalGAS DISTRIBUTIONCURB VALVE REPLACEMENTSIncident Related to the Medium Pressure System (Excluding Dig-in)Replace Curb Valves with EFVsMP Main & Service Plastic | Capital | GAS DISTRIBUTION | CURB VALVE REPLACEMENTS | Incident Related to the Medium Pressure System (Excluding Dig-in) | Replace Curb Valves with EFVs | MP Main & Service Plastic | 1323853.9442 | 0 | 0 | 0 | 1323853.9442 | 996999.96 | 1026999.96 | 1057999.92 | 1089999.96 | 4171999.8 | 326853.9841 | -1026999.96 | -1057999.92 | -1089999.96 | -2848145.8558 | 32.78% | -100% | -100% | -100% | -68.27% | YES | 215750 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONDEPARTMENT OVERHEAD POOL - GASNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | DEPARTMENT OVERHEAD POOL - GAS | Non-RAMP | Non-RAMP | Non-RAMP | 14627188.8513 | 0 | 0 | 0 | 14627188.8513 | 5871999.96 | 6048000 | 6228999.96 | 6414999.96 | 24563999.88 | 8755188.8913 | -6048000 | -6228999.96 | -6414999.96 | -9936811.0287 | 149.1% | -100% | -100% | -100% | -40.45% | YES | G09050 | NO | NR
CapitalGAS DISTRIBUTIONDISTRIBUTION EASEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | DISTRIBUTION EASEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 7192.2 | 0 | 0 | 0 | 7192.2 | 0 | 0 | 0 | 0 | 0 | 7192.2 | 0 | 0 | 0 | 7192.2 | 100% | 100% | 100% | 100% | 100% | YES | 5040 | NO | NR
CapitalGAS DISTRIBUTIONEARLY VINTAGE PROGRAM - DRESSER MECHANICAL COUPLING REMOVALIncident Related to the Medium Pressure System (Excluding Dig-in)Early Vintage Program- Dresser Mech Coupling RemovalMain Steel | Capital | GAS DISTRIBUTION | EARLY VINTAGE PROGRAM - DRESSER MECHANICAL COUPLING REMOVAL | Incident Related to the Medium Pressure System (Excluding Dig-in) | Early Vintage Program- Dresser Mech Coupling Removal | Main Steel | 1575713.0348 | 0 | 0 | 0 | 1575713.0348 | 498000 | 513000 | 528000 | 543999.96 | 2082999.96 | 1077713.0348 | -513000 | -528000 | -543999.96 | -507286.9252 | 216.4% | -100% | -100% | -100% | -24.35% | YES | 195660 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONEARLY VINTAGE PROGRAM - OIL DRIP PIPING REMOVALIncident Related to the Medium Pressure System (Excluding Dig-in)Early Vintage Program- Oil Drip Piping RemovalMain Steel | Capital | GAS DISTRIBUTION | EARLY VINTAGE PROGRAM - OIL DRIP PIPING REMOVAL | Incident Related to the Medium Pressure System (Excluding Dig-in) | Early Vintage Program- Oil Drip Piping Removal | Main Steel | 1006040.9074 | 0 | 0 | 0 | 1006040.9074 | 1494999.96 | 1539999.96 | 1585999.92 | 1633999.92 | 6254999.76 | -488959.0526 | -1539999.96 | -1585999.92 | -1633999.92 | -5248958.8526 | -32.71% | -100% | -100% | -100% | -83.92% | YES | 195670 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONEARLY VINTAGE PROGRAM - REMOVAL OF CLOSED VALVES BETWEEN HP/MP ZONESIncident Related to the Medium Pressure System (Excluding Dig-in)Early Vintage Program-Remove Closed Valves b/w HP/MPMain Steel | Capital | GAS DISTRIBUTION | EARLY VINTAGE PROGRAM - REMOVAL OF CLOSED VALVES BETWEEN HP/MP ZONES | Incident Related to the Medium Pressure System (Excluding Dig-in) | Early Vintage Program-Remove Closed Valves b/w HP/MP | Main Steel | 633357.1228 | 0 | 0 | 0 | 633357.1228 | 889999.92 | 916999.92 | 945000 | 972999.96 | 3724999.8 | -256642.7972 | -916999.92 | -945000 | -972999.96 | -3091642.6772 | -28.84% | -100% | -100% | -100% | -83% | YES | 195690 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONGAS OPS CONTROL CENTER PROJ DISTR REG STATION & OTHERIncident Related to the Medium Pressure System (Excluding Dig-in)CCM Distribution Field Asset Real Time MonitoringN/A | Capital | GAS DISTRIBUTION | GAS OPS CONTROL CENTER PROJ DISTR REG STATION & OTHER | Incident Related to the Medium Pressure System (Excluding Dig-in) | CCM Distribution Field Asset Real Time Monitoring | N/A | 1935413.7516 | 0 | 0 | 0 | 1935413.7516 | 3765000 | 3877999.92 | 3993999.96 | 4113999.96 | 15750999.84 | -1829586.2484 | -3877999.92 | -3993999.96 | -4113999.96 | -13815586.0883 | -48.59% | -100% | -100% | -100% | -87.71% | YES | 215740 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONLEAK REPAIRIncident Related to the Medium Pressure System (Excluding Dig-in)Leak Repair (Capital)MP Main Plastic | Capital | GAS DISTRIBUTION | LEAK REPAIR | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair (Capital) | MP Main Plastic | 6586365.6424 | 0 | 0 | 0 | 6586365.6424 | 3907999.92 | 4024999.92 | 4146000 | 4270999.92 | 16349999.76 | 2678365.7224 | -4024999.92 | -4146000 | -4270999.92 | -9763634.1176 | 68.54% | -100% | -100% | -100% | -59.72% | YES | 5080 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONLEAK REPAIRIncident Related to the Medium Pressure System (Excluding Dig-in)Leak Repair (Capital)MP Main Steel | Capital | GAS DISTRIBUTION | LEAK REPAIR | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair (Capital) | MP Main Steel | 9879548.4636 | 0 | 0 | 0 | 9879548.4636 | 6138999.96 | 6322999.92 | 6511999.92 | 6706999.92 | 25680999.72 | 3740548.5036 | -6322999.92 | -6511999.92 | -6706999.92 | -15801451.2564 | 60.93% | -100% | -100% | -100% | -61.53% | YES | 5080 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONLOCAL ENGINEERING POOL - GASIncident Related to the Medium Pressure System (Excluding Dig-in)Human Factors Mitigations - Gas Handling PlansN/A | Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factors Mitigations - Gas Handling Plans | N/A | 240130.308 | 0 | 0 | 0 | 240130.308 | 288000 | 297000 | 306000 | 315000 | 1206000 | -47869.692 | -297000 | -306000 | -315000 | -965869.692 | -16.62% | -100% | -100% | -100% | -80.09% | YES | G09020 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONLOCAL ENGINEERING POOL - GASNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Non-RAMP | Non-RAMP | Non-RAMP | 22386882.555 | 0 | 0 | 0 | 22386882.555 | 22357999.92 | 23026999.92 | 23718000 | 24429000 | 93531999.84 | 28882.635 | -23026999.92 | -23718000 | -24429000 | -71145117.285 | 0.1292% | -100% | -100% | -100% | -76.07% | YES | G09020 | NO | NR
CapitalGAS DISTRIBUTIONLOCAL ENGINEERING POOL - GASRecords ManagementGGIS GrowthN/A | Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Records Management | GGIS Growth | N/A | 0 | 0 | 0 | 0 | 0 | 126000 | 129999.96 | 133999.92 | 138000 | 527999.88 | -126000 | -129999.96 | -133999.92 | -138000 | -527999.88 | -100% | -100% | -100% | -100% | -100% | YES | G09020 | NO | SDG&E-CFF-6
CapitalGAS DISTRIBUTIONLOCAL ENGINEERING POOL - GASRecords ManagementRAMP: SDG&E-CFF-6, New: Gas Geographic Information System GroupN/A | Capital | GAS DISTRIBUTION | LOCAL ENGINEERING POOL - GAS | Records Management | RAMP: SDG&E-CFF-6, New: Gas Geographic Information System Group | N/A | 2430710.6976 | 0 | 0 | 0 | 2430710.6976 | 909000 | 936000 | 963999.96 | 993000 | 3801999.96 | 1521710.6976 | -936000 | -963999.96 | -993000 | -1371289.2624 | 167.4% | -100% | -100% | -100% | -36.07% | YES | G09020 | NO | SDG&E-CFF-6
CapitalGAS DISTRIBUTIONMETER AND REGULATOR MATERIALSNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | METER AND REGULATOR MATERIALS | Non-RAMP | Non-RAMP | Non-RAMP | 10134979.73 | 0 | 0 | 0 | 12997153.69 | 8344999.92 | 8595000 | 8853000 | 9118999.92 | 34911999.84 | 1789979.81 | -8595000 | -8853000 | -9118999.92 | -21914846.15 | 21.45% | -100% | -100% | -100% | -62.77% | YES | 5020 | NO | NR
CapitalGAS DISTRIBUTIONNEW BUSINESS- BALANCEDIncident Related to the Medium Pressure System (Excluding Dig-in)Field and Public SafetyMeter & Beyond the Meter | Capital | GAS DISTRIBUTION | NEW BUSINESS- BALANCED | Incident Related to the Medium Pressure System (Excluding Dig-in) | Field and Public Safety | Meter & Beyond the Meter | 224280.3074 | 0 | 0 | 0 | 224280.3074 | 0 | 0 | 0 | 0 | 0 | 224280.3074 | 0 | 0 | 0 | 224280.3074 | 100% | 100% | 100% | 100% | 100% | YES | 00500B | YES | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONNEW BUSINESS- BALANCEDNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | NEW BUSINESS- BALANCED | Non-RAMP | Non-RAMP | Non-RAMP | 2263763.7724 | 0 | 0 | 0 | 2263763.7724 | 2325000 | 2394999.96 | 2466999.96 | 2541000 | 9727999.92 | -61236.2276 | -2394999.96 | -2466999.96 | -2541000 | -7464236.1476 | -2.634% | -100% | -100% | -100% | -76.73% | YES | 00500B | YES | NR
CapitalGAS DISTRIBUTIONNEW BUSINESSNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | NEW BUSINESS | Non-RAMP | Non-RAMP | Non-RAMP | 7694613.4761 | 0 | 0 | 0 | 7694613.4761 | 4753999.92 | 4896999.96 | 5043999.96 | 5194999.92 | 19889999.76 | 2940613.5561 | -4896999.96 | -5043999.96 | -5194999.92 | -12195386.2839 | 61.86% | -100% | -100% | -100% | -61.31% | YES | 5000 | NO | NR
CapitalGAS DISTRIBUTIONPIPE RELOCATIONS - FRANCHISE AND FREEWAYNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | PIPE RELOCATIONS - FRANCHISE AND FREEWAY | Non-RAMP | Non-RAMP | Non-RAMP | 9239246.8259 | 0 | 0 | 0 | 9239246.8259 | 5755999.92 | 5928999.96 | 6106999.92 | 6289999.92 | 24081999.72 | 3483246.9059 | -5928999.96 | -6106999.92 | -6289999.92 | -14842752.8941 | 60.52% | -100% | -100% | -100% | -61.63% | YES | 5050 | NO | NR
CapitalGAS DISTRIBUTIONPIPING IN VAUTS REPLACEMENT PROGRAMIncident Related to the Medium Pressure System (Excluding Dig-in)Piping in Vaults Replacement ProgramMP Main Steel | Capital | GAS DISTRIBUTION | PIPING IN VAUTS REPLACEMENT PROGRAM | Incident Related to the Medium Pressure System (Excluding Dig-in) | Piping in Vaults Replacement Program | MP Main Steel | 328078.8664 | 0 | 0 | 0 | 328078.8664 | 1494999.96 | 1539999.96 | 1585999.92 | 1633999.92 | 6254999.76 | -1166921.0936 | -1539999.96 | -1585999.92 | -1633999.92 | -5926920.8936 | -78.05% | -100% | -100% | -100% | -94.75% | YES | 195680 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONPRESSURE BETTERMENTNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | PRESSURE BETTERMENT | Non-RAMP | Non-RAMP | Non-RAMP | 495474.3913 | 0 | 0 | 0 | 495474.3913 | 0 | 0 | 0 | 0 | 0 | 495474.3913 | 0 | 0 | 0 | 495474.3913 | 100% | 100% | 100% | 100% | 100% | YES | 5030 | NO | NR
CapitalGAS DISTRIBUTIONREGULATOR STATION IMPROVEMENTS AND OTHERIncident Related to the Medium Pressure System (Excluding Dig-in)Reg Station Replacement ProgramHP Supply Line | Capital | GAS DISTRIBUTION | REGULATOR STATION IMPROVEMENTS AND OTHER | Incident Related to the Medium Pressure System (Excluding Dig-in) | Reg Station Replacement Program | HP Supply Line | 1041238.1435 | 0 | 0 | 0 | 1041238.1435 | 213999.96 | 220999.92 | 226999.92 | 234000 | 895999.8 | 827238.1835 | -220999.92 | -226999.92 | -234000 | 145238.3435 | 386.6% | -100% | -100% | -100% | 16.21% | YES | 5100 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONREGULATOR STATION IMPROVEMENTS AND OTHERIncident Related to the Medium Pressure System (Excluding Dig-in)Reg Station Replacement ProgramHP-MP Main Steel & Plastic | Capital | GAS DISTRIBUTION | REGULATOR STATION IMPROVEMENTS AND OTHER | Incident Related to the Medium Pressure System (Excluding Dig-in) | Reg Station Replacement Program | HP-MP Main Steel & Plastic | 2114028.958 | 0 | 0 | 0 | 2114028.958 | 429000 | 441000 | 454999.92 | 468000 | 1792999.92 | 1685028.9579 | -441000 | -454999.92 | -468000 | 321029.038 | 392.8% | -100% | -100% | -100% | 17.9% | YES | 5100 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONSYSTEMS MINOR ADDITIONS, RELOCATIONS AND RETIREMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | SYSTEMS MINOR ADDITIONS, RELOCATIONS AND RETIREMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 7213219.6766 | 0 | 0 | 0 | 7213219.6766 | 5202000 | 5358000 | 5518999.92 | 5683999.92 | 21762999.84 | 2011219.6766 | -5358000 | -5518999.92 | -5683999.92 | -14549780.1634 | 38.66% | -100% | -100% | -100% | -66.86% | YES | 5010 | NO | NR
CapitalGAS DISTRIBUTIONTOOLS AND EQUIPMENTExcavation Damage (Dig-In) on the Gas SystemLocating EquipmentMP | Capital | GAS DISTRIBUTION | TOOLS AND EQUIPMENT | Excavation Damage (Dig-In) on the Gas System | Locating Equipment | MP | 0 | 0 | 0 | 0 | 0 | 210000 | 216000 | 222999.96 | 229999.92 | 878999.88 | -210000 | -216000 | -222999.96 | -229999.92 | -878999.88 | -100% | -100% | -100% | -100% | -100% | YES | 5060 | NO | SDG&E-Risk-7
CapitalGAS DISTRIBUTIONTOOLS AND EQUIPMENTIncident Related to the Medium Pressure System (Excluding Dig-in)Human Factor Mitigations - OpQual Training & CertN/A | Capital | GAS DISTRIBUTION | TOOLS AND EQUIPMENT | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factor Mitigations - OpQual Training & Cert | N/A | 151000 | 0 | 0 | 0 | 151000 | 411000 | 423000 | 435999.96 | 448999.92 | 1718999.88 | -260000 | -423000 | -435999.96 | -448999.92 | -1567999.88 | -63.26% | -100% | -100% | -100% | -91.22% | YES | 5060 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONTOOLS AND EQUIPMENTNon-RAMPNon-RAMPNon-RAMP | Capital | GAS DISTRIBUTION | TOOLS AND EQUIPMENT | Non-RAMP | Non-RAMP | Non-RAMP | 897178.17 | 0 | 0 | 0 | 1052618.71 | 3024999.96 | 3115999.92 | 3210000 | 3306000 | 12656999.88 | -2127821.79 | -3115999.92 | -3210000 | -3306000 | -11604381.17 | -70.34% | -100% | -100% | -100% | -91.68% | YES | 5060 | NO | NR
CapitalGAS DISTRIBUTIONUNDERPERFORMING STEEL REPLACEMENT PROGRAM (1934-1965 VINTAGE)Incident Related to the Medium Pressure System (Excluding Dig-in)Underperforming Steel Replacement Program - 1934-1965 Vintage (19564)MP Main Steel | Capital | GAS DISTRIBUTION | UNDERPERFORMING STEEL REPLACEMENT PROGRAM (1934-1965 VINTAGE) | Incident Related to the Medium Pressure System (Excluding Dig-in) | Underperforming Steel Replacement Program - 1934-1965 Vintage (19564) | MP Main Steel | 5182096.114 | 0 | 0 | 0 | 5182096.114 | 2989999.92 | 3079999.92 | 3171999.96 | 3267000 | 12508999.8 | 2192096.194 | -3079999.92 | -3171999.96 | -3267000 | -7326903.686 | 73.31% | -100% | -100% | -100% | -58.57% | YES | 195640 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONUNDERPERFORMING STEEL REPLACEMENT PROGRAM - OTHER (POST 1965 VINTAGE)Incident Related to the Medium Pressure System (Excluding Dig-in)Underperforming Steel Replacement Program - Other Steel (Post-1965 Vintage)MP Main Steel | Capital | GAS DISTRIBUTION | UNDERPERFORMING STEEL REPLACEMENT PROGRAM - OTHER (POST 1965 VINTAGE) | Incident Related to the Medium Pressure System (Excluding Dig-in) | Underperforming Steel Replacement Program - Other Steel (Post-1965 Vintage) | MP Main Steel | 1532684.5051 | 0 | 0 | 0 | 1532684.5051 | 2989999.92 | 3079999.92 | 3171999.96 | 3267000 | 12508999.8 | -1457315.4149 | -3079999.92 | -3171999.96 | -3267000 | -10976315.2949 | -48.74% | -100% | -100% | -100% | -87.75% | YES | 5140 | NO | SDG&E-Risk-9
CapitalGAS DISTRIBUTIONUNDERPERFORMING STEEL REPLACEMENT PROGRAM - THREADED MAIN (PRE-1934 VINTAGE)Incident Related to the Medium Pressure System (Excluding Dig-in)Underperforming Steel Replacement Program (Pre-1934 vintage)MP Main Steel | Capital | GAS DISTRIBUTION | UNDERPERFORMING STEEL REPLACEMENT PROGRAM - THREADED MAIN (PRE-1934 VINTAGE) | Incident Related to the Medium Pressure System (Excluding Dig-in) | Underperforming Steel Replacement Program (Pre-1934 vintage) | MP Main Steel | 8009702.5429 | 0 | 0 | 0 | 8280045.0629 | 6975999.96 | 7185000 | 7401000 | 7623000 | 29184999.96 | 1033702.5829 | -7185000 | -7401000 | -7623000 | -20904954.8971 | 14.82% | -100% | -100% | -100% | -71.63% | YES | 195650 | NO | SDG&E-Risk-9
CapitalGAS ENGINEERINGLOCAL GT SUPERVISION AND ENGINEERING POOLNon-RAMPNon-RAMPNon-RAMP | Capital | GAS ENGINEERING | LOCAL GT SUPERVISION AND ENGINEERING POOL | Non-RAMP | Non-RAMP | Non-RAMP | 367273.0114 | 0 | 0 | 0 | 367273.0114 | 294000 | 303000 | 312000 | 321000 | 1230000 | 73273.0114 | -303000 | -312000 | -321000 | -862726.9886 | 24.92% | -100% | -100% | -100% | -70.14% | YES | EN9030 | NO | NR
CapitalGAS INTEGRITY PROGRAMSDIMPIncident Related to the Medium Pressure System (Excluding Dig-in)Distribution Integrity Management Program (DIMP)Plastic - Main (VIPP) | Capital | GAS INTEGRITY PROGRAMS | DIMP | Incident Related to the Medium Pressure System (Excluding Dig-in) | Distribution Integrity Management Program (DIMP) | Plastic - Main (VIPP) | 82374849.1508 | 0 | 0 | 0 | 82374849.1508 | 16023000 | 16503999.96 | 16998999.96 | 17508999.96 | 67034999.88 | 66351849.1508 | -16503999.96 | -16998999.96 | -17508999.96 | 15339849.2708 | 414.1% | -100% | -100% | -100% | 22.88% | YES | 95460 | YES | SDG&E-Risk-9
CapitalGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA)Transmission - HCA | Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - HCA | 9824103.5438 | 0 | 0 | 0 | 9824103.5438 | 24693999.96 | 25434000 | 26197999.92 | 26982999.96 | 103308999.84 | -14869896.4162 | -25434000 | -26197999.92 | -26982999.96 | -93484896.2962 | -60.22% | -100% | -100% | -100% | -90.49% | YES | 214770 | NO | SDG&E-Risk-3
CapitalGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA)Transmission - Non-HCA | Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - Non-HCA | 1599272.5738 | 0 | 0 | 0 | 1599272.5738 | 1575000 | 1623000 | 1671000 | 1722000 | 6591000 | 24272.5738 | -1623000 | -1671000 | -1722000 | -4991727.4262 | 1.541% | -100% | -100% | -100% | -75.74% | YES | 214770 | NO | SDG&E-Risk-3
CapitalGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)NEW - Gas Transmission Safety Rule (GTSR) Part 2Transmission - HCA & non-HCA | Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Gas Transmission Safety Rule (GTSR) Part 2 | Transmission - HCA & non-HCA | 0 | 0 | 0 | 0 | 0 | 331999.92 | 342000 | 351999.96 | 363000 | 1388999.88 | -331999.92 | -342000 | -351999.96 | -363000 | -1388999.88 | -100% | -100% | -100% | -100% | -100% | YES | 214770 | NO | SDG&E-Risk-3
CapitalGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)NEW - Valve RuleTransmission - HCA & non-HCA | Capital | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Valve Rule | Transmission - HCA & non-HCA | 0 | 0 | 0 | 0 | 0 | 459999.96 | 474000 | 487999.92 | 502999.92 | 1924999.8 | -459999.96 | -474000 | -487999.92 | -502999.92 | -1924999.8 | -100% | -100% | -100% | -100% | -100% | YES | 214770 | NO | SDG&E-Risk-3
CapitalGAS INTEGRITY PROGRAMSTIMPIncident Related to the High Pressure System (Excluding Dig-in)Integrity Assessments & Remediation (HCA and Non-HCA)Transmission - HCA | Capital | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - HCA | 31299714.0411 | 0 | 0 | 0 | 31299714.0411 | 8794999.92 | 9058999.92 | 9330000 | 9610999.92 | 36794999.76 | 22504714.1211 | -9058999.92 | -9330000 | -9610999.92 | -5495285.7189 | 255.9% | -100% | -100% | -100% | -14.93% | YES | 34680 | YES | SDG&E-Risk-3
CapitalGAS INTEGRITY PROGRAMSTIMPIncident Related to the High Pressure System (Excluding Dig-in)Integrity Assessments & Remediation (HCA and Non-HCA)Transmission - Non-HCA | Capital | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - Non-HCA | 638769.3225 | 0 | 0 | 0 | 638769.3225 | 462000 | 475999.92 | 490999.92 | 504999.96 | 1933999.8 | 176769.3225 | -475999.92 | -490999.92 | -504999.96 | -1295230.4775 | 38.26% | -100% | -100% | -100% | -66.97% | YES | 34680 | YES | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT AUXILIARY EQUIPMENT& INFRASTRUCTUREIncident Related to the High Pressure System (Excluding Dig-in)Security and Auxuliary EquipmentOverall | Capital | GAS TRANSMISSION | GT AUXILIARY EQUIPMENT& INFRASTRUCTURE | Incident Related to the High Pressure System (Excluding Dig-in) | Security and Auxuliary Equipment | Overall | 1433954.6576 | 0 | 0 | 0 | 1433954.6576 | 228999.96 | 235999.92 | 243000 | 249999.96 | 957999.84 | 1204954.6976 | -235999.92 | -243000 | -249999.96 | 475954.8176 | 526.2% | -100% | -100% | -100% | 49.68% | YES | 4190 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT AUXILIARY EQUIPMENT& INFRASTRUCTURENon-RAMPNon-RAMPNon-RAMP | Capital | GAS TRANSMISSION | GT AUXILIARY EQUIPMENT& INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 172999.92 | 177999.96 | 183000 | 187999.92 | 721999.8 | -172999.92 | -177999.96 | -183000 | -187999.92 | -721999.8 | -100% | -100% | -100% | -100% | -100% | YES | 4190 | NO | NR
CapitalGAS TRANSMISSIONGT CAPITAL TOOLSNon-RAMPNon-RAMPNon-RAMP | Capital | GAS TRANSMISSION | GT CAPITAL TOOLS | Non-RAMP | Non-RAMP | Non-RAMP | 172149.3651 | 0 | 0 | 0 | 172149.3651 | 147000 | 150999.96 | 156000 | 160999.92 | 614999.88 | 25149.3651 | -150999.96 | -156000 | -160999.92 | -442850.5149 | 17.11% | -100% | -100% | -100% | -72.01% | YES | 4360 | NO | NR
CapitalGAS TRANSMISSIONGT CATHODIC PROTECTIONIncident Related to the High Pressure System (Excluding Dig-in)Cathodic Protection - Capital (HCA & Non-HCA)Transmission - HCA | Capital | GAS TRANSMISSION | GT CATHODIC PROTECTION | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection - Capital (HCA & Non-HCA) | Transmission - HCA | 47775.7133 | 0 | 0 | 0 | 47775.7133 | 783999.96 | 807000 | 831999.96 | 855999.96 | 3278999.88 | -736224.2467 | -807000 | -831999.96 | -855999.96 | -3231224.1667 | -93.91% | -100% | -100% | -100% | -98.54% | YES | 4160 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT CATHODIC PROTECTIONIncident Related to the High Pressure System (Excluding Dig-in)Cathodic Protection - Capital (HCA & Non-HCA)Transmission - Non-HCA | Capital | GAS TRANSMISSION | GT CATHODIC PROTECTION | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection - Capital (HCA & Non-HCA) | Transmission - Non-HCA | 10487.3517 | 0 | 0 | 0 | 10487.3517 | 171999.96 | 177999.96 | 183000 | 189000 | 721999.92 | -161512.6083 | -177999.96 | -183000 | -189000 | -711512.5683 | -93.9% | -100% | -100% | -100% | -98.55% | YES | 4160 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT COMPRESSOR STATIONS ADDITIONS/REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Compressor Stations - CapitalTransmission - Facilities | Capital | GAS TRANSMISSION | GT COMPRESSOR STATIONS ADDITIONS/REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Compressor Stations - Capital | Transmission - Facilities | 4814882.129 | 0 | 0 | 0 | 4814882.129 | 6540999.96 | 6736999.92 | 6939000 | 7146999.96 | 27363999.84 | -1726117.831 | -6736999.92 | -6939000 | -7146999.96 | -22549117.7109 | -26.39% | -100% | -100% | -100% | -82.4% | YES | 4150 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT M&R STATIONS ADDITIONS/REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Measurement & Regulation - Capital (HCA & Non-HCA)Transmission - HCA | Capital | GAS TRANSMISSION | GT M&R STATIONS ADDITIONS/REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation - Capital (HCA & Non-HCA) | Transmission - HCA | 2202633.7869 | 0 | 0 | 0 | 2202633.7869 | 1335999.96 | 1374000 | 1416000 | 1458000 | 5583999.96 | 866633.8269 | -1374000 | -1416000 | -1458000 | -3381366.1731 | 64.87% | -100% | -100% | -100% | -60.55% | YES | 4080 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT M&R STATIONS ADDITIONS/REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Measurement & Regulation - Capital (HCA & Non-HCA)Transmission - Non-HCA | Capital | GAS TRANSMISSION | GT M&R STATIONS ADDITIONS/REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation - Capital (HCA & Non-HCA) | Transmission - Non-HCA | 483504.9776 | 0 | 0 | 0 | 483504.9776 | 294999.96 | 304999.92 | 312999.96 | 322999.92 | 1235999.76 | 188505.0176 | -304999.92 | -312999.96 | -322999.92 | -752494.7824 | 63.9% | -100% | -100% | -100% | -60.88% | YES | 4080 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT PIPELINE REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Leak Repair (HCA & Non- HCA)Tranmsission - HCA | Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Leak Repair (HCA & Non- HCA) | Tranmsission - HCA | -0.52767 | 0 | 0 | 0 | -0.52767 | 816000 | 840000 | 865999.92 | 891999.96 | 3413999.88 | -816000.5277 | -840000 | -865999.92 | -891999.96 | -3414000.4077 | -100% | -100% | -100% | -100% | -100% | YES | 4120 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT PIPELINE REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Leak Repair (HCA & Non- HCA)Transmission - Non-HCA | Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Leak Repair (HCA & Non- HCA) | Transmission - Non-HCA | -0.03477 | 0 | 0 | 0 | -0.03477 | 178999.92 | 184999.92 | 189999.96 | 195999.96 | 749999.76 | -178999.9548 | -184999.92 | -189999.96 | -195999.96 | -749999.7948 | -100% | -100% | -100% | -100% | -100% | YES | 4120 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT PIPELINE REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Pipeline relocation and replacement (HCA & Non-HCA)Transmission - HCA | Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline relocation and replacement (HCA & Non-HCA) | Transmission - HCA | 210080.2593 | 0 | 0 | 0 | 210080.2593 | 405999.96 | 418999.92 | 430999.92 | 444000 | 1699999.8 | -195919.7007 | -418999.92 | -430999.92 | -444000 | -1489919.5407 | -48.26% | -100% | -100% | -100% | -87.64% | YES | 4120 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT PIPELINE REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Pipeline relocation and replacement (HCA & Non-HCA)Transmission - Non-HCA | Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline relocation and replacement (HCA & Non-HCA) | Transmission - Non-HCA | 43865.4984 | 0 | 0 | 0 | 43865.4984 | 90000 | 91999.92 | 94999.92 | 97999.92 | 374999.76 | -46134.5016 | -91999.92 | -94999.92 | -97999.92 | -331134.2616 | -51.26% | -100% | -100% | -100% | -88.3% | YES | 4120 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT PIPELINE REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Shallow Exposure (HCA & Non-HCA)Transmission - HCA | Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Shallow Exposure (HCA & Non-HCA) | Transmission - HCA | 1892169.0727 | 0 | 0 | 0 | 1892169.0727 | 405999.96 | 418999.92 | 430999.92 | 444000 | 1699999.8 | 1486169.1127 | -418999.92 | -430999.92 | -444000 | 192169.2727 | 366.1% | -100% | -100% | -100% | 11.3% | YES | 4120 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONGT PIPELINE REPLACEMENTSIncident Related to the High Pressure System (Excluding Dig-in)Shallow Exposure (HCA & Non-HCA)Transmission - Non-HCA | Capital | GAS TRANSMISSION | GT PIPELINE REPLACEMENTS | Incident Related to the High Pressure System (Excluding Dig-in) | Shallow Exposure (HCA & Non-HCA) | Transmission - Non-HCA | 385495.5033 | 0 | 0 | 0 | 385495.5033 | 90000 | 91999.92 | 94999.92 | 97999.92 | 374999.76 | 295495.5033 | -91999.92 | -94999.92 | -97999.92 | 10495.7433 | 328.3% | -100% | -100% | -100% | 2.799% | YES | 4120 | NO | SDG&E-Risk-3
CapitalGAS TRANSMISSIONMORENO COMPRESSOR STATION MODERNIZATIONIncident Related to the High Pressure System (Excluding Dig-in)Compressor Stations - CapitalTransmission - Facilities | Capital | GAS TRANSMISSION | MORENO COMPRESSOR STATION MODERNIZATION | Incident Related to the High Pressure System (Excluding Dig-in) | Compressor Stations - Capital | Transmission - Facilities | 55964436.4589 | 0 | 0 | 0 | 55964436.4589 | 0 | 0 | 0 | 0 | 0 | 55964436.4589 | 0 | 0 | 0 | 55964436.4589 | 100% | 100% | 100% | 100% | 100% | YES | 4900 | NO | SDG&E-Risk-3
CapitalINFORMATION TECHNOLOGYAPP MODERNIZATION & VULNERABILITY REDUCTION - PHASE 2Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | APP MODERNIZATION & VULNERABILITY REDUCTION - PHASE 2 | Non-RAMP | Non-RAMP | Non-RAMP | -16586 | 0 | 0 | 0 | -16586 | 4725000 | 4866999.96 | 5013000 | 5163000 | 19767999.96 | -4741586 | -4866999.96 | -5013000 | -5163000 | -19784585.96 | -100.4% | -100% | -100% | -100% | -100.1% | YES | 00920AR | NO | NR
CapitalINFORMATION TECHNOLOGYBUSINESS ADAPTATION TECHNOLOGIES & DIGITALIZATIONNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | BUSINESS ADAPTATION TECHNOLOGIES & DIGITALIZATION | Non-RAMP | Non-RAMP | Non-RAMP | 1588960.6456 | 0 | 0 | 0 | 1588960.6456 | 1405999.92 | 1447999.92 | 1491000 | 1536000 | 5880999.84 | 182960.7256 | -1447999.92 | -1491000 | -1536000 | -4292039.1944 | 13.01% | -100% | -100% | -100% | -72.98% | NO | 00921R | NO | NR
CapitalINFORMATION TECHNOLOGYCAISO MANDATES 2023Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CAISO MANDATES 2023 | Non-RAMP | Non-RAMP | Non-RAMP | 1993000.2445 | 0 | 0 | 0 | 1993000.2445 | 444999.96 | 457999.92 | 471999.96 | 486000 | 1860999.84 | 1548000.2845 | -457999.92 | -471999.96 | -486000 | 132000.4045 | 347.9% | -100% | -100% | -100% | 7.093% | YES | 00920W | NO | NR
CapitalINFORMATION TECHNOLOGYCAISO MANDATES 2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CAISO MANDATES 2024 | Non-RAMP | Non-RAMP | Non-RAMP | 332524.417 | 0 | 0 | 0 | 332524.417 | 1825999.92 | 1879999.92 | 1935999.96 | 1993999.92 | 7635999.72 | -1493475.503 | -1879999.92 | -1935999.96 | -1993999.92 | -7303475.303 | -81.79% | -100% | -100% | -100% | -95.65% | YES | 00920AF | NO | NR
CapitalINFORMATION TECHNOLOGYCIS REGULATORY & ENHANCEMENTS 2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CIS REGULATORY & ENHANCEMENTS 2024 | Non-RAMP | Non-RAMP | Non-RAMP | 24428788.4651 | 0 | 0 | 0 | 24428788.4651 | 28077000 | 28918999.92 | 29787000 | 30681000 | 117463999.92 | -3648211.5349 | -28918999.92 | -29787000 | -30681000 | -93035211.455 | -12.99% | -100% | -100% | -100% | -79.2% | NO | 00903G | NO | NR
CapitalINFORMATION TECHNOLOGYCLEAN TRANSPORTATION PRODUCT TEAM 2023-2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CLEAN TRANSPORTATION PRODUCT TEAM 2023-2024 | Non-RAMP | Non-RAMP | Non-RAMP | 1731874.0965 | 0 | 0 | 0 | 1731874.0965 | 2020999.92 | 2082000 | 2143999.92 | 2208999.96 | 8455999.8 | -289125.8235 | -2082000 | -2143999.92 | -2208999.96 | -6724125.7035 | -14.31% | -100% | -100% | -100% | -79.52% | NO | 00903H | NO | NR
CapitalINFORMATION TECHNOLOGYCLOUD DATA LAKENon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CLOUD DATA LAKE | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 2952999.96 | 3042000 | 3132999.96 | 3226999.92 | 12354999.84 | -2952999.96 | -3042000 | -3132999.96 | -3226999.92 | -12354999.84 | -100% | -100% | -100% | -100% | -100% | NO | 00907M | NO | NR
CapitalINFORMATION TECHNOLOGYCONSTRUCTION, PLANNING AND DESIGN (CPD) ENHANCEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CONSTRUCTION, PLANNING AND DESIGN (CPD) ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 1626278.53 | 0 | 0 | 0 | 1626278.53 | 2328000 | 2397999.96 | 2469999.96 | 2544000 | 9739999.92 | -701721.47 | -2397999.96 | -2469999.96 | -2544000 | -8113721.3899 | -30.14% | -100% | -100% | -100% | -83.3% | YES | 00920F | NO | NR
CapitalINFORMATION TECHNOLOGYCONTACT CENTER OF THE FUTURE (CCOTF)Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CONTACT CENTER OF THE FUTURE (CCOTF) | Non-RAMP | Non-RAMP | Non-RAMP | 9240199.175 | 0 | 0 | 0 | 9240199.175 | 11563999.92 | 11910999.96 | 12268999.92 | 12636999.96 | 48380999.76 | -2323800.745 | -11910999.96 | -12268999.92 | -12636999.96 | -39140800.585 | -20.1% | -100% | -100% | -100% | -80.9% | NO | 00903B | NO | NR
CapitalINFORMATION TECHNOLOGYCROSS-FUNCTIONAL WORK MANAGEMENT ENHANCEMENTSNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | CROSS-FUNCTIONAL WORK MANAGEMENT ENHANCEMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 261999.96 | 270000 | 277999.92 | 285999.96 | 1095999.84 | -261999.96 | -270000 | -277999.92 | -285999.96 | -1095999.84 | -100% | -100% | -100% | -100% | -100% | NO | 00921Q | NO | NR
CapitalINFORMATION TECHNOLOGYDATA GOVERNANCE TOOLS & FRAMEWORKNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | DATA GOVERNANCE TOOLS & FRAMEWORK | Non-RAMP | Non-RAMP | Non-RAMP | 4987428.5982 | 0 | 0 | 0 | 4987428.5982 | 2658000 | 2737999.92 | 2820000 | 2904999.96 | 11120999.88 | 2329428.5982 | -2737999.92 | -2820000 | -2904999.96 | -6133571.2818 | 87.64% | -100% | -100% | -100% | -55.15% | NO | 00921F | NO | NR
CapitalINFORMATION TECHNOLOGYDIGITAL SERVICE INTEGRATION PLATFORMNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | DIGITAL SERVICE INTEGRATION PLATFORM | Non-RAMP | Non-RAMP | Non-RAMP | 3303209.5243 | 0 | 0 | 0 | 3303209.5243 | 1830999.96 | 1885999.92 | 1942999.92 | 2001000 | 7660999.8 | 1472209.5643 | -1885999.92 | -1942999.92 | -2001000 | -4357790.2757 | 80.4% | -100% | -100% | -100% | -56.88% | NO | 00921E | NO | NR
CapitalINFORMATION TECHNOLOGYDISTRIBUTION INTERCONNECTION INFO. SYSTEM - RULE 21 AND NET ENERGY METERING ENHANCEMENTS - PHASE 2Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | DISTRIBUTION INTERCONNECTION INFO. SYSTEM - RULE 21 AND NET ENERGY METERING ENHANCEMENTS - PHASE 2 | Non-RAMP | Non-RAMP | Non-RAMP | 1493677.2188 | 0 | 0 | 0 | 1493677.2188 | 1765999.92 | 1818999.96 | 1873999.92 | 1929999.96 | 7388999.76 | -272322.7012 | -1818999.96 | -1873999.92 | -1929999.96 | -5895322.5412 | -15.42% | -100% | -100% | -100% | -79.79% | YES | 00920X | NO | NR
CapitalINFORMATION TECHNOLOGYELECTRIC GRID OPS SMALL CAPITAL 2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | ELECTRIC GRID OPS SMALL CAPITAL 2024 | Non-RAMP | Non-RAMP | Non-RAMP | 211408.7648 | 0 | 0 | 0 | 211408.7648 | 519000 | 534999.96 | 550999.92 | 567000 | 2171999.88 | -307591.2353 | -534999.96 | -550999.92 | -567000 | -1960591.1153 | -59.27% | -100% | -100% | -100% | -90.27% | YES | 00908T | NO | NR
CapitalINFORMATION TECHNOLOGYENGINEERING & CONSTRUCTION DOCUMENT CENTRALIZATION AND COMPLIANCENon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | ENGINEERING & CONSTRUCTION DOCUMENT CENTRALIZATION AND COMPLIANCE | Non-RAMP | Non-RAMP | Non-RAMP | -13413.272 | 0 | 0 | 0 | -13413.272 | 762000 | 784999.92 | 808999.92 | 832999.92 | 3188999.76 | -775413.272 | -784999.92 | -808999.92 | -832999.92 | -3202413.032 | -101.8% | -100% | -100% | -100% | -100.4% | NO | 00921N | NO | NR
CapitalINFORMATION TECHNOLOGYENTERPRISE DISTRIBUTED ENERGY RESOURCE MANAGEMENT SYSTEM (DERMS)Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | ENTERPRISE DISTRIBUTED ENERGY RESOURCE MANAGEMENT SYSTEM (DERMS) | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 3933999.96 | 4051999.92 | 4173999.96 | 4299000 | 16458999.84 | -3933999.96 | -4051999.92 | -4173999.96 | -4299000 | -16458999.84 | -100% | -100% | -100% | -100% | -100% | YES | 00920BA | NO | NR
CapitalINFORMATION TECHNOLOGYENTERPRISE PRODUCTIVITY & COLLAB SDGENon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | ENTERPRISE PRODUCTIVITY & COLLAB SDGE | Non-RAMP | Non-RAMP | Non-RAMP | 1033667.114 | 0 | 0 | 0 | 1033667.114 | 0 | 0 | 0 | 0 | 0 | 1033667.114 | 0 | 0 | 0 | 1033667.114 | 100% | 100% | 100% | 100% | 100% | NO | 00921ZA | NO | NR
CapitalINFORMATION TECHNOLOGYFOUNDATIONAL ANALYTICS FOR SAFETY, COMPLIANCE AND EFFICIENCYNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | FOUNDATIONAL ANALYTICS FOR SAFETY, COMPLIANCE AND EFFICIENCY | Non-RAMP | Non-RAMP | Non-RAMP | 1022067.5685 | 0 | 0 | 0 | 1022067.5685 | 6930999.96 | 7138999.92 | 7353000 | 7573999.92 | 28996999.8 | -5908932.3915 | -7138999.92 | -7353000 | -7573999.92 | -27974932.2315 | -85.25% | -100% | -100% | -100% | -96.48% | YES | 00920BD | NO | NR
CapitalINFORMATION TECHNOLOGYGRC & REGULATORY MANAGEMENT SYSTEM - PHASE 3Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | GRC & REGULATORY MANAGEMENT SYSTEM - PHASE 3 | Non-RAMP | Non-RAMP | Non-RAMP | 1687748.1941 | 0 | 0 | 0 | 1687748.1941 | 1494000 | 1539000 | 1584999.96 | 1632999.96 | 6250999.92 | 193748.1941 | -1539000 | -1584999.96 | -1632999.96 | -4563251.7259 | 12.97% | -100% | -100% | -100% | -73% | NO | 00921A | NO | NR
CapitalINFORMATION TECHNOLOGYINVESTMENT PRIORITIZATIONNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | INVESTMENT PRIORITIZATION | Non-RAMP | Non-RAMP | Non-RAMP | 2874463.6965 | 0 | 0 | 0 | 2874463.6965 | 10935000 | 11262999.96 | 11601000 | 11949000 | 45747999.96 | -8060536.3035 | -11262999.96 | -11601000 | -11949000 | -42873536.2635 | -73.71% | -100% | -100% | -100% | -93.72% | YES | 00920E | NO | NR
CapitalINFORMATION TECHNOLOGYIOS EPOCH MOBILITY APPS 2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | IOS EPOCH MOBILITY APPS 2024 | Non-RAMP | Non-RAMP | Non-RAMP | 1084406.9816 | 0 | 0 | 0 | 1084406.9816 | 0 | 0 | 0 | 0 | 0 | 1084406.9816 | 0 | 0 | 0 | 1084406.9816 | 100% | 100% | 100% | 100% | 100% | YES | 00920ZB | NO | NR
CapitalINFORMATION TECHNOLOGYIT ELECTRIC OPERATIONS SYSTEMSFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | IT ELECTRIC OPERATIONS SYSTEMS | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 581513.7495 | 0 | 0 | 0 | 581513.7495 | 0 | 0 | 0 | 0 | 0 | 581513.7495 | 0 | 0 | 0 | 581513.7495 | 100% | 100% | 100% | 100% | 100% | YES | 00920ZC | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYIT NON-RAMP APPLICATIONS-SRMNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | IT NON-RAMP APPLICATIONS-SRM | Non-RAMP | Non-RAMP | Non-RAMP | 3300474.0042 | 0 | 0 | 0 | 3300474.0042 | 0 | 0 | 0 | 0 | 0 | 3300474.0042 | 0 | 0 | 0 | 3300474.0042 | 100% | 100% | 100% | 100% | 100% | YES | 00926C | NO | NR
CapitalINFORMATION TECHNOLOGYIT NON-RAMP CUSTOMER SERVICENon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | IT NON-RAMP CUSTOMER SERVICE | Non-RAMP | Non-RAMP | Non-RAMP | 1819729.8379 | 0 | 0 | 0 | 1819729.8379 | 0 | 0 | 0 | 0 | 0 | 1819729.8379 | 0 | 0 | 0 | 1819729.8379 | 100% | 100% | 100% | 100% | 100% | NO | 00926A | NO | NR
CapitalINFORMATION TECHNOLOGYIT QUALITY AND CONTINUOUS TESTING PLATFORMSNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | IT QUALITY AND CONTINUOUS TESTING PLATFORMS | Non-RAMP | Non-RAMP | Non-RAMP | 747611.8847 | 0 | 0 | 0 | 747611.8847 | 1174999.92 | 1209999.96 | 1245999.96 | 1282999.92 | 4913999.76 | -427388.0353 | -1209999.96 | -1245999.96 | -1282999.92 | -4166387.8753 | -36.37% | -100% | -100% | -100% | -84.79% | NO | 00907A | NO | NR
CapitalINFORMATION TECHNOLOGYLOCAL AREA DISTRIBUTION CONTROLLER (LADC) 2023-2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | LOCAL AREA DISTRIBUTION CONTROLLER (LADC) 2023-2024 | Non-RAMP | Non-RAMP | Non-RAMP | 913319.0524 | 0 | 0 | 0 | 913319.0524 | 0 | 0 | 0 | 0 | 0 | 913319.0524 | 0 | 0 | 0 | 913319.0524 | 100% | 100% | 100% | 100% | 100% | YES | 00920L | NO | NR
CapitalINFORMATION TECHNOLOGYMY ENERGY CENTERNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | MY ENERGY CENTER | Non-RAMP | Non-RAMP | Non-RAMP | 12152003.5315 | 0 | 0 | 0 | 12152003.5315 | 0 | 0 | 0 | 0 | 0 | 12152003.5315 | 0 | 0 | 0 | 12152003.5315 | 100% | 100% | 100% | 100% | 100% | NO | 00903ZB | NO | NR
CapitalINFORMATION TECHNOLOGYNETBRAIN ENHANCEMENTS (P)Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | NETBRAIN ENHANCEMENTS (P) | Non-RAMP | Non-RAMP | Non-RAMP | 465720.4716 | 0 | 0 | 0 | 465720.4716 | 0 | 0 | 0 | 0 | 0 | 465720.4716 | 0 | 0 | 0 | 465720.4716 | 100% | 100% | 100% | 100% | 100% | YES | 00925ZA | NO | NR
CapitalINFORMATION TECHNOLOGYNETWORK SYSTEMSFoundational Technology SystemsNetwork & Voice System ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | NETWORK SYSTEMS | Foundational Technology Systems | Network & Voice System Resiliency | N/A | 2217071.6865 | 0 | 0 | 0 | 2217071.6865 | 0 | 0 | 0 | 0 | 0 | 2217071.6865 | 0 | 0 | 0 | 2217071.6865 | 100% | 100% | 100% | 100% | 100% | YES | 00925ZC | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYNON-RAMP APPLICATIONSNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | NON-RAMP APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 7211006.9065 | 0 | 0 | 0 | 7211006.9065 | 0 | 0 | 0 | 0 | 0 | 7211006.9065 | 0 | 0 | 0 | 7211006.9065 | 100% | 100% | 100% | 100% | 100% | NO | 00926B | NO | NR
CapitalINFORMATION TECHNOLOGYPOWERWORKZ AGILE PROGRAMNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | POWERWORKZ AGILE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | 1027539.4194 | 0 | 0 | 0 | 1027539.4194 | 0 | 0 | 0 | 0 | 0 | 1027539.4194 | 0 | 0 | 0 | 1027539.4194 | 100% | 100% | 100% | 100% | 100% | YES | 00920ZA | NO | NR
CapitalINFORMATION TECHNOLOGYPROJECT ECHELON SDGENon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | PROJECT ECHELON SDGE | Non-RAMP | Non-RAMP | Non-RAMP | 2007405.413 | 0 | 0 | 0 | 2007405.413 | 0 | 0 | 0 | 0 | 0 | 2007405.413 | 0 | 0 | 0 | 2007405.413 | 100% | 100% | 100% | 100% | 100% | NO | 00903ZA | NO | NR
CapitalINFORMATION TECHNOLOGYRAMP - ADVANCED DATA AND DECISION MODELINGFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - ADVANCED DATA AND DECISION MODELING | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 643603.255 | 0 | 0 | 0 | 643603.255 | 4677999.96 | 4818000 | 4962999.96 | 5112000 | 19570999.92 | -4034396.705 | -4818000 | -4962999.96 | -5112000 | -18927396.665 | -86.24% | -100% | -100% | -100% | -96.71% | YES | 00920BE | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - CLOUD FOUNDATIONSFoundational Technology SystemsCloud Resiliency ServicesN/A | Capital | INFORMATION TECHNOLOGY | RAMP - CLOUD FOUNDATIONS | Foundational Technology Systems | Cloud Resiliency Services | N/A | 5413520.6227 | 0 | 0 | 0 | 5413520.6227 | 6274999.92 | 6462999.96 | 6657000 | 6856999.92 | 26251999.8 | -861479.2973 | -6462999.96 | -6657000 | -6856999.92 | -20838479.1773 | -13.73% | -100% | -100% | -100% | -79.38% | YES | 00908X | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - DECISION ANALYTICS & SITUATIONAL AWARENESSFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - DECISION ANALYTICS & SITUATIONAL AWARENESS | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 525487.6271 | 0 | 0 | 0 | 525487.6271 | 1813999.92 | 1867999.92 | 1923999.96 | 1981999.92 | 7587999.72 | -1288512.2929 | -1867999.92 | -1923999.96 | -1981999.92 | -7062512.093 | -71.03% | -100% | -100% | -100% | -93.07% | YES | 00920BF | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - DIGI REMOTE MANAGER 2023Foundational Technology SystemsMonitoring Systems and ServicesN/A | Capital | INFORMATION TECHNOLOGY | RAMP - DIGI REMOTE MANAGER 2023 | Foundational Technology Systems | Monitoring Systems and Services | N/A | 6865.9018 | 0 | 0 | 0 | 6865.9018 | 0 | 0 | 0 | 0 | 0 | 6865.9018 | 0 | 0 | 0 | 6865.9018 | 100% | 100% | 100% | 100% | 100% | YES | 00908O | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - DIGITAL ASSET AND DAMAGES DETECTION PLATFORMFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL ASSET AND DAMAGES DETECTION PLATFORM | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 2529952.3196 | 0 | 0 | 0 | 2529952.3196 | 4347000 | 4476999.96 | 4611000 | 4749000 | 18183999.96 | -1817047.6804 | -4476999.96 | -4611000 | -4749000 | -15654047.6404 | -41.8% | -100% | -100% | -100% | -86.09% | YES | 00920P | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - DIGITAL PROCESS AUTOMATIONFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL PROCESS AUTOMATION | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 1758092.6095 | 0 | 0 | 0 | 1758092.6095 | 1893999.96 | 1950999.96 | 2008999.92 | 2070000 | 7923999.84 | -135907.3505 | -1950999.96 | -2008999.92 | -2070000 | -6165907.2305 | -7.176% | -100% | -100% | -100% | -77.81% | YES | 00920BC | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - DIGITAL PROCESS AUTOMATIONNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL PROCESS AUTOMATION | Non-RAMP | Non-RAMP | Non-RAMP | 3516182.219 | 0 | 0 | 0 | 3516182.219 | 3837999.96 | 3952999.92 | 4071000 | 4192999.92 | 16054999.8 | -321817.741 | -3952999.92 | -4071000 | -4192999.92 | -12538817.581 | -8.385% | -100% | -100% | -100% | -78.1% | YES | 00920BC | NO | NR
CapitalINFORMATION TECHNOLOGYRAMP - DIGITAL WORKSPACEFoundational Technology SystemsEnd User Access and Supporting ServicesN/A | Capital | INFORMATION TECHNOLOGY | RAMP - DIGITAL WORKSPACE | Foundational Technology Systems | End User Access and Supporting Services | N/A | 68240.8059 | 0 | 0 | 0 | 68240.8059 | 0 | 0 | 0 | 0 | 0 | 68240.8059 | 0 | 0 | 0 | 68240.8059 | 100% | 100% | 100% | 100% | 100% | YES | 00908B | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - ELECTIRC DISTRIBUTION ASSET INVESTMENTAsset ManagementAsset ManagementN/A | Capital | INFORMATION TECHNOLOGY | RAMP - ELECTIRC DISTRIBUTION ASSET INVESTMENT | Asset Management | Asset Management | N/A | 0 | 0 | 0 | 0 | 0 | 4677999.96 | 4818000 | 4962999.96 | 5112000 | 19570999.92 | -4677999.96 | -4818000 | -4962999.96 | -5112000 | -19570999.92 | -100% | -100% | -100% | -100% | -100% | YES | 00920BL | NO | SDG&E-CFF-1
CapitalINFORMATION TECHNOLOGYRAMP - EMERGENCY COMMUNICATIONS ENHANCEMENTSFoundational Technology SystemsEmergency Operations Center (EOC) Technology ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - EMERGENCY COMMUNICATIONS ENHANCEMENTS | Foundational Technology Systems | Emergency Operations Center (EOC) Technology Resiliency | N/A | 556.4929 | 0 | 0 | 0 | 556.4929 | 0 | 0 | 0 | 0 | 0 | 556.4929 | 0 | 0 | 0 | 556.4929 | 100% | 100% | 100% | 100% | 100% | YES | 00908F | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - ENERGY TRANSITION DIGITAL TWINFoundational Technology SystemsMonitoring Systems and ServicesN/A | Capital | INFORMATION TECHNOLOGY | RAMP - ENERGY TRANSITION DIGITAL TWIN | Foundational Technology Systems | Monitoring Systems and Services | N/A | 2517037.4197 | 0 | 0 | 0 | 2517037.4197 | 2346000 | 2415999.96 | 2487999.96 | 2562999.96 | 9812999.88 | 171037.4197 | -2415999.96 | -2487999.96 | -2562999.96 | -7295962.4603 | 7.291% | -100% | -100% | -100% | -74.35% | YES | 00920BB | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - FIELD MOBILE HARDWARE REPLACEMENTFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - FIELD MOBILE HARDWARE REPLACEMENT | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 2554000.5769 | 0 | 0 | 0 | 2554000.5769 | 4186999.92 | 4312999.92 | 4443000 | 4575999.96 | 17518999.8 | -1632999.3431 | -4312999.92 | -4443000 | -4575999.96 | -14964999.2231 | -39% | -100% | -100% | -100% | -85.42% | YES | 00920H | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - FIELD SERVICE DELIVERY (FSD) - DATA & ANALYTICS PLATFORMFoundational Technology SystemsElectric Operations Systems (SDGE) Resiliency; Gas Operations Systems ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - FIELD SERVICE DELIVERY (FSD) - DATA & ANALYTICS PLATFORM | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency; Gas Operations Systems Resiliency | N/A | 3194318.7468 | 0 | 0 | 0 | 3194318.7468 | 5754999.96 | 5928000 | 6105999.96 | 6288999.96 | 24077999.88 | -2560681.2132 | -5928000 | -6105999.96 | -6288999.96 | -20883681.1332 | -44.49% | -100% | -100% | -100% | -86.73% | YES | 00920T | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - FIELD SERVICE DELIVERY (FSD) - SCHEDULING & DISPATCH PHASEFoundational Technology SystemsElectric Operations Systems (SDGE) Resiliency; Gas Operations Systems ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - FIELD SERVICE DELIVERY (FSD) - SCHEDULING & DISPATCH PHASE | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency; Gas Operations Systems Resiliency | N/A | 17630759.3042 | 0 | 0 | 0 | 17630759.3042 | 12480000 | 12853999.92 | 13239999.96 | 13636999.92 | 52210999.8 | 5150759.3042 | -12853999.92 | -13239999.96 | -13636999.92 | -34580240.4958 | 41.27% | -100% | -100% | -100% | -66.23% | YES | 00920AI | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - GIS MODERNIZATIONFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - GIS MODERNIZATION | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 2403155.7766 | 0 | 0 | 0 | 2403155.7766 | 405999.96 | 417999.96 | 430999.92 | 444000 | 1698999.84 | 1997155.8166 | -417999.96 | -430999.92 | -444000 | 704155.9367 | 491.9% | -100% | -100% | -100% | 41.45% | YES | 00920M | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - INFRASTRUCTURE AS A SERVICE (IAAS) IMPLEMENTATIONFoundational Technology SystemsCloud Resiliency ServicesN/A | Capital | INFORMATION TECHNOLOGY | RAMP - INFRASTRUCTURE AS A SERVICE (IAAS) IMPLEMENTATION | Foundational Technology Systems | Cloud Resiliency Services | N/A | 0 | 0 | 0 | 0 | 0 | 2362999.92 | 2433999.96 | 2506999.92 | 2581999.92 | 9885999.72 | -2362999.92 | -2433999.96 | -2506999.92 | -2581999.92 | -9885999.72 | -100% | -100% | -100% | -100% | -100% | YES | 00908W | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - JUNIPER 2022 EQUIPMENT REPLACEMENT AGREEMENTFoundational Technology SystemsNetwork & Voice System ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - JUNIPER 2022 EQUIPMENT REPLACEMENT AGREEMENT | Foundational Technology Systems | Network & Voice System Resiliency | N/A | 1370514 | 0 | 0 | 0 | 1370514 | 1408999.92 | 1450999.92 | 1494999.96 | 1539999.96 | 5894999.76 | -38485.92 | -1450999.92 | -1494999.96 | -1539999.96 | -4524485.76 | -2.731% | -100% | -100% | -100% | -76.75% | YES | 00925F | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - LOCAL AREA NETWORK (LAN) REFRESH 2022Foundational Technology SystemsNetwork & Voice System ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - LOCAL AREA NETWORK (LAN) REFRESH 2022 | Foundational Technology Systems | Network & Voice System Resiliency | N/A | 1337599.3942 | 0 | 0 | 0 | 1337599.3942 | 5841000 | 6015999.96 | 6196999.92 | 6382999.92 | 24436999.8 | -4503400.6058 | -6015999.96 | -6196999.92 | -6382999.92 | -23099400.4058 | -77.1% | -100% | -100% | -100% | -94.53% | YES | 00925L | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - TELECOM SITE IMPROVEMENTSFoundational Technology SystemsNetwork & Voice System ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - TELECOM SITE IMPROVEMENTS | Foundational Technology Systems | Network & Voice System Resiliency | N/A | 2213183.806 | 0 | 0 | 0 | 2213183.806 | 4395999.96 | 4527999.96 | 4663999.92 | 4803999.96 | 18391999.8 | -2182816.154 | -4527999.96 | -4663999.92 | -4803999.96 | -16178815.994 | -49.65% | -100% | -100% | -100% | -87.97% | YES | 00925Q | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - TRANSMISSION COMMUNICATIONS RELIABILITY IMPROVEMENT (TCRI) 2024Foundational Technology SystemsNetwork & Voice System ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - TRANSMISSION COMMUNICATIONS RELIABILITY IMPROVEMENT (TCRI) 2024 | Foundational Technology Systems | Network & Voice System Resiliency | N/A | 3096972.5737 | 0 | 0 | 0 | 3096972.5737 | 5532000 | 5697999.96 | 5869999.92 | 6045999.96 | 23145999.84 | -2435027.4263 | -5697999.96 | -5869999.92 | -6045999.96 | -20049027.2663 | -44.02% | -100% | -100% | -100% | -86.62% | YES | 00925K | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - VEGETATION MANAGEMENT - WORK MANAGEMENTFoundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - VEGETATION MANAGEMENT - WORK MANAGEMENT | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 0 | 0 | 0 | 0 | 0 | 2103999.96 | 2166999.96 | 2232000 | 2298999.96 | 8801999.88 | -2103999.96 | -2166999.96 | -2232000 | -2298999.96 | -8801999.88 | -100% | -100% | -100% | -100% | -100% | YES | 00920R | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - VEHICLE TELEMATICS - PHASE 2Foundational Technology SystemsElectric Operations Systems (SDGE) ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - VEHICLE TELEMATICS - PHASE 2 | Foundational Technology Systems | Electric Operations Systems (SDGE) Resiliency | N/A | 0 | 0 | 0 | 0 | 0 | 390000 | 402000 | 414000 | 426000 | 1632000 | -390000 | -402000 | -414000 | -426000 | -1632000 | -100% | -100% | -100% | -100% | -100% | YES | 00920BI | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - VIRTUAL DESKTOP EXPANSION (VDI) - PHASE 2Foundational Technology SystemsEnd User Access and Supporting ServicesN/A | Capital | INFORMATION TECHNOLOGY | RAMP - VIRTUAL DESKTOP EXPANSION (VDI) - PHASE 2 | Foundational Technology Systems | End User Access and Supporting Services | N/A | 128304.5585 | 0 | 0 | 0 | 128304.5585 | 1830999.96 | 1884999.96 | 1941999.96 | 2001000 | 7658999.88 | -1702695.4015 | -1884999.96 | -1941999.96 | -2001000 | -7530695.3215 | -92.99% | -100% | -100% | -100% | -98.32% | YES | 00908C | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP - WIDE AREA NETWORK (WAN) REFRESHFoundational Technology SystemsNetwork & Voice System ResiliencyN/A | Capital | INFORMATION TECHNOLOGY | RAMP - WIDE AREA NETWORK (WAN) REFRESH | Foundational Technology Systems | Network & Voice System Resiliency | N/A | 424810.5481 | 0 | 0 | 0 | 424810.5481 | 3582000 | 3690000 | 3801000 | 3915000 | 14988000 | -3157189.4518 | -3690000 | -3801000 | -3915000 | -14563189.4519 | -88.14% | -100% | -100% | -100% | -97.17% | YES | 00925R | NO | SDG&E-CFF-4
CapitalINFORMATION TECHNOLOGYRAMP- ASSET 360 - ASSET DATA FOUNDATIONAsset ManagementAsset ManagementN/A | Capital | INFORMATION TECHNOLOGY | RAMP- ASSET 360 - ASSET DATA FOUNDATION | Asset Management | Asset Management | N/A | 2271951.7344 | 0 | 0 | 0 | 2271951.7344 | 2941999.92 | 3030000 | 3120999.96 | 3214999.92 | 12307999.8 | -670048.1856 | -3030000 | -3120999.96 | -3214999.92 | -10036048.0656 | -22.78% | -100% | -100% | -100% | -81.54% | YES | 00920BM | NO | SDG&E-CFF-1
CapitalINFORMATION TECHNOLOGYRCM UPGRADESNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | RCM UPGRADES | Non-RAMP | Non-RAMP | Non-RAMP | 236700 | 0 | 0 | 0 | 236700 | 0 | 0 | 0 | 0 | 0 | 236700 | 0 | 0 | 0 | 236700 | 100% | 100% | 100% | 100% | 100% | YES | 00908ZA | NO | NR
CapitalINFORMATION TECHNOLOGYSMART GRID OPERATIONS 2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | SMART GRID OPERATIONS 2024 | Non-RAMP | Non-RAMP | Non-RAMP | 3434767.5366 | 0 | 0 | 0 | 3434767.5366 | 2970000 | 3058999.92 | 3150999.96 | 3246000 | 12425999.88 | 464767.5366 | -3058999.92 | -3150999.96 | -3246000 | -8991232.3434 | 15.65% | -100% | -100% | -100% | -72.36% | YES | 00920C | NO | NR
CapitalINFORMATION TECHNOLOGYSMART METER (PRODUCT) 2022-2024Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | SMART METER (PRODUCT) 2022-2024 | Non-RAMP | Non-RAMP | Non-RAMP | 1820233.5037 | 0 | 0 | 0 | 1820233.5037 | 0 | 0 | 0 | 0 | 0 | 1820233.5037 | 0 | 0 | 0 | 1820233.5037 | 100% | 100% | 100% | 100% | 100% | NO | 00900D | NO | NR
CapitalINFORMATION TECHNOLOGYSMART METER 2.0Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | SMART METER 2.0 | Non-RAMP | Non-RAMP | Non-RAMP | 13348505.1075 | 0 | 0 | 0 | 13348505.1075 | 0 | 0 | 0 | 0 | 0 | 13348505.1075 | 0 | 0 | 0 | 13348505.1075 | 100% | 100% | 100% | 100% | 100% | NO | 218810 | NO | NR
CapitalINFORMATION TECHNOLOGYSMART METER NETWORK DEVICESNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | SMART METER NETWORK DEVICES | Non-RAMP | Non-RAMP | Non-RAMP | 356425.1646 | 0 | 0 | 0 | 356425.1646 | 0 | 0 | 0 | 0 | 0 | 356425.1646 | 0 | 0 | 0 | 356425.1646 | 100% | 100% | 100% | 100% | 100% | NO | 00900ZA | NO | NR
CapitalINFORMATION TECHNOLOGYSORT UPGRADE- ENTERPRISENon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | SORT UPGRADE- ENTERPRISE | Non-RAMP | Non-RAMP | Non-RAMP | 1304731.636 | 0 | 0 | 0 | 1304731.636 | 0 | 0 | 0 | 0 | 0 | 1304731.636 | 0 | 0 | 0 | 1304731.636 | 100% | 100% | 100% | 100% | 100% | NO | 00903ZC | NO | NR
CapitalINFORMATION TECHNOLOGYTEMS 2024 (P)Non-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | TEMS 2024 (P) | Non-RAMP | Non-RAMP | Non-RAMP | 551463 | 0 | 0 | 0 | 551463 | 0 | 0 | 0 | 0 | 0 | 551463 | 0 | 0 | 0 | 551463 | 100% | 100% | 100% | 100% | 100% | YES | 00925ZB | NO | NR
CapitalINFORMATION TECHNOLOGYTEST ACCELERATION ENABLEMENT (TAE) WITH DEVSECOPSNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | TEST ACCELERATION ENABLEMENT (TAE) WITH DEVSECOPS | Non-RAMP | Non-RAMP | Non-RAMP | 1454125.8917 | 0 | 0 | 0 | 1454125.8917 | 2038999.92 | 2100000 | 2163000 | 2227999.92 | 8529999.84 | -584874.0283 | -2100000 | -2163000 | -2227999.92 | -7075873.9483 | -28.68% | -100% | -100% | -100% | -82.95% | NO | 00921D | NO | NR
CapitalINFORMATION TECHNOLOGYTM1 ENHANCEMENTS- O&M PROCESS MODERNIZATIONNon-RAMPNon-RAMPNon-RAMP | Capital | INFORMATION TECHNOLOGY | TM1 ENHANCEMENTS- O&M PROCESS MODERNIZATION | Non-RAMP | Non-RAMP | Non-RAMP | 123167.4316 | 0 | 0 | 0 | 123167.4316 | 0 | 0 | 0 | 0 | 0 | 123167.4316 | 0 | 0 | 0 | 123167.4316 | 100% | 100% | 100% | 100% | 100% | NO | 00921ZB | NO | NR
CapitalSAFETY MANAGEMENT SYSTEMSCONTRACTOR FIELD SAFETY MANAGEMENT POOLIncident Involving a ContractorEnhanced Verification of Class 1Overall | Capital | SAFETY MANAGEMENT SYSTEMS | CONTRACTOR FIELD SAFETY MANAGEMENT POOL | Incident Involving a Contractor | Enhanced Verification of Class 1 | Overall | 97280.6725 | 0 | 0 | 0 | 97280.6725 | 144000 | 147999.96 | 151999.92 | 156999.96 | 600999.84 | -46719.3275 | -147999.96 | -151999.92 | -156999.96 | -503719.1675 | -32.44% | -100% | -100% | -100% | -83.81% | YES | S09060 | NO | SDG&E-Risk-4
CapitalSAFETY MANAGEMENT SYSTEMSCONTRACTOR FIELD SAFETY MANAGEMENT POOLIncident Involving a ContractorEnterprise-Wide Contractor Incident andN/A | Capital | SAFETY MANAGEMENT SYSTEMS | CONTRACTOR FIELD SAFETY MANAGEMENT POOL | Incident Involving a Contractor | Enterprise-Wide Contractor Incident and | N/A | 0 | 0 | 0 | 0 | 0 | 70999.92 | 72999.96 | 75000 | 76999.92 | 295999.8 | -70999.92 | -72999.96 | -75000 | -76999.92 | -295999.8 | -100% | -100% | -100% | -100% | -100% | YES | S09060 | NO | SDG&E-Risk-4
CapitalSAFETY MANAGEMENT SYSTEMSCONTRACTOR FIELD SAFETY MANAGEMENT POOLIncident Involving a ContractorField Safety OversightOverall | Capital | SAFETY MANAGEMENT SYSTEMS | CONTRACTOR FIELD SAFETY MANAGEMENT POOL | Incident Involving a Contractor | Field Safety Oversight | Overall | 2211948.8014 | 0 | 0 | 0 | 2211948.8014 | 2757999.96 | 2841000 | 2925999.96 | 3013999.92 | 11538999.84 | -546051.1586 | -2841000 | -2925999.96 | -3013999.92 | -9327051.0386 | -19.8% | -100% | -100% | -100% | -80.83% | YES | S09060 | NO | SDG&E-Risk-4
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTADVANCED PROTECTIONWildfire Involving SDG&E EquipmentAdvanced ProtectionTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ADVANCED PROTECTION | Wildfire Involving SDG&E Equipment | Advanced Protection | Tier 3 | 14811763.9553 | 0 | 0 | 0 | 14811763.9553 | 6945999.96 | 7153999.92 | 7368000 | 7588999.92 | 29056999.8 | 7865763.9953 | -7153999.92 | -7368000 | -7588999.92 | -14245235.8447 | 113.2% | -100% | -100% | -100% | -49.03% | YES | 152590 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTADVANCED WEATHER STATION INTEGRATION AND FORECASTWildfire Involving SDG&E EquipmentAdvanced Weather Station IntegrationN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ADVANCED WEATHER STATION INTEGRATION AND FORECAST | Wildfire Involving SDG&E Equipment | Advanced Weather Station Integration | N/A | 116008.5098 | 0 | 0 | 0 | 116008.5098 | 475999.92 | 489999.96 | 504999.96 | 519999.96 | 1990999.8 | -359991.4102 | -489999.96 | -504999.96 | -519999.96 | -1874991.2902 | -75.63% | -100% | -100% | -100% | -94.17% | YES | 192470 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTAVIATION FIREFIGHTING PROGRAMWildfire Involving SDG&E EquipmentAviation Firefighting ProgramTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | AVIATION FIREFIGHTING PROGRAM | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 3 | 2241358.8401 | 0 | 0 | 0 | 2241358.8401 | 9567999.96 | 9855999.96 | 10152000 | 10456999.92 | 40032999.84 | -7326641.12 | -9855999.96 | -10152000 | -10456999.92 | -37791640.9999 | -76.57% | -100% | -100% | -100% | -94.4% | YES | 202770 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTCNF FIRE HARDENINGWildfire Involving SDG&E EquipmentCleveland National Forest Fire Hardening T1-T2Tier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | CNF FIRE HARDENING | Wildfire Involving SDG&E Equipment | Cleveland National Forest Fire Hardening T1-T2 | Tier 3 | 1035885.1086 | 0 | 0 | 0 | 1035885.1086 | 1512000 | 1557000 | 1603999.92 | 1651999.92 | 6324999.84 | -476114.8914 | -1557000 | -1603999.92 | -1651999.92 | -5289114.7314 | -31.49% | -100% | -100% | -100% | -83.62% | YES | 81650 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTCORRECTIVE MAINTENANCE PROGRAM TIER 2&3Wildfire Involving SDG&E EquipmentTransmission System InspectionN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | CORRECTIVE MAINTENANCE PROGRAM TIER 2&3 | Wildfire Involving SDG&E Equipment | Transmission System Inspection | N/A | 1042850.7261 | 0 | 0 | 0 | 1042850.7261 | 726999.96 | 748999.92 | 771000 | 793999.92 | 3040999.8 | 315850.7661 | -748999.92 | -771000 | -793999.92 | -1998149.0739 | 43.45% | -100% | -100% | -100% | -65.71% | YES | 201270 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTDIGITAL FORTRESSFoundational Technology SystemsEmergency Management OperationsN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | DIGITAL FORTRESS | Foundational Technology Systems | Emergency Management Operations | N/A | 3153510.0469 | 0 | 0 | 0 | 3153510.0469 | 0 | 0 | 0 | 0 | 0 | 3153510.0469 | 0 | 0 | 0 | 3153510.0469 | 100% | 100% | 100% | 100% | 100% | YES | 218820 | YES | SDG&E-CFF-4
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTDRONE INVESTIGATION ASSESMENT AND REPAIRWildfire Involving SDG&E EquipmentDistribution System Inspection Drone InspectionsTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | DRONE INVESTIGATION ASSESMENT AND REPAIR | Wildfire Involving SDG&E Equipment | Distribution System Inspection Drone Inspections | Tier 2 | 73078532.4154 | 0 | 0 | 0 | 73078532.4154 | 8665999.92 | 8925999.96 | 9193999.92 | 9469999.92 | 36255999.72 | 64412532.4954 | -8925999.96 | -9193999.92 | -9469999.92 | 36822532.6954 | 743.3% | -100% | -100% | -100% | 101.6% | YES | 202480 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTEMERGENCY MANAGEMENT OPERATIONSFoundational Technology SystemsEmergency Management OperationsN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | EMERGENCY MANAGEMENT OPERATIONS | Foundational Technology Systems | Emergency Management Operations | N/A | 0 | 0 | 0 | 0 | 0 | 2949000 | 3036999.96 | 3127999.92 | 3222000 | 12335999.88 | -2949000 | -3036999.96 | -3127999.92 | -3222000 | -12335999.88 | -100% | -100% | -100% | -100% | -100% | YES | 218790 | YES | SDG&E-CFF-4
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTFIRE SCIENCE ENHANCEMENT (WRRM-OPS)Wildfire Involving SDG&E EquipmentWRRM - OPSN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | FIRE SCIENCE ENHANCEMENT (WRRM-OPS) | Wildfire Involving SDG&E Equipment | WRRM - OPS | N/A | 0.45004 | 0 | 0 | 0 | -838494.59 | 3144999.96 | 3238999.92 | 3336000 | 3435999.96 | 13155999.84 | -3144999.51 | -3238999.92 | -3336000 | -3435999.96 | -13994494.43 | -100% | -100% | -100% | -100% | -106.4% | YES | 192480 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTHFTD EXPULSION FUSE REPLACEMENTWildfire Involving SDG&E EquipmentHFTD Expulsion Fuse ReplacementsTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD EXPULSION FUSE REPLACEMENT | Wildfire Involving SDG&E Equipment | HFTD Expulsion Fuse Replacements | Tier 2 | 99058.3415 | 0 | 0 | 0 | 99058.3415 | 0 | 0 | 0 | 0 | 0 | 99058.3415 | 0 | 0 | 0 | 99058.3415 | 100% | 100% | 100% | 100% | 100% | YES | 192420 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTHFTD EXPULSION FUSE REPLACEMENTWildfire Involving SDG&E EquipmentHFTD Expulsion Fuse ReplacementsTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD EXPULSION FUSE REPLACEMENT | Wildfire Involving SDG&E Equipment | HFTD Expulsion Fuse Replacements | Tier 3 | 107313.2033 | 0 | 0 | 0 | 107313.2033 | 0 | 0 | 0 | 0 | 0 | 107313.2033 | 0 | 0 | 0 | 107313.2033 | 100% | 100% | 100% | 100% | 100% | YES | 192420 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTHFTD HOT LINE CLAMPSWildfire Involving SDG&E EquipmentHotline ClampsTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD HOT LINE CLAMPS | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 2 | 578970.6886 | 0 | 0 | 0 | 578970.6886 | 0 | 0 | 0 | 0 | 0 | 578970.6886 | 0 | 0 | 0 | 578970.6886 | 100% | 100% | 100% | 100% | 100% | YES | 242420 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTHFTD HOT LINE CLAMPSWildfire Involving SDG&E EquipmentHotline ClampsTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD HOT LINE CLAMPS | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 3 | 102171.298 | 0 | 0 | 0 | 102171.298 | 0 | 0 | 0 | 0 | 0 | 102171.298 | 0 | 0 | 0 | 102171.298 | 100% | 100% | 100% | 100% | 100% | YES | 242420 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTHFTD SCADA CAPACITOR REPLACEMENTWildfire Involving SDG&E EquipmentSCADA Capacitors (HFTD Tier 2)Tier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD SCADA CAPACITOR REPLACEMENT | Wildfire Involving SDG&E Equipment | SCADA Capacitors (HFTD Tier 2) | Tier 2 | 189384.0625 | 0 | 0 | 0 | 189384.0625 | 1788999.96 | 1842999.96 | 1897999.92 | 1954999.92 | 7484999.76 | -1599615.8975 | -1842999.96 | -1897999.92 | -1954999.92 | -7295615.6975 | -89.41% | -100% | -100% | -100% | -97.47% | YES | 202580 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTHFTD TRANSM. FIBER OPTICSWildfire Involving SDG&E EquipmentLTE Communication NetworkN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HFTD TRANSM. FIBER OPTICS | Wildfire Involving SDG&E Equipment | LTE Communication Network | N/A | 13676161.8256 | 0 | 0 | 0 | 13676161.8256 | 9652999.92 | 9942999.96 | 10240999.92 | 10548000 | 40384999.8 | 4023161.9056 | -9942999.96 | -10240999.92 | -10548000 | -26708837.9744 | 41.68% | -100% | -100% | -100% | -66.14% | YES | 191340 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTHIGH RISK POLE REPLACEMENT PROGRAM HFTDWildfire Involving SDG&E EquipmentStrategic Pole Replacement Program (HFTD)HFTD Tiers 2 & 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | HIGH RISK POLE REPLACEMENT PROGRAM HFTD | Wildfire Involving SDG&E Equipment | Strategic Pole Replacement Program (HFTD) | HFTD Tiers 2 & 3 | 2444670.0972 | 0 | 0 | 0 | 2444670.0972 | 7957999.92 | 8196999.96 | 8442999.96 | 8695999.92 | 33293999.76 | -5513329.8228 | -8196999.96 | -8442999.96 | -8695999.92 | -30849329.6628 | -69.28% | -100% | -100% | -100% | -92.66% | YES | 222420 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTLIGHTNING ARRESTOR REPLACEMENT PROGRAMElectric Infrastructure IntegrityAvian Protection ProgramOH Distribution | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | LIGHTNING ARRESTOR REPLACEMENT PROGRAM | Electric Infrastructure Integrity | Avian Protection Program | OH Distribution | 1065808.6687 | 0 | 0 | 0 | 1065808.6687 | 1719000 | 1770999.96 | 1824000 | 1878999.96 | 7192999.92 | -653191.3313 | -1770999.96 | -1824000 | -1878999.96 | -6127191.2513 | -38% | -100% | -100% | -100% | -85.18% | YES | 202820 | YES | SDG&E-Risk-2
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTLIGHTNING ARRESTOR REPLACEMENT PROGRAMWildfire Involving SDG&E EquipmentLightning Arrestor Removal/Replacement ProgramTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | LIGHTNING ARRESTOR REPLACEMENT PROGRAM | Wildfire Involving SDG&E Equipment | Lightning Arrestor Removal/Replacement Program | Tier 2 | 1238736.1041 | 0 | 0 | 0 | 1238736.1041 | 232999.92 | 240000 | 246999.96 | 253999.92 | 973999.8 | 1005736.1841 | -240000 | -246999.96 | -253999.92 | 264736.3041 | 431.6% | -100% | -100% | -100% | 27.18% | YES | 202820 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTLIGHTNING ARRESTOR REPLACEMENT PROGRAMWildfire Involving SDG&E EquipmentLightning Arrestor Removal/Replacement ProgramTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | LIGHTNING ARRESTOR REPLACEMENT PROGRAM | Wildfire Involving SDG&E Equipment | Lightning Arrestor Removal/Replacement Program | Tier 3 | 1454168.47 | 0 | 0 | 0 | 1454168.47 | 2059999.92 | 2121999.96 | 2185999.92 | 2251999.92 | 8619999.72 | -605831.45 | -2121999.96 | -2185999.92 | -2251999.92 | -7165831.25 | -29.41% | -100% | -100% | -100% | -83.13% | YES | 202820 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTOH SYSTEM COVERED CONDUCTORWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Covered ConductorTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM COVERED CONDUCTOR | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Conductor | Tier 2 | 43446468.6545 | 0 | 0 | 0 | 43446468.6545 | 16224999.96 | 16224999.96 | 16224999.96 | 16224999.96 | 64899999.84 | 27221468.6945 | -16224999.96 | -16224999.96 | -16224999.96 | -21453531.1855 | 167.8% | -100% | -100% | -100% | -33.06% | YES | 202850 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTOH SYSTEM COVERED CONDUCTORWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Covered ConductorTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM COVERED CONDUCTOR | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Conductor | Tier 3 | 31515426.5974 | 0 | 0 | 0 | 31515426.5974 | 73915999.92 | 73915999.92 | 73915999.92 | 73915999.92 | 295663999.68 | -42400573.3226 | -73915999.92 | -73915999.92 | -73915999.92 | -264148573.0826 | -57.36% | -100% | -100% | -100% | -89.34% | YES | 202850 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTOH SYSTEM TRADITIONAL HARDENINGWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Bare ConductorTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM TRADITIONAL HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 2 | 321847.8481 | 0 | 0 | 0 | 321847.8481 | 0 | 0 | 0 | 0 | 0 | 321847.8481 | 0 | 0 | 0 | 321847.8481 | 100% | 100% | 100% | 100% | 100% | YES | 202840 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTOH SYSTEM TRADITIONAL HARDENINGWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Bare ConductorTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OH SYSTEM TRADITIONAL HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 3 | 3254239.347 | 0 | 0 | 0 | 3254239.347 | 6868999.92 | 7074999.96 | 7287000 | 7506000 | 28736999.88 | -3614760.573 | -7074999.96 | -7287000 | -7506000 | -25482760.533 | -52.62% | -100% | -100% | -100% | -88.68% | YES | 202840 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTOVERHEAD TRANSMISSION FIRE HARDENING (DISTRIBUTION UNDERBUILD)Wildfire Involving SDG&E EquipmentOH Trans Fire Hardening Dist UnderbuildTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OVERHEAD TRANSMISSION FIRE HARDENING (DISTRIBUTION UNDERBUILD) | Wildfire Involving SDG&E Equipment | OH Trans Fire Hardening Dist Underbuild | Tier 2 | 12448112.2909 | 0 | 0 | 0 | 12448112.2909 | 16791999.96 | 17295000 | 17814000 | 18346999.92 | 70247999.88 | -4343887.6691 | -17295000 | -17814000 | -18346999.92 | -57799887.5891 | -25.87% | -100% | -100% | -100% | -82.28% | YES | 141400 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTOVERHEAD TRANSMISSION FIRE HARDENING (DISTRIBUTION UNDERBUILD)Wildfire Involving SDG&E EquipmentOH Trans Fire Hardening Dist UnderbuildTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | OVERHEAD TRANSMISSION FIRE HARDENING (DISTRIBUTION UNDERBUILD) | Wildfire Involving SDG&E Equipment | OH Trans Fire Hardening Dist Underbuild | Tier 3 | 0 | 0 | 0 | 0 | 0 | 1341000 | 1381999.92 | 1422999.96 | 1465999.92 | 5611999.8 | -1341000 | -1381999.92 | -1422999.96 | -1465999.92 | -5611999.8 | -100% | -100% | -100% | -100% | -100% | YES | 141400 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPOLE REPLACEMENT AND REINFORCEMENT IN HFTDWildfire Involving SDG&E EquipmentDistribution System Inspection CMP 10 Year Intrusive T2Tier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP 10 Year Intrusive T2 | Tier 2 | 208177.9167 | 0 | 0 | 0 | 208177.9167 | 1482999.96 | 1527000 | 1572999.96 | 1620000 | 6202999.92 | -1274822.0433 | -1527000 | -1572999.96 | -1620000 | -5994822.0033 | -85.96% | -100% | -100% | -100% | -96.64% | YES | 2390 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPOLE REPLACEMENT AND REINFORCEMENT IN HFTDWildfire Involving SDG&E EquipmentDistribution System Inspection CMP 5 Year Detailed Inspections T1-T2Tier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP 5 Year Detailed Inspections T1-T2 | Tier 2 | 3747202.6698 | 0 | 0 | 0 | 3747202.6698 | 4257000 | 4384999.92 | 4516999.92 | 4651999.92 | 17810999.76 | -509797.3302 | -4384999.92 | -4516999.92 | -4651999.92 | -14063797.0902 | -11.98% | -100% | -100% | -100% | -78.96% | YES | 2390 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPOLE REPLACEMENT AND REINFORCEMENT IN HFTDWildfire Involving SDG&E EquipmentDistribution System Inspection CMP 5 Year Detailed Inspections T1-T2Tier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP 5 Year Detailed Inspections T1-T2 | Tier 3 | 4059469.5606 | 0 | 0 | 0 | 4059469.5606 | 3285000 | 3382999.92 | 3483999.96 | 3588999.96 | 13740999.84 | 774469.5606 | -3382999.92 | -3483999.96 | -3588999.96 | -9681530.2794 | 23.58% | -100% | -100% | -100% | -70.46% | YES | 2390 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPOLE REPLACEMENT AND REINFORCEMENT IN HFTDWildfire Involving SDG&E EquipmentDistribution System Inspection CMP Annual Patrol T1-T2Tier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP Annual Patrol T1-T2 | Tier 2 | 1873601.3242 | 0 | 0 | 0 | 1873601.3242 | 469999.92 | 483999.96 | 498999.96 | 513999.96 | 1966999.8 | 1403601.4042 | -483999.96 | -498999.96 | -513999.96 | -93398.4758 | 298.6% | -100% | -100% | -100% | -4.748% | YES | 2390 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPOLE REPLACEMENT AND REINFORCEMENT IN HFTDWildfire Involving SDG&E EquipmentDistribution System Inspection CMP Annual Patrol T1-T2Tier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection CMP Annual Patrol T1-T2 | Tier 3 | 520444.8074 | 0 | 0 | 0 | 520444.8074 | 396000 | 408000 | 420000 | 432999.96 | 1656999.96 | 124444.8074 | -408000 | -420000 | -432999.96 | -1136555.1526 | 31.43% | -100% | -100% | -100% | -68.59% | YES | 2390 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPOLE REPLACEMENT AND REINFORCEMENT IN HFTDWildfire Involving SDG&E EquipmentDistribution System Inspection HFTD Tier 3 Inspections T1-T2Tier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | POLE REPLACEMENT AND REINFORCEMENT IN HFTD | Wildfire Involving SDG&E Equipment | Distribution System Inspection HFTD Tier 3 Inspections T1-T2 | Tier 3 | 0 | 0 | 0 | 0 | 0 | 2472000 | 2545999.92 | 2622000 | 2700999.96 | 10340999.88 | -2472000 | -2545999.92 | -2622000 | -2700999.96 | -10340999.88 | -100% | -100% | -100% | -100% | -100% | YES | 2390 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPSPP ALL HAZARDS & K2Wildfire Involving SDG&E EquipmentPSPP ALL HAZARDS & K2N/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | PSPP ALL HAZARDS & K2 | Wildfire Involving SDG&E Equipment | PSPP ALL HAZARDS & K2 | N/A | 9801017.3364 | 0 | 0 | 0 | 9801017.3364 | 0 | 0 | 0 | 0 | 0 | 9801017.3364 | 0 | 0 | 0 | 9801017.3364 | 100% | 100% | 100% | 100% | 100% | YES | 238790 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPUBLIC SAFETY POWER SHUTOFF (PSPS) ENGINEERING ENHANCEMENTSWildfire Involving SDG&E EquipmentPSPS SectionalizingTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | PUBLIC SAFETY POWER SHUTOFF (PSPS) ENGINEERING ENHANCEMENTS | Wildfire Involving SDG&E Equipment | PSPS Sectionalizing | Tier 2 | 1087264.1267 | 0 | 0 | 0 | 1087264.1267 | 1965000 | 2023999.92 | 2085000 | 2148000 | 8221999.92 | -877735.8733 | -2023999.92 | -2085000 | -2148000 | -7134735.7933 | -44.67% | -100% | -100% | -100% | -86.78% | YES | 192450 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTPUBLIC SAFETY POWER SHUTOFF (PSPS) ENGINEERING ENHANCEMENTSWildfire Involving SDG&E EquipmentPSPS SectionalizingTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | PUBLIC SAFETY POWER SHUTOFF (PSPS) ENGINEERING ENHANCEMENTS | Wildfire Involving SDG&E Equipment | PSPS Sectionalizing | Tier 3 | 1087264.1267 | 0 | 0 | 0 | 1087264.1267 | 0 | 0 | 0 | 0 | 0 | 1087264.1267 | 0 | 0 | 0 | 1087264.1267 | 100% | 100% | 100% | 100% | 100% | YES | 192450 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTSTRATEGIC UNDERGROUNDINGWildfire Involving SDG&E EquipmentStrategic UndergroundingTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STRATEGIC UNDERGROUNDING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 2 | 49184147.1968 | 0 | 0 | 0 | 49184147.1968 | 38314999.92 | 43881999.96 | 44298999.96 | 44856000 | 171351999.84 | 10869147.2768 | -43881999.96 | -44298999.96 | -44856000 | -122167852.6432 | 28.37% | -100% | -100% | -100% | -71.3% | YES | 192460 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTSTRATEGIC UNDERGROUNDINGWildfire Involving SDG&E EquipmentStrategic UndergroundingTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STRATEGIC UNDERGROUNDING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 3 | 164659972.5495 | 0 | 0 | 0 | 164659972.5495 | 65241000 | 74718000 | 75429000 | 76377000 | 291765000 | 99418972.5495 | -74718000 | -75429000 | -76377000 | -127105027.4505 | 152.4% | -100% | -100% | -100% | -43.56% | YES | 192460 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTTWIN ENGINE MEDIUM LIFT HELICOPTERWildfire Involving SDG&E EquipmentAviation Firefighting ProgramTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | TWIN ENGINE MEDIUM LIFT HELICOPTER | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 3 | 767439.27 | 0 | 0 | 0 | 789930.16 | 0 | 0 | 0 | 0 | 0 | 767439.27 | 0 | 0 | 0 | 789930.16 | 100% | 100% | 100% | 100% | 100% | YES | 212560 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWILDFIRE AND CLIMATE RESILIENCE CENTERWildfire Involving SDG&E EquipmentEmergency Management OperationsN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WILDFIRE AND CLIMATE RESILIENCE CENTER | Wildfire Involving SDG&E Equipment | Emergency Management Operations | N/A | 784335.3742 | 0 | 0 | 0 | 955368.0042 | 0 | 0 | 0 | 0 | 0 | 784335.3742 | 0 | 0 | 0 | 955368.0042 | 100% | 100% | 100% | 100% | 100% | YES | 197800 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWIRELESS FAULT INDICATORSWildfire Involving SDG&E EquipmentWireless Fault IndicatorsTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WIRELESS FAULT INDICATORS | Wildfire Involving SDG&E Equipment | Wireless Fault Indicators | Tier 2 | 1448.6828 | 0 | 0 | 0 | 1448.6828 | 666999.96 | 687000 | 706999.92 | 729000 | 2789999.88 | -665551.2772 | -687000 | -706999.92 | -729000 | -2788551.1972 | -99.78% | -100% | -100% | -100% | -99.95% | YES | 112530 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWIRELESS FAULT INDICATORSWildfire Involving SDG&E EquipmentWireless Fault IndicatorsTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WIRELESS FAULT INDICATORS | Wildfire Involving SDG&E Equipment | Wireless Fault Indicators | Tier 3 | 1448.6828 | 0 | 0 | 0 | 1448.6828 | 666999.96 | 687000 | 708000 | 727999.92 | 2789999.88 | -665551.2772 | -687000 | -708000 | -727999.92 | -2788551.1972 | -99.78% | -100% | -100% | -100% | -99.95% | YES | 112530 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP ADVANCED ANALYTICSWildfire Involving SDG&E EquipmentCentralized Repository for DataN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP ADVANCED ANALYTICS | Wildfire Involving SDG&E Equipment | Centralized Repository for Data | N/A | 4744997.1444 | 0 | 0 | 0 | 4744997.1444 | 5007000 | 5157000 | 5311999.92 | 5470999.92 | 20946999.84 | -262002.8556 | -5157000 | -5311999.92 | -5470999.92 | -16202002.6956 | -5.233% | -100% | -100% | -100% | -77.35% | YES | 218840 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP ASSET AND WORK MANAGEMENT ANALYTICSWildfire Involving SDG&E EquipmentWMP ASSET AND WORK MANAGEMENT ANALYTICSN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP ASSET AND WORK MANAGEMENT ANALYTICS | Wildfire Involving SDG&E Equipment | WMP ASSET AND WORK MANAGEMENT ANALYTICS | N/A | 1139326.7816 | 0 | 0 | 0 | 1139326.7816 | 0 | 0 | 0 | 0 | 0 | 1139326.7816 | 0 | 0 | 0 | 1139326.7816 | 100% | 100% | 100% | 100% | 100% | YES | 248770 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP ASSET INVESTMENT PRIORITIZATIONAsset ManagementAsset ManagementN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP ASSET INVESTMENT PRIORITIZATION | Asset Management | Asset Management | N/A | 677983.1677 | 0 | 0 | 0 | 677983.1677 | 2371999.92 | 2442999.96 | 2515999.92 | 2590999.92 | 9921999.72 | -1694016.7523 | -2442999.96 | -2515999.92 | -2590999.92 | -9244016.5523 | -71.42% | -100% | -100% | -100% | -93.17% | YES | 218770 | YES | SDG&E-CFF-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP CENTRALIZED REPOSITORY FOR DATAWildfire Involving SDG&E EquipmentCentralized Repository for DataN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP CENTRALIZED REPOSITORY FOR DATA | Wildfire Involving SDG&E Equipment | Centralized Repository for Data | N/A | 6086216.0367 | 0 | 0 | 0 | 6086216.0367 | 6712999.92 | 6913999.92 | 7120999.92 | 7335000 | 28082999.76 | -626783.8833 | -6913999.92 | -7120999.92 | -7335000 | -21996783.7233 | -9.337% | -100% | -100% | -100% | -78.33% | YES | 208910 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP CIRCUIT RISK INDEXWildfire Involving SDG&E EquipmentFire Science and Climate Adaptation DepartmentN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP CIRCUIT RISK INDEX | Wildfire Involving SDG&E Equipment | Fire Science and Climate Adaptation Department | N/A | 0 | 0 | 0 | 0 | 0 | 526999.92 | 543000 | 558999.96 | 576000 | 2204999.88 | -526999.92 | -543000 | -558999.96 | -576000 | -2204999.88 | -100% | -100% | -100% | -100% | -100% | YES | 208770 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP MICROGRIDSWildfire Involving SDG&E EquipmentMicrogridsTier 2 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP MICROGRIDS | Wildfire Involving SDG&E Equipment | Microgrids | Tier 2 | 1276576.7271 | 0 | 0 | 0 | 1276576.7271 | 3009000 | 3099000 | 3192000 | 3288000 | 12588000 | -1732423.2729 | -3099000 | -3192000 | -3288000 | -11311423.2729 | -57.57% | -100% | -100% | -100% | -89.86% | YES | 192490 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP MICROGRIDSWildfire Involving SDG&E EquipmentMicrogridsTier 3 | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP MICROGRIDS | Wildfire Involving SDG&E Equipment | Microgrids | Tier 3 | 5819198.1507 | 0 | 0 | 0 | 5819198.1507 | 0 | 0 | 0 | 0 | 0 | 5819198.1507 | 0 | 0 | 0 | 5819198.1507 | 100% | 100% | 100% | 100% | 100% | YES | 192490 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP OPERATION MEGAPHONEWildfire Involving SDG&E EquipmentWMP OPERATION MEGAPHONEN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP OPERATION MEGAPHONE | Wildfire Involving SDG&E Equipment | WMP OPERATION MEGAPHONE | N/A | 366795 | 0 | 0 | 0 | 366795 | 0 | 0 | 0 | 0 | 0 | 366795 | 0 | 0 | 0 | 366795 | 100% | 100% | 100% | 100% | 100% | YES | 238800 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP PRIVATE LTEWildfire Involving SDG&E EquipmentLTE Communication NetworkN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP PRIVATE LTE | Wildfire Involving SDG&E Equipment | LTE Communication Network | N/A | 12745554.7968 | 0 | 0 | 0 | 12745554.7968 | 82902000 | 85389000 | 87951000 | 90589999.92 | 346831999.92 | -70156445.2032 | -85389000 | -87951000 | -90589999.92 | -334086445.1232 | -84.63% | -100% | -100% | -100% | -96.33% | YES | 198730 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP PSPS MOBILE AND ENS ENHANCEMENTSWildfire Involving SDG&E EquipmentCommunication PracticesN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP PSPS MOBILE AND ENS ENHANCEMENTS | Wildfire Involving SDG&E Equipment | Communication Practices | N/A | 6719063.47 | 0 | 0 | 0 | 6719063.47 | 3699000 | 3810000 | 3924000 | 4041999.96 | 15474999.96 | 3020063.4701 | -3810000 | -3924000 | -4041999.96 | -8755936.4899 | 81.65% | -100% | -100% | -100% | -56.58% | YES | 208900 | YES | SDG&E-Risk-1
CapitalWILDFIRE MITIGATION & VEGETATION MANAGEMENTWMP VEGETATION MANAGEMENT SERVICE POWERWWildfire Involving SDG&E EquipmentWMP VEGETATION MANAGEMENT SERVICE POWERWN/A | Capital | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | WMP VEGETATION MANAGEMENT SERVICE POWERW | Wildfire Involving SDG&E Equipment | WMP VEGETATION MANAGEMENT SERVICE POWERW | N/A | 622158.424 | 0 | 0 | 0 | 622158.424 | 0 | 0 | 0 | 0 | 0 | 622158.424 | 0 | 0 | 0 | 622158.424 | 100% | 100% | 100% | 100% | 100% | YES | 238770 | YES | SDG&E-Risk-1
O&MADMINISTRATIVE & GENERALACCOUNTING RESEARCH & BUSINESS CONTROLSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | ACCOUNTING RESEARCH & BUSINESS CONTROLS | Non-RAMP | Non-RAMP | Non-RAMP | 389792.3998 | 0 | 0 | 0 | 482426.3398 | 454999.9992 | 468999.9996 | 483000 | 496999.9992 | 1903999.998 | -65207.5994 | -468999.9996 | -483000 | -496999.9992 | -1421573.6582 | -14.33% | -100% | -100% | -100% | -74.66% | NO | 2100-3555.000 | NO | NR
O&MADMINISTRATIVE & GENERALACCOUNTS PAYABLE (AP)Non-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | ACCOUNTS PAYABLE (AP) | Non-RAMP | Non-RAMP | Non-RAMP | 1102762.3931 | 0 | 0 | 0 | 1309124.4931 | 1119999.9996 | 1153999.9992 | 1188999.9996 | 1224999.9996 | 4687999.998 | -17237.6065 | -1153999.9992 | -1188999.9996 | -1224999.9996 | -3378875.5049 | -1.539% | -100% | -100% | -100% | -72.07% | NO | 2100-3058.000 | NO | NR
O&MADMINISTRATIVE & GENERALAFFILIATE BILLING & COSTING (ABC)Non-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | AFFILIATE BILLING & COSTING (ABC) | Non-RAMP | Non-RAMP | Non-RAMP | 383337.3989 | 0 | 0 | 0 | 466162.5189 | 444000 | 456999.9996 | 471000 | 484999.9992 | 1856999.9988 | -60662.6011 | -456999.9996 | -471000 | -484999.9992 | -1390837.4799 | -13.66% | -100% | -100% | -100% | -74.9% | NO | 2100-0274.000 | NO | NR
O&MADMINISTRATIVE & GENERALASSET & PROJECT ACCOUNTING (A&PA) - PLANT ACCOUNTING AND FINANCIAL & RATEBASE SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | ASSET & PROJECT ACCOUNTING (A&PA) - PLANT ACCOUNTING AND FINANCIAL & RATEBASE SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 2664743.8427 | 0 | 0 | 0 | 3133279.0327 | 2766999.9996 | 2850000 | 2935999.9992 | 3024000 | 11576999.9988 | -102256.1569 | -2850000 | -2935999.9992 | -3024000 | -8443720.9661 | -3.696% | -100% | -100% | -100% | -72.94% | NO | 1AG003.000 | NO | NR
O&MADMINISTRATIVE & GENERALASSISTANT CONTROLLERNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | ASSISTANT CONTROLLER | Non-RAMP | Non-RAMP | Non-RAMP | 347529.9759 | 0 | 0 | 0 | 420212.5959 | 357999.9996 | 369000 | 379999.9992 | 390999.9996 | 1497999.9984 | -10470.0237 | -369000 | -379999.9992 | -390999.9996 | -1077787.4025 | -2.925% | -100% | -100% | -100% | -71.95% | NO | 2100-3050.000 | NO | NR
O&MADMINISTRATIVE & GENERALBILLABLE PROJECT ACCOUNTING & SUNDRY SERVICES (BPA & SS)Non-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | BILLABLE PROJECT ACCOUNTING & SUNDRY SERVICES (BPA & SS) | Non-RAMP | Non-RAMP | Non-RAMP | 792830.5769 | 0 | 0 | 0 | 937718.3769 | 969000 | 997999.9992 | 1027999.9992 | 1059000 | 4053999.9984 | -176169.4231 | -997999.9992 | -1027999.9992 | -1059000 | -3116281.6215 | -18.18% | -100% | -100% | -100% | -76.87% | NO | 1AG004.000 | NO | NR
O&MADMINISTRATIVE & GENERALBUSINESS INNOVATIONS AND FINANCIAL SYSTEMS CLIENT SUPPORTNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | BUSINESS INNOVATIONS AND FINANCIAL SYSTEMS CLIENT SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | 903664.2258 | 0 | 0 | 0 | 1086851.9458 | 816000 | 840000 | 864999.9996 | 891000 | 3411999.9996 | 87664.2258 | -840000 | -864999.9996 | -891000 | -2325148.0538 | 10.74% | -100% | -100% | -100% | -68.15% | NO | 1AG002.000 | NO | NR
O&MADMINISTRATIVE & GENERALCLAIMS PAYMENTS AND RECOVERY COSTSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | CLAIMS PAYMENTS AND RECOVERY COSTS | Non-RAMP | Non-RAMP | Non-RAMP | 3148834.0001 | 0 | 0 | 0 | 3148834.0001 | 4221999.9996 | 4348999.9992 | 4479000 | 4612999.9992 | 17662999.998 | -1073165.9995 | -4348999.9992 | -4479000 | -4612999.9992 | -14514165.9979 | -25.42% | -100% | -100% | -100% | -82.17% | NO | 1AG008.000 | NO | NR
O&MADMINISTRATIVE & GENERALCLAIMSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | CLAIMS | Non-RAMP | Non-RAMP | Non-RAMP | 1479845.1032 | 0 | 0 | 0 | 1906573.7433 | 1419999.9996 | 1462999.9992 | 1506999.9996 | 1551999.9996 | 5941999.998 | 59845.1036 | -1462999.9992 | -1506999.9996 | -1551999.9996 | -4035426.2547 | 4.214% | -100% | -100% | -100% | -67.91% | NO | 1AG007.000 | NO | NR
O&MADMINISTRATIVE & GENERALCOMMUNITY RELATIONS NSSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | COMMUNITY RELATIONS NSS | Non-RAMP | Non-RAMP | Non-RAMP | 678.6 | 0 | 0 | 0 | -59151.75 | 334999.9992 | 345000 | 354999.9996 | 366000 | 1400999.9988 | -334321.3992 | -345000 | -354999.9996 | -366000 | -1460151.7488 | -99.8% | -100% | -100% | -100% | -104.2% | YES | 1AG012.000 | NO | NR
O&MADMINISTRATIVE & GENERALCOMMUNITY RELATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | COMMUNITY RELATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 1137814.0428 | 0 | 0 | 0 | 1415740.3328 | 1255999.9992 | 1293999.9996 | 1332999.9996 | 1372999.9992 | 5255999.9976 | -118185.9564 | -1293999.9996 | -1332999.9996 | -1372999.9992 | -3840259.6648 | -9.41% | -100% | -100% | -100% | -73.06% | YES | 2100-4009.000 | NO | NR
O&MADMINISTRATIVE & GENERALFINANCIAL & BUSINESS PLANNINGNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | FINANCIAL & BUSINESS PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | 6431010.1368 | 0 | 0 | 0 | 7650490.6268 | 7185999.9996 | 7401999.9996 | 7623999.9996 | 7852999.9992 | 30064999.998 | -754989.8628 | -7401999.9996 | -7623999.9996 | -7852999.9992 | -22414509.3712 | -10.51% | -100% | -100% | -100% | -74.55% | YES | 1AG001.000 | NO | NR
O&MADMINISTRATIVE & GENERALFINANCIAL ACCOUNTINGNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | FINANCIAL ACCOUNTING | Non-RAMP | Non-RAMP | Non-RAMP | 1098011.1644 | 0 | 0 | 0 | 1334226.8144 | 1074999.9996 | 1107000 | 1140000 | 1173999.9996 | 4495999.9992 | 23011.1648 | -1107000 | -1140000 | -1173999.9996 | -3161773.1848 | 2.141% | -100% | -100% | -100% | -70.32% | NO | 2100-3051.000 | NO | NR
O&MADMINISTRATIVE & GENERALFINANCIAL PLANNING SYSTEMSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | FINANCIAL PLANNING SYSTEMS | Non-RAMP | Non-RAMP | Non-RAMP | 934715.9485 | 0 | 0 | 0 | 1185143.3385 | 883999.9992 | 910999.9992 | 937999.9992 | 966000 | 3698999.9976 | 50715.9493 | -910999.9992 | -937999.9992 | -966000 | -2513856.6591 | 5.737% | -100% | -100% | -100% | -67.96% | NO | 2100-4080.000 | NO | NR
O&MADMINISTRATIVE & GENERALGENERAL COUNSELNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | GENERAL COUNSEL | Non-RAMP | Non-RAMP | Non-RAMP | 11824991.4905 | 0 | 0 | 0 | 14283531.4105 | 11889000 | 12246000 | 12612999.9996 | 12990999.9996 | 49738999.9992 | -64008.5095 | -12246000 | -12612999.9996 | -12990999.9996 | -35455468.5887 | -0.5384% | -100% | -100% | -100% | -71.28% | NO | 1AG006.000 | NO | NR
O&MADMINISTRATIVE & GENERALGRC & REVENUE REQUIREMENTS - GRC ACCOUNTABILITY REPORTINGNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | GRC & REVENUE REQUIREMENTS - GRC ACCOUNTABILITY REPORTING | Non-RAMP | Non-RAMP | Non-RAMP | 504896.2402 | 0 | 0 | 0 | 586724.4202 | 315000 | 324000 | 333999.9996 | 343999.9992 | 1316999.9988 | 189896.2402 | -324000 | -333999.9996 | -343999.9992 | -730275.5786 | 60.28% | -100% | -100% | -100% | -55.45% | NO | 2100-0006.000 | NO | NR
O&MADMINISTRATIVE & GENERALGRC & REVENUE REQUIREMENTS - GRC CASE MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | GRC & REVENUE REQUIREMENTS - GRC CASE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 760635.8849 | 0 | 0 | 0 | 935972.7749 | 829999.9992 | 855000 | 880999.9992 | 906999.9996 | 3472999.998 | -69364.1142 | -855000 | -880999.9992 | -906999.9996 | -2537027.2231 | -8.357% | -100% | -100% | -100% | -73.05% | NO | 2100-3430.000 | NO | NR
O&MADMINISTRATIVE & GENERALGRC & REVENUE REQUIREMENTSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | GRC & REVENUE REQUIREMENTS | Non-RAMP | Non-RAMP | Non-RAMP | 589103.3048 | 0 | 0 | 0 | 739104.4948 | 819999.9996 | 844999.9992 | 870000 | 895999.9992 | 3430999.998 | -230896.6948 | -844999.9992 | -870000 | -895999.9992 | -2691895.5032 | -28.16% | -100% | -100% | -100% | -78.46% | NO | 2100-3602.000 | NO | NR
O&MADMINISTRATIVE & GENERALPOLICY & PROCEEDINGS - CASE MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | POLICY & PROCEEDINGS - CASE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 3118164.6895 | 0 | 0 | 0 | 3706346.3195 | 3756000 | 3868999.9992 | 3984999.9996 | 4104999.9996 | 15714999.9984 | -637835.3105 | -3868999.9992 | -3984999.9996 | -4104999.9996 | -12008653.6789 | -16.98% | -100% | -100% | -100% | -76.42% | NO | 2100-3428.000 | NO | NR
O&MADMINISTRATIVE & GENERALPOLICY & PROCEEDINGS - TARIFFS AND COMPLIANCE AND STRATEGIC PLANNINGNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | POLICY & PROCEEDINGS - TARIFFS AND COMPLIANCE AND STRATEGIC PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | 1269932.2462 | 0 | 0 | 0 | 1513446.1962 | 2155999.9992 | 2220999.9996 | 2287999.9992 | 2356999.9992 | 9021999.9972 | -886067.753 | -2220999.9996 | -2287999.9992 | -2356999.9992 | -7508553.801 | -41.1% | -100% | -100% | -100% | -83.22% | NO | 1AG010.000 | NO | NR
O&MADMINISTRATIVE & GENERALREGULATORY POLICY & LEGISLATIVE ANALYSISNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | REGULATORY POLICY & LEGISLATIVE ANALYSIS | Non-RAMP | Non-RAMP | Non-RAMP | 108419.6304 | 0 | 0 | 0 | 164544.7003 | 261000 | 268999.9992 | 276999.9996 | 285000 | 1091999.9988 | -152580.3697 | -268999.9992 | -276999.9996 | -285000 | -927455.2985 | -58.46% | -100% | -100% | -100% | -84.93% | NO | 2100-4006.000 | NO | NR
O&MADMINISTRATIVE & GENERALREGULATORY REPORTING AND REGULATORY ACCOUNTSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | REGULATORY REPORTING AND REGULATORY ACCOUNTS | Non-RAMP | Non-RAMP | Non-RAMP | 1352787.1185 | 0 | 0 | 0 | 1647705.2085 | 1773999.9996 | 1827000 | 1881999.9996 | 1938000 | 7420999.9992 | -421212.8811 | -1827000 | -1881999.9996 | -1938000 | -5773294.7907 | -23.74% | -100% | -100% | -100% | -77.8% | NO | 1AG005.000 | NO | NR
O&MADMINISTRATIVE & GENERALSAN FRANCISCO OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | SAN FRANCISCO OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 830514.9733 | 0 | 0 | 0 | 1007509.0233 | 898999.9992 | 925999.9992 | 954000 | 982999.9992 | 3761999.9976 | -68485.0259 | -925999.9992 | -954000 | -982999.9992 | -2754490.9743 | -7.618% | -100% | -100% | -100% | -73.22% | NO | 2100-3991.000 | NO | NR
O&MADMINISTRATIVE & GENERALSVP - STATE GOVERNMENT AFFAIRS & CRONon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | SVP - STATE GOVERNMENT AFFAIRS & CRO | Non-RAMP | Non-RAMP | Non-RAMP | 927486.9277 | 0 | 0 | 0 | 1059847.5477 | 582000 | 598999.9992 | 616999.9992 | 636000 | 2433999.9984 | 345486.9277 | -598999.9992 | -616999.9992 | -636000 | -1374152.4507 | 59.36% | -100% | -100% | -100% | -56.46% | NO | 2100-3162.000 | NO | NR
O&MADMINISTRATIVE & GENERALVP - CONTROLLER & CAONon-RAMPNon-RAMPNon-RAMP | O&M | ADMINISTRATIVE & GENERAL | VP - CONTROLLER & CAO | Non-RAMP | Non-RAMP | Non-RAMP | 1063431.2957 | 0 | 0 | 0 | 1077570.0157 | 475999.9992 | 489999.9996 | 504999.9996 | 519999.9996 | 1990999.998 | 587431.2965 | -489999.9996 | -504999.9996 | -519999.9996 | -913429.9823 | 123.4% | -100% | -100% | -100% | -45.88% | NO | 1AG000.000 | NO | NR
O&MCLEAN ENERGY INNOVATIONSADVANCED CLEAN TECHNOLOGYNon-RAMPNon-RAMPNon-RAMP | O&M | CLEAN ENERGY INNOVATIONS | ADVANCED CLEAN TECHNOLOGY | Non-RAMP | Non-RAMP | Non-RAMP | 1817365.1882 | 0 | 0 | 0 | 2139585.9983 | 1377999.9996 | 1419000 | 1461999.9996 | 1506000 | 5764999.9992 | 439365.1887 | -1419000 | -1461999.9996 | -1506000 | -3625414.0009 | 31.88% | -100% | -100% | -100% | -62.89% | YES | 1DD002.000 | NO | NR
O&MCLEAN ENERGY INNOVATIONSDISTRIBUTED ENERGY RESOURCE ENGINEERINGNon-RAMPNon-RAMPNon-RAMP | O&M | CLEAN ENERGY INNOVATIONS | DISTRIBUTED ENERGY RESOURCE ENGINEERING | Non-RAMP | Non-RAMP | Non-RAMP | 877497.0223 | 0 | 0 | 0 | 1208302.3823 | 1204999.9992 | 1240999.9992 | 1278000 | 1315999.9992 | 5039999.9976 | -327502.9769 | -1240999.9992 | -1278000 | -1315999.9992 | -3831697.6154 | -27.18% | -100% | -100% | -100% | -76.03% | YES | 1DD005.000 | NO | NR
O&MCLEAN ENERGY INNOVATIONSHYDROGEN STRATEGY AND IMPLEMENTATIONNon-RAMPNon-RAMPNon-RAMP | O&M | CLEAN ENERGY INNOVATIONS | HYDROGEN STRATEGY AND IMPLEMENTATION | Non-RAMP | Non-RAMP | Non-RAMP | 652459.3439 | 0 | 0 | 0 | 766960.6739 | 696000 | 717000 | 738999.9996 | 760999.9992 | 2912999.9988 | -43540.6561 | -717000 | -738999.9996 | -760999.9992 | -2146039.3249 | -6.256% | -100% | -100% | -100% | -73.67% | YES | 1DD001.000 | NO | NR
O&MCLEAN ENERGY INNOVATIONSSUSTAINABLE COMMUNITIESNon-RAMPNon-RAMPNon-RAMP | O&M | CLEAN ENERGY INNOVATIONS | SUSTAINABLE COMMUNITIES | Non-RAMP | Non-RAMP | Non-RAMP | 317417 | 0 | 0 | 0 | 426600.28 | 0 | 0 | 0 | 0 | 0 | 317417 | 0 | 0 | 0 | 426600.28 | 100% | 100% | 100% | 100% | 100% | YES | 1DD004.000 | NO | NR
O&MCLEAN TRANSPORTATIONCLEAN TRANSPORTATION - NSSNon-RAMPNon-RAMPNon-RAMP | O&M | CLEAN TRANSPORTATION | CLEAN TRANSPORTATION - NSS | Non-RAMP | Non-RAMP | Non-RAMP | 4271808.5298 | 0 | 0 | 0 | 4762084.6998 | 4921999.9992 | 5070000 | 5221999.9992 | 5379000 | 20592999.9984 | -650191.4694 | -5070000 | -5221999.9992 | -5379000 | -15830915.2986 | -13.21% | -100% | -100% | -100% | -76.88% | YES | 1CT001.000 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSCOMPENSATION - SPOT CASH (GRC USE ONLY)Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | COMPENSATION - SPOT CASH (GRC USE ONLY) | Non-RAMP | Non-RAMP | Non-RAMP | 1675912.4202 | 0 | 0 | 0 | 2907516.7402 | 1705999.9992 | 1756999.9992 | 1809999.9996 | 1863999.9996 | 7136999.9976 | -30087.579 | -1756999.9992 | -1809999.9996 | -1863999.9996 | -4229483.2574 | -1.764% | -100% | -100% | -100% | -59.26% | NO | 1CP000.002 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSCOMPENSATION - VARIABLE PAY (GRC USE ONLY)Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | COMPENSATION - VARIABLE PAY (GRC USE ONLY) | Non-RAMP | Non-RAMP | Non-RAMP | 105030440.807 | 0 | 0 | 0 | 129799602.747 | 34701000 | 35742000 | 36813999.9996 | 37917999.9996 | 145174999.9992 | 70329440.807 | -35742000 | -36813999.9996 | -37917999.9996 | -15375397.2522 | 202.7% | -100% | -100% | -100% | -10.59% | NO | 1CP000.000 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSCOMPENSATION-SPECIAL RECOGNITION AWARDSNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | COMPENSATION-SPECIAL RECOGNITION AWARDS | Non-RAMP | Non-RAMP | Non-RAMP | 505477.94 | 0 | 0 | 0 | 678571.98 | 393999.9996 | 405999.9996 | 417999.9996 | 430999.9992 | 1648999.998 | 111477.9404 | -405999.9996 | -417999.9996 | -430999.9992 | -970428.018 | 28.29% | -100% | -100% | -100% | -58.85% | NO | 1CP000.003 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSHEALTH BENEFITS - EMP ASSISTANCE PROGRAMNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS - EMP ASSISTANCE PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | 732755.35 | 0 | 0 | 0 | 732846.8 | 510000 | 525000 | 540999.9996 | 556999.9992 | 2132999.9988 | 222755.35 | -525000 | -540999.9996 | -556999.9992 | -1400153.1988 | 43.68% | -100% | -100% | -100% | -65.64% | YES | 1PB000.004 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSHEALTH BENEFITS - VISIONNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS - VISION | Non-RAMP | Non-RAMP | Non-RAMP | 264403.58 | 0 | 0 | 0 | 403270.54 | 277999.9992 | 285999.9996 | 294999.9996 | 303999.9996 | 1162999.998 | -13596.4192 | -285999.9996 | -294999.9996 | -303999.9996 | -759729.458 | -4.891% | -100% | -100% | -100% | -65.32% | NO | 1PB000.002 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSHEALTH BENEFITS-DENTALNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS-DENTAL | Non-RAMP | Non-RAMP | Non-RAMP | 3360092.85 | 0 | 0 | 0 | 4201816.12 | 3486999.9996 | 3591999.9996 | 3699999.9996 | 3810999.9996 | 14589999.9984 | -126907.1496 | -3591999.9996 | -3699999.9996 | -3810999.9996 | -10388183.8784 | -3.639% | -100% | -100% | -100% | -71.2% | NO | 1PB000.001 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSHEALTH BENEFITS-MEDICALNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS-MEDICAL | Non-RAMP | Non-RAMP | Non-RAMP | 62528018.4795 | 0 | 0 | 0 | 79454854.6695 | 57592999.9992 | 59320999.9992 | 61101000 | 62934000 | 240948999.9984 | 4935018.4803 | -59320999.9992 | -61101000 | -62934000 | -161494145.3289 | 8.569% | -100% | -100% | -100% | -67.02% | NO | 1PB000.000 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSHEALTH BENEFITS-WELLNESSNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | HEALTH BENEFITS-WELLNESS | Non-RAMP | Non-RAMP | Non-RAMP | 777612.06 | 0 | 0 | 0 | 940311.26 | 1221000 | 1257999.9996 | 1296000 | 1335000 | 5109999.9996 | -443387.94 | -1257999.9996 | -1296000 | -1335000 | -4169688.7396 | -36.31% | -100% | -100% | -100% | -81.6% | NO | 1PB000.003 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSOTHER BENEFITS - BENEFIT ADMIN FEESNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - BENEFIT ADMIN FEES | Non-RAMP | Non-RAMP | Non-RAMP | 1038376.2 | 0 | 0 | 0 | 1196359.11 | 1056000 | 1087999.9992 | 1120999.9992 | 1155000 | 4419999.9984 | -17623.8 | -1087999.9992 | -1120999.9992 | -1155000 | -3223640.8884 | -1.669% | -100% | -100% | -100% | -72.93% | NO | 1PB000.012 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSOTHER BENEFITS - EDUCATIONAL ASSISTANCENon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - EDUCATIONAL ASSISTANCE | Non-RAMP | Non-RAMP | Non-RAMP | 664381.45 | 0 | 0 | 0 | 789834.52 | 771999.9996 | 795000 | 819000 | 843999.9996 | 3229999.9992 | -107618.5496 | -795000 | -819000 | -843999.9996 | -2440165.4792 | -13.94% | -100% | -100% | -100% | -75.55% | NO | 1PB000.013 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSOTHER BENEFITS - EMERGENCY CARENon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - EMERGENCY CARE | Non-RAMP | Non-RAMP | Non-RAMP | 154573 | 0 | 0 | 0 | 154573 | 207999.9996 | 213999.9996 | 219999.9996 | 226999.9992 | 868999.998 | -53426.9996 | -213999.9996 | -219999.9996 | -226999.9992 | -714426.998 | -25.69% | -100% | -100% | -100% | -82.21% | NO | 1PB000.014 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSOTHER BENEFITS - MASS TRANSITNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - MASS TRANSIT | Non-RAMP | Non-RAMP | Non-RAMP | 24775 | 0 | 0 | 0 | 31675 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 535999.998 | -103224.9992 | -132000 | -135999.9996 | -139999.9992 | -504324.998 | -80.64% | -100% | -100% | -100% | -94.09% | NO | 1PB000.015 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSOTHER BENEFITS - RETIREMENT ACTIVITIESNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - RETIREMENT ACTIVITIES | Non-RAMP | Non-RAMP | Non-RAMP | 49238.79 | 0 | 0 | 0 | 58986.29 | 87000 | 90000 | 93000 | 96000 | 366000 | -37761.21 | -90000 | -93000 | -96000 | -307013.71 | -43.4% | -100% | -100% | -100% | -83.88% | NO | 1PB000.016 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSOTHER BENEFITS - SERVICE RECOGNITIONNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | OTHER BENEFITS - SERVICE RECOGNITION | Non-RAMP | Non-RAMP | Non-RAMP | 114004.47 | 0 | 0 | 0 | 146219.67 | 133999.9992 | 138000 | 141999.9996 | 145999.9992 | 559999.998 | -19995.5292 | -138000 | -141999.9996 | -145999.9992 | -413780.328 | -14.92% | -100% | -100% | -100% | -73.89% | NO | 1PB000.017 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSRETIREMENT BENEFITS - RETIREMENT SAVINGS PLANNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | RETIREMENT BENEFITS - RETIREMENT SAVINGS PLAN | Non-RAMP | Non-RAMP | Non-RAMP | 21577904.29 | 0 | 0 | 0 | 26995287.31 | 22953999.9996 | 23643000 | 24351999.9996 | 25083000 | 96031999.9992 | -1376095.7096 | -23643000 | -24351999.9996 | -25083000 | -69036712.6892 | -5.995% | -100% | -100% | -100% | -71.89% | NO | 1PB000.009 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSRETIREMENT BENEFITS - SUPPLEMENTAL PENSIONNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | RETIREMENT BENEFITS - SUPPLEMENTAL PENSION | Non-RAMP | Non-RAMP | Non-RAMP | 2964924 | 0 | 0 | 0 | 3060548 | 972999.9996 | 1002000 | 1032000 | 1062999.9996 | 4069999.9992 | 1991924.0004 | -1002000 | -1032000 | -1062999.9996 | -1009451.9992 | 204.7% | -100% | -100% | -100% | -24.8% | NO | 1PB000.011 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSRETIREMENT BENEFITS-NQ SAVINGS PLANNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | RETIREMENT BENEFITS-NQ SAVINGS PLAN | Non-RAMP | Non-RAMP | Non-RAMP | 251084 | 0 | 0 | 0 | 251084 | 124999.9992 | 129000 | 132999.9996 | 136999.9992 | 523999.998 | 126084.0008 | -129000 | -132999.9996 | -136999.9992 | -272915.998 | 100.9% | -100% | -100% | -100% | -52.08% | NO | 1PB000.010 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSWELFARE BENEFITS - BUSINESS TRAVEL INSNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | WELFARE BENEFITS - BUSINESS TRAVEL INS | Non-RAMP | Non-RAMP | Non-RAMP | 47712.99 | 0 | 0 | 0 | 47712.99 | 27000 | 27999.9996 | 28999.9992 | 30000 | 113999.9988 | 20712.99 | -27999.9996 | -28999.9992 | -30000 | -66287.0088 | 76.71% | -100% | -100% | -100% | -58.15% | NO | 1PB000.007 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSWELFARE BENEFITS-AD&D INSURANCENon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | WELFARE BENEFITS-AD&D INSURANCE | Non-RAMP | Non-RAMP | Non-RAMP | 127028.02 | 0 | 0 | 0 | 159920.31 | 135999.9996 | 139999.9992 | 144000 | 147999.9996 | 567999.9984 | -8971.9796 | -139999.9992 | -144000 | -147999.9996 | -408079.6884 | -6.597% | -100% | -100% | -100% | -71.85% | NO | 1PB000.006 | NO | NR
O&MCORPORATE CENTER - COMPENSATION & BENEFITSWELFARE BENEFITS-LIFE INSURANCENon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - COMPENSATION & BENEFITS | WELFARE BENEFITS-LIFE INSURANCE | Non-RAMP | Non-RAMP | Non-RAMP | 534962.41 | 0 | 0 | 0 | 671388.7 | 567000 | 583999.9992 | 601999.9992 | 619999.9992 | 2372999.9976 | -32037.59 | -583999.9992 | -601999.9992 | -619999.9992 | -1701611.2976 | -5.65% | -100% | -100% | -100% | -71.71% | NO | 1PB000.008 | NO | NR
O&MCORPORATE CENTER - GENERAL ADMINISTRATIONSECC DERPRECIATION ROR - F923.4Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SECC DERPRECIATION ROR - F923.4 | Non-RAMP | Non-RAMP | Non-RAMP | 2148189.9 | 0 | 0 | 0 | 2148189.9 | 1767999.9996 | 1821000 | 1875999.9996 | 1932000 | 7396999.9992 | 380189.9004 | -1821000 | -1875999.9996 | -1932000 | -5248810.0992 | 21.5% | -100% | -100% | -100% | -70.96% | NO | 1SE000.002 | NO | NR
O&MCORPORATE CENTER - GENERAL ADMINISTRATIONSECC OUTSIDE SERVICES EMPLOYED - F923.1Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SECC OUTSIDE SERVICES EMPLOYED - F923.1 | Non-RAMP | Non-RAMP | Non-RAMP | 61691295.5292 | 0 | 0 | 0 | 61691295.5292 | 55797999.9996 | 57471999.9996 | 59196000 | 60972000 | 233437999.9992 | 5893295.5296 | -57471999.9996 | -59196000 | -60972000 | -171746704.47 | 10.56% | -100% | -100% | -100% | -73.57% | YES | 1SE000.001 | NO | NR
O&MCORPORATE CENTER - GENERAL ADMINISTRATIONSECC OUTSIDE SERVICES EMPLOYED - F923.1Physical SecurityPlanning, Awareness, Risk Management, and Incident ManagementPlanning, Awareness, Risk Management, and Incident Management | O&M | CORPORATE CENTER - GENERAL ADMINISTRATION | SECC OUTSIDE SERVICES EMPLOYED - F923.1 | Physical Security | Planning, Awareness, Risk Management, and Incident Management | Planning, Awareness, Risk Management, and Incident Management | 667019.4 | 0 | 0 | 0 | 667019.4 | 493999.9992 | 508999.9992 | 523999.9992 | 540000 | 2066999.9976 | 173019.4008 | -508999.9992 | -523999.9992 | -540000 | -1399980.5976 | 35.02% | -100% | -100% | -100% | -67.73% | YES | 1SE000.001 | NO | SDG&E-CFF-5
O&MCORPORATE CENTER - INSURANCEEXCESS WORKERS COMPENSATION INSURANCE - F925.1Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - INSURANCE | EXCESS WORKERS COMPENSATION INSURANCE - F925.1 | Non-RAMP | Non-RAMP | Non-RAMP | 2903547.78 | 0 | 0 | 0 | 2903547.78 | 3756999.9996 | 3870000 | 3985999.9992 | 4105999.9992 | 15718999.998 | -853452.2196 | -3870000 | -3985999.9992 | -4105999.9992 | -12815452.218 | -22.72% | -100% | -100% | -100% | -81.53% | NO | 1SN000.003 | YES | NR
O&MCORPORATE CENTER - INSURANCERSECC EXCESS LIABILITY INSURANCE PLPD - F925.0Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - INSURANCE | RSECC EXCESS LIABILITY INSURANCE PLPD - F925.0 | Non-RAMP | Non-RAMP | Non-RAMP | 44457522.1392 | 0 | 0 | 0 | 44457522.1392 | 54132000 | 55755999.9996 | 57429000 | 59151999.9996 | 226468999.9992 | -9674477.8608 | -55755999.9996 | -57429000 | -59151999.9996 | -182011477.86 | -17.87% | -100% | -100% | -100% | -80.37% | NO | 1SN000.002 | YES | NR
O&MCORPORATE CENTER - INSURANCERSECC EXCESS LIABILITY INSURANCE PLPD - F925.5 WILDFIRENon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - INSURANCE | RSECC EXCESS LIABILITY INSURANCE PLPD - F925.5 WILDFIRE | Non-RAMP | Non-RAMP | Non-RAMP | 146668408.2192 | 0 | 0 | 0 | 146668408.2192 | 172696999.9992 | 177877999.9992 | 183213999.9996 | 188709999.9996 | 722498999.9976 | -26028591.78 | -177877999.9992 | -183213999.9996 | -188709999.9996 | -575830591.7784 | -15.07% | -100% | -100% | -100% | -79.7% | NO | 1SN000.006 | YES | NR
O&MCORPORATE CENTER - INSURANCERSECC OTHER LIABILITY INSURANCE NON-NUCLEAR - F925.3Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - INSURANCE | RSECC OTHER LIABILITY INSURANCE NON-NUCLEAR - F925.3 | Non-RAMP | Non-RAMP | Non-RAMP | 2575857.39 | 0 | 0 | 0 | 2575857.39 | 3129000 | 3222999.9996 | 3319999.9992 | 3420000 | 13091999.9988 | -553142.61 | -3222999.9996 | -3319999.9992 | -3420000 | -10516142.6088 | -17.68% | -100% | -100% | -100% | -80.32% | NO | 1SN000.004 | YES | NR
O&MCORPORATE CENTER - INSURANCESECC PROPERTY INSURANCE NON-NUCLEAR - 924.0Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - INSURANCE | SECC PROPERTY INSURANCE NON-NUCLEAR - 924.0 | Non-RAMP | Non-RAMP | Non-RAMP | 12525836.3892 | 0 | 0 | 0 | 12525836.3892 | 16860000 | 17365999.9992 | 17886999.9996 | 18423999.9996 | 70536999.9984 | -4334163.6108 | -17365999.9992 | -17886999.9996 | -18423999.9996 | -58011163.6092 | -25.71% | -100% | -100% | -100% | -82.24% | NO | 1SN000.000 | NO | NR
O&MCORPORATE CENTER - INSURANCESECC PROPERTY INSURANCE NUCLEAR - 924.1Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - INSURANCE | SECC PROPERTY INSURANCE NUCLEAR - 924.1 | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 13999.9992 | 13999.9992 | 13999.9992 | 13999.9992 | 55999.9968 | -13999.9992 | -13999.9992 | -13999.9992 | -13999.9992 | -55999.9968 | -100% | -100% | -100% | -100% | -100% | NO | 1SN000.001 | NO | NR
O&MCORPORATE CENTER - INSURANCESECC SURETY BONDS - F925.6Non-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - INSURANCE | SECC SURETY BONDS - F925.6 | Non-RAMP | Non-RAMP | Non-RAMP | 95515.9992 | 0 | 0 | 0 | 95515.9992 | 106999.9992 | 109999.9992 | 112999.9992 | 115999.9992 | 445999.9968 | -11484 | -109999.9992 | -112999.9992 | -115999.9992 | -350483.9976 | -10.73% | -100% | -100% | -100% | -78.58% | NO | 1SN000.007 | NO | NR
O&MCORPORATE CENTER - PENSION & PBOPEMPLOYEE PBOPNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - PENSION & PBOP | EMPLOYEE PBOP | Non-RAMP | Non-RAMP | Non-RAMP | 220462 | 0 | 0 | 0 | 974259 | 346999.9992 | 357000 | 367999.9992 | 378999.9996 | 1450999.998 | -126537.9992 | -357000 | -367999.9992 | -378999.9996 | -476740.998 | -36.47% | -100% | -100% | -100% | -32.86% | NO | 1PN000.001 | YES | NR
O&MCORPORATE CENTER - PENSION & PBOPEMPLOYEE PENSIONNon-RAMPNon-RAMPNon-RAMP | O&M | CORPORATE CENTER - PENSION & PBOP | EMPLOYEE PENSION | Non-RAMP | Non-RAMP | Non-RAMP | 34927302.69 | 0 | 0 | 0 | 44230374.6 | 34927999.9992 | 35976000 | 37054999.9992 | 38166999.9996 | 146125999.998 | -697.3092 | -35976000 | -37054999.9992 | -38166999.9996 | -101895625.398 | -0.001996% | -100% | -100% | -100% | -69.73% | NO | 1PN000.000 | YES | NR
O&MCS - FIELD OPERATIONSCUSTOMER FIELD OPERATIONS SUPERVISIONNon-RAMPNon-RAMPNon-RAMP | O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS SUPERVISION | Non-RAMP | Non-RAMP | Non-RAMP | 1530164.7035 | 0 | 0 | 0 | 1888303.4835 | 1335000 | 1374999.9996 | 1416000 | 1458000 | 5583999.9996 | 195164.7035 | -1374999.9996 | -1416000 | -1458000 | -3695696.5161 | 14.62% | -100% | -100% | -100% | -66.18% | YES | 1FC002.000 | NO | NR
O&MCS - FIELD OPERATIONSCUSTOMER FIELD OPERATIONS SUPPORTIncident Related to the Medium Pressure System (Excluding Dig-in)CSF Quality Assurance (QA) ProgramMeter and Beyond the Meter | O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS SUPPORT | Incident Related to the Medium Pressure System (Excluding Dig-in) | CSF Quality Assurance (QA) Program | Meter and Beyond the Meter | 287065.4952 | 0 | 0 | 0 | 307461.0052 | 282999.9996 | 291000 | 300000 | 309000 | 1182999.9996 | 4065.4956 | -291000 | -300000 | -309000 | -875538.9944 | 1.437% | -100% | -100% | -100% | -74.01% | YES | 1FC004.000 | NO | SDG&E-Risk-9
O&MCS - FIELD OPERATIONSCUSTOMER FIELD OPERATIONS SUPPORTNon-RAMPNon-RAMPNon-RAMP | O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | 4298386.1918 | 0 | 0 | 0 | 5263302.5818 | 3231000 | 3327999.9996 | 3427999.9992 | 3531000 | 13517999.9988 | 1067386.1918 | -3327999.9996 | -3427999.9992 | -3531000 | -8254697.417 | 33.04% | -100% | -100% | -100% | -61.06% | YES | 1FC004.000 | NO | NR
O&MCS - FIELD OPERATIONSCUSTOMER FIELD OPERATIONSIncident Involving an EmployeeEmployee Behavioral Accident Prevention Process ProgramOverall | O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Incident Involving an Employee | Employee Behavioral Accident Prevention Process Program | Overall | 327305.1498 | 0 | 0 | 0 | 421629.0599 | 264999.9996 | 273000 | 280999.9992 | 288999.9996 | 1107999.9984 | 62305.1502 | -273000 | -280999.9992 | -288999.9996 | -686370.9385 | 23.51% | -100% | -100% | -100% | -61.95% | YES | 1FC001.000 | NO | SDG&E-Risk-8
O&MCS - FIELD OPERATIONSCUSTOMER FIELD OPERATIONSIncident Involving an EmployeePersonal Protective EquipmentN/A | O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Incident Involving an Employee | Personal Protective Equipment | N/A | 93983.98 | 0 | 0 | 0 | 140158.81 | 99000 | 102000 | 105000 | 108000 | 414000 | -5016.02 | -102000 | -105000 | -108000 | -273841.19 | -5.067% | -100% | -100% | -100% | -66.15% | YES | 1FC001.000 | NO | SDG&E-Risk-8
O&MCS - FIELD OPERATIONSCUSTOMER FIELD OPERATIONSIncident Related to the Medium Pressure System (Excluding Dig-in)Field and Public SafetyMeter and Beyond the Meter | O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Incident Related to the Medium Pressure System (Excluding Dig-in) | Field and Public Safety | Meter and Beyond the Meter | 12230603.6949 | 0 | 0 | 0 | 14963368.2777 | 11971999.9992 | 12330999.9996 | 12700999.9992 | 13083000 | 50086999.998 | 258603.6957 | -12330999.9996 | -12700999.9992 | -13083000 | -35123631.7203 | 2.16% | -100% | -100% | -100% | -70.13% | YES | 1FC001.000 | NO | SDG&E-Risk-9
O&MCS - FIELD OPERATIONSCUSTOMER FIELD OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | CS - FIELD OPERATIONS | CUSTOMER FIELD OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 7183053.7207 | 0 | 0 | 0 | 8788010.6979 | 5590999.9992 | 5758999.9992 | 5931999.9996 | 6109999.9992 | 23391999.9972 | 1592053.7215 | -5758999.9992 | -5931999.9996 | -6109999.9992 | -14603989.2993 | 28.48% | -100% | -100% | -100% | -62.43% | YES | 1FC001.000 | NO | NR
O&MCS - FIELD OPERATIONSSMART METER OPERATIONSIncident Involving an EmployeeEmployee Behavioral Accident Prevention Process ProgramOverall | O&M | CS - FIELD OPERATIONS | SMART METER OPERATIONS | Incident Involving an Employee | Employee Behavioral Accident Prevention Process Program | Overall | 161657.0452 | 0 | 0 | 0 | 203550.3252 | 126000 | 129999.9996 | 133999.9992 | 138000 | 527999.9988 | 35657.0452 | -129999.9996 | -133999.9992 | -138000 | -324449.6736 | 28.3% | -100% | -100% | -100% | -61.45% | YES | 1FC005.000 | NO | SDG&E-Risk-8
O&MCS - FIELD OPERATIONSSMART METER OPERATIONSIncident Involving an EmployeePersonal Protective EquipmentN/A | O&M | CS - FIELD OPERATIONS | SMART METER OPERATIONS | Incident Involving an Employee | Personal Protective Equipment | N/A | 47912.7 | 0 | 0 | 0 | 72721.15 | 39000 | 39999.9996 | 40999.9992 | 42000 | 161999.9988 | 8912.7 | -39999.9996 | -40999.9992 | -42000 | -89278.8488 | 22.85% | -100% | -100% | -100% | -55.11% | YES | 1FC005.000 | NO | SDG&E-Risk-8
O&MCS - FIELD OPERATIONSSMART METER OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | CS - FIELD OPERATIONS | SMART METER OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 10980440.4517 | 0 | 0 | 0 | 13222460.1117 | 9258000 | 9535999.9992 | 9822000 | 10116999.9996 | 38732999.9988 | 1722440.4517 | -9535999.9992 | -9822000 | -10116999.9996 | -25510539.8871 | 18.6% | -100% | -100% | -100% | -65.86% | YES | 1FC005.000 | NO | NR
O&MCS - FIELD OPERATIONSWORK MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | CS - FIELD OPERATIONS | WORK MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 3411605.7705 | 0 | 0 | 0 | 4250281.9505 | 3699999.9996 | 3810999.9996 | 3924999.9996 | 4042999.9992 | 15478999.998 | -288394.2291 | -3810999.9996 | -3924999.9996 | -4042999.9992 | -11228718.0475 | -7.794% | -100% | -100% | -100% | -72.54% | YES | 1FC003.000 | NO | NR
O&MCS - INFORMATIONCUSTOMER PRICING, LOAD RESEARCH, ANALYSIS, AND FORECASTINGNon-RAMPNon-RAMPNon-RAMP | O&M | CS - INFORMATION | CUSTOMER PRICING, LOAD RESEARCH, ANALYSIS, AND FORECASTING | Non-RAMP | Non-RAMP | Non-RAMP | 4899086.6714 | 0 | 0 | 0 | 6183473.0114 | 4572999.9996 | 4710000 | 4851000 | 4996999.9992 | 19130999.9988 | 326086.6718 | -4710000 | -4851000 | -4996999.9992 | -12947526.9874 | 7.131% | -100% | -100% | -100% | -67.68% | NO | 1IN000.000 | NO | NR
O&MCS - INFORMATIONCUSTOMER PROGRAMS AND BUSINESS SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | CS - INFORMATION | CUSTOMER PROGRAMS AND BUSINESS SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 4817828.634 | 0 | 0 | 0 | 20225403.874 | 6504999.9996 | 6699999.9996 | 6900999.9996 | 7107999.9996 | 27213999.9984 | -1687171.3656 | -6699999.9996 | -6900999.9996 | -7107999.9996 | -6988596.1244 | -25.94% | -100% | -100% | -100% | -25.68% | NO | 1IN002.000 | NO | NR
O&MCS - INFORMATIONMARKETING, COMMUNICATIONS, RESEARCH AND ANALYTICSNon-RAMPNon-RAMPNon-RAMP | O&M | CS - INFORMATION | MARKETING, COMMUNICATIONS, RESEARCH AND ANALYTICS | Non-RAMP | Non-RAMP | Non-RAMP | 6769413.5111 | 0 | 0 | 0 | 8185216.4411 | 9358999.9992 | 9639999.9996 | 9928999.9992 | 10227000 | 39154999.998 | -2589586.4881 | -9639999.9996 | -9928999.9992 | -10227000 | -30969783.5569 | -27.67% | -100% | -100% | -100% | -79.1% | NO | 1IN001.000 | NO | NR
O&MCS - INFORMATIONRAMP - NATURAL GAS APPLIANCE TESTING (NGAT)Incident Related to the Medium Pressure System (Excluding Dig-in)RAMP Natural Gas Appliance Testing (NGAT)Meter and Beyond the Meter | O&M | CS - INFORMATION | RAMP - NATURAL GAS APPLIANCE TESTING (NGAT) | Incident Related to the Medium Pressure System (Excluding Dig-in) | RAMP Natural Gas Appliance Testing (NGAT) | Meter and Beyond the Meter | 301324.32 | 0 | 0 | 0 | 394312.2 | 712999.9992 | 733999.9992 | 756000 | 778999.9992 | 2981999.9976 | -411675.6792 | -733999.9992 | -756000 | -778999.9992 | -2587687.7976 | -57.74% | -100% | -100% | -100% | -86.78% | YES | 1IN002.001 | NO | SDG&E-Risk-9
O&MCS - INFORMATIONRAMP - SAFETY COMMUNICATIONSCustomer and Public Safety – Contact with Electric EquipmentRAMP General Safety CommunicationsOverall | O&M | CS - INFORMATION | RAMP - SAFETY COMMUNICATIONS | Customer and Public Safety – Contact with Electric Equipment | RAMP General Safety Communications | Overall | 395440.9558 | 0 | 0 | 0 | 395440.9558 | 1767000 | 1819999.9992 | 1875000 | 1930999.9992 | 7392999.9984 | -1371559.0442 | -1819999.9992 | -1875000 | -1930999.9992 | -6997559.0426 | -77.62% | -100% | -100% | -100% | -94.65% | YES | 1IN001.001 | NO | SDG&E-Risk-5
O&MCS - INFORMATIONRAMP - SAFETY COMMUNICATIONSIncident Related to the Medium Pressure System (Excluding Dig-in)RAMP Gas Public Safety CommunicationsOverall | O&M | CS - INFORMATION | RAMP - SAFETY COMMUNICATIONS | Incident Related to the Medium Pressure System (Excluding Dig-in) | RAMP Gas Public Safety Communications | Overall | 424363.9558 | 0 | 0 | 0 | 424363.9558 | 2791999.9992 | 2875999.9992 | 2961999.9996 | 3051000 | 11680999.998 | -2367636.0434 | -2875999.9992 | -2961999.9996 | -3051000 | -11256636.0422 | -84.8% | -100% | -100% | -100% | -96.37% | YES | 1IN001.001 | NO | SDG&E-Risk-9
O&MCS - OFFICE OPERATIONSBILLINGNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | BILLING | Non-RAMP | Non-RAMP | Non-RAMP | 7405916.5407 | 0 | 0 | 0 | 9033295.5107 | 7455999.9996 | 7680000 | 7909999.9992 | 8146999.9992 | 31192999.998 | -50083.4589 | -7680000 | -7909999.9992 | -8146999.9992 | -22159704.4873 | -0.6717% | -100% | -100% | -100% | -71.04% | NO | 1OO000.000 | NO | NR
O&MCS - OFFICE OPERATIONSBRANCH OFFICESNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | BRANCH OFFICES | Non-RAMP | Non-RAMP | Non-RAMP | 1130284.6724 | 0 | 0 | 0 | 1219519.2124 | 0 | 0 | 0 | 0 | 0 | 1130284.6724 | 0 | 0 | 0 | 1219519.2124 | 100% | 100% | 100% | 100% | 100% | NO | 1OO003.000 | NO | NR
O&MCS - OFFICE OPERATIONSCCC OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | CCC OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 14622324.538 | 0 | 0 | 0 | 18043740.148 | 12336000 | 12705999.9996 | 13086999.9996 | 13479999.9996 | 51608999.9988 | 2286324.538 | -12705999.9996 | -13086999.9996 | -13479999.9996 | -33565259.8508 | 18.53% | -100% | -100% | -100% | -65.04% | YES | 1OO004.000 | NO | NR
O&MCS - OFFICE OPERATIONSCCC SUPPORTNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | CCC SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | 4111885.2245 | 0 | 0 | 0 | 4982810.6145 | 4554999.9996 | 4692000 | 4833000 | 4977999.9996 | 19057999.9992 | -443114.7751 | -4692000 | -4833000 | -4977999.9996 | -14075189.3847 | -9.728% | -100% | -100% | -100% | -73.85% | YES | 1OO005.000 | NO | NR
O&MCS - OFFICE OPERATIONSCREDIT & COLLECTIONSNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | CREDIT & COLLECTIONS | Non-RAMP | Non-RAMP | Non-RAMP | 2087809.8532 | 0 | 0 | 0 | 2493152.9032 | 2367999.9996 | 2439000 | 2511999.9996 | 2586999.9996 | 9905999.9988 | -280190.1464 | -2439000 | -2511999.9996 | -2586999.9996 | -7412847.0956 | -11.83% | -100% | -100% | -100% | -74.83% | NO | 1OO001.000 | NO | NR
O&MCS - OFFICE OPERATIONSCUSTOMER OPERATIONS COMPLIANCE AND STRATEGYNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | CUSTOMER OPERATIONS COMPLIANCE AND STRATEGY | Non-RAMP | Non-RAMP | Non-RAMP | 2962597.1221 | 0 | 0 | 0 | 3715846.6321 | 5244000 | 5400999.9996 | 5562999.9996 | 5730000 | 21937999.9992 | -2281402.8779 | -5400999.9996 | -5562999.9996 | -5730000 | -18222153.3671 | -43.51% | -100% | -100% | -100% | -83.06% | NO | 1OO006.000 | NO | NR
O&MCS - OFFICE OPERATIONSPOSTAGENon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | POSTAGE | Non-RAMP | Non-RAMP | Non-RAMP | 5480067.02 | 0 | 0 | 0 | 7006839.97 | 3825999.9996 | 3940999.9992 | 4059000 | 4180999.9992 | 16006999.998 | 1654067.0204 | -3940999.9992 | -4059000 | -4180999.9992 | -9000160.028 | 43.23% | -100% | -100% | -100% | -56.23% | NO | 1OO002.001 | NO | NR
O&MCS - OFFICE OPERATIONSREMITTANCE PROCESSINGNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | REMITTANCE PROCESSING | Non-RAMP | Non-RAMP | Non-RAMP | 1299134.5213 | 0 | 0 | 0 | 1600462.1313 | 769999.9992 | 792999.9996 | 816999.9996 | 841999.9992 | 3221999.9976 | 529134.5221 | -792999.9996 | -816999.9996 | -841999.9992 | -1621537.8663 | 68.72% | -100% | -100% | -100% | -50.33% | NO | 1OO002.000 | NO | NR
O&MCS - OFFICE OPERATIONSSAFETY - METER REVENUE PROTECTIONNon-RAMPNon-RAMPNon-RAMP | O&M | CS - OFFICE OPERATIONS | SAFETY - METER REVENUE PROTECTION | Non-RAMP | Non-RAMP | Non-RAMP | 336199.7859 | 0 | 0 | 0 | 421748.1359 | 381000 | 391999.9992 | 403999.9992 | 415999.9992 | 1592999.9976 | -44800.2141 | -391999.9992 | -403999.9992 | -415999.9992 | -1171251.8617 | -11.76% | -100% | -100% | -100% | -73.52% | YES | 1OO001.001 | NO | NR
O&MCYBERSECURITYNON-SHARED CYBERSECURITYCybersecurityAll MitigationsOverall | O&M | CYBERSECURITY | NON-SHARED CYBERSECURITY | Cybersecurity | All Mitigations | Overall | 11922.27 | 0 | 0 | 0 | 13542.55 | 21999.9996 | 22999.9992 | 24000 | 24999.9996 | 93999.9984 | -10077.7296 | -22999.9992 | -24000 | -24999.9996 | -80457.4484 | -45.81% | -100% | -100% | -100% | -85.59% | YES | 1CS001.000 | NO | SDG&E-Risk-6
O&MCYBERSECURITYSHARED CYBERSECURITYCybersecurityAll MitigationsOverall | O&M | CYBERSECURITY | SHARED CYBERSECURITY | Cybersecurity | All Mitigations | Overall | 13783875.3869 | 0 | 0 | 0 | 15466760.6469 | 18144000 | 18687999.9996 | 19248999.9996 | 19825999.9992 | 75906999.9984 | -4360124.6131 | -18687999.9996 | -19248999.9996 | -19825999.9992 | -60440239.3515 | -24.03% | -100% | -100% | -100% | -79.62% | YES | 2100-3101.000 | NO | SDG&E-Risk-6
O&MELECTRIC DISTRIBUTIONCOMPLIANCE MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | COMPLIANCE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 3343523.979 | 0 | 0 | 0 | 4319063.839 | 5487000 | 5652000 | 5821999.9992 | 5997000 | 22957999.9992 | -2143476.021 | -5652000 | -5821999.9992 | -5997000 | -18638936.1602 | -39.06% | -100% | -100% | -100% | -81.19% | YES | 1ED015.000 | NO | NR
O&MELECTRIC DISTRIBUTIONCONSTRUCTION MANAGEMENTIncident Involving an EmployeeMandatory Employee Health and Safety Training Programs and Standardized PoliciesN/A | O&M | ELECTRIC DISTRIBUTION | CONSTRUCTION MANAGEMENT | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | N/A | 5109.7759 | 0 | 0 | 0 | 12282.785 | 9000 | 9000 | 9000 | 9000 | 36000 | -3890.2241 | -9000 | -9000 | -9000 | -23717.215 | -43.22% | -100% | -100% | -100% | -65.88% | YES | 1ED002.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONCONSTRUCTION MANAGEMENTIncident Involving an EmployeePersonal Protective EquipmentN/A | O&M | ELECTRIC DISTRIBUTION | CONSTRUCTION MANAGEMENT | Incident Involving an Employee | Personal Protective Equipment | N/A | 5109.7759 | 0 | 0 | 0 | 12282.785 | 9000 | 9000 | 9000 | 9000 | 36000 | -3890.2241 | -9000 | -9000 | -9000 | -23717.215 | -43.22% | -100% | -100% | -100% | -65.88% | YES | 1ED002.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONCONSTRUCTION MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | CONSTRUCTION MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 2620816.884 | 0 | 0 | 0 | 3323771.7758 | 4593000 | 4731000 | 4872999.9996 | 5019999.9996 | 19216999.9992 | -1972183.116 | -4731000 | -4872999.9996 | -5019999.9996 | -15893228.2234 | -42.94% | -100% | -100% | -100% | -82.7% | YES | 1ED002.000 | NO | NR
O&MELECTRIC DISTRIBUTIONDISTRIBUTION DESIGN AND PROJECT MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | DISTRIBUTION DESIGN AND PROJECT MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 1127552.1984 | 0 | 0 | 0 | 1380423.5184 | 1485999.9996 | 1530999.9996 | 1576999.9992 | 1623999.9996 | 6217999.998 | -358447.8012 | -1530999.9996 | -1576999.9992 | -1623999.9996 | -4837576.4796 | -24.12% | -100% | -100% | -100% | -77.8% | YES | 1ED007.000 | NO | NR
O&MELECTRIC DISTRIBUTIONELECTRIC ENGINEERING (TNG)Non-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING (TNG) | Non-RAMP | Non-RAMP | Non-RAMP | 26437.1685 | 0 | 0 | 0 | 37193.4985 | 75999.9996 | 78000 | 79999.9992 | 81999.9996 | 315999.9984 | -49562.8311 | -78000 | -79999.9992 | -81999.9996 | -278806.4999 | -65.21% | -100% | -100% | -100% | -88.23% | YES | 1ED012.001 | NO | NR
O&MELECTRIC DISTRIBUTIONELECTRIC ENGINEERINGAsset ManagementAIM (Gov, Strat, AIP)N/A | O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING | Asset Management | AIM (Gov, Strat, AIP) | N/A | 16671.2662 | 0 | 0 | 0 | 19277.0289 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | 19999.9968 | 11671.267 | -4999.9992 | -4999.9992 | -4999.9992 | -722.9679 | 233.4% | -100% | -100% | -100% | -3.615% | YES | 1ED012.000 | NO | SDG&E-CFF-1
O&MELECTRIC DISTRIBUTIONELECTRIC ENGINEERINGIncident Involving an EmployeePersonal Protective EquipmentN/A | O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING | Incident Involving an Employee | Personal Protective Equipment | N/A | 4998.7834 | 0 | 0 | 0 | 7604.5461 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 97999.998 | -18001.2158 | -24000 | -24999.9996 | -25999.9992 | -90395.4519 | -78.27% | -100% | -100% | -100% | -92.24% | YES | 1ED012.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONELECTRIC ENGINEERINGNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | ELECTRIC ENGINEERING | Non-RAMP | Non-RAMP | Non-RAMP | 2009789.3506 | 0 | 0 | 0 | 2265154.0952 | 2388999.9996 | 2460999.9996 | 2535000 | 2610999.9996 | 9995999.9988 | -379210.649 | -2460999.9996 | -2535000 | -2610999.9996 | -7730845.9036 | -15.87% | -100% | -100% | -100% | -77.34% | YES | 1ED012.000 | NO | NR
O&MELECTRIC DISTRIBUTIONELECTRIC REGIONAL OPERATIONSIncident Involving an EmployeeEmployee Accidental Behavior ProgramNone | O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Incident Involving an Employee | Employee Accidental Behavior Program | None | 62339.4212 | 0 | 0 | 0 | 165224.7366 | 79999.9992 | 81999.9996 | 84000 | 87000 | 332999.9988 | -17660.578 | -81999.9996 | -84000 | -87000 | -167775.2622 | -22.08% | -100% | -100% | -100% | -50.38% | YES | 1ED008.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONELECTRIC REGIONAL OPERATIONSIncident Involving an EmployeeMandatory Employee Health and Safety Training Programs and Standardized PoliciesNone | O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | None | 144886.8493 | 0 | 0 | 0 | 247772.1647 | 186999.9996 | 192999.9996 | 198999.9996 | 204999.9996 | 783999.9984 | -42113.1503 | -192999.9996 | -198999.9996 | -204999.9996 | -536227.8337 | -22.52% | -100% | -100% | -100% | -68.4% | YES | 1ED008.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONELECTRIC REGIONAL OPERATIONSIncident Involving an EmployeePersonal Protective EquipmentNone | O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Incident Involving an Employee | Personal Protective Equipment | None | 467174.0998 | 0 | 0 | 0 | 570059.4152 | 601999.9992 | 619999.9992 | 639000 | 657999.9996 | 2518999.998 | -134825.8994 | -619999.9992 | -639000 | -657999.9996 | -1948940.5828 | -22.4% | -100% | -100% | -100% | -77.37% | YES | 1ED008.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONELECTRIC REGIONAL OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | ELECTRIC REGIONAL OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 35125453.746 | 0 | 0 | 0 | 45105329.3398 | 40531999.9992 | 41748000 | 42999999.9996 | 44289999.9996 | 169569999.9984 | -5406546.2532 | -41748000 | -42999999.9996 | -44289999.9996 | -124464670.6586 | -13.34% | -100% | -100% | -100% | -73.4% | YES | 1ED008.000 | NO | NR
O&MELECTRIC DISTRIBUTIONELECTRIC SYSTEM OPERATIONS (TNG - GISS)Records ManagementGIS Jobs ProcessedN/A | O&M | ELECTRIC DISTRIBUTION | ELECTRIC SYSTEM OPERATIONS (TNG - GISS) | Records Management | GIS Jobs Processed | N/A | 2186867.1926 | 0 | 0 | 0 | 2587465.3726 | 1039999.9992 | 1071000 | 1102999.9992 | 1135999.9992 | 4349999.9976 | 1146867.1934 | -1071000 | -1102999.9992 | -1135999.9992 | -1762534.625 | 110.3% | -100% | -100% | -100% | -40.52% | YES | 1ED003.001 | NO | SDG&E-CFF-6
O&MELECTRIC DISTRIBUTIONELECTRIC SYSTEM OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | ELECTRIC SYSTEM OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 41361768.9958 | 0 | 0 | 0 | 50978634.2758 | 34092000 | 35115000 | 36168000 | 37252999.9992 | 142627999.9992 | 7269768.9958 | -35115000 | -36168000 | -37252999.9992 | -91649365.7234 | 21.32% | -100% | -100% | -100% | -64.26% | YES | 1ED003.000 | NO | NR
O&MELECTRIC DISTRIBUTIONET&D: OPERATIONS SERVICESIncident Involving an EmployeeOSHA Voluntary Protection ProgramN/A | O&M | ELECTRIC DISTRIBUTION | ET&D: OPERATIONS SERVICES | Incident Involving an Employee | OSHA Voluntary Protection Program | N/A | 621366.0763 | 0 | 0 | 0 | 656088.0865 | 78000 | 79999.9992 | 81999.9996 | 84000 | 323999.9988 | 543366.0763 | -79999.9992 | -81999.9996 | -84000 | 332088.0877 | 696.6% | -100% | -100% | -100% | 102.5% | YES | 1ED005.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONET&D: OPERATIONS SERVICESIncident Involving an EmployeePersonal Protective EquipmentNone | O&M | ELECTRIC DISTRIBUTION | ET&D: OPERATIONS SERVICES | Incident Involving an Employee | Personal Protective Equipment | None | 1286021.3022 | 0 | 0 | 0 | 1320743.3124 | 823999.9992 | 849000 | 873999.9996 | 900000 | 3446999.9988 | 462021.303 | -849000 | -873999.9996 | -900000 | -2126256.6864 | 56.07% | -100% | -100% | -100% | -61.68% | YES | 1ED005.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONET&D: OPERATIONS SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | ET&D: OPERATIONS SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 2430129.1151 | 0 | 0 | 0 | 3518085.4347 | 1558999.9992 | 1605999.9996 | 1654999.9992 | 1704999.9996 | 6524999.9976 | 871129.1159 | -1605999.9996 | -1654999.9992 | -1704999.9996 | -3006914.5629 | 55.88% | -100% | -100% | -100% | -46.08% | YES | 1ED005.000 | NO | NR
O&MELECTRIC DISTRIBUTIONET&D: SUBSTATION C&O (RELAY & SCADA)Incident Involving an EmployeePersonal Protective EquipmentNone | O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O (RELAY & SCADA) | Incident Involving an Employee | Personal Protective Equipment | None | 41066.3051 | 0 | 0 | 0 | 49564.1106 | 30999.9996 | 31999.9992 | 33000 | 33999.9996 | 129999.9984 | 10066.3055 | -31999.9992 | -33000 | -33999.9996 | -80435.8878 | 32.47% | -100% | -100% | -100% | -61.87% | YES | 1ED006.002 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONET&D: SUBSTATION C&O (RELAY & SCADA)Non-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O (RELAY & SCADA) | Non-RAMP | Non-RAMP | Non-RAMP | 3874932.692 | 0 | 0 | 0 | 4716215.4365 | 4161000 | 4285999.9992 | 4414999.9992 | 4546999.9992 | 17408999.9976 | -286067.308 | -4285999.9992 | -4414999.9992 | -4546999.9992 | -12692784.5611 | -6.875% | -100% | -100% | -100% | -72.91% | YES | 1ED006.002 | NO | NR
O&MELECTRIC DISTRIBUTIONET&D: SUBSTATION C&OElectric Infrastructure IntegritySubstation Inspections & Repairs GO-174Inspections & Repairs | O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Electric Infrastructure Integrity | Substation Inspections & Repairs GO-174 | Inspections & Repairs | 1843039.1867 | 0 | 0 | 0 | 2139725.2691 | 1350999.9996 | 1392000 | 1432999.9992 | 1476000 | 5651999.9988 | 492039.1871 | -1392000 | -1432999.9992 | -1476000 | -3512274.7297 | 36.42% | -100% | -100% | -100% | -62.14% | YES | 1ED006.000 | NO | SDG&E-Risk-2
O&MELECTRIC DISTRIBUTIONET&D: SUBSTATION C&OIncident Involving an EmployeeOSHA Voluntary Protection ProgramN/A | O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Incident Involving an Employee | OSHA Voluntary Protection Program | N/A | 24900.1998 | 0 | 0 | 0 | 74347.8802 | 163999.9992 | 168999.9996 | 174000 | 178999.9992 | 685999.998 | -139099.7994 | -168999.9996 | -174000 | -178999.9992 | -611652.1178 | -84.82% | -100% | -100% | -100% | -89.16% | YES | 1ED006.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONET&D: SUBSTATION C&OIncident Involving an EmployeePersonal Protective EquipmentNone | O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Incident Involving an Employee | Personal Protective Equipment | None | 256316.2272 | 0 | 0 | 0 | 2382566.4844 | 162000 | 166999.9992 | 171999.9996 | 177000 | 677999.9988 | 94316.2272 | -166999.9992 | -171999.9996 | -177000 | 1704566.4856 | 58.22% | -100% | -100% | -100% | 251.4% | YES | 1ED006.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONET&D: SUBSTATION C&ONon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | ET&D: SUBSTATION C&O | Non-RAMP | Non-RAMP | Non-RAMP | 8417864.8556 | 0 | 0 | 0 | 8417864.8556 | 4903999.9992 | 5049999.9996 | 5202000 | 5358000 | 20513999.9988 | 3513864.8564 | -5049999.9996 | -5202000 | -5358000 | -12096135.1432 | 71.65% | -100% | -100% | -100% | -58.97% | YES | 1ED006.000 | NO | NR
O&MELECTRIC DISTRIBUTIONOFFICERNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | OFFICER | Non-RAMP | Non-RAMP | Non-RAMP | 987280.686 | 0 | 0 | 0 | 1164432.136 | 1450999.9992 | 1494999.9996 | 1539999.9996 | 1585999.9992 | 6071999.9976 | -463719.3132 | -1494999.9996 | -1539999.9996 | -1585999.9992 | -4907567.8616 | -31.96% | -100% | -100% | -100% | -80.82% | YES | 1ED016.000 | NO | NR
O&MELECTRIC DISTRIBUTIONPORTFOLIO & PROJECT MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | PORTFOLIO & PROJECT MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 455992.4673 | 0 | 0 | 0 | 665295.2173 | 582000 | 598999.9992 | 616999.9992 | 636000 | 2433999.9984 | -126007.5327 | -598999.9992 | -616999.9992 | -636000 | -1768704.7811 | -21.65% | -100% | -100% | -100% | -72.67% | YES | 1ED014.000 | NO | NR
O&MELECTRIC DISTRIBUTIONREGIONAL PUBLIC AFFAIRSNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | REGIONAL PUBLIC AFFAIRS | Non-RAMP | Non-RAMP | Non-RAMP | 1639241.65 | 0 | 0 | 0 | 1946526.26 | 1566000 | 1612999.9992 | 1660999.9992 | 1710999.9996 | 6550999.998 | 73241.65 | -1612999.9992 | -1660999.9992 | -1710999.9996 | -4604473.738 | 4.677% | -100% | -100% | -100% | -70.29% | YES | 1ED022.000 | NO | NR
O&MELECTRIC DISTRIBUTIONRELIABILITY AND CAPACITYNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | RELIABILITY AND CAPACITY | Non-RAMP | Non-RAMP | Non-RAMP | 2281598.8853 | 0 | 0 | 0 | 2832680.6953 | 2785999.9992 | 2869999.9992 | 2955999.9996 | 3045000 | 11656999.998 | -504401.1139 | -2869999.9992 | -2955999.9996 | -3045000 | -8824319.3027 | -18.1% | -100% | -100% | -100% | -75.7% | YES | 1ED001.000 | NO | NR
O&MELECTRIC DISTRIBUTIONSERVICE ORDER TEAM (SOT)Non-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | SERVICE ORDER TEAM (SOT) | Non-RAMP | Non-RAMP | Non-RAMP | 7936206.3582 | 0 | 0 | 0 | 9484410.1082 | 4635000 | 4773999.9996 | 4917000 | 5064999.9996 | 19390999.9992 | 3301206.3583 | -4773999.9996 | -4917000 | -5064999.9996 | -9906589.8909 | 71.22% | -100% | -100% | -100% | -51.09% | YES | 1ED010.000 | NO | NR
O&MELECTRIC DISTRIBUTIONSKILLS & COMPLIANCE TRAINING (TNG)Incident Involving an EmployeePersonal Protective EquipmentNone | O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING (TNG) | Incident Involving an Employee | Personal Protective Equipment | None | 35131.0315 | 0 | 0 | 0 | 42157.8876 | 121999.9992 | 126000 | 129999.9996 | 133999.9992 | 511999.998 | -86868.9677 | -126000 | -129999.9996 | -133999.9992 | -469842.1103 | -71.2% | -100% | -100% | -100% | -91.77% | YES | 1ED009.001 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONSKILLS & COMPLIANCE TRAINING (TNG)Non-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING (TNG) | Non-RAMP | Non-RAMP | Non-RAMP | 284241.9829 | 0 | 0 | 0 | 341095.6368 | 1273999.9992 | 1311999.9996 | 1350999.9996 | 1390999.9992 | 5327999.9976 | -989758.0163 | -1311999.9996 | -1350999.9996 | -1390999.9992 | -4986904.3608 | -77.69% | -100% | -100% | -100% | -93.6% | YES | 1ED009.001 | NO | NR
O&MELECTRIC DISTRIBUTIONSKILLS & COMPLIANCE TRAININGIncident Involving an EmployeeIndustrial Athletic TrainerN/A | O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING | Incident Involving an Employee | Industrial Athletic Trainer | N/A | 153319.5 | 0 | 0 | 0 | 153319.5 | 27000 | 27999.9996 | 28999.9992 | 30000 | 113999.9988 | 126319.5 | -27999.9996 | -28999.9992 | -30000 | 39319.5012 | 467.8% | -100% | -100% | -100% | 34.49% | YES | 1ED009.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONSKILLS & COMPLIANCE TRAININGIncident Involving an EmployeePersonal Protective EquipmentN/A | O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING | Incident Involving an Employee | Personal Protective Equipment | N/A | 52367.3033 | 0 | 0 | 0 | 62826.5245 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 535999.998 | -75632.6959 | -132000 | -135999.9996 | -139999.9992 | -473173.4735 | -59.09% | -100% | -100% | -100% | -88.28% | YES | 1ED009.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONSKILLS & COMPLIANCE TRAININGNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | SKILLS & COMPLIANCE TRAINING | Non-RAMP | Non-RAMP | Non-RAMP | 1103495.7801 | 0 | 0 | 0 | 1354517.0889 | 1693999.9992 | 1743999.9996 | 1795999.9992 | 1849999.9992 | 7083999.9972 | -590504.2191 | -1743999.9996 | -1795999.9992 | -1849999.9992 | -5729482.9083 | -34.86% | -100% | -100% | -100% | -80.88% | YES | 1ED009.000 | NO | NR
O&MELECTRIC DISTRIBUTIONTROUBLESHOOTINGIncident Involving an EmployeeMandatory Employee Health and Safety Training Programs and Standardized PoliciesNone | O&M | ELECTRIC DISTRIBUTION | TROUBLESHOOTING | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | None | 36252.2885 | 0 | 0 | 0 | 65255.3461 | 30000 | 30999.9996 | 31999.9992 | 33000 | 125999.9988 | 6252.2885 | -30999.9996 | -31999.9992 | -33000 | -60744.6528 | 20.84% | -100% | -100% | -100% | -48.21% | YES | 1ED013.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONTROUBLESHOOTINGIncident Involving an EmployeePersonal Protective EquipmentNone | O&M | ELECTRIC DISTRIBUTION | TROUBLESHOOTING | Incident Involving an Employee | Personal Protective Equipment | None | 44308.6033 | 0 | 0 | 0 | 73311.6609 | 36999.9996 | 37999.9992 | 39000 | 39999.9996 | 153999.9984 | 7308.6037 | -37999.9992 | -39000 | -39999.9996 | -80688.3375 | 19.75% | -100% | -100% | -100% | -52.4% | YES | 1ED013.000 | NO | SDG&E-Risk-8
O&MELECTRIC DISTRIBUTIONTROUBLESHOOTINGNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC DISTRIBUTION | TROUBLESHOOTING | Non-RAMP | Non-RAMP | Non-RAMP | 12854531.1184 | 0 | 0 | 0 | 15696830.7632 | 10807999.9992 | 11131999.9992 | 11466000 | 11809999.9992 | 45215999.9976 | 2046531.1192 | -11131999.9992 | -11466000 | -11809999.9992 | -29519169.2344 | 18.94% | -100% | -100% | -100% | -65.28% | YES | 1ED013.000 | NO | NR
O&MELECTRIC GENERATIONGENERATION - PLANT - ADMINNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC GENERATION | GENERATION - PLANT - ADMIN | Non-RAMP | Non-RAMP | Non-RAMP | 296993.7081 | 0 | 0 | 0 | 457286.0481 | 292999.9992 | 301999.9992 | 310999.9992 | 319999.9992 | 1225999.9968 | 3993.7089 | -301999.9992 | -310999.9992 | -319999.9992 | -768713.9487 | 1.363% | -100% | -100% | -100% | -62.7% | YES | 1EG001.000 | NO | NR
O&MELECTRIC GENERATIONGENERATION DISTRIBUTED ENERGY FACILITIESNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC GENERATION | GENERATION DISTRIBUTED ENERGY FACILITIES | Non-RAMP | Non-RAMP | Non-RAMP | 1433003.0709 | 0 | 0 | 0 | 1803525.6109 | 1569000 | 1615999.9992 | 1663999.9992 | 1713999.9996 | 6562999.998 | -135996.9291 | -1615999.9992 | -1663999.9992 | -1713999.9996 | -4759474.3871 | -8.668% | -100% | -100% | -100% | -72.52% | YES | 1EG004.000 | NO | NR
O&MELECTRIC GENERATIONGENERATION PLANT CUYAMACA PEAKNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC GENERATION | GENERATION PLANT CUYAMACA PEAK | Non-RAMP | Non-RAMP | Non-RAMP | 1321663.5596 | 0 | 0 | 0 | 1488289.6596 | 1077999.9996 | 1110000 | 1143000 | 1176999.9996 | 4507999.9992 | 243663.56 | -1110000 | -1143000 | -1176999.9996 | -3019710.3396 | 22.6% | -100% | -100% | -100% | -66.99% | YES | 1EG007.000 | NO | NR
O&MELECTRIC GENERATIONGENERATION PLANT DESERT STARNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC GENERATION | GENERATION PLANT DESERT STAR | Non-RAMP | Non-RAMP | Non-RAMP | 15597905.01 | 0 | 0 | 0 | 21189482.91 | 15979999.9992 | 16458999.9996 | 16953000 | 17461999.9992 | 66853999.998 | -382094.9892 | -16458999.9996 | -16953000 | -17461999.9992 | -45664517.088 | -2.391% | -100% | -100% | -100% | -68.3% | YES | 1EG006.000 | NO | NR
O&MELECTRIC GENERATIONGENERATION PLANT MIRAMARNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC GENERATION | GENERATION PLANT MIRAMAR | Non-RAMP | Non-RAMP | Non-RAMP | 1416401.2311 | 0 | 0 | 0 | 1552543.2311 | 2175000 | 2239999.9992 | 2307000 | 2376000 | 9097999.9992 | -758598.7689 | -2239999.9992 | -2307000 | -2376000 | -7545456.7681 | -34.88% | -100% | -100% | -100% | -82.94% | YES | 1EG002.000 | NO | NR
O&MELECTRIC GENERATIONGENERATION PLANT PALOMARNon-RAMPNon-RAMPNon-RAMP | O&M | ELECTRIC GENERATION | GENERATION PLANT PALOMAR | Non-RAMP | Non-RAMP | Non-RAMP | 20128612.7439 | 0 | 0 | 0 | 28299679.9639 | 21927999.9996 | 22585999.9992 | 23263999.9992 | 23961999.9996 | 91739999.9976 | -1799387.2557 | -22585999.9992 | -23263999.9992 | -23961999.9996 | -63440320.0337 | -8.206% | -100% | -100% | -100% | -69.15% | YES | 1EG003.000 | NO | NR
O&MFLEET SERVICESASSET MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | ASSET MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 1273400.7236 | 0 | 0 | 0 | 1523136.1936 | 1548000 | 1593999.9996 | 1641999.9996 | 1690999.9992 | 6474999.9984 | -274599.2764 | -1593999.9996 | -1641999.9996 | -1690999.9992 | -4951863.8048 | -17.74% | -100% | -100% | -100% | -76.48% | NO | 1FS003.000 | NO | NR
O&MFLEET SERVICESAUTOMOTIVE FUELSNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | AUTOMOTIVE FUELS | Non-RAMP | Non-RAMP | Non-RAMP | 7276166.81 | 0 | 0 | 0 | 8679870.38 | 7569999.9996 | 7797000 | 8031000 | 8271999.9996 | 31669999.9992 | -293833.1896 | -7797000 | -8031000 | -8271999.9996 | -22990129.6192 | -3.882% | -100% | -100% | -100% | -72.59% | NO | 1FS002.001 | NO | NR
O&MFLEET SERVICESCOMMUTATION FEE CREDITSNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | COMMUTATION FEE CREDITS | Non-RAMP | Non-RAMP | Non-RAMP | -287002.94 | 0 | 0 | 0 | -359135.44 | -271999.9992 | -279999.9996 | -288000 | -297000 | -1136999.9988 | -15002.9408 | 279999.9996 | 288000 | 297000 | 777864.5588 | 5.516% | -100% | -100% | -100% | -68.41% | NO | 1FS006.000 | NO | NR
O&MFLEET SERVICESEXISTING LEASES & FEESNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | EXISTING LEASES & FEES | Non-RAMP | Non-RAMP | Non-RAMP | 15228120.91 | 0 | 0 | 0 | 19783574 | 18027999.9996 | 18568999.9992 | 19125999.9996 | 19699999.9992 | 75422999.9976 | -2799879.0896 | -18568999.9992 | -19125999.9996 | -19699999.9992 | -55639425.9976 | -15.53% | -100% | -100% | -100% | -73.77% | NO | 1FS001.001 | NO | NR
O&MFLEET SERVICESFINANCIAL & SYSTEMSNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | FINANCIAL & SYSTEMS | Non-RAMP | Non-RAMP | Non-RAMP | 1815829.59 | 0 | 0 | 0 | 2253655.49 | 1293000 | 1332000 | 1371999.9996 | 1413000 | 5409999.9996 | 522829.59 | -1332000 | -1371999.9996 | -1413000 | -3156344.5096 | 40.44% | -100% | -100% | -100% | -58.34% | NO | 1FS004.000 | NO | NR
O&MFLEET SERVICESHYDROGEN FUEL-CELL VEHICLESNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | HYDROGEN FUEL-CELL VEHICLES | Non-RAMP | Non-RAMP | Non-RAMP | 9479 | 0 | 0 | 0 | 9479 | 30000 | 30999.9996 | 31999.9992 | 33000 | 125999.9988 | -20521 | -30999.9996 | -31999.9992 | -33000 | -116520.9988 | -68.4% | -100% | -100% | -100% | -92.48% | NO | 1FS001.004 | NO | NR
O&MFLEET SERVICESMAINTENANCE GARAGE OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | MAINTENANCE GARAGE OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 16821456.1529 | 0 | 0 | 0 | 20844497.6229 | 14433000 | 14865999.9996 | 15312000 | 15771000 | 60381999.9996 | 2388456.1529 | -14865999.9996 | -15312000 | -15771000 | -39537502.3767 | 16.55% | -100% | -100% | -100% | -65.48% | YES | 1FS002.000 | NO | NR
O&MFLEET SERVICESMAINTENANCE OPERATIONS MANAGEMENT & SUPERVISIONNon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | MAINTENANCE OPERATIONS MANAGEMENT & SUPERVISION | Non-RAMP | Non-RAMP | Non-RAMP | 819669.3607 | 0 | 0 | 0 | 1132095.5207 | 742999.9992 | 765000 | 787999.9992 | 811999.9992 | 3107999.9976 | 76669.3615 | -765000 | -787999.9992 | -811999.9992 | -1975904.4769 | 10.32% | -100% | -100% | -100% | -63.57% | YES | 1FS005.000 | NO | NR
O&MFLEET SERVICESREPLACEMENT PLAN AND SALVAGENon-RAMPNon-RAMPNon-RAMP | O&M | FLEET SERVICES | REPLACEMENT PLAN AND SALVAGE | Non-RAMP | Non-RAMP | Non-RAMP | 2885128 | 0 | 0 | 0 | 2885128 | 4156999.9992 | 4281999.9996 | 4410000 | 4542000 | 17390999.9988 | -1271871.9992 | -4281999.9996 | -4410000 | -4542000 | -14505871.9988 | -30.6% | -100% | -100% | -100% | -83.41% | NO | 1FS001.002 | NO | NR
O&MFLEET SERVICESTELEMATICS SERVICE FEESIncident Involving an EmployeeEnhanced Employee Safe DrivingTrainingVehicle Incident | O&M | FLEET SERVICES | TELEMATICS SERVICE FEES | Incident Involving an Employee | Enhanced Employee Safe DrivingTraining | Vehicle Incident | 403534 | 0 | 0 | 0 | 403534 | 963999.9996 | 993000 | 1023000 | 1053999.9996 | 4033999.9992 | -560465.9996 | -993000 | -1023000 | -1053999.9996 | -3630465.9992 | -58.14% | -100% | -100% | -100% | -90% | YES | 1FS008.000 | NO | SDG&E-Risk-8
O&MGAS DISTRIBUTIONASSET MANAGEMENTAsset ManagementAIM (Gov, Strat, AIP)N/A | O&M | GAS DISTRIBUTION | ASSET MANAGEMENT | Asset Management | AIM (Gov, Strat, AIP) | N/A | 0 | 0 | 0 | 0 | 0 | 123999.9996 | 127999.9992 | 132000 | 135999.9996 | 519999.9984 | -123999.9996 | -127999.9992 | -132000 | -135999.9996 | -519999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1GD009.000 | NO | SDG&E-CFF-1
O&MGAS DISTRIBUTIONASSET MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | ASSET MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 459604.1338 | 0 | 0 | 0 | 549228.0338 | 693000 | 712999.9992 | 733999.9992 | 756000 | 2895999.9984 | -233395.8662 | -712999.9992 | -733999.9992 | -756000 | -2346771.9646 | -33.68% | -100% | -100% | -100% | -81.03% | YES | 1GD009.000 | NO | NR
O&MGAS DISTRIBUTIONASSET MANAGEMENTRecords ManagementGas Geographic Information SystemN/A | O&M | GAS DISTRIBUTION | ASSET MANAGEMENT | Records Management | Gas Geographic Information System | N/A | 686928.9856 | 0 | 0 | 0 | 824732.1256 | 730999.9992 | 752999.9988 | 775999.9992 | 798999.9984 | 3058999.9956 | -44071.0136 | -752999.9988 | -775999.9992 | -798999.9984 | -2234267.87 | -6.029% | -100% | -100% | -100% | -73.04% | YES | 1GD009.000 | NO | SDG&E-CFF-6
O&MGAS DISTRIBUTIONCATHODIC PROTECTIONIncident Related to the Medium Pressure System (Excluding Dig-in)Cathodic Protection - O&MHP Supply Line | O&M | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection - O&M | HP Supply Line | 393161.6642 | 0 | 0 | 0 | 412687.3732 | 111999.9996 | 114999.9996 | 117999.9996 | 121999.9992 | 466999.998 | 281161.6646 | -114999.9996 | -117999.9996 | -121999.9992 | -54312.6248 | 251% | -100% | -100% | -100% | -11.63% | YES | 1GD008.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONCATHODIC PROTECTIONIncident Related to the Medium Pressure System (Excluding Dig-in)Cathodic Protection - O&MMP Main Steel | O&M | GAS DISTRIBUTION | CATHODIC PROTECTION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Cathodic Protection - O&M | MP Main Steel | 1914354.3729 | 0 | 0 | 0 | 2285342.8439 | 1954999.9992 | 2013999.9996 | 2074999.9992 | 2136999.9996 | 8180999.9976 | -40645.6263 | -2013999.9996 | -2074999.9992 | -2136999.9996 | -5895657.1537 | -2.079% | -100% | -100% | -100% | -72.07% | YES | 1GD008.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONELECTRIC SUPPORTNon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | ELECTRIC SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | 755969.7413 | 0 | 0 | 0 | 961555.3513 | 559999.9992 | 576999.9996 | 594000 | 612000 | 2342999.9988 | 195969.7421 | -576999.9996 | -594000 | -612000 | -1381444.6475 | 34.99% | -100% | -100% | -100% | -58.96% | YES | 1GD006.000 | NO | NR
O&MGAS DISTRIBUTIONLEAK SURVEYIncident Related to the Medium Pressure System (Excluding Dig-in)Pipeline Monitoring (Leak Mitigation, Bridge & Span, Unstable Earth, and Pipeline PatrolHP Transmission | O&M | GAS DISTRIBUTION | LEAK SURVEY | Incident Related to the Medium Pressure System (Excluding Dig-in) | Pipeline Monitoring (Leak Mitigation, Bridge & Span, Unstable Earth, and Pipeline Patrol | HP Transmission | 56144.508 | 0 | 0 | 0 | 56144.508 | 27000 | 27999.9996 | 28999.9992 | 30000 | 113999.9988 | 29144.508 | -27999.9996 | -28999.9992 | -30000 | -57855.4908 | 107.9% | -100% | -100% | -100% | -50.75% | YES | 1GD001.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONLEAK SURVEYIncident Related to the Medium Pressure System (Excluding Dig-in)Pipeline Monitoring (Leak Mitigation, Bridge & Span, Unstable Earth, and Pipeline PatrolMP Overall | O&M | GAS DISTRIBUTION | LEAK SURVEY | Incident Related to the Medium Pressure System (Excluding Dig-in) | Pipeline Monitoring (Leak Mitigation, Bridge & Span, Unstable Earth, and Pipeline Patrol | MP Overall | 2700732.1707 | 0 | 0 | 0 | 3067230.1607 | 2304000 | 2373000 | 2443999.9992 | 2517000 | 9637999.9992 | 396732.1707 | -2373000 | -2443999.9992 | -2517000 | -6570769.8385 | 17.22% | -100% | -100% | -100% | -68.18% | YES | 1GD001.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONMAIN MAINTENANCEIncident Related to the Medium Pressure System (Excluding Dig-in)Gas Distribution Emergency Department - Main PortionMP Main Steel & Plastic | O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Gas Distribution Emergency Department - Main Portion | MP Main Steel & Plastic | 1299794.2833 | 0 | 0 | 0 | 1386675.9633 | 1296999.9996 | 1335999.9996 | 1375999.9992 | 1416999.9996 | 5425999.998 | 2794.2837 | -1335999.9996 | -1375999.9992 | -1416999.9996 | -4039324.0347 | 0.2154% | -100% | -100% | -100% | -74.44% | YES | 1GD003.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONMAIN MAINTENANCEIncident Related to the Medium Pressure System (Excluding Dig-in)Leak Repair - Main PortionMP Main Plastic | O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Main Portion | MP Main Plastic | 479824.3946 | 0 | 0 | 0 | 531958.6186 | 369999.9996 | 381000 | 391999.9992 | 403999.9992 | 1546999.998 | 109824.395 | -381000 | -391999.9992 | -403999.9992 | -1015041.3794 | 29.68% | -100% | -100% | -100% | -65.61% | YES | 1GD003.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONMAIN MAINTENANCEIncident Related to the Medium Pressure System (Excluding Dig-in)Leak Repair - Main PortionMP Main Steel | O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Main Portion | MP Main Steel | 719736.592 | 0 | 0 | 0 | 797937.928 | 637999.9992 | 657000 | 676999.9992 | 696999.9996 | 2668999.998 | 81736.5928 | -657000 | -676999.9992 | -696999.9996 | -1871062.07 | 12.81% | -100% | -100% | -100% | -70.1% | YES | 1GD003.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONMAIN MAINTENANCENon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | MAIN MAINTENANCE | Non-RAMP | Non-RAMP | Non-RAMP | 2164837.1412 | 0 | 0 | 0 | 3010415.2912 | 2977999.9992 | 3066999.9996 | 3159000 | 3253999.9992 | 12457999.998 | -813162.858 | -3066999.9996 | -3159000 | -3253999.9992 | -9447584.7068 | -27.31% | -100% | -100% | -100% | -75.84% | YES | 1GD003.000 | NO | NR
O&MGAS DISTRIBUTIONMEASUREMENT & REGULATIONIncident Related to the Medium Pressure System (Excluding Dig-in)Control Center Modernization - Incremental add of personnelN/A | O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Control Center Modernization - Incremental add of personnel | N/A | 0 | 0 | 0 | 0 | 0 | 540000 | 555999.9996 | 573000 | 589999.9992 | 2258999.9988 | -540000 | -555999.9996 | -573000 | -589999.9992 | -2258999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1GD007.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONMEASUREMENT & REGULATIONIncident Related to the Medium Pressure System (Excluding Dig-in)Regulator Station, Valve, and Large Meter Set InspectionHP Supply Line | O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Regulator Station, Valve, and Large Meter Set Inspection | HP Supply Line | 130097.4689 | 0 | 0 | 0 | 158375.8311 | 90000 | 93000 | 96000 | 99000 | 378000 | 40097.4689 | -93000 | -96000 | -99000 | -219624.1689 | 44.55% | -100% | -100% | -100% | -58.1% | YES | 1GD007.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONMEASUREMENT & REGULATIONIncident Related to the Medium Pressure System (Excluding Dig-in)Regulator Station, Valve, and Large Meter Set InspectionMP Overall | O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Incident Related to the Medium Pressure System (Excluding Dig-in) | Regulator Station, Valve, and Large Meter Set Inspection | MP Overall | 4599236.8802 | 0 | 0 | 0 | 5984876.628 | 4398999.9996 | 4530999.9996 | 4665999.9996 | 4806000 | 18401999.9988 | 200236.8806 | -4530999.9996 | -4665999.9996 | -4806000 | -12417123.3708 | 4.552% | -100% | -100% | -100% | -67.48% | YES | 1GD007.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONMEASUREMENT & REGULATIONNon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | MEASUREMENT & REGULATION | Non-RAMP | Non-RAMP | Non-RAMP | 1570073.5924 | 0 | 0 | 0 | 1677589.2224 | 772999.9992 | 795999.9996 | 819999.9996 | 844999.9992 | 3233999.9976 | 797073.5932 | -795999.9996 | -819999.9996 | -844999.9992 | -1556410.7752 | 103.1% | -100% | -100% | -100% | -48.13% | YES | 1GD007.000 | NO | NR
O&MGAS DISTRIBUTIONOPERATIONS MANAGEMENT, SUPERVISION & TRAININGExcavation Damage (Dig-In) on the Gas SystemL&M Training GroupingsMP | O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Excavation Damage (Dig-In) on the Gas System | L&M Training Groupings | MP | 299570.3628 | 0 | 0 | 0 | 307605.1428 | 840999.9996 | 865999.9992 | 891999.9996 | 918999.9996 | 3517999.998 | -541429.6368 | -865999.9992 | -891999.9996 | -918999.9996 | -3210394.8552 | -64.38% | -100% | -100% | -100% | -91.26% | YES | 1GD010.000 | NO | SDG&E-Risk-7
O&MGAS DISTRIBUTIONOPERATIONS MANAGEMENT, SUPERVISION & TRAININGIncident Related to the Medium Pressure System (Excluding Dig-in)Human Factors Mitigation - QA/QC ProgramN/A | O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factors Mitigation - QA/QC Program | N/A | 293997.9829 | 0 | 0 | 0 | 293997.9829 | 337999.9992 | 348000 | 357999.9996 | 369000 | 1412999.9988 | -44002.0163 | -348000 | -357999.9996 | -369000 | -1119002.0159 | -13.02% | -100% | -100% | -100% | -79.19% | YES | 1GD010.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONOPERATIONS MANAGEMENT, SUPERVISION & TRAININGIncident Related to the Medium Pressure System (Excluding Dig-in)Human Factors Mitigations - Ops Qual TrainingN/A | O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Incident Related to the Medium Pressure System (Excluding Dig-in) | Human Factors Mitigations - Ops Qual Training | N/A | 1940112.377 | 0 | 0 | 0 | 2246226.087 | 1872000 | 1927999.9992 | 1986000 | 2046000 | 7831999.9992 | 68112.377 | -1927999.9992 | -1986000 | -2046000 | -5585773.9122 | 3.638% | -100% | -100% | -100% | -71.32% | YES | 1GD010.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONOPERATIONS MANAGEMENT, SUPERVISION & TRAININGNon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | OPERATIONS MANAGEMENT, SUPERVISION & TRAINING | Non-RAMP | Non-RAMP | Non-RAMP | 6010873.2065 | 0 | 0 | 0 | 7381936.6565 | 7236999.9996 | 7455000 | 7678999.9992 | 7908000 | 30278999.9988 | -1226126.7931 | -7455000 | -7678999.9992 | -7908000 | -22897063.3423 | -16.94% | -100% | -100% | -100% | -75.62% | YES | 1GD010.000 | NO | NR
O&MGAS DISTRIBUTIONOTHER SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | OTHER SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 207891.5248 | 0 | 0 | 0 | 239530.3448 | 0 | 0 | 0 | 0 | 0 | 207891.5248 | 0 | 0 | 0 | 239530.3448 | 100% | 100% | 100% | 100% | 100% | YES | 1GD000.000 | NO | NR
O&MGAS DISTRIBUTIONR-LOCATE & MARKExcavation Damage (Dig-In) on the Gas SystemLocate & Mark Activities (HP)HP | O&M | GAS DISTRIBUTION | R-LOCATE & MARK | Excavation Damage (Dig-In) on the Gas System | Locate & Mark Activities (HP) | HP | 501445.0084 | 0 | 0 | 0 | 589550.1629 | 108999.9996 | 111999.9996 | 114999.9996 | 117999.9996 | 453999.9984 | 392445.0088 | -111999.9996 | -114999.9996 | -117999.9996 | 135550.1645 | 360% | -100% | -100% | -100% | 29.86% | YES | 1GD002.000 | NO | SDG&E-Risk-7
O&MGAS DISTRIBUTIONR-LOCATE & MARKExcavation Damage (Dig-In) on the Gas SystemLocate & Mark Activities (MP)MP | O&M | GAS DISTRIBUTION | R-LOCATE & MARK | Excavation Damage (Dig-In) on the Gas System | Locate & Mark Activities (MP) | MP | 9217769.0774 | 0 | 0 | 0 | 10891767.0129 | 3844999.9992 | 3960000 | 4078999.9992 | 4201999.9992 | 16085999.9976 | 5372769.0782 | -3960000 | -4078999.9992 | -4201999.9992 | -5194232.9847 | 139.7% | -100% | -100% | -100% | -32.29% | YES | 1GD002.000 | NO | SDG&E-Risk-7
O&MGAS DISTRIBUTIONR-LOCATE & MARKExcavation Damage (Dig-In) on the Gas SystemLocate & Mark Quality AssuranceMP | O&M | GAS DISTRIBUTION | R-LOCATE & MARK | Excavation Damage (Dig-In) on the Gas System | Locate & Mark Quality Assurance | MP | 293997.9829 | 0 | 0 | 0 | 293997.9829 | 159999.9996 | 165000 | 169999.9992 | 174999.9996 | 669999.9984 | 133997.9833 | -165000 | -169999.9992 | -174999.9996 | -376002.0155 | 83.75% | -100% | -100% | -100% | -56.12% | YES | 1GD002.000 | NO | SDG&E-Risk-7
O&MGAS DISTRIBUTIONSERVICE MAINTENANCEIncident Related to the Medium Pressure System (Excluding Dig-in)Gas Distribution Emergency Department - Service PortionMP Service Steel & Plastic | O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Gas Distribution Emergency Department - Service Portion | MP Service Steel & Plastic | 1166845.3686 | 0 | 0 | 0 | 1427489.0086 | 777000 | 799999.9992 | 823999.9992 | 849000 | 3249999.9984 | 389845.3686 | -799999.9992 | -823999.9992 | -849000 | -1822510.9898 | 50.17% | -100% | -100% | -100% | -56.08% | YES | 1GD004.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONSERVICE MAINTENANCEIncident Related to the Medium Pressure System (Excluding Dig-in)Leak Repair - Service PortionMP Service Plastic | O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Service Portion | MP Service Plastic | 682950.9807 | 0 | 0 | 0 | 885546.2656 | 588000 | 606000 | 624000 | 642999.9996 | 2460999.9996 | 94950.9806 | -606000 | -624000 | -642999.9996 | -1575453.734 | 16.15% | -100% | -100% | -100% | -64.02% | YES | 1GD004.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONSERVICE MAINTENANCEIncident Related to the Medium Pressure System (Excluding Dig-in)Leak Repair - Service PortionMP Service Steel | O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Incident Related to the Medium Pressure System (Excluding Dig-in) | Leak Repair - Service Portion | MP Service Steel | 1024424.0511 | 0 | 0 | 0 | 1227019.3361 | 891999.9996 | 918999.9996 | 946999.9992 | 973999.9992 | 3731999.9976 | 132424.0514 | -918999.9996 | -946999.9992 | -973999.9992 | -2504980.6615 | 14.85% | -100% | -100% | -100% | -67.12% | YES | 1GD004.000 | NO | SDG&E-Risk-9
O&MGAS DISTRIBUTIONSERVICE MAINTENANCENon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | SERVICE MAINTENANCE | Non-RAMP | Non-RAMP | Non-RAMP | 2118010.7585 | 0 | 0 | 0 | 2806489.0785 | 865999.9992 | 891999.9996 | 918999.9996 | 946999.9992 | 3623999.9976 | 1252010.7593 | -891999.9996 | -918999.9996 | -946999.9992 | -817510.9191 | 144.6% | -100% | -100% | -100% | -22.56% | YES | 1GD004.000 | NO | NR
O&MGAS DISTRIBUTIONTOOLSIncident Involving an EmployeePersonal Protective EquipmentN/A | O&M | GAS DISTRIBUTION | TOOLS | Incident Involving an Employee | Personal Protective Equipment | N/A | 357798.93 | 0 | 0 | 0 | 596801.47 | 499999.9992 | 514999.9992 | 529999.9992 | 546000 | 2090999.9976 | -142201.0692 | -514999.9992 | -529999.9992 | -546000 | -1494198.5276 | -28.44% | -100% | -100% | -100% | -71.46% | YES | 1GD005.000 | NO | SDG&E-Risk-8
O&MGAS DISTRIBUTIONTOOLSNon-RAMPNon-RAMPNon-RAMP | O&M | GAS DISTRIBUTION | TOOLS | Non-RAMP | Non-RAMP | Non-RAMP | 1662610.5419 | 0 | 0 | 0 | 2040479.0919 | 1390999.9992 | 1432999.9992 | 1476000 | 1519999.9992 | 5819999.9976 | 271610.5427 | -1432999.9992 | -1476000 | -1519999.9992 | -3779520.9057 | 19.53% | -100% | -100% | -100% | -64.94% | YES | 1GD005.000 | NO | NR
O&MGAS INTEGRITY PROGRAMSDIMPIncident Related to the Medium Pressure System (Excluding Dig-in)Distribution Integrity Management Program (DIMP)Plastic - Main (VIPP) | O&M | GAS INTEGRITY PROGRAMS | DIMP | Incident Related to the Medium Pressure System (Excluding Dig-in) | Distribution Integrity Management Program (DIMP) | Plastic - Main (VIPP) | 660744.1471 | 0 | 0 | 0 | 829495.0471 | 0 | 0 | 0 | 0 | 0 | 660744.1471 | 0 | 0 | 0 | 829495.0471 | 100% | 100% | 100% | 100% | 100% | YES | 1TD002.000 | YES | SDG&E-Risk-9
O&MGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA)Transmission - HCA | O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - HCA | 0 | 0 | 0 | 0 | 0 | 76999.9992 | 78000 | 79999.9992 | 81999.9996 | 316999.998 | -76999.9992 | -78000 | -79999.9992 | -81999.9996 | -316999.998 | -100% | -100% | -100% | -100% | -100% | YES | 1TD005.000 | NO | SDG&E-Risk-3
O&MGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA)Transmission - Non-HCA | O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | Gas Transmission Safety Rule - MAOP Reconfirmation (HCA and Non-HCA) | Transmission - Non-HCA | 0 | 0 | 0 | 0 | 0 | 24000 | 24999.9996 | 25999.9992 | 27000 | 101999.9988 | -24000 | -24999.9996 | -25999.9992 | -27000 | -101999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1TD005.000 | NO | SDG&E-Risk-3
O&MGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)NEW - Gas Transmission Safety Rule (GTSR) Part 2Transmission - HCA & non-HCA | O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Gas Transmission Safety Rule (GTSR) Part 2 | Transmission - HCA & non-HCA | 0 | 0 | 0 | 0 | 0 | 18000 | 18999.9996 | 19999.9992 | 21000 | 77999.9988 | -18000 | -18999.9996 | -19999.9992 | -21000 | -77999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1TD005.000 | NO | SDG&E-Risk-3
O&MGAS INTEGRITY PROGRAMSGAS SAFETY ENHANCEMENT PROGRAMSIncident Related to the High Pressure System (Excluding Dig-in)NEW - Valve RuleTransmission - HCA & non-HCA | O&M | GAS INTEGRITY PROGRAMS | GAS SAFETY ENHANCEMENT PROGRAMS | Incident Related to the High Pressure System (Excluding Dig-in) | NEW - Valve Rule | Transmission - HCA & non-HCA | 0 | 0 | 0 | 0 | 0 | 27000 | 27999.9996 | 28999.9992 | 30000 | 113999.9988 | -27000 | -27999.9996 | -28999.9992 | -30000 | -113999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1TD005.000 | NO | SDG&E-Risk-3
O&MGAS INTEGRITY PROGRAMSTIMPIncident Related to the High Pressure System (Excluding Dig-in)Integrity Assessments & Remediation (HCA and Non-HCA)Transmission - HCA | O&M | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - HCA | 30929651.1047 | 0 | 0 | 0 | 37153165.8147 | 10149000 | 10452999.9996 | 10767000 | 11089999.9992 | 42458999.9988 | 20780651.1047 | -10452999.9996 | -10767000 | -11089999.9992 | -5305834.1841 | 204.8% | -100% | -100% | -100% | -12.5% | YES | 1TD001.000 | YES | SDG&E-Risk-3
O&MGAS INTEGRITY PROGRAMSTIMPIncident Related to the High Pressure System (Excluding Dig-in)Integrity Assessments & Remediation (HCA and Non-HCA)Transmission - Non-HCA | O&M | GAS INTEGRITY PROGRAMS | TIMP | Incident Related to the High Pressure System (Excluding Dig-in) | Integrity Assessments & Remediation (HCA and Non-HCA) | Transmission - Non-HCA | 631217.9028 | 0 | 0 | 0 | 631217.9028 | 534000 | 549999.9996 | 565999.9992 | 582999.9996 | 2232999.9984 | 97217.9028 | -549999.9996 | -565999.9992 | -582999.9996 | -1601782.0956 | 18.21% | -100% | -100% | -100% | -71.73% | YES | 1TD001.000 | YES | SDG&E-Risk-3
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemOutreach for Latent 3rd Party Damages (HP)N/A | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Outreach for Latent 3rd Party Damages (HP) | N/A | 0 | 0 | 0 | 0 | 0 | 999.9996 | 999.9996 | 999.9996 | 999.9996 | 3999.9984 | -999.9996 | -999.9996 | -999.9996 | -999.9996 | -3999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemOutreach for Latent 3rd Party Damages (MP)N/A | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Outreach for Latent 3rd Party Damages (MP) | N/A | 869.102 | 0 | 0 | 0 | 1271.9414 | 3000 | 3000 | 3000 | 3000 | 12000 | -2130.898 | -3000 | -3000 | -3000 | -10728.0586 | -71.03% | -100% | -100% | -100% | -89.4% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (HP) (T1 - T4)Emergency Officials (HP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | Emergency Officials (HP) | 0 | 0 | 0 | 0 | 0 | 999.9996 | 999.9996 | 999.9996 | 999.9996 | 3999.9984 | -999.9996 | -999.9996 | -999.9996 | -999.9996 | -3999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (HP) (T1 - T4)Excavators (HP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | Excavators (HP) | 869.102 | 0 | 0 | 0 | 1271.9414 | 6000 | 6000 | 6000 | 6000 | 24000 | -5130.898 | -6000 | -6000 | -6000 | -22728.0586 | -85.51% | -100% | -100% | -100% | -94.7% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (HP) (T1 - T4)Local Public Officials (HP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | Local Public Officials (HP) | 869.102 | 0 | 0 | 0 | 1271.9414 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | 19999.9968 | -4130.8972 | -4999.9992 | -4999.9992 | -4999.9992 | -18728.0554 | -82.62% | -100% | -100% | -100% | -93.64% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (HP) (T1 - T4)The Affected Public (HP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (HP) (T1 - T4) | The Affected Public (HP) | 36112.51 | 0 | 0 | 0 | 38126.707 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 97999.998 | 13112.5108 | -24000 | -24999.9996 | -25999.9992 | -59873.291 | 57.01% | -100% | -100% | -100% | -61.1% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (MP) (T1 - T4)Emergency Officials (MP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | Emergency Officials (MP) | 869.102 | 0 | 0 | 0 | 1271.9414 | 3000 | 3000 | 3000 | 3000 | 12000 | -2130.898 | -3000 | -3000 | -3000 | -10728.0586 | -71.03% | -100% | -100% | -100% | -89.4% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (MP) (T1 - T4)Excavators (MP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | Excavators (MP) | 4345.51 | 0 | 0 | 0 | 6359.707 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 97999.998 | -18654.4892 | -24000 | -24999.9996 | -25999.9992 | -91640.291 | -81.11% | -100% | -100% | -100% | -93.51% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (MP) (T1 - T4)Local Public Officials (MP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | Local Public Officials (MP) | 3476.408 | 0 | 0 | 0 | 5087.7656 | 18999.9996 | 19999.9992 | 21000 | 21999.9996 | 81999.9984 | -15523.5916 | -19999.9992 | -21000 | -21999.9996 | -76912.2328 | -81.7% | -100% | -100% | -100% | -93.8% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONExcavation Damage (Dig-In) on the Gas SystemPublic Awareness (MP) (T1 - T4)The Affected Public (MP) | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Excavation Damage (Dig-In) on the Gas System | Public Awareness (MP) (T1 - T4) | The Affected Public (MP) | 174173.652 | 0 | 0 | 0 | 184647.4764 | 121999.9992 | 126000 | 129999.9996 | 133999.9992 | 511999.998 | 52173.6528 | -126000 | -129999.9996 | -133999.9992 | -327352.5216 | 42.77% | -100% | -100% | -100% | -63.94% | YES | 1SI001.000 | NO | SDG&E-Risk-7
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONNon-RAMPNon-RAMPNon-RAMP | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Non-RAMP | Non-RAMP | Non-RAMP | 310067.0831 | 0 | 0 | 0 | 310067.0831 | 102999.9996 | 105999.9996 | 108999.9996 | 111999.9996 | 429999.9984 | 207067.0835 | -105999.9996 | -108999.9996 | -111999.9996 | -119932.9153 | 201% | -100% | -100% | -100% | -27.89% | YES | 1SI001.001 | NO | NR
O&MGAS SYSTEM STAFF & TECHNOLOGYDAMAGE PREVENTIONNon-RAMPNon-RAMPNon-RAMP | O&M | GAS SYSTEM STAFF & TECHNOLOGY | DAMAGE PREVENTION | Non-RAMP | Non-RAMP | Non-RAMP | 49161.712 | 0 | 0 | 0 | 71720.7184 | 171999.9996 | 175999.9992 | 180999.9996 | 186000 | 714999.9984 | -122838.2876 | -175999.9992 | -180999.9996 | -186000 | -643279.28 | -71.42% | -100% | -100% | -100% | -89.97% | YES | 1SI001.000 | NO | NR
O&MGAS TRANSMISSIONCOMPRESSOR STATION OPERATIONS - MORENOIncident Related to the High Pressure System (Excluding Dig-in)Compressor StationTransmission - Facilities | O&M | GAS TRANSMISSION | COMPRESSOR STATION OPERATIONS - MORENO | Incident Related to the High Pressure System (Excluding Dig-in) | Compressor Station | Transmission - Facilities | 3463730.9239 | 0 | 0 | 0 | 3463730.9239 | 3502999.9992 | 3607999.9992 | 3715999.9992 | 3828000 | 14654999.9976 | -39269.0753 | -3607999.9992 | -3715999.9992 | -3828000 | -11191269.0737 | -1.121% | -100% | -100% | -100% | -76.36% | YES | 1GT001.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONCOMPRESSOR STATION OPERATIONS - MORENOIncident Related to the High Pressure System (Excluding Dig-in)Engineering, Oversight Compliance ReviewN/A | O&M | GAS TRANSMISSION | COMPRESSOR STATION OPERATIONS - MORENO | Incident Related to the High Pressure System (Excluding Dig-in) | Engineering, Oversight Compliance Review | N/A | 6496 | 0 | 0 | 0 | 6496 | 93000 | 96000 | 99000 | 102000 | 390000 | -86504 | -96000 | -99000 | -102000 | -383504 | -93.02% | -100% | -100% | -100% | -98.33% | YES | 1GT001.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONCOMPRESSOR STATION OPERATIONS - MORENONon-RAMPNon-RAMPNon-RAMP | O&M | GAS TRANSMISSION | COMPRESSOR STATION OPERATIONS - MORENO | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 256999.9992 | 264999.9996 | 273000 | 280999.9992 | 1075999.998 | -256999.9992 | -264999.9996 | -273000 | -280999.9992 | -1075999.998 | -100% | -100% | -100% | -100% | -100% | YES | 1GT001.000 | NO | NR
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)Cathodic Protection (HCA & Non-HCA)Transmission - HCA | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection (HCA & Non-HCA) | Transmission - HCA | 110379.7648 | 0 | 0 | 0 | 110379.7648 | 70999.9992 | 72999.9996 | 75000 | 76999.9992 | 295999.998 | 39379.7656 | -72999.9996 | -75000 | -76999.9992 | -185620.2332 | 55.46% | -100% | -100% | -100% | -62.71% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)Cathodic Protection (HCA & Non-HCA)Transmission - Non-HCA | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Cathodic Protection (HCA & Non-HCA) | Transmission - Non-HCA | 24229.7932 | 0 | 0 | 0 | 24229.7932 | 15999.9996 | 15999.9996 | 15999.9996 | 15999.9996 | 63999.9984 | 8229.7936 | -15999.9996 | -15999.9996 | -15999.9996 | -39770.2052 | 51.44% | -100% | -100% | -100% | -62.14% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)Engineering, Oversight Compliance ReviewN/A | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Engineering, Oversight Compliance Review | N/A | 22154.28 | 0 | 0 | 0 | 23791.43 | 93000 | 96000 | 99000 | 102000 | 390000 | -70845.72 | -96000 | -99000 | -102000 | -366208.57 | -76.18% | -100% | -100% | -100% | -93.9% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)Measurement & Regulation Station Maintenance (HCA & Non-HCA)Transmission - HCA | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation Station Maintenance (HCA & Non-HCA) | Transmission - HCA | 298617.2605 | 0 | 0 | 0 | 363231.4893 | 324999.9996 | 334999.9992 | 345000 | 355999.9992 | 1360999.998 | -26382.7391 | -334999.9992 | -345000 | -355999.9992 | -997768.5087 | -8.118% | -100% | -100% | -100% | -73.31% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)Measurement & Regulation Station Maintenance (HCA & Non-HCA)Transmission - Non-HCA | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Measurement & Regulation Station Maintenance (HCA & Non-HCA) | Transmission - Non-HCA | 65549.9108 | 0 | 0 | 0 | 79733.522 | 72000 | 73999.9992 | 75999.9996 | 78000 | 299999.9988 | -6450.0892 | -73999.9992 | -75999.9996 | -78000 | -220266.4768 | -8.958% | -100% | -100% | -100% | -73.42% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)OdorizationTransmission Facilities | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Odorization | Transmission Facilities | 0 | 0 | 0 | 0 | 0 | 9999.9996 | 9999.9996 | 9999.9996 | 9999.9996 | 39999.9984 | -9999.9996 | -9999.9996 | -9999.9996 | -9999.9996 | -39999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)Pipeline Maintenance (HCA & Non-HCA)Transmission - HCA | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline Maintenance (HCA & Non-HCA) | Transmission - HCA | 1077570.9758 | 0 | 0 | 0 | 1278579.0354 | 564000 | 580999.9992 | 598999.9992 | 616999.9992 | 2360999.9976 | 513570.9758 | -580999.9992 | -598999.9992 | -616999.9992 | -1082420.9622 | 91.06% | -100% | -100% | -100% | -45.85% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSIncident Related to the High Pressure System (Excluding Dig-in)Pipeline Maintenance (HCA & Non-HCA)Transmission - Non-HCA | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Incident Related to the High Pressure System (Excluding Dig-in) | Pipeline Maintenance (HCA & Non-HCA) | Transmission - Non-HCA | 236539.6504 | 0 | 0 | 0 | 280663.3708 | 123999.9996 | 127999.9992 | 132000 | 135999.9996 | 519999.9984 | 112539.6508 | -127999.9992 | -132000 | -135999.9996 | -239336.6276 | 90.76% | -100% | -100% | -100% | -46.03% | YES | 1GT000.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONPIPELINE & INSTRUMENTATION OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | GAS TRANSMISSION | PIPELINE & INSTRUMENTATION OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | -0.1574 | 0 | 0 | 0 | 58228.9626 | 1008000 | 1038000 | 1069999.9992 | 1102999.9992 | 4218999.9984 | -1008000.1574 | -1038000 | -1069999.9992 | -1102999.9992 | -4160771.0358 | -100% | -100% | -100% | -100% | -98.62% | YES | 1GT000.000 | NO | NR
O&MGAS TRANSMISSIONTECHNICAL SERVICESIncident Related to the High Pressure System (Excluding Dig-in)Engineering, Oversight Compliance ReviewN/A | O&M | GAS TRANSMISSION | TECHNICAL SERVICES | Incident Related to the High Pressure System (Excluding Dig-in) | Engineering, Oversight Compliance Review | N/A | 79787.945 | 0 | 0 | 0 | 892384.345 | 48999.9996 | 51000 | 52999.9992 | 54999.9996 | 207999.9984 | 30787.9454 | -51000 | -52999.9992 | -54999.9996 | 684384.3466 | 62.83% | -100% | -100% | -100% | 329% | YES | 1GT002.000 | NO | SDG&E-Risk-3
O&MGAS TRANSMISSIONTECHNICAL SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | GAS TRANSMISSION | TECHNICAL SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 6999.9996 | 6999.9996 | 6999.9996 | 6999.9996 | 27999.9984 | -6999.9996 | -6999.9996 | -6999.9996 | -6999.9996 | -27999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1GT002.000 | NO | NR
O&MINFORMATION TECHNOLOGYNON-SHARED OPERATIONAL APPLICATIONSFoundational Technology SystemsAll MitigationsN/A | O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL APPLICATIONS | Foundational Technology Systems | All Mitigations | N/A | 1789947.4574 | 0 | 0 | 0 | 2335933.0724 | 1818999.9996 | 1873999.9992 | 1929999.9996 | 1987999.9992 | 7610999.9976 | -29052.5422 | -1873999.9992 | -1929999.9996 | -1987999.9992 | -5275066.9252 | -1.597% | -100% | -100% | -100% | -69.31% | YES | 1IT002.000 | NO | SDG&E-CFF-4
O&MINFORMATION TECHNOLOGYNON-SHARED OPERATIONAL APPLICATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 12141666.3427 | 0 | 0 | 0 | 15371435.5077 | 12342999.9996 | 12712999.9992 | 13095000 | 13488000 | 51638999.9988 | -201333.6569 | -12712999.9992 | -13095000 | -13488000 | -36267564.4911 | -1.631% | -100% | -100% | -100% | -70.23% | YES | 1IT002.000 | NO | NR
O&MINFORMATION TECHNOLOGYNON-SHARED OPERATIONAL INFRASTRUCTUREFoundational Technology SystemsAll MitigationsN/A | O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL INFRASTRUCTURE | Foundational Technology Systems | All Mitigations | N/A | 3022588.0367 | 0 | 0 | 0 | 3513931.8179 | 2853000 | 2938999.9992 | 3027000 | 3117999.9996 | 11936999.9988 | 169588.0367 | -2938999.9992 | -3027000 | -3117999.9996 | -8423068.1809 | 5.944% | -100% | -100% | -100% | -70.56% | YES | 1IT004.000 | NO | SDG&E-CFF-4
O&MINFORMATION TECHNOLOGYNON-SHARED OPERATIONAL INFRASTRUCTURENon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | NON-SHARED OPERATIONAL INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | 5084677.2732 | 0 | 0 | 0 | 6787932.072 | 4801999.9992 | 4945999.9992 | 5094999.9996 | 5247999.9996 | 20090999.9976 | 282677.274 | -4945999.9992 | -5094999.9996 | -5247999.9996 | -13303067.9256 | 5.887% | -100% | -100% | -100% | -66.21% | YES | 1IT004.000 | NO | NR
O&MINFORMATION TECHNOLOGYSHARED APPLICATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | SHARED APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 15845031.7502 | 0 | 0 | 0 | 19788346.6102 | 21342999.9996 | 21982999.9992 | 22641999.9996 | 23320999.9992 | 89288999.9976 | -5497968.2494 | -21982999.9992 | -22641999.9996 | -23320999.9992 | -69500653.3874 | -25.76% | -100% | -100% | -100% | -77.84% | NO | 2100-3071.000 | NO | NR
O&MINFORMATION TECHNOLOGYSHARED INFRASTRUCTURENon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | SHARED INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | 3369453.7716 | 0 | 0 | 0 | 4317355.2816 | 4398999.9996 | 4530999.9996 | 4666999.9992 | 4806999.9996 | 18403999.998 | -1029546.228 | -4530999.9996 | -4666999.9992 | -4806999.9996 | -14086644.7164 | -23.4% | -100% | -100% | -100% | -76.54% | NO | 2100-3097.000 | NO | NR
O&MINFORMATION TECHNOLOGYSHARED OPERATIONAL APPLICATIONSFoundational Technology SystemsAll MitigationsN/A | O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL APPLICATIONS | Foundational Technology Systems | All Mitigations | N/A | 2155097.524 | 0 | 0 | 0 | 2686441.4859 | 2856999.9996 | 2943000 | 3030999.9996 | 3121999.9992 | 11952999.9984 | -701902.4756 | -2943000 | -3030999.9996 | -3121999.9992 | -9266558.5125 | -24.57% | -100% | -100% | -100% | -77.52% | YES | 2100-3073.000 | NO | SDG&E-CFF-4
O&MINFORMATION TECHNOLOGYSHARED OPERATIONAL APPLICATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL APPLICATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 10681894.9695 | 0 | 0 | 0 | 12916676.1876 | 14163999.9996 | 14589000 | 15027000 | 15477999.9996 | 59257999.9992 | -3482105.0301 | -14589000 | -15027000 | -15477999.9996 | -46341323.8116 | -24.58% | -100% | -100% | -100% | -78.2% | YES | 2100-3073.000 | NO | NR
O&MINFORMATION TECHNOLOGYSHARED OPERATIONAL INFRASTRUCTUREFoundational Technology SystemsAll MitigationsN/A | O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL INFRASTRUCTURE | Foundational Technology Systems | All Mitigations | N/A | 19875209.7255 | 0 | 0 | 0 | 23735483.5087 | 21741000 | 22392999.9996 | 23064000 | 23755999.9992 | 90953999.9988 | -1865790.2745 | -22392999.9996 | -23064000 | -23755999.9992 | -67218516.4901 | -8.582% | -100% | -100% | -100% | -73.9% | YES | 2100-0207.000 | NO | SDG&E-CFF-4
O&MINFORMATION TECHNOLOGYSHARED OPERATIONAL INFRASTRUCTURENon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL INFRASTRUCTURE | Non-RAMP | Non-RAMP | Non-RAMP | 10853553.5205 | 0 | 0 | 0 | 15648304.9473 | 13188999.9996 | 13584999.9996 | 13992999.9996 | 14412999.9996 | 55179999.9984 | -2335446.4791 | -13584999.9996 | -13992999.9996 | -14412999.9996 | -39531695.0511 | -17.71% | -100% | -100% | -100% | -71.64% | YES | 2100-0207.000 | NO | NR
O&MINFORMATION TECHNOLOGYSHARED OPERATIONAL SUPPORTFoundational Technology SystemsAll MitigationsN/A | O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL SUPPORT | Foundational Technology Systems | All Mitigations | N/A | 508952.8831 | 0 | 0 | 0 | 508952.8831 | 918000 | 945999.9996 | 973999.9992 | 1002999.9996 | 3840999.9984 | -409047.1169 | -945999.9996 | -973999.9992 | -1002999.9996 | -3332047.1153 | -44.56% | -100% | -100% | -100% | -86.75% | YES | 2100-0460.000 | NO | SDG&E-CFF-4
O&MINFORMATION TECHNOLOGYSHARED OPERATIONAL SUPPORTNon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | SHARED OPERATIONAL SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | 2226148.4151 | 0 | 0 | 0 | 3070822.3551 | 4015999.9992 | 4135999.9992 | 4260000 | 4387999.9992 | 16799999.9976 | -1789851.5841 | -4135999.9992 | -4260000 | -4387999.9992 | -13729177.6425 | -44.57% | -100% | -100% | -100% | -81.72% | YES | 2100-0460.000 | NO | NR
O&MINFORMATION TECHNOLOGYSHARED SUPPORTNon-RAMPNon-RAMPNon-RAMP | O&M | INFORMATION TECHNOLOGY | SHARED SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | 5036182.9912 | 0 | 0 | 0 | 5787121.1312 | 7360999.9992 | 7581999.9996 | 7809000 | 8043000 | 30794999.9988 | -2324817.0079 | -7581999.9996 | -7809000 | -8043000 | -25007878.8676 | -31.58% | -100% | -100% | -100% | -81.21% | NO | 2100-3172.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTBUSINESS IMPROVEMENT AND PROCESS OPTIMIZATIONNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | BUSINESS IMPROVEMENT AND PROCESS OPTIMIZATION | Non-RAMP | Non-RAMP | Non-RAMP | 347180.6295 | 0 | 0 | 0 | 403281.2095 | 294999.9996 | 303999.9996 | 312999.9996 | 321999.9996 | 1233999.9984 | 52180.6299 | -303999.9996 | -312999.9996 | -321999.9996 | -830718.7889 | 17.69% | -100% | -100% | -100% | -67.32% | NO | 1HR007.001 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTBUSINESS OPTIMIZATIONNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | BUSINESS OPTIMIZATION | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 127999.9992 | 132000 | 135999.9996 | 139999.9992 | 535999.998 | -127999.9992 | -132000 | -135999.9996 | -139999.9992 | -535999.998 | -100% | -100% | -100% | -100% | -100% | NO | 1HR007.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTDIVERSITY AND INCLUSIONNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | DIVERSITY AND INCLUSION | Non-RAMP | Non-RAMP | Non-RAMP | 518570.876 | 0 | 0 | 0 | 589338.606 | 625999.9992 | 645000 | 663999.9996 | 684000 | 2618999.9988 | -107429.1232 | -645000 | -663999.9996 | -684000 | -2029661.3928 | -17.16% | -100% | -100% | -100% | -77.5% | NO | 1HR004.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTDIVERSITY AND WORKFORCE MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | DIVERSITY AND WORKFORCE MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 2453930.9968 | 0 | 0 | 0 | 2943208.9168 | 3259999.9992 | 3357999.9996 | 3459000 | 3562999.9992 | 13639999.998 | -806069.0024 | -3357999.9996 | -3459000 | -3562999.9992 | -10696791.0812 | -24.73% | -100% | -100% | -100% | -78.42% | NO | 1HR005.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTDRUG AND ALCOHOL TESTING PROGRAMIncident Involving an EmployeeDrug & Alcohol Testing ProgramN/A | O&M | PEOPLE AND CULTURE DEPARTMENT | DRUG AND ALCOHOL TESTING PROGRAM | Incident Involving an Employee | Drug & Alcohol Testing Program | N/A | 166215.85 | 0 | 0 | 0 | 192571.7 | 138999.9996 | 142999.9992 | 147999.9996 | 151999.9992 | 581999.9976 | 27215.8504 | -142999.9992 | -147999.9996 | -151999.9992 | -389428.2976 | 19.58% | -100% | -100% | -100% | -66.91% | YES | 2100-3414.000 | NO | SDG&E-Risk-8
O&MPEOPLE AND CULTURE DEPARTMENTDRUG AND ALCOHOL TESTING PROGRAMNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | DRUG AND ALCOHOL TESTING PROGRAM | Non-RAMP | Non-RAMP | Non-RAMP | 194100.0029 | 0 | 0 | 0 | 237585.3129 | 105000 | 108000 | 111000 | 114999.9996 | 438999.9996 | 89100.0029 | -108000 | -111000 | -114999.9996 | -201414.6867 | 84.86% | -100% | -100% | -100% | -45.88% | YES | 2100-3414.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTEMPLOYEE CARE SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | EMPLOYEE CARE SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 1149043.5141 | 0 | 0 | 0 | 1196637.7741 | 1533000 | 1578999.9996 | 1626000 | 1674999.9996 | 6412999.9992 | -383956.4859 | -1578999.9996 | -1626000 | -1674999.9996 | -5216362.2251 | -25.05% | -100% | -100% | -100% | -81.34% | NO | 2100-3505.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTEXECUTIVE OFFICESIncident Involving an EmployeeUtilizing OSHA and Industry Best Practices and Industry BenchmarkingN/A | O&M | PEOPLE AND CULTURE DEPARTMENT | EXECUTIVE OFFICES | Incident Involving an Employee | Utilizing OSHA and Industry Best Practices and Industry Benchmarking | N/A | 1050689 | 0 | 0 | 0 | 2072533.94 | 0 | 0 | 0 | 0 | 0 | 1050689 | 0 | 0 | 0 | 2072533.94 | 100% | 100% | 100% | 100% | 100% | YES | 1HR008.000 | NO | SDG&E-Risk-8
O&MPEOPLE AND CULTURE DEPARTMENTEXECUTIVE OFFICESNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | EXECUTIVE OFFICES | Non-RAMP | Non-RAMP | Non-RAMP | 591082.765 | 0 | 0 | 0 | 580752.735 | 1203999.9996 | 1239999.9996 | 1276999.9992 | 1314999.9996 | 5035999.998 | -612917.2346 | -1239999.9996 | -1276999.9992 | -1314999.9996 | -4455247.263 | -50.91% | -100% | -100% | -100% | -88.47% | YES | 1HR008.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTHUMAN RESOURCESNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | HUMAN RESOURCES | Non-RAMP | Non-RAMP | Non-RAMP | 2730243.4355 | 0 | 0 | 0 | 3351099.5655 | 2829999.9996 | 2914999.9992 | 3001999.9992 | 3091999.9992 | 11838999.9972 | -99756.5641 | -2914999.9992 | -3001999.9992 | -3091999.9992 | -8487900.4317 | -3.525% | -100% | -100% | -100% | -71.69% | NO | 1HR003.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTLONG-TERM DISABILITY (LTD)Non-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | LONG-TERM DISABILITY (LTD) | Non-RAMP | Non-RAMP | Non-RAMP | 3895334.0001 | 0 | 0 | 0 | 4802925.3101 | 2490999.9996 | 2565999.9996 | 2643000 | 2721999.9996 | 10421999.9988 | 1404334.0005 | -2565999.9996 | -2643000 | -2721999.9996 | -5619074.6887 | 56.38% | -100% | -100% | -100% | -53.92% | NO | 1HR002.001 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTORGANIZATIONAL EFFECTIVENESSNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | ORGANIZATIONAL EFFECTIVENESS | Non-RAMP | Non-RAMP | Non-RAMP | 1759980.5616 | 0 | 0 | 0 | 2095927.7516 | 2052999.9996 | 2115000 | 2178000 | 2242999.9992 | 8588999.9988 | -293019.438 | -2115000 | -2178000 | -2242999.9992 | -6493072.2472 | -14.27% | -100% | -100% | -100% | -75.6% | YES | 1HR006.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTPEOPLE RESEARCHNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | PEOPLE RESEARCH | Non-RAMP | Non-RAMP | Non-RAMP | 193952.0974 | 0 | 0 | 0 | 233928.6074 | 0 | 0 | 0 | 0 | 0 | 193952.0974 | 0 | 0 | 0 | 233928.6074 | 100% | 100% | 100% | 100% | 100% | NO | 2100-3834.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTTOTAL DISABILITYNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | TOTAL DISABILITY | Non-RAMP | Non-RAMP | Non-RAMP | 286948.45 | 0 | 0 | 0 | 357234.07 | 325999.9992 | 336000 | 345999.9996 | 355999.9992 | 1363999.998 | -39051.5492 | -336000 | -345999.9996 | -355999.9992 | -1006765.928 | -11.98% | -100% | -100% | -100% | -73.81% | NO | 1HR001.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTVP - PEOPLE AND CULTURENon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | VP - PEOPLE AND CULTURE | Non-RAMP | Non-RAMP | Non-RAMP | 351576.2059 | 0 | 0 | 0 | 506648.3059 | 0 | 0 | 0 | 0 | 0 | 351576.2059 | 0 | 0 | 0 | 506648.3059 | 100% | 100% | 100% | 100% | 100% | YES | 1HR000.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTWELLNESS PROGRAMSIncident Involving an EmployeeEmployee Wellness ProgramsOverall | O&M | PEOPLE AND CULTURE DEPARTMENT | WELLNESS PROGRAMS | Incident Involving an Employee | Employee Wellness Programs | Overall | 128249.1025 | 0 | 0 | 0 | 128249.1025 | 195000 | 201000 | 207000 | 213000 | 816000 | -66750.8975 | -201000 | -207000 | -213000 | -687750.8975 | -34.23% | -100% | -100% | -100% | -84.28% | YES | 2100-3506.000 | NO | SDG&E-Risk-8
O&MPEOPLE AND CULTURE DEPARTMENTWELLNESS PROGRAMSNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | WELLNESS PROGRAMS | Non-RAMP | Non-RAMP | Non-RAMP | 3.5257 | 0 | 0 | 0 | 27462.2257 | 24000 | 24999.9996 | 25999.9992 | 27000 | 101999.9988 | -23996.4743 | -24999.9996 | -25999.9992 | -27000 | -74537.7731 | -99.99% | -100% | -100% | -100% | -73.08% | YES | 2100-3506.000 | NO | NR
O&MPEOPLE AND CULTURE DEPARTMENTWORKERS' COMPENSATIONNon-RAMPNon-RAMPNon-RAMP | O&M | PEOPLE AND CULTURE DEPARTMENT | WORKERS' COMPENSATION | Non-RAMP | Non-RAMP | Non-RAMP | 3366253.67 | 0 | 0 | 0 | 4165677.13 | 3828000 | 3942999.9996 | 4060999.9992 | 4182999.9996 | 16014999.9984 | -461746.33 | -3942999.9996 | -4060999.9992 | -4182999.9996 | -11849322.8684 | -12.06% | -100% | -100% | -100% | -73.99% | NO | 1HR002.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESCORPORATE REAL ESTATENon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | CORPORATE REAL ESTATE | Non-RAMP | Non-RAMP | Non-RAMP | 769602.5676 | 0 | 0 | 0 | 911156.3476 | 666999.9996 | 687000 | 708000 | 729000 | 2790999.9996 | 102602.568 | -687000 | -708000 | -729000 | -1879843.652 | 15.38% | -100% | -100% | -100% | -67.35% | NO | 2100-3030.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESFACILITES OPS - SHARED SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | FACILITES OPS - SHARED SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 4256012.9692 | 0 | 0 | 0 | 4777711.3392 | 4351999.9992 | 4482999.9996 | 4617000 | 4755999.9996 | 18207999.9984 | -95987.03 | -4482999.9996 | -4617000 | -4755999.9996 | -13430288.6592 | -2.206% | -100% | -100% | -100% | -73.76% | YES | 2100-3323.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESFACILITIES CAPITAL PROGRAMSNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | FACILITIES CAPITAL PROGRAMS | Non-RAMP | Non-RAMP | Non-RAMP | 78037.2805 | 0 | 0 | 0 | 117406.8205 | 165000 | 169999.9992 | 174999.9996 | 180000 | 689999.9988 | -86962.7195 | -169999.9992 | -174999.9996 | -180000 | -572593.1783 | -52.7% | -100% | -100% | -100% | -82.98% | YES | 2100-3025.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESHQ FACILITIES MAINTENANCENon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | HQ FACILITIES MAINTENANCE | Non-RAMP | Non-RAMP | Non-RAMP | 1507901.0958 | 0 | 0 | 0 | 2121320.2658 | 1395000 | 1437000 | 1479999.9996 | 1524000 | 5835999.9996 | 112901.0958 | -1437000 | -1479999.9996 | -1524000 | -3714679.7338 | 8.093% | -100% | -100% | -100% | -63.65% | YES | 2100-0708.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESREAL ESTATE PLANNINGNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | REAL ESTATE PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | 1165192.923 | 0 | 0 | 0 | 1279626.023 | 1449999.9996 | 1494000 | 1539000 | 1584999.9996 | 6067999.9992 | -284807.0766 | -1494000 | -1539000 | -1584999.9996 | -4788373.9762 | -19.64% | -100% | -100% | -100% | -78.91% | YES | 2100-0706.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESSDG&E FACILITIES OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E FACILITIES OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 4925637.5612 | 0 | 0 | 0 | 5999139.3112 | 5904999.9996 | 6081999.9996 | 6264000 | 6451999.9992 | 24702999.9984 | -979362.4384 | -6081999.9996 | -6264000 | -6451999.9992 | -18703860.6872 | -16.59% | -100% | -100% | -100% | -75.71% | YES | 1RE001.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESSDG&E RENTSNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E RENTS | Non-RAMP | Non-RAMP | Non-RAMP | 6108159.43 | 0 | 0 | 0 | 7813463.01 | 5451000 | 5614999.9992 | 5782999.9992 | 5955999.9996 | 22804999.998 | 657159.43 | -5614999.9992 | -5782999.9992 | -5955999.9996 | -14991536.988 | 12.06% | -100% | -100% | -100% | -65.74% | NO | 1RE003.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESSDG&E SECURITYNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E SECURITY | Non-RAMP | Non-RAMP | Non-RAMP | 1858090.4599 | 0 | 0 | 0 | 2265115.8649 | 2044999.9992 | 2106999.9996 | 2169999.9996 | 2235000 | 8556999.9984 | -186909.5393 | -2106999.9996 | -2169999.9996 | -2235000 | -6291884.1335 | -9.14% | -100% | -100% | -100% | -73.53% | YES | 1RE004.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESSDG&E SECURITYPhysical SecurityContract SecurityN/A | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SDG&E SECURITY | Physical Security | Contract Security | N/A | 1858090.4599 | 0 | 0 | 0 | 2265115.8649 | 2044999.9992 | 2106000 | 2169000 | 2233999.9992 | 8553999.9984 | -186909.5393 | -2106000 | -2169000 | -2233999.9992 | -6288884.1335 | -9.14% | -100% | -100% | -100% | -73.52% | YES | 1RE004.000 | NO | SDG&E-CFF-5
O&MREAL ESTATE, LAND SERVICES & FACILITIESSHARED SERVICES OPEX MAINTNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SHARED SERVICES OPEX MAINT | Non-RAMP | Non-RAMP | Non-RAMP | 3392903.6378 | 0 | 0 | 0 | 4407254.7178 | 3261000 | 3358999.9992 | 3459999.9996 | 3564000 | 13643999.9988 | 131903.6378 | -3358999.9992 | -3459999.9996 | -3564000 | -9236745.281 | 4.045% | -100% | -100% | -100% | -67.7% | YES | 2100-0700.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESSHARED SERVICES RENTSNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | SHARED SERVICES RENTS | Non-RAMP | Non-RAMP | Non-RAMP | 13055332.7 | 0 | 0 | 0 | 15874758.05 | 12192999.9996 | 12558999.9996 | 12936000 | 13323999.9996 | 51011999.9988 | 862332.7004 | -12558999.9996 | -12936000 | -13323999.9996 | -35137241.9488 | 7.072% | -100% | -100% | -100% | -68.88% | NO | 2100-4066.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESTRIBAL RELATIONS & LAND SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | TRIBAL RELATIONS & LAND SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 1476463.38 | 0 | 0 | 0 | 1760898.62 | 1029999.9996 | 1060999.9992 | 1092999.9996 | 1125999.9996 | 4309999.998 | 446463.3804 | -1060999.9992 | -1092999.9996 | -1125999.9996 | -2549101.378 | 43.35% | -100% | -100% | -100% | -59.14% | YES | 1RE002.000 | NO | NR
O&MREAL ESTATE, LAND SERVICES & FACILITIESVP OPERATIONS SUPPORTNon-RAMPNon-RAMPNon-RAMP | O&M | REAL ESTATE, LAND SERVICES & FACILITIES | VP OPERATIONS SUPPORT | Non-RAMP | Non-RAMP | Non-RAMP | 462486.7581 | 0 | 0 | 0 | 578284.7481 | 397999.9992 | 409999.9992 | 421999.9992 | 435000 | 1664999.9976 | 64486.7589 | -409999.9992 | -421999.9992 | -435000 | -1086715.2495 | 16.2% | -100% | -100% | -100% | -65.27% | NO | 2100-3588.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSASSET MANAGEMENTAsset ManagementAIM (Gov, Strat, AIP)N/A | O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Asset Management | AIM (Gov, Strat, AIP) | N/A | 421606.1896 | 0 | 0 | 0 | 492678.9727 | 720000 | 741000 | 762999.9996 | 786000 | 3009999.9996 | -298393.8104 | -741000 | -762999.9996 | -786000 | -2517321.0269 | -41.44% | -100% | -100% | -100% | -83.63% | YES | 1SM003.000 | NO | SDG&E-CFF-1
O&MSAFETY MANAGEMENT SYSTEMSASSET MANAGEMENTAsset ManagementAsset Data Syst & Rec Mgt (Data Integration)N/A | O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Asset Management | Asset Data Syst & Rec Mgt (Data Integration) | N/A | 194032.9362 | 0 | 0 | 0 | 194032.9362 | 168999.9996 | 174000 | 178999.9992 | 183999.9996 | 705999.9984 | 25032.9366 | -174000 | -178999.9992 | -183999.9996 | -511967.0622 | 14.81% | -100% | -100% | -100% | -72.52% | YES | 1SM003.000 | NO | SDG&E-CFF-1
O&MSAFETY MANAGEMENT SYSTEMSASSET MANAGEMENTAsset ManagementAsset Data Syst & Rec Mgt (Gov, Quality, Rec Mgt)N/A | O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Asset Management | Asset Data Syst & Rec Mgt (Gov, Quality, Rec Mgt) | N/A | 62564.1104 | 0 | 0 | 0 | 89067.1404 | 0 | 0 | 0 | 0 | 0 | 62564.1104 | 0 | 0 | 0 | 89067.1404 | 100% | 100% | 100% | 100% | 100% | YES | 1SM003.000 | NO | SDG&E-CFF-1
O&MSAFETY MANAGEMENT SYSTEMSASSET MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | ASSET MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 0.07799 | 0 | 0 | 0 | 717.9849 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 97999.998 | -22999.9212 | -24000 | -24999.9996 | -25999.9992 | -97282.0131 | -100% | -100% | -100% | -100% | -99.27% | YES | 1SM003.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSBUSINESS TECHNOLOGY SOLUTIONSNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | BUSINESS TECHNOLOGY SOLUTIONS | Non-RAMP | Non-RAMP | Non-RAMP | 2217214.949 | 0 | 0 | 0 | 2742546.529 | 2704999.9992 | 2785999.9992 | 2869999.9992 | 2955999.9996 | 11316999.9972 | -487785.0502 | -2785999.9992 | -2869999.9992 | -2955999.9996 | -8574453.4682 | -18.03% | -100% | -100% | -100% | -75.77% | YES | 1SM004.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSENERGY RISK MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | ENERGY RISK MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 1730808.9495 | 0 | 0 | 0 | 2001857.8295 | 1668000 | 1717999.9992 | 1770000 | 1822999.9992 | 6978999.9984 | 62808.9495 | -1717999.9992 | -1770000 | -1822999.9992 | -4977142.1689 | 3.766% | -100% | -100% | -100% | -71.32% | NO | 1SM006.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSENTERPRISE RISK MANAGEMENTAsset ManagementAIMDAT (Data Analytics)N/A | O&M | SAFETY MANAGEMENT SYSTEMS | ENTERPRISE RISK MANAGEMENT | Asset Management | AIMDAT (Data Analytics) | N/A | 159033.6566 | 0 | 0 | 0 | 188559.6566 | 207000 | 213000 | 219000 | 225999.9996 | 864999.9996 | -47966.3434 | -213000 | -219000 | -225999.9996 | -676440.343 | -23.17% | -100% | -100% | -100% | -78.2% | YES | 1SM005.000 | NO | SDG&E-CFF-1
O&MSAFETY MANAGEMENT SYSTEMSENTERPRISE RISK MANAGEMENTNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | ENTERPRISE RISK MANAGEMENT | Non-RAMP | Non-RAMP | Non-RAMP | 3264699.9446 | 0 | 0 | 0 | 4481374.7446 | 4569999.9996 | 4707000 | 4848999.9996 | 4993999.9992 | 19119999.9984 | -1305300.055 | -4707000 | -4848999.9996 | -4993999.9992 | -14638625.2538 | -28.56% | -100% | -100% | -100% | -76.56% | YES | 1SM005.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Non-RAMP | Non-RAMP | Non-RAMP | 131645.3701 | 0 | 0 | 0 | 131645.3701 | 165000 | 169999.9992 | 174999.9996 | 178999.9992 | 688999.998 | -33354.6299 | -169999.9992 | -174999.9996 | -178999.9992 | -557354.6279 | -20.21% | -100% | -100% | -100% | -80.89% | YES | 1SM001.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMSafety Management SystemDevelopment and Implementation of a Strong Management of Change PlatformN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Development and Implementation of a Strong Management of Change Platform | N/A | 0 | 0 | 0 | 0 | 0 | 84999.9996 | 87999.9996 | 90999.9996 | 93999.9996 | 357999.9984 | -84999.9996 | -87999.9996 | -90999.9996 | -93999.9996 | -357999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1SM001.000 | NO | SDG&E-CFF-7
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMSafety Management SystemDevelopment and Implementation of an Enterprise-Wide SMSN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Development and Implementation of an Enterprise-Wide SMS | N/A | 604691.6724 | 0 | 0 | 0 | 772503.9024 | 925999.9992 | 952999.9992 | 981999.9996 | 1011000 | 3871999.998 | -321308.3268 | -952999.9992 | -981999.9996 | -1011000 | -3099496.0956 | -34.7% | -100% | -100% | -100% | -80.05% | YES | 1SM001.000 | NO | SDG&E-CFF-7
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMSafety Management SystemEnhanced Documentation and Recordkeeping PracticesN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Enhanced Documentation and Recordkeeping Practices | N/A | 0 | 0 | 0 | 0 | 0 | 27999.9996 | 28999.9992 | 30000 | 30999.9996 | 117999.9984 | -27999.9996 | -28999.9992 | -30000 | -30999.9996 | -117999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1SM001.000 | NO | SDG&E-CFF-7
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMSafety Management SystemEnhanced Employee and Stakeholder Engagement, including SMS Competence, Awareness, Survey and TrainingN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Enhanced Employee and Stakeholder Engagement, including SMS Competence, Awareness, Survey and Training | N/A | 0 | 0 | 0 | 0 | 0 | 27999.9996 | 28999.9992 | 30000 | 30999.9996 | 117999.9984 | -27999.9996 | -28999.9992 | -30000 | -30999.9996 | -117999.9984 | -100% | -100% | -100% | -100% | -100% | YES | 1SM001.000 | NO | SDG&E-CFF-7
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMSafety Management SystemEnhanced Stakeholder Feedback and Key Performance Indicator Monitoring, Tracking, and ReportingN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Enhanced Stakeholder Feedback and Key Performance Indicator Monitoring, Tracking, and Reporting | N/A | 0 | 0 | 0 | 0 | 0 | 57000 | 58999.9992 | 60999.9996 | 63000 | 239999.9988 | -57000 | -58999.9992 | -60999.9996 | -63000 | -239999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1SM001.000 | NO | SDG&E-CFF-7
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMSafety Management SystemIntegration of New Technology and Enhanced Data and Analytics Capabilities for Continuous Safety ImprovementN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | Integration of New Technology and Enhanced Data and Analytics Capabilities for Continuous Safety Improvement | N/A | 0 | 0 | 0 | 0 | 0 | 240000 | 246999.9996 | 252999.9996 | 261000 | 1000999.9992 | -240000 | -246999.9996 | -252999.9996 | -261000 | -1000999.9992 | -100% | -100% | -100% | -100% | -100% | YES | 1SM001.000 | NO | SDG&E-CFF-7
O&MSAFETY MANAGEMENT SYSTEMSSAFETY MANAGEMENT SYSTEMSafety Management SystemSMS Program Benchmarking, Measurement, and Maturity Assessment for Continuous ImprovementN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY MANAGEMENT SYSTEM | Safety Management System | SMS Program Benchmarking, Measurement, and Maturity Assessment for Continuous Improvement | N/A | 0 | 0 | 0 | 0 | 0 | 57000 | 58999.9992 | 60999.9996 | 63000 | 239999.9988 | -57000 | -58999.9992 | -60999.9996 | -63000 | -239999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1SM001.000 | NO | SDG&E-CFF-7
O&MSAFETY MANAGEMENT SYSTEMSSAFETYIncident Involving a ContractorContractor Oversight ProgramOverall | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving a Contractor | Contractor Oversight Program | Overall | 1044451.2853 | 0 | 0 | 0 | 1213953.6293 | 1206000 | 1242000 | 1278999.9996 | 1317000 | 5043999.9996 | -161548.7147 | -1242000 | -1278999.9996 | -1317000 | -3830046.3703 | -13.4% | -100% | -100% | -100% | -75.93% | YES | 1SM002.002 | NO | SDG&E-Risk-4
O&MSAFETY MANAGEMENT SYSTEMSSAFETYIncident Involving an EmployeeBreak/rest trailers with filtered air systemsNon-Vehicle incident | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Break/rest trailers with filtered air systems | Non-Vehicle incident | -0.58655 | 0 | 0 | 0 | 21865.9974 | 169999.9992 | 174999.9996 | 180000 | 184999.9992 | 709999.998 | -170000.5857 | -174999.9996 | -180000 | -184999.9992 | -688134.0005 | -100% | -100% | -100% | -100% | -96.92% | YES | 1SM002.001 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSAFETYIncident Involving an EmployeeDesigner support to update & convert safety trainingN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Designer support to update & convert safety training | N/A | -0.03905 | 0 | 0 | 0 | 4099.9455 | 31999.9992 | 33000 | 33999.9996 | 34999.9992 | 133999.998 | -32000.0383 | -33000 | -33999.9996 | -34999.9992 | -129900.0525 | -100% | -100% | -100% | -100% | -96.94% | YES | 1SM002.001 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSAFETYIncident Involving an EmployeeEmployee Wildfire Smoke Protection Cal/OSHA emergency regulationN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Employee Wildfire Smoke Protection Cal/OSHA emergency regulation | N/A | 21444.8069 | 0 | 0 | 0 | 24178.1299 | 18000 | 18999.9996 | 19999.9992 | 21000 | 77999.9988 | 3444.8069 | -18999.9996 | -19999.9992 | -21000 | -53821.8689 | 19.14% | -100% | -100% | -100% | -69% | YES | 1SM002.001 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSAFETYIncident Involving an EmployeeEnhanced Mandatory Employee Training (OSHA): Certified Occupational Safety Specialist, Certified Utility Safety Professional; Certified Safety ProfessionalOverall | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Enhanced Mandatory Employee Training (OSHA): Certified Occupational Safety Specialist, Certified Utility Safety Professional; Certified Safety Professional | Overall | 8041.0288 | 0 | 0 | 0 | 9407.6903 | 6999.9996 | 6999.9996 | 6999.9996 | 6999.9996 | 27999.9984 | 1041.0292 | -6999.9996 | -6999.9996 | -6999.9996 | -18592.3081 | 14.87% | -100% | -100% | -100% | -66.4% | YES | 1SM002.001 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSAFETYIncident Involving an EmployeeMandatory Employee Health and Safety Training Programs and Standardized PoliciesOverall | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Mandatory Employee Health and Safety Training Programs and Standardized Policies | Overall | 743842.1573 | 0 | 0 | 0 | 825841.8473 | 627999.9996 | 645999.9996 | 664999.9992 | 684999.9996 | 2623999.998 | 115842.1577 | -645999.9996 | -664999.9992 | -684999.9996 | -1798158.1507 | 18.45% | -100% | -100% | -100% | -68.53% | YES | 1SM002.001 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSAFETYIncident Involving an EmployeeRespiratory protection for wildfire smoke particulatesOverall | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Incident Involving an Employee | Respiratory protection for wildfire smoke particulates | Overall | 0 | 0 | 0 | 0 | 0 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | 7999.9968 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -7999.9968 | -100% | -100% | -100% | -100% | -100% | YES | 1SM002.001 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSAFETYNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Non-RAMP | Non-RAMP | Non-RAMP | 122340.84 | 0 | 0 | 0 | 123216.51 | 211999.9992 | 217999.9992 | 225000 | 231999.9996 | 886999.998 | -89659.1592 | -217999.9992 | -225000 | -231999.9996 | -763783.488 | -42.29% | -100% | -100% | -100% | -86.11% | YES | 1SM002.003 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSSAFETYNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Non-RAMP | Non-RAMP | Non-RAMP | 0.3473 | 0 | 0 | 0 | 42375.9333 | 249999.9996 | 258000 | 265999.9992 | 273999.9996 | 1047999.9984 | -249999.6523 | -258000 | -265999.9992 | -273999.9996 | -1005624.0651 | -100% | -100% | -100% | -100% | -95.96% | YES | 1SM002.002 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSSAFETYNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Non-RAMP | Non-RAMP | Non-RAMP | 0.76602 | 0 | 0 | 0 | 24600.673 | 183999.9996 | 189999.9996 | 195999.9996 | 201999.9996 | 771999.9984 | -183999.2336 | -189999.9996 | -195999.9996 | -201999.9996 | -747399.3254 | -100% | -100% | -100% | -100% | -96.81% | YES | 1SM002.001 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSSAFETYNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | SAFETY | Non-RAMP | Non-RAMP | Non-RAMP | 583992.6365 | 0 | 0 | 0 | 745541.6165 | 550999.9992 | 567999.9996 | 585000 | 603000 | 2306999.9988 | 32992.6373 | -567999.9996 | -585000 | -603000 | -1561458.3823 | 5.988% | -100% | -100% | -100% | -67.68% | YES | 1SM002.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSSDG&E FIELD SAFETYIncident Involving an EmployeeSafe Driving ProgramsVehicle Incident | O&M | SAFETY MANAGEMENT SYSTEMS | SDG&E FIELD SAFETY | Incident Involving an Employee | Safe Driving Programs | Vehicle Incident | 24253.34 | 0 | 0 | 0 | 24253.34 | 100999.9992 | 103999.9992 | 106999.9992 | 109999.9992 | 421999.9968 | -76746.6592 | -103999.9992 | -106999.9992 | -109999.9992 | -397746.6568 | -75.99% | -100% | -100% | -100% | -94.25% | YES | 2100-0214.000 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSDG&E FIELD SAFETYIncident Involving an EmployeeStrong Safety CultureN/A | O&M | SAFETY MANAGEMENT SYSTEMS | SDG&E FIELD SAFETY | Incident Involving an Employee | Strong Safety Culture | N/A | 368550 | 0 | 0 | 0 | 368550 | 252000 | 259999.9992 | 267999.9996 | 276000 | 1055999.9988 | 116550 | -259999.9992 | -267999.9996 | -276000 | -687449.9988 | 46.25% | -100% | -100% | -100% | -65.1% | YES | 2100-0214.000 | NO | SDG&E-Risk-8
O&MSAFETY MANAGEMENT SYSTEMSSDG&E FIELD SAFETYNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | SDG&E FIELD SAFETY | Non-RAMP | Non-RAMP | Non-RAMP | 1087915.4014 | 0 | 0 | 0 | 1271254.6214 | 1020999.9996 | 1050999.9996 | 1081999.9992 | 1114999.9992 | 4268999.9976 | 66915.4018 | -1050999.9996 | -1081999.9992 | -1114999.9992 | -2997745.3762 | 6.554% | -100% | -100% | -100% | -70.22% | YES | 2100-0214.000 | NO | NR
O&MSAFETY MANAGEMENT SYSTEMSVP- RISK MGMT & CHF COMPL OFCRNon-RAMPNon-RAMPNon-RAMP | O&M | SAFETY MANAGEMENT SYSTEMS | VP- RISK MGMT & CHF COMPL OFCR | Non-RAMP | Non-RAMP | Non-RAMP | 527359.6817 | 0 | 0 | 0 | 1185042.7218 | 471000 | 484999.9992 | 499999.9992 | 514999.9992 | 1970999.9976 | 56359.6818 | -484999.9992 | -499999.9992 | -514999.9992 | -785957.2758 | 11.97% | -100% | -100% | -100% | -39.88% | YES | 1SM000.000 | NO | NR
O&MSDG&E ENERGY PROCUREMENTBACK OFFICENon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENERGY PROCUREMENT | BACK OFFICE | Non-RAMP | Non-RAMP | Non-RAMP | 4606002.58 | 0 | 0 | 0 | 5729031.85 | 4008999.9996 | 4128999.9996 | 4252999.9992 | 4380999.9996 | 16771999.998 | 597002.5804 | -4128999.9996 | -4252999.9992 | -4380999.9996 | -11042968.148 | 14.89% | -100% | -100% | -100% | -65.84% | YES | 1EP003.000 | NO | NR
O&MSDG&E ENERGY PROCUREMENTENERGY SUPPLY & DISPATCHNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENERGY PROCUREMENT | ENERGY SUPPLY & DISPATCH | Non-RAMP | Non-RAMP | Non-RAMP | 2205089.4608 | 0 | 0 | 0 | 2663094.5108 | 2434999.9992 | 2508000 | 2583000 | 2659999.9992 | 10185999.9984 | -229910.5384 | -2508000 | -2583000 | -2659999.9992 | -7522905.4876 | -9.442% | -100% | -100% | -100% | -73.86% | YES | 1EP002.000 | NO | NR
O&MSDG&E ENERGY PROCUREMENTORIGINATION & PORTFOLIO DESIGNNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENERGY PROCUREMENT | ORIGINATION & PORTFOLIO DESIGN | Non-RAMP | Non-RAMP | Non-RAMP | 1755781.9505 | 0 | 0 | 0 | 2037989.1905 | 2799000 | 2883000 | 2968999.9992 | 3057999.9996 | 11708999.9988 | -1043218.0495 | -2883000 | -2968999.9992 | -3057999.9996 | -9671010.8083 | -37.27% | -100% | -100% | -100% | -82.59% | YES | 1EP001.000 | NO | NR
O&MSDG&E ENERGY PROCUREMENTRESOURCE PLANNINGNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENERGY PROCUREMENT | RESOURCE PLANNING | Non-RAMP | Non-RAMP | Non-RAMP | 780113.0635 | 0 | 0 | 0 | 1065358.2435 | 1359000 | 1399999.9992 | 1441999.9992 | 1485000 | 5685999.9984 | -578886.9365 | -1399999.9992 | -1441999.9992 | -1485000 | -4620641.7549 | -42.6% | -100% | -100% | -100% | -81.26% | YES | 1EP004.000 | NO | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSEG -SONGS WKP_GRP_1Non-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | EG -SONGS WKP_GRP_1 | Non-RAMP | Non-RAMP | Non-RAMP | 1142922.89 | 0 | 0 | 0 | 1694426.68 | 1575000 | 1575000 | 1575000 | 1575000 | 6300000 | -432077.11 | -1575000 | -1575000 | -1575000 | -4605573.32 | -27.43% | -100% | -100% | -100% | -73.1% | YES | 1EV003.000 | YES | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSENVIRONMENTAL SDGE NSS COST CENTERNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | ENVIRONMENTAL SDGE NSS COST CENTER | Non-RAMP | Non-RAMP | Non-RAMP | 7132422.738 | 0 | 0 | 0 | 8917508.778 | 7969999.9992 | 8208999.9996 | 8454999.9996 | 8709000 | 33342999.9984 | -837577.2612 | -8208999.9996 | -8454999.9996 | -8709000 | -24425491.2204 | -10.51% | -100% | -100% | -100% | -73.26% | YES | 1EV000.000 | NO | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSRNERBA-AB32 FEES-ELECTRICNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-AB32 FEES-ELECTRIC | Non-RAMP | Non-RAMP | Non-RAMP | 652150 | 0 | 0 | 0 | 652150 | 472999.9992 | 486999.9996 | 501999.9996 | 516999.9996 | 1978999.998 | 179150.0008 | -486999.9996 | -501999.9996 | -516999.9996 | -1326849.998 | 37.88% | -100% | -100% | -100% | -67.05% | NO | 1EV001.002 | YES | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSRNERBA-AB32 FEES-GASNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-AB32 FEES-GAS | Non-RAMP | Non-RAMP | Non-RAMP | 1367841 | 0 | 0 | 0 | 1367841 | 1029000 | 1059999.9996 | 1092000 | 1125000 | 4305999.9996 | 338841 | -1059999.9996 | -1092000 | -1125000 | -2938158.9996 | 32.93% | -100% | -100% | -100% | -68.23% | NO | 1EV002.002 | YES | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSRNERBA-LDARNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-LDAR | Non-RAMP | Non-RAMP | Non-RAMP | 2077717.4665 | 0 | 0 | 0 | 2292941.6165 | 66999.9996 | 69000 | 70999.9992 | 72999.9996 | 279999.9984 | 2010717.4669 | -69000 | -70999.9992 | -72999.9996 | 2012941.6181 | 3001% | -100% | -100% | -100% | 718.9% | NO | 1EV002.003 | YES | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSRNERBA-MS4-ELECTRICNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-MS4-ELECTRIC | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 24000 | -6000 | -6000 | -6000 | -6000 | -24000 | -100% | -100% | -100% | -100% | -100% | NO | 1EV001.003 | YES | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSRNERBA-MS4-GASNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-MS4-GAS | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 24000 | -6000 | -6000 | -6000 | -6000 | -24000 | -100% | -100% | -100% | -100% | -100% | NO | 1EV002.004 | YES | NR
O&MSDG&E ENVIRONMENTAL SERVICES AND SONGSRNERBA-SUBPART WNon-RAMPNon-RAMPNon-RAMP | O&M | SDG&E ENVIRONMENTAL SERVICES AND SONGS | RNERBA-SUBPART W | Non-RAMP | Non-RAMP | Non-RAMP | 0 | 0 | 0 | 0 | 0 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | 7999.9968 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -7999.9968 | -100% | -100% | -100% | -100% | -100% | NO | 1EV002.001 | YES | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYCUSTOMER PROGRAMS & SUPPORT SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | CUSTOMER PROGRAMS & SUPPORT SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 2608587.1099 | 0 | 0 | 0 | 3170228.6398 | 1311999.9996 | 1350999.9996 | 1392000 | 1434000 | 5488999.9992 | 1296587.1102 | -1350999.9996 | -1392000 | -1434000 | -2318771.3594 | 98.83% | -100% | -100% | -100% | -42.24% | NO | 1SS009.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYELECTRIC PORTFOLIONon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | ELECTRIC PORTFOLIO | Non-RAMP | Non-RAMP | Non-RAMP | 3224865.0809 | 0 | 0 | 0 | 3650714.5109 | 2221999.9992 | 2289000 | 2358000 | 2428999.9992 | 9297999.9984 | 1002865.0816 | -2289000 | -2358000 | -2428999.9992 | -5647285.4875 | 45.13% | -100% | -100% | -100% | -60.74% | NO | 1SS006.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYGAS PORTFOLIONon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | GAS PORTFOLIO | Non-RAMP | Non-RAMP | Non-RAMP | 716512.3124 | 0 | 0 | 0 | 846292.3224 | 0 | 0 | 0 | 0 | 0 | 716512.3124 | 0 | 0 | 0 | 846292.3224 | 100% | 100% | 100% | 100% | 100% | NO | 1SSNEW.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYIT & TELECOM PORTFOLIO - SDG&ENon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | IT & TELECOM PORTFOLIO - SDG&E | Non-RAMP | Non-RAMP | Non-RAMP | 3749466.1833 | 0 | 0 | 0 | 4376933.2333 | 2151000 | 2215999.9992 | 2281999.9992 | 2349999.9996 | 8998999.998 | 1598466.1833 | -2215999.9992 | -2281999.9992 | -2349999.9996 | -4622066.7647 | 74.31% | -100% | -100% | -100% | -51.36% | NO | 2100-3332.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYLOGISTICS SHOPS SOUTH - PURCHASING POOLNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | LOGISTICS SHOPS SOUTH - PURCHASING POOL | Non-RAMP | Non-RAMP | Non-RAMP | 4280021.8157 | 0 | 0 | 0 | 5565133.4857 | 1290999.9996 | 1329999.9996 | 1369999.9992 | 1410999.9996 | 5401999.998 | 2989021.8161 | -1329999.9996 | -1369999.9992 | -1410999.9996 | 163133.4877 | 231.5% | -100% | -100% | -100% | 3.02% | NO | 1SS004.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYLOGISTICS SHOPS SOUTH - WAREHOUSE POOLNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | LOGISTICS SHOPS SOUTH - WAREHOUSE POOL | Non-RAMP | Non-RAMP | Non-RAMP | 9005204.0371 | 0 | 0 | 0 | 10596660.5471 | 7624999.9992 | 7854000 | 8089999.9992 | 8332999.9992 | 31901999.9976 | 1380204.0379 | -7854000 | -8089999.9992 | -8332999.9992 | -21305339.4505 | 18.1% | -100% | -100% | -100% | -66.78% | YES | 1SS001.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYOFFICE SERVICES - NON-SHARED SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | OFFICE SERVICES - NON-SHARED SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 3471548.6 | 0 | 0 | 0 | 3857824.83 | 3363000 | 3463999.9992 | 3567999.9996 | 3675000 | 14069999.9988 | 108548.6 | -3463999.9992 | -3567999.9996 | -3675000 | -10212175.1688 | 3.228% | -100% | -100% | -100% | -72.58% | YES | 1SS003.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYOFFICE SERVICES - SHARED SERVICESNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | OFFICE SERVICES - SHARED SERVICES | Non-RAMP | Non-RAMP | Non-RAMP | 487969.7775 | 0 | 0 | 0 | 839481.6575 | 564999.9996 | 582000 | 598999.9992 | 616999.9992 | 2362999.998 | -77030.2221 | -582000 | -598999.9992 | -616999.9992 | -1523518.3405 | -13.63% | -100% | -100% | -100% | -64.47% | NO | 2100-3407.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYSTRATEGY & SUPPLY CHAIN SUSTAINABILITYNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | STRATEGY & SUPPLY CHAIN SUSTAINABILITY | Non-RAMP | Non-RAMP | Non-RAMP | 2485307.8941 | 0 | 0 | 0 | 2962016.0841 | 858000 | 883999.9992 | 910999.9992 | 937999.9992 | 3590999.9976 | 1627307.8941 | -883999.9992 | -910999.9992 | -937999.9992 | -628983.9135 | 189.7% | -100% | -100% | -100% | -17.52% | NO | 1SS007.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYSUPPLIER DIVERSITYNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SUPPLIER DIVERSITY | Non-RAMP | Non-RAMP | Non-RAMP | 939748.7624 | 0 | 0 | 0 | 1162907.6024 | 940999.9992 | 969000 | 997999.9992 | 1027999.9992 | 3935999.9976 | -1251.2368 | -969000 | -997999.9992 | -1027999.9992 | -2773092.3952 | -0.133% | -100% | -100% | -100% | -70.45% | NO | 1SS005.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYSUPPLY OPERATIONSNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | SUPPLY OPERATIONS | Non-RAMP | Non-RAMP | Non-RAMP | 611476.8424 | 0 | 0 | 0 | 648138.0524 | 1476999.9996 | 1521000 | 1566999.9996 | 1614000 | 6178999.9992 | -865523.1572 | -1521000 | -1566999.9996 | -1614000 | -5530861.9468 | -58.6% | -100% | -100% | -100% | -89.51% | NO | 2100-3331.000 | NO | NR
O&MSUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITYTECHNOLOGY, INTELLIGENCE, POLICY & SOLUTIONSNon-RAMPNon-RAMPNon-RAMP | O&M | SUPPLY MGT, LOGISTICS, & SUPPLIER DIVERSITY | TECHNOLOGY, INTELLIGENCE, POLICY & SOLUTIONS | Non-RAMP | Non-RAMP | Non-RAMP | 2385703.2272 | 0 | 0 | 0 | 3287718.6772 | 1521000 | 1566999.9996 | 1614000 | 1662000 | 6363999.9996 | 864703.2272 | -1566999.9996 | -1614000 | -1662000 | -3076281.3224 | 56.85% | -100% | -100% | -100% | -48.34% | NO | 2100-3016.000 | NO | NR
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentDist Syst InspectCMP 5 Yr Detail InspectTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist Syst InspectCMP 5 Yr Detail Inspect | Tier 2 | 201991.1097 | 0 | 0 | 0 | 201991.1097 | 132000 | 135999.9996 | 139999.9992 | 144000 | 551999.9988 | 69991.1097 | -135999.9996 | -139999.9992 | -144000 | -350008.8891 | 53.02% | -100% | -100% | -100% | -63.41% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentDist Syst InspectCMP 5 Yr Detail InspectTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist Syst InspectCMP 5 Yr Detail Inspect | Tier 3 | 336532.9768 | 0 | 0 | 0 | 336532.9768 | 225000 | 231999.9996 | 238999.9992 | 246000 | 941999.9988 | 111532.9768 | -231999.9996 | -238999.9992 | -246000 | -605467.022 | 49.57% | -100% | -100% | -100% | -64.27% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentDist System Inspect CMP Annual PatrolTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspect CMP Annual Patrol | Tier 2 | 154243.739 | 0 | 0 | 0 | 154243.739 | 171999.9996 | 177000 | 181999.9992 | 186999.9996 | 717999.9984 | -17756.2606 | -177000 | -181999.9992 | -186999.9996 | -563756.2594 | -10.32% | -100% | -100% | -100% | -78.52% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentDist System Inspect CMP Annual PatrolTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspect CMP Annual Patrol | Tier 3 | 129698.9491 | 0 | 0 | 0 | 129698.9491 | 144999.9996 | 148999.9992 | 153000 | 157999.9992 | 604999.998 | -15301.0505 | -148999.9992 | -153000 | -157999.9992 | -475301.0489 | -10.55% | -100% | -100% | -100% | -78.56% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentDist System Inspection Drone InspectionsTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspection Drone Inspections | Tier 3 | 32869592.8412 | 0 | 0 | 0 | 32869592.8412 | 14443999.9992 | 14877999.9996 | 15324000 | 15783999.9996 | 60429999.9984 | 18425592.842 | -14877999.9996 | -15324000 | -15783999.9996 | -27560407.1572 | 127.6% | -100% | -100% | -100% | -45.61% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentDist System Inspection HFTD Tier 3 InspectionsTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspection HFTD Tier 3 Inspections | Tier 3 | 0 | 0 | 0 | 0 | 0 | 373999.9992 | 384999.9996 | 396999.9996 | 408999.9996 | 1564999.998 | -373999.9992 | -384999.9996 | -396999.9996 | -408999.9996 | -1564999.998 | -100% | -100% | -100% | -100% | -100% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentDist System Inspection IR/CoronaTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Dist System Inspection IR/Corona | Tier 2 | 138733.9999 | 0 | 0 | 0 | 138733.9999 | 199999.9992 | 205999.9992 | 211999.9992 | 217999.9992 | 835999.9968 | -61265.9993 | -205999.9992 | -211999.9992 | -217999.9992 | -697265.9969 | -30.63% | -100% | -100% | -100% | -83.41% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentIntrusive PolesTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Intrusive Poles | Tier 2 | 59555.2116 | 0 | 0 | 0 | 59555.2116 | 48999.9996 | 49999.9992 | 51999.9996 | 54000 | 204999.9984 | 10555.212 | -49999.9992 | -51999.9996 | -54000 | -145444.7868 | 21.54% | -100% | -100% | -100% | -70.95% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentIntrusive PolesTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | Intrusive Poles | Tier 3 | 13332.9285 | 0 | 0 | 0 | 13332.9285 | 94999.9992 | 97999.9992 | 100999.9992 | 103999.9992 | 397999.9968 | -81667.0707 | -97999.9992 | -100999.9992 | -103999.9992 | -384667.0683 | -85.97% | -100% | -100% | -100% | -96.65% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTASSET MANAGEMENT & INSPECTIONSWildfire Involving SDG&E EquipmentLiDAR FlightsN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | ASSET MANAGEMENT & INSPECTIONS | Wildfire Involving SDG&E Equipment | LiDAR Flights | N/A | 31361 | 0 | 0 | 0 | 31361 | 1711999.9992 | 1762999.9992 | 1815999.9996 | 1869999.9996 | 7160999.9976 | -1680638.9992 | -1762999.9992 | -1815999.9996 | -1869999.9996 | -7129638.9976 | -98.17% | -100% | -100% | -100% | -99.56% | YES | 1WM004.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTDATA GOVERNANCEWildfire Involving SDG&E EquipmentData GovernanceN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | DATA GOVERNANCE | Wildfire Involving SDG&E Equipment | Data Governance | N/A | 1322326.8922 | 0 | 0 | 0 | 1322367.7322 | 1873999.9992 | 1929999.9996 | 1987999.9992 | 2047999.9992 | 7839999.9972 | -551673.107 | -1929999.9996 | -1987999.9992 | -2047999.9992 | -6517632.265 | -29.44% | -100% | -100% | -100% | -83.13% | YES | 1WM007.002 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTEMERGENCY PLANNING & PREPAREDNESSWildfire Involving SDG&E EquipmentEmergency Management OperationsN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | EMERGENCY PLANNING & PREPAREDNESS | Wildfire Involving SDG&E Equipment | Emergency Management Operations | N/A | 17536855.2396 | 0 | 0 | 0 | 17581794.8796 | 18471999.9996 | 19026000 | 19596999.9996 | 20184999.9996 | 77279999.9988 | -935144.76 | -19026000 | -19596999.9996 | -20184999.9996 | -59698205.1192 | -5.062% | -100% | -100% | -100% | -77.25% | YES | 1WM001.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentAdvanced ProtectionTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Advanced Protection | Tier 3 | 145415.1656 | 0 | 0 | 0 | 145415.1656 | 0 | 0 | 0 | 0 | 0 | 145415.1656 | 0 | 0 | 0 | 145415.1656 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentAvian Protection ProgramOH Distribution | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Avian Protection Program | OH Distribution | 30391.6984 | 0 | 0 | 0 | 30391.6984 | 0 | 0 | 0 | 0 | 0 | 30391.6984 | 0 | 0 | 0 | 30391.6984 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentBLM Land ManagementNew01 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | BLM Land Management | New01 | 0 | 0 | 0 | 0 | 0 | 4999.9992 | 4999.9992 | 4999.9992 | 4999.9992 | 19999.9968 | -4999.9992 | -4999.9992 | -4999.9992 | -4999.9992 | -19999.9968 | -100% | -100% | -100% | -100% | -100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentCNF Access RoadsNone | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | CNF Access Roads | None | 231729.6576 | 0 | 0 | 0 | 231729.6576 | 0 | 0 | 0 | 0 | 0 | 231729.6576 | 0 | 0 | 0 | 231729.6576 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentCNF Land ManagementN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | CNF Land Management | N/A | 0 | 0 | 0 | 0 | 0 | 153000 | 157999.9992 | 162999.9996 | 168000 | 641999.9988 | -153000 | -157999.9992 | -162999.9996 | -168000 | -641999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentEARLY FAULT DETECTIONNone | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | EARLY FAULT DETECTION | None | 125187.6834 | 0 | 0 | 0 | 125187.6834 | 0 | 0 | 0 | 0 | 0 | 125187.6834 | 0 | 0 | 0 | 125187.6834 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentHotline ClampsTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 2 | 89649.8318 | 0 | 0 | 0 | 89649.8318 | 207999.9996 | 213999.9996 | 219999.9996 | 226999.9992 | 868999.998 | -118350.1678 | -213999.9996 | -219999.9996 | -226999.9992 | -779350.1662 | -56.9% | -100% | -100% | -100% | -89.68% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentHotline ClampsTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Hotline Clamps | Tier 3 | 16114.1136 | 0 | 0 | 0 | 16114.1136 | 207999.9996 | 213999.9996 | 219999.9996 | 226999.9992 | 868999.998 | -191885.886 | -213999.9996 | -219999.9996 | -226999.9992 | -852885.8844 | -92.25% | -100% | -100% | -100% | -98.15% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentLTE Communication NetworkNone | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | LTE Communication Network | None | 843342.8695 | 0 | 0 | 0 | 843342.8695 | 0 | 0 | 0 | 0 | 0 | 843342.8695 | 0 | 0 | 0 | 843342.8695 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentMicrogridsTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Microgrids | Tier 2 | 1018926.3194 | 0 | 0 | 0 | 1018926.3194 | 1834999.9992 | 1890000 | 1947000 | 2004000 | 7675999.9992 | -816073.6798 | -1890000 | -1947000 | -2004000 | -6657073.6798 | -44.47% | -100% | -100% | -100% | -86.73% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Bare ConductorNon-HFTD | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Non-HFTD | 0 | 0 | 0 | 0 | 0 | 1999.9992 | 1999.9992 | 1999.9992 | 1999.9992 | 7999.9968 | -1999.9992 | -1999.9992 | -1999.9992 | -1999.9992 | -7999.9968 | -100% | -100% | -100% | -100% | -100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Bare ConductorTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 2 | 226925.6525 | 0 | 0 | 0 | 226925.6525 | 30000 | 30999.9996 | 31999.9992 | 33000 | 125999.9988 | 196925.6525 | -30999.9996 | -31999.9992 | -33000 | 100925.6537 | 656.4% | -100% | -100% | -100% | 80.1% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Bare ConductorTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Bare Conductor | Tier 3 | 2338483.1927 | 0 | 0 | 0 | 2338483.1927 | 22999.9992 | 24000 | 24999.9996 | 25999.9992 | 97999.998 | 2315483.1935 | -24000 | -24999.9996 | -25999.9992 | 2240483.1947 | 10067% | -100% | -100% | -100% | 2286% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Covered CondTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Cond | Tier 2 | 1404008.0475 | 0 | 0 | 0 | 1404008.0475 | 121999.9992 | 126000 | 129999.9996 | 133999.9992 | 511999.998 | 1282008.0483 | -126000 | -129999.9996 | -133999.9992 | 892008.0495 | 1051% | -100% | -100% | -100% | 174.2% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentOH Dist Fire Hardening Covered CondTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Dist Fire Hardening Covered Cond | Tier 3 | 1014161.5327 | 0 | 0 | 0 | 1014161.5327 | 552999.9996 | 570000 | 586999.9992 | 604999.9992 | 2314999.998 | 461161.5331 | -570000 | -586999.9992 | -604999.9992 | -1300838.4653 | 83.39% | -100% | -100% | -100% | -56.19% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentOH Trans Fire Hardening Dist UnderbuildTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | OH Trans Fire Hardening Dist Underbuild | Tier 2 | 623 | 0 | 0 | 0 | 623 | 0 | 0 | 0 | 0 | 0 | 623 | 0 | 0 | 0 | 623 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentResiliency Assistance ProgramsTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Assistance Programs | Tier 2 | 0 | 0 | 0 | 0 | 0 | 1252999.9992 | 1290999.9996 | 1329999.9996 | 1369999.9992 | 5243999.9976 | -1252999.9992 | -1290999.9996 | -1329999.9996 | -1369999.9992 | -5243999.9976 | -100% | -100% | -100% | -100% | -100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentResiliency Assistance ProgramsTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Assistance Programs | Tier 3 | 489447.7061 | 0 | 0 | 0 | 489447.7061 | 835999.9992 | 861000 | 886999.9992 | 913999.9992 | 3497999.9976 | -346552.2931 | -861000 | -886999.9992 | -913999.9992 | -3008552.2915 | -41.45% | -100% | -100% | -100% | -86.01% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentResiliency Grant ProgramsTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Grant Programs | Tier 2 | 0 | 0 | 0 | 0 | 0 | 5586999.9996 | 5754000 | 5926999.9992 | 6105000 | 23372999.9988 | -5586999.9996 | -5754000 | -5926999.9992 | -6105000 | -23372999.9988 | -100% | -100% | -100% | -100% | -100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentResiliency Grant ProgramsTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Resiliency Grant Programs | Tier 3 | 979765.7838 | 0 | 0 | 0 | 979765.7838 | 3036000 | 3126999.9996 | 3219999.9996 | 3316999.9992 | 12699999.9984 | -2056234.2162 | -3126999.9996 | -3219999.9996 | -3316999.9992 | -11720234.2146 | -67.73% | -100% | -100% | -100% | -92.29% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentStandby Power ProgramsTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Standby Power Programs | Tier 3 | 5206457.297 | 0 | 0 | 0 | 5206457.297 | 11820000 | 12174000 | 12538999.9992 | 12915000 | 49447999.9992 | -6613542.703 | -12174000 | -12538999.9992 | -12915000 | -44241542.7022 | -55.95% | -100% | -100% | -100% | -89.47% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentStrategic Pole Replacement Program (HFTD)HFTD Tiers 2 & 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Strategic Pole Replacement Program (HFTD) | HFTD Tiers 2 & 3 | 151220.8685 | 0 | 0 | 0 | 151220.8685 | 0 | 0 | 0 | 0 | 0 | 151220.8685 | 0 | 0 | 0 | 151220.8685 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentStrategic UndergroundingTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 2 | 347769.5822 | 0 | 0 | 0 | 347769.5822 | 1234999.9992 | 1272000 | 1309999.9992 | 1348999.9992 | 5165999.9976 | -887230.417 | -1272000 | -1309999.9992 | -1348999.9992 | -4818230.4154 | -71.84% | -100% | -100% | -100% | -93.27% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentStrategic UndergroundingTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Strategic Undergrounding | Tier 3 | 1134151.1881 | 0 | 0 | 0 | 1134151.1881 | 2100999.9996 | 2163999.9996 | 2229000 | 2295000 | 8788999.9992 | -966848.8115 | -2163999.9996 | -2229000 | -2295000 | -7654848.8111 | -46.02% | -100% | -100% | -100% | -87.1% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID DESIGN & SYSTEM HARDENINGWildfire Involving SDG&E EquipmentTransmission System InspectionNone | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID DESIGN & SYSTEM HARDENING | Wildfire Involving SDG&E Equipment | Transmission System Inspection | None | 5645 | 0 | 0 | 0 | 5645 | 0 | 0 | 0 | 0 | 0 | 5645 | 0 | 0 | 0 | 5645 | 100% | 100% | 100% | 100% | 100% | YES | 1WM003.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID OPERATIONS & OPERATING PROTOCOLSWildfire Involving SDG&E EquipmentAviation Firefighting ProgramNon-HFTD | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Non-HFTD | 0.49266 | 0 | 0 | 0 | 31.8337 | 342000 | 351999.9996 | 363000 | 373999.9992 | 1430999.9988 | -341999.5073 | -351999.9996 | -363000 | -373999.9992 | -1430968.1651 | -100% | -100% | -100% | -100% | -100% | YES | 1WM006.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID OPERATIONS & OPERATING PROTOCOLSWildfire Involving SDG&E EquipmentAviation Firefighting ProgramTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 2 | -0.08764 | 0 | 0 | 0 | 376.0044 | 4746999.9996 | 4888999.9992 | 5035999.9992 | 5187000 | 19858999.998 | -4747000.0872 | -4888999.9992 | -5035999.9992 | -5187000 | -19858623.9936 | -100% | -100% | -100% | -100% | -100% | YES | 1WM006.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID OPERATIONS & OPERATING PROTOCOLSWildfire Involving SDG&E EquipmentAviation Firefighting ProgramTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Aviation Firefighting Program | Tier 3 | 7665013.6849 | 0 | 0 | 0 | 7665650.9519 | 8049999.9996 | 8292000 | 8539999.9992 | 8796000 | 33677999.9988 | -384986.3147 | -8292000 | -8539999.9992 | -8796000 | -26012349.0469 | -4.782% | -100% | -100% | -100% | -77.24% | YES | 1WM006.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID OPERATIONS & OPERATING PROTOCOLSWildfire Involving SDG&E EquipmentWildfire Infrastructure Protection TeamsTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Wildfire Infrastructure Protection Teams | Tier 2 | 0 | 0 | 0 | 0 | 0 | 1095999.9996 | 1128999.9996 | 1162999.9992 | 1197999.9996 | 4585999.998 | -1095999.9996 | -1128999.9996 | -1162999.9992 | -1197999.9996 | -4585999.998 | -100% | -100% | -100% | -100% | -100% | YES | 1WM006.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTGRID OPERATIONS & OPERATING PROTOCOLSWildfire Involving SDG&E EquipmentWildfire Infrastructure Protection TeamsTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | GRID OPERATIONS & OPERATING PROTOCOLS | Wildfire Involving SDG&E Equipment | Wildfire Infrastructure Protection Teams | Tier 3 | 4822242 | 0 | 0 | 0 | 4822242 | 2580999.9996 | 2658000 | 2737999.9992 | 2820000 | 10796999.9988 | 2241242.0004 | -2658000 | -2737999.9992 | -2820000 | -5974757.9988 | 86.84% | -100% | -100% | -100% | -55.34% | YES | 1WM006.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTRESOURCE ALLOCATION METHODOLOGYWildfire Involving SDG&E EquipmentAsset ManagementNone | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | RESOURCE ALLOCATION METHODOLOGY | Wildfire Involving SDG&E Equipment | Asset Management | None | 103507.3686 | 0 | 0 | 0 | 114976.4686 | 0 | 0 | 0 | 0 | 0 | 103507.3686 | 0 | 0 | 0 | 114976.4686 | 100% | 100% | 100% | 100% | 100% | YES | 1WM007.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTRESOURCE ALLOCATION METHODOLOGYWildfire Involving SDG&E EquipmentWildfire Mitigation PersonnelNone | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | RESOURCE ALLOCATION METHODOLOGY | Wildfire Involving SDG&E Equipment | Wildfire Mitigation Personnel | None | 2710499.6979 | 0 | 0 | 0 | 36469530.5579 | 8781999.9996 | 9045000 | 9315999.9996 | 9594999.9996 | 36737999.9988 | -6071500.3017 | -9045000 | -9315999.9996 | -9594999.9996 | -268469.4409 | -69.14% | -100% | -100% | -100% | -0.7308% | YES | 1WM007.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTRISK ASSESSMENT & MAPPINGWildfire Involving SDG&E EquipmentRisk Assessment & MappingN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | RISK ASSESSMENT & MAPPING | Wildfire Involving SDG&E Equipment | Risk Assessment & Mapping | N/A | 4684549.6967 | 0 | 0 | 0 | 4684549.6967 | 2754999.9996 | 2838000 | 2922999.9996 | 3010999.9992 | 11526999.9984 | 1929549.6971 | -2838000 | -2922999.9996 | -3010999.9992 | -6842450.3017 | 70.04% | -100% | -100% | -100% | -59.36% | YES | 1WM007.001 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTSITUATIONAL AWARENESS AND FORECASTINGIncident Involving an EmployeeWildfire Smoke ParticulatesN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SITUATIONAL AWARENESS AND FORECASTING | Incident Involving an Employee | Wildfire Smoke Particulates | N/A | 44991 | 0 | 0 | 0 | 44991 | 114000 | 117000 | 120999.9996 | 124999.9992 | 476999.9988 | -69009 | -117000 | -120999.9996 | -124999.9992 | -432008.9988 | -60.53% | -100% | -100% | -100% | -90.57% | YES | 1WM002.000 | YES | SDG&E-Risk-8
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTSITUATIONAL AWARENESS AND FORECASTINGWildfire Involving SDG&E EquipmentFire Science and Climate Adaptation DepartmentN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | SITUATIONAL AWARENESS AND FORECASTING | Wildfire Involving SDG&E Equipment | Fire Science and Climate Adaptation Department | N/A | 5486441.7474 | 0 | 0 | 0 | 5547130.6474 | 4296000 | 4425000 | 4557000 | 4692999.9996 | 17970999.9996 | 1190441.7474 | -4425000 | -4557000 | -4692999.9996 | -12423869.3522 | 27.71% | -100% | -100% | -100% | -69.13% | YES | 1WM002.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTSTAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENTWildfire Involving SDG&E EquipmentMylar Balloon AlternativeN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | Mylar Balloon Alternative | N/A | 1728 | 0 | 0 | 0 | 1728 | 97999.9992 | 100999.9992 | 103999.9992 | 106999.9992 | 409999.9968 | -96271.9992 | -100999.9992 | -103999.9992 | -106999.9992 | -408271.9968 | -98.24% | -100% | -100% | -100% | -99.58% | YES | 1WM008.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTSTAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENTWildfire Involving SDG&E EquipmentPSPS Communication PracticesN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | PSPS Communication Practices | N/A | 7369719.7738 | 0 | 0 | 0 | 7369719.7738 | 11257999.9992 | 11595999.9996 | 11943999.9996 | 12303000 | 47100999.9984 | -3888280.2254 | -11595999.9996 | -11943999.9996 | -12303000 | -39731280.2246 | -34.54% | -100% | -100% | -100% | -84.35% | YES | 1WM008.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTSTAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENTWildfire Involving SDG&E EquipmentWMP AFN Customer SupportN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | WMP AFN Customer Support | N/A | 1495517.8571 | 0 | 0 | 0 | 1495517.8571 | 1582999.9992 | 1629999.9996 | 1678999.9992 | 1728999.9996 | 6620999.9976 | -87482.1421 | -1629999.9996 | -1678999.9992 | -1728999.9996 | -5125482.1405 | -5.526% | -100% | -100% | -100% | -77.41% | YES | 1WM008.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTSTAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENTWildfire Involving SDG&E EquipmentWMP Tribal Customer SupportN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | STAKEHOLDER COOPERATION & COMMUNITY ENGAGEMENT | Wildfire Involving SDG&E Equipment | WMP Tribal Customer Support | N/A | 156488.3783 | 0 | 0 | 0 | 156488.3783 | 228000 | 234999.9996 | 241999.9992 | 249000 | 953999.9988 | -71511.6217 | -234999.9996 | -241999.9992 | -249000 | -797511.6205 | -31.36% | -100% | -100% | -100% | -83.6% | YES | 1WM008.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSP. - TREE TRIMMING ONLYElectric Infrastructure IntegrityTree Trimming (non-HFTD)N/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Electric Infrastructure Integrity | Tree Trimming (non-HFTD) | N/A | 35382139.6622 | 0 | 0 | 0 | 40120164.5642 | 19516999.9992 | 20103000 | 20706000 | 21327000 | 81652999.9992 | 15865139.663 | -20103000 | -20706000 | -21327000 | -41532835.435 | 81.29% | -100% | -100% | -100% | -50.87% | YES | 1WM005.001 | YES | SDG&E-Risk-2
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSP. - TREE TRIMMING ONLYWildfire Involving SDG&E EquipmentEnhanced Vegetation ManagementTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Enhanced Vegetation Management | Tier 2 | 2725052.1536 | 0 | 0 | 0 | 2968027.7896 | 7444999.9992 | 7668000 | 7897999.9992 | 8134999.9992 | 31145999.9976 | -4719947.8456 | -7668000 | -7897999.9992 | -8134999.9992 | -28177972.208 | -63.4% | -100% | -100% | -100% | -90.47% | YES | 1WM005.001 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSP. - TREE TRIMMING ONLYWildfire Involving SDG&E EquipmentEnhanced Vegetation ManagementTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Enhanced Vegetation Management | Tier 3 | 1261516.5768 | 0 | 0 | 0 | 1383004.3948 | 5637000 | 5805999.9996 | 5979999.9996 | 6159000 | 23581999.9992 | -4375483.4232 | -5805999.9996 | -5979999.9996 | -6159000 | -22198995.6044 | -77.62% | -100% | -100% | -100% | -94.14% | YES | 1WM005.001 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSP. - TREE TRIMMING ONLYWildfire Involving SDG&E EquipmentTree TrimmingTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Tree Trimming | Tier 2 | 21555057.2919 | 0 | 0 | 0 | 25442667.4679 | 18594000 | 19150999.9992 | 19725000 | 20316999.9996 | 77786999.9988 | 2961057.2919 | -19150999.9992 | -19725000 | -20316999.9996 | -52344332.5309 | 15.92% | -100% | -100% | -100% | -67.29% | YES | 1WM005.001 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSP. - TREE TRIMMING ONLYWildfire Involving SDG&E EquipmentTree TrimmingTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP. - TREE TRIMMING ONLY | Wildfire Involving SDG&E Equipment | Tree Trimming | Tier 3 | 15289883.8964 | 0 | 0 | 0 | 18448567.1644 | 15421999.9992 | 15885000 | 16362000 | 16852999.9992 | 64521999.9984 | -132116.1028 | -15885000 | -16362000 | -16852999.9992 | -46073432.834 | -0.8567% | -100% | -100% | -100% | -71.41% | YES | 1WM005.001 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSPWildfire Involving SDG&E EquipmentFuels Management ProgramTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Fuels Management Program | Tier 2 | 623092.5703 | 0 | 0 | 0 | 623092.5703 | 1125000 | 1158999.9996 | 1194000 | 1230000 | 4707999.9996 | -501907.4297 | -1158999.9996 | -1194000 | -1230000 | -4084907.4293 | -44.61% | -100% | -100% | -100% | -86.77% | YES | 1WM005.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSPWildfire Involving SDG&E EquipmentFuels Management ProgramTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Fuels Management Program | Tier 3 | 2899776.7824 | 0 | 0 | 0 | 2899776.7824 | 4494000 | 4629000 | 4767999.9996 | 4911000 | 18801999.9996 | -1594223.2176 | -4629000 | -4767999.9996 | -4911000 | -15902223.2172 | -35.47% | -100% | -100% | -100% | -84.58% | YES | 1WM005.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSPWildfire Involving SDG&E EquipmentPole BrushingNon-HFTD | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Pole Brushing | Non-HFTD | 804917.6987 | 0 | 0 | 0 | 804917.6987 | 679999.9992 | 699999.9996 | 720999.9996 | 742999.9992 | 2843999.9976 | 124917.6995 | -699999.9996 | -720999.9996 | -742999.9992 | -2039082.2989 | 18.37% | -100% | -100% | -100% | -71.7% | YES | 1WM005.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSPWildfire Involving SDG&E EquipmentPole BrushingTier 2 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Pole Brushing | Tier 2 | 3258492.2486 | 0 | 0 | 0 | 3258492.2486 | 3100999.9992 | 3193999.9992 | 3289999.9992 | 3387999.9996 | 12972999.9972 | 157492.2494 | -3193999.9992 | -3289999.9992 | -3387999.9996 | -9714507.7486 | 5.079% | -100% | -100% | -100% | -74.88% | YES | 1WM005.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSPWildfire Involving SDG&E EquipmentPole BrushingTier 3 | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Pole Brushing | Tier 3 | 3057166.7686 | 0 | 0 | 0 | 3057166.7686 | 2896999.9992 | 2983999.9992 | 3072999.9996 | 3165000 | 12118999.998 | 160166.7694 | -2983999.9992 | -3072999.9996 | -3165000 | -9061833.2294 | 5.529% | -100% | -100% | -100% | -74.77% | YES | 1WM005.000 | YES | SDG&E-Risk-1
O&MWILDFIRE MITIGATION & VEGETATION MANAGEMENTVEGETATION MGMT & INSPWildfire Involving SDG&E EquipmentVegetation Restoration InitiativeN/A | O&M | WILDFIRE MITIGATION & VEGETATION MANAGEMENT | VEGETATION MGMT & INSP | Wildfire Involving SDG&E Equipment | Vegetation Restoration Initiative | N/A | 926075.5103 | 0 | 0 | 0 | 931515.4603 | 1071000 | 1102999.9992 | 1135999.9992 | 1170000 | 4479999.9984 | -144924.4897 | -1102999.9992 | -1135999.9992 | -1170000 | -3548484.5381 | -13.53% | -100% | -100% | -100% | -79.21% | YES | 1WM005.000 | YES | SDG&E-Risk-1