## 2022
2022 WMP Actual and GRC Forecast
Covered Conductor
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Actual) | Covered Conductor Installation | 61.23 miles | 3220.85 | 89512 | ARC Summary 2022 | na | 2023 WMP states 63 mile completed in 2022 (pg 3)
GRC (Forecast) | Overhead System Covered Conductor | 60 miles | 786 | 78593 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Units/O&M) 44; (Cap) 84, 62 | (Units) 49 + 11 = 60; (O&M) 642 + 144 = 786; (Cap) 64446 + 14147 = 78593; (Cap) Item # 202850; RAMP Line Item ID: C07/M2 T1-T2
Strategic Undergrounding
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Actual) | Distribution Undergrounding | 65 miles | 175.55 | 126675.09 | ARC Summary 2022 | na | na
GRC (Forecast) | Strategic Undergrounding | 65 miles | 1260 | 125981 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Units/O&M) 42; (Cap) 226, 61 | (Units) 41+24 = 65; (O&M) 794 + 466 = 1260; (Cap) 79368 + 46613 = 125981; (Cap) Item # 192460; RAMP Line Item ID: C16/M11 T1-T2
Hardening
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Actual) | Traditional Hardening Overhead | 26.3 miles | 3249.08 | 23267.67 | ARC Summary 2022 | na | na
| Distribution Underbuilt | .6 miles | 0 | 3237.21 | ARC Summary 2022 | na | na
| Transmission Overhead | 18.28 miles | 0 | 0 | ARC Summary 2022 | na | na
GRC (Forecast) | OH System Traditional Hardening | 24 miles | 171 | 16311 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (O&M) 56; (Cap) 120, 62 | (Units Tier 3 & 2) 10.5 +13.5 = 24; (O&M) 75 + 96 = 171; (Cap Tier 2 & 3) 6851 + 8808 = 15659; (Cap) Item # 202840; RAMP Line Item ID: C17/M12 T1-T3
| CNF Fire Hardening (distribution overhead) | 0 miles | na* | 1999 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 214, 61 | (Units) 0; (O&M) not mentioned, see *; (Cap) 1999; (Cap) Item # 081650; RAMP Line Item ID: C19
| Distribution Underbuilt | 2.7 miles | na | 4729 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 186, 61 | (Units) .2 + 2.5 = 2.7; (O&M) not mentioned in working papers; (Cap) 350 + 4379 = 4729; (Cap) Item # 141400; RAMP Line Item ID: C18/M13 T1-T2
* = CNF circuit hardening does not have O&M RAMP worksheet; no expected hardening to take place. CNF Access Roads and CNF Land Management are accounted for with O&M RAMP worksheets (pgs 53-54); additional explanation regarding cost of 5-year permitting on pg 31.

## 2023
2023 WMP Forecast and GRC Forecast
Covered Conductor
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Covered Conductor Installation | 60 miles | 2220 | 76806 | WMP 2023 | (Units) 143; (Spend) Table 11
GRC (Forecast) | Overhead System Covered Conductor | 60 miles | 692 | 69222 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Units/O&M) 44; (Cap) 84, 62 | (Units) 49 + 11 = 60; (O&M) 568 + 124 = 692; (Cap) 56762 + 12460 = 69222; (Cap) Item # 202850; RAMP Line Item ID: C07/M2 T1-T2
Strategic Undergrounding
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Transmission Undergrounding | na | 0 | 0 | na | na | WMP 2023 targets do not break out SUG by transmission/distribution
| Distribution Undergrounding | 84 miles | 436 | 196200 | WMP 2023 | (Units) 143; (Spend) Table 11 | WMP 2023 targets do not break out SUG by transmission/distribution
GRC (Forecast) | Strategic Undergrounding | 80 miles | 1911 | 191143 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Units/O&M) 42; (Cap) 226, 61 | (Units) 50 +30 = 80; (O&M) 1204 +707 = 1911; (Cap) 120410 + 70733 = 191143; Item # 192460; RAMP Line Item ID: C16/M11 T1-T2
Hardening
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Traditional Hardening Overhead | 1.9 miles | 1800 | 1985 | WMP 2023 | (Units) 143; (Spend) Table 11 | na
| Distribution Underbuilt | 7.1 miles | 0 | 11397 | WMP 2023 | (Units) 143; (Spend) Table 11 | na
| Transmission Overhead | 14.1 miles | 0 | 0 | WMP 2023 | (Units) 143; (Spend) Table 11 | na
GRC (Forecast) | OH System Traditional Hardening (same as bare conductor hardening?) | 5 miles | 53 | 5479 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (O&M) 56; (Cap) 120, 62 | (Units Tier 3 & 2) 5; (O&M) 23 + 30 = 53; (Cap) 5479; (Cap) Item # 202840; RAMP Line Item ID: C17/M12 T1-T3
| CNF Fire Hardening (distribution overhead) | 0 miles | na* | 1675 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 214, 61 | (Units) 0; (O&M) not mentioned, see *; (Cap) 1675; (Cap) Item # 081650; RAMP Line Item ID: C19
| Distribution Underbuilt | 8.8 miles | na | 8635 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 186, 61 | (Units) .6 +8.2 = 8.8; (O&M) not mentioned in working papers; (Cap) 638 + 7997 = 8635; (Cap) Item # 141400; RAMP Line Item ID: C18/M13 T1-T2
DELTA
| Traditional Hardening Overhead | 3.1 | 1747 | 3494
| Distribution Underbuilt | 1.7 | 0 | 2762
* = CNF circuit hardening does not have O&M RAMP worksheet; no expected hardening to take place. CNF Access Roads and CNF Land Management are accounted for with O&M RAMP worksheets (pgs 53-54); additional explanation regarding cost of 5-year permitting on pg 31.

## 2024 TY
2024 WMP Forecast and GRC Forecast
Covered Conductor
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Covered Conductor Installation | 60 miles | 592 | 59217 | WMP 2023 | (Units) 143; (Spend) Table 11 | na
GRC (Forecast) | Overhead System Covered Conductor | 60 miles | 592 | 59217 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Units/O&M) 44; (Cap) 62 | (Units) 49 + 11 = 60; (O&M) 485 = 107 = 592; (Cap) 78558 + 10659 = 59217; (Cap) Item # 202850; (Units/O&M) RAMP Line Item ID: C07/M2 T1-T2
Strategic Undergrounding
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Transmission Undergrounding | na | 0 | 0 | na | na | WMP 2023 targets/spend do not break out SUG by transmission/distribution
| Distribution Undergrounding | 125 miles | 2921 | 291933 | WMP 2023 | (Units) 143; (Spend) Table 11 | WMP 2023 targets/spend do not break out SUG by transmission/distribution
GRC (Forecast) | Strategic Undergrounding | 125 miles | 2921 | 292062 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Units/O&M) 42; (Cap) 226, 61 | (Units) 79 + 46 = 125 ; (O&M) 1840 + 1081 = 2921; (Cap) 184000 + 108062 = 292062; (Cap) Item # 192460; RAMP Line Item ID: C16/M11 T1-T2
Hardening
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Traditional Hardening Overhead | 0 miles | 48 | 892 | WMP 2023 | (Units) 143; (Spend) Table 11 | na
| Distribution Underbuilt | 1 mile | 0 | 14789 | WMP 2023 | (Units) 143; (Spend) Table 11 | na
| Transmission Overhead | 10.2 miles | 0 | 0 | WMP 2023 | (Units) 143; (Spend) Table 11 | na
GRC (Forecast) | OH System Traditional Hardening (same as bare conductor hardening?) | 5 miles | 46 | 5479 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (O&M) 56; (Cap) 120, 62 | (Units Tier 3 & 2) 5; (O&M) 20 + 26 = 46; (Cap) 5479); (Cap) Item # 202840; RAMP Line Item ID: C17/M12 T1-T3
| CNF Fire Hardening (distribution overhead) | 0 miles | na* | 1206 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 214, 61 | (Units) 0; (O&M) not mentioned, see *; (Cap) 1206; (Cap) Item # 081650; RAMP Line Item ID: C19
| Distribution Underbuilt | 14.8 miles | na | 14464 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 186, 61 | (Units) 1 + 13.8 = 14.8; (O&M) not mentioned in working papers; (Cap) 1070 + 13394 = 14464; (Cap) Item # 141400; RAMP Line Item ID: C18/M13 T1-T2
DELTA
| Traditional Hardening Overhead | 5 | 2 | 4587
| Distribution Underbuilt | 13.8 | 0 | 325
* = CNF circuit hardening does not have O&M RAMP worksheet; no expected hardening to take place. CNF Access Roads and CNF Land Management are accounted for with O&M RAMP worksheets (pgs 53-54); additional explanation regarding cost of 5-year permitting on pg 31.

## 2025
2025 WMP Forecast and GRC Forecast
Covered Conductor
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Covered Conductor Installation | 40 miles | 592 | 48246 | QDR submitted 01 May 2023): (Spend) Table 11; (Units) Table 12 | na | na
GRC (Forecast) | Overhead System Covered Conductor | 40 miles | 592 | 39478
| DELTA | 0 | 0 | 8768
Strategic Undergrounding
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Transmission Undergrounding | na | 0 | 0 | na | na | WMP 2023 targets/spend do not break out SUG by transmission/distribution
| Distribution Undergrounding | 150 miles | 2921 | 356654 | QDR submitted 01 May 2023): (Spend) Table 11; (Units) Table 12 | na | WMP 2023 targets/spend do not break out SUG by transmission/distribution
GRC (Forecast) | Strategic Undergrounding | 150 miles | 2921 | 350475
| DELTA | 0 | 0 | 6179
Hardening
|  | Units | Spend O&M ($000) | Spend Capital ($000) | Sources | Page | Notes
WMP (Forecast) | Traditional Hardening Overhead | 0.6 miles | 48 | 905 | QDR submitted 01 May 2023): (Spend) Table 11; (Units) Table 12 | na | na
| Distribution Underbuilt | 3.4 miles | 0 | 4747 | QDR submitted 01 May 2023): (Spend) Table 11; (Units) Table 12 | na | na
GRC (Forecast) (Same as 2024) | OH System Traditional Hardening (same as bare conductor hardening?) | 5 miles | 46 | 5479 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (O&M) 56; (Cap) 120, 62 | (Units Tier 3 & 2) 5; (O&M) 20 + 26 = 46; (Cap) 5479); (Cap) Item # 202840; RAMP Line Item ID: C17/M12 T1-T3
| CNF Fire Hardening (distribution overhead) | 0 miles | na | 1206 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 214, 61 | (Units) 0; (O&M) not mentioned, see *; (Cap) 1206; (Cap) Item # 081650; RAMP Line Item ID: C19
| Distribution Underbuilt | 14.8 miles | na | 14464 | (Units/O&M) 2024 Service Workpapers; (Cap) 2024 GRC Work Capital Papers | (Cap) 186, 61 | (Units) 1 + 13.8 = 14.8; (O&M) not mentioned in working papers; (Cap) 1070 + 13394 = 14464; (Cap) Item # 141400; RAMP Line Item ID: C18/M13 T1-T2
DELTA
| Traditional Hardening Overhead | 4.4 | 2 | 4574
| Distribution Underbuilt | 11.4 | 0 | 9717