## 2022
2022 WMP & GRC Actuals
Spend ($000)
Vegetation Inspections (Detailed inspections of vegetation - pre-inspection/tree trimming) WMP.494
Source |  | Units Completed (Inspections) - Territory - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - 7.3.5.2 | 509110 | 59775 | 31799 | 17288 | -162
GRC | TTBA | 491822 | 59937 | Subset not reported |  |  |  | Direct charge to IO/Cost Center. Deltas in spend may occur due to the retroactive balancing of accounts. (No units or cost split in T11 or T12). Recorded GRC units reflect actual inventory at the end of 2021. 2022 - 2024 targets forecasted numbers in GRC.
Fuels Management Program ("slash" - VM FMP, FSCA Grants, Land Services Fuels Abatement) WMP.497
Source |  | Units Completed (Poles Cleared) - HFTD - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - 7.3.5.5 | 500 | 7896 | 7896 | 0 | 0 | 0
GRC | WMPMA | 500 | 7896 | 7896 |  |  |  | All FM work is in HFTD
Clearance (Other Discretionary Inspections of Vegetation - enhanced inspections, patrols, trim) WMP.501
Source |  | Units Completed (trim/remove) - Territory- | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - 7.3.5.2 | 10488 | 10257 |  | -2336 | 0 | 0
GRC | TTBA | 12824 | 10257 |  |  |  |  | Actual WMP units resulted from a modification in scope beginning in 2022 that was based on historical "enhanced" tree trim history
Pole Clearing (brushing) WMP. 512
Source |  | Units Completed (Poles) - Territory - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - | 35485 | 6104.9138 | 5372.3242 | 1485 | -0.08615 | 0
GRC | WMPMA | 34000 | 6105 | 5372.3242 |  |  |  | Unit delta based on the assumption of the continuation of historical units. WMP 2021 actual units increased as a result of new poles subject to PRC 4292.
QA/QC (of vegetation inspections: pre-inspection & tree trimming) WMP.505
Source |  | Units Completed | O&M Spend | Notes
WMP | WMP22 - 7.3.5.13 | N/A | N/A | Not required in metrics tables per 2021 WSD guidelines.
GRC | TTBA | 15% of inspections | 59937
10,000 Tree Planting Initiaitive (Right Tree Right Place & Community Tree Rebate Program) WMP.1325 & WMP.1237
Source |  | Units Completed | O&M Spend | Notes
WMP | WMP22 - 7.3.5.13 | N/A | N/A | Discretionary activity - Not reported
GRC | WMPMA | 10000 | 872

## 2023
2023 WMP & GRC Projections
Spend ($000)
Vegetation Inspections (Detailed inspections of vegetation - pre-inspection/tree trimming) WMP.494
Source |  | Units Completed (Inspections) - Territory - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP23 - 8.2.2.1 | 485400 | 44559 | 23699 | -6422 | 419 | -2785 | 2023 targets and spend are forecasted.
GRC | TTBA | 491822 | 44140 | 26484
Fuels Management Program ("slash" - VM FMP, FSCA Grants, Land Services Fuels Abatement) WMP.497
Source |  | Units Completed (Poles Cleared) - HFTD - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP23 - 8.2.3 | 500 | 7011 | 7011 | 0 | 979 | 979
GRC | WMPMA | 500 | 6032 | 6032 |  |  |  | 2023 WMP forecast spend increase based on 10-year Corporate plan. 2023 WMP forecast spend based on 2022 actual. (Includes $1.2M erroneous accrual)
Clearance (Other Discretionary Inspections of Vegetation - enhanced inspections, patrols, trim) WMP.501
Source |  | Units Completed (trim/remove) - Territory- | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP23 - 8.2.3.2 | 11000 | 10235 | 10235 | -1824 | 0 | 0
GRC | TTBA | 12824 | 10235 | 10235 |  |  |  | use 2022 comments
Pole Clearing (brushing) WMP. 512
Source |  | Units Completed (Poles) - Territory - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - 8.2.3.1 | 27890 | 6411 | 5645 | -6110 | -366 | -443 | Scope is variable due to number of trees needing work performed.
GRC | WMPMA | 34000 | 6777 | 6088 |  |  |  | 2023 WMP forecast spend based on 2022 actual.
QA/QC (of vegetation inspections: pre-inspection & tree trimming) WMP.505
Source |  | Units Completed | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - 8.2.5 | 15% of VM inspections | N/A | N/A |  |  |  | Spend was not provided in T11 - it is rolled into pre-inspection.
GRC | TTBA | 15% of inspections | N/A | 44140
10,000 Tree Planting Initiaitive (Right Tree Right Place & Community Tree Rebate Program) WMP.1325 & WMP.1237
Source |  | Units Competed | O&M Spend | Notes
WMP | WMP22 - 8.2.3.6 | 10000 | 1000 | Discretionary activity - Not reported
GRC | WMPMA | 10000 | 1000

## 2024
2024 WMP & GRC Projections
Spend ($000)
Vegetation Inspections (Detailed inspections of vegetation - pre-inspection/tree trimming) WMP.494
Source |  | Units Completed (Inspections) - Territory - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP23 - 8.2.2.1 | 374200 | 45387 | 27232 | -80800 | 0 | 0
GRC | TTBA | 455000 | 45387 | 27232 |  |  |  | 2022 - 2024 targets forecasted numbers in GRC.
Fuels Management Program ("slash" - VM FMP, FSCA Grants, Land Services Fuels Abatement) WMP.497
Source |  | Units Completed (Poles Cleared) - HFTD - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP23 - 8.2.3 | 500 | 6513 | 6513 | -50 | 240 | 240
GRC | WMPMA | 550 | 6273 | 6273 |  |  |  | 2024 WMP forecast spend increase based on 10-year Corporate plan. 2024 WMP forecast spend based on 2023 actual.
Clearance (Other Discretionary Inspections of Vegetation - enhanced inspections, patrols, trim) WMP.501
Source |  | Units Completed (trim/remove) - Territory- | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP23 - 8.2.3.2 | 11200 | 10235 | 10235 | -1624 | 0 | 0
GRC | TTBA | 12824 | 10235 | 10235 |  |  |  | Scope is variable due to number of trees needing work performed.
Pole Clearing (brushing) WMP. 512
Source |  | Units Completed (Poles) - Territory - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - 8.2.3.1 | 33010 | 7267 | 7267 | -990 | 240 | 955
GRC | WMPMA | 34000 | 7027 | 6312 |  |  |  | 2024 WMP forecast spend based on 2023 actual.
QA/QC (of vegetation inspections: pre-inspection & tree trimming) WMP.505
Source |  | Units Completed - Territory - | O&M Spend - Territory - | O&M Spend - HFTD - | Unit Delta | Spend Delta - Territory - | Spend Delta - HFTD - | Notes
WMP | 02.01.2023 QDR T11 WMP22 - 8.2.5 | 15% of VM inspections
GRC | TTBA | 15% of inspections | 15% of inspections | 45387
10,000 Tree Planting Initiaitive (Right Tree Right Place & Community Tree Rebate Program) WMP.1325 & WMP.1237
Source |  | Units Competed | O&M Spend | Notes
WMP | WMP22 - 8.2.3.6 | 10000 | 1000 | Discretionary activity - Not reported
GRC | WMPMA | 10000 | 1000