## TAB 1 Project Information
Row/Line # | Project Name | Location | Project Description | Project Description - Where | Project Description - Why | 1st assignment | 2nd assignment | 3rd assignment | Notes | Transmission Project Size | Substation Project Area | Transmission Voltage Level (kV) | Substation or Transformer Capacity (MVA) | Utility Approval | Year of Utility Approval | Process for Utility Approval | CAISO Year | Year when considered in CAISO TPP | Year when expected to be considered in CAISO TPP | Link to TPP where project is considered or expected to be considered (if applicable and available) | FERC: Year | CEQA Status | CEQA/NEPA Document Type | CEQA/NEPA Lead Agency | CPUC Advice Letter or Application | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status: Year | Project Status | Original Planned In-Service Date | Current Planned In-Service Date | Original Cost or Cost Range ($M) - CAISO approved projects only | Actual Cost ($M) - FERC | Actual Cost ($M) - CPUC | Capital Expenditure ($M) | Cost Cap ($M) | Cost Spent on Construction Work in Progress ($M) | % Cost in High Voltage TAC - | % Cost in Low Voltage TAC (200 and below) | Primary Purpose & Benefit
1 | Mira Sorrento 138/12KV Sub & Cirs. 1442 Thru 1446 | San Diego | New 69/12 kv substation and loop in of existing tieline | See "location" | See "purpose and need" | 1 | 3 |  | added 3 | N/A | 5 acres | 69kV, 12kv | 120MVA | Yes | 2002 | SDG&E Board of Director approval | N/A | N/A | N/A | Not included in TPP | 2014 | Final Certified | MND | CPUC | Application A.11-10-015 | PTC | 2010 | Approved | 2012 | Operational | 2014 | 2014-12-01 |  | 19 | 13.3 | See "Actual Costs" | N/A | N/A | 0% | 100% | Improve reliability, tie capacity in the area and reduce overloading of adjacent substations.
2 | Salt Creek-Land Purchase, New Substa. & 3 New Ckts | Chula Vista | New 69/12 kv substation and loop in of existing tieline | See "location" | See "purpose and need" | 1 | 3 |  | added 3 | N/A | approx. 35 acres | 69kV |  | Yes | 2012 | SDG&E Board of Director approval | 2015 | 2013-2014 | N/A | http://www.caiso.com/Documents/Board-Approved2014-2015TransmissionPlan.pdf | 2017 | NTP issued | EIR | CPUC | Application A.13-09-014 | PTC | 2013 | Approved | 2016 | Post Construction | 2016 | 2017-09-20 | $70 Million - $77 Million | 33.4 | 16.3 | See "Actual Costs" | N/A |  | 0% | 100% | Improve reliability, tie capacity in the area and reduce overloading of adjacent substations.
3 | Sunrise Powerlink | San Diego, Imperial | The project consists of a new electric transmission line between the existing Imperial Valley and Sycamore Canyon substations, a proposed new Suncrest Substation, and other system modifications in order to reliably operate the new line. A 22-mile portion of the line between Sycamore Canyon Substation and Suncrest Substation will be an overhead, double-circuit 230-kV transmission line consisting of both lattice steel and steel pole structures and a 6-mile portion will be a 230-kV double-circuit underground transmission line. The 92-mile segment from Suncrest Substation to Imperial Valley Substation will be a 500-kV single-circuit transmission line comprised of lattice steel structures. | See "location" | See "purpose and need" | 4 | 5 |  |  | See Project Description | 40 acres (Suncrest) | 500kV, 230kV |  | Yes |  | Sempra Board of Directors Approval |  |  | N/A |  | 2012 | Final Certified | EIR/EIS | CPUC/BLM/FS | Application A.06-08-010 | CPCN | 2006 | Approved | 2008 | Operational | 2012 | 2012-06-01 |  | 1819.5 | 12.4 | See "Actual Costs" | $1,883M |  | 100 | 0 | Maintain reliability in delivery of power to the San Diego region, reduce the cost of energy, and accommodate the delivery of renewable energy to meet state and federal renewable energy goals from resources in the Imperial Valley and wind and other sources in San Diego County
4 | Ocean Ranch Land Purchase, New Substation | Oceanside | Construct and operate the Ocean Ranch 69/12-kV Substation and associated distribution lines. The Project will consist of the following: a new 69/12 kilovolt (kV) low-profile electric substation located on a 9.66 acre site on Avenida del Oro north of Avenida de la Plata; approximately 1,500 feet of underground power line duct bank to loop an existing 69 kV circuit into the new substation; four new 12 kV distribution circuits that would intercept four existing circuits in the vicinity; and a telecommunication system that would include a 40 foot monopole and attached microwave antenna. | See "location" | (1) Provide additional capacity to serve the existing area load and forecasted customer-driven electrical load growth; and (2) prevent potential long outages or disruption of service to SDG&E customers in the Oceanside area. | 1 |  |  |  | N/A | 9.66 | 69kV | Initial buildout capacity is 60MVA and ultimate buildout capacity is 120MVA | Yes |  | Sempra Board of Directors Approval | 2016 | 2015-2016 | N/A | https://www.caiso.com/Documents/Board-Approved2015-2016TransmissionPlan.pdf | N/A |  | MND | CPUC | Application # 16-07-016 | PTC | 2016-07-27 | Approved | 2017 | Permitting | 2019 | 2019-05-01 | $68 Million | N/A | N/A | See "Actual Costs" | N/A | 4.5 | 0% | 100% | Meet the area's existing and forecasted electric load growth, Maintain substation and Circuit Reliability and additional Tie and Transformer Capacity; Reduce area substation loading to optimum operating conditions
5 | South Orange County Reliability Enhancement (SOCRE) | Orange and San Diego | Build a new 230kV GIS substation and rebuild an existing 138kV substation (GIS). Replace an existing 138kV transmission line with a new 230kV double circuit transmission line. | See "location" | See "purpose and need" | 1 | 6 |  | added 6 | 8 miles | 5 acres | 230kV, 138kV | 352 MVA | Yes | 2011 | Sempra Board of Approval | 2011 | 2010-2011 | N/A |  | N/A | Final Certified | CPCN | CEQA | Application A.12-05-020 | CPCN | 2012 | Approved | 2016 | about to begin construction | 2017 | 2021 | $365 Million | N/A | N/A | See "Actual Costs" | 381M | 59.9 |  |  | Provide transmission reliability; reduce risk of outages in South Orange County, comply with mandatory NERC, WECC and CAISO standards. Replace aging infrastructure and improve transmission and distribution operating flexibility.
6 | Relocate South Bay Substation | San Diego | Relocate existing of the existing 138/69kV substation to a new site .5 mile down the road. This will facilitate the development of Chula Vista's Bayfront Master Plan. An existing 230kV transmission line will be looped in at the new site. | See "location" | See "purpose and need" | 7 |  |  |  | approx. 1 mile | 9.7 acres | 230kV, 69kV | 224MVA | Yes | 2008 | SDG&E Board of Director approval | 2010 | 2009-2010 | N/A |  | 2016 | Final Certified | EIR | CPUC and CCC | Application A. 10-06-007 | PTC | 2010 | Approved | 2013 | Operational | 2012 | 2016-06-01 |  | 130.3 | 3.1 | See "Actual Costs" |  |  |  |  | Replace aging and obsolete equipment, provide for future load growth, facilitate the City of Chula Vista's bayfront redevelopment goals by relocating the substation.
7 | ECO Substation | San Diego | The project included building a new 500/230/138 kilovolt (kV) substation (ECO Substation) in the Jacumba area, looping-in the Southwest Powerlink (SWPL) into the new ECO Substation, building a new 138 kV transmission line, approximately 13.3 miles in length, running between the new ECO Substation and the rebuilt Boulevard Substation, rebuild the existing Boulevard 69/12kV substation as a 138/69/12kV substation, and rebuild the White Star Communication Facility. | See "location" | See "purpose and need" | 5 |  |  |  | 13 Miles | 58 acres | 500kV, 230kV, 138kV, 69kV | 1120 MVA @ 500/230kV (ECO) 350 MVA @ 230/138kV (ECO) 220 MVA @138/69kV (BUE) 25 MVA @ 138/12kV (BUE) | Yes |  | Sempra Board of Directors Approval | N/A | N/A | N/A | Not included in TPP | 2014 | Final Certified | EIR/EIS | CPUC and BLM | Application A. 09-08-003 | PTC | 2009 | Approved | 2012 | Operational |  | 2014-07-01 |  | 417.7 | 18.9 | See "Actual Costs" | NA |  |  |  | Provide an interconnection hub for renewable generation along SDG&E’s existing Southwest Powerlink (SWPL) 500 kV transmission line. Facilitate the interconnection of renewable generation sources in the Boulevard area. Provide a second source for the southeastern transmission system that avoids the vulnerability of common structure outages, thus increasing the reliability of electrical service for Boulevard, Jacumba, and other surrounding communities.
8 | TL 629 DE-GC-CN SW Pole Replacements - CNF | San Diego | Approximately 29.8 miles in total length, with approximately 9.6 miles located within the CNF boundary and approximately 20.2 miles located outside the CNF boundary; runs from Descanso Substation east to Glencliff Substation located south of Pine Valley, from Glencliff Substation southeast to Cameron Tap near Kitchen Creek road and Interstate 8, from Cameron Tap south to Cameron Substation off Buckman Springs Road, and from Cameron Tap east to Crestwood Substation south of the Golden Acorn Casino on the Campo Indian reservation | See "location" | See "purpose and need" | 8 |  |  |  | Approximately 30 miles | N/A | 69kV, 12kv |  | Yes |  | SDGE Board of Director Approval | N/A | N/A | N/A | Not included in TPP | 2019 | Final Certified | EIR/EIS | CPUC & USFS are Co-Lead Agencies | Application | PTC |  | Approved | 2016 | Construction |  | 2019-07-01 |  | N/A | N/A | See "Actual Costs" |  | 199.2 | 0% | 100%
9 | TL 637 CRE-ST SW Pole Replacements | San Diego | Replacing wood poles with steel poles | See "location" | See "purpose and need" | 8 |  |  |  | N/A | N/A | 69kV | N/A | Yes |  |  | N/A | N/A | N/A | Not included in TPP | 2014 | Final Certified | MND | CPUC | Application A.13-03-003 | Application | 2013-03-13 | Approved | 2014 | Complete | 2014 | 2014-09-01 | N/A | 43.2 | 3.3 | See "Actual Costs" |  |  | 0% | 100% | To enhance reliability during fires
10 | TL6926 Rincon-Valley Center SW Pole Replace | Valley Center | TL6926 Wood to Steel project replaces wood poles with steel poles in high fire risk area in the Valley Center area. It includes approx. 5 miles and 50 poles. This project will help improve the reliability of TL6926 from Rincon to Valley Center in fire - prone areas by replacing existing wood poles with equivalent steel poles. The fire hardening work will transfer existing conductor and will use slightly longer insulators, and utilize increased vertical and horizontal spacing. | See "location" | See "purpose and need" | 8 |  |  |  | Approximately 5 miles | N/A | 69kV, 12kV | N/A | Yes |  |  | N/A | N/A | N/A | Not included in TPP | N/A | TBD | TBD | CPUC | Application | PTC | 2018-11-01 | To be filed | 2017 | Preliminary Design |  | 2019-12-01 |  | N/A | N/A | See "Actual Costs" |  | 8.4 | 0% | 100%
11 | TL649 Otay-San Ysidro-Border SW Pole Replace | San Diego | Wood-to-steel conversion of a portion of an existing 69kv tieline | See "location" | See "purpose and need" | 8 |  |  | changed from 7 to 8 | approx. 7 miles | N/A | 69kV, 12 kV | N/A | Yes | 2013 |  | N/A | N/A | N/A | Not included in TPP | N/A | PEA deemed complete | PTC | CPUC | PTC | PTC | 2015 | Filed & under review | 2017 | Permitting | 2017 | 2019-09-01 |  | N/A | N/A | See "Actual Costs" | N/A | 4.4 | 0% | 100% | wood to steel to decrease fire risk
12 | TL686 Warners to Narrows SW Pole Replace TL687 Borrego Springs | San Diego | Fire Hardening initiative to replace wood poles with equivalent steel poles within the Fire Threat Zone Area in Warner Springs. | See "location" | See "purpose and need" | 8 |  |  | changed from 7 to 8 | N/A |  | 69kV, 12kV |  | Yes |  |  | N/A | N/A | N/A | Not included in TPP | N/A | TBD | TBD | TBD | TBD | Advice Letter and PTC | TBD | TBD | TBD | Preliminary Design | TBD | TBD |  | N/A | N/A | See "Actual Costs" | N/A | 0.6 | 0% | 100%
13 | TL13821 and TL13828-Fanita Junction Enhancement | San Diego | The project entails replacing and modifying electrical transmission infrastructure, including poles and overhead conductor, on an approximately 11‐mile stretch of TL 13821 spanning between the Sycamore, Carlton Hills, and Santee Substations. The project also will convert TL 13821, an existing 3‐terminal transmission line, into two 2‐terminal lines - TL 13821 from the Sycamore Substation to the Santee Substation (8 miles), and TL 13828 from the Sycamore Substation to the Carlton Hills Substation (7 miles). | See "location" | See "purpose and need" | 1 |  |  |  | approximately 26 miles | N/A | 138kv |  | Yes |  |  | 2010 | 2009-2010 | N/A | Not available online | 2016 | N/A | N/A | CPUC | Advice Letter 2433-E | Advice Letter | 2012 | Approved | 2013 | Complete | 2013 | 2016-11-01 |  | 49.9 | 5.6 | See "Actual Costs" |  | N/A | 0% | 100% | Reliability
14 | Poseidon Project-Modify Cannon Sub & Install 2 Ckts | Carlsbad | To provide 38 MW of power to the Poseidon Desalination Plant through the expansion of the existing Cannon Substation for an additional 56 MVA and the installation of additional distribution and transmission lines. | See "location" | See "purpose and need" | 3 |  |  |  | N/A | Approx. 3 acres | 138kV | 56 MVA | Yes |  |  | N/A | N/A | N/A | Not included in TPP | 2014 | Advice Letter | N/A | CPUC | AL | Advice Letter | 2012 | Approved |  | Complete |  | 2014-09-01 |  | 14.6 | 11.5 | See "Actual Costs" | N/A | N/A |  |  | Support energy need for new desalination plant and improve system reliability
15 | Wood to Steel Pole Replace.-TL690E | Camp Pendleton | wood-to-steel conversion and reconductor of an existing 69kv tieline | See "location" | See "purpose and need" | 8 | 1 |  | added 1 | approx. 5 miles | N/A | 69kV | N/A | Yes |  |  | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | N/A | To be filed | TBD | CPUC | likely PTC | Unknown | 2018 (expected) | To be filed | 2017 | Planning | 2021 | 2021 | $24 Million - $28 Million | N/A | N/A | See "Actual Costs" |  | 2.1 | 0% | 100% | wood to steel to decrease fire risk
16 | TL691 Avo-Mon Wood to Steel | Camp Pendleton | wood-to-steel conversion and reconductor of an existing 69kv tieline | See "location" | See "purpose and need" | 8 |  |  |  | approx. 9 miles | N/A | 69kV | N/A | Yes |  |  | N/A | N/A | N/A | Not included in TPP | TBD | planning | TBD | CPUC | Advice letter or PTC | Advice letter or PTC | 2018 (expected) | To be filed | 2017 | Planning | 2020 | 2020 |  | N/A | N/A | See "Actual Costs" | N/A | 2.5 | 0% | 100% | wood to steel to decrease fire risk
17 | TL695/6971 Reconductor & Wood to Steel | Camp Pendleton | wood-to-steel conversion and reconductor of an existing 69kv tieline | See "location" | See "purpose and need" | 1 | 8 |  | changed from 6 to 1 | approx. 10 miles | N/A | 69kV | N/A | Yes |  |  | 2012 | 2011-2012 | N/A | Not available online | N/A | PEA deemed complete | MND | CPUC | PTC | PTC | 2016-04-01 | Filed and under review | 2017 | permitting | 2018 | 2019 | $12 Million - $15 Million | N/A | N/A | See "Actual Costs" | N/A | 3.8 | 0% | 100% | wood to steel to decrease fire risk
18 | TL697 San Luis Rey Wood to Steel | Camp Pendleton | wood-to-steel conversion and reconductor of an existing 69kv tieline | See "location" | See "purpose and need" | 8 | 1 |  | added 1 | approx. 3 miles | N/A | 69 | N/A | Yes |  |  | N/A | N/A | N/A | Not included in TPP | N/A | N/A | CatEx | CPUC | CatEx | CatEx | N/A | N/A | N/A | construction | 2018 | 2018 |  | N/A | N/A | See "Actual Costs" | N/A | 1.8 | 0% | 100% | wood to steel to decrease fire risk
19 | Wood to Steel Pole Replace.-TL6912 | Camp Pendleton | wood-to-steel conversion and reconductor of an existing 69kv tieline | See "location" | See "purpose and need" | 1 | 8 |  |  | approx. 6 miles | N/A | 69 | N/A | Yes |  |  | N/A | N/A | N/A |  | N/A | planning | CatEx or Advice Letter | CPUC | CatEx or Advice Letter | CatEx or Advice Letter | not yet filed - 2017 | to be filed | 2017 | planning | 2019 | 2019 |  | N/A | N/A | See "Actual Costs" | N/A | 1.6 | 0% | 100% | wood to steel to decrease fire risk
20 | Ocotillo Express-Interconnect. Switchyard | Imperial Valley |  | See "location" | See "purpose and need" | 2 |  |  |  | N/A | [6 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 48.5 | 1.1 | See "Actual Costs" |  | 0
21 | CSolar-Generator Interconnection | Imperial Valley | interconnection of large generator (PV) including new switchyard and tielines | See "location" | See "purpose and need" | 2 |  |  |  | N/A | [6 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 5.6 | 0.2 | See "Actual Costs" |  | 0
22 | Centinela-Generator Interconnection | Imperial Valley | interconnection of large generator (PV) including new switchyard and tielines | See "location" | See "purpose and need" | 2 |  |  |  | N/A | [6 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 0.0004 | 0 | See "Actual Costs" |  | 0
23 | Merchant Switchyard & Transmission | Boulder City, Nevada |  | See "location" | See "purpose and need" | 7 | [10 empty] | N/A | N/A | N/A |  | N/A | [12 empty] | 0 | 0 | See "Actual Costs" |  | 15.6
24 | Campo Verde Solar-Generator Interconnect. |  |  | See "location" | See "purpose and need" | 2 |  |  |  | N/A | [6 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 1.1 | 0 | See "Actual Costs" |  | 0
25 | Pio Pico Energy Ctr. Gen. Interconnect | Chula Vista | interconnection of large generator (natural gas turbines) | See "location" | See "purpose and need" | 2 |  |  |  | N/A | N/A | N/A | N/A | Yes |  |  | N/A | N/A | N/A | Not included in TPP | 2016 |  |  |  | catex | CatEx |  | complete |  | complete | N/A | 2016-04-21 |  | 9.7 | 0.3 | See "Actual Costs" |  |  |  |  | Large generator interconnection
26 | Sycamore-Penasquitos New 230KV TL | San Diego | Install a new 230 kV transmission line between existing Sycamore Canyon and Penasquitos Substations. | See "location" | See "purpose and need" | 1 | 5 |  | added 5 | 14 miles | NA | 230kV | NA | Yes | 2013-10-23 | SDG&E Board of Director approval | 2013 | 2012-2013 | N/A | http://www.caiso.com/Documents/BoardApproved2012-2013TransmissionPlan.pdf | 2018 | Final Certified | EIR | CPUC | Application | CPCN |  | Approved | 2016 | Construction | 2017-06-01 | 2018-06-01 | $133 Million | 0 | 0 | See "Actual Costs" | 260 | 133.2 | 100% | 0% | The project was identified by CAISO and state task force as necessary to ensure grid reliability and serve to strengthen renewable energy infrastructure in the region
27 | 500 KV Series Capacitor-ECO Sub | San Diego | Install new 500kV series capacitors at the ECO Substation | See "location" | See "purpose and need" | 4 |  |  |  | NA | work completed within existing footprint of ECO Substation | 500kV | NA | Yes | 2013 | Capital Budget Committee |  |  |  |  | See In-service date | Final Certified - Included as part of ECO Substation Project | EIR/EIS | CPUC/BLM | Application | PTC | 2009 | Approved | 2012 | Operational |  | In Service |  | 15 | 0.1 | See "Actual Costs" |  |  | 100% | 0% | The series capacitor helps provide voltage stability on the 500kV (SWPL) transmission line. Looping-in ECO onto SWPL significantly decreased the effectiveness of the existing series capacitors at the IV substation. Therefore a new series capacitor was needed at ECO to provide the voltage stability support
28 | TL674A Reconfigure/TL666D RFS | San Diego | Removal of approximately 6 miles of OH 69kV transmission line. To remove the line, an existing 69kV line will need to be reconfigured and extended into the Del Mar substation. In addition, two portions of separate existing 12kV lines will be converted from an OH to UG position. | See "location" | See "purpose and need" | 7 |  |  |  | 6 miles |  | 69kV |  | Yes | 2014 | SDG&E Board of Director approval | 2013 | 2012-2013 | N/A | http://www.caiso.com/Documents/BoardApproved2012-2013TransmissionPlan.pdf | 2019 | Application and PEA filed at CPUC | not determined yet. expect MND | CPUC and CCC | Application A. 17-06-029 | PTC | 2017 | Filed and under review |  | under review with CPUC | 2019 | 2019 | $12 Million - $15 Million | 0 | 0 | See "Actual Costs" |  | 2.2 | 0% | 100% | Meet Mandatory NERC reliability criteria in the Del Mar area. Address safety, environmental, and reliability concerns in the Del Mar area.
29 | Talega-Add Synchronous Condensers | Orange |  | See "location" | See "purpose and need" | 1 | [10 empty] | 2013 | 2012-2013 | N/A | http://www.caiso.com/Documents/BoardApproved2012-2013TransmissionPlan.pdf | N/A | [10 empty] | In Service |  | 84.2 | 0.4 | See "Actual Costs" |  |  | 100% | 0%
30 | IV West Generator Interconnection (Q608) | Imperial Valley | interconnection of large generator (PV) including new switchyard and tielines | See "location" | See "purpose and need" | 2 |  |  |  | N/A | N/A | N/A | N/A | Yes |  |  | N/A | N/A | N/A | Not included in TPP | 2015 | catex | catex |  | catex | CatEx |  | complete |  | complete |  | 2015-02-23 |  | 1.1 | 0.2 | See "Actual Costs" |  |  |  |  | Large generator interconnection
31 | New Vine 69/12KV Substation | San Diego | new 69/12 kv substation and loop in of existing tieline | See "location" | See "purpose and need" | 1 | 3 |  | added 3 | N/A | 1.5 Acre Sub | 69kV/12kV |  | Yes |  |  | 2015 | 2014-2015 | N/A | http://www.caiso.com/Documents/Board-Approved2014-2015TransmissionPlan.pdf | 2017 |  |  |  | Application A.14-05-021 | PTC | 2014 | Approved |  | In construction |  | 2017-11-01 |  | 0 | 0 | See "Actual Costs" |  | 30.3 | 0% | 100%
32 | Imperial Valley Flow Controller | Imperial Valley | Reliability driven need to regulate flow on TL23050, Imperial Valley- La Rosita 230kV Line by installing an 800 MVA flow control device. | See "location" | See "purpose and need" | 4 | [5 empty] | 230kV, 500kV |  | Yes |  |  | 2014 | 2013-2014 | N/A | http://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2017 | [8 empty] | In service | 2017-05-01 | 2017-05-01 | $55 Million - $300 Million | 48.9 | 0.6 | See "Actual Costs" |  |  | 100% | 0%
33 | Artesian 230kV Expansion-Prel. Eng. | San Diego | Loop In TL23051 to the existing 69/12kV Artesian substation to provide a new source into the 69kV system, creating TL23051 and TL23072. Reconductor TL6939 and new TL6974 from Artesian to Bernardo substation to support the increasing capacity needs in the system. | See "location" | See "purpose and need" | 1 | [5 empty] | 12kV, 69kV, and 230kV |  | Yes | 2018-04-01 |  | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | N/A |  |  |  | Application | PTC | 2017-08-16 | [5 empty] | $44 Million - $64 Million | 3.9 | 0 | See "Actual Costs" |  | 3.8
34 | San Luis Rey Synchronous Condensers | San Diego | Build a new shelter enclosed 230kV Gas Insulated Switchgear (GIS) and a new Control Shelter adjacent to the GIS. Install two +225/-120MVAr Synchronous Condensers enclosed in a new shelter facility. Install two 230/17.5/12.47kV generator step-up (GSU) transformers. Install two 230kV double circuit cable poles along with associated conduits. | See "location" | See "purpose and need" | 1 | 5 |  | added 5 |  |  | 230kV | Two 250MVA GSU Transformers | Yes | 2014-12-01 | SDG&E Board of Director approval | 2014 | 2013-2014 | N/A | http://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2017 |  |  |  | Does not require commission filing |  |  |  |  | Construction | 2017-06-01 | 2017-12-01 | $80 Million | 0 | 0 | See "Actual Costs" |  | 146.6 |  |  | To mitigate voltage stability concerns in response to the loss of generation at SONGS and South Bay Power Plants; along with the planned closure of Encina Power Plant and increase in renewable generation.
35 | Miguel 500kV Voltage Support | San Diego | Install two +225/-120MVAr Synchronous Condensers enclosed in a new shelter facility. Install two 230/17.5/12.47kV generator step-up (GSU) transformers. | See "location" | See "purpose and need" | 1 | [5 empty] | 500kV | One 500MVA GSU Transformer | Yes | 2015-04-01 | SDG&E Board of Director approval | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2017 |  |  |  | Does not require commission filing |  |  |  |  | Operational | 2017-03-31 | 2017-04-01 | $30 Million - $40 Million | 55.9 | 0.5 | See "Actual Costs" |  |  | 100% | 0% | To mitigate voltage stability concerns in response to the loss of generation at SONGS and South Bay Power Plants; along with the planned closure of Encina Power Plant and increase in renewable generation.
36 | TL6975 Escondido - San Marcos | Escondido to San Marcos | To address NERC Category B violations, this project proposes to install a second 69kV line between San Marcos substation and Escondido substation to provide a continuous rating of 137MVA. | See "location" | See "purpose and need" | 1 |  |  |  |  | Escondido, San Marcos | 69kV, 12kV |  | Yes |  |  | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2020 |  |  |  | Application | PTC | 2017-11-01 |  |  | Design |  | 2020-11-01 | $18 Million - $22 Million | 0 | 0 | See "Actual Costs" |  | 2.4 | 0% | 100%
37 | TL13835 Wood to Steel | Camp Pendleton | wood-to-steel conversion and reconductor of an existing 69kv tieline | See "location" | See "purpose and need" | 1 | 8 |  |  | approx. 1 mile | N/A | 69kV | N/A | Yes |  |  | N/A | N/A | N/A | Not included in TPP | 2018 | waiting on CPEN | Catex (CPUC); REIR CPEN | CPUC? CPEN? | Catex | CatEx |  | waiting on CPEN |  | design/permitting |  | 2018 |  | N/A | N/A | See "Actual Costs" |  | 0.4 | 0% | 100% | wood to steel to decrease fire risk
38 | Jacumba Solar Gen Interconnect (Q644A) | Jacumba | Small Generation Interconnection agreement with Jacumba Solar Farm generator to connect to the ECO substation via 138kV transmission line. | See "location" | See "purpose and need" | 2 |  |  |  |  | ECO | 138kV |  |  |  |  | N/A | N/A | N/A | Not included in TPP | 2017 | [8 empty] | In service |  | 2017-07-17 |  | 2.9 | 0.1 | See "Actual Costs"
39 | Tule Wind - Generator Interconnect | San Diego | Large Generation Interconnection agreement with Tule Wind generator to connect to Boulevard Ease Sub via a 138kV transmission line. | See "location" | See "purpose and need" | 2 |  |  |  |  | Boulevard Substation | 138kV |  | Yes | 2011 |  | N/A | N/A | N/A | Not included in TPP | 2017 | [8 empty] | In construction |  | 2017-10-01 |  | 0.7 | 0 | See "Actual Costs"
40 | Mid-Coast Trolley Extension Project | San Diego | Temporary and permanent relocation of tielines to allow for new train tracks (TL604, 612, 611, 613, 617) | See "location" | See "purpose and need" | 7 |  |  |  | N/A | N/A | 69 and 12 kv | N/A | Yes | 2016 | SDGE BoD | N/A | N/A | N/A | Not included in TPP | See In-service date | N/A | CatEx | Permitted under SANDAG project | N/A - does not require commission filing | N/A - does not require commission filing | N/A | N/A | N/A | Planning and in construction | various | various |  | 2.5 | 14.9 | See "Actual Costs" |  | 0 |  |  | relocate gas and electric facilities so SANDAG can construct additional train tracks for their Mid Coast Trolley project (http://www.sandag.org/index.asp?projectid=250&fuseaction=projects.detail).
41 | TL690A | Camp Pendleton | wood-to-steel conversion and reconductor of an existing 69kv tieline | See "location" | See "purpose and need" | 1 | 8 |  |  | approx. 3 miles | N/A | 69 | N/A |  |  |  | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2018 | approved | catex | CPUC | catex | CatEx |  | N/A |  | construction |  | 2018 | $24 Million - $28 Million | N/A | N/A | See "Actual Costs" |  | 1.5 | 0% | 100% | wood to steel to decrease fire risk
42 | Carlsbad Energy Center Project | San Diego | Large Generation Interconnection agreement with Carlsbad Energy Center consisting of six combustion turbines with a net output of 633MW interconnecting to Encina Substation | See "location" | See "purpose and need" | 2 |  |  |  |  | Encina Sub | 138kV/230kV |  |  |  |  | N/A | N/A | N/A | Not included in TPP | See In-service date | [8 empty] | In construction |  | 138kV Feb 2018 - 230kV Mar 2018 |  | 0 | 0 | See "Actual Costs" |  | 1.4
43 | Vista Energy Storage Project | San Diego | Small Generation Interconnection agreement with Vista Energy Storage to bring 20MW of battery energy and interconnect to 69kV bus at Melrose Substation. | See "location" | See "purpose and need" | 2 |  |  |  |  | Melrose Sub | 69kV |  |  | 2016 |  | N/A | N/A | N/A | Not included in TPP | N/A | [8 empty] | In construction | 2018-04-01 |  |  | 0 | 0 | See "Actual Costs" |  | 0.5
44 | MIGUEL TO BAY BLVD NEW 230KV LINE | San Diego | Construction of a new 230kV line between Miguel and Bay Blvd substation to be added to open side of existing poles. Cross arms, insulators and hardware will be added to 55 existing structures. Transmission pole outside Bay blvd substation to be replaced with a cable pole to allow one of the lines to be converted from overhead to underground going into the substation. | See "location" | See "purpose and need" | 1 |  |  |  | Approximately 10 miles |  | 230kV |  | Yes | 2017 | Capital Budget Committee | 2016 | 2015-2016 | N/A | https://www.caiso.com/Documents/Board-Approved2015-2016TransmissionPlan.pdf | 2018 | N/A | No discretionary permit |  | N/A - does not require commission filing | N/A - does not require commission filing |  |  |  | Planning | 2018-12-31 | 2018-12-31 | $20 Million - $45 Million | 0 | 0 | See "Actual Costs" |  | 0.3 | 100 | 0 | The main objectives are to mitigate all NERC thermal violations, reinforce the southern 230kV loop and increase operational flexibility of the system.
45 | Expedited Storage Procurement (ESP) | San Diego | 37.5 MW of battery energy storage connected to Escondido Sub (30MW) and El Cajon Sub (7.5 MW) | See "location" | See "purpose and need" | 2 | [5 empty] | 12kV |  | Yes | 2016 | SDG&E Board of Director Approval | N/A | N/A | N/A | Not included in TPP | 2017 | N/A | No discretionary permit |  | AL | AL | 2016 | Approved | 2016 | Operational | 2017-01-31 | 2017-03-03 |  | 2.6 | 89 | See "Actual Costs" |  |  | 0 | 100 | Improve reliability due to concerns regarding potential natural gas shortages
46 | BC14XXX (TL6906 MESA RIM LOOP-IN) | San Diego | Loop in two new lines (TL6906 and TL6978) into Mesa Rim 69kV Substation and replace existing wood cable poles with new steel poles. | See "location" | See "purpose and need" | 1 | 8 | 7 | added 7 | Approximately 1,500 feet |  | 69kV |  | Yes | 2015 | Capital Budget Committee | 2014 | 2013-2014 | N/A | http://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2018 | N/A | No discretionary permit |  | TBD | TBD |  |  |  | Planning | 2018-12-31 | 2018-12-31 | $5 Million - $7 Million | 0 | 0 | See "Actual Costs" |  | 0 | 0% | 100% | Improve reliability by adding a third and fourth power line via loop-in of TL6906 to Mesa Rim Substation. The existing wood cable poles have been identified by our compliance program to be replaced due to deterioration.
47 | Synchronized Phasor Measurement System |  |  | See "location" | See "purpose and need" | 9 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 3.8 | 6.2 | See "Actual Costs" |  | 3
48 | Install Bank 61 At Miguel | San Diego Co. | Miguel (1) Tap TL138 into Miguel Bank 60 (2) This project will add a 138kV disconnect and breaker to the 138kV side of Bank 60. TL13824 will be brought in to connect to this equipment along with all associated relaying. This work is authorized by Master Work Order PSS0002. Los Coches (3) This project will replace four 138kV disconnects and two 138kV breakers to the existing TL13824 position. TL13824 relaying will also be replaced. This work is authorized by Master Work Order PS0002. South Bay (4) This project will replace the existing TL13824 relays. This work is authorized by Master Work Order PS0002. Sycamore Canyon (5) This project will purchase and install a new spare 230/138kV transformer on a foundation at Sycamore Canyon. This work is authorized by Master Work Order PS0002 | See "location" | See "purpose and need" | 6 | 7 |  |  | N/A | 4 | 230/138 kV | 392 MVA (Bank 61) | Yes | (1) 2011 (2) 2011 (3) 2010 (4) 2010 (5) 2010 | Capital Budget Committee |  |  |  |  | See In-service date | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 12/31/2012 (2) 12/31/2012 (3) 12/1/2011 (4) 12/1/2011 (5) 12/1/2011 | In Service |  | 7.5 | 0.1 | See "Actual Costs" |  |  | 70 | 30
49 | Otay Substation Rebuild | San Diego Co. | (1) Convert 69 kV transfer bus to a main bus (2) Replace six 69 kV breakers (3) Install two 69/12 kV transformer banks (4) Install 12 kV switchgear (5) Install two 7.2 MVAR stepped 12 kV capacitors (6) Install new control house | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 0.8 | 69/12 kV | 28 MVA (Bank 30) | Yes | 2006 | Capital Budget Committee |  |  |  | Not included in TPP | 2013 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2009 | 2013-12-31 |  | 7.6 | 7.4 | See "Actual Costs" |  | 0 | 0 | 100
50 | Substation Security Installations |  | Install new or upgrade existing and/or replace security systems at 59 substations to comply with NERC CIP guidelines. | See "location" | See "purpose and need" | 9 |  |  |  | N/A | N/A | N/A | N/A | Yes | 2008 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | N/A | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | On-Going | On-Going | Ongoing |  | 43.4 | 3.2 | See "Actual Costs" |  | 0 | 30 | 70
51 | IV Sub Bank 82 Addition | Imperial Valley Co. | Preliminary Engineering (1) Add four sets of reactors to BK82. Opened on the 1145 for Preliminary Engineering Only. Authorization for this work is covered by Master Work Order 5985198. (2) This work order is written to fund the modification of the 500kV reactor by adding a Southern States Circuit Switcher in series with the circuit breaker. Authorization is on Master WO 5985198. (3) This work order is written to provide funds for the replacement of the remaining 230kV and 500kV porcelain CVTs and PTs. Authorization for this work is covered under Master Work Order 5985198. (4) This work order is for the addition of seismic springs to the tiedowns at IV Sub. Authorization for this work is covered by Master Work Order 5985198. (5) Provide the necessary network upgrades to interconnect the Imperial Valley Solar Facility to the 230kV bus at the Imperial Valley Substation (6) Provide facilities to interconnect the Imperial Valley Solar Project to the 230kV bus at the Imperial Valley Substation (7) Install Bank 82 (500/230kV) at the Imperial Valley Substation. Bank 82 is a delivery network upgrade required for the IV Solar Project. (8) Install protective relays in the AES substation to connect into Drew Switchyard. Connect fiber optics to communications panel. | See "location" | See "purpose and need" | 2 | 6 |  |  | N/A | 64 | 500/230 kV | 1000 MVA (Bank 82) | Yes | (1 - 4) 2014 (5-7) 2010 (8) 2013 | Capital Budget Committee |  |  |  |  | 2013 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 12/1/2015 (2) 12/31/2014 (3) 12/31/2014 (4) 12/1/2015 (5) 12/31/2011 (6) 12/31/2011 (7) 12/31/2011 (8) 9/15/2013 | 2013-11-15 |  | 18.2 | 0.2 | See "Actual Costs" |  | 0 | 100 | 0
52 | 69KV & 12KV Capacitor Installation (Rincon) (Lilac) (Santa Ysabel) (Warners) | San Diego Co. | (1) Install 69kV and 12kV capacitor banks at various substations in the eastern part of the electric transmission system to resolve steady state and post contingency voltage issues. Rincon (2) Install permanent new foundation steel pole for TL683 at Rincon Substation (3) Set concrete foundation for new steel pole for TL683 at Rincon Substation (4) Re-string new 636 ACSS Conductor from Z247132 to substation rack. Top transmission pole Z214709 1ft above 12kV. Return TL682 and TL683 to normal configuration. (5) Install 12kV Capacitor Banks A&B (6) Add 69kV Capacitor Banks 1 & 2 at Rincon Substation under Master WO 5984590. Lilac (7) Install 12kV Capacitor Bank C (8) Install 69kV Capacitor Banks 1 and 2 Santa Ysabel (9) Install 12kV Capacitor Bank (10) Add 69kV Capacitor Banks 1 and 2 at Santa Ysabel Substation under Master WO 5984590 Warners (11) Install 12kV Capacitor Bank (12) Add 69kV Capacitor Bank 1 and 2 | See "location" | See "purpose and need" | 1 | 10 |  |  | N/A |  |  |  | Yes | (1) 2012 (2) 2012 (3) 2012 (4) 2014 (5) 2009 (6) 2010 (7) 2009 (8) 2010 (9) 2009 (10) 2010 (11) 2009 (12) 2010 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | See In-service date | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 12/1/2014 (2) 6/1/2012 (3) 6/1/2012 (4) 4/30/2014 (5) 6/1/2009 (6) 12/1/2011 (7) 6/1/2010 (8) 12/1/2011 (9) 6/1/2010 (10) 12/1/2011 (11) 6/1/2010 (12) 12/1/2011 | (6) 6/23/13 (8) 12/18/13 (10) 7/19/13 (11) On Hold |  | 12 | 1.9 | See "Actual Costs" |  | 0 | 0 | 100
53 | Overstressed Breaker Replacements (Escondido) (Rose Canyon) (Murray) (El Cajon) (Division) (Penasquitos) (Mission) (Genesee) (Montgomery) (Melrose) |  | Escondido (1) This work order will replace 69kV overstressed breakers at Escondido Substation as identified by Transmission Planning's short circuit study. All of the breakers being replaced are oil circuit breakers and the new breakers are gas. Rose Canyon (2) Remove four overstressed 69kV breakers and replace with new 69kV 40kA breakers. This work order will be under the Master Work Order for Budget 9170 - PET0002 Murray (3) Remove six overstressed 69kV breakers and replace with new 69kV 40kA breakers. This work order will be under the Master Work Order for budget 9170 - PET0002 El Cajon (4) Remove eight overstressed 69kV breakers and replace with new 69kV 40kA breakers. This work order will be under the Master Work Order for budget 9170 - PET0002 Division (5) Remove five overstressed 69kV breakers and replace with new 138kV 63kA breakers. This work order will be under the Master Work Order for budget 9170 - PET0002 Penasquitos (6) This work order will replace 69kV overstressed breakers at Panasquitos Substation as identified by Transmission Planning's short circuit study. 21 of the breakers being replaced are oil circuit breakers and 6 are gas breakers. All breakers are being replaced with new rated gas breakers. This work order is authorized under the approved Master Work Order PET0002 Mission (7) This work order will replace twenty one 69kV overstressed breakers at Mission Substation as identified by Transmission Planning's short circuit study. All breakers are being replaced with new rated gas breakers. Genesee (8) Remove six overstressed 69kV breakers and replace with new 69V 40kA breakers. This work order will be under the MASTER work order for budget 9170 - PET0002 Montgomery (9) Remove four overstressed 69kV breakers and replace with new 69kV 40kA breakers. Add the 69kV Bus Tie Breaker. This work order will be under the MASTER work order for budget 9170 - PET002 (10) This work order is written to provide funds for the addition of a control shelter. Authorization for this work is covered under Master Work Order 5985198. Melrose (11) Remove five overstressed 69kV breakers and replace with new 69kV 40kA breakers. This work order will be under the MASTER work order for budget 9170 - PET002 | See "location" | See "purpose and need" | 10 | 6 |  | added 6 | N/A | N/A | 69 kV | N/A | Yes | (1) 2010 (2) 2014 (3) 2014 (4) 2014 (5) 2014 (6) 2011 (7) 2012 (8) 2014 (9) 2014 (10) 2014 (11) 2014 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2015 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 12/1/2011 (2) 1/20/2015 (3) 1/30/2015 (4) 1/30/2015 (5) 12/30/2015 (6) 12/15/2012 (7) 12/15/2014 (8) 1/30/2015 (9) 12/30/2015 (10) 12/1/2015 (11) 12/30/2015 | 2015-08-26 |  | 22.1 | 0.5 | See "Actual Costs" |  | 0 | 0 | 100
54 | Los Coches Sub-Rebuild 138/69kV | San Diego Co. | Miguel (1) Upgrade TL632 Protection Granite (2) Upgrade TL632 Protection Los Coches (3) Phase 3 Includes: Removal of the existing 69kV shelter and half of the 69kV rack including foundations. Grading the yard between the two energized buses. Continuation of the new 12kV and 69kV racks and install of bank 31. This work order is authorized under parent work order number PSS0012 (4) Los Coches Substation - Upgrade the existing facilities and install a new 230kV bus. Approval for this work is covered under Master Work Order 5985198. Funding for this work is included in the current blanket budget 1145. (5) Relocate transmission facilities to accommodate new 138kV substation bus system (6) Construct install trench and duct package to accommodate the rebuilding of Los Coches 138kV substation (TL632) (7) Construct - Install 424' UG Cable and accessories to accommodate the rebuilding of Los Coches 138kV substation (8) Construct Install Trench and duct package to accommodate the rebuilding of Los Coches 138kV substation (TL631) (9) Construct- Install 263' UG Cable and accessories to accommodate the rebuilding of Los Coches 138kV substation (10) Engineering and design to re-arrange the transmission circuit for TL13819 and TL13824 in order to accommodate rebuild at Los Coches Substation (11) Install four (4) each micropile foundations (12) Engineering and design to re-arrange the transmission circuit TL13824 in order to accommodate rebuild at Los Coches Substation (13) Engineering and design to re-arrange the transmission circuits in order to accommodate the rebuild at Los Coches Substation (14) Engineering, design, and construction to install two 69kV cable pole foundations for TL632/TL6914 to accommodate Los Coches rebuild (15) Relocate TL632 to accommodate substation rebuild (16) Site development for the initial phase of the project to include: grading, drainage, site walls, fencing, access road, bioretention basin, landscaping, and irrigation. Installation of a new 138kV bus to off load the existing bus to make room for the 69kV bus. This work order is authorized under parent work order number PSS0012. (17) Los Coches Modification Project - Capital Cost Accrual & Retention for Work Order 5984790. This work order is authorized under parent work order number PSS0012. (18) Phase 2 includes removal of all above and below grade structures from the existing 138kV yard. Grading the yard to appropriate level, creating a temporary and permanent access roads to the pad, installation of a control shelter, 1/2 the 69kV rack, two distribution transformers, and eight 12kV circuits, along with associated 12kV capacitors and relation of one 69kV capacitor. This work order is authorized under parent work order number PSS0012. Santee (19) Replace TL13819 relay panel at Santee | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 2.3 | 138/69 kV | 224 MVA (Bank 51) | Yes | (1- 2) 2015 (3) 2016 (4) 2010 (5) 2013 (6) 2015 (7) 2016 (8) 2015 (9) 2016 (10) 2015 (11) 2015 (12) 2014 (13) 2014 (14) 2016 (15) 2015 (16) 2013 (17) 2013 (18) 2014 (19) 2014 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | See In-service date | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Construction | (1-3) 6/1/2016 (4) 12/30/2014 (5) 5/30/2015 (6) 4/15/2016 (7) 3/13/2016 (8) 4/15/2015 (9) 5/13/2016 (10) 12/1/2018 (11) 2/27/2015 (12) 12/1/2018 (13) 12/1/2014 (14) 12/1/2016 (15) 5/29/2015 (16) 6/1/2016 (17) 6/1/2016 (18) 6/6/2018 (19) 3/1/2015 | Phase 1 ISD - 11/10/15 Phase 2 ISD - 8/31/16 Phase 3 ISD - 8/21/17 Phase 4 ISD - 2/9/18 |  | 57 | 13.7 | See "Actual Costs" |  | 14.7 | 5 | 95
55 | Sunnyside 69/12kV Rebuild | San Diego Co. | (1) This project will relocate TL628 get always that feeds Sunnyside Substation rebuild project. (2) This project will rebuild Sunnyside 69/12kV substation to replace obsolete equipment, increase capacity and allow the tielines to be undergrounded. This is the Master Work for this project. (3) This work order is written to fund the engineering assessment of Sunnyside Substation. This work order will be moved to a specific budget once the scope and cost has been determined. Approval for this work is covered under Master Work Order 5985198. | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 0.6 | 69/12 kV | 28 MVA | Yes | (1) 2014 (2) 2012 (3) 2012 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2014 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 12/31/2014 (2) 12/1/2013 (3) 12/31/2013 | 2014-12-17 |  | 10.3 | 5 | See "Actual Costs" |  |  | 0 | 100
56 | SCADA Expansion-Transmission (Carlton Hills) (San Mateo) (San Ysidro) |  | Carlton Hills (1) This work order provides funds to install Transmission SCADA at Carlton Hills Substation. This work order is approved under Master Work Order PSE0001. San Mateo (2) This work order provides funds to install transmission SCADA at San Mateo Substation. This work order is approved under Master Work Order PSE0001 San Ysidro (3) This work order installs transmission SCADA and RTU. This work is approved on Master Work Order PSE0001 | See "location" | See "purpose and need" | 9 |  |  |  | N/A | N/A | 69 kV | N/A | Yes | 2012 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2015 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2013-12-31 | 2015-02-09 |  | 5.3 | 0.5 | See "Actual Costs" |  |  | 0 | 100
57 | Penasquitos-Add 230kV Capacitor Banks | San Diego Co. | Install (2) 230 kV, 75 MVAr capacitor banks at Penasquitos Substation to provide stead state and contingency voltage support. | See "location" | See "purpose and need" | 1 |  |  |  | N/A | 7 | 230 kV | 392 MVA (Bank 60), 224 (Bank 70/71) | Yes | 2012 | Capital Budget Committee |  |  |  |  | 2013 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2013-06-01 | 2013-07-10 |  | 7.2 | 0.1 | See "Actual Costs" |  |  | 100 | 0
58 | Sycamore Canyon-Add 60 KV Reactor Banks | San Diego Co. | Install (4) 59kV, 50MVAr reactor banks at Sycamore Canyon Substation to provide steady stete and contingency voltage support | See "location" | See "purpose and need" | 10 |  |  |  | N/A | 11 | 230/138/69 kV | 392 MVA (Bank 60), 224 MVA (Bank 70/71) | Yes | 2012 | Capital Budget Committee |  |  |  |  | 2014 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2013-12-31 | 2014-06-26 |  | 4.8 | 0 | See "Actual Costs" |  |  | 0 | 100
59 | Sta F Substation Improvements |  | This work order revision is written to fund the engineering, architectural assessment, and improvements of Station F substation building. This revision updates the actual approved costs and moves this work order to its specific budget 13126. | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 0.7 | 69/12 kV | 28 MVA | Yes | 2014 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2013 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2014-12-31 | 2013-12-20 |  | 1.5 | 0 | See "Actual Costs" |  |  | 0 | 100
60 | Miguel Substation BK 80 Replacement |  | (1) This work order is written to fund the repair/replacement of ML BK 80 C phase transformer. This revision increases the amount of this work order to $9,388,000 (including AFUDC) and transfers this work order to budget 13127. It also changes scope of work from repair to replacement. (2) This work order is written to fund the replacement of the spare phase for BK82 (Imperial Valley) | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 3.8 | 500/230 kV | 1120 MVA (Bank 80) | Yes | 2013 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2013 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 6/30/2014 (2) 12/31/2014 | 2013-06-18 |  | 1.7 | 0 | See "Actual Costs" |  |  | 100 | 0
61 | Shunt Reactor on Suncrest 500kV Bus | San Diego Co. | Suncrest (1) This work order is written to fund the installation of three 500kV reactors, one 500kV disconnect, one 500kV Circuit Breaker, one 500kV circuit switcher, and associated relaying. Authorization by Master Work Order PSS0013 (2) This work order is written to fund the installation of a spare 500kV Reactor at Suncrest Sub Imperial Valley (3) This work order is written to fund the installation of a spare 500kV reactor at Imperial Valley Sub Miguel (4) This work order is written to fund the installation of a spare 500kV reactor at Miguel Sub. Authorization by Master Work Order PSS0013 | See "location" | See "purpose and need" | 10 |  |  |  | N/A | 36 | 500/230 kV | 1120 MVA (Bank 80) | Yes | (1) 2013 (2) 2013 (3) 2013 (4) 2013 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2017 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Construction | (1) 12/31/2014 (2) 6/30/2015 (3) 6/30/2015 (4) 6/31/2015 | 2017-10-14 |  | 9.7 | 0 | See "Actual Costs" |  | 0 | 100 | 0
62 | Talega Bank 50 Replacement |  | (1) This work order funds Talega Bank 50 replacement and installation of system spare at Talega. This WO will serve as master WO. (2) Move 980575 from Los Coches to Talega and install at Bk 50 This work will be done under the Master Work Order 5981145 authorized expenditures of $4.2 M | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 4.2 | 138/69 kV | 224 MVA (Bank 50) | Yes | (1) 2013 (2) 2015 | Capital Budget Committee |  |  |  | Not included in TPP | 2014 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 6/1/2014 (2) 6/1/2016 | 2014-03-07 |  | 3.3 | 0 | See "Actual Costs" |  |  | 0 | 100
63 | Wabash Substation Rebuild |  | (1) This job installs the last span of conductor from Z252307 to the substation rack this connects TL652 into Wabash Substation. (2) Approval for this work is covered under Master Work Order PSS0015 Rev 1 is to move WO5984755 onto the master WO and for the full design and construction of the substation. | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 0.7 | 69 kV | N/A | Yes | (1) 2014 (2) 2013 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2014 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 12/31/2014 (2) 12/31/2014 | 2014-12-19 |  | 10 | 1.1 | See "Actual Costs" |  |  | 0 | 100
64 | Kearny 69/12KV Sub Rebuild/Reloc-Pre Eng |  | (1) Install two new cable poles to bring TL600 and TL672 underground into the new 69kV rack at Kearny Substation. Remove approximately five spans of OH conductor and poles from Z96111 to Old Kearny Substation. Install cable and trench for TL663 from vault along Complex Dr. to new 69KV rack at Kearny Substation. Parent Work Order Number: PSS0028 Kearny 69/12 Substation Rebuild Master Work Order Approved to $39,568,000. (2) This work order is for engineering, design, and construction of relocating/rebuilding existing Kearny Sub to SDG&E owned property to the West. This revision 1 of this work order moves this under the Parent Work Order PSS0028 and revises costs from prelim engineering to total overall substation costs. | See "location" | See "purpose and need" | 7 |  |  |  | N/A | 1.8 | 69/12 kV | 28 MVA (Bank 30) | Yes | 2016 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2018 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Planning | (1) 5/1/2018 (2) 6/1/2016 | 2018-12-01 |  | 0 | 0 | See "Actual Costs" |  | 6.8 | 0 | 100
65 | SONGS Station Light & Power |  | Install two sets of 3-phase, 230kV-480V, 300kVA, Station Light & Power transformers one at the east bus and one at the west bus to accommodate removal of the current 4kV source from the power plant side. Revision 2 updates the ISD and adds approx. $270k to project cost due to construction constraints and added scope of splitting the battery load. | See "location" | See "purpose and need" | 7 |  |  |  | N/A | N/A | 230 kV | N/A | Yes | 2016 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2016 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2016-06-30 | 2016-01-22 |  | 2.4 | 0 | See "Actual Costs" |  |  | 100 | 0
66 | Imperial Valley Sub Oper. Reliability & Security |  | (1) This work order is written to provide funds for the replacement of the obsolete manual SL&P switches with Trayer Switches. This will also incorporate the addition of the BK 82 tertiary as a source and upgrade automatic throwovers. This work will be partially billable to IID Authorization is on Master Work Order PIV0001. (2) This work order is written to provide funds for the installation of grounding wells at Imperial Valley substation. These will enhance the performance of the tieline relays during a fault. This work may be billable to IID, which will be determined at a later date. Rev 1 is issued to add funds for the additional ground grid required to be installed Master Work Order is PIV0001. (3) This work order is written to provide funds for the replacement of the control cable trench covers and the additional shoring of the trench walls. This work may be billable to IID, which will be determined at a later date. Authorization is on Master Work Order PIV0001. | See "location" | See "purpose and need" | 9 |  |  |  | N/A | 64 | 500/230 kV | N/A |  | 2015 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2017 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 6/30/2016 (2) 12/31/2015 (3) 6/30/2016 | 2017-04-29 |  | 11.1 | 0 | See "Actual Costs" |  |  | 100 | 0
67 | Encina Bank 61 | San Diego Co. | (1) This project will install a second 230/138kV transformer at Encina. The funds for this project are approved under master work order PSS0018 (2) The work order will replace the stock transformer used at Encina. The funds for this project are approved under the master work order PSS0018 | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 7 | 230/138 kV | 392 MVA (Bank 61) |  | 2015 | Capital Budget Committee |  |  |  |  | 2015 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | (1) 6/30/2016 (2) 6/1/2016 | 2015-11-20 |  | 11.7 | 0.1 | See "Actual Costs" |  |  | 100 | 0
68 | Poway Substation Rebuild (Rancho Carmel) |  | Poway (1) Install 3 new cable poles with foundation. Install approximately 2000ft of 3000KCML copper, 1000ft of 1750 copper, and 1000ft of ADDSS Fiber and associated hardware. Remove old transmission structures, wires, & hardware. (2) 69/12kV Low Profile Substation, seven (7) 69kV GCBs, two (2) 69/12kV banks, associated 69kV disconnects, eight (8) 12kV VCBs, control shelter, associated relays and communications, and SCADA control. Underground three existing 69kV TLs going into the substation. Site Development and move substation fence line to the property Substation Design Engineering Civil/Structural Engineering Land Environmental (3) Dig trench for COX Cable, To be paid for by COX. Rancho Carmel (4) Install new TL 648 Relay Panel. Remove existing relaying. | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 2.6 | 69/12 kV | 28 MVA (Bank 30) |  | 2015 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2018 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Construction | (1) 4/28/2018 (2) 12/1/2016 (3) 12/1/2016 (4) 6/1/2016 | 2018-02-26 |  |  |  | See "Actual Costs" |  |  | 0 | 100
69 | Silvergate Sub: Install Spare Transformer |  | Add one 230kV breaker, two 138kV breakers, two 230kV disconnects and all associated relays, controls and foundations. | See "location" | See "purpose and need" | 1 |  |  |  | N/A | 4.8 | 230/69 kV | 224 MVA (Bank 70) |  | 2015 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2016 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2015-10-01 | 2016-04-13 |  | 0.3 | 1.3 | See "Actual Costs" |  | 11.6 | 30 | 70
70 | Miguel Sub Hydro & Water Quality Enhance |  | Mitigate erosion of damage to slopes and structural damage to hydraulic conveyances at Miguel Substation. | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 14.5 | 500/230/138/69 kV | N/A |  | 2015 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2016 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Operational | 2016-06-01 | 2016-06-30 |  | 0 | 0 | See "Actual Costs" |  | 3.7 | 30 | 70
71 | Mission Bank 71 Addition | San Diego Co. | This project will remove Banks 51 and 52 and install a new Bank 71. This is authorized by the parent work order PSS0031 for this project | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 3 | 230 kV | 224 MVA (Bank 71) |  | 2016 | Capital Budget Committee |  |  |  |  | 2018 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Construction | 2017-12-01 | 2018-12-18 |  | 0 | 0 | See "Actual Costs" |  | 3.4 | 100 | 0
72 | Rancho Santa Fe Sub Fire Hardening (Encinitas) (Lake Hodges) (North City West) | San Diego Co. | Rancho Santa Fe (1) Install new two 1/4s switchgear, new 69/12kV standard profile 30 MVA transformer, new control shelter, new control panels, and associated relaying, equipment. Install new protective devices on the 12kV circuits. Remove existing 69/4kV transformer, 4kV breakers and switch rack, 12kV 1/4 switchgear, and 69/12kV MVA transformer (in spare position) Encinitas (2) Install new TL 674 Relay Panel. Remove existing relaying. Lake Hodges (3) Install new TL 616 Relay Panel. Remove existing relaying. North City West (4) Install new TL 674 Relay Panel. Remove existing relaying. | See "location" | See "purpose and need" | 8 |  |  |  | N/A | 0.5 | 69/12 kV | 28 MVA (Bank 30) |  | 2016 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2018 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Construction | 2018-04-01 | 2018-10-11 |  | 0 | 0 | See "Actual Costs" |  | 2.4 | 0 | 100
73 | Camp Pendleton Voltage Support | San Diego Co. | Basilone (1) Rev 1 is issued to move the work order to the 16128 budget. Authorization for this is on the Parent Work Order PSS0032. Pendleton (2) Rev 2 is to add the replacement of CB1, CB2, and CB3 to the WO for Pendleton 69kV Substation. CB1, CB2, and CB3 are being replaced as a result of age and CB type (Oil). Avocado (3) This work order is written to replace the relay panel at Avocado as part of the Pendleton Sub Rebuild. Authorization for this is on Parent Work Order PSS0032. Monserate (4) This work order is written to replace the relay panel at Monserate as part of the Pendleton Sub Rebuild. Authorization for this is on a Parent Work Order PSS0032. San Luis Rey (5) This work order is written to replace the relay panel at San Luis Rey as part of the Pendleton Sub Rebuild. Authorization for this is on Parent Work Order PSS032. | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 1 | 69 kV | 28 MVA (Bank 30/31) |  | (1) 2016 (2) 2017 (3) 2016 (4) 2016 (5) 2016 | Capital Budget Committee | 2016 | 2015-2016 | N/A | https://www.caiso.com/Documents/Board-Approved2015-2016TransmissionPlan.pdf | See In-service date | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Construction | (1) 12/31/2017 (2) 12/31/2017 (3) 12/31/2017 (4) 12/31/2017 (5) 12/31/2017 | (1) 9/1/17 (2) 1/26/18 |  | 0 | 0 | See "Actual Costs" |  | 4 | 0 | 100
74 | Warners Substation 69kV Control & Protection Replacement | San Diego Co. | Remove Old Relaying and control shelter and TL682 (985728) & TL686 (985429) OCBs Install New Relaying and new control shelter and new 69kV Bk 30 breaker (993842) and TL682 (988719) & TL686 (98820) GCBs. (from stock) | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 1.1 | 69/12 kV | 6 MVA (Bank 30) |  | 2016 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2017 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A |  | 2017-12-01 | 2017-12-04 |  | 0 | 0 | See "Actual Costs" |  | 2.6 | 0 | 100
75 | Descanso Substation 69kV Control & Protection Replacement | San Diego Co. | Replace Descanso Substation control shelter because it is too small for new control & protection requirements. | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 0.8 | 69/12 kV | 6 MVA (Bank 30) |  | 2016 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2017 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A |  |  | 2017-12-05 |  | 0 | 0 | See "Actual Costs" |  | 3 | 0 | 100
76 | Substation Auxiliary Power System (Sycamore) (Lilac) (Scripps) |  | Initial procurement of 1-GenCell 5kW Fuel Cells to be used as auxiliary power for substation control shelters. The GenCell hydrogen fuel cell will be installed at Cranking Path Black Start and Bulk Power Substations as an emergency power supply, to ensure uninterrupted communication, interrogation, control and protection during extended outages. The permanent installations will take the place of mobile battery or diesel generators, which are mobilized for extended outages. This installation is committed to (Sycamore, Lilac, & Scripps) Substation. | See "location" | See "purpose and need" | 9 |  |  |  | N/A | N/A | N/A | N/A |  | 2016 | Capital Budget Committee | N/A | N/A | N/A | Not included in TPP | 2018 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A |  | 2016-12-31 | 2018-02-13 |  | 0 | 0 | See "Actual Costs" |  | 1.6 | 0 | 100
77 | HVDC Conversion of Southwest Powerlink | Arizona, Imperial Valley Co., San Diego Co. | This work order is for preliminary engineering to the feasibility and costs of rebuilding and converting the SWPL to an HVDC transmission line. The costs include determining technology and developing permit requirements. | See "location" | See "purpose and need" | 4 |  |  |  | N/A |  |  |  |  | 2017 | Capital Budget Committee |  |  |  |  | 2019 | N/A | N/A | N/A | Does not require commission filing. | N/A | N/A | N/A | N/A | Planning | 2019-12-30 | 2019-12-30 |  | 0 | 0 | See "Actual Costs" |  | 1.1 | 100 | 0
78 | IV Bank 80 Replacement |  | TBD | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 64 | 500/230 kV | 1000 MVA (Bank 80) | Planning | Planning | [5 empty] | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | Planning | TBD | TBD |  |  |  | See "Actual Costs" |  |  | TBD | TBD
79 | Avocado Sub Rebuild |  | TBD | See "location" | See "purpose and need" | 6 |  |  |  | N/A | 1.7 | 69/12 kV | 28 MVA (Bank 31), 13 MVA (Bank 32) | Planning | Planning |  | N/A | N/A | N/A | Not included in TPP | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | Planning | TBD | TBD |  |  |  | See "Actual Costs" |  |  | TBD | TBD
80 | Camp Pendleton Tower Lighting | San Diego/Orange | Install aviation warning lights to comply with Camp Pendleton Air Operations. Install 68 light on tie lines numbers 23030, 23006, 23002, 23010. Also improve access roads and install access ladders on towers. | See "location" | See "purpose and need" | 8 |  |  |  | N/A |  | 230 |  |  |  |  | N/A | N/A | N/A | Not included in TPP | 2012 | [9 empty] | Initiated in 2007 | Completed in 2012 |  | 2.7 | 0 | See "Actual Costs"
81 | TL6910-Miguel to Border SW Pole Replace | San Diego | Reliability project on 69kV transmission line TL6910 to replace wood poles with steel poles in fire threat areas to mitigate fire risks in fire prone areas. | See "location" | See "purpose and need" | 8 |  |  |  | 4.5 miles |  | 69 |  |  | 2009 |  | N/A | N/A | N/A | Not included in TPP | 2013 | [9 empty] | 2012-12-31 | 2013-08-01 |  | 8.4 | 0.4 | See "Actual Costs"
82 | TL616-Rancho Santa Fe-Bernardo-Lake Hodges SW Pole | San Diego | Replace approximately 70 wood poles with SW poles and associated transmission, distribution and communication overhead hardware for the TL616 wood to steel project. The existing transmission conductor will be transferred to the new steel poles. | See "location" | See "purpose and need" | 8 |  |  |  | 4 miles |  | 69 |  |  | 2009 |  | N/A | N/A | N/A | Not included in TPP | 2012 | [9 empty] | 2012-12-31 | 2012-06-01 |  | 9.9 | 1.5 | See "Actual Costs"
83 | TL6914 Los Coches-Loveland SW Pole Replace | San Diego | To replace wood poles with steel poles on TL6914 between Los Coches Substation and Loveland Substation. | See "location" | See "purpose and need" | 8 |  |  |  | 12 miles |  | 69 |  | Yes | 2009 |  | N/A | N/A | N/A | Not included in TPP | 2015 |  |  |  | AL | Advice letter | 2012 | Approved |  | complete | 2013-03-31 | 2015-08-01 |  | 32.9 | 9.5 | See "Actual Costs" |  |  |  | 100%
84 | TL 6913 Poway-Pomerado SW Pole Replace. | San Diego | Capacity project to reconductor 69kV transmission line TL6913 between Poway and Pomerado substations to meet the requested rating of 148MVA. | See "location" | See "purpose and need" | 1 | 8 |  |  | 3 miles |  | 69 |  |  | 2009 |  | N/A | N/A | N/A | Not included in TPP | 2012 | [9 empty] | 2012-12-31 | 2012-12-31 |  | 8 | 1.2 | See "Actual Costs"
85 | TL694A Melrose Loop-In Project | San Diego | This CAISO approved project is necessary to improve electric reliability to the surrounding region. The current arrangement leaves Melrose potentially islanded during a N-1 contingency. The scope of the work includes but is not limited to the installation of 5 miles of new underground underground infrastructure with 3000 KCMIL copper cables, the installation of 3 new cable poles, and associated substation work. The work will impact existing TL694A. | See "location" | See "purpose and need" | 1 |  |  |  | 5 miles |  | 69 |  |  | 2011 | [5 empty] | 2013 | [9 empty] | 2013-08-31 | 2013-08-31 |  | 33.8 | 0.14 | See "Actual Costs"
86 | TL676 Mission to Mesa Heights Reconductor | San Diego | Reconductor TL676 (including some 12kV underbuild) from Mesa Heights to Mission Substation, and install new UG getaways into the substations. Replace approx 85 existing wood poles with steel poles. | See "location" | See "purpose and need" | 1 |  |  |  | 4.3 miles |  | 69 |  |  | 2009 |  | 2011 | 2010-2011 | N/A | Not available online | 2018 | [9 empty] | 2018-12-01 | 2018-12-31 | $19 Million | 0 | 0 | See "Actual Costs" |  | 5
87 | New TL ES-Ash #2 | San Diego | Install a new 69kV Transmission line from Escondido Substation to Ash Substation. Line was built in a underground duct package. The cable installed was 3000 kcmil Cu. The line has a rating of 174 MVA. | See "location" | See "purpose and need" | Richard Rodriguez |  |  |  | 3.2 miles |  | 69 |  |  | 2009 |  | 2009 | 2008-2009 | N/A | Not available online | 2013 | [9 empty] | 2012-12-31 | 2013-02-14 | $8.8 Million | 30.3 | 1.5 | See "Actual Costs"
88 | Trans. SCADA Network Upgrade |  | EMS XA/21 is a Supervisory Control and Data Acquisition (SCADA) application used to control the bulk electric system assets of SDG&E. For reliability, security and regulatory reasons, the production system is on a dedicated secure network that runs independently from the corporate network. The current release (R11) or XA/21 needs to be upgraded to release 15 (R15). The upgrade can be accomplished using the production network infrastructure, however this introduces reliability and compliance risk. To mitigate this risk, this project will build out new network infrastructure, with additional firewalls, to implement this new release and also improve our security design. | See "location" | See "purpose and need" | 9 |  |  |  | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A | Not included in TPP | 2013 | [9 empty] | 2013-12-31 | 2013-12-31 |  | 1.1 | 5.2 | See "Actual Costs"
89 | Borrego Solar 1 Interconnection | San Diego | Upgrade the Borrego 69kV Substation to accommodate a 20MW Solar Project that is seeking a 69kV interconnection to the Borrego Substation. Add a 69kV breaker and associated facilities to interconnect the solar project. Connect the project to Borrego Substation from the point of change of ownership with 1-500 KCMIL/AL cable in an underground duct package. | See "location" | See "purpose and need" | 2 |  |  |  | 0.1 miles |  | 69 |  |  | 2010 |  | N/A | N/A | N/A | Not included in TPP | 2012 | [9 empty] | 2012-11-30 | 2012-11-30 |  | 8.4 | 0.05 | See "Actual Costs"
90 | Ramona Transmission Reliability Project | San Diego | This project separates joint infrastructure, mitigates heavy mechanical load and fire hardens facilities on the tie line 635 and tie line 6917 with 12kV underbuild. | See "location" | See "purpose and need" | 6 | 7 |  | 8 | 0.76 miles |  | 69 |  |  | 2010 |  | N/A | N/A | N/A | Not included in TPP | 2013 | [9 empty] | 2013-12-31 | 2013-12-31 |  | 10.3 | 0.8 | See "Actual Costs"
91 | Hoodoo Switchyard on TL50002 | State of Arizona | Interconnection of 290 MW of solar power (CAISO Q468, Agua Caliente Solar) to TL50002 in Arizona. This required a 500 kV switchyard to be constructed approx. 50 miles east of Yuma Arizona. Arizona Public Service was responsible to design, construct and bill the generator for the switchyard. SDG&E is one of three utilities obligated to reimburse the generator for Hoodoo Wash (switchyard). Our responsibility was estimated in the LGIA to be $16.3 M, the actual costs were$13.7 M. | See "location" | See "purpose and need" | 2 |  |  |  | 1 mile |  | 500 |  |  |  |  | N/A | N/A | N/A | Not included in TPP | 2012 | [9 empty] | 2012-01-01 | 2012-01-01 |  | 14.3 | 0 | See "Actual Costs"
92 | TL 13833-W2S | San Diego |  | See "location" | See "purpose and need" | 1 |  |  |  | 5.8 miles |  | 138 |  |  | 2010 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A |  | 3.3 | 0.3 | See "Actual Costs" |  | 0
93 | TL663 Mission to Kearny Reconductor | San Diego | Purpose is to mitigate NERC Category B reliability criteria. The scope of work involves overhead and underground work. The overhead work entails re-conductoring the overhead line to provide a new minimum continuous rating of 204MVA from existing 97MVA (with a 9-hour emergency rating of 129MVA). This requires a complete re-conductor of overhead line from 1-1033.5 ACSR/AW and 2-336.4 ACSR/AW to 2-636 ACSS/AW (twin bundled). The underground portion of the project requires pulling new cable through existing ducts to create twin bundled 1750MCM Cu cable and undergrounding the OH portion on Murphy Canyon Road to Clairemont Mesa to Kearny Sub. | See "location" | See "purpose and need" | 1 |  |  |  | 5.8 |  | 69 |  |  | 2011 |  | 2011 | 2010-2011 | N/A | Not included in TPP | 2018 | [9 empty] | 2018-12-31 | 2018-12-31 | $18 Million | 0 | 0 | See "Actual Costs" |  | 8
94 | TL670 Mission to Clairemont Reconductor | San Diego | Capacity project to reconductor 69kV transmission line TL670 between Mission and Clairemont substations to meet the requested rating of 137MVA. | See "location" | See "purpose and need" | 1 |  |  |  | 8 miles |  | 69 |  |  | 2011 |  | 2011 | 2010-2011 | N/A | Not available online | 2013 | [9 empty] | 2013-12-31 | 2013-12-31 |  | 6.1 | 1 | See "Actual Costs"
95 | TL664-Wood to Steel | San Diego | Replace approx. 20 existing wood poles with steel poles, including installing engineered foundation poles near the railroad crossings for improved reliability. | See "location" | See "purpose and need" | 8 |  |  |  | Approx. 1 mile |  | 69 |  |  | 2011 |  | N/A | N/A | N/A | Not included in TPP | 2017 | [9 empty] | 2013-06-01 | 2017-06-01 |  | 2.5 | 0 | See "Actual Costs" |  | 0.2
96 | TL13804 Encina-Batiquitos-PQ-Wood to Steel | San Diego | This project will install 12 foundation at six locations for new engineered steel H-frame structures to replace existing wood structures. This project will install 60 steel H-frame structures to replace existing wood H-frames on TL13804 in fire threat area and transfer existing conductor on a portion of TL13804, as well as install about 6250' of new conductor on a portion of TL13804. | See "location" | See "purpose and need" | 8 |  |  |  | 4 miles |  | 138 |  |  | 2011 |  | N/A | N/A | N/A | Not included in TPP | 2013 | [9 empty] | 2012-12-31 | 2013-06-30 |  | 12.5 | 0 | See "Actual Costs"
97 | TL13835 and TL13837 UG Conversion | San Diego | Tie Line 13835 and Tie Line 13837 Laguna Niguel Underground Conversion - Cable, Splices, and Fiber Optic Cable. This project installs 9730 double circuit feet of 138kV trench with an additional spare duct set, substructures, cabling and fiber optics for TL13835 and TL13837 from Laguna Niguel substations for the underground conversion in Laguna Niguel, CA. | See "location" | See "purpose and need" | 7 |  |  |  | 1.8 miles |  | 138 |  |  | 2011 |  | N/A | N/A | N/A | Not included in TPP | 2013 | [9 empty] | 2013-12-31 | 2013-03-07 |  | 16.9 | 0.4 | See "Actual Costs"
98 | TL617 Direct Buried Cable Replacement | San Diego | This project replaces aging transmission underground infrastructure and involves the replacement of approximately 2.5 miles of direct buried cable with Cross-linked polyethyiene (XLPE) 1750 KCMIL copper cable in a newly constructed double circuit 69kV transmission duct infrastructure from La Jolla substation to cable pole Z63501 located on the top of Mount Soledad. | See "location" | See "purpose and need" | 6 |  |  |  | 2.5 miles |  | 69 |  |  | 2011 |  | N/A | N/A | N/A | Not included in TPP | 2014 | [9 empty] | 2013-06-30 | 2014-05-23 | Completed June 2013, also note, according to the PM, this project was a Categorical Exemption from PUC permitting thus not sure why there would be a PUC data request on this | 11.9 | 0 | See "Actual Costs"
99 | TL626 Reconductor | San Diego | This line is being removed from service as part of the approved alternative for the CNF project which instead has TL6931 being reconductored and rebuilt wood to steel. | See "location" | See "purpose and need" | 7 |  |  |  | 19 miles |  | 69 |  |  | 2011 |  | 2011 | 2010-2011 | N/A | Not available online | 2019 | [9 empty] | 2019-04-01 | 2019-04-01 |  | 5.4 | 0 | See "Actual Costs" |  | 0
100 | Camp Pendleton 12kV Service |  |  | See "location" | See "purpose and need" | 10 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 7.1 | 7.3 | See "Actual Costs" |  | 0
101 | TL613-Direct Buried Cable Replace. | San Diego | Reliability project to replace old vintage direct-buried cable in Pacific Beach to mitigate potential faults of 69kV transmission line TL613. | See "location" | See "purpose and need" | 6 |  |  |  | 2 miles |  | 69 |  |  | 2012 |  | N/A | N/A | N/A | Not included in TPP | 2014 | [9 empty] | 2014-06-01 | 2014-06-16 |  | 10.4 | 0 | See "Actual Costs"
102 | Pico Sub: Loop-In TL13833 |  | Loop in TL13833 to Pico substation, creating TL13846. | See "location" | See "purpose and need" | 1 |  |  |  | 0.2 miles |  | 138kV | [8 empty] | 2013 | [9 empty] | 2013-08-01 | 2013-08-01 |  | 2.6 | 0.06 | See "Actual Costs"
103 | Composite Core Conductor |  | This project will install composite conductor on key spans within the system to enhance the network. It has been determined the composite conductors will be of use for high temperature and low-sag applications. Prior to the selection of the composite core conductor, studies and evaluations will be done. A follow-up performance report will be compiled to reflect on the application of such new technologies and shared amongst industry peers. | See "location" | See "purpose and need" | R & D Project |  |  |  | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A | Not included in TPP | 2013 | [9 empty] | 2013-12-31 | 2013-12-31 |  | 4.9 | 0 | See "Actual Costs"
104 | Transmission ROW: Palos Verde-North Gila |  | This project is to pay the ROW expenses associated with SDG&E's share of the APS- Palos Verde - North Gila 500kV transmission line. This payment covers costs from January 2012 through December 31, 2016. Work authorized within this project is classified under the following accounts: 350.2 Lan and ROW (Transmission). This budget is required for SDG&E to pay their contractual agreement with Arizona Public Service for the allocation of the ROW costs of the Palos Verde - North Gila 500kV transmission line. | See "location" | See "purpose and need" | 4 |  |  |  | 111.4 miles plus Hassayampa to Palo Verde |  | 500 |  |  |  |  | N/A | N/A | N/A | Not included in TPP | 2016 | [9 empty] | 2012-01-01 | 2016-12-31 |  | 3.2 | 0 | See "Actual Costs"
105 | TL629-E Reconductor | San Diego | This project replaces wood poles with weatherized steel pole in fire prone areas and reconductors 8.6 miles of existing transmission and adds TL6958 as a double circuit transmission line. | See "location" | See "purpose and need" | 6 | 8 |  |  | 8.6 miles |  | 69 |  |  | 2012 | [5 empty] | 2018 | [9 empty] | 2017-01-01 | 2018-05-01 |  | 3.7 | 0 | See "Actual Costs" |  | 0 |  | 100%
106 | Direct Buried Cable Replace.: TL615 & 659 | San Diego | Replacing existing Direct Buried Cable for TL615 and TL659. New alignment is approx. 3.3 miles long and will have both circuits in the same conduit package. A 96 count fiber communication line will also be included. Curb to Curb repaving is required once project is energized. | See "location" | See "purpose and need" | 6 | 9 |  |  | 3.3 miles |  | 69 |  |  | 2012 |  | N/A | N/A | N/A | Not included in TPP | 2020 | [9 empty] | 2021-02-18 | 2020-09-02 |  | 0 | 0 | See "Actual Costs" |  | 3.5
107 | TL633-Overhead Reconductor | San Diego | Reconductor 69kV transmission line TL633 from Bernardo Sub to Rancho Carmel Sub to achieve a rating of 137MVA. Joint project with the City of San Diego to construct the line in a new underground alignment along major thoroughfares from substation to substation, and install underground cables to meet the requested rating of 137MVA. | See "location" | See "purpose and need" | 1 |  |  |  | 3.1 miles |  | 69 |  |  | 2012 |  | 2012 | 2011-2012 | N/A | Not available online | 2019 | [9 empty] | 2019-04-23 | 2019-01-28 | $11 Million - $13 Million | 0 | 0 | See "Actual Costs" |  | 8.5
108 | TL23042 Outage Restoration |  | TL23042 outage restoration due to a 230kV cable pole fire caused by vandalism on 4/17/2012 | See "location" | See "purpose and need" | 6 |  |  |  | Single Structure | [6 empty] | N/A | N/A | N/A | Not included in TPP | 2012 | [9 empty] | 2012-12-01 | 2012-12-01 |  | 1.7 | 0 | See "Actual Costs"
109 | TL636-Wood to Steel | San Diego | Replace 57 wood pole with steel poles | See "location" | See "purpose and need" | 8 |  |  |  | 4.6 |  | 69 |  |  | 2012 |  | N/A | N/A | N/A | Not included in TPP | 2020 | [9 empty] | 2014-06-01 | 2020-09-01 |  |  |  | See "Actual Costs" |  | 0.6
110 | TL628/643 Miguel Gateway Wood-to-Steel Proj | San Diego | This project will harden the electric transmission system to improve reliability. This project replaces approximately 18 wood poles with steel poles. Seven wood poles will be replaced on TL 628 and eleven | See "location" | See "purpose and need" | 8 | [5 empty] | 69 |  |  | 2012 |  | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 1.2 | 0 | See "Actual Costs" |  | 0
111 | TL694-Wood to Steel | San Diego | Replace 62 wood pole with steel poles | See "location" | See "purpose and need" | 8 |  |  |  | 4.7 |  | 69 |  |  | 2012 |  | N/A | N/A | N/A | Not included in TPP | 2020 | [9 empty] | 2014-06-01 | 2020-10-01 |  | 0 | 0 | See "Actual Costs" |  | 0.7
112 | TL631 Reconductor Project |  |  | See "location" | See "purpose and need" | 1 |  |  |  | 4.0 miles | [10 empty] | 2019 | [9 empty] | 2018-08-06 | 2019-01-09 |  | 0.9 | 0 | See "Actual Costs" |  | 0
113 | TL600-Reliability Pole Replacements | San Diego | Adding an additional 96 count fiber communication line from Rose Canyon Sub to Clairemont Sub. There is no way to add the line and stay GO95 compliant so 16 poles will be replaced to accommodate the fiber. There is distribution underbuild and existing 3rd part comm as well | See "location" | See "purpose and need" | 9 |  |  |  | 4.0 miles |  | 69 |  |  | 2012 |  | N/A | N/A | N/A | Not included in TPP | 2019 | [9 empty] | 2018-08-06 | 2019-01-09 |  | 1.6 | 0.5 | See "Actual Costs" |  | 0.3
114 | Aerial Marking For Safety and Compliance | San Diego/ Orange County | Aerial Marking for Safety and Compliance These projects will add aerial marker balls and or lighting at various locations identified by transmission engineering, transmission maintenance or the AL&M support team as safety issues or necessary for FAA Compliance. The intent is to reduce the risk of collisions and improve safety be alerting aviation personnel of transmission line crossings and structures. | See "location" |  | 8 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 2.5 | 0 | See "Actual Costs" |  | 6.9
115 | TL13815 Trans. Bridge Structure Reconfig | San Diego | This project was initiated by Transmission Engineering as a response to customer project development proposal. This project provides cost savings to the easement renewal, and also avoids contentious and potential litigation by the landowner. The project also addresses overloaded tower condition discovered engineering analysis of the existing structures. Remove tower legs and bridge structure on three existing tower bridge structures and re configure existing transmission conductors | See "location" | See "purpose and need" | 7 |  |  |  | 0.6 miles |  | 138 |  |  | 2014 |  | N/A | N/A | N/A | Not included in TPP | 2015 | [9 empty] | Completed in 2015 | Completed in 2015 |  | 8.9 | 0 | See "Actual Costs"
116 | TL628-Direct Buried Cable Replace. | San Diego | The TL628 (Sunny side - Sweetwater) direct buried cable replacement project will involve replacing approximately 1/2 mile of direct-buried cable and associated aging underground infrastructure with 1750KCMIL copper cable within a double-circuit 69kV transmission duct package from existing cable poles Z183803 to Z183809. This project will occur in conjunction with the TL628 20A conversion project on Plaza Bonita Rd. | See "location" | See "purpose and need" | 6 |  |  |  | 0.5 miles |  | 69 |  |  | 2014 |  | N/A | N/A | N/A | Not included in TPP | 2015 | [9 empty] | 2015-12-31 | 2015-12-31 |  | 3.9 | 0 | See "Actual Costs"
117 | TL698 Wood to Steel Project | San Diego | Replace 81 wood pole with steel poles | See "location" | See "purpose and need" | 8 |  |  |  | 4.4 |  | 69 |  |  | 2014 |  | N/A | N/A | N/A | Not included in TPP | 2019 | [9 empty] | 2018-02-01 | 2019-12-01 |  | 0 | 0 | See "Actual Costs" |  | 0.4
118 | Sycamore Landfill Relocation | San Diego | Relocate 4 transmission tielines to allow the Sycamore Landfill to develop the rest of their property. This project installed 27 new engineered foundation poles with new conductor. | See "location" | See "purpose and need" | 7 |  |  |  | Approx. 1 mile |  | 69-138-230 |  |  | 2015 |  | N/A | N/A | N/A | Not included in TPP | 2016 | [9 empty] | 2016-08-12 | 2016-08-12 |  | 14.2 | 0.5 | See "Actual Costs"
119 | Cole Grade Rd 20A | San Diego | Relocation of 3 poles due to city road widening. Transmission only. Project is on hold. | See "location" | See "purpose and need" | 7 | [5 empty] | 69 |  |  | 2016 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A - Hold |  | 0 | 0 | See "Actual Costs" |  | 0
120 | TL678 Reloc for Lake Jennings Mkt Place | San Diego | Customer request to relocate part of TL678 to allow for site development | See "location" | See "purpose and need" | 7 |  |  |  | Less than 1 mile |  | 69 |  |  | 2016 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A - Hold |  | 0 | 0 | See "Actual Costs" |  | 0
121 | TL600: MESA HEIGHTS LOOP-IN + RECONDUCT - GRC |  | Reconductor TL600 from Mesa Heights to Clairemont and loop TL600 into Mesa Heights Substation. Replace existing wood structures with steel. | See "location" | See "purpose and need" | 1 |  |  |  | 2.2 miles | [6 empty] | 2016 | 2015-2016 | N/A | https://www.caiso.com/Documents/Board-Approved2015-2016TransmissionPlan.pdf | 2018 | [9 empty] | 2017-06-01 | 2018-06-01 | $15 Million - $20 Million | 0 | 0 | See "Actual Costs" |  | 0
122 | POWAY-POMERADO 69KV #2 - GRC |  | Install a second 69kV tieline from Poway to Pomerado Substation to increase reliability in the Poway area. | See "location" | See "purpose and need" | 1 |  |  |  | 3.75 miles | [10 empty] | 2019 | [9 empty] | 2019-10-21 | 2019-10-21 |  | 0 | 0 | See "Actual Costs" |  | 0
123 | TL617-BALBOA AVE OVHD TO UG CONVERSION - GRC |  | City Driven OH to UG conversion. On Hold | See "location" | See "purpose and need" | 7 |  |  |  | 3 miles | [6 empty] | N/A | N/A | N/A | Not included in TPP | 2018 | [9 empty] | 2018-03-30 | 2018-03-30 |  | 0 | 0 | See "Actual Costs" |  | 0
124 | TL683-COLE GRADE ROAD WIDENING - GRC |  | Relocation of 3 poles due to city road widening. Transmission only. Project is on hold. | See "location" | See "purpose and need" | 7 |  |  |  | 0.2 miles | [6 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A - Hold |  | 0 | 0 | See "Actual Costs" |  | 0
125 | TL617-REMOVAL OF ROSE CANYON TAP - GRC |  | Reconfigure TL617, TL600, and TL664 coming into Rose Canyon Substation. This includes removal and replacement of four transmission structures with double circuit steel structures near Rose Canyon Substation. | See "location" | See "purpose and need" | 1 |  |  |  | ~0.25 miles if structure replacements required on both sides of I-5 freeway |  | 69kV |  |  |  |  | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2018 | [9 empty] | 2017-12-31 | 2018-06-01 | $3.2 Million - $4 Million | 0 | 0 | See "Actual Costs" |  | 0
126 | TL13834-TRABUCO-CAPISTRANO 138KV LINE - GRC |  | Scope of work replaces terminal equipment at Trabuco and Capistrano to achieve 274 MVA. No transmission line conductor upgrades are required. | See "location" | See "purpose and need" | 1 |  |  |  | 0 |  | 69kV |  |  |  |  | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | N/A | [10 empty] | N/A - Cancelled | $1 Million | 0 | 0 | See "Actual Costs" |  | 0
127 | TL23001/04 SAN LUIS REY TO MISSION | San Diego | Convert wood to steel poles from TL23001 and TL23004 between substations San Luis Rey and Mission. | See "location" | See "purpose and need" | 8 | [5 empty] | 230kV | [8 empty] | 2019 | [10 empty] | 2019-01-03 |  | 0 | 0 | See "Actual Costs" |  | 0.3
128 | TL660-CALTRAN I-5 WIDENING @ BIRMINGHAM | San Diego | Caltrans request to relocate part of TL660 to allow for I5 freeway widening | See "location" | See "purpose and need" | 7 |  |  |  | 0.2 miles |  | 69 |  |  | 2016 |  | N/A | N/A | N/A | Not included in TPP | 2017 | [9 empty] | 2017-09-07 | 2017-09-07 |  | 0 | 0 | See "Actual Costs"
129 | TL605 Reconductor: Silvergate - Urban | San Diego | Reconductor 0.6 miles of overhead conductor and 1.1 miles of existing underground cable to achieve a continuous rating of 136 MVA. The overhead portion may be converted to underground cable to eliminate three overhead freeway crossings. | See "location" | See "purpose and need" | 1 |  |  |  | 1.7 miles |  | 69 |  |  | 2016 |  | 2016 | 2015-2016 | N/A | https://www.caiso.com/Documents/Board-Approved2015-2016TransmissionPlan.pdf | 2018 | [9 empty] | 2017-05-01 | 2018-02-14 | $5 Million - $6 Million | 0 | 0 | See "Actual Costs" |  | 0.002
130 | Granite Substation 69kV Loop-In | San Diego | Creating new tie line to connect Los Coches Sub and Granite Sub to prevent an n-1 contingency. This project will reconfigure other tie lines in our corridor as well a connect Granite to the corridor via a new route. | See "location" | See "purpose and need" | 1 |  |  |  | 2.3 miles |  | 69 |  |  | 2017 |  | 2015 | 2014-2015 | N/A | http://www.caiso.com/Documents/Board-Approved2014-2015TransmissionPlan.pdf | 2020 | [9 empty] | 2021-07-01 | 2020-06-26 | $15.2 Million - $19.8 Million | 0 | 0 | See "Actual Costs" |  | 0.022
131 | TL696 Winterhawk Customer Relocation | San Diego | Customer requested. Has not paid processing fee yet, project on hold. Scope is to monitor and advise during construction so that our facilities are not impacted. One pole and one span possibly impacted. | See "location" | See "purpose and need" | 7 |  |  |  | 0.1 miles |  | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | 2018 | [10 empty] | 2018-12-31 |  | 0 | 0 | See "Actual Costs" |  | 0
132 | TL611 OLD TOWN - PT LOMA | San Diego | Replace direct buried underground cable along old Sea World Drive | See "location" | See "purpose and need" | 6 |  |  |  | Approx. 1.5 miles |  | 69 |  |  | 2017 | [5 empty] | 2020 | [9 empty] | 2019-11-15 | 2020-05-01 |  | 0 | 0 | See "Actual Costs" |  | 0
133 | TL603B SWEETWATER TAP REMOVAL | San Diego | Creating a new tie line from National City Sub to Sweetwater Sub to prevent an n-1 contingency overload. New line will be underground. Remove portion of TL603 that connects National City Sub and TL603 Tap. | See "location" | See "purpose and need" | 1 |  |  |  | 1.7 miles |  | 69 |  |  | 2017 |  | 2013 | 2012-2013 | N/A | http://www.caiso.com/Documents/BoardApproved2012-2013TransmissionPlan.pdf | 2020 | [9 empty] | 2021-07-01 | 2020-04-14 | $10 Million - $12 Million | 0 | 0 | See "Actual Costs" |  | 0.1
134 | TL628 Relocation - National City CarMax | San Diego | Customer request to relocate part of TL628 to allow for site development | See "location" | See "purpose and need" | 7 |  |  |  | Less than 1 mile |  | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | 2018 | [9 empty] | 2018-01-12 | 2018-01-12 |  | 0 | 0 | See "Actual Costs" |  | 0
135 | TL6943 UG CONV-GENESEE AVE BRIDGE | San Diego | Install transmission conduit in the new Caltrans Genesee bridge and convert the existing TL6943 overhead span across the I5 freeway to underground through the bridge. | See "location" | See "purpose and need" | 7 |  |  |  | 0.2 miles |  | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | 2017 | [9 empty] | 2017-09-28 | 2017-11-10 |  | 0 | 0 | See "Actual Costs" |  | 2
136 | TL6905 MIRAMESA COMMUNITY RELOCATION | San Diego | Convert ~0.25 miles of overhead TL6905 to underground (from Structure Z96512 to Z90429) for customer development of parcel | See "location" | See "purpose and need" | 7 |  |  |  | 0.25 miles |  | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | N/A | [9 empty] | 2018-12-31 | On Hold Due to Customer Commitment |  | 0 | 0 | See "Actual Costs" |  | 0
137 | TL674 QUAIL MEADOWS | San Diego | Convert ~800 feet of overhead TL674 from Structure Z24551 to Z3230317 to underground for customer development of parcel | See "location" | See "purpose and need" | 7 |  |  |  | 800 feet |  | 69 |  |  | 2017 | [5 empty] | 2018 | [9 empty] | 2018-12-31 | 2018-12-31 |  | 0 | 0 | See "Actual Costs" |  | 0
138 | TL23041-42-6910 OTAY VALLEY RESTORATION |  | Customer requested. Has not paid processing fee yet, project on hold. Scope is to monitor and advise during construction so that our facilities are not impacted. | See "location" | See "purpose and need" | 7 |  |  |  | 0.25 miles |  | 230/69kV |  |  |  |  | N/A | N/A | N/A | Not included in TPP | N/A | [9 empty] | on hold | On Hold |  | 0 | 0 | See "Actual Costs" |  | 0
139 | TL660 STUB POLE RELOCATION | San Diego | Remove four existing stub poles and either guy existing transmission poles or replace with steel poles. | See "location" | See "purpose and need" | 8 |  |  |  | 0.25 miles |  | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | 2018 | [9 empty] | 2018-12-30 | 2018-08-27 |  | 0 | 0 | See "Actual Costs" |  | 0
140 | TL690 DB CABLE REPLACE (OSIDE-OSIDE TAP) | San Diego | Direct buried cable aging infrastructure replacement. | See "location" | See "purpose and need" | 6 | [5 empty] | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | 2020 | [10 empty] | 2020-08-24 |  | 0 | 0 | See "Actual Costs" |  | 0.06
141 | TL628 DB CALBE REPLACE (H ST & RANCHO DR) | San Diego | Relocation of 3 poles due to city road widening. Transmission only. Project is on hold. | See "location" | See "purpose and need" | 7 | [5 empty] | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A - Hold |  | 0 | 0 | See "Actual Costs" |  | 0.022
142 | TL661/664 DB CABLE REPLACE (LUSK BLVD) | San Diego | New Project, no schedule yet | See "location" | See "purpose and need" | 6 | [5 empty] | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A |  | 0 | 0 | See "Actual Costs" |  | 0
143 | TL698 AVOCADO SUB GATEWAY DB CABLE REPLACE | San Diego | New Project, no schedule yet | See "location" | See "purpose and need" | 6 | [5 empty] | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A |  | 0 | 0 | See "Actual Costs" |  | 0.026
144 | TL693 SAN LUIS REY GATEWAY DB CABLE REPLACE | San Diego | Project Cancelled | See "location" | See "purpose and need" | 6 | [5 empty] | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A - Cancelled |  | 0 | 0 | See "Actual Costs" |  | 0
145 | TL697 OCEANSIDE SUB GATWEAY DB CABLE REPLACE | San Diego | New Project, no schedule yet | See "location" | See "purpose and need" | 6 | [5 empty] | 69 |  |  | 2017 |  | N/A | N/A | N/A | Not included in TPP | N/A | [10 empty] | N/A |  | 0 | 0 | See "Actual Costs" |  | 0.026
146 | 2ND 69KV LINE POMERADO TO POWAY | San Diego |  | See "location" | See "purpose and need" | Duplicate Above | [5 empty] | 69 |  |  | 2017 |  | 2015 | 2014-2015 | N/A | http://www.caiso.com/Documents/Board-Approved2014-2015TransmissionPlan.pdf | N/A | [11 empty] | $17 Million - $19 Million | 0 | 0 | See "Actual Costs" |  | 0.119
147 | TL662/666 Torrey Pines Reliability Project | San Diego | Project Cancelled | See "location" | See "purpose and need" | 1 | [5 empty] | 69 | [8 empty] | N/A | [10 empty] | N/A - Cancelled |  |  |  | See "Actual Costs"
148 | TL667 DB Cable Replacement (El Camino Real) | San Diego | Replace direct buried cable from Sea Country Ln to Carmel Valley road along El Camino Real. | See "location" | See "purpose and need" | 6 |  |  |  | 2.8 miles |  | 69 |  |  |  |  | N/A | N/A | N/A | Not included in TPP | 2020 | [10 empty] | 2020-06-15 |  |  |  | See "Actual Costs"
149 | TL13820 Reconductor (Chicarita - Sycamore) | San Diego | Project Cancelled (due to Planning Update) | See "location" | See "purpose and need" | 1 | [5 empty] | 138 |  |  |  |  | 2013 | 2012-2013 | N/A | http://www.caiso.com/Documents/BoardApproved2012-2013TransmissionPlan.pdf | N/A | [10 empty] | N/A - Cancelled | $0.5 Million - $1 Million |  |  | See "Actual Costs"
150 | Automated Fault Location |  |  | See "location" | See "purpose and need" | 9 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 0 | 0 | See "Actual Costs" |  | 1.3
151 | Friars Sub Reliability Enhancement Project | San Diego | Reliability project to mitigate N-1 contingencies of 138kV transmission lines feeding Friars Substation. | See "location" | See "purpose and need" | 6 |  |  |  | 1000' | [6 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 4.2 | 0.1 | See "Actual Costs" |  | 0 | 0 | 100
152 | Transmission System Spares |  |  | See "location" | See "purpose and need" | 6 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 5.6 | 0 | See "Actual Costs" |  | 0
153 | SONGS Mesa: New 230kV Switchyard |  |  | See "location" | See "purpose and need" | 1 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 0 | 0 | See "Actual Costs" |  | 16.4
154 | CBM Gas Circuit Breakers |  |  | See "location" | See "purpose and need" | 6 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 3.6 | 2 | See "Actual Costs" |  | 5.3
155 | Union Pacific RR Land Purchase |  |  | See "location" | See "purpose and need" | 6 | [10 empty] | N/A | N/A | N/A | Not included in TPP | N/A | [12 empty] | 21.5 | 0 | See "Actual Costs" |  | 0
156 | SONGS Synchronous Condenser | San Diego | Installation of one 225 MVAr Synchronous Condenser unit that will be housed , including the installation of a concrete foundation to support a pre-fabricated metal enclosure that will house one complete synchronous condenser unit, with space for a second synchronous condenser unit. | see "location" | See "purpose and need" | 1 |  |  |  | NA | All work within existing switchyard | 230kV | One 250MVA GSU Transformer | Yes | 2015 | SDG&E Board of Director Approval | 2013 | 2012-2013 | N/A | http://www.caiso.com/Documents/BoardApproved2012-2013TransmissionPlan.pdf | 2018 |  |  |  | Does not require commission filing | NA | NA | NA | NA | Construction | 2017-08-01 | 2018-08-01 |  | 0 | 0 | See "Actual Costs" |  | 66.6 | 100% | 0% | To mitigate voltage stability concerns in response to the loss of generation at SONGS and South Bay Power Plants; along with the planned closure of Encina Power Plant and increase in renewable generation.
157 | TL6931 WTS (CNF) | San Diego | Rebuild approximately 6 miles of 69kV from wood poles to steel. This line runs from Crestwood substation st the west terminus to the Boulevard substation at the east terminus. Note: this line was added to the scope of the Cleveland National Forest in 2016 as part of the Federally Preferred Alternative. | see "location" | See "purpose and need" | 8 |  |  |  | Approximately 6 miles | N/A | 69 |  | Yes |  | Sempra BOD | N/A | N/A | N/A | Not included in TPP | 2017 | Final Certified | EIR/EIS | CPUC/USDA Forest Service | A | PTC | 2012 | Approved | 2016 | Construction | 2014 | 2017-10-31 |  | 0 | 0 | See "Actual Costs" |  | 0 | 0% | 100% | Improve electric system reliability and safety
158 | San Mateo Substation Expansion | Orange County | Rebuild of the aging infrastructure of San Mateo Substation to new construction and reliability standards | see "location" | See "purpose and need" | 6 |  |  |  | N/A |  |  | 120MVA | Yes | 2017 | TRC |  |  |  |  | 2021 | Expected PEA Completion | EIR | CPUC | Application | PTC | Not Yet Filed | To Be Filed | 2018 | Planning | 2021 | 2021 |  | 0 | 0 | See "Actual Costs" |  | 0.1 | 70% | 30% | Enhance reliability and minimize outage impact to the transmission and distribution systems in the San Clemente area
159 | Basilone Substation 15 Mvar Capacitor | Orange County | Mitigate voltage deviations at Basilone, Las Pulgas and Japanese Mesa | see "location" | See "purpose and need" | 1 |  |  |  |  | 0.88 | 69 kV | 15 MVA | Yes | 2016 | Capital Budget Committee | 2016 | 2015-2016 | N/A | https://www.caiso.com/Documents/Board-Approved2015-2016TransmissionPlan.pdf | 2016 |  |  |  | Does not require commission filing | N/A | N/A |  |  | Operational | 2016 | 2016-12-31 | $1.5 Million - $2 Million | 0 | 0 | See "Actual Costs" |  | 4
160 | Mission Bank #51 and #52 replacement | San Diego | Mitigate overload on Bank 51 and improve voltage control with a bank that has load tap change capability by replacing Bank 51 and Bank 52. Replace both class 50 banks with a calss 70 Bank (224 MVA). | see "location" | See "purpose and need" | 1 |  |  |  |  | 3.17 | 138/69 kV | 224 MVA | Yes | 2016 | Capital Budget Committee | 2014 | 2013-2014 | N/A | https://www.caiso.com/Documents/Board-Approved2013-2014TransmissionPlan_July162014.pdf | 2018 |  |  |  | Does not require commission filing | N/A | N/A |  |  | Construction | 2018 | 2018-06-30 | $10 Million | 0 | 0 | See "Actual Costs" |  | 3.4
161 | TL692 Camp Pendleton wood to steel | Camp Pendleton | wood to steel pole replacement and reconductor for TL692 | see "location" | See "purpose and need" | 1 | 8 |  |  | approx. 7 miles | N/A | 69 | N/A | Yes | [6 empty] | 2019 | planning | TBD | CPUC | TBD | TBD | 2018 (expected) | To Be Filed |  | planning, permitting |  | 2019 |  |  |  | See "Actual Costs" |  |  |  |  | Wood to steel project to reduce fire risk

## 2012_2017 Accounting
Row Line/No. | Budget Code | Project Name | Voltage Level | CAISO | 2012 Project Actual Dollars (thousands) | 2013 Project Actual Dollars (thousands) | 2014 Project Actual Dollars (thousands) | 2015 Project Actual Dollars (thousands) | 2016 Project Actual Dollars (thousands) | 2017 Project Actual Dollars to-date (thousands) | 6 Year Actual Spent | 1st assignment | 2nd assignment | 3rd assignment | Peak-Driven | Gen Interconnection | Load Interconnection | Improve grid efficiency (LCR) | Support public policy requirements or goals (RPS) | Upgrade, repair or replacement of existing facilities | Relocation or removal of facilities | Customer and/or employee safety (e.g., fire-hardening). | Grid visibility, control and measurement. | Provide reliable service under conditions not driven by peak load.
1 | 2252 | Mira Sorrento 138/12KV Sub & Cirs. 1442 Thru 1446 | LV | N/A | 1065.342 | 8972.101 | 18040.117 | 679.907 | 50.954 | -0.034 | 28808.387 | 1 | 3 | 0 | 14404.1935 |  | 14404.1935
2 | 2258 | Salt Creek-Land Purchase, New Substa. & 3 New Ckts | LV | 2013-2014 | 1413.424 | 1458.42 | 2025.145 | 1871.053 | 18275.712 | 15879.401 | 40923.155 | 1 | 3 | 0 | 20461.5775 |  | 20461.5775
3 | 4138 | Sunrise Powerlink | HV | 0 | 284740.973 | 4514.12 | 690.105 | 65992.774 | -1329.612 | 0.73 | 354609.09 | 4 | 5 | 1 | 177304.545 |  |  | 35460.909 | 141843.636
4 | 5253 | Ocean Ranch Land Purchase, New Substation | LV | 2015-2016 | 5035.607 | 117.818 | 151.676 | 1003.951 | 1228.021 | 1692.071 | 9229.144 | 1 | 0 | 0 | 9229.144
5 | 6129 | South Orange County Reliability Enhancement (SOCRE) | HV | 2010-2011 | 3768.136 | 5835.794 | 13215.046 | 6695.268 | 11761.027 | 12837.907 | 54113.178 | 1 | 6 | 0 | 27056.589 |  |  |  |  | 27056.589
6 | 6132 | Relocate South Bay Substation | HV | 2009-2010 | 1776.301 | 4629.021 | 16314.738 | 61022.946 | 42324.012 | 1055.539 | 127122.557 | 7 | 0 | 0 | [6 empty] | 127122.557
7 | 7139 | ECO Substation | HV | N/A | 60606.841 | 201005.47 | 139236.921 | 8759.043 | 1171.293 | 60.043 | 410839.611 | 5 | 0 | 0 |  |  |  |  | 410839.611
8 | 8165 | TL 629 DE-GC-CN SW Pole Replacements - CNF | LV | N/A | 3337.69 | -1855.936 | 4235.429 | 10519.426 | 84800.132 | 89254.137 | 190290.878 | 8 | 0 | 0 | [7 empty] | 190290.878
9 | 9125 | TL 637 CRE-ST SW Pole Replacements | LV | N/A | 6682.806 | 1996.974 | 34340.138 | 1882.942 | 8.93 | 0 | 44911.79 | 8 | 0 | 0 | [7 empty] | 44911.79
10 | 9132 | TL6926 Rincon-Valley Center SW Pole Replace | LV | N/A | 1461.531 | 700.254 | 307.399 | 662.415 | 1036.562 | 785.5 | 4953.661 | 8 | 0 | 0 | [7 empty] | 4953.661
11 | 9137 | TL649 Otay-San Ysidro-Border SW Pole Replace | LV | N/A | 116.95 | 260.284 | 874.929 | 924.592 | 975.391 | 675.322 | 3827.468 | 8 | 0 | 0 | [7 empty] | 3827.468
12 | 9142 | TL686 Warners to Narrows SW Pole Replace TL687 Borrego Springs | LV | N/A | 52.904 | 76.463 | 150.642 | 106.975 | 100.19 | 100.424 | 587.598 | 8 | 0 | 0 | [7 empty] | 587.598
13 | 9166 | TL13821 and TL13828-Fanita Junction Enhancement | LV | 2009-2010 | 7299.74 | 1071.161 | 4375.288 | 27752.576 | 14294.963 | -122.519 | 54671.209 | 1 | 0 | 0 | 54671.209
14 | 9276 | Poseidon Project-Modify Cannon Sub & Install 2 Ckts | LV | N/A | 1.217 | 5415.465 | 21277.014 | -603.362 | 0.733 | 0 | 26091.067 | 3 | 0 | 0 |  |  | 26091.067
15 | 10143 | Wood to Steel Pole Replace.-TL690E | LV | 2013-2014 | 89.171 | 106.541 | 182.99 | 328.254 | 414.77 | 678.018 | 1799.744 | 8 | 1 | 0 | 899.872 | [6 empty] | 899.872
16 | 10144 | TL691 Avo-Mon Wood to Steel | LV | N/A | 33.179 | 56.381 | 90.616 | 119.766 | 1206.005 | 875.47 | 2381.417 | 8 | 0 | 0 | [7 empty] | 2381.417
17 | 10146 | TL695/6971 Reconductor & Wood to Steel | LV | 2011-2012 | 60.871 | 202.157 | 253.511 | 1215.066 | 934.417 | 1069.644 | 3735.666 | 1 | 8 | 0 | 1867.833 | [6 empty] | 1867.833
18 | 10147 | TL697 San Luis Rey Wood to Steel | LV | N/A | 2.529 | 2.061 | 25.223 | 59.838 | 605.095 | 1006.364 | 1701.11 | 8 | 1 | 0 | 850.555 | [6 empty] | 850.555
19 | 10149 | Wood to Steel Pole Replace.-TL6912 | LV | N/A | 86.508 | 20.681 | 25.841 | 34.493 | 542.907 | 760.08 | 1470.51 | 1 | 8 | 0 | 735.255 | [6 empty] | 735.255
20 | 11146 | Ocotillo Express-Interconnect. Switchyard | LV | N/A | 23620.962 | 25525.572 | 27.194 | 7.152 | 221.842 | 1.017 | 49403.739 | 2 | 0 | 0 |  | 49403.739
21 | 11149 | CSolar-Generator Interconnection | LV | N/A | 3972.797 | 4790.448 | -2987.304 | 63.27 | -25.897 | -118.401 | 5694.913 | 2 | 0 | 0 |  | 5694.913
22 | 11150 | Centinela-Generator Interconnection | LV | N/A | 1131.38 | 2200.981 | -2246.4 | 264.786 | 281.435 | -579.876 | 1052.306 | 2 | 0 | 0 |  | 1052.306
23 | 12140 | Merchant Switchyard & Transmission | LV | N/A | 8853.725 | 3589.006 | 1186.43 | 829.319 | 940.274 | 152.562 | 15551.316 | 7 | 0 | 0 | [6 empty] | 15551.316
24 | 12142 | Campo Verde Solar-Generator Interconnect. | LV | N/A | 1026.115 | 65.124 | 1.892 | 0 | 0 | 0 | 1093.131 | 2 | 0 | 0 |  | 1093.131
25 | 12158 | Pio Pico Energy Ctr. Gen. Interconnect | LV | N/A | 688.81 | 524.665 | 2008.629 | 6527.608 | 334.157 | -21.997 | 10061.872 | 2 | 0 | 0 |  | 10061.872
26 | 13128 | Sycamore-Penasquitos New 230KV TL | HV | 2012-2013 | 0 | 1935.468 | 3864.85 | 20979.044 | 38685.581 | 66148.081 | 131613.024 | 1 | 5 | 0 | 65806.512 |  |  |  | 65806.512
27 | 13129 | 500 KV Series Capacitor-ECO Sub | HV | 0 | 0 | 11150.295 | 3944.286 | 1.962 | 0 | 0 | 15096.543 | 4 | 0 | 0 |  |  |  | 15096.543
28 | 13130 | TL674A Reconfigure/TL666D RFS | LV | 2012-2013 | 0 | 295.901 | 652.524 | 94.25 | 381.414 | 763.583 | 2187.672 | 7 | 0 | 0 | [6 empty] | 2187.672
29 | 13131 | Talega-Add Synchronous Condensers | HV | 2012-2013 | 89.785 | 11514.811 | 41890.132 | 26537.708 | 4497.072 | 63.364 | 84592.872 | 1 | 0 | 0 | 84592.872
30 | 13140 | IV West Generator Interconnection (Q608) | LV | N/A | 0 | 0 | 1794.797 | -497.43 | 15.418 | 0 | 1312.785 | 2 | 0 | 0 |  | 1312.785
31 | 13243 | New Vine 69/12KV Substation | LV | 2014-2015 | 0 | 146.071 | 818.164 | 1750.74 | 9591.161 | 17343.796 | 29649.932 | 1 | 3 | 0 | 14824.966 |  | 14824.966
32 | 14127 | Imperial Valley Flow Controller | HV | 2013-2014 | 0 | 0 | 87.447 | 11075.008 | 26993.784 | 11291.793 | 49448.032 | 4 | 0 | 0 |  |  |  | 49448.032
33 | 14128 | Artesian 230kV Expansion-Prel. Eng. | HV | 2013-2014 | 812.767 | 5.249 | 4167.351 | 1428.528 | 1250.991 | 812.767 | 8477.653 | 1 | 0 | 0 | 8477.653
34 | 14130 | San Luis Rey Synchronous Condensers | HV | 2013-2014 | 0 | 0 | 12293.115 | 66571.721 | 55837.773 | 19502.987 | 154205.596 | 1 | 5 | 0 | 77102.798 |  |  |  | 77102.798
35 | 14131 | Miguel 500kV Voltage Support | HV | 2013-2014 | 0 | 0 | 294.345 | 4546.09 | 32559.167 | 18926.502 | 56326.104 | 1 | 0 | 0 | 56326.104
36 | 14137 | TL6975 Escondido - San Marcos | LV | 2013-2014 | 0 | 0 | 0.245 | 691.756 | 1119.592 | 573.604 | 2385.197 | 1 | 0 | 0 | 2385.197
37 | 14138 | TL13835 Wood to Steel | LV | N/A | 0 | 0 | 20.047 | 10.718 | 164.858 | 221.944 | 417.567 | 1 | 8 | 0 | 208.7835 | [6 empty] | 208.7835
38 | 15129 | Jacumba Solar Gen Interconnect (Q644A) | LV | N/A | 0 | 0 | 0 | 87.281 | 837.314 | 2074.907 | 2999.502 | 2 | 0 | 0 |  | 2999.502
39 | 15133 | Tule Wind - Generator Interconnect | LV | N/A | 100 | 0 | 0 | 6.63 | 103.686 | 541.268 | 751.584 | 2 | 0 | 0 |  | 751.584
40 | 15258 | Mid-Coast Trolley Extension Project | LV | N/A | 0 | 0 | 163.165 | -267.196 | 7700.695 | 17231.571 | 24828.235 | 7 | 0 | 0 | [6 empty] | 24828.235
41 | 16132 | TL690A | LV | 2013-2014 | 0 | 0 | 0 | 0 | 681.784 | 712.003 | 1393.787 | 1 | 8 | 0 | 696.8935 | [6 empty] | 696.8935
42 | 16134 | Carlsbad Energy Center Project | LV | N/A | 0 | 0 | 0 | 0 | 697.697 | 660.33 | 1358.027 | 2 | 0 | 0 |  | 1358.027
43 | 16137 | Vista Energy Storage Project | LV | N/A | 0 | 0 | 0 | 0 | 0 | 421.538 | 421.538 | 2 | 0 | 0 |  | 421.538
44 | 16157 | MIGUEL TO BAY BLVD NEW 230KV LINE | HV | 2015-2016 | 0 | 0 | 0 | 0 | 0 | 262.344 | 262.344 | 1 | 0 | 0 | 262.344
45 | 16249 | Expedited Storage Procurement (ESP) | LV | N/A | 0 | 0 | 0 | 0 | 56625.128 | 34947.807 | 91572.935 | 2 | 0 | 0 |  | 91572.935
46 | 17130 | BC14XXX (TL6906 MESA RIM LOOP-IN) | LV | 2013-2014 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 8 | 7
47 | 10138 | Synchronized Phasor Measurement System | HV | N/A | 1697.476 | 1177.965 | 1514.36 | 2571.926 | 2364.242 | 1831.592 | 11157.561 | 9 | 0 | 0 | [8 empty] | 11157.561
48 | 6133 | Install Bank 61 At Miguel | HV | 0 | 1181.05 | 134.501 | 1.091 | 0 | 0 | 0 | 1316.642 | 6 | 7 | 0 | [5 empty] | 658.321 | 658.321
49 | 6251 | Otay Substation Rebuild | HV | 0 | 1148.784 | 762.665 | 0 | 0 | 0 | 0 | 1911.449 | 6 | 0 | 0 | [5 empty] | 1911.449
50 | 8162 | Substation Security Installations | HV | N/A | 9523.898 | 5972.932 | 5381.686 | 10203.139 | 5900.771 | 143.235 | 37125.661 | 9 | 0 | 0 | [8 empty] | 37125.661
51 | 8163 | IV Sub Bank 82 Addition | HV | 0 | 5066.803 | 7121.228 | 0.281 | 37.194 | 6.673 | 0.693 | 12232.872 | 2 | 6 | 0 |  | 6116.436 |  |  |  | 6116.436
52 | 9168 | 69KV & 12KV Capacitor Installation | LV | #N/A | 3911.48 | 2044.061 | 1400.906 | 34.595 | 0 | 0 | 7391.042 | 1 | 10 | 0 | 3695.521 | [8 empty] | 3695.521
53 | 9170 | Overstressed Breaker Replacements | HV | #N/A | 5372.37 | 4602.186 | 4531.157 | 3233.68 | 1358.697 | 165.49 | 19263.58 | 10 | 6 | 0 | [5 empty] | 9631.79 |  |  |  | 9631.79
54 | 10135 | Los Coches Sub-Rebuild 138/69kV | LV | N/A | 3527.413 | 6599.765 | 21914.537 | 25759.863 | 18152.157 | 8956.466 | 84910.201 | 6 | 0 | 0 | [5 empty] | 84910.201
55 | 12125 | Sunnyside 69/12kV Rebuild | LV | N/A | 798.299 | 3726.14 | 7049.616 | 4861.52 | 202.033 | -2.169 | 16635.439 | 6 | 0 | 0 | [5 empty] | 16635.439
56 | 12132 | SCADA Expansion-Transmission | HV | #N/A | 346.069 | 1600.731 | 546.283 | 545.749 | 1870.345 | 917.847 | 5827.024 | 9 | 0 | 0 | [8 empty] | 5827.024
57 | 12134 | Penasquitos-Add 230kV Capacitor Banks | HV | 0 | 3012.498 | 4275.278 | 30.297 | -2.584 | 0 | 0 | 7315.489 | 1 | 0 | 0 | 7315.489
58 | 12157 | Sycamore Canyon-Add 60 KV Reactor Banks | LV | 0 | 0 | 3132.134 | 1690.454 | 0.906 | 0 | 0 | 4823.494 | 10 | 0 | 0 | [9 empty] | 4823.494
59 | 13126 | Sta F Substation Improvements | LV | N/A | 29.425 | 1295.295 | 132.168 | 0.179 | 0 | 0 | 1457.067 | 6 | 0 | 0 | [5 empty] | 1457.067
60 | 13127 | Miguel Substation BK 80 Replacement | HV | N/A | 0 | 746.327 | 4570.371 | -3642 | 0 | -0.767 | 1673.931 | 6 | 0 | 0 | [5 empty] | 1673.931
61 | 13133 | Shunt Reactor on Suncrest 500kV Bus | HV | N/A | 12.821 | 1744.226 | 7299.563 | 688.526 | 12.821 | 74.417 | 9832.374 | 10 | 0 | 0 | [9 empty] | 9832.374
62 | 13134 | Talega Bank 50 Replacement | LV | 0 | 0 | 937.983 | 1259.894 | 3.689 | 778.186 | 279.73 | 3259.482 | 6 | 0 | 0 | [5 empty] | 3259.482
63 | 13136 | Wabash Substation Rebuild | LV | N/A | 0 | 1667.234 | 6575.599 | 2211.435 | 622.929 | -10.51 | 11066.687 | 6 | 0 | 0 | [5 empty] | 11066.687
64 | 13242 | Kearny 69/12KV Sub Rebuild/Reloc-Pre Eng | LV | N/A | 0 | 175.093 | 102.79 | 206.56 | 4846.38 | 2491.068 | 7821.891 | 7 | 0 | 0 | [6 empty] | 7821.891
65 | 14129 | SONGS Station Light & Power | HV | N/A | 0 | 0 | 628.895 | 1394.253 | 345.152 | 0.431 | 2368.731 | 7 | 0 | 0 | [6 empty] | 2368.731
66 | 14132 | Imperial Valley Sub Oper. Reliability & Security | HV | N/A | 0 | 419.364 | 3809.483 | 4538.463 | 1070.913 | 1282.525 | 11120.748 | 9 | 0 | 0 | [8 empty] | 11120.748
67 | 14142 | Encina Bank 61 | HV | 0 | 0 | 0 | 8.476 | 8542.379 | 3184.625 | 8.1 | 11743.58 | 6 | 0 | 0 | [5 empty] | 11743.58
68 | 14143 | Poway Substation Rebuild | LV | #N/A | 0 | 0 | 21.39 | 2636.559 | 6635.203 | 3089.528 | 12382.68 | 6 | 0 | 0 | [5 empty] | 12382.68
69 | 15128 | Silvergate Sub: Install Spare Transformer | HV | N/A | 0 | 0 | 0 | 1750.716 | 485.415 | 54.38 | 2290.511 | 1 | 0 | 0 | 2290.511
70 | 15130 | Miguel Sub Hydro & Water Quality Enhance | HV | N/A | 0 | 0 | 0 | 854.374 | 2555.335 | 323.642 | 3733.351 | 6 | 0 | 0 | [5 empty] | 3733.351
71 | 15132 | Mission Bank 71 Addition | HV | 0 | 0 | 0 | 0 | 0 | 2098.169 | 1352.433 | 3450.602 | 6 | 0 | 0 | [5 empty] | 3450.602
72 | 15246 | Rancho Santa Fe Sub Fire Hardening | LV | #N/A | 0 | 0 | 0 | 0 | 638.718 | 1712.426 | 2351.144 | 8 | 0 | 0 | [7 empty] | 2351.144
73 | 16128 | Camp Pendleton Voltage Support | LV | 2015-2016 | 0 | 0 | 0 | 0 | 2037.322 | 1882.725 | 3920.047 | 6 | 0 | 0 | [5 empty] | 3920.047
74 | 16130 | Warners Substation 69kV Control & Protection Replacement | LV | N/A | 0 | 0 | 0 | 0 | 1178.188 | 1402.064 | 2580.252 | 6 | 0 | 0 | [5 empty] | 2580.252
75 | 16131 | Descanso Substation 69kV Control & Protection Replacement | LV | N/A | 0 | 109.21 | 28.46 | 152.578 | 1258.831 | 1419.005 | 2968.084 | 6 | 0 | 0 | [5 empty] | 2968.084
76 | 16133 | Substation Auxiliary Power System | LV | #N/A | 0 | 0 | 0 | 0 | 1154.354 | 469.81 | 1624.164 | 9 | 0 | 0 | [8 empty] | 1624.164
77 | 16159 | HVDC Conversion of Southwest Powerlink | HV | 0 | 0 | 0 | 0 | 0 | 0 | 1084.16 | 1084.16 | 4 | 0 | 0 |  |  |  | 1084.16
78 | TBD20.0 | IV Bank 80 Replacement | HV | 0 | [6 empty] | 0 | 6 | 0 | 0 | [5 empty] | 0
79 | TBD36.0 | Avocado Sub Rebuild | LV | N/A | [6 empty] | 0 | 6 | 0 | 0 | [5 empty] | 0
80 | 7138 | Camp Pendleton Tower Lighting | LV | N/A | 1338.206 | 0 | 0 | 0 | 0 | 0 | 1338.206 | 8 | 0 | 0 | [7 empty] | 1338.206
81 | 9134 | TL6910-Miguel to Border SW Pole Replace | LV | N/A | 2634.403 | 5319.095 | 104.69 | 0.085 | 0 | 0 | 8058.273 | 8 | 0 | 0 | [7 empty] | 8058.273
82 | 9135 | TL616-Rancho Santa Fe-Bernardo-Lake Hodges SW Pole | LV | N/A | 1077.316 | -16.669 | 127.809 | 86.889 | 0 | 0 | 1275.345 | 8 | 0 | 0 | [7 empty] | 1275.345
83 | 9136 | TL6914 Los Coches-Loveland SW Pole Replace | LV | N/A | 2946.836 | 4658.33 | 20096.548 | 13961.846 | 102.585 | 67.805 | 41833.95 | 8 | 0 | 0 | [7 empty] | 41833.95
84 | 9138 | TL 6913 Poway-Pomerado SW Pole Replace. | LV | N/A | 1022.102 | 7700.557 | 315.968 | 0.008 | 0.042 | 0 | 9038.677 | 1 | 8 | 0 | 4519.3385 | [6 empty] | 4519.3385
85 | 11151 | TL694A Melrose Loop-In Project | LV | 0 | 1159.429 | 13943.557 | 17160.769 | 1417.017 | 81.447 | 0 | 33762.219 | 1 | 0 | 0 | 33762.219
86 | 9153 | TL676 Mission to Mesa Heights Reconductor | LV | 2010-2011 | 148.872 | 142.084 | 388.9 | 678.757 | 1907.46 | 1650.264 | 4916.337 | 1 | 0 | 0 | 4916.337
87 | 9160 | New TL ES-Ash #2 | LV | 2008-2009 | 12899.61 | 16291.974 | 1142.489 | 68.245 | 0 | 0 | 30402.318 | 1 | 0 | 0 | 30402.318
88 | 9174 | Trans. SCADA Network Upgrade | HV | N/A | 0 | 2306.375 | 783.723 | 2.917 | 0 | 0 | 3093.015 | 9 | 0 | 0 | [8 empty] | 3093.015
89 | 10134 | Borrego Solar 1 Interconnection | LV | N/A | 7208.416 | 296.773 | 79.679 | 0.596 | 0 | 0 | 7585.464 | 2 | 0 | 0 |  | 7585.464
90 | 10140 | Ramona Transmission Reliability Project | LV | N/A | 6376.603 | 2068.859 | 414.015 | 139.655 | 6.941 | 0 | 9006.073 | 6 | 7 | 0 | [5 empty] | 4503.0365 | 4503.0365
91 | 10142 | Hoodoo Switchyard on TL50002 | HV | N/A | 0 | 0 | 14295.209 | 0.938 | 0 | 0 | 14296.147 | 2 | 0 | 0 |  | 14296.147
92 | 10150 | TL 13833-W2S | LV | N/A | 322.106 | 1165.887 | 2044.036 | 0 | 0 | 0 | 3532.029 | 1 | 0 | 0 | 3532.029
93 | 11126 | TL663 Mission to Kearny Reconductor | LV | 2010-2011 | 274.341 | 83.138 | 287.792 | 649.837 | 5038.151 | 1602.776 | 7936.035 | 1 | 0 | 0 | 7936.035
94 | 11127 | TL670 Mission to Clairemont Reconductor | LV | 2010-2011 | 576.285 | 4660.805 | 474.879 | 920.815 | 442.035 | 1.562 | 7076.381 | 1 | 0 | 0 | 7076.381
95 | 11133 | TL664-Wood to Steel | LV | N/A | 84.654 | 243.657 | 261.253 | 140.43 | 1766.206 | 160.136 | 2656.336 | 8 | 0 | 0 | [7 empty] | 2656.336
96 | 11138 | TL13804 Encina-Batiquitos-PQ-Wood to Steel | LV | N/A | 10107.451 | 2411.115 | 18.823 | 0 | 0 | 0 | 12537.389 | 8 | 0 | 0 | [7 empty] | 12537.389
97 | 11142 | TL13835 and TL13837 UG Conversion | LV | N/A | 13482.918 | 2086.719 | 11.962 | 0 | 0 | 0 | 15581.599 | 7 | 0 | 0 | [6 empty] | 15581.599
98 | 11143 | TL617 Direct Buried Cable Replacement | LV | N/A | 10227.866 | 1096.47 | 94.303 | 0 | 0 | 0 | 11418.639 | 6 | 0 | 0 | [5 empty] | 11418.639
99 | 11148 | TL626 Reconductor | LV | 2010-2011 | 5275.451 | 53.813 | 1.713 | 0 | 0 | 0 | 5330.977 | 7 | 0 | 0 | [6 empty] | 5330.977
100 | 11257 | Camp Pendleton 12kV Service | LV | N/A | 4338.264 | 9547.843 | 474.29 | 25.947 | 47.264 | 1.129 | 14434.737 | 10 | 0 | 0 | [9 empty] | 14434.737
101 | 12126 | TL613-Direct Buried Cable Replace. | LV | N/A | 0 | 4057.874 | 6428.218 | 0.843 | 56.128 | 0 | 10543.063 | 6 | 0 | 0 | [5 empty] | 10543.063
102 | 12127 | Pico Sub: Loop-In TL13833 | LV | 0 | 1724.116 | 850.222 | 25.147 | 0.007 | 0 | 0 | 2599.492 | 1 | 0 | 0 | 2599.492
103 | 12130 | Composite Core Conductor | LV | N/A | 2763.648 | 1901.025 | 420.427 | -149.395 | 0 | 0 | 4935.705 | 6 | 0 | 0 | [5 empty] | 4935.705
104 | 12133 | Transmission ROW: Palos Verde-North Gila | HV | N/A | 2741.942 | 434.24 | 33.015 | 0 | 0 | 0 | 3209.197 | 4 | 0 | 0 |  |  |  | 3209.197
105 | 12135 | TL629-E Reconductor | LV | 0 | 3680.419 | 3.559 | 0.606 | 0 | 0 | 0 | 3684.584 | 6 | 8 | 0 | [5 empty] | 1842.292 |  | 1842.292
106 | 12138 | Direct Buried Cable Replace.: TL615 & 659 | LV | N/A | 217.764 | 767.78 | 496.372 | 370.909 | 576.769 | 1041.457 | 3471.051 | 6 | 9 | 0 | [5 empty] | 1735.5255 |  |  | 1735.5255
107 | 12139 | TL633-Overhead Reconductor | LV | 2011-2012 | 9.527 | 6.289 | 704.967 | 805.999 | 3251.824 | 3657.39 | 8435.996 | 1 | 0 | 0 | 8435.996
108 | 12143 | TL23042 Outage Restoration | HV | N/A | 1595.08 | 117.246 | 19.018 | 0 | 0 | 0 | 1731.344 | 6 | 0 | 0 | [5 empty] | 1731.344
109 | 12144 | TL636-Wood to Steel | LV | N/A | 12.107 | 1.1 | 14.565 | 53.09 | 15.212 | 548.239 | 644.313 | 8 | 0 | 0 | [7 empty] | 644.313
110 | 12147 | TL628/643 Miguel Gateway Wood-to-Steel Proj | LV | N/A | 6.505 | 778.836 | 362.378 | 0.011 | 0 | 0 | 1147.73 | 8 | 0 | 0 | [7 empty] | 1147.73
111 | 12149 | TL694-Wood to Steel | LV | N/A | 0 | 0 | 3.829 | 23.422 | 204.111 | 470.414 | 701.776 | 8 | 0 | 0 | [7 empty] | 701.776
112 | 12154 | TL631 Reconductor Project | LV | 0 | 477.986 | 247.402 | 120.138 | 18.214 | 4.758 | 0 | 868.498 | 1 | 0 | 0 | 868.498
113 | 12156 | TL600-Reliability Pole Replacements | LV | N/A | 187.23 | 1162.259 | 106.382 | 650.915 | 131.791 | 150.472 | 2389.049 | 9 | 0 | 0 | [8 empty] | 2389.049
114 | 12159 | Aerial Marking For Safety | LV | #N/A | 403.225 | 495.452 | 556.302 | 918.106 | 1247.081 | 5707.616 | 9327.782 | 8 | 0 | 0 | [7 empty] | 9327.782
115 | 14125 | TL13815 Trans. Bridge Structure Reconfig | LV | N/A | 24.881 | 66.223 | 306.353 | 437.605 | 8088.103 | -0.01 | 8923.155 | 7 | 0 | 0 | [6 empty] | 8923.155
116 | 14133 | TL628-Direct Buried Cable Replace. | LV | N/A | 0 | 0 | 930.311 | 1898.329 | 965.306 | 110.098 | 3904.044 | 6 | 0 | 0 | [5 empty] | 3904.044
117 | 14140 | TL698 Wood to Steel Project | LV | N/A | 0 | 0 | 0 | 0 | 77.692 | 326.671 | 404.363 | 8 | 0 | 0 | [7 empty] | 404.363
118 | 15126 | Sycamore Landfill Relocation | LV | N/A | 30.26 | 88.814 | 46.592 | 658.383 | 16330.996 | 31.19 | 17186.235 | 7 | 0 | 0 | [6 empty] | 17186.235
119 | 16127 | Cole Grade Rd 20A | LV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
120 | 16129 | TL678 Reloc for Lake Jennings Mkt Place | LV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
121 | 16143 | TL600: MESA HEIGHTS LOOP-IN + RECONDUCT - GRC | LV | 2015-2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
122 | 16144 | POWAY-POMERADO 69KV #2 - GRC | LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
123 | 16145 | TL617-BALBOA AVE OVHD TO UG CONVERSION - GRC | LV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
124 | 16146 | TL638-COLE GRADE ROAD WIDENING - GRC | LV | #N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
125 | 16147 | TL617-REMOVAL OF ROSE CANYON TAP - GRC | LV | 2013-2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
126 | 16148 | TL13834-TRABUCO-CAPISTRANO 138KV LINE - GRC | LV | 2013-2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
127 | 16150 | TL23001/04 SAN LUIS REY TO MISSION | HV | 0 | 402.86 | 38.071 | 82.87 | 52.64 | -405.682 | 118.029 | 288.788 | 8 | 0 | 0 | [7 empty] | 288.788
128 | 16151 | TL660-CALTRAN I-5 WIDENING @ BIRMINGHAM | LV | N/A | 0 | 0 | 0 | 0 | 0 | 44.496 | 44.496 | 7 | 0 | 0 | [6 empty] | 44.496
129 | 16158 | TL605 Reconductor: Silvergate - Urban | LV | 2015-2016 | 0 | 0 | 0 | 0 | 0 | 1.781 | 1.781 | 1 | 0 | 0 | 1.781
130 | 17125 | Granite Substation 69kV Loop-In | LV | 2014-2015 | 0 | 0 | 0 | 0 | 0 | 21.836 | 21.836 | 1 | 0 | 0 | 21.836
131 | 17126 | TL696 Winterhawk Customer Relocation | LV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
132 | 17127 | TL611 OLD TOWN - PT LOMA | LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
133 | 17129 | TL603B SWEETWATER TAP REMOVAL | LV | 2012-2013 | 0 | 0 | 0 | 0 | 0 | 129.414 | 129.414 | 1 | 0 | 0 | 129.414
134 | 17131 | TL628 Relocation - Nationa City CarMax | LV | #N/A | 0 | 0 | 0 | 0 | 0 | -4 | -4 | 7 | 0 | 0 | [6 empty] | -4
135 | 17132 | TL6943 UG CONV-GENESEE AVE BRIDGE | LV | N/A | 0 | 0 | 0 | 11.431 | 21.706 | 1931.157 | 1964.294 | 7 | 0 | 0 | [6 empty] | 1964.294
136 | 17134 | TL6905 MIRAMESA COMMUNITY RELOCATION | LV | N/A | 0 | 0 | 0 | 0 | 0 | 3.014 | 3.014 | 7 | 0 | 0 | [6 empty] | 3.014
137 | 17135 | TL674 QUAIL MEADOWS | LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
138 | 17136 | TL23041-42-6910 OTAY VALLEY RESTORATION | HV | N/A | 0 | 0 | 0 | 0 | 0 | 1.847 | 1.847 | 7 | 0 | 0 | [6 empty] | 1.847
139 | 17137 | TL660 STUB POLE RELOCATION | LV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 0
140 | 17142 | TL690 DB CABLE REPLACE (OSIDE-OSIDE TAP) | LV | N/A | 0 | 0 | 0 | 0 | 0 | 58.737 | 58.737 | 6 | 0 | 0 | [5 empty] | 58.737
141 | 17143 | TL628 DB CALBE REPLACE (H ST & RANCHO DR) | LV | N/A | 0 | 0 | 0 | 0 | 0 | 22.052 | 22.052 | 7 | 0 | 0 | [6 empty] | 22.052
142 | 17144 | TL661/664 DB CABLE REPLACE (LUSK BLVD) | LV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
143 | 17145 | TL698 AVOCADO SUB GATEWAY DB CABLE REPLACE | LV | N/A | 0 | 0 | 0 | 0 | 0 | 26.037 | 26.037 | 6 | 0 | 0 | [5 empty] | 26.037
144 | 17146 | TL693 SAN LUIS REY GATEWAY DB CABLE REPLACE | LV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
145 | 17147 | TL697 OCEANSIDE SUB GATWEAY DB CABLE REPLACE | LV | N/A | 0 | 0 | 0 | 0 | 0 | 26.405 | 26.405 | 6 | 0 | 0 | [5 empty] | 26.405
146 | 17149 | 2ND 69KV LINE POMERADO TO POWAY | LV | 2014-2015 | 0 | 0 | 0 | 0 | 0 | 119.95 | 119.95 | 1 | 0 | 0 | 119.95
147 | TBD02 | TL662/666 Torrey Pines Relibaility Project | LV | #N/A | [6 empty] | 0 | 1 | 0 | 0 | 0
148 | TBD06 | TL667 DB Cable Replacement (El Camino Real) | LV | N/A | [6 empty] | 0 | 6 | 0 | 0 | [5 empty] | 0
149 | TBD15 | TL13820 Reconductor (Chicarita - Sycamore) | LV | 2012-2013 | [6 empty] | 0 | 1 | 0 | 0 | 0
150 | 12129 | Automated Fault Location | LV | N/A | 28.113 | 44.251 | 183.955 | 441.93 | 357.181 | 233 | 1288.43 | 9 | 0 | 0 | [8 empty] | 1288.43
151 | 12155 | Friars Sub Reliability Enhancement Project | LV | N/A | 40.402 | 1776.059 | 2029.094 | 442.709 | -0.022 | 0 | 4288.242 | 6 | 0 | 0 | [5 empty] | 4288.242
152 | 12160 | Transmission System Spares | HV | N/A | 0 | 9451.101 | -3866.014 | 0 | 0 | 0 | 5585.087 | 6 | 0 | 0 | [5 empty] | 5585.087
153 | 13132 | SONGS Mesa: New 230kV Switchyard | HV | N/A | 0 | 9.738 | 197.272 | 26905.228 | 32076.777 | 23786.917 | 82975.932 | 1 | 0 | 0 | 82975.932
154 | 13139 | CBM Gas Circuit Breakers | HV | N/A | 0 | 26.756 | 1954.597 | 3207.521 | 2032.595 | 1378.68 | 8600.149 | 6 | 0 | 0 | [5 empty] | 8600.149
155 | 14134 | Union Pacific RR Land Purchase | LV | N/A | 0 | 0 | 21540.422 | 1.518 | 0 | 0 | 21541.94 | 6 | 0 | 0 | [5 empty] | 21541.94
156 | 13132 | SONGS Synchronous Condenser | HV | 2012-2013 | 0 | 9.738 | 197.272 | 26905.228 | 32076.777 | 23786.917 | 82975.932 | 1 | 0 | 0 | 82975.932
157 |  | TL6931 WTS (CNF) | LV | N/A | [6 empty] | 0 | 8 | 0 | 0 | [7 empty] | 0
158 | 16103 | San Mateo Substation Expansion | LV | 0 | [6 empty] | 0 | 6 | 0 | 0 | [5 empty] | 0
159 | 16128 | Basilone Substation 15 Mvar Capacitor | LV | 2015-2016 | [6 empty] | 0 | 1 | 0 | 0 | 0
160 | 15132 | Mission Bank #51 and #52 replacement | LV | 2013-2014 | [6 empty] | 0 | 1 | 0 | 0 | 0

## 2015_2017 Accounting
Row Line/No. | Budget Code | Project Name | Voltage Level | CAISO | 2015 Project Actual Dollars (thousands) | 2016 Project Actual Dollars (thousands) | 2017 Project Actual Dollars to-date (thousands) | 3 Year Actual Spent | 1st assignment | 2nd assignment | 3rd assignment | Peak-Driven | Gen Interconnection | Load Interconnection | Improve grid efficiency (LCR) | Support public policy requirements or goals (RPS) | Upgrade, repair or replacement of existing facilities | Relocation or removal of facilities | Customer and/or employee safety (e.g., fire-hardening). | Grid visibility, control and measurement. | Provide reliable service under conditions not driven by peak load.
1 | 2252 | Mira Sorrento 138/12KV Sub & Cirs. 1442 Thru 1446 | LV | N/A | 679.907 | 50.954 | -0.034 | 730.827 | 1 | 3 | 0 | 365.4135 |  | 365.4135
2 | 2258 | Salt Creek-Land Purchase, New Substa. & 3 New Ckts | LV | 2013-2014 | 1871.053 | 18275.712 | 15879.401 | 36026.166 | 1 | 3 | 0 | 18013.083 |  | 18013.083
3 | 4138 | Sunrise Powerlink | HV | 0 | 65992.774 | -1329.612 | 0.73 | 64663.892 | 4 | 5 | 1 | 32331.946 |  |  | 6466.3892 | 25865.5568
4 | 5253 | Ocean Ranch Land Purchase, New Substation | LV | 2015-2016 | 1003.951 | 1228.021 | 1692.071 | 3924.043 | 1 | 0 | 0 | 3924.043
5 | 6129 | South Orange County Reliability Enhancement (SOCRE) | HV | 2010-2011 | 6695.268 | 11761.027 | 12837.907 | 31294.202 | 1 | 6 | 0 | 15647.101 |  |  |  |  | 15647.101
6 | 6132 | Relocate South Bay Substation | HV | 2009-2010 | 61022.946 | 42324.012 | 1055.539 | 104402.497 | 7 | 0 | 0 | [6 empty] | 104402.497
7 | 7139 | ECO Substation | HV | N/A | 8759.043 | 1171.293 | 60.043 | 9990.379 | 5 | 0 | 0 |  |  |  |  | 9990.379
8 | 8165 | TL 629 DE-GC-CN SW Pole Replacements - CNF | LV | N/A | 10519.426 | 84800.132 | 89254.137 | 184573.695 | 8 | 0 | 0 | [7 empty] | 184573.695
9 | 9125 | TL 637 CRE-ST SW Pole Replacements | LV | N/A | 1882.942 | 8.93 | 0 | 1891.872 | 8 | 0 | 0 | [7 empty] | 1891.872
10 | 9132 | TL6926 Rincon-Valley Center SW Pole Replace | LV | N/A | 662.415 | 1036.562 | 785.5 | 2484.477 | 8 | 0 | 0 | [7 empty] | 2484.477
11 | 9137 | TL649 Otay-San Ysidro-Border SW Pole Replace | LV | N/A | 924.592 | 975.391 | 675.322 | 2575.305 | 8 | 0 | 0 | [7 empty] | 2575.305
12 | 9142 | TL686 Warners to Narrows SW Pole Replace TL687 Borrego Springs | LV | N/A | 106.975 | 100.19 | 100.424 | 307.589 | 8 | 0 | 0 | [7 empty] | 307.589
13 | 9166 | TL13821 and TL13828-Fanita Junction Enhancement | LV | 2009-2010 | 27752.576 | 14294.963 | -122.519 | 41925.02 | 1 | 0 | 0 | 41925.02
14 | 9276 | Poseidon Project-Modify Cannon Sub & Install 2 Ckts | LV | N/A | -603.362 | 0.733 | 0 | -602.629 | 3 | 0 | 0 |  |  | -602.629
15 | 10143 | Wood to Steel Pole Replace.-TL690E | LV | 2013-2014 | 328.254 | 414.77 | 678.018 | 1421.042 | 8 | 1 | 0 | 710.521 | [6 empty] | 710.521
16 | 10144 | TL691 Avo-Mon Wood to Steel | LV | N/A | 119.766 | 1206.005 | 875.47 | 2201.241 | 8 | 0 | 0 | [7 empty] | 2201.241
17 | 10146 | TL695/6971 Reconductor & Wood to Steel | LV | 2011-2012 | 1215.066 | 934.417 | 1069.644 | 3219.127 | 1 | 8 | 0 | 1609.5635 | [6 empty] | 1609.5635
18 | 10147 | TL697 San Luis Rey Wood to Steel | LV | N/A | 59.838 | 605.095 | 1006.364 | 1671.297 | 8 | 1 | 0 | 835.6485 | [6 empty] | 835.6485
19 | 10149 | Wood to Steel Pole Replace.-TL6912 | LV | N/A | 34.493 | 542.907 | 760.08 | 1337.48 | 1 | 8 | 0 | 668.74 | [6 empty] | 668.74
20 | 11146 | Ocotillo Express-Interconnect. Switchyard | LV | N/A | 7.152 | 221.842 | 1.017 | 230.011 | 2 | 0 | 0 |  | 230.011
21 | 11149 | CSolar-Generator Interconnection | LV | N/A | 63.27 | -25.897 | -118.401 | -81.028 | 2 | 0 | 0 |  | -81.028
22 | 11150 | Centinela-Generator Interconnection | LV | N/A | 264.786 | 281.435 | -579.876 | -33.655 | 2 | 0 | 0 |  | -33.655
23 | 12140 | Merchant Switchyard & Transmission | LV | N/A | 829.319 | 940.274 | 152.562 | 1922.155 | 7 | 0 | 0 | [6 empty] | 1922.155
24 | 12142 | Campo Verde Solar-Generator Interconnect. | LV | N/A | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
25 | 12158 | Pio Pico Energy Ctr. Gen. Interconnect | LV | N/A | 6527.608 | 334.157 | -21.997 | 6839.768 | 2 | 0 | 0 |  | 6839.768
26 | 13128 | Sycamore-Penasquitos New 230KV TL | HV | 2012-2013 | 20979.044 | 38685.581 | 66148.081 | 125812.706 | 1 | 5 | 0 | 62906.353 |  |  |  | 62906.353
27 | 13129 | 500 KV Series Capacitor-ECO Sub | HV | 0 | 1.962 | 0 | 0 | 1.962 | 4 | 0 | 0 |  |  |  | 1.962
28 | 13130 | TL674A Reconfigure/TL666D RFS | LV | 2012-2013 | 94.25 | 381.414 | 763.583 | 1239.247 | 7 | 0 | 0 | [6 empty] | 1239.247
29 | 13131 | Talega-Add Synchronous Condensers | HV | 2012-2013 | 26537.708 | 4497.072 | 63.364 | 31098.144 | 1 | 0 | 0 | 31098.144
30 | 13140 | IV West Generator Interconnection (Q608) | LV | N/A | -497.43 | 15.418 | 0 | -482.012 | 2 | 0 | 0 |  | -482.012
31 | 13243 | New Vine 69/12KV Substation | LV | 2014-2015 | 1750.74 | 9591.161 | 17343.796 | 28685.697 | 1 | 3 | 0 | 14342.8485 |  | 14342.8485
32 | 14127 | Imperial Valley Flow Controller | HV | 2013-2014 | 11075.008 | 26993.784 | 11291.793 | 49360.585 | 4 | 0 | 0 |  |  |  | 49360.585
33 | 14128 | Artesian 230kV Expansion-Prel. Eng. | HV | 2013-2014 | 1428.528 | 1250.991 | 812.767 | 3492.286 | 1 | 0 | 0 | 3492.286
34 | 14130 | San Luis Rey Synchronous Condensers | HV | 2013-2014 | 66571.721 | 55837.773 | 19502.987 | 141912.481 | 1 | 5 | 0 | 70956.2405 |  |  |  | 70956.2405
35 | 14131 | Miguel 500kV Voltage Support | HV | 2013-2014 | 4546.09 | 32559.167 | 18926.502 | 56031.759 | 1 | 0 | 0 | 56031.759
36 | 14137 | TL6975 Escondido - San Marcos | LV | 2013-2014 | 691.756 | 1119.592 | 573.604 | 2384.952 | 1 | 0 | 0 | 2384.952
37 | 14138 | TL13835 Wood to Steel | LV | N/A | 10.718 | 164.858 | 221.944 | 397.52 | 1 | 8 | 0 | 198.76 | [6 empty] | 198.76
38 | 15129 | Jacumba Solar Gen Interconnect (Q644A) | LV | N/A | 87.281 | 837.314 | 2074.907 | 2999.502 | 2 | 0 | 0 |  | 2999.502
39 | 15133 | Tule Wind - Generator Interconnect | LV | N/A | 6.63 | 103.686 | 541.268 | 651.584 | 2 | 0 | 0 |  | 651.584
40 | 15258 | Mid-Coast Trolley Extension Project | LV | N/A | -267.196 | 7700.695 | 17231.571 | 24665.07 | 7 | 0 | 0 | [6 empty] | 24665.07
41 | 16132 | TL690A | LV | 2013-2014 | 0 | 681.784 | 712.003 | 1393.787 | 1 | 8 | 0 | 696.8935 | [6 empty] | 696.8935
42 | 16134 | Carlsbad Energy Center Project | LV | N/A | 0 | 697.697 | 660.33 | 1358.027 | 2 | 0 | 0 |  | 1358.027
43 | 16137 | Vista Energy Storage Project | LV | N/A | 0 | 0 | 421.538 | 421.538 | 2 | 0 | 0 |  | 421.538
44 | 16157 | MIGUEL TO BAY BLVD NEW 230KV LINE | HV | 2015-2016 | 0 | 0 | 262.344 | 262.344 | 1 | 0 | 0 | 262.344
45 | 16249 | Expedited Storage Procurement (ESP) | LV | N/A | 0 | 56625.128 | 34947.807 | 91572.935 | 2 | 0 | 0 |  | 91572.935
46 | 17130 | BC14XXX (TL6906 MESA RIM LOOP-IN) | LV | 2013-2014 | 0 |  |  | 0 | 1 | 8 | 7
47 | 10138 | Synchronized Phasor Measurement System | HV | N/A | 2571.926 | 2364.242 | 1831.592 | 6767.76 | 9 | 0 | 0 | [8 empty] | 6767.76
48 | 6133 | Install Bank 61 At Miguel | HV | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0 | [5 empty] | 0 | 0
49 | 6251 | Otay Substation Rebuild | HV | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
50 | 8162 | Substation Security Installations | HV | N/A | 10203.139 | 5900.771 | 143.235 | 16247.145 | 9 | 0 | 0 | [8 empty] | 16247.145
51 | 8163 | IV Sub Bank 82 Addition | HV | 0 | 37.194 | 6.673 | 0.693 | 44.56 | 2 | 6 | 0 |  | 22.28 |  |  |  | 22.28
52 | 9168 | 69KV & 12KV Capacitor Installation | LV | #N/A | 34.595 | 0 | 0 | 34.595 | 1 | 10 | 0 | 17.2975 | [8 empty] | 17.2975
53 | 9170 | Overstressed Breaker Replacements | HV | #N/A | 3233.68 | 1358.697 | 165.49 | 4757.867 | 10 | 6 | 0 | [5 empty] | 2378.9335 |  |  |  | 2378.9335
54 | 10135 | Los Coches Sub-Rebuild 138/69kV | LV | N/A | 25759.863 | 18152.157 | 8956.466 | 52868.486 | 6 | 0 | 0 | [5 empty] | 52868.486
55 | 12125 | Sunnyside 69/12kV Rebuild | LV | N/A | 4861.52 | 202.033 | -2.169 | 5061.384 | 6 | 0 | 0 | [5 empty] | 5061.384
56 | 12132 | SCADA Expansion-Transmission | HV | #N/A | 545.749 | 1870.345 | 917.847 | 3333.941 | 9 | 0 | 0 | [8 empty] | 3333.941
57 | 12134 | Penasquitos-Add 230kV Capacitor Banks | HV | 0 | -2.584 | 0 | 0 | -2.584 | 1 | 0 | 0 | -2.584
58 | 12157 | Sycamore Canyon-Add 60 KV Reactor Banks | LV | 0 | 0.906 | 0 | 0 | 0.906 | 10 | 0 | 0 | [9 empty] | 0.906
59 | 13126 | Sta F Substation Improvements | LV | N/A | 0.179 | 0 | 0 | 0.179 | 6 | 0 | 0 | [5 empty] | 0.179
60 | 13127 | Miguel Substation BK 80 Replacement | HV | N/A | -3642 | 0 | -0.767 | -3642.767 | 6 | 0 | 0 | [5 empty] | -3642.767
61 | 13133 | Shunt Reactor on Suncrest 500kV Bus | HV | N/A | 688.526 | 12.821 | 74.417 | 775.764 | 10 | 0 | 0 | [9 empty] | 775.764
62 | 13134 | Talega Bank 50 Replacement | LV | 0 | 3.689 | 778.186 | 279.73 | 1061.605 | 6 | 0 | 0 | [5 empty] | 1061.605
63 | 13136 | Wabash Substation Rebuild | LV | N/A | 2211.435 | 622.929 | -10.51 | 2823.854 | 6 | 0 | 0 | [5 empty] | 2823.854
64 | 13242 | Kearny 69/12KV Sub Rebuild/Reloc-Pre Eng | LV | N/A | 206.56 | 4846.38 | 2491.068 | 7544.008 | 7 | 0 | 0 | [6 empty] | 7544.008
65 | 14129 | SONGS Station Light & Power | HV | N/A | 1394.253 | 345.152 | 0.431 | 1739.836 | 7 | 0 | 0 | [6 empty] | 1739.836
66 | 14132 | Imperial Valley Sub Oper. Reliability & Security | HV | N/A | 4538.463 | 1070.913 | 1282.525 | 6891.901 | 9 | 0 | 0 | [8 empty] | 6891.901
67 | 14142 | Encina Bank 61 | HV | 0 | 8542.379 | 3184.625 | 8.1 | 11735.104 | 6 | 0 | 0 | [5 empty] | 11735.104
68 | 14143 | Poway Substation Rebuild | LV | #N/A | 2636.559 | 6635.203 | 3089.528 | 12361.29 | 6 | 0 | 0 | [5 empty] | 12361.29
69 | 15128 | Silvergate Sub: Install Spare Transformer | HV | N/A | 1750.716 | 485.415 | 54.38 | 2290.511 | 1 | 0 | 0 | 2290.511
70 | 15130 | Miguel Sub Hydro & Water Quality Enhance | HV | N/A | 854.374 | 2555.335 | 323.642 | 3733.351 | 6 | 0 | 0 | [5 empty] | 3733.351
71 | 15132 | Mission Bank 71 Addition | HV | 0 | 0 | 2098.169 | 1352.433 | 3450.602 | 6 | 0 | 0 | [5 empty] | 3450.602
72 | 15246 | Rancho Santa Fe Sub Fire Hardening | LV | #N/A | 0 | 638.718 | 1712.426 | 2351.144 | 8 | 0 | 0 | [7 empty] | 2351.144
73 | 16128 | Camp Pendleton Voltage Support | LV | 2015-2016 | 0 | 2037.322 | 1882.725 | 3920.047 | 6 | 0 | 0 | [5 empty] | 3920.047
74 | 16130 | Warners Substation 69kV Control & Protection Replacement | LV | N/A | 0 | 1178.188 | 1402.064 | 2580.252 | 6 | 0 | 0 | [5 empty] | 2580.252
75 | 16131 | Descanso Substation 69kV Control & Protection Replacement | LV | N/A | 152.578 | 1258.831 | 1419.005 | 2830.414 | 6 | 0 | 0 | [5 empty] | 2830.414
76 | 16133 | Substation Auxiliary Power System | LV | #N/A | 0 | 1154.354 | 469.81 | 1624.164 | 9 | 0 | 0 | [8 empty] | 1624.164
77 | 16159 | HVDC Conversion of Southwest Powerlink | HV | 0 | 0 | 0 | 1084.16 | 1084.16 | 4 | 0 | 0 |  |  |  | 1084.16
78 | TBD20.0 | IV Bank 80 Replacement | HV | 0 |  |  |  | 0 | 6 | 0 | 0 | [5 empty] | 0
79 | TBD36.0 | Avocado Sub Rebuild | LV | N/A |  |  |  | 0 | 6 | 0 | 0 | [5 empty] | 0
80 | 7138 | Camp Pendleton Tower Lighting | LV | N/A | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 0
81 | 9134 | TL6910-Miguel to Border SW Pole Replace | LV | N/A | 0.085 | 0 | 0 | 0.085 | 8 | 0 | 0 | [7 empty] | 0.085
82 | 9135 | TL616-Rancho Santa Fe-Bernardo-Lake Hodges SW Pole | LV | N/A | 86.889 | 0 | 0 | 86.889 | 8 | 0 | 0 | [7 empty] | 86.889
83 | 9136 | TL6914 Los Coches-Loveland SW Pole Replace | LV | N/A | 13961.846 | 102.585 | 67.805 | 14132.236 | 8 | 0 | 0 | [7 empty] | 14132.236
84 | 9138 | TL 6913 Poway-Pomerado SW Pole Replace. | LV | N/A | 0.008 | 0.042 | 0 | 0.05 | 1 | 8 | 0 | 0.025 | [6 empty] | 0.025
85 | 11151 | TL694A Melrose Loop-In Project | LV | 0 | 1417.017 | 81.447 | 0 | 1498.464 | 1 | 0 | 0 | 1498.464
86 | 9153 | TL676 Mission to Mesa Heights Reconductor | LV | 2010-2011 | 678.757 | 1907.46 | 1650.264 | 4236.481 | 1 | 0 | 0 | 4236.481
87 | 9160 | New TL ES-Ash #2 | LV | 2008-2009 | 68.245 | 0 | 0 | 68.245 | 1 | 0 | 0 | 68.245
88 | 9174 | Trans. SCADA Network Upgrade | HV | N/A | 2.917 | 0 | 0 | 2.917 | 9 | 0 | 0 | [8 empty] | 2.917
89 | 10134 | Borrego Solar 1 Interconnection | LV | N/A | 0.596 | 0 | 0 | 0.596 | 2 | 0 | 0 |  | 0.596
90 | 10140 | Ramona Transmission Reliability Project | LV | N/A | 139.655 | 6.941 | 0 | 146.596 | 6 | 7 | 0 | [5 empty] | 73.298 | 73.298
91 | 10142 | Hoodoo Switchyard on TL50002 | HV | N/A | 0.938 | 0 | 0 | 0.938 | 2 | 0 | 0 |  | 0.938
92 | 10150 | TL 13833-W2S | LV | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
93 | 11126 | TL663 Mission to Kearny Reconductor | LV | 2010-2011 | 649.837 | 5038.151 | 1602.776 | 7290.764 | 1 | 0 | 0 | 7290.764
94 | 11127 | TL670 Mission to Clairemont Reconductor | LV | 2010-2011 | 920.815 | 442.035 | 1.562 | 1364.412 | 1 | 0 | 0 | 1364.412
95 | 11133 | TL664-Wood to Steel | LV | N/A | 140.43 | 1766.206 | 160.136 | 2066.772 | 8 | 0 | 0 | [7 empty] | 2066.772
96 | 11138 | TL13804 Encina-Batiquitos-PQ-Wood to Steel | LV | N/A | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 0
97 | 11142 | TL13835 and TL13837 UG Conversion | LV | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
98 | 11143 | TL617 Direct Buried Cable Replacement | LV | N/A | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
99 | 11148 | TL626 Reconductor | LV | 2010-2011 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
100 | 11257 | Camp Pendleton 12kV Service | LV | N/A | 25.947 | 47.264 | 1.129 | 74.34 | 10 | 0 | 0 | [9 empty] | 74.34
101 | 12126 | TL613-Direct Buried Cable Replace. | LV | N/A | 0.843 | 56.128 | 0 | 56.971 | 6 | 0 | 0 | [5 empty] | 56.971
102 | 12127 | Pico Sub: Loop-In TL13833 | LV | 0 | 0.007 | 0 | 0 | 0.007 | 1 | 0 | 0 | 0.007
103 | 12130 | Composite Core Conductor | LV | N/A | -149.395 | 0 | 0 | -149.395 | 6 | 0 | 0 | [5 empty] | -149.395
104 | 12133 | Transmission ROW: Palos Verde-North Gila | HV | N/A | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  |  |  | 0
105 | 12135 | TL629-E Reconductor | LV | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 0 | [5 empty] | 0 |  | 0
106 | 12138 | Direct Buried Cable Replace.: TL615 & 659 | LV | N/A | 370.909 | 576.769 | 1041.457 | 1989.135 | 6 | 9 | 0 | [5 empty] | 994.5675 |  |  | 994.5675
107 | 12139 | TL633-Overhead Reconductor | LV | 2011-2012 | 805.999 | 3251.824 | 3657.39 | 7715.213 | 1 | 0 | 0 | 7715.213
108 | 12143 | TL23042 Outage Restoration | HV | N/A | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
109 | 12144 | TL636-Wood to Steel | LV | N/A | 53.09 | 15.212 | 548.239 | 616.541 | 8 | 0 | 0 | [7 empty] | 616.541
110 | 12147 | TL628/643 Miguel Gateway Wood-to-Steel Proj | LV | N/A | 0.011 | 0 | 0 | 0.011 | 8 | 0 | 0 | [7 empty] | 0.011
111 | 12149 | TL694-Wood to Steel | LV | N/A | 23.422 | 204.111 | 470.414 | 697.947 | 8 | 0 | 0 | [7 empty] | 697.947
112 | 12154 | TL631 Reconductor Project | LV | 0 | 18.214 | 4.758 | 0 | 22.972 | 1 | 0 | 0 | 22.972
113 | 12156 | TL600-Reliability Pole Replacements | LV | N/A | 650.915 | 131.791 | 150.472 | 933.178 | 9 | 0 | 0 | [8 empty] | 933.178
114 | 12159 | Aerial Marking For Safety | LV | #N/A | 918.106 | 1247.081 | 5707.616 | 7872.803 | 8 | 0 | 0 | [7 empty] | 7872.803
115 | 14125 | TL13815 Trans. Bridge Structure Reconfig | LV | N/A | 437.605 | 8088.103 | -0.01 | 8525.698 | 7 | 0 | 0 | [6 empty] | 8525.698
116 | 14133 | TL628-Direct Buried Cable Replace. | LV | N/A | 1898.329 | 965.306 | 110.098 | 2973.733 | 6 | 0 | 0 | [5 empty] | 2973.733
117 | 14140 | TL698 Wood to Steel Project | LV | N/A | 0 | 77.692 | 326.671 | 404.363 | 8 | 0 | 0 | [7 empty] | 404.363
118 | 15126 | Sycamore Landfill Relocation | LV | N/A | 658.383 | 16330.996 | 31.19 | 17020.569 | 7 | 0 | 0 | [6 empty] | 17020.569
119 | 16127 | Cole Grade Rd 20A | LV | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
120 | 16129 | TL678 Reloc for Lake Jennings Mkt Place | LV | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
121 | 16143 | TL600: MESA HEIGHTS LOOP-IN + RECONDUCT - GRC | LV | 2015-2016 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
122 | 16144 | POWAY-POMERADO 69KV #2 - GRC | LV | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
123 | 16145 | TL617-BALBOA AVE OVHD TO UG CONVERSION - GRC | LV | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
124 | 16146 | TL638-COLE GRADE ROAD WIDENING - GRC | LV | #N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
125 | 16147 | TL617-REMOVAL OF ROSE CANYON TAP - GRC | LV | 2013-2014 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
126 | 16148 | TL13834-TRABUCO-CAPISTRANO 138KV LINE - GRC | LV | 2013-2014 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
127 | 16150 | TL23001/04 SAN LUIS REY TO MISSION | HV | 0 | 52.64 | -405.682 | 118.029 | -235.013 | 8 | 0 | 0 | [7 empty] | -235.013
128 | 16151 | TL660-CALTRAN I-5 WIDENING @ BIRMINGHAM | LV | N/A | 0 | 0 | 44.496 | 44.496 | 7 | 0 | 0 | [6 empty] | 44.496
129 | 16158 | TL605 Reconductor: Silvergate - Urban | LV | 2015-2016 | 0 | 0 | 1.781 | 1.781 | 1 | 0 | 0 | 1.781
130 | 17125 | Granite Substation 69kV Loop-In | LV | 2014-2015 | 0 | 0 | 21.836 | 21.836 | 1 | 0 | 0 | 21.836
131 | 17126 | TL696 Winterhawk Customer Relocation | LV | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
132 | 17127 | TL611 OLD TOWN - PT LOMA | LV | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
133 | 17129 | TL603B SWEETWATER TAP REMOVAL | LV | 2012-2013 | 0 | 0 | 129.414 | 129.414 | 1 | 0 | 0 | 129.414
134 | 17131 | TL628 Relocation - Nationa City CarMax | LV | #N/A | 0 | 0 | -4 | -4 | 7 | 0 | 0 | [6 empty] | -4
135 | 17132 | TL6943 UG CONV-GENESEE AVE BRIDGE | LV | N/A | 11.431 | 21.706 | 1931.157 | 1964.294 | 7 | 0 | 0 | [6 empty] | 1964.294
136 | 17134 | TL6905 MIRAMESA COMMUNITY RELOCATION | LV | N/A | 0 | 0 | 3.014 | 3.014 | 7 | 0 | 0 | [6 empty] | 3.014
137 | 17135 | TL674 QUAIL MEADOWS | LV | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 0
138 | 17136 | TL23041-42-6910 OTAY VALLEY RESTORATION | HV | N/A | 0 | 0 | 1.847 | 1.847 | 7 | 0 | 0 | [6 empty] | 1.847
139 | 17137 | TL660 STUB POLE RELOCATION | LV | N/A | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 0
140 | 17142 | TL690 DB CABLE REPLACE (OSIDE-OSIDE TAP) | LV | N/A | 0 | 0 | 58.737 | 58.737 | 6 | 0 | 0 | [5 empty] | 58.737
141 | 17143 | TL628 DB CALBE REPLACE (H ST & RANCHO DR) | LV | N/A | 0 | 0 | 22.052 | 22.052 | 7 | 0 | 0 | [6 empty] | 22.052
142 | 17144 | TL661/664 DB CABLE REPLACE (LUSK BLVD) | LV | N/A | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
143 | 17145 | TL698 AVOCADO SUB GATEWAY DB CABLE REPLACE | LV | N/A | 0 | 0 | 26.037 | 26.037 | 6 | 0 | 0 | [5 empty] | 26.037
144 | 17146 | TL693 SAN LUIS REY GATEWAY DB CABLE REPLACE | LV | N/A | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
145 | 17147 | TL697 OCEANSIDE SUB GATWEAY DB CABLE REPLACE | LV | N/A | 0 | 0 | 26.405 | 26.405 | 6 | 0 | 0 | [5 empty] | 26.405
146 | 17149 | 2ND 69KV LINE POMERADO TO POWAY | LV | 2014-2015 | 0 | 0 | 119.95 | 119.95 | 1 | 0 | 0 | 119.95
147 | TBD02 | TL662/666 Torrey Pines Relibaility Project | LV | #N/A |  |  |  | 0 | 1 | 0 | 0 | 0
148 | TBD06 | TL667 DB Cable Replacement (El Camino Real) | LV | N/A |  |  |  | 0 | 6 | 0 | 0 | [5 empty] | 0
149 | TBD15 | TL13820 Reconductor (Chicarita - Sycamore) | LV | 2012-2013 |  |  |  | 0 | 1 | 0 | 0 | 0
150 | 12129 | Automated Fault Location | LV | N/A | 441.93 | 357.181 | 233 | 1032.111 | 9 | 0 | 0 | [8 empty] | 1032.111
151 | 12155 | Friars Sub Reliability Enhancement Project | LV | N/A | 442.709 | -0.022 | 0 | 442.687 | 6 | 0 | 0 | [5 empty] | 442.687
152 | 12160 | Transmission System Spares | HV | N/A | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 0
153 | 13132 | SONGS Mesa: New 230kV Switchyard | HV | N/A | 26905.228 | 32076.777 | 23786.917 | 82768.922 | 1 | 0 | 0 | 82768.922
154 | 13139 | CBM Gas Circuit Breakers | HV | N/A | 3207.521 | 2032.595 | 1378.68 | 6618.796 | 6 | 0 | 0 | [5 empty] | 6618.796
155 | 14134 | Union Pacific RR Land Purchase | LV | N/A | 1.518 | 0 | 0 | 1.518 | 6 | 0 | 0 | [5 empty] | 1.518
156 | 13132 | SONGS Synchronous Condenser | HV | 2012-2013 | 26905.228 | 32076.777 | 23786.917 | 82768.922 | 1 | 0 | 0 | 82768.922
157 |  | TL6931 WTS (CNF) | LV | N/A |  |  |  | 0 | 8 | 0 | 0 | [7 empty] | 0
158 | 16103 | San Mateo Substation Expansion | LV | 0 |  |  |  | 0 | 6 | 0 | 0 | [5 empty] | 0
159 | 16128 | Basilone Substation 15 Mvar Capacitor | LV | 2015-2016 |  |  |  | 0 | 1 | 0 | 0 | 0
160 | 15132 | Mission Bank #51 and #52 replacement | LV | 2013-2014 |  |  |  | 0 | 1 | 0 | 0 | 0

## 2018_2022 Accounting
Row Line/No. | Budget Code | Project Name | 2017 Project Expected Dollars Into Ratebase (thousands) | 2018 Project Expected Dollars Into Ratebase (thousands) | 2019 Project Expected Dollars Into Ratebase (thousands) | 2020 Project Expected Dollars Into Ratebase (thousands) | 2021 Project Expected Dollars Into Ratebase (thousands) | 2022 Project Expected Dollars Into Ratebase (thousands) | Assignment1 | Assignment2 | Assignment3 | Peak-Driven | Gen Interconnection | Load Interconnection | Improve grid efficiency (LCR) | Support public policy requirements or goals (RPS) | Upgrade, repair or replacement of existing facilities | Relocation or removal of facilities | Customer and/or employee safety (e.g., fire-hardening). | Grid visibility, control and measurement. | Provide reliable service under conditions not driven by peak load.
1 | 2252 | Mira Sorrento 138/12KV Sub & Cirs. 1442 Thru 1446 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0
2 | 2258 | Salt Creek-Land Purchase, New Substa. & 3 New Ckts | 25539.0466 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0
3 | 4138 | Sunrise Powerlink | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 1
4 | 5253 | Ocean Ranch Land Purchase, New Substation | 0 | 0 | 20388.4509 | 0 | 0 | 0 | 1 | 0 | 0 | 20388.4509
5 | 6129 | South Orange County Reliability Enhancement (SOCRE) | 0 | 0 | 125907 | 5362 | 69039 | 79123 | 1 | 6 | 0 | 139715.5 |  |  |  |  | 139715.5
6 | 6132 | Relocate South Bay Substation | 0 | 4485.196 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 4485.196
7 | 6133 | Install Bank 61 At Miguel | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0
8 | 6251 | Otay Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
9 | 7138 | Camp Pendleton Tower Lighting | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
10 | 7139 | ECO Substation | -25 | 1500 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  |  |  |  | 1500 | [5 empty] | d
11 | 8158 | New TL13835 Tap at Talega | 4.6963 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
12 | 8162 | Substation Security Installations | 140.3618 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
13 | 8163 | IV Sub Bank 82 Addition | -0.0005 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0
14 | 9125 | TL 637 CRE-ST SW Pole Replacements | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
15 | 9132 | TL6926 Rincon-Valley Center SW Pole Replace | 0 | 0 | 0 | 10857.6672 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 10857.6672
16 | 9134 | TL6910-Miguel to Border SW Pole Replace | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
17 | 9135 | TL616-Rancho Santa Fe-Bernardo-Lake Hodges SW Pole | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
18 | 9136 | TL6914 Los Coches-Loveland SW Pole Replace | 56.4992 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
19 | 9137 | TL649 Otay-San Ysidro-Border SW Pole Replace | 0 | 0 | 13254.7909 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 13254.7909
20 | 9138 | TL 6913 Poway-Pomerado SW Pole Replace. | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 0
21 | 9142 | TL686 Warners to Narrows SW Pole Replace TL687 Borrego Springs | 0 | 0 | 0 | 0 | 9256.3088 | 0 | 8 | 0 | 0
22 | 9153 | TL676 Mission to Mesa Heights Reconductor | 0 | 11870.9081 | 640 | 0 | 0 | 0 | 1 | 0 | 0 | 12510.9081
23 | 9160 | New TL ES-Ash #2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
24 | 9166 | TL13821 and TL13828-Fanita Junction Enhancement | 45.0202 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
25 | 9168 | 69KV & 12KV Capacitor Installation | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 0
26 | 9170 | Overstressed Breaker Replacements | 0 | 373.1517 | 0 | 0 | 0 | 0 | 10 | 6 | 0 | [5 empty] | 186.5758 |  |  |  | 186.5758
27 | 9174 | Trans. SCADA Network Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
28 | 9276 | Poseidon Project-Modify Cannon Sub & Install 2 Ckts | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
29 | 10134 | Borrego Solar 1 Interconnection | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
30 | 10135 | Los Coches Sub-Rebuild 138/69kV | 11427.8527 | 100 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 100
31 | 10138 | Synchronized Phasor Measurement System | 2155.6226 | 4260 | 2368 | 2368 | 2368 | 2368 | 9 | 0 | 0 | [8 empty] | 13732
32 | 10140 | Ramona Transmission Reliability Project | -0.00047 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 0
33 | 10142 | Hoodoo Switchyard on TL50002 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
34 | 10143 | Wood to Steel Pole Replace.-TL690E | 0 | 0 | 0 | 0 | 32767.4718 | 14848 | 8 | 1 | 0 | 23807.7359 | [6 empty] | 23807.7359
35 | 10144 | TL691 Avo-Mon Wood to Steel | 0 | 0 | 0 | 13179.3561 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 13179.3561
36 | 10146 | TL695/6971 Reconductor & Wood to Steel | 0 | 0 | 4598.3629 | 8637.4332 | 0 | 0 | 1 | 8 | 0 | 6617.898 | [6 empty] | 6617.898
37 | 10147 | TL697 San Luis Rey Wood to Steel | 4241.194 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 0
38 | 10149 | Wood to Steel Pole Replace.-TL6912 | 0 | 0 | 8939.0269 | 0 | 0 | 0 | 1 | 8 | 0 | 4469.5134 | [6 empty] | 4469.5134
39 | 10150 | TL 13833-W2S | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
40 | 11126 | TL663 Mission to Kearny Reconductor | 0 | 13999.4608 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 13999.4608
41 | 11127 | TL670 Mission to Clairemont Reconductor | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
42 | 11133 | TL664-Wood to Steel | 3190.1882 | 150 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 150
43 | 11138 | TL13804 Encina-Batiquitos-PQ-Wood to Steel | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
44 | 11142 | TL13835 and TL13837 UG Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
45 | 11143 | TL617 Direct Buried Cable Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
46 | 11146 | Ocotillo Express-Interconnect. Switchyard | 0.92725 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
47 | 11148 | TL626 Reconductor | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
48 | 11149 | CSolar-Generator Interconnection | -118.4014 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
49 | 11150 | Centinela-Generator Interconnection | -580.7936 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
50 | 11151 | TL694A Melrose Loop-In Project | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
51 | 11257 | Camp Pendleton 12kV Service | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
52 | 12125 | Sunnyside 69/12kV Rebuild | -4.3192 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
53 | 12126 | TL613-Direct Buried Cable Replace. | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
54 | 12127 | Pico Sub: Loop-In TL13833 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
55 | 12129 | Automated Fault Location | 167.8377 | 265 | 212 | 212 | 212 | 212 | 9 | 0 | 0 | [8 empty] | 1113
56 | 12130 | Composite Core Conductor | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
57 | 12132 | SCADA Expansion-Transmission | 0 | 3247.6725 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | [8 empty] | 3247.6725
58 | 12133 | Transmission ROW: Palos Verde-North Gila | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
59 | 12134 | Penasquitos-Add 230kV Capacitor Banks | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
60 | 12135 | TL629-E Reconductor | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 0
61 | 12138 | Direct Buried Cable Replace.: TL615 & 659 | 0 | 0 | 0 | 20750.968 | 480 | 0 | 6 | 9 | 0 | [5 empty] | 10615.484 |  |  | 10615.484
62 | 12139 | TL633-Overhead Reconductor | 0 | 0 | 14751.0122 | 0 | 0 | 0 | 1 | 0 | 0 | 14751.0122
63 | 12140 | Merchant Switchyard & Transmission | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
64 | 12142 | Campo Verde Solar-Generator Interconnect. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
65 | 12143 | TL23042 Outage Restoration | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
66 | 12144 | TL636-Wood to Steel | 0 | 0 | 0 | 819.6661 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 819.6661
67 | 12147 | TL628/643 Miguel Gateway Wood-to-Steel Proj | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
68 | 12149 | TL694-Wood to Steel | 0 | 6072.0015 | 336 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 6408.0015
69 | 12154 | TL631 Reconductor Project | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
70 | 12155 | Friars Sub Reliability Enhancement Project | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
71 | 12156 | TL600-Reliability Pole Replacements | 277.5578 | 1520 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | [8 empty] | 1520
72 | 12157 | Sycamore Canyon-Add 60 KV Reactor Banks | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
73 | 12158 | Pio Pico Energy Ctr. Gen. Interconnect | -21.4876 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
74 | 12159 | Aerial Marking For Safety | 7334.8533 | 9250 | 1200 | 1200 | 1200 | 1200 | 8 | 0 | 0 | [7 empty] | 14050
75 | 12160 | Transmission System Spares | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
76 | 13126 | Sta F Substation Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
77 | 13127 | Miguel Substation BK 80 Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
78 | 13128 | Sycamore-Penasquitos New 230KV TL | 0 | 113237.5553 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 56618.7776 |  |  |  | 56618.7776
79 | 13129 | 500 KV Series Capacitor-ECO Sub | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
80 | 13130 | TL674A Reconfigure/TL666D RFS | 0 | 0 | 11905.0553 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 11905.0553
81 | 13131 | Talega-Add Synchronous Condensers | 55.1141 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
82 | 13132 | SONGS Synchronous Condenser | 0 | 96205 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 96205
83 | 13133 | Shunt Reactor on Suncrest 500kV Bus | -74.4173 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
84 | 13134 | Talega Bank 50 Replacement | 202.5801 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
85 | 13136 | Wabash Substation Rebuild | -10.5094 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
86 | 13139 | CBM Gas Circuit Breakers | 0 | 0 | 0 | 0 | 10823.0693 | 0 | 6 | 0 | 0 | [5 empty] | 10823.0693
87 | 13140 | IV West Generator Interconnection (Q608) | -0.00024 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
88 | 13242 | Kearny 69/12KV Sub Rebuild/Reloc-Pre Eng | 0 | 9562.9159 | 80 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 9642.9159
89 | 13243 | New Vine 69/12KV Substation | 0 | 10725.4762 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 5362.7381 |  | 5362.7381
90 | 14125 | TL13815 Trans. Bridge Structure Reconfig | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
91 | 14127 | Imperial Valley Flow Controller | 10041.396 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
92 | 14128 | Artesian 230kV Expansion-Prel. Eng. | 0 | 0 | 0 | 49823.3295 | 588.2248 | 0 | 1 | 0 | 0 | 50411.5543
93 | 14129 | SONGS Station Light & Power | 0.43126 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
94 | 14130 | San Luis Rey Synchronous Condensers | 139713.3961 | 236.9748 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 118.4874 |  |  |  | 118.4874
95 | 14131 | Miguel 500kV Voltage Support | 20516.2968 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
96 | 14132 | Imperial Valley Sub Oper. Reliability & Security | 2005.7161 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0
97 | 14133 | TL628-Direct Buried Cable Replace. | 287.8146 | 520 | 278.4 | 1958.4 | 3052.8 | 0 | 6 | 0 | 0 | [5 empty] | 5809.6
98 | 14134 | Union Pacific RR Land Purchase | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
99 | 14137 | TL6975 Escondido - San Marcos | 0 | 0 | 0 | 16835.0749 | 0 | 0 | 1 | 0 | 0 | 16835.0749
100 | 14138 | TL13835 Wood to Steel | 0 | 2766.5169 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 1383.2585 | [6 empty] | 1383.2585
101 | 14140 | TL698 Wood to Steel Project | 0 | 428.5627 | 78.4 | 1800 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 2306.9627
102 | 14142 | Encina Bank 61 | 4.9888 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
103 | 14143 | Poway Substation Rebuild | 0 | 13330.6406 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 13330.6406
104 | 15126 | Sycamore Landfill Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
105 | 15128 | Silvergate Sub: Install Spare Transformer | 52.9951 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
106 | 15129 | Jacumba Solar Gen Interconnect (Q644A) | 2337.7442 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
107 | 15130 | Miguel Sub Hydro & Water Quality Enhance | 3509.4402 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
108 | 15132 | Mission Bank 71 Addition | 0 | 7845.6741 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 7845.6741
109 | 15133 | Tule Wind - Generator Interconnect | 597.5656 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
110 | 15246 | Rancho Santa Fe Sub Fire Hardening | 0 | 2416.8889 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 2416.8889
111 | 15258 | Mid-Coast Trolley Extension Project | 1516 | 0 | 1398 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 1398
112 | 16103 | San Mateo Substation Expansion | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
113 | 16127 | Cole Grade Rd 20A | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
114 | 16128 | Camp Pendleton Voltage Support | 4245.9128 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
115 | 16129 | TL678 Reloc for Lake Jennings Mkt Place | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
116 | 16130 | Warners Substation 69kV Control & Protection Replacement | 3316.9252 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
117 | 16131 | Descanso Substation 69kV Control & Protection Replacement | 3031.6913 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
118 | 16132 | TL690A | 0 | 5163.2806 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 2581.6403 | [6 empty] | 2581.6403
119 | 16133 | Substation Auxiliary Power System | 0 | 0 | 874.1839 | 0 | 0 | 0 | 9 | 0 | 0 | [8 empty] | 874.1839
120 | 16134 | Carlsbad Energy Center Project | 0 | 3186.0854 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 3186.0854
121 | 16137 | Vista Energy Storage Project | 0 | 246.7285 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 246.7285
122 | 16138 | Substation DC Reliability Upgrade Proj | 0 | 0 | 6602.82 | 0 | 0 | 0 | 1 | 0 | 0 | 6602.82
123 | 16143 | TL600: MESA HEIGHTS LOOP-IN + RECONDUCT - GRC | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
124 | 16144 | POWAY-POMERADO 69KV #2 - GRC | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
125 | 16145 | TL617-BALBOA AVE OVHD TO UG CONVERSION - GRC | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
126 | 16146 | TL638-COLE GRADE ROAD WIDENING - GRC | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
127 | 16147 | TL617-REMOVAL OF ROSE CANYON TAP - GRC | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
128 | 16148 | TL13834-TRABUCO-CAPISTRANO 138KV LINE - GRC | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
129 | 16150 | TL23001/04 SAN LUIS REY TO MISSION | 0 | 0 | 11788.9293 | 0 | 0 | 0 | 8 | 0 | 0 | [7 empty] | 11788.9293
130 | 16151 | TL660-CALTRAN I-5 WIDENING @ BIRMINGHAM | 0 | 12.5 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | [6 empty] | 12.5
131 | 16157 | MIGUEL TO BAY BLVD NEW 230KV LINE | 0 | 0 | 13645.4595 | 0 | 0 | 0 | 1 | 0 | 0 | 13645.4595
132 | 16158 | TL605 Reconductor: Silvergate - Urban | 0 | 0 | 0 | 282.9823 | 0 | 0 | 1 | 0 | 0 | 282.9823
133 | 16159 | HVDC Conversion of Southwest Powerlink | 0 | 0 | 1440.6202 | 0 | 0 | 0 | 4 | 0 | 0 |  |  |  | 1440.6202
134 | 16249 | Expedited Storage Procurement (ESP) | 96503 | 1494 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 1494
135 | 17125 | Granite Substation 69kV Loop-In | 0 | 0 | 0 | 5887.9314 | 5596.8 | 0 | 1 | 0 | 0 | 11484.7314
136 | 17126 | TL696 Winterhawk Customer Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
137 | 17127 | TL611 OLD TOWN - PT LOMA | 0 | 0 | 0 | 5394 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 5394
138 | 17129 | TL603B SWEETWATER TAP REMOVAL | 0 | 0 | 0 | 4310.2767 | 3993.6 | 0 | 1 | 0 | 0 | 8303.8767
139 | 17130 | BC14XXX (TL6906 MESA RIM LOOP-IN) | 0 | 0 | 6380 | 0 | 0 | 0 | 1 | 8 | 7 | 2126.6667 | [5 empty] | 2126.6667 | 2126.6667
140 | 17131 | TL628 Relocation - Nationa City CarMax | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
141 | 17132 | TL6943 UG CONV-GENESEE AVE BRIDGE | 3807.2108 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
142 | 17134 | TL6905 MIRAMESA COMMUNITY RELOCATION | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
143 | 17135 | TL674 QUAIL MEADOWS | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
144 | 17136 | TL23041-42-6910 OTAY VALLEY RESTORATION | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
145 | 17137 | TL660 STUB POLE RELOCATION | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
146 | 17139 | Substation 230kV Bus Rebuilds | 0 | 0 | 0 | 7660 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 7660
147 | 17142 | TL690 DB CABLE REPLACE (OSIDE-OSIDE TAP) | 0 | 0 | 0 | 0 | 5535.32 | 0 | 6 | 0 | 0 | [5 empty] | 5535.32
148 | 17143 | TL628 DB CALBE REPLACE (H ST & RANCHO DR) | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0
149 | 17144 | TL661/664 DB CABLE REPLACE (LUSK BLVD) | 0 | 0 | 0 | 0 | 913 | 0 | 6 | 0 | 0 | [5 empty] | 913
150 | 17145 | TL698 AVOCADO SUB GATEWAY DB CABLE REPLACE | 0 | 0 | 0 | 0 | 809 | 0 | 6 | 0 | 0 | [5 empty] | 809
151 | 17146 | TL693 SAN LUIS REY GATEWAY DB CABLE REPLACE | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
152 | 17147 | TL697 OCEANSIDE SUB GATWEAY DB CABLE REPLACE | 0 | 0 | 0 | 0 | 871.4167 | 0 | 6 | 0 | 0 | [5 empty] | 871.4167
153 | 17149 | 2ND 69KV LINE POMERADO TO POWAY | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
154 | 8165 | TL 629 DE-GC-CN SW Pole Replacements - CNF | 103405.7079 | 217212.6436 | 171028.7644 | 99802.5008 | 30 | 0 | 8 | 0 | 0 | [7 empty] | 488073.9087
155 | TBD02.0 | TL662/666 Torrey Pines Relibaility Project | 0 | 0 | 0 | 0 | 5670.9 | 0 | 1 | 0 | 0 | 5670.9
156 | TBD04.0 | TL673 DB Cable Repl (Rose Canyon to La Jolla) | 0 | 0 | 0 | 0 | 12021.45 | 0 | 6 | 0 | 0 | [5 empty] | 12021.45
157 | TBD06.0 | TL667 DB Cable Replacement (El Camino Real) | 0 | 0 | 0 | 0 | 9993 | 0 | 6 | 0 | 0 | [5 empty] | 9993
158 | TBD15.0 | TL13820 Reconductor (Chicarita - Sycamore) | 0 | 0 | 0 | 3490.65 | 5744 | 0 | 1 | 0 | 0 | 9234.65
159 | TBD20.0 | IV Bank 80 Replacement | 0 | 0 | 6240 | 0 | 0 | 0 | 6 | 0 | 0 | [5 empty] | 6240
160 | 17153 | Avocado Sub Rebuild | 0 | 0 | 4280 | 0 | 0 | 0 | 6 | 0 | 0 | [7 empty] | 4280
161 |  | TL6931 WTS (CNF) | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
162 |  | Basilone Substation 15 Mvar Capacitor | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
163 |  | Mission Bank #51 and #52 replacement | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0

## 2012_2017
Category | Total Spent | Percentage
1. Provide reliable service under peak load conditions. | 901739.9055 | 30.57%
2. Interconnect new generation. | 193720.379 | 6.567%
3. Interconnect new load. | 75781.804 | 2.569%
4. Improve grid efficiency (e.g., reduce Local Capacity Requirements, reduce congestion-related costs, reduce losses). | 104298.841 | 3.536%
5. Support public policy requirements or goals (e.g., Renewable Portfolio Standard (RPS) requirements). | 695592.557 | 23.58%
6. Upgrade, repair or replacement of existing facilities (e.g., adding spare transformer, replacing old direct-buried cable). | 285896.234 | 9.691%
7. Relocation or removal of facilities (e.g., under-grounding, accommodate third-party customer construction). | 234095.4285 | 7.935%
8. Customer and/or employee safety (e.g., fire-hardening). | 341139.0295 | 11.56%
9. Grid visibility, control and measurement. | 75361.1775 | 2.555%
10. Provide reliable service under conditions not driven by peak load. | 42417.916 | 1.438%
2950043.272

## 2015_2017
Category | Total Spent | Percentage
1. Provide reliable service under peak load conditions. | 548714.2925 | 37.18%
2. Interconnect new generation. | 103500.484 | 7.013%
3. Interconnect new load. | 32118.716 | 2.176%
4. Improve grid efficiency (e.g., reduce Local Capacity Requirements, reduce congestion-related costs, reduce losses). | 56913.0962 | 3.856%
5. Support public policy requirements or goals (e.g., Renewable Portfolio Standard (RPS) requirements). | 169718.5293 | 11.5%
6. Upgrade, repair or replacement of existing facilities (e.g., adding spare transformer, replacing old direct-buried cable). | 127955.47 | 8.67%
7. Relocation or removal of facilities (e.g., under-grounding, accommodate third-party customer construction). | 169164.081 | 11.46%
8. Customer and/or employee safety (e.g., fire-hardening). | 226748.1085 | 15.36%
9. Grid visibility, control and measurement. | 37827.6845 | 2.563%
10. Provide reliable service under conditions not driven by peak load. | 3247.241 | 0.22%
1475907.703

## 2018_2022
Category | 2018 thru 2022 Projections | Percentage
1. Provide reliable service under peak load conditions. | 523129.0971 | 34.87%
2. Interconnect new generation. | 4926.8139 | 0.3284%
3. Interconnect new load. | 5362.7381 | 0.3574%
4. Improve grid efficiency (e.g., reduce Local Capacity Requirements, reduce congestion-related costs, reduce losses). | 1440.6202 | 0.09602%
5. Support public policy requirements or goals (e.g., Renewable Portfolio Standard (RPS) requirements). | 58237.265 | 3.881%
6. Upgrade, repair or replacement of existing facilities (e.g., adding spare transformer, replacing old direct-buried cable). | 237863.7306 | 15.85%
7. Relocation or removal of facilities (e.g., under-grounding, accommodate third-party customer construction). | 29570.3338 | 1.971%
8. Customer and/or employee safety (e.g., fire-hardening). | 608572.884 | 40.56%
9. Grid visibility, control and measurement. | 31102.3403 | 2.073%
10. Provide reliable service under conditions not driven by peak load. | 186.5758 | 0.01244%
1500392.399

## Summary
Category | 2012 - 2017 | 2015 - 2017 | 2018 - 2022
1. Provide reliable service under peak load conditions. | 30.57% | 37.18% | 34.87%
2. Interconnect new generation. | 6.567% | 7.013% | 0.3284%
3. Interconnect new load. | 2.569% | 2.176% | 0.3574%
4. Improve grid efficiency (e.g., reduce Local Capacity Requirements, reduce congestion-related costs, reduce losses). | 3.536% | 3.856% | 0.09602%
5. Support public policy requirements or goals (e.g., Renewable Portfolio Standard (RPS) requirements). | 23.58% | 11.5% | 3.881%
6. Upgrade, repair or replacement of existing facilities (e.g., adding spare transformer, replacing old direct-buried cable). | 9.691% | 8.67% | 15.85%
7. Relocation or removal of facilities (e.g., under-grounding, accommodate third-party customer construction). | 7.935% | 11.46% | 1.971%
8. Customer and/or employee safety (e.g., fire-hardening). | 11.56% | 15.36% | 40.56%
9. Grid visibility, control and measurement. | 2.555% | 2.563% | 2.073%
10. Provide reliable service under conditions not driven by peak load. | 1.438% | 0.22% | 0.01244%

## TAB 4 Blanket Bdgts (actuals) (hidden)
Utility | SDG&E
|  | 2012 |  |  | 2013 |  |  | 2014 |  |  | 2015 |  |  | 2016 |  |  | January - August 2017 |  |  | TOTAL
Blanket Budget Code | Description of Blanket Budget Code | Aggregate Capital Spend on 2012 Work Orders ($) | Number of Work Orders (2012) | Average Capital Spend per WOA (2012) | Aggregate Capital Spend on 2013 Work Orders ($) | Number of Work Orders (2013) | Number of item x installed (2013) | Aggregate Capital Spend on 2014 Work Orders ($) | Number of Work Orders (2014) | Number of item x installed (2014) | Aggregate Capital Spend on 2015 Work Orders ($) | Number of Work Orders (2015) | Number of item x installed (2015) | Aggregate Capital Spend on 2016 Work Orders ($) | Number of Work Orders (2016) | Number of item x installed (2016) | Capital Spend on 2017 Work Orders ($) | Number of Work Orders (2017) | Number of item x installed (2017) | Capital Spend Total Work Orders ($)
004 | SONGS Units 2 & 3 | 41250233.82 | 119 | 346640.6203 | 16773147.25 | 109 | 153882.0849 | 3825409.6 | 21 | 182162.3619 | 698535.65 | 10 | 69853.565 | 1184.26 | 4 | 296.065 | -0.09 | 2 | -0.045 | 62548510.49
005 | SONGS Common Facilities | 4822529.72 | 25 | 192901.1888 | 6497059.25 | 20 | 324852.9625 | 2681604.98 | 6 | 446934.1633 | 1228423.7 | 2 | 614211.85 | -31690383.79 | 2 | -15845191.895 | -1157335.21 | 2 | -578667.605 | -17618101.35
006 | Generation Capital Tools & Test Eqpt. | 700879.26 | 3 | 233626.42 | 319755.21 | 3 | 106585.07 | -2301.04 | 2 | -1150.52 | 150330.8 | 2 | 75165.4 | 159086.58 | 2 | 79543.29 | 31861.93 | 2 | 15930.965 | 1359612.74
008 | Miramar Plant Operational Enhancements | 502064.43 | 13 | 38620.3408 | 1014408.74 | 14 | 72457.7671 | 11395605.45 | 6 | 1899267.575 | 41128.49 | 5 | 8225.698 | 148769.32 | 3 | 49589.7733 | 291541.87 | 2 | 145770.935 | 13393518.3
009 | Palomar Plant Operational Enhancements | 11661553.09 | 50 | 233231.0618 | 11716293.54 | 56 | 209219.5275 | 36453446.13 | 31 | 1175917.6171 | 3630448.68 | 27 | 134461.0622 | 12232597.57 | 20 | 611629.8785 | 4105848.57 | 12 | 342154.0475 | 79800187.58
010 | Desert Star Energy Center Operational Enhancements | 2097320.11 | 31 | 67655.4874 | 5594494.72 | 48 | 116551.9733 | 8913575.74 | 16 | 557098.4838 | 1640148.71 | 16 | 102509.2944 | 3546972.69 | 8 | 443371.5862 | 1749634.36 | 14 | 124973.8829 | 23542146.33
011 | Cuyamaca Peak Energy Plant Oper. Enhancements | 226186.62 | 4 | 56546.655 | 243280.94 | 7 | 34754.42 | 3404.13 | 2 | 1702.065 | 642423.95 | 2 | 321211.975 | 4949020.21 | 5 | 989804.042 | 3784341.59 | 6 | 630723.5983 | 9848657.44
100 | Electric Transmission Line Reliability Projects | 19922071.02 | 521 | 38238.1402 | 14533837.51 | 397 | 36609.1625 | 15299130.36 | 462 | 33115.0008 | 19684246.14 | 544 | 36184.276 | 32955476.32 | 669 | 49260.8017 | 29892066.69 | 818 | 36542.8688 | 132286828.04
102 | Electric Transmission Line Relocation Projects | -1313570.52 | 33 | -39805.1673 | 895909.62 | 26 | 34458.0623 | 228343.1 | 22 | 10379.2318 | -596141.49 | 13 | -45857.0377 | 1026117.45 | 18 | 57006.525 | 336872.8 | 12 | 28072.7333 | 577530.96
103 | Transmission Substation Reliability | 2777576.43 | 20 | 138878.8215 | 1138542.4 | 32 | 35579.45 | 2411155.19 | 29 | 83143.2824 | 2907435.88 | 20 | 145371.794 | 3153284.64 | 39 | 80853.4523 | 4362631.69 | 36 | 121184.2136 | 16750626.23
104 | Renewal Of Transmission Line Easements | 974901.78 | 12 | 81241.815 | -623153.35 | 6 | -103858.8917 | 305208.76 | 6 | 50868.1267 | 19356.13 | 4 | 4839.0325 | 4119545.45 | 3 | 1373181.8167 | 6031.99 | 2 | 3015.995 | 4801890.76
105 | Electric Trans. Street & Highway Relocations | 1319503.55 | 15 | 87966.9033 | 255005.48 | 11 | 23182.3164 | -1969498.91 | 16 | -123093.6819 | 136243.52 | 20 | 6812.176 | 1154238.25 | 14 | 82445.5893 | 526913.22 | 12 | 43909.435 | 1422405.11
106 | Electric Transmission Tools & Equipment | 262628.77 | 1 | 262628.77 | 152264.14 | 1 | 152264.14 | 298241.98 | 1 | 298241.98 | 330941.31 | 1 | 330941.31 | 309462.46 | 1 | 309462.46 | 273206.19 | 1 | 273206.19 | 1626744.85
112 | Environmental Capital Permit Compliance | 6724152.11 | 1 | 6724152.11 | -5666639.15 | 2 | -2833319.575 | 224348.66 | 2 | 112174.33 | 123331.94 | 2 | 61665.97 | 315.42 | 1 | 315.42 | 14273.69 | 1 | 14273.69 | 1419782.67
1145 | Transmission Infrastructure Improvements | 14393661.47 | 69 | 208603.7894 | 5630413.75 | 76 | 74084.3914 | 12727987.52 | 96 | 132583.2033 | 10456432.9 | 115 | 90925.5035 | 12395419.18 | 104 | 119186.7229 | 6090261.54 | 100 | 60902.6154 | 61694176.36
3171 | Transmission System Automation | 2296306.47 | 32 | 71759.5772 | 1432063.66 | 44 | 32546.9014 | 1082192.28 | 24 | 45091.345 | 1662748.88 | 26 | 63951.88 | 2193629.09 | 11 | 199420.8264 | 1130907.84 | 10 | 113090.784 | 9797848.22
6254 | Emergency Transformer & Switchgear | 1275461.58 | 6 | 212576.93 | 5722162.95 | 11 | 520196.6318 | 1930249.17 | 8 | 241281.1462 | 1044662.72 | 10 | 104466.272 | 5791951.11 | 6 | 965325.185 | 3874138.62 | 5 | 774827.724 | 19638626.15
07144 | Fiber Optic for Relay Protection & Telecommunication | 5969327.67 | 127 | 47002.5801 | 6923934.34 | 126 | 54951.8598 | 6111826.88 | 115 | 53146.3207 | 4132981.92 | 107 | 38625.9993 | 3143185.3 | 98 | 32073.3194 | 5023229.37 | 106 | 47388.9563 | 31304485.48
08165 | TL 629 DE-GC-CN SW Pole Replacements | 1124964.94 | 1 | 1124964.94 | -1619564.35 | 2 | -809782.175 | 4175179.34 | 14 | 298227.0957 | 9897738.99 | 22 | 449897.2268 | 84800132.3 | 48 | 1766669.4229 | 85020731.79 | 65 | 1308011.2583 | 183399183.01
09144 | OpEx 20/20 CBM Transmission Sub. | 175944.21 | 10 | 17594.421 | 2122454.98 | 10 | 212245.498 | 986320.49 | 19 | 51911.6047 | 537265.63 | 20 | 26863.2815 | 748289.61 | 14 | 53449.2579 | 669237.85 | 14 | 47802.7036 | 5239512.77
09153 | TL676 Mission to Mesa Heights Reconductor | 148871.78 | 1 | 148871.78 | 142084.44 | 1 | 142084.44 | 388900.43 | 1 | 388900.43 | 678756.65 | 3 | 226252.2167 | 1907460.47 | 4 | 476865.1175 | 1015502.62 | 4 | 253875.655 | 4281576.39
15125 | Critical Asset Security | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12215504.41 | 10 | 1221550.441 | 6575815.05 | 14 | 469701.075 | 5855130.01 | 18 | 325285.0006 | 24646449.47
16126 | Substation Security Proj Under $500k | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4425241.59 | 16 | 276577.5994 | 2108319.04 | 17 | 124018.7671 | 6533560.63
99128 | Transmission Ceramic Insulator Replacement | 1018220.25 | 2 | 509110.125 | 77338.98 | 3 | 25779.66 | 296231.78 | 3 | 98743.9267 | 147079.55 | 2 | 73539.775 | 419.21 | 1 | 419.21 | 58.68 | 1 | 58.68 | 1539348.45

## Tab 5 Blanket Bdgts (projected) (hidden)
CONFIDENTIAL
Line | Budget Code | Budget Code Name | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
1 | 100 | Electric Transmission Line Reliability Projects - 1999 - Total | 33810.8531 | 23000 | 19520 | 21520 | 23520 | 11520
2 | 102 | Electric Transmission Line Relocation Projects - Total | 380.0422 | 200 | 0 | 0 | 0 | 0
3 | 103 | Transmission Substation Reliability Projects - 1999 - Total | 4546.0833 | 2086 | 1844.8 | 2000 | 2000 | 2160
4 | 104 | Renewal of Electric Transmission Line Easements - Total | 100 | 1000 | 16000 | 640 | 640 | 640
5 | 105 | Governmental Electric Transmission Line Relocations. | 1378.2181 | 630 | 480 | 480 | 480 | 480
6 | 106 | Electric Transmission Tools & Equipment - Total | 353.4414 | 0 | 0 | 0 | 0 | 0
10 | 203.1 | Distribution Substation Reliability Projects - Total | -9.7374 | 0 | 0 | 0 | 0 | 0
11 | 1145 | Transmission Obsolete Equipment | 7738.9965 | 3700 | 2160 | 2160 | 2160 | 2160
12 | 3171 | System Automation | 1169.6475 | 2000 | 1600 | 1600 | 1600 | 1600
13 | 6254.1 | Emergency Equipment Purchase | 5072.5592 | 600 | 160 | 160 | 160 | 160
14 | 7144 | Fiber Optics | 7533.1969 | 8515 | 6774.8 | 5222.8 | 5341.6 | 5200.4
85 | 9144 | CBM 09144 | 0 | 1015.2209 | 0 | 0 | 0 | 0
76 | 14243.1 | Borrego Springs Microgrid 2.0 | 0 | 3.7996 | 0 | 0 | 0 | 0
72 | 15258.1 | Mid-Coast Trolley | 1516 | 0 | 1398
9 | 16126 | Substation Security Installations | 2236.7305 | 1290 | 1032 | 1032 | 1032 | 1032
53 | 16249.1 | Expedited Storage Procurement (ESP) | 2369.1467 | 0 | 0 | 0 | 0 | 0
94 | TBD37.0 | Down Town Land Purchase | 0 | 0 | 0 | 0 | 0 | 0
Note on C16: Aldrich, Daniel: ISD $'s include CWIP Balance
Note on E19: Aldrich, Daniel: This version reflects the removal of $30M for the downtown land purchase in 2018 per VP decision

## Tab 6 Lookup Table for Rev.Req. (hidden)
Rate Effective Period | Rev.Req. Allocation Factor | Revenue Requirement | Gross Transmission Plant ($M) | Cycle Filing | FERC Docket No.
2011-09-01 | 24.81% | 402.243 | 1621.48 | TO3 - Cycle 5 | ER11-4318-000; 001; 002
2012-09-01 | 35.22% | 609.716 | 1731.133 | TO3 - Cycle 6 | ER-2454-000; 001; 002
2013-09-01 | 30.34% | 541.698 | 1785.183 | TO4 - Cycle 1 | ER13-941-001
2014-08-01 | 32.61% | 582.184 | 1785.183 | TO4 - Cycle 1 (OOC Filing) | ER14-2252-000
2015-08-01 | 20.42% | 745.843 | 3652.963 | TO4 - Cycle 2 | ER15-553-000
2016-01-01 | 18.1% | 716.366 | 3958.529 | TO4 - Cycle 3 | ER16-445-000
2017-01-01 | 17.17% | 785.262 | 4574.358 | TO4 - Cycle 4 | ER17-470-000
* This tab is used to create a formula to calculate the revenue requirement percentage. Please see narrative for details.